## Constraints
Order # | Project Name | Bio Constraints | Cultural Constraints | EFS Constraints | Notes
35217268 | SH - BUCKS CREEK 1101 CB | 1. There is California red-legged frog and Foothill yellow-legged frog MRHCP modeled habitat within the project area, no constraints as long as species-specific AMMs are implemented. Could require work during the dry season (May 15 - Oct 15) and/or biomonitoring. 2. There are two spotted owl activity centers within the vicinity. They are outside of visual/auditory harassment zone. Potential Heli restrictions Feb 2- July 15 3. There are multiple water crossings. Potential Permitting* | Entire Project: Project activities within the Caltrans ROW will require a Caltrans Encroachment Permit. Upon review by Caltrans, additional cultural resource protection measures may be required. Native American consultation will be required and possible tribal monitoring/archaeological monitoring. Added cost and 30 Days to ERTC timeline. Alternative 2: The UG portion passes through an ESA and would require monitoring, testing, and/or mitigation. It is strongly recommended that this alternative be avoided. | No Constraints | 4.8 miles
35217272 | SH - KESWICK 1101 LR 1586 | 1. There is California red-legged frog and Foothill yellow-legged frog MRHCP modeled habitat within the project area, no constraints as long as species-specific AMMs are implemented. Could require work during the dry season (May 15 - Oct 15) and/or biomonitoring. 2. There are multiple water crossings. Potential Permitting* | Entire Project: Numerous cultural resources within the project area. Cost: Fieldwork will include monitoring on portions of OH and all UG. Site record updates (esp. BLM land) and survey of access routes. Field work is anticipated to take at least 5-6 weeks. | No Constraints | 7.45 miles
35217273 | SH - UPPER LAKE 1101 CB | 1. Abundant stock ponds with potential suitable habitat for tricolored blackbird are found within the project vicinity. Many locations are within the standard buffer of 350 feet of suitable nesting habitat (nesting March 1 – August 15). Potential for nesting bird surveys depending on scope of work within areas adjacent to stock ponds. 2. There are 3 waterway crossings and 10 potential* water crossings. Potential Permitting* | Entire Project: Project activities within the Caltrans ROW will require a Caltrans Encroachment Permit. Upon review by Caltrans, additional cultural resource protection measures may be required. Preferred OH/RG (as designed): Cost: fieldwork will include monitoring on portions of OH, anticipated to take 1-2 weeks. Alternative 1: Cost: fieldwork will include monitoring on additional portions of UG, anticipated to take 1-2 weeks Alternative 2: Cost: fieldwork will include monitoring all UG portions, anticipated to take 3-6 weeks Alternative 3: Native American consultation will be required and possible tribal monitoring/archaeological monitoring. Added cost and 30 Days to ERTC timeline Proposed alternative route poses risk for encountering human remains, if found would cause significant delays. Cost: Fieldwork will include monitoring all OH + UG portions, anticipated to take 1-2 months | No Constraints | 1.11 miles
35217270 | SH - KONOCTI 1102 LR 965078 | 1. There is California red-legged frog MRHCP modeled habitat within the project area, no constraints as long as species-specific AMMs are implemented. Could require work during the dry season (May 15 - Oct 15) and/or biomonitoring. Mitigation expenses should be considered for undergrounding portions within modeled habitat. Roughly 23cents/sqft. 2. A portion of the project appears to be within a vernal pool/wetland. VERY HIGH RISK FOR PERMITTING. CONTACT BIOLOGIST NICK BURTON TO ASSIST IN FIELD SCOPING. 3. There are 6 waterway crossings. Potential Permitting* | Entire Project: Project activities within the Caltrans ROW will require a Caltrans Encroachment Permit. Upon review by Caltrans, additional cultural resource protection measures may be required. Preferred OH/+UG (as designed) Cost: fieldwork will include monitoring on portions of OH and UG, anticipated to take 2 weeks. Alternative 1: Cost: fieldwork will include monitoring on additional portions of UG, anticipated to take 3 weeks Alternative 2: Cost: fieldwork will include monitoring all UG portions, anticipated to take 6-8 weeks | Cost Constraint Two contaminated sites but one is completed-case closed. Other contaminated site requires EFS fieldwork/sampling. | 6.27 miles
* Aquatic Features = For overhead, ensure no poles are located within the riparian area or waterways to avoid permit triggers. For undergrounding, need to ensure that there is no excavation within the bed, bank, or channel of the waterways. If HDD is utilized, ensure that entry/exit pits are outside of the riparian zone. No constraints if designed properly.