## Sheet1
Order No | Order Description | MAT | Division | Phase Number | User Status | Curr Status Date | UNSE In | UNSE Out | ESTS In | ESTS Out | ADER In | ADER Out | PEND In | PEND Out | UNSC In | UNSC Out | CONS In | CONS Out | DOCC In | DOCC Out | DCNL In | DCNL Out | MAPP In | MAPP Out | FICL In | FICL Out | CLSD In | CLSD Out | CNCL In | CNCL Out | CPND In | CPND Out
30948153 | OC2 REPLACE #6CU WITH 4AR, VASONA 1103 | 08W | DA | Completion | ECES_CA1/CLSD | 12/13/2015 | 09/12/2012 | 09/24/2012 | 09/24/2012 | 12/10/2012 | 12/29/2012 | 12/29/2012 | 04/02/2013 | 07/12/2013 | 07/12/2013 | 08/27/2013 | 08/27/2013 | 10/08/2013 | 10/08/2013 | 12/06/2013 | 12/06/2013 | 12/13/2013 | 12/13/2013 | 01/15/2014 | 01/15/2014 | 12/10/2015 | 12/13/2015 | 12/31/9999
30949571 | OC4 GRN VALLEY 2103 WIRE DOWN NEAR 1993 | 08W | CC | Completion | ECES_CA1/CLSD | 03/19/2016 | 09/20/2012 | 08/27/2013 | 08/27/2013 | 09/17/2013 | 09/17/2013 | 10/10/2013 | 12/04/2013 | 12/06/2013 | 12/06/2013 | 01/13/2014 | 01/13/2014 | 03/10/2014 | 03/10/2014 | 03/31/2014 | 03/31/2014 | 04/09/2014 | 04/09/2014 | 04/29/2014 | 04/29/2014 | 03/18/2016 | 03/19/2016 | 12/31/9999
30951870 | 2014 MALAGA 1102 RECONDUCTOR CENTRAL | 08W | FR | Completion | ECES_CA1/CLSD | 11/14/2015 | 10/01/2012 | 10/29/2012 | 10/29/2012 | 12/04/2012 | 12/04/2012 | 01/17/2013 | 01/31/2013 | 07/12/2013 | 07/12/2013 | 07/26/2013 | 07/26/2013 | 03/18/2014 | 03/18/2014 | 04/11/2014 | 04/11/2014 | 04/18/2014 | 04/18/2014 | 10/14/2015 | 10/14/2015 | 11/13/2015 | 11/14/2015 | 12/31/9999
30951871 | OC4 2014 MALAGA 1102 RECONDUCTOR AMERICA | 08W | FR | Completion | ECES_CA1/CLSD | 07/12/2014 | 10/01/2012 | 10/29/2012 | 10/29/2012 | 12/04/2012 | 12/04/2012 | 01/17/2013 | 01/31/2013 | 07/12/2013 | 07/12/2013 | 07/26/2013 | 07/26/2013 | 03/22/2014 | 03/22/2014 | 04/11/2014 | 04/11/2014 | 04/18/2014 | 04/18/2014 | 07/02/2014 | 07/02/2014 | 07/09/2014 | 07/12/2014 | 12/31/9999
30951993 | OC4 XSPRING VALLEY ROAD WIRE REPLACEMENT | 08W | CC | Completion | ECES_CA1/CLSD | 03/19/2016 | 10/02/2012 | 07/31/2013 | 08/22/2013 | 08/29/2013 | 08/29/2013 | 09/05/2013 | 09/10/2013 | 10/01/2013 | 10/01/2013 | 03/10/2014 | 03/10/2014 | 04/17/2014 | 04/17/2014 | 05/19/2014 | 05/19/2014 | 05/30/2014 | 05/30/2014 | 03/18/2016 |  |  | 03/19/2016 | 12/31/9999
30965813 | OC4 +MESA 1102 WIREDOWN - C/O 8953 | 08W | LP | Completion | ECES_CA1/CLSD | 12/13/2014 | 12/12/2012 | 02/27/2014 | 02/27/2014 | 03/26/2014 | 04/25/2014 | 05/01/2014 | 06/20/2014 | 07/01/2014 | 07/01/2014 | 08/27/2014 | 08/27/2014 | 10/06/2014 | 10/06/2014 | 10/21/2014 | 10/21/2014 | 10/30/2014 | 10/30/2014 | 11/04/2014 | 11/04/2014 | 12/05/2014 | 12/13/2014 | 12/31/9999
30967034 | OC4 LINE DOWN - DAVIS 1107 RECON-REFRAME | 08W | SA | Completion | ECES_CA1/CLSD | 01/31/2015 | 12/20/2012 | 01/18/2013 | 01/18/2013 | 03/07/2013 | 03/07/2013 | 03/25/2013 | 03/25/2013 | 03/27/2013 | 03/27/2013 | 12/31/2013 | 12/31/2013 | 01/17/2014 | 10/29/2014 | 01/29/2015 |  |  | 02/24/2014 | 04/10/2014 | 04/10/2014 | 05/05/2014 | 01/31/2015 | 12/31/9999
30968294 | OC2 2013, BAKERSFIELD 2104, RE-CONDUCTOR | 08W | KE | Completion | ECES_CA1/CLSD | 10/13/2014 | 12/28/2012 | 07/08/2013 | 07/08/2013 | 08/16/2013 | 08/16/2013 | 08/23/2013 | 08/23/2013 | 12/26/2013 | 12/26/2013 | 02/21/2014 | 02/21/2014 | 04/01/2014 | 04/01/2014 | 04/28/2014 | 04/28/2014 | 05/10/2014 | 05/10/2014 | 06/19/2014 | 06/19/2014 | 10/10/2014 | 10/13/2014 | 10/13/2014
30971722 | OC4RECNDUCT 2 SP OF WIRE @ MAPLE & CEDAR | 08W | CC | Completion | ECES_CA1/CLSD | 04/09/2016 | 01/16/2013 | 10/31/2013 | 02/19/2014 | 02/28/2014 | 02/28/2014 | 03/27/2014 | 03/31/2014 | 03/31/2014 | 03/31/2014 | 08/27/2014 | 08/27/2014 | 09/17/2014 | 09/17/2014 | 09/26/2014 | 09/26/2014 | 10/09/2014 | 10/09/2014 | 10/13/2014 | 10/13/2014 | 04/05/2016 | 04/09/2016 | 12/31/9999
30971802 | OC4 RECONDUCTOR INST FUSES VACA DIXON 11 | 08W | SA | Completion | ECES_CA1/CLSD | 01/05/2015 | 01/17/2013 | 02/04/2013 | 02/04/2013 | 03/13/2013 | 03/13/2013 | 03/25/2013 | 03/25/2013 | 03/27/2013 | 03/27/2013 | 12/31/2013 | 12/31/2013 | 01/31/2014 | 10/28/2014 | 12/05/2014 | 01/31/2014 | 02/07/2014 | 02/07/2014 | 05/02/2014 | 05/02/2014 | 06/12/2014 | 01/05/2015 | 12/31/9999
30972334 | OP-1101 RECOND_SAN PABLO & O'HATCH (R) | 08W | EB | Completion | ECES_CA1/CLSD | 09/28/2019 | 01/25/2013 | 08/12/2013 | 08/12/2013 | 09/03/2013 | 09/03/2013 | 09/24/2013 | 12/07/2014 | 01/05/2015 | 06/05/2014 | 12/07/2014 | 01/05/2015 | 04/02/2015 | 08/22/2019 | 09/26/2019 |  |  | 05/01/2015 | 05/15/2015 | 09/26/2019 | 09/26/2019 | 09/28/2019 | 12/31/9999
30972547 | OCGC XDEL MONTE 2104 RECOND PORTOLA WD | 08W | CC | Completion | ECES_CA2/CLSD | 10/18/2015 | 01/22/2013 | 03/14/2014 | 03/14/2014 | 03/31/2014 | 03/31/2014 | 04/30/2014 | 04/30/2014 | 06/19/2014 | 06/19/2014 | 06/30/2014 | 06/30/2014 | 10/29/2014 | 10/29/2014 | 11/03/2014 |  |  | 11/03/2014 | 11/19/2014 | 11/19/2014 | 10/16/2015 | 10/18/2015 | 12/31/9999
30972642 | WIREDOWN-RECOND-KERN OIL 1116 | 08W | KE | Completion | ECES_CA1/CLSD | 10/17/2015 | 01/23/2013 | 12/24/2013 | 12/24/2013 | 12/28/2013 | 12/28/2013 | 01/03/2014 | 01/04/2014 | 01/04/2014 | 01/04/2014 | 07/16/2014 | 07/16/2014 | 08/20/2014 | 08/20/2014 | 09/05/2014 |  |  | 09/05/2014 | 11/25/2014 | 11/25/2014 | 10/16/2015 | 10/17/2015 | 12/31/9999
30974004 | OC4 DIXON 1103 RECONDUCTOR | 08W | SA | Completion | ECES_CA1/CLSD | 10/15/2016 | 01/29/2013 | 07/03/2013 | 07/03/2013 | 08/16/2013 | 08/16/2013 | 08/22/2013 | 08/23/2013 | 01/09/2014 | 01/09/2014 | 07/14/2014 | 07/14/2014 | 10/30/2014 | 10/30/2014 | 11/07/2014 | 11/07/2014 | 12/01/2014 | 12/01/2014 | 12/20/2014 | 12/20/2014 | 10/12/2016 | 10/15/2016 | 12/31/9999
30974166 | +SLO 1107 WIREDOWN (BOB JONES TRAIL) | 08W | LP | Completion | ECES_CA1/CLSD | 09/03/2016 | 01/30/2013 | 02/25/2014 | 02/25/2014 | 05/14/2014 | 05/28/2014 | 05/28/2014 | 08/12/2014 | 08/20/2015 | 08/20/2015 | 10/01/2015 | 10/01/2015 | 12/04/2015 | 07/01/2016 | 08/31/2016 | 05/27/2014 | 05/28/2014 | 04/14/2016 | 06/20/2016 | 06/20/2016 | 06/22/2016 | 09/03/2016 | 12/31/9999
30974168 | OC4 LLAGAS 2101 RECONDUCTOR 4 SPANS | 08W | SJ | Completion | ECES_CA1/CLSD | 04/09/2016 | 01/30/2013 | 08/08/2013 | 08/08/2013 | 09/04/2013 | 09/04/2013 | 10/02/2013 | 11/13/2013 | 11/20/2013 | 11/20/2013 | 04/10/2014 | 04/10/2014 | 07/31/2014 | 03/17/2016 | 03/17/2016 | 08/26/2014 | 09/08/2014 | 09/08/2014 | 09/25/2014 | 03/17/2016 | 04/05/2016 | 04/09/2016 | 12/31/9999
30974722 | OC4 DEL MONTE 2102 ELM WIREDWN RECONDUCT | 08W | CC | Completion | ECES_CA1/CLSD | 12/10/2016 | 02/01/2013 | 08/28/2013 | 08/28/2013 | 10/02/2013 | 10/02/2013 | 10/17/2013 | 10/22/2013 | 03/10/2014 | 03/10/2014 | 05/26/2014 | 05/26/2014 | 08/01/2014 | 08/01/2014 | 09/11/2014 | 09/11/2014 | 10/17/2016 | 10/17/2016 | 12/01/2016 | 12/01/2016 | 12/08/2016 | 12/10/2016 | 12/31/9999
30974723 | OCGC DEL MONTE 2105 VAN BURN WIRE RECON | 08W | CC | Completion | ECES_CA1/CLSD | 04/23/2016 | 02/01/2013 | 09/09/2013 | 09/09/2013 | 10/25/2013 | 10/25/2013 | 10/25/2013 | 11/14/2013 | 01/07/2014 | 01/07/2014 | 02/03/2014 | 02/03/2014 | 12/03/2014 | 12/03/2014 | 04/20/2016 | [6 empty] | 04/23/2016 | 12/31/9999
30974724 | OCGC DEL MNTE 2104 RECTR CORRAL TIERRA | 08W | CC | Completion | ECES_CA1/CLSD | 12/26/2015 | 02/01/2013 | 10/31/2013 | 10/31/2013 | 01/10/2014 | 01/10/2014 | 01/28/2014 | 01/28/2014 | 01/28/2014 | 01/28/2014 | 03/27/2014 | 03/27/2014 | 12/19/2014 | 12/19/2014 | 12/27/2014 |  |  | 12/27/2014 | 12/29/2014 | 12/29/2014 | 12/21/2015 | 12/26/2015 | 12/31/9999
30974733 | OC2 XREPL COND, BEACH ROAD @ PALM BEACH | 08W | CC | Completion | ECES_CA1/CLSD | 04/11/2015 | 02/01/2013 | 08/12/2013 | 08/12/2013 | 09/03/2013 | 09/03/2013 | 09/11/2013 | 09/15/2013 | 09/18/2013 | 09/18/2013 | 02/27/2014 | 02/27/2014 | 03/28/2014 | 12/11/2014 | 04/08/2015 | 04/24/2014 | 05/06/2014 | 05/06/2014 | 05/22/2014 | 05/22/2014 | 07/01/2014 | 04/11/2015 | 12/31/9999
30975188 | OCGC+SLO 1103 WD @ 14125 - 12-70838 | 08W | LP | Completion | ECES_CA1/CLSD | 06/13/2015 | 02/04/2013 | 03/03/2014 | 03/03/2014 | 04/02/2014 | 04/02/2014 | 05/07/2014 | 05/09/2014 | 05/14/2014 | 05/14/2014 | 10/16/2014 | 10/16/2014 | 03/10/2015 | 03/10/2015 | 03/11/2015 |  |  | 03/11/2015 | 05/16/2015 | 05/16/2015 | 06/10/2015 | 06/13/2015 | 12/31/9999
30975601 | NEWARK 2103 CKT - RECONDUCTOR OH | 08W | MI | Completion | ECES_CA1/CLSD | 01/17/2015 | 02/06/2013 | 09/02/2013 | 09/17/2013 | 10/01/2013 | 10/01/2013 | 10/07/2013 | 10/10/2013 | 01/02/2014 | 01/02/2014 | 03/17/2014 | 03/17/2014 | 04/03/2014 | 04/03/2014 | 04/11/2014 |  |  | 04/11/2014 | 05/14/2014 | 12/08/2014 | 01/12/2015 | 01/17/2015 | 12/31/9999
30975805 | OCGC XINDUSTRIAL WY ANNEALED COND,KC1102 | 08W | CC | Completion | ECES_CA1/CLSD | 12/26/2015 | 02/06/2013 | 03/31/2014 | 03/31/2014 | 04/21/2014 | 04/21/2014 | 05/02/2014 | 05/02/2014 | 05/09/2014 | 05/09/2014 | 11/10/2014 | 11/10/2014 | 01/14/2015 | 01/14/2015 | 01/15/2015 |  |  | 01/15/2015 | 01/23/2015 | 01/23/2015 | 12/21/2015 | 12/26/2015 | 12/31/9999
30976210 | OC4 WIREDOWN-RECOND-ELK HILLS 1106 | 08W | KE | Completion | ECES_CA1/CLSD | 04/11/2015 | 02/08/2013 | 04/01/2013 | 04/01/2013 | 04/05/2013 | 04/05/2013 | 06/06/2013 | 07/17/2013 | 10/02/2013 | 10/02/2013 | 03/18/2014 | 03/18/2014 | 04/01/2014 | 04/01/2014 | 05/05/2014 | 05/05/2014 | 05/26/2014 | 05/26/2014 | 12/19/2014 | 12/19/2014 | 04/06/2015 | 04/11/2015 | 12/31/9999
30977168 | OC4 OCGC FRNCH CMP 1102 RECOND & RELOCA | 08W | ST | Completion | ECES_CA1/CLSD | 02/20/2016 | 02/13/2013 | 10/25/2013 | 10/25/2013 | 12/23/2013 | 12/23/2013 | 01/11/2014 | 02/13/2014 | 02/24/2014 | 03/17/2014 | 04/28/2014 | 04/28/2014 | 09/25/2014 | 09/25/2014 | 01/06/2015 | 01/06/2015 | 01/15/2015 | 01/15/2015 | 01/21/2016 | 01/21/2016 | 02/17/2016 | 02/20/2016 | 12/31/9999
30977613 | WDDB OTTER 1102 PHASE 3 | 08W | CC | Pending | ECES_CA1/PEND | 02/28/2019 | 05/17/2017 | 09/26/2018 | 09/26/2018 | 09/26/2018 | 09/26/2018 | 02/20/2019 | 02/28/2019 | 12/31/9999 | [6 empty] | 05/01/2017 | 05/17/2017
30977614 | WDDB OTTER 1102 PHASE 4 | 08W | CC | Pre-Construction | ECES_CA1/UNSC | 12/05/2019 | 04/18/2017 | 09/28/2018 | 09/28/2018 | 09/28/2018 | 09/28/2018 | 02/18/2019 | 02/28/2019 | 12/05/2019 | 12/05/2019 | 12/31/9999 |  |  |  |  | 04/03/2017 | 04/18/2017
30977615 | WDDB OTTER 1102 PHASE 5 | 08W | CC | Pre-Construction | ECES_CA1/UNSC | 12/06/2019 | 02/14/2018 | 06/13/2018 | 01/10/2019 | 02/07/2019 | 06/13/2018 | 08/14/2018 | 12/06/2019 | 12/06/2019 | 12/06/2019 | 12/06/2019 |  |  |  |  | 01/13/2018 | 02/14/2018
30978199 | OC4 HMB1102 CO5905 RECONDUCTOR 470 FT | 08W | PN | Completion | ECES_CA1/CLSD | 02/14/2015 | 10/08/2013 | 01/09/2014 | 01/09/2014 | 01/29/2014 | 01/29/2014 | 02/18/2014 | 02/21/2014 | 04/22/2014 | 04/22/2014 | 06/11/2014 | 06/11/2014 | 07/16/2014 | 10/02/2014 | 10/30/2014 | 10/30/2014 | 11/25/2014 | 11/25/2014 | 12/26/2014 | 12/26/2014 | 02/12/2015 | 02/14/2015 | 12/31/9999
30978886 | OCGC RECONDUCTOR TO REMOVE SPLICES | 08W | DA | Completion | ECES_CA1/CLSD | 12/26/2015 | 02/22/2013 | 03/18/2014 | 03/18/2014 | 04/24/2014 | 04/24/2014 | 05/01/2014 | 06/24/2014 | 09/25/2014 | 09/25/2014 | 12/29/2014 | 12/29/2014 | 05/21/2015 | 05/21/2015 | 05/28/2015 | 06/17/2014 | 06/24/2014 | 05/28/2015 | 08/12/2015 | 08/12/2015 | 12/21/2015 | 12/26/2015 | 12/31/9999
30979240 | OCGC XRECON 4 SPS OF WR GLEENWOOD-CE2106 | 08W | CC | Completion | ECES_CA1/CLSD | 12/13/2015 | 02/24/2013 | 02/24/2014 | 04/30/2014 | 05/01/2014 | 05/01/2014 | 05/11/2014 | 06/12/2014 | 07/17/2014 | 07/17/2014 | 11/24/2014 | 11/24/2014 | 02/25/2015 | 02/25/2015 | 03/05/2015 | 05/26/2014 | 06/12/2014 | 03/05/2015 | 03/17/2015 | 03/17/2015 | 12/07/2015 | 12/13/2015 | 12/31/9999
30979241 | OCGC XRECON 2 SPN@GRNITE CRK/HWY17 S VLY | 08W | CC | Completion | ECES_CA1/CLSD | 10/17/2015 | 02/24/2013 | 10/31/2013 | 02/19/2014 | 02/28/2014 | 02/28/2014 | 03/28/2014 | 03/31/2014 | 07/01/2014 | 07/01/2014 | 09/04/2014 | 09/04/2014 | 11/22/2014 | 12/21/2014 | 12/21/2014 | 01/30/2014 | 02/19/2014 | 12/03/2014 | 12/19/2014 | 12/21/2014 | 10/16/2015 | 10/17/2015 | 12/31/9999
30979379 | +RECNDUCTR TO REMOVE SPLICES VASONA 110 | 08W | DA | Completion | ECES_CA1/CLSD | 05/14/2016 | 02/25/2013 | 02/27/2014 | 02/27/2014 | 03/24/2014 | 03/24/2014 | 04/14/2014 | 04/14/2014 | 06/04/2014 | 06/04/2014 | 06/17/2014 | 06/17/2014 | 08/11/2014 | 08/11/2014 | 01/21/2016 |  |  | 01/21/2016 | 01/25/2016 | 04/05/2016 | 05/11/2016 | 05/14/2016 | 12/31/9999
30979787 | OCGC2014 CASTLE CR RD RECONDUCTOR LW2224 | 08W | DI | Completion | ECES_CA1/CLSD | 06/25/2016 | 02/27/2013 | 01/20/2014 | 01/20/2014 | 02/12/2014 | 02/12/2014 | 03/31/2014 | 04/07/2014 | 05/29/2014 | 05/29/2014 | 07/28/2014 | 07/28/2014 | 01/29/2015 | 05/03/2016 | 06/20/2016 |  |  | 03/06/2015 | 03/25/2015 | 07/03/2015 | 08/06/2015 | 06/25/2016 | 12/31/9999
30980061 | *CANC* RECONDUCTOR 1 SP @ THOMPSON*CANC | 08W | CC | Completion | ECES_CA1/CLSD | 04/03/2014 | 02/27/2013 | 10/31/2013 | 02/19/2014 | 02/24/2014 | 02/24/2014 | 02/24/2014 | [6 empty] | 02/24/2014 | 03/04/2014 | 01/30/2014 | 02/19/2014 |  |  |  |  | 04/03/2014 | 12/31/9999 | 03/04/2014 | 04/03/2014
30980068 | 285 LITTLEFIELD AVE SSF | 08W | PN | Completion | ECES_CA1/CLSD | 02/14/2015 | 02/28/2013 | 09/04/2013 | 09/06/2013 | 09/23/2013 | 09/04/2013 | 09/04/2013 | 09/27/2013 | 10/01/2013 | 10/01/2013 | 03/05/2014 | 03/05/2014 | 03/25/2014 | 03/25/2014 | 12/22/2014 |  |  | 12/22/2014 | 12/22/2014 | 12/22/2014 | 02/12/2015 | 02/14/2015 | 12/31/9999
30980069 | R1 MB-1106 RECONDUCTORING | 08W | PN | Completion | ECES_CA1/CLSD | 02/20/2016 | 10/08/2013 | 12/02/2013 | 12/02/2013 | 01/03/2014 | 01/03/2014 | 01/17/2014 | 01/29/2014 | 03/11/2014 | 03/11/2014 | 08/11/2014 | 08/11/2014 | 09/17/2014 | 09/17/2014 | 09/09/2015 |  |  | 09/09/2015 | 01/22/2016 | 01/22/2016 | 02/17/2016 | 02/20/2016 | 12/31/9999
30980443 | XRECOND 4433/23327 @ 105 RODGERS RD | 08W | CC | Completion | ECES_CA1/CLSD | 08/05/2017 | 03/01/2013 | 10/31/2013 | 10/31/2013 | 12/13/2013 | 12/13/2013 | 01/28/2014 | 02/03/2014 | 02/03/2014 | 02/03/2014 | 05/29/2014 | 05/29/2014 | 11/13/2014 | 11/13/2014 | 09/10/2015 |  |  | 09/10/2015 | 01/26/2016 | 01/26/2016 | 07/29/2017 | 08/05/2017 | 12/31/9999
30980444 | OC4 XRECOND 310 FT 1-0C, LKHRN & CAST BL | 08W | CC | Completion | ECES_CA1/CLSD | 02/14/2015 | 03/01/2013 | 10/31/2013 | 02/19/2014 | 02/26/2014 | 02/26/2014 | 03/01/2014 | 03/12/2014 | 03/12/2014 | 03/12/2014 | 07/21/2014 | 07/21/2014 | 07/31/2014 | 07/31/2014 | 10/21/2014 | 10/21/2014 | 11/15/2014 | 11/15/2014 | 11/18/2014 | 11/18/2014 | 02/12/2015 | 02/14/2015 | 12/31/9999
30981327 | OC4 RECON 800FT 4AR - BAKERSFIELD 1110 | 08W | KE | Completion | ECES_CA1/CLSD | 02/06/2016 | 06/05/2013 | 07/08/2013 | 07/08/2013 | 08/21/2013 | 08/21/2013 | 09/05/2013 | 09/11/2013 | 10/30/2013 | 10/30/2013 | 06/16/2014 | 06/16/2014 | 06/25/2014 | 06/25/2014 | 08/05/2014 | 08/05/2014 | 08/21/2014 | 08/21/2014 | 01/19/2016 | 01/19/2016 | 02/03/2016 | 02/06/2016 | 12/31/9999
30981330 | 2015 MCFARLAND 1104 RECONDUCTOR | 08W | KE | Completion | ECES_CA1/CLSD | 03/19/2016 | 03/06/2013 | 06/26/2014 | 06/22/2015 | 06/22/2015 | 07/08/2014 | 09/19/2014 | 09/19/2014 | 06/12/2015 | 06/22/2015 | 06/23/2015 | 06/23/2015 | 08/27/2015 | 08/27/2015 | 09/09/2015 |  |  | 09/09/2015 | 03/18/2016 |  |  | 03/19/2016 | 12/31/9999
30981641 | RECOND 1608FT 2CU-SAN BERNARD 1101 | 08W | KE | Completion | ECES_CA1/CLSD | 03/19/2016 | 03/07/2013 | 12/12/2013 | 12/12/2013 | 12/26/2013 | 12/26/2013 | 02/03/2014 | 02/07/2014 | 02/11/2014 | 02/11/2014 | 09/28/2015 | 09/28/2015 | 10/27/2015 | 10/27/2015 | 03/18/2016 | [6 empty] | 03/19/2016 | 12/31/9999
30981763 | OCGC 2014 LAMONT 1106 RECONDUCTOR | 08W | KE | Completion | ECES_CA1/CLSD | 04/11/2015 | 03/08/2013 | 12/12/2013 | 12/12/2013 | 01/29/2014 | 03/14/2014 | 04/02/2014 | 04/06/2014 | 04/18/2014 | 04/18/2014 | 09/09/2014 | 09/09/2014 | 01/07/2015 | 01/07/2015 | 02/02/2015 | 03/13/2014 | 03/14/2014 | 02/02/2015 | 03/11/2015 | 03/11/2015 | 04/02/2015 | 04/11/2015 | 12/31/9999
30982568 | OC4 LKVL1101RECOND3SPAN-BRWNSRDLKVLHW,PE | 08W | SO | Completion | ECES_CA1/CLSD | 05/16/2015 | 03/12/2013 | 03/12/2013 | 03/12/2013 | 03/26/2013 | 03/26/2013 | 03/29/2013 | 06/27/2013 | 11/15/2013 | 11/15/2013 | 06/30/2014 | 06/30/2014 | 09/30/2014 | 09/30/2014 | 10/17/2014 | 10/17/2014 | 10/30/2014 | 10/30/2014 | 11/19/2014 | 11/19/2014 | 05/11/2015 | 05/16/2015 | 12/31/9999
30982640 | OC4 OCGC INSTREEW-5600MARSHALLPTLMA,OLEM | 08W | SO | Completion | ECES_CA1/CLSD | 12/13/2015 | 03/13/2013 | 06/22/2013 | 06/22/2013 | 08/29/2013 | 08/29/2013 | 08/29/2013 | 09/16/2013 | 10/07/2013 | 10/07/2013 | 06/30/2014 | 06/30/2014 | 12/01/2014 | 12/01/2014 | 12/08/2014 | 12/08/2014 | 12/10/2014 | 12/10/2014 | 12/24/2014 | 12/24/2014 | 12/07/2015 | 12/13/2015 | 12/31/9999
30982694 | OCCC +Z DIVIDE 1102 WD 13-0006459 | 08W | LP | Completion | ECES_CA1/CLSD | 09/17/2016 | 03/13/2013 | 02/27/2014 | 02/27/2014 | 03/20/2014 | 03/20/2014 | 05/01/2014 | 07/29/2014 | 08/15/2014 | 08/15/2014 | 09/01/2014 | 09/01/2014 | 12/29/2015 | 07/27/2016 | 08/31/2016 | 05/29/2014 | 06/05/2014 | 04/13/2016 | 07/01/2016 | 07/01/2016 | 07/19/2016 | 09/17/2016 | 12/31/9999
30984641 | OCLH PARL 1103 RECON 2 SPANS 800' OF 2CU | 08W | FR | Completion | ECES_CA1/CLSD | 02/14/2015 | 03/21/2013 | 08/14/2013 | 08/14/2013 | 09/20/2013 | 09/20/2013 | 09/23/2013 | 09/24/2013 | 10/04/2013 | 10/04/2013 | 05/28/2014 | 05/28/2014 | 07/22/2014 | 07/22/2014 | 12/18/2014 |  |  | 12/18/2014 | 01/13/2015 | 01/13/2015 | 02/12/2015 | 02/14/2015 | 12/31/9999
30984775 | OCGC 93PL OH DET WIRE ON NAPA 1104 | 08W | NB | Completion | ECES_CA1/CLSD | 08/19/2017 | 03/22/2013 | 06/22/2013 | 09/24/2013 | 10/01/2013 | 10/01/2013 | 10/01/2013 | 10/02/2013 | 11/22/2013 | 11/22/2013 | 02/13/2014 | 02/13/2014 | 09/08/2016 | 09/08/2016 | 09/16/2016 | 09/21/2013 | 09/24/2013 | 09/16/2016 | 12/22/2016 | 07/25/2017 | 08/18/2017 | 08/19/2017 | 12/31/9999
30985803 | OCLH BARTON 1101 4 ACSR | 08W | FR | Completion | ECES_CA1/CLSD | 09/21/2019 | 03/27/2013 | 08/07/2013 | 08/07/2013 | 08/24/2013 | 08/24/2013 | 09/11/2013 | 09/15/2013 | 11/25/2013 | 11/25/2013 | 11/21/2014 | 11/21/2014 | 12/17/2014 | 08/22/2019 | 09/19/2019 |  |  | 09/09/2015 | 02/09/2016 | 02/09/2016 | 03/18/2016 | 09/21/2019 | 12/31/9999
30989646 | OC4 E WEST SAC 1109 RECONDUCTOR 700 FEET | 08W | SA | Completion | ECES_CA1/CLSD | 01/31/2015 | 04/15/2013 | 07/30/2013 | 07/30/2013 | 09/19/2013 | 09/19/2013 | 09/24/2013 | 09/24/2013 | 10/15/2013 | 10/15/2013 | 01/06/2014 | 01/06/2014 | 01/17/2014 | 10/29/2014 | 01/29/2015 | 02/12/2014 | 02/24/2014 | 02/24/2014 | 07/01/2014 | 07/01/2014 | 09/11/2014 | 01/31/2015 | 12/31/9999
30989894 | OCGC ARCATA 1105 REMOVE EXCESS SPLICES | 08W | HB | Completion | ECES_CA1/CLSD | 01/26/2019 | 04/16/2013 | 05/16/2014 | 05/16/2014 | 06/11/2014 | 06/11/2014 | 06/26/2014 | 08/18/2014 | 04/21/2015 | 04/21/2015 | 05/12/2015 | 05/12/2015 | 07/02/2015 | 12/19/2018 | 01/22/2019 |  |  | 09/09/2015 | 02/01/2016 | 02/01/2016 | 02/11/2016 | 01/26/2019 | 12/31/9999
30990258 | OCGC XKING CITY 1106 RECONDUCTORING | 08W | CC | Completion | ECES_CA1/CLSD | 12/26/2015 | 04/18/2013 | 04/07/2014 | 05/08/2014 | 05/13/2014 | 05/02/2014 | 05/05/2014 | 05/28/2014 | 10/02/2014 | 10/02/2014 | 10/28/2014 | 10/28/2014 | 12/15/2014 | 12/15/2014 | 12/23/2014 | 05/01/2014 | 05/01/2014 | 12/23/2014 | 12/24/2014 | 12/24/2014 | 12/21/2015 | 12/26/2015 | 12/31/9999
30991832 | OCLH SCHINDLER 1105 - REPLACE 2 SPANS 4 | 08W | FR | Completion | ECES_CA1/CLSD | 02/14/2015 | 04/23/2013 | 08/06/2013 | 08/06/2013 | 08/22/2013 | 08/22/2013 | 08/27/2013 | 09/10/2013 | 09/11/2013 | 09/11/2013 | 09/08/2014 | 09/08/2014 | 09/26/2014 | 09/26/2014 | 10/05/2014 |  |  | 10/05/2014 | 12/29/2014 | 12/29/2014 | 02/12/2015 | 02/14/2015 | 12/31/9999
30992890 | OC4 XRECNDUCTOR 2 SPOF 4AR TW-PRESCOTT R | 08W | CC | Completion | ECES_CA1/CLSD | 08/16/2014 | 04/29/2013 | 08/27/2013 | 08/27/2013 | 09/04/2013 | 09/04/2013 | 09/18/2013 | 09/24/2013 | 02/19/2014 | 02/19/2014 | 03/11/2014 | 03/11/2014 | 04/09/2014 | 04/09/2014 | 05/16/2014 | 05/16/2014 | 05/30/2014 | 05/30/2014 | 06/13/2014 | 06/13/2014 | 08/13/2014 | 08/16/2014 | 12/31/9999
30993194 | MEN 402 REPL 630FT &3 PLS/219 ATHERTON A | 08W | PN | Completion | ECES_CA1/CLSD | 01/28/2018 | 04/30/2013 | 09/02/2013 | 09/24/2013 | 09/27/2013 | 09/24/2013 | 09/24/2013 | 10/01/2013 | 11/27/2013 | 11/27/2013 | 03/03/2014 | 03/03/2014 | 10/11/2014 | 10/11/2014 | 01/14/2015 |  |  | 01/14/2015 | 01/14/2015 | 01/14/2015 | 01/22/2018 | 01/28/2018 | 12/31/9999
30993279 | OCLHRECOND 5 SPANS 4AR,@ 50/52 NASHUA RD | 08W | CC | Completion | ECES_CA1/CLSD | 04/11/2015 | 04/30/2013 | 02/28/2014 | 02/28/2014 | 03/27/2014 | 03/27/2014 | 04/11/2014 | 04/11/2014 | 05/07/2014 | 05/07/2014 | 06/05/2014 | 06/05/2014 | 06/27/2014 | 12/11/2014 | 04/08/2015 |  |  | 07/08/2014 | 07/14/2014 | 07/14/2014 | 10/10/2014 | 04/11/2015 | 12/31/9999
30993327 | OCLHR1 RECONDUCTOR 390' OHDUMBARTON 2111 | 08W | MI | Completion | ECES_CA1/CLSD | 05/09/2015 | 04/30/2013 | 09/02/2013 | 09/02/2013 | 09/11/2013 | 09/11/2013 | 09/24/2013 | 09/27/2013 | 11/05/2013 | 11/05/2013 | 02/25/2014 | 02/25/2014 | 03/12/2014 | 09/02/2014 | 10/02/2014 |  |  | 03/22/2014 | 04/19/2014 | 04/03/2015 | 05/08/2015 | 05/09/2015 | 12/31/9999
30997023 | OCGC RECONDUC TO REMOVE SPLICES LG1106 | 08W | DA | Completion | ECES_CA1/CLSD | 02/20/2016 | 05/17/2013 | 02/25/2014 | 04/17/2014 | 04/17/2014 | 04/15/2014 | 04/17/2014 | 06/12/2014 | 08/21/2014 | 08/21/2014 | 11/07/2014 | 11/07/2014 | 01/06/2015 | 01/06/2015 | 02/06/2015 | 05/27/2014 | 06/12/2014 | 02/06/2015 | 01/28/2016 | 01/28/2016 | 02/17/2016 | 02/20/2016 | 12/31/9999
30997782 | *CANC* CAMBRIA LINE RECONFIG *CANC | 08W | LP | Completion | ECES_CA1/CLSD | 12/03/2017 | 05/21/2013 | 12/05/2013 | [10 empty] | 04/09/2014 | 04/09/2014 | 12/05/2013 | 04/09/2014 |  |  |  |  | 12/03/2017 | 12/31/9999 | 11/22/2017 | 12/03/2017
30997783 | OC4+RECONDUCTOR FAIRWY 1107 AT FUCO 1219 | 08W | LP | Completion | ECES_CA1/CLSD | 11/08/2014 | 05/21/2013 | 06/03/2013 | 06/03/2013 | 06/11/2013 | 06/11/2013 | 07/12/2013 | 07/18/2013 | 07/30/2013 | 07/30/2013 | 10/28/2013 | 10/28/2013 | 11/12/2013 | 11/12/2013 | 05/16/2014 | 05/16/2014 | 05/27/2014 | 05/27/2014 | 07/03/2014 | 10/06/2014 | 11/03/2014 | 11/08/2014 | 12/31/9999
31001492 | OC4 OCLH PLEASANTON RECONDUCTOR 2700' WI | 08W | MI | Completion | ECES_CA1/CLSD | 03/19/2016 | 06/08/2013 | 03/10/2014 | 03/10/2014 | 03/17/2014 | 03/25/2014 | 03/31/2014 | 04/02/2014 | 07/14/2014 | 07/14/2014 | 08/25/2014 | 08/25/2014 | 12/12/2014 | 12/18/2015 | 12/21/2015 | 01/14/2015 | 01/15/2015 | 01/15/2015 | 01/29/2015 | 12/21/2015 | 03/18/2016 | 03/19/2016 | 12/31/9999
31002333 | MIDWAY 1104- INSTALL FUSE | 08W | KE | Completion | ECES_CA1/CLSD | 02/14/2015 | 06/12/2013 | 03/03/2014 | 03/03/2014 | 03/28/2014 | 03/28/2014 | 04/21/2014 | 04/23/2014 | 05/02/2014 | 05/02/2014 | 08/07/2014 | 08/07/2014 | 09/04/2014 | 09/04/2014 | 10/15/2014 |  |  | 10/15/2014 | 11/25/2014 | 11/25/2014 | 02/12/2015 | 02/14/2015 | 12/31/9999
31006463 | OCLHXRECOND BV1102-HARKINS RD@BURTON AVE | 08W | CC | Completion | ECES_CA1/CLSD | 02/14/2015 | 07/01/2013 | 03/20/2014 | 03/20/2014 | 05/09/2014 | 05/09/2014 | 05/22/2014 | 05/23/2014 | 06/21/2014 | 06/21/2014 | 09/25/2014 | 09/25/2014 | 10/22/2014 | 10/22/2014 | 10/25/2014 |  |  | 10/25/2014 | 11/18/2014 | 11/18/2014 | 02/12/2015 | 02/14/2015 | 12/31/9999
31007718 | *CANC* WIRE DOWN SERVICE REL JOB *CANC | 08W | SA | Completion | ECES_CA1/CLSD | 09/06/2013 | 07/11/2013 | 08/07/2013 | [18 empty] | 09/06/2013 | 12/31/9999 | 08/12/2013 | 09/06/2013
31008212 | OC4 RECON 1/0A W/397A MERRIL ST-BV 1103- | 08W | CC | Completion | ECES_CA1/CLSD | 10/17/2015 | 07/12/2013 | 07/26/2013 | 11/13/2013 | 04/10/2014 | 04/10/2014 | 04/25/2014 | 04/25/2014 | 06/17/2014 | 06/17/2014 | 07/14/2014 | 07/14/2014 | 10/10/2014 | 10/10/2014 | 10/29/2014 | 10/29/2014 | 11/14/2014 | 11/14/2014 | 11/15/2014 | 11/15/2014 | 10/16/2015 | 10/17/2015 | 12/31/9999
31008213 | XBUENA VISTA 1103 NUTTING 4AR | 08W | CC | Completion | ECES_CA1/CLSD | 10/17/2015 | 12/27/2013 | 03/13/2014 | 04/27/2014 | 05/01/2014 | 05/01/2014 | 05/05/2014 | 05/05/2014 | 07/03/2014 | 07/03/2014 | 07/14/2014 | 07/14/2014 | 11/19/2014 | 11/19/2014 | 11/21/2014 | 10/25/2013 | 11/13/2013 | 11/21/2014 | 12/19/2014 | 12/19/2014 | 10/16/2015 | 10/17/2015 | 12/31/9999
31009249 | RPL 800' OH CONDUCTOR GREENBRAE 1101 | 08W | NB | Completion | ECES_CA1/CLSD | 09/23/2017 | 07/18/2013 | 06/04/2014 | 06/04/2014 | 07/14/2014 | 07/14/2014 | 07/18/2014 | 06/01/2015 | 06/24/2015 | 06/24/2015 | 08/24/2015 | 08/24/2015 | 11/02/2015 | 08/16/2017 | 09/18/2017 |  |  | 04/15/2016 | 06/01/2016 | 06/01/2016 | 07/19/2016 | 09/23/2017 | 12/31/9999
31011324 | OCGC XREPL DETERIORTD COND SMITH RD WAT | 08W | CC | Completion | ECES_CA1/CLSD | 09/12/2015 | 07/27/2013 | 04/01/2014 | 04/01/2014 | 04/05/2014 | 04/05/2014 | 05/10/2014 | 05/12/2014 | 06/30/2014 | 06/30/2014 | 11/10/2014 | 11/10/2014 | 02/13/2015 | 02/13/2015 | 02/18/2015 |  |  | 02/18/2015 | 04/02/2015 | 08/05/2015 | 09/08/2015 | 09/12/2015 | 12/31/9999
31016170 | OCGC XRECONDUCTORING PRI @ IVERSON RD | 08W | CC | Completion | ECES_CA1/CLSD | 08/27/2016 | 08/21/2013 | 03/10/2014 | 04/17/2014 | 04/18/2014 | 04/18/2014 | 04/21/2014 | 06/12/2014 | 08/04/2014 | 08/04/2014 | 11/25/2014 | 11/25/2014 | 02/13/2015 | 02/13/2015 | 02/23/2015 | 06/09/2014 | 06/12/2014 | 02/23/2015 | 07/11/2016 | 07/11/2016 | 08/22/2016 | 08/27/2016 | 12/31/9999
31016636 | OC4 OCGC CORRAL 1101 RELOCAT 4ACSR (WIR | 08W | ST | Completion | ECES_CA1/CLSD | 08/20/2016 | 08/23/2013 | 01/20/2014 | 01/20/2014 | 03/11/2014 | 03/11/2014 | 03/19/2014 | 04/24/2014 | 04/09/2015 | 07/15/2015 | 10/19/2015 | 10/19/2015 | 01/20/2016 | 01/20/2016 | 04/12/2016 | 04/21/2014 | 04/22/2014 | 04/12/2016 | 07/19/2016 | 07/19/2016 | 08/17/2016 | 08/20/2016 | 12/31/9999
31017531 | OC4 OCGC KERN POWER 2103 4 SPANS RECONDU | 08W | KE | Completion | ECES_CA1/CLSD | 05/16/2015 | 08/27/2013 | 03/03/2014 | 03/05/2014 | 04/03/2014 | 04/03/2014 | 04/21/2014 | 06/12/2014 | 09/16/2014 | 09/16/2014 | 12/02/2014 | 12/02/2014 | 01/21/2015 | 01/21/2015 | 02/03/2015 | 02/03/2015 | 02/12/2015 | 02/12/2015 | 04/10/2015 | 04/10/2015 | 05/11/2015 | 05/16/2015 | 12/31/9999
31017692 | *CANC* WD SISQUOC 1102 PHASE 3A RE*CANC | 08W | LP | Completion | ECES_CA1/CLSD | 01/05/2015 | 08/28/2013 | 12/02/2014 | [18 empty] | 01/05/2015 | 12/31/9999 | 12/02/2014 | 01/05/2015
31017694 | +BPO WD SANTA MARIA 1109 RECNDUCTR & FU | 08W | LP | Completion | ECES_CA1/CLSD | 12/13/2014 | 08/28/2013 | 02/27/2014 | 02/27/2014 | 04/25/2014 | 06/12/2014 | 06/24/2014 | 06/24/2014 | 07/14/2014 | 07/14/2014 | 08/04/2014 | 08/04/2014 | 09/04/2014 | 09/04/2014 | 10/06/2014 | 05/29/2014 | 06/12/2014 | 10/06/2014 | 10/11/2014 | 10/11/2014 | 12/05/2014 | 12/13/2014 | 12/31/9999
31019802 | OC4 EP REPLACE DAMAGED CONDUCT , HICKORY | 08W | NV | Completion | ECES_CA1/CLSD | 01/31/2015 | 09/08/2013 | 09/13/2013 | 09/13/2013 | 09/17/2013 | 09/17/2013 | 09/24/2013 | 09/26/2013 | 09/27/2013 | 09/27/2013 | 02/08/2014 | 02/08/2014 | 03/05/2014 | 10/29/2014 | 01/29/2015 | 03/17/2014 | 03/21/2014 | 03/21/2014 | 04/28/2014 | 04/28/2014 | 06/12/2014 | 01/31/2015 | 12/31/9999
31021152 | OC4 OCGC R2 2014 DINUBA 1105 RECONDUCTOR | 08W | FR | Completion | ECES_CA1/CLSD | 07/18/2015 | 09/13/2013 | 03/21/2014 | 03/21/2014 | 04/08/2014 | 05/01/2014 | 05/19/2014 | 05/20/2014 | 06/09/2014 | 06/09/2014 | 06/30/2014 | 06/30/2014 | 08/29/2014 | 06/10/2015 | 07/07/2015 | 05/01/2014 | 05/01/2014 | 10/10/2014 | 01/13/2015 | 01/13/2015 | 01/13/2015 | 07/18/2015 | 12/31/9999
31028173 | OC4 +OCEANO 1103 HWY 101 REC | 08W | LP | Completion | ECES_CA1/CLSD | 07/18/2015 | 10/14/2013 | 02/10/2014 | 02/10/2014 | 02/27/2014 | 02/27/2014 | 04/16/2014 | 04/20/2015 | 04/20/2015 | 04/20/2015 | 04/20/2015 | 07/01/2014 | 09/18/2014 | 04/20/2015 | 06/08/2015 | 09/29/2014 | 10/20/2014 | 10/20/2014 | 11/14/2014 | 06/08/2015 | 07/10/2015 | 07/18/2015 | 12/31/9999
31036265 | R1128-RECNDUCTOR 3 SPANS,NSTALL CUT | 08W | EB | Completion | ECES_CA1/CLSD | 01/28/2018 | 11/15/2013 | 09/12/2014 | 09/12/2014 | 10/20/2014 | 10/20/2014 | 10/20/2014 | 02/16/2015 | 02/18/2015 | 02/18/2015 | 08/31/2015 | 08/31/2015 | 09/22/2015 | 09/22/2015 | 11/13/2015 | 12/12/2014 | 01/13/2015 | 11/13/2015 | 09/14/2016 | 09/14/2016 | 01/22/2018 | 01/28/2018 | 12/31/9999
31038431 | OC4 OCCC WD CABRILLO 1104 13-0056541 | 08W | LP | Completion | ECES_CA1/CLSD | 03/19/2016 | 11/23/2013 | 01/02/2015 | 01/02/2015 | 02/26/2015 | 04/07/2015 | 04/08/2015 | 04/11/2015 | 07/03/2015 | 07/03/2015 | 07/24/2015 | 07/24/2015 | 08/21/2015 | 08/21/2015 | 08/28/2015 | 08/28/2015 | 02/18/2016 | 02/18/2016 | 02/25/2016 | 02/25/2016 | 03/15/2016 | 03/19/2016 | 12/31/9999
31039795 | MABURY 1102 WIRE DOWN 13-0077162 | 08W | SJ | Completion | ECES_CA1/CLSD | 03/19/2016 | 12/04/2013 | 04/15/2015 | 04/15/2015 | 06/03/2015 | 06/03/2015 | 06/28/2015 | 07/22/2015 | 07/23/2015 | 07/23/2015 | 09/28/2015 | 09/28/2015 | 10/16/2015 | 10/16/2015 | 03/18/2016 | 07/15/2015 | 07/22/2015 |  |  |  |  | 03/19/2016 | 12/31/9999
31040925 | RECONDUCT #4ACSR_W.JACKSON_HAYWRD | 08W | MI | Completion | ECES_CA1/CLSD | 06/09/2018 | 12/06/2013 | 06/29/2015 | 06/29/2015 | 07/29/2015 | 07/29/2015 | 08/07/2015 | 08/07/2015 | 10/19/2015 | 10/19/2015 | 11/02/2015 | 11/02/2015 | 12/09/2015 | 12/09/2015 | 04/15/2016 |  |  | 04/15/2016 | 06/18/2016 | 06/18/2016 | 06/07/2018 | 06/09/2018 | 12/31/9999
31043129 | EB-RELIAIBLITY K1103-RECONDUT | 08W | EB | Completion | ECES_CA1/CLSD | 11/24/2018 | 12/18/2013 | 02/08/2017 | 02/08/2017 | 02/08/2017 | 02/08/2017 | 05/08/2017 | 05/08/2017 | 08/18/2017 | 08/18/2017 | 10/24/2017 | 10/24/2017 | 11/08/2017 | 10/17/2018 | 11/19/2018 |  |  | 11/20/2017 | 12/07/2017 | 12/07/2017 | 01/19/2018 | 11/24/2018 | 12/31/9999
31043566 | OCGC XRECOND 500FT W. ZAYANTE RD CE 2105 | 08W | CC | Completion | ECES_CA1/CLSD | 12/26/2015 | 12/18/2013 | 07/07/2014 | 07/07/2014 | 07/30/2014 | 07/30/2014 | 08/01/2014 | 08/01/2014 | 10/17/2014 | 10/17/2014 | 11/15/2014 | 11/15/2014 | 02/24/2015 | 02/24/2015 | 03/05/2015 |  |  | 03/05/2015 | 03/13/2015 | 03/13/2015 | 12/21/2015 | 12/26/2015 | 12/31/9999
31043567 | OCGC XRECON W/675FT TW LOKHRT GL CE 2105 | 08W | CC | Completion | ECES_CA1/CLSD | 12/26/2015 | 12/18/2013 | 07/07/2014 | 07/07/2014 | 07/25/2014 | 07/25/2014 | 07/31/2014 | 07/31/2014 | 10/06/2014 | 10/06/2014 | 12/01/2014 | 12/01/2014 | 01/28/2015 | 01/28/2015 | 02/13/2015 |  |  | 02/13/2015 | 04/25/2015 | 04/25/2015 | 12/21/2015 | 12/26/2015 | 12/31/9999
31047513 | OCGC RECONDUCTOR 2 SPANS DIXON 1103 | 08W | SA | Completion | ECES_CA1/CLSD | 03/19/2016 | 01/08/2014 | 03/16/2015 | 06/23/2015 | 06/30/2015 |  |  | 07/02/2015 | 08/14/2015 | 08/14/2015 | 08/24/2015 | 08/24/2015 | 09/09/2015 | 09/09/2015 | 02/17/2016 | 06/16/2015 | 06/23/2015 | 02/17/2016 | 02/23/2016 | 02/23/2016 | 03/18/2016 | 03/19/2016 | 12/31/9999
31048179 | OC4 OCGC SONOMA1105-WIREDWN-8TH ST EAST | 08W | SO | Completion | ECES_CA1/CLSD | 06/16/2018 | 01/10/2014 | 06/04/2014 | 06/04/2014 | 07/18/2014 | 07/18/2014 | 07/23/2014 | 07/28/2014 | 08/04/2014 | 08/04/2014 | 12/22/2014 | 12/22/2014 | 01/06/2015 | 01/06/2015 | 01/26/2015 | 01/26/2015 | 01/29/2015 | 01/29/2015 | 02/02/2015 | 02/02/2015 | 06/13/2018 | 06/16/2018 | 12/31/9999
31048895 | OCGC RECONDUCT 1-SPAN -WILLITS 1103 | 08W | HB | Completion | ECES_CA1/CLSD | 06/25/2016 | 01/13/2014 | 06/04/2014 | 06/04/2014 | 07/24/2014 | 07/24/2014 | 07/28/2014 | 09/19/2014 | 11/17/2014 | 11/17/2014 | 12/02/2014 | 12/02/2014 | 07/10/2015 | 07/10/2015 | 09/10/2015 |  |  | 09/10/2015 | 02/08/2016 | 02/08/2016 | 06/20/2016 | 06/25/2016 | 12/31/9999
31053110 | MABURY 1102 WIRE DOWN 14-0004189 | 08W | SJ | Completion | ECES_CA1/CLSD | 02/06/2021 | 01/30/2014 | 04/15/2015 | 04/15/2015 | 06/25/2015 | 06/25/2015 | 07/03/2015 | 08/13/2015 | 10/05/2015 |  |  | 10/05/2015 | 01/12/2016 | 09/01/2020 | 02/02/2021 | 07/15/2015 | 08/13/2015 | 04/16/2016 | 07/06/2016 | 07/06/2016 | 08/23/2016 | 02/06/2021 | 12/31/9999
31054897 | OCGC BH402 LS CO10192 REPL.2 SPANS OH LI | 08W | PN | Completion | ECES_CA2/CLSD | 02/06/2021 | 02/06/2014 | 06/30/2014 | 06/30/2014 | 07/07/2014 | 07/07/2014 | 07/18/2014 | 12/07/2014 | 12/12/2014 | 12/12/2014 | 01/22/2015 | 01/22/2015 | 06/03/2015 | 06/03/2015 | 09/10/2015 |  |  | 09/10/2015 | 12/01/2015 | 12/01/2015 | 02/03/2021 | 02/06/2021 | 12/31/9999
31059794 | OCGC CLARKSVILLE 2104 RECONDUCTOR,PHASE1 | 08W | SI | Completion | ECES_CA1/CLSD | 01/14/2017 | 01/06/2015 | 02/04/2015 | 02/04/2015 | 03/19/2015 | 03/19/2015 | 04/20/2015 | 04/23/2015 | 08/28/2015 | 08/28/2015 | 12/28/2015 | 12/28/2015 | 05/23/2016 | 12/28/2016 | 12/28/2016 | 12/24/2014 | 01/06/2015 | 07/15/2016 | 10/26/2016 | 12/28/2016 | 01/11/2017 | 01/14/2017 | 12/31/9999
31060016 | OCCCRECO 1 SPAN LINE SIDE FU 1829 TW2107 | 08W | DI | Completion | ECES_CA1/CLSD | 12/26/2015 | 03/03/2014 | 03/03/2014 | 03/03/2014 | 04/23/2014 | 04/23/2014 | 04/26/2014 | 08/04/2014 | 11/13/2014 | 11/13/2014 | 12/23/2014 |  |  | 03/18/2015 | 05/11/2015 | 06/02/2014 | 06/12/2014 | 01/21/2015 | 01/31/2015 | 05/11/2015 | 12/21/2015 | 12/26/2015 | 12/31/9999
31062729 | LERDO 1103 RECONDUCTOR 1,700FT WD | 08W | KE | Completion | ECES_CA1/CLSD | 03/19/2016 | 03/13/2014 | 05/07/2015 | 05/07/2015 | 06/04/2015 | 06/04/2015 | 06/23/2015 | 07/06/2015 | 07/06/2015 | 07/06/2015 | 09/22/2015 | 09/22/2015 | 11/02/2015 | 11/02/2015 | 03/18/2016 | [6 empty] | 03/19/2016 | 12/31/9999
31063598 | WEEDPATCH 1106 RECOND WIRE DOWN | 08W | KE | Completion | ECES_CA1/CLSD | 08/27/2016 | 03/17/2014 | 06/11/2015 | 06/11/2015 | 06/17/2015 | 06/17/2015 | 07/24/2015 | 07/28/2015 | 08/04/2015 | 08/04/2015 | 11/23/2015 | 11/23/2015 | 12/16/2015 | 12/16/2015 | 04/15/2016 |  |  | 04/15/2016 | 07/11/2016 | 07/11/2016 | 08/23/2016 | 08/27/2016 | 12/31/9999
31066529 | OCGC CEDAR CRK 1101-RECOND 3528' Y2015 | 08W | NV | Completion | ECES_CA1/CLSD | 12/16/2017 | 04/01/2014 | 06/20/2014 | 08/19/2014 | 09/15/2014 | 09/15/2014 | 09/29/2014 | 09/29/2014 | 08/24/2015 |  |  | 08/24/2015 | 11/06/2015 | 11/06/2015 | 04/26/2016 | 08/13/2014 | 08/19/2014 | 04/26/2016 | 06/16/2016 | 11/15/2017 | 12/14/2017 | 12/16/2017 | 12/31/9999
31067784 | OCGC XRECON 300' OF 4AR W/ 4/0A FORD ST | 08W | CC | Completion | ECES_CA1/CLSD | 06/13/2015 | 04/07/2014 | 07/07/2014 | 07/07/2014 | 08/01/2014 | 08/01/2014 | 08/06/2014 | 08/06/2014 | 10/29/2014 | 10/29/2014 | 11/26/2014 | 11/26/2014 | 04/02/2015 | 04/02/2015 | 04/18/2015 |  |  | 04/18/2015 | 05/04/2015 | 05/04/2015 | 06/10/2015 | 06/13/2015 | 12/31/9999
31069570 | X-SPENCE 1121 WIREDOWN 3779 | 08W | CC | Completion | ECES_CA1/CLSD | 07/23/2016 | 04/16/2014 | 04/15/2015 | 04/15/2015 | 07/14/2015 | 07/17/2015 | 07/18/2015 | 07/28/2015 | 08/03/2015 | 08/03/2015 | 09/07/2015 | 09/07/2015 | 12/09/2015 | 12/09/2015 | 04/13/2016 | 07/15/2015 | 07/17/2015 | 04/13/2016 | 06/16/2016 | 06/16/2016 | 07/19/2016 | 07/23/2016 | 12/31/9999
31071681 | OCGC 1105-JEFFREY PINE RECON 600' | 08W | NV | Completion | ECES_CA1/CLSD | 03/19/2016 | 04/25/2014 | 01/26/2015 | 01/26/2015 | 03/08/2015 | 03/08/2015 | 03/30/2015 | 03/30/2015 | 05/18/2015 | 05/18/2015 | 07/07/2015 | 07/07/2015 | 08/31/2015 | 08/31/2015 | 02/18/2016 |  |  | 02/18/2016 | 02/24/2016 | 02/24/2016 | 03/18/2016 | 03/19/2016 | 12/31/9999
31073205 | *CANC* R6 BUENA VISTA 1102 WD RECO*CANC | 08W | CC | Completion | ECES_CA1/CLSD | 07/03/2015 | 05/02/2014 | 04/15/2015 | 04/15/2015 | 06/17/2015 | [16 empty] | 07/03/2015 | 12/31/9999 | 06/17/2015 | 07/03/2015
31075442 | BORDEN 1103 RECONDUCTORING | 08W | YO | Completion | ECES_CA1/CLSD | 09/24/2016 | 05/11/2014 | 01/07/2016 | 01/07/2016 | 01/22/2016 | 01/22/2016 | 01/28/2016 | 02/10/2016 | 02/29/2016 | 02/29/2016 | 03/15/2016 | 03/15/2016 | 04/04/2016 | 04/04/2016 | 04/14/2016 |  |  | 04/14/2016 | 08/26/2016 | 08/26/2016 | 09/21/2016 | 09/24/2016 | 12/31/9999
31079018 | *CANC* BIG BEND 1102 - BLOOMER HIL *CANC | 08W | NV | Completion | ECES_CA1/CLSD | 11/03/2019 | 07/18/2018 | 12/17/2018 | 06/12/2018 | 07/18/2018 | [10 empty] | 12/17/2018 | 10/10/2019 |  |  |  |  | 11/03/2019 | 12/31/9999 | 10/10/2019 | 11/03/2019
31082152 | OCCC XRECNDUCTR 2900' HRD TAP GNZLS 1104 | 08W | CC | Completion | ECES_CA1/CLSD | 07/23/2016 | 06/12/2014 | 04/27/2015 | 04/27/2015 | 05/23/2015 | 05/23/2015 | 06/28/2015 | 07/10/2015 | 07/24/2015 | 07/24/2015 | 09/11/2015 | 09/11/2015 | 12/14/2015 | 12/14/2015 | 04/15/2016 |  |  | 04/15/2016 | 06/16/2016 | 06/16/2016 | 07/19/2016 | 07/23/2016 | 12/31/9999
31082393 | RECON THREE SPANS CHERRY RIDGE RD | 08W | SO | Documentation | ECES_CA1/DOCC | 09/05/2019 | 06/12/2014 | 11/30/2016 | 02/11/2019 | 02/20/2019 | 11/07/2017 | 11/07/2017 | 02/21/2019 | 03/21/2019 | 03/21/2019 | 07/18/2019 | 07/18/2019 | 09/05/2019 | 09/05/2019 | 12/31/9999 | 03/01/2017 | 03/22/2017
31082394 | OCGC N SIX SPANS FRATI LN | 08W | SO | Completion | ECES_CA1/CLSD | 07/20/2019 | 08/21/2017 | 08/22/2017 | 08/22/2017 | 11/09/2017 | 11/09/2017 | 11/09/2017 | 05/24/2018 | 07/02/2018 | 07/02/2018 | 07/16/2018 | 07/16/2018 | 09/24/2018 | 09/24/2018 | 09/25/2018 | 03/04/2017 | 03/22/2017 | 09/25/2018 | 07/17/2019 |  |  | 07/20/2019 | 12/31/9999
31083701 | OCCC HMB-1103RECOND 400' OH PRI_INST C/O | 08W | PN | Completion | ECES_CA1/CLSD | 08/27/2016 | 06/20/2014 | 07/06/2015 | 07/06/2015 | 07/30/2015 | 07/30/2015 | 08/26/2015 | 10/08/2015 | 10/08/2015 | 10/08/2015 | 11/02/2015 | 11/02/2015 | 06/13/2016 | 06/13/2016 | 06/27/2016 | 10/06/2015 | 10/08/2015 | 06/27/2016 | 07/06/2016 | 07/06/2016 | 08/23/2016 | 08/27/2016 | 12/31/9999
31085776 | SANTA MARIA 1109 (HWY166/E/O BLACK RD) | 08W | LP | Completion | ECES_CA1/CLSD | 10/28/2017 | 06/30/2014 | 07/06/2015 | 07/06/2015 | 07/06/2015 | 07/06/2015 | 07/23/2015 | 10/14/2015 | 11/16/2015 | 11/16/2015 | 12/10/2015 | 12/10/2015 | 06/06/2016 | 06/06/2016 | 07/11/2016 | 10/06/2015 | 10/14/2015 | 07/11/2016 | 10/04/2016 | 09/18/2017 | 10/24/2017 | 10/28/2017 | 12/31/9999
31086638 | OCCC CABRILLO 1104 WIREDOWN 14-0036943 | 08W | LP | Completion | ECES_CA1/CLSD | 11/19/2016 | 07/03/2014 | 05/07/2015 | 05/07/2015 | 06/08/2015 | 06/08/2015 | 06/26/2015 | 06/30/2015 | 08/07/2015 | 08/07/2015 | 10/05/2015 | 10/05/2015 | 10/26/2015 | 10/26/2015 | 09/22/2016 |  |  | 09/22/2016 | 09/27/2016 | 09/27/2016 | 11/14/2016 | 11/19/2016 | 12/31/9999
31089263 | MOVE FUSE 1179/RECON WITH TREE WIRE | 08W | DI | Initiation | ECES_CA1/UNSE | 01/25/2019 | 01/25/2019 | 12/31/9999 | 05/24/2016 | 07/23/2016 | 07/23/2016 | 08/02/2016 | 08/03/2016 | 11/09/2016 | 11/09/2016 | 01/25/2019
31089385 | *CANC* R5WD REPL 1 SPAN WITH 4/0AL*CANC | 08W | LP | Completion | ECES_CA1/CLSD | 01/05/2015 | 07/17/2014 | 12/05/2014 | [18 empty] | 01/05/2015 | 12/31/9999 | 12/05/2014 | 01/05/2015
31093073 | XSHELL RD, REPL 450' 6CU OH CONDUCTOR | 08W | CC | Completion | ECES_CA1/CLSD | 07/23/2016 | 08/05/2014 | 05/05/2015 | 05/05/2015 | 05/26/2015 | 05/26/2015 | 06/23/2015 | 08/13/2015 | 09/02/2015 | 09/02/2015 | 09/22/2015 | 09/22/2015 | 10/26/2015 | 10/26/2015 | 04/16/2016 | 08/05/2015 | 08/13/2015 | 04/16/2016 | 06/06/2016 | 06/06/2016 | 07/19/2016 | 07/23/2016 | 12/31/9999
31093074 | +SM 1109 RECON (HWY 166 / E/O SIMAS RD) | 08W | LP | Completion | ECES_CA1/CLSD | 12/17/2016 | 08/05/2014 | 05/07/2015 | 05/07/2015 | 06/30/2015 | 06/30/2015 | 07/23/2015 | 07/30/2015 | 10/06/2015 | 10/06/2015 | 12/09/2015 | 12/09/2015 | 06/14/2016 | 06/14/2016 | 08/01/2016 |  |  | 08/01/2016 | 11/15/2016 | 11/15/2016 | 12/14/2016 | 12/17/2016 | 12/31/9999
31093779 | MABURY 1104 WIRE DOWN 14-0043849 | 08W | SJ | Completion | ECES_CA1/CLSD | 08/27/2016 | 08/08/2014 | 04/15/2015 | 04/15/2015 | 06/12/2015 | 06/12/2015 | 06/28/2015 | 08/13/2015 | 10/16/2015 | 10/16/2015 | 10/19/2015 | 10/19/2015 | 01/21/2016 | 01/21/2016 | 05/02/2016 | 07/15/2015 | 08/13/2015 | 05/02/2016 | 07/12/2016 | 07/12/2016 | 08/23/2016 | 08/27/2016 | 12/31/9999
31094780 | OH WIRE DOWN REPLACEMENT ME1110 | 08W | MI | Completion | ECES_CA1/CLSD | 09/21/2019 | 08/13/2014 | 06/29/2015 | 06/29/2015 | 07/31/2015 | 07/31/2015 | 08/07/2015 | 06/28/2016 | 06/30/2016 | 06/30/2016 | 07/11/2016 | 07/11/2016 | 08/12/2016 | 07/21/2019 | 08/16/2019 |  |  | 09/09/2016 | 01/23/2017 | 08/16/2019 | 09/19/2019 | 09/21/2019 | 12/31/9999
31095523 | OCGCELIAIBLITY -K1103, REPL #4ACSR W | 08W | EB | Completion | ECES_CA1/CLSD | 04/25/2020 | 08/19/2014 | 09/09/2016 | 09/09/2016 | 11/08/2016 | 11/08/2016 | 11/23/2016 | 12/16/2016 | 04/26/2017 | 04/26/2017 | 09/11/2017 | 09/11/2017 | 06/07/2018 | 02/28/2020 | 04/24/2020 | 12/09/2016 | 12/16/2016 | 06/08/2018 | 07/17/2018 | 07/17/2018 | 07/17/2019 | 04/25/2020 | 12/31/9999
31097449 | XPRUNEDALE 1107 WD C/O 4485 | 08W | CC | Completion | ECES_CA1/CLSD | 10/28/2017 | 08/27/2014 | 04/15/2015 | 04/15/2015 | 04/27/2015 | 04/27/2015 | 04/30/2015 | 05/01/2015 | 07/03/2015 | 07/03/2015 | 09/18/2015 | 09/18/2015 | 11/12/2015 | 11/12/2015 | 03/18/2016 |  |  |  |  | 09/18/2017 | 10/24/2017 | 10/28/2017 | 12/31/9999
31097452 | XCAMPHORA 1101 WD FCO 7091 | 08W | CC | Completion | ECES_CA1/CLSD | 07/23/2016 | 08/27/2014 | 04/27/2015 | 04/27/2015 | 05/11/2015 | 05/11/2015 | 06/13/2015 | 06/18/2015 | 06/26/2015 | 06/26/2015 | 09/07/2015 | 09/07/2015 | 12/21/2015 | 12/21/2015 | 04/12/2016 |  |  | 04/12/2016 | 06/17/2016 | 06/17/2016 | 07/19/2016 | 07/23/2016 | 12/31/9999
31098259 | OCCC SALINAS 1106 WIRE DOWN FCO56459 | 08W | CC | Completion | ECES_CA1/CLSD | 07/23/2016 | 09/02/2014 | 07/06/2015 | 07/06/2015 | 07/24/2015 | 07/24/2015 | 07/29/2015 | 07/31/2015 | 09/15/2015 | 09/15/2015 | 11/19/2015 |  |  | 11/19/2015 | 04/13/2016 |  |  | 04/13/2016 | 06/16/2016 | 06/16/2016 | 07/19/2016 | 07/23/2016 | 12/31/9999
31098360 | OCCC XGONZALES 1104 WIRE DOWN FCO 5005 | 08W | CC | Completion | ECES_CA1/CLSD | 07/23/2016 | 09/02/2014 | 04/27/2015 | 04/27/2015 | 05/14/2015 | 05/14/2015 | 06/13/2015 | 07/09/2015 | 07/10/2015 | 07/10/2015 | 11/04/2015 | 11/04/2015 | 11/19/2015 | 11/19/2015 | 04/14/2016 |  |  | 04/14/2016 | 06/20/2016 | 06/20/2016 | 07/19/2016 | 07/23/2016 | 12/31/9999
31098626 | CLARKSVILLE 2104 RECONDUCTOR -PH 3 Y2018 | 08W | SI | Post-Doc | ECES_CA1/FICL | 01/05/2021 | 11/03/2017 | 04/16/2018 | 04/16/2018 | 05/31/2018 | 05/31/2018 | 06/20/2018 | 06/24/2018 | 09/18/2018 | 09/18/2018 | 04/13/2020 | 04/13/2020 | 11/20/2020 | 11/20/2020 | 11/23/2020 | 11/01/2017 | 11/03/2017 | 11/23/2020 | 01/05/2021 | 01/05/2021 | 12/31/9999
31098634 | +MESA 1102 WIREDOWN (OSO FLACO TAP) | 08W | LP | Completion | ECES_CA1/CLSD | 06/18/2016 | 09/03/2014 | 05/07/2015 | 05/07/2015 | 06/16/2015 | 06/16/2015 | 07/23/2015 | 08/11/2015 | 08/27/2015 | 08/27/2015 | 09/03/2015 | 09/03/2015 | 11/04/2015 | 11/04/2015 | 04/13/2016 | 08/07/2015 | 08/11/2015 | 04/13/2016 | 06/01/2016 | 06/01/2016 | 06/13/2016 | 06/18/2016 | 12/31/9999
31100467 | OCGC ZAMORA 1105 RECONDUCTOR 3 SPANS | 08W | SI | Completion | ECES_CA1/CLSD | 02/18/2017 | 09/11/2014 | 03/02/2015 | 03/02/2015 | 05/28/2015 | 06/09/2015 | 06/18/2015 | 06/24/2015 | 12/29/2015 | 12/29/2015 | 01/18/2016 | 01/18/2016 | 04/14/2016 | 01/18/2017 | 02/17/2017 | 06/01/2015 | 06/09/2015 | 05/11/2016 | 09/13/2016 | 09/13/2016 | 10/13/2016 | 02/18/2017 | 12/31/9999
31102548 | OC4 COTTONWOOD 1102-RECON 918' | 08W | NV | Completion | ECES_CA1/CLSD | 06/25/2016 | 09/23/2014 | 01/19/2015 | 01/19/2015 | 03/12/2015 | 03/12/2015 | 03/31/2015 | 05/22/2015 | 05/27/2015 | 05/27/2015 | 07/06/2015 | 07/06/2015 | 08/17/2015 | 08/17/2015 | 09/09/2015 |  |  | 09/09/2015 | 04/04/2016 | 04/04/2016 | 06/20/2016 | 06/25/2016 | 12/31/9999
31102963 | +SISQUOC 1104 WD (ORCUTT-GAREY RD) | 08W | LP | Completion | ECES_CA1/CLSD | 10/15/2016 | 09/24/2014 | 05/07/2015 | 05/07/2015 | 06/12/2015 | 06/12/2015 | 06/26/2015 | 06/29/2015 | 07/29/2015 | 07/29/2015 | 08/25/2015 | 08/25/2015 | 05/06/2016 | 05/06/2016 | 06/03/2016 |  |  | 06/03/2016 | 09/08/2016 | 09/08/2016 | 10/14/2016 | 10/15/2016 | 12/31/9999
31109716 | 2016 GUERNSEY 1104 ANNEALED RECOND | 08W | FR | Completion | ECES_CA1/CLSD | 09/12/2020 | 10/24/2014 | 12/01/2015 | 01/05/2016 | 01/22/2016 | 01/22/2016 | 02/25/2016 | 02/29/2016 | 08/11/2016 | 08/11/2016 | 08/30/2016 | 08/30/2016 | 10/27/2016 | 08/04/2020 | 09/10/2020 | 12/29/2015 | 01/05/2016 | 11/01/2016 | 02/27/2017 | 11/15/2017 | 12/14/2017 | 09/12/2020 | 12/31/9999
31111367 | OCGC XR CONDCTR 4 SPANS @TROUT G&OSPREY | 08W | CC | Completion | ECES_CA1/CLSD | 07/20/2019 | 10/29/2014 | 04/23/2015 | 04/23/2015 | 04/28/2015 | 04/28/2015 | 05/08/2015 | 05/13/2015 | 06/29/2015 | 06/29/2015 | 09/11/2015 | 09/11/2015 | 10/21/2015 | 06/25/2019 | 07/17/2019 |  |  | 04/15/2016 | 06/03/2016 | 12/16/2016 | 01/09/2017 | 07/20/2019 | 12/31/9999
31112500 | OCGC RECON 780FT OF 4ACSR MONTE RIO 1111 | 08W | SO | Completion | ECES_CA1/CLSD | 11/18/2017 | 11/03/2014 | 11/19/2015 | 02/20/2016 | 03/03/2016 | 03/03/2016 | 03/11/2016 | 03/16/2016 | 06/20/2016 | 06/20/2016 | 07/04/2016 | 07/04/2016 | 11/07/2016 | 11/07/2016 | 11/14/2016 | 02/18/2016 | 02/20/2016 | 11/14/2016 | 01/19/2017 | 10/20/2017 | 11/16/2017 | 11/18/2017 | 12/31/9999
31113693 | OCCC DOLAN RD 1104 WIREDOWN COOPER RD | 08W | CC | Completion | ECES_CA1/CLSD | 12/17/2016 | 11/07/2014 | 02/12/2016 | 02/12/2016 | 02/12/2016 | 02/12/2016 | 03/10/2016 | 03/10/2016 | 03/22/2016 | 03/22/2016 | 06/15/2016 | 06/15/2016 | 07/01/2016 | 07/01/2016 | 08/17/2016 |  |  | 08/17/2016 | 11/08/2016 | 11/08/2016 | 12/14/2016 | 12/17/2016 | 12/31/9999
31115088 | OCGC RECON 900FT 4CU/4/0ALTW FTROSS 1121 | 08W | SO | Completion | ECES_CA1/CLSD | 10/28/2017 | 11/14/2014 | 11/19/2015 | 02/20/2016 | 02/22/2016 | 02/22/2016 | 02/22/2016 | 03/03/2016 | 04/08/2016 | 04/08/2016 | 10/05/2016 | 10/05/2016 | 12/06/2016 | 12/06/2016 | 12/09/2016 | 02/18/2016 | 02/20/2016 | 12/09/2016 | 01/20/2017 | 09/18/2017 | 10/24/2017 | 10/28/2017 | 12/31/9999
31115947 | EL NIDO 1103 REPLACE ANNEALTED 650FT | 08W | YO | Completion | ECES_CA1/CLSD | 11/19/2016 | 11/18/2014 | 12/03/2015 | 12/03/2015 | 01/14/2016 | 01/14/2016 | 01/14/2016 | 01/20/2016 | 03/31/2016 | 03/31/2016 | 06/07/2016 | 06/07/2016 | 06/20/2016 | 06/20/2016 | 06/27/2016 |  |  | 06/27/2016 | 10/28/2016 | 10/28/2016 | 11/15/2016 | 11/19/2016 | 12/31/9999
31119865 | OCCC BEL 403 REPLC200FT OH LINE INST C/O | 08W | PN | Completion | ECES_CA1/CLSD | 07/23/2016 | 12/08/2014 | 11/17/2015 | 11/17/2015 | 12/07/2015 | 12/07/2015 | 01/14/2016 | 01/19/2016 | 01/25/2016 | 01/25/2016 | 04/08/2016 | 04/08/2016 | 04/13/2016 | 04/13/2016 | 05/20/2016 |  |  | 05/20/2016 | 06/24/2016 | 06/24/2016 | 07/19/2016 | 07/23/2016 | 12/31/9999
31120755 | RECONDUCTOR ND2101 WIREDOWN | 08W | MI | Completion | ECES_CA1/CLSD | 09/02/2017 | 12/12/2014 | 02/01/2016 | 03/01/2016 | 03/02/2016 | 02/26/2016 | 03/01/2016 | 03/14/2016 | 05/24/2016 | 05/24/2016 | 06/01/2016 | 06/01/2016 | 06/07/2016 | 06/07/2016 | 08/10/2016 |  |  | 08/10/2016 | 10/14/2016 | 10/14/2016 | 08/31/2017 | 09/02/2017 | 12/31/9999
31120911 | X-DOLN RD 1104 WIREDOWN BLNCO ARMSTRNG | 08W | CC | Completion | ECES_CA1/CLSD | 02/18/2017 | 12/12/2014 | 06/16/2016 | 06/16/2016 | 07/06/2016 | 07/06/2016 | 07/19/2016 | 07/22/2016 | 08/01/2016 | 08/01/2016 | 08/30/2016 | 08/30/2016 | 09/01/2016 | 09/01/2016 | 09/16/2016 |  |  | 09/16/2016 | 12/23/2016 | 12/23/2016 | 02/17/2017 | 02/18/2017 | 12/31/9999
31120912 | X-DOLAN RD 1101 WIREDWN STRAWBRRY CYN | 08W | CC | Completion | ECES_CA1/CLSD | 10/28/2017 | 01/28/2015 | 02/18/2016 | 02/18/2016 | 04/23/2016 | 04/23/2016 | 05/02/2016 | 05/05/2016 | 06/06/2016 | 06/06/2016 | 08/22/2016 | 08/22/2016 | 09/20/2016 | 09/20/2016 | 09/28/2016 |  |  | 09/28/2016 | 12/22/2016 | 09/18/2017 | 10/24/2017 | 10/28/2017 | 12/31/9999
31121472 | +OCEANO 1104 WD 14-0067445 | 08W | LP | Completion | ECES_CA1/CLSD | 07/21/2018 | 12/17/2014 | 01/15/2016 | 05/17/2016 | 05/17/2016 | 04/20/2016 | 04/21/2016 | 05/18/2016 | 08/31/2016 | 08/31/2016 | 09/29/2016 | 09/29/2016 | 09/26/2017 | 09/26/2017 | 09/28/2017 | 04/15/2016 | 04/20/2016 | 09/28/2017 | 10/12/2017 | 10/12/2017 | 07/19/2018 | 07/21/2018 | 12/31/9999
31121571 | REPL OH WIRE PORT CHICAGO W/O NICHOLS | 08W | DI | Completion | ECES_CA1/CLSD | 03/04/2018 | 03/01/2016 | 03/07/2016 | 03/07/2016 | 09/09/2016 | 09/09/2016 | 11/16/2016 | 11/18/2016 | 02/27/2017 | 02/27/2017 | 03/28/2017 | 03/28/2017 | 05/24/2017 | 01/24/2018 | 03/02/2018 | 02/20/2016 | 03/01/2016 | 07/03/2017 | 08/09/2017 | 08/09/2017 | 09/13/2017 | 03/04/2018 | 12/31/9999
31122088 | KINGSBRG 1114 600' RECOND WIREDOWN | 08W | FR | Completion | ECES_CA1/CLSD | 08/27/2016 | 12/18/2014 | 11/04/2015 | 11/04/2015 | 11/05/2015 | 11/05/2015 | 12/31/2015 | 12/31/2015 | 01/06/2016 | 01/06/2016 | 03/22/2016 | 03/22/2016 | 04/08/2016 | 04/08/2016 | 05/09/2016 |  |  | 05/09/2016 | 07/27/2016 | 07/27/2016 | 08/23/2016 | 08/27/2016 | 12/31/9999
31122833 | OCCC BASALT 1106 WIRE DWN FUSE 1157 ZONE | 08W | NB | Completion | ECES_CA1/CLSD | 12/17/2016 | 12/23/2014 | 10/21/2015 | 10/21/2015 | 12/03/2015 | 12/03/2015 | 01/08/2016 | 01/28/2016 | 06/08/2016 | 06/08/2016 | 07/11/2016 | 07/11/2016 | 08/17/2016 | 08/17/2016 | 09/10/2016 | 01/20/2016 | 01/28/2016 | 09/10/2016 | 12/05/2016 | 12/05/2016 | 12/14/2016 | 12/17/2016 | 12/31/9999
31124815 | OCCC X-SLDD 1114 WREDWN RECND. S/O HY101 | 08W | CC | Completion | ECES_CA1/CLSD | 02/06/2021 | 01/05/2015 | 02/01/2016 | 02/01/2016 | 03/16/2016 | 03/16/2016 | 03/28/2016 | 05/12/2016 | 05/16/2016 | 05/16/2016 | 06/06/2016 | 06/06/2016 | 06/20/2016 | 11/30/2020 | 02/05/2021 | 05/02/2016 | 05/12/2016 | 08/16/2016 | 11/01/2016 | 11/01/2016 | 12/14/2016 | 02/06/2021 | 12/31/9999
31124819 | OCCC KING CITY 1106 WD 14-0067419 | 08W | CC | Completion | ECES_CA1/CLSD | 04/22/2017 | 01/05/2015 | 02/01/2016 | 02/01/2016 | 03/07/2016 | 03/07/2016 | 03/18/2016 | 03/21/2016 | 06/09/2016 | 06/09/2016 | 06/29/2016 | 06/29/2016 | 08/01/2016 | 01/05/2017 | 02/14/2017 |  |  | 08/29/2016 | 11/26/2016 | 02/14/2017 | 04/19/2017 | 04/22/2017 | 12/31/9999
31125443 | OCLH PASO ROBLES 1103 WD 14-0066395 | 08W | LP | Completion | ECES_CA1/CLSD | 03/25/2017 | 01/06/2015 | 03/23/2016 | 03/23/2016 | 06/14/2016 | 07/01/2016 | 07/15/2016 | 07/20/2016 | 08/03/2016 | 08/03/2016 | 10/24/2016 | 10/24/2016 | 11/30/2016 | 11/30/2016 | 02/10/2017 | 06/22/2016 | 07/01/2016 | 02/10/2017 | 03/01/2017 | 03/01/2017 | 03/20/2017 | 03/25/2017 | 12/31/9999
31125646 | OCGC D 2350' EXCESS SLICES SW6041 | 08W | HB | Completion | ECES_CA1/CLSD | 12/17/2016 | 01/07/2015 | 11/09/2015 | 11/09/2015 | 11/23/2015 | 11/23/2015 | 12/09/2015 | 12/22/2015 | 01/13/2016 | 01/13/2016 | 06/02/2016 | 06/02/2016 | 06/27/2016 | 06/27/2016 | 08/11/2016 |  |  | 08/11/2016 | 11/02/2016 | 11/02/2016 | 12/14/2016 | 12/17/2016 | 12/31/9999
31126827 | OCGC EP RECONDUCTOR WILLIAMS 1102- Y2016 | 08W | SA | Post-Doc | ECES_CA1/PREC | 09/15/2017 | 01/09/2015 | 10/12/2015 | 10/12/2015 | 12/30/2015 | 01/12/2016 | 01/27/2016 | 03/11/2016 | 03/11/2016 | 03/11/2016 | 05/30/2016 | 05/30/2016 | 06/16/2016 | 06/16/2016 | 08/10/2016 | 01/11/2016 | 01/12/2016 | 08/10/2016 | 11/05/2016 | 11/05/2016 | 01/25/2017 | 01/28/2017 | 09/15/2017
31128279 | OCGC SPAULDING 1101 WIREDOWN SS OF 6607 | 08W | SI | Completion | ECES_CA1/CLSD | 01/28/2017 | 01/15/2015 | 11/23/2015 | 11/23/2015 | 12/08/2015 | 12/08/2015 | 01/20/2016 | 01/21/2016 | 01/21/2016 | 01/21/2016 | 07/13/2016 | 07/13/2016 | 09/01/2016 | 09/01/2016 | 09/16/2016 |  |  | 09/16/2016 | 12/21/2016 | 12/21/2016 | 01/25/2017 | 01/28/2017 | 12/31/9999
31129830 | OCCC BIG TREES 402 _ 14-0076789 PHASE 1 | 08W | CC | Completion | ECES_CA1/CLSD | 03/10/2018 | 01/22/2015 | 01/14/2016 | 05/01/2016 | 05/19/2016 | 05/19/2016 | 05/27/2016 | 05/31/2016 | 08/22/2016 | 08/22/2016 | 09/06/2016 | 09/06/2016 | 10/24/2016 | 01/24/2018 | 03/07/2018 | 04/14/2016 | 05/01/2016 | 11/30/2016 | 01/23/2017 | 01/23/2017 | 02/17/2017 | 03/10/2018 | 12/31/9999
31132867 | HMB1101 REPLACE OH LINE SKYLINE BLVD | 08W | PN | Completion | ECES_CA1/CLSD | 01/12/2019 | 02/05/2015 | 10/31/2017 | 10/31/2017 | 10/31/2017 | 01/17/2018 | 04/13/2018 | 07/03/2018 | 07/05/2018 | 07/05/2018 | 07/09/2018 | 07/09/2018 | 08/06/2018 | 08/06/2018 | 08/31/2018 | 12/27/2017 | 01/17/2018 | 08/31/2018 | 10/02/2018 | 10/02/2018 | 01/09/2019 | 01/12/2019 | 12/31/9999
31133991 | OCGC WIRE DOWN-RECONDUCTOR LIVE OAK 1102 | 08W | SI | Completion | ECES_CA1/CLSD | 12/17/2016 | 02/12/2015 | 11/23/2015 | 03/01/2016 | 03/01/2016 | 03/01/2016 | 03/02/2016 | 03/02/2016 | 05/13/2016 | 05/13/2016 | 07/19/2016 | 07/19/2016 | 07/28/2016 | 07/28/2016 | 08/26/2016 | 02/22/2016 | 03/01/2016 | 08/26/2016 | 11/28/2016 | 11/28/2016 | 12/14/2016 | 12/17/2016 | 12/31/9999
31134351 | +MESA 1102 (JOSHUA ST & ORCHARD RD) | 08W | LP | Completion | ECES_CA1/CLSD | 02/18/2017 | 02/13/2015 | 12/29/2015 | 12/29/2015 | 02/17/2016 | 02/17/2016 | 02/22/2016 | 02/25/2016 | 02/29/2016 | 02/29/2016 | 06/23/2016 | 06/23/2016 | 09/30/2016 | 09/30/2016 | 10/06/2016 |  |  | 10/06/2016 | 01/23/2017 | 01/23/2017 | 02/17/2017 | 02/18/2017 | 12/31/9999
31136738 | X-KING CITY 1102 WD 15-0009162 | 08W | CC | Completion | ECES_CA1/CLSD | 09/02/2017 | 02/24/2015 | 04/15/2016 | 04/15/2016 | 05/27/2016 | 05/27/2016 | 05/27/2016 | 05/31/2016 | 06/08/2016 | 06/08/2016 | 06/09/2016 |  |  | 06/09/2016 | 08/10/2016 |  |  | 08/10/2016 | 10/19/2016 | 10/19/2016 | 08/29/2017 | 09/02/2017 | 12/31/9999
31139913 | +SANTA MARIA 1110 ANNEALED RIVER X-ING | 08W | LP | Completion | ECES_CA1/CLSD | 01/28/2017 | 03/10/2015 | 06/01/2015 | 06/01/2015 | 06/18/2015 | 06/18/2015 | 06/18/2015 | 06/19/2015 | 08/28/2015 | 08/28/2015 | 09/28/2015 | 09/28/2015 | 12/09/2016 | 12/09/2016 | 12/10/2016 |  |  | 12/10/2016 | 12/13/2016 | 12/13/2016 | 01/25/2017 | 01/28/2017 | 12/31/9999
31140055 | OCGC RECONDUCTOR PUEBLO 2103 AT SW 7927 | 08W | NB | Completion | ECES_CA1/CLSD | 02/11/2017 | 03/10/2015 | 04/19/2016 | 07/21/2016 | 07/28/2016 | 07/28/2016 | 07/29/2016 | 08/01/2016 | 09/21/2016 | 09/21/2016 | 11/21/2016 | 11/21/2016 | 12/16/2016 | 12/16/2016 | 12/22/2016 | 07/19/2016 | 07/21/2016 | 12/22/2016 | 02/02/2017 | 02/02/2017 | 02/06/2017 | 02/11/2017 | 12/31/9999
31143734 | 2016 REEDLEY 1104 WIRE DOWN RECONDUCT | 08W | FR | Completion | ECES_CA1/CLSD | 01/14/2017 | 05/11/2016 | 06/03/2016 | 06/03/2016 | 06/28/2016 | 06/28/2016 | 06/28/2016 | 07/11/2016 | 08/16/2016 | 08/16/2016 | 09/12/2016 | 09/12/2016 | 09/29/2016 | 12/08/2016 | 12/19/2016 |  |  | 10/05/2016 | 12/08/2016 | 12/19/2016 | 01/09/2017 | 01/14/2017 | 12/31/9999
31144558 | WDN 15-0013313 CE2105-HUBBARD GULCH | 08W | CC | Completion | ECES_CA1/CLSD | 02/04/2017 | 03/31/2015 | 03/30/2016 | 03/30/2016 | 05/31/2016 | 05/31/2016 | 06/10/2016 | 06/10/2016 | 08/12/2016 | 08/12/2016 | 09/07/2016 | 09/07/2016 | 11/10/2016 | 11/10/2016 | 11/17/2016 |  |  | 11/17/2016 | 02/02/2017 | 02/02/2017 | 02/02/2017 | 02/04/2017 | 12/31/9999
31144778 | OCGC TRINIDAD 1102 EXCESSIVE SPLICES | 08W | HB | Completion | ECES_CA1/CLSD | 09/23/2017 | 03/31/2015 | 10/26/2015 | 02/09/2016 | 02/09/2016 |  |  | 02/16/2016 | 04/19/2016 | 04/19/2016 | 06/21/2016 | 06/21/2016 | 09/22/2016 | 08/16/2017 | 09/18/2017 | 01/25/2016 | 02/09/2016 | 09/28/2016 | 12/27/2016 | 12/27/2016 | 01/25/2017 | 09/23/2017 | 12/31/9999
31145622 | OCGC 2016 CORCORAN 1108 RECOND WIREDOWN | 08W | FR | Completion | ECES_CA1/CLSD | 07/14/2018 | 04/03/2015 | 01/04/2016 | 04/06/2016 | 06/27/2016 | 06/27/2016 | 07/18/2016 | 08/02/2016 | 09/15/2016 | 09/15/2016 | 10/24/2016 | 10/24/2016 | 01/31/2017 | 05/21/2018 | 06/11/2018 | 04/04/2016 | 04/06/2016 | 02/07/2017 | 03/21/2017 | 06/11/2018 | 07/09/2018 | 07/14/2018 | 12/31/9999
31150684 | MORAGA 1103 RECNDUCTOR 350' (2SPANS) | 08W | DI | Completion | ECES_CA1/CLSD | 01/29/2018 | 04/24/2015 | 05/09/2016 | 05/09/2016 | 06/08/2016 | 06/08/2016 | 08/01/2016 | 02/13/2017 | 02/14/2017 | 02/14/2017 | 03/09/2017 | 03/09/2017 | 03/30/2017 | 03/30/2017 | 04/11/2017 | 08/08/2016 | 08/09/2016 | 04/11/2017 | 05/31/2017 | 12/14/2017 | 01/23/2018 | 01/29/2018 | 12/31/9999
31152787 | OCLH CLOVIS 2110 WIRE DOWN RECONDUCTOR | 08W | FR | Completion | ECES_CA1/CLSD | 07/25/2020 | 05/05/2015 | 12/31/2015 | 12/31/2015 | 02/04/2016 | 04/12/2016 | 04/21/2016 | 04/21/2016 | 09/09/2016 |  |  | 09/09/2016 | 12/27/2016 | 04/20/2020 | 07/20/2020 | 03/31/2016 | 04/12/2016 | 01/03/2017 | 01/26/2017 | 10/20/2017 | 11/16/2017 | 07/25/2020 | 12/31/9999
31153724 | OCGC BANTA 1103 RECOND 968FT 6CU | 08W | ST | Completion | ECES_CA1/CLSD | 12/17/2016 | 05/08/2015 | 03/03/2016 | 03/03/2016 | 03/30/2016 | 03/30/2016 | 04/22/2016 | 05/11/2016 | 06/09/2016 | 06/09/2016 | 06/17/2016 | 06/17/2016 | 07/15/2016 | 07/15/2016 | 08/24/2016 |  |  | 08/24/2016 | 12/05/2016 | 12/05/2016 | 12/14/2016 | 12/17/2016 | 12/31/9999
31154886 | OCGC EP RECONDUCTOR ARBUCKLE 1102 -Y2016 | 08W | SA | Completion | ECES_CA1/CLSD | 11/19/2016 | 05/14/2015 | 03/03/2016 | 03/03/2016 | 04/01/2016 | 04/01/2016 | 04/25/2016 | 05/13/2016 | 05/16/2016 | 05/16/2016 | 06/21/2016 | 06/21/2016 | 07/01/2016 | 07/01/2016 | 08/19/2016 |  |  | 08/19/2016 | 11/03/2016 | 11/03/2016 | 11/15/2016 | 11/19/2016 | 12/31/9999
31156130 | SAN ARDO 1102 WD #15-0024843 | 08W | CC | Completion | ECES_CA1/CLSD | 03/25/2017 | 05/20/2015 | 05/09/2016 | 05/09/2016 | 06/06/2016 | 06/06/2016 | 06/20/2016 | 06/24/2016 | 08/25/2016 | 08/25/2016 | 10/13/2016 |  |  | 10/13/2016 | 10/24/2016 |  |  | 10/24/2016 | 01/20/2017 | 01/20/2017 | 03/20/2017 | 03/25/2017 | 12/31/9999
31157301 | X-RECNDUCTR-POINT M1101_2598 SMITH GRDE | 08W | CC | Completion | ECES_CA1/CLSD | 06/17/2018 | 05/27/2015 | 03/08/2016 | 03/08/2016 | 05/17/2016 | 05/17/2016 | 05/17/2016 | 05/17/2016 | 07/12/2016 | 07/12/2016 | 07/19/2016 | 07/19/2016 | 09/01/2016 | 09/01/2016 | 09/09/2016 |  |  | 09/09/2016 | 02/04/2017 | 02/04/2017 | 06/13/2018 | 06/17/2018 | 12/31/9999
31157545 | OCGC HARDWICK 1102 WIRE DWN RECNDUCTOR | 08W | FR | Completion | ECES_CA1/CLSD | 02/18/2017 | 05/28/2015 | 03/24/2016 | 07/01/2016 | 07/05/2016 | 07/05/2016 | 07/12/2016 | 08/15/2016 | 08/17/2016 | 08/17/2016 | 08/23/2016 | 08/23/2016 | 09/20/2016 | 09/20/2016 | 09/27/2016 | 06/23/2016 | 07/01/2016 | 09/27/2016 | 12/19/2016 | 12/19/2016 | 02/17/2017 | 02/18/2017 | 12/31/9999
31157953 | RECON 1SPAN N/O FISH ROCK GUALALA1112 | 08W | HB | Completion | ECES_CA1/CLSD | 01/28/2017 | 05/29/2015 | 03/31/2016 | 03/31/2016 | 04/01/2016 | 04/01/2016 | 04/01/2016 |  |  | 04/01/2016 | 06/13/2016 | 06/13/2016 | 06/24/2016 | 06/24/2016 | 08/11/2016 |  |  | 08/11/2016 | 11/02/2016 | 11/02/2016 | 01/25/2017 | 01/28/2017 | 12/31/9999
31163618 | SOLEDAD 2102 RECONDUCTORING JOB | 08W | CC | Completion | ECES_CA1/CLSD | 02/06/2021 | 06/24/2015 | 05/23/2016 | 05/23/2016 | 06/13/2016 | 06/13/2016 | 06/30/2016 | 06/30/2016 | 08/15/2016 | 08/15/2016 | 09/19/2016 | 09/19/2016 | 08/10/2017 | 11/30/2020 | 02/05/2021 |  |  | 08/11/2017 | 09/14/2017 | 09/14/2017 | 11/21/2017 | 02/06/2021 | 12/31/9999
31163857 | X LOS OSITOS 2102 WDWN_15-0036239 | 08W | CC | Completion | ECES_CA1/CLSD | 12/23/2017 | 06/24/2015 | 04/06/2016 |  |  | 04/06/2016 | 05/25/2016 | 05/25/2016 | 05/25/2016 | 05/25/2016 | 06/07/2017 | 06/07/2017 | 08/03/2017 | 08/03/2017 | 08/07/2017 |  |  | 08/07/2017 | 11/10/2017 | 11/10/2017 | 12/18/2017 | 12/23/2017 | 12/31/9999
31169728 | 2017 GRIZZLY PEAK REPL #6 CU-UWF | 08W | EB | Completion | ECES_CA2/CLSD | 01/18/2020 | 07/17/2015 | 09/20/2017 | 09/20/2017 | 10/04/2017 | 10/04/2017 | 05/02/2018 | 08/09/2018 | 08/10/2018 | 08/10/2018 | 08/30/2018 | 08/30/2018 | 02/08/2019 | 12/23/2019 | 01/17/2020 |  |  | 03/06/2019 | 04/10/2019 | 04/10/2019 | 04/11/2019 | 01/18/2020 | 12/31/9999
31169729 | OCGCABILITY 2017 D1112/K1101 UWF | 08W | EB | Completion | ECES_CA2/CLSD | 03/23/2019 | 07/17/2015 | 09/14/2017 | 09/14/2017 | 09/14/2017 | 09/14/2017 | 11/08/2017 | 04/17/2018 | 04/29/2018 | 04/29/2018 | 05/17/2018 | 05/17/2018 | 07/23/2018 | 07/23/2018 | 07/24/2018 |  |  | 07/24/2018 | 08/28/2018 | 08/28/2018 | 03/18/2019 | 03/23/2019 | 12/31/9999
31170650 | X-SAN BENITO 2101 WIREDOWN 15-0039468 | 08W | CC | Completion | ECES_CA1/CLSD | 12/17/2016 | 07/21/2015 | 04/12/2016 | 04/12/2016 | 05/10/2016 | 05/10/2016 | 05/27/2016 | 06/02/2016 | 06/08/2016 | 06/08/2016 | 06/23/2016 | 06/23/2016 | 07/11/2016 | 07/11/2016 | 08/23/2016 |  |  | 08/23/2016 | 11/16/2016 | 11/16/2016 | 12/14/2016 | 12/17/2016 | 12/31/9999
31173660 | OCGC SANTA ROSA A 1108 RECOND 6SPANS | 08W | SO | Completion | ECES_CA2/CLSD | 02/06/2021 | 08/04/2015 | 01/15/2016 | 01/15/2016 | 03/25/2016 | 03/25/2016 | 03/25/2016 | 04/04/2016 | 07/07/2016 | 07/07/2016 | 07/20/2016 | 07/20/2016 | 08/15/2016 | 08/15/2016 | 09/13/2016 |  |  | 09/13/2016 | 12/16/2016 | 12/16/2016 | 02/03/2021 | 02/06/2021 | 12/31/9999
31175817 | +OCEANO 1108 WIREDOWN 15-0043519 | 08W | LP | Completion | ECES_CA1/CLSD | 02/11/2017 | 08/13/2015 | 04/29/2016 | 07/30/2016 | 08/01/2016 | 08/01/2016 | 08/04/2016 | 08/19/2016 | 09/01/2016 | 09/01/2016 | 10/10/2016 | 10/10/2016 | 11/30/2016 | 11/30/2016 | 12/01/2016 | 07/29/2016 | 07/30/2016 | 12/01/2016 | 01/18/2017 | 01/18/2017 | 02/07/2017 | 02/11/2017 | 12/31/9999
31204479 | RECOND 3 SPANS GARDEN TRACT | 08W | EB | Completion | ECES_CA1/CLSD | 01/20/2018 | 12/08/2015 | 12/09/2016 | 12/09/2016 | 12/09/2016 | 03/21/2017 | 04/06/2017 | 08/16/2017 | 09/22/2017 | 09/22/2017 | 11/13/2017 |  |  | 12/15/2017 | 12/15/2017 | 03/10/2017 | 03/21/2017 | 12/12/2017 | 12/14/2017 | 12/15/2017 | 01/19/2018 | 01/20/2018 | 12/31/9999
31204706 | MVWF THROCKMORTON LANE ALTO 1124 | 08W | NB | Completion | ECES_CA1/CLSD | 11/04/2019 | 12/07/2015 | 10/06/2016 | 12/21/2016 | 07/12/2017 | 07/12/2017 | 07/12/2017 | 07/18/2017 | 08/22/2017 | 08/26/2017 | 09/01/2017 | 09/01/2017 | 07/31/2018 | 11/04/2019 | 11/04/2019 | 12/14/2016 | 12/21/2016 | 12/12/2018 | 12/17/2018 | 12/17/2018 | 04/17/2019 | 11/04/2019 | 12/31/9999
31205198 | MVWF 206 REED ST, COUNTY, ALTO 1125 | 08W | NB | Completion | ECES_CA1/CLSD | 11/04/2019 | 12/10/2015 | 10/05/2016 | 01/10/2017 | 07/13/2017 | 07/13/2017 | 08/14/2017 | 06/06/2018 | 06/25/2018 | 06/28/2018 | 07/17/2018 | 07/17/2018 | 07/18/2018 | 11/04/2019 | 11/04/2019 | 01/05/2017 | 01/10/2017 | 10/03/2018 | 11/30/2018 | 11/30/2018 | 02/21/2019 | 11/04/2019 | 12/31/9999
31205343 | MVWF 388 SUMMIT AVE, CITY, ALTO 1124 | 08W | NB | Completion | ECES_CA1/CLSD | 11/04/2019 | 12/10/2015 | 10/05/2016 | 01/10/2017 | 08/16/2017 | 08/16/2017 | 08/24/2017 | 03/07/2018 | 05/31/2018 | 05/31/2018 | 06/29/2018 | 06/29/2018 | 07/31/2018 | 11/04/2019 | 11/04/2019 | 01/05/2017 | 01/10/2017 | 11/05/2018 | 12/17/2018 | 12/17/2018 | 03/21/2019 | 11/04/2019 | 12/31/9999
31205418 | MVWF BROOKLINE AVE, COUNTY, ALTO 1125 | 08W | NB | Completion | ECES_CA1/CLSD | 04/20/2019 | 12/11/2015 | 01/02/2017 | 02/07/2017 | 07/13/2017 | 07/13/2017 | 08/03/2017 | 08/09/2017 | 02/02/2018 | 02/02/2018 | 07/17/2018 | 07/17/2018 | 07/31/2018 | 07/31/2018 | 10/03/2018 | 01/31/2017 | 02/07/2017 | 10/03/2018 | 12/17/2018 | 12/17/2018 | 04/17/2019 | 04/20/2019 | 12/31/9999
31205937 | 109 HELENS LN,CITY/CNTY,ALTO | 08W | NB | Completion | ECES_CA1/CLSD | 03/23/2019 | 12/14/2015 | 12/28/2016 | 03/22/2017 | 09/25/2017 | 09/25/2017 | 10/03/2017 | 10/04/2017 | 11/30/2017 | 11/30/2017 | 07/02/2018 | 07/02/2018 | 12/17/2018 | 02/28/2019 | 03/20/2019 | 03/18/2017 | 03/22/2017 | 12/18/2018 | 02/25/2019 |  |  | 03/23/2019 | 12/31/9999
31206678 | MVWF SEQUOIA VLY RD CTY/CNTY AL1125/1124 | 08W | NB | Post-Doc | ECES_CA1/FICL | 05/21/2020 | 12/16/2015 | 08/19/2016 | 05/17/2018 | 06/12/2018 | 06/12/2018 | 06/12/2018 | 07/31/2018 | 07/31/2018 | 07/31/2018 | 05/15/2019 |  |  | 05/15/2019 | 05/04/2020 | 11/19/2016 | 11/22/2016 | 05/04/2020 | 05/21/2020 | 05/21/2020 | 12/31/9999
31206912 | X WDN 15-0073161 CE2103-OLD GRAHM HL R | 08W | CC | Completion | ECES_CA1/CLSD | 12/28/2019 | 12/17/2015 | 01/13/2017 | 01/13/2017 | 01/13/2017 | 05/11/2017 | 06/01/2017 | 07/21/2017 | 08/07/2017 | 08/07/2017 | 06/04/2018 | 06/04/2018 | 07/30/2018 | 11/19/2019 | 12/22/2019 | 04/14/2017 | 05/11/2017 | 07/31/2018 | 08/28/2018 | 09/12/2018 | 11/29/2018 | 12/28/2019 | 12/31/9999
31207089 | ESA BOULEVARD ORNE AVE, LARKSPUR GB 1103 | 08W | NB | Completion | ECES_CA1/CLSD | 06/29/2019 | 12/16/2015 | 02/06/2017 | 03/22/2017 | 10/03/2017 | 10/03/2017 | 10/26/2017 | 10/30/2017 | 12/26/2017 | 12/26/2017 | 07/02/2018 | 07/02/2018 | 12/18/2018 | 05/14/2019 | 06/22/2019 | 03/18/2017 | 03/22/2017 | 12/19/2018 | 12/21/2018 | 12/21/2018 | 02/25/2019 | 06/29/2019 | 12/31/9999
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 | 08W | NB | Documentation | ECES_CA1/DOCC | 05/05/2020 | 01/31/2019 | 02/05/2019 | 02/05/2019 | 06/10/2019 | 09/27/2017 | 09/27/2017 | 06/13/2019 | 06/19/2019 | 06/19/2019 | 11/18/2019 | 11/18/2019 | 05/05/2020 | 05/05/2020 | 12/31/9999 | 03/18/2017 | 03/22/2017
31207126 | MVWF PANORAMIC HWY, COUNTY, ALTO 1125 | 08W | NB | Completion | ECES_CA1/CLSD | 07/20/2019 | 12/17/2015 | 10/05/2016 | 01/10/2017 | 09/12/2017 | 09/12/2017 | 09/12/2017 | 09/14/2017 | 10/31/2017 | 10/31/2017 | 06/01/2018 | 06/01/2018 | 07/19/2018 | 07/19/2018 | 10/04/2018 | 01/05/2017 | 01/10/2017 | 10/04/2018 | 12/17/2018 | 12/17/2018 | 07/16/2019 | 07/20/2019 | 12/31/9999
31207128 | *CANC* MVWF ALTO 1125 MUIR WOOD DR *CANC | 08W | NB | Completion | ECES_CA1/CLSD | 05/03/2020 | 04/03/2020 | 04/03/2020 | [12 empty] | 04/03/2020 | 04/04/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/04/2020 | 05/03/2020
31207160 | +SANTA MARIA 1108 WD 15-076543 | 08W | LP | Completion | ECES_CA1/CLSD | 12/22/2018 | 12/17/2015 | 09/21/2016 | 09/21/2016 | 09/21/2016 | 01/07/2017 | 05/15/2017 | 05/15/2017 | 05/25/2017 | 05/25/2017 | 06/30/2017 | 06/30/2017 | 10/10/2017 | 11/08/2018 | 12/20/2018 | 12/21/2016 | 01/07/2017 | 10/11/2017 | 11/13/2017 | 11/13/2017 | 01/16/2018 | 12/22/2018 | 12/31/9999
31209950 | R7 RECON POTTER VLY 1105 ( VAN ARSDALE) | 08W | HB | Documentation | ECES_CA1/DOCC | 09/05/2019 | 10/03/2017 | 04/30/2018 | 01/10/2019 | 04/10/2019 | 04/10/2019 | 04/11/2019 | 04/19/2019 | 06/11/2019 | 06/11/2019 | 07/08/2019 | 07/08/2019 | 09/05/2019 | 09/05/2019 | 12/31/9999 | 03/31/2016 | 04/19/2016
31211274 | OCGC PINEDALE 2109 - RECONDUCTOR | 08W | FR | Completion | ECES_CA1/CLSD | 04/07/2018 | 01/08/2016 | 01/04/2017 | 01/04/2017 | 01/04/2017 | 03/01/2017 | 08/02/2017 | 08/03/2017 | 09/14/2017 | 09/14/2017 | 10/02/2017 | 10/02/2017 | 12/19/2017 | 12/19/2017 | 01/11/2018 | 02/28/2017 | 03/01/2017 | 01/11/2018 | 01/19/2018 | 01/19/2018 | 04/04/2018 | 04/07/2018 | 12/31/9999
31211275 | OCGC CANTUNA 1103 - RECONDUCTORING | 08W | FR | Completion | ECES_CA1/CLSD | 09/15/2018 | 01/08/2016 | 01/19/2017 | 01/19/2017 | 01/19/2017 | 04/26/2017 | 07/11/2017 | 07/13/2017 | 10/03/2017 | 10/03/2017 | 12/25/2017 | 12/25/2017 | 01/29/2018 | 08/08/2018 | 09/11/2018 | 04/20/2017 | 04/26/2017 | 01/30/2018 | 02/02/2018 | 02/28/2018 | 04/16/2018 | 09/15/2018 | 12/31/9999
31212864 | LP402 164 SELBY LN ATHERTON | 08W | PN | Completion | ECES_CA1/CLSD | 12/23/2017 | 01/14/2016 | 09/19/2016 | 09/19/2016 | 10/05/2016 | 10/05/2016 | 11/07/2016 | 01/20/2017 | 03/31/2017 | 03/31/2017 | 08/28/2017 | 08/28/2017 | 09/12/2017 | 09/12/2017 | 10/10/2017 | 12/19/2016 | 01/20/2017 | 10/10/2017 | 11/16/2017 | 11/16/2017 | 12/18/2017 | 12/23/2017 | 12/31/9999
31212879 | OCGC RECONDUCTOR 6 CU ON E. NICOLAUS 11 | 08W | SI | Completion | ECES_CA1/CLSD | 01/20/2018 | 01/14/2016 | 01/30/2017 | 01/30/2017 | 01/30/2017 | 05/10/2017 | 05/18/2017 | 05/22/2017 | 05/23/2017 | 05/23/2017 | 10/09/2017 | 10/09/2017 | 12/04/2017 | 12/04/2017 | 12/07/2017 | 05/01/2017 | 05/10/2017 | 12/07/2017 | 12/27/2017 | 12/27/2017 | 01/19/2018 | 01/20/2018 | 12/31/9999
31212922 | +SISQUOC 1104 WD-15-0070918 | 08W | LP | Completion | ECES_CA1/CLSD | 09/16/2017 | 01/14/2016 | 09/21/2016 | 09/21/2016 | 09/21/2016 | 12/23/2016 | 12/23/2016 | 12/23/2016 | 03/21/2017 | 03/21/2017 | 05/01/2017 | 05/01/2017 | 06/28/2017 | 06/28/2017 | 06/29/2017 | 12/21/2016 | 12/23/2016 | 06/29/2017 | 07/27/2017 | 07/27/2017 | 09/12/2017 | 09/16/2017 | 12/31/9999
31213040 | OCGC RECONDUCTOR 6 CU ON OLIVEHURST 1104 | 08W | SI | Completion | ECES_CA1/CLSD | 06/17/2018 | 01/14/2016 | 02/08/2017 | 02/08/2017 | 02/08/2017 | 05/31/2017 | 06/05/2017 | 06/05/2017 | 06/07/2017 | 06/07/2017 | 07/20/2017 | 07/20/2017 | 08/07/2017 | 08/07/2017 | 08/08/2017 | 05/10/2017 | 05/31/2017 | 08/08/2017 | 08/29/2017 | 08/29/2017 | 06/13/2018 | 06/17/2018 | 12/31/9999
31215474 | RECONDUCTOR ROB ROY 2104-MCDONALD RD | 08W | CC | Completion | ECES_CA1/CLSD | 06/20/2020 | 07/19/2018 | 09/26/2018 | 11/15/2018 | 01/09/2019 | 01/09/2019 | 01/31/2019 | 03/28/2019 | 03/28/2019 | 03/28/2019 | 05/02/2019 | 05/02/2019 | 06/11/2019 | 01/28/2020 | 05/19/2020 | 06/16/2018 | 07/19/2018 | 07/22/2019 | 08/06/2019 | 05/19/2020 | 06/17/2020 | 06/20/2020 | 12/31/9999
31216725 | X BEN LOMOND401-RIDGE RD-FUSE6295 | 08W | CC | Completion | ECES_CA1/CLSD | 07/21/2018 | 02/03/2016 | 10/06/2016 | 10/06/2016 | 10/06/2016 | 01/07/2017 | 06/23/2017 | 09/26/2017 | 10/03/2017 | 10/03/2017 | 11/03/2017 | 11/03/2017 | 11/21/2017 | 06/19/2018 | 07/17/2018 | 01/05/2017 | 01/07/2017 | 11/22/2017 | 12/12/2017 | 12/12/2017 | 02/12/2018 | 07/21/2018 | 12/31/9999
31221409 | OCGC X TERMINOUS 1102 REPL. 800FT W/#2AR | 08W | ST | Completion | ECES_CA1/CLSD | 09/15/2018 | 02/25/2016 | 08/22/2016 | 08/22/2016 | 08/22/2016 | 12/14/2016 | 06/19/2017 | 06/19/2017 | 08/25/2017 | 11/02/2017 | 11/08/2017 | 11/08/2017 | 02/05/2018 | 08/08/2018 | 09/11/2018 | 11/22/2016 | 12/14/2016 | 02/12/2018 | 02/15/2018 | 02/15/2018 | 07/11/2018 | 09/15/2018 | 12/31/9999
31222251 | X WDN_16-09640-212 CREST RD OTTER 1101 | 08W | CC | Completion | ECES_CA1/CLSD | 07/21/2018 | 03/01/2016 | 02/10/2017 | 02/10/2017 | 02/10/2017 | 05/13/2017 | 05/25/2017 | 05/25/2017 | 07/21/2017 | 07/21/2017 | 08/21/2017 | 08/21/2017 | 11/06/2017 | 06/19/2018 | 07/17/2018 | 05/12/2017 | 05/13/2017 | 11/07/2017 | 12/05/2017 | 12/05/2017 | 02/13/2018 | 07/21/2018 | 12/31/9999
31229986 | OCGC JACINTO 1101 RECOND 9677'OF 3-6CU | 08W | NV | Completion | ECES_CA1/CLSD | 03/31/2018 | 04/08/2016 | 08/30/2016 | 12/13/2016 | 06/16/2017 | 06/16/2017 | 06/16/2017 | 07/12/2017 | 07/27/2017 | 07/27/2017 | 08/01/2017 | 01/04/2018 | 01/22/2018 | 12/15/2017 | 12/19/2017 | 11/29/2016 | 12/13/2016 | 01/22/2018 | 01/26/2018 | 01/26/2018 | 03/27/2018 | 03/31/2018 | 12/31/9999
31232280 | ZACA 1102 LONG CYN RD, SANTA YNEZ | 08W | LP | Post-Doc | ECES_CA1/FICL | 07/27/2020 | 04/20/2018 | 10/15/2018 | 10/15/2018 | 10/15/2018 | 10/15/2018 | 03/26/2019 | 04/01/2019 | 04/17/2019 | 04/17/2019 | 05/23/2019 | 05/23/2019 | 08/09/2019 | 11/04/2019 | 07/27/2020 | 03/28/2018 | 04/20/2018 | 08/21/2019 | 12/31/9999 | 07/27/2020 | 12/31/9999 | 11/02/2019 | 11/04/2019
31234871 | -RELIAIBLITY 2017 - UWF K1104/X1105/6 | 08W | EB | Completion | ECES_CA2/CLSD | 01/18/2020 | 04/28/2016 | 04/27/2017 | 04/27/2017 | 08/14/2017 | 08/14/2017 | 04/23/2018 | 06/25/2018 | 06/25/2018 | 06/25/2018 | 07/18/2018 | 07/18/2018 | 10/08/2018 | 12/23/2019 | 01/13/2020 |  |  | 10/18/2018 | 02/27/2019 | 02/27/2019 | 04/08/2019 | 01/18/2020 | 12/31/9999
31246140 | WY1105 - RECOND 3000 FT OF 4AR W 2ARTW | 08W | NV | Completion | ECES_CA1/CLSD | 04/13/2019 | 06/07/2016 | 09/25/2017 | 03/26/2018 | 04/16/2018 | 11/09/2017 | 11/28/2017 | 01/30/2018 | 02/21/2018 | 04/16/2018 | 05/28/2018 | 05/28/2018 | 09/20/2018 | 03/13/2019 | 03/21/2019 |  |  | 09/21/2018 | 10/30/2018 | 03/21/2019 | 04/13/2019 | 04/13/2019 | 12/31/9999
31246787 | RECONDUCTOR 4 SPANS - 100 DEODARA WAY | 08W | SF | Initiation | ECES_CA1/UNSE | 06/10/2016 | 06/10/2016 | 12/31/9999
31248532 | CWSP HALF MOON BAY 1101 LS CO4063 | 08W | PN | Completion | ECES_CA1/CLSD | 02/06/2021 | 06/20/2016 | 03/13/2018 | 01/10/2019 | 07/09/2019 | 07/23/2018 | 07/23/2018 | 07/09/2019 | 04/22/2020 | 04/22/2020 | 07/13/2020 | 07/13/2020 | 08/21/2020 | 10/26/2020 | 11/05/2020 | 06/12/2018 | 06/21/2018 | 09/22/2020 | 10/08/2020 | 11/05/2020 | 02/02/2021 | 02/06/2021 | 12/31/9999
31255868 | R2ROB ROY 2104 HIGH SPLICE CABLE REPLACE | 08W | CC | Completion | ECES_CA1/CLSD | 04/13/2019 | 07/06/2016 | 04/30/2018 | 04/30/2018 | 05/14/2018 | 05/14/2018 | 05/15/2018 | 07/17/2018 | 07/25/2018 | 07/25/2018 | 08/09/2018 |  |  | 03/13/2019 | 04/13/2019 |  |  | 08/10/2018 | 08/28/2018 | 09/19/2018 | 10/08/2018 | 04/13/2019 | 12/31/9999
31264915 | R7 RECONDUCTOR WILSON RD- RINCON 1103 | 08W | SO | Completion | ECES_CA1/CLSD | 04/13/2019 | 08/23/2016 | 03/15/2018 | 05/02/2018 | 05/04/2018 | 04/10/2018 | 04/18/2018 | 08/14/2018 | 08/29/2018 | 08/29/2018 | 08/29/2018 |  |  | 03/13/2019 | 03/21/2019 |  |  | 10/03/2018 | 11/30/2018 | 03/21/2019 | 04/13/2019 | 04/13/2019 | 12/31/9999
31269259 | ZACA 1101 FOXEN CYN RD, LOS OLIVOS | 08W | LP | Post-Doc | ECES_CA1/FICL | 05/27/2020 | 06/13/2018 | 10/16/2018 | 10/16/2018 | 10/16/2018 | 10/16/2018 | 03/19/2019 | 04/01/2019 | 04/12/2019 | 04/12/2019 | 05/16/2019 | 05/16/2019 | 08/09/2019 | 01/28/2020 | 05/27/2020 | 06/03/2018 | 06/13/2018 | 08/12/2019 | 10/01/2019 | 05/27/2020 | 12/31/9999
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | 08W | CC | Documentation | ECES_CA1/DOCC | 02/10/2021 | 07/19/2018 | 10/23/2018 | 10/23/2018 | 10/23/2018 | 10/23/2018 | 02/08/2019 | 02/08/2021 | 02/10/2021 | 02/06/2021 | 02/08/2021 |  |  | 02/10/2021 | 12/31/9999 | 06/27/2018 | 07/19/2018
31272375 | CWSP PT. MORETTI BEYOND 5995 | 08W | CC | Documentation | ECES_CA1/DOCC | 02/03/2021 | 08/10/2018 | 09/11/2018 | 09/11/2018 | 09/11/2018 | 09/11/2018 | 02/01/2019 | 02/15/2019 | 02/03/2021 |  |  |  |  | 02/03/2021 | 12/31/9999 | 07/19/2018 | 08/10/2018
31275384 | OCGC DUCTOR MAYS CANYON-MIRABEL 1101 | 08W | SO | Completion | ECES_CA1/CLSD | 11/21/2020 | 10/05/2016 | 09/21/2017 | 09/21/2017 | 12/07/2017 | 12/07/2017 | 12/07/2017 | 06/07/2018 | 07/02/2018 | 07/02/2018 | 07/16/2018 | 07/16/2018 | 10/16/2018 | 10/16/2018 | 10/24/2018 |  |  | 10/24/2018 | 04/10/2020 | 04/10/2020 | 11/19/2020 | 11/21/2020 | 12/31/9999
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 | 08W | SO | Documentation | ECES_CA1/DOCC | 09/05/2019 | 10/07/2016 | 09/21/2017 | 02/14/2019 | 02/28/2019 | 08/01/2018 | 08/01/2018 | 02/28/2019 | 04/25/2019 | 04/25/2019 | 07/18/2019 | 07/18/2019 | 09/05/2019 | 09/05/2019 | 12/31/9999 | 12/21/2017 | 01/18/2018
31278200 | +OCEANO 1102 S HALCYON & PINE RDGE | 08W | LP | Completion | ECES_CA1/CLSD | 07/04/2020 | 10/17/2016 | 09/27/2017 | 01/14/2019 | 01/15/2019 | 01/15/2019 | 01/15/2019 | 02/08/2019 | 02/22/2019 | 02/22/2019 | 03/13/2019 | 03/13/2019 | 03/29/2019 | 03/29/2019 | 04/10/2019 | 12/27/2017 | 01/02/2018 | 04/10/2019 | 04/10/2020 | 04/10/2020 | 06/29/2020 | 07/04/2020 | 12/31/9999
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 | 08W | CC | Initiation | ECES_CA1/UNSE | 02/14/2019 | 02/14/2019 | 12/31/9999 | [12 empty] | 01/30/2019 | 02/14/2019
31286361 | *CNCL* FRUITLAND 42 C/O 7449 | 08W | HB | Initiation | ECES_CA1/UNSE | 08/16/2019 | 08/16/2019 | 12/31/9999 | [12 empty] | 08/07/2019 | 08/16/2019
31286571 | *R4 EL DORADO PH 2102 HIGH SPLICE AREA | 08W | SI | Completion | ECES_CA1/CLSD | 07/20/2019 | 12/01/2016 | 04/13/2018 | 04/13/2018 | 06/05/2018 | 06/05/2018 | 06/20/2018 | 06/24/2018 | 09/11/2018 | 09/11/2018 | 09/17/2018 |  |  | 09/17/2018 | 09/18/2018 |  |  | 09/18/2018 | 10/30/2018 | 10/30/2018 | 07/16/2019 | 07/20/2019 | 12/31/9999
31286573 | APPLE HILL 2102 HIGH SPLICE AREA | 08W | SI | Completion | ECES_CA1/CLSD | 05/09/2020 | 12/01/2016 | 09/12/2018 | 01/14/2019 | 01/30/2019 | 10/15/2018 | 11/06/2018 | 01/30/2019 | 03/18/2019 | 03/18/2019 | 04/29/2019 | 04/29/2019 | 06/24/2019 | 06/24/2019 | 06/26/2019 | 10/11/2018 | 10/15/2018 | 06/26/2019 | 08/28/2019 | 08/28/2019 | 05/06/2020 | 05/09/2020 | 12/31/9999
31288039 | HOOPA 1101 RCOND WITH TREE WIRE | 08W | HB | Initiation | ECES_CA1/UNSE | 12/08/2016 | 12/08/2016 | 12/31/9999
31289238 | FRUITLAND 1142 INS TREE WIRE LR 6064 | 08W | HB | Documentation | ECES_CA1/DOCC | 06/01/2020 | 12/13/2016 | 06/13/2018 | 01/10/2019 | 03/11/2019 | 08/08/2018 | 08/09/2018 | 07/24/2019 | 07/26/2019 | 07/26/2019 | 09/05/2019 | 07/01/2019 | 07/24/2019 | 06/01/2020 | 12/31/9999 |  |  | 01/25/2020 | 02/27/2020 | 02/27/2020 | 06/01/2020
31289354 | *Cncl* BIG RIVER 1101 FUSE 5187 RECON | 08W | HB | Initiation | ECES_CA1/UNSE | 12/14/2016 | 12/14/2016 | 12/31/9999
31289812 | RECOND TAP W TW - LCO 5265 GUALALA 1112 | 08W | SO | Initiation | ECES_CA1/UNSE | 12/15/2016 | 12/15/2016 | 12/31/9999
31290145 | R7 SAN RAFAEL 1107 COND REPLACEMENT | 08W | NB | Post-Doc | ECES_CA1/FICL | 01/02/2020 | 12/19/2016 | 05/02/2018 | 01/10/2019 | 02/26/2019 | 09/10/2018 | 09/10/2018 | 03/11/2019 | 04/09/2019 | 04/09/2019 | 07/18/2019 | 07/18/2019 | 09/05/2019 | 09/05/2019 | 12/19/2019 | 08/01/2018 | 08/10/2018 | 12/19/2019 | 01/02/2020 | 01/02/2020 | 12/31/9999
31290147 | OCCCR7 OLEMA 1101 REPLACE COND VISION RD | 08W | NB | Completion | ECES_CA1/CLSD | 01/30/2021 | 12/19/2016 | 05/02/2018 | 02/11/2019 | 02/16/2019 | 08/29/2018 | 08/29/2018 | 05/14/2019 | 05/14/2019 | 05/14/2019 | 07/18/2019 | 07/18/2019 | 09/23/2019 | 09/23/2019 | 01/19/2021 | 08/01/2018 | 08/10/2018 | 01/19/2021 | 01/21/2021 | 01/21/2021 | 01/25/2021 | 01/30/2021 | 12/31/9999
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | 08W | LP | Design | ECES_CA1/ESTS | 08/11/2020 | 12/29/2016 | 07/17/2018 | 08/11/2020 | 12/31/9999 | 03/16/2020 | 05/18/2020 | 07/14/2020 | 08/11/2020 | 07/01/2020 | 07/14/2020 |  |  |  |  | 10/01/2018 | 10/16/2018
31297273 | RECOND HWY1 (BY SW 92493)- GUALALA 1111 | 08W | SO | Initiation | ECES_CA1/UNSE | 01/19/2017 | 01/19/2017 | 12/31/9999
31308015 | *CANC* SLO 1107 RECOND 3836 FT 10S *CANC | 08W | LP | Completion | ECES_CA1/CLSD | 09/05/2019 | 03/19/2019 | 06/13/2019 | [12 empty] | 06/13/2019 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
31316186 | *CANC* HMB1102 CO12457 #17-00290*CANC | 08W | PN | Completion | ECES_CA1/CLSD | 12/12/2018 | 04/01/2017 | 07/24/2018 | 07/24/2018 | 09/25/2018 | [16 empty] | 12/12/2018 | 12/12/2018 | 11/02/2018 | 12/05/2018
31319329 | SAN LUIS OBISP1103 - RECOND WITH 2CU TW | 08W | LP | Initiation | ECES_CA1/UNSE | 04/13/2017 | 04/13/2017 | 12/31/9999
31319444 | RECON 5-SPANS PORTER CRK RD-RINCON 1103 | 08W | SO | Post-Doc | ECES_CA1/FICL | 11/09/2020 | 04/13/2017 | 11/05/2018 | 11/05/2018 | 12/10/2018 | 02/13/2019 | 02/19/2019 | 02/19/2019 | 06/17/2019 | 06/17/2019 | 06/24/2019 | 06/24/2019 | 12/17/2019 | 09/10/2020 | 11/09/2020 | 01/30/2019 | 02/13/2019 | 01/21/2020 | 01/28/2020 | 11/09/2020 | 12/31/9999
31326119 | WEIMAR 1101 - NATURE'S WAY RECONDUCTOR | 08W | SI | Completion | ECES_CA1/CLSD | 05/30/2020 | 04/11/2018 | 06/19/2018 | 05/13/2019 | 06/18/2019 | 06/18/2019 | 06/24/2019 | 06/24/2019 | 06/27/2019 | 06/27/2019 | 09/30/2019 | 09/30/2019 | 12/30/2019 | 12/30/2019 | 05/07/2020 | 08/07/2018 | 08/11/2018 | 05/07/2020 | 05/28/2020 | 05/28/2020 | 05/28/2020 | 05/30/2020 | 12/31/9999
31330635 | FORESTHILL 1102 - SPRING GARDEN RD 08W | 08W | SI | Completion | ECES_CA1/CLSD | 05/30/2020 | 06/09/2017 | 04/04/2018 | 05/02/2018 | 05/16/2018 | 05/16/2018 | 06/20/2018 | 07/11/2018 | 09/18/2018 | 09/18/2018 | 09/19/2018 | 09/19/2018 | 12/04/2018 | 12/04/2018 | 12/05/2018 | 07/04/2018 | 07/06/2018 | 12/05/2018 | 12/18/2018 | 12/18/2018 | 05/25/2020 | 05/30/2020 | 12/31/9999
31334290 | RECON 24 SPANS -ALBION RIDGE RD | 08W | HB | Initiation | ECES_CA1/UNSE | 06/28/2017 | 06/28/2017 | 12/31/9999
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | 08W | HB | Pending | ECES_CA1/PEND | 04/12/2019 | 06/28/2017 | 05/09/2018 | 01/10/2019 | 02/12/2019 | 10/18/2018 | 10/18/2018 | 04/12/2019 | 12/31/9999 | 04/11/2019 | 04/12/2019 |  |  |  |  | 08/08/2018 | 08/21/2018
31334292 | RECON 9-SPANS, AUSTIN CREEK RD | 08W | SO | Completion | ECES_CA1/CLSD | 11/21/2020 | 06/28/2017 | 05/02/2018 | 01/10/2019 | 02/25/2019 |  |  | 02/25/2019 | 03/20/2019 | 03/20/2019 | 07/01/2019 | 07/01/2019 | 12/17/2019 | 12/17/2019 | 09/10/2020 | 08/01/2018 | 08/15/2018 | 09/10/2020 | 09/17/2020 | 09/17/2020 | 11/16/2020 | 11/21/2020 | 12/31/9999
31338871 | RELIAIBLITY RICHMOND-REPL #6 CU-UWF_PH2 | 08W | EB | Completion | ECES_CA1/CLSD | 04/25/2020 | 07/25/2017 | 09/21/2017 | 09/21/2017 | 10/17/2017 | 01/17/2018 | 05/16/2018 | 07/06/2018 | 07/20/2018 | 08/22/2018 | 10/02/2018 | 10/02/2018 | 10/15/2018 | 03/18/2020 | 04/24/2020 | 12/21/2017 | 01/17/2018 | 11/16/2018 | 11/20/2018 | 11/20/2018 | 02/13/2019 | 04/25/2020 | 12/31/9999
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT | 08W | DI | Post-Doc | ECES_CA1/FICL | 09/30/2020 | 01/22/2019 | 01/31/2019 | 12/13/2019 | 12/13/2019 | 12/10/2019 | 12/13/2019 | 03/10/2020 | 03/10/2020 | 03/10/2020 | 03/26/2020 | 03/26/2020 | 05/15/2020 | 08/24/2020 | 09/30/2020 | 12/13/2018 | 01/16/2019 | 05/19/2020 | 07/17/2020 | 09/30/2020 | 12/31/9999
31344015 | CNCL: 2019 CALISTOGA 1101 HIGH SPLICE CT | 08W | NB | Documentation | ECES_CA1/DOCC | 10/08/2018 | 08/22/2017 | 05/02/2018 | 08/10/2018 | 10/08/2018 | [8 empty] | 10/08/2018 | 12/31/9999 | 08/01/2018 | 08/10/2018
31344016 | 2019 OLEMA 1101 HIGH SPLICE CNT_1 | 08W | NB | Initiation | ECES_CA1/UNSE | 08/22/2017 | 08/22/2017 | 12/31/9999
31344017 | 2019 OLEMA 1101 HIGH SPLICE CNT_2 | 08W | NB | Initiation | ECES_CA1/UNSE | 08/22/2017 | 08/22/2017 | 12/31/9999
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | 08W | NB | Initiation | ECES_CA1/UNSE | 10/05/2017 | 10/05/2017 | 12/31/9999
31360766 | FROGTOWN 1701 RECOND 1153FTTO 1/0ACSR TW | 08W | ST | Completion | ECES_CA1/CLSD | 02/29/2020 | 10/12/2017 | 06/13/2018 | 10/19/2018 | 11/06/2018 | 11/06/2018 | 03/15/2019 | 03/18/2019 | 04/29/2019 | 04/29/2019 | 05/06/2019 | 05/06/2019 | 06/18/2019 | 06/18/2019 | 08/22/2019 | 09/12/2018 | 10/19/2018 | 08/22/2019 | 08/28/2019 | 08/28/2019 | 02/25/2020 | 02/29/2020 | 12/31/9999
31361488 | *CANC* RECOND 15 298 FT 6CU 4CU & *CANC | 08W | NB | Completion | ECES_CA1/CLSD | 10/03/2019 | 10/18/2017 | 07/30/2018 | 01/10/2019 | 01/31/2019 | 09/20/2018 | 09/20/2018 | 09/20/2018 | 01/10/2019 |  |  |  |  | 09/23/2019 | 09/23/2019 | 09/23/2019 | 09/23/2019 |  |  |  |  | 10/03/2019 | 12/31/9999 | 09/23/2019 | 10/03/2019
31361489 | OLEMA 1101 HIGH SPLICE COUNT 3 | 08W | NB | Initiation | ECES_CA1/UNSE | 10/18/2017 | 10/18/2017 | 12/31/9999
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | 08W | SO | Construction | ECES_CA1/CONS | 08/24/2020 | 10/23/2017 | 10/30/2018 | 06/03/2019 | 06/19/2019 | 01/11/2019 | 03/06/2019 | 06/19/2019 | 07/24/2020 | 07/24/2020 | 08/24/2020 | 08/24/2020 | 12/31/9999 |  |  | 12/28/2018 | 01/11/2019
31361969 | RECON 9,400 FT - POINT ARENA 1101 | 08W | SO | Estimating Ready | ECES_CA1/UNSE | 10/23/2017 | 10/23/2017 | 12/31/9999
31364228 | RECOND 4490FT OF 4ACSR WITH 2CU TW | 08W | LP | Initiation | ECES_CA1/UNSE | 11/07/2017 | 11/07/2017 | 12/31/9999
31374249 | 14184 FT OF 4ACSR&3363 FT OF 6CUW 2CU TW | 08W | LP | Initiation | ECES_CA1/UNSE | 04/08/2020 | 04/08/2020 | 12/31/9999 | [12 empty] | 02/25/2019 | 04/08/2020
31387895 | *CANC* REPL 17 500' OF 4AR & 4CU I *CANC | 08W | NB | Completion | ECES_CA1/CLSD | 09/05/2019 | 01/16/2019 | 01/31/2019 | [12 empty] | 01/31/2019 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE | 08W | NB | Documentation | ECES_CA1/DOCC | 12/17/2019 | 12/18/2018 | 12/18/2018 | 12/18/2018 | 02/06/2019 | 02/06/2019 | 02/22/2019 |  |  |  |  | 10/15/2019 | 12/17/2019 | 12/17/2019 | 12/31/9999 | 11/27/2018 | 12/18/2018
31389448 | *CANC* SILVERADO 2104 RECONDUCTOR*CANC | 08W | NB | Completion | ECES_CA1/CLSD | 03/02/2019 | 04/20/2018 | 11/05/2018 | 11/05/2018 | 11/06/2018 | [8 empty] | 11/06/2018 | 11/28/2018 | [6 empty] | 03/02/2019 | 12/31/9999 | 02/06/2019 | 03/02/2019
31392316 | *CANC* 2018MONTERIO1112/MOLINO1102WILDFI | 08W | SO | Completion | ECES_CA1/CLSD | 06/09/2018 | 05/16/2018 | 05/17/2018 | [10 empty] | 05/17/2018 | 06/08/2018 | [6 empty] | 06/09/2018 | 12/31/9999
31429487 | OTTER-1101 S030CC121 – TRANS POLES | 08W | CC | Pending | ECES_CA2/PEND | 10/17/2019 | 03/18/2019 | 03/26/2019 | 03/26/2019 | 07/12/2019 | 07/12/2019 | 07/29/2019 | 10/17/2019 | 12/31/9999 | 10/09/2019 | 10/17/2019
31434881 | 0P 3100 SKYWAY RD PARADISE TUSCAN RIDGE | 08W | NV | Pending | ECES_CA1/PEND | 06/11/2019 | 04/19/2019 | 05/15/2019 |  |  | 05/15/2019 | 06/10/2019 | 06/11/2019 | 12/31/9999
31462406 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | 08W | LP | Design | ECES_CA1/ADER | 08/26/2019 | 08/13/2019 | 08/26/2019 | 08/26/2019 | 08/26/2019 | 08/26/2019 | 12/31/9999
31478906 | RAISE T-LINE H-FRAME DONNELS-MI WUK 18/2 | 08W | YO | Pre-Construction | ECES_CA1/UNSC | 04/13/2020 | 11/21/2019 | 02/19/2020 |  |  |  |  | 02/19/2020 | 04/13/2020 | 04/13/2020 | 12/31/9999
35008479 | R2 2019 AUBERRY 1101 RECONDUCTOR | 08W | FR | Completion | ECES_CA1/CLSD | 05/31/2020 | 08/29/2017 | 10/10/2018 | 03/04/2019 | 03/04/2019 | 03/04/2019 | 03/04/2019 | 03/04/2019 | 04/24/2019 | 04/24/2019 | 05/03/2019 | 05/03/2019 | 06/17/2019 | 06/17/2019 | 09/09/2019 |  |  | 09/09/2019 | 12/05/2019 | 12/05/2019 | 05/25/2020 | 05/31/2020 | 12/31/9999
35013233 | R2RPL OH WIRE ON GONZALS-1101 17-0063084 | 08W | CC | Initiation | ECES_CA1/UNSE | 03/04/2020 | 03/04/2020 | 12/31/9999 | [12 empty] | 03/03/2020 | 03/04/2020
35015703 | *CANC* FOOTHILL 1101 LS CO9973 REP *CANC | 08W | LP | Completion | ECES_CA1/CLSD | 09/05/2019 | 09/13/2017 | 08/14/2018 | 08/14/2018 | 12/17/2018 | [10 empty] | 12/17/2018 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | 08W | CC | Pending | ECES_CA1/PEND | 04/11/2019 | 09/15/2017 | 06/26/2018 | 04/11/2019 | 04/11/2019 | 04/11/2019 | 04/11/2019 | 04/11/2019 | 12/31/9999
35015705 | *CANC* R2 OH RECONDUCTR ROB ROY 21*CANC | 08W | CC | Completion | ECES_CA1/CLSD | 09/05/2019 | 09/15/2017 | 07/10/2018 | 03/18/2019 | 04/11/2019 | 10/25/2018 | 10/25/2018 | 03/18/2019 | 03/18/2019 |  |  |  |  | 04/11/2019 | 05/10/2019 | 05/10/2019 | 07/03/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/02/2019 | 09/05/2019
35015706 | *CANC* OH RECONDUCTOR - ROB ROY 210*CANC | 08W | CC | Completion | ECES_CA1/CLSD | 09/05/2019 | 09/15/2017 | 07/10/2018 | 03/18/2019 | 03/20/2019 | 10/16/2018 | 10/16/2018 | 03/20/2019 | 03/27/2019 |  |  |  |  | 03/27/2019 | 05/10/2019 | 05/10/2019 | 07/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/02/2019 | 09/05/2019
35018620 | *CANC* RECON CAB 1104 17K FT LASAL *CANC | 08W | LP | Completion | ECES_CA1/CLSD | 09/05/2019 | 09/25/2017 | 07/16/2018 | 07/16/2018 | 12/02/2018 | [10 empty] | 12/02/2018 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35018787 | HALSEY 1101 - S039NO112 HIGH SPLICE 08J | 08W | SI | Completion | ECES_CA1/CLSD | 01/16/2021 | 09/29/2017 | 10/02/2018 | 06/26/2019 | 06/26/2019 | 06/26/2019 | 06/26/2019 | 06/26/2019 | 07/16/2019 | 07/16/2019 | 07/23/2019 | 07/23/2019 | 10/10/2019 | 10/10/2019 | 12/28/2020 |  |  | 12/28/2020 | 01/12/2021 | 01/12/2021 | 01/13/2021 | 01/16/2021 | 12/31/9999
35018788 | APPLE HILL 1104 - S049NO119 HIGH SPLICE | 08W | SI | Completion | ECES_CA1/CLSD | 09/12/2020 | 01/17/2019 | 01/24/2019 | 05/28/2019 | 05/28/2019 | 05/28/2019 | 05/28/2019 | 05/28/2019 | 06/17/2019 | 06/17/2019 | 07/29/2019 | 07/29/2019 | 10/08/2019 | 10/08/2019 | 08/15/2020 | 02/07/2019 | 02/14/2019 | 08/15/2020 | 09/04/2020 | 09/04/2020 | 09/10/2020 | 09/12/2020 | 12/31/9999 | 01/07/2019 | 01/17/2019
35018886 | *CANC* RPL OH WIRE ON GABILN 1101 *CANC | 08W | CC | Completion | ECES_CA1/CLSD | 09/05/2019 | 10/03/2017 | 01/30/2019 | [10 empty] | 03/19/2019 | 03/29/2019 | 03/29/2019 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35019004 | PURISIMA 1101 LS SW8139 REPL OH LINE | 08W | CC | Initiation | ECES_CA1/UNSE | 10/06/2017 | 10/06/2017 | 12/31/9999
35019006 | ROB ROY 2104 CO11865 REPLACE OH LINE | 08W | CC | Completion | ECES_CA1/CLSD | 07/25/2020 | 10/06/2017 | 07/10/2018 | 04/10/2020 | 04/13/2020 | 06/20/2019 | 06/20/2019 | 06/20/2019 | 08/22/2019 | 08/22/2019 | 09/09/2019 | 09/09/2019 | 01/15/2020 | 06/10/2020 | 06/10/2020 |  |  | 04/13/2020 | 06/10/2020 | 06/10/2020 | 07/24/2020 | 07/25/2020 | 12/31/9999
35023687 | R2RPL OH WIRE ON B LOMND 0401 17-0095503 | 08W | CC | Documentation | ECES_CA1/DOCC | 10/28/2020 | 12/06/2017 | 05/31/2019 | 06/04/2019 | 06/11/2019 | 06/11/2019 | 06/11/2019 | 06/13/2019 | 08/30/2019 | 08/30/2019 | 09/23/2019 | 09/23/2019 | 02/11/2020 | 10/28/2020 | 12/31/9999 |  |  | 04/13/2020 | 04/27/2020 | 04/27/2020 | 10/28/2020
35024428 | SUMMIT 1101 RECONDUCTOR W TREE WIRE | 08W | SI | Initiation | ECES_CA1/UNSE | 12/26/2017 | 12/26/2017 | 12/31/9999
35024647 | RR 2104 RECOND 1051 ZONE W TW | 08W | CC | Initiation | ECES_CA1/UNSE | 01/03/2018 | 01/03/2018 | 12/31/9999
35024926 | MARTELL 1101 RECONDCUTOR 3,700FT | 08W | ST | Post-Doc | ECES_CA1/FICL | 01/04/2021 | 01/08/2018 | 10/15/2018 | 10/15/2018 | 02/04/2019 | 02/04/2019 | 02/04/2019 | 02/21/2019 | 03/07/2019 | 03/07/2019 | 03/15/2019 | 03/15/2019 | 04/04/2019 | 04/04/2019 | 07/14/2020 |  |  | 07/14/2020 | 01/04/2021 | 01/04/2021 | 12/31/9999
35026420 | *CANC*OAKLAND X-1104 OH RECOND SKYLINE | 08W | EB | Completion | ECES_CA2/CLSD | 08/05/2020 | 02/08/2018 | 10/08/2018 | [10 empty] | 05/28/2020 | 05/28/2020 | 04/24/2020 | 05/08/2020 |  |  |  |  | 08/05/2020 | 12/31/9999 | 07/03/2020 | 08/05/2020
35026643 | RECONDUCTOR DIAMOND SPRINGS 1105 | 08W | SI | Documentation | ECES_CA1/DCNL | 01/26/2021 | 02/11/2019 | 01/26/2021 | 11/01/2018 | 02/11/2019 | [10 empty] | 01/26/2021 | 12/31/9999
35029270 | MORGAN HILL 2111 RECOND 13-SPANS W TW | 08W | SJ | Initiation | ECES_CA1/UNSE | 03/06/2018 | 03/06/2018 | 12/31/9999
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | 08W | PN | Pending | ECES_CA1/PEND | 12/31/2019 | 02/25/2019 | 05/20/2019 | 12/31/2019 | 12/31/2019 | 12/31/2019 | 12/31/2019 | 12/31/2019 | 12/31/9999 | [6 empty] | 10/17/2019 | 10/30/2019 | [6 empty] | 07/05/2019 | 07/11/2019
35030654 | TW ON WOODSIDE1101 N/O 7573 | 08W | PN | Completion | ECES_CA1/CLSD | 01/23/2021 | 03/30/2018 | 11/20/2018 | 01/10/2019 | 03/01/2019 | 03/01/2019 | 03/04/2019 | 03/06/2019 | 05/09/2019 | 05/09/2019 | 08/08/2019 | 08/08/2019 | 01/16/2020 | 04/21/2020 | 06/08/2020 | 12/29/2018 | 01/10/2019 | 01/17/2020 | 03/30/2020 | 06/08/2020 | 01/22/2021 | 01/23/2021 | 12/31/9999
35031139 | SHADY GLEN 1102 RECONDUCTOR BEYOND 6343 | 08W | SI | Completion | ECES_CA1/CLSD | 08/08/2020 | 04/04/2018 | 02/24/2019 | 01/18/2020 | 02/26/2020 | 07/11/2019 | 07/11/2019 | 07/11/2019 | 07/31/2019 | 07/31/2019 | 10/07/2019 | 10/07/2019 | 12/31/2019 | 12/31/2019 | 01/02/2020 | 07/01/2019 | 07/03/2019 | 01/02/2020 | 01/13/2020 | 02/26/2020 | 08/07/2020 | 08/08/2020 | 12/31/9999
35031660 | *CANC* PH 1:REPL 14 000' OF 4AR IN *CANC | 08W | DA | Completion | ECES_CA1/CLSD | 09/05/2019 | 04/10/2018 | 10/23/2018 | 10/23/2018 | 02/01/2019 |  |  |  |  | 07/18/2019 | 08/05/2019 |  |  | 03/20/2019 | 03/22/2019 | 03/22/2019 | 07/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35031662 | CWSP - LOS GATOS 1106 - LB44 - PHASE 2.1 | 08W | DA | Post-Doc | ECES_CA2/FICL | 07/02/2020 | 04/10/2018 | 10/23/2018 | 10/23/2018 | 10/04/2019 | 10/04/2019 | 10/04/2019 | 10/07/2019 | 01/13/2020 | 01/13/2020 | 02/03/2020 | 02/03/2020 | 03/26/2020 | 05/26/2020 | 07/02/2020 |  |  | 03/30/2020 | 05/26/2020 | 07/02/2020 | 12/31/9999
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | 08W | DA | Design | ECES_CA2/ESTS | 10/23/2018 | 04/10/2018 | 10/23/2018 | 10/23/2018 | 12/31/9999
35032266 | APPLE HILL 1104 RECONDUCTOR | 08W | SI | Completion | ECES_CA1/CLSD | 05/09/2020 | 04/18/2018 | 05/31/2019 | 05/31/2019 | 06/11/2019 | 04/23/2020 | 04/30/2020 | 07/08/2019 | 07/15/2019 | 07/15/2019 | 10/10/2019 |  |  | 10/10/2019 | 04/15/2020 | 06/12/2019 | 06/13/2019 | 04/15/2020 | 04/22/2020 | 04/30/2020 | 05/05/2020 | 05/09/2020 | 12/31/9999
35039002 | OCGC 2018 CALISTOGA 1101 LEVEL 2 DEMO | 08W | NB | Completion | ECES_CA1/CLSD | 08/15/2020 | 05/01/2018 | 06/07/2018 | 08/29/2018 | 08/29/2018 | 08/29/2018 | 08/29/2018 | 08/29/2018 | 09/12/2018 | 09/12/2018 | 09/26/2018 | 09/26/2018 | 03/29/2019 | 03/29/2019 | 04/02/2019 | 08/15/2018 | 08/27/2018 | 04/02/2019 | 09/20/2019 | 09/20/2019 | 08/10/2020 | 08/15/2020 | 12/31/9999
35039748 | CWSP-MIWUK 1702-LR 38218 | 08W | YO | Initiation | ECES_CA1/UNSE | 04/16/2020 | 04/16/2020 | 12/31/9999 | [12 empty] | 08/17/2018 | 04/16/2020
35039757 | *CANC* CWSP - BURNS 2101 - OCB - P*CANC | 08W | CC | Completion | ECES_CA1/CLSD | 01/07/2021 | 04/16/2020 | 06/05/2020 | [10 empty] | 06/12/2020 | 06/12/2020 | 08/17/2018 | 04/16/2020 |  |  |  |  | 01/07/2021 | 12/31/9999 | 12/16/2020 | 01/07/2021
35039957 | *CANC* CWSP - STANISLAUS 1702 LR18 *CANC | 08W | ST | Completion | ECES_CA1/CLSD | 05/03/2020 | 05/09/2018 | 05/06/2019 | [12 empty] | 05/06/2019 | 04/04/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/04/2020 | 05/03/2020
35039982 | CWSP: MIWUK 1702_OCB WILDFIRE HARDENING | 08W | YO | Initiation | ECES_CA1/UNSE | 04/16/2020 | 04/16/2020 | 12/31/9999 | [12 empty] | 08/17/2018 | 04/16/2020
35040016 | *CANC* CWSP-SILVERADO 2104-LR 722 *CANC | 08W | NB | Completion | ECES_CA1/CLSD | 09/05/2019 | 05/10/2018 | 11/04/2018 | [12 empty] | 11/04/2018 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35040017 | CWSP - OAK K 1102 OCB LVL 1 HARDENING | 08W | EB | Initiation | ECES_CA1/UNSE | 02/17/2021 | 02/17/2021 | 12/31/9999 | [6 empty] | 07/03/2019 | 07/27/2019 |  |  | 08/29/2019 | 08/29/2019 | 01/07/2021 | 02/05/2021 | [6 empty] | 02/05/2021 | 02/17/2021
35040018 | CWSP - MORAGA 1101 (VARIOUS) - OCB | 08W | DI | Initiation | ECES_CA1/UNSE | 01/23/2020 | 01/23/2020 | 12/31/9999 | [6 empty] | 02/14/2019 | 05/30/2019 |  |  | 08/29/2019 | 08/29/2019 | 08/29/2019 | 01/06/2020 | [6 empty] | 01/06/2020 | 01/23/2020
35040118 | CWSP: MIWUK 1701_OCB WILDFIRE HARDENING | 08W | YO | Initiation | ECES_CA1/UNSE | 04/16/2020 | 04/16/2020 | 12/31/9999 | [12 empty] | 08/17/2018 | 04/16/2020
35040225 | HIGGINS 1110 RECONDUCTOR | 08W | SI | Completion | ECES_CA1/CLSD | 05/23/2020 | 05/11/2018 | 05/31/2019 | 06/27/2019 | 06/28/2019 | 06/28/2019 | 06/28/2019 | 07/01/2019 | 08/01/2019 | 08/01/2019 | 09/10/2019 | 09/10/2019 | 10/10/2019 | 10/10/2019 | 05/04/2020 | 06/26/2019 | 06/27/2019 | 05/04/2020 | 05/20/2020 | 05/20/2020 | 05/21/2020 | 05/23/2020 | 12/31/9999
35040505 | CWSP - BIG BASIN 1101 - LR 10296 - PH1 | 08W | CC | Design | ECES_CA1/ESTS | 11/12/2020 | 05/15/2018 | 08/13/2018 | 11/12/2020 | 12/31/9999 | [10 empty] | 08/13/2020 | 11/05/2020 | [6 empty] | 11/05/2020 | 11/12/2020
35040506 | RR2105 RESILIENCE - 5090 ZONE STEEL & TW | 08W | CC | Initiation | ECES_CA1/UNSE | 05/15/2018 | 05/15/2018 | 12/31/9999
35040742 | OCGC - 2018 MONTE RIO 1112 OH TO UG DEMO | 08W | SO | Completion | ECES_CA1/CLSD | 11/23/2019 | 05/17/2018 | 06/07/2018 | 09/04/2018 | 09/04/2018 | 09/04/2018 | 09/04/2018 | 09/04/2018 | 10/10/2018 | 10/10/2018 | 10/19/2018 | 10/19/2018 | 04/09/2019 | 04/09/2019 | 04/09/2019 | 09/01/2018 | 09/04/2018 | 04/09/2019 | 10/09/2019 | 10/09/2019 | 11/22/2019 | 11/23/2019 | 12/31/9999
35040961 | CWSP: 2018 K-1102 OH TO UG DEMO | 08W | DI | Completion | ECES_CA1/CLSD | 01/23/2021 | 05/21/2018 | 06/07/2018 | 06/07/2018 | 08/09/2018 | 08/09/2018 | 08/09/2018 | 09/04/2018 | 09/21/2018 | 09/21/2018 | 10/22/2018 | 10/22/2018 | 06/18/2019 | 12/29/2020 | 01/21/2021 | 08/31/2018 | 09/04/2018 | 06/21/2019 | 09/20/2019 | 09/20/2019 | 10/15/2019 | 01/23/2021 | 12/31/9999
35041202 | *TRSFR* 35052732 CWSP-BB 1101 - LR *CANC | 08W | CC | Completion | ECES_CA1/CLSD | 08/05/2020 | 04/16/2020 | 05/29/2020 | [10 empty] | 06/10/2020 | 06/10/2020 | 08/17/2018 | 04/16/2020 |  |  |  |  | 08/05/2020 | 12/31/9999 | 07/03/2020 | 08/05/2020
35041205 | *CANC* WSP LOS GATOS 1106 LR 60116*CANC | 08W | DA | Completion | ECES_CA1/CLSD | 01/07/2021 | 04/16/2020 | 06/05/2020 | [10 empty] | 06/12/2020 | 06/12/2020 | 08/17/2018 | 04/16/2020 |  |  |  |  | 01/07/2021 | 12/31/9999 | 12/16/2020 | 01/07/2021
35042365 | CWSP - CAMP EVERS 2106 - LR 60124 - PH 5 | 08W | DA | Initiation | ECES_CA1/UNSE | 05/29/2018 | 05/29/2018 | 12/31/9999
35042366 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 4 | 08W | DA | Initiation | ECES_CA1/UNSE | 05/29/2018 | 05/29/2018 | 12/31/9999
35042367 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 3 | 08W | DA | Initiation | ECES_CA1/UNSE | 01/23/2020 | 01/23/2020 | 12/31/9999 | 10/30/2019 | 01/03/2020 |  |  |  |  | 10/25/2019 | 10/30/2019 |  |  |  |  | 01/03/2020 | 01/06/2020 | [6 empty] | 01/06/2020 | 01/23/2020
35042368 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 2 | 08W | DA | Initiation | ECES_CA1/UNSE | 05/29/2018 | 05/29/2018 | 12/31/9999
35042369 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 1 | 08W | DA | Initiation | ECES_CA1/UNSE | 05/29/2018 | 05/29/2018 | 12/31/9999
35042417 | *TRSFR* 35052727 CWSP LG1106 LR6011*CANC | 08W | DA | Completion | ECES_CA1/CLSD | 08/05/2020 | 04/16/2020 | 06/05/2020 | [10 empty] | 06/12/2020 | 06/12/2020 | 08/17/2018 | 04/16/2020 |  |  |  |  | 08/05/2020 | 12/31/9999 | 07/03/2020 | 08/05/2020
35042421 | CWSP - MIWUK 1701 - LR 8050 | 08W | YO | Initiation | ECES_CA1/UNSE | 02/21/2020 | 02/21/2020 | 12/31/9999 | [12 empty] | 08/17/2018 | 02/21/2020
35042603 | DIAMOND SPRINGS 1103 RECOND 18-0029738 | 08W | SI | Initiation | ECES_CA1/UNSE | 06/01/2018 | 06/01/2018 | 12/31/9999
35042612 | *CANC* CWSP-ORO FINO 1101 LR-2022 *CANC | 08W | NV | Completion | ECES_CA1/CLSD | 05/03/2020 | 06/01/2018 | 05/06/2019 | [12 empty] | 05/06/2019 | 04/04/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/04/2020 | 05/03/2020
35042631 | *CANC*DO NOT USE* CWSP-VOLTA 1102-L*CANC | 08W | NV | Completion | ECES_CA1/CLSD | 05/03/2020 | 05/31/2018 | 05/29/2019 | [12 empty] | 05/29/2019 | 04/02/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/02/2020 | 05/03/2020
35042647 | *TRSFR* 35052733 CWSP-BB 1101 - LR *CANC | 08W | CC | Completion | ECES_CA1/CLSD | 08/05/2020 | 04/16/2020 | 05/29/2020 | [10 empty] | 06/10/2020 | 06/10/2020 | 08/17/2018 | 04/16/2020 |  |  |  |  | 08/05/2020 | 12/31/9999 | 07/03/2020 | 08/05/2020
35042648 | *TRSFR* 35052734 CWSP-CE 2105 - LR *CANC | 08W | CC | Completion | ECES_CA1/CLSD | 08/05/2020 | 04/16/2020 | 05/29/2020 | [10 empty] | 06/10/2020 | 06/10/2020 | 08/17/2018 | 04/16/2020 |  |  |  |  | 08/05/2020 | 12/31/9999 | 07/03/2020 | 08/05/2020
35042719 | CWSP-AMGWIN STEEL POLE & TW DEMO PH | 08W | NB | Completion | ECES_CA1/CLSD | 11/07/2020 | 05/31/2018 | 09/01/2018 | 10/17/2018 | 10/17/2018 | 10/17/2018 | 10/17/2018 | 10/17/2018 | 01/15/2019 | 01/15/2019 | 01/29/2019 | 01/29/2019 | 10/29/2019 | 10/29/2019 | 04/10/2020 | 09/01/2018 | 09/13/2018 | 04/10/2020 | 04/21/2020 | 04/21/2020 | 11/03/2020 | 11/07/2020 | 12/31/9999
35042893 | *CANC* CWSP - BURNS 2101 - OCB - PH*CANC | 08W | CC | Completion | ECES_CA1/CLSD | 07/03/2020 | 04/16/2020 | 05/01/2020 | [10 empty] | 05/12/2020 | 05/12/2020 | 08/17/2018 | 04/16/2020 |  |  |  |  | 07/03/2020 | 12/31/9999 | 06/06/2020 | 07/03/2020
35042923 | *CANC* CWSP-ORO FINO 1101-LR 2022 *CANC | 08W | NV | Completion | ECES_CA1/CLSD | 05/03/2020 | 06/04/2018 | 05/06/2019 | [12 empty] | 05/06/2019 | 04/04/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/04/2020 | 05/03/2020
35043143 | *TRSFR* 35052728 CWSP LG1107 LR6009*CANC | 08W | DA | Completion | ECES_CA1/CLSD | 08/05/2020 | 04/16/2020 | 06/05/2020 | [10 empty] | 06/12/2020 | 06/12/2020 | 08/17/2018 | 04/16/2020 |  |  |  |  | 08/05/2020 | 12/31/9999 | 07/03/2020 | 08/05/2020
35043245 | *CANC* CWSP-ORO FINO 1101 OCB PH 1 *CANC | 08W | NV | Completion | ECES_CA1/CLSD | 05/03/2020 | 06/07/2018 | 05/06/2019 | [12 empty] | 05/06/2019 | 04/04/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/04/2020 | 05/03/2020
35043246 | *CANC* CWSP-ORO FINO 1101 OCB PH 2 *CANC | 08W | NV | Completion | ECES_CA1/CLSD | 05/03/2020 | 06/07/2018 | 05/06/2019 | [12 empty] | 05/06/2019 | 04/04/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/04/2020 | 05/03/2020
35043247 | *CANC* CWSP-ORO FINO 1101 OCB PH 3 *CANC | 08W | NV | Completion | ECES_CA1/CLSD | 05/03/2020 | 06/07/2018 | 05/06/2019 | [12 empty] | 05/06/2019 | 04/04/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/04/2020 | 05/03/2020
35043280 | *CANC*DO NOT USE*CWSP-PINE GROVE 11*CANC | 08W | ST | Completion | ECES_CA1/CLSD | 05/03/2020 | 06/07/2018 | 05/30/2019 | [12 empty] | 05/30/2019 | 04/02/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/02/2020 | 05/03/2020
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 | 08W | ST | Post-Doc | ECES_CA2/FICL | 11/05/2020 | 01/24/2019 | 05/16/2019 | 09/18/2019 | 09/19/2019 | 09/19/2019 | 09/19/2019 | 09/20/2019 | 10/11/2019 | 10/11/2019 | 10/14/2019 | 10/14/2019 | 12/22/2019 | 10/26/2020 | 11/05/2020 |  |  | 12/23/2019 | 01/13/2020 | 11/05/2020 | 12/31/9999
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | 08W | HB | Pre-Construction | ECES_CA1/UNSC | 09/02/2020 | 06/07/2018 | 06/07/2018 | 09/04/2019 | 05/22/2020 | 05/22/2020 | 05/22/2020 | 05/22/2020 | 09/02/2020 | 09/02/2020 | 12/31/9999 |  |  |  |  | 06/29/2019 | 07/03/2019
35043299 | CWSP-OH COND RPLC: EEL RIVER 1102 FU1907 | 08W | HB | Design | ECES_CA1/ESTS | 11/05/2020 | 06/07/2018 | 06/07/2018 | 11/05/2020 | 12/31/9999 | 06/14/2019 | 06/20/2019 | 04/16/2020 | 06/24/2020 | 07/26/2019 | 12/31/9999 | 09/02/2019 | 12/17/2019 | 09/16/2020 | 11/03/2020 | 11/03/2020 | 11/05/2020
35043303 | CWSP-OH COND RPLC: EEL RIVER 1102 FU1909 | 08W | HB | Documentation | ECES_CA1/DOCC | 04/16/2020 | 06/07/2018 | 06/07/2018 | 06/01/2019 | 06/03/2019 | 06/03/2019 | 06/03/2019 | 06/06/2019 | 06/26/2019 | 06/26/2019 | 08/05/2019 | 08/05/2019 | 09/23/2019 | 04/16/2020 | 12/31/9999 | 02/26/2020 | 04/16/2020
35043304 | *CANC* 2019 OH COND RPLC: EEL RIVE *CANC | 08W | HB | Completion | ECES_CA1/CLSD | 09/05/2019 | 06/07/2018 | 06/07/2018 | 06/07/2018 | 01/26/2019 | [8 empty] | 03/19/2019 | 03/29/2019 | 03/29/2019 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35043311 | CWSP - MIWUK 1701- LR8060 | 08W | YO | Initiation | ECES_CA1/UNSE | 04/16/2020 | 04/16/2020 | 12/31/9999 | [12 empty] | 08/17/2018 | 04/16/2020
35043381 | CWSP-MIWUK 1702-LR 6018-PHASE 1 | 08W | YO | Initiation | ECES_CA1/UNSE | 04/16/2020 | 04/16/2020 | 12/31/9999 | [12 empty] | 08/17/2018 | 04/16/2020
35043384 | CWSP-CURTIS 1705 - TS843 & 10590 | 08W | YO | Initiation | ECES_CA1/UNSE | 04/16/2020 | 04/16/2020 | 12/31/9999 | [12 empty] | 08/17/2018 | 04/16/2020
35043385 | *CANC* CWSP - TASSAJARA 2112 - FUS *CANC | 08W | DI | Completion | ECES_CA1/CLSD | 10/03/2019 | 06/11/2018 | 08/08/2018 | 08/08/2018 | 02/06/2019 | [8 empty] | 03/22/2019 | 03/27/2019 | 03/27/2019 | 09/23/2019 |  |  |  |  | 10/03/2019 | 12/31/9999 | 09/23/2019 | 10/03/2019
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | 08W | ST | Design | ECES_CA2/ESTS | 08/09/2019 | 06/11/2018 | 08/09/2019 | 08/09/2019 | 12/31/9999
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | 08W | ST | Design | ECES_CA2/ESTS | 11/03/2020 | 06/11/2018 | 08/09/2019 | 11/03/2020 | 12/31/9999 | 10/12/2020 | 11/03/2020
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | 08W | ST | Pending | ECES_CA2/PEND | 11/16/2020 | 06/11/2018 | 08/09/2019 | 08/09/2019 | 10/01/2020 | 10/01/2020 | 10/01/2020 | 11/16/2020 | 12/31/9999 | 11/13/2020 | 11/16/2020
35043586 | *CANC* PACIFICA 1102 WD: INS TREE W*CANC | 08W | PN | Completion | ECES_CA1/CLSD | 08/05/2020 | 06/13/2018 | 01/03/2019 | [10 empty] | 03/04/2020 | 07/14/2020 | 01/04/2020 | 03/04/2020 |  |  |  |  | 08/05/2020 | 12/31/9999 | 07/14/2020 | 08/05/2020
35043604 | CWSP - MIWUK 1702 - LR6018 - PHASE 2 | 08W | YO | Initiation | ECES_CA1/UNSE | 04/16/2020 | 04/16/2020 | 12/31/9999 | [12 empty] | 08/17/2018 | 04/16/2020
35043763 | *CANC* CWSP - MIDDLETOWN 1101-TS 1 *CANC | 08W | HB | Completion | ECES_CA1/CLSD | 10/03/2019 | 06/15/2018 | 12/04/2018 | [12 empty] | 12/04/2018 | 09/23/2019 |  |  |  |  | 10/03/2019 | 12/31/9999 | 09/23/2019 | 10/03/2019
35043830 | CWSP - MIRABEL 02 /MONTE RIO 13 - LR 652 | 08W | SO | Initiation | ECES_CA1/UNSE | 01/23/2020 | 01/23/2020 | 12/31/9999 | [10 empty] | 10/08/2018 | 10/09/2019 | 10/09/2019 | 01/06/2020 | [6 empty] | 01/06/2020 | 01/23/2020
35043949 | *CANC*DO NOT USE*CWSP-ORO FINO 1102*CANC | 08W | NV | Completion | ECES_CA1/CLSD | 05/03/2020 | 06/20/2018 | 07/24/2019 | [12 empty] | 07/24/2019 | 04/02/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/02/2020 | 05/03/2020
35043950 | CWSP - MIWUK 1701 - LR 10600 | 08W | YO | Initiation | ECES_CA1/UNSE | 04/16/2020 | 04/16/2020 | 12/31/9999 | [12 empty] | 08/17/2018 | 04/16/2020
35043952 | CWSP - MIWUK 1702 - LR 8090 | 08W | YO | Initiation | ECES_CA1/UNSE | 04/16/2020 | 04/16/2020 | 12/31/9999 | [12 empty] | 08/17/2018 | 04/16/2020
35043953 | *CANC* CWSP-ORO FINO 1102 LR-2560 *CANC | 08W | NV | Completion | ECES_CA1/CLSD | 05/03/2020 | 06/20/2018 | 05/06/2019 | [12 empty] | 05/06/2019 | 04/04/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/04/2020 | 05/03/2020
35043954 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC | 08W | NV | Completion | ECES_CA1/CLSD | 05/03/2020 | 06/20/2018 | 05/06/2019 | [12 empty] | 05/06/2019 | 04/02/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/02/2020 | 05/03/2020
35043955 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC | 08W | NV | Completion | ECES_CA1/CLSD | 05/03/2020 | 06/20/2018 | 05/06/2019 | [12 empty] | 05/06/2019 | 04/02/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/02/2020 | 05/03/2020
35043956 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC | 08W | NV | Completion | ECES_CA1/CLSD | 05/03/2020 | 06/20/2018 | 05/06/2019 | [12 empty] | 05/06/2019 | 04/02/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/02/2020 | 05/03/2020
35043986 | *CANC*DO NOT USE*CWSP-PINE GROVE 11*CANC | 08W | ST | Completion | ECES_CA1/CLSD | 05/03/2020 | 06/19/2018 | 05/06/2019 | [12 empty] | 05/06/2019 | 04/02/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/02/2020 | 05/03/2020
35043993 | CWSP - CAMPEVERS2105 - LR 74170 - 4KVPH4 | 08W | CC | Initiation | ECES_CA2/UNSE | 06/19/2018 | 06/19/2018 | 12/31/9999
35043994 | CWSP - CAMP EVERS 2105 - LR 11384 ZONE | 08W | CC | Initiation | ECES_CA2/UNSE | 06/19/2018 | 06/19/2018 | 12/31/9999
35044115 | CWSP - ROB ROY 2105 - LR 5166 | 08W | CC | Initiation | ECES_CA1/UNSE | 06/19/2018 | 06/19/2018 | 12/31/9999
35044117 | CWSP: LOS GATOS 1107 - LR60092 PH 2 | 08W | DA | Initiation | ECES_CA1/UNSE | 01/23/2020 | 01/23/2020 | 12/31/9999 | [6 empty] | 10/25/2019 | 01/03/2020 |  |  |  |  | 01/03/2020 | 01/06/2020 | [6 empty] | 01/06/2020 | 01/23/2020
35044284 | *CANC* CWSP-KONOCTI 1102-LR 532 *CANC | 08W | HB | Completion | ECES_CA1/CLSD | 09/05/2019 | 06/21/2018 | 12/04/2018 | [12 empty] | 12/04/2018 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35045959 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC | 08W | NV | Completion | ECES_CA1/CLSD | 05/03/2020 | 06/25/2018 | 05/06/2019 | [12 empty] | 05/06/2019 | 04/02/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/02/2020 | 05/03/2020
35046211 | CWSP - GARBERVILLE 1102 HENDRIX PILOT | 08W | HB | Initiation | ECES_CA1/UNSE | 07/12/2019 | 07/12/2019 | 12/31/9999 | 05/23/2019 | 07/12/2019
35046276 | CWSP LOS GATOS 1107-LR60092 PH 3 | 08W | DA | Initiation | ECES_CA1/UNSE | 06/27/2018 | 06/27/2018 | 12/31/9999
35046278 | CWSP LOS GATOS 1107-LR60092 PH 4 | 08W | DA | Initiation | ECES_CA1/UNSE | 06/27/2018 | 06/27/2018 | 12/31/9999
35046279 | CWSP - LOS GATOS 1107-LR60092 PH 5 | 08W | DA | Initiation | ECES_CA1/UNSE | 06/27/2018 | 06/27/2018 | 12/31/9999
35046280 | CWSP - LOS GATOS 1107 - LR60092 PH 6 | 08W | DA | Initiation | ECES_CA1/UNSE | 06/27/2018 | 06/27/2018 | 12/31/9999
35046366 | *CANC* CWSP BRUNSWICK 1105 LR-1030*CANC | 08W | SI | Completion | ECES_CA1/CLSD | 06/03/2020 | 06/28/2018 | 10/08/2018 | [6 empty] | 11/20/2019 | 05/16/2020 |  |  | 10/08/2018 | 07/30/2019 | 07/30/2019 | 11/05/2019 |  |  |  |  | 06/03/2020 | 12/31/9999 | 05/16/2020 | 06/03/2020
35046371 | ECOP - STANISLAUS 1702 LR 37276 | 08W | ST | Documentation | ECES_CA1/DCNL | 12/28/2020 | 12/26/2020 | 12/28/2020 | [12 empty] | 12/28/2020 | 12/31/9999
35046383 | *CANC* CWSP - MIWUK 1701 LR11800 &*CANC | 08W | YO | Completion | ECES_CA1/CLSD | 08/06/2019 | 02/14/2019 | 07/15/2019 | [12 empty] | 08/17/2018 | 02/14/2019 |  |  |  |  | 08/06/2019 | 12/31/9999 | 07/15/2019 | 08/06/2019
35046726 | *CANC* CWSP - LOS GATOS 1106 - LB4 *CANC | 08W | DA | Completion | ECES_CA1/CLSD | 09/05/2019 | 07/03/2018 | 11/16/2018 | [12 empty] | 11/16/2018 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35046759 | *CANC* CWSP - VOLTA 1102 - LR 1648 *CANC | 08W | NV | Completion | ECES_CA1/CLSD | 09/05/2019 | 07/04/2018 | 12/04/2018 | [12 empty] | 12/04/2018 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35046793 | *CANC* CWSP-SALT SPRINGS 2102-LR31 *CANC | 08W | ST | Completion | ECES_CA1/CLSD | 07/03/2019 | 07/06/2018 | 01/26/2019 | [6 empty] | 06/14/2019 | 06/20/2019 |  |  | 03/20/2019 | 04/02/2019 | 06/13/2019 | 06/14/2019 | 06/20/2019 | 06/26/2019 |  |  | 07/03/2019 | 12/31/9999 | 06/26/2019 | 07/03/2019
35046896 | *CANC* CWSP - FITCH MOUNTAIN 1113 *CANC | 08W | SO | Completion | ECES_CA1/CLSD | 09/05/2019 | 07/06/2018 | 11/10/2018 | [12 empty] | 11/10/2018 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35047143 | *CANC*DO NOT USE* CWSP - VOLTA 1102*CANC | 08W | NV | Completion | ECES_CA1/CLSD | 05/03/2020 | 07/09/2018 | 05/06/2019 | [12 empty] | 05/06/2019 | 04/02/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/02/2020 | 05/03/2020
35047146 | REDBUD 1101 RELOCATE FUSE 4865 IN T*CANC | 08W | HB | Completion | ECES_CA1/CLSD | 02/06/2020 | 07/09/2018 | 07/09/2018 | 07/09/2018 | 07/10/2019 |  |  |  |  | 10/25/2019 | 01/03/2020 |  |  |  |  | 01/03/2020 | 01/06/2020 |  |  |  |  | 02/06/2020 | 12/31/9999 | 01/06/2020 | 02/06/2020
35047311 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 1 | 08W | CC | Initiation | ECES_CA1/UNSE | 07/11/2018 | 07/11/2018 | 12/31/9999
35047312 | *CANC*CWSP-CAMP EVERS 2106 - 5020 P*CANC | 08W | CC | Completion | ECES_CA1/CLSD | 09/05/2019 | 07/11/2018 | 11/04/2018 | [12 empty] | 11/04/2018 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35047314 | CWSP - CAMPEVERS2105 - LR10294 - 4KV PH1 | 08W | CC | Initiation | ECES_CA1/UNSE | 07/11/2018 | 07/11/2018 | 12/31/9999
35047315 | CWSP: CAMPEVERS 2105 - LR11010 - 4KV PH2 | 08W | CC | Initiation | ECES_CA1/UNSE | 07/11/2018 | 07/11/2018 | 12/31/9999
35047316 | CWSP - CAMPEVERS2105 - LR 5206 - 4KV PH3 | 08W | CC | Initiation | ECES_CA1/UNSE | 07/11/2018 | 07/11/2018 | 12/31/9999
35047317 | CWSP - CAMPEVERS2105 - LR 5300 - 4KV PH7 | 08W | CC | Initiation | ECES_CA1/UNSE | 07/11/2018 | 07/11/2018 | 12/31/9999
35047318 | CWSP - CAMPEVERS2105 - BT402CB - 4KV PH6 | 08W | CC | Initiation | ECES_CA1/UNSE | 07/11/2018 | 07/11/2018 | 12/31/9999
35047402 | *CANC* CWSP-SALT SPRINGS 2102-LR31 *CANC | 08W | ST | Completion | ECES_CA1/CLSD | 07/03/2019 | 07/11/2018 | 01/25/2019 | [6 empty] | 06/14/2019 | 06/20/2019 |  |  | 03/20/2019 | 06/10/2019 | 06/13/2019 | 06/14/2019 | 06/20/2019 | 06/26/2019 | 01/25/2019 | 01/26/2019 | 07/03/2019 | 12/31/9999 | 06/26/2019 | 07/03/2019
35047414 | *CANC* CWSP - PARADISE 1106 - OCB *CANC | 08W | NV | Completion | ECES_CA1/CLSD | 09/05/2019 | 07/11/2018 | 11/16/2018 | [12 empty] | 11/16/2018 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35047418 | *CANC*DO NOT USE* CWSP-EL DORADO PH*CANC | 08W | SI | Completion | ECES_CA1/CLSD | 05/03/2020 | 07/11/2018 | 05/06/2019 | [12 empty] | 05/06/2019 | 04/02/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/02/2020 | 05/03/2020
35047419 | *CANC*CWSP-SHINGLE SPRINGS 2109-LR *CANC | 08W | SI | Completion | ECES_CA1/CLSD | 07/03/2020 | 07/11/2018 | 10/27/2018 | [6 empty] | 02/14/2019 | 06/10/2020 |  |  |  |  | 10/27/2018 | 11/29/2018 |  |  |  |  | 07/03/2020 | 12/31/9999 | 06/10/2020 | 07/03/2020
35047420 | CWSP - BRUNSWICK 1106 - LR 51486 | 08W | SI | Initiation | ECES_CA1/UNSE | 07/11/2018 | 07/11/2018 | 12/31/9999
35047422 | CWSP - PLACERVILLE 2106 - LR 1104 | 08W | SI | Initiation | ECES_CA1/UNSE | 07/11/2018 | 07/11/2018 | 12/31/9999
35047429 | CWSP - WILLITS 1104 - LR 34008 PH 1 | 08W | HB | Initiation | ECES_CA2/UNSE | 07/11/2018 | 07/11/2018 | 12/31/9999
35047557 | *CANCEL*CWSP-BRUNSWICK 1105 LR-32536 | 08W | SI | Initiation | ECES_CA1/UNSE | 01/23/2020 | 01/23/2020 | 12/31/9999 | [10 empty] | 10/08/2018 | 10/09/2019 | 10/09/2019 | 01/06/2020 | [6 empty] | 01/06/2020 | 01/23/2020
35047601 | ECOP-BRUNSWICK 1105-H01-LR32536 ZONE PH2 | 08W | SI | Initiation | ECES_CA1/UNSE | 07/13/2018 | 07/13/2018 | 12/31/9999
35048009 | CWSP - APPLE HILL 2102 LR97982 HARDENING | 08W | SI | Initiation | ECES_CA2/UNSE | 07/18/2018 | 07/18/2018 | 12/31/9999
35048011 | *CANC* CWSP - EL DORADO PH 2101 LR | 08W | SI | Completion | ECES_CA2/CLSD | 09/05/2019 | 07/18/2018 | 11/16/2018 | [12 empty] | 11/16/2018 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35048058 | *CANC* CWSP-COLUMBIA HILL 1101-LR | 08W | SI | Completion | ECES_CA2/CLSD | 09/05/2019 | 07/19/2018 | 12/03/2018 | [12 empty] | 12/03/2018 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35048613 | CWSP - PARADISE 1106 - LR 2084 | 08W | NV | Initiation | ECES_CA1/UNSE | 07/25/2018 | 07/25/2018 | 12/31/9999
35048678 | ECOP-BRUNSWICK 1105-H01-LR32536 ZONE PH3 | 08W | SI | Initiation | ECES_CA1/UNSE | 07/25/2018 | 07/25/2018 | 12/31/9999
35049537 | CWSP - BIG BASIN 1102 - 9741 | 08W | CC | Initiation | ECES_CA1/UNSE | 07/31/2018 | 07/31/2018 | 12/31/9999
35049538 | CWSP - BIG BASIN 1102 - 12758 | 08W | CC | Initiation | ECES_CA1/UNSE | 07/31/2018 | 07/31/2018 | 12/31/9999
35049913 | *CANC* CWSP - BRUNSWICK 1103 LR220 | 08W | SI | Completion | ECES_CA2/CLSD | 09/05/2019 | 07/24/2019 | 07/25/2019 | [12 empty] | 07/25/2019 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35050942 | CWSP: GARBERVILLE 1101 HENDRIX PILOT | 08W | HB | Initiation | ECES_CA1/UNSE | 08/02/2018 | 08/02/2018 | 12/31/9999
35050945 | CWSP - BRUNSWICK 1106 - 2143 | 08W | SI | Initiation | ECES_CA1/UNSE | 08/02/2018 | 08/02/2018 | 12/31/9999
35050947 | CWSP - BRUNSWICK 1106 - 2794 - PH 1 | 08W | SI | Initiation | ECES_CA1/UNSE | 08/02/2018 | 08/02/2018 | 12/31/9999
35050949 | CWSP - BRUNSWICK 1106 - 2794 - PH 2 | 08W | SI | Initiation | ECES_CA1/UNSE | 08/02/2018 | 08/02/2018 | 12/31/9999
35050950 | CWSP - BRUNSWICK 1106 - 2794 - PH 3 | 08W | SI | Initiation | ECES_CA1/UNSE | 08/02/2018 | 08/02/2018 | 12/31/9999
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | 08W | SO | Initiation | ECES_CA1/UNSE | 07/12/2019 | 07/12/2019 | 12/31/9999 | 09/19/2018 | 07/12/2019
35051252 | CWSP - PLACERVILLE 2106 - LR 1104 | 08W | SI | Initiation | ECES_CA1/UNSE | 08/08/2018 | 08/08/2018 | 12/31/9999
35051268 | CWSP - WILLITS 1104 - LR 34008 - PH 2 | 08W | HB | Initiation | ECES_CA2/UNSE | 08/07/2018 | 08/07/2018 | 12/31/9999
35051356 | CWSP - EL DORADO PH 2101 LR 26000 PH 2 | 08W | SI | Initiation | ECES_CA2/UNSE | 08/08/2018 | 08/08/2018 | 12/31/9999
35051472 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3 | 08W | CC | Design | ECES_CA1/ESTS | 07/16/2019 | 08/08/2018 | 07/16/2019 | 07/16/2019 | 12/31/9999
35051484 | CWSP - MONTE RIO 1113 - 8299 | 08W | SO | Initiation | ECES_CA2/UNSE | 08/08/2018 | 08/08/2018 | 12/31/9999
35051485 | CWSP - MONTE RIO 1111 - 1701 | 08W | SO | Initiation | ECES_CA2/UNSE | 08/08/2018 | 08/08/2018 | 12/31/9999
35052121 | *CANC* ZAMORA 1105 WIRE DOWN LR 36762 | 08W | SA | Completion | ECES_CA2/CLSD | 08/25/2018 | 08/10/2018 | 08/20/2018 | [18 empty] | 08/25/2018 | 12/31/9999
35052128 | *CANC*DO NOT USE* CWSP-STANISLAUS17*CANC | 08W | ST | Completion | ECES_CA1/CLSD | 05/03/2020 | 08/10/2018 | 05/06/2019 | [12 empty] | 05/06/2019 | 04/02/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/02/2020 | 05/03/2020
35052129 | *CANC*DO NOT USE*CWSP-STANISLAUS170*CANC | 08W | ST | Completion | ECES_CA1/CLSD | 05/03/2020 | 08/10/2018 | 05/06/2019 | [12 empty] | 05/06/2019 | 04/02/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/02/2020 | 05/03/2020
35052327 | CWSP-PARADISE 1101 OCB ZONE | 08W | NV | Initiation | ECES_CA1/UNSE | 08/15/2018 | 08/15/2018 | 12/31/9999
35052328 | CALISTOGA 1101 WIRE DOWN 18-0052856 | 08W | NB | Initiation | ECES_CA1/UNSE | 08/15/2018 | 08/15/2018 | 12/31/9999
35052718 | OCGC CWSP: ANGWIN OH TO UG DEMO - PH 2 | 08W | NB | Completion | ECES_CA2/CLSD | 04/26/2020 | 08/16/2018 | 08/22/2018 | 08/22/2018 | 11/02/2018 | 11/02/2018 | 11/02/2018 | 11/07/2018 | 01/11/2019 | 01/11/2019 | 02/18/2019 | 02/18/2019 | 10/29/2019 | 03/27/2020 | 04/24/2020 |  |  | 10/30/2019 | 11/12/2019 | 03/25/2020 | 03/25/2020 | 04/26/2020 | 12/31/9999
35052726 | CWSP - LOS GATOS 1106 LR 60116 PH1 | 08W | DA | Initiation | ECES_CA2/UNSE | 08/17/2018 | 08/17/2018 | 12/31/9999
35052727 | CWSP LOS GATOS 1106 LR 1106 PHASE 2 | 08W | DA | Initiation | ECES_CA2/UNSE | 08/17/2018 | 08/17/2018 | 12/31/9999
35052728 | CWSP - LOS GATOS 1107 LR 60092 PH1 | 08W | DA | Initiation | ECES_CA2/UNSE | 08/17/2018 | 08/17/2018 | 12/31/9999
35052729 | CWSP - BURNS 2101 - PH 1 | 08W | CC | Initiation | ECES_CA2/UNSE | 08/17/2018 | 08/17/2018 | 12/31/9999
35052730 | CWSP - BURNS 2101- PH 2 | 08W | CC | Initiation | ECES_CA2/UNSE | 08/17/2018 | 08/17/2018 | 12/31/9999
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | 08W | CC | Pre-Construction | ECES_CA2/UNSC | 08/18/2020 | 08/17/2018 | 03/08/2019 | 08/04/2020 | 08/04/2020 | 08/04/2020 | 08/04/2020 | 08/13/2020 | 08/18/2020 | 08/18/2020 | 12/31/9999
35052732 | CWSP - BIG BASIN 1101 5028 ZONE | 08W | CC | Initiation | ECES_CA2/UNSE | 08/17/2018 | 08/17/2018 | 12/31/9999
35052733 | CWSP - BIG BASIN 1101 - 10296 ZONE PH2 | 08W | CC | Initiation | ECES_CA2/UNSE | 08/17/2018 | 08/17/2018 | 12/31/9999
35052734 | CWSP - CAMP EVERS 2105 - LR 5232-33542 | 08W | CC | Initiation | ECES_CA2/UNSE | 08/17/2018 | 08/17/2018 | 12/31/9999
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | 08W | YO | Pre-Construction | ECES_CA2/UNSC | 10/21/2020 | 04/19/2019 | 08/12/2019 | 07/10/2020 | 07/13/2020 | 07/13/2020 | 07/13/2020 | 09/05/2020 | 10/21/2020 | 10/21/2020 | 12/31/9999 |  |  |  |  | 03/06/2019 | 04/19/2019
35052736 | CWSP - MIWUK 1701 LR11800 | 08W | YO | Initiation | ECES_CA2/UNSE | 08/17/2018 | 08/17/2018 | 12/31/9999
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | 08W | YO | Pending | ECES_CA2/PEND | 06/29/2020 | 08/17/2018 | 08/09/2019 | 06/18/2020 | 06/19/2020 | 06/19/2020 | 06/29/2020 | 06/29/2020 | 12/31/9999
35052738 | CWSP-CURTIS1705-TS843-PHASE1 | 08W | YO | Initiation | ECES_CA2/UNSE | 08/17/2018 | 08/17/2018 | 12/31/9999
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | 08W | YO | Construction | ECES_CA2/CONS | 05/21/2020 | 08/17/2018 | 08/06/2019 | 08/06/2019 | 04/10/2020 | 04/10/2020 | 04/10/2020 | 05/13/2020 | 05/13/2020 | 05/13/2020 | 05/21/2020 | 05/21/2020 | 12/31/9999
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | 08W | YO | Post-Doc | ECES_CA2/FICL | 02/09/2021 | 08/17/2018 | 08/06/2019 | 08/06/2019 | 03/19/2020 | 03/19/2020 | 03/19/2020 | 03/19/2020 | 04/08/2020 | 04/08/2020 | 04/23/2020 | 04/23/2020 | 08/08/2020 | 02/09/2021 | 02/09/2021 |  |  | 11/04/2020 | 11/30/2020 | 02/09/2021 | 02/09/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | 08W | YO | Construction | ECES_CA2/CONS | 08/17/2020 | 08/17/2018 | 08/09/2019 | 12/17/2019 | 12/18/2019 | 12/19/2019 | 12/19/2019 | 08/13/2020 | 08/13/2020 | 08/13/2020 | 08/17/2020 | 08/17/2020 | 12/31/9999
35052822 | CWSP - MIWUK 1701 - LR 8050 | 08W | YO | Initiation | ECES_CA2/UNSE | 08/17/2018 | 08/17/2018 | 12/31/9999
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | 08W | YO | Pre-Construction | ECES_CA2/UNSC | 10/25/2020 | 08/17/2018 | 08/06/2019 | 08/06/2019 | 07/02/2020 | 07/02/2020 | 07/03/2020 | 07/31/2020 | 10/25/2020 | 10/25/2020 | 12/31/9999
35052824 | CWSP - MIWUK 1702 - LR6018 - PH 2 | 08W | YO | Initiation | ECES_CA2/UNSE | 08/17/2018 | 08/17/2018 | 12/31/9999
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | 08W | YO | Construction | ECES_CA2/CONS | 08/31/2020 | 08/17/2018 | 08/06/2019 | 04/29/2020 | 04/29/2020 | 04/29/2020 | 04/29/2020 | 05/21/2020 | 05/27/2020 | 05/27/2020 | 08/31/2020 | 08/31/2020 | 12/31/9999
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | 08W | DI | Documentation | ECES_CA2/MAPP | 02/10/2021 | 08/20/2018 | 09/06/2018 | 05/17/2019 | 05/22/2019 | 05/22/2019 | 05/22/2019 | 12/02/2019 | 12/02/2019 | 12/02/2019 | 12/27/2019 | 12/27/2019 | 02/08/2021 | 02/08/2021 | 02/10/2021 |  |  | 02/10/2021 | 12/31/9999
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | 08W | PN | Pre-Construction | ECES_CA1/UNSC | 11/30/2020 | 08/28/2018 | 10/01/2018 | 06/13/2019 | 06/13/2019 | 06/13/2019 | 06/13/2019 | 11/24/2020 | 11/30/2020 | 11/30/2020 | 12/31/9999
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | 08W | SI | Initiation | ECES_CA2/UNSE | 09/05/2018 | 09/05/2018 | 12/31/9999
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | SI | Design | ECES_CA2/ESTS | 08/10/2020 | 09/20/2018 | 08/10/2020 | 08/10/2020 | 12/31/9999
35056433 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 | 08W | SI | Initiation | ECES_CA2/UNSE | 09/20/2018 | 09/20/2018 | 12/31/9999
35056434 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 | 08W | SI | Initiation | ECES_CA2/UNSE | 09/20/2018 | 09/20/2018 | 12/31/9999
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | 08W | SI | Initiation | ECES_CA2/UNSE | 09/20/2018 | 09/20/2018 | 12/31/9999
35056438 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 5 | 08W | SI | Initiation | ECES_CA2/UNSE | 09/20/2018 | 09/20/2018 | 12/31/9999
35056439 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 | 08W | SI | Initiation | ECES_CA2/UNSE | 09/20/2018 | 09/20/2018 | 12/31/9999
35056666 | *CANC* EST HILL 1101 LR 50486 HARDENING | 08W | SI | Completion | ECES_CA2/CLSD | 09/29/2018 | 09/24/2018 | 09/28/2018 | [18 empty] | 09/29/2018 | 12/31/9999
35056732 | CWSP FOREST HILL 1101 LR 50486 HARDENING | 08W | SI | Initiation | ECES_CA2/UNSE | 09/25/2018 | 09/25/2018 | 12/31/9999
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | SI | Pending | ECES_CA2/PEND | 08/31/2020 | 09/25/2018 | 06/18/2019 | 08/28/2020 | 08/31/2020 | 08/31/2020 | 08/31/2020 | 08/31/2020 | 12/31/9999
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | 08W | YO | Construction | ECES_CA2/CONS | 09/07/2020 | 09/25/2018 | 08/06/2019 | 06/22/2020 | 06/22/2020 | 06/22/2020 | 06/22/2020 | 06/22/2020 | 07/24/2020 | 07/24/2020 | 09/07/2020 | 09/07/2020 | 12/31/9999
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | SI | Approval | ECES_CA2/APPR | 11/17/2020 | 09/26/2018 | 06/18/2019 | 10/16/2020 | 11/17/2020 | 11/17/2020 | 11/17/2020 | 07/22/2020 | 07/22/2020
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | SI | Documentation | ECES_CA2/DOCC | 12/26/2019 | 09/27/2018 | 06/18/2019 | 08/23/2019 | 08/27/2019 | 09/24/2019 | 09/24/2019 | 08/27/2019 | 09/16/2019 | 09/24/2019 | 10/16/2019 | 10/16/2019 | 12/26/2019 | 12/26/2019 | 12/31/9999
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | SI | Pending | ECES_CA2/PEND | 07/17/2020 | 09/27/2018 | 06/18/2019 | 05/18/2020 | 07/16/2020 | 07/16/2020 | 07/16/2020 | 07/17/2020 | 07/17/2020 | 07/17/2020 | 07/17/2020
35057802 | CWSP-CAMPEVERS2105 - LR 12590 - 4KV PH5 | 08W | CC | Initiation | ECES_CA2/UNSE | 10/03/2018 | 10/03/2018 | 12/31/9999
35057921 | PUEBLO 2103 RECOND W TW PAST FUSE 2013 | 08W | NB | Initiation | ECES_CA2/UNSE | 10/04/2018 | 10/04/2018 | 12/31/9999
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | 08W | SI | Design | ECES_CA2/ESTS | 04/14/2020 | 10/05/2018 | 04/14/2020 | 04/14/2020 | 12/31/9999
35058060 | SWIFT 2110 - CONDUCTOR REPL | 08W | SJ | Initiation | ECES_CA2/UNSE | 10/05/2018 | 10/05/2018 | 12/31/9999
35058080 | *CANC* X-1104 OH RECOND SKYLINE *CANC | 08W | EB | Completion | ECES_CA1/CLSD | 09/05/2019 | 10/05/2018 | 11/21/2018 | [12 empty] | 11/21/2018 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35058272 | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 | 08W | SI | Initiation | ECES_CA2/UNSE | 10/08/2018 | 10/08/2018 | 12/31/9999
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | SI | Construction | ECES_CA2/CONS | 04/13/2020 | 10/08/2018 | 06/18/2019 | 06/18/2019 | 09/16/2019 | 09/16/2019 | 09/16/2019 | 09/17/2019 | 12/31/2019 | 12/31/2019 | 04/13/2020 | 04/13/2020 | 12/31/9999
35058794 | CWSP - APPLE HILL 2102 - 7502 - PHASE 1 | 08W | SI | Initiation | ECES_CA2/UNSE | 10/11/2018 | 10/11/2018 | 12/31/9999
35058795 | CWSP - APPLE HILL 2102 - 7502 - PHASE 2 | 08W | SI | Initiation | ECES_CA2/UNSE | 10/11/2018 | 10/11/2018 | 12/31/9999
35058797 | CWSP - APPLE HILL 2102 - 7502 - PHASE 3 | 08W | SI | Initiation | ECES_CA2/UNSE | 10/11/2018 | 10/11/2018 | 12/31/9999
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | 08W | NV | Documentation | ECES_CA2/DOCC | 02/06/2020 | 10/10/2018 | 06/18/2019 | 08/29/2019 | 08/29/2019 | 08/29/2019 | 08/29/2019 | 08/30/2019 | 10/14/2019 | 10/14/2019 | 10/21/2019 | 10/21/2019 | 02/06/2020 | 02/06/2020 | 12/31/9999
35059696 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH | 08W | SI | Initiation | ECES_CA2/UNSE | 10/18/2018 | 10/18/2018 | 12/31/9999
35060027 | CWSP-PARADISE 1104-TS 1571 | 08W | NV | Initiation | ECES_CA1/UNSE | 10/23/2018 | 10/23/2018 | 12/31/9999
35060157 | CWSP- HENDRIX DEMO - LIVERMORE TRNG CNTR | 08W | MI | Completion | ECES_CA1/CLSD | 02/29/2020 | 03/05/2019 | 03/14/2019 | 03/14/2019 | 03/25/2019 | 03/25/2019 | 03/25/2019 | 03/25/2019 | 03/25/2019 | 03/25/2019 | 05/24/2019 | 05/24/2019 | 10/16/2019 | 10/16/2019 | 10/24/2019 | 02/24/2019 | 02/28/2019 | 10/24/2019 | 11/04/2019 | 11/04/2019 | 02/25/2020 | 02/29/2020 | 12/31/9999
35060228 | 2019 OH COND RPLC: EEL RIVER 1102 FU1903 | 08W | HB | Initiation | ECES_CA1/UNSE | 10/24/2018 | 10/24/2018 | 12/31/9999
35060229 | 2018 OH COND RPLC: FRUITLAND 42 C/O 7449 | 08W | HB | Completion | ECES_CA1/CLSD | 09/26/2020 | 10/24/2018 | 01/03/2019 | 01/03/2019 | 03/06/2019 | 03/06/2019 | 03/06/2019 | 03/06/2019 | 03/11/2019 | 03/11/2019 | 07/01/2019 | 07/01/2019 | 09/05/2019 | 09/05/2019 | 06/22/2020 |  |  | 06/22/2020 | 09/10/2020 | 09/10/2020 | 09/24/2020 | 09/26/2020 | 12/31/9999
35060383 | WDDB - FRUITLAND 1142CB C/O 1679 | 08W | HB | Initiation | ECES_CA1/UNSE | 10/24/2018 | 10/24/2018 | 12/31/9999
35060387 | WDDB BIG RIVER 1101 FUSE 5187 RECONDUCTO | 08W | HB | Initiation | ECES_CA1/UNSE | 10/24/2018 | 10/24/2018 | 12/31/9999
35060580 | *CANC*BIG BEND 1102 - BLOOMER *CANC | 08W | NV | Completion | ECES_CA1/CLSD | 09/05/2019 | 10/26/2018 | 01/31/2019 | [16 empty] | 01/31/2019 | 08/05/2019 | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35060581 | *CANC* RECONDUCT PT. MORETTI FROM 5043 | 08W | CC | Completion | ECES_CA1/CLSD | 01/12/2019 | 10/26/2018 | 01/09/2019 | [18 empty] | 01/12/2019 | 12/31/9999
35060582 | SLO 1107 RECOD 3884 FT WITH 2CU TW | 08W | LP | Post-Doc | ECES_CA1/FICL | 07/27/2020 | 10/26/2018 | 12/07/2018 | 03/06/2019 | 03/06/2019 | 03/06/2019 | 03/06/2019 | 03/06/2019 | 04/08/2019 | 04/08/2019 | 07/10/2019 | 07/10/2019 | 10/25/2019 | 12/11/2019 | 07/27/2020 |  |  | 10/28/2019 | 11/22/2019 | 07/27/2020 | 12/31/9999
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | 08W | CC | Pending | ECES_CA2/PEND | 02/27/2020 | 10/26/2018 | 03/07/2019 | 02/26/2020 | 02/26/2020 | 02/26/2020 | 02/27/2020 | 02/27/2020 | 12/31/9999
35060586 | *CANC* RECONDUCTOR 5885 FT ZACA *CANC | 08W | LP | Completion | ECES_CA1/CLSD | 09/05/2019 | 10/26/2018 | 02/01/2019 | [10 empty] | 03/20/2019 | 03/25/2019 | 03/25/2019 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35060587 | *CANC* REPLACE~1.2MILES_MAINLINE_ *CANC | 08W | LP | Completion | ECES_CA1/CLSD | 09/05/2019 | 10/26/2018 | 02/01/2019 | [10 empty] | 03/20/2019 | 03/25/2019 | 03/25/2019 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35060990 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH3.01 | 08W | SI | Initiation | ECES_CA2/UNSE | 10/30/2018 | 10/30/2018 | 12/31/9999
35060991 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH2.01 | 08W | SI | Initiation | ECES_CA2/UNSE | 10/30/2018 | 10/30/2018 | 12/31/9999
35060992 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH1.01 | 08W | SI | Initiation | ECES_CA2/UNSE | 10/30/2018 | 10/30/2018 | 12/31/9999
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 | 08W | SI | Design | ECES_CA2/ESTS | 08/10/2020 | 10/30/2018 | 08/10/2020 | 08/10/2020 | 12/31/9999
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | 08W | SI | Design | ECES_CA2/ESTS | 08/10/2020 | 10/30/2018 | 08/10/2020 | 08/10/2020 | 12/31/9999
35060995 | CWSP-BRUNSWICK 1106 LR-2104 ZONE | 08W | SI | Initiation | ECES_CA2/UNSE | 10/30/2018 | 10/30/2018 | 12/31/9999
35061041 | CWSP – MONTE RIO 1112 – TS 15401 | 08W | SO | Initiation | ECES_CA2/UNSE | 10/30/2018 | 10/30/2018 | 12/31/9999
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | SI | Construction | ECES_CA2/CONS | 05/31/2020 | 10/31/2018 | 07/26/2019 | 05/18/2020 | 05/19/2020 | 05/19/2020 | 05/19/2020 | 05/27/2020 | 05/27/2020 | 05/27/2020 | 05/31/2020 | 05/31/2020 | 12/31/9999
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | SI | Construction | ECES_CA2/CONS | 09/14/2020 | 10/31/2018 | 07/26/2019 | 09/09/2020 | 09/09/2020 | 09/09/2020 | 09/09/2020 | 09/11/2020 | 09/14/2020 | 07/06/2020 | 08/07/2020 | 09/14/2020 | 12/31/9999
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | 08W | SI | Post-Doc | ECES_CA2/FICL | 10/27/2020 | 10/31/2018 | 07/26/2019 | 02/03/2020 | 02/13/2020 | 02/13/2020 | 02/14/2020 | 05/11/2020 | 05/16/2020 | 05/16/2020 | 05/18/2020 | 05/18/2020 | 08/20/2020 | 10/27/2020 | 10/27/2020 |  |  | 08/28/2020 | 10/26/2020 | 10/27/2020 | 10/27/2020
35061709 | SILVERADO 2104 RECONDUCTOR PROJECT | 08W | NB | Documentation | ECES_CA2/DOCC | 12/17/2019 | 11/06/2018 | 11/06/2018 | 11/06/2018 | 02/26/2019 | 02/26/2019 | 02/26/2019 | 03/27/2019 | 06/01/2019 | 06/01/2019 | 07/01/2019 | 07/01/2019 | 12/17/2019 | 12/17/2019 | 12/31/9999
35061810 | CWSP - EL DORADO PH 2101 ZONE 19612 | 08W | SI | Initiation | ECES_CA2/UNSE | 11/07/2018 | 11/07/2018 | 12/31/9999
35061811 | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 | 08W | SI | Initiation | ECES_CA2/UNSE | 11/07/2018 | 11/07/2018 | 12/31/9999
35061812 | CWSP - EL DORADO PH 2102 ZONE 6645 | 08W | SI | Initiation | ECES_CA2/UNSE | 11/07/2018 | 11/07/2018 | 12/31/9999
35062173 | Cancl FIRE PADSE 1105 INST NOVA BILLE RD | 08W | NV | Initiation | ECES_CA1/UNSE | 11/12/2018 | 11/12/2018 | 12/31/9999
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | 08W | SI | Initiation | ECES_CA2/UNSE | 01/04/2021 | 01/04/2021 | 12/31/9999 | [14 empty] | 12/22/2020 | 12/22/2020 | 12/22/2020 | 01/04/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | 08W | SI | Design | ECES_CA2/ESTS | 02/13/2021 | 11/15/2018 | 02/13/2021 | 02/13/2021 | 12/31/9999
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | 08W | SI | Initiation | ECES_CA2/UNSE | 11/15/2018 | 11/15/2018 | 12/31/9999
35064793 | LP RECONDUCTOR, CABRILLO 1104 S006CC102 | 08W | LP | Post-Doc | ECES_CA2/FICL | 05/29/2020 | 11/21/2018 | 11/26/2018 | 02/22/2019 | 02/25/2019 | 02/25/2019 | 02/25/2019 | 08/20/2019 | 08/20/2019 | 08/20/2019 | 08/20/2019 | 08/20/2019 | 09/18/2019 | 05/29/2020 | 05/29/2020 |  |  | 09/19/2019 | 12/12/2019 | 05/29/2020 | 05/29/2020
35065727 | *CANC* CAMP FIRE SOUTH SKYWAY EXTEN*CANC | 08W | NV | Completion | ECES_CA1/CLSD | 06/03/2020 | 12/03/2018 | 12/03/2018 | 03/04/2020 | 05/04/2020 | [10 empty] | 12/04/2019 | 03/04/2020 |  |  |  |  | 06/03/2020 | 12/31/9999 | 05/04/2020 | 06/03/2020
35065842 | CWSP-EL DORADO 2101 - LR 26000 - PH3 | 08W | SI | Initiation | ECES_CA2/UNSE | 12/03/2018 | 12/03/2018 | 12/31/9999
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | 08W | LP | Estimating Ready | ECES_CA2/UNSE | 12/10/2018 | 12/10/2018 | 12/31/9999
35066745 | BIG BEND 1102 - BLOOMER HILL 08W PHS 2 | 08W | NV | Completion | ECES_CA2/CLSD | 05/09/2020 | 12/11/2018 | 02/06/2019 | 06/05/2019 | 06/05/2019 | 05/28/2019 | 05/28/2019 | 06/05/2019 | 07/16/2019 | 07/16/2019 | 09/23/2019 | 09/23/2019 | 11/22/2019 | 11/22/2019 | 02/28/2020 |  |  | 02/28/2020 | 03/12/2020 | 03/12/2020 | 05/06/2020 | 05/09/2020 | 12/31/9999
35067619 | CWSP – MONTE RIO 1112 – LR 120 | 08W | SO | Initiation | ECES_CA2/UNSE | 12/21/2018 | 12/21/2018 | 12/31/9999
35071495 | RPL OH.CON.RESERVATION RD.1102 18-011072 | 08W | CC | Estimating Ready | ECES_CA1/UNSE | 01/17/2019 | 01/17/2019 | 12/31/9999
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 | 08W | NB | Documentation | ECES_CA2/DOCC | 05/13/2020 | 01/23/2019 | 02/06/2019 | 02/06/2019 | 06/10/2019 | 06/10/2019 | 06/10/2019 | 08/16/2019 | 08/28/2019 | 08/28/2019 | 10/14/2019 | 10/14/2019 | 05/13/2020 | 05/13/2020 | 12/31/9999
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | 08W | DA | Design | ECES_CA2/ESTS | 09/24/2019 | 01/23/2019 | 09/24/2019 | 09/24/2019 | 12/31/9999
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | 08W | ST | Construction | ECES_CA2/CONS | 07/31/2020 | 01/24/2019 | 08/05/2019 | 05/19/2020 | 05/19/2020 | 05/19/2020 | 05/19/2020 | 05/19/2020 | 07/17/2020 | 07/17/2020 | 07/31/2020 | 07/31/2020 | 12/31/9999
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | 08W | ST | Design | ECES_CA2/ADER | 10/13/2020 | 01/24/2019 | 08/05/2019 | 08/05/2019 | 10/13/2020 | 10/13/2020 | 12/31/9999
35072362 | CWSP-OH COND RPLC: EEL RIVER 1102 FU1913 | 08W | HB | Completion | ECES_CA2/CLSD | 05/31/2020 | 01/24/2019 | 05/30/2019 | 08/30/2019 | 08/30/2019 | 08/30/2019 | 08/30/2019 | 08/30/2019 | 09/05/2019 | 09/05/2019 | 09/24/2019 | 09/24/2019 | 12/17/2019 | 12/17/2019 | 02/26/2020 | 02/26/2020 | 03/23/2020 | 03/23/2020 | 04/02/2020 | 04/02/2020 | 05/25/2020 | 05/31/2020 | 12/31/9999
35072363 | *CANC* RECOND 15 298 FT 6CU 4CU & | 08W | NB | Completion | ECES_CA2/CLSD | 09/05/2019 | 01/24/2019 | 03/12/2019 | [10 empty] | 03/20/2019 | 06/13/2019 | 06/13/2019 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 09/05/2019
35072720 | RPL OH WIRE ON GABILN 1101 17-0077248 | 08W | CC | Completion | ECES_CA2/CLSD | 07/25/2020 | 01/28/2019 | 03/05/2019 | 06/10/2019 | 06/10/2019 | 06/10/2019 | 06/20/2019 | 06/20/2019 | 08/30/2019 | 08/30/2019 | 09/16/2019 | 09/16/2019 | 01/16/2020 | 01/16/2020 | 02/10/2020 |  |  | 02/10/2020 | 03/31/2020 | 03/31/2020 | 07/24/2020 | 07/25/2020 | 12/31/9999
35073059 | SONOMA1104 WIREDOWN | 08W | SO | Estimating Ready | ECES_CA1/UNSE | 01/31/2019 | 01/31/2019 | 12/31/9999
35073637 | LOS GATOS 1107 RECOND FUSE 468855 ZONE | 08W | DA | Estimating Ready | ECES_CA1/UNSE | 02/04/2019 | 02/04/2019 | 12/31/9999
35074009 | ALTO 1124 WIRE DOWN ILIS 18-0109573 | 08W | NB | Initiation | ECES_CA1/UNSE | 02/06/2019 | 02/06/2019 | 12/31/9999
35074388 | RECOND GV2101 FUSE 12347 ZONE | 08W | CC | Estimating Ready | ECES_CA2/UNSE | 02/08/2019 | 02/08/2019 | 12/31/9999
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | 08W | ST | Design | ECES_CA1/ESTS | 02/17/2021 | 01/13/2021 | 02/17/2021 | 02/17/2021 | 12/31/9999
35075365 | RPL OH.COND.CAMP EVERS 2106 19-0015630 | 08W | CC | Estimating Ready | ECES_CA1/UNSE | 02/19/2019 | 02/19/2019 | 12/31/9999
35075591 | SILVERADO 2105 WIRE DOWN PH 1 (CANCEL) | 08W | NB | Completion | ECES_CA1/CLSD | 05/22/2019 | 02/20/2019 | 02/20/2019 | 02/20/2019 | 05/22/2019 | [16 empty] | 05/22/2019 | 12/31/9999
35075594 | SILVERADO 2105 WIRE DOWN PH-2 (CANCEL) | 08W | NB | Completion | ECES_CA1/CLSD | 05/22/2019 | 02/20/2019 | 05/22/2019 | 02/20/2019 | 02/20/2019 | [16 empty] | 05/22/2019 | 12/31/9999
35075647 | SILVERADO 2105 WIRE DOWN PH-3 (CANCEL) | 08W | NB | Completion | ECES_CA1/CLSD | 05/22/2019 | 02/20/2019 | 05/22/2019 | 02/20/2019 | 02/20/2019 | [16 empty] | 05/22/2019 | 12/31/9999
35075650 | SILVERADO 2105 WIRE DOWN PH-4 (CANCEL) | 08W | NB | Completion | ECES_CA1/CLSD | 05/22/2019 | 02/20/2019 | 04/10/2019 | 04/10/2019 | 05/22/2019 | [16 empty] | 05/22/2019 | 12/31/9999
35076062 | *CANC* RECONDUCTOR 17547 FT OF 4AC *CANC | 08W | LP | Completion | ECES_CA1/CLSD | 10/03/2019 | 02/25/2019 | 03/06/2019 | [12 empty] | 03/06/2019 | 09/24/2019 |  |  |  |  | 10/03/2019 | 12/31/9999 | 09/24/2019 | 10/03/2019
35076064 | *CANC* 14184 FT OF 4ACSR&3363 FT OF 6CU | 08W | LP | Completion | ECES_CA1/CLSD | 03/09/2019 | 02/25/2019 | 03/08/2019 | [18 empty] | 03/09/2019 | 12/31/9999
35076129 | DIAMOND SPRINGS 1105 RECOND WD18-0105867 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/26/2019 | 02/26/2019 | 12/31/9999
35076130 | TAMARACK 1101 WD 19-0011942 | 08W | SI | Initiation | ECES_CA1/UNSE | 02/26/2019 | 02/26/2019 | 12/31/9999
35077348 | RECONDUCTOR 17547 FT OF 4ACSR W 2CU TW | 08W | LP | Initiation | ECES_CA2/UNSE | 03/05/2019 | 03/05/2019 | 12/31/9999
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR | 08W | NB | Design | ECES_CA1/ADER | 01/20/2021 | 10/21/2020 | 01/20/2021 | 01/20/2021 | 01/20/2021 | 01/20/2021 | 12/31/9999 |  |  | 11/20/2019 | 02/05/2020 | 09/05/2019 | 10/15/2019 | 10/03/2020 | 10/04/2020 | 10/04/2020 | 10/05/2020 | [6 empty] | 10/05/2020 | 10/21/2020
35081660 | OH RECONDUCTOR - ROB ROY 2105 -S028CC119 | 08W | CC | Documentation | ECES_CA2/DCNL | 03/27/2019 | 03/27/2019 | 03/27/2019 | 03/27/2019 | 03/27/2019 | [10 empty] | 03/27/2019 | 12/31/9999
35081748 | OH RECONDUCTOR - ROB ROY 2105 -S028CC119 | 08W | CC | Completion | ECES_CA1/CLSD | 06/20/2020 | 03/27/2019 | 03/27/2019 | 05/28/2019 | 05/28/2019 | 05/28/2019 | 05/28/2019 | 05/28/2019 | 08/23/2019 | 08/23/2019 | 09/09/2019 | 09/09/2019 | 02/24/2020 | 02/24/2020 | 04/06/2020 |  |  | 04/06/2020 | 04/23/2020 | 04/23/2020 | 06/17/2020 | 06/20/2020 | 12/31/9999
35081862 | MARTELL 1101 RECOND. 4ACSR W/ 1/0AR TW | 08W | ST | Initiation | ECES_CA2/UNSE | 03/28/2019 | 03/28/2019 | 12/31/9999
35085393 | CWSP - SILVERADO 2104 - LR722 PH 1B | 08W | NB | Post-Doc | ECES_CA2/FICL | 10/28/2020 | 04/10/2019 | 04/18/2019 | 04/18/2019 | 06/13/2019 | 06/13/2019 | 06/13/2019 | 06/25/2019 | 08/07/2019 | 08/07/2019 | 12/31/9999 | 09/03/2019 | 04/01/2020 | 09/09/2020 | 10/28/2020 |  |  | 10/28/2020 | 10/28/2020 | 10/28/2020 | 12/31/9999
35085532 | CWSP - SILVERADO 2104 - LR722 PH 1C | 08W | NB | Post-Doc | ECES_CA2/FICL | 11/11/2020 | 04/10/2019 | 04/18/2019 | 04/18/2019 | 06/06/2019 | 06/06/2019 | 06/06/2019 | 07/17/2019 | 07/27/2019 | 07/27/2019 | 09/16/2019 | 09/16/2019 | 01/23/2020 | 01/23/2020 | 10/28/2020 |  |  | 10/28/2020 | 11/11/2020 | 11/11/2020 | 12/31/9999
35085533 | CWSP - SILVERADO 2104 - LR722 PH 1D | 08W | NB | Post-Doc | ECES_CA2/FICL | 08/17/2020 | 04/10/2019 | 04/18/2019 | 08/30/2019 | 09/06/2019 | 09/06/2019 | 09/06/2019 | 09/06/2019 | 09/10/2019 | 09/10/2019 | 09/11/2019 | 09/11/2019 | 05/13/2020 | 05/13/2020 | 08/04/2020 |  |  | 08/04/2020 | 08/17/2020 | 08/17/2020 | 12/31/9999
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E | 08W | NB | Documentation | ECES_CA2/DOCC | 02/21/2020 | 04/10/2019 | 05/03/2019 | 05/03/2019 | 08/16/2019 | 08/16/2019 | 08/16/2019 | 08/16/2019 | 09/27/2019 | 09/27/2019 | 10/14/2019 | 10/14/2019 | 02/21/2020 | 02/21/2020 | 12/31/9999
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | 08W | NB | Documentation | ECES_CA2/DOCC | 02/06/2020 | 04/10/2019 | 05/03/2019 | 05/03/2019 | 07/26/2019 | 07/26/2019 | 07/26/2019 | 08/01/2019 | 10/04/2019 | 10/04/2019 | 11/11/2019 | 11/11/2019 | 02/06/2020 | 02/06/2020 | 12/31/9999
35085536 | CWSP - SILVERADO 2104 - LR722 PH 1G | 08W | NB | Documentation | ECES_CA2/DOCC | 12/11/2019 | 04/10/2019 | 05/03/2019 | 05/03/2019 | 08/12/2019 | 08/12/2019 | 08/12/2019 | 08/13/2019 | 09/20/2019 | 09/20/2019 | 10/01/2019 | 10/01/2019 | 12/11/2019 | 12/11/2019 | 12/31/9999
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H | 08W | NB | Documentation | ECES_CA2/DOCC | 05/13/2020 | 04/10/2019 | 04/25/2019 | 08/30/2019 | 08/30/2019 | 07/03/2019 | 07/03/2019 | 09/05/2019 | 12/31/9999 | 09/09/2019 | 09/16/2019 | 09/16/2019 | 05/13/2020 | 05/13/2020 | 12/31/9999
35085538 | SILVERADO 2105 WIRE DOWN - PH 1 | 08W | NB | Post-Doc | ECES_CA2/FICL | 09/02/2020 | 04/10/2019 | 04/11/2019 | 04/11/2019 | 07/26/2019 | 07/26/2019 | 07/26/2019 | 09/05/2019 | 12/31/9999 | 09/09/2019 | 09/16/2019 | 09/16/2019 | 04/29/2020 | 04/29/2020 | 08/25/2020 |  |  | 08/25/2020 | 09/02/2020 | 09/02/2020 | 12/31/9999
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 | 08W | NB | Documentation | ECES_CA2/DOCC | 05/13/2020 | 04/10/2019 | 04/18/2019 | 04/18/2019 | 08/08/2019 | 08/08/2019 | 08/09/2019 | 09/04/2019 | 09/09/2019 | 09/09/2019 | 10/07/2019 | 10/07/2019 | 05/13/2020 | 05/13/2020 | 12/31/9999
35085680 | SILVERADO 2105 WIRE DOWN - PH 3 | 08W | NB | Design | ECES_CA2/ESTS | 12/19/2019 | 04/10/2019 | 04/18/2019 | 12/19/2019 | 12/31/9999 | 07/23/2019 | 07/23/2019 | 07/23/2019 | 12/19/2019
35085681 | SILVERADO 2105 WIRE DOWN - PH 4 | 08W | NB | Documentation | ECES_CA2/DOCC | 10/14/2019 | 04/10/2019 | 04/11/2019 | 04/11/2019 | 06/07/2019 | 06/07/2019 | 06/07/2019 | 08/28/2019 | 08/30/2019 | 08/30/2019 | 09/04/2019 | 09/04/2019 | 10/14/2019 | 10/14/2019 | 12/31/9999
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | 08W | CC | Pending | ECES_CA1/PEND | 06/25/2019 | 04/11/2019 | 04/11/2019 | 06/25/2019 | 06/25/2019 | 06/25/2019 | 06/25/2019 | 06/25/2019 | 12/31/9999
35089880 | OCGC PIH SILVERADO 2104 - ANGWIN UG_PH 2 | 08W | NB | Completion | ECES_CA1/CLSD | 08/29/2020 | 04/25/2019 | 04/25/2019 | 06/18/2019 | 06/25/2019 | 06/06/2020 | 07/30/2020 | 08/12/2019 | 09/23/2019 | 09/23/2019 | 10/29/2019 | 06/18/2019 | 06/18/2019 | 10/29/2019 | 10/29/2019 | 06/05/2019 | 06/18/2019 | 10/29/2019 | 06/05/2020 | 07/30/2020 | 08/26/2020 | 08/29/2020 | 12/31/9999
35093737 | FAIRVIEW 2207-CROCKETT BLVD-WIRE DOWN | 08W | DI | Initiation | ECES_CA1/UNSE | 04/30/2019 | 04/30/2019 | 12/31/9999
35094388 | CWSP-KONOCTI 1102-LR 532 PH 1 | 08W | HB | Documentation | ECES_CA2/MAPP | 02/07/2020 | 05/01/2019 | 05/22/2019 | 05/22/2019 | 07/01/2019 | 07/01/2019 | 07/01/2019 | 08/28/2019 | 09/16/2019 | 09/16/2019 | 09/23/2019 | 08/28/2019 | 08/28/2019 | 09/23/2019 | 02/07/2020 |  |  | 02/07/2020 | 12/31/9999
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | 08W | HB | Design | ECES_CA2/ESTS | 05/29/2019 | 05/01/2019 | 05/29/2019 | 05/29/2019 | 12/31/9999
35094390 | CWSP-KONOCTI 1102-LR 532 PH 3 | 08W | HB | Documentation | ECES_CA2/DOCC | 05/13/2020 | 05/01/2019 | 06/06/2019 | 06/06/2019 | 07/26/2019 | 07/26/2019 | 07/26/2019 | 08/09/2019 | 09/13/2019 | 09/13/2019 | 09/24/2019 | 09/24/2019 | 05/13/2020 | 05/13/2020 | 12/31/9999
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | 08W | HB | Pre-Construction | ECES_CA2/UNSC | 02/14/2020 | 05/01/2019 | 08/14/2019 | 01/10/2020 | 01/10/2020 | 01/10/2020 | 01/10/2020 | 01/17/2020 | 02/14/2020 | 02/14/2020 | 12/31/9999
35094392 | OCGC CWSP-KONOCTI 1102-LR 532 PH 5 | 08W | HB | Post-Doc | ECES_CA2/FICL | 08/26/2020 | 05/01/2019 | 07/11/2019 | 07/11/2019 | 08/29/2019 | 08/29/2019 | 08/29/2019 | 08/29/2019 | 10/22/2019 | 10/22/2019 | 12/11/2019 |  |  | 04/20/2020 | 08/26/2020 |  |  | 12/12/2019 | 03/05/2020 | 08/26/2020 | 12/31/9999
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | 08W | HB | Post-Doc | ECES_CA2/FICL | 01/29/2021 | 05/01/2019 | 07/12/2019 | 12/19/2019 | 12/19/2019 | 12/19/2019 | 12/19/2019 | 12/19/2019 | 02/14/2020 | 02/14/2020 | 04/27/2020 | 04/27/2020 | 08/11/2020 | 01/29/2021 | 01/29/2021 |  |  | 08/12/2020 | 09/23/2020 | 01/29/2021 | 01/29/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | 08W | HB | Documentation | ECES_CA2/DOCC | 12/29/2020 | 05/01/2019 | 07/31/2019 | 12/04/2019 | 12/09/2019 | 12/09/2019 | 12/09/2019 | 12/11/2019 | 02/03/2020 | 02/04/2020 | 02/24/2020 | 02/24/2020 | 12/29/2020 | 12/29/2020 | 12/31/9999
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | 08W | HB | Design | ECES_CA2/ESTS | 08/13/2020 | 05/01/2019 | 08/13/2020 | 08/13/2020 | 12/31/9999
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | 08W | HB | Pre-Construction | ECES_CA2/UNSC | 03/20/2020 | 05/01/2019 | 07/31/2019 | 02/21/2020 | 02/21/2020 | 02/21/2020 | 02/21/2020 | 02/21/2020 | 03/20/2020 | 03/20/2020 | 12/31/9999
35094397 | CWSP-KONOCTI 1102-LR 532 PH 10 | 08W | HB | Documentation | ECES_CA2/DOCC | 02/09/2021 | 05/01/2019 | 07/31/2019 | 07/31/2019 | 12/19/2019 | 12/19/2019 | 12/19/2019 | 12/26/2019 | 02/14/2020 | 02/14/2020 | 05/11/2020 | 05/11/2020 | 02/09/2021 | 02/09/2021 | 12/31/9999
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | 08W | ST | Pending | ECES_CA2/PEND | 06/29/2020 | 05/03/2019 | 08/12/2019 | 06/29/2020 | 06/29/2020 | 06/29/2020 | 06/29/2020 | 06/29/2020 | 12/31/9999
35094514 | CWSP-ORO FINO 1101 LR-2022 PH 1.1 | 08W | NV | Pending | ECES_CA2/PEND | 09/29/2020 | 05/03/2019 | 11/18/2019 | 11/18/2019 | 08/03/2020 | 08/03/2020 | 08/04/2020 | 09/29/2020 | 12/31/9999 | 09/28/2020 | 09/29/2020
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 | 08W | NV | Design | ECES_CA2/ESTS | 10/22/2020 | 05/03/2019 | 11/18/2019 | 10/22/2020 | 12/31/9999 | 09/10/2020 | 10/22/2020
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | 08W | NV | Pending | ECES_CA2/PEND | 10/29/2020 | 05/03/2019 | 11/18/2019 | 10/29/2020 | 10/29/2020 | 10/29/2020 | 10/29/2020 | 10/29/2020 | 12/31/9999
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | 08W | NV | Pending | ECES_CA2/PEND | 10/29/2020 | 05/03/2019 | 11/18/2019 | 10/27/2020 | 10/28/2020 | 10/28/2020 | 10/29/2020 | 10/29/2020 | 12/31/9999
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 | 08W | NV | Design | ECES_CA2/ADER | 11/13/2020 | 05/03/2019 | 11/18/2019 | 11/05/2020 | 11/13/2020 | 11/13/2020 | 12/31/9999
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | 08W | NV | Design | ECES_CA2/ADER | 10/14/2020 | 05/03/2019 | 11/18/2019 | 09/28/2020 | 10/14/2020 | 10/14/2020 | 12/31/9999
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 | 08W | NV | Design | ECES_CA2/ADER | 09/10/2020 | 05/03/2019 | 11/18/2019 | 11/18/2019 | 09/10/2020 | 09/10/2020 | 12/31/9999
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | 08W | NV | Pending | ECES_CA2/PEND | 08/01/2020 | 05/03/2019 | 11/18/2019 | 11/18/2019 | 07/31/2020 | 07/31/2020 | 08/01/2020 | 08/01/2020 | 12/31/9999
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | 08W | NV | Pending | ECES_CA2/PEND | 12/22/2020 | 05/03/2019 | 11/18/2019 | 12/16/2020 | 12/18/2020 | 12/18/2020 | 12/18/2020 | 12/22/2020 | 12/22/2020
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | 08W | ST | Design | ECES_CA2/ADER | 10/23/2020 | 05/03/2019 | 08/12/2019 | 08/12/2019 | 10/23/2020 | 10/23/2020 | 12/31/9999
35095164 | CWSP-ORO FINO 1101 LR-2022 PH 3.1 | 08W | NV | Pre-Construction | ECES_CA2/UNSC | 10/06/2020 | 05/03/2019 | 11/18/2019 | 11/18/2019 | 08/12/2020 | 08/12/2020 | 08/12/2020 | 08/13/2020 | 10/06/2020 | 10/06/2020 | 12/31/9999
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 | 08W | NV | Post-Doc | ECES_CA2/FICL | 01/28/2021 | 05/03/2019 | 06/18/2019 | 06/18/2019 | 07/22/2019 | 07/22/2019 | 07/22/2019 | 07/22/2019 | 08/19/2019 | 08/19/2019 | 09/16/2019 | 09/16/2019 | 11/25/2019 | 11/25/2019 | 01/26/2021 |  |  | 01/26/2021 | 01/28/2021 | 01/28/2021 | 12/31/9999
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | 08W | SI | Post-Doc | ECES_CA2/FICL | 01/12/2021 | 05/03/2019 | 06/18/2019 | 03/04/2020 | 03/04/2020 | 03/04/2020 | 03/10/2020 | 03/10/2020 | 04/27/2020 | 04/27/2020 | 07/10/2020 | 07/10/2020 | 08/24/2020 | 08/24/2020 | 12/15/2020 |  |  | 12/15/2020 | 01/12/2021 | 01/12/2021 | 12/31/9999
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | 08W | ST | Pending | ECES_CA2/PEND | 07/07/2020 | 05/03/2019 | 08/05/2019 | 07/02/2020 | 07/06/2020 | 07/06/2020 | 07/07/2020 | 07/07/2020 | 12/31/9999
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | 08W | ST | Pending | ECES_CA2/PEND | 08/24/2020 | 05/03/2019 | 08/12/2019 | 08/12/2019 | 08/10/2020 | 08/10/2020 | 08/10/2020 | 08/24/2020 | 12/31/9999 | 08/22/2020 | 08/24/2020
35095246 | BUCOCAMP - ERIKA DRIVE, PARADISE | 08W | NV | Pre-Construction | ECES_CA1/UNSC | 01/28/2021 | 05/05/2019 | 05/05/2019 | 05/05/2019 | 05/05/2019 | 05/05/2019 | 05/06/2019 | 05/07/2019 | 01/28/2021 | 01/28/2021 | 12/31/9999
35098578 | CWSP-COLUMBIA HILL 1101-LR 2212 PH2 | 08W | SI | Completion | ECES_CA2/CLSD | 12/05/2020 | 05/08/2019 | 06/11/2019 | 06/11/2019 | 08/30/2019 | 08/30/2019 | 09/16/2019 | 09/16/2019 | 09/30/2019 | 09/30/2019 | 09/30/2019 | 09/30/2019 | 12/27/2019 | 11/24/2020 | 12/02/2020 |  |  | 11/06/2020 | 11/18/2020 | 11/18/2020 | 11/19/2020 | 12/05/2020 | 12/31/9999
35098579 | CWSP-COLUMBIA HILL 1101-LR 2212 PH3 | 08W | SI | Completion | ECES_CA2/CLSD | 11/21/2020 | 05/08/2019 | 06/05/2019 | 08/30/2019 | 08/30/2019 | 08/30/2019 | 08/30/2019 | 08/30/2019 | 09/03/2019 | 09/03/2019 | 10/09/2019 |  |  | 10/09/2019 | 03/02/2020 |  |  | 03/02/2020 | 11/12/2020 | 11/12/2020 | 11/16/2020 | 11/21/2020 | 12/31/9999
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | 08W | SI | Documentation | ECES_CA2/DOCC | 12/07/2020 | 05/08/2019 | 05/31/2019 | 04/24/2020 | 04/24/2020 | 10/24/2019 | 10/24/2019 | 04/24/2020 | 05/04/2020 | 05/04/2020 | 05/14/2020 | 05/14/2020 | 12/07/2020 | 12/07/2020 | 12/31/9999
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 | 08W | SI | Documentation | ECES_CA2/DOCC | 11/24/2020 | 05/08/2019 | 06/05/2019 | 08/06/2019 | 08/07/2019 | 08/07/2019 | 08/08/2019 | 08/08/2019 | 08/23/2019 | 08/23/2019 | 09/18/2019 | 09/18/2019 | 11/25/2019 | 11/24/2020 | 12/31/9999 |  |  | 09/29/2020 | 10/13/2020 | 11/03/2020 | 11/03/2020 | 11/07/2020 | 11/24/2020
35099603 | MORRO BAY 1102 RECON 4728 FT W TW | 08W | LP | Initiation | ECES_CA1/UNSE | 05/10/2019 | 05/10/2019 | 12/31/9999
35099654 | BR-04-01-W (E) SUNSET DR PARB | 08W | NV | Documentation | ECES_CA2/DOCC | 10/28/2020 | 05/11/2019 | 05/11/2019 | 07/01/2019 | 07/01/2019 | 07/01/2019 | 07/01/2019 | 07/03/2019 | 10/31/2019 | 10/31/2019 | 11/11/2019 | 11/11/2019 | 10/28/2020 | 10/28/2020 | 12/31/9999
35101875 | BR-01-10-W (E) BILLIE & LUCKY JOHN PARB | 08W | NV | Post-Doc | ECES_CA1/FICL | 08/21/2020 | 05/15/2019 | 05/15/2019 | 08/19/2019 | 08/20/2019 | 08/20/2019 | 08/20/2019 | 08/20/2019 | 08/30/2019 | 08/30/2019 | 10/28/2019 | 10/28/2019 | 08/04/2020 | 08/04/2020 | 08/06/2020 |  |  | 08/06/2020 | 08/21/2020 | 08/21/2020 | 12/31/9999
35101876 | BR-01-08-W (E) MADRONE_BILLE_GRAHAM PARB | 08W | NV | Post-Doc | ECES_CA1/FICL | 07/04/2020 | 05/15/2019 | 07/02/2019 | 08/06/2019 | 08/07/2019 | 08/07/2019 | 08/07/2019 | 08/08/2019 | 09/27/2019 | 09/27/2019 | 11/11/2019 | 11/11/2019 | 06/16/2020 | 06/16/2020 | 06/17/2020 |  |  | 06/17/2020 | 07/04/2020 | 07/04/2020 | 12/31/9999
35101877 | BR-01-06-W (E) THOMASSON LN PARB | 08W | NV | Post-Doc | ECES_CA1/FICL | 09/30/2020 | 05/15/2019 | 05/15/2019 | 08/09/2019 | 08/09/2019 | 08/09/2019 | 08/12/2019 | 11/26/2019 | 11/27/2019 | 11/27/2019 | 07/08/2020 |  |  | 08/24/2020 | 09/30/2020 | 07/15/2019 | 07/25/2019 | 07/13/2020 | 07/20/2020 | 09/30/2020 | 12/31/9999
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 | 08W | DI | Post-Doc | ECES_CA2/FICL | 08/07/2020 | 05/16/2019 | 05/20/2019 | 07/09/2019 | 07/11/2019 | 07/11/2019 | 07/11/2019 | 08/01/2019 | 09/12/2019 | 09/12/2019 | 09/23/2019 | 09/23/2019 | 01/23/2020 | 01/23/2020 | 01/24/2020 |  |  | 01/24/2020 | 08/07/2020 | 08/07/2020 | 12/31/9999
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | 08W | DI | Documentation | ECES_CA2/DOCC | 09/21/2020 | 05/17/2019 | 05/20/2019 | 10/24/2019 | 10/25/2019 | 10/25/2019 | 10/28/2019 | 01/24/2020 | 04/15/2020 | 01/23/2020 | 01/24/2020 | 04/15/2020 | 05/01/2020 | 09/21/2020 | 12/31/9999 |  |  | 05/07/2020 | 09/16/2020 | 09/16/2020 | 09/21/2020
35103324 | CWSP - ROSSMOOR 1102 - OCB | 08W | DI | Completion | ECES_CA2/CLSD | 12/05/2020 | 05/17/2019 | 05/20/2019 | 08/02/2019 | 08/02/2019 | 08/02/2019 | 08/02/2019 | 08/02/2019 | 08/20/2019 | 09/26/2019 | 10/01/2019 | 10/01/2019 | 03/05/2020 | 07/30/2020 | 08/28/2020 |  |  | 05/12/2020 | 05/27/2020 | 12/02/2020 | 12/03/2020 | 12/05/2020 | 12/31/9999
35103325 | CWSP - MORAGA 1102 & 1104 - OCB | 08W | DI | Completion | ECES_CA2/CLSD | 12/12/2020 | 05/17/2019 | 05/20/2019 | 08/28/2019 | 09/04/2019 | 09/04/2019 | 09/04/2019 | 09/04/2019 | 10/15/2019 | 10/15/2019 | 10/28/2019 | 10/28/2019 | 06/01/2020 | 06/01/2020 | 06/23/2020 |  |  | 06/23/2020 | 10/28/2020 | 10/28/2020 | 12/09/2020 | 12/12/2020 | 12/31/9999
35103617 | BR-07-09-W (E) WOODGLEN PARB | 08W | NV | Initiation | ECES_CA1/UNSE | 05/20/2019 | 05/20/2019 | 12/31/9999
35103619 | BR-10-03-W (E) FILBERT PARB | 08W | NV | Initiation | ECES_CA1/UNSE | 05/20/2019 | 05/20/2019 | 12/31/9999
35103942 | BR-09-03-W (E) CONNIE CIR PARB | 08W | NV | Initiation | ECES_CA1/UNSE | 05/20/2019 | 05/20/2019 | 12/31/9999
35104252 | BR-05-03-W (E) CLARK PH II PARB | 08W | NV | Initiation | ECES_CA1/UNSE | 05/21/2019 | 05/21/2019 | 12/31/9999
35105646 | BR-03-05-W (E) DEAN RD, PARB | 08W | NV | Construction | ECES_CA2/CONS | 07/16/2020 | 05/23/2019 | 03/13/2020 | 06/02/2020 | 06/02/2020 | 06/02/2020 | 06/02/2020 | 06/03/2020 | 06/22/2020 | 06/22/2020 | 07/16/2020 | 07/16/2020 | 12/31/9999
35105647 | BR-03-09-W (E) MERRILL RD PARB | 08W | NV | Documentation | ECES_CA2/DOCC | 12/19/2020 | 05/23/2019 | 07/12/2019 | 08/28/2019 | 08/28/2019 | 08/28/2019 | 08/28/2019 | 08/29/2019 | 09/26/2019 | 09/26/2019 | 11/11/2019 | 11/11/2019 | 12/19/2020 | 12/19/2020 | 12/31/9999 |  |  |  |  | 12/19/2020 | 12/19/2020
35105649 | BR-14-02-W (E) DRENDEL PARB | 08W | NV | Post-Doc | ECES_CA2/FICL | 12/29/2020 | 05/23/2019 | 07/29/2019 | 07/29/2019 | 10/22/2019 | 10/22/2019 | 10/22/2019 | 10/23/2019 | 10/24/2019 | 02/07/2020 | 02/21/2020 | 02/21/2020 | 10/28/2020 | 10/28/2020 | 12/15/2020 |  |  | 12/15/2020 | 12/29/2020 | 12/29/2020 | 12/31/9999
35105650 | BR-08-06-W (E) FICKETT LN PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 05/23/2019 | 05/23/2019 | 12/31/9999
35105653 | BR-14-01-W (E) SALIDA WAY, PARB | 08W | NV | Pending | ECES_CA2/PEND | 11/17/2020 | 05/23/2019 | 11/16/2020 | 11/16/2020 | 11/16/2020 | 11/16/2020 | 11/17/2020 | 11/17/2020 | 12/31/9999
35105656 | *CANC*BR-04-02-W (E) CASTLE DR PARB | 08W | NV | Completion | ECES_CA2/CLSD | 01/07/2021 | 05/23/2019 | 12/11/2020 | [10 empty] | 12/14/2020 | 12/14/2020 | [6 empty] | 01/07/2021 | 12/31/9999 | 12/28/2020 | 01/07/2021
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 | 08W | NV | Post-Doc | ECES_CA2/FICL | 10/14/2020 | 05/24/2019 | 06/18/2019 | 06/18/2019 | 08/26/2019 | 08/26/2019 | 08/26/2019 | 08/27/2019 | 10/07/2019 | 10/07/2019 | 10/22/2019 | 10/22/2019 | 05/20/2020 | 05/20/2020 | 09/01/2020 |  |  | 09/01/2020 | 10/14/2020 | 10/14/2020 | 12/31/9999
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | 08W | NV | Post-Doc | ECES_CA2/FICL | 09/08/2020 | 05/28/2019 | 06/18/2019 | 06/18/2019 | 08/27/2019 | 08/27/2019 | 08/27/2019 | 10/17/2019 | 10/22/2019 | 10/22/2019 | 10/30/2019 | 10/30/2019 | 02/19/2020 | 02/19/2020 | 08/31/2020 |  |  | 08/31/2020 | 09/08/2020 | 09/08/2020 | 12/31/9999
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | 08W | NV | Documentation | ECES_CA2/DOCC | 06/03/2020 | 05/28/2019 | 06/18/2019 | 09/10/2019 | 09/12/2019 | 09/12/2019 | 09/12/2019 | 10/18/2019 | 10/22/2019 | 10/22/2019 | 10/30/2019 | 10/30/2019 | 06/03/2020 | 06/03/2020 | 12/31/9999
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | 08W | NV | Post-Doc | ECES_CA2/FICL | 01/19/2021 | 05/29/2019 | 06/18/2019 | 06/18/2019 | 10/28/2019 | 10/28/2019 | 11/01/2019 | 11/04/2019 | 11/07/2019 | 11/07/2019 | 02/12/2020 | 02/12/2020 | 04/17/2020 | 04/17/2020 | 01/11/2021 |  |  | 01/11/2021 | 01/19/2021 | 01/19/2021 | 12/31/9999
35107689 | OCGC CWSP - PINE GROVE 1102 - LR1222 - | 08W | ST | Post-Doc | ECES_CA2/FICL | 11/05/2020 | 05/30/2019 | 08/05/2019 | 08/05/2019 | 11/14/2019 | 11/14/2019 | 11/15/2019 | 01/29/2020 | 01/30/2020 | 01/30/2020 | 02/15/2020 | 02/15/2020 | 05/15/2020 | 10/26/2020 | 11/05/2020 |  |  | 05/19/2020 | 06/05/2020 | 11/05/2020 | 12/31/9999
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | SI | Documentation | ECES_CA2/DOCC | 03/09/2020 | 06/03/2019 | 06/18/2019 | 10/04/2019 | 10/09/2019 | 10/09/2019 | 10/09/2019 | 10/30/2019 | 12/07/2019 | 12/07/2019 | 03/09/2020 |  |  | 03/09/2020 | 12/31/9999
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | SI | Design | ECES_CA2/ESTS | 06/18/2019 | 06/03/2019 | 06/18/2019 | 06/18/2019 | 12/31/9999
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | SI | Documentation | ECES_CA2/DOCC | 12/26/2019 | 06/03/2019 | 06/18/2019 | 06/18/2019 | 08/23/2019 | 08/23/2019 | 08/23/2019 | 08/23/2019 | 09/16/2019 | 09/16/2019 | 12/26/2019 |  |  | 12/26/2019 | 12/31/9999
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | SI | Documentation | ECES_CA2/DOCC | 12/26/2019 | 06/03/2019 | 06/18/2019 | 09/03/2019 | 12/31/9999 | 09/03/2019 | 09/03/2019 | 09/12/2019 | 09/28/2019 | 09/28/2019 | 12/26/2019 |  |  | 12/26/2019 | 12/31/9999
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | SI | Documentation | ECES_CA2/DOCC | 05/04/2020 | 06/03/2019 | 06/18/2019 | 11/08/2019 | 11/08/2019 | 11/08/2019 | 11/12/2019 | 11/13/2019 | 12/04/2019 | 12/04/2019 | 03/11/2020 | 03/11/2020 | 05/04/2020 | 05/04/2020 | 12/31/9999
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | SI | Design | ECES_CA2/ADER | 10/14/2020 | 06/03/2019 | 06/18/2019 | 06/18/2019 | 10/14/2020 | 10/14/2020 | 12/31/9999
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | SI | Documentation | ECES_CA2/DOCC | 04/02/2020 | 06/03/2019 | 06/18/2019 | 06/18/2019 | 10/14/2019 | 10/14/2019 | 10/14/2019 | 01/08/2020 | 01/21/2020 | 01/21/2020 | 04/02/2020 |  |  | 04/02/2020 | 12/31/9999
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | SI | Documentation | ECES_CA2/DOCC | 05/29/2020 | 06/03/2019 | 06/18/2019 | 12/30/2019 | 12/31/2019 | 12/31/2019 | 01/03/2020 | 01/25/2020 | 01/30/2020 | 01/30/2020 | 04/30/2020 | 04/30/2020 | 05/29/2020 | 05/29/2020 | 12/31/9999
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | SI | Documentation | ECES_CA2/DOCC | 04/30/2020 | 06/03/2019 | 06/18/2019 | 09/17/2019 | 09/17/2019 | 09/17/2019 | 09/18/2019 | 09/30/2019 | 09/30/2019 | 09/30/2019 | 04/30/2020 |  |  | 04/30/2020 | 12/31/9999
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | SI | Documentation | ECES_CA2/DOCC | 03/09/2020 | 06/03/2019 | 06/18/2019 | 09/18/2019 | 09/18/2019 | 09/18/2019 | 09/18/2019 | 09/19/2019 | 10/03/2019 | 10/03/2019 | 03/09/2020 |  |  | 03/09/2020 | 12/31/9999
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | SI | Documentation | ECES_CA2/DOCC | 04/30/2020 | 06/03/2019 | 06/18/2019 | 09/04/2019 | 09/05/2019 | 09/05/2019 | 09/05/2019 | 10/07/2019 | 10/08/2019 | 10/08/2019 | 04/30/2020 | 04/30/2020 | 04/30/2020 | 04/30/2020 | 12/31/9999
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | SI | Documentation | ECES_CA2/DOCC | 02/11/2020 | 06/03/2019 | 06/18/2019 | 09/24/2019 | 09/24/2019 | 09/24/2019 | 09/24/2019 | 09/25/2019 | 09/28/2019 | 09/28/2019 | 11/01/2019 | 11/01/2019 | 02/11/2020 | 02/11/2020 | 12/31/9999
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | SI | Documentation | ECES_CA2/DOCC | 04/20/2020 | 06/03/2019 | 06/18/2019 | 09/24/2019 | 09/25/2019 | 09/25/2019 | 09/25/2019 | 03/23/2020 | 03/23/2020 | 03/23/2020 | 04/20/2020 |  |  | 04/20/2020 | 12/31/9999
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | SI | Documentation | ECES_CA2/DOCC | 04/13/2020 | 06/03/2019 | 06/18/2019 | 01/15/2020 | 01/17/2020 | 01/17/2020 | 01/17/2020 | 01/17/2020 | 02/04/2020 | 02/04/2020 | 02/05/2020 | 02/05/2020 | 04/13/2020 | 04/13/2020 | 12/31/9999
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | SI | Documentation | ECES_CA2/DOCC | 03/09/2020 | 06/03/2019 | 06/18/2019 | 11/06/2019 | 11/06/2019 | 11/06/2019 | 11/06/2019 | 12/20/2019 | 03/09/2020 | 12/19/2019 | 12/20/2019 |  |  | 03/09/2020 | 12/31/9999
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | SI | Documentation | ECES_CA2/DOCC | 04/02/2020 | 06/03/2019 | 06/18/2019 | 06/18/2019 | 08/23/2019 | 08/23/2019 | 08/26/2019 | 08/26/2019 | 10/15/2019 | 10/15/2019 | 04/02/2020 |  |  | 04/02/2020 | 12/31/9999
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | 08W | NV | Post-Doc | ECES_CA2/FICL | 01/15/2021 | 06/04/2019 | 06/18/2019 | 11/08/2019 | 11/08/2019 | 11/08/2019 | 11/08/2019 | 11/08/2019 | 11/08/2019 | 11/08/2019 | 12/10/2019 | 12/10/2019 | 03/18/2020 | 03/18/2020 | 12/07/2020 |  |  | 12/07/2020 | 01/15/2021 | 01/15/2021 | 12/31/9999
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 | 08W | NV | Post-Doc | ECES_CA2/FICL | 12/24/2020 | 06/04/2019 | 06/18/2019 | 06/18/2019 | 10/01/2019 | 10/01/2019 | 10/02/2019 | 10/02/2019 | 11/06/2019 | 11/06/2019 | 02/17/2020 | 02/17/2020 | 06/03/2020 | 06/03/2020 | 12/07/2020 |  |  | 12/07/2020 | 12/24/2020 | 12/24/2020 | 12/31/9999
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | 08W | NV | Documentation | ECES_CA2/DOCC | 02/07/2020 | 06/04/2019 | 06/18/2019 | 09/18/2019 | 09/19/2019 | 09/19/2019 | 09/20/2019 | 09/20/2019 | 09/20/2019 | 09/20/2019 | 11/14/2019 | 11/14/2019 | 02/07/2020 | 02/07/2020 | 12/31/9999
35109832 | BR-03-01-W (E) GATE LN PARB | 08W | NV | Post-Doc | ECES_CA2/FICL | 11/24/2020 | 06/03/2019 | 07/02/2019 | 08/19/2019 | 08/19/2019 | 08/19/2019 | 08/19/2019 | 11/26/2019 | 11/26/2019 | 11/26/2019 | 03/31/2020 | 03/31/2020 | 04/13/2020 | 04/13/2020 | 11/05/2020 |  |  | 11/05/2020 | 11/24/2020 | 11/24/2020 | 12/31/9999
35110369 | BR-03-03-W (E) GINNY_SUNRISE PARB | 08W | NV | Documentation | ECES_CA2/MAPP | 06/17/2020 | 06/05/2019 | 08/13/2019 | 10/09/2019 | 10/09/2019 | 10/09/2019 | 10/09/2019 | 10/10/2019 | 10/14/2019 | 10/14/2019 | 12/16/2019 | 12/16/2019 | 06/16/2020 | 06/16/2020 | 06/17/2020 |  |  | 06/17/2020 | 12/31/9999
35110372 | BR-03-04-W (E) SWEETBRIAR PARB | 08W | NV | Documentation | ECES_CA2/DOCC | 07/28/2020 | 06/05/2019 | 07/30/2019 | 10/23/2019 | 10/23/2019 | 10/23/2019 | 10/23/2019 | 10/29/2019 | 11/30/2019 | 11/30/2019 | 12/16/2019 | 12/16/2019 | 07/28/2020 | 07/28/2020 | 12/31/9999
35110374 | *CANC*BR-03-06-W (E) LUNAR LN PARB | 08W | NV | Other | ECES_CA2/CNCL | 02/03/2021 | 06/05/2019 | 12/30/2020 | [20 empty] | 02/03/2021 | 12/31/9999
35110377 | BR-03-10-W (E) SHAY LN PARB | 08W | NV | Documentation | ECES_CA2/MAPP | 08/06/2020 | 06/05/2019 | 08/12/2019 | 09/19/2019 | 09/23/2019 | 09/23/2019 | 09/23/2019 | 09/23/2019 | 09/23/2019 | 09/23/2019 | 11/04/2019 | 11/04/2019 | 08/04/2020 | 08/04/2020 | 08/06/2020 |  |  | 08/06/2020 | 12/31/9999
35110379 | BR-03-11-W (E) WHITAKER RD PARB | 08W | NV | Post-Doc | ECES_CA2/FICL | 12/11/2020 | 06/05/2019 | 09/18/2019 | 10/31/2019 | 10/31/2019 | 10/31/2019 | 10/31/2019 | 10/31/2019 | 10/31/2019 | 10/31/2019 | 12/09/2019 | 12/09/2019 | 08/13/2020 | 08/13/2020 | 11/30/2020 |  |  | 11/30/2020 | 12/11/2020 | 12/11/2020 | 12/31/9999
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | 08W | NV | Documentation | ECES_CA2/MAPP | 02/04/2021 | 06/04/2019 | 06/18/2019 | 09/12/2019 | 09/12/2019 | 09/12/2019 | 09/12/2019 | 09/13/2019 | 10/10/2019 | 10/10/2019 | 01/27/2020 | 01/27/2020 | 05/13/2020 | 05/13/2020 | 02/04/2021 |  |  | 02/04/2021 | 12/31/9999
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 | 08W | NV | Documentation | ECES_CA2/MAPP | 01/11/2021 | 06/04/2019 | 06/18/2019 | 09/25/2019 | 10/01/2019 | 10/01/2019 | 10/02/2019 | 10/03/2019 | 10/25/2019 | 10/25/2019 | 04/14/2020 | 04/14/2020 | 05/06/2020 | 05/06/2020 | 01/11/2021 |  |  | 01/11/2021 | 12/31/9999
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | 08W | NV | Post-Doc | ECES_CA2/FICL | 09/08/2020 | 06/04/2019 | 06/18/2019 | 09/09/2019 | 09/12/2019 | 09/12/2019 | 09/12/2019 | 10/02/2019 | 10/14/2019 | 10/14/2019 | 10/21/2019 | 10/21/2019 | 12/26/2019 | 12/26/2019 | 08/31/2020 |  |  | 08/31/2020 | 09/08/2020 | 09/08/2020 | 12/31/9999
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 | 08W | NV | Post-Doc | ECES_CA2/FICL | 11/30/2020 | 06/04/2019 | 06/18/2019 | 09/09/2019 | 09/10/2019 | 09/10/2019 | 09/10/2019 | 09/10/2019 | 10/01/2019 | 10/01/2019 | 10/14/2019 | 10/14/2019 | 02/07/2020 | 02/07/2020 | 11/10/2020 |  |  | 11/10/2020 | 11/30/2020 | 11/30/2020 | 12/31/9999
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 | 08W | NV | Post-Doc | ECES_CA2/FICL | 09/02/2020 | 06/04/2019 | 06/18/2019 | 08/29/2019 | 08/29/2019 | 08/29/2019 | 08/29/2019 | 09/12/2019 | 09/13/2019 | 09/13/2019 | 09/30/2019 | 09/30/2019 | 02/19/2020 | 02/19/2020 | 08/24/2020 |  |  | 08/24/2020 | 09/02/2020 | 09/02/2020 | 12/31/9999
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | 08W | NV | Documentation | ECES_CA2/DOCC | 12/26/2019 | 06/04/2019 | 06/18/2019 | 08/22/2019 | 08/22/2019 | 08/22/2019 | 08/22/2019 | 08/27/2019 | 09/09/2019 | 09/09/2019 | 09/30/2019 | 09/30/2019 | 12/26/2019 | 12/26/2019 | 12/31/9999
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 | 08W | NV | Post-Doc | ECES_CA2/FICL | 01/04/2021 | 06/04/2019 | 06/18/2019 | 06/18/2019 | 08/26/2019 | 08/26/2019 | 08/26/2019 | 08/27/2019 | 10/08/2019 | 10/08/2019 | 10/21/2019 | 10/21/2019 | 02/19/2020 | 02/19/2020 | 12/14/2020 |  |  | 12/14/2020 | 01/04/2021 | 01/04/2021 | 12/31/9999
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | 08W | NV | Post-Doc | ECES_CA2/FICL | 12/17/2020 | 06/04/2019 | 06/18/2019 | 06/18/2019 | 09/05/2019 | 09/05/2019 | 09/18/2019 | 10/30/2019 | 10/31/2019 | 10/31/2019 | 01/24/2020 | 01/24/2020 | 04/17/2020 | 04/17/2020 | 12/07/2020 |  |  | 12/07/2020 | 12/17/2020 | 12/17/2020 | 12/31/9999
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 | 08W | NV | Documentation | ECES_CA2/MAPP | 02/16/2021 | 06/04/2019 | 06/18/2019 | 09/11/2019 | 09/13/2019 | 09/13/2019 | 09/13/2019 | 09/21/2020 | 09/21/2020 | 09/21/2020 | 09/22/2020 | 02/17/2020 | 06/03/2020 | 09/22/2020 | 02/16/2021 |  |  | 02/16/2021 | 12/31/9999
35110556 | BR-04-12-W (E) SUBSTATION/PATH PARB | 08W | NV | Design | ECES_CA2/ESTS | 06/06/2019 | 06/06/2019 | 06/06/2019 | 06/06/2019 | 12/31/9999
35111486 | BR-04-03-W (E) EDWARDS & RIPLEY PARB | 08W | NV | Post-Doc | ECES_CA2/FICL | 08/05/2020 | 06/13/2019 | 06/13/2019 | 08/16/2019 | 08/16/2019 | 08/16/2019 | 08/16/2019 | 01/10/2020 | 01/14/2020 | 01/14/2020 | 07/27/2020 |  |  | 07/27/2020 | 07/28/2020 |  |  | 07/28/2020 | 08/05/2020 | 08/05/2020 | 12/31/9999
35111500 | CWSP-RECON UPPER LAKE 01 HUNTERS PT RD | 08W | HB | Completion | ECES_CA1/CLSD | 12/19/2020 | 06/13/2019 | 06/13/2019 | 06/13/2019 | 07/01/2019 | 07/01/2019 | 07/01/2019 | 09/05/2019 | 10/03/2019 | 10/03/2019 | 12/17/2019 | 08/28/2019 | 09/05/2019 | 12/17/2019 | 01/21/2020 |  |  | 01/21/2020 | 01/28/2020 | 01/28/2020 | 12/15/2020 | 12/19/2020 | 12/31/9999
35112076 | OCGC FULTON 1107-OH TO UG MARK W SPG | 08W | SO | Documentation | ECES_CA2/MAPP | 04/27/2020 | 06/19/2019 | 06/19/2019 | 09/29/2019 | 09/30/2019 | 09/30/2019 | 09/30/2019 | 11/19/2019 | 12/12/2019 | 12/12/2019 | 12/12/2019 | 12/12/2019 | 04/16/2020 | 04/16/2020 | 04/27/2020 |  |  | 04/27/2020 | 12/31/9999
35112089 | BR-01-05-W (E) MEYERS PARB | 08W | NV | Documentation | ECES_CA2/DOCC | 08/04/2020 | 06/19/2019 | 07/24/2019 | 10/03/2019 | 10/03/2019 | 10/03/2019 | 10/09/2019 | 10/09/2019 | 10/15/2019 | 10/15/2019 | 12/02/2019 | 12/02/2019 | 08/04/2020 | 08/04/2020 | 12/31/9999
35112090 | BR-01-07-W (E) BILLE_REGIS PARB | 08W | NV | Documentation | ECES_CA2/DOCC | 07/23/2020 | 06/19/2019 | 07/24/2019 | 09/18/2019 | 09/18/2019 | 09/18/2019 | 09/18/2019 | 11/27/2019 | 12/03/2019 | 12/03/2019 | 12/16/2019 | 12/16/2019 | 07/23/2020 | 07/23/2020 | 12/31/9999
35112091 | BR-01-09-W (E) FERN PARB | 08W | NV | Post-Doc | ECES_CA2/FICL | 08/19/2020 | 06/19/2019 | 08/12/2019 | 08/12/2019 | 10/09/2019 | 10/09/2019 | 10/09/2019 | 10/10/2019 | 10/10/2019 | 10/10/2019 | 11/07/2019 | 11/07/2019 | 08/04/2020 | 08/04/2020 | 08/06/2020 |  |  | 08/06/2020 | 08/19/2020 | 08/19/2020 | 12/31/9999
35112092 | BR-14-06 (E) BLUE DANUBE PARB | 08W | NV | Post-Doc | ECES_CA2/FICL | 08/21/2020 | 06/19/2019 | 08/06/2019 | 08/06/2019 | 10/01/2019 | 10/01/2019 | 10/01/2019 | 11/26/2019 | 12/03/2019 | 12/03/2019 | 12/16/2019 | 12/16/2019 | 08/11/2020 | 08/11/2020 | 08/12/2020 |  |  | 08/12/2020 | 08/21/2020 | 08/21/2020 | 12/31/9999
35112126 | BR-01-03-W (E) PARAGALIA PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 06/18/2019 | 06/18/2019 | 12/31/9999
35112128 | BR-01-04-W (E) W. WAGSTAFF PARB | 08W | NV | Documentation | ECES_CA2/DOCC | 10/28/2020 | 06/18/2019 | 10/03/2019 | 10/04/2019 | 10/07/2019 | 10/07/2019 | 10/07/2019 | 10/08/2019 | 11/27/2019 | 11/27/2019 | 08/24/2020 | 08/24/2020 | 10/28/2020 | 10/28/2020 | 12/31/9999
35112157 | *CANC*CWSP - MIWUK 1701 - LR 10600 | 08W | YO | Initiation | ECES_CA2/UNSE | 06/19/2019 | 06/19/2019 | 12/31/9999
35112158 | *CANC*CWSP - MIWUK 1701 - LR 10600 | 08W | YO | Initiation | ECES_CA2/UNSE | 06/19/2019 | 06/19/2019 | 12/31/9999
35112159 | *CANC*CWSP - MIWUK 1701 - LR 10600 | 08W | YO | Initiation | ECES_CA2/UNSE | 06/19/2019 | 06/19/2019 | 12/31/9999
35112220 | BR-04-06-W (E) VALLEY RIDGE PARB | 08W | NV | Construction | ECES_CA2/CONS | 07/16/2020 | 06/19/2019 | 07/08/2019 | 12/06/2019 | 12/10/2019 | 12/10/2019 | 12/11/2019 | 12/13/2019 | 05/06/2020 | 05/06/2020 | 07/16/2020 | 07/16/2020 | 12/31/9999
35112249 | BR-04-07-W (E) CRESTMOOR PARB | 08W | NV | Documentation | ECES_CA2/DOCC | 08/25/2020 | 06/19/2019 | 07/16/2019 | 09/03/2019 | 10/03/2019 | 10/03/2019 | 12/31/9999 | 10/09/2019 | 11/27/2019 | 11/27/2019 | 12/09/2019 | 12/09/2019 | 08/25/2020 | 08/25/2020 | 12/31/9999
35112340 | *CANC*CWSP - MIWUK 1701 - LR 10600 | 08W | YO | Initiation | ECES_CA2/UNSE | 06/19/2019 | 06/19/2019 | 12/31/9999
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | SI | Construction | ECES_CA2/CONS | 03/31/2020 | 06/20/2019 | 07/22/2019 | 10/22/2019 | 10/22/2019 | 10/22/2019 | 10/22/2019 | 10/23/2019 | 01/03/2020 | 01/03/2020 | 03/31/2020 | 03/31/2020 | 12/31/9999
35112426 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.3 | 08W | SI | Post-Doc | ECES_CA2/FICL | 02/02/2021 | 06/20/2019 | 07/01/2019 | 07/01/2019 | 09/09/2019 | 09/09/2019 | 09/09/2019 | 09/09/2019 | 11/07/2019 | 11/07/2019 | 12/26/2019 |  |  | 12/26/2019 | 12/02/2020 |  |  | 12/02/2020 | 02/02/2021 | 02/02/2021 | 12/31/9999
35112427 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.4 | 08W | SI | Completion | ECES_CA2/CLSD | 12/12/2020 | 06/20/2019 | 07/18/2019 | 11/12/2019 | 11/13/2019 | 11/13/2019 | 11/13/2019 | 11/13/2019 | 11/25/2019 | 11/25/2019 | 12/23/2019 | 12/23/2019 | 02/25/2020 | 02/25/2020 | 11/06/2020 |  |  | 11/06/2020 | 12/04/2020 | 12/04/2020 | 12/09/2020 | 12/12/2020 | 12/31/9999
35112428 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.5 | 08W | SI | Completion | ECES_CA2/CLSD | 01/30/2021 | 06/20/2019 | 07/09/2019 | 09/26/2019 | 09/26/2019 | 09/26/2019 | 09/26/2019 | 01/06/2020 | 01/13/2020 | 01/13/2020 | 02/27/2020 |  |  | 02/27/2020 | 11/16/2020 |  |  | 11/16/2020 | 12/08/2020 | 12/08/2020 | 01/28/2021 | 01/30/2021 | 12/31/9999
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | SI | Construction | ECES_CA2/CONS | 08/21/2020 | 06/20/2019 | 07/26/2019 | 07/26/2019 | 10/15/2019 | 10/15/2019 | 10/15/2019 | 01/07/2020 | 08/21/2020 | 12/26/2019 | 01/07/2020 | 08/21/2020 | 12/31/9999
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | 08W | SI | Post-Doc | ECES_CA2/FICL | 12/11/2020 | 06/20/2019 | 07/16/2019 | 07/21/2020 | 07/24/2020 | 07/24/2020 | 07/27/2020 | 07/27/2020 | 07/29/2020 | 03/03/2020 | 06/04/2020 | 07/29/2020 | 10/06/2020 | 10/06/2020 | 11/18/2020 |  |  | 11/18/2020 | 12/11/2020 | 12/11/2020 | 12/31/9999
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | 08W | SI | Documentation | ECES_CA2/DOCC | 11/23/2020 | 06/20/2019 | 07/10/2019 | 07/13/2020 | 07/14/2020 | 07/14/2020 | 07/15/2020 | 07/21/2020 | 07/31/2020 | 09/11/2020 | 10/14/2020 | 10/14/2020 | 11/23/2020 | 11/23/2020 | 12/31/9999
35112433 | CWSP - EL DORADO 2102 - LR19562 - PH 1.3 | 08W | SI | Documentation | ECES_CA2/MAPP | 01/27/2021 | 06/20/2019 | 07/30/2019 | 07/30/2019 | 10/11/2019 | 10/11/2019 | 10/11/2019 | 10/11/2019 | 12/10/2019 | 12/10/2019 | 03/09/2020 | 03/09/2020 | 06/30/2020 | 06/30/2020 | 01/27/2021 |  |  | 01/27/2021 | 12/31/9999
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | 08W | SI | Documentation | ECES_CA2/DOCC | 10/06/2020 | 06/20/2019 | 09/10/2019 | 07/28/2020 | 07/28/2020 | 07/28/2020 | 07/28/2020 | 07/28/2020 | 07/29/2020 | 07/21/2020 | 07/21/2020 | 07/29/2020 | 10/06/2020 | 10/06/2020 | 12/31/9999
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | 08W | SI | Post-Doc | ECES_CA2/FICL | 01/11/2021 | 06/20/2019 | 07/09/2019 | 07/21/2020 | 07/24/2020 | 07/24/2020 | 07/24/2020 | 07/24/2020 | 07/29/2020 | 12/10/2019 | 03/09/2020 | 07/29/2020 | 09/08/2020 | 09/08/2020 | 12/14/2020 |  |  | 12/14/2020 | 01/11/2021 | 01/11/2021 | 12/31/9999
35112436 | CWSP - EL DORADO 2102 - LR19562 - PH 1.6 | 08W | SI | Documentation | ECES_CA2/MAPP | 12/29/2020 | 06/20/2019 | 06/27/2019 | 06/27/2019 | 09/27/2019 | 09/27/2019 | 09/27/2019 | 09/28/2019 | 11/26/2019 | 11/26/2019 | 03/23/2020 | 03/23/2020 | 06/30/2020 | 06/30/2020 | 12/29/2020 |  |  | 12/29/2020 | 12/31/9999
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | 08W | SI | Post-Doc | ECES_CA2/FICL | 01/04/2021 | 06/20/2019 | 07/10/2019 | 10/24/2019 | 10/24/2019 | 10/24/2019 | 10/24/2019 | 10/24/2019 | 12/10/2019 | 12/10/2019 | 03/23/2020 | 03/23/2020 | 08/04/2020 | 08/04/2020 | 11/18/2020 |  |  | 11/18/2020 | 01/04/2021 | 01/04/2021 | 12/31/9999
35112876 | BR-04-02-W (E) CASTLE_CLIFF DR PARB | 08W | NV | Post-Doc | ECES_CA2/FICL | 12/14/2020 | 06/25/2019 | 06/25/2019 | 07/18/2019 | 07/18/2019 | 07/18/2019 | 07/18/2019 | 07/22/2019 | 11/25/2019 | 11/25/2019 | 01/14/2020 | 01/14/2020 | 04/28/2020 | 12/14/2020 | 12/14/2020 |  |  | 05/04/2020 | 06/01/2020 | 12/14/2020 | 12/14/2020
35112968 | WOODSIDE 1101 RECOND FUSE 1097 ZONE | 08W | PN | Initiation | ECES_CA2/UNSE | 06/26/2019 | 06/26/2019 | 12/31/9999
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | 08W | ST | Design | ECES_CA2/ESTS | 10/03/2020 | 06/26/2019 | 08/09/2019 | 10/03/2020 | 12/31/9999 | 10/02/2020 | 10/03/2020
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | 08W | ST | Pending | ECES_CA2/PEND | 12/04/2020 | 06/26/2019 | 08/09/2019 | 09/11/2020 | 09/14/2020 | 09/14/2020 | 09/15/2020 | 12/04/2020 | 12/31/9999 | 12/02/2020 | 12/04/2020
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | 08W | ST | Design | ECES_CA2/ADER | 08/28/2020 | 06/26/2019 | 08/09/2019 | 08/09/2019 | 08/28/2020 | 08/28/2020 | 12/31/9999
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | 08W | ST | Design | ECES_CA2/ADER | 11/06/2020 | 06/26/2019 | 08/09/2019 | 08/09/2019 | 11/06/2020 | 11/06/2020 | 12/31/9999
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | 08W | ST | Design | ECES_CA2/ESTS | 11/10/2020 | 06/26/2019 | 08/09/2019 | 11/10/2020 | 12/31/9999 | 10/15/2020 | 11/10/2020
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | 08W | ST | Pending | ECES_CA2/PEND | 10/29/2020 | 06/26/2019 | 08/09/2019 | 10/29/2020 | 10/29/2020 | 10/29/2020 | 10/29/2020 | 10/29/2020 | 12/31/9999
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | 08W | ST | Pending | ECES_CA2/PEND | 10/08/2020 | 06/26/2019 | 08/09/2019 | 08/09/2019 | 07/24/2020 | 07/24/2020 | 07/24/2020 | 10/08/2020 | 10/08/2020 | 10/08/2020 | 10/08/2020
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | 08W | ST | Pending | ECES_CA2/PEND | 09/17/2020 | 06/26/2019 | 08/09/2019 | 08/18/2020 | 08/19/2020 | 08/19/2020 | 08/19/2020 | 09/17/2020 | 12/31/9999 | 09/16/2020 | 09/17/2020
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | 08W | ST | Pending | ECES_CA2/PEND | 10/12/2020 | 06/26/2019 | 08/09/2019 | 09/14/2020 | 10/08/2020 | 10/08/2020 | 10/08/2020 | 10/12/2020 | 10/12/2020 | 10/12/2020 | 10/12/2020
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | 08W | ST | Construction | ECES_CA2/CONS | 12/15/2020 | 06/26/2019 | 08/09/2019 | 12/04/2020 | 12/07/2020 | 12/07/2020 | 12/07/2020 | 12/08/2020 | 12/15/2020 | 07/27/2020 | 08/17/2020 | 12/15/2020 | 12/31/9999
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | 08W | ST | Construction | ECES_CA2/CONS | 08/17/2020 | 06/26/2019 | 08/09/2019 | 03/18/2020 | 03/19/2020 | 03/19/2020 | 03/20/2020 | 03/20/2020 | 05/13/2020 | 07/02/2020 | 08/17/2020 | 08/17/2020 | 12/31/9999
35113103 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.3 | 08W | DA | Completion | ECES_CA2/CLSD | 12/19/2020 | 06/26/2019 | 06/27/2019 | 06/27/2019 | 07/26/2019 | 07/26/2019 | 07/26/2019 | 07/26/2019 | 09/16/2019 | 09/16/2019 | 09/30/2019 | 09/30/2019 | 11/19/2019 | 12/24/2019 | 01/03/2020 |  |  | 11/20/2019 | 12/18/2019 | 01/03/2020 | 12/17/2020 | 12/19/2020 | 12/31/9999
35113104 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.2 | 08W | DA | Completion | ECES_CA2/CLSD | 10/31/2020 | 06/26/2019 | 06/27/2019 | 06/27/2019 | 08/16/2019 | 08/16/2019 | 08/16/2019 | 08/19/2019 | 09/23/2019 | 09/23/2019 | 10/14/2019 | 10/14/2019 | 01/06/2020 | 01/06/2020 | 01/07/2020 |  |  | 01/07/2020 | 07/09/2020 | 07/09/2020 | 10/29/2020 | 10/31/2020 | 12/31/9999
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | 08W | DA | Post-Doc | ECES_CA2/FICL | 12/23/2020 | 06/26/2019 | 06/27/2019 | 06/27/2019 | 09/12/2019 | 09/12/2019 | 09/12/2019 | 11/18/2019 | 12/06/2019 | 12/06/2019 | 12/23/2019 | 12/23/2019 | 11/19/2020 | 11/19/2020 | 12/03/2020 |  |  | 12/03/2020 | 12/23/2020 | 12/23/2020 | 12/31/9999
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | 08W | DA | Initiation | ECES_CA2/UNSE | 09/24/2019 | 09/24/2019 | 12/31/9999 | 09/19/2019 | 09/24/2019
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | 08W | DA | Design | ECES_CA2/ESTS | 10/14/2019 | 06/26/2019 | 10/14/2019 | 10/14/2019 | 12/31/9999
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | 08W | DA | Construction | ECES_CA2/CONS | 07/22/2020 | 06/26/2019 | 08/01/2019 | 03/04/2020 | 03/05/2020 | 03/05/2020 | 03/05/2020 | 03/10/2020 | 03/10/2020 | 03/10/2020 | 07/22/2020 | 07/22/2020 | 12/31/9999
35113109 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.2 | 08W | DA | Completion | ECES_CA2/CLSD | 10/31/2020 | 06/26/2019 | 06/27/2019 | 06/27/2019 | 09/12/2019 | 09/12/2019 | 09/12/2019 | 11/07/2019 | 11/07/2019 | 11/07/2019 | 12/19/2019 |  |  | 12/19/2019 | 12/26/2019 |  |  | 12/26/2019 | 02/28/2020 | 02/28/2020 | 10/28/2020 | 10/31/2020 | 12/31/9999
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | 08W | DA | Initiation | ECES_CA2/UNSE | 06/26/2019 | 06/26/2019 | 12/31/9999
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | 08W | DA | Initiation | ECES_CA2/UNSE | 06/26/2019 | 06/26/2019 | 12/31/9999
35113871 | SILVERADO 2104 RECONDUCTOR - PHASE 2 | 08W | NB | Completion | ECES_CA2/CLSD | 01/02/2021 | 07/02/2019 | 07/11/2019 | 07/11/2019 | 08/01/2019 | 08/01/2019 | 08/01/2019 | 08/27/2019 | 08/30/2019 | 08/30/2019 | 12/11/2019 | 12/11/2019 | 12/17/2019 | 12/17/2019 | 08/19/2020 |  |  | 08/19/2020 | 08/25/2020 | 08/25/2020 | 01/01/2021 | 01/02/2021 | 12/31/9999
35113945 | CWSP - BRUNSWICK 1102 - LR 1010 | 08W | SI | Initiation | ECES_CA2/UNSE | 07/03/2019 | 07/03/2019 | 12/31/9999
35113946 | CWSP - WYANDOTTE 1103 – LR 1974 | 08W | NV | Initiation | ECES_CA2/UNSE | 07/03/2019 | 07/03/2019 | 12/31/9999
35113947 | CWSP - LOS GATOS 1107 – LR 60114 | 08W | CC | Initiation | ECES_CA2/UNSE | 07/03/2019 | 07/03/2019 | 12/31/9999
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | 08W | CC | Pre-Construction | ECES_CA2/UNSC | 12/11/2020 | 07/03/2019 | 07/22/2019 | 07/31/2020 | 07/31/2020 | 07/31/2020 | 07/31/2020 | 12/11/2020 | 12/11/2020 | 12/11/2020 | 12/11/2020
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | 08W | CC | Pre-Construction | ECES_CA2/UNSC | 09/02/2020 | 07/03/2019 | 07/22/2019 | 08/17/2020 | 08/17/2020 | 08/17/2020 | 08/17/2020 | 09/02/2020 | 09/02/2020 | 09/02/2020 | 09/02/2020
35113952 | *CANC* BB1101-LR10296-PH1.4 | 08W | CC | Completion | ECES_CA2/CLSD | 11/03/2019 | 07/03/2019 | 10/16/2019 | [18 empty] | 11/03/2019 | 12/31/9999 | 10/16/2019 | 11/03/2019
35113953 | *CANC* BB1101-LR10296-PH1.5 | 08W | CC | Completion | ECES_CA2/CLSD | 11/03/2019 | 07/03/2019 | 10/16/2019 | [18 empty] | 11/03/2019 | 12/31/9999 | 10/16/2019 | 11/03/2019
35113954 | *CANC* BB1101-LR10296-PH1.6 | 08W | CC | Completion | ECES_CA2/CLSD | 11/03/2019 | 07/03/2019 | 10/16/2019 | [18 empty] | 11/03/2019 | 12/31/9999 | 10/16/2019 | 11/03/2019
35113955 | *CANC* B1101-LR10296-PH1.7 | 08W | CC | Completion | ECES_CA2/CLSD | 11/03/2019 | 07/03/2019 | 10/16/2019 | [18 empty] | 11/03/2019 | 12/31/9999 | 10/16/2019 | 11/03/2019
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | 08W | ST | Design | ECES_CA2/ESTS | 08/09/2019 | 07/03/2019 | 08/09/2019 | 08/09/2019 | 12/31/9999
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | 08W | ST | Design | ECES_CA2/ADER | 10/26/2020 | 07/03/2019 | 08/09/2019 | 08/09/2019 | 10/26/2020 | 10/26/2020 | 12/31/9999
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | 08W | ST | Pending | ECES_CA2/PEND | 10/28/2020 | 07/03/2019 | 08/09/2019 | 10/27/2020 | 10/27/2020 | 10/27/2020 | 10/28/2020 | 10/28/2020 | 12/31/9999
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | 08W | ST | Pending | ECES_CA2/PEND | 09/18/2020 | 07/03/2019 | 08/09/2019 | 09/17/2020 | 09/18/2020 | 09/18/2020 | 09/18/2020 | 09/18/2020 | 12/31/9999
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | 08W | ST | Pending | ECES_CA2/PEND | 09/15/2020 | 07/03/2019 | 08/09/2019 | 08/09/2019 | 09/03/2020 | 09/03/2020 | 09/14/2020 | 09/15/2020 | 09/15/2020
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | 08W | ST | Pending | ECES_CA2/PEND | 09/29/2020 | 07/03/2019 | 08/09/2019 | 09/28/2020 | 09/28/2020 | 09/28/2020 | 09/28/2020 | 09/29/2020 | 12/31/9999
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | 08W | ST | Design | ECES_CA2/ESTS | 08/09/2019 | 07/03/2019 | 08/09/2019 | 08/09/2019 | 12/31/9999
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | 08W | ST | Construction | ECES_CA2/CONS | 07/21/2020 | 07/03/2019 | 08/05/2019 | 07/15/2020 | 07/16/2020 | 07/16/2020 | 07/16/2020 | 07/16/2020 | 07/17/2020 | 07/17/2020 | 07/21/2020 | 07/21/2020 | 12/31/9999
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | 08W | ST | Construction | ECES_CA2/CONS | 08/11/2020 | 07/03/2019 | 08/05/2019 | 08/05/2019 | 06/17/2020 | 06/17/2020 | 06/17/2020 | 06/17/2020 | 07/07/2020 | 07/07/2020 | 08/11/2020 | 08/11/2020 | 12/31/9999
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | 08W | ST | Documentation | ECES_CA2/DOCC | 12/20/2020 | 07/03/2019 | 08/05/2019 | 04/08/2020 | 04/08/2020 | 04/08/2020 | 04/08/2020 | 04/08/2020 | 05/18/2020 | 05/18/2020 | 06/09/2020 | 06/09/2020 | 11/12/2020 | 12/20/2020 | 12/31/9999 |  |  | 11/16/2020 | 12/16/2020 | 12/16/2020 | 12/20/2020
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | 08W | ST | Documentation | ECES_CA2/DOCC | 10/25/2020 | 07/03/2019 | 08/05/2019 | 04/23/2020 | 04/23/2020 | 04/23/2020 | 04/24/2020 | 04/24/2020 | 05/13/2020 | 05/13/2020 | 06/09/2020 | 06/09/2020 | 08/25/2020 | 10/25/2020 | 12/31/9999 |  |  | 09/08/2020 | 10/13/2020 | 10/13/2020 | 10/25/2020
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | 08W | ST | Construction | ECES_CA2/CONS | 08/04/2020 | 07/03/2019 | 08/06/2019 | 08/06/2019 | 04/15/2020 | 04/15/2020 | 04/15/2020 | 06/08/2020 | 06/08/2020 | 06/08/2020 | 08/04/2020 | 08/04/2020 | 12/31/9999
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | 08W | ST | Pre-Construction | ECES_CA2/UNSC | 09/11/2020 | 07/03/2019 | 08/06/2019 | 08/06/2019 | 06/17/2020 | 06/17/2020 | 06/17/2020 | 09/10/2020 | 09/11/2020 | 09/11/2020 | 12/31/9999
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | 08W | ST | Pending | ECES_CA2/PEND | 11/17/2020 | 07/03/2019 | 08/12/2019 | 11/11/2020 | 11/11/2020 | 11/11/2020 | 11/17/2020 | 11/17/2020 | 12/31/9999
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | 08W | ST | Construction | ECES_CA2/CONS | 08/04/2020 | 07/03/2019 | 08/12/2019 | 05/30/2020 | 06/01/2020 | 06/01/2020 | 06/01/2020 | 06/25/2020 | 06/25/2020 | 06/25/2020 | 08/04/2020 | 08/04/2020 | 12/31/9999
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | 08W | ST | Construction | ECES_CA2/CONS | 07/17/2020 | 07/03/2019 | 08/12/2019 | 04/23/2020 | 04/23/2020 | 04/23/2020 | 04/24/2020 | 04/24/2020 | 06/08/2020 | 06/08/2020 | 07/17/2020 | 07/17/2020 | 12/31/9999
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | 08W | ST | Pre-Construction | ECES_CA2/UNSC | 07/17/2020 | 07/03/2019 | 08/12/2019 | 06/14/2020 | 06/15/2020 | 06/15/2020 | 06/15/2020 | 06/15/2020 | 07/17/2020 | 07/17/2020 | 12/31/9999
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | 08W | ST | Construction | ECES_CA2/CONS | 09/21/2020 | 07/03/2019 | 08/12/2019 | 05/18/2020 | 05/18/2020 | 05/18/2020 | 05/18/2020 | 05/19/2020 | 07/28/2020 | 07/28/2020 | 09/21/2020 | 09/21/2020 | 12/31/9999
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | 08W | ST | Pre-Construction | ECES_CA2/UNSC | 09/04/2020 | 07/03/2019 | 08/12/2019 | 06/11/2020 | 06/12/2020 | 06/12/2020 | 06/12/2020 | 09/04/2020 | 09/04/2020 | 09/04/2020 | 09/04/2020
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | 08W | ST | Design | ECES_CA2/ADER | 09/15/2020 | 07/03/2019 | 08/12/2019 | 08/12/2019 | 09/15/2020 | 09/15/2020 | 12/31/9999
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | 08W | CC | Construction | ECES_CA2/CONS | 01/19/2021 | 07/03/2019 | 07/09/2019 | 04/22/2020 | 05/15/2020 | 05/15/2020 | 05/18/2020 | 06/25/2020 | 07/08/2020 | 07/08/2020 | 08/04/2020 | 01/19/2021 | 12/31/9999 | 01/13/2021 | 01/19/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | 08W | CC | Post-Doc | ECES_CA2/FICL | 12/23/2020 | 07/03/2019 | 09/19/2019 | 04/28/2020 | 04/28/2020 | 04/28/2020 | 04/28/2020 | 04/28/2020 | 05/07/2020 | 05/07/2020 | 05/27/2020 | 05/27/2020 | 11/24/2020 | 11/24/2020 | 11/30/2020 |  |  | 11/30/2020 | 12/23/2020 | 12/23/2020 | 12/31/9999
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | 08W | CC | Construction | ECES_CA2/CONS | 08/03/2020 | 07/03/2019 | 07/22/2019 | 04/27/2020 | 04/27/2020 | 04/27/2020 | 04/27/2020 | 04/27/2020 | 05/01/2020 | 05/01/2020 | 08/03/2020 | 08/03/2020 | 12/31/9999
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | 08W | CC | Construction | ECES_CA2/CONS | 07/27/2020 | 07/03/2019 | 08/21/2019 | 06/09/2020 | 07/02/2020 | 07/02/2020 | 07/02/2020 | 07/16/2020 | 07/22/2020 | 07/22/2020 | 07/27/2020 | 07/27/2020 | 12/31/9999
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | 08W | CC | Construction | ECES_CA2/CONS | 05/26/2020 | 07/03/2019 | 08/05/2019 | 10/31/2019 | 11/01/2019 | 11/01/2019 | 11/04/2019 | 11/04/2019 | 02/06/2020 | 02/06/2020 | 03/18/2020 | 05/26/2020 | 12/31/9999 | 05/11/2020 | 05/26/2020
35114431 | CWSP - MORAGA 1101 - LR108540 - PH5 | 08W | DI | Post-Doc | ECES_CA2/FICL | 01/06/2021 | 07/09/2019 | 08/15/2019 | 11/27/2019 | 12/03/2019 | 12/03/2019 | 12/05/2019 | 12/17/2019 | 01/02/2020 | 01/02/2020 | 01/06/2020 | 01/06/2020 | 04/17/2020 | 09/22/2020 | 01/06/2021 |  |  | 04/30/2020 | 09/16/2020 | 01/06/2021 | 12/31/9999
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | 08W | YO | Pre-Construction | ECES_CA2/UNSC | 10/08/2020 | 07/11/2019 | 08/09/2019 | 08/11/2020 | 08/12/2020 | 08/12/2020 | 08/13/2020 | 08/13/2020 | 10/08/2020 | 10/08/2020 | 12/31/9999
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | 08W | YO | Pending | ECES_CA2/PEND | 10/09/2020 | 07/11/2019 | 08/09/2019 | 08/04/2020 | 08/05/2020 | 08/05/2020 | 08/05/2020 | 10/09/2020 | 12/31/9999 | 10/08/2020 | 10/09/2020
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | 08W | YO | Design | ECES_CA2/ADER | 11/06/2020 | 07/11/2019 | 08/09/2019 | 11/04/2020 | 11/06/2020 | 11/06/2020 | 12/31/9999
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | 08W | YO | Design | ECES_CA2/ESTS | 10/22/2020 | 07/11/2019 | 08/09/2019 | 10/22/2020 | 12/31/9999 | 09/23/2020 | 09/24/2020 | 09/24/2020 | 10/22/2020
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | 08W | YO | Construction | ECES_CA2/CONS | 07/27/2020 | 07/11/2019 | 08/09/2019 | 02/12/2020 | 02/12/2020 | 02/12/2020 | 02/12/2020 | 02/13/2020 | 05/15/2020 | 05/15/2020 | 07/27/2020 | 07/27/2020 | 12/31/9999
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | 08W | YO | Construction | ECES_CA2/CONS | 05/22/2020 | 07/11/2019 | 08/09/2019 | 02/28/2020 | 03/03/2020 | 03/03/2020 | 03/03/2020 | 05/08/2020 | 05/08/2020 | 05/08/2020 | 05/22/2020 | 05/22/2020 | 12/31/9999
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | 08W | YO | Construction | ECES_CA2/CONS | 09/08/2020 | 07/11/2019 | 08/09/2019 | 07/23/2020 | 07/23/2020 | 07/23/2020 | 07/23/2020 | 07/23/2020 | 07/28/2020 | 07/28/2020 | 09/08/2020 | 09/08/2020 | 12/31/9999
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | 08W | YO | Construction | ECES_CA2/CONS | 07/13/2020 | 07/11/2019 | 08/09/2019 | 04/06/2020 | 04/06/2020 | 04/06/2020 | 04/06/2020 | 06/29/2020 | 07/07/2020 | 07/07/2020 | 07/13/2020 | 07/13/2020 | 12/31/9999
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | 08W | YO | Construction | ECES_CA2/CONS | 08/19/2020 | 07/11/2019 | 08/06/2019 | 02/13/2020 | 02/14/2020 | 02/14/2020 | 02/16/2020 | 02/18/2020 | 04/06/2020 | 04/06/2020 | 08/19/2020 | 08/19/2020 | 12/31/9999
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | 08W | YO | Construction | ECES_CA2/CONS | 07/27/2020 | 07/11/2019 | 08/06/2019 | 04/20/2020 | 04/21/2020 | 04/21/2020 | 04/21/2020 | 04/21/2020 | 05/15/2020 | 05/15/2020 | 07/27/2020 | 07/27/2020 | 12/31/9999
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | 08W | YO | Construction | ECES_CA2/CONS | 10/26/2020 | 07/11/2019 | 08/06/2019 | 07/04/2020 | 07/07/2020 | 07/07/2020 | 07/07/2020 | 07/07/2020 | 07/13/2020 | 07/13/2020 | 10/26/2020 | 10/26/2020 | 12/31/9999
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | 08W | YO | Pre-Construction | ECES_CA2/UNSC | 09/28/2020 | 07/11/2019 | 08/06/2019 | 08/06/2019 | 07/20/2020 | 07/20/2020 | 07/24/2020 | 07/24/2020 | 09/28/2020 | 09/28/2020 | 12/31/9999
35115080 | BR-02-10-W (E) HARVEY RD PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/11/2019 | 07/11/2019 | 12/31/9999
35115084 | BR-01-11-W (E) MONTNA DR PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/11/2019 | 07/11/2019 | 12/31/9999
35115147 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.2 | 08W | SI | Post-Doc | ECES_CA2/FICL | 02/08/2021 | 07/12/2019 | 07/26/2019 | 02/24/2020 | 02/24/2020 | 02/24/2020 | 02/25/2020 | 02/25/2020 | 02/26/2020 | 02/26/2020 | 05/04/2020 | 05/04/2020 | 08/20/2020 | 08/20/2020 | 01/28/2021 |  |  | 01/28/2021 | 02/08/2021 | 02/08/2021 | 12/31/9999
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | 08W | SI | Post-Doc | ECES_CA2/FICL | 02/10/2021 | 07/12/2019 | 07/26/2019 | 04/23/2020 | 04/23/2020 | 04/23/2020 | 04/24/2020 | 04/24/2020 | 05/15/2020 | 05/15/2020 | 05/20/2020 | 05/20/2020 | 12/01/2020 | 02/05/2021 | 02/10/2021 |  |  | 12/14/2020 | 01/12/2021 | 02/10/2021 | 12/31/9999
35115149 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.4 | 08W | SI | Completion | ECES_CA2/CLSD | 12/12/2020 | 07/12/2019 | 07/26/2019 | 07/26/2019 | 11/22/2019 | 11/22/2019 | 11/24/2019 | 11/27/2019 | 02/28/2020 | 02/28/2020 | 05/13/2020 | 05/13/2020 | 06/10/2020 | 06/10/2020 | 06/17/2020 |  |  | 06/17/2020 | 08/11/2020 | 08/11/2020 | 12/09/2020 | 12/12/2020 | 12/31/9999
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | 08W | SI | Post-Doc | ECES_CA2/FICL | 10/16/2020 | 07/12/2019 | 07/26/2019 | 05/30/2020 | 06/01/2020 | 06/01/2020 | 06/01/2020 | 06/01/2020 | 06/10/2020 | 06/10/2020 | 06/15/2020 | 06/15/2020 | 09/09/2020 | 09/09/2020 | 09/11/2020 |  |  | 09/11/2020 | 10/16/2020 | 10/16/2020 | 12/31/9999
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | SI | Construction | ECES_CA2/CONS | 08/10/2020 | 07/12/2019 | 07/26/2019 | 07/26/2019 | 05/28/2020 | 05/28/2020 | 05/28/2020 | 07/25/2020 | 07/27/2020 | 07/27/2020 | 08/10/2020 | 08/10/2020 | 12/31/9999
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | SI | Construction | ECES_CA2/CONS | 11/23/2020 | 07/12/2019 | 07/26/2019 | 08/26/2020 | 08/26/2020 | 08/26/2020 | 08/26/2020 | 08/26/2020 | 08/26/2020 | 08/26/2020 | 11/23/2020 | 11/23/2020 | 12/31/9999
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | SI | Construction | ECES_CA2/CONS | 10/21/2020 | 07/12/2019 | 07/26/2019 | 07/01/2020 | 07/01/2020 | 07/01/2020 | 07/02/2020 | 07/27/2020 | 07/28/2020 | 07/28/2020 | 10/21/2020 | 10/21/2020 | 12/31/9999
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | SI | Construction | ECES_CA2/CONS | 08/17/2020 | 07/12/2019 | 07/26/2019 | 07/01/2020 | 07/01/2020 | 07/01/2020 | 07/02/2020 | 08/13/2020 | 08/13/2020 | 08/13/2020 | 08/17/2020 | 08/17/2020 | 12/31/9999
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | 08W | # | Construction | ECES_CA2/CONS | 01/15/2020 | 07/12/2019 | 07/26/2019 | 11/14/2019 | 11/14/2019 | 11/14/2019 | 11/14/2019 | 11/14/2019 | 12/26/2019 | 12/26/2019 | 01/15/2020 | 01/15/2020 | 12/31/9999
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | 08W | SI | Documentation | ECES_CA2/DOCC | 01/15/2021 | 07/12/2019 | 07/25/2019 | 05/18/2020 | 05/19/2020 | 05/19/2020 | 06/09/2020 | 06/09/2020 | 06/11/2020 | 06/11/2020 | 06/11/2020 | 06/11/2020 | 07/09/2020 | 01/15/2021 | 12/31/9999 |  |  | 07/10/2020 | 09/08/2020 | 09/08/2020 | 01/15/2021
35115157 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.4 | 08W | SI | Post-Doc | ECES_CA2/FICL | 11/24/2020 | 07/12/2019 | 07/26/2019 | 07/26/2019 | 11/13/2019 | 11/13/2019 | 11/13/2019 | 11/14/2019 | 01/06/2020 | 01/06/2020 | 03/02/2020 | 05/07/2020 | 10/02/2020 | 10/02/2020 | 10/13/2020 |  |  | 10/13/2020 | 11/24/2020 | 11/24/2020 | 12/31/9999
35115158 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.5 | 08W | SI | Completion | ECES_CA2/CLSD | 12/12/2020 | 07/12/2019 | 07/26/2019 | 05/18/2020 | 05/22/2020 | 05/22/2020 | 05/22/2020 | 05/22/2020 | 05/28/2020 | 03/03/2020 | 03/09/2020 | 05/28/2020 | 07/20/2020 | 07/20/2020 | 07/21/2020 |  |  | 07/21/2020 | 09/15/2020 | 09/15/2020 | 12/09/2020 | 12/12/2020 | 12/31/9999
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | 08W | ST | Design | ECES_CA2/ESTS | 10/27/2020 | 07/16/2019 | 08/05/2019 | 10/27/2020 | 12/31/9999 | 10/21/2020 | 10/27/2020
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | 08W | ST | Pending | ECES_CA2/PEND | 11/03/2020 | 07/16/2019 | 08/05/2019 | 08/05/2019 | 07/07/2020 | 07/07/2020 | 07/08/2020 | 11/03/2020 | 12/31/9999 | 10/29/2020 | 11/03/2020
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | 08W | ST | Pending | ECES_CA2/PEND | 09/02/2020 | 07/16/2019 | 08/05/2019 | 04/16/2020 | 04/23/2020 | 04/23/2020 | 04/23/2020 | 09/02/2020 | 12/31/9999 | 07/16/2020 | 09/02/2020
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | 08W | ST | Pre-Construction | ECES_CA2/UNSC | 10/29/2020 | 07/16/2019 | 08/05/2019 | 08/05/2019 | 08/12/2020 | 08/12/2020 | 08/13/2020 | 09/08/2020 | 10/29/2020 | 10/29/2020 | 12/31/9999
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | 08W | ST | Pending | ECES_CA2/PEND | 11/16/2020 | 07/16/2019 | 08/05/2019 | 11/13/2020 | 11/13/2020 | 11/13/2020 | 11/16/2020 | 11/16/2020 | 12/31/9999
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | 08W | ST | Pending | ECES_CA2/PEND | 10/19/2020 | 07/16/2019 | 08/05/2019 | 08/05/2019 | 05/28/2020 | 05/28/2020 | 05/28/2020 | 10/19/2020 | 12/31/9999 | 10/18/2020 | 10/19/2020
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | 08W | ST | Pre-Construction | ECES_CA2/UNSC | 11/16/2020 | 07/16/2019 | 08/05/2019 | 11/13/2020 | 11/13/2020 | 11/13/2020 | 11/13/2020 | 11/13/2020 | 11/16/2020 | 11/16/2020 | 12/31/9999
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | 08W | ST | Construction | ECES_CA2/CONS | 10/22/2020 | 07/16/2019 | 08/05/2019 | 05/14/2020 | 05/14/2020 | 05/14/2020 | 05/14/2020 | 07/21/2020 | 09/04/2020 | 09/04/2020 | 10/22/2020 | 10/22/2020 | 12/31/9999
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | 08W | ST | Documentation | ECES_CA2/DOCC | 02/17/2021 | 07/16/2019 | 08/05/2019 | 01/09/2020 | 01/10/2020 | 01/10/2020 | 01/13/2020 | 03/06/2020 | 04/13/2020 | 04/13/2020 | 05/25/2020 | 05/25/2020 | 02/17/2021 | 02/17/2021 | 12/31/9999
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | 08W | ST | Pre-Construction | ECES_CA2/UNSC | 02/04/2021 | 07/16/2019 | 08/05/2019 | 07/02/2020 | 07/07/2020 | 07/07/2020 | 07/07/2020 | 12/29/2020 | 02/04/2021 | 02/04/2021 | 12/31/9999
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | 08W | ST | Pending | ECES_CA2/PEND | 07/15/2020 | 07/16/2019 | 08/05/2019 | 07/14/2020 | 07/14/2020 | 07/14/2020 | 07/14/2020 | 07/15/2020 | 12/31/9999
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | 08W | ST | Pre-Construction | ECES_CA2/UNSC | 01/19/2021 | 07/16/2019 | 08/05/2019 | 07/02/2020 | 07/03/2020 | 07/03/2020 | 07/03/2020 | 11/04/2020 | 01/19/2021 | 01/19/2021 | 12/31/9999 | 10/22/2020 | 10/25/2020
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | 08W | YO | Construction | ECES_CA2/CONS | 03/23/2020 | 07/17/2019 | 08/09/2019 | 08/09/2019 | 10/14/2019 | 10/14/2019 | 10/14/2019 | 10/16/2019 | 03/18/2020 | 03/18/2020 | 03/23/2020 | 03/23/2020 | 12/31/9999
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | 08W | YO | Construction | ECES_CA2/CONS | 09/07/2020 | 07/17/2019 | 08/09/2019 | 05/07/2020 | 05/08/2020 | 05/08/2020 | 05/08/2020 | 07/23/2020 | 07/28/2020 | 07/28/2020 | 09/07/2020 | 09/07/2020 | 12/31/9999
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | 08W | YO | Pending | ECES_CA2/PEND | 05/27/2020 | 07/17/2019 | 08/09/2019 | 08/09/2019 | 05/27/2020 | 05/27/2020 | 05/27/2020 | 05/27/2020 | 12/31/9999
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | 08W | YO | Pending | ECES_CA2/PEND | 11/10/2020 | 07/17/2019 | 08/09/2019 | 10/23/2020 | 11/10/2020 | 11/10/2020 | 11/10/2020 | 11/10/2020 | 12/31/9999 | 08/26/2020 | 10/23/2020
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | 08W | YO | Design | ECES_CA2/ESTS | 08/20/2020 | 07/17/2019 | 08/09/2019 | 08/20/2020 | 12/31/9999 | 08/14/2020 | 08/20/2020
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | 08W | YO | Construction | ECES_CA2/CONS | 10/14/2020 | 07/17/2019 | 08/09/2019 | 08/09/2019 | 01/08/2020 | 01/08/2020 | 01/09/2020 | 01/10/2020 | 07/31/2020 | 07/31/2020 | 10/14/2020 | 10/14/2020 | 12/31/9999
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | 08W | YO | Documentation | ECES_CA2/DOCC | 02/05/2021 | 07/17/2019 | 08/06/2019 | 08/06/2019 | 02/24/2020 | 02/24/2020 | 02/24/2020 | 02/25/2020 | 04/24/2020 | 04/24/2020 | 07/29/2020 | 07/29/2020 | 02/05/2021 | 02/05/2021 | 12/31/9999
35116393 | CWSP - MIWUK 1702 - OCB - PH 1.3 | 08W | YO | Completion | ECES_CA2/CLSD | 01/16/2021 | 07/17/2019 | 08/06/2019 | 11/12/2019 | 11/18/2019 | 11/18/2019 | 11/18/2019 | 11/21/2019 | 12/10/2019 | 12/10/2019 | 12/12/2019 | 01/02/2020 | 03/25/2020 | 10/01/2020 | 10/29/2020 | 05/06/2020 | 05/14/2020 | 03/30/2020 | 05/06/2020 | 10/29/2020 | 01/12/2021 | 01/16/2021 | 12/31/9999
35116394 | CWSP - MIWUK 1702 - OCB - PH 1.4 | 08W | YO | Completion | ECES_CA2/CLSD | 01/16/2021 | 07/17/2019 | 08/06/2019 | 08/06/2019 | 01/22/2020 | 01/22/2020 | 02/19/2020 | 02/19/2020 | 02/28/2020 | 02/28/2020 | 03/24/2020 | 03/24/2020 | 06/25/2020 | 06/25/2020 | 06/26/2020 |  |  | 06/26/2020 | 08/21/2020 | 08/21/2020 | 01/12/2021 | 01/16/2021 | 12/31/9999
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | 08W | YO | Construction | ECES_CA2/CONS | 07/27/2020 | 07/17/2019 | 08/06/2019 | 08/06/2019 | 05/22/2020 | 05/22/2020 | 05/22/2020 | 07/08/2020 | 07/08/2020 | 07/08/2020 | 07/27/2020 | 07/27/2020 | 12/31/9999
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | 08W | YO | Construction | ECES_CA2/CONS | 09/24/2020 | 07/17/2019 | 08/06/2019 | 08/06/2019 | 05/29/2020 | 05/29/2020 | 05/29/2020 | 07/15/2020 | 09/17/2020 | 09/17/2020 | 09/24/2020 | 09/24/2020 | 12/31/9999
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | 08W | YO | Pending | ECES_CA2/PEND | 08/14/2020 | 07/17/2019 | 08/06/2019 | 06/09/2020 | 06/10/2020 | 06/10/2020 | 06/15/2020 | 08/14/2020 | 12/31/9999 | 08/13/2020 | 08/14/2020 |  |  |  |  | 07/29/2020 | 08/10/2020
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | 08W | YO | Design | ECES_CA2/ESTS | 09/21/2020 | 07/17/2019 | 08/06/2019 | 09/21/2020 | 12/31/9999 | 09/17/2020 | 09/21/2020
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | 08W | YO | Pre-Construction | ECES_CA2/UNSC | 09/01/2020 | 07/17/2019 | 08/06/2019 | 08/21/2020 | 08/21/2020 | 08/21/2020 | 08/21/2020 | 08/21/2020 | 09/01/2020 | 09/01/2020 | 12/31/9999
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | 08W | YO | Design | ECES_CA2/ESTS | 11/05/2020 | 07/17/2019 | 08/06/2019 | 11/05/2020 | 12/31/9999 | 10/14/2020 | 11/05/2020
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | 08W | YO | Design | ECES_CA2/ESTS | 08/06/2019 | 07/17/2019 | 08/06/2019 | 08/06/2019 | 12/31/9999
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | 08W | YO | Documentation | ECES_CA2/DOCC | 02/05/2021 | 07/17/2019 | 08/06/2019 | 02/25/2020 | 02/27/2020 | 02/27/2020 | 02/27/2020 | 04/01/2020 | 06/24/2020 | 06/24/2020 | 07/09/2020 | 07/09/2020 | 02/05/2021 | 02/05/2021 | 12/31/9999
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | 08W | YO | Construction | ECES_CA2/CONS | 10/30/2020 | 07/17/2019 | 08/06/2019 | 04/15/2020 | 04/16/2020 | 04/16/2020 | 04/16/2020 | 07/20/2020 | 08/10/2020 | 08/10/2020 | 10/30/2020 | 10/30/2020 | 12/31/9999
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | 08W | YO | Construction | ECES_CA2/CONS | 07/27/2020 | 07/17/2019 | 08/06/2019 | 04/05/2020 | 04/07/2020 | 04/07/2020 | 04/07/2020 | 06/26/2020 | 06/26/2020 | 06/26/2020 | 07/27/2020 | 07/27/2020 | 12/31/9999
35116511 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 | 08W | ST | Pre-Construction | ECES_CA2/UNSC | 11/09/2020 | 07/18/2019 | 08/05/2019 | 08/05/2019 | 08/04/2020 | 08/04/2020 | 08/04/2020 | 08/04/2020 | 11/09/2020 | 11/09/2020 | 12/31/9999
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | 08W | ST | Pending | ECES_CA2/PEND | 07/23/2020 | 07/18/2019 | 08/05/2019 | 08/05/2019 | 07/22/2020 | 07/22/2020 | 07/23/2020 | 07/23/2020 | 12/31/9999
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 | 08W | ST | Pending | ECES_CA2/PEND | 10/01/2020 | 07/18/2019 | 08/05/2019 | 09/30/2020 | 09/30/2020 | 09/30/2020 | 09/30/2020 | 10/01/2020 | 12/31/9999
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | 08W | ST | Pending | ECES_CA2/PEND | 09/22/2020 | 07/18/2019 | 08/05/2019 | 09/15/2020 | 09/21/2020 | 09/21/2020 | 09/22/2020 | 09/22/2020 | 12/31/9999
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | 08W | ST | Pre-Construction | ECES_CA2/UNSC | 07/20/2020 | 07/18/2019 | 08/12/2019 | 05/29/2020 | 05/29/2020 | 05/29/2020 | 05/29/2020 | 05/29/2020 | 07/20/2020 | 07/20/2020 | 12/31/9999
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | 08W | ST | Pending | ECES_CA2/PEND | 07/15/2020 | 07/18/2019 | 08/12/2019 | 06/03/2020 | 06/07/2020 | 06/07/2020 | 06/09/2020 | 07/15/2020 | 12/31/9999 | 07/14/2020 | 07/15/2020
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | 08W | ST | Pending | ECES_CA2/PEND | 08/24/2020 | 07/18/2019 | 08/12/2019 | 08/24/2020 | 08/24/2020 | 08/24/2020 | 08/24/2020 | 08/24/2020 | 12/31/9999
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | 08W | ST | Pending | ECES_CA2/PEND | 01/21/2021 | 07/18/2019 | 08/12/2019 | 10/27/2020 | 10/27/2020 | 10/27/2020 | 10/29/2020 | 01/21/2021 | 12/31/9999 | 01/20/2021 | 01/21/2021
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | 08W | ST | Pending | ECES_CA2/PEND | 12/30/2020 | 07/18/2019 | 08/12/2019 | 08/26/2020 | 08/27/2020 | 08/27/2020 | 08/27/2020 | 12/30/2020 | 12/31/9999 | 10/29/2020 | 12/30/2020
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | 08W | YO | Documentation | ECES_CA2/DOCC | 02/08/2021 | 07/18/2019 | 08/06/2019 | 07/23/2020 | 07/24/2020 | 07/24/2020 | 07/27/2020 | 08/28/2020 | 09/02/2020 | 07/28/2020 | 08/28/2020 | 09/02/2020 | 02/08/2021 | 02/08/2021 | 12/31/9999
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | 08W | YO | Pre-Construction | ECES_CA2/UNSC | 07/22/2020 | 07/18/2019 | 08/06/2019 | 04/14/2020 | 04/15/2020 | 04/15/2020 | 04/15/2020 | 05/28/2020 | 07/22/2020 | 07/22/2020 | 12/31/9999
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | 08W | YO | Documentation | ECES_CA2/DOCC | 12/18/2020 | 07/18/2019 | 08/06/2019 | 02/20/2020 | 02/20/2020 | 02/20/2020 | 02/20/2020 | 05/01/2020 | 06/08/2020 | 06/08/2020 | 06/08/2020 | 06/08/2020 | 12/18/2020 | 12/18/2020 | 12/31/9999
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | 08W | YO | Pending | ECES_CA2/PEND | 10/26/2020 | 07/18/2019 | 08/06/2019 | 08/21/2020 | 08/21/2020 | 08/21/2020 | 08/24/2020 | 10/26/2020 | 12/31/9999 | 10/23/2020 | 10/26/2020
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | 08W | YO | Completion | ECES_CA2/CLSD | 01/16/2021 | 07/18/2019 | 08/06/2019 | 04/22/2020 | 04/23/2020 | 04/23/2020 | 04/23/2020 | 04/23/2020 | 05/28/2020 | 05/28/2020 | 06/08/2020 | 06/08/2020 | 09/29/2020 | 09/29/2020 | 10/05/2020 |  |  | 10/05/2020 | 10/30/2020 | 10/30/2020 | 01/12/2021 | 01/16/2021 | 12/31/9999
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | 08W | ST | Pending | ECES_CA2/PEND | 08/27/2020 | 07/19/2019 | 08/12/2019 | 08/27/2020 | 08/27/2020 | 08/27/2020 | 08/27/2020 | 08/27/2020 | 12/31/9999
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | 08W | ST | Pending | ECES_CA2/PEND | 11/10/2020 | 07/19/2019 | 08/12/2019 | 06/18/2020 | 06/18/2020 | 06/18/2020 | 06/18/2020 | 11/10/2020 | 12/31/9999 | 11/09/2020 | 11/10/2020
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | 08W | ST | Design | ECES_CA2/ADER | 10/07/2020 | 07/19/2019 | 08/12/2019 | 08/31/2020 | 10/07/2020 | 10/07/2020 | 12/31/9999
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | 08W | ST | Pending | ECES_CA2/PEND | 12/08/2020 | 07/19/2019 | 08/12/2019 | 12/07/2020 | 12/08/2020 | 12/08/2020 | 12/08/2020 | 12/08/2020 | 12/31/9999
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | 08W | ST | Design | ECES_CA2/ADER | 11/20/2020 | 07/19/2019 | 08/12/2019 | 11/03/2020 | 11/20/2020 | 11/20/2020 | 12/31/9999
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 | 08W | ST | Pending | ECES_CA2/PEND | 11/10/2020 | 07/19/2019 | 08/12/2019 | 08/12/2019 | 07/16/2020 | 07/16/2020 | 07/16/2020 | 11/10/2020 | 12/31/9999 | 11/09/2020 | 11/10/2020
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 | 08W | NV | Design | ECES_CA2/ESTS | 11/18/2019 | 07/23/2019 | 11/18/2019 | 11/18/2019 | 12/31/9999
35117398 | BR-01-12-W (E) MYRTLE WAY, PARB | 08W | NV | Design | ECES_CA2/ESTS | 12/04/2019 | 07/24/2019 | 12/04/2019 | 12/04/2019 | 12/31/9999
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | SI | Construction | ECES_CA2/CONS | 01/06/2021 | 07/24/2019 | 09/04/2019 | 06/10/2020 | 06/23/2020 | 12/09/2020 | 12/09/2020 | 01/06/2021 | 01/06/2021 | 12/09/2020 | 12/09/2020 | 01/06/2021 | 12/31/9999
35117444 | CWSP - VOLTA 1102 LR 1648 PH 2.1 | 08W | NV | Post-Doc | ECES_CA2/FICL | 02/03/2021 | 07/24/2019 | 07/25/2019 | 07/25/2019 | 08/29/2019 | 08/29/2019 | 08/29/2019 | 08/30/2019 | 09/28/2019 | 09/28/2019 | 01/27/2020 | 01/27/2020 | 05/06/2020 | 05/06/2020 | 12/05/2020 |  |  | 12/05/2020 | 02/03/2021 | 02/03/2021 | 12/31/9999
35117455 | BR-02-04-W (E) HERMAN PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/25/2019 | 07/25/2019 | 12/31/9999
35117540 | BR-02-01-W (E) CLARK RD & SAN JOSE PARB | 08W | NV | Design | ECES_CA2/ESTS | 12/18/2020 | 07/24/2019 | 08/14/2020 | 12/18/2020 | 12/31/9999 | 08/20/2020 | 12/18/2020
35117983 | BR-02-07-W (E) DOLORES DR, PARB | 08W | NV | Documentation | ECES_CA2/DOCC | 12/19/2020 | 07/25/2019 | 12/19/2020 | [10 empty] | 12/19/2020 | 12/31/9999
35117986 | BR-02-08-W (E) DIAMOND LN PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/25/2019 | 07/25/2019 | 12/31/9999
35118422 | BR-02-13-W (E) LANCASTER DR PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/29/2019 | 07/29/2019 | 12/31/9999
35118425 | BR-04-04-W (E) VALLEY VIEW PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/29/2019 | 07/29/2019 | 12/31/9999
35118433 | BR-04-10-W (E) CRESTVIEW PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/30/2019 | 07/30/2019 | 12/31/9999
35118438 | BR-11-01-W (E) FOSTER RD, PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/30/2019 | 07/30/2019 | 12/31/9999
35118502 | BR-06-01-W (E) DELIA WAY, PARB | 08W | NV | Design | ECES_CA2/ESTS | 09/18/2019 | 07/30/2019 | 09/18/2019 | 09/18/2019 | 12/31/9999
35118504 | BR-06-02-W (E) COPELAND RD PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/30/2019 | 07/30/2019 | 12/31/9999
35118511 | BR-06-03-W (E) DEL MAR AVE PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/30/2019 | 07/30/2019 | 12/31/9999
35118513 | BR-06-04-W (E) HEAVENLY PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/30/2019 | 07/30/2019 | 12/31/9999
35118515 | BR-07-02-W (E) YOUNG AVE PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/30/2019 | 07/30/2019 | 12/31/9999
35118516 | BR-07-04-W_03 (E) PECK LN PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/30/2019 | 07/30/2019 | 12/31/9999
35118517 | BR-07-05-W (E) FLICKER LN, PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/30/2019 | 07/30/2019 | 12/31/9999
35118518 | BR-07-06-W (E) NIELSEN DR PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/30/2019 | 07/30/2019 | 12/31/9999
35118519 | BR-07-08-W (E) FOLAND RD PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/30/2019 | 07/30/2019 | 12/31/9999
35118662 | BR-11-07-W (E) APPLE LN PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/31/2019 | 07/31/2019 | 12/31/9999
35118663 | BR-01-01-W (E) HEAVENS GATE PARB | 08W | NV | Construction | ECES_CA2/CONS | 12/19/2020 | 07/31/2019 | 08/26/2019 | 08/26/2019 | 06/01/2020 | 06/01/2020 | 06/01/2020 | 09/02/2020 | 09/18/2020 | 09/18/2020 | 12/19/2020 | 12/19/2020 | 12/31/9999
35118671 | BR-MG-1A-W DRAKE CT PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/31/2019 | 07/31/2019 | 12/31/9999
35118673 | BR-MG-4A-W WICHITA DR PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/31/2019 | 07/31/2019 | 12/31/9999
35118674 | BR-MG-05-W PUEBLO DR PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/31/2019 | 07/31/2019 | 12/31/9999
35118675 | BR-MG-05-W SHAW CIR PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/31/2019 | 07/31/2019 | 12/31/9999
35118700 | BR-10-01-W (E) STARLIGHT CT PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/30/2019 | 07/30/2019 | 12/31/9999
35118701 | *CANC* BR-10-02-W (E) CIRCLEWOOD DR, PA | 08W | NV | Completion | ECES_CA2/CLSD | 11/05/2020 | 07/30/2019 | 09/22/2020 | [18 empty] | 11/05/2020 | 12/31/9999 | 10/03/2020 | 11/05/2020
35118702 | BR-11-03-W (E) GREGS WAY, PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 07/30/2019 | 07/30/2019 | 12/31/9999
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | 08W | CC | Post-Doc | ECES_CA2/FICL | 08/18/2020 | 08/07/2019 | 08/13/2019 | 11/26/2019 | 12/02/2019 | 12/02/2019 | 12/04/2019 | 02/19/2020 | 02/20/2020 | 02/20/2020 | 03/02/2020 | 03/02/2020 | 07/15/2020 | 07/15/2020 | 07/16/2020 |  |  | 07/16/2020 | 08/18/2020 | 08/18/2020 | 12/31/9999
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | 08W | DA | Construction | ECES_CA2/CONS | 06/08/2020 | 08/07/2019 | 08/20/2019 | 12/11/2019 | 12/11/2019 | 12/11/2019 | 12/11/2019 | 12/16/2019 | 05/18/2020 | 05/18/2020 | 06/08/2020 | 06/08/2020 | 12/31/9999
35119966 | CWSP - LOS GATOS 1106 - LB44 - PH 2.6F | 08W | DA | Post-Doc | ECES_CA2/FICL | 12/17/2020 | 08/07/2019 | 08/20/2019 | 08/20/2019 | 11/21/2019 | 11/21/2019 | 11/21/2019 | 11/22/2019 | 01/21/2020 | 01/21/2020 | 02/06/2020 | 02/06/2020 | 04/02/2020 | 11/30/2020 | 12/17/2020 |  |  | 04/10/2020 | 05/13/2020 | 12/17/2020 | 12/31/9999
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | 08W | DA | Initiation | ECES_CA2/UNSE | 08/07/2019 | 08/07/2019 | 12/31/9999
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | 08W | DA | Initiation | ECES_CA2/UNSE | 08/07/2019 | 08/07/2019 | 12/31/9999
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | 08W | DA | Documentation | ECES_CA2/DOCC | 12/03/2020 | 08/07/2019 | 08/21/2019 | 08/21/2019 | 11/27/2019 | 11/27/2019 | 11/27/2019 | 12/02/2019 | 01/22/2020 | 01/22/2020 | 03/23/2020 | 03/23/2020 | 12/03/2020 | 12/03/2020 | 12/31/9999
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | 08W | DA | Post-Doc | ECES_CA2/FICL | 01/21/2021 | 08/07/2019 | 08/21/2019 | 12/03/2019 | 12/03/2019 | 12/03/2019 | 12/03/2019 | 12/03/2019 | 01/20/2020 | 01/20/2020 | 02/19/2020 | 02/19/2020 | 11/20/2020 | 11/20/2020 | 01/05/2021 |  |  | 01/05/2021 | 01/21/2021 | 01/21/2021 | 12/31/9999
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | 08W | DA | Initiation | ECES_CA2/UNSE | 08/07/2019 | 08/07/2019 | 12/31/9999
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | 08W | NV | Documentation | ECES_CA2/DOCC | 01/08/2021 | 08/14/2019 | 08/14/2019 | 11/18/2020 | 11/20/2020 | 11/20/2020 | 11/20/2020 | 11/20/2020 | 01/08/2021 | 11/20/2020 | 11/20/2020 | 03/16/2020 | 11/18/2020 | 01/08/2021 | 12/31/9999
35121739 | *CANCEL* CENTERILLE REMOVAL - BUTTE 1105 | 08W | NV | Completion | ECES_CA1/CLSD | 09/01/2019 | 08/21/2019 | 08/23/2019 | 08/23/2019 | 08/27/2019 | [14 empty] | 08/27/2019 | 08/27/2019 | 09/01/2019 | 12/31/9999
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 | 08W | NV | Design | ECES_CA2/ADER | 09/11/2020 | 09/21/2019 | 11/18/2019 | 11/18/2019 | 09/11/2020 | 09/11/2020 | 12/31/9999
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | 08W | NV | Pre-Construction | ECES_CA2/UNSC | 08/12/2020 | 09/21/2019 | 11/18/2019 | 08/01/2020 | 08/03/2020 | 08/03/2020 | 08/03/2020 | 08/07/2020 | 08/12/2020 | 08/12/2020 | 12/31/9999
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | 08W | NV | Pending | ECES_CA2/PEND | 10/28/2020 | 09/21/2019 | 11/18/2019 | 08/28/2020 | 09/01/2020 | 09/01/2020 | 09/04/2020 | 10/28/2020 | 12/31/9999 | 10/27/2020 | 10/28/2020
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | 08W | NV | Pre-Construction | ECES_CA2/UNSC | 08/18/2020 | 09/21/2019 | 11/18/2019 | 07/13/2020 | 07/13/2020 | 07/13/2020 | 07/13/2020 | 08/12/2020 | 08/18/2020 | 08/18/2020 | 12/31/9999
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | 08W | NV | Design | ECES_CA2/ESTS | 11/12/2020 | 09/21/2019 | 11/18/2019 | 11/12/2020 | 12/31/9999 | 10/22/2020 | 11/12/2020
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | 08W | NV | Pending | ECES_CA2/PEND | 12/29/2020 | 09/21/2019 | 11/18/2019 | 11/18/2019 | 07/28/2020 | 07/28/2020 | 07/28/2020 | 12/29/2020 | 12/31/9999 | 10/27/2020 | 12/29/2020
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | 08W | NV | Pending | ECES_CA2/PEND | 11/03/2020 | 09/21/2019 | 11/18/2019 | 08/10/2020 | 08/23/2020 | 08/23/2020 | 08/24/2020 | 11/03/2020 | 12/31/9999 | 10/26/2020 | 11/03/2020
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | 08W | NV | Pending | ECES_CA2/PEND | 11/02/2020 | 09/21/2019 | 11/18/2019 | 08/25/2020 | 08/26/2020 | 08/26/2020 | 08/26/2020 | 11/02/2020 | 12/31/9999 | 10/26/2020 | 11/02/2020
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | 08W | NV | Pending | ECES_CA2/PEND | 11/09/2020 | 09/23/2019 | 11/18/2019 | 11/09/2020 | 11/09/2020 | 11/09/2020 | 11/09/2020 | 11/09/2020 | 12/31/9999
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | 08W | NV | Pending | ECES_CA2/PEND | 12/02/2020 | 09/23/2019 | 11/18/2019 | 10/08/2020 | 10/08/2020 | 10/08/2020 | 10/08/2020 | 12/02/2020 | 12/31/9999 | 11/30/2020 | 12/02/2020
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | 08W | NV | Pending | ECES_CA2/PEND | 09/04/2020 | 09/23/2019 | 11/18/2019 | 09/04/2020 | 09/04/2020 | 09/04/2020 | 09/04/2020 | 09/04/2020 | 12/31/9999
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | 08W | NV | Pending | ECES_CA2/PEND | 10/06/2020 | 09/23/2019 | 11/18/2019 | 08/12/2020 | 08/12/2020 | 08/12/2020 | 08/12/2020 | 10/06/2020 | 10/06/2020 | 10/06/2020 | 10/06/2020
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | 08W | NV | Pending | ECES_CA2/PEND | 10/10/2020 | 09/23/2019 | 11/18/2019 | 09/25/2020 | 10/01/2020 | 10/01/2020 | 10/09/2020 | 10/10/2020 | 12/31/9999
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | 08W | NV | Pending | ECES_CA2/PEND | 09/11/2020 | 09/23/2019 | 11/18/2019 | 11/18/2019 | 09/09/2020 | 09/09/2020 | 09/09/2020 | 09/11/2020 | 12/31/9999
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | 08W | NV | Pending | ECES_CA2/PEND | 10/27/2020 | 09/23/2019 | 11/18/2019 | 11/18/2019 | 08/05/2020 | 08/05/2020 | 08/14/2020 | 10/27/2020 | 12/31/9999 | 10/26/2020 | 10/27/2020
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | 08W | NV | Pending | ECES_CA2/PEND | 11/02/2020 | 09/23/2019 | 11/18/2019 | 11/18/2019 | 07/07/2020 | 07/07/2020 | 07/07/2020 | 11/02/2020 | 12/31/9999 | 09/28/2020 | 11/02/2020
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | 08W | NV | Pending | ECES_CA2/PEND | 09/29/2020 | 09/23/2019 | 11/18/2019 | 07/01/2020 | 07/01/2020 | 07/01/2020 | 07/01/2020 | 09/29/2020 | 12/31/9999 | 09/28/2020 | 09/29/2020
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 | 08W | NV | Pending | ECES_CA2/PEND | 09/29/2020 | 09/23/2019 | 11/18/2019 | 05/06/2020 | 05/06/2020 | 05/06/2020 | 05/06/2020 | 09/29/2020 | 12/31/9999 | 09/28/2020 | 09/29/2020
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | 08W | NV | Pending | ECES_CA2/PEND | 09/28/2020 | 09/23/2019 | 11/18/2019 | 08/05/2020 | 08/05/2020 | 08/05/2020 | 08/06/2020 | 09/28/2020 | 09/28/2020 | 09/28/2020 | 09/28/2020
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | 08W | NV | Pending | ECES_CA2/PEND | 09/29/2020 | 09/23/2019 | 11/18/2019 | 11/18/2019 | 08/04/2020 | 08/04/2020 | 08/06/2020 | 09/29/2020 | 12/31/9999 | 09/28/2020 | 09/29/2020
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 | 08W | NV | Pending | ECES_CA2/PEND | 11/02/2020 | 09/23/2019 | 11/18/2019 | 06/23/2020 | 06/24/2020 | 06/24/2020 | 06/24/2020 | 11/02/2020 | 12/31/9999 | 09/28/2020 | 11/02/2020
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | 08W | NV | Pending | ECES_CA2/PEND | 10/14/2020 | 09/23/2019 | 11/18/2019 | 11/18/2019 | 08/13/2020 | 08/14/2020 | 08/14/2020 | 10/14/2020 | 12/31/9999 | 09/28/2020 | 10/14/2020
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 | 08W | NV | Pending | ECES_CA2/PEND | 12/03/2020 | 09/23/2019 | 11/18/2019 | 09/23/2020 | 09/25/2020 | 09/25/2020 | 09/28/2020 | 12/03/2020 | 12/31/9999 | 11/10/2020 | 12/03/2020
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | 08W | NV | Pending | ECES_CA2/PEND | 09/29/2020 | 09/23/2019 | 11/18/2019 | 06/03/2020 | 06/05/2020 | 06/05/2020 | 06/05/2020 | 09/29/2020 | 12/31/9999 | 09/28/2020 | 09/29/2020
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 | 08W | NV | Pending | ECES_CA2/PEND | 10/28/2020 | 09/23/2019 | 11/18/2019 | 10/25/2020 | 10/25/2020 | 10/25/2020 | 10/27/2020 | 10/28/2020 | 12/31/9999
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | 08W | NV | Pending | ECES_CA2/PEND | 10/13/2020 | 09/23/2019 | 11/18/2019 | 11/18/2019 | 08/06/2020 | 08/06/2020 | 08/10/2020 | 10/13/2020 | 12/31/9999 | 09/28/2020 | 10/13/2020
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | 08W | NV | Pending | ECES_CA2/PEND | 09/29/2020 | 09/23/2019 | 11/18/2019 | 07/17/2020 | 07/17/2020 | 07/17/2020 | 07/17/2020 | 09/29/2020 | 12/31/9999 | 09/28/2020 | 09/29/2020
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | 08W | NV | Pending | ECES_CA2/PEND | 10/26/2020 | 09/23/2019 | 11/18/2019 | 09/17/2020 | 09/17/2020 | 09/17/2020 | 09/17/2020 | 10/26/2020 | 10/26/2020 | 10/26/2020 | 10/26/2020
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | 08W | NV | Pending | ECES_CA2/PEND | 10/27/2020 | 09/23/2019 | 11/18/2019 | 10/02/2020 | 10/02/2020 | 10/02/2020 | 10/05/2020 | 10/27/2020 | 10/27/2020 | 10/27/2020 | 10/27/2020
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | 08W | NV | Pending | ECES_CA2/PEND | 11/02/2020 | 09/23/2019 | 11/18/2019 | 10/30/2020 | 10/30/2020 | 10/30/2020 | 11/02/2020 | 11/02/2020 | 12/31/9999
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | 08W | NV | Pending | ECES_CA2/PEND | 10/28/2020 | 09/23/2019 | 11/18/2019 | 08/12/2020 | 08/12/2020 | 08/12/2020 | 08/12/2020 | 10/28/2020 | 12/31/9999 | 10/27/2020 | 10/28/2020
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | 08W | NV | Pending | ECES_CA2/PEND | 10/28/2020 | 09/23/2019 | 11/18/2019 | 09/03/2020 | 09/03/2020 | 09/03/2020 | 09/03/2020 | 10/28/2020 | 12/31/9999 | 10/27/2020 | 10/28/2020
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 | 08W | NV | Pending | ECES_CA2/PEND | 11/14/2020 | 09/23/2019 | 11/18/2019 | 10/15/2020 | 10/15/2020 | 10/15/2020 | 10/19/2020 | 11/14/2020 | 12/31/9999 | 11/13/2020 | 11/14/2020
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | 08W | NV | Pending | ECES_CA2/PEND | 10/27/2020 | 09/23/2019 | 11/18/2019 | 08/31/2020 | 08/31/2020 | 08/31/2020 | 09/08/2020 | 10/27/2020 | 12/31/9999 | 10/26/2020 | 10/27/2020
35129640 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 | 08W | NV | Pending | ECES_CA2/PEND | 11/16/2020 | 09/23/2019 | 11/18/2019 | 11/18/2019 | 06/24/2020 | 06/24/2020 | 06/24/2020 | 11/16/2020 | 11/16/2020 | 11/16/2020 | 11/16/2020
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | 08W | NV | Pending | ECES_CA2/PEND | 09/08/2020 | 09/23/2019 | 11/18/2019 | 09/08/2020 | 09/08/2020 | 09/08/2020 | 09/08/2020 | 09/08/2020 | 12/31/9999
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | 08W | NV | Pending | ECES_CA2/PEND | 10/30/2020 | 09/23/2019 | 11/18/2019 | 10/29/2020 | 10/30/2020 | 10/30/2020 | 10/30/2020 | 10/30/2020 | 12/31/9999
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | 08W | NV | Pending | ECES_CA2/PEND | 09/23/2020 | 09/23/2019 | 11/18/2019 | 09/23/2020 | 09/23/2020 | 09/23/2020 | 09/23/2020 | 09/23/2020 | 09/23/2020
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | 08W | NV | Pending | ECES_CA2/PEND | 12/29/2020 | 09/23/2019 | 11/18/2019 | 11/18/2019 | 07/30/2020 | 07/30/2020 | 07/31/2020 | 12/29/2020 | 12/31/9999 | 12/14/2020 | 12/29/2020
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | 08W | NV | Pending | ECES_CA2/PEND | 08/06/2020 | 09/23/2019 | 11/18/2019 | 08/05/2020 | 08/06/2020 | 08/06/2020 | 08/06/2020 | 08/06/2020 | 12/31/9999
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | 08W | NV | Construction | ECES_CA2/CONS | 10/28/2020 | 09/23/2019 | 11/18/2019 | 07/13/2020 | 07/14/2020 | 07/14/2020 | 07/14/2020 | 07/14/2020 | 10/27/2020 | 10/27/2020 | 10/28/2020 | 10/28/2020 | 12/31/9999
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 | 08W | NV | Design | ECES_CA2/ESTS | 10/16/2020 | 09/23/2019 | 11/18/2019 | 10/16/2020 | 12/31/9999 | 09/30/2020 | 10/16/2020
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | 08W | NV | Design | ECES_CA2/ESTS | 11/18/2019 | 09/23/2019 | 11/18/2019 | 11/18/2019 | 12/31/9999
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | 08W | NV | Design | ECES_CA2/ADER | 11/09/2020 | 09/23/2019 | 11/18/2019 | 10/22/2020 | 11/09/2020 | 11/09/2020 | 12/31/9999
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | 08W | NV | Pending | ECES_CA2/PEND | 09/30/2020 | 09/23/2019 | 11/18/2019 | 09/25/2020 | 09/29/2020 | 09/29/2020 | 09/29/2020 | 09/30/2020 | 12/31/9999
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | 08W | NV | Pending | ECES_CA2/PEND | 11/24/2020 | 09/23/2019 | 11/18/2019 | 10/02/2020 | 10/05/2020 | 10/05/2020 | 10/05/2020 | 11/24/2020 | 12/31/9999 | 11/23/2020 | 11/24/2020
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 | 08W | NV | Pending | ECES_CA2/PEND | 11/04/2020 | 09/23/2019 | 11/18/2019 | 10/12/2020 | 11/04/2020 | 11/04/2020 | 11/04/2020 | 11/04/2020 | 12/31/9999
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | 08W | NV | Pending | ECES_CA2/PEND | 10/21/2020 | 09/23/2019 | 11/18/2019 | 10/19/2020 | 10/20/2020 | 10/20/2020 | 10/20/2020 | 10/21/2020 | 12/31/9999
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | 08W | NV | Pending | ECES_CA2/PEND | 10/23/2020 | 09/23/2019 | 11/18/2019 | 10/23/2020 | 10/23/2020 | 10/23/2020 | 10/23/2020 | 10/23/2020 | 12/31/9999
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | 08W | NV | Design | ECES_CA2/ADER | 10/29/2020 | 09/23/2019 | 11/18/2019 | 11/18/2019 | 10/29/2020 | 10/29/2020 | 12/31/9999
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | 08W | NV | Design | ECES_CA2/ESTS | 11/18/2019 | 09/23/2019 | 11/18/2019 | 11/18/2019 | 12/31/9999
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | SI | Design | ECES_CA2/ESTS | 02/24/2020 | 09/24/2019 | 02/24/2020 | 02/24/2020 | 12/31/9999
35129944 | SILVERADO 2105 - DIST.UNDERBUILD RECON | 08W | NB | Pre-Construction | ECES_CA2/UNSC | 07/17/2020 | 09/25/2019 | 12/19/2019 | 02/22/2020 | 02/24/2020 | 02/24/2020 | 02/24/2020 | 02/27/2020 | 07/17/2020 | 07/17/2020 | 12/31/9999
35134806 | BR-03-14-W (E) PENTZ RD, PARB | 08W | NV | Estimating Ready | ECES_CA2/UNSE | 05/04/2020 | 05/04/2020 | 12/31/9999 | 10/21/2019 | 05/04/2020
35135005 | MVWF ALTO 1125 MUIR WOOD DR,MUIR BEACH | 08W | NB | Initiation | ECES_CA1/UNSE | 10/22/2019 | 10/22/2019 | 12/31/9999
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | 08W | NV | Construction | ECES_CA2/CONS | 07/21/2020 | 10/29/2019 | 10/29/2019 | 02/07/2020 | 02/07/2020 | 02/07/2020 | 02/07/2020 | 02/10/2020 | 05/20/2020 | 05/20/2020 | 07/21/2020 | 07/21/2020 | 12/31/9999
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | 08W | HB | Design | ECES_CA1/ESTS | 08/04/2020 | 11/06/2019 | 08/04/2020 | 08/04/2020 | 12/31/9999
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | 08W | HB | Design | ECES_CA1/ESTS | 07/23/2020 | 11/06/2019 | 07/23/2020 | 07/23/2020 | 12/31/9999
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | 08W | HB | Design | ECES_CA1/ESTS | 07/30/2020 | 11/06/2019 | 07/30/2020 | 07/30/2020 | 12/31/9999
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | 08W | HB | Initiation | ECES_CA1/UNSE | 11/06/2019 | 11/06/2019 | 12/31/9999
35141419 | BR-03-07-W (E) TIMBER WALK PARB | 08W | NV | Post-Doc | ECES_CA2/FICL | 12/19/2020 | 11/20/2019 | 11/20/2019 | 11/20/2019 | 12/11/2019 | 12/11/2019 | 12/11/2019 | 12/18/2019 | 12/18/2019 | 12/18/2019 | 03/31/2020 | 03/31/2020 | 12/19/2020 | 12/19/2020 | 12/19/2020 |  |  |  |  | 12/19/2020 | 12/31/9999
35141837 | *CANC*BR-04-01-W (E) SUNSET DR PARB | 08W | NV | Other | ECES_CA1/PROD | 12/28/2020 | 11/22/2019 | 12/03/2019 | 12/03/2019 | 12/06/2019 | 12/06/2019 | 12/06/2019 | 12/09/2019 | 12/28/2020 | 12/07/2019 | 12/09/2019
35142198 | BR-03-08-W (E) BELLEVIEW PARB | 08W | NV | Pre-Construction | ECES_CA1/UNSC | 12/18/2019 | 11/26/2019 | 12/03/2019 | 12/03/2019 | 12/11/2019 | 12/11/2019 | 12/11/2019 | 12/18/2019 | 12/18/2019 | 12/18/2019 | 12/31/9999
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | SI | Construction | ECES_CA2/CONS | 09/07/2020 | 12/03/2019 | 12/12/2019 | 06/04/2020 | 06/08/2020 | 06/08/2020 | 06/13/2020 | 06/15/2020 | 07/17/2020 | 07/17/2020 | 09/07/2020 | 09/07/2020 | 12/31/9999
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | SI | Pending | ECES_CA2/PEND | 09/14/2020 | 12/03/2019 | 12/12/2019 | 09/02/2020 | 09/02/2020 | 09/02/2020 | 09/02/2020 | 09/14/2020 | 09/14/2020 | 09/14/2020 | 09/14/2020
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | SI | Construction | ECES_CA2/CONS | 10/26/2020 | 12/03/2019 | 12/12/2019 | 07/20/2020 | 07/22/2020 | 07/22/2020 | 07/22/2020 | 07/28/2020 | 08/22/2020 | 08/22/2020 | 10/26/2020 | 10/26/2020 | 12/31/9999
35144588 | PSPS MITIGATION - ROSSMOOR 1106 | 08W | DI | Initiation | ECES_CA1/UNSE | 12/09/2019 | 12/09/2019 | 12/31/9999
35144589 | PSPS MITIGATION - MORAGA 1103 | 08W | DI | Initiation | ECES_CA1/UNSE | 12/09/2019 | 12/09/2019 | 12/31/9999
35144591 | PSPS MITIGATION - STAFFORD 1101 - PH1 | 08W | NB | Initiation | ECES_CA1/UNSE | 12/09/2019 | 12/09/2019 | 12/31/9999
35144592 | PSPS MITIGATION - STAFFORD 1101 - PH2 | 08W | NB | Initiation | ECES_CA1/UNSE | 12/09/2019 | 12/09/2019 | 12/31/9999
35144940 | *CANC* PSPS - HICKS 2101 – CB | 08W | SJ | Completion | ECES_CA2/CLSD | 09/03/2020 | 12/11/2019 | 03/13/2020 | 03/18/2020 | 03/24/2020 | 03/18/2020 | 03/18/2020 | [6 empty] | 03/24/2020 | 04/01/2020 | 04/01/2020 | 08/12/2020 |  |  |  |  | 09/03/2020 | 12/31/9999 | 08/18/2020 | 09/03/2020
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | 08W | CC | Pending | ECES_CA2/PEND | 12/15/2020 | 04/09/2020 | 05/18/2020 | 12/09/2020 | 12/15/2020 | 12/15/2020 | 12/15/2020 | 12/15/2020 | 12/31/9999
35144942 | *CANC* PSPS - PAUL SWEET 2105 - CB | 08W | CC | Completion | ECES_CA2/CLSD | 09/03/2020 | 12/11/2019 | 03/24/2020 | [12 empty] | 03/24/2020 | 08/06/2020 |  |  |  |  | 09/03/2020 | 12/31/9999 | 08/06/2020 | 09/03/2020
35144943 | PSPS - ROB ROY 2105 - CB | 08W | CC | Pending | ECES_CA2/PEND | 11/16/2020 | 12/11/2019 | 07/02/2020 | 11/06/2020 | 11/16/2020 | 11/16/2020 | 11/16/2020 | 11/16/2020 | 12/31/9999
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | 08W | PN | Pending | ECES_CA1/PEND | 05/29/2020 | 12/11/2019 | 03/20/2020 | 05/21/2020 | 05/26/2020 | 05/26/2020 | 05/26/2020 | 05/29/2020 | 12/31/9999 |  |  |  |  | 04/28/2020 | 04/28/2020 | 04/28/2020 | 05/07/2020
35145001 | PSPS - CLAYTON 2215 - CB | 08W | DI | Pending | ECES_CA2/PEND | 10/16/2020 | 12/12/2019 | 03/03/2020 | 10/12/2020 | 10/14/2020 | 10/14/2020 | 10/14/2020 | 10/16/2020 | 12/31/9999
35145002 | PSPS - IGNACIO 1101 - CB | 08W | NB | Pending | ECES_CA2/PEND | 11/02/2020 | 12/12/2019 | 01/17/2020 | 11/02/2020 | 11/02/2020 | 11/02/2020 | 11/02/2020 | 11/02/2020 | 12/31/9999
35145003 | PSPS CWSP - MORAGA 1103 - CB | 08W | DI | Pre-Construction | ECES_CA2/UNSC | 12/10/2020 | 12/12/2019 | 03/09/2020 | 05/26/2020 | 05/27/2020 | 05/27/2020 | 06/01/2020 | 06/03/2020 | 12/10/2020 | 12/10/2020 | 12/31/9999
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | 08W | DI | Pending | ECES_CA2/PEND | 07/13/2020 | 12/12/2019 | 02/25/2020 | 07/04/2020 | 07/13/2020 | 07/13/2020 | 07/13/2020 | 07/13/2020 | 12/31/9999
35145005 | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 | 08W | NB | Documentation | ECES_CA2/DOCC | 05/26/2020 | 12/12/2019 | 03/27/2020 | 03/27/2020 | 05/26/2020 | [8 empty] | 05/26/2020 | 12/31/9999
35145006 | PSPS - STAFFORD 1101 LR 1298 | 08W | NB | Pending | ECES_CA2/PEND | 12/14/2020 | 12/12/2019 | 05/21/2020 | 05/21/2020 | 12/11/2020 | 12/11/2020 | 12/11/2020 | 12/14/2020 | 12/31/9999
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | SI | Pending | ECES_CA2/PEND | 12/21/2020 | 12/13/2019 | 05/05/2020 | 05/05/2020 | 06/11/2020 | 06/11/2020 | 06/12/2020 | 12/21/2020 | 12/31/9999 | 12/17/2020 | 12/21/2020
35145523 | *CANC* PSPS - FULTON 1102 HARDENING | 08W | SO | Completion | ECES_CA2/CLSD | 09/03/2020 | 12/13/2019 | 02/06/2020 | 02/06/2020 | 05/26/2020 | [8 empty] | 05/26/2020 | 08/18/2020 | [6 empty] | 09/03/2020 | 12/31/9999 | 08/18/2020 | 09/03/2020
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | 08W | SO | Pending | ECES_CA2/PEND | 11/02/2020 | 12/13/2019 | 03/07/2020 | 11/02/2020 | 11/02/2020 | 11/02/2020 | 11/02/2020 | 11/02/2020 | 12/31/9999
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | 08W | SO | Pending | ECES_CA2/PEND | 10/25/2020 | 12/13/2019 | 04/16/2020 | 10/21/2020 | 10/21/2020 | 10/21/2020 | 10/21/2020 | 10/25/2020 | 12/31/9999
35145540 | PSPS - FROGTOWN 1702 - CB | 08W | ST | Pending | ECES_CA2/PEND | 09/02/2020 | 12/13/2019 | 02/10/2020 | 02/10/2020 | 08/19/2020 | 08/19/2020 | 08/19/2020 | 09/02/2020 | 09/02/2020
35147045 | *CANC* *DO NOT USE* PSPS - CASTRO V*CANC | 08W | MI | Completion | ECES_CA1/CLSD | 10/03/2020 | 12/30/2019 | 03/31/2020 | 03/31/2020 | 04/21/2020 | [8 empty] | 08/17/2020 | 08/17/2020 | 04/21/2020 | 08/17/2020 |  |  |  |  | 10/03/2020 | 12/31/9999 | 09/03/2020 | 10/03/2020
35148272 | CREATED IN ERROR | 08W | YO | Initiation | ECES_CA2/UNSE | 01/09/2020 | 01/09/2020 | 12/31/9999
35155680 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.02 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155681 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.03 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155682 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.04 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155683 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.05 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155684 | CWSP-BRUNSWICK 1105 LR2140 - PH 1.06 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155685 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.07 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155686 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.08 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155687 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.09 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155688 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.10 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155689 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.11 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155690 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.12 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155691 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.13 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155692 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.14 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155693 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.15 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155694 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.16 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155695 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.02 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155696 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.03 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155697 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.04 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155698 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.05 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155699 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.06 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155740 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.07 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155741 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.08 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155742 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.09 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155743 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.10 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155744 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.11 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155746 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.12 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155747 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.13 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155748 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.14 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155749 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.15 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155750 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.16 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155751 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.17 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155752 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.02 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155753 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.03 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155754 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.04 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155755 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.05 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155756 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.06 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155757 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.07 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155758 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.08 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155759 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.09 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155840 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.10 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155841 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.11 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35155842 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.12 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/07/2020 | 02/07/2020 | 12/31/9999
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | 08W | NB | Construction | ECES_CA1/CONS | 07/27/2020 | 02/20/2020 | 02/20/2020 | 02/20/2020 | 03/12/2020 | 03/12/2020 | 03/12/2020 | 06/30/2020 | 07/01/2020 | 07/01/2020 | 07/27/2020 | 07/27/2020 | 12/31/9999
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | 08W | SI | Design | ECES_CA2/ADER | 11/02/2020 | 02/26/2020 | 08/10/2020 | 11/02/2020 | 11/02/2020 | 11/02/2020 | 11/02/2020
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | 08W | SI | Design | ECES_CA2/ADER | 11/02/2020 | 03/06/2020 | 08/10/2020 | 08/10/2020 | 11/02/2020 | 11/02/2020 | 12/31/9999
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | 08W | SI | Design | ECES_CA2/ESTS | 08/10/2020 | 03/06/2020 | 08/10/2020 | 08/10/2020 | 12/31/9999
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 | 08W | SI | Design | ECES_CA2/ESTS | 08/10/2020 | 03/06/2020 | 08/10/2020 | 08/10/2020 | 12/31/9999
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | 08W | SI | Design | ECES_CA2/ESTS | 08/10/2020 | 03/06/2020 | 08/10/2020 | 08/10/2020 | 12/31/9999
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 | 08W | SI | Design | ECES_CA2/ESTS | 08/10/2020 | 03/06/2020 | 08/10/2020 | 08/10/2020 | 12/31/9999
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 | 08W | SI | Design | ECES_CA2/ADER | 11/02/2020 | 03/06/2020 | 08/10/2020 | 08/10/2020 | 11/02/2020 | 11/02/2020 | 12/31/9999
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 | 08W | SI | Design | ECES_CA2/ESTS | 08/10/2020 | 03/06/2020 | 08/10/2020 | 08/10/2020 | 12/31/9999
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 | 08W | SI | Design | ECES_CA2/ESTS | 08/10/2020 | 03/06/2020 | 08/10/2020 | 08/10/2020 | 12/31/9999
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 | 08W | SI | Design | ECES_CA2/ESTS | 08/11/2020 | 03/06/2020 | 08/11/2020 | 08/11/2020 | 12/31/9999
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 | 08W | SI | Design | ECES_CA2/ESTS | 08/10/2020 | 03/06/2020 | 08/10/2020 | 08/10/2020 | 12/31/9999
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 | 08W | SI | Design | ECES_CA2/ESTS | 08/10/2020 | 03/06/2020 | 08/10/2020 | 08/10/2020 | 12/31/9999
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 | 08W | SI | Design | ECES_CA2/ESTS | 08/11/2020 | 03/06/2020 | 08/11/2020 | 08/11/2020 | 12/31/9999
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 | 08W | SI | Design | ECES_CA2/ESTS | 08/10/2020 | 03/06/2020 | 08/10/2020 | 08/10/2020 | 12/31/9999
35161152 | OCT2019 BRICEBURG FIRE REBUILD | 08W | YO | Pre-Construction | ECES_CA2/UNSC | 12/11/2020 | 03/10/2020 | 07/14/2020 | 07/14/2020 | 09/23/2020 | 09/23/2020 | 09/23/2020 | 10/30/2020 | 12/11/2020 | 12/11/2020 | 12/31/9999
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | SI | Design | ECES_CA1/ESTS | 08/10/2020 | 03/25/2020 | 08/10/2020 | 08/10/2020 | 12/31/9999
35167137 | CANCEL DUPLICATE ORDER | 08W | SI | Initiation | ECES_CA1/UNSE | 03/25/2020 | 03/25/2020 | 12/31/9999
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | SI | Design | ECES_CA2/ESTS | 09/08/2020 | 03/25/2020 | 09/08/2020 | 09/08/2020 | 12/31/9999
35168820 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.4 | 08W | SI | Design | ECES_CA1/ESTS | 08/10/2020 | 03/25/2020 | 08/10/2020 | 08/10/2020 | 12/31/9999
35168821 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.5 | 08W | SI | Design | ECES_CA1/ESTS | 08/10/2020 | 03/25/2020 | 08/10/2020 | 08/10/2020 | 12/31/9999
35168822 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.6 | 08W | SI | Design | ECES_CA1/ESTS | 08/10/2020 | 03/25/2020 | 08/10/2020 | 08/10/2020 | 12/31/9999
35168823 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.7 | 08W | SI | Design | ECES_CA1/ESTS | 08/10/2020 | 03/25/2020 | 08/10/2020 | 08/10/2020 | 12/31/9999
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 | 08W | NV | Design | ECES_CA2/ESTS | 08/05/2020 | 04/03/2020 | 08/05/2020 | 08/05/2020 | 12/31/9999
35171354 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | 08W | CC | Completion | ECES_CA1/CLSD | 12/19/2020 | 04/09/2020 | 04/09/2020 | 05/14/2020 | 05/14/2020 | 05/14/2020 | 05/14/2020 | 05/14/2020 | 06/11/2020 | 06/11/2020 | 07/21/2020 |  |  | 07/21/2020 | 07/22/2020 |  |  | 07/22/2020 | 07/24/2020 | 07/24/2020 | 12/17/2020 | 12/19/2020 | 12/31/9999
35171705 | BR-03-12-W (E) PENTZ RD SRTS PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 04/10/2020 | 04/10/2020 | 12/31/9999
35172093 | *CANC* EL DORADO PH 2102 LR19542 P*CANC | 08W | SI | Completion | ECES_CA1/CLSD | 05/03/2020 | 04/17/2020 | 04/28/2020 | [18 empty] | 05/03/2020 | 12/31/9999 | 04/28/2020 | 05/03/2020
35172094 | CWSP-EL DORADO PH 2102 LR19542 PH 1*CANC | 08W | SI | Completion | ECES_CA1/CLSD | 05/03/2020 | 04/17/2020 | 04/28/2020 | [18 empty] | 05/03/2020 | 12/31/9999 | 04/28/2020 | 05/03/2020
35172521 | *CANC* EL DORADO PH 2102 LR19542 P*CANC | 08W | SI | Completion | ECES_CA1/CLSD | 05/03/2020 | 04/17/2020 | 04/28/2020 | [18 empty] | 05/03/2020 | 12/31/9999 | 04/28/2020 | 05/03/2020
35172522 | *CANC* CWSP-EL DORADO PH 2102 LR195*CANC | 08W | SI | Completion | ECES_CA1/CLSD | 05/03/2020 | 04/17/2020 | 04/28/2020 | [18 empty] | 05/03/2020 | 12/31/9999 | 04/28/2020 | 05/03/2020
35173253 | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 | 08W | SI | Initiation | ECES_CA2/UNSE | 04/20/2020 | 04/20/2020 | 12/31/9999
35173255 | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 | 08W | SI | Initiation | ECES_CA2/UNSE | 04/20/2020 | 04/20/2020 | 12/31/9999
35173320 | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 | 08W | SI | Initiation | ECES_CA2/UNSE | 04/20/2020 | 04/20/2020 | 12/31/9999
35173321 | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 | 08W | SI | Initiation | ECES_CA2/UNSE | 04/20/2020 | 04/20/2020 | 12/31/9999
35173387 | BR-09-01-W (E) SKYWAY PH3 20A PARB | 08W | NV | Design | ECES_CA2/ESTS | 04/21/2020 | 04/21/2020 | 04/21/2020 | 04/21/2020 | 12/31/9999
35173754 | ECOP-BRUNSWICK 1106-H08-LR51486 | 08W | SI | Initiation | ECES_CA2/UNSE | 04/22/2020 | 04/22/2020 | 12/31/9999
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | 08W | ST | Design | ECES_CA2/ESTS | 07/20/2020 | 04/22/2020 | 07/20/2020 | 07/20/2020 | 12/31/9999
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | SI | Initiation | ECES_CA2/UNSE | 04/22/2020 | 04/22/2020 | 12/31/9999
35173959 | CWSP-MIWUK 1702-LR 38218-PH 1.6 | 08W | YO | Design | ECES_CA2/ESTS | 11/12/2020 | 04/23/2020 | 04/27/2020 | 11/12/2020 | 12/31/9999 | 10/28/2020 | 11/12/2020
35174085 | PSPS - FIA320 - LR @ 101269978 | 08W | ST | Pre-Construction | ECES_CA1/UNSC | 08/04/2020 | 04/23/2020 | 04/23/2020 | 05/07/2020 | 05/07/2020 | 05/07/2020 | 05/07/2020 | 05/11/2020 | 08/04/2020 | 08/04/2020 | 12/31/9999
35174174 | ECOP-STANISLAUS 1702-H03-LR1850 | 08W | ST | Initiation | ECES_CA2/UNSE | 04/24/2020 | 04/24/2020 | 12/31/9999
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | SI | Initiation | ECES_CA2/UNSE | 04/27/2020 | 04/27/2020 | 12/31/9999
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | SI | Initiation | ECES_CA2/UNSE | 04/27/2020 | 04/27/2020 | 12/31/9999
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | 08W | ST | Design | ECES_CA2/ESTS | 09/30/2020 | 04/27/2020 | 09/30/2020 | 09/30/2020 | 12/31/9999
35174468 | ECOP-STANISLAUS 1702-H01-LR37276-PH2 | 08W | ST | Design | ECES_CA2/ESTS | 09/30/2020 | 04/27/2020 | 09/30/2020 | 09/30/2020 | 12/31/9999
35174469 | ECOP-PINE GROVE 1102-H01-LR45292 | 08W | ST | Design | ECES_CA2/ESTS | 09/30/2020 | 04/27/2020 | 09/30/2020 | 09/30/2020 | 12/31/9999
35174470 | ECOP-MOLINO 1102-H01-LR318 | 08W | SO | Initiation | ECES_CA2/UNSE | 04/27/2020 | 04/27/2020 | 12/31/9999
35174471 | ECOP-MONTE RIO 1113-H07-LR180 | 08W | SO | Initiation | ECES_CA2/UNSE | 04/27/2020 | 04/27/2020 | 12/31/9999
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | 08W | NB | Initiation | ECES_CA2/UNSE | 04/27/2020 | 04/27/2020 | 12/31/9999
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | 08W | NB | Initiation | ECES_CA2/UNSE | 04/27/2020 | 04/27/2020 | 12/31/9999
35174474 | ECOP-CALISTOGA 1101-H01-LR736 PH1 | 08W | NB | Initiation | ECES_CA2/UNSE | 04/27/2020 | 04/27/2020 | 12/31/9999
35174475 | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 | 08W | NB | Initiation | ECES_CA2/UNSE | 04/27/2020 | 04/27/2020 | 12/31/9999
35174476 | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 | 08W | SO | Initiation | ECES_CA2/UNSE | 04/27/2020 | 04/27/2020 | 12/31/9999
35174477 | ECOP-CALISTOGA 1101-H01-LR736-PH3 | 08W | NB | Initiation | ECES_CA2/UNSE | 04/27/2020 | 04/27/2020 | 12/31/9999
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1 | 08W | HB | Initiation | ECES_CA2/UNSE | 04/27/2020 | 04/27/2020 | 12/31/9999
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2 | 08W | HB | Initiation | ECES_CA2/UNSE | 04/27/2020 | 04/27/2020 | 12/31/9999
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3 | 08W | HB | Initiation | ECES_CA2/UNSE | 04/27/2020 | 04/27/2020 | 12/31/9999
35174993 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.2 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/01/2020 | 05/01/2020 | 12/31/9999
35175131 | *CANC* - PLACERVILLE 2106 - LR1104 - PH2 | 08W | SI | Completion | ECES_CA2/CLSD | 06/03/2020 | 05/01/2020 | 05/16/2020 | [18 empty] | 06/03/2020 | 12/31/9999 | 05/16/2020 | 06/03/2020
35175132 | *CANC* - PLACERVILLE 2106 - LR1104 - PH | 08W | SI | Other | ECES_CA2/CNCL | 05/16/2020 | 05/01/2020 | 05/16/2020 | [20 empty] | 05/16/2020 | 12/31/9999
35175549 | BR-05-07-W (E) HIGH SCHOOL MAXWELL PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 05/04/2020 | 05/04/2020 | 12/31/9999
35175843 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.2 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/05/2020 | 05/05/2020 | 12/31/9999
35175844 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.3 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/05/2020 | 05/05/2020 | 12/31/9999
35175845 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.4 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/05/2020 | 05/05/2020 | 12/31/9999
35175846 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.5 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/05/2020 | 05/05/2020 | 12/31/9999
35175847 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/05/2020 | 05/05/2020 | 12/31/9999
35175848 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.3 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/05/2020 | 05/05/2020 | 12/31/9999
35175849 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.4 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/05/2020 | 05/05/2020 | 12/31/9999
35175850 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.5 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/05/2020 | 05/05/2020 | 12/31/9999
35175852 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.2 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/05/2020 | 05/05/2020 | 12/31/9999
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/05/2020 | 05/05/2020 | 12/31/9999
35175854 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.4 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/05/2020 | 05/05/2020 | 12/31/9999
35175855 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.5 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/05/2020 | 05/05/2020 | 12/31/9999
35175856 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/05/2020 | 05/05/2020 | 12/31/9999
35175857 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.3 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/05/2020 | 05/05/2020 | 12/31/9999
35175858 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.4 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/05/2020 | 05/05/2020 | 12/31/9999
35175859 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.5 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/05/2020 | 05/05/2020 | 12/31/9999
35176209 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.3 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/07/2020 | 05/07/2020 | 12/31/9999
35176210 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.4 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/07/2020 | 05/07/2020 | 12/31/9999
35176211 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.5 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/07/2020 | 05/07/2020 | 12/31/9999
35176497 | ECOP-STANISLAUS 1702-H03-LR1850 | 08W | ST | Initiation | ECES_CA1/UNSE | 05/11/2020 | 05/11/2020 | 12/31/9999
35176549 | ECOP-MONTE RIO 1113-H07-LR180 | 08W | SO | Initiation | ECES_CA1/UNSE | 05/12/2020 | 05/12/2020 | 12/31/9999
35177107 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.6 | 08W | SI | Initiation | ECES_CA1/UNSE | 05/13/2020 | 05/13/2020 | 12/31/9999
35177108 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.7 | 08W | SI | Initiation | ECES_CA1/UNSE | 05/13/2020 | 05/13/2020 | 12/31/9999
35177109 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.6 | 08W | SI | Initiation | ECES_CA1/UNSE | 05/13/2020 | 05/13/2020 | 12/31/9999
35177110 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.7 | 08W | SI | Initiation | ECES_CA1/UNSE | 05/13/2020 | 05/13/2020 | 12/31/9999
35177111 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.8 | 08W | SI | Initiation | ECES_CA2/UNSE | 05/13/2020 | 05/13/2020 | 12/31/9999
35179069 | BUCOCAMPTUG WILDWOOD LN PARADISE | 08W | NV | Post-Doc | ECES_CA1/FICL | 10/28/2020 | 08/21/2020 | 10/09/2020 | 07/21/2020 | 07/21/2020 | 07/21/2020 | 07/21/2020 | 07/22/2020 | 08/21/2020 | 07/22/2020 | 07/22/2020 |  |  | 10/09/2020 | 10/14/2020 |  |  | 10/14/2020 | 10/28/2020 | 10/28/2020 | 12/31/9999
35179328 | BUCOCAMPTUG SUN RIVER CT PARADISE | 08W | NV | Documentation | ECES_CA1/DOCC | 01/26/2021 | 05/28/2020 | 10/06/2020 | 10/06/2020 | 10/18/2020 | 10/18/2020 | 10/18/2020 | 10/20/2020 | 11/05/2020 | 11/05/2020 | 11/06/2020 | 11/06/2020 | 01/26/2021 | 01/26/2021 | 12/31/9999
35180088 | BUCOCAMPTUG 5507 ROCKFORD LN PARADISE | 08W | NV | Documentation | ECES_CA1/DOCC | 01/26/2021 | 06/03/2020 | 09/04/2020 | 09/04/2020 | 10/04/2020 | 10/04/2020 | 10/04/2020 | 10/04/2020 | 10/23/2020 | 10/23/2020 | 11/06/2020 | 11/06/2020 | 01/26/2021 | 01/26/2021 | 12/31/9999
35181199 | ECOP-WEST POINT 1101-H03-TS L373 | 08W | ST | Design | ECES_CA2/ESTS | 09/30/2020 | 06/10/2020 | 09/30/2020 | 09/30/2020 | 12/31/9999
35181318 | BUCOCAMPTUG 6650 WHITTALL LN PARADISE | 08W | NV | Documentation | ECES_CA1/DOCC | 01/26/2021 | 06/10/2020 | 07/27/2020 | 09/14/2020 | 09/14/2020 | 09/14/2020 | 09/14/2020 | 09/15/2020 | 10/23/2020 | 10/23/2020 | 10/23/2020 | 10/23/2020 | 01/26/2021 | 01/26/2021 | 12/31/9999
35181319 | BUCOCAMPTUG STINSON LN PARADISE | 08W | NV | Documentation | ECES_CA1/DOCC | 12/03/2020 | 06/10/2020 | 07/27/2020 | 07/27/2020 | 08/26/2020 | 08/26/2020 | 08/26/2020 | 08/26/2020 | 08/26/2020 | 08/26/2020 | 08/27/2020 | 08/27/2020 | 12/03/2020 | 12/03/2020 | 12/31/9999
35181576 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH1 | 08W | NV | Initiation | ECES_CA2/UNSE | 06/12/2020 | 06/12/2020 | 12/31/9999
35181924 | BUCOCAMPTUG ROE RD/WILSON LN PARADISE | 08W | NV | Post-Doc | ECES_CA1/FICL | 12/04/2020 | 06/15/2020 | 06/15/2020 | 06/15/2020 | 06/16/2020 | 06/16/2020 | 06/16/2020 | 06/17/2020 | 06/17/2020 | 06/17/2020 | 07/02/2020 | 07/02/2020 | 11/18/2020 | 11/18/2020 | 11/20/2020 |  |  | 11/20/2020 | 12/04/2020 | 12/04/2020 | 12/31/9999
35181939 | WD RECONDUCTORING ON WYANDOTTE 1103 | 08W | NV | Initiation | ECES_CA2/UNSE | 06/16/2020 | 06/16/2020 | 12/31/9999
35185714 | WDDB - OTTER 1102 - LR 2002 | 08W | CC | Initiation | ECES_CA2/UNSE | 07/09/2020 | 07/09/2020 | 12/31/9999
35191130 | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 | 08W | NB | Initiation | ECES_CA2/UNSE | 08/03/2020 | 08/03/2020 | 12/31/9999
35191311 | ECOP - MONTE RIO 1113 - H06-LR8299 | 08W | SO | Initiation | ECES_CA1/UNSE | 08/04/2020 | 08/04/2020 | 12/31/9999
35191313 | ECOP - MONTE RIO 1113 - H06-LR8299 | 08W | SO | Initiation | ECES_CA1/UNSE | 08/04/2020 | 08/04/2020 | 12/31/9999
35191316 | ECOP - OAKHURST 1103 - H01-LR10190 | 08W | YO | Initiation | ECES_CA1/UNSE | 08/04/2020 | 08/04/2020 | 12/31/9999
35191317 | ECOP - BRUNSWICK 1106 - H03 - LR4639 | 08W | SI | Initiation | ECES_CA1/UNSE | 08/04/2020 | 08/04/2020 | 12/31/9999
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | 08W | NB | Design | ECES_CA1/ESTS | 02/11/2021 | 08/04/2020 | 02/11/2021 | 02/11/2021 | 12/31/9999
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | 08W | NB | Initiation | ECES_CA1/UNSE | 08/04/2020 | 08/04/2020 | 12/31/9999
35191380 | ECOP - MIWUK 1702 - H02-LR9270 | 08W | YO | Initiation | ECES_CA1/UNSE | 08/04/2020 | 08/04/2020 | 12/31/9999
35191381 | ECOP - MIWUK 1702 - H03-LR9270 | 08W | YO | Initiation | ECES_CA1/UNSE | 08/04/2020 | 08/04/2020 | 12/31/9999
35191382 | ECOP - MORAGA 1105 - H01-CB | 08W | DI | Initiation | ECES_CA1/UNSE | 08/04/2020 | 08/04/2020 | 12/31/9999
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | 08W | NB | Design | ECES_CA1/ESTS | 01/15/2021 | 08/04/2020 | 01/15/2021 | 01/15/2021 | 12/31/9999
35191553 | BR-13-01-W (E) LIGHTFOOT WAY PARB | 08W | NV | Design | ECES_CA2/ESTS | 08/05/2020 | 08/05/2020 | 08/05/2020 | 08/05/2020 | 12/31/9999
35191930 | ECOP - WOODACRE 1101 - H01-LR404 PH1 | 08W | NB | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35191934 | ECOP - WOODACRE 1101 - H01-LR404 PH2 | 08W | NB | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35191937 | ECOP - PUEBLO 2102 - H01-LR792 | 08W | NB | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 | 08W | NB | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192025 | ECOP - FORESTHILL 1101 - H02-LR1802 PH1 | 08W | SI | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192028 | ECOP - FORESTHILL 1101 - H02-LR1802 PH2 | 08W | SI | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192029 | ECOP - FORESTHILL 1101 - H02-LR1802 PH3 | 08W | SI | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192031 | ECOP - COLUMBIA HILL 1101 - H01-LR35424 | 08W | SI | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 | 08W | SI | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192035 | ECOP - MIRABEL 1101 - H01-LR298 | 08W | SO | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192036 | ECOP - RINCON 1103 - H01-LR474 | 08W | SO | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192037 | ECOP - SILVERADO 2105 - H01-LR1421 | 08W | NB | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192039 | ECOP - MONTE RIO 1113 - H04-LR320 | 08W | SO | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192040 | ECOP - MONTE RIO 1113 - H08-LR477 | 08W | SO | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192041 | ECOP - WEST POINT 1101 - H01-LR4706 | 08W | ST | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192043 | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 | 08W | ST | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192044 | ECOP - PINE GROVE 1102 - H03-LR13438 PH2 | 08W | ST | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192045 | ECOP - STANISLAUS 1702 - H02-LR75348 | 08W | ST | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192046 | ECOP - PINE GROVE 1102 - H04-LR3172 PH1 | 08W | ST | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192047 | ECOP - PINE GROVE 1102 - H04-LR3172 PH2 | 08W | ST | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192048 | ECOP - PINE GROVE 1102 - H04-LR3172 PH3 | 08W | ST | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192049 | ECOP - PINE GROVE 1102 - H04-LR3172 PH4 | 08W | ST | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192050 | ECOP - WEST POINT 1102 - H01-TS1303 | 08W | ST | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192051 | ECOP - SALT SPRINGS 2102 - H01-LR4796 | 08W | ST | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192052 | ECOP - WEST POINT 1102 - H05-LR34416 | 08W | ST | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | 08W | YO | Construction | ECES_CA2/CONS | 02/12/2021 | 08/07/2020 | 01/22/2021 | 01/22/2021 | 01/23/2021 | 01/23/2021 | 01/23/2021 | 01/25/2021 | 02/01/2021 | 02/01/2021 | 02/12/2021 | 02/12/2021 | 12/31/9999
35192054 | ECOP-OAKHURST 1103-LR 5470 | 08W | YO | Initiation | ECES_CA2/UNSE | 08/07/2020 | 08/07/2020 | 12/31/9999
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | 08W | DI | Design | ECES_CA2/ESTS | 02/02/2021 | 01/07/2021 | 02/02/2021 | 02/02/2021 | 12/31/9999
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | 08W | HB | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | 08W | HB | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192283 | ECOP - CALISTOGA 1101 - H04-LR1087 | 08W | NB | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | 08W | NB | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 | 08W | SI | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 | 08W | SI | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB | 08W | SI | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 | 08W | SI | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 | 08W | SI | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | 08W | SI | Design | ECES_CA2/ESTS | 02/11/2021 | 08/09/2020 | 02/11/2021 | 02/11/2021 | 12/31/9999
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | 08W | SI | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | 08W | SO | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192293 | ECOP - MOLINO 1102 - H03-LR396 PH1 | 08W | SO | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192294 | ECOP - MOLINO 1102 - H03-LR396 PH2 | 08W | SO | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192295 | ECOP - RINCON 1103 - H02-LR198 | 08W | SO | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192296 | ECOP - PINE GROVE 1102 - H06-LR83098 | 08W | ST | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192297 | ECOP - PINE GROVE 1102 - H07-CB | 08W | ST | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192298 | ECOP - SALT SPRINGS 2102 - H02-LR37300 | 08W | ST | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192299 | ECOP - SALT SPRINGS 2102 - H04-LR97924 | 08W | ST | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192300 | ECOP - WEST POINT 1101 - H04-TSL3355 | 08W | ST | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192301 | ECOP - WEST POINT 1102 - H06-LR36676 | 08W | ST | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192302 | ECOP - WEST POINT 1102 - H07-LR93116 | 08W | ST | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192303 | ECOP - MARIPOSA 2101 - H01-LR10170 PH1 | 08W | YO | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192304 | ECOP - MARIPOSA 2101 - H01-LR10170 PH2 | 08W | YO | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192305 | ECOP - MIWUK 1702 - H01-LR8130 | 08W | YO | Initiation | ECES_CA2/UNSE | 08/09/2020 | 08/09/2020 | 12/31/9999
35192683 | BR-05-15-W CLARK-5 PARB | 08W | NV | Design | ECES_CA2/ESTS | 08/11/2020 | 08/11/2020 | 08/11/2020 | 08/11/2020 | 12/31/9999
35193883 | BUCOCAMPTUG 622 PEARSON RD PARADISE | 08W | NV | Construction | ECES_CA1/CONS | 12/04/2020 | 08/19/2020 | 08/20/2020 | 08/20/2020 | 10/09/2020 | 10/09/2020 | 10/10/2020 | 10/14/2020 | 10/22/2020 | 10/22/2020 | 12/04/2020 | 12/04/2020 | 12/31/9999
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | 08W | ST | Design | ECES_CA2/ESTS | 09/10/2020 | 09/10/2020 | 09/10/2020 | 09/10/2020 | 12/31/9999
35200008 | BUCOCAMPTUG MOORE RD PARADISE UG SHORT | 08W | NV | Construction | ECES_CA1/CONS | 02/12/2021 | 09/14/2020 | 11/24/2020 | 11/24/2020 | 12/23/2020 | 12/23/2020 | 12/28/2020 | 01/03/2021 | 02/09/2021 | 02/09/2021 | 02/12/2021 | 02/12/2021 | 12/31/9999
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 | 08W | SI | Initiation | ECES_CA2/UNSE | 09/15/2020 | 09/15/2020 | 12/31/9999
35206134 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.2 | 08W | CC | Initiation | ECES_CA2/UNSE | 10/13/2020 | 10/13/2020 | 12/31/9999
35206135 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.3 | 08W | CC | Initiation | ECES_CA2/UNSE | 10/13/2020 | 10/13/2020 | 12/31/9999
35206136 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.4 | 08W | CC | Initiation | ECES_CA2/UNSE | 10/13/2020 | 10/13/2020 | 12/31/9999
35206138 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.5 | 08W | CC | Initiation | ECES_CA2/UNSE | 10/13/2020 | 10/13/2020 | 12/31/9999
35212401 | FRRB - MONTICELLO 1101 CB | 08W | NB | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212402 | FRRB - MONTICELLO 1101 LR 666 | 08W | NB | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212403 | FRRB - MONTICELLO 1101 LR 654 | 08W | NB | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212404 | FRRB - MONTICELLO 1101 LR 630 | 08W | NB | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212405 | FRRB - MONTICELLO 1101 LR 93384 | 08W | NB | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212406 | FRRB - MONTICELLO 1101 LR 37384 | 08W | NB | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212407 | FRRB - SILVERADO 2102 LR 636 | 08W | NB | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212408 | FRRB - SILVERADO 2102 LR 34959 | 08W | NB | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212409 | FRRB - SILVERADO 2104 LR 645 | 08W | NB | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212410 | FRRB - SILVERADO 2104 LR 708 | 08W | NB | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212411 | FRRB - SILVERADO 2104 LR 722 | 08W | NB | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212412 | FRRB - SILVERADO 2104 LR 37632 | 08W | NB | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212413 | FRRB - SILVERADO 2105 LR 658898 | 08W | NB | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212414 | FRRB - SILVERADO 2105 LR 131568 | 08W | NB | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212415 | FRRB - SILVERADO 2105 LR 167360 | 08W | NB | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212416 | FRRB - CALISTOGA 1102 LR 634 | 08W | NB | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212417 | FRRB - CALISTOGA 1102 LR 769230 | 08W | NB | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | 08W | SO | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212419 | FRRB - DUNBAR 1101 - LR 416 | 08W | SO | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212460 | FRRB - RINCON 1101 LR 14605 | 08W | SO | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212461 | FRRB - RINCON 1101 LR 663641 | 08W | SO | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212462 | FRRB - RINCON 1103 LR 198 | 08W | SO | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212463 | FRRB - RINCON 1103 LR 474 | 08W | SO | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212464 | FRRB - CALISTOGA 1101 LR 886282 | 08W | SO | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212465 | FRRB - VACAVILLE 1108 LR 38316 | 08W | SA | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212466 | FRRB - VACAVILLE 1108 LR 8762 | 08W | SA | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212467 | FRRB - LAURELES 1111 LR 2020 | 08W | CC | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212468 | FRRB - POINT MORETTI 1101 LR36516 | 08W | CC | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212469 | FRRB - POINT MORETTI 1101 LR12122 | 08W | CC | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212470 | FRRB - POINT MORETTI 1101 LR83716 | 08W | CC | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212471 | FRRB - POINT MORETTI 1101 LR5076 | 08W | CC | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212472 | FRRB - BIG BASIN 1102 LR5066 | 08W | CC | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212473 | FRRB - BIG BASIN 1102 LR10254 | 08W | CC | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212474 | FRRB - BIG BASIN 1102 LR12758 | 08W | CC | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212475 | FRRB - BIG BASIN 1101 CB | 08W | CC | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212476 | FRRB - BIG BASIN 1101 LR5000 | 08W | CC | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212477 | FRRB - BIG BASIN 1101 LR10720 | 08W | CC | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212478 | FRRB - SWIFT 2110 XR332 | 08W | SJ | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212479 | FRRB - BIG BEND 1102 CB | 08W | NV | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212480 | FRRB - BIG BEND 1102 LR1972 | 08W | NV | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212481 | FRRB - WYANDOTTE 1103 LR1508 | 08W | NV | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212483 | FRRB - WYANDOTTE 1103 LR1974 | 08W | NV | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212486 | FRRB - KANAKA 1101 CB | 08W | NV | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212487 | FRRB - KANAKA 1101 LR1034 | 08W | NV | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212488 | FRRB - KANAKA 1101 LR1406 | 08W | NV | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212489 | FRRB - GIRVAN 1101 LR1330 | 08W | NV | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212490 | FRRB - GIRVAN 1101 LR323094 | 08W | NV | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | 08W | YO | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212492 | FRRB - AUBERRY 1101 R2845 | 08W | FR | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212493 | FRRB - AUBERRY 1101 R324 | 08W | FR | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212494 | FRRB - AUBERRY 1101 LR37536 | 08W | FR | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212495 | FRRB - AUBERRY 1101 LR233716 | 08W | FR | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35212496 | FRRB - HB TRINITY COUNTY | 08W | HB | Initiation | ECES_CA2/UNSE | 11/08/2020 | 11/08/2020 | 12/31/9999
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | 08W | YO | Design | ECES_CA2/ESTS | 02/10/2021 | 11/23/2020 | 02/10/2021 | 02/10/2021 | 12/31/9999
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | NV | Design | ECES_CA2/ESTS | 02/16/2021 | 11/23/2020 | 02/16/2021 | 02/16/2021 | 12/31/9999
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | 08W | HB | Initiation | ECES_CA2/UNSE | 11/23/2020 | 11/23/2020 | 12/31/9999
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | 08W | HB | Initiation | ECES_CA2/UNSE | 11/23/2020 | 11/23/2020 | 12/31/9999
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | 08W | HB | Initiation | ECES_CA2/UNSE | 11/23/2020 | 11/23/2020 | 12/31/9999
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | NV | Initiation | ECES_CA2/UNSE | 11/23/2020 | 11/23/2020 | 12/31/9999
35217273 | SH - UPPER LAKE 1101 CB | 08W | HB | Initiation | ECES_CA2/UNSE | 11/23/2020 | 11/23/2020 | 12/31/9999
35217274 | FRRB - PN DIVISION SAN MATEO COUNTY | 08W | PN | Initiation | ECES_CA2/UNSE | 11/23/2020 | 11/23/2020 | 12/31/9999
35217275 | FRRB - PN DIVISION SANTA CRUZ COUNTY | 08W | PN | Initiation | ECES_CA2/UNSE | 11/23/2020 | 11/23/2020 | 12/31/9999
35219092 | CWSP - POSO MOUNTAIN 2104CB | 08W | KE | Initiation | ECES_CA2/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219093 | CWSP - TIDEWATER 210614072 | 08W | DI | Initiation | ECES_CA2/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219094 | CNCL CWSP - VACA DIXON 1101126774 | 08W | SA | Initiation | ECES_CA2/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219096 | CWSP - KIRKER 2104442850 | 08W | DI | Initiation | ECES_CA2/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | 08W | YO | Initiation | ECES_CA2/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | 08W | HB | Initiation | ECES_CA2/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219099 | CWSP - HIGHLANDS 1102628 | 08W | HB | Initiation | ECES_CA2/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | NV | Initiation | ECES_CA1/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219264 | CWSP - POSO MOUNTAIN 2103CB | 08W | KE | Initiation | ECES_CA2/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219265 | CWSP - CRESTA 1101546650 | 08W | NV | Initiation | ECES_CA1/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219266 | CWSP - MARIPOSA 2102CB PH 1 | 08W | YO | Design | ECES_CA2/ESTS | 02/11/2021 | 12/09/2020 | 02/11/2021 | 02/11/2021 | 12/31/9999
35219267 | CWSP - MARIPOSA 2102440236 PH1 | 08W | YO | Initiation | ECES_CA2/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219268 | CWSP - MARIPOSA 210197142 PH 1 | 08W | YO | Design | ECES_CA2/ESTS | 02/10/2021 | 12/09/2020 | 02/10/2021 | 02/10/2021 | 12/31/9999
35219269 | CWSP - VACA DIXON 110540092 | 08W | SA | Initiation | ECES_CA2/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219272 | CWSP - MIDDLETOWN 1101481876 | 08W | HB | Initiation | ECES_CA2/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219273 | CWSP - VOLTA 110149742 | 08W | NV | Design | ECES_CA2/ESTS | 02/11/2021 | 12/09/2020 | 02/11/2021 | 02/11/2021 | 12/31/9999
35219275 | CWSP - PUTAH CREEK 110246012 | 08W | SA | Approval | ECES_CA1/APPR | 02/16/2021 | 12/09/2020 | 02/10/2021 | 02/10/2021 | 02/16/2021 | 02/16/2021 | 02/16/2021
35219276 | CWSP - VACAVILLE 11046542 | 08W | SA | Initiation | ECES_CA2/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219279 | CWSP - VACAVILLE 11088762 | 08W | SA | Initiation | ECES_CA1/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | 08W | HB | Initiation | ECES_CA2/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | 08W | SI | Initiation | ECES_CA2/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219282 | CWSP - NORTH DUBLIN 2101 CB | 08W | MI | Initiation | ECES_CA1/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219283 | CWSP - NORTH DUBLIN 2101 CB | 08W | MI | Initiation | ECES_CA1/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | 08W | NV | Initiation | ECES_CA2/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | 08W | NV | Initiation | ECES_CA2/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219289 | CWSP - OREGON TRAIL 110335002 PH1 | 08W | NV | Initiation | ECES_CA2/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219291 | CWSP - VACA DIXON 1101126774 | 08W | SA | Initiation | ECES_CA1/UNSE | 12/09/2020 | 12/09/2020 | 12/31/9999
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | 08W | SI | Initiation | ECES_CA1/UNSE | 12/10/2020 | 12/10/2020 | 12/31/9999
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | 08W | SI | Initiation | ECES_CA1/UNSE | 12/10/2020 | 12/10/2020 | 12/31/9999
35219587 | CWSP - MARIPOSA 2102440236 PH2 | 08W | YO | Initiation | ECES_CA2/UNSE | 12/11/2020 | 12/11/2020 | 12/31/9999
35219588 | CWSP - MARIPOSA 2102440236 PH3 | 08W | YO | Initiation | ECES_CA2/UNSE | 12/11/2020 | 12/11/2020 | 12/31/9999
35219589 | CWSP - WILDWOOD 11011454 | 08W | NV | Initiation | ECES_CA2/UNSE | 12/11/2020 | 12/11/2020 | 12/31/9999
35219590 | CWSP - VACA DIXON 1105965390 | 08W | SA | Initiation | ECES_CA2/UNSE | 12/11/2020 | 12/11/2020 | 12/31/9999
35219591 | CWSP - OLETA 1101754718 | 08W | ST | Initiation | ECES_CA2/UNSE | 12/11/2020 | 12/11/2020 | 12/31/9999
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | 08W | HB | Initiation | ECES_CA2/UNSE | 12/21/2020 | 12/21/2020 | 12/31/9999
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | 08W | HB | Initiation | ECES_CA2/UNSE | 12/21/2020 | 12/21/2020 | 12/31/9999
35220936 | FRRB - BUTANO STATE PARK - PN SM | 08W | PN | Initiation | ECES_CA2/UNSE | 12/21/2020 | 12/21/2020 | 12/31/9999
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | 08W | HB | Initiation | ECES_CA2/UNSE | 12/28/2020 | 12/28/2020 | 12/31/9999
35222233 | NULL PM | 08W | FR | Initiation | ECES_CA1/UNSE | 12/30/2020 | 12/30/2020 | 12/31/9999
35222234 | OAKHURST 1101 - #581 MIAMI MOUNTAIN | 08W | YO | Initiation | ECES_CA2/UNSE | 12/30/2020 | 12/30/2020 | 12/31/9999
35222235 | DUNLAP 1102 - #631 UC BERKELEY WHITAKER | 08W | FR | Initiation | ECES_CA2/UNSE | 12/30/2020 | 12/30/2020 | 12/31/9999
35222236 | MARIPOSA 2101 - #531 SLAUGHTER HOUSE | 08W | YO | Initiation | ECES_CA2/UNSE | 12/30/2020 | 12/30/2020 | 12/31/9999
35223024 | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | 08W | NB | Initiation | ECES_CA2/UNSE | 01/04/2021 | 01/04/2021 | 12/31/9999
35223026 | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | 08W | NB | Initiation | ECES_CA2/UNSE | 01/04/2021 | 01/04/2021 | 12/31/9999
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | 08W | NB | Initiation | ECES_CA2/UNSE | 01/04/2021 | 01/04/2021 | 12/31/9999
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | 08W | NB | Initiation | ECES_CA2/UNSE | 01/04/2021 | 01/04/2021 | 12/31/9999
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | NV | Initiation | ECES_CA2/UNSE | 01/04/2021 | 01/04/2021 | 12/31/9999
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | 08W | SI | Initiation | ECES_CA2/UNSE | 01/04/2021 | 01/04/2021 | 12/31/9999
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | 08W | SI | Initiation | ECES_CA2/UNSE | 01/04/2021 | 01/04/2021 | 12/31/9999
35223037 | PSPS - OAKHURST 1101 - OAKHURST | 08W | YO | Initiation | ECES_CA2/UNSE | 01/04/2021 | 01/04/2021 | 12/31/9999
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | 08W | ST | Design | ECES_CA2/ESTS | 01/28/2021 | 01/04/2021 | 01/28/2021 | 01/28/2021 | 12/31/9999
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | NV | Initiation | ECES_CA2/UNSE | 01/04/2021 | 01/04/2021 | 12/31/9999
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | 08W | SI | Initiation | ECES_CA2/UNSE | 01/04/2021 | 01/04/2021 | 12/31/9999
35223061 | PSPS - CALISTOGA 1102 - DUNAWEAL WTP | 08W | NB | Initiation | ECES_CA2/UNSE | 01/04/2021 | 01/04/2021 | 12/31/9999
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | 08W | NB | Initiation | ECES_CA2/UNSE | 01/04/2021 | 01/04/2021 | 12/31/9999
35223063 | PSPS - DUNBAR 1101 - OAKMONT | 08W | SO | Initiation | ECES_CA2/UNSE | 01/04/2021 | 01/04/2021 | 12/31/9999
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | 08W | NV | Design | ECES_CA2/ESTS | 01/28/2021 | 01/05/2021 | 01/28/2021 | 01/28/2021 | 12/31/9999
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | 08W | NV | Pre-Construction | ECES_CA2/UNSC | 01/27/2021 | 01/05/2021 | 01/25/2021 | 01/25/2021 | 01/25/2021 | 01/25/2021 | 01/25/2021 | 01/27/2021 | 01/27/2021 | 01/27/2021 | 01/27/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | 08W | NV | Pre-Construction | ECES_CA2/UNSC | 02/17/2021 | 01/05/2021 | 01/26/2021 | 01/26/2021 | 02/16/2021 | 02/16/2021 | 02/16/2021 | 02/17/2021 | 02/17/2021 | 02/17/2021 | 02/17/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | 08W | NB | Initiation | ECES_CA2/UNSE | 01/07/2021 | 01/07/2021 | 12/31/9999
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE | 08W | NB | Initiation | ECES_CA2/UNSE | 01/07/2021 | 01/07/2021 | 12/31/9999
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | 08W | NV | Initiation | ECES_CA2/UNSE | 01/07/2021 | 01/07/2021 | 12/31/9999
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | 08W | SI | Initiation | ECES_CA2/UNSE | 01/08/2021 | 01/08/2021 | 12/31/9999
35224378 | CWSP - VACAVILLE 11046542 - PH 2 | 08W | SA | Initiation | ECES_CA2/UNSE | 01/08/2021 | 01/08/2021 | 12/31/9999
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | NV | Initiation | ECES_CA2/UNSE | 01/14/2021 | 01/14/2021 | 12/31/9999
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | NV | Initiation | ECES_CA2/UNSE | 01/14/2021 | 01/14/2021 | 12/31/9999
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/13/2021 | 01/13/2021 | 12/31/9999
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/13/2021 | 01/13/2021 | 12/31/9999
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | 08W | DI | Initiation | ECES_CA1/UNSE | 01/13/2021 | 01/13/2021 | 12/31/9999
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | 08W | SO | Initiation | ECES_CA2/UNSE | 01/13/2021 | 01/13/2021 | 12/31/9999
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | 08W | SO | Initiation | ECES_CA2/UNSE | 01/13/2021 | 01/13/2021 | 12/31/9999
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | 08W | SO | Initiation | ECES_CA2/UNSE | 01/13/2021 | 01/13/2021 | 12/31/9999
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | 08W | SO | Initiation | ECES_CA2/UNSE | 01/13/2021 | 01/13/2021 | 12/31/9999
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | 08W | NV | Design | ECES_CA2/ESTS | 01/28/2021 | 01/13/2021 | 01/28/2021 | 01/28/2021 | 12/31/9999
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | 08W | NV | Pending | ECES_CA2/PEND | 02/16/2021 | 01/13/2021 | 01/28/2021 | 02/16/2021 | 02/16/2021 | 02/16/2021 | 02/16/2021 | 02/16/2021 | 12/31/9999
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | 08W | NV | Pre-Construction | ECES_CA2/UNSC | 02/02/2021 | 01/13/2021 | 01/29/2021 | 01/29/2021 | 02/01/2021 | 02/01/2021 | 02/01/2021 | 02/02/2021 | 02/02/2021 | 02/02/2021 | 12/31/9999
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | 08W | NV | Pre-Construction | ECES_CA2/UNSC | 02/05/2021 | 01/13/2021 | 01/14/2021 | 01/22/2021 | 01/22/2021 | 01/22/2021 | 01/22/2021 | 02/03/2021 | 02/05/2021 | 02/05/2021 | 12/31/9999
35225825 | CWSP - DESCHUTES 11049718 PH2 | 08W | NV | Initiation | ECES_CA2/UNSE | 01/13/2021 | 01/13/2021 | 12/31/9999
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | 08W | NV | Initiation | ECES_CA2/UNSE | 01/13/2021 | 01/13/2021 | 12/31/9999
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | 08W | NV | Initiation | ECES_CA2/UNSE | 01/13/2021 | 01/13/2021 | 12/31/9999
35225828 | CWSP - OREGON TRAIL 110335002 PH4 | 08W | NV | Initiation | ECES_CA2/UNSE | 01/13/2021 | 01/13/2021 | 12/31/9999
35225829 | CWSP - OREGON TRAIL 110335002 PH5 | 08W | NV | Initiation | ECES_CA2/UNSE | 01/13/2021 | 01/13/2021 | 12/31/9999
35226240 | CWSP - MARIPOSA 210197142 PH 3 | 08W | YO | Design | ECES_CA2/ESTS | 02/08/2021 | 01/15/2021 | 02/08/2021 | 02/08/2021 | 12/31/9999
35226241 | CWSP - MARIPOSA 210197142 PH 2 | 08W | YO | Design | ECES_CA2/ADER | 02/17/2021 | 01/15/2021 | 02/09/2021 | 02/09/2021 | 02/17/2021 | 02/17/2021 | 12/31/9999
35226367 | BR-04-13-W (E) SUBSTATION/PATH PARB | 08W | NV | Design | ECES_CA2/ESTS | 01/15/2021 | 01/15/2021 | 01/15/2021 | 01/15/2021 | 12/31/9999
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/19/2021 | 01/19/2021 | 12/31/9999
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/19/2021 | 01/19/2021 | 12/31/9999
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/19/2021 | 01/19/2021 | 12/31/9999
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/19/2021 | 01/19/2021 | 12/31/9999
35226625 | FRRB - ELK CREEK 1101 LR 2106 | 08W | NV | Initiation | ECES_CA2/UNSE | 01/19/2021 | 01/19/2021 | 12/31/9999
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | 08W | SO | Initiation | ECES_CA2/UNSE | 01/19/2021 | 01/19/2021 | 12/31/9999
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | NV | Initiation | ECES_CA2/UNSE | 01/19/2021 | 01/19/2021 | 12/31/9999
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | NV | Initiation | ECES_CA2/UNSE | 01/19/2021 | 01/19/2021 | 12/31/9999
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | NV | Initiation | ECES_CA2/UNSE | 01/19/2021 | 01/19/2021 | 12/31/9999
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | NV | Initiation | ECES_CA2/UNSE | 01/19/2021 | 01/19/2021 | 12/31/9999
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | NV | Initiation | ECES_CA2/UNSE | 01/19/2021 | 01/19/2021 | 12/31/9999
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/19/2021 | 01/19/2021 | 12/31/9999
35226659 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.2 | 08W | SI | Initiation | ECES_CA2/UNSE | 01/19/2021 | 01/19/2021 | 12/31/9999
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | 08W | NV | Initiation | ECES_CA2/UNSE | 01/19/2021 | 01/19/2021 | 12/31/9999
35226720 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.3 | 08W | SI | Initiation | ECES_CA2/UNSE | 01/19/2021 | 01/19/2021 | 12/31/9999
35226723 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.4 | 08W | SI | Initiation | ECES_CA2/UNSE | 01/19/2021 | 01/19/2021 | 12/31/9999
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | 08W | NV | Initiation | ECES_CA2/UNSE | 01/20/2021 | 01/20/2021 | 12/31/9999
35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | 08W | NV | Initiation | ECES_CA2/UNSE | 01/20/2021 | 01/20/2021 | 12/31/9999
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/22/2021 | 01/22/2021 | 12/31/9999
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | 08W | SI | Design | ECES_CA2/ESTS | 02/12/2021 | 01/20/2021 | 02/12/2021 | 02/12/2021 | 12/31/9999
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | 08W | SI | Initiation | ECES_CA2/UNSE | 01/20/2021 | 01/20/2021 | 12/31/9999
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | 08W | SI | Initiation | ECES_CA2/UNSE | 01/20/2021 | 01/20/2021 | 12/31/9999
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | 08W | SI | Initiation | ECES_CA2/UNSE | 01/20/2021 | 01/20/2021 | 12/31/9999
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | 08W | SI | Initiation | ECES_CA2/UNSE | 01/20/2021 | 01/20/2021 | 12/31/9999
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | 08W | SI | Design | ECES_CA2/ESTS | 02/16/2021 | 01/20/2021 | 02/16/2021 | 02/16/2021 | 12/31/9999
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | 08W | SI | Design | ECES_CA2/ESTS | 02/16/2021 | 01/20/2021 | 02/16/2021 | 02/16/2021 | 12/31/9999
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | 08W | SI | Initiation | ECES_CA2/UNSE | 01/20/2021 | 01/20/2021 | 12/31/9999
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | 08W | SI | Design | ECES_CA2/ESTS | 02/11/2021 | 01/20/2021 | 02/11/2021 | 02/11/2021 | 12/31/9999
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | 08W | SI | Initiation | ECES_CA2/UNSE | 01/20/2021 | 01/20/2021 | 12/31/9999
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | 08W | SI | Initiation | ECES_CA2/UNSE | 01/20/2021 | 01/20/2021 | 12/31/9999
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/20/2021 | 01/20/2021 | 12/31/9999
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/20/2021 | 01/20/2021 | 12/31/9999
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/20/2021 | 01/20/2021 | 12/31/9999
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/20/2021 | 01/20/2021 | 12/31/9999
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/20/2021 | 01/20/2021 | 12/31/9999
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/20/2021 | 01/20/2021 | 12/31/9999
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/20/2021 | 01/20/2021 | 12/31/9999
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/20/2021 | 01/20/2021 | 12/31/9999
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/20/2021 | 01/20/2021 | 12/31/9999
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35226900 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | 08W | NV | Initiation | ECES_CA2/UNSE | 01/20/2021 | 01/20/2021 | 12/31/9999
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35227013 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 2 | 08W | NB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 3 | 08W | NB | Initiation | ECES_CA2/UNSE | 01/21/2021 | 01/21/2021 | 12/31/9999
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | 08W | YO | Construction | ECES_CA2/CONS | 02/12/2021 | 01/22/2021 | 01/23/2021 | 01/23/2021 | 01/23/2021 | 01/23/2021 | 01/23/2021 | 01/23/2021 | 01/23/2021 | 01/23/2021 | 02/12/2021 | 02/12/2021 | 12/31/9999
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/22/2021 | 01/22/2021 | 12/31/9999
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/22/2021 | 01/22/2021 | 12/31/9999
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/22/2021 | 01/22/2021 | 12/31/9999
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/22/2021 | 01/22/2021 | 12/31/9999
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/22/2021 | 01/22/2021 | 12/31/9999
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/22/2021 | 01/22/2021 | 12/31/9999
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/22/2021 | 01/22/2021 | 12/31/9999
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/22/2021 | 01/22/2021 | 12/31/9999
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | 08W | YO | Pre-Construction | ECES_CA1/UNSC | 02/01/2021 | 01/22/2021 | 01/22/2021 | 01/23/2021 | 01/24/2021 | 01/24/2021 | 01/24/2021 | 01/24/2021 | 02/01/2021 | 02/01/2021 | 12/31/9999
35227204 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.5 | 08W | SI | Initiation | ECES_CA2/UNSE | 01/22/2021 | 01/22/2021 | 12/31/9999
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | 08W | YO | Initiation | ECES_CA2/UNSE | 01/22/2021 | 01/22/2021 | 12/31/9999
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | 08W | YO | Initiation | ECES_CA2/UNSE | 01/22/2021 | 01/22/2021 | 12/31/9999
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | 08W | YO | Initiation | ECES_CA2/UNSE | 01/22/2021 | 01/22/2021 | 12/31/9999
35227263 | CWSP - MARIPOSA 2102CB PH 2 | 08W | YO | Design | ECES_CA2/ESTS | 02/10/2021 | 01/22/2021 | 02/10/2021 | 02/10/2021 | 12/31/9999
35227651 | CWSP - VACAVILLE 11046542 PH 1.2 | 08W | SA | Initiation | ECES_CA2/UNSE | 01/26/2021 | 01/26/2021 | 12/31/9999
35227652 | CWSP - VACAVILLE 11046542 PH 1.3 | 08W | SA | Initiation | ECES_CA2/UNSE | 01/26/2021 | 01/26/2021 | 12/31/9999
35227653 | CWSP - VACAVILLE 11046542 PH 1.4 | 08W | SA | Initiation | ECES_CA2/UNSE | 01/26/2021 | 01/26/2021 | 12/31/9999
35227654 | CWSP - VACAVILLE 11046542 PH 1.5 | 08W | SA | Initiation | ECES_CA2/UNSE | 01/26/2021 | 01/26/2021 | 12/31/9999
35227655 | CWSP - KIRKER 2104442850 PH 2 | 08W | DI | Initiation | ECES_CA2/UNSE | 01/26/2021 | 01/26/2021 | 12/31/9999
35227656 | CWSP - VACAVILLE 11046542 - PH 2.3 | 08W | SA | Initiation | ECES_CA2/UNSE | 01/26/2021 | 01/26/2021 | 12/31/9999
35227657 | CWSP - VACAVILLE 11046542 - PH 2.4 | 08W | SA | Initiation | ECES_CA2/UNSE | 01/26/2021 | 01/26/2021 | 12/31/9999
35227658 | CWSP - VACAVILLE 11046542 - PH 2.5 | 08W | SA | Initiation | ECES_CA2/UNSE | 01/26/2021 | 01/26/2021 | 12/31/9999
35227659 | CWSP - VACAVILLE 11046542 - PH 2.6 | 08W | SA | Initiation | ECES_CA2/UNSE | 01/26/2021 | 01/26/2021 | 12/31/9999
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/26/2021 | 01/26/2021 | 12/31/9999
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/26/2021 | 01/26/2021 | 12/31/9999
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/26/2021 | 01/26/2021 | 12/31/9999
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/26/2021 | 01/26/2021 | 12/31/9999
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/26/2021 | 01/26/2021 | 12/31/9999
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/26/2021 | 01/26/2021 | 12/31/9999
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/26/2021 | 01/26/2021 | 12/31/9999
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/26/2021 | 01/26/2021 | 12/31/9999
35227870 | CWSP - VACAVILLE 11046542 - PH 2.2 | 08W | SA | Initiation | ECES_CA2/UNSE | 01/28/2021 | 01/28/2021 | 12/31/9999
35228082 | BR-14-04-W (E) ARROWHEAD DR PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 01/27/2021 | 01/27/2021 | 12/31/9999
35228083 | BR-14-05-W (E) HILLPARK LN DR PARB | 08W | NV | Initiation | ECES_CA2/UNSE | 01/27/2021 | 01/27/2021 | 12/31/9999
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/29/2021 | 01/29/2021 | 12/31/9999
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/29/2021 | 01/29/2021 | 12/31/9999
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | 08W | HB | Initiation | ECES_CA2/UNSE | 01/29/2021 | 01/29/2021 | 12/31/9999
35228449 | RIO DELL STORM REBUILD | 08W | HB | Pending | ECES_CA2/PEND | 02/10/2021 | 01/30/2021 | 01/31/2021 | 01/31/2021 | 02/01/2021 | 02/01/2021 | 02/01/2021 | 02/10/2021 | 12/31/9999 | 02/01/2021 | 02/10/2021
35228774 | PSPS - DUNBAR 1101 - OAKMONT PH 2 | 08W | SO | Initiation | ECES_CA2/UNSE | 02/02/2021 | 02/02/2021 | 12/31/9999
35228775 | PSPS - DUNBAR 1101 - OAKMONT PH 3 | 08W | SO | Initiation | ECES_CA2/UNSE | 02/02/2021 | 02/02/2021 | 12/31/9999
35229043 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 1 | 08W | NV | Initiation | ECES_CA2/UNSE | 02/03/2021 | 02/03/2021 | 12/31/9999
35229051 | CORNING 1102 - REMOTE GRID #299 & # 300 | 08W | NV | Initiation | ECES_CA2/UNSE | 02/03/2021 | 02/03/2021 | 12/31/9999
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | 08W | HB | Initiation | ECES_CA2/UNSE | 02/04/2021 | 02/04/2021 | 12/31/9999
35231543 | CWSP - TIDEWATER 210614072 PH 2 | 08W | DI | Initiation | ECES_CA2/UNSE | 02/08/2021 | 02/08/2021 | 12/31/9999
35231544 | CWSP - TIDEWATER 210614072 PH 3 | 08W | DI | Initiation | ECES_CA2/UNSE | 02/08/2021 | 02/08/2021 | 12/31/9999
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/08/2021 | 02/08/2021 | 12/31/9999
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/08/2021 | 02/08/2021 | 12/31/9999
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | 08W | SI | Design | ECES_CA2/ESTS | 02/16/2021 | 02/08/2021 | 02/16/2021 | 02/16/2021 | 12/31/9999
35231620 | CWSP - HIGHLANDS 1102628 PH 1.2 | 08W | HB | Initiation | ECES_CA2/UNSE | 02/08/2021 | 02/08/2021 | 12/31/9999
35231621 | CWSP - HIGHLANDS 1102628 PH 1.3 | 08W | HB | Initiation | ECES_CA2/UNSE | 02/08/2021 | 02/08/2021 | 12/31/9999
35231622 | CWSP - HIGHLANDS 1102628 PH 1.4 | 08W | HB | Initiation | ECES_CA2/UNSE | 02/08/2021 | 02/08/2021 | 12/31/9999
35231623 | CWSP - HIGHLANDS 1102628 PH 1.5 | 08W | HB | Initiation | ECES_CA2/UNSE | 02/08/2021 | 02/08/2021 | 12/31/9999
35231624 | CWSP - HIGHLANDS 1102628 PH 1.6 | 08W | HB | Initiation | ECES_CA2/UNSE | 02/08/2021 | 02/08/2021 | 12/31/9999
35231625 | CWSP - HIGHLANDS 1102628 PH 1.7 | 08W | HB | Initiation | ECES_CA2/UNSE | 02/08/2021 | 02/08/2021 | 12/31/9999
35231626 | CWSP - HIGHLANDS 1102628 PH 1.8 | 08W | HB | Initiation | ECES_CA2/UNSE | 02/08/2021 | 02/08/2021 | 12/31/9999
35231627 | CWSP - HIGHLANDS 1102628 PH 1.9 | 08W | HB | Initiation | ECES_CA2/UNSE | 02/08/2021 | 02/08/2021 | 12/31/9999
35231628 | CWSP - HIGHLANDS 1102628 PH 1.10 | 08W | HB | Initiation | ECES_CA2/UNSE | 02/08/2021 | 02/08/2021 | 12/31/9999
35231629 | CWSP - HIGHLANDS 1102628 PH 1.11 | 08W | HB | Initiation | ECES_CA2/UNSE | 02/08/2021 | 02/08/2021 | 12/31/9999
35231630 | CWSP - HIGHLANDS 1102628 PH 1.12 | 08W | HB | Initiation | ECES_CA2/UNSE | 02/08/2021 | 02/08/2021 | 12/31/9999
35231631 | CWSP - HIGHLANDS 1102628 PH 1.13 | 08W | HB | Initiation | ECES_CA2/UNSE | 02/08/2021 | 02/08/2021 | 12/31/9999
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | 08W | SI | Design | ECES_CA2/ESTS | 02/16/2021 | 02/11/2021 | 02/16/2021 | 02/16/2021 | 12/31/9999
35232298 | FRRB - WYANDOTTE 1103 - W1 - PH1.1 | 08W | NV | Initiation | ECES_CA2/UNSE | 02/12/2021 | 02/12/2021 | 12/31/9999
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | 08W | NV | Initiation | ECES_CA2/UNSE | 02/12/2021 | 02/12/2021 | 12/31/9999
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | 08W | NV | Initiation | ECES_CA2/UNSE | 02/12/2021 | 02/12/2021 | 12/31/9999
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | 08W | NV | Initiation | ECES_CA2/UNSE | 02/12/2021 | 02/12/2021 | 12/31/9999
35232445 | CWSP - DESCHUTES 11049718 PH 2.5 | 08W | NV | Initiation | ECES_CA2/UNSE | 02/12/2021 | 02/12/2021 | 12/31/9999
35232650 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/16/2021 | 02/16/2021 | 12/31/9999
35232651 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.3 | 08W | SI | Initiation | ECES_CA2/UNSE | 02/16/2021 | 02/16/2021 | 12/31/9999
35232718 | FRRB - WYANDOTTE 1103 - W2 - PH2.1 | 08W | NV | Initiation | ECES_CA2/UNSE | 02/17/2021 | 02/17/2021 | 12/31/9999
35232960 | CWSP - DESCHUTES 11049718 PH1.2 | 08W | NV | Initiation | ECES_CA2/UNSE | 02/17/2021 | 02/17/2021 | 12/31/9999
74011865 | PH.3 - RECON. ECHO SUMMIT 1101 11,600' | 08W | SI | Initiation | ECES_CA2/UNSE | 03/13/2019 | 03/13/2019 | 12/31/9999 | 06/29/2017 | 08/16/2017 | 08/16/2017 | 03/13/2019 | 06/29/2017 | 06/29/2017
74014860 | R2 REPL OH COND/ ALTERNTE BACKTIE CE2104 | 08W | CC | Initiation | ECES_CA2/UNSE | 09/12/2017 | 09/12/2017 | 12/31/9999
74015668 | *CANC* RPL OH WIRE ON OTTER-1101 S | 08W | CC | Completion | ECES_CA2/CLSD | 09/05/2019 | 10/19/2017 | 01/07/2019 | [10 empty] | 08/05/2019 | 08/05/2019 | 01/07/2019 | 08/05/2019 |  |  |  |  | 09/05/2019 | 12/31/9999 | 08/05/2019 | 12/31/9999
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | 08W | SI | Documentation | ECES_CA2/DOCC | 10/10/2019 | 10/04/2018 | 12/10/2018 | 12/10/2018 | 05/14/2019 | 05/14/2019 | 05/31/2019 | 06/18/2019 | 07/27/2019 | 07/27/2019 | 10/10/2019 |  |  | 10/10/2019 | 12/31/9999
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | 08W | SI | Documentation | ECES_CA2/DOCC | 10/10/2019 | 10/04/2018 | 12/10/2018 | 12/10/2018 | 04/26/2019 | 04/26/2019 | 06/04/2019 | 06/24/2019 | 07/27/2019 | 07/27/2019 | 10/10/2019 |  |  | 10/10/2019 | 12/31/9999
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | 08W | SO | Documentation | ECES_CA2/DOCC | 06/24/2020 | 01/07/2019 | 02/06/2019 | 02/06/2019 | 02/06/2019 | 02/06/2019 | 05/01/2019 | 08/09/2019 | 06/24/2020 | 07/31/2019 | 08/09/2019 |  |  | 06/24/2020 | 12/31/9999
74021962 | *DO NOT USE* CWSP: DIABLO WILDFIRE HARDE | 08W | DI | Completion | ECES_CA2/CLSD | 01/07/2021 | 10/04/2018 | 05/01/2019 | 05/01/2019 | 05/22/2019 | [10 empty] | 05/22/2019 | 12/14/2020 |  |  |  |  | 01/07/2021 | 12/31/9999 | 12/14/2020 | 01/07/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | 08W | EB | Documentation | ECES_CA2/DOCC | 08/13/2020 | 10/04/2018 | 04/22/2019 | 04/22/2019 | 04/22/2019 | 04/22/2019 | 05/06/2019 | 05/20/2019 | 07/01/2019 | 07/01/2019 | 08/19/2019 | 08/19/2019 | 08/13/2020 | 08/13/2020 | 12/31/9999
74021964 | X-1104 OH RECOND SKYLINE | 08W | EB | Documentation | ECES_CA2/DOCC | 10/08/2018 | 10/04/2018 | 10/08/2018 | [10 empty] | 10/08/2018 | 12/31/9999
74022040 | 2019 CALISTOGA 1101 HIGH SPLICE COUNT | 08W | NB | Post-Doc | ECES_CA2/FICL | 12/08/2020 | 10/08/2018 | 10/10/2018 | 10/10/2018 | 02/06/2019 | 02/06/2019 | 02/14/2019 | 03/30/2019 | 03/31/2019 | 03/29/2019 | 03/30/2019 |  |  | 03/31/2019 | 01/24/2020 |  |  | 01/24/2020 | 03/03/2020 | 12/08/2020 | 12/08/2020
74022302 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH | 08W | SI | Initiation | ECES_CA2/UNSE | 10/17/2018 | 10/17/2018 | 12/31/9999
74022380 | *CANC* BRUNSWICK 1103 LR2200 | 08W | SI | Completion | ECES_CA2/CLSD | 12/03/2020 | 10/22/2018 | 07/25/2019 | 07/25/2019 | 12/03/2019 | [12 empty] | 12/04/2019 | 09/30/2020 | 12/03/2019 | 12/04/2019 | 12/03/2020 | 12/31/9999 | 11/04/2020 | 12/03/2020
74022381 | *CANC* CWSP - CAMP EVERS 2106 - 50 | 08W | CC | Completion | ECES_CA2/CLSD | 05/03/2020 | 10/22/2018 | 07/29/2019 | 07/29/2019 | 08/14/2019 | [10 empty] | 08/14/2019 | 04/06/2020 |  |  |  |  | 05/03/2020 | 12/31/9999 | 04/06/2020 | 05/03/2020
74022382 | CWSP-COLUMBIA HILL 1101-LR 2212 PH1 | 08W | SI | Completion | ECES_CA2/CLSD | 01/23/2021 | 10/22/2018 | 06/05/2019 | 06/05/2019 | 08/13/2019 | 08/13/2019 | 08/30/2019 | 09/12/2019 | 10/08/2019 | 10/08/2019 | 12/27/2019 |  |  | 11/19/2020 | 01/21/2021 |  |  | 06/17/2020 | 07/03/2020 | 07/03/2020 | 09/08/2020 | 01/23/2021 | 12/31/9999
74022383 | CWSP-EL DORADO PH 2102 LR19542 PH 1.0 | 08W | SI | Initiation | ECES_CA2/UNSE | 10/22/2018 | 10/22/2018 | 12/31/9999
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | 08W | SO | Construction | ECES_CA2/CONS | 05/25/2020 | 10/22/2018 | 04/03/2019 | 04/03/2019 | 04/05/2019 | 04/05/2019 | 06/06/2019 | 06/06/2019 | 05/11/2020 | 05/11/2020 | 05/25/2020 | 05/25/2020 | 12/31/9999
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | 08W | HB | Approval | ECES_CA2/APPR | 06/30/2020 | 10/22/2018 | 05/08/2019 | 03/12/2020 | 06/30/2020 | 01/30/2020 | 02/25/2020 | 02/25/2020 | 03/12/2020
74022386 | *CANC* CWSP - LOS GATOS 1106 - LB4 | 08W | SJ | Completion | ECES_CA2/CLSD | 02/03/2021 | 10/22/2018 | 01/27/2020 | [12 empty] | 01/27/2020 | 05/05/2020 |  |  |  |  | 02/03/2021 | 12/31/9999 | 01/15/2021 | 02/03/2021
74022387 | CWSP-MIDDLETOWN 1101-TS 1079 | 08W | HB | Completion | ECES_CA2/CLSD | 01/16/2021 | 10/22/2018 | 02/15/2019 | 02/15/2019 | 02/15/2019 | 02/15/2019 | 03/18/2019 | 04/05/2019 | 04/08/2019 | 04/08/2019 | 06/13/2019 | 06/13/2019 | 06/13/2019 | 06/13/2019 | 04/07/2020 |  |  | 04/07/2020 | 05/04/2020 | 05/04/2020 | 01/14/2021 | 01/16/2021 | 12/31/9999
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | 08W | EB | Documentation | ECES_CA2/DOCC | 11/13/2020 | 10/22/2018 | 12/18/2018 | 05/04/2019 | 10/07/2019 | 10/07/2019 | 10/07/2019 | 10/08/2019 | 12/19/2019 | 01/09/2020 | 03/02/2020 | 03/02/2020 | 11/13/2020 | 11/13/2020 | 12/31/9999 | 02/08/2019 | 05/04/2019
74022389 | *CANC* CWSP - PARADISE 1106 - OCB & LR 2 | 08W | NV | Completion | ECES_CA2/CLSD | 01/07/2021 | 10/22/2018 | 12/30/2020 | [18 empty] | 01/07/2021 | 12/31/9999 | 12/30/2020 | 01/07/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | 08W | NB | Documentation | ECES_CA2/DOCC | 05/20/2020 | 10/22/2018 | 04/19/2019 | 04/19/2019 | 08/08/2019 | 08/08/2019 | 08/08/2019 | 01/13/2020 | 01/22/2020 | 09/19/2019 | 10/28/2019 | 01/22/2020 | 05/20/2020 | 05/20/2020 | 12/31/9999
74022391 | *CANC* **DO NOT USE**CWSP - VOLTA 1102 | 08W | NV | Completion | ECES_CA2/CLSD | 12/03/2020 | 10/22/2018 | 06/18/2019 | 06/18/2019 | 07/29/2019 | 07/29/2019 | 10/31/2019 | [6 empty] | 05/12/2020 | 10/12/2020 |  |  |  |  | 10/31/2019 | 05/12/2020 | 12/03/2020 | 12/31/9999 | 11/04/2020 | 12/03/2020
74022614 | CWSP - CAMP FIRE PADSE 1105 QUAIL RD | 08W | NV | Initiation | ECES_CA2/UNSE | 11/12/2018 | 11/12/2018 | 12/31/9999
74022615 | CWSP - CAMP FIRE PADSE 1105 PENTZ RD | 08W | NV | Post-Doc | ECES_CA2/FICL | 03/14/2019 | 11/12/2018 | 03/14/2019 | [10 empty] | 03/14/2019 | 03/14/2019 |  |  |  |  | 03/14/2019 | 12/31/9999
74022620 | *DO NOT USE* RPL OH WIRE ON OTTER-1101 S | 08W | CC | Documentation | ECES_CA2/DCNL | 02/06/2019 | 11/07/2018 | 02/06/2019 | [12 empty] | 02/06/2019 | 12/31/9999
74022663 | CAMP FIRE RECOND LINE HONEY RN BUTTE 05 | 08W | NV | Documentation | ECES_CA2/DOCC | 10/15/2020 | 11/14/2018 | 03/14/2019 |  |  | 04/15/2020 | 04/15/2020 | 04/15/2020 | 10/15/2020 |  |  |  |  | 10/15/2020 | 12/31/9999
74022664 | CAMP FIRE RECONDUCTOR LINE DEPOT RD | 08W | NV | Post-Doc | ECES_CA2/FICL | 09/23/2020 | 11/14/2018 | 01/03/2019 | 01/03/2019 | 01/03/2019 | 01/03/2019 | 03/14/2019 | 06/01/2020 | 07/27/2020 | 07/27/2020 | 08/11/2020 |  |  | 08/11/2020 | 08/13/2020 |  |  | 08/13/2020 | 09/23/2020 | 09/23/2020 | 12/31/9999
74022720 | CWSP-CAMP FIRE PADSE 1105 INST BIKE PATH | 08W | NV | Post-Doc | ECES_CA2/FICL | 07/06/2020 | 11/13/2018 | 11/13/2018 | 07/06/2020 | 07/06/2020 | 11/13/2018 | 03/14/2019 | [12 empty] | 07/06/2020 | 07/06/2020
74022721 | CWSP - CAMP FIRE PADSE 1106 BILLIE RD | 08W | NV | Documentation | ECES_CA2/DOCC | 06/01/2020 | 11/13/2018 | 03/14/2019 | [10 empty] | 06/01/2020 | 12/31/9999 |  |  | 12/16/2019 | 06/01/2020 | 03/14/2019 | 12/16/2019
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD | 08W | NV | Design | ECES_CA2/ESTS | 07/29/2020 | 11/13/2018 | 01/03/2019 | 07/29/2020 | 12/31/9999 | 01/03/2019 | 03/14/2019 | [12 empty] | 03/14/2019 | 07/29/2020
74022723 | CWSP - CAMP FIRE PDSE 1106 PONDEROSA WAY | 08W | NV | Pending | ECES_CA2/PEND | 06/01/2020 | 11/13/2018 | 11/13/2018 | 11/13/2018 | 03/14/2019 |  |  | 06/01/2020 | 12/31/9999 | [10 empty] | 03/14/2019 | 06/01/2020
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | 08W | NB | Documentation | ECES_CA2/DOCC | 12/17/2019 | 02/14/2019 | 02/19/2019 | 02/19/2019 | 06/06/2019 |  |  | 08/17/2019 | 08/23/2019 | 08/23/2019 | 08/26/2019 | 08/26/2019 | 12/17/2019 | 12/17/2019 | 12/31/9999
74024660 | 2019 CALISTOGA 1101 SUB ORDER | 08W | NB | Initiation | ECES_CA2/UNSE | 03/04/2019 | 03/04/2019 | 12/31/9999
74024661 | CWSP-BRUNSWICK 1105 LR32536 PH1 SUBORDER | 08W | SI | Initiation | ECES_CA2/UNSE | 03/04/2019 | 03/04/2019 | 12/31/9999
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | 08W | SO | Construction | ECES_CA2/CONS | 07/24/2020 | 08/14/2019 | 01/24/2020 | 03/10/2020 | 04/16/2020 | 01/24/2020 | 01/30/2020 | 04/29/2020 | 05/01/2020 | 05/06/2020 | 07/24/2020 | 07/24/2020 | 12/31/9999