## Constraints
Order # | Project Name | Bio Constraints | Cultural Constraints | EFS Constraints | Notes
35217268 | SH - BUCKS CREEK 1101 CB | 1. There is California red-legged frog and Foothill yellow-legged frog MRHCP modeled habitat within the project area, no constraints as long as species-specific AMMs are implemented. Could require work during the dry season (May 15 - Oct 15) and/or biomonitoring. 2. There are two spotted owl activity centers within the vicinity. They are outside of visual/auditory harassment zone. Potential Heli restrictions Feb 2- July 15 3. There are multiple water crossings. Potential Permitting* | Entire Project: Project activities within the Caltrans ROW will require a Caltrans Encroachment Permit. Upon review by Caltrans, additional cultural resource protection measures may be required. Native American consultation will be required and possible tribal monitoring/archaeological monitoring. Added cost and 30 Days to ERTC timeline. Alternative 2: The UG portion passes through an ESA and would require monitoring, testing, and/or mitigation. It is strongly recommended that this alternative be avoided. | No Constraints | 4.8 miles
* Aquatic Features = For overhead, ensure no poles are located within the riparian area or waterways to avoid permit triggers. For undergrounding, need to ensure that there is no excavation within the bed, bank, or channel of the waterways. If HDD is utilized, ensure that entry/exit pits are outside of the riparian zone. No constraints if designed properly.