## Cover
2021 Project Opportunity Tracker
2026-08-05

## Summary
Miles Hardened by Project Type and Approval Status with PO
Project Type | Approved (Scoped) | Approved (Not Scoped) | For Approval | Total
Fire Rebuild | 12.7 | 0 | 0 | 12.7
In-Construction | 39.805 | 0 | 0 | 39.805
Top 250 Miles | 0 | 0 | 0 | 0
Top 20% MAVF CPZ | 0 | 41.3164 | 0 | 41.3164
ECOP | 0 | 49.04 | 6.9 | 55.94
PSPS - Scoped | 0 | 0 | 3.59 | 3.59
PSPS - Not Scoped | 0 | 0 | 0 | 0
DSDD | 0 | 0 | 4.977 | 4.977
Remote Grid | 0 | 0 | 5.69 | 5.69
Line Removal | 0 | 13.7603 | 0 | 13.7603
Total | 52.505 | 104.1167 | 21.157 | 177.7787
Miles Hardened by Project Type and Approval Status without PO
Project Type | Approved (Scoped) | Approved (Not Scoped) | For Approval | Total
Fire Rebuild | 0 | 13 | 0 | 13 | Note - This is line removal assocaited to Fire Rebuild
In-Construction | 0 | 0 | 0 | 0
Top 250 Miles | 0 | 50 | 0 | 50
Top 20% MAVF CPZ | 0 | 0 | 0 | 0
ECOP | 0 | 0 | 0 | 0
PSPS - Scoped | 0 | 0 | 0 | 0
PSPS - Not Scoped | 0 | 0 | 12.5 | 12.5
DSDD | 0 | 0 |  | 0
Remote Grid | 0 | 0 | 0 | 0
Line Removal | 0 | 4.7 | 0 | 4.7
Total | 0 | 67.7 | 12.5 | 80.2
Miles Hardened by Project Type and Approval Status without PO
Project Type | Approved (Scoped) | Approved (Not Scoped) | For Approval | Total
Fire Rebuild | 12.7 | 13 | 0 | 25.7
In-Construction | 39.805 | 0 | 0 | 39.805
Top 250 Miles | 0 | 50 | 0 | 50
Top 20% MAVF CPZ | 0 | 41.3164 | 0 | 41.3164
ECOP | 0 | 49.04 | 6.9 | 55.94
PSPS - Scoped | 0 | 0 | 3.59 | 3.59
PSPS - Not Scoped | 0 | 0 | 12.5 | 12.5
DSDD | 0 | 0 | 4.977 | 4.977
Remote Grid | 0 | 0 | 5.69 | 5.69
Line Removal | 0 | 18.4603 | 0 | 18.4603
Total | 52.505 | 171.8167 | 33.657 | 257.9787
2021 Projection | [5 empty] | In Scoping Discount Rate | 50%
Project Type | Approved (Scoped) | Approved (Not Scoped) | For Approval | Total |  | PSPS Discount Rate | 2%
Fire Rebuild | 12.7 | 6.5 | 0 | 19.2
In-Construction | 39.805 | 0 | 0 | 39.805
Top 250 Miles | 0 | 25 | 0 | 25
Top 20% MAVF CPZ | 0 | 20.6582 | 0 | 20.6582
ECOP | 0 | 24.52 | 3.45 | 27.97
PSPS - Scoped | 0 | 0 | 0.0718 | 0.0718 | Note - Discounted at PSPS rates
PSPS - Not Scoped | 0 | 0 | 0.25 | 0.25 | Note - Discounted at PSPS rates
DSDD | 0 | 0 | 4.977 | 4.977 | Note - Not discounted
Remote Grid | 0 | 0 | 2.845 | 2.845
Line Removal | 0 | 18.4603 | 0 | 18.4603 | Note - Not Discounted
Total | 52.505 | 95.1385 | 11.5938 | 159.2373

## Tracker
Approval Status | Project Order Number | Circuit | Circuit Name | CPZ | Project Type | Miles Hardened | Total Miles | Mean MAVF Core Risk | Mean MAVF Core Risk Rank
Approved (Scoped) | 77779999 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 110369412 | Fire Rebuild | 4.8 | 15.5679 | 0.0078448 | 2055
Approved (Scoped) | 77779999 | 102781101 | ELK CREEK 1101 | ELK CREEK 11012106 | Fire Rebuild | 7.9 | 13.2402 | 0.1961 | 340
Approved (Scoped) | 74022384 | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 111324918 | In-Construction | 4.59 | 5.4965 | 0.1575 | 481
Approved (Scoped) | 35098621 | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | In-Construction | 0.52 | 9.1336 | 0.12922 | 606
Approved (Scoped) | 35157845 | 43432105 | SILVERADO 2105 | SILVERADO 2105658898 | In-Construction | 1.27 | 17.1737 | 0.035763 | 1361
Approved (Scoped) | 35094397 | 43311102 | KONOCTI 1102 | KONOCTI 1102532 | In-Construction | 1.07 | 9.7315 | 0.0090595 | 1999
Approved (Scoped) | 35061206 | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | In-Construction | 1.77 | 17.7473 | 0.0062036 | 2144
Approved (Scoped) | 35061212 | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | In-Construction | 1.79 | 17.7473 | 0.0062036 | 2144
Approved (Scoped) | 35115151 | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | In-Construction | 1.9 | 17.7473 | 0.0062036 | 2144
Approved (Scoped) | 35117443 | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | In-Construction | 2.16 | 17.7473 | 0.0062036 | 2144
Approved (Scoped) | 35116383 | 163661701 | MIWUK 1701 | MIWUK 1701953336 | In-Construction | 1.38 | 11.8581 | 0.0038168 | 2267
Approved (Scoped) | 35116384 | 163661701 | MIWUK 1701 | MIWUK 1701953336 | In-Construction | 1.67 | 11.8581 | 0.0038168 | 2267
Approved (Scoped) | 35114040 | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | In-Construction | 1.4 | 17.2598 | 0.0037571 | 2271
Approved (Scoped) | 35114048 | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | In-Construction | 1.4 | 17.2598 | 0.0037571 | 2271
Approved (Scoped) | 35052821 | 163661701 | MIWUK 1701 | MIWUK 1701CB | In-Construction | 1.72 | 16.2494 | 0.0029901 | 2353
Approved (Scoped) | 35056746 | 163661701 | MIWUK 1701 | MIWUK 1701CB | In-Construction | 2.02 | 16.2494 | 0.0029901 | 2353
Approved (Scoped) | 35115050 | 163661701 | MIWUK 1701 | MIWUK 1701CB | In-Construction | 1.61 | 16.2494 | 0.0029901 | 2353
Approved (Scoped) | 35115053 | 163661701 | MIWUK 1701 | MIWUK 1701CB | In-Construction | 1.81 | 16.2494 | 0.0029901 | 2353
Approved (Scoped) | 35115054 | 163661701 | MIWUK 1701 | MIWUK 1701CB | In-Construction | 1.4 | 16.2494 | 0.0029901 | 2353
Approved (Scoped) | 35115055 | 163661701 | MIWUK 1701 | MIWUK 1701CB | In-Construction | 2.13 | 16.2494 | 0.0029901 | 2353
Approved (Scoped) | 35116391 | 163661702 | MIWUK 1702 | MIWUK 1702CB | In-Construction | 0.69 | 9.055 | 0.0028161 | 2369
Approved (Scoped) | 35116395 | 163661702 | MIWUK 1702 | MIWUK 1702CB | In-Construction | 1.71 | 9.055 | 0.0028161 | 2369
Approved (Scoped) | 35116800 | 163661702 | Miwuk 1702 | MIWUK 1702823548 | In-Construction | 1.175 | 19.7318 | 0.0025098 | 2411
Approved (Scoped) | 35114100 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 21065020 | In-Construction | 1.04 | 15.0734 | 0.0021265 | 2464
Approved (Scoped) | 35116442 | 163661702 | MIWUK 1702 | MIWUK 170238218 | In-Construction | 0.31 | 10.9416 | 0.00074696 | 2678
Approved (Scoped) | 35116444 | 163661702 | MIWUK 1702 | MIWUK 170238218 | In-Construction | 2.1 | 10.9416 | 0.00074696 | 2678
Approved (Scoped) | 35052825 | 163661702 | MIWUK 1702 | MIWUK 1702S2247 | In-Construction | 1.17 | 1.4879 | 0.00049228 | 2737
Approved (Not Scoped) |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 1103CUS391 | Top 250 Miles |  | 0.022596 | 3.1639 | 1
Approved (Not Scoped) |  | 48011144 | CALPINE 1144 | CALPINE 1144276-G | Top 250 Miles |  | 0.014759 | 1.8786 | 2
Approved (Not Scoped) |  | 254452101 | MARIPOSA 2101 | MARIPOSA 210190130 | Top 250 Miles |  | 0.09394 | 1.6924 | 3
Approved (Not Scoped) |  | 252062111 | SHEPHERD 2111 | SHEPHERD 2111688294 | Top 250 Miles |  | 0.01514 | 1.4425 | 4
Approved (Not Scoped) |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103CB | Top 250 Miles |  | 0.052975 | 1.3006 | 5
Approved (Not Scoped) |  | 42871101 | UPPER LAKE 1101 | UPPER LAKE 1101CB | Top 250 Miles |  | 1.1133 | 1.2559 | 6
Approved (Not Scoped) |  | 103451101 | KESWICK 1101 | KESWICK 11011586 | Top 250 Miles |  | 7.4478 | 1.2524 | 7
Approved (Not Scoped) |  | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | Top 250 Miles |  | 4.7058 | 0.91632 | 8
Approved (Not Scoped) |  | 43311102 | KONOCTI 1102 | KONOCTI 1102965078 | Top 250 Miles |  | 6.2704 | 0.87629 | 9
Approved (Not Scoped) |  | 254452102 | MARIPOSA 2102 | MARIPOSA 2102241564 | Top 250 Miles |  | 0.71281 | 0.77248 | 10
Approved (Not Scoped) |  | 102211101 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | Top 250 Miles |  | 4.8008 | 0.73491 | 11
Approved (Not Scoped) |  | 152582109 | DEL MAR 2109 | DEL MAR 2109378446 | Top 250 Miles |  | 0.098166 | 0.73151 | 12
Approved (Not Scoped) |  | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102CB | Top 250 Miles |  | 0.46739 | 0.72481 | 13
Approved (Not Scoped) |  | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | Top 250 Miles |  | 27.7328 | 0.71618 | 14
Approved (Not Scoped) |  | 253642104 | POSO MOUNTAIN 2104 | POSO MOUNTAIN 2104CB | Top 250 Miles |  | 5.3534 | 0.70423 | 15
Approved (Not Scoped) |  | 252691104 | INDIAN FLAT 1104 | INDIAN FLAT 11044440 | Top 250 Miles |  | 0.23386 | 0.68656 | 16
Approved (Not Scoped) |  | 102781101 | ELK CREEK 1101 | ELK CREEK 1101CB | Top 250 Miles |  | 0.084235 | 0.67079 | 17
Approved (Not Scoped) |  | 14652106 | TIDEWATER 2106 | TIDEWATER 210614072 | Top 250 Miles |  | 3.6652 | 0.65331 | 18
Approved (Not Scoped) |  | 43211101 | HARTLEY 1101 | HARTLEY 1101980662 | Top 250 Miles |  | 0.22763 | 0.64187 | 19
Approved (Not Scoped) |  | 63591101 | VACA DIXON 1101 | VACA DIXON 1101126774 | Top 250 Miles |  | 0.78766 | 0.62029 | 20
Approved (Not Scoped) |  | 14452104 | KIRKER 2104 | KIRKER 2104442850 | Top 250 Miles |  | 5.7542 | 0.61454 | 21
Approved (Not Scoped) |  | 254432104 | COARSEGOLD 2104 | COARSEGOLD 2104CB | Top 250 Miles |  | 2.4277 | 0.59573 | 22
Approved (Not Scoped) |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101118494 | Top 250 Miles |  | 1.0659 | 0.58092 | 23
Approved (Not Scoped) |  | 43201102 | STAFFORD 1102 | STAFFORD 1102784704 | Top 250 Miles |  | 0.027274 | 0.564 | 24
Approved (Not Scoped) |  | 63642108 | PEABODY 2108 | PEABODY 2108113684 | Top 250 Miles |  | 0.36709 | 0.55276 | 25
Approved (Not Scoped) |  | 63642106 | PEABODY 2106 | PEABODY 2106250154 | Top 250 Miles |  | 0.28499 | 0.55243 | 26
Approved (Not Scoped) |  | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | Top 250 Miles |  | 14.2224 | 0.5487 | 27
Approved (Not Scoped) |  | 14662112 | TASSAJARA 2112 | TASSAJARA 21123202 | Top 250 Miles |  | 0.39174 | 0.53731 | 28
Approved (Not Scoped) |  | 102911109 | WYANDOTTE 1109 | WYANDOTTE 110932586 | Top 250 Miles |  | 1.3417 | 0.52987 | 29
Approved (Not Scoped) |  | 253642103 | POSO MOUNTAIN 2103 | POSO MOUNTAIN 2103CB | Top 250 Miles |  | 2.3287 | 0.51619 | 30
Approved (Not Scoped) |  | 48011146 | CALPINE 1146 | CALPINE 1146200-G | Top 250 Miles |  | 0.0085246 | 0.50979 | 31
Approved (Not Scoped) |  | 48011146 | CALPINE 1146 | CALPINE 1146394G | Top 250 Miles |  | 0.011292 | 0.50979 | 32
Approved (Not Scoped) |  | 102251101 | CRESTA 1101 | CRESTA 1101546650 | Top 250 Miles |  | 0.89694 | 0.50291 | 33
Approved (Not Scoped) |  | 42821102 | CLOVERDALE 1102 | CLOVERDALE 110247214 | Top 250 Miles |  | 0.027329 | 0.48427 | 34
Approved (Not Scoped) |  | 254452102 | MARIPOSA 2102 | MARIPOSA 2102CB | Top 250 Miles |  | 5.2539 | 0.47165 | 35
Approved (Not Scoped) |  | 254452101 | MARIPOSA 2101 | MARIPOSA 210197142 | Top 250 Miles |  | 4.6029 | 0.47122 | 36
Approved (Not Scoped) |  | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | Top 250 Miles |  | 23.1653 | 0.46772 | 37
Approved (Not Scoped) |  | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101481876 | Top 250 Miles |  | 0.8534 | 0.46769 | 38
Approved (Not Scoped) |  | 102541101 | VOLTA 1101 | VOLTA 110149742 | Top 250 Miles |  | 3.4766 | 0.46433 | 39
Approved (Not Scoped) |  | 14241101 | SUNOL 1101 | SUNOL 110148180 | Top 250 Miles |  | 0.013145 | 0.46103 | 40
Approved (Not Scoped) |  | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110246012 | Top 250 Miles |  | 0.63713 | 0.45557 | 41
Approved (Not Scoped) |  | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | Top 250 Miles |  | 14.6602 | 0.44642 | 42
Approved (Not Scoped) |  | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110564118 | Top 250 Miles |  | 1.6451 | 0.44262 | 43
Approved (Not Scoped) |  | 82931101 | POINT MORETTI 1101 | POINT MORETTI 1101CB | Top 250 Miles |  | 0.012787 | 0.44218 | 44
Approved (Not Scoped) |  | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | Top 250 Miles |  | 5.7104 | 0.4353 | 45
Approved (Not Scoped) |  | 14592105 | BRENTWOOD 2105 | BRENTWOOD 210596324 | Top 250 Miles |  | 0.48214 | 0.4317 | 46
Approved (Not Scoped) |  | 14052101 | NORTH DUBLIN 2101 | NORTH DUBLIN 2101CB | Top 250 Miles |  | 1.7629 | 0.42859 | 47
Approved (Not Scoped) |  | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | Top 250 Miles |  | 18.6049 | 0.42526 | 48
Approved (Not Scoped) |  | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | Top 250 Miles |  | 57.1429 | 0.42185 | 49
Approved (Not Scoped) |  | 254452102 | MARIPOSA 2102 | MARIPOSA 2102440236 | Top 250 Miles |  | 4.2727 | 0.4205 | 50
Approved (Not Scoped) |  | 42141101 | CLEAR LAKE 1101 | CLEAR LAKE 1101881362 | Top 250 Miles |  | 0.29834 | 0.41959 | 51
Approved (Not Scoped) |  | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | Top 250 Miles |  | 7.8323 | 0.41883 | 52
Approved (Not Scoped) |  | 63591105 | VACA DIXON 1105 | VACA DIXON 1105965390 | Top 250 Miles |  | 0.75147 | 0.41415 | 53
Approved (Not Scoped) |  | 163541101 | OLETA 1101 | OLETA 1101754718 | Top 250 Miles |  | 2.8841 | 0.40712 | 54
Approved (Not Scoped) |  | 42711101 | CALISTOGA 1101 | CALISTOGA 1101CB | Top 250 Miles |  | 0.13777 | 0.40561 | 55
Approved (Not Scoped) | 35062376 | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | Top 20% MAVF CPZ | 11 | 10.847 | 0.27855 | 159
Approved (Not Scoped) | 35062375 | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | Top 20% MAVF CPZ | 12.03 | 17.8687 | 0.24281 | 227
Approved (Not Scoped) | 35062374 | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | Top 20% MAVF CPZ | 8.53 | 17.8687 | 0.24281 | 227
Approved (Not Scoped) | 31354988 | 42301101 | TULUCAY 1101 | TULUCAY 1101628 | Top 20% MAVF CPZ | 1.9034 | 4.1726 | 0.19686 | 338
Approved (Not Scoped) | 35054184 | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | Top 20% MAVF CPZ | 4.9 | 9.1336 | 0.12922 | 606
Approved (Not Scoped) | 35026643 | 152261105 | DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 11052102 | Top 20% MAVF CPZ | 1.402 | 37.4816 | 0.11621 | 666
Approved (Not Scoped) | 74024660 | 42711101 | CALISTOGA 1101 | CALISTOGA 1101734 | Top 20% MAVF CPZ | 0.961 | 13.7047 | 0.11348 | 683
Approved (Not Scoped) | 35075103 | 163451701 | FROGTOWN 1701 | FROGTOWN 17011623 | Top 20% MAVF CPZ | 0.59 | 15.2605 | 0.1076 | 721
Approved (Not Scoped) | 35137590 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101CB | ECOP | 0.53 | 4.731 | 0.36174 | 86
Approved (Not Scoped) | 35191319 | 42991105 | LAS GALLINAS A 1105 | LAS GALLINAS A 110599904 | ECOP | 0.76 | 5.5621 | 0.25006 | 215
Approved (Not Scoped) | 35192284 | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | ECOP | 5.89 | 30.3762 | 0.22347 | 279
Approved (Not Scoped) | 35137593 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 11014646 | ECOP | 1.38 | 18.5633 | 0.19983 | 328
Approved (Not Scoped) | 35137596 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 11014646 | ECOP | 0.97 | 18.5633 | 0.19983 | 328
Approved (Not Scoped) | 35192280 | 12022212 | CLAYTON 2212 | CLAYTON 221296224 | ECOP | 2.38 | 19.3992 | 0.18755 | 377
Approved (Not Scoped) | 35192281 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | ECOP | 5.2 | 10.6994 | 0.1603 | 468
Approved (Not Scoped) | 35192282 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | ECOP | 5 | 10.6994 | 0.1603 | 468
Approved (Not Scoped) | 35174478 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | ECOP | 8.17 | 27.4082 | 0.15935 | 474
Approved (Not Scoped) | 35174479 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | ECOP | 7 | 27.4082 | 0.15935 | 474
Approved (Not Scoped) | 35174501 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | ECOP | 7 | 27.4082 | 0.15935 | 474
Approved (Not Scoped) | 35192292 | 42561107 | FULTON 1107 | FULTON 1107604 | ECOP | 2.6 | 17.4386 | 0.12169 | 637
Approved (Not Scoped) | 35191383 | 43432102 | SILVERADO 2102 | SILVERADO 210258626 | ECOP | 1.05 | 15.2217 | 0.117 | 663
Approved (Not Scoped) | 35191318 | 43432102 | SILVERADO 2102 | SILVERADO 210258626 | ECOP | 1.11 | 15.2217 | 0.117 | 663
For Approval |  | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | ECOP | 2.59 | 44.1915 | 0.092281 | 811
For Approval |  | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | ECOP | 2.18 | 44.1915 | 0.092281 | 811
For Approval |  | 43292102 | PUEBLO 2102 | PUEBLO 2102792 | ECOP | 2.13 | 19.3407 | 0.073389 | 951
For Approval | 35145540 | 163451702 | FROGTOWN 1702 | FROGTOWN 1702CB | PSPS - Scoped | 1.09 | 1.4614 | 0.039234 | 1316
For Approval | 35145524 | 43321103 | RINCON 1103 | RINCON 1103CB | PSPS - Scoped | 0.72 | 2.4433 | 0.016461 | 1755
For Approval | 35145525 | 43321104 | RINCON 1104 | RINCON 1104CB | PSPS - Scoped | 1.78 | 0.56024 | 4.3928e-06 | 3302
For Approval |  | 103191101 | BANGOR 1101 | BANGOR 1101979830 | PSPS - Not Scoped |  | 0.42309 | 0.3972 | 59
For Approval |  | 103191101 | BANGOR 1101 | BANGOR 110180670 | PSPS - Not Scoped |  | 14.4199 | 0.27059 | 179
For Approval |  | 103191101 | BANGOR 1101 | BANGOR 110131502 | PSPS - Not Scoped |  | 11.8734 | 0.24429 | 225
For Approval |  | 103191101 | BANGOR 1101 | BANGOR 1101CB | PSPS - Not Scoped |  | 18.7561 | 0.19378 | 355
For Approval |  | 103191101 | BANGOR 1101 | BANGOR 110182350 | PSPS - Not Scoped |  | 19.6266 | 0.19196 | 363
For Approval |  | 103191101 | BANGOR 1101 | BANGOR 1101301886 | PSPS - Not Scoped |  | 2.635 | 0.15165 | 509
For Approval |  | 103191101 | BANGOR 1101 | BANGOR 1101870548 | PSPS - Not Scoped |  | 5.0876 | 0.13326 | 591
For Approval |  | 103191101 | BANGOR 1101 | BANGOR 11017446 | PSPS - Not Scoped |  | 43.5002 | 0.12828 | 613
For Approval |  | 103191101 | BANGOR 1101 | BANGOR 110155206 | PSPS - Not Scoped |  | 0 | 0.11351 | 682
For Approval |  | 103191101 | BANGOR 1101 | BANGOR 11011958 | PSPS - Not Scoped |  | 33.8504 | 0.096142 | 785
For Approval |  | 103191101 | BANGOR 1101 | BANGOR 11011804 | PSPS - Not Scoped |  | 42.8988 | 0.068197 | 994
For Approval |  | 103191101 | BANGOR 1101 | BANGOR 11011806 | PSPS - Not Scoped |  | 4.0291 | 0.024567 | 1567
For Approval |  | 42711102 | CALISTOGA 1102 | CALISTOGA 1102CB | PSPS - Not Scoped |  | 0.32187 | 0.095153 | 790
For Approval |  | 42711102 | CALISTOGA 1102 | CALISTOGA 1102141073 | PSPS - Not Scoped |  | 1.2408 | 0.065722 | 1014
For Approval |  | 42711102 | CALISTOGA 1102 | CALISTOGA 110266730 | PSPS - Not Scoped |  | 1.0586 | 0.064035 | 1027
For Approval |  | 42711102 | CALISTOGA 1102 | CALISTOGA 1102634 | PSPS - Not Scoped |  | 11.216 | 0.029373 | 1477
For Approval |  | 42711102 | CALISTOGA 1102 | CALISTOGA 1102769230 | PSPS - Not Scoped |  | 11.021 | 0.022338 | 1624
For Approval |  | 42711102 | CALISTOGA 1102 | CALISTOGA 1102705 | PSPS - Not Scoped |  | 0.38677 | 0.00021298 | 2828
For Approval |  | 42711102 | CALISTOGA 1102 | CALISTOGA 1102184814 | PSPS - Not Scoped |  | 0.42402 | 8.707e-06 | 3098
For Approval |  | 42711102 | CALISTOGA 1102 | CALISTOGA 1102960240 | PSPS - Not Scoped |  | 0.50732 | 8.0789e-06 | 3122
For Approval |  | 163541101 | OLETA 1101 | OLETA 1101754718 | PSPS - Not Scoped |  | 2.8841 | 0.40712 | 54
For Approval |  | 163541101 | OLETA 1101 | OLETA 1101CB | PSPS - Not Scoped |  | 0.084664 | 0.35138 | 95
For Approval |  | 163541101 | OLETA 1101 | OLETA 1101296804 | PSPS - Not Scoped |  | 3.2862 | 0.31954 | 119
For Approval |  | 163541101 | OLETA 1101 | OLETA 1101400470 | PSPS - Not Scoped |  | 0.20759 | 0.27287 | 174
For Approval |  | 163541101 | OLETA 1101 | OLETA 11011208 | PSPS - Not Scoped |  | 33.0009 | 0.19404 | 352
For Approval |  | 163541101 | OLETA 1101 | OLETA 11011217 | PSPS - Not Scoped |  | 14.1973 | 0.17295 | 426
For Approval |  | 163541101 | OLETA 1101 | OLETA 1101239062 | PSPS - Not Scoped |  | 12.193 | 0.14634 | 542
For Approval |  | 163541101 | OLETA 1101 | OLETA 110151740 | PSPS - Not Scoped |  | 15.5571 | 0.107 | 725
For Approval |  | 163541101 | OLETA 1101 | OLETA 110163500 | PSPS - Not Scoped |  | 0.20333 | 0.099652 | 767
For Approval |  | 163541101 | OLETA 1101 | OLETA 110113478 | PSPS - Not Scoped |  | 12.3348 | 0.062159 | 1041
For Approval |  | 163541101 | OLETA 1101 | OLETA 1101894006 | PSPS - Not Scoped |  | 0.39028 | 0.03239 | 1417
For Approval |  | 163011101 | MARTELL 1101 | MARTELL 1101CB | PSPS - Not Scoped |  | 5.879 | 0.067405 | 999
For Approval |  | 163011101 | MARTELL 1101 | MARTELL 11016074 | PSPS - Not Scoped |  | 3.6816 | 0.027132 | 1511
For Approval |  | 163011101 | MARTELL 1101 | MARTELL 110111244 | PSPS - Not Scoped |  | 20.6924 | 0.01399 | 1822
For Approval |  | 163011101 | MARTELL 1101 | MARTELL 110198374 | PSPS - Not Scoped |  | 0.8271 | 0.011616 | 1898
For Approval |  | 163011101 | MARTELL 1101 | MARTELL 110191216 | PSPS - Not Scoped |  | 40.579 | 0.010587 | 1936
For Approval |  | 153081112 | PLACERVILLE 1112 | PLACERVILLE 1112CB | PSPS - Not Scoped |  | 8.513 | 0.0065148 | 2123
For Approval |  | 153081112 | PLACERVILLE 1112 | PLACERVILLE 111219712 | PSPS - Not Scoped |  | 12.9125 | 0.0064118 | 2135
For Approval |  | 153081112 | PLACERVILLE 1112 | PLACERVILLE 111219742 | PSPS - Not Scoped |  | 6.5567 | 0.0025093 | 2412
For Approval |  | 42711102 | CALISTOGA 1102 | CALISTOGA 1102CB | PSPS - Not Scoped |  | 0.32187 | 0.095153 | 790
For Approval |  | 42711102 | CALISTOGA 1102 | CALISTOGA 1102141073 | PSPS - Not Scoped |  | 1.2408 | 0.065722 | 1014
For Approval |  | 42711102 | CALISTOGA 1102 | CALISTOGA 110266730 | PSPS - Not Scoped |  | 1.0586 | 0.064035 | 1027
For Approval |  | 42711102 | CALISTOGA 1102 | CALISTOGA 1102634 | PSPS - Not Scoped |  | 11.216 | 0.029373 | 1477
For Approval |  | 42711102 | CALISTOGA 1102 | CALISTOGA 1102769230 | PSPS - Not Scoped |  | 11.021 | 0.022338 | 1624
For Approval |  | 42711102 | CALISTOGA 1102 | CALISTOGA 1102705 | PSPS - Not Scoped |  | 0.38677 | 0.00021298 | 2828
For Approval |  | 42711102 | CALISTOGA 1102 | CALISTOGA 1102184814 | PSPS - Not Scoped |  | 0.42402 | 8.707e-06 | 3098
For Approval |  | 42711102 | CALISTOGA 1102 | CALISTOGA 1102960240 | PSPS - Not Scoped |  | 0.50732 | 8.0789e-06 | 3122
For Approval |  | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101806 | PSPS - Not Scoped |  | 11.2762 | 0.030867 | 1446
For Approval |  | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101804 | PSPS - Not Scoped |  | 21.8915 | 0.016525 | 1753
For Approval |  | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101CB | PSPS - Not Scoped |  | 4.3721 | 0.014057 | 1817
For Approval |  | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101808 | PSPS - Not Scoped |  | 6.1786 | 0.010361 | 1944
For Approval |  | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | PSPS - Not Scoped |  | 4.1491 | 0.0088541 | 2010
For Approval |  | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101978 | PSPS - Not Scoped |  | 13.9579 | 0.00055148 | 2720
For Approval |  | 152101101 | ALLEGHANY 1101 | ALLEGHANY 11011101/2 | PSPS - Not Scoped |  | 0.020437 | 1.7836e-05 | 2977
For Approval |  | 152101101 | ALLEGHANY 1101 | ALLEGHANY 11011101/2 | PSPS - Not Scoped |  | 0.020437 | 1.7836e-05 | 2977
For Approval |  | 43071101 | DUNBAR 1101 | DUNBAR 11014817 | PSPS - Not Scoped |  | 3.1568 | 0.019666 | 1677
For Approval |  | 43071101 | DUNBAR 1101 | DUNBAR 1101416 | PSPS - Not Scoped |  | 2.6414 | 0.019316 | 1684
For Approval |  | 43071101 | DUNBAR 1101 | DUNBAR 110179086 | PSPS - Not Scoped |  | 6.8083 | 0.018179 | 1701
For Approval |  | 43071101 | DUNBAR 1101 | DUNBAR 110147964 | PSPS - Not Scoped |  | 6.5107 | 0.014662 | 1794
For Approval |  | 43071101 | DUNBAR 1101 | DUNBAR 1101302 | PSPS - Not Scoped |  | 8.7659 | 0.013839 | 1826
For Approval |  | 43071101 | DUNBAR 1101 | DUNBAR 1101CB | PSPS - Not Scoped |  | 3.1203 | 0.007993 | 2048
For Approval |  | 43071101 | DUNBAR 1101 | DUNBAR 1101343 | PSPS - Not Scoped |  | 4.4381 | 0.0075606 | 2069
For Approval |  | 43071101 | DUNBAR 1101 | DUNBAR 1101160 | PSPS - Not Scoped |  | 2.7777 | 0.0024952 | 2414
For Approval |  | 43071101 | DUNBAR 1101 | DUNBAR 110113481 | PSPS - Not Scoped |  | 0 | 0.0016289 | 2534
For Approval |  | 43071101 | DUNBAR 1101 | DUNBAR 1101234 | PSPS - Not Scoped |  | 3.4708 | 0.0015051 | 2556
For Approval |  | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | PSPS - Not Scoped |  | 5.7104 | 0.4353 | 45
For Approval |  | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 2101CB | PSPS - Not Scoped |  | 24.9941 | 0.38665 | 68
For Approval |  | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21011350 | PSPS - Not Scoped |  | 21.7526 | 0.27537 | 169
For Approval |  | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21011102 | PSPS - Not Scoped |  | 43.4367 | 0.14479 | 548
For Approval |  | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 210135466 | PSPS - Not Scoped |  | 7.3565 | 0.095562 | 787
For Approval |  | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 210151584 | PSPS - Not Scoped |  | 21.7785 | 0.057318 | 1090
For Approval |  | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 210192474 | PSPS - Not Scoped |  | 15.1059 | 0.046937 | 1212
For Approval |  | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21011346 | PSPS - Not Scoped |  | 30.8214 | 0.035841 | 1357
For Approval |  | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21011130 | PSPS - Not Scoped |  | 20.0341 | 0.031834 | 1433
For Approval |  | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21011180 | PSPS - Not Scoped |  | 12.9566 | 0.020771 | 1656
For Approval |  | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21012422 | PSPS - Not Scoped |  | 8.671 | 0.018043 | 1706
For Approval |  | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21011184 | PSPS - Not Scoped |  | 11.6971 | 0.0048403 | 2212
For Approval |  | 152481110 | BRUNSWICK 1110 | BRUNSWICK 11102664 | PSPS - Not Scoped |  | 8.0242 | 0.066185 | 1011
For Approval |  | 152481110 | BRUNSWICK 1110 | BRUNSWICK 111061602 | PSPS - Not Scoped |  | 9.8175 | 0.014648 | 1796
For Approval |  | 152481110 | BRUNSWICK 1110 | BRUNSWICK 1110CB | PSPS - Not Scoped |  | 0.0034177 | 0.0064174 | 2134
For Approval |  | 152481110 | BRUNSWICK 1110 | BRUNSWICK 111094368 | PSPS - Not Scoped |  | 0.37065 | 0.0040353 | 2254
For Approval |  | 152481110 | BRUNSWICK 1110 | BRUNSWICK 111063100 | PSPS - Not Scoped |  | 4.0969 | 0.00023675 | 2817
For Approval |  | 152481110 | BRUNSWICK 1110 | BRUNSWICK 11103907 | PSPS - Not Scoped |  | 0.89367 | 3.1747e-05 | 2928
For Approval |  | 152481110 | BRUNSWICK 1110 | BRUNSWICK 111095576 | PSPS - Not Scoped |  | 0 | 1.5765e-05 | 2999
For Approval |  | 254421101 | OAKHURST 1101 | OAKHURST 1101636114 | PSPS - Not Scoped |  | 20.4936 | 0.26702 | 183
For Approval |  | 254421101 | OAKHURST 1101 | OAKHURST 110110090 | PSPS - Not Scoped |  | 44.0886 | 0.17437 | 421
For Approval |  | 254421101 | OAKHURST 1101 | OAKHURST 11015490 | PSPS - Not Scoped |  | 25.0102 | 0.14657 | 541
For Approval |  | 254421101 | OAKHURST 1101 | OAKHURST 1101CB | PSPS - Not Scoped |  | 2.3149 | 0.086583 | 847
For Approval |  | 102911109 | WYANDOTTE 1109 | WYANDOTTE 110932586 | PSPS - Not Scoped |  | 1.3417 | 0.52987 | 29
For Approval |  | 102911109 | WYANDOTTE 1109 | WYANDOTTE 1109702710 | PSPS - Not Scoped |  | 2.6641 | 0.24845 | 218
For Approval |  | 102911109 | WYANDOTTE 1109 | WYANDOTTE 110979932 | PSPS - Not Scoped |  | 22.0664 | 0.20828 | 311
For Approval |  | 102911109 | WYANDOTTE 1109 | WYANDOTTE 11095607 | PSPS - Not Scoped |  | 4.5158 | 0.19115 | 368
For Approval |  | 102911109 | WYANDOTTE 1109 | WYANDOTTE 110913052 | PSPS - Not Scoped |  | 19.5651 | 0.18514 | 387
For Approval |  | 102911109 | WYANDOTTE 1109 | WYANDOTTE 11091520 | PSPS - Not Scoped |  | 4.1643 | 0.1287 | 609
For Approval |  | 102911109 | WYANDOTTE 1109 | WYANDOTTE 11091040 | PSPS - Not Scoped |  | 1.046 | 0.032999 | 1407
For Approval |  | 102911109 | WYANDOTTE 1109 | WYANDOTTE 11095973 | PSPS - Not Scoped |  | 0.085914 | 0.026544 | 1522
For Approval |  | 102911109 | WYANDOTTE 1109 | WYANDOTTE 110942650 | PSPS - Not Scoped |  | 0.90716 | 0.024082 | 1577
For Approval |  | 43211102 | HARTLEY 1102 | HARTLEY 1102385838 | PSPS - Not Scoped |  | 1.2468 | 0.21349 | 299
For Approval |  | 43211102 | HARTLEY 1102 | HARTLEY 1102524 | PSPS - Not Scoped |  | 0.24826 | 0.19015 | 369
For Approval |  | 43211102 | HARTLEY 1102 | HARTLEY 1102CB | PSPS - Not Scoped |  | 3.428 | 0.077778 | 918
For Approval |  | 43211102 | HARTLEY 1102 | HARTLEY 1102824 | PSPS - Not Scoped |  | 0.085463 | 0.00072721 | 2680
For Approval |  | 153082106 | PLACERVILLE 2106 | PLACERVILLE 2106935216 | PSPS - Not Scoped |  | 21.0371 | 0.079474 | 904
For Approval |  | 153082106 | PLACERVILLE 2106 | PLACERVILLE 2106CB | PSPS - Not Scoped |  | 6.554 | 0.050873 | 1168
For Approval |  | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210692012 | PSPS - Not Scoped |  | 18.5175 | 0.044304 | 1238
For Approval |  | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21067522 | PSPS - Not Scoped |  | 67.3656 | 0.035529 | 1363
For Approval |  | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21062224 | PSPS - Not Scoped |  | 10.51 | 0.032512 | 1415
For Approval |  | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210619552 | PSPS - Not Scoped |  | 21.3424 | 0.029928 | 1462
For Approval |  | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21069712 | PSPS - Not Scoped |  | 24.7147 | 0.021241 | 1646
For Approval |  | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | PSPS - Not Scoped |  | 43.2776 | 0.020262 | 1666
For Approval |  | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | PSPS - Not Scoped |  | 49.4989 | 0.0064469 | 2131
For Approval |  | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210623190 | PSPS - Not Scoped |  | 3.6786 | 0.0023536 | 2430
For Approval |  | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210619732 | PSPS - Not Scoped |  | 9.2596 | 1.6359e-05 | 2992
For Approval | 35052731 | 82841101 | BIG BASIN 1101 | BIG BASIN 110110296 | DSDD | 1.47 | 14.4211 | 0.0021702 | 2456
For Approval | 35052737 | 163661701 | MIWUK 1701 | MIWUK 1701953336 | DSDD | 1.587 | 11.8581 | 0.0038168 | 2267
For Approval | 35094513 | 162821702 | STANISLAUS 1702 | STANISLAUS 17021804 | DSDD | 1.92 | 8.3797 | 0.00058985 | 2712
For Approval |  | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | Remote Grid | 0.7 | 49.4989 | 0.0064469 | 2131
For Approval |  | 254061102 | DUNLAP 1102 | DUNLAP 1102778286 | Remote Grid | 2.6 | 2.6029 | 0.0004909 | 2738
For Approval |  | 254421101 | OAKHURST 1101 | OAKHURST 110110090 | Remote Grid | 1.4 | 44.0886 | 0.17437 | 421
For Approval |  | 254452101 | MARIPOSA 2101 | MARIPOSA 210135244 | Remote Grid | 0.99 | 17.4635 | 0.17286 | 428
Approved (Not Scoped) |  | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | Line Removal | 0.14205 | 43.2776 | 0.020262 | 1666
Approved (Not Scoped) |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | Line Removal | 0.29042 | 22.4168 | 0.012814 | 1849
Approved (Not Scoped) |  | 102931101 | COTTONWOOD 1101 | COTTONWOOD 11011610 | Line Removal | 0.26683 | 38.4226 | 0.15996 | 470
Approved (Not Scoped) |  | 103321101 | CEDAR CREEK 1101 | CEDAR CREEK 11011664 | Line Removal | 0.13743 | 29.572 | 0.22209 | 281
Approved (Not Scoped) |  | 103321101 | CEDAR CREEK 1101 | CEDAR CREEK 11011608 | Line Removal | 0.10502 | 33.4541 | 0.099644 | 768
Approved (Not Scoped) |  | 103351101 | DESCHUTES 1101 | DESCHUTES 11011580 | Line Removal | 0.096355 | 47.4617 | 0.18779 | 375
Approved (Not Scoped) |  | 103351101 | DESCHUTES 1101 | DESCHUTES 11011580 | Line Removal | 0.045927 | 47.4617 | 0.18779 | 375
Approved (Not Scoped) |  | 103351101 | DESCHUTES 1101 | DESCHUTES 11011580 | Line Removal | 0.12204 | 47.4617 | 0.18779 | 375
Approved (Not Scoped) |  | 103351104 | DESCHUTES 1104 | DESCHUTES 11041370 | Line Removal | 0.045971 | 13.5869 | 0.34561 | 100
Approved (Not Scoped) |  | 182981102 | JOLON 1102 | JOLON 1102CB | Line Removal | 0.086583 | 23.5798 | 0.058399 | 1075
Approved (Not Scoped) |  | 103351104 | DESCHUTES 1104 | DESCHUTES 11041370 | Line Removal | 0.030087 | 13.5869 | 0.34561 | 100
Approved (Not Scoped) |  | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | Line Removal | 0.18779 | 18.6049 | 0.42526 | 48
Approved (Not Scoped) |  | 103351104 | DESCHUTES 1104 | DESCHUTES 11041370 | Line Removal | 0.015091 | 13.5869 | 0.34561 | 100
Approved (Not Scoped) |  | 103441102 | JESSUP 1102 | JESSUP 110276068 | Line Removal | 0.055565 | 17.1802 | 0.070348 | 977
Approved (Not Scoped) |  | 103441102 | JESSUP 1102 | JESSUP 11023105 | Line Removal | 0.10463 | 6.0031 | 0.35978 | 89
Approved (Not Scoped) |  | 103441102 | JESSUP 1102 | JESSUP 1102158468 | Line Removal | 0.071985 | 0.69613 | 8.3063e-06 | 3114
Approved (Not Scoped) |  | 103441102 | JESSUP 1102 | JESSUP 110296554 | Line Removal | 0.091225 | 8.0717 | 0.22645 | 267
Approved (Not Scoped) |  | 103601101 | WHITMORE 1101 | WHITMORE 11011594 | Line Removal | 0.060437 | 24.2649 | 0.11449 | 678
Approved (Not Scoped) |  | 103601101 | WHITMORE 1101 | WHITMORE 11011598 | Line Removal | 0.040196 | 33.5165 | 0.09042 | 820
Approved (Not Scoped) |  | 103601101 | WHITMORE 1101 | WHITMORE 110145262 | Line Removal | 0.041775 | 28.7967 | 0.11334 | 685
Approved (Not Scoped) |  | 043051101 | MONTICELLO 1101 | MONTICELLO 1101630 | Line Removal | 0.091756 | 18.7154 | 0.10515 | 732
Approved (Not Scoped) |  | 043051101 | MONTICELLO 1101 | MONTICELLO 1101630 | Line Removal | 0.77059 | 18.7154 | 0.10515 | 732
Approved (Not Scoped) |  | 043051101 | MONTICELLO 1101 | MONTICELLO 1101630 | Line Removal | 0.16418 | 18.7154 | 0.10515 | 732
Approved (Not Scoped) |  | 103601101 | WHITMORE 1101 | WHITMORE 11011598 | Line Removal | 0.3018 | 33.5165 | 0.09042 | 820
Approved (Not Scoped) |  | 103601101 | WHITMORE 1101 | WHITMORE 1101N/A | Line Removal | 0.21042 | #N/A | #N/A | #N/A
Approved (Not Scoped) |  | 103601101 | WHITMORE 1101 | WHITMORE 110145262 | Line Removal | 0.145 | 28.7967 | 0.11334 | 685
Approved (Not Scoped) |  | 103601101 | WHITMORE 1101 | WHITMORE 11011598 | Line Removal | 0.068764 | 33.5165 | 0.09042 | 820
Approved (Not Scoped) |  | 182611103 | PASO ROBLES 1103 | PASO ROBLES 1103N50 | Line Removal | 0.75402 | 2.2288 | 0.30039 | 138
Approved (Not Scoped) |  | 252192105 | BEAR VALLEY 2105 | BEAR VALLEY 2105454432 | Line Removal | 1.3627 | 14.4352 | 0.08233 | 882
Approved (Not Scoped) |  | 043051101 | MONTICELLO 1101 | MONTICELLO 11014360 | Line Removal | 0.61669 | 7.564 | 0.10101 | 757
Approved (Not Scoped) |  | 043051101 | MONTICELLO 1101 | MONTICELLO 1101N/A | Line Removal | 0.14237 | #N/A | #N/A | #N/A
Approved (Not Scoped) |  | 043141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | Line Removal | 0.43374 | 27.7328 | 0.71618 | 14
Approved (Not Scoped) |  | 043361103 | HIGHLANDS 1103 | HIGHLANDS 1103828 | Line Removal | 0.083584 | 8.5948 | 0.31086 | 127
Approved (Not Scoped) |  | 102812101 | BIG MEADOWS 2101 | CRESCENT MILLS 2101CB | Line Removal | 3.5012 | 2.8253 | 0.029932 | 1461
Approved (Not Scoped) |  | 254452101 | MARIPOSA 2101 | MARIPOSA 2101752630 | Line Removal | 0.048292 | 18.9925 | 0.11205 | 700
Approved (Not Scoped) |  | 103321101 | CEDAR CREEK 1101 | CEDAR CREEK 11011664 | Line Removal | 0.16172 | 29.572 | 0.22209 | 281
Approved (Not Scoped) |  | 103321101 | CEDAR CREEK 1101 | CEDAR CREEK 1101CB | Line Removal | 0.063231 | 15.4219 | 0.18254 | 392
Approved (Not Scoped) |  | 102911105 | BIG BEND 1102 | BIG BEND 11021972 | Line Removal | 0.20374 | 21.2964 | 0.040961 | 1288
Approved (Not Scoped) |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | Line Removal | 0.18668 | 27.2173 | 0.050062 | 1176
Approved (Not Scoped) |  | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012016 | Line Removal | 0.0054208 | 0.09383 | 2.6614e-06 | 3445
Approved (Not Scoped) |  | 102541101 | VOLTA 1101 | VOLTA 110180454 | Line Removal | 0.26396 | 31.8338 | 0.14786 | 532
Approved (Not Scoped) |  | 043361103 | HIGHLANDS 1103 | HIGHLANDS 1103482 | Line Removal | 0.49348 | 24.5081 | 0.26975 | 181
Approved (Not Scoped) |  | 043191101 | REDBUD 1101 | REDBUD 1101323962 | Line Removal | 0.04269 | 20.5821 | 0.17389 | 423
Approved (Not Scoped) |  | 254452101 | MARIPOSA 2101 | MARIPOSA 210135244 | Line Removal | 0.1874 | 17.4635 | 0.17286 | 428
Approved (Not Scoped) |  | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y66 | Line Removal | 0.11163 | 16.9474 | 0.28279 | 153
Approved (Not Scoped) |  | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 2101CB | Line Removal | 0.0084041 | 2.106 | 0.00079069 | 2673
Approved (Not Scoped) |  | 254452101 | MARIPOSA 2101 | MARIPOSA 2101309438 | Line Removal | 0.078543 | 3.6909 | 0.12966 | 605
Approved (Not Scoped) |  | 252192105 | BEAR VALLEY 2105 | BEAR VALLEY 210521160 | Line Removal | 0.41252 | 23.7846 | 0.065187 | 1019
Approved (Not Scoped) |  | 103601101 | WHITMORE 1101 | WHITMORE 110145262 | Line Removal | 0.093922 | 28.7967 | 0.11334 | 685
Approved (Not Scoped) |  | 103351101 | DESCHUTES 1101 | DESCHUTES 11011654 | Line Removal | 0.259 | 17.5396 | 0.057486 | 1086
Approved (Not Scoped) |  | 103351101 | DESCHUTES 1101 | DESCHUTES 11011580 | Line Removal | 0.19099 | 47.4617 | 0.18779 | 375
Approved (Not Scoped) |  | 103321101 | CEDAR CREEK 1101 | CEDAR CREEK 11011656 | Line Removal | 0.14634 | 32.2308 | 0.039176 | 1318
Approved (Not Scoped) |  | 043292102 | PUEBLO 2102 | PUEBLO 2102792 | Line Removal | 0.045894 | 19.3407 | 0.073389 | 951
Approved (Not Scoped) |  | 024131102 | MENLO 1102 | MENLO 1102W80 | Line Removal | 0.07226 | 18.9504 | 0.12598 | 620