## Workbook Description
Enhanced Vegetation Management (EVM) Update
Information Updated as of 29 January, 2021
Contents
1 | Workbook Description - Overview of workbook contents and key definitions
2 | Summary Reporting - Summary statistics of the components of 2021 plan and execution of EVM work on mileage
3 | 2021 Certified EVM Plan - List of projects determined to be in scope of 2021 plan (composed of the WGC Approved Plan "No Regrets", Commitments, and Additional Optimized Miles
4 | PI In Progress Mileage Details - Patrol Inspections In Progress
5 | PI Complete Mileage Details - Patrol Inspections Completed
6 | WV Ready Mileage Details - Work Verification Ready
7 | WV Pass Mileage Details - Work Verification Passed
Glossary - In order of presentation
Summary Reporting
| Targeted Miles | Miles in the plan was approved on 11/13/20
| Commitments for 2021 | The Commitment Miles were approved on 12/18/20
| Additional Optimized Miles | The Additional Optimized Miles were approved on 12/18/20
| PI In Progress Inventory Trees Only Miles | Patrol Inspections being done with trees in area (not confirmed)
| PI In Progress No Trees Miles | Patrol Inspections being done with no trees in area (not confirmed)
| PI In Progress Tree Work Pending Miles | Patrol Inspections being done on areas where tree work is to be performed (not confirmed)
| PI Complete - Tree Work Pending Miles | Patrol Inspections completed on areas where tree work is to be performed (not confirmed)
| WV Ready - Inventory Trees Only Miles | Work Verification to be done on areas with trees (not confirmed)
| WV Ready - No Trees Miles | Work Verification to be done on areas with no trees (not confirmed)
| WV Ready - Tree Work Complete | Work Verification to be done on areas with trees that have finished tree work (not confirmed)
| WV Pass - Inventory Trees Only Miles | Work Verification completed on areas with trees (not confirmed)
| WV Pass - No Trees Miles | Work Verification completed on areas with no trees (not confirmed)
| WV Pass - Tree Work Complete Miles | Work Verification completed on areas with trees that have finished tree work (not confirmed)
2021 Certified EVM Plan
| REGION | Region where CPZ is located.
| DIVISION | Division where CPZ is located.
| CIRCUITNAME | Name of Circuit.
| PZ_IDX | Unique ID for each Circuit Protection Zone.
| CIRCUIT_PR | Circuit Protection Zone Name
| TARGET_MILES | Miles to be done in CPZ according to workplan.
| WGC_Approved_Plan | Indicator if CPZ is a part of the WGC No Regrets Mileage.
| 1800_Mile_Plan ($538M) | Indicator if CPZ is part of 2021 plan.
| Commitments | Indicator if CPZ is a part of the Commitments Mileage.
| Additional Optimized | Indicator if CPZ is a part of the Additional Optimized Mileage.
| RISK_GROUP_EVM | CPZ bucketed according total risk.
| RISK_VALUE_ADDRESSED | Available risk on the CPZ .

## Summary Reporting
Enhanced Vegetation Management (EVM) Summary Reporting
Information Updated as of 29 January, 2021
2021 Plan Summary
Total Miles
| Targeted Miles | 1055.7472
| Commitments for 2021 | 252.4867
| Additional Optimized Miles | 441.0996
| Total | 1749.3335
| PI in Progress Mileage Details | inventory the amount of trees in an area | nothing at risk in the areas | miles that need to be worked
|  | PI In Progress Inventory Trees Only Miles | PI In Progress No Trees Miles | PI In Progress Tree Work Pending Miles
| Total | 3.9715 | 19.1258 | 151.7108
| PI Complete Mileage Details | Doing the work or the work is in process for execution
PI Complete - Tree Work Pending Miles
| Total | 26.1757
| WV Ready Mileage Details | Validating the numbers being assessed
|  | WV Ready - Inventory Trees Only Miles | WV Ready - No Trees Miles | WV Ready - Tree Work Complete
| Total | 12.5267 | 8.0931 | 8.4131
WV Pass Mileage Details
|  | WV Pass - Inventory Trees Only Miles | WV Pass - No Trees Miles | WV Pass - Tree Work Complete Miles
| Total | 4.4769 | 2.3546 | 6.2604
8134.8677
2500
Top 20% CPZ
EVM Projects that fall outside the top 20% represent CPZs which PG&E had made commitments to the community (e.g., Santa Cruz, Nevada City), as well as a few projects prioritized based on the tree weighted risk.

## 2021 Certified EVM Plan
Region where CPZ is located. | Division where CPZ is located. | Name of Circuit. | Unique ID for each Circuit Protection Zone. | Circuit Protection Zone Name | Miles to be done in CPZ according to workplan. | Indicator if CPZ is a part of the WGC No Regrets Mileage. | Indicator if CPZ is part of 2021 plan. | Indicator if CPZ is a part of the Commitments Mileage. | Indicator if CPZ is a part of the Additional Optimized Mileage. | CPZ bucketed according total risk. | Available risk on the CPZ .
REGION | DIVISION | CIRCUITNAME | PZ_IDX | CIRCUIT_PR | TARGET_MILES | WGC_Approved_Plan | 1800_Mile_Plan ($538M) | Commitments | Additional Optimized | RISK_GROUP_EVM | RISK_VALUE_ADDRESSED
North Coast | NC_North Coast | RIO DELL 1102 | 6060 | RIO DELL 11024230 | 22.7074 | 1 | 1 | 0 | 0 | 1. <= 10% | 18.5803
Sierra | SI_Sierra | APPLE HILL 2102 | 3901 | APPLE HILL 2102circuit_breaker | 37.2691 | 0 | 1 | 0 | 1 | 1. <= 10% | 25.2589
Central Valley | YO_Yosemite | OAKHURST 1101 | 2763 | OAKHURST 110110090 | 26.661 | 1 | 1 | 0 | 0 | 1. <= 10% | 24.8226
North Coast | HU_Humboldt | FORT SEWARD 1121 | 6600 | FORT SEWARD 11211690 | 10.4326 | 1 | 1 | 0 | 0 | 1. <= 10% | 10.8257
North Coast | HU_Humboldt | MIDDLETOWN 1101 | 6356 | MIDDLETOWN 1101622 | 11.285 | 1 | 1 | 0 | 0 | 1. <= 10% | 26.84
North Valley | NV_North Valley | OREGON TRAIL 1104 | 1601 | OREGON TRAIL 11041574 | 16.1627 | 1 | 1 | 0 | 0 | 1. <= 10% | 41.5016
North Valley | NV_North Valley | BIG BEND 1102 | 3547 | BIG BEND 11021972 | 21.1589 | 0 | 1 | 0 | 1 | 1. <= 10% | 8.028
Sierra | SI_Sierra | HIGGINS 1109 | 5504 | HIGGINS 110950072 | 51.4699 | 1 | 1 | 0 | 0 | 1. <= 10% | 42.0939
North Valley | NV_North Valley | DESCHUTES 1101 | 2237 | DESCHUTES 11011580 | 45.4328 | 1 | 1 | 0 | 0 | 1. <= 10% | 20.4631
Sierra | SI_Sierra | DIAMOND SPRINGS 1105 | 3079 | DIAMOND SPRINGS 11057722 | 48.4366 | 0 | 1 | 0 | 1 | 1. <= 10% | 27.443
North Valley | NV_North Valley | CHALLENGE 1102 | 5557 | CHALLENGE 11021064 | 19.8066 | 0 | 1 | 0 | 1 | 1. <= 10% | 9.1991
Central Valley | YO_Yosemite | OAKHURST 1101 | 1973 | OAKHURST 11015490 | 10.1473 | 0 | 1 | 0 | 1 | 1. <= 10% | 15.937
Sierra | SI_Sierra | SHINGLE SPRINGS 2109 | 2248 | SHINGLE SPRINGS 210913322 | 40.3987 | 1 | 1 | 0 | 0 | 1. <= 10% | 33.0717
North Valley | NV_North Valley | DESCHUTES 1104 | 3638 | DESCHUTES 11041370 | 14.0494 | 1 | 1 | 0 | 0 | 1. <= 10% | 37.0772
North Valley | NV_North Valley | STILLWATER 1102 | 4317 | STILLWATER 1102circuit_breaker | 25.5741 | 1 | 1 | 0 | 0 | 1. <= 10% | 21.6253
North Coast | HU_Humboldt | UKIAH 1111 | 3596 | UKIAH 1111534 | 18.2775 | 1 | 1 | 0 | 0 | 1. <= 10% | 18.9464
Sierra | SI_Sierra | WISE 1102 | 3716 | WISE 11022230 | 23.6739 | 1 | 1 | 0 | 0 | 1. <= 10% | 34.0761
North Valley | NV_North Valley | OREGON TRAIL 1104 | 5783 | OREGON TRAIL 11041634 | 16.6307 | 1 | 1 | 0 | 0 | 1. <= 10% | 50.9274
North Valley | NV_North Valley | OREGON TRAIL 1104 | 662 | OREGON TRAIL 1104circuit_breaker | 10.7214 | 1 | 1 | 0 | 0 | 1. <= 10% | 17.03
Bay Area | NB_North Bay | PUEBLO 2103 | 3568 | PUEBLO 2103678 | 34.0994 | 0 | 1 | 0 | 1 | 1. <= 10% | 13.0698
North Valley | NV_North Valley | CEDAR CREEK 1101 | 39 | CEDAR CREEK 11011664 | 28.9169 | 1 | 1 | 0 | 0 | 1. <= 10% | 18.9423
Central Valley | FR_Fresno | AUBERRY 1101 | 4967 | AUBERRY 1101R2578 | 39.5581 | 1 | 1 | 0 | 0 | 1. <= 10% | 22.8753
Sierra | SI_Sierra | HIGGINS 1109 | 5121 | HIGGINS 1109circuit_breaker | 27.6797 | 1 | 1 | 0 | 0 | 1. <= 10% | 18.3144
North Coast | SO_Sonoma | FITCH MOUNTAIN 1113 | 7148 | FITCH MOUNTAIN 11136751 | 20.5953 | 0 | 1 | 0 | 1 | 1. <= 10% | 7.9553
Sierra | SI_Sierra | PIKE CITY 1101 | 3018 | PIKE CITY 1101circuit_breaker | 19.3667 | 0 | 1 | 0 | 1 | 1. <= 10% | 3.759
Central Valley | YO_Yosemite | MARIPOSA 2102 | 3795 | MARIPOSA 210210880 | 39.2456 | 1 | 1 | 0 | 0 | 1. <= 10% | 51.8448
Sierra | SA_Sacramento | VACA DIXON 1105 | 4403 | VACA DIXON 110540092 | 24.8036 | 1 | 1 | 0 | 0 | 1. <= 10% | 57.9125
North Coast | HU_Humboldt | BRIDGEVILLE 1102 | 4918 | BRIDGEVILLE 1102circuit_breaker | 25.1581 | 0 | 1 | 0 | 1 | 1. <= 10% | 4.4347
North Coast | HU_Humboldt | GARBERVILLE 1102 | 9323 | GARBERVILLE 110256048 | 4.8422 | 0 | 1 | 0 | 1 | 1. <= 10% | 2.5452
North Valley | NV_North Valley | CEDAR CREEK 1101 | 2436 | CEDAR CREEK 11011656 | 31.3055 | 0 | 1 | 0 | 1 | 1. <= 10% | 6.9273
Sierra | SI_Sierra | BELL 1107 | 1508 | BELL 11072400 | 10.9303 | 0 | 1 | 0 | 1 | 1. <= 10% | 13.8736
North Coast | HU_Humboldt | LAYTONVILLE 1102 | 2529 | LAYTONVILLE 1102500 | 14.7133 | 1 | 1 | 0 | 0 | 1. <= 10% | 9.2215
Sierra | SI_Sierra | BANGOR 1101 | 749 | BANGOR 11017446 | 24.9468 | 0 | 1 | 0 | 1 | 1. <= 10% | 8.8686
Sierra | SI_Sierra | MOUNTAIN QUARRIES 2101 | 3848 | MOUNTAIN QUARRIES 2101circuit_breaker | 25.8396 | 1 | 1 | 0 | 0 | 1. <= 10% | 26.0302
North Valley | NV_North Valley | CEDAR CREEK 1101 | 3510 | CEDAR CREEK 11011608 | 32.8294 | 0 | 1 | 0 | 1 | 1. <= 10% | 12.83
Sierra | SI_Sierra | BELL 1107 | 1789 | BELL 110750172 | 5.6606 | 0 | 1 | 0 | 1 | 1. <= 10% | 9.0902
North Coast | HU_Humboldt | PHILO 1101 | 6519 | PHILO 110137222 | 25.1165 | 1 | 1 | 0 | 0 | 1. <= 10% | 11.3077
North Coast | HU_Humboldt | WILLITS 1103 | 1520 | WILLITS 110391810 | 26.0356 | 0 | 1 | 0 | 1 | 1. <= 10% | 4.3045
Central Coast | CC_Central Coast | BIG BASIN 1102 | 1416 | BIG BASIN 1102circuit_breaker | 7.5284 | 0 | 1 | 1 | 0 | 6. >50% | 0.12641
North Coast | SO_Sonoma | GEYSERVILLE 1101 | 2778 | GEYSERVILLE 1101166 | 11.1278 | 1 | 1 | 0 | 0 | 1. <= 10% | 9.9522
North Valley | NV_North Valley | RED BLUFF 1101 | 864 | RED BLUFF 11011334 | 39.9742 | 1 | 1 | 0 | 0 | 1. <= 10% | 43.7155
Central Valley | YO_Yosemite | OAKHURST 1103 | 1817 | OAKHURST 1103circuit_breaker | 26.5585 | 1 | 1 | 0 | 0 | 1. <= 10% | 19.3125
North Coast | HU_Humboldt | FRUITLAND 1142 | 8284 | FRUITLAND 114293234 | 10.6913 | 0 | 1 | 0 | 1 | 1. <= 10% | 0.94073
Sierra | SI_Sierra | BELL 1108 | 4798 | BELL 11082202 | 29.8174 | 1 | 1 | 0 | 0 | 1. <= 10% | 26.3011
North Coast | SO_Sonoma | SALMON CREEK 1101 | 6598 | SALMON CREEK 110188998 | 7.8739 | 1 | 1 | 0 | 0 | 1. <= 10% | 11.6778
North Coast | HU_Humboldt | LAYTONVILLE 1102 | 7640 | LAYTONVILLE 1102572 | 20.9059 | 0 | 1 | 0 | 1 | 1. <= 10% | 6.6374
Sierra | SI_Sierra | APPLE HILL 2102 | 1194 | APPLE HILL 21021532 | 36.914 | 0 | 1 | 0 | 1 | 1. <= 10% | 6.9968
North Valley | NV_North Valley | WYANDOTTE 1109 | 1486 | WYANDOTTE 110979932 | 21.1451 | 1 | 1 | 0 | 0 | 1. <= 10% | 23.4289
North Valley | NV_North Valley | STILLWATER 1102 | 6222 | STILLWATER 110248952 | 10.0246 | 1 | 1 | 0 | 0 | 1. <= 10% | 16.2746
Sierra | SI_Sierra | PENRYN 1103 | 1224 | PENRYN 11032198 | 17.0445 | 1 | 1 | 0 | 0 | 1. <= 10% | 23.2613
North Valley | NV_North Valley | DESCHUTES 1104 | 1665 | DESCHUTES 110449024 | 15.7625 | 1 | 1 | 0 | 0 | 1. <= 10% | 47.9874
North Valley | NV_North Valley | STILLWATER 1102 | 538 | STILLWATER 11021644 | 22.8153 | 1 | 1 | 0 | 0 | 1. <= 10% | 16.7746
Sierra | SA_Sacramento | VACAVILLE 1108 | 2360 | VACAVILLE 110838316 | 16.5822 | 1 | 1 | 0 | 0 | 1. <= 10% | 31.9111
Central Valley | FR_Fresno | AUBERRY 1102 | 204 | AUBERRY 1102circuit_breaker | 32.928 | 1 | 1 | 0 | 0 | 1. <= 10% | 42.968
Sierra | SI_Sierra | BRUNSWICK 1103 | 3632 | BRUNSWICK 11032784 | 14.5339 | 0 | 1 | 1 | 0 | 6. >50% | 0.00013761
Bay Area | NB_North Bay | LAS GALLINAS A 1105 | 7713 | LAS GALLINAS A 110599904 | 5.4655 | 1 | 1 | 0 | 0 | 1. <= 10% | 5.8391
North Valley | NV_North Valley | DESCHUTES 1104 | 1661 | DESCHUTES 11049718 | 20.3059 | 1 | 1 | 0 | 0 | 1. <= 10% | 27.7145
Sierra | SI_Sierra | BROWNS VALLEY 1101 | 7209 | BROWNS VALLEY 110193870 | 21.0303 | 1 | 1 | 0 | 0 | 1. <= 10% | 19.6578
North Valley | NV_North Valley | COTTONWOOD 1101 | 6616 | COTTONWOOD 110168190 | 23.6848 | 1 | 1 | 0 | 0 | 1. <= 10% | 27.6706
Central Valley | YO_Yosemite | OAKHURST 1103 | 4692 | OAKHURST 110363334 | 13.8756 | 1 | 1 | 0 | 0 | 1. <= 10% | 16.7655
Sierra | SI_Sierra | WISE 1102 | 105 | WISE 11022054 | 12.8886 | 1 | 1 | 0 | 0 | 1. <= 10% | 22.5588
Sierra | SI_Sierra | SHINGLE SPRINGS 2109 | 1980 | SHINGLE SPRINGS 210912392 | 14.6294 | 1 | 1 | 0 | 0 | 1. <= 10% | 11.1292
North Coast | HU_Humboldt | WILLITS 1102 | 3495 | WILLITS 1102circuit_breaker | 4.9256 | 1 | 1 | 0 | 0 | 1. <= 10% | 5.2993
Sierra | SI_Sierra | LINCOLN 1104 | 4729 | LINCOLN 11042070 | 21.0958 | 1 | 1 | 0 | 0 | 1. <= 10% | 18.6329
Central Valley | FR_Fresno | TIVY VALLEY 1107 | 6372 | TIVY VALLEY 1107584840 | 24.0636 | 1 | 1 | 0 | 0 | 1. <= 10% | 10.7204
North Valley | NV_North Valley | DESCHUTES 1104 | 1301 | DESCHUTES 1104circuit_breaker | 12.1854 | 1 | 1 | 0 | 0 | 1. <= 10% | 22.4208
Sierra | SI_Sierra | BRUNSWICK 1103 | 957 | BRUNSWICK 1103circuit_breaker | 5.2894 | 0 | 1 | 1 | 0 | 6. >50% | 2.2599e-05
Central Valley | YO_Yosemite | SAN JOAQUIN NO2 1103 | 1374 | SAN JOAQUIN #2 110310320 | 11.4659 | 1 | 1 | 0 | 0 | 1. <= 10% | 11.6645
Central Valley | YO_Yosemite | COARSEGOLD 2103 | 1577 | COARSEGOLD 210310820 | 25.5261 | 1 | 1 | 0 | 0 | 1. <= 10% | 32.3309
North Valley | NV_North Valley | DESCHUTES 1104 | 3707 | DESCHUTES 11049726 | 15.0013 | 1 | 1 | 0 | 0 | 1. <= 10% | 35.4739
Sierra | SI_Sierra | DIAMOND SPRINGS 1105 | 2148 | DIAMOND SPRINGS 110519910 | 18.5989 | 1 | 1 | 0 | 0 | 1. <= 10% | 17.5176
Sierra | SI_Sierra | BRUNSWICK 1104 | 4033 | BRUNSWICK 11041020 | 28.1614 | 0 | 1 | 1 | 0 | 4. >30 - 40% | 0.52549
Sierra | SI_Sierra | BRUNSWICK 1104 | 1085 | BRUNSWICK 11042112 | 18.3706 | 0 | 1 | 1 | 0 | 4. >30 - 40% | 0.82521
Central Coast | CC_Central Coast | CAMP EVERS 2105 | 1759 | CAMP EVERS 210510912 | 4.5447 | 0 | 1 | 1 | 0 | 6. >50% | 0.067156
North Valley | NV_North Valley | GIRVAN 1101 | 5926 | GIRVAN 11011330 | 30.511 | 0 | 1 | 1 | 0 | 1. <= 10% | 7.308
North Valley | NV_North Valley | GIRVAN 1101 | 5137 | GIRVAN 11011636 | 19.1061 | 0 | 1 | 1 | 0 | 3. >20 - 30% | 5.4261
North Valley | NV_North Valley | GIRVAN 1101 | 4039 | GIRVAN 1101323094 | 35.307 | 0 | 1 | 1 | 0 | 1. <= 10% | 11.098
North Valley | NV_North Valley | GIRVAN 1101 | 4392 | GIRVAN 11019732 | 20.0625 | 0 | 1 | 1 | 0 | 4. >30 - 40% | 3.2288
Central Coast | SJ_San Jose | MORGAN HILL 2105 | 3082 | MORGAN HILL 2105XR564 | 5.2131 | 0 | 1 | 1 | 0 | 4. >30 - 40% | 2.4234
North Valley | NV_North Valley | OREGON TRAIL 1103 | 2683 | OREGON TRAIL 11031500 | 7.5712 | 0 | 1 | 1 | 0 | 4. >30 - 40% | 1.0296
Central Coast | LP_Los Padres | PASO ROBLES 1103 | 6910 | PASO ROBLES 1103N58 | 0.51648 | 0 | 1 | 1 | 0 | 6. >50% | 1.0177
Central Coast | LP_Los Padres | PASO ROBLES 1104 | 2761 | PASO ROBLES 1104P02 | 0.10928 | 0 | 1 | 1 | 0 | 6. >50% | 0.17241
Central Coast | LP_Los Padres | PASO ROBLES 1107 | 7938 | PASO ROBLES 1107circuit_breaker | 0.64659 | 0 | 1 | 1 | 0 | 6. >50% | 0
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1107 | 4945 | SAN LUIS OBISPO 1107V60 | 15.1773 | 0 | 1 | 1 | 0 | 5. >40 - 50% | 1.5179
Central Coast | LP_Los Padres | SANTA YNEZ 1102 | 270 | SANTA YNEZ 1101circuit_breaker | 0.32576 | 0 | 1 | 1 | 0 | 6. >50% | 0
Central Coast | LP_Los Padres | ZACA 1102 | 8297 | SANTA YNEZ 1104circuit_breaker | 1.0943 | 0 | 1 | 1 | 0 | 4. >30 - 40% | 1.0291
Bay Area | NB_North Bay | SILVERADO 2104 | 5665 | SILVERADO 2104632 | 7.2991 | 0 | 1 | 1 | 0 | 1. <= 10% | 5.1022
Bay Area | NB_North Bay | SILVERADO 2104 | 4559 | SILVERADO 210478268 | 5.7636 | 0 | 1 | 1 | 0 | 2. >10 - 20% | 2.8603
Bay Area | DI_Diablo | SOBRANTE 1102 | 3496 | SOBRANTE 1102circuit_breaker | 10.6581 | 0 | 1 | 1 | 0 | 6. >50% | 0.0038248
Bay Area | PE_Peninsula | WOODSIDE 1101 | 5540 | WOODSIDE 11018974 | 11.2475 | 0 | 1 | 1 | 0 | 1. <= 10% | 2.6906
Central Coast | LP_Los Padres | ZACA 1102 | 2756 | ZACA 1102Y48 | 3.4494 | 0 | 1 | 1 | 0 | 5. >40 - 50% | 3.6543
1749.3335

## PI In Progress Mileage Details (hidden)
CIRCUIT NAME | PI IN PROGRESS INVENTORY TREES ONLY MILES | PI IN PROGRESS NO TREES MILES | PI IN PROGRESS TREE WORK PENDING MILES
AUBERRY 1101 | 0.051637 | 0.38347 | 6.7244
BANGOR 1101 | 0.25707 | 0.080156 | 10.3275
BELL 1108 | 0 | 0 | 0.054921
BIG BASIN 1102 | 0 | 0 | 0.025613
BIG BEND 1102 | 0.068886 | 0 | 0.1034
BRUNSWICK 1103 | 0 | 0.45353 | 1.2695
DESCHUTES 1104 | 0.83901 | 2.8744 | 9.0261
DIAMOND SPRINGS 1105 | 0 | 0 | 0
HIGGINS 1109 | 0.06418 | 10.447 | 62.1667
LINCOLN 1104 | 0.74747 | 3.3359 | 13.2415
MARIPOSA 2102 | 0 | 0 | 3.9385
MIDDLETOWN 1101 | 0.1473 | 0.8586 | 4.3467
MOUNTAIN QUARRIES 2101 | 1.2513 | 0.37404 | 2.2911
OAKHURST 1101 | 0.039958 | 0 | 13.352
OAKHURST 1103 | 0 | 0.013882 | 2.2049
OREGON TRAIL 1103 | 0 | 0 | 0.85684
OREGON TRAIL 1104 | 0 | 0 | 0.094731
PASO ROBLES 1103 | 0 | 0 | 0
PENRYN 1103 | 0 | 0 | 0.021011
PIKE CITY 1101 | 0 | 0.13006 | 0.54658
PUEBLO 2103 | 0.00019841 | 0.088238 | 1.7242
SAN LUIS OBISPO 1107 | 0 | 0 | 0.8852
SHINGLE SPRINGS 2109 | 0.48115 | 0 | 5.3847
SILVERADO 2104 | 0 | 0 | 1.5311
TIVY VALLEY 1107 | 0 | 0 | 5.6673
WOODSIDE 1101 | 0.023355 | 0.086594 | 5.9265
Totals: | 3.9715 | 19.1258 | 151.7108

## PI Complete Milage Details (hidden)
CIRCUIT NAME | PI COMPLETE - TREE WORK PENDING MILES
AUBERRY 1101 | 3.948
BANGOR 1101 | 0.057548
BELL 1108 | 0
BIG BASIN 1102 | 0
BIG BEND 1102 | 0.046205
BRUNSWICK 1103 | 0
DESCHUTES 1104 | 1.6321
DIAMOND SPRINGS 1105 | 1.2232
HIGGINS 1109 | 0
LINCOLN 1104 | 0
MARIPOSA 2102 | 2.342
MIDDLETOWN 1101 | 0.74094
MOUNTAIN QUARRIES 2101 | 3.8364
OAKHURST 1101 | 0.80134
OAKHURST 1103 | 0.34584
OREGON TRAIL 1103 | 1.4741
OREGON TRAIL 1104 | 2.6355
PASO ROBLES 1103 | 0
PENRYN 1103 | 0
PIKE CITY 1101 | 0
PUEBLO 2103 | 0.14324
SAN LUIS OBISPO 1107 | 0
SHINGLE SPRINGS 2109 | 1.0898
SILVERADO 2104 | 0.2218
TIVY VALLEY 1107 | 5.1492
WOODSIDE 1101 | 0.48832
Totals: | 26.1757

## WV Ready Mileage Details (hidden)
CIRCUIT NAME | WV READY - INVENTORY TREES ONLY MILES | WV READY - NO TREES MILES | WV READY - TREE WORK COMPLETE
DESCHUTES 1104 | 7.17 | 2.9956 | 2.901
HIGGINS 1109 | 0.05864 | 1.5024 | 0.025204
SHINGLE SPRINGS 2109 | 2.1049 | 1.2761 | 0.31133
MOUNTAIN QUARRIES 2101 | 1.2171 | 1.0919 | 0.020793
MARIPOSA 2102 | 0.73237 | 0.86414 | 0
SAN LUIS OBISPO 1107 | 0.12469 | 0.19212 | 0.095646
MIDDLETOWN 1101 | 0.34948 | 0.073563 | 0.45214
OAKHURST 1103 | 0.39995 | 0.041772 | 0
SILVERADO 2104 | 0.014259 | 0.039508 | 0.31073
PUEBLO 2103 | 0 | 0.008053 | 0.0078916
WOODSIDE 1101 | 0.0048508 | 0.0080131 | 0
AUBERRY 1101 | 0.077711 | 0 | 0
BANGOR 1101 | 0 | 0 | 0
BELL 1108 | 0 | 0 | 0
BIG BASIN 1102 | 0 | 0 | 0
BIG BEND 1102 | 0 | 0 | 0
BRUNSWICK 1103 | 2.472e-05 | 0 | 0
DIAMOND SPRINGS 1105 | 0.024943 | 0 | 0
LINCOLN 1104 | 0.12954 | 0 | 0
OAKHURST 1101 | 0 | 0 | 1.4773
OREGON TRAIL 1103 | 0 | 0 | 2.1462
OREGON TRAIL 1104 | 0.046717 | 0 | 0
PASO ROBLES 1103 | 0 | 0 | 0
PENRYN 1103 | 0 | 0 | 0
PIKE CITY 1101 | 0 | 0 | 0
TIVY VALLEY 1107 | 0.071543 | 0 | 0.66476
Totals: | 12.5267 | 8.0931 | 8.4131

## WV Pass Mileage Details (hidden)
CIRCUIT NAME | WV PASS - INVENTORY TREES ONLY MILES | WV PASS - NO TREES MILES | WV PASS - TREE WORK COMPLETE MILES
APPLE HILL 2102 | 0 | 0.00010992 | 0
LINCOLN 1104 | 0 | 0.21022 | 0
MARIPOSA 2102 | 2.7039 | 1.4483 | 0
MIDDLETOWN 1101 | 0.24953 | 0.25877 | 0.60129
OAKHURST 1101 | 0.012445 | 0.026807 | 3.6757
OAKHURST 1103 | 0.80857 | 0.025085 | 0
OREGON TRAIL 1103 | 0 | 0 | 0.16452
SHINGLE SPRINGS 2109 | 0.70248 | 0.38531 | 0.10012
TIVY VALLEY 1107 | 0 | 0 | 1.7188
Totals: | 4.4769 | 2.3546 | 6.2604

## EVM CPZ List (hidden)
Region | PZ_idx | pixel_count | mean_mavf_core_risk | feeder_id | feeder_name | circuit_protection_zone_id | primary_length_m_hftd_23 | Total mavf_core_risk | mean_mavf_core_risk_RANK | Primary_length_miles_hftd_232 | Cumulative Miles | Remaining Risk | Remaining Miles | Risk Value Addressed | Duplicate Check | 2021 EVM Plan - WGC No Regrets | 2021 EVM Plan - Commitments | 2021 EVM Plan - Additional Optimized
Central Coast | 8297 | 2 | 0.51453 | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 1104circuit_breaker | 295.2522 | 1.0291 | 683 | 0.18346 | 0.18346 | 5407.3082 | 1.0943 | 1.0291 | 1 | #N/A | 5407.3082 | #N/A
Sierra | 8244 | 2 | 0.41379 | 63681103 | PUTAH CREEK 1103 | PUTAH CREEK 11033783 | 329.1954 | 0.82757 | 750 | 0.20455 | 0.38801 | 5406.4807 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6700 | 9 | 0.39527 | 42661103 | WILLITS 1103 | WILLITS 1103966 | 1339.7772 | 3.5574 | 340 | 0.8325 | 1.2205 | 5402.9232 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4403 | 197 | 0.29397 | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | 37400.5677 | 57.9125 | 2 | 23.2396 | 24.4601 | 5345.0107 | 24.8036 | 57.9125 | 1 | 5345.0107 | #N/A | #N/A
Sierra | 7064 | 7 | 0.292 | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110246012 | 945.6535 | 2.044 | 491 | 0.5876 | 25.0477 | 5342.9667 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6204 | 2 | 0.2736 | 63172101 | MADISON 2101 | MADISON 21011975 | 127.6157 | 0.54719 | 877 | 0.079297 | 25.127 | 5342.4195 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2559 | 21 | 0.27112 | 102781101 | ELK CREEK 1101 | ELK CREEK 11012008 | 8128.4527 | 5.6936 | 245 | 5.0508 | 30.1778 | 5336.726 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3638 | 148 | 0.26179 | 103351104 | DESCHUTES 1104 | DESCHUTES 11041370 | 19292.4005 | 38.7456 | 16 | 11.9877 | 42.1656 | 5297.9803 | 14.0494 | 37.0772 | 1 | 5297.9803 | #N/A | #N/A
North Coast | 9535 | 2 | 0.25943 | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103circuit_breaker | 85.2366 | 0.51885 | 891 | 0.052964 | 42.2185 | 5297.4615 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3511 | 76 | 0.25486 | 63601108 | VACAVILLE 1108 | VACAVILLE 11088762 | 22706.5359 | 19.3692 | 65 | 14.1092 | 56.3277 | 5278.0922 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6336 | 47 | 0.24907 | 103351101 | DESCHUTES 1101 | DESCHUTES 1101circuit_breaker | 6460.1699 | 11.7062 | 128 | 4.0142 | 60.3419 | 5266.3861 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8993 | 2 | 0.23786 | 102541101 | VOLTA 1101 | VOLTA 110149742 | 5593.8568 | 0.47572 | 917 | 3.4759 | 63.8177 | 5265.9103 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5783 | 224 | 0.23311 | 103521104 | OREGON TRAIL 1104 | OREGON TRAIL 11041634 | 28112.1395 | 52.2161 | 4 | 17.4681 | 81.2858 | 5213.6942 | 16.6307 | 50.9274 | 1 | 5213.6942 | #N/A | #N/A
Sierra | 6125 | 64 | 0.22711 | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 11028352 | 8943.386 | 14.5349 | 100 | 5.5572 | 86.843 | 5199.1593 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4339 | 118 | 0.22707 | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y04 | 24112.9415 | 26.7943 | 38 | 14.9831 | 101.826 | 5172.3651 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4340 | 10 | 0.22681 | 42661103 | WILLITS 1103 | WILLITS 110337504 | 1413.5779 | 2.2681 | 454 | 0.87836 | 102.7044 | 5170.0969 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1665 | 216 | 0.22216 | 103351104 | DESCHUTES 1104 | DESCHUTES 110449024 | 25640.9937 | 47.9874 | 6 | 15.9326 | 118.637 | 5122.1095 | 15.7625 | 47.9874 | 1 | 5122.1095 | #N/A | #N/A
Central Valley | 5807 | 141 | 0.22154 | 254432104 | COARSEGOLD 2104 | COARSEGOLD 21046288 | 16779.965 | 31.2372 | 26 | 10.4266 | 129.0636 | 5090.8724 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2282 | 3 | 0.22048 | 102931101 | COTTONWOOD 1101 | COTTONWOOD 11011510 | 494.2929 | 0.66143 | 828 | 0.30714 | 129.3707 | 5090.211 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5985 | 107 | 0.21615 | 153652105 | SHINGLE SPRINGS 2105 | SHINGLE SPRINGS 210519522 | 15477.8093 | 23.1275 | 47 | 9.6175 | 138.9882 | 5067.0834 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6737 | 11 | 0.20515 | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110564118 | 2045.917 | 2.2567 | 457 | 1.2713 | 140.2594 | 5064.8268 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2021 | 225 | 0.20288 | 254432104 | COARSEGOLD 2104 | COARSEGOLD 21045310 | 28358.0547 | 45.6473 | 9 | 17.6209 | 157.8803 | 5019.1795 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1138 | 34 | 0.20023 | 13232105 | LONE TREE 2105 | LONE TREE 210521210 | 16983.4147 | 6.8077 | 209 | 10.553 | 168.4333 | 5012.3718 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2533 | 2 | 0.19892 | 63591105 | VACA DIXON 1105 | VACA DIXON 11059792 | 1598.1228 | 0.39784 | 959 | 0.99303 | 169.4263 | 5011.974 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1601 | 235 | 0.19694 | 103521104 | OREGON TRAIL 1104 | OREGON TRAIL 11041574 | 26331.2246 | 46.2816 | 8 | 16.3615 | 185.7878 | 4965.6923 | 16.1627 | 41.5016 | 1 | 4965.6923 | #N/A | #N/A
North Valley | 7507 | 65 | 0.19678 | 103441102 | JESSUP 1102 | JESSUP 11023105 | 9428.2851 | 12.7904 | 115 | 5.8585 | 191.6463 | 4952.9019 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6610 | 33 | 0.19496 | 103191101 | BANGOR 1101 | BANGOR 110155206 | 3897.0387 | 6.4338 | 221 | 2.4215 | 194.0678 | 4946.4681 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5931 | 166 | 0.18534 | 254432104 | COARSEGOLD 2104 | COARSEGOLD 21045525 | 20995.911 | 30.7671 | 27 | 13.0463 | 207.114 | 4915.7011 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6073 | 13 | 0.18481 | 43161101 | SALMON CREEK 1101 | SALMON CREEK 1101196 | 5757.7629 | 2.4025 | 441 | 3.5777 | 210.6917 | 4913.2985 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5498 | 119 | 0.18449 | 252062111 | SHEPHERD 2111 | SHEPHERD 2111R1400 | 29130.6459 | 21.9543 | 53 | 18.1009 | 228.7927 | 4891.3443 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 445 | 53 | 0.18431 | 192221101 | GARBERVILLE 1101 | GARBERVILLE 11011604 | 6822.8212 | 9.7685 | 158 | 4.2395 | 233.0322 | 4881.5758 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1661 | 152 | 0.18233 | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 26275.4179 | 27.7145 | 35 | 16.3268 | 249.3589 | 4853.8613 | 20.3059 | 27.7145 | 1 | 4853.8613 | #N/A | #N/A
North Coast | 3086 | 3 | 0.18138 | 42141101 | CLEAR LAKE 1101 | CLEAR LAKE 1101486 | 343.3545 | 0.54415 | 881 | 0.21335 | 249.5723 | 4853.3171 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2360 | 177 | 0.18029 | 63601108 | VACAVILLE 1108 | VACAVILLE 110838316 | 25488.4092 | 31.9111 | 25 | 15.8378 | 265.41 | 4821.406 | 16.5822 | 31.9111 | 1 | 4821.406 | #N/A | #N/A
North Valley | 190 | 624 | 0.17911 | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 92189.591 | 111.7647 | 1 | 57.2839 | 322.694 | 4709.6414 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7265 | 5 | 0.1776 | 63591101 | VACA DIXON 1101 | VACA DIXON 110118292 | 1339.9258 | 0.88798 | 732 | 0.83259 | 323.5266 | 4708.7534 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3707 | 202 | 0.17561 | 103351104 | DESCHUTES 1104 | DESCHUTES 11049726 | 24438.8213 | 35.4739 | 19 | 15.1856 | 338.7122 | 4673.2795 | 15.0013 | 35.4739 | 1 | 4673.2795 | #N/A | #N/A
Central Coast | 2761 | 1 | 0.17241 | 182611104 | PASO ROBLES 1104 | PASO ROBLES 1104P02 | 389.1275 | 0.17241 | 1202 | 0.24179 | 338.9539 | 4673.1071 | 0.10928 | 0.17241 | 1 | #N/A | 4673.1071 | #N/A
North Coast | 5502 | 15 | 0.17198 | 43211101 | HARTLEY 1101 | HARTLEY 1101658 | 4569.0388 | 2.5796 | 418 | 2.8391 | 341.793 | 4670.5275 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7007 | 5 | 0.17112 | 63801102 | JAMESON 1102 | JAMESON 11028842 | 757.4983 | 0.8556 | 743 | 0.47069 | 342.2637 | 4669.6719 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1301 | 135 | 0.16608 | 103351104 | DESCHUTES 1104 | DESCHUTES 1104circuit_breaker | 19511.2444 | 22.4208 | 52 | 12.1237 | 354.3874 | 4647.2511 | 12.1854 | 22.4208 | 1 | 4647.2511 | #N/A | #N/A
Central Coast | 819 | 238 | 0.16262 | 182681102 | ZACA 1102 | ZACA 1102Y54 | 53471.0661 | 38.7034 | 17 | 33.2254 | 387.6128 | 4608.5477 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4570 | 39 | 0.16097 | 43361103 | HIGHLANDS 1103 | HIGHLANDS 1103828 | 12064.542 | 6.2778 | 229 | 7.4966 | 395.1093 | 4602.2699 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6356 | 240 | 0.16032 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101622 | 25790.8227 | 38.4777 | 18 | 16.0257 | 411.135 | 4563.7921 | 11.285 | 26.84 | 1 | 4563.7921 | #N/A | #N/A
Central Coast | 6910 | 47 | 0.15925 | 182611103 | PASO ROBLES 1103 | PASO ROBLES 1103N58 | 7139.6018 | 7.4845 | 192 | 4.4363 | 415.5714 | 4556.3076 | 0.51648 | 1.0177 | 1 | #N/A | 4556.3076 | #N/A
Sierra | 733 | 124 | 0.15785 | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110267858 | 18688.4623 | 19.5736 | 61 | 11.6125 | 427.1838 | 4536.734 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6598 | 78 | 0.15666 | 43161101 | SALMON CREEK 1101 | SALMON CREEK 110188998 | 9919.7992 | 12.2196 | 120 | 6.1639 | 433.3477 | 4524.5143 | 7.8739 | 11.6778 | 1 | 4524.5143 | #N/A | #N/A
North Valley | 6517 | 75 | 0.15638 | 103451101 | KESWICK 1101 | KESWICK 110148480 | 17324.1107 | 11.7286 | 127 | 10.7647 | 444.1124 | 4512.7857 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3982 | 81 | 0.15291 | 103521102 | OREGON TRAIL 1102 | OREGON TRAIL 11021382 | 8802.4775 | 12.3855 | 117 | 5.4696 | 449.582 | 4500.4003 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 9488 | 2 | 0.15106 | 153612105 | CLARKSVILLE 2105 | CLARKSVILLE 2105circuit_breaker | 759.3509 | 0.30213 | 1035 | 0.47184 | 450.0538 | 4500.0981 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1239 | 2 | 0.15005 | 183052113 | TEMPLETON 2113 | TEMPLETON 2113circuit_breaker | 879.0751 | 0.30009 | 1041 | 0.54623 | 450.6001 | 4499.798 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6431 | 16 | 0.14976 | 63681103 | PUTAH CREEK 1103 | PUTAH CREEK 11033851 | 6216.3391 | 2.3961 | 442 | 3.8627 | 454.4627 | 4497.4019 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5096 | 65 | 0.14873 | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 110477098 | 16911.4845 | 9.6674 | 161 | 10.5083 | 464.971 | 4487.7345 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7698 | 2 | 0.14795 | 14422109 | CAYETANO 2109 | CAYETANO 2109MR186 | 547.3474 | 0.2959 | 1045 | 0.34011 | 465.3111 | 4487.4386 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5194 | 66 | 0.14727 | 183052113 | TEMPLETON 2113 | TEMPLETON 2113A20 | 10922.8343 | 9.7196 | 159 | 6.7871 | 472.0983 | 4477.719 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 204 | 307 | 0.14221 | 254151102 | AUBERRY 1102 | AUBERRY 1102circuit_breaker | 55632.597 | 43.659 | 12 | 34.5685 | 506.6668 | 4434.06 | 32.928 | 42.968 | 1 | 4434.06 | #N/A | #N/A
North Valley | 1336 | 10 | 0.13953 | 103541105 | RED BLUFF 1105 | RED BLUFF 11051564 | 1829.5964 | 1.3953 | 593 | 1.1369 | 507.8036 | 4432.6647 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2220 | 203 | 0.13854 | 254432104 | COARSEGOLD 2104 | COARSEGOLD 2104369777 | 29945.6871 | 28.1228 | 32 | 18.6074 | 526.411 | 4404.5419 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1883 | 23 | 0.13744 | 103461101 | PANORAMA 1101 | PANORAMA 1101circuit_breaker | 4988.6634 | 3.1611 | 378 | 3.0998 | 529.5108 | 4401.3808 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2424 | 84 | 0.13658 | 255292108 | WOODWARD 2108 | WOODWARD 2108R2860 | 17727.1373 | 11.4725 | 131 | 11.0151 | 540.5259 | 4389.9083 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2963 | 69 | 0.13588 | 103351104 | DESCHUTES 1104 | DESCHUTES 11041582 | 9068.1485 | 9.3758 | 162 | 5.6347 | 546.1606 | 4380.5325 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4059 | 101 | 0.13537 | 102931103 | COTTONWOOD 1103 | COTTONWOOD 11031344 | 15508.3048 | 13.6725 | 103 | 9.6364 | 555.797 | 4366.86 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 105 | 170 | 0.13473 | 152271102 | WISE 1102 | WISE 11022054 | 20797.7702 | 22.9035 | 50 | 12.9231 | 568.7202 | 4343.9565 | 12.8886 | 22.5588 | 1 | 4343.9565 | #N/A | #N/A
Sierra | 891 | 28 | 0.13302 | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 1102circuit_breaker | 7914.4674 | 3.7245 | 326 | 4.9178 | 573.638 | 4340.232 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1911 | 48 | 0.13276 | 42661104 | WILLITS 1104 | WILLITS 1104circuit_breaker | 4814.9119 | 6.3727 | 224 | 2.9918 | 576.6298 | 4333.8593 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3795 | 394 | 0.13159 | 254452102 | MARIPOSA 2102 | MARIPOSA 210210880 | 63141.8494 | 51.8448 | 5 | 39.2345 | 615.8643 | 4282.0145 | 39.2456 | 51.8448 | 1 | 4282.0145 | #N/A | #N/A
Central Valley | 5945 | 18 | 0.13127 | 254432104 | COARSEGOLD 2104 | COARSEGOLD 2104570682 | 3262.933 | 2.3629 | 445 | 2.0275 | 617.8918 | 4279.6517 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3080 | 39 | 0.13114 | 42571102 | MOLINO 1102 | MOLINO 110279306 | 5037.4953 | 5.1143 | 261 | 3.1302 | 621.022 | 4274.5373 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3587 | 76 | 0.13104 | 254151102 | AUBERRY 1102 | AUBERRY 1102R309 | 13825.8859 | 9.9592 | 151 | 8.591 | 629.613 | 4264.5782 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 890 | 162 | 0.13084 | 102931102 | COTTONWOOD 1102 | COTTONWOOD 1102circuit_breaker | 25573.0555 | 21.1966 | 55 | 15.8904 | 645.5033 | 4243.3816 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3716 | 266 | 0.13059 | 152271102 | WISE 1102 | WISE 11022230 | 36254.0831 | 34.7369 | 21 | 22.5272 | 668.0306 | 4208.6447 | 23.6739 | 34.0761 | 1 | 4208.6447 | #N/A | #N/A
Central Valley | 3450 | 177 | 0.12922 | 254151102 | AUBERRY 1102 | AUBERRY 1102R2850 | 41610.2357 | 22.8722 | 51 | 25.8554 | 693.886 | 4185.7725 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 662 | 143 | 0.12899 | 103521104 | OREGON TRAIL 1104 | OREGON TRAIL 1104circuit_breaker | 15260.0733 | 18.4455 | 72 | 9.4822 | 703.3681 | 4167.327 | 10.7214 | 17.03 | 1 | 4167.327 | #N/A | #N/A
Central Valley | 1973 | 304 | 0.1287 | 254421101 | OAKHURST 1101 | OAKHURST 11015490 | 39826.5176 | 39.1235 | 15 | 24.747 | 728.1152 | 4128.2036 | 10.1473 | 15.937 | 1 | #N/A | #N/A | 4128.2036
Central Coast | 2593 | 151 | 0.128 | 182611103 | PASO ROBLES 1103 | PASO ROBLES 1103N54 | 30731.9341 | 19.3286 | 66 | 19.0959 | 747.2111 | 4108.875 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 502 | 127 | 0.12773 | 102931102 | COTTONWOOD 1102 | COTTONWOOD 11029026 | 19720.6221 | 16.2213 | 89 | 12.2538 | 759.4649 | 4092.6537 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5017 | 109 | 0.12748 | 43361103 | HIGHLANDS 1103 | HIGHLANDS 1103circuit_breaker | 16763.7621 | 13.8949 | 102 | 10.4165 | 769.8815 | 4078.7588 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3127 | 49 | 0.12582 | 182661104 | SAN MIGUEL 1104 | SAN MIGUEL 1104R58 | 14371.1045 | 6.1653 | 234 | 8.9298 | 778.8112 | 4072.5935 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5903 | 4 | 0.12522 | 42631108 | PETALUMA C 1108 | PETALUMA C 1108618 | 13883.0282 | 0.50087 | 897 | 8.6265 | 787.4378 | 4072.0926 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 86 | 156 | 0.12451 | 103571105 | TYLER 1105 | TYLER 11051704 | 18219.6369 | 19.4232 | 64 | 11.3212 | 798.7589 | 4052.6694 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1571 | 351 | 0.1245 | 102931103 | COTTONWOOD 1103 | COTTONWOOD 11031348 | 45791.5824 | 43.6979 | 11 | 28.4536 | 827.2125 | 4008.9715 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8455 | 16 | 0.12339 | 43201102 | STAFFORD 1102 | STAFFORD 11021202 | 11742.1904 | 1.9742 | 505 | 7.2963 | 834.5087 | 4006.9973 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3596 | 154 | 0.12303 | 42771111 | UKIAH 1111 | UKIAH 1111534 | 30274.4024 | 18.9464 | 67 | 18.8116 | 853.3204 | 3988.0508 | 18.2775 | 18.9464 | 1 | 3988.0508 | #N/A | #N/A
Central Coast | 1399 | 79 | 0.12271 | 182681102 | ZACA 1102 | ZACA 1102Y02 | 15863.9802 | 9.6937 | 160 | 9.8574 | 863.1778 | 3978.3571 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6222 | 134 | 0.12145 | 103561102 | STILLWATER 1102 | STILLWATER 110248952 | 16989.9527 | 16.2746 | 88 | 10.5571 | 873.7348 | 3962.0826 | 10.0246 | 16.2746 | 1 | 3962.0826 | #N/A | #N/A
Central Valley | 192 | 383 | 0.12107 | 254432104 | COARSEGOLD 2104 | COARSEGOLD 21045300 | 59987.7854 | 46.3711 | 7 | 37.2747 | 911.0095 | 3915.7115 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1391 | 134 | 0.12019 | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102998 | 23041.0417 | 16.1058 | 91 | 14.317 | 925.3266 | 3899.6057 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6489 | 32 | 0.11931 | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102circuit_breaker | 7090.0728 | 3.818 | 323 | 4.4056 | 929.7321 | 3895.7877 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3724 | 150 | 0.11922 | 103351101 | DESCHUTES 1101 | DESCHUTES 11011380 | 27539.9827 | 17.8832 | 79 | 17.1125 | 946.8447 | 3877.9044 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7350 | 16 | 0.11881 | 182611103 | PASO ROBLES 1103 | PASO ROBLES 11032731 | 2616.6102 | 1.901 | 514 | 1.6259 | 948.4706 | 3876.0035 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1744 | 126 | 0.11726 | 252941107 | TIVY VALLEY 1107 | TIVY VALLEY 1107869946 | 48055.8133 | 14.7751 | 97 | 29.8605 | 978.331 | 3861.2284 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1577 | 307 | 0.11508 | 254432103 | COARSEGOLD 2103 | COARSEGOLD 210310820 | 45523.6929 | 35.3292 | 20 | 28.2871 | 1006.6181 | 3825.8992 | 25.5261 | 32.3309 | 1 | 3825.8992 | #N/A | #N/A
North Valley | 6021 | 42 | 0.1146 | 102931101 | COTTONWOOD 1101 | COTTONWOOD 110131500 | 6089.5352 | 4.8132 | 274 | 3.7839 | 1010.402 | 3821.086 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1789 | 243 | 0.11438 | 152701107 | BELL 1107 | BELL 110750172 | 27581.8653 | 27.7939 | 34 | 17.1386 | 1027.5406 | 3793.2921 | 5.6606 | 9.0902 | 1 | #N/A | #N/A | 3793.2921
Sierra | 7292 | 26 | 0.11398 | 63801103 | JAMESON 1103 | JAMESON 1103circuit_breaker | 3720.1837 | 2.9634 | 392 | 2.3116 | 1029.8522 | 3790.3287 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2409 | 473 | 0.11269 | 254432104 | COARSEGOLD 2104 | COARSEGOLD 210410400 | 67877.1847 | 53.3043 | 3 | 42.1769 | 1072.0291 | 3737.0244 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5388 | 180 | 0.11235 | 103541103 | RED BLUFF 1103 | RED BLUFF 11031702 | 26173.4534 | 20.2222 | 58 | 16.2634 | 1088.2925 | 3716.8022 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5473 | 162 | 0.11188 | 103191101 | BANGOR 1101 | BANGOR 110180670 | 22220.3587 | 18.1242 | 75 | 13.8071 | 1102.0996 | 3698.678 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8205 | 2 | 0.11176 | 102781101 | ELK CREEK 1101 | ELK CREEK 110193504 | 3298.9383 | 0.22351 | 1130 | 2.0499 | 1104.1495 | 3698.4545 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6616 | 251 | 0.11024 | 102931101 | COTTONWOOD 1101 | COTTONWOOD 110168190 | 37929.7081 | 27.6706 | 36 | 23.5684 | 1127.7179 | 3670.7839 | 23.6848 | 27.6706 | 1 | 3670.7839 | #N/A | #N/A
Sierra | 7282 | 66 | 0.11023 | 153652108 | SHINGLE SPRINGS 2108 | SHINGLE SPRINGS 210851476 | 7007.9313 | 7.2751 | 198 | 4.3545 | 1132.0724 | 3663.5088 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4329 | 82 | 0.10882 | 43361103 | HIGHLANDS 1103 | HIGHLANDS 1103568 | 12324.8036 | 8.9233 | 171 | 7.6583 | 1139.7307 | 3654.5855 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6761 | 58 | 0.1087 | 63601111 | VACAVILLE 1111 | VACAVILLE 111113652 | 6983.1183 | 6.3046 | 226 | 4.3391 | 1144.0698 | 3648.2809 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2632 | 36 | 0.10715 | 183041102 | BUELLTON 1102 | BUELLTON 1102circuit_breaker | 8489.4268 | 3.8574 | 321 | 5.2751 | 1149.3449 | 3644.4235 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 864 | 408 | 0.10715 | 103541101 | RED BLUFF 1101 | RED BLUFF 11011334 | 62500.9171 | 43.7155 | 10 | 38.8363 | 1188.1811 | 3600.7081 | 39.9742 | 43.7155 | 1 | 3600.7081 | #N/A | #N/A
Central Valley | 6138 | 85 | 0.10489 | 254432104 | COARSEGOLD 2104 | COARSEGOLD 210410335 | 9369.0411 | 8.9154 | 172 | 5.8217 | 1194.0028 | 3591.7926 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4384 | 241 | 0.10469 | 103191101 | BANGOR 1101 | BANGOR 110182350 | 30346.6456 | 25.231 | 44 | 18.8565 | 1212.8593 | 3566.5617 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9084 | 14 | 0.10421 | 43211101 | HARTLEY 1101 | HARTLEY 11014710 | 2414.0517 | 1.459 | 579 | 1.5 | 1214.3593 | 3565.1027 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4268 | 197 | 0.10339 | 254151102 | AUBERRY 1102 | AUBERRY 110237466 | 50295.1648 | 20.3675 | 57 | 31.252 | 1245.6113 | 3544.7352 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9386 | 3 | 0.10306 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 1102circuit_breaker | 1038.6996 | 0.30919 | 1023 | 0.64542 | 1246.2567 | 3544.426 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7209 | 192 | 0.10238 | 152921101 | BROWNS VALLEY 1101 | BROWNS VALLEY 110193870 | 28752.0223 | 19.6578 | 60 | 17.8657 | 1264.1224 | 3524.7682 | 21.0303 | 19.6578 | 1 | 3524.7682 | #N/A | #N/A
Sierra | 4869 | 59 | 0.10177 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | 9165.9911 | 6.0045 | 237 | 5.6955 | 1269.8179 | 3518.7637 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1685 | 134 | 0.10135 | 183041102 | BUELLTON 1102 | BUELLTON 1102Y50 | 17178.6356 | 13.5803 | 104 | 10.6743 | 1280.4922 | 3505.1834 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5653 | 49 | 0.10107 | 152531101 | FLINT 1101 | FLINT 1101750 | 7461.0283 | 4.9524 | 269 | 4.6361 | 1285.1282 | 3500.231 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3978 | 164 | 0.10044 | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 23785.8023 | 16.4715 | 87 | 14.7798 | 1299.9081 | 3483.7595 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1015 | 322 | 0.1004 | 162991101 | CORRAL 1101 | CORRAL 110136652 | 58059.3769 | 32.3296 | 24 | 36.0764 | 1335.9845 | 3451.4299 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1458 | 151 | 0.10004 | 254151101 | AUBERRY 1101 | AUBERRY 1101circuit_breaker | 29094.1652 | 15.1058 | 94 | 18.0783 | 1354.0627 | 3436.3241 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 167 | 102 | 0.098378 | 163231101 | NORTH BRANCH 1101 | NORTH BRANCH 110111206 | 28150.1513 | 10.0345 | 149 | 17.4917 | 1371.5544 | 3426.2896 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4692 | 183 | 0.098165 | 254421103 | OAKHURST 1103 | OAKHURST 110363334 | 27690.7454 | 17.9641 | 78 | 17.2062 | 1388.7607 | 3408.3254 | 13.8756 | 16.7655 | 1 | 3408.3254 | #N/A | #N/A
North Coast | 4752 | 64 | 0.098139 | 43211101 | HARTLEY 1101 | HARTLEY 1101698 | 9794.4645 | 6.2809 | 228 | 6.086 | 1394.8466 | 3402.0446 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2349 | 51 | 0.097361 | 102911109 | WYANDOTTE 1109 | WYANDOTTE 11091520 | 5746.3127 | 4.9654 | 268 | 3.5706 | 1398.4172 | 3397.0792 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 8695 | 25 | 0.096932 | 152921101 | BROWNS VALLEY 1101 | BROWNS VALLEY 110117011 | 3005.3172 | 2.4233 | 438 | 1.8674 | 1400.2847 | 3394.6559 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5352 | 92 | 0.096529 | 103571105 | TYLER 1105 | TYLER 11051536 | 27372.4849 | 8.8807 | 173 | 17.0085 | 1417.2931 | 3385.7752 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7852 | 29 | 0.095618 | 102781101 | ELK CREEK 1101 | ELK CREEK 11012002 | 24592.8123 | 2.7729 | 402 | 15.2813 | 1432.5744 | 3383.0023 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7087 | 43 | 0.095517 | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 1103circuit_breaker | 4346.4203 | 4.1072 | 308 | 2.7007 | 1435.2751 | 3378.8951 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 247 | 166 | 0.095332 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 11022582 | 32088.8606 | 15.8251 | 92 | 19.9391 | 1455.2142 | 3363.07 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7841 | 38 | 0.094821 | 42141102 | CLEAR LAKE 1102 | CLEAR LAKE 1102904 | 5254.2064 | 3.6032 | 335 | 3.2648 | 1458.479 | 3359.4668 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7750 | 4 | 0.094696 | 153612109 | CLARKSVILLE 2109 | CLARKSVILLE 2109circuit_breaker | 1633.6693 | 0.37879 | 969 | 1.0151 | 1459.4941 | 3359.088 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2668 | 55 | 0.094586 | 102781101 | ELK CREEK 1101 | ELK CREEK 110137334 | 15414.1675 | 5.2022 | 257 | 9.5779 | 1469.0721 | 3353.8858 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2050 | 133 | 0.094564 | 254432103 | COARSEGOLD 2103 | COARSEGOLD 21035020 | 25953.2029 | 12.577 | 116 | 16.1266 | 1485.1986 | 3341.3088 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 912 | 200 | 0.093359 | 162991101 | CORRAL 1101 | CORRAL 1101circuit_breaker | 42004.2216 | 18.6718 | 69 | 26.1002 | 1511.2988 | 3322.637 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6448 | 16 | 0.093164 | 152582109 | DEL MAR 2109 | DEL MAR 2109circuit_breaker | 3009.0839 | 1.4906 | 574 | 1.8698 | 1513.1686 | 3321.1464 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1486 | 253 | 0.092604 | 102911109 | WYANDOTTE 1109 | WYANDOTTE 110979932 | 34098.0677 | 23.4289 | 46 | 21.1876 | 1534.3561 | 3297.7176 | 21.1451 | 23.4289 | 1 | 3297.7176 | #N/A | #N/A
North Valley | 1206 | 3 | 0.09231 | 103541103 | RED BLUFF 1103 | RED BLUFF 1103circuit_breaker | 126.6017 | 0.27693 | 1067 | 0.078667 | 1534.4348 | 3297.4406 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3497 | 98 | 0.092286 | 103441102 | JESSUP 1102 | JESSUP 110296554 | 12714.8897 | 9.0441 | 168 | 7.9007 | 1542.3355 | 3288.3966 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 81 | 144 | 0.091663 | 153701104 | LINCOLN 1104 | LINCOLN 110451756 | 24962.2729 | 13.1994 | 110 | 15.5108 | 1557.8463 | 3275.1972 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7203 | 124 | 0.091485 | 162991101 | CORRAL 1101 | CORRAL 110112608 | 27099.2397 | 11.3441 | 133 | 16.8387 | 1574.685 | 3263.8531 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6949 | 80 | 0.090399 | 152271102 | WISE 1102 | WISE 11022234 | 24231.786 | 7.2319 | 199 | 15.0569 | 1589.7419 | 3256.6212 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 8888 | 4 | 0.089773 | 63642108 | PEABODY 2108 | PEABODY 2108circuit_breaker | 604.4135 | 0.35909 | 982 | 0.37556 | 1590.1175 | 3256.2621 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1224 | 281 | 0.089249 | 152561103 | PENRYN 1103 | PENRYN 11032198 | 32169.4149 | 25.0789 | 45 | 19.9891 | 1610.1066 | 3231.1832 | 17.0445 | 23.2613 | 1 | 3231.1832 | #N/A | #N/A
Central Coast | 2756 | 41 | 0.089128 | 182681102 | ZACA 1102 | ZACA 1102Y48 | 6193.8861 | 3.6543 | 331 | 3.8487 | 1613.9553 | 3227.5289 | 3.4494 | 3.6543 | 1 | #N/A | 3227.5289 | #N/A
Sierra | 2066 | 5 | 0.088432 | 153701104 | LINCOLN 1104 | LINCOLN 11045391 | 1530.1829 | 0.44216 | 932 | 0.95081 | 1614.9061 | 3227.0868 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2772 | 12 | 0.088193 | 152561106 | PENRYN 1106 | PENRYN 110651674 | 1609.198 | 1.0583 | 676 | 0.99991 | 1615.906 | 3226.0285 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6934 | 56 | 0.087976 | 254452102 | MARIPOSA 2102 | MARIPOSA 2102440236 | 6786.4552 | 4.9267 | 271 | 4.2169 | 1620.1229 | 3221.1018 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1949 | 5 | 0.087117 | 182661105 | SAN MIGUEL 1105 | SAN MIGUEL 1105circuit_breaker | 2410.7396 | 0.43559 | 937 | 1.498 | 1621.6209 | 3220.6662 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3223 | 35 | 0.086668 | 103261103 | ANDERSON 1103 | ANDERSON 11031600 | 4989.8706 | 3.0334 | 389 | 3.1006 | 1624.7215 | 3217.6328 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5513 | 118 | 0.086667 | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 17564.7145 | 10.2267 | 146 | 10.9142 | 1635.6357 | 3207.4061 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3761 | 201 | 0.086089 | 254601103 | SAND CREEK 1103 | SAND CREEK 11037140 | 42354.6264 | 17.3038 | 82 | 26.3179 | 1661.9536 | 3190.1023 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8315 | 26 | 0.085959 | 14052103 | NORTH DUBLIN 2103 | NORTH DUBLIN 210311101 | 5926.9536 | 2.2349 | 459 | 3.6828 | 1665.6364 | 3187.8673 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1508 | 381 | 0.085749 | 152701107 | BELL 1107 | BELL 11072400 | 40028.1973 | 32.6703 | 23 | 24.8724 | 1690.5088 | 3155.1971 | 10.9303 | 13.8736 | 1 | #N/A | #N/A | 3155.1971
Central Valley | 6785 | 115 | 0.08541 | 254151102 | AUBERRY 1102 | AUBERRY 1102R1013 | 19936.8067 | 9.8222 | 156 | 12.3882 | 1702.897 | 3145.3749 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2440 | 135 | 0.084535 | 152921101 | BROWNS VALLEY 1101 | BROWNS VALLEY 11011268 | 17547.6887 | 11.4123 | 132 | 10.9036 | 1713.8006 | 3133.9627 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7386 | 82 | 0.084485 | 103541101 | RED BLUFF 1101 | RED BLUFF 110176020 | 14298.5591 | 6.9278 | 203 | 8.8847 | 1722.6853 | 3127.0348 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4128 | 118 | 0.084394 | 12022212 | CLAYTON 2212 | CLAYTON 22122944 | 23517.364 | 9.9585 | 152 | 14.613 | 1737.2983 | 3117.0764 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3495 | 66 | 0.08342 | 42661102 | WILLITS 1102 | WILLITS 1102circuit_breaker | 7444.0734 | 5.5057 | 247 | 4.6255 | 1741.9238 | 3111.5707 | 4.9256 | 5.2993 | 1 | 3111.5707 | #N/A | #N/A
North Coast | 6600 | 131 | 0.082639 | 192321121 | FORT SEWARD 1121 | FORT SEWARD 11211690 | 15633.7781 | 10.8257 | 143 | 9.7144 | 1751.6382 | 3100.745 | 10.4326 | 10.8257 | 1 | 3100.745 | #N/A | #N/A
North Coast | 2658 | 133 | 0.082528 | 42271105 | COTATI 1105 | COTATI 110536536 | 25960.937 | 10.9762 | 141 | 16.1314 | 1767.7696 | 3089.7688 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4207 | 49 | 0.081896 | 103401102 | GIRVAN 1102 | GIRVAN 1102circuit_breaker | 5934.374 | 4.0129 | 314 | 3.6874 | 1771.457 | 3085.756 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4729 | 228 | 0.081723 | 153701104 | LINCOLN 1104 | LINCOLN 11042070 | 26390.3487 | 18.6329 | 70 | 16.3982 | 1787.8552 | 3067.1231 | 21.0958 | 18.6329 | 1 | 3067.1231 | #N/A | #N/A
North Valley | 6432 | 44 | 0.081472 | 103331101 | CORNING 1101 | CORNING 110182846 | 7599.2356 | 3.5848 | 337 | 4.7219 | 1792.5772 | 3063.5383 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8199 | 45 | 0.080522 | 103261101 | ANDERSON 1101 | ANDERSON 11012051 | 8118.8203 | 3.6235 | 333 | 5.0448 | 1797.622 | 3059.9148 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2693 | 23 | 0.080049 | 182742101 | SAN BENITO 2101 | SAN BENITO 210136912 | 7482.8922 | 1.8411 | 521 | 4.6497 | 1802.2716 | 3058.0737 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1374 | 146 | 0.079894 | 252521103 | SAN JOAQUIN #2 1103 | SAN JOAQUIN #2 110310320 | 18926.5803 | 11.6645 | 129 | 11.7604 | 1814.0321 | 3046.4092 | 11.4659 | 11.6645 | 1 | 3046.4092 | #N/A | #N/A
North Valley | 5188 | 58 | 0.079634 | 102911109 | WYANDOTTE 1109 | WYANDOTTE 11095607 | 6796.939 | 4.6188 | 278 | 4.2234 | 1818.2555 | 3041.7904 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8090 | 47 | 0.078846 | 102781101 | ELK CREEK 1101 | ELK CREEK 11012106 | 21303.4581 | 3.7058 | 328 | 13.2374 | 1831.4928 | 3038.0846 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3848 | 331 | 0.078641 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 2101circuit_breaker | 40183.7682 | 26.0302 | 41 | 24.969 | 1856.4619 | 3012.0544 | 25.8396 | 26.0302 | 1 | 3012.0544 | #N/A | #N/A
North Coast | 2080 | 80 | 0.078231 | 43351103 | LUCERNE 1103 | LUCERNE 11031280 | 11811.7208 | 6.2585 | 232 | 7.3395 | 1863.8013 | 3005.7959 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5006 | 6 | 0.077068 | 63601109 | VACAVILLE 1109 | VACAVILLE 110941782 | 1089.8371 | 0.46241 | 923 | 0.67719 | 1864.4785 | 3005.3335 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 934 | 88 | 0.076876 | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y66 | 25950.7807 | 6.7651 | 210 | 16.1251 | 1880.6036 | 2998.5685 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4646 | 255 | 0.076685 | 102931103 | COTTONWOOD 1103 | COTTONWOOD 11039072 | 45954.2203 | 19.5548 | 63 | 28.5546 | 1909.1582 | 2979.0137 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2804 | 219 | 0.076254 | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 28435.4313 | 16.6995 | 85 | 17.669 | 1926.8271 | 2962.3142 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4127 | 48 | 0.075419 | 42281104 | POTTER VALLEY P H 1104 | POTTER VALLEY P H 110495878 | 7653.5834 | 3.6201 | 334 | 4.7557 | 1931.5829 | 2958.6941 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2763 | 540 | 0.075309 | 254421101 | OAKHURST 1101 | OAKHURST 110110090 | 71069.2859 | 40.6671 | 14 | 44.1604 | 1975.7433 | 2918.027 | 26.661 | 24.8226 | 1 | 2918.027 | #N/A | #N/A
North Valley | 2247 | 207 | 0.075307 | 103441102 | JESSUP 1102 | JESSUP 11021550 | 28670.4982 | 15.5885 | 93 | 17.815 | 1993.5583 | 2902.4385 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4022 | 178 | 0.074482 | 254601103 | SAND CREEK 1103 | SAND CREEK 11037420 | 38096.5412 | 13.2578 | 109 | 23.6721 | 2017.2304 | 2889.1807 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6306 | 103 | 0.074476 | 42871101 | UPPER LAKE 1101 | UPPER LAKE 1101412 | 17548.709 | 7.671 | 187 | 10.9043 | 2028.1346 | 2881.5097 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 338 | 60 | 0.074164 | 102931101 | COTTONWOOD 1101 | COTTONWOOD 1101circuit_breaker | 7715.0522 | 4.4498 | 286 | 4.7939 | 2032.9285 | 2877.0599 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4335 | 24 | 0.073876 | 102781101 | ELK CREEK 1101 | ELK CREEK 11012228 | 4717.8323 | 1.773 | 529 | 2.9315 | 2035.86 | 2875.2868 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 603 | 42 | 0.073873 | 252561101 | KERCKHOFF 1101 | KERCKHOFF 1101circuit_breaker | 27412.9116 | 3.1027 | 387 | 17.0336 | 2052.8936 | 2872.1842 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2148 | 241 | 0.074121 | 152261105 | DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 110519910 | 32811.9682 | 17.8631 | 80 | 20.3884 | 2073.282 | 2854.3211 | 18.5989 | 17.5176 | 2 | 2854.3211 | #N/A | #N/A
Central Valley | 2148 | 1 | 4.9046e-06 | 152261105 | DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 110519910 | 32811.9682 | 4.9046e-06 | 80 | 20.3884 | 2093.6704 | 2854.3211 |  |  | 2 | 2854.3211 | #N/A | #N/A
Central Coast | 5296 | 109 | 0.073532 | 182681102 | ZACA 1102 | ZACA 1102circuit_breaker | 24178.8119 | 8.015 | 180 | 15.024 | 2108.6945 | 2846.3061 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4894 | 69 | 0.07303 | 42821102 | CLOVERDALE 1102 | CLOVERDALE 1102156 | 8650.9367 | 5.0391 | 264 | 5.3754 | 2114.0699 | 2841.267 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2565 | 25 | 0.072922 | 103441103 | JESSUP 1103 | JESSUP 11031540 | 2468.2792 | 1.823 | 525 | 1.5337 | 2115.6036 | 2839.444 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1366 | 367 | 0.072884 | 254601103 | SAND CREEK 1103 | SAND CREEK 110345190 | 58836.3475 | 26.7484 | 39 | 36.5592 | 2152.1628 | 2812.6956 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1853 | 154 | 0.072883 | 43191101 | REDBUD 1101 | REDBUD 1101323962 | 32521.6427 | 11.224 | 135 | 20.208 | 2172.3708 | 2801.4717 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1871 | 112 | 0.072213 | 252941107 | TIVY VALLEY 1107 | TIVY VALLEY 1107R1817 | 30260.3712 | 8.0879 | 177 | 18.8029 | 2191.1737 | 2793.3838 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6490 | 74 | 0.07173 | 152701108 | BELL 1108 | BELL 11085703 | 7165.6312 | 5.308 | 253 | 4.4525 | 2195.6263 | 2788.0758 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 56 | 91 | 0.071723 | 63601111 | VACAVILLE 1111 | VACAVILLE 1111circuit_breaker | 10814.1289 | 6.5268 | 217 | 6.7196 | 2202.3458 | 2781.5489 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2173 | 78 | 0.071621 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101circuit_breaker | 13452.3274 | 5.5864 | 246 | 8.3589 | 2210.7047 | 2775.9625 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 60 | 1 | 0.071046 | 162991101 | CORRAL 1101 | CORRAL 110175204 | 154.2541 | 0.071046 | 1448 | 0.095849 | 2210.8006 | 2775.8914 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3481 | 173 | 0.070389 | 63801105 | JAMESON 1105 | JAMESON 11057652 | 21719.6282 | 12.1773 | 122 | 13.4959 | 2224.2965 | 2763.7141 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3437 | 75 | 0.06994 | 42141101 | CLEAR LAKE 1101 | CLEAR LAKE 1101406 | 17278.745 | 5.2455 | 256 | 10.7365 | 2235.033 | 2758.4686 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7479 | 1 | 0.069642 | 13912107 | WILLOW PASS 2107 | WILLOW PASS 2107P500R | 1031.3201 | 0.069642 | 1452 | 0.64083 | 2235.6739 | 2758.399 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6227 | 108 | 0.069507 | 152271102 | WISE 1102 | WISE 1102697216 | 21260.5149 | 7.5068 | 191 | 13.2107 | 2248.8845 | 2750.8922 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3424 | 7 | 0.069419 | 12022215 | CLAYTON 2215 | CLAYTON 2215circuit_breaker | 3378.3697 | 0.48593 | 909 | 2.0992 | 2250.9838 | 2750.4063 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1887 | 2 | 0.06938 | 102911106 | WYANDOTTE 1106 | WYANDOTTE 110641650 | 1286.1146 | 0.13876 | 1268 | 0.79915 | 2251.7829 | 2750.2675 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5552 | 20 | 0.06907 | 152561107 | PENRYN 1107 | PENRYN 11072704 | 1994.2196 | 1.3814 | 598 | 1.2392 | 2253.0221 | 2748.8861 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7817 | 40 | 0.068637 | 103351101 | DESCHUTES 1101 | DESCHUTES 11019722 | 4975.6844 | 2.7455 | 405 | 3.0917 | 2256.1138 | 2746.1407 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 8201 | 8 | 0.068411 | 63681105 | PUTAH CREEK 1105 | PUTAH CREEK 110546162 | 1002.572 | 0.54729 | 876 | 0.62297 | 2256.7368 | 2745.5934 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6093 | 1 | 0.068058 | 63172101 | MADISON 2101 | MADISON 21011606 | 1536.4017 | 0.068058 | 1458 | 0.95468 | 2257.6915 | 2745.5253 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4798 | 416 | 0.068023 | 152701108 | BELL 1108 | BELL 11082202 | 51314.2889 | 28.2975 | 31 | 31.8852 | 2289.5767 | 2717.2278 | 29.8174 | 26.3011 | 1 | 2717.2278 | #N/A | #N/A
Bay Area | 7713 | 90 | 0.067762 | 42991105 | LAS GALLINAS A 1105 | LAS GALLINAS A 110599904 | 8897.752 | 6.0985 | 236 | 5.5288 | 2295.1055 | 2711.1293 | 5.4655 | 5.8391 | 1 | 2711.1293 | #N/A | #N/A
Bay Area | 389 | 181 | 0.067548 | 42711101 | CALISTOGA 1101 | CALISTOGA 1101734 | 20110.861 | 12.2262 | 119 | 12.4963 | 2307.6018 | 2698.9031 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 834 | 97 | 0.06605 | 182611104 | PASO ROBLES 1104 | PASO ROBLES 1104R56 | 17514.7266 | 6.4068 | 222 | 10.8831 | 2318.4849 | 2692.4962 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1329 | 148 | 0.066034 | 162991102 | CORRAL 1102 | CORRAL 1102circuit_breaker | 25529.3697 | 9.7731 | 157 | 15.8632 | 2334.3481 | 2682.7232 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4967 | 422 | 0.066009 | 254151101 | AUBERRY 1101 | AUBERRY 1101R2578 | 74321.3837 | 27.8557 | 33 | 46.1812 | 2380.5293 | 2654.8675 | 39.5581 | 22.8753 | 1 | 2654.8675 | #N/A | #N/A
Sierra | 248 | 2 | 0.065976 | 63172101 | MADISON 2101 | MADISON 210189332 | 1160.8504 | 0.13195 | 1275 | 0.72132 | 2381.2506 | 2654.7355 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4477 | 50 | 0.065896 | 42871101 | UPPER LAKE 1101 | UPPER LAKE 1101660 | 8469.2097 | 3.2948 | 368 | 5.2625 | 2386.5131 | 2651.4407 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5956 | 18 | 0.065242 | 254432104 | COARSEGOLD 2104 | COARSEGOLD 210490356 | 7895.0402 | 1.1744 | 637 | 4.9057 | 2391.4189 | 2650.2664 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2425 | 60 | 0.064794 | 103441102 | JESSUP 1102 | JESSUP 11021314 | 8285.2738 | 3.8877 | 318 | 5.1482 | 2396.5671 | 2646.3787 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4317 | 334 | 0.064746 | 103561102 | STILLWATER 1102 | STILLWATER 1102circuit_breaker | 40538.5999 | 21.6253 | 54 | 25.1895 | 2421.7566 | 2624.7534 | 25.5741 | 21.6253 | 1 | 2624.7534 | #N/A | #N/A
North Coast | 9224 | 35 | 0.064742 | 42661103 | WILLITS 1103 | WILLITS 1103circuit_breaker | 4233.1434 | 2.266 | 455 | 2.6304 | 2424.387 | 2622.4874 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5326 | 27 | 0.063562 | 102911109 | WYANDOTTE 1109 | WYANDOTTE 1109circuit_breaker | 3677.1991 | 1.7162 | 537 | 2.2849 | 2426.6719 | 2620.7712 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1088 | 81 | 0.063318 | 254432104 | COARSEGOLD 2104 | COARSEGOLD 210410030 | 23477.104 | 5.1287 | 260 | 14.588 | 2441.2599 | 2615.6425 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8700 | 3 | 0.063015 | 102541101 | VOLTA 1101 | VOLTA 110165764 | 16669.3981 | 0.18905 | 1179 | 10.3579 | 2451.6177 | 2615.4534 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5211 | 92 | 0.062852 | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 111324918 | 8527.9094 | 5.7824 | 244 | 5.299 | 2456.9167 | 2609.6711 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 466 | 420 | 0.062652 | 102931103 | COTTONWOOD 1103 | COTTONWOOD 11031616 | 73500.8728 | 26.3137 | 40 | 45.6713 | 2502.588 | 2583.3574 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7963 | 56 | 0.062453 | 43411101 | CALPELLA 1101 | CALPELLA 11013419 | 12991.6223 | 3.4974 | 347 | 8.0726 | 2510.6607 | 2579.86 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2009 | 5 | 0.062331 | 153701104 | LINCOLN 1104 | LINCOLN 11042072 | 512.0053 | 0.31165 | 1020 | 0.31815 | 2510.9788 | 2579.5484 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9469 | 17 | 0.062315 | 14452104 | KIRKER 2104 | KIRKER 2104442850 | 9153.4289 | 1.0594 | 674 | 5.6877 | 2516.6665 | 2578.489 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5504 | 676 | 0.062269 | 152691109 | HIGGINS 1109 | HIGGINS 110950072 | 82323.743 | 42.0939 | 13 | 51.1536 | 2567.8201 | 2536.3951 | 51.4699 | 42.0939 | 1 | 2536.3951 | #N/A | #N/A
North Coast | 2778 | 160 | 0.062201 | 42891101 | GEYSERVILLE 1101 | GEYSERVILLE 1101166 | 18354.3619 | 9.9522 | 153 | 11.4049 | 2579.2249 | 2526.4429 | 11.1278 | 9.9522 | 1 | 2526.4429 | #N/A | #N/A
North Valley | 4708 | 123 | 0.061968 | 103521102 | OREGON TRAIL 1102 | OREGON TRAIL 1102circuit_breaker | 15165.9787 | 7.6221 | 188 | 9.4237 | 2588.6486 | 2518.8209 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1980 | 180 | 0.061829 | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210912392 | 23968.2562 | 11.1292 | 137 | 14.8932 | 2603.5418 | 2507.6917 | 14.6294 | 11.1292 | 1 | 2507.6917 | #N/A | #N/A
Central Valley | 698 | 422 | 0.061681 | 254432103 | COARSEGOLD 2103 | COARSEGOLD 2103circuit_breaker | 61823.6709 | 26.0295 | 42 | 38.4154 | 2641.9572 | 2481.6622 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6799 | 13 | 0.061653 | 182721102 | SANTA YNEZ 1102 | SANTA YNEZ 1102circuit_breaker | 1351.6956 | 0.8015 | 760 | 0.8399 | 2642.7972 | 2480.8607 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1466 | 67 | 0.061527 | 42821101 | CLOVERDALE 1101 | CLOVERDALE 1101circuit_breaker | 7970.5303 | 4.1223 | 307 | 4.9527 | 2647.7498 | 2476.7384 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3817 | 163 | 0.061492 | 103331101 | CORNING 1101 | CORNING 110164090 | 22037.5277 | 10.0231 | 150 | 13.6935 | 2661.4433 | 2466.7153 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6065 | 49 | 0.061398 | 182661104 | SAN MIGUEL 1104 | SAN MIGUEL 1104N60 | 12563.9317 | 3.0085 | 390 | 7.8069 | 2669.2502 | 2463.7068 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6417 | 20 | 0.060947 | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110537476 | 3321.5283 | 1.2189 | 626 | 2.0639 | 2671.3141 | 2462.4879 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6626 | 36 | 0.060796 | 153612104 | CLARKSVILLE 2104 | CLARKSVILLE 2104circuit_breaker | 14071.4401 | 2.1887 | 467 | 8.7436 | 2680.0576 | 2460.2992 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 888 | 53 | 0.060656 | 103331102 | CORNING 1102 | CORNING 110290036 | 19887.703 | 3.2148 | 375 | 12.3576 | 2692.4153 | 2457.0844 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6195 | 504 | 0.060404 | 152691109 | HIGGINS 1109 | HIGGINS 110950078 | 77708.0128 | 30.4436 | 28 | 48.2855 | 2740.7008 | 2426.6408 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5665 | 216 | 0.060272 | 43432104 | SILVERADO 2104 | SILVERADO 2104632 | 29545.0013 | 13.0187 | 111 | 18.3584 | 2759.0592 | 2413.6221 | 7.2991 | 5.1022 | 1 | #N/A | 2413.6221 | #N/A
North Coast | 7360 | 73 | 0.059961 | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 22902.6806 | 4.3771 | 294 | 14.2311 | 2773.2903 | 2409.245 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1731 | 301 | 0.059694 | 103541104 | RED BLUFF 1104 | RED BLUFF 110451238 | 63182.0088 | 17.968 | 77 | 39.2595 | 2812.5497 | 2391.277 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1610 | 12 | 0.059289 | 103441101 | JESSUP 1101 | JESSUP 1101circuit_breaker | 2330.0107 | 0.71147 | 800 | 1.4478 | 2813.9975 | 2390.5655 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6674 | 59 | 0.059158 | 192221101 | GARBERVILLE 1101 | GARBERVILLE 110139524 | 7261.0619 | 3.4903 | 349 | 4.5118 | 2818.5093 | 2387.0752 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3082 | 41 | 0.059107 | 83242105 | MORGAN HILL 2105 | MORGAN HILL 2105XR564 | 8673.0497 | 2.4234 | 437 | 5.3892 | 2823.8985 | 2384.6518 | 5.2131 | 2.4234 | 1 | #N/A | 2384.6518 | #N/A
North Valley | 8921 | 56 | 0.058979 | 102781101 | ELK CREEK 1101 | ELK CREEK 11012032 | 13755.3854 | 3.3028 | 367 | 8.5472 | 2832.4457 | 2381.349 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 322 | 117 | 0.058732 | 103331102 | CORNING 1102 | CORNING 110253184 | 51349.7049 | 6.8716 | 206 | 31.9072 | 2864.3529 | 2374.4774 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7388 | 24 | 0.058607 | 14052103 | NORTH DUBLIN 2103 | NORTH DUBLIN 21039473 | 3725.6021 | 1.4066 | 591 | 2.315 | 2866.6679 | 2373.0708 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1057 | 94 | 0.05841 | 153701101 | LINCOLN 1101 | LINCOLN 110195756 | 9885.2869 | 5.4906 | 248 | 6.1424 | 2872.8103 | 2367.5802 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6372 | 338 | 0.05829 | 252941107 | TIVY VALLEY 1107 | TIVY VALLEY 1107584840 | 72367.2531 | 19.7021 | 59 | 44.9669 | 2917.7773 | 2347.8782 | 24.0636 | 10.7204 | 1 | 2347.8782 | #N/A | #N/A
North Valley | 3191 | 56 | 0.057704 | 103261103 | ANDERSON 1103 | ANDERSON 1103circuit_breaker | 5997.7664 | 3.2314 | 371 | 3.7268 | 2921.5041 | 2344.6467 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8735 | 26 | 0.057599 | 254601103 | SAND CREEK 1103 | SAND CREEK 11037823F | 7345.0348 | 1.4976 | 573 | 4.564 | 2926.0681 | 2343.1491 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6519 | 197 | 0.0574 | 42601101 | PHILO 1101 | PHILO 110137222 | 40901.8789 | 11.3077 | 134 | 25.4152 | 2951.4833 | 2331.8414 | 25.1165 | 11.3077 | 1 | 2331.8414 | #N/A | #N/A
Sierra | 3324 | 14 | 0.057397 | 152561105 | PENRYN 1105 | PENRYN 11051378 | 1299.5417 | 0.80356 | 758 | 0.8075 | 2952.2908 | 2331.0378 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1025 | 526 | 0.057365 | 254452102 | MARIPOSA 2102 | MARIPOSA 210237282 | 81850.6465 | 30.1742 | 29 | 50.8596 | 3003.1504 | 2300.8636 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 8370 | 84 | 0.057274 | 153651103 | SHINGLE SPRINGS 1103 | SHINGLE SPRINGS 1103circuit_breaker | 9623.2164 | 4.811 | 275 | 5.9796 | 3009.13 | 2296.0526 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3539 | 62 | 0.057097 | 14422109 | CAYETANO 2109 | CAYETANO 2109circuit_breaker | 30595.1389 | 3.54 | 344 | 19.0109 | 3028.141 | 2292.5126 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5848 | 259 | 0.056452 | 103571105 | TYLER 1105 | TYLER 110585132 | 50197.6466 | 14.6211 | 99 | 31.1914 | 3059.3323 | 2277.8915 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2248 | 586 | 0.056436 | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210913322 | 66862.7414 | 33.0717 | 22 | 41.5466 | 3100.8789 | 2244.8198 | 40.3987 | 33.0717 | 1 | 2244.8198 | #N/A | #N/A
North Coast | 1615 | 115 | 0.056414 | 42271105 | COTATI 1105 | COTATI 110599720 | 14251.5886 | 6.4876 | 219 | 8.8555 | 3109.7344 | 2238.3321 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4469 | 6 | 0.05591 | 103142102 | LOGAN CREEK 2102 | LOGAN CREEK 21022226 | 5964.9276 | 0.33546 | 1001 | 3.7064 | 3113.4409 | 2237.9967 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 538 | 309 | 0.055068 | 103561102 | STILLWATER 1102 | STILLWATER 11021644 | 36671.0244 | 17.0159 | 84 | 22.7863 | 3136.2272 | 2220.9808 | 22.8153 | 16.7746 | 1 | 2220.9808 | #N/A | #N/A
North Coast | 6282 | 142 | 0.054399 | 42571102 | MOLINO 1102 | MOLINO 110266006 | 14413.6045 | 7.7247 | 185 | 8.9562 | 3145.1834 | 2213.2561 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4896 | 127 | 0.054194 | 254151102 | AUBERRY 1102 | AUBERRY 1102R902 | 24311.5038 | 6.8827 | 205 | 15.1065 | 3160.2898 | 2206.3734 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4582 | 41 | 0.05409 | 252411104 | COPPERMINE 1104 | COPPERMINE 1104R755 | 14117.8234 | 2.2177 | 464 | 8.7724 | 3169.0622 | 2204.1557 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 9379 | 5 | 0.054019 | 183052113 | TEMPLETON 2113 | TEMPLETON 21132949 | 766.5719 | 0.2701 | 1077 | 0.47633 | 3169.5386 | 2203.8856 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2297 | 18 | 0.053846 | 103441102 | JESSUP 1102 | JESSUP 1102circuit_breaker | 1622.8923 | 0.96923 | 706 | 1.0084 | 3170.547 | 2202.9164 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7890 | 143 | 0.054413 | 103191101 | BANGOR 1101 | BANGOR 110131502 | 19075.5291 | 7.7811 | 183 | 11.853 | 3182.4 | 2195.1353 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Sierra | 7890 | 5 | 0.03194 | 103191101 | BANGOR 1101 | BANGOR 110131502 | 19075.5291 | 0.1597 | 183 | 11.853 | 3194.2529 | 2194.9756 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Sierra | 5121 | 344 | 0.05324 | 152691109 | HIGGINS 1109 | HIGGINS 1109circuit_breaker | 35901.2045 | 18.3144 | 73 | 22.308 | 3216.5609 | 2176.6612 | 27.6797 | 18.3144 | 1 | 2176.6612 | #N/A | #N/A
North Valley | 39 | 357 | 0.05306 | 103321101 | CEDAR CREEK 1101 | CEDAR CREEK 11011664 | 47829.7335 | 18.9423 | 68 | 29.72 | 3246.2809 | 2157.7188 | 28.9169 | 18.9423 | 1 | 2157.7188 | #N/A | #N/A
North Coast | 6814 | 54 | 0.053057 | 42271103 | COTATI 1103 | COTATI 1103circuit_breaker | 19561.5616 | 2.8651 | 398 | 12.155 | 3258.4359 | 2154.8537 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2246 | 13 | 0.053052 | 182611103 | PASO ROBLES 1103 | PASO ROBLES 110355374 | 3793.0347 | 0.68967 | 812 | 2.3569 | 3260.7928 | 2154.1641 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5581 | 22 | 0.052661 | 14652106 | TIDEWATER 2106 | TIDEWATER 210614072 | 5897.3117 | 1.1585 | 643 | 3.6644 | 3264.4572 | 2153.0055 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6060 | 354 | 0.052487 | 192251102 | RIO DELL 1102 | RIO DELL 11024230 | 36847.6257 | 18.5803 | 71 | 22.896 | 3287.3532 | 2134.4253 | 22.7074 | 18.5803 | 1 | 2134.4253 | #N/A | #N/A
Central Coast | 9000 | 31 | 0.052132 | 182611103 | PASO ROBLES 1103 | PASO ROBLES 110359763 | 4529.9707 | 1.6161 | 552 | 2.8148 | 3290.168 | 2132.8092 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6632 | 157 | 0.051828 | 103321101 | CEDAR CREEK 1101 | CEDAR CREEK 1101circuit_breaker | 24905.7197 | 8.1369 | 176 | 15.4757 | 3305.6437 | 2124.6722 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5074 | 82 | 0.051446 | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21092679 | 11499.2833 | 4.2186 | 303 | 7.1453 | 3312.7891 | 2120.4536 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6617 | 76 | 0.050912 | 42681102 | LAYTONVILLE 1102 | LAYTONVILLE 110268436 | 14642.1114 | 3.8693 | 320 | 9.0982 | 3321.8872 | 2116.5843 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2402 | 147 | 0.050708 | 162991101 | CORRAL 1101 | CORRAL 110112612 | 31361.0381 | 7.4541 | 193 | 19.4868 | 3341.3741 | 2109.1302 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1817 | 456 | 0.050377 | 254421103 | OAKHURST 1103 | OAKHURST 1103circuit_breaker | 50881.3747 | 22.972 | 48 | 31.6162 | 3372.9903 | 2086.1582 | 26.5585 | 19.3125 | 1 | 2086.1582 | #N/A | #N/A
Sierra | 6754 | 50 | 0.050025 | 153612104 | CLARKSVILLE 2104 | CLARKSVILLE 210419632 | 8385.252 | 2.5013 | 425 | 5.2104 | 3378.2006 | 2083.6569 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3506 | 11 | 0.049772 | 182721101 | SANTA YNEZ 1101 | SANTA YNEZ 1101Y14 | 7302.2086 | 0.54749 | 875 | 4.5374 | 3382.738 | 2083.1094 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1926 | 153 | 0.049714 | 153132105 | NARROWS 2105 | NARROWS 210534069 | 25148.2731 | 7.6062 | 189 | 15.6264 | 3398.3644 | 2075.5032 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1218 | 109 | 0.049497 | 153651104 | SHINGLE SPRINGS 1104 | SHINGLE SPRINGS 110419502 | 68814.3237 | 5.3952 | 252 | 42.7592 | 3441.1236 | 2070.108 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7920 | 29 | 0.048702 | 14422111 | CAYETANO 2111 | CAYETANO 2111circuit_breaker | 8282.7924 | 1.4124 | 588 | 5.1467 | 3446.2703 | 2068.6957 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7153 | 52 | 0.048693 | 163231101 | NORTH BRANCH 1101 | NORTH BRANCH 110111158 | 16351.0693 | 2.532 | 422 | 10.1601 | 3456.4304 | 2066.1637 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5104 | 21 | 0.048375 | 103261101 | ANDERSON 1101 | ANDERSON 11011752 | 5082.8869 | 1.0159 | 686 | 3.1584 | 3459.5888 | 2065.1478 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5869 | 82 | 0.048119 | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 1113583202 | 7085.4902 | 3.9458 | 317 | 4.4027 | 3463.9915 | 2061.202 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7162 | 18 | 0.048073 | 152561107 | PENRYN 1107 | PENRYN 110790970 | 1720.141 | 0.86532 | 738 | 1.0688 | 3465.0603 | 2060.3367 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2237 | 428 | 0.047811 | 103351101 | DESCHUTES 1101 | DESCHUTES 11011580 | 74786.9655 | 20.4631 | 56 | 46.4705 | 3511.5308 | 2039.8735 | 45.4328 | 20.4631 | 1 | 2039.8735 | #N/A | #N/A
Sierra | 3287 | 272 | 0.047665 | 152271102 | WISE 1102 | WISE 1102307494 | 49357.8411 | 12.965 | 112 | 30.6695 | 3542.2003 | 2026.9085 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6839 | 138 | 0.047548 | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 1113356 | 15672.6029 | 6.5616 | 214 | 9.7385 | 3551.9388 | 2020.347 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2529 | 194 | 0.047533 | 42681102 | LAYTONVILLE 1102 | LAYTONVILLE 1102500 | 32899.6268 | 9.2215 | 165 | 20.4429 | 3572.3817 | 2011.1255 | 14.7133 | 9.2215 | 1 | 2011.1255 | #N/A | #N/A
Bay Area | 442 | 197 | 0.04686 | 12022212 | CLAYTON 2212 | CLAYTON 221296224 | 26353.3688 | 9.2315 | 164 | 16.3752 | 3588.7569 | 2001.894 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2512 | 93 | 0.046411 | 102931103 | COTTONWOOD 1103 | COTTONWOOD 110335470 | 31917.2696 | 4.3162 | 298 | 19.8325 | 3608.5894 | 1997.5778 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3065 | 56 | 0.046308 | 152571101 | HORSESHOE 1101 | HORSESHOE 110150140 | 6170.3672 | 2.5933 | 417 | 3.8341 | 3612.4235 | 1994.9845 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 9682 | 6 | 0.046172 | 63642106 | PEABODY 2106 | PEABODY 21065500 | 589.7469 | 0.27703 | 1066 | 0.36645 | 3612.7899 | 1994.7075 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5334 | 197 | 0.046073 | 103441101 | JESSUP 1101 | JESSUP 11011496 | 23100.1991 | 9.0763 | 167 | 14.3538 | 3627.1437 | 1985.6312 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2729 | 240 | 0.04604 | 102911109 | WYANDOTTE 1109 | WYANDOTTE 110913052 | 31409.8673 | 11.0495 | 140 | 19.5172 | 3646.6609 | 1974.5816 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3269 | 244 | 0.045923 | 103441102 | JESSUP 1102 | JESSUP 110276068 | 26885.9006 | 11.2051 | 136 | 16.7061 | 3663.367 | 1963.3765 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3701 | 72 | 0.045735 | 152691107 | HIGGINS 1107 | HIGGINS 11077559 | 7109.6813 | 3.2929 | 369 | 4.4177 | 3667.7848 | 1960.0836 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3393 | 376 | 0.045655 | 102931101 | COTTONWOOD 1101 | COTTONWOOD 11011610 | 61705.5201 | 17.1663 | 83 | 38.342 | 3706.1268 | 1942.9173 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7114 | 95 | 0.045612 | 162991102 | CORRAL 1102 | CORRAL 110214026 | 16308.5206 | 4.3331 | 295 | 10.1336 | 3716.2604 | 1938.5842 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9283 | 19 | 0.045542 | 102911109 | WYANDOTTE 1109 | WYANDOTTE 110932586 | 2312.4178 | 0.86529 | 739 | 1.4369 | 3717.6973 | 1937.7189 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8769 | 22 | 0.045486 | 103331101 | CORNING 1101 | CORNING 110185162 | 9259.5842 | 1.0007 | 693 | 5.7536 | 3723.4509 | 1936.7182 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 989 | 163 | 0.045463 | 183052113 | TEMPLETON 2113 | TEMPLETON 2113A70 | 39039.5646 | 7.4104 | 194 | 24.2581 | 3747.709 | 1929.3078 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8231 | 22 | 0.045442 | 254432104 | COARSEGOLD 2104 | COARSEGOLD 2104circuit_breaker | 3906.143 | 0.99973 | 694 | 2.4272 | 3750.1361 | 1928.308 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3071 | 16 | 0.045236 | 83242105 | MORGAN HILL 2105 | MORGAN HILL 210542348 | 2297.9263 | 0.72378 | 796 | 1.4279 | 3751.564 | 1927.5843 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9493 | 36 | 0.046397 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101612 | 6226.4809 | 1.6703 | 542 | 3.869 | 3755.433 | 1925.914 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 9493 | 1 | 2.0413e-05 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101612 | 6226.4809 | 2.0413e-05 | 542 | 3.869 | 3759.3019 | 1925.9139 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 2142 | 47 | 0.04513 | 42891102 | GEYSERVILLE 1102 | GEYSERVILLE 110289714 | 4342.1142 | 2.1211 | 478 | 2.6981 | 3762 | 1923.7928 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8360 | 24 | 0.044737 | 103451101 | KESWICK 1101 | KESWICK 11011586 | 11919.3257 | 1.0737 | 671 | 7.4063 | 3769.4063 | 1922.7191 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4774 | 2 | 0.044408 | 43051101 | MONTICELLO 1101 | MONTICELLO 1101720 | 11082.9735 | 0.088816 | 1382 | 6.8866 | 3776.2929 | 1922.6303 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5927 | 111 | 0.04412 | 102911107 | WYANDOTTE 1107 | WYANDOTTE 110737472 | 13224.7658 | 4.8973 | 273 | 8.2175 | 3784.5104 | 1917.733 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1166 | 277 | 0.043864 | 152561105 | PENRYN 1105 | PENRYN 11051342 | 32719.8008 | 12.1504 | 123 | 20.3311 | 3804.8416 | 1905.5827 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7909 | 52 | 0.043849 | 163781705 | PEORIA 1705 | PEORIA 1705circuit_breaker | 11339.1152 | 2.2801 | 453 | 7.0458 | 3811.8874 | 1903.3025 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 821 | 618 | 0.043798 | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 1107circuit_breaker | 81888.8347 | 27.067 | 37 | 50.8833 | 3862.7707 | 1876.2356 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8727 | 6 | 0.043664 | 182661106 | SAN MIGUEL 1106 | SAN MIGUEL 1106N34 | 3289.5998 | 0.26198 | 1084 | 2.0441 | 3864.8148 | 1875.9736 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1489 | 80 | 0.043592 | 152261105 | DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 110518935 | 10773.8274 | 3.4873 | 351 | 6.6945 | 3871.5093 | 1872.4862 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3665 | 409 | 0.043277 | 42661104 | WILLITS 1104 | WILLITS 1104934 | 49456.388 | 17.7005 | 81 | 30.7308 | 3902.2401 | 1854.7858 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3912 | 274 | 0.043159 | 163541101 | OLETA 1101 | OLETA 11011208 | 52737.327 | 11.8256 | 126 | 32.7694 | 3935.0095 | 1842.9601 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 422 | 281 | 0.043122 | 102931102 | COTTONWOOD 1102 | COTTONWOOD 11021578 | 45006.6873 | 12.1173 | 124 | 27.9659 | 3962.9754 | 1830.8428 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7588 | 18 | 0.04305 | 103551101 | RISING RIVER 1101 | RISING RIVER 11011532 | 4719.7178 | 0.77491 | 773 | 2.9327 | 3965.9081 | 1830.0679 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4578 | 98 | 0.042859 | 103401102 | GIRVAN 1102 | GIRVAN 110280726 | 10897.7797 | 4.2002 | 305 | 6.7716 | 3972.6796 | 1825.8677 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5406 | 46 | 0.042741 | 43361102 | HIGHLANDS 1102 | HIGHLANDS 110280660 | 9091.4024 | 1.9661 | 506 | 5.6491 | 3978.3288 | 1823.9016 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7124 | 5 | 0.042507 | 63681105 | PUTAH CREEK 1105 | PUTAH CREEK 11058812 | 1876.8402 | 0.21253 | 1148 | 1.1662 | 3979.495 | 1823.689 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 129 | 389 | 0.042412 | 252521103 | SAN JOAQUIN #2 1103 | SAN JOAQUIN #2 1103circuit_breaker | 109277.3995 | 16.4981 | 86 | 67.9018 | 4047.3968 | 1807.1909 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4241 | 149 | 0.042918 | 162991102 | CORRAL 1102 | CORRAL 110236666 | 26276.8597 | 6.3947 | 223 | 16.3277 | 4063.7245 | 1800.7962 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Coast | 4241 | 2 | 3.7537e-06 | 162991102 | CORRAL 1102 | CORRAL 110236666 | 26276.8597 | 7.5073e-06 | 223 | 16.3277 | 4080.0522 | 1800.7962 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 6566 | 77 | 0.042327 | 192221101 | GARBERVILLE 1101 | GARBERVILLE 1101circuit_breaker | 9321.3726 | 3.2592 | 370 | 5.792 | 4085.8442 | 1797.537 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2867 | 26 | 0.042274 | 103441103 | JESSUP 1103 | JESSUP 110338864 | 2871.393 | 1.0991 | 661 | 1.7842 | 4087.6284 | 1796.4378 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4913 | 22 | 0.042242 | 103541104 | RED BLUFF 1104 | RED BLUFF 11041566 | 15161.638 | 0.92933 | 720 | 9.421 | 4097.0494 | 1795.5085 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5512 | 74 | 0.042161 | 192321121 | FORT SEWARD 1121 | FORT SEWARD 1121circuit_breaker | 11649.7657 | 3.1199 | 385 | 7.2388 | 4104.2882 | 1792.3886 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2581 | 140 | 0.042039 | 153701101 | LINCOLN 1101 | LINCOLN 11012310 | 17598.5614 | 5.8855 | 241 | 10.9352 | 4115.2234 | 1786.5031 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3722 | 86 | 0.041845 | 103461102 | PANORAMA 1102 | PANORAMA 11021526 | 17981.687 | 3.5987 | 336 | 11.1733 | 4126.3967 | 1782.9044 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7240 | 42 | 0.041669 | 12022212 | CLAYTON 2212 | CLAYTON 22127758 | 5210.7596 | 1.7501 | 533 | 3.2378 | 4129.6346 | 1781.1543 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 380 | 215 | 0.041626 | 162991101 | CORRAL 1101 | CORRAL 110112606 | 36019.0707 | 8.9495 | 169 | 22.3812 | 4152.0158 | 1772.2047 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8902 | 4 | 0.041486 | 253642104 | POSO MOUNTAIN 2104 | POSO MOUNTAIN 2104circuit_breaker | 5614.2654 | 0.16595 | 1218 | 3.4885 | 4155.5043 | 1772.0388 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4012 | 281 | 0.041144 | 103441101 | JESSUP 1101 | JESSUP 110141356 | 52454.1999 | 11.5613 | 130 | 32.5935 | 4188.0978 | 1760.4775 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3133 | 241 | 0.041052 | 254151101 | AUBERRY 1101 | AUBERRY 1101R314 | 67647.5297 | 9.8936 | 154 | 42.0342 | 4230.132 | 1750.5839 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5257 | 270 | 0.040964 | 43311102 | KONOCTI 1102 | KONOCTI 110264664 | 43740.7498 | 11.0602 | 139 | 27.1792 | 4257.3113 | 1739.5237 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8284 | 23 | 0.040901 | 192311142 | FRUITLAND 1142 | FRUITLAND 114293234 | 18464.5673 | 0.94073 | 718 | 11.4733 | 4268.7846 | 1738.5829 | 10.6913 | 0.94073 | 1 | #N/A | #N/A | 1738.5829
North Valley | 9163 | 2 | 0.040887 | 103321101 | CEDAR CREEK 1101 | CEDAR CREEK 11011710 | 117.4627 | 0.081775 | 1415 | 0.072988 | 4268.8576 | 1738.5012 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6980 | 126 | 0.040859 | 152561107 | PENRYN 1107 | PENRYN 11072708 | 15108.1749 | 5.1482 | 259 | 9.3878 | 4278.2454 | 1733.353 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2495 | 100 | 0.040819 | 42571101 | MOLINO 1101 | MOLINO 1101338 | 10257.7274 | 4.0819 | 310 | 6.3739 | 4284.6192 | 1729.271 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2159 | 207 | 0.04073 | 163761704 | RACETRACK 1704 | RACETRACK 1704circuit_breaker | 36598.3736 | 8.431 | 174 | 22.7412 | 4307.3604 | 1720.84 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 84 | 317 | 0.040685 | 103331101 | CORNING 1101 | CORNING 110185152 | 37238.3316 | 12.8973 | 113 | 23.1388 | 4330.4992 | 1707.9427 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1849 | 397 | 0.040607 | 152561103 | PENRYN 1103 | PENRYN 1103circuit_breaker | 45768.8176 | 16.1209 | 90 | 28.4394 | 4358.9387 | 1691.8218 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 992 | 251 | 0.040443 | 42711101 | CALISTOGA 1101 | CALISTOGA 1101890 | 37703.1619 | 10.1513 | 148 | 23.4277 | 4382.3663 | 1681.6705 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 133 | 334 | 0.040275 | 153612103 | CLARKSVILLE 2103 | CLARKSVILLE 210319572 | 49656.7912 | 13.4518 | 106 | 30.8553 | 4413.2216 | 1668.2187 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5999 | 80 | 0.040151 | 102781101 | ELK CREEK 1101 | ELK CREEK 11012004 | 34785.4675 | 3.2121 | 376 | 21.6147 | 4434.8363 | 1665.0066 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3249 | 132 | 0.0401 | 42681102 | LAYTONVILLE 1102 | LAYTONVILLE 110237586 | 21840.8846 | 5.2932 | 254 | 13.5713 | 4448.4076 | 1659.7133 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7987 | 62 | 0.039949 | 14422109 | CAYETANO 2109 | CAYETANO 21099504 | 23307.0461 | 2.4769 | 427 | 14.4823 | 4462.8899 | 1657.2365 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1807 | 224 | 0.039866 | 153132105 | NARROWS 2105 | NARROWS 21057203 | 29234.7991 | 8.9301 | 170 | 18.1657 | 4481.0555 | 1648.3064 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4918 | 112 | 0.039623 | 192461102 | BRIDGEVILLE 1102 | BRIDGEVILLE 1102circuit_breaker | 40164.6361 | 4.4377 | 289 | 24.9571 | 4506.0127 | 1643.8687 | 25.1581 | 4.4347 | 1 | #N/A | #N/A | 1643.8687
Sierra | 631 | 25 | 0.039513 | 152561105 | PENRYN 1105 | PENRYN 110550548 | 2946.7985 | 0.98781 | 701 | 1.8311 | 4507.8437 | 1642.8809 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2520 | 155 | 0.03943 | 152561103 | PENRYN 1103 | PENRYN 1103660 | 16391.1944 | 6.1116 | 235 | 10.185 | 4518.0288 | 1636.7693 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4552 | 72 | 0.039291 | 102781101 | ELK CREEK 1101 | ELK CREEK 11012212 | 17989.0535 | 2.8289 | 401 | 11.1779 | 4529.2066 | 1633.9404 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3901 | 643 | 0.039283 | 153662102 | APPLE HILL 2102 | APPLE HILL 2102circuit_breaker | 66687.7451 | 25.2589 | 43 | 41.4378 | 4570.6445 | 1608.6814 | 37.2691 | 25.2589 | 1 | #N/A | #N/A | 1608.6814
Sierra | 2860 | 42 | 0.039271 | 153652108 | SHINGLE SPRINGS 2108 | SHINGLE SPRINGS 210819762 | 6558.8623 | 1.6494 | 546 | 4.0755 | 4574.7199 | 1607.032 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8475 | 69 | 0.039041 | 254601103 | SAND CREEK 1103 | SAND CREEK 1103circuit_breaker | 20610.8944 | 2.6938 | 408 | 12.807 | 4587.527 | 1604.3382 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3594 | 3 | 0.03904 | 13751102 | VASCO 1102 | VASCO 1102MR178 | 2230.6889 | 0.11712 | 1302 | 1.3861 | 4588.913 | 1604.2211 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3008 | 262 | 0.038838 | 153132105 | NARROWS 2105 | NARROWS 21052228 | 33185.7143 | 10.1756 | 147 | 20.6206 | 4609.5337 | 1594.0455 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4039 | 286 | 0.038804 | 103401101 | GIRVAN 1101 | GIRVAN 1101323094 | 58215.1727 | 11.098 | 138 | 36.1732 | 4645.7069 | 1582.9475 | 35.307 | 11.098 | 1 | #N/A | 1582.9475 | #N/A
North Valley | 2841 | 267 | 0.038648 | 102911107 | WYANDOTTE 1107 | WYANDOTTE 11071026 | 34466.4557 | 10.319 | 145 | 21.4165 | 4667.1234 | 1572.6285 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2229 | 14 | 0.038647 | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102414 | 8076.5942 | 0.54106 | 883 | 5.0186 | 4672.1419 | 1572.0874 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7670 | 28 | 0.038455 | 152561105 | PENRYN 1105 | PENRYN 110550550 | 3634.5722 | 1.0768 | 670 | 2.2584 | 4674.4003 | 1571.0107 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4992 | 110 | 0.038404 | 103331102 | CORNING 1102 | CORNING 11021622 | 54857.2254 | 4.2244 | 302 | 34.0867 | 4708.487 | 1566.7862 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3079 | 1 | 0.29793 | 152261105 | DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 11057722 | 95268.3331 | 0.29793 | 30 | 59.197 | 4767.684 | 1566.4883 | 48.4366 | 27.443 | 2 | #N/A | #N/A | 1566.4883
Sierra | 3079 | 743 | 0.038021 | 152261105 | DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 11057722 | 95268.3331 | 28.2497 | 30 | 59.197 | 4826.881 | 1538.2386 |  |  | 2 | #N/A | #N/A | 1538.2386
Central Coast | 1699 | 18 | 0.038288 | 183052112 | TEMPLETON 2112 | TEMPLETON 2112R28 | 3272.9638 | 0.68918 | 813 | 2.0337 | 4828.9147 | 1537.5494 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3240 | 20 | 0.038067 | 103541104 | RED BLUFF 1104 | RED BLUFF 1104circuit_breaker | 2365.4631 | 0.76134 | 778 | 1.4698 | 4830.3845 | 1536.7881 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5549 | 8 | 0.037729 | 43051101 | MONTICELLO 1101 | MONTICELLO 110165454 | 1332.2655 | 0.30184 | 1036 | 0.82783 | 4831.2124 | 1536.4862 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5262 | 50 | 0.037642 | 152561105 | PENRYN 1105 | PENRYN 11052406 | 4637.0241 | 1.8821 | 518 | 2.8813 | 4834.0937 | 1534.6041 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4504 | 123 | 0.037498 | 153652110 | SHINGLE SPRINGS 2110 | SHINGLE SPRINGS 211051790 | 12398.7678 | 4.6123 | 280 | 7.7042 | 4841.7979 | 1529.9919 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5336 | 7 | 0.037301 | 254452102 | MARIPOSA 2102 | MARIPOSA 2102241564 | 874.7258 | 0.2611 | 1085 | 0.54353 | 4842.3414 | 1529.7308 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4183 | 33 | 0.037201 | 43292102 | PUEBLO 2102 | PUEBLO 2102618 | 3904.0753 | 1.2276 | 623 | 2.4259 | 4844.7673 | 1528.5031 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 759 | 492 | 0.037041 | 152261105 | DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 11052102 | 60433.983 | 18.2244 | 74 | 37.5519 | 4882.3193 | 1510.2788 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3480 | 88 | 0.036598 | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21092053 | 9206.1637 | 3.2207 | 374 | 5.7204 | 4888.0397 | 1507.0581 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5292 | 6 | 0.036536 | 63601108 | VACAVILLE 1108 | VACAVILLE 110847860 | 451.5656 | 0.21922 | 1138 | 0.28059 | 4888.3203 | 1506.8389 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2013 | 27 | 0.036411 | 42681101 | LAYTONVILLE 1101 | LAYTONVILLE 1101518 | 3441.5642 | 0.9831 | 702 | 2.1385 | 4890.4588 | 1505.8558 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 345 | 9 | 0.036139 | 43292102 | PUEBLO 2102 | PUEBLO 2102656 | 592.9592 | 0.32525 | 1008 | 0.36845 | 4890.8272 | 1505.5305 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 512 | 31 | 0.03591 | 42661103 | WILLITS 1103 | WILLITS 1103696 | 8552.3738 | 1.1132 | 657 | 5.3142 | 4896.1414 | 1504.4173 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 508 | 376 | 0.035823 | 153612104 | CLARKSVILLE 2104 | CLARKSVILLE 210413352 | 54145.4284 | 13.4695 | 105 | 33.6444 | 4929.7858 | 1490.9478 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2819 | 547 | 0.035775 | 153132101 | NARROWS 2101 | NARROWS 21011202 | 73260.5674 | 19.5689 | 62 | 45.522 | 4975.3078 | 1471.379 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2065 | 215 | 0.035745 | 153741101 | DOBBINS 1101 | DOBBINS 11011808 | 24893.8312 | 7.6851 | 186 | 15.4683 | 4990.7761 | 1463.6938 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 590 | 41 | 0.035696 | 43201102 | STAFFORD 1102 | STAFFORD 1102524 | 9046.5504 | 1.4635 | 578 | 5.6213 | 4996.3974 | 1462.2303 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7656 | 75 | 0.03542 | 14052103 | NORTH DUBLIN 2103 | NORTH DUBLIN 2103circuit_breaker | 20889.9745 | 2.6565 | 413 | 12.9804 | 5009.3778 | 1459.5738 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5383 | 27 | 0.035394 | 13751102 | VASCO 1102 | VASCO 110211338 | 8850.5675 | 0.95564 | 712 | 5.4995 | 5014.8773 | 1458.6182 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2279 | 94 | 0.035216 | 103221101 | KANAKA 1101 | KANAKA 11011034 | 21171.6713 | 3.3103 | 366 | 13.1555 | 5028.0328 | 1455.3078 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6475 | 9 | 0.034655 | 152571101 | HORSESHOE 1101 | HORSESHOE 11011682 | 944.4917 | 0.31189 | 1019 | 0.58688 | 5028.6196 | 1454.9959 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9707 | 8 | 0.034594 | 42891102 | GEYSERVILLE 1102 | GEYSERVILLE 1102756 | 948.4078 | 0.27675 | 1068 | 0.58931 | 5029.2089 | 1454.7192 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1983 | 146 | 0.034575 | 153791101 | SMARTVILLE 1101 | SMARTVILLE 1101circuit_breaker | 26009.9248 | 5.0479 | 263 | 16.1618 | 5045.3708 | 1449.6713 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8449 | 8 | 0.034451 | 43211102 | HARTLEY 1102 | HARTLEY 1102524 | 2350.321 | 0.27561 | 1070 | 1.4604 | 5046.8312 | 1449.3957 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4143 | 105 | 0.033977 | 43191102 | REDBUD 1102 | REDBUD 1102circuit_breaker | 26827.5429 | 3.5676 | 339 | 16.6699 | 5063.501 | 1445.8281 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1419 | 203 | 0.033752 | 192321122 | FORT SEWARD 1122 | FORT SEWARD 1122circuit_breaker | 28255.3669 | 6.8517 | 207 | 17.5571 | 5081.0581 | 1438.9764 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5135 | 235 | 0.033689 | 43361103 | HIGHLANDS 1103 | HIGHLANDS 1103482 | 38824.923 | 7.917 | 184 | 24.1247 | 5105.1828 | 1431.0594 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3383 | 22 | 0.033661 | 43021102 | WOODACRE 1102 | WOODACRE 1102851 | 2053.4749 | 0.74053 | 786 | 1.276 | 5106.4588 | 1430.3188 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8364 | 3 | 0.033609 | 42021102 | NAPA 1102 | NAPA 11025039 | 68.3438 | 0.10083 | 1350 | 0.042467 | 5106.5012 | 1430.218 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3421 | 197 | 0.033578 | 254061103 | DUNLAP 1103 | DUNLAP 11037040 | 39870.7942 | 6.6149 | 212 | 24.7746 | 5131.2758 | 1423.603 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1043 | 157 | 0.033565 | 254452101 | MARIPOSA 2101 | MARIPOSA 210110990 | 64117.5165 | 5.2697 | 255 | 39.8408 | 5171.1165 | 1418.3334 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2034 | 369 | 0.033444 | 42601101 | PHILO 1101 | PHILO 1101circuit_breaker | 48254.7037 | 12.3408 | 118 | 29.9841 | 5201.1006 | 1405.9925 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7419 | 79 | 0.033293 | 42821102 | CLOVERDALE 1102 | CLOVERDALE 11024646 | 22119.9907 | 2.6302 | 415 | 13.7447 | 5214.8453 | 1403.3624 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6331 | 12 | 0.033289 | 83182107 | LLAGAS 2107 | LLAGAS 2107XR188 | 2228.2099 | 0.39946 | 958 | 1.3845 | 5216.2299 | 1402.9629 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 444 | 30 | 0.03312 | 42711101 | CALISTOGA 1101 | CALISTOGA 11011087 | 3128.3884 | 0.9936 | 697 | 1.9439 | 5218.1738 | 1401.9693 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5478 | 152 | 0.03298 | 42821102 | CLOVERDALE 1102 | CLOVERDALE 1102672 | 35674.8205 | 5.013 | 265 | 22.1673 | 5240.3411 | 1396.9563 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1087 | 411 | 0.03466 | 103191101 | BANGOR 1101 | BANGOR 11011958 | 54026.2311 | 14.2451 | 101 | 33.5703 | 5273.9114 | 1382.7112 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Valley | 1087 | 28 | 0.0078783 | 103191101 | BANGOR 1101 | BANGOR 11011958 | 54026.2311 | 0.22059 | 101 | 33.5703 | 5307.4817 | 1382.4907 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 2125 | 176 | 0.032907 | 42251101 | HOPLAND 1101 | HOPLAND 11014626 | 40127.548 | 5.7917 | 243 | 24.9341 | 5332.4158 | 1376.699 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5265 | 112 | 0.032801 | 152561103 | PENRYN 1103 | PENRYN 110351658 | 12333.3131 | 3.6738 | 330 | 7.6636 | 5340.0794 | 1373.0252 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3279 | 103 | 0.032753 | 254421103 | OAKHURST 1103 | OAKHURST 110310570 | 15685.0936 | 3.3736 | 363 | 9.7463 | 5349.8257 | 1369.6516 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3432 | 134 | 0.03275 | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 40504.507 | 4.3884 | 292 | 25.1683 | 5374.994 | 1365.2632 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6968 | 78 | 0.032553 | 153612105 | CLARKSVILLE 2105 | CLARKSVILLE 210575884 | 17165.4943 | 2.5391 | 420 | 10.6661 | 5385.6601 | 1362.7241 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1782 | 247 | 0.032468 | 42821101 | CLOVERDALE 1101 | CLOVERDALE 1101112 | 30254.9758 | 8.0196 | 179 | 18.7996 | 5404.4597 | 1354.7045 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5193 | 14 | 0.032454 | 14241101 | SUNOL 1101 | SUNOL 1101MR169 | 4614.9374 | 0.45435 | 928 | 2.8676 | 5407.3273 | 1354.2501 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7752 | 1 | 0.031908 | 14662106 | TASSAJARA 2106 | TASSAJARA 2106circuit_breaker | 809.5956 | 0.031908 | 1663 | 0.50306 | 5407.8303 | 1354.2182 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7037 | 111 | 0.031745 | 14232108 | SAN RAMON 2108 | SAN RAMON 2108circuit_breaker | 13911.3335 | 3.5237 | 346 | 8.6441 | 5416.4744 | 1350.6945 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5749 | 80 | 0.031715 | 43211101 | HARTLEY 1101 | HARTLEY 11011306 | 15400.0788 | 2.5372 | 421 | 9.5692 | 5426.0436 | 1348.1573 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9280 | 13 | 0.031674 | 103461102 | PANORAMA 1102 | PANORAMA 11021632 | 13751.6318 | 0.41176 | 952 | 8.5449 | 5434.5885 | 1347.7456 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6966 | 2 | 0.031628 | 63642113 | PEABODY 2113 | PEABODY 2113circuit_breaker | 1530.5409 | 0.063256 | 1482 | 0.95103 | 5435.5395 | 1347.6823 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6091 | 41 | 0.031508 | 162161101 | ELECTRA 1101 | ELECTRA 11011238 | 5695.7641 | 1.2918 | 614 | 3.5392 | 5439.0787 | 1346.3905 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3175 | 425 | 0.031347 | 42561107 | FULTON 1107 | FULTON 1107214 | 48113.355 | 13.3226 | 108 | 29.8962 | 5468.9749 | 1333.0678 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3347 | 10 | 0.031337 | 42271105 | COTATI 1105 | COTATI 1105616 | 2435.445 | 0.31337 | 1018 | 1.5133 | 5470.4882 | 1332.7545 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8781 | 52 | 0.03133 | 252192105 | BEAR VALLEY 2105 | BEAR VALLEY 21059570 | 12951.7997 | 1.6291 | 548 | 8.0479 | 5478.5361 | 1331.1253 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9323 | 91 | 0.031305 | 192221102 | GARBERVILLE 1102 | GARBERVILLE 110256048 | 7998.8346 | 2.8488 | 400 | 4.9702 | 5483.5064 | 1328.2765 | 4.8422 | 2.5452 | 1 | #N/A | #N/A | 1328.2765
North Coast | 5213 | 200 | 0.031247 | 192221102 | GARBERVILLE 1102 | GARBERVILLE 11024744 | 26935.3901 | 6.2493 | 233 | 16.7369 | 5500.2432 | 1322.0272 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2206 | 28 | 0.031244 | 162991103 | CORRAL 1103 | CORRAL 110313474 | 3896.5378 | 0.87484 | 734 | 2.4212 | 5502.6644 | 1321.1524 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5557 | 51 | 0.10861 | 103201102 | CHALLENGE 1102 | CHALLENGE 11021064 | 32164.5669 | 5.5392 | 166 | 19.9861 | 5522.6505 | 1315.6132 | 19.8066 | 9.1991 | 2 | #N/A | #N/A | 1315.6132
North Valley | 5557 | 244 | 0.015 | 103201102 | CHALLENGE 1102 | CHALLENGE 11021064 | 32164.5669 | 3.6599 | 166 | 19.9861 | 5542.6367 | 1311.9533 |  |  | 2 | #N/A | #N/A | 1311.9533
North Coast | 1014 | 202 | 0.031073 | 192401101 | HOOPA 1101 | HOOPA 11013290 | 21820.8937 | 6.2767 | 230 | 13.5589 | 5556.1955 | 1305.6766 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5882 | 40 | 0.030883 | 103261101 | ANDERSON 1101 | ANDERSON 1101circuit_breaker | 4993.2396 | 1.2353 | 619 | 3.1027 | 5559.2982 | 1304.4412 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6311 | 7 | 0.03067 | 62081104 | ARBUCKLE 1104 | ARBUCKLE 110447282 | 3612.2461 | 0.21469 | 1147 | 2.2445 | 5561.5427 | 1304.2266 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3215 | 31 | 0.03055 | 254421101 | OAKHURST 1101 | OAKHURST 1101circuit_breaker | 3669.1128 | 0.94705 | 715 | 2.2799 | 5563.8226 | 1303.2795 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5210 | 103 | 0.030547 | 252192105 | BEAR VALLEY 2105 | BEAR VALLEY 210511210 | 27422.5497 | 3.1464 | 381 | 17.0396 | 5580.8622 | 1300.1331 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4284 | 96 | 0.030538 | 42711102 | CALISTOGA 1102 | CALISTOGA 1102769230 | 16210.9352 | 2.9316 | 394 | 10.073 | 5590.9352 | 1297.2015 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 903 | 23 | 0.030534 | 103541104 | RED BLUFF 1104 | RED BLUFF 11041630 | 3396.4013 | 0.70229 | 807 | 2.1104 | 5593.0456 | 1296.4993 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6478 | 17 | 0.030509 | 62881105 | MAXWELL 1105 | MAXWELL 11053008 | 5862.1498 | 0.51865 | 892 | 3.6426 | 5596.6882 | 1295.9806 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4180 | 198 | 0.030178 | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 11134566 | 18477.8969 | 5.9751 | 238 | 11.4816 | 5608.1698 | 1290.0055 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1463 | 180 | 0.030164 | 103561101 | STILLWATER 1101 | STILLWATER 110148950 | 20085.728 | 5.4295 | 249 | 12.4807 | 5620.6505 | 1284.5759 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7617 | 116 | 0.029975 | 42661103 | WILLITS 1103 | WILLITS 1103826 | 12450.1328 | 3.4771 | 352 | 7.7362 | 5628.3867 | 1281.0988 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7739 | 3 | 0.029822 | 103331102 | CORNING 1102 | CORNING 11021900 | 3377.7597 | 0.089467 | 1380 | 2.0988 | 5630.4855 | 1281.0094 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6662 | 2 | 0.029761 | 42631108 | PETALUMA C 1108 | PETALUMA C 1108208 | 19951.8799 | 0.059522 | 1497 | 12.3975 | 5642.883 | 1280.9498 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2407 | 69 | 0.029387 | 182631103 | SAN LUIS OBISPO 1103 | SAN LUIS OBISPO 110342344 | 14174.6452 | 2.0277 | 497 | 8.8077 | 5651.6907 | 1278.9221 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4559 | 201 | 0.029353 | 43432104 | SILVERADO 2104 | SILVERADO 210478268 | 19338.5201 | 5.9 | 240 | 12.0164 | 5663.7071 | 1273.0221 | 5.7636 | 2.8603 | 1 | #N/A | 1273.0221 | #N/A
North Coast | 4955 | 152 | 0.02926 | 42601101 | PHILO 1101 | PHILO 11013700 | 29050.7038 | 4.4475 | 287 | 18.0513 | 5681.7584 | 1268.5746 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4809 | 186 | 0.029177 | 153132105 | NARROWS 2105 | NARROWS 21052748 | 21028.293 | 5.427 | 250 | 13.0664 | 5694.8248 | 1263.1476 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3510 | 441 | 0.029093 | 103321101 | CEDAR CREEK 1101 | CEDAR CREEK 11011608 | 53533.2272 | 12.83 | 114 | 33.264 | 5728.0888 | 1250.3176 | 32.8294 | 12.83 | 1 | #N/A | #N/A | 1250.3176
Sierra | 3858 | 33 | 0.02904 | 63801105 | JAMESON 1105 | JAMESON 11059472 | 3577.3351 | 0.95833 | 710 | 2.2229 | 5730.3116 | 1249.3592 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7546 | 341 | 0.028957 | 42891101 | GEYSERVILLE 1101 | GEYSERVILLE 110179788 | 63216.603 | 9.8744 | 155 | 39.281 | 5769.5926 | 1239.4848 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 930 | 506 | 0.02894 | 254452102 | MARIPOSA 2102 | MARIPOSA 21029590 | 58305.4261 | 14.6437 | 98 | 36.2293 | 5805.8219 | 1224.8411 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 676 | 5 | 0.02847 | 252921110 | STONE CORRAL 1110 | STONE CORRAL 111075288 | 1818.7235 | 0.14235 | 1258 | 1.1301 | 5806.952 | 1224.6988 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6713 | 23 | 0.028239 | 182581105 | GOLDTREE 1105 | GOLDTREE 1105circuit_breaker | 11071.7645 | 0.6495 | 834 | 6.8797 | 5813.8317 | 1224.0493 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 64 | 295 | 0.028175 | 43021102 | WOODACRE 1102 | WOODACRE 1102circuit_breaker | 33390.0506 | 8.3115 | 175 | 20.7476 | 5834.5793 | 1215.7377 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1019 | 260 | 0.028094 | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 46009.8876 | 7.3045 | 196 | 28.5892 | 5863.1685 | 1208.4333 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7563 | 138 | 0.028043 | 43311102 | KONOCTI 1102 | KONOCTI 1102716 | 21759.5686 | 3.87 | 319 | 13.5208 | 5876.6892 | 1204.5633 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 49 | 437 | 0.027919 | 43361103 | HIGHLANDS 1103 | HIGHLANDS 1103520 | 75802.3106 | 12.2004 | 121 | 47.1014 | 5923.7906 | 1192.3629 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6679 | 58 | 0.027902 | 183052113 | TEMPLETON 2113 | TEMPLETON 21136055 | 63807.832 | 1.6183 | 551 | 39.6483 | 5963.4389 | 1190.7445 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4431 | 827 | 0.027718 | 254452102 | MARIPOSA 2102 | MARIPOSA 210237288 | 136885.5796 | 22.9229 | 49 | 85.0567 | 6048.4957 | 1167.8216 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3201 | 64 | 0.027559 | 252192105 | BEAR VALLEY 2105 | BEAR VALLEY 21059480 | 19971.3977 | 1.7638 | 530 | 12.4096 | 6060.9053 | 1166.0579 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6532 | 293 | 0.02733 | 254452102 | MARIPOSA 2102 | MARIPOSA 21021960 | 39674.5223 | 8.0077 | 182 | 24.6526 | 6085.5579 | 1158.0502 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4009 | 49 | 0.027276 | 183052113 | TEMPLETON 2113 | TEMPLETON 2113A60 | 10180.3906 | 1.3365 | 606 | 6.3258 | 6091.8837 | 1156.7136 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6409 | 53 | 0.0272 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 110281296 | 10798.5955 | 1.4416 | 583 | 6.7099 | 6098.5937 | 1155.272 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6188 | 115 | 0.027186 | 252811102 | MERCED FALLS 1102 | MERCED FALLS 110238748 | 24704.6356 | 3.1264 | 383 | 15.3507 | 6113.9444 | 1152.1456 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6535 | 126 | 0.027125 | 163781704 | PEORIA 1704 | PEORIA 170411232 | 19016.7925 | 3.4178 | 356 | 11.8165 | 6125.7609 | 1148.7279 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4898 | 62 | 0.027087 | 43021101 | WOODACRE 1101 | WOODACRE 11011456 | 6154.4242 | 1.6794 | 540 | 3.8242 | 6129.5851 | 1147.0485 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5449 | 8 | 0.026934 | 83242111 | MORGAN HILL 2111 | MORGAN HILL 2111XR186 | 2744.6855 | 0.21547 | 1145 | 1.7055 | 6131.2905 | 1146.833 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3615 | 25 | 0.026675 | 42031122 | ALTO 1122 | ALTO 11221212 | 2589.3247 | 0.66688 | 822 | 1.6089 | 6132.8995 | 1146.1661 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8575 | 14 | 0.026665 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 11011314 | 1494.2319 | 0.3733 | 973 | 0.92847 | 6133.8279 | 1145.7928 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6168 | 7 | 0.026603 | 63172101 | MADISON 2101 | MADISON 210137082 | 1451.8754 | 0.18622 | 1184 | 0.90215 | 6134.7301 | 1145.6066 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4047 | 411 | 0.026522 | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 2109circuit_breaker | 43399.3801 | 10.9005 | 142 | 26.9671 | 6161.6972 | 1134.7061 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6292 | 85 | 0.026185 | 42891101 | GEYSERVILLE 1101 | GEYSERVILLE 110137454 | 10482.9729 | 2.2257 | 462 | 6.5138 | 6168.211 | 1132.4804 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3547 | 307 | 0.02615 | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 33902.4073 | 8.028 | 178 | 21.066 | 6189.277 | 1124.4524 | 21.1589 | 8.028 | 1 | #N/A | #N/A | 1124.4524
Sierra | 4023 | 16 | 0.026066 | 63601104 | VACAVILLE 1104 | VACAVILLE 1104circuit_breaker | 1499.3098 | 0.41706 | 948 | 0.93163 | 6190.2086 | 1124.0353 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5041 | 83 | 0.025913 | 42271103 | COTATI 1103 | COTATI 1103132 | 40702.0776 | 2.1508 | 475 | 25.2911 | 6215.4997 | 1121.8845 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8339 | 78 | 0.025891 | 192461101 | BRIDGEVILLE 1101 | BRIDGEVILLE 110169866 | 10521.7386 | 2.0195 | 500 | 6.5379 | 6222.0376 | 1119.865 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6851 | 50 | 0.025801 | 42871101 | UPPER LAKE 1101 | UPPER LAKE 1101472084 | 7182.4083 | 1.29 | 616 | 4.4629 | 6226.5006 | 1118.5749 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2773 | 149 | 0.025788 | 43432104 | SILVERADO 2104 | SILVERADO 2104806 | 29193.0346 | 3.8424 | 322 | 18.1397 | 6244.6403 | 1114.7326 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7532 | 44 | 0.025728 | 192311142 | FRUITLAND 1142 | FRUITLAND 11426064 | 9593.2152 | 1.132 | 652 | 5.9609 | 6250.6012 | 1113.6006 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5137 | 211 | 0.025716 | 103401101 | GIRVAN 1101 | GIRVAN 11011636 | 24954.3397 | 5.4261 | 251 | 15.5059 | 6266.1071 | 1108.1744 | 19.1061 | 5.4261 | 1 | #N/A | 1108.1744 | #N/A
Bay Area | 7659 | 186 | 0.025598 | 43432102 | SILVERADO 2102 | SILVERADO 210258626 | 24429.8093 | 4.7612 | 276 | 15.18 | 6281.2871 | 1103.4132 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4776 | 131 | 0.025593 | 103541105 | RED BLUFF 1105 | RED BLUFF 110585632 | 20457.0684 | 3.3527 | 364 | 12.7114 | 6293.9985 | 1100.0605 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2338 | 18 | 0.025539 | 182631103 | SAN LUIS OBISPO 1103 | SAN LUIS OBISPO 1103circuit_breaker | 4883.612 | 0.45971 | 926 | 3.0345 | 6297.033 | 1099.6008 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6264 | 61 | 0.025489 | 83242105 | MORGAN HILL 2105 | MORGAN HILL 2105XR070 | 9521.4048 | 1.5548 | 566 | 5.9163 | 6302.9494 | 1098.046 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 749 | 588 | 0.025511 | 103191101 | BANGOR 1101 | BANGOR 11017446 | 69879.8096 | 15.0002 | 95 | 43.4213 | 6346.3707 | 1083.0458 | 24.9468 | 8.8686 | 2 | #N/A | #N/A | 1083.0458
Bay Area | 749 | 1 | 0.0098998 | 103191101 | BANGOR 1101 | BANGOR 11017446 | 69879.8096 | 0.0098998 | 95 | 43.4213 | 6389.7919 | 1083.0359 |  |  | 2 | #N/A | #N/A | 1083.0359
Central Valley | 7470 | 47 | 0.025339 | 254452101 | MARIPOSA 2101 | MARIPOSA 210197142 | 7406.0615 | 1.1909 | 632 | 4.6019 | 6394.3939 | 1081.845 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5878 | 124 | 0.025253 | 43292103 | PUEBLO 2103 | PUEBLO 210378504 | 12406.3687 | 3.1314 | 382 | 7.709 | 6402.1028 | 1078.7135 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7148 | 318 | 0.025203 | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 11136751 | 35962.163 | 8.0144 | 181 | 22.3458 | 6424.4487 | 1070.6991 | 20.5953 | 7.9553 | 1 | #N/A | #N/A | 1070.6991
Bay Area | 8719 | 121 | 0.025136 | 42711101 | CALISTOGA 1101 | CALISTOGA 110189150 | 15360.2828 | 3.0414 | 388 | 9.5444 | 6433.9931 | 1067.6577 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2102 | 474 | 0.025135 | 42711101 | CALISTOGA 1101 | CALISTOGA 1101736 | 56743.887 | 11.914 | 125 | 35.259 | 6469.2521 | 1055.7436 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3119 | 290 | 0.025091 | 182562102 | CHOLAME 2102 | CHOLAME 2102X06 | 53331.3621 | 7.2765 | 197 | 33.1386 | 6502.3907 | 1048.4671 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5912 | 129 | 0.025012 | 254151101 | AUBERRY 1101 | AUBERRY 1101R2839 | 20609.1212 | 3.2266 | 373 | 12.8059 | 6515.1966 | 1045.2405 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8745 | 80 | 0.024987 | 192311141 | FRUITLAND 1141 | FRUITLAND 114137410 | 7642.4024 | 1.9989 | 503 | 4.7488 | 6519.9453 | 1043.2416 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7319 | 114 | 0.025417 | 63801102 | JAMESON 1102 | JAMESON 110265516 | 12202.9885 | 2.8975 | 396 | 7.5826 | 6527.5279 | 1040.3441 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 7319 | 2 | 1.6305e-06 | 63801102 | JAMESON 1102 | JAMESON 110265516 | 12202.9885 | 3.2609e-06 | 396 | 7.5826 | 6535.1105 | 1040.3441 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 2042 | 280 | 0.024759 | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 11051904 | 47497.3243 | 6.9326 | 202 | 29.5135 | 6564.624 | 1033.4115 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3315 | 46 | 0.024681 | 43432102 | SILVERADO 2102 | SILVERADO 2102714 | 5471.307 | 1.1353 | 649 | 3.3997 | 6568.0237 | 1032.2761 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4876 | 264 | 0.02471 | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 11031448 | 49370.4838 | 6.5234 | 216 | 30.6774 | 6598.7011 | 1025.7527 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Sierra | 4876 | 1 | 0.012123 | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 11031448 | 49370.4838 | 0.012123 | 216 | 30.6774 | 6629.3784 | 1025.7406 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 3787 | 53 | 0.024606 | 42271102 | COTATI 1102 | COTATI 1102681 | 6118.1742 | 1.3041 | 610 | 3.8017 | 6633.1801 | 1024.4365 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4785 | 88 | 0.024551 | 103461102 | PANORAMA 1102 | PANORAMA 11021342 | 19597.5982 | 2.1604 | 472 | 12.1774 | 6645.3575 | 1022.276 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4620 | 85 | 0.024467 | 42271103 | COTATI 1103 | COTATI 110379140 | 15556.81 | 2.0797 | 482 | 9.6666 | 6655.024 | 1020.1963 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1266 | 140 | 0.024441 | 252811102 | MERCED FALLS 1102 | MERCED FALLS 11029470 | 36994.5762 | 3.4217 | 354 | 22.9874 | 6678.0114 | 1016.7746 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4163 | 42 | 0.024376 | 252521103 | SAN JOAQUIN #2 1103 | SAN JOAQUIN #2 1103157026 | 5166.9066 | 1.0238 | 684 | 3.2106 | 6681.222 | 1015.7508 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8986 | 1 | 0.024371 | 43040401 | GARCIA 0401 | GARCIA 0401circuit_breaker | 68.2264 | 0.024371 | 1726 | 0.042394 | 6681.2644 | 1015.7264 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7575 | 12 | 0.024278 | 182601106 | OCEANO 1106 | OCEANO 1106circuit_breaker | 1811.9234 | 0.29134 | 1050 | 1.1259 | 6682.3902 | 1015.4351 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 8031 | 89 | 0.024252 | 152201101 | PIKE CITY 1101 | PIKE CITY 11011720 | 9790.3862 | 2.1584 | 473 | 6.0835 | 6688.4737 | 1013.2767 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2652 | 29 | 0.024246 | 163541101 | OLETA 1101 | OLETA 110163500 | 6425.1593 | 0.70315 | 806 | 3.9924 | 6692.4661 | 1012.5735 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5290 | 66 | 0.024152 | 152561107 | PENRYN 1107 | PENRYN 11072706 | 7658.9338 | 1.594 | 557 | 4.759 | 6697.2251 | 1010.9795 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4382 | 135 | 0.023527 | 192411101 | LOW GAP 1101 | LOW GAP 11014086 | 18494.205 | 3.1761 | 377 | 11.4918 | 6708.7169 | 1007.8034 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3568 | 570 | 0.023503 | 43292103 | PUEBLO 2103 | PUEBLO 2103678 | 56171.914 | 13.3968 | 107 | 34.9036 | 6743.6205 | 994.4066 | 34.0994 | 13.0698 | 1 | #N/A | #N/A | 994.4066
North Valley | 1140 | 308 | 0.023479 | 102911107 | WYANDOTTE 1107 | WYANDOTTE 110777578 | 31530.7542 | 7.2314 | 200 | 19.5923 | 6763.2128 | 987.1752 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1668 | 100 | 0.023388 | 192221102 | GARBERVILLE 1102 | GARBERVILLE 11022010 | 10929.7392 | 2.3388 | 446 | 6.7914 | 6770.0042 | 984.8364 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1827 | 252 | 0.023184 | 153652105 | SHINGLE SPRINGS 2105 | SHINGLE SPRINGS 2105circuit_breaker | 31350.2151 | 5.8423 | 242 | 19.4801 | 6789.4843 | 978.9942 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1905 | 191 | 0.023156 | 163231101 | NORTH BRANCH 1101 | NORTH BRANCH 1101TS1115 | 28340.5083 | 4.4229 | 291 | 17.61 | 6807.0943 | 974.5713 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3891 | 17 | 0.023096 | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102878 | 2592.1013 | 0.39264 | 965 | 1.6107 | 6808.705 | 974.1787 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4601 | 25 | 0.022885 | 14592105 | BRENTWOOD 2105 | BRENTWOOD 2105B504R | 12899.4497 | 0.57211 | 867 | 8.0153 | 6816.7203 | 973.6065 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7989 | 52 | 0.024111 | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110264044 | 8899.6249 | 1.2537 | 611 | 5.53 | 6822.2503 | 972.3528 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 7989 | 5 | 0.0091459 | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110264044 | 8899.6249 | 0.04573 | 611 | 5.53 | 6827.7802 | 972.3071 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Sierra | 1677 | 38 | 0.022789 | 152691103 | HIGGINS 1103 | HIGGINS 11039753 | 3306.1166 | 0.86597 | 737 | 2.0543 | 6829.8346 | 971.4411 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1785 | 656 | 0.022752 | 254432104 | COARSEGOLD 2104 | COARSEGOLD 210410110 | 79684.5808 | 14.9256 | 96 | 49.5137 | 6879.3483 | 956.5155 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5286 | 27 | 0.022746 | 42271105 | COTATI 1105 | COTATI 1105634 | 11162.845 | 0.61415 | 848 | 6.9363 | 6886.2845 | 955.9013 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7221 | 71 | 0.02274 | 43311102 | KONOCTI 1102 | KONOCTI 1102948 | 9863.4507 | 1.6146 | 554 | 6.1289 | 6892.4134 | 954.2868 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7640 | 296 | 0.022706 | 42681102 | LAYTONVILLE 1102 | LAYTONVILLE 1102572 | 34430.0284 | 6.721 | 211 | 21.3938 | 6913.8072 | 947.5657 | 20.9059 | 6.6374 | 1 | #N/A | #N/A | 947.5657
Sierra | 5059 | 219 | 0.02259 | 152261106 | DIAMOND SPRINGS 1106 | DIAMOND SPRINGS 110656026 | 24259.9065 | 4.9473 | 270 | 15.0744 | 6928.8816 | 942.6184 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3735 | 195 | 0.022453 | 152691109 | HIGGINS 1109 | HIGGINS 1109594 | 23079.0602 | 4.3783 | 293 | 14.3407 | 6943.2223 | 938.2401 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6815 | 3 | 0.022388 | 43181102 | BELLEVUE 1102 | BELLEVUE 1102392 | 223.0422 | 0.067165 | 1465 | 0.13859 | 6943.3609 | 938.1729 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1017 | 100 | 0.022378 | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 11021312 | 15846.2392 | 2.2378 | 458 | 9.8464 | 6953.2073 | 935.9351 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6904 | 61 | 0.02234 | 43432104 | SILVERADO 2104 | SILVERADO 2104708 | 5638.2492 | 1.3627 | 600 | 3.5034 | 6956.7107 | 934.5724 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3092 | 167 | 0.022257 | 42711102 | CALISTOGA 1102 | CALISTOGA 1102634 | 19084.7717 | 3.7169 | 327 | 11.8587 | 6968.5694 | 930.8555 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1410 | 815 | 0.022179 | 254452101 | MARIPOSA 2101 | MARIPOSA 21019400 | 101390.2805 | 18.0755 | 76 | 63.001 | 7031.5704 | 912.78 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9107 | 14 | 0.022169 | 42711101 | CALISTOGA 1101 | CALISTOGA 110135588 | 4848.4058 | 0.31037 | 1021 | 3.0127 | 7034.5831 | 912.4696 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 500 | 98 | 0.022114 | 42711101 | CALISTOGA 1101 | CALISTOGA 110143924 | 11371.1135 | 2.1672 | 470 | 7.0657 | 7041.6487 | 910.3024 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6812 | 34 | 0.021951 | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | 12434.0103 | 0.74635 | 784 | 7.7261 | 7049.3749 | 909.5561 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1268 | 196 | 0.021889 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 11014646 | 29953.689 | 4.2902 | 301 | 18.6124 | 7067.9872 | 905.2659 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2172 | 39 | 0.021873 | 43051101 | MONTICELLO 1101 | MONTICELLO 11014360 | 11112.131 | 0.85304 | 746 | 6.9048 | 7074.892 | 904.4129 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2497 | 5 | 0.021854 | 42271102 | COTATI 1102 | COTATI 1102825 | 749.4567 | 0.10927 | 1328 | 0.46569 | 7075.3577 | 904.3036 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2933 | 9 | 0.021844 | 83432101 | HICKS 2101 | HICKS 2101XR548 | 1925.3259 | 0.1966 | 1164 | 1.1963 | 7076.554 | 904.107 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3243 | 48 | 0.024972 | 163541101 | OLETA 1101 | OLETA 11011217 | 21207.62 | 1.1987 | 498 | 13.1778 | 7089.7318 | 902.9083 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Sierra | 3243 | 45 | 0.018387 | 163541101 | OLETA 1101 | OLETA 11011217 | 21207.62 | 0.82741 | 498 | 13.1778 | 7102.9096 | 902.0809 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 5067 | 146 | 0.021613 | 42571102 | MOLINO 1102 | MOLINO 1102658 | 17538.0269 | 3.1554 | 379 | 10.8976 | 7113.8072 | 898.9255 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 14 | 102 | 0.021603 | 42951101 | MENDOCINO 1101 | MENDOCINO 110137462 | 11379.0989 | 2.2035 | 466 | 7.0706 | 7120.8779 | 896.722 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9243 | 113 | 0.021493 | 42261101 | BOLINAS 1101 | BOLINAS 1101530 | 17644.1845 | 2.4287 | 436 | 10.9636 | 7131.8415 | 894.2933 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 837 | 431 | 0.021444 | 152691103 | HIGGINS 1103 | HIGGINS 1103circuit_breaker | 45196.8083 | 9.2424 | 163 | 28.084 | 7159.9254 | 885.0509 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3302 | 13 | 0.021414 | 42891101 | GEYSERVILLE 1101 | GEYSERVILLE 1101circuit_breaker | 1595.2814 | 0.27838 | 1065 | 0.99126 | 7160.9167 | 884.7725 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5902 | 125 | 0.021389 | 254421102 | OAKHURST 1102 | OAKHURST 110210100 | 16350.2682 | 2.6736 | 411 | 10.1596 | 7171.0763 | 882.099 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3548 | 82 | 0.021317 | 103201102 | CHALLENGE 1102 | CHALLENGE 11021902 | 8106.7957 | 1.748 | 535 | 5.0373 | 7176.1136 | 880.351 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2908 | 307 | 0.021237 | 43311102 | KONOCTI 1102 | KONOCTI 110275382 | 35775.2475 | 6.5197 | 218 | 22.2297 | 7198.3433 | 873.8313 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1059 | 115 | 0.02122 | 12022212 | CLAYTON 2212 | CLAYTON 2212Y504R | 18903.0653 | 2.4403 | 434 | 11.7458 | 7210.0891 | 871.391 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1882 | 30 | 0.021141 | 42571104 | MOLINO 1104 | MOLINO 1104380 | 4061.4593 | 0.63424 | 839 | 2.5237 | 7212.6128 | 870.7567 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2263 | 12 | 0.021126 | 42141102 | CLEAR LAKE 1102 | CLEAR LAKE 1102circuit_breaker | 1141.6054 | 0.25352 | 1093 | 0.70936 | 7213.3222 | 870.5032 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4973 | 2 | 0.021086 | 43292102 | PUEBLO 2102 | PUEBLO 21021326 | 326.1269 | 0.042172 | 1595 | 0.20265 | 7213.5248 | 870.4611 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4554 | 47 | 0.021063 | 42871101 | UPPER LAKE 1101 | UPPER LAKE 1101452 | 4787.2263 | 0.98998 | 698 | 2.9746 | 7216.4995 | 869.4711 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3789 | 75 | 0.020998 | 43182103 | BELLEVUE 2103 | BELLEVUE 2103478 | 13352.3887 | 1.5749 | 562 | 8.2968 | 7224.7962 | 867.8962 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6981 | 13 | 0.020846 | 162991102 | CORRAL 1102 | CORRAL 110213498 | 1585.9579 | 0.271 | 1075 | 0.98547 | 7225.7817 | 867.6252 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7725 | 104 | 0.02073 | 152201102 | PIKE CITY 1102 | PIKE CITY 1102circuit_breaker | 15132.7411 | 2.1559 | 474 | 9.403 | 7235.1848 | 865.4693 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3233 | 5 | 0.020676 | 42561102 | FULTON 1102 | FULTON 1102circuit_breaker | 646.4219 | 0.10338 | 1344 | 0.40167 | 7235.5864 | 865.3659 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9385 | 38 | 0.020657 | 42991105 | LAS GALLINAS A 1105 | LAS GALLINAS A 1105532 | 7030.3171 | 0.78498 | 764 | 4.3684 | 7239.9549 | 864.5809 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8799 | 60 | 0.020479 | 43071102 | DUNBAR 1102 | DUNBAR 1102694641 | 6527.852 | 1.2287 | 621 | 4.0562 | 7244.0111 | 863.3522 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 997 | 31 | 0.020396 | 162991103 | CORRAL 1103 | CORRAL 1103circuit_breaker | 4196.3293 | 0.63226 | 841 | 2.6075 | 7246.6186 | 862.7199 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7324 | 15 | 0.020366 | 43432102 | SILVERADO 2102 | SILVERADO 2102808 | 1683.2795 | 0.30549 | 1028 | 1.0459 | 7247.6645 | 862.4145 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1385 | 18 | 0.020256 | 42721107 | SONOMA 1107 | SONOMA 1107126 | 6523.4267 | 0.36461 | 979 | 4.0535 | 7251.718 | 862.0498 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 9096 | 101 | 0.020247 | 254432104 | COARSEGOLD 2104 | COARSEGOLD 21046210 | 17177.2503 | 2.045 | 490 | 10.6734 | 7262.3914 | 860.0049 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3520 | 7 | 0.020219 | 152571101 | HORSESHOE 1101 | HORSESHOE 1101circuit_breaker | 1020.0278 | 0.14153 | 1262 | 0.63382 | 7263.0252 | 859.8633 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6034 | 324 | 0.020184 | 103271101 | ANTLER 1101 | ANTLER 11011378 | 39346.0984 | 6.5397 | 215 | 24.4485 | 7287.4738 | 853.3237 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2644 | 245 | 0.020039 | 103561102 | STILLWATER 1102 | STILLWATER 11021466 | 32904.1054 | 4.9095 | 272 | 20.4457 | 7307.9194 | 848.4141 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 810 | 59 | 0.020034 | 14662104 | TASSAJARA 2104 | TASSAJARA 210419042 | 9296.9258 | 1.182 | 635 | 5.7768 | 7313.6963 | 847.2321 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3864 | 215 | 0.020016 | 43432102 | SILVERADO 2102 | SILVERADO 210234959 | 41070.2397 | 4.3034 | 300 | 25.5199 | 7339.2161 | 842.9288 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7545 | 48 | 0.02 | 103441101 | JESSUP 1101 | JESSUP 11011993 | 4413.0116 | 0.95999 | 708 | 2.7421 | 7341.9582 | 841.9688 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 9434 | 2 | 0.019873 | 152582109 | DEL MAR 2109 | DEL MAR 210975802 | 547.5648 | 0.039747 | 1606 | 0.34024 | 7342.2985 | 841.929 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5926 | 368 | 0.019859 | 103401101 | GIRVAN 1101 | GIRVAN 11011330 | 49037.4544 | 7.308 | 195 | 30.4705 | 7372.7689 | 834.621 | 30.511 | 7.308 | 1 | #N/A | 834.621 | #N/A
North Coast | 2330 | 218 | 0.01978 | 42891102 | GEYSERVILLE 1102 | GEYSERVILLE 1102484 | 50631.555 | 4.312 | 299 | 31.461 | 7404.2299 | 830.309 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1205 | 80 | 0.019775 | 183052113 | TEMPLETON 2113 | TEMPLETON 2113A08 | 13880.8278 | 1.582 | 558 | 8.6251 | 7412.855 | 828.727 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6042 | 77 | 0.019755 | 163541101 | OLETA 1101 | OLETA 11014768 | 18073.0157 | 1.5211 | 570 | 11.23 | 7424.0851 | 827.2059 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5246 | 12 | 0.019672 | 103331101 | CORNING 1101 | CORNING 110187304 | 3402.7975 | 0.23607 | 1114 | 2.1144 | 7426.1995 | 826.9698 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1717 | 32 | 0.019633 | 183052111 | TEMPLETON 2111 | TEMPLETON 2111circuit_breaker | 2988.8542 | 0.62824 | 842 | 1.8572 | 7428.0567 | 826.3416 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 865 | 108 | 0.019603 | 83242105 | MORGAN HILL 2105 | MORGAN HILL 2105XR152 | 11909.7787 | 2.1171 | 479 | 7.4004 | 7435.4571 | 824.2244 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4905 | 114 | 0.019538 | 42681102 | LAYTONVILLE 1102 | LAYTONVILLE 1102circuit_breaker | 16837.2871 | 2.2274 | 461 | 10.4622 | 7445.9193 | 821.997 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1351 | 173 | 0.019513 | 153612104 | CLARKSVILLE 2104 | CLARKSVILLE 210419772 | 28983.153 | 3.3758 | 362 | 18.0093 | 7463.9286 | 818.6212 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5183 | 266 | 0.019499 | 192401101 | HOOPA 1101 | HOOPA 11013174 | 28229.9925 | 5.1867 | 258 | 17.5413 | 7481.4699 | 813.4346 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2710 | 324 | 0.019401 | 43411101 | CALPELLA 1101 | CALPELLA 11011204 | 47939.0001 | 6.2858 | 227 | 29.7879 | 7511.2578 | 807.1488 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 383 | 152 | 0.019343 | 13751102 | VASCO 1102 | VASCO 1102MR176 | 62221.1335 | 2.9401 | 393 | 38.6624 | 7549.9202 | 804.2087 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1870 | 9 | 0.019297 | 42721105 | SONOMA 1105 | SONOMA 1105404 | 18092.5178 | 0.17367 | 1201 | 11.2422 | 7561.1623 | 804.035 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4539 | 219 | 0.019256 | 192411101 | LOW GAP 1101 | LOW GAP 110137498 | 26210.4026 | 4.217 | 304 | 16.2864 | 7577.4487 | 799.818 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6270 | 6 | 0.019216 | 42301101 | TULUCAY 1101 | TULUCAY 1101628 | 3826.9754 | 0.1153 | 1307 | 2.378 | 7579.8267 | 799.7027 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1910 | 15 | 0.019154 | 43432102 | SILVERADO 2102 | SILVERADO 210298998 | 4139.5096 | 0.28731 | 1054 | 2.5722 | 7582.3989 | 799.4154 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1207 | 333 | 0.019118 | 102541102 | VOLTA 1102 | VOLTA 110237350 | 39083.1019 | 6.3663 | 225 | 24.2851 | 7606.684 | 793.0491 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2295 | 240 | 0.019027 | 163341101 | CLAY 1101 | CLAY 110113442 | 40782.5793 | 4.5666 | 281 | 25.3411 | 7632.0251 | 788.4825 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7629 | 35 | 0.018955 | 152921101 | BROWNS VALLEY 1101 | BROWNS VALLEY 110136622 | 6467.9583 | 0.66343 | 827 | 4.019 | 7636.0441 | 787.8191 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2436 | 367 | 0.018875 | 103321101 | CEDAR CREEK 1101 | CEDAR CREEK 11011656 | 51035.8707 | 6.9273 | 204 | 31.7122 | 7667.7563 | 780.8918 | 31.3055 | 6.9273 | 1 | #N/A | #N/A | 780.8918
North Coast | 2491 | 236 | 0.01886 | 42561102 | FULTON 1102 | FULTON 1102287172 | 29351.4047 | 4.4509 | 285 | 18.2381 | 7685.9944 | 776.4409 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 77 | 60 | 0.018856 | 152811105 | WHEATLAND 1105 | WHEATLAND 110591170 | 15619.5143 | 1.1314 | 653 | 9.7055 | 7695.6999 | 775.3095 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6074 | 98 | 0.01877 | 42851121 | FORT ROSS 1121 | FORT ROSS 112170288 | 18893.0241 | 1.8394 | 522 | 11.7396 | 7707.4395 | 773.4701 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 528 | 242 | 0.018718 | 192321121 | FORT SEWARD 1121 | FORT SEWARD 11211602 | 27815.4127 | 4.5297 | 283 | 17.2837 | 7724.7232 | 768.9404 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8265 | 25 | 0.018684 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101614 | 2239.5087 | 0.46709 | 921 | 1.3916 | 7726.1148 | 768.4733 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6166 | 49 | 0.018652 | 14662113 | TASSAJARA 2113 | TASSAJARA 2113MR276 | 6095.1274 | 0.91393 | 724 | 3.7873 | 7729.9021 | 767.5594 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6039 | 110 | 0.018609 | 102911107 | WYANDOTTE 1107 | WYANDOTTE 110796390 | 13317.923 | 2.047 | 489 | 8.2754 | 7738.1775 | 765.5124 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3929 | 35 | 0.018568 | 192291121 | CARLOTTA 1121 | CARLOTTA 1121circuit_breaker | 3350.89 | 0.64987 | 833 | 2.0821 | 7740.2596 | 764.8625 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8874 | 1 | 0.018527 | 182391103 | OILFIELDS 1103 | OILFIELDS 1103N46 | 9360.626 | 0.018527 | 1781 | 5.8164 | 7746.076 | 764.844 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8716 | 3 | 0.01839 | 253642101 | POSO MOUNTAIN 2101 | POSO MOUNTAIN 21013990 | 6347.4219 | 0.055169 | 1513 | 3.9441 | 7750.0201 | 764.7888 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2401 | 14 | 0.018353 | 102541101 | VOLTA 1101 | VOLTA 110180454 | 50010.0284 | 0.25694 | 1088 | 31.0748 | 7781.0949 | 764.5319 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3229 | 47 | 0.018272 | 43191102 | REDBUD 1102 | REDBUD 1102510 | 5477.4083 | 0.8588 | 741 | 3.4035 | 7784.4984 | 763.6731 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6987 | 194 | 0.01826 | 42871101 | UPPER LAKE 1101 | UPPER LAKE 11011276 | 20671.4818 | 3.5424 | 343 | 12.8447 | 7797.3431 | 760.1307 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5777 | 4 | 0.018258 | 42891101 | GEYSERVILLE 1101 | GEYSERVILLE 1101482 | 352.7494 | 0.073031 | 1439 | 0.21919 | 7797.5623 | 760.0577 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3084 | 134 | 0.018254 | 42251101 | HOPLAND 1101 | HOPLAND 1101768 | 26862.8023 | 2.4461 | 433 | 16.6918 | 7814.254 | 757.6116 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5197 | 34 | 0.018209 | 192321121 | FORT SEWARD 1121 | FORT SEWARD 11211663 | 3125.6698 | 0.6191 | 845 | 1.9422 | 7816.1962 | 756.9925 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4569 | 139 | 0.018142 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031504 | 16411.1206 | 2.5217 | 424 | 10.1974 | 7826.3936 | 754.4708 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7733 | 152 | 0.018089 | 103191101 | BANGOR 1101 | BANGOR 1101circuit_breaker | 28650.9927 | 2.7495 | 404 | 17.8029 | 7844.1965 | 751.7213 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7722 | 135 | 0.018065 | 43051101 | MONTICELLO 1101 | MONTICELLO 1101718 | 42515.7179 | 2.4388 | 435 | 26.418 | 7870.6146 | 749.2825 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3694 | 111 | 0.018011 | 252192101 | BEAR VALLEY 2101 | BEAR VALLEY 21014500 | 34089.7521 | 1.9992 | 502 | 21.1824 | 7891.7969 | 747.2833 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 21 | 28 | 0.018004 | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 1113154 | 2751.1631 | 0.50412 | 896 | 1.7095 | 7893.5064 | 746.7791 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8766 | 29 | 0.017974 | 14241101 | SUNOL 1101 | SUNOL 11018721 | 4212.4471 | 0.52124 | 890 | 2.6175 | 7896.1239 | 746.2579 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4993 | 37 | 0.017971 | 43432104 | SILVERADO 2104 | SILVERADO 2104722 | 11871.204 | 0.66491 | 825 | 7.3764 | 7903.5003 | 745.593 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4162 | 226 | 0.017946 | 153132105 | NARROWS 2105 | NARROWS 2105circuit_breaker | 57069.9064 | 4.0559 | 312 | 35.4616 | 7938.9619 | 741.5371 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7235 | 11 | 0.017937 | 42821102 | CLOVERDALE 1102 | CLOVERDALE 1102262 | 947.9156 | 0.19731 | 1161 | 0.58901 | 7939.5509 | 741.3398 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2260 | 369 | 0.017905 | 252531103 | SAN JOAQUIN #3 1103 | SAN JOAQUIN #3 1103circuit_breaker | 45356.6535 | 6.6069 | 213 | 28.1833 | 7967.7342 | 734.7329 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5408 | 92 | 0.017835 | 182721101 | SANTA YNEZ 1101 | SANTA YNEZ 1101Y52 | 36116.1135 | 1.6408 | 547 | 22.4415 | 7990.1758 | 733.092 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1069 | 597 | 0.017739 | 152031103 | GRASS VALLEY 1103 | GRASS VALLEY 11032180 | 70305.7957 | 10.5904 | 144 | 43.686 | 8033.8617 | 722.5016 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4383 | 1 | 0.017735 | 14652106 | TIDEWATER 2106 | TIDEWATER 210657926 | 0 | 0.017735 | 1792 | 0 | 8033.8617 | 722.4838 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1080 | 84 | 0.017678 | 43361102 | HIGHLANDS 1102 | HIGHLANDS 110275140 | 13187.2724 | 1.485 | 576 | 8.1942 | 8042.0559 | 720.9989 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1818 | 427 | 0.017676 | 43311102 | KONOCTI 1102 | KONOCTI 1102circuit_breaker | 52446.7628 | 7.5478 | 190 | 32.5889 | 8074.6448 | 713.4511 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7857 | 100 | 0.017554 | 42021112 | NAPA 1112 | NAPA 11121723 | 15407.0792 | 1.7554 | 531 | 9.5735 | 8084.2183 | 711.6957 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7027 | 18 | 0.017547 | 252941107 | TIVY VALLEY 1107 | TIVY VALLEY 11077380 | 18290.2186 | 0.31585 | 1015 | 11.365 | 8095.5833 | 711.3798 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9383 | 3 | 0.017525 | 48011146 | CALPINE 1146 | CALPINE 1146400 | 5057.3021 | 0.052574 | 1529 | 3.1425 | 8098.7258 | 711.3273 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 813 | 82 | 0.017525 | 182541103 | ATASCADERO 1103 | ATASCADERO 1103A18 | 12533.7225 | 1.437 | 585 | 7.7881 | 8106.5139 | 709.8903 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7078 | 290 | 0.017438 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 210151584 | 35042.6767 | 5.0571 | 262 | 21.7745 | 8128.2884 | 704.8332 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 710 | 67 | 0.017409 | 42811112 | MONTE RIO 1112 | MONTE RIO 11125040 | 6507.7866 | 1.1664 | 641 | 4.0437 | 8132.3321 | 703.6668 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 552 | 38 | 0.017405 | 43091103 | GREENBRAE 1103 | GREENBRAE 11031260 | 4080.5899 | 0.66139 | 829 | 2.5356 | 8134.8677 | 703.0054 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9239 | 99 | 0.017383 | 192461101 | BRIDGEVILLE 1101 | BRIDGEVILLE 1101circuit_breaker | 13703.3241 | 1.721 | 536 | 8.5148 | 8143.3826 | 701.2844 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4192 | 6 | 0.017356 | 103531103 | RAWSON 1103 | RAWSON 110385334 | 3724.4141 | 0.10414 | 1341 | 2.3142 | 8145.6968 | 701.1803 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 9095 | 56 | 0.017334 | 152691109 | HIGGINS 1109 | HIGGINS 11097863 | 6799.2947 | 0.97068 | 705 | 4.2249 | 8149.9217 | 700.2096 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4587 | 206 | 0.017267 | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210985766 | 29469.33 | 3.557 | 341 | 18.3114 | 8168.2331 | 696.6526 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8471 | 197 | 0.017151 | 42681102 | LAYTONVILLE 1102 | LAYTONVILLE 11022502 | 27326.5363 | 3.3788 | 359 | 16.9799 | 8185.213 | 693.2738 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2077 | 159 | 0.017082 | 192221102 | GARBERVILLE 1102 | GARBERVILLE 1102circuit_breaker | 17301.6263 | 2.7161 | 407 | 10.7507 | 8195.9637 | 690.5577 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4267 | 139 | 0.017011 | 192311141 | FRUITLAND 1141 | FRUITLAND 114195324 | 14576.7142 | 2.3645 | 444 | 9.0575 | 8205.0213 | 688.1932 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7776 | 21 | 0.016994 | 14502110 | VINEYARD 2110 | VINEYARD 2110circuit_breaker | 8669.9033 | 0.35687 | 985 | 5.3872 | 8210.4085 | 687.8363 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 214 | 4 | 0.016941 | 63172101 | MADISON 2101 | MADISON 21017702 | 1421.2134 | 0.067763 | 1461 | 0.8831 | 8211.2916 | 687.7686 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6989 | 201 | 0.016839 | 102911107 | WYANDOTTE 1107 | WYANDOTTE 110738438 | 27120.5563 | 3.3846 | 358 | 16.8519 | 8228.1435 | 684.384 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8331 | 56 | 0.016816 | 43021101 | WOODACRE 1101 | WOODACRE 110191900 | 10288.938 | 0.94168 | 717 | 6.3932 | 8234.5368 | 683.4423 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7384 | 13 | 0.016757 | 192311142 | FRUITLAND 1142 | FRUITLAND 11422006 | 12367.8837 | 0.21784 | 1141 | 7.685 | 8242.2218 | 683.2245 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5540 | 207 | 0.016752 | 24251101 | WOODSIDE 1101 | WOODSIDE 11018974 | 21603.9606 | 3.4676 | 353 | 13.4241 | 8255.6459 | 679.7569 | 11.2475 | 2.6906 | 1 | #N/A | 679.7569 | #N/A
North Valley | 8289 | 130 | 0.016688 | 103271101 | ANTLER 1101 | ANTLER 11011376 | 14477.8455 | 2.1695 | 469 | 8.9961 | 8264.642 | 677.5874 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3099 | 23 | 0.016678 | 163011103 | MARTELL 1103 | MARTELL 110368192 | 3980.4628 | 0.3836 | 967 | 2.4733 | 8267.1153 | 677.2038 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3794 | 212 | 0.016625 | 103221101 | KANAKA 1101 | KANAKA 110165606 | 20432.7894 | 3.5245 | 345 | 12.6963 | 8279.8117 | 673.6793 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1108 | 4 | 0.016548 | 42631109 | PETALUMA C 1109 | PETALUMA C 1109128 | 54365.1404 | 0.066191 | 1471 | 33.7809 | 8313.5926 | 673.6131 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 704 | 7 | 0.016529 | 43371102 | LAKEVILLE 1102 | LAKEVILLE 1102280 | 3287.3324 | 0.1157 | 1304 | 2.0427 | 8315.6353 | 673.4974 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6602 | 58 | 0.016482 | 103441101 | JESSUP 1101 | JESSUP 11019752 | 6269.3077 | 0.95594 | 711 | 3.8956 | 8319.5308 | 672.5415 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 456 | 83 | 0.016471 | 43021101 | WOODACRE 1101 | WOODACRE 110196844 | 9464.5637 | 1.3671 | 599 | 5.881 | 8325.4118 | 671.1744 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6015 | 8 | 0.016402 | 43091103 | GREENBRAE 1103 | GREENBRAE 110356884 | 883.8137 | 0.13122 | 1277 | 0.54918 | 8325.961 | 671.0432 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 271 | 50 | 0.0164 | 42891102 | GEYSERVILLE 1102 | GEYSERVILLE 1102350 | 6355.4918 | 0.81998 | 752 | 3.9491 | 8329.9101 | 670.2232 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 703 | 120 | 0.016377 | 42031124 | ALTO 1124 | ALTO 1124430 | 11716.5372 | 1.9653 | 507 | 7.2803 | 8337.1904 | 668.2579 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 8932 | 3 | 0.016372 | 152921101 | BROWNS VALLEY 1101 | BROWNS VALLEY 1101circuit_breaker | 1061.2697 | 0.049117 | 1545 | 0.65944 | 8337.8499 | 668.2088 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1536 | 45 | 0.016348 | 42681102 | LAYTONVILLE 1102 | LAYTONVILLE 110264908 | 5371.196 | 0.73565 | 787 | 3.3375 | 8341.1874 | 667.4732 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1830 | 307 | 0.016209 | 152261106 | DIAMOND SPRINGS 1106 | DIAMOND SPRINGS 110610587 | 35174.8047 | 4.9763 | 266 | 21.8566 | 8363.044 | 662.4969 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5982 | 7 | 0.016156 | 253642101 | POSO MOUNTAIN 2101 | POSO MOUNTAIN 21012181 | 26885.9284 | 0.11309 | 1313 | 16.7061 | 8379.7501 | 662.3838 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6027 | 26 | 0.016111 | 42661103 | WILLITS 1103 | WILLITS 1103964 | 4036.5135 | 0.41889 | 946 | 2.5082 | 8382.2583 | 661.9649 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4636 | 389 | 0.01611 | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210961892 | 48517.9876 | 6.2666 | 231 | 30.1477 | 8412.406 | 655.6983 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1291 | 179 | 0.015982 | 42571102 | MOLINO 1102 | MOLINO 1102178 | 19242.2295 | 2.8607 | 399 | 11.9566 | 8424.3625 | 652.8376 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8325 | 16 | 0.015923 | 192221102 | GARBERVILLE 1102 | GARBERVILLE 11028189 | 1628.0781 | 0.25477 | 1090 | 1.0116 | 8425.3742 | 652.5828 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8756 | 5 | 0.015919 | 43191102 | REDBUD 1102 | REDBUD 110244119 | 603.3084 | 0.079595 | 1419 | 0.37488 | 8425.7491 | 652.5032 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 304 | 250 | 0.015884 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21011350 | 34651.2737 | 3.9709 | 315 | 21.5313 | 8447.2804 | 648.5323 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5431 | 175 | 0.015812 | 43291104 | PUEBLO 1104 | PUEBLO 11041304 | 30920.9317 | 2.7671 | 403 | 19.2134 | 8466.4937 | 645.7652 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7091 | 137 | 0.015811 | 192221101 | GARBERVILLE 1101 | GARBERVILLE 11011770 | 13857.9245 | 2.1661 | 471 | 8.6109 | 8475.1046 | 643.599 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3635 | 60 | 0.015804 | 43432102 | SILVERADO 2102 | SILVERADO 2102636 | 6273.2424 | 0.94825 | 714 | 3.898 | 8479.0026 | 642.6508 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4875 | 64 | 0.015786 | 42571102 | MOLINO 1102 | MOLINO 110241392 | 6064.4075 | 1.0103 | 688 | 3.7682 | 8482.7709 | 641.6404 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1326 | 118 | 0.015762 | 42561102 | FULTON 1102 | FULTON 11024522 | 13642.0128 | 1.86 | 519 | 8.4768 | 8491.2476 | 639.7805 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6036 | 39 | 0.015735 | 43071101 | DUNBAR 1101 | DUNBAR 1101416 | 4032.4336 | 0.61367 | 849 | 2.5056 | 8493.7533 | 639.1668 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8696 | 2 | 0.015717 | 43071103 | DUNBAR 1103 | DUNBAR 11033135 | 100.9792 | 0.031434 | 1670 | 0.062746 | 8493.816 | 639.1354 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6718 | 77 | 0.015714 | 102971111 | SYCAMORE CREEK 1111 | SYCAMORE CREEK 1111circuit_breaker | 12547.7716 | 1.21 | 629 | 7.7968 | 8501.6128 | 637.9254 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5071 | 4 | 0.015708 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 110313018 | 201.9138 | 0.062831 | 1483 | 0.12546 | 8501.7383 | 637.8625 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1907 | 104 | 0.015638 | 42771113 | UKIAH 1113 | UKIAH 1113circuit_breaker | 12034.1255 | 1.6263 | 549 | 7.4777 | 8509.216 | 636.2362 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3958 | 12 | 0.015572 | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 110113424 | 2488.4546 | 0.18686 | 1181 | 1.5463 | 8510.7622 | 636.0493 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2011 | 52 | 0.015571 | 192311141 | FRUITLAND 1141 | FRUITLAND 1141circuit_breaker | 4594.941 | 0.80968 | 756 | 2.8552 | 8513.6174 | 635.2397 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7058 | 70 | 0.015561 | 103221101 | KANAKA 1101 | KANAKA 11011044 | 9870.7715 | 1.0893 | 665 | 6.1334 | 8519.7508 | 634.1504 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7373 | 100 | 0.015514 | 183041101 | BUELLTON 1101 | BUELLTON 1101Y26 | 23209.1215 | 1.5514 | 567 | 14.4215 | 8534.1723 | 632.599 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 623 | 132 | 0.015421 | 152481106 | BRUNSWICK 1106 | BRUNSWICK 11062790 | 15218.0635 | 2.0356 | 494 | 9.4561 | 8543.6283 | 630.5634 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5797 | 103 | 0.015358 | 103551101 | RISING RIVER 1101 | RISING RIVER 11011530 | 16264.4687 | 1.5819 | 559 | 10.1063 | 8553.7346 | 628.9816 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1325 | 66 | 0.015296 | 152561107 | PENRYN 1107 | PENRYN 1107circuit_breaker | 6429.3235 | 1.0096 | 690 | 3.995 | 8557.7296 | 627.972 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1852 | 205 | 0.015243 | 103521102 | OREGON TRAIL 1102 | OREGON TRAIL 110249144 | 28540.0535 | 3.1249 | 384 | 17.734 | 8575.4636 | 624.8471 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6371 | 133 | 0.015206 | 42871101 | UPPER LAKE 1101 | UPPER LAKE 110175370 | 17069.5104 | 2.0223 | 499 | 10.6065 | 8586.0701 | 622.8248 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8459 | 36 | 0.015159 | 254452101 | MARIPOSA 2101 | MARIPOSA 2101circuit_breaker | 4029.4321 | 0.54574 | 880 | 2.5038 | 8588.5738 | 622.279 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6719 | 41 | 0.015058 | 43021101 | WOODACRE 1101 | WOODACRE 1101circuit_breaker | 4013.0588 | 0.61739 | 847 | 2.4936 | 8591.0674 | 621.6616 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 244 | 25 | 0.014999 | 43321103 | RINCON 1103 | RINCON 1103circuit_breaker | 3908.5393 | 0.37497 | 972 | 2.4287 | 8593.4961 | 621.2867 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3078 | 46 | 0.014965 | 42661104 | WILLITS 1104 | WILLITS 11044650 | 5679.3968 | 0.6884 | 814 | 3.529 | 8597.0251 | 620.5983 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7126 | 71 | 0.014918 | 163011102 | MARTELL 1102 | MARTELL 1102circuit_breaker | 7916.9254 | 1.0592 | 675 | 4.9193 | 8601.9444 | 619.5391 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1151 | 87 | 0.014912 | 162991103 | CORRAL 1103 | CORRAL 110336680 | 13725.8331 | 1.2973 | 612 | 8.5288 | 8610.4733 | 618.2417 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4103 | 239 | 0.014824 | 103201102 | CHALLENGE 1102 | CHALLENGE 1102circuit_breaker | 24978.1439 | 3.543 | 342 | 15.5207 | 8625.994 | 614.6988 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4609 | 24 | 0.014822 | 192311141 | FRUITLAND 1141 | FRUITLAND 11418860 | 3211.911 | 0.35573 | 986 | 1.9958 | 8627.9898 | 614.343 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2629 | 1 | 0.028392 | 43292102 | PUEBLO 2102 | PUEBLO 2102792 | 30375.5803 | 0.028392 | 348 | 18.8745 | 8646.8643 | 614.3147 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 2629 | 235 | 0.014761 | 43292102 | PUEBLO 2102 | PUEBLO 2102792 | 30375.5803 | 3.4689 | 348 | 18.8745 | 8665.7388 | 610.8457 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 5934 | 94 | 0.014763 | 42891101 | GEYSERVILLE 1101 | GEYSERVILLE 110135492 | 14162.9366 | 1.3877 | 595 | 8.8004 | 8674.5392 | 609.458 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6533 | 131 | 0.014736 | 163541102 | OLETA 1102 | OLETA 1102circuit_breaker | 21808.3893 | 1.9304 | 508 | 13.5511 | 8688.0903 | 607.5276 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1099 | 161 | 0.014734 | 252811102 | MERCED FALLS 1102 | MERCED FALLS 110287352 | 42562.7821 | 2.3721 | 443 | 26.4473 | 8714.5376 | 605.1555 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4799 | 53 | 0.01473 | 42661104 | WILLITS 1104 | WILLITS 110434006 | 6444.3113 | 0.78067 | 766 | 4.0043 | 8718.5419 | 604.3748 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3018 | 256 | 0.014683 | 152201101 | PIKE CITY 1101 | PIKE CITY 1101circuit_breaker | 31954.3985 | 3.759 | 325 | 19.8555 | 8738.3974 | 600.6158 | 19.3667 | 3.759 | 1 | #N/A | #N/A | 600.6158
Central Valley | 7448 | 113 | 0.014628 | 254421101 | OAKHURST 1101 | OAKHURST 11016220 | 32301.3797 | 1.6529 | 545 | 20.0711 | 8758.4686 | 598.9629 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 285 | 20 | 0.014622 | 83242110 | MORGAN HILL 2110 | MORGAN HILL 2110XR326 | 3216.8739 | 0.29243 | 1049 | 1.9989 | 8760.4674 | 598.6704 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2709 | 5 | 0.014578 | 42561107 | FULTON 1107 | FULTON 1107circuit_breaker | 487.3016 | 0.072892 | 1440 | 0.3028 | 8760.7702 | 598.5976 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4254 | 78 | 0.014552 | 43182103 | BELLEVUE 2103 | BELLEVUE 2103552 | 11666.895 | 1.1351 | 650 | 7.2495 | 8768.0197 | 597.4625 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4087 | 233 | 0.0145 | 42571101 | MOLINO 1101 | MOLINO 1101322 | 24774.6668 | 3.3785 | 360 | 15.3943 | 8783.414 | 594.084 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2580 | 255 | 0.014458 | 254151101 | AUBERRY 1101 | AUBERRY 1101R2579 | 55665.4542 | 3.6868 | 329 | 34.5889 | 8818.0029 | 590.3972 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 801 | 182 | 0.014383 | 42821102 | CLOVERDALE 1102 | CLOVERDALE 1102570 | 26431.4448 | 2.6177 | 416 | 16.4237 | 8834.4266 | 587.7795 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5748 | 90 | 0.01437 | 153741101 | DOBBINS 1101 | DOBBINS 110169722 | 10673.4289 | 1.2933 | 613 | 6.6322 | 8841.0588 | 586.4862 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1027 | 217 | 0.014315 | 192221102 | GARBERVILLE 1102 | GARBERVILLE 11028652 | 21012.1269 | 3.1063 | 386 | 13.0563 | 8854.1151 | 583.38 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 453 | 97 | 0.014294 | 43311102 | KONOCTI 1102 | KONOCTI 1102596 | 15791.9595 | 1.3865 | 596 | 9.8127 | 8863.9278 | 581.9935 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3769 | 17 | 0.014266 | 42771111 | UKIAH 1111 | UKIAH 111129452 | 5841.787 | 0.24252 | 1103 | 3.6299 | 8867.5577 | 581.751 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2256 | 34 | 0.014206 | 14502107 | VINEYARD 2107 | VINEYARD 2107circuit_breaker | 4200.246 | 0.48301 | 913 | 2.6099 | 8870.1676 | 581.268 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 640 | 144 | 0.014295 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 17298.8853 | 2.0585 | 485 | 10.749 | 8880.9166 | 579.2095 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 640 | 1 | 0.00013369 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 17298.8853 | 0.00013369 | 485 | 10.749 | 8891.6656 | 579.2094 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Valley | 3420 | 8 | 0.014161 | 103441103 | JESSUP 1103 | JESSUP 1103circuit_breaker | 998.4804 | 0.11329 | 1312 | 0.62043 | 8892.2861 | 579.0961 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5847 | 78 | 0.014087 | 42721102 | SONOMA 1102 | SONOMA 1102118 | 9282.9853 | 1.0988 | 662 | 5.7682 | 8898.0542 | 577.9973 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6887 | 158 | 0.014003 | 42091101 | MIRABEL 1101 | MIRABEL 1101116 | 16655.9357 | 2.2124 | 465 | 10.3495 | 8908.4038 | 575.7849 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 492 | 464 | 0.013969 | 153741101 | DOBBINS 1101 | DOBBINS 11011264 | 55887.5598 | 6.4814 | 220 | 34.7269 | 8943.1307 | 569.3034 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 514 | 184 | 0.013884 | 254061103 | DUNLAP 1103 | DUNLAP 11037220 | 39952.2483 | 2.5547 | 419 | 24.8252 | 8967.9558 | 566.7488 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7449 | 178 | 0.013877 | 252192101 | BEAR VALLEY 2101 | BEAR VALLEY 21014160 | 36553.6326 | 2.4701 | 428 | 22.7134 | 8990.6692 | 564.2787 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6446 | 15 | 0.013873 | 182631107 | SAN LUIS OBISPO 1107 | SAN LUIS OBISPO 110788962 | 3512.4168 | 0.20809 | 1151 | 2.1825 | 8992.8517 | 564.0706 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3876 | 113 | 0.013866 | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 111324550 | 12900.9804 | 1.5669 | 564 | 8.0163 | 9000.868 | 562.5038 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 730 | 240 | 0.013837 | 83242105 | MORGAN HILL 2105 | MORGAN HILL 2105XR176 | 32979.6694 | 3.321 | 365 | 20.4926 | 9021.3606 | 559.1828 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6642 | 11 | 0.015895 | 42021112 | NAPA 1112 | NAPA 11121302 | 14540.3445 | 0.17484 | 617 | 9.0349 | 9030.3956 | 559.008 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 6642 | 82 | 0.013473 | 42021112 | NAPA 1112 | NAPA 11121302 | 14540.3445 | 1.1048 | 617 | 9.0349 | 9039.4305 | 557.9032 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 6670 | 26 | 0.013758 | 42821102 | CLOVERDALE 1102 | CLOVERDALE 1102670 | 4063.4864 | 0.3577 | 984 | 2.5249 | 9041.9554 | 557.5455 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 258 | 54 | 0.013726 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 11022584 | 13236.8465 | 0.74119 | 785 | 8.225 | 9050.1804 | 556.8043 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6425 | 255 | 0.013681 | 103401102 | GIRVAN 1102 | GIRVAN 11021028 | 28149.0621 | 3.4886 | 350 | 17.491 | 9067.6714 | 553.3157 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2755 | 42 | 0.01366 | 152561107 | PENRYN 1107 | PENRYN 11072410 | 4627.9566 | 0.57371 | 866 | 2.8757 | 9070.5471 | 552.742 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4613 | 68 | 0.013631 | 42661103 | WILLITS 1103 | WILLITS 110391948 | 11264.7541 | 0.9269 | 722 | 6.9996 | 9077.5467 | 551.8151 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5010 | 57 | 0.013606 | 43432102 | SILVERADO 2102 | SILVERADO 21023010 | 5441.3026 | 0.77557 | 771 | 3.3811 | 9080.9278 | 551.0395 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8070 | 57 | 0.0136 | 103541104 | RED BLUFF 1104 | RED BLUFF 11041302 | 21098.7836 | 0.77517 | 772 | 13.1102 | 9094.038 | 550.2643 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3093 | 8 | 0.013593 | 152331108 | EAST MARYSVILLE 1108 | EAST MARYSVILLE 11081706 | 891.2903 | 0.10874 | 1330 | 0.55382 | 9094.5918 | 550.1556 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4590 | 81 | 0.013585 | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 1113352 | 9077.2683 | 1.1004 | 660 | 5.6404 | 9100.2321 | 549.0552 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3972 | 26 | 0.013538 | 12022213 | CLAYTON 2213 | CLAYTON 2213circuit_breaker | 6236.8648 | 0.352 | 987 | 3.8754 | 9104.1075 | 548.7032 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6156 | 337 | 0.013527 | 42771114 | UKIAH 1114 | UKIAH 1114408 | 59693.1649 | 4.5587 | 282 | 37.0916 | 9141.1991 | 544.1445 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5971 | 158 | 0.013514 | 192221101 | GARBERVILLE 1101 | GARBERVILLE 110135706 | 16258.1269 | 2.1352 | 476 | 10.1023 | 9151.3015 | 542.0093 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6733 | 27 | 0.013491 | 42711101 | CALISTOGA 1101 | CALISTOGA 1101circuit_breaker | 3212.9518 | 0.36424 | 980 | 1.9964 | 9153.2979 | 541.6451 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 375 | 508 | 0.013435 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21011102 | 71641.3725 | 6.825 | 208 | 44.5159 | 9197.8138 | 534.82 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2076 | 13 | 0.013418 | 102911109 | WYANDOTTE 1109 | WYANDOTTE 11091040 | 1355.0481 | 0.17443 | 1199 | 0.84199 | 9198.6558 | 534.6456 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2918 | 152 | 0.013396 | 183052111 | TEMPLETON 2111 | TEMPLETON 2111R86 | 17358.9842 | 2.0361 | 492 | 10.7864 | 9209.4421 | 532.6095 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6699 | 116 | 0.01325 | 152561105 | PENRYN 1105 | PENRYN 110551676 | 11966.6651 | 1.537 | 569 | 7.4357 | 9216.8779 | 531.0724 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4588 | 50 | 0.013126 | 43191101 | REDBUD 1101 | REDBUD 1101454 | 8939.3598 | 0.65628 | 830 | 5.5547 | 9222.4325 | 530.4161 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5027 | 221 | 0.013025 | 152241101 | HALSEY 1101 | HALSEY 11012414 | 23778.9553 | 2.8785 | 397 | 14.7756 | 9237.2081 | 527.5376 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1273 | 203 | 0.013023 | 103351101 | DESCHUTES 1101 | DESCHUTES 11011652 | 32556.3926 | 2.6436 | 414 | 20.2296 | 9257.4377 | 524.894 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4337 | 19 | 0.012996 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 11022094 | 5527.8648 | 0.24692 | 1101 | 3.4349 | 9260.8725 | 524.6471 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5157 | 231 | 0.012993 | 192221102 | GARBERVILLE 1102 | GARBERVILLE 11022500 | 25786.904 | 3.0015 | 391 | 16.0232 | 9276.8958 | 521.6456 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7795 | 77 | 0.01283 | 192311141 | FRUITLAND 1141 | FRUITLAND 11413902 | 4505.0192 | 0.98791 | 700 | 2.7993 | 9279.6951 | 520.6577 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6403 | 126 | 0.012822 | 42681101 | LAYTONVILLE 1101 | LAYTONVILLE 11011760 | 15633.6438 | 1.6155 | 553 | 9.7143 | 9289.4094 | 519.0421 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4667 | 110 | 0.012748 | 42821102 | CLOVERDALE 1102 | CLOVERDALE 1102674 | 25986.6813 | 1.4022 | 592 | 16.1474 | 9305.5567 | 517.6399 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9027 | 39 | 0.012744 | 103611101 | WILDWOOD 1101 | WILDWOOD 110198896 | 15545.2226 | 0.49702 | 899 | 9.6594 | 9315.2161 | 517.1429 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3075 | 339 | 0.012741 | 42571102 | MOLINO 1102 | MOLINO 1102104 | 34941.2444 | 4.3192 | 297 | 21.7115 | 9336.9275 | 512.8237 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5255 | 39 | 0.012733 | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 1113406 | 3309.8931 | 0.4966 | 900 | 2.0567 | 9338.9842 | 512.3271 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6208 | 21 | 0.012733 | 43161101 | SALMON CREEK 1101 | SALMON CREEK 110137368 | 10726.7893 | 0.26739 | 1081 | 6.6653 | 9345.6495 | 512.0597 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3782 | 164 | 0.012731 | 42661103 | WILLITS 1103 | WILLITS 11032506 | 19186.052 | 2.0878 | 480 | 11.9217 | 9357.5712 | 509.9719 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3211 | 320 | 0.0127 | 182601104 | OCEANO 1104 | OCEANO 1104Q10 | 37945.3605 | 4.064 | 311 | 23.5781 | 9381.1493 | 505.9079 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1194 | 558 | 0.01265 | 153662102 | APPLE HILL 2102 | APPLE HILL 21021532 | 60833.3699 | 7.0586 | 201 | 37.8001 | 9418.9494 | 498.8492 | 36.914 | 6.9968 | 1 | #N/A | #N/A | 498.8492
Bay Area | 7715 | 72 | 0.012558 | 12022215 | CLAYTON 2215 | CLAYTON 2215W531R | 10534.5095 | 0.90415 | 727 | 6.5458 | 9425.4953 | 497.9451 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2016 | 87 | 0.012514 | 43291104 | PUEBLO 1104 | PUEBLO 11042802 | 14988.5406 | 1.0887 | 666 | 9.3134 | 9434.8087 | 496.8563 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2039 | 116 | 0.012507 | 183181101 | SAN JUSTO 1101 | SAN JUSTO 110136902 | 19755.8941 | 1.4509 | 581 | 12.2757 | 9447.0845 | 495.4055 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2362 | 136 | 0.012496 | 24251101 | WOODSIDE 1101 | WOODSIDE 11018884 | 12455.5334 | 1.6995 | 538 | 7.7395 | 9454.824 | 493.706 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6975 | 45 | 0.012432 | 182721101 | SANTA YNEZ 1101 | SANTA YNEZ 1101Y16 | 12159.0407 | 0.55943 | 869 | 7.5553 | 9462.3792 | 493.1465 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7961 | 114 | 0.012411 | 42851121 | FORT ROSS 1121 | FORT ROSS 1121circuit_breaker | 20387.5307 | 1.4149 | 587 | 12.6682 | 9475.0475 | 491.7317 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2154 | 325 | 0.012398 | 182541101 | ATASCADERO 1101 | ATASCADERO 1101A02 | 42537.755 | 4.0292 | 313 | 26.4317 | 9501.4792 | 487.7025 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2131 | 155 | 0.01236 | 43291105 | PUEBLO 1105 | PUEBLO 1105696 | 30001.1055 | 1.9158 | 510 | 18.6418 | 9520.121 | 485.7867 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 284 | 333 | 0.012317 | 103601101 | WHITMORE 1101 | WHITMORE 11011598 | 53639.2857 | 4.1017 | 309 | 33.3299 | 9553.4509 | 481.685 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6032 | 59 | 0.012311 | 42571101 | MOLINO 1101 | MOLINO 1101891 | 5053.4192 | 0.72638 | 793 | 3.14 | 9556.5909 | 480.9586 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7295 | 80 | 0.012271 | 162821702 | STANISLAUS 1702 | STANISLAUS 1702circuit_breaker | 12811.6118 | 0.98169 | 703 | 7.9608 | 9564.5517 | 479.9769 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4870 | 36 | 0.012252 | 42031124 | ALTO 1124 | ALTO 11243121 | 4421.122 | 0.44106 | 934 | 2.7472 | 9567.2989 | 479.5359 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1154 | 188 | 0.012204 | 152691104 | HIGGINS 1104 | HIGGINS 11044281 | 21369.438 | 2.2943 | 450 | 13.2783 | 9580.5772 | 477.2415 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5815 | 89 | 0.012189 | 255292108 | WOODWARD 2108 | WOODWARD 210878448 | 28435.4926 | 1.0848 | 668 | 17.669 | 9598.2462 | 476.1568 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5984 | 87 | 0.012046 | 183181101 | SAN JUSTO 1101 | SAN JUSTO 11014339 | 11461.6704 | 1.048 | 679 | 7.1219 | 9605.3682 | 475.1087 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4860 | 4 | 0.012037 | 103491102 | MC ARTHUR 1102 | MC ARTHUR 11021324 | 3069.2847 | 0.048146 | 1555 | 1.9072 | 9607.2753 | 475.0606 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3022 | 57 | 0.01198 | 42891102 | GEYSERVILLE 1102 | GEYSERVILLE 1102274 | 7596.7493 | 0.68286 | 816 | 4.7204 | 9611.9957 | 474.3777 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8685 | 5 | 0.011946 | 14351104 | FREMONT 1104 | FREMONT 1104MR339 | 1796.5075 | 0.059732 | 1494 | 1.1163 | 9613.112 | 474.318 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6757 | 36 | 0.011943 | 192311142 | FRUITLAND 1142 | FRUITLAND 11426054 | 16837.555 | 0.42997 | 940 | 10.4624 | 9623.5744 | 473.888 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3335 | 1 | 0.011924 | 253191101 | SAN BERNARD 1101 | SAN BERNARD 1101circuit_breaker | 1475.2454 | 0.011924 | 1867 | 0.91667 | 9624.4911 | 473.8761 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8908 | 111 | 0.011905 | 192221102 | GARBERVILLE 1102 | GARBERVILLE 110237054 | 13349.1892 | 1.3215 | 607 | 8.2948 | 9632.7859 | 472.5546 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3366 | 379 | 0.011856 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 36746.286 | 4.4934 | 284 | 22.8331 | 9655.6189 | 468.0612 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8910 | 4 | 0.011848 | 42271102 | COTATI 1102 | COTATI 1102circuit_breaker | 2904.3184 | 0.047392 | 1564 | 1.8047 | 9657.4236 | 468.0138 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4291 | 122 | 0.011831 | 152691107 | HIGGINS 1107 | HIGGINS 11071070 | 11964.8264 | 1.4434 | 582 | 7.4346 | 9664.8582 | 466.5704 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6145 | 98 | 0.01181 | 42601102 | PHILO 1102 | PHILO 1102circuit_breaker | 10918.6301 | 1.1574 | 644 | 6.7845 | 9671.6427 | 465.413 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6611 | 72 | 0.011732 | 24251101 | WOODSIDE 1101 | WOODSIDE 110147872 | 7099.6124 | 0.84471 | 747 | 4.4115 | 9676.0542 | 464.5683 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4519 | 5 | 0.011719 | 102841106 | ANITA 1106 | ANITA 11062418 | 185.0114 | 0.058595 | 1501 | 0.11496 | 9676.1692 | 464.5097 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3314 | 7 | 0.011701 | 42271105 | COTATI 1105 | COTATI 1105734248 | 774.6582 | 0.081908 | 1413 | 0.48135 | 9676.6505 | 464.4278 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8082 | 20 | 0.011695 | 182631104 | SAN LUIS OBISPO 1104 | SAN LUIS OBISPO 1104350030 | 8366.5404 | 0.2339 | 1117 | 5.1987 | 9681.8492 | 464.1939 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4425 | 14 | 0.011686 | 14101105 | ALHAMBRA 1105 | ALHAMBRA 110595016 | 1054.2618 | 0.16361 | 1223 | 0.65509 | 9682.5043 | 464.0303 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8343 | 37 | 0.011624 | 192171101 | WILLOW CREEK 1101 | WILLOW CREEK 11013050 | 4461.1677 | 0.43008 | 939 | 2.772 | 9685.2764 | 463.6002 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 944 | 32 | 0.011513 | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102514 | 5004.0934 | 0.36842 | 976 | 3.1094 | 9688.3858 | 463.2318 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2683 | 294 | 0.011488 | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 11031500 | 41462.2575 | 3.3774 | 361 | 25.7634 | 9714.1492 | 459.8544 | 7.5712 | 1.0296 | 1 | #N/A | 459.8544 | #N/A
North Coast | 7533 | 13 | 0.011465 | 42561102 | FULTON 1102 | FULTON 11024994 | 1753.9056 | 0.14905 | 1248 | 1.0898 | 9715.239 | 459.7053 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2480 | 180 | 0.011455 | 182601104 | OCEANO 1104 | OCEANO 1104Q08 | 19963.0067 | 2.0619 | 484 | 12.4044 | 9727.6435 | 457.6435 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 8821 | 21 | 0.011419 | 152181102 | FORESTHILL 1102 | FORESTHILL 1102circuit_breaker | 2652.1639 | 0.2398 | 1108 | 1.648 | 9729.2914 | 457.4037 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1312 | 366 | 0.011375 | 43432104 | SILVERADO 2104 | SILVERADO 210437632 | 42656.5483 | 4.1631 | 306 | 26.5055 | 9755.797 | 453.2406 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5238 | 98 | 0.01127 | 43432105 | SILVERADO 2105 | SILVERADO 2105616 | 11577.8412 | 1.1045 | 659 | 7.1941 | 9762.9911 | 452.1361 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7740 | 29 | 0.011243 | 182681101 | ZACA 1101 | ZACA 1101circuit_breaker | 11111.2282 | 0.32604 | 1006 | 6.9042 | 9769.8953 | 451.8101 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 482 | 55 | 0.01124 | 252941107 | TIVY VALLEY 1107 | TIVY VALLEY 1107circuit_breaker | 19259.2253 | 0.61822 | 846 | 11.9671 | 9781.8624 | 451.1918 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4392 | 288 | 0.011211 | 103401101 | GIRVAN 1101 | GIRVAN 11019732 | 33998.8263 | 3.2288 | 372 | 21.1259 | 9802.9883 | 447.963 | 20.0625 | 3.2288 | 1 | #N/A | 447.963 | #N/A
North Coast | 1700 | 136 | 0.011178 | 43351106 | LUCERNE 1106 | LUCERNE 1106664 | 15102.6309 | 1.5203 | 571 | 9.3843 | 9812.3727 | 446.4427 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6583 | 66 | 0.011121 | 254432103 | COARSEGOLD 2103 | COARSEGOLD 21036110 | 16696.1653 | 0.73399 | 788 | 10.3745 | 9822.7472 | 445.7087 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1016 | 27 | 0.011067 | 192311142 | FRUITLAND 1142 | FRUITLAND 1142circuit_breaker | 16901.355 | 0.29881 | 1043 | 10.502 | 9833.2492 | 445.4099 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6521 | 37 | 0.011058 | 103451101 | KESWICK 1101 | KESWICK 11011590 | 10135.4927 | 0.40915 | 954 | 6.2979 | 9839.5471 | 445.0008 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 305 | 8 | 0.011031 | 48011144 | CALPINE 1144 | CALPINE 1144circuit_breaker | 42270.0145 | 0.088245 | 1383 | 26.2654 | 9865.8125 | 444.9125 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1169 | 108 | 0.011021 | 182601104 | OCEANO 1104 | OCEANO 1104V36 | 15485.8164 | 1.1903 | 633 | 9.6224 | 9875.4349 | 443.7222 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 700 | 42 | 0.010992 | 43432105 | SILVERADO 2105 | SILVERADO 21051306 | 4731.2419 | 0.46168 | 925 | 2.9399 | 9878.3747 | 443.2605 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7578 | 167 | 0.010971 | 42251101 | HOPLAND 1101 | HOPLAND 110194006 | 18955.1203 | 1.8322 | 523 | 11.7782 | 9890.1529 | 441.4283 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8710 | 5 | 0.01096 | 48011146 | CALPINE 1146 | CALPINE 1146circuit_breaker | 4947.493 | 0.054802 | 1516 | 3.0742 | 9893.2271 | 441.3735 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1520 | 404 | 0.010955 | 42661103 | WILLITS 1103 | WILLITS 110391810 | 47349.2019 | 4.4256 | 290 | 29.4214 | 9922.6486 | 436.9479 | 26.0356 | 4.3045 | 1 | #N/A | #N/A | 436.9479
Bay Area | 4400 | 13 | 0.010916 | 14652106 | TIDEWATER 2106 | TIDEWATER 210665866 | 2331.7066 | 0.14191 | 1259 | 1.4489 | 9924.0974 | 436.806 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3824 | 60 | 0.010857 | 83182107 | LLAGAS 2107 | LLAGAS 210740407 | 6648.3182 | 0.65143 | 832 | 4.1311 | 9928.2285 | 436.1546 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5769 | 90 | 0.010819 | 43051101 | MONTICELLO 1101 | MONTICELLO 1101630 | 28630.1876 | 0.97368 | 704 | 17.79 | 9946.0185 | 435.1809 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1062 | 185 | 0.010817 | 152461103 | PLACER 1103 | PLACER 1103circuit_breaker | 20608.1987 | 2.0012 | 501 | 12.8053 | 9958.8238 | 433.1797 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6595 | 227 | 0.010657 | 103351101 | DESCHUTES 1101 | DESCHUTES 11011654 | 28373.2901 | 2.4192 | 439 | 17.6303 | 9976.4541 | 430.7604 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4156 | 8 | 0.01065 | 42991104 | LAS GALLINAS A 1104 | LAS GALLINAS A 1104304 | 683.5311 | 0.085197 | 1395 | 0.42473 | 9976.8789 | 430.6752 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 932 | 3 | 0.010641 | 13501108 | JARVIS 1108 | JARVIS 1108MR576 | 434.201 | 0.031924 | 1662 | 0.2698 | 9977.1487 | 430.6433 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8849 | 9 | 0.010637 | 83182105 | LLAGAS 2105 | LLAGAS 2105XR234 | 1152.082 | 0.09573 | 1360 | 0.71587 | 9977.8645 | 430.5476 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1493 | 187 | 0.010631 | 192251102 | RIO DELL 1102 | RIO DELL 11021504 | 17338.0675 | 1.988 | 504 | 10.7734 | 9988.6379 | 428.5596 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6351 | 180 | 0.010613 | 103221101 | KANAKA 1101 | KANAKA 110175744 | 17040.8886 | 1.9104 | 513 | 10.5887 | 9999.2266 | 426.6492 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 102 | 165 | 0.0106 | 102911110 | WYANDOTTE 1110 | WYANDOTTE 11101954 | 19698.3887 | 1.749 | 534 | 12.24 | 10011.4666 | 424.9001 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2790 | 206 | 0.010566 | 42951101 | MENDOCINO 1101 | MENDOCINO 110148750 | 28628.3227 | 2.1767 | 468 | 17.7888 | 10029.2554 | 422.7235 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6262 | 180 | 0.010507 | 254061102 | DUNLAP 1102 | DUNLAP 11027060 | 28682.1944 | 1.8912 | 516 | 17.8223 | 10047.0777 | 420.8322 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4628 | 20 | 0.010499 | 102911107 | WYANDOTTE 1107 | WYANDOTTE 1107circuit_breaker | 1641.1081 | 0.20999 | 1149 | 1.0197 | 10048.0975 | 420.6223 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6357 | 160 | 0.010423 | 43361103 | HIGHLANDS 1103 | HIGHLANDS 11031282 | 23288.0926 | 1.6676 | 543 | 14.4705 | 10062.568 | 418.9546 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 9085 | 58 | 0.01041 | 251511101 | WISHON 1101 | WISHON 1101circuit_breaker | 12397.8907 | 0.60376 | 852 | 7.7037 | 10070.2717 | 418.3509 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1932 | 223 | 0.010397 | 192221101 | GARBERVILLE 1101 | GARBERVILLE 11011514 | 23737.6018 | 2.3186 | 448 | 14.7499 | 10085.0215 | 416.0323 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 915 | 239 | 0.010369 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 36627.2391 | 2.4782 | 426 | 22.7591 | 10107.7806 | 413.5541 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6402 | 132 | 0.010226 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 11011325 | 13821.691 | 1.3499 | 604 | 8.5884 | 10116.369 | 412.2042 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7267 | 9 | 0.010172 | 42721106 | SONOMA 1106 | SONOMA 1106376 | 1147.4391 | 0.091552 | 1373 | 0.71299 | 10117.082 | 412.1126 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1496 | 374 | 0.010158 | 103201102 | CHALLENGE 1102 | CHALLENGE 11025462 | 37568.0951 | 3.7989 | 324 | 23.3437 | 10140.4258 | 408.3137 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7787 | 108 | 0.010079 | 192221101 | GARBERVILLE 1101 | GARBERVILLE 11012026 | 10220.4249 | 1.0885 | 667 | 6.3507 | 10146.7764 | 407.2252 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9044 | 24 | 0.01002 | 43501103 |  | 171410 | 2859.7024 | 0.24049 | 1107 | 1.7769 | 10148.5534 | 406.9847 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5770 | 4 | 0.0099935 | 102041104 | NOTRE DAME 1104 | NOTRE DAME 1104circuit_breaker | 1372.1379 | 0.039974 | 1603 | 0.85261 | 10149.406 | 406.9447 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1921 | 123 | 0.009981 | 182821103 | MESA 1103 | MESA 1103M72 | 14559.7479 | 1.2277 | 622 | 9.047 | 10158.453 | 405.717 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5242 | 171 | 0.0098919 | 43071102 | DUNBAR 1102 | DUNBAR 1102261774 | 21759.8537 | 1.6915 | 539 | 13.5209 | 10171.9739 | 404.0255 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8943 | 17 | 0.0098895 | 163341103 | CLAY 1103 | CLAY 11031821 | 4972.0887 | 0.16812 | 1216 | 3.0895 | 10175.0634 | 403.8574 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3918 | 206 | 0.0098439 | 163351704 | CURTIS 1704 | CURTIS 1704circuit_breaker | 22095.5217 | 2.0278 | 496 | 13.7295 | 10188.7929 | 401.8296 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7755 | 79 | 0.0098226 | 103451101 | KESWICK 1101 | KESWICK 11011588 | 14089.0434 | 0.77598 | 770 | 8.7545 | 10197.5475 | 401.0536 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 727 | 29 | 0.009728 | 42271105 | COTATI 1105 | COTATI 1105circuit_breaker | 4287.6063 | 0.28211 | 1060 | 2.6642 | 10200.2117 | 400.7715 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4072 | 88 | 0.0097183 | 43051101 | MONTICELLO 1101 | MONTICELLO 1101666 | 16769.5218 | 0.85521 | 744 | 10.4201 | 10210.6318 | 399.9163 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8245 | 25 | 0.0096857 | 252561101 | KERCKHOFF 1101 | KERCKHOFF 1101R308 | 6217.3701 | 0.24214 | 1105 | 3.8633 | 10214.4951 | 399.6741 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5206 | 43 | 0.0095951 | 43051101 | MONTICELLO 1101 | MONTICELLO 110137384 | 15055.0544 | 0.41259 | 951 | 9.3548 | 10223.8498 | 399.2615 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 876 | 239 | 0.0095641 | 254452101 | MARIPOSA 2101 | MARIPOSA 210110240 | 34426.9078 | 2.2858 | 452 | 21.3919 | 10245.2417 | 396.9757 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5657 | 5 | 0.0095603 | 182821101 | MESA 1101 | MESA 11016113 | 1783.5868 | 0.047802 | 1559 | 1.1083 | 10246.35 | 396.9279 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1212 | 234 | 0.0095256 | 153132102 | NARROWS 2102 | NARROWS 2102circuit_breaker | 36006.3008 | 2.229 | 460 | 22.3733 | 10268.7233 | 394.6989 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4055 | 63 | 0.0094734 | 42661103 | WILLITS 1103 | WILLITS 1103538 | 10337.071 | 0.59683 | 857 | 6.4232 | 10275.1464 | 394.1021 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5091 | 288 | 0.0094647 | 42661104 | WILLITS 1104 | WILLITS 1104504 | 36161.7196 | 2.7258 | 406 | 22.4698 | 10297.6163 | 391.3762 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5679 | 186 | 0.0094328 | 103201101 | CHALLENGE 1101 | CHALLENGE 11015460 | 19026.207 | 1.7545 | 532 | 11.8223 | 10309.4386 | 389.6217 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9108 | 74 | 0.0094145 | 103221101 | KANAKA 1101 | KANAKA 1101circuit_breaker | 7526.6787 | 0.69667 | 809 | 4.6769 | 10314.1154 | 388.925 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3148 | 178 | 0.009338 | 42661103 | WILLITS 1103 | WILLITS 11032500 | 48289.254 | 1.6622 | 544 | 30.0055 | 10344.121 | 387.2629 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6874 | 103 | 0.0093379 | 163201102 | WEST POINT 1102 | WEST POINT 110234416 | 16938.9243 | 0.9618 | 707 | 10.5254 | 10354.6463 | 386.3011 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4943 | 129 | 0.0093223 | 153662102 | APPLE HILL 2102 | APPLE HILL 210251792 | 14681.2766 | 1.2026 | 630 | 9.1225 | 10363.7689 | 385.0985 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7155 | 21 | 0.0093157 | 192311142 | FRUITLAND 1142 | FRUITLAND 114263170 | 19693.2907 | 0.19563 | 1168 | 12.2368 | 10376.0057 | 384.9029 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2379 | 103 | 0.0093057 | 42141101 | CLEAR LAKE 1101 | CLEAR LAKE 11011302 | 11041.6679 | 0.95848 | 709 | 6.861 | 10382.8667 | 383.9444 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1261 | 425 | 0.0093027 | 163351703 | CURTIS 1703 | CURTIS 17039180 | 93135.0691 | 3.9536 | 316 | 57.8714 | 10440.7381 | 379.9908 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8365 | 96 | 0.0092799 | 192461102 | BRIDGEVILLE 1102 | BRIDGEVILLE 110237486 | 16908.281 | 0.89087 | 731 | 10.5063 | 10451.2444 | 379.0999 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4680 | 9 | 0.0092694 | 182541103 | ATASCADERO 1103 | ATASCADERO 1103A88 | 1106.7141 | 0.083425 | 1402 | 0.68768 | 10451.9321 | 379.0165 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 290 | 60 | 0.0092488 | 42951101 | MENDOCINO 1101 | MENDOCINO 110131322 | 7456.8364 | 0.55493 | 871 | 4.6335 | 10456.5656 | 378.4615 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6721 | 79 | 0.009234 | 42091102 | MIRABEL 1102 | MIRABEL 1102334 | 7485.5189 | 0.72948 | 791 | 4.6513 | 10461.2168 | 377.732 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8011 | 3 | 0.0092136 | 42821102 | CLOVERDALE 1102 | CLOVERDALE 1102circuit_breaker | 420.2416 | 0.027641 | 1698 | 0.26113 | 10461.478 | 377.7044 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3425 | 208 | 0.0092116 | 42571102 | MOLINO 1102 | MOLINO 1102396 | 25719.6473 | 1.916 | 509 | 15.9814 | 10477.4594 | 375.7884 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 952 | 290 | 0.0091932 | 103221101 | KANAKA 1101 | KANAKA 110183288 | 28024.1151 | 2.666 | 412 | 17.4134 | 10494.8728 | 373.1224 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2538 | 33 | 0.0090807 | 43211101 | HARTLEY 1101 | HARTLEY 110186876 | 3441.3803 | 0.29966 | 1042 | 2.1384 | 10497.0112 | 372.8227 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1008 | 225 | 0.0090491 | 192411101 | LOW GAP 1101 | LOW GAP 11012094 | 24081.2978 | 2.036 | 493 | 14.9634 | 10511.9746 | 370.7867 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2774 | 90 | 0.0090214 | 42031124 | ALTO 1124 | ALTO 1124432 | 12584.9285 | 0.81193 | 754 | 7.8199 | 10519.7945 | 369.9747 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7830 | 77 | 0.0089969 | 192411101 | LOW GAP 1101 | LOW GAP 110186816 | 7103.5026 | 0.69276 | 810 | 4.4139 | 10524.2084 | 369.282 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4365 | 55 | 0.0089959 | 163201101 | WEST POINT 1101 | WEST POINT 1101circuit_breaker | 7549.0145 | 0.49477 | 902 | 4.6907 | 10528.8991 | 368.7872 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5453 | 273 | 0.0089751 | 103201101 | CHALLENGE 1101 | CHALLENGE 1101circuit_breaker | 26688.0859 | 2.4502 | 432 | 16.5832 | 10545.4823 | 366.337 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 66 | 79 | 0.0089602 | 152921101 | BROWNS VALLEY 1101 | BROWNS VALLEY 110197188 | 10687.565 | 0.70785 | 803 | 6.6409 | 10552.1233 | 365.6292 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2781 | 61 | 0.0089554 | 103461101 | PANORAMA 1101 | PANORAMA 11019092 | 16503.8389 | 0.54628 | 878 | 10.255 | 10562.3783 | 365.0829 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5439 | 97 | 0.0089439 | 153132101 | NARROWS 2101 | NARROWS 2101circuit_breaker | 25133.8252 | 0.86756 | 736 | 15.6174 | 10577.9957 | 364.2153 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1837 | 58 | 0.0089264 | 183052110 | TEMPLETON 2110 | TEMPLETON 2110R06 | 8134.5668 | 0.51773 | 893 | 5.0546 | 10583.0503 | 363.6976 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5523 | 2 | 0.00892 | 82931101 | POINT MORETTI 1101 | POINT MORETTI 11015104 | 3011.2994 | 0.01784 | 1791 | 1.8711 | 10584.9214 | 363.6798 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1477 | 201 | 0.0089078 | 192221101 | GARBERVILLE 1101 | GARBERVILLE 11011750 | 23509.5028 | 1.7905 | 526 | 14.6081 | 10599.5296 | 361.8893 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1703 | 329 | 0.0088988 | 153132102 | NARROWS 2102 | NARROWS 21022220 | 43302.8869 | 2.9277 | 395 | 26.9072 | 10626.4367 | 358.9616 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4543 | 130 | 0.0088328 | 153132105 | NARROWS 2105 | NARROWS 210551582 | 15330.2671 | 1.1483 | 646 | 9.5258 | 10635.9625 | 357.8133 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2628 | 523 | 0.0088141 | 153662102 | APPLE HILL 2102 | APPLE HILL 210277546 | 69457.7296 | 4.6098 | 279 | 43.159 | 10679.1215 | 353.2035 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Valley | 2628 | 1 | 0.0035106 | 153662102 | APPLE HILL 2102 | APPLE HILL 210277546 | 69457.7296 | 0.0035106 | 279 | 43.159 | 10722.2805 | 353.2 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Sierra | 3171 | 215 | 0.0087857 | 152271102 | WISE 1102 | WISE 1102circuit_breaker | 29505.5664 | 1.8889 | 517 | 18.3339 | 10740.6144 | 351.3111 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8930 | 36 | 0.0087216 | 252192105 | BEAR VALLEY 2105 | BEAR VALLEY 21054170 | 15319.6375 | 0.31398 | 1017 | 9.5192 | 10750.1336 | 350.9971 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4789 | 391 | 0.008703 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 38602.5649 | 3.4029 | 357 | 23.9865 | 10774.1201 | 347.5943 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5633 | 39 | 0.0086954 | 254421103 | OAKHURST 1103 | OAKHURST 11035732 | 5570.0761 | 0.33912 | 995 | 3.4611 | 10777.5812 | 347.2551 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7594 | 177 | 0.0086865 | 42661103 | WILLITS 1103 | WILLITS 110337506 | 18589.4866 | 1.5375 | 568 | 11.551 | 10789.1322 | 345.7176 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4753 | 48 | 0.0086545 | 43292103 | PUEBLO 2103 | PUEBLO 21031970 | 5037.9118 | 0.41542 | 949 | 3.1304 | 10792.2626 | 345.3022 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4359 | 105 | 0.0086285 | 43351106 | LUCERNE 1106 | LUCERNE 1106526 | 16072.0884 | 0.906 | 726 | 9.9867 | 10802.2493 | 344.3962 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4292 | 23 | 0.0085969 | 103491101 | MC ARTHUR 1101 | MC ARTHUR 110138998 | 15389.4778 | 0.19773 | 1160 | 9.5626 | 10811.8119 | 344.1985 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4945 | 182 | 0.0085705 | 182631107 | SAN LUIS OBISPO 1107 | SAN LUIS OBISPO 1107V60 | 25701.6823 | 1.5598 | 565 | 15.9703 | 10827.7822 | 342.6386 | 15.1773 | 1.5179 | 1 | #N/A | 342.6386 | #N/A
Central Valley | 9511 | 23 | 0.0085676 | 161380201 | TIGER CREEK 0201 | TIGER CREEK 0201circuit_breaker | 6272.7997 | 0.19705 | 1162 | 3.8977 | 10831.6799 | 342.4416 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9487 | 49 | 0.0085488 | 101321101 | PIT NO 5 1101 | PIT NO 5 11011618 | 9746.1598 | 0.41889 | 947 | 6.056 | 10837.7359 | 342.0227 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8869 | 20 | 0.0085256 | 163541101 | OLETA 1101 | OLETA 1101circuit_breaker | 5372.4907 | 0.17051 | 1210 | 3.3383 | 10841.0742 | 341.8522 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5162 | 135 | 0.0084906 | 252531102 | SAN JOAQUIN #3 1102 | SAN JOAQUIN #3 1102circuit_breaker | 15601.4012 | 1.1462 | 647 | 9.6943 | 10850.7685 | 340.706 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8995 | 8 | 0.0084841 | 101321101 | PIT NO 5 1101 | PIT NO 5 1101circuit_breaker | 1162.2395 | 0.067873 | 1460 | 0.72218 | 10851.4907 | 340.6381 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3208 | 244 | 0.0084732 | 103451101 | KESWICK 1101 | KESWICK 11019712 | 29985.2487 | 2.0674 | 483 | 18.632 | 10870.1226 | 338.5706 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2219 | 76 | 0.0084724 | 83392110 | SWIFT 2110 | SWIFT 2110XR366 | 13196.8212 | 0.64391 | 838 | 8.2001 | 10878.3227 | 337.9267 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3501 | 210 | 0.0084667 | 152561107 | PENRYN 1107 | PENRYN 1107346 | 22020.6709 | 1.778 | 528 | 13.683 | 10892.0057 | 336.1487 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3438 | 8 | 0.0084369 | 153132102 | NARROWS 2102 | NARROWS 21022718 | 747.0941 | 0.067495 | 1464 | 0.46422 | 10892.47 | 336.0812 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6929 | 52 | 0.0083873 | 43371102 | LAKEVILLE 1102 | LAKEVILLE 11023341 | 11684.2399 | 0.43614 | 936 | 7.2602 | 10899.7302 | 335.6451 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7822 | 1 | 0.0083717 | 42271105 | COTATI 1105 | COTATI 1105893 | 105.1251 | 0.0083717 | 1933 | 0.065322 | 10899.7955 | 335.6367 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3023 | 66 | 0.0083262 | 153652108 | SHINGLE SPRINGS 2108 | SHINGLE SPRINGS 210819622 | 8713.308 | 0.54953 | 873 | 5.4142 | 10905.2097 | 335.0872 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6103 | 11 | 0.0083008 | 163231101 | NORTH BRANCH 1101 | NORTH BRANCH 110113496 | 2903.2847 | 0.091309 | 1374 | 1.804 | 10907.0138 | 334.9959 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7335 | 41 | 0.0082695 | 43071101 | DUNBAR 1101 | DUNBAR 11014817 | 4994.4292 | 0.33905 | 996 | 3.1034 | 10910.1171 | 334.6568 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2067 | 182 | 0.008266 | 163201102 | WEST POINT 1102 | WEST POINT 1102circuit_breaker | 28676.4886 | 1.5044 | 572 | 17.8187 | 10927.9359 | 333.1524 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7345 | 2 | 0.0082504 | 254151101 | AUBERRY 1101 | AUBERRY 110149122 | 6376.7942 | 0.016501 | 1809 | 3.9624 | 10931.8982 | 333.1359 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6120 | 88 | 0.0082285 | 42811113 | MONTE RIO 1113 | MONTE RIO 11131991 | 11352.1197 | 0.72411 | 794 | 7.0539 | 10938.9521 | 332.4118 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7614 | 48 | 0.0081941 | 254452102 | MARIPOSA 2102 | MARIPOSA 2102circuit_breaker | 8453.5074 | 0.39332 | 964 | 5.2528 | 10944.2049 | 332.0185 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3488 | 109 | 0.0081063 | 163541101 | OLETA 1101 | OLETA 110113478 | 19228.1516 | 0.88359 | 733 | 11.9478 | 10956.1527 | 331.1349 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5722 | 1 | 0.0081045 | 43040401 | GARCIA 0401 | GARCIA 0401666 | 3911.285 | 0.0081045 | 1937 | 2.4304 | 10958.5831 | 331.1268 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4035 | 110 | 0.0081008 | 103031102 | ORO FINO 1102 | ORO FINO 11022096 | 22689.7759 | 0.89108 | 730 | 14.0988 | 10972.6818 | 330.2357 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8909 | 11 | 0.0079304 | 102911109 | WYANDOTTE 1109 | WYANDOTTE 110942650 | 1091.021 | 0.087234 | 1388 | 0.67793 | 10973.3598 | 330.1485 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2318 | 282 | 0.0078911 | 103601101 | WHITMORE 1101 | WHITMORE 11011594 | 39015.2543 | 2.2253 | 463 | 24.2429 | 10997.6027 | 327.9232 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4507 | 82 | 0.0078609 | 182631104 | SAN LUIS OBISPO 1104 | SAN LUIS OBISPO 1104V40 | 22025.4599 | 0.6446 | 837 | 13.686 | 11011.2887 | 327.2786 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4566 | 57 | 0.0078457 | 152271101 | WISE 1101 | WISE 1101circuit_breaker | 6518.1918 | 0.4472 | 930 | 4.0502 | 11015.3389 | 326.8314 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3522 | 137 | 0.0078069 | 103721101 | PIT NO 1 1101 | PIT NO 1 11011552 | 20793.5873 | 1.0695 | 672 | 12.9205 | 11028.2594 | 325.7619 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5007 | 159 | 0.0078006 | 42031125 | ALTO 1125 | ALTO 1125902 | 19412.9994 | 1.2403 | 618 | 12.0627 | 11040.3221 | 324.5216 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5259 | 202 | 0.0077899 | 43071103 | DUNBAR 1103 | DUNBAR 1103534 | 25938.9873 | 1.5736 | 563 | 16.1177 | 11056.4398 | 322.948 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1768 | 593 | 0.0077896 | 103191101 | BANGOR 1101 | BANGOR 11011804 | 69024.4911 | 4.6192 | 277 | 42.8898 | 11099.3297 | 318.3288 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6685 | 35 | 0.0077718 | 43311102 | KONOCTI 1102 | KONOCTI 110264464 | 3132.1045 | 0.27201 | 1073 | 1.9462 | 11101.2759 | 318.0567 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2135 | 4 | 0.0077682 | 43292102 | PUEBLO 2102 | PUEBLO 2102circuit_breaker | 802.3935 | 0.031073 | 1673 | 0.49858 | 11101.7744 | 318.0257 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4073 | 183 | 0.0077156 | 192221102 | GARBERVILLE 1102 | GARBERVILLE 11021510 | 21228.5996 | 1.412 | 589 | 13.1908 | 11114.9653 | 316.6137 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 949 | 24 | 0.0077012 | 43071102 | DUNBAR 1102 | DUNBAR 1102903030 | 2345.7829 | 0.18483 | 1186 | 1.4576 | 11116.4229 | 316.4289 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6896 | 101 | 0.0076923 | 192461101 | BRIDGEVILLE 1101 | BRIDGEVILLE 110137484 | 12953.0865 | 0.77693 | 769 | 8.0487 | 11124.4716 | 315.652 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9320 | 17 | 0.0076587 | 43432104 | SILVERADO 2104 | SILVERADO 2104645 | 1626.8938 | 0.1302 | 1279 | 1.0109 | 11125.4825 | 315.5218 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4730 | 33 | 0.0076551 | 153132102 | NARROWS 2102 | NARROWS 210276952 | 3554.8483 | 0.25262 | 1095 | 2.2089 | 11127.6913 | 315.2691 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2439 | 133 | 0.007653 | 43191101 | REDBUD 1101 | REDBUD 1101circuit_breaker | 15284.1769 | 1.0178 | 685 | 9.4971 | 11137.1885 | 314.2513 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 9177 | 8 | 0.0076224 | 83182101 | LLAGAS 2101 | LLAGAS 21014523 | 1169.9655 | 0.06098 | 1488 | 0.72698 | 11137.9155 | 314.1903 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7191 | 213 | 0.0076073 | 192221101 | GARBERVILLE 1101 | GARBERVILLE 110197300 | 22729.2098 | 1.6204 | 550 | 14.1233 | 11152.0387 | 312.57 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5072 | 5 | 0.0075719 | 43381101 | POINT ARENA 1101 | POINT ARENA 110137426 | 776.126 | 0.03786 | 1616 | 0.48226 | 11152.521 | 312.5321 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3097 | 26 | 0.0075562 | 43161101 | SALMON CREEK 1101 | SALMON CREEK 1101194 | 7700.4518 | 0.19646 | 1165 | 4.7848 | 11157.3058 | 312.3356 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7359 | 59 | 0.0075413 | 163201102 | WEST POINT 1102 | WEST POINT 11021369 | 15950.4182 | 0.44494 | 931 | 9.9111 | 11167.217 | 311.8907 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2844 | 1 | 0.0075289 | 252931103 | TEJON 1103 | TEJON 11032280 | 2624.0904 | 0.0075289 | 1949 | 1.6305 | 11168.8475 | 311.8832 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 38 | 70 | 0.0075118 | 43191101 | REDBUD 1101 | REDBUD 1101708166 | 13686.2588 | 0.52582 | 889 | 8.5042 | 11177.3517 | 311.3573 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3660 | 46 | 0.0074706 | 42811113 | MONTE RIO 1113 | MONTE RIO 11131137 | 4563.9223 | 0.34365 | 990 | 2.8359 | 11180.1876 | 311.0137 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4289 | 157 | 0.0074491 | 153662102 | APPLE HILL 2102 | APPLE HILL 210297982 | 15759.3574 | 1.1695 | 640 | 9.7924 | 11189.98 | 309.8442 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 782 | 115 | 0.0074226 | 182821101 | MESA 1101 | MESA 1101M86 | 18124.1497 | 0.8536 | 745 | 11.2618 | 11201.2419 | 308.9906 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4380 | 361 | 0.0074151 | 42661103 | WILLITS 1103 | WILLITS 1103968 | 42022.0904 | 2.6769 | 410 | 26.1113 | 11227.3532 | 306.3137 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 315 | 126 | 0.0074109 | 152201101 | PIKE CITY 1101 | PIKE CITY 11011730 | 13838.6427 | 0.93378 | 719 | 8.5989 | 11235.9521 | 305.38 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5574 | 259 | 0.0073881 | 192221102 | GARBERVILLE 1102 | GARBERVILLE 11026084 | 24635.362 | 1.9135 | 512 | 15.3077 | 11251.2598 | 303.4664 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7501 | 28 | 0.0073855 | 103501101 | PIT NO 7 1101 | PIT NO 7 1101circuit_breaker | 4357.8457 | 0.20679 | 1154 | 2.7078 | 11253.9676 | 303.2596 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5990 | 104 | 0.0073765 | 102831103 | PARADISE 1103 | PARADISE 1103circuit_breaker | 53143.2931 | 0.76716 | 776 | 33.0217 | 11286.9893 | 302.4925 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 8415 | 125 | 0.0073643 | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 14778.7102 | 0.92054 | 723 | 9.1831 | 11296.1724 | 301.5719 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2001 | 5 | 0.0073597 | 252341104 | REEDLEY 1104 | REEDLEY 1104274990 | 2623.0001 | 0.036799 | 1626 | 1.6299 | 11297.8023 | 301.5351 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1527 | 8 | 0.0073429 | 14302106 | MEADOW LANE 2106 | MEADOW LANE 2106C558R | 1360.7806 | 0.058743 | 1500 | 0.84555 | 11298.6478 | 301.4764 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3038 | 185 | 0.0073272 | 192221102 | GARBERVILLE 1102 | GARBERVILLE 11022540 | 23928.4593 | 1.3555 | 603 | 14.8685 | 11313.5163 | 300.1209 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1947 | 15 | 0.0073186 | 42271105 | COTATI 1105 | COTATI 1105328 | 1823.3649 | 0.10978 | 1326 | 1.133 | 11314.6492 | 300.0111 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2019 | 138 | 0.0073091 | 183041101 | BUELLTON 1101 | BUELLTON 1101Y06 | 46315.0095 | 1.0087 | 691 | 28.7788 | 11343.428 | 299.0024 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 783 | 45 | 0.0072747 | 43071101 | DUNBAR 1101 | DUNBAR 1101circuit_breaker | 3778.218 | 0.32736 | 1005 | 2.3477 | 11345.7757 | 298.6751 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3683 | 87 | 0.0072708 | 42031125 | ALTO 1125 | ALTO 1125510 | 11874.2275 | 0.63256 | 840 | 7.3783 | 11353.154 | 298.0425 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4371 | 39 | 0.0072232 | 43411102 | CALPELLA 1102 | CALPELLA 1102496 | 5425.0881 | 0.28171 | 1061 | 3.371 | 11356.525 | 297.7608 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3620 | 317 | 0.0072179 | 254452101 | MARIPOSA 2101 | MARIPOSA 210110070 | 41751.638 | 2.2881 | 451 | 25.9433 | 11382.4683 | 295.4727 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9191 | 42 | 0.0072075 | 14662112 | TASSAJARA 2112 | TASSAJARA 21126392 | 8416.1442 | 0.30271 | 1033 | 5.2295 | 11387.6978 | 295.17 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2130 | 220 | 0.0071888 | 43411101 | CALPELLA 1101 | CALPELLA 1101542 | 37983.2329 | 1.5815 | 560 | 23.6017 | 11411.2995 | 293.5885 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1065 | 41 | 0.0071754 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 11022044 | 13144.9091 | 0.29419 | 1047 | 8.1679 | 11419.4674 | 293.2943 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7140 | 15 | 0.0071484 | 83182104 | LLAGAS 2104 | LLAGAS 2104XR294 | 4685.9835 | 0.10723 | 1335 | 2.9117 | 11422.3791 | 293.1871 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6807 | 21 | 0.0071336 | 42571102 | MOLINO 1102 | MOLINO 1102982462 | 2320.9625 | 0.14981 | 1245 | 1.4422 | 11423.8213 | 293.0373 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 796 | 209 | 0.0071315 | 43071102 | DUNBAR 1102 | DUNBAR 1102246 | 21342.108 | 1.4905 | 575 | 13.2614 | 11437.0826 | 291.5468 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 8892 | 94 | 0.0071193 | 153741101 | DOBBINS 1101 | DOBBINS 110191464 | 11341.1652 | 0.66921 | 820 | 7.0471 | 11444.1297 | 290.8776 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5821 | 24 | 0.0070701 | 254452101 | MARIPOSA 2101 | MARIPOSA 2101309438 | 5630.6567 | 0.16968 | 1212 | 3.4987 | 11447.6284 | 290.7079 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4806 | 58 | 0.0070354 | 252192101 | BEAR VALLEY 2101 | BEAR VALLEY 210190550 | 12881.7348 | 0.40805 | 955 | 8.0043 | 11455.6328 | 290.2998 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 853 | 17 | 0.0070095 | 163781701 | PEORIA 1701 | PEORIA 17019811 | 4687.197 | 0.11916 | 1297 | 2.9125 | 11458.5453 | 290.1807 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3145 | 52 | 0.0069807 | 42271103 | COTATI 1103 | COTATI 110361736 | 18397.7495 | 0.363 | 981 | 11.4318 | 11469.9771 | 289.8177 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2973 | 18 | 0.0069559 | 42251101 | HOPLAND 1101 | HOPLAND 1101558 | 2272.5532 | 0.12521 | 1287 | 1.4121 | 11471.3892 | 289.6925 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5444 | 293 | 0.0069456 | 14101105 | ALHAMBRA 1105 | ALHAMBRA 110582622 | 41695.7116 | 2.0351 | 495 | 25.9085 | 11497.2977 | 287.6574 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1141 | 124 | 0.0069215 | 43071101 | DUNBAR 1101 | DUNBAR 1101302 | 13818.0912 | 0.85826 | 742 | 8.5862 | 11505.8839 | 286.7991 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8709 | 5 | 0.0068611 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210510225 | 292.7321 | 0.034306 | 1642 | 0.1819 | 11506.0658 | 286.7648 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7765 | 71 | 0.0068409 | 43071102 | DUNBAR 1102 | DUNBAR 1102861496 | 7248.9399 | 0.48571 | 910 | 4.5043 | 11510.57 | 286.2791 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9082 | 26 | 0.0068059 | 43321103 | RINCON 1103 | RINCON 11035152 | 2561.9657 | 0.17695 | 1196 | 1.5919 | 11512.162 | 286.1022 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6476 | 232 | 0.0068018 | 192401101 | HOOPA 1101 | HOOPA 11013304 | 27461.6659 | 1.578 | 561 | 17.0639 | 11529.2259 | 284.5242 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 963 | 734 | 0.0067718 | 163201102 | WEST POINT 1102 | WEST POINT 11024788 | 113054.7153 | 4.9705 | 267 | 70.2489 | 11599.4748 | 279.5537 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7679 | 88 | 0.0067652 | 152181101 | FORESTHILL 1101 | FORESTHILL 110175340 | 8005.6151 | 0.59533 | 858 | 4.9745 | 11604.4492 | 278.9583 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2786 | 1 | 0.0067338 | 13911101 | WILLOW PASS 1101 | WILLOW PASS 1101circuit_breaker | 2388.9792 | 0.0067338 | 1963 | 1.4844 | 11605.9337 | 278.9516 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1490 | 182 | 0.0067166 | 163451702 | FROGTOWN 1702 | FROGTOWN 17021573 | 28787.0124 | 1.2224 | 625 | 17.8874 | 11623.8211 | 277.7292 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5192 | 87 | 0.0067157 | 163451702 | FROGTOWN 1702 | FROGTOWN 17027108 | 14176.7324 | 0.58426 | 864 | 8.809 | 11632.6301 | 277.1449 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 9374 | 11 | 0.0067153 | 63172101 | MADISON 2101 | MADISON 210113372 | 6078.9039 | 0.073868 | 1435 | 3.7773 | 11636.4074 | 277.071 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8880 | 102 | 0.0067128 | 254432104 | COARSEGOLD 2104 | COARSEGOLD 21045516 | 29689.925 | 0.6847 | 815 | 18.4485 | 11654.8558 | 276.3863 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4541 | 26 | 0.0067088 | 163201101 | WEST POINT 1101 | WEST POINT 110112256 | 10485.7942 | 0.17443 | 1200 | 6.5156 | 11661.3714 | 276.2119 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1751 | 107 | 0.0066952 | 102211101 | BUCKS CREEK 1101 | BUCKS CREEK 1101circuit_breaker | 31149.9295 | 0.71638 | 798 | 19.3557 | 11680.727 | 275.4955 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4890 | 150 | 0.0066901 | 163451702 | FROGTOWN 1702 | FROGTOWN 17028482 | 23167.7877 | 1.0035 | 692 | 14.3958 | 11695.1228 | 274.492 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5113 | 7 | 0.0066751 | 42751111 | FITCH MOUNTAIN 1111 | FITCH MOUNTAIN 1111circuit_breaker | 486.7283 | 0.046726 | 1569 | 0.30244 | 11695.4253 | 274.4453 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3525 | 344 | 0.006672 | 182671108 | SANTA MARIA 1108 | SANTA MARIA 1108M80 | 94108.6643 | 2.2952 | 449 | 58.4764 | 11753.9017 | 272.1501 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4203 | 164 | 0.0066719 | 182821101 | MESA 1101 | MESA 11016111 | 37685.5687 | 1.0942 | 664 | 23.4167 | 11777.3184 | 271.0559 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1530 | 20 | 0.006661 | 42251101 | HOPLAND 1101 | HOPLAND 110180620 | 1849.3413 | 0.13322 | 1273 | 1.1491 | 11778.4675 | 270.9227 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6920 | 319 | 0.006654 | 192411101 | LOW GAP 1101 | LOW GAP 11014160 | 34571.9467 | 2.1226 | 477 | 21.482 | 11799.9495 | 268.8001 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4735 | 99 | 0.0066003 | 43071101 | DUNBAR 1101 | DUNBAR 110179086 | 10550.9054 | 0.65343 | 831 | 6.556 | 11806.5055 | 268.1466 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5080 | 22 | 0.0065807 | 102541101 | VOLTA 1101 | VOLTA 11011568 | 36682.0507 | 0.14477 | 1254 | 22.7932 | 11829.2987 | 268.0019 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5980 | 136 | 0.0065659 | 43051101 | MONTICELLO 1101 | MONTICELLO 110193384 | 25527.468 | 0.89297 | 729 | 15.862 | 11845.1607 | 267.1089 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1003 | 20 | 0.0065233 | 42771114 | UKIAH 1114 | UKIAH 1114822 | 3178.5328 | 0.13047 | 1278 | 1.975 | 11847.1358 | 266.9784 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 786 | 551 | 0.0064873 | 153132102 | NARROWS 2102 | NARROWS 210248484 | 66722.6758 | 3.5745 | 338 | 41.4595 | 11888.5953 | 263.4039 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4630 | 85 | 0.006454 | 182601104 | OCEANO 1104 | OCEANO 1104Q12 | 16245.9078 | 0.54859 | 874 | 10.0947 | 11898.6901 | 262.8553 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6804 | 93 | 0.0064424 | 103271101 | ANTLER 1101 | ANTLER 11011612 | 14104.292 | 0.59914 | 854 | 8.764 | 11907.4541 | 262.2562 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 74 | 60 | 0.0064415 | 42031124 | ALTO 1124 | ALTO 1124428 | 6700.9234 | 0.38649 | 966 | 4.1638 | 11911.6178 | 261.8697 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 999 | 18 | 0.0064187 | 42251101 | HOPLAND 1101 | HOPLAND 1101770 | 7603.6292 | 0.11554 | 1305 | 4.7247 | 11916.3425 | 261.7542 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4411 | 158 | 0.006408 | 252811102 | MERCED FALLS 1102 | MERCED FALLS 110285002 | 57333.7596 | 1.0125 | 687 | 35.6255 | 11951.968 | 260.7417 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3793 | 286 | 0.0063917 | 43321103 | RINCON 1103 | RINCON 1103474 | 29554.6121 | 1.828 | 524 | 18.3644 | 11970.3324 | 258.9137 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2794 | 36 | 0.0063809 | 182631101 | SAN LUIS OBISPO 1101 | SAN LUIS OBISPO 1101circuit_breaker | 5333.7243 | 0.22971 | 1120 | 3.3142 | 11973.6466 | 258.684 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2591 | 495 | 0.006368 | 183052111 | TEMPLETON 2111 | TEMPLETON 2111A66 | 54317.8357 | 3.1522 | 380 | 33.7515 | 12007.3982 | 255.5318 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3166 | 680 | 0.0063679 | 153662102 | APPLE HILL 2102 | APPLE HILL 2102186912 | 78311.5629 | 4.3301 | 296 | 48.6605 | 12056.0587 | 251.2017 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 276 | 35 | 0.0063559 | 42891101 | GEYSERVILLE 1101 | GEYSERVILLE 1101122 | 7052.0878 | 0.22246 | 1133 | 4.382 | 12060.4406 | 250.9792 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 842 | 3 | 0.0063204 | 42721103 | SONOMA 1103 | SONOMA 1103418 | 326.2189 | 0.018961 | 1774 | 0.2027 | 12060.6434 | 250.9603 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5725 | 24 | 0.006314 | 42271102 | COTATI 1102 | COTATI 1102260 | 4171.7031 | 0.15154 | 1242 | 2.5922 | 12063.2355 | 250.8087 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1283 | 168 | 0.0062707 | 43321101 | RINCON 1101 | RINCON 1101578 | 27632.8586 | 1.0535 | 678 | 17.1703 | 12080.4058 | 249.7552 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7927 | 37 | 0.0062471 | 163781705 | PEORIA 1705 | PEORIA 1705999 | 3715.0604 | 0.23114 | 1118 | 2.3084 | 12082.7142 | 249.5241 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3755 | 1 | 0.0062313 | 252341112 | REEDLEY 1112 | REEDLEY 11127240 | 1451.4793 | 0.0062313 | 1969 | 0.90191 | 12083.6161 | 249.5179 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5363 | 59 | 0.006231 | 163201102 | WEST POINT 1102 | WEST POINT 11021305 | 18286.9662 | 0.36763 | 977 | 11.363 | 12094.9791 | 249.1502 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1846 | 109 | 0.0062118 | 103441101 | JESSUP 1101 | JESSUP 11019002 | 12312.9538 | 0.67709 | 818 | 7.6509 | 12102.63 | 248.4731 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6095 | 56 | 0.0061987 | 163201102 | WEST POINT 1102 | WEST POINT 11021303 | 25499.4036 | 0.34713 | 989 | 15.8446 | 12118.4746 | 248.126 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9321 | 18 | 0.0061911 | 192171102 | WILLOW CREEK 1102 | WILLOW CREEK 110237374 | 2046.1835 | 0.11144 | 1319 | 1.2714 | 12119.7461 | 248.0146 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2170 | 3 | 0.0061911 | 43302103 | MONROE 2103 | MONROE 2103circuit_breaker | 674.1153 | 0.018573 | 1780 | 0.41888 | 12120.1649 | 247.996 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1083 | 23 | 0.0061563 | 83531107 | MC KEE 1107 | MC KEE 1107XR010 | 4483.0278 | 0.1416 | 1261 | 2.7856 | 12122.9506 | 247.8544 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7256 | 382 | 0.0061114 | 182541103 | ATASCADERO 1103 | ATASCADERO 1103A06 | 56511.8674 | 2.3346 | 447 | 35.1148 | 12158.0654 | 245.5198 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4877 | 12 | 0.0060995 | 163011103 | MARTELL 1103 | MARTELL 1103circuit_breaker | 1549.4828 | 0.073194 | 1437 | 0.9628 | 12159.0282 | 245.4466 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 899 | 98 | 0.0060958 | 102911105 | WYANDOTTE 1105 | WYANDOTTE 1105329930 | 9878.9278 | 0.59739 | 855 | 6.1385 | 12165.1667 | 244.8493 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 861 | 443 | 0.0060605 | 163451702 | FROGTOWN 1702 | FROGTOWN 170275252 | 90444.8522 | 2.6848 | 409 | 56.1998 | 12221.3665 | 242.1645 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2624 | 406 | 0.0060603 | 163451702 | FROGTOWN 1702 | FROGTOWN 170212282 | 58310.0701 | 2.4605 | 430 | 36.2322 | 12257.5987 | 239.704 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1076 | 603 | 0.006038 | 152691103 | HIGGINS 1103 | HIGGINS 110332120 | 64628.4099 | 3.6409 | 332 | 40.1582 | 12297.7569 | 236.063 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 539 | 570 | 0.005999 | 153652110 | SHINGLE SPRINGS 2110 | SHINGLE SPRINGS 21107742 | 73513.8191 | 3.4194 | 355 | 45.6794 | 12343.4362 | 232.6436 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 142 | 165 | 0.0059963 | 152431102 | SHADY GLEN 1102 | SHADY GLEN 11022232 | 16796.8272 | 0.98939 | 699 | 10.4371 | 12353.8733 | 231.6542 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5941 | 342 | 0.0059962 | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 110111188 | 48300.9598 | 2.0507 | 487 | 30.0128 | 12383.8861 | 229.6036 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3260 | 755 | 0.0058828 | 153132105 | NARROWS 2105 | NARROWS 21052216 | 90284.175 | 4.4415 | 288 | 56.1 | 12439.9861 | 225.1621 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2332 | 286 | 0.005859 | 152031103 | GRASS VALLEY 1103 | GRASS VALLEY 11032110 | 31856.0669 | 1.6757 | 541 | 19.7944 | 12459.7805 | 223.4864 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3459 | 7 | 0.0058383 | 63121101 | CORTINA 1101 | CORTINA 1101302192 | 1666.8417 | 0.040868 | 1598 | 1.0357 | 12460.8162 | 223.4455 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8636 | 202 | 0.0058222 | 102211102 | BUCKS CREEK 1102 | BUCKS CREEK 1102circuit_breaker | 47507.7824 | 1.1761 | 636 | 29.52 | 12490.3362 | 222.2694 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6107 | 178 | 0.0058175 | 153662102 | APPLE HILL 2102 | APPLE HILL 21026552 | 20150.542 | 1.0355 | 681 | 12.521 | 12502.8572 | 221.2339 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6741 | 189 | 0.0057992 | 103751102 | BIG BEND 1102 | BIG BEND 1102circuit_breaker | 27533.9662 | 1.0961 | 663 | 17.1088 | 12519.966 | 220.1379 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4631 | 84 | 0.0057937 | 254432102 | COARSEGOLD 2102 | COARSEGOLD 2102circuit_breaker | 22592.2597 | 0.48667 | 908 | 14.0382 | 12534.0042 | 219.6512 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4182 | 7 | 0.0057792 | 83242105 | MORGAN HILL 2105 | MORGAN HILL 2105XR494 | 485.8055 | 0.040455 | 1600 | 0.30187 | 12534.306 | 219.6107 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4734 | 105 | 0.005751 | 24251101 | WOODSIDE 1101 | WOODSIDE 11018972 | 9771.1957 | 0.60385 | 851 | 6.0715 | 12540.3776 | 219.0069 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 627 | 87 | 0.005749 | 42681101 | LAYTONVILLE 1101 | LAYTONVILLE 1101circuit_breaker | 9592.9795 | 0.50016 | 898 | 5.9608 | 12546.3384 | 218.5067 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6771 | 116 | 0.005746 | 163751102 | PINE GROVE 1102 | PINE GROVE 110235576 | 12655.9114 | 0.66654 | 823 | 7.864 | 12554.2024 | 217.8402 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2292 | 1034 | 0.0057379 | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21067522 | 108764.9416 | 5.9329 | 239 | 67.5834 | 12621.7858 | 211.9072 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5553 | 9 | 0.005729 | 183101103 | CABRILLO 1103 | CABRILLO 11031437 | 4397.9316 | 0.051561 | 1533 | 2.7327 | 12624.5185 | 211.8557 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7473 | 8 | 0.0057172 | 43292103 | PUEBLO 2103 | PUEBLO 2103694 | 1193.6984 | 0.045737 | 1576 | 0.74173 | 12625.2602 | 211.8099 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6921 | 76 | 0.0056866 | 152181101 | FORESTHILL 1101 | FORESTHILL 11011820 | 8970.0583 | 0.43218 | 938 | 5.5737 | 12630.834 | 211.3778 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6183 | 5 | 0.0056778 | 103721101 | PIT NO 1 1101 | PIT NO 1 11019702 | 994.3298 | 0.028389 | 1691 | 0.61785 | 12631.4518 | 211.3494 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7139 | 58 | 0.0056595 | 42031124 | ALTO 1124 | ALTO 11243745 | 7368.4316 | 0.32825 | 1003 | 4.5785 | 12636.0303 | 211.0211 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3986 | 232 | 0.0056462 | 163201102 | WEST POINT 1102 | WEST POINT 110236676 | 27353.6284 | 1.3099 | 608 | 16.9968 | 12653.0271 | 209.7112 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2664 | 25 | 0.0056186 | 182562102 | CHOLAME 2102 | CHOLAME 2102X10 | 32569.8267 | 0.14047 | 1264 | 20.2379 | 12673.265 | 209.5707 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4618 | 230 | 0.0056093 | 42681101 | LAYTONVILLE 1101 | LAYTONVILLE 1101402 | 37059.5588 | 1.2901 | 615 | 23.0277 | 12696.2928 | 208.2806 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7948 | 12 | 0.0055833 | 152271101 | WISE 1101 | WISE 11011404 | 1996.1981 | 0.066999 | 1467 | 1.2404 | 12697.5332 | 208.2136 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5635 | 51 | 0.0055607 | 42251101 | HOPLAND 1101 | HOPLAND 11011100 | 4021.7261 | 0.2836 | 1058 | 2.499 | 12700.0321 | 207.93 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 334 | 19 | 0.0055606 | 42271102 | COTATI 1102 | COTATI 1102464 | 2945.14 | 0.10565 | 1337 | 1.83 | 12701.8622 | 207.8244 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4389 | 31 | 0.0055603 | 43432104 | SILVERADO 2104 | SILVERADO 2104circuit_breaker | 2560.2139 | 0.17237 | 1203 | 1.5908 | 12703.453 | 207.652 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3414 | 370 | 0.0055337 | 42661104 | WILLITS 1104 | WILLITS 110434008 | 36886.2403 | 2.0475 | 488 | 22.92 | 12726.373 | 205.6045 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4643 | 410 | 0.0055194 | 83242111 | MORGAN HILL 2111 | MORGAN HILL 2111XR398 | 59220.7716 | 2.263 | 456 | 36.7981 | 12763.1711 | 203.3415 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4581 | 92 | 0.0055189 | 254061102 | DUNLAP 1102 | DUNLAP 11027849F | 13949.6344 | 0.50774 | 895 | 8.6679 | 12771.839 | 202.8338 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3798 | 144 | 0.0055165 | 152301101 | BONNIE NOOK 1101 | BONNIE NOOK 110186696 | 15534.4182 | 0.79438 | 762 | 9.6526 | 12781.4916 | 202.0394 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8967 | 30 | 0.0055157 | 42011108 | SAN RAFAEL 1108 | SAN RAFAEL 110863598 | 3076.8023 | 0.16547 | 1220 | 1.9118 | 12783.4035 | 201.874 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9343 | 15 | 0.0054903 | 43501103 |  | 701650 | 1191.4526 | 0.082354 | 1409 | 0.74033 | 12784.1438 | 201.7916 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7780 | 49 | 0.0054807 | 43071102 | DUNBAR 1102 | DUNBAR 1102528 | 5365.7106 | 0.26856 | 1079 | 3.3341 | 12787.4779 | 201.5231 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4238 | 293 | 0.0054872 | 153661103 | APPLE HILL 1103 | APPLE HILL 11038412 | 32448.6667 | 1.6077 | 555 | 20.1627 | 12807.6406 | 199.9153 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 4238 | 1 | 0.0029321 | 153661103 | APPLE HILL 1103 | APPLE HILL 11038412 | 32448.6667 | 0.0029321 | 555 | 20.1627 | 12827.8032 | 199.9124 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 7539 | 129 | 0.005458 | 42721103 | SONOMA 1103 | SONOMA 11033052 | 21211.1693 | 0.70408 | 805 | 13.18 | 12840.9832 | 199.2083 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1107 | 138 | 0.0054385 | 182661106 | SAN MIGUEL 1106 | SAN MIGUEL 1106circuit_breaker | 56840.9678 | 0.75051 | 782 | 35.3193 | 12876.3026 | 198.4578 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8732 | 7 | 0.0054186 | 13532109 | LAKEWOOD 2109 | LAKEWOOD 210964992 | 587.7906 | 0.03793 | 1615 | 0.36524 | 12876.6678 | 198.4199 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4497 | 219 | 0.0054134 | 182631107 | SAN LUIS OBISPO 1107 | SAN LUIS OBISPO 1107V02 | 29017.7252 | 1.1855 | 634 | 18.0308 | 12894.6986 | 197.2343 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 589 | 453 | 0.0054111 | 152181102 | FORESTHILL 1102 | FORESTHILL 11022106 | 45220.1977 | 2.4513 | 431 | 28.0985 | 12922.7971 | 194.7831 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4605 | 355 | 0.0053954 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 43569.7992 | 1.9154 | 511 | 27.073 | 12949.8701 | 192.8677 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8242 | 82 | 0.0053843 | 102041104 | NOTRE DAME 1104 | NOTRE DAME 11042408 | 18145.7739 | 0.44151 | 933 | 11.2753 | 12961.1454 | 192.4262 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5846 | 22 | 0.0053788 | 82831109 | MILPITAS 1109 | MILPITAS 1109XR524 | 16623.6103 | 0.11833 | 1299 | 10.3294 | 12971.4748 | 192.3079 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 128 | 94 | 0.0054062 | 42891102 | GEYSERVILLE 1102 | GEYSERVILLE 1102522 | 11530.9091 | 0.50819 | 894 | 7.165 | 12978.6398 | 191.7997 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 128 | 1 | 0.0023496 | 42891102 | GEYSERVILLE 1102 | GEYSERVILLE 1102522 | 11530.9091 | 0.0023496 | 894 | 7.165 | 12985.8047 | 191.7973 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 9742 | 3 | 0.0053485 | 43201102 | STAFFORD 1102 | STAFFORD 1102circuit_breaker | 669.8914 | 0.016045 | 1818 | 0.41625 | 12986.221 | 191.7813 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6849 | 138 | 0.0052869 | 152691104 | HIGGINS 1104 | HIGGINS 1104circuit_breaker | 16734.2321 | 0.72959 | 790 | 10.3982 | 12996.6192 | 191.0517 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1092 | 61 | 0.0052863 | 163781705 | PEORIA 1705 | PEORIA 17056697 | 6657.3541 | 0.32247 | 1009 | 4.1367 | 13000.7558 | 190.7292 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4941 | 65 | 0.0052788 | 43071101 | DUNBAR 1101 | DUNBAR 110147964 | 10130.7271 | 0.34312 | 991 | 6.2949 | 13007.0508 | 190.3861 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2222 | 64 | 0.0052695 | 152701108 | BELL 1108 | BELL 1108circuit_breaker | 6935.3327 | 0.33725 | 998 | 4.3094 | 13011.3602 | 190.0488 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4728 | 154 | 0.0052559 | 163351705 | CURTIS 1705 | CURTIS 1705circuit_breaker | 21100.4775 | 0.80941 | 757 | 13.1112 | 13024.4714 | 189.2394 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2046 | 54 | 0.0052545 | 42031120 | ALTO 1120 | ALTO 11201214 | 5446.0036 | 0.28374 | 1056 | 3.384 | 13027.8554 | 188.9557 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2752 | 23 | 0.0052524 | 14662112 | TASSAJARA 2112 | TASSAJARA 211238868 | 2492.9277 | 0.12081 | 1294 | 1.549 | 13029.4044 | 188.8349 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 926 | 259 | 0.0052515 | 163351703 | CURTIS 1703 | CURTIS 17036064 | 30178.8533 | 1.3601 | 602 | 18.7523 | 13048.1567 | 187.4747 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3291 | 203 | 0.0052213 | 163781705 | PEORIA 1705 | PEORIA 17051834 | 37631.0076 | 1.0599 | 673 | 23.3828 | 13071.5395 | 186.4148 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1793 | 354 | 0.0052026 | 152701108 | BELL 1108 | BELL 11082226 | 38840.6709 | 1.8417 | 520 | 24.1345 | 13095.674 | 184.5731 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1994 | 93 | 0.005194 | 182601102 |  | V56 | 14519.9082 | 0.48304 | 912 | 9.0222 | 13104.6962 | 184.0901 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2835 | 221 | 0.0052051 | 102541101 | VOLTA 1101 | VOLTA 11011596 | 34685.9379 | 1.1503 | 645 | 21.5528 | 13126.2491 | 182.9398 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Coast | 2835 | 1 | 0.001196 | 102541101 | VOLTA 1101 | VOLTA 11011596 | 34685.9379 | 0.001196 | 645 | 21.5528 | 13147.8019 | 182.9386 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Coast | 2675 | 16 | 0.0051697 | 182631104 | SAN LUIS OBISPO 1104 | SAN LUIS OBISPO 1104V10 | 5741.8428 | 0.082715 | 1406 | 3.5678 | 13151.3697 | 182.8558 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5429 | 2 | 0.0051578 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 1103circuit_breaker | 375.8787 | 0.010316 | 1889 | 0.23356 | 13151.6033 | 182.8455 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8885 | 116 | 0.0051496 | 103611101 | WILDWOOD 1101 | WILDWOOD 11011576 | 13123.158 | 0.59736 | 856 | 8.1543 | 13159.7576 | 182.2482 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7936 | 33 | 0.0051299 | 192291121 | CARLOTTA 1121 | CARLOTTA 112142896 | 3183.4592 | 0.16929 | 1213 | 1.9781 | 13161.7357 | 182.0789 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4414 | 11 | 0.0051112 | 14662108 | TASSAJARA 2108 | TASSAJARA 210865438 | 1087.8821 | 0.056223 | 1510 | 0.67598 | 13162.4117 | 182.0227 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7247 | 57 | 0.0050747 | 102911102 | WYANDOTTE 1102 | WYANDOTTE 110213044 | 6256.4266 | 0.28926 | 1051 | 3.8876 | 13166.2993 | 181.7334 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5717 | 273 | 0.0050692 | 183052113 | TEMPLETON 2113 | TEMPLETON 2113A10 | 49852.2593 | 1.3839 | 597 | 30.9767 | 13197.276 | 180.3495 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4409 | 116 | 0.0050679 | 43411101 | CALPELLA 1101 | CALPELLA 1101circuit_breaker | 17245.9403 | 0.58788 | 862 | 10.7161 | 13207.9922 | 179.7616 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8669 | 57 | 0.0050676 | 43371102 | LAKEVILLE 1102 | LAKEVILLE 110287432 | 15489.4062 | 0.28885 | 1052 | 9.6247 | 13217.6168 | 179.4728 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7229 | 20 | 0.0050637 | 153652108 | SHINGLE SPRINGS 2108 | SHINGLE SPRINGS 2108circuit_breaker | 2376.1029 | 0.10127 | 1349 | 1.4764 | 13219.0933 | 179.3715 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8114 | 97 | 0.0049987 | 42861101 | ANNAPOLIS 1101 | ANNAPOLIS 1101608 | 28636.0357 | 0.48487 | 911 | 17.7936 | 13236.8869 | 178.8866 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2473 | 54 | 0.0049965 | 163341103 | CLAY 1103 | CLAY 110334338 | 14279.384 | 0.26981 | 1078 | 8.8728 | 13245.7597 | 178.6168 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4387 | 30 | 0.0049874 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210511010 | 3577.8936 | 0.14962 | 1246 | 2.2232 | 13247.9829 | 178.4672 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9262 | 4 | 0.0049535 | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110346860 | 1140.2586 | 0.019814 | 1769 | 0.70852 | 13248.6914 | 178.4474 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1923 | 113 | 0.0049435 | 163351704 | CURTIS 1704 | CURTIS 170411290 | 12662.0411 | 0.55861 | 870 | 7.8678 | 13256.5592 | 177.8888 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9040 | 229 | 0.0049372 | 42681102 | LAYTONVILLE 1102 | LAYTONVILLE 1102682 | 23844.5349 | 1.1306 | 654 | 14.8163 | 13271.3755 | 176.7581 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3469 | 282 | 0.0049372 | 192171101 | WILLOW CREEK 1101 | WILLOW CREEK 11014904 | 29923.3138 | 1.3923 | 594 | 18.5935 | 13289.969 | 175.3659 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 984 | 5 | 0.0049303 | 42151111 | SANTA ROSA A 1111 | SANTA ROSA A 1111circuit_breaker | 423.6161 | 0.024652 | 1724 | 0.26322 | 13290.2322 | 175.3412 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7013 | 239 | 0.0049131 | 43432105 | SILVERADO 2105 | SILVERADO 2105658898 | 27768.6234 | 1.1742 | 638 | 17.2546 | 13307.4868 | 174.167 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7623 | 10 | 0.004906 | 83182107 | LLAGAS 2107 | LLAGAS 2107XR178 | 1344.6176 | 0.04906 | 1546 | 0.83551 | 13308.3223 | 174.1179 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1215 | 517 | 0.0048935 | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | 55423.1935 | 2.53 | 423 | 34.4384 | 13342.7607 | 171.5879 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5420 | 213 | 0.0048752 | 42091101 | MIRABEL 1101 | MIRABEL 1101298 | 20135.0832 | 1.0384 | 680 | 12.5114 | 13355.2721 | 170.5495 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3296 | 330 | 0.0048308 | 102541102 | VOLTA 1102 | VOLTA 11021646 | 37561.3918 | 1.5942 | 556 | 23.3396 | 13378.6116 | 168.9554 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3803 | 66 | 0.0048275 | 163781705 | PEORIA 1705 | PEORIA 170510580 | 11664.5509 | 0.31862 | 1011 | 7.248 | 13385.8596 | 168.6367 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5880 | 32 | 0.0048125 | 192381102 | EEL RIVER 1102 | EEL RIVER 11024814 | 43150.0728 | 0.154 | 1237 | 26.8122 | 13412.6718 | 168.4827 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6605 | 3 | 0.0048076 | 163881101 | IONE 1101 | IONE 1101circuit_breaker | 1810.1911 | 0.014423 | 1838 | 1.1248 | 13413.7966 | 168.4683 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5445 | 4 | 0.0048044 | 42141102 | CLEAR LAKE 1102 | CLEAR LAKE 11024708 | 312.1287 | 0.019218 | 1773 | 0.19395 | 13413.9906 | 168.4491 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3964 | 88 | 0.004802 | 103601101 | WHITMORE 1101 | WHITMORE 1101circuit_breaker | 9527.4078 | 0.42258 | 941 | 5.9201 | 13419.9106 | 168.0265 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5873 | 9 | 0.0047857 | 103021101 | GANSNER 1101 | GANSNER 110137550 | 1056.3754 | 0.043071 | 1591 | 0.6564 | 13420.5671 | 167.9834 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2618 | 168 | 0.0047763 | 163341103 | CLAY 1103 | CLAY 11031230 | 24532.2816 | 0.80242 | 759 | 15.2436 | 13435.8107 | 167.181 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 432 | 148 | 0.0047581 | 152691110 | HIGGINS 1110 | HIGGINS 1110circuit_breaker | 15857.3316 | 0.70421 | 804 | 9.8533 | 13445.664 | 166.4768 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4466 | 241 | 0.0047299 | 42601102 | PHILO 1102 | PHILO 1102928 | 22042.0965 | 1.1399 | 648 | 13.6963 | 13459.3603 | 165.3369 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2395 | 96 | 0.0047155 | 43311102 | KONOCTI 1102 | KONOCTI 1102532 | 15232.9913 | 0.45268 | 929 | 9.4653 | 13468.8256 | 164.8842 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5056 | 47 | 0.0046946 | 43182103 | BELLEVUE 2103 | BELLEVUE 2103648 | 5275.9485 | 0.22065 | 1135 | 3.2783 | 13472.104 | 164.6636 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8169 | 15 | 0.0046848 | 42271102 | COTATI 1102 | COTATI 1102462 | 4359.8054 | 0.070272 | 1449 | 2.7091 | 13474.813 | 164.5933 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4720 | 17 | 0.0046583 | 14241101 | SUNOL 1101 | SUNOL 1101MR196 | 3630.319 | 0.079191 | 1422 | 2.2558 | 13477.0688 | 164.5141 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2312 | 304 | 0.0046373 | 163541102 | OLETA 1102 | OLETA 11021204 | 39941.6187 | 1.4097 | 590 | 24.8186 | 13501.8874 | 163.1044 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4334 | 154 | 0.0046627 | 152691104 | HIGGINS 1104 | HIGGINS 11041006 | 16662.2327 | 0.71805 | 797 | 10.3534 | 13512.2408 | 162.3863 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 4334 | 1 | 9.1091e-06 | 152691104 | HIGGINS 1104 | HIGGINS 11041006 | 16662.2327 | 9.1091e-06 | 797 | 10.3534 | 13522.5942 | 162.3863 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Coast | 3035 | 65 | 0.0046321 | 182541103 | ATASCADERO 1103 | ATASCADERO 1103circuit_breaker | 11975.6869 | 0.30109 | 1038 | 7.4413 | 13530.0356 | 162.0852 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8121 | 13 | 0.0046288 | 182681101 | ZACA 1101 | ZACA 1101Y72 | 8576.3267 | 0.060174 | 1492 | 5.3291 | 13535.3646 | 162.0251 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5608 | 8 | 0.0046285 | 43361103 | HIGHLANDS 1103 | HIGHLANDS 11034630 | 963.0506 | 0.037028 | 1624 | 0.59841 | 13535.9631 | 161.988 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6701 | 216 | 0.0046273 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21011180 | 20702.9508 | 0.9995 | 695 | 12.8642 | 13548.8273 | 160.9885 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 788 | 164 | 0.0045876 | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101806 | 19005.4498 | 0.75237 | 780 | 11.8094 | 13560.6367 | 160.2362 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 882 | 40 | 0.0045467 | 42271105 | COTATI 1105 | COTATI 11055156 | 7460.4725 | 0.18187 | 1190 | 4.6357 | 13565.2724 | 160.0543 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4514 | 64 | 0.0056035 | 163541102 | OLETA 1102 | OLETA 110241396 | 10921.5489 | 0.35863 | 983 | 6.7863 | 13572.0588 | 159.6957 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Sierra | 4514 | 15 | 1.0112e-05 | 163541102 | OLETA 1102 | OLETA 110241396 | 10921.5489 | 0.00015168 | 983 | 6.7863 | 13578.8451 | 159.6955 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 8624 | 41 | 0.0045155 | 42011108 | SAN RAFAEL 1108 | SAN RAFAEL 11081250 | 5757.8877 | 0.18514 | 1185 | 3.5778 | 13582.4229 | 159.5104 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5134 | 1 | 0.0045132 | 42631108 | PETALUMA C 1108 | PETALUMA C 1108632 | 23698.3277 | 0.0045132 | 2013 | 14.7255 | 13597.1483 | 159.5059 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3987 | 51 | 0.0044898 | 163011101 | MARTELL 1101 | MARTELL 1101circuit_breaker | 8464.9135 | 0.22898 | 1122 | 5.2599 | 13602.4082 | 159.2769 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 365 | 103 | 0.004488 | 163351701 | CURTIS 1701 | CURTIS 1701circuit_breaker | 13323.4289 | 0.46227 | 924 | 8.2788 | 13610.687 | 158.8146 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7057 | 173 | 0.0044571 | 183052113 | TEMPLETON 2113 | TEMPLETON 2113A12 | 65018.3777 | 0.77108 | 775 | 40.4005 | 13651.0875 | 158.0435 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6237 | 205 | 0.0044538 | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 11014786 | 28957.9323 | 0.91303 | 725 | 17.9936 | 13669.0811 | 157.1305 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7850 | 33 | 0.0044423 | 163201102 | WEST POINT 1102 | WEST POINT 110272036 | 3794.583 | 0.1466 | 1251 | 2.3578 | 13671.439 | 156.9839 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4321 | 170 | 0.004437 | 182601104 | OCEANO 1104 | OCEANO 1104Q06 | 19967.3254 | 0.75429 | 779 | 12.4071 | 13683.8461 | 156.2296 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8923 | 147 | 0.0044131 | 192171103 | WILLOW CREEK 1103 | WILLOW CREEK 11033090 | 16560.5655 | 0.64873 | 835 | 10.2903 | 13694.1363 | 155.5809 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7477 | 20 | 0.0044052 | 43381101 | POINT ARENA 1101 | POINT ARENA 110183354 | 8260.8147 | 0.088104 | 1384 | 5.133 | 13699.2694 | 155.4928 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2785 | 141 | 0.0043948 | 163011103 | MARTELL 1103 | MARTELL 11033152 | 27174.8741 | 0.61966 | 844 | 16.8857 | 13716.1551 | 154.8731 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1888 | 258 | 0.0043945 | 152101102 | ALLEGHANY 1102 | ALLEGHANY 1102circuit_breaker | 29167.4333 | 1.1338 | 651 | 18.1238 | 13734.2788 | 153.7393 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 256 | 108 | 0.004377 | 152481106 | BRUNSWICK 1106 | BRUNSWICK 11067099 | 12185.6359 | 0.47272 | 918 | 7.5718 | 13741.8506 | 153.2666 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5452 | 36 | 0.0043667 | 162991102 | CORRAL 1102 | CORRAL 110214028 | 5856.3944 | 0.1572 | 1230 | 3.639 | 13745.4896 | 153.1094 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 208 | 186 | 0.0043642 | 153661103 | APPLE HILL 1103 | APPLE HILL 110313312 | 19652.8137 | 0.81174 | 755 | 12.2117 | 13757.7013 | 152.2977 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5597 | 283 | 0.0043257 | 183052110 | TEMPLETON 2110 | TEMPLETON 2110N32 | 46049.4952 | 1.2242 | 624 | 28.6138 | 13786.3152 | 151.0735 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 156 | 476 | 0.0043136 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21011346 | 49477.6546 | 2.0533 | 486 | 30.744 | 13817.0591 | 149.0203 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 457 | 87 | 0.0042722 | 42571102 | MOLINO 1102 | MOLINO 110251788 | 9018.9359 | 0.37168 | 974 | 5.6041 | 13822.6632 | 148.6486 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3850 | 204 | 0.0042368 | 153741101 | DOBBINS 1101 | DOBBINS 11015202 | 26082.7071 | 0.86432 | 740 | 16.207 | 13838.8703 | 147.7843 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3118 | 235 | 0.0042313 | 43471101 | PENNGROVE 1101 | PENNGROVE 1101170 | 31125.6451 | 0.99434 | 696 | 19.3406 | 13858.2108 | 146.7899 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3742 | 263 | 0.0042081 | 103561101 | STILLWATER 1101 | STILLWATER 11011320 | 31197.3185 | 1.1067 | 658 | 19.3851 | 13877.596 | 145.6832 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6423 | 154 | 0.0042079 | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110576498 | 23931.4188 | 0.64802 | 836 | 14.8703 | 13892.4662 | 145.0352 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3498 | 169 | 0.0042048 | 42011108 | SAN RAFAEL 1108 | SAN RAFAEL 1108516 | 17633.1443 | 0.71062 | 802 | 10.9567 | 13903.423 | 144.3246 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6140 | 142 | 0.0041839 | 103031102 | ORO FINO 1102 | ORO FINO 11022040 | 14724.8662 | 0.59411 | 860 | 9.1496 | 13912.5726 | 143.7304 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1432 | 159 | 0.0041778 | 103401102 | GIRVAN 1102 | GIRVAN 11029012 | 25756.1785 | 0.66427 | 826 | 16.0041 | 13928.5767 | 143.0662 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2372 | 46 | 0.0041778 | 254452101 | MARIPOSA 2101 | MARIPOSA 210190180 | 7283.0829 | 0.19218 | 1175 | 4.5255 | 13933.1022 | 142.874 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 883 | 242 | 0.004173 | 163761704 | RACETRACK 1704 | RACETRACK 170455798 | 37898.11 | 1.0099 | 689 | 23.5488 | 13956.651 | 141.8641 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6892 | 145 | 0.004102 | 163751102 | PINE GROVE 1102 | PINE GROVE 110283098 | 13034.6629 | 0.5948 | 859 | 8.0994 | 13964.7504 | 141.2693 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4034 | 34 | 0.0040704 | 42771114 | UKIAH 1114 | UKIAH 1114528 | 4515.409 | 0.13839 | 1269 | 2.8057 | 13967.5561 | 141.1309 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2508 | 299 | 0.0040668 | 153081110 | PLACERVILLE 1110 | PLACERVILLE 111019582 | 35889.5226 | 1.216 | 628 | 22.3007 | 13989.8568 | 139.915 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8139 | 99 | 0.0040598 | 42571102 | MOLINO 1102 | MOLINO 11026917 | 11483.727 | 0.40192 | 957 | 7.1357 | 13996.9925 | 139.5131 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8644 | 38 | 0.0040576 | 182611103 | PASO ROBLES 1103 | PASO ROBLES 1103N52 | 10495.5857 | 0.15419 | 1234 | 6.5217 | 14003.5141 | 139.3589 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2193 | 332 | 0.0040474 | 42571102 | MOLINO 1102 | MOLINO 1102318 | 31101.718 | 1.3437 | 605 | 19.3257 | 14022.8398 | 138.0151 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6650 | 83 | 0.0040471 | 163541101 | OLETA 1101 | OLETA 110151740 | 20448.965 | 0.33591 | 999 | 12.7064 | 14035.5462 | 137.6792 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5862 | 20 | 0.0040003 | 43411102 | CALPELLA 1102 | CALPELLA 1102circuit_breaker | 3000.9026 | 0.080005 | 1417 | 1.8647 | 14037.4109 | 137.5992 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3041 | 1 | 0.0039947 | 182981102 | JOLON 1102 | JOLON 11027070 | 6723.3881 | 0.0039947 | 2024 | 4.1777 | 14041.5886 | 137.5952 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9446 | 8 | 0.0039945 | 43432102 | SILVERADO 2102 | SILVERADO 2102circuit_breaker | 345.0876 | 0.031956 | 1661 | 0.21443 | 14041.803 | 137.5633 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3340 | 233 | 0.0039877 | 152691104 | HIGGINS 1104 | HIGGINS 1104324510 | 20001.4265 | 0.92912 | 721 | 12.4283 | 14054.2313 | 136.6341 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8293 | 51 | 0.0039502 | 102911105 | WYANDOTTE 1105 | WYANDOTTE 1105circuit_breaker | 15173.6855 | 0.20146 | 1156 | 9.4285 | 14063.6598 | 136.4327 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7336 | 103 | 0.0039498 | 163451702 | FROGTOWN 1702 | FROGTOWN 17027134 | 28875.1403 | 0.40683 | 956 | 17.9422 | 14081.602 | 136.0258 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3521 | 119 | 0.0039437 | 182601104 | OCEANO 1104 | OCEANO 1104V38 | 18252.5164 | 0.46929 | 920 | 11.3416 | 14092.9436 | 135.5566 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3747 | 125 | 0.0039417 | 254601103 | SAND CREEK 1103 | SAND CREEK 11037070 | 28595.1882 | 0.49271 | 904 | 17.7682 | 14110.7118 | 135.0638 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8520 | 41 | 0.0039331 | 182631107 | SAN LUIS OBISPO 1107 | SAN LUIS OBISPO 1107V62 | 10856.7862 | 0.16126 | 1227 | 6.7461 | 14117.4579 | 134.9026 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5959 | 3 | 0.0039291 | 42011108 | SAN RAFAEL 1108 | SAN RAFAEL 11081247 | 414.4526 | 0.011787 | 1868 | 0.25753 | 14117.7154 | 134.8908 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7100 | 89 | 0.0039165 | 14232108 | SAN RAMON 2108 | SAN RAMON 210853732 | 12570.9742 | 0.34857 | 988 | 7.8112 | 14125.5267 | 134.5422 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2548 | 138 | 0.0038943 | 102541102 | VOLTA 1102 | VOLTA 11021504 | 13357.6434 | 0.53742 | 884 | 8.3001 | 14133.8267 | 134.0048 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8805 | 42 | 0.0038911 | 163341103 | CLAY 1103 | CLAY 110359714 | 7453.2846 | 0.16343 | 1224 | 4.6313 | 14138.458 | 133.8414 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7781 | 2 | 0.0038792 | 253642104 | POSO MOUNTAIN 2104 | POSO MOUNTAIN 210448268 | 7515.6606 | 0.0077584 | 1942 | 4.67 | 14143.128 | 133.8336 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1955 | 377 | 0.0038488 | 162161101 | ELECTRA 1101 | ELECTRA 1101circuit_breaker | 51915.3729 | 1.451 | 580 | 32.2587 | 14175.3867 | 132.3826 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1073 | 228 | 0.0038346 | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 1101764 | 23872.6753 | 0.8743 | 735 | 14.8338 | 14190.2205 | 131.5083 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2182 | 41 | 0.0069651 | 42271103 | COTATI 1103 | COTATI 1103148 | 23990.7662 | 0.28557 | 1034 | 14.9072 | 14205.1277 | 131.2227 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 2182 | 38 | 0.0004463 | 42271103 | COTATI 1103 | COTATI 1103148 | 23990.7662 | 0.01696 | 1034 | 14.9072 | 14220.0348 | 131.2058 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 513 | 21 | 0.0038233 | 42811111 | MONTE RIO 1111 | MONTE RIO 1111292 | 22117.1152 | 0.08029 | 1416 | 13.7429 | 14233.7778 | 131.1255 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 953 | 314 | 0.0038102 | 152481106 | BRUNSWICK 1106 | BRUNSWICK 110651484 | 32219.8738 | 1.1964 | 631 | 20.0205 | 14253.7983 | 129.9291 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2645 | 1 | 0.00381 | 152561106 | PENRYN 1106 | PENRYN 1106circuit_breaker | 70.2637 | 0.00381 | 2033 | 0.04366 | 14253.8419 | 129.9253 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5451 | 122 | 0.0037984 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21012422 | 13951.5772 | 0.46341 | 922 | 8.6691 | 14262.511 | 129.4619 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3652 | 205 | 0.0037979 | 152181101 | FORESTHILL 1101 | FORESTHILL 110150486 | 18756.9603 | 0.77858 | 767 | 11.655 | 14274.1661 | 128.6833 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2283 | 306 | 0.0037933 | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 55502.9271 | 1.1607 | 642 | 34.4879 | 14308.654 | 127.5225 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 50 | 41 | 0.0037804 | 43071102 | DUNBAR 1102 | DUNBAR 1102448 | 3456.1423 | 0.155 | 1232 | 2.1475 | 14310.8015 | 127.3675 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5051 | 105 | 0.0037779 | 103191101 | BANGOR 1101 | BANGOR 11011806 | 13609.8138 | 0.39668 | 961 | 8.4567 | 14319.2583 | 126.9709 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8418 | 159 | 0.0037739 | 183052110 | TEMPLETON 2110 | TEMPLETON 2110N30 | 32940.3855 | 0.60006 | 853 | 20.4682 | 14339.7265 | 126.3708 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5825 | 71 | 0.0037707 | 43321103 | RINCON 1103 | RINCON 1103198 | 10388.1795 | 0.26772 | 1080 | 6.4549 | 14346.1814 | 126.1031 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 293 | 45 | 0.0037478 | 14662112 | TASSAJARA 2112 | TASSAJARA 2112D514R | 4376.3944 | 0.16865 | 1215 | 2.7194 | 14348.9007 | 125.9344 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 9639 | 11 | 0.0037287 | 152691107 | HIGGINS 1107 | HIGGINS 1107746082 | 1365.375 | 0.041016 | 1597 | 0.8484 | 14349.7491 | 125.8934 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5573 | 330 | 0.0037235 | 252531103 | SAN JOAQUIN #3 1103 | SAN JOAQUIN #3 11035100 | 42249.6443 | 1.2288 | 620 | 26.2527 | 14376.0018 | 124.6647 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2315 | 36 | 0.0037177 | 42291101 | OLEMA 1101 | OLEMA 1101320 | 5064.1889 | 0.13384 | 1271 | 3.1467 | 14379.1486 | 124.5308 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8018 | 29 | 0.0037007 | 42271102 | COTATI 1102 | COTATI 1102282 | 4768.5619 | 0.10732 | 1334 | 2.963 | 14382.1116 | 124.4235 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 570 | 108 | 0.003681 | 43381101 | POINT ARENA 1101 | POINT ARENA 1101circuit_breaker | 18269.3482 | 0.39755 | 960 | 11.352 | 14393.4637 | 124.026 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1867 | 195 | 0.0036482 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21011184 | 18770.5875 | 0.7114 | 801 | 11.6635 | 14405.1272 | 123.3146 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7128 | 23 | 0.0036476 | 42891102 | GEYSERVILLE 1102 | GEYSERVILLE 1102circuit_breaker | 3579.9474 | 0.083896 | 1401 | 2.2245 | 14407.3516 | 123.2307 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9200 | 21 | 0.0036362 | 102211103 | BUCKS CREEK 1103 | BUCKS CREEK 1103circuit_breaker | 3699.7995 | 0.076361 | 1430 | 2.2989 | 14409.6506 | 123.1543 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5124 | 12 | 0.0036227 | 252921108 | STONE CORRAL 1108 | STONE CORRAL 11087100 | 3682.723 | 0.043472 | 1586 | 2.2883 | 14411.9389 | 123.1108 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2816 | 581 | 0.0035928 | 183052110 | TEMPLETON 2110 | TEMPLETON 2110R90 | 106123.5164 | 2.0874 | 481 | 65.9421 | 14477.881 | 121.0234 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3235 | 79 | 0.0035783 | 103751101 | BIG BEND 1101 | BIG BEND 1101180398 | 9616.0055 | 0.28269 | 1059 | 5.9751 | 14483.8561 | 120.7407 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1959 | 137 | 0.003575 | 43432103 | SILVERADO 2103 | SILVERADO 2103circuit_breaker | 18626.4797 | 0.48977 | 905 | 11.574 | 14495.4301 | 120.2509 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1596 | 70 | 0.0035702 | 163341103 | CLAY 1103 | CLAY 11037124 | 15711.1032 | 0.24991 | 1098 | 9.7624 | 14505.1925 | 120.001 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 787 | 211 | 0.0035483 | 182601102 |  | circuit_breaker | 32849.6375 | 0.74869 | 783 | 20.4118 | 14525.6043 | 119.2523 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1805 | 291 | 0.0035458 | 102541102 | VOLTA 1102 | VOLTA 11021650 | 34674.2454 | 1.0318 | 682 | 21.5456 | 14547.1499 | 118.2205 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8095 | 36 | 0.0035418 | 163201102 | WEST POINT 1102 | WEST POINT 1102L3733 | 2820.1267 | 0.1275 | 1282 | 1.7523 | 14548.9022 | 118.093 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9592 | 1 | 0.0035147 | 42861101 | ANNAPOLIS 1101 | ANNAPOLIS 1101circuit_breaker | 1058.7166 | 0.0035147 | 2040 | 0.65786 | 14549.5601 | 118.0895 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 26 | 156 | 0.0034877 | 42951101 | MENDOCINO 1101 | MENDOCINO 1101circuit_breaker | 18680.8862 | 0.54409 | 882 | 11.6078 | 14561.1678 | 117.5454 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6406 | 99 | 0.0034129 | 42771114 | UKIAH 1114 | UKIAH 11143606 | 16376.8546 | 0.33787 | 997 | 10.1761 | 14571.3439 | 117.2075 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6388 | 7 | 0.0034124 | 14052101 | NORTH DUBLIN 2101 | NORTH DUBLIN 2101circuit_breaker | 5815.8712 | 0.023887 | 1732 | 3.6138 | 14574.9577 | 117.1836 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1592 | 15 | 0.0033639 | 182661104 | SAN MIGUEL 1104 | SAN MIGUEL 1104R66 | 11247.2619 | 0.050459 | 1539 | 6.9887 | 14581.9465 | 117.1332 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6550 | 59 | 0.0033558 | 43071103 | DUNBAR 1103 | DUNBAR 11033127 | 14668.3464 | 0.19799 | 1159 | 9.1145 | 14591.061 | 116.9352 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 998 | 565 | 0.0033541 | 153662102 | APPLE HILL 2102 | APPLE HILL 21029722 | 61644.8871 | 1.8951 | 515 | 38.3043 | 14629.3653 | 115.0401 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6572 | 3 | 0.0033473 | 82951102 | EDENVALE 1102 | EDENVALE 1102XR064 | 956.603 | 0.010042 | 1893 | 0.59441 | 14629.9597 | 115.0301 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7934 | 10 | 0.0033432 | 255451102 | CAL WATER 1102 | CAL WATER 1102920714 | 6508.6114 | 0.033432 | 1652 | 4.0443 | 14634.004 | 114.9966 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2254 | 316 | 0.003334 | 162821701 | STANISLAUS 1701 | STANISLAUS 17011812 | 31400.4893 | 1.0536 | 677 | 19.5114 | 14653.5153 | 113.9431 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5899 | 1 | 0.003332 | 182981103 | JOLON 1103 | JOLON 1103circuit_breaker | 18381.2801 | 0.003332 | 2047 | 11.4216 | 14664.9369 | 113.9397 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7050 | 36 | 0.0033193 | 153612109 | CLARKSVILLE 2109 | CLARKSVILLE 21096502 | 3563.6935 | 0.1195 | 1296 | 2.2144 | 14667.1513 | 113.8202 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2055 | 7 | 0.0032953 | 182541103 | ATASCADERO 1103 | ATASCADERO 1103A46 | 983.4741 | 0.023067 | 1736 | 0.6111 | 14667.7624 | 113.7972 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8783 | 128 | 0.0032816 | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 1101585 | 22710.6586 | 0.42004 | 944 | 14.1117 | 14681.8741 | 113.3771 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9247 | 12 | 0.00328 | 103031102 | ORO FINO 1102 | ORO FINO 11022236 | 4120.4561 | 0.03936 | 1609 | 2.5603 | 14684.4345 | 113.3378 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 510 | 31 | 0.0032464 | 43381101 | POINT ARENA 1101 | POINT ARENA 110147952 | 16717.6297 | 0.10064 | 1352 | 10.3879 | 14694.8223 | 113.2371 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 857 | 92 | 0.003245 | 42561107 | FULTON 1107 | FULTON 110777670 | 10408.8422 | 0.29854 | 1044 | 6.4678 | 14701.2901 | 112.9386 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2343 | 555 | 0.0032185 | 152301102 | BONNIE NOOK 1102 | BONNIE NOOK 1102circuit_breaker | 55059.6809 | 1.7863 | 527 | 34.2125 | 14735.5026 | 111.1523 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1103 | 238 | 0.0032131 | 254432102 | COARSEGOLD 2102 | COARSEGOLD 210210040 | 28189.7477 | 0.76472 | 777 | 17.5163 | 14753.0189 | 110.3876 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6326 | 1 | 0.0031997 | 42091102 | MIRABEL 1102 | MIRABEL 11027347 | 1145.4102 | 0.0031997 | 2051 | 0.71172 | 14753.7306 | 110.3844 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1287 | 228 | 0.0031893 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 210192474 | 23834.445 | 0.72716 | 792 | 14.81 | 14768.5406 | 109.6573 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5942 | 24 | 0.0031813 | 103441101 | JESSUP 1101 | JESSUP 11013383 | 1995.2743 | 0.07635 | 1431 | 1.2398 | 14769.7804 | 109.5809 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2053 | 174 | 0.0031698 | 83481110 | STELLING 1110 | STELLING 111060094 | 15898.3782 | 0.55155 | 872 | 9.8788 | 14779.6592 | 109.0294 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2127 | 66 | 0.0031681 | 83531111 | MC KEE 1111 | MC KEE 1111711900 | 14114.2959 | 0.2091 | 1150 | 8.7702 | 14788.4294 | 108.8203 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3741 | 211 | 0.0031648 | 153661104 | APPLE HILL 1104 | APPLE HILL 110412832 | 23528.5139 | 0.66776 | 821 | 14.6199 | 14803.0494 | 108.1525 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3014 | 779 | 0.0031597 | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 80528.8854 | 2.4614 | 429 | 50.0383 | 14853.0877 | 105.6911 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4647 | 259 | 0.0031553 | 153661104 | APPLE HILL 1104 | APPLE HILL 110412842 | 24430.5416 | 0.81722 | 753 | 15.1804 | 14868.2681 | 104.8739 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8723 | 101 | 0.0031515 | 192171102 | WILLOW CREEK 1102 | WILLOW CREEK 1102circuit_breaker | 11718.7349 | 0.3183 | 1013 | 7.2817 | 14875.5498 | 104.5556 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3928 | 96 | 0.0031339 | 42571101 | MOLINO 1101 | MOLINO 11015042 | 9764.6994 | 0.30085 | 1039 | 6.0675 | 14881.6173 | 104.2547 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5422 | 135 | 0.0031226 | 153132105 | NARROWS 2105 | NARROWS 21052426 | 12992.6156 | 0.42154 | 942 | 8.0732 | 14889.6905 | 103.8332 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5266 | 359 | 0.003118 | 152181101 | FORESTHILL 1101 | FORESTHILL 11011802 | 35584.2456 | 1.1194 | 656 | 22.111 | 14911.8015 | 102.7138 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2594 | 777 | 0.0031095 | 153662102 | APPLE HILL 2102 | APPLE HILL 21028372 | 90180.3006 | 2.4161 | 440 | 56.0354 | 14967.837 | 100.2977 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3263 | 77 | 0.0030978 | 102541102 | VOLTA 1102 | VOLTA 110297816 | 8457.2763 | 0.23853 | 1110 | 5.2551 | 14973.0921 | 100.0592 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1850 | 133 | 0.0030892 | 153652110 | SHINGLE SPRINGS 2110 | SHINGLE SPRINGS 211051800 | 14770.4871 | 0.41086 | 953 | 9.178 | 14982.27 | 99.6483 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1254 | 9 | 0.0030858 | 103031102 | ORO FINO 1102 | ORO FINO 11022556 | 10716.6127 | 0.027772 | 1696 | 6.659 | 14988.929 | 99.6205 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 198 | 56 | 0.0030669 | 182731101 | RESERVATION ROAD 1101 | RESERVATION ROAD 1101circuit_breaker | 7957.2831 | 0.17175 | 1206 | 4.9444 | 14993.8734 | 99.4488 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 584 | 11 | 0.0030585 | 192221103 | GARBERVILLE 1103 | GARBERVILLE 1103circuit_breaker | 841.9717 | 0.033644 | 1650 | 0.52318 | 14994.3966 | 99.4152 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2906 | 294 | 0.0030497 | 102971111 | SYCAMORE CREEK 1111 | SYCAMORE CREEK 11112014 | 36180.8061 | 0.89661 | 728 | 22.4817 | 15016.8783 | 98.5185 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3569 | 16 | 0.0030406 | 43471101 | PENNGROVE 1101 | PENNGROVE 1101554 | 1740.0436 | 0.048649 | 1549 | 1.0812 | 15017.9595 | 98.4699 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1879 | 158 | 0.0030404 | 42291101 | OLEMA 1101 | OLEMA 1101416 | 25936.9304 | 0.48038 | 916 | 16.1165 | 15034.076 | 97.9895 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8904 | 46 | 0.0030262 | 103721101 | PIT NO 1 1101 | PIT NO 1 1101circuit_breaker | 10477.1422 | 0.13921 | 1267 | 6.5102 | 15040.5862 | 97.8503 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5033 | 46 | 0.0031093 | 163541102 | OLETA 1102 | OLETA 11022642 | 7497.8568 | 0.14303 | 1253 | 4.659 | 15045.2451 | 97.7073 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Sierra | 5033 | 2 | 0.0010588 | 163541102 | OLETA 1102 | OLETA 11022642 | 7497.8568 | 0.0021177 | 1253 | 4.659 | 15049.9041 | 97.7052 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Sierra | 3416 | 361 | 0.0029991 | 153662102 | APPLE HILL 2102 | APPLE HILL 21027502 | 37014.7956 | 1.0827 | 669 | 22.9999 | 15072.904 | 96.6225 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1730 | 72 | 0.0029928 | 14502108 | VINEYARD 2108 | VINEYARD 2108MR172 | 8979.3146 | 0.21548 | 1144 | 5.5795 | 15078.4835 | 96.407 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1082 | 319 | 0.0029914 | 192401101 | HOOPA 1101 | HOOPA 110137202 | 39996.9216 | 0.95424 | 713 | 24.8529 | 15103.3364 | 95.4528 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7415 | 32 | 0.0029901 | 83182101 | LLAGAS 2101 | LLAGAS 2101XR586 | 7394.3416 | 0.095685 | 1361 | 4.5946 | 15107.931 | 95.3571 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1058 | 83 | 0.002961 | 103491101 | MC ARTHUR 1101 | MC ARTHUR 11011492 | 15180.4428 | 0.24576 | 1102 | 9.4327 | 15117.3637 | 95.1113 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5327 | 285 | 0.0029463 | 103751101 | BIG BEND 1101 | BIG BEND 1101641808 | 46054.2939 | 0.8397 | 748 | 28.6168 | 15145.9805 | 94.2716 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9122 | 18 | 0.0029241 | 103401101 | GIRVAN 1101 | GIRVAN 1101circuit_breaker | 2142.1974 | 0.052634 | 1528 | 1.3311 | 15147.3116 | 94.219 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7283 | 265 | 0.0029189 | 42601102 | PHILO 1102 | PHILO 11022600 | 32189.254 | 0.7735 | 774 | 20.0015 | 15167.3131 | 93.4455 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8014 | 83 | 0.0029157 | 103732101 | PIT NO 3 2101 | PIT NO 3 21011482 | 19365.2645 | 0.242 | 1106 | 12.033 | 15179.3461 | 93.2035 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3504 | 36 | 0.0028891 | 42091101 | MIRABEL 1101 | MIRABEL 1101circuit_breaker | 3875.2533 | 0.10401 | 1342 | 2.408 | 15181.7541 | 93.0995 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4557 | 474 | 0.0028728 | 163751102 | PINE GROVE 1102 | PINE GROVE 11023168 | 48743.192 | 1.3617 | 601 | 30.2876 | 15212.0417 | 91.7378 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5973 | 40 | 0.0028593 | 42571101 | MOLINO 1101 | MOLINO 1101152 | 3850.1683 | 0.11437 | 1309 | 2.3924 | 15214.4341 | 91.6234 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9730 | 2 | 0.0028588 | 42871101 | UPPER LAKE 1101 | UPPER LAKE 1101circuit_breaker | 1791.2622 | 0.0057175 | 1979 | 1.113 | 15215.5471 | 91.6177 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4858 | 234 | 0.0028438 | 152301101 | BONNIE NOOK 1101 | BONNIE NOOK 1101circuit_breaker | 23724.1813 | 0.66546 | 824 | 14.7415 | 15230.2886 | 90.9522 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3846 | 21 | 0.0028366 | 182681101 | ZACA 1101 | ZACA 1101Y70 | 8678.0315 | 0.05957 | 1496 | 5.3923 | 15235.6809 | 90.8927 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7820 | 44 | 0.0028362 | 14402108 | LAS POSITAS 2108 | LAS POSITAS 2108MR182 | 10768.7759 | 0.12479 | 1290 | 6.6914 | 15242.3723 | 90.7679 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1085 | 292 | 0.0028299 | 152481104 | BRUNSWICK 1104 | BRUNSWICK 11042112 | 30961.8119 | 0.82634 | 751 | 19.2388 | 15261.6111 | 89.9415 | 18.3706 | 0.82521 | 1 | #N/A | 89.9415 | #N/A
Bay Area | 7844 | 68 | 0.0028233 | 42271103 | COTATI 1103 | COTATI 110387402 | 18214.2492 | 0.19198 | 1176 | 11.3178 | 15272.9289 | 89.7495 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6694 | 3 | 0.0028166 | 42771111 | UKIAH 1111 | UKIAH 11112504 | 52.248 | 0.0084498 | 1930 | 0.032465 | 15272.9614 | 89.7411 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2636 | 108 | 0.0028133 | 14232107 | SAN RAMON 2107 | SAN RAMON 2107MR284 | 23158.7135 | 0.30384 | 1031 | 14.3902 | 15287.3515 | 89.4372 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7276 | 17 | 0.0028085 | 43211101 | HARTLEY 1101 | HARTLEY 1101circuit_breaker | 2204.3614 | 0.047745 | 1560 | 1.3697 | 15288.7212 | 89.3895 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2432 | 1 | 0.0029335 | 42151104 | SANTA ROSA A 1104 | SANTA ROSA A 1104220 | 15355.5551 | 0.0029335 | 1097 | 9.5415 | 15298.2627 | 89.3866 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 2432 | 89 | 0.0027758 | 42151104 | SANTA ROSA A 1104 | SANTA ROSA A 1104220 | 15355.5551 | 0.24705 | 1097 | 9.5415 | 15307.8042 | 89.1395 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 218 | 110 | 0.002764 | 43071102 | DUNBAR 1102 | DUNBAR 1102circuit_breaker | 11754.0323 | 0.30404 | 1030 | 7.3036 | 15315.1078 | 88.8355 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 850 | 106 | 0.0027591 | 163781704 | PEORIA 1704 | PEORIA 170459596 | 32203.8416 | 0.29247 | 1048 | 20.0105 | 15335.1184 | 88.543 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7999 | 52 | 0.0027405 | 43051101 | MONTICELLO 1101 | MONTICELLO 1101654 | 12946.7956 | 0.14251 | 1257 | 8.0448 | 15343.1631 | 88.4005 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2815 | 17 | 0.0027246 | 42571102 | MOLINO 1102 | MOLINO 1102344 | 1463.3176 | 0.046318 | 1572 | 0.90926 | 15344.0724 | 88.3542 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7812 | 113 | 0.0027135 | 83242105 | MORGAN HILL 2105 | MORGAN HILL 2105XR268 | 12821.0297 | 0.30662 | 1027 | 7.9666 | 15352.039 | 88.0476 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 600 | 530 | 0.0027117 | 152261106 | DIAMOND SPRINGS 1106 | DIAMOND SPRINGS 11062100 | 62659.5156 | 1.4372 | 584 | 38.9348 | 15390.9738 | 86.6103 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9157 | 67 | 0.0027114 | 43071101 | DUNBAR 1101 | DUNBAR 1101343 | 7034.2123 | 0.18167 | 1191 | 4.3709 | 15395.3447 | 86.4287 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2655 | 526 | 0.0027079 | 163751102 | PINE GROVE 1102 | PINE GROVE 11023172 | 59226.0308 | 1.4243 | 586 | 36.8013 | 15432.146 | 85.0043 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8617 | 1 | 0.0026979 | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110135874 | 440.1765 | 0.0026979 | 2063 | 0.27351 | 15432.4195 | 85.0016 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 150 | 14 | 0.0026951 | 192151132 | NEWBURG 1132 | NEWBURG 11322074 | 1527.0717 | 0.037732 | 1619 | 0.94888 | 15433.3684 | 84.9639 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 324 | 452 | 0.0026949 | 163201102 | WEST POINT 1102 | WEST POINT 11024790 | 53036.5916 | 1.2181 | 627 | 32.9554 | 15466.3238 | 83.7458 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5835 | 251 | 0.0026935 | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210981390 | 30296.9721 | 0.67607 | 819 | 18.8257 | 15485.1495 | 83.0697 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4817 | 123 | 0.002692 | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119612 | 14689.1645 | 0.33111 | 1002 | 9.1274 | 15494.2769 | 82.7386 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 9421 | 73 | 0.0026902 | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101808 | 9882.4147 | 0.19639 | 1167 | 6.1406 | 15500.4175 | 82.5422 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7173 | 106 | 0.0026766 | 42681101 | LAYTONVILLE 1101 | LAYTONVILLE 110189606 | 18642.295 | 0.28372 | 1057 | 11.5838 | 15512.0013 | 82.2585 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 532 | 11 | 0.0026625 | 183052113 | TEMPLETON 2113 | TEMPLETON 2113R82 | 60266.4888 | 0.029288 | 1683 | 37.4478 | 15549.4492 | 82.2292 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 784 | 81 | 0.0026592 | 152691107 | HIGGINS 1107 | HIGGINS 1107circuit_breaker | 8142.9425 | 0.2154 | 1146 | 5.0598 | 15554.509 | 82.0138 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9498 | 40 | 0.0026529 | 42261101 | BOLINAS 1101 | BOLINAS 1101806 | 4898.4533 | 0.10612 | 1336 | 3.0438 | 15557.5527 | 81.9077 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1316 | 165 | 0.0026527 | 254151101 | AUBERRY 1101 | AUBERRY 1101R2838 | 32678.392 | 0.4377 | 935 | 20.3054 | 15577.8581 | 81.47 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1854 | 3 | 0.0026389 | 42021112 | NAPA 1112 | NAPA 1112circuit_breaker | 272.3504 | 0.0079168 | 1940 | 0.16923 | 15578.0273 | 81.4621 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9369 | 27 | 0.0026378 | 42811113 | MONTE RIO 1113 | MONTE RIO 1113678 | 2967.1836 | 0.07122 | 1447 | 1.8437 | 15579.8711 | 81.3909 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3908 | 188 | 0.0026357 | 254432102 | COARSEGOLD 2102 | COARSEGOLD 21025380 | 22745.3926 | 0.49551 | 901 | 14.1333 | 15594.0044 | 80.8954 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6352 | 5 | 0.0026253 | 163341101 | CLAY 1101 | CLAY 1101circuit_breaker | 707.4258 | 0.013126 | 1850 | 0.43957 | 15594.444 | 80.8823 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2700 | 303 | 0.0026155 | 103601101 | WHITMORE 1101 | WHITMORE 110145262 | 46035.1045 | 0.79248 | 763 | 28.6049 | 15623.0489 | 80.0898 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1211 | 273 | 0.0026154 | 254421103 | OAKHURST 1103 | OAKHURST 11035480 | 27507.5877 | 0.71402 | 799 | 17.0924 | 15640.1413 | 79.3758 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8168 | 206 | 0.0026009 | 82841102 | BIG BASIN 1102 | BIG BASIN 110211062 | 21172.9967 | 0.53578 | 886 | 13.1563 | 15653.2976 | 78.84 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1346 | 241 | 0.0025975 | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | 27692.5615 | 0.62601 | 843 | 17.2074 | 15670.5049 | 78.214 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 519 | 451 | 0.0025958 | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210692012 | 46683.5024 | 1.1707 | 639 | 29.0078 | 15699.5127 | 77.0433 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6664 | 119 | 0.002594 | 192171103 | WILLOW CREEK 1103 | WILLOW CREEK 11037514 | 13903.8607 | 0.30868 | 1025 | 8.6395 | 15708.1521 | 76.7346 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4265 | 76 | 0.0025849 | 24251101 | WOODSIDE 1101 | WOODSIDE 11011922 | 7077.1681 | 0.19646 | 1166 | 4.3975 | 15712.5497 | 76.5381 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6109 | 268 | 0.0025736 | 153082106 | PLACERVILLE 2106 | PLACERVILLE 2106935216 | 33799.5586 | 0.68972 | 811 | 21.0021 | 15733.5518 | 75.8484 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4624 | 73 | 0.0025712 | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101circuit_breaker | 6967.0605 | 0.18769 | 1180 | 4.3291 | 15737.8809 | 75.6607 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2817 | 132 | 0.0025415 | 42811113 | MONTE RIO 1113 | MONTE RIO 1113346 | 16237.5238 | 0.33548 | 1000 | 10.0895 | 15747.9704 | 75.3252 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7409 | 94 | 0.0025375 | 24101101 | HALF MOON BAY 1101 | HALF MOON BAY 11012500 | 9460.9126 | 0.23852 | 1111 | 5.8787 | 15753.8491 | 75.0867 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2031 | 77 | 0.0025361 | 163541102 | OLETA 1102 | OLETA 11021228 | 12585.9936 | 0.19528 | 1170 | 7.8206 | 15761.6697 | 74.8914 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1708 | 307 | 0.0025321 | 42761101 | FORT BRAGG A 1101 | FORT BRAGG A 110195294 | 43187.6602 | 0.77737 | 768 | 26.8356 | 15788.5053 | 74.1141 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2368 | 277 | 0.0025239 | 163451702 | FROGTOWN 1702 | FROGTOWN 1702290609 | 29095.2779 | 0.69913 | 808 | 18.079 | 15806.5842 | 73.4149 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5240 | 36 | 0.0025159 | 42091101 | MIRABEL 1101 | MIRABEL 11014859 | 2980.2139 | 0.090574 | 1376 | 1.8518 | 15808.4361 | 73.3244 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8982 | 15 | 0.0025076 | 43351103 | LUCERNE 1103 | LUCERNE 11034200 | 6495.7462 | 0.037615 | 1620 | 4.0363 | 15812.4723 | 73.2868 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7480 | 4 | 0.0025063 | 42721104 | SONOMA 1104 | SONOMA 11045661 | 3397.3315 | 0.010025 | 1896 | 2.111 | 15814.5833 | 73.2767 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7552 | 183 | 0.0025029 | 43321103 | RINCON 1103 | RINCON 1103568 | 20662.4363 | 0.45803 | 927 | 12.839 | 15827.4224 | 72.8187 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9470 | 26 | 0.0024979 | 102541102 | VOLTA 1102 | VOLTA 1102circuit_breaker | 5307.8332 | 0.064946 | 1475 | 3.2981 | 15830.7205 | 72.7538 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7638 | 2 | 0.0024964 | 182391103 | OILFIELDS 1103 | OILFIELDS 1103N62 | 8948.1922 | 0.0049929 | 1997 | 5.5601 | 15836.2806 | 72.7488 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3005 | 333 | 0.0024957 | 152431102 | SHADY GLEN 1102 | SHADY GLEN 1102circuit_breaker | 33414.9149 | 0.83108 | 749 | 20.7631 | 15857.0437 | 71.9177 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2714 | 69 | 0.0024913 | 103311101 | BURNEY 1102 | BURNEY 11021358 | 12955.3272 | 0.1719 | 1205 | 8.0501 | 15865.0938 | 71.7458 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4861 | 32 | 0.0024853 | 42811113 | MONTE RIO 1113 | MONTE RIO 1113180 | 3131.1085 | 0.079529 | 1420 | 1.9456 | 15867.0394 | 71.6663 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2199 | 220 | 0.0024815 | 163351702 | CURTIS 1702 | CURTIS 170247488 | 29796.4907 | 0.54593 | 879 | 18.5147 | 15885.554 | 71.1203 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6524 | 1 | 0.0024798 | 182191101 | SAN ARDO 1101 | SAN ARDO 11017632 | 668.3905 | 0.0024798 | 2077 | 0.41532 | 15885.9693 | 71.1178 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9603 | 74 | 0.0024672 | 192251102 | RIO DELL 1102 | RIO DELL 110275970 | 11373.8899 | 0.18257 | 1188 | 7.0674 | 15893.0367 | 70.9353 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4724 | 58 | 0.0024604 | 182811102 | SISQUOC 1102 | SISQUOC 1102M54 | 30625.2961 | 0.14271 | 1256 | 19.0297 | 15912.0664 | 70.7926 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 964 | 532 | 0.0024588 | 152691110 | HIGGINS 1110 | HIGGINS 11102408 | 57049.967 | 1.3081 | 609 | 35.4492 | 15947.5156 | 69.4845 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8021 | 48 | 0.0024584 | 252192105 | BEAR VALLEY 2105 | BEAR VALLEY 210576694 | 7317.351 | 0.118 | 1301 | 4.5468 | 15952.0624 | 69.3665 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 140 | 321 | 0.0024444 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21011130 | 31854.654 | 0.78465 | 765 | 19.7936 | 15971.856 | 68.5818 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2694 | 6 | 0.0024408 | 13501108 | JARVIS 1108 | JARVIS 1108MR368 | 761.5311 | 0.014645 | 1833 | 0.47319 | 15972.3292 | 68.5672 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1381 | 199 | 0.0024268 | 182541103 | ATASCADERO 1103 | ATASCADERO 1103A16 | 28337.886 | 0.48294 | 914 | 17.6083 | 15989.9375 | 68.0842 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5536 | 135 | 0.0024096 | 102541102 | VOLTA 1102 | VOLTA 11029742 | 14622.5954 | 0.3253 | 1007 | 9.0861 | 15999.0236 | 67.7589 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7441 | 2 | 0.0024066 | 252921110 | STONE CORRAL 1110 | STONE CORRAL 11107784F | 586.0706 | 0.0048132 | 2001 | 0.36417 | 15999.3877 | 67.7541 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4823 | 47 | 0.0024029 | 163201101 | WEST POINT 1101 | WEST POINT 110136674 | 15191.9661 | 0.11294 | 1314 | 9.4398 | 16008.8276 | 67.6412 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1813 | 133 | 0.002399 | 82831109 | MILPITAS 1109 | MILPITAS 1109XR082 | 30817.3767 | 0.31906 | 1010 | 19.149 | 16027.9766 | 67.3221 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6735 | 3 | 0.002395 | 162821702 | STANISLAUS 1702 | STANISLAUS 1702L3151 | 1598.9081 | 0.0071849 | 1958 | 0.99352 | 16028.9701 | 67.3149 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2824 | 1 | 0.0023862 | 42851121 | FORT ROSS 1121 | FORT ROSS 11214947 | 16678.3963 | 0.0023862 | 2079 | 10.3635 | 16039.3336 | 67.3126 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3792 | 44 | 0.0023509 | 43291105 | PUEBLO 1105 | PUEBLO 1105716 | 4005.9439 | 0.10344 | 1343 | 2.4892 | 16041.8228 | 67.2091 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4407 | 20 | 0.0023507 | 103132101 | CRESCENT MILLS 2101 | CRESCENT MILLS 21013113 | 1853.1278 | 0.047014 | 1566 | 1.1515 | 16042.9742 | 67.1621 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6687 | 8 | 0.002348 | 43291104 | PUEBLO 1104 | PUEBLO 1104640 | 1072.0071 | 0.018784 | 1776 | 0.66611 | 16043.6404 | 67.1433 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9009 | 25 | 0.002341 | 42841112 | GUALALA 1112 | GUALALA 1112circuit_breaker | 2540.8884 | 0.058525 | 1502 | 1.5788 | 16045.2192 | 67.0848 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7068 | 24 | 0.0023307 | 163011102 | MARTELL 1102 | MARTELL 110299214 | 2497.7197 | 0.055938 | 1511 | 1.552 | 16046.7712 | 67.0289 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6862 | 99 | 0.0023138 | 152261104 | DIAMOND SPRINGS 1104 | DIAMOND SPRINGS 11042093 | 12960.3084 | 0.22907 | 1121 | 8.0532 | 16054.8244 | 66.7998 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6493 | 34 | 0.0023071 | 183031101 | PALMER 1101 | PALMER 1101M84 | 34798.532 | 0.078441 | 1427 | 21.6228 | 16076.4472 | 66.7213 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8661 | 72 | 0.002305 | 162821701 | STANISLAUS 1701 | STANISLAUS 1701circuit_breaker | 10963.5629 | 0.16596 | 1217 | 6.8124 | 16083.2596 | 66.5554 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 924 | 641 | 0.0023037 | 163201102 | WEST POINT 1102 | WEST POINT 110293116 | 68737.6903 | 1.4767 | 577 | 42.7116 | 16125.9712 | 65.0787 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Sierra | 924 | 1 | 4.0476e-06 | 163201102 | WEST POINT 1102 | WEST POINT 110293116 | 68737.6903 | 4.0476e-06 | 577 | 42.7116 | 16168.6828 | 65.0787 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 280 | 110 | 0.002298 | 42011104 | SAN RAFAEL 1104 | SAN RAFAEL 1104802 | 12060.44 | 0.25278 | 1094 | 7.494 | 16176.1768 | 64.8259 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6295 | 17 | 0.0022967 | 103491101 | MC ARTHUR 1101 | MC ARTHUR 11011488 | 2966.0846 | 0.039044 | 1610 | 1.843 | 16178.0199 | 64.7869 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1265 | 50 | 0.0022776 | 163451702 | FROGTOWN 1702 | FROGTOWN 170232556 | 7932.1339 | 0.11388 | 1311 | 4.9288 | 16182.9487 | 64.673 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7680 | 32 | 0.0022758 | 42811111 | MONTE RIO 1111 | MONTE RIO 111137520 | 3470.728 | 0.072826 | 1441 | 2.1566 | 16185.1053 | 64.6002 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 281 | 140 | 0.0022756 | 183071101 | PERRY 1101 | PERRY 1101V78 | 47298.9569 | 0.31858 | 1012 | 29.3902 | 16214.4955 | 64.2816 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9593 | 8 | 0.0022605 | 103081105 | BUTTE 1105 | BUTTE 1105244246 | 885.0826 | 0.018084 | 1789 | 0.54996 | 16215.0454 | 64.2635 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6031 | 15 | 0.0022542 | 42811113 | MONTE RIO 1113 | MONTE RIO 11131989 | 1164.5069 | 0.033813 | 1647 | 0.72359 | 16215.769 | 64.2297 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9833 | 1 | 0.0022494 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 11038920 | 185.7819 | 0.0022494 | 2088 | 0.11544 | 16215.8845 | 64.2275 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1986 | 124 | 0.0022488 | 43021102 | WOODACRE 1102 | WOODACRE 11021280 | 13606.7096 | 0.27886 | 1064 | 8.4548 | 16224.3393 | 63.9486 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2791 | 125 | 0.0022424 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210510294 | 13600.6961 | 0.2803 | 1062 | 8.4511 | 16232.7904 | 63.6683 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 9114 | 47 | 0.0022344 | 163351704 | CURTIS 1704 | CURTIS 170411300 | 5848.9555 | 0.10502 | 1338 | 3.6344 | 16236.4247 | 63.5633 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6836 | 1 | 0.0022314 | 162821702 | STANISLAUS 1702 | STANISLAUS 17024905 | 3770.3669 | 0.0022314 | 2090 | 2.3428 | 16238.7675 | 63.5611 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4346 | 30 | 0.0022265 | 43321102 | RINCON 1102 | RINCON 1102circuit_breaker | 4493.3108 | 0.066795 | 1469 | 2.792 | 16241.5595 | 63.4943 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2722 | 143 | 0.0022096 | 152181101 | FORESTHILL 1101 | FORESTHILL 1101circuit_breaker | 14707.8472 | 0.31598 | 1014 | 9.139 | 16250.6986 | 63.1783 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4283 | 329 | 0.0022008 | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210619552 | 34224.6242 | 0.72407 | 795 | 21.2662 | 16271.9648 | 62.4542 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1663 | 127 | 0.0022005 | 102211103 | BUCKS CREEK 1103 | BUCKS CREEK 1103338520 | 12303.5892 | 0.27946 | 1063 | 7.6451 | 16279.6098 | 62.1748 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 9338 | 24 | 0.0021596 | 254432102 | COARSEGOLD 2102 | COARSEGOLD 210210610 | 2195.6315 | 0.05183 | 1531 | 1.3643 | 16280.9741 | 62.1229 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4482 | 39 | 0.0021577 | 252561101 | KERCKHOFF 1101 | KERCKHOFF 1101R353 | 22124.1321 | 0.08415 | 1399 | 13.7473 | 16294.7214 | 62.0388 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1401 | 102 | 0.0021466 | 103271101 | ANTLER 1101 | ANTLER 11011520 | 14269.0206 | 0.21896 | 1139 | 8.8664 | 16303.5878 | 61.8198 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1566 | 176 | 0.0021421 | 24131102 | MENLO 1102 | MENLO 1102W80 | 29528.8058 | 0.37701 | 971 | 18.3483 | 16321.9361 | 61.4428 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6503 | 59 | 0.0021363 | 183101104 | CABRILLO 1104 | CABRILLO 1104Y24 | 28736.9146 | 0.12604 | 1286 | 17.8563 | 16339.7924 | 61.3168 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2232 | 92 | 0.0021246 | 103081105 | BUTTE 1105 | BUTTE 11051243 | 8294.0568 | 0.19546 | 1169 | 5.1537 | 16344.9461 | 61.1213 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5551 | 37 | 0.0021216 | 182721102 | SANTA YNEZ 1102 | SANTA YNEZ 1102Y18 | 7602.3972 | 0.0785 | 1426 | 4.7239 | 16349.67 | 61.0428 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5525 | 92 | 0.0021144 | 24101101 | HALF MOON BAY 1101 | HALF MOON BAY 1101circuit_breaker | 12179.0697 | 0.19452 | 1172 | 7.5677 | 16357.2377 | 60.8483 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3123 | 73 | 0.0021107 | 163751101 | PINE GROVE 1101 | PINE GROVE 11011021 | 6749.2717 | 0.15408 | 1236 | 4.1938 | 16361.4315 | 60.6942 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 715 | 149 | 0.0021106 | 153662102 | APPLE HILL 2102 | APPLE HILL 210212025 | 14681.1435 | 0.31448 | 1016 | 9.1224 | 16370.554 | 60.3797 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4719 | 196 | 0.0021085 | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052130 | 23157.9038 | 0.41327 | 950 | 14.3896 | 16384.9436 | 59.9665 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4145 | 175 | 0.0020921 | 152261106 | DIAMOND SPRINGS 1106 | DIAMOND SPRINGS 110676088 | 17715.9929 | 0.36612 | 978 | 11.0082 | 16395.9518 | 59.6004 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5561 | 3 | 0.0020895 | 82841102 | BIG BASIN 1102 | BIG BASIN 110210254 | 3441.3015 | 0.0062684 | 1968 | 2.1383 | 16398.0902 | 59.5941 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5138 | 72 | 0.0020729 | 83252106 | PAUL SWEET 2106 | PAUL SWEET 210610424 | 9066.2649 | 0.14925 | 1247 | 5.6335 | 16403.7237 | 59.4448 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4726 | 368 | 0.0020424 | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21069712 | 39873.7428 | 0.7516 | 781 | 24.7764 | 16428.5001 | 58.6932 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8884 | 27 | 0.0020422 | 22811103 | PACIFICA 1103 | PACIFICA 11033907 | 5462.3478 | 0.05514 | 1514 | 3.3941 | 16431.8942 | 58.6381 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1425 | 17 | 0.0020411 | 42991105 | LAS GALLINAS A 1105 | LAS GALLINAS A 1105904 | 1736.6554 | 0.034699 | 1641 | 1.0791 | 16432.9733 | 58.6034 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 9105 | 34 | 0.0020375 | 252501101 | BALCH NO 1 1101 | BALCH NO 1 1101circuit_breaker | 13497.4542 | 0.069275 | 1455 | 8.3869 | 16441.3602 | 58.5341 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7796 | 9 | 0.0020359 | 24251101 | WOODSIDE 1101 | WOODSIDE 11018601 | 961.631 | 0.018323 | 1785 | 0.59753 | 16441.9578 | 58.5158 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4455 | 110 | 0.0020305 | 163201102 | WEST POINT 1102 | WEST POINT 11021341 | 16262.9038 | 0.22336 | 1131 | 10.1053 | 16452.0631 | 58.2924 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5042 | 97 | 0.0020274 | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210163464 | 21978.0825 | 0.19665 | 1163 | 13.6565 | 16465.7196 | 58.0958 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4765 | 13 | 0.0020268 | 42891101 | GEYSERVILLE 1101 | GEYSERVILLE 1101480 | 1516.0203 | 0.026348 | 1706 | 0.94201 | 16466.6616 | 58.0694 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 23 | 9 | 0.0020215 | 14662103 | TASSAJARA 2103 | TASSAJARA 2103circuit_breaker | 651.7218 | 0.018193 | 1788 | 0.40496 | 16467.0666 | 58.0512 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 312 | 39 | 0.0020208 | 43071103 | DUNBAR 1103 | DUNBAR 1103440 | 4464.9005 | 0.078811 | 1423 | 2.7744 | 16469.8409 | 57.9724 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7576 | 57 | 0.0020204 | 103561101 | STILLWATER 1101 | STILLWATER 1101circuit_breaker | 6237.7847 | 0.11516 | 1308 | 3.876 | 16473.7169 | 57.8573 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1557 | 557 | 0.0020177 | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 1101circuit_breaker | 63408.1463 | 1.1239 | 655 | 39.4 | 16513.1169 | 56.7334 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5424 | 25 | 0.0020063 | 42851121 | FORT ROSS 1121 | FORT ROSS 112137326 | 8318.589 | 0.050157 | 1541 | 5.1689 | 16518.2858 | 56.6832 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7639 | 119 | 0.0020022 | 42811112 | MONTE RIO 1112 | MONTE RIO 1112120 | 11062.7422 | 0.23827 | 1112 | 6.8741 | 16525.1599 | 56.445 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4687 | 296 | 0.0020014 | 152031103 | GRASS VALLEY 1103 | GRASS VALLEY 11031700 | 34777.5165 | 0.59243 | 861 | 21.6097 | 16546.7696 | 55.8525 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 374 | 17 | 0.0019955 | 162821702 | STANISLAUS 1702 | STANISLAUS 17021804 | 13424.5046 | 0.033923 | 1646 | 8.3416 | 16555.1112 | 55.8186 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5939 | 199 | 0.0019866 | 163781701 | PEORIA 1701 | PEORIA 170190090 | 46519.9218 | 0.39534 | 962 | 28.9061 | 16584.0174 | 55.4233 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5003 | 33 | 0.0019761 | 43211102 | HARTLEY 1102 | HARTLEY 1102circuit_breaker | 4816.0328 | 0.065211 | 1473 | 2.9925 | 16587.0099 | 55.3581 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9176 | 11 | 0.0019607 | 103031102 | ORO FINO 1102 | ORO FINO 110239154 | 1419.8889 | 0.021568 | 1752 | 0.88228 | 16587.8922 | 55.3365 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7457 | 78 | 0.0019572 | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 210135466 | 11954.1294 | 0.15266 | 1241 | 7.4279 | 16595.3201 | 55.1838 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4953 | 59 | 0.0019563 | 103132101 | CRESCENT MILLS 2101 | CRESCENT MILLS 21012056 | 5959.1083 | 0.11542 | 1306 | 3.7028 | 16599.023 | 55.0684 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8130 | 27 | 0.0019292 | 103441101 | JESSUP 1101 | JESSUP 11012839 | 2364.3372 | 0.05209 | 1530 | 1.4691 | 16600.4921 | 55.0163 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4777 | 126 | 0.0019229 | 163761703 | RACETRACK 1703 | RACETRACK 17039190 | 14436.1267 | 0.24229 | 1104 | 8.9702 | 16609.4623 | 54.774 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9539 | 10 | 0.0018937 | 43311102 | KONOCTI 1102 | KONOCTI 11024421 | 585.3593 | 0.018937 | 1775 | 0.36373 | 16609.826 | 54.7551 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4707 | 71 | 0.0018749 | 42841112 | GUALALA 1112 | GUALALA 111223444 | 23359.6524 | 0.13312 | 1274 | 14.515 | 16624.341 | 54.622 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3896 | 87 | 0.0018698 | 102541102 | VOLTA 1102 | VOLTA 11021502 | 11858.7407 | 0.16267 | 1225 | 7.3687 | 16631.7097 | 54.4593 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5593 | 4 | 0.0018566 | 182391103 | OILFIELDS 1103 | OILFIELDS 1103N48 | 76392.1084 | 0.0074263 | 1951 | 47.4678 | 16679.1775 | 54.4519 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 9018 | 52 | 0.0018537 | 163751102 | PINE GROVE 1102 | PINE GROVE 11029145 | 4703.8594 | 0.09639 | 1359 | 2.9228 | 16682.1004 | 54.3555 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5804 | 99 | 0.0018443 | 254432102 | COARSEGOLD 2102 | COARSEGOLD 210210050 | 11531.9078 | 0.18258 | 1187 | 7.1656 | 16689.266 | 54.1729 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2833 | 28 | 0.0018369 | 103491101 | MC ARTHUR 1101 | MC ARTHUR 110137388 | 12648.9045 | 0.051433 | 1534 | 7.8597 | 16697.1256 | 54.1215 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5948 | 436 | 0.0018264 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 110292622 | 49506.0782 | 0.7963 | 761 | 30.7616 | 16727.8873 | 53.3252 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4174 | 84 | 0.0018251 | 182631103 | SAN LUIS OBISPO 1103 | SAN LUIS OBISPO 1103V82 | 12932.1765 | 0.15331 | 1238 | 8.0357 | 16735.9229 | 53.1719 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2726 | 30 | 0.0018199 | 42861101 | ANNAPOLIS 1101 | ANNAPOLIS 110176842 | 9045.3441 | 0.054597 | 1518 | 5.6205 | 16741.5435 | 53.1173 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1416 | 74 | 0.0018069 | 82841102 | BIG BASIN 1102 | BIG BASIN 1102circuit_breaker | 10031.5247 | 0.13371 | 1272 | 6.2333 | 16747.7768 | 52.9836 | 7.5284 | 0.12641 | 1 | #N/A | 52.9836 | #N/A
North Coast | 6947 | 115 | 0.0018025 | 192021121 | ARCATA 1121 | ARCATA 11211206 | 11057.5552 | 0.20728 | 1153 | 6.8708 | 16754.6476 | 52.7763 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3578 | 40 | 0.0018017 | 153082106 | PLACERVILLE 2106 | PLACERVILLE 2106circuit_breaker | 10352.4951 | 0.072068 | 1443 | 6.4327 | 16761.0803 | 52.7042 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 711 | 104 | 0.0017922 | 82841102 | BIG BASIN 1102 | BIG BASIN 110296986 | 9463.8689 | 0.18639 | 1182 | 5.8806 | 16766.9609 | 52.5178 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5251 | 275 | 0.001792 | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101804 | 34767.038 | 0.49281 | 903 | 21.6032 | 16788.5641 | 52.025 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6214 | 96 | 0.001786 | 83252106 | PAUL SWEET 2106 | PAUL SWEET 21068091 | 9677.9322 | 0.17146 | 1207 | 6.0136 | 16794.5777 | 51.8536 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9466 | 21 | 0.0017789 | 43381101 | POINT ARENA 1101 | POINT ARENA 11014923 | 4611.3164 | 0.037358 | 1622 | 2.8653 | 16797.4431 | 51.8162 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 973 | 17 | 0.0017745 | 163781704 | PEORIA 1704 | PEORIA 170413494 | 3111.8752 | 0.030167 | 1679 | 1.9336 | 16799.3767 | 51.786 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7975 | 52 | 0.001772 | 163011101 | MARTELL 1101 | MARTELL 11016074 | 5835.7283 | 0.092143 | 1369 | 3.6262 | 16803.0029 | 51.6939 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2028 | 72 | 0.0017702 | 152762102 | EL DORADO PH 2102 | EL DORADO PH 21026645 | 6883.7119 | 0.12746 | 1284 | 4.2773 | 16807.2802 | 51.5664 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3965 | 12 | 0.0017643 | 43191102 | REDBUD 1102 | REDBUD 1102432 | 1279.6978 | 0.021171 | 1758 | 0.79517 | 16808.0754 | 51.5453 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4355 | 2 | 0.0017579 | 42711102 | CALISTOGA 1102 | CALISTOGA 1102705 | 320.3013 | 0.0035158 | 2039 | 0.19903 | 16808.2744 | 51.5417 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8666 | 37 | 0.0017549 | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 11011079 | 5531.7956 | 0.064932 | 1476 | 3.4373 | 16811.7117 | 51.4768 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2938 | 8 | 0.0017453 | 103311101 | BURNEY 1102 | BURNEY 11022402 | 2243.205 | 0.013963 | 1844 | 1.3939 | 16813.1055 | 51.4628 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7662 | 149 | 0.0017417 | 254432102 | COARSEGOLD 2102 | COARSEGOLD 210210330 | 15524.0665 | 0.25952 | 1086 | 9.6462 | 16822.7518 | 51.2033 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3452 | 27 | 0.001739 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 11039112 | 5442.5238 | 0.046954 | 1568 | 3.3818 | 16826.1336 | 51.1564 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6902 | 218 | 0.0017313 | 182541103 | ATASCADERO 1103 | ATASCADERO 1103A14 | 40416.4237 | 0.37741 | 970 | 25.1136 | 16851.2472 | 50.779 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8528 | 23 | 0.0017309 | 82841102 | BIG BASIN 1102 | BIG BASIN 11022253 | 2352.4543 | 0.03981 | 1604 | 1.4617 | 16852.7089 | 50.7392 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2205 | 547 | 0.0017277 | 163451701 | FROGTOWN 1701 | FROGTOWN 170113412 | 62186.2508 | 0.94506 | 716 | 38.6407 | 16891.3497 | 49.7941 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7553 | 9 | 0.0017264 | 182821103 | MESA 1103 | MESA 1103M92 | 1573.0951 | 0.015537 | 1822 | 0.97748 | 16892.3271 | 49.7786 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 637 | 198 | 0.001724 | 103031102 | ORO FINO 1102 | ORO FINO 11022090 | 23596.9335 | 0.34135 | 993 | 14.6625 | 16906.9896 | 49.4372 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3944 | 144 | 0.0017211 | 163451702 | FROGTOWN 1702 | FROGTOWN 170291134 | 22498.6303 | 0.24784 | 1100 | 13.98 | 16920.9696 | 49.1894 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1077 | 10 | 0.0017144 | 183101103 | CABRILLO 1103 | CABRILLO 1103Y12 | 40069.4408 | 0.017144 | 1798 | 24.898 | 16945.8676 | 49.1722 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9541 | 15 | 0.0017133 | 42291101 | OLEMA 1101 | OLEMA 110175686 | 6456.4354 | 0.0257 | 1715 | 4.0118 | 16949.8794 | 49.1465 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5248 | 27 | 0.001705 | 42091101 | MIRABEL 1101 | MIRABEL 1101228 | 3472.2526 | 0.046034 | 1573 | 2.1576 | 16952.037 | 49.1005 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 8334 | 147 | 0.001698 | 152181101 | FORESTHILL 1101 | FORESTHILL 110137238 | 18519.0658 | 0.2496 | 1099 | 11.5072 | 16963.5442 | 48.8509 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3121 | 11 | 0.0016936 | 42721104 | SONOMA 1104 | SONOMA 110478372 | 26611.5178 | 0.01863 | 1779 | 16.5356 | 16980.0798 | 48.8323 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8547 | 49 | 0.0016918 | 163201102 | WEST POINT 1102 | WEST POINT 11021535 | 4933.5895 | 0.0829 | 1405 | 3.0656 | 16983.1454 | 48.7494 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3162 | 9 | 0.0016891 | 163201101 | WEST POINT 1101 | WEST POINT 11014706 | 18548.1318 | 0.015202 | 1824 | 11.5253 | 16994.6707 | 48.7342 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7753 | 76 | 0.0016774 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 210660120 | 7017.9486 | 0.12748 | 1283 | 4.3607 | 16999.0314 | 48.6067 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4076 | 207 | 0.0016525 | 182611104 | PASO ROBLES 1104 | PASO ROBLES 1104R12 | 42365.8362 | 0.34206 | 992 | 26.3249 | 17025.3563 | 48.2646 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3997 | 367 | 0.0016469 | 102911107 | WYANDOTTE 1107 | WYANDOTTE 11071510 | 41028.1557 | 0.6044 | 850 | 25.4937 | 17050.85 | 47.6602 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 161 | 286 | 0.0016436 | 103201101 | CHALLENGE 1101 | CHALLENGE 110198174 | 31495.8005 | 0.47006 | 919 | 19.5706 | 17070.4206 | 47.1902 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8741 | 9 | 0.0016398 | 163201101 | WEST POINT 1101 | WEST POINT 1101L3355 | 3577.4455 | 0.014759 | 1829 | 2.2229 | 17072.6435 | 47.1754 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9394 | 19 | 0.0016384 | 42261101 | BOLINAS 1101 | BOLINAS 11011232 | 3520.8723 | 0.03113 | 1672 | 2.1878 | 17074.8313 | 47.1443 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4304 | 58 | 0.0016381 | 253642101 | POSO MOUNTAIN 2101 | POSO MOUNTAIN 21014456 | 37862.2156 | 0.095012 | 1363 | 23.5265 | 17098.3578 | 47.0493 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1800 | 97 | 0.0016262 | 14091108 | CASTRO VALLEY 1108 | CASTRO VALLEY 1108MR748 | 10026.1125 | 0.15774 | 1229 | 6.2299 | 17104.5877 | 46.8915 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7085 | 32 | 0.0016191 | 24131102 | MENLO 1102 | MENLO 110212249 | 3776.3578 | 0.051811 | 1532 | 2.3465 | 17106.9342 | 46.8397 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7099 | 30 | 0.0016144 | 192411101 | LOW GAP 1101 | LOW GAP 1101circuit_breaker | 3490.2509 | 0.048432 | 1552 | 2.1687 | 17109.103 | 46.7913 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5621 | 420 | 0.0016135 | 153661104 | APPLE HILL 1104 | APPLE HILL 110497086 | 41232.2745 | 0.67766 | 817 | 25.6205 | 17134.7235 | 46.1136 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3710 | 95 | 0.0016115 | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 1101circuit_breaker | 16524.9105 | 0.15309 | 1239 | 10.2681 | 17144.9916 | 45.9605 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4990 | 239 | 0.0016005 | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LB48 | 23832.8123 | 0.38252 | 968 | 14.809 | 17159.8006 | 45.578 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2960 | 55 | 0.0015982 | 43351106 | LUCERNE 1106 | LUCERNE 110638632 | 7104.2847 | 0.0879 | 1386 | 4.4144 | 17164.215 | 45.4901 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3016 | 5 | 0.0015963 | 152701107 | BELL 1107 | BELL 1107circuit_breaker | 198.4714 | 0.0079817 | 1939 | 0.12332 | 17164.3383 | 45.4821 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 689 | 81 | 0.0015912 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210512590 | 7908.9298 | 0.12889 | 1280 | 4.9144 | 17169.2527 | 45.3532 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2470 | 46 | 0.0015906 | 152691110 | HIGGINS 1110 | HIGGINS 111051794 | 6256.2965 | 0.073168 | 1438 | 3.8875 | 17173.1402 | 45.2801 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2069 | 161 | 0.0015892 | 42091102 | MIRABEL 1102 | MIRABEL 110238514 | 17032.4383 | 0.25586 | 1089 | 10.5835 | 17183.7237 | 45.0242 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4462 | 39 | 0.0015741 | 254432102 | COARSEGOLD 2102 | COARSEGOLD 21025722 | 3182.9469 | 0.061392 | 1487 | 1.9778 | 17185.7015 | 44.9628 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1746 | 46 | 0.0015536 | 152491102 | WEIMAR 1102 | WEIMAR 11026175 | 4390.4905 | 0.071468 | 1445 | 2.7281 | 17188.4296 | 44.8913 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3827 | 60 | 0.00155 | 254151101 | AUBERRY 1101 | AUBERRY 110137536 | 8826.9707 | 0.093 | 1366 | 5.4848 | 17193.9144 | 44.7983 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1117 | 72 | 0.0015461 | 162161101 | ELECTRA 1101 | ELECTRA 110136816 | 8016.99 | 0.11132 | 1320 | 4.9815 | 17198.8959 | 44.687 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1060 | 196 | 0.0015455 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012260 | 22959.7746 | 0.30293 | 1032 | 14.2665 | 17213.1625 | 44.3841 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5073 | 179 | 0.0015432 | 192401101 | HOOPA 1101 | HOOPA 110182542 | 18590.2459 | 0.27624 | 1069 | 11.5514 | 17224.7139 | 44.1079 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 9161 | 11 | 0.0015403 | 152321101 | DRUM 1101 | DRUM 1101circuit_breaker | 3389.5909 | 0.016944 | 1802 | 2.1062 | 17226.8201 | 44.0909 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6696 | 273 | 0.0015397 | 103031102 | ORO FINO 1102 | ORO FINO 110238698 | 25102.3894 | 0.42033 | 943 | 15.5979 | 17242.418 | 43.6706 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1573 | 36 | 0.001531 | 43321104 | RINCON 1104 | RINCON 1104circuit_breaker | 4001.0684 | 0.055116 | 1515 | 2.4861 | 17244.9041 | 43.6155 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2546 | 124 | 0.001527 | 102831104 | PARADISE 1104 | PARADISE 1104circuit_breaker | 47006.8323 | 0.18935 | 1177 | 29.2087 | 17274.1128 | 43.4261 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9046 | 11 | 0.0015266 | 101321101 | PIT NO 5 1101 | PIT NO 5 11011614 | 3000.4112 | 0.016792 | 1806 | 1.8644 | 17275.9772 | 43.4093 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7072 | 41 | 0.0015252 | 163341103 | CLAY 1103 | CLAY 1103circuit_breaker | 9300.035 | 0.062535 | 1485 | 5.7788 | 17281.756 | 43.3468 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4597 | 8 | 0.0015233 | 182551102 | CAYUCOS 1102 | CAYUCOS 1102W18 | 3816.311 | 0.012187 | 1864 | 2.3713 | 17284.1273 | 43.3346 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7202 | 74 | 0.0015217 | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11018233 | 8056.6943 | 0.11261 | 1315 | 5.0062 | 17289.1335 | 43.222 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7358 | 99 | 0.0015186 | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110136514 | 10964.1377 | 0.15034 | 1244 | 6.8128 | 17295.9463 | 43.0717 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 491 | 59 | 0.0015179 | 42031122 | ALTO 1122 | ALTO 112278672 | 5142.0354 | 0.089559 | 1378 | 3.1951 | 17299.1414 | 42.9821 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3043 | 151 | 0.0015116 | 102041104 | NOTRE DAME 1104 | NOTRE DAME 11042028 | 17363.4694 | 0.22824 | 1124 | 10.7892 | 17309.9306 | 42.7539 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5393 | 202 | 0.0015089 | 183041101 | BUELLTON 1101 | BUELLTON 1101Y36 | 59828.4788 | 0.30479 | 1029 | 37.1757 | 17347.1063 | 42.4491 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9976 | 1 | 0.0015073 | 43150241 | TOCALOMA 0241 | TOCALOMA 0241circuit_breaker | 26.5151 | 0.0015073 | 2129 | 0.016476 | 17347.1227 | 42.4476 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7469 | 22 | 0.0015057 | 103721101 | PIT NO 1 1101 | PIT NO 1 110170952 | 2745.2229 | 0.033125 | 1654 | 1.7058 | 17348.8285 | 42.4144 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3774 | 95 | 0.0015045 | 192401101 | HOOPA 1101 | HOOPA 11017468 | 10422.5231 | 0.14293 | 1255 | 6.4763 | 17355.3048 | 42.2715 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6546 | 8 | 0.0015044 | 182492102 | HOLLISTER 2102 | HOLLISTER 21024780 | 2943.6622 | 0.012035 | 1865 | 1.8291 | 17357.1339 | 42.2595 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 47 | 202 | 0.0014936 | 254452101 | MARIPOSA 2101 | MARIPOSA 210135244 | 27730.4872 | 0.30172 | 1037 | 17.2309 | 17374.3648 | 41.9577 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2020 | 325 | 0.0014826 | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210911092 | 36166.6657 | 0.48185 | 915 | 22.4729 | 17396.8377 | 41.4759 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1673 | 6 | 0.0014806 | 182631105 | SAN LUIS OBISPO 1105 | SAN LUIS OBISPO 1105796050 | 2135.0041 | 0.0088838 | 1922 | 1.3266 | 17398.1644 | 41.467 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4695 | 186 | 0.001475 | 42151104 | SANTA ROSA A 1104 | SANTA ROSA A 1104642 | 21539.3089 | 0.27435 | 1071 | 13.3839 | 17411.5483 | 41.1927 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8737 | 34 | 0.0014654 | 182562102 | CHOLAME 2102 | CHOLAME 21025597 | 8229.9238 | 0.049822 | 1542 | 5.1138 | 17416.6621 | 41.1428 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5394 | 133 | 0.0014651 | 163351702 | CURTIS 1702 | CURTIS 17029220 | 17305.2505 | 0.19485 | 1171 | 10.753 | 17427.4151 | 40.948 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5590 | 59 | 0.0014605 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 11022070 | 15820.4099 | 0.086172 | 1391 | 9.8303 | 17437.2454 | 40.8618 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8829 | 7 | 0.0014576 | 14502107 | VINEYARD 2107 | VINEYARD 2107MR332 | 460.8485 | 0.010203 | 1891 | 0.28636 | 17437.5318 | 40.8516 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2461 | 254 | 0.0014541 | 152762101 | EL DORADO PH 2101 | EL DORADO PH 2101circuit_breaker | 26755.9987 | 0.36934 | 975 | 16.6254 | 17454.1572 | 40.4823 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7116 | 2 | 0.0014493 | 183031101 | PALMER 1101 | PALMER 110198478 | 7555.738 | 0.0028986 | 2057 | 4.6949 | 17458.8521 | 40.4794 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8158 | 133 | 0.0014487 | 24131103 | MENLO 1103 | MENLO 11037902 | 18489.6466 | 0.19267 | 1174 | 11.4889 | 17470.341 | 40.2867 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4787 | 167 | 0.0014339 | 163751102 | PINE GROVE 1102 | PINE GROVE 1102circuit_breaker | 17217.3979 | 0.23946 | 1109 | 10.6984 | 17481.0394 | 40.0472 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3556 | 32 | 0.0014337 | 163451702 | FROGTOWN 1702 | FROGTOWN 1702circuit_breaker | 4274.7494 | 0.045877 | 1574 | 2.6562 | 17483.6956 | 40.0014 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5011 | 63 | 0.0014312 | 254061102 | DUNLAP 1102 | DUNLAP 11027360 | 13675.786 | 0.090166 | 1377 | 8.4977 | 17492.1934 | 39.9112 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6623 | 85 | 0.0014292 | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210113532 | 8511.6067 | 0.12148 | 1293 | 5.2889 | 17497.4822 | 39.7897 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4699 | 202 | 0.0014285 | 162161101 | ELECTRA 1101 | ELECTRA 11017104 | 19862.8394 | 0.28856 | 1053 | 12.3422 | 17509.8244 | 39.5011 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 9129 | 65 | 0.0014274 | 162831702 |  | circuit_breaker | 11948.6238 | 0.092782 | 1367 | 7.4245 | 17517.2489 | 39.4084 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 325 | 45 | 0.001427 | 182821101 | MESA 1101 | MESA 1101circuit_breaker | 18758.3645 | 0.064216 | 1479 | 11.6559 | 17528.9048 | 39.3441 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5744 | 12 | 0.0014263 | 42151104 | SANTA ROSA A 1104 | SANTA ROSA A 110464565 | 1301.8977 | 0.017116 | 1800 | 0.80896 | 17529.7138 | 39.327 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4033 | 372 | 0.0014248 | 152481104 | BRUNSWICK 1104 | BRUNSWICK 11041020 | 46114.191 | 0.53002 | 888 | 28.654 | 17558.3678 | 38.797 | 28.1614 | 0.52549 | 1 | #N/A | 38.797 | #N/A
Central Valley | 1362 | 98 | 0.0014248 | 163661701 | MIWUK 1701 | MIWUK 170193062 | 13308.2221 | 0.13963 | 1265 | 8.2693 | 17566.6372 | 38.6574 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 578 | 397 | 0.0014208 | 152762101 | EL DORADO PH 2101 | EL DORADO PH 21016852 | 40526.8318 | 0.56407 | 868 | 25.1822 | 17591.8194 | 38.0933 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Valley | 578 | 1 | 9.0108e-06 | 152762101 | EL DORADO PH 2101 | EL DORADO PH 21016852 | 40526.8318 | 9.0108e-06 | 868 | 25.1822 | 17617.0016 | 38.0933 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 6809 | 17 | 0.0014163 | 42811113 | MONTE RIO 1113 | MONTE RIO 11138299 | 1927.3515 | 0.024077 | 1729 | 1.1976 | 17618.1992 | 38.0692 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2592 | 60 | 0.0014148 | 153661104 | APPLE HILL 1104 | APPLE HILL 110412947 | 5562.8913 | 0.084889 | 1398 | 3.4566 | 17621.6558 | 37.9843 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3473 | 28 | 0.0014147 | 43071103 | DUNBAR 1103 | DUNBAR 1103circuit_breaker | 3351.8236 | 0.039611 | 1608 | 2.0827 | 17623.7385 | 37.9447 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2139 | 7 | 0.0014049 | 252811102 | MERCED FALLS 1102 | MERCED FALLS 110222774 | 1272.8669 | 0.0098346 | 1900 | 0.79092 | 17624.5294 | 37.9349 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7643 | 55 | 0.0014042 | 254432102 | COARSEGOLD 2102 | COARSEGOLD 210210207 | 5760.3678 | 0.07723 | 1429 | 3.5793 | 17628.1088 | 37.8577 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4253 | 180 | 0.0013948 | 103521102 | OREGON TRAIL 1102 | OREGON TRAIL 11021584 | 20999.2286 | 0.25106 | 1096 | 13.0483 | 17641.1571 | 37.6066 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6260 | 526 | 0.0013928 | 163751102 | PINE GROVE 1102 | PINE GROVE 11026080 | 56095.9807 | 0.73263 | 789 | 34.8564 | 17676.0135 | 36.874 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7683 | 128 | 0.0013845 | 42151104 | SANTA ROSA A 1104 | SANTA ROSA A 1104716 | 14273.5878 | 0.17721 | 1195 | 8.8692 | 17684.8827 | 36.6968 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8791 | 7 | 0.0013712 | 163341102 | CLAY 1102 | CLAY 1102circuit_breaker | 1255.8462 | 0.0095983 | 1904 | 0.78035 | 17685.663 | 36.6872 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2486 | 229 | 0.0013549 | 42601102 | PHILO 1102 | PHILO 1102920 | 26207.5142 | 0.31026 | 1022 | 16.2846 | 17701.9476 | 36.3769 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 574 | 35 | 0.0013549 | 43351106 | LUCERNE 1106 | LUCERNE 110647198 | 4671.7433 | 0.04742 | 1563 | 2.9029 | 17704.8505 | 36.3295 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8397 | 109 | 0.0013459 | 83481110 | STELLING 1110 | STELLING 111060080 | 15400.8729 | 0.1467 | 1250 | 9.5697 | 17714.4202 | 36.1828 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6831 | 254 | 0.0013413 | 103751101 | BIG BEND 1101 | BIG BEND 1101circuit_breaker | 35800.1144 | 0.34069 | 994 | 22.2452 | 17736.6653 | 35.8421 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1561 | 54 | 0.0013387 | 162991103 | CORRAL 1103 | CORRAL 110359770 | 6842.3899 | 0.072287 | 1442 | 4.2517 | 17740.917 | 35.7698 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2549 | 117 | 0.0013173 | 24131103 | MENLO 1103 | MENLO 11031721 | 10927.2973 | 0.15412 | 1235 | 6.7899 | 17747.7069 | 35.6157 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4538 | 22 | 0.0013089 | 182971101 | PURISIMA 1101 | PURISIMA 1101Y42 | 2254.0917 | 0.028796 | 1687 | 1.4006 | 17749.1075 | 35.5869 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6913 | 65 | 0.0013081 | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 6679.2994 | 0.085027 | 1397 | 4.1503 | 17753.2578 | 35.5019 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3408 | 230 | 0.0013077 | 163351702 | CURTIS 1702 | CURTIS 17026008 | 28195.182 | 0.30077 | 1040 | 17.5197 | 17770.7775 | 35.2011 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7210 | 11 | 0.0013055 | 14161106 | ROSSMOOR 1106 | ROSSMOOR 110639424 | 1232.955 | 0.01436 | 1842 | 0.76612 | 17771.5436 | 35.1867 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8363 | 88 | 0.0012968 | 163761703 | RACETRACK 1703 | RACETRACK 17036014 | 11321.9024 | 0.11412 | 1310 | 7.0351 | 17778.5787 | 35.0726 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5890 | 41 | 0.0012966 | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 210237300 | 11257.5171 | 0.053159 | 1525 | 6.9951 | 17785.5738 | 35.0194 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2984 | 25 | 0.0012963 | 162821702 | STANISLAUS 1702 | STANISLAUS 17021888 | 30461.9306 | 0.032406 | 1659 | 18.9282 | 17804.502 | 34.987 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8296 | 7 | 0.001295 | 83432101 | HICKS 2101 | HICKS 2101circuit_breaker | 4105.0932 | 0.0090651 | 1918 | 2.5508 | 17807.0528 | 34.978 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2953 | 117 | 0.0012912 | 163761703 | RACETRACK 1703 | RACETRACK 170311270 | 19572.4814 | 0.15107 | 1243 | 12.1618 | 17819.2145 | 34.8269 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2406 | 4 | 0.0012883 | 182951102 | FOOTHILL 1102 | FOOTHILL 1102V06 | 1798.9532 | 0.0051532 | 1992 | 1.1178 | 17820.3324 | 34.8218 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5720 | 79 | 0.0012865 | 42151111 | SANTA ROSA A 1111 | SANTA ROSA A 1111114 | 9582.7736 | 0.10163 | 1348 | 5.9545 | 17826.2868 | 34.7201 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3 | 62 | 0.0012861 | 152691104 | HIGGINS 1104 | HIGGINS 1104498932 | 5868.3896 | 0.07974 | 1418 | 3.6464 | 17829.9333 | 34.6404 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2615 | 381 | 0.0012848 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 210660124 | 36237.2416 | 0.48951 | 906 | 22.5168 | 17852.45 | 34.1509 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 2615 | 1 | 9.7149e-06 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 210660124 | 36237.2416 | 9.7149e-06 | 906 | 22.5168 | 17874.9668 | 34.1509 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Sierra | 7910 | 17 | 0.0012814 | 152031103 | GRASS VALLEY 1103 | GRASS VALLEY 110358498 | 2050.6115 | 0.021784 | 1751 | 1.2742 | 17876.241 | 34.1291 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5530 | 65 | 0.0012796 | 153661104 | APPLE HILL 1104 | APPLE HILL 1104circuit_breaker | 6802.485 | 0.083174 | 1404 | 4.2269 | 17880.4679 | 34.0459 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8824 | 6 | 0.0012794 | 14351104 | FREMONT 1104 | FREMONT 1104MR707 | 2328.9027 | 0.0076763 | 1944 | 1.4471 | 17881.915 | 34.0382 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2681 | 69 | 0.0012765 | 82841102 | BIG BASIN 1102 | BIG BASIN 110212124 | 6852.9075 | 0.088081 | 1385 | 4.2582 | 17886.1732 | 33.9501 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5809 | 36 | 0.0012691 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 210694770 | 3595.9649 | 0.045686 | 1578 | 2.2344 | 17888.4076 | 33.9045 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6825 | 46 | 0.0012689 | 163781701 | PEORIA 1701 | PEORIA 1701circuit_breaker | 14117.7933 | 0.05837 | 1503 | 8.7724 | 17897.18 | 33.8461 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2384 | 419 | 0.0012655 | 153661104 | APPLE HILL 1104 | APPLE HILL 110413512 | 45529.6464 | 0.53023 | 887 | 28.2908 | 17925.4708 | 33.3159 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1364 | 45 | 0.0012632 | 163351705 | CURTIS 1705 | CURTIS 170539256 | 42574.1624 | 0.056842 | 1507 | 26.4543 | 17951.9251 | 33.259 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7251 | 30 | 0.0012617 | 14091108 | CASTRO VALLEY 1108 | CASTRO VALLEY 1108MR341 | 3784.8751 | 0.03785 | 1617 | 2.3518 | 17954.277 | 33.2212 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 682 | 80 | 0.0012586 | 103721101 | PIT NO 1 1101 | PIT NO 1 11013312 | 12918.6838 | 0.10069 | 1351 | 8.0273 | 17962.3042 | 33.1205 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5092 | 44 | 0.0012573 | 192151133 | NEWBURG 1133 | NEWBURG 1133circuit_breaker | 3484.7774 | 0.055322 | 1512 | 2.1653 | 17964.4696 | 33.0652 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7428 | 131 | 0.0012556 | 42761101 | FORT BRAGG A 1101 | FORT BRAGG A 11013113 | 16133.333 | 0.16449 | 1222 | 10.0248 | 17974.4944 | 32.9007 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 977 | 14 | 0.00125 | 24101102 | HALF MOON BAY 1102 | HALF MOON BAY 11022032 | 2245.4219 | 0.017499 | 1794 | 1.3952 | 17975.8896 | 32.8832 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 127 | 463 | 0.0012494 | 153661103 | APPLE HILL 1103 | APPLE HILL 1103circuit_breaker | 47137.6043 | 0.57849 | 865 | 29.2899 | 18005.1796 | 32.3047 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 127 | 1 | 4.8348e-06 | 153661103 | APPLE HILL 1103 | APPLE HILL 1103circuit_breaker | 47137.6043 | 4.8348e-06 | 865 | 29.2899 | 18034.4695 | 32.3047 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 9055 | 2 | 0.0012445 | 14592105 | BRENTWOOD 2105 | BRENTWOOD 210596324 | 775.7684 | 0.002489 | 2074 | 0.48204 | 18034.9515 | 32.3022 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3395 | 7 | 0.0012362 | 258861101 | SO. CAL. EDISON #3 1101 | SO. CAL. EDISON #3 1101circuit_breaker | 13165.8307 | 0.0086536 | 1926 | 8.1809 | 18043.1324 | 32.2935 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1533 | 118 | 0.0012344 | 83252106 | PAUL SWEET 2106 | PAUL SWEET 21065178 | 11755.1342 | 0.14566 | 1252 | 7.3043 | 18050.4367 | 32.1479 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3883 | 250 | 0.0012337 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210510214 | 22399.2356 | 0.30842 | 1026 | 13.9182 | 18064.3549 | 31.8394 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6677 | 6 | 0.0012306 | 42461106 | BASALT 1106 | BASALT 11065030 | 2570.7987 | 0.0073833 | 1952 | 1.5974 | 18065.9524 | 31.8321 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7400 | 25 | 0.0012262 | 42871101 | UPPER LAKE 1101 | UPPER LAKE 11016663 | 3763.6845 | 0.030656 | 1676 | 2.3386 | 18068.291 | 31.8014 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7702 | 62 | 0.0012205 | 163751101 | PINE GROVE 1101 | PINE GROVE 1101circuit_breaker | 6897.7403 | 0.07567 | 1432 | 4.2861 | 18072.5771 | 31.7257 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4288 | 42 | 0.0012171 | 42271104 | COTATI 1104 | COTATI 110475972 | 4863.4766 | 0.051118 | 1537 | 3.022 | 18075.5991 | 31.6746 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4260 | 225 | 0.0012134 | 254452101 | MARIPOSA 2101 | MARIPOSA 21018030 | 30213.4552 | 0.27302 | 1072 | 18.7738 | 18094.3728 | 31.4016 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4696 | 26 | 0.0012107 | 252531102 | SAN JOAQUIN #3 1102 | SAN JOAQUIN #3 110210342 | 2930.8819 | 0.031479 | 1669 | 1.8212 | 18096.194 | 31.3701 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8214 | 19 | 0.0012095 | 253642103 | POSO MOUNTAIN 2103 | POSO MOUNTAIN 21033988 | 26364.8424 | 0.02298 | 1740 | 16.3823 | 18112.5764 | 31.3471 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8117 | 13 | 0.0012068 | 192401101 | HOOPA 1101 | HOOPA 110193038 | 1584.2405 | 0.015689 | 1820 | 0.9844 | 18113.5608 | 31.3315 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3925 | 50 | 0.0012022 | 152031101 | GRASS VALLEY 1101 | GRASS VALLEY 11012766 | 5321.5191 | 0.060111 | 1493 | 3.3066 | 18116.8674 | 31.2713 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4928 | 60 | 0.0011963 | 192251102 | RIO DELL 1102 | RIO DELL 110270960 | 5431.663 | 0.071776 | 1444 | 3.3751 | 18120.2425 | 31.1996 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9153 | 50 | 0.0011918 | 42811111 | MONTE RIO 1111 | MONTE RIO 11113891 | 5703.541 | 0.059592 | 1495 | 3.544 | 18123.7865 | 31.14 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 230 | 24 | 0.0011867 | 43311102 | KONOCTI 1102 | KONOCTI 11022293 | 2621.5628 | 0.02848 | 1688 | 1.629 | 18125.4154 | 31.1115 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8383 | 37 | 0.001185 | 14241101 | SUNOL 1101 | SUNOL 1101circuit_breaker | 4242.1562 | 0.043844 | 1585 | 2.636 | 18128.0514 | 31.0677 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4804 | 100 | 0.001184 | 183052110 | TEMPLETON 2110 | TEMPLETON 2110R94 | 21302.3977 | 0.1184 | 1298 | 13.2367 | 18141.2881 | 30.9492 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 335 | 191 | 0.0011761 | 43021101 | WOODACRE 1101 | WOODACRE 1101404 | 19975.081 | 0.22463 | 1126 | 12.4119 | 18153.7 | 30.7246 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6088 | 64 | 0.0011614 | 163661702 | MIWUK 1702 | MIWUK 170219772 | 6198.5938 | 0.074328 | 1434 | 3.8516 | 18157.5517 | 30.6503 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 65 | 74 | 0.0011503 | 252931102 | TEJON 1102 | TEJON 11022455 | 10444.6875 | 0.085122 | 1396 | 6.49 | 18164.0417 | 30.5652 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 265 | 86 | 0.0011501 | 42091102 | MIRABEL 1102 | MIRABEL 1102332 | 9065.6252 | 0.098904 | 1355 | 5.6331 | 18169.6748 | 30.4663 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9319 | 33 | 0.0011495 | 42811111 | MONTE RIO 1111 | MONTE RIO 111159046 | 5445.8416 | 0.037933 | 1614 | 3.3839 | 18173.0587 | 30.4283 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3185 | 199 | 0.0011475 | 153081112 | PLACERVILLE 1112 | PLACERVILLE 111219712 | 20689.2133 | 0.22836 | 1123 | 12.8557 | 18185.9144 | 30.2 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2994 | 18 | 0.0011462 | 152691103 | HIGGINS 1103 | HIGGINS 11032194 | 1734.1421 | 0.020631 | 1762 | 1.0775 | 18186.9919 | 30.1793 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2433 | 222 | 0.001142 | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 110135424 | 22222.0885 | 0.25352 | 1092 | 13.8082 | 18200.8001 | 29.9258 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3109 | 134 | 0.0011403 | 43351103 | LUCERNE 1103 | LUCERNE 1103630 | 19624.8492 | 0.1528 | 1240 | 12.1943 | 18212.9944 | 29.773 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6982 | 1 | 0.0022795 | 42211104 | NOVATO 1104 | NOVATO 110455398 | 4828.5632 | 0.0022795 | 1632 | 3.0003 | 18215.9947 | 29.7707 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 6982 | 30 | 0.0011013 | 42211104 | NOVATO 1104 | NOVATO 110455398 | 4828.5632 | 0.033038 | 1632 | 3.0003 | 18218.995 | 29.7377 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Valley | 7955 | 103 | 0.0011276 | 163351703 | CURTIS 1703 | CURTIS 1703circuit_breaker | 13991.6786 | 0.11614 | 1303 | 8.694 | 18227.6891 | 29.6216 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4122 | 99 | 0.0011237 | 163231101 | NORTH BRANCH 1101 | NORTH BRANCH 1101circuit_breaker | 23932.4889 | 0.11124 | 1321 | 14.871 | 18242.56 | 29.5103 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9115 | 57 | 0.0011205 | 42261101 | BOLINAS 1101 | BOLINAS 110137034 | 7287.0481 | 0.063866 | 1480 | 4.528 | 18247.088 | 29.4465 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3702 | 154 | 0.001118 | 182631101 | SAN LUIS OBISPO 1101 | SAN LUIS OBISPO 1101V12 | 33846.6296 | 0.17217 | 1204 | 21.0313 | 18268.1193 | 29.2743 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1467 | 9 | 0.0011177 | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 44784.9902 | 0.010059 | 1892 | 27.8281 | 18295.9474 | 29.2642 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 413 | 277 | 0.0011158 | 192021122 | ARCATA 1122 | ARCATA 11225384 | 24769.8423 | 0.30908 | 1024 | 15.3913 | 18311.3387 | 28.9551 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8197 | 63 | 0.0011062 | 192291121 | CARLOTTA 1121 | CARLOTTA 112144150 | 5746.8082 | 0.06969 | 1451 | 3.5709 | 18314.9096 | 28.8855 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2916 | 59 | 0.0011053 | 14091109 | CASTRO VALLEY 1109 | CASTRO VALLEY 1109MR334 | 9273.2114 | 0.065212 | 1472 | 5.7621 | 18320.6717 | 28.8202 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7949 | 49 | 0.0010956 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 210611533 | 4271.438 | 0.053683 | 1521 | 2.6541 | 18323.3258 | 28.7666 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7505 | 113 | 0.0010955 | 43432105 | SILVERADO 2105 | SILVERADO 21051421 | 15418.6642 | 0.12379 | 1291 | 9.5807 | 18332.9065 | 28.6428 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1067 | 86 | 0.0010928 | 13801101 | MORAGA 1101 | MORAGA 1101circuit_breaker | 10864.992 | 0.093981 | 1364 | 6.7512 | 18339.6577 | 28.5488 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1121 | 202 | 0.0010891 | 152701109 | BELL 1109 | BELL 1109circuit_breaker | 22001.4253 | 0.21999 | 1137 | 13.671 | 18353.3288 | 28.3288 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9020 | 86 | 0.001083 | 103381102 | FRENCH GULCH 1102 | FRENCH GULCH 11022902 | 11239.784 | 0.093136 | 1365 | 6.9841 | 18360.3128 | 28.2357 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3465 | 18 | 0.0010819 | 43351103 | LUCERNE 1103 | LUCERNE 1103circuit_breaker | 3472.4667 | 0.019474 | 1771 | 2.1577 | 18362.4705 | 28.2162 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4319 | 20 | 0.0010773 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 1103circuit_breaker | 2489.4218 | 0.021546 | 1753 | 1.5469 | 18364.0174 | 28.1946 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9418 | 4 | 0.0010714 | 42481101 | IGNACIO 1101 | IGNACIO 11011779 | 385.9886 | 0.0042854 | 2016 | 0.23984 | 18364.2572 | 28.1904 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3089 | 6 | 0.0010698 | 152481103 | BRUNSWICK 1103 | BRUNSWICK 11032200 | 8965.9105 | 0.0064186 | 1965 | 5.5712 | 18369.8284 | 28.1839 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6055 | 77 | 0.0010637 | 192171101 | WILLOW CREEK 1101 | WILLOW CREEK 110191926 | 7078.2935 | 0.081905 | 1414 | 4.3982 | 18374.2266 | 28.102 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7183 | 17 | 0.0010637 | 43351106 | LUCERNE 1106 | LUCERNE 11062327 | 1891.7626 | 0.018082 | 1790 | 1.1755 | 18375.4021 | 28.084 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7943 | 33 | 0.0010626 | 42811111 | MONTE RIO 1111 | MONTE RIO 1111240 | 4934.4459 | 0.035066 | 1637 | 3.0661 | 18378.4682 | 28.0489 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5185 | 65 | 0.001049 | 82841101 | BIG BASIN 1101 | BIG BASIN 110110720 | 7531.494 | 0.068186 | 1457 | 4.6799 | 18383.1481 | 27.9807 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7263 | 106 | 0.0010488 | 163881101 | IONE 1101 | IONE 1101L3141 | 21707.6376 | 0.11117 | 1324 | 13.4885 | 18396.6366 | 27.8695 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3198 | 27 | 0.0010464 | 103132101 | CRESCENT MILLS 2101 | CRESCENT MILLS 2101circuit_breaker | 3593.1531 | 0.028253 | 1692 | 2.2327 | 18398.8693 | 27.8413 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7482 | 38 | 0.001046 | 254421102 | OAKHURST 1102 | OAKHURST 1102circuit_breaker | 3940.8287 | 0.039746 | 1607 | 2.4487 | 18401.318 | 27.8015 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4223 | 64 | 0.0010383 | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210623190 | 5913.2611 | 0.066453 | 1470 | 3.6743 | 18404.9923 | 27.7351 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4351 | 72 | 0.0010377 | 162161102 | ELECTRA 1102 | ELECTRA 11024756 | 15007.7986 | 0.074716 | 1433 | 9.3254 | 18414.3177 | 27.6604 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2978 | 216 | 0.0010374 | 82841101 | BIG BASIN 1101 | BIG BASIN 110110296 | 23203.6203 | 0.22408 | 1127 | 14.4181 | 18428.7358 | 27.4363 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 648 | 28 | 0.001035 | 182331101 | GABILAN 1101 | GABILAN 1101579969 | 5768.1438 | 0.02898 | 1685 | 3.5842 | 18432.3199 | 27.4073 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2234 | 277 | 0.0010335 | 103031102 | ORO FINO 1102 | ORO FINO 11022560 | 26913.6157 | 0.28627 | 1055 | 16.7233 | 18449.0433 | 27.121 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4390 | 46 | 0.0010317 | 182631104 | SAN LUIS OBISPO 1104 | SAN LUIS OBISPO 1104V14 | 13115.916 | 0.04746 | 1562 | 8.1498 | 18457.1931 | 27.0736 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8974 | 12 | 0.0010311 | 42811113 | MONTE RIO 1113 | MONTE RIO 11131067 | 1294.5528 | 0.012373 | 1861 | 0.8044 | 18457.9975 | 27.0612 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5896 | 18 | 0.0010281 | 182601106 | OCEANO 1106 | OCEANO 1106V28 | 2046.144 | 0.018506 | 1782 | 1.2714 | 18459.2689 | 27.0427 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1525 | 152 | 0.0010151 | 192291121 | CARLOTTA 1121 | CARLOTTA 11214914 | 15711.3837 | 0.15429 | 1233 | 9.7626 | 18469.0315 | 26.8884 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2713 | 227 | 0.0010134 | 254151101 | AUBERRY 1101 | AUBERRY 1101R2845 | 28634.7335 | 0.23003 | 1119 | 17.7928 | 18486.8243 | 26.6584 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7367 | 179 | 0.0010129 | 163661701 | MIWUK 1701 | MIWUK 17018050 | 19483.5578 | 0.18132 | 1192 | 12.1065 | 18498.9308 | 26.477 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2375 | 10 | 0.00099933 | 163751102 | PINE GROVE 1102 | PINE GROVE 110245292 | 17509.1139 | 0.0099933 | 1897 | 10.8797 | 18509.8105 | 26.4671 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1719 | 7 | 0.00099704 | 163341101 | CLAY 1101 | CLAY 110113450 | 553.6801 | 0.0069792 | 1960 | 0.34404 | 18510.1545 | 26.4601 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 43 | 4 | 0.00099634 | 42811111 | MONTE RIO 1111 | MONTE RIO 11111703 | 2219.017 | 0.0039854 | 2026 | 1.3788 | 18511.5334 | 26.4561 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6447 | 110 | 0.00099565 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 210637210 | 10381.5121 | 0.10952 | 1327 | 6.4508 | 18517.9841 | 26.3466 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4353 | 3 | 0.00099468 | 182201122 | SPENCE 1122 | SPENCE 1122circuit_breaker | 14788.6218 | 0.002984 | 2053 | 9.1892 | 18527.1734 | 26.3436 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5112 | 260 | 0.00099292 | 163661702 | MIWUK 1702 | MIWUK 17026018 | 31416.8747 | 0.25816 | 1087 | 19.5215 | 18546.6949 | 26.0854 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2954 | 100 | 0.00099126 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012586 | 8954.8757 | 0.099126 | 1353 | 5.5643 | 18552.2592 | 25.9863 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 423 | 172 | 0.00099015 | 252931102 | TEJON 1102 | TEJON 11023751 | 32633.9479 | 0.17031 | 1211 | 20.2778 | 18572.537 | 25.816 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2640 | 189 | 0.00098584 | 252192101 | BEAR VALLEY 2101 | BEAR VALLEY 210110000 | 47046.2975 | 0.18632 | 1183 | 29.2332 | 18601.7702 | 25.6297 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1001 | 546 | 0.00098331 | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 61569.4579 | 0.53689 | 885 | 38.2575 | 18640.0277 | 25.0928 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3526 | 238 | 0.00098292 | 82841102 | BIG BASIN 1102 | BIG BASIN 110212992 | 22897.5855 | 0.23393 | 1116 | 14.2279 | 18654.2556 | 24.8588 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1201 | 15 | 0.00098117 | 42851121 | FORT ROSS 1121 | FORT ROSS 11212987 | 3345.8187 | 0.014718 | 1830 | 2.079 | 18656.3346 | 24.8441 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1347 | 3 | 0.00097066 | 14662112 | TASSAJARA 2112 | TASSAJARA 2112circuit_breaker | 219.0837 | 0.002912 | 2056 | 0.13613 | 18656.4707 | 24.8412 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1104 | 23 | 0.00096311 | 42991106 | LAS GALLINAS A 1106 | LAS GALLINAS A 1106circuit_breaker | 2059.9533 | 0.022152 | 1746 | 1.28 | 18657.7507 | 24.8191 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5215 | 40 | 0.00096175 | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052100 | 6320.6672 | 0.03847 | 1612 | 3.9275 | 18661.6782 | 24.7806 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 371 | 179 | 0.0009547 | 163451702 | FROGTOWN 1702 | FROGTOWN 1702L5407 | 29150.3712 | 0.17089 | 1208 | 18.1132 | 18679.7914 | 24.6097 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4005 | 96 | 0.00095444 | 83622104 | CAMP EVERS 2104 | CAMP EVERS 210410442 | 8552.2815 | 0.091626 | 1372 | 5.3141 | 18685.1055 | 24.5181 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3384 | 1 | 0.00095184 | 22861104 | SERRAMONTE 1104 | SERRAMONTE 110412705 | 414.5607 | 0.00095184 | 2162 | 0.2576 | 18685.3631 | 24.5171 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5304 | 109 | 0.000939 | 152431101 | SHADY GLEN 1101 | SHADY GLEN 11012768 | 11242.1065 | 0.10235 | 1345 | 6.9855 | 18692.3486 | 24.4148 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2551 | 60 | 0.00093833 | 42851121 | FORT ROSS 1121 | FORT ROSS 1121124 | 29943.2023 | 0.0563 | 1509 | 18.6058 | 18710.9544 | 24.3585 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 714 | 255 | 0.00093306 | 152261106 | DIAMOND SPRINGS 1106 | DIAMOND SPRINGS 110650324 | 27285.9774 | 0.23793 | 1113 | 16.9547 | 18727.9092 | 24.1205 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3057 | 84 | 0.00093168 | 82841101 | BIG BASIN 1101 | BIG BASIN 1101circuit_breaker | 7584.3674 | 0.078261 | 1428 | 4.7127 | 18732.6219 | 24.0423 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7397 | 35 | 0.00092851 | 42091102 | MIRABEL 1102 | MIRABEL 110257840 | 4145.2916 | 0.032498 | 1656 | 2.5758 | 18735.1976 | 24.0098 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5738 | 5 | 0.00092277 | 182981102 | JOLON 1102 | JOLON 1102circuit_breaker | 36119.0128 | 0.0046139 | 2006 | 22.4433 | 18757.6409 | 24.0052 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4045 | 143 | 0.00092196 | 152762102 | EL DORADO PH 2102 | EL DORADO PH 210219542 | 15104.0184 | 0.13184 | 1276 | 9.3852 | 18767.0261 | 23.8733 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3689 | 31 | 0.00091714 | 254151101 | AUBERRY 1101 | AUBERRY 1101R322 | 12046.3509 | 0.028431 | 1689 | 7.4853 | 18774.5114 | 23.8449 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1084 | 242 | 0.00091133 | 192401101 | HOOPA 1101 | HOOPA 1101circuit_breaker | 23835.3937 | 0.22054 | 1136 | 14.8106 | 18789.322 | 23.6244 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4688 | 130 | 0.00090795 | 182631104 | SAN LUIS OBISPO 1104 | SAN LUIS OBISPO 1104V46 | 30343.0121 | 0.11803 | 1300 | 18.8543 | 18808.1763 | 23.5063 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1531 | 194 | 0.00090774 | 192171101 | WILLOW CREEK 1101 | WILLOW CREEK 11015002 | 21536.2249 | 0.1761 | 1197 | 13.382 | 18821.5583 | 23.3302 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9481 | 94 | 0.0008952 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012248 | 14718.1001 | 0.084149 | 1400 | 9.1454 | 18830.7037 | 23.2461 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8645 | 92 | 0.00089464 | 103611101 | WILDWOOD 1101 | WILDWOOD 110185112 | 10853.0331 | 0.082307 | 1410 | 6.7438 | 18837.4474 | 23.1638 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2795 | 100 | 0.00089425 | 153081112 | PLACERVILLE 1112 | PLACERVILLE 111219742 | 9960.0097 | 0.089425 | 1381 | 6.1889 | 18843.6363 | 23.0743 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8291 | 30 | 0.00088921 | 163341103 | CLAY 1103 | CLAY 11037142 | 5016.468 | 0.026676 | 1705 | 3.1171 | 18846.7534 | 23.0477 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1670 | 28 | 0.00088871 | 43351106 | LUCERNE 1106 | LUCERNE 110676850 | 2991.9456 | 0.024884 | 1721 | 1.8591 | 18848.6125 | 23.0228 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2092 | 224 | 0.0008884 | 163451701 | FROGTOWN 1701 | FROGTOWN 17011623 | 24542.3809 | 0.199 | 1158 | 15.2499 | 18863.8624 | 22.8238 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7075 | 42 | 0.00088751 | 182671108 | SANTA MARIA 1108 | SANTA MARIA 1108M18 | 23036.475 | 0.037275 | 1623 | 14.3142 | 18878.1766 | 22.7865 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1456 | 141 | 0.00088617 | 83041101 | BEN LOMOND 1101 | BEN LOMOND 1101BL 1101 | 13712.9137 | 0.12495 | 1289 | 8.5208 | 18886.6974 | 22.6616 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7660 | 69 | 0.00088263 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 210612840 | 6527.3425 | 0.060901 | 1489 | 4.0559 | 18890.7533 | 22.6007 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3103 | 447 | 0.00088095 | 152481106 | BRUNSWICK 1106 | BRUNSWICK 11062416 | 45937.2563 | 0.39379 | 963 | 28.5441 | 18919.2974 | 22.2069 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 296 | 52 | 0.00087538 | 42811111 | MONTE RIO 1111 | MONTE RIO 111164758 | 17002.078 | 0.04552 | 1579 | 10.5646 | 18929.862 | 22.1613 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5156 | 13 | 0.00087029 | 12022212 | CLAYTON 2212 | CLAYTON 2212circuit_breaker | 3174.2004 | 0.011314 | 1875 | 1.9724 | 18931.8343 | 22.15 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1156 | 378 | 0.000868 | 103031101 | ORO FINO 1101 | ORO FINO 1101circuit_breaker | 39834.6591 | 0.32811 | 1004 | 24.7521 | 18956.5864 | 21.8219 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6048 | 207 | 0.0008663 | 152321101 | DRUM 1101 | DRUM 11011602 | 26765.8492 | 0.17932 | 1194 | 16.6315 | 18973.218 | 21.6426 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7933 | 20 | 0.00085771 | 252811102 | MERCED FALLS 1102 | MERCED FALLS 110222772 | 3605.0516 | 0.017154 | 1797 | 2.2401 | 18975.458 | 21.6255 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6297 | 204 | 0.00085758 | 182811103 | SISQUOC 1103 | SISQUOC 1103M14 | 32732.59 | 0.17495 | 1198 | 20.3391 | 18995.7971 | 21.4505 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3317 | 92 | 0.00085633 | 42261101 | BOLINAS 1101 | BOLINAS 1101504 | 10456.414 | 0.078783 | 1424 | 6.4973 | 19002.2944 | 21.3717 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4944 | 71 | 0.00085566 | 24251101 | WOODSIDE 1101 | WOODSIDE 11018912 | 6353.9227 | 0.060752 | 1490 | 3.9481 | 19006.2426 | 21.311 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6928 | 60 | 0.00085557 | 163351704 | CURTIS 1704 | CURTIS 17046060 | 6649.044 | 0.051334 | 1535 | 4.1315 | 19010.3741 | 21.2596 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 340 | 27 | 0.00085352 | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052204 | 11642.89 | 0.023045 | 1738 | 7.2346 | 19017.6087 | 21.2366 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 970 | 93 | 0.00085182 | 163451701 | FROGTOWN 1701 | FROGTOWN 1701circuit_breaker | 16003.3182 | 0.079219 | 1421 | 9.944 | 19027.5527 | 21.1574 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 286 | 312 | 0.00084831 | 82841101 | BIG BASIN 1101 | BIG BASIN 110169550 | 28833.0726 | 0.26467 | 1082 | 17.916 | 19045.4687 | 20.8927 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 639 | 6 | 0.000848 | 43321101 | RINCON 1101 | RINCON 1101580 | 541.3735 | 0.005088 | 1993 | 0.33639 | 19045.8051 | 20.8876 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4775 | 99 | 0.00084088 | 163201102 | WEST POINT 1102 | WEST POINT 110277204 | 11906.8331 | 0.083247 | 1403 | 7.3986 | 19053.2036 | 20.8044 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6941 | 6 | 0.00084062 | 43061101 | COVELO 1101 | COVELO 1101536 | 15104.7289 | 0.0050437 | 1994 | 9.3856 | 19062.5893 | 20.7993 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 9097 | 64 | 0.00083763 | 254601103 | SAND CREEK 1103 | SAND CREEK 110397354 | 13531.0761 | 0.053608 | 1522 | 8.4078 | 19070.9971 | 20.7457 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7802 | 133 | 0.00083616 | 252192105 | BEAR VALLEY 2105 | BEAR VALLEY 210513430 | 21403.3287 | 0.11121 | 1322 | 13.2994 | 19084.2965 | 20.6345 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4763 | 6 | 0.00083392 | 43081101 | BIG RIVER 1101 | BIG RIVER 11013019 | 423.4937 | 0.0050035 | 1995 | 0.26315 | 19084.5597 | 20.6295 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3842 | 249 | 0.00083369 | 254151101 | AUBERRY 1101 | AUBERRY 1101R319 | 33658.5688 | 0.20759 | 1152 | 20.9145 | 19105.4741 | 20.4219 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 484 | 123 | 0.00083188 | 152481110 | BRUNSWICK 1110 | BRUNSWICK 11102664 | 12678.4586 | 0.10232 | 1346 | 7.878 | 19113.3521 | 20.3196 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2744 | 589 | 0.00082963 | 163751101 | PINE GROVE 1101 | PINE GROVE 11013170 | 64707.4468 | 0.48865 | 907 | 40.2073 | 19153.5595 | 19.8309 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 771 | 73 | 0.00082499 | 42091102 | MIRABEL 1102 | MIRABEL 1102circuit_breaker | 7538.7631 | 0.060224 | 1491 | 4.6844 | 19158.2438 | 19.7707 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4706 | 38 | 0.0008229 | 83500401 | SEACLIFF 0401 | SEACLIFF 040112946 | 3742.632 | 0.03127 | 1671 | 2.3256 | 19160.5694 | 19.7394 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8495 | 27 | 0.00081928 | 103031102 | ORO FINO 1102 | ORO FINO 1102circuit_breaker | 3368.9824 | 0.022121 | 1747 | 2.0934 | 19162.6628 | 19.7173 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2692 | 6 | 0.00081837 | 102541101 | VOLTA 1101 | VOLTA 110153118 | 15490.2629 | 0.0049102 | 2000 | 9.6252 | 19172.288 | 19.7124 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3413 | 9 | 0.00081696 | 163011101 | MARTELL 1101 | MARTELL 110198374 | 936.3607 | 0.0073527 | 1954 | 0.58183 | 19172.8698 | 19.7051 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2210 | 5 | 0.00081142 | 102911110 | WYANDOTTE 1110 | WYANDOTTE 11101952 | 417.0111 | 0.0040571 | 2023 | 0.25912 | 19173.1289 | 19.701 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8519 | 175 | 0.00080925 | 83392110 | SWIFT 2110 | SWIFT 2110XR254 | 39910.094 | 0.14162 | 1260 | 24.799 | 19197.9279 | 19.5594 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6601 | 10 | 0.00080821 | 163692101 | SALT SPRINGS 2101 | SALT SPRINGS 210110416 | 928.207 | 0.0080821 | 1938 | 0.57676 | 19198.5047 | 19.5513 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8127 | 7 | 0.0008057 | 83140401 | FELTON 0401 | FELTON 0401circuit_breaker | 3781.4684 | 0.0056399 | 1981 | 2.3497 | 19200.8544 | 19.5457 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3329 | 241 | 0.00080471 | 163751102 | PINE GROVE 1102 | PINE GROVE 110213438 | 26763.0781 | 0.19393 | 1173 | 16.6298 | 19217.4842 | 19.3517 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 362 | 134 | 0.00080462 | 82931101 | POINT MORETTI 1101 | POINT MORETTI 11015078 | 23596.4557 | 0.10782 | 1332 | 14.6622 | 19232.1463 | 19.2439 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1352 | 184 | 0.00080384 | 163451702 | FROGTOWN 1702 | FROGTOWN 170211212 | 34480.8483 | 0.14791 | 1249 | 21.4254 | 19253.5717 | 19.096 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2217 | 158 | 0.00080147 | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210152456 | 16414.576 | 0.12663 | 1285 | 10.1995 | 19263.7713 | 18.9694 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6999 | 108 | 0.00079974 | 192171101 | WILLOW CREEK 1101 | WILLOW CREEK 110129362 | 11564.4444 | 0.086372 | 1389 | 7.1858 | 19270.9571 | 18.883 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4276 | 213 | 0.00079338 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 110290548 | 29415.2854 | 0.16899 | 1214 | 18.2778 | 19289.2349 | 18.714 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2656 | 51 | 0.00079055 | 163781705 | PEORIA 1705 | PEORIA 170567898 | 5781.6377 | 0.040318 | 1602 | 3.5925 | 19292.8274 | 18.6737 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3021 | 44 | 0.00079038 | 42811113 | MONTE RIO 1113 | MONTE RIO 1113320 | 4416.0265 | 0.034777 | 1639 | 2.744 | 19295.5714 | 18.6389 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2336 | 335 | 0.00078662 | 42841112 | GUALALA 1112 | GUALALA 11121294 | 31035.4817 | 0.26352 | 1083 | 19.2845 | 19314.856 | 18.3754 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4501 | 345 | 0.00078293 | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052210 | 36677.2724 | 0.27011 | 1076 | 22.7902 | 19337.6462 | 18.1053 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3309 | 5 | 0.00077912 | 192151132 | NEWBURG 1132 | NEWBURG 11323425 | 360.086 | 0.0038956 | 2031 | 0.22375 | 19337.8699 | 18.1014 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3373 | 281 | 0.00077604 | 82021107 | LOS GATOS 1107 | LOS GATOS 110760114 | 39175.9013 | 0.21807 | 1140 | 24.3428 | 19362.2127 | 17.8833 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7389 | 280 | 0.00077341 | 103021101 | GANSNER 1101 | GANSNER 11012424 | 30151.5298 | 0.21656 | 1143 | 18.7353 | 19380.948 | 17.6668 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5208 | 544 | 0.00077179 | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210611132 | 69399.8401 | 0.41986 | 945 | 43.123 | 19424.071 | 17.2469 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3924 | 19 | 0.00077054 | 183101103 | CABRILLO 1103 | CABRILLO 1103Y10 | 7083.7808 | 0.01464 | 1834 | 4.4017 | 19428.4727 | 17.2323 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2032 | 206 | 0.00076827 | 82841102 | BIG BASIN 1102 | BIG BASIN 11025066 | 23248.0337 | 0.15826 | 1228 | 14.4457 | 19442.9183 | 17.074 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2405 | 62 | 0.00076233 | 103491101 | MC ARTHUR 1101 | MC ARTHUR 11011546 | 20599.9851 | 0.047265 | 1565 | 12.8002 | 19455.7186 | 17.0267 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 146 | 6 | 0.0007611 | 162821702 | STANISLAUS 1702 | STANISLAUS 17026028 | 8608.783 | 0.0045666 | 2010 | 5.3492 | 19461.0678 | 17.0222 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3152 | 300 | 0.00075835 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 1103H82 | 49003.1871 | 0.22751 | 1125 | 30.4492 | 19491.517 | 16.7947 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5046 | 148 | 0.00075636 | 152431102 | SHADY GLEN 1102 | SHADY GLEN 110248894 | 13914.1946 | 0.11194 | 1317 | 8.6459 | 19500.1628 | 16.6827 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 317 | 181 | 0.00075423 | 153081110 | PLACERVILLE 1110 | PLACERVILLE 1110circuit_breaker | 18295.3344 | 0.13652 | 1270 | 11.3682 | 19511.531 | 16.5462 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8441 | 95 | 0.00075205 | 182631104 | SAN LUIS OBISPO 1104 | SAN LUIS OBISPO 11042293 | 14494.4535 | 0.071445 | 1446 | 9.0064 | 19520.5375 | 16.4748 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7746 | 71 | 0.00074984 | 153662102 | APPLE HILL 2102 | APPLE HILL 210289934 | 9059.6456 | 0.053239 | 1524 | 5.6294 | 19526.1669 | 16.4215 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4225 | 35 | 0.00074936 | 42261101 | BOLINAS 1101 | BOLINAS 11011236 | 5655.0294 | 0.026227 | 1709 | 3.5139 | 19529.6807 | 16.3953 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5583 | 110 | 0.00074579 | 43182103 | BELLEVUE 2103 | BELLEVUE 2103646 | 12247.7458 | 0.082037 | 1411 | 7.6104 | 19537.2911 | 16.3133 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6865 | 93 | 0.00074533 | 152481106 | BRUNSWICK 1106 | BRUNSWICK 110663124 | 9428.9995 | 0.069315 | 1454 | 5.8589 | 19543.15 | 16.2439 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1713 | 271 | 0.00074288 | 163661701 | MIWUK 1701 | MIWUK 1701circuit_breaker | 28710.6531 | 0.20132 | 1157 | 17.84 | 19560.99 | 16.0426 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2243 | 249 | 0.00073122 | 252192105 | BEAR VALLEY 2105 | BEAR VALLEY 210521160 | 38250.3476 | 0.18207 | 1189 | 23.7677 | 19584.7577 | 15.8606 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 108 | 306 | 0.00073103 | 152762102 | EL DORADO PH 2102 | EL DORADO PH 2102circuit_breaker | 32849.8127 | 0.2237 | 1129 | 20.4119 | 19605.1696 | 15.6369 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1759 | 92 | 0.00072996 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210510912 | 8140.064 | 0.067156 | 1466 | 5.058 | 19610.2276 | 15.5697 | 4.5447 | 0.067156 | 1 | #N/A | 15.5697 | #N/A
North Coast | 1184 | 140 | 0.0007275 | 42251101 | HOPLAND 1101 | HOPLAND 1101960 | 23874.8083 | 0.10185 | 1347 | 14.8351 | 19625.0627 | 15.4679 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7767 | 15 | 0.00072555 | 83040401 | BEN LOMOND 0401 | BEN LOMOND 04015144 | 6409.4899 | 0.010883 | 1882 | 3.9827 | 19629.0454 | 15.457 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 9599 | 37 | 0.00072418 | 252931102 | TEJON 1102 | TEJON 11023760 | 10548.2717 | 0.026795 | 1703 | 6.5544 | 19635.5998 | 15.4302 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 9056 | 6 | 0.00072162 | 83531108 | MC KEE 1108 | MC KEE 110870535 | 1019.3465 | 0.0043297 | 2015 | 0.63339 | 19636.2331 | 15.4258 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5794 | 68 | 0.00071494 | 14161108 | ROSSMOOR 1108 | ROSSMOOR 110837848 | 9580.5994 | 0.048616 | 1550 | 5.9531 | 19642.1863 | 15.3772 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4028 | 8 | 0.00070606 | 163351705 | CURTIS 1705 | CURTIS 170565908 | 21139.8755 | 0.0056485 | 1980 | 13.1357 | 19655.322 | 15.3716 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1143 | 417 | 0.00070604 | 252192105 | BEAR VALLEY 2105 | BEAR VALLEY 21059560 | 58396.3744 | 0.29442 | 1046 | 36.2858 | 19691.6078 | 15.0772 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8952 | 3 | 0.00070597 | 42042101 |  | circuit_breaker | 305.1807 | 0.0021179 | 2095 | 0.18963 | 19691.7974 | 15.075 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2083 | 43 | 0.00070297 | 42481101 | IGNACIO 1101 | IGNACIO 11011300 | 4134.7438 | 0.030228 | 1678 | 2.5692 | 19694.3666 | 15.0448 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4021 | 45 | 0.00070211 | 254452101 | MARIPOSA 2101 | MARIPOSA 21014410 | 36631.6496 | 0.031595 | 1668 | 22.7618 | 19717.1285 | 15.0132 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8971 | 19 | 0.00069997 | 43381101 | POINT ARENA 1101 | POINT ARENA 11011296 | 4384.7382 | 0.013299 | 1848 | 2.7245 | 19719.853 | 14.9999 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1459 | 310 | 0.00069965 | 163351702 | CURTIS 1702 | CURTIS 1702circuit_breaker | 35160.9523 | 0.21689 | 1142 | 21.848 | 19741.701 | 14.783 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 593 | 3 | 0.00069322 | 152701110 | BELL 1110 | BELL 111056214 | 144.7507 | 0.0020797 | 2096 | 0.089944 | 19741.7909 | 14.781 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8101 | 62 | 0.00069313 | 83481110 | STELLING 1110 | STELLING 11109265 | 9183.0563 | 0.042974 | 1592 | 5.7061 | 19747.497 | 14.738 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6123 | 61 | 0.00069166 | 43021101 | WOODACRE 1101 | WOODACRE 11011238 | 5891.9294 | 0.042192 | 1594 | 3.6611 | 19751.1581 | 14.6958 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7724 | 84 | 0.00068742 | 101321101 | PIT NO 5 1101 | PIT NO 5 11011606 | 8892.9459 | 0.057743 | 1504 | 5.5258 | 19756.6839 | 14.638 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8544 | 5 | 0.00067396 | 42991105 | LAS GALLINAS A 1105 | LAS GALLINAS A 1105circuit_breaker | 658.6815 | 0.0033698 | 2045 | 0.40929 | 19757.0932 | 14.6347 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5030 | 240 | 0.00067305 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 21065020 | 24453.2376 | 0.16153 | 1226 | 15.1945 | 19772.2877 | 14.4731 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3487 | 54 | 0.00067269 | 254421103 | OAKHURST 1103 | OAKHURST 110377384 | 7607.5657 | 0.036325 | 1629 | 4.7271 | 19777.0149 | 14.4368 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2705 | 122 | 0.00067236 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 11036018 | 24500.2785 | 0.082028 | 1412 | 15.2238 | 19792.2386 | 14.3548 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 976 | 334 | 0.00067074 | 103081105 | BUTTE 1105 | BUTTE 1105134600 | 44940.5828 | 0.22403 | 1128 | 27.9248 | 19820.1634 | 14.1308 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7181 | 22 | 0.00066452 | 183101103 | CABRILLO 1103 | CABRILLO 1103Y46 | 37171.7089 | 0.014619 | 1835 | 23.0974 | 19843.2608 | 14.1161 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9158 | 39 | 0.00066238 | 102541102 | VOLTA 1102 | VOLTA 110293418 | 4264.808 | 0.025833 | 1714 | 2.65 | 19845.9108 | 14.0903 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6725 | 80 | 0.00065967 | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 210297924 | 8204.8506 | 0.052773 | 1527 | 5.0983 | 19851.0091 | 14.0375 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1114 | 287 | 0.00065898 | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LB44 | 30802.2438 | 0.18913 | 1178 | 19.1396 | 19870.1487 | 13.8484 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3772 | 22 | 0.00065886 | 163751102 | PINE GROVE 1102 | PINE GROVE 11021765 | 2330.5339 | 0.014495 | 1837 | 1.4481 | 19871.5969 | 13.8339 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7719 | 40 | 0.00065815 | 163661702 | MIWUK 1702 | MIWUK 1702S1547 | 4436.0854 | 0.026326 | 1708 | 2.7565 | 19874.3533 | 13.8076 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5933 | 78 | 0.00065633 | 163351702 | CURTIS 1702 | CURTIS 17029111 | 9135.0634 | 0.051194 | 1536 | 5.6763 | 19880.0296 | 13.7564 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6161 | 66 | 0.00065544 | 254061102 | DUNLAP 1102 | DUNLAP 1102circuit_breaker | 10788.4174 | 0.043259 | 1588 | 6.7036 | 19886.7332 | 13.7131 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3589 | 91 | 0.00065008 | 14241101 | SUNOL 1101 | SUNOL 1101MR297 | 9415.923 | 0.059157 | 1499 | 5.8508 | 19892.584 | 13.654 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4356 | 89 | 0.00064859 | 163661702 | MIWUK 1702 | MIWUK 170238218 | 17457.0622 | 0.057725 | 1505 | 10.8473 | 19903.4313 | 13.5963 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6273 | 133 | 0.00064645 | 163201101 | WEST POINT 1101 | WEST POINT 110113444 | 26771.8299 | 0.085978 | 1392 | 16.6352 | 19920.0665 | 13.5103 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8207 | 128 | 0.00064352 | 42291101 | OLEMA 1101 | OLEMA 1101602 | 25492.7395 | 0.082371 | 1408 | 15.8404 | 19935.907 | 13.4279 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8087 | 31 | 0.00064242 | 82021107 | LOS GATOS 1107 | LOS GATOS 110760024 | 6397.1295 | 0.019915 | 1767 | 3.975 | 19939.882 | 13.408 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8278 | 39 | 0.00063781 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210533542 | 3984.6462 | 0.024875 | 1722 | 2.4759 | 19942.3579 | 13.3831 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1363 | 65 | 0.00063702 | 162821701 | STANISLAUS 1701 | STANISLAUS 17011331 | 7071.5091 | 0.041407 | 1596 | 4.394 | 19946.7519 | 13.3417 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1390 | 3 | 0.0024739 | 163351704 | CURTIS 1704 | CURTIS 17048140 | 42473.8563 | 0.0074216 | 1134 | 26.392 | 19973.1439 | 13.3343 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Valley | 1390 | 347 | 0.00061488 | 163351704 | CURTIS 1704 | CURTIS 17048140 | 42473.8563 | 0.21336 | 1134 | 26.392 | 19999.536 | 13.1209 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Coast | 5506 | 60 | 0.00063079 | 82841102 | BIG BASIN 1102 | BIG BASIN 110212758 | 9878.3441 | 0.037848 | 1618 | 6.1381 | 20005.6741 | 13.0831 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3752 | 221 | 0.00062993 | 42291101 | OLEMA 1101 | OLEMA 110150396 | 20493.6346 | 0.13922 | 1266 | 12.7342 | 20018.4082 | 12.9439 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7298 | 54 | 0.00062929 | 43381101 | POINT ARENA 1101 | POINT ARENA 11012637 | 6500.6025 | 0.033982 | 1644 | 4.0393 | 20022.4475 | 12.9099 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1696 | 26 | 0.00062895 | 42261101 | BOLINAS 1101 | BOLINAS 1101circuit_breaker | 3408.2951 | 0.016353 | 1814 | 2.1178 | 20024.5653 | 12.8935 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4481 | 167 | 0.0006255 | 83371107 | SARATOGA 1107 | SARATOGA 1107413816 | 17947.1279 | 0.10446 | 1340 | 11.1518 | 20035.7172 | 12.7891 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1200 | 44 | 0.00062518 | 14241101 | SUNOL 1101 | SUNOL 1101MR298 | 8010.2959 | 0.027508 | 1700 | 4.9774 | 20040.6945 | 12.7616 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1966 | 51 | 0.00062056 | 42011108 | SAN RAFAEL 1108 | SAN RAFAEL 110839156 | 5556.6949 | 0.031649 | 1667 | 3.4528 | 20044.1473 | 12.7299 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2503 | 947 | 0.00061759 | 152481106 | BRUNSWICK 1106 | BRUNSWICK 110651486 | 91172.3296 | 0.58486 | 863 | 56.6518 | 20100.7991 | 12.1451 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2536 | 41 | 0.00061574 | 43081101 | BIG RIVER 1101 | BIG RIVER 110155402 | 3203.2885 | 0.025245 | 1717 | 1.9904 | 20102.7896 | 12.1198 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3288 | 9 | 0.00061547 | 152031101 | GRASS VALLEY 1101 | GRASS VALLEY 1101circuit_breaker | 1152.0117 | 0.0055392 | 1983 | 0.71583 | 20103.5054 | 12.1143 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7978 | 2 | 0.00061364 | 63601111 | VACAVILLE 1111 | VACAVILLE 111112342 | 237.1733 | 0.0012273 | 2144 | 0.14737 | 20103.6528 | 12.113 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5592 | 6 | 0.00061154 | 83040401 | BEN LOMOND 0401 | BEN LOMOND 04015206 | 11401.1639 | 0.0036692 | 2038 | 7.0844 | 20110.7371 | 12.1094 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4594 | 75 | 0.00060942 | 43081101 | BIG RIVER 1101 | BIG RIVER 11011286 | 6546.1056 | 0.045707 | 1577 | 4.0676 | 20114.8047 | 12.0637 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8009 | 40 | 0.00060897 | 183071101 | PERRY 1101 | PERRY 110185870 | 14444.7623 | 0.024359 | 1727 | 8.9756 | 20123.7802 | 12.0393 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6483 | 275 | 0.0006014 | 182541101 | ATASCADERO 1101 | ATASCADERO 1101A50 | 30172.5253 | 0.16538 | 1221 | 18.7483 | 20142.5286 | 11.8739 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 969 | 260 | 0.00059828 | 254421103 | OAKHURST 1103 | OAKHURST 110310140 | 27059.5406 | 0.15555 | 1231 | 16.814 | 20159.3426 | 11.7184 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3255 | 76 | 0.00059569 | 103031102 | ORO FINO 1102 | ORO FINO 110265932 | 6996.2918 | 0.045272 | 1581 | 4.3473 | 20163.6899 | 11.6731 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1421 | 187 | 0.00059275 | 163661701 | MIWUK 1701 | MIWUK 1701953336 | 19079.6137 | 0.11084 | 1325 | 11.8555 | 20175.5454 | 11.5623 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1559 | 290 | 0.00058909 | 163011101 | MARTELL 1101 | MARTELL 110111244 | 33683.9339 | 0.17084 | 1209 | 20.9302 | 20196.4756 | 11.3914 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7329 | 115 | 0.00058799 | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 110190730 | 13390.7322 | 0.067619 | 1462 | 8.3206 | 20204.7962 | 11.3238 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5177 | 58 | 0.00058724 | 42851121 | FORT ROSS 1121 | FORT ROSS 1121560 | 8402.379 | 0.03406 | 1643 | 5.221 | 20210.0172 | 11.2897 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1655 | 214 | 0.00058422 | 192171103 | WILLOW CREEK 1103 | WILLOW CREEK 110347966 | 27180.6372 | 0.12502 | 1288 | 16.8893 | 20226.9065 | 11.1647 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2996 | 3 | 0.00058327 | 14402108 | LAS POSITAS 2108 | LAS POSITAS 2108MR190 | 1015.7929 | 0.0017498 | 2116 | 0.63118 | 20227.5377 | 11.163 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8841 | 13 | 0.000576 | 252192101 | BEAR VALLEY 2101 | BEAR VALLEY 210110019 | 3187.4941 | 0.007488 | 1950 | 1.9806 | 20229.5183 | 11.1555 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7174 | 25 | 0.00057521 | 192381102 | EEL RIVER 1102 | EEL RIVER 11021902 | 9656.571 | 0.01438 | 1841 | 6.0003 | 20235.5186 | 11.1411 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2897 | 8 | 0.00057168 | 83432101 | HICKS 2101 | HICKS 2101XR162 | 1339.293 | 0.0045734 | 2009 | 0.8322 | 20236.3508 | 11.1365 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8574 | 84 | 0.00057063 | 103104401 | SPANISH CREEK 4401 | SPANISH CREEK 4401circuit_breaker | 9502.8761 | 0.047933 | 1557 | 5.9048 | 20242.2556 | 11.0886 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5012 | 392 | 0.00056968 | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 1101502 | 60118.0927 | 0.22332 | 1132 | 37.3556 | 20279.6112 | 10.8653 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3962 | 71 | 0.0005685 | 43311108 | KONOCTI 1108 | KONOCTI 11081278 | 7722.6194 | 0.040363 | 1601 | 4.7986 | 20284.4099 | 10.8249 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1855 | 213 | 0.00056517 | 83692104 | ROB ROY 2104 | ROB ROY 2104circuit_breaker | 22978.5798 | 0.12038 | 1295 | 14.2782 | 20298.6881 | 10.7045 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1861 | 49 | 0.00056491 | 24101102 | HALF MOON BAY 1102 | HALF MOON BAY 11028848 | 4923.8197 | 0.027681 | 1697 | 3.0595 | 20301.7476 | 10.6769 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3304 | 51 | 0.00055682 | 43351106 | LUCERNE 1106 | LUCERNE 110638436 | 7130.3909 | 0.028398 | 1690 | 4.4306 | 20306.1782 | 10.6485 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6026 | 88 | 0.00055459 | 42811113 | MONTE RIO 1113 | MONTE RIO 1113202 | 8479.0365 | 0.048804 | 1548 | 5.2686 | 20311.4468 | 10.5996 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8106 | 98 | 0.00055442 | 103031102 | ORO FINO 1102 | ORO FINO 1102127563 | 11105.9314 | 0.054333 | 1520 | 6.9009 | 20318.3478 | 10.5453 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1580 | 117 | 0.00055409 | 42811113 | MONTE RIO 1113 | MONTE RIO 11133970 | 11846.1263 | 0.064828 | 1477 | 7.3608 | 20325.7086 | 10.4805 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2478 | 68 | 0.00055283 | 163661702 | MIWUK 1702 | MIWUK 17028130 | 15891.4897 | 0.037592 | 1621 | 9.8745 | 20335.5831 | 10.4429 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4731 | 112 | 0.00055278 | 153081112 | PLACERVILLE 1112 | PLACERVILLE 1112circuit_breaker | 13371.697 | 0.061911 | 1486 | 8.3088 | 20343.8919 | 10.381 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6867 | 232 | 0.00055231 | 24131103 | MENLO 1103 | MENLO 11038512 | 26938.1265 | 0.12814 | 1281 | 16.7386 | 20360.6305 | 10.2528 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9113 | 14 | 0.00055052 | 24131102 | MENLO 1102 | MENLO 11028896 | 1013.7193 | 0.0077072 | 1943 | 0.6299 | 20361.2604 | 10.2451 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5601 | 21 | 0.00054983 | 183071101 | PERRY 1101 | PERRY 1101circuit_breaker | 4085.1746 | 0.011547 | 1871 | 2.5384 | 20363.7988 | 10.2336 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8189 | 59 | 0.00054947 | 103491101 | MC ARTHUR 1101 | MC ARTHUR 11011544 | 22817.5943 | 0.032419 | 1658 | 14.1782 | 20377.977 | 10.2012 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5779 | 134 | 0.00054651 | 83242111 | MORGAN HILL 2111 | MORGAN HILL 2111XR292 | 17517.5113 | 0.073232 | 1436 | 10.8849 | 20388.8618 | 10.1279 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2783 | 10 | 0.00054599 | 24131102 | MENLO 1102 | MENLO 11029110 | 1403.503 | 0.0054599 | 1986 | 0.8721 | 20389.7339 | 10.1225 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2742 | 14 | 0.00054407 | 13501111 | JARVIS 1111 | JARVIS 1111MR121 | 1635.8418 | 0.007617 | 1946 | 1.0165 | 20390.7504 | 10.1149 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6613 | 109 | 0.00054403 | 83041101 | BEN LOMOND 1101 | BEN LOMOND 110196738 | 10935.49 | 0.0593 | 1498 | 6.795 | 20397.5454 | 10.0556 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3937 | 260 | 0.00054352 | 103021101 | GANSNER 1101 | GANSNER 11012006 | 27571.1883 | 0.14132 | 1263 | 17.1319 | 20414.6773 | 9.9142 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7366 | 3 | 0.00054333 | 152481107 | BRUNSWICK 1107 | BRUNSWICK 110765574 | 445.925 | 0.00163 | 2122 | 0.27708 | 20414.9544 | 9.9126 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4416 | 435 | 0.00053943 | 82021107 | LOS GATOS 1107 | LOS GATOS 110760118 | 42371.3391 | 0.23465 | 1115 | 26.3283 | 20441.2827 | 9.678 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6453 | 26 | 0.00053807 | 43381101 | POINT ARENA 1101 | POINT ARENA 1101476 | 4407.3314 | 0.01399 | 1843 | 2.7386 | 20444.0213 | 9.664 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1786 | 18 | 0.00053702 | 183011101 | MORRO BAY 1101 | MORRO BAY 1101V66 | 5689.205 | 0.0096664 | 1903 | 3.5351 | 20447.5564 | 9.6543 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3996 | 35 | 0.00053574 | 42811111 | MONTE RIO 1111 | MONTE RIO 1111140 | 4235.2908 | 0.018751 | 1777 | 2.6317 | 20450.1881 | 9.6356 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3904 | 27 | 0.00053301 | 43321101 | RINCON 1101 | RINCON 1101576 | 4105.0155 | 0.014391 | 1840 | 2.5507 | 20452.7388 | 9.6212 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2888 | 509 | 0.00053262 | 152261103 | DIAMOND SPRINGS 1103 | DIAMOND SPRINGS 1103circuit_breaker | 52640.7509 | 0.27111 | 1074 | 32.7094 | 20485.4483 | 9.3501 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7175 | 49 | 0.00053172 | 102211103 | BUCKS CREEK 1103 | BUCKS CREEK 11031131 | 4424.1224 | 0.026054 | 1711 | 2.749 | 20488.1973 | 9.324 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 177 | 126 | 0.00053103 | 152691104 | HIGGINS 1104 | HIGGINS 11041374 | 12504.4738 | 0.06691 | 1468 | 7.7699 | 20495.9672 | 9.2571 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7873 | 16 | 0.00053027 | 42811112 | MONTE RIO 1112 | MONTE RIO 1112999 | 1406.4428 | 0.0084844 | 1929 | 0.87392 | 20496.8411 | 9.2486 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 9933 | 1 | 0.0005296 | 163781704 | PEORIA 1704 | PEORIA 170492888 | 400.6025 | 0.0005296 | 2192 | 0.24892 | 20497.0901 | 9.2481 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7811 | 185 | 0.00052817 | 103132101 | CRESCENT MILLS 2101 | CRESCENT MILLS 21012562 | 25377.9444 | 0.097711 | 1357 | 15.7691 | 20512.8592 | 9.1504 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 841 | 69 | 0.0005265 | 163692101 | SALT SPRINGS 2101 | SALT SPRINGS 21011216 | 8899.3047 | 0.036328 | 1628 | 5.5298 | 20518.389 | 9.114 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6139 | 68 | 0.00052544 | 83192101 | GREEN VALLEY 2101 | GREEN VALLEY 210136820 | 7189.3721 | 0.03573 | 1631 | 4.4673 | 20522.8562 | 9.0783 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 659 | 317 | 0.00052282 | 83622104 | CAMP EVERS 2104 | CAMP EVERS 21045096 | 32780.5456 | 0.16573 | 1219 | 20.3689 | 20543.2251 | 8.9126 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5572 | 183 | 0.00052231 | 83192101 | GREEN VALLEY 2101 | GREEN VALLEY 210111054 | 38401.1556 | 0.095583 | 1362 | 23.8614 | 20567.0865 | 8.817 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9136 | 41 | 0.00051912 | 14241101 | SUNOL 1101 | SUNOL 1101MR387 | 7477.4807 | 0.021284 | 1755 | 4.6463 | 20571.7328 | 8.7957 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2412 | 166 | 0.00051779 | 254421103 | OAKHURST 1103 | OAKHURST 110310190 | 18572.0473 | 0.085952 | 1393 | 11.5401 | 20583.2729 | 8.7098 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 9302 | 40 | 0.00051449 | 252501101 | BALCH NO 1 1101 | BALCH NO 1 1101R372 | 9846.4194 | 0.020579 | 1763 | 6.1183 | 20589.3912 | 8.6892 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5284 | 34 | 0.00051011 | 163451701 | FROGTOWN 1701 | FROGTOWN 1701L3361 | 3015.6838 | 0.017344 | 1795 | 1.8739 | 20591.265 | 8.6718 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3938 | 54 | 0.0005098 | 254421103 | OAKHURST 1103 | OAKHURST 11035120 | 10236.3208 | 0.027529 | 1699 | 6.3606 | 20597.6256 | 8.6443 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1866 | 96 | 0.00050952 | 153081111 | PLACERVILLE 1111 | PLACERVILLE 1111circuit_breaker | 10305.9598 | 0.048914 | 1547 | 6.4038 | 20604.0294 | 8.5954 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8506 | 19 | 0.00050897 | 163781705 | PEORIA 1705 | PEORIA 170570198 | 3727.5999 | 0.0096704 | 1902 | 2.3162 | 20606.3456 | 8.5857 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1086 | 8 | 0.00050831 | 152461104 | PLACER 1104 | PLACER 110451732 | 825.7758 | 0.0040665 | 2022 | 0.51311 | 20606.8587 | 8.5817 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8891 | 86 | 0.00050107 | 82841102 | BIG BASIN 1102 | BIG BASIN 11028403 | 7917.119 | 0.043092 | 1590 | 4.9195 | 20611.7782 | 8.5386 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1412 | 114 | 0.00049975 | 163661701 | MIWUK 1701 | MIWUK 170111800 | 15184.802 | 0.056971 | 1506 | 9.4354 | 20621.2136 | 8.4816 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5603 | 89 | 0.00049813 | 83252107 | PAUL SWEET 2107 | PAUL SWEET 210710986 | 13450.8089 | 0.044334 | 1584 | 8.3579 | 20629.5715 | 8.4373 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5660 | 159 | 0.00049416 | 42291101 | OLEMA 1101 | OLEMA 11011318 | 13978.4041 | 0.078571 | 1425 | 8.6858 | 20638.2573 | 8.3587 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 82 | 225 | 0.00049415 | 152241101 | HALSEY 1101 | HALSEY 11011704 | 21258.1613 | 0.11118 | 1323 | 13.2092 | 20651.4665 | 8.2475 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8273 | 34 | 0.0004939 | 254061103 | DUNLAP 1103 | DUNLAP 1103circuit_breaker | 8988.316 | 0.016793 | 1805 | 5.5851 | 20657.0516 | 8.2307 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 753 | 19 | 0.00048998 | 182811103 | SISQUOC 1103 | SISQUOC 1103M98 | 11235.2762 | 0.0093097 | 1915 | 6.9813 | 20664.0329 | 8.2214 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2669 | 142 | 0.00048991 | 163661702 | MIWUK 1702 | MIWUK 1702circuit_breaker | 16506.2205 | 0.069568 | 1453 | 10.2565 | 20674.2894 | 8.1518 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5340 | 130 | 0.00048935 | 192101101 | MAPLE CREEK 1101 | MAPLE CREEK 1101circuit_breaker | 15254.5949 | 0.063615 | 1481 | 9.4788 | 20683.7681 | 8.0882 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6143 | 12 | 0.00048899 | 152481105 | BRUNSWICK 1105 | BRUNSWICK 110584480 | 7615.7819 | 0.0058678 | 1975 | 4.7322 | 20688.5004 | 8.0824 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8004 | 26 | 0.00048416 | 102041104 | NOTRE DAME 1104 | NOTRE DAME 11042537 | 8206.2423 | 0.012588 | 1859 | 5.0991 | 20693.5995 | 8.0698 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6787 | 374 | 0.00048057 | 102971111 | SYCAMORE CREEK 1111 | SYCAMORE CREEK 11112268 | 35773.7446 | 0.17973 | 1193 | 22.2288 | 20715.8282 | 7.89 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7506 | 20 | 0.00047746 | 12101102 | OAKLAND K 1102 | OAKLAND K 110217430 | 2362.1685 | 0.0095491 | 1906 | 1.4678 | 20717.296 | 7.8805 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5834 | 71 | 0.00047137 | 103132101 | CRESCENT MILLS 2101 | CRESCENT MILLS 21012230 | 8832.0855 | 0.033467 | 1651 | 5.488 | 20722.784 | 7.847 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1833 | 97 | 0.00046827 | 152691104 | HIGGINS 1104 | HIGGINS 1104842642 | 9304.2839 | 0.045422 | 1580 | 5.7814 | 20728.5654 | 7.8016 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3984 | 49 | 0.00046333 | 182981102 | JOLON 1102 | JOLON 11027040 | 31780.5056 | 0.022703 | 1741 | 19.7475 | 20748.3129 | 7.7789 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2936 | 200 | 0.0004631 | 152431101 | SHADY GLEN 1101 | SHADY GLEN 110132726 | 20147.5271 | 0.09262 | 1368 | 12.5191 | 20760.832 | 7.6863 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 937 | 152 | 0.00046219 | 162821701 | STANISLAUS 1701 | STANISLAUS 170179826 | 16403.2639 | 0.070253 | 1450 | 10.1925 | 20771.0245 | 7.616 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 669 | 442 | 0.00046108 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 210612760 | 42934.8809 | 0.2038 | 1155 | 26.6785 | 20797.703 | 7.4122 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2552 | 107 | 0.00045986 | 24080401 | EMERALD LAKE 0401 | EMERALD LAKE 0401circuit_breaker | 23419.0309 | 0.049205 | 1544 | 14.5519 | 20812.2549 | 7.363 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4312 | 30 | 0.00045777 | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11053611 | 2597.3823 | 0.013733 | 1847 | 1.6139 | 20813.8689 | 7.3493 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5700 | 71 | 0.00045718 | 14091108 | CASTRO VALLEY 1108 | CASTRO VALLEY 1108MR243 | 8931.2655 | 0.03246 | 1657 | 5.5496 | 20819.4185 | 7.3168 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1146 | 63 | 0.00045711 | 82841101 | BIG BASIN 1101 | BIG BASIN 110195690 | 6270.3435 | 0.028798 | 1686 | 3.8962 | 20823.3147 | 7.288 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5533 | 213 | 0.00045595 | 42771115 | UKIAH 1115 | UKIAH 1115circuit_breaker | 26755.7552 | 0.097118 | 1358 | 16.6253 | 20839.9399 | 7.1909 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2902 | 38 | 0.00045464 | 82841102 | BIG BASIN 1102 | BIG BASIN 110276752 | 4328.6941 | 0.017276 | 1796 | 2.6897 | 20842.6297 | 7.1736 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1683 | 241 | 0.00045324 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 1103H80 | 31887.8354 | 0.10923 | 1329 | 19.8142 | 20862.4439 | 7.0644 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8479 | 24 | 0.00045118 | 182941102 | OTTER 1102 | OTTER 11022012 | 14639.7556 | 0.010828 | 1884 | 9.0967 | 20871.5406 | 7.0536 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5093 | 153 | 0.00045007 | 254601103 | SAND CREEK 1103 | SAND CREEK 11037110 | 29837.817 | 0.068861 | 1456 | 18.5404 | 20890.0809 | 6.9847 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 994 | 107 | 0.00045418 | 14091106 | CASTRO VALLEY 1106 | CASTRO VALLEY 1106MR337 | 13193.9222 | 0.048598 | 1551 | 8.1983 | 20898.2792 | 6.9361 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Coast | 994 | 1 | 2.0361e-06 | 14091106 | CASTRO VALLEY 1106 | CASTRO VALLEY 1106MR337 | 13193.9222 | 2.0361e-06 | 1551 | 8.1983 | 20906.4776 | 6.9361 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 2359 | 35 | 0.00044463 | 42811113 | MONTE RIO 1113 | MONTE RIO 1113477 | 2831.9084 | 0.015562 | 1821 | 1.7597 | 20908.2372 | 6.9205 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7257 | 54 | 0.00044462 | 182731102 | RESERVATION ROAD 1102 | RESERVATION ROAD 11023030 | 10130.7204 | 0.024009 | 1730 | 6.2949 | 20914.5322 | 6.8965 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7625 | 19 | 0.00044296 | 183071101 | PERRY 1101 | PERRY 1101W26 | 4390.419 | 0.0084163 | 1931 | 2.7281 | 20917.2602 | 6.8881 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7613 | 9 | 0.00043887 | 13801105 | MORAGA 1105 | MORAGA 110531512 | 2816.3842 | 0.0039498 | 2027 | 1.75 | 20919.0103 | 6.8842 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2187 | 50 | 0.00043641 | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210136764 | 4920.5157 | 0.021821 | 1750 | 3.0575 | 20922.0677 | 6.8624 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7758 | 78 | 0.00043309 | 162821701 | STANISLAUS 1701 | STANISLAUS 17017144 | 7457.9017 | 0.033781 | 1649 | 4.6341 | 20926.7019 | 6.8286 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5891 | 213 | 0.00042761 | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 110180930 | 29611.6951 | 0.091082 | 1375 | 18.3998 | 20945.1017 | 6.7375 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6506 | 29 | 0.00042521 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 21055188 | 3191.7712 | 0.012331 | 1862 | 1.9833 | 20947.085 | 6.7252 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8447 | 126 | 0.00042334 | 14091106 | CASTRO VALLEY 1106 | CASTRO VALLEY 11068971 | 12641.384 | 0.053341 | 1523 | 7.855 | 20954.94 | 6.6718 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3122 | 57 | 0.00042324 | 43311108 | KONOCTI 1108 | KONOCTI 1108950 | 9061.9141 | 0.024125 | 1728 | 5.6308 | 20960.5708 | 6.6477 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2458 | 212 | 0.00042216 | 83692104 | ROB ROY 2104 | ROB ROY 210410714 | 22255.4392 | 0.089499 | 1379 | 13.8289 | 20974.3997 | 6.5582 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3778 | 120 | 0.0004212 | 42761101 | FORT BRAGG A 1101 | FORT BRAGG A 11014698 | 12907.3842 | 0.050544 | 1538 | 8.0203 | 20982.4199 | 6.5077 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7960 | 130 | 0.00042095 | 163751101 | PINE GROVE 1101 | PINE GROVE 110194936 | 14913.8447 | 0.054724 | 1517 | 9.267 | 20991.687 | 6.4529 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7881 | 48 | 0.0004203 | 252192105 | BEAR VALLEY 2105 | BEAR VALLEY 21054609 | 7321.9227 | 0.020174 | 1764 | 4.5496 | 20996.2366 | 6.4328 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6526 | 120 | 0.00042021 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 1103695411 | 13109.0272 | 0.050425 | 1540 | 8.1456 | 21004.3822 | 6.3823 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7052 | 9 | 0.00041908 | 254452102 | MARIPOSA 2102 | MARIPOSA 2102594143 | 751.6885 | 0.0037717 | 2035 | 0.46708 | 21004.8492 | 6.3786 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3649 | 41 | 0.00041755 | 163751101 | PINE GROVE 1101 | PINE GROVE 110152088 | 4068.7441 | 0.017119 | 1799 | 2.5282 | 21007.3774 | 6.3614 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8802 | 14 | 0.00041583 | 103381101 | FRENCH GULCH 1101 | FRENCH GULCH 11011892 | 4073.3832 | 0.0058216 | 1976 | 2.5311 | 21009.9085 | 6.3556 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1120 | 60 | 0.00041564 | 102831105 | PARADISE 1105 | PARADISE 1105circuit_breaker | 19516.665 | 0.024939 | 1719 | 12.1271 | 21022.0356 | 6.3307 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7770 | 8 | 0.00041158 | 42091102 | MIRABEL 1102 | MIRABEL 11021139 | 2923.0188 | 0.0032926 | 2048 | 1.8163 | 21023.8519 | 6.3274 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1341 | 22 | 0.00040811 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 11036014 | 6646.3728 | 0.0089784 | 1920 | 4.1299 | 21027.9818 | 6.3184 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5922 | 58 | 0.00040762 | 152481105 | BRUNSWICK 1105 | BRUNSWICK 1105circuit_breaker | 10665.1471 | 0.023642 | 1734 | 6.627 | 21034.6088 | 6.2948 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6997 | 78 | 0.00040691 | 83371107 | SARATOGA 1107 | SARATOGA 1107167792 | 7328.1795 | 0.031739 | 1665 | 4.5535 | 21039.1623 | 6.263 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9083 | 64 | 0.0004058 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 11036065 | 9622.0817 | 0.025971 | 1713 | 5.9789 | 21045.1412 | 6.2371 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3024 | 1 | 0.00040553 | 253671103 | PANOCHE 1103 | PANOCHE 11034016 | 3776.8409 | 0.00040553 | 2209 | 2.3468 | 21047.488 | 6.2366 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6045 | 23 | 0.00040541 | 163781701 | PEORIA 1701 | PEORIA 170176030 | 8122.6361 | 0.0093245 | 1914 | 5.0472 | 21052.5352 | 6.2273 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 329 | 89 | 0.00040509 | 182771102 | CAMBRIA 1102 | CAMBRIA 1102circuit_breaker | 25658.8486 | 0.036053 | 1630 | 15.9437 | 21068.4788 | 6.1913 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6620 | 15 | 0.00040507 | 42291101 | OLEMA 1101 | OLEMA 11011686 | 1962.0765 | 0.0060761 | 1972 | 1.2192 | 21069.698 | 6.1852 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6063 | 69 | 0.00040499 | 13801101 | MORAGA 1101 | MORAGA 110118216 | 7868.0142 | 0.027944 | 1694 | 4.889 | 21074.587 | 6.1572 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1009 | 278 | 0.00040456 | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 21023142 | 27128.7333 | 0.11247 | 1316 | 16.857 | 21091.444 | 6.0448 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1012 | 204 | 0.00040396 | 102541102 | VOLTA 1102 | VOLTA 110253130 | 22286.621 | 0.082407 | 1407 | 13.8483 | 21105.2922 | 5.9624 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 739 | 94 | 0.00040385 | 42841112 | GUALALA 1112 | GUALALA 1112662 | 8946.2004 | 0.037962 | 1613 | 5.5589 | 21110.8511 | 5.9244 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1625 | 79 | 0.00040369 | 152481107 | BRUNSWICK 1107 | BRUNSWICK 110750010 | 9532.5902 | 0.031892 | 1664 | 5.9233 | 21116.7744 | 5.8925 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6126 | 247 | 0.00040099 | 42841111 | GUALALA 1111 | GUALALA 111135562 | 22847.3348 | 0.099045 | 1354 | 14.1967 | 21130.9711 | 5.7935 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 674 | 88 | 0.00040017 | 42811113 | MONTE RIO 1113 | MONTE RIO 1113524 | 10034.2173 | 0.035215 | 1633 | 6.235 | 21137.2061 | 5.7583 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8537 | 14 | 0.00039667 | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 2102L485 | 1339.4234 | 0.0055534 | 1982 | 0.83228 | 21138.0383 | 5.7527 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5662 | 28 | 0.00039666 | 82931101 | POINT MORETTI 1101 | POINT MORETTI 11015076 | 10957.7607 | 0.011107 | 1880 | 6.8088 | 21144.8472 | 5.7416 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1414 | 2 | 0.0021111 | 24131102 | MENLO 1102 | MENLO 11028952 | 10925.0954 | 0.0042223 | 1571 | 6.7885 | 21151.6357 | 5.7374 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 1414 | 115 | 0.00036653 | 24131102 | MENLO 1102 | MENLO 11028952 | 10925.0954 | 0.042151 | 1571 | 6.7885 | 21158.4242 | 5.6952 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Sierra | 3147 | 276 | 0.00039005 | 152431101 | SHADY GLEN 1101 | SHADY GLEN 110151696 | 28237.56 | 0.10765 | 1333 | 17.546 | 21175.9702 | 5.5876 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8990 | 30 | 0.00038961 | 182971101 | PURISIMA 1101 | PURISIMA 1101Y44 | 16580.432 | 0.011688 | 1870 | 10.3026 | 21186.2728 | 5.5759 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1464 | 6 | 0.00038567 | 14232107 | SAN RAMON 2107 | SAN RAMON 2107circuit_breaker | 477.5582 | 0.002314 | 2085 | 0.29674 | 21186.5696 | 5.5736 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5960 | 116 | 0.00038475 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 2105circuit_breaker | 12905.269 | 0.044631 | 1583 | 8.019 | 21194.5885 | 5.5289 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7522 | 48 | 0.00038379 | 101321101 | PIT NO 5 1101 | PIT NO 5 11011658 | 7306.3402 | 0.018422 | 1784 | 4.5399 | 21199.1285 | 5.5105 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4442 | 26 | 0.00038308 | 43321101 | RINCON 1101 | RINCON 1101circuit_breaker | 2521.3047 | 0.0099601 | 1898 | 1.5667 | 21200.6952 | 5.5006 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8694 | 14 | 0.000383 | 254061102 | DUNLAP 1102 | DUNLAP 110239190 | 2902.8014 | 0.005362 | 1988 | 1.8037 | 21202.4989 | 5.4952 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8007 | 15 | 0.00038262 | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 2102L7283 | 1066.8481 | 0.0057393 | 1977 | 0.66291 | 21203.1618 | 5.4895 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 869 | 126 | 0.00038218 | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 21024796 | 11537.3564 | 0.048155 | 1554 | 7.169 | 21210.3308 | 5.4413 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6457 | 28 | 0.00037354 | 42031125 | ALTO 1125 | ALTO 11251158 | 3766.7299 | 0.010459 | 1887 | 2.3405 | 21212.6713 | 5.4308 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2757 | 3 | 0.00037024 | 82952107 | EDENVALE 2107 | EDENVALE 2107XR336 | 2932.2246 | 0.0011107 | 2150 | 1.822 | 21214.4933 | 5.4297 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1584 | 35 | 0.00036949 | 183101104 | CABRILLO 1104 | CABRILLO 1104Y22 | 14759.1555 | 0.012932 | 1854 | 9.1709 | 21223.6642 | 5.4168 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5418 | 331 | 0.00036763 | 162161101 | ELECTRA 1101 | ELECTRA 110161816 | 37900.7563 | 0.12168 | 1292 | 23.5504 | 21247.2146 | 5.2951 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4155 | 89 | 0.00036727 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 21065302 | 9619.5872 | 0.032687 | 1655 | 5.9773 | 21253.192 | 5.2624 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6236 | 24 | 0.00036702 | 42811113 | MONTE RIO 1113 | MONTE RIO 11131313 | 1981.3722 | 0.0088085 | 1923 | 1.2312 | 21254.4231 | 5.2536 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2427 | 251 | 0.00036622 | 192431109 | HARRIS 1109 | HARRIS 1109700 | 23735.6051 | 0.091921 | 1370 | 14.7486 | 21269.1718 | 5.1617 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4885 | 5 | 0.00036615 | 182541101 | ATASCADERO 1101 | ATASCADERO 1101A22 | 209.5535 | 0.0018308 | 2109 | 0.13021 | 21269.302 | 5.1599 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2271 | 73 | 0.00036573 | 13801101 | MORAGA 1101 | MORAGA 1101108540 | 7755.7349 | 0.026699 | 1704 | 4.8192 | 21274.1212 | 5.1332 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1845 | 272 | 0.00036276 | 42761102 | FORT BRAGG A 1102 | FORT BRAGG A 110231304 | 34687.2851 | 0.09867 | 1356 | 21.5537 | 21295.6748 | 5.0345 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6153 | 24 | 0.00036155 | 163661702 | MIWUK 1702 | MIWUK 1702S2247 | 2394.0014 | 0.0086771 | 1925 | 1.4876 | 21297.1624 | 5.0258 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 582 | 716 | 0.00035578 | 152481102 | BRUNSWICK 1102 | BRUNSWICK 11021010 | 70806.9227 | 0.25474 | 1091 | 43.9974 | 21341.1598 | 4.7711 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3663 | 98 | 0.00035504 | 252691104 | INDIAN FLAT 1104 | INDIAN FLAT 1104circuit_breaker | 20602.0949 | 0.034794 | 1638 | 12.8015 | 21353.9613 | 4.7363 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4948 | 9 | 0.00035426 | 103311102 | BURNEY 1102 | BURNEY 110297318 | 1004.5656 | 0.0031884 | 2052 | 0.62421 | 21354.5855 | 4.7331 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5118 | 96 | 0.00035192 | 163351705 | CURTIS 1705 | CURTIS 1705843 | 10626.4913 | 0.033784 | 1648 | 6.603 | 21361.1885 | 4.6993 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1671 | 66 | 0.00034883 | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 110136880 | 9538.3272 | 0.023023 | 1739 | 5.9268 | 21367.1153 | 4.6763 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1564 | 40 | 0.00034655 | 252531101 | SAN JOAQUIN #3 1101 | SAN JOAQUIN #3 1101673480 | 20465.7113 | 0.013862 | 1845 | 12.7168 | 21379.8321 | 4.6624 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7916 | 47 | 0.00034614 | 103311101 | BURNEY 1102 | BURNEY 11029042 | 5080.7921 | 0.016269 | 1816 | 3.1571 | 21382.9892 | 4.6462 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3867 | 29 | 0.00034598 | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110112122 | 9019.8604 | 0.010034 | 1894 | 5.6047 | 21388.5939 | 4.6361 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 9051 | 196 | 0.00034477 | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 21028442 | 19520.8754 | 0.067574 | 1463 | 12.1297 | 21400.7236 | 4.5686 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 856 | 77 | 0.00034206 | 103551101 | RISING RIVER 1101 | RISING RIVER 1101circuit_breaker | 14030.5414 | 0.026339 | 1707 | 8.7182 | 21409.4418 | 4.5422 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3703 | 270 | 0.00033975 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 210612518 | 25588.9357 | 0.091732 | 1371 | 15.9002 | 21425.342 | 4.4505 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5879 | 192 | 0.00033923 | 182941102 | OTTER 1102 | OTTER 110263868 | 25330.6289 | 0.065133 | 1474 | 15.7397 | 21441.0817 | 4.3854 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6889 | 10 | 0.00033735 | 42011107 | SAN RAFAEL 1107 | SAN RAFAEL 11071415 | 1054.2427 | 0.0033735 | 2044 | 0.65508 | 21441.7368 | 4.382 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6299 | 33 | 0.00033666 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 110247006 | 7271.2685 | 0.01111 | 1879 | 4.5182 | 21446.2549 | 4.3709 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3017 | 82 | 0.00033026 | 182601102 |  | V50 | 10661.0029 | 0.027081 | 1702 | 6.6244 | 21452.8794 | 4.3438 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6009 | 191 | 0.00032832 | 103551101 | RISING RIVER 1101 | RISING RIVER 11019032 | 35634.3752 | 0.062709 | 1484 | 22.1422 | 21475.0215 | 4.2811 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8659 | 30 | 0.00032668 | 163661702 | MIWUK 1702 | MIWUK 17021808 | 2945.2419 | 0.0098005 | 1901 | 1.8301 | 21476.8516 | 4.2713 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4307 | 145 | 0.00032398 | 153081111 | PLACERVILLE 1111 | PLACERVILLE 11118582 | 14528.3903 | 0.046977 | 1567 | 9.0275 | 21485.8791 | 4.2243 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7385 | 14 | 0.00032359 | 42811112 | MONTE RIO 1112 | MONTE RIO 111215401 | 1388.1732 | 0.0045303 | 2012 | 0.86257 | 21486.7417 | 4.2198 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 588 | 19 | 0.00032313 | 163351703 | CURTIS 1703 | CURTIS 170356972 | 13676.594 | 0.0061394 | 1971 | 8.4982 | 21495.24 | 4.2136 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 106 | 136 | 0.00031868 | 163761703 | RACETRACK 1703 | RACETRACK 17038120 | 14368.0422 | 0.043341 | 1587 | 8.9279 | 21504.1678 | 4.1703 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1334 | 41 | 0.00031839 | 83622103 | CAMP EVERS 2103 | CAMP EVERS 21035753 | 3895.5708 | 0.013054 | 1852 | 2.4206 | 21506.5884 | 4.1572 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1168 | 8 | 0.00031822 | 163781705 | PEORIA 1705 | PEORIA 170575274 | 450.4418 | 0.0025458 | 2072 | 0.27989 | 21506.8683 | 4.1547 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2145 | 41 | 0.00031524 | 192151131 | NEWBURG 1131 | NEWBURG 1131circuit_breaker | 3684.9558 | 0.012925 | 1855 | 2.2897 | 21509.1581 | 4.1418 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3139 | 115 | 0.00031635 | 12501105 | EL CERRITO G 1105 | EL CERRITO G 1105BR160 | 13118.739 | 0.03638 | 1627 | 8.1516 | 21517.3097 | 4.1054 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Coast | 3139 | 1 | 2.8524e-06 | 12501105 | EL CERRITO G 1105 | EL CERRITO G 1105BR160 | 13118.739 | 2.8524e-06 | 1627 | 8.1516 | 21525.4613 | 4.1054 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 9522 | 30 | 0.0003119 | 13921104 | FRANKLIN 1104 | FRANKLIN 1104P146 | 5649.6032 | 0.0093569 | 1913 | 3.5105 | 21528.9718 | 4.096 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3679 | 138 | 0.0003065 | 163351705 | CURTIS 1705 | CURTIS 170510590 | 15780.5647 | 0.042297 | 1593 | 9.8056 | 21538.7773 | 4.0537 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7983 | 70 | 0.0003063 | 182951102 | FOOTHILL 1102 | FOOTHILL 1102circuit_breaker | 12510.7066 | 0.021441 | 1754 | 7.7738 | 21546.5511 | 4.0323 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1950 | 1 | 0.0034993 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 110369412 | 21261.3098 | 0.0034993 | 1589 | 13.2112 | 21559.7623 | 4.0288 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 1950 | 140 | 0.00028297 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 110369412 | 21261.3098 | 0.039616 | 1589 | 13.2112 | 21572.9735 | 3.9892 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Valley | 6835 | 115 | 0.00030544 | 103381101 | FRENCH GULCH 1101 | FRENCH GULCH 11012905 | 15608.0555 | 0.035126 | 1635 | 9.6984 | 21582.6718 | 3.9541 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5585 | 56 | 0.00030495 | 152691103 | HIGGINS 1103 | HIGGINS 1103995672 | 5336.5048 | 0.017077 | 1801 | 3.3159 | 21585.9878 | 3.937 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4424 | 99 | 0.00030337 | 83182101 | LLAGAS 2101 | LLAGAS 21011449 | 16208.7254 | 0.030034 | 1680 | 10.0716 | 21596.0594 | 3.9069 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2244 | 55 | 0.00030266 | 182601104 | OCEANO 1104 | OCEANO 1104circuit_breaker | 11912.9543 | 0.016646 | 1807 | 7.4024 | 21603.4618 | 3.8903 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3281 | 357 | 0.00030238 | 103221101 | KANAKA 1101 | KANAKA 11011406 | 43311.9933 | 0.10795 | 1331 | 26.9128 | 21630.3746 | 3.7823 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 580 | 135 | 0.00030219 | 163661701 | MIWUK 1701 | MIWUK 170110600 | 17528.1979 | 0.040795 | 1599 | 10.8915 | 21641.2661 | 3.7416 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2132 | 79 | 0.00029979 | 152261104 | DIAMOND SPRINGS 1104 | DIAMOND SPRINGS 1104circuit_breaker | 9049.1715 | 0.023684 | 1733 | 5.6229 | 21646.889 | 3.7179 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1680 | 97 | 0.00029938 | 42981101 | ELK 1101 | ELK 110191336 | 11968.0294 | 0.02904 | 1684 | 7.4366 | 21654.3256 | 3.6888 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1791 | 167 | 0.00029753 | 42761101 | FORT BRAGG A 1101 | FORT BRAGG A 11014622 | 21198.3263 | 0.049687 | 1543 | 13.172 | 21667.4976 | 3.6391 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4077 | 178 | 0.0002973 | 254452101 | MARIPOSA 2101 | MARIPOSA 210110170 | 26174.8185 | 0.05292 | 1526 | 16.2643 | 21683.7619 | 3.5862 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3431 | 83 | 0.00029534 | 42811111 | MONTE RIO 1111 | MONTE RIO 1111256 | 11643.9499 | 0.024513 | 1725 | 7.2352 | 21690.9971 | 3.5617 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6315 | 7 | 0.00029356 | 182951101 | FOOTHILL 1101 | FOOTHILL 1101549904 | 12017.3608 | 0.0020549 | 2097 | 7.4672 | 21698.4644 | 3.5597 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3533 | 187 | 0.00029156 | 163751101 | PINE GROVE 1101 | PINE GROVE 11013166 | 20128.8983 | 0.054521 | 1519 | 12.5075 | 21710.9719 | 3.5051 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9034 | 9 | 0.00029152 | 102541102 | VOLTA 1102 | VOLTA 110280982 | 836.5231 | 0.0026237 | 2068 | 0.51979 | 21711.4917 | 3.5025 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3214 | 50 | 0.0002908 | 43311108 | KONOCTI 1108 | KONOCTI 1108circuit_breaker | 9103.4044 | 0.01454 | 1836 | 5.6566 | 21717.1483 | 3.488 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4408 | 73 | 0.00029004 | 182731102 | RESERVATION ROAD 1102 | RESERVATION ROAD 1102circuit_breaker | 12102.7686 | 0.021173 | 1757 | 7.5203 | 21724.6686 | 3.4668 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1988 | 3 | 0.00028956 | 83392102 | SWIFT 2102 | SWIFT 2102circuit_breaker | 706.8877 | 0.00086869 | 2168 | 0.43924 | 21725.1078 | 3.4659 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4445 | 3 | 0.00028861 | 183052113 | TEMPLETON 2113 | TEMPLETON 2113A30 | 401.1046 | 0.00086582 | 2170 | 0.24923 | 21725.357 | 3.4651 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3543 | 303 | 0.0002886 | 152481105 | BRUNSWICK 1105 | BRUNSWICK 110532536 | 34249.9271 | 0.087446 | 1387 | 21.2819 | 21746.6389 | 3.3776 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6525 | 13 | 0.00028492 | 43191101 | REDBUD 1101 | REDBUD 1101400 | 1401.7515 | 0.003704 | 2037 | 0.87101 | 21747.51 | 3.3739 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8487 | 68 | 0.00028357 | 182941102 | OTTER 1102 | OTTER 11022166 | 6559.0006 | 0.019283 | 1772 | 4.0756 | 21751.5855 | 3.3546 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4931 | 25 | 0.00028351 | 182631107 | SAN LUIS OBISPO 1107 | SAN LUIS OBISPO 1107V18 | 4192.834 | 0.0070877 | 1959 | 2.6053 | 21754.1908 | 3.3475 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1005 | 26 | 0.00027992 | 254452101 | MARIPOSA 2101 | MARIPOSA 2101439030 | 31566.7616 | 0.007278 | 1955 | 19.6147 | 21773.8055 | 3.3403 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2060 | 40 | 0.00027985 | 102541102 | VOLTA 1102 | VOLTA 11021648 | 6728.2286 | 0.011194 | 1878 | 4.1807 | 21777.9862 | 3.3291 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3882 | 32 | 0.00027814 | 82841101 | BIG BASIN 1101 | BIG BASIN 110112838 | 3775.6915 | 0.0089004 | 1921 | 2.3461 | 21780.3323 | 3.3202 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5401 | 10 | 0.00027611 | 163451702 | FROGTOWN 1702 | FROGTOWN 170236870 | 1179.9136 | 0.0027611 | 2061 | 0.73316 | 21781.0655 | 3.3174 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1160 | 17 | 0.00027572 | 252811102 | MERCED FALLS 1102 | MERCED FALLS 1102circuit_breaker | 11883.3184 | 0.0046872 | 2004 | 7.3839 | 21788.4494 | 3.3127 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2811 | 67 | 0.00027559 | 101321101 | PIT NO 5 1101 | PIT NO 5 11011660 | 7855.6791 | 0.018465 | 1783 | 4.8813 | 21793.3307 | 3.2943 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7605 | 33 | 0.00027435 | 163781704 | PEORIA 1704 | PEORIA 1704circuit_breaker | 11652.3164 | 0.0090534 | 1919 | 7.2404 | 21800.5712 | 3.2852 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3890 | 96 | 0.00027091 | 42011108 | SAN RAFAEL 1108 | SAN RAFAEL 1108322 | 11483.9582 | 0.026007 | 1712 | 7.1358 | 21807.7069 | 3.2592 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1639 | 238 | 0.00027075 | 162831702 |  | 9690 | 27542.9968 | 0.064438 | 1478 | 17.1144 | 21824.8214 | 3.1948 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6607 | 120 | 0.00026889 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 110398440 | 13071.9471 | 0.032267 | 1660 | 8.1225 | 21832.9439 | 3.1625 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4121 | 212 | 0.00026739 | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LA64 | 20491.3377 | 0.056688 | 1508 | 12.7327 | 21845.6766 | 3.1058 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3239 | 20 | 0.00026582 | 22721106 | SNEATH LANE 1106 | SNEATH LANE 1106circuit_breaker | 3587.2513 | 0.0053163 | 1990 | 2.229 | 21847.9056 | 3.1005 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2036 | 394 | 0.00026562 | 192171103 | WILLOW CREEK 1103 | WILLOW CREEK 11032936 | 53467.3373 | 0.10465 | 1339 | 33.2231 | 21881.1287 | 2.9958 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7598 | 93 | 0.00026552 | 103732101 | PIT NO 3 2101 | PIT NO 3 2101circuit_breaker | 10857.4498 | 0.024694 | 1723 | 6.7465 | 21887.8752 | 2.9711 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4066 | 140 | 0.0002644 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 210610718 | 13748.6879 | 0.037016 | 1625 | 8.543 | 21896.4182 | 2.9341 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2108 | 103 | 0.00026316 | 163661701 | MIWUK 1701 | MIWUK 170153038 | 10691.9033 | 0.027105 | 1701 | 6.6436 | 21903.0619 | 2.907 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6723 | 184 | 0.00026155 | 83252106 | PAUL SWEET 2106 | PAUL SWEET 2106428102 | 19212.6145 | 0.048126 | 1556 | 11.9382 | 21915 | 2.8589 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6523 | 92 | 0.00026069 | 14091108 | CASTRO VALLEY 1108 | CASTRO VALLEY 110810315 | 8831.8074 | 0.023983 | 1731 | 5.4878 | 21920.4879 | 2.8349 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3207 | 18 | 0.0002597 | 43201101 | STAFFORD 1101 | STAFFORD 1101circuit_breaker | 1888.1069 | 0.0046746 | 2005 | 1.1732 | 21921.6611 | 2.8302 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2907 | 138 | 0.00025459 | 163351704 | CURTIS 1704 | CURTIS 1704803 | 15628.5101 | 0.035133 | 1634 | 9.7111 | 21931.3722 | 2.7951 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7028 | 89 | 0.00025399 | 192021122 | ARCATA 1122 | ARCATA 11224218 | 7920.8951 | 0.022605 | 1743 | 4.9218 | 21936.294 | 2.7725 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2063 | 125 | 0.00025348 | 182742104 | SAN BENITO 2104 | SAN BENITO 210488772 | 37629.3808 | 0.031685 | 1666 | 23.3818 | 21959.6758 | 2.7408 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3745 | 41 | 0.00025346 | 254151101 | AUBERRY 1101 | AUBERRY 1101D4982 | 4312.861 | 0.010392 | 1888 | 2.6799 | 21962.3557 | 2.7304 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3507 | 112 | 0.00025082 | 163351703 | CURTIS 1703 | CURTIS 17039330 | 66426.892 | 0.028092 | 1693 | 41.2757 | 22003.6314 | 2.7023 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4938 | 53 | 0.00025058 | 14101105 | ALHAMBRA 1105 | ALHAMBRA 110581514 | 5038.5618 | 0.013281 | 1849 | 3.1308 | 22006.7622 | 2.689 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5765 | 84 | 0.00024864 | 163661702 | MIWUK 1702 | MIWUK 17029270 | 9423.8186 | 0.020886 | 1760 | 5.8557 | 22012.6179 | 2.6682 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3219 | 10 | 0.00024817 | 163351703 | CURTIS 1703 | CURTIS 170390320 | 44739.8635 | 0.0024817 | 2075 | 27.8001 | 22040.418 | 2.6657 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1538 | 17 | 0.00024698 | 182631101 | SAN LUIS OBISPO 1101 | SAN LUIS OBISPO 1101483444 | 2987.6026 | 0.0041987 | 2021 | 1.8564 | 22042.2744 | 2.6615 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 986 | 346 | 0.00024665 | 83692104 | ROB ROY 2104 | ROB ROY 21045082 | 32076.122 | 0.085342 | 1394 | 19.9312 | 22062.2056 | 2.5761 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1290 | 49 | 0.00024526 | 152431101 | SHADY GLEN 1101 | SHADY GLEN 1101circuit_breaker | 5163.0926 | 0.012018 | 1866 | 3.2082 | 22065.4138 | 2.5641 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6067 | 39 | 0.00024124 | 43081101 | BIG RIVER 1101 | BIG RIVER 11011052 | 4296.6961 | 0.0094083 | 1912 | 2.6698 | 22068.0836 | 2.5547 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4653 | 91 | 0.00024089 | 182811102 | SISQUOC 1102 | SISQUOC 1102M52 | 54915.488 | 0.021921 | 1749 | 34.1229 | 22102.2065 | 2.5328 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3903 | 194 | 0.0002404 | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 11011419 | 24046.9564 | 0.046637 | 1570 | 14.9421 | 22117.1486 | 2.4862 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 894 | 63 | 0.00023753 | 163781705 | PEORIA 1705 | PEORIA 170590374 | 6578.4615 | 0.014965 | 1827 | 4.0877 | 22121.2362 | 2.4712 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 420 | 11 | 0.00023681 | 42491101 | SAUSALITO 1101 | SAUSALITO 1101circuit_breaker | 1238.4516 | 0.002605 | 2071 | 0.76954 | 22122.0058 | 2.4686 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8753 | 8 | 0.00023539 | 163661702 | MIWUK 1702 | MIWUK 170236888 | 990.9397 | 0.0018831 | 2107 | 0.61574 | 22122.6215 | 2.4667 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2968 | 368 | 0.00023444 | 42601102 | PHILO 1102 | PHILO 11021308 | 51499.148 | 0.086273 | 1390 | 32.0001 | 22154.6216 | 2.3804 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4093 | 63 | 0.0002325 | 162831702 |  | 10720 | 7647.7028 | 0.014648 | 1831 | 4.7521 | 22159.3737 | 2.3658 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8028 | 62 | 0.0002325 | 192151131 | NEWBURG 1131 | NEWBURG 113190242 | 5381.5662 | 0.014415 | 1839 | 3.3439 | 22162.7176 | 2.3514 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5123 | 33 | 0.00023226 | 82841101 | BIG BASIN 1101 | BIG BASIN 11015000 | 3211.5435 | 0.0076645 | 1945 | 1.9956 | 22164.7132 | 2.3437 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1147 | 49 | 0.00023144 | 42011108 | SAN RAFAEL 1108 | SAN RAFAEL 11081210 | 5233.0326 | 0.01134 | 1874 | 3.2517 | 22167.9648 | 2.3324 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6077 | 66 | 0.00023006 | 42291101 | OLEMA 1101 | OLEMA 11011252 | 6562.8215 | 0.015184 | 1825 | 4.0779 | 22172.0428 | 2.3172 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8427 | 7 | 0.0002296 | 162831702 |  | 86032 | 1615.684 | 0.0016072 | 2124 | 1.0039 | 22173.0467 | 2.3156 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7045 | 111 | 0.00022846 | 24101101 | HALF MOON BAY 1101 | HALF MOON BAY 11018902 | 21140.1681 | 0.025359 | 1716 | 13.1359 | 22186.1826 | 2.2902 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6538 | 33 | 0.00022823 | 252691104 | INDIAN FLAT 1104 | INDIAN FLAT 110410270 | 6119.8904 | 0.0075315 | 1948 | 3.8027 | 22189.9853 | 2.2827 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 455 | 298 | 0.00022815 | 152491101 | WEIMAR 1101 | WEIMAR 11012084 | 29727.9123 | 0.06799 | 1459 | 18.4721 | 22208.4574 | 2.2147 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4997 | 212 | 0.00022785 | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 110111236 | 31569.3587 | 0.048303 | 1553 | 19.6163 | 22228.0737 | 2.1664 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5710 | 22 | 0.00022735 | 13801103 | MORAGA 1103 | MORAGA 1103circuit_breaker | 1860.265 | 0.0050018 | 1996 | 1.1559 | 22229.2296 | 2.1614 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1046 | 70 | 0.00022689 | 42031125 | ALTO 1125 | ALTO 11251256 | 6410.4568 | 0.015882 | 1819 | 3.9833 | 22233.2129 | 2.1455 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 875 | 30 | 0.0002254 | 183052108 | TEMPLETON 2108 | TEMPLETON 2108A64 | 3063.2438 | 0.0067619 | 1962 | 1.9034 | 22235.1163 | 2.1387 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6047 | 65 | 0.00022531 | 163781705 | PEORIA 1705 | PEORIA 170587222 | 8240.0572 | 0.014645 | 1832 | 5.1201 | 22240.2364 | 2.1241 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3012 | 151 | 0.00022487 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210510728 | 16827.1381 | 0.033956 | 1645 | 10.4559 | 22250.6923 | 2.0901 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4596 | 67 | 0.00022455 | 42981101 | ELK 1101 | ELK 11018779 | 6865.4129 | 0.015045 | 1826 | 4.266 | 22254.9583 | 2.0751 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4002 | 179 | 0.00022235 | 152251101 | SPAULDING 1101 | SPAULDING 1101578852 | 33138.4596 | 0.0398 | 1605 | 20.5913 | 22275.5495 | 2.0353 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8152 | 24 | 0.00021964 | 83242111 | MORGAN HILL 2111 | MORGAN HILL 21114461 | 3633.9489 | 0.0052714 | 1991 | 2.258 | 22277.8076 | 2.03 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2492 | 135 | 0.00021958 | 152481110 | BRUNSWICK 1110 | BRUNSWICK 111061602 | 14421.8376 | 0.029644 | 1682 | 8.9613 | 22286.7689 | 2.0004 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1189 | 97 | 0.00021753 | 83692105 | ROB ROY 2105 | ROB ROY 21055166 | 8833.6807 | 0.0211 | 1759 | 5.489 | 22292.2579 | 1.9793 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 58 | 6 | 0.00021706 | 182771102 | CAMBRIA 1102 | CAMBRIA 1102W50 | 779.9345 | 0.0013024 | 2138 | 0.48463 | 22292.7425 | 1.978 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 572 | 76 | 0.00021535 | 42811111 | MONTE RIO 1111 | MONTE RIO 111123916 | 8839.5506 | 0.016366 | 1813 | 5.4926 | 22298.2351 | 1.9616 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 438 | 52 | 0.00021528 | 42811112 | MONTE RIO 1112 | MONTE RIO 1112circuit_breaker | 5973.9084 | 0.011195 | 1877 | 3.712 | 22301.9472 | 1.9504 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7490 | 23 | 0.0002137 | 163781704 | PEORIA 1704 | PEORIA 1704877670 | 10595.2996 | 0.004915 | 1999 | 6.5836 | 22308.5308 | 1.9455 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2991 | 145 | 0.00021346 | 254151101 | AUBERRY 1101 | AUBERRY 1101R324 | 17331.696 | 0.030952 | 1674 | 10.7694 | 22319.3002 | 1.9145 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 951 | 77 | 0.00021187 | 182551102 | CAYUCOS 1102 | CAYUCOS 1102circuit_breaker | 20474.7402 | 0.016314 | 1815 | 12.7224 | 22332.0226 | 1.8982 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3406 | 183 | 0.00021115 | 152031101 | GRASS VALLEY 1101 | GRASS VALLEY 11012208 | 18884.1728 | 0.038641 | 1611 | 11.7341 | 22343.7567 | 1.8596 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6585 | 95 | 0.00020897 | 83500401 | SEACLIFF 0401 | SEACLIFF 0401circuit_breaker | 9172.6769 | 0.019852 | 1768 | 5.6996 | 22349.4563 | 1.8397 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2191 | 24 | 0.00020744 | 42481101 | IGNACIO 1101 | IGNACIO 11011264 | 3308.6659 | 0.0049785 | 1998 | 2.0559 | 22351.5122 | 1.8348 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1475 | 109 | 0.00020743 | 192341102 | HUMBOLDT BAY 1102 | HUMBOLDT BAY 11024724 | 10436.2695 | 0.02261 | 1742 | 6.4848 | 22357.997 | 1.8122 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6880 | 148 | 0.00020633 | 43081101 | BIG RIVER 1101 | BIG RIVER 110169032 | 13621.9318 | 0.030536 | 1677 | 8.4643 | 22366.4613 | 1.7816 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4193 | 23 | 0.00020526 | 83622103 | CAMP EVERS 2103 | CAMP EVERS 210311056 | 2611.1508 | 0.0047209 | 2003 | 1.6225 | 22368.0838 | 1.7769 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1126 | 16 | 0.00020498 | 43201101 | STAFFORD 1101 | STAFFORD 11011082 | 1691.5237 | 0.0032797 | 2049 | 1.0511 | 22369.1348 | 1.7736 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2837 | 10 | 0.00020405 | 182951102 | FOOTHILL 1102 | FOOTHILL 110299432 | 2389.4026 | 0.0020405 | 2099 | 1.4847 | 22370.6195 | 1.7716 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 9699 | 9 | 0.00020355 | 152271101 | WISE 1101 | WISE 110163199 | 989.41 | 0.001832 | 2108 | 0.61479 | 22371.2343 | 1.7697 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 621 | 21 | 0.00020307 | 163761703 | RACETRACK 1703 | RACETRACK 170310870 | 3188.0176 | 0.0042644 | 2019 | 1.9809 | 22373.2153 | 1.7655 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6971 | 123 | 0.00020254 | 82021107 | LOS GATOS 1107 | LOS GATOS 11072917 | 12406.0821 | 0.024912 | 1720 | 7.7088 | 22380.9241 | 1.7406 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1761 | 53 | 0.00019906 | 13801102 | MORAGA 1102 | MORAGA 1102circuit_breaker | 8031.17 | 0.01055 | 1886 | 4.9903 | 22385.9144 | 1.73 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1124 | 54 | 0.00019762 | 42291101 | OLEMA 1101 | OLEMA 11011200 | 4658.8808 | 0.010671 | 1885 | 2.8949 | 22388.8093 | 1.7193 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2853 | 33 | 0.00019621 | 42811111 | MONTE RIO 1111 | MONTE RIO 111153477 | 3299.3477 | 0.006475 | 1964 | 2.0501 | 22390.8594 | 1.7129 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2691 | 43 | 0.00019481 | 14161108 | ROSSMOOR 1108 | ROSSMOOR 110845268 | 4023.0288 | 0.008377 | 1932 | 2.4998 | 22393.3592 | 1.7045 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3784 | 7 | 0.00019061 | 162991102 | CORRAL 1102 | CORRAL 110275622 | 1424.9314 | 0.0013343 | 2135 | 0.88541 | 22394.2446 | 1.7032 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3648 | 190 | 0.0001846 | 152491102 | WEIMAR 1102 | WEIMAR 1102circuit_breaker | 19516.5086 | 0.035075 | 1636 | 12.127 | 22406.3716 | 1.6681 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1392 | 259 | 0.00018425 | 103031101 | ORO FINO 1101 | ORO FINO 11012022 | 27985.9982 | 0.04772 | 1561 | 17.3897 | 22423.7613 | 1.6204 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2706 | 43 | 0.00018395 | 42981101 | ELK 1101 | ELK 1101900 | 9529.0573 | 0.00791 | 1941 | 5.9211 | 22429.6824 | 1.6125 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1518 | 615 | 0.00018138 | 163011101 | MARTELL 1101 | MARTELL 110191216 | 66328.7264 | 0.11155 | 1318 | 41.2147 | 22470.8971 | 1.5009 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3230 | 13 | 0.00018055 | 182571103 | DIVIDE 1103 | DIVIDE 110348160 | 4025.5628 | 0.0023472 | 2083 | 2.5014 | 22473.3985 | 1.4986 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1763 | 6 | 0.00017761 | 42261101 | BOLINAS 1101 | BOLINAS 11011064 | 546.0033 | 0.0010656 | 2153 | 0.33927 | 22473.7378 | 1.4975 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2498 | 271 | 0.00017657 | 152241101 | HALSEY 1101 | HALSEY 1101circuit_breaker | 27545.8987 | 0.04785 | 1558 | 17.1162 | 22490.854 | 1.4496 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3106 | 105 | 0.00017449 | 42031125 | ALTO 1125 | ALTO 11251226 | 12208.7235 | 0.018322 | 1786 | 7.5861 | 22498.4401 | 1.4313 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8105 | 36 | 0.00017436 | 252531101 | SAN JOAQUIN #3 1101 | SAN JOAQUIN #3 110110060 | 10431.3936 | 0.0062769 | 1967 | 6.4818 | 22504.9219 | 1.425 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2555 | 113 | 0.00017405 | 152691104 | HIGGINS 1104 | HIGGINS 1104533648 | 10867.9062 | 0.019668 | 1770 | 6.753 | 22511.6749 | 1.4054 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8027 | 55 | 0.00017254 | 42011107 | SAN RAFAEL 1107 | SAN RAFAEL 11071276 | 5613.9148 | 0.0094899 | 1908 | 3.4883 | 22515.1632 | 1.3959 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5332 | 98 | 0.00017216 | 14101105 | ALHAMBRA 1105 | ALHAMBRA 11058302 | 13278.3332 | 0.016872 | 1803 | 8.2508 | 22523.414 | 1.379 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2810 | 260 | 0.00017172 | 83622103 | CAMP EVERS 2103 | CAMP EVERS 210311046 | 26125.6746 | 0.044646 | 1582 | 16.2337 | 22539.6477 | 1.3344 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5149 | 8 | 0.00017116 | 182801101 | BAYWOOD 1101 | BAYWOOD 1101circuit_breaker | 6577.3472 | 0.0013693 | 2134 | 4.087 | 22543.7347 | 1.333 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5291 | 51 | 0.0001679 | 14161108 | ROSSMOOR 1108 | ROSSMOOR 1108circuit_breaker | 5393.569 | 0.0085631 | 1928 | 3.3514 | 22547.0861 | 1.3244 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8642 | 50 | 0.00016513 | 83692104 | ROB ROY 2104 | ROB ROY 21045304 | 4973.8861 | 0.0082564 | 1935 | 3.0906 | 22550.1767 | 1.3162 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 9289 | 44 | 0.00016486 | 83692104 | ROB ROY 2104 | ROB ROY 21046577 | 5612.3201 | 0.007254 | 1957 | 3.4873 | 22553.6641 | 1.3089 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1460 | 56 | 0.0001641 | 12350401 | ORINDA 0401 | ORINDA 0401N545R | 7502.4589 | 0.0091894 | 1917 | 4.6618 | 22558.3259 | 1.2997 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7339 | 103 | 0.00016337 | 163351705 | CURTIS 1705 | CURTIS 17058110 | 13092.5709 | 0.016828 | 1804 | 8.1353 | 22566.4612 | 1.2829 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7589 | 156 | 0.00016085 | 183181101 | SAN JUSTO 1101 | SAN JUSTO 11014002 | 29265.3642 | 0.025092 | 1718 | 18.1846 | 22584.6459 | 1.2578 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 893 | 103 | 0.00015935 | 254061102 | DUNLAP 1102 | DUNLAP 11027050 | 14670.6683 | 0.016413 | 1812 | 9.1159 | 22593.7618 | 1.2414 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2161 | 127 | 0.00015771 | 254421103 | OAKHURST 1103 | OAKHURST 11035470 | 15314.9972 | 0.02003 | 1765 | 9.5163 | 22603.2781 | 1.2214 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4718 | 147 | 0.00015679 | 252192101 | BEAR VALLEY 2101 | BEAR VALLEY 2101circuit_breaker | 30106.3475 | 0.023048 | 1737 | 18.7072 | 22621.9853 | 1.1983 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 138 | 201 | 0.00015394 | 163761703 | RACETRACK 1703 | RACETRACK 1703circuit_breaker | 24637.5385 | 0.030943 | 1675 | 15.3091 | 22637.2944 | 1.1674 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2806 | 217 | 0.00015336 | 42011107 | SAN RAFAEL 1107 | SAN RAFAEL 11071166 | 19693.934 | 0.03328 | 1653 | 12.2372 | 22649.5316 | 1.1341 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6081 | 101 | 0.00015323 | 163351702 | CURTIS 1702 | CURTIS 170268380 | 10695.6106 | 0.015476 | 1823 | 6.6459 | 22656.1775 | 1.1186 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2842 | 7 | 0.00015069 | 42771114 | UKIAH 1114 | UKIAH 1114544 | 423.9084 | 0.0010548 | 2154 | 0.2634 | 22656.4409 | 1.1176 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6656 | 7 | 0.00015067 | 42491102 | SAUSALITO 1102 | SAUSALITO 11021224 | 1179.0057 | 0.0010547 | 2155 | 0.7326 | 22657.1735 | 1.1165 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1097 | 92 | 0.00015027 | 83242104 | MORGAN HILL 2104 | MORGAN HILL 2104XR018 | 9365.0904 | 0.013825 | 1846 | 5.8192 | 22662.9927 | 1.1027 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 186 | 233 | 0.00014908 | 43081101 | BIG RIVER 1101 | BIG RIVER 110179628 | 23966.4375 | 0.034735 | 1640 | 14.892 | 22677.8848 | 1.068 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2099 | 79 | 0.00014871 | 152481102 | BRUNSWICK 1102 | BRUNSWICK 1102circuit_breaker | 9785.3713 | 0.011748 | 1869 | 6.0803 | 22683.9651 | 1.0562 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1472 | 150 | 0.00014745 | 83912110 | PIERCY 2110 | PIERCY 2110XR258 | 32262.0914 | 0.022117 | 1748 | 20.0467 | 22704.0119 | 1.0341 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Valley | 1472 | 1 | 1.0133e-06 | 83912110 | PIERCY 2110 | PIERCY 2110XR258 | 32262.0914 | 1.0133e-06 | 1748 | 20.0467 | 22724.0586 | 1.0341 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Valley | 3135 | 111 | 0.00014607 | 162831702 |  | 9280 | 10238.6401 | 0.016214 | 1817 | 6.362 | 22730.4206 | 1.0179 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8988 | 76 | 0.00014591 | 82021107 | LOS GATOS 1107 | LOS GATOS 1107LA60 | 13828.9369 | 0.011089 | 1881 | 8.5929 | 22739.0135 | 1.0068 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2224 | 147 | 0.00014417 | 42981101 | ELK 1101 | ELK 1101circuit_breaker | 18644.2912 | 0.021193 | 1756 | 11.585 | 22750.5985 | 0.98559 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5254 | 89 | 0.0001421 | 14241101 | SUNOL 1101 | SUNOL 1101MR299 | 8022.9478 | 0.012647 | 1858 | 4.9852 | 22755.5837 | 0.97294 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1190 | 4 | 0.00014059 | 14232106 | SAN RAMON 2106 | SAN RAMON 2106circuit_breaker | 655.1911 | 0.00056237 | 2191 | 0.40712 | 22755.9908 | 0.97238 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 174 | 130 | 0.00014031 | 182031103 | KING CITY 1103 | KING CITY 11037038 | 28474.5458 | 0.01824 | 1787 | 17.6933 | 22773.6841 | 0.95414 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3860 | 166 | 0.00014024 | 102530401 | GRAYS FLAT 0401 | GRAYS FLAT 0401circuit_breaker | 17210.1208 | 0.02328 | 1735 | 10.6939 | 22784.378 | 0.93086 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4865 | 18 | 0.00013996 | 163781704 | PEORIA 1704 | PEORIA 17048040 | 11308.8739 | 0.0025193 | 2073 | 7.027 | 22791.405 | 0.92834 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5641 | 25 | 0.00013994 | 13432207 | FAIRVIEW 2207 | FAIRVIEW 2207P150 | 3652.8381 | 0.0034985 | 2042 | 2.2698 | 22793.6747 | 0.92484 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4468 | 330 | 0.00013862 | 152491101 | WEIMAR 1101 | WEIMAR 11012058 | 33216.2606 | 0.045746 | 1575 | 20.6396 | 22814.3144 | 0.8791 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2562 | 161 | 0.00013823 | 152481106 | BRUNSWICK 1106 | BRUNSWICK 11062104 | 15655.9212 | 0.022255 | 1745 | 9.7281 | 22824.0425 | 0.85684 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6840 | 89 | 0.00013772 | 182941102 | OTTER 1102 | OTTER 11022002 | 13828.3943 | 0.012257 | 1863 | 8.5926 | 22832.6351 | 0.84459 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5174 | 13 | 0.00013603 | 183052113 | TEMPLETON 2113 | TEMPLETON 2113A32 | 2317.4886 | 0.0017684 | 2115 | 1.44 | 22834.0751 | 0.84282 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7444 | 223 | 0.00013458 | 42981101 | ELK 1101 | ELK 11011260 | 24474.7526 | 0.03001 | 1681 | 15.2079 | 22849.283 | 0.81281 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 194 | 32 | 0.00013327 | 152481105 | BRUNSWICK 1105 | BRUNSWICK 1105733408 | 5559.4271 | 0.0042647 | 2018 | 3.4545 | 22852.7375 | 0.80854 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7954 | 113 | 0.00013188 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012476 | 12812.7347 | 0.014902 | 1828 | 7.9615 | 22860.6989 | 0.79364 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6722 | 18 | 0.00013097 | 42481101 | IGNACIO 1101 | IGNACIO 1101circuit_breaker | 2568.3258 | 0.0023575 | 2081 | 1.5959 | 22862.2948 | 0.79128 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6703 | 44 | 0.00013002 | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 2102L491 | 3564.5514 | 0.005721 | 1978 | 2.2149 | 22864.5097 | 0.78556 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4927 | 11 | 0.00012588 | 83192101 | GREEN VALLEY 2101 | GREEN VALLEY 210112130 | 2080.1983 | 0.0013847 | 2132 | 1.2926 | 22865.8023 | 0.78418 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3711 | 179 | 0.00012523 | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110110726 | 17020.6225 | 0.022416 | 1744 | 10.5761 | 22876.3784 | 0.76176 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1481 | 59 | 0.00012298 | 42811113 | MONTE RIO 1113 | MONTE RIO 1113circuit_breaker | 7159.5444 | 0.0072556 | 1956 | 4.4487 | 22880.8271 | 0.75451 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 313 | 82 | 0.00012102 | 83192101 | GREEN VALLEY 2101 | GREEN VALLEY 210112106 | 9141.9925 | 0.0099233 | 1899 | 5.6806 | 22886.5077 | 0.74458 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3226 | 73 | 0.00011943 | 163240402 | TAR FLAT 0402 | TAR FLAT 04023144 | 7378.011 | 0.0087181 | 1924 | 4.5845 | 22891.0922 | 0.73586 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6142 | 106 | 0.00011793 | 103491101 | MC ARTHUR 1101 | MC ARTHUR 11011490 | 13967.782 | 0.012501 | 1860 | 8.6792 | 22899.7714 | 0.72336 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7900 | 69 | 0.00011763 | 102541102 | VOLTA 1102 | VOLTA 110254932 | 6888.3237 | 0.0081164 | 1936 | 4.2802 | 22904.0516 | 0.71525 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8970 | 14 | 0.00011702 | 42491102 | SAUSALITO 1102 | SAUSALITO 110284278 | 2267.2637 | 0.0016382 | 2121 | 1.4088 | 22905.4604 | 0.71361 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6422 | 54 | 0.00011679 | 152481106 | BRUNSWICK 1106 | BRUNSWICK 11064639 | 5228.1955 | 0.0063064 | 1966 | 3.2486 | 22908.709 | 0.7073 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3550 | 15 | 0.00011615 | 183071101 | PERRY 1101 | PERRY 1101V88 | 1316.7813 | 0.0017422 | 2117 | 0.81821 | 22909.5272 | 0.70556 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2078 | 23 | 0.00011598 | 43351106 | LUCERNE 1106 | LUCERNE 1106circuit_breaker | 2265.0742 | 0.0026676 | 2065 | 1.4075 | 22910.9347 | 0.70289 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1396 | 7 | 0.00011487 | 163341101 | CLAY 1101 | CLAY 110184572 | 598.9234 | 0.00080407 | 2173 | 0.37215 | 22911.3068 | 0.70209 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6394 | 47 | 0.00011702 | 43071101 | DUNBAR 1101 | DUNBAR 1101234 | 5211.7421 | 0.0054998 | 1984 | 3.2384 | 22914.5453 | 0.69659 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 6394 | 1 | 4.514e-06 | 43071101 | DUNBAR 1101 | DUNBAR 1101234 | 5211.7421 | 4.514e-06 | 1984 | 3.2384 | 22917.7837 | 0.69658 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 5658 | 49 | 0.00010917 | 12541106 | OAKLAND X 1106 | OAKLAND X 1106CR020 | 3933.9507 | 0.0053494 | 1989 | 2.4444 | 22920.2281 | 0.69123 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 9254 | 6 | 0.00010652 | 253671103 | PANOCHE 1103 | PANOCHE 11034036 | 13306.7166 | 0.00063911 | 2183 | 8.2684 | 22928.4965 | 0.6906 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5946 | 13 | 0.00010562 | 163781701 | PEORIA 1701 | PEORIA 170169124 | 4347.2792 | 0.0013731 | 2133 | 2.7013 | 22931.1978 | 0.68922 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1778 | 36 | 0.00010524 | 183101104 | CABRILLO 1104 | CABRILLO 1104circuit_breaker | 5579.5239 | 0.0037888 | 2034 | 3.467 | 22934.6648 | 0.68543 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4579 | 47 | 0.00010238 | 182771101 | CAMBRIA 1101 | CAMBRIA 1101V76 | 29392.3861 | 0.0048118 | 2002 | 18.2636 | 22952.9283 | 0.68062 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3709 | 34 | 0.00010181 | 183011102 | MORRO BAY 1102 | MORRO BAY 110247584 | 14612.5687 | 0.0034617 | 2043 | 9.0798 | 22962.0082 | 0.67716 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6442 | 7 | 0.00010106 | 163351703 | CURTIS 1703 | CURTIS 17039210 | 37044.9289 | 0.00070741 | 2178 | 23.0186 | 22985.0268 | 0.67645 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 8515 | 34 | 9.887e-05 | 152591102 | SUMMIT 1102 | SUMMIT 110249484 | 4326.7918 | 0.0033616 | 2046 | 2.6885 | 22987.7154 | 0.67309 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8903 | 38 | 9.8725e-05 | 182941101 | OTTER 1101 | OTTER 11017611 | 7068.0362 | 0.0037516 | 2036 | 4.3919 | 22992.1072 | 0.66934 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 686 | 212 | 9.8215e-05 | 182731101 | RESERVATION ROAD 1101 | RESERVATION ROAD 11013026 | 34466.6969 | 0.020822 | 1761 | 21.4166 | 23013.5238 | 0.64852 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 79 | 9 | 9.6499e-05 | 22721107 | SNEATH LANE 1107 | SNEATH LANE 1107circuit_breaker | 1051.9745 | 0.00086849 | 2169 | 0.65367 | 23014.1775 | 0.64765 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6485 | 122 | 9.4076e-05 | 152241102 | HALSEY 1102 | HALSEY 1102circuit_breaker | 12469.8674 | 0.011477 | 1872 | 7.7484 | 23021.9259 | 0.63617 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3027 | 21 | 9.3591e-05 | 182771101 | CAMBRIA 1101 | CAMBRIA 1101circuit_breaker | 9200.2096 | 0.0019654 | 2102 | 5.7167 | 23027.6427 | 0.63421 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5961 | 25 | 9.0413e-05 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 2101circuit_breaker | 3325.4736 | 0.0022603 | 2087 | 2.0664 | 23029.709 | 0.63195 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6520 | 32 | 8.9881e-05 | 12041112 | OAKLAND D 1112 | OAKLAND D 1112CR192 | 3810.1619 | 0.0028762 | 2059 | 2.3675 | 23032.0765 | 0.62907 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7289 | 61 | 8.9007e-05 | 14671103 | SOBRANTE 1103 | SOBRANTE 1103circuit_breaker | 6759.5318 | 0.0054294 | 1987 | 4.2002 | 23036.2767 | 0.62364 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6731 | 83 | 8.8803e-05 | 162161101 | ELECTRA 1101 | ELECTRA 1101L1697 | 8779.0798 | 0.0073707 | 1953 | 5.4551 | 23041.7318 | 0.61627 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4977 | 68 | 8.6934e-05 | 102361101 | HAMILTON BRANCH 1101 | HAMILTON BRANCH 11012046 | 14724.19 | 0.0059115 | 1974 | 9.1492 | 23050.881 | 0.61036 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1967 | 89 | 8.5223e-05 | 182492105 | HOLLISTER 2105 | HOLLISTER 21054018 | 69788.1445 | 0.0075849 | 1947 | 43.3643 | 23094.2453 | 0.60277 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6186 | 154 | 8.517e-05 | 42761102 | FORT BRAGG A 1102 | FORT BRAGG A 1102956 | 18050.2005 | 0.013116 | 1851 | 11.2159 | 23105.4612 | 0.58966 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3988 | 234 | 8.5109e-05 | 103311101 | BURNEY 1102 | BURNEY 11021340 | 28964.4993 | 0.019916 | 1766 | 17.9977 | 23123.4589 | 0.56974 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 259 | 311 | 8.4236e-05 | 83692105 | ROB ROY 2105 | ROB ROY 21055090 | 34034.3802 | 0.026197 | 1710 | 21.148 | 23144.6068 | 0.54354 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 320 | 132 | 8.205e-05 | 163351704 | CURTIS 1704 | CURTIS 170463502 | 16791.7983 | 0.010831 | 1883 | 10.4339 | 23155.0408 | 0.53271 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2890 | 101 | 8.2001e-05 | 83252105 | PAUL SWEET 2105 | PAUL SWEET 2105circuit_breaker | 12715.3949 | 0.0082821 | 1934 | 7.901 | 23162.9418 | 0.52443 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3571 | 55 | 8.098e-05 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 11038089 | 4645.2114 | 0.0044539 | 2014 | 2.8864 | 23165.8282 | 0.51998 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1338 | 118 | 8.0867e-05 | 103311101 | BURNEY 1102 | BURNEY 11021322 | 23390.5578 | 0.0095423 | 1907 | 14.5342 | 23180.3624 | 0.51044 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5977 | 33 | 8.038e-05 | 152571104 | HORSESHOE 1104 | HORSESHOE 110450142 | 3538.232 | 0.0026525 | 2066 | 2.1986 | 23182.5609 | 0.50778 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7554 | 69 | 7.9712e-05 | 24131103 | MENLO 1103 | MENLO 11038982 | 7297.022 | 0.0055001 | 1985 | 4.5342 | 23187.0951 | 0.50228 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3611 | 20 | 7.9697e-05 | 103381101 | FRENCH GULCH 1101 | FRENCH GULCH 1101circuit_breaker | 3697.5337 | 0.0015939 | 2125 | 2.2975 | 23189.3926 | 0.50069 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 826 | 352 | 7.9078e-05 | 42981101 | ELK 1101 | ELK 11011272 | 35495.0764 | 0.027835 | 1695 | 22.0556 | 23211.4482 | 0.47285 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 8935 | 24 | 7.8714e-05 | 152591101 | SUMMIT 1101 | SUMMIT 110147786 | 2854.4871 | 0.0018891 | 2106 | 1.7737 | 23213.2219 | 0.47096 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7774 | 123 | 7.6823e-05 | 152481106 | BRUNSWICK 1106 | BRUNSWICK 1106circuit_breaker | 14079.7489 | 0.0094492 | 1909 | 8.7487 | 23221.9707 | 0.46152 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2514 | 147 | 7.6636e-05 | 152241102 | HALSEY 1102 | HALSEY 11022514 | 15960.9106 | 0.011265 | 1876 | 9.9176 | 23231.8883 | 0.45025 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7092 | 51 | 7.646e-05 | 182492106 | HOLLISTER 2106 | HOLLISTER 21064004 | 12351.5176 | 0.0038995 | 2030 | 7.6749 | 23239.5632 | 0.44635 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1902 | 125 | 7.5456e-05 | 83371107 | SARATOGA 1107 | SARATOGA 1107LC12 | 12044.8193 | 0.009432 | 1910 | 7.4843 | 23247.0475 | 0.43692 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6119 | 56 | 7.5143e-05 | 182492105 | HOLLISTER 2105 | HOLLISTER 21054048 | 26554.045 | 0.004208 | 2020 | 16.4999 | 23263.5474 | 0.43271 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5624 | 16 | 7.4669e-05 | 182052102 | SOLEDAD 2102 | SOLEDAD 21027048 | 25828.9181 | 0.0011947 | 2147 | 16.0493 | 23279.5968 | 0.43152 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5711 | 37 | 7.3647e-05 | 12101102 | OAKLAND K 1102 | OAKLAND K 1102circuit_breaker | 4723.266 | 0.0027249 | 2062 | 2.9349 | 23282.5317 | 0.42879 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3675 | 3 | 7.3262e-05 | 182492104 | HOLLISTER 2104 | HOLLISTER 210491424 | 430.1131 | 0.00021979 | 2275 | 0.26726 | 23282.7989 | 0.42857 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2386 | 228 | 7.265e-05 | 103732101 | PIT NO 3 2101 | PIT NO 3 21011360 | 33967.8078 | 0.016564 | 1808 | 21.1066 | 23303.9055 | 0.41201 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3292 | 261 | 7.1538e-05 | 103031102 | ORO FINO 1102 | ORO FINO 110276008 | 25688.6957 | 0.018671 | 1778 | 15.9622 | 23319.8677 | 0.39334 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1783 | 56 | 7.1186e-05 | 182941102 | OTTER 1102 | OTTER 110298036 | 14861.2597 | 0.0039864 | 2025 | 9.2344 | 23329.1021 | 0.38935 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1816 | 181 | 7.0733e-05 | 42761104 | FORT BRAGG A 1104 | FORT BRAGG A 11044690 | 18031.2616 | 0.012803 | 1856 | 11.2041 | 23340.3062 | 0.37655 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7364 | 25 | 6.8791e-05 | 163781704 | PEORIA 1704 | PEORIA 170413490 | 6383.5889 | 0.0017198 | 2118 | 3.9666 | 23344.2728 | 0.37483 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5681 | 149 | 6.7303e-05 | 102541101 | VOLTA 1101 | VOLTA 11011640 | 16481.2885 | 0.010028 | 1895 | 10.241 | 23354.5138 | 0.3648 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3628 | 60 | 6.5739e-05 | 183052108 | TEMPLETON 2108 | TEMPLETON 2108A40 | 5903.9832 | 0.0039443 | 2029 | 3.6686 | 23358.1823 | 0.36085 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7129 | 71 | 6.4044e-05 | 182941101 | OTTER 1101 | OTTER 11012052 | 7777.1247 | 0.0045471 | 2011 | 4.8325 | 23363.0148 | 0.35631 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6972 | 62 | 6.3618e-05 | 13432207 | FAIRVIEW 2207 | FAIRVIEW 220799096 | 15872.9643 | 0.0039443 | 2028 | 9.863 | 23372.8778 | 0.35236 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 748 | 210 | 6.1703e-05 | 43081101 | BIG RIVER 1101 | BIG RIVER 1101952 | 26689.2485 | 0.012958 | 1853 | 16.5839 | 23389.4617 | 0.3394 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 688 | 52 | 5.6936e-05 | 252811102 | MERCED FALLS 1102 | MERCED FALLS 11029460 | 14069.7042 | 0.0029607 | 2054 | 8.7425 | 23398.2042 | 0.33644 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 892 | 40 | 5.6086e-05 | 258591101 | TULE POWER HOUSE 1101 | TULE POWER HOUSE 1101circuit_breaker | 6363.6748 | 0.0022435 | 2089 | 3.9542 | 23402.1584 | 0.3342 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3727 | 2 | 5.4726e-05 | 43292102 | PUEBLO 2102 | PUEBLO 2102698 | 187.7325 | 0.00010945 | 2360 | 0.11665 | 23402.2751 | 0.33409 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 644 | 85 | 5.4118e-05 | 13801105 | MORAGA 1105 | MORAGA 1105circuit_breaker | 9314.4848 | 0.0046 | 2007 | 5.7878 | 23408.0629 | 0.32949 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 938 | 52 | 5.393e-05 | 83252106 | PAUL SWEET 2106 | PAUL SWEET 2106circuit_breaker | 8257.1442 | 0.0028044 | 2060 | 5.1307 | 23413.1936 | 0.32669 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 806 | 46 | 5.3926e-05 | 183071101 | PERRY 1101 | PERRY 1101V74 | 6365.4334 | 0.0024806 | 2076 | 3.9553 | 23417.1489 | 0.32421 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3780 | 177 | 5.4141e-05 | 82021106 | LOS GATOS 1106 | LOS GATOS 110660116 | 19897.4804 | 0.0095829 | 1905 | 12.3637 | 23429.5126 | 0.31462 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 3780 | 1 | 6.3716e-06 | 82021106 | LOS GATOS 1106 | LOS GATOS 110660116 | 19897.4804 | 6.3716e-06 | 1905 | 12.3637 | 23441.8763 | 0.31462 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Valley | 1263 | 174 | 5.3393e-05 | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 11012646 | 28470.7774 | 0.0092904 | 1916 | 17.6909 | 23459.5672 | 0.30533 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6983 | 27 | 5.2711e-05 | 102361101 | HAMILTON BRANCH 1101 | HAMILTON BRANCH 110190334 | 5355.1369 | 0.0014232 | 2131 | 3.3275 | 23462.8948 | 0.3039 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5645 | 37 | 5.221e-05 | 182492102 | HOLLISTER 2102 | HOLLISTER 2102855412 | 42101.5076 | 0.0019318 | 2104 | 26.1607 | 23489.0554 | 0.30197 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1912 | 19 | 5.1829e-05 | 83692104 | ROB ROY 2104 | ROB ROY 210410930 | 1570.0142 | 0.00098475 | 2160 | 0.97556 | 23490.031 | 0.30099 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7528 | 133 | 5.1296e-05 | 103091102 | CLARK ROAD 1102 | CLARK ROAD 11022068 | 16704.4746 | 0.0068224 | 1961 | 10.3797 | 23500.4107 | 0.29416 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 406 | 351 | 5.0163e-05 | 152481106 | BRUNSWICK 1106 | BRUNSWICK 11062796 | 31981.5846 | 0.017607 | 1793 | 19.8724 | 23520.2831 | 0.27656 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9005 | 5 | 5.0138e-05 | 103381102 | FRENCH GULCH 1102 | FRENCH GULCH 1102circuit_breaker | 2729.0129 | 0.00025069 | 2260 | 1.6957 | 23521.9788 | 0.27631 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7829 | 8 | 4.999e-05 | 253141103 | CUYAMA 1103 | CUYAMA 1103622728 | 3818.1464 | 0.00039992 | 2212 | 2.3725 | 23524.3513 | 0.27591 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6134 | 44 | 4.89e-05 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 11036012 | 8085.8325 | 0.0021516 | 2093 | 5.0243 | 23529.3756 | 0.27375 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6376 | 50 | 4.8358e-05 | 163160401 | PINECREST 0401 | PINECREST 04011818 | 5011.2665 | 0.0024179 | 2078 | 3.1139 | 23532.4895 | 0.27134 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7302 | 69 | 4.7521e-05 | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110136516 | 6707.2903 | 0.003279 | 2050 | 4.1677 | 23536.6572 | 0.26806 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7300 | 17 | 4.6802e-05 | 83182101 | LLAGAS 2101 | LLAGAS 21011451 | 9962.9329 | 0.00079564 | 2174 | 6.1907 | 23542.8479 | 0.26726 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4887 | 92 | 4.6558e-05 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012474 | 12716.7551 | 0.0042833 | 2017 | 7.9018 | 23550.7497 | 0.26298 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7853 | 50 | 4.5984e-05 | 14341106 | VALLEY VIEW 1106 | VALLEY VIEW 1106P166 | 7008.3242 | 0.0022992 | 2086 | 4.3548 | 23555.1045 | 0.26068 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7759 | 42 | 4.5551e-05 | 42491102 | SAUSALITO 1102 | SAUSALITO 11021268 | 8059.3403 | 0.0019131 | 2105 | 5.0078 | 23560.1123 | 0.25877 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 9147 | 8 | 4.4597e-05 | 254061102 | DUNLAP 1102 | DUNLAP 1102778286 | 4188.0047 | 0.00035677 | 2227 | 2.6023 | 23562.7146 | 0.25841 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2475 | 66 | 4.3598e-05 | 163661702 | MIWUK 1702 | MIWUK 17028090 | 6478.2235 | 0.0028775 | 2058 | 4.0254 | 23566.74 | 0.25553 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7253 | 45 | 4.346e-05 | 253671103 | PANOCHE 1103 | PANOCHE 11034008 | 56762.8241 | 0.0019557 | 2103 | 35.2708 | 23602.0108 | 0.25358 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 2429 | 42 | 4.3142e-05 | 162161102 | ELECTRA 1102 | ELECTRA 11026014 | 8101.0669 | 0.001812 | 2111 | 5.0338 | 23607.0445 | 0.25176 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3422 | 219 | 4.3007e-05 | 103132101 | CRESCENT MILLS 2101 | CRESCENT MILLS 21012232 | 22620.3804 | 0.0094184 | 1911 | 14.0556 | 23621.1002 | 0.24235 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6606 | 63 | 4.2384e-05 | 152481110 | BRUNSWICK 1110 | BRUNSWICK 111063100 | 6591.8915 | 0.0026702 | 2064 | 4.096 | 23625.1962 | 0.23968 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6218 | 206 | 4.1703e-05 | 182222104 | DEL MONTE 2104 | DEL MONTE 21043088 | 24826.2717 | 0.0085907 | 1927 | 15.4263 | 23640.6225 | 0.23109 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4963 | 12 | 4.0928e-05 | 152591102 | SUMMIT 1102 | SUMMIT 11022302 | 2346.259 | 0.00049113 | 2196 | 1.4579 | 23642.0804 | 0.23059 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 219 | 256 | 4.0107e-05 | 83692104 | ROB ROY 2104 | ROB ROY 210410960 | 27847.2688 | 0.010267 | 1890 | 17.3035 | 23659.3839 | 0.22033 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5636 | 116 | 3.9646e-05 | 83692104 | ROB ROY 2104 | ROB ROY 210410954 | 11322.6315 | 0.0045989 | 2008 | 7.0356 | 23666.4194 | 0.21573 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3387 | 292 | 3.926e-05 | 152491101 | WEIMAR 1101 | WEIMAR 11012740 | 30589.1767 | 0.011464 | 1873 | 19.0072 | 23685.4267 | 0.20426 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1216 | 427 | 3.8622e-05 | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS CEMENT 110147968 | 65252.4191 | 0.016492 | 1810 | 40.546 | 23725.9726 | 0.18777 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7700 | 33 | 3.8384e-05 | 182941102 | OTTER 1102 | OTTER 1102circuit_breaker | 10537.6394 | 0.0012667 | 2140 | 6.5478 | 23732.5204 | 0.18651 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 816 | 92 | 3.8195e-05 | 14161101 | ROSSMOOR 1101 | ROSSMOOR 110168920 | 9481.3207 | 0.0035139 | 2041 | 5.8914 | 23738.4118 | 0.18299 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2873 | 63 | 3.7601e-05 | 83692105 | ROB ROY 2105 | ROB ROY 210538430 | 8878.6769 | 0.0023689 | 2080 | 5.517 | 23743.9288 | 0.18062 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5619 | 71 | 3.6778e-05 | 182222104 | DEL MONTE 2104 | DEL MONTE 21049500 | 9189.3701 | 0.0026112 | 2069 | 5.71 | 23749.6388 | 0.17801 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5760 | 63 | 3.429e-05 | 162831702 |  | 693441 | 6840.8929 | 0.0021602 | 2092 | 4.2507 | 23753.8895 | 0.17585 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2346 | 483 | 3.4122e-05 | 152241102 | HALSEY 1102 | HALSEY 110239104 | 48994.5328 | 0.016481 | 1811 | 30.4438 | 23784.3333 | 0.15937 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 571 | 176 | 3.4072e-05 | 83392110 | SWIFT 2110 | SWIFT 2110XR332 | 79862.0317 | 0.0059967 | 1973 | 49.624 | 23833.9573 | 0.15337 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1047 | 2 | 3.3723e-05 | 13501101 | JARVIS 1101 | JARVIS 1101MR210 | 567.7092 | 6.7445e-05 | 2436 | 0.35276 | 23834.31 | 0.15331 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4450 | 38 | 3.2967e-05 | 14341106 | VALLEY VIEW 1106 | VALLEY VIEW 1106circuit_breaker | 5669.0772 | 0.0012527 | 2141 | 3.5226 | 23837.8326 | 0.15205 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4796 | 65 | 3.279e-05 | 103381102 | FRENCH GULCH 1102 | FRENCH GULCH 11021462 | 14444.9129 | 0.0021314 | 2094 | 8.9756 | 23846.8083 | 0.14992 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3405 | 72 | 3.2695e-05 | 42011107 | SAN RAFAEL 1107 | SAN RAFAEL 1107circuit_breaker | 7424.3496 | 0.0023541 | 2082 | 4.6133 | 23851.4215 | 0.14757 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5230 | 75 | 3.0933e-05 | 42011108 | SAN RAFAEL 1108 | SAN RAFAEL 1108circuit_breaker | 6729.9719 | 0.00232 | 2084 | 4.1818 | 23855.6033 | 0.14525 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2988 | 410 | 3.0887e-05 | 182371111 | LAURELES 1111 | LAURELES 1111432 | 79055.4755 | 0.012664 | 1857 | 49.1228 | 23904.7261 | 0.13258 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2382 | 219 | 2.8153e-05 | 42761102 | FORT BRAGG A 1102 | FORT BRAGG A 110235592 | 21272.3021 | 0.0061655 | 1970 | 13.218 | 23917.9441 | 0.12642 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 147 | 21 | 2.7968e-05 | 152591102 | SUMMIT 1102 | SUMMIT 1102circuit_breaker | 1626.5971 | 0.00058732 | 2189 | 1.0107 | 23918.9548 | 0.12583 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 9546 | 3 | 2.7932e-05 | 163781704 | PEORIA 1704 | PEORIA 170488630 | 1252.5971 | 8.3796e-05 | 2397 | 0.77833 | 23919.7332 | 0.12575 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6413 | 66 | 2.7171e-05 | 42841111 | GUALALA 1111 | GUALALA 1111887180 | 7924.3024 | 0.0017933 | 2113 | 4.9239 | 23924.6571 | 0.12395 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8206 | 23 | 2.5865e-05 | 182941101 | OTTER 1101 | OTTER 1101circuit_breaker | 9899.5429 | 0.00059489 | 2188 | 6.1513 | 23930.8084 | 0.12336 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5225 | 77 | 2.5847e-05 | 103732101 | PIT NO 3 2101 | PIT NO 3 21011386 | 10692.089 | 0.0019902 | 2101 | 6.6438 | 23937.4521 | 0.12137 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3496 | 150 | 2.5498e-05 | 14671102 | SOBRANTE 1102 | SOBRANTE 1102circuit_breaker | 16784.222 | 0.0038248 | 2032 | 10.4292 | 23947.8814 | 0.11755 | 10.6581 | 0.0038248 | 1 | #N/A | 0.11755 | #N/A
Central Valley | 1876 | 73 | 2.4865e-05 | 163451701 | FROGTOWN 1701 | FROGTOWN 17016807 | 7647.5853 | 0.0018152 | 2110 | 4.752 | 23952.6334 | 0.11573 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6692 | 1 | 2.4798e-05 | 182191101 | SAN ARDO 1101 | SAN ARDO 110193072 | 1004.5467 | 2.4798e-05 | 2568 | 0.6242 | 23953.2576 | 0.11571 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5099 | 14 | 2.4115e-05 | 83622104 | CAMP EVERS 2104 | CAMP EVERS 2104circuit_breaker | 1223.0517 | 0.0003376 | 2233 | 0.75997 | 23954.0175 | 0.11537 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9664 | 1 | 2.3974e-05 | 192221102 | GARBERVILLE 1102 | GARBERVILLE 11022124 | 5026.2322 | 2.3974e-05 | 2574 | 3.1232 | 23957.1407 | 0.11534 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 854 | 32 | 2.3782e-05 | 13432207 | FAIRVIEW 2207 | FAIRVIEW 2207M501R | 3375.143 | 0.00076101 | 2176 | 2.0972 | 23959.2379 | 0.11458 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8613 | 11 | 2.3185e-05 | 82931101 | POINT MORETTI 1101 | POINT MORETTI 11015074 | 2072.4094 | 0.00025504 | 2259 | 1.2877 | 23960.5256 | 0.11433 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7628 | 128 | 2.283e-05 | 182222104 | DEL MONTE 2104 | DEL MONTE 21042762 | 14335.4933 | 0.0029222 | 2055 | 8.9077 | 23969.4333 | 0.11141 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1532 | 43 | 2.2768e-05 | 43321103 | RINCON 1103 | RINCON 1103472 | 4843.5768 | 0.00097903 | 2161 | 3.0097 | 23972.4429 | 0.11043 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1431 | 5 | 2.1279e-05 | 182082103 | LOS OSITOS 2103 | LOS OSITOS 21033010 | 49533.9507 | 0.0001064 | 2367 | 30.779 | 24003.2219 | 0.11032 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7288 | 37 | 2.1079e-05 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 210616000 | 3279.9189 | 0.00077994 | 2175 | 2.038 | 24005.26 | 0.10954 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5169 | 19 | 2.1004e-05 | 42981101 | ELK 1101 | ELK 11011300 | 2515.6031 | 0.00039907 | 2213 | 1.5631 | 24006.8231 | 0.10914 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 606 | 10 | 2.0605e-05 | 182492105 | HOLLISTER 2105 | HOLLISTER 21054724 | 7277.4055 | 0.00020605 | 2288 | 4.522 | 24011.345 | 0.10893 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8776 | 2 | 2.0012e-05 | 88820401 | COAST RD 0401 | COAST RD 04015134 | 465.4637 | 4.0025e-05 | 2511 | 0.28923 | 24011.6343 | 0.10889 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6856 | 32 | 1.9122e-05 | 162161102 | ELECTRA 1102 | ELECTRA 1102circuit_breaker | 4216.8732 | 0.00061191 | 2185 | 2.6202 | 24014.2545 | 0.10828 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 9623 | 4 | 1.8858e-05 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210595394 | 797.3729 | 7.5431e-05 | 2415 | 0.49546 | 24014.75 | 0.10821 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4629 | 48 | 1.866e-05 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210574170 | 5724.1198 | 0.00089567 | 2166 | 3.5568 | 24018.3068 | 0.10731 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2007 | 49 | 1.8066e-05 | 13340401 | SPRUCE 0401 | SPRUCE 0401BR316 | 6628.9852 | 0.00088523 | 2167 | 4.1191 | 24022.4258 | 0.10643 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7834 | 8 | 1.7889e-05 | 103381101 | FRENCH GULCH 1101 | FRENCH GULCH 11011464 | 1371.4854 | 0.00014311 | 2329 | 0.8522 | 24023.278 | 0.10628 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2075 | 102 | 1.775e-05 | 152241102 | HALSEY 1102 | HALSEY 11025739 | 10731.8696 | 0.0018105 | 2112 | 6.6685 | 24029.9465 | 0.10447 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4261 | 10 | 1.7726e-05 | 182731102 | RESERVATION ROAD 1102 | RESERVATION ROAD 110222136 | 1694.8476 | 0.00017726 | 2304 | 1.0531 | 24030.9996 | 0.1043 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9138 | 3 | 1.7629e-05 | 192171101 | WILLOW CREEK 1101 | WILLOW CREEK 1101circuit_breaker | 437.858 | 5.2886e-05 | 2472 | 0.27207 | 24031.2717 | 0.10424 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 732 | 2 | 1.7373e-05 | 182331101 | GABILAN 1101 | GABILAN 11013034 | 558.7507 | 3.4746e-05 | 2526 | 0.34719 | 24031.6189 | 0.10421 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8571 | 3 | 1.7354e-05 | 83040401 | BEN LOMOND 0401 | BEN LOMOND 04015400 | 712.5707 | 5.2063e-05 | 2475 | 0.44277 | 24032.0617 | 0.10416 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2265 | 17 | 1.7288e-05 | 83040401 | BEN LOMOND 0401 | BEN LOMOND 040116010 | 2728.9115 | 0.0002939 | 2245 | 1.6957 | 24033.7573 | 0.10386 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5747 | 76 | 1.7162e-05 | 83040401 | BEN LOMOND 0401 | BEN LOMOND 0401circuit_breaker | 12506.4618 | 0.0013043 | 2137 | 7.7712 | 24041.5285 | 0.10256 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8949 | 2 | 1.6595e-05 | 82831109 | MILPITAS 1109 | MILPITAS 1109XR044 | 77.0548 | 3.3191e-05 | 2535 | 0.04788 | 24041.5764 | 0.10252 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6283 | 3 | 1.6591e-05 | 82841101 | BIG BASIN 1101 | BIG BASIN 11015479 | 274.045 | 4.9772e-05 | 2479 | 0.17028 | 24041.7467 | 0.10247 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6320 | 18 | 1.6398e-05 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 21055577 | 1864.9283 | 0.00029517 | 2244 | 1.1588 | 24042.9055 | 0.10218 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 923 | 61 | 1.6287e-05 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210511384 | 6564.1653 | 0.00099352 | 2159 | 4.0788 | 24046.9843 | 0.10119 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2347 | 19 | 1.6097e-05 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 21059031 | 1758.1932 | 0.00030583 | 2241 | 1.0925 | 24048.0767 | 0.10088 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9616 | 1 | 1.5991e-05 | 192251102 | RIO DELL 1102 | RIO DELL 11027124 | 1081.3743 | 1.5991e-05 | 2621 | 0.67193 | 24048.7487 | 0.10086 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 9640 | 2 | 1.5975e-05 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210510996 | 1226.2093 | 3.1949e-05 | 2538 | 0.76193 | 24049.5106 | 0.10083 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5464 | 128 | 1.5966e-05 | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101978 | 17657.6918 | 0.0020436 | 2098 | 10.972 | 24060.4826 | 0.098789 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3444 | 29 | 1.5563e-05 | 103181101 | CHESTER 1101 | CHESTER 1101circuit_breaker | 3248.2591 | 0.00045133 | 2205 | 2.0184 | 24062.501 | 0.098337 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 16 | 20 | 1.5554e-05 | 42011106 | SAN RAFAEL 1106 | SAN RAFAEL 1106910 | 2037.0021 | 0.00031109 | 2239 | 1.2657 | 24063.7667 | 0.098026 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3733 | 142 | 1.5546e-05 | 83371105 | SARATOGA 1105 | SARATOGA 1105LC14 | 15716.535 | 0.0022075 | 2091 | 9.7658 | 24073.5325 | 0.095819 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6797 | 78 | 1.5467e-05 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210510786 | 7281.933 | 0.0012064 | 2146 | 4.5248 | 24078.0573 | 0.094612 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5172 | 1 | 1.5374e-05 | 192381103 | EEL RIVER 1103 | EEL RIVER 11033820 | 5191.5083 | 1.5374e-05 | 2626 | 3.2259 | 24081.2831 | 0.094597 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 898 | 33 | 1.5316e-05 | 13350402 | WALDO 0402 | WALDO 0402circuit_breaker | 4721.9877 | 0.00050542 | 2195 | 2.9341 | 24084.2172 | 0.094092 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8058 | 82 | 1.5088e-05 | 182222104 | DEL MONTE 2104 | DEL MONTE 210436720 | 9052.9085 | 0.0012372 | 2143 | 5.6252 | 24089.8425 | 0.092854 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2449 | 12 | 1.5082e-05 | 182131101 | GONZALES 1101 | GONZALES 11013094 | 5968.4042 | 0.00018099 | 2301 | 3.7086 | 24093.551 | 0.092673 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7211 | 27 | 1.4846e-05 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 210611006 | 3330.3404 | 0.00040085 | 2211 | 2.0694 | 24095.6204 | 0.092273 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6991 | 7 | 1.4755e-05 | 82841101 | BIG BASIN 1101 | BIG BASIN 110165444 | 738.7266 | 0.00010328 | 2371 | 0.45902 | 24096.0794 | 0.092169 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8862 | 14 | 1.4749e-05 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 2106834583 | 972.7555 | 0.00020649 | 2287 | 0.60444 | 24096.6839 | 0.091963 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3271 | 87 | 1.459e-05 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 21055146 | 9692.8148 | 0.0012694 | 2139 | 6.0228 | 24102.7067 | 0.090693 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 463 | 73 | 1.4337e-05 | 82841101 | BIG BASIN 1101 | BIG BASIN 11015028 | 7931.4866 | 0.0010466 | 2156 | 4.9284 | 24107.6351 | 0.089647 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3377 | 9 | 1.4286e-05 | 102831106 | PARADISE 1106 | PARADISE 11061212 | 9061.9313 | 0.00012857 | 2342 | 5.6308 | 24113.2659 | 0.089518 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4273 | 2 | 1.4177e-05 | 102541101 | VOLTA 1101 | VOLTA 11011516 | 39161.809 | 2.8354e-05 | 2551 | 24.334 | 24137.6 | 0.08949 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5106 | 16 | 1.3809e-05 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 21061625 | 1453.5601 | 0.00022095 | 2274 | 0.9032 | 24138.5032 | 0.089269 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 125 | 66 | 1.3786e-05 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 21055232 | 7297.0471 | 0.00090985 | 2165 | 4.5342 | 24143.0373 | 0.088359 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1735 | 28 | 1.3359e-05 | 42811112 | MONTE RIO 1112 | MONTE RIO 111264682 | 2767.8678 | 0.00037406 | 2220 | 1.7199 | 24144.7572 | 0.087985 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1440 | 133 | 1.3327e-05 | 153082106 | PLACERVILLE 2106 | PLACERVILLE 210619732 | 14586.2182 | 0.0017725 | 2114 | 9.0635 | 24153.8207 | 0.086213 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4517 | 1 | 1.3323e-05 | 24101102 | HALF MOON BAY 1102 | HALF MOON BAY 1102circuit_breaker | 168.7519 | 1.3323e-05 | 2640 | 0.10486 | 24153.9255 | 0.086199 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3806 | 35 | 1.3239e-05 | 182052102 | SOLEDAD 2102 | SOLEDAD 210242506 | 13203.3163 | 0.00046337 | 2202 | 8.2042 | 24162.1297 | 0.085736 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8034 | 7 | 1.3231e-05 | 182191101 | SAN ARDO 1101 | SAN ARDO 11017094 | 1399.194 | 9.262e-05 | 2384 | 0.86942 | 24162.9991 | 0.085643 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6732 | 8 | 1.3218e-05 | 182492104 | HOLLISTER 2104 | HOLLISTER 21044403 | 9894.6539 | 0.00010574 | 2369 | 6.1483 | 24169.1473 | 0.085537 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5667 | 90 | 1.3053e-05 | 182371112 | LAURELES 1112 | LAURELES 11122768 | 9769.2909 | 0.0011748 | 2149 | 6.0704 | 24175.2177 | 0.084363 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 632 | 71 | 1.2892e-05 | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210511004 | 6906.8406 | 0.00091536 | 2164 | 4.2917 | 24179.5094 | 0.083447 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5274 | 9 | 1.2875e-05 | 102831106 | PARADISE 1106 | PARADISE 1106circuit_breaker | 16790.7997 | 0.00011587 | 2352 | 10.4333 | 24189.9427 | 0.083331 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2058 | 4 | 1.2653e-05 | 42711102 | CALISTOGA 1102 | CALISTOGA 1102706 | 636.0356 | 5.0612e-05 | 2477 | 0.39521 | 24190.3379 | 0.083281 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5186 | 3 | 1.2576e-05 | 42561104 | FULTON 1104 | FULTON 1104466 | 626.0978 | 3.7728e-05 | 2517 | 0.38904 | 24190.727 | 0.083243 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6165 | 12 | 1.2433e-05 | 82841102 | BIG BASIN 1102 | BIG BASIN 11029741 | 1047.536 | 0.0001492 | 2323 | 0.65091 | 24191.3779 | 0.083094 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5356 | 126 | 1.2227e-05 | 103271101 | ANTLER 1101 | ANTLER 11011384 | 14263.9901 | 0.0015406 | 2127 | 8.8632 | 24200.2411 | 0.081553 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7580 | 16 | 1.219e-05 | 83622104 | CAMP EVERS 2104 | CAMP EVERS 210411048 | 1365.3169 | 0.00019504 | 2296 | 0.84837 | 24201.0895 | 0.081358 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8302 | 3 | 1.217e-05 | 42811111 | MONTE RIO 1111 | MONTE RIO 1111circuit_breaker | 425.3264 | 3.6511e-05 | 2522 | 0.26429 | 24201.3538 | 0.081322 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 9412 | 7 | 1.2141e-05 | 153652110 | SHINGLE SPRINGS 2110 | SHINGLE SPRINGS 2110circuit_breaker | 1202.0334 | 8.4988e-05 | 2395 | 0.74691 | 24202.1007 | 0.081237 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4394 | 10 | 1.2123e-05 | 43432105 | SILVERADO 2105 | SILVERADO 2105circuit_breaker | 958.0432 | 0.00012123 | 2344 | 0.5953 | 24202.696 | 0.081115 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5648 | 101 | 1.2118e-05 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 210611044 | 12091.4268 | 0.0012239 | 2145 | 7.5133 | 24210.2092 | 0.079892 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6649 | 18 | 1.1913e-05 | 42811111 | MONTE RIO 1111 | MONTE RIO 1111506 | 1987.3505 | 0.00021443 | 2281 | 1.2349 | 24211.4441 | 0.079677 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6410 | 39 | 1.1785e-05 | 24251104 | WOODSIDE 1104 | WOODSIDE 11043583 | 4480.4665 | 0.00045963 | 2203 | 2.784 | 24214.2281 | 0.079218 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3011 | 16 | 1.1717e-05 | 103271101 | ANTLER 1101 | ANTLER 1101circuit_breaker | 2574.4725 | 0.00018747 | 2299 | 1.5997 | 24215.8278 | 0.07903 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8417 | 3 | 1.1677e-05 | 82841102 | BIG BASIN 1102 | BIG BASIN 110212779 | 407.3922 | 3.5032e-05 | 2525 | 0.25314 | 24216.081 | 0.078995 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7992 | 15 | 1.1677e-05 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 21067603 | 1504.5923 | 0.00017516 | 2307 | 0.93491 | 24217.0159 | 0.07882 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1978 | 2 | 1.1591e-05 | 153652108 | SHINGLE SPRINGS 2108 | SHINGLE SPRINGS 210851474 | 394.2246 | 2.3182e-05 | 2578 | 0.24496 | 24217.2609 | 0.078797 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4979 | 31 | 1.1588e-05 | 24251101 | WOODSIDE 1101 | WOODSIDE 11018522 | 3168.3928 | 0.00035924 | 2226 | 1.9687 | 24219.2296 | 0.078437 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6764 | 6 | 1.1506e-05 | 42491102 | SAUSALITO 1102 | SAUSALITO 11021500 | 1851.8444 | 6.9038e-05 | 2432 | 1.1507 | 24220.3803 | 0.078368 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8385 | 3 | 1.1443e-05 | 192311141 | FRUITLAND 1141 | FRUITLAND 11418746 | 895.774 | 3.4329e-05 | 2530 | 0.55661 | 24220.9369 | 0.078334 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7215 | 32 | 1.1354e-05 | 24251101 | WOODSIDE 1101 | WOODSIDE 11012299 | 2949.4431 | 0.00036334 | 2225 | 1.8327 | 24222.7696 | 0.077971 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3490 | 1 | 1.1152e-05 | 83182106 | LLAGAS 2106 | LLAGAS 2106XR146 | 2566.3115 | 1.1152e-05 | 2666 | 1.5946 | 24224.3642 | 0.07796 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5661 | 9 | 1.1068e-05 | 82841101 | BIG BASIN 1101 | BIG BASIN 11019773 | 724.7249 | 9.9609e-05 | 2374 | 0.45032 | 24224.8146 | 0.07786 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2826 | 26 | 1.0919e-05 | 42811111 | MONTE RIO 1111 | MONTE RIO 11111701 | 2197.6127 | 0.0002839 | 2247 | 1.3655 | 24226.1801 | 0.077576 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9376 | 6 | 1.0833e-05 | 43091103 | GREENBRAE 1103 | GREENBRAE 11036083 | 549.3456 | 6.5e-05 | 2443 | 0.34135 | 24226.5214 | 0.077511 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 546 | 40 | 1.0726e-05 | 152481107 | BRUNSWICK 1107 | BRUNSWICK 110750008 | 3726.9612 | 0.00042903 | 2207 | 2.3158 | 24228.8373 | 0.077082 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8373 | 10 | 1.0592e-05 | 83622106 | CAMP EVERS 2106 | CAMP EVERS 2106circuit_breaker | 828.2056 | 0.00010592 | 2368 | 0.51462 | 24229.3519 | 0.076976 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5867 | 46 | 1.0434e-05 | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110139126 | 3614.1844 | 0.00047994 | 2199 | 2.2457 | 24231.5976 | 0.076496 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7098 | 17 | 1.0316e-05 | 192171103 | WILLOW CREEK 1103 | WILLOW CREEK 1103circuit_breaker | 6235.9798 | 0.00017537 | 2306 | 3.8749 | 24235.4725 | 0.076321 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 8182 | 14 | 1.0215e-05 | 153612109 | CLARKSVILLE 2109 | CLARKSVILLE 210951744 | 1413.2019 | 0.00014301 | 2330 | 0.87812 | 24236.3506 | 0.076178 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3714 | 27 | 1.0188e-05 | 83622103 | CAMP EVERS 2103 | CAMP EVERS 210355638 | 2080.9167 | 0.00027507 | 2251 | 1.293 | 24237.6436 | 0.075903 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6059 | 1 | 1.423e-05 | 42811113 | MONTE RIO 1113 | MONTE RIO 1113250 | 1971.2642 | 1.423e-05 | 2290 | 1.2249 | 24238.8685 | 0.075888 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 6059 | 19 | 9.9696e-06 | 42811113 | MONTE RIO 1113 | MONTE RIO 1113250 | 1971.2642 | 0.00018942 | 2290 | 1.2249 | 24240.0934 | 0.075699 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Valley | 7192 | 1 | 1.0153e-05 | 163201101 | WEST POINT 1101 | WEST POINT 1101L2219 | 5487.8839 | 1.0153e-05 | 2677 | 3.41 | 24243.5034 | 0.075689 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 388 | 28 | 1.01e-05 | 24251104 | WOODSIDE 1104 | WOODSIDE 11049032 | 6850.4288 | 0.0002828 | 2249 | 4.2567 | 24247.7601 | 0.075406 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7484 | 35 | 1.0093e-05 | 42811112 | MONTE RIO 1112 | MONTE RIO 1112212 | 3618.1726 | 0.00035327 | 2229 | 2.2482 | 24250.0083 | 0.075053 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6747 | 25 | 9.9751e-06 | 183582101 | BURNS 2101 | BURNS 2101circuit_breaker | 2668.3535 | 0.00024938 | 2262 | 1.658 | 24251.6663 | 0.074803 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3669 | 3 | 9.9469e-06 | 102831104 | PARADISE 1104 | PARADISE 1104920400 | 7211.2587 | 2.9841e-05 | 2548 | 4.4809 | 24256.1472 | 0.074774 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9863 | 1 | 9.8611e-06 | 101321101 | PIT NO 5 1101 | PIT NO 5 110190846 | 149.205 | 9.8611e-06 | 2683 | 0.092712 | 24256.2399 | 0.074764 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1812 | 112 | 9.59e-06 | 43081101 | BIG RIVER 1101 | BIG RIVER 11013002 | 11691.8924 | 0.0010741 | 2152 | 7.265 | 24263.5049 | 0.07369 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 9899 | 1 | 9.5707e-06 | 152031103 | GRASS VALLEY 1103 | GRASS VALLEY 1103circuit_breaker | 191.1806 | 9.5707e-06 | 2690 | 0.11879 | 24263.6237 | 0.07368 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6857 | 2 | 9.5334e-06 | 163201101 | WEST POINT 1101 | WEST POINT 1101L373 | 12006.0598 | 1.9067e-05 | 2601 | 7.4602 | 24271.0839 | 0.073661 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 722 | 8 | 9.5085e-06 | 43432105 | SILVERADO 2105 | SILVERADO 21051308 | 812.0716 | 7.6068e-05 | 2412 | 0.5046 | 24271.5885 | 0.073585 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3911 | 6 | 9.4913e-06 | 182071101 | CAMPHORA 1101 | CAMPHORA 110177978 | 3393.7443 | 5.6948e-05 | 2460 | 2.1088 | 24273.6973 | 0.073528 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3631 | 30 | 9.3801e-06 | 153652105 | SHINGLE SPRINGS 2105 | SHINGLE SPRINGS 210511172 | 3051.051 | 0.0002814 | 2250 | 1.8958 | 24275.5931 | 0.073247 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 8165 | 3 | 9.3401e-06 | 152481110 | BRUNSWICK 1110 | BRUNSWICK 111094368 | 431.1432 | 2.802e-05 | 2552 | 0.2679 | 24275.861 | 0.073219 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3927 | 102 | 9.3224e-06 | 254061103 | DUNLAP 1103 | DUNLAP 11037080 | 17013.9683 | 0.00095088 | 2163 | 10.572 | 24286.433 | 0.072268 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6393 | 55 | 9.2835e-06 | 83252102 | PAUL SWEET 2102 | PAUL SWEET 21025291 | 5450.0475 | 0.00051059 | 2193 | 3.3865 | 24289.8195 | 0.071757 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1503 | 29 | 9.1338e-06 | 102361101 | HAMILTON BRANCH 1101 | HAMILTON BRANCH 1101circuit_breaker | 3577.0016 | 0.00026488 | 2253 | 2.2226 | 24292.0422 | 0.071492 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4802 | 166 | 9.0946e-06 | 192171103 | WILLOW CREEK 1103 | WILLOW CREEK 11035012 | 17863.1995 | 0.0015097 | 2128 | 11.0997 | 24303.1418 | 0.069983 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7583 | 23 | 8.9357e-06 | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 110740353 | 2152.3519 | 0.00020552 | 2289 | 1.3374 | 24304.4793 | 0.069777 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1395 | 3 | 8.8293e-06 | 22811103 | PACIFICA 1103 | PACIFICA 1103circuit_breaker | 224.0976 | 2.6488e-05 | 2562 | 0.13925 | 24304.6185 | 0.069751 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 409 | 9 | 8.7329e-06 | 22811102 | PACIFICA 1102 | PACIFICA 1102circuit_breaker | 430.7272 | 7.8596e-05 | 2406 | 0.26764 | 24304.8861 | 0.069672 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8305 | 4 | 8.6353e-06 | 163781704 | PEORIA 1704 | PEORIA 17046090 | 1011.0046 | 3.4541e-05 | 2528 | 0.62821 | 24305.5144 | 0.069637 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8366 | 7 | 8.5875e-06 | 42091102 | MIRABEL 1102 | MIRABEL 11027401 | 1171.4888 | 6.0113e-05 | 2452 | 0.72793 | 24306.2423 | 0.069577 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6609 | 148 | 8.4165e-06 | 182222104 | DEL MONTE 2104 | DEL MONTE 21042624 | 29790.8638 | 0.0012456 | 2142 | 18.5112 | 24324.7535 | 0.068332 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4302 | 24 | 8.4103e-06 | 14161106 | ROSSMOOR 1106 | ROSSMOOR 1106circuit_breaker | 2246.1308 | 0.00020185 | 2292 | 1.3957 | 24326.1491 | 0.06813 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1430 | 243 | 8.344e-06 | 103031101 | ORO FINO 1101 | ORO FINO 1101121988 | 29450.0073 | 0.0020276 | 2100 | 18.2994 | 24344.4485 | 0.066102 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 3210 | 14 | 8.2252e-06 | 163761703 | RACETRACK 1703 | RACETRACK 170310850 | 927.6524 | 0.00011515 | 2353 | 0.57642 | 24345.0249 | 0.065987 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 661 | 19 | 8.2066e-06 | 152531101 | FLINT 1101 | FLINT 110140666 | 1886.431 | 0.00015593 | 2317 | 1.1722 | 24346.1971 | 0.065831 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9142 | 73 | 8.1926e-06 | 42841111 | GUALALA 1111 | GUALALA 1111445166 | 9193.5626 | 0.00059806 | 2187 | 5.7126 | 24351.9097 | 0.065233 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3212 | 79 | 8.1848e-06 | 83622103 | CAMP EVERS 2103 | CAMP EVERS 210310946 | 8744.1235 | 0.0006466 | 2182 | 5.4333 | 24357.3431 | 0.064586 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6317 | 1 | 8.9187e-06 | 152691104 | HIGGINS 1104 | HIGGINS 110432747 | 966.1489 | 8.9187e-06 | 2390 | 0.60034 | 24357.9434 | 0.064578 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Sierra | 6317 | 10 | 8.0984e-06 | 152691104 | HIGGINS 1104 | HIGGINS 110432747 | 966.1489 | 8.0984e-05 | 2390 | 0.60034 | 24358.5437 | 0.064497 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 1534 | 6 | 8.1086e-06 | 42151104 | SANTA ROSA A 1104 | SANTA ROSA A 1104circuit_breaker | 380.5489 | 4.8652e-05 | 2483 | 0.23646 | 24358.7802 | 0.064448 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6440 | 5 | 8.0931e-06 | 14341106 | VALLEY VIEW 1106 | VALLEY VIEW 1106P128 | 184.0685 | 4.0465e-05 | 2509 | 0.11437 | 24358.8946 | 0.064407 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4306 | 28 | 8.0242e-06 | 153651103 | SHINGLE SPRINGS 1103 | SHINGLE SPRINGS 11038752 | 2895.0362 | 0.00022468 | 2271 | 1.7989 | 24360.6935 | 0.064183 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8674 | 1 | 7.9052e-06 | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 1105circuit_breaker | 296.5288 | 7.9052e-06 | 2705 | 0.18425 | 24360.8777 | 0.064175 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8980 | 10 | 7.8955e-06 | 42291101 | OLEMA 1101 | OLEMA 110149756 | 1000.1369 | 7.8955e-05 | 2403 | 0.62146 | 24361.4992 | 0.064096 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 817 | 10 | 7.8663e-06 | 152481104 | BRUNSWICK 1104 | BRUNSWICK 110456468 | 8462.4654 | 7.8663e-05 | 2405 | 5.2583 | 24366.7575 | 0.064017 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8089 | 21 | 7.8562e-06 | 43081101 | BIG RIVER 1101 | BIG RIVER 1101circuit_breaker | 2894.9274 | 0.00016498 | 2311 | 1.7988 | 24368.5563 | 0.063852 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5049 | 28 | 7.8457e-06 | 42811113 | MONTE RIO 1113 | MONTE RIO 11135026 | 2955.8477 | 0.00021968 | 2276 | 1.8367 | 24370.393 | 0.063633 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8134 | 40 | 7.829e-06 | 82931101 | POINT MORETTI 1101 | POINT MORETTI 11015401 | 4092.0757 | 0.00031316 | 2238 | 2.5427 | 24372.9357 | 0.063319 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5312 | 189 | 7.7744e-06 | 42761101 | FORT BRAGG A 1101 | FORT BRAGG A 11013100 | 19614.6509 | 0.0014694 | 2130 | 12.188 | 24385.1237 | 0.06185 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7519 | 51 | 7.7463e-06 | 152241101 | HALSEY 1101 | HALSEY 11015731 | 5029.6194 | 0.00039506 | 2215 | 3.1253 | 24388.2489 | 0.061455 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 957 | 3 | 7.7314e-06 | 152481103 | BRUNSWICK 1103 | BRUNSWICK 1103circuit_breaker | 8459.5799 | 2.3194e-05 | 2577 | 5.2565 | 24393.5055 | 0.061432 | 5.2894 | 2.2599e-05 | 1 | #N/A | 0.061432 | #N/A
North Coast | 7206 | 3 | 7.716e-06 | 42091102 | MIRABEL 1102 | MIRABEL 1102841 | 1089.713 | 2.3148e-05 | 2579 | 0.67712 | 24394.1826 | 0.061409 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 488 | 49 | 7.6627e-06 | 152161101 | AUBURN 1101 | AUBURN 1101circuit_breaker | 5202.5567 | 0.00037547 | 2219 | 3.2327 | 24397.4153 | 0.061033 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 685 | 42 | 7.6293e-06 | 42151107 | SANTA ROSA A 1107 | SANTA ROSA A 1107circuit_breaker | 4761.8386 | 0.00032043 | 2237 | 2.9589 | 24400.3742 | 0.060713 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3696 | 30 | 7.4892e-06 | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LA46 | 2467.6552 | 0.00022468 | 2272 | 1.5333 | 24401.9075 | 0.060488 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3409 | 135 | 7.4601e-06 | 152491101 | WEIMAR 1101 | WEIMAR 1101circuit_breaker | 14826.071 | 0.0010071 | 2158 | 9.2125 | 24411.12 | 0.059481 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4764 | 5 | 7.447e-06 | 42811113 | MONTE RIO 1113 | MONTE RIO 1113532 | 836.4221 | 3.7235e-05 | 2519 | 0.51973 | 24411.6397 | 0.059444 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 836 | 3 | 7.4351e-06 | 153651104 | SHINGLE SPRINGS 1104 | SHINGLE SPRINGS 1104circuit_breaker | 901.8218 | 2.2305e-05 | 2581 | 0.56037 | 24412.2001 | 0.059421 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3013 | 1 | 7.4332e-06 | 43191102 | REDBUD 1102 | REDBUD 11022013 | 125.6367 | 7.4332e-06 | 2709 | 0.078067 | 24412.2782 | 0.059414 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9617 | 1 | 7.3847e-06 | 42281104 | POTTER VALLEY P H 1104 | POTTER VALLEY P H 1104circuit_breaker | 158.6806 | 7.3847e-06 | 2710 | 0.0986 | 24412.3768 | 0.059407 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1409 | 6 | 7.3809e-06 | 163240402 | TAR FLAT 0402 | TAR FLAT 0402circuit_breaker | 1258.5471 | 4.4286e-05 | 2496 | 0.78202 | 24413.1588 | 0.059362 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1656 | 228 | 7.372e-06 | 83622103 | CAMP EVERS 2103 | CAMP EVERS 210312990 | 21722.1338 | 0.0016808 | 2119 | 13.4975 | 24426.6563 | 0.057681 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2859 | 354 | 7.365e-06 | 152241101 | HALSEY 1101 | HALSEY 110176178 | 32534.9057 | 0.0026072 | 2070 | 20.2162 | 24446.8725 | 0.055074 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1878 | 18 | 7.344e-06 | 42151104 | SANTA ROSA A 1104 | SANTA ROSA A 110439786 | 1494.4367 | 0.00013219 | 2336 | 0.9286 | 24447.8011 | 0.054942 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2928 | 3 | 7.2838e-06 | 14662108 | TASSAJARA 2108 | TASSAJARA 210883368 | 128.9574 | 2.1851e-05 | 2584 | 0.08013 | 24447.8813 | 0.05492 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1172 | 228 | 7.1917e-06 | 42761102 | FORT BRAGG A 1102 | FORT BRAGG A 1102418 | 21780.1498 | 0.0016397 | 2120 | 13.5336 | 24461.4148 | 0.053281 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3862 | 36 | 7.1765e-06 | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LA42 | 4461.918 | 0.00025835 | 2256 | 2.7725 | 24464.1873 | 0.053022 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 9573 | 10 | 7.175e-06 | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110110722 | 974.5061 | 7.175e-05 | 2426 | 0.60553 | 24464.7929 | 0.05295 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4123 | 33 | 7.1547e-06 | 163240401 | TAR FLAT 0401 | TAR FLAT 0401circuit_breaker | 5449.6774 | 0.0002361 | 2264 | 3.3863 | 24468.1791 | 0.052714 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4056 | 35 | 7.1293e-06 | 42981101 | ELK 1101 | ELK 11014628 | 3351.298 | 0.00024953 | 2261 | 2.0824 | 24470.2615 | 0.052465 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7349 | 6 | 7.1186e-06 | 42761103 | FORT BRAGG A 1103 | FORT BRAGG A 1103circuit_breaker | 271.1874 | 4.2712e-05 | 2501 | 0.16851 | 24470.43 | 0.052422 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5918 | 1 | 7.1087e-06 | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102556 | 0 | 7.1087e-06 | 2715 | 0 | 24470.43 | 0.052415 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 9322 | 9 | 7.1019e-06 | 152491101 | WEIMAR 1101 | WEIMAR 11016139 | 997.9281 | 6.3917e-05 | 2446 | 0.62008 | 24471.0501 | 0.052351 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5808 | 17 | 7.0731e-06 | 163761703 | RACETRACK 1703 | RACETRACK 17032553 | 1162.4255 | 0.00012024 | 2346 | 0.7223 | 24471.7724 | 0.052231 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 9266 | 31 | 7.0525e-06 | 83192101 | GREEN VALLEY 2101 | GREEN VALLEY 21016601 | 3063.6094 | 0.00021863 | 2277 | 1.9036 | 24473.6761 | 0.052012 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 550 | 11 | 7.014e-06 | 22811102 | PACIFICA 1102 | PACIFICA 110266732 | 1010.3488 | 7.7154e-05 | 2409 | 0.6278 | 24474.3039 | 0.051935 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2696 | 16 | 6.9968e-06 | 14241101 | SUNOL 1101 | SUNOL 1101MR650 | 1692.8493 | 0.00011195 | 2357 | 1.0519 | 24475.3557 | 0.051823 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4486 | 55 | 6.9923e-06 | 42011108 | SAN RAFAEL 1108 | SAN RAFAEL 11081262 | 6212.9384 | 0.00038458 | 2218 | 3.8605 | 24479.2163 | 0.051439 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4129 | 3 | 6.9796e-06 | 152481104 | BRUNSWICK 1104 | BRUNSWICK 1104circuit_breaker | 2663.6104 | 2.0939e-05 | 2589 | 1.6551 | 24480.8714 | 0.051418 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4205 | 22 | 6.9479e-06 | 152481106 | BRUNSWICK 1106 | BRUNSWICK 110633050 | 1491.043 | 0.00015285 | 2319 | 0.92649 | 24481.7979 | 0.051265 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4891 | 96 | 6.9129e-06 | 152491101 | WEIMAR 1101 | WEIMAR 11012764 | 9841.7615 | 0.00066364 | 2181 | 6.1154 | 24487.9133 | 0.050601 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 617 | 383 | 6.8951e-06 | 182371111 | LAURELES 1111 | LAURELES 11112020 | 53149.3291 | 0.0026408 | 2067 | 33.0255 | 24520.9387 | 0.04796 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4230 | 33 | 6.7786e-06 | 42151104 | SANTA ROSA A 1104 | SANTA ROSA A 110432180 | 3607.4547 | 0.00022369 | 2273 | 2.2416 | 24523.1803 | 0.047737 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4675 | 40 | 6.7764e-06 | 83622103 | CAMP EVERS 2103 | CAMP EVERS 21035404 | 3769.8779 | 0.00027106 | 2252 | 2.3425 | 24525.5228 | 0.047466 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8715 | 7 | 6.6732e-06 | 43051101 | MONTICELLO 1101 | MONTICELLO 1101circuit_breaker | 898.3339 | 4.6712e-05 | 2490 | 0.5582 | 24526.081 | 0.047419 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4368 | 25 | 6.6555e-06 | 42091102 | MIRABEL 1102 | MIRABEL 1102206 | 2879.3705 | 0.00016639 | 2310 | 1.7892 | 24527.8701 | 0.047252 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 636 | 26 | 6.6371e-06 | 43311108 | KONOCTI 1108 | KONOCTI 11084039 | 2945.2304 | 0.00017256 | 2309 | 1.8301 | 24529.7002 | 0.04708 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3558 | 23 | 6.6098e-06 | 152161102 | AUBURN 1102 | AUBURN 1102circuit_breaker | 1981.8221 | 0.00015203 | 2320 | 1.2314 | 24530.9317 | 0.046928 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5199 | 15 | 6.5866e-06 | 152261105 | DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 1105circuit_breaker | 2499.6007 | 9.8799e-05 | 2375 | 1.5532 | 24532.4848 | 0.046829 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7115 | 154 | 6.5644e-06 | 83692104 | ROB ROY 2104 | ROB ROY 210410298 | 17304.3139 | 0.0010109 | 2157 | 10.7524 | 24543.2372 | 0.045818 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1048 | 115 | 6.5557e-06 | 152261106 | DIAMOND SPRINGS 1106 | DIAMOND SPRINGS 110699658 | 12193.3312 | 0.0007539 | 2177 | 7.5766 | 24550.8138 | 0.045064 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6385 | 54 | 6.5526e-06 | 152241102 | HALSEY 1102 | HALSEY 11026129 | 5155.4944 | 0.00035384 | 2228 | 3.2035 | 24554.0173 | 0.04471 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5467 | 40 | 6.5405e-06 | 163351701 | CURTIS 1701 | CURTIS 170190120 | 4659.8125 | 0.00026162 | 2254 | 2.8955 | 24556.9128 | 0.044449 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1875 | 247 | 6.5172e-06 | 13801104 | MORAGA 1104 | MORAGA 1104circuit_breaker | 22579.2249 | 0.0016097 | 2123 | 14.0301 | 24570.9428 | 0.042839 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 575 | 202 | 6.5083e-06 | 152491102 | WEIMAR 1102 | WEIMAR 11022038 | 21541.6585 | 0.0013147 | 2136 | 13.3854 | 24584.3282 | 0.041524 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4947 | 240 | 6.4881e-06 | 83252104 | PAUL SWEET 2104 | PAUL SWEET 21045394 | 23022.1384 | 0.0015572 | 2126 | 14.3053 | 24598.6335 | 0.039967 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2851 | 3 | 6.4742e-06 | 13810401 | WAYNE 0401 | WAYNE 040175010 | 282.8935 | 1.9423e-05 | 2598 | 0.17578 | 24598.8093 | 0.039948 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 9182 | 13 | 6.4299e-06 | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110183716 | 3791.8733 | 8.3588e-05 | 2398 | 2.3562 | 24601.1654 | 0.039864 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7131 | 8 | 6.4295e-06 | 152531101 | FLINT 1101 | FLINT 1101circuit_breaker | 831.0934 | 5.1436e-05 | 2476 | 0.51642 | 24601.6818 | 0.039813 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5217 | 183 | 6.4234e-06 | 42761104 | FORT BRAGG A 1104 | FORT BRAGG A 11041316 | 21724.3712 | 0.0011755 | 2148 | 13.4989 | 24615.1807 | 0.038637 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1796 | 105 | 6.378e-06 | 42151104 | SANTA ROSA A 1104 | SANTA ROSA A 1104210 | 10547.5245 | 0.00066969 | 2180 | 6.5539 | 24621.7347 | 0.037968 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 4061 | 1 | 6.3417e-06 | 152031102 | GRASS VALLEY 1102 | GRASS VALLEY 1102circuit_breaker | 284.9196 | 6.3417e-06 | 2724 | 0.17704 | 24621.9117 | 0.037961 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 9057 | 24 | 6.314e-06 | 152161102 | AUBURN 1102 | AUBURN 11028611 | 2944.6304 | 0.00015154 | 2322 | 1.8297 | 24623.7414 | 0.03781 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6462 | 17 | 6.3118e-06 | 152481110 | BRUNSWICK 1110 | BRUNSWICK 11103907 | 1437.9091 | 0.0001073 | 2365 | 0.89347 | 24624.6349 | 0.037702 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5753 | 34 | 6.2266e-06 | 43081101 | BIG RIVER 1101 | BIG RIVER 11012183 | 4246.8638 | 0.0002117 | 2284 | 2.6389 | 24627.2738 | 0.037491 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 9867 | 8 | 6.2246e-06 | 252192105 | BEAR VALLEY 2105 | BEAR VALLEY 2105circuit_breaker | 6175.4075 | 4.9797e-05 | 2478 | 3.8372 | 24631.111 | 0.037441 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7454 | 25 | 6.2217e-06 | 42761102 | FORT BRAGG A 1102 | FORT BRAGG A 1102circuit_breaker | 2547.229 | 0.00015554 | 2318 | 1.5828 | 24632.6938 | 0.037285 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3462 | 4 | 6.1854e-06 | 83500402 | SEACLIFF 0402 | SEACLIFF 0402circuit_breaker | 417.7951 | 2.4741e-05 | 2569 | 0.25961 | 24632.9534 | 0.037261 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6144 | 14 | 6.1743e-06 | 83692104 | ROB ROY 2104 | ROB ROY 21049973 | 921.5182 | 8.644e-05 | 2393 | 0.5726 | 24633.526 | 0.037174 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4805 | 1 | 6.1642e-06 | 42811113 | MONTE RIO 1113 | MONTE RIO 1113652 | 2244.0392 | 6.1642e-06 | 2727 | 1.3944 | 24634.9204 | 0.037168 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3797 | 35 | 6.1457e-06 | 13432207 | FAIRVIEW 2207 | FAIRVIEW 2207P304 | 8495.039 | 0.0002151 | 2280 | 5.2786 | 24640.1989 | 0.036953 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2043 | 1 | 6.1144e-06 | 192151131 | NEWBURG 1131 | NEWBURG 11313446 | 0 | 6.1144e-06 | 2728 | 0 | 24640.1989 | 0.036947 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 9752 | 8 | 6.0839e-06 | 83192101 | GREEN VALLEY 2101 | GREEN VALLEY 21011645 | 777.8514 | 4.8671e-05 | 2482 | 0.48333 | 24640.6823 | 0.036898 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6706 | 35 | 6.075e-06 | 42761102 | FORT BRAGG A 1102 | FORT BRAGG A 1102816 | 3663.972 | 0.00021262 | 2283 | 2.2767 | 24642.9589 | 0.036685 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2319 | 5 | 6.0567e-06 | 22811101 | PACIFICA 1101 | PACIFICA 11015001 | 1174.8636 | 3.0284e-05 | 2545 | 0.73003 | 24643.689 | 0.036655 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 34 | 24 | 6.0352e-06 | 163351701 | CURTIS 1701 | CURTIS 17019230 | 3602.8642 | 0.00014484 | 2327 | 2.2387 | 24645.9277 | 0.03651 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3357 | 5 | 5.9897e-06 | 42711102 | CALISTOGA 1102 | CALISTOGA 1102circuit_breaker | 862.9478 | 2.9949e-05 | 2547 | 0.53621 | 24646.4639 | 0.03648 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7060 | 62 | 5.9878e-06 | 192251102 | RIO DELL 1102 | RIO DELL 11028852 | 6733.2314 | 0.00037125 | 2221 | 4.1838 | 24650.6477 | 0.036109 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9133 | 3 | 5.9518e-06 | 42011107 | SAN RAFAEL 1107 | SAN RAFAEL 11073323 | 214.7286 | 1.7855e-05 | 2608 | 0.13343 | 24650.7812 | 0.036091 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 3591 | 10 | 5.9296e-06 | 43302107 | MONROE 2107 | MONROE 210765424 | 1114.9522 | 5.9296e-05 | 2455 | 0.6928 | 24651.474 | 0.036032 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4004 | 16 | 5.902e-06 | 43091103 | GREENBRAE 1103 | GREENBRAE 1103circuit_breaker | 1165.1033 | 9.4432e-05 | 2382 | 0.72396 | 24652.1979 | 0.035938 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6665 | 12 | 5.8876e-06 | 152481102 | BRUNSWICK 1102 | BRUNSWICK 1102940 | 1331.1883 | 7.0652e-05 | 2430 | 0.82716 | 24653.0251 | 0.035867 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7708 | 52 | 5.8852e-06 | 182371111 | LAURELES 1111 | LAURELES 111110141 | 4696.5789 | 0.00030603 | 2240 | 2.9183 | 24655.9434 | 0.035561 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2848 | 20 | 5.8701e-06 | 152461101 | PLACER 1101 | PLACER 1101circuit_breaker | 1809.155 | 0.0001174 | 2349 | 1.1242 | 24657.0676 | 0.035444 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3790 | 11 | 5.8522e-06 | 42011108 | SAN RAFAEL 1108 | SAN RAFAEL 11081457 | 1229.3805 | 6.4374e-05 | 2445 | 0.7639 | 24657.8315 | 0.035379 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6318 | 83 | 5.8014e-06 | 83481110 | STELLING 1110 | STELLING 111060090 | 10215.1138 | 0.00048152 | 2198 | 6.3474 | 24664.1788 | 0.034898 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 525 | 3 | 5.7986e-06 | 162821702 | STANISLAUS 1702 | STANISLAUS 170237278 | 10956.0145 | 1.7396e-05 | 2610 | 6.8077 | 24670.9866 | 0.03488 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6622 | 8 | 5.7824e-06 | 42091102 | MIRABEL 1102 | MIRABEL 11022043 | 914.8961 | 4.626e-05 | 2491 | 0.56849 | 24671.5551 | 0.034834 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8605 | 3 | 5.7663e-06 | 182971101 | PURISIMA 1101 | PURISIMA 110154728 | 1017.1008 | 1.7299e-05 | 2611 | 0.632 | 24672.1871 | 0.034817 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 3632 | 24 | 5.7637e-06 | 152481103 | BRUNSWICK 1103 | BRUNSWICK 11032784 | 23108.4794 | 0.00013833 | 2333 | 14.3589 | 24686.546 | 0.034678 | 14.5339 | 0.00013761 | 1 | #N/A | 0.034678 | #N/A
Central Coast | 4068 | 149 | 5.7579e-06 | 82021107 | LOS GATOS 1107 | LOS GATOS 110760092 | 15505.8611 | 0.00085793 | 2171 | 9.6349 | 24696.1809 | 0.03382 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2184 | 31 | 5.7481e-06 | 42761102 | FORT BRAGG A 1102 | FORT BRAGG A 11021226 | 2760.5742 | 0.00017819 | 2302 | 1.7153 | 24697.8962 | 0.033642 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6381 | 12 | 5.7125e-06 | 42011101 | SAN RAFAEL 1101 | SAN RAFAEL 110168970 | 1316.5192 | 6.855e-05 | 2433 | 0.81805 | 24698.7143 | 0.033574 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 832 | 3 | 5.6323e-06 | 162821702 | STANISLAUS 1702 | STANISLAUS 170237276 | 18919.7774 | 1.6897e-05 | 2615 | 11.7562 | 24710.4705 | 0.033557 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7332 | 1 | 5.6253e-06 | 192291121 | CARLOTTA 1121 | CARLOTTA 11214045 | 0 | 5.6253e-06 | 2734 | 0 | 24710.4705 | 0.033551 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1588 | 121 | 5.574e-06 | 83371106 | SARATOGA 1106 | SARATOGA 1106LC24 | 12995.8406 | 0.00067446 | 2179 | 8.0752 | 24718.5457 | 0.032877 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6159 | 29 | 5.5719e-06 | 152461102 | PLACER 1102 | PLACER 1102circuit_breaker | 2698.3238 | 0.00016159 | 2313 | 1.6767 | 24720.2224 | 0.032715 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8429 | 1 | 6.9219e-06 | 43081101 | BIG RIVER 1101 | BIG RIVER 1101954 | 11972.4011 | 6.9219e-06 | 2186 | 7.4393 | 24727.6617 | 0.032708 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
North Coast | 8429 | 108 | 5.5578e-06 | 43081101 | BIG RIVER 1101 | BIG RIVER 1101954 | 11972.4011 | 0.00060024 | 2186 | 7.4393 | 24735.101 | 0.032108 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Valley | 4968 | 12 | 5.5456e-06 | 162821702 | STANISLAUS 1702 | STANISLAUS 17021850 | 21674.5076 | 6.6547e-05 | 2440 | 13.4679 | 24748.5689 | 0.032041 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8313 | 14 | 5.4549e-06 | 82841102 | BIG BASIN 1102 | BIG BASIN 11026219 | 1442.8917 | 7.6368e-05 | 2411 | 0.89657 | 24749.4655 | 0.031965 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6172 | 4 | 5.4347e-06 | 42761104 | FORT BRAGG A 1104 | FORT BRAGG A 110465894 | 322.1994 | 2.1739e-05 | 2586 | 0.20021 | 24749.6657 | 0.031943 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1339 | 32 | 5.4174e-06 | 83622103 | CAMP EVERS 2103 | CAMP EVERS 21035402 | 3816.6305 | 0.00017336 | 2308 | 2.3715 | 24752.0372 | 0.03177 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7418 | 5 | 5.3873e-06 | 43351106 | LUCERNE 1106 | LUCERNE 11062355 | 560.2517 | 2.6937e-05 | 2559 | 0.34812 | 24752.3853 | 0.031743 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1711 | 27 | 5.3411e-06 | 42841111 | GUALALA 1111 | GUALALA 1111402866 | 2022.5208 | 0.00014421 | 2328 | 1.2567 | 24753.6421 | 0.031599 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1776 | 43 | 5.2922e-06 | 43211101 | HARTLEY 1101 | HARTLEY 1101738 | 3766.2764 | 0.00022757 | 2269 | 2.3403 | 24755.9823 | 0.031371 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 361 | 9 | 5.2885e-06 | 192021122 | ARCATA 1122 | ARCATA 112233060 | 701.4158 | 4.7597e-05 | 2485 | 0.43584 | 24756.4182 | 0.031324 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7979 | 28 | 5.2364e-06 | 42841112 | GUALALA 1112 | GUALALA 11124431 | 2212.4234 | 0.00014662 | 2324 | 1.3747 | 24757.7929 | 0.031177 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 364 | 5 | 5.236e-06 | 42771114 | UKIAH 1114 | UKIAH 1114circuit_breaker | 555.5725 | 2.618e-05 | 2563 | 0.34522 | 24758.1381 | 0.031151 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4324 | 77 | 5.2257e-06 | 182941101 | OTTER 1101 | OTTER 1101440 | 9356.989 | 0.00040238 | 2210 | 5.8142 | 24763.9523 | 0.030748 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7630 | 28 | 5.2216e-06 | 43081101 | BIG RIVER 1101 | BIG RIVER 11015065 | 3543.5774 | 0.0001462 | 2325 | 2.2019 | 24766.1542 | 0.030602 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 308 | 8 | 5.2004e-06 | 83252102 | PAUL SWEET 2102 | PAUL SWEET 2102circuit_breaker | 590.0954 | 4.1604e-05 | 2506 | 0.36667 | 24766.5208 | 0.030561 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8987 | 2 | 5.1733e-06 | 83622103 | CAMP EVERS 2103 | CAMP EVERS 2103circuit_breaker | 146.1912 | 1.0347e-05 | 2674 | 0.090839 | 24766.6117 | 0.03055 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4574 | 17 | 5.102e-06 | 14692102 | RESEARCH 2102 | RESEARCH 21029746 | 1130.0389 | 8.6735e-05 | 2392 | 0.70217 | 24767.3138 | 0.030464 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1451 | 219 | 5.0631e-06 | 14671101 | SOBRANTE 1101 | SOBRANTE 1101circuit_breaker | 22159.2029 | 0.0011088 | 2151 | 13.7691 | 24781.0829 | 0.029355 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3285 | 18 | 5.0101e-06 | 14662108 | TASSAJARA 2108 | TASSAJARA 210812712 | 1348.3115 | 9.0181e-05 | 2389 | 0.8378 | 24781.9207 | 0.029265 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6149 | 15 | 5.0044e-06 | 83692105 | ROB ROY 2105 | ROB ROY 210571630 | 1881.1605 | 7.5066e-05 | 2417 | 1.1689 | 24783.0896 | 0.029189 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7769 | 2 | 4.9886e-06 | 152481103 | BRUNSWICK 1103 | BRUNSWICK 11038918 | 2321.7397 | 9.9772e-06 | 2679 | 1.4427 | 24784.5323 | 0.02918 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1182 | 1 | 4.8973e-06 | 43292103 | PUEBLO 2103 | PUEBLO 210398394 | 20.0123 | 4.8973e-06 | 2743 | 0.012435 | 24784.5447 | 0.029175 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7309 | 1 | 4.897e-06 | 42631109 | PETALUMA C 1109 | PETALUMA C 1109738866 | 2889.9768 | 4.897e-06 | 2744 | 1.7957 | 24786.3405 | 0.02917 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 391 | 2 | 4.8821e-06 | 14161104 | ROSSMOOR 1104 | ROSSMOOR 1104circuit_breaker | 0 | 9.7642e-06 | 2684 | 0 | 24786.3405 | 0.02916 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 429 | 96 | 4.8689e-06 | 83371107 | SARATOGA 1107 | SARATOGA 1107LC26 | 9086.0614 | 0.00046741 | 2201 | 5.6458 | 24791.9863 | 0.028693 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 524 | 15 | 4.8617e-06 | 43361104 | HIGHLANDS 1104 | HIGHLANDS 110439458 | 1626.6223 | 7.2926e-05 | 2425 | 1.0107 | 24792.997 | 0.02862 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2769 | 106 | 4.7894e-06 | 83432101 | HICKS 2101 | HICKS 2101XR250 | 12241.6477 | 0.00050767 | 2194 | 7.6066 | 24800.6036 | 0.028112 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2728 | 7 | 4.7855e-06 | 192251102 | RIO DELL 1102 | RIO DELL 1102circuit_breaker | 655.8803 | 3.3498e-05 | 2532 | 0.40754 | 24801.0112 | 0.028078 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5345 | 69 | 4.7003e-06 | 42841111 | GUALALA 1111 | GUALALA 1111circuit_breaker | 5963.2451 | 0.00032432 | 2235 | 3.7054 | 24804.7166 | 0.027754 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 625 | 23 | 4.6738e-06 | 43071101 | DUNBAR 1101 | DUNBAR 1101160 | 3768.8878 | 0.0001075 | 2363 | 2.3419 | 24807.0584 | 0.027647 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 751 | 65 | 4.6724e-06 | 82021108 | LOS GATOS 1108 | LOS GATOS 1108LB86 | 7195.675 | 0.00030371 | 2242 | 4.4712 | 24811.5296 | 0.027343 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4900 | 21 | 4.6178e-06 | 12501112 | EL CERRITO G 1112 | EL CERRITO G 1112BR178 | 2290.0818 | 9.6974e-05 | 2378 | 1.423 | 24812.9526 | 0.027246 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5281 | 42 | 4.6142e-06 | 163201102 | WEST POINT 1102 | WEST POINT 11025357 | 5289.0317 | 0.0001938 | 2297 | 3.2865 | 24816.2391 | 0.027052 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8436 | 1 | 4.6135e-06 | 14161101 | ROSSMOOR 1101 | ROSSMOOR 110181770 | 0 | 4.6135e-06 | 2748 | 0 | 24816.2391 | 0.027048 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3149 | 41 | 4.5594e-06 | 83692105 | ROB ROY 2105 | ROB ROY 210512474 | 4762.2826 | 0.00018694 | 2300 | 2.9591 | 24819.1982 | 0.026861 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5241 | 1 | 4.557e-06 | 42631108 | PETALUMA C 1108 | PETALUMA C 1108600 | 8142.768 | 4.557e-06 | 2750 | 5.0597 | 24824.2579 | 0.026856 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9360 | 4 | 4.5029e-06 | 43501103 |  | 5060 | 477.3134 | 1.8011e-05 | 2607 | 0.29659 | 24824.5545 | 0.026838 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 9013 | 9 | 4.4957e-06 | 153741101 | DOBBINS 1101 | DOBBINS 1101circuit_breaker | 1079.0936 | 4.0462e-05 | 2510 | 0.67052 | 24825.225 | 0.026798 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3917 | 67 | 4.4939e-06 | 182371111 | LAURELES 1111 | LAURELES 1111circuit_breaker | 11332.9679 | 0.00030109 | 2243 | 7.042 | 24832.267 | 0.026496 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 395 | 82 | 4.4762e-06 | 43191102 | REDBUD 1102 | REDBUD 1102922 | 12117.314 | 0.00036705 | 2223 | 7.5293 | 24839.7963 | 0.026129 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1360 | 15 | 4.4623e-06 | 22811103 | PACIFICA 1103 | PACIFICA 110311153 | 1394.6966 | 6.6935e-05 | 2438 | 0.86662 | 24840.6629 | 0.026062 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9841 | 6 | 4.4599e-06 | 103301101 | BOGARD 1101 | BOGARD 1101circuit_breaker | 830.5012 | 2.6759e-05 | 2561 | 0.51605 | 24841.179 | 0.026036 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 8330 | 3 | 4.4034e-06 | 43302103 | MONROE 2103 | MONROE 210392868 | 437.4753 | 1.321e-05 | 2642 | 0.27183 | 24841.4508 | 0.026023 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6675 | 7 | 4.3991e-06 | 24101101 | HALF MOON BAY 1101 | HALF MOON BAY 110148868 | 1128.5857 | 3.0794e-05 | 2543 | 0.70127 | 24842.1521 | 0.025992 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 791 | 22 | 4.3962e-06 | 14692102 | RESEARCH 2102 | RESEARCH 210263274 | 2064.5249 | 9.6717e-05 | 2379 | 1.2828 | 24843.4349 | 0.025895 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6333 | 3 | 4.3938e-06 | 42851121 | FORT ROSS 1121 | FORT ROSS 1121134 | 12414.5774 | 1.3181e-05 | 2643 | 7.7141 | 24851.149 | 0.025882 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7824 | 1 | 4.3596e-06 | 14161107 | ROSSMOOR 1107 | ROSSMOOR 11077311 | 0 | 4.3596e-06 | 2753 | 0 | 24851.149 | 0.025877 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9727 | 3 | 4.3513e-06 | 42811113 | MONTE RIO 1113 | MONTE RIO 11135024 | 545.8664 | 1.3054e-05 | 2646 | 0.33919 | 24851.4882 | 0.025864 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7788 | 1 | 4.4328e-06 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 11038898 | 1026.3244 | 4.4328e-06 | 2513 | 0.63773 | 24852.1259 | 0.02586 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 7788 | 8 | 4.3391e-06 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 11038898 | 1026.3244 | 3.4713e-05 | 2513 | 0.63773 | 24852.7636 | 0.025825 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Coast | 2056 | 17 | 4.3328e-06 | 83692105 | ROB ROY 2105 | ROB ROY 210512586 | 2805.9717 | 7.3658e-05 | 2423 | 1.7435 | 24854.5072 | 0.025752 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 260 | 46 | 4.3146e-06 | 83371104 | SARATOGA 1104 | SARATOGA 110413314 | 4930.3505 | 0.00019847 | 2293 | 3.0636 | 24857.5708 | 0.025553 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8777 | 2 | 4.2937e-06 | 24240402 | WATERSHED 0402 | WATERSHED 0402circuit_breaker | 0 | 8.5873e-06 | 2698 | 0 | 24857.5708 | 0.025545 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4616 | 9 | 4.2754e-06 | 42631109 | PETALUMA C 1109 | PETALUMA C 110948000 | 15185.5394 | 3.8478e-05 | 2515 | 9.4359 | 24867.0066 | 0.025506 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3894 | 37 | 4.2667e-06 | 83692105 | ROB ROY 2105 | ROB ROY 210512584 | 5377.6554 | 0.00015787 | 2316 | 3.3415 | 24870.3481 | 0.025348 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6777 | 4 | 4.2654e-06 | 182541102 | ATASCADERO 1102 | ATASCADERO 1102A26 | 1034.6974 | 1.7062e-05 | 2612 | 0.64293 | 24870.9911 | 0.025331 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5237 | 51 | 4.259e-06 | 42861101 | ANNAPOLIS 1101 | ANNAPOLIS 1101554 | 43657.3063 | 0.00021721 | 2279 | 27.1274 | 24898.1185 | 0.025114 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4682 | 6 | 4.2303e-06 | 83692105 | ROB ROY 2105 | ROB ROY 2105circuit_breaker | 778.4452 | 2.5382e-05 | 2564 | 0.4837 | 24898.6022 | 0.025089 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4825 | 3 | 4.2125e-06 | 83252102 | PAUL SWEET 2102 | PAUL SWEET 210212850 | 1087.1798 | 1.2637e-05 | 2651 | 0.67554 | 24899.2777 | 0.025076 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5659 | 149 | 4.2078e-06 | 12101102 | OAKLAND K 1102 | OAKLAND K 1102CR014 | 16905.4788 | 0.00062696 | 2184 | 10.5046 | 24909.7823 | 0.024449 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6973 | 1 | 4.1877e-06 | 153612106 | CLARKSVILLE 2106 | CLARKSVILLE 210619642 | 618.1955 | 4.1877e-06 | 2756 | 0.38413 | 24910.1664 | 0.024445 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2181 | 47 | 4.1765e-06 | 83252109 | PAUL SWEET 2109 | PAUL SWEET 2109circuit_breaker | 4486.5579 | 0.0001963 | 2294 | 2.7878 | 24912.9542 | 0.024248 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 839 | 6 | 4.1761e-06 | 43321102 | RINCON 1102 | RINCON 1102644 | 652.5483 | 2.5057e-05 | 2566 | 0.40547 | 24913.3597 | 0.024223 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5223 | 3 | 4.1715e-06 | 22811101 | PACIFICA 1101 | PACIFICA 1101circuit_breaker | 222.8126 | 1.2515e-05 | 2652 | 0.13845 | 24913.4981 | 0.024211 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 8784 | 6 | 4.1687e-06 | 152701108 | BELL 1108 | BELL 110880680 | 685.5234 | 2.5012e-05 | 2567 | 0.42596 | 24913.9241 | 0.024186 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7508 | 93 | 4.1653e-06 | 82021106 | LOS GATOS 1106 | LOS GATOS 1106circuit_breaker | 10732.6188 | 0.00038737 | 2217 | 6.6689 | 24920.593 | 0.023799 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 946 | 35 | 4.1621e-06 | 42011109 | SAN RAFAEL 1109 | SAN RAFAEL 110991742 | 6806.4298 | 0.00014567 | 2326 | 4.2293 | 24924.8224 | 0.023653 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4391 | 2 | 4.1381e-06 | 182052101 | SOLEDAD 2101 | SOLEDAD 21017056 | 6257.9858 | 8.2761e-06 | 2703 | 3.8885 | 24928.7109 | 0.023645 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2882 | 89 | 4.1108e-06 | 13532107 | LAKEWOOD 2107 | LAKEWOOD 210769586 | 8401.1793 | 0.00036586 | 2224 | 5.2202 | 24933.9311 | 0.023279 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3836 | 37 | 4.1048e-06 | 13600401 | LAS AROMAS 0401 | LAS AROMAS 04013342 | 3654.0283 | 0.00015188 | 2321 | 2.2705 | 24936.2016 | 0.023127 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 193 | 5 | 4.0852e-06 | 192251102 | RIO DELL 1102 | RIO DELL 11028768 | 449.1583 | 2.0426e-05 | 2591 | 0.27909 | 24936.4807 | 0.023106 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2445 | 1 | 4.0796e-06 | 82161102 | LOYOLA 1102 | LOYOLA 110260082 | 51.5332 | 4.0796e-06 | 2757 | 0.032021 | 24936.5128 | 0.023102 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 726 | 48 | 4.0751e-06 | 42011104 | SAN RAFAEL 1104 | SAN RAFAEL 1104circuit_breaker | 5364.6138 | 0.0001956 | 2295 | 3.3334 | 24939.8462 | 0.022907 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8271 | 4 | 4.0553e-06 | 43051101 | MONTICELLO 1101 | MONTICELLO 110152910 | 3504.9565 | 1.6221e-05 | 2619 | 2.1779 | 24942.0241 | 0.02289 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1259 | 120 | 4.0527e-06 | 83371106 | SARATOGA 1106 | SARATOGA 1106LC22 | 11864.1721 | 0.00048633 | 2197 | 7.3721 | 24949.3961 | 0.022404 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3969 | 44 | 4.0405e-06 | 13600401 | LAS AROMAS 0401 | LAS AROMAS 0401LA401R | 4766.0601 | 0.00017778 | 2303 | 2.9615 | 24952.3576 | 0.022226 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2281 | 30 | 4.0384e-06 | 42031124 | ALTO 1124 | ALTO 1124circuit_breaker | 3322.8701 | 0.00012115 | 2345 | 2.0647 | 24954.4223 | 0.022105 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5023 | 3 | 4.0364e-06 | 152261106 | DIAMOND SPRINGS 1106 | DIAMOND SPRINGS 1106circuit_breaker | 305.3669 | 1.2109e-05 | 2656 | 0.18975 | 24954.6121 | 0.022093 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 180 | 3 | 4.0039e-06 | 42141101 | CLEAR LAKE 1101 | CLEAR LAKE 110192870 | 859.6824 | 1.2012e-05 | 2657 | 0.53418 | 24955.1463 | 0.022081 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1418 | 52 | 4.0009e-06 | 12101104 | OAKLAND K 1104 | OAKLAND K 1104CR204 | 6584.4717 | 0.00020805 | 2286 | 4.0914 | 24959.2377 | 0.021873 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5970 | 1 | 3.9985e-06 | 43371102 | LAKEVILLE 1102 | LAKEVILLE 1102530 | 291.9883 | 3.9985e-06 | 2761 | 0.18143 | 24959.4191 | 0.021869 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5792 | 8 | 3.9786e-06 | 83242105 | MORGAN HILL 2105 | MORGAN HILL 2105circuit_breaker | 791.0708 | 3.1829e-05 | 2539 | 0.49155 | 24959.9106 | 0.021837 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 717 | 51 | 3.9753e-06 | 13151105 | RADUM 1105 | RADUM 1105MR282 | 4954.2228 | 0.00020274 | 2291 | 3.0784 | 24962.9891 | 0.021635 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9195 | 18 | 3.9373e-06 | 12541106 | OAKLAND X 1106 | OAKLAND X 1106CR266 | 1901.6084 | 7.0871e-05 | 2429 | 1.1816 | 24964.1707 | 0.021564 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7432 | 12 | 3.9331e-06 | 42771114 | UKIAH 1114 | UKIAH 111472990 | 1032.2982 | 4.7197e-05 | 2489 | 0.64144 | 24964.8121 | 0.021516 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5148 | 17 | 3.9296e-06 | 42011105 | SAN RAFAEL 1105 | SAN RAFAEL 1105534 | 1383.1216 | 6.6803e-05 | 2439 | 0.85943 | 24965.6715 | 0.02145 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4363 | 10 | 3.9206e-06 | 163451702 | FROGTOWN 1702 | FROGTOWN 170274648 | 1211.7571 | 3.9206e-05 | 2512 | 0.75295 | 24966.4245 | 0.02141 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1446 | 19 | 3.9045e-06 | 42261101 | BOLINAS 1101 | BOLINAS 1101528 | 2645.4949 | 7.4186e-05 | 2420 | 1.6438 | 24968.0683 | 0.021336 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7858 | 4 | 3.9018e-06 | 42011104 | SAN RAFAEL 1104 | SAN RAFAEL 11042235 | 240.5368 | 1.5607e-05 | 2623 | 0.14946 | 24968.2178 | 0.021321 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5191 | 20 | 3.9009e-06 | 12101104 | OAKLAND K 1104 | OAKLAND K 1104CR206 | 2883.3047 | 7.8019e-05 | 2407 | 1.7916 | 24970.0094 | 0.021243 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5484 | 1 | 3.8878e-06 | 162821702 | STANISLAUS 1702 | STANISLAUS 170275348 | 8681.8427 | 3.8878e-06 | 2763 | 5.3946 | 24975.404 | 0.021239 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4545 | 103 | 3.8467e-06 | 83692104 | ROB ROY 2104 | ROB ROY 210412596 | 11237.3875 | 0.00039621 | 2214 | 6.9826 | 24982.3866 | 0.020843 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6304 | 57 | 3.8203e-06 | 163661702 | MIWUK 1702 | MIWUK 170247143 | 7868.7696 | 0.00021775 | 2278 | 4.8894 | 24987.276 | 0.020625 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2249 | 16 | 3.8018e-06 | 12101104 | OAKLAND K 1104 | OAKLAND K 1104CR326 | 2098.9601 | 6.0829e-05 | 2450 | 1.3042 | 24988.5803 | 0.020564 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 814 | 68 | 3.786e-06 | 12541104 | OAKLAND X 1104 | OAKLAND X 1104CR022 | 9630.8273 | 0.00025745 | 2257 | 5.9843 | 24994.5646 | 0.020306 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1279 | 219 | 3.7253e-06 | 163351702 | CURTIS 1702 | CURTIS 17028000 | 23052.1801 | 0.00081584 | 2172 | 14.324 | 25008.8885 | 0.019491 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4106 | 37 | 3.7238e-06 | 12541104 | OAKLAND X 1104 | OAKLAND X 1104CR214 | 4637.1496 | 0.00013778 | 2335 | 2.8814 | 25011.7699 | 0.019353 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9419 | 30 | 3.6816e-06 | 42841111 | GUALALA 1111 | GUALALA 1111498 | 3498.0819 | 0.00011045 | 2358 | 2.1736 | 25013.9435 | 0.019242 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 10015 | 1 | 3.6783e-06 | 163351705 | CURTIS 1705 | CURTIS 170511790 | 22.8988 | 3.6783e-06 | 2765 | 0.014229 | 25013.9578 | 0.019239 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4535 | 15 | 3.6713e-06 | 43311108 | KONOCTI 1108 | KONOCTI 11084041 | 1537.6241 | 5.507e-05 | 2463 | 0.95544 | 25014.9132 | 0.019184 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 233 | 5 | 3.6469e-06 | 82021102 | LOS GATOS 1102 | LOS GATOS 1102circuit_breaker | 1766.8106 | 1.8234e-05 | 2606 | 1.0978 | 25016.011 | 0.019165 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 69 | 13 | 3.6433e-06 | 22811102 | PACIFICA 1102 | PACIFICA 11026783 | 2227.3024 | 4.7363e-05 | 2487 | 1.384 | 25017.395 | 0.019118 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 548 | 90 | 3.6289e-06 | 43091102 | GREENBRAE 1102 | GREENBRAE 11021254 | 9494.3832 | 0.0003266 | 2234 | 5.8995 | 25023.2946 | 0.018791 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7001 | 2 | 3.6112e-06 | 12101101 | OAKLAND K 1101 | OAKLAND K 1101CR346 | 301.378 | 7.2223e-06 | 2711 | 0.18727 | 25023.4818 | 0.018784 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 52 | 58 | 3.6106e-06 | 163351702 | CURTIS 1702 | CURTIS 170234426 | 7090.4475 | 0.00020941 | 2285 | 4.4058 | 25027.8876 | 0.018575 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2971 | 53 | 3.5981e-06 | 12541104 | OAKLAND X 1104 | OAKLAND X 1104CR288 | 4410.6695 | 0.0001907 | 2298 | 2.7407 | 25030.6283 | 0.018384 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7055 | 30 | 3.5825e-06 | 192431108 | HARRIS 1108 | HARRIS 11082062 | 2687.4494 | 0.00010748 | 2364 | 1.6699 | 25032.2982 | 0.018277 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7486 | 2 | 3.5715e-06 | 82161102 | LOYOLA 1102 | LOYOLA 1102LL12 | 176.3756 | 7.1431e-06 | 2714 | 0.10959 | 25032.4078 | 0.01827 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3681 | 24 | 3.553e-06 | 83252104 | PAUL SWEET 2104 | PAUL SWEET 210411074 | 4575.9781 | 8.5271e-05 | 2394 | 2.8434 | 25035.2512 | 0.018184 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2863 | 1 | 3.5303e-06 | 192331104 | EUREKA E 1104 | EUREKA E 110435934 | 163.1504 | 3.5303e-06 | 2767 | 0.10138 | 25035.3525 | 0.018181 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3063 | 1 | 3.5154e-06 | 42011106 | SAN RAFAEL 1106 | SAN RAFAEL 110648752 | 44.4852 | 3.5154e-06 | 2768 | 0.027642 | 25035.3802 | 0.018177 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 671 | 10 | 3.5112e-06 | 14161106 | ROSSMOOR 1106 | ROSSMOOR 110676468 | 812.7944 | 3.5112e-05 | 2524 | 0.50505 | 25035.8852 | 0.018142 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1229 | 131 | 3.4848e-06 | 163351703 | CURTIS 1703 | CURTIS 17039240 | 17593.4022 | 0.00045651 | 2204 | 10.932 | 25046.8173 | 0.017686 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 6293 | 100 | 3.4755e-06 | 163351705 | CURTIS 1705 | CURTIS 17058170 | 12248.0291 | 0.00034755 | 2231 | 7.6106 | 25054.4278 | 0.017338 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4672 | 46 | 3.4629e-06 | 14161101 | ROSSMOOR 1101 | ROSSMOOR 11018132 | 4210.4765 | 0.00015929 | 2315 | 2.6163 | 25057.0441 | 0.017179 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3113 | 1 | 3.4538e-06 | 103541105 | RED BLUFF 1105 | RED BLUFF 1105161818 | 275.1903 | 3.4538e-06 | 2769 | 0.171 | 25057.2151 | 0.017175 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6909 | 75 | 3.4467e-06 | 12350401 | ORINDA 0401 | ORINDA 04013442 | 7643.0559 | 0.0002585 | 2255 | 4.7492 | 25061.9643 | 0.016917 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5153 | 29 | 3.4383e-06 | 14161106 | ROSSMOOR 1106 | ROSSMOOR 1106L522R | 3036.9141 | 9.9712e-05 | 2373 | 1.8871 | 25063.8513 | 0.016817 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 227 | 16 | 3.4112e-06 | 83252106 | PAUL SWEET 2106 | PAUL SWEET 210612828 | 1804.684 | 5.4579e-05 | 2466 | 1.1214 | 25064.9727 | 0.016762 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1354 | 5 | 3.4057e-06 | 192431108 | HARRIS 1108 | HARRIS 11084674 | 465.5681 | 1.7028e-05 | 2613 | 0.28929 | 25065.262 | 0.016745 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2779 | 38 | 3.4045e-06 | 42271104 | COTATI 1104 | COTATI 1104circuit_breaker | 5446.6395 | 0.00012937 | 2339 | 3.3844 | 25068.6464 | 0.016616 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3318 | 2 | 3.3979e-06 | 83371107 | SARATOGA 1107 | SARATOGA 1107circuit_breaker | 273.8424 | 6.7959e-06 | 2719 | 0.17016 | 25068.8165 | 0.016609 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5179 | 8 | 3.3892e-06 | 14671101 | SOBRANTE 1101 | SOBRANTE 110142914 | 755.7626 | 2.7113e-05 | 2558 | 0.46961 | 25069.2861 | 0.016582 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8718 | 2 | 3.3891e-06 | 254432102 | COARSEGOLD 2102 | COARSEGOLD 2102383092 | 613.1926 | 6.7782e-06 | 2720 | 0.38102 | 25069.6672 | 0.016575 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4698 | 6 | 3.3781e-06 | 14341103 | VALLEY VIEW 1103 | VALLEY VIEW 1103P160 | 868.2348 | 2.0269e-05 | 2593 | 0.5395 | 25070.2067 | 0.016555 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 959 | 34 | 3.3298e-06 | 13090402 | BRYANT 0402 | BRYANT 0402circuit_breaker | 3304.7718 | 0.00011321 | 2355 | 2.0535 | 25072.2601 | 0.016442 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7330 | 7 | 3.3292e-06 | 14161102 | ROSSMOOR 1102 | ROSSMOOR 1102circuit_breaker | 400.2166 | 2.3304e-05 | 2576 | 0.24868 | 25072.5088 | 0.016419 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 9058 | 3 | 3.3136e-06 | 43361104 | HIGHLANDS 1104 | HIGHLANDS 110484640 | 569.7278 | 9.9409e-06 | 2680 | 0.35401 | 25072.8628 | 0.016409 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 346 | 135 | 3.2962e-06 | 163351702 | CURTIS 1702 | CURTIS 170210940 | 13795.9366 | 0.00044499 | 2206 | 8.5724 | 25081.4352 | 0.015964 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7676 | 86 | 3.2934e-06 | 83371107 | SARATOGA 1107 | SARATOGA 11075696 | 8008.7281 | 0.00028323 | 2248 | 4.9764 | 25086.4116 | 0.01568 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2119 | 144 | 3.2578e-06 | 14671102 | SOBRANTE 1102 | SOBRANTE 1102L510R | 14977.7338 | 0.00046912 | 2200 | 9.3067 | 25095.7184 | 0.015211 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2117 | 71 | 3.2501e-06 | 43361104 | HIGHLANDS 1104 | HIGHLANDS 1104circuit_breaker | 7426.3873 | 0.00023075 | 2267 | 4.6145 | 25100.3329 | 0.014981 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1297 | 54 | 3.2486e-06 | 163781701 | PEORIA 1701 | PEORIA 17013186 | 15920.2864 | 0.00017543 | 2305 | 9.8924 | 25110.2253 | 0.014805 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 421 | 120 | 3.2484e-06 | 14671102 | SOBRANTE 1102 | SOBRANTE 1102L520R | 11876.5417 | 0.00038981 | 2216 | 7.3797 | 25117.605 | 0.014415 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2012 | 3 | 3.2294e-06 | 83771102 | VASONA 1102 | VASONA 1102circuit_breaker | 282.6401 | 9.6881e-06 | 2687 | 0.17562 | 25117.7807 | 0.014406 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6033 | 44 | 3.2246e-06 | 182291102 | HATTON 1102 | HATTON 11022010 | 6466.4829 | 0.00014188 | 2331 | 4.0181 | 25121.7988 | 0.014264 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4496 | 21 | 3.2055e-06 | 42271104 | COTATI 1104 | COTATI 1104426 | 3056.6341 | 6.7316e-05 | 2437 | 1.8993 | 25123.6981 | 0.014196 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1202 | 13 | 3.2021e-06 | 13801103 | MORAGA 1103 | MORAGA 110381146 | 1121.0612 | 4.1627e-05 | 2505 | 0.69659 | 25124.3947 | 0.014155 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8711 | 13 | 3.1945e-06 | 13532224 | LAKEWOOD 2224 | LAKEWOOD 2224568670 | 1334.4522 | 4.1529e-05 | 2507 | 0.82919 | 25125.2238 | 0.014113 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1136 | 4 | 3.1938e-06 | 13801105 | MORAGA 1105 | MORAGA 11058354 | 320.2661 | 1.2775e-05 | 2649 | 0.199 | 25125.4228 | 0.014101 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2507 | 6 | 3.1846e-06 | 13432207 | FAIRVIEW 2207 | FAIRVIEW 2207P148 | 1241.4753 | 1.9108e-05 | 2600 | 0.77142 | 25126.1943 | 0.014081 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 522 | 3 | 3.1822e-06 | 42011109 | SAN RAFAEL 1109 | SAN RAFAEL 1109418 | 8200.6281 | 9.5465e-06 | 2691 | 5.0956 | 25131.2899 | 0.014072 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7461 | 6 | 3.1688e-06 | 182381101 | DOLAN ROAD 1101 | DOLAN ROAD 110122158 | 274.4783 | 1.9013e-05 | 2602 | 0.17055 | 25131.4604 | 0.014053 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1469 | 35 | 3.1109e-06 | 42011101 | SAN RAFAEL 1101 | SAN RAFAEL 1101circuit_breaker | 3967.8905 | 0.00010888 | 2361 | 2.4655 | 25133.926 | 0.013944 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1253 | 191 | 3.0703e-06 | 82021107 | LOS GATOS 1107 | LOS GATOS 1107circuit_breaker | 24420.9564 | 0.00058642 | 2190 | 15.1745 | 25149.1005 | 0.013358 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7941 | 1 | 3.0668e-06 | 42481105 |  | 1943 | 1959.963 | 3.0668e-06 | 2773 | 1.2179 | 25150.3183 | 0.013354 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4226 | 8 | 3.0659e-06 | 42211104 | NOVATO 1104 | NOVATO 11041282 | 722.7771 | 2.4527e-05 | 2570 | 0.44911 | 25150.7674 | 0.01333 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7585 | 45 | 3.0645e-06 | 83371115 | SARATOGA 1115 | SARATOGA 1115LC20 | 4697.8741 | 0.0001379 | 2334 | 2.9191 | 25153.6866 | 0.013192 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7080 | 11 | 3.0249e-06 | 14091108 | CASTRO VALLEY 1108 | CASTRO VALLEY 1108MR273 | 1166.5861 | 3.3274e-05 | 2534 | 0.72488 | 25154.4114 | 0.013159 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3454 | 22 | 3.0188e-06 | 12101104 | OAKLAND K 1104 | OAKLAND K 1104432850 | 1972.5088 | 6.6413e-05 | 2441 | 1.2257 | 25155.6371 | 0.013092 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1701 | 25 | 3.0134e-06 | 82021101 | LOS GATOS 1101 | LOS GATOS 1101circuit_breaker | 2776.4398 | 7.5336e-05 | 2416 | 1.7252 | 25157.3623 | 0.013017 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4981 | 2 | 2.9943e-06 | 182951101 | FOOTHILL 1101 | FOOTHILL 1101circuit_breaker | 18495.1348 | 5.9886e-06 | 2729 | 11.4923 | 25168.8546 | 0.013011 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2962 | 80 | 2.9897e-06 | 42011101 | SAN RAFAEL 1101 | SAN RAFAEL 1101494 | 8677.8794 | 0.00023918 | 2263 | 5.3922 | 25174.2468 | 0.012772 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7223 | 44 | 2.9871e-06 | 42481104 | IGNACIO 1104 | IGNACIO 1104450582 | 4879.3488 | 0.00013143 | 2337 | 3.0319 | 25177.2787 | 0.01264 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4303 | 11 | 2.9622e-06 | 42011105 | SAN RAFAEL 1105 | SAN RAFAEL 1105344 | 796.0448 | 3.2584e-05 | 2537 | 0.49464 | 25177.7733 | 0.012608 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5127 | 3 | 2.9348e-06 | 42011105 | SAN RAFAEL 1105 | SAN RAFAEL 1105circuit_breaker | 373.6826 | 8.8044e-06 | 2696 | 0.2322 | 25178.0055 | 0.012599 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1380 | 18 | 2.8995e-06 | 42011106 | SAN RAFAEL 1106 | SAN RAFAEL 11061230 | 1200.481 | 5.219e-05 | 2474 | 0.74594 | 25178.7515 | 0.012547 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5252 | 121 | 2.8847e-06 | 182291101 | HATTON 1101 | HATTON 110137088 | 10725.9565 | 0.00034905 | 2230 | 6.6648 | 25185.4163 | 0.012198 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5428 | 24 | 2.8314e-06 | 182371111 | LAURELES 1111 | LAURELES 11116617 | 2923.677 | 6.7954e-05 | 2435 | 1.8167 | 25187.233 | 0.01213 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6433 | 26 | 2.8314e-06 | 182371112 | LAURELES 1112 | LAURELES 1112438 | 7535.0705 | 7.3616e-05 | 2424 | 4.6821 | 25191.915 | 0.012056 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 761 | 6 | 2.828e-06 | 22811104 | PACIFICA 1104 | PACIFICA 1104circuit_breaker | 1298.4065 | 1.6968e-05 | 2614 | 0.80679 | 25192.7218 | 0.012039 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2563 | 4 | 2.8233e-06 | 182961110 | PRUNEDALE 1110 | PRUNEDALE 11103716 | 500.9046 | 1.1293e-05 | 2663 | 0.31125 | 25193.0331 | 0.012028 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5620 | 4 | 2.8173e-06 | 182721102 | SANTA YNEZ 1102 | SANTA YNEZ 1102320270 | 464.6996 | 1.1269e-05 | 2664 | 0.28875 | 25193.3218 | 0.012017 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1865 | 19 | 2.8049e-06 | 182742104 | SAN BENITO 2104 | SAN BENITO 2104circuit_breaker | 7728.5813 | 5.3294e-05 | 2471 | 4.8023 | 25198.1242 | 0.011963 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1765 | 27 | 2.8021e-06 | 12061103 | BERKELEY F 1103 | BERKELEY F 1103BR110 | 3020.133 | 7.5657e-05 | 2414 | 1.8766 | 25200.0008 | 0.011888 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8137 | 33 | 2.7998e-06 | 83481110 | STELLING 1110 | STELLING 11102243 | 3010.4448 | 9.2395e-05 | 2386 | 1.8706 | 25201.8714 | 0.011795 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4136 | 12 | 2.7958e-06 | 42011106 | SAN RAFAEL 1106 | SAN RAFAEL 1106837 | 1084.0764 | 3.355e-05 | 2531 | 0.67361 | 25202.545 | 0.011762 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9946 | 14 | 2.794e-06 | 13801101 | MORAGA 1101 | MORAGA 110183424 | 2587.2467 | 3.9116e-05 | 2514 | 1.6076 | 25204.1526 | 0.011723 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2627 | 121 | 2.7925e-06 | 82021101 | LOS GATOS 1101 | LOS GATOS 1101LB40 | 13423.6309 | 0.00033789 | 2232 | 8.3411 | 25212.4937 | 0.011385 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 9544 | 3 | 2.7892e-06 | 163351703 | CURTIS 1703 | CURTIS 170349746 | 601.9007 | 8.3675e-06 | 2700 | 0.374 | 25212.8677 | 0.011376 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 6012 | 83 | 2.7825e-06 | 43361104 | HIGHLANDS 1104 | HIGHLANDS 110448262 | 9900.0196 | 0.00023095 | 2266 | 6.1516 | 25219.0193 | 0.011145 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2118 | 2 | 2.7645e-06 | 13532227 | LAKEWOOD 2227 | LAKEWOOD 2227W503R | 121.8736 | 5.529e-06 | 2736 | 0.075729 | 25219.095 | 0.01114 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8050 | 21 | 2.7633e-06 | 183011102 | MORRO BAY 1102 | MORRO BAY 1102circuit_breaker | 5907.9517 | 5.8029e-05 | 2458 | 3.671 | 25222.766 | 0.011082 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4001 | 82 | 2.762e-06 | 182371112 | LAURELES 1112 | LAURELES 11122142 | 12390.3415 | 0.00022649 | 2270 | 7.699 | 25230.465 | 0.010855 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2588 | 45 | 2.7554e-06 | 102551101 | EAST QUINCY 1101 | EAST QUINCY 1101circuit_breaker | 4164.7046 | 0.00012399 | 2343 | 2.5878 | 25233.0529 | 0.010731 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8223 | 28 | 2.7356e-06 | 82021101 | LOS GATOS 1101 | LOS GATOS 110160052 | 3109.1853 | 7.6598e-05 | 2410 | 1.932 | 25234.9848 | 0.010655 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 195 | 8 | 2.7298e-06 | 13700401 | ARLINGTON 0401 | ARLINGTON 0401circuit_breaker | 973.3919 | 2.1838e-05 | 2585 | 0.60484 | 25235.5897 | 0.010633 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2600 | 84 | 2.7293e-06 | 183071101 | PERRY 1101 | PERRY 1101V72 | 9688.7012 | 0.00022926 | 2268 | 6.0203 | 25241.6099 | 0.010404 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 629 | 40 | 2.7035e-06 | 42031125 | ALTO 1125 | ALTO 1125935 | 5180.4035 | 0.00010814 | 2362 | 3.219 | 25244.8289 | 0.010296 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1961 | 9 | 2.6941e-06 | 13801103 | MORAGA 1103 | MORAGA 1103E510R | 662.3347 | 2.4247e-05 | 2571 | 0.41156 | 25245.2404 | 0.010271 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7016 | 9 | 2.6901e-06 | 83371107 | SARATOGA 1107 | SARATOGA 11076867 | 985.9493 | 2.4211e-05 | 2572 | 0.61264 | 25245.8531 | 0.010247 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4743 | 1 | 2.667e-06 | 42481105 |  | 84764 | 2403.7519 | 2.667e-06 | 2787 | 1.4936 | 25247.3467 | 0.010244 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2072 | 1 | 2.6646e-06 | 14091106 | CASTRO VALLEY 1106 | CASTRO VALLEY 1106MR205 | 143.1328 | 2.6646e-06 | 2788 | 0.088939 | 25247.4356 | 0.010242 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2253 | 139 | 2.6568e-06 | 182371111 | LAURELES 1111 | LAURELES 11112028 | 14048.0686 | 0.00036929 | 2222 | 8.7291 | 25256.1647 | 0.0098725 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2216 | 20 | 2.6433e-06 | 13532107 | LAKEWOOD 2107 | LAKEWOOD 210738404 | 3768.6783 | 5.2865e-05 | 2473 | 2.3417 | 25258.5064 | 0.0098197 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 4592 | 28 | 2.6352e-06 | 43211101 | HARTLEY 1101 | HARTLEY 110194178 | 3325.1898 | 7.3787e-05 | 2422 | 2.0662 | 25260.5726 | 0.0097459 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4949 | 1 | 3.0524e-06 | 12840401 | RIDGE 0401 | RIDGE 0401circuit_breaker | 4156.4129 | 3.0524e-06 | 2377 | 2.5827 | 25263.1553 | 0.0097428 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 4949 | 36 | 2.6193e-06 | 12840401 | RIDGE 0401 | RIDGE 0401circuit_breaker | 4156.4129 | 9.4296e-05 | 2377 | 2.5827 | 25265.738 | 0.0096485 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Coast | 6996 | 1 | 2.5957e-06 | 182541101 | ATASCADERO 1101 | ATASCADERO 1101circuit_breaker | 491.5839 | 2.5957e-06 | 2789 | 0.30546 | 25266.0434 | 0.0096459 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1996 | 16 | 2.5936e-06 | 43351103 | LUCERNE 1103 | LUCERNE 11031663 | 1947.6462 | 4.1497e-05 | 2508 | 1.2102 | 25267.2536 | 0.0096044 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4378 | 29 | 2.5817e-06 | 83242109 | MORGAN HILL 2109 | MORGAN HILL 2109XR246 | 4044.708 | 7.487e-05 | 2418 | 2.5133 | 25269.7669 | 0.0095296 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 792 | 12 | 2.575e-06 | 163781701 | PEORIA 1701 | PEORIA 17019250 | 13421.5992 | 3.09e-05 | 2542 | 8.3398 | 25278.1067 | 0.0094987 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4524 | 36 | 2.5722e-06 | 12101104 | OAKLAND K 1104 | OAKLAND K 1104CR208 | 3895.4111 | 9.2599e-05 | 2385 | 2.4205 | 25280.5272 | 0.0094061 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2952 | 36 | 2.5493e-06 | 183071101 | PERRY 1101 | PERRY 1101W52 | 4757.9409 | 9.1775e-05 | 2387 | 2.9564 | 25283.4836 | 0.0093143 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1251 | 5 | 2.5403e-06 | 182721104 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y30 | 984.7789 | 1.2702e-05 | 2650 | 0.61191 | 25284.0956 | 0.0093016 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1173 | 30 | 2.5248e-06 | 182852204 | VIEJO 2204 | VIEJO 2204circuit_breaker | 3591.9838 | 7.5743e-05 | 2413 | 2.232 | 25286.3275 | 0.0092259 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1814 | 24 | 2.5237e-06 | 42031122 | ALTO 1122 | ALTO 1122circuit_breaker | 3067.3601 | 6.057e-05 | 2451 | 1.906 | 25288.2335 | 0.0091653 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6591 | 51 | 2.5218e-06 | 182291102 | HATTON 1102 | HATTON 1102648928 | 5792.882 | 0.00012861 | 2341 | 3.5995 | 25291.833 | 0.0090367 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5028 | 11 | 2.5166e-06 | 12061105 | BERKELEY F 1105 | BERKELEY F 1105BR100 | 1156.966 | 2.7683e-05 | 2554 | 0.71891 | 25292.5519 | 0.009009 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4062 | 8 | 2.5032e-06 | 42011104 | SAN RAFAEL 1104 | SAN RAFAEL 11042651 | 1083.7544 | 2.0026e-05 | 2595 | 0.67341 | 25293.2253 | 0.008989 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5914 | 44 | 2.497e-06 | 42481104 | IGNACIO 1104 | IGNACIO 11041290 | 5098.9497 | 0.00010987 | 2359 | 3.1683 | 25296.3937 | 0.0088791 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6914 | 43 | 2.4773e-06 | 182852203 | VIEJO 2203 | VIEJO 2203circuit_breaker | 4363.1693 | 0.00010652 | 2366 | 2.7111 | 25299.1048 | 0.0087726 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2189 | 1 | 3.3871e-06 | 83432103 | HICKS 2103 | HICKS 2103LB50 | 18634.0428 | 3.3871e-06 | 2265 | 11.5787 | 25310.6835 | 0.0087692 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Coast | 2189 | 94 | 2.4629e-06 | 83432103 | HICKS 2103 | HICKS 2103LB50 | 18634.0428 | 0.00023151 | 2265 | 11.5787 | 25322.2621 | 0.0085377 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Coast | 6805 | 119 | 2.4661e-06 | 182222103 | DEL MONTE 2103 | DEL MONTE 21032000 | 14596.6085 | 0.00029346 | 2246 | 9.0699 | 25331.332 | 0.0082442 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6923 | 33 | 2.4507e-06 | 42031122 | ALTO 1122 | ALTO 112265474 | 4236.5189 | 8.0874e-05 | 2402 | 2.6324 | 25333.9645 | 0.0081633 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8738 | 26 | 2.4274e-06 | 182371111 | LAURELES 1111 | LAURELES 11116421 | 2777.3682 | 6.3112e-05 | 2448 | 1.7258 | 25335.6903 | 0.0081002 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6965 | 6 | 2.4273e-06 | 182082102 | LOS OSITOS 2102 | LOS OSITOS 21027470 | 6032.2925 | 1.4564e-05 | 2631 | 3.7483 | 25339.4385 | 0.0080857 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2168 | 26 | 2.4212e-06 | 182222103 | DEL MONTE 2103 | DEL MONTE 21032654 | 2963.5999 | 6.2951e-05 | 2449 | 1.8415 | 25341.28 | 0.0080227 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 4487 | 4 | 2.4142e-06 | 163781701 | PEORIA 1701 | PEORIA 170184318 | 16239.9493 | 9.6569e-06 | 2688 | 10.091 | 25351.3711 | 0.0080131 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2419 | 10 | 2.4094e-06 | 12061105 | BERKELEY F 1105 | BERKELEY F 1105circuit_breaker | 1678.7947 | 2.4094e-05 | 2573 | 1.0432 | 25352.4142 | 0.007989 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2103 | 4 | 2.4086e-06 | 83371105 | SARATOGA 1105 | SARATOGA 1105circuit_breaker | 514.5552 | 9.6344e-06 | 2689 | 0.31973 | 25352.734 | 0.0079793 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1605 | 7 | 2.4043e-06 | 12101101 | OAKLAND K 1101 | OAKLAND K 1101CR172 | 572.872 | 1.683e-05 | 2616 | 0.35597 | 25353.0899 | 0.0079625 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5885 | 38 | 2.4023e-06 | 183071101 | PERRY 1101 | PERRY 1101W12 | 5951.1009 | 9.1287e-05 | 2388 | 3.6978 | 25356.7878 | 0.0078712 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3182 | 1 | 2.6224e-06 | 12101101 | OAKLAND K 1101 | OAKLAND K 1101circuit_breaker | 559.1884 | 2.6224e-06 | 2587 | 0.34746 | 25357.1352 | 0.0078686 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Bay Area | 3182 | 8 | 2.3746e-06 | 12101101 | OAKLAND K 1101 | OAKLAND K 1101circuit_breaker | 559.1884 | 1.8997e-05 | 2587 | 0.34746 | 25357.4827 | 0.0078496 | #N/A | #N/A | 2 | #N/A | #N/A | #N/A
Central Coast | 1942 | 134 | 2.4021e-06 | 182371112 | LAURELES 1112 | LAURELES 111268454 | 12588.4111 | 0.00032188 | 2236 | 7.8221 | 25365.3048 | 0.0075277 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3378 | 3 | 2.4003e-06 | 12101101 | OAKLAND K 1101 | OAKLAND K 1101CR178 | 529.8862 | 7.2008e-06 | 2712 | 0.32926 | 25365.634 | 0.0075205 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6006 | 3 | 2.3993e-06 | 13380401 | WOOD 0401 | WOOD 0401circuit_breaker | 198.8033 | 7.1979e-06 | 2713 | 0.12353 | 25365.7576 | 0.0075133 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4742 | 31 | 2.3868e-06 | 83371103 | SARATOGA 1103 | SARATOGA 1103LC16 | 6890.8055 | 7.399e-05 | 2421 | 4.2817 | 25370.0393 | 0.0074393 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4640 | 1 | 2.3732e-06 | 102911102 | WYANDOTTE 1102 | WYANDOTTE 110213914 | 43.1117 | 2.3732e-06 | 2794 | 0.026788 | 25370.0661 | 0.007437 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1695 | 4 | 2.3725e-06 | 182371112 | LAURELES 1112 | LAURELES 1112circuit_breaker | 334.2836 | 9.49e-06 | 2692 | 0.20771 | 25370.2738 | 0.0074275 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 5355 | 9 | 2.3592e-06 | 43311108 | KONOCTI 1108 | KONOCTI 11084037 | 1312.7691 | 2.1233e-05 | 2588 | 0.81572 | 25371.0895 | 0.0074062 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7396 | 23 | 2.3539e-06 | 163351702 | CURTIS 1702 | CURTIS 1702S2123 | 2995.553 | 5.4139e-05 | 2467 | 1.8613 | 25372.9509 | 0.0073521 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 9978 | 1 | 2.3484e-06 | 153612105 | CLARKSVILLE 2105 | CLARKSVILLE 210551478 | 81.0541 | 2.3484e-06 | 2795 | 0.050365 | 25373.0012 | 0.0073497 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7069 | 6 | 2.3216e-06 | 182222103 | DEL MONTE 2103 | DEL MONTE 210342226 | 616.5067 | 1.393e-05 | 2636 | 0.38308 | 25373.3843 | 0.0073358 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3919 | 50 | 2.3176e-06 | 182381101 | DOLAN ROAD 1101 | DOLAN ROAD 11013012 | 5235.0908 | 0.00011588 | 2351 | 3.2529 | 25376.6372 | 0.0072199 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4148 | 179 | 2.3163e-06 | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 11038894 | 18016.3153 | 0.00041461 | 2208 | 11.1948 | 25387.8321 | 0.0068053 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3718 | 46 | 2.2938e-06 | 12541106 | OAKLAND X 1106 | OAKLAND X 1106CR006 | 5810.9825 | 0.00010551 | 2370 | 3.6108 | 25391.4428 | 0.0066998 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 2738 | 57 | 2.286e-06 | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102circuit_breaker | 11973.99 | 0.0001303 | 2338 | 7.4403 | 25398.8831 | 0.0065695 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1269 | 1 | 2.2637e-06 | 182040405 | CARMEL 0405 | CARMEL 0405circuit_breaker | 58.7067 | 2.2637e-06 | 2797 | 0.036479 | 25398.9196 | 0.0065672 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1597 | 1 | 2.2516e-06 | 182631105 | SAN LUIS OBISPO 1105 | SAN LUIS OBISPO 1105circuit_breaker | 67.4906 | 2.2516e-06 | 2798 | 0.041937 | 25398.9615 | 0.006565 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9756 | 1 | 2.2389e-06 | 42011109 | SAN RAFAEL 1109 | SAN RAFAEL 11092213 | 666.4301 | 2.2389e-06 | 2799 | 0.4141 | 25399.3756 | 0.0065628 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4978 | 43 | 2.2384e-06 | 13681112 | EDES 1112 | EDES 1112CR312 | 5725.9493 | 9.6253e-05 | 2380 | 3.5579 | 25402.9336 | 0.0064665 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4057 | 12 | 2.2317e-06 | 182852202 | VIEJO 2202 | VIEJO 22022606 | 1139.9059 | 2.678e-05 | 2560 | 0.7083 | 25403.6419 | 0.0064397 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4565 | 72 | 2.2143e-06 | 103311101 | BURNEY 1102 | BURNEY 110245984 | 7772.5624 | 0.00015943 | 2314 | 4.8296 | 25408.4715 | 0.0062803 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6508 | 25 | 2.2126e-06 | 24080402 | EMERALD LAKE 0402 | EMERALD LAKE 04028858 | 3073.6226 | 5.5314e-05 | 2462 | 1.9099 | 25410.3814 | 0.006225 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6087 | 7 | 2.2046e-06 | 42011101 | SAN RAFAEL 1101 | SAN RAFAEL 1101310 | 395.8699 | 1.5432e-05 | 2625 | 0.24598 | 25410.6274 | 0.0062095 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6509 | 3 | 2.1969e-06 | 24181104 | SAN CARLOS 1104 | SAN CARLOS 110475210 | 618.926 | 6.5906e-06 | 2721 | 0.38458 | 25411.012 | 0.006203 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5893 | 54 | 2.1906e-06 | 24060404 | CAROLANDS 0404 | CAROLANDS 04049024 | 5539.7321 | 0.00011829 | 2348 | 3.4422 | 25414.4542 | 0.0060847 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5151 | 3 | 2.1882e-06 | 13432207 | FAIRVIEW 2207 | FAIRVIEW 2207circuit_breaker | 267.7583 | 6.5645e-06 | 2722 | 0.16638 | 25414.6206 | 0.0060781 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8536 | 25 | 2.187e-06 | 12101103 | OAKLAND K 1103 | OAKLAND K 1103CR422 | 3148.3595 | 5.4675e-05 | 2465 | 1.9563 | 25416.5769 | 0.0060234 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 774 | 36 | 2.1858e-06 | 12101104 | OAKLAND K 1104 | OAKLAND K 1104CR210 | 4546.547 | 7.869e-05 | 2404 | 2.8251 | 25419.402 | 0.0059447 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 9104 | 6 | 2.1773e-06 | 182222103 | DEL MONTE 2103 | DEL MONTE 21032204 | 592.6413 | 1.3064e-05 | 2645 | 0.36825 | 25419.7702 | 0.0059317 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6362 | 1 | 2.1733e-06 | 14341106 | VALLEY VIEW 1106 | VALLEY VIEW 1106P180 | 133.4076 | 2.1733e-06 | 2800 | 0.082896 | 25419.8531 | 0.0059295 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6954 | 1 | 2.1662e-06 | 182852203 | VIEJO 2203 | VIEJO 22032634 | 0 | 2.1662e-06 | 2801 | 0 | 25419.8531 | 0.0059273 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 59 | 1 | 2.1437e-06 | 24012102 | BAY MEADOWS 2102 | BAY MEADOWS 2102circuit_breaker | 5.118 | 2.1437e-06 | 2802 | 0.0031802 | 25419.8563 | 0.0059252 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5852 | 25 | 2.141e-06 | 182852204 | VIEJO 2204 | VIEJO 22049540 | 2249.934 | 5.3526e-05 | 2470 | 1.398 | 25421.2543 | 0.0058717 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 526 | 13 | 2.1374e-06 | 182541101 | ATASCADERO 1101 | ATASCADERO 11012379 | 1171.3689 | 2.7786e-05 | 2553 | 0.72785 | 25421.9822 | 0.0058439 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2893 | 5 | 2.136e-06 | 24251104 | WOODSIDE 1104 | WOODSIDE 11049116 | 1213.0994 | 1.068e-05 | 2673 | 0.75378 | 25422.736 | 0.0058332 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3391 | 7 | 2.1318e-06 | 82021101 | LOS GATOS 1101 | LOS GATOS 110160136 | 461.7186 | 1.4923e-05 | 2629 | 0.2869 | 25423.0229 | 0.0058183 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 9222 | 1 | 2.1312e-06 | 182222104 | DEL MONTE 2104 | DEL MONTE 21043066 | 26.0345 | 2.1312e-06 | 2803 | 0.016177 | 25423.039 | 0.0058161 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7709 | 1 | 2.1302e-06 | 13801105 | MORAGA 1105 | MORAGA 110518396 | 125.7014 | 2.1302e-06 | 2804 | 0.078107 | 25423.1171 | 0.005814 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6806 | 26 | 2.1145e-06 | 182222103 | DEL MONTE 2103 | DEL MONTE 210332886 | 2565.9589 | 5.4976e-05 | 2464 | 1.5944 | 25424.7116 | 0.005759 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6644 | 21 | 2.1099e-06 | 13801101 | MORAGA 1101 | MORAGA 11017616 | 2295.5196 | 4.4308e-05 | 2495 | 1.4264 | 25426.1379 | 0.0057147 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 283 | 40 | 2.096e-06 | 12541106 | OAKLAND X 1106 | OAKLAND X 1106circuit_breaker | 6219.7565 | 8.3841e-05 | 2396 | 3.8648 | 25430.0027 | 0.0056309 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 995 | 20 | 2.0931e-06 | 182852201 | VIEJO 2201 | VIEJO 22019490 | 2513.194 | 4.1862e-05 | 2504 | 1.5616 | 25431.5643 | 0.005589 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5052 | 15 | 2.0883e-06 | 103311101 | BURNEY 1102 | BURNEY 1102circuit_breaker | 1949.5939 | 3.1325e-05 | 2541 | 1.2114 | 25432.7758 | 0.0055577 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 289 | 21 | 2.0882e-06 | 12840402 | RIDGE 0402 | RIDGE 0402circuit_breaker | 2818.3373 | 4.3853e-05 | 2498 | 1.7512 | 25434.527 | 0.0055138 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7417 | 4 | 2.0845e-06 | 182040402 | CARMEL 0402 | CARMEL 0402circuit_breaker | 461.4011 | 8.3381e-06 | 2702 | 0.2867 | 25434.8137 | 0.0055055 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5764 | 8 | 2.0845e-06 | 182852201 | VIEJO 2201 | VIEJO 22019698 | 912.5815 | 1.6676e-05 | 2617 | 0.56705 | 25435.3807 | 0.0054888 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5207 | 6 | 2.0675e-06 | 24060404 | CAROLANDS 0404 | CAROLANDS 040484797 | 159.0147 | 1.2405e-05 | 2653 | 0.098807 | 25435.4795 | 0.0054764 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8323 | 5 | 2.0555e-06 | 24181104 | SAN CARLOS 1104 | SAN CARLOS 110436864 | 812.4562 | 1.0278e-05 | 2675 | 0.50484 | 25435.9844 | 0.0054661 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1411 | 80 | 2.0371e-06 | 182852201 | VIEJO 2201 | VIEJO 22019114 | 10880.685 | 0.00016296 | 2312 | 6.7609 | 25442.7453 | 0.0053032 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6135 | 17 | 2.0366e-06 | 183071101 | PERRY 1101 | PERRY 1101W10 | 1609.5516 | 3.4622e-05 | 2527 | 1.0001 | 25443.7455 | 0.0052686 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6936 | 69 | 2.0366e-06 | 24181104 | SAN CARLOS 1104 | SAN CARLOS 11049052 | 7726.2126 | 0.00014052 | 2332 | 4.8008 | 25448.5463 | 0.005128 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 931 | 1 | 2.0361e-06 | 83481109 | STELLING 1109 | STELLING 110913228 | 1453.4738 | 2.0361e-06 | 2806 | 0.90315 | 25449.4494 | 0.005126 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7684 | 21 | 2.0352e-06 | 24080402 | EMERALD LAKE 0402 | EMERALD LAKE 0402circuit_breaker | 3052.0291 | 4.2739e-05 | 2499 | 1.8964 | 25451.3459 | 0.0050833 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 71 | 1 | 2.0339e-06 | 24110404 | HILLSDALE 0404 | HILLSDALE 040485812 | 0 | 2.0339e-06 | 2807 | 0 | 25451.3459 | 0.0050812 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 8419 | 2 | 2.0064e-06 | 254452102 | MARIPOSA 2102 | MARIPOSA 210210250 | 66.9649 | 4.0128e-06 | 2760 | 0.04161 | 25451.3875 | 0.0050772 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6763 | 15 | 2.0048e-06 | 12101101 | OAKLAND K 1101 | OAKLAND K 1101CR170 | 2012.9178 | 3.0072e-05 | 2546 | 1.2508 | 25452.6383 | 0.0050471 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6338 | 129 | 1.9939e-06 | 83431116 | HICKS 1116 | HICKS 111660050 | 13194.2857 | 0.00025721 | 2258 | 8.1985 | 25460.8368 | 0.0047899 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7699 | 27 | 1.9837e-06 | 182291101 | HATTON 1101 | HATTON 1101circuit_breaker | 2553.7001 | 5.3559e-05 | 2469 | 1.5868 | 25462.4236 | 0.0047364 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1235 | 47 | 1.9771e-06 | 13180401 | PALO SECO 0401 | PALO SECO 0401circuit_breaker | 7450.9364 | 9.2923e-05 | 2383 | 4.6298 | 25467.0534 | 0.0046435 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2423 | 52 | 1.9449e-06 | 12101103 | OAKLAND K 1103 | OAKLAND K 1103CR188 | 5757.5465 | 0.00010113 | 2372 | 3.5776 | 25470.631 | 0.0045423 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3744 | 33 | 1.9359e-06 | 182971101 | PURISIMA 1101 | PURISIMA 1101circuit_breaker | 5755.7195 | 6.3885e-05 | 2447 | 3.5764 | 25474.2074 | 0.0044784 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5480 | 7 | 1.9356e-06 | 12101104 | OAKLAND K 1104 | OAKLAND K 1104circuit_breaker | 2362.6398 | 1.3549e-05 | 2639 | 1.4681 | 25475.6755 | 0.0044649 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2068 | 19 | 1.9351e-06 | 13340402 | SPRUCE 0402 | SPRUCE 0402BR304 | 2445.8736 | 3.6767e-05 | 2521 | 1.5198 | 25477.1953 | 0.0044281 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1844 | 31 | 1.9227e-06 | 182291102 | HATTON 1102 | HATTON 1102circuit_breaker | 3118.5334 | 5.9602e-05 | 2454 | 1.9378 | 25479.133 | 0.0043685 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6323 | 28 | 1.9179e-06 | 182852202 | VIEJO 2202 | VIEJO 2202circuit_breaker | 3355.2545 | 5.37e-05 | 2468 | 2.0849 | 25481.2179 | 0.0043148 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 542 | 1 | 1.9085e-06 | 83531103 | MC KEE 1103 | MC KEE 1103XR028 | 1085.7736 | 1.9085e-06 | 2809 | 0.67467 | 25481.8926 | 0.0043129 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2322 | 8 | 1.9043e-06 | 12541104 | OAKLAND X 1104 | OAKLAND X 1104circuit_breaker | 2011.6074 | 1.5234e-05 | 2628 | 1.25 | 25483.1425 | 0.0042977 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 63 | 31 | 1.9002e-06 | 12541105 | OAKLAND X 1105 | OAKLAND X 1105circuit_breaker | 3428.0095 | 5.8907e-05 | 2457 | 2.1301 | 25485.2726 | 0.0042388 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3434 | 3 | 1.8966e-06 | 12690401 | FLORENCE 0401 | FLORENCE 0401CR220 | 350.2675 | 5.6899e-06 | 2732 | 0.21765 | 25485.4902 | 0.0042331 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1020 | 20 | 1.8927e-06 | 103021101 | GANSNER 1101 | GANSNER 110152664 | 1440.8216 | 3.7855e-05 | 2516 | 0.89528 | 25486.3855 | 0.0041952 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3120 | 7 | 1.8922e-06 | 43201102 | STAFFORD 1102 | STAFFORD 110242542 | 623.2409 | 1.3245e-05 | 2641 | 0.38726 | 25486.7728 | 0.004182 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 7645 | 4 | 1.8905e-06 | 42251101 | HOPLAND 1101 | HOPLAND 1101circuit_breaker | 1104.2357 | 7.5621e-06 | 2708 | 0.68614 | 25487.4589 | 0.0041744 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5759 | 61 | 1.8858e-06 | 24040403 | BERESFORD 0403 | BERESFORD 04039154 | 6496.7789 | 0.00011503 | 2354 | 4.0369 | 25491.4958 | 0.0040594 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5120 | 52 | 1.8742e-06 | 13111109 | SAN LEANDRO U 1109 | SAN LEANDRO U 1109CR182 | 7762.1289 | 9.7458e-05 | 2376 | 4.8232 | 25496.319 | 0.0039619 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 9245 | 17 | 1.8693e-06 | 182371111 | LAURELES 1111 | LAURELES 111184523 | 1964.6047 | 3.1778e-05 | 2540 | 1.2207 | 25497.5397 | 0.0039301 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5517 | 7 | 1.8675e-06 | 12690401 | FLORENCE 0401 | FLORENCE 0401circuit_breaker | 996.0372 | 1.3073e-05 | 2644 | 0.61891 | 25498.1587 | 0.0039171 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4662 | 8 | 1.8545e-06 | 42031125 | ALTO 1125 | ALTO 1125circuit_breaker | 831.7602 | 1.4836e-05 | 2630 | 0.51683 | 25498.6755 | 0.0039022 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 249 | 35 | 1.8475e-06 | 83431116 | HICKS 1116 | HICKS 1116circuit_breaker | 4776.7233 | 6.4663e-05 | 2444 | 2.9681 | 25501.6436 | 0.0038376 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 613 | 70 | 1.8447e-06 | 14161101 | ROSSMOOR 1101 | ROSSMOOR 1101L503R | 6929.1359 | 0.00012913 | 2340 | 4.3056 | 25505.9492 | 0.0037084 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4984 | 6 | 1.8308e-06 | 183011101 | MORRO BAY 1101 | MORRO BAY 1101W20 | 3169.5643 | 1.0985e-05 | 2669 | 1.9695 | 25507.9186 | 0.0036975 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5085 | 7 | 1.8273e-06 | 42481103 | IGNACIO 1103 | IGNACIO 1103circuit_breaker | 849.0798 | 1.2791e-05 | 2648 | 0.52759 | 25508.4462 | 0.0036847 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 695 | 26 | 1.8253e-06 | 182222104 | DEL MONTE 2104 | DEL MONTE 21042760 | 4362.4601 | 4.7457e-05 | 2486 | 2.7107 | 25511.1569 | 0.0036372 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6876 | 19 | 1.817e-06 | 182852201 | VIEJO 2201 | VIEJO 2201circuit_breaker | 8158.9016 | 3.4524e-05 | 2529 | 5.0697 | 25516.2267 | 0.0036027 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3662 | 3 | 1.8084e-06 | 183031101 | PALMER 1101 | PALMER 1101M82 | 16759.4337 | 5.4252e-06 | 2739 | 10.4138 | 25526.6405 | 0.0035973 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 645 | 16 | 1.7974e-06 | 12091102 | OAKLAND J 1102 | OAKLAND J 1102CR252 | 1754.2398 | 2.8758e-05 | 2550 | 1.09 | 25527.7305 | 0.0035685 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2509 | 5 | 1.7822e-06 | 14091101 | CASTRO VALLEY 1101 | CASTRO VALLEY 1101MR204 | 232.9604 | 8.9111e-06 | 2695 | 0.14475 | 25527.8753 | 0.0035596 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3426 | 28 | 1.7774e-06 | 24251104 | WOODSIDE 1104 | WOODSIDE 11049030 | 3145.1983 | 4.9768e-05 | 2480 | 1.9543 | 25529.8296 | 0.0035098 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2238 | 122 | 1.7533e-06 | 102541101 | VOLTA 1101 | VOLTA 110185234 | 12197.7117 | 0.0002139 | 2282 | 7.5793 | 25537.4089 | 0.0032959 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1112 | 54 | 1.7526e-06 | 24181103 | SAN CARLOS 1103 | SAN CARLOS 11039148 | 6379.4044 | 9.4639e-05 | 2381 | 3.964 | 25541.3729 | 0.0032013 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 386 | 40 | 1.7498e-06 | 24031103 | BELMONT 1103 | BELMONT 11038958 | 5350.191 | 6.9991e-05 | 2431 | 3.3245 | 25544.6973 | 0.0031313 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1757 | 4 | 1.749e-06 | 12060402 | BERKELEY F 0402 | BERKELEY F 0402circuit_breaker | 226.0238 | 6.9961e-06 | 2717 | 0.14044 | 25544.8378 | 0.0031243 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2603 | 17 | 1.744e-06 | 12091106 | OAKLAND J 1106 | OAKLAND J 1106CR164 | 2328.9296 | 2.9647e-05 | 2549 | 1.4471 | 25546.2849 | 0.0030946 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8948 | 4 | 1.7386e-06 | 83242105 | MORGAN HILL 2105 | MORGAN HILL 2105XR602 | 356.9004 | 6.9545e-06 | 2718 | 0.22177 | 25546.5067 | 0.0030877 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6127 | 67 | 1.7382e-06 | 12541106 | OAKLAND X 1106 | OAKLAND X 1106CR008 | 7102.0164 | 0.00011646 | 2350 | 4.413 | 25550.9197 | 0.0029712 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3736 | 3 | 1.7301e-06 | 42031120 | ALTO 1120 | ALTO 1120500 | 498.0083 | 5.1903e-06 | 2741 | 0.30945 | 25551.2291 | 0.002966 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4406 | 13 | 1.7296e-06 | 182852202 | VIEJO 2202 | VIEJO 220285904 | 1316.0449 | 2.2484e-05 | 2580 | 0.81775 | 25552.0469 | 0.0029436 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 10107 | 1 | 1.7279e-06 | 152481104 | BRUNSWICK 1104 | BRUNSWICK 1104761310 | 43.1053 | 1.7279e-06 | 2812 | 0.026784 | 25552.0736 | 0.0029418 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 197 | 1 | 1.7129e-06 | 42631109 | PETALUMA C 1109 | PETALUMA C 1109270 | 2986.7863 | 1.7129e-06 | 2813 | 1.8559 | 25553.9296 | 0.0029401 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6784 | 29 | 1.707e-06 | 182731102 | RESERVATION ROAD 1102 | RESERVATION ROAD 11023032 | 4109.0682 | 4.9503e-05 | 2481 | 2.5533 | 25556.4828 | 0.0028906 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6768 | 25 | 1.7043e-06 | 182291102 | HATTON 1102 | HATTON 11029642 | 1925.8934 | 4.2607e-05 | 2502 | 1.1967 | 25557.6795 | 0.002848 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 451 | 1 | 1.7033e-06 | 43211102 | HARTLEY 1102 | HARTLEY 1102824 | 137.5107 | 1.7033e-06 | 2814 | 0.085445 | 25557.7649 | 0.0028463 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4110 | 16 | 1.7013e-06 | 14341106 | VALLEY VIEW 1106 | VALLEY VIEW 1106P176 | 1598.933 | 2.722e-05 | 2557 | 0.99353 | 25558.7585 | 0.0028191 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 181 | 9 | 1.6946e-06 | 13480401 | ESTUDILLO 0401 | ESTUDILLO 0401circuit_breaker | 1368.0825 | 1.5252e-05 | 2627 | 0.85009 | 25559.6086 | 0.0028038 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9368 | 2 | 1.6884e-06 | 14091106 | CASTRO VALLEY 1106 | CASTRO VALLEY 1106MR233 | 164.9976 | 3.3768e-06 | 2770 | 0.10252 | 25559.7111 | 0.0028005 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4813 | 49 | 1.6813e-06 | 13681112 | EDES 1112 | EDES 1112CR282 | 6573.0208 | 8.2382e-05 | 2399 | 4.0843 | 25563.7954 | 0.0027181 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1079 | 3 | 1.6717e-06 | 182852201 | VIEJO 2201 | VIEJO 22012064 | 1409.3976 | 5.0151e-06 | 2742 | 0.87576 | 25564.6711 | 0.0027131 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 160 | 5 | 1.6696e-06 | 43491103 | CORONA 1103 | CORONA 11034446 | 734.2401 | 8.3481e-06 | 2701 | 0.45624 | 25565.1274 | 0.0027047 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1767 | 1 | 1.6459e-06 | 83242105 | MORGAN HILL 2105 | MORGAN HILL 2105XR578 | 251.9162 | 1.6459e-06 | 2816 | 0.15653 | 25565.2839 | 0.0027031 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2447 | 28 | 1.6363e-06 | 24181104 | SAN CARLOS 1104 | SAN CARLOS 11048846 | 3326.5951 | 4.5816e-05 | 2493 | 2.067 | 25567.3509 | 0.0026572 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2724 | 4 | 1.6307e-06 | 12501112 | EL CERRITO G 1112 | EL CERRITO G 1112BR180 | 850.589 | 6.5228e-06 | 2723 | 0.52853 | 25567.8795 | 0.0026507 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 226 | 12 | 1.6265e-06 | 24060404 | CAROLANDS 0404 | CAROLANDS 04049026 | 1254.4036 | 1.9518e-05 | 2597 | 0.77945 | 25568.6589 | 0.0026312 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2301 | 3 | 1.6257e-06 | 83242106 | MORGAN HILL 2106 | MORGAN HILL 2106circuit_breaker | 0 | 4.877e-06 | 2745 | 0 | 25568.6589 | 0.0026263 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7692 | 10 | 1.6131e-06 | 24251104 | WOODSIDE 1104 | WOODSIDE 110411555 | 1379.9837 | 1.6131e-05 | 2620 | 0.85748 | 25569.5164 | 0.0026102 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1941 | 1 | 1.6072e-06 | 24141102 | RALSTON 1102 | RALSTON 11022028 | 2900.1535 | 1.6072e-06 | 2818 | 1.8021 | 25571.3185 | 0.0026086 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4930 | 36 | 1.5965e-06 | 182222104 | DEL MONTE 2104 | DEL MONTE 21049096 | 4576.3876 | 5.7473e-05 | 2459 | 2.8436 | 25574.1621 | 0.0025511 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4020 | 1 | 1.5962e-06 | 103311102 | BURNEY 1102 | BURNEY 110257046 | 77.1037 | 1.5962e-06 | 2820 | 0.04791 | 25574.21 | 0.0025495 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4178 | 45 | 1.593e-06 | 24080402 | EMERALD LAKE 0402 | EMERALD LAKE 04028872 | 7185.3167 | 7.1683e-05 | 2427 | 4.4647 | 25578.6748 | 0.0024778 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2515 | 4 | 1.5687e-06 | 182222104 | DEL MONTE 2104 | DEL MONTE 21042032 | 253.941 | 6.2748e-06 | 2725 | 0.15779 | 25578.8326 | 0.0024716 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5708 | 31 | 1.5672e-06 | 102551101 | EAST QUINCY 1101 | EAST QUINCY 11012452 | 2653.0626 | 4.8583e-05 | 2484 | 1.6485 | 25580.4811 | 0.002423 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5032 | 9 | 1.5588e-06 | 182852202 | VIEJO 2202 | VIEJO 22029120 | 2530.9244 | 1.4029e-05 | 2635 | 1.5726 | 25582.0537 | 0.002409 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1306 | 21 | 1.5564e-06 | 13170401 | HOLLYWOOD 0401 | HOLLYWOOD 0401circuit_breaker | 4478.6501 | 3.2684e-05 | 2536 | 2.7829 | 25584.8366 | 0.0023763 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7151 | 10 | 1.5555e-06 | 13681112 | EDES 1112 | EDES 1112CR306 | 1619.5833 | 1.5555e-05 | 2624 | 1.0064 | 25585.843 | 0.0023607 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3308 | 4 | 1.5554e-06 | 43091104 | GREENBRAE 1104 | GREENBRAE 1104751 | 342.6723 | 6.2216e-06 | 2726 | 0.21293 | 25586.0559 | 0.0023545 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1993 | 44 | 1.5546e-06 | 83431116 | HICKS 1116 | HICKS 1116LB16 | 4954.2992 | 6.8402e-05 | 2434 | 3.0785 | 25589.1344 | 0.0022861 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 369 | 23 | 1.5535e-06 | 24040403 | BERESFORD 0403 | BERESFORD 0403circuit_breaker | 1971.1564 | 3.5731e-05 | 2523 | 1.2248 | 25590.3592 | 0.0022504 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4320 | 9 | 1.5432e-06 | 12541101 | OAKLAND X 1101 | OAKLAND X 1101CR224 | 791.862 | 1.3889e-05 | 2637 | 0.49204 | 25590.8513 | 0.0022365 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 543 | 5 | 1.5385e-06 | 42031120 | ALTO 1120 | ALTO 112088190 | 530.6966 | 7.6926e-06 | 2707 | 0.32976 | 25591.181 | 0.0022288 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6898 | 3 | 1.5371e-06 | 182440422 | PACIFIC GROVE 0422 | PACIFIC GROVE 04222614 | 283.1092 | 4.6114e-06 | 2749 | 0.17592 | 25591.3569 | 0.0022242 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 40 | 53 | 1.5338e-06 | 24251104 | WOODSIDE 1104 | WOODSIDE 1104555372 | 6600.4202 | 8.1294e-05 | 2401 | 4.1013 | 25595.4582 | 0.0021429 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6845 | 2 | 1.5301e-06 | 12501112 | EL CERRITO G 1112 | EL CERRITO G 111257953 | 188.8354 | 3.0603e-06 | 2774 | 0.11734 | 25595.5756 | 0.0021398 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 136 | 51 | 1.5223e-06 | 183011102 | MORRO BAY 1102 | MORRO BAY 1102W34 | 11103.8333 | 7.7636e-05 | 2408 | 6.8996 | 25602.4752 | 0.0020622 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7806 | 9 | 1.5199e-06 | 182852202 | VIEJO 2202 | VIEJO 22029089 | 2193.9182 | 1.3679e-05 | 2638 | 1.3632 | 25603.8384 | 0.0020485 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3322 | 75 | 1.5079e-06 | 182852202 | VIEJO 2202 | VIEJO 22029104 | 9288.626 | 0.00011309 | 2356 | 5.7717 | 25609.6101 | 0.0019354 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7828 | 11 | 1.4948e-06 | 12091102 | OAKLAND J 1102 | OAKLAND J 1102CR254 | 1602.2826 | 1.6443e-05 | 2618 | 0.99561 | 25610.6057 | 0.001919 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5793 | 2 | 1.4816e-06 | 24251102 | WOODSIDE 1102 | WOODSIDE 11028862 | 97.31 | 2.9632e-06 | 2778 | 0.060466 | 25610.6662 | 0.001916 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3771 | 80 | 1.4803e-06 | 182291101 | HATTON 1101 | HATTON 11012026 | 7951.2018 | 0.00011843 | 2347 | 4.9406 | 25615.6068 | 0.0017976 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2408 | 13 | 1.4731e-06 | 182852202 | VIEJO 2202 | VIEJO 22029112 | 1129.5145 | 1.9151e-05 | 2599 | 0.70185 | 25616.3087 | 0.0017784 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1081 | 15 | 1.4618e-06 | 182222103 | DEL MONTE 2103 | DEL MONTE 210386496 | 1909.93 | 2.1926e-05 | 2582 | 1.1868 | 25617.4954 | 0.0017565 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6816 | 1 | 1.4548e-06 | 83431115 | HICKS 1115 | HICKS 111512494 | 84.655 | 1.4548e-06 | 2821 | 0.052602 | 25617.548 | 0.001755 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4812 | 19 | 1.4532e-06 | 14091108 | CASTRO VALLEY 1108 | CASTRO VALLEY 1108circuit_breaker | 2110.9437 | 2.7611e-05 | 2555 | 1.3117 | 25618.8597 | 0.0017274 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 745 | 2 | 1.4443e-06 | 13531102 | LAKEWOOD 1102 | LAKEWOOD 1102circuit_breaker | 153.4063 | 2.8887e-06 | 2781 | 0.095322 | 25618.955 | 0.0017245 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4871 | 41 | 1.4412e-06 | 12091102 | OAKLAND J 1102 | OAKLAND J 1102CR184 | 5568.9906 | 5.9089e-05 | 2456 | 3.4604 | 25622.4155 | 0.0016655 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2647 | 4 | 1.4409e-06 | 13320401 |  | CR242 | 362.7025 | 5.7634e-06 | 2730 | 0.22537 | 25622.6408 | 0.0016597 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4097 | 13 | 1.4398e-06 | 13432207 | FAIRVIEW 2207 | FAIRVIEW 2207P142 | 1449.2328 | 1.8718e-05 | 2604 | 0.90051 | 25623.5413 | 0.001641 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6234 | 8 | 1.4369e-06 | 182852202 | VIEJO 2202 | VIEJO 22029118 | 903.5074 | 1.1495e-05 | 2660 | 0.56141 | 25624.1028 | 0.0016295 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1645 | 1 | 1.4293e-06 | 14091109 | CASTRO VALLEY 1109 | CASTRO VALLEY 1109circuit_breaker | 222.2939 | 1.4293e-06 | 2822 | 0.13813 | 25624.2409 | 0.001628 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7033 | 4 | 1.4126e-06 | 182852202 | VIEJO 2202 | VIEJO 220235388 | 676.3797 | 5.6503e-06 | 2733 | 0.42028 | 25624.6612 | 0.0016224 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9585 | 10 | 1.4051e-06 | 12091102 | OAKLAND J 1102 | OAKLAND J 1102CR102 | 846.0426 | 1.4051e-05 | 2634 | 0.52571 | 25625.1869 | 0.0016083 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 822 | 31 | 1.378e-06 | 183011102 | MORRO BAY 1102 | MORRO BAY 1102W22 | 3676.1403 | 4.2718e-05 | 2500 | 2.2842 | 25627.4711 | 0.0015656 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1013 | 8 | 1.3761e-06 | 42031123 | ALTO 1123 | ALTO 1123circuit_breaker | 1041.5153 | 1.1009e-05 | 2668 | 0.64717 | 25628.1183 | 0.0015546 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7297 | 2 | 1.3684e-06 | 103311102 | BURNEY 1102 | BURNEY 110237284 | 11.2633 | 2.7368e-06 | 2784 | 0.0069987 | 25628.1253 | 0.0015519 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3926 | 35 | 1.3532e-06 | 13681112 | EDES 1112 | EDES 1112CR100 | 5399.0675 | 4.7361e-05 | 2488 | 3.3548 | 25631.4801 | 0.0015045 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8192 | 8 | 1.3359e-06 | 182852202 | VIEJO 2202 | VIEJO 22029488 | 1141.9334 | 1.0687e-05 | 2672 | 0.70956 | 25632.1897 | 0.0014938 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6710 | 1 | 1.3174e-06 | 182852202 | VIEJO 2202 | VIEJO 220292792 | 0 | 1.3174e-06 | 2823 | 0 | 25632.1897 | 0.0014925 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3642 | 11 | 1.2892e-06 | 14671101 | SOBRANTE 1101 | SOBRANTE 1101L534R | 1291.9266 | 1.4182e-05 | 2633 | 0.80277 | 25632.9924 | 0.0014783 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3626 | 10 | 1.289e-06 | 14091101 | CASTRO VALLEY 1101 | CASTRO VALLEY 1101MR359 | 1462.9174 | 1.289e-05 | 2647 | 0.90901 | 25633.9015 | 0.0014654 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5814 | 16 | 1.2744e-06 | 12091105 | OAKLAND J 1105 | OAKLAND J 1105CR256 | 1245.6022 | 2.0391e-05 | 2592 | 0.77398 | 25634.6754 | 0.0014451 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 410 | 56 | 1.2726e-06 | 24141101 | RALSTON 1101 | RALSTON 1101circuit_breaker | 7097.0963 | 7.1265e-05 | 2428 | 4.4099 | 25639.0854 | 0.0013738 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2000 | 47 | 1.2717e-06 | 13111114 | SAN LEANDRO U 1114 | SAN LEANDRO U 1114MR218 | 8791.3954 | 5.977e-05 | 2453 | 5.4627 | 25644.5481 | 0.001314 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2334 | 1 | 1.2694e-06 | 182852204 | VIEJO 2204 | VIEJO 22049110 | 20.6903 | 1.2694e-06 | 2824 | 0.012856 | 25644.5609 | 0.0013127 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 8717 | 9 | 1.2674e-06 | 158031101 | ECHO SUMMIT 1101 | ECHO SUMMIT 1101741586 | 1137.7952 | 1.1407e-05 | 2661 | 0.70699 | 25645.2679 | 0.0013013 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2921 | 20 | 1.2578e-06 | 43201101 | STAFFORD 1101 | STAFFORD 11011298 | 2037.2045 | 2.5155e-05 | 2565 | 1.2659 | 25646.5338 | 0.0012762 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 868 | 34 | 1.2523e-06 | 13681112 | EDES 1112 | EDES 1112CR308 | 5048.7285 | 4.258e-05 | 2503 | 3.1371 | 25649.6709 | 0.0012336 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 9061 | 9 | 1.2401e-06 | 158031101 | ECHO SUMMIT 1101 | ECHO SUMMIT 1101344250 | 1299.2708 | 1.1161e-05 | 2665 | 0.80733 | 25650.4783 | 0.0012224 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3597 | 1 | 1.2376e-06 | 182492104 | HOLLISTER 2104 | HOLLISTER 210441808 | 4.0767 | 1.2376e-06 | 2826 | 0.0025331 | 25650.4808 | 0.0012212 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5376 | 27 | 1.2368e-06 | 24181104 | SAN CARLOS 1104 | SAN CARLOS 11048942 | 3376.0521 | 3.3394e-05 | 2533 | 2.0978 | 25652.5786 | 0.0011878 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 8763 | 10 | 1.2258e-06 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 2101439 | 1041.6607 | 1.2258e-05 | 2654 | 0.64726 | 25653.2258 | 0.0011756 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 1545 | 36 | 1.2236e-06 | 158031101 | ECHO SUMMIT 1101 | ECHO SUMMIT 11012500 | 3502.0827 | 4.4048e-05 | 2497 | 2.1761 | 25655.4019 | 0.0011315 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3814 | 1 | 1.2196e-06 | 183011102 | MORRO BAY 1102 | MORRO BAY 1102V84 | 101.4196 | 1.2196e-06 | 2827 | 0.063019 | 25655.4649 | 0.0011303 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 199 | 8 | 1.2131e-06 | 24120401 | LAS PULGAS 0401 | LAS PULGAS 0401circuit_breaker | 583.9042 | 9.705e-06 | 2686 | 0.36282 | 25655.8278 | 0.0011206 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2513 | 2 | 1.2119e-06 | 182052102 | SOLEDAD 2102 | SOLEDAD 21027562 | 2922.6853 | 2.4237e-06 | 2792 | 1.8161 | 25657.6438 | 0.0011182 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2617 | 12 | 1.2099e-06 | 14091104 | CASTRO VALLEY 1104 | CASTRO VALLEY 1104MR201 | 1973.7097 | 1.4518e-05 | 2632 | 1.2264 | 25658.8702 | 0.0011036 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8443 | 1 | 1.2096e-06 | 182402106 | FORT ORD 2106 | FORT ORD 210637286 | 3227.6123 | 1.2096e-06 | 2828 | 2.0055 | 25660.8758 | 0.0011024 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 42 | 2 | 1.1955e-06 | 12091105 | OAKLAND J 1105 | OAKLAND J 1105153228 | 241.8819 | 2.391e-06 | 2793 | 0.1503 | 25661.0261 | 0.0011 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 9773 | 1 | 1.1835e-06 | 158031101 | ECHO SUMMIT 1101 | ECHO SUMMIT 110155262 | 266.534 | 1.1835e-06 | 2829 | 0.16562 | 25661.1917 | 0.0010989 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7884 | 1 | 1.182e-06 | 42291101 | OLEMA 1101 | OLEMA 110137074 | 21.9456 | 1.182e-06 | 2830 | 0.013636 | 25661.2053 | 0.0010977 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2481 | 10 | 1.1589e-06 | 182131103 | GONZALES 1103 | GONZALES 11033096 | 2007.6917 | 1.1589e-05 | 2659 | 1.2475 | 25662.4529 | 0.0010861 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 1286 | 4 | 1.1565e-06 | 182052101 | SOLEDAD 2101 | SOLEDAD 2101circuit_breaker | 1217.4718 | 4.6259e-06 | 2747 | 0.7565 | 25663.2094 | 0.0010815 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7483 | 2 | 1.1563e-06 | 102551101 | EAST QUINCY 1101 | EAST QUINCY 11011319 | 230.1059 | 2.3127e-06 | 2796 | 0.14298 | 25663.3523 | 0.0010791 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4550 | 24 | 1.1499e-06 | 22721101 | SNEATH LANE 1101 | SNEATH LANE 110134438 | 2524.5868 | 2.7599e-05 | 2556 | 1.5687 | 25664.921 | 0.0010515 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 474 | 77 | 1.1457e-06 | 12501105 | EL CERRITO G 1105 | EL CERRITO G 1105circuit_breaker | 11881.4228 | 8.8216e-05 | 2391 | 7.3828 | 25672.3038 | 0.00096333 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2622 | 49 | 1.1419e-06 | 14341105 | VALLEY VIEW 1105 | VALLEY VIEW 1105P190 | 4841.3798 | 5.5953e-05 | 2461 | 3.0083 | 25675.3121 | 0.00090738 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3517 | 39 | 1.1395e-06 | 12600401 | OAK 0401 | OAK 0401circuit_breaker | 5406.3145 | 4.4441e-05 | 2494 | 3.3593 | 25678.6714 | 0.00086294 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6115 | 66 | 1.1295e-06 | 24012102 | BAY MEADOWS 2102 | BAY MEADOWS 210257886 | 6347.2399 | 7.4545e-05 | 2419 | 3.944 | 25682.6154 | 0.00078839 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3200 | 73 | 1.1249e-06 | 13111109 | SAN LEANDRO U 1109 | SAN LEANDRO U 1109CR002 | 10902.831 | 8.2117e-05 | 2400 | 6.7747 | 25689.3901 | 0.00070628 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 8392 | 1 | 1.1231e-06 | 182051114 | SOLEDAD 1114 | SOLEDAD 111435306 | 1328.8876 | 1.1231e-06 | 2832 | 0.82573 | 25690.2159 | 0.00070515 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3199 | 5 | 1.1104e-06 | 12091106 | OAKLAND J 1106 | OAKLAND J 1106CR330 | 845.057 | 5.552e-06 | 2735 | 0.52509 | 25690.741 | 0.0006996 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 359 | 10 | 1.1028e-06 | 182971101 | PURISIMA 1101 | PURISIMA 110149394 | 1434.279 | 1.1028e-05 | 2667 | 0.89122 | 25691.6322 | 0.00068857 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5182 | 9 | 1.0972e-06 | 14101105 | ALHAMBRA 1105 | ALHAMBRA 1105circuit_breaker | 1107.679 | 9.8746e-06 | 2681 | 0.68828 | 25692.3205 | 0.0006787 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 8049 | 5 | 1.0862e-06 | 14161104 | ROSSMOOR 1104 | ROSSMOOR 110479146 | 400.4315 | 5.431e-06 | 2738 | 0.24882 | 25692.5693 | 0.00067327 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9380 | 9 | 1.0794e-06 | 102361101 | HAMILTON BRANCH 1101 | HAMILTON BRANCH 11012436 | 2038.321 | 9.7145e-06 | 2685 | 1.2666 | 25693.8358 | 0.00066355 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 954 | 4 | 1.072e-06 | 182221101 | DEL MONTE 1101 | DEL MONTE 110138582 | 792.5912 | 4.288e-06 | 2754 | 0.49249 | 25694.3283 | 0.00065927 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4052 | 3 | 1.0661e-06 | 12501110 | EL CERRITO G 1110 | EL CERRITO G 1110circuit_breaker | 376.2535 | 3.1983e-06 | 2771 | 0.23379 | 25694.5621 | 0.00065607 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 9984 | 1 | 1.0532e-06 | 163160401 | PINECREST 0401 | PINECREST 0401circuit_breaker | 20.6165 | 1.0532e-06 | 2833 | 0.01281 | 25694.5749 | 0.00065501 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6441 | 19 | 1.0495e-06 | 158031101 | ECHO SUMMIT 1101 | ECHO SUMMIT 11018922 | 1790.6655 | 1.994e-05 | 2596 | 1.1127 | 25695.6876 | 0.00063507 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 638 | 2 | 1.0264e-06 | 12091105 | OAKLAND J 1105 | OAKLAND J 1105CR130 | 753.2352 | 2.0529e-06 | 2805 | 0.46804 | 25696.1556 | 0.00063302 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1652 | 1 | 1.0225e-06 | 12091118 | OAKLAND J 1118 | OAKLAND J 1118CR198 | 515.4771 | 1.0225e-06 | 2834 | 0.3203 | 25696.4759 | 0.000632 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7965 | 4 | 1.0103e-06 | 22721107 | SNEATH LANE 1107 | SNEATH LANE 110715341 | 518.827 | 4.0413e-06 | 2758 | 0.32238 | 25696.7983 | 0.00062796 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3699 | 3 | 1.0068e-06 | 12501112 | EL CERRITO G 1112 | EL CERRITO G 1112circuit_breaker | 510.801 | 3.0205e-06 | 2776 | 0.3174 | 25697.1157 | 0.00062494 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4475 | 10 | 9.8727e-07 | 182291102 | HATTON 1102 | HATTON 11022070 | 797.8151 | 9.8727e-06 | 2682 | 0.49574 | 25697.6114 | 0.00061506 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 2274 | 2 | 9.8392e-07 | 63601112 | VACAVILLE 1112 | VACAVILLE 1112circuit_breaker | 207.005 | 1.9678e-06 | 2808 | 0.12863 | 25697.7401 | 0.0006131 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 141 | 11 | 9.7725e-07 | 14091108 | CASTRO VALLEY 1108 | CASTRO VALLEY 1108MR379 | 1604.9824 | 1.075e-05 | 2671 | 0.99729 | 25698.7374 | 0.00060235 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 440 | 3 | 9.7678e-07 | 182601105 | OCEANO 1105 | OCEANO 1105V44 | 1004.1237 | 2.9303e-06 | 2779 | 0.62393 | 25699.3613 | 0.00059942 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 6054 | 3 | 9.6346e-07 | 83242111 | MORGAN HILL 2111 | MORGAN HILL 2111circuit_breaker | 461.9266 | 2.8904e-06 | 2780 | 0.28703 | 25699.6483 | 0.00059653 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7726 | 3 | 9.6109e-07 | 12091105 | OAKLAND J 1105 | OAKLAND J 1105CR150 | 288.2243 | 2.8833e-06 | 2782 | 0.17909 | 25699.8274 | 0.00059364 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3401 | 22 | 9.4818e-07 | 42481105 |  | 318 | 2707.537 | 2.086e-05 | 2590 | 1.6824 | 25701.5098 | 0.00057278 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4756 | 9 | 9.379e-07 | 182631108 | SAN LUIS OBISPO 1108 | SAN LUIS OBISPO 1108circuit_breaker | 2912.0068 | 8.4411e-06 | 2699 | 1.8094 | 25703.3192 | 0.00056434 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4494 | 40 | 9.2444e-07 | 12501105 | EL CERRITO G 1105 | EL CERRITO G 1105BR194 | 5780.6278 | 3.6977e-05 | 2520 | 3.5919 | 25706.9112 | 0.00052736 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5974 | 9 | 9.1582e-07 | 24181104 | SAN CARLOS 1104 | SAN CARLOS 110479774 | 1093.2973 | 8.2424e-06 | 2704 | 0.67934 | 25707.5905 | 0.00051912 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1646 | 3 | 9.0864e-07 | 12501111 | EL CERRITO G 1111 | EL CERRITO G 1111circuit_breaker | 521.1606 | 2.7259e-06 | 2785 | 0.32383 | 25707.9143 | 0.0005164 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4313 | 2 | 8.834e-07 | 182090401 | MONTEREY 0401 | MONTEREY 04012642 | 395.9249 | 1.7668e-06 | 2810 | 0.24602 | 25708.1603 | 0.00051463 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4623 | 2 | 8.7797e-07 | 22721107 | SNEATH LANE 1107 | SNEATH LANE 11071277 | 61.1173 | 1.7559e-06 | 2811 | 0.037977 | 25708.1983 | 0.00051287 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3555 | 8 | 8.7795e-07 | 12650401 | FAIRMOUNT 0401 | FAIRMOUNT 0401circuit_breaker | 2166.002 | 7.0236e-06 | 2716 | 1.3459 | 25709.5442 | 0.00050585 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6801 | 10 | 8.7699e-07 | 103021101 | GANSNER 1101 | GANSNER 110199388 | 1047.5058 | 8.7699e-06 | 2697 | 0.65089 | 25710.1951 | 0.00049708 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3855 | 9 | 8.7465e-07 | 182090402 | MONTEREY 0402 | MONTEREY 04022644 | 887.4818 | 7.8719e-06 | 2706 | 0.55146 | 25710.7466 | 0.00048921 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1956 | 3 | 8.6505e-07 | 14091101 | CASTRO VALLEY 1101 | CASTRO VALLEY 1101MR518 | 621.9183 | 2.5951e-06 | 2790 | 0.38644 | 25711.133 | 0.00048661 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3585 | 2 | 8.4613e-07 | 13681112 | EDES 1112 | EDES 1112circuit_breaker | 342.8746 | 1.6923e-06 | 2815 | 0.21305 | 25711.3461 | 0.00048492 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 9495 | 22 | 8.3913e-07 | 102361101 | HAMILTON BRANCH 1101 | HAMILTON BRANCH 110118205 | 3707.1238 | 1.8461e-05 | 2605 | 2.3035 | 25713.6496 | 0.00046646 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 9208 | 24 | 8.3885e-07 | 13921104 | FRANKLIN 1104 | FRANKLIN 1104P136 | 6756.6357 | 2.0133e-05 | 2594 | 4.1984 | 25717.8479 | 0.00044633 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 476 | 1 | 8.1308e-07 | 22721102 | SNEATH LANE 1102 | SNEATH LANE 110210255 | 0 | 8.1308e-07 | 2837 | 0 | 25717.8479 | 0.00044551 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3646 | 14 | 8.1299e-07 | 14341105 | VALLEY VIEW 1105 | VALLEY VIEW 1105P126 | 1553.9705 | 1.1382e-05 | 2662 | 0.96559 | 25718.8135 | 0.00043413 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 3167 | 2 | 8.0976e-07 | 14341105 | VALLEY VIEW 1105 | VALLEY VIEW 1105circuit_breaker | 104.2614 | 1.6195e-06 | 2817 | 0.064785 | 25718.8783 | 0.00043251 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7735 | 13 | 7.892e-07 | 42491102 | SAUSALITO 1102 | SAUSALITO 1102410 | 1900.8841 | 1.026e-05 | 2676 | 1.1812 | 25720.0595 | 0.00042225 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 5474 | 1 | 7.779e-07 | 182631102 | SAN LUIS OBISPO 1102 | SAN LUIS OBISPO 1102597518 | 881.7949 | 7.779e-07 | 2838 | 0.54792 | 25720.6074 | 0.00042147 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 7161 | 5 | 7.6941e-07 | 182631107 | SAN LUIS OBISPO 1107 | SAN LUIS OBISPO 1107circuit_breaker | 1569.1089 | 3.8471e-06 | 2764 | 0.975 | 25721.5824 | 0.00041763 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 25 | 60 | 7.6714e-07 | 24141101 | RALSTON 1101 | RALSTON 110148936 | 7442.666 | 4.6028e-05 | 2492 | 4.6247 | 25726.207 | 0.0003716 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1040 | 23 | 7.5645e-07 | 13111114 | SAN LEANDRO U 1114 | SAN LEANDRO U 1114MR545 | 3494.5659 | 1.7398e-05 | 2609 | 2.1714 | 25728.3785 | 0.0003542 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 196 | 6 | 7.558e-07 | 12101103 | OAKLAND K 1103 | OAKLAND K 1103circuit_breaker | 859.4149 | 4.5348e-06 | 2751 | 0.53402 | 25728.9125 | 0.00034967 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2371 | 4 | 7.5488e-07 | 13111114 | SAN LEANDRO U 1114 | SAN LEANDRO U 1114MR544 | 1064.9351 | 3.0195e-06 | 2777 | 0.66172 | 25729.5742 | 0.00034665 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5766 | 1 | 7.2609e-07 | 42991104 | LAS GALLINAS A 1104 | LAS GALLINAS A 11041220 | 0 | 7.2609e-07 | 2839 | 0 | 25729.5742 | 0.00034592 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6253 | 15 | 7.2314e-07 | 102361101 | HAMILTON BRANCH 1101 | HAMILTON BRANCH 11012082 | 2146.9459 | 1.0847e-05 | 2670 | 1.334 | 25730.9082 | 0.00033507 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5600 | 1 | 7.2039e-07 | 42991105 | LAS GALLINAS A 1105 | LAS GALLINAS A 11051218 | 60.2784 | 7.2039e-07 | 2840 | 0.037455 | 25730.9457 | 0.00033435 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 8825 | 5 | 7.1959e-07 | 158031101 | ECHO SUMMIT 1101 | ECHO SUMMIT 1101481660 | 778.9778 | 3.5979e-06 | 2766 | 0.48403 | 25731.4297 | 0.00033075 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7531 | 8 | 7.194e-07 | 13111109 | SAN LEANDRO U 1109 | SAN LEANDRO U 1109CR284 | 1126.0171 | 5.7552e-06 | 2731 | 0.69967 | 25732.1294 | 0.000325 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 3715 | 14 | 7.1314e-07 | 102361101 | HAMILTON BRANCH 1101 | HAMILTON BRANCH 11013049 | 1766.4723 | 9.984e-06 | 2678 | 1.0976 | 25733.227 | 0.00031502 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4257 | 1 | 6.989e-07 | 182601103 | OCEANO 1103 | OCEANO 1103V22 | 1804.8041 | 6.989e-07 | 2841 | 1.1215 | 25734.3485 | 0.00031432 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 3165 | 4 | 6.9853e-07 | 182852204 | VIEJO 2204 | VIEJO 22049098 | 444.1507 | 2.7941e-06 | 2783 | 0.27598 | 25734.6245 | 0.00031152 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 1494 | 27 | 6.9392e-07 | 102361101 | HAMILTON BRANCH 1101 | HAMILTON BRANCH 110187784 | 2328.7215 | 1.8736e-05 | 2603 | 1.447 | 25736.0715 | 0.00029279 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6355 | 32 | 6.8466e-07 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012246 | 2937.4924 | 2.1909e-05 | 2583 | 1.8253 | 25737.8968 | 0.00027088 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 342 | 1 | 6.8369e-07 | 14101102 | ALHAMBRA 1102 | ALHAMBRA 1102circuit_breaker | 306.9084 | 6.8369e-07 | 2842 | 0.1907 | 25738.0875 | 0.00027019 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 737 | 18 | 6.7734e-07 | 13350401 | WALDO 0401 | WALDO 0401circuit_breaker | 2562.0667 | 1.2192e-05 | 2655 | 1.592 | 25739.6795 | 0.000258 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 4836 | 1 | 6.7393e-07 | 182052102 | SOLEDAD 2102 | SOLEDAD 21027008 | 3543.9744 | 6.7393e-07 | 2843 | 2.2021 | 25741.8816 | 0.00025733 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5548 | 6 | 6.7159e-07 | 13111114 | SAN LEANDRO U 1114 | SAN LEANDRO U 11149838 | 1189.5493 | 4.0295e-06 | 2759 | 0.73915 | 25742.6207 | 0.0002533 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5396 | 14 | 6.6231e-07 | 22721102 | SNEATH LANE 1102 | SNEATH LANE 1102circuit_breaker | 1789.3661 | 9.2723e-06 | 2693 | 1.1119 | 25743.7326 | 0.00024403 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 486 | 1 | 6.5519e-07 | 24031110 | BELMONT 1110 | BELMONT 11109090 | 0 | 6.5519e-07 | 2844 | 0 | 25743.7326 | 0.00024337 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 2477 | 2 | 6.2669e-07 | 12501113 | EL CERRITO G 1113 | EL CERRITO G 1113circuit_breaker | 336.063 | 1.2534e-06 | 2825 | 0.20882 | 25743.9414 | 0.00024212 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 418 | 15 | 6.1289e-07 | 14091104 | CASTRO VALLEY 1104 | CASTRO VALLEY 1104MR236 | 1927.0653 | 9.1934e-06 | 2694 | 1.1974 | 25745.1388 | 0.00023292 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 7712 | 5 | 6.0933e-07 | 13921101 | FRANKLIN 1101 | FRANKLIN 1101P138 | 2364.7362 | 3.0467e-06 | 2775 | 1.4694 | 25746.6082 | 0.00022988 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 7348 | 50 | 6.0715e-07 | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012510 | 6780.2402 | 3.0357e-05 | 2544 | 4.213 | 25750.8213 | 0.00019952 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 6261 | 1 | 5.6516e-07 | 22721102 | SNEATH LANE 1102 | SNEATH LANE 110275844 | 184.0425 | 5.6516e-07 | 2845 | 0.11436 | 25750.9356 | 0.00019895 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 9903 | 1 | 5.6405e-07 | 252691104 | INDIAN FLAT 1104 | INDIAN FLAT 11044440 | 376.2849 | 5.6405e-07 | 2846 | 0.23381 | 25751.1694 | 0.00019839 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2660 | 8 | 5.6289e-07 | 182402107 | FORT ORD 2107 | FORT ORD 210736596 | 6277.7799 | 4.5031e-06 | 2752 | 3.9008 | 25755.0703 | 0.00019389 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1096 | 2 | 5.6263e-07 | 22721101 | SNEATH LANE 1101 | SNEATH LANE 110168070 | 175.9556 | 1.1253e-06 | 2831 | 0.10933 | 25755.1796 | 0.00019276 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 6179 | 10 | 5.5275e-07 | 102361101 | HAMILTON BRANCH 1101 | HAMILTON BRANCH 110153192 | 1145.8186 | 5.5275e-06 | 2737 | 0.71198 | 25755.8916 | 0.00018724 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Coast | 2576 | 1 | 5.0594e-07 | 182222102 | DEL MONTE 2102 | DEL MONTE 21029060 | 1038.0388 | 5.0594e-07 | 2847 | 0.64501 | 25756.5366 | 0.00018673 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 8203 | 6 | 4.5367e-07 | 152591101 | SUMMIT 1101 | SUMMIT 110186658 | 1026.4158 | 2.722e-06 | 2786 | 0.63779 | 25757.1744 | 0.00018401 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 7328 | 35 | 4.5126e-07 | 152591101 | SUMMIT 1101 | SUMMIT 110148632 | 4368.1754 | 1.5794e-05 | 2622 | 2.7143 | 25759.8886 | 0.00016821 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 5702 | 1 | 4.451e-07 | 22721101 | SNEATH LANE 1101 | SNEATH LANE 1101circuit_breaker | 448.9693 | 4.451e-07 | 2848 | 0.27898 | 25760.1676 | 0.00016777 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 9118 | 9 | 4.4281e-07 | 152591101 | SUMMIT 1101 | SUMMIT 11016627 | 903.7825 | 3.9853e-06 | 2762 | 0.56158 | 25760.7292 | 0.00016378 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1275 | 2 | 4.3004e-07 | 13030402 | BANCROFT 0402 | BANCROFT 0402circuit_breaker | 149.8171 | 8.6008e-07 | 2835 | 0.093092 | 25760.8223 | 0.00016292 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 5721 | 91 | 4.1162e-07 | 163692101 | SALT SPRINGS 2101 | SALT SPRINGS 21011232 | 10582.3145 | 3.7458e-05 | 2518 | 6.5755 | 25767.3978 | 0.00012546 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5537 | 2 | 4.1109e-07 | 152591101 | SUMMIT 1101 | SUMMIT 110148636 | 42.0553 | 8.2218e-07 | 2836 | 0.026132 | 25767.4239 | 0.00012464 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6917 | 8 | 3.8943e-07 | 152591101 | SUMMIT 1101 | SUMMIT 1101742 | 2091.8057 | 3.1154e-06 | 2772 | 1.2998 | 25768.7237 | 0.00012153 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7826 | 13 | 3.6857e-07 | 163692101 | SALT SPRINGS 2101 | SALT SPRINGS 21013116 | 1222.9143 | 4.7914e-06 | 2746 | 0.75988 | 25769.4836 | 0.00011674 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 5387 | 185 | 3.5676e-07 | 152291101 | TAMARACK 1101 | TAMARACK 1101circuit_breaker | 28053.5786 | 6.6001e-05 | 2442 | 17.4317 | 25786.9153 | 5.0734e-05 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 7363 | 68 | 3.5256e-07 | 163692101 | SALT SPRINGS 2101 | SALT SPRINGS 21014913 | 6222.6929 | 2.3974e-05 | 2575 | 3.8666 | 25790.7819 | 2.676e-05 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Sierra | 6918 | 13 | 3.2661e-07 | 152591101 | SUMMIT 1101 | SUMMIT 110158642 | 3078.8651 | 4.2459e-06 | 2755 | 1.9131 | 25792.695 | 2.2514e-05 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 2421 | 8 | 3.2221e-07 | 102361101 | HAMILTON BRANCH 1101 | HAMILTON BRANCH 110137436 | 951.9489 | 2.5776e-06 | 2791 | 0.59151 | 25793.2865 | 1.9937e-05 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 1305 | 1 | 3.1284e-07 | 24031110 | BELMONT 1110 | BELMONT 111039182 | 111.8017 | 3.1284e-07 | 2851 | 0.06947 | 25793.356 | 1.9624e-05 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 1985 | 42 | 2.8436e-07 | 254061103 | DUNLAP 1103 | DUNLAP 11037170 | 8635.1099 | 1.1943e-05 | 2658 | 5.3656 | 25798.7216 | 7.681e-06 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 4747 | 21 | 2.571e-07 | 103181102 | CHESTER 1102 | CHESTER 11022564 | 3485.5234 | 5.3991e-06 | 2740 | 2.1658 | 25800.8874 | 2.282e-06 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Bay Area | 4237 | 2 | 1.8035e-07 | 24031103 | BELMONT 1103 | BELMONT 11038956 | 228.0716 | 3.607e-07 | 2849 | 0.14172 | 25801.0291 | 1.9213e-06 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Valley | 5682 | 2 | 1.6079e-07 | 103181102 | CHESTER 1102 | CHESTER 1102circuit_breaker | 460.5923 | 3.2158e-07 | 2850 | 0.2862 | 25801.3153 | 1.5997e-06 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
Central Valley | 9477 | 11 | 1.4543e-07 | 254061102 | DUNLAP 1102 | DUNLAP 11027290 | 1178.1007 | 1.5997e-06 | 2819 | 0.73204 | 25802.0474 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9714 |  |  | 24181104 | SAN CARLOS 1104 | SAN CARLOS 11049048 | 24.5909 | 0 | 2911 | 0.01528 | 25802.0626 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7447 |  |  | 182391103 | OILFIELDS 1103 | OILFIELDS 11032757 | 4491.0736 | 0 | 3060 | 2.7906 | 25804.8533 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9001 |  |  | 254452101 | MARIPOSA 2101 | MARIPOSA 210190130 | 144.8101 | 0 | 3027 | 0.089981 | 25804.9432 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9068 |  |  | 252531101 | SAN JOAQUIN #3 1101 | SAN JOAQUIN #3 1101circuit_breaker | 8550.0082 | 0 | 3023 | 5.3127 | 25810.256 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9663 |  |  | 43201102 | STAFFORD 1102 | STAFFORD 1102784704 | 43.8835 | 0 | 2864 | 0.027268 | 25810.2832 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9393 |  |  | 12022215 | CLAYTON 2215 | CLAYTON 22159765 | 425.4979 | 0 | 2875 | 0.26439 | 25810.5476 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9758 |  |  | 42711102 | CALISTOGA 1102 | CALISTOGA 110266730 | 1883.757 | 0 | 2907 | 1.1705 | 25811.7181 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7313 |  |  | 63642106 | PEABODY 2106 | PEABODY 2106circuit_breaker | 1514.2978 | 0 | 3066 | 0.94094 | 25812.6591 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9918 |  |  | 162831702 |  | 188426 | 4.572 | 0 | 2885 | 0.0028409 | 25812.6619 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9400 |  |  | 253642103 | POSO MOUNTAIN 2103 | POSO MOUNTAIN 2103circuit_breaker | 3720.379 | 0 | 2854 | 2.3117 | 25814.9737 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 10004 |  |  | 158041101 | WASHINGTON CITY GEN. 1101 | WASHINGTON CITY GEN. 1101circuit_breaker | 20.3534 | 0 | 2896 | 0.012647 | 25814.9863 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9403 |  |  | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 21023118 | 115.8501 | 0 | 2877 | 0.071986 | 25815.0583 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9683 |  |  | 182611103 | PASO ROBLES 1103 | PASO ROBLES 1103N02 | 70.9341 | 0 | 2862 | 0.044076 | 25815.1024 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9410 |  |  | 43071101 | DUNBAR 1101 | DUNBAR 110113481 | 0 | 0 | 2855 | 0 | 25815.1024 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9735 |  |  | 12061105 | BERKELEY F 1105 | BERKELEY F 1105BR166 | 61.4345 | 0 | 2905 | 0.038174 | 25815.1405 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 8116 |  |  | 42631108 | PETALUMA C 1108 | PETALUMA C 1108636 | 14844.2499 | 0 | 3005 | 9.2238 | 25824.3643 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9794 |  |  | 43211101 | HARTLEY 1101 | HARTLEY 110158095 | 251.9158 | 0 | 2910 | 0.15653 | 25824.5209 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 8946 |  |  | 103261101 | ANDERSON 1101 | ANDERSON 11011390 | 15.3102 | 0 | 3029 | 0.0095133 | 25824.5304 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7241 |  |  | 182631107 | SAN LUIS OBISPO 1107 | SAN LUIS OBISPO 1107V58 | 1708.3239 | 0 | 3068 | 1.0615 | 25825.5919 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7133 |  |  | 153652105 | SHINGLE SPRINGS 2105 | SHINGLE SPRINGS 210551738 | 26.6806 | 0 | 3070 | 0.016579 | 25825.6085 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9937 |  |  | 182611103 | PASO ROBLES 1103 | PASO ROBLES 1103N04 | 858.0287 | 0 | 2892 | 0.53315 | 25826.1416 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 10128 |  |  | 158011101 | SIERRA CITY GEN 1101 | SIERRA CITY GEN 11011101/2 | 8.5137 | 0 | 2868 | 0.0052902 | 25826.1469 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9987 |  |  | 182581105 | GOLDTREE 1105 | GOLDTREE 1105551904 | 35.7177 | 0 | 2897 | 0.022194 | 25826.1691 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 10133 |  |  | 48011146 | CALPINE 1146 | CALPINE 1146394G | 18.1683 | 0 | 2874 | 0.011289 | 25826.1804 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9654 |  |  | 103221101 | KANAKA 1101 | KANAKA 11011036 | 979.1369 | 0 | 2870 | 0.60841 | 25826.7888 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 8404 |  |  | 42091102 | MIRABEL 1102 | MIRABEL 110213597 | 625.9642 | 0 | 3036 | 0.38896 | 25827.1777 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9681 |  |  | 182611103 | PASO ROBLES 1103 | PASO ROBLES 1103451760 | 82.4454 | 0 | 2863 | 0.051229 | 25827.229 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9441 |  |  | 102781101 | ELK CREEK 1101 | ELK CREEK 1101circuit_breaker | 130.7379 | 0 | 2913 | 0.081237 | 25827.3102 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9704 |  |  | 12501105 | EL CERRITO G 1105 | EL CERRITO G 1105BR164 | 91.5845 | 0 | 2861 | 0.056908 | 25827.3671 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 8335 |  |  | 152481104 | BRUNSWICK 1104 | BRUNSWICK 11047181 | 1196.7092 | 0 | 3038 | 0.7436 | 25828.1107 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7745 |  |  | 182082103 | LOS OSITOS 2103 | LOS OSITOS 21037062 | 19658.415 | 0 | 3015 | 12.2152 | 25840.3259 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9450 |  |  | 153612103 | CLARKSVILLE 2103 | CLARKSVILLE 2103circuit_breaker | 239.3697 | 0 | 2891 | 0.14874 | 25840.4746 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7381 |  |  | 43061101 | COVELO 1101 | COVELO 110137328 | 6550.0939 | 0 | 3063 | 4.07 | 25844.5447 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 10158 |  |  | 189001101 | DIABLO CANYON 1101 | DIABLO CANYON 1101circuit_breaker | 0 | 0 | 2856 | 0 | 25844.5447 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9098 |  |  | 255292108 | WOODWARD 2108 | WOODWARD 2108688294 | 24.3604 | 0 | 3021 | 0.015137 | 25844.5598 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 8689 |  |  | 14671103 | SOBRANTE 1103 | SOBRANTE 1103N510R | 404.6092 | 0 | 3034 | 0.25141 | 25844.8112 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 8771 |  |  | 14091108 | CASTRO VALLEY 1108 | CASTRO VALLEY 1108MR525 | 98.2491 | 0 | 3032 | 0.061049 | 25844.8723 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7967 |  |  | 42851121 | FORT ROSS 1121 | FORT ROSS 1121204 | 30176.1504 | 0 | 3008 | 18.7506 | 25863.6229 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7180 |  |  | 42661102 | WILLITS 1102 | WILLITS 11021270 | 0 | 0 | 3059 | 0 | 25863.6229 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7710 |  |  | 24251101 | WOODSIDE 1101 | WOODSIDE 1101circuit_breaker | 16.0021 | 0 | 3017 | 0.0099432 | 25863.6328 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7357 |  |  | 182391103 | OILFIELDS 1103 | OILFIELDS 11035175 | 3372.5858 | 0 | 3064 | 2.0956 | 25865.7284 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9905 |  |  | 82831109 | MILPITAS 1109 | MILPITAS 110962157 | 72.1015 | 0 | 2883 | 0.044802 | 25865.7732 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7326 |  |  | 182581107 | GOLDTREE 1107 | GOLDTREE 1107circuit_breaker | 1525.8896 | 0 | 3065 | 0.94814 | 25866.7214 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9928 |  |  | 158011101 | SIERRA CITY GEN 1101 | SIERRA CITY GEN 1101circuit_breaker | 21.2814 | 0 | 2881 | 0.013224 | 25866.7346 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9035 |  |  | 152582109 | DEL MAR 2109 | DEL MAR 210938684 | 0 | 0 | 3025 | 0 | 25866.7346 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9948 |  |  | 12541104 | OAKLAND X 1104 | OAKLAND X 1104CR101 | 28.3921 | 0 | 2893 | 0.017642 | 25866.7522 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 8019 |  |  | 14592105 | BRENTWOOD 2105 | BRENTWOOD 2105502672 | 1990.2405 | 0 | 3006 | 1.2367 | 25867.9889 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9092 |  |  | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210595050 | 223.2117 | 0 | 3022 | 0.1387 | 25868.1276 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9490 |  |  | 188881701 |  | circuit_breaker | 168.4127 | 0 | 2917 | 0.10465 | 25868.2323 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9990 |  |  | 182402106 | FORT ORD 2106 | FORT ORD 21069656 | 188.9883 | 0 | 2899 | 0.11743 | 25868.3497 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 8702 |  |  | 252021101 | ANTELOPE 1101 | ANTELOPE 11011631 | 1210.7069 | 0 | 3033 | 0.7523 | 25869.102 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7587 |  |  | 43291105 | PUEBLO 1105 | PUEBLO 11053022 | 238.6731 | 0 | 3030 | 0.1483 | 25869.2503 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9337 |  |  | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 1105990354 | 6.5127 | 0 | 2853 | 0.0040468 | 25869.2543 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9662 |  |  | 258131101 | SCE TEHACHAPI 1101 | SCE TEHACHAPI 1101circuit_breaker | 1862.134 | 0 | 2852 | 1.1571 | 25870.4114 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7896 |  |  | 152481110 | BRUNSWICK 1110 | BRUNSWICK 1110circuit_breaker | 6.096 | 0 | 3013 | 0.0037879 | 25870.4152 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 8272 |  |  | 102601101 | GLENN 1101 | GLENN 11012012 | 480.0698 | 0 | 3002 | 0.2983 | 25870.7135 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9502 |  |  | 103331101 | CORNING 1101 | CORNING 110135974 | 114.0493 | 0 | 2914 | 0.070867 | 25870.7844 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 8310 |  |  | 102541101 | VOLTA 1101 | VOLTA 1101circuit_breaker | 14809.7042 | 0 | 3001 | 9.2023 | 25879.9867 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9209 |  |  | 102911103 | WYANDOTTE 1103 | WYANDOTTE 110366146 | 252.3083 | 0 | 2859 | 0.15678 | 25880.1435 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 8157 |  |  | 182601103 | OCEANO 1103 | OCEANO 110376678 | 88.7522 | 0 | 3003 | 0.055148 | 25880.1986 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9519 |  |  | 42631109 | PETALUMA C 1109 | PETALUMA C 1109664732 | 1437.8147 | 0 | 2904 | 0.89342 | 25881.092 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7406 |  |  | 42481105 |  | 908 | 1022.6867 | 0 | 3061 | 0.63547 | 25881.7275 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7009 |  |  | 182981102 | JOLON 1102 | JOLON 11027004 | 8688.0359 | 0 | 3072 | 5.3985 | 25887.126 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9721 |  |  | 182631107 | SAN LUIS OBISPO 1107 | SAN LUIS OBISPO 1107V08 | 39.9511 | 0 | 2902 | 0.024824 | 25887.1508 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9031 |  |  | 14232103 | SAN RAMON 2103 | SAN RAMON 2103MR279 | 4.572 | 0 | 3026 | 0.0028409 | 25887.1537 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7042 |  |  | 43501103 |  | circuit_breaker | 0 | 0 | 3071 | 0 | 25887.1537 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7391 |  |  | 183221111 | TRES PINOS 1111 | TRES PINOS 11114032 | 0 | 0 | 3062 | 0 | 25887.1537 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 8333 |  |  | 14232101 | SAN RAMON 2101 | SAN RAMON 2101circuit_breaker | 940.3742 | 0 | 3010 | 0.58432 | 25887.738 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7902 |  |  | 43061101 | COVELO 1101 | COVELO 110196896 | 5810.2676 | 0 | 3012 | 3.6103 | 25891.3483 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9047 |  |  | 182082103 | LOS OSITOS 2103 | LOS OSITOS 21037468 | 736.8159 | 0 | 3024 | 0.45784 | 25891.8061 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9340 |  |  | 42561102 | FULTON 1102 | FULTON 110258990 | 0 | 0 | 2871 | 0 | 25891.8061 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9770 |  |  | 163661701 | MIWUK 1701 | MIWUK 170179118 | 31.1564 | 0 | 2908 | 0.01936 | 25891.8255 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7668 |  |  | 14232107 | SAN RAMON 2107 | SAN RAMON 2107MR441 | 40.2016 | 0 | 3018 | 0.02498 | 25891.8505 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9776 |  |  | 14232102 | SAN RAMON 2102 | SAN RAMON 2102circuit_breaker | 2478.2008 | 0 | 2909 | 1.5399 | 25893.3904 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9561 |  |  | 158001101 | DOWNIEVILLE DIESEL 1101 | DOWNIEVILLE DIESEL 1101circuit_breaker | 36.9839 | 0 | 2869 | 0.022981 | 25893.4133 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9803 |  |  | 14241101 | SUNOL 1101 | SUNOL 110148180 | 13.6404 | 0 | 2912 | 0.0084757 | 25893.4218 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9275 |  |  | 43051101 | MONTICELLO 1101 | MONTICELLO 11011780 | 105.9265 | 0 | 2900 | 0.06582 | 25893.4876 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9837 |  |  | 14091108 | CASTRO VALLEY 1108 | CASTRO VALLEY 11087742 | 4.5721 | 0 | 2916 | 0.002841 | 25893.4905 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9578 |  |  | 253642101 | POSO MOUNTAIN 2101 | POSO MOUNTAIN 21011703 | 1455.5285 | 0 | 2867 | 0.90442 | 25894.3949 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9849 |  |  | 152531102 | FLINT 1102 | FLINT 1102circuit_breaker | 149.4178 | 0 | 2918 | 0.092844 | 25894.4878 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 10125 |  |  | 153132104 | NARROWS 2104 | NARROWS 2104circuit_breaker | 4.572 | 0 | 2866 | 0.0028409 | 25894.4906 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9864 |  |  | 48011144 | CALPINE 1144 | CALPINE 1144962 | 6465.1165 | 0 | 2920 | 4.0172 | 25898.5078 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 10038 |  |  | 158031101 | ECHO SUMMIT 1101 | ECHO SUMMIT 1101circuit_breaker | 49.1761 | 0 | 2890 | 0.030557 | 25898.5384 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9197 |  |  | 42821102 | CLOVERDALE 1102 | CLOVERDALE 110247214 | 43.972 | 0 | 3069 | 0.027323 | 25898.5657 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 10071 |  |  | 48011144 | CALPINE 1144 | CALPINE 1144276-G | 23.7478 | 0 | 2889 | 0.014756 | 25898.5805 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9904 |  |  | 183041101 | BUELLTON 1101 | BUELLTON 110163389 | 0 | 0 | 2882 | 0 | 25898.5805 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 10077 |  |  | 43361101 | HIGHLANDS 1101 | HIGHLANDS 1101circuit_breaker | 42.5019 | 0 | 2886 | 0.026409 | 25898.6069 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9906 |  |  | 42631109 | PETALUMA C 1109 | PETALUMA C 1109373772 | 28.6691 | 0 | 2884 | 0.017814 | 25898.6247 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7938 |  |  | 182611107 | PASO ROBLES 1107 | PASO ROBLES 1107circuit_breaker | 447.6357 | 0 | 3009 | 0.27815 | 25898.9028 | -2.7536e-12 | 0.64659 | 0 | 1 | #N/A | -2.7536e-12 | #N/A
| 9927 |  |  | 103611101 | WILDWOOD 1101 | WILDWOOD 1101circuit_breaker | 96.3625 | 0 | 2887 | 0.059877 | 25898.9627 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7005 |  |  | 152591101 | SUMMIT 1101 | SUMMIT 1101circuit_breaker | 200.821 | 0 | 3073 | 0.12478 | 25899.0875 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 8915 |  |  | 182981102 | JOLON 1102 | JOLON 11027068 | 5962.9889 | 0 | 3031 | 3.7052 | 25902.7927 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9344 |  |  | 152251101 | SPAULDING 1101 | SPAULDING 1101circuit_breaker | 56.7484 | 0 | 2880 | 0.035262 | 25902.828 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 8920 |  |  | 14592105 | BRENTWOOD 2105 | BRENTWOOD 21056512 | 1047.7996 | 0 | 3020 | 0.65107 | 25903.4791 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 8959 |  |  | 152261106 | DIAMOND SPRINGS 1106 | DIAMOND SPRINGS 1106176130 | 32.0737 | 0 | 3028 | 0.01993 | 25903.499 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9963 |  |  | 183111102 | CMC 1102 | CMC 1102circuit_breaker | 590.8612 | 0 | 2894 | 0.36714 | 25903.8661 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9347 |  |  | 183111101 | CMC 1101 | CMC 1101circuit_breaker | 3293.5334 | 0 | 2872 | 2.0465 | 25905.9126 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 8351 |  |  | 12501110 | EL CERRITO G 1110 | EL CERRITO G 1110BR236 | 784.0637 | 0 | 3037 | 0.48719 | 25906.3998 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7742 |  |  | 163201101 | WEST POINT 1101 | WEST POINT 1101L1969 | 1741.0416 | 0 | 3016 | 1.0818 | 25907.4817 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9986 |  |  | 48011146 | CALPINE 1146 | CALPINE 1146200-G | 13.7161 | 0 | 2895 | 0.0085228 | 25907.4902 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9625 |  |  | 48011144 | CALPINE 1144 | CALPINE 1144962 | 63.3636 | 0 | 2873 | 0.039372 | 25907.5296 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9989 |  |  | 188071101 | SCE REFUGIO 1101 | SCE REFUGIO 1101circuit_breaker | 3.6129 | 0 | 2903 | 0.0022449 | 25907.5318 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7912 |  |  | 63172101 | MADISON 2101 | MADISON 21011969 | 200.8341 | 0 | 3000 | 0.12479 | 25907.6566 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9995 |  |  | 82931101 | POINT MORETTI 1101 | POINT MORETTI 1101circuit_breaker | 20.574 | 0 | 2898 | 0.012784 | 25907.6694 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7970 |  |  | 83392109 | SWIFT 2109 | SWIFT 2109XR300 | 121.3159 | 0 | 3007 | 0.075382 | 25907.7448 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7305 |  |  | 183031101 | PALMER 1101 | PALMER 1101M88 | 3785.6453 | 0 | 3067 | 2.3523 | 25910.0971 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9646 |  |  | 103321101 | CEDAR CREEK 1101 | CEDAR CREEK 11011362 | 24.9515 | 0 | 2879 | 0.015504 | 25910.1126 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9648 |  |  | 182402106 | FORT ORD 2106 | FORT ORD 21069658 | 156.0125 | 0 | 2876 | 0.096942 | 25910.2095 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 10074 |  |  | 158001101 | DOWNIEVILLE DIESEL 1101 | DOWNIEVILLE DIESEL 11011101/2 | 15.6648 | 0 | 2888 | 0.0097337 | 25910.2192 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 10104 |  |  | 103451101 | KESWICK 1101 | KESWICK 1101circuit_breaker | 26.6683 | 0 | 2915 | 0.016571 | 25910.2358 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 10095 |  |  | 48011144 | CALPINE 1144 | CALPINE 1144304 | 74.6067 | 0 | 2919 | 0.046358 | 25910.2822 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 10114 |  |  | 153132105 | NARROWS 2105 | NARROWS 21052214 | 4.5721 | 0 | 2906 | 0.0028409 | 25910.285 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 10123 |  |  | 254421103 | OAKHURST 1103 | OAKHURST 110310723 | 6.3415 | 0 | 2860 | 0.0039404 | 25910.2889 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7908 |  |  | 42491101 | SAUSALITO 1101 | SAUSALITO 11011270 | 817.322 | 0 | 3011 | 0.50786 | 25910.7968 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 10118 |  |  | 158041101 | WASHINGTON CITY GEN. 1101 | WASHINGTON CITY GEN. 11011101/2 | 5.7117 | 0 | 2857 | 0.0035491 | 25910.8004 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 8129 |  |  | 182391103 | OILFIELDS 1103 | OILFIELDS 1103N40 | 1192.0163 | 0 | 3004 | 0.74068 | 25911.541 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7848 |  |  | 43201102 | STAFFORD 1102 | STAFFORD 1102361952 | 2196.587 | 0 | 3014 | 1.3649 | 25912.9059 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9594 |  |  | 102911110 | WYANDOTTE 1110 | WYANDOTTE 11102590 | 0 | 0 | 2865 | 0 | 25912.9059 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9588 |  |  | 153081109 | PLACERVILLE 1109 | PLACERVILLE 1109circuit_breaker | 25.9925 | 0 | 2858 | 0.016151 | 25912.9221 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 10152 |  |  | 83622105 | CAMP EVERS 2105 | CAMP EVERS 2105BL 2101 | 5.191 | 0 | 2878 | 0.0032255 | 25912.9253 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 7590 |  |  | 43091101 | GREENBRAE 1101 | GREENBRAE 110182270 | 4.572 | 0 | 3019 | 0.0028409 | 25912.9282 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 9439 |  |  | 14662112 | TASSAJARA 2112 | TASSAJARA 21123202 | 628.2778 | 0 | 2901 | 0.39039 | 25913.3185 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 8654 |  |  | 252721106 | KERN OIL 1106 | KERN OIL 110646960 | 1285.0343 | 0 | 3035 | 0.79848 | 25914.117 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5737 |  |  | 24141102 | RALSTON 1102 | RALSTON 1102circuit_breaker | 1520.1281 | 0 | 3052 | 0.94456 | 25915.0616 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5746 |  |  | 14662104 | TASSAJARA 2104 | TASSAJARA 2104circuit_breaker | 118.3029 | 0 | 3051 | 0.07351 | 25915.1351 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5900 |  |  | 182391103 | OILFIELDS 1103 | OILFIELDS 1103N64 | 16233.6548 | 0 | 3048 | 10.0871 | 25925.2222 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 6335 |  |  | 83192101 | GREEN VALLEY 2101 | GREEN VALLEY 210112824 | 107.6616 | 0 | 3043 | 0.066898 | 25925.2891 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 6911 |  |  | 182391103 | OILFIELDS 1103 | OILFIELDS 1103N42 | 4452.4168 | 0 | 3074 | 2.7666 | 25928.0557 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 6363 |  |  | 14232117 | SAN RAMON 2117 | SAN RAMON 2117circuit_breaker | 735.1259 | 0 | 3042 | 0.45679 | 25928.5125 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5861 |  |  | 192381102 | EEL RIVER 1102 | EEL RIVER 110249130 | 2552.3517 | 0 | 3039 | 1.586 | 25930.0985 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5219 |  |  | 43211101 | HARTLEY 1101 | HARTLEY 1101471 | 134.4299 | 0 | 2943 | 0.083531 | 25930.182 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 4873 |  |  | 13921104 | FRANKLIN 1104 | FRANKLIN 1104circuit_breaker | 233.9749 | 0 | 2949 | 0.14539 | 25930.3274 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 6212 |  |  | 43201102 | STAFFORD 1102 | STAFFORD 11021048 | 8411.3678 | 0 | 3045 | 5.2266 | 25935.554 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5196 |  |  | 14662109 | TASSAJARA 2109 | TASSAJARA 2109circuit_breaker | 1458.9789 | 0 | 2944 | 0.90657 | 25936.4605 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5126 |  |  | 162821702 | STANISLAUS 1702 | STANISLAUS 1702L611 | 4813.9395 | 0 | 2947 | 2.9912 | 25939.4518 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5152 |  |  | 252841102 | OROSI 1102 | OROSI 11027948F | 423.4544 | 0 | 2946 | 0.26312 | 25939.7149 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 6633 |  |  | 253911102 | LAMONT 1102 | LAMONT 11024222 | 805.2366 | 0 | 3076 | 0.50035 | 25940.2152 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 6717 |  |  | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 110376762 | 0 | 0 | 3075 | 0 | 25940.2152 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 4674 |  |  | 24141102 | RALSTON 1102 | RALSTON 11029126 | 1709.1714 | 0 | 2953 | 1.062 | 25941.2773 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5482 |  |  | 183011102 | MORRO BAY 1102 | MORRO BAY 1102V80 | 18.5609 | 0 | 3057 | 0.011533 | 25941.2888 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5309 |  |  | 182852204 | VIEJO 2204 | VIEJO 22049440 | 10.1911 | 0 | 2991 | 0.0063324 | 25941.2951 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5253 |  |  | 63171105 | MADISON 1105 | MADISON 11057712 | 630.6114 | 0 | 2942 | 0.39184 | 25941.687 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 6226 |  |  | 43381101 | POINT ARENA 1101 | POINT ARENA 11013702 | 7868.7714 | 0 | 3044 | 4.8894 | 25946.5764 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 4593 |  |  | 162671103 | WESTLEY 1103 | WESTLEY 11039010 | 1485.982 | 0 | 2955 | 0.92335 | 25947.4998 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 6387 |  |  | 83432103 | HICKS 2103 | HICKS 2103XR248 | 124.695 | 0 | 3040 | 0.077482 | 25947.5772 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 6444 |  |  | 163011102 | MARTELL 1102 | MARTELL 110292172 | 186.9738 | 0 | 3049 | 0.11618 | 25947.6934 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 4723 |  |  | 182601105 | OCEANO 1105 | OCEANO 1105V48 | 142.1722 | 0 | 2941 | 0.088342 | 25947.7818 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 4784 |  |  | 12660404 | BERKELEY T 0404 | BERKELEY T 0404circuit_breaker | 6.096 | 0 | 2950 | 0.0037879 | 25947.7855 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5400 |  |  | 42301101 | TULUCAY 1101 | TULUCAY 1101circuit_breaker | 121.1978 | 0 | 3058 | 0.075309 | 25947.8609 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 4721 |  |  | 14101102 | ALHAMBRA 1102 | ALHAMBRA 110213333 | 130.2273 | 0 | 2952 | 0.080919 | 25947.9418 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 4573 |  |  | 182852202 | VIEJO 2202 | VIEJO 220255787 | 58.9251 | 0 | 2956 | 0.036614 | 25947.9784 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 6003 |  |  | 42761102 | FORT BRAGG A 1102 | FORT BRAGG A 110233064 | 0 | 0 | 3046 | 0 | 25947.9784 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5756 |  |  | 42011107 | SAN RAFAEL 1107 | SAN RAFAEL 1107434 | 4.572 | 0 | 3050 | 0.0028409 | 25947.9812 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5688 |  |  | 12350401 | ORINDA 0401 | ORINDA 0401circuit_breaker | 160.4005 | 0 | 3053 | 0.099668 | 25948.0809 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5100 |  |  | 103491101 | MC ARTHUR 1101 | MC ARTHUR 110137344 | 181.3406 | 0 | 2948 | 0.11268 | 25948.1936 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5604 |  |  | 252941107 | TIVY VALLEY 1107 | TIVY VALLEY 110737522 | 731.9163 | 0 | 3054 | 0.45479 | 25948.6484 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5908 |  |  | 82952113 | EDENVALE 2113 | EDENVALE 2113circuit_breaker | 24.568 | 0 | 3047 | 0.015266 | 25948.6636 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5528 |  |  | 83392107 | SWIFT 2107 | SWIFT 2107XR526 | 3165.9502 | 0 | 3055 | 1.9672 | 25950.6309 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5514 |  |  | 42631108 | PETALUMA C 1108 | PETALUMA C 1108628 | 14935.6028 | 0 | 3056 | 9.2806 | 25959.9114 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 6474 |  |  | 183011101 | MORRO BAY 1101 | MORRO BAY 1101W04 | 0 | 0 | 3077 | 0 | 25959.9114 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 5181 |  |  | 182631104 | SAN LUIS OBISPO 1104 | SAN LUIS OBISPO 1104circuit_breaker | 889.5466 | 0 | 2945 | 0.55274 | 25960.4642 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 6367 |  |  | 162821702 | STANISLAUS 1702 | STANISLAUS 1702L5381 | 1946.774 | 0 | 3041 | 1.2097 | 25961.6738 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 4622 |  |  | 42011106 | SAN RAFAEL 1106 | SAN RAFAEL 110668694 | 0 | 0 | 2954 | 0 | 25961.6738 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 2596 |  |  | 22721106 | SNEATH LANE 1106 | SNEATH LANE 11061339 | 0 | 0 | 2988 | 0 | 25961.6738 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 2444 |  |  | 192381102 | EEL RIVER 1102 | EEL RIVER 1102530 | 8758.0357 | 0 | 2992 | 5.442 | 25967.1158 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 3390 |  |  | 182391103 | OILFIELDS 1103 | OILFIELDS 11037006 | 5321.5914 | 0 | 2934 | 3.3067 | 25970.4225 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 2676 |  |  | 182631101 | SAN LUIS OBISPO 1101 | SAN LUIS OBISPO 1101592368 | 0 | 0 | 2985 | 0 | 25970.4225 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 3048 |  |  | 14452104 | KIRKER 2104 | KIRKER 2104circuit_breaker | 74.5132 | 0 | 2939 | 0.0463 | 25970.4688 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 4130 |  |  | 42721104 | SONOMA 1104 | SONOMA 1104914376 | 702.83 | 0 | 2923 | 0.43672 | 25970.9055 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 3647 |  |  | 83371103 | SARATOGA 1103 | SARATOGA 1103LC82 | 4.8945 | 0 | 2928 | 0.0030413 | 25970.9086 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 3019 |  |  | 83371103 | SARATOGA 1103 | SARATOGA 1103LC40 | 438.1448 | 0 | 2951 | 0.27225 | 25971.1808 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 4309 |  |  | 42721105 | SONOMA 1105 | SONOMA 1105138 | 615.5192 | 0 | 2960 | 0.38247 | 25971.5633 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 2720 |  |  | 182581108 | GOLDTREE 1108 | GOLDTREE 1108circuit_breaker | 3288.9555 | 0 | 2983 | 2.0437 | 25973.6069 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 2831 |  |  | 13912108 | WILLOW PASS 2108 | WILLOW PASS 2108circuit_breaker | 235.7533 | 0 | 2982 | 0.14649 | 25973.7534 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 3104 |  |  | 42271103 | COTATI 1103 | COTATI 1103252 | 0 | 0 | 2938 | 0 | 25973.7534 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 2715 |  |  | 14341105 | VALLEY VIEW 1105 | VALLEY VIEW 1105P124 | 0 | 0 | 2984 | 0 | 25973.7534 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 3577 |  |  | 252721106 | KERN OIL 1106 | KERN OIL 11063301 | 657.9886 | 0 | 2930 | 0.40886 | 25974.1623 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 4467 |  |  | 253642101 | POSO MOUNTAIN 2101 | POSO MOUNTAIN 2101circuit_breaker | 6924.1001 | 0 | 2957 | 4.3024 | 25978.4647 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 2590 |  |  | 103491101 | MC ARTHUR 1101 | MC ARTHUR 110153120 | 0 | 0 | 2989 | 0 | 25978.4647 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 3225 |  |  | 43051101 | MONTICELLO 1101 | MONTICELLO 11011589 | 6934.0024 | 0 | 2937 | 4.3086 | 25982.7733 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 4117 |  |  | 182331101 | GABILAN 1101 | GABILAN 11013722 | 1147.7092 | 0 | 2924 | 0.71315 | 25983.4865 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 4154 |  |  | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110378862 | 423.5836 | 0 | 2922 | 0.2632 | 25983.7497 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 3874 |  |  | 182082103 | LOS OSITOS 2103 | LOS OSITOS 21037082 | 1889.198 | 0 | 2925 | 1.1739 | 25984.9236 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 3835 |  |  | 42631109 | PETALUMA C 1109 | PETALUMA C 1109circuit_breaker | 1526.3367 | 0 | 2926 | 0.94842 | 25985.872 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 2626 |  |  | 43091103 | GREENBRAE 1103 | GREENBRAE 11037315 | 0 | 0 | 2987 | 0 | 25985.872 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 4373 |  |  | 182852201 | VIEJO 2201 | VIEJO 22019704 | 786.5986 | 0 | 2958 | 0.48877 | 25986.3607 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 2673 |  |  | 182981102 | JOLON 1102 | JOLON 11027002 | 11843.464 | 0 | 2986 | 7.3592 | 25993.7199 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 3245 |  |  | 83182101 | LLAGAS 2101 | LLAGAS 2101XR244 | 321.7387 | 0 | 2936 | 0.19992 | 25993.9198 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 3532 |  |  | 83192101 | GREEN VALLEY 2101 | GREEN VALLEY 210190860 | 5419.4084 | 0 | 2933 | 3.3675 | 25997.2873 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 2578 |  |  | 253801101 | ARVIN 1101 | ARVIN 110194892 | 345.9853 | 0 | 2990 | 0.21499 | 25997.5023 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 3553 |  |  | 24251104 | WOODSIDE 1104 | WOODSIDE 1104circuit_breaker | 246.681 | 0 | 2932 | 0.15328 | 25997.6556 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 3767 |  |  | 102931103 | COTTONWOOD 1103 | COTTONWOOD 1103circuit_breaker | 1201.9482 | 0 | 2927 | 0.74686 | 25998.4024 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 4316 |  |  | 14232119 | SAN RAMON 2119 | SAN RAMON 2119circuit_breaker | 757.1628 | 0 | 2959 | 0.47048 | 25998.8729 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 3286 |  |  | 42761104 | FORT BRAGG A 1104 | FORT BRAGG A 110436526 | 19.7226 | 0 | 2935 | 0.012255 | 25998.8852 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 3602 |  |  | 42991107 | LAS GALLINAS A 1107 | LAS GALLINAS A 1107554 | 200.8758 | 0 | 2929 | 0.12482 | 25999.01 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 3576 |  |  | 42721107 | SONOMA 1107 | SONOMA 1107294 | 321.4105 | 0 | 2921 | 0.19972 | 25999.2097 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 3036 |  |  | 42631108 | PETALUMA C 1108 | PETALUMA C 1108630 | 2581.7965 | 0 | 2940 | 1.6043 | 26000.814 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 4206 |  |  | 102911109 | WYANDOTTE 1109 | WYANDOTTE 11095973 | 0 | 0 | 2931 | 0 | 26000.814 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 2554 |  |  | 182551101 | CAYUCOS 1101 | CAYUCOS 11014701 | 3147.6745 | 0 | 2981 | 1.9559 | 26002.7698 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 1981 |  |  | 42631108 | PETALUMA C 1108 | PETALUMA C 1108296 | 23764.0701 | 0 | 2994 | 14.7663 | 26017.5361 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 1629 |  |  | 13532224 | LAKEWOOD 2224 | LAKEWOOD 2224W544R | 0 | 0 | 2996 | 0 | 26017.5361 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
North Coast | 1196 | 1 | 0 | 42761101 | FORT BRAGG A 1101 | FORT BRAGG A 1101circuit_breaker | 290.3604 | 0 | 2967 | 0.18042 | 26017.7166 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 461 |  |  | 182852203 | VIEJO 2203 | VIEJO 22039094 | 160.2742 | 0 | 2975 | 0.09959 | 26017.8161 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 1213 |  |  | 43201102 | STAFFORD 1102 | STAFFORD 11021019 | 191.5288 | 0 | 2966 | 0.11901 | 26017.9352 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 246 |  |  | 42151108 | SANTA ROSA A 1108 | SANTA ROSA A 1108626 | 219.1314 | 0 | 2978 | 0.13616 | 26018.0713 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 2087 |  |  | 182391103 | OILFIELDS 1103 | OILFIELDS 1103N44 | 28861.9134 | 0 | 2993 | 17.934 | 26036.0053 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 1007 |  |  | 182391103 | OILFIELDS 1103 | OILFIELDS 110383158 | 28457.0143 | 0 | 2970 | 17.6824 | 26053.6876 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 1192 |  |  | 82952107 | EDENVALE 2107 | EDENVALE 2107circuit_breaker | 293.9737 | 0 | 2968 | 0.18267 | 26053.8703 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 203 |  |  | 22811102 | PACIFICA 1102 | PACIFICA 110252715 | 0 | 0 | 2979 | 0 | 26053.8703 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 1178 |  |  | 43321102 | RINCON 1102 | RINCON 1102640 | 16.0031 | 0 | 2969 | 0.0099439 | 26053.8802 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 384 |  |  | 42631108 | PETALUMA C 1108 | PETALUMA C 110856774 | 259.5884 | 0 | 2977 | 0.1613 | 26054.0415 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 1370 |  |  | 43061101 | COVELO 1101 | COVELO 1101562360 | 3783.6743 | 0 | 2963 | 2.3511 | 26056.3926 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 657 |  |  | 183101103 | CABRILLO 1103 | CABRILLO 1103circuit_breaker | 423.065 | 0 | 2972 | 0.26288 | 26056.6555 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 873 |  |  | 42721104 | SONOMA 1104 | SONOMA 1104414 | 669.1199 | 0 | 2961 | 0.41577 | 26057.0713 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 1372 |  |  | 103481101 | LOS MOLINOS 1101 | LOS MOLINOS 11011308 | 205.1097 | 0 | 2962 | 0.12745 | 26057.1987 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 1587 |  |  | 83252105 | PAUL SWEET 2105 | PAUL SWEET 210510290 | 4.572 | 0 | 2998 | 0.0028409 | 26057.2016 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 1298 |  |  | 42721105 | SONOMA 1105 | SONOMA 11054456 | 2092.6975 | 0 | 2964 | 1.3003 | 26058.5019 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 504 |  |  | 12091116 | OAKLAND J 1116 | OAKLAND J 1116circuit_breaker | 0 | 0 | 2974 | 0 | 26058.5019 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 401 |  |  | 82831108 | MILPITAS 1108 | MILPITAS 1108XR122 | 49.0072 | 0 | 2976 | 0.030452 | 26058.5323 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 1657 |  |  | 102812101 | BIG MEADOWS 2101 | BIG MEADOWS 21012016 | 20.5741 | 0 | 2995 | 0.012784 | 26058.5451 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 647 |  |  | 12501112 | EL CERRITO G 1112 | EL CERRITO G 1112BR196 | 68.9404 | 0 | 2973 | 0.042838 | 26058.588 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 1383 |  |  | 182131104 | GONZALES 1104 | GONZALES 110422418 | 1354.2941 | 0 | 2971 | 0.84152 | 26059.4295 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 1606 |  |  | 182151101 | LOS COCHES 1101 | LOS COCHES 1101circuit_breaker | 3722.9416 | 0 | 2997 | 2.3133 | 26061.7428 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 1457 |  |  | 43201102 | STAFFORD 1102 | STAFFORD 11021258 | 110.3452 | 0 | 2999 | 0.068565 | 26061.8114 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 11 |  |  | 182611103 | PASO ROBLES 1103 | PASO ROBLES 1103N50 | 3452.721 | 0 | 2980 | 2.1454 | 26063.9568 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
| 1267 |  |  | 192381103 | EEL RIVER 1103 | EEL RIVER 1103circuit_breaker | 0 | 0 | 2965 | 0 | 26063.9568 | -2.7536e-12 | #N/A | #N/A | 1 | #N/A | #N/A | #N/A
[6 empty] | Totals: | 41945885.4693 | 5408.3373 |  | 26063.9568 |  |  | 1749.0078 | 1451.4964

## GRID_DATA_sorted (hidden)
REGION | DIVISION | CIRCUITNAME | PZ_IDX | CIRCUIT_PR | TOTAL_GRID_mavf_core_risk | GRID_RISK_AREA_SQHM | TOTAL_MILES | COMPLETED_MILES | REMAINING_MILES | INSPECTED_MILES | ST_COUNT | ACTUAL_TREE_COUNT | ACTUAL_TREE_WORK | ACTUAL_TREE_WORK_REMOVAL | COMPLETED_TREE_WORK | COMPLETED_TREE_WORK_REMOVAL | REMAINING_CS_REFUSALS | REMAINING_CS_COUNT | REMAINING_FACTOR | EST_TREE_COUNT | EST_TREE_PI | EST_TREE_WORK | EST_REMOVAL | EST_REMAINING_TREE_PI | EST_REMAINING_TREE_WORK | EST_REMAINING_REMOVAL | EST_COST_TO_COMPLETE_KDOL | ZONE_RISK_INTENSITY_FACTOR | TW_ADJ_GRID_RISK | AVG_MAVF_CORE_RISK_RANK_RN | Total CPZ Risk | mean_mavf_core | CPZ_EXCLUSION | CARRY_OVER_KEEP | TARGET_LIST | MUST_KEEP | MK_TW_MI_Target_TWRank | WGC_Approved_Plan | 2021 | 2022 | 2023 | Unconstrained_EVM_RR | Unconstrained_Dx_RR | RISK_GROUP_Dx | RISK_GROUP_EVM | RISK_VALUE_ADDRESSED | Remain TW Per Mi | TW per Mi | Percent_Completed
Central Coast | LP_Los Padres | ZACA 1102 | 8297 | SANTA YNEZ 1104circuit_breaker | 5.0946 | 18.0528 | 1.0943 | 0 | 1.0943 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1 | 99 |  | 20 | 14 | 99 | 20 | 14 | 36.31 | 0.28221 | 0.01174 | 1 | 1.0291 | 0.51453 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 4. >30 - 40% | 1.0291 | 18.2762 | 18.2762 | 0%
Sierra | SA_Sacramento | PUTAH CREEK 1103 | 8244 | PUTAH CREEK 11033783 | 3.1038 | 8.3543 | 0.28163 | 0.28163 | 0 | 0.28163 | 6 | 32 | 12 | 10 | 12 | 10 | 0 | 8 | 0 | 32 |  | 12 | 10 | 0 | 0 | 0 | 0 | 0.37152 | 0 | 2 | 0.82757 | 0.41379 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0 | 0 | 42.6093 | 100%
North Coast | HU_Humboldt | WILLITS 1103 | 6700 | WILLITS 1103966 | 5.1853 | 9.5799 | 0.3892 | 0 | 0.3892 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 98 |  | 20 | 14 | 98 | 20 | 14 | 36.22 | 0.54127 | 0.02251 | 3 | 3.5574 | 0.39527 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1. <= 10% | 3. >20 - 30% | 3.5574 | 51.3869 | 51.3869 | 0%
Sierra | SA_Sacramento | VACA DIXON 1105 | 4403 | VACA DIXON 110540092 | 150.2157 | 589.0281 | 24.8036 | 0 | 24.8036 | 0.054735 | 912 | 1 | 0 | 0 | 0 | 0 | 0 | 494 | 0.99779 | 1666 |  | 302 | 200 | 1665 | 302 | 200 | 563.59 | 0.25502 | 0.16015 | 4 | 57.9125 | 0.29397 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 57.9125 | 12.1757 | 12.1757 | 0%
Sierra | SA_Sacramento | PUTAH CREEK 1102 | 7064 | PUTAH CREEK 110246012 | 4.6885 | 15.1449 | 0.76742 | 0.48485 | 0.28258 | 0.76742 | 40 | 219 | 83 | 65 | 63 | 47 | 0 | 29 | 0 | 219 |  | 83 | 65 | 0 | 20 | 18 | 27.4 | 0.30957 | 0.01287 | 5 | 2.044 | 0.292 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 0.75262 | 70.7775 | 108.154 | 63.18%
Sierra | SA_Sacramento | MADISON 2101 | 6204 | MADISON 21011975 | 1.2028 | 7.7589 | 0.075 | 0 | 0.075 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 16 |  | 5 | 4 | 16 | 5 | 4 | 8.29 | 0.15503 | 0.00161 | 6 | 0.54719 | 0.2736 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1. <= 10% | 6. >50% | 0.54719 | 66.6667 | 66.6667 | 0%
North Valley | NV_North Valley | ELK CREEK 1101 | 2559 | ELK CREEK 11012008 | 21.8511 | 99.3157 | 5.6411 | 0 | 5.6411 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 1 | 85 |  | 17 | 12 | 85 | 17 | 12 | 30.94 | 0.22002 | 0.00778 | 7 | 5.6936 | 0.27112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1. <= 10% | 5. >40 - 50% | 5.6936 | 3.0136 | 3.0136 | 0%
North Valley | NV_North Valley | DESCHUTES 1104 | 3638 | DESCHUTES 11041370 | 68.0935 | 277.1808 | 14.6816 | 0.63201 | 14.0494 | 0.65947 | 1189 | 86 | 3 | 2 | 2 | 1 | 0 | 408 | 0.95508 | 2160 |  | 379 | 251 | 2074 | 377 | 250 | 703.15 | 0.24566 | 0.19259 | 8 | 38.7456 | 0.26179 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 37.0772 | 26.8338 | 25.8146 | 4.305%
Sierra | SA_Sacramento | VACAVILLE 1108 | 3511 | VACAVILLE 11088762 | 51.7145 | 319.6224 | 14.9078 | 0 | 14.9078 | 0 | 491 | 0 | 0 | 0 | 0 | 0 | 0 | 262 | 1 | 904 |  | 165 | 110 | 904 | 165 | 110 | 307.41 | 0.1618 | 0.05551 | 10 | 19.3692 | 0.25486 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 19.3692 | 11.0681 | 11.0681 | 0%
North Valley | NV_North Valley | DESCHUTES 1101 | 6336 | DESCHUTES 1101circuit_breaker | 21.1411 | 112.0119 | 6.3428 | 0 | 6.3428 | 0 | 559 | 0 | 0 | 0 | 0 | 0 | 0 | 157 | 1 | 1027 |  | 187 | 124 | 1027 | 187 | 124 | 348.62 | 0.18874 | 0.07339 | 11 | 11.7062 | 0.24907 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 11.7062 | 29.4822 | 29.4822 | 0%
North Valley | NV_North Valley | VOLTA 1101 | 8993 | VOLTA 110149742 | 13.413 | 84.1183 | 3.7318 | 0 | 3.7318 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 1 | 194 |  | 37 | 25 | 194 | 37 | 25 | 68.15 | 0.15945 | 0.01227 | 12 | 0.47572 | 0.23786 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 0.47572 | 9.9147 | 9.9147 | 0%
North Valley | NV_North Valley | OREGON TRAIL 1104 | 5783 | OREGON TRAIL 11041634 | 84.6404 | 350.0522 | 17.0515 | 0.42083 | 16.6307 | 0.81155 | 1059 | 157 | 26 | 25 | 0 | 0 | 0 | 612 | 0.95241 | 2000 |  | 360 | 246 | 1843 | 360 | 246 | 659.07 | 0.24179 | 0.181 | 13 | 52.2161 | 0.23311 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 50.9274 | 21.6467 | 21.1125 | 2.468%
Sierra | SA_Sacramento | PUTAH CREEK 1102 | 6125 | PUTAH CREEK 11028352 | 30.1982 | 158.9728 | 7.3015 | 6.3316 | 0.96989 | 7.2049 | 316 | 821 | 320 | 239 | 285 | 214 | 0 | 254 | 0.013229 | 829 |  | 321 | 240 | 8 | 36 | 26 | 50.04 | 0.18996 | 0.01422 | 14 | 14.5349 | 0.22711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 1.9307 | 37.1178 | 43.9635 | 86.72%
Central Coast | LP_Los Padres | SANTA YNEZ 1104 | 4339 | SANTA YNEZ 1104Y04 | 74.3641 | 352.4477 | 16.1883 | 0 | 16.1883 | 0 | 241 | 0 | 0 | 0 | 0 | 0 | 0 | 329 | 1 | 450 |  | 83 | 56 | 450 | 83 | 56 | 154.21 | 0.21099 | 0.03642 | 15 | 26.7943 | 0.22707 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 26.7943 | 5.1272 | 5.1272 | 0%
North Coast | HU_Humboldt | WILLITS 1103 | 4340 | WILLITS 110337504 | 5.0625 | 27.8378 | 1.593 | 0 | 1.593 | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 1 | 248 |  | 47 | 32 | 248 | 47 | 32 | 86.71 | 0.18186 | 0.01777 | 16 | 2.2681 | 0.22681 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 2.2681 | 29.5042 | 29.5042 | 0%
North Valley | NV_North Valley | DESCHUTES 1104 | 1665 | DESCHUTES 110449024 | 75.2025 | 338.7487 | 15.7625 | 0 | 15.7625 | 0 | 695 | 0 | 0 | 0 | 0 | 0 | 0 | 415 | 1 | 1274 |  | 232 | 154 | 1274 | 232 | 154 | 432.5 | 0.222 | 0.1071 | 17 | 47.9874 | 0.22216 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 47.9874 | 14.7185 | 14.7185 | 0%
Central Valley | YO_Yosemite | COARSEGOLD 2104 | 5807 | COARSEGOLD 21046288 | 63.7774 | 281.7869 | 10.7962 | 9.2087 | 1.5875 | 10.5718 | 445 | 1138 | 288 | 208 | 268 | 196 | 0 | 356 | 0.020788 | 1155 |  | 291 | 210 | 17 | 23 | 14 | 33.04 | 0.22633 | 0.01082 | 18 | 31.2372 | 0.22154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 4.5932 | 14.4882 | 26.9539 | 85.3%
Sierra | SI_Sierra | SHINGLE SPRINGS 2105 | 5985 | SHINGLE SPRINGS 210519522 | 51.5704 | 269.2431 | 9.8083 | 0.21269 | 9.5956 | 0.21269 | 454 | 33 | 20 | 18 | 20 | 18 | 0 | 206 | 0.97832 | 852 |  | 170 | 117 | 819 | 150 | 99 | 279.21 | 0.19154 | 0.05974 | 20 | 23.1275 | 0.21615 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 22.626 | 15.6321 | 17.3322 | 2.168%
North Coast | HU_Humboldt | POTTER VALLEY P H 1105 | 6737 | POTTER VALLEY P H 110564118 | 5.8923 | 41.3124 | 2.0415 | 0.65284 | 1.3886 | 1.7848 | 215 | 193 | 39 | 18 | 0 | 0 | 0 | 99 | 0.12571 | 244 |  | 48 | 24 | 51 | 48 | 24 | 70.35 | 0.14263 | 0.01424 | 21 | 2.2567 | 0.20515 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 1.535 | 34.5663 | 23.5124 | 31.98%
Central Valley | YO_Yosemite | COARSEGOLD 2104 | 2021 | COARSEGOLD 21045310 | 108.5101 | 534.3014 | 21.1345 | 17.1093 | 4.0252 | 20.9392 | 785 | 2642 | 441 | 352 | 388 | 310 | 0 | 695 | 0.0092392 | 2655 |  | 443 | 354 | 13 | 55 | 44 | 76.52 | 0.20309 | 0.02323 | 22 | 45.6473 | 0.20288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 8.6938 | 13.664 | 20.961 | 80.95%
Bay Area | DI_Diablo | LONE TREE 2105 | 1138 | LONE TREE 210521210 | 31.6645 | 274.9071 | 14.1108 | 0.4428 | 13.6682 | 0.5714 | 101 | 77 | 11 | 4 | 7 | 4 | 0 | 274 | 0.95951 | 265 |  | 47 | 28 | 188 | 40 | 24 | 71.72 | 0.11518 | 0.00958 | 23 | 6.8077 | 0.20023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 6.5941 | 2.9265 | 3.3308 | 3.138%
Sierra | SA_Sacramento | VACA DIXON 1105 | 2533 | VACA DIXON 11059792 | 4.0705 | 20.2732 | 1.175 | 0 | 1.175 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 1 | 27 |  | 7 | 5 | 27 | 7 | 5 | 12.02 | 0.20078 | 0.00292 | 24 | 0.39784 | 0.19892 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.39784 | 5.9574 | 5.9574 | 0%
North Valley | NV_North Valley | OREGON TRAIL 1104 | 1601 | OREGON TRAIL 11041574 | 89.0256 | 417.2123 | 18.0242 | 1.8616 | 16.1627 | 2.2858 | 1849 | 545 | 92 | 53 | 71 | 33 | 0 | 716 | 0.87318 | 3488 |  | 624 | 405 | 2943 | 553 | 372 | 1022.48 | 0.21338 | 0.24537 | 25 | 46.2816 | 0.19694 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 41.5016 | 34.2146 | 34.62 | 10.33%
North Valley | NV_North Valley | JESSUP 1102 | 7507 | JESSUP 11023105 | 30.497 | 153.9699 | 6.6358 | 0 | 6.6358 | 0 | 335 | 0 | 0 | 0 | 0 | 0 | 0 | 173 | 1 | 621 |  | 114 | 76 | 621 | 114 | 76 | 212.07 | 0.19807 | 0.04695 | 26 | 12.7904 | 0.19678 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 12.7904 | 17.1796 | 17.1796 | 0%
Sierra | SI_Sierra | BANGOR 1101 | 6610 | BANGOR 110155206 | 11.6519 | 57.3732 | 3.1869 | 2.685 | 0.5017 | 2.9229 | 227 | 411 | 143 | 114 | 137 | 110 | 0 | 106 | 0.082843 | 446 |  | 150 | 118 | 35 | 13 | 8 | 20.96 | 0.20309 | 0.00549 | 27 | 6.4338 | 0.19496 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 1.0128 | 25.9117 | 47.0672 | 84.25%
Central Valley | YO_Yosemite | COARSEGOLD 2104 | 5931 | COARSEGOLD 21045525 | 67.3226 | 337.3094 | 11.5225 | 9.9083 | 1.6142 | 10.1973 | 424 | 1177 | 295 | 257 | 285 | 250 | 0 | 374 | 0.11501 | 1267 |  | 311 | 268 | 90 | 26 | 18 | 43.72 | 0.19959 | 0.01079 | 28 | 30.7671 | 0.18534 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 4.3102 | 16.107 | 26.9906 | 85.99%
North Coast | SO_Sonoma | SALMON CREEK 1101 | 6073 | SALMON CREEK 1101196 | 4.6351 | 65.704 | 5.111 | 0 | 5.111 | 0 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 1 | 210 |  | 40 | 27 | 210 | 40 | 27 | 73.7 | 0.070545 | 0.00587 | 29 | 2.4025 | 0.18481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 2.4025 | 7.8263 | 7.8263 | 0%
Central Valley | FR_Fresno | SHEPHERD 2111 | 5498 | SHEPHERD 2111R1400 | 68.9954 | 427.8912 | 19.0684 | 0 | 19.0684 | 0 | 310 | 4 | 0 | 0 | 0 | 0 | 0 | 382 | 1 | 579 |  | 106 | 71 | 575 | 106 | 71 | 196.97 | 0.16125 | 0.03554 | 30 | 21.9543 | 0.18449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 21.9543 | 5.5589 | 5.5589 | 0%
North Coast | HU_Humboldt | GARBERVILLE 1101 | 445 | GARBERVILLE 11011604 | 15.4573 | 94.7547 | 5.4547 | 0 | 5.4547 | 0 | 459 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 1 | 846 |  | 155 | 103 | 846 | 155 | 103 | 288.49 | 0.16313 | 0.05258 | 31 | 9.7685 | 0.18431 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 9.7685 | 28.4157 | 28.4157 | 0%
North Valley | NV_North Valley | DESCHUTES 1104 | 1661 | DESCHUTES 11049718 | 52.0914 | 363.4698 | 20.3059 | 0 | 20.3059 | 0 | 993 | 0 | 0 | 0 | 0 | 0 | 0 | 488 | 1 | 1816 |  | 329 | 218 | 1816 | 329 | 218 | 614.17 | 0.14332 | 0.09805 | 32 | 27.7145 | 0.18233 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 27.7145 | 16.2022 | 16.2022 | 0%
North Coast | HU_Humboldt | KONOCTI 1102 | 3086 | CLEAR LAKE 1101486 | 1.4778 | 9.3516 | 0.49545 | 0.43902 | 0.056439 | 0.49545 | 67 | 98 | 12 | 1 | 10 | 1 | 0 | 18 | 0 | 98 |  | 12 | 1 | 0 | 2 | 0 | 2.74 | 0.15803 | 0.00066 | 33 | 0.54415 | 0.18138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.061986 | 35.4362 | 24.2202 | 88.61%
Sierra | SA_Sacramento | VACAVILLE 1108 | 2360 | VACAVILLE 110838316 | 65.7593 | 378.8788 | 16.5822 | 0 | 16.5822 | 0 | 861 | 1 | 0 | 0 | 0 | 0 | 0 | 281 | 1 | 1577 |  | 286 | 189 | 1576 | 286 | 189 | 533.66 | 0.17356 | 0.10322 | 34 | 31.9111 | 0.18029 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 31.9111 | 17.2474 | 17.2474 | 0%
North Valley | NV_North Valley | OREGON TRAIL 1103 | 190 | OREGON TRAIL 110335002 | 224.1458 | 1240.6611 | 55.8786 | 49.9784 | 5.9002 | 54.5807 | 3801 | 8872 | 1129 | 656 | 1102 | 645 | 0 | 2127 | 0.023227 | 9033 |  | 1158 | 675 | 161 | 56 | 30 | 91.21 | 0.18067 | 0.02104 | 35 | 111.7647 | 0.17911 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 11.8012 | 9.4912 | 20.7235 | 89.44%
Sierra | SA_Sacramento | VACA DIXON 1101 | 7265 | VACA DIXON 110118292 | 2.8804 | 23.0896 | 0.57973 | 0 | 0.57973 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 16 |  | 5 | 4 | 16 | 5 | 4 | 8.29 | 0.12475 | 0.0013 | 36 | 0.88798 | 0.1776 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.88798 | 8.6246 | 8.6246 | 0%
North Valley | NV_North Valley | DESCHUTES 1104 | 3707 | DESCHUTES 11049726 | 66.1961 | 351.6962 | 15.0013 | 0 | 15.0013 | 0 | 606 | 0 | 0 | 0 | 0 | 0 | 0 | 384 | 1 | 1113 |  | 203 | 134 | 1113 | 203 | 134 | 378.28 | 0.18822 | 0.07945 | 37 | 35.4739 | 0.17561 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 35.4739 | 13.5321 | 13.5321 | 0%
Central Coast | LP_Los Padres | PASO ROBLES 1104 | 2761 | PASO ROBLES 1104P02 | 1.3461 | 7.7492 | 0.10928 | 0 | 0.10928 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 14 |  | 5 | 4 | 14 | 5 | 4 | 8.11 | 0.17371 | 0.00181 | 38 | 0.17241 | 0.17241 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 6. >50% | 0.17241 | 45.7539 | 45.7539 | 0%
North Coast | HU_Humboldt | HARTLEY 1101 | 5502 | HARTLEY 1101658 | 9.3251 | 77.7311 | 3.7621 | 0 | 3.7621 | 0 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 1 | 279 |  | 52 | 35 | 279 | 52 | 35 | 96.35 | 0.11997 | 0.01297 | 39 | 2.5796 | 0.17198 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 2.5796 | 13.822 | 13.822 | 0%
Sierra | SA_Sacramento | JAMESON 1102 | 7007 | JAMESON 11028842 | 1.7933 | 21.7754 | 0.83712 | 0 | 0.83712 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 81 |  | 17 | 12 | 81 | 17 | 12 | 30.58 | 0.082354 | 0.00291 | 40 | 0.8556 | 0.17112 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.8556 | 20.3077 | 20.3077 | 0%
North Valley | NV_North Valley | DESCHUTES 1104 | 1301 | DESCHUTES 1104circuit_breaker | 38.4764 | 249.5088 | 12.1854 | 0 | 12.1854 | 0 | 795 | 0 | 0 | 0 | 0 | 0 | 0 | 301 | 1 | 1456 |  | 265 | 175 | 1456 | 265 | 175 | 494.09 | 0.15421 | 0.08498 | 41 | 22.4208 | 0.16608 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 22.4208 | 21.7473 | 21.7473 | 0%
Central Coast | LP_Los Padres | ZACA 1102 | 819 | ZACA 1102Y54 | 82.0739 | 680.8108 | 31.3441 | 0 | 31.3441 | 0 | 759 | 0 | 0 | 0 | 0 | 0 | 0 | 521 | 1 | 1391 |  | 253 | 167 | 1391 | 253 | 167 | 471.8 | 0.12055 | 0.06342 | 42 | 38.7034 | 0.16262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 38.7034 | 8.0717 | 8.0717 | 0%
North Coast | HU_Humboldt | HIGHLANDS 1103 | 4570 | HIGHLANDS 1103828 | 40.4327 | 196.2693 | 8.0055 | 6.4949 | 1.5106 | 8.0055 | 520 | 1099 | 247 | 97 | 180 | 76 | 1 | 264 | 0 | 1099 |  | 247 | 97 | 0 | 67 | 21 | 91.79 | 0.20601 | 0.0287 | 43 | 6.2778 | 0.16097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 1.1846 | 44.3531 | 30.8538 | 81.13%
North Coast | HU_Humboldt | MIDDLETOWN 1101 | 6356 | MIDDLETOWN 1101622 | 49.9484 | 362.6862 | 16.1782 | 4.8934 | 11.285 | 11.5788 | 5902 | 6046 | 1384 | 802 | 907 | 521 | 0 | 538 | 0.2843 | 9097 |  | 1935 | 1165 | 3051 | 1028 | 644 | 1682.95 | 0.13772 | 0.29439 | 44 | 38.4777 | 0.16032 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 26.84 | 91.0941 | 119.6052 | 30.25%
Central Coast | LP_Los Padres | PASO ROBLES 1103 | 6910 | PASO ROBLES 1103N58 | 16.7575 | 107.7647 | 3.7983 | 3.2818 | 0.51648 | 3.2818 | 140 | 311 | 27 | 12 | 27 | 12 | 0 | 75 | 0.13598 | 347 |  | 34 | 17 | 36 | 7 | 5 | 12.83 | 0.1555 | 0.00226 | 45 | 7.4845 | 0.15925 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 6. >50% | 1.0177 | 13.5534 | 8.9514 | 86.4%
Sierra | SA_Sacramento | PUTAH CREEK 1102 | 733 | PUTAH CREEK 110267858 | 33.4537 | 234.6659 | 10.611 | 8.8748 | 1.7362 | 10.5206 | 660 | 1433 | 601 | 423 | 518 | 352 | 0 | 307 | 0.0085139 | 1443 |  | 603 | 424 | 10 | 85 | 72 | 117.35 | 0.14256 | 0.0252 | 46 | 19.5736 | 0.15785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 3.2026 | 48.9582 | 56.8279 | 83.64%
North Coast | SO_Sonoma | SALMON CREEK 1101 | 6598 | SALMON CREEK 110188998 | 20.98 | 173.7024 | 8.2392 | 0.36534 | 7.8739 | 0.60511 | 1470 | 21 | 21 | 5 | 0 | 0 | 0 | 153 | 0.92656 | 2506 |  | 471 | 302 | 2485 | 471 | 302 | 868.92 | 0.12078 | 0.11829 | 47 | 12.2196 | 0.15666 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 11.6778 | 59.8182 | 57.1657 | 4.434%
North Valley | NV_North Valley | KESWICK 1101 | 6517 | KESWICK 110148480 | 28.6475 | 276.7793 | 13.6483 | 12.2583 | 1.3902 | 13.6477 | 525 | 1432 | 329 | 300 | 282 | 256 | 0 | 925 | 4.163e-05 | 1432 |  | 329 | 300 | 0 | 47 | 44 | 64.39 | 0.1035 | 0.01012 | 48 | 11.7286 | 0.15638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 1.1946 | 33.8093 | 24.1056 | 89.82%
North Valley | NV_North Valley | OREGON TRAIL 1102 | 3982 | OREGON TRAIL 11021382 | 22.2427 | 136.621 | 5.9968 | 0.45777 | 5.539 | 0.45777 | 504 | 16 | 1 | 0 | 1 | 0 | 0 | 251 | 0.92366 | 873 |  | 157 | 104 | 857 | 156 | 104 | 290.85 | 0.16281 | 0.05281 | 49 | 12.3855 | 0.15291 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 11.44 | 28.1639 | 26.1807 | 7.634%
Sierra | SI_Sierra | CLARKSVILLE 2104 | 9488 | CLARKSVILLE 2105circuit_breaker | 0.36066 | 6.4269 | 0.32273 | 0.31061 | 0.012121 | 0.32273 | 1 | 3 | 2 | 0 | 2 | 0 | 0 | 8 | 0 | 3 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0.056116 | 0 | 50 | 0.30213 | 0.15106 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.011348 | 0 | 6.1972 | 96.24%
Sierra | SA_Sacramento | PUTAH CREEK 1103 | 6431 | PUTAH CREEK 11033851 | 10.978 | 80.6656 | 3.461 | 3.192 | 0.26894 | 3.461 | 29 | 178 | 59 | 37 | 50 | 28 | 0 | 66 | 0 | 178 |  | 59 | 37 | 0 | 9 | 9 | 12.33 | 0.13609 | 0.00255 | 52 | 2.3961 | 0.14976 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.18619 | 33.4648 | 17.0472 | 92.23%
Central Coast | LP_Los Padres | SANTA YNEZ 1104 | 5096 | SANTA YNEZ 110477098 | 29.9711 | 261.7984 | 11.522 | 0 | 11.522 | 0 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 212 | 1 | 265 |  | 50 | 34 | 265 | 50 | 34 | 92.35 | 0.11448 | 0.0119 | 53 | 9.6674 | 0.14873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 9.6674 | 4.3395 | 4.3395 | 0%
Central Valley | FR_Fresno | AUBERRY 1102 | 204 | AUBERRY 1102circuit_breaker | 108.4546 | 845.2061 | 33.4576 | 0.52936 | 32.928 | 0.55189 | 1166 | 17 | 0 | 0 | 0 | 0 | 0 | 674 | 0.9835 | 2112 |  | 380 | 251 | 2095 | 380 | 251 | 709.15 | 0.12832 | 0.10139 | 56 | 43.659 | 0.14221 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 42.968 | 11.5403 | 11.3577 | 1.582%
North Valley | NV_North Valley | RED BLUFF 1105 | 1336 | RED BLUFF 11051564 | 4.6594 | 45.2241 | 1.3854 | 0 | 1.3854 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1 | 40 |  | 9 | 7 | 40 | 9 | 7 | 15.93 | 0.10303 | 0.00193 | 57 | 1.3953 | 0.13953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 1.3953 | 6.4962 | 6.4962 | 0%
Central Valley | YO_Yosemite | COARSEGOLD 2104 | 2220 | COARSEGOLD 2104369777 | 66.0069 | 443.6728 | 18.3176 | 15.4723 | 2.8453 | 18.2121 | 705 | 2050 | 575 | 482 | 544 | 459 | 0 | 549 | 0.0057591 | 2057 |  | 576 | 483 | 7 | 32 | 24 | 44.47 | 0.14877 | 0.0099 | 58 | 28.1228 | 0.13854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 4.3683 | 11.2468 | 31.4451 | 84.47%
North Valley | NV_North Valley | PANORAMA 1101 | 1883 | PANORAMA 1101circuit_breaker | 10.5206 | 82.6715 | 3.1165 | 2.9256 | 0.19091 | 3.0652 | 72 | 278 | 23 | 9 | 20 | 9 | 0 | 116 | 0.016469 | 280 |  | 23 | 9 | 2 | 3 | 0 | 4.29 | 0.12726 | 0.00079 | 59 | 3.1611 | 0.13744 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.19364 | 15.7143 | 7.3801 | 93.87%
Central Valley | FR_Fresno | WOODWARD 2108 | 2424 | WOODWARD 2108R2860 | 26.2282 | 236.1729 | 11.4402 | 10.589 | 0.85114 | 11.3805 | 462 | 1046 | 314 | 272 | 291 | 252 | 0 | 211 | 0.0052149 | 1050 |  | 315 | 273 | 4 | 24 | 21 | 33.24 | 0.11106 | 0.00554 | 60 | 11.4725 | 0.13658 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 0.85354 | 28.1976 | 27.5346 | 92.56%
North Valley | NV_North Valley | DESCHUTES 1104 | 2963 | DESCHUTES 11041582 | 18.467 | 121.4627 | 6.2619 | 0 | 6.2619 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 162 | 1 | 1011 |  | 184 | 122 | 1011 | 184 | 122 | 343.07 | 0.15204 | 0.05817 | 61 | 9.3758 | 0.13588 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 9.3758 | 29.3839 | 29.3839 | 0%
North Valley | NV_North Valley | COTTONWOOD 1103 | 4059 | COTTONWOOD 11031344 | 25.8039 | 212.8178 | 9.6937 | 9.19 | 0.50398 | 9.6937 | 530 | 1016 | 176 | 103 | 174 | 102 | 0 | 341 | 0 | 1016 |  | 176 | 103 | 0 | 2 | 1 | 2.74 | 0.12125 | 0.0005 | 62 | 13.6725 | 0.13537 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.71083 | 3.9684 | 18.156 | 94.8%
Sierra | SI_Sierra | WISE 1102 | 105 | WISE 11022054 | 39.1083 | 306.578 | 13.0856 | 0.19697 | 12.8886 | 0.57311 | 1015 | 145 | 41 | 23 | 16 | 10 | 0 | 478 | 0.9562 | 1919 |  | 363 | 236 | 1774 | 347 | 226 | 635.05 | 0.12756 | 0.09204 | 63 | 22.9035 | 0.13473 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 22.5588 | 26.9229 | 27.7404 | 1.505%
Sierra | SA_Sacramento | PUTAH CREEK 1102 | 891 | PUTAH CREEK 1102circuit_breaker | 16.9299 | 142.463 | 5.1661 | 4.7525 | 0.41364 | 5.1661 | 100 | 348 | 58 | 36 | 51 | 32 | 0 | 122 | 0 | 348 |  | 58 | 36 | 0 | 7 | 4 | 9.59 | 0.11884 | 0.00173 | 64 | 3.7245 | 0.13302 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.29821 | 16.9231 | 11.227 | 91.99%
North Coast | HU_Humboldt | WILLITS 1104 | 1911 | WILLITS 1104circuit_breaker | 11.2762 | 99.3011 | 3.6881 | 2.3259 | 1.3621 | 3.4133 | 539 | 964 | 212 | 55 | 169 | 44 | 0 | 172 | 0.074513 | 1038 |  | 225 | 64 | 74 | 56 | 20 | 83.38 | 0.11356 | 0.01322 | 65 | 6.3727 | 0.13276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 2.3536 | 41.1123 | 61.0075 | 63.07%
Central Valley | YO_Yosemite | MARIPOSA 2102 | 3795 | MARIPOSA 210210880 | 116.8183 | 1021.4119 | 39.2456 | 0 | 39.2456 | 11.9778 | 2958 | 0 | 0 | 0 | 0 | 0 | 0 | 1362 | 0.6948 | 3741 |  | 676 | 446 | 3741 | 676 | 446 | 1262.81 | 0.11437 | 0.16077 | 66 | 51.8448 | 0.13159 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 51.8448 | 17.2248 | 17.2248 | 0%
Central Valley | YO_Yosemite | COARSEGOLD 2104 | 5945 | COARSEGOLD 2104570682 | 2.1849 | 29.9995 | 1.786 | 0.9517 | 0.83428 | 1.7646 | 98 | 283 | 71 | 58 | 47 | 39 | 0 | 82 | 0.011983 | 285 |  | 71 | 58 | 2 | 24 | 19 | 33.06 | 0.072831 | 0.00363 | 67 | 2.3629 | 0.13127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 1.1038 | 28.7673 | 39.754 | 53.29%
North Coast | SO_Sonoma | MOLINO 1102 | 3080 | MOLINO 110279306 | 11.5432 | 109.4429 | 4.0648 | 1.7544 | 2.3104 | 3.683 | 746 | 486 | 129 | 38 | 37 | 7 | 1 | 157 | 0.093933 | 614 |  | 152 | 53 | 128 | 115 | 46 | 169.07 | 0.10547 | 0.02522 | 68 | 5.1143 | 0.13114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 2.907 | 49.7746 | 37.3945 | 43.16%
Central Valley | FR_Fresno | AUBERRY 1102 | 3587 | AUBERRY 1102R309 | 24.2805 | 207.7602 | 8.9201 | 0 | 8.9201 | 0 | 276 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | 1 | 513 |  | 95 | 63 | 513 | 95 | 63 | 176.32 | 0.11687 | 0.02309 | 69 | 9.9592 | 0.13104 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 9.9592 | 10.6501 | 10.6501 | 0%
North Valley | NV_North Valley | COTTONWOOD 1102 | 890 | COTTONWOOD 1102circuit_breaker | 41.6788 | 349.2321 | 14.4778 | 0 | 14.4778 | 0 | 371 | 0 | 0 | 0 | 0 | 0 | 0 | 344 | 1 | 686 |  | 126 | 84 | 686 | 126 | 84 | 234.36 | 0.11934 | 0.03127 | 70 | 21.1966 | 0.13084 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 21.1966 | 8.703 | 8.703 | 0%
Sierra | SI_Sierra | WISE 1102 | 3716 | WISE 11022230 | 79.0957 | 566.3462 | 24.133 | 0.45909 | 23.6739 | 0.45909 | 1945 | 151 | 48 | 14 | 47 | 13 | 0 | 871 | 0.98098 | 3628 |  | 677 | 429 | 3477 | 630 | 416 | 1176.03 | 0.13966 | 0.18296 | 71 | 34.7369 | 0.13059 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 34.0761 | 26.6116 | 28.0529 | 1.902%
Central Valley | FR_Fresno | AUBERRY 1102 | 3450 | AUBERRY 1102R2850 | 64.2626 | 657.5265 | 26.3384 | 0 | 26.3384 | 0 | 840 | 0 | 0 | 0 | 0 | 0 | 0 | 457 | 1 | 1538 |  | 279 | 185 | 1538 | 279 | 185 | 520.65 | 0.097734 | 0.0567 | 72 | 22.8722 | 0.12922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 22.8722 | 10.5929 | 10.5929 | 0%
North Valley | NV_North Valley | OREGON TRAIL 1104 | 662 | OREGON TRAIL 1104circuit_breaker | 37.5951 | 265.7493 | 11.6125 | 0.89091 | 10.7214 | 3.0403 | 1672 | 794 | 231 | 197 | 28 | 9 | 0 | 477 | 0.73818 | 3044 |  | 638 | 466 | 2250 | 610 | 457 | 1038.2 | 0.14147 | 0.17944 | 73 | 18.4455 | 0.12899 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 17.03 | 56.8955 | 54.9408 | 7.672%
Central Valley | YO_Yosemite | OAKHURST 1101 | 1973 | OAKHURST 11015490 | 69.9862 | 599.1732 | 24.9106 | 14.7633 | 10.1473 | 24.0985 | 3010 | 5604 | 1873 | 855 | 1056 | 603 | 0 | 936 | 0.032601 | 5783 |  | 1905 | 876 | 179 | 849 | 273 | 1179.24 | 0.1168 | 0.20621 | 74 | 39.1235 | 0.1287 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 15.937 | 83.6672 | 76.4735 | 59.26%
Central Coast | LP_Los Padres | PASO ROBLES 1103 | 2593 | PASO ROBLES 1103N54 | 57.3189 | 510.0351 | 23.0886 | 21.2409 | 1.8477 | 21.6498 | 214 | 904 | 95 | 33 | 94 | 33 | 0 | 427 | 0.062317 | 929 |  | 100 | 36 | 25 | 6 | 3 | 10.47 | 0.11238 | 0.0014 | 75 | 19.3286 | 0.128 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 1.5468 | 3.2472 | 4.3311 | 92%
North Valley | NV_North Valley | COTTONWOOD 1102 | 502 | COTTONWOOD 11029026 | 35.3585 | 274.6415 | 12.8235 | 0 | 12.8235 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 314 | 1 | 829 |  | 152 | 101 | 829 | 152 | 101 | 282.85 | 0.12874 | 0.04069 | 76 | 16.2213 | 0.12773 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 16.2213 | 11.8533 | 11.8533 | 0%
North Coast | HU_Humboldt | HIGHLANDS 1103 | 5017 | HIGHLANDS 1103circuit_breaker | 26.6669 | 232.5816 | 11.8278 | 9.0947 | 2.733 | 11.2758 | 821 | 2026 | 572 | 188 | 457 | 111 | 0 | 579 | 0.046677 | 2096 |  | 585 | 196 | 70 | 128 | 85 | 181.66 | 0.11466 | 0.03052 | 77 | 13.8949 | 0.12748 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 3.2106 | 46.8358 | 49.4596 | 76.89%
Central Coast | LP_Los Padres | SAN MIGUEL 1104 | 3127 | SAN MIGUEL 1104R58 | 17.1608 | 157.9333 | 9.2008 | 0.17405 | 9.0267 | 0.17405 | 62 | 1 | 0 | 0 | 0 | 0 | 0 | 136 | 0.98108 | 123 |  | 24 | 17 | 122 | 24 | 17 | 43.86 | 0.10866 | 0.00542 | 78 | 6.1653 | 0.12582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 6.0487 | 2.6588 | 2.6085 | 1.892%
North Coast | SO_Sonoma | PETALUMA C 1108 | 5903 | PETALUMA C 1108618 | 15.8794 | 251.1311 | 8.4739 | 7.1193 | 1.3545 | 8.4739 | 702 | 1115 | 514 | 363 | 373 | 257 | 0 | 353 | 0 | 1115 |  | 514 | 363 | 0 | 141 | 106 | 193.17 | 0.063232 | 0.01854 | 79 | 0.50087 | 0.12522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 0.080063 | 104.094 | 60.6571 | 84.02%
North Valley | NV_North Valley | TYLER 1105 | 86 | TYLER 11051704 | 35.423 | 271.3583 | 12.2848 | 0 | 12.2848 | 0 | 618 | 0 | 0 | 0 | 0 | 0 | 0 | 278 | 1 | 1135 |  | 207 | 137 | 1135 | 207 | 137 | 385.74 | 0.13054 | 0.05619 | 80 | 19.4232 | 0.12451 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 19.4232 | 16.85 | 16.85 | 0%
North Valley | NV_North Valley | COTTONWOOD 1103 | 1571 | COTTONWOOD 11031348 | 88.5983 | 671.0186 | 28.4909 | 26.3252 | 2.1657 | 28.0994 | 2170 | 4868 | 1848 | 1287 | 1833 | 1282 | 0 | 1017 | 0.01374 | 4922 |  | 1858 | 1293 | 54 | 25 | 11 | 39.11 | 0.13204 | 0.00686 | 81 | 43.6979 | 0.1245 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 3.3217 | 11.5435 | 65.2138 | 92.4%
Bay Area | NB_North Bay | STAFFORD 1102 | 8455 | STAFFORD 11021202 | 8.5967 | 199.0573 | 7.5943 | 0 | 7.5943 | 0 | 242 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 1 | 452 |  | 83 | 56 | 452 | 83 | 56 | 154.39 | 0.043187 | 0.00745 | 82 | 1.9742 | 0.12339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 1.9742 | 10.9292 | 10.9292 | 0%
North Coast | HU_Humboldt | UKIAH 1111 | 3596 | UKIAH 1111534 | 38.8009 | 436.8365 | 18.2775 | 0 | 18.2775 | 0 | 3062 | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 1 | 5573 |  | 1007 | 664 | 5573 | 1007 | 664 | 1881.16 | 0.088822 | 0.18599 | 83 | 18.9464 | 0.12303 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 18.9464 | 55.0952 | 55.0952 | 0%
Central Coast | LP_Los Padres | ZACA 1102 | 1399 | ZACA 1102Y02 | 31.6582 | 253.861 | 11.7814 | 0 | 11.7814 | 0 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 224 | 1 | 492 |  | 91 | 61 | 492 | 91 | 61 | 168.95 | 0.12471 | 0.0236 | 84 | 9.6937 | 0.12271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 9.6937 | 7.724 | 7.724 | 0%
North Valley | NV_North Valley | STILLWATER 1102 | 6222 | STILLWATER 110248952 | 28.6368 | 229.4403 | 10.0246 | 0 | 10.0246 | 0 | 1319 | 0 | 0 | 0 | 0 | 0 | 0 | 245 | 1 | 2408 |  | 436 | 288 | 2408 | 436 | 288 | 814.04 | 0.12481 | 0.11316 | 85 | 16.2746 | 0.12145 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 16.2746 | 43.4929 | 43.4929 | 0%
Central Valley | YO_Yosemite | COARSEGOLD 2104 | 192 | COARSEGOLD 21045300 | 110.3696 | 858.7766 | 35.8125 | 30.5434 | 5.2691 | 35.2125 | 1075 | 3699 | 647 | 511 | 555 | 429 | 0 | 1023 | 0.016754 | 3732 |  | 653 | 515 | 33 | 98 | 86 | 137.23 | 0.12852 | 0.02619 | 86 | 46.3711 | 0.12107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 6.8226 | 18.5989 | 18.2339 | 85.29%
North Coast | HU_Humboldt | MIDDLETOWN 1102 | 1391 | MIDDLETOWN 1102998 | 37.7887 | 369.141 | 14.2614 | 11.1945 | 3.0669 | 13.9059 | 518 | 1868 | 328 | 210 | 253 | 173 | 1 | 519 | 0.024927 | 1892 |  | 332 | 213 | 24 | 79 | 40 | 110.39 | 0.10237 | 0.01682 | 87 | 16.1058 | 0.12019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 3.4635 | 25.7593 | 23.2797 | 78.5%
North Coast | HU_Humboldt | MIDDLETOWN 1102 | 6489 | MIDDLETOWN 1102circuit_breaker | 18.3826 | 128.7858 | 5.8532 | 3.7133 | 2.1398 | 5.1152 | 205 | 276 | 120 | 91 | 49 | 30 | 0 | 199 | 0.1261 | 324 |  | 129 | 97 | 48 | 80 | 67 | 113.92 | 0.14274 | 0.02374 | 88 | 3.818 | 0.11931 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 1.3958 | 37.3871 | 22.0392 | 63.44%
North Valley | NV_North Valley | DESCHUTES 1101 | 3724 | DESCHUTES 11011380 | 45.3808 | 479.33 | 17.1883 | 0 | 17.1883 | 0 | 1107 | 0 | 0 | 0 | 0 | 0 | 0 | 392 | 1 | 2023 |  | 367 | 242 | 2023 | 367 | 242 | 684.86 | 0.094676 | 0.07225 | 89 | 17.8832 | 0.11922 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 17.8832 | 21.3518 | 21.3518 | 0%
Central Coast | LP_Los Padres | PASO ROBLES 1103 | 7350 | PASO ROBLES 11032731 | 2.5275 | 28.0451 | 0.99943 | 0.92803 | 0.071402 | 0.99943 | 25 | 65 | 2 | 0 | 1 | 0 | 0 | 18 | 0 | 65 |  | 2 | 0 | 0 | 1 | 0 | 1.37 | 0.090123 | 0.00019 | 90 | 1.901 | 0.11881 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.13581 | 14.0053 | 2.0011 | 92.86%
Central Valley | FR_Fresno | TIVY VALLEY 1107 | 1744 | TIVY VALLEY 1107869946 | 46.5087 | 636.6279 | 27.8379 | 13.3314 | 14.5064 | 27.4284 | 484 | 2064 | 842 | 777 | 104 | 88 | 0 | 492 | 0.014709 | 2077 |  | 844 | 779 | 13 | 740 | 691 | 1014.97 | 0.073055 | 0.11241 | 91 | 14.7751 | 0.11726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1. <= 10% | 1. <= 10% | 7.6993 | 51.0118 | 30.3184 | 47.89%
Central Valley | YO_Yosemite | COARSEGOLD 2103 | 1577 | COARSEGOLD 210310820 | 87.8163 | 723.561 | 27.8934 | 2.3672 | 25.5261 | 2.4985 | 1061 | 263 | 56 | 40 | 56 | 40 | 0 | 615 | 0.91043 | 2028 |  | 376 | 252 | 1765 | 320 | 212 | 597.25 | 0.12137 | 0.08076 | 92 | 35.3292 | 0.11508 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 32.3309 | 12.5362 | 13.4799 | 8.487%
North Valley | NV_North Valley | COTTONWOOD 1101 | 6021 | COTTONWOOD 110131500 | 7.6803 | 58.0532 | 4.6801 | 0 | 4.6801 | 0 | 298 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 1 | 553 |  | 102 | 68 | 553 | 102 | 68 | 189.51 | 0.1323 | 0.02806 | 93 | 4.8132 | 0.1146 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 4.8132 | 21.7943 | 21.7943 | 0%
Sierra | SI_Sierra | BELL 1107 | 1789 | BELL 110750172 | 50.2345 | 437.385 | 17.3078 | 11.647 | 5.6606 | 16.2146 | 1562 | 4179 | 1278 | 881 | 957 | 713 | 1 | 596 | 0.063161 | 4359 |  | 1311 | 903 | 180 | 354 | 190 | 501.18 | 0.11485 | 0.08454 | 94 | 27.7939 | 0.11438 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 9.0902 | 62.5375 | 75.7463 | 67.29%
Sierra | SA_Sacramento | JAMESON 1103 | 7292 | JAMESON 1103circuit_breaker | 6.9037 | 66.8283 | 2.5627 | 0 | 2.5627 | 0 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 1 | 321 |  | 60 | 40 | 321 | 60 | 40 | 111.09 | 0.10331 | 0.01289 | 95 | 2.9634 | 0.11398 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 2.9634 | 23.4129 | 23.4129 | 0%
Central Valley | YO_Yosemite | COARSEGOLD 2104 | 2409 | COARSEGOLD 210410400 | 155.48 | 1136.9905 | 43.8059 | 41.5436 | 2.2625 | 42.6513 | 1216 | 3639 | 762 | 592 | 715 | 557 | 0 | 1457 | 0.026356 | 3698 |  | 773 | 599 | 59 | 58 | 42 | 84.77 | 0.13675 | 0.01649 | 96 | 53.3043 | 0.11269 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 2.7531 | 25.6354 | 17.646 | 94.84%
North Valley | NV_North Valley | RED BLUFF 1103 | 5388 | RED BLUFF 11031702 | 45.6703 | 393.8046 | 16.8487 | 0 | 16.8487 | 0 | 829 | 0 | 0 | 0 | 0 | 0 | 0 | 374 | 1 | 1518 |  | 276 | 183 | 1518 | 276 | 183 | 514.74 | 0.11597 | 0.06656 | 97 | 20.2222 | 0.11235 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 20.2222 | 16.3811 | 16.3811 | 0%
Sierra | SI_Sierra | BANGOR 1101 | 5473 | BANGOR 110180670 | 33.2054 | 298.7886 | 14.6979 | 11.0587 | 3.6392 | 14.6153 | 756 | 2032 | 592 | 541 | 499 | 452 | 0 | 484 | 0.0056182 | 2040 |  | 593 | 542 | 8 | 94 | 90 | 129.5 | 0.11113 | 0.02172 | 98 | 18.1242 | 0.11188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 4.4875 | 25.8298 | 40.3459 | 75.24%
North Valley | NV_North Valley | ELK CREEK 1101 | 8205 | ELK CREEK 110193504 | 3.8717 | 31.4921 | 1.0739 | 0 | 1.0739 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1 | 34 |  | 8 | 6 | 34 | 8 | 6 | 14.02 | 0.12294 | 0.00205 | 99 | 0.22351 | 0.11176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.22351 | 7.4497 | 7.4497 | 0%
North Valley | NV_North Valley | COTTONWOOD 1101 | 6616 | COTTONWOOD 110168190 | 54.2633 | 557.3494 | 23.6848 | 0 | 23.6848 | 0 | 1452 | 0 | 0 | 0 | 0 | 0 | 0 | 538 | 1 | 2649 |  | 480 | 317 | 2649 | 480 | 317 | 896.01 | 0.09736 | 0.09718 | 100 | 27.6706 | 0.11024 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 27.6706 | 20.2661 | 20.2661 | 0%
Sierra | SI_Sierra | SHINGLE SPRINGS 2108 | 7282 | SHINGLE SPRINGS 210851476 | 11.8015 | 118.495 | 5.0407 | 0 | 5.0407 | 0 | 482 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 1 | 888 |  | 162 | 108 | 888 | 162 | 108 | 301.86 | 0.099595 | 0.03355 | 101 | 7.2751 | 0.11023 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 7.2751 | 32.1383 | 32.1383 | 0%
North Coast | HU_Humboldt | HIGHLANDS 1103 | 4329 | HIGHLANDS 1103568 | 20.9935 | 168.4835 | 7.0506 | 5.1875 | 1.8631 | 7.0506 | 490 | 1055 | 372 | 92 | 311 | 61 | 0 | 276 | 0 | 1055 |  | 372 | 92 | 0 | 61 | 31 | 83.57 | 0.1246 | 0.01581 | 102 | 8.9233 | 0.10882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 2.3579 | 32.7417 | 52.7617 | 73.58%
Sierra | SA_Sacramento | VACAVILLE 1111 | 6761 | VACAVILLE 111113652 | 15.3993 | 162.1455 | 5.8564 | 5.3307 | 0.52576 | 5.7996 | 400 | 1637 | 679 | 488 | 645 | 462 | 0 | 271 | 0.0097018 | 1644 |  | 680 | 489 | 7 | 35 | 27 | 48.58 | 0.094972 | 0.00691 | 103 | 6.3046 | 0.1087 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 0.56599 | 66.5706 | 116.1115 | 91.02%
Central Coast | LP_Los Padres | BUELLTON 1102 | 2632 | BUELLTON 1102circuit_breaker | 9.5739 | 99.9364 | 5.5973 | 5.5074 | 0.089962 | 5.5973 | 161 | 273 | 82 | 44 | 80 | 44 | 0 | 175 | 0 | 273 |  | 82 | 44 | 0 | 2 | 0 | 2.74 | 0.0958 | 0.0004 | 104 | 3.8574 | 0.10715 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.061997 | 22.2316 | 14.6498 | 98.39%
North Valley | NV_North Valley | RED BLUFF 1101 | 864 | RED BLUFF 11011334 | 102.6179 | 884.7607 | 39.9742 | 0 | 39.9742 | 0 | 1531 | 0 | 0 | 0 | 0 | 0 | 0 | 877 | 1 | 2793 |  | 506 | 334 | 2793 | 506 | 334 | 944.59 | 0.11598 | 0.12204 | 105 | 43.7155 | 0.10715 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 43.7155 | 12.6582 | 12.6582 | 0%
Central Valley | YO_Yosemite | COARSEGOLD 2104 | 6138 | COARSEGOLD 210410335 | 11.6162 | 125.1395 | 5.2487 | 4.761 | 0.48788 | 5.2477 | 212 | 621 | 81 | 57 | 72 | 48 | 0 | 153 | 0.00018042 | 621 |  | 81 | 57 | 0 | 9 | 9 | 12.33 | 0.092826 | 0.00174 | 106 | 8.9154 | 0.10489 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.82871 | 18.4472 | 15.4325 | 90.71%
Sierra | SI_Sierra | BANGOR 1101 | 4384 | BANGOR 110182350 | 55.1834 | 472.9002 | 20.4634 | 18.0172 | 2.4462 | 19.6246 | 1129 | 3715 | 1614 | 1404 | 1478 | 1290 | 0 | 744 | 0.040991 | 3800 |  | 1629 | 1414 | 85 | 151 | 124 | 214.52 | 0.11669 | 0.03664 | 107 | 25.231 | 0.10469 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 3.0161 | 61.7281 | 79.6054 | 88.05%
North Coast | HU_Humboldt | HARTLEY 1101 | 9084 | HARTLEY 11014710 | 4.8183 | 38.1432 | 2.2975 | 0 | 2.2975 | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 1 | 172 |  | 33 | 23 | 172 | 33 | 23 | 60.69 | 0.12632 | 0.00867 | 108 | 1.459 | 0.10421 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 1.459 | 14.3632 | 14.3632 | 0%
Central Valley | FR_Fresno | AUBERRY 1102 | 4268 | AUBERRY 110237466 | 75.1175 | 817.6128 | 30.8723 | 0.50455 | 30.3678 | 0.67917 | 681 | 66 | 12 | 10 | 0 | 0 | 0 | 618 | 0.978 | 1287 |  | 234 | 157 | 1221 | 234 | 157 | 430.47 | 0.091874 | 0.0447 | 109 | 20.3675 | 0.10339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 20.0346 | 7.7055 | 7.5796 | 1.634%
North Valley | NV_North Valley | CLARK ROAD 1102 | 9386 | CLARK ROAD 1102circuit_breaker | 0.90279 | 16.3818 | 1.1059 | 1.0604 | 0.045455 | 1.0973 | 41 | 45 | 5 | 0 | 3 | 0 | 0 | 43 | 0.0077068 | 46 |  | 5 | 0 | 1 | 2 | 0 | 2.83 | 0.05511 | 0.00023 | 110 | 0.30919 | 0.10306 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.012709 | 44 | 4.5213 | 95.89%
Sierra | SI_Sierra | BROWNS VALLEY 1101 | 7209 | BROWNS VALLEY 110193870 | 40.5698 | 414.4797 | 21.0303 | 0 | 21.0303 | 0 | 1457 | 0 | 0 | 0 | 0 | 0 | 0 | 461 | 1 | 2658 |  | 481 | 318 | 2658 | 481 | 318 | 898.19 | 0.097881 | 0.0979 | 111 | 19.6578 | 0.10238 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 19.6578 | 22.8718 | 22.8718 | 0%
Sierra | SI_Sierra | MOUNTAIN QUARRIES 2101 | 4869 | MOUNTAIN QUARRIES 21016953 | 16.4839 | 160.9623 | 6.5299 | 0 | 6.5299 | 0 | 423 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 1 | 780 |  | 143 | 95 | 780 | 143 | 95 | 266.11 | 0.10241 | 0.03045 | 112 | 6.0045 | 0.10177 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 6.0045 | 21.8992 | 21.8992 | 0%
Central Coast | LP_Los Padres | BUELLTON 1102 | 1685 | BUELLTON 1102Y50 | 25.6458 | 283.0617 | 10.5968 | 10.4191 | 0.17765 | 10.5968 | 341 | 1040 | 99 | 4 | 98 | 3 | 0 | 417 | 0 | 1040 |  | 99 | 4 | 0 | 1 | 1 | 1.37 | 0.090601 | 0.00019 | 113 | 13.5803 | 0.10135 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.22767 | 5.629 | 9.3425 | 98.32%
Sierra | SI_Sierra | FLINT 1101 | 5653 | FLINT 1101750 | 6.9428 | 92.7628 | 3.9481 | 0 | 3.9481 | 0 | 367 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 1 | 679 |  | 124 | 83 | 679 | 124 | 83 | 230.99 | 0.074845 | 0.0193 | 114 | 4.9524 | 0.10107 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 4.9524 | 31.4075 | 31.4075 | 0%
Sierra | SA_Sacramento | VACAVILLE 1104 | 3978 | VACAVILLE 11046542 | 32.7166 | 352.5962 | 13.508 | 0 | 13.508 | 0 | 753 | 0 | 0 | 0 | 0 | 0 | 0 | 287 | 1 | 1380 |  | 251 | 166 | 1380 | 251 | 166 | 468.07 | 0.092788 | 0.04843 | 115 | 16.4715 | 0.10044 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 16.4715 | 18.5816 | 18.5816 | 0%
Central Valley | ST_Stockton | CORRAL 1101 | 1015 | CORRAL 110136652 | 72.1737 | 688.1572 | 33.5112 | 32.0208 | 1.4903 | 33.4201 | 581 | 2034 | 411 | 299 | 401 | 292 | 0 | 1098 | 0.0027185 | 2037 |  | 412 | 299 | 3 | 11 | 7 | 15.34 | 0.10488 | 0.0024 | 116 | 32.3296 | 0.1004 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 1.4378 | 7.3809 | 12.2944 | 95.55%
Central Valley | FR_Fresno | AUBERRY 1101 | 1458 | AUBERRY 1101circuit_breaker | 43.7192 | 429.1457 | 18.1076 | 3.7294 | 14.378 | 6.1621 | 951 | 544 | 96 | 67 | 2 | 1 | 0 | 692 | 0.65969 | 1691 |  | 304 | 205 | 1147 | 302 | 204 | 516.97 | 0.10187 | 0.06398 | 117 | 15.1058 | 0.10004 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 11.9945 | 21.0043 | 16.7886 | 20.6%
Central Valley | ST_Stockton | NORTH BRANCH 1101 | 167 | NORTH BRANCH 110111206 | 27.1998 | 385.0865 | 17.2689 | 0 | 17.2689 | 0 | 243 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 1 | 454 |  | 84 | 56 | 454 | 84 | 56 | 155.94 | 0.070633 | 0.01234 | 118 | 10.0345 | 0.098378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 10.0345 | 4.8642 | 4.8642 | 0%
Central Valley | YO_Yosemite | OAKHURST 1103 | 4692 | OAKHURST 110363334 | 37.373 | 352.3005 | 14.8676 | 0.99223 | 13.8756 | 2.7801 | 1068 | 327 | 161 | 65 | 26 | 13 | 0 | 471 | 0.81301 | 1914 |  | 449 | 255 | 1587 | 423 | 242 | 722.34 | 0.10608 | 0.09331 | 119 | 17.9641 | 0.098165 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 16.7655 | 30.4852 | 30.1999 | 6.674%
North Coast | HU_Humboldt | HARTLEY 1101 | 4752 | HARTLEY 1101698 | 19.3463 | 172.2664 | 8.1491 | 0 | 8.1491 | 0 | 666 | 0 | 0 | 0 | 0 | 0 | 0 | 147 | 1 | 1222 |  | 222 | 147 | 1222 | 222 | 147 | 414.12 | 0.1123 | 0.05184 | 120 | 6.2809 | 0.098139 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 6.2809 | 27.2424 | 27.2424 | 0%
North Valley | NV_North Valley | WYANDOTTE 1109 | 2349 | WYANDOTTE 11091520 | 8.8779 | 80.4788 | 3.4343 | 0.0028409 | 3.4314 | 0.14621 | 242 | 29 | 6 | 5 | 0 | 0 | 0 | 115 | 0.95743 | 462 |  | 86 | 59 | 433 | 86 | 59 | 156.79 | 0.11031 | 0.01973 | 121 | 4.9654 | 0.097361 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 4.9613 | 25.0624 | 25.0416 | 0.08272%
Sierra | SI_Sierra | BROWNS VALLEY 1101 | 8695 | BROWNS VALLEY 110117011 | 5.7079 | 64.6988 | 2.5992 | 0 | 2.5992 | 0 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 1 | 366 |  | 68 | 46 | 366 | 68 | 46 | 126.1 | 0.088222 | 0.01247 | 122 | 2.4233 | 0.096932 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 2.4233 | 26.1615 | 26.1615 | 0%
North Valley | NV_North Valley | TYLER 1105 | 5352 | TYLER 11051536 | 39.6494 | 385.8349 | 17.8494 | 0 | 17.8494 | 0 | 508 | 0 | 0 | 0 | 0 | 0 | 0 | 313 | 1 | 935 |  | 171 | 113 | 935 | 171 | 113 | 318.42 | 0.10276 | 0.03654 | 123 | 8.8807 | 0.096529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 8.8807 | 9.5801 | 9.5801 | 0%
North Valley | NV_North Valley | ELK CREEK 1101 | 7852 | ELK CREEK 11012002 | 14.4493 | 283.2521 | 19.6763 | 0 | 19.6763 | 0 | 398 | 0 | 0 | 0 | 0 | 0 | 0 | 292 | 1 | 735 |  | 135 | 90 | 735 | 135 | 90 | 251.1 | 0.051012 | 0.01432 | 124 | 2.7729 | 0.095618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 2.7729 | 6.861 | 6.861 | 0%
North Valley | NV_North Valley | OREGON TRAIL 1103 | 7087 | OREGON TRAIL 1103circuit_breaker | 6.7668 | 58.0316 | 2.1739 | 2.0956 | 0.07803 | 2.1161 | 218 | 497 | 152 | 71 | 152 | 71 | 0 | 90 | 0.026573 | 508 |  | 154 | 72 | 11 | 2 | 1 | 3.73 | 0.1166 | 0.00048 | 125 | 4.1072 | 0.095517 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.14743 | 25.6311 | 70.8416 | 96.4%
North Valley | NV_North Valley | CLARK ROAD 1102 | 247 | CLARK ROAD 11022582 | 34.6893 | 517.4693 | 19.7852 | 16.8723 | 2.9129 | 19.785 | 621 | 1592 | 810 | 447 | 735 | 414 | 0 | 595 | 9.5725e-06 | 1592 |  | 810 | 447 | 0 | 75 | 33 | 102.75 | 0.067036 | 0.01045 | 126 | 15.8251 | 0.095332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 2.3298 | 25.7477 | 40.9396 | 85.28%
North Coast | HU_Humboldt | CLEAR LAKE 1102 | 7841 | CLEAR LAKE 1102904 | 3.78 | 55.2377 | 3.0415 | 0 | 3.0415 | 0 | 248 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 1 | 463 |  | 85 | 57 | 463 | 85 | 57 | 158.12 | 0.068432 | 0.0121 | 127 | 3.6032 | 0.094821 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 3.6032 | 27.9469 | 27.9469 | 0%
Sierra | SI_Sierra | CLARKSVILLE 2109 | 7750 | CLARKSVILLE 2109circuit_breaker | 0.96763 | 23.2925 | 0.58788 | 0.24432 | 0.34356 | 0.24432 | 9 | 17 | 12 | 12 | 12 | 12 | 0 | 16 | 0.58441 | 34 |  | 16 | 15 | 17 | 4 | 3 | 7.01 | 0.041542 | 0.00035 | 128 | 0.37879 | 0.094696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.22136 | 11.6428 | 27.2165 | 41.56%
North Valley | NV_North Valley | ELK CREEK 1101 | 2668 | ELK CREEK 110137334 | 18.2902 | 184.6163 | 8.9667 | 0 | 8.9667 | 0 | 159 | 0 | 0 | 0 | 0 | 0 | 0 | 166 | 1 | 301 |  | 56 | 38 | 301 | 56 | 38 | 103.81 | 0.099071 | 0.01154 | 129 | 5.2022 | 0.094586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 5.2022 | 6.2454 | 6.2454 | 0%
Central Valley | YO_Yosemite | COARSEGOLD 2103 | 2050 | COARSEGOLD 21035020 | 36.799 | 397.6354 | 16.7623 | 0.56742 | 16.1951 | 0.56742 | 446 | 84 | 19 | 17 | 19 | 17 | 0 | 296 | 0.96615 | 878 |  | 164 | 114 | 794 | 145 | 97 | 270.11 | 0.092545 | 0.0279 | 130 | 12.577 | 0.094564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 12.1514 | 8.9533 | 9.7839 | 3.385%
Central Valley | ST_Stockton | CORRAL 1101 | 912 | CORRAL 1101circuit_breaker | 47.0092 | 545.9463 | 26.5994 | 25.485 | 1.1144 | 26.1932 | 317 | 1089 | 116 | 58 | 114 | 56 | 0 | 851 | 0.015273 | 1098 |  | 118 | 59 | 9 | 4 | 3 | 6.29 | 0.086106 | 0.00072 | 131 | 18.6718 | 0.093359 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.78226 | 3.5894 | 4.4362 | 95.81%
Sierra | SI_Sierra | DEL MAR 2109 | 6448 | DEL MAR 2109circuit_breaker | 4.178 | 55.5026 | 2.792 | 0 | 2.792 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 1 | 139 |  | 27 | 19 | 139 | 27 | 19 | 49.5 | 0.075275 | 0.00423 | 132 | 1.4906 | 0.093164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 1.4906 | 9.6703 | 9.6703 | 0%
North Valley | NV_North Valley | WYANDOTTE 1109 | 1486 | WYANDOTTE 110979932 | 51.8844 | 511.9789 | 21.1451 | 0 | 21.1451 | 0 | 1644 | 0 | 0 | 0 | 0 | 0 | 0 | 707 | 1 | 2998 |  | 543 | 358 | 2998 | 543 | 358 | 1013.73 | 0.10134 | 0.11443 | 133 | 23.4289 | 0.092604 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 23.4289 | 25.6797 | 25.6797 | 0%
North Valley | NV_North Valley | RED BLUFF 1103 | 1206 | RED BLUFF 1103circuit_breaker | 0.93722 | 12.7602 | 0.4178 | 0 | 0.4178 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1 | 54 |  | 12 | 9 | 54 | 12 | 9 | 21.3 | 0.073449 | 0.00183 | 134 | 0.27693 | 0.09231 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.27693 | 28.7217 | 28.7217 | 0%
North Valley | NV_North Valley | JESSUP 1102 | 3497 | JESSUP 110296554 | 16.3994 | 170.1126 | 7.6383 | 0 | 7.6383 | 0 | 535 | 0 | 0 | 0 | 0 | 0 | 0 | 187 | 1 | 984 |  | 179 | 119 | 984 | 179 | 119 | 333.79 | 0.096403 | 0.03588 | 135 | 9.0441 | 0.092286 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 9.0441 | 23.4347 | 23.4347 | 0%
Sierra | SI_Sierra | LINCOLN 1104 | 81 | LINCOLN 110451756 | 28.3013 | 360.8456 | 20.6112 | 0 | 20.6112 | 0 | 646 | 0 | 0 | 0 | 0 | 0 | 0 | 422 | 1 | 1185 |  | 216 | 143 | 1185 | 216 | 143 | 402.57 | 0.07843 | 0.03523 | 136 | 13.1994 | 0.091663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 13.1994 | 10.4798 | 10.4798 | 0%
Central Valley | ST_Stockton | CORRAL 1101 | 7203 | CORRAL 110112608 | 30.6904 | 331.9737 | 16.3947 | 14.2119 | 2.1828 | 14.8413 | 250 | 697 | 75 | 40 | 74 | 39 | 0 | 514 | 0.094751 | 741 |  | 83 | 45 | 44 | 9 | 6 | 16.29 | 0.092448 | 0.00173 | 137 | 11.3441 | 0.091485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 1.5103 | 4.1232 | 5.0626 | 86.69%
Sierra | SI_Sierra | WISE 1102 | 6949 | WISE 11022234 | 26.274 | 383.5944 | 17.5583 | 11.103 | 6.4553 | 13.493 | 1538 | 3815 | 1088 | 691 | 983 | 648 | 0 | 591 | 0.23153 | 4465 |  | 1206 | 769 | 650 | 223 | 121 | 364.01 | 0.068494 | 0.03176 | 138 | 7.2319 | 0.090399 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 2.6588 | 34.5452 | 68.6853 | 63.24%
Sierra | SA_Sacramento | PEABODY 2108 | 8888 | PEABODY 2108circuit_breaker | 0.75207 | 11.6019 | 0.45227 | 0 | 0.45227 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 72 |  | 15 | 11 | 72 | 15 | 11 | 27.03 | 0.064823 | 0.00202 | 139 | 0.35909 | 0.089773 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.35909 | 33.1658 | 33.1658 | 0%
Sierra | SI_Sierra | PENRYN 1103 | 1224 | PENRYN 11032198 | 39.1231 | 438.889 | 18.3763 | 1.332 | 17.0445 | 1.5042 | 1920 | 197 | 18 | 7 | 16 | 6 | 0 | 701 | 0.91815 | 3410 |  | 599 | 391 | 3213 | 583 | 385 | 1087.88 | 0.089141 | 0.10807 | 140 | 25.0789 | 0.089249 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 23.2613 | 34.2046 | 32.5963 | 7.248%
Central Coast | LP_Los Padres | ZACA 1102 | 2756 | ZACA 1102Y48 | 4.3582 | 60.5815 | 3.4494 | 0 | 3.4494 | 0 | 183 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 1 | 345 |  | 64 | 43 | 345 | 64 | 43 | 118.73 | 0.071939 | 0.00957 | 141 | 3.6543 | 0.089128 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 5. >40 - 50% | 3.6543 | 18.5538 | 18.5538 | 0%
Sierra | SI_Sierra | LINCOLN 1104 | 2066 | LINCOLN 11045391 | 1.8382 | 18.5249 | 0.90436 | 0 | 0.90436 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 1 | 41 |  | 9 | 7 | 41 | 9 | 7 | 16.02 | 0.099228 | 0.00186 | 142 | 0.44216 | 0.088432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.44216 | 9.9518 | 9.9518 | 0%
Central Valley | YO_Yosemite | MARIPOSA 2102 | 6934 | MARIPOSA 2102440236 | 7.8157 | 80.2163 | 2.3939 | 0 | 2.3939 | 0.90777 | 353 | 8 | 8 | 7 | 3 | 3 | 0 | 96 | 0.62081 | 414 |  | 82 | 57 | 406 | 79 | 54 | 144.77 | 0.097433 | 0.01601 | 144 | 4.9267 | 0.087976 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 4.9267 | 33 | 34.2532 | 0%
Central Coast | LP_Los Padres | SAN MIGUEL 1105 | 1949 | SAN MIGUEL 1105circuit_breaker | 2.6472 | 33.6305 | 1.7515 | 1.3464 | 0.4053 | 1.3464 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 25 | 0.23129 | 9 |  | 1 | 1 | 3 | 1 | 1 | 1.64 | 0.078716 | 0.00016 | 145 | 0.43559 | 0.087117 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.10079 | 2.4673 | 0.57093 | 76.87%
North Valley | NV_North Valley | ANDERSON 1103 | 3223 | ANDERSON 11031600 | 4.8952 | 75.9569 | 4.6561 | 0 | 4.6561 | 0 | 253 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 1 | 472 |  | 87 | 58 | 472 | 87 | 58 | 161.67 | 0.064447 | 0.01166 | 146 | 3.0334 | 0.086668 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 3.0334 | 18.6853 | 18.6853 | 0%
Sierra | SI_Sierra | SHINGLE SPRINGS 2109 | 5513 | SHINGLE SPRINGS 210935598 | 19.3574 | 253.0908 | 10.1843 | 0 | 10.1843 | 0 | 636 | 0 | 0 | 0 | 0 | 0 | 0 | 226 | 1 | 1167 |  | 212 | 141 | 1167 | 212 | 141 | 395.47 | 0.076484 | 0.03372 | 147 | 10.2267 | 0.086667 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 10.2267 | 20.8164 | 20.8164 | 0%
Central Valley | FR_Fresno | SAND CREEK 1103 | 3761 | SAND CREEK 11037140 | 55.8492 | 655.2143 | 26.0057 | 0 | 26.0057 | 0 | 426 | 0 | 0 | 0 | 0 | 0 | 0 | 582 | 1 | 786 |  | 144 | 96 | 786 | 144 | 96 | 268.02 | 0.085238 | 0.02552 | 148 | 17.3038 | 0.086089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 17.3038 | 5.5373 | 5.5373 | 0%
Bay Area | MI_Mission | NORTH DUBLIN 2103 | 8315 | NORTH DUBLIN 210311101 | 7.3884 | 87.6999 | 4.7102 | 0 | 4.7102 | 0 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 1 | 296 |  | 55 | 37 | 296 | 55 | 37 | 101.99 | 0.084246 | 0.00964 | 149 | 2.2349 | 0.085959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 2.2349 | 11.6767 | 11.6767 | 0%
Sierra | SI_Sierra | BELL 1107 | 1508 | BELL 11072400 | 52.3083 | 579.9889 | 25.7392 | 14.8091 | 10.9303 | 23.6621 | 2937 | 7665 | 2015 | 1398 | 1310 | 1003 | 2 | 960 | 0.080697 | 8096 |  | 2093 | 1449 | 431 | 783 | 446 | 1111.5 | 0.090188 | 0.14684 | 150 | 32.6703 | 0.085749 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 13.8736 | 71.6357 | 81.3156 | 57.54%
Central Valley | FR_Fresno | AUBERRY 1102 | 6785 | AUBERRY 1102R1013 | 30.1966 | 303.1481 | 12.8379 | 0 | 12.8379 | 0 | 672 | 0 | 0 | 0 | 0 | 0 | 0 | 259 | 1 | 1233 |  | 224 | 149 | 1233 | 224 | 149 | 417.85 | 0.09961 | 0.0464 | 151 | 9.8222 | 0.08541 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 9.8222 | 17.4484 | 17.4484 | 0%
Sierra | SI_Sierra | BROWNS VALLEY 1101 | 2440 | BROWNS VALLEY 11011268 | 22.9161 | 257.8567 | 11.2723 | 0.65928 | 10.6131 | 0.71231 | 872 | 271 | 81 | 76 | 80 | 76 | 0 | 267 | 0.93681 | 1766 |  | 352 | 256 | 1495 | 272 | 180 | 507.19 | 0.088871 | 0.05027 | 152 | 11.4123 | 0.084535 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 10.7448 | 25.6288 | 31.2269 | 5.849%
North Valley | NV_North Valley | RED BLUFF 1101 | 7386 | RED BLUFF 110176020 | 17.1772 | 216.2454 | 9.3045 | 0 | 9.3045 | 0 | 418 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 1 | 771 |  | 141 | 94 | 771 | 141 | 94 | 262.56 | 0.079434 | 0.02329 | 153 | 6.9278 | 0.084485 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 6.9278 | 15.1539 | 15.1539 | 0%
Bay Area | DI_Diablo | CLAYTON 2212 | 4128 | CLAYTON 22122944 | 28.893 | 319.1724 | 14.1222 | 12.8973 | 1.2248 | 14.1222 | 392 | 1098 | 348 | 120 | 300 | 77 | 0 | 474 | 0 | 1098 |  | 348 | 120 | 0 | 48 | 43 | 65.76 | 0.090525 | 0.00904 | 154 | 9.9585 | 0.084394 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 0.86369 | 39.1897 | 24.6421 | 91.33%
North Coast | HU_Humboldt | WILLITS 1102 | 3495 | WILLITS 1102circuit_breaker | 10.2605 | 104.2507 | 5.1174 | 0.19205 | 4.9256 | 0.34091 | 1360 | 71 | 21 | 2 | 14 | 0 | 0 | 139 | 0.93338 | 2388 |  | 441 | 279 | 2317 | 427 | 279 | 793.52 | 0.098421 | 0.08739 | 155 | 5.5057 | 0.08342 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 5.2993 | 86.6905 | 86.1762 | 3.753%
North Coast | HU_Humboldt | FORT SEWARD 1121 | 6600 | FORT SEWARD 11211690 | 18.7023 | 202.3066 | 10.4326 | 0 | 10.4326 | 0 | 4955 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 1 | 9010 |  | 1627 | 1073 | 9010 | 1627 | 1073 | 3039.89 | 0.092445 | 0.31276 | 156 | 10.8257 | 0.082639 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 10.8257 | 155.9538 | 155.9538 | 0%
North Coast | SO_Sonoma | COTATI 1105 | 2658 | COTATI 110536536 | 23.6985 | 424.9786 | 17.5551 | 14.4178 | 3.1371 | 17.5551 | 1594 | 1904 | 445 | 68 | 362 | 38 | 0 | 599 | 0 | 1904 |  | 445 | 68 | 0 | 83 | 30 | 113.71 | 0.055764 | 0.00962 | 157 | 10.9762 | 0.082528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 1.9615 | 26.4574 | 25.3487 | 82.13%
North Valley | NV_North Valley | GIRVAN 1102 | 4207 | GIRVAN 1102circuit_breaker | 6.6407 | 108.3827 | 6.2682 | 0 | 6.2682 | 0 | 427 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 1 | 788 |  | 144 | 96 | 788 | 144 | 96 | 268.2 | 0.061271 | 0.01835 | 158 | 4.0129 | 0.081896 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 4.0129 | 22.9732 | 22.9732 | 0%
Sierra | SI_Sierra | LINCOLN 1104 | 4729 | LINCOLN 11042070 | 35.2297 | 426.6486 | 21.0958 | 0 | 21.0958 | 0 | 1523 | 0 | 0 | 0 | 0 | 0 | 0 | 439 | 1 | 2778 |  | 503 | 332 | 2778 | 503 | 332 | 939.13 | 0.082573 | 0.08637 | 159 | 18.6329 | 0.081723 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 18.6329 | 23.8436 | 23.8436 | 0%
North Valley | NV_North Valley | CORNING 1101 | 6432 | CORNING 110182846 | 7.8193 | 105.7873 | 4.4398 | 4.0831 | 0.35663 | 4.4398 | 110 | 440 | 95 | 79 | 93 | 77 | 0 | 160 | 0 | 440 |  | 95 | 79 | 0 | 2 | 2 | 2.74 | 0.073916 | 0.00031 | 160 | 3.5848 | 0.081472 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.28795 | 5.6081 | 21.3975 | 91.97%
North Valley | NV_North Valley | ANDERSON 1101 | 8199 | ANDERSON 11012051 | 7.097 | 109.5667 | 4.8981 | 0 | 4.8981 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 1 | 212 |  | 40 | 27 | 212 | 40 | 27 | 73.88 | 0.064773 | 0.00539 | 161 | 3.6235 | 0.080522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 3.6235 | 8.1664 | 8.1664 | 0%
Central Coast | CC_Central Coast | SAN BENITO 2101 | 2693 | SAN BENITO 210136912 | 4.4489 | 104.3971 | 5.511 | 0 | 5.511 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 1 | 212 |  | 40 | 27 | 212 | 40 | 27 | 73.88 | 0.042615 | 0.00354 | 162 | 1.8411 | 0.080049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 1.8411 | 7.2582 | 7.2582 | 0%
Central Valley | YO_Yosemite | SAN JOAQUIN NO2 1103 | 1374 | SAN JOAQUIN #2 110310320 | 22.3941 | 283.424 | 11.4659 | 0 | 11.4659 | 0 | 1533 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 1 | 2796 |  | 506 | 334 | 2796 | 506 | 334 | 944.86 | 0.079013 | 0.08314 | 163 | 11.6645 | 0.079894 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 11.6645 | 44.1308 | 44.1308 | 0%
North Valley | NV_North Valley | WYANDOTTE 1109 | 5188 | WYANDOTTE 11095607 | 7.6031 | 113.2739 | 4.5653 | 0 | 4.5653 | 0 | 466 | 0 | 0 | 0 | 0 | 0 | 0 | 166 | 1 | 859 |  | 157 | 104 | 859 | 157 | 104 | 292.4 | 0.067121 | 0.02191 | 164 | 4.6188 | 0.079634 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 4.6188 | 34.3895 | 34.3895 | 0%
North Valley | NV_North Valley | ELK CREEK 1101 | 8090 | ELK CREEK 11012106 | 30.703 | 302.701 | 13.2513 | 0 | 13.2513 | 0 | 983 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 1 | 1797 |  | 326 | 216 | 1797 | 326 | 216 | 608.35 | 0.10143 | 0.06876 | 165 | 3.7058 | 0.078846 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 3.7058 | 24.6013 | 24.6013 | 0%
Sierra | SI_Sierra | MOUNTAIN QUARRIES 2101 | 3848 | MOUNTAIN QUARRIES 2101circuit_breaker | 46.4651 | 578.7652 | 25.8396 | 0 | 25.8396 | 0 | 2525 | 0 | 0 | 0 | 0 | 0 | 0 | 569 | 1 | 4598 |  | 831 | 548 | 4598 | 831 | 548 | 1552.29 | 0.080283 | 0.13873 | 166 | 26.0302 | 0.078641 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 26.0302 | 32.16 | 32.16 | 0%
North Coast | HU_Humboldt | LUCERNE 1103 | 2080 | LUCERNE 11031280 | 8.0097 | 187.9493 | 10.2258 | 0.67519 | 9.5508 | 0.9214 | 516 | 88 | 13 | 1 | 0 | 0 | 0 | 230 | 0.90989 | 952 |  | 171 | 106 | 864 | 171 | 106 | 312.03 | 0.042616 | 0.01515 | 167 | 6.2585 | 0.078231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 5.8454 | 17.9043 | 16.7225 | 6.603%
Sierra | SA_Sacramento | VACAVILLE 1109 | 5006 | VACAVILLE 110941782 | 0.90722 | 9.4793 | 0.29527 | 0 | 0.29527 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 21 |  | 6 | 5 | 21 | 6 | 5 | 10.11 | 0.095706 | 0.00119 | 168 | 0.46241 | 0.077068 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.46241 | 20.3207 | 20.3207 | 0%
Central Coast | LP_Los Padres | SANTA YNEZ 1104 | 934 | SANTA YNEZ 1104Y66 | 22.7873 | 364.5567 | 15.0167 | 0 | 15.0167 | 0 | 328 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 1 | 608 |  | 112 | 74 | 608 | 112 | 74 | 208.16 | 0.062507 | 0.01456 | 169 | 6.7651 | 0.076876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 6.7651 | 7.4584 | 7.4584 | 0%
North Valley | NV_North Valley | COTTONWOOD 1103 | 4646 | COTTONWOOD 11039072 | 52.0509 | 749.9505 | 29.4366 | 28.3593 | 1.0773 | 29.4366 | 979 | 3472 | 937 | 504 | 931 | 501 | 0 | 931 | 0 | 3472 |  | 937 | 504 | 0 | 6 | 3 | 8.22 | 0.069406 | 0.00087 | 170 | 19.5548 | 0.076685 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.71563 | 5.5696 | 31.8312 | 96.34%
Sierra | SI_Sierra | SHINGLE SPRINGS 2109 | 2804 | SHINGLE SPRINGS 21099372 | 28.7988 | 426.2538 | 19.4159 | 0.81458 | 18.6013 | 0.81458 | 1616 | 107 | 9 | 6 | 9 | 6 | 0 | 438 | 0.95805 | 2930 |  | 520 | 344 | 2823 | 511 | 338 | 954.14 | 0.067563 | 0.07179 | 171 | 16.6995 | 0.076254 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 15.9989 | 27.4712 | 26.7822 | 4.195%
North Coast | HU_Humboldt | POTTER VALLEY P H 1104 | 4127 | POTTER VALLEY P H 110495878 | 7.2244 | 139.0708 | 5.6267 | 0.24261 | 5.3841 | 0.37443 | 424 | 20 | 5 | 0 | 0 | 0 | 0 | 102 | 0.93345 | 750 |  | 139 | 89 | 730 | 139 | 89 | 256.13 | 0.051948 | 0.01501 | 172 | 3.6201 | 0.075419 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 3.464 | 25.8168 | 24.7036 | 4.312%
Central Valley | YO_Yosemite | OAKHURST 1101 | 2763 | OAKHURST 110110090 | 80.1746 | 1092.1389 | 43.679 | 17.018 | 26.661 | 32.678 | 4966 | 8969 | 3516 | 1704 | 1817 | 954 | 0 | 1571 | 0.25186 | 11243 |  | 3927 | 1975 | 2274 | 2110 | 1021 | 3095.36 | 0.073411 | 0.32209 | 173 | 40.6671 | 0.075309 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 24.8226 | 79.1419 | 89.906 | 38.96%
North Valley | NV_North Valley | JESSUP 1102 | 2247 | JESSUP 11021550 | 27.5019 | 384.8272 | 17.8619 | 0 | 17.8619 | 0 | 824 | 0 | 0 | 0 | 0 | 0 | 0 | 430 | 1 | 1509 |  | 274 | 181 | 1509 | 274 | 181 | 511.19 | 0.071466 | 0.04072 | 174 | 15.5885 | 0.075307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 15.5885 | 15.3399 | 15.3399 | 0%
Central Valley | FR_Fresno | SAND CREEK 1103 | 4022 | SAND CREEK 11037420 | 39.9428 | 601.8799 | 23.6663 | 0 | 23.6663 | 0 | 646 | 0 | 0 | 0 | 0 | 0 | 0 | 533 | 1 | 1185 |  | 216 | 143 | 1185 | 216 | 143 | 402.57 | 0.066363 | 0.02981 | 175 | 13.2578 | 0.074482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 13.2578 | 9.1269 | 9.1269 | 0%
North Coast | HU_Humboldt | UPPER LAKE 1101 | 6306 | UPPER LAKE 1101412 | 21.3648 | 318.1549 | 11.36 | 5.4587 | 5.9013 | 11.36 | 969 | 1108 | 224 | 93 | 11 | 0 | 0 | 309 | 0 | 1108 |  | 224 | 93 | 0 | 213 | 93 | 291.81 | 0.067152 | 0.02974 | 176 | 7.671 | 0.074476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 3.985 | 36.0936 | 19.7182 | 48.05%
North Valley | NV_North Valley | COTTONWOOD 1102 | 338 | COTTONWOOD 1101circuit_breaker | 10.1389 | 122.7623 | 6.0006 | 0.10152 | 5.8991 | 0.10152 | 417 | 16 | 2 | 2 | 2 | 2 | 0 | 159 | 0.98308 | 773 |  | 140 | 94 | 757 | 138 | 92 | 257.19 | 0.08259 | 0.0237 | 177 | 4.4498 | 0.074164 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 4.3745 | 23.3936 | 23.3311 | 1.692%
North Valley | NV_North Valley | ELK CREEK 1101 | 4335 | ELK CREEK 11012228 | 5.5914 | 68.1758 | 3.282 | 0 | 3.282 | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 1 | 292 |  | 55 | 37 | 292 | 55 | 37 | 101.63 | 0.082014 | 0.00938 | 178 | 1.773 | 0.073876 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 1.773 | 16.758 | 16.758 | 0%
Central Valley | FR_Fresno | KERCKHOFF 1101 | 603 | KERCKHOFF 1101circuit_breaker | 20.1482 | 396.1296 | 16.9032 | 0 | 16.9032 | 0.27216 | 451 | 7 | 2 | 2 | 2 | 2 | 0 | 346 | 0.9839 | 825 |  | 151 | 101 | 818 | 149 | 99 | 277.75 | 0.050863 | 0.01576 | 179 | 3.1027 | 0.073873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 3.1027 | 8.8149 | 8.9332 | 0%
Sierra | SI_Sierra | DIAMOND SPRINGS 1105 | 2148 | DIAMOND SPRINGS 110519910 | 40.6295 | 497.7959 | 18.9657 | 0.36667 | 18.5989 | 1.4812 | 1526 | 57 | 3 | 3 | 0 | 0 | 0 | 957 | 0.9219 | 2623 |  | 468 | 310 | 2566 | 468 | 310 | 872.1 | 0.081619 | 0.07943 | 180 | 17.8631 | 0.073814 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 17.5176 | 25.1628 | 24.6761 | 1.933%
Central Coast | LP_Los Padres | ZACA 1102 | 5296 | ZACA 1102circuit_breaker | 21.5156 | 362.5909 | 16.8763 | 0 | 16.8763 | 0 | 292 | 0 | 0 | 0 | 0 | 0 | 0 | 279 | 1 | 543 |  | 100 | 67 | 543 | 100 | 67 | 185.87 | 0.059338 | 0.01234 | 181 | 8.015 | 0.073532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 8.015 | 5.9255 | 5.9255 | 0%
North Coast | SO_Sonoma | CLOVERDALE 1102 | 4894 | CLOVERDALE 1102156 | 12.9702 | 146.0544 | 5.4839 | 0.99167 | 4.4924 | 5.3458 | 408 | 111 | 94 | 60 | 49 | 23 | 0 | 195 | 0.025177 | 130 |  | 97 | 62 | 19 | 48 | 39 | 67.47 | 0.088804 | 0.00886 | 182 | 5.0391 | 0.07303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 4.128 | 10.6847 | 17.6881 | 18.08%
North Valley | NV_North Valley | JESSUP 1103 | 2565 | JESSUP 11031540 | 3.4986 | 46.0882 | 2.5928 | 0 | 2.5928 | 0 | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 1 | 566 |  | 104 | 69 | 566 | 104 | 69 | 193.42 | 0.075911 | 0.01642 | 183 | 1.823 | 0.072922 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 1.823 | 40.111 | 40.111 | 0%
Central Valley | FR_Fresno | SAND CREEK 1103 | 1366 | SAND CREEK 110345190 | 66.6137 | 958.6136 | 36.5509 | 0.1125 | 36.4384 | 0.1125 | 1497 | 2 | 0 | 0 | 0 | 0 | 0 | 807 | 0.99692 | 2724 |  | 493 | 326 | 2722 | 493 | 326 | 920.39 | 0.06949 | 0.07124 | 184 | 26.7484 | 0.072884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 26.666 | 13.5297 | 13.488 | 0.3078%
North Coast | HU_Humboldt | REDBUD 1101 | 1853 | REDBUD 1101323962 | 33.7865 | 490.3082 | 19.9731 | 14.0083 | 5.9648 | 19.9731 | 1041 | 2301 | 632 | 319 | 386 | 140 | 0 | 827 | 0 | 2301 |  | 632 | 319 | 0 | 246 | 179 | 337.02 | 0.068909 | 0.03525 | 185 | 11.224 | 0.072883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 3.3519 | 41.2421 | 31.6425 | 70.14%
Central Valley | FR_Fresno | TIVY VALLEY 1107 | 1871 | TIVY VALLEY 1107R1817 | 23.1674 | 451.1694 | 18.7248 | 5.0761 | 13.6487 | 18.454 | 351 | 2242 | 1046 | 962 | 14 | 10 | 0 | 296 | 0.014464 | 2251 |  | 1048 | 963 | 9 | 1034 | 953 | 1417.39 | 0.05135 | 0.11041 | 186 | 8.0879 | 0.072213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1. <= 10% | 1. <= 10% | 5.8953 | 75.7583 | 55.9685 | 27.11%
Sierra | SI_Sierra | BELL 1108 | 6490 | BELL 11085703 | 6.5267 | 110.0401 | 5.0436 | 0.18447 | 4.8591 | 0.2358 | 867 | 124 | 50 | 48 | 45 | 44 | 0 | 166 | 0.95325 | 1637 |  | 325 | 230 | 1513 | 280 | 186 | 519.77 | 0.059312 | 0.03453 | 187 | 5.308 | 0.07173 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 5.1139 | 57.6239 | 64.4386 | 3.658%
Sierra | SA_Sacramento | VACAVILLE 1111 | 56 | VACAVILLE 1111circuit_breaker | 11.9443 | 133.6221 | 5.1583 | 4.2314 | 0.92708 | 5.0564 | 342 | 1258 | 437 | 307 | 414 | 291 | 0 | 244 | 0.019753 | 1271 |  | 439 | 309 | 13 | 25 | 18 | 35.42 | 0.089388 | 0.00465 | 188 | 6.5268 | 0.071723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 1.173 | 26.9663 | 85.105 | 82.03%
North Coast | HU_Humboldt | MIDDLETOWN 1101 | 2173 | MIDDLETOWN 1101circuit_breaker | 15.9971 | 245.9501 | 9.4739 | 7.3174 | 2.1564 | 8.4144 | 528 | 600 | 196 | 139 | 144 | 108 | 0 | 399 | 0.11183 | 709 |  | 216 | 152 | 109 | 72 | 44 | 108.45 | 0.065042 | 0.00974 | 189 | 5.5864 | 0.071621 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 1.2716 | 33.3884 | 22.7996 | 77.24%
Central Valley | ST_Stockton | CORRAL 1101 | 60 | CORRAL 110175204 | 0.34995 | 5.2111 | 0.8553 | 0.80549 | 0.049811 | 0.8553 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.067155 | 0 | 190 | 0.071046 | 0.071046 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.0041375 | 0 | 0 | 94.18%
Sierra | SA_Sacramento | JAMESON 1105 | 3481 | JAMESON 11057652 | 24.4607 | 369.9677 | 16.4076 | 0 | 16.4076 | 0 | 1171 | 0 | 0 | 0 | 0 | 0 | 0 | 358 | 1 | 2139 |  | 388 | 256 | 2139 | 388 | 256 | 724.07 | 0.066116 | 0.05334 | 191 | 12.1773 | 0.070389 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 12.1773 | 23.6476 | 23.6476 | 0%
North Coast | HU_Humboldt | CLEAR LAKE 1101 | 3437 | CLEAR LAKE 1101406 | 10.6248 | 221.5172 | 6.0794 | 3.6439 | 2.4354 | 5.9828 | 411 | 472 | 95 | 39 | 0 | 0 | 0 | 127 | 0.015888 | 484 |  | 97 | 40 | 12 | 97 | 40 | 133.97 | 0.047964 | 0.00967 | 192 | 5.2455 | 0.06994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 2.1014 | 39.8289 | 15.9556 | 59.94%
Bay Area | DI_Diablo | WILLOW PASS 2107 | 7479 | WILLOW PASS 2107P500R | 0.47343 | 24.2629 | 0.92765 | 0 | 0.92765 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1 | 20 |  | 5 | 5 | 20 | 5 | 5 | 8.65 | 0.019513 | 0.0002 | 193 | 0.069642 | 0.069642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.069642 | 5.39 | 5.39 | 0%
Sierra | SI_Sierra | WISE 1102 | 6227 | WISE 1102697216 | 22.2986 | 276.2612 | 11.6246 | 0.016288 | 11.6083 | 0.1303 | 763 | 6 | 4 | 4 | 0 | 0 | 0 | 427 | 0.98879 | 1388 |  | 255 | 170 | 1382 | 255 | 170 | 473.73 | 0.080716 | 0.0428 | 194 | 7.5068 | 0.069507 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 7.4963 | 21.967 | 21.9362 | 0.1401%
Bay Area | DI_Diablo | CLAYTON 2215 | 3424 | CLAYTON 2215circuit_breaker | 2.4615 | 50.2241 | 2.2091 | 0 | 2.2091 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 1 | 30 |  | 7 | 6 | 30 | 7 | 6 | 12.29 | 0.049011 | 0.00071 | 195 | 0.48593 | 0.069419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.48593 | 3.1687 | 3.1687 | 0%
North Valley | NV_North Valley | WYANDOTTE 1106 | 1887 | WYANDOTTE 110641650 | 2.1496 | 31.1466 | 1.4237 | 0 | 1.4237 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 1 | 36 |  | 8 | 6 | 36 | 8 | 6 | 14.2 | 0.069016 | 0.00115 | 196 | 0.13876 | 0.06938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.13876 | 5.6193 | 5.6193 | 0%
Sierra | SI_Sierra | PENRYN 1107 | 5552 | PENRYN 11072704 | 0.94925 | 36.918 | 2.1483 | 0 | 2.1483 | 0 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1 | 539 |  | 99 | 66 | 539 | 99 | 66 | 184.14 | 0.025712 | 0.00529 | 197 | 1.3814 | 0.06907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 1.3814 | 46.083 | 46.083 | 0%
North Valley | NV_North Valley | DESCHUTES 1101 | 7817 | DESCHUTES 11019722 | 7.1903 | 94.1121 | 4.289 | 0 | 4.289 | 0 | 335 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 1 | 621 |  | 114 | 76 | 621 | 114 | 76 | 212.07 | 0.076402 | 0.01811 | 198 | 2.7455 | 0.068637 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 2.7455 | 26.5795 | 26.5795 | 0%
Sierra | SA_Sacramento | PUTAH CREEK 1105 | 8201 | PUTAH CREEK 110546162 | 0.87988 | 14.0087 | 0.69924 | 0 | 0.69924 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1 | 43 |  | 10 | 7 | 43 | 10 | 7 | 17.57 | 0.062809 | 0.00131 | 199 | 0.54729 | 0.068411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.54729 | 14.3012 | 14.3012 | 0%
Sierra | SA_Sacramento | MADISON 2101 | 6093 | MADISON 21011606 | 0.55905 | 8.8109 | 0.47614 | 0 | 0.47614 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 25 |  | 6 | 5 | 25 | 6 | 5 | 10.47 | 0.06345 | 0.00079 | 200 | 0.068058 | 0.068058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.068058 | 12.6014 | 12.6014 | 0%
Sierra | SI_Sierra | BELL 1108 | 4798 | BELL 11082202 | 49.3606 | 756.6967 | 32.0807 | 2.2634 | 29.8174 | 2.5299 | 2867 | 339 | 122 | 105 | 105 | 96 | 0 | 1182 | 0.92114 | 5146 |  | 991 | 678 | 4807 | 886 | 582 | 1646.45 | 0.065232 | 0.12018 | 201 | 28.2975 | 0.068023 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 26.3011 | 29.7142 | 30.8909 | 7.055%
Bay Area | NB_North Bay | LAS GALLINAS A 1105 | 7713 | LAS GALLINAS A 110599904 | 10.8893 | 161.0908 | 5.7083 | 0.24261 | 5.4655 | 0.27235 | 2220 | 182 | 37 | 14 | 30 | 11 | 0 | 119 | 0.95229 | 4033 |  | 733 | 474 | 3851 | 703 | 463 | 1309.7 | 0.067598 | 0.09882 | 202 | 6.0985 | 0.067762 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 5.8391 | 128.6243 | 128.4088 | 4.25%
Bay Area | NB_North Bay | CALISTOGA 1101 | 389 | CALISTOGA 1101734 | 18.3565 | 341.7057 | 14.107 | 7.7873 | 6.3197 | 13.9511 | 3204 | 5339 | 1311 | 796 | 485 | 256 | 1 | 624 | 0.011049 | 5403 |  | 1323 | 804 | 64 | 838 | 548 | 1153.82 | 0.05372 | 0.09361 | 203 | 12.2262 | 0.067548 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1. <= 10% | 1. <= 10% | 5.4771 | 132.6013 | 93.7832 | 55.2%
Central Coast | LP_Los Padres | PASO ROBLES 1104 | 834 | PASO ROBLES 1104R56 | 13.7564 | 222.7828 | 10.2625 | 0.28106 | 9.9814 | 0.28106 | 304 | 30 | 0 | 0 | 0 | 0 | 0 | 172 | 0.97261 | 579 |  | 101 | 67 | 549 | 101 | 67 | 187.78 | 0.061748 | 0.01297 | 204 | 6.4068 | 0.06605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 6.2314 | 10.1188 | 9.8417 | 2.739%
Central Valley | ST_Stockton | CORRAL 1102 | 1329 | CORRAL 1102circuit_breaker | 24.7765 | 348.7853 | 17.2555 | 0 | 17.2555 | 0 | 304 | 0 | 0 | 0 | 0 | 0 | 0 | 398 | 1 | 564 |  | 104 | 69 | 564 | 104 | 69 | 193.24 | 0.071037 | 0.01536 | 205 | 9.7731 | 0.066034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 9.7731 | 6.0271 | 6.0271 | 0%
Central Valley | FR_Fresno | AUBERRY 1101 | 4967 | AUBERRY 1101R2578 | 74.3355 | 1142.1598 | 48.1706 | 8.6125 | 39.5581 | 20.7544 | 2274 | 2839 | 839 | 657 | 5 | 4 | 1 | 1736 | 0.56915 | 5196 |  | 1265 | 938 | 2357 | 1260 | 934 | 1938.33 | 0.065083 | 0.17052 | 206 | 27.8557 | 0.066009 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 22.8753 | 31.8518 | 26.2608 | 17.88%
Sierra | SA_Sacramento | MADISON 2101 | 248 | MADISON 210189332 | 0.17136 | 4.8588 | 1.086 | 0 | 1.086 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 36 |  | 8 | 6 | 36 | 8 | 6 | 14.2 | 0.035268 | 0.00059 | 207 | 0.13195 | 0.065976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.13195 | 7.3666 | 7.3666 | 0%
North Coast | HU_Humboldt | UPPER LAKE 1101 | 4477 | UPPER LAKE 1101660 | 6.9147 | 142.782 | 6.3845 | 3.5165 | 2.868 | 6.3845 | 349 | 595 | 103 | 27 | 0 | 0 | 0 | 170 | 0 | 595 |  | 103 | 27 | 0 | 103 | 27 | 141.11 | 0.048428 | 0.01037 | 208 | 3.2948 | 0.065896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 1.4801 | 35.9136 | 16.1329 | 55.08%
Central Valley | YO_Yosemite | COARSEGOLD 2104 | 5956 | COARSEGOLD 210490356 | 3.7462 | 109.4883 | 4.2108 | 4.01 | 0.20076 | 4.0102 | 29 | 93 | 10 | 9 | 10 | 9 | 0 | 114 | 0.047632 | 96 |  | 11 | 9 | 3 | 1 | 0 | 1.64 | 0.034215 | 7e-05 | 209 | 1.1744 | 0.065242 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.055989 | 4.9811 | 2.6123 | 95.23%
North Valley | NV_North Valley | JESSUP 1102 | 2425 | JESSUP 11021314 | 9.0661 | 125.7287 | 6.3333 | 0 | 6.3333 | 0 | 503 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 1 | 926 |  | 169 | 112 | 926 | 169 | 112 | 314.87 | 0.072108 | 0.02534 | 210 | 3.8877 | 0.064794 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 3.8877 | 26.6842 | 26.6842 | 0%
North Valley | NV_North Valley | STILLWATER 1102 | 4317 | STILLWATER 1102circuit_breaker | 37.1824 | 564.3379 | 25.5741 | 0 | 25.5741 | 0 | 4181 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 1 | 7605 |  | 1374 | 906 | 7605 | 1374 | 906 | 2566.83 | 0.065887 | 0.18825 | 211 | 21.6253 | 0.064746 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 21.6253 | 53.7263 | 53.7263 | 0%
North Coast | HU_Humboldt | WILLITS 1103 | 9224 | WILLITS 1103circuit_breaker | 5.7628 | 82.4427 | 2.8517 | 0 | 2.8517 | 0 | 447 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1 | 824 |  | 151 | 100 | 824 | 151 | 100 | 281.03 | 0.069901 | 0.02195 | 212 | 2.266 | 0.064742 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 2.266 | 52.9508 | 52.9508 | 0%
North Valley | NV_North Valley | WYANDOTTE 1109 | 5326 | WYANDOTTE 1109circuit_breaker | 2.8415 | 63.092 | 2.4739 | 0 | 2.4739 | 0 | 203 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 1 | 381 |  | 71 | 47 | 381 | 71 | 47 | 131.56 | 0.045038 | 0.00665 | 213 | 1.7162 | 0.063562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 1.7162 | 28.7 | 28.7 | 0%
Central Valley | YO_Yosemite | COARSEGOLD 2104 | 1088 | COARSEGOLD 210410030 | 19.6693 | 308.6777 | 13.8947 | 13.2278 | 0.66686 | 13.8907 | 286 | 952 | 171 | 160 | 163 | 152 | 0 | 325 | 0.00028624 | 952 |  | 171 | 160 | 0 | 8 | 8 | 10.96 | 0.063721 | 0.00106 | 214 | 5.1287 | 0.063318 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.24615 | 11.9966 | 12.3069 | 95.2%
North Valley | NV_North Valley | VOLTA 1101 | 8700 | VOLTA 110165764 | 1.9261 | 210.1221 | 9.6858 | 0 | 9.6858 | 0 | 609 | 0 | 0 | 0 | 0 | 0 | 0 | 147 | 1 | 1118 |  | 204 | 135 | 1118 | 204 | 135 | 380.1 | 0.0091667 | 0.00389 | 215 | 0.18905 | 0.063015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.18905 | 21.0618 | 21.0618 | 0%
North Coast | SO_Sonoma | FITCH MOUNTAIN 1113 | 5211 | FITCH MOUNTAIN 111324918 | 9.3099 | 156.3161 | 5.7612 | 0.048674 | 5.7127 | 5.2163 | 3982 | 494 | 494 | 3 | 1 | 0 | 0 | 245 | 0.094579 | 1179 |  | 618 | 85 | 685 | 617 | 85 | 906.94 | 0.059558 | 0.07641 | 216 | 5.7824 | 0.062852 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1. <= 10% | 1. <= 10% | 5.7337 | 108.0052 | 107.2698 | 0.8449%
North Valley | NV_North Valley | COTTONWOOD 1103 | 466 | COTTONWOOD 11031616 | 64.1053 | 1064.3078 | 46.504 | 44.4903 | 2.0136 | 46.2415 | 1592 | 5185 | 937 | 450 | 932 | 449 | 0 | 1436 | 0.0056447 | 5201 |  | 940 | 452 | 16 | 8 | 3 | 12.4 | 0.060232 | 0.001 | 217 | 26.3137 | 0.062652 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 1.1394 | 3.9729 | 20.2133 | 95.67%
North Coast | HU_Humboldt | CALPELLA 1101 | 7963 | CALPELLA 11013419 | 12.1801 | 154.9958 | 6.1479 | 0 | 6.1479 | 0 | 972 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 1 | 1777 |  | 323 | 213 | 1777 | 323 | 213 | 602.44 | 0.078583 | 0.05278 | 218 | 3.4974 | 0.062453 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 3.4974 | 52.5381 | 52.5381 | 0%
Sierra | SI_Sierra | LINCOLN 1101 | 2009 | LINCOLN 11042072 | 1.139 | 4.0652 | 0.28371 | 0 | 0.28371 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 41 |  | 9 | 7 | 41 | 9 | 7 | 16.02 | 0.28018 | 0.00524 | 219 | 0.31165 | 0.062331 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 0.31165 | 31.7223 | 31.7223 | 0%
Bay Area | DI_Diablo | KIRKER 2104 | 9469 | KIRKER 2104442850 | 6.0975 | 129.7892 | 4.8902 | 0 | 4.8902 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 1 | 70 |  | 15 | 11 | 70 | 15 | 11 | 26.85 | 0.04698 | 0.00147 | 220 | 1.0594 | 0.062315 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 1.0594 | 3.0674 | 3.0674 | 0%
Sierra | SI_Sierra | HIGGINS 1109 | 5504 | HIGGINS 110950072 | 72.6416 | 1260.8789 | 51.4699 | 0 | 51.4699 | 0 | 5632 | 0 | 0 | 0 | 0 | 0 | 0 | 1104 | 1 | 10240 |  | 1849 | 1219 | 10240 | 1849 | 1219 | 3454.73 | 0.057612 | 0.22151 | 221 | 42.0939 | 0.062269 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 42.0939 | 35.9239 | 35.9239 | 0%
North Coast | SO_Sonoma | GEYSERVILLE 1101 | 2778 | GEYSERVILLE 1101166 | 18.0682 | 288.78 | 11.1278 | 0 | 11.1278 | 0 | 2885 | 0 | 0 | 0 | 0 | 0 | 0 | 199 | 1 | 5251 |  | 949 | 626 | 5251 | 949 | 626 | 1772.72 | 0.062567 | 0.12347 | 222 | 9.9522 | 0.062201 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 9.9522 | 85.2816 | 85.2816 | 0%
North Valley | NV_North Valley | OREGON TRAIL 1102 | 4708 | OREGON TRAIL 1102circuit_breaker | 11.1362 | 197.2755 | 8.8905 | 1.0165 | 7.8741 | 2.6239 | 762 | 495 | 67 | 63 | 1 | 0 | 0 | 321 | 0.70487 | 1479 |  | 246 | 181 | 984 | 245 | 181 | 424.21 | 0.05645 | 0.02876 | 223 | 7.6221 | 0.061968 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 6.7506 | 31.1149 | 27.6699 | 11.43%
Sierra | SI_Sierra | SHINGLE SPRINGS 2109 | 1980 | SHINGLE SPRINGS 210912392 | 22.9044 | 361.9534 | 14.6294 | 0 | 14.6294 | 0 | 2074 | 0 | 0 | 0 | 0 | 0 | 0 | 355 | 1 | 3779 |  | 683 | 451 | 3779 | 683 | 451 | 1275.82 | 0.06328 | 0.08987 | 224 | 11.1292 | 0.061829 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 11.1292 | 46.6869 | 46.6869 | 0%
Central Valley | YO_Yosemite | COARSEGOLD 2103 | 698 | COARSEGOLD 2103circuit_breaker | 57.1234 | 909.0223 | 36.3254 | 0.19356 | 36.1316 | 0.26326 | 1422 | 49 | 12 | 11 | 8 | 7 | 0 | 710 | 0.99275 | 2625 |  | 479 | 319 | 2576 | 471 | 312 | 877.11 | 0.062841 | 0.06155 | 225 | 26.0295 | 0.061681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 25.8906 | 13.0357 | 13.1864 | 0.5329%
Central Coast | LP_Los Padres | SANTA YNEZ 1102 | 6799 | SANTA YNEZ 1102circuit_breaker | 2.1515 | 24.3058 | 1.382 | 0 | 1.382 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 1 | 78 |  | 16 | 11 | 78 | 16 | 11 | 28.94 | 0.088517 | 0.00295 | 226 | 0.8015 | 0.061653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.8015 | 11.5774 | 11.5774 | 0%
North Coast | SO_Sonoma | CLOVERDALE 1101 | 1466 | CLOVERDALE 1101circuit_breaker | 6.4256 | 137.4719 | 5.4456 | 0 | 5.4456 | 0.36042 | 1138 | 10 | 10 | 3 | 5 | 0 | 0 | 82 | 0.93382 | 1951 |  | 362 | 236 | 1941 | 357 | 236 | 663.78 | 0.046741 | 0.0347 | 227 | 4.1223 | 0.061527 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 4.1223 | 65.557 | 66.4752 | 0%
North Valley | NV_North Valley | CORNING 1101 | 3817 | CORNING 110164090 | 17.2935 | 283.4994 | 13.3193 | 12.4138 | 0.90549 | 13.3193 | 532 | 2604 | 231 | 190 | 228 | 187 | 0 | 460 | 0 | 2604 |  | 231 | 190 | 0 | 3 | 3 | 4.11 | 0.061 | 0.00038 | 228 | 10.0231 | 0.061492 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.68141 | 3.3131 | 17.3432 | 93.2%
Central Coast | LP_Los Padres | SAN MIGUEL 1104 | 6065 | SAN MIGUEL 1104N60 | 8.5446 | 163.5887 | 8.2019 | 0 | 8.2019 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 1 | 96 |  | 19 | 14 | 96 | 19 | 14 | 34.67 | 0.052232 | 0.00206 | 229 | 3.0085 | 0.061398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 3.0085 | 2.3165 | 2.3165 | 0%
North Coast | HU_Humboldt | POTTER VALLEY P H 1105 | 6417 | POTTER VALLEY P H 110537476 | 2.9718 | 47.5285 | 2.6305 | 0.7214 | 1.9091 | 2.6305 | 434 | 511 | 204 | 106 | 23 | 10 | 0 | 74 | 0 | 511 |  | 204 | 106 | 0 | 181 | 96 | 247.97 | 0.062528 | 0.02353 | 230 | 1.2189 | 0.060947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 0.88465 | 94.8095 | 77.552 | 27.42%
Sierra | SI_Sierra | CLARKSVILLE 2104 | 6626 | CLARKSVILLE 2104circuit_breaker | 14.5909 | 216.0468 | 8.2657 | 5.5438 | 2.722 | 5.8045 | 214 | 482 | 168 | 130 | 167 | 130 | 0 | 250 | 0.29776 | 601 |  | 190 | 145 | 119 | 23 | 15 | 42.22 | 0.067536 | 0.00323 | 231 | 2.1887 | 0.060796 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.72075 | 8.4498 | 22.9865 | 67.07%
North Valley | NV_North Valley | CORNING 1102 | 888 | CORNING 110290036 | 13.9388 | 253.1344 | 14.3828 | 0 | 14.3828 | 0 | 279 | 0 | 0 | 0 | 0 | 0 | 0 | 249 | 1 | 519 |  | 96 | 64 | 519 | 96 | 64 | 178.23 | 0.055065 | 0.01099 | 232 | 3.2148 | 0.060656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 3.2148 | 6.6747 | 6.6747 | 0%
Sierra | SI_Sierra | HIGGINS 1109 | 6195 | HIGGINS 110950078 | 69.0697 | 1166.4895 | 46.9655 | 0 | 46.9655 | 0 | 1856 | 0 | 0 | 0 | 0 | 0 | 0 | 974 | 1 | 3383 |  | 612 | 404 | 3383 | 612 | 404 | 1142.91 | 0.059212 | 0.07535 | 233 | 30.4436 | 0.060404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1. <= 10% | 1. <= 10% | 30.4436 | 13.0308 | 13.0308 | 0%
Bay Area | NB_North Bay | SILVERADO 2104 | 5665 | SILVERADO 2104632 | 43.8387 | 506.2742 | 18.6242 | 11.3252 | 7.2991 | 18.6233 | 5726 | 14072 | 4012 | 2349 | 3305 | 1862 | 1 | 819 | 5.0846e-05 | 14073 |  | 4012 | 2349 | 1 | 707 | 487 | 968.68 | 0.086591 | 0.1273 | 234 | 13.0187 | 0.060272 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 5.1022 | 96.8619 | 215.4182 | 60.81%
North Coast | HU_Humboldt | HIGHLANDS 1102 | 7360 | HIGHLANDS 1102628 | 16.8587 | 329.9933 | 14.0894 | 11.3208 | 2.7686 | 13.8936 | 276 | 688 | 192 | 170 | 96 | 86 | 0 | 344 | 0.013899 | 695 |  | 193 | 171 | 7 | 97 | 85 | 133.52 | 0.051088 | 0.0103 | 235 | 4.3771 | 0.059961 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 0.8601 | 35.0363 | 13.6982 | 80.35%
North Valley | NV_North Valley | RED BLUFF 1104 | 1731 | RED BLUFF 110451238 | 50.3068 | 925.582 | 38.3432 | 37.1252 | 1.2178 | 38.2102 | 926 | 3685 | 165 | 117 | 158 | 115 | 0 | 1132 | 0.0034675 | 3691 |  | 166 | 118 | 6 | 8 | 3 | 11.5 | 0.054352 | 0.0009 | 236 | 17.968 | 0.059694 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.57068 | 6.5692 | 4.3293 | 96.82%
North Valley | NV_North Valley | JESSUP 1101 | 1610 | JESSUP 1101circuit_breaker | 1.8372 | 34.7173 | 1.5199 | 0 | 1.5199 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1 | 167 |  | 32 | 22 | 167 | 32 | 22 | 58.87 | 0.052919 | 0.00352 | 237 | 0.71147 | 0.059289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.71147 | 21.0542 | 21.0542 | 0%
North Coast | HU_Humboldt | GARBERVILLE 1101 | 6674 | GARBERVILLE 110139524 | 4.4456 | 99.7396 | 5.0252 | 0 | 5.0252 | 0 | 1146 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 1 | 2093 |  | 380 | 251 | 2093 | 380 | 251 | 708.97 | 0.044572 | 0.03522 | 238 | 3.4903 | 0.059158 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 3.4903 | 75.619 | 75.619 | 0%
Central Coast | SJ_San Jose | MORGAN HILL 2105 | 3082 | MORGAN HILL 2105XR564 | 11.3128 | 130.6132 | 5.2131 | 0 | 5.2131 | 0 | 181 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 1 | 341 |  | 63 | 43 | 341 | 63 | 43 | 117 | 0.086613 | 0.01135 | 239 | 2.4234 | 0.059107 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 4. >30 - 40% | 2.4234 | 12.085 | 12.085 | 0%
North Valley | NV_North Valley | ELK CREEK 1101 | 8921 | ELK CREEK 11012032 | 6.1679 | 227.1595 | 8.5733 | 0 | 8.5733 | 0 | 311 | 0 | 0 | 0 | 0 | 0 | 0 | 149 | 1 | 577 |  | 106 | 71 | 577 | 106 | 71 | 197.15 | 0.027152 | 0.00598 | 240 | 3.3028 | 0.058979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 3.3028 | 12.364 | 12.364 | 0%
North Valley | NV_North Valley | CORNING 1102 | 322 | CORNING 110253184 | 27.577 | 626.0037 | 30.7856 | 0 | 30.7856 | 0 | 494 | 0 | 0 | 0 | 0 | 0 | 0 | 494 | 1 | 909 |  | 166 | 110 | 909 | 166 | 110 | 309.23 | 0.044053 | 0.01521 | 241 | 6.8716 | 0.058732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 6.8716 | 5.3921 | 5.3921 | 0%
Bay Area | MI_Mission | NORTH DUBLIN 2103 | 7388 | NORTH DUBLIN 21039473 | 2.5432 | 36.8137 | 1.5261 | 0 | 1.5261 | 0 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 1 | 290 |  | 54 | 37 | 290 | 54 | 37 | 100.08 | 0.069084 | 0.00776 | 242 | 1.4066 | 0.058607 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 1.4066 | 35.3835 | 35.3835 | 0%
Sierra | SI_Sierra | LINCOLN 1101 | 1057 | LINCOLN 110195756 | 8.0779 | 166.2376 | 8.5606 | 0 | 8.5606 | 0 | 1256 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 1 | 2293 |  | 416 | 275 | 2293 | 416 | 275 | 776.29 | 0.048592 | 0.04203 | 243 | 5.4906 | 0.05841 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 5.4906 | 48.5947 | 48.5947 | 0%
Central Valley | FR_Fresno | TIVY VALLEY 1107 | 6372 | TIVY VALLEY 1107584840 | 55.3272 | 1062.5445 | 44.2242 | 20.1606 | 24.0636 | 36.8972 | 1351 | 3328 | 863 | 649 | 148 | 98 | 0 | 869 | 0.16568 | 3737 |  | 937 | 698 | 409 | 789 | 600 | 1117.74 | 0.05207 | 0.08543 | 244 | 19.7021 | 0.05829 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 10.7204 | 32.7881 | 21.1875 | 45.59%
North Valley | NV_North Valley | ANDERSON 1103 | 3191 | ANDERSON 1103circuit_breaker | 6.584 | 115.1879 | 6.4496 | 0 | 6.4496 | 0 | 678 | 0 | 0 | 0 | 0 | 0 | 0 | 162 | 1 | 1243 |  | 226 | 150 | 1243 | 226 | 150 | 421.49 | 0.057159 | 0.02686 | 245 | 3.2314 | 0.057704 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 3.2314 | 35.0408 | 35.0408 | 0%
Central Valley | FR_Fresno | SAND CREEK 1103 | 8735 | SAND CREEK 11037823F | 8.553 | 129.268 | 5.5453 | 0 | 5.5453 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 1 | 105 |  | 21 | 15 | 105 | 21 | 15 | 38.22 | 0.066165 | 0.00289 | 246 | 1.4976 | 0.057599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 1.4976 | 3.787 | 3.787 | 0%
North Coast | HU_Humboldt | PHILO 1101 | 6519 | PHILO 110137222 | 28.9434 | 579.9983 | 25.1165 | 0 | 25.1165 | 0 | 3818 | 0 | 0 | 0 | 0 | 0 | 0 | 332 | 1 | 6946 |  | 1255 | 827 | 6946 | 1255 | 827 | 2344.49 | 0.049902 | 0.13023 | 247 | 11.3077 | 0.0574 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 11.3077 | 49.9672 | 49.9672 | 0%
Sierra | SI_Sierra | PENRYN 1105 | 3324 | PENRYN 11051378 | 0.15917 | 6.4452 | 0.79659 | 0 | 0.79659 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 1 | 127 |  | 25 | 17 | 127 | 25 | 17 | 45.68 | 0.024697 | 0.00128 | 248 | 0.80356 | 0.057397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.80356 | 31.3837 | 31.3837 | 0%
Central Valley | YO_Yosemite | MARIPOSA 2102 | 1025 | MARIPOSA 210237282 | 67.7459 | 1290.4946 | 52.3972 | 0.57822 | 51.8191 | 18.9994 | 3783 | 612 | 520 | 369 | 265 | 192 | 0 | 1786 | 0.6374 | 4999 |  | 1312 | 892 | 4387 | 1047 | 700 | 1829.22 | 0.052496 | 0.11429 | 249 | 30.1742 | 0.057365 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1. <= 10% | 1. <= 10% | 29.8414 | 20.2049 | 25.0395 | 1.104%
Sierra | SI_Sierra | SHINGLE SPRINGS 1103 | 8370 | SHINGLE SPRINGS 1103circuit_breaker | 9.5136 | 165.858 | 7.2883 | 0.031439 | 7.2566 | 0.031439 | 1002 | 5 | 0 | 0 | 0 | 0 | 0 | 169 | 0.99569 | 1829 |  | 331 | 219 | 1824 | 331 | 219 | 617.63 | 0.05736 | 0.03948 | 250 | 4.811 | 0.057274 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 4.7901 | 45.6135 | 45.4155 | 0.4314%
Bay Area | MI_Mission | CAYETANO 2109 | 3539 | CAYETANO 2109circuit_breaker | 23.4446 | 508.173 | 23.933 | 0 | 23.933 | 0 | 339 | 0 | 0 | 0 | 0 | 0 | 0 | 512 | 1 | 628 |  | 115 | 77 | 628 | 115 | 77 | 214.07 | 0.046135 | 0.01103 | 251 | 3.54 | 0.057097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 3.54 | 4.8051 | 4.8051 | 0%
North Valley | NV_North Valley | TYLER 1105 | 5848 | TYLER 110585132 | 39.1052 | 674.7312 | 30.7258 | 0 | 30.7258 | 0 | 895 | 0 | 0 | 0 | 0 | 0 | 0 | 596 | 1 | 1638 |  | 297 | 197 | 1638 | 297 | 197 | 554.31 | 0.057957 | 0.03579 | 252 | 14.6211 | 0.056452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 14.6211 | 9.6662 | 9.6662 | 0%
Sierra | SI_Sierra | SHINGLE SPRINGS 2109 | 2248 | SHINGLE SPRINGS 210913322 | 59.5538 | 1042.0542 | 40.3987 | 0 | 40.3987 | 0 | 4969 | 0 | 0 | 0 | 0 | 0 | 0 | 907 | 1 | 9036 |  | 1632 | 1076 | 9036 | 1632 | 1076 | 3049.08 | 0.05715 | 0.19395 | 253 | 33.0717 | 0.056436 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 33.0717 | 40.3974 | 40.3974 | 0%
North Coast | SO_Sonoma | COTATI 1105 | 1615 | COTATI 110599720 | 16.0693 | 247.0254 | 9.3739 | 6.5949 | 2.779 | 9.3739 | 1291 | 1882 | 520 | 57 | 463 | 44 | 0 | 389 | 0 | 1882 |  | 520 | 57 | 0 | 57 | 13 | 78.09 | 0.065051 | 0.00771 | 254 | 6.4876 | 0.056414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 1.9233 | 20.5111 | 55.4734 | 70.35%
North Valley | NV_North Valley | LOGAN CREEK 2102 | 4469 | LOGAN CREEK 21022226 | 3.2609 | 69.5731 | 3.5235 | 0 | 3.5235 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1 | 147 |  | 28 | 20 | 147 | 28 | 20 | 51.59 | 0.04687 | 0.00273 | 255 | 0.33546 | 0.05591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.33546 | 7.9467 | 7.9467 | 0%
North Valley | NV_North Valley | STILLWATER 1102 | 538 | STILLWATER 11021644 | 34.354 | 549.4635 | 23.1436 | 0.32841 | 22.8153 | 0.41515 | 2504 | 92 | 5 | 1 | 4 | 1 | 0 | 582 | 0.98206 | 4570 |  | 814 | 535 | 4478 | 810 | 534 | 1512.72 | 0.062523 | 0.10531 | 256 | 17.0159 | 0.055068 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 16.7746 | 35.5024 | 35.1718 | 1.419%
North Coast | SO_Sonoma | MOLINO 1102 | 6282 | MOLINO 110266006 | 11.4468 | 172.1029 | 6.6453 | 2.7563 | 3.889 | 6.6453 | 2392 | 2309 | 567 | 210 | 107 | 17 | 0 | 338 | 0 | 2309 |  | 567 | 210 | 0 | 460 | 193 | 630.2 | 0.066512 | 0.06362 | 257 | 7.7247 | 0.054399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 4.5207 | 118.2819 | 85.3239 | 41.48%
Central Valley | FR_Fresno | AUBERRY 1102 | 4896 | AUBERRY 1102R902 | 25.9579 | 353.2407 | 14.8794 | 0 | 14.8794 | 0 | 533 | 0 | 0 | 0 | 0 | 0 | 0 | 293 | 1 | 980 |  | 179 | 119 | 980 | 179 | 119 | 333.43 | 0.073485 | 0.02735 | 258 | 6.8827 | 0.054194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 6.8827 | 12.0301 | 12.0301 | 0%
Central Valley | FR_Fresno | COPPERMINE 1104 | 4582 | COPPERMINE 1104R755 | 9.7364 | 248.6783 | 9.0523 | 0.048106 | 9.0042 | 0.048106 | 107 | 3 | 1 | 0 | 0 | 0 | 0 | 151 | 0.99469 | 208 |  | 40 | 27 | 205 | 40 | 27 | 73.25 | 0.039152 | 0.00326 | 259 | 2.2177 | 0.05409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 2.2059 | 4.4424 | 4.4188 | 0.5314%
North Valley | NV_North Valley | JESSUP 1102 | 2297 | JESSUP 1102circuit_breaker | 3.6907 | 66.2159 | 2.2027 | 0 | 2.2027 | 0 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1 | 383 |  | 71 | 48 | 383 | 71 | 48 | 131.74 | 0.055737 | 0.00823 | 261 | 0.96923 | 0.053846 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 0.96923 | 32.2339 | 32.2339 | 0%
Sierra | SI_Sierra | BANGOR 1101 | 7890 | BANGOR 110131502 | 16.334 | 297.0612 | 12.7472 | 9.2667 | 3.4805 | 12.3483 | 623 | 1466 | 630 | 592 | 503 | 466 | 0 | 427 | 0.03129 | 1502 |  | 637 | 596 | 36 | 134 | 130 | 186.82 | 0.054985 | 0.01532 | 262 | 7.9408 | 0.053654 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 2.1682 | 38.5003 | 49.9719 | 72.7%
Sierra | SI_Sierra | HIGGINS 1109 | 5121 | HIGGINS 1109circuit_breaker | 44.4718 | 677.8852 | 27.6797 | 0 | 27.6797 | 0 | 3702 | 0 | 0 | 0 | 0 | 0 | 0 | 640 | 1 | 6735 |  | 1217 | 802 | 6735 | 1217 | 802 | 2273.44 | 0.065604 | 0.16602 | 263 | 18.3144 | 0.05324 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 18.3144 | 43.9672 | 43.9672 | 0%
North Valley | NV_North Valley | CEDAR CREEK 1101 | 39 | CEDAR CREEK 11011664 | 27.5241 | 707.4948 | 28.9169 | 0 | 28.9169 | 0 | 6530 | 0 | 0 | 0 | 0 | 0 | 0 | 661 | 1 | 11871 |  | 2143 | 1412 | 11871 | 2143 | 1412 | 4004.3 | 0.038904 | 0.17336 | 264 | 18.9423 | 0.05306 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 18.9423 | 74.109 | 74.109 | 0%
North Coast | SO_Sonoma | COTATI 1103 | 6814 | COTATI 1103circuit_breaker | 16.8301 | 369.0597 | 12.7763 | 0.50133 | 12.275 | 0.50133 | 229 | 26 | 0 | 0 | 0 | 0 | 0 | 258 | 0.96076 | 437 |  | 76 | 51 | 411 | 76 | 51 | 141.11 | 0.045603 | 0.00721 | 265 | 2.8651 | 0.053057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 2.7527 | 6.1914 | 5.9485 | 3.924%
Central Coast | LP_Los Padres | PASO ROBLES 1103 | 2246 | PASO ROBLES 110355374 | 3.2544 | 65.7145 | 2.5055 | 2.5055 | 0 | 2.5055 | 25 | 92 | 8 | 5 | 8 | 5 | 0 | 32 | 0 | 92 |  | 8 | 5 | 0 | 0 | 0 | 0 | 0.049524 | 0 | 266 | 0.68967 | 0.053052 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0 | 0 | 3.193 | 100%
Bay Area | DI_Diablo | TIDEWATER 2106 | 5581 | TIDEWATER 210614072 | 4.2008 | 93.8473 | 3.8555 | 0 | 3.8555 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 1 | 67 |  | 14 | 10 | 67 | 14 | 10 | 25.21 | 0.044762 | 0.0013 | 267 | 1.1585 | 0.052661 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 1.1585 | 3.6312 | 3.6312 | 0%
North Coast | NC_North Coast | RIO DELL 1102 | 6060 | RIO DELL 11024230 | 22.0562 | 463.151 | 22.7074 | 0 | 22.7074 | 0 | 11919 | 0 | 0 | 0 | 0 | 0 | 0 | 457 | 1 | 21657 |  | 3908 | 2575 | 21657 | 3908 | 2575 | 7303.09 | 0.047622 | 0.38699 | 268 | 18.5803 | 0.052487 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 18.5803 | 172.1026 | 172.1026 | 0%
Central Coast | LP_Los Padres | PASO ROBLES 1103 | 9000 | PASO ROBLES 110359763 | 3.0735 | 58.2765 | 3.1367 | 3.1367 | 0 | 3.1367 | 81 | 207 | 89 | 75 | 89 | 75 | 0 | 49 | 0 | 207 |  | 89 | 75 | 0 | 0 | 0 | 0 | 0.052739 | 0 | 269 | 1.6161 | 0.052132 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0 | 0 | 28.3734 | 100%
North Valley | NV_North Valley | CEDAR CREEK 1101 | 6632 | CEDAR CREEK 1101circuit_breaker | 26.7913 | 432.6591 | 15.8042 | 0 | 15.8042 | 0 | 966 | 0 | 0 | 0 | 0 | 0 | 0 | 354 | 1 | 1766 |  | 321 | 212 | 1766 | 321 | 212 | 598.71 | 0.061922 | 0.04133 | 270 | 8.1369 | 0.051828 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 8.1369 | 20.3111 | 20.3111 | 0%
Sierra | SI_Sierra | SHINGLE SPRINGS 2109 | 5074 | SHINGLE SPRINGS 21092679 | 8.0579 | 168.5214 | 7.06 | 0 | 7.06 | 0 | 601 | 0 | 0 | 0 | 0 | 0 | 0 | 149 | 1 | 1104 |  | 201 | 133 | 1104 | 201 | 133 | 374.73 | 0.047815 | 0.01998 | 271 | 4.2186 | 0.051446 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 4.2186 | 28.4701 | 28.4701 | 0%
North Coast | HU_Humboldt | LAYTONVILLE 1102 | 6617 | LAYTONVILLE 110268436 | 8.5955 | 206.4379 | 8.1735 | 0 | 8.1735 | 0 | 1609 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 1 | 2934 |  | 531 | 351 | 2934 | 531 | 351 | 991.53 | 0.041637 | 0.04597 | 272 | 3.8693 | 0.050912 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 3.8693 | 64.9662 | 64.9662 | 0%
Central Valley | ST_Stockton | CORRAL 1101 | 2402 | CORRAL 110112612 | 25.8429 | 476.9083 | 18.8055 | 18.2949 | 0.51061 | 18.8055 | 336 | 1002 | 138 | 68 | 129 | 62 | 0 | 610 | 0 | 1002 |  | 138 | 68 | 0 | 9 | 6 | 12.33 | 0.054188 | 0.00101 | 273 | 7.4541 | 0.050708 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.20239 | 17.6261 | 7.3383 | 97.28%
Central Valley | YO_Yosemite | OAKHURST 1103 | 1817 | OAKHURST 1103circuit_breaker | 38.7004 | 735.6037 | 31.5911 | 5.0324 | 26.5585 | 7.3866 | 4093 | 989 | 596 | 143 | 518 | 116 | 0 | 1766 | 0.76618 | 6693 |  | 1626 | 822 | 5704 | 1108 | 706 | 2031.32 | 0.05261 | 0.12121 | 274 | 22.972 | 0.050377 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 19.3125 | 41.7192 | 51.4702 | 15.93%
Sierra | SI_Sierra | CLARKSVILLE 2104 | 6754 | CLARKSVILLE 210419632 | 20.8227 | 121.914 | 4.4792 | 4.2494 | 0.22955 | 4.404 | 229 | 1223 | 463 | 351 | 459 | 347 | 0 | 234 | 0.016786 | 1230 |  | 464 | 352 | 7 | 5 | 5 | 7.48 | 0.1708 | 0.00178 | 275 | 2.5013 | 0.050025 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.12818 | 21.7822 | 103.5907 | 94.87%
Central Coast | LP_Los Padres | SANTA YNEZ 1101 | 3506 | SANTA YNEZ 1101Y14 | 2.1955 | 93.0049 | 6.09 | 0 | 6.09 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 1 | 227 |  | 43 | 29 | 227 | 43 | 29 | 79.34 | 0.023606 | 0.00211 | 276 | 0.54749 | 0.049772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.54749 | 7.0608 | 7.0608 | 0%
Sierra | SI_Sierra | NARROWS 2105 | 1926 | NARROWS 210534069 | 16.6258 | 378.1489 | 16.0044 | 0 | 16.0044 | 0 | 711 | 0 | 0 | 0 | 0 | 0 | 0 | 372 | 1 | 1303 |  | 237 | 157 | 1303 | 237 | 157 | 441.96 | 0.043966 | 0.02167 | 277 | 7.6062 | 0.049714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 7.6062 | 14.8085 | 14.8085 | 0%
Sierra | SI_Sierra | SHINGLE SPRINGS 1104 | 1218 | SHINGLE SPRINGS 110419502 | 106.9987 | 1123.2164 | 44.7358 | 39.1157 | 5.6201 | 41.9771 | 3539 | 6599 | 2313 | 1895 | 2270 | 1864 | 0 | 2200 | 0.061667 | 6996 |  | 2385 | 1942 | 397 | 115 | 78 | 193.28 | 0.095261 | 0.02278 | 278 | 5.3952 | 0.049497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 0.67779 | 20.4624 | 53.313 | 87.44%
Bay Area | MI_Mission | CAYETANO 2111 | 7920 | CAYETANO 2111circuit_breaker | 3.6718 | 105.1053 | 5.4591 | 0 | 5.4591 | 0 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 1 | 152 |  | 29 | 20 | 152 | 29 | 20 | 53.41 | 0.034935 | 0.00211 | 279 | 1.4124 | 0.048702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 1.4124 | 5.3122 | 5.3122 | 0%
Central Valley | ST_Stockton | NORTH BRANCH 1101 | 7153 | NORTH BRANCH 110111158 | 10.5534 | 277.5268 | 16.0989 | 0 | 16.0989 | 0 | 245 | 0 | 0 | 0 | 0 | 0 | 0 | 322 | 1 | 457 |  | 84 | 57 | 457 | 84 | 57 | 156.21 | 0.038027 | 0.00664 | 280 | 2.532 | 0.048693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 2.532 | 5.2178 | 5.2178 | 0%
North Valley | NV_North Valley | ANDERSON 1101 | 5104 | ANDERSON 11011752 | 6.6287 | 76.2896 | 3.0994 | 0 | 3.0994 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 1 | 67 |  | 14 | 10 | 67 | 14 | 10 | 25.21 | 0.086888 | 0.00253 | 281 | 1.0159 | 0.048375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 1.0159 | 4.517 | 4.517 | 0%
North Coast | SO_Sonoma | FITCH MOUNTAIN 1113 | 5869 | FITCH MOUNTAIN 1113583202 | 5.602 | 131.5157 | 5.633 | 0 | 5.633 | 0 | 1443 | 0 | 0 | 0 | 0 | 0 | 0 | 212 | 1 | 2633 |  | 477 | 315 | 2633 | 477 | 315 | 890.46 | 0.042596 | 0.04225 | 282 | 3.9458 | 0.048119 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 3.9458 | 84.6803 | 84.6803 | 0%
Sierra | SI_Sierra | PENRYN 1107 | 7162 | PENRYN 110790970 | 3.1512 | 42.5619 | 2.5636 | 0 | 2.5636 | 0 | 478 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 1 | 880 |  | 161 | 107 | 880 | 161 | 107 | 299.77 | 0.074037 | 0.02479 | 283 | 0.86532 | 0.048073 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 0.86532 | 62.8014 | 62.8014 | 0%
North Valley | NV_North Valley | DESCHUTES 1101 | 2237 | DESCHUTES 11011580 | 52.5666 | 1161.7773 | 45.4328 | 0 | 45.4328 | 0 | 7075 | 0 | 0 | 0 | 0 | 0 | 0 | 1021 | 1 | 12860 |  | 2321 | 1530 | 12860 | 2321 | 1530 | 4337.17 | 0.045247 | 0.21838 | 284 | 20.4631 | 0.047811 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 20.4631 | 51.0865 | 51.0865 | 0%
Sierra | SI_Sierra | WISE 1102 | 3287 | WISE 1102307494 | 30.7935 | 700.1962 | 30.067 | 0 | 30.067 | 0 | 2305 | 0 | 0 | 0 | 0 | 0 | 0 | 862 | 1 | 4198 |  | 759 | 501 | 4198 | 759 | 501 | 1417.65 | 0.043978 | 0.06941 | 285 | 12.965 | 0.047665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 12.965 | 25.2436 | 25.2436 | 0%
North Coast | SO_Sonoma | FITCH MOUNTAIN 1113 | 6839 | FITCH MOUNTAIN 1113356 | 11.5807 | 303.248 | 10.4828 | 0 | 10.4828 | 4.4146 | 2838 | 86 | 86 | 0 | 1 | 0 | 0 | 346 | 0.57887 | 3076 |  | 626 | 357 | 2990 | 625 | 357 | 1125.35 | 0.038189 | 0.04963 | 286 | 6.5616 | 0.047548 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 6.5616 | 59.6217 | 59.7171 | 0%
North Coast | HU_Humboldt | LAYTONVILLE 1102 | 2529 | LAYTONVILLE 1102500 | 16.77 | 376.1975 | 14.7133 | 0 | 14.7133 | 0 | 4755 | 0 | 0 | 0 | 0 | 0 | 0 | 246 | 1 | 8647 |  | 1562 | 1030 | 8647 | 1562 | 1030 | 2918.17 | 0.044578 | 0.14479 | 287 | 9.2215 | 0.047533 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1. <= 10% | 1. <= 10% | 9.2215 | 106.1628 | 106.1628 | 0%
Bay Area | DI_Diablo | CLAYTON 2212 | 442 | CLAYTON 221296224 | 21.7828 | 414.8543 | 16.617 | 11.0309 | 5.5862 | 16.617 | 2360 | 3911 | 1489 | 486 | 1225 | 341 | 2 | 860 | 0 | 3911 |  | 1489 | 486 | 0 | 264 | 145 | 361.68 | 0.052507 | 0.02882 | 288 | 9.2315 | 0.04686 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 3.1034 | 47.2595 | 89.6068 | 66.38%
North Valley | NV_North Valley | COTTONWOOD 1103 | 2512 | COTTONWOOD 110335470 | 14.1041 | 397.7824 | 20.0608 | 19.9006 | 0.16004 | 20.0608 | 324 | 980 | 77 | 16 | 77 | 16 | 0 | 684 | 0 | 980 |  | 77 | 16 | 0 | 0 | 0 | 0 | 0.035457 | 0 | 289 | 4.3162 | 0.046411 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.034433 | 0 | 3.8383 | 99.2%
Sierra | SI_Sierra | HORSESHOE 1101 | 3065 | HORSESHOE 110150140 | 2.7468 | 66.7893 | 3.2011 | 0 | 3.2011 | 0 | 442 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 1 | 815 |  | 149 | 99 | 815 | 149 | 99 | 277.48 | 0.041126 | 0.01274 | 290 | 2.5933 | 0.046308 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 2.5933 | 46.546 | 46.546 | 0%
Sierra | SA_Sacramento | PEABODY 2106 | 9682 | PEABODY 21065500 | 1.1437 | 17.4293 | 0.71155 | 0 | 0.71155 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 1 | 58 |  | 12 | 9 | 58 | 12 | 9 | 21.66 | 0.065618 | 0.00164 | 291 | 0.27703 | 0.046172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.27703 | 16.8645 | 16.8645 | 0%
North Valley | NV_North Valley | JESSUP 1101 | 5334 | JESSUP 11011496 | 17.7673 | 320.9118 | 13.7955 | 0 | 13.7955 | 0 | 1413 | 0 | 0 | 0 | 0 | 0 | 0 | 352 | 1 | 2578 |  | 467 | 309 | 2578 | 467 | 309 | 871.81 | 0.055365 | 0.05376 | 292 | 9.0763 | 0.046073 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 9.0763 | 33.8517 | 33.8517 | 0%
North Valley | NV_North Valley | WYANDOTTE 1109 | 2729 | WYANDOTTE 110913052 | 26.9424 | 558.6368 | 20.2973 | 0.92652 | 19.371 | 2.608 | 1693 | 613 | 145 | 128 | 33 | 25 | 0 | 711 | 0.87151 | 3303 |  | 632 | 450 | 2690 | 599 | 425 | 1062.73 | 0.048229 | 0.06007 | 293 | 11.0495 | 0.04604 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 10.5453 | 30.9225 | 31.1371 | 4.565%
North Valley | NV_North Valley | JESSUP 1102 | 3269 | JESSUP 110276068 | 19.6817 | 418.2412 | 16.4767 | 0 | 16.4767 | 0 | 1857 | 0 | 0 | 0 | 0 | 0 | 0 | 405 | 1 | 3385 |  | 612 | 404 | 3385 | 612 | 404 | 1143.09 | 0.047058 | 0.05989 | 294 | 11.2051 | 0.045923 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 11.2051 | 37.1433 | 37.1433 | 0%
Sierra | SI_Sierra | HIGGINS 1107 | 3701 | HIGGINS 11077559 | 5.2319 | 159.4442 | 5.8438 | 0 | 5.8438 | 0 | 1615 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 1 | 2945 |  | 533 | 352 | 2945 | 533 | 352 | 995.26 | 0.032814 | 0.03637 | 295 | 3.2929 | 0.045735 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 3.2929 | 91.2086 | 91.2086 | 0%
North Valley | NV_North Valley | COTTONWOOD 1101 | 3393 | COTTONWOOD 11011610 | 38.4063 | 826.1904 | 37.0616 | 0.18201 | 36.8795 | 0.18201 | 2323 | 24 | 5 | 3 | 5 | 3 | 0 | 806 | 0.99509 | 4234 |  | 766 | 505 | 4210 | 761 | 502 | 1421.47 | 0.046486 | 0.07356 | 296 | 17.1663 | 0.045655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1. <= 10% | 2. >10 - 20% | 17.082 | 20.6347 | 20.6683 | 0.4911%
Central Valley | ST_Stockton | CORRAL 1102 | 7114 | CORRAL 110214026 | 12.7625 | 255.8483 | 11.9525 | 1.3193 | 10.6331 | 1.414 | 137 | 74 | 5 | 4 | 5 | 4 | 0 | 271 | 0.8817 | 304 |  | 48 | 33 | 230 | 43 | 29 | 79.61 | 0.049883 | 0.00446 | 297 | 4.3331 | 0.045612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 3.8549 | 4.044 | 4.0159 | 11.04%
North Valley | NV_North Valley | WYANDOTTE 1109 | 9283 | WYANDOTTE 110932586 | 1.2655 | 18.8454 | 1.0333 | 0 | 1.0333 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1 | 56 |  | 12 | 9 | 56 | 12 | 9 | 21.48 | 0.067154 | 0.00168 | 298 | 0.86529 | 0.045542 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.86529 | 11.6129 | 11.6129 | 0%
North Valley | NV_North Valley | CORNING 1101 | 8769 | CORNING 110185162 | 5.9899 | 107.0474 | 6.0244 | 6.0244 | 0 | 6.0244 | 74 | 341 | 39 | 37 | 39 | 37 | 0 | 173 | 0 | 341 |  | 39 | 37 | 0 | 0 | 0 | 0 | 0.055956 | 0 | 299 | 1.0007 | 0.045486 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0 | 0 | 6.4736 | 100%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 989 | TEMPLETON 2113A70 | 0 | 0 | 1.6951 | 0 | 1.6951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 300 | 7.4104 | 0.045463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 7.4104 | 2.3598 | 2.3598 | 0%
Central Valley | YO_Yosemite | COARSEGOLD 2103 | 8231 | COARSEGOLD 2104circuit_breaker | 10.18 | 73.9064 | 3.2672 | 1.6646 | 1.6027 | 1.9466 | 73 | 173 | 26 | 21 | 19 | 14 | 0 | 119 | 0.40421 | 232 |  | 37 | 29 | 59 | 18 | 15 | 29.97 | 0.13774 | 0.00516 | 301 | 0.99973 | 0.045442 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 0.49039 | 11.2314 | 11.3246 | 50.95%
Central Coast | SJ_San Jose | MORGAN HILL 2105 | 3071 | MORGAN HILL 210542348 | 2.0488 | 66.5786 | 2.936 | 0 | 2.936 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 1 | 181 |  | 35 | 24 | 181 | 35 | 24 | 64.24 | 0.030773 | 0.00224 | 302 | 0.72378 | 0.045236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.72378 | 11.921 | 11.921 | 0%
North Coast | HU_Humboldt | MIDDLETOWN 1101 | 9493 | MIDDLETOWN 1101612 | 5.8114 | 168.9643 | 3.6063 | 1.3333 | 2.2731 | 2.9061 | 1764 | 2432 | 174 | 112 | 115 | 61 | 0 | 95 | 0.19416 | 3056 |  | 287 | 187 | 624 | 172 | 126 | 291.8 | 0.034394 | 0.0123 | 303 | 1.6703 | 0.045144 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 1.0528 | 75.6674 | 79.5841 | 36.97%
North Coast | SO_Sonoma | GEYSERVILLE 1102 | 2142 | GEYSERVILLE 110289714 | 2.9586 | 67.1567 | 2.7081 | 0.12822 | 2.5799 | 0.18864 | 1088 | 8 | 1 | 0 | 0 | 0 | 0 | 79 | 0.93034 | 1858 |  | 336 | 222 | 1850 | 336 | 222 | 626.82 | 0.044055 | 0.03078 | 304 | 2.1211 | 0.04513 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 3. >20 - 30% | 2.0207 | 130.2364 | 124.0702 | 4.735%
North Valley | NV_North Valley | KESWICK 1101 | 8360 | KESWICK 11011586 | 4.0601 | 143.1137 | 6.992 | 5.6487 | 1.3434 | 6.992 | 251 | 775 | 95 | 92 | 38 | 38 | 0 | 257 | 0 | 775 |  | 95 | 92 | 0 | 57 | 54 | 78.09 | 0.028369 | 0.00336 | 305 | 1.0737 | 0.044737 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 6. >50% | 0.20629 | 42.4306 | 13.5869 | 80.79%
Bay Area | NB_North Bay | MONTICELLO 1101 | 4774 | MONTICELLO 1101720 | 2.9309 | 186.4239 | 6.835 | 0 | 6.835 | 0 | 711 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 1 | 1303 |  | 237 | 157 | 1303 | 237 | 157 | 441.96 | 0.015721 | 0.00775 | 306 | 0.088816 | 0.044408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 5. >40 - 50% | 0.088816 | 34.6743 | 34.6743 | 0%
North Valley | NV_North Valley | WYANDOTTE 1107 | 5927 | WYANDOTTE 110737472 | 6.9894 | 165.1436 | 7.7777 | 5.6403 | 2.1373 | 7.5693 | 779 | 1584 | 653 | 543 | 547 | 454 | 0 | 290 | 0.026786 | 1622 |  | 660 | 548 | 38 | 113 | 94 | 158.23 | 0.042323 | 0.00994 | 307 | 4.8973 | 0.04412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1. <= 10% | 4. >30 - 40% | 1.3458 | 52.8702 | 84.8585 | 72.52%
Sierra | SI_Sierra | PENRYN 1105 | 1166 | PENRYN 11051342 | 19.0589 | 416.1968 | 20.99 | 1.0672 | 19.9227 | 1.0672 | 2210 | 421 | 193 | 167 | 193 | 167 | 0 | 494 | 0.94915 | 4242 |  | 884 | 623 | 3821 | 691 | 456 | 1290.56 | 0.045793 | 0.0658 | 308 | 12.1504 | 0.043864 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 11.5326 | 34.684 | 42.1154 | 5.085%
Central Valley | YO_Yosemite | PEORIA 1705 | 7909 | PEORIA 1705circuit_breaker | 5.622 | 149.3769 | 7.2142 | 0.74773 | 6.4665 | 0.79602 | 137 | 15 | 4 | 1 | 4 | 1 | 0 | 122 | 0.88966 | 247 |  | 48 | 31 | 232 | 44 | 30 | 81.16 | 0.037637 | 0.00344 | 309 | 2.2801 | 0.043849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 2.0438 | 6.8043 | 6.6535 | 10.36%
Sierra | SI_Sierra | DIAMOND SPRINGS 1107 | 821 | DIAMOND SPRINGS 1107circuit_breaker | 73.5027 | 1255.5532 | 54.1604 | 45.3748 | 8.7858 | 49.8331 | 5788 | 11067 | 4305 | 3467 | 4273 | 3439 | 0 | 2463 | 0.079897 | 11908 |  | 4457 | 3567 | 841 | 184 | 128 | 327.77 | 0.058542 | 0.0224 | 310 | 27.067 | 0.043798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 4.3908 | 20.9429 | 82.2926 | 83.78%
Central Coast | LP_Los Padres | SAN MIGUEL 1106 | 8727 | SAN MIGUEL 1106N34 | 1.6216 | 48.6144 | 3.7771 | 0 | 3.7771 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 1 | 18 |  | 5 | 4 | 18 | 5 | 4 | 8.47 | 0.033356 | 0.00035 | 311 | 0.26198 | 0.043664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.26198 | 1.3238 | 1.3238 | 0%
Sierra | SI_Sierra | DIAMOND SPRINGS 1105 | 1489 | DIAMOND SPRINGS 110518935 | 10.1407 | 136.6714 | 5.0652 | 0.040909 | 5.0242 | 0 | 578 | 1 | 1 | 0 | 0 | 0 | 0 | 229 | 1 | 1063 |  | 194 | 128 | 1062 | 194 | 128 | 361.36 | 0.074198 | 0.02993 | 312 | 3.4873 | 0.043592 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 3.4592 | 38.6128 | 38.3009 | 0.8077%
North Coast | HU_Humboldt | WILLITS 1104 | 3665 | WILLITS 1104934 | 31.1776 | 823.0671 | 28.5794 | 19.0002 | 9.579 | 28.5794 | 9650 | 21576 | 3864 | 1920 | 3241 | 1602 | 0 | 1144 | 0 | 21576 |  | 3864 | 1920 | 0 | 623 | 318 | 853.51 | 0.03788 | 0.04907 | 313 | 17.7005 | 0.043277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 5.9327 | 65.0383 | 135.2025 | 66.48%
Central Valley | ST_Stockton | OLETA 1101 | 3912 | OLETA 11011208 | 36.5499 | 803.2772 | 33.2068 | 26.9638 | 6.243 | 32.1608 | 749 | 1482 | 227 | 109 | 131 | 74 | 0 | 652 | 0.0315 | 1525 |  | 235 | 114 | 43 | 104 | 40 | 146.35 | 0.045501 | 0.00984 | 314 | 11.8256 | 0.043159 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 2.2233 | 16.6587 | 7.0769 | 81.2%
North Valley | NV_North Valley | COTTONWOOD 1102 | 422 | COTTONWOOD 11021578 | 31.2698 | 701.8235 | 29.7583 | 0 | 29.7583 | 0 | 2966 | 0 | 0 | 0 | 0 | 0 | 0 | 612 | 1 | 5398 |  | 976 | 644 | 5398 | 976 | 644 | 1822.94 | 0.044555 | 0.09042 | 315 | 12.1173 | 0.043122 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 1. <= 10% | 12.1173 | 32.7975 | 32.7975 | 0%
North Valley | NV_North Valley | RISING RIVER 1101 | 7588 | RISING RIVER 11011532 | 2.0722 | 55.7598 | 4.3826 | 0 | 4.3826 | 0 | 379 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 1 | 701 |  | 128 | 85 | 701 | 128 | 85 | 238.45 | 0.037163 | 0.00989 | 316 | 0.77491 | 0.04305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 0.77491 | 29.2066 | 29.2066 | 0%
North Valley | NV_North Valley | GIRVAN 1102 | 4578 | GIRVAN 110280726 | 8.4274 | 175.4376 | 8.067 | 0 | 8.067 | 0 | 620 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 1 | 1138 |  | 207 | 137 | 1138 | 207 | 137 | 386.01 | 0.048037 | 0.02068 | 317 | 4.2002 | 0.042859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 4.2002 | 25.66 | 25.66 | 0%
North Coast | HU_Humboldt | HIGHLANDS 1102 | 5406 | HIGHLANDS 110280660 | 9.3276 | 142.9527 | 6.2919 | 4.7979 | 1.4939 | 6.0712 | 180 | 323 | 57 | 37 | 19 | 5 | 0 | 194 | 0.035068 | 335 |  | 59 | 38 | 12 | 40 | 33 | 55.88 | 0.06525 | 0.00543 | 318 | 1.9661 | 0.042741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.46683 | 26.7748 | 9.3772 | 76.26%
Sierra | SA_Sacramento | PUTAH CREEK 1105 | 7124 | PUTAH CREEK 11058812 | 0.86672 | 25.2527 | 1.0625 | 0 | 1.0625 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1 | 25 |  | 6 | 5 | 25 | 6 | 5 | 10.47 | 0.034322 | 0.00043 | 319 | 0.21253 | 0.042507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.21253 | 5.6471 | 5.6471 | 0%
Central Valley | YO_Yosemite | SAN JOAQUIN NO2 1103 | 129 | SAN JOAQUIN #2 1103circuit_breaker | 72.0253 | 1633.3833 | 67.9301 | 0 | 67.9301 | 0 | 3779 | 0 | 0 | 0 | 0 | 0 | 0 | 1233 | 1 | 6875 |  | 1242 | 819 | 6875 | 1242 | 819 | 2320.29 | 0.044096 | 0.11388 | 320 | 16.4981 | 0.042412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2. >10 - 20% | 1. <= 10% | 16.4981 | 18.2835 | 18.2835 | 0%
Central Valley | ST_Stockton | CORRAL 1102 | 4241 | CORRAL 110236666 | 25.5785 | 443.4028 | 17.6712 | 0.48788 | 17.1831 | 0.48788 | 309 | 35 | 3 | 0 | 3 | 0 | 0 | 387 | 0.97239 | 593 |  | 105 | 68 | 558 | 102 | 68 | 189.96 | 0.057687 | 0.01224 | 321 | 6.3948 | 0.042349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 6.2181 | 5.936 | 5.9419 | 2.761%
North Coast | HU_Humboldt | GARBERVILLE 1101 | 6566 | GARBERVILLE 1101circuit_breaker | 5.0095 | 85.7743 | 5.0739 | 0 | 5.0739 | 0 | 937 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1 | 1714 |  | 311 | 206 | 1714 | 311 | 206 | 580.33 | 0.058404 | 0.03777 | 322 | 3.2592 | 0.042327 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 3.2592 | 61.2945 | 61.2945 | 0%
North Valley | NV_North Valley | JESSUP 1103 | 2867 | JESSUP 110338864 | 0.27266 | 11.3679 | 0.79034 | 0 | 0.79034 | 0 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 1 | 156 |  | 30 | 21 | 156 | 30 | 21 | 55.14 | 0.023985 | 0.0015 | 323 | 1.0991 | 0.042274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 1.0991 | 37.9583 | 37.9583 | 0%
North Valley | NV_North Valley | RED BLUFF 1104 | 4913 | RED BLUFF 11041566 | 9.9957 | 230.5371 | 12.4466 | 10.7723 | 1.6742 | 10.9761 | 223 | 315 | 27 | 8 | 25 | 8 | 0 | 311 | 0.11814 | 364 |  | 36 | 14 | 49 | 11 | 6 | 19.48 | 0.043358 | 0.00099 | 324 | 0.92933 | 0.042242 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.12501 | 6.5701 | 2.8924 | 86.55%
North Coast | HU_Humboldt | FORT SEWARD 1121 | 5512 | FORT SEWARD 1121circuit_breaker | 4.6107 | 149.7628 | 8.0996 | 0 | 8.0996 | 0 | 792 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 1 | 1451 |  | 264 | 175 | 1451 | 264 | 175 | 492.27 | 0.030787 | 0.0169 | 325 | 3.1199 | 0.042161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 3.1199 | 32.5941 | 32.5941 | 0%
Sierra | SI_Sierra | LINCOLN 1101 | 2581 | LINCOLN 11012310 | 9.8761 | 226.7041 | 10.0581 | 0 | 10.0581 | 0 | 431 | 0 | 0 | 0 | 0 | 0 | 0 | 204 | 1 | 795 |  | 145 | 97 | 795 | 145 | 97 | 270.2 | 0.043564 | 0.01314 | 326 | 5.8855 | 0.042039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 5.8855 | 14.4162 | 14.4162 | 0%
North Valley | NV_North Valley | PANORAMA 1102 | 3722 | PANORAMA 11021526 | 8.26 | 220.9042 | 13.4108 | 0 | 13.4108 | 0 | 593 | 0 | 0 | 0 | 0 | 0 | 0 | 283 | 1 | 1089 |  | 198 | 132 | 1089 | 198 | 132 | 369.27 | 0.037392 | 0.0154 | 327 | 3.5987 | 0.041845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 3.5987 | 14.7642 | 14.7642 | 0%
Bay Area | DI_Diablo | CLAYTON 2212 | 7240 | CLAYTON 22127758 | 5.2127 | 78.2546 | 2.8718 | 2.0962 | 0.77557 | 2.8718 | 321 | 367 | 99 | 54 | 45 | 14 | 1 | 109 | 0 | 367 |  | 99 | 54 | 0 | 54 | 40 | 73.98 | 0.066612 | 0.00748 | 328 | 1.7501 | 0.041669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.47264 | 69.6264 | 34.4734 | 72.99%
Central Valley | ST_Stockton | CORRAL 1101 | 380 | CORRAL 110112606 | 23.4498 | 513.8396 | 22.0011 | 21.1542 | 0.84697 | 22.0011 | 516 | 2494 | 323 | 198 | 309 | 184 | 0 | 689 | 0 | 2494 |  | 323 | 198 | 0 | 14 | 14 | 19.18 | 0.045636 | 0.00133 | 329 | 8.9495 | 0.041626 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.34453 | 16.5295 | 14.6811 | 96.15%
Central Valley | KE_Kern | POSO MOUNTAIN 2104 | 8902 | POSO MOUNTAIN 2104circuit_breaker | 1.2089 | 67.6105 | 5.2841 | 0.18106 | 5.103 | 0.18106 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 74 | 0.96573 | 29 |  | 6 | 5 | 22 | 6 | 5 | 10.2 | 0.01788 | 0.00022 | 330 | 0.16595 | 0.041486 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.16026 | 1.1758 | 1.1355 | 3.427%
North Valley | NV_North Valley | JESSUP 1101 | 4012 | JESSUP 110141356 | 30.4117 | 739.3651 | 32.1269 | 0 | 32.1269 | 0 | 1447 | 0 | 0 | 0 | 0 | 0 | 0 | 733 | 1 | 2640 |  | 478 | 316 | 2640 | 478 | 316 | 892.46 | 0.041132 | 0.04088 | 331 | 11.5613 | 0.041144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 11.5613 | 14.8785 | 14.8785 | 0%
Central Valley | FR_Fresno | AUBERRY 1101 | 3133 | AUBERRY 1101R314 | 35.186 | 1059.4193 | 42.0417 | 18.6504 | 23.3913 | 27.8104 | 999 | 1754 | 328 | 213 | 2 | 1 | 0 | 1207 | 0.3385 | 2372 |  | 440 | 287 | 618 | 438 | 286 | 655.68 | 0.033213 | 0.03025 | 332 | 9.8936 | 0.041052 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 5.5046 | 18.7249 | 10.4658 | 44.36%
North Coast | HU_Humboldt | KONOCTI 1102 | 5257 | KONOCTI 110264664 | 29.4272 | 711.0392 | 25.0845 | 19.2366 | 5.8479 | 24.9926 | 2659 | 6356 | 1569 | 918 | 1260 | 741 | 0 | 918 | 0.0036619 | 6374 |  | 1572 | 920 | 18 | 312 | 179 | 429.06 | 0.041386 | 0.02685 | 333 | 11.0602 | 0.040964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 2.5785 | 53.3523 | 62.6683 | 76.69%
North Coast | HU_Humboldt | FRUITLAND 1142 | 8284 | FRUITLAND 114293234 | 6.881 | 220.7115 | 10.6913 | 0 | 10.6913 | 0 | 5688 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 1 | 10342 |  | 1867 | 1231 | 10342 | 1867 | 1231 | 3488.57 | 0.031176 | 0.12103 | 334 | 0.94073 | 0.040901 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 2. >10 - 20% | 1. <= 10% | 0.94073 | 174.6282 | 174.6282 | 0%
Sierra | SI_Sierra | PENRYN 1107 | 6980 | PENRYN 11072708 | 5.5125 | 223.7294 | 10.4826 | 0 | 10.4826 | 0 | 1521 | 0 | 0 | 0 | 0 | 0 | 0 | 248 | 1 | 2774 |  | 502 | 332 | 2774 | 502 | 332 | 937.4 | 0.024639 | 0.02572 | 336 | 5.1482 | 0.040859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 5.1482 | 47.889 | 47.889 | 0%
North Coast | SO_Sonoma | MOLINO 1101 | 2495 | MOLINO 1101338 | 6.2073 | 152.383 | 7.4402 | 0.30473 | 7.1354 | 7.0917 | 1920 | 159 | 157 | 1 | 0 | 0 | 0 | 310 | 0.046838 | 323 |  | 187 | 21 | 164 | 187 | 21 | 270.95 | 0.040735 | 0.01584 | 337 | 4.0819 | 0.040819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 3.9147 | 26.2073 | 25.1339 | 4.096%
Central Valley | YO_Yosemite | RACETRACK 1704 | 2159 | RACETRACK 1704circuit_breaker | 18.666 | 490.0317 | 19.983 | 16.2134 | 3.7695 | 18.6402 | 642 | 1947 | 535 | 288 | 482 | 257 | 0 | 588 | 0.067197 | 2026 |  | 549 | 298 | 79 | 67 | 41 | 98.9 | 0.038091 | 0.00531 | 338 | 8.431 | 0.04073 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 1.5904 | 17.7742 | 27.4734 | 81.14%
North Valley | NV_North Valley | CORNING 1101 | 84 | CORNING 110185152 | 23.4532 | 504.296 | 23.7027 | 22.2871 | 1.4155 | 23.7027 | 1759 | 6062 | 869 | 785 | 863 | 783 | 0 | 858 | 0 | 6062 |  | 869 | 785 | 0 | 6 | 2 | 8.22 | 0.046507 | 0.00058 | 339 | 12.8973 | 0.040685 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.77023 | 4.2387 | 36.6626 | 94.03%
Sierra | SI_Sierra | PENRYN 1103 | 1849 | PENRYN 1103circuit_breaker | 28.7997 | 637.2958 | 29.8104 | 14.8432 | 14.9674 | 18.372 | 3092 | 3525 | 1036 | 738 | 934 | 658 | 0 | 1097 | 0.38371 | 5684 |  | 1426 | 995 | 2159 | 492 | 337 | 868.35 | 0.045191 | 0.04623 | 340 | 16.1209 | 0.040607 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 8.0941 | 32.8714 | 47.8356 | 49.79%
Bay Area | NB_North Bay | CALISTOGA 1101 | 992 | CALISTOGA 1101890 | 21.6289 | 502.9331 | 24.3652 | 19.0517 | 5.3134 | 24.1561 | 3153 | 3176 | 343 | 157 | 163 | 72 | 0 | 687 | 0.0085816 | 3225 |  | 352 | 163 | 49 | 189 | 91 | 263.34 | 0.043006 | 0.0169 | 341 | 10.1513 | 0.040443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 2.2138 | 35.5701 | 14.4469 | 78.19%
Sierra | SI_Sierra | CLARKSVILLE 2103 | 133 | CLARKSVILLE 210319572 | 31.7513 | 721.8547 | 29.975 | 20.7239 | 9.2511 | 21.6862 | 1740 | 3136 | 840 | 586 | 820 | 571 | 0 | 1163 | 0.27652 | 4013 |  | 999 | 691 | 877 | 179 | 120 | 324.16 | 0.043986 | 0.01637 | 342 | 13.4518 | 0.040275 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 4.1516 | 19.349 | 33.3278 | 69.14%
North Valley | NV_North Valley | ELK CREEK 1101 | 5999 | ELK CREEK 11012004 | 16.1257 | 425.1371 | 24.6527 | 0 | 24.6527 | 0 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 353 | 1 | 1047 |  | 191 | 127 | 1047 | 191 | 127 | 355.9 | 0.037931 | 0.01506 | 343 | 3.2121 | 0.040151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 3.2121 | 7.7476 | 7.7476 | 0%
North Coast | HU_Humboldt | LAYTONVILLE 1102 | 3249 | LAYTONVILLE 110237586 | 14.0024 | 330.4892 | 13.8801 | 0 | 13.8801 | 0 | 3529 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 1 | 6421 |  | 1160 | 765 | 6421 | 1160 | 765 | 2167.09 | 0.042369 | 0.1022 | 344 | 5.2932 | 0.0401 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 1. <= 10% | 5.2932 | 83.5728 | 83.5728 | 0%
Bay Area | MI_Mission | CAYETANO 2109 | 7987 | CAYETANO 21099504 | 12.0827 | 278.7892 | 13.4744 | 0 | 13.4744 | 0 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 230 | 1 | 256 |  | 48 | 33 | 256 | 48 | 33 | 88.8 | 0.04334 | 0.00433 | 345 | 2.4769 | 0.039949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 2.4769 | 3.5623 | 3.5623 | 0%
Sierra | SI_Sierra | NARROWS 2105 | 1807 | NARROWS 21057203 | 15.9624 | 425.7307 | 18.6657 | 0 | 18.6657 | 0 | 2230 | 0 | 0 | 0 | 0 | 0 | 0 | 427 | 1 | 4062 |  | 735 | 485 | 4062 | 735 | 485 | 1372.53 | 0.037494 | 0.0573 | 346 | 8.9301 | 0.039866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 8.9301 | 39.377 | 39.377 | 0%
North Coast | HU_Humboldt | BRIDGEVILLE 1102 | 4918 | BRIDGEVILLE 1102circuit_breaker | 17.0788 | 512.7373 | 25.1752 | 0.017045 | 25.1581 | 0.017045 | 6934 | 16 | 0 | 0 | 0 | 0 | 0 | 419 | 0.99932 | 12612 |  | 2274 | 1499 | 12596 | 2274 | 1499 | 4249.02 | 0.033309 | 0.15751 | 347 | 4.4377 | 0.039623 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 2. >10 - 20% | 1. <= 10% | 4.4347 | 90.3882 | 90.327 | 0.06771%
Sierra | SI_Sierra | PENRYN 1105 | 631 | PENRYN 110550548 | 2.3734 | 60.353 | 4.0703 | 0 | 4.0703 | 0 | 376 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 1 | 695 |  | 127 | 85 | 695 | 127 | 85 | 236.54 | 0.039325 | 0.01039 | 348 | 0.98781 | 0.039513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 0.98781 | 31.2019 | 31.2019 | 0%
Sierra | SI_Sierra | PENRYN 1103 | 2520 | PENRYN 1103660 | 9.6293 | 259.5158 | 11.4523 | 0.16856 | 11.2837 | 0.15833 | 1616 | 19 | 0 | 0 | 0 | 0 | 0 | 458 | 0.98617 | 2925 |  | 526 | 347 | 2906 | 526 | 347 | 982.16 | 0.037105 | 0.04058 | 349 | 6.1116 | 0.03943 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 6.0216 | 46.6159 | 45.9297 | 1.472%
North Valley | NV_North Valley | ELK CREEK 1101 | 4552 | ELK CREEK 11012212 | 7.0065 | 202.9357 | 15.5809 | 0 | 15.5809 | 0 | 537 | 0 | 0 | 0 | 0 | 0 | 0 | 222 | 1 | 987 |  | 180 | 120 | 987 | 180 | 120 | 335.43 | 0.034526 | 0.01292 | 350 | 2.8289 | 0.039291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 2.8289 | 11.5526 | 11.5526 | 0%
Sierra | SI_Sierra | APPLE HILL 2102 | 3901 | APPLE HILL 2102circuit_breaker | 34.6046 | 852.1487 | 37.2691 | 0 | 37.2691 | 0 | 13369 | 0 | 0 | 0 | 0 | 0 | 0 | 1916 | 1 | 24290 |  | 4383 | 2888 | 24290 | 4383 | 2888 | 8190.81 | 0.040609 | 0.37011 | 351 | 25.2589 | 0.039283 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 2. >10 - 20% | 1. <= 10% | 25.2589 | 117.604 | 117.604 | 0%
Sierra | SI_Sierra | SHINGLE SPRINGS 2108 | 2860 | SHINGLE SPRINGS 210819762 | 0.66107 | 25.5706 | 0.98542 | 0 | 0.98542 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1 | 145 |  | 28 | 19 | 145 | 28 | 19 | 51.41 | 0.025853 | 0.00151 | 352 | 1.6494 | 0.039271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 1.6494 | 28.4144 | 28.4144 | 0%
Central Valley | FR_Fresno | SAND CREEK 1103 | 8475 | SAND CREEK 1103circuit_breaker | 5.389 | 252.6345 | 12.2604 | 0 | 12.2604 | 0 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 177 | 1 | 256 |  | 48 | 33 | 256 | 48 | 33 | 88.8 | 0.021331 | 0.00213 | 353 | 2.6938 | 0.039041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 2.6938 | 3.915 | 3.915 | 0%
Bay Area | MI_Mission | VASCO 1102 | 3594 | VASCO 1102MR178 | 1.2113 | 25.9275 | 1.5155 | 0 | 1.5155 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1 | 25 |  | 6 | 5 | 25 | 6 | 5 | 10.47 | 0.04672 | 0.00058 | 354 | 0.11712 | 0.03904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.11712 | 3.959 | 3.959 | 0%
Sierra | SI_Sierra | NARROWS 2105 | 3008 | NARROWS 21052228 | 19.8464 | 563.4309 | 21.9716 | 0 | 21.9716 | 0 | 3365 | 0 | 0 | 0 | 0 | 0 | 0 | 477 | 1 | 6123 |  | 1106 | 730 | 6123 | 1106 | 730 | 2066.29 | 0.035224 | 0.08101 | 355 | 10.1756 | 0.038838 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 1. <= 10% | 10.1756 | 50.3377 | 50.3377 | 0%
North Valley | NV_North Valley | GIRVAN 1101 | 4039 | GIRVAN 1101323094 | 33.8602 | 811.6811 | 35.307 | 0 | 35.307 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 691 | 1 | 6368 |  | 1150 | 759 | 6368 | 1150 | 759 | 2148.62 | 0.041716 | 0.09976 | 356 | 11.098 | 0.038804 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 2. >10 - 20% | 1. <= 10% | 11.098 | 32.5714 | 32.5714 | 0%
North Valley | NV_North Valley | WYANDOTTE 1107 | 2841 | WYANDOTTE 11071026 | 23.0575 | 539.2715 | 23.1381 | 16.7699 | 6.368 | 21.8763 | 1884 | 3558 | 1022 | 884 | 824 | 702 | 0 | 757 | 0.054531 | 3745 |  | 1056 | 906 | 187 | 232 | 204 | 334.67 | 0.042757 | 0.02063 | 357 | 10.319 | 0.038648 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 2.84 | 36.4322 | 45.6391 | 72.48%
North Coast | HU_Humboldt | MIDDLETOWN 1102 | 2229 | MIDDLETOWN 1102414 | 9.942 | 153.098 | 6.0299 | 4.1871 | 1.8428 | 5.5536 | 327 | 626 | 118 | 70 | 68 | 35 | 0 | 178 | 0.078994 | 674 |  | 127 | 76 | 48 | 59 | 41 | 85.15 | 0.064939 | 0.00797 | 358 | 0.54106 | 0.038647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.16535 | 32.0164 | 21.0616 | 69.44%
Sierra | SI_Sierra | PENRYN 1105 | 7670 | PENRYN 110550550 | 1.5887 | 53.3745 | 2.3994 | 0 | 2.3994 | 0 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 1 | 308 |  | 58 | 39 | 308 | 58 | 39 | 107.18 | 0.029765 | 0.00359 | 359 | 1.0768 | 0.038455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 1.0768 | 24.1724 | 24.1724 | 0%
North Valley | NV_North Valley | CORNING 1102 | 4992 | CORNING 11021622 | 34.238 | 716.5566 | 32.8119 | 0 | 32.8119 | 0 | 926 | 0 | 0 | 0 | 0 | 0 | 0 | 513 | 1 | 1694 |  | 307 | 203 | 1694 | 307 | 203 | 573.05 | 0.047781 | 0.0305 | 360 | 4.2244 | 0.038404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 4.2244 | 9.3564 | 9.3564 | 0%
Sierra | SI_Sierra | DIAMOND SPRINGS 1105 | 3079 | DIAMOND SPRINGS 11057722 | 57.4365 | 1453.3456 | 50.3862 | 1.9496 | 48.4366 | 3.5659 | 8251 | 332 | 55 | 52 | 0 | 0 | 0 | 1975 | 0.92923 | 14267 |  | 2570 | 1709 | 13935 | 2570 | 1709 | 4775.05 | 0.03952 | 0.2112 | 361 | 28.5476 | 0.03837 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 2. >10 - 20% | 1. <= 10% | 27.443 | 53.0591 | 51.0061 | 3.869%
Central Coast | LP_Los Padres | TEMPLETON 2112 | 1699 | TEMPLETON 2112R28 | 2.6134 | 48.9645 | 2.7725 | 0 | 2.7725 | 0 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 1 | 228 |  | 43 | 29 | 228 | 43 | 29 | 79.43 | 0.053373 | 0.00477 | 362 | 0.68918 | 0.038288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.68918 | 15.5093 | 15.5093 | 0%
North Valley | NV_North Valley | RED BLUFF 1104 | 3240 | RED BLUFF 1104circuit_breaker | 0.95772 | 27.7274 | 1.2146 | 1.1288 | 0.085606 | 1.2146 | 48 | 189 | 12 | 4 | 9 | 4 | 0 | 48 | 0 | 189 |  | 12 | 4 | 0 | 3 | 0 | 4.11 | 0.03454 | 0.00022 | 363 | 0.76134 | 0.038067 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.05366 | 35.0442 | 9.8799 | 92.94%
Bay Area | NB_North Bay | MONTICELLO 1101 | 5549 | MONTICELLO 110165454 | 0.52384 | 25.0443 | 1.4903 | 0 | 1.4903 | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1 | 292 |  | 55 | 37 | 292 | 55 | 37 | 101.63 | 0.020917 | 0.00239 | 364 | 0.30184 | 0.037729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.30184 | 36.9043 | 36.9043 | 0%
Sierra | SI_Sierra | PENRYN 1105 | 5262 | PENRYN 11052406 | 3.4224 | 89.2224 | 5.3676 | 0 | 5.3676 | 0 | 738 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 1 | 1352 |  | 246 | 163 | 1352 | 246 | 163 | 458.7 | 0.038358 | 0.01962 | 365 | 1.8821 | 0.037642 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 1.8821 | 45.8304 | 45.8304 | 0%
Sierra | SI_Sierra | SHINGLE SPRINGS 2110 | 4504 | SHINGLE SPRINGS 211051790 | 2.8115 | 124.7525 | 5.2205 | 0.64508 | 4.5754 | 0.64508 | 756 | 44 | 20 | 7 | 20 | 7 | 0 | 130 | 0.87643 | 1258 |  | 241 | 153 | 1214 | 221 | 146 | 412.03 | 0.022536 | 0.01036 | 366 | 4.6123 | 0.037498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 4.0423 | 48.302 | 46.1646 | 12.36%
Central Valley | YO_Yosemite | MARIPOSA 2102 | 5336 | MARIPOSA 2102241564 | 0.075979 | 5.4896 | 0.048864 | 0 | 0.048864 | 0.048864 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.013841 | 0 | 367 | 0.2611 | 0.037301 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.2611 | 0 | 0 | 0%
Bay Area | NB_North Bay | PUEBLO 2102 | 4183 | PUEBLO 2102618 | 1.8815 | 58.8066 | 2.4491 | 2.1364 | 0.31269 | 2.3585 | 353 | 540 | 125 | 68 | 95 | 49 | 0 | 91 | 0.036965 | 564 |  | 129 | 71 | 24 | 34 | 22 | 48.74 | 0.031994 | 0.00226 | 368 | 1.2276 | 0.037201 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.15674 | 108.7341 | 52.6734 | 87.23%
Sierra | SI_Sierra | DIAMOND SPRINGS 1105 | 759 | DIAMOND SPRINGS 11052102 | 43.445 | 924.8114 | 37.1093 | 0.83106 | 36.2782 | 2.9419 | 5492 | 948 | 253 | 231 | 54 | 47 | 0 | 1822 | 0.92072 | 10142 |  | 1913 | 1325 | 9194 | 1859 | 1278 | 3374.29 | 0.046977 | 0.1816 | 369 | 18.2244 | 0.037041 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 1. <= 10% | 17.8162 | 51.2429 | 51.5504 | 2.239%
Sierra | SI_Sierra | SHINGLE SPRINGS 2109 | 3480 | SHINGLE SPRINGS 21092053 | 9.1356 | 163.1596 | 5.2038 | 0.32008 | 4.8837 | 0.32008 | 814 | 22 | 6 | 6 | 6 | 6 | 0 | 125 | 0.93849 | 1421 |  | 260 | 174 | 1399 | 254 | 168 | 473.89 | 0.055992 | 0.02957 | 370 | 3.2207 | 0.036598 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 3.0226 | 52.0096 | 49.9636 | 6.151%
Sierra | SA_Sacramento | VACAVILLE 1108 | 5292 | VACAVILLE 110847860 | 0.81209 | 12.8055 | 0.44148 | 0 | 0.44148 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 107 |  | 21 | 15 | 107 | 21 | 15 | 38.4 | 0.063417 | 0.00277 | 371 | 0.21922 | 0.036536 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.21922 | 47.5676 | 47.5676 | 0%
North Coast | HU_Humboldt | LAYTONVILLE 1101 | 2013 | LAYTONVILLE 1101518 | 1.5941 | 58.318 | 3.3261 | 1.3436 | 1.9826 | 2.6214 | 850 | 1471 | 448 | 379 | 375 | 335 | 0 | 81 | 0.21188 | 1801 |  | 508 | 419 | 330 | 133 | 84 | 211.91 | 0.027334 | 0.00756 | 372 | 0.9831 | 0.036411 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.58599 | 67.0844 | 152.7298 | 40.39%
Bay Area | NB_North Bay | PUEBLO 2102 | 345 | PUEBLO 2102656 | 0.36807 | 10.0072 | 0.29223 | 0.12973 | 0.16231 | 0.29223 | 84 | 158 | 19 | 8 | 3 | 1 | 0 | 14 | 0 | 158 |  | 19 | 8 | 0 | 16 | 7 | 21.92 | 0.03678 | 0.00122 | 373 | 0.32525 | 0.036139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.18065 | 98.5764 | 65.0162 | 44.39%
North Coast | HU_Humboldt | WILLITS 1103 | 512 | WILLITS 1103696 | 4.4235 | 135.3613 | 7.0737 | 0 | 7.0737 | 0 | 959 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 1 | 1754 |  | 318 | 211 | 1754 | 318 | 211 | 593.52 | 0.032679 | 0.02161 | 374 | 1.1132 | 0.03591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 1.1132 | 44.9554 | 44.9554 | 0%
Sierra | SI_Sierra | CLARKSVILLE 2104 | 508 | CLARKSVILLE 210413352 | 29.9731 | 873.724 | 36.2409 | 30.8117 | 5.4292 | 33.6769 | 2089 | 7049 | 3020 | 2425 | 2933 | 2363 | 2 | 1430 | 0.070749 | 7318 |  | 3069 | 2457 | 269 | 136 | 94 | 210.53 | 0.034305 | 0.0097 | 375 | 13.4695 | 0.035823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 2.0178 | 25.0499 | 84.6833 | 85.02%
Sierra | SI_Sierra | NARROWS 2101 | 2819 | NARROWS 21011202 | 45.6509 | 1123.23 | 45.4824 | 0 | 45.4824 | 0 | 3083 | 0 | 0 | 0 | 0 | 0 | 0 | 987 | 1 | 5611 |  | 1014 | 669 | 5611 | 1014 | 669 | 1894.17 | 0.040643 | 0.0857 | 376 | 19.5689 | 0.035775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 1. <= 10% | 19.5689 | 22.2943 | 22.2943 | 0%
Sierra | SA_Sacramento | DOBBINS 1101 | 2065 | DOBBINS 11011808 | 11.1906 | 304.5886 | 15.3116 | 0 | 15.3116 | 0.11496 | 2234 | 0 | 0 | 0 | 0 | 0 | 0 | 348 | 0.99249 | 4039 |  | 730 | 482 | 4039 | 730 | 482 | 1363.61 | 0.03674 | 0.05577 | 377 | 7.6851 | 0.035745 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 7.6851 | 47.6764 | 47.6764 | 0%
Bay Area | NB_North Bay | STAFFORD 1102 | 590 | STAFFORD 1102524 | 5.7206 | 212.0291 | 6.9686 | 0 | 6.9686 | 0 | 923 | 0 | 0 | 0 | 0 | 0 | 0 | 169 | 1 | 1688 |  | 306 | 203 | 1688 | 306 | 203 | 571.14 | 0.02698 | 0.01717 | 378 | 1.4635 | 0.035696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 1.4635 | 43.9115 | 43.9115 | 0%
Bay Area | MI_Mission | NORTH DUBLIN 2103 | 7656 | NORTH DUBLIN 2103circuit_breaker | 9.9768 | 306.0304 | 13.1883 | 0 | 13.1883 | 0 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 1 | 437 |  | 81 | 54 | 437 | 81 | 54 | 150.3 | 0.032601 | 0.00549 | 379 | 2.6565 | 0.03542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 2.6565 | 6.1418 | 6.1418 | 0%
Bay Area | MI_Mission | VASCO 1102 | 5383 | VASCO 110211338 | 4.5676 | 155.3134 | 7.411 | 0 | 7.411 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | 1 | 139 |  | 27 | 19 | 139 | 27 | 19 | 49.5 | 0.029409 | 0.00165 | 380 | 0.95564 | 0.035394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.95564 | 3.6432 | 3.6432 | 0%
North Valley | NV_North Valley | KANAKA 1101 | 2279 | KANAKA 11011034 | 5.5137 | 245.0958 | 11.4553 | 0 | 11.4553 | 0 | 2651 | 0 | 0 | 0 | 0 | 0 | 0 | 249 | 1 | 4826 |  | 872 | 576 | 4826 | 872 | 576 | 1628.98 | 0.022496 | 0.04079 | 381 | 3.3103 | 0.035216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 3.3103 | 76.1219 | 76.1219 | 0%
Sierra | SI_Sierra | HORSESHOE 1101 | 6475 | HORSESHOE 11011682 | 1.1716 | 17.7038 | 0.60057 | 0 | 0.60057 | 0 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 281 |  | 53 | 36 | 281 | 53 | 36 | 97.9 | 0.066177 | 0.00729 | 382 | 0.31189 | 0.034655 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.31189 | 88.2498 | 88.2498 | 0%
Sierra | SI_Sierra | SMARTVILLE 1101 | 1983 | SMARTVILLE 1101circuit_breaker | 17.9034 | 392.3511 | 16.1027 | 0 | 16.1027 | 0 | 596 | 0 | 0 | 0 | 0 | 0 | 0 | 366 | 1 | 1095 |  | 199 | 132 | 1095 | 199 | 132 | 371.18 | 0.045631 | 0.01888 | 384 | 5.0479 | 0.034575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 5.0479 | 12.3582 | 12.3582 | 0%
North Coast | HU_Humboldt | HARTLEY 1102 | 8449 | HARTLEY 1102524 | 0.79001 | 32.7615 | 2.1576 | 0 | 2.1576 | 0 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1 | 286 |  | 54 | 36 | 286 | 54 | 36 | 99.72 | 0.024114 | 0.00271 | 385 | 0.27561 | 0.034451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.27561 | 25.0281 | 25.0281 | 0%
North Coast | HU_Humboldt | REDBUD 1102 | 4143 | REDBUD 1102circuit_breaker | 12.6017 | 436.7298 | 15.3562 | 4.383 | 10.9733 | 7.9898 | 631 | 383 | 168 | 138 | 4 | 0 | 0 | 426 | 0.47971 | 939 |  | 269 | 205 | 556 | 265 | 205 | 413.09 | 0.028855 | 0.0159 | 386 | 3.5676 | 0.033977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 2.5493 | 24.1495 | 17.5173 | 28.54%
North Coast | HU_Humboldt | FORT SEWARD 1122 | 1419 | FORT SEWARD 1122circuit_breaker | 10.9925 | 399.2229 | 17.035 | 0 | 17.035 | 0 | 4117 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 1 | 7489 |  | 1353 | 892 | 7489 | 1353 | 892 | 2527.62 | 0.027535 | 0.07747 | 387 | 6.8517 | 0.033752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 1. <= 10% | 6.8517 | 79.4245 | 79.4245 | 0%
North Coast | HU_Humboldt | HIGHLANDS 1103 | 5135 | HIGHLANDS 1103482 | 13.0652 | 611.55 | 24.0892 | 21.872 | 2.2174 | 24.0892 | 1005 | 2111 | 569 | 205 | 505 | 162 | 2 | 651 | 0 | 2111 |  | 569 | 205 | 0 | 64 | 43 | 87.68 | 0.021364 | 0.00284 | 388 | 7.917 | 0.033689 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.72876 | 28.8623 | 23.6205 | 90.8%
Bay Area | NB_North Bay | WOODACRE 1102 | 3383 | WOODACRE 1102851 | 1.0376 | 32.1129 | 1.0473 | 0 | 1.0473 | 0 | 311 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1 | 577 |  | 106 | 71 | 577 | 106 | 71 | 197.15 | 0.03231 | 0.00712 | 389 | 0.74053 | 0.033661 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.74053 | 101.208 | 101.208 | 0%
Bay Area | NB_North Bay | NAPA 1102 | 8364 | NAPA 11025039 | 0.12741 | 7.8637 | 6.4352 | 0 | 6.4352 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 169 | 1 | 41 |  | 9 | 7 | 41 | 9 | 7 | 16.02 | 0.016202 | 0.0003 | 390 | 0.10083 | 0.033609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.10083 | 1.3986 | 1.3986 | 0%
Central Valley | FR_Fresno | DUNLAP 1103 | 3421 | DUNLAP 11037040 | 16.0627 | 610.1777 | 25.85 | 0 | 25.85 | 0 | 1105 | 0 | 0 | 0 | 0 | 0 | 0 | 477 | 1 | 2019 |  | 366 | 242 | 2019 | 366 | 242 | 683.13 | 0.026325 | 0.02003 | 391 | 6.6149 | 0.033578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 6.6149 | 14.1586 | 14.1586 | 0%
Central Valley | YO_Yosemite | MARIPOSA 2101 | 1043 | MARIPOSA 210110990 | 76.9705 | 1006.8777 | 39.3913 | 0.23826 | 39.153 | 32.6705 | 4244 | 290 | 216 | 87 | 146 | 70 | 0 | 1246 | 0.17062 | 1607 |  | 454 | 244 | 1317 | 308 | 174 | 540.49 | 0.076445 | 0.04896 | 392 | 5.2697 | 0.033565 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 5.2378 | 7.8666 | 11.5254 | 0.6048%
North Coast | HU_Humboldt | PHILO 1101 | 2034 | PHILO 1101circuit_breaker | 16.8117 | 748.831 | 32.1123 | 0 | 32.1123 | 0 | 7147 | 0 | 0 | 0 | 0 | 0 | 0 | 553 | 1 | 12991 |  | 2345 | 1546 | 12991 | 2345 | 1546 | 4381.84 | 0.022451 | 0.10947 | 393 | 12.3408 | 0.033444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2. >10 - 20% | 1. <= 10% | 12.3408 | 73.025 | 73.025 | 0%
North Coast | SO_Sonoma | CLOVERDALE 1102 | 7419 | CLOVERDALE 11024646 | 8.6618 | 305.7868 | 14.3869 | 1.7682 | 12.6188 | 13.1746 | 545 | 68 | 28 | 16 | 0 | 0 | 0 | 294 | 0.084265 | 152 |  | 43 | 26 | 84 | 43 | 26 | 66.47 | 0.028326 | 0.00253 | 394 | 2.6302 | 0.033293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 2.3069 | 3.4076 | 2.9888 | 12.29%
Central Coast | SJ_San Jose | LLAGAS 2107 | 6331 | LLAGAS 2107XR188 | 0.93071 | 31.4645 | 1.8699 | 0 | 1.8699 | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1 | 241 |  | 45 | 31 | 241 | 45 | 31 | 83.34 | 0.02958 | 0.00277 | 395 | 0.39946 | 0.033289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.39946 | 24.0656 | 24.0656 | 0%
Bay Area | NB_North Bay | CALISTOGA 1101 | 444 | CALISTOGA 11011087 | 0.89679 | 41.4409 | 2.0074 | 0.99451 | 1.0129 | 2.0074 | 309 | 323 | 82 | 28 | 34 | 0 | 0 | 90 | 0 | 323 |  | 82 | 28 | 0 | 48 | 28 | 65.76 | 0.02164 | 0.00216 | 396 | 0.9936 | 0.03312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.50135 | 47.3897 | 40.8491 | 49.54%
North Coast | SO_Sonoma | CLOVERDALE 1102 | 5478 | CLOVERDALE 1102672 | 20.6146 | 574.8027 | 21.7261 | 7.6074 | 14.1188 | 19.4485 | 1358 | 467 | 373 | 235 | 164 | 74 | 3 | 591 | 0.10483 | 727 |  | 420 | 266 | 260 | 256 | 192 | 374.12 | 0.035864 | 0.01909 | 397 | 5.013 | 0.03298 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 3.2577 | 18.1319 | 19.3316 | 35.01%
Sierra | SI_Sierra | BANGOR 1101 | 1087 | BANGOR 11011958 | 25.4385 | 757.5626 | 32.2112 | 27.2847 | 4.9263 | 31.4009 | 2192 | 7065 | 3248 | 2755 | 3043 | 2595 | 0 | 1143 | 0.025154 | 7165 |  | 3266 | 2767 | 100 | 223 | 172 | 314.51 | 0.033579 | 0.01557 | 398 | 14.4657 | 0.032951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 2.2124 | 45.267 | 101.3934 | 84.71%
North Coast | HU_Humboldt | HOPLAND 1101 | 2125 | HOPLAND 11014626 | 19.385 | 633.8802 | 27.1525 | 0 | 27.1525 | 0 | 1643 | 0 | 0 | 0 | 0 | 0 | 0 | 427 | 1 | 2996 |  | 542 | 358 | 2996 | 542 | 358 | 1012.18 | 0.030581 | 0.03447 | 399 | 5.7917 | 0.032907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 5.7917 | 19.9614 | 19.9614 | 0%
Sierra | SI_Sierra | PENRYN 1103 | 5265 | PENRYN 110351658 | 6.0665 | 130.6653 | 6.5983 | 0.54924 | 6.0491 | 0.81477 | 626 | 6 | 0 | 0 | 0 | 0 | 0 | 259 | 0.87652 | 1013 |  | 183 | 122 | 1007 | 183 | 122 | 341.34 | 0.046428 | 0.01767 | 400 | 3.6738 | 0.032801 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 3.368 | 30.2527 | 27.7344 | 8.324%
Central Valley | YO_Yosemite | OAKHURST 1103 | 3279 | OAKHURST 110310570 | 10.4019 | 266.4697 | 9.2928 | 0.0056818 | 9.2871 | 4.9364 | 941 | 52 | 31 | 10 | 0 | 0 | 0 | 390 | 0.4688 | 859 |  | 177 | 107 | 807 | 177 | 107 | 315.12 | 0.039036 | 0.01437 | 401 | 3.3736 | 0.032753 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 3.3715 | 19.0587 | 19.047 | 0.06114%
North Coast | HU_Humboldt | MIDDLETOWN 1103 | 3432 | MIDDLETOWN 1103830 | 22.3958 | 531.2528 | 23.6456 | 0 | 23.6456 | 0 | 1192 | 0 | 0 | 0 | 0 | 0 | 0 | 368 | 1 | 2177 |  | 395 | 261 | 2177 | 395 | 261 | 737.08 | 0.042157 | 0.03463 | 402 | 4.3884 | 0.03275 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 4.3884 | 16.705 | 16.705 | 0%
Sierra | SI_Sierra | CLARKSVILLE 2105 | 6968 | CLARKSVILLE 210575884 | 5.0673 | 219.6633 | 8.8278 | 0.74242 | 8.0854 | 0.74242 | 337 | 10 | 1 | 0 | 1 | 0 | 0 | 185 | 0.9159 | 582 |  | 106 | 70 | 572 | 105 | 70 | 195.33 | 0.023068 | 0.00504 | 403 | 2.5391 | 0.032553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 2.3256 | 12.9863 | 12.0075 | 8.41%
North Coast | SO_Sonoma | CLOVERDALE 1101 | 1782 | CLOVERDALE 1101112 | 13.0378 | 446.2114 | 18.0875 | 0 | 18.0875 | 0 | 2468 | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 1 | 4494 |  | 812 | 536 | 4494 | 812 | 536 | 1516.9 | 0.029219 | 0.04934 | 404 | 8.0196 | 0.032468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 8.0196 | 44.8929 | 44.8929 | 0%
Bay Area | MI_Mission | SUNOL 1101 | 5193 | SUNOL 1101MR169 | 0.72704 | 46.1803 | 2.6962 | 1.5833 | 1.1129 | 1.9312 | 20 | 19 | 12 | 2 | 0 | 0 | 0 | 76 | 0.28372 | 33 |  | 15 | 4 | 14 | 15 | 4 | 21.81 | 0.015744 | 0.00049 | 405 | 0.45435 | 0.032454 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.18754 | 13.4786 | 5.5634 | 58.72%
Bay Area | DI_Diablo | TASSAJARA 2106 | 7752 | TASSAJARA 2106circuit_breaker | 0.48925 | 21.1211 | 0.60095 | 0 | 0.60095 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 1 | 105 |  | 21 | 15 | 105 | 21 | 15 | 38.22 | 0.023164 | 0.00101 | 406 | 0.031908 | 0.031908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.031908 | 34.9448 | 34.9448 | 0%
Bay Area | MI_Mission | SAN RAMON 2108 | 7037 | SAN RAMON 2108circuit_breaker | 8.0398 | 243.9046 | 8.936 | 5.3862 | 3.5498 | 8.2542 | 1036 | 1499 | 311 | 99 | 76 | 29 | 3 | 451 | 0.0763 | 1643 |  | 337 | 116 | 144 | 261 | 87 | 370.53 | 0.032963 | 0.01789 | 407 | 3.5237 | 0.031745 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 1.3998 | 73.525 | 37.7127 | 60.28%
North Coast | HU_Humboldt | HARTLEY 1101 | 5749 | HARTLEY 11011306 | 6.3427 | 258.0736 | 11.3739 | 0 | 11.3739 | 0 | 531 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 1 | 977 |  | 178 | 118 | 977 | 178 | 118 | 331.79 | 0.024577 | 0.0091 | 408 | 2.5372 | 0.031715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 2.5372 | 15.6499 | 15.6499 | 0%
North Valley | NV_North Valley | PANORAMA 1102 | 9280 | PANORAMA 11021632 | 2.9019 | 160.4819 | 8.9324 | 0 | 8.9324 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 1 | 119 |  | 24 | 16 | 119 | 24 | 16 | 43.59 | 0.018083 | 0.0009 | 409 | 0.41176 | 0.031674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.41176 | 2.6869 | 2.6869 | 0%
Sierra | SA_Sacramento | PEABODY 2113 | 6966 | PEABODY 2113circuit_breaker | 0.82088 | 23.9049 | 0.77178 | 0 | 0.77178 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1 | 25 |  | 6 | 5 | 25 | 6 | 5 | 10.47 | 0.03434 | 0.00043 | 410 | 0.063256 | 0.031628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.063256 | 7.7742 | 7.7742 | 0%
Central Valley | ST_Stockton | ELECTRA 1101 | 6091 | ELECTRA 11011238 | 2.966 | 111.9826 | 5.0858 | 0 | 5.0858 | 0 | 546 | 1 | 0 | 0 | 0 | 0 | 0 | 109 | 1 | 1005 |  | 183 | 121 | 1004 | 183 | 121 | 341.07 | 0.026486 | 0.01008 | 411 | 1.2918 | 0.031508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 1.2918 | 35.9826 | 35.9826 | 0%
North Coast | SO_Sonoma | FULTON 1107 | 3175 | FULTON 1107214 | 22.9527 | 762.9742 | 32.1063 | 23.3939 | 8.7121 | 31.8188 | 4273 | 6606 | 2030 | 1237 | 1499 | 894 | 17 | 1651 | 0.0089546 | 6676 |  | 2043 | 1245 | 70 | 544 | 351 | 751.58 | 0.030083 | 0.03403 | 412 | 13.3226 | 0.031347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 3.6151 | 62.4417 | 63.6325 | 72.86%
North Coast | SO_Sonoma | COTATI 1105 | 3347 | COTATI 1105616 | 0.87354 | 48.2614 | 2.3752 | 2.3324 | 0.042803 | 2.3752 | 90 | 100 | 13 | 0 | 6 | 0 | 0 | 66 | 0 | 100 |  | 13 | 0 | 0 | 7 | 0 | 9.59 | 0.0181 | 0.00026 | 413 | 0.31337 | 0.031337 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.0056473 | 163.5398 | 5.4732 | 98.2%
Central Valley | YO_Yosemite | BEAR VALLEY 2105 | 8781 | BEAR VALLEY 21059570 | 8.2828 | 212.3474 | 7.9159 | 0 | 7.9159 | 0 | 207 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1 | 388 |  | 72 | 48 | 388 | 72 | 48 | 133.56 | 0.039006 | 0.00584 | 414 | 1.6291 | 0.03133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 1.6291 | 9.0956 | 9.0956 | 0%
North Coast | HU_Humboldt | GARBERVILLE 1102 | 9323 | GARBERVILLE 110256048 | 3.3436 | 110.3438 | 5.4199 | 0.57746 | 4.8422 | 4.7241 | 3255 | 2337 | 2334 | 1864 | 0 | 0 | 0 | 140 | 0.12839 | 3097 |  | 2471 | 1955 | 760 | 2471 | 1955 | 3453.67 | 0.030301 | 0.1557 | 415 | 2.8488 | 0.031305 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 2. >10 - 20% | 1. <= 10% | 2.5452 | 510.3016 | 455.9136 | 10.65%
North Coast | HU_Humboldt | GARBERVILLE 1102 | 5213 | GARBERVILLE 11024744 | 11.5674 | 366.145 | 17.0549 | 0 | 17.0549 | 0 | 4105 | 0 | 0 | 0 | 0 | 0 | 0 | 452 | 1 | 7467 |  | 1349 | 889 | 7467 | 1349 | 889 | 2520.16 | 0.031592 | 0.08862 | 416 | 6.2493 | 0.031247 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 1. <= 10% | 6.2493 | 79.0974 | 79.0974 | 0%
Central Valley | ST_Stockton | CORRAL 1103 | 2206 | CORRAL 110313474 | 3.9438 | 72.4403 | 4.2739 | 0 | 4.2739 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 1 | 303 |  | 57 | 38 | 303 | 57 | 38 | 105.36 | 0.054442 | 0.00645 | 417 | 0.87484 | 0.031244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.87484 | 13.3369 | 13.3369 | 0%
North Valley | NV_North Valley | CHALLENGE 1102 | 5557 | CHALLENGE 11021064 | 12.643 | 453.7913 | 19.8066 | 0 | 19.8066 | 0 | 10938 | 0 | 0 | 0 | 0 | 0 | 0 | 421 | 1 | 19875 |  | 3587 | 2363 | 19875 | 3587 | 2363 | 6702.94 | 0.027861 | 0.20781 | 418 | 9.1991 | 0.031183 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 2. >10 - 20% | 1. <= 10% | 9.1991 | 181.101 | 181.101 | 0%
North Coast | HU_Humboldt | HOOPA 1101 | 1014 | HOOPA 11013290 | 9.4565 | 292.2648 | 12.8576 | 0 | 12.8576 | 0 | 4402 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 1 | 8006 |  | 1446 | 953 | 8006 | 1446 | 953 | 2701.56 | 0.032356 | 0.09729 | 419 | 6.2767 | 0.031073 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 1. <= 10% | 6.2767 | 112.4629 | 112.4629 | 0%
North Valley | NV_North Valley | ANDERSON 1101 | 5882 | ANDERSON 1101circuit_breaker | 2.9107 | 91.7089 | 3.3239 | 0 | 3.3239 | 0 | 287 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 1 | 533 |  | 98 | 66 | 533 | 98 | 66 | 182.23 | 0.031739 | 0.00647 | 420 | 1.2353 | 0.030883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 1.2353 | 29.4838 | 29.4838 | 0%
Sierra | SA_Sacramento | ARBUCKLE 1104 | 6311 | ARBUCKLE 110447282 | 1.3954 | 48.5155 | 2.4371 | 0 | 2.4371 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1 | 87 |  | 18 | 13 | 87 | 18 | 13 | 32.49 | 0.028763 | 0.00108 | 421 | 0.21469 | 0.03067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.21469 | 7.3858 | 7.3858 | 0%
Central Valley | YO_Yosemite | OAKHURST 1101 | 3215 | OAKHURST 1101circuit_breaker | 1.8813 | 39.813 | 0.83977 | 0.60436 | 0.23542 | 0.83977 | 122 | 300 | 122 | 52 | 82 | 35 | 0 | 48 | 0 | 300 |  | 122 | 52 | 0 | 40 | 17 | 54.8 | 0.047255 | 0.00393 | 422 | 0.94705 | 0.03055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.26549 | 169.9115 | 145.2774 | 71.97%
Central Valley | YO_Yosemite | BEAR VALLEY 2105 | 5210 | BEAR VALLEY 210511210 | 12.565 | 389.5246 | 17.0117 | 0.075947 | 16.9358 | 0.075947 | 555 | 2 | 0 | 0 | 0 | 0 | 0 | 305 | 0.99554 | 1018 |  | 185 | 123 | 1016 | 185 | 123 | 344.89 | 0.032257 | 0.01241 | 423 | 3.1464 | 0.030547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 3.1323 | 10.9236 | 10.8748 | 0.4464%
Bay Area | NB_North Bay | CALISTOGA 1102 | 4284 | CALISTOGA 1102769230 | 7.6629 | 308.6124 | 10.5519 | 4.7125 | 5.8394 | 8.5705 | 2263 | 2817 | 416 | 216 | 218 | 86 | 0 | 436 | 0.18778 | 3591 |  | 556 | 308 | 774 | 338 | 222 | 532.72 | 0.02483 | 0.01745 | 424 | 2.9316 | 0.030538 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 1.6223 | 57.8827 | 52.692 | 44.66%
North Valley | NV_North Valley | RED BLUFF 1104 | 903 | RED BLUFF 11041630 | 1.6457 | 52.0356 | 2.4892 | 0.6108 | 1.8782 | 0.6108 | 181 | 55 | 2 | 1 | 2 | 1 | 0 | 56 | 0.75462 | 312 |  | 50 | 33 | 257 | 48 | 32 | 88.89 | 0.031627 | 0.00316 | 425 | 0.70229 | 0.030534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.52991 | 25.5561 | 20.0867 | 24.54%
Sierra | SA_Sacramento | MAXWELL 1105 | 6478 | MAXWELL 11053008 | 1.3509 | 71.4937 | 8.418 | 0 | 8.418 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 1 | 121 |  | 24 | 17 | 121 | 24 | 17 | 43.77 | 0.018896 | 0.00094 | 426 | 0.51865 | 0.030509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.51865 | 2.851 | 2.851 | 0%
North Coast | SO_Sonoma | FITCH MOUNTAIN 1113 | 4180 | FITCH MOUNTAIN 11134566 | 8.8126 | 322.9736 | 12.0008 | 0 | 12.0008 | 0.020455 | 3590 | 0 | 0 | 0 | 0 | 0 | 0 | 355 | 0.9983 | 6520 |  | 1178 | 777 | 6520 | 1178 | 777 | 2200.66 | 0.027286 | 0.06684 | 427 | 5.9751 | 0.030178 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 5.9751 | 98.1605 | 98.1605 | 0%
North Valley | NV_North Valley | STILLWATER 1101 | 1463 | STILLWATER 110148950 | 6.7339 | 215.8596 | 9.6201 | 0 | 9.6201 | 0 | 1678 | 0 | 0 | 0 | 0 | 0 | 0 | 266 | 1 | 3059 |  | 554 | 366 | 3059 | 554 | 366 | 1034.29 | 0.031196 | 0.03594 | 428 | 5.4295 | 0.030164 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 5.4295 | 57.5879 | 57.5879 | 0%
North Coast | HU_Humboldt | WILLITS 1103 | 7617 | WILLITS 1103826 | 6.1808 | 195.9797 | 8.7223 | 0.20701 | 8.5153 | 0.30057 | 4052 | 472 | 92 | 48 | 55 | 34 | 0 | 242 | 0.96554 | 7589 |  | 1377 | 896 | 7117 | 1322 | 862 | 2451.67 | 0.031538 | 0.0867 | 429 | 3.4771 | 0.029975 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 1. <= 10% | 3.3946 | 155.2492 | 157.8703 | 2.373%
North Valley | NV_North Valley | CORNING 1102 | 7739 | CORNING 11021900 | 0.98864 | 31.3631 | 1.8585 | 0 | 1.8585 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 1 | 16 |  | 5 | 4 | 16 | 5 | 4 | 8.29 | 0.031522 | 0.00033 | 430 | 0.089467 | 0.029822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.089467 | 2.6903 | 2.6903 | 0%
North Coast | SO_Sonoma | PETALUMA C 1108 | 6662 | PETALUMA C 1108208 | 16.1262 | 340.4353 | 11.8309 | 11.0477 | 0.78314 | 11.8309 | 705 | 798 | 307 | 129 | 236 | 69 | 0 | 352 | 0 | 798 |  | 307 | 129 | 0 | 71 | 60 | 97.27 | 0.047369 | 0.00699 | 431 | 0.059522 | 0.029761 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.0039401 | 90.6602 | 25.9491 | 93.38%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1103 | 2407 | SAN LUIS OBISPO 110342344 | 5.4986 | 218.2551 | 9.6568 | 0 | 9.6568 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 1 | 267 |  | 50 | 34 | 267 | 50 | 34 | 92.53 | 0.025194 | 0.00262 | 432 | 2.0277 | 0.029387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 2.0277 | 5.1777 | 5.1777 | 0%
Bay Area | NB_North Bay | SILVERADO 2104 | 4559 | SILVERADO 210478268 | 9.2007 | 307.3726 | 11.889 | 6.1256 | 5.7636 | 11.8426 | 4135 | 9220 | 3741 | 2232 | 3152 | 1858 | 0 | 659 | 0.0039029 | 9249 |  | 3746 | 2235 | 29 | 594 | 377 | 816.39 | 0.029933 | 0.03697 | 433 | 5.9 | 0.029353 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 2. >10 - 20% | 2. >10 - 20% | 2.8603 | 103.0599 | 315.0808 | 51.52%
North Coast | HU_Humboldt | PHILO 1101 | 4955 | PHILO 11013700 | 12.952 | 418.4916 | 17.478 | 0 | 17.478 | 0 | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 1 | 6114 |  | 1105 | 729 | 6114 | 1105 | 729 | 2064.11 | 0.030949 | 0.07111 | 434 | 4.4475 | 0.02926 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 4.4475 | 63.2222 | 63.2222 | 0%
Sierra | SI_Sierra | NARROWS 2105 | 4809 | NARROWS 21052748 | 11.133 | 343.8892 | 13.9008 | 0 | 13.9008 | 0 | 3027 | 0 | 0 | 0 | 0 | 0 | 0 | 335 | 1 | 5509 |  | 996 | 657 | 5509 | 996 | 657 | 1860.33 | 0.032374 | 0.06705 | 435 | 5.427 | 0.029177 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 5.427 | 71.6508 | 71.6508 | 0%
North Valley | NV_North Valley | CEDAR CREEK 1101 | 3510 | CEDAR CREEK 11011608 | 19.5282 | 794.2142 | 32.8294 | 0 | 32.8294 | 0 | 8143 | 0 | 0 | 0 | 0 | 0 | 0 | 680 | 1 | 14800 |  | 2671 | 1760 | 14800 | 2671 | 1760 | 4991.27 | 0.024588 | 0.13657 | 436 | 12.83 | 0.029093 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 2. >10 - 20% | 1. <= 10% | 12.83 | 81.3601 | 81.3601 | 0%
Sierra | SA_Sacramento | JAMESON 1105 | 3858 | JAMESON 11059472 | 1.3757 | 55.9335 | 2.1313 | 0 | 2.1313 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1 | 212 |  | 40 | 27 | 212 | 40 | 27 | 73.88 | 0.024595 | 0.00205 | 437 | 0.95833 | 0.02904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.95833 | 18.7683 | 18.7683 | 0%
North Coast | SO_Sonoma | GEYSERVILLE 1101 | 7546 | GEYSERVILLE 110179788 | 18.9576 | 843.6386 | 39.6341 | 0 | 39.6341 | 0 | 3979 | 0 | 0 | 0 | 0 | 0 | 0 | 498 | 1 | 7238 |  | 1307 | 862 | 7238 | 1307 | 862 | 2442.01 | 0.022471 | 0.06107 | 438 | 9.8744 | 0.028957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 9.8744 | 32.9767 | 32.9767 | 0%
Central Valley | YO_Yosemite | MARIPOSA 2102 | 930 | MARIPOSA 21029590 | 29.9841 | 1017.5896 | 36.1254 | 1.2492 | 34.8759 | 2.2989 | 4683 | 553 | 107 | 40 | 71 | 27 | 0 | 1271 | 0.93636 | 8528 |  | 1547 | 989 | 7975 | 1476 | 962 | 2739.87 | 0.029466 | 0.09044 | 439 | 14.6437 | 0.02894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 1. <= 10% | 14.1372 | 42.3214 | 42.8231 | 3.458%
Central Valley | FR_Fresno | STONE CORRAL 1110 | 676 | STONE CORRAL 111075288 | 0.76455 | 32.856 | 1.9907 | 0 | 1.9907 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 1 | 94 |  | 19 | 13 | 94 | 19 | 13 | 34.49 | 0.02327 | 0.00092 | 440 | 0.14235 | 0.02847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.14235 | 9.5443 | 9.5443 | 0%
Central Coast | LP_Los Padres | GOLDTREE 1105 | 6713 | GOLDTREE 1105circuit_breaker | 1.316 | 154.8778 | 7.7301 | 7.125 | 0.60511 | 7.125 | 56 | 155 | 12 | 2 | 12 | 2 | 0 | 135 | 0.07828 | 164 |  | 14 | 3 | 9 | 2 | 1 | 3.55 | 0.0084971 | 4e-05 | 441 | 0.6495 | 0.028239 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.050843 | 3.3052 | 1.8111 | 92.17%
Bay Area | NB_North Bay | WOODACRE 1102 | 64 | WOODACRE 1102circuit_breaker | 9.926 | 411.0411 | 19.1551 | 0 | 19.1551 | 0 | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 1 | 10182 |  | 1838 | 1212 | 10182 | 1838 | 1212 | 3434.44 | 0.024148 | 0.09229 | 442 | 8.3115 | 0.028175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 1. <= 10% | 8.3115 | 95.9535 | 95.9535 | 0%
Bay Area | NB_North Bay | SILVERADO 2104 | 1019 | SILVERADO 2104726 | 15.9867 | 720.8566 | 26.7544 | 22.0708 | 4.6833 | 26.2723 | 1465 | 3138 | 841 | 329 | 628 | 183 | 0 | 719 | 0.018016 | 3186 |  | 850 | 335 | 48 | 222 | 152 | 308.46 | 0.022177 | 0.01024 | 443 | 7.3045 | 0.028094 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 1.2786 | 47.4021 | 31.7705 | 82.49%
North Coast | HU_Humboldt | KONOCTI 1102 | 7563 | KONOCTI 1102716 | 7.1993 | 323.1749 | 12.8949 | 9.2483 | 3.6468 | 12.8949 | 1308 | 2830 | 757 | 449 | 552 | 340 | 0 | 371 | 0 | 2830 |  | 757 | 449 | 0 | 205 | 109 | 280.85 | 0.022277 | 0.0095 | 444 | 3.87 | 0.028043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 1.0945 | 56.214 | 58.7054 | 71.72%
North Coast | HU_Humboldt | HIGHLANDS 1103 | 49 | HIGHLANDS 1103520 | 34.5387 | 1152.2759 | 49.0095 | 38.7195 | 10.29 | 48.6911 | 3776 | 6570 | 1221 | 508 | 942 | 342 | 2 | 1534 | 0.0064961 | 6615 |  | 1229 | 513 | 45 | 287 | 171 | 397.24 | 0.029974 | 0.01789 | 445 | 12.2004 | 0.027919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 2.5616 | 27.8913 | 25.0768 | 79%
Central Valley | YO_Yosemite | MARIPOSA 2102 | 4431 | MARIPOSA 210237288 | 47.2273 | 2171.0131 | 83.5008 | 0 | 83.5008 | 6.9591 | 4822 | 27 | 27 | 26 | 0 | 0 | 0 | 2373 | 0.91666 | 8065 |  | 1478 | 983 | 8038 | 1478 | 983 | 2748.28 | 0.021754 | 0.06686 | 447 | 22.9229 | 0.027718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 22.9229 | 17.7004 | 17.7004 | 0%
Central Valley | YO_Yosemite | BEAR VALLEY 2105 | 3201 | BEAR VALLEY 21059480 | 4.4313 | 286.616 | 11.8903 | 0 | 11.8903 | 0 | 196 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 1 | 368 |  | 68 | 46 | 368 | 68 | 46 | 126.28 | 0.015461 | 0.00219 | 448 | 1.7638 | 0.027559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 1.7638 | 5.7189 | 5.7189 | 0%
Central Valley | YO_Yosemite | MARIPOSA 2102 | 6532 | MARIPOSA 21021960 | 17.3154 | 634.905 | 24.5136 | 0.4447 | 24.0689 | 14.9335 | 2178 | 219 | 216 | 176 | 5 | 5 | 0 | 963 | 0.39081 | 1770 |  | 496 | 361 | 1551 | 491 | 356 | 812.26 | 0.027272 | 0.02784 | 449 | 8.0077 | 0.02733 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 7.8624 | 20.3997 | 20.2336 | 1.814%
North Valley | NV_North Valley | CLARK ROAD 1102 | 6409 | CLARK ROAD 110281296 | 5.8651 | 195.3138 | 9.5549 | 8.4466 | 1.1081 | 9.5545 | 375 | 604 | 218 | 103 | 176 | 88 | 0 | 324 | 3.9643e-05 | 604 |  | 218 | 103 | 0 | 42 | 15 | 57.54 | 0.030029 | 0.00262 | 451 | 1.4416 | 0.0272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.16719 | 37.9012 | 22.8155 | 88.4%
Central Valley | YO_Yosemite | MERCED FALLS 1102 | 6188 | MERCED FALLS 110238748 | 11.7707 | 413.5929 | 16.9456 | 15.8189 | 1.1267 | 16.9456 | 314 | 1287 | 249 | 210 | 239 | 201 | 0 | 650 | 0 | 1287 |  | 249 | 210 | 0 | 10 | 9 | 13.7 | 0.02846 | 0.00059 | 452 | 3.1264 | 0.027186 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.20787 | 8.8754 | 14.694 | 93.35%
Central Valley | YO_Yosemite | PEORIA 1704 | 6535 | PEORIA 170411232 | 8.807 | 315.623 | 12.2619 | 9.1061 | 3.1559 | 12.2619 | 322 | 788 | 93 | 76 | 82 | 65 | 0 | 244 | 0 | 788 |  | 93 | 76 | 0 | 11 | 11 | 15.07 | 0.027904 | 0.00064 | 453 | 3.4178 | 0.027125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.87964 | 3.4856 | 7.5844 | 74.26%
Bay Area | NB_North Bay | WOODACRE 1101 | 4898 | WOODACRE 11011456 | 2.4306 | 122.5746 | 3.7483 | 1.9515 | 1.7968 | 3.7483 | 1702 | 2367 | 569 | 195 | 443 | 128 | 0 | 179 | 0 | 2367 |  | 569 | 195 | 0 | 126 | 67 | 172.62 | 0.01983 | 0.0052 | 454 | 1.6794 | 0.027087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.80504 | 70.1254 | 151.8023 | 52.06%
Central Coast | SJ_San Jose | MORGAN HILL 2111 | 5449 | MORGAN HILL 2111XR186 | 0.83203 | 37.3975 | 3.3911 | 0 | 3.3911 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 1 | 79 |  | 16 | 12 | 79 | 16 | 12 | 29.03 | 0.022248 | 0.00074 | 455 | 0.21547 | 0.026934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.21547 | 4.7182 | 4.7182 | 0%
Sierra | SA_Sacramento | MADISON 2101 | 6168 | MADISON 210137082 | 1.2478 | 26.6592 | 1.6544 | 0 | 1.6544 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 1 | 128 |  | 25 | 17 | 128 | 25 | 17 | 45.77 | 0.046806 | 0.00243 | 458 | 0.18622 | 0.026603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.18622 | 15.1116 | 15.1116 | 0%
Sierra | SI_Sierra | SHINGLE SPRINGS 2109 | 4047 | SHINGLE SPRINGS 2109circuit_breaker | 16.3617 | 615.6813 | 28.8778 | 0 | 28.8778 | 0 | 5091 | 0 | 0 | 0 | 0 | 0 | 0 | 663 | 1 | 9257 |  | 1672 | 1102 | 9257 | 1672 | 1102 | 3123.77 | 0.026575 | 0.0924 | 459 | 10.9005 | 0.026522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 1. <= 10% | 10.9005 | 57.8991 | 57.8991 | 0%
North Coast | SO_Sonoma | GEYSERVILLE 1101 | 6292 | GEYSERVILLE 110137454 | 4.4238 | 199.1574 | 6.3661 | 0 | 6.3661 | 0 | 963 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 1 | 1761 |  | 320 | 211 | 1761 | 320 | 211 | 596.89 | 0.022213 | 0.01478 | 460 | 2.2257 | 0.026185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 2.2257 | 50.2663 | 50.2663 | 0%
North Valley | NV_North Valley | BIG BEND 1102 | 3547 | BIG BEND 11021972 | 12.4062 | 463.8688 | 21.1589 | 0 | 21.1589 | 0 | 13418 | 0 | 0 | 0 | 0 | 0 | 0 | 499 | 1 | 24379 |  | 4399 | 2898 | 24379 | 4399 | 2898 | 8220.74 | 0.026745 | 0.24465 | 461 | 8.028 | 0.02615 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 2. >10 - 20% | 1. <= 10% | 8.028 | 207.903 | 207.903 | 0%
Sierra | SA_Sacramento | VACAVILLE 1104 | 4023 | VACAVILLE 1104circuit_breaker | 0.56421 | 27.1013 | 0.42273 | 0 | 0.42273 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 72 |  | 15 | 11 | 72 | 15 | 11 | 27.03 | 0.020818 | 0.00065 | 462 | 0.41706 | 0.026066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.41706 | 35.4839 | 35.4839 | 0%
North Coast | SO_Sonoma | COTATI 1103 | 5041 | COTATI 1103132 | 12.7367 | 631.1283 | 24.9669 | 0 | 24.9669 | 0 | 1213 | 0 | 0 | 0 | 0 | 0 | 0 | 485 | 1 | 2215 |  | 401 | 265 | 2215 | 401 | 265 | 748.72 | 0.020181 | 0.01683 | 463 | 2.1508 | 0.025913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 2.1508 | 16.0613 | 16.0613 | 0%
North Coast | HU_Humboldt | BRIDGEVILLE 1101 | 8339 | BRIDGEVILLE 110169866 | 3.7418 | 165.3214 | 6.8002 | 5.7169 | 1.0833 | 6.8002 | 1774 | 4468 | 697 | 461 | 587 | 406 | 0 | 176 | 0 | 4468 |  | 697 | 461 | 0 | 110 | 55 | 150.7 | 0.022634 | 0.00518 | 464 | 2.0195 | 0.025891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.32173 | 101.5385 | 102.4971 | 84.07%
North Coast | HU_Humboldt | UPPER LAKE 1101 | 6851 | UPPER LAKE 1101472084 | 2.4193 | 78.9427 | 3.4735 | 1.9549 | 1.5186 | 3.4735 | 281 | 311 | 56 | 33 | 0 | 0 | 0 | 103 | 0 | 311 |  | 56 | 33 | 0 | 56 | 33 | 76.72 | 0.030646 | 0.00357 | 465 | 1.29 | 0.025801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.56399 | 36.877 | 16.1221 | 56.28%
Bay Area | NB_North Bay | SILVERADO 2104 | 2773 | SILVERADO 2104806 | 9.4365 | 449.2822 | 20.5854 | 14.1167 | 6.4688 | 19.5299 | 1480 | 2226 | 513 | 329 | 167 | 89 | 0 | 450 | 0.051274 | 2364 |  | 538 | 346 | 138 | 371 | 257 | 520.69 | 0.021003 | 0.0162 | 466 | 3.8424 | 0.025788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 1.2074 | 57.3527 | 26.135 | 68.58%
North Coast | HU_Humboldt | FRUITLAND 1142 | 7532 | FRUITLAND 11426064 | 3.0713 | 163.4529 | 7.8886 | 0 | 7.8886 | 0 | 3824 | 0 | 0 | 0 | 0 | 0 | 0 | 142 | 1 | 6957 |  | 1257 | 829 | 6957 | 1257 | 829 | 2348.22 | 0.01879 | 0.04911 | 467 | 1.132 | 0.025728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 1.132 | 159.3431 | 159.3431 | 0%
North Valley | NV_North Valley | GIRVAN 1101 | 5137 | GIRVAN 11011636 | 7.7549 | 364.0173 | 19.1061 | 0 | 19.1061 | 0 | 2115 | 0 | 0 | 0 | 0 | 0 | 0 | 468 | 1 | 3853 |  | 697 | 460 | 3853 | 697 | 460 | 1301.66 | 0.021304 | 0.03088 | 468 | 5.4261 | 0.025716 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 2. >10 - 20% | 3. >20 - 30% | 5.4261 | 36.4806 | 36.4806 | 0%
Bay Area | NB_North Bay | SILVERADO 2102 | 7659 | SILVERADO 210258626 | 10.2584 | 415.0623 | 15.0379 | 5.5794 | 9.4585 | 13.2097 | 1833 | 1604 | 416 | 163 | 115 | 11 | 0 | 514 | 0.12157 | 2010 |  | 489 | 212 | 406 | 374 | 201 | 548.92 | 0.024715 | 0.01922 | 469 | 4.7612 | 0.025598 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 2.9947 | 39.5411 | 32.5179 | 37.1%
North Valley | NV_North Valley | RED BLUFF 1105 | 4776 | RED BLUFF 110585632 | 9.2024 | 290.1825 | 12.7148 | 0.48258 | 12.2322 | 0.48258 | 489 | 134 | 15 | 15 | 15 | 15 | 0 | 295 | 0.96205 | 1000 |  | 173 | 120 | 866 | 158 | 105 | 294.4 | 0.031712 | 0.01042 | 470 | 3.3527 | 0.025593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 3.2254 | 12.9167 | 13.6062 | 3.795%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1103 | 2338 | SAN LUIS OBISPO 1103circuit_breaker | 1.7939 | 94.3655 | 3.8703 | 0 | 3.8703 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 1 | 183 |  | 35 | 24 | 183 | 35 | 24 | 64.42 | 0.01901 | 0.00138 | 471 | 0.45971 | 0.025539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.45971 | 9.0433 | 9.0433 | 0%
Central Coast | SJ_San Jose | MORGAN HILL 2105 | 6264 | MORGAN HILL 2105XR070 | 4.134 | 149.1702 | 7.5038 | 0 | 7.5038 | 0 | 475 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | 1 | 875 |  | 160 | 106 | 875 | 160 | 106 | 297.95 | 0.027714 | 0.00922 | 472 | 1.5548 | 0.025489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 1.5548 | 21.3226 | 21.3226 | 0%
Sierra | SI_Sierra | BANGOR 1101 | 749 | BANGOR 11017446 | 26.1035 | 982.8048 | 42.2222 | 17.2754 | 24.9468 | 33.2201 | 7082 | 13508 | 5509 | 5083 | 3466 | 3247 | 0 | 1408 | 0.21321 | 16253 |  | 6004 | 5410 | 2745 | 2538 | 2163 | 3724.11 | 0.02656 | 0.14017 | 473 | 15.0101 | 0.025484 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 2. >10 - 20% | 1. <= 10% | 8.8686 | 101.7366 | 142.2002 | 40.92%
Central Valley | YO_Yosemite | MARIPOSA 2101 | 7470 | MARIPOSA 210197142 | 3.6743 | 127.6927 | 4.2742 | 0.029545 | 4.2447 | 0.19432 | 227 | 77 | 22 | 14 | 0 | 0 | 0 | 133 | 0.95454 | 482 |  | 97 | 64 | 405 | 97 | 64 | 169.34 | 0.028775 | 0.0058 | 474 | 1.1909 | 0.025339 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 1.1827 | 22.852 | 22.6941 | 0.6912%
Bay Area | NB_North Bay | PUEBLO 2103 | 5878 | PUEBLO 210378504 | 4.3905 | 194.8771 | 7.5481 | 1.1123 | 6.4358 | 4.3663 | 3922 | 2131 | 711 | 417 | 359 | 149 | 0 | 343 | 0.42154 | 5138 |  | 1254 | 775 | 3007 | 895 | 626 | 1496.78 | 0.02253 | 0.04193 | 475 | 3.1314 | 0.025253 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 2.67 | 139.0659 | 166.1344 | 14.74%
North Coast | SO_Sonoma | FITCH MOUNTAIN 1113 | 7148 | FITCH MOUNTAIN 11136751 | 12.9601 | 532.2206 | 20.7483 | 0.15303 | 20.5953 | 16.4994 | 10356 | 5705 | 2545 | 407 | 0 | 0 | 0 | 703 | 0.20478 | 9559 |  | 3240 | 865 | 3854 | 3240 | 865 | 4785.66 | 0.024351 | 0.16406 | 476 | 8.0144 | 0.025203 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 2. >10 - 20% | 1. <= 10% | 7.9553 | 157.3177 | 156.1574 | 0.7376%
Bay Area | NB_North Bay | CALISTOGA 1101 | 8719 | CALISTOGA 110189150 | 6.8422 | 236.1685 | 10.1742 | 3.9299 | 6.2445 | 10.1742 | 2342 | 4665 | 1116 | 672 | 204 | 75 | 0 | 432 | 0 | 4665 |  | 1116 | 672 | 0 | 912 | 597 | 1249.44 | 0.028972 | 0.05494 | 477 | 3.0414 | 0.025136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 1.8667 | 146.0483 | 109.6888 | 38.63%
Bay Area | NB_North Bay | CALISTOGA 1101 | 2102 | CALISTOGA 1101736 | 20.5849 | 839.4035 | 34.3621 | 21.2856 | 13.0767 | 34.3015 | 6469 | 10840 | 2364 | 1146 | 871 | 219 | 0 | 1471 | 0.0017637 | 10861 |  | 2368 | 1148 | 21 | 1497 | 929 | 2052.78 | 0.024523 | 0.07634 | 478 | 11.914 | 0.025135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 1. <= 10% | 4.534 | 114.4784 | 68.9131 | 61.94%
Central Coast | LP_Los Padres | CHOLAME 2102 | 3119 | CHOLAME 2102X06 | 18.8109 | 736.2124 | 33.6975 | 32.903 | 0.79451 | 33.6964 | 810 | 1206 | 261 | 92 | 257 | 91 | 0 | 672 | 3.3722e-05 | 1206 |  | 261 | 92 | 0 | 4 | 1 | 5.48 | 0.025551 | 0.00021 | 479 | 7.2765 | 0.025091 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.17156 | 5.0346 | 7.7454 | 97.64%
Central Valley | FR_Fresno | AUBERRY 1101 | 5912 | AUBERRY 1101R2839 | 6.7276 | 290.2122 | 12.2879 | 1.2396 | 11.0481 | 2.5782 | 721 | 336 | 68 | 41 | 1 | 1 | 0 | 381 | 0.79018 | 1380 |  | 258 | 167 | 1044 | 257 | 166 | 446.05 | 0.023182 | 0.01239 | 480 | 3.2266 | 0.025012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 2.9011 | 23.2619 | 20.9963 | 10.09%
North Coast | HU_Humboldt | FRUITLAND 1141 | 8745 | FRUITLAND 114137410 | 2.6677 | 98.1768 | 4.9989 | 0 | 4.9989 | 0.20473 | 3055 | 10 | 10 | 0 | 0 | 0 | 0 | 131 | 0.95904 | 5342 |  | 974 | 636 | 5332 | 974 | 636 | 1814.26 | 0.027173 | 0.05503 | 481 | 1.9989 | 0.024987 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 1.9989 | 194.8443 | 194.8443 | 0%
Sierra | SA_Sacramento | JAMESON 1102 | 7319 | JAMESON 110265516 | 4.3241 | 186.9894 | 7.5547 | 0 | 7.5547 | 0 | 715 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 1 | 1311 |  | 238 | 158 | 1311 | 238 | 158 | 444.05 | 0.023125 | 0.01144 | 482 | 2.8975 | 0.024979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 2.8975 | 31.5034 | 31.5034 | 0%
North Coast | HU_Humboldt | POTTER VALLEY P H 1105 | 2042 | POTTER VALLEY P H 11051904 | 16.3416 | 771.4514 | 30.5985 | 22.7042 | 7.8943 | 30.5985 | 2129 | 4528 | 1005 | 525 | 651 | 350 | 0 | 837 | 0 | 4528 |  | 1005 | 525 | 0 | 354 | 175 | 484.98 | 0.021183 | 0.01559 | 483 | 6.9326 | 0.024759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 1.7886 | 44.8424 | 32.8448 | 74.2%
Bay Area | NB_North Bay | SILVERADO 2102 | 3315 | SILVERADO 2102714 | 1.9682 | 116.4813 | 4.7131 | 0 | 4.7131 | 0.12027 | 755 | 67 | 7 | 7 | 3 | 3 | 0 | 161 | 0.97448 | 1415 |  | 252 | 169 | 1348 | 249 | 166 | 462.45 | 0.016897 | 0.00875 | 484 | 1.1353 | 0.024681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 1.1353 | 52.8318 | 53.4684 | 0%
North Valley | NV_North Valley | OREGON TRAIL 1103 | 4876 | OREGON TRAIL 11031448 | 18.3595 | 686.1786 | 30.4888 | 25.882 | 4.6068 | 30.311 | 3097 | 6859 | 735 | 526 | 679 | 480 | 0 | 937 | 0.005833 | 6892 |  | 741 | 530 | 33 | 62 | 50 | 87.91 | 0.026756 | 0.00345 | 485 | 6.5355 | 0.024662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.98751 | 13.4583 | 24.304 | 84.89%
North Coast | SO_Sonoma | COTATI 1102 | 3787 | COTATI 1102681 | 2.2592 | 90.6856 | 3.5286 | 3.1725 | 0.35606 | 3.5286 | 259 | 735 | 209 | 75 | 203 | 73 | 0 | 139 | 0 | 735 |  | 209 | 75 | 0 | 6 | 2 | 8.22 | 0.024913 | 0.00031 | 486 | 1.3041 | 0.024606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.1316 | 16.8511 | 59.2303 | 89.91%
North Valley | NV_North Valley | PANORAMA 1102 | 4785 | PANORAMA 11021342 | 6.1634 | 271.9574 | 12.2621 | 0 | 12.2621 | 0 | 385 | 0 | 0 | 0 | 0 | 0 | 0 | 237 | 1 | 711 |  | 130 | 87 | 711 | 130 | 87 | 242.09 | 0.022663 | 0.00613 | 487 | 2.1604 | 0.024551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 2.1604 | 10.6018 | 10.6018 | 0%
North Coast | SO_Sonoma | COTATI 1103 | 4620 | COTATI 110379140 | 7.3517 | 246.2828 | 8.5163 | 0.43845 | 8.0778 | 0.5733 | 529 | 72 | 39 | 11 | 39 | 11 | 0 | 219 | 0.93268 | 979 |  | 204 | 121 | 907 | 165 | 110 | 307.68 | 0.029851 | 0.01024 | 488 | 2.0797 | 0.024467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 1.9726 | 20.4263 | 23.9541 | 5.148%
Central Valley | YO_Yosemite | MERCED FALLS 1102 | 1266 | MERCED FALLS 11029470 | 11.6935 | 552.2011 | 22.1943 | 21.3091 | 0.88523 | 22.1943 | 107 | 820 | 146 | 96 | 144 | 96 | 0 | 795 | 0 | 820 |  | 146 | 96 | 0 | 2 | 0 | 2.74 | 0.021176 | 9e-05 | 489 | 3.4217 | 0.024441 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.13648 | 2.2593 | 6.5783 | 96.01%
Central Valley | YO_Yosemite | SAN JOAQUIN NO2 1103 | 4163 | SAN JOAQUIN #2 1103157026 | 3.2755 | 82.0984 | 3.4265 | 0.098485 | 3.328 | 0.098485 | 439 | 6 | 3 | 3 | 3 | 3 | 0 | 79 | 0.97126 | 792 |  | 147 | 99 | 786 | 144 | 96 | 268.02 | 0.039898 | 0.01195 | 490 | 1.0238 | 0.024376 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 0.99435 | 43.2688 | 42.9007 | 2.874%
Central Coast | LP_Los Padres | OCEANO 1106 | 7575 | OCEANO 1106circuit_breaker | 0.38843 | 30.1784 | 1.8017 | 0 | 1.8017 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 1 | 257 |  | 48 | 33 | 257 | 48 | 33 | 88.89 | 0.012871 | 0.00128 | 492 | 0.29134 | 0.024278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.29134 | 26.6414 | 26.6414 | 0%
Sierra | SI_Sierra | PIKE CITY 1101 | 8031 | PIKE CITY 11011720 | 3.1221 | 128.8235 | 6.0767 | 0 | 6.0767 | 1.7407 | 4350 | 235 | 235 | 219 | 0 | 0 | 0 | 179 | 0.71354 | 5880 |  | 1255 | 891 | 5645 | 1255 | 891 | 2227.4 | 0.024235 | 0.06325 | 493 | 2.1584 | 0.024252 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 2.1584 | 206.5264 | 206.5264 | 0%
Central Valley | ST_Stockton | OLETA 1101 | 2652 | OLETA 110163500 | 3.2051 | 100.754 | 6.0699 | 2.5589 | 3.511 | 2.7027 | 162 | 90 | 7 | 4 | 4 | 4 | 0 | 149 | 0.55474 | 260 |  | 39 | 25 | 170 | 35 | 21 | 63.25 | 0.031812 | 0.00232 | 494 | 0.70315 | 0.024246 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.40672 | 9.9687 | 6.4252 | 42.16%
Sierra | SI_Sierra | PENRYN 1107 | 5290 | PENRYN 11072706 | 8.1598 | 143.8619 | 10.0159 | 0 | 10.0159 | 0 | 1208 | 0 | 0 | 0 | 0 | 0 | 0 | 248 | 1 | 2206 |  | 400 | 264 | 2206 | 400 | 264 | 746.54 | 0.05672 | 0.04718 | 495 | 1.594 | 0.024152 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 1.594 | 39.9365 | 39.9365 | 0%
North Coast | HU_Humboldt | LOW GAP 1101 | 4382 | LOW GAP 11014086 | 5.175 | 230.6993 | 11.8585 | 0 | 11.8585 | 0 | 2610 | 0 | 0 | 0 | 0 | 0 | 0 | 242 | 1 | 4752 |  | 859 | 567 | 4752 | 859 | 567 | 1604.51 | 0.022432 | 0.04007 | 496 | 3.1761 | 0.023527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 3.1761 | 72.4374 | 72.4374 | 0%
Bay Area | NB_North Bay | PUEBLO 2103 | 3568 | PUEBLO 2103678 | 22.3552 | 980.5276 | 34.9527 | 0.85322 | 34.0994 | 3.3102 | 11594 | 1788 | 667 | 347 | 420 | 160 | 0 | 1467 | 0.90529 | 20859 |  | 4108 | 2615 | 19071 | 3688 | 2455 | 6768.95 | 0.022799 | 0.17484 | 497 | 13.3968 | 0.023503 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 2. >10 - 20% | 1. <= 10% | 13.0698 | 108.1543 | 117.5304 | 2.441%
North Valley | NV_North Valley | WYANDOTTE 1107 | 1140 | WYANDOTTE 110777578 | 12.7629 | 545.2789 | 22.8545 | 14.5716 | 8.283 | 21.4125 | 3197 | 5281 | 1956 | 1523 | 1735 | 1350 | 0 | 902 | 0.063097 | 5648 |  | 2022 | 1567 | 367 | 287 | 217 | 426.22 | 0.023406 | 0.01397 | 498 | 7.2314 | 0.023479 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 2.6208 | 34.6495 | 88.4726 | 63.76%
North Coast | HU_Humboldt | GARBERVILLE 1102 | 1668 | GARBERVILLE 11022010 | 3.1826 | 152.2064 | 6.9159 | 0 | 6.9159 | 0 | 1715 | 0 | 0 | 0 | 0 | 0 | 0 | 182 | 1 | 3127 |  | 566 | 374 | 3127 | 566 | 374 | 1056.85 | 0.02091 | 0.02461 | 499 | 2.3388 | 0.023388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 2.3388 | 81.8403 | 81.8403 | 0%
Sierra | SI_Sierra | SHINGLE SPRINGS 2105 | 1827 | SHINGLE SPRINGS 2105circuit_breaker | 8.6183 | 495.3824 | 18.7985 | 0 | 18.7985 | 0 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 429 | 1 | 3691 |  | 668 | 441 | 3691 | 668 | 441 | 1247.35 | 0.017397 | 0.02417 | 500 | 5.8423 | 0.023184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 5.8423 | 35.5348 | 35.5348 | 0%
Central Valley | ST_Stockton | NORTH BRANCH 1101 | 1905 | NORTH BRANCH 1101TS1115 | 10.3705 | 443.7833 | 18.9563 | 1.786 | 17.1703 | 1.9419 | 1044 | 322 | 107 | 101 | 107 | 101 | 0 | 390 | 0.89756 | 2035 |  | 418 | 306 | 1713 | 311 | 205 | 580.24 | 0.023368 | 0.01511 | 501 | 4.4229 | 0.023156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 4.0062 | 18.1127 | 22.0508 | 9.422%
North Coast | HU_Humboldt | MIDDLETOWN 1102 | 3891 | MIDDLETOWN 1102878 | 2.5311 | 52.0129 | 2.5233 | 1.5938 | 0.92955 | 2.5233 | 91 | 180 | 48 | 33 | 12 | 3 | 0 | 103 | 0 | 180 |  | 48 | 33 | 0 | 36 | 30 | 49.32 | 0.048663 | 0.00364 | 502 | 0.39264 | 0.023096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.14464 | 38.7286 | 19.0227 | 63.16%
Bay Area | DI_Diablo | BRENTWOOD 2105 | 4601 | BRENTWOOD 2105B504R | 6.5291 | 167.7834 | 8.41 | 0 | 8.41 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 169 | 1 | 94 |  | 19 | 13 | 94 | 19 | 13 | 34.49 | 0.038914 | 0.00154 | 503 | 0.57211 | 0.022885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.57211 | 2.2592 | 2.2592 | 0%
Sierra | SA_Sacramento | PUTAH CREEK 1102 | 7989 | PUTAH CREEK 110264044 | 3.5625 | 112.4029 | 5.582 | 5.0786 | 0.50341 | 5.4337 | 148 | 405 | 176 | 152 | 159 | 136 | 0 | 127 | 0.026567 | 412 |  | 177 | 153 | 7 | 18 | 17 | 25.29 | 0.031694 | 0.00119 | 504 | 1.2995 | 0.022798 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.11719 | 35.7562 | 31.709 | 90.98%
Sierra | SI_Sierra | HIGGINS 1103 | 1677 | HIGGINS 11039753 | 0.973 | 42.4802 | 1.4089 | 0 | 1.4089 | 0 | 299 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 1 | 555 |  | 102 | 68 | 555 | 102 | 68 | 189.69 | 0.022905 | 0.00486 | 505 | 0.86597 | 0.022789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.86597 | 72.3968 | 72.3968 | 0%
Central Valley | YO_Yosemite | COARSEGOLD 2104 | 1785 | COARSEGOLD 210410110 | 34.2127 | 1269.2084 | 48.7303 | 35.9339 | 12.7964 | 46.9011 | 6589 | 13588 | 2352 | 1714 | 2084 | 1498 | 0 | 1719 | 0.037537 | 14038 |  | 2433 | 1767 | 450 | 349 | 269 | 518.63 | 0.026956 | 0.01956 | 506 | 14.9256 | 0.022752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 3.9194 | 27.2733 | 49.9279 | 73.74%
North Coast | SO_Sonoma | COTATI 1105 | 5286 | COTATI 1105634 | 5.703 | 212.4495 | 7.0547 | 6.2273 | 0.82746 | 6.5242 | 252 | 310 | 29 | 7 | 10 | 3 | 0 | 179 | 0.075197 | 345 |  | 36 | 11 | 35 | 26 | 8 | 38.77 | 0.026844 | 0.00145 | 507 | 0.61415 | 0.022746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.072035 | 31.4214 | 5.103 | 88.27%
North Coast | HU_Humboldt | KONOCTI 1102 | 7221 | KONOCTI 1102948 | 2.8391 | 137.4492 | 6.5657 | 5.1975 | 1.3682 | 6.5657 | 786 | 1827 | 201 | 116 | 126 | 65 | 0 | 229 | 0 | 1827 |  | 201 | 116 | 0 | 75 | 51 | 102.75 | 0.020656 | 0.00322 | 508 | 1.6146 | 0.02274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.33645 | 54.8173 | 30.6136 | 79.16%
North Coast | HU_Humboldt | LAYTONVILLE 1102 | 7640 | LAYTONVILLE 1102572 | 10.4694 | 471.6105 | 21.1693 | 0.26345 | 20.9059 | 0.45152 | 7817 | 160 | 49 | 36 | 42 | 31 | 0 | 389 | 0.97867 | 14065 |  | 2559 | 1690 | 13905 | 2517 | 1659 | 4699.74 | 0.022199 | 0.11619 | 509 | 6.721 | 0.022706 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 2. >10 - 20% | 1. <= 10% | 6.6374 | 120.3968 | 120.8825 | 1.244%
Sierra | SI_Sierra | DIAMOND SPRINGS 1106 | 5059 | DIAMOND SPRINGS 110656026 | 6.2003 | 348.5671 | 15.0038 | 5.2998 | 9.7042 | 13.9583 | 5452 | 5623 | 2803 | 2192 | 2449 | 1902 | 0 | 567 | 0.069679 | 6314 |  | 2928 | 2274 | 691 | 479 | 372 | 718.42 | 0.017788 | 0.01772 | 510 | 4.9473 | 0.02259 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 3.1998 | 49.3602 | 195.1507 | 35.32%
Sierra | SI_Sierra | HIGGINS 1109 | 3735 | HIGGINS 1109594 | 6.8848 | 281.7551 | 11.7076 | 0 | 11.7076 | 0 | 1487 | 0 | 0 | 0 | 0 | 0 | 0 | 277 | 1 | 2713 |  | 491 | 324 | 2713 | 491 | 324 | 916.84 | 0.024435 | 0.02495 | 511 | 4.3783 | 0.022453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 4.3783 | 41.9387 | 41.9387 | 0%
North Coast | SO_Sonoma | BELLEVUE 1102 | 6815 | BELLEVUE 1102392 | 0.072183 | 8.6735 | 0.25284 | 0 | 0.25284 | 0 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 30 |  | 7 | 6 | 29 | 7 | 6 | 12.2 | 0.0083222 | 0.00012 | 512 | 0.067165 | 0.022388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.067165 | 27.6854 | 27.6854 | 0%
North Coast | HU_Humboldt | MIDDLETOWN 1102 | 1017 | MIDDLETOWN 11021312 | 7.1419 | 205.7622 | 8.2727 | 6.3222 | 1.9506 | 8.2727 | 257 | 1208 | 212 | 74 | 171 | 54 | 0 | 316 | 0 | 1208 |  | 212 | 74 | 0 | 41 | 20 | 56.17 | 0.03471 | 0.00296 | 513 | 2.2378 | 0.022378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.52764 | 21.0195 | 25.6264 | 76.42%
Bay Area | NB_North Bay | SILVERADO 2104 | 6904 | SILVERADO 2104708 | 1.0242 | 62.0987 | 2.4214 | 1.4468 | 0.97462 | 2.3917 | 499 | 1126 | 352 | 177 | 220 | 81 | 0 | 147 | 0.01228 | 1137 |  | 354 | 178 | 11 | 134 | 97 | 184.57 | 0.016493 | 0.0046 | 514 | 1.3627 | 0.02234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.54851 | 137.4893 | 146.1963 | 59.75%
Bay Area | NB_North Bay | CALISTOGA 1102 | 3092 | CALISTOGA 1102634 | 5.8078 | 348.7434 | 11.8375 | 6.6112 | 5.2263 | 11.2021 | 2892 | 4385 | 1236 | 398 | 690 | 95 | 0 | 591 | 0.053678 | 4668 |  | 1287 | 432 | 283 | 597 | 337 | 843.36 | 0.016654 | 0.02067 | 515 | 3.7169 | 0.022257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 1.641 | 114.2294 | 108.7223 | 55.85%
Central Valley | YO_Yosemite | MARIPOSA 2101 | 1410 | MARIPOSA 21019400 | 31.188 | 1667.4398 | 60.8176 | 31.1172 | 29.7004 | 58.2525 | 10159 | 14706 | 4014 | 2461 | 3055 | 1829 | 0 | 2415 | 0.042178 | 15485 |  | 4155 | 2554 | 779 | 1100 | 725 | 1577.11 | 0.018704 | 0.04278 | 516 | 18.0755 | 0.022179 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 8.8272 | 37.0366 | 68.319 | 51.16%
Bay Area | NB_North Bay | CALISTOGA 1101 | 9107 | CALISTOGA 110135588 | 1.433 | 60.8587 | 2.7117 | 1.7883 | 0.92348 | 2.6977 | 241 | 668 | 83 | 70 | 8 | 8 | 0 | 101 | 0.0051683 | 670 |  | 83 | 70 | 2 | 75 | 62 | 102.93 | 0.023546 | 0.00367 | 517 | 0.31037 | 0.022169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.1057 | 81.2141 | 30.6076 | 65.94%
Bay Area | NB_North Bay | CALISTOGA 1101 | 500 | CALISTOGA 110143924 | 5.6901 | 186.55 | 7.9661 | 3.8652 | 4.1011 | 7.7888 | 2295 | 3639 | 552 | 227 | 124 | 17 | 2 | 500 | 0.022253 | 3732 |  | 569 | 238 | 93 | 445 | 221 | 618.02 | 0.030502 | 0.02822 | 518 | 2.1672 | 0.022114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 1.1157 | 108.5065 | 71.4277 | 48.52%
North Valley | NV_North Valley | WILDWOOD 1101 | 6812 | WILDWOOD 11011454 | 2.9319 | 165.9465 | 7.5449 | 0 | 7.5449 | 0 | 211 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 1 | 395 |  | 73 | 49 | 395 | 73 | 49 | 135.56 | 0.017668 | 0.00268 | 519 | 0.74635 | 0.021951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.74635 | 9.6754 | 9.6754 | 0%
North Coast | HU_Humboldt | MIDDLETOWN 1101 | 1268 | MIDDLETOWN 11014646 | 12.8138 | 502.2364 | 19.3343 | 14.3356 | 4.9987 | 18.7943 | 3710 | 5444 | 1376 | 867 | 1063 | 659 | 1 | 796 | 0.027928 | 5632 |  | 1410 | 889 | 188 | 347 | 230 | 492.31 | 0.025513 | 0.01841 | 520 | 4.2902 | 0.021889 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 1.1092 | 69.4184 | 72.9275 | 74.15%
Bay Area | NB_North Bay | MONTICELLO 1101 | 2172 | MONTICELLO 11014360 | 5.5392 | 285.024 | 9.6369 | 0 | 9.6369 | 0 | 1036 | 0 | 0 | 0 | 0 | 0 | 0 | 169 | 1 | 1894 |  | 343 | 227 | 1894 | 343 | 227 | 640.37 | 0.019434 | 0.01386 | 521 | 0.85304 | 0.021873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 0.85304 | 35.5922 | 35.5922 | 0%
Central Coast | SJ_San Jose | HICKS 2101 | 2933 | HICKS 2101XR548 | 0.46706 | 39.2756 | 2.2652 | 0 | 2.2652 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 1 | 112 |  | 22 | 16 | 112 | 22 | 16 | 40.22 | 0.011892 | 0.00054 | 523 | 0.1966 | 0.021844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.1966 | 9.7124 | 9.7124 | 0%
Central Valley | ST_Stockton | OLETA 1101 | 3243 | OLETA 11011217 | 4.942 | 295.2811 | 14.5129 | 5.2508 | 9.2619 | 8.6742 | 490 | 485 | 167 | 109 | 126 | 83 | 0 | 235 | 0.40231 | 848 |  | 233 | 153 | 363 | 107 | 70 | 179.26 | 0.016736 | 0.00372 | 524 | 2.0261 | 0.021786 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 1.293 | 11.5527 | 16.0547 | 36.18%
North Coast | SO_Sonoma | MOLINO 1102 | 5067 | MOLINO 1102658 | 5.0372 | 232.4255 | 9.7102 | 0.65701 | 9.0532 | 7.2212 | 4328 | 606 | 428 | 94 | 127 | 1 | 0 | 385 | 0.25633 | 2624 |  | 792 | 334 | 2018 | 665 | 333 | 1092.67 | 0.021672 | 0.02997 | 525 | 3.1554 | 0.021613 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 2.9419 | 73.4545 | 81.5635 | 6.766%
North Coast | HU_Humboldt | MENDOCINO 1101 | 14 | MENDOCINO 110137462 | 2.348 | 144.6664 | 7.3746 | 0 | 7.3746 | 0 | 524 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 1 | 964 |  | 176 | 117 | 964 | 176 | 117 | 327.88 | 0.01623 | 0.00594 | 526 | 2.2035 | 0.021603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 2.2035 | 23.8656 | 23.8656 | 0%
Bay Area | NB_North Bay | BOLINAS 1101 | 9243 | BOLINAS 1101530 | 5.4354 | 227.4028 | 11.1152 | 0.44773 | 10.6674 | 1.622 | 1146 | 138 | 137 | 44 | 92 | 0 | 1 | 225 | 0.85408 | 1926 |  | 461 | 258 | 1788 | 369 | 258 | 666.45 | 0.023902 | 0.01834 | 527 | 2.4287 | 0.021493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 2.3309 | 34.5913 | 41.4749 | 4.028%
Sierra | SI_Sierra | HIGGINS 1103 | 837 | HIGGINS 1103circuit_breaker | 12.8681 | 698.3653 | 29.4911 | 0 | 29.4911 | 0 | 5796 | 0 | 0 | 0 | 0 | 0 | 0 | 718 | 1 | 10538 |  | 1902 | 1254 | 10538 | 1902 | 1254 | 3554.16 | 0.018426 | 0.07288 | 528 | 9.2424 | 0.021444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 9.2424 | 64.494 | 64.494 | 0%
North Coast | SO_Sonoma | GEYSERVILLE 1101 | 3302 | GEYSERVILLE 1101circuit_breaker | 1.5057 | 45.6667 | 2.0716 | 0 | 2.0716 | 0 | 355 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1 | 657 |  | 120 | 80 | 657 | 120 | 80 | 223.53 | 0.032971 | 0.00823 | 529 | 0.27838 | 0.021414 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.27838 | 57.9265 | 57.9265 | 0%
Central Valley | YO_Yosemite | OAKHURST 1102 | 5902 | OAKHURST 110210100 | 5.7424 | 235.0718 | 9.903 | 0.46534 | 9.4377 | 0.62064 | 1441 | 190 | 36 | 24 | 30 | 22 | 0 | 239 | 0.93733 | 2654 |  | 482 | 319 | 2464 | 452 | 297 | 841 | 0.024428 | 0.02296 | 530 | 2.6736 | 0.021389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 2.5479 | 47.8931 | 48.672 | 4.699%
North Valley | NV_North Valley | CHALLENGE 1102 | 3548 | CHALLENGE 11021902 | 2.498 | 101.2766 | 4.2672 | 0 | 4.2672 | 0 | 3228 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 1 | 5874 |  | 1061 | 700 | 5874 | 1061 | 700 | 1982.23 | 0.024665 | 0.05442 | 531 | 1.748 | 0.021317 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 1.748 | 248.6388 | 248.6388 | 0%
North Coast | HU_Humboldt | KONOCTI 1102 | 2908 | KONOCTI 110275382 | 14.017 | 588.0369 | 23.6159 | 15.9926 | 7.6233 | 23.614 | 5164 | 9541 | 2412 | 1297 | 1759 | 917 | 0 | 1093 | 8.0198e-05 | 9542 |  | 2412 | 1297 | 1 | 653 | 380 | 894.7 | 0.023837 | 0.03237 | 532 | 6.5197 | 0.021237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 2.1046 | 85.6585 | 102.1345 | 67.72%
Bay Area | DI_Diablo | CLAYTON 2212 | 1059 | CLAYTON 2212Y504R | 5.5949 | 277.5367 | 12.3439 | 10.3407 | 2.0032 | 12.3439 | 530 | 1625 | 623 | 281 | 511 | 210 | 0 | 523 | 0 | 1625 |  | 623 | 281 | 0 | 112 | 71 | 153.44 | 0.020159 | 0.00469 | 533 | 2.4403 | 0.02122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.39602 | 55.91 | 50.4701 | 83.77%
North Coast | SO_Sonoma | MOLINO 1104 | 1882 | MOLINO 1104380 | 2.0185 | 69.3743 | 3.011 | 0 | 3.011 | 0.47538 | 314 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0.84212 | 491 |  | 90 | 60 | 491 | 90 | 60 | 167.49 | 0.029095 | 0.00545 | 534 | 0.63424 | 0.021141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.63424 | 29.8906 | 29.8906 | 0%
North Coast | HU_Humboldt | CLEAR LAKE 1102 | 2263 | CLEAR LAKE 1102circuit_breaker | 0.43059 | 19.6584 | 1.7528 | 0 | 1.7528 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1 | 303 |  | 57 | 38 | 303 | 57 | 38 | 105.36 | 0.021904 | 0.0026 | 535 | 0.25352 | 0.021126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.25352 | 32.5186 | 32.5186 | 0%
Bay Area | NB_North Bay | PUEBLO 2102 | 4973 | PUEBLO 21021326 | 0.065496 | 6.4049 | 0.61799 | 0.20417 | 0.41383 | 0.61799 | 53 | 117 | 8 | 4 | 0 | 0 | 0 | 15 | 0 | 117 |  | 8 | 4 | 0 | 8 | 4 | 10.96 | 0.010226 | 0.00017 | 536 | 0.042172 | 0.021086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.02824 | 19.3318 | 12.9451 | 33.04%
North Coast | HU_Humboldt | UPPER LAKE 1101 | 4554 | UPPER LAKE 1101452 | 2.0108 | 90.3241 | 5.0532 | 2.5424 | 2.5108 | 5.0532 | 793 | 793 | 109 | 22 | 1 | 0 | 0 | 129 | 0 | 793 |  | 109 | 22 | 0 | 108 | 22 | 147.96 | 0.022262 | 0.005 | 537 | 0.98998 | 0.021063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.49189 | 43.0143 | 21.5704 | 50.31%
North Coast | SO_Sonoma | BELLEVUE 2103 | 3789 | BELLEVUE 2103478 | 4.6974 | 220.4522 | 8.5939 | 0 | 8.5939 | 0 | 511 | 0 | 0 | 0 | 0 | 0 | 0 | 286 | 1 | 940 |  | 172 | 114 | 940 | 172 | 114 | 320.24 | 0.021308 | 0.00762 | 538 | 1.5749 | 0.020998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 1.5749 | 20.0141 | 20.0141 | 0%
Central Valley | ST_Stockton | CORRAL 1102 | 6981 | CORRAL 110213498 | 0.47502 | 21.8492 | 0.92405 | 0 | 0.92405 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 41 |  | 9 | 7 | 41 | 9 | 7 | 16.02 | 0.021741 | 0.00041 | 539 | 0.271 | 0.020846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.271 | 9.7397 | 9.7397 | 0%
Sierra | SI_Sierra | PIKE CITY 1102 | 7725 | PIKE CITY 1102circuit_breaker | 3.8085 | 187.1223 | 9.4653 | 0 | 9.4653 | 0.70928 | 6322 | 711 | 711 | 711 | 0 | 0 | 0 | 300 | 0.92507 | 11343 |  | 2630 | 1976 | 10632 | 2630 | 1976 | 4559.98 | 0.020353 | 0.11131 | 540 | 2.1559 | 0.02073 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 2. >10 - 20% | 1. <= 10% | 2.1559 | 277.8558 | 277.8558 | 0%
North Coast | SO_Sonoma | FULTON 1102 | 3233 | FULTON 1102circuit_breaker | 0.098021 | 8.0438 | 0.45095 | 0.077652 | 0.3733 | 0.17008 | 121 | 129 | 20 | 1 | 0 | 0 | 1 | 19 | 0.62285 | 274 |  | 47 | 20 | 145 | 47 | 20 | 77.44 | 0.012186 | 0.00119 | 541 | 0.10338 | 0.020676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.085577 | 125.9056 | 104.2251 | 17.22%
Bay Area | NB_North Bay | LAS GALLINAS A 1105 | 9385 | LAS GALLINAS A 1105532 | 0.84054 | 90.3233 | 3.6146 | 0 | 3.6146 | 0 | 238 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1 | 444 |  | 82 | 55 | 444 | 82 | 55 | 152.3 | 0.009306 | 0.00159 | 542 | 0.78498 | 0.020657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.78498 | 22.6859 | 22.6859 | 0%
North Coast | SO_Sonoma | DUNBAR 1102 | 8799 | DUNBAR 1102694641 | 1.7732 | 84.3065 | 3.8527 | 0 | 3.8527 | 0 | 1111 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 1 | 2030 |  | 368 | 243 | 2030 | 368 | 243 | 686.86 | 0.021033 | 0.01609 | 543 | 1.2287 | 0.020479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 1.2287 | 95.5186 | 95.5186 | 0%
Central Valley | ST_Stockton | CORRAL 1103 | 997 | CORRAL 1103circuit_breaker | 1.5876 | 78.7518 | 5.2822 | 0 | 5.2822 | 0 | 117 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 1 | 225 |  | 43 | 29 | 225 | 43 | 29 | 79.16 | 0.020159 | 0.0018 | 544 | 0.63226 | 0.020396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.63226 | 8.1406 | 8.1406 | 0%
Bay Area | NB_North Bay | SILVERADO 2102 | 7324 | SILVERADO 2102808 | 0.71831 | 51.3417 | 1.7934 | 0.13977 | 1.6536 | 0.66061 | 207 | 46 | 1 | 1 | 0 | 0 | 0 | 46 | 0.63164 | 291 |  | 46 | 32 | 245 | 46 | 32 | 85.07 | 0.013991 | 0.00134 | 545 | 0.30549 | 0.020366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.28168 | 27.8181 | 25.65 | 7.794%
North Coast | SO_Sonoma | SONOMA 1107 | 1385 | SONOMA 1107126 | 1.6129 | 79.0368 | 4.5091 | 0 | 4.5091 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 1 | 83 |  | 17 | 12 | 83 | 17 | 12 | 30.76 | 0.020407 | 0.00072 | 546 | 0.36461 | 0.020256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.36461 | 3.7702 | 3.7702 | 0%
Central Valley | YO_Yosemite | COARSEGOLD 2104 | 9096 | COARSEGOLD 21046210 | 5.1856 | 253.1232 | 9.7182 | 6.8549 | 2.8633 | 9.0725 | 388 | 1052 | 245 | 230 | 177 | 166 | 0 | 208 | 0.066437 | 1100 |  | 254 | 236 | 48 | 77 | 70 | 109.81 | 0.020486 | 0.00328 | 547 | 2.045 | 0.020247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.60251 | 26.8924 | 26.1366 | 70.54%
Sierra | SI_Sierra | HORSESHOE 1101 | 3520 | HORSESHOE 1101circuit_breaker | 0.34119 | 14.5254 | 0.99375 | 0 | 0.99375 | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 1 | 216 |  | 41 | 28 | 216 | 41 | 28 | 75.61 | 0.023489 | 0.002 | 548 | 0.14153 | 0.020219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.14153 | 41.2579 | 41.2579 | 0%
North Valley | NV_North Valley | ANTLER 1101 | 6034 | ANTLER 11011378 | 9.5576 | 521.8001 | 24.2697 | 0 | 24.2697 | 0 | 8528 | 0 | 0 | 0 | 0 | 0 | 0 | 560 | 1 | 15499 |  | 2797 | 1843 | 15499 | 2797 | 1843 | 5226.8 | 0.018317 | 0.10653 | 549 | 6.5397 | 0.020184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2. >10 - 20% | 1. <= 10% | 6.5397 | 115.2466 | 115.2466 | 0%
North Valley | NV_North Valley | STILLWATER 1102 | 2644 | STILLWATER 11021466 | 11.5423 | 433.2124 | 19.8962 | 0 | 19.8962 | 0 | 2002 | 0 | 0 | 0 | 0 | 0 | 0 | 505 | 1 | 3648 |  | 660 | 436 | 3648 | 660 | 436 | 1232.52 | 0.026643 | 0.03657 | 550 | 4.9095 | 0.020039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 4.9095 | 33.1721 | 33.1721 | 0%
Bay Area | DI_Diablo | TASSAJARA 2104 | 810 | TASSAJARA 210419042 | 2.3628 | 123.5088 | 6.5379 | 0 | 6.5379 | 0 | 403 | 0 | 0 | 0 | 0 | 0 | 0 | 158 | 1 | 744 |  | 136 | 91 | 744 | 136 | 91 | 253.28 | 0.019131 | 0.00541 | 551 | 1.182 | 0.020034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 1.182 | 20.8019 | 20.8019 | 0%
Bay Area | NB_North Bay | SILVERADO 2102 | 3864 | SILVERADO 210234959 | 10.5073 | 666.5197 | 25.4598 | 3.3955 | 22.0644 | 14.8496 | 2242 | 1264 | 583 | 397 | 62 | 7 | 0 | 782 | 0.41674 | 2966 |  | 891 | 600 | 1702 | 829 | 593 | 1288.91 | 0.015764 | 0.02718 | 552 | 4.3034 | 0.020016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 3.7294 | 37.5718 | 34.9963 | 13.34%
North Valley | NV_North Valley | JESSUP 1101 | 7545 | JESSUP 11011993 | 2.006 | 98.2216 | 4.1716 | 0 | 4.1716 | 0 | 348 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 1 | 644 |  | 118 | 79 | 644 | 118 | 79 | 219.62 | 0.020423 | 0.00501 | 553 | 0.95999 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.95999 | 28.2866 | 28.2866 | 0%
Sierra | SI_Sierra | DEL MAR 2109 | 9434 | DEL MAR 210975802 | 1.0908 | 13.3615 | 0.40852 | 0 | 0.40852 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 30 |  | 7 | 6 | 30 | 7 | 6 | 12.29 | 0.081641 | 0.00119 | 554 | 0.039747 | 0.019873 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.039747 | 17.1349 | 17.1349 | 0%
North Valley | NV_North Valley | GIRVAN 1101 | 5926 | GIRVAN 11011330 | 15.5067 | 661.1165 | 30.511 | 0 | 30.511 | 0 | 4933 | 0 | 0 | 0 | 0 | 0 | 0 | 645 | 1 | 8970 |  | 1620 | 1068 | 8970 | 1620 | 1068 | 3026.7 | 0.023455 | 0.07901 | 555 | 7.308 | 0.019859 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 2. >10 - 20% | 1. <= 10% | 7.308 | 53.0956 | 53.0956 | 0%
North Coast | SO_Sonoma | GEYSERVILLE 1102 | 2330 | GEYSERVILLE 1102484 | 15.3103 | 863.7013 | 32.4288 | 15.8303 | 16.5987 | 25.6023 | 1939 | 864 | 406 | 209 | 104 | 19 | 7 | 841 | 0.21051 | 1608 |  | 541 | 298 | 744 | 437 | 279 | 665.65 | 0.017726 | 0.01611 | 556 | 4.312 | 0.01978 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 2.2071 | 26.3274 | 16.6827 | 48.82%
Central Valley | ST_Stockton | OLETA 1101 | 6042 | OLETA 11014768 | 4.3804 | 261.7861 | 11.7614 | 6.5498 | 5.2116 | 11.5716 | 506 | 690 | 217 | 133 | 109 | 60 | 0 | 180 | 0.016135 | 705 |  | 220 | 135 | 15 | 111 | 75 | 153.42 | 0.016733 | 0.00386 | 558 | 1.5211 | 0.019755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.67402 | 21.2988 | 18.7053 | 55.69%
North Valley | NV_North Valley | CORNING 1101 | 5246 | CORNING 110187304 | 1.2065 | 48.5291 | 3.121 | 2.8826 | 0.23864 | 3.121 | 31 | 61 | 12 | 7 | 9 | 4 | 0 | 70 | 0 | 61 |  | 12 | 7 | 0 | 3 | 3 | 4.11 | 0.024861 | 0.00016 | 559 | 0.23607 | 0.019672 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.01805 | 12.5714 | 3.8449 | 92.36%
Central Coast | LP_Los Padres | TEMPLETON 2111 | 1717 | TEMPLETON 2111circuit_breaker | 1.4526 | 62.7209 | 2.2797 | 0 | 2.2797 | 0 | 246 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 1 | 459 |  | 85 | 57 | 459 | 85 | 57 | 157.76 | 0.02316 | 0.00409 | 560 | 0.62824 | 0.019633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.62824 | 37.285 | 37.285 | 0%
Central Coast | SJ_San Jose | MORGAN HILL 2105 | 865 | MORGAN HILL 2105XR152 | 4.8587 | 222.0985 | 10.6445 | 0 | 10.6445 | 0 | 1178 | 0 | 0 | 0 | 0 | 0 | 0 | 232 | 1 | 2151 |  | 390 | 258 | 2151 | 390 | 258 | 727.89 | 0.021876 | 0.01774 | 561 | 2.1171 | 0.019603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 2.1171 | 36.6386 | 36.6386 | 0%
North Coast | HU_Humboldt | LAYTONVILLE 1102 | 4905 | LAYTONVILLE 1102circuit_breaker | 5.4076 | 211.226 | 11.2835 | 0 | 11.2835 | 0 | 3815 | 0 | 0 | 0 | 0 | 0 | 0 | 193 | 1 | 6940 |  | 1254 | 827 | 6940 | 1254 | 827 | 2342.58 | 0.025601 | 0.06676 | 562 | 2.2274 | 0.019538 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 2.2274 | 111.1355 | 111.1355 | 0%
Sierra | SI_Sierra | CLARKSVILLE 2104 | 1351 | CLARKSVILLE 210419772 | 8.8288 | 391.395 | 16.1015 | 15.1951 | 0.90663 | 16.1015 | 721 | 2773 | 1104 | 878 | 1100 | 876 | 0 | 759 | 0 | 2773 |  | 1104 | 878 | 0 | 4 | 2 | 5.48 | 0.022557 | 0.00019 | 563 | 3.3758 | 0.019513 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.19008 | 4.4119 | 68.565 | 94.37%
North Coast | HU_Humboldt | HOOPA 1101 | 5183 | HOOPA 11013174 | 6.9494 | 366.8829 | 17.9583 | 0 | 17.9583 | 0 | 7219 | 0 | 0 | 0 | 0 | 0 | 0 | 273 | 1 | 13122 |  | 2369 | 1561 | 13122 | 2369 | 1561 | 4426.51 | 0.018942 | 0.09331 | 564 | 5.1867 | 0.019499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 1. <= 10% | 5.1867 | 131.9165 | 131.9165 | 0%
North Coast | HU_Humboldt | CALPELLA 1101 | 2710 | CALPELLA 11011204 | 15.6128 | 776.66 | 31.5472 | 0 | 31.5472 | 0 | 3127 | 0 | 0 | 0 | 0 | 0 | 0 | 537 | 1 | 5691 |  | 1028 | 678 | 5691 | 1028 | 678 | 1920.55 | 0.020103 | 0.04297 | 565 | 6.2858 | 0.019401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 6.2858 | 32.5861 | 32.5861 | 0%
Bay Area | MI_Mission | VASCO 1102 | 383 | VASCO 1102MR176 | 9.4868 | 854.9609 | 35.3551 | 0 | 35.3551 | 0 | 443 | 0 | 0 | 0 | 0 | 0 | 0 | 509 | 1 | 817 |  | 149 | 99 | 817 | 149 | 99 | 277.66 | 0.011096 | 0.00344 | 566 | 2.9401 | 0.019343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 2.9401 | 4.2144 | 4.2144 | 0%
North Coast | SO_Sonoma | SONOMA 1105 | 1870 | SONOMA 1105404 | 2.3392 | 296.956 | 13.071 | 0 | 13.071 | 0 | 997 | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 1 | 1823 |  | 331 | 219 | 1823 | 331 | 219 | 617.54 | 0.0078774 | 0.00542 | 567 | 0.17367 | 0.019297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.17367 | 25.3232 | 25.3232 | 0%
North Coast | HU_Humboldt | LOW GAP 1101 | 4539 | LOW GAP 110137498 | 5.7538 | 326.6947 | 16.0015 | 0 | 16.0015 | 0 | 4223 | 0 | 0 | 0 | 0 | 0 | 0 | 317 | 1 | 7681 |  | 1387 | 915 | 7681 | 1387 | 915 | 2591.48 | 0.017612 | 0.0508 | 568 | 4.217 | 0.019256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 4.217 | 86.6793 | 86.6793 | 0%
Bay Area | NB_North Bay | TULUCAY 1101 | 6270 | TULUCAY 1101628 | 1.0782 | 39.9734 | 2.21 | 0 | 2.21 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1 | 110 |  | 22 | 15 | 110 | 22 | 15 | 40.04 | 0.026972 | 0.00123 | 569 | 0.1153 | 0.019216 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.1153 | 9.9546 | 9.9546 | 0%
Bay Area | NB_North Bay | SILVERADO 2102 | 1910 | SILVERADO 210298998 | 1.0423 | 58.4718 | 3.0394 | 0 | 3.0394 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 1 | 148 |  | 29 | 20 | 148 | 29 | 20 | 53.05 | 0.017825 | 0.00107 | 570 | 0.28731 | 0.019154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.28731 | 9.5414 | 9.5414 | 0%
North Valley | NV_North Valley | VOLTA 1102 | 1207 | VOLTA 110237350 | 11.7817 | 561.5634 | 22.2369 | 0 | 22.2369 | 0 | 5174 | 0 | 0 | 0 | 0 | 0 | 0 | 529 | 1 | 9408 |  | 1699 | 1120 | 9408 | 1699 | 1120 | 3174.35 | 0.02098 | 0.07412 | 571 | 6.3663 | 0.019118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 6.3663 | 76.4044 | 76.4044 | 0%
Central Valley | ST_Stockton | CLAY 1101 | 2295 | CLAY 110113442 | 12.7007 | 588.2141 | 25.1093 | 20.9642 | 4.1451 | 24.8706 | 1131 | 2632 | 239 | 138 | 174 | 101 | 0 | 464 | 0.0095039 | 2652 |  | 243 | 140 | 20 | 69 | 39 | 96.33 | 0.021592 | 0.0031 | 572 | 4.5666 | 0.019027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.75386 | 16.6463 | 9.6777 | 83.49%
Sierra | SI_Sierra | BROWNS VALLEY 1101 | 7629 | BROWNS VALLEY 110136622 | 1.8883 | 97.9571 | 5.7369 | 0 | 5.7369 | 0 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 1 | 548 |  | 101 | 67 | 548 | 101 | 67 | 187.69 | 0.019277 | 0.00405 | 573 | 0.66343 | 0.018955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.66343 | 17.6052 | 17.6052 | 0%
North Valley | NV_North Valley | CEDAR CREEK 1101 | 2436 | CEDAR CREEK 11011656 | 13.1451 | 696.3446 | 31.3055 | 0 | 31.3055 | 0 | 12096 | 0 | 0 | 0 | 0 | 0 | 0 | 659 | 1 | 21978 |  | 3966 | 2613 | 21978 | 3966 | 2613 | 7411.44 | 0.018877 | 0.15568 | 574 | 6.9273 | 0.018875 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 2. >10 - 20% | 1. <= 10% | 6.9273 | 126.687 | 126.687 | 0%
North Coast | SO_Sonoma | FULTON 1102 | 2491 | FULTON 1102287172 | 8.3343 | 497.4943 | 20.0466 | 0 | 20.0466 | 0.0017045 | 2492 | 115 | 28 | 27 | 24 | 24 | 0 | 352 | 0.99991 | 4652 |  | 848 | 568 | 4537 | 824 | 544 | 1537.21 | 0.016753 | 0.0287 | 575 | 4.4509 | 0.01886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 4.4509 | 41.1042 | 42.3015 | 0%
Sierra | SI_Sierra | WHEATLAND 1105 | 77 | WHEATLAND 110591170 | 5.515 | 255.0491 | 12.4419 | 0 | 12.4419 | 0 | 312 | 0 | 0 | 0 | 0 | 0 | 0 | 230 | 1 | 579 |  | 106 | 71 | 579 | 106 | 71 | 197.33 | 0.021623 | 0.00477 | 576 | 1.1314 | 0.018856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 1.1314 | 8.5196 | 8.5196 | 0%
North Coast | SO_Sonoma | FORT ROSS 1121 | 6074 | FORT ROSS 112170288 | 5.4133 | 280.0277 | 11.1778 | 0 | 11.1778 | 0 | 6108 | 0 | 0 | 0 | 0 | 0 | 0 | 211 | 1 | 11104 |  | 2005 | 1321 | 11104 | 2005 | 1321 | 3746.21 | 0.019331 | 0.0806 | 577 | 1.8394 | 0.01877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 1. <= 10% | 1.8394 | 179.3727 | 179.3727 | 0%
North Coast | HU_Humboldt | FORT SEWARD 1121 | 528 | FORT SEWARD 11211602 | 6.026 | 346.4293 | 17.9612 | 0 | 17.9612 | 0 | 6564 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 1 | 11932 |  | 2154 | 1420 | 11932 | 2154 | 1420 | 4024.86 | 0.017395 | 0.07791 | 578 | 4.5297 | 0.018718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 1. <= 10% | 4.5297 | 119.9253 | 119.9253 | 0%
North Coast | HU_Humboldt | MIDDLETOWN 1101 | 8265 | MIDDLETOWN 1101614 | 0.75789 | 14.9535 | 0.59186 | 0.1714 | 0.42045 | 0.35189 | 313 | 271 | 60 | 27 | 41 | 17 | 0 | 54 | 0.40544 | 506 |  | 103 | 56 | 235 | 62 | 39 | 106.09 | 0.050683 | 0.00653 | 579 | 0.46709 | 0.018684 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.33182 | 147.4595 | 174.0288 | 28.96%
Bay Area | MI_Mission | TASSAJARA 2113 | 6166 | TASSAJARA 2113MR276 | 1.147 | 82.6401 | 3.0648 | 0 | 3.0648 | 0 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 1 | 403 |  | 75 | 50 | 403 | 75 | 50 | 139.02 | 0.013879 | 0.00216 | 580 | 0.91393 | 0.018652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.91393 | 24.4716 | 24.4716 | 0%
North Valley | NV_North Valley | WYANDOTTE 1107 | 6039 | WYANDOTTE 110796390 | 3.6411 | 168.3079 | 7.1165 | 5.4676 | 1.6489 | 6.832 | 547 | 1324 | 438 | 383 | 373 | 328 | 0 | 315 | 0.039973 | 1364 |  | 445 | 388 | 40 | 72 | 60 | 102.24 | 0.021633 | 0.00324 | 581 | 2.047 | 0.018609 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.47427 | 43.6664 | 62.5309 | 76.83%
North Coast | HU_Humboldt | CARLOTTA 1121 | 3929 | CARLOTTA 1121circuit_breaker | 0.94166 | 54.3742 | 2.6653 | 0 | 2.6653 | 0 | 579 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 1 | 1064 |  | 194 | 129 | 1064 | 194 | 129 | 361.54 | 0.017318 | 0.00699 | 582 | 0.64987 | 0.018568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.64987 | 72.7862 | 72.7862 | 0%
Central Coast | LP_Los Padres | OILFIELDS 1103 | 8874 | OILFIELDS 1103N46 | 0.39252 | 118.023 | 4.8102 | 4.8102 | 0 | 4.8102 | 163 | 390 | 14 | 5 | 14 | 5 | 0 | 128 | 0 | 390 |  | 14 | 5 | 0 | 0 | 0 | 0 | 0.0033258 | 0 | 583 | 0.018527 | 0.018527 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0 | 0 | 2.9105 | 100%
Central Valley | KE_Kern | POSO MOUNTAIN 2101 | 8716 | POSO MOUNTAIN 21013990 | 0.29589 | 62.5289 | 3.9739 | 3.9739 | 0 | 3.9739 | 3 | 9 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.004732 | 0 | 584 | 0.055169 | 0.01839 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0 | 0 | 0 | 100%
North Valley | NV_North Valley | VOLTA 1101 | 2401 | VOLTA 110180454 | 15.6277 | 741.2365 | 32.1123 | 0 | 32.1123 | 0 | 5620 | 0 | 0 | 0 | 0 | 0 | 0 | 677 | 1 | 10218 |  | 1845 | 1216 | 10218 | 1845 | 1216 | 3447.27 | 0.021083 | 0.08089 | 585 | 0.25694 | 0.018353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 1. <= 10% | 0.25694 | 57.4546 | 57.4546 | 0%
North Coast | HU_Humboldt | REDBUD 1102 | 3229 | REDBUD 1102510 | 1.4244 | 56.0681 | 3.2928 | 0.79848 | 2.4945 | 2.4248 | 264 | 388 | 94 | 59 | 0 | 0 | 0 | 151 | 0.2636 | 518 |  | 118 | 75 | 130 | 118 | 75 | 173.36 | 0.025404 | 0.00623 | 586 | 0.8588 | 0.018272 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.65059 | 47.3039 | 35.8357 | 24.25%
North Coast | HU_Humboldt | UPPER LAKE 1101 | 6987 | UPPER LAKE 11011276 | 8.1991 | 344.8469 | 13.1072 | 5.2269 | 7.8803 | 12.686 | 1807 | 2970 | 469 | 254 | 8 | 8 | 0 | 394 | 0.032136 | 3076 |  | 488 | 267 | 106 | 480 | 259 | 667.14 | 0.023776 | 0.02373 | 587 | 3.5424 | 0.01826 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 2.1297 | 60.9114 | 37.2315 | 39.88%
North Coast | SO_Sonoma | GEYSERVILLE 1101 | 5777 | GEYSERVILLE 1101482 | 0.59842 | 14.8387 | 0.56761 | 0 | 0.56761 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 230 |  | 43 | 30 | 230 | 43 | 30 | 79.61 | 0.040329 | 0.00361 | 588 | 0.073031 | 0.018258 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.073031 | 75.7558 | 75.7558 | 0%
North Coast | HU_Humboldt | HOPLAND 1101 | 3084 | HOPLAND 1101768 | 6.1112 | 398.0694 | 18.9006 | 0 | 18.9006 | 0 | 842 | 0 | 0 | 0 | 0 | 0 | 0 | 289 | 1 | 1541 |  | 280 | 185 | 1541 | 280 | 185 | 522.29 | 0.015352 | 0.00894 | 589 | 2.4461 | 0.018254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 2.4461 | 14.8144 | 14.8144 | 0%
North Coast | HU_Humboldt | FORT SEWARD 1121 | 5197 | FORT SEWARD 11211663 | 0.23114 | 37.1767 | 1.679 | 0 | 1.679 | 0 | 259 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 1 | 483 |  | 89 | 60 | 483 | 89 | 60 | 165.4 | 0.0062174 | 0.00115 | 590 | 0.6191 | 0.018209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.6191 | 53.0085 | 53.0085 | 0%
North Valley | NV_North Valley | WYANDOTTE 1103 | 4569 | WYANDOTTE 11031504 | 3.41 | 223.6211 | 10.4227 | 0.54205 | 9.8807 | 0.75758 | 819 | 80 | 41 | 34 | 38 | 31 | 0 | 270 | 0.92732 | 1471 |  | 294 | 201 | 1391 | 256 | 170 | 475.91 | 0.015249 | 0.00812 | 591 | 2.5217 | 0.018142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 2.3906 | 25.9091 | 28.2076 | 5.201%
Sierra | SI_Sierra | BANGOR 1101 | 7733 | BANGOR 1101circuit_breaker | 10.348 | 419.8749 | 18.3814 | 14.3438 | 4.0377 | 17.5559 | 985 | 2332 | 680 | 618 | 570 | 512 | 0 | 524 | 0.044913 | 2413 |  | 695 | 628 | 81 | 125 | 116 | 178.54 | 0.024645 | 0.00641 | 592 | 2.7495 | 0.018089 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.60395 | 30.9583 | 37.8099 | 78.03%
Bay Area | NB_North Bay | MONTICELLO 1101 | 7722 | MONTICELLO 1101718 | 9.0388 | 595.672 | 25.0801 | 0 | 25.0801 | 0 | 2481 | 0 | 0 | 0 | 0 | 0 | 0 | 472 | 1 | 4518 |  | 817 | 539 | 4518 | 817 | 539 | 1525.91 | 0.015174 | 0.02578 | 593 | 2.4388 | 0.018065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 2.4388 | 32.5756 | 32.5756 | 0%
Central Valley | YO_Yosemite | BEAR VALLEY 2101 | 3694 | BEAR VALLEY 21014500 | 11.7834 | 521.0096 | 22.7019 | 17.2358 | 5.4661 | 22.6867 | 334 | 1070 | 145 | 118 | 127 | 106 | 0 | 573 | 0.00066741 | 1070 |  | 145 | 118 | 0 | 18 | 12 | 24.66 | 0.022616 | 0.00085 | 594 | 1.9992 | 0.018011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.48136 | 3.293 | 6.3871 | 75.92%
North Coast | SO_Sonoma | FITCH MOUNTAIN 1113 | 21 | FITCH MOUNTAIN 1113154 | 0.63237 | 53.529 | 3.0697 | 1.8911 | 1.1786 | 3.0693 | 163 | 424 | 147 | 11 | 146 | 11 | 0 | 100 | 0.0001234 | 424 |  | 147 | 11 | 0 | 1 | 0 | 1.37 | 0.011814 | 2e-05 | 595 | 0.50412 | 0.018004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.19356 | 0.84847 | 47.8875 | 61.61%
Bay Area | MI_Mission | SUNOL 1101 | 8766 | SUNOL 11018721 | 0.78215 | 62.5584 | 2.6631 | 1.9131 | 0.74981 | 2.2525 | 89 | 121 | 3 | 1 | 0 | 0 | 0 | 79 | 0.15419 | 148 |  | 8 | 5 | 27 | 8 | 5 | 13.39 | 0.012503 | 0.00021 | 596 | 0.52124 | 0.017974 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.14676 | 10.6694 | 3.0041 | 71.84%
Bay Area | NB_North Bay | SILVERADO 2104 | 4993 | SILVERADO 2104722 | 3.0384 | 147.3878 | 5.9235 | 4.2513 | 1.6722 | 5.9235 | 890 | 2347 | 792 | 439 | 604 | 307 | 2 | 360 | 0 | 2347 |  | 792 | 439 | 0 | 188 | 132 | 257.56 | 0.020615 | 0.00806 | 597 | 0.66491 | 0.017971 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.1877 | 112.4295 | 133.7051 | 71.77%
Sierra | SI_Sierra | NARROWS 2105 | 4162 | NARROWS 2105circuit_breaker | 14.1006 | 879.058 | 35.2227 | 0.9142 | 34.3085 | 0.94697 | 3004 | 230 | 140 | 123 | 138 | 122 | 0 | 812 | 0.97311 | 5550 |  | 1101 | 757 | 5320 | 963 | 635 | 1798.11 | 0.016041 | 0.03212 | 598 | 4.0559 | 0.017946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 3.9506 | 28.0688 | 31.2582 | 2.595%
North Coast | SO_Sonoma | CLOVERDALE 1102 | 7235 | CLOVERDALE 1102262 | 0.83658 | 39.4108 | 1.2023 | 0.1483 | 1.0542 | 1.193 | 145 | 60 | 60 | 15 | 44 | 9 | 0 | 65 | 0.007719 | 62 |  | 60 | 15 | 2 | 16 | 6 | 22.1 | 0.021227 | 0.00071 | 599 | 0.19731 | 0.017937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.17301 | 15.1779 | 49.9055 | 12.33%
Central Valley | YO_Yosemite | SAN JOAQUIN NO3 1103 | 2260 | SAN JOAQUIN #3 1103circuit_breaker | 13.2711 | 637.7853 | 28.5731 | 0 | 28.5731 | 0 | 3182 | 1 | 0 | 0 | 0 | 0 | 0 | 578 | 1 | 5792 |  | 1046 | 690 | 5791 | 1046 | 690 | 1954.21 | 0.020808 | 0.04526 | 600 | 6.6069 | 0.017905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2. >10 - 20% | 2. >10 - 20% | 6.6069 | 36.6079 | 36.6079 | 0%
Central Coast | LP_Los Padres | SANTA YNEZ 1101 | 5408 | SANTA YNEZ 1101Y52 | 13.2833 | 437.1351 | 22.7866 | 0 | 22.7866 | 0 | 355 | 0 | 0 | 0 | 0 | 0 | 0 | 315 | 1 | 657 |  | 120 | 80 | 657 | 120 | 80 | 223.53 | 0.030387 | 0.00758 | 601 | 1.6408 | 0.017835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 1.6408 | 5.2663 | 5.2663 | 0%
Sierra | SI_Sierra | GRASS VALLEY 1103 | 1069 | GRASS VALLEY 11032180 | 19.3081 | 1067.4854 | 43.6527 | 0 | 43.6527 | 0 | 6530 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 1 | 11871 |  | 2143 | 1412 | 11871 | 2143 | 1412 | 4004.3 | 0.018087 | 0.0806 | 602 | 10.5904 | 0.017739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 1. <= 10% | 10.5904 | 49.0921 | 49.0921 | 0%
Bay Area | DI_Diablo | WILLOW PASS 1101 | 4383 | TIDEWATER 210657926 | 1.4e-05 | 1.4744 | 0.78902 | 0 | 0.78902 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 14 |  | 5 | 4 | 14 | 5 | 4 | 8.11 | 9.4956e-06 | 0 | 603 | 0.017735 | 0.017735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.017735 | 6.337 | 6.337 | 0%
North Coast | HU_Humboldt | HIGHLANDS 1102 | 1080 | HIGHLANDS 110275140 | 5.0523 | 116.4779 | 7.0917 | 6.396 | 0.69564 | 7.0917 | 160 | 550 | 70 | 34 | 41 | 15 | 0 | 280 | 0 | 550 |  | 70 | 34 | 0 | 29 | 19 | 39.73 | 0.043375 | 0.00262 | 604 | 1.485 | 0.017678 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.14567 | 41.688 | 9.8707 | 90.19%
North Coast | HU_Humboldt | KONOCTI 1102 | 1818 | KONOCTI 1102circuit_breaker | 13.7631 | 855.2281 | 34.3277 | 19.4945 | 14.8333 | 33.8777 | 11791 | 28577 | 5864 | 3792 | 3371 | 2107 | 0 | 1456 | 0.013109 | 28858 |  | 5915 | 3825 | 281 | 2544 | 1718 | 3510.57 | 0.016093 | 0.08513 | 605 | 7.5478 | 0.017676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2. >10 - 20% | 1. <= 10% | 3.2615 | 171.5056 | 172.3101 | 56.79%
Bay Area | NB_North Bay | NAPA 1112 | 7857 | NAPA 11121723 | 4.5801 | 275.5387 | 10.0972 | 0 | 10.0972 | 0 | 672 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 1 | 1233 |  | 224 | 149 | 1233 | 224 | 149 | 417.85 | 0.016622 | 0.00774 | 606 | 1.7554 | 0.017554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 1.7554 | 22.1845 | 22.1845 | 0%
Central Valley | FR_Fresno | TIVY VALLEY 1107 | 7027 | TIVY VALLEY 11077380 | 10.6048 | 281.5459 | 13.7021 | 7.7278 | 5.9742 | 13.6131 | 206 | 1103 | 311 | 246 | 69 | 63 | 0 | 251 | 0.0064965 | 1106 |  | 311 | 246 | 3 | 242 | 183 | 331.81 | 0.037666 | 0.01895 | 607 | 0.31585 | 0.017547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 0.13771 | 40.5072 | 22.6973 | 56.4%
North Coast | HU_Humboldt | CALPINE 1146 | 9383 | CALPINE 1146400 | 1.1467 | 65.1142 | 3.0269 | 0 | 3.0269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.01761 | 0.00015 | 608 | 0.052574 | 0.017525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.052574 | 1.3215 | 1.3215 | 0%
Central Coast | LP_Los Padres | ATASCADERO 1103 | 813 | ATASCADERO 1103A18 | 2.4053 | 132.5985 | 7.3066 | 0 | 7.3066 | 0 | 312 | 0 | 0 | 0 | 0 | 0 | 0 | 227 | 1 | 579 |  | 106 | 71 | 579 | 106 | 71 | 197.33 | 0.01814 | 0.004 | 609 | 1.437 | 0.017525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 1.437 | 14.5074 | 14.5074 | 0%
Sierra | SI_Sierra | MOUNTAIN QUARRIES 2101 | 7078 | MOUNTAIN QUARRIES 210151584 | 9.7712 | 530.6351 | 21.3121 | 0 | 21.3121 | 0 | 2462 | 0 | 0 | 0 | 0 | 0 | 0 | 435 | 1 | 4483 |  | 811 | 535 | 4483 | 811 | 535 | 1514.54 | 0.018414 | 0.03105 | 610 | 5.0571 | 0.017438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 3. >20 - 30% | 5.0571 | 38.0535 | 38.0535 | 0%
North Coast | SO_Sonoma | MONTE RIO 1112 | 710 | MONTE RIO 11125040 | 0.26076 | 32.53 | 1.4261 | 0 | 1.4261 | 0 | 1140 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | 1 | 2082 |  | 378 | 250 | 2082 | 378 | 250 | 705.24 | 0.008016 | 0.0063 | 611 | 1.1664 | 0.017409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 1.1664 | 265.0518 | 265.0518 | 0%
Bay Area | NB_North Bay | GREENBRAE 1103 | 552 | GREENBRAE 11031260 | 0.99121 | 57.8797 | 2.8341 | 0 | 2.8341 | 0 | 1243 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 1 | 2270 |  | 411 | 272 | 2270 | 411 | 272 | 767.37 | 0.017125 | 0.01464 | 612 | 0.66139 | 0.017405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 4. >30 - 40% | 0.66139 | 145.02 | 145.02 | 0%
North Coast | HU_Humboldt | BRIDGEVILLE 1101 | 9239 | BRIDGEVILLE 1101circuit_breaker | 3.2424 | 207.8426 | 8.5233 | 7.7994 | 0.72386 | 8.414 | 2746 | 6246 | 907 | 501 | 842 | 474 | 0 | 222 | 0.012821 | 6310 |  | 919 | 509 | 64 | 77 | 35 | 111.25 | 0.0156 | 0.0025 | 613 | 1.721 | 0.017383 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.14616 | 106.3736 | 107.8221 | 91.51%
North Valley | NV_North Valley | RAWSON 1103 | 4192 | RAWSON 110385334 | 1.2944 | 56.4595 | 4.4674 | 0 | 4.4674 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 1 | 47 |  | 10 | 8 | 47 | 10 | 8 | 17.93 | 0.022926 | 0.00048 | 614 | 0.10414 | 0.017356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 6. >50% | 0.10414 | 2.2384 | 2.2384 | 0%
Sierra | SI_Sierra | HIGGINS 1109 | 9095 | HIGGINS 11097863 | 0.95046 | 77.9609 | 2.8254 | 0 | 2.8254 | 0 | 531 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 1 | 977 |  | 178 | 118 | 977 | 178 | 118 | 331.79 | 0.012192 | 0.00451 | 615 | 0.97068 | 0.017334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2. >10 - 20% | 5. >40 - 50% | 0.97068 | 63.0004 | 63.0004 | 0%
Sierra | SI_Sierra | SHINGLE SPRINGS 2109 | 4587 | SHINGLE SPRINGS 210985766 | 5.146 | 340.4491 | 16.3534 | 0 | 16.3534 | 0 | 1374 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 1 | 2507 |  | 454 | 300 | 2507 | 454 | 300 | 847.61 | 0.015115 | 0.01427 | 616 | 3.557 | 0.017267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 3.557 | 27.7618 | 27.7618 | 0%
North Coast | HU_Humboldt | LAYTONVILLE 1102 | 8471 | LAYTONVILLE 11022502 | 6.3689 | 382.6381 | 17.4871 | 0 | 17.4871 | 0 | 2779 | 0 | 0 | 0 | 0 | 0 | 0 | 204 | 1 | 5059 |  | 914 | 603 | 5059 | 914 | 603 | 1707.49 | 0.016645 | 0.03163 | 617 | 3.3788 | 0.017151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 3.3788 | 52.267 | 52.267 | 0%
North Coast | HU_Humboldt | GARBERVILLE 1102 | 2077 | GARBERVILLE 1102circuit_breaker | 3.5356 | 208.1031 | 10.3191 | 0 | 10.3191 | 0 | 3278 | 0 | 0 | 0 | 0 | 0 | 0 | 421 | 1 | 5965 |  | 1078 | 711 | 5965 | 1078 | 711 | 2013.71 | 0.01699 | 0.03808 | 618 | 2.7161 | 0.017082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 2.7161 | 104.4662 | 104.4662 | 0%
North Coast | HU_Humboldt | FRUITLAND 1141 | 4267 | FRUITLAND 114195324 | 2.8421 | 190.2621 | 9.4777 | 0 | 9.4777 | 0 | 7001 | 0 | 0 | 0 | 0 | 0 | 0 | 354 | 1 | 12726 |  | 2297 | 1514 | 12726 | 2297 | 1514 | 4292.23 | 0.014938 | 0.07135 | 619 | 2.3645 | 0.017011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 2.3645 | 242.3596 | 242.3596 | 0%
Bay Area | MI_Mission | VINEYARD 2110 | 7776 | VINEYARD 2110circuit_breaker | 2.4862 | 121.4647 | 6.8953 | 0 | 6.8953 | 0 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 1 | 228 |  | 43 | 29 | 228 | 43 | 29 | 79.43 | 0.020468 | 0.00183 | 620 | 0.35687 | 0.016994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.35687 | 6.2362 | 6.2362 | 0%
Sierra | SA_Sacramento | MADISON 2101 | 214 | MADISON 21017702 | 0.17539 | 13.0084 | 0.84583 | 0 | 0.84583 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 23 |  | 6 | 5 | 23 | 6 | 5 | 10.29 | 0.013483 | 0.00017 | 621 | 0.067763 | 0.016941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.067763 | 7.0936 | 7.0936 | 0%
North Valley | NV_North Valley | WYANDOTTE 1107 | 6989 | WYANDOTTE 110738438 | 6.2898 | 399.4181 | 16.8464 | 9.5691 | 7.2773 | 16.3025 | 2497 | 6462 | 2227 | 1912 | 1962 | 1678 | 0 | 624 | 0.032288 | 6609 |  | 2254 | 1930 | 147 | 292 | 252 | 413.27 | 0.015747 | 0.00956 | 622 | 3.3846 | 0.016839 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 1.4621 | 40.1249 | 133.7971 | 56.8%
Bay Area | NB_North Bay | WOODACRE 1101 | 8331 | WOODACRE 110191900 | 2.2392 | 218.4325 | 8.3691 | 7.3445 | 1.0246 | 8.3691 | 711 | 1769 | 594 | 202 | 501 | 155 | 0 | 242 | 0 | 1769 |  | 594 | 202 | 0 | 93 | 47 | 127.41 | 0.010251 | 0.00198 | 623 | 0.94168 | 0.016816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.11529 | 90.7652 | 70.9751 | 87.76%
North Coast | HU_Humboldt | FRUITLAND 1142 | 7384 | FRUITLAND 11422006 | 2.1329 | 174.223 | 8.2451 | 0 | 8.2451 | 0 | 2929 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 1 | 5331 |  | 963 | 636 | 5331 | 963 | 636 | 1799.1 | 0.012242 | 0.02451 | 624 | 0.21784 | 0.016757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 0.21784 | 116.797 | 116.797 | 0%
Bay Area | PE_Peninsula | WOODSIDE 1101 | 5540 | WOODSIDE 11018974 | 5.2826 | 336.5601 | 14.4956 | 3.2481 | 11.2475 | 9.8117 | 10700 | 11695 | 4790 | 2783 | 1892 | 943 | 0 | 887 | 0.32312 | 17978 |  | 5924 | 3530 | 6283 | 4032 | 2587 | 6089.31 | 0.015696 | 0.1316 | 625 | 3.4676 | 0.016752 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3. >20 - 30% | 1. <= 10% | 2.6906 | 358.4785 | 408.6745 | 22.41%
North Valley | NV_North Valley | ANTLER 1101 | 8289 | ANTLER 11011376 | 3.584 | 191.444 | 8.6093 | 0 | 8.6093 | 0 | 4113 | 0 | 0 | 0 | 0 | 0 | 0 | 211 | 1 | 7481 |  | 1351 | 891 | 7481 | 1351 | 891 | 2524.16 | 0.018721 | 0.05259 | 626 | 2.1695 | 0.016688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 2.1695 | 156.9237 | 156.9237 | 0%
Central Valley | ST_Stockton | MARTELL 1103 | 3099 | MARTELL 110368192 | 0.825 | 51.3569 | 2.757 | 0 | 2.757 | 0 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 1 | 170 |  | 33 | 22 | 170 | 33 | 22 | 60.51 | 0.016064 | 0.0011 | 627 | 0.3836 | 0.016678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.3836 | 11.9695 | 11.9695 | 0%
North Valley | NV_North Valley | KANAKA 1101 | 3794 | KANAKA 110165606 | 4.9852 | 319.502 | 13.3752 | 0 | 13.3752 | 0 | 10030 | 0 | 0 | 0 | 0 | 0 | 0 | 326 | 1 | 18226 |  | 3289 | 2168 | 18226 | 3289 | 2168 | 6146.27 | 0.015603 | 0.10671 | 628 | 3.5245 | 0.016625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3. >20 - 30% | 1. <= 10% | 3.5245 | 245.9031 | 245.9031 | 0%
North Coast | SO_Sonoma | PETALUMA C 1109 | 1108 | PETALUMA C 1109128 | 26.2609 | 848.0368 | 35.3061 | 0 | 35.3061 | 0 | 966 | 0 | 0 | 0 | 0 | 0 | 0 | 635 | 1 | 1766 |  | 321 | 212 | 1766 | 321 | 212 | 598.71 | 0.030967 | 0.02067 | 629 | 0.066191 | 0.016548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 0.066191 | 9.0919 | 9.0919 | 0%
North Coast | SO_Sonoma | LAKEVILLE 1102 | 704 | LAKEVILLE 1102280 | 0.72163 | 54.0463 | 2.6422 | 2.5011 | 0.1411 | 2.6422 | 18 | 42 | 16 | 11 | 13 | 11 | 0 | 53 | 0 | 42 |  | 16 | 11 | 0 | 3 | 0 | 4.11 | 0.013352 | 8e-05 | 630 | 0.1157 | 0.016529 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.0061787 | 21.2617 | 6.0555 | 94.66%
North Valley | NV_North Valley | JESSUP 1101 | 6602 | JESSUP 11019752 | 1.7483 | 108.5661 | 4.1741 | 0 | 4.1741 | 0 | 376 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 1 | 695 |  | 127 | 85 | 695 | 127 | 85 | 236.54 | 0.016104 | 0.00425 | 631 | 0.95594 | 0.016482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.95594 | 30.4261 | 30.4261 | 0%
Bay Area | NB_North Bay | WOODACRE 1101 | 456 | WOODACRE 110196844 | 2.9673 | 171.0688 | 5.6218 | 3.6831 | 1.9386 | 5.6218 | 1902 | 3468 | 914 | 185 | 747 | 126 | 0 | 283 | 0 | 3468 |  | 914 | 185 | 0 | 167 | 59 | 228.79 | 0.017346 | 0.00602 | 632 | 1.3671 | 0.016471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.47143 | 86.143 | 162.5819 | 65.52%
North Coast | SO_Sonoma | GEYSERVILLE 1102 | 271 | GEYSERVILLE 1102350 | 1.9769 | 110.129 | 5.34 | 0.71913 | 4.621 | 3.3956 | 501 | 301 | 190 | 135 | 43 | 2 | 0 | 143 | 0.36411 | 637 |  | 251 | 176 | 336 | 208 | 174 | 315.2 | 0.01795 | 0.00776 | 634 | 0.81998 | 0.0164 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.70958 | 45.0117 | 47.0041 | 13.47%
Bay Area | NB_North Bay | ALTO 1124 | 703 | ALTO 1124430 | 2.0966 | 122.3995 | 6.5256 | 0 | 6.5256 | 0 | 2540 | 0 | 0 | 0 | 0 | 0 | 0 | 243 | 1 | 4625 |  | 836 | 552 | 4625 | 836 | 552 | 1561.57 | 0.017129 | 0.02978 | 635 | 1.9653 | 0.016377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 1.9653 | 128.1114 | 128.1114 | 0%
Sierra | SI_Sierra | BROWNS VALLEY 1101 | 8932 | BROWNS VALLEY 1101circuit_breaker | 0.11557 | 7.3894 | 0.67746 | 0 | 0.67746 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 16 |  | 5 | 4 | 16 | 5 | 4 | 8.29 | 0.01564 | 0.00016 | 636 | 0.049117 | 0.016372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.049117 | 7.3805 | 7.3805 | 0%
North Coast | HU_Humboldt | LAYTONVILLE 1102 | 1536 | LAYTONVILLE 110264908 | 1.3123 | 66.3128 | 2.6566 | 0.32576 | 2.3309 | 0.55076 | 783 | 255 | 80 | 61 | 73 | 57 | 0 | 68 | 0.79269 | 1392 |  | 287 | 198 | 1137 | 214 | 141 | 395.51 | 0.01979 | 0.00881 | 637 | 0.73565 | 0.016348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.64544 | 91.8112 | 108.0317 | 12.26%
Sierra | SI_Sierra | DIAMOND SPRINGS 1106 | 1830 | DIAMOND SPRINGS 110610587 | 9.8035 | 542.571 | 22.3244 | 0.38712 | 21.9373 | 0.38712 | 4459 | 3 | 0 | 0 | 0 | 0 | 0 | 759 | 0.98266 | 7972 |  | 1439 | 949 | 7969 | 1439 | 949 | 2688.64 | 0.018069 | 0.05407 | 638 | 4.9763 | 0.016209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 4.89 | 65.596 | 64.4585 | 1.734%
Central Valley | KE_Kern | POSO MOUNTAIN 2101 | 5982 | POSO MOUNTAIN 21012181 | 3.8282 | 313.2026 | 16.0443 | 16.0443 | 0 | 16.0443 | 11 | 31 | 8 | 8 | 8 | 8 | 0 | 224 | 0 | 31 |  | 8 | 8 | 0 | 0 | 0 | 0 | 0.012223 | 0 | 639 | 0.11309 | 0.016156 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0 | 0 | 0.49862 | 100%
North Coast | HU_Humboldt | WILLITS 1103 | 6027 | WILLITS 1103964 | 1.5493 | 69.9454 | 3.3169 | 0 | 3.3169 | 0 | 211 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 1 | 395 |  | 73 | 49 | 395 | 73 | 49 | 135.56 | 0.02215 | 0.00336 | 640 | 0.41889 | 0.016111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.41889 | 22.0088 | 22.0088 | 0%
Sierra | SI_Sierra | SHINGLE SPRINGS 2109 | 4636 | SHINGLE SPRINGS 210961892 | 12.3309 | 747.9239 | 28.5763 | 0.31004 | 28.2663 | 0.31004 | 3069 | 76 | 36 | 31 | 36 | 31 | 0 | 628 | 0.98915 | 5601 |  | 1034 | 690 | 5525 | 998 | 659 | 1864.51 | 0.016487 | 0.03421 | 641 | 6.2666 | 0.01611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 6.1986 | 35.3071 | 36.1838 | 1.085%
North Coast | SO_Sonoma | MOLINO 1102 | 1291 | MOLINO 1102178 | 4.4215 | 296.4949 | 10.932 | 1.325 | 9.607 | 7.9837 | 4260 | 602 | 413 | 167 | 78 | 0 | 1 | 592 | 0.26969 | 2692 |  | 790 | 416 | 2090 | 712 | 416 | 1163.54 | 0.014913 | 0.02208 | 642 | 2.8607 | 0.015982 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 2.514 | 74.1126 | 72.2649 | 12.12%
North Coast | HU_Humboldt | GARBERVILLE 1102 | 8325 | GARBERVILLE 11028189 | 0.56804 | 36.7279 | 1.8542 | 0 | 1.8542 | 0 | 710 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 1 | 1302 |  | 237 | 157 | 1302 | 237 | 157 | 441.87 | 0.015466 | 0.00762 | 643 | 0.25477 | 0.015923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.25477 | 127.8202 | 127.8202 | 0%
Sierra | SI_Sierra | MOUNTAIN QUARRIES 2101 | 304 | MOUNTAIN QUARRIES 21011350 | 7.9403 | 442.7158 | 18.4369 | 0 | 18.4369 | 0 | 1737 | 0 | 0 | 0 | 0 | 0 | 0 | 382 | 1 | 3167 |  | 573 | 378 | 3167 | 573 | 378 | 1070.04 | 0.017935 | 0.02137 | 645 | 3.9709 | 0.015884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 3.9709 | 31.0789 | 31.0789 | 0%
Bay Area | NB_North Bay | PUEBLO 1104 | 5431 | PUEBLO 11041304 | 8.181 | 454.9686 | 18.7557 | 0 | 18.7557 | 0 | 827 | 0 | 0 | 0 | 0 | 0 | 0 | 381 | 1 | 1514 |  | 275 | 182 | 1514 | 275 | 182 | 513.01 | 0.017981 | 0.01028 | 646 | 2.7671 | 0.015812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 2.7671 | 14.6622 | 14.6622 | 0%
North Coast | HU_Humboldt | GARBERVILLE 1101 | 7091 | GARBERVILLE 11011770 | 2.4676 | 185.1198 | 8.0227 | 0 | 8.0227 | 0 | 4418 | 0 | 0 | 0 | 0 | 0 | 0 | 133 | 1 | 8035 |  | 1451 | 957 | 8035 | 1451 | 957 | 2711.02 | 0.01333 | 0.04022 | 647 | 2.1661 | 0.015811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 2.1661 | 180.8612 | 180.8612 | 0%
Bay Area | NB_North Bay | SILVERADO 2102 | 3635 | SILVERADO 2102636 | 0.98703 | 58.4203 | 2.1771 | 0.062689 | 2.1146 | 2.0002 | 710 | 499 | 280 | 215 | 61 | 19 | 0 | 129 | 0.081253 | 605 |  | 299 | 228 | 106 | 238 | 209 | 335.6 | 0.016895 | 0.00836 | 648 | 0.94825 | 0.015804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.92103 | 112.5517 | 137.3397 | 2.88%
North Coast | SO_Sonoma | MOLINO 1102 | 4875 | MOLINO 110241392 | 2.7795 | 87.365 | 4.2472 | 0.06553 | 4.1818 | 0.19432 | 1032 | 8 | 8 | 2 | 0 | 0 | 0 | 155 | 0.95425 | 1808 |  | 335 | 218 | 1800 | 335 | 218 | 620.95 | 0.031815 | 0.02216 | 649 | 1.0103 | 0.015786 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 0.99479 | 80.1087 | 78.8763 | 1.543%
North Coast | SO_Sonoma | FULTON 1102 | 1326 | FULTON 11024522 | 3.1187 | 197.0121 | 7.846 | 0 | 7.846 | 0 | 771 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 1 | 1412 |  | 257 | 170 | 1412 | 257 | 170 | 479.17 | 0.01583 | 0.00846 | 650 | 1.86 | 0.015762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 1.86 | 32.7554 | 32.7554 | 0%
North Coast | SO_Sonoma | DUNBAR 1101 | 6036 | DUNBAR 1101416 | 1.0621 | 57.7838 | 2.5373 | 0.23712 | 2.3002 | 2.1455 | 1103 | 146 | 135 | 80 | 65 | 41 | 0 | 80 | 0.15444 | 457 |  | 191 | 117 | 311 | 126 | 76 | 200.61 | 0.01838 | 0.00482 | 651 | 0.61367 | 0.015735 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.55632 | 54.7781 | 75.2766 | 9.345%
North Coast | SO_Sonoma | DUNBAR 1103 | 8696 | DUNBAR 11033135 | 0.15218 | 12.369 | 0.3483 | 0.021591 | 0.3267 | 0.3483 | 37 | 14 | 14 | 9 | 2 | 1 | 0 | 37 | 0 | 14 |  | 14 | 9 | 0 | 12 | 8 | 16.44 | 0.012303 | 0.00031 | 652 | 0.031434 | 0.015717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.029485 | 36.7304 | 40.1958 | 6.199%
North Valley | NV_North Valley | SYCAMORE CREEK 1111 | 6718 | SYCAMORE CREEK 1111circuit_breaker | 5.866 | 206.2213 | 10.4381 | 7.7411 | 2.6972 | 10.2983 | 596 | 1166 | 148 | 125 | 104 | 82 | 0 | 230 | 0.013391 | 1181 |  | 151 | 127 | 15 | 47 | 45 | 65.74 | 0.028445 | 0.00278 | 653 | 1.21 | 0.015714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.31266 | 17.4257 | 14.4663 | 74.16%
North Valley | NV_North Valley | WYANDOTTE 1103 | 5071 | WYANDOTTE 110313018 | 0.13392 | 9.5577 | 1.2392 | 0 | 1.2392 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 1 | 78 |  | 16 | 11 | 78 | 16 | 11 | 28.94 | 0.014012 | 0.00047 | 654 | 0.062831 | 0.015708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.062831 | 12.9115 | 12.9115 | 0%
North Coast | HU_Humboldt | UKIAH 1113 | 1907 | UKIAH 1113circuit_breaker | 2.956 | 194.9735 | 7.6277 | 0 | 7.6277 | 0 | 1376 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 1 | 2511 |  | 455 | 301 | 2511 | 455 | 301 | 849.34 | 0.015161 | 0.01434 | 655 | 1.6263 | 0.015638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 1.6263 | 59.6514 | 59.6514 | 0%
Central Valley | ST_Stockton | CALAVERAS CEMENT 1101 | 3958 | CALAVERAS CEMENT 110113424 | 0.60913 | 59.8693 | 1.3275 | 0 | 1.3275 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 1 | 67 |  | 14 | 10 | 67 | 14 | 10 | 25.21 | 0.010174 | 0.0003 | 656 | 0.18686 | 0.015572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.18686 | 10.5464 | 10.5464 | 0%
North Coast | HU_Humboldt | FRUITLAND 1141 | 2011 | FRUITLAND 1141circuit_breaker | 2.0615 | 69.7612 | 3.186 | 0 | 3.186 | 0 | 2128 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 1 | 3877 |  | 701 | 463 | 3877 | 701 | 463 | 1309.3 | 0.02955 | 0.04307 | 657 | 0.80968 | 0.015571 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 0.80968 | 220.0262 | 220.0262 | 0%
North Valley | NV_North Valley | KANAKA 1101 | 7058 | KANAKA 11011044 | 1.5959 | 124.7356 | 5.8169 | 0 | 5.8169 | 0 | 1838 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 1 | 3350 |  | 606 | 400 | 3350 | 606 | 400 | 1131.72 | 0.012794 | 0.01612 | 658 | 1.0893 | 0.015561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 1.0893 | 104.18 | 104.18 | 0%
Central Coast | LP_Los Padres | BUELLTON 1101 | 7373 | BUELLTON 1101Y26 | 5.7758 | 355.3425 | 13.7708 | 0.44905 | 13.3216 | 0.44905 | 175 | 16 | 1 | 0 | 1 | 0 | 0 | 249 | 0.96739 | 335 |  | 60 | 40 | 319 | 59 | 40 | 109.54 | 0.016254 | 0.00199 | 659 | 1.5514 | 0.015514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 1.5008 | 4.4289 | 4.357 | 3.261%
Sierra | SI_Sierra | BRUNSWICK 1106 | 623 | BRUNSWICK 11062790 | 3.2962 | 239.2427 | 8.4254 | 3.1375 | 5.2879 | 5.6214 | 2864 | 3219 | 1111 | 943 | 758 | 654 | 0 | 373 | 0.3328 | 4954 |  | 1425 | 1150 | 1735 | 667 | 496 | 1069.94 | 0.013778 | 0.01911 | 660 | 2.0356 | 0.015421 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 1.2776 | 126.1375 | 169.1319 | 37.24%
North Valley | NV_North Valley | RISING RIVER 1101 | 5797 | RISING RIVER 11011530 | 2.5368 | 234.3484 | 11.6468 | 0 | 11.6468 | 0 | 1495 | 0 | 0 | 0 | 0 | 0 | 0 | 264 | 1 | 2727 |  | 494 | 326 | 2727 | 494 | 326 | 922.21 | 0.010825 | 0.01112 | 661 | 1.5819 | 0.015358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 1.5819 | 42.4152 | 42.4152 | 0%
Sierra | SI_Sierra | PENRYN 1107 | 1325 | PENRYN 1107circuit_breaker | 2.9882 | 65.2067 | 6.1858 | 0 | 6.1858 | 0 | 812 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 1 | 1487 |  | 270 | 179 | 1487 | 270 | 179 | 503.73 | 0.045827 | 0.02573 | 662 | 1.0096 | 0.015296 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 1.0096 | 43.6484 | 43.6484 | 0%
North Valley | NV_North Valley | OREGON TRAIL 1102 | 1852 | OREGON TRAIL 110249144 | 7.6254 | 375.869 | 17.3888 | 0.73277 | 16.6559 | 1.6847 | 1244 | 217 | 35 | 28 | 0 | 0 | 0 | 626 | 0.90312 | 2268 |  | 407 | 274 | 2051 | 407 | 274 | 742.18 | 0.020287 | 0.01717 | 663 | 3.1249 | 0.015243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 2.9932 | 24.4358 | 23.4058 | 4.214%
North Coast | HU_Humboldt | UPPER LAKE 1101 | 6371 | UPPER LAKE 110175370 | 3.7019 | 262.3159 | 9.6576 | 4.1771 | 5.4805 | 9.6576 | 1286 | 1776 | 391 | 221 | 1 | 1 | 0 | 299 | 0 | 1776 |  | 391 | 221 | 0 | 390 | 220 | 534.3 | 0.014112 | 0.01144 | 664 | 2.0223 | 0.015206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 1.1476 | 71.1615 | 40.4864 | 43.25%
Central Valley | YO_Yosemite | MARIPOSA 2101 | 8459 | MARIPOSA 2101circuit_breaker | 2.5121 | 105.0238 | 4.0773 | 0.21951 | 3.8578 | 0.32102 | 200 | 53 | 9 | 5 | 1 | 1 | 0 | 196 | 0.92127 | 399 |  | 73 | 48 | 346 | 72 | 47 | 129.78 | 0.02392 | 0.00358 | 665 | 0.54574 | 0.015159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.51636 | 18.6637 | 17.9041 | 5.384%
Bay Area | NB_North Bay | WOODACRE 1101 | 6719 | WOODACRE 1101circuit_breaker | 0.93948 | 69.8258 | 3.2345 | 1.8809 | 1.3536 | 2.4095 | 951 | 1197 | 285 | 98 | 230 | 76 | 0 | 198 | 0.25506 | 1641 |  | 366 | 151 | 444 | 136 | 75 | 226.28 | 0.013455 | 0.0038 | 666 | 0.61739 | 0.015058 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.25837 | 100.4729 | 113.1561 | 58.15%
North Coast | SO_Sonoma | RINCON 1103 | 244 | RINCON 1103circuit_breaker | 0.62577 | 83.7774 | 2.5642 | 0.42102 | 2.1432 | 2.265 | 272 | 164 | 164 | 50 | 146 | 42 | 0 | 126 | 0.1167 | 223 |  | 175 | 57 | 59 | 29 | 15 | 45.04 | 0.0074695 | 0.00045 | 667 | 0.37497 | 0.014999 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.3134 | 13.5313 | 68.2473 | 16.42%
North Coast | HU_Humboldt | WILLITS 1104 | 3078 | WILLITS 11044650 | 2.5351 | 106.2109 | 2.8803 | 2.8091 | 0.071212 | 2.8803 | 261 | 659 | 124 | 49 | 122 | 49 | 0 | 129 | 0 | 659 |  | 124 | 49 | 0 | 2 | 0 | 2.74 | 0.023868 | 0.0001 | 668 | 0.6884 | 0.014965 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.01702 | 28.0851 | 43.051 | 97.53%
Central Valley | ST_Stockton | MARTELL 1102 | 7126 | MARTELL 1102circuit_breaker | 1.6119 | 146.4685 | 5.971 | 0 | 5.971 | 0 | 507 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 1 | 933 |  | 170 | 113 | 933 | 170 | 113 | 316.87 | 0.011005 | 0.00389 | 669 | 1.0592 | 0.014918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 1.0592 | 28.4708 | 28.4708 | 0%
Central Valley | ST_Stockton | CORRAL 1103 | 1151 | CORRAL 110336680 | 3.476 | 222.5025 | 11.4182 | 0 | 11.4182 | 0 | 227 | 0 | 0 | 0 | 0 | 0 | 0 | 281 | 1 | 424 |  | 79 | 53 | 424 | 79 | 53 | 146.39 | 0.015622 | 0.00257 | 670 | 1.2973 | 0.014912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 1.2973 | 6.9188 | 6.9188 | 0%
North Valley | NV_North Valley | CHALLENGE 1102 | 4103 | CHALLENGE 1102circuit_breaker | 4.7388 | 327.5851 | 14.8621 | 0 | 14.8621 | 0 | 10916 | 0 | 0 | 0 | 0 | 0 | 0 | 349 | 1 | 19835 |  | 3579 | 2359 | 19835 | 3579 | 2359 | 6688.38 | 0.014466 | 0.10766 | 671 | 3.543 | 0.014824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3. >20 - 30% | 1. <= 10% | 3.543 | 240.8135 | 240.8135 | 0%
North Coast | HU_Humboldt | FRUITLAND 1141 | 4609 | FRUITLAND 11418860 | 0.5522 | 42.6067 | 2.1536 | 0 | 2.1536 | 0 | 2141 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 1 | 3900 |  | 705 | 466 | 3900 | 705 | 466 | 1316.85 | 0.01296 | 0.019 | 672 | 0.35573 | 0.014822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 0.35573 | 327.3591 | 327.3591 | 0%
Bay Area | NB_North Bay | PUEBLO 2102 | 2629 | PUEBLO 2102792 | 8.8934 | 529.1511 | 17.7985 | 11.5388 | 6.2595 | 17.6364 | 4449 | 8053 | 2681 | 1286 | 1849 | 776 | 7 | 666 | 0.0091087 | 8127 |  | 2694 | 1295 | 74 | 845 | 519 | 1164.31 | 0.016807 | 0.02953 | 673 | 3.4973 | 0.014819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 1.23 | 134.9955 | 151.3612 | 64.83%
North Coast | SO_Sonoma | GEYSERVILLE 1101 | 5934 | GEYSERVILLE 110135492 | 4.3569 | 238.9095 | 10.5998 | 0 | 10.5998 | 0 | 1368 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 1 | 2497 |  | 452 | 299 | 2497 | 452 | 299 | 843.97 | 0.018237 | 0.01714 | 674 | 1.3877 | 0.014763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 1.3877 | 42.6423 | 42.6423 | 0%
Central Valley | ST_Stockton | OLETA 1102 | 6533 | OLETA 1102circuit_breaker | 4.8128 | 303.5463 | 13.6604 | 0.046212 | 13.6144 | 0.046212 | 722 | 3 | 1 | 0 | 0 | 0 | 0 | 286 | 0.99662 | 1322 |  | 241 | 159 | 1319 | 241 | 159 | 448.88 | 0.015855 | 0.00795 | 675 | 1.9304 | 0.014736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 1.9239 | 17.7019 | 17.6422 | 0.3383%
Central Valley | YO_Yosemite | MERCED FALLS 1102 | 1099 | MERCED FALLS 110287352 | 8.0894 | 655.3649 | 25.3631 | 24.0371 | 1.3259 | 25.2574 | 482 | 2103 | 363 | 274 | 341 | 257 | 0 | 749 | 0.0041668 | 2107 |  | 364 | 274 | 4 | 23 | 17 | 31.87 | 0.012343 | 0.00059 | 676 | 2.3721 | 0.014734 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.12401 | 17.3461 | 14.3516 | 94.77%
North Coast | HU_Humboldt | WILLITS 1104 | 4799 | WILLITS 110434006 | 1.8677 | 113.0101 | 4.8318 | 3.5907 | 1.2413 | 4.7322 | 533 | 1014 | 151 | 69 | 102 | 48 | 0 | 225 | 0.020618 | 1034 |  | 155 | 71 | 20 | 53 | 23 | 74.41 | 0.016527 | 0.00182 | 677 | 0.78067 | 0.01473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.20055 | 42.6976 | 32.079 | 74.31%
Sierra | SI_Sierra | PIKE CITY 1101 | 3018 | PIKE CITY 1101circuit_breaker | 8.3978 | 464.762 | 19.3667 | 0 | 19.3667 | 0.6767 | 12783 | 265 | 265 | 248 | 0 | 0 | 0 | 926 | 0.96506 | 22679 |  | 4309 | 2913 | 22414 | 4309 | 2913 | 7920.59 | 0.018069 | 0.1619 | 678 | 3.759 | 0.014683 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3. >20 - 30% | 1. <= 10% | 3.759 | 222.4957 | 222.4957 | 0%
Central Valley | YO_Yosemite | OAKHURST 1101 | 7448 | OAKHURST 11016220 | 4.1155 | 455.4217 | 19.6489 | 17.8258 | 1.8231 | 19.6475 | 597 | 1865 | 895 | 663 | 678 | 590 | 0 | 515 | 6.7472e-05 | 1865 |  | 895 | 663 | 0 | 217 | 73 | 297.29 | 0.0090367 | 0.00408 | 679 | 1.6529 | 0.014628 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.15337 | 119.0276 | 45.5497 | 90.72%
Central Coast | SJ_San Jose | MORGAN HILL 2110 | 285 | MORGAN HILL 2110XR326 | 1.2642 | 59.4576 | 3.7222 | 0 | 3.7222 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 1 | 163 |  | 31 | 22 | 163 | 31 | 22 | 57.14 | 0.021263 | 0.00137 | 680 | 0.29243 | 0.014622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.29243 | 8.3285 | 8.3285 | 0%
North Coast | SO_Sonoma | FULTON 1107 | 2709 | FULTON 1107circuit_breaker | 0.25035 | 28.4129 | 1.0513 | 0.78712 | 0.2642 | 1.0513 | 104 | 141 | 42 | 18 | 24 | 7 | 3 | 74 | 0 | 141 |  | 42 | 18 | 0 | 18 | 11 | 24.66 | 0.0088112 | 0.00033 | 681 | 0.072892 | 0.014578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.018318 | 68.129 | 39.9496 | 74.87%
North Coast | SO_Sonoma | BELLEVUE 2103 | 4254 | BELLEVUE 2103552 | 2.3256 | 180.8699 | 9.0884 | 0.57254 | 8.5159 | 0.56799 | 918 | 11 | 6 | 2 | 6 | 2 | 0 | 363 | 0.9375 | 1585 |  | 292 | 191 | 1574 | 286 | 189 | 533.48 | 0.012858 | 0.00765 | 682 | 1.1351 | 0.014552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 1.0636 | 33.5842 | 32.1287 | 6.3%
North Coast | SO_Sonoma | MOLINO 1101 | 4087 | MOLINO 1101322 | 4.5259 | 396.0054 | 15.4244 | 0.6767 | 14.7477 | 14.8672 | 5246 | 998 | 980 | 9 | 161 | 1 | 1 | 750 | 0.036124 | 1343 |  | 1042 | 50 | 345 | 881 | 49 | 1238.02 | 0.011429 | 0.02094 | 683 | 3.3785 | 0.0145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 3.2302 | 59.738 | 67.5552 | 4.387%
Central Valley | FR_Fresno | AUBERRY 1101 | 2580 | AUBERRY 1101R2579 | 9.9619 | 836.7669 | 33.0322 | 8.7604 | 24.272 | 22.9752 | 1615 | 2589 | 903 | 765 | 26 | 24 | 1 | 884 | 0.30446 | 3486 |  | 1065 | 872 | 897 | 1039 | 848 | 1504.16 | 0.011905 | 0.02572 | 684 | 3.6868 | 0.014458 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 2.7091 | 42.8066 | 32.2413 | 26.52%
North Coast | SO_Sonoma | CLOVERDALE 1102 | 801 | CLOVERDALE 1102570 | 6.0085 | 447.54 | 17.1623 | 3.9284 | 13.2341 | 15.7288 | 1716 | 949 | 860 | 349 | 520 | 65 | 1 | 680 | 0.083527 | 1210 |  | 907 | 380 | 261 | 387 | 315 | 553.68 | 0.013426 | 0.0108 | 685 | 2.6177 | 0.014383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 2.0185 | 29.2427 | 52.8484 | 22.89%
Sierra | SA_Sacramento | DOBBINS 1101 | 5748 | DOBBINS 110169722 | 1.4006 | 99.2504 | 4.8612 | 0 | 4.8612 | 0 | 915 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 1 | 1674 |  | 304 | 201 | 1674 | 304 | 201 | 567.14 | 0.014112 | 0.00892 | 686 | 1.2933 | 0.01437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 1.2933 | 62.5363 | 62.5363 | 0%
North Coast | HU_Humboldt | GARBERVILLE 1102 | 1027 | GARBERVILLE 11028652 | 3.8642 | 290.626 | 13.7208 | 0 | 13.7208 | 0 | 6985 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 1 | 12697 |  | 2292 | 1511 | 12697 | 2292 | 1511 | 4282.77 | 0.013296 | 0.06337 | 687 | 3.1063 | 0.014315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 3.1063 | 167.0452 | 167.0452 | 0%
North Coast | HU_Humboldt | KONOCTI 1102 | 453 | KONOCTI 1102596 | 3.9309 | 246.0561 | 9.8847 | 8.2937 | 1.5911 | 9.8847 | 598 | 1306 | 210 | 76 | 141 | 44 | 0 | 390 | 0 | 1306 |  | 210 | 76 | 0 | 69 | 32 | 94.53 | 0.015976 | 0.00229 | 688 | 1.3865 | 0.014294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.22318 | 43.3663 | 21.245 | 83.91%
North Coast | HU_Humboldt | UKIAH 1111 | 3769 | UKIAH 111129452 | 1.8945 | 69.9469 | 3.3231 | 0 | 3.3231 | 0 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 1 | 474 |  | 87 | 58 | 474 | 87 | 58 | 161.85 | 0.027085 | 0.0049 | 689 | 0.24252 | 0.014266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.24252 | 26.1803 | 26.1803 | 0%
Bay Area | MI_Mission | VINEYARD 2107 | 2256 | VINEYARD 2107circuit_breaker | 1.0986 | 62.4278 | 3.4386 | 0 | 3.4386 | 0 | 444 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 1 | 819 |  | 150 | 99 | 819 | 150 | 99 | 279.21 | 0.017598 | 0.00549 | 690 | 0.48301 | 0.014206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.48301 | 43.6219 | 43.6219 | 0%
North Coast | HU_Humboldt | MIDDLETOWN 1101 | 640 | MIDDLETOWN 110148212 | 5.9003 | 289.8137 | 11.3244 | 5.9352 | 5.3892 | 8.7843 | 2231 | 2517 | 662 | 372 | 442 | 256 | 1 | 540 | 0.22431 | 3429 |  | 827 | 481 | 912 | 385 | 225 | 609.53 | 0.020359 | 0.0163 | 691 | 2.0586 | 0.014197 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 0.97967 | 71.4391 | 73.0279 | 52.41%
North Valley | NV_North Valley | JESSUP 1103 | 3420 | JESSUP 1103circuit_breaker | 0.23102 | 12.4404 | 0.68049 | 0 | 0.68049 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 134 |  | 26 | 18 | 134 | 26 | 18 | 47.68 | 0.01857 | 0.001 | 692 | 0.11329 | 0.014161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.11329 | 38.2076 | 38.2076 | 0%
North Coast | SO_Sonoma | SONOMA 1102 | 5847 | SONOMA 1102118 | 1.2363 | 108.0607 | 4.9544 | 0 | 4.9544 | 0 | 269 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 1 | 501 |  | 92 | 62 | 501 | 92 | 62 | 171.13 | 0.01144 | 0.00219 | 693 | 1.0988 | 0.014087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 1.0988 | 18.5695 | 18.5695 | 0%
North Coast | SO_Sonoma | MIRABEL 1101 | 6887 | MIRABEL 1101116 | 3.5666 | 263.3445 | 10.354 | 0.1642 | 10.1898 | 4.8422 | 3974 | 320 | 320 | 15 | 3 | 0 | 0 | 411 | 0.53233 | 4168 |  | 1015 | 473 | 3848 | 1012 | 473 | 1732.76 | 0.013543 | 0.0285 | 694 | 2.2124 | 0.014003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 2.1773 | 99.3153 | 98.03 | 1.586%
Sierra | SA_Sacramento | DOBBINS 1101 | 492 | DOBBINS 11011264 | 9.6319 | 810.7735 | 36.2131 | 0.20208 | 36.011 | 0.60303 | 10099 | 351 | 118 | 112 | 36 | 35 | 0 | 807 | 0.98335 | 18397 |  | 3375 | 2258 | 18046 | 3339 | 2223 | 6198.57 | 0.01188 | 0.08248 | 695 | 6.4814 | 0.013969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3. >20 - 30% | 1. <= 10% | 6.4453 | 92.7217 | 93.1984 | 0.558%
Central Valley | FR_Fresno | DUNLAP 1103 | 514 | DUNLAP 11037220 | 7.0594 | 577.3562 | 24.4081 | 0.10701 | 24.3011 | 0.17027 | 1252 | 21 | 1 | 1 | 0 | 0 | 0 | 411 | 0.99302 | 2291 |  | 412 | 273 | 2270 | 412 | 273 | 768.74 | 0.012227 | 0.01048 | 696 | 2.5547 | 0.013884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 2.5435 | 16.9539 | 16.8796 | 0.4384%
Central Valley | YO_Yosemite | BEAR VALLEY 2101 | 7449 | BEAR VALLEY 21014160 | 10.6877 | 590.2013 | 22.678 | 12.36 | 10.3182 | 22.0606 | 514 | 1708 | 503 | 443 | 427 | 369 | 0 | 634 | 0.027226 | 1734 |  | 508 | 446 | 26 | 81 | 77 | 113.31 | 0.018109 | 0.00305 | 697 | 2.4701 | 0.013877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 1.1238 | 7.8502 | 22.4005 | 54.5%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1107 | 6446 | SAN LUIS OBISPO 110788962 | 0.55515 | 62.1956 | 3.0017 | 0 | 3.0017 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 1 | 79 |  | 16 | 12 | 79 | 16 | 12 | 29.03 | 0.0089259 | 0.0003 | 698 | 0.20809 | 0.013873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.20809 | 5.3303 | 5.3303 | 0%
North Coast | SO_Sonoma | FITCH MOUNTAIN 1113 | 3876 | FITCH MOUNTAIN 111324550 | 3.258 | 194.7619 | 9.8 | 0 | 9.8 | 0.23864 | 1042 | 0 | 0 | 0 | 0 | 0 | 0 | 278 | 0.97565 | 1858 |  | 337 | 223 | 1858 | 337 | 223 | 628.91 | 0.016728 | 0.01172 | 699 | 1.5669 | 0.013866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 1.5669 | 34.3878 | 34.3878 | 0%
Central Coast | SJ_San Jose | MORGAN HILL 2105 | 730 | MORGAN HILL 2105XR176 | 10.0355 | 582.5905 | 23.9917 | 0 | 23.9917 | 0 | 1861 | 0 | 0 | 0 | 0 | 0 | 0 | 520 | 1 | 3392 |  | 614 | 405 | 3392 | 614 | 405 | 1146.46 | 0.017226 | 0.02199 | 700 | 3.321 | 0.013837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 3.321 | 25.5922 | 25.5922 | 0%
Bay Area | NB_North Bay | NAPA 1112 | 6642 | NAPA 11121302 | 2.8427 | 257.4064 | 10.0134 | 0 | 10.0134 | 0 | 473 | 0 | 0 | 0 | 0 | 0 | 0 | 182 | 1 | 871 |  | 159 | 106 | 871 | 159 | 106 | 296.22 | 0.011044 | 0.00365 | 701 | 1.2796 | 0.01376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 1.2796 | 15.8786 | 15.8786 | 0%
North Coast | SO_Sonoma | CLOVERDALE 1102 | 6670 | CLOVERDALE 1102670 | 1.1483 | 69.8725 | 2.8443 | 0.31875 | 2.5256 | 2.8364 | 264 | 109 | 56 | 43 | 3 | 0 | 0 | 97 | 0.0027966 | 110 |  | 56 | 43 | 1 | 53 | 43 | 72.7 | 0.016434 | 0.00181 | 702 | 0.3577 | 0.013758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.31762 | 20.9854 | 19.6884 | 11.21%
North Valley | NV_North Valley | CLARK ROAD 1102 | 258 | CLARK ROAD 11022584 | 2.1539 | 190.2393 | 8.7949 | 7.7068 | 1.0881 | 8.7917 | 201 | 535 | 293 | 153 | 250 | 139 | 0 | 262 | 0.00036609 | 535 |  | 293 | 153 | 0 | 43 | 14 | 58.91 | 0.011322 | 0.00101 | 703 | 0.74119 | 0.013726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.091697 | 39.5196 | 33.3148 | 87.63%
North Valley | NV_North Valley | GIRVAN 1102 | 6425 | GIRVAN 11021028 | 6.5542 | 414.3508 | 19.0383 | 0 | 19.0383 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 505 | 1 | 4371 |  | 790 | 521 | 4371 | 790 | 521 | 1475.69 | 0.015818 | 0.02598 | 704 | 3.4886 | 0.013681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 3.4886 | 41.4954 | 41.4954 | 0%
Sierra | SI_Sierra | PENRYN 1107 | 2755 | PENRYN 11072410 | 1.5504 | 70.1667 | 5.1267 | 0 | 5.1267 | 0 | 591 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 1 | 1086 |  | 198 | 131 | 1086 | 198 | 131 | 369 | 0.022095 | 0.0091 | 705 | 0.57371 | 0.01366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.57371 | 38.6213 | 38.6213 | 0%
North Coast | HU_Humboldt | WILLITS 1103 | 4613 | WILLITS 110391948 | 1.3299 | 139.4644 | 6.2314 | 0 | 6.2314 | 0 | 904 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1 | 1654 |  | 300 | 199 | 1654 | 300 | 199 | 559.86 | 0.0095354 | 0.00595 | 706 | 0.9269 | 0.013631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.9269 | 48.143 | 48.143 | 0%
Bay Area | NB_North Bay | SILVERADO 2102 | 5010 | SILVERADO 21023010 | 1.8129 | 86.107 | 3.4614 | 0 | 3.4614 | 0 | 494 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 1 | 909 |  | 166 | 110 | 909 | 166 | 110 | 309.23 | 0.021054 | 0.00727 | 707 | 0.77557 | 0.013606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.77557 | 47.958 | 47.958 | 0%
North Valley | NV_North Valley | RED BLUFF 1104 | 8070 | RED BLUFF 11041302 | 3.679 | 305.7101 | 13.9417 | 13.5206 | 0.42121 | 13.7184 | 474 | 1825 | 132 | 116 | 130 | 114 | 0 | 422 | 0.016016 | 1839 |  | 135 | 118 | 14 | 5 | 4 | 8.11 | 0.012034 | 0.00013 | 708 | 0.77517 | 0.0136 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.02342 | 11.8705 | 9.6832 | 96.98%
Sierra | SI_Sierra | EAST MARYSVILLE 1108 | 3093 | EAST MARYSVILLE 11081706 | 0.26385 | 19.6842 | 1.5072 | 0 | 1.5072 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 1 | 34 |  | 8 | 6 | 34 | 8 | 6 | 14.02 | 0.013404 | 0.00022 | 709 | 0.10874 | 0.013593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.10874 | 5.3079 | 5.3079 | 0%
North Coast | SO_Sonoma | FITCH MOUNTAIN 1113 | 4590 | FITCH MOUNTAIN 1113352 | 2.1767 | 137.8011 | 5.461 | 3.6992 | 1.7617 | 5.4608 | 726 | 1279 | 409 | 29 | 368 | 22 | 0 | 167 | 3.4681e-05 | 1279 |  | 409 | 29 | 0 | 41 | 7 | 56.17 | 0.015796 | 0.00135 | 710 | 1.1004 | 0.013585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.35498 | 23.2724 | 74.8949 | 67.74%
Bay Area | DI_Diablo | CLAYTON 2213 | 3972 | CLAYTON 2213circuit_breaker | 0.85641 | 88.8657 | 3.8354 | 0 | 3.8354 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 1 | 183 |  | 35 | 24 | 183 | 35 | 24 | 64.42 | 0.0096372 | 0.0007 | 711 | 0.352 | 0.013538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.352 | 9.1255 | 9.1255 | 0%
North Coast | HU_Humboldt | UKIAH 1114 | 6156 | UKIAH 1114408 | 17.9959 | 1017.8939 | 36.5237 | 0 | 36.5237 | 0 | 4739 | 0 | 0 | 0 | 0 | 0 | 0 | 554 | 1 | 8618 |  | 1556 | 1026 | 8618 | 1556 | 1026 | 2907.34 | 0.01768 | 0.0572 | 712 | 4.5587 | 0.013527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 4.5587 | 42.6025 | 42.6025 | 0%
North Coast | HU_Humboldt | GARBERVILLE 1101 | 5971 | GARBERVILLE 110135706 | 3.4122 | 221.9358 | 10.5623 | 0.10019 | 10.4621 | 0.74962 | 5060 | 999 | 353 | 202 | 296 | 154 | 0 | 212 | 0.92903 | 9547 |  | 1896 | 1220 | 8548 | 1600 | 1066 | 2961.32 | 0.015375 | 0.05115 | 713 | 2.1352 | 0.013514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 2.115 | 152.9327 | 179.5062 | 0.9486%
Bay Area | NB_North Bay | CALISTOGA 1101 | 6733 | CALISTOGA 1101circuit_breaker | 1.6957 | 69.9053 | 2.2602 | 1.1756 | 1.0847 | 2.2602 | 191 | 423 | 123 | 67 | 77 | 27 | 0 | 70 | 0 | 423 |  | 123 | 67 | 0 | 46 | 40 | 63.02 | 0.024257 | 0.00232 | 714 | 0.36424 | 0.013491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.1748 | 42.4096 | 54.4193 | 52.01%
Sierra | SI_Sierra | MOUNTAIN QUARRIES 2101 | 375 | MOUNTAIN QUARRIES 21011102 | 16.1393 | 995.4284 | 42.4178 | 0 | 42.4178 | 0 | 3613 | 0 | 0 | 0 | 0 | 0 | 0 | 904 | 1 | 6573 |  | 1187 | 783 | 6573 | 1187 | 783 | 2217.76 | 0.016213 | 0.04002 | 715 | 6.825 | 0.013435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 6.825 | 27.9835 | 27.9835 | 0%
North Valley | NV_North Valley | WYANDOTTE 1109 | 2076 | WYANDOTTE 11091040 | 0.46964 | 16.904 | 0.78239 | 0 | 0.78239 | 0.35303 | 121 | 151 | 59 | 56 | 1 | 1 | 0 | 20 | 0.54878 | 278 |  | 83 | 72 | 127 | 82 | 71 | 123.77 | 0.027783 | 0.00474 | 716 | 0.17443 | 0.013418 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.17443 | 104.8076 | 106.0857 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2111 | 2918 | TEMPLETON 2111R86 | 3.3419 | 242.644 | 10.4083 | 0 | 10.4083 | 0 | 1671 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 1 | 3047 |  | 551 | 364 | 3047 | 551 | 364 | 1029.1 | 0.013773 | 0.01578 | 717 | 2.0361 | 0.013396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 2.0361 | 52.9384 | 52.9384 | 0%
Sierra | SI_Sierra | PENRYN 1105 | 6699 | PENRYN 110551676 | 2.2395 | 188.3117 | 9.4665 | 0 | 9.4665 | 0 | 1007 | 0 | 0 | 0 | 0 | 0 | 0 | 258 | 1 | 1841 |  | 334 | 221 | 1841 | 334 | 221 | 623.27 | 0.011892 | 0.00826 | 718 | 1.537 | 0.01325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 1.537 | 35.2824 | 35.2824 | 0%
North Coast | HU_Humboldt | REDBUD 1101 | 4588 | REDBUD 1101454 | 1.2333 | 134.67 | 5.3286 | 4.6693 | 0.65928 | 5.3286 | 260 | 347 | 106 | 22 | 95 | 18 | 0 | 202 | 0 | 347 |  | 106 | 22 | 0 | 11 | 4 | 15.07 | 0.009158 | 0.00021 | 719 | 0.65628 | 0.013126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.081199 | 16.6849 | 19.8927 | 87.63%
Sierra | SI_Sierra | HALSEY 1101 | 5027 | HALSEY 11012414 | 6.5201 | 322.0105 | 14.3991 | 1.4657 | 12.9333 | 1.7629 | 3303 | 868 | 257 | 179 | 245 | 173 | 0 | 388 | 0.87757 | 6143 |  | 1210 | 808 | 5275 | 965 | 635 | 1796.8 | 0.020248 | 0.04063 | 720 | 2.8785 | 0.013025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 2.5855 | 74.6134 | 84.0333 | 10.18%
North Valley | NV_North Valley | DESCHUTES 1101 | 1273 | DESCHUTES 11011652 | 5.8339 | 551.0592 | 20.4436 | 0 | 20.4436 | 0 | 1312 | 0 | 0 | 0 | 0 | 0 | 0 | 448 | 1 | 2395 |  | 434 | 287 | 2395 | 434 | 287 | 810.13 | 0.010587 | 0.00955 | 721 | 2.6436 | 0.013023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 2.6436 | 21.2292 | 21.2292 | 0%
North Coast | HU_Humboldt | GARBERVILLE 1102 | 5157 | GARBERVILLE 11022500 | 4.3768 | 346.4493 | 15.7985 | 0 | 15.7985 | 0 | 8035 | 0 | 0 | 0 | 0 | 0 | 0 | 411 | 1 | 14604 |  | 2636 | 1737 | 14604 | 2636 | 1737 | 4925.68 | 0.012633 | 0.06925 | 723 | 3.0015 | 0.012993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 3.0015 | 166.8514 | 166.8514 | 0%
North Coast | HU_Humboldt | FRUITLAND 1141 | 7795 | FRUITLAND 11413902 | 0.61517 | 87.4485 | 4.1835 | 0 | 4.1835 | 3.9392 | 2322 | 675 | 675 | 84 | 366 | 40 | 0 | 74 | 0.0584 | 922 |  | 720 | 113 | 247 | 354 | 73 | 507.21 | 0.0070346 | 0.00518 | 724 | 0.98791 | 0.01283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.98791 | 84.6177 | 172.1038 | 0%
North Coast | HU_Humboldt | LAYTONVILLE 1101 | 6403 | LAYTONVILLE 11011760 | 1.9638 | 201.3077 | 8.9678 | 2.6023 | 6.3655 | 8.9678 | 3122 | 5701 | 1999 | 1545 | 1471 | 1201 | 0 | 197 | 0 | 5701 |  | 1999 | 1545 | 0 | 528 | 344 | 723.36 | 0.0097553 | 0.01071 | 725 | 1.6155 | 0.012822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 1.1467 | 82.9467 | 222.9086 | 29.02%
North Coast | SO_Sonoma | CLOVERDALE 1102 | 4667 | CLOVERDALE 1102674 | 5.3023 | 393.4674 | 16.3136 | 10.1191 | 6.1945 | 15.4739 | 1038 | 601 | 379 | 213 | 97 | 18 | 1 | 369 | 0.051477 | 699 |  | 397 | 225 | 98 | 300 | 207 | 419.82 | 0.013476 | 0.00841 | 726 | 1.4022 | 0.012748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.53245 | 48.43 | 24.3355 | 62.03%
North Valley | NV_North Valley | WILDWOOD 1101 | 9027 | WILDWOOD 110198896 | 1.0708 | 118.9619 | 4.8761 | 0 | 4.8761 | 0 | 901 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 1 | 1648 |  | 299 | 198 | 1648 | 299 | 198 | 557.95 | 0.0090015 | 0.0056 | 727 | 0.49702 | 0.012744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.49702 | 61.319 | 61.319 | 0%
North Coast | SO_Sonoma | MOLINO 1102 | 3075 | MOLINO 1102104 | 8.0711 | 581.7482 | 23.0672 | 0.57538 | 22.4919 | 22.486 | 9969 | 1101 | 1075 | 611 | 37 | 3 | 1 | 1244 | 0.025198 | 1557 |  | 1157 | 665 | 456 | 1120 | 662 | 1575.44 | 0.013874 | 0.03231 | 728 | 4.3192 | 0.012741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 4.2114 | 49.7958 | 50.1577 | 2.494%
North Coast | SO_Sonoma | FITCH MOUNTAIN 1113 | 5255 | FITCH MOUNTAIN 1113406 | 0.4666 | 45.2658 | 1.9362 | 0 | 1.9362 | 0 | 502 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 1 | 924 |  | 169 | 112 | 924 | 169 | 112 | 314.69 | 0.010308 | 0.00362 | 729 | 0.4966 | 0.012733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.4966 | 87.2855 | 87.2855 | 0%
North Coast | SO_Sonoma | SALMON CREEK 1101 | 6208 | SALMON CREEK 110137368 | 1.5666 | 159.2096 | 6.3975 | 0 | 6.3975 | 0 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 1 | 265 |  | 50 | 34 | 265 | 50 | 34 | 92.35 | 0.0098396 | 0.00102 | 730 | 0.26739 | 0.012733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.26739 | 7.8155 | 7.8155 | 0%
North Coast | HU_Humboldt | WILLITS 1103 | 3782 | WILLITS 11032506 | 3.7581 | 296.345 | 11.8769 | 0 | 11.8769 | 0 | 6289 | 1 | 0 | 0 | 0 | 0 | 0 | 220 | 1 | 11434 |  | 2064 | 1360 | 11433 | 2064 | 1360 | 3856.65 | 0.012681 | 0.05443 | 731 | 2.0878 | 0.012731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 2.0878 | 173.7828 | 173.7828 | 0%
Central Coast | LP_Los Padres | OCEANO 1104 | 3211 | OCEANO 1104Q10 | 8.3856 | 561.6423 | 21.4816 | 8.9521 | 12.5295 | 10.922 | 881 | 1193 | 177 | 48 | 147 | 39 | 0 | 874 | 0.49157 | 1985 |  | 321 | 143 | 792 | 174 | 104 | 309.66 | 0.01493 | 0.0054 | 732 | 4.064 | 0.0127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 2.3704 | 13.8872 | 14.943 | 41.67%
Sierra | SI_Sierra | APPLE HILL 2102 | 1194 | APPLE HILL 21021532 | 15.5379 | 984.6148 | 37.2405 | 0.32652 | 36.914 | 0.32652 | 10881 | 356 | 162 | 127 | 162 | 127 | 0 | 1389 | 0.99123 | 19954 |  | 3699 | 2457 | 19598 | 3537 | 2330 | 6609.51 | 0.015781 | 0.11607 | 733 | 7.0586 | 0.01265 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3. >20 - 30% | 1. <= 10% | 6.9968 | 95.8173 | 99.3273 | 0.8768%
Bay Area | DI_Diablo | CLAYTON 2215 | 7715 | CLAYTON 2215W531R | 1.9404 | 148.3325 | 7.0417 | 0 | 7.0417 | 0 | 297 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 1 | 552 |  | 101 | 68 | 552 | 101 | 68 | 188.05 | 0.013082 | 0.00275 | 734 | 0.90415 | 0.012558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.90415 | 14.3432 | 14.3432 | 0%
Bay Area | NB_North Bay | PUEBLO 1104 | 2016 | PUEBLO 11042802 | 1.8623 | 249.6636 | 9.164 | 0 | 9.164 | 0 | 412 | 0 | 0 | 0 | 0 | 0 | 0 | 162 | 1 | 760 |  | 139 | 93 | 760 | 139 | 93 | 258.83 | 0.0074594 | 0.00216 | 735 | 1.0887 | 0.012514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 1.0887 | 15.168 | 15.168 | 0%
Central Coast | CC_Central Coast | SAN JUSTO 1101 | 2039 | SAN JUSTO 110136902 | 4.6035 | 289.9659 | 12.7756 | 0 | 12.7756 | 0 | 1024 | 0 | 0 | 0 | 0 | 0 | 0 | 268 | 1 | 1872 |  | 340 | 225 | 1872 | 340 | 225 | 634.28 | 0.015876 | 0.01122 | 736 | 1.4509 | 0.012507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 1.4509 | 26.6133 | 26.6133 | 0%
Bay Area | PE_Peninsula | WOODSIDE 1101 | 2362 | WOODSIDE 11018884 | 3.1159 | 155.2107 | 6.7898 | 0.036553 | 6.7532 | 1.2875 | 5370 | 1470 | 484 | 211 | 31 | 15 | 0 | 312 | 0.81038 | 9383 |  | 1913 | 1153 | 7913 | 1882 | 1138 | 3290.51 | 0.020075 | 0.07856 | 737 | 1.6995 | 0.012496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3. >20 - 30% | 1. <= 10% | 1.6904 | 278.6819 | 281.7473 | 0.5384%
Central Coast | LP_Los Padres | SANTA YNEZ 1101 | 6975 | SANTA YNEZ 1101Y16 | 2.2277 | 153.5628 | 8.0456 | 0 | 8.0456 | 0 | 224 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | 1 | 419 |  | 78 | 52 | 419 | 78 | 52 | 144.57 | 0.014507 | 0.00235 | 738 | 0.55943 | 0.012432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.55943 | 9.6947 | 9.6947 | 0%
North Coast | SO_Sonoma | FORT ROSS 1121 | 7961 | FORT ROSS 1121circuit_breaker | 3.2046 | 331.469 | 13.2241 | 0 | 13.2241 | 0 | 5078 | 0 | 0 | 0 | 0 | 0 | 0 | 219 | 1 | 9234 |  | 1667 | 1099 | 9234 | 1667 | 1099 | 3114.85 | 0.009668 | 0.03351 | 739 | 1.4149 | 0.012411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 1.4149 | 126.0582 | 126.0582 | 0%
Central Coast | LP_Los Padres | ATASCADERO 1101 | 2154 | ATASCADERO 1101A02 | 8.2094 | 673.5632 | 28.2549 | 0 | 28.2549 | 0 | 2504 | 0 | 0 | 0 | 0 | 0 | 0 | 519 | 1 | 4559 |  | 824 | 544 | 4559 | 824 | 544 | 1539.19 | 0.012188 | 0.02088 | 740 | 4.0292 | 0.012398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 4.0292 | 29.1631 | 29.1631 | 0%
Bay Area | NB_North Bay | PUEBLO 1105 | 2131 | PUEBLO 1105696 | 5.6032 | 484.8015 | 20.5729 | 0 | 20.5729 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 366 | 1 | 1465 |  | 266 | 176 | 1465 | 266 | 176 | 496.27 | 0.011558 | 0.00639 | 741 | 1.9158 | 0.01236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 1.9158 | 12.9296 | 12.9296 | 0%
North Valley | NV_North Valley | WHITMORE 1101 | 284 | WHITMORE 11011598 | 6.4371 | 741.3581 | 31.0229 | 0 | 31.0229 | 0 | 13243 | 0 | 0 | 0 | 0 | 0 | 0 | 678 | 1 | 24061 |  | 4341 | 2861 | 24061 | 4341 | 2861 | 8112.66 | 0.0086829 | 0.07838 | 742 | 4.1017 | 0.012317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3. >20 - 30% | 1. <= 10% | 4.1017 | 139.9288 | 139.9288 | 0%
North Coast | SO_Sonoma | MOLINO 1101 | 6032 | MOLINO 1101891 | 0.8441 | 78.9386 | 2.9081 | 0.083333 | 2.8246 | 2.6246 | 1404 | 164 | 141 | 4 | 2 | 0 | 0 | 171 | 0.097493 | 414 |  | 186 | 34 | 250 | 184 | 34 | 274.58 | 0.010693 | 0.00409 | 743 | 0.72638 | 0.012311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.70552 | 65.1415 | 63.9583 | 2.866%
Central Valley | ST_Stockton | STANISLAUS 1702 | 7295 | STANISLAUS 1702circuit_breaker | 0.93026 | 93.6541 | 4.3475 | 1.557 | 2.7905 | 3.3587 | 907 | 824 | 116 | 67 | 29 | 12 | 0 | 160 | 0.22745 | 1201 |  | 185 | 112 | 377 | 156 | 100 | 247.65 | 0.009933 | 0.00322 | 744 | 0.98169 | 0.012271 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.63011 | 55.9034 | 42.5528 | 35.81%
Sierra | SI_Sierra | HIGGINS 1104 | 1154 | HIGGINS 11044281 | 4.3632 | 370.0049 | 13.585 | 0 | 13.585 | 0 | 3261 | 0 | 0 | 0 | 0 | 0 | 0 | 293 | 1 | 5934 |  | 1072 | 707 | 5934 | 1072 | 707 | 2002.7 | 0.011792 | 0.02629 | 746 | 2.2943 | 0.012204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 2.2943 | 78.9103 | 78.9103 | 0%
Central Valley | FR_Fresno | WOODWARD 2108 | 5815 | WOODWARD 210878448 | 2.7561 | 347.3024 | 18.5466 | 17.8612 | 0.68561 | 18.1606 | 309 | 854 | 191 | 164 | 187 | 160 | 0 | 270 | 0.020812 | 866 |  | 193 | 165 | 12 | 6 | 5 | 9.3 | 0.0079358 | 0.0001 | 747 | 1.0848 | 0.012189 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.040101 | 8.7514 | 10.4062 | 96.3%
Central Coast | CC_Central Coast | SAN JUSTO 1101 | 5984 | SAN JUSTO 11014339 | 3.507 | 201.7771 | 7.6453 | 0 | 7.6453 | 0 | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 1 | 757 |  | 138 | 92 | 757 | 138 | 92 | 257.19 | 0.01738 | 0.00499 | 748 | 1.048 | 0.012046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 1.048 | 18.0504 | 18.0504 | 0%
North Valley | NV_North Valley | MC ARTHUR 1102 | 4860 | MC ARTHUR 11021324 | 0.13492 | 25.4691 | 1.8142 | 0 | 1.8142 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1 | 20 |  | 5 | 5 | 20 | 5 | 5 | 8.65 | 0.0052974 | 6e-05 | 749 | 0.048146 | 0.012037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.048146 | 2.756 | 2.756 | 0%
North Coast | SO_Sonoma | GEYSERVILLE 1102 | 3022 | GEYSERVILLE 1102274 | 1.6194 | 137.5338 | 6.6157 | 1.8816 | 4.7341 | 3.5536 | 560 | 149 | 26 | 6 | 1 | 1 | 0 | 189 | 0.46286 | 625 |  | 113 | 64 | 476 | 112 | 63 | 196.28 | 0.011774 | 0.00274 | 750 | 0.68286 | 0.01198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.48864 | 23.6582 | 17.0805 | 28.44%
Bay Area | MI_Mission | FREMONT 1104 | 8685 | FREMONT 1104MR339 | 0.14743 | 26.2827 | 1.2051 | 0 | 1.2051 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1 | 74 |  | 15 | 11 | 74 | 15 | 11 | 27.21 | 0.0056095 | 0.00017 | 751 | 0.059732 | 0.011946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.059732 | 12.447 | 12.447 | 0%
North Coast | HU_Humboldt | FRUITLAND 1142 | 6757 | FRUITLAND 11426054 | 3.3128 | 207.1145 | 10.2112 | 0 | 10.2112 | 0 | 6056 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 1 | 11010 |  | 1988 | 1310 | 11010 | 1988 | 1310 | 3714.46 | 0.015995 | 0.06612 | 752 | 0.42997 | 0.011943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 0.42997 | 194.6887 | 194.6887 | 0%
Central Valley | KE_Kern | SAN BERNARD 1101 | 3335 | SAN BERNARD 1101circuit_breaker | 0.24585 | 21.5679 | 2.0011 | 0 | 2.0011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.011399 | 9e-05 | 753 | 0.011924 | 0.011924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.011924 | 1.9989 | 1.9989 | 0%
North Coast | HU_Humboldt | GARBERVILLE 1102 | 8908 | GARBERVILLE 110237054 | 1.6985 | 186.9932 | 8.4703 | 0 | 8.4703 | 0 | 4286 | 0 | 0 | 0 | 0 | 0 | 0 | 204 | 1 | 7796 |  | 1408 | 928 | 7796 | 1408 | 928 | 2630.6 | 0.0090835 | 0.02659 | 754 | 1.3215 | 0.011905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 1.3215 | 166.2286 | 166.2286 | 0%
North Valley | NV_North Valley | WYANDOTTE 1103 | 3366 | WYANDOTTE 11031974 | 6.32 | 534.6199 | 22.992 | 0 | 22.992 | 0 | 12602 | 0 | 0 | 0 | 0 | 0 | 0 | 581 | 1 | 22897 |  | 4132 | 2722 | 22897 | 4132 | 2722 | 7721.57 | 0.011821 | 0.10157 | 755 | 4.4934 | 0.011856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3. >20 - 30% | 1. <= 10% | 4.4934 | 179.7143 | 179.7143 | 0%
North Coast | SO_Sonoma | COTATI 1102 | 8910 | COTATI 1102circuit_breaker | 0.90791 | 48.9797 | 1.914 | 1.8672 | 0.04678 | 1.914 | 25 | 57 | 16 | 0 | 16 | 0 | 0 | 82 | 0 | 57 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0.018536 | 0 | 756 | 0.047392 | 0.011848 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.0011583 | 0 | 8.3594 | 97.56%
Sierra | SI_Sierra | HIGGINS 1107 | 4291 | HIGGINS 11071070 | 2.3612 | 172.3762 | 7.4983 | 0 | 7.4983 | 0 | 2810 | 0 | 0 | 0 | 0 | 0 | 0 | 179 | 1 | 5115 |  | 925 | 610 | 5115 | 925 | 610 | 1727.6 | 0.013698 | 0.02635 | 757 | 1.4434 | 0.011831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 1.4434 | 123.3614 | 123.3614 | 0%
North Coast | HU_Humboldt | PHILO 1102 | 6145 | PHILO 1102circuit_breaker | 1.7734 | 205.4117 | 8.6985 | 0 | 8.6985 | 0 | 3204 | 0 | 0 | 0 | 0 | 0 | 0 | 167 | 1 | 5831 |  | 1054 | 695 | 5831 | 1054 | 695 | 1968.77 | 0.0086335 | 0.01892 | 758 | 1.1574 | 0.01181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 1.1574 | 121.1705 | 121.1705 | 0%
Bay Area | PE_Peninsula | WOODSIDE 1101 | 6611 | WOODSIDE 110147872 | 1.38 | 121.1886 | 4.9839 | 0 | 4.9839 | 0 | 4288 | 0 | 0 | 0 | 0 | 0 | 0 | 363 | 1 | 7799 |  | 1409 | 929 | 7799 | 1409 | 929 | 2632.24 | 0.011387 | 0.03336 | 759 | 0.84471 | 0.011732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 0.84471 | 282.7102 | 282.7102 | 0%
North Valley | NV_North Valley | ANITA 1106 | 4519 | ANITA 11062418 | 0.085774 | 13.0076 | 2.2017 | 0 | 2.2017 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1 | 141 |  | 27 | 19 | 141 | 27 | 19 | 49.68 | 0.0065942 | 0.00037 | 760 | 0.058595 | 0.011719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.058595 | 12.2632 | 12.2632 | 0%
Bay Area | DI_Diablo | ALHAMBRA 1105 | 4425 | ALHAMBRA 110595016 | 0.25004 | 21.275 | 0.85928 | 0 | 0.85928 | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 317 |  | 59 | 40 | 317 | 59 | 40 | 109.36 | 0.011753 | 0.00144 | 763 | 0.16361 | 0.011686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.16361 | 68.6621 | 68.6621 | 0%
North Coast | HU_Humboldt | WILLOW CREEK 1101 | 8343 | WILLOW CREEK 11013050 | 0.52257 | 49.8358 | 2.3937 | 0 | 2.3937 | 0 | 1202 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 1 | 2195 |  | 398 | 263 | 2195 | 398 | 263 | 742.81 | 0.010486 | 0.00868 | 764 | 0.43008 | 0.011624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.43008 | 166.2663 | 166.2663 | 0%
North Coast | HU_Humboldt | MIDDLETOWN 1102 | 944 | MIDDLETOWN 1102514 | 0.12978 | 53.6398 | 2.3027 | 1.7042 | 0.59848 | 2.3027 | 104 | 255 | 29 | 9 | 22 | 6 | 0 | 105 | 0 | 255 |  | 29 | 9 | 0 | 7 | 3 | 9.59 | 0.0024195 | 4e-05 | 765 | 0.36842 | 0.011513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.095757 | 11.6962 | 12.5942 | 74.01%
North Valley | NV_North Valley | OREGON TRAIL 1103 | 2683 | OREGON TRAIL 11031500 | 7.258 | 548.0609 | 24.8356 | 17.2644 | 7.5712 | 24.1477 | 2736 | 6038 | 1240 | 923 | 833 | 561 | 0 | 994 | 0.027697 | 6176 |  | 1265 | 939 | 138 | 432 | 378 | 604.26 | 0.013243 | 0.0119 | 766 | 3.3774 | 0.011488 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3. >20 - 30% | 4. >30 - 40% | 1.0296 | 57.0582 | 50.9349 | 69.51%
North Coast | SO_Sonoma | FULTON 1102 | 7533 | FULTON 11024994 | 0.38376 | 51.0369 | 2.3748 | 0 | 2.3748 | 0 | 246 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 1 | 459 |  | 85 | 57 | 459 | 85 | 57 | 157.76 | 0.0075192 | 0.00133 | 767 | 0.14905 | 0.011465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.14905 | 35.7923 | 35.7923 | 0%
Central Coast | LP_Los Padres | OCEANO 1104 | 2480 | OCEANO 1104Q08 | 3.8075 | 336.9749 | 13.3508 | 0.15208 | 13.1989 | 0.39659 | 1174 | 288 | 104 | 95 | 72 | 64 | 0 | 489 | 0.97029 | 2369 |  | 481 | 344 | 2081 | 409 | 280 | 747.62 | 0.011299 | 0.00961 | 768 | 2.0619 | 0.011455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 2.0384 | 30.9875 | 36.0279 | 1.139%
Sierra | SI_Sierra | FORESTHILL 1102 | 8821 | FORESTHILL 1102circuit_breaker | 0.21386 | 9.9497 | 0.46837 | 0 | 0.46837 | 0 | 267 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1 | 497 |  | 92 | 61 | 497 | 92 | 61 | 170.77 | 0.021494 | 0.00411 | 769 | 0.2398 | 0.011419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.2398 | 196.4254 | 196.4254 | 0%
Bay Area | NB_North Bay | SILVERADO 2104 | 1312 | SILVERADO 210437632 | 10.1723 | 783.3851 | 31.3167 | 19.8441 | 11.4725 | 31.2006 | 6892 | 15178 | 5900 | 3157 | 4732 | 2334 | 13 | 1846 | 0.0037072 | 15224 |  | 5908 | 3163 | 46 | 1176 | 829 | 1615.26 | 0.012985 | 0.03175 | 770 | 4.1631 | 0.011375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 1.5251 | 102.5057 | 188.6535 | 63.37%
Bay Area | NB_North Bay | SILVERADO 2105 | 5238 | SILVERADO 2105616 | 2.5006 | 203.0783 | 6.5595 | 4.0464 | 2.5131 | 6.4544 | 1457 | 2532 | 777 | 262 | 530 | 160 | 1 | 388 | 0.016025 | 2575 |  | 785 | 267 | 43 | 255 | 107 | 353.22 | 0.012313 | 0.00653 | 771 | 1.1045 | 0.01127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.42314 | 101.4696 | 119.6743 | 61.69%
Central Coast | LP_Los Padres | ZACA 1101 | 7740 | ZACA 1101circuit_breaker | 1.3868 | 144.3252 | 8.2648 | 0 | 8.2648 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 1 | 141 |  | 27 | 19 | 141 | 27 | 19 | 49.68 | 0.0096085 | 0.00054 | 772 | 0.32604 | 0.011243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.32604 | 3.2669 | 3.2669 | 0%
Central Valley | FR_Fresno | TIVY VALLEY 1107 | 482 | TIVY VALLEY 1107circuit_breaker | 2.2658 | 252.8092 | 13.7366 | 9.3061 | 4.4305 | 13.564 | 320 | 657 | 180 | 142 | 26 | 25 | 0 | 234 | 0.01256 | 664 |  | 181 | 143 | 7 | 155 | 118 | 212.98 | 0.0089627 | 0.00289 | 773 | 0.61822 | 0.01124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.1994 | 34.9848 | 13.1765 | 67.75%
North Valley | NV_North Valley | GIRVAN 1101 | 4392 | GIRVAN 11019732 | 5.6584 | 451.1193 | 20.0625 | 0 | 20.0625 | 0 | 1771 | 0 | 0 | 0 | 0 | 0 | 0 | 507 | 1 | 3228 |  | 584 | 386 | 3228 | 584 | 386 | 1090.6 | 0.012543 | 0.01523 | 774 | 3.2288 | 0.011211 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3. >20 - 30% | 4. >30 - 40% | 3.2288 | 29.109 | 29.109 | 0%
North Coast | HU_Humboldt | LUCERNE 1106 | 1700 | LUCERNE 1106664 | 2.0459 | 162.4552 | 8.3606 | 0 | 8.3606 | 0 | 1798 | 1 | 0 | 0 | 0 | 0 | 0 | 226 | 1 | 3278 |  | 593 | 392 | 3277 | 593 | 392 | 1107.34 | 0.012594 | 0.01553 | 775 | 1.5203 | 0.011178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 1.5203 | 70.9279 | 70.9279 | 0%
Central Valley | YO_Yosemite | COARSEGOLD 2103 | 6583 | COARSEGOLD 21036110 | 2.4694 | 246.4452 | 11.3809 | 0 | 11.3809 | 0 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 1 | 328 |  | 61 | 41 | 328 | 61 | 41 | 113.09 | 0.01002 | 0.00127 | 776 | 0.73399 | 0.011121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.73399 | 5.3599 | 5.3599 | 0%
North Coast | HU_Humboldt | FRUITLAND 1142 | 1016 | FRUITLAND 1142circuit_breaker | 4.4173 | 281.7119 | 9.9991 | 0 | 9.9991 | 0 | 4901 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 1 | 8912 |  | 1609 | 1061 | 8912 | 1609 | 1061 | 3006.41 | 0.01568 | 0.05246 | 777 | 0.29881 | 0.011067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 0.29881 | 160.9152 | 160.9152 | 0%
North Valley | NV_North Valley | KESWICK 1101 | 6521 | KESWICK 11011590 | 1.7615 | 141.7481 | 5.553 | 5.4682 | 0.085038 | 5.553 | 93 | 552 | 88 | 77 | 86 | 76 | 0 | 285 | 0 | 552 |  | 88 | 77 | 0 | 2 | 1 | 2.74 | 0.012427 | 5e-05 | 778 | 0.40915 | 0.011058 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.0062656 | 23.5189 | 15.8472 | 98.47%
North Coast | SO_Sonoma | CALPINE 1144 | 305 | CALPINE 1144circuit_breaker | 4.5733 | 556.5076 | 24.7682 | 0.90341 | 23.8648 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 785 | 1 | 20 |  | 5 | 5 | 20 | 5 | 5 | 8.65 | 0.0082178 | 9e-05 | 779 | 0.088245 | 0.011031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.085026 | 0.20951 | 0.20187 | 3.647%
Central Coast | LP_Los Padres | OCEANO 1104 | 1169 | OCEANO 1104V36 | 2.4376 | 245.7967 | 12.118 | 0 | 12.118 | 0 | 245 | 0 | 0 | 0 | 0 | 0 | 0 | 470 | 1 | 457 |  | 84 | 57 | 457 | 84 | 57 | 156.21 | 0.0099173 | 0.00173 | 780 | 1.1903 | 0.011021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 1.1903 | 6.9318 | 6.9318 | 0%
Bay Area | NB_North Bay | SILVERADO 2105 | 700 | SILVERADO 21051306 | 1.7345 | 111.4204 | 3.4504 | 1.6436 | 1.8068 | 3.2309 | 1075 | 2228 | 924 | 298 | 796 | 254 | 0 | 144 | 0.063618 | 2353 |  | 947 | 313 | 125 | 151 | 59 | 218.12 | 0.015567 | 0.00489 | 781 | 0.46168 | 0.010992 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.24176 | 83.5723 | 274.4626 | 47.63%
North Coast | HU_Humboldt | HOPLAND 1101 | 7578 | HOPLAND 110194006 | 4.741 | 377.9539 | 13.6422 | 0 | 13.6422 | 0 | 1884 | 0 | 0 | 0 | 0 | 0 | 0 | 227 | 1 | 3434 |  | 621 | 410 | 3434 | 621 | 410 | 1159.83 | 0.012544 | 0.0162 | 782 | 1.8322 | 0.010971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 1.8322 | 45.5204 | 45.5204 | 0%
North Coast | HU_Humboldt | CALPINE 1146 | 8710 | CALPINE 1146circuit_breaker | 1.3934 | 81.4956 | 3.8456 | 0.24356 | 3.6021 | 0.24356 | 37 | 48 | 18 | 12 | 18 | 12 | 0 | 135 | 0.93667 | 122 |  | 33 | 23 | 74 | 15 | 11 | 27.21 | 0.017097 | 0.00053 | 783 | 0.054802 | 0.01096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.051331 | 4.1643 | 8.5811 | 6.333%
North Coast | HU_Humboldt | WILLITS 1103 | 1520 | WILLITS 110391810 | 11.5545 | 673.9023 | 26.7686 | 0.73295 | 26.0356 | 0.87348 | 11270 | 1126 | 219 | 132 | 217 | 130 | 0 | 659 | 0.96737 | 20936 |  | 3794 | 2488 | 19810 | 3577 | 2358 | 6683.39 | 0.017146 | 0.12753 | 784 | 4.4256 | 0.010955 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3. >20 - 30% | 1. <= 10% | 4.3045 | 137.3888 | 141.7334 | 2.738%
Bay Area | DI_Diablo | TIDEWATER 2106 | 4400 | TIDEWATER 210665866 | 0.89365 | 45.9405 | 4.3519 | 0 | 4.3519 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 1 | 154 |  | 30 | 21 | 154 | 30 | 21 | 54.96 | 0.019452 | 0.00121 | 785 | 0.14191 | 0.010916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.14191 | 6.8936 | 6.8936 | 0%
Central Coast | SJ_San Jose | LLAGAS 2107 | 3824 | LLAGAS 210740407 | 1.4537 | 119.3948 | 5.0947 | 0 | 5.0947 | 0 | 535 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 1 | 984 |  | 179 | 119 | 984 | 179 | 119 | 333.79 | 0.012175 | 0.00453 | 786 | 0.65143 | 0.010857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.65143 | 35.1346 | 35.1346 | 0%
Bay Area | NB_North Bay | MONTICELLO 1101 | 5769 | MONTICELLO 1101630 | 3.4423 | 434.6271 | 19.1773 | 0 | 19.1773 | 0 | 726 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 1 | 1331 |  | 242 | 160 | 1331 | 242 | 160 | 451.33 | 0.0079202 | 0.00399 | 787 | 0.97368 | 0.010819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.97368 | 12.6191 | 12.6191 | 0%
Sierra | SI_Sierra | PLACER 1103 | 1062 | PLACER 1103circuit_breaker | 7.8679 | 332.2877 | 15.922 | 0.67538 | 15.2468 | 0.94962 | 2608 | 201 | 73 | 53 | 43 | 39 | 1 | 419 | 0.94036 | 4666 |  | 880 | 586 | 4465 | 837 | 547 | 1548.54 | 0.023678 | 0.04121 | 788 | 2.0012 | 0.010817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 1.9164 | 54.8968 | 55.2695 | 4.242%
North Valley | NV_North Valley | DESCHUTES 1101 | 6595 | DESCHUTES 11011654 | 4.3519 | 473.049 | 18.8485 | 0 | 18.8485 | 0 | 1693 | 0 | 0 | 0 | 0 | 0 | 0 | 438 | 1 | 3087 |  | 559 | 369 | 3087 | 559 | 369 | 1043.66 | 0.0091996 | 0.01069 | 789 | 2.4192 | 0.010657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 2.4192 | 29.6576 | 29.6576 | 0%
Bay Area | NB_North Bay | LAS GALLINAS A 1104 | 4156 | LAS GALLINAS A 1104304 | 0.004791 | 7.1263 | 0.18314 | 0 | 0.18314 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 14 |  | 5 | 4 | 14 | 5 | 4 | 8.11 | 0.0006723 | 1e-05 | 790 | 0.085197 | 0.01065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.085197 | 27.3009 | 27.3009 | 0%
Bay Area | MI_Mission | JARVIS 1108 | 932 | JARVIS 1108MR576 | 0.0868 | 23.8205 | 1.133 | 0 | 1.133 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 1 | 121 |  | 24 | 17 | 121 | 24 | 17 | 43.77 | 0.0036439 | 0.00018 | 791 | 0.031924 | 0.010641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.031924 | 21.1836 | 21.1836 | 0%
Central Coast | SJ_San Jose | LLAGAS 2105 | 8849 | LLAGAS 2105XR234 | 0.11467 | 18.0074 | 1.0862 | 0 | 1.0862 | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 1 | 174 |  | 33 | 23 | 174 | 33 | 23 | 60.87 | 0.0063681 | 0.00044 | 792 | 0.09573 | 0.010637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.09573 | 30.3819 | 30.3819 | 0%
North Coast | NC_North Coast | RIO DELL 1102 | 1493 | RIO DELL 11021504 | 2.5377 | 227.7368 | 11.0581 | 0.02822 | 11.0301 | 8.2638 | 9143 | 2430 | 2430 | 1459 | 22 | 5 | 0 | 281 | 0.25269 | 6629 |  | 3188 | 1958 | 4199 | 3166 | 1953 | 4715.33 | 0.011143 | 0.07336 | 793 | 1.988 | 0.010631 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 1.9829 | 287.0324 | 288.2943 | 0.2552%
North Valley | NV_North Valley | KANAKA 1101 | 6351 | KANAKA 110175744 | 2.3604 | 261.3988 | 10.4987 | 0.12936 | 10.3693 | 0.16193 | 3952 | 57 | 22 | 16 | 20 | 15 | 0 | 248 | 0.98458 | 7135 |  | 1300 | 859 | 7078 | 1280 | 844 | 2390.62 | 0.0090298 | 0.02403 | 794 | 1.9104 | 0.010613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 1.8869 | 123.4411 | 123.8252 | 1.232%
North Valley | NV_North Valley | WYANDOTTE 1110 | 102 | WYANDOTTE 11101954 | 3.8629 | 306.4151 | 13.639 | 0.041856 | 13.5972 | 0.041856 | 1437 | 1 | 0 | 0 | 0 | 0 | 0 | 321 | 0.99693 | 2615 |  | 473 | 313 | 2614 | 473 | 313 | 883.27 | 0.012607 | 0.0124 | 795 | 1.749 | 0.0106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 1.7437 | 34.7867 | 34.6799 | 0.3069%
North Coast | HU_Humboldt | MENDOCINO 1101 | 2790 | MENDOCINO 110148750 | 5.714 | 493.302 | 16.7519 | 0 | 16.7519 | 0 | 4526 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 1 | 8231 |  | 1487 | 980 | 8231 | 1487 | 980 | 2777.98 | 0.011583 | 0.03582 | 796 | 2.1767 | 0.010566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 2.1767 | 88.7661 | 88.7661 | 0%
Central Valley | FR_Fresno | DUNLAP 1102 | 6262 | DUNLAP 11027060 | 3.5868 | 480.3007 | 18.9212 | 0 | 18.9212 | 0 | 1978 | 0 | 0 | 0 | 0 | 0 | 0 | 368 | 1 | 3604 |  | 652 | 430 | 3604 | 652 | 430 | 1217.6 | 0.0074678 | 0.01012 | 797 | 1.8912 | 0.010507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 1.8912 | 34.4587 | 34.4587 | 0%
North Valley | NV_North Valley | WYANDOTTE 1107 | 4628 | WYANDOTTE 1107circuit_breaker | 0.3323 | 46.0581 | 2.3193 | 0.80947 | 1.5097 | 1.3576 | 309 | 462 | 229 | 187 | 184 | 146 | 0 | 89 | 0.41467 | 700 |  | 273 | 216 | 238 | 89 | 70 | 143.35 | 0.0072149 | 0.00134 | 798 | 0.20999 | 0.010499 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.13668 | 58.9537 | 117.707 | 34.9%
North Coast | HU_Humboldt | HIGHLANDS 1103 | 6357 | HIGHLANDS 11031282 | 4.012 | 407.3164 | 15.164 | 10.2138 | 4.9504 | 15.164 | 1490 | 3173 | 822 | 394 | 678 | 308 | 0 | 453 | 0 | 3173 |  | 822 | 394 | 0 | 144 | 86 | 197.28 | 0.0098499 | 0.00295 | 799 | 1.6676 | 0.010423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.5444 | 29.0887 | 54.2073 | 67.36%
Central Valley | FR_Fresno | WISHON 1101 | 9085 | WISHON 1101circuit_breaker | 1.3939 | 161.8997 | 7.2214 | 2.1722 | 5.0492 | 7.1343 | 346 | 696 | 301 | 283 | 3 | 1 | 0 | 204 | 0.012064 | 704 |  | 302 | 284 | 8 | 299 | 283 | 410.35 | 0.0086098 | 0.00535 | 800 | 0.60376 | 0.01041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.42215 | 59.2168 | 41.8201 | 30.08%
North Coast | HU_Humboldt | GARBERVILLE 1101 | 1932 | GARBERVILLE 11011514 | 2.7572 | 317.6475 | 14.7761 | 0 | 14.7761 | 0 | 6085 | 0 | 0 | 0 | 0 | 0 | 0 | 267 | 1 | 11062 |  | 1997 | 1316 | 11062 | 1997 | 1316 | 3731.47 | 0.0086802 | 0.03605 | 801 | 2.3186 | 0.010397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 2.3186 | 135.1503 | 135.1503 | 0%
North Coast | HU_Humboldt | MIDDLETOWN 1101 | 915 | MIDDLETOWN 1101548 | 7.4952 | 605.5027 | 25.086 | 14.2318 | 10.854 | 22.1108 | 5654 | 7303 | 2062 | 1338 | 891 | 617 | 1 | 1395 | 0.1186 | 8522 |  | 2282 | 1483 | 1219 | 1391 | 866 | 2015.38 | 0.012379 | 0.0358 | 803 | 2.4782 | 0.010369 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 1.0722 | 128.1558 | 90.9671 | 56.73%
North Coast | HU_Humboldt | MIDDLETOWN 1101 | 6402 | MIDDLETOWN 11011325 | 2.818 | 247.6275 | 8.4237 | 4.8525 | 3.571 | 7.8716 | 4143 | 6742 | 1166 | 717 | 933 | 609 | 1 | 380 | 0.065539 | 7236 |  | 1255 | 776 | 494 | 322 | 167 | 485.6 | 0.01138 | 0.00762 | 804 | 1.3499 | 0.010226 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.57226 | 90.1702 | 148.9849 | 57.61%
North Coast | SO_Sonoma | SONOMA 1102 | 7267 | SONOMA 1106376 | 0.71835 | 40.403 | 1.215 | 0 | 1.215 | 0 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 1 | 201 |  | 38 | 26 | 201 | 38 | 26 | 70.15 | 0.017779 | 0.0014 | 805 | 0.091552 | 0.010172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.091552 | 31.2767 | 31.2767 | 0%
North Valley | NV_North Valley | CHALLENGE 1102 | 1496 | CHALLENGE 11025462 | 7.3321 | 535.2789 | 23.8621 | 1.0771 | 22.785 | 1.4557 | 10256 | 523 | 102 | 97 | 83 | 78 | 0 | 609 | 0.939 | 18023 |  | 3260 | 2178 | 17500 | 3177 | 2100 | 5927.49 | 0.013698 | 0.09049 | 806 | 3.7989 | 0.010158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3. >20 - 30% | 1. <= 10% | 3.6275 | 139.4336 | 136.6182 | 4.514%
North Coast | HU_Humboldt | GARBERVILLE 1101 | 7787 | GARBERVILLE 11012026 | 1.5591 | 144.5906 | 6.4831 | 0 | 6.4831 | 0 | 4631 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 1 | 8422 |  | 1521 | 1003 | 8422 | 1521 | 1003 | 2841.75 | 0.010783 | 0.0341 | 807 | 1.0885 | 0.010079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 1.0885 | 234.6084 | 234.6084 | 0%
North Coast | SO_Sonoma | FITCH MOUNTAIN 1111 | 9044 | 171410 | 0.40625 | 41.2156 | 1.6146 | 0 | 1.6146 | 0 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1 | 237 |  | 45 | 30 | 237 | 45 | 30 | 82.98 | 0.0098567 | 0.00092 | 808 | 0.24049 | 0.01002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.24049 | 27.871 | 27.871 | 0%
North Valley | NV_North Valley | NOTRE DAME 1104 | 5770 | NOTRE DAME 1104circuit_breaker | 0.122 | 11.2848 | 0.76439 | 0 | 0.76439 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 63 |  | 13 | 10 | 63 | 13 | 10 | 23.48 | 0.010811 | 0.00029 | 809 | 0.039974 | 0.0099935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.039974 | 17.0069 | 17.0069 | 0%
Central Coast | LP_Los Padres | MESA 1103 | 1921 | MESA 1103M72 | 2.5188 | 222.332 | 10.5002 | 0 | 10.5002 | 0 | 485 | 0 | 0 | 0 | 0 | 0 | 0 | 214 | 1 | 893 |  | 163 | 108 | 893 | 163 | 108 | 303.68 | 0.011329 | 0.00384 | 810 | 1.2277 | 0.009981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 1.2277 | 15.5235 | 15.5235 | 0%
North Coast | SO_Sonoma | DUNBAR 1102 | 5242 | DUNBAR 1102261774 | 2.6546 | 275.4767 | 11.3731 | 0 | 11.3731 | 0 | 1255 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 1 | 2291 |  | 415 | 274 | 2291 | 415 | 274 | 774.74 | 0.0096362 | 0.00832 | 811 | 1.6915 | 0.0098919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 1.6915 | 36.4896 | 36.4896 | 0%
Central Valley | ST_Stockton | CLAY 1103 | 8943 | CLAY 11031821 | 0.87991 | 73.5307 | 2.8697 | 0 | 2.8697 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 1 | 192 |  | 37 | 25 | 192 | 37 | 25 | 67.97 | 0.011967 | 0.00092 | 812 | 0.16812 | 0.0098895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.16812 | 12.8933 | 12.8933 | 0%
Central Valley | YO_Yosemite | CURTIS 1704 | 3918 | CURTIS 1704circuit_breaker | 2.3 | 390.714 | 16.1436 | 9.3989 | 6.7447 | 13.8464 | 2587 | 5100 | 1109 | 508 | 1079 | 494 | 0 | 594 | 0.1423 | 5770 |  | 1230 | 588 | 670 | 151 | 94 | 267.17 | 0.0058866 | 0.00185 | 813 | 2.0278 | 0.0098439 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.84722 | 22.388 | 76.1914 | 58.22%
North Valley | NV_North Valley | KESWICK 1101 | 7755 | KESWICK 11011588 | 2.0716 | 176.8107 | 8.3248 | 1.3843 | 6.9405 | 1.7746 | 867 | 89 | 21 | 20 | 2 | 2 | 0 | 225 | 0.78683 | 1337 |  | 248 | 170 | 1248 | 246 | 168 | 449.34 | 0.011717 | 0.00599 | 814 | 0.77598 | 0.0098226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.64695 | 35.444 | 29.7905 | 16.63%
North Coast | SO_Sonoma | COTATI 1105 | 727 | COTATI 1105circuit_breaker | 1.1036 | 97.4657 | 3.9544 | 2.6619 | 1.2924 | 3.0619 | 185 | 280 | 27 | 2 | 18 | 2 | 0 | 179 | 0.22568 | 359 |  | 42 | 12 | 79 | 24 | 10 | 39.99 | 0.011323 | 0.00057 | 815 | 0.28211 | 0.009728 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.092205 | 18.5698 | 10.6212 | 67.32%
Bay Area | NB_North Bay | MONTICELLO 1101 | 4072 | MONTICELLO 1101666 | 1.9089 | 254.7513 | 12.8301 | 0 | 12.8301 | 0 | 1036 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 1 | 1894 |  | 343 | 227 | 1894 | 343 | 227 | 640.37 | 0.0074933 | 0.00534 | 816 | 0.85521 | 0.0097183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.85521 | 26.734 | 26.734 | 0%
Central Valley | FR_Fresno | KERCKHOFF 1101 | 8245 | KERCKHOFF 1101R308 | 0.87726 | 104.4663 | 3.7227 | 0 | 3.7227 | 0 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 1 | 299 |  | 56 | 38 | 299 | 56 | 38 | 103.63 | 0.0083975 | 0.00098 | 817 | 0.24214 | 0.0096857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.24214 | 15.0427 | 15.0427 | 0%
Bay Area | NB_North Bay | MONTICELLO 1101 | 5206 | MONTICELLO 110137384 | 1.8063 | 192.2782 | 6.5348 | 0 | 6.5348 | 0 | 844 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 1 | 1545 |  | 281 | 186 | 1545 | 281 | 186 | 524.02 | 0.0093943 | 0.00549 | 818 | 0.41259 | 0.0095951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.41259 | 43.0002 | 43.0002 | 0%
Central Valley | YO_Yosemite | MARIPOSA 2101 | 876 | MARIPOSA 210110240 | 9.7755 | 526.3988 | 19.7979 | 10.6568 | 9.1411 | 19.6866 | 3200 | 5348 | 1659 | 1538 | 981 | 904 | 0 | 778 | 0.005625 | 5381 |  | 1665 | 1542 | 33 | 684 | 638 | 940.05 | 0.018571 | 0.02641 | 819 | 2.2858 | 0.0095641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 1.0554 | 74.8269 | 84.0998 | 53.83%
Central Coast | LP_Los Padres | MESA 1101 | 5657 | MESA 11016113 | 0.46808 | 39.527 | 1.8504 | 0 | 1.8504 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 1 | 18 |  | 5 | 4 | 18 | 5 | 4 | 8.47 | 0.011842 | 0.00012 | 820 | 0.047802 | 0.0095603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.047802 | 2.7021 | 2.7021 | 0%
Sierra | SI_Sierra | NARROWS 2102 | 1212 | NARROWS 2102circuit_breaker | 6.5796 | 564.7696 | 22.935 | 20.0919 | 2.8432 | 21.3877 | 1550 | 5928 | 3434 | 2901 | 3309 | 2798 | 0 | 812 | 0.067467 | 6119 |  | 3469 | 2924 | 191 | 160 | 126 | 236.39 | 0.01165 | 0.00388 | 821 | 2.229 | 0.0095256 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.27632 | 56.275 | 151.2533 | 87.6%
North Coast | HU_Humboldt | WILLITS 1103 | 4055 | WILLITS 1103538 | 1.4442 | 143.8869 | 5.6585 | 0 | 5.6585 | 0 | 1813 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 1 | 3305 |  | 598 | 395 | 3305 | 598 | 395 | 1116.71 | 0.010037 | 0.01248 | 822 | 0.59683 | 0.0094734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 0.59683 | 105.6813 | 105.6813 | 0%
North Coast | HU_Humboldt | WILLITS 1104 | 5091 | WILLITS 1104504 | 8.4521 | 541.4149 | 23.0682 | 18.097 | 4.9712 | 23.0682 | 11056 | 28973 | 4064 | 2469 | 3654 | 2192 | 0 | 1060 | 0 | 28973 |  | 4064 | 2469 | 0 | 410 | 277 | 561.7 | 0.015611 | 0.01331 | 823 | 2.7258 | 0.0094647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 0.58742 | 82.4749 | 176.1734 | 78.45%
North Valley | NV_North Valley | CHALLENGE 1101 | 5679 | CHALLENGE 11015460 | 2.3172 | 256.4077 | 11.393 | 0 | 11.393 | 0 | 8415 | 0 | 0 | 0 | 0 | 0 | 0 | 262 | 1 | 15294 |  | 2760 | 1819 | 15294 | 2760 | 1819 | 5157.66 | 0.0090372 | 0.05187 | 824 | 1.7545 | 0.0094328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 1.7545 | 242.2542 | 242.2542 | 0%
North Valley | NV_North Valley | KANAKA 1101 | 9108 | KANAKA 1101circuit_breaker | 0.70283 | 84.3378 | 3.7604 | 0 | 3.7604 | 0 | 580 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 1 | 1066 |  | 194 | 129 | 1066 | 194 | 129 | 361.72 | 0.0083335 | 0.00336 | 825 | 0.69667 | 0.0094145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.69667 | 51.59 | 51.59 | 0%
North Coast | HU_Humboldt | WILLITS 1103 | 3148 | WILLITS 11032500 | 4.9995 | 580.8779 | 23.8377 | 0 | 23.8377 | 0 | 5438 | 0 | 0 | 0 | 0 | 0 | 0 | 415 | 1 | 9888 |  | 1785 | 1177 | 9888 | 1785 | 1177 | 3335.37 | 0.0086068 | 0.03195 | 826 | 1.6622 | 0.009338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 1.6622 | 74.8814 | 74.8814 | 0%
Central Valley | ST_Stockton | WEST POINT 1102 | 6874 | WEST POINT 110234416 | 3.0122 | 324.8959 | 12.8663 | 1.3326 | 11.5337 | 6.6044 | 5556 | 5589 | 1371 | 1005 | 1134 | 869 | 0 | 630 | 0.48669 | 10505 |  | 2259 | 1590 | 4916 | 1125 | 721 | 1983.69 | 0.0092714 | 0.02169 | 827 | 0.9618 | 0.0093379 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 0.86219 | 97.5401 | 175.5751 | 10.36%
Sierra | SI_Sierra | APPLE HILL 2102 | 4943 | APPLE HILL 210251792 | 2.2271 | 217.0736 | 9.3684 | 0.063636 | 9.3045 | 5.6956 | 2582 | 716 | 515 | 335 | 0 | 0 | 0 | 351 | 0.39203 | 2559 |  | 848 | 555 | 1843 | 848 | 555 | 1327.63 | 0.01026 | 0.01809 | 828 | 1.2026 | 0.0093223 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 1.1944 | 91.1383 | 90.5173 | 0.6793%
North Coast | HU_Humboldt | FRUITLAND 1142 | 7155 | FRUITLAND 114263170 | 5.3837 | 239.0843 | 11.6837 | 0 | 11.6837 | 0 | 5927 | 0 | 0 | 0 | 0 | 0 | 0 | 207 | 1 | 10776 |  | 1945 | 1282 | 10776 | 1945 | 1282 | 3634.49 | 0.022518 | 0.09107 | 829 | 0.19563 | 0.0093157 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 3. >20 - 30% | 1. <= 10% | 0.19563 | 166.4711 | 166.4711 | 0%
North Coast | HU_Humboldt | LUCERNE 1106 | 2379 | CLEAR LAKE 11011302 | 0.028578 | 23.6497 | 0.85587 | 0 | 0.85587 | 0 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1 | 415 |  | 77 | 52 | 415 | 77 | 52 | 142.84 | 0.0012084 | 0.00019 | 830 | 0.95848 | 0.0093057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.95848 | 89.9668 | 89.9668 | 0%
Central Valley | YO_Yosemite | CURTIS 1703 | 1261 | CURTIS 17039180 | 10.3509 | 1490.6808 | 58.6381 | 47.6953 | 10.9428 | 58.1455 | 3079 | 5966 | 773 | 401 | 657 | 365 | 0 | 1490 | 0.0084009 | 6013 |  | 782 | 407 | 47 | 125 | 42 | 175.48 | 0.0069437 | 0.0018 | 831 | 3.9536 | 0.0093027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.73781 | 11.423 | 13.336 | 81.34%
North Coast | HU_Humboldt | BRIDGEVILLE 1102 | 8365 | BRIDGEVILLE 110237486 | 1.9466 | 239.0679 | 10.1193 | 0 | 10.1193 | 0 | 5743 | 0 | 0 | 0 | 0 | 0 | 0 | 167 | 1 | 10441 |  | 1885 | 1243 | 10441 | 1885 | 1243 | 3522.14 | 0.0081424 | 0.03192 | 832 | 0.89087 | 0.0092799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 0.89087 | 186.2774 | 186.2774 | 0%
Central Coast | LP_Los Padres | ATASCADERO 1103 | 4680 | ATASCADERO 1103A88 | 0.4333 | 35.0743 | 1.6572 | 0 | 1.6572 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 1 | 179 |  | 34 | 24 | 179 | 34 | 24 | 62.69 | 0.012354 | 0.00087 | 833 | 0.083425 | 0.0092694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.083425 | 20.5166 | 20.5166 | 0%
North Coast | HU_Humboldt | MENDOCINO 1101 | 290 | MENDOCINO 110131322 | 1.3527 | 134.7937 | 5.9608 | 0 | 5.9608 | 0 | 811 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 1 | 1485 |  | 270 | 179 | 1485 | 270 | 179 | 503.55 | 0.010035 | 0.00563 | 834 | 0.55493 | 0.0092488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.55493 | 45.296 | 45.296 | 0%
North Coast | SO_Sonoma | MIRABEL 1102 | 6721 | MIRABEL 1102334 | 1.0298 | 117.7285 | 5.7778 | 0.20265 | 5.575 | 5.7307 | 2083 | 253 | 253 | 83 | 74 | 0 | 0 | 259 | 0.0081621 | 284 |  | 259 | 87 | 31 | 185 | 87 | 256.24 | 0.0087472 | 0.00336 | 835 | 0.72948 | 0.009234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.70387 | 33.1839 | 44.8264 | 3.507%
North Coast | SO_Sonoma | MOLINO 1102 | 3425 | MOLINO 1102396 | 4.8636 | 422.7933 | 16.7932 | 1.4165 | 15.3767 | 16.4127 | 4074 | 395 | 366 | 152 | 52 | 4 | 0 | 844 | 0.022658 | 563 |  | 396 | 172 | 168 | 344 | 168 | 486.4 | 0.011503 | 0.00823 | 837 | 1.916 | 0.0092116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 1.7544 | 22.3715 | 23.581 | 8.435%
North Valley | NV_North Valley | KANAKA 1101 | 952 | KANAKA 110183288 | 3.4232 | 382.7763 | 17.1095 | 0 | 17.1095 | 0 | 8545 | 0 | 0 | 0 | 0 | 0 | 0 | 379 | 1 | 15530 |  | 2803 | 1847 | 15530 | 2803 | 1847 | 5237.81 | 0.0089431 | 0.05213 | 838 | 2.666 | 0.0091932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 2.666 | 163.8274 | 163.8274 | 0%
North Coast | HU_Humboldt | HARTLEY 1101 | 2538 | HARTLEY 110186876 | 0.81365 | 61.1892 | 3.7731 | 0 | 3.7731 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 1 | 441 |  | 81 | 55 | 441 | 81 | 55 | 150.66 | 0.013297 | 0.00224 | 839 | 0.29966 | 0.0090807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.29966 | 21.4677 | 21.4677 | 0%
North Coast | HU_Humboldt | LOW GAP 1101 | 1008 | LOW GAP 11012094 | 3.2253 | 335.5357 | 14.9405 | 0 | 14.9405 | 0 | 5487 | 0 | 0 | 0 | 0 | 0 | 0 | 291 | 1 | 9976 |  | 1801 | 1187 | 9976 | 1801 | 1187 | 3365.21 | 0.0096123 | 0.036 | 840 | 2.036 | 0.0090491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 2.036 | 120.5446 | 120.5446 | 0%
Bay Area | NB_North Bay | ALTO 1124 | 2774 | ALTO 1124432 | 1.579 | 188.5826 | 10.1867 | 0 | 10.1867 | 0 | 3134 | 0 | 0 | 0 | 0 | 0 | 0 | 334 | 1 | 5704 |  | 1031 | 680 | 5704 | 1031 | 680 | 1925.83 | 0.0083731 | 0.01795 | 841 | 0.81193 | 0.0090214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 0.81193 | 101.21 | 101.21 | 0%
North Coast | HU_Humboldt | LOW GAP 1101 | 7830 | LOW GAP 110186816 | 1.0965 | 112.3697 | 4.7818 | 0 | 4.7818 | 0 | 1405 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 1 | 2564 |  | 464 | 307 | 2564 | 464 | 307 | 866.44 | 0.0097579 | 0.00941 | 842 | 0.69276 | 0.0089969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.69276 | 97.0342 | 97.0342 | 0%
Central Valley | ST_Stockton | WEST POINT 1101 | 4365 | WEST POINT 1101circuit_breaker | 1.133 | 112.7863 | 4.9722 | 0.015909 | 4.9562 | 0.086932 | 676 | 90 | 16 | 13 | 2 | 1 | 0 | 163 | 0.98252 | 1308 |  | 238 | 160 | 1218 | 236 | 159 | 432.94 | 0.010046 | 0.00493 | 843 | 0.49477 | 0.0089959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.49319 | 47.6166 | 47.8665 | 0.32%
North Valley | NV_North Valley | CHALLENGE 1101 | 5453 | CHALLENGE 1101circuit_breaker | 3.3036 | 367.6336 | 16.1833 | 0 | 16.1833 | 0 | 11049 | 0 | 0 | 0 | 0 | 0 | 0 | 366 | 1 | 20077 |  | 3623 | 2387 | 20077 | 3623 | 2387 | 6770.44 | 0.008986 | 0.0677 | 844 | 2.4502 | 0.0089751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 2.4502 | 223.8723 | 223.8723 | 0%
Sierra | SI_Sierra | BROWNS VALLEY 1101 | 66 | BROWNS VALLEY 110197188 | 1.7571 | 130.4733 | 5.5653 | 0 | 5.5653 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 1 | 947 |  | 173 | 115 | 947 | 173 | 115 | 322.24 | 0.013467 | 0.00484 | 845 | 0.70785 | 0.0089602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.70785 | 31.0852 | 31.0852 | 0%
North Valley | NV_North Valley | PANORAMA 1101 | 2781 | PANORAMA 11019092 | 3.0365 | 196.0638 | 9.9892 | 9.8265 | 0.16269 | 9.9892 | 41 | 885 | 29 | 21 | 24 | 16 | 0 | 574 | 0 | 885 |  | 29 | 21 | 0 | 5 | 5 | 6.85 | 0.015487 | 0.00016 | 846 | 0.54628 | 0.0089554 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.008897 | 30.7334 | 2.9031 | 98.37%
Sierra | SI_Sierra | NARROWS 2101 | 5439 | NARROWS 2101circuit_breaker | 3.2008 | 297.5738 | 13.5328 | 0.057576 | 13.4752 | 0.057576 | 317 | 0 | 0 | 0 | 0 | 0 | 0 | 203 | 0.99575 | 585 |  | 108 | 72 | 585 | 108 | 72 | 200.61 | 0.010756 | 0.00242 | 847 | 0.86756 | 0.0089439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.86386 | 8.0147 | 7.9806 | 0.4255%
Central Coast | LP_Los Padres | TEMPLETON 2110 | 1837 | TEMPLETON 2110R06 | 1.7547 | 132.7847 | 6.4161 | 0 | 6.4161 | 2.6919 | 1054 | 50 | 47 | 18 | 47 | 18 | 0 | 231 | 0.58045 | 1168 |  | 250 | 152 | 1118 | 203 | 134 | 378.73 | 0.013215 | 0.00558 | 848 | 0.51773 | 0.0089264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.51773 | 31.6392 | 38.9645 | 0%
Central Coast | CC_Central Coast | POINT MORETTI 1101 | 5523 | POINT MORETTI 11015104 | 0.06682 | 38.0119 | 2.0142 | 0 | 2.0142 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1 | 29 |  | 7 | 6 | 29 | 7 | 6 | 12.2 | 0.0017579 | 3e-05 | 849 | 0.01784 | 0.00892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.01784 | 3.4753 | 3.4753 | 0%
North Coast | HU_Humboldt | GARBERVILLE 1101 | 1477 | GARBERVILLE 11011750 | 3.1879 | 337.3069 | 14.8254 | 0 | 14.8254 | 0 | 6908 | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 1 | 12557 |  | 2267 | 1494 | 12557 | 2267 | 1494 | 4235.92 | 0.0094512 | 0.04455 | 850 | 1.7905 | 0.0089078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 1.7905 | 152.9135 | 152.9135 | 0%
Sierra | SI_Sierra | NARROWS 2102 | 1703 | NARROWS 21022220 | 7.5178 | 740.9119 | 27.9983 | 24.8693 | 3.129 | 27.6905 | 3719 | 8261 | 4496 | 3769 | 4289 | 3605 | 0 | 927 | 0.010992 | 8335 |  | 4509 | 3778 | 74 | 220 | 173 | 308.06 | 0.010147 | 0.00464 | 851 | 2.9277 | 0.0088988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.32719 | 70.3105 | 161.0455 | 88.82%
Sierra | SI_Sierra | NARROWS 2105 | 4543 | NARROWS 210551582 | 1.8113 | 207.9696 | 9.0943 | 0 | 9.0943 | 0 | 622 | 0 | 0 | 0 | 0 | 0 | 0 | 214 | 1 | 1142 |  | 208 | 138 | 1142 | 208 | 138 | 387.74 | 0.0087093 | 0.00377 | 852 | 1.1483 | 0.0088328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 1.1483 | 22.8714 | 22.8714 | 0%
Sierra | SI_Sierra | APPLE HILL 2102 | 2628 | APPLE HILL 210277546 | 8.624 | 952.2809 | 42.2199 | 4.4294 | 37.7905 | 21.2574 | 8353 | 4255 | 1918 | 1630 | 2 | 2 | 0 | 1384 | 0.49651 | 11793 |  | 3278 | 2527 | 7538 | 3276 | 2525 | 5166.54 | 0.0090562 | 0.06169 | 853 | 4.6133 | 0.0088039 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 4.1293 | 86.6884 | 77.6411 | 10.49%
Central Valley | YO_Yosemite | BEAR VALLEY 2105 | 8930 | BEAR VALLEY 21054170 | 0.58921 | 184.5364 | 7.3614 | 0 | 7.3614 | 0 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 1 | 297 |  | 56 | 38 | 297 | 56 | 38 | 103.45 | 0.0031929 | 0.00037 | 855 | 0.31398 | 0.0087216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.31398 | 7.6073 | 7.6073 | 0%
North Valley | NV_North Valley | WYANDOTTE 1103 | 4789 | WYANDOTTE 11031976 | 4.9481 | 570.8938 | 23.0348 | 0 | 23.0348 | 0 | 10629 | 0 | 0 | 0 | 0 | 0 | 0 | 526 | 1 | 19314 |  | 3485 | 2297 | 19314 | 3485 | 2297 | 6512.71 | 0.0086673 | 0.06281 | 856 | 3.4029 | 0.008703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 3.4029 | 151.2925 | 151.2925 | 0%
Central Valley | YO_Yosemite | OAKHURST 1103 | 5633 | OAKHURST 11035732 | 0.99757 | 78.7071 | 3.7489 | 0.20549 | 3.5434 | 2.5352 | 402 | 173 | 71 | 38 | 69 | 37 | 0 | 171 | 0.32373 | 413 |  | 115 | 67 | 240 | 46 | 30 | 84.62 | 0.012674 | 0.00121 | 857 | 0.33912 | 0.0086954 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.32053 | 12.982 | 30.676 | 5.481%
North Coast | HU_Humboldt | WILLITS 1103 | 7594 | WILLITS 110337506 | 3.2608 | 314.0689 | 11.9182 | 0 | 11.9182 | 0 | 4911 | 0 | 0 | 0 | 0 | 0 | 0 | 197 | 1 | 8930 |  | 1613 | 1063 | 8930 | 1613 | 1063 | 3013.51 | 0.010382 | 0.03482 | 858 | 1.5375 | 0.0086865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 1.5375 | 135.3394 | 135.3394 | 0%
Bay Area | NB_North Bay | PUEBLO 2103 | 4753 | PUEBLO 21031970 | 0.84603 | 91.6458 | 3.6718 | 0 | 3.6718 | 0 | 613 | 0 | 0 | 0 | 0 | 0 | 0 | 126 | 1 | 1125 |  | 205 | 136 | 1125 | 205 | 136 | 382.1 | 0.0092315 | 0.00394 | 859 | 0.41542 | 0.0086545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.41542 | 55.8312 | 55.8312 | 0%
North Coast | HU_Humboldt | LUCERNE 1106 | 4359 | LUCERNE 1106526 | 2.4057 | 180.1932 | 9.0733 | 0 | 9.0733 | 0 | 656 | 1 | 1 | 1 | 0 | 0 | 0 | 205 | 1 | 1205 |  | 220 | 146 | 1204 | 220 | 146 | 409.76 | 0.013351 | 0.00611 | 860 | 0.906 | 0.0086285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.906 | 24.247 | 24.247 | 0%
North Valley | NV_North Valley | MC ARTHUR 1101 | 4292 | MC ARTHUR 110138998 | 1.8923 | 181.4133 | 10.0894 | 0 | 10.0894 | 0 | 249 | 0 | 0 | 0 | 0 | 0 | 0 | 222 | 1 | 464 |  | 86 | 57 | 464 | 86 | 57 | 159.58 | 0.010431 | 0.00187 | 861 | 0.19773 | 0.0085969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.19773 | 8.5238 | 8.5238 | 0%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1107 | 4945 | SAN LUIS OBISPO 1107V60 | 2.9464 | 415.5674 | 15.5968 | 0.41951 | 15.1773 | 0.96913 | 1790 | 379 | 96 | 68 | 74 | 54 | 0 | 246 | 0.93786 | 3439 |  | 650 | 434 | 3060 | 576 | 380 | 1064.52 | 0.00709 | 0.00849 | 862 | 1.5598 | 0.0085705 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 3. >20 - 30% | 5. >40 - 50% | 1.5179 | 37.9515 | 41.6753 | 2.69%
Central Valley | ST_Stockton | TIGER CREEK 0201 | 9511 | TIGER CREEK 0201circuit_breaker | 0.71803 | 102.1359 | 4.057 | 2.3968 | 1.6602 | 3.8136 | 1427 | 2301 | 517 | 482 | 427 | 402 | 0 | 115 | 0.059988 | 2457 |  | 545 | 501 | 156 | 118 | 99 | 175.7 | 0.0070301 | 0.00172 | 863 | 0.19705 | 0.0085676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.08064 | 71.0746 | 134.3355 | 59.08%
North Valley | NV_North Valley | PIT NO 5 1101 | 9487 | PIT NO 5 11011618 | 1.161 | 136.5619 | 5.8269 | 0 | 5.8269 | 0 | 2436 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 1 | 4436 |  | 802 | 529 | 4436 | 802 | 529 | 1497.98 | 0.008502 | 0.01418 | 864 | 0.41889 | 0.0085488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 0.41889 | 137.6377 | 137.6377 | 0%
Central Valley | ST_Stockton | OLETA 1101 | 8869 | OLETA 1101circuit_breaker | 0.27498 | 54.6607 | 2.4087 | 1.7763 | 0.63239 | 2.4087 | 30 | 101 | 28 | 9 | 0 | 0 | 0 | 36 | 0 | 101 |  | 28 | 9 | 0 | 28 | 9 | 38.36 | 0.0050307 | 0.00029 | 865 | 0.17051 | 0.0085256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.044767 | 44.2767 | 11.6245 | 73.75%
Central Valley | YO_Yosemite | SAN JOAQUIN NO3 1102 | 5162 | SAN JOAQUIN #3 1102circuit_breaker | 1.7824 | 202.816 | 9.2354 | 0.10928 | 9.1261 | 0.51553 | 1108 | 66 | 28 | 25 | 19 | 16 | 0 | 194 | 0.94418 | 1977 |  | 375 | 254 | 1911 | 356 | 238 | 659.71 | 0.0087883 | 0.00651 | 866 | 1.1462 | 0.0084906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 1.1327 | 39.0088 | 40.6046 | 1.183%
North Valley | NV_North Valley | PIT NO 5 1101 | 8995 | PIT NO 5 1101circuit_breaker | 0.11304 | 24.2005 | 1.2856 | 0 | 1.2856 | 0 | 506 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1 | 931 |  | 170 | 113 | 931 | 170 | 113 | 316.69 | 0.0046708 | 0.00165 | 867 | 0.067873 | 0.0084841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.067873 | 132.2334 | 132.2334 | 0%
North Valley | NV_North Valley | KESWICK 1101 | 3208 | KESWICK 11019712 | 4.0273 | 390.784 | 18.0744 | 15.0691 | 3.0053 | 17.3807 | 1013 | 3040 | 730 | 657 | 678 | 608 | 0 | 1135 | 0.038383 | 3111 |  | 743 | 666 | 71 | 65 | 58 | 95.44 | 0.010306 | 0.00139 | 868 | 2.0674 | 0.0084732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.34376 | 21.6284 | 41.1078 | 83.37%
Central Coast | SJ_San Jose | SWIFT 2110 | 2219 | SWIFT 2110XR366 | 1.5375 | 199.5621 | 9.6286 | 0 | 9.6286 | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 1 | 330 |  | 62 | 41 | 330 | 62 | 41 | 114.64 | 0.0077042 | 0.00099 | 869 | 0.64391 | 0.0084724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.64391 | 6.4392 | 6.4392 | 0%
Sierra | SI_Sierra | PENRYN 1107 | 3501 | PENRYN 1107346 | 2.7886 | 245.6928 | 13.1625 | 0.64773 | 12.5146 | 0.67045 | 2074 | 67 | 8 | 5 | 7 | 4 | 0 | 327 | 0.94906 | 3653 |  | 657 | 433 | 3586 | 650 | 429 | 1213.24 | 0.01135 | 0.01534 | 870 | 1.778 | 0.0084667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 1.6905 | 51.9394 | 49.9145 | 4.921%
Sierra | SI_Sierra | NARROWS 2102 | 3438 | NARROWS 21022718 | 0.28945 | 18.486 | 0.89848 | 0.89848 | 0 | 0.89848 | 112 | 362 | 185 | 164 | 183 | 162 | 0 | 41 | 0 | 362 |  | 185 | 164 | 0 | 2 | 2 | 2.74 | 0.015658 | 7e-05 | 871 | 0.067495 | 0.0084369 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0 | 0 | 205.9022 | 100%
North Coast | SO_Sonoma | LAKEVILLE 1102 | 6929 | LAKEVILLE 11023341 | 1.2343 | 196.6068 | 8.3907 | 7.0462 | 1.3445 | 8.3907 | 233 | 474 | 194 | 76 | 163 | 65 | 0 | 233 | 0 | 474 |  | 194 | 76 | 0 | 31 | 11 | 42.47 | 0.0062778 | 0.0004 | 872 | 0.43614 | 0.0083873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.069886 | 23.0568 | 23.1208 | 83.98%
North Coast | SO_Sonoma | COTATI 1105 | 7822 | COTATI 1105893 | 0.011635 | 1.4007 | 0.19413 | 0.13239 | 0.061742 | 0.19413 | 35 | 83 | 11 | 3 | 8 | 2 | 0 | 6 | 0 | 83 |  | 11 | 3 | 0 | 3 | 1 | 4.11 | 0.0083068 | 5e-05 | 873 | 0.0083717 | 0.0083717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.0026626 | 48.589 | 56.6634 | 68.2%
Sierra | SI_Sierra | SHINGLE SPRINGS 2108 | 3023 | SHINGLE SPRINGS 210819622 | 1.3567 | 84.5246 | 5.2542 | 0 | 5.2542 | 0 | 931 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 1 | 1703 |  | 309 | 205 | 1703 | 309 | 205 | 576.6 | 0.01605 | 0.01031 | 874 | 0.54953 | 0.0083262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 0.54953 | 58.8105 | 58.8105 | 0%
Central Valley | ST_Stockton | NORTH BRANCH 1101 | 6103 | NORTH BRANCH 110113496 | 1.1976 | 84.6251 | 4.257 | 0 | 4.257 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 1 | 123 |  | 24 | 17 | 123 | 24 | 17 | 43.95 | 0.014152 | 0.00071 | 875 | 0.091309 | 0.0083008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.091309 | 5.6378 | 5.6378 | 0%
North Coast | SO_Sonoma | DUNBAR 1101 | 7335 | DUNBAR 11014817 | 0.45489 | 80.8385 | 3.5964 | 0.76117 | 2.8352 | 3.4377 | 444 | 265 | 252 | 134 | 68 | 27 | 0 | 226 | 0.044131 | 301 |  | 259 | 138 | 36 | 191 | 111 | 264.91 | 0.0056271 | 0.00223 | 876 | 0.33905 | 0.0082695 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.26729 | 67.3667 | 72.0164 | 21.16%
Central Valley | ST_Stockton | WEST POINT 1102 | 2067 | WEST POINT 1102circuit_breaker | 2.6114 | 373.2946 | 16.8348 | 2.0312 | 14.8036 | 8.5919 | 6159 | 5363 | 1566 | 1223 | 1148 | 910 | 0 | 941 | 0.48964 | 10845 |  | 2556 | 1875 | 5482 | 1408 | 965 | 2422.34 | 0.0069955 | 0.02048 | 877 | 1.5044 | 0.008266 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 1.3229 | 95.112 | 151.8279 | 12.07%
Central Valley | FR_Fresno | AUBERRY 1101 | 7345 | AUBERRY 110149122 | 0.87525 | 73.2515 | 3.1992 | 0 | 3.1992 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 113 | 1 | 230 |  | 43 | 30 | 230 | 43 | 30 | 79.61 | 0.011949 | 0.00107 | 878 | 0.016501 | 0.0082504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.016501 | 13.4407 | 13.4407 | 0%
North Coast | SO_Sonoma | MONTE RIO 1113 | 6120 | MONTE RIO 11131991 | 1.5026 | 173.1512 | 7.535 | 0 | 7.535 | 3.9273 | 1002 | 5 | 5 | 4 | 3 | 3 | 0 | 247 | 0.4788 | 882 |  | 164 | 109 | 877 | 161 | 106 | 299.5 | 0.0086778 | 0.00291 | 879 | 0.72411 | 0.0082285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.72411 | 21.3668 | 21.765 | 0%
Central Valley | YO_Yosemite | MARIPOSA 2102 | 7614 | MARIPOSA 2102circuit_breaker | 0.45592 | 108.2837 | 4.0267 | 0 | 4.0267 | 0 | 248 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 1 | 463 |  | 85 | 57 | 463 | 85 | 57 | 158.12 | 0.0042104 | 0.00074 | 880 | 0.39332 | 0.0081941 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.39332 | 21.1091 | 21.1091 | 0%
Central Valley | ST_Stockton | OLETA 1101 | 3488 | OLETA 110113478 | 1.9449 | 276.5205 | 12.6585 | 4.4146 | 8.2441 | 8.9159 | 701 | 687 | 289 | 190 | 9 | 4 | 0 | 294 | 0.29566 | 1067 |  | 358 | 236 | 380 | 349 | 232 | 512.33 | 0.0070335 | 0.0051 | 881 | 0.88359 | 0.0081063 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.57546 | 42.3332 | 28.2813 | 34.87%
North Coast | HU_Humboldt | GARCIA 0401 | 5722 | GARCIA 0401666 | 0.98547 | 54.4645 | 2.4335 | 0 | 2.4335 | 0 | 1294 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 1 | 2362 |  | 428 | 283 | 2362 | 428 | 283 | 798.94 | 0.018094 | 0.0161 | 882 | 0.0081045 | 0.0081045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 0.0081045 | 175.8767 | 175.8767 | 0%
North Valley | NV_North Valley | ORO FINO 1102 | 4035 | ORO FINO 11022096 | 2.3729 | 311.7709 | 14.4549 | 0 | 14.4549 | 3.492 | 10524 | 126 | 121 | 84 | 19 | 9 | 0 | 735 | 0.75842 | 14630 |  | 2738 | 1809 | 14504 | 2719 | 1800 | 5030.39 | 0.007611 | 0.04303 | 883 | 0.89108 | 0.0081008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 0.89108 | 188.102 | 189.4164 | 0%
North Valley | NV_North Valley | WYANDOTTE 1109 | 8909 | WYANDOTTE 110942650 | 0.14808 | 17.8851 | 0.41648 | 0.0018939 | 0.41458 | 0.095265 | 123 | 51 | 37 | 36 | 35 | 34 | 0 | 23 | 0.77126 | 233 |  | 71 | 59 | 182 | 36 | 25 | 65.7 | 0.0082795 | 0.00062 | 884 | 0.087234 | 0.0079304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.086837 | 86.8342 | 170.4775 | 0.4548%
North Valley | NV_North Valley | WHITMORE 1101 | 2318 | WHITMORE 11011594 | 4.0048 | 541.5296 | 22.6652 | 0 | 22.6652 | 0 | 6482 | 0 | 0 | 0 | 0 | 0 | 0 | 482 | 1 | 11783 |  | 2127 | 1402 | 11783 | 2127 | 1402 | 3974.46 | 0.0073954 | 0.03271 | 885 | 2.2253 | 0.0078911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 2.2253 | 93.8445 | 93.8445 | 0%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1104 | 4507 | SAN LUIS OBISPO 1104V40 | 2.8707 | 365.4012 | 14.2377 | 0.86269 | 13.3748 | 0.90758 | 304 | 80 | 6 | 0 | 6 | 0 | 0 | 279 | 0.93626 | 608 |  | 103 | 65 | 528 | 97 | 65 | 180.41 | 0.0078562 | 0.00158 | 886 | 0.6446 | 0.0078609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.60553 | 7.2524 | 7.2343 | 6.059%
Sierra | SI_Sierra | WISE 1101 | 4566 | WISE 1101circuit_breaker | 1.9534 | 131.3664 | 6.3538 | 0.12689 | 6.2269 | 0.16439 | 673 | 2 | 0 | 0 | 0 | 0 | 0 | 183 | 0.97413 | 1204 |  | 219 | 145 | 1202 | 219 | 145 | 408.21 | 0.01487 | 0.00677 | 887 | 0.4472 | 0.0078457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.43827 | 35.17 | 34.4676 | 1.997%
North Valley | NV_North Valley | PIT NO 1 1101 | 3522 | PIT NO 1 11011552 | 2.3308 | 264.2095 | 14.4879 | 0 | 14.4879 | 0 | 3292 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 1 | 5990 |  | 1082 | 714 | 5990 | 1082 | 714 | 2021.44 | 0.0088218 | 0.01985 | 888 | 1.0695 | 0.0078069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 1.0695 | 74.6831 | 74.6831 | 0%
Bay Area | NB_North Bay | ALTO 1125 | 5007 | ALTO 1125902 | 1.8209 | 252.5972 | 11.8733 | 0 | 11.8733 | 0 | 2392 | 0 | 0 | 0 | 0 | 0 | 0 | 242 | 1 | 4356 |  | 788 | 520 | 4356 | 788 | 520 | 1471.6 | 0.0072087 | 0.01181 | 889 | 1.2403 | 0.0078006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 1.2403 | 66.3674 | 66.3674 | 0%
North Coast | SO_Sonoma | DUNBAR 1103 | 5259 | DUNBAR 1103534 | 3.0219 | 381.1398 | 16.6758 | 5.835 | 10.8407 | 14.4172 | 2934 | 633 | 560 | 368 | 237 | 86 | 0 | 694 | 0.13544 | 1356 |  | 691 | 454 | 723 | 454 | 368 | 687.05 | 0.0079285 | 0.00748 | 890 | 1.5736 | 0.0077899 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 1.023 | 41.8791 | 41.4374 | 34.99%
Sierra | SI_Sierra | BANGOR 1101 | 1768 | BANGOR 11011804 | 5.8672 | 964.7329 | 41.1509 | 16.9464 | 24.2045 | 35.4019 | 6408 | 8294 | 3253 | 2894 | 2489 | 2207 | 0 | 1292 | 0.13971 | 9921 |  | 3547 | 3088 | 1627 | 1058 | 881 | 1595.89 | 0.0060816 | 0.01338 | 891 | 4.6192 | 0.0077896 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 2.717 | 43.7108 | 86.1949 | 41.18%
North Coast | HU_Humboldt | KONOCTI 1102 | 6685 | KONOCTI 110264464 | 0.34792 | 40.5441 | 2.1581 | 1.2282 | 0.92992 | 2.1581 | 409 | 730 | 205 | 145 | 149 | 99 | 0 | 106 | 0 | 730 |  | 205 | 145 | 0 | 56 | 46 | 76.72 | 0.0085812 | 0.001 | 892 | 0.27201 | 0.0077718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.11721 | 60.22 | 94.989 | 56.91%
Bay Area | NB_North Bay | PUEBLO 2102 | 2135 | PUEBLO 2102circuit_breaker | 0.2409 | 10.3747 | 0.85284 | 0.73371 | 0.11913 | 0.85284 | 2 | 10 | 2 | 0 | 0 | 0 | 0 | 17 | 0 | 10 |  | 2 | 0 | 0 | 2 | 0 | 2.74 | 0.02322 | 0.0001 | 893 | 0.031073 | 0.0077682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.0043404 | 16.7886 | 2.3451 | 86.03%
North Coast | HU_Humboldt | GARBERVILLE 1102 | 4073 | GARBERVILLE 11021510 | 1.9724 | 257.9459 | 13.0328 | 0 | 13.0328 | 0 | 4711 | 0 | 0 | 0 | 0 | 0 | 0 | 441 | 1 | 8567 |  | 1547 | 1020 | 8567 | 1547 | 1020 | 2890.42 | 0.0076466 | 0.0246 | 894 | 1.412 | 0.0077156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 1.412 | 118.7008 | 118.7008 | 0%
North Coast | SO_Sonoma | DUNBAR 1102 | 949 | DUNBAR 1102903030 | 0.24802 | 48.5873 | 1.84 | 0 | 1.84 | 0 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 1 | 615 |  | 113 | 75 | 615 | 113 | 75 | 210.16 | 0.0051047 | 0.0012 | 895 | 0.18483 | 0.0077012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.18483 | 61.4143 | 61.4143 | 0%
North Coast | HU_Humboldt | BRIDGEVILLE 1101 | 6896 | BRIDGEVILLE 110137484 | 1.2784 | 170.7458 | 7.903 | 5.9879 | 1.915 | 7.903 | 2335 | 5573 | 1147 | 615 | 935 | 487 | 0 | 210 | 0 | 5573 |  | 1147 | 615 | 0 | 212 | 128 | 290.44 | 0.0074873 | 0.0033 | 896 | 0.77693 | 0.0076923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.18825 | 110.7072 | 145.1342 | 75.77%
Sierra | SI_Sierra | NARROWS 2102 | 4730 | NARROWS 210276952 | 0.29487 | 31.643 | 1.1585 | 0.79697 | 0.36155 | 0.81496 | 177 | 304 | 232 | 207 | 229 | 205 | 0 | 47 | 0.29655 | 403 |  | 250 | 219 | 99 | 21 | 14 | 37.68 | 0.0093186 | 0.00041 | 898 | 0.25262 | 0.0076551 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.078838 | 58.0828 | 215.7921 | 68.79%
North Coast | HU_Humboldt | REDBUD 1101 | 2439 | REDBUD 1101circuit_breaker | 1.9056 | 210.8265 | 11.0981 | 4.0729 | 7.025 | 11.0979 | 856 | 2178 | 567 | 273 | 119 | 38 | 0 | 565 | 1.7065e-05 | 2178 |  | 567 | 273 | 0 | 448 | 235 | 613.76 | 0.0090388 | 0.00842 | 899 | 1.0178 | 0.007653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.64429 | 63.7722 | 51.0898 | 36.7%
Central Coast | SJ_San Jose | LLAGAS 2101 | 9177 | LLAGAS 21014523 | 0.10385 | 17.6776 | 1.3127 | 0 | 1.3127 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 1 | 118 |  | 23 | 16 | 118 | 23 | 16 | 42.13 | 0.0058744 | 0.00028 | 900 | 0.06098 | 0.0076224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.06098 | 17.5213 | 17.5213 | 0%
North Coast | HU_Humboldt | GARBERVILLE 1101 | 7191 | GARBERVILLE 110197300 | 1.9605 | 291.8202 | 14.1027 | 0 | 14.1027 | 0 | 5654 | 0 | 0 | 0 | 0 | 0 | 0 | 254 | 1 | 10280 |  | 1856 | 1223 | 10280 | 1856 | 1223 | 3467.92 | 0.0067181 | 0.02593 | 901 | 1.6204 | 0.0076073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 1.6204 | 131.6065 | 131.6065 | 0%
North Coast | HU_Humboldt | POINT ARENA 1101 | 5072 | POINT ARENA 110137426 | 0.054338 | 11.3266 | 0.60341 | 0 | 0.60341 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 59 |  | 13 | 9 | 59 | 13 | 9 | 23.12 | 0.0047974 | 0.00013 | 902 | 0.03786 | 0.0075719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.03786 | 21.5443 | 21.5443 | 0%
North Coast | SO_Sonoma | SALMON CREEK 1101 | 3097 | SALMON CREEK 1101194 | 1.1975 | 124.8688 | 7.2947 | 0 | 7.2947 | 0 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 1 | 784 |  | 143 | 95 | 784 | 143 | 95 | 266.47 | 0.0095904 | 0.00285 | 903 | 0.19646 | 0.0075562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.19646 | 19.6033 | 19.6033 | 0%
Central Valley | ST_Stockton | WEST POINT 1102 | 7359 | WEST POINT 11021369 | 1.7575 | 256.3449 | 9.9189 | 3.1784 | 6.7405 | 8.7053 | 2615 | 2991 | 886 | 661 | 715 | 519 | 0 | 270 | 0.12236 | 3574 |  | 991 | 730 | 583 | 276 | 211 | 430.59 | 0.0068558 | 0.00393 | 904 | 0.44494 | 0.0075413 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.30236 | 40.9463 | 99.9099 | 32.04%
Central Valley | KE_Kern | TEJON 1103 | 2844 | TEJON 11032280 | 0.14684 | 26.7464 | 2.1527 | 0 | 2.1527 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 1 | 16 |  | 5 | 4 | 16 | 5 | 4 | 8.29 | 0.0054901 | 6e-05 | 905 | 0.0075289 | 0.0075289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.0075289 | 2.3227 | 2.3227 | 0%
North Coast | HU_Humboldt | REDBUD 1101 | 38 | REDBUD 1101708166 | 2.3704 | 238.7843 | 9.1644 | 7.2223 | 1.942 | 9.1644 | 436 | 741 | 244 | 115 | 141 | 56 | 0 | 275 | 0 | 741 |  | 244 | 115 | 0 | 103 | 59 | 141.11 | 0.0099268 | 0.00213 | 906 | 0.52582 | 0.0075118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.11143 | 53.0369 | 26.6248 | 78.81%
North Coast | SO_Sonoma | MONTE RIO 1113 | 3660 | MONTE RIO 11131137 | 0.40579 | 51.0572 | 1.8169 | 0 | 1.8169 | 0.71439 | 870 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 0.6068 | 966 |  | 175 | 116 | 966 | 175 | 116 | 326.69 | 0.0079477 | 0.00289 | 907 | 0.34365 | 0.0074706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.34365 | 96.3202 | 96.3202 | 0%
Sierra | SI_Sierra | APPLE HILL 2102 | 4289 | APPLE HILL 210297982 | 1.6589 | 248.6887 | 9.639 | 0 | 9.639 | 0 | 5361 | 0 | 0 | 0 | 0 | 0 | 0 | 472 | 1 | 9748 |  | 1760 | 1160 | 9748 | 1760 | 1160 | 3288.52 | 0.0066707 | 0.02441 | 908 | 1.1695 | 0.0074491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 1.1695 | 182.5913 | 182.5913 | 0%
Central Coast | LP_Los Padres | MESA 1101 | 782 | MESA 1101M86 | 1.9727 | 283.0444 | 13.1199 | 0 | 13.1199 | 0 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 259 | 1 | 256 |  | 48 | 33 | 256 | 48 | 33 | 88.8 | 0.0069697 | 0.0007 | 909 | 0.8536 | 0.0074226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.8536 | 3.6586 | 3.6586 | 0%
North Coast | HU_Humboldt | WILLITS 1103 | 4380 | WILLITS 1103968 | 5.4078 | 670.6982 | 24.9973 | 0.041098 | 24.9564 | 0.12633 | 9887 | 236 | 42 | 27 | 42 | 27 | 0 | 558 | 0.99495 | 18112 |  | 3268 | 2153 | 17876 | 3226 | 2126 | 6028.46 | 0.008063 | 0.05409 | 910 | 2.6769 | 0.0074151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 2.6725 | 129.2652 | 130.7339 | 0.1644%
Sierra | SI_Sierra | PIKE CITY 1101 | 315 | PIKE CITY 11011730 | 1.6986 | 203.2511 | 9.046 | 0.027462 | 9.0186 | 4.421 | 4106 | 774 | 774 | 616 | 1 | 1 | 0 | 468 | 0.51127 | 4593 |  | 1464 | 1071 | 3819 | 1463 | 1070 | 2348.02 | 0.008357 | 0.02542 | 911 | 0.93378 | 0.0074109 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 0.93094 | 162.221 | 161.8391 | 0.3036%
North Coast | HU_Humboldt | GARBERVILLE 1102 | 5574 | GARBERVILLE 11026084 | 2.3465 | 349.7636 | 14.9278 | 0 | 14.9278 | 0 | 10842 | 0 | 0 | 0 | 0 | 0 | 0 | 429 | 1 | 19701 |  | 3555 | 2343 | 19701 | 3555 | 2343 | 6643.44 | 0.0067087 | 0.04959 | 912 | 1.9135 | 0.0073881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 1.9135 | 238.1456 | 238.1456 | 0%
North Valley | NV_North Valley | PIT NO 7 1101 | 7501 | PIT NO 7 1101circuit_breaker | 0.51787 | 57.0725 | 2.803 | 0 | 2.803 | 0 | 787 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 1 | 1441 |  | 262 | 173 | 1441 | 262 | 173 | 488.63 | 0.0090739 | 0.00494 | 913 | 0.20679 | 0.0073855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 5. >40 - 50% | 0.20679 | 93.4703 | 93.4703 | 0%
North Valley | NV_North Valley | PARADISE 1103 | 5990 | PARADISE 1103circuit_breaker | 11.6636 | 1122.5157 | 50.9068 | 32.9934 | 17.9133 | 46.2788 | 4022 | 7170 | 2479 | 2353 | 1882 | 1796 | 0 | 3181 | 0.090912 | 7835 |  | 2599 | 2432 | 665 | 717 | 636 | 1042.14 | 0.010391 | 0.01549 | 914 | 0.76716 | 0.0073765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 0.26995 | 40.0262 | 51.0541 | 64.81%
Sierra | SI_Sierra | COLUMBIA HILL 1101 | 8415 | COLUMBIA HILL 11012212 | 1.7799 | 240.8689 | 9.0288 | 0 | 9.0288 | 2.6934 | 5450 | 2023 | 1877 | 1723 | 50 | 48 | 0 | 370 | 0.70169 | 8976 |  | 3132 | 2551 | 6953 | 3082 | 2503 | 4848.11 | 0.0073895 | 0.04736 | 915 | 0.92054 | 0.0073643 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3. >20 - 30% | 2. >10 - 20% | 0.92054 | 341.3526 | 346.8904 | 0%
Central Valley | FR_Fresno | REEDLEY 1104 | 2001 | REEDLEY 1104274990 | 0.15895 | 30.3984 | 1.7627 | 0 | 1.7627 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1 | 43 |  | 10 | 7 | 43 | 10 | 7 | 17.57 | 0.0052288 | 0.00011 | 916 | 0.036799 | 0.0073597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.036799 | 5.6731 | 5.6731 | 0%
Bay Area | DI_Diablo | MEADOW LANE 2106 | 1527 | MEADOW LANE 2106C558R | 0.071801 | 19.146 | 1.2843 | 0 | 1.2843 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 1 | 199 |  | 38 | 26 | 199 | 38 | 26 | 69.97 | 0.0037502 | 0.0003 | 917 | 0.058743 | 0.0073429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.058743 | 29.5886 | 29.5886 | 0%
North Coast | HU_Humboldt | GARBERVILLE 1102 | 3038 | GARBERVILLE 11022540 | 2.1578 | 323.6009 | 15.8987 | 0 | 15.8987 | 0 | 4564 | 0 | 0 | 0 | 0 | 0 | 0 | 426 | 1 | 8300 |  | 1499 | 988 | 8300 | 1499 | 988 | 2800.63 | 0.0066681 | 0.02078 | 918 | 1.3555 | 0.0073272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 3. >20 - 30% | 1.3555 | 94.2846 | 94.2846 | 0%
North Coast | SO_Sonoma | COTATI 1105 | 1947 | COTATI 1105328 | 0.30307 | 41.5296 | 1.6712 | 1.454 | 0.21723 | 1.6712 | 125 | 279 | 22 | 0 | 20 | 0 | 0 | 64 | 0 | 279 |  | 22 | 0 | 0 | 2 | 0 | 2.74 | 0.0072976 | 3e-05 | 919 | 0.10978 | 0.0073186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.01427 | 9.2066 | 13.1641 | 87%
Central Coast | LP_Los Padres | BUELLTON 1101 | 2019 | BUELLTON 1101Y06 | 6.2332 | 700.6618 | 29.7778 | 0 | 29.7778 | 0 | 338 | 0 | 0 | 0 | 0 | 0 | 0 | 512 | 1 | 626 |  | 115 | 77 | 626 | 115 | 77 | 213.89 | 0.0088962 | 0.00213 | 920 | 1.0087 | 0.0073091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 1.0087 | 3.8619 | 3.8619 | 0%
North Coast | SO_Sonoma | DUNBAR 1101 | 783 | DUNBAR 1101circuit_breaker | 0.47725 | 83.5837 | 3.5542 | 0.0079545 | 3.5462 | 0.66231 | 325 | 69 | 23 | 4 | 1 | 1 | 0 | 153 | 0.81365 | 559 |  | 113 | 64 | 490 | 112 | 63 | 197.54 | 0.0057098 | 0.00133 | 921 | 0.32736 | 0.0072747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.32663 | 31.583 | 31.7937 | 0.2238%
Bay Area | NB_North Bay | ALTO 1125 | 3683 | ALTO 1125510 | 2.0207 | 186.2014 | 8.6436 | 0 | 8.6436 | 0 | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 1 | 3662 |  | 662 | 437 | 3662 | 662 | 437 | 1236.52 | 0.010852 | 0.01494 | 922 | 0.63256 | 0.0072708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 4. >30 - 40% | 0.63256 | 76.5888 | 76.5888 | 0%
North Coast | HU_Humboldt | CALPELLA 1102 | 4371 | CALPELLA 1102496 | 0.71847 | 126.0551 | 5.04 | 0 | 5.04 | 0 | 386 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 1 | 713 |  | 131 | 87 | 713 | 131 | 87 | 243.64 | 0.0056996 | 0.00155 | 923 | 0.28171 | 0.0072232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3. >20 - 30% | 6. >50% | 0.28171 | 25.9923 | 25.9923 | 0%
Central Valley | YO_Yosemite | MARIPOSA 2101 | 3620 | MARIPOSA 210110070 | 3.8391 | 651.7516 | 24.5856 | 3.8822 | 20.7034 | 18.6845 | 2066 | 3570 | 1353 | 780 | 122 | 102 | 0 | 782 | 0.24002 | 4473 |  | 1516 | 888 | 903 | 1394 | 786 | 1991.05 | 0.0058905 | 0.01707 | 924 | 2.2881 | 0.0072179 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 1.9268 | 67.3319 | 61.6621 | 15.79%
Bay Area | DI_Diablo | TASSAJARA 2112 | 9191 | TASSAJARA 21126392 | 0.67283 | 109.0381 | 5.1674 | 0 | 5.1674 | 0 | 237 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 1 | 443 |  | 82 | 55 | 443 | 82 | 55 | 152.21 | 0.0061706 | 0.00105 | 925 | 0.30271 | 0.0072075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.30271 | 15.8686 | 15.8686 | 0%
North Coast | HU_Humboldt | CALPELLA 1101 | 2130 | CALPELLA 1101542 | 5.7716 | 629.5351 | 23.2536 | 0 | 23.2536 | 0 | 1648 | 0 | 0 | 0 | 0 | 0 | 0 | 386 | 1 | 3005 |  | 544 | 359 | 3005 | 544 | 359 | 1015.73 | 0.0091681 | 0.01037 | 926 | 1.5815 | 0.0071888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 1.5815 | 23.3942 | 23.3942 | 0%
North Valley | NV_North Valley | CLARK ROAD 1102 | 1065 | CLARK ROAD 11022044 | 0.71361 | 105.5267 | 8.5134 | 7.7394 | 0.77424 | 8.4788 | 173 | 303 | 139 | 47 | 116 | 39 | 0 | 205 | 0.0040711 | 304 |  | 139 | 47 | 1 | 23 | 8 | 31.6 | 0.0067623 | 0.00032 | 927 | 0.29419 | 0.0071754 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.026755 | 29.7065 | 16.3271 | 90.91%
Central Coast | SJ_San Jose | LLAGAS 2104 | 7140 | LLAGAS 2104XR294 | 0.27589 | 56.0231 | 2.9657 | 0 | 2.9657 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1 | 165 |  | 32 | 22 | 165 | 32 | 22 | 58.69 | 0.0049246 | 0.00033 | 928 | 0.10723 | 0.0071484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.10723 | 10.79 | 10.79 | 0%
North Coast | SO_Sonoma | MOLINO 1102 | 6807 | MOLINO 1102982462 | 0.47308 | 53.9301 | 2.0182 | 0.037121 | 1.9812 | 0.87083 | 875 | 113 | 64 | 22 | 37 | 0 | 0 | 110 | 0.56851 | 1023 |  | 229 | 131 | 910 | 192 | 131 | 344.94 | 0.0087721 | 0.0035 | 929 | 0.14981 | 0.0071336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.14706 | 96.9085 | 113.4685 | 1.839%
North Coast | SO_Sonoma | DUNBAR 1102 | 796 | DUNBAR 1102246 | 1.9435 | 312.5211 | 12.5716 | 0.29848 | 12.2733 | 0.72708 | 1667 | 243 | 75 | 17 | 0 | 0 | 0 | 279 | 0.94216 | 3107 |  | 593 | 359 | 2864 | 593 | 359 | 1070.17 | 0.0062187 | 0.00767 | 930 | 1.4905 | 0.0071315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 1.4551 | 48.3163 | 47.1698 | 2.374%
Sierra | SA_Sacramento | DOBBINS 1101 | 8892 | DOBBINS 110191464 | 1.8754 | 183.8447 | 8.0585 | 0.24773 | 7.8106 | 0.8608 | 2550 | 739 | 216 | 202 | 86 | 83 | 0 | 202 | 0.89318 | 4886 |  | 966 | 697 | 4147 | 880 | 614 | 1578.83 | 0.010201 | 0.01867 | 931 | 0.66921 | 0.0071193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 0.64863 | 112.6673 | 119.8731 | 3.074%
Central Valley | YO_Yosemite | MARIPOSA 2101 | 5821 | MARIPOSA 2101309438 | 1.0375 | 75.6294 | 3.4206 | 0.00075758 | 3.4199 | 0.23523 | 299 | 74 | 21 | 11 | 2 | 1 | 0 | 115 | 0.93123 | 591 |  | 116 | 74 | 517 | 114 | 73 | 202.71 | 0.013719 | 0.00325 | 932 | 0.16968 | 0.0070701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.16965 | 33.3344 | 33.9117 | 0.02215%
Central Valley | YO_Yosemite | BEAR VALLEY 2101 | 4806 | BEAR VALLEY 210190550 | 0.78053 | 176.8726 | 7.8379 | 3.7723 | 4.0655 | 7.7049 | 414 | 859 | 347 | 310 | 333 | 296 | 0 | 199 | 0.016963 | 872 |  | 349 | 312 | 13 | 16 | 16 | 23.09 | 0.004413 | 0.00015 | 933 | 0.40805 | 0.0070354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.21166 | 3.9355 | 44.5274 | 48.13%
Central Valley | YO_Yosemite | PEORIA 1701 | 853 | PEORIA 17019811 | 0.20352 | 58.3458 | 3.507 | 0 | 3.507 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 1 | 90 |  | 18 | 13 | 90 | 18 | 13 | 32.76 | 0.0034881 | 0.00013 | 934 | 0.11916 | 0.0070095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.11916 | 5.1326 | 5.1326 | 0%
North Coast | SO_Sonoma | COTATI 1103 | 3145 | COTATI 110361736 | 2.6678 | 239.114 | 11.815 | 0 | 11.815 | 0 | 741 | 0 | 0 | 0 | 0 | 0 | 0 | 230 | 1 | 1358 |  | 247 | 164 | 1358 | 247 | 164 | 460.61 | 0.011157 | 0.00573 | 935 | 0.363 | 0.0069807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.363 | 20.9057 | 20.9057 | 0%
North Coast | HU_Humboldt | HOPLAND 1101 | 2973 | HOPLAND 1101558 | 0.22072 | 53.1401 | 3.5932 | 0 | 3.5932 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 1 | 557 |  | 102 | 68 | 557 | 102 | 68 | 189.87 | 0.0041536 | 0.00088 | 936 | 0.12521 | 0.0069559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.12521 | 28.3871 | 28.3871 | 0%
Bay Area | DI_Diablo | ALHAMBRA 1105 | 5444 | ALHAMBRA 110582622 | 4.6754 | 717.1477 | 25.1794 | 0 | 25.1794 | 0 | 2442 | 0 | 0 | 0 | 0 | 0 | 0 | 574 | 1 | 4447 |  | 804 | 531 | 4447 | 804 | 531 | 1501.71 | 0.0065194 | 0.0109 | 937 | 2.0351 | 0.0069456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 2.0351 | 31.9309 | 31.9309 | 0%
North Coast | SO_Sonoma | DUNBAR 1101 | 1141 | DUNBAR 1101302 | 0.91966 | 188.0428 | 7.5367 | 1.3371 | 6.1996 | 4.8303 | 1022 | 278 | 252 | 124 | 82 | 24 | 0 | 422 | 0.3591 | 949 |  | 374 | 204 | 671 | 292 | 180 | 460.43 | 0.0048907 | 0.00297 | 938 | 0.85826 | 0.0069215 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.70599 | 47.0997 | 49.6236 | 17.74%
North Coast | SO_Sonoma | DUNBAR 1102 | 7765 | DUNBAR 1102861496 | 0.70136 | 106.5372 | 4.2117 | 0 | 4.2117 | 0 | 914 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 1 | 1672 |  | 304 | 201 | 1672 | 304 | 201 | 566.96 | 0.0065833 | 0.00416 | 940 | 0.48571 | 0.0068409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.48571 | 72.1792 | 72.1792 | 0%
North Coast | SO_Sonoma | RINCON 1103 | 9082 | RINCON 11035152 | 0.11699 | 18.1769 | 0.56117 | 0.10625 | 0.45492 | 0.56117 | 196 | 35 | 35 | 10 | 35 | 10 | 0 | 15 | 0 | 35 |  | 35 | 10 | 0 | 0 | 0 | 0 | 0.006436 | 0 | 941 | 0.17695 | 0.0068059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.14345 | 0 | 62.3692 | 18.93%
North Coast | HU_Humboldt | HOOPA 1101 | 6476 | HOOPA 11013304 | 2.4262 | 327.2404 | 14.6759 | 0 | 14.6759 | 0 | 6345 | 0 | 0 | 0 | 0 | 0 | 0 | 222 | 1 | 11535 |  | 2082 | 1373 | 11535 | 2082 | 1373 | 3890.49 | 0.0074142 | 0.0321 | 942 | 1.578 | 0.0068018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 1.578 | 141.8648 | 141.8648 | 0%
Central Valley | ST_Stockton | WEST POINT 1102 | 963 | WEST POINT 11024788 | 9.9373 | 1687.9473 | 68.7544 | 1.5125 | 67.2419 | 7.0932 | 14337 | 3375 | 1082 | 922 | 488 | 406 | 0 | 2693 | 0.89683 | 26736 |  | 5297 | 3699 | 23361 | 4809 | 3293 | 8690.82 | 0.0058872 | 0.05887 | 943 | 4.9705 | 0.0067718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 4. >30 - 40% | 2. >10 - 20% | 4.8612 | 71.518 | 77.0424 | 2.2%
Sierra | SI_Sierra | FORESTHILL 1101 | 7679 | FORESTHILL 110175340 | 0.86422 | 127.304 | 4.9468 | 0 | 4.9468 | 0.56042 | 2831 | 114 | 114 | 85 | 96 | 76 | 0 | 291 | 0.88671 | 4683 |  | 940 | 630 | 4569 | 844 | 554 | 1567.49 | 0.0067886 | 0.01191 | 944 | 0.59533 | 0.0067652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.59533 | 170.616 | 190.0226 | 0%
Bay Area | DI_Diablo | WILLOW PASS 1101 | 2786 | WILLOW PASS 1101circuit_breaker | 0.1257 | 22.5402 | 1.7932 | 0 | 1.7932 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1 | 18 |  | 5 | 4 | 18 | 5 | 4 | 8.47 | 0.0055768 | 6e-05 | 945 | 0.0067338 | 0.0067338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.0067338 | 2.7883 | 2.7883 | 0%
Central Valley | ST_Stockton | FROGTOWN 1702 | 1490 | FROGTOWN 17021573 | 2.4367 | 509.0478 | 18.1801 | 0 | 18.1801 | 0 | 590 | 0 | 0 | 0 | 0 | 0 | 0 | 327 | 1 | 1084 |  | 197 | 131 | 1084 | 197 | 131 | 367.45 | 0.0047867 | 0.00196 | 946 | 1.2224 | 0.0067166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 1.2224 | 10.836 | 10.836 | 0%
Central Valley | ST_Stockton | FROGTOWN 1702 | 5192 | FROGTOWN 17027108 | 1.108 | 200.865 | 11.339 | 0 | 11.339 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 1 | 439 |  | 81 | 54 | 439 | 81 | 54 | 150.48 | 0.0055162 | 0.00093 | 947 | 0.58426 | 0.0067157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.58426 | 7.1435 | 7.1435 | 0%
Sierra | SA_Sacramento | MADISON 2101 | 9374 | MADISON 210113372 | 0.37122 | 51.0332 | 3.6485 | 0 | 3.6485 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 1 | 25 |  | 6 | 5 | 25 | 6 | 5 | 10.47 | 0.007274 | 9e-05 | 948 | 0.073868 | 0.0067153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.073868 | 1.6445 | 1.6445 | 0%
Central Valley | YO_Yosemite | COARSEGOLD 2104 | 8880 | COARSEGOLD 21045516 | 4.3067 | 456.5318 | 18.1585 | 17.3847 | 0.77386 | 18.1581 | 347 | 1429 | 297 | 279 | 272 | 258 | 0 | 414 | 2.086e-05 | 1429 |  | 297 | 279 | 0 | 25 | 21 | 34.25 | 0.0094334 | 0.00049 | 949 | 0.6847 | 0.0067128 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.02918 | 32.3054 | 16.356 | 95.74%
Central Valley | ST_Stockton | WEST POINT 1101 | 4541 | WEST POINT 110112256 | 0.16944 | 98.7132 | 3.9741 | 0 | 3.9741 | 0 | 2797 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 1 | 5092 |  | 920 | 607 | 5092 | 920 | 607 | 1718.68 | 0.0017165 | 0.00328 | 950 | 0.17443 | 0.0067088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.17443 | 231.5017 | 231.5017 | 0%
North Valley | NV_North Valley | BUCKS CREEK 1101 | 1751 | BUCKS CREEK 1101circuit_breaker | 6.8984 | 305.1517 | 7.8358 | 0 | 7.8358 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 183 | 1 | 1810 |  | 328 | 217 | 1810 | 328 | 217 | 612.26 | 0.022606 | 0.01542 | 951 | 0.71638 | 0.0066952 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.71638 | 41.8592 | 41.8592 | 0%
Central Valley | ST_Stockton | FROGTOWN 1702 | 4890 | FROGTOWN 17028482 | 1.9496 | 354.5237 | 13.6383 | 0 | 13.6383 | 0 | 464 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 1 | 855 |  | 156 | 104 | 855 | 156 | 104 | 290.67 | 0.0054991 | 0.00178 | 952 | 1.0035 | 0.0066901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 1.0035 | 11.4384 | 11.4384 | 0%
North Coast | SO_Sonoma | FITCH MOUNTAIN 1111 | 5113 | FITCH MOUNTAIN 1111circuit_breaker | 0.81437 | 36.0527 | 0.8178 | 0.056818 | 0.76098 | 0.19678 | 73 | 37 | 6 | 0 | 0 | 0 | 0 | 16 | 0.75938 | 147 |  | 27 | 15 | 110 | 27 | 15 | 46.89 | 0.022588 | 0.00127 | 953 | 0.046726 | 0.0066751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.043479 | 35.4803 | 33.0153 | 6.948%
Central Coast | LP_Los Padres | SANTA MARIA 1108 | 3525 | SANTA MARIA 1108M80 | 7.3461 | 1407.5906 | 55.536 | 0 | 55.536 | 0 | 1574 | 0 | 0 | 0 | 0 | 0 | 0 | 777 | 1 | 2871 |  | 520 | 343 | 2871 | 520 | 343 | 970.79 | 0.0052189 | 0.00564 | 954 | 2.2952 | 0.006672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 2.2952 | 9.3633 | 9.3633 | 0%
Central Coast | LP_Los Padres | MESA 1101 | 4203 | MESA 11016111 | 3.8533 | 603.8159 | 22.161 | 0 | 22.161 | 0 | 417 | 0 | 0 | 0 | 0 | 0 | 0 | 340 | 1 | 770 |  | 141 | 94 | 770 | 141 | 94 | 262.47 | 0.0063816 | 0.00187 | 955 | 1.0942 | 0.0066719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 1.0942 | 6.3625 | 6.3625 | 0%
North Coast | HU_Humboldt | HOPLAND 1101 | 1530 | HOPLAND 110180620 | 0.24149 | 21.4217 | 0.88902 | 0 | 0.88902 | 0 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 283 |  | 53 | 36 | 283 | 53 | 36 | 98.08 | 0.011273 | 0.00124 | 956 | 0.13322 | 0.006661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.13322 | 59.6165 | 59.6165 | 0%
North Coast | HU_Humboldt | LOW GAP 1101 | 6920 | LOW GAP 11014160 | 2.69 | 446.1046 | 20.6706 | 0 | 20.6706 | 0 | 8510 | 0 | 0 | 0 | 0 | 0 | 0 | 444 | 1 | 15466 |  | 2791 | 1840 | 15466 | 2791 | 1840 | 5215.61 | 0.00603 | 0.035 | 957 | 2.1226 | 0.006654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4. >30 - 40% | 2. >10 - 20% | 2.1226 | 135.0224 | 135.0224 | 0%
North Coast | SO_Sonoma | DUNBAR 1101 | 4735 | DUNBAR 110179086 | 1.8005 | 185.6204 | 8.2225 | 0.12652 | 8.096 | 0.2964 | 1267 | 18 | 18 | 5 | 10 | 1 | 0 | 311 | 0.96395 | 2248 |  | 422 | 272 | 2230 | 412 | 271 | 765.14 | 0.0096997 | 0.00831 | 958 | 0.65343 | 0.0066003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.64338 | 50.8892 | 51.3224 | 1.539%
North Valley | NV_North Valley | VOLTA 1101 | 5080 | VOLTA 11011568 | 12.5951 | 564.0782 | 22.6894 | 0 | 22.6894 | 0 | 1136 | 0 | 0 | 0 | 0 | 0 | 0 | 517 | 1 | 2075 |  | 376 | 249 | 2075 | 376 | 249 | 701.87 | 0.022329 | 0.01746 | 959 | 0.14477 | 0.0065807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 0.14477 | 16.5716 | 16.5716 | 0%
Bay Area | NB_North Bay | MONTICELLO 1101 | 5980 | MONTICELLO 110193384 | 2.0275 | 320.5196 | 16.6973 | 0 | 16.6973 | 0 | 1160 | 0 | 0 | 0 | 0 | 0 | 0 | 213 | 1 | 2119 |  | 384 | 254 | 2119 | 384 | 254 | 716.79 | 0.0063256 | 0.00505 | 960 | 0.89297 | 0.0065659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.89297 | 22.9977 | 22.9977 | 0%
North Coast | HU_Humboldt | UKIAH 1114 | 1003 | UKIAH 1114822 | 0.48315 | 71.0181 | 2.5898 | 0 | 2.5898 | 0 | 357 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 1 | 661 |  | 121 | 81 | 661 | 121 | 81 | 225.26 | 0.0068032 | 0.00171 | 961 | 0.13047 | 0.0065233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.13047 | 46.7222 | 46.7222 | 0%
Sierra | SI_Sierra | NARROWS 2102 | 786 | NARROWS 210248484 | 7.8032 | 1020.2688 | 41.6979 | 28.5127 | 13.1852 | 39.2652 | 12214 | 25277 | 11144 | 9944 | 10421 | 9355 | 0 | 1623 | 0.058343 | 26572 |  | 11378 | 10098 | 1295 | 957 | 743 | 1427.64 | 0.0076482 | 0.01522 | 962 | 3.5745 | 0.0064873 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 1.1303 | 72.5812 | 272.8673 | 68.38%
Central Coast | LP_Los Padres | OCEANO 1104 | 4630 | OCEANO 1104Q12 | 2.2152 | 311.0557 | 10.5746 | 0 | 10.5746 | 0 | 333 | 0 | 0 | 0 | 0 | 0 | 0 | 310 | 1 | 617 |  | 113 | 76 | 617 | 113 | 76 | 210.34 | 0.0071214 | 0.00167 | 963 | 0.54859 | 0.006454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.54859 | 10.686 | 10.686 | 0%
North Valley | NV_North Valley | ANTLER 1101 | 6804 | ANTLER 11011612 | 1.2098 | 194.5587 | 8.7892 | 0 | 8.7892 | 0 | 2170 | 0 | 0 | 0 | 0 | 0 | 0 | 209 | 1 | 3953 |  | 715 | 472 | 3953 | 715 | 472 | 1335.32 | 0.006218 | 0.00924 | 964 | 0.59914 | 0.0064424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.59914 | 81.3498 | 81.3498 | 0%
Bay Area | NB_North Bay | ALTO 1124 | 74 | ALTO 1124428 | 1.0483 | 85.8963 | 4.0119 | 0 | 4.0119 | 0 | 1167 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 1 | 2132 |  | 386 | 255 | 2132 | 386 | 255 | 720.7 | 0.012205 | 0.0098 | 965 | 0.38649 | 0.0064415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.38649 | 96.213 | 96.213 | 0%
North Coast | HU_Humboldt | HOPLAND 1101 | 999 | HOPLAND 1101770 | 0.67607 | 138.9215 | 7.6574 | 0 | 7.6574 | 0 | 374 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1 | 691 |  | 127 | 84 | 691 | 127 | 84 | 236.18 | 0.0048665 | 0.00129 | 966 | 0.11554 | 0.0064187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.11554 | 16.5853 | 16.5853 | 0%
Central Valley | YO_Yosemite | MERCED FALLS 1102 | 4411 | MERCED FALLS 110285002 | 6.9108 | 899.1333 | 35.0034 | 34.7002 | 0.30341 | 35.0034 | 83 | 840 | 95 | 49 | 95 | 49 | 0 | 1186 | 0 | 840 |  | 95 | 49 | 0 | 0 | 0 | 0 | 0.0076861 | 0 | 967 | 1.0125 | 0.006408 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.008776 | 0 | 2.714 | 99.13%
North Coast | SO_Sonoma | RINCON 1103 | 3793 | RINCON 1103474 | 3.4088 | 504.2783 | 18.5339 | 1.6905 | 16.8434 | 18.4557 | 6412 | 1697 | 1520 | 471 | 1465 | 429 | 0 | 679 | 0.0042204 | 1746 |  | 1529 | 477 | 49 | 64 | 48 | 92.09 | 0.0067598 | 0.0009 | 968 | 1.828 | 0.0063917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 1.6613 | 3.7997 | 82.4975 | 9.121%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1101 | 2794 | SAN LUIS OBISPO 1101circuit_breaker | 0.46787 | 68.8112 | 2.8036 | 0 | 2.8036 | 0 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 1 | 321 |  | 60 | 40 | 321 | 60 | 40 | 111.09 | 0.0067994 | 0.00085 | 969 | 0.22971 | 0.0063809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.22971 | 21.4011 | 21.4011 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2111 | 2591 | TEMPLETON 2111A66 | 7.9835 | 877.0325 | 35.714 | 0 | 35.714 | 0 | 4566 | 0 | 0 | 0 | 0 | 0 | 0 | 772 | 1 | 8304 |  | 1500 | 989 | 8304 | 1500 | 989 | 2802.36 | 0.0091029 | 0.02839 | 970 | 3.1522 | 0.006368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 3.1522 | 42.0003 | 42.0003 | 0%
Sierra | SI_Sierra | APPLE HILL 2102 | 3166 | APPLE HILL 2102186912 | 6.8841 | 1181.1229 | 45.2871 | 4.2782 | 41.0091 | 16.8665 | 10181 | 1890 | 1191 | 1015 | 0 | 0 | 0 | 1569 | 0.62757 | 13500 |  | 3286 | 2396 | 11610 | 3286 | 2396 | 5546.72 | 0.0058284 | 0.03983 | 971 | 4.3301 | 0.0063679 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4. >30 - 40% | 2. >10 - 20% | 3.9211 | 80.1286 | 72.5593 | 9.447%
North Coast | SO_Sonoma | GEYSERVILLE 1101 | 276 | GEYSERVILLE 1101122 | 1.2325 | 110.3603 | 5.0881 | 0 | 5.0881 | 0.06572 | 299 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 0.98708 | 548 |  | 101 | 67 | 548 | 101 | 67 | 187.69 | 0.011168 | 0.00235 | 972 | 0.22246 | 0.0063559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.22246 | 19.8504 | 19.8504 | 0%
North Coast | SO_Sonoma | COTATI 1102 | 5725 | COTATI 1102260 | 0.38018 | 66.6209 | 2.8036 | 2.2449 | 0.55871 | 2.8036 | 168 | 341 | 85 | 38 | 74 | 30 | 0 | 98 | 0 | 341 |  | 85 | 38 | 0 | 11 | 8 | 15.07 | 0.0057066 | 0.00013 | 974 | 0.15154 | 0.006314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.030198 | 19.6881 | 30.3182 | 80.07%
North Coast | SO_Sonoma | RINCON 1101 | 1283 | RINCON 1101578 | 2.7889 | 417.6474 | 17.3468 | 2.7371 | 14.6097 | 15.2479 | 2136 | 1029 | 1029 | 280 | 752 | 170 | 0 | 673 | 0.12099 | 1500 |  | 1114 | 336 | 471 | 362 | 166 | 538.33 | 0.0066776 | 0.00503 | 975 | 1.0535 | 0.0062707 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.88726 | 24.7781 | 64.2194 | 15.78%
Central Valley | YO_Yosemite | PEORIA 1705 | 7927 | PEORIA 1705999 | 0.40587 | 50.2507 | 2.5356 | 0 | 2.5356 | 0 | 352 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1 | 651 |  | 119 | 80 | 651 | 119 | 80 | 221.62 | 0.0080769 | 0.002 | 976 | 0.23114 | 0.0062471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.23114 | 46.9316 | 46.9316 | 0%
Central Valley | FR_Fresno | REEDLEY 1112 | 3755 | REEDLEY 11127240 | 0.10744 | 20.6937 | 1.1256 | 0 | 1.1256 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 16 |  | 5 | 4 | 16 | 5 | 4 | 8.29 | 0.005192 | 5e-05 | 977 | 0.0062313 | 0.0062313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.0062313 | 4.4422 | 4.4422 | 0%
Central Valley | ST_Stockton | WEST POINT 1102 | 5363 | WEST POINT 11021305 | 1.3482 | 261.9145 | 11.4059 | 5.0563 | 6.3496 | 11.2697 | 3191 | 4726 | 905 | 584 | 606 | 328 | 0 | 466 | 0.011939 | 4795 |  | 918 | 592 | 69 | 312 | 264 | 433.65 | 0.0051474 | 0.00334 | 978 | 0.36763 | 0.006231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.20466 | 49.1368 | 80.4849 | 44.33%
North Valley | NV_North Valley | JESSUP 1101 | 1846 | JESSUP 11019002 | 1.1454 | 211.5624 | 8.9417 | 0 | 8.9417 | 0 | 659 | 0 | 0 | 0 | 0 | 0 | 0 | 244 | 1 | 1209 |  | 220 | 146 | 1209 | 220 | 146 | 410.21 | 0.0054139 | 0.00248 | 979 | 0.67709 | 0.0062118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.67709 | 24.6039 | 24.6039 | 0%
Central Valley | ST_Stockton | WEST POINT 1102 | 6095 | WEST POINT 11021303 | 3.3886 | 355.9792 | 15.2619 | 2.6445 | 12.6172 | 10.9574 | 9020 | 13958 | 2891 | 2350 | 2345 | 1897 | 0 | 680 | 0.28204 | 18581 |  | 3725 | 2900 | 4623 | 1380 | 1003 | 2306.67 | 0.0095191 | 0.02732 | 980 | 0.34713 | 0.0061987 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 0.28697 | 109.3742 | 244.0713 | 17.33%
North Coast | HU_Humboldt | WILLOW CREEK 1102 | 9321 | WILLOW CREEK 110237374 | 0.23514 | 45.153 | 1.2627 | 0 | 1.2627 | 1.2627 | 1063 | 130 | 130 | 104 | 5 | 0 | 0 | 31 | 0 | 130 |  | 130 | 104 | 0 | 125 | 104 | 171.25 | 0.0052077 | 0.00135 | 981 | 0.11144 | 0.0061911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.11144 | 98.9951 | 102.9549 | 0%
North Coast | SO_Sonoma | MONROE 2103 | 2170 | MONROE 2103circuit_breaker | 0.022172 | 8.518 | 0.6697 | 0 | 0.6697 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 25 |  | 6 | 5 | 25 | 6 | 5 | 10.47 | 0.002603 | 3e-05 | 982 | 0.018573 | 0.0061911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.018573 | 8.9593 | 8.9593 | 0%
Central Coast | SJ_San Jose | MC KEE 1107 | 1083 | MC KEE 1107XR010 | 0.19704 | 33.9141 | 2.1746 | 0 | 2.1746 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 1 | 168 |  | 32 | 22 | 168 | 32 | 22 | 58.96 | 0.0058099 | 0.00039 | 983 | 0.1416 | 0.0061563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.1416 | 14.7152 | 14.7152 | 0%
Central Coast | LP_Los Padres | ATASCADERO 1103 | 7256 | ATASCADERO 1103A06 | 4.4682 | 811.6969 | 33.3352 | 0.81894 | 32.5163 | 3.2148 | 1987 | 152 | 147 | 71 | 61 | 4 | 0 | 1241 | 0.90356 | 3423 |  | 739 | 462 | 3271 | 678 | 458 | 1223.25 | 0.0055047 | 0.00776 | 984 | 2.3346 | 0.0061114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 2.2772 | 20.8511 | 22.1687 | 2.457%
Central Valley | ST_Stockton | MARTELL 1103 | 4877 | MARTELL 1103circuit_breaker | 0.2639 | 51.3676 | 2.2551 | 0 | 2.2551 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 1 | 105 |  | 21 | 15 | 105 | 21 | 15 | 38.22 | 0.0051374 | 0.00022 | 985 | 0.073194 | 0.0060995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.073194 | 9.3122 | 9.3122 | 0%
North Valley | NV_North Valley | WYANDOTTE 1105 | 899 | WYANDOTTE 1105329930 | 0.97705 | 152.5782 | 7.0051 | 0 | 7.0051 | 0 | 759 | 0 | 0 | 0 | 0 | 0 | 0 | 178 | 1 | 1391 |  | 253 | 167 | 1391 | 253 | 167 | 471.8 | 0.0064036 | 0.00337 | 986 | 0.59739 | 0.0060958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.59739 | 36.1165 | 36.1165 | 0%
Central Valley | ST_Stockton | FROGTOWN 1702 | 861 | FROGTOWN 170275252 | 5.1765 | 1320.5196 | 59.6852 | 0 | 59.6852 | 0 | 1751 | 0 | 0 | 0 | 0 | 0 | 0 | 961 | 1 | 3192 |  | 578 | 381 | 3192 | 578 | 381 | 1079.14 | 0.0039201 | 0.00471 | 987 | 2.6848 | 0.0060605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 2.6848 | 9.6841 | 9.6841 | 0%
Central Valley | ST_Stockton | FROGTOWN 1702 | 2624 | FROGTOWN 170212282 | 5.6272 | 772.4414 | 34.7163 | 0 | 34.7163 | 0 | 2118 | 0 | 0 | 0 | 0 | 0 | 0 | 728 | 1 | 3858 |  | 698 | 461 | 3858 | 698 | 461 | 1303.48 | 0.007285 | 0.01057 | 988 | 2.4605 | 0.0060603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 2.4605 | 20.1058 | 20.1058 | 0%
Sierra | SI_Sierra | HIGGINS 1103 | 1076 | HIGGINS 110332120 | 6.1797 | 991.4891 | 40.5492 | 0 | 40.5492 | 0 | 11273 | 0 | 0 | 0 | 0 | 0 | 0 | 1040 | 1 | 20484 |  | 3696 | 2436 | 20484 | 3696 | 2436 | 6907.08 | 0.0062328 | 0.0479 | 989 | 3.6409 | 0.006038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4. >30 - 40% | 2. >10 - 20% | 3.6409 | 91.1484 | 91.1484 | 0%
Sierra | SI_Sierra | SHINGLE SPRINGS 2110 | 539 | SHINGLE SPRINGS 21107742 | 10.368 | 1101.512 | 45.6909 | 1.1722 | 44.5186 | 1.1758 | 7024 | 181 | 43 | 39 | 43 | 39 | 0 | 1036 | 0.97427 | 12620 |  | 2288 | 1519 | 12439 | 2245 | 1480 | 4195.16 | 0.0094125 | 0.04394 | 990 | 3.4194 | 0.005999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4. >30 - 40% | 2. >10 - 20% | 3.3317 | 50.4284 | 50.0756 | 2.565%
Sierra | SI_Sierra | SHADY GLEN 1102 | 142 | SHADY GLEN 11022232 | 1.7813 | 287.6958 | 10.978 | 0 | 10.978 | 0.26345 | 6847 | 9 | 3 | 3 | 0 | 0 | 0 | 287 | 0.976 | 12157 |  | 2196 | 1448 | 12148 | 2196 | 1448 | 4101.84 | 0.0061917 | 0.02827 | 991 | 0.98939 | 0.0059963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 0.98939 | 200.0359 | 200.0359 | 0%
Central Valley | ST_Stockton | CALAVERAS CEMENT 1101 | 5941 | CALAVERAS CEMENT 110111188 | 2.5566 | 659.1942 | 29.1797 | 0.1428 | 29.0369 | 0.10246 | 1904 | 1 | 0 | 0 | 0 | 0 | 0 | 1007 | 0.99649 | 3459 |  | 626 | 413 | 3458 | 626 | 413 | 1168.84 | 0.0038784 | 0.00505 | 992 | 2.0507 | 0.0059962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 2.0407 | 21.5588 | 21.4532 | 0.4894%
Sierra | SI_Sierra | NARROWS 2105 | 3260 | NARROWS 21052216 | 10.0158 | 1340.582 | 53.8008 | 0.20152 | 53.5992 | 0.32879 | 7716 | 195 | 82 | 76 | 79 | 73 | 0 | 1308 | 0.99389 | 14134 |  | 2598 | 1734 | 13939 | 2519 | 1661 | 4705.54 | 0.0074712 | 0.03913 | 993 | 4.4415 | 0.0058828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4. >30 - 40% | 2. >10 - 20% | 4.4249 | 46.9969 | 48.2893 | 0.3746%
Sierra | SI_Sierra | GRASS VALLEY 1103 | 2332 | GRASS VALLEY 11032110 | 3.0317 | 441.4611 | 18.5792 | 0 | 18.5792 | 0 | 6980 | 0 | 0 | 0 | 0 | 0 | 0 | 469 | 1 | 12688 |  | 2290 | 1510 | 12688 | 2290 | 1510 | 4279.22 | 0.0068674 | 0.0327 | 994 | 1.6757 | 0.005859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 1.6757 | 123.2563 | 123.2563 | 0%
Sierra | SA_Sacramento | CORTINA 1101 | 3459 | CORTINA 1101302192 | 0.1317 | 25.8327 | 1.871 | 0 | 1.871 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1 | 23 |  | 6 | 5 | 23 | 6 | 5 | 10.29 | 0.0050984 | 6e-05 | 995 | 0.040868 | 0.0058383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.040868 | 3.2068 | 3.2068 | 0%
North Valley | NV_North Valley | BUCKS CREEK 1102 | 8636 | BUCKS CREEK 1102circuit_breaker | 3.5488 | 715.8607 | 27.6752 | 0 | 27.6752 | 0 | 4260 | 0 | 0 | 0 | 0 | 0 | 0 | 729 | 1 | 7748 |  | 1399 | 923 | 7748 | 1399 | 923 | 2613.95 | 0.0049574 | 0.01442 | 996 | 1.1761 | 0.0058222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 1.1761 | 50.5507 | 50.5507 | 0%
Sierra | SI_Sierra | APPLE HILL 2102 | 6107 | APPLE HILL 21026552 | 5.6483 | 358.3852 | 13.3553 | 0 | 13.3553 | 0.044129 | 3205 | 13 | 12 | 12 | 0 | 0 | 0 | 546 | 0.9967 | 5826 |  | 1062 | 705 | 5813 | 1062 | 705 | 1978.11 | 0.01576 | 0.0348 | 997 | 1.0355 | 0.0058175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4. >30 - 40% | 2. >10 - 20% | 1.0355 | 79.519 | 79.519 | 0%
North Valley | NV_North Valley | BIG BEND 1102 | 6741 | BIG BEND 1102circuit_breaker | 1.9819 | 397.9306 | 17.3771 | 0 | 17.3771 | 0 | 5725 | 0 | 0 | 0 | 0 | 0 | 0 | 356 | 1 | 10409 |  | 1879 | 1239 | 10409 | 1879 | 1239 | 3511.04 | 0.0049804 | 0.01946 | 998 | 1.0961 | 0.0057992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 1.0961 | 108.1309 | 108.1309 | 0%
Central Valley | YO_Yosemite | COARSEGOLD 2102 | 4631 | COARSEGOLD 2102circuit_breaker | 1.2592 | 296.6238 | 13.514 | 7.7254 | 5.7884 | 11.9633 | 994 | 1609 | 572 | 478 | 303 | 245 | 0 | 251 | 0.11475 | 1818 |  | 610 | 503 | 209 | 307 | 258 | 439.4 | 0.0042451 | 0.00271 | 999 | 0.48667 | 0.0057937 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.20845 | 53.0367 | 45.1383 | 57.17%
Central Coast | SJ_San Jose | MORGAN HILL 2105 | 4182 | MORGAN HILL 2105XR494 | 0.13143 | 14.0743 | 1.2563 | 0 | 1.2563 | 0 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1 | 170 |  | 33 | 22 | 170 | 33 | 22 | 60.51 | 0.009338 | 0.00064 | 1000 | 0.040455 | 0.0057792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.040455 | 26.2687 | 26.2687 | 0%
Bay Area | PE_Peninsula | WOODSIDE 1101 | 4734 | WOODSIDE 11018972 | 0.67601 | 146.4763 | 5.9856 | 0 | 5.9856 | 0 | 4466 | 0 | 0 | 0 | 0 | 0 | 0 | 314 | 1 | 8122 |  | 1467 | 967 | 8122 | 1467 | 967 | 2740.77 | 0.0046152 | 0.01408 | 1001 | 0.60385 | 0.005751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.60385 | 245.088 | 245.088 | 0%
North Coast | HU_Humboldt | LAYTONVILLE 1101 | 627 | LAYTONVILLE 1101circuit_breaker | 1.0957 | 153.5249 | 5.5583 | 1.7449 | 3.8134 | 5.4206 | 3519 | 7135 | 2417 | 1996 | 2157 | 1817 | 0 | 181 | 0.024772 | 7294 |  | 2446 | 2015 | 159 | 289 | 198 | 410.24 | 0.0071368 | 0.00429 | 1002 | 0.50016 | 0.005749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.34315 | 75.7845 | 440.06 | 31.39%
Central Valley | ST_Stockton | PINE GROVE 1102 | 6771 | PINE GROVE 110235576 | 0.90552 | 177.8037 | 8.2036 | 0 | 8.2036 | 0.26023 | 3954 | 2 | 2 | 2 | 2 | 2 | 0 | 372 | 0.96828 | 6966 |  | 1260 | 832 | 6964 | 1258 | 830 | 2350.22 | 0.0050928 | 0.01332 | 1003 | 0.66654 | 0.005746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.66654 | 153.3473 | 153.5911 | 0%
Sierra | SI_Sierra | PLACERVILLE 2106 | 2292 | PLACERVILLE 21067522 | 12.2176 | 1577.0101 | 65.7597 | 0 | 65.7597 | 0 | 19994 | 0 | 0 | 0 | 0 | 0 | 0 | 2555 | 1 | 36321 |  | 6552 | 4317 | 36321 | 6552 | 4317 | 12245.13 | 0.0077473 | 0.10555 | 1004 | 5.9329 | 0.0057379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4. >30 - 40% | 1. <= 10% | 5.9329 | 99.6356 | 99.6356 | 0%
Central Coast | LP_Los Padres | CABRILLO 1103 | 5553 | CABRILLO 11031437 | 0.26252 | 52.3834 | 2.6614 | 0 | 2.6614 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 1 | 49 |  | 11 | 8 | 49 | 11 | 8 | 19.48 | 0.0050115 | 0.00011 | 1005 | 0.051561 | 0.005729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.051561 | 4.1332 | 4.1332 | 0%
Bay Area | NB_North Bay | PUEBLO 2103 | 7473 | PUEBLO 2103694 | 0.018588 | 3.1176 | 0.15076 | 0 | 0.15076 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 14 |  | 5 | 4 | 14 | 5 | 4 | 8.11 | 0.0059624 | 6e-05 | 1006 | 0.045737 | 0.0057172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.045737 | 33.1658 | 33.1658 | 0%
Sierra | SI_Sierra | FORESTHILL 1101 | 6921 | FORESTHILL 11011820 | 0.73058 | 123.2673 | 5.2848 | 0 | 5.2848 | 0 | 4001 | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 1 | 7278 |  | 1315 | 867 | 7278 | 1315 | 867 | 2456.57 | 0.0059268 | 0.01621 | 1007 | 0.43218 | 0.0056866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.43218 | 248.8245 | 248.8245 | 0%
North Valley | NV_North Valley | MC ARTHUR 1102 | 6183 | PIT NO 1 11019702 | 0.12158 | 13.7401 | 0.67576 | 0 | 0.67576 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1 | 112 |  | 22 | 16 | 112 | 22 | 16 | 40.22 | 0.0088488 | 0.0004 | 1008 | 0.028389 | 0.0056778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.028389 | 32.5561 | 32.5561 | 0%
Bay Area | NB_North Bay | ALTO 1124 | 7139 | ALTO 11243745 | 1.5655 | 70.361 | 2.078 | 0 | 2.078 | 0 | 266 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 1 | 495 |  | 91 | 61 | 495 | 91 | 61 | 169.22 | 0.02225 | 0.00421 | 1009 | 0.32825 | 0.0056595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.32825 | 43.7915 | 43.7915 | 0%
Central Valley | ST_Stockton | WEST POINT 1102 | 3986 | WEST POINT 110236676 | 2.0712 | 387.4741 | 16.7078 | 3.3193 | 13.3884 | 13.5184 | 7464 | 11619 | 3119 | 2613 | 2117 | 1801 | 0 | 810 | 0.19089 | 14209 |  | 3586 | 2921 | 2590 | 1469 | 1120 | 2245.63 | 0.0053454 | 0.01633 | 1010 | 1.3099 | 0.0056462 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 1.0497 | 109.7215 | 214.6307 | 19.87%
Central Coast | LP_Los Padres | CHOLAME 2102 | 2664 | CHOLAME 2102X10 | 1.7921 | 443.9159 | 20.6491 | 20.1502 | 0.49886 | 20.6428 | 33 | 88 | 10 | 3 | 10 | 3 | 0 | 420 | 0.00030268 | 88 |  | 10 | 3 | 0 | 0 | 0 | 0 | 0.0040371 | 0 | 1011 | 0.14047 | 0.0056186 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.0033935 | 0 | 0.48428 | 97.58%
North Coast | HU_Humboldt | LAYTONVILLE 1101 | 4618 | LAYTONVILLE 1101402 | 3.0915 | 608.8526 | 23.3324 | 13.732 | 9.6004 | 23.1134 | 5449 | 12897 | 5700 | 4777 | 5425 | 4587 | 0 | 592 | 0.0093835 | 12990 |  | 5717 | 4788 | 93 | 292 | 201 | 408.41 | 0.0050776 | 0.00308 | 1012 | 1.2901 | 0.0056093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.53084 | 30.4155 | 245.0242 | 58.85%
Sierra | SI_Sierra | WISE 1101 | 7948 | WISE 11011404 | 0.3893 | 53.1361 | 1.7964 | 0 | 1.7964 | 0 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 1 | 250 |  | 47 | 32 | 250 | 47 | 32 | 86.89 | 0.0073264 | 0.00072 | 1013 | 0.066999 | 0.0055833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.066999 | 26.1634 | 26.1634 | 0%
North Coast | HU_Humboldt | HOPLAND 1101 | 5635 | HOPLAND 11011100 | 0.34049 | 79.9945 | 2.9608 | 0 | 2.9608 | 0 | 327 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 1 | 606 |  | 111 | 74 | 606 | 111 | 74 | 206.61 | 0.0042564 | 0.00098 | 1014 | 0.2836 | 0.0055607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.2836 | 37.4899 | 37.4899 | 0%
North Coast | SO_Sonoma | COTATI 1102 | 334 | COTATI 1102464 | 0.38099 | 62.5017 | 3.0496 | 2.6053 | 0.44451 | 2.878 | 184 | 278 | 62 | 20 | 58 | 19 | 0 | 105 | 0.056266 | 297 |  | 66 | 22 | 19 | 8 | 3 | 12.67 | 0.0060956 | 0.0001 | 1015 | 0.10565 | 0.0055606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.015399 | 17.9974 | 21.642 | 85.43%
Bay Area | NB_North Bay | SILVERADO 2104 | 4389 | SILVERADO 2104circuit_breaker | 0.278 | 60.2403 | 2.2326 | 1.0614 | 1.1712 | 2.2216 | 657 | 1104 | 462 | 227 | 207 | 30 | 0 | 132 | 0.0049203 | 1110 |  | 463 | 228 | 6 | 256 | 198 | 351.26 | 0.0046149 | 0.00246 | 1016 | 0.17237 | 0.0055603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.090424 | 218.577 | 207.3838 | 47.54%
North Coast | HU_Humboldt | WILLITS 1104 | 3414 | WILLITS 110434008 | 2.1998 | 473.4231 | 22.5773 | 19.0218 | 3.5553 | 20.9652 | 14578 | 39957 | 8229 | 5982 | 8133 | 5927 | 0 | 1165 | 0.071405 | 41848 |  | 8570 | 6207 | 1891 | 437 | 280 | 768.88 | 0.0046466 | 0.00422 | 1017 | 2.0475 | 0.0055337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.32242 | 122.915 | 379.5853 | 84.25%
Central Coast | SJ_San Jose | MORGAN HILL 2111 | 4643 | MORGAN HILL 2111XR398 | 4.3341 | 884.4071 | 36.5297 | 0 | 36.5297 | 0 | 4760 | 0 | 0 | 0 | 0 | 0 | 0 | 635 | 1 | 8656 |  | 1563 | 1031 | 8656 | 1563 | 1031 | 2920.35 | 0.0049006 | 0.01593 | 1018 | 2.263 | 0.0055194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 2.263 | 42.7871 | 42.7871 | 0%
Central Valley | FR_Fresno | DUNLAP 1102 | 4581 | DUNLAP 11027849F | 1.0818 | 209.7891 | 7.8945 | 0 | 7.8945 | 0 | 702 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 1 | 1287 |  | 234 | 155 | 1287 | 234 | 155 | 436.41 | 0.0051564 | 0.00251 | 1019 | 0.50774 | 0.0055189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.50774 | 29.6409 | 29.6409 | 0%
Sierra | SI_Sierra | BONNIE NOOK 1101 | 3798 | BONNIE NOOK 110186696 | 1.861 | 288.7435 | 9.885 | 0 | 9.885 | 0.60303 | 4842 | 21 | 7 | 3 | 0 | 0 | 0 | 527 | 0.939 | 8289 |  | 1500 | 987 | 8268 | 1500 | 987 | 2799.12 | 0.006445 | 0.0201 | 1020 | 0.79438 | 0.0055165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 0.79438 | 151.7445 | 151.7445 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1108 | 8967 | SAN RAFAEL 110863598 | 0.25451 | 54.2365 | 2.379 | 0 | 2.379 | 0 | 785 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 1 | 1438 |  | 261 | 173 | 1438 | 261 | 173 | 486.99 | 0.0046926 | 0.00255 | 1021 | 0.16547 | 0.0055157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.16547 | 109.711 | 109.711 | 0%
North Coast | SO_Sonoma | FITCH MOUNTAIN 1111 | 9343 | 701650 | 0.12479 | 9.4706 | 0.24148 | 0 | 0.24148 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 76 |  | 16 | 11 | 76 | 16 | 11 | 28.76 | 0.013177 | 0.00044 | 1022 | 0.082354 | 0.0054903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.082354 | 66.2588 | 66.2588 | 0%
North Coast | SO_Sonoma | DUNBAR 1102 | 7780 | DUNBAR 1102528 | 0.55611 | 70.5839 | 3.3278 | 0 | 3.3278 | 0 | 538 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1 | 989 |  | 180 | 120 | 989 | 180 | 120 | 335.61 | 0.0078787 | 0.00295 | 1023 | 0.26856 | 0.0054807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.26856 | 54.0891 | 54.0891 | 0%
Sierra | SI_Sierra | APPLE HILL 1103 | 4238 | APPLE HILL 11038412 | 3.4028 | 503.8134 | 19.9564 | 0 | 19.9564 | 0 | 9649 | 471 | 235 | 227 | 235 | 227 | 0 | 443 | 1 | 18006 |  | 3399 | 2312 | 17535 | 3164 | 2085 | 5912.83 | 0.0067542 | 0.04444 | 1024 | 1.6107 | 0.0054785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4. >30 - 40% | 2. >10 - 20% | 1.6107 | 158.5453 | 170.321 | 0%
North Coast | SO_Sonoma | SONOMA 1103 | 7539 | SONOMA 11033052 | 1.8493 | 367.9213 | 11.9591 | 0 | 11.9591 | 0 | 1023 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 1 | 1870 |  | 339 | 224 | 1870 | 339 | 224 | 632.73 | 0.0050264 | 0.00354 | 1025 | 0.70408 | 0.005458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.70408 | 28.3466 | 28.3466 | 0%
Central Coast | LP_Los Padres | SAN MIGUEL 1106 | 1107 | SAN MIGUEL 1106circuit_breaker | 3.9107 | 749.7423 | 32.439 | 0 | 32.439 | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 376 | 1 | 421 |  | 78 | 52 | 421 | 78 | 52 | 144.75 | 0.005216 | 0.00085 | 1026 | 0.75051 | 0.0054385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.75051 | 2.4045 | 2.4045 | 0%
Bay Area | DI_Diablo | LAKEWOOD 2109 | 8732 | LAKEWOOD 210964992 | 7e-06 | 3.6116 | 0.80284 | 0 | 0.80284 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1 | 87 |  | 18 | 13 | 87 | 18 | 13 | 32.49 | 1.9382e-06 | 0 | 1027 | 0.03793 | 0.0054186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.03793 | 22.4204 | 22.4204 | 0%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1107 | 4497 | SAN LUIS OBISPO 1107V02 | 2.8683 | 423.4153 | 17.0754 | 0 | 17.0754 | 0 | 601 | 0 | 0 | 0 | 0 | 0 | 0 | 358 | 1 | 1104 |  | 201 | 133 | 1104 | 201 | 133 | 374.73 | 0.0067742 | 0.00283 | 1028 | 1.1855 | 0.0054134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 1.1855 | 11.7713 | 11.7713 | 0%
Sierra | SI_Sierra | FORESTHILL 1102 | 589 | FORESTHILL 11022106 | 3.5587 | 662.4695 | 26.8095 | 0.86496 | 25.9445 | 12.582 | 10015 | 11001 | 5076 | 4507 | 2163 | 1928 | 0 | 1206 | 0.53069 | 20659 |  | 6819 | 5656 | 9658 | 4656 | 3728 | 7247.94 | 0.0053719 | 0.05201 | 1029 | 2.4513 | 0.0054111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4. >30 - 40% | 2. >10 - 20% | 2.3722 | 179.4599 | 254.3504 | 3.226%
North Valley | NV_North Valley | WYANDOTTE 1103 | 4605 | WYANDOTTE 11031508 | 3.2858 | 601.2569 | 26.3981 | 0 | 26.3981 | 0 | 4210 | 0 | 0 | 0 | 0 | 0 | 0 | 528 | 1 | 7658 |  | 1383 | 912 | 7658 | 1383 | 912 | 2583.93 | 0.0054648 | 0.01572 | 1030 | 1.9154 | 0.0053954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 1.9154 | 52.3901 | 52.3901 | 0%
North Valley | NV_North Valley | NOTRE DAME 1104 | 8242 | NOTRE DAME 11042408 | 0.99456 | 259.8679 | 12.0398 | 0 | 12.0398 | 0 | 643 | 0 | 0 | 0 | 0 | 0 | 0 | 246 | 1 | 1180 |  | 215 | 142 | 1180 | 215 | 142 | 400.75 | 0.0038272 | 0.00171 | 1031 | 0.44151 | 0.0053843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.44151 | 17.8575 | 17.8575 | 0%
Central Coast | SJ_San Jose | MILPITAS 1109 | 5846 | MILPITAS 1109XR524 | 0.63571 | 213.6714 | 10.9786 | 0 | 10.9786 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 1 | 123 |  | 24 | 17 | 123 | 24 | 17 | 43.95 | 0.0029752 | 0.00015 | 1032 | 0.11833 | 0.0053788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.11833 | 2.1861 | 2.1861 | 0%
North Coast | SO_Sonoma | GEYSERVILLE 1102 | 128 | GEYSERVILLE 1102522 | 1.1176 | 169.7399 | 7.5784 | 0.9375 | 6.6409 | 2.2555 | 532 | 46 | 9 | 0 | 0 | 0 | 0 | 218 | 0.70238 | 733 |  | 134 | 83 | 687 | 134 | 83 | 245.41 | 0.0065844 | 0.00183 | 1033 | 0.51054 | 0.0053741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.44738 | 20.178 | 17.6818 | 12.37%
Bay Area | NB_North Bay | STAFFORD 1102 | 9742 | STAFFORD 1102circuit_breaker | 0.18233 | 8.4698 | 0.17614 | 0 | 0.17614 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 41 |  | 9 | 7 | 41 | 9 | 7 | 16.02 | 0.021527 | 0.0004 | 1034 | 0.016045 | 0.0053485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.016045 | 51.0968 | 51.0968 | 0%
Sierra | SI_Sierra | HIGGINS 1104 | 6849 | HIGGINS 1104circuit_breaker | 1.3465 | 172.1333 | 7.8328 | 0 | 7.8328 | 0 | 1010 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 1 | 1846 |  | 335 | 222 | 1846 | 335 | 222 | 625.09 | 0.0078222 | 0.00545 | 1035 | 0.72959 | 0.0052869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.72959 | 42.7691 | 42.7691 | 0%
Central Valley | YO_Yosemite | PEORIA 1705 | 1092 | PEORIA 17056697 | 0.69067 | 95.7028 | 4.2585 | 1.5593 | 2.6992 | 1.5739 | 250 | 291 | 22 | 19 | 22 | 19 | 0 | 103 | 0.63042 | 585 |  | 76 | 55 | 294 | 54 | 36 | 100.44 | 0.0072168 | 0.00081 | 1036 | 0.32247 | 0.0052863 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.20439 | 20.0056 | 17.8466 | 36.62%
North Coast | SO_Sonoma | DUNBAR 1101 | 4941 | DUNBAR 110147964 | 0.59778 | 177.1733 | 6.2492 | 1.7545 | 4.4947 | 4.2106 | 678 | 1154 | 500 | 291 | 0 | 0 | 0 | 222 | 0.32622 | 1560 |  | 574 | 340 | 406 | 574 | 340 | 822.92 | 0.003374 | 0.00403 | 1037 | 0.34312 | 0.0052788 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.24679 | 127.7061 | 91.8511 | 28.08%
Sierra | SI_Sierra | BELL 1108 | 2222 | BELL 1108circuit_breaker | 1.6578 | 143.1123 | 5.6011 | 2.0803 | 3.5208 | 2.6968 | 549 | 843 | 253 | 200 | 216 | 171 | 0 | 231 | 0.51853 | 1366 |  | 348 | 263 | 523 | 132 | 92 | 227.91 | 0.011584 | 0.00318 | 1038 | 0.33725 | 0.0052695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.21199 | 37.4911 | 62.1302 | 37.14%
Central Valley | YO_Yosemite | CURTIS 1705 | 4728 | CURTIS 1705circuit_breaker | 0.93149 | 308.1169 | 12.6492 | 8.0381 | 4.6114 | 12.4477 | 1845 | 3294 | 1321 | 755 | 1190 | 676 | 0 | 520 | 0.015931 | 3348 |  | 1331 | 761 | 54 | 141 | 85 | 198.03 | 0.0030232 | 0.00089 | 1039 | 0.80941 | 0.0052559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.29508 | 30.5766 | 105.2237 | 63.55%
Bay Area | NB_North Bay | ALTO 1120 | 2046 | ALTO 11201214 | 0.42201 | 119.7651 | 3.9326 | 0 | 3.9326 | 0 | 554 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 1 | 1018 |  | 186 | 123 | 1018 | 186 | 123 | 346.44 | 0.0035237 | 0.00136 | 1040 | 0.28374 | 0.0052545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.28374 | 47.2972 | 47.2972 | 0%
Bay Area | DI_Diablo | TASSAJARA 2112 | 2752 | TASSAJARA 211238868 | 0.17893 | 34.9246 | 1.886 | 0 | 1.886 | 0 | 389 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1 | 719 |  | 132 | 88 | 719 | 132 | 88 | 245.55 | 0.0051234 | 0.00141 | 1041 | 0.12081 | 0.0052524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.12081 | 69.99 | 69.99 | 0%
Central Valley | YO_Yosemite | CURTIS 1703 | 926 | CURTIS 17036064 | 3.687 | 490.3494 | 19.3616 | 16.1447 | 3.2169 | 18.7621 | 1509 | 2247 | 153 | 97 | 128 | 79 | 0 | 643 | 0.03096 | 2332 |  | 168 | 107 | 85 | 40 | 28 | 62.45 | 0.0075191 | 0.00063 | 1042 | 1.3601 | 0.0052515 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.22598 | 12.4345 | 8.677 | 83.39%
Central Valley | YO_Yosemite | PEORIA 1705 | 3291 | PEORIA 17051834 | 4.3112 | 599.0701 | 21.7063 | 1.9292 | 19.7771 | 4.6102 | 796 | 373 | 76 | 45 | 2 | 1 | 0 | 468 | 0.78761 | 1521 |  | 285 | 183 | 1148 | 283 | 182 | 491.03 | 0.0071965 | 0.00423 | 1043 | 1.0599 | 0.0052213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.96572 | 14.3095 | 13.1299 | 8.888%
Sierra | SI_Sierra | BELL 1108 | 1793 | BELL 11082226 | 3.2047 | 592.8241 | 23.2231 | 19.0746 | 4.1485 | 20.6689 | 3552 | 7862 | 2455 | 2058 | 2378 | 2000 | 0 | 889 | 0.10998 | 8573 |  | 2583 | 2143 | 711 | 205 | 143 | 344.84 | 0.0054059 | 0.0023 | 1044 | 1.8417 | 0.0052026 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.329 | 49.4156 | 111.2254 | 82.14%
Central Coast | LP_Los Padres | OCEANO 1102 | 1994 | V56 | 1.1682 | 212.6886 | 7.8981 | 0 | 7.8981 | 0 | 411 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 1 | 759 |  | 139 | 92 | 759 | 139 | 92 | 258.74 | 0.0054924 | 0.00159 | 1045 | 0.48304 | 0.005194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.48304 | 17.5992 | 17.5992 | 0%
North Valley | NV_North Valley | VOLTA 1101 | 2835 | VOLTA 11011596 | 2.1626 | 445.45 | 21.6604 | 0 | 21.6604 | 0 | 6756 | 0 | 0 | 0 | 0 | 0 | 0 | 462 | 1 | 12281 |  | 2217 | 1461 | 12281 | 2217 | 1461 | 4142.58 | 0.0048549 | 0.02238 | 1046 | 1.1515 | 0.005187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 1.1515 | 102.3526 | 102.3526 | 0%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1104 | 2675 | SAN LUIS OBISPO 1104V10 | 0.5208 | 42.2841 | 2.197 | 0 | 2.197 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 1 | 40 |  | 9 | 7 | 40 | 9 | 7 | 15.93 | 0.012317 | 0.00023 | 1047 | 0.082715 | 0.0051697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.082715 | 4.0966 | 4.0966 | 0%
North Valley | NV_North Valley | WILDWOOD 1101 | 8885 | WILDWOOD 11011576 | 1.1025 | 186.3573 | 7.7284 | 0 | 7.7284 | 0 | 3504 | 0 | 0 | 0 | 0 | 0 | 0 | 158 | 1 | 6375 |  | 1152 | 760 | 6375 | 1152 | 760 | 2151.99 | 0.0059163 | 0.01417 | 1049 | 0.59736 | 0.0051496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.59736 | 149.0604 | 149.0604 | 0%
North Coast | HU_Humboldt | CARLOTTA 1121 | 7936 | CARLOTTA 112142896 | 0.23256 | 42.4195 | 2.2095 | 0 | 2.2095 | 0.042424 | 634 | 66 | 29 | 19 | 0 | 0 | 0 | 48 | 0.9808 | 1207 |  | 237 | 157 | 1141 | 237 | 157 | 427.38 | 0.0054824 | 0.0027 | 1050 | 0.16929 | 0.0051299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.16929 | 107.2656 | 107.2656 | 0%
Bay Area | DI_Diablo | TASSAJARA 2108 | 4414 | TASSAJARA 210865438 | 0.098167 | 19.5001 | 0.73201 | 0 | 0.73201 | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 292 |  | 55 | 37 | 292 | 55 | 37 | 101.63 | 0.0050342 | 0.00058 | 1051 | 0.056223 | 0.0051112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.056223 | 75.1358 | 75.1358 | 0%
North Valley | NV_North Valley | WYANDOTTE 1102 | 7247 | WYANDOTTE 110213044 | 0.5257 | 113.279 | 4.1131 | 0 | 4.1131 | 0 | 367 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 1 | 679 |  | 124 | 83 | 679 | 124 | 83 | 230.99 | 0.0046407 | 0.0012 | 1052 | 0.28926 | 0.0050747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.28926 | 30.1478 | 30.1478 | 0%
Central Coast | LP_Los Padres | ATASCADERO 1103 | 5717 | TEMPLETON 2113A10 | 0.082587 | 20.9515 | 0.14924 | 0 | 0.14924 | 0.14924 | 22 | 31 | 24 | 10 | 3 | 0 | 0 | 9 | 0 | 31 |  | 24 | 10 | 0 | 21 | 10 | 28.77 | 0.0039418 | 0.00017 | 1053 | 1.3839 | 0.0050692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 1.3839 | 140.7107 | 160.8122 | 0%
North Coast | HU_Humboldt | CALPELLA 1101 | 4409 | CALPELLA 1101circuit_breaker | 1.3453 | 251.9913 | 11.9947 | 0 | 11.9947 | 0 | 795 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 1 | 1456 |  | 265 | 175 | 1456 | 265 | 175 | 494.09 | 0.0053388 | 0.00294 | 1054 | 0.58788 | 0.0050679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.58788 | 22.0931 | 22.0931 | 0%
North Coast | SO_Sonoma | LAKEVILLE 1102 | 8669 | LAKEVILLE 110287432 | 1.414 | 206.9053 | 8.4337 | 7.8653 | 0.56837 | 8.4337 | 244 | 328 | 100 | 63 | 72 | 52 | 0 | 205 | 0 | 328 |  | 100 | 63 | 0 | 28 | 11 | 38.36 | 0.006834 | 0.0004 | 1055 | 0.28885 | 0.0050676 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.019467 | 49.2636 | 11.8572 | 93.26%
Sierra | SI_Sierra | SHINGLE SPRINGS 2108 | 7229 | SHINGLE SPRINGS 2108circuit_breaker | 1.1e-05 | 2.1588 | 0.091667 | 0 | 0.091667 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 14 |  | 5 | 4 | 14 | 5 | 4 | 8.11 | 5.0953e-06 | 0 | 1056 | 0.10127 | 0.0050637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.10127 | 54.5455 | 54.5455 | 0%
North Coast | HU_Humboldt | ANNAPOLIS 1101 | 8114 | ANNAPOLIS 1101608 | 0.89868 | 386.5149 | 18.1716 | 0 | 18.1716 | 0 | 7527 | 0 | 0 | 0 | 0 | 0 | 0 | 245 | 1 | 13681 |  | 2469 | 1628 | 13681 | 2469 | 1628 | 4613.82 | 0.0023251 | 0.01194 | 1057 | 0.48487 | 0.0049987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.48487 | 135.8714 | 135.8714 | 0%
Central Valley | ST_Stockton | CLAY 1103 | 2473 | CLAY 110334338 | 0.9712 | 192.7193 | 9.7725 | 0 | 9.7725 | 0 | 348 | 0 | 0 | 0 | 0 | 0 | 0 | 197 | 1 | 644 |  | 118 | 79 | 644 | 118 | 79 | 219.62 | 0.0050394 | 0.00124 | 1058 | 0.26981 | 0.0049965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.26981 | 12.0747 | 12.0747 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2105 | 4387 | CAMP EVERS 210511010 | 0.10359 | 25.2186 | 1.6968 | 0 | 1.6968 | 0 | 1335 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 1 | 2437 |  | 441 | 292 | 2437 | 441 | 292 | 823.5 | 0.0041076 | 0.00377 | 1059 | 0.14962 | 0.0049874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.14962 | 259.904 | 259.904 | 0%
North Valley | NV_North Valley | OREGON TRAIL 1103 | 9262 | OREGON TRAIL 110346860 | 0.035466 | 12.1427 | 0.69602 | 0.63996 | 0.056061 | 0.69602 | 9 | 82 | 12 | 2 | 11 | 2 | 0 | 16 | 0 | 82 |  | 12 | 2 | 0 | 1 | 0 | 1.37 | 0.0029208 | 1e-05 | 1060 | 0.019814 | 0.0049535 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.0015959 | 17.8378 | 17.2408 | 91.95%
Central Valley | YO_Yosemite | CURTIS 1704 | 1923 | CURTIS 170411290 | 1.2907 | 248.6017 | 9.1489 | 5.8759 | 3.2729 | 8.6309 | 1676 | 2342 | 475 | 254 | 419 | 224 | 0 | 295 | 0.056618 | 2515 |  | 506 | 275 | 173 | 87 | 51 | 134.76 | 0.005192 | 0.00094 | 1061 | 0.55861 | 0.0049435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.19984 | 26.5818 | 55.3074 | 64.23%
North Coast | HU_Humboldt | LAYTONVILLE 1102 | 9040 | LAYTONVILLE 1102682 | 1.5408 | 316.3906 | 14.0371 | 0 | 14.0371 | 0 | 8526 | 0 | 0 | 0 | 0 | 0 | 0 | 261 | 1 | 15495 |  | 2797 | 1843 | 15495 | 2797 | 1843 | 5226.44 | 0.00487 | 0.02832 | 1062 | 1.1306 | 0.0049372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 1.1306 | 199.2574 | 199.2574 | 0%
North Coast | HU_Humboldt | WILLOW CREEK 1101 | 3469 | WILLOW CREEK 11014904 | 1.9232 | 418.1093 | 24.8337 | 0 | 24.8337 | 0.26269 | 7366 | 7 | 7 | 0 | 0 | 0 | 0 | 388 | 0.98942 | 13254 |  | 2398 | 1576 | 13247 | 2398 | 1576 | 4477.49 | 0.0045998 | 0.02294 | 1063 | 1.3923 | 0.0049372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 1.3923 | 96.5623 | 96.5623 | 0%
North Coast | SO_Sonoma | SANTA ROSA A 1111 | 984 | SANTA ROSA A 1111circuit_breaker | 0.037416 | 8.5492 | 0.31042 | 0.044508 | 0.26591 | 0.31042 | 64 | 131 | 42 | 13 | 19 | 0 | 0 | 9 | 0 | 131 |  | 42 | 13 | 0 | 23 | 13 | 31.51 | 0.0043765 | 0.00021 | 1064 | 0.024652 | 0.0049303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.021117 | 86.4957 | 135.302 | 14.34%
Bay Area | NB_North Bay | SILVERADO 2105 | 7013 | SILVERADO 2105658898 | 2.919 | 505.7768 | 16.9818 | 10.535 | 6.4468 | 16.9667 | 4276 | 10321 | 4609 | 2383 | 4039 | 1992 | 0 | 663 | 0.00089222 | 10328 |  | 4610 | 2384 | 7 | 571 | 392 | 782.9 | 0.0057713 | 0.00685 | 1065 | 1.1742 | 0.0049131 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.44578 | 88.5713 | 271.4668 | 62.04%
Central Coast | SJ_San Jose | LLAGAS 2107 | 7623 | LLAGAS 2107XR178 | 0.42985 | 32.0089 | 2.6288 | 0 | 2.6288 | 0 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 1 | 470 |  | 87 | 58 | 470 | 87 | 58 | 161.49 | 0.013429 | 0.00243 | 1066 | 0.04906 | 0.004906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.04906 | 33.0951 | 33.0951 | 0%
Sierra | SI_Sierra | EL DORADO PH 2101 | 1215 | EL DORADO PH 210126000 | 3.287 | 663.3657 | 33.5259 | 0 | 33.5259 | 2.1759 | 23030 | 680 | 673 | 623 | 3 | 3 | 0 | 1645 | 0.9351 | 39799 |  | 7730 | 5272 | 39119 | 7727 | 5269 | 14106.7 | 0.0049551 | 0.07962 | 1067 | 2.53 | 0.0048935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 4. >30 - 40% | 1. <= 10% | 2.53 | 230.4782 | 230.5677 | 0%
North Coast | SO_Sonoma | MIRABEL 1101 | 5420 | MIRABEL 1101298 | 1.3566 | 276.0134 | 10.4545 | 0.15549 | 10.2991 | 7.9455 | 6494 | 630 | 630 | 48 | 0 | 0 | 0 | 486 | 0.24 | 3463 |  | 1141 | 385 | 2833 | 1141 | 385 | 1818.14 | 0.0049151 | 0.01166 | 1068 | 1.0384 | 0.0048752 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 1.023 | 110.7869 | 109.1391 | 1.487%
North Valley | NV_North Valley | VOLTA 1102 | 3296 | VOLTA 11021646 | 2.9595 | 539.3191 | 23.6345 | 0 | 23.6345 | 0 | 9459 | 0 | 0 | 0 | 0 | 0 | 0 | 519 | 1 | 17190 |  | 3102 | 2044 | 17190 | 3102 | 2044 | 5796.84 | 0.0054875 | 0.0354 | 1069 | 1.5942 | 0.0048308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4. >30 - 40% | 2. >10 - 20% | 1.5942 | 131.249 | 131.249 | 0%
Central Valley | YO_Yosemite | PEORIA 1705 | 3803 | PEORIA 170510580 | 6.1193 | 226.0887 | 6.9633 | 0.20114 | 6.7621 | 0.32633 | 343 | 7 | 0 | 0 | 0 | 0 | 0 | 147 | 0.95314 | 612 |  | 111 | 74 | 605 | 111 | 74 | 206.52 | 0.027066 | 0.00625 | 1070 | 0.31862 | 0.0048275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.30941 | 16.415 | 15.9408 | 2.889%
North Coast | HU_Humboldt | EEL RIVER 1102 | 5880 | EEL RIVER 11024814 | 1.9138 | 610.1383 | 27.7273 | 22.4064 | 5.3208 | 27.678 | 3745 | 7802 | 1568 | 1074 | 726 | 475 | 0 | 599 | 0.001776 | 7814 |  | 1570 | 1075 | 12 | 844 | 600 | 1157.36 | 0.0031367 | 0.0055 | 1071 | 0.154 | 0.0048125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.029552 | 158.6218 | 56.623 | 80.81%
Central Valley | ST_Stockton | IONE 1101 | 6605 | IONE 1101circuit_breaker | 0.089458 | 24.6363 | 2.0936 | 0 | 2.0936 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 1 | 165 |  | 32 | 22 | 165 | 32 | 22 | 58.69 | 0.0036311 | 0.00024 | 1072 | 0.014423 | 0.0048076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.014423 | 15.285 | 15.285 | 0%
North Valley | NV_North Valley | WHITMORE 1101 | 3964 | WHITMORE 1101circuit_breaker | 0.72871 | 144.7315 | 6.2602 | 0 | 6.2602 | 0 | 2667 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 1 | 4855 |  | 878 | 579 | 4855 | 878 | 579 | 1639.81 | 0.0050349 | 0.00919 | 1074 | 0.42258 | 0.004802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.42258 | 140.2505 | 140.2505 | 0%
North Valley | NV_North Valley | GANSNER 1101 | 5873 | GANSNER 110137550 | 0.043055 | 13.75 | 1.2814 | 0 | 1.2814 | 0 | 346 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 1 | 641 |  | 118 | 78 | 641 | 118 | 78 | 219.35 | 0.0031313 | 0.00077 | 1075 | 0.043071 | 0.0047857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.043071 | 92.0839 | 92.0839 | 0%
Central Valley | ST_Stockton | CLAY 1103 | 2618 | CLAY 11031230 | 1.8368 | 396.9987 | 17.1659 | 0 | 17.1659 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 288 | 1 | 947 |  | 173 | 115 | 947 | 173 | 115 | 322.24 | 0.0046268 | 0.00166 | 1076 | 0.80242 | 0.0047763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.80242 | 10.0781 | 10.0781 | 0%
Sierra | SI_Sierra | HIGGINS 1110 | 432 | HIGGINS 1110circuit_breaker | 1.0618 | 257.285 | 11.4167 | 0 | 11.4167 | 0 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 276 | 1 | 3553 |  | 643 | 424 | 3553 | 643 | 424 | 1200.68 | 0.0041269 | 0.00552 | 1077 | 0.70421 | 0.0047581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.70421 | 56.3212 | 56.3212 | 0%
North Coast | HU_Humboldt | PHILO 1102 | 4466 | PHILO 1102928 | 1.4044 | 349.3315 | 14.0095 | 0 | 14.0095 | 0 | 6619 | 0 | 0 | 0 | 0 | 0 | 0 | 207 | 1 | 12032 |  | 2172 | 1432 | 12032 | 2172 | 1432 | 4058.52 | 0.0040201 | 0.01816 | 1078 | 1.1399 | 0.0047299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 1.1399 | 155.038 | 155.038 | 0%
North Coast | HU_Humboldt | KONOCTI 1102 | 2395 | KONOCTI 1102532 | 0.91023 | 199.9428 | 9.0489 | 6.4479 | 2.6011 | 9.0381 | 1867 | 4543 | 861 | 513 | 667 | 371 | 0 | 524 | 0.001193 | 4547 |  | 862 | 513 | 4 | 195 | 142 | 267.51 | 0.0045525 | 0.00185 | 1079 | 0.45268 | 0.0047155 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.13013 | 74.9672 | 95.2606 | 71.26%
North Coast | SO_Sonoma | BELLEVUE 2103 | 5056 | BELLEVUE 2103648 | 0.42561 | 84.7179 | 4.2328 | 0 | 4.2328 | 0 | 560 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 1 | 1029 |  | 188 | 124 | 1029 | 188 | 124 | 350.17 | 0.0050239 | 0.00196 | 1080 | 0.22065 | 0.0046946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.22065 | 44.4154 | 44.4154 | 0%
North Coast | SO_Sonoma | COTATI 1102 | 8169 | COTATI 1102462 | 0.65348 | 78.2513 | 2.69 | 2.2835 | 0.40644 | 2.6044 | 159 | 279 | 100 | 19 | 93 | 16 | 0 | 73 | 0.031824 | 289 |  | 102 | 20 | 10 | 9 | 4 | 13.23 | 0.0083511 | 0.00016 | 1081 | 0.070272 | 0.0046848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.010618 | 22.1435 | 37.9187 | 84.89%
Bay Area | MI_Mission | SUNOL 1101 | 4720 | SUNOL 1101MR196 | 0.59671 | 66.7441 | 3.5608 | 2.718 | 0.84299 | 3.3271 | 95 | 104 | 4 | 2 | 0 | 0 | 0 | 92 | 0.065635 | 116 |  | 6 | 4 | 12 | 6 | 4 | 9.3 | 0.0089403 | 0.00011 | 1082 | 0.079191 | 0.0046583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.018748 | 7.1175 | 1.685 | 76.33%
Central Valley | ST_Stockton | OLETA 1102 | 2312 | OLETA 11021204 | 2.4838 | 588.0524 | 25.8053 | 0.0011364 | 25.8042 | 0.26288 | 5348 | 330 | 123 | 108 | 0 | 0 | 0 | 474 | 0.98981 | 9955 |  | 1861 | 1254 | 9625 | 1861 | 1254 | 3415.82 | 0.0042238 | 0.01635 | 1083 | 1.4097 | 0.0046373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 1.4097 | 72.1201 | 72.117 | 0.004404%
Sierra | SI_Sierra | HIGGINS 1104 | 4334 | HIGGINS 11041006 | 1.5783 | 314.7491 | 11.0777 | 0.033144 | 11.0443 | 0.033144 | 3907 | 1 | 0 | 0 | 0 | 0 | 0 | 308 | 0.99701 | 7087 |  | 1280 | 844 | 7086 | 1280 | 844 | 2391.34 | 0.0050145 | 0.01335 | 1084 | 0.71806 | 0.0046326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.7159 | 115.8967 | 115.548 | 0.2992%
Central Coast | LP_Los Padres | ATASCADERO 1103 | 3035 | ATASCADERO 1103circuit_breaker | 0.71163 | 140.2591 | 6.658 | 0 | 6.658 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 239 | 1 | 739 |  | 135 | 90 | 739 | 135 | 90 | 251.46 | 0.0050737 | 0.00142 | 1085 | 0.30109 | 0.0046321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.30109 | 20.2765 | 20.2765 | 0%
Central Coast | LP_Los Padres | ZACA 1101 | 8121 | ZACA 1101Y72 | 0.88296 | 118.0092 | 5.9985 | 0 | 5.9985 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 1 | 141 |  | 27 | 19 | 141 | 27 | 19 | 49.68 | 0.0074821 | 0.00042 | 1086 | 0.060174 | 0.0046288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.060174 | 4.5011 | 4.5011 | 0%
North Coast | HU_Humboldt | HIGHLANDS 1103 | 5608 | HIGHLANDS 11034630 | 2.356 | 73.1323 | 3.3953 | 2.5502 | 0.84508 | 3.3953 | 286 | 604 | 176 | 67 | 134 | 38 | 0 | 139 | 0 | 604 |  | 176 | 67 | 0 | 42 | 29 | 57.54 | 0.032215 | 0.00281 | 1087 | 0.037028 | 0.0046285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.0092162 | 49.6997 | 51.8369 | 75.11%
Sierra | SI_Sierra | MOUNTAIN QUARRIES 2101 | 6701 | MOUNTAIN QUARRIES 21011180 | 1.26 | 288.6443 | 13.0413 | 0 | 13.0413 | 0 | 4343 | 0 | 0 | 0 | 0 | 0 | 0 | 309 | 1 | 7899 |  | 1427 | 941 | 7899 | 1427 | 941 | 2665.9 | 0.0043652 | 0.01295 | 1088 | 0.9995 | 0.0046273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.9995 | 109.4217 | 109.4217 | 0%
Sierra | SI_Sierra | ALLEGHANY 1101 | 788 | ALLEGHANY 1101806 | 1.0864 | 235.6249 | 11.7061 | 0 | 11.7061 | 0 | 6765 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 1 | 12297 |  | 2220 | 1463 | 12297 | 2220 | 1463 | 4148.13 | 0.0046109 | 0.02129 | 1089 | 0.75237 | 0.0045876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 0.75237 | 189.6454 | 189.6454 | 0%
North Coast | SO_Sonoma | COTATI 1105 | 882 | COTATI 11055156 | 0.60373 | 94.1278 | 4.5968 | 3.9695 | 0.62708 | 4.2833 | 196 | 476 | 34 | 9 | 24 | 6 | 0 | 166 | 0.068188 | 501 |  | 39 | 12 | 25 | 15 | 6 | 22.8 | 0.0064139 | 0.0002 | 1090 | 0.18187 | 0.0045467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.02481 | 23.9203 | 8.4842 | 86.35%
Central Valley | ST_Stockton | OLETA 1102 | 4514 | OLETA 110241396 | 0.76964 | 135.6233 | 6.8958 | 0 | 6.8958 | 0.26496 | 1977 | 3 | 3 | 2 | 0 | 0 | 0 | 192 | 0.96158 | 3467 |  | 630 | 416 | 3464 | 630 | 416 | 1174.86 | 0.0056748 | 0.00743 | 1091 | 0.35878 | 0.0045415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.35878 | 91.3595 | 91.3595 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1108 | 8624 | SAN RAFAEL 11081250 | 0.33769 | 57.1923 | 2.9723 | 0 | 2.9723 | 0 | 482 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1 | 888 |  | 162 | 108 | 888 | 162 | 108 | 301.86 | 0.0059045 | 0.00199 | 1092 | 0.18514 | 0.0045155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.18514 | 54.5024 | 54.5024 | 0%
North Coast | SO_Sonoma | PETALUMA C 1108 | 5134 | PETALUMA C 1108632 | 2.5026 | 373.6371 | 14.7794 | 13.2786 | 1.5008 | 14.639 | 162 | 407 | 113 | 49 | 72 | 18 | 0 | 379 | 0.0094957 | 410 |  | 114 | 49 | 3 | 42 | 31 | 57.81 | 0.0066979 | 0.00058 | 1093 | 0.0045132 | 0.0045132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.00045829 | 27.9859 | 7.7135 | 89.85%
Central Valley | ST_Stockton | MARTELL 1101 | 3987 | MARTELL 1101circuit_breaker | 0.91608 | 155.8596 | 5.3581 | 0.13371 | 5.2244 | 0.21667 | 402 | 15 | 9 | 2 | 0 | 0 | 0 | 220 | 0.95956 | 727 |  | 139 | 89 | 712 | 139 | 89 | 254.51 | 0.0058776 | 0.0017 | 1094 | 0.22898 | 0.0044898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.22327 | 26.6058 | 25.9418 | 2.495%
Central Valley | YO_Yosemite | CURTIS 1701 | 365 | CURTIS 1701circuit_breaker | 0.68239 | 250.0651 | 11.2547 | 2.2534 | 9.0015 | 3.0186 | 887 | 510 | 131 | 44 | 126 | 42 | 0 | 360 | 0.7318 | 1698 |  | 347 | 187 | 1188 | 221 | 145 | 409.69 | 0.0027289 | 0.00125 | 1095 | 0.46227 | 0.004488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.36972 | 24.5514 | 30.8315 | 20.02%
Central Coast | LP_Los Padres | ATASCADERO 1103 | 7057 | TEMPLETON 2113A12 | 0.037005 | 13.4274 | 0.012689 | 0 | 0.012689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.0027559 | 2e-05 | 1096 | 0.77108 | 0.0044571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.77108 | 315.2239 | 315.2239 | 0%
Central Valley | ST_Stockton | CALAVERAS CEMENT 1101 | 6237 | CALAVERAS CEMENT 11014786 | 1.6506 | 427.6021 | 15.8723 | 0.5875 | 15.2848 | 7.2487 | 1581 | 1002 | 979 | 622 | 492 | 219 | 3 | 648 | 0.54331 | 2569 |  | 1263 | 809 | 1567 | 771 | 590 | 1197.3 | 0.0038601 | 0.00619 | 1097 | 0.91303 | 0.0044538 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.87923 | 50.4421 | 79.5723 | 3.701%
Central Coast | LP_Los Padres | OCEANO 1104 | 4321 | OCEANO 1104Q06 | 1.6226 | 346.3149 | 12.7269 | 2.3462 | 10.3807 | 2.5341 | 819 | 279 | 47 | 11 | 40 | 7 | 1 | 577 | 0.80089 | 1480 |  | 265 | 155 | 1201 | 225 | 148 | 416.34 | 0.0046853 | 0.00219 | 1099 | 0.75429 | 0.004437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.61523 | 21.6749 | 20.822 | 18.44%
North Coast | HU_Humboldt | WILLOW CREEK 1103 | 8923 | WILLOW CREEK 11033090 | 0.76706 | 215.7903 | 10.5045 | 0 | 10.5045 | 0 | 4192 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 1 | 7625 |  | 1377 | 908 | 7625 | 1377 | 908 | 2572.74 | 0.0035546 | 0.01018 | 1100 | 0.64873 | 0.0044131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.64873 | 131.0861 | 131.0861 | 0%
North Coast | HU_Humboldt | POINT ARENA 1101 | 7477 | POINT ARENA 110183354 | 0.57738 | 124.8965 | 5.4773 | 0 | 5.4773 | 0 | 1446 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 1 | 2638 |  | 478 | 316 | 2638 | 478 | 316 | 892.28 | 0.0046229 | 0.00459 | 1101 | 0.088104 | 0.0044052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.088104 | 87.2697 | 87.2697 | 0%
Central Valley | ST_Stockton | MARTELL 1103 | 2785 | MARTELL 11033152 | 1.2041 | 352.6086 | 16.1994 | 0 | 16.1994 | 0 | 427 | 0 | 0 | 0 | 0 | 0 | 0 | 332 | 1 | 788 |  | 144 | 96 | 788 | 144 | 96 | 268.2 | 0.0034148 | 0.00102 | 1102 | 0.61966 | 0.0043948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.61966 | 8.8892 | 8.8892 | 0%
Sierra | SI_Sierra | ALLEGHANY 1102 | 1888 | ALLEGHANY 1102circuit_breaker | 1.513 | 357.2875 | 16.203 | 0 | 16.203 | 0 | 10105 | 0 | 0 | 0 | 0 | 0 | 0 | 471 | 1 | 18363 |  | 3314 | 2184 | 18363 | 3314 | 2184 | 6192.85 | 0.0042348 | 0.02918 | 1103 | 1.1338 | 0.0043945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 1.1338 | 204.5296 | 204.5296 | 0%
Sierra | SI_Sierra | BRUNSWICK 1106 | 256 | BRUNSWICK 11067099 | 1.1 | 187.8761 | 6.628 | 0.45871 | 6.1691 | 6.5299 | 2604 | 2572 | 1075 | 909 | 273 | 231 | 0 | 350 | 0.014802 | 2642 |  | 1088 | 917 | 70 | 815 | 686 | 1122.85 | 0.0058551 | 0.00992 | 1104 | 0.47272 | 0.004377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.43999 | 132.1094 | 164.1513 | 6.921%
Central Valley | ST_Stockton | CORRAL 1102 | 5452 | CORRAL 110214028 | 1.3598 | 81.2315 | 4.4585 | 0 | 4.4585 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 1 | 181 |  | 35 | 24 | 181 | 35 | 24 | 64.24 | 0.01674 | 0.00122 | 1105 | 0.1572 | 0.0043667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.1572 | 7.8501 | 7.8501 | 0%
Sierra | SI_Sierra | APPLE HILL 1103 | 208 | APPLE HILL 110313312 | 1.3858 | 334.5357 | 16.8771 | 0 | 16.8771 | 0 | 4517 | 0 | 0 | 0 | 0 | 0 | 0 | 399 | 1 | 8215 |  | 1484 | 978 | 8215 | 1484 | 978 | 2772.43 | 0.0041425 | 0.01278 | 1106 | 0.81174 | 0.0043642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.81174 | 87.9299 | 87.9299 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2110 | 5597 | TEMPLETON 2110N32 | 2.3627 | 677.4442 | 29.4672 | 0.069697 | 29.3975 | 0.069697 | 2127 | 12 | 0 | 0 | 0 | 0 | 0 | 836 | 0.99763 | 3878 |  | 699 | 461 | 3866 | 699 | 461 | 1305.57 | 0.0034876 | 0.00507 | 1107 | 1.2242 | 0.0043257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 1.2213 | 23.7775 | 23.7213 | 0.2365%
Sierra | SI_Sierra | MOUNTAIN QUARRIES 2101 | 156 | MOUNTAIN QUARRIES 21011346 | 3.0994 | 665.7449 | 30.16 | 0 | 30.16 | 0 | 4452 | 0 | 0 | 0 | 0 | 0 | 0 | 703 | 1 | 8097 |  | 1462 | 964 | 8097 | 1462 | 964 | 2731.67 | 0.0046555 | 0.01415 | 1108 | 2.0533 | 0.0043136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 2.0533 | 48.4747 | 48.4747 | 0%
North Coast | SO_Sonoma | MOLINO 1102 | 457 | MOLINO 110251788 | 0.97287 | 164.7014 | 6.7585 | 0 | 6.7585 | 0.14867 | 2934 | 5 | 5 | 1 | 4 | 0 | 0 | 271 | 0.978 | 5228 |  | 949 | 624 | 5223 | 945 | 624 | 1764.72 | 0.0059068 | 0.01161 | 1109 | 0.37168 | 0.0042722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.37168 | 139.8235 | 140.4153 | 0%
Sierra | SA_Sacramento | DOBBINS 1101 | 3850 | DOBBINS 11015202 | 1.3698 | 382.5166 | 16.6061 | 0 | 16.6061 | 0.51591 | 3875 | 690 | 350 | 340 | 298 | 290 | 0 | 368 | 0.96893 | 7520 |  | 1584 | 1154 | 6830 | 1286 | 864 | 2376.52 | 0.0035809 | 0.00958 | 1110 | 0.86432 | 0.0042368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.86432 | 77.4416 | 95.3869 | 0%
North Coast | SO_Sonoma | PENNGROVE 1101 | 3118 | PENNGROVE 1101170 | 1.9886 | 496.3242 | 18.8277 | 13.4426 | 5.385 | 18.8277 | 1509 | 1845 | 388 | 45 | 258 | 20 | 0 | 663 | 0 | 1845 |  | 388 | 45 | 0 | 130 | 25 | 178.1 | 0.0040066 | 0.00108 | 1111 | 0.99434 | 0.0042313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.2844 | 24.141 | 20.608 | 71.4%
North Valley | NV_North Valley | STILLWATER 1101 | 3742 | STILLWATER 11011320 | 2.6104 | 452.4414 | 20.5886 | 0 | 20.5886 | 0 | 4386 | 0 | 0 | 0 | 0 | 0 | 0 | 511 | 1 | 7977 |  | 1441 | 950 | 7977 | 1441 | 950 | 2692.1 | 0.0057696 | 0.01729 | 1112 | 1.1067 | 0.0042081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 1.1067 | 69.9901 | 69.9901 | 0%
North Coast | HU_Humboldt | POTTER VALLEY P H 1105 | 6423 | POTTER VALLEY P H 110576498 | 1.6161 | 376.241 | 14.5544 | 7.0763 | 7.4778 | 14.3843 | 4905 | 14275 | 2661 | 1752 | 1673 | 1017 | 0 | 389 | 0.011686 | 14379 |  | 2680 | 1764 | 104 | 1007 | 747 | 1388.95 | 0.0042954 | 0.00899 | 1113 | 0.64802 | 0.0042079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.33294 | 134.6645 | 184.1373 | 48.62%
Bay Area | NB_North Bay | SAN RAFAEL 1108 | 3498 | SAN RAFAEL 1108516 | 1.4839 | 219.6433 | 10.5 | 0 | 10.5 | 0 | 2497 | 0 | 0 | 0 | 0 | 0 | 0 | 374 | 1 | 4547 |  | 822 | 542 | 4547 | 822 | 542 | 1535.37 | 0.0067558 | 0.01155 | 1114 | 0.71062 | 0.0042048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.71062 | 78.2857 | 78.2857 | 0%
North Valley | NV_North Valley | ORO FINO 1102 | 6140 | ORO FINO 11022040 | 0.82287 | 167.9398 | 8.5943 | 0 | 8.5943 | 2.3494 | 5449 | 276 | 276 | 186 | 0 | 0 | 0 | 188 | 0.72663 | 7475 |  | 1576 | 1043 | 7199 | 1576 | 1043 | 2807.03 | 0.0048998 | 0.01606 | 1115 | 0.59411 | 0.0041839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.59411 | 183.377 | 183.377 | 0%
North Valley | NV_North Valley | GIRVAN 1102 | 1432 | GIRVAN 11029012 | 3.1607 | 341.4702 | 15.0557 | 0.48693 | 14.5687 | 0.48939 | 702 | 23 | 4 | 4 | 4 | 4 | 0 | 404 | 0.96749 | 1268 |  | 230 | 154 | 1245 | 226 | 150 | 421.67 | 0.009256 | 0.00435 | 1116 | 0.66427 | 0.0041778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.64279 | 15.5127 | 15.2766 | 3.234%
Central Valley | YO_Yosemite | MARIPOSA 2101 | 2372 | MARIPOSA 210190180 | 0.43335 | 116.61 | 3.9708 | 0.0066288 | 3.9642 | 0.075 | 278 | 15 | 7 | 5 | 7 | 5 | 0 | 103 | 0.98111 | 522 |  | 100 | 67 | 507 | 93 | 62 | 173.04 | 0.0037162 | 0.00072 | 1117 | 0.19218 | 0.0041778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.19186 | 23.4599 | 25.1836 | 0.1669%
Central Valley | YO_Yosemite | RACETRACK 1704 | 883 | RACETRACK 170455798 | 2.7714 | 590.9942 | 23.1534 | 19.5769 | 3.5763 | 23.1534 | 1596 | 3654 | 972 | 411 | 838 | 314 | 0 | 841 | 0 | 3654 |  | 972 | 411 | 0 | 134 | 97 | 183.58 | 0.0046894 | 0.00131 | 1118 | 1.0099 | 0.004173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.15599 | 37.4686 | 41.9809 | 84.55%
Central Valley | ST_Stockton | PINE GROVE 1102 | 6892 | PINE GROVE 110283098 | 0.88068 | 166.8864 | 7.4333 | 0.11951 | 7.3138 | 3.9345 | 2878 | 1477 | 1448 | 1312 | 397 | 363 | 0 | 406 | 0.4707 | 3943 |  | 1894 | 1606 | 2466 | 1497 | 1243 | 2272.83 | 0.0052771 | 0.01643 | 1119 | 0.5948 | 0.004102 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.58523 | 204.6808 | 254.7982 | 1.608%
North Coast | HU_Humboldt | UKIAH 1114 | 4034 | UKIAH 1114528 | 0.26857 | 79.6661 | 4.1706 | 0 | 4.1706 | 0 | 584 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1 | 1073 |  | 195 | 130 | 1073 | 195 | 130 | 363.72 | 0.0033712 | 0.00137 | 1120 | 0.13839 | 0.0040704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.13839 | 46.7554 | 46.7554 | 0%
Sierra | SI_Sierra | PLACERVILLE 1110 | 2508 | PLACERVILLE 111019582 | 2.4923 | 506.8046 | 21.2475 | 0 | 21.2475 | 0 | 2764 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 1 | 5032 |  | 909 | 600 | 5032 | 909 | 600 | 1698.21 | 0.0049177 | 0.0093 | 1121 | 1.216 | 0.0040668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 1.216 | 42.7814 | 42.7814 | 0%
North Coast | SO_Sonoma | MOLINO 1102 | 8139 | MOLINO 11026917 | 0.92973 | 182.1786 | 7.165 | 0.21799 | 6.947 | 7.0731 | 1763 | 421 | 409 | 173 | 0 | 0 | 1 | 246 | 0.01282 | 462 |  | 416 | 178 | 41 | 416 | 178 | 573.61 | 0.0051034 | 0.00441 | 1122 | 0.40192 | 0.0040598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.38969 | 59.8822 | 58.0603 | 3.042%
Central Coast | LP_Los Padres | PASO ROBLES 1103 | 8644 | PASO ROBLES 1103N52 | 1.0632 | 140.3896 | 6.3252 | 6.3252 | 0 | 6.3252 | 88 | 398 | 11 | 10 | 11 | 10 | 0 | 115 | 0 | 398 |  | 11 | 10 | 0 | 0 | 0 | 0 | 0.0075731 | 0 | 1123 | 0.15419 | 0.0040576 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0 | 0 | 1.7391 | 100%
North Coast | SO_Sonoma | MOLINO 1102 | 2193 | MOLINO 1102318 | 2.1187 | 489.7272 | 19.1587 | 0.46742 | 18.6913 | 19.018 | 12385 | 956 | 945 | 325 | 113 | 3 | 0 | 1031 | 0.0073449 | 1121 |  | 975 | 345 | 165 | 862 | 342 | 1195.79 | 0.0043264 | 0.00775 | 1124 | 1.3437 | 0.0040474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 1.3109 | 46.1177 | 50.8907 | 2.44%
Central Valley | ST_Stockton | OLETA 1101 | 6650 | OLETA 110151740 | 1.7594 | 304.0871 | 16.0508 | 13.1498 | 2.9009 | 16.0508 | 436 | 736 | 169 | 89 | 102 | 72 | 0 | 266 | 0 | 736 |  | 169 | 89 | 0 | 67 | 17 | 91.79 | 0.0057857 | 0.00081 | 1125 | 0.33591 | 0.0040471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.060711 | 23.0959 | 10.5291 | 81.93%
North Coast | HU_Humboldt | CALPELLA 1102 | 5862 | CALPELLA 1102circuit_breaker | 0.19047 | 45.2767 | 1.9492 | 0 | 1.9492 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 1 | 303 |  | 57 | 38 | 303 | 57 | 38 | 105.36 | 0.0042068 | 0.0005 | 1126 | 0.080005 | 0.0040003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.080005 | 29.2421 | 29.2421 | 0%
Central Coast | CC_Central Coast | JOLON 1102 | 3041 | JOLON 11027070 | 0.40704 | 102.0382 | 6.6678 | 0 | 6.6678 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 1 | 161 |  | 31 | 21 | 161 | 31 | 21 | 56.96 | 0.0039891 | 0.00026 | 1127 | 0.0039947 | 0.0039947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.0039947 | 4.6492 | 4.6492 | 0%
Bay Area | NB_North Bay | SILVERADO 2102 | 9446 | SILVERADO 2102circuit_breaker | 0.11677 | 15.8014 | 0.82879 | 0.0058712 | 0.82311 | 0.4322 | 176 | 26 | 23 | 3 | 23 | 3 | 0 | 40 | 0.47852 | 185 |  | 53 | 23 | 159 | 30 | 20 | 55.41 | 0.0073898 | 0.00046 | 1128 | 0.031956 | 0.0039945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.031737 | 36.4473 | 63.9488 | 0.7084%
Sierra | SI_Sierra | HIGGINS 1104 | 3340 | HIGGINS 1104324510 | 1.288 | 304.6696 | 11.8045 | 0.081629 | 11.7227 | 0.19205 | 4757 | 2 | 2 | 2 | 2 | 2 | 0 | 274 | 0.98373 | 8512 |  | 1539 | 1015 | 8510 | 1537 | 1013 | 2871.59 | 0.0042275 | 0.01351 | 1129 | 0.92912 | 0.0039877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.92268 | 131.1128 | 130.3735 | 0.6915%
North Valley | NV_North Valley | WYANDOTTE 1105 | 8293 | WYANDOTTE 1105circuit_breaker | 0.29538 | 124.1286 | 3.0148 | 0.49602 | 2.5186 | 0.49602 | 95 | 70 | 24 | 23 | 24 | 23 | 0 | 45 | 0.83547 | 224 |  | 53 | 43 | 154 | 29 | 20 | 53.59 | 0.0023796 | 0.00014 | 1130 | 0.20146 | 0.0039502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.1683 | 11.5145 | 17.5801 | 16.45%
Central Valley | ST_Stockton | FROGTOWN 1701 | 7336 | FROGTOWN 17027134 | 0.79456 | 403.8629 | 38.4688 | 0 | 38.4688 | 0 | 893 | 0 | 0 | 0 | 0 | 0 | 0 | 727 | 1 | 1634 |  | 297 | 196 | 1634 | 297 | 196 | 553.95 | 0.0019674 | 0.00122 | 1131 | 0.40683 | 0.0039498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.40683 | 7.7206 | 7.7206 | 0%
Central Coast | LP_Los Padres | OCEANO 1104 | 3521 | OCEANO 1104V38 | 1.3903 | 254.6708 | 10.7688 | 0 | 10.7688 | 0 | 310 | 10 | 1 | 1 | 1 | 1 | 0 | 412 | 1 | 585 |  | 107 | 72 | 575 | 106 | 71 | 196.97 | 0.0054593 | 0.0012 | 1132 | 0.46929 | 0.0039437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.46929 | 9.8433 | 9.9362 | 0%
Central Valley | FR_Fresno | SAND CREEK 1103 | 3747 | SAND CREEK 11037070 | 0.91996 | 396.8379 | 17.4292 | 0 | 17.4292 | 0 | 752 | 0 | 0 | 0 | 0 | 0 | 0 | 248 | 1 | 1378 |  | 250 | 166 | 1378 | 250 | 166 | 466.52 | 0.0023182 | 0.00121 | 1133 | 0.49271 | 0.0039417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.49271 | 14.3438 | 14.3438 | 0%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1107 | 8520 | SAN LUIS OBISPO 1107V62 | 0.93906 | 157.3699 | 6.3333 | 0 | 6.3333 | 0 | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 1 | 316 |  | 59 | 40 | 316 | 59 | 40 | 109.27 | 0.0059672 | 0.00073 | 1134 | 0.16126 | 0.0039331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.16126 | 9.3158 | 9.3158 | 0%
Bay Area | MI_Mission | SAN RAMON 2108 | 7100 | SAN RAMON 210853732 | 0.81387 | 229.0166 | 8.0468 | 6.2093 | 1.8377 | 8.0468 | 618 | 1338 | 325 | 76 | 214 | 38 | 3 | 366 | 0 | 1338 |  | 325 | 76 | 0 | 111 | 38 | 152.07 | 0.0035538 | 0.00082 | 1136 | 0.34857 | 0.0039165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.079605 | 60.4019 | 40.3888 | 77.16%
North Valley | NV_North Valley | VOLTA 1102 | 2548 | VOLTA 11021504 | 0.70393 | 195.72 | 7.5436 | 0 | 7.5436 | 0 | 5147 | 0 | 0 | 0 | 0 | 0 | 0 | 182 | 1 | 9359 |  | 1690 | 1114 | 9359 | 1690 | 1114 | 3157.61 | 0.0035966 | 0.01264 | 1137 | 0.53742 | 0.0038943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.53742 | 224.0321 | 224.0321 | 0%
Central Valley | ST_Stockton | CLAY 1103 | 8805 | CLAY 110359714 | 0.33279 | 106.5674 | 4.2723 | 0 | 4.2723 | 0.093939 | 118 | 6 | 2 | 0 | 0 | 0 | 0 | 89 | 0.97801 | 228 |  | 44 | 28 | 222 | 44 | 28 | 80.26 | 0.0031229 | 0.00029 | 1138 | 0.16343 | 0.0038911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.16343 | 10.2988 | 10.2988 | 0%
Central Valley | KE_Kern | POSO MOUNTAIN 2104 | 7781 | POSO MOUNTAIN 210448268 | 0.44065 | 92.9246 | 4.6553 | 0 | 4.6553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.004742 | 4e-05 | 1139 | 0.0077584 | 0.0038792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.0077584 | 0.85924 | 0.85924 | 0%
Central Valley | ST_Stockton | ELECTRA 1101 | 1955 | ELECTRA 1101circuit_breaker | 2.2461 | 816.6121 | 32.1634 | 0 | 32.1634 | 0 | 4523 | 0 | 0 | 0 | 0 | 0 | 0 | 682 | 1 | 8226 |  | 1486 | 979 | 8226 | 1486 | 979 | 2776.16 | 0.0027505 | 0.0085 | 1140 | 1.451 | 0.0038488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 1.451 | 46.2015 | 46.2015 | 0%
Sierra | SI_Sierra | COLUMBIA HILL 1101 | 1073 | COLUMBIA HILL 1101764 | 1.1863 | 329.6118 | 14.0259 | 0 | 14.0259 | 0 | 6840 | 0 | 0 | 0 | 0 | 0 | 0 | 652 | 1 | 12434 |  | 2244 | 1479 | 12434 | 2244 | 1479 | 4193.34 | 0.003599 | 0.01679 | 1141 | 0.8743 | 0.0038346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 0.8743 | 159.9892 | 159.9892 | 0%
North Coast | SO_Sonoma | COTATI 1103 | 2182 | COTATI 1103148 | 1.3706 | 309.3535 | 15.2277 | 0 | 15.2277 | 0 | 974 | 0 | 0 | 0 | 0 | 0 | 0 | 319 | 1 | 1781 |  | 323 | 214 | 1781 | 323 | 214 | 602.8 | 0.0044304 | 0.00298 | 1142 | 0.30253 | 0.0038295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.30253 | 21.2114 | 21.2114 | 0%
North Coast | SO_Sonoma | MONTE RIO 1111 | 513 | MONTE RIO 1111292 | 2.1341 | 104.0755 | 2.9068 | 0.23068 | 2.6761 | 2.8633 | 382 | 211 | 190 | 177 | 6 | 0 | 0 | 97 | 0.014986 | 222 |  | 192 | 178 | 11 | 186 | 178 | 255.81 | 0.020505 | 0.00793 | 1143 | 0.08029 | 0.0038233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.073918 | 69.5032 | 66.0516 | 7.936%
Sierra | SI_Sierra | BRUNSWICK 1106 | 953 | BRUNSWICK 110651484 | 2.5095 | 522.587 | 21.336 | 2.8303 | 18.5055 | 8.9826 | 9811 | 5532 | 2163 | 1844 | 1365 | 1211 | 0 | 1108 | 0.57899 | 15855 |  | 4026 | 3072 | 10323 | 2661 | 1861 | 4574.64 | 0.0048021 | 0.02657 | 1144 | 1.1964 | 0.0038102 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 1.0377 | 143.7951 | 188.6953 | 13.27%
Sierra | SI_Sierra | PENRYN 1107 | 2645 | PENRYN 1106circuit_breaker | 0.057524 | 9.2648 | 0.44754 | 0 | 0.44754 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 87 |  | 18 | 13 | 87 | 18 | 13 | 32.49 | 0.0062089 | 0.00023 | 1145 | 0.00381 | 0.00381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.00381 | 40.2201 | 40.2201 | 0%
Sierra | SI_Sierra | MOUNTAIN QUARRIES 2101 | 5451 | MOUNTAIN QUARRIES 21012422 | 0.71822 | 193.6839 | 8.4945 | 0 | 8.4945 | 0 | 3013 | 0 | 0 | 0 | 0 | 0 | 0 | 187 | 1 | 5484 |  | 991 | 654 | 5484 | 991 | 654 | 1851.23 | 0.0037082 | 0.00764 | 1146 | 0.46341 | 0.0037984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.46341 | 116.6636 | 116.6636 | 0%
Sierra | SI_Sierra | FORESTHILL 1101 | 3652 | FORESTHILL 110150486 | 1.2038 | 351.5124 | 13.0176 | 0.00075758 | 13.0169 | 6.7924 | 8161 | 2612 | 2108 | 1650 | 1374 | 1162 | 0 | 828 | 0.47821 | 9705 |  | 3388 | 2494 | 7093 | 2014 | 1332 | 3397.55 | 0.0034247 | 0.01434 | 1147 | 0.77858 | 0.0037979 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.77853 | 154.7225 | 260.2628 | 0.00582%
Sierra | SI_Sierra | BRUNSWICK 1105 | 2283 | BRUNSWICK 11052140 | 2.5966 | 896.3034 | 34.0612 | 1.5174 | 32.5438 | 14.6157 | 25599 | 5083 | 3686 | 3152 | 1192 | 1134 | 9 | 1872 | 0.5709 | 31629 |  | 8475 | 6307 | 26546 | 7283 | 5173 | 12366.85 | 0.002897 | 0.04387 | 1148 | 1.1607 | 0.0037933 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4. >30 - 40% | 2. >10 - 20% | 1.109 | 223.7911 | 248.817 | 4.455%
North Coast | SO_Sonoma | DUNBAR 1102 | 50 | DUNBAR 1102448 | 0.2629 | 79.9706 | 2.918 | 0 | 2.918 | 0 | 355 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1 | 657 |  | 120 | 80 | 657 | 120 | 80 | 223.53 | 0.0032874 | 0.00082 | 1149 | 0.155 | 0.0037804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.155 | 41.1242 | 41.1242 | 0%
Sierra | SI_Sierra | BANGOR 1101 | 5051 | BANGOR 11011806 | 0.87936 | 202.4855 | 8.0542 | 7.1136 | 0.94034 | 7.9839 | 741 | 3398 | 2349 | 2304 | 2299 | 2254 | 0 | 261 | 0.0087241 | 3410 |  | 2351 | 2305 | 12 | 52 | 51 | 72.32 | 0.0043429 | 0.00047 | 1150 | 0.39668 | 0.0037779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.046313 | 55.2991 | 291.8986 | 88.32%
Central Coast | LP_Los Padres | TEMPLETON 2110 | 8418 | TEMPLETON 2110N30 | 1.6289 | 442.0903 | 20.4928 | 0 | 20.4928 | 0 | 1426 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 1 | 2602 |  | 471 | 311 | 2602 | 471 | 311 | 879.45 | 0.0036845 | 0.00361 | 1151 | 0.60006 | 0.0037739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.60006 | 22.9837 | 22.9837 | 0%
North Coast | SO_Sonoma | RINCON 1103 | 5825 | RINCON 1103198 | 0.61869 | 199.0134 | 6.9019 | 2.2898 | 4.6121 | 6.9019 | 714 | 253 | 249 | 100 | 238 | 91 | 0 | 270 | 0 | 253 |  | 249 | 100 | 0 | 11 | 9 | 15.07 | 0.0031088 | 7e-05 | 1152 | 0.26772 | 0.0037707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.1789 | 2.385 | 36.0771 | 33.18%
Bay Area | DI_Diablo | TASSAJARA 2112 | 293 | TASSAJARA 2112D514R | 0.51132 | 46.7325 | 2.4244 | 0 | 2.4244 | 0 | 377 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1 | 697 |  | 128 | 85 | 697 | 128 | 85 | 238.09 | 0.010942 | 0.00291 | 1153 | 0.16865 | 0.0037478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.16865 | 52.7959 | 52.7959 | 0%
Sierra | SI_Sierra | HIGGINS 1107 | 9639 | HIGGINS 1107746082 | 0.10903 | 32.5736 | 1.0462 | 0 | 1.0462 | 0 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 1 | 297 |  | 56 | 38 | 297 | 56 | 38 | 103.45 | 0.0033472 | 0.00039 | 1154 | 0.041016 | 0.0037287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.041016 | 53.5264 | 53.5264 | 0%
Central Valley | YO_Yosemite | SAN JOAQUIN NO3 1103 | 5573 | SAN JOAQUIN #3 11035100 | 2.3333 | 630.7435 | 25.6025 | 0 | 25.6025 | 0 | 2963 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 1 | 5393 |  | 975 | 643 | 5393 | 975 | 643 | 1821.12 | 0.0036994 | 0.0075 | 1155 | 1.2288 | 0.0037235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 1.2288 | 38.0823 | 38.0823 | 0%
Bay Area | NB_North Bay | OLEMA 1101 | 2315 | OLEMA 1101320 | 0.15663 | 56.554 | 4.8557 | 0 | 4.8557 | 0 | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 113 | 1 | 566 |  | 104 | 69 | 566 | 104 | 69 | 193.42 | 0.0027697 | 0.0006 | 1156 | 0.13384 | 0.0037177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.13384 | 21.4182 | 21.4182 | 0%
North Coast | SO_Sonoma | COTATI 1102 | 8018 | COTATI 1102282 | 0.40252 | 68.8903 | 3.1042 | 2.432 | 0.67216 | 2.7134 | 236 | 287 | 104 | 6 | 87 | 5 | 0 | 137 | 0.12587 | 342 |  | 114 | 13 | 55 | 27 | 8 | 41.94 | 0.0058429 | 0.00033 | 1157 | 0.10732 | 0.0037007 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.023239 | 40.1691 | 36.7248 | 78.35%
North Coast | HU_Humboldt | POINT ARENA 1101 | 570 | POINT ARENA 1101circuit_breaker | 0.84378 | 336.7792 | 11.6589 | 0 | 11.6589 | 0 | 5958 | 0 | 0 | 0 | 0 | 0 | 0 | 216 | 1 | 10832 |  | 1956 | 1289 | 10832 | 1956 | 1289 | 3654.6 | 0.0025054 | 0.01019 | 1158 | 0.39755 | 0.003681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.39755 | 167.7688 | 167.7688 | 0%
Sierra | SI_Sierra | MOUNTAIN QUARRIES 2101 | 1867 | MOUNTAIN QUARRIES 21011184 | 1.229 | 305.8688 | 12.5629 | 0 | 12.5629 | 0 | 7274 | 0 | 0 | 0 | 0 | 0 | 0 | 405 | 1 | 13222 |  | 2387 | 1573 | 13222 | 2387 | 1573 | 4460.17 | 0.004018 | 0.01994 | 1159 | 0.7114 | 0.0036482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 0.7114 | 190.0042 | 190.0042 | 0%
North Coast | SO_Sonoma | GEYSERVILLE 1102 | 7128 | GEYSERVILLE 1102circuit_breaker | 0.51648 | 88.6198 | 2.0117 | 0.074432 | 1.9373 | 0.27576 | 249 | 22 | 13 | 6 | 0 | 0 | 0 | 63 | 0.86293 | 423 |  | 87 | 56 | 401 | 87 | 56 | 155.28 | 0.005828 | 0.00105 | 1160 | 0.083896 | 0.0036476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.080792 | 44.9076 | 43.2461 | 3.7%
North Valley | NV_North Valley | BUCKS CREEK 1103 | 9200 | BUCKS CREEK 1103circuit_breaker | 0.34789 | 55.4857 | 2.1288 | 0 | 2.1288 | 0 | 649 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 1 | 1191 |  | 217 | 144 | 1191 | 217 | 144 | 404.48 | 0.0062699 | 0.00283 | 1161 | 0.076361 | 0.0036362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.076361 | 101.9359 | 101.9359 | 0%
Central Valley | FR_Fresno | STONE CORRAL 1108 | 5124 | STONE CORRAL 11087100 | 0.13845 | 47.2447 | 3.0472 | 0 | 3.0472 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1 | 103 |  | 21 | 14 | 103 | 21 | 14 | 38.04 | 0.0029304 | 0.00013 | 1162 | 0.043472 | 0.0036227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.043472 | 6.8917 | 6.8917 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2110 | 2816 | TEMPLETON 2110R90 | 5.2683 | 1519.0823 | 65.9062 | 0.78485 | 65.1212 | 29.8661 | 6774 | 2108 | 2073 | 591 | 1104 | 329 | 1 | 1839 | 0.54684 | 8842 |  | 3288 | 1392 | 6734 | 2184 | 1063 | 3598.14 | 0.0034681 | 0.01575 | 1163 | 2.0874 | 0.0035928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 2.0626 | 33.5375 | 49.889 | 1.191%
North Valley | NV_North Valley | BIG BEND 1101 | 3235 | BIG BEND 1101180398 | 0.20918 | 128.0994 | 4.5498 | 0.32917 | 4.2206 | 0.39318 | 319 | 89 | 70 | 68 | 67 | 66 | 0 | 114 | 0.91358 | 629 |  | 169 | 134 | 540 | 102 | 68 | 188.34 | 0.0016329 | 0.00035 | 1164 | 0.28269 | 0.0035783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.26224 | 24.1669 | 37.1444 | 7.235%
Bay Area | NB_North Bay | SILVERADO 2103 | 1959 | SILVERADO 2103circuit_breaker | 1.1958 | 334.9112 | 11.8922 | 3.4085 | 8.4837 | 8.0583 | 1296 | 1876 | 1078 | 422 | 638 | 114 | 2 | 429 | 0.32239 | 2639 |  | 1216 | 513 | 763 | 578 | 399 | 860.53 | 0.0035706 | 0.00429 | 1165 | 0.48977 | 0.003575 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.34939 | 68.1306 | 102.2516 | 28.66%
Central Valley | ST_Stockton | CLAY 1103 | 1596 | CLAY 11037124 | 0.57221 | 224.8641 | 12.4218 | 0 | 12.4218 | 0 | 239 | 0 | 0 | 0 | 0 | 0 | 0 | 211 | 1 | 446 |  | 82 | 55 | 446 | 82 | 55 | 152.48 | 0.0025447 | 0.00043 | 1166 | 0.24991 | 0.0035702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.24991 | 6.6013 | 6.6013 | 0%
Central Coast | LP_Los Padres | OCEANO 1102 | 787 | circuit_breaker | 1.1514 | 503.2238 | 21.3364 | 0 | 21.3364 | 0 | 1218 | 0 | 0 | 0 | 0 | 0 | 0 | 436 | 1 | 2224 |  | 403 | 266 | 2224 | 403 | 266 | 752.27 | 0.0022881 | 0.00192 | 1167 | 0.74869 | 0.0035483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.74869 | 18.8879 | 18.8879 | 0%
North Valley | NV_North Valley | VOLTA 1102 | 1805 | VOLTA 11021650 | 1.3653 | 462.5267 | 21.7973 | 0 | 21.7973 | 0 | 11903 | 0 | 0 | 0 | 0 | 0 | 0 | 487 | 1 | 21628 |  | 3903 | 2572 | 21628 | 3903 | 2572 | 7293.63 | 0.0029519 | 0.02396 | 1168 | 1.0318 | 0.0035458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 1.0318 | 179.0585 | 179.0585 | 0%
North Coast | HU_Humboldt | ANNAPOLIS 1101 | 9592 | ANNAPOLIS 1101circuit_breaker | 0.016946 | 6.6374 | 0.22292 | 0 | 0.22292 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 38 |  | 9 | 7 | 38 | 9 | 7 | 15.75 | 0.0025531 | 5e-05 | 1170 | 0.0035147 | 0.0035147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.0035147 | 40.3738 | 40.3738 | 0%
North Coast | HU_Humboldt | MENDOCINO 1101 | 26 | MENDOCINO 1101circuit_breaker | 1.8605 | 329.0613 | 13.1794 | 0 | 13.1794 | 0 | 1613 | 0 | 0 | 0 | 0 | 0 | 0 | 277 | 1 | 2941 |  | 532 | 352 | 2941 | 532 | 352 | 993.53 | 0.0056538 | 0.00625 | 1171 | 0.54409 | 0.0034877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.54409 | 40.3662 | 40.3662 | 0%
North Coast | HU_Humboldt | UKIAH 1114 | 6406 | UKIAH 11143606 | 0.52369 | 226.9954 | 11.1076 | 0 | 11.1076 | 0 | 1433 | 0 | 0 | 0 | 0 | 0 | 0 | 146 | 1 | 2615 |  | 474 | 313 | 2615 | 474 | 313 | 884.73 | 0.0023071 | 0.00227 | 1172 | 0.33787 | 0.0034129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.33787 | 42.6736 | 42.6736 | 0%
Bay Area | MI_Mission | NORTH DUBLIN 2101 | 6388 | NORTH DUBLIN 2101circuit_breaker | 0.1081 | 23.3107 | 0.75284 | 0 | 0.75284 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1 | 16 |  | 5 | 4 | 16 | 5 | 4 | 8.29 | 0.0046374 | 5e-05 | 1173 | 0.023887 | 0.0034124 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.023887 | 6.6415 | 6.6415 | 0%
Central Coast | LP_Los Padres | SAN MIGUEL 1104 | 1592 | SAN MIGUEL 1104R66 | 0.52619 | 145.9128 | 5.9239 | 0 | 5.9239 | 0 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 1 | 159 |  | 31 | 21 | 159 | 31 | 21 | 56.78 | 0.0036062 | 0.00023 | 1174 | 0.050459 | 0.0033639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.050459 | 5.2331 | 5.2331 | 0%
North Coast | SO_Sonoma | DUNBAR 1103 | 6550 | DUNBAR 11033127 | 0.79895 | 225.1413 | 9.01 | 2.8593 | 6.1508 | 8.5123 | 223 | 84 | 84 | 34 | 40 | 4 | 1 | 294 | 0.055241 | 107 |  | 88 | 37 | 23 | 48 | 33 | 67.83 | 0.0035486 | 0.00035 | 1175 | 0.19799 | 0.0033558 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.13516 | 7.8039 | 9.7669 | 31.73%
Sierra | SI_Sierra | APPLE HILL 2102 | 998 | APPLE HILL 21029722 | 3.3723 | 943.2878 | 37.9511 | 0 | 37.9511 | 0 | 11829 | 0 | 0 | 0 | 0 | 0 | 0 | 1559 | 1 | 21493 |  | 3878 | 2556 | 21493 | 3878 | 2556 | 7247.23 | 0.003575 | 0.02883 | 1176 | 1.8951 | 0.0033541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 1.8951 | 102.184 | 102.184 | 0%
Central Coast | SJ_San Jose | EDENVALE 1102 | 6572 | EDENVALE 1102XR064 | 0.03646 | 9.0147 | 1.1227 | 0 | 1.1227 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 40 |  | 9 | 7 | 40 | 9 | 7 | 15.93 | 0.0040445 | 8e-05 | 1177 | 0.010042 | 0.0033473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.010042 | 8.0162 | 8.0162 | 0%
Central Valley | KE_Kern | CAL WATER 1102 | 7934 | CAL WATER 1102920714 | 0.28636 | 74.3343 | 2.9545 | 0 | 2.9545 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1 | 14 |  | 5 | 4 | 14 | 5 | 4 | 8.11 | 0.0038523 | 4e-05 | 1178 | 0.033432 | 0.0033432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.033432 | 1.6923 | 1.6923 | 0%
Central Valley | ST_Stockton | STANISLAUS 1701 | 2254 | STANISLAUS 17011812 | 1.3962 | 378.5292 | 17.6782 | 2.7517 | 14.9265 | 16.3915 | 8376 | 2405 | 2373 | 1808 | 1175 | 841 | 0 | 1064 | 0.072787 | 3513 |  | 2573 | 1940 | 1108 | 1398 | 1099 | 2014.98 | 0.0036885 | 0.01072 | 1179 | 1.0536 | 0.003334 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.88956 | 93.6588 | 145.5463 | 15.57%
Central Coast | CC_Central Coast | JOLON 1103 | 5899 | JOLON 1103circuit_breaker | 1.2915 | 206.2547 | 12.6502 | 0 | 12.6502 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 1 | 739 |  | 135 | 90 | 739 | 135 | 90 | 251.46 | 0.0062618 | 0.00176 | 1180 | 0.003332 | 0.003332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.003332 | 10.6718 | 10.6718 | 0%
Sierra | SI_Sierra | CLARKSVILLE 2109 | 7050 | CLARKSVILLE 21096502 | 0.15125 | 47.0052 | 2.6337 | 0 | 2.6337 | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 1 | 521 |  | 96 | 64 | 521 | 96 | 64 | 178.41 | 0.0032178 | 0.00064 | 1181 | 0.1195 | 0.0033193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.1195 | 36.4505 | 36.4505 | 0%
Central Coast | LP_Los Padres | ATASCADERO 1103 | 2055 | ATASCADERO 1103A46 | 0.089732 | 19.1449 | 1.0955 | 0 | 1.0955 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1 | 112 |  | 22 | 16 | 112 | 22 | 16 | 40.22 | 0.004687 | 0.00021 | 1182 | 0.023067 | 0.0032953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.023067 | 20.083 | 20.083 | 0%
Central Valley | ST_Stockton | CALAVERAS CEMENT 1101 | 8783 | CALAVERAS CEMENT 1101585 | 1.4221 | 346.3203 | 14.4973 | 0 | 14.4973 | 0 | 473 | 0 | 0 | 0 | 0 | 0 | 0 | 327 | 1 | 871 |  | 159 | 106 | 871 | 159 | 106 | 296.22 | 0.0041064 | 0.00136 | 1183 | 0.42004 | 0.0032816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.42004 | 10.9675 | 10.9675 | 0%
North Valley | NV_North Valley | ORO FINO 1102 | 9247 | ORO FINO 11022236 | 0.087709 | 68.7597 | 2.0938 | 0.0039773 | 2.0898 | 1.3578 | 286 | 115 | 115 | 90 | 1 | 1 | 0 | 60 | 0.35152 | 302 |  | 149 | 113 | 187 | 148 | 112 | 219.59 | 0.0012756 | 0.00039 | 1184 | 0.03936 | 0.00328 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.039285 | 70.8211 | 71.1642 | 0.19%
North Coast | HU_Humboldt | POINT ARENA 1101 | 510 | POINT ARENA 110147952 | 0.964 | 264.4133 | 9.6763 | 0 | 9.6763 | 0 | 6131 | 0 | 0 | 0 | 0 | 0 | 0 | 178 | 1 | 11146 |  | 2012 | 1326 | 11146 | 2012 | 1326 | 3759.58 | 0.0036458 | 0.01525 | 1185 | 0.10064 | 0.0032464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.10064 | 207.9302 | 207.9302 | 0%
North Coast | SO_Sonoma | FULTON 1107 | 857 | FULTON 110777670 | 0.46915 | 168.3493 | 6.5314 | 5.678 | 0.85341 | 6.5314 | 867 | 1801 | 674 | 488 | 567 | 416 | 7 | 397 | 0 | 1801 |  | 674 | 488 | 0 | 107 | 72 | 146.59 | 0.0027868 | 0.00062 | 1186 | 0.29854 | 0.003245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.039007 | 125.3795 | 103.1932 | 86.93%
Sierra | SI_Sierra | BONNIE NOOK 1102 | 2343 | BONNIE NOOK 1102circuit_breaker | 2.75 | 870.4159 | 35.5994 | 0.055682 | 35.5438 | 7.7114 | 23231 | 1870 | 1805 | 1606 | 1 | 1 | 0 | 2119 | 0.78339 | 34928 |  | 7769 | 5535 | 33058 | 7768 | 5534 | 13617.38 | 0.0031594 | 0.05103 | 1187 | 1.7863 | 0.0032185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4. >30 - 40% | 2. >10 - 20% | 1.7835 | 218.5476 | 218.2338 | 0.1564%
Central Valley | YO_Yosemite | COARSEGOLD 2102 | 1103 | COARSEGOLD 210210040 | 1.4343 | 473.6661 | 18.9299 | 0 | 18.9299 | 0 | 4046 | 4 | 2 | 1 | 0 | 0 | 0 | 478 | 1 | 7364 |  | 1331 | 878 | 7360 | 1331 | 878 | 2485.87 | 0.0030281 | 0.00838 | 1188 | 0.76472 | 0.0032131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.76472 | 70.312 | 70.312 | 0%
Sierra | SI_Sierra | MOUNTAIN QUARRIES 2101 | 1287 | MOUNTAIN QUARRIES 210192474 | 1.2575 | 360.9554 | 13.7589 | 0 | 13.7589 | 0 | 6096 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 1 | 11082 |  | 2001 | 1319 | 11082 | 2001 | 1319 | 3738.75 | 0.0034838 | 0.0145 | 1190 | 0.72716 | 0.0031893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.72716 | 145.4331 | 145.4331 | 0%
North Valley | NV_North Valley | JESSUP 1101 | 5942 | JESSUP 11013383 | 0.077053 | 31.1862 | 1.2339 | 0 | 1.2339 | 0 | 237 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1 | 443 |  | 82 | 55 | 443 | 82 | 55 | 152.21 | 0.0024707 | 0.00042 | 1191 | 0.07635 | 0.0031813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.07635 | 66.4559 | 66.4559 | 0%
Central Coast | DA_De Anza | STELLING 1110 | 2053 | STELLING 111060094 | 0.78906 | 262.6154 | 9.0419 | 0 | 9.0419 | 0 | 4666 | 0 | 0 | 0 | 0 | 0 | 0 | 157 | 1 | 8486 |  | 1532 | 1010 | 8486 | 1532 | 1010 | 2862.58 | 0.0030046 | 0.00957 | 1192 | 0.55155 | 0.0031698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.55155 | 169.4342 | 169.4342 | 0%
Central Coast | SJ_San Jose | MC KEE 1111 | 2127 | MC KEE 1111711900 | 0.92918 | 225.7263 | 8.5223 | 0 | 8.5223 | 0 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 1 | 548 |  | 101 | 67 | 548 | 101 | 67 | 187.69 | 0.0041164 | 0.00086 | 1193 | 0.2091 | 0.0031681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.2091 | 11.8512 | 11.8512 | 0%
Sierra | SI_Sierra | APPLE HILL 1104 | 3741 | APPLE HILL 110412832 | 1.2271 | 330.0639 | 14.0089 | 0 | 14.0089 | 0.80644 | 5517 | 4 | 4 | 4 | 0 | 0 | 0 | 541 | 0.94243 | 9458 |  | 1711 | 1129 | 9454 | 1711 | 1129 | 3194.93 | 0.0037176 | 0.01323 | 1194 | 0.66776 | 0.0031648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.66776 | 122.1366 | 122.1366 | 0%
Sierra | SI_Sierra | PLACERVILLE 2106 | 3014 | PLACERVILLE 21061104 | 4.0871 | 1194.9695 | 50.1216 | 0 | 50.1216 | 0 | 32113 | 0 | 0 | 0 | 0 | 0 | 0 | 2604 | 1 | 58329 |  | 10522 | 6932 | 58329 | 10522 | 6932 | 19664.75 | 0.0034203 | 0.07483 | 1195 | 2.4614 | 0.0031597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 4. >30 - 40% | 2. >10 - 20% | 2.4614 | 209.9295 | 209.9295 | 0%
Sierra | SI_Sierra | APPLE HILL 1104 | 4647 | APPLE HILL 110412842 | 1.1453 | 345.528 | 14.4125 | 0.0015152 | 14.411 | 2.4438 | 6892 | 343 | 336 | 283 | 34 | 33 | 0 | 786 | 0.83044 | 10747 |  | 2214 | 1521 | 10404 | 2180 | 1488 | 3922.96 | 0.0033146 | 0.01503 | 1196 | 0.81722 | 0.0031553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.81713 | 151.2735 | 153.6167 | 0.01051%
North Coast | HU_Humboldt | WILLOW CREEK 1102 | 8723 | WILLOW CREEK 1102circuit_breaker | 0.4718 | 148.3584 | 6.55 | 0.19375 | 6.3563 | 5.396 | 2045 | 717 | 716 | 86 | 208 | 29 | 0 | 337 | 0.17618 | 1373 |  | 835 | 164 | 656 | 627 | 135 | 918.03 | 0.0031801 | 0.00415 | 1197 | 0.3183 | 0.0031515 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.30889 | 98.6431 | 127.4809 | 2.958%
North Coast | SO_Sonoma | MOLINO 1101 | 3928 | MOLINO 11015042 | 0.37869 | 105.0227 | 4.4519 | 0.079924 | 4.3718 | 4.3699 | 1043 | 135 | 128 | 0 | 0 | 0 | 0 | 205 | 0.018421 | 170 |  | 134 | 4 | 35 | 134 | 4 | 186.73 | 0.0036058 | 0.001 | 1198 | 0.30085 | 0.0031339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.29544 | 30.6511 | 30.0995 | 1.795%
Sierra | SI_Sierra | NARROWS 2105 | 5422 | NARROWS 21052426 | 1.0645 | 230.3589 | 11.9845 | 0 | 11.9845 | 0 | 2558 | 0 | 0 | 0 | 0 | 0 | 0 | 298 | 1 | 4658 |  | 842 | 556 | 4658 | 842 | 556 | 1572.76 | 0.0046209 | 0.00809 | 1199 | 0.42154 | 0.0031226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.42154 | 70.2576 | 70.2576 | 0%
Sierra | SI_Sierra | FORESTHILL 1101 | 5266 | FORESTHILL 11011802 | 2.0856 | 557.4859 | 22.9585 | 0 | 22.9585 | 8.0886 | 11966 | 1225 | 1225 | 1007 | 1140 | 936 | 0 | 1453 | 0.64768 | 15307 |  | 3766 | 2681 | 14082 | 2626 | 1745 | 4865 | 0.0037411 | 0.02043 | 1200 | 1.1194 | 0.003118 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 1.1194 | 114.3802 | 164.0349 | 0%
Sierra | SI_Sierra | APPLE HILL 2102 | 2594 | APPLE HILL 21028372 | 5.3854 | 1414.2684 | 56.4121 | 20.7436 | 35.6686 | 43.2184 | 16095 | 18782 | 8615 | 7617 | 6599 | 5898 | 0 | 2233 | 0.23388 | 25621 |  | 9849 | 8430 | 6839 | 3250 | 2532 | 5068.01 | 0.0038079 | 0.02573 | 1201 | 2.4161 | 0.0031095 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 1.5277 | 91.1167 | 174.5901 | 36.77%
North Valley | NV_North Valley | VOLTA 1102 | 3263 | VOLTA 110297816 | 0.31434 | 107.5161 | 4.8367 | 0 | 4.8367 | 0 | 3396 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 1 | 6179 |  | 1116 | 736 | 6179 | 1116 | 736 | 2085.03 | 0.0029237 | 0.00678 | 1202 | 0.23853 | 0.0030978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.23853 | 230.7338 | 230.7338 | 0%
Sierra | SI_Sierra | SHINGLE SPRINGS 2110 | 1850 | SHINGLE SPRINGS 211051800 | 4.041 | 219.9633 | 9.6773 | 0.12481 | 9.5525 | 0.22633 | 1518 | 10 | 3 | 2 | 0 | 0 | 0 | 237 | 0.97661 | 2714 |  | 493 | 325 | 2704 | 493 | 325 | 918.77 | 0.018371 | 0.01883 | 1203 | 0.41086 | 0.0030892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 0.40556 | 51.6097 | 50.9441 | 1.29%
North Valley | NV_North Valley | ORO FINO 1102 | 1254 | ORO FINO 11022556 | 1.2606 | 153.9374 | 6.5559 | 0.35019 | 6.2057 | 5.2396 | 3240 | 1045 | 501 | 430 | 28 | 27 | 0 | 294 | 0.20078 | 2229 |  | 715 | 571 | 1184 | 687 | 544 | 1047.75 | 0.0081891 | 0.0117 | 1204 | 0.027772 | 0.0030858 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.026289 | 110.705 | 109.0625 | 5.342%
Central Coast | CC_Central Coast | RESERVATION ROAD 1101 | 198 | RESERVATION ROAD 1101circuit_breaker | 0.25684 | 86.4004 | 4.3835 | 4.2784 | 0.10511 | 4.2784 | 105 | 170 | 31 | 4 | 31 | 4 | 0 | 143 | 0.023979 | 175 |  | 32 | 5 | 5 | 1 | 1 | 1.82 | 0.0029726 | 1e-05 | 1205 | 0.17175 | 0.0030669 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.0041184 | 9.5135 | 7.3001 | 97.6%
North Coast | HU_Humboldt | GARBERVILLE 1101 | 584 | GARBERVILLE 1103circuit_breaker | 1.274 | 63.1463 | 3.0712 | 0 | 3.0712 | 0 | 439 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 1 | 809 |  | 148 | 98 | 809 | 148 | 98 | 275.57 | 0.020175 | 0.00621 | 1206 | 0.033644 | 0.0030585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.033644 | 48.1894 | 48.1894 | 0%
North Valley | NV_North Valley | SYCAMORE CREEK 1111 | 2906 | SYCAMORE CREEK 11112014 | 1.6255 | 596.0809 | 21.7542 | 5.6129 | 16.1413 | 11.6731 | 5393 | 2175 | 15 | 9 | 7 | 3 | 0 | 464 | 0.46341 | 6719 |  | 835 | 550 | 4544 | 828 | 547 | 1543.32 | 0.002727 | 0.0047 | 1207 | 0.89661 | 0.0030497 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.66527 | 51.297 | 38.3835 | 25.8%
North Coast | SO_Sonoma | PENNGROVE 1101 | 3569 | PENNGROVE 1101554 | 0.044426 | 32.1199 | 1.1962 | 0.73807 | 0.45814 | 1.011 | 157 | 189 | 42 | 7 | 30 | 4 | 0 | 53 | 0.15484 | 235 |  | 51 | 13 | 46 | 21 | 9 | 32.91 | 0.0013831 | 6e-05 | 1208 | 0.048649 | 0.0030406 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.018632 | 45.8371 | 42.6346 | 61.7%
Bay Area | NB_North Bay | OLEMA 1101 | 1879 | OLEMA 1101416 | 0.74389 | 376.7925 | 15.0462 | 5.9663 | 9.0801 | 8.6108 | 2053 | 757 | 428 | 122 | 332 | 35 | 0 | 381 | 0.42771 | 2357 |  | 717 | 313 | 1600 | 385 | 278 | 671.45 | 0.0019743 | 0.00158 | 1209 | 0.48038 | 0.0030404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.2899 | 42.4004 | 47.6532 | 39.65%
North Valley | NV_North Valley | PIT NO 1 1101 | 8904 | PIT NO 1 1101circuit_breaker | 0.48034 | 165.952 | 7.8116 | 0 | 7.8116 | 0 | 178 | 0 | 0 | 0 | 0 | 0 | 0 | 188 | 1 | 336 |  | 62 | 42 | 336 | 62 | 42 | 115.18 | 0.0028945 | 0.00037 | 1210 | 0.13921 | 0.0030262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.13921 | 7.937 | 7.937 | 0%
Central Valley | ST_Stockton | OLETA 1102 | 5033 | OLETA 11022642 | 0.21067 | 96.2335 | 4.6 | 0.0081439 | 4.5919 | 0.29735 | 265 | 32 | 2 | 1 | 0 | 0 | 0 | 91 | 0.93536 | 494 |  | 87 | 58 | 462 | 87 | 58 | 160.77 | 0.0021892 | 0.0004 | 1211 | 0.14514 | 0.0030238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.14489 | 18.9466 | 18.913 | 0.177%
Sierra | SI_Sierra | APPLE HILL 2102 | 3416 | APPLE HILL 21027502 | 1.7965 | 625.5632 | 24.9271 | 0.83939 | 24.0877 | 1.7231 | 11425 | 951 | 480 | 441 | 389 | 361 | 0 | 1262 | 0.93087 | 20276 |  | 3967 | 2739 | 19325 | 3578 | 2378 | 6641.11 | 0.0028717 | 0.02137 | 1212 | 1.0827 | 0.0029991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 1.0462 | 148.5406 | 159.1442 | 3.367%
Bay Area | MI_Mission | VINEYARD 2108 | 1730 | VINEYARD 2108MR172 | 0.79893 | 194.8222 | 6.665 | 0 | 6.665 | 0 | 472 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 1 | 869 |  | 159 | 106 | 869 | 159 | 106 | 296.04 | 0.0041008 | 0.00136 | 1213 | 0.21548 | 0.0029928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.21548 | 23.8561 | 23.8561 | 0%
North Coast | HU_Humboldt | HOOPA 1101 | 1082 | HOOPA 110137202 | 1.42 | 485.1563 | 23.9311 | 0 | 23.9311 | 0 | 12051 | 0 | 0 | 0 | 0 | 0 | 0 | 494 | 1 | 21897 |  | 3951 | 2604 | 21897 | 3951 | 2604 | 7383.6 | 0.0029268 | 0.02405 | 1214 | 0.95424 | 0.0029914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 0.95424 | 165.0992 | 165.0992 | 0%
Central Coast | SJ_San Jose | LLAGAS 2101 | 7415 | LLAGAS 2101XR586 | 0.25672 | 136.6247 | 4.8409 | 0 | 4.8409 | 0 | 143 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 1 | 272 |  | 51 | 35 | 272 | 51 | 35 | 94.35 | 0.001879 | 0.0002 | 1215 | 0.095685 | 0.0029901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.095685 | 10.5352 | 10.5352 | 0%
North Valley | NV_North Valley | MC ARTHUR 1101 | 1058 | MC ARTHUR 11011492 | 0.56493 | 221.0948 | 10.1443 | 0 | 10.1443 | 0 | 1666 | 0 | 0 | 0 | 0 | 0 | 0 | 223 | 1 | 3038 |  | 550 | 363 | 3038 | 550 | 363 | 1026.92 | 0.0025551 | 0.00292 | 1216 | 0.24576 | 0.002961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.24576 | 54.2175 | 54.2175 | 0%
North Valley | NV_North Valley | BIG BEND 1101 | 5327 | BIG BEND 1101641808 | 1.3764 | 627.2585 | 25.7928 | 0 | 25.7928 | 0 | 3407 | 0 | 0 | 0 | 0 | 0 | 0 | 583 | 1 | 6199 |  | 1120 | 739 | 6199 | 1120 | 739 | 2092.31 | 0.0021943 | 0.00511 | 1217 | 0.8397 | 0.0029463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.8397 | 43.423 | 43.423 | 0%
North Valley | NV_North Valley | GIRVAN 1101 | 9122 | GIRVAN 1101circuit_breaker | 0.14089 | 11.958 | 0.72708 | 0 | 0.72708 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1 | 161 |  | 31 | 21 | 161 | 31 | 21 | 56.96 | 0.011782 | 0.00076 | 1218 | 0.052634 | 0.0029241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.052634 | 42.6361 | 42.6361 | 0%
North Coast | HU_Humboldt | PHILO 1102 | 7283 | PHILO 11022600 | 1.444 | 440.489 | 17.9678 | 0 | 17.9678 | 0 | 10064 | 0 | 0 | 0 | 0 | 0 | 0 | 263 | 1 | 18288 |  | 3300 | 2175 | 18288 | 3300 | 2175 | 6166.92 | 0.0032782 | 0.0225 | 1219 | 0.7735 | 0.0029189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 0.7735 | 183.6619 | 183.6619 | 0%
North Valley | NV_North Valley | PIT NO 3 2101 | 8014 | PIT NO 3 21011482 | 0.85349 | 251.1991 | 11.7638 | 0 | 11.7638 | 0 | 5475 | 0 | 0 | 0 | 0 | 0 | 0 | 257 | 1 | 9955 |  | 1797 | 1185 | 9955 | 1797 | 1185 | 3357.84 | 0.0033977 | 0.0127 | 1220 | 0.242 | 0.0029157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.242 | 152.7564 | 152.7564 | 0%
North Coast | SO_Sonoma | MIRABEL 1101 | 3504 | MIRABEL 1101circuit_breaker | 0.038768 | 38.9192 | 1.9786 | 0 | 1.9786 | 0.021023 | 365 | 8 | 8 | 1 | 0 | 0 | 0 | 106 | 0.98937 | 676 |  | 130 | 83 | 668 | 130 | 83 | 238.22 | 0.00099612 | 0.00027 | 1221 | 0.10401 | 0.0028891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.10401 | 65.7031 | 65.7031 | 0%
Central Valley | ST_Stockton | PINE GROVE 1102 | 4557 | PINE GROVE 11023168 | 1.9928 | 708.7701 | 28.5634 | 0.48561 | 28.0778 | 4.3839 | 12070 | 1002 | 1000 | 674 | 770 | 527 | 0 | 1085 | 0.84652 | 19567 |  | 4350 | 2881 | 18565 | 3580 | 2354 | 6575.45 | 0.0028116 | 0.02093 | 1222 | 1.3617 | 0.0028728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 3. >20 - 30% | 1.3385 | 127.5027 | 152.2925 | 1.7%
North Coast | SO_Sonoma | MOLINO 1101 | 5973 | MOLINO 1101152 | 0.25571 | 67.6817 | 2.4011 | 0.041477 | 2.3597 | 2.2182 | 669 | 86 | 83 | 0 | 0 | 0 | 0 | 111 | 0.076195 | 180 |  | 100 | 11 | 94 | 100 | 11 | 145.46 | 0.0037781 | 0.00079 | 1223 | 0.11437 | 0.0028593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.11239 | 42.379 | 41.6469 | 1.727%
North Coast | HU_Humboldt | UPPER LAKE 1101 | 9730 | UPPER LAKE 1101circuit_breaker | 4.6046 | 42.7062 | 1.3701 | 1.0288 | 0.34129 | 1.0288 | 25 | 4 | 0 | 0 | 0 | 0 | 0 | 22 | 0.2491 | 18 |  | 3 | 2 | 14 | 3 | 2 | 5.37 | 0.10782 | 0.00067 | 1224 | 0.0057175 | 0.0028588 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.0014242 | 8.7902 | 2.1897 | 75.09%
Sierra | SI_Sierra | BONNIE NOOK 1101 | 4858 | BONNIE NOOK 1101circuit_breaker | 1.0423 | 341.6105 | 12.6655 | 0 | 12.6655 | 7.492 | 7275 | 636 | 631 | 531 | 2 | 2 | 0 | 797 | 0.40847 | 6037 |  | 1606 | 1174 | 5401 | 1604 | 1172 | 2683.57 | 0.0030511 | 0.01018 | 1225 | 0.66546 | 0.0028438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 4. >30 - 40% | 0.66546 | 126.6429 | 126.8008 | 0%
Central Coast | LP_Los Padres | ZACA 1101 | 3846 | ZACA 1101Y70 | 0.19672 | 99.3259 | 6.386 | 0 | 6.386 | 0 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 113 | 1 | 296 |  | 55 | 37 | 296 | 55 | 37 | 101.99 | 0.0019806 | 0.00023 | 1226 | 0.05957 | 0.0028366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.05957 | 8.6126 | 8.6126 | 0%
Bay Area | MI_Mission | LAS POSITAS 2108 | 7820 | LAS POSITAS 2108MR182 | 1.287 | 165.4713 | 6.6913 | 0 | 6.6913 | 0 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 1 | 385 |  | 71 | 48 | 385 | 71 | 48 | 131.92 | 0.0077776 | 0.00115 | 1227 | 0.12479 | 0.0028362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.12479 | 10.6108 | 10.6108 | 0%
Sierra | SI_Sierra | BRUNSWICK 1104 | 1085 | BRUNSWICK 11042112 | 1.4074 | 492.0422 | 18.3958 | 0.025379 | 18.3706 | 0.92311 | 5469 | 452 | 328 | 237 | 0 | 0 | 0 | 485 | 0.94982 | 9897 |  | 2033 | 1361 | 9445 | 2033 | 1361 | 3635.26 | 0.0028603 | 0.01209 | 1228 | 0.82634 | 0.0028299 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 4. >30 - 40% | 4. >30 - 40% | 0.82521 | 110.6657 | 110.5142 | 0.138%
North Coast | SO_Sonoma | COTATI 1103 | 7844 | COTATI 110387402 | 0.47188 | 231.432 | 10.7943 | 0 | 10.7943 | 0 | 371 | 0 | 0 | 0 | 0 | 0 | 0 | 189 | 1 | 686 |  | 126 | 84 | 686 | 126 | 84 | 234.36 | 0.002039 | 0.00053 | 1229 | 0.19198 | 0.0028233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.19198 | 11.6728 | 11.6728 | 0%
North Coast | HU_Humboldt | UKIAH 1111 | 6694 | UKIAH 11112504 | 1e-06 | 0.97222 | 0.095455 | 0 | 0.095455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 1.0286e-06 | 0 | 1230 | 0.0084498 | 0.0028166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 6. >50% | 0.0084498 | 41.9048 | 41.9048 | 0%
Bay Area | MI_Mission | SAN RAMON 2107 | 2636 | SAN RAMON 2107MR284 | 3.2797 | 473.3523 | 14.4125 | 0 | 14.4125 | 0 | 932 | 0 | 0 | 0 | 0 | 0 | 0 | 294 | 1 | 1705 |  | 309 | 205 | 1705 | 309 | 205 | 576.78 | 0.0069286 | 0.00445 | 1231 | 0.30384 | 0.0028133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4. >30 - 40% | 5. >40 - 50% | 0.30384 | 21.4397 | 21.4397 | 0%
North Coast | HU_Humboldt | HARTLEY 1101 | 7276 | HARTLEY 1101circuit_breaker | 0.078027 | 18.1842 | 0.97064 | 0 | 0.97064 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 116 |  | 23 | 16 | 116 | 23 | 16 | 41.95 | 0.0042909 | 0.00021 | 1232 | 0.047745 | 0.0028085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.047745 | 23.6956 | 23.6956 | 0%
North Coast | SO_Sonoma | SANTA ROSA A 1104 | 2432 | SANTA ROSA A 1104220 | 1.1966 | 208.1512 | 9.1871 | 5.0847 | 4.1025 | 9.1208 | 600 | 902 | 278 | 204 | 31 | 8 | 1 | 438 | 0.0072153 | 910 |  | 279 | 205 | 8 | 248 | 197 | 340.48 | 0.0057488 | 0.00296 | 1233 | 0.24998 | 0.0027776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.11163 | 60.4515 | 30.3686 | 55.35%
North Coast | SO_Sonoma | DUNBAR 1102 | 218 | DUNBAR 1102circuit_breaker | 0.54033 | 157.0978 | 7.3689 | 0 | 7.3689 | 0.98902 | 1163 | 568 | 212 | 105 | 0 | 0 | 0 | 208 | 0.86579 | 2407 |  | 545 | 325 | 1839 | 545 | 325 | 912.16 | 0.0034394 | 0.0039 | 1234 | 0.30404 | 0.002764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.30404 | 73.9591 | 73.9591 | 0%
Central Valley | YO_Yosemite | PEORIA 1704 | 850 | PEORIA 170459596 | 0.7281 | 379.9213 | 19.3407 | 16.568 | 2.7727 | 19.3407 | 411 | 1195 | 278 | 221 | 236 | 194 | 0 | 430 | 0 | 1195 |  | 278 | 221 | 0 | 42 | 27 | 57.54 | 0.0019165 | 0.00017 | 1235 | 0.29247 | 0.0027591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.041929 | 15.1475 | 14.3738 | 85.66%
Bay Area | NB_North Bay | MONTICELLO 1101 | 7999 | MONTICELLO 1101654 | 0.21707 | 150.8465 | 8.0248 | 0 | 8.0248 | 0 | 393 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 1 | 726 |  | 133 | 88 | 726 | 133 | 88 | 247.55 | 0.001439 | 0.0004 | 1236 | 0.14251 | 0.0027405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.14251 | 16.5736 | 16.5736 | 0%
North Coast | SO_Sonoma | MOLINO 1102 | 2815 | MOLINO 1102344 | 0.36527 | 61.6801 | 3.0566 | 0.11458 | 2.942 | 0.83239 | 954 | 46 | 34 | 0 | 0 | 0 | 0 | 130 | 0.72768 | 1316 |  | 264 | 152 | 1270 | 264 | 152 | 475.98 | 0.005922 | 0.00325 | 1237 | 0.046318 | 0.0027246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.044581 | 89.7335 | 86.3697 | 3.749%
Central Coast | SJ_San Jose | MORGAN HILL 2105 | 7812 | MORGAN HILL 2105XR268 | 0.4067 | 179.8247 | 7.2318 | 0 | 7.2318 | 0 | 1403 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 1 | 2560 |  | 464 | 306 | 2560 | 464 | 306 | 866.08 | 0.0022616 | 0.00218 | 1238 | 0.30662 | 0.0027135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.30662 | 64.1609 | 64.1609 | 0%
Sierra | SI_Sierra | DIAMOND SPRINGS 1106 | 600 | DIAMOND SPRINGS 11062100 | 2.7566 | 982.1098 | 41.3379 | 2.0405 | 39.2973 | 15.0797 | 14719 | 8106 | 5095 | 4577 | 2696 | 2492 | 0 | 1601 | 0.63521 | 25092 |  | 8160 | 6596 | 16986 | 5464 | 4104 | 9014.42 | 0.0028069 | 0.03189 | 1239 | 1.4372 | 0.0027117 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 3. >20 - 30% | 1.3663 | 139.0425 | 197.3976 | 4.936%
North Coast | SO_Sonoma | DUNBAR 1101 | 9157 | DUNBAR 1101343 | 0.38267 | 113.7517 | 4.1063 | 0.093939 | 4.0123 | 1.9097 | 973 | 69 | 68 | 49 | 12 | 8 | 0 | 179 | 0.53494 | 1021 |  | 241 | 163 | 952 | 229 | 155 | 399.41 | 0.0033641 | 0.0016 | 1240 | 0.18167 | 0.0027114 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.17751 | 57.0743 | 58.691 | 2.288%
Central Valley | ST_Stockton | PINE GROVE 1102 | 2655 | PINE GROVE 11023172 | 2.7132 | 852.5701 | 34.875 | 0.22633 | 34.6487 | 1.4661 | 16523 | 669 | 646 | 578 | 329 | 284 | 0 | 1908 | 0.95796 | 29425 |  | 5834 | 3996 | 28756 | 5505 | 3712 | 10129.89 | 0.0031823 | 0.03643 | 1241 | 1.4243 | 0.0027079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 5. >40 - 50% | 2. >10 - 20% | 1.4151 | 158.8805 | 167.2832 | 0.649%
North Coast | HU_Humboldt | NEWBURG 1132 | 150 | NEWBURG 11322074 | 0.043261 | 16.239 | 0.40587 | 0.070455 | 0.33542 | 0.40587 | 209 | 425 | 61 | 22 | 0 | 0 | 0 | 10 | 0 | 425 |  | 61 | 22 | 0 | 61 | 22 | 83.57 | 0.002664 | 0.00034 | 1243 | 0.037732 | 0.0026951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.031182 | 181.8634 | 150.294 | 17.36%
Central Valley | ST_Stockton | WEST POINT 1102 | 324 | WEST POINT 11024790 | 2.4134 | 796.0254 | 35.0199 | 6.3809 | 28.639 | 28.1932 | 16619 | 24359 | 5406 | 4384 | 3940 | 3183 | 0 | 1686 | 0.19494 | 30245 |  | 6468 | 5084 | 5886 | 2528 | 1901 | 3993.1 | 0.0030318 | 0.01594 | 1244 | 1.2181 | 0.0026949 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 0.99614 | 88.2712 | 184.6951 | 18.22%
Sierra | SI_Sierra | SHINGLE SPRINGS 2109 | 5835 | SHINGLE SPRINGS 210981390 | 1.1253 | 466.2211 | 17.1066 | 0 | 17.1066 | 0 | 2641 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 1 | 4808 |  | 869 | 573 | 4808 | 869 | 573 | 1623.25 | 0.0024138 | 0.00436 | 1245 | 0.67607 | 0.0026935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.67607 | 50.799 | 50.799 | 0%
Sierra | SI_Sierra | EL DORADO PH 2101 | 4817 | EL DORADO PH 210119612 | 0.61454 | 233.3748 | 10.0822 | 0.010795 | 10.0714 | 1.7127 | 6110 | 437 | 207 | 181 | 131 | 116 | 0 | 650 | 0.83013 | 9658 |  | 1872 | 1278 | 9221 | 1741 | 1162 | 3215.06 | 0.0026333 | 0.00953 | 1246 | 0.33111 | 0.002692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.33076 | 172.8657 | 185.6738 | 0.1071%
Sierra | SI_Sierra | ALLEGHANY 1101 | 9421 | ALLEGHANY 1101808 | 0.30806 | 110.5034 | 5.3451 | 0 | 5.3451 | 0 | 3633 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 1 | 6610 |  | 1194 | 787 | 6610 | 1194 | 787 | 2230.68 | 0.0027878 | 0.00692 | 1247 | 0.19639 | 0.0026902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.19639 | 223.3832 | 223.3832 | 0%
North Coast | HU_Humboldt | LAYTONVILLE 1101 | 7173 | LAYTONVILLE 110189606 | 5.9673 | 292.9455 | 12.9047 | 3.1348 | 9.7699 | 8.0534 | 4978 | 6559 | 1835 | 1214 | 1225 | 771 | 1 | 424 | 0.37593 | 9962 |  | 2449 | 1619 | 3403 | 1224 | 848 | 1983.15 | 0.02037 | 0.05185 | 1248 | 0.28372 | 0.0026766 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 5. >40 - 50% | 2. >10 - 20% | 0.2148 | 125.2829 | 189.7753 | 24.29%
Sierra | SI_Sierra | HIGGINS 1107 | 784 | HIGGINS 1107circuit_breaker | 0.051385 | 83.6874 | 4.1144 | 0 | 4.1144 | 0 | 942 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 1 | 1723 |  | 313 | 207 | 1723 | 313 | 207 | 583.88 | 0.00061401 | 0.0004 | 1250 | 0.2154 | 0.0026592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.2154 | 76.0744 | 76.0744 | 0%
Bay Area | NB_North Bay | BOLINAS 1101 | 9498 | BOLINAS 1101806 | 0.12168 | 58.262 | 2.79 | 0 | 2.79 | 0 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 1 | 328 |  | 61 | 41 | 328 | 61 | 41 | 113.09 | 0.0020884 | 0.00026 | 1251 | 0.10612 | 0.0026529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.10612 | 21.8641 | 21.8641 | 0%
Central Valley | FR_Fresno | AUBERRY 1101 | 1316 | AUBERRY 1101R2838 | 1.9583 | 499.5707 | 20.8712 | 0 | 20.8712 | 0 | 2588 | 0 | 0 | 0 | 0 | 0 | 0 | 799 | 1 | 4712 |  | 852 | 562 | 4712 | 852 | 562 | 1591.32 | 0.00392 | 0.00694 | 1252 | 0.4377 | 0.0026527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.4377 | 40.8218 | 40.8218 | 0%
Bay Area | NB_North Bay | NAPA 1102 | 1854 | NAPA 1112circuit_breaker | 0 | 0 | 0.71534 | 0 | 0.71534 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 29 |  | 7 | 6 | 29 | 7 | 6 | 12.2 | 0 | 0 | 1253 | 0.0079168 | 0.0026389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0079168 | 9.7855 | 9.7855 | 0%
North Coast | SO_Sonoma | MONTE RIO 1113 | 9369 | MONTE RIO 1113678 | 0.14069 | 19.8683 | 0.69034 | 0 | 0.69034 | 0.38504 | 488 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0.44225 | 397 |  | 73 | 48 | 397 | 73 | 48 | 135.74 | 0.0070812 | 0.00107 | 1254 | 0.07122 | 0.0026378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.07122 | 105.7449 | 105.7449 | 0%
Central Valley | YO_Yosemite | COARSEGOLD 2102 | 3908 | COARSEGOLD 21025380 | 0.76119 | 298.7331 | 11.8108 | 0.22311 | 11.5877 | 0.35909 | 1785 | 24 | 10 | 2 | 10 | 2 | 0 | 284 | 0.9696 | 3179 |  | 581 | 379 | 3155 | 571 | 377 | 1066.22 | 0.002548 | 0.00303 | 1255 | 0.49551 | 0.0026357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.48615 | 49.2764 | 49.1923 | 1.889%
Central Valley | ST_Stockton | CLAY 1101 | 6352 | CLAY 1101circuit_breaker | 0.029848 | 14.1153 | 0.47822 | 0.25985 | 0.21818 | 0.25985 | 17 | 25 | 7 | 1 | 7 | 1 | 0 | 13 | 0.45663 | 45 |  | 11 | 4 | 20 | 4 | 3 | 7.28 | 0.0021146 | 2e-05 | 1256 | 0.013126 | 0.0026253 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0059888 | 18.3333 | 23.002 | 54.34%
North Valley | NV_North Valley | WHITMORE 1101 | 2700 | WHITMORE 110145262 | 4.2177 | 644.0483 | 28.2055 | 0 | 28.2055 | 0 | 5837 | 0 | 0 | 0 | 0 | 0 | 0 | 588 | 1 | 10612 |  | 1916 | 1263 | 10612 | 1916 | 1263 | 3580 | 0.0065487 | 0.02609 | 1257 | 0.79248 | 0.0026155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 3. >20 - 30% | 0.79248 | 67.93 | 67.93 | 0%
Central Valley | YO_Yosemite | OAKHURST 1103 | 1211 | OAKHURST 11035480 | 4.3786 | 386.3597 | 15.339 | 0.53314 | 14.8059 | 12.115 | 3950 | 1991 | 1146 | 630 | 668 | 312 | 0 | 841 | 0.21019 | 3501 |  | 1419 | 810 | 1510 | 751 | 498 | 1164.77 | 0.011333 | 0.0177 | 1258 | 0.71402 | 0.0026154 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 3. >20 - 30% | 0.6892 | 50.7231 | 92.5092 | 3.476%
Central Coast | CC_Central Coast | BIG BASIN 1102 | 8168 | BIG BASIN 110211062 | 0.63006 | 289.8179 | 11.889 | 0 | 11.889 | 2.1886 | 8168 | 444 | 444 | 209 | 0 | 0 | 0 | 330 | 0.81591 | 12556 |  | 2630 | 1650 | 12112 | 2630 | 1650 | 4693.18 | 0.002174 | 0.01189 | 1259 | 0.53578 | 0.0026009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 0.53578 | 221.2126 | 221.2126 | 0%
Central Valley | ST_Stockton | PINE GROVE 1102 | 1346 | PINE GROVE 11021222 | 1.3011 | 431.2912 | 20.0297 | 0 | 20.0297 | 0.026326 | 10916 | 17 | 15 | 15 | 8 | 8 | 0 | 1247 | 0.99869 | 19826 |  | 3590 | 2371 | 19809 | 3582 | 2363 | 6690.15 | 0.0030167 | 0.02247 | 1260 | 0.62601 | 0.0025975 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 3. >20 - 30% | 0.62601 | 178.8341 | 179.2335 | 0%
Sierra | SI_Sierra | PLACERVILLE 2106 | 519 | PLACERVILLE 210692012 | 1.8653 | 724.6782 | 29.9756 | 0 | 29.9756 | 0.38807 | 14031 | 62 | 61 | 0 | 0 | 0 | 0 | 1773 | 0.98705 | 25224 |  | 4601 | 2991 | 25162 | 4601 | 2991 | 8567.95 | 0.002574 | 0.02463 | 1261 | 1.1707 | 0.0025958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 3. >20 - 30% | 1.1707 | 153.4917 | 153.4917 | 0%
North Coast | HU_Humboldt | WILLOW CREEK 1103 | 6664 | WILLOW CREEK 11037514 | 0.39355 | 175.8096 | 9.5125 | 0 | 9.5125 | 0 | 3274 | 0 | 0 | 0 | 0 | 0 | 0 | 358 | 1 | 5958 |  | 1076 | 710 | 5958 | 1076 | 710 | 2010.34 | 0.0022385 | 0.00501 | 1262 | 0.30868 | 0.002594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.30868 | 113.1143 | 113.1143 | 0%
Bay Area | PE_Peninsula | WOODSIDE 1101 | 4265 | WOODSIDE 11011922 | 0.24147 | 113.0498 | 4.6883 | 2.4252 | 2.2631 | 3.0494 | 2306 | 2606 | 1118 | 625 | 1033 | 595 | 0 | 304 | 0.34956 | 4074 |  | 1383 | 800 | 1468 | 350 | 205 | 611.62 | 0.002136 | 0.00155 | 1263 | 0.19646 | 0.0025849 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.094831 | 154.6573 | 294.9923 | 51.73%
Sierra | SI_Sierra | PLACERVILLE 2106 | 6109 | PLACERVILLE 2106935216 | 1.4168 | 490.5689 | 19.8473 | 0 | 19.8473 | 4.6205 | 3257 | 278 | 278 | 261 | 0 | 0 | 0 | 933 | 0.7672 | 4825 |  | 1100 | 803 | 4547 | 1100 | 803 | 1916.23 | 0.0028881 | 0.00661 | 1264 | 0.68972 | 0.0025736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.68972 | 55.423 | 55.423 | 0%
Sierra | SI_Sierra | ALLEGHANY 1101 | 4624 | ALLEGHANY 1101circuit_breaker | 0.40303 | 134.1326 | 5.8206 | 0 | 5.8206 | 0 | 3413 | 0 | 0 | 0 | 0 | 0 | 0 | 214 | 1 | 6210 |  | 1122 | 740 | 6210 | 1122 | 740 | 2096.04 | 0.0030047 | 0.00701 | 1265 | 0.18769 | 0.0025712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.18769 | 192.7622 | 192.7622 | 0%
North Coast | SO_Sonoma | MONTE RIO 1113 | 2817 | MONTE RIO 1113346 | 0.85266 | 250.9931 | 10.1653 | 0.8392 | 9.3263 | 3.9004 | 3606 | 302 | 74 | 15 | 39 | 6 | 0 | 573 | 0.61631 | 4345 |  | 804 | 497 | 4043 | 765 | 491 | 1411.92 | 0.0033971 | 0.0054 | 1266 | 0.33548 | 0.0025415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.30779 | 82.0259 | 79.0923 | 8.256%
Bay Area | PE_Peninsula | HALF MOON BAY 1101 | 7409 | HALF MOON BAY 11012500 | 0.3497 | 159.2993 | 6.7593 | 0 | 6.7593 | 0 | 3305 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 1 | 6014 |  | 1087 | 717 | 6014 | 1087 | 717 | 2030.45 | 0.0021952 | 0.00496 | 1267 | 0.23852 | 0.0025375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.23852 | 160.8159 | 160.8159 | 0%
Central Valley | ST_Stockton | OLETA 1102 | 2031 | OLETA 11021228 | 0.44397 | 210.7162 | 14.4241 | 0 | 14.4241 | 0 | 1210 | 0 | 0 | 0 | 0 | 0 | 0 | 274 | 1 | 2210 |  | 400 | 265 | 2210 | 400 | 265 | 746.9 | 0.0021069 | 0.00175 | 1268 | 0.19528 | 0.0025361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.19528 | 27.7315 | 27.7315 | 0%
North Coast | HU_Humboldt | FORT BRAGG A 1101 | 1708 | FORT BRAGG A 110195294 | 1.6411 | 623.2402 | 27.0089 | 0 | 27.0089 | 0 | 9392 | 0 | 0 | 0 | 0 | 0 | 0 | 456 | 1 | 17068 |  | 3080 | 2030 | 17068 | 3080 | 2030 | 5755.72 | 0.0026332 | 0.01686 | 1269 | 0.77737 | 0.0025321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 3. >20 - 30% | 0.77737 | 114.0365 | 114.0365 | 0%
Central Valley | ST_Stockton | FROGTOWN 1702 | 2368 | FROGTOWN 1702290609 | 1.0519 | 409.3736 | 17.6047 | 0 | 17.6047 | 0 | 2560 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 1 | 4661 |  | 843 | 556 | 4661 | 843 | 556 | 1574.4 | 0.0025695 | 0.0045 | 1270 | 0.69913 | 0.0025239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.69913 | 47.8848 | 47.8848 | 0%
North Coast | SO_Sonoma | MIRABEL 1101 | 5240 | MIRABEL 11014859 | 0.3015 | 103.1709 | 3.7589 | 0.073485 | 3.6854 | 2.9742 | 3084 | 493 | 493 | 53 | 8 | 0 | 0 | 212 | 0.20875 | 1665 |  | 705 | 193 | 1172 | 697 | 193 | 1060.37 | 0.0029223 | 0.00424 | 1271 | 0.090574 | 0.0025159 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.088803 | 189.1238 | 187.5548 | 1.955%
North Coast | HU_Humboldt | LUCERNE 1103 | 8982 | LUCERNE 11034200 | 1.416 | 90.3402 | 4.1197 | 0 | 4.1197 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 1 | 179 |  | 34 | 24 | 179 | 34 | 24 | 62.69 | 0.015674 | 0.00111 | 1272 | 0.037615 | 0.0025076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.037615 | 8.253 | 8.253 | 0%
North Coast | SO_Sonoma | SONOMA 1104 | 7480 | SONOMA 11045661 | 0.34526 | 47.4748 | 2.3778 | 0 | 2.3778 | 0 | 294 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 1 | 546 |  | 100 | 67 | 546 | 100 | 67 | 186.14 | 0.0072724 | 0.00151 | 1273 | 0.010025 | 0.0025063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.010025 | 42.055 | 42.055 | 0%
North Coast | SO_Sonoma | RINCON 1103 | 7552 | RINCON 1103568 | 1.0721 | 311.2593 | 12.5642 | 1.6989 | 10.8653 | 12.4532 | 4417 | 1026 | 827 | 419 | 604 | 233 | 0 | 574 | 0.0088334 | 1097 |  | 840 | 427 | 71 | 236 | 194 | 329.71 | 0.0034443 | 0.00169 | 1274 | 0.45803 | 0.0025029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.3961 | 21.7204 | 66.8566 | 13.52%
North Valley | NV_North Valley | VOLTA 1102 | 9470 | VOLTA 1102circuit_breaker | 0.66472 | 84.7578 | 4.4381 | 0 | 4.4381 | 0 | 1896 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 1 | 3455 |  | 625 | 413 | 3455 | 625 | 413 | 1167.2 | 0.0078426 | 0.01019 | 1275 | 0.064946 | 0.0024979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 0.064946 | 140.827 | 140.827 | 0%
Central Coast | LP_Los Padres | OILFIELDS 1103 | 7638 | OILFIELDS 1103N62 | 0.27012 | 108.728 | 5.6839 | 5.465 | 0.21894 | 5.6839 | 96 | 194 | 5 | 0 | 4 | 0 | 0 | 146 | 0 | 194 |  | 5 | 0 | 0 | 1 | 0 | 1.37 | 0.0024843 | 1e-05 | 1276 | 0.0049929 | 0.0024964 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.00019232 | 4.5675 | 0.87968 | 96.15%
Sierra | SI_Sierra | SHADY GLEN 1102 | 3005 | SHADY GLEN 1102circuit_breaker | 1.2716 | 484.0984 | 19.4187 | 0 | 19.4187 | 0 | 8231 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 1 | 14960 |  | 2700 | 1779 | 14960 | 2700 | 1779 | 5045.4 | 0.0026268 | 0.01475 | 1277 | 0.83108 | 0.0024957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 0.83108 | 139.0409 | 139.0409 | 0%
North Valley | NV_North Valley | BURNEY 1101 | 2714 | BURNEY 11021358 | 0.51068 | 173.0362 | 8.2453 | 0 | 8.2453 | 0 | 1899 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 1 | 3461 |  | 626 | 413 | 3461 | 626 | 413 | 1169.11 | 0.0029513 | 0.00384 | 1278 | 0.1719 | 0.0024913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.1719 | 75.9224 | 75.9224 | 0%
North Coast | SO_Sonoma | MONTE RIO 1113 | 4861 | MONTE RIO 1113180 | 0.058054 | 49.0353 | 2.1795 | 0 | 2.1795 | 0.068371 | 1555 | 1 | 1 | 1 | 0 | 0 | 0 | 126 | 0.96863 | 2748 |  | 498 | 330 | 2747 | 498 | 330 | 929.49 | 0.0011839 | 0.00123 | 1279 | 0.079529 | 0.0024853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.079529 | 228.488 | 228.488 | 0%
Central Valley | YO_Yosemite | CURTIS 1702 | 2199 | CURTIS 170247488 | 0.59071 | 461.8984 | 17.9347 | 0.1892 | 17.7455 | 0.37841 | 2267 | 219 | 85 | 28 | 85 | 28 | 0 | 396 | 0.9789 | 4261 |  | 816 | 510 | 4042 | 731 | 482 | 1365.25 | 0.0012789 | 0.00194 | 1280 | 0.54593 | 0.0024815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.54017 | 41.1936 | 45.4985 | 1.055%
Central Coast | CC_Central Coast | SAN ARDO 1101 | 6524 | SAN ARDO 11017632 | 0.022801 | 19.9999 | 2.3386 | 0 | 2.3386 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1 | 16 |  | 5 | 4 | 16 | 5 | 4 | 8.29 | 0.0011401 | 1e-05 | 1281 | 0.0024798 | 0.0024798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0024798 | 2.138 | 2.138 | 0%
North Coast | NC_North Coast | RIO DELL 1102 | 9603 | RIO DELL 110275970 | 0.29364 | 149.476 | 7.3472 | 0 | 7.3472 | 0 | 1423 | 0 | 0 | 0 | 0 | 0 | 0 | 212 | 1 | 2596 |  | 470 | 311 | 2596 | 470 | 311 | 877.54 | 0.0019645 | 0.00192 | 1282 | 0.18257 | 0.0024672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.18257 | 63.9703 | 63.9703 | 0%
Central Coast | LP_Los Padres | SISQUOC 1102 | 4724 | SISQUOC 1102M54 | 1.2966 | 437.7498 | 19.0267 | 18.6456 | 0.38106 | 19.0267 | 279 | 496 | 57 | 0 | 57 | 0 | 0 | 408 | 0 | 496 |  | 57 | 0 | 0 | 0 | 0 | 0 | 0.0029619 | 0 | 1283 | 0.14271 | 0.0024604 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0028581 | 0 | 2.9958 | 98%
Sierra | SI_Sierra | HIGGINS 1110 | 964 | HIGGINS 11102408 | 2.2924 | 866.2004 | 34.2737 | 0 | 34.2737 | 0 | 9125 | 0 | 0 | 0 | 0 | 0 | 0 | 824 | 1 | 16583 |  | 2993 | 1972 | 16583 | 2993 | 1972 | 5592.88 | 0.0026465 | 0.01647 | 1284 | 1.3081 | 0.0024588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 1.3081 | 87.3265 | 87.3265 | 0%
Central Valley | YO_Yosemite | BEAR VALLEY 2105 | 8021 | BEAR VALLEY 210576694 | 0.23092 | 62.5069 | 2.997 | 0 | 2.997 | 0 | 398 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 1 | 735 |  | 135 | 90 | 735 | 135 | 90 | 251.1 | 0.0036942 | 0.00104 | 1285 | 0.118 | 0.0024584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.118 | 45.0455 | 45.0455 | 0%
Sierra | SI_Sierra | MOUNTAIN QUARRIES 2101 | 140 | MOUNTAIN QUARRIES 21011130 | 1.3102 | 504.6973 | 20.5614 | 0 | 20.5614 | 0 | 6863 | 0 | 0 | 0 | 0 | 0 | 0 | 489 | 1 | 12475 |  | 2252 | 1484 | 12475 | 2252 | 1484 | 4207.99 | 0.0025961 | 0.01216 | 1286 | 0.78465 | 0.0024444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 0.78465 | 109.5258 | 109.5258 | 0%
Bay Area | MI_Mission | JARVIS 1108 | 2694 | JARVIS 1108MR368 | 0.011199 | 4.5767 | 0.086174 | 0 | 0.086174 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 43 |  | 10 | 7 | 43 | 10 | 7 | 17.57 | 0.002447 | 5e-05 | 1287 | 0.014645 | 0.0024408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.014645 | 116.044 | 116.044 | 0%
Central Coast | LP_Los Padres | ATASCADERO 1103 | 1381 | ATASCADERO 1103A16 | 0.9599 | 462.2247 | 18.0578 | 1.9487 | 16.1091 | 7.1034 | 752 | 691 | 607 | 345 | 77 | 68 | 1 | 502 | 0.60663 | 1527 |  | 759 | 446 | 836 | 682 | 378 | 1009.58 | 0.0020767 | 0.00295 | 1288 | 0.48294 | 0.0024268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.43083 | 42.3363 | 42.0318 | 10.79%
North Valley | NV_North Valley | VOLTA 1102 | 5536 | VOLTA 11029742 | 0.49411 | 206.9829 | 9.1254 | 0 | 9.1254 | 0 | 6664 | 0 | 0 | 0 | 0 | 0 | 0 | 232 | 1 | 12114 |  | 2187 | 1441 | 12114 | 2187 | 1441 | 4086.45 | 0.0023872 | 0.01086 | 1289 | 0.3253 | 0.0024096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 0.3253 | 239.6613 | 239.6613 | 0%
Central Valley | FR_Fresno | STONE CORRAL 1110 | 7441 | STONE CORRAL 11107784F | 0.024266 | 12.4704 | 0.87311 | 0 | 0.87311 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 1 | 34 |  | 8 | 6 | 34 | 8 | 6 | 14.02 | 0.0019459 | 3e-05 | 1290 | 0.0048132 | 0.0024066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0048132 | 9.1627 | 9.1627 | 0%
Central Valley | ST_Stockton | WEST POINT 1101 | 4823 | WEST POINT 110136674 | 0.68214 | 207.834 | 8.247 | 0.030682 | 8.2161 | 0.041856 | 6109 | 50 | 50 | 35 | 16 | 1 | 0 | 504 | 0.99492 | 11100 |  | 2045 | 1350 | 11050 | 2029 | 1349 | 3774.23 | 0.0032821 | 0.01385 | 1291 | 0.11294 | 0.0024029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 0.11251 | 246.9542 | 247.9699 | 0.372%
Central Coast | SJ_San Jose | MILPITAS 1109 | 1813 | MILPITAS 1109XR082 | 1.2691 | 459.4251 | 18.3436 | 0 | 18.3436 | 0 | 726 | 0 | 0 | 0 | 0 | 0 | 0 | 312 | 1 | 1331 |  | 242 | 160 | 1331 | 242 | 160 | 451.33 | 0.0027624 | 0.00139 | 1292 | 0.31906 | 0.002399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.31906 | 13.1926 | 13.1926 | 0%
Central Valley | ST_Stockton | STANISLAUS 1702 | 6735 | STANISLAUS 1702L3151 | 0.039326 | 13.9405 | 0.44242 | 0.031629 | 0.41061 | 0.2161 | 326 | 302 | 93 | 31 | 87 | 25 | 0 | 22 | 0.51156 | 611 |  | 150 | 69 | 309 | 63 | 44 | 114.12 | 0.002821 | 0.00037 | 1293 | 0.0071849 | 0.002395 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0066682 | 153.4317 | 339.0411 | 7.149%
North Coast | SO_Sonoma | FORT ROSS 1121 | 2824 | FORT ROSS 11214947 | 5.1143 | 288.9026 | 10.1081 | 0 | 10.1081 | 0 | 4249 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 1 | 7728 |  | 1396 | 920 | 7728 | 1396 | 920 | 2608.04 | 0.017702 | 0.05139 | 1294 | 0.0023862 | 0.0023862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 5. >40 - 50% | 2. >10 - 20% | 0.0023862 | 138.1065 | 138.1065 | 0%
Bay Area | NB_North Bay | PUEBLO 1105 | 3792 | PUEBLO 1105716 | 0.14275 | 71.0111 | 3.0636 | 0 | 3.0636 | 0 | 463 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1 | 853 |  | 156 | 104 | 853 | 156 | 104 | 290.49 | 0.0020102 | 0.00065 | 1295 | 0.10344 | 0.0023509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.10344 | 50.9199 | 50.9199 | 0%
North Valley | NV_North Valley | CRESCENT MILLS 2101 | 4407 | CRESCENT MILLS 21013113 | 0.027866 | 17.5276 | 0.48883 | 0 | 0.48883 | 0 | 302 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1 | 561 |  | 103 | 69 | 561 | 103 | 69 | 191.6 | 0.0015898 | 0.00034 | 1296 | 0.047014 | 0.0023507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.047014 | 210.709 | 210.709 | 0%
Bay Area | NB_North Bay | PUEBLO 1104 | 6687 | PUEBLO 1104640 | 0.006202 | 6.3896 | 0.35227 | 0 | 0.35227 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 30 |  | 7 | 6 | 30 | 7 | 6 | 12.29 | 0.00097063 | 1e-05 | 1297 | 0.018784 | 0.002348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.018784 | 19.871 | 19.871 | 0%
North Coast | HU_Humboldt | GUALALA 1112 | 9009 | GUALALA 1112circuit_breaker | 0.022599 | 33.7224 | 1.5186 | 0 | 1.5186 | 0 | 461 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1 | 849 |  | 155 | 103 | 849 | 155 | 103 | 288.76 | 0.00067015 | 0.00022 | 1298 | 0.058525 | 0.002341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.058525 | 102.0703 | 102.0703 | 0%
Central Valley | ST_Stockton | MARTELL 1102 | 7068 | MARTELL 110299214 | 0.080708 | 14.8715 | 0.77708 | 0 | 0.77708 | 0 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 203 |  | 39 | 26 | 203 | 39 | 26 | 71.7 | 0.005427 | 0.00044 | 1299 | 0.055938 | 0.0023307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.055938 | 50.1877 | 50.1877 | 0%
Sierra | SI_Sierra | DIAMOND SPRINGS 1104 | 6862 | DIAMOND SPRINGS 11042093 | 0.61891 | 204.1135 | 7.8225 | 0 | 7.8225 | 0 | 1499 | 0 | 0 | 0 | 0 | 0 | 0 | 192 | 1 | 2734 |  | 495 | 327 | 2734 | 495 | 327 | 924.21 | 0.0030322 | 0.00312 | 1300 | 0.22907 | 0.0023138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.22907 | 63.2787 | 63.2787 | 0%
Central Coast | LP_Los Padres | PALMER 1101 | 6493 | PALMER 1101M84 | 0.76632 | 408.9747 | 22.5917 | 0 | 22.5917 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 1 | 134 |  | 26 | 18 | 134 | 26 | 18 | 47.68 | 0.0018738 | 0.0001 | 1301 | 0.078441 | 0.0023071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.078441 | 1.1509 | 1.1509 | 0%
Central Valley | ST_Stockton | STANISLAUS 1701 | 8661 | STANISLAUS 1701circuit_breaker | 0.76718 | 180.3629 | 9.5593 | 1.2892 | 8.2703 | 2.3097 | 1453 | 361 | 32 | 20 | 5 | 0 | 0 | 314 | 0.75839 | 2371 |  | 396 | 261 | 2010 | 391 | 261 | 716.57 | 0.0042536 | 0.00346 | 1302 | 0.16596 | 0.002305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.14358 | 47.2778 | 41.4257 | 13.49%
Central Valley | ST_Stockton | WEST POINT 1102 | 924 | WEST POINT 110293116 | 2.2413 | 951.4955 | 42.014 | 2.9286 | 39.0854 | 23.6064 | 18925 | 13684 | 5732 | 4129 | 3518 | 2125 | 0 | 1901 | 0.43813 | 28747 |  | 8449 | 5919 | 15063 | 4931 | 3794 | 8111.14 | 0.0023555 | 0.02415 | 1303 | 1.4767 | 0.0023001 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 3. >20 - 30% | 1.3737 | 126.1596 | 201.0996 | 6.971%
Bay Area | NB_North Bay | SAN RAFAEL 1104 | 280 | SAN RAFAEL 1104802 | 1.1326 | 241.3492 | 9.9021 | 0 | 9.9021 | 0 | 1143 | 0 | 0 | 0 | 0 | 0 | 0 | 311 | 1 | 2088 |  | 379 | 250 | 2088 | 379 | 250 | 707.15 | 0.0046929 | 0.0037 | 1304 | 0.25278 | 0.002298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.25278 | 38.2748 | 38.2748 | 0%
North Valley | NV_North Valley | MC ARTHUR 1101 | 6295 | MC ARTHUR 11011488 | 0.045892 | 32.263 | 2.3331 | 0 | 2.3331 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 1 | 412 |  | 76 | 51 | 412 | 76 | 51 | 141.2 | 0.0014224 | 0.00022 | 1305 | 0.039044 | 0.0022967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.039044 | 32.5741 | 32.5741 | 0%
Central Valley | ST_Stockton | FROGTOWN 1702 | 1265 | FROGTOWN 170232556 | 0.15427 | 113.298 | 6.5146 | 0 | 6.5146 | 0 | 433 | 0 | 0 | 0 | 0 | 0 | 0 | 162 | 1 | 799 |  | 146 | 97 | 799 | 146 | 97 | 271.93 | 0.0013616 | 0.00041 | 1306 | 0.11388 | 0.0022776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.11388 | 22.4113 | 22.4113 | 0%
North Coast | SO_Sonoma | MONTE RIO 1111 | 7680 | MONTE RIO 111137520 | 0.036455 | 46.7074 | 1.9161 | 0.10189 | 1.8142 | 1.9161 | 1365 | 341 | 341 | 191 | 0 | 0 | 0 | 72 | 0 | 341 |  | 341 | 191 | 0 | 341 | 191 | 467.17 | 0.0007805 | 0.00055 | 1307 | 0.072826 | 0.0022758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.068953 | 187.9612 | 177.9658 | 5.318%
Central Coast | LP_Los Padres | PERRY 1101 | 281 | PERRY 1101V78 | 1.1748 | 633.5567 | 28.1996 | 1.3496 | 26.85 | 7.2165 | 871 | 608 | 599 | 477 | 432 | 332 | 0 | 674 | 0.74409 | 1794 |  | 814 | 620 | 1186 | 382 | 288 | 630.08 | 0.0018543 | 0.00147 | 1308 | 0.31858 | 0.0022756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.30333 | 14.2272 | 28.8656 | 4.786%
North Coast | SO_Sonoma | MONTE RIO 1113 | 6031 | MONTE RIO 11131989 | 0.062747 | 19.0685 | 0.6303 | 0 | 0.6303 | 0 | 468 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1 | 862 |  | 157 | 105 | 862 | 157 | 105 | 292.67 | 0.0032906 | 0.00107 | 1310 | 0.033813 | 0.0022542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.033813 | 249.0865 | 249.0865 | 0%
Bay Area | NB_North Bay | WOODACRE 1102 | 1986 | WOODACRE 11021280 | 0.44976 | 206.1543 | 8.3348 | 0 | 8.3348 | 0 | 934 | 0 | 0 | 0 | 0 | 0 | 0 | 257 | 1 | 1708 |  | 310 | 205 | 1708 | 310 | 205 | 578.42 | 0.0021817 | 0.00141 | 1312 | 0.27886 | 0.0022488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.27886 | 37.1932 | 37.1932 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2105 | 2791 | CAMP EVERS 210510294 | 0.19291 | 115.4136 | 7.0712 | 0 | 7.0712 | 0 | 5609 | 0 | 0 | 0 | 0 | 0 | 0 | 248 | 1 | 10198 |  | 1841 | 1214 | 10198 | 1841 | 1214 | 3439.99 | 0.0016715 | 0.0064 | 1313 | 0.2803 | 0.0022424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.2803 | 260.3514 | 260.3514 | 0%
Central Valley | YO_Yosemite | CURTIS 1704 | 9114 | CURTIS 170411300 | 2.2341 | 108.6419 | 3.6714 | 2.5008 | 1.1706 | 3.4241 | 408 | 806 | 230 | 155 | 224 | 150 | 0 | 159 | 0.067372 | 857 |  | 239 | 161 | 51 | 15 | 11 | 25.14 | 0.020564 | 0.00064 | 1314 | 0.10502 | 0.0022344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.033485 | 12.8135 | 65.0978 | 68.11%
Central Valley | ST_Stockton | STANISLAUS 1702 | 6836 | STANISLAUS 17024905 | 0.030353 | 21.855 | 0.81477 | 0.050379 | 0.76439 | 0.54527 | 555 | 279 | 78 | 33 | 78 | 33 | 0 | 43 | 0.33078 | 616 |  | 140 | 74 | 337 | 62 | 41 | 115.27 | 0.0013888 | 0.00018 | 1315 | 0.0022314 | 0.0022314 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0020934 | 81.11 | 171.8271 | 6.183%
North Coast | SO_Sonoma | RINCON 1102 | 4346 | RINCON 1102circuit_breaker | 0.063831 | 59.3236 | 3.464 | 0.1875 | 3.2767 | 0.41894 | 210 | 12 | 5 | 1 | 1 | 1 | 0 | 94 | 0.87906 | 358 |  | 69 | 44 | 346 | 68 | 43 | 124.3 | 0.001076 | 0.00015 | 1316 | 0.066795 | 0.0022265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.063183 | 20.7526 | 19.9191 | 5.413%
Sierra | SI_Sierra | FORESTHILL 1101 | 2722 | FORESTHILL 1101circuit_breaker | 0.52912 | 234.2219 | 9.8299 | 0 | 9.8299 | 1.1356 | 4007 | 1110 | 1110 | 1085 | 1031 | 1010 | 0 | 659 | 0.88447 | 7557 |  | 2274 | 1853 | 6447 | 1243 | 843 | 2283.14 | 0.002259 | 0.00584 | 1317 | 0.31598 | 0.0022096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.31598 | 126.4506 | 231.3344 | 0%
Sierra | SI_Sierra | PLACERVILLE 2106 | 4283 | PLACERVILLE 210619552 | 1.1496 | 577.0453 | 24.5129 | 0 | 24.5129 | 0.33939 | 7115 | 6 | 6 | 6 | 0 | 0 | 0 | 1449 | 0.98615 | 12760 |  | 2308 | 1523 | 12754 | 2308 | 1523 | 4309.82 | 0.0019922 | 0.00956 | 1318 | 0.72407 | 0.0022008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.72407 | 94.1546 | 94.1546 | 0%
North Valley | NV_North Valley | BUCKS CREEK 1103 | 1663 | BUCKS CREEK 1103338520 | 0.35861 | 171.4345 | 7.6063 | 0 | 7.6063 | 0 | 4544 | 0 | 0 | 0 | 0 | 0 | 0 | 202 | 1 | 8264 |  | 1492 | 984 | 8264 | 1492 | 984 | 2787.8 | 0.0020918 | 0.00649 | 1319 | 0.27946 | 0.0022005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.27946 | 196.1545 | 196.1545 | 0%
Central Valley | FR_Fresno | KERCKHOFF 1101 | 4482 | KERCKHOFF 1101R353 | 0.90887 | 270.7951 | 12.5958 | 5.6402 | 6.9557 | 12.5958 | 154 | 483 | 163 | 154 | 124 | 115 | 0 | 159 | 0 | 483 |  | 163 | 154 | 0 | 39 | 39 | 53.43 | 0.0033563 | 0.00027 | 1321 | 0.08415 | 0.0021577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.046469 | 5.6069 | 12.9408 | 44.78%
North Valley | NV_North Valley | ANTLER 1101 | 1401 | ANTLER 11011520 | 0.36705 | 211.7899 | 9.2545 | 0 | 9.2545 | 0 | 3076 | 0 | 0 | 0 | 0 | 0 | 0 | 259 | 1 | 5598 |  | 1012 | 667 | 5598 | 1012 | 667 | 1890.26 | 0.0017331 | 0.00365 | 1322 | 0.21896 | 0.0021466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.21896 | 109.3517 | 109.3517 | 0%
Bay Area | PE_Peninsula | MENLO 1102 | 1566 | MENLO 1102W80 | 0.8318 | 451.7046 | 18.4894 | 0 | 18.4894 | 0 | 2546 | 0 | 0 | 0 | 0 | 0 | 0 | 358 | 1 | 4636 |  | 838 | 553 | 4636 | 838 | 553 | 1565.3 | 0.0018415 | 0.00321 | 1323 | 0.37701 | 0.0021421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.37701 | 45.3233 | 45.3233 | 0%
Central Coast | LP_Los Padres | CABRILLO 1104 | 6503 | CABRILLO 1104Y24 | 1.5013 | 389.5791 | 19.9455 | 0 | 19.9455 | 0 | 539 | 0 | 0 | 0 | 0 | 0 | 0 | 297 | 1 | 991 |  | 181 | 120 | 991 | 181 | 120 | 337.16 | 0.0038536 | 0.00145 | 1324 | 0.12604 | 0.0021363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.12604 | 9.0747 | 9.0747 | 0%
North Valley | NV_North Valley | CENTERVILLE 1101 | 2232 | BUTTE 11051243 | 0.25203 | 165.7497 | 6.0655 | 0 | 6.0655 | 0.19223 | 1476 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 0.96831 | 2607 |  | 472 | 312 | 2607 | 472 | 312 | 881.27 | 0.0015206 | 0.00149 | 1325 | 0.19546 | 0.0021246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.19546 | 77.8168 | 77.8168 | 0%
Central Coast | LP_Los Padres | SANTA YNEZ 1102 | 5551 | SANTA YNEZ 1102Y18 | 0.29017 | 80.2301 | 4.0909 | 0 | 4.0909 | 3.5875 | 277 | 379 | 87 | 29 | 0 | 0 | 0 | 58 | 0.12306 | 442 |  | 99 | 37 | 63 | 99 | 37 | 141.3 | 0.0036167 | 0.00074 | 1326 | 0.0785 | 0.0021216 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0785 | 24.2 | 24.2 | 0%
Bay Area | PE_Peninsula | HALF MOON BAY 1101 | 5525 | HALF MOON BAY 1101circuit_breaker | 0.36379 | 169.0458 | 8.414 | 0 | 8.414 | 0 | 1456 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 1 | 2656 |  | 481 | 318 | 2656 | 481 | 318 | 898.01 | 0.002152 | 0.00215 | 1327 | 0.19452 | 0.0021144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.19452 | 57.1665 | 57.1665 | 0%
Central Valley | ST_Stockton | PINE GROVE 1101 | 3123 | PINE GROVE 11011021 | 0.24586 | 79.1999 | 2.9589 | 0 | 2.9589 | 0 | 1398 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 1 | 2551 |  | 462 | 305 | 2551 | 462 | 305 | 862.53 | 0.0031043 | 0.00298 | 1328 | 0.15408 | 0.0021107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.15408 | 156.139 | 156.139 | 0%
Sierra | SI_Sierra | APPLE HILL 2102 | 715 | APPLE HILL 210212025 | 0.5012 | 272.6009 | 10.0176 | 0 | 10.0176 | 0 | 2081 | 0 | 0 | 0 | 0 | 0 | 0 | 357 | 1 | 3791 |  | 686 | 453 | 3791 | 686 | 453 | 1281.01 | 0.0018386 | 0.00262 | 1329 | 0.31448 | 0.0021106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.31448 | 68.4794 | 68.4794 | 0%
Sierra | SI_Sierra | BRUNSWICK 1105 | 4719 | BRUNSWICK 11052130 | 0.75025 | 402.8664 | 13.7725 | 0.97481 | 12.7979 | 8.9867 | 10942 | 3974 | 3952 | 3521 | 1574 | 1509 | 28 | 796 | 0.34749 | 10883 |  | 5199 | 4343 | 6909 | 3625 | 2834 | 5588.06 | 0.0018623 | 0.01404 | 1330 | 0.41327 | 0.0021085 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 0.38403 | 283.2492 | 377.4903 | 7.078%
Sierra | SI_Sierra | DIAMOND SPRINGS 1106 | 4145 | DIAMOND SPRINGS 110676088 | 0.35251 | 196.5513 | 8.5114 | 0.031439 | 8.4799 | 0.39924 | 3942 | 370 | 289 | 244 | 166 | 152 | 0 | 306 | 0.95309 | 7204 |  | 1523 | 1058 | 6834 | 1357 | 906 | 2474.15 | 0.0017935 | 0.00506 | 1331 | 0.36612 | 0.0020921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.36477 | 160.025 | 178.9372 | 0.3694%
Central Coast | CC_Central Coast | BIG BASIN 1102 | 5561 | BIG BASIN 110210254 | 0.053105 | 42.2191 | 2.3053 | 0.60682 | 1.6985 | 2.3053 | 723 | 382 | 381 | 290 | 55 | 37 | 0 | 74 | 0 | 382 |  | 381 | 290 | 0 | 326 | 253 | 446.62 | 0.0012578 | 0.00085 | 1332 | 0.0062684 | 0.0020895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0046184 | 191.9358 | 165.2711 | 26.32%
Central Coast | CC_Central Coast | PAUL SWEET 2106 | 5138 | PAUL SWEET 210610424 | 0.33565 | 186.472 | 6.5144 | 0 | 6.5144 | 0 | 1430 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 1 | 2609 |  | 473 | 312 | 2609 | 473 | 312 | 882.82 | 0.0018 | 0.00177 | 1333 | 0.14925 | 0.0020729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.14925 | 72.6084 | 72.6084 | 0%
Sierra | SI_Sierra | PLACERVILLE 2106 | 4726 | PLACERVILLE 21069712 | 1.0123 | 557.1995 | 22.7445 | 0 | 22.7445 | 0 | 11731 | 0 | 0 | 0 | 0 | 0 | 0 | 976 | 1 | 21315 |  | 3846 | 2534 | 21315 | 3846 | 2534 | 7187.37 | 0.0018168 | 0.01453 | 1334 | 0.7516 | 0.0020424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 0.7516 | 169.0958 | 169.0958 | 0%
Bay Area | PE_Peninsula | PACIFICA 1103 | 8884 | PACIFICA 11033907 | 0.097025 | 59.0809 | 5.1013 | 0 | 5.1013 | 0 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 1 | 306 |  | 57 | 39 | 306 | 57 | 39 | 105.63 | 0.0016422 | 0.00019 | 1335 | 0.05514 | 0.0020422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.05514 | 11.1736 | 11.1736 | 0%
Bay Area | NB_North Bay | LAS GALLINAS A 1105 | 1425 | LAS GALLINAS A 1105904 | 0.15965 | 43.6701 | 1.715 | 0 | 1.715 | 0 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 1 | 170 |  | 33 | 22 | 170 | 33 | 22 | 60.51 | 0.0036557 | 0.00025 | 1336 | 0.034699 | 0.0020411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.034699 | 19.2424 | 19.2424 | 0%
Central Valley | FR_Fresno | BALCH NO 1 1101 | 9105 | BALCH NO 1 1101circuit_breaker | 0.39228 | 185.961 | 8.6504 | 0 | 8.6504 | 0 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 1 | 232 |  | 44 | 30 | 232 | 44 | 30 | 81.16 | 0.0021095 | 0.00019 | 1337 | 0.069275 | 0.0020375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.069275 | 5.0865 | 5.0865 | 0%
Central Valley | ST_Stockton | WEST POINT 1102 | 4455 | WEST POINT 11021341 | 0.39577 | 178.5947 | 8.9951 | 1.8006 | 7.1947 | 7.0254 | 3516 | 4133 | 814 | 625 | 641 | 485 | 0 | 350 | 0.21898 | 5534 |  | 1067 | 792 | 1401 | 426 | 307 | 709.71 | 0.002216 | 0.00196 | 1339 | 0.22336 | 0.0020305 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.17865 | 59.2103 | 118.6205 | 20.02%
Sierra | SI_Sierra | EL DORADO PH 2101 | 5042 | EL DORADO PH 210163464 | 0.56481 | 299.3962 | 13.1098 | 2.5021 | 10.6078 | 3.4886 | 4128 | 370 | 82 | 73 | 11 | 11 | 0 | 399 | 0.73389 | 5880 |  | 1077 | 729 | 5510 | 1066 | 718 | 1956.32 | 0.0018865 | 0.00418 | 1340 | 0.19665 | 0.0020274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.15912 | 100.4924 | 82.152 | 19.09%
North Coast | SO_Sonoma | GEYSERVILLE 1101 | 4765 | GEYSERVILLE 1101480 | 0.32312 | 51.6035 | 1.6735 | 0 | 1.6735 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1 | 143 |  | 28 | 19 | 143 | 28 | 19 | 51.23 | 0.0062615 | 0.00036 | 1341 | 0.026348 | 0.0020268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.026348 | 16.7316 | 16.7316 | 0%
Bay Area | DI_Diablo | TASSAJARA 2103 | 23 | TASSAJARA 2103circuit_breaker | 0.076627 | 34.4397 | 2.096 | 0 | 2.096 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 1 | 557 |  | 102 | 68 | 557 | 102 | 68 | 189.87 | 0.002225 | 0.00047 | 1342 | 0.018193 | 0.0020215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.018193 | 48.6636 | 48.6636 | 0%
North Coast | SO_Sonoma | DUNBAR 1103 | 312 | DUNBAR 1103440 | 0.13556 | 80.5048 | 2.7735 | 0.65852 | 2.1152 | 2.2799 | 142 | 93 | 86 | 45 | 51 | 21 | 1 | 133 | 0.17796 | 141 |  | 95 | 51 | 48 | 44 | 30 | 64.6 | 0.0016839 | 0.00015 | 1343 | 0.078811 | 0.0020208 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.060104 | 20.8023 | 34.2529 | 23.74%
North Valley | NV_North Valley | STILLWATER 1101 | 7576 | STILLWATER 1101circuit_breaker | 0.42044 | 89.9858 | 4.3019 | 0 | 4.3019 | 0 | 618 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 1 | 1135 |  | 207 | 137 | 1135 | 207 | 137 | 385.74 | 0.0046723 | 0.00201 | 1344 | 0.11516 | 0.0020204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.11516 | 48.1183 | 48.1183 | 0%
Sierra | SI_Sierra | COLUMBIA HILL 1101 | 1557 | COLUMBIA HILL 1101circuit_breaker | 2.2788 | 1022.6265 | 38.765 | 0 | 38.765 | 2.6453 | 11203 | 80 | 80 | 79 | 0 | 0 | 0 | 1710 | 0.93176 | 19047 |  | 3503 | 2334 | 18967 | 3503 | 2334 | 6506.14 | 0.0022284 | 0.01623 | 1345 | 1.1239 | 0.0020177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 1.1239 | 90.3651 | 90.3651 | 0%
North Coast | SO_Sonoma | FORT ROSS 1121 | 5424 | FORT ROSS 112137326 | 0.10894 | 99.789 | 4.758 | 0 | 4.758 | 0 | 997 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1 | 1823 |  | 331 | 219 | 1823 | 331 | 219 | 617.54 | 0.0010917 | 0.00075 | 1346 | 0.050157 | 0.0020063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.050157 | 69.5677 | 69.5677 | 0%
North Coast | SO_Sonoma | MONTE RIO 1112 | 7639 | MONTE RIO 1112120 | 0.34617 | 148.1274 | 7.0627 | 0.0068182 | 7.0559 | 0.059659 | 4932 | 24 | 7 | 5 | 0 | 0 | 0 | 372 | 0.99155 | 8917 |  | 1613 | 1064 | 8893 | 1613 | 1064 | 3010.18 | 0.002337 | 0.00784 | 1347 | 0.23827 | 0.0020022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.23804 | 228.6039 | 228.3833 | 0.09654%
Sierra | SI_Sierra | GRASS VALLEY 1103 | 4687 | GRASS VALLEY 11031700 | 1.3712 | 489.3219 | 20.665 | 0 | 20.665 | 0.4053 | 5954 | 122 | 122 | 85 | 0 | 0 | 0 | 530 | 0.98039 | 10734 |  | 2038 | 1348 | 10612 | 2038 | 1348 | 3747.14 | 0.0028022 | 0.01188 | 1348 | 0.59243 | 0.0020014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 0.59243 | 98.621 | 98.621 | 0%
Central Valley | ST_Stockton | STANISLAUS 1702 | 374 | STANISLAUS 17021804 | 0.13291 | 205.4302 | 10.1598 | 1.39 | 8.7699 | 9.172 | 6040 | 3535 | 1606 | 815 | 1579 | 789 | 0 | 591 | 0.097234 | 4603 |  | 1799 | 942 | 1068 | 220 | 153 | 397.52 | 0.000647 | 0.0003 | 1349 | 0.033923 | 0.0019955 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.029282 | 25.0858 | 177.0696 | 13.68%
Central Valley | YO_Yosemite | PEORIA 1701 | 5939 | PEORIA 170190090 | 5.6251 | 613.8383 | 29.8328 | 0.54848 | 29.2843 | 0.94527 | 943 | 120 | 23 | 7 | 21 | 7 | 0 | 478 | 0.96831 | 1790 |  | 326 | 208 | 1670 | 305 | 201 | 568.15 | 0.0091638 | 0.00581 | 1350 | 0.39534 | 0.0019866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.38807 | 10.4151 | 10.9276 | 1.839%
North Coast | HU_Humboldt | HARTLEY 1102 | 5003 | HARTLEY 1102circuit_breaker | 0.64411 | 96.5749 | 5.8324 | 0 | 5.8324 | 0 | 345 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 1 | 639 |  | 117 | 78 | 639 | 117 | 78 | 217.8 | 0.0066695 | 0.00162 | 1351 | 0.065211 | 0.0019761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.065211 | 20.0604 | 20.0604 | 0%
Sierra | SI_Sierra | MOUNTAIN QUARRIES 2101 | 7457 | MOUNTAIN QUARRIES 210135466 | 0.42053 | 192.291 | 8.6267 | 0 | 8.6267 | 0 | 1281 | 0 | 0 | 0 | 0 | 0 | 0 | 208 | 1 | 2339 |  | 424 | 280 | 2339 | 424 | 280 | 791.39 | 0.0021869 | 0.00193 | 1353 | 0.15266 | 0.0019572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.15266 | 49.1497 | 49.1497 | 0%
North Valley | NV_North Valley | CRESCENT MILLS 2101 | 4953 | CRESCENT MILLS 21012056 | 0.14115 | 85.7409 | 5.1583 | 0 | 5.1583 | 0 | 2107 | 0 | 0 | 0 | 0 | 0 | 0 | 178 | 1 | 3839 |  | 694 | 458 | 3839 | 694 | 458 | 1296.29 | 0.0016463 | 0.00238 | 1354 | 0.11542 | 0.0019563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.11542 | 134.5396 | 134.5396 | 0%
North Valley | NV_North Valley | JESSUP 1101 | 8130 | JESSUP 11012839 | 0.023671 | 34.5065 | 1.1879 | 0 | 1.1879 | 0 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1 | 326 |  | 61 | 41 | 326 | 61 | 41 | 112.91 | 0.00068599 | 9e-05 | 1355 | 0.05209 | 0.0019292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.05209 | 51.352 | 51.352 | 0%
Central Valley | YO_Yosemite | RACETRACK 1703 | 4777 | RACETRACK 17039190 | 0.33774 | 209.3394 | 8.8129 | 0.070265 | 8.7426 | 1.1884 | 1224 | 264 | 242 | 55 | 0 | 0 | 0 | 416 | 0.86515 | 2198 |  | 592 | 287 | 1934 | 592 | 287 | 985.1 | 0.0016134 | 0.00199 | 1356 | 0.24229 | 0.0019229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.24036 | 67.7143 | 67.1744 | 0.7973%
North Coast | HU_Humboldt | GUALALA 1112 | 4707 | GUALALA 111223444 | 0.97459 | 366.7608 | 14.5678 | 0 | 14.5678 | 0 | 8314 | 0 | 0 | 0 | 0 | 0 | 0 | 269 | 1 | 15110 |  | 2727 | 1797 | 15110 | 2727 | 1797 | 5095.89 | 0.0026573 | 0.01507 | 1358 | 0.13312 | 0.0018749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 0.13312 | 187.1936 | 187.1936 | 0%
North Valley | NV_North Valley | VOLTA 1102 | 3896 | VOLTA 11021502 | 0.28861 | 164.1536 | 7.4869 | 0 | 7.4869 | 0 | 5830 | 0 | 0 | 0 | 0 | 0 | 0 | 172 | 1 | 10599 |  | 1914 | 1261 | 10599 | 1914 | 1261 | 3576.09 | 0.0017581 | 0.007 | 1359 | 0.16267 | 0.0018698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.16267 | 255.6454 | 255.6454 | 0%
Central Coast | LP_Los Padres | OILFIELDS 1103 | 5593 | OILFIELDS 1103N48 | 5.7371 | 1103.2205 | 47.4807 | 47.1884 | 0.29223 | 47.4807 | 1290 | 1987 | 124 | 35 | 123 | 35 | 0 | 1086 | 0 | 1987 |  | 124 | 35 | 0 | 1 | 0 | 1.37 | 0.0052003 | 1e-05 | 1360 | 0.0074263 | 0.0018566 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 4.5707e-05 | 3.4219 | 2.6116 | 99.38%
Central Valley | ST_Stockton | PINE GROVE 1102 | 9018 | PINE GROVE 11029145 | 0.10449 | 48.7727 | 1.8309 | 0.0020833 | 1.8288 | 1.3828 | 914 | 92 | 86 | 53 | 5 | 4 | 0 | 83 | 0.24475 | 501 |  | 160 | 102 | 409 | 155 | 98 | 249.16 | 0.0021424 | 0.00069 | 1361 | 0.09639 | 0.0018537 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.09628 | 84.7556 | 87.3901 | 0.1138%
Central Valley | YO_Yosemite | COARSEGOLD 2102 | 5804 | COARSEGOLD 210210050 | 0.21594 | 172.0748 | 7.2831 | 0 | 7.2831 | 0.57102 | 1269 | 1 | 1 | 0 | 0 | 0 | 0 | 191 | 0.9216 | 2136 |  | 388 | 256 | 2135 | 388 | 256 | 723.71 | 0.0012549 | 0.00101 | 1362 | 0.18258 | 0.0018443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.18258 | 53.2737 | 53.2737 | 0%
North Valley | NV_North Valley | MC ARTHUR 1101 | 2833 | MC ARTHUR 110137388 | 0.37214 | 135.2215 | 8.0434 | 0 | 8.0434 | 0 | 1121 | 0 | 0 | 0 | 0 | 0 | 0 | 149 | 1 | 2048 |  | 371 | 246 | 2048 | 371 | 246 | 692.59 | 0.0027521 | 0.00212 | 1363 | 0.051433 | 0.0018369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.051433 | 46.1249 | 46.1249 | 0%
North Valley | NV_North Valley | CLARK ROAD 1102 | 5948 | CLARK ROAD 110292622 | 1.4042 | 791.0216 | 30.497 | 23.3591 | 7.1379 | 29.5508 | 3187 | 6747 | 3049 | 2474 | 2865 | 2365 | 0 | 932 | 0.031026 | 6927 |  | 3082 | 2495 | 180 | 217 | 130 | 313.49 | 0.0017752 | 0.0008 | 1364 | 0.7963 | 0.0018264 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.18638 | 30.4012 | 101.0592 | 76.59%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1103 | 4174 | SAN LUIS OBISPO 1103V82 | 0.98733 | 203.1953 | 9.2875 | 0 | 9.2875 | 0 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 199 | 1 | 385 |  | 71 | 48 | 385 | 71 | 48 | 131.92 | 0.004859 | 0.00072 | 1365 | 0.15331 | 0.0018251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.15331 | 7.6447 | 7.6447 | 0%
North Coast | HU_Humboldt | ANNAPOLIS 1101 | 2726 | ANNAPOLIS 110176842 | 0.19175 | 114.0841 | 5.0314 | 0 | 5.0314 | 0 | 2127 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 1 | 3875 |  | 701 | 463 | 3875 | 701 | 463 | 1309.12 | 0.0016808 | 0.00245 | 1366 | 0.054597 | 0.0018199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.054597 | 139.3239 | 139.3239 | 0%
Central Coast | CC_Central Coast | BIG BASIN 1102 | 1416 | BIG BASIN 1102circuit_breaker | 0.25282 | 163.279 | 7.9631 | 0.43466 | 7.5284 | 6.503 | 4108 | 961 | 950 | 523 | 180 | 81 | 1 | 401 | 0.18335 | 2331 |  | 1197 | 686 | 1370 | 1017 | 605 | 1516.59 | 0.0015484 | 0.00327 | 1367 | 0.13371 | 0.0018069 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 5. >40 - 50% | 6. >50% | 0.12641 | 135.0883 | 150.3189 | 5.458%
North Coast | HU_Humboldt | ARCATA 1121 | 6947 | ARCATA 11211206 | 0.31239 | 166.9058 | 6.8826 | 0 | 6.8826 | 0 | 5380 | 0 | 0 | 0 | 0 | 0 | 0 | 133 | 1 | 9782 |  | 1766 | 1164 | 9782 | 1766 | 1164 | 3299.8 | 0.0018716 | 0.00687 | 1368 | 0.20728 | 0.0018025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.20728 | 256.59 | 256.59 | 0%
Sierra | SI_Sierra | PLACERVILLE 2106 | 3578 | PLACERVILLE 2106circuit_breaker | 0.13184 | 71.5212 | 3.3919 | 0 | 3.3919 | 0.15379 | 663 | 3 | 3 | 3 | 0 | 0 | 0 | 141 | 0.95466 | 1164 |  | 214 | 143 | 1161 | 214 | 143 | 397.67 | 0.0018434 | 0.00082 | 1369 | 0.072068 | 0.0018017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.072068 | 63.0923 | 63.0923 | 0%
Central Coast | CC_Central Coast | BIG BASIN 1102 | 711 | BIG BASIN 110296986 | 0.19487 | 130.7628 | 5.4447 | 0 | 5.4447 | 3.4585 | 3950 | 470 | 469 | 188 | 5 | 5 | 0 | 250 | 0.36479 | 3091 |  | 942 | 500 | 2621 | 937 | 495 | 1519.58 | 0.0014902 | 0.0029 | 1370 | 0.18639 | 0.0017922 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.18639 | 172.0941 | 173.0124 | 0%
Sierra | SI_Sierra | ALLEGHANY 1101 | 5251 | ALLEGHANY 1101804 | 0.91348 | 451.5094 | 21.0044 | 0 | 21.0044 | 0 | 12117 | 0 | 0 | 0 | 0 | 0 | 0 | 559 | 1 | 22016 |  | 3973 | 2618 | 22016 | 3973 | 2618 | 7424.45 | 0.0020232 | 0.01671 | 1371 | 0.49281 | 0.001792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 3. >20 - 30% | 0.49281 | 189.1512 | 189.1512 | 0%
Central Coast | CC_Central Coast | PAUL SWEET 2106 | 6214 | PAUL SWEET 21068091 | 0.20781 | 127.7619 | 5.1657 | 0 | 5.1657 | 0 | 2789 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 1 | 5077 |  | 918 | 605 | 5077 | 918 | 605 | 1714.59 | 0.0016265 | 0.0031 | 1372 | 0.17146 | 0.001786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.17146 | 177.71 | 177.71 | 0%
North Coast | HU_Humboldt | POINT ARENA 1101 | 9466 | POINT ARENA 11014923 | 0.0953 | 73.6373 | 2.7703 | 0 | 2.7703 | 0 | 878 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 1 | 1607 |  | 292 | 193 | 1607 | 292 | 193 | 544.67 | 0.0012942 | 0.00079 | 1373 | 0.037358 | 0.0017789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.037358 | 105.4051 | 105.4051 | 0%
Central Valley | YO_Yosemite | PEORIA 1704 | 973 | PEORIA 170413494 | 0.060894 | 55.973 | 3.6161 | 2.5309 | 1.0852 | 3.386 | 24 | 148 | 14 | 12 | 11 | 9 | 0 | 71 | 0.063636 | 152 |  | 15 | 13 | 4 | 4 | 4 | 5.84 | 0.0010879 | 1e-05 | 1374 | 0.030167 | 0.0017745 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0090533 | 3.6859 | 4.1481 | 69.99%
Central Valley | ST_Stockton | MARTELL 1101 | 7975 | MARTELL 11016074 | 0.19072 | 81.4714 | 3.5955 | 0 | 3.5955 | 0 | 674 | 0 | 0 | 0 | 0 | 0 | 0 | 126 | 1 | 1236 |  | 225 | 149 | 1236 | 225 | 149 | 419.49 | 0.0023409 | 0.0011 | 1375 | 0.092143 | 0.001772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.092143 | 62.579 | 62.579 | 0%
Sierra | SI_Sierra | EL DORADO PH 2102 | 2028 | EL DORADO PH 21026645 | 0.20135 | 89.0993 | 3.8259 | 0 | 3.8259 | 2.9919 | 2984 | 104 | 102 | 87 | 0 | 0 | 0 | 256 | 0.21801 | 1288 |  | 316 | 228 | 1184 | 316 | 228 | 539.48 | 0.0022598 | 0.00148 | 1376 | 0.12746 | 0.0017702 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.12746 | 82.5939 | 82.5939 | 0%
North Coast | HU_Humboldt | REDBUD 1102 | 3965 | REDBUD 1102432 | 0.17857 | 35.784 | 2.4218 | 0.45208 | 1.9697 | 0.94432 | 251 | 103 | 14 | 1 | 0 | 0 | 0 | 114 | 0.61007 | 389 |  | 67 | 36 | 286 | 67 | 36 | 117.53 | 0.0049903 | 0.0007 | 1377 | 0.021171 | 0.0017643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.017219 | 34.0154 | 27.6656 | 18.67%
North Coast | HU_Humboldt | MIDDLETOWN 1101 | 8666 | MIDDLETOWN 11011079 | 0.000489 | 63.7349 | 3.0519 | 2.4797 | 0.57216 | 2.9803 | 276 | 445 | 61 | 48 | 39 | 31 | 0 | 248 | 0.023458 | 457 |  | 63 | 49 | 12 | 24 | 18 | 33.96 | 7.6724e-06 | 0 | 1379 | 0.064932 | 0.0017549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.012173 | 41.9464 | 20.6429 | 81.25%
North Valley | NV_North Valley | BURNEY 1101 | 2938 | BURNEY 11022402 | 0.072687 | 24.0345 | 1.6208 | 0 | 1.6208 | 0 | 201 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1 | 377 |  | 70 | 47 | 377 | 70 | 47 | 129.83 | 0.0030243 | 0.00044 | 1380 | 0.013963 | 0.0017453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.013963 | 43.1877 | 43.1877 | 0%
Central Valley | YO_Yosemite | COARSEGOLD 2102 | 7662 | COARSEGOLD 210210330 | 0.2827 | 179.4214 | 7.472 | 2.6155 | 4.8564 | 7.472 | 1883 | 3895 | 682 | 530 | 470 | 374 | 0 | 152 | 0 | 3895 |  | 682 | 530 | 0 | 212 | 156 | 290.44 | 0.0015756 | 0.00069 | 1381 | 0.25952 | 0.0017417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.16868 | 43.6534 | 91.2745 | 35%
Bay Area | PE_Peninsula | HALF MOON BAY 1103 | 3452 | HALF MOON BAY 11039112 | 0.10597 | 61.1097 | 2.8159 | 1.9703 | 0.84564 | 2.2977 | 366 | 247 | 52 | 0 | 31 | 0 | 0 | 92 | 0.18402 | 372 |  | 75 | 15 | 125 | 44 | 15 | 71.53 | 0.001734 | 0.00016 | 1382 | 0.046954 | 0.001739 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.014101 | 52.0314 | 26.6344 | 69.97%
Central Coast | LP_Los Padres | ATASCADERO 1103 | 6902 | ATASCADERO 1103A14 | 0.95556 | 546.2268 | 23.1911 | 1.1799 | 22.0112 | 6.2777 | 1825 | 515 | 474 | 298 | 39 | 31 | 2 | 582 | 0.72931 | 2941 |  | 913 | 588 | 2426 | 874 | 557 | 1415.72 | 0.0017494 | 0.00318 | 1383 | 0.37741 | 0.0017313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.35821 | 39.7071 | 39.3686 | 5.088%
Central Coast | CC_Central Coast | BIG BASIN 1102 | 8528 | BIG BASIN 11022253 | 0.023541 | 27.8646 | 0.91439 | 0 | 0.91439 | 0.86761 | 393 | 107 | 107 | 64 | 0 | 0 | 0 | 25 | 0.05116 | 144 |  | 114 | 69 | 37 | 114 | 69 | 159.51 | 0.00084483 | 0.0002 | 1384 | 0.03981 | 0.0017309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.03981 | 124.6727 | 124.6727 | 0%
Central Valley | ST_Stockton | FROGTOWN 1701 | 2205 | FROGTOWN 170113412 | 1.5534 | 981.1982 | 38.0574 | 0.30947 | 37.7479 | 0.34337 | 5626 | 26 | 3 | 3 | 0 | 0 | 0 | 834 | 0.99098 | 10163 |  | 1833 | 1209 | 10137 | 1833 | 1209 | 3423.54 | 0.0015832 | 0.00603 | 1385 | 0.94506 | 0.0017277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.93737 | 48.559 | 48.1641 | 0.8132%
Central Coast | LP_Los Padres | MESA 1103 | 7553 | MESA 1103M92 | 0.034563 | 28.1921 | 0.94318 | 0 | 0.94318 | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1 | 216 |  | 41 | 28 | 216 | 41 | 28 | 75.61 | 0.001226 | 0.0001 | 1386 | 0.015537 | 0.0017264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.015537 | 43.4699 | 43.4699 | 0%
North Valley | NV_North Valley | ORO FINO 1102 | 637 | ORO FINO 11022090 | 0.56577 | 386.5091 | 14.7195 | 0.12254 | 14.597 | 5.3581 | 9301 | 2657 | 1399 | 1204 | 205 | 185 | 0 | 822 | 0.63598 | 13407 |  | 3339 | 2482 | 10750 | 3134 | 2297 | 5261.08 | 0.0014638 | 0.00954 | 1387 | 0.34135 | 0.001724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.33851 | 214.7021 | 226.8418 | 0.8325%
Central Valley | ST_Stockton | FROGTOWN 1702 | 3944 | FROGTOWN 170291134 | 0.60438 | 322.3653 | 13.7636 | 0 | 13.7636 | 0 | 894 | 0 | 0 | 0 | 0 | 0 | 0 | 285 | 1 | 1636 |  | 297 | 197 | 1636 | 297 | 197 | 554.13 | 0.0018748 | 0.00116 | 1388 | 0.24784 | 0.0017211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.24784 | 21.5786 | 21.5786 | 0%
Central Coast | LP_Los Padres | CABRILLO 1103 | 1077 | CABRILLO 1103Y12 | 10.4102 | 630.1934 | 25.2928 | 0 | 25.2928 | 0 | 411 | 0 | 0 | 0 | 0 | 0 | 0 | 493 | 1 | 759 |  | 139 | 92 | 759 | 139 | 92 | 258.74 | 0.016519 | 0.00477 | 1389 | 0.017144 | 0.0017144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.017144 | 5.4956 | 5.4956 | 0%
Bay Area | NB_North Bay | OLEMA 1101 | 9541 | OLEMA 110175686 | 0.17382 | 104.3228 | 3.9473 | 0 | 3.9473 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 1 | 212 |  | 40 | 27 | 212 | 40 | 27 | 73.88 | 0.0016662 | 0.00014 | 1390 | 0.0257 | 0.0017133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0257 | 10.1334 | 10.1334 | 0%
North Coast | SO_Sonoma | MIRABEL 1101 | 5248 | MIRABEL 1101228 | 0.18327 | 46.4811 | 1.5578 | 0 | 1.5578 | 0 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1 | 612 |  | 112 | 75 | 612 | 112 | 75 | 208.52 | 0.0039429 | 0.00092 | 1391 | 0.046034 | 0.001705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.046034 | 71.8979 | 71.8979 | 0%
Sierra | SI_Sierra | FORESTHILL 1101 | 8334 | FORESTHILL 110137238 | 0.66796 | 258.842 | 11.1561 | 0 | 11.1561 | 0 | 6268 | 0 | 0 | 0 | 0 | 0 | 0 | 462 | 1 | 11395 |  | 2057 | 1356 | 11395 | 2057 | 1356 | 3843.64 | 0.0025806 | 0.01104 | 1392 | 0.2496 | 0.001698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 0.2496 | 184.3841 | 184.3841 | 0%
North Coast | SO_Sonoma | SONOMA 1104 | 3121 | SONOMA 110478372 | 3.2141 | 422.6658 | 16.1542 | 0 | 16.1542 | 0 | 2136 | 0 | 0 | 0 | 0 | 0 | 0 | 329 | 1 | 3891 |  | 704 | 464 | 3891 | 704 | 464 | 1314.67 | 0.0076045 | 0.01113 | 1393 | 0.01863 | 0.0016936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 0.01863 | 43.5801 | 43.5801 | 0%
Central Valley | ST_Stockton | WEST POINT 1102 | 8547 | WEST POINT 11021535 | 0.12526 | 67.5182 | 3.4716 | 0.775 | 2.6966 | 2.997 | 1733 | 2872 | 621 | 488 | 529 | 432 | 0 | 236 | 0.13672 | 3304 |  | 699 | 540 | 432 | 170 | 108 | 271.78 | 0.0018551 | 0.00066 | 1394 | 0.0829 | 0.0016918 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.064393 | 63.0426 | 201.3486 | 22.32%
Central Valley | ST_Stockton | WEST POINT 1101 | 3162 | WEST POINT 11014706 | 0.47602 | 289.6454 | 11.7835 | 0.021023 | 11.7625 | 3.046 | 8197 | 682 | 681 | 534 | 192 | 133 | 0 | 761 | 0.7415 | 11729 |  | 2675 | 1848 | 11047 | 2483 | 1715 | 4395.94 | 0.0016435 | 0.00849 | 1395 | 0.015202 | 0.0016891 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.015175 | 211.0946 | 227.0119 | 0.1784%
Central Coast | CC_Central Coast | CAMP EVERS 2106 | 7753 | CAMP EVERS 210660120 | 0.093326 | 58.1077 | 2.3314 | 0 | 2.3314 | 0.84697 | 711 | 221 | 215 | 155 | 0 | 0 | 0 | 143 | 0.63672 | 1051 |  | 366 | 255 | 830 | 366 | 255 | 576.12 | 0.0016061 | 0.00122 | 1396 | 0.12748 | 0.0016774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.12748 | 156.9846 | 156.9846 | 0%
Central Coast | LP_Los Padres | PASO ROBLES 1104 | 4076 | PASO ROBLES 1104R12 | 1.0315 | 609.1641 | 33.2623 | 0 | 33.2623 | 0 | 2001 | 0 | 0 | 0 | 0 | 0 | 0 | 431 | 1 | 3646 |  | 660 | 435 | 3646 | 660 | 435 | 1232.34 | 0.0016934 | 0.00232 | 1397 | 0.34206 | 0.0016525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.34206 | 19.8423 | 19.8423 | 0%
North Valley | NV_North Valley | WYANDOTTE 1107 | 3997 | WYANDOTTE 11071510 | 1.3886 | 664.9391 | 25.7201 | 15.7809 | 9.9392 | 25.0324 | 3649 | 7849 | 2640 | 2313 | 2153 | 1907 | 0 | 842 | 0.026737 | 8027 |  | 2672 | 2334 | 178 | 519 | 427 | 727.05 | 0.0020883 | 0.00225 | 1398 | 0.6044 | 0.0016469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.23356 | 52.2175 | 103.8877 | 61.36%
North Valley | NV_North Valley | CHALLENGE 1101 | 161 | CHALLENGE 110198174 | 0.72097 | 405.5695 | 20.3517 | 0 | 20.3517 | 0 | 13592 | 0 | 0 | 0 | 0 | 0 | 0 | 497 | 1 | 24695 |  | 4456 | 2936 | 24695 | 4456 | 2936 | 8327.27 | 0.0017777 | 0.01647 | 1399 | 0.47006 | 0.0016436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 0.47006 | 218.9497 | 218.9497 | 0%
Central Valley | ST_Stockton | WEST POINT 1101 | 8741 | WEST POINT 1101L3355 | 0.069119 | 42.2305 | 1.8411 | 0 | 1.8411 | 0 | 1376 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 1 | 2511 |  | 455 | 301 | 2511 | 455 | 301 | 849.34 | 0.0016367 | 0.00155 | 1400 | 0.014759 | 0.0016398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.014759 | 247.1351 | 247.1351 | 0%
Bay Area | NB_North Bay | BOLINAS 1101 | 9394 | BOLINAS 11011232 | 0.047004 | 42.7114 | 2.0562 | 0 | 2.0562 | 0 | 284 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 1 | 528 |  | 97 | 65 | 528 | 97 | 65 | 180.41 | 0.0011005 | 0.00022 | 1401 | 0.03113 | 0.0016384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.03113 | 47.1733 | 47.1733 | 0%
Central Valley | KE_Kern | POSO MOUNTAIN 2101 | 4304 | POSO MOUNTAIN 21014456 | 1.7869 | 494.2827 | 22.9693 | 22.9025 | 0.066856 | 22.9693 | 20 | 306 | 45 | 10 | 45 | 10 | 0 | 341 | 0 | 306 |  | 45 | 10 | 0 | 0 | 0 | 0 | 0.0036152 | 0 | 1402 | 0.095012 | 0.0016381 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.00027655 | 0 | 1.9591 | 99.71%
Bay Area | MI_Mission | CASTRO VALLEY 1108 | 1800 | CASTRO VALLEY 1108MR748 | 0.17378 | 198.4353 | 6.7201 | 0.17841 | 6.5417 | 5.9153 | 688 | 229 | 119 | 69 | 20 | 14 | 0 | 407 | 0.11975 | 380 |  | 146 | 87 | 151 | 126 | 73 | 186.21 | 0.00087573 | 0.00023 | 1403 | 0.15774 | 0.0016262 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.15355 | 19.2611 | 21.7259 | 2.655%
Bay Area | PE_Peninsula | MENLO 1102 | 7085 | MENLO 110212249 | 0.066108 | 37.749 | 1.0555 | 0 | 1.0555 | 0 | 289 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1 | 537 |  | 99 | 66 | 537 | 99 | 66 | 183.96 | 0.0017513 | 0.00036 | 1404 | 0.051811 | 0.0016191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.051811 | 93.7951 | 93.7951 | 0%
North Coast | HU_Humboldt | LOW GAP 1101 | 7099 | LOW GAP 1101circuit_breaker | 0.21709 | 48.483 | 2.1286 | 0 | 2.1286 | 0 | 1097 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 1 | 2004 |  | 363 | 240 | 2004 | 363 | 240 | 677.67 | 0.0044777 | 0.00338 | 1405 | 0.048432 | 0.0016144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.048432 | 170.5347 | 170.5347 | 0%
Sierra | SI_Sierra | APPLE HILL 1104 | 5621 | APPLE HILL 110497086 | 1.0018 | 651.5468 | 25.5091 | 0.097159 | 25.4119 | 2.5606 | 10623 | 460 | 456 | 408 | 1 | 1 | 0 | 1374 | 0.89962 | 17826 |  | 3590 | 2473 | 17366 | 3589 | 2472 | 6479.87 | 0.0015376 | 0.01148 | 1406 | 0.67766 | 0.0016135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 0.67508 | 141.2329 | 140.7341 | 0.3809%
Central Valley | ST_Stockton | CALAVERAS CEMENT 1101 | 3710 | CALAVERAS CEMENT 1101circuit_breaker | 1.4835 | 230.5914 | 9.2843 | 0 | 9.2843 | 0 | 469 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 1 | 864 |  | 158 | 105 | 864 | 158 | 105 | 294.22 | 0.0064333 | 0.00211 | 1407 | 0.15309 | 0.0016115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.15309 | 17.018 | 17.018 | 0%
Central Coast | DA_De Anza | LOS GATOS 1106 | 4990 | LOS GATOS 1106LB48 | 0.56719 | 343.2284 | 14.9356 | 0 | 14.9356 | 0.2947 | 6609 | 0 | 0 | 0 | 0 | 0 | 0 | 339 | 0.98027 | 11777 |  | 2126 | 1401 | 11777 | 2126 | 1401 | 3972.55 | 0.0016525 | 0.00731 | 1408 | 0.38252 | 0.0016005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.38252 | 142.3444 | 142.3444 | 0%
North Coast | HU_Humboldt | LUCERNE 1106 | 2960 | LUCERNE 110638632 | 0.13016 | 94.7408 | 5.6778 | 0 | 5.6778 | 0 | 593 | 1 | 1 | 0 | 1 | 0 | 0 | 155 | 1 | 1090 |  | 199 | 132 | 1089 | 198 | 132 | 369.27 | 0.0013738 | 0.00057 | 1409 | 0.0879 | 0.0015982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0879 | 34.8724 | 35.0485 | 0%
Sierra | SI_Sierra | BELL 1107 | 3016 | BELL 1107circuit_breaker | 0.024311 | 7.2233 | 0.30852 | 0.20189 | 0.10663 | 0.30852 | 25 | 116 | 23 | 15 | 14 | 8 | 0 | 12 | 0 | 116 |  | 23 | 15 | 0 | 9 | 7 | 12.33 | 0.0033656 | 6e-05 | 1410 | 0.0079817 | 0.0015963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0027586 | 84.405 | 74.5488 | 65.44%
Central Coast | CC_Central Coast | CAMP EVERS 2105 | 689 | CAMP EVERS 210512590 | 0.1551 | 131.3563 | 5.8377 | 0 | 5.8377 | 0 | 3579 | 0 | 0 | 0 | 0 | 0 | 0 | 221 | 1 | 6512 |  | 1176 | 776 | 6512 | 1176 | 776 | 2197.2 | 0.0011808 | 0.00289 | 1411 | 0.12889 | 0.0015912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.12889 | 201.4496 | 201.4496 | 0%
Sierra | SI_Sierra | HIGGINS 1110 | 2470 | HIGGINS 111051794 | 0.10212 | 66.6519 | 3.208 | 0 | 3.208 | 0 | 699 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 1 | 1282 |  | 233 | 154 | 1282 | 233 | 154 | 434.59 | 0.0015322 | 0.00074 | 1412 | 0.073168 | 0.0015906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.073168 | 72.632 | 72.632 | 0%
North Coast | SO_Sonoma | MIRABEL 1102 | 2069 | MIRABEL 110238514 | 0.48283 | 292.2083 | 12.0297 | 0.82633 | 11.2034 | 11.9034 | 5056 | 1047 | 1047 | 293 | 289 | 0 | 0 | 748 | 0.010501 | 1144 |  | 1064 | 304 | 97 | 775 | 304 | 1070.48 | 0.0016524 | 0.00266 | 1413 | 0.25586 | 0.0015892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.23828 | 69.1754 | 88.4475 | 6.869%
Central Valley | YO_Yosemite | COARSEGOLD 2102 | 4462 | COARSEGOLD 21025722 | 0.096302 | 45.8252 | 1.854 | 0 | 1.854 | 0 | 274 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 1 | 510 |  | 94 | 63 | 510 | 94 | 63 | 174.68 | 0.0021015 | 0.00041 | 1414 | 0.061392 | 0.0015741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.061392 | 50.7018 | 50.7018 | 0%
Sierra | SI_Sierra | WEIMAR 1102 | 1746 | WEIMAR 11026175 | 0.083721 | 46.0012 | 1.7953 | 0 | 1.7953 | 0 | 835 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 1 | 1529 |  | 278 | 184 | 1529 | 278 | 184 | 518.47 | 0.00182 | 0.00105 | 1415 | 0.071468 | 0.0015536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.071468 | 154.8518 | 154.8518 | 0%
Central Valley | FR_Fresno | AUBERRY 1101 | 3827 | AUBERRY 110137536 | 0.24533 | 124.6494 | 4.6019 | 0.25758 | 4.3441 | 0.45928 | 753 | 22 | 14 | 9 | 8 | 7 | 0 | 181 | 0.9002 | 1264 |  | 240 | 159 | 1242 | 232 | 152 | 429.62 | 0.0019682 | 0.00095 | 1416 | 0.093 | 0.00155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.087791 | 53.4054 | 52.1524 | 5.597%
Central Valley | ST_Stockton | ELECTRA 1101 | 1117 | ELECTRA 110136816 | 0.051113 | 109.3954 | 5.0434 | 0 | 5.0434 | 0 | 1163 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 1 | 2124 |  | 385 | 255 | 2124 | 385 | 255 | 718.61 | 0.00046723 | 0.00037 | 1417 | 0.11132 | 0.0015461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.11132 | 76.3378 | 76.3378 | 0%
North Valley | NV_North Valley | BIG MEADOWS 2101 | 1060 | BIG MEADOWS 21012260 | 0.46695 | 285.7748 | 12.4566 | 0 | 12.4566 | 0 | 6512 | 0 | 0 | 0 | 0 | 0 | 0 | 506 | 1 | 11838 |  | 2137 | 1409 | 11838 | 2137 | 1409 | 3993.11 | 0.001634 | 0.00726 | 1418 | 0.30293 | 0.0015455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.30293 | 171.5552 | 171.5552 | 0%
North Coast | HU_Humboldt | HOOPA 1101 | 5073 | HOOPA 110182542 | 0.34347 | 245.3242 | 13.4106 | 0 | 13.4106 | 0 | 5758 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 1 | 10469 |  | 1890 | 1246 | 10469 | 1890 | 1246 | 3531.51 | 0.0014001 | 0.0055 | 1419 | 0.27624 | 0.0015432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.27624 | 140.9332 | 140.9332 | 0%
Sierra | SI_Sierra | DRUM 1101 | 9161 | DRUM 1101circuit_breaker | 0.095918 | 62.647 | 1.5511 | 0 | 1.5511 | 0 | 371 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 1 | 686 |  | 126 | 84 | 686 | 126 | 84 | 234.36 | 0.0015311 | 0.0004 | 1420 | 0.016944 | 0.0015403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.016944 | 81.2308 | 81.2308 | 0%
North Valley | NV_North Valley | ORO FINO 1102 | 6696 | ORO FINO 110238698 | 0.54743 | 354.9415 | 15.9201 | 0 | 15.9201 | 4.7652 | 9467 | 189 | 189 | 124 | 0 | 0 | 0 | 509 | 0.70068 | 12244 |  | 2364 | 1558 | 12055 | 2364 | 1558 | 4323.63 | 0.0015423 | 0.00758 | 1421 | 0.42033 | 0.0015397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.42033 | 148.4918 | 148.4918 | 0%
North Coast | SO_Sonoma | SANTA ROSA A 1104 | 1573 | RINCON 1104circuit_breaker | 0.072987 | 83.1737 | 3.4303 | 0.068561 | 3.3617 | 0.89432 | 931 | 129 | 129 | 23 | 0 | 0 | 0 | 199 | 0.73929 | 1388 |  | 358 | 174 | 1259 | 358 | 174 | 603.77 | 0.00087753 | 0.00065 | 1422 | 0.055116 | 0.001531 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.054014 | 106.4924 | 104.364 | 1.999%
North Valley | NV_North Valley | PARADISE 1104 | 2546 | PARADISE 1104circuit_breaker | 0.83059 | 963.5226 | 47.8432 | 24.568 | 23.275 | 40.479 | 4289 | 5661 | 2122 | 2012 | 1532 | 1456 | 0 | 3069 | 0.15392 | 6862 |  | 2339 | 2155 | 1201 | 807 | 699 | 1213.68 | 0.00086203 | 0.00145 | 1423 | 0.18935 | 0.001527 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.092115 | 34.6724 | 48.8889 | 51.35%
North Valley | NV_North Valley | PIT NO 5 1101 | 9046 | PIT NO 5 11011614 | 0.068414 | 26.4768 | 1.31 | 0 | 1.31 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1 | 466 |  | 86 | 58 | 466 | 86 | 58 | 159.76 | 0.0025839 | 0.00046 | 1424 | 0.016792 | 0.0015266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.016792 | 65.647 | 65.647 | 0%
Central Valley | ST_Stockton | CLAY 1103 | 7072 | CLAY 1103circuit_breaker | 0.42432 | 99.8469 | 5.5227 | 0 | 5.5227 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 1 | 181 |  | 35 | 24 | 181 | 35 | 24 | 64.24 | 0.0042497 | 0.00031 | 1425 | 0.062535 | 0.0015252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.062535 | 6.3374 | 6.3374 | 0%
Central Coast | LP_Los Padres | CAYUCOS 1102 | 4597 | CAYUCOS 1102W18 | 0.045163 | 42.6352 | 1.9153 | 0 | 1.9153 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 1 | 63 |  | 13 | 10 | 63 | 13 | 10 | 23.48 | 0.0010593 | 3e-05 | 1426 | 0.012187 | 0.0015233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.012187 | 6.7873 | 6.7873 | 0%
Sierra | SI_Sierra | COLUMBIA HILL 1101 | 7202 | COLUMBIA HILL 11018233 | 0.21185 | 120.8921 | 4.672 | 0 | 4.672 | 0 | 1901 | 0 | 0 | 0 | 0 | 0 | 0 | 247 | 1 | 3464 |  | 627 | 414 | 3464 | 627 | 414 | 1170.75 | 0.0017524 | 0.00228 | 1427 | 0.11261 | 0.0015217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.11261 | 134.2046 | 134.2046 | 0%
Central Coast | CC_Central Coast | POINT MORETTI 1101 | 7358 | POINT MORETTI 110136514 | 0.21751 | 170.623 | 7.3655 | 0 | 7.3655 | 0 | 5170 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 1 | 9401 |  | 1697 | 1119 | 9401 | 1697 | 1119 | 3170.98 | 0.0012748 | 0.0045 | 1428 | 0.15034 | 0.0015186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.15034 | 230.3975 | 230.3975 | 0%
Bay Area | NB_North Bay | ALTO 1122 | 491 | ALTO 112278672 | 0.50549 | 103.2655 | 5.3919 | 0 | 5.3919 | 0 | 1008 | 0 | 0 | 0 | 0 | 0 | 0 | 206 | 1 | 1843 |  | 334 | 221 | 1843 | 334 | 221 | 623.45 | 0.0048951 | 0.0034 | 1429 | 0.089559 | 0.0015179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.089559 | 61.9453 | 61.9453 | 0%
North Valley | NV_North Valley | NOTRE DAME 1104 | 3043 | NOTRE DAME 11042028 | 0.33298 | 231.2527 | 9.8915 | 0 | 9.8915 | 0 | 3126 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 1 | 5689 |  | 1028 | 678 | 5689 | 1028 | 678 | 1920.37 | 0.0014399 | 0.00308 | 1430 | 0.22824 | 0.0015116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.22824 | 103.9279 | 103.9279 | 0%
Central Coast | LP_Los Padres | BUELLTON 1101 | 5393 | BUELLTON 1101Y36 | 1.1999 | 794.5874 | 35.8415 | 0 | 35.8415 | 0 | 654 | 0 | 0 | 0 | 0 | 0 | 0 | 476 | 1 | 1200 |  | 218 | 145 | 1200 | 218 | 145 | 406.66 | 0.0015101 | 0.00068 | 1431 | 0.30479 | 0.0015089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.30479 | 6.0823 | 6.0823 | 0%
North Valley | NV_North Valley | PIT NO 1 1101 | 7469 | PIT NO 1 110170952 | 0.046359 | 36.1861 | 1.8295 | 0 | 1.8295 | 0 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 1 | 219 |  | 42 | 28 | 219 | 42 | 28 | 77.25 | 0.0012811 | 0.00011 | 1433 | 0.033125 | 0.0015057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.033125 | 22.9565 | 22.9565 | 0%
North Coast | HU_Humboldt | HOOPA 1101 | 3774 | HOOPA 11017468 | 0.18105 | 132.278 | 7.2282 | 0 | 7.2282 | 0.25 | 2655 | 9 | 9 | 0 | 0 | 0 | 0 | 160 | 0.96541 | 4675 |  | 853 | 557 | 4666 | 853 | 557 | 1588.55 | 0.0013687 | 0.00243 | 1434 | 0.14293 | 0.0015045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.14293 | 118.0097 | 118.0097 | 0%
Central Coast | CC_Central Coast | HOLLISTER 2102 | 6546 | HOLLISTER 21024780 | 0.051926 | 24.7241 | 2.0917 | 0 | 2.0917 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 1 | 134 |  | 26 | 18 | 134 | 26 | 18 | 47.68 | 0.0021002 | 0.00011 | 1435 | 0.012035 | 0.0015044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.012035 | 12.4303 | 12.4303 | 0%
Central Valley | YO_Yosemite | MARIPOSA 2101 | 47 | MARIPOSA 210135244 | 0.69566 | 439.6934 | 17.1491 | 11.3619 | 5.7873 | 16.4669 | 1434 | 3153 | 423 | 376 | 366 | 338 | 0 | 488 | 0.03978 | 3257 |  | 442 | 388 | 104 | 76 | 50 | 113.48 | 0.0015822 | 0.00025 | 1436 | 0.30172 | 0.0014936 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.10182 | 13.1322 | 25.774 | 66.25%
Sierra | SI_Sierra | SHINGLE SPRINGS 2109 | 2020 | SHINGLE SPRINGS 210911092 | 0.84492 | 553.8124 | 22.3091 | 0 | 22.3091 | 0 | 3812 | 0 | 0 | 0 | 0 | 0 | 0 | 502 | 1 | 6935 |  | 1253 | 826 | 6935 | 1253 | 826 | 2340.76 | 0.0015257 | 0.00398 | 1437 | 0.48185 | 0.0014826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.48185 | 56.1654 | 56.1654 | 0%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1105 | 1673 | SAN LUIS OBISPO 1105796050 | 0.023154 | 17.9443 | 0.75606 | 0 | 0.75606 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 1 | 110 |  | 22 | 15 | 110 | 22 | 15 | 40.04 | 0.0012903 | 6e-05 | 1438 | 0.0088838 | 0.0014806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0088838 | 29.0982 | 29.0982 | 0%
North Coast | SO_Sonoma | SANTA ROSA A 1104 | 4695 | SANTA ROSA A 1104642 | 0.56026 | 308.4726 | 12.775 | 2.2339 | 10.5411 | 11.5246 | 912 | 315 | 305 | 243 | 2 | 0 | 2 | 747 | 0.097877 | 478 |  | 335 | 263 | 163 | 333 | 263 | 470.88 | 0.0018162 | 0.00126 | 1439 | 0.27435 | 0.001475 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.22638 | 31.5906 | 26.2231 | 17.49%
Central Coast | LP_Los Padres | CHOLAME 2102 | 8737 | CHOLAME 21025597 | 0.19365 | 111.7064 | 5.2059 | 5.0312 | 0.17443 | 5.2059 | 108 | 166 | 5 | 4 | 4 | 4 | 0 | 96 | 0 | 166 |  | 5 | 4 | 0 | 1 | 0 | 1.37 | 0.0017336 | 0 | 1440 | 0.049822 | 0.0014654 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0016694 | 5.7329 | 0.96045 | 96.65%
Central Valley | YO_Yosemite | CURTIS 1702 | 5394 | CURTIS 17029220 | 0.51606 | 235.9918 | 10.8367 | 1.0498 | 9.7869 | 1.5411 | 1359 | 404 | 124 | 88 | 116 | 86 | 0 | 254 | 0.85779 | 2531 |  | 509 | 343 | 2127 | 393 | 257 | 729.84 | 0.0021868 | 0.00179 | 1441 | 0.19485 | 0.0014651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.17598 | 40.1556 | 46.9698 | 9.688%
North Valley | NV_North Valley | CLARK ROAD 1102 | 5590 | CLARK ROAD 11022070 | 0.76243 | 223.925 | 12.4328 | 8.0547 | 4.378 | 12.0472 | 417 | 833 | 335 | 223 | 238 | 144 | 0 | 313 | 0.031015 | 857 |  | 339 | 226 | 24 | 101 | 82 | 140.53 | 0.0034049 | 0.00072 | 1442 | 0.086172 | 0.0014605 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.030344 | 23.0697 | 27.2667 | 64.79%
Bay Area | MI_Mission | VINEYARD 2107 | 8829 | VINEYARD 2107MR332 | 0.023546 | 15.0081 | 1.2038 | 0 | 1.2038 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 1 | 114 |  | 23 | 16 | 114 | 23 | 16 | 41.77 | 0.0015689 | 8e-05 | 1443 | 0.010203 | 0.0014576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.010203 | 19.1064 | 19.1064 | 0%
Sierra | SI_Sierra | EL DORADO PH 2101 | 2461 | EL DORADO PH 2101circuit_breaker | 0.70831 | 375.7478 | 17.9945 | 0.061364 | 17.9331 | 8.222 | 10040 | 933 | 900 | 860 | 378 | 354 | 0 | 974 | 0.54308 | 10841 |  | 2688 | 2038 | 9908 | 2310 | 1684 | 4056.42 | 0.0018851 | 0.00905 | 1444 | 0.36934 | 0.0014541 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.36808 | 128.8118 | 149.3789 | 0.341%
Central Coast | LP_Los Padres | PALMER 1101 | 7116 | PALMER 110198478 | 0.08922 | 96.5894 | 4.6208 | 0 | 4.6208 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 1 | 145 |  | 28 | 19 | 145 | 28 | 19 | 51.41 | 0.0009237 | 5e-05 | 1445 | 0.0028986 | 0.0014493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0028986 | 6.0595 | 6.0595 | 0%
Bay Area | PE_Peninsula | MENLO 1103 | 8158 | MENLO 11037902 | 0.22123 | 231.6905 | 10.943 | 0 | 10.943 | 0 | 1907 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 1 | 3475 |  | 629 | 415 | 3475 | 629 | 415 | 1174.48 | 0.00095485 | 0.00125 | 1446 | 0.19267 | 0.0014487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.19267 | 57.4797 | 57.4797 | 0%
Central Valley | ST_Stockton | PINE GROVE 1102 | 4787 | PINE GROVE 1102circuit_breaker | 0.53961 | 304.9223 | 13.5049 | 0 | 13.5049 | 0 | 4988 | 0 | 0 | 0 | 0 | 0 | 0 | 556 | 1 | 9070 |  | 1638 | 1080 | 9070 | 1638 | 1080 | 3060.36 | 0.0017697 | 0.00603 | 1447 | 0.23946 | 0.0014339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.23946 | 121.2891 | 121.2891 | 0%
Central Valley | ST_Stockton | FROGTOWN 1702 | 3556 | FROGTOWN 1702circuit_breaker | 0.17135 | 47.2571 | 3.0447 | 0 | 3.0447 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 1 | 239 |  | 45 | 31 | 239 | 45 | 31 | 83.16 | 0.0036258 | 0.00034 | 1448 | 0.045877 | 0.0014337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.045877 | 14.7798 | 14.7798 | 0%
Central Valley | FR_Fresno | DUNLAP 1102 | 5011 | DUNLAP 11027360 | 0.25538 | 189.8042 | 9.2366 | 0 | 9.2366 | 0 | 555 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 1 | 1020 |  | 186 | 123 | 1020 | 186 | 123 | 346.62 | 0.0013455 | 0.00052 | 1449 | 0.090166 | 0.0014312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.090166 | 20.1374 | 20.1374 | 0%
Sierra | SI_Sierra | EL DORADO PH 2101 | 6623 | EL DORADO PH 210113532 | 0.16966 | 116.6872 | 5.2706 | 0 | 5.2706 | 0 | 3736 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 1 | 6797 |  | 1228 | 810 | 6797 | 1228 | 810 | 2294.09 | 0.001454 | 0.00371 | 1450 | 0.12148 | 0.0014292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.12148 | 232.9886 | 232.9886 | 0%
Central Valley | ST_Stockton | ELECTRA 1101 | 4699 | ELECTRA 11017104 | 0.38061 | 234.5348 | 10.8494 | 0 | 10.8494 | 0 | 4633 | 0 | 0 | 0 | 0 | 0 | 0 | 295 | 1 | 8426 |  | 1522 | 1003 | 8426 | 1522 | 1003 | 2843.48 | 0.0016228 | 0.00514 | 1451 | 0.28856 | 0.0014285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.28856 | 140.2838 | 140.2838 | 0%
Central Valley | YO_Yosemite | SPRING GAP 1702 | 9129 | circuit_breaker | 0.28223 | 185.0877 | 7.2254 | 0 | 7.2254 | 0 | 1073 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 1 | 1961 |  | 356 | 235 | 1961 | 356 | 235 | 664.21 | 0.0015249 | 0.00113 | 1452 | 0.092782 | 0.0014274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.092782 | 49.2708 | 49.2708 | 0%
Central Coast | LP_Los Padres | MESA 1101 | 325 | MESA 1101circuit_breaker | 0.25542 | 313.8741 | 14.0114 | 0 | 14.0114 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 1 | 119 |  | 24 | 16 | 119 | 24 | 16 | 43.59 | 0.00081376 | 4e-05 | 1453 | 0.064216 | 0.001427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.064216 | 1.7129 | 1.7129 | 0%
Sierra | SI_Sierra | BRUNSWICK 1104 | 4033 | BRUNSWICK 11041020 | 0.93169 | 699.678 | 28.4042 | 0.2428 | 28.1614 | 0.29015 | 11296 | 329 | 190 | 182 | 189 | 181 | 0 | 754 | 0.98978 | 20645 |  | 3856 | 2598 | 20316 | 3667 | 2417 | 6852.23 | 0.0013316 | 0.01015 | 1455 | 0.53002 | 0.0014248 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 5. >40 - 50% | 4. >30 - 40% | 0.52549 | 130.2139 | 135.7547 | 0.8548%
Central Valley | YO_Yosemite | MIWUK 1701 | 1362 | MIWUK 170193062 | 0.34804 | 206.2442 | 8.7566 | 3.328 | 5.4286 | 7.4411 | 3375 | 630 | 586 | 410 | 345 | 261 | 20 | 466 | 0.15023 | 1553 |  | 753 | 520 | 923 | 408 | 259 | 642.03 | 0.0016875 | 0.00143 | 1456 | 0.13963 | 0.0014248 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.086561 | 75.1575 | 85.992 | 38.01%
Sierra | SI_Sierra | EL DORADO PH 2101 | 578 | EL DORADO PH 21016852 | 0.92534 | 537.6767 | 25.2229 | 1.6428 | 23.5801 | 13.4739 | 14527 | 4036 | 2818 | 2566 | 964 | 925 | 0 | 1391 | 0.46581 | 16330 |  | 5036 | 4028 | 12294 | 4072 | 3103 | 6685.1 | 0.001721 | 0.01457 | 1457 | 0.56408 | 0.0014173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 0.52734 | 172.6879 | 199.6597 | 6.513%
North Coast | SO_Sonoma | MONTE RIO 1113 | 6809 | MONTE RIO 11138299 | 0.038616 | 29.5776 | 0.92273 | 0 | 0.92273 | 0 | 477 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1 | 878 |  | 160 | 107 | 878 | 160 | 107 | 298.22 | 0.0013056 | 0.00043 | 1458 | 0.024077 | 0.0014163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.024077 | 173.399 | 173.399 | 0%
Sierra | SI_Sierra | APPLE HILL 1104 | 2592 | APPLE HILL 110412947 | 0.21044 | 119.4456 | 4.511 | 0 | 4.511 | 0 | 3452 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 1 | 6281 |  | 1135 | 748 | 6281 | 1135 | 748 | 2120.24 | 0.0017618 | 0.00416 | 1459 | 0.084889 | 0.0014148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.084889 | 251.608 | 251.608 | 0%
North Coast | SO_Sonoma | DUNBAR 1103 | 3473 | DUNBAR 1103circuit_breaker | 0.082199 | 47.7521 | 2.3884 | 0.21193 | 2.1765 | 1.7509 | 219 | 51 | 10 | 1 | 0 | 0 | 0 | 82 | 0.26691 | 160 |  | 30 | 15 | 109 | 30 | 15 | 50.91 | 0.0017214 | 0.00011 | 1460 | 0.039611 | 0.0014147 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.036096 | 13.7835 | 12.5605 | 8.873%
Central Valley | YO_Yosemite | MERCED FALLS 1102 | 2139 | MERCED FALLS 110222774 | 0.016956 | 17.9889 | 0.67008 | 0.67008 | 0 | 0.67008 | 2 | 40 | 3 | 3 | 3 | 3 | 0 | 23 | 0 | 40 |  | 3 | 3 | 0 | 0 | 0 | 0 | 0.00094258 | 0 | 1461 | 0.0098346 | 0.0014049 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0 | 0 | 4.4771 | 100%
Central Valley | YO_Yosemite | COARSEGOLD 2102 | 7643 | COARSEGOLD 210210207 | 0.10208 | 45.0328 | 1.8682 | 0 | 1.8682 | 0 | 566 | 4 | 0 | 0 | 0 | 0 | 0 | 39 | 1 | 1044 |  | 190 | 126 | 1040 | 190 | 126 | 353.9 | 0.0022668 | 0.0009 | 1462 | 0.07723 | 0.0014042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.07723 | 101.7032 | 101.7032 | 0%
North Valley | NV_North Valley | OREGON TRAIL 1102 | 4253 | OREGON TRAIL 11021584 | 0.79885 | 315.484 | 13.9006 | 0.86818 | 13.0324 | 1.2133 | 2744 | 336 | 121 | 106 | 121 | 106 | 0 | 527 | 0.91272 | 4895 |  | 945 | 650 | 4559 | 824 | 544 | 1539.19 | 0.0025321 | 0.00434 | 1463 | 0.25106 | 0.0013948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.23538 | 63.2271 | 67.9828 | 6.246%
Central Valley | ST_Stockton | PINE GROVE 1102 | 6260 | PINE GROVE 11026080 | 1.0627 | 828.2205 | 32.6631 | 0 | 32.6631 | 0 | 9640 | 0 | 0 | 0 | 0 | 0 | 0 | 1016 | 1 | 17518 |  | 3161 | 2083 | 17518 | 3161 | 2083 | 5907.19 | 0.0012831 | 0.00843 | 1464 | 0.73263 | 0.0013928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.73263 | 96.776 | 96.776 | 0%
North Coast | SO_Sonoma | SANTA ROSA A 1104 | 7683 | SANTA ROSA A 1104716 | 0.29852 | 213.0098 | 8.4159 | 0.45644 | 7.9595 | 7.3051 | 555 | 306 | 299 | 285 | 0 | 0 | 0 | 415 | 0.13199 | 441 |  | 324 | 301 | 135 | 324 | 301 | 456.03 | 0.0014014 | 0.00094 | 1465 | 0.17721 | 0.0013845 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.1676 | 40.7062 | 38.4985 | 5.424%
Central Valley | ST_Stockton | CLAY 1103 | 8791 | CLAY 1102circuit_breaker | 0.005424 | 14.4596 | 1.2343 | 0.54242 | 0.69205 | 0.54242 | 32 | 25 | 0 | 0 | 0 | 0 | 0 | 25 | 0.56053 | 64 |  | 8 | 6 | 39 | 8 | 6 | 14.47 | 0.00037511 | 1e-05 | 1466 | 0.0095983 | 0.0013712 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0053817 | 11.5599 | 6.4815 | 43.95%
North Coast | HU_Humboldt | PHILO 1102 | 2486 | PHILO 1102920 | 0.59225 | 379.6985 | 19.1528 | 0 | 19.1528 | 0 | 4529 | 0 | 0 | 0 | 0 | 0 | 0 | 329 | 1 | 8237 |  | 1487 | 981 | 8237 | 1487 | 981 | 2778.52 | 0.0015598 | 0.00482 | 1467 | 0.31026 | 0.0013549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.31026 | 77.6386 | 77.6386 | 0%
North Coast | HU_Humboldt | LUCERNE 1106 | 574 | LUCERNE 110647198 | 0.13885 | 58.3237 | 3.6839 | 0 | 3.6839 | 0 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 1 | 437 |  | 81 | 54 | 437 | 81 | 54 | 150.3 | 0.0023807 | 0.0004 | 1468 | 0.04742 | 0.0013549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.04742 | 21.9876 | 21.9876 | 0%
Central Coast | DA_De Anza | STELLING 1110 | 8397 | STELLING 111060080 | 0.27749 | 229.7346 | 10.5822 | 0 | 10.5822 | 0 | 2973 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 1 | 5411 |  | 978 | 645 | 5411 | 978 | 645 | 1826.85 | 0.0012079 | 0.00246 | 1469 | 0.1467 | 0.0013459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.1467 | 92.4194 | 92.4194 | 0%
North Valley | NV_North Valley | BIG BEND 1101 | 6831 | BIG BEND 1101circuit_breaker | 0.8374 | 582.5725 | 22.5583 | 0 | 22.5583 | 0 | 4943 | 0 | 0 | 0 | 0 | 0 | 0 | 522 | 1 | 8989 |  | 1623 | 1070 | 8989 | 1623 | 1070 | 3032.52 | 0.0014374 | 0.00485 | 1470 | 0.34069 | 0.0013413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.34069 | 71.9468 | 71.9468 | 0%
Central Valley | ST_Stockton | CORRAL 1103 | 1561 | CORRAL 110359770 | 0.45199 | 134.7469 | 7.2879 | 0 | 7.2879 | 0 | 285 | 0 | 0 | 0 | 0 | 0 | 0 | 166 | 1 | 530 |  | 98 | 65 | 530 | 98 | 65 | 181.96 | 0.0033543 | 0.00068 | 1471 | 0.072287 | 0.0013387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.072287 | 13.447 | 13.447 | 0%
Central Coast | DA_De Anza | MENLO 1103 | 2549 | MENLO 11031721 | 0.1766 | 165.1884 | 6.7687 | 0 | 6.7687 | 0 | 2244 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 1 | 4087 |  | 739 | 488 | 4087 | 739 | 488 | 1380.26 | 0.0010691 | 0.00164 | 1472 | 0.15412 | 0.0013173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.15412 | 109.1782 | 109.1782 | 0%
Central Coast | LP_Los Padres | PURISIMA 1101 | 4538 | PURISIMA 1101Y42 | 0.049903 | 46.9874 | 3.3665 | 0 | 3.3665 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 1 | 176 |  | 34 | 23 | 176 | 34 | 23 | 62.42 | 0.0010621 | 8e-05 | 1473 | 0.028796 | 0.0013089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.028796 | 10.0996 | 10.0996 | 0%
Sierra | SI_Sierra | ALLEGHANY 1101 | 6913 | ALLEGHANY 1101VR816 | 0.11298 | 88.8648 | 4.3733 | 0 | 4.3733 | 0 | 1783 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 1 | 3250 |  | 588 | 388 | 3250 | 588 | 388 | 1098.06 | 0.0012713 | 0.00155 | 1474 | 0.085027 | 0.0013081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.085027 | 134.4524 | 134.4524 | 0%
Central Valley | YO_Yosemite | CURTIS 1702 | 3408 | CURTIS 17026008 | 0.57538 | 444.4549 | 18.3483 | 0 | 18.3483 | 0 | 5009 | 0 | 0 | 0 | 0 | 0 | 0 | 411 | 1 | 9108 |  | 1645 | 1084 | 9108 | 1645 | 1084 | 3073.37 | 0.0012946 | 0.00443 | 1475 | 0.30077 | 0.0013077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.30077 | 89.6541 | 89.6541 | 0%
Bay Area | DI_Diablo | ROSSMOOR 1106 | 7210 | ROSSMOOR 110639424 | 0.023826 | 18.2465 | 1.0678 | 0 | 1.0678 | 0 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1 | 265 |  | 50 | 34 | 265 | 50 | 34 | 92.35 | 0.0013058 | 0.00014 | 1476 | 0.01436 | 0.0013055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.01436 | 46.8251 | 46.8251 | 0%
Central Valley | YO_Yosemite | RACETRACK 1703 | 8363 | RACETRACK 17036014 | 0.17017 | 138.1418 | 5.5371 | 0.0035985 | 5.5335 | 1.2153 | 1088 | 91 | 67 | 14 | 2 | 2 | 0 | 190 | 0.78051 | 1643 |  | 348 | 200 | 1552 | 346 | 198 | 613.7 | 0.0012319 | 0.00089 | 1477 | 0.11412 | 0.0012968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.11405 | 62.528 | 62.8485 | 0.06499%
Central Valley | ST_Stockton | SALT SPRINGS 2102 | 5890 | SALT SPRINGS 210237300 | 0.27036 | 110.7044 | 4.7402 | 0 | 4.7402 | 0 | 2193 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 1 | 3995 |  | 722 | 477 | 3995 | 722 | 477 | 1348.69 | 0.0024422 | 0.00367 | 1478 | 0.053159 | 0.0012966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.053159 | 152.3158 | 152.3158 | 0%
Central Valley | ST_Stockton | STANISLAUS 1702 | 2984 | STANISLAUS 17021888 | 0.35529 | 335.3498 | 16.8848 | 2.1919 | 14.693 | 16.7956 | 10573 | 15059 | 1799 | 722 | 1639 | 585 | 0 | 928 | 0.0052831 | 15161 |  | 1817 | 734 | 102 | 178 | 149 | 253.04 | 0.0010595 | 0.00039 | 1479 | 0.032406 | 0.0012963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0282 | 12.1146 | 107.6113 | 12.98%
Central Coast | SJ_San Jose | HICKS 2101 | 8296 | HICKS 2101circuit_breaker | 0.035679 | 26.8043 | 2.203 | 0 | 2.203 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 1 | 29 |  | 7 | 6 | 29 | 7 | 6 | 12.2 | 0.0013311 | 2e-05 | 1480 | 0.0090651 | 0.001295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0090651 | 3.1774 | 3.1774 | 0%
Central Valley | YO_Yosemite | RACETRACK 1703 | 2953 | RACETRACK 170311270 | 0.60508 | 320.5321 | 13.7027 | 0.43883 | 13.2638 | 0.9161 | 1443 | 2 | 1 | 0 | 1 | 0 | 0 | 456 | 0.93314 | 2459 |  | 446 | 294 | 2457 | 445 | 294 | 830.78 | 0.0018877 | 0.00175 | 1481 | 0.15107 | 0.0012912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.14623 | 33.5499 | 32.5484 | 3.202%
Central Coast | LP_Los Padres | FOOTHILL 1102 | 2406 | FOOTHILL 1102V06 | 0.04094 | 19.8816 | 1.5684 | 0 | 1.5684 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1 | 54 |  | 12 | 9 | 54 | 12 | 9 | 21.3 | 0.0020592 | 5e-05 | 1482 | 0.0051532 | 0.0012883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0051532 | 7.6512 | 7.6512 | 0%
North Coast | SO_Sonoma | SANTA ROSA A 1111 | 5720 | SANTA ROSA A 1111114 | 0.2469 | 171.0811 | 6.086 | 2.6174 | 3.4688 | 6.086 | 724 | 1613 | 598 | 269 | 268 | 86 | 0 | 226 | 0 | 1613 |  | 598 | 269 | 0 | 330 | 183 | 452.1 | 0.0014432 | 0.00099 | 1483 | 0.10163 | 0.0012865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.057926 | 95.1351 | 98.2585 | 43.01%
Sierra | SI_Sierra | HIGGINS 1104 | 3 | HIGGINS 1104498932 | 0.13078 | 90.5703 | 3.5066 | 0 | 3.5066 | 0 | 845 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 1 | 1547 |  | 281 | 186 | 1547 | 281 | 186 | 524.2 | 0.001444 | 0.00084 | 1484 | 0.07974 | 0.0012861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.07974 | 80.1339 | 80.1339 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2106 | 2615 | CAMP EVERS 210660124 | 0.73072 | 613.388 | 26.2407 | 0 | 26.2407 | 2.653 | 14537 | 941 | 940 | 616 | 1 | 1 | 0 | 1770 | 0.8989 | 24682 |  | 5223 | 3438 | 23741 | 5222 | 3437 | 9290.83 | 0.0011913 | 0.01294 | 1485 | 0.48952 | 0.0012815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 0.48952 | 199.0037 | 199.0418 | 0%
Sierra | SI_Sierra | GRASS VALLEY 1103 | 7910 | GRASS VALLEY 110358498 | 0.046387 | 37.3912 | 1.6583 | 0 | 1.6583 | 0 | 548 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 1 | 1007 |  | 184 | 122 | 1007 | 184 | 122 | 342.71 | 0.0012406 | 0.00047 | 1486 | 0.021784 | 0.0012814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.021784 | 110.9548 | 110.9548 | 0%
Sierra | SI_Sierra | APPLE HILL 1104 | 5530 | APPLE HILL 1104circuit_breaker | 0.13362 | 83.7432 | 3.5407 | 0 | 3.5407 | 0.54053 | 765 | 2 | 2 | 2 | 0 | 0 | 0 | 209 | 0.84734 | 1190 |  | 218 | 145 | 1188 | 218 | 145 | 405.58 | 0.0015956 | 0.00072 | 1487 | 0.083174 | 0.0012796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.083174 | 61.5694 | 61.5694 | 0%
Bay Area | MI_Mission | SUNOL 1101 | 8824 | FREMONT 1104MR707 | 0.12773 | 37.4044 | 1.2778 | 1.1375 | 0.14034 | 1.1809 | 7 | 51 | 0 | 0 | 0 | 0 | 0 | 52 | 0.075886 | 53 |  | 0 | 0 | 2 | 0 | 0 | 0.18 | 0.0034147 | 0 | 1488 | 0.0076763 | 0.0012794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.00084306 | 0 | 0 | 89.02%
Central Coast | CC_Central Coast | BIG BASIN 1102 | 2681 | BIG BASIN 110212124 | 0.13428 | 109.3658 | 3.9449 | 0 | 3.9449 | 3.446 | 2669 | 338 | 334 | 137 | 98 | 35 | 0 | 304 | 0.12646 | 952 |  | 445 | 210 | 614 | 347 | 175 | 530.65 | 0.0012278 | 0.00089 | 1489 | 0.088081 | 0.0012765 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.088081 | 87.962 | 112.8043 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2106 | 5809 | CAMP EVERS 210694770 | 0.000387 | 30.6778 | 1.6288 | 0 | 1.6288 | 0.10492 | 563 | 52 | 52 | 37 | 0 | 0 | 0 | 115 | 0.93558 | 1020 |  | 228 | 154 | 968 | 228 | 154 | 399.48 | 1.2615e-05 | 1e-05 | 1490 | 0.045686 | 0.0012691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.045686 | 139.9814 | 139.9814 | 0%
Central Valley | YO_Yosemite | PEORIA 1701 | 6825 | PEORIA 1701circuit_breaker | 0.37044 | 237.8577 | 9.2932 | 0.16761 | 9.1254 | 0.23049 | 101 | 13 | 1 | 1 | 0 | 0 | 0 | 167 | 0.9752 | 204 |  | 37 | 26 | 191 | 37 | 26 | 67.88 | 0.0015574 | 0.00012 | 1491 | 0.05837 | 0.0012689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.057316 | 4.0546 | 3.9814 | 1.804%
Sierra | SI_Sierra | APPLE HILL 1104 | 2384 | APPLE HILL 110413512 | 1.0299 | 682.6046 | 30.5299 | 0.038826 | 30.4909 | 18.4835 | 14509 | 4199 | 4018 | 3328 | 5 | 4 | 1 | 1885 | 0.39458 | 14600 |  | 5895 | 4565 | 10401 | 5890 | 4561 | 9005.39 | 0.0015087 | 0.01848 | 1492 | 0.53023 | 0.0012655 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 3. >20 - 30% | 0.52955 | 193.1723 | 193.0892 | 0.1272%
Central Valley | YO_Yosemite | CURTIS 1705 | 1364 | CURTIS 170539256 | 2.031 | 645.0706 | 25.2758 | 16.8536 | 8.4222 | 23.5256 | 3544 | 5754 | 3014 | 1239 | 2964 | 1219 | 0 | 902 | 0.069244 | 6200 |  | 3095 | 1292 | 446 | 131 | 73 | 219.61 | 0.0031485 | 0.00086 | 1493 | 0.056842 | 0.0012632 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.01894 | 15.5542 | 122.4493 | 66.68%
Bay Area | MI_Mission | CASTRO VALLEY 1108 | 7251 | CASTRO VALLEY 1108MR341 | 0.062063 | 76.4561 | 2.4059 | 0 | 2.4059 | 0.082765 | 194 | 3 | 3 | 0 | 0 | 0 | 0 | 123 | 0.9656 | 355 |  | 68 | 44 | 352 | 68 | 44 | 124.84 | 0.00081175 | 0.00011 | 1494 | 0.03785 | 0.0012617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.03785 | 28.2642 | 28.2642 | 0%
North Valley | NV_North Valley | PIT NO 1 1101 | 682 | PIT NO 1 11013312 | 0.23648 | 176.5387 | 7.8396 | 0 | 7.8396 | 0 | 609 | 0 | 0 | 0 | 0 | 0 | 0 | 179 | 1 | 1118 |  | 204 | 135 | 1118 | 204 | 135 | 380.1 | 0.0013395 | 0.00057 | 1495 | 0.10069 | 0.0012586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.10069 | 26.0218 | 26.0218 | 0%
North Coast | HU_Humboldt | NEWBURG 1133 | 5092 | NEWBURG 1133circuit_breaker | 0.093117 | 60.5339 | 3.7445 | 0.016667 | 3.7278 | 3.5854 | 2251 | 6390 | 824 | 504 | 10 | 6 | 0 | 62 | 0.042486 | 6564 |  | 856 | 525 | 174 | 846 | 519 | 1174.68 | 0.0015383 | 0.00271 | 1496 | 0.055322 | 0.0012573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.055076 | 226.941 | 228.6015 | 0.4451%
North Coast | HU_Humboldt | FORT BRAGG A 1101 | 7428 | FORT BRAGG A 11013113 | 0.19415 | 230.5649 | 8.4477 | 0 | 8.4477 | 0 | 3983 | 0 | 0 | 0 | 0 | 0 | 0 | 146 | 1 | 7245 |  | 1309 | 863 | 7245 | 1309 | 863 | 2445.38 | 0.00084204 | 0.00229 | 1497 | 0.16449 | 0.0012556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.16449 | 154.9529 | 154.9529 | 0%
Bay Area | PE_Peninsula | HALF MOON BAY 1102 | 977 | HALF MOON BAY 11022032 | 0.027731 | 39.9082 | 3.2114 | 0 | 3.2114 | 0 | 363 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 1 | 671 |  | 123 | 82 | 671 | 123 | 82 | 228.9 | 0.00069487 | 0.00018 | 1498 | 0.017499 | 0.00125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.017499 | 38.3015 | 38.3015 | 0%
Sierra | SI_Sierra | APPLE HILL 1103 | 127 | APPLE HILL 1103circuit_breaker | 0.72791 | 635.0772 | 37.4161 | 0 | 37.4161 | 0 | 8223 | 0 | 0 | 0 | 0 | 0 | 0 | 1245 | 1 | 14945 |  | 2697 | 1778 | 14945 | 2697 | 1778 | 5039.94 | 0.0011462 | 0.00643 | 1499 | 0.57849 | 0.0012468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.57849 | 72.0813 | 72.0813 | 0%
Bay Area | DI_Diablo | BRENTWOOD 2105 | 9055 | BRENTWOOD 210596324 | 0.25513 | 4.9896 | 0.20436 | 0 | 0.20436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.051132 | 0.00043 | 1500 | 0.002489 | 0.0012445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.002489 | 19.5737 | 19.5737 | 0%
Central Valley | YO_Yosemite | SO. CAL. EDISON NO3 1101 | 3395 | SO. CAL. EDISON #3 1101circuit_breaker | 0.56235 | 176.6016 | 6.5682 | 0.425 | 6.1432 | 1.175 | 80 | 62 | 28 | 27 | 0 | 0 | 0 | 130 | 0.82111 | 191 |  | 53 | 44 | 129 | 53 | 44 | 84.22 | 0.0031843 | 0.00035 | 1501 | 0.0086536 | 0.0012362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0080937 | 8.6275 | 8.0692 | 6.471%
Central Coast | CC_Central Coast | PAUL SWEET 2106 | 1533 | PAUL SWEET 21065178 | 0.24757 | 187.7617 | 7.7953 | 0 | 7.7953 | 0 | 3187 | 0 | 0 | 0 | 0 | 0 | 0 | 202 | 1 | 5800 |  | 1048 | 691 | 5800 | 1048 | 691 | 1957.76 | 0.0013185 | 0.00287 | 1502 | 0.14566 | 0.0012344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.14566 | 134.4406 | 134.4406 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2105 | 3883 | CAMP EVERS 210510214 | 0.46919 | 320.7931 | 13.0778 | 0 | 13.0778 | 0 | 8656 | 0 | 0 | 0 | 0 | 0 | 0 | 348 | 1 | 15731 |  | 2839 | 1871 | 15731 | 2839 | 1871 | 5305.22 | 0.0014626 | 0.00863 | 1503 | 0.30842 | 0.0012337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.30842 | 217.0848 | 217.0848 | 0%
Bay Area | NB_North Bay | BASALT 1106 | 6677 | BASALT 11065030 | 0.10858 | 47.8939 | 5.1496 | 0 | 5.1496 | 0 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 1 | 159 |  | 31 | 21 | 159 | 31 | 21 | 56.78 | 0.0022672 | 0.00015 | 1504 | 0.0073833 | 0.0012306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0073833 | 6.0199 | 6.0199 | 0%
North Coast | HU_Humboldt | UPPER LAKE 1101 | 7400 | UPPER LAKE 11016663 | 0.11048 | 60.9183 | 2.4402 | 0.90966 | 1.5305 | 2.4402 | 185 | 424 | 199 | 184 | 0 | 0 | 0 | 69 | 0 | 424 |  | 199 | 184 | 0 | 199 | 184 | 272.63 | 0.0018136 | 0.00075 | 1505 | 0.030656 | 0.0012262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.019228 | 130.0235 | 81.5523 | 37.28%
Central Valley | ST_Stockton | PINE GROVE 1101 | 7702 | PINE GROVE 1101circuit_breaker | 0.02096 | 80.705 | 3.7223 | 0 | 3.7223 | 0 | 1174 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 1 | 2144 |  | 389 | 257 | 2144 | 389 | 257 | 725.89 | 0.00025971 | 0.00021 | 1506 | 0.07567 | 0.0012205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.07567 | 104.5039 | 104.5039 | 0%
North Coast | SO_Sonoma | COTATI 1104 | 4288 | COTATI 110475972 | 0.11292 | 73.2438 | 3.1824 | 0.085038 | 3.0973 | 0.085038 | 104 | 2 | 1 | 0 | 1 | 0 | 0 | 86 | 0.97328 | 198 |  | 38 | 25 | 196 | 37 | 25 | 68.33 | 0.0015416 | 0.00012 | 1507 | 0.051118 | 0.0012171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.049752 | 11.9457 | 11.9407 | 2.672%
Central Valley | YO_Yosemite | MARIPOSA 2101 | 4260 | MARIPOSA 21018030 | 0.64128 | 509.9559 | 19.2053 | 3.9036 | 15.3017 | 8.3242 | 2271 | 2023 | 515 | 458 | 357 | 318 | 0 | 554 | 0.56657 | 4367 |  | 939 | 738 | 2344 | 582 | 420 | 1008.3 | 0.0012575 | 0.00152 | 1508 | 0.27302 | 0.0012134 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.21753 | 38.035 | 48.8927 | 20.33%
Central Valley | YO_Yosemite | SAN JOAQUIN NO3 1102 | 4696 | SAN JOAQUIN #3 110210342 | 0.040825 | 56.2671 | 2.6585 | 0 | 2.6585 | 0 | 719 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 1 | 1318 |  | 240 | 159 | 1318 | 240 | 159 | 447.42 | 0.00072556 | 0.00036 | 1509 | 0.031479 | 0.0012107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.031479 | 90.2757 | 90.2757 | 0%
Central Valley | KE_Kern | POSO MOUNTAIN 2103 | 8214 | POSO MOUNTAIN 21033988 | 2.2725 | 310.3759 | 16.4127 | 0 | 16.4127 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 219 | 1 | 43 |  | 10 | 7 | 43 | 10 | 7 | 17.57 | 0.0073216 | 0.00015 | 1510 | 0.02298 | 0.0012095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.02298 | 0.60928 | 0.60928 | 0%
North Coast | HU_Humboldt | HOOPA 1101 | 8117 | HOOPA 110193038 | 0.015735 | 16.6631 | 0.67045 | 0 | 0.67045 | 0 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1 | 263 |  | 49 | 33 | 263 | 49 | 33 | 90.8 | 0.0009443 | 0.0001 | 1511 | 0.015689 | 0.0012068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.015689 | 73.0847 | 73.0847 | 0%
Sierra | SI_Sierra | GRASS VALLEY 1101 | 3925 | GRASS VALLEY 11012766 | 0.12236 | 103.2767 | 4.2585 | 0.14545 | 4.1131 | 0.30966 | 1403 | 11 | 6 | 6 | 0 | 0 | 0 | 140 | 0.92728 | 2385 |  | 436 | 290 | 2374 | 436 | 290 | 810.98 | 0.0011848 | 0.00107 | 1512 | 0.060111 | 0.0012022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.058058 | 106.0036 | 102.3829 | 3.416%
North Coast | NC_North Coast | RIO DELL 1102 | 4928 | RIO DELL 110270960 | 0.13493 | 95.6477 | 4.9562 | 0 | 4.9562 | 0.12159 | 2037 | 17 | 17 | 1 | 0 | 0 | 0 | 144 | 0.97547 | 3637 |  | 672 | 433 | 3620 | 672 | 433 | 1246.44 | 0.0014107 | 0.00197 | 1513 | 0.071776 | 0.0011963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.071776 | 135.5864 | 135.5864 | 0%
North Coast | SO_Sonoma | MONTE RIO 1111 | 9153 | MONTE RIO 11113891 | 0.081099 | 72.0014 | 3.2057 | 0 | 3.2057 | 3.2055 | 1092 | 871 | 871 | 856 | 13 | 0 | 0 | 86 | 5.9081e-05 | 871 |  | 871 | 856 | 0 | 858 | 856 | 1175.46 | 0.0011264 | 0.00201 | 1514 | 0.059592 | 0.0011918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.059592 | 267.6498 | 271.7051 | 0%
North Coast | HU_Humboldt | KONOCTI 1102 | 230 | KONOCTI 11022293 | 0.20679 | 39.5136 | 1.6384 | 1.0597 | 0.5786 | 1.6384 | 280 | 465 | 88 | 38 | 53 | 17 | 0 | 81 | 0 | 465 |  | 88 | 38 | 0 | 35 | 21 | 47.95 | 0.0052334 | 0.00038 | 1515 | 0.02848 | 0.0011867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.010057 | 60.491 | 53.7094 | 64.67%
Bay Area | MI_Mission | SUNOL 1101 | 8383 | SUNOL 1101circuit_breaker | 0.12715 | 64.4016 | 2.8019 | 2.4114 | 0.39072 | 2.7165 | 79 | 207 | 12 | 5 | 0 | 0 | 0 | 81 | 0.030485 | 212 |  | 13 | 6 | 5 | 13 | 6 | 18.26 | 0.0019743 | 5e-05 | 1516 | 0.043844 | 0.001185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0061139 | 33.2719 | 4.6397 | 86.06%
Central Coast | LP_Los Padres | TEMPLETON 2110 | 4804 | TEMPLETON 2110R94 | 0.32676 | 302.6583 | 13.239 | 0 | 13.239 | 0 | 1112 | 0 | 0 | 0 | 0 | 0 | 0 | 337 | 1 | 2032 |  | 368 | 244 | 2032 | 368 | 244 | 687.04 | 0.0010796 | 0.00083 | 1517 | 0.1184 | 0.001184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.1184 | 27.7966 | 27.7966 | 0%
Bay Area | NB_North Bay | WOODACRE 1101 | 335 | WOODACRE 1101404 | 0.46158 | 300.4224 | 12.5339 | 8.1695 | 4.3642 | 12.5322 | 4215 | 7858 | 2177 | 1035 | 1729 | 820 | 3 | 901 | 0.00013599 | 7859 |  | 2177 | 1035 | 1 | 448 | 215 | 613.85 | 0.0015364 | 0.00143 | 1518 | 0.22463 | 0.0011761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.078213 | 102.6533 | 173.6889 | 65.18%
Central Valley | YO_Yosemite | MIWUK 1702 | 6088 | MIWUK 170219772 | 0.020849 | 12.3913 | 0.68485 | 0.2089 | 0.47595 | 0.46383 | 194 | 40 | 17 | 17 | 0 | 0 | 0 | 28 | 0.32273 | 158 |  | 39 | 32 | 118 | 39 | 32 | 64.05 | 0.0016826 | 0.00014 | 1519 | 0.074328 | 0.0011614 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.051656 | 81.9419 | 56.9469 | 30.5%
Central Valley | KE_Kern | TEJON 1102 | 65 | TEJON 11022455 | 0.23621 | 169.3648 | 6.25 | 6.1553 | 0.094508 | 6.25 | 193 | 735 | 36 | 8 | 36 | 8 | 0 | 301 | 0 | 735 |  | 36 | 8 | 0 | 0 | 0 | 0 | 0.0013947 | 0 | 1520 | 0.085122 | 0.0011503 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.0012871 | 0 | 5.76 | 98.48%
North Coast | SO_Sonoma | MIRABEL 1102 | 265 | MIRABEL 1102332 | 0.29562 | 151.5434 | 5.1116 | 0.33598 | 4.7756 | 5.1116 | 2718 | 857 | 857 | 244 | 249 | 0 | 1 | 369 | 0 | 857 |  | 857 | 244 | 0 | 608 | 244 | 832.96 | 0.0019508 | 0.00247 | 1521 | 0.098904 | 0.0011501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.092403 | 127.3147 | 167.6594 | 6.573%
Sierra | SI_Sierra | PLACERVILLE 1112 | 3185 | PLACERVILLE 111219712 | 0.44287 | 293.2081 | 14.2212 | 0 | 14.2212 | 0.58352 | 4127 | 549 | 412 | 381 | 35 | 16 | 0 | 364 | 0.95897 | 7748 |  | 1712 | 1238 | 7199 | 1677 | 1222 | 2945.4 | 0.0015104 | 0.00527 | 1523 | 0.22836 | 0.0011475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.22836 | 117.9224 | 120.3835 | 0%
Sierra | SI_Sierra | GRASS VALLEY 1101 | 2994 | HIGGINS 11032194 | 5.5e-05 | 21.6804 | 1.0206 | 0 | 1.0206 | 0 | 648 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 1 | 1189 |  | 216 | 143 | 1189 | 216 | 143 | 402.93 | 2.5368e-06 | 0 | 1524 | 0.020631 | 0.0011462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.020631 | 211.6311 | 211.6311 | 0%
Sierra | SI_Sierra | COLUMBIA HILL 1101 | 2433 | COLUMBIA HILL 110135424 | 0.32644 | 345.2507 | 15.1159 | 0 | 15.1159 | 0 | 3824 | 0 | 0 | 0 | 0 | 0 | 0 | 823 | 1 | 6957 |  | 1257 | 829 | 6957 | 1257 | 829 | 2348.22 | 0.00094551 | 0.00247 | 1525 | 0.25352 | 0.001142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.25352 | 83.1574 | 83.1574 | 0%
North Coast | HU_Humboldt | LUCERNE 1103 | 3109 | LUCERNE 1103630 | 0.65331 | 221.9558 | 14.2727 | 0 | 14.2727 | 0 | 1202 | 0 | 0 | 0 | 0 | 0 | 0 | 424 | 1 | 2195 |  | 398 | 263 | 2195 | 398 | 263 | 742.81 | 0.0029434 | 0.00244 | 1526 | 0.1528 | 0.0011403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.1528 | 27.8854 | 27.8854 | 0%
Bay Area | NB_North Bay | NOVATO 1104 | 6982 | NOVATO 110455398 | 0.054952 | 92.0826 | 3.5205 | 0 | 3.5205 | 0 | 213 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1 | 399 |  | 74 | 50 | 399 | 74 | 50 | 137.29 | 0.00059677 | 9e-05 | 1527 | 0.035317 | 0.0011393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.035317 | 21.02 | 21.02 | 0%
Central Valley | YO_Yosemite | CURTIS 1703 | 7955 | CURTIS 1703circuit_breaker | 0.34338 | 173.9138 | 7.2064 | 5.7723 | 1.4341 | 6.9288 | 487 | 1275 | 258 | 114 | 249 | 109 | 0 | 232 | 0.038528 | 1310 |  | 264 | 118 | 35 | 15 | 9 | 23.7 | 0.0019744 | 6e-05 | 1528 | 0.11614 | 0.0011276 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.023113 | 10.4596 | 36.6339 | 80.1%
Central Valley | ST_Stockton | NORTH BRANCH 1101 | 4122 | NORTH BRANCH 1101circuit_breaker | 0.30484 | 312.372 | 18.6367 | 0 | 18.6367 | 0 | 322 | 0 | 0 | 0 | 0 | 0 | 0 | 358 | 1 | 597 |  | 110 | 73 | 597 | 110 | 73 | 204.43 | 0.0009759 | 0.00022 | 1529 | 0.11124 | 0.0011237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.11124 | 5.9023 | 5.9023 | 0%
Bay Area | NB_North Bay | BOLINAS 1101 | 9115 | BOLINAS 110137034 | 0.12326 | 110.6444 | 4.9799 | 3.2854 | 1.6943 | 4.6044 | 825 | 573 | 534 | 436 | 59 | 15 | 14 | 146 | 0.075416 | 687 |  | 555 | 450 | 114 | 496 | 435 | 689.78 | 0.001114 | 0.00115 | 1530 | 0.063866 | 0.0011205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.021729 | 292.7431 | 111.4475 | 65.97%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1101 | 3702 | SAN LUIS OBISPO 1101V12 | 0.80298 | 504.948 | 19.3343 | 0 | 19.3343 | 0 | 532 | 0 | 0 | 0 | 0 | 0 | 0 | 290 | 1 | 978 |  | 178 | 118 | 978 | 178 | 118 | 331.88 | 0.0015902 | 0.00059 | 1531 | 0.17217 | 0.001118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.17217 | 9.2064 | 9.2064 | 0%
Sierra | SI_Sierra | BRUNSWICK 1103 | 1467 | BRUNSWICK 110350070 | 0.94791 | 655.7066 | 27.9619 | 0 | 27.9619 | 0 | 15276 | 0 | 0 | 0 | 0 | 0 | 0 | 1606 | 1 | 27753 |  | 5007 | 3299 | 27753 | 5007 | 3299 | 9357.36 | 0.0014456 | 0.01505 | 1532 | 0.010059 | 0.0011177 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 4. >30 - 40% | 0.010059 | 179.0649 | 179.0649 | 0%
North Coast | HU_Humboldt | ARCATA 1122 | 413 | ARCATA 11225384 | 0.45029 | 418.2017 | 14.9121 | 0 | 14.9121 | 0 | 11363 | 0 | 0 | 0 | 0 | 0 | 0 | 354 | 1 | 20647 |  | 3726 | 2455 | 20647 | 3726 | 2455 | 6962.85 | 0.0010767 | 0.00834 | 1533 | 0.30908 | 0.0011158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.30908 | 249.8638 | 249.8638 | 0%
North Coast | HU_Humboldt | CARLOTTA 1121 | 8197 | CARLOTTA 112144150 | 0.077063 | 64.365 | 3.1975 | 0 | 3.1975 | 0 | 1559 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1 | 2843 |  | 515 | 340 | 2843 | 515 | 340 | 961.42 | 0.0011973 | 0.00128 | 1534 | 0.06969 | 0.0011062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.06969 | 161.0614 | 161.0614 | 0%
Bay Area | MI_Mission | CASTRO VALLEY 1111 | 2916 | CASTRO VALLEY 1109MR334 | 0.16153 | 156.3252 | 10.5144 | 0 | 10.5144 | 0 | 261 | 0 | 0 | 0 | 0 | 0 | 0 | 419 | 1 | 486 |  | 90 | 60 | 486 | 90 | 60 | 167.04 | 0.0010333 | 0.00019 | 1535 | 0.065212 | 0.0011053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.065212 | 8.5597 | 8.5597 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2106 | 7949 | CAMP EVERS 210611533 | 0.064278 | 36.1907 | 1.5199 | 0 | 1.5199 | 0 | 873 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 1 | 1598 |  | 290 | 192 | 1598 | 290 | 192 | 541.12 | 0.0017761 | 0.00107 | 1536 | 0.053683 | 0.0010956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.053683 | 190.8037 | 190.8037 | 0%
Bay Area | NB_North Bay | SILVERADO 2105 | 7505 | SILVERADO 21051421 | 0.24126 | 283.7304 | 9.6106 | 6.8998 | 2.7106 | 9.6083 | 1062 | 2354 | 846 | 149 | 699 | 55 | 0 | 326 | 0.00023648 | 2354 |  | 846 | 149 | 0 | 147 | 94 | 201.39 | 0.00085033 | 0.00026 | 1537 | 0.12379 | 0.0010955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.034913 | 54.2314 | 88.0277 | 71.79%
Bay Area | DI_Diablo | MORAGA 1101 | 1067 | MORAGA 1101circuit_breaker | 0.12826 | 126.2484 | 4.9275 | 3.8689 | 1.0585 | 4.814 | 505 | 1732 | 688 | 367 | 586 | 283 | 2 | 272 | 0.023023 | 1753 |  | 692 | 370 | 21 | 106 | 87 | 147.11 | 0.0010159 | 0.00022 | 1538 | 0.093981 | 0.0010928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 6. >50% | 0.020189 | 100.1396 | 140.4374 | 78.52%
Sierra | SI_Sierra | BELL 1109 | 1121 | BELL 1109circuit_breaker | 0.64013 | 365.9135 | 16.2379 | 0.23693 | 16.0009 | 0.29792 | 3482 | 52 | 15 | 15 | 14 | 14 | 0 | 427 | 0.98165 | 6271 |  | 1139 | 756 | 6219 | 1125 | 742 | 2100.96 | 0.0017494 | 0.00409 | 1539 | 0.21999 | 0.0010891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5. >40 - 50% | 5. >40 - 50% | 0.21678 | 70.3083 | 70.1446 | 1.459%
North Valley | NV_North Valley | FRENCH GULCH 1102 | 9020 | FRENCH GULCH 11022902 | 0.10725 | 156.9106 | 6.728 | 0 | 6.728 | 0 | 1785 | 0 | 0 | 0 | 0 | 0 | 0 | 211 | 1 | 3254 |  | 589 | 389 | 3254 | 589 | 389 | 1099.79 | 0.00068353 | 0.00084 | 1540 | 0.093136 | 0.001083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.093136 | 87.5442 | 87.5442 | 0%
North Coast | HU_Humboldt | LUCERNE 1103 | 3465 | LUCERNE 1103circuit_breaker | 0.062397 | 47.8881 | 3.6373 | 0 | 3.6373 | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 1 | 330 |  | 62 | 41 | 330 | 62 | 41 | 114.64 | 0.001303 | 0.00017 | 1541 | 0.019474 | 0.0010819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.019474 | 17.0456 | 17.0456 | 0%
Bay Area | PE_Peninsula | HALF MOON BAY 1103 | 4319 | HALF MOON BAY 1103circuit_breaker | 0.024639 | 38.4321 | 1.8106 | 1.5394 | 0.27121 | 1.8106 | 395 | 444 | 83 | 0 | 76 | 0 | 0 | 48 | 0 | 444 |  | 83 | 0 | 0 | 7 | 0 | 9.59 | 0.0006411 | 1e-05 | 1542 | 0.021546 | 0.0010773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0032274 | 25.8101 | 45.841 | 85.02%
Sierra | SI_Sierra | BRUNSWICK 1103 | 3089 | BRUNSWICK 11032200 | 0.23598 | 164.8368 | 5.7299 | 0.00018939 | 5.7297 | 2.0223 | 4461 | 861 | 861 | 747 | 0 | 0 | 0 | 359 | 0.64705 | 6111 |  | 1809 | 1372 | 5250 | 1809 | 1372 | 2950.83 | 0.0014316 | 0.00539 | 1544 | 0.0064186 | 0.0010698 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.0064184 | 315.7214 | 315.711 | 0.003305%
North Coast | HU_Humboldt | WILLOW CREEK 1101 | 6055 | WILLOW CREEK 110191926 | 0.097252 | 102.2938 | 6.3873 | 0 | 6.3873 | 0 | 3165 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 1 | 5760 |  | 1041 | 686 | 5760 | 1041 | 686 | 1944.57 | 0.00095071 | 0.00206 | 1545 | 0.081905 | 0.0010637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.081905 | 162.9794 | 162.9794 | 0%
North Coast | HU_Humboldt | LUCERNE 1106 | 7183 | LUCERNE 11062327 | 0.11156 | 33.695 | 1.5299 | 0 | 1.5299 | 0 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 1 | 259 |  | 49 | 33 | 259 | 49 | 33 | 90.44 | 0.003311 | 0.00034 | 1546 | 0.018082 | 0.0010637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.018082 | 32.0277 | 32.0277 | 0%
North Coast | SO_Sonoma | MONTE RIO 1111 | 7943 | MONTE RIO 1111240 | 0.14059 | 116.3123 | 4.7297 | 0.016856 | 4.7129 | 4.7297 | 3203 | 1219 | 984 | 312 | 61 | 7 | 0 | 349 | 0 | 1219 |  | 984 | 312 | 0 | 923 | 305 | 1264.51 | 0.0012087 | 0.00232 | 1547 | 0.035066 | 0.0010626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.034941 | 195.8463 | 208.0455 | 0.3564%
Central Coast | CC_Central Coast | BIG BASIN 1101 | 5185 | BIG BASIN 110110720 | 0.077973 | 94.6189 | 4.8472 | 0 | 4.8472 | 2.5125 | 2633 | 172 | 172 | 131 | 0 | 0 | 0 | 310 | 0.48166 | 2481 |  | 589 | 406 | 2309 | 589 | 406 | 1014.74 | 0.00082407 | 0.00101 | 1548 | 0.068186 | 0.001049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.068186 | 121.5145 | 121.5145 | 0%
Central Valley | ST_Stockton | IONE 1101 | 7263 | IONE 1101L3141 | 0.4357 | 351.2989 | 13.7727 | 2.0203 | 11.7525 | 2.9922 | 432 | 152 | 12 | 4 | 0 | 0 | 0 | 221 | 0.78274 | 776 |  | 126 | 80 | 624 | 126 | 80 | 228.78 | 0.0012402 | 0.00032 | 1549 | 0.11117 | 0.0010488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.094865 | 10.7212 | 9.1485 | 14.67%
North Valley | NV_North Valley | CRESCENT MILLS 2101 | 3198 | CRESCENT MILLS 2101circuit_breaker | 0.090673 | 73.0874 | 4.3843 | 0 | 4.3843 | 0 | 1064 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 1 | 1944 |  | 353 | 233 | 1944 | 353 | 233 | 658.57 | 0.0012406 | 0.00091 | 1550 | 0.028253 | 0.0010464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.028253 | 80.5149 | 80.5149 | 0%
Central Valley | YO_Yosemite | OAKHURST 1102 | 7482 | OAKHURST 1102circuit_breaker | 1.2967 | 99.1713 | 4.2977 | 0.62045 | 3.6773 | 0.43996 | 795 | 44 | 31 | 5 | 26 | 5 | 0 | 143 | 0.89763 | 1351 |  | 268 | 162 | 1307 | 242 | 157 | 449.17 | 0.013075 | 0.00658 | 1551 | 0.039746 | 0.001046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.034008 | 65.8096 | 62.3585 | 14.44%
Sierra | SI_Sierra | PLACERVILLE 2106 | 4223 | PLACERVILLE 210623190 | 0.062794 | 45.6969 | 2.05 | 0 | 2.05 | 0 | 532 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 1 | 978 |  | 178 | 118 | 978 | 178 | 118 | 331.88 | 0.0013741 | 0.00051 | 1552 | 0.066453 | 0.0010383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.066453 | 86.8293 | 86.8293 | 0%
Central Valley | ST_Stockton | ELECTRA 1102 | 4351 | ELECTRA 11024756 | 0.26695 | 234.4949 | 9.3148 | 0 | 9.3148 | 0 | 558 | 0 | 0 | 0 | 0 | 0 | 0 | 262 | 1 | 1026 |  | 187 | 124 | 1026 | 187 | 124 | 348.53 | 0.0011384 | 0.00044 | 1553 | 0.074716 | 0.0010377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.074716 | 20.0756 | 20.0756 | 0%
Central Coast | CC_Central Coast | BIG BASIN 1101 | 2978 | BIG BASIN 110110296 | 0.30085 | 373.6592 | 17.3739 | 0 | 17.3739 | 11.9928 | 12227 | 1697 | 1692 | 828 | 1 | 0 | 0 | 1335 | 0.30972 | 8578 |  | 2934 | 1646 | 6881 | 2933 | 1646 | 4637.5 | 0.00080515 | 0.00491 | 1554 | 0.22408 | 0.0010374 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.22408 | 168.8168 | 168.8744 | 0%
Central Coast | CC_Central Coast | GABILAN 1101 | 648 | GABILAN 1101579969 | 0.09744 | 101.5716 | 5.7254 | 0 | 5.7254 | 0 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 1 | 405 |  | 75 | 50 | 405 | 75 | 50 | 139.2 | 0.00095932 | 0.00015 | 1555 | 0.02898 | 0.001035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.02898 | 13.0996 | 13.0996 | 0%
North Valley | NV_North Valley | ORO FINO 1102 | 2234 | ORO FINO 11022560 | 0.4814 | 405.5848 | 16.1313 | 0.12879 | 16.0025 | 10.5814 | 12184 | 3817 | 2539 | 1758 | 1102 | 628 | 0 | 811 | 0.34404 | 11433 |  | 3913 | 2664 | 7616 | 2811 | 2036 | 4536.51 | 0.0011869 | 0.00694 | 1556 | 0.28627 | 0.0010335 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.28399 | 175.6605 | 242.5726 | 0.7984%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1104 | 4390 | SAN LUIS OBISPO 1104V14 | 0.42035 | 229.885 | 8.4174 | 0 | 8.4174 | 0 | 302 | 0 | 0 | 0 | 0 | 0 | 0 | 208 | 1 | 561 |  | 103 | 69 | 561 | 103 | 69 | 191.6 | 0.0018285 | 0.00039 | 1557 | 0.04746 | 0.0010317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.04746 | 12.2365 | 12.2365 | 0%
Central Coast | LP_Los Padres | OCEANO 1106 | 5896 | OCEANO 1106V28 | 0.052053 | 22.4575 | 0.48333 | 0 | 0.48333 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1 | 59 |  | 13 | 9 | 59 | 13 | 9 | 23.12 | 0.0023178 | 6e-05 | 1559 | 0.018506 | 0.0010281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.018506 | 26.8966 | 26.8966 | 0%
North Coast | HU_Humboldt | CARLOTTA 1121 | 1525 | CARLOTTA 11214914 | 0.17191 | 239.5416 | 11.8519 | 0 | 11.8519 | 0 | 4799 | 0 | 0 | 0 | 0 | 0 | 0 | 244 | 1 | 8727 |  | 1576 | 1039 | 8727 | 1576 | 1039 | 2944.55 | 0.00071767 | 0.00235 | 1560 | 0.15429 | 0.0010151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.15429 | 132.9745 | 132.9745 | 0%
Central Valley | FR_Fresno | AUBERRY 1101 | 2713 | AUBERRY 1101R2845 | 0.66247 | 440.9713 | 17.4841 | 0.97992 | 16.5042 | 1.733 | 3422 | 309 | 150 | 107 | 0 | 0 | 0 | 613 | 0.90088 | 5918 |  | 1163 | 775 | 5609 | 1163 | 775 | 2098.12 | 0.0015023 | 0.00363 | 1561 | 0.23003 | 0.0010134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.21714 | 70.4671 | 66.5176 | 5.605%
Central Valley | YO_Yosemite | MIWUK 1701 | 7367 | MIWUK 17018050 | 0.22816 | 256.6429 | 9.9392 | 0.2911 | 9.6481 | 8.2814 | 4579 | 1119 | 829 | 350 | 633 | 224 | 0 | 610 | 0.16679 | 2508 |  | 1080 | 515 | 1389 | 447 | 291 | 737.4 | 0.00088902 | 0.00083 | 1562 | 0.18132 | 0.0010129 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.17601 | 46.3303 | 108.6606 | 2.929%
Central Valley | ST_Stockton | PINE GROVE 1102 | 2375 | PINE GROVE 110245292 | 0.58566 | 278.9115 | 11.6278 | 0 | 11.6278 | 0.13523 | 5872 | 5 | 5 | 1 | 0 | 0 | 0 | 582 | 0.98837 | 10556 |  | 1910 | 1257 | 10551 | 1910 | 1257 | 3566.29 | 0.0020998 | 0.00834 | 1563 | 0.0099933 | 0.00099933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.0099933 | 164.2609 | 164.2609 | 0%
Central Valley | ST_Stockton | CLAY 1101 | 1719 | CLAY 110113450 | 0.17686 | 16.4323 | 0.98447 | 0.64792 | 0.33655 | 0.98447 | 54 | 80 | 20 | 4 | 0 | 0 | 0 | 16 | 0 | 80 |  | 20 | 4 | 0 | 20 | 4 | 27.4 | 0.010763 | 0.00045 | 1564 | 0.0069792 | 0.00099704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0023859 | 59.426 | 20.3155 | 65.81%
North Coast | SO_Sonoma | MONTE RIO 1111 | 43 | MONTE RIO 11111703 | 8.9e-05 | 25.4028 | 0.87292 | 0 | 0.87292 | 0.87216 | 589 | 405 | 405 | 309 | 54 | 2 | 0 | 46 | 0.00086787 | 406 |  | 405 | 309 | 1 | 351 | 307 | 480.96 | 3.5036e-06 | 0 | 1565 | 0.0039854 | 0.00099634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0039854 | 402.1002 | 463.9618 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2106 | 6447 | CAMP EVERS 210637210 | 0.17087 | 162.1467 | 7.7413 | 0 | 7.7413 | 0 | 4276 | 0 | 0 | 0 | 0 | 0 | 0 | 406 | 1 | 7777 |  | 1405 | 926 | 7777 | 1405 | 926 | 2624.78 | 0.0010538 | 0.00308 | 1566 | 0.10952 | 0.00099565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.10952 | 181.4943 | 181.4943 | 0%
Central Coast | CC_Central Coast | SPENCE 1104 | 4353 | SPENCE 1122circuit_breaker | 0.33508 | 233.3928 | 66.6583 | 0 | 66.6583 | 0 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 1906 | 1 | 484 |  | 89 | 60 | 484 | 89 | 60 | 165.49 | 0.0014357 | 0.00027 | 1567 | 0.002984 | 0.00099468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.002984 | 1.3352 | 1.3352 | 0%
Central Valley | YO_Yosemite | MIWUK 1702 | 5112 | MIWUK 17026018 | 0.49149 | 451.1886 | 21.221 | 0.9589 | 20.2621 | 21.2063 | 10073 | 1505 | 520 | 349 | 138 | 44 | 0 | 1185 | 0.00069614 | 1518 |  | 522 | 351 | 13 | 384 | 307 | 527.25 | 0.0010893 | 0.00087 | 1568 | 0.25816 | 0.00099292 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.24649 | 18.9516 | 24.5982 | 4.519%
North Valley | NV_North Valley | BIG MEADOWS 2101 | 2954 | BIG MEADOWS 21012586 | 0.16233 | 141.7715 | 8.4792 | 0 | 8.4792 | 0 | 3557 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 1 | 6472 |  | 1169 | 771 | 6472 | 1169 | 771 | 2184.01 | 0.001145 | 0.00278 | 1569 | 0.099126 | 0.00099126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.099126 | 137.8673 | 137.8673 | 0%
Central Valley | KE_Kern | TEJON 1102 | 423 | TEJON 11023751 | 0.42564 | 490.4324 | 21.036 | 20.9472 | 0.088826 | 21.036 | 437 | 953 | 70 | 37 | 70 | 37 | 0 | 744 | 0 | 953 |  | 70 | 37 | 0 | 0 | 0 | 0 | 0.00086789 | 0 | 1570 | 0.17031 | 0.00099015 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00071913 | 0 | 3.3276 | 99.58%
Central Valley | YO_Yosemite | BEAR VALLEY 2101 | 2640 | BEAR VALLEY 210110000 | 0.73634 | 800.4823 | 29.5894 | 24.1597 | 5.4297 | 28.6852 | 501 | 1894 | 446 | 388 | 401 | 347 | 0 | 809 | 0.030557 | 1922 |  | 451 | 391 | 28 | 50 | 44 | 71.02 | 0.00091987 | 0.0001 | 1571 | 0.18632 | 0.00098584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.034191 | 9.2086 | 15.2419 | 81.65%
Sierra | SI_Sierra | EL DORADO PH 2101 | 1001 | EL DORADO PH 210119752 | 1.3406 | 964.7662 | 38.8045 | 4.8987 | 33.9059 | 15.0375 | 19955 | 13573 | 7447 | 6954 | 4856 | 4483 | 1 | 2486 | 0.61248 | 35775 |  | 11452 | 9593 | 22202 | 6596 | 5110 | 11034.7 | 0.0013895 | 0.01906 | 1572 | 0.53689 | 0.00098331 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 3. >20 - 30% | 0.46911 | 194.5386 | 295.1201 | 12.62%
Central Coast | CC_Central Coast | BIG BASIN 1102 | 3526 | BIG BASIN 110212992 | 0.31398 | 294.4598 | 12.6754 | 0 | 12.6754 | 8.6407 | 8998 | 1409 | 1405 | 614 | 0 | 0 | 0 | 820 | 0.31831 | 6614 |  | 2344 | 1233 | 5205 | 2344 | 1233 | 3679.73 | 0.0010663 | 0.0052 | 1573 | 0.23393 | 0.00098292 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.23393 | 184.9254 | 184.9254 | 0%
North Coast | SO_Sonoma | FORT ROSS 1121 | 1201 | FORT ROSS 11212987 | 0.29059 | 71.3516 | 2.4335 | 0 | 2.4335 | 0.087689 | 746 | 26 | 26 | 20 | 0 | 0 | 0 | 38 | 0.96397 | 1344 |  | 266 | 179 | 1318 | 266 | 179 | 483.04 | 0.0040727 | 0.00225 | 1574 | 0.014718 | 0.00098117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.014718 | 109.3066 | 109.3066 | 0%
Bay Area | DI_Diablo | TASSAJARA 2112 | 1347 | TASSAJARA 2112circuit_breaker | 0.002911 | 2.71 | 0.18087 | 0 | 0.18087 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 76 |  | 16 | 11 | 76 | 16 | 11 | 28.76 | 0.0010742 | 4e-05 | 1575 | 0.002912 | 0.00097066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.002912 | 88.4607 | 88.4607 | 0%
Bay Area | NB_North Bay | LAS GALLINAS A 1106 | 1104 | LAS GALLINAS A 1106circuit_breaker | 0.57979 | 110.9917 | 2.9295 | 0 | 2.9295 | 0 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 1 | 430 |  | 80 | 53 | 430 | 80 | 53 | 148.3 | 0.0052237 | 0.00087 | 1576 | 0.022152 | 0.00096311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.022152 | 27.308 | 27.308 | 0%
Sierra | SI_Sierra | BRUNSWICK 1105 | 5215 | BRUNSWICK 11052100 | 0.031481 | 35.9461 | 1.7437 | 0 | 1.7437 | 0.064962 | 1257 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 0.96275 | 2209 |  | 400 | 265 | 2209 | 400 | 265 | 746.81 | 0.00087578 | 0.00073 | 1577 | 0.03847 | 0.00096175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.03847 | 229.3907 | 229.3907 | 0%
Central Valley | ST_Stockton | FROGTOWN 1702 | 371 | FROGTOWN 1702L5407 | 0.4483 | 456.1353 | 17.1585 | 0 | 17.1585 | 0 | 370 | 0 | 0 | 0 | 0 | 0 | 0 | 295 | 1 | 684 |  | 125 | 83 | 684 | 125 | 83 | 232.81 | 0.00098282 | 0.00026 | 1578 | 0.17089 | 0.0009547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.17089 | 7.285 | 7.285 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2104 | 4005 | CAMP EVERS 210410442 | 0.14362 | 160.5307 | 8.6123 | 0 | 8.6123 | 0 | 3390 | 0 | 0 | 0 | 0 | 0 | 0 | 248 | 1 | 6168 |  | 1114 | 735 | 6168 | 1114 | 735 | 2081.3 | 0.00089466 | 0.00207 | 1579 | 0.091626 | 0.00095444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.091626 | 129.3497 | 129.3497 | 0%
Bay Area | PE_Peninsula | SERRAMONTE 1104 | 3384 | SERRAMONTE 110412705 | 0.000522 | 11.8704 | 0.47462 | 0 | 0.47462 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 56 |  | 12 | 9 | 56 | 12 | 9 | 21.48 | 4.3975e-05 | 0 | 1580 | 0.00095184 | 0.00095184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00095184 | 25.2833 | 25.2833 | 0%
Sierra | SI_Sierra | SHADY GLEN 1101 | 5304 | SHADY GLEN 11012768 | 0.15021 | 178.9227 | 8.2044 | 0 | 8.2044 | 0 | 3164 | 0 | 0 | 0 | 0 | 0 | 0 | 213 | 1 | 5758 |  | 1040 | 686 | 5758 | 1040 | 686 | 1943.02 | 0.0008395 | 0.00182 | 1581 | 0.10235 | 0.000939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.10235 | 126.7619 | 126.7619 | 0%
North Coast | SO_Sonoma | FORT ROSS 1121 | 2551 | FORT ROSS 1121124 | 2.3703 | 427.1567 | 18.1964 | 0 | 18.1964 | 0 | 5527 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 1 | 10049 |  | 1814 | 1196 | 10049 | 1814 | 1196 | 3389.59 | 0.005549 | 0.02093 | 1582 | 0.0563 | 0.00093833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 3. >20 - 30% | 0.0563 | 99.69 | 99.69 | 0%
Sierra | SI_Sierra | DIAMOND SPRINGS 1106 | 714 | DIAMOND SPRINGS 110650324 | 0.29616 | 299.2899 | 13.6301 | 0 | 13.6301 | 0 | 4582 | 0 | 0 | 0 | 0 | 0 | 0 | 545 | 1 | 8333 |  | 1505 | 992 | 8333 | 1505 | 992 | 2811.82 | 0.00098954 | 0.0031 | 1583 | 0.23793 | 0.00093306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.23793 | 110.4173 | 110.4173 | 0%
Central Coast | CC_Central Coast | BIG BASIN 1101 | 3057 | BIG BASIN 1101circuit_breaker | 0.12155 | 146.3741 | 4.9926 | 0 | 4.9926 | 2.6152 | 2357 | 201 | 201 | 107 | 5 | 5 | 0 | 254 | 0.4762 | 2245 |  | 571 | 351 | 2044 | 566 | 346 | 959.38 | 0.0008304 | 0.00098 | 1584 | 0.078261 | 0.00093168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.078261 | 113.3675 | 114.369 | 0%
North Coast | SO_Sonoma | MIRABEL 1102 | 7397 | MIRABEL 110257840 | 0.020387 | 41.3781 | 1.8911 | 0.063636 | 1.8275 | 1.8911 | 1026 | 297 | 297 | 159 | 69 | 1 | 0 | 131 | 0 | 297 |  | 297 | 159 | 0 | 228 | 158 | 312.36 | 0.0004927 | 0.00023 | 1585 | 0.032498 | 0.00092851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.031404 | 124.7632 | 157.0516 | 3.365%
Central Coast | CC_Central Coast | JOLON 1102 | 5738 | JOLON 1102circuit_breaker | 0.89411 | 521.1314 | 23.9407 | 0 | 23.9407 | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 334 | 1 | 294 |  | 55 | 37 | 294 | 55 | 37 | 101.81 | 0.0017157 | 0.0002 | 1586 | 0.0046139 | 0.00092277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0046139 | 2.2973 | 2.2973 | 0%
Sierra | SI_Sierra | EL DORADO PH 2102 | 4045 | EL DORADO PH 210219542 | 0.20043 | 171.5617 | 7.9705 | 0 | 7.9705 | 6.1756 | 4572 | 137 | 131 | 121 | 1 | 1 | 0 | 622 | 0.22519 | 2009 |  | 469 | 344 | 1872 | 468 | 343 | 809.64 | 0.0011682 | 0.00114 | 1587 | 0.13184 | 0.00092196 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.13184 | 58.7169 | 58.8423 | 0%
Central Valley | FR_Fresno | AUBERRY 1101 | 3689 | AUBERRY 1101R322 | 0.20227 | 207.3656 | 7.6494 | 0 | 7.6494 | 0 | 228 | 0 | 0 | 0 | 0 | 0 | 0 | 172 | 1 | 426 |  | 79 | 53 | 426 | 79 | 53 | 146.57 | 0.00097544 | 0.00016 | 1588 | 0.028431 | 0.00091714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.028431 | 10.3276 | 10.3276 | 0%
North Coast | HU_Humboldt | HOOPA 1101 | 1084 | HOOPA 1101circuit_breaker | 0.30625 | 326.5477 | 16.1951 | 0 | 16.1951 | 0 | 7909 | 0 | 0 | 0 | 0 | 0 | 0 | 339 | 1 | 14375 |  | 2594 | 1710 | 14375 | 2594 | 1710 | 4847.53 | 0.00093784 | 0.00506 | 1589 | 0.22054 | 0.00091133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.22054 | 160.1721 | 160.1721 | 0%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1104 | 4688 | SAN LUIS OBISPO 1104V46 | 0.33048 | 400.286 | 18.5585 | 0 | 18.5585 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 302 | 1 | 1510 |  | 274 | 182 | 1510 | 274 | 182 | 511.28 | 0.0008256 | 0.00047 | 1590 | 0.11803 | 0.00090795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.11803 | 14.7641 | 14.7641 | 0%
North Coast | HU_Humboldt | WILLOW CREEK 1101 | 1531 | WILLOW CREEK 11015002 | 0.17951 | 264.9455 | 12.4549 | 0.00075758 | 12.454 | 0.17992 | 4321 | 39 | 39 | 1 | 21 | 0 | 0 | 312 | 0.98555 | 7785 |  | 1438 | 923 | 7746 | 1417 | 923 | 2638.43 | 0.00067753 | 0.002 | 1591 | 0.1761 | 0.00090774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.17609 | 113.7789 | 115.4563 | 0.006083%
North Valley | NV_North Valley | BIG MEADOWS 2101 | 9481 | BIG MEADOWS 21012248 | 0.18261 | 159.4492 | 8.0333 | 0 | 8.0333 | 0 | 5116 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 1 | 9303 |  | 1680 | 1107 | 9303 | 1680 | 1107 | 3138.87 | 0.0011453 | 0.004 | 1592 | 0.084149 | 0.0008952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.084149 | 209.1286 | 209.1286 | 0%
North Valley | NV_North Valley | WILDWOOD 1101 | 8645 | WILDWOOD 110185112 | 0.1351 | 149.8233 | 7.1949 | 0 | 7.1949 | 0 | 3103 | 0 | 0 | 0 | 0 | 0 | 0 | 174 | 1 | 5647 |  | 1020 | 673 | 5647 | 1020 | 673 | 1905.63 | 0.00090174 | 0.00191 | 1593 | 0.082307 | 0.00089464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.082307 | 141.7674 | 141.7674 | 0%
Sierra | SI_Sierra | PLACERVILLE 1112 | 2795 | PLACERVILLE 111219742 | 0.093713 | 173.5554 | 7.2532 | 0 | 7.2532 | 0 | 1392 | 0 | 0 | 0 | 0 | 0 | 0 | 213 | 1 | 2540 |  | 460 | 304 | 2540 | 460 | 304 | 858.8 | 0.00053996 | 0.00052 | 1594 | 0.089425 | 0.00089425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.089425 | 63.4201 | 63.4201 | 0%
Central Valley | ST_Stockton | CLAY 1103 | 8291 | CLAY 11037142 | 0.05709 | 61.7121 | 5.1515 | 0 | 5.1515 | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 1 | 521 |  | 96 | 64 | 521 | 96 | 64 | 178.41 | 0.0009251 | 0.00018 | 1595 | 0.026676 | 0.00088921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.026676 | 18.6353 | 18.6353 | 0%
North Coast | HU_Humboldt | LUCERNE 1106 | 1670 | LUCERNE 110676850 | 0.002197 | 37.183 | 2.8373 | 0 | 2.8373 | 0 | 255 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 1 | 475 |  | 88 | 59 | 475 | 88 | 59 | 163.31 | 5.9086e-05 | 1e-05 | 1596 | 0.024884 | 0.00088871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.024884 | 31.0153 | 31.0153 | 0%
Central Valley | ST_Stockton | FROGTOWN 1701 | 2092 | FROGTOWN 17011623 | 0.37704 | 401.8137 | 15.9023 | 0 | 15.9023 | 0 | 2258 | 0 | 0 | 0 | 0 | 0 | 0 | 335 | 1 | 4113 |  | 744 | 491 | 4113 | 744 | 491 | 1389.45 | 0.00093835 | 0.00145 | 1597 | 0.199 | 0.0008884 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.199 | 46.7858 | 46.7858 | 0%
Central Coast | LP_Los Padres | SANTA MARIA 1108 | 7075 | SANTA MARIA 1108M18 | 0.32938 | 295.864 | 14.308 | 0 | 14.308 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 1 | 183 |  | 35 | 24 | 183 | 35 | 24 | 64.42 | 0.0011133 | 8e-05 | 1598 | 0.037275 | 0.00088751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.037275 | 2.4462 | 2.4462 | 0%
Central Coast | CC_Central Coast | BEN LOMOND 1101 | 1456 | BEN LOMOND 1101BL 1101 | 0.17711 | 199.5386 | 9.0936 | 0 | 9.0936 | 0 | 6138 | 0 | 0 | 0 | 0 | 0 | 0 | 296 | 1 | 11159 |  | 2014 | 1328 | 11159 | 2014 | 1328 | 3763.49 | 0.00088761 | 0.00372 | 1599 | 0.12495 | 0.00088617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.12495 | 221.4754 | 221.4754 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2106 | 7660 | CAMP EVERS 210612840 | 0.047273 | 90.9861 | 3.3574 | 0 | 3.3574 | 0 | 1599 | 0 | 0 | 0 | 0 | 0 | 0 | 213 | 1 | 2916 |  | 528 | 349 | 2916 | 528 | 349 | 985.8 | 0.00051956 | 0.00057 | 1600 | 0.060901 | 0.00088263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.060901 | 157.2652 | 157.2652 | 0%
Sierra | SI_Sierra | BRUNSWICK 1106 | 3103 | BRUNSWICK 11062416 | 0.74755 | 646.7265 | 24.6966 | 1.022 | 23.6748 | 1.6269 | 11607 | 74 | 14 | 7 | 0 | 0 | 0 | 1399 | 0.93412 | 19775 |  | 3569 | 2350 | 19701 | 3569 | 2350 | 6662.62 | 0.0011559 | 0.00858 | 1601 | 0.39379 | 0.00088095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.37749 | 150.7509 | 144.5139 | 4.138%
North Coast | SO_Sonoma | MONTE RIO 1111 | 296 | MONTE RIO 111164758 | 0.34211 | 253.0312 | 9.9057 | 0.062311 | 9.8434 | 9.9019 | 5128 | 3729 | 3729 | 3260 | 45 | 2 | 0 | 586 | 0.00038239 | 3733 |  | 3730 | 3260 | 4 | 3685 | 3258 | 5048.81 | 0.001352 | 0.01036 | 1602 | 0.04552 | 0.00087538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 4. >30 - 40% | 0.045233 | 374.3636 | 376.5516 | 0.629%
Bay Area | DI_Diablo | CLAYTON 2212 | 5156 | CLAYTON 2212circuit_breaker | 0.14149 | 57.2806 | 2.1394 | 1.9566 | 0.18258 | 2.1394 | 92 | 261 | 50 | 7 | 39 | 0 | 0 | 73 | 0 | 261 |  | 50 | 7 | 0 | 11 | 7 | 15.07 | 0.0024702 | 6e-05 | 1603 | 0.011314 | 0.00087029 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00096552 | 60.249 | 23.3711 | 91.46%
North Valley | NV_North Valley | ORO FINO 1101 | 1156 | ORO FINO 1101circuit_breaker | 0.55061 | 492.0187 | 23.3011 | 0.51742 | 22.7837 | 12.9078 | 15162 | 5580 | 3734 | 3162 | 154 | 142 | 0 | 1453 | 0.44605 | 17867 |  | 5951 | 4623 | 12287 | 5797 | 4481 | 9047.72 | 0.0011191 | 0.01349 | 1604 | 0.32811 | 0.000868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 4. >30 - 40% | 0.32082 | 254.4362 | 255.3953 | 2.221%
Sierra | SI_Sierra | DRUM 1101 | 6048 | DRUM 11011602 | 0.36454 | 426.8984 | 16.1695 | 0 | 16.1695 | 0 | 7430 | 0 | 0 | 0 | 0 | 0 | 0 | 447 | 1 | 13505 |  | 2438 | 1607 | 13505 | 2438 | 1607 | 4555.51 | 0.00085393 | 0.00433 | 1605 | 0.17932 | 0.0008663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.17932 | 150.7776 | 150.7776 | 0%
Central Valley | YO_Yosemite | MERCED FALLS 1102 | 7933 | MERCED FALLS 110222772 | 0.19001 | 63.5823 | 2.4193 | 2.4193 | 0 | 2.4193 | 9 | 256 | 33 | 26 | 33 | 26 | 0 | 82 | 0 | 256 |  | 33 | 26 | 0 | 0 | 0 | 0 | 0.0029884 | 0 | 1606 | 0.017154 | 0.00085771 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 13.6402 | 100%
Central Coast | LP_Los Padres | SISQUOC 1103 | 6297 | SISQUOC 1103M14 | 0.5569 | 557.6022 | 20.6722 | 0 | 20.6722 | 0 | 859 | 0 | 0 | 0 | 0 | 0 | 0 | 335 | 1 | 1572 |  | 286 | 189 | 1572 | 286 | 189 | 533.3 | 0.00099874 | 0.00059 | 1607 | 0.17495 | 0.00085758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.17495 | 13.835 | 13.835 | 0%
Bay Area | NB_North Bay | BOLINAS 1101 | 3317 | BOLINAS 1101504 | 0.13385 | 156.1239 | 6.6053 | 0.094508 | 6.5108 | 0.094508 | 765 | 39 | 39 | 35 | 5 | 1 | 3 | 295 | 0.98569 | 1420 |  | 290 | 201 | 1381 | 285 | 200 | 514.74 | 0.00085734 | 0.00051 | 1608 | 0.078783 | 0.00085633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.077655 | 43.7735 | 43.9041 | 1.431%
Bay Area | PE_Peninsula | WOODSIDE 1101 | 4944 | WOODSIDE 11018912 | 0.048026 | 61.7017 | 2.7424 | 2.0464 | 0.69602 | 2.7388 | 1049 | 2743 | 940 | 402 | 793 | 371 | 1 | 203 | 0.0013122 | 2746 |  | 940 | 402 | 3 | 147 | 31 | 201.66 | 0.00077836 | 0.00024 | 1609 | 0.060752 | 0.00085566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.015419 | 211.2 | 342.7624 | 74.62%
Central Valley | YO_Yosemite | CURTIS 1704 | 6928 | CURTIS 17046060 | 0.01443 | 53.9541 | 1.8795 | 1.3006 | 0.57898 | 1.8795 | 241 | 567 | 167 | 105 | 165 | 105 | 0 | 75 | 0 | 567 |  | 167 | 105 | 0 | 2 | 0 | 2.74 | 0.00026745 | 0 | 1610 | 0.051334 | 0.00085557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.015813 | 3.4544 | 88.8513 | 69.2%
Sierra | SI_Sierra | BRUNSWICK 1105 | 340 | BRUNSWICK 11052204 | 0.10093 | 173.7943 | 6.8797 | 0.48996 | 6.3898 | 4.9085 | 5076 | 1540 | 1539 | 1180 | 583 | 403 | 1 | 485 | 0.28652 | 4185 |  | 2017 | 1495 | 2645 | 1434 | 1092 | 2202.63 | 0.00058072 | 0.00173 | 1611 | 0.023045 | 0.00085352 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.021404 | 224.4211 | 293.1799 | 7.122%
Central Valley | ST_Stockton | FROGTOWN 1701 | 970 | FROGTOWN 1701circuit_breaker | 0.19761 | 214.1136 | 9.3941 | 0 | 9.3941 | 0 | 787 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 1 | 1441 |  | 262 | 173 | 1441 | 262 | 173 | 488.63 | 0.00092292 | 0.0005 | 1612 | 0.079219 | 0.00085182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.079219 | 27.8898 | 27.8898 | 0%
Central Coast | CC_Central Coast | BIG BASIN 1101 | 286 | BIG BASIN 110169550 | 0.36704 | 393.7233 | 16.7203 | 0.077462 | 16.643 | 11.6947 | 9315 | 1585 | 1482 | 512 | 84 | 46 | 0 | 969 | 0.30057 | 6673 |  | 2400 | 1117 | 5088 | 2316 | 1071 | 3630.84 | 0.00093224 | 0.00449 | 1613 | 0.26467 | 0.00084831 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.26345 | 139.1577 | 143.5384 | 0.4633%
North Coast | SO_Sonoma | RINCON 1101 | 639 | RINCON 1101580 | 0.010146 | 7.2432 | 0.34451 | 0 | 0.34451 | 0 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 237 |  | 45 | 30 | 237 | 45 | 30 | 82.98 | 0.0014008 | 0.00013 | 1614 | 0.005088 | 0.000848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.005088 | 130.6212 | 130.6212 | 0%
Central Valley | ST_Stockton | ELECTRA 1102 | 4775 | WEST POINT 110277204 | 0.095226 | 140.3535 | 6.2032 | 0.40341 | 5.7998 | 3.2328 | 1135 | 525 | 481 | 224 | 400 | 151 | 0 | 255 | 0.47886 | 1518 |  | 661 | 343 | 993 | 261 | 192 | 446.94 | 0.00067847 | 0.00037 | 1615 | 0.083247 | 0.00084088 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.077833 | 45.0015 | 106.5576 | 6.503%
North Coast | HU_Humboldt | COVELO 1101 | 6941 | COVELO 1101536 | 1.1473 | 179.9915 | 10.0826 | 0 | 10.0826 | 0 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 1 | 415 |  | 77 | 52 | 415 | 77 | 52 | 142.84 | 0.0063741 | 0.00102 | 1616 | 0.0050437 | 0.00084062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0050437 | 7.6369 | 7.6369 | 0%
Central Valley | FR_Fresno | SAND CREEK 1103 | 9097 | SAND CREEK 110397354 | 0.20466 | 165.6971 | 8.5934 | 0 | 8.5934 | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 1 | 512 |  | 94 | 63 | 512 | 94 | 63 | 174.86 | 0.0012351 | 0.00024 | 1617 | 0.053608 | 0.00083763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.053608 | 10.9387 | 10.9387 | 0%
Central Valley | YO_Yosemite | BEAR VALLEY 2105 | 7802 | BEAR VALLEY 210513430 | 0.30217 | 333.1056 | 11.9646 | 0 | 11.9646 | 0 | 3672 | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 1 | 6681 |  | 1207 | 796 | 6681 | 1207 | 796 | 2254.88 | 0.00090714 | 0.00228 | 1618 | 0.11121 | 0.00083616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.11121 | 100.8811 | 100.8811 | 0%
Central Valley | FR_Fresno | AUBERRY 1101 | 3842 | AUBERRY 1101R319 | 0.36885 | 484.2653 | 21.3875 | 0.65455 | 20.7328 | 5.9636 | 5325 | 343 | 330 | 184 | 37 | 28 | 0 | 919 | 0.72116 | 7326 |  | 1591 | 1015 | 6983 | 1554 | 987 | 2757.45 | 0.00076167 | 0.00246 | 1620 | 0.20759 | 0.00083369 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.20123 | 74.9538 | 74.3892 | 3.06%
Sierra | SI_Sierra | BRUNSWICK 1110 | 484 | BRUNSWICK 11102664 | 0.16997 | 151.3171 | 6.1619 | 0.0066288 | 6.1553 | 4.9873 | 1934 | 913 | 757 | 414 | 0 | 0 | 0 | 239 | 0.19063 | 1585 |  | 879 | 494 | 672 | 879 | 494 | 1264.71 | 0.0011233 | 0.00205 | 1621 | 0.10232 | 0.00083188 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.10221 | 142.8037 | 142.6501 | 0.1076%
Central Valley | ST_Stockton | PINE GROVE 1101 | 2744 | PINE GROVE 11013170 | 0.69341 | 888.3318 | 39.5837 | 0 | 39.5837 | 0 | 8893 | 0 | 0 | 0 | 0 | 0 | 0 | 846 | 1 | 16162 |  | 2917 | 1922 | 16162 | 2917 | 1922 | 5450.87 | 0.00078058 | 0.00473 | 1622 | 0.48865 | 0.00082963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.48865 | 73.6919 | 73.6919 | 0%
North Coast | SO_Sonoma | MIRABEL 1102 | 771 | MIRABEL 1102circuit_breaker | 0.080452 | 109.2794 | 5.4381 | 0.8464 | 4.5915 | 5.4379 | 1708 | 505 | 501 | 195 | 142 | 1 | 1 | 421 | 3.4827e-05 | 505 |  | 501 | 195 | 0 | 359 | 194 | 491.83 | 0.0007362 | 0.00055 | 1623 | 0.060224 | 0.00082499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.050849 | 78.1883 | 92.1283 | 15.56%
Central Coast | CC_Central Coast | SEACLIFF 0401 | 4706 | SEACLIFF 040112946 | 0.036142 | 69.0682 | 2.1699 | 0 | 2.1699 | 0 | 847 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1 | 1550 |  | 282 | 186 | 1550 | 282 | 186 | 525.84 | 0.00052328 | 0.00031 | 1624 | 0.03127 | 0.0008229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.03127 | 129.9607 | 129.9607 | 0%
North Valley | NV_North Valley | ORO FINO 1102 | 8495 | ORO FINO 1102circuit_breaker | 0.051217 | 72.4882 | 3.1527 | 0 | 3.1527 | 1.7807 | 1774 | 219 | 215 | 164 | 6 | 4 | 0 | 218 | 0.43518 | 1626 |  | 470 | 332 | 1407 | 464 | 328 | 762.31 | 0.00070656 | 0.00068 | 1625 | 0.022121 | 0.00081928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.022121 | 147.1777 | 149.0809 | 0%
North Valley | NV_North Valley | VOLTA 1101 | 2692 | VOLTA 110153118 | 3.0368 | 208.016 | 8.9386 | 0 | 8.9386 | 0 | 333 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | 1 | 617 |  | 113 | 76 | 617 | 113 | 76 | 210.34 | 0.014599 | 0.00343 | 1626 | 0.0049102 | 0.00081837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0049102 | 12.6417 | 12.6417 | 0%
Central Valley | ST_Stockton | MARTELL 1101 | 3413 | MARTELL 110198374 | 0.015674 | 13.5348 | 0.65076 | 0.16458 | 0.48617 | 0.42367 | 25 | 24 | 5 | 1 | 0 | 0 | 0 | 17 | 0.34895 | 44 |  | 9 | 4 | 20 | 9 | 4 | 14.13 | 0.0011581 | 2e-05 | 1627 | 0.0073527 | 0.00081696 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0054931 | 18.5119 | 13.83 | 25.29%
Central Coast | SJ_San Jose | SWIFT 2110 | 8519 | SWIFT 2110XR254 | 0.28978 | 532.9752 | 24.235 | 0 | 24.235 | 0 | 1082 | 0 | 0 | 0 | 0 | 0 | 0 | 415 | 1 | 1977 |  | 359 | 237 | 1977 | 359 | 237 | 669.76 | 0.0005437 | 0.00041 | 1629 | 0.14162 | 0.00080925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.14162 | 14.8133 | 14.8133 | 0%
Central Valley | ST_Stockton | SALT SPRINGS 2101 | 6601 | SALT SPRINGS 210110416 | 0.013889 | 18.3343 | 0.39394 | 0 | 0.39394 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 179 |  | 34 | 24 | 179 | 34 | 24 | 62.69 | 0.00075754 | 5e-05 | 1630 | 0.0080821 | 0.00080821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0080821 | 86.3077 | 86.3077 | 0%
Central Valley | ST_Stockton | PINE GROVE 1102 | 3329 | PINE GROVE 110213438 | 0.39878 | 432.4975 | 16.7246 | 0.46534 | 16.2591 | 5.5888 | 9512 | 1076 | 1074 | 964 | 33 | 21 | 0 | 886 | 0.66583 | 12585 |  | 3151 | 2333 | 11509 | 3118 | 2312 | 5307.47 | 0.00092203 | 0.00598 | 1632 | 0.19393 | 0.00080471 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.18854 | 191.7696 | 188.4049 | 2.782%
Central Coast | CC_Central Coast | POINT MORETTI 1101 | 362 | POINT MORETTI 11015078 | 0.13606 | 295.233 | 12.9153 | 0 | 12.9153 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 299 | 1 | 14540 |  | 2624 | 1730 | 14540 | 2624 | 1730 | 4903.48 | 0.00046084 | 0.00251 | 1633 | 0.10782 | 0.00080462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.10782 | 203.1692 | 203.1692 | 0%
Central Valley | ST_Stockton | FROGTOWN 1702 | 1352 | FROGTOWN 170211212 | 0.22311 | 509.9315 | 21.4144 | 0 | 21.4144 | 0 | 1142 | 0 | 0 | 0 | 0 | 0 | 0 | 376 | 1 | 2086 |  | 378 | 250 | 2086 | 378 | 250 | 705.6 | 0.00043754 | 0.00034 | 1634 | 0.14791 | 0.00080384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.14791 | 17.6517 | 17.6517 | 0%
Sierra | SI_Sierra | EL DORADO PH 2101 | 2217 | EL DORADO PH 210152456 | 0.16272 | 206.8123 | 10.1973 | 0 | 10.1973 | 0 | 4873 | 0 | 0 | 0 | 0 | 0 | 0 | 386 | 1 | 8861 |  | 1600 | 1055 | 8861 | 1600 | 1055 | 2989.49 | 0.0007868 | 0.00262 | 1635 | 0.12663 | 0.00080147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.12663 | 156.9035 | 156.9035 | 0%
North Coast | HU_Humboldt | WILLOW CREEK 1101 | 6999 | WILLOW CREEK 110129362 | 0.090147 | 140.4913 | 7.228 | 0 | 7.228 | 0 | 4007 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 1 | 7289 |  | 1317 | 868 | 7289 | 1317 | 868 | 2460.3 | 0.00064166 | 0.00176 | 1636 | 0.086372 | 0.00079974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.086372 | 182.2073 | 182.2073 | 0%
North Valley | NV_North Valley | CLARK ROAD 1102 | 4276 | CLARK ROAD 110290548 | 0.37063 | 433.4796 | 17.7593 | 7.7097 | 10.0496 | 10.7754 | 1635 | 1598 | 571 | 479 | 379 | 345 | 0 | 878 | 0.39325 | 2770 |  | 783 | 619 | 1172 | 404 | 274 | 658.96 | 0.00085502 | 0.00072 | 1637 | 0.16899 | 0.00079338 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.095628 | 40.2005 | 44.0896 | 43.41%
Central Valley | YO_Yosemite | PEORIA 1705 | 2656 | PEORIA 170567898 | 0.016676 | 80.4095 | 3.4125 | 0 | 3.4125 | 0 | 373 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 1 | 690 |  | 126 | 84 | 690 | 126 | 84 | 234.72 | 0.00020739 | 5e-05 | 1638 | 0.040318 | 0.00079055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.040318 | 36.9231 | 36.9231 | 0%
North Coast | SO_Sonoma | MONTE RIO 1113 | 3021 | MONTE RIO 1113320 | 0.067914 | 71.3274 | 3.4369 | 0 | 3.4369 | 0 | 2141 | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 1 | 3900 |  | 705 | 466 | 3900 | 705 | 466 | 1316.85 | 0.00095215 | 0.0014 | 1639 | 0.034777 | 0.00079038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.034777 | 205.1248 | 205.1248 | 0%
North Coast | HU_Humboldt | GUALALA 1112 | 2336 | GUALALA 11121294 | 0.45953 | 472.2837 | 19.9169 | 0 | 19.9169 | 0 | 9538 | 0 | 0 | 0 | 0 | 0 | 0 | 413 | 1 | 17333 |  | 3128 | 2061 | 17333 | 3128 | 2061 | 5845.33 | 0.000973 | 0.00633 | 1640 | 0.26352 | 0.00078662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.26352 | 157.0529 | 157.0529 | 0%
Sierra | SI_Sierra | BRUNSWICK 1105 | 4501 | BRUNSWICK 11052210 | 0.41366 | 596.7514 | 23.6981 | 1.3053 | 22.3928 | 9.2979 | 17348 | 6734 | 3315 | 3026 | 1668 | 1540 | 0 | 1537 | 0.60765 | 25885 |  | 6770 | 5302 | 19151 | 5102 | 3762 | 8713.33 | 0.00069319 | 0.00735 | 1641 | 0.27011 | 0.00078293 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.25523 | 227.8411 | 285.6768 | 5.508%
North Coast | HU_Humboldt | NEWBURG 1132 | 3309 | NEWBURG 11323425 | 0.006504 | 9.8726 | 0.57898 | 0 | 0.57898 | 0.57898 | 282 | 614 | 100 | 55 | 0 | 0 | 0 | 13 | 0 | 614 |  | 100 | 55 | 0 | 100 | 55 | 137 | 0.00065879 | 0.00014 | 1642 | 0.0038956 | 0.00077912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0038956 | 172.7184 | 172.7184 | 0%
Central Coast | DA_De Anza | LOS GATOS 1107 | 3373 | LOS GATOS 110760114 | 0.44765 | 592.9062 | 22.793 | 0 | 22.793 | 0 | 4911 | 0 | 0 | 0 | 0 | 0 | 0 | 439 | 1 | 8930 |  | 1613 | 1063 | 8930 | 1613 | 1063 | 3013.51 | 0.00075501 | 0.00253 | 1643 | 0.21807 | 0.00077604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.21807 | 70.7674 | 70.7674 | 0%
North Valley | NV_North Valley | GANSNER 1101 | 7389 | GANSNER 11012424 | 0.40596 | 451.353 | 18.3008 | 0 | 18.3008 | 0 | 10480 | 0 | 0 | 0 | 0 | 0 | 0 | 489 | 1 | 19044 |  | 3437 | 2265 | 19044 | 3437 | 2265 | 6422.65 | 0.00089942 | 0.00643 | 1644 | 0.21656 | 0.00077341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.21656 | 187.8064 | 187.8064 | 0%
Sierra | SI_Sierra | PLACERVILLE 2106 | 5208 | PLACERVILLE 210611132 | 0.78519 | 1019.2476 | 42.5968 | 0 | 42.5968 | 0 | 11682 | 0 | 0 | 0 | 0 | 0 | 0 | 1738 | 1 | 21226 |  | 3830 | 2524 | 21226 | 3830 | 2524 | 7157.44 | 0.00077037 | 0.00614 | 1645 | 0.41986 | 0.00077179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.41986 | 89.9129 | 89.9129 | 0%
Central Coast | LP_Los Padres | CABRILLO 1103 | 3924 | CABRILLO 1103Y10 | 0.052337 | 108.8439 | 5.3544 | 0 | 5.3544 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 1 | 167 |  | 32 | 22 | 167 | 32 | 22 | 58.87 | 0.00048084 | 3e-05 | 1646 | 0.01464 | 0.00077054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.01464 | 5.9764 | 5.9764 | 0%
Central Coast | CC_Central Coast | BIG BASIN 1102 | 2032 | BIG BASIN 11025066 | 0.21838 | 313.7251 | 12.3833 | 0.75682 | 11.6265 | 8.8854 | 10666 | 2588 | 2587 | 1097 | 124 | 49 | 1 | 539 | 0.28247 | 8063 |  | 3575 | 1748 | 5475 | 3451 | 1699 | 5220.62 | 0.00069607 | 0.005 | 1647 | 0.15826 | 0.00076827 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.14859 | 296.8215 | 288.6945 | 6.112%
North Valley | NV_North Valley | MC ARTHUR 1101 | 2405 | MC ARTHUR 11011546 | 0.39812 | 261.5174 | 14.1532 | 0 | 14.1532 | 0 | 1165 | 0 | 0 | 0 | 0 | 0 | 0 | 259 | 1 | 2128 |  | 386 | 255 | 2128 | 386 | 255 | 720.34 | 0.0015223 | 0.00122 | 1648 | 0.047265 | 0.00076233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.047265 | 27.2729 | 27.2729 | 0%
Central Valley | ST_Stockton | STANISLAUS 1702 | 146 | STANISLAUS 17026028 | 0.001774 | 66.6079 | 4.304 | 0.30663 | 3.9972 | 4.3038 | 2684 | 1828 | 648 | 276 | 625 | 257 | 0 | 246 | 4.4004e-05 | 1828 |  | 648 | 276 | 0 | 23 | 19 | 31.51 | 2.6633e-05 | 0 | 1649 | 0.0045666 | 0.0007611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0042411 | 5.7541 | 150.5584 | 7.124%
Bay Area | PE_Peninsula | HALF MOON BAY 1103 | 3152 | HALF MOON BAY 1103H82 | 0.46149 | 742.2162 | 30.6585 | 16.1871 | 14.4714 | 18.4093 | 5261 | 1210 | 207 | 36 | 121 | 31 | 0 | 952 | 0.39954 | 5032 |  | 897 | 491 | 3822 | 776 | 460 | 1407.1 | 0.00062177 | 0.001 | 1650 | 0.22751 | 0.00075835 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.10739 | 53.623 | 29.2578 | 52.8%
Sierra | SI_Sierra | SHADY GLEN 1102 | 5046 | SHADY GLEN 110248894 | 0.22249 | 228.0361 | 8.8585 | 0.28314 | 8.5756 | 0.32879 | 4178 | 169 | 56 | 45 | 52 | 42 | 0 | 242 | 0.96288 | 7486 |  | 1378 | 916 | 7317 | 1326 | 874 | 2475.15 | 0.0009757 | 0.00269 | 1651 | 0.11194 | 0.00075636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.10837 | 154.6253 | 155.5564 | 3.196%
Sierra | SI_Sierra | PLACERVILLE 1110 | 317 | PLACERVILLE 1110circuit_breaker | 0.45037 | 269.7671 | 12.4867 | 0 | 12.4867 | 0 | 2588 | 0 | 0 | 0 | 0 | 0 | 0 | 418 | 1 | 4712 |  | 852 | 562 | 4712 | 852 | 562 | 1591.32 | 0.0016695 | 0.00296 | 1652 | 0.13652 | 0.00075423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.13652 | 68.2324 | 68.2324 | 0%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1104 | 8441 | SAN LUIS OBISPO 11042293 | 0.1904 | 207.7159 | 8.5095 | 0 | 8.5095 | 0 | 909 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 1 | 1663 |  | 302 | 200 | 1663 | 302 | 200 | 563.41 | 0.00091664 | 0.00058 | 1653 | 0.071445 | 0.00075205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.071445 | 35.4899 | 35.4899 | 0%
Sierra | SI_Sierra | APPLE HILL 2102 | 7746 | APPLE HILL 210289934 | 0.27317 | 134.4823 | 6.1314 | 0 | 6.1314 | 0 | 943 | 0 | 0 | 0 | 0 | 0 | 0 | 233 | 1 | 1725 |  | 313 | 207 | 1725 | 313 | 207 | 584.06 | 0.0020313 | 0.00132 | 1654 | 0.053239 | 0.00074984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.053239 | 51.0484 | 51.0484 | 0%
Bay Area | NB_North Bay | BOLINAS 1101 | 4225 | BOLINAS 11011236 | 0.043455 | 65.2453 | 3.7481 | 0 | 3.7481 | 0 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 1 | 902 |  | 165 | 109 | 902 | 165 | 109 | 307.23 | 0.00066602 | 0.00023 | 1655 | 0.026227 | 0.00074936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.026227 | 44.0222 | 44.0222 | 0%
North Coast | SO_Sonoma | BELLEVUE 2103 | 5583 | BELLEVUE 2103646 | 0.17649 | 234.6969 | 8.1487 | 5.1866 | 2.9621 | 6.8117 | 972 | 2371 | 814 | 536 | 679 | 441 | 4 | 461 | 0.16407 | 2663 |  | 867 | 571 | 292 | 188 | 130 | 283.84 | 0.00075198 | 0.00029 | 1656 | 0.082037 | 0.00074579 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.029821 | 63.468 | 106.3977 | 63.65%
Sierra | SI_Sierra | BRUNSWICK 1106 | 6865 | BRUNSWICK 110663124 | 0.07737 | 102.2455 | 4.0409 | 0.32178 | 3.7189 | 2.9191 | 2538 | 1775 | 773 | 585 | 175 | 102 | 0 | 261 | 0.27761 | 3058 |  | 1005 | 738 | 1283 | 830 | 636 | 1252.57 | 0.00075671 | 0.00131 | 1657 | 0.069315 | 0.00074533 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.063793 | 223.1819 | 248.7064 | 7.963%
Central Valley | YO_Yosemite | MIWUK 1701 | 1713 | MIWUK 1701circuit_breaker | 0.29663 | 375.3192 | 18.5947 | 0.6375 | 17.9572 | 7.7598 | 9084 | 2183 | 614 | 364 | 252 | 87 | 0 | 1192 | 0.58268 | 11802 |  | 2350 | 1508 | 9619 | 2098 | 1421 | 3739.97 | 0.00079034 | 0.00345 | 1658 | 0.20132 | 0.00074288 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.19442 | 116.8334 | 126.3801 | 3.428%
Central Valley | YO_Yosemite | BEAR VALLEY 2105 | 2243 | BEAR VALLEY 210521160 | 1.0051 | 588.2553 | 24.339 | 0 | 24.339 | 0 | 2841 | 0 | 0 | 0 | 0 | 0 | 0 | 495 | 1 | 5171 |  | 935 | 617 | 5171 | 935 | 617 | 1746.34 | 0.0017086 | 0.00332 | 1659 | 0.18207 | 0.00073122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.18207 | 38.4157 | 38.4157 | 0%
Sierra | SI_Sierra | EL DORADO PH 2102 | 108 | EL DORADO PH 2102circuit_breaker | 0.45794 | 461.6566 | 20.2761 | 0.016098 | 20.26 | 15.3445 | 12997 | 1011 | 720 | 638 | 153 | 141 | 0 | 1263 | 0.24322 | 6755 |  | 1756 | 1321 | 5744 | 1603 | 1180 | 2713.07 | 0.00099195 | 0.00331 | 1660 | 0.2237 | 0.00073103 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.22352 | 79.1213 | 86.6043 | 0.0794%
Central Coast | CC_Central Coast | CAMP EVERS 2105 | 1759 | CAMP EVERS 210510912 | 0.062887 | 106.3487 | 4.5447 | 0 | 4.5447 | 0 | 3567 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 1 | 6490 |  | 1172 | 773 | 6490 | 1172 | 773 | 2189.74 | 0.00059133 | 0.00144 | 1661 | 0.067156 | 0.00072996 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 6. >50% | 6. >50% | 0.067156 | 257.883 | 257.883 | 0%
North Coast | HU_Humboldt | HOPLAND 1101 | 1184 | HOPLAND 1101960 | 0.33349 | 358.472 | 20.3282 | 0 | 20.3282 | 0 | 1170 | 0 | 0 | 0 | 0 | 0 | 0 | 312 | 1 | 2137 |  | 387 | 256 | 2137 | 387 | 256 | 722.52 | 0.00093032 | 0.00075 | 1662 | 0.10185 | 0.0007275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.10185 | 19.0376 | 19.0376 | 0%
Central Coast | CC_Central Coast | BEN LOMOND 0401 | 7767 | BEN LOMOND 04015144 | 0.01216 | 69.5025 | 2.9502 | 0 | 2.9502 | 0 | 1341 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1 | 2447 |  | 443 | 293 | 2447 | 443 | 293 | 827.14 | 0.00017496 | 0.00016 | 1663 | 0.010883 | 0.00072555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.010883 | 150.1599 | 150.1599 | 0%
Central Valley | KE_Kern | TEJON 1102 | 9599 | TEJON 11023760 | 0.12825 | 154.8779 | 6.2258 | 6.2258 | 0 | 6.2258 | 64 | 300 | 40 | 31 | 40 | 31 | 0 | 141 | 0 | 300 |  | 40 | 31 | 0 | 0 | 0 | 0 | 0.00082807 | 0 | 1664 | 0.026795 | 0.00072418 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 6.4249 | 100%
Central Coast | SJ_San Jose | MC KEE 1108 | 9056 | MC KEE 110870535 | 0.009494 | 16.0085 | 1.0864 | 0 | 1.0864 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1 | 41 |  | 9 | 7 | 41 | 9 | 7 | 16.02 | 0.00059306 | 1e-05 | 1665 | 0.0043297 | 0.00072162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0043297 | 8.2845 | 8.2845 | 0%
Bay Area | DI_Diablo | ROSSMOOR 1108 | 5794 | ROSSMOOR 110837848 | 0.092093 | 132.1988 | 5.8831 | 2.5223 | 3.3608 | 5.8831 | 859 | 619 | 405 | 264 | 315 | 215 | 1 | 283 | 0 | 619 |  | 405 | 264 | 0 | 90 | 49 | 123.3 | 0.00069663 | 0.00013 | 1666 | 0.048616 | 0.00071494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.027772 | 26.7794 | 68.8407 | 42.87%
Central Valley | YO_Yosemite | CURTIS 1705 | 4028 | CURTIS 170565908 | 4.8803 | 365.308 | 14.5136 | 10.6487 | 3.865 | 14.5136 | 1449 | 2729 | 1292 | 424 | 1224 | 408 | 0 | 540 | 0 | 2729 |  | 1292 | 424 | 0 | 68 | 16 | 93.16 | 0.013359 | 0.00189 | 1667 | 0.0056485 | 0.00070606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0015042 | 17.594 | 89.0197 | 73.37%
Central Valley | YO_Yosemite | BEAR VALLEY 2105 | 1143 | BEAR VALLEY 21059560 | 1.0179 | 920.9682 | 35.8606 | 0 | 35.8606 | 0 | 10556 | 0 | 0 | 0 | 0 | 0 | 0 | 743 | 1 | 19182 |  | 3461 | 2281 | 19182 | 3461 | 2281 | 6467.95 | 0.0011053 | 0.00795 | 1668 | 0.29442 | 0.00070604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.29442 | 96.5126 | 96.5126 | 0%
Bay Area | EB_East Bay | FAIRVIEW 2207 | 8952 | circuit_breaker | 0.012466 | 35.3795 | 3.11 | 0 | 3.11 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 1 | 49 |  | 11 | 8 | 49 | 11 | 8 | 19.48 | 0.00035235 | 1e-05 | 1669 | 0.0021179 | 0.00070597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0021179 | 3.5369 | 3.5369 | 0%
Bay Area | NB_North Bay | IGNACIO 1101 | 2083 | IGNACIO 11011300 | 0.061277 | 111.2383 | 3.6955 | 0 | 3.6955 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 1 | 448 |  | 83 | 55 | 448 | 83 | 55 | 154.03 | 0.00055086 | 0.0001 | 1670 | 0.030228 | 0.00070297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.030228 | 22.46 | 22.46 | 0%
Central Valley | YO_Yosemite | MARIPOSA 2101 | 4021 | MARIPOSA 21014410 | 0.81166 | 624.8532 | 23.0093 | 0.33163 | 22.6777 | 20.3364 | 3287 | 253 | 253 | 153 | 195 | 100 | 0 | 846 | 0.11617 | 948 |  | 379 | 236 | 695 | 184 | 136 | 314.63 | 0.001299 | 0.0005 | 1671 | 0.031595 | 0.00070211 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.03114 | 8.1137 | 16.4716 | 1.441%
North Coast | HU_Humboldt | POINT ARENA 1101 | 8971 | POINT ARENA 11011296 | 0.022785 | 70.84 | 3.2419 | 0 | 3.2419 | 0 | 348 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 1 | 644 |  | 118 | 79 | 644 | 118 | 79 | 219.62 | 0.00032164 | 8e-05 | 1672 | 0.013299 | 0.00069997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.013299 | 36.3989 | 36.3989 | 0%
Central Valley | YO_Yosemite | CURTIS 1702 | 1459 | CURTIS 1702circuit_breaker | 1.9938 | 515.3708 | 20.3572 | 1.154 | 19.2032 | 1.4593 | 2872 | 434 | 175 | 88 | 164 | 80 | 0 | 540 | 0.92832 | 5287 |  | 1052 | 667 | 4853 | 888 | 587 | 1653.33 | 0.0038687 | 0.00714 | 1673 | 0.21689 | 0.00069965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.2046 | 46.2422 | 51.6771 | 5.669%
Sierra | SI_Sierra | BELL 1110 | 593 | BELL 111056214 | 1.0905 | 25.7611 | 0.72462 | 0.034848 | 0.68977 | 0.10227 | 137 | 24 | 17 | 4 | 0 | 0 | 0 | 23 | 0.85886 | 248 |  | 59 | 33 | 224 | 59 | 33 | 100.99 | 0.042333 | 0.00519 | 1674 | 0.0020797 | 0.00069322 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.0019797 | 85.5354 | 81.4219 | 4.809%
Central Coast | DA_De Anza | STELLING 1110 | 8101 | STELLING 11109265 | 0.10855 | 116.0571 | 4.433 | 0 | 4.433 | 0 | 565 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 1 | 1038 |  | 189 | 126 | 1038 | 189 | 126 | 352.35 | 0.00093534 | 0.00037 | 1675 | 0.042974 | 0.00069313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.042974 | 42.6352 | 42.6352 | 0%
Bay Area | NB_North Bay | WOODACRE 1101 | 6123 | WOODACRE 11011238 | 0.037175 | 82.9637 | 3.5339 | 1.2479 | 2.286 | 3.5339 | 2340 | 4120 | 914 | 278 | 637 | 177 | 0 | 207 | 0 | 4120 |  | 914 | 278 | 0 | 277 | 101 | 379.49 | 0.00044809 | 0.00026 | 1676 | 0.042192 | 0.00069166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.027293 | 121.1732 | 258.6377 | 35.31%
North Valley | NV_North Valley | PIT NO 5 1101 | 7724 | PIT NO 5 11011606 | 0.10286 | 112.0073 | 4.8093 | 0 | 4.8093 | 0 | 1542 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 1 | 2812 |  | 509 | 336 | 2812 | 509 | 336 | 950.41 | 0.00091829 | 0.00097 | 1677 | 0.057743 | 0.00068742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.057743 | 105.837 | 105.837 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2106 | 5030 | CAMP EVERS 21065020 | 0.22223 | 309.458 | 14.6491 | 0 | 14.6491 | 0.70947 | 7596 | 92 | 91 | 84 | 0 | 0 | 0 | 896 | 0.95157 | 13230 |  | 2462 | 1647 | 13138 | 2462 | 1647 | 4555.36 | 0.00071814 | 0.00368 | 1679 | 0.16153 | 0.00067305 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.16153 | 168.0655 | 168.0655 | 0%
Central Valley | YO_Yosemite | OAKHURST 1103 | 3487 | OAKHURST 110377384 | 0.10086 | 130.4802 | 5.135 | 0 | 5.135 | 4.6559 | 1422 | 240 | 223 | 80 | 81 | 26 | 0 | 523 | 0.093313 | 482 |  | 267 | 109 | 242 | 186 | 83 | 276.6 | 0.00077301 | 0.0003 | 1680 | 0.036325 | 0.00067269 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.036325 | 36.2217 | 51.9957 | 0%
Bay Area | PE_Peninsula | HALF MOON BAY 1103 | 2705 | HALF MOON BAY 11036018 | 0.14388 | 361.7819 | 16.2481 | 12.2379 | 4.0102 | 14.6242 | 1528 | 2337 | 433 | 131 | 296 | 105 | 0 | 497 | 0.099942 | 2616 |  | 483 | 164 | 279 | 187 | 59 | 281.3 | 0.00039768 | 0.00015 | 1681 | 0.082028 | 0.00067236 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.020245 | 46.6308 | 29.7265 | 75.32%
North Valley | NV_North Valley | CENTERVILLE 1101 | 976 | BUTTE 1105134600 | 0.53068 | 685.6487 | 24.1602 | 1.0312 | 23.1292 | 1.0369 | 2279 | 38 | 7 | 7 | 7 | 7 | 0 | 555 | 0.95708 | 4011 |  | 725 | 481 | 3973 | 718 | 474 | 1341.23 | 0.00077398 | 0.00116 | 1682 | 0.22403 | 0.00067074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.21447 | 31.0431 | 30.008 | 4.268%
Central Coast | LP_Los Padres | CABRILLO 1103 | 7181 | CABRILLO 1103Y46 | 0.88394 | 555.3494 | 31.5345 | 0 | 31.5345 | 0 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 470 | 1 | 265 |  | 50 | 34 | 265 | 50 | 34 | 92.35 | 0.0015917 | 0.00017 | 1683 | 0.014619 | 0.00066452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.014619 | 1.5856 | 1.5856 | 0%
North Valley | NV_North Valley | VOLTA 1102 | 9158 | VOLTA 110293418 | 0.047443 | 58.0359 | 2.1417 | 0 | 2.1417 | 0 | 1765 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 1 | 3217 |  | 582 | 384 | 3217 | 582 | 384 | 1086.87 | 0.00081748 | 0.00099 | 1684 | 0.025833 | 0.00066238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.025833 | 271.751 | 271.751 | 0%
Central Valley | ST_Stockton | SALT SPRINGS 2102 | 6725 | SALT SPRINGS 210297924 | 0.041948 | 61.7454 | 3.158 | 0 | 3.158 | 0 | 2241 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 1 | 4082 |  | 738 | 487 | 4082 | 738 | 487 | 1378.44 | 0.00067937 | 0.00104 | 1685 | 0.052773 | 0.00065967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.052773 | 233.6956 | 233.6956 | 0%
Central Coast | DA_De Anza | LOS GATOS 1106 | 1114 | LOS GATOS 1106LB44 | 0.28084 | 482.1818 | 17.3799 | 0 | 17.3799 | 0 | 8006 | 0 | 0 | 0 | 0 | 0 | 0 | 416 | 1 | 14551 |  | 2626 | 1731 | 14551 | 2626 | 1731 | 4907.21 | 0.00058244 | 0.00318 | 1686 | 0.18913 | 0.00065898 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.18913 | 151.0939 | 151.0939 | 0%
Central Valley | YO_Yosemite | CURTIS 1702 | 5933 | CURTIS 17029111 | 0.01515 | 80.662 | 3.9231 | 0 | 3.9231 | 0 | 539 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 1 | 991 |  | 181 | 120 | 991 | 181 | 120 | 337.16 | 0.00018782 | 7e-05 | 1689 | 0.051194 | 0.00065633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.051194 | 46.1369 | 46.1369 | 0%
Central Valley | FR_Fresno | DUNLAP 1102 | 6161 | DUNLAP 1102circuit_breaker | 0.09318 | 159.7207 | 5.8663 | 0 | 5.8663 | 0.33068 | 775 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 0.94363 | 1340 |  | 243 | 161 | 1340 | 243 | 161 | 453.51 | 0.00058339 | 0.00029 | 1690 | 0.043259 | 0.00065544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.043259 | 41.4231 | 41.4231 | 0%
Bay Area | MI_Mission | SUNOL 1101 | 3589 | SUNOL 1101MR297 | 0.10506 | 142.3359 | 4.9165 | 1.8443 | 3.0722 | 4.4771 | 632 | 504 | 83 | 27 | 2 | 0 | 0 | 189 | 0.089372 | 608 |  | 102 | 40 | 104 | 100 | 40 | 146.36 | 0.00073809 | 0.00015 | 1691 | 0.059157 | 0.00065008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.036965 | 32.5504 | 20.7466 | 37.51%
Central Valley | YO_Yosemite | MIWUK 1702 | 4356 | MIWUK 170238218 | 0.19334 | 262.3968 | 13.0455 | 0.3322 | 12.7133 | 8.8544 | 6487 | 1935 | 1042 | 749 | 486 | 343 | 0 | 938 | 0.32127 | 5724 |  | 1726 | 1200 | 3789 | 1240 | 857 | 2039.81 | 0.00073681 | 0.0019 | 1692 | 0.057725 | 0.00064859 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.056255 | 97.536 | 132.3066 | 2.546%
Central Valley | ST_Stockton | WEST POINT 1101 | 6273 | WEST POINT 110113444 | 0.28218 | 366.6245 | 14.3235 | 0 | 14.3235 | 0.2786 | 8874 | 230 | 228 | 196 | 22 | 20 | 0 | 895 | 0.98055 | 16044 |  | 3082 | 2077 | 15814 | 3060 | 2057 | 5615.46 | 0.00076966 | 0.0049 | 1693 | 0.085978 | 0.00064645 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.085978 | 213.6352 | 215.1711 | 0%
Bay Area | NB_North Bay | OLEMA 1101 | 8207 | OLEMA 1101602 | 0.10095 | 317.7538 | 16.1788 | 0 | 16.1788 | 0 | 1019 | 0 | 0 | 0 | 0 | 0 | 0 | 387 | 1 | 1863 |  | 338 | 224 | 1863 | 338 | 224 | 630.73 | 0.00031771 | 0.00022 | 1694 | 0.082371 | 0.00064352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.082371 | 20.8916 | 20.8916 | 0%
Central Coast | DA_De Anza | LOS GATOS 1107 | 8087 | LOS GATOS 110760024 | 0.028269 | 81.1968 | 3.1027 | 0 | 3.1027 | 0 | 214 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 1 | 401 |  | 74 | 50 | 401 | 74 | 50 | 137.47 | 0.00034815 | 5e-05 | 1695 | 0.019915 | 0.00064242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.019915 | 23.8506 | 23.8506 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2105 | 8278 | CAMP EVERS 210533542 | 0.11436 | 69.3958 | 3.5945 | 0 | 3.5945 | 0 | 2455 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 1 | 4470 |  | 808 | 533 | 4470 | 808 | 533 | 1509.26 | 0.001648 | 0.00277 | 1696 | 0.024875 | 0.00063781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.024875 | 224.7874 | 224.7874 | 0%
Central Valley | ST_Stockton | STANISLAUS 1701 | 1363 | STANISLAUS 17011331 | 0.099162 | 132.2886 | 7.8462 | 0.36307 | 7.4831 | 7.4095 | 5073 | 1441 | 1249 | 623 | 712 | 309 | 0 | 517 | 0.055663 | 1954 |  | 1342 | 684 | 513 | 630 | 375 | 909.27 | 0.00074959 | 0.00098 | 1697 | 0.041407 | 0.00063702 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.039491 | 84.1892 | 171.0379 | 4.627%
Central Valley | YO_Yosemite | CURTIS 1704 | 1390 | CURTIS 17048140 | 0.43078 | 632.8276 | 27.5907 | 15.2924 | 12.2985 | 26.8545 | 5867 | 11399 | 3412 | 2443 | 3269 | 2396 | 0 | 1306 | 0.026682 | 11684 |  | 3463 | 2477 | 285 | 194 | 81 | 291.43 | 0.00068072 | 0.00027 | 1698 | 0.22079 | 0.00063081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.098414 | 15.7743 | 125.5132 | 55.43%
Central Coast | CC_Central Coast | BIG BASIN 1102 | 5506 | BIG BASIN 110212758 | 0.038203 | 102.6915 | 5.4417 | 0.15644 | 5.2852 | 3.9348 | 3430 | 1489 | 1356 | 640 | 354 | 109 | 3 | 370 | 0.2769 | 3217 |  | 1668 | 846 | 1728 | 1314 | 737 | 1955.7 | 0.00037202 | 0.00102 | 1699 | 0.037848 | 0.00063079 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.036759 | 248.6175 | 306.5237 | 2.875%
Bay Area | NB_North Bay | OLEMA 1101 | 3752 | OLEMA 110150396 | 0.12141 | 265.8236 | 11.4818 | 0 | 11.4818 | 0 | 2220 | 0 | 0 | 0 | 0 | 0 | 0 | 455 | 1 | 4044 |  | 731 | 483 | 4044 | 731 | 483 | 1365.43 | 0.00045674 | 0.00069 | 1700 | 0.13922 | 0.00062993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.13922 | 63.6659 | 63.6659 | 0%
North Coast | HU_Humboldt | POINT ARENA 1101 | 7298 | POINT ARENA 11012637 | 0.070898 | 138.1811 | 4.1786 | 0 | 4.1786 | 0 | 2831 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 1 | 5153 |  | 931 | 614 | 5153 | 931 | 614 | 1739.24 | 0.00051308 | 0.00099 | 1701 | 0.033982 | 0.00062929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.033982 | 222.802 | 222.802 | 0%
Bay Area | NB_North Bay | BOLINAS 1101 | 1696 | BOLINAS 1101circuit_breaker | 0.027562 | 46.6346 | 2.0261 | 0.30265 | 1.7235 | 0.57348 | 196 | 19 | 17 | 1 | 9 | 0 | 2 | 81 | 0.71696 | 283 |  | 66 | 34 | 264 | 57 | 34 | 101.85 | 0.00059102 | 7e-05 | 1702 | 0.016353 | 0.00062895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.01391 | 33.0725 | 32.5743 | 14.94%
Central Coast | DA_De Anza | SARATOGA 1107 | 4481 | SARATOGA 1107413816 | 0.16396 | 286.2203 | 12.2686 | 0 | 12.2686 | 0 | 4615 | 0 | 0 | 0 | 0 | 0 | 0 | 251 | 1 | 8393 |  | 1516 | 999 | 8393 | 1516 | 999 | 2832.29 | 0.00057286 | 0.00181 | 1703 | 0.10446 | 0.0006255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.10446 | 123.5679 | 123.5679 | 0%
Bay Area | MI_Mission | SUNOL 1101 | 1200 | SUNOL 1101MR298 | 0.29791 | 109.1868 | 4.4737 | 3.3142 | 1.1595 | 4.4737 | 165 | 310 | 73 | 27 | 8 | 1 | 0 | 144 | 0 | 310 |  | 73 | 27 | 0 | 65 | 26 | 89.05 | 0.0027285 | 0.00037 | 1704 | 0.027508 | 0.00062518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0071295 | 56.0601 | 16.3177 | 74.08%
Bay Area | NB_North Bay | SAN RAFAEL 1108 | 1966 | SAN RAFAEL 110839156 | 0.009013 | 77.3343 | 2.9932 | 0 | 2.9932 | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 113 | 1 | 2101 |  | 381 | 252 | 2101 | 381 | 252 | 711.06 | 0.00011655 | 9e-05 | 1705 | 0.031649 | 0.00062056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.031649 | 127.2893 | 127.2893 | 0%
Sierra | SI_Sierra | BRUNSWICK 1106 | 2503 | BRUNSWICK 110651486 | 0.90856 | 1367.6704 | 55.4939 | 0.1464 | 55.3477 | 0.3858 | 32704 | 207 | 198 | 173 | 0 | 0 | 0 | 3194 | 0.99305 | 59196 |  | 10839 | 7183 | 58989 | 10839 | 7183 | 20158.44 | 0.00066431 | 0.01497 | 1706 | 0.58486 | 0.00061759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 4. >30 - 40% | 0.58332 | 195.8346 | 195.3186 | 0.2638%
North Coast | HU_Humboldt | BIG RIVER 1101 | 2536 | BIG RIVER 110155402 | 0.15618 | 97.1947 | 4.8936 | 0 | 4.8936 | 0 | 1540 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 1 | 2809 |  | 509 | 336 | 2809 | 509 | 336 | 950.14 | 0.0016069 | 0.0017 | 1707 | 0.025245 | 0.00061574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.025245 | 104.0142 | 104.0142 | 0%
Sierra | SI_Sierra | GRASS VALLEY 1101 | 3288 | GRASS VALLEY 1101circuit_breaker | 4.1e-05 | 13.4279 | 0.91648 | 0.11894 | 0.79754 | 0.14527 | 189 | 173 | 107 | 103 | 107 | 103 | 0 | 44 | 0.8415 | 472 |  | 163 | 140 | 299 | 56 | 37 | 103.63 | 3.0533e-06 | 0 | 1708 | 0.0055392 | 0.00061547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0048203 | 70.2161 | 177.8549 | 12.98%
Sierra | SA_Sacramento | VACAVILLE 1111 | 7978 | VACAVILLE 111112342 | 0.001116 | 1.8384 | 0.068939 | 0.035038 | 0.034091 | 0.068939 | 10 | 61 | 30 | 28 | 29 | 28 | 0 | 2 | 0 | 61 |  | 30 | 28 | 0 | 1 | 0 | 1.37 | 0.00060704 | 0 | 1709 | 0.0012273 | 0.00061364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0006069 | 29.3333 | 435.1648 | 50.82%
Central Coast | CC_Central Coast | BEN LOMOND 0401 | 5592 | BEN LOMOND 04015206 | 0.26763 | 177.6363 | 6.7436 | 0 | 6.7436 | 0 | 5416 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 1 | 9848 |  | 1778 | 1172 | 9848 | 1778 | 1172 | 3322.18 | 0.0015066 | 0.00557 | 1710 | 0.0036692 | 0.00061154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.0036692 | 263.6589 | 263.6589 | 0%
North Coast | HU_Humboldt | BIG RIVER 1101 | 4594 | BIG RIVER 11011286 | 0.073684 | 136.3222 | 5.3716 | 0 | 5.3716 | 0 | 3318 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 1 | 6038 |  | 1091 | 719 | 6038 | 1091 | 719 | 2038.09 | 0.00054051 | 0.00123 | 1711 | 0.045707 | 0.00060942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.045707 | 203.1056 | 203.1056 | 0%
Central Coast | LP_Los Padres | PERRY 1101 | 8009 | PERRY 110185870 | 0.18906 | 203.3674 | 10.2741 | 0 | 10.2741 | 0 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 1 | 299 |  | 56 | 38 | 299 | 56 | 38 | 103.63 | 0.00092967 | 0.00011 | 1712 | 0.024359 | 0.00060897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.024359 | 5.4506 | 5.4506 | 0%
Central Coast | LP_Los Padres | ATASCADERO 1101 | 6483 | ATASCADERO 1101A50 | 0.097822 | 399.2761 | 17.4362 | 0 | 17.4362 | 0 | 1695 | 0 | 0 | 0 | 0 | 0 | 0 | 476 | 1 | 3090 |  | 559 | 369 | 3090 | 559 | 369 | 1043.93 | 0.000245 | 0.00028 | 1713 | 0.16538 | 0.0006014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.16538 | 32.0598 | 32.0598 | 0%
Central Valley | YO_Yosemite | OAKHURST 1103 | 969 | OAKHURST 110310140 | 0.21333 | 382.6442 | 16.7873 | 0.43258 | 16.3547 | 3.8712 | 3535 | 279 | 177 | 50 | 135 | 39 | 0 | 1057 | 0.7694 | 5228 |  | 1071 | 640 | 4949 | 936 | 601 | 1727.73 | 0.00055753 | 0.00109 | 1714 | 0.15555 | 0.00059828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.15154 | 57.2311 | 63.7982 | 2.577%
North Valley | NV_North Valley | ORO FINO 1102 | 3255 | ORO FINO 110265932 | 0.071521 | 87.1295 | 3.7328 | 0.12197 | 3.6108 | 3.3619 | 2691 | 2140 | 1137 | 1008 | 322 | 309 | 0 | 194 | 0.099345 | 2627 |  | 1225 | 1066 | 487 | 903 | 757 | 1280.94 | 0.00082086 | 0.00154 | 1715 | 0.045272 | 0.00059569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.043793 | 250.0834 | 328.1749 | 3.268%
Central Valley | YO_Yosemite | MIWUK 1701 | 1421 | MIWUK 1701953336 | 0.16796 | 242.2121 | 12.3106 | 0.42064 | 11.8898 | 1.3549 | 6087 | 932 | 49 | 33 | 17 | 10 | 0 | 749 | 0.88994 | 10780 |  | 1827 | 1205 | 9848 | 1810 | 1195 | 3366.02 | 0.00069344 | 0.00261 | 1716 | 0.11084 | 0.00059275 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.10705 | 152.2317 | 148.4086 | 3.417%
Central Valley | ST_Stockton | MARTELL 1101 | 1559 | MARTELL 110111244 | 0.40914 | 556.0575 | 22.483 | 0 | 22.483 | 0 | 5672 | 0 | 0 | 0 | 0 | 0 | 0 | 688 | 1 | 10312 |  | 1862 | 1227 | 10312 | 1862 | 1227 | 3479.02 | 0.00073579 | 0.00285 | 1717 | 0.17084 | 0.00058909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.17084 | 82.8183 | 82.8183 | 0%
Sierra | SI_Sierra | COLUMBIA HILL 1101 | 7329 | COLUMBIA HILL 110190730 | 0.24014 | 215.3701 | 7.8127 | 0 | 7.8127 | 0 | 1333 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 1 | 2433 |  | 441 | 291 | 2433 | 441 | 291 | 823.14 | 0.001115 | 0.00102 | 1718 | 0.067619 | 0.00058799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.067619 | 56.4466 | 56.4466 | 0%
North Coast | SO_Sonoma | FORT ROSS 1121 | 5177 | FORT ROSS 1121560 | 0.093721 | 119.0472 | 4.7049 | 0 | 4.7049 | 0 | 1801 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 1 | 3283 |  | 594 | 392 | 3283 | 594 | 392 | 1109.25 | 0.00078726 | 0.00097 | 1719 | 0.03406 | 0.00058724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.03406 | 126.2507 | 126.2507 | 0%
North Coast | HU_Humboldt | WILLOW CREEK 1103 | 1655 | WILLOW CREEK 110347966 | 0.23158 | 347.6594 | 17.5047 | 0.21439 | 17.2903 | 2.6403 | 5513 | 315 | 315 | 77 | 289 | 62 | 0 | 642 | 0.84916 | 8827 |  | 1852 | 1090 | 8512 | 1563 | 1028 | 2907.39 | 0.0006661 | 0.00216 | 1720 | 0.12502 | 0.00058422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.12349 | 90.3973 | 105.7999 | 1.225%
Bay Area | MI_Mission | LAS POSITAS 2108 | 2996 | LAS POSITAS 2108MR190 | 0.10122 | 23.4813 | 1.2197 | 0 | 1.2197 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 32 |  | 8 | 6 | 32 | 8 | 6 | 13.84 | 0.0043108 | 7e-05 | 1721 | 0.0017498 | 0.00058327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0017498 | 6.559 | 6.559 | 0%
Central Valley | YO_Yosemite | BEAR VALLEY 2101 | 8841 | BEAR VALLEY 210110019 | 0.012791 | 29.9647 | 1.5703 | 1.4756 | 0.094697 | 1.5703 | 36 | 102 | 4 | 4 | 4 | 4 | 0 | 31 | 0 | 102 |  | 4 | 4 | 0 | 0 | 0 | 0 | 0.00042687 | 0 | 1722 | 0.007488 | 0.000576 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00045157 | 0 | 2.5473 | 93.97%
North Coast | HU_Humboldt | EEL RIVER 1102 | 7174 | EEL RIVER 11021902 | 0.42609 | 176.1944 | 6.3216 | 4.2966 | 2.0252 | 6.3216 | 2411 | 5085 | 1220 | 750 | 779 | 495 | 0 | 153 | 0 | 5085 |  | 1220 | 750 | 0 | 441 | 255 | 604.17 | 0.0024183 | 0.00222 | 1723 | 0.01438 | 0.00057521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0046068 | 217.7574 | 192.9894 | 67.97%
Central Coast | SJ_San Jose | HICKS 2101 | 2897 | HICKS 2101XR162 | 0.10808 | 63.3176 | 3.3811 | 0 | 3.3811 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 1 | 94 |  | 19 | 13 | 94 | 19 | 13 | 34.49 | 0.0017069 | 7e-05 | 1724 | 0.0045734 | 0.00057168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0045734 | 5.6195 | 5.6195 | 0%
North Valley | NV_North Valley | SPANISH CREEK 4401 | 8574 | SPANISH CREEK 4401circuit_breaker | 0.057923 | 87.2889 | 4.1417 | 0 | 4.1417 | 0 | 688 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 1 | 1262 |  | 230 | 152 | 1262 | 230 | 152 | 428.68 | 0.00066358 | 0.00032 | 1725 | 0.047933 | 0.00057063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.047933 | 55.5332 | 55.5332 | 0%
Central Valley | ST_Stockton | CALAVERAS CEMENT 1101 | 5012 | CALAVERAS CEMENT 1101502 | 1.4005 | 881.2508 | 37.7525 | 0 | 37.7525 | 0 | 2362 | 0 | 0 | 0 | 0 | 0 | 0 | 1028 | 1 | 4302 |  | 778 | 513 | 4302 | 778 | 513 | 1453.04 | 0.0015892 | 0.00257 | 1726 | 0.22332 | 0.00056968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.22332 | 20.6079 | 20.6079 | 0%
North Coast | HU_Humboldt | KONOCTI 1108 | 3962 | KONOCTI 11081278 | 0.18868 | 116.2114 | 6.3958 | 0 | 6.3958 | 0 | 674 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 1 | 1236 |  | 225 | 149 | 1236 | 225 | 149 | 419.49 | 0.0016236 | 0.00076 | 1727 | 0.040363 | 0.0005685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.040363 | 35.1792 | 35.1792 | 0%
Central Coast | CC_Central Coast | ROB ROY 2104 | 1855 | ROB ROY 2104circuit_breaker | 0.22807 | 346.077 | 14.3292 | 0 | 14.3292 | 0 | 4465 | 0 | 0 | 0 | 0 | 0 | 0 | 335 | 1 | 8121 |  | 1467 | 967 | 8121 | 1467 | 967 | 2740.68 | 0.00065902 | 0.00201 | 1728 | 0.12038 | 0.00056517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.12038 | 102.3786 | 102.3786 | 0%
Bay Area | PE_Peninsula | HALF MOON BAY 1102 | 1861 | HALF MOON BAY 11028848 | 0.04304 | 75.4528 | 4.5271 | 0 | 4.5271 | 0 | 1789 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 1 | 3261 |  | 590 | 390 | 3261 | 590 | 390 | 1101.79 | 0.00057042 | 0.0007 | 1729 | 0.027681 | 0.00056491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.027681 | 130.3267 | 130.3267 | 0%
North Coast | HU_Humboldt | LUCERNE 1106 | 3304 | LUCERNE 110638436 | 0.00787 | 94.6548 | 4.7824 | 0 | 4.7824 | 0 | 465 | 0 | 0 | 0 | 0 | 0 | 0 | 142 | 1 | 857 |  | 156 | 104 | 857 | 156 | 104 | 290.85 | 8.3144e-05 | 3e-05 | 1730 | 0.028398 | 0.00055682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.028398 | 32.6197 | 32.6197 | 0%
North Coast | SO_Sonoma | MONTE RIO 1113 | 6026 | MONTE RIO 1113202 | 0.039416 | 88.2758 | 4.1875 | 0 | 4.1875 | 2.0938 | 2262 | 14 | 12 | 3 | 0 | 0 | 0 | 254 | 0.5 | 2074 |  | 385 | 249 | 2060 | 385 | 249 | 712.85 | 0.00044651 | 0.00036 | 1731 | 0.048804 | 0.00055459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.048804 | 91.9403 | 91.9403 | 0%
North Valley | NV_North Valley | ORO FINO 1102 | 8106 | ORO FINO 1102127563 | 0.079478 | 170.8798 | 6.8625 | 0.41212 | 6.4504 | 5.2449 | 3672 | 923 | 680 | 571 | 11 | 11 | 0 | 290 | 0.23572 | 2498 |  | 964 | 759 | 1575 | 953 | 748 | 1447.36 | 0.00046511 | 0.00092 | 1732 | 0.054333 | 0.00055442 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.05107 | 147.7433 | 140.4736 | 6.005%
North Coast | SO_Sonoma | MONTE RIO 1113 | 1580 | MONTE RIO 11133970 | 0.078096 | 205.8334 | 9.3513 | 1.4661 | 7.885 | 3.322 | 3107 | 569 | 86 | 32 | 34 | 18 | 0 | 668 | 0.64476 | 4215 |  | 745 | 467 | 3646 | 711 | 449 | 1302.21 | 0.00037941 | 0.00056 | 1733 | 0.064828 | 0.00055409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.054663 | 90.1708 | 79.6678 | 15.68%
Central Valley | YO_Yosemite | MIWUK 1702 | 2478 | MIWUK 17028130 | 0.19584 | 255.988 | 10.8598 | 1.4699 | 9.39 | 9.7456 | 3631 | 2083 | 792 | 495 | 397 | 226 | 0 | 595 | 0.1026 | 2761 |  | 914 | 576 | 678 | 517 | 350 | 769.31 | 0.00076503 | 0.00082 | 1734 | 0.037592 | 0.00055283 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.032504 | 55.0588 | 84.1632 | 13.54%
Sierra | SI_Sierra | PLACERVILLE 1112 | 4731 | PLACERVILLE 1112circuit_breaker | 0.079967 | 162.9407 | 6.7892 | 0.19659 | 6.5924 | 0.19659 | 1710 | 108 | 53 | 51 | 53 | 51 | 0 | 177 | 0.97104 | 3135 |  | 601 | 413 | 3027 | 548 | 362 | 1023.19 | 0.00049077 | 0.00056 | 1735 | 0.061911 | 0.00055278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.060116 | 83.1257 | 88.5229 | 2.896%
Bay Area | PE_Peninsula | MENLO 1103 | 6867 | MENLO 11038512 | 0.23964 | 344.8459 | 14.5019 | 0 | 14.5019 | 0 | 7513 | 0 | 0 | 0 | 0 | 0 | 0 | 315 | 1 | 13656 |  | 2465 | 1625 | 13656 | 2465 | 1625 | 4606.09 | 0.00069492 | 0.00356 | 1736 | 0.12814 | 0.00055231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.12814 | 169.9778 | 169.9778 | 0%
Bay Area | PE_Peninsula | MENLO 1102 | 9113 | MENLO 11028896 | 0.011985 | 25.6019 | 1.585 | 0 | 1.585 | 0 | 612 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1 | 1124 |  | 205 | 136 | 1124 | 205 | 136 | 382.01 | 0.00046813 | 0.0002 | 1737 | 0.0077072 | 0.00055052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0077072 | 129.3344 | 129.3344 | 0%
Central Coast | LP_Los Padres | PERRY 1101 | 5601 | PERRY 1101circuit_breaker | 0.031344 | 71.0897 | 2.5081 | 0 | 2.5081 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 1 | 187 |  | 36 | 24 | 187 | 36 | 24 | 66.15 | 0.00044091 | 3e-05 | 1738 | 0.011547 | 0.00054983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.011547 | 14.3532 | 14.3532 | 0%
North Valley | NV_North Valley | MC ARTHUR 1101 | 8189 | MC ARTHUR 11011544 | 0.39156 | 265.0558 | 15.9419 | 0 | 15.9419 | 0 | 1188 | 0 | 0 | 0 | 0 | 0 | 0 | 323 | 1 | 2170 |  | 393 | 260 | 2170 | 393 | 260 | 733.71 | 0.0014773 | 0.00121 | 1739 | 0.032419 | 0.00054947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.032419 | 24.6521 | 24.6521 | 0%
Central Coast | SJ_San Jose | MORGAN HILL 2111 | 5779 | MORGAN HILL 2111XR292 | 0.11405 | 309.1963 | 12.0068 | 0 | 12.0068 | 0 | 845 | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 1 | 1547 |  | 281 | 186 | 1547 | 281 | 186 | 524.2 | 0.00036886 | 0.00022 | 1740 | 0.073232 | 0.00054651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.073232 | 23.4034 | 23.4034 | 0%
Bay Area | PE_Peninsula | MENLO 1102 | 2783 | MENLO 11029110 | 0.005466 | 23.1328 | 0.96458 | 0 | 0.96458 | 0 | 266 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 1 | 495 |  | 91 | 61 | 495 | 91 | 61 | 169.22 | 0.00023629 | 4e-05 | 1741 | 0.0054599 | 0.00054599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0054599 | 94.3413 | 94.3413 | 0%
Bay Area | MI_Mission | JARVIS 1111 | 2742 | JARVIS 1111MR121 | 0.031878 | 17.1788 | 1.7456 | 0 | 1.7456 | 0 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1 | 455 |  | 84 | 56 | 455 | 84 | 56 | 156.03 | 0.0018557 | 0.00032 | 1742 | 0.007617 | 0.00054407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.007617 | 48.1198 | 48.1198 | 0%
Central Coast | CC_Central Coast | BEN LOMOND 1101 | 6613 | BEN LOMOND 110196738 | 0.062885 | 96.8025 | 5.0292 | 0 | 5.0292 | 0.010795 | 2956 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 0.99785 | 5369 |  | 970 | 640 | 5369 | 970 | 640 | 1812.11 | 0.00064962 | 0.00131 | 1743 | 0.0593 | 0.00054403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0593 | 192.8749 | 192.8749 | 0%
North Valley | NV_North Valley | GANSNER 1101 | 3937 | GANSNER 11012006 | 0.29203 | 387.3484 | 17.0248 | 0 | 17.0248 | 0 | 8402 | 0 | 0 | 0 | 0 | 0 | 0 | 430 | 1 | 15270 |  | 2756 | 1816 | 15270 | 2756 | 1816 | 5150.02 | 0.00075392 | 0.00432 | 1744 | 0.14132 | 0.00054352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.14132 | 161.8814 | 161.8814 | 0%
Sierra | SI_Sierra | BRUNSWICK 1107 | 7366 | BRUNSWICK 110765574 | 0.004364 | 7.9223 | 0.42254 | 0 | 0.42254 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1 | 98 |  | 20 | 14 | 98 | 20 | 14 | 36.22 | 0.00055085 | 2e-05 | 1745 | 0.00163 | 0.00054333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00163 | 47.333 | 47.333 | 0%
Central Coast | DA_De Anza | LOS GATOS 1107 | 4416 | LOS GATOS 110760118 | 0.41326 | 723.7377 | 27.8384 | 0 | 27.8384 | 0 | 15104 | 0 | 0 | 0 | 0 | 0 | 0 | 675 | 1 | 27441 |  | 4951 | 3262 | 27441 | 4951 | 3262 | 9252.56 | 0.00057101 | 0.00588 | 1746 | 0.23465 | 0.00053943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.23465 | 177.8476 | 177.8476 | 0%
North Coast | HU_Humboldt | POINT ARENA 1101 | 6453 | POINT ARENA 1101476 | 0.059275 | 69.2834 | 2.8773 | 0 | 2.8773 | 0 | 429 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 1 | 791 |  | 145 | 96 | 791 | 145 | 96 | 269.84 | 0.00085554 | 0.00026 | 1747 | 0.01399 | 0.00053807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.01399 | 50.3949 | 50.3949 | 0%
Central Coast | LP_Los Padres | MORRO BAY 1101 | 1786 | MORRO BAY 1101V66 | 0.049946 | 91.343 | 3.2693 | 0 | 3.2693 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 1 | 98 |  | 20 | 14 | 98 | 20 | 14 | 36.22 | 0.0005468 | 2e-05 | 1748 | 0.0096664 | 0.00053702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0096664 | 6.1175 | 6.1175 | 0%
North Coast | SO_Sonoma | RINCON 1101 | 3904 | RINCON 1101576 | 0.055668 | 140.8408 | 3.0638 | 0.70189 | 2.3619 | 2.4019 | 210 | 166 | 153 | 66 | 56 | 0 | 1 | 129 | 0.21605 | 251 |  | 169 | 77 | 85 | 113 | 77 | 162.46 | 0.00039525 | 9e-05 | 1750 | 0.014391 | 0.00053301 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.011094 | 47.8422 | 55.1598 | 22.91%
Sierra | SI_Sierra | DIAMOND SPRINGS 1103 | 2888 | DIAMOND SPRINGS 1103circuit_breaker | 0.71096 | 731.956 | 36.8059 | 1.4356 | 35.3705 | 1.6023 | 6043 | 507 | 167 | 143 | 167 | 143 | 0 | 911 | 0.95647 | 11015 |  | 2064 | 1393 | 10508 | 1897 | 1250 | 3544.61 | 0.00097132 | 0.00383 | 1751 | 0.27111 | 0.00053262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.26053 | 53.6323 | 56.078 | 3.9%
North Valley | NV_North Valley | BUCKS CREEK 1103 | 7175 | BUCKS CREEK 11031131 | 0.039956 | 74.3436 | 2.9773 | 0 | 2.9773 | 0 | 2069 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 1 | 3770 |  | 682 | 450 | 3770 | 682 | 450 | 1273.64 | 0.00053745 | 0.00076 | 1752 | 0.026054 | 0.00053172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.026054 | 229.0687 | 229.0687 | 0%
Sierra | SI_Sierra | HIGGINS 1104 | 177 | HIGGINS 11041374 | 0.14367 | 165.6835 | 6.1949 | 0 | 6.1949 | 0 | 2277 | 0 | 0 | 0 | 0 | 0 | 0 | 172 | 1 | 4147 |  | 750 | 495 | 4147 | 750 | 495 | 1400.73 | 0.00086713 | 0.00135 | 1753 | 0.06691 | 0.00053103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.06691 | 121.0676 | 121.0676 | 0%
North Coast | SO_Sonoma | MONTE RIO 1112 | 7873 | MONTE RIO 1112999 | 0.39783 | 41.0145 | 2.1356 | 0 | 2.1356 | 0 | 1179 | 0 | 0 | 0 | 0 | 0 | 0 | 182 | 1 | 2153 |  | 390 | 258 | 2153 | 390 | 258 | 728.07 | 0.0096997 | 0.00787 | 1754 | 0.0084844 | 0.00053027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.0084844 | 182.6179 | 182.6179 | 0%
Central Valley | YO_Yosemite | PEORIA 1704 | 9933 | PEORIA 170492888 | 0.001071 | 1.9007 | 0.20966 | 0.12481 | 0.085038 | 0.20966 | 1 | 17 | 9 | 3 | 9 | 3 | 0 | 6 | 0 | 17 |  | 9 | 3 | 0 | 0 | 0 | 0 | 0.00056347 | 0 | 1755 | 0.0005296 | 0.0005296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0002148 | 0 | 42.9268 | 59.53%
North Valley | NV_North Valley | CRESCENT MILLS 2101 | 7811 | CRESCENT MILLS 21012562 | 0.17785 | 362.9201 | 22.0574 | 0 | 22.0574 | 0 | 7313 | 0 | 0 | 0 | 0 | 0 | 0 | 548 | 1 | 13292 |  | 2399 | 1581 | 13292 | 2399 | 1581 | 4482.91 | 0.00049005 | 0.00244 | 1756 | 0.097711 | 0.00052817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.097711 | 108.7618 | 108.7618 | 0%
Central Valley | ST_Stockton | SALT SPRINGS 2101 | 841 | SALT SPRINGS 21011216 | 0.074864 | 125.016 | 5.6638 | 0 | 5.6638 | 0 | 1849 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 1 | 3370 |  | 610 | 403 | 3370 | 610 | 403 | 1139 | 0.00059884 | 0.00076 | 1757 | 0.036328 | 0.0005265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.036328 | 107.7011 | 107.7011 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2101 | 6139 | GREEN VALLEY 210136820 | 0.047679 | 98.356 | 5.0129 | 0 | 5.0129 | 0 | 1190 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 1 | 2173 |  | 394 | 260 | 2173 | 394 | 260 | 735.35 | 0.00048476 | 0.0004 | 1758 | 0.03573 | 0.00052544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.03573 | 78.5976 | 78.5976 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2104 | 659 | CAMP EVERS 21045096 | 0.27513 | 503.7972 | 20.7945 | 0 | 20.7945 | 0 | 10434 | 0 | 0 | 0 | 0 | 0 | 0 | 549 | 1 | 18960 |  | 3421 | 2255 | 18960 | 3421 | 2255 | 6393.17 | 0.00054611 | 0.00388 | 1759 | 0.16573 | 0.00052282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.16573 | 164.5146 | 164.5146 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2101 | 5572 | GREEN VALLEY 210111054 | 0.55143 | 640.3616 | 21.8259 | 0 | 21.8259 | 0 | 9812 | 0 | 0 | 0 | 0 | 0 | 0 | 433 | 1 | 17831 |  | 3218 | 2120 | 17831 | 3218 | 2120 | 6013.45 | 0.00086112 | 0.00576 | 1760 | 0.095583 | 0.00052231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.095583 | 147.4392 | 147.4392 | 0%
Bay Area | MI_Mission | SUNOL 1101 | 9136 | SUNOL 1101MR387 | 0.054509 | 107.2455 | 5.2742 | 4.1701 | 1.1042 | 5.0985 | 136 | 209 | 12 | 6 | 0 | 0 | 0 | 128 | 0.033324 | 218 |  | 14 | 7 | 9 | 14 | 7 | 19.99 | 0.00050826 | 1e-05 | 1761 | 0.021284 | 0.00051912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0044558 | 12.6792 | 2.6544 | 79.06%
Central Valley | YO_Yosemite | OAKHURST 1103 | 2412 | OAKHURST 110310190 | 0.16341 | 313.6217 | 12.5267 | 0.73883 | 11.7879 | 12.4733 | 6933 | 5907 | 1474 | 1117 | 810 | 487 | 0 | 740 | 0.0042636 | 5961 |  | 1484 | 1123 | 54 | 674 | 636 | 928.24 | 0.00052103 | 0.00073 | 1762 | 0.085952 | 0.00051779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.080883 | 57.1774 | 118.4669 | 5.898%
Central Valley | FR_Fresno | BALCH NO 1 1101 | 9302 | BALCH NO 1 1101R372 | 0.20857 | 141.3081 | 5.5263 | 0 | 5.5263 | 0 | 229 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 1 | 428 |  | 79 | 53 | 428 | 79 | 53 | 146.75 | 0.001476 | 0.00024 | 1763 | 0.020579 | 0.00051449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.020579 | 14.2952 | 14.2952 | 0%
Central Valley | ST_Stockton | FROGTOWN 1701 | 5284 | FROGTOWN 1701L3361 | 0.007036 | 15.1169 | 0.52576 | 0 | 0.52576 | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1 | 221 |  | 42 | 28 | 221 | 42 | 28 | 77.43 | 0.00046544 | 4e-05 | 1764 | 0.017344 | 0.00051011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.017344 | 79.8847 | 79.8847 | 0%
Central Valley | YO_Yosemite | OAKHURST 1103 | 3938 | OAKHURST 11035120 | 0.044165 | 88.4514 | 3.7042 | 0.012879 | 3.6913 | 0.53617 | 3083 | 843 | 107 | 64 | 59 | 21 | 0 | 105 | 0.85525 | 5642 |  | 974 | 636 | 4799 | 915 | 615 | 1685.46 | 0.00049931 | 0.00095 | 1765 | 0.027529 | 0.0005098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.027434 | 247.881 | 262.9471 | 0.3477%
Sierra | SI_Sierra | PLACERVILLE 1111 | 1866 | PLACERVILLE 1111circuit_breaker | 0.083329 | 164.7987 | 7.7992 | 0 | 7.7992 | 0 | 1891 | 0 | 0 | 0 | 0 | 0 | 0 | 234 | 1 | 3446 |  | 624 | 412 | 3446 | 624 | 412 | 1165.02 | 0.00050564 | 0.00066 | 1766 | 0.048914 | 0.00050952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.048914 | 80.0078 | 80.0078 | 0%
Central Valley | YO_Yosemite | PEORIA 1705 | 8506 | PEORIA 170570198 | 0.012426 | 34.7239 | 2.0312 | 0.024432 | 2.007 | 0.07197 | 188 | 25 | 11 | 11 | 11 | 11 | 0 | 51 | 0.96457 | 366 |  | 74 | 54 | 341 | 63 | 43 | 117 | 0.00035785 | 5e-05 | 1767 | 0.0096704 | 0.00050897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.009555 | 31.39 | 36.4308 | 1.203%
Sierra | SI_Sierra | PLACER 1104 | 1086 | PLACER 110451732 | 0.009168 | 13.3022 | 0.72992 | 0 | 0.72992 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1 | 101 |  | 20 | 14 | 101 | 20 | 14 | 36.49 | 0.00068921 | 3e-05 | 1768 | 0.0040665 | 0.00050831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0040665 | 27.4001 | 27.4001 | 0%
Central Coast | CC_Central Coast | BIG BASIN 1102 | 8891 | BIG BASIN 11028403 | 0.063536 | 114.154 | 4.793 | 0 | 4.793 | 1.5059 | 3960 | 39 | 39 | 12 | 0 | 0 | 0 | 238 | 0.68582 | 4979 |  | 931 | 600 | 4940 | 931 | 600 | 1720.07 | 0.00055658 | 0.00108 | 1769 | 0.043092 | 0.00050107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.043092 | 194.2419 | 194.2419 | 0%
Central Valley | YO_Yosemite | MIWUK 1701 | 1412 | MIWUK 170111800 | 0.18366 | 214.8892 | 10.7083 | 0.57424 | 10.1341 | 9.3225 | 5090 | 1559 | 961 | 556 | 632 | 373 | 0 | 871 | 0.12941 | 2757 |  | 1177 | 699 | 1198 | 545 | 326 | 854.47 | 0.00085469 | 0.00097 | 1770 | 0.056971 | 0.00049975 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.053916 | 53.7789 | 109.9144 | 5.363%
Central Coast | CC_Central Coast | PAUL SWEET 2107 | 5603 | PAUL SWEET 210710986 | 0.077321 | 184.9344 | 8.6138 | 0 | 8.6138 | 0 | 1568 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 1 | 2860 |  | 518 | 342 | 2860 | 518 | 342 | 967.06 | 0.0004181 | 0.00045 | 1771 | 0.044334 | 0.00049813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.044334 | 60.1359 | 60.1359 | 0%
Bay Area | NB_North Bay | OLEMA 1101 | 5660 | OLEMA 11011318 | 0.093058 | 211.8739 | 8.6384 | 0 | 8.6384 | 0 | 3504 | 0 | 0 | 0 | 0 | 0 | 0 | 333 | 1 | 6375 |  | 1152 | 760 | 6375 | 1152 | 760 | 2151.99 | 0.00043921 | 0.00105 | 1772 | 0.078571 | 0.00049416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.078571 | 133.3573 | 133.3573 | 0%
Sierra | SI_Sierra | HALSEY 1101 | 82 | HALSEY 11011704 | 0.35899 | 295.9725 | 12.41 | 0.24716 | 12.1629 | 0.24716 | 5281 | 104 | 33 | 33 | 31 | 31 | 0 | 316 | 0.98008 | 9515 |  | 1732 | 1153 | 9411 | 1701 | 1122 | 3177.36 | 0.0012129 | 0.00429 | 1773 | 0.11118 | 0.00049415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.10897 | 139.8518 | 139.5644 | 1.992%
Central Valley | FR_Fresno | DUNLAP 1103 | 8273 | DUNLAP 1103circuit_breaker | 0.055511 | 113.8965 | 4.4506 | 0 | 4.4506 | 0 | 403 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 1 | 744 |  | 136 | 91 | 744 | 136 | 91 | 253.28 | 0.00048738 | 0.00014 | 1774 | 0.016793 | 0.0004939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.016793 | 30.5579 | 30.5579 | 0%
Central Coast | LP_Los Padres | SISQUOC 1103 | 753 | SISQUOC 1103M98 | 0.058282 | 136.6076 | 7.4581 | 0.23504 | 7.2231 | 0.23504 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 0.96849 | 77 |  | 16 | 11 | 77 | 16 | 11 | 28.85 | 0.00042664 | 1e-05 | 1775 | 0.0093097 | 0.00048998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0090163 | 2.2151 | 2.1453 | 3.151%
Central Valley | YO_Yosemite | MIWUK 1702 | 2669 | MIWUK 1702circuit_breaker | 0.13367 | 204.9628 | 9.5737 | 0.725 | 8.8489 | 4.1826 | 4409 | 1421 | 510 | 352 | 194 | 121 | 7 | 588 | 0.56312 | 5937 |  | 1326 | 890 | 4516 | 1132 | 769 | 1957.28 | 0.00065219 | 0.00154 | 1776 | 0.069568 | 0.00048991 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.064301 | 127.926 | 138.5048 | 7.573%
North Coast | HU_Humboldt | MAPLE CREEK 1101 | 5340 | MAPLE CREEK 1101circuit_breaker | 0.11144 | 206.196 | 9.9121 | 0 | 9.9121 | 0 | 4745 | 0 | 0 | 0 | 0 | 0 | 0 | 177 | 1 | 8629 |  | 1558 | 1027 | 8629 | 1558 | 1027 | 2911.07 | 0.00054045 | 0.00175 | 1777 | 0.063615 | 0.00048935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.063615 | 157.1813 | 157.1813 | 0%
Sierra | SI_Sierra | BRUNSWICK 1105 | 6143 | BRUNSWICK 110584480 | 0.134 | 124.6285 | 5.382 | 0 | 5.382 | 0.83163 | 4106 | 113 | 111 | 85 | 0 | 0 | 0 | 367 | 0.84548 | 6428 |  | 1252 | 837 | 6315 | 1252 | 837 | 2283.59 | 0.0010752 | 0.0028 | 1778 | 0.0058678 | 0.00048899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0058678 | 232.6269 | 232.6269 | 0%
North Valley | NV_North Valley | NOTRE DAME 1104 | 8004 | NOTRE DAME 11042537 | 0.030744 | 125.3179 | 4.4318 | 0 | 4.4318 | 0 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 1 | 408 |  | 76 | 51 | 408 | 76 | 51 | 140.84 | 0.00024533 | 4e-05 | 1779 | 0.012588 | 0.00048416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.012588 | 17.1487 | 17.1487 | 0%
North Valley | NV_North Valley | SYCAMORE CREEK 1111 | 6787 | SYCAMORE CREEK 11112268 | 0.25679 | 512.9688 | 21.4061 | 0 | 21.4061 | 0 | 15525 | 0 | 0 | 0 | 0 | 0 | 0 | 547 | 1 | 28205 |  | 5089 | 3353 | 28205 | 5089 | 3353 | 9510.38 | 0.00050059 | 0.0053 | 1780 | 0.17973 | 0.00048057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.17973 | 237.7364 | 237.7364 | 0%
Bay Area | EB_East Bay | OAKLAND K 1102 | 7506 | OAKLAND K 110217430 | 0.01266 | 62.1231 | 1.8314 | 0.86136 | 0.97008 | 1.8314 | 268 | 656 | 116 | 81 | 1 | 1 | 0 | 54 | 0 | 656 |  | 116 | 81 | 0 | 115 | 80 | 157.55 | 0.00020379 | 5e-05 | 1781 | 0.0095491 | 0.00047746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.005058 | 118.5474 | 63.3382 | 47.03%
North Valley | NV_North Valley | CRESCENT MILLS 2101 | 5834 | CRESCENT MILLS 21012230 | 0.041575 | 89.433 | 6.5769 | 0 | 6.5769 | 0 | 1709 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 1 | 3116 |  | 564 | 372 | 3116 | 564 | 372 | 1053.12 | 0.00046487 | 0.00055 | 1782 | 0.033467 | 0.00047137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.033467 | 85.7548 | 85.7548 | 0%
Sierra | SI_Sierra | HIGGINS 1104 | 1833 | HIGGINS 1104842642 | 0.065148 | 113.9832 | 4.8989 | 0 | 4.8989 | 0 | 1883 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 1 | 3432 |  | 621 | 410 | 3432 | 621 | 410 | 1159.65 | 0.00057156 | 0.00074 | 1783 | 0.045422 | 0.00046827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.045422 | 126.7641 | 126.7641 | 0%
Central Coast | CC_Central Coast | JOLON 1102 | 3984 | JOLON 11027040 | 0.36804 | 451.1422 | 20.1812 | 0 | 20.1812 | 0 | 566 | 0 | 0 | 0 | 0 | 0 | 0 | 302 | 1 | 1040 |  | 190 | 126 | 1040 | 190 | 126 | 353.9 | 0.00081579 | 0.00032 | 1784 | 0.022703 | 0.00046333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.022703 | 9.4147 | 9.4147 | 0%
Sierra | SI_Sierra | SHADY GLEN 1101 | 2936 | SHADY GLEN 110132726 | 0.18822 | 308.5068 | 12.929 | 0 | 12.929 | 0 | 4032 | 0 | 0 | 0 | 0 | 0 | 0 | 324 | 1 | 7334 |  | 1325 | 874 | 7334 | 1325 | 874 | 2475.31 | 0.00061009 | 0.00168 | 1785 | 0.09262 | 0.0004631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.09262 | 102.483 | 102.483 | 0%
Central Valley | ST_Stockton | STANISLAUS 1701 | 937 | STANISLAUS 170179826 | 0.097923 | 262.9157 | 10.6462 | 0 | 10.6462 | 0.32879 | 2788 | 55 | 55 | 43 | 0 | 0 | 0 | 392 | 0.96912 | 4973 |  | 944 | 629 | 4918 | 944 | 629 | 1735.9 | 0.00037245 | 0.00073 | 1786 | 0.070253 | 0.00046219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.070253 | 88.67 | 88.67 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2106 | 669 | CAMP EVERS 210612760 | 0.28015 | 613.7923 | 27.0392 | 0 | 27.0392 | 0.63996 | 12101 | 197 | 196 | 180 | 0 | 0 | 0 | 1570 | 0.97633 | 21664 |  | 4070 | 2732 | 21467 | 4070 | 2732 | 7507.93 | 0.00045643 | 0.00386 | 1787 | 0.2038 | 0.00046108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.2038 | 150.5222 | 150.5222 | 0%
Bay Area | PE_Peninsula | EMERALD LAKE 0401 | 2552 | EMERALD LAKE 0401circuit_breaker | 0.058411 | 309.0551 | 15.7581 | 0 | 15.7581 | 0 | 3030 | 0 | 0 | 0 | 0 | 0 | 0 | 465 | 1 | 5515 |  | 997 | 657 | 5515 | 997 | 657 | 1862.24 | 0.000189 | 0.00039 | 1788 | 0.049205 | 0.00045986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.049205 | 63.2689 | 63.2689 | 0%
Sierra | SI_Sierra | BRUNSWICK 1105 | 4312 | BRUNSWICK 11053611 | 0.00699 | 18.021 | 0.57292 | 0 | 0.57292 | 0.17481 | 428 | 12 | 12 | 11 | 0 | 0 | 0 | 49 | 0.69488 | 561 |  | 112 | 78 | 549 | 112 | 78 | 202.85 | 0.00038788 | 9e-05 | 1789 | 0.013733 | 0.00045777 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.013733 | 195.4909 | 195.4909 | 0%
Bay Area | MI_Mission | CASTRO VALLEY 1108 | 5700 | CASTRO VALLEY 1108MR243 | 0.087108 | 115.7914 | 4.872 | 1.1193 | 3.7527 | 2.9886 | 449 | 204 | 181 | 92 | 2 | 0 | 0 | 273 | 0.38657 | 524 |  | 239 | 131 | 320 | 237 | 131 | 353.49 | 0.00075228 | 0.00037 | 1790 | 0.03246 | 0.00045718 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.025002 | 63.1553 | 49.0561 | 22.97%
Central Coast | CC_Central Coast | BIG BASIN 1101 | 1146 | BIG BASIN 110195690 | 0.043828 | 111.1927 | 5.6453 | 0 | 5.6453 | 2.7481 | 2802 | 118 | 118 | 56 | 1 | 0 | 0 | 421 | 0.5132 | 2736 |  | 591 | 368 | 2618 | 590 | 368 | 1043.92 | 0.00039416 | 0.00048 | 1791 | 0.028798 | 0.00045711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.028798 | 104.5124 | 104.6895 | 0%
North Coast | HU_Humboldt | UKIAH 1115 | 5533 | UKIAH 1115circuit_breaker | 0.24363 | 449.296 | 18.6318 | 0 | 18.6318 | 0 | 2445 | 0 | 0 | 0 | 0 | 0 | 0 | 404 | 1 | 4452 |  | 805 | 531 | 4452 | 805 | 531 | 1503.53 | 0.00054225 | 0.00091 | 1792 | 0.097118 | 0.00045595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.097118 | 43.2057 | 43.2057 | 0%
Central Coast | CC_Central Coast | BIG BASIN 1102 | 2902 | BIG BASIN 110276752 | 0.12109 | 104.731 | 4.4509 | 0 | 4.4509 | 3.2015 | 3175 | 410 | 410 | 166 | 52 | 3 | 0 | 260 | 0.28071 | 2032 |  | 703 | 359 | 1622 | 651 | 356 | 1037.85 | 0.0011562 | 0.00157 | 1793 | 0.017276 | 0.00045464 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.017276 | 146.261 | 157.9439 | 0%
Bay Area | PE_Peninsula | HALF MOON BAY 1103 | 1683 | HALF MOON BAY 1103H80 | 0.22606 | 465.3691 | 19.883 | 5.3439 | 14.539 | 5.8964 | 4558 | 476 | 61 | 17 | 53 | 17 | 0 | 674 | 0.70344 | 6307 |  | 1114 | 711 | 5831 | 1061 | 694 | 1978.36 | 0.00048576 | 0.00107 | 1794 | 0.10923 | 0.00045324 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.079872 | 72.9761 | 56.0279 | 26.88%
Central Coast | CC_Central Coast | OTTER 1102 | 8479 | OTTER 11022012 | 0.25882 | 173.6314 | 9.0008 | 0 | 9.0008 | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 1 | 221 |  | 42 | 28 | 221 | 42 | 28 | 77.43 | 0.0014906 | 0.00013 | 1795 | 0.010828 | 0.00045118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.010828 | 4.6663 | 4.6663 | 0%
Central Valley | FR_Fresno | SAND CREEK 1103 | 5093 | SAND CREEK 11037110 | 0.21015 | 447.07 | 18.3483 | 0 | 18.3483 | 0 | 2337 | 0 | 0 | 0 | 0 | 0 | 0 | 348 | 1 | 4256 |  | 770 | 508 | 4256 | 770 | 508 | 1437.94 | 0.00047006 | 0.00075 | 1796 | 0.068861 | 0.00045007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.068861 | 41.9658 | 41.9658 | 0%
Bay Area | MI_Mission | CASTRO VALLEY 1106 | 994 | CASTRO VALLEY 1106MR337 | 0.066913 | 198.194 | 8.9087 | 1.0265 | 7.882 | 4.8843 | 792 | 399 | 398 | 361 | 0 | 0 | 0 | 384 | 0.45174 | 1054 |  | 517 | 440 | 655 | 517 | 440 | 767.24 | 0.00033761 | 0.00036 | 1797 | 0.0486 | 0.00045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.042999 | 65.5924 | 58.0331 | 11.52%
North Coast | SO_Sonoma | MONTE RIO 1113 | 2359 | MONTE RIO 1113477 | 0.000129 | 34.9655 | 1.3288 | 0 | 1.3288 | 0.56875 | 535 | 1 | 1 | 0 | 0 | 0 | 0 | 85 | 0.57198 | 564 |  | 104 | 68 | 563 | 104 | 68 | 193.15 | 3.6893e-06 | 0 | 1798 | 0.015562 | 0.00044463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.015562 | 78.2668 | 78.2668 | 0%
Central Coast | CC_Central Coast | RESERVATION ROAD 1102 | 7257 | RESERVATION ROAD 11023030 | 0.081118 | 185.1531 | 10.1892 | 0 | 10.1892 | 0 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 199 | 1 | 432 |  | 80 | 54 | 432 | 80 | 54 | 148.48 | 0.00043811 | 7e-05 | 1799 | 0.024009 | 0.00044462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.024009 | 7.8514 | 7.8514 | 0%
Central Coast | LP_Los Padres | PERRY 1101 | 7625 | PERRY 1101W26 | 0.031278 | 66.735 | 2.7858 | 0 | 2.7858 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 1 | 150 |  | 29 | 20 | 150 | 29 | 20 | 53.23 | 0.00046869 | 3e-05 | 1800 | 0.0084163 | 0.00044296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0084163 | 10.41 | 10.41 | 0%
Bay Area | DI_Diablo | MORAGA 1105 | 7613 | MORAGA 110531512 | 0.039542 | 60.1182 | 1.9197 | 1.5576 | 0.36212 | 1.9197 | 60 | 136 | 24 | 2 | 7 | 0 | 0 | 38 | 0 | 136 |  | 24 | 2 | 0 | 17 | 2 | 23.29 | 0.00065774 | 2e-05 | 1801 | 0.0039498 | 0.00043887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00074508 | 46.9456 | 12.502 | 81.14%
Sierra | SI_Sierra | EL DORADO PH 2101 | 2187 | EL DORADO PH 210136764 | 0.019821 | 54.8258 | 3.3044 | 0 | 3.3044 | 0 | 1833 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 1 | 3341 |  | 605 | 399 | 3341 | 605 | 399 | 1129.54 | 0.00036153 | 0.00045 | 1802 | 0.021821 | 0.00043641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.021821 | 183.0916 | 183.0916 | 0%
Central Valley | ST_Stockton | STANISLAUS 1701 | 7758 | STANISLAUS 17017144 | 0.045489 | 108.6404 | 4.4072 | 0.022917 | 4.3843 | 0.057955 | 1176 | 2 | 2 | 2 | 0 | 0 | 0 | 173 | 0.98685 | 2122 |  | 386 | 256 | 2120 | 386 | 256 | 719.62 | 0.00041871 | 0.00034 | 1803 | 0.033781 | 0.00043309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.033606 | 88.0418 | 87.584 | 0.52%
Central Valley | ST_Stockton | CALAVERAS CEMENT 1101 | 5891 | CALAVERAS CEMENT 110180930 | 0.099999 | 438.476 | 18.4636 | 0 | 18.4636 | 0 | 2268 | 0 | 0 | 0 | 0 | 0 | 0 | 619 | 1 | 4131 |  | 747 | 493 | 4131 | 747 | 493 | 1395.18 | 0.00022806 | 0.00035 | 1804 | 0.091082 | 0.00042761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.091082 | 40.4579 | 40.4579 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2105 | 6506 | CAMP EVERS 21055188 | 0.013739 | 23.5351 | 1.1498 | 0 | 1.1498 | 0 | 201 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 377 |  | 70 | 47 | 377 | 70 | 47 | 129.83 | 0.00058377 | 8e-05 | 1805 | 0.012331 | 0.00042521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.012331 | 60.8796 | 60.8796 | 0%
Bay Area | MI_Mission | CASTRO VALLEY 1106 | 8447 | CASTRO VALLEY 11068971 | 0.091214 | 209.4135 | 7.3778 | 1.6049 | 5.7729 | 7.3761 | 1293 | 647 | 625 | 314 | 0 | 0 | 0 | 343 | 0.00023104 | 648 |  | 625 | 314 | 1 | 625 | 314 | 856.34 | 0.00043557 | 0.00057 | 1806 | 0.053341 | 0.00042334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.041737 | 108.2642 | 84.7131 | 21.75%
North Coast | HU_Humboldt | KONOCTI 1108 | 3122 | KONOCTI 1108950 | 0.11525 | 113.1324 | 5.5445 | 0.20455 | 5.34 | 0.23769 | 323 | 33 | 9 | 7 | 8 | 6 | 0 | 161 | 0.95713 | 606 |  | 114 | 77 | 573 | 106 | 71 | 196.79 | 0.0010187 | 0.00022 | 1807 | 0.024125 | 0.00042324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.023235 | 19.8503 | 20.5609 | 3.689%
Central Coast | CC_Central Coast | ROB ROY 2104 | 2458 | ROB ROY 210410714 | 0.1417 | 317.1275 | 14.6888 | 0 | 14.6888 | 0 | 2983 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 1 | 5429 |  | 981 | 647 | 5429 | 981 | 647 | 1832.58 | 0.00044683 | 0.00091 | 1808 | 0.089499 | 0.00042216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.089499 | 66.7855 | 66.7855 | 0%
North Coast | HU_Humboldt | FORT BRAGG A 1101 | 3778 | FORT BRAGG A 11014698 | 0.007851 | 204.51 | 8.4218 | 0 | 8.4218 | 0 | 1849 | 0 | 0 | 0 | 0 | 0 | 0 | 184 | 1 | 3370 |  | 610 | 403 | 3370 | 610 | 403 | 1139 | 3.8389e-05 | 5e-05 | 1809 | 0.050544 | 0.0004212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.050544 | 72.4312 | 72.4312 | 0%
Central Valley | ST_Stockton | PINE GROVE 1101 | 7960 | PINE GROVE 110194936 | 0.098823 | 219.0745 | 9.0208 | 0 | 9.0208 | 0 | 1888 | 0 | 0 | 0 | 0 | 0 | 0 | 183 | 1 | 3441 |  | 623 | 411 | 3441 | 623 | 411 | 1163.2 | 0.00045109 | 0.00058 | 1810 | 0.054724 | 0.00042095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.054724 | 69.0624 | 69.0624 | 0%
Central Valley | YO_Yosemite | BEAR VALLEY 2105 | 7881 | BEAR VALLEY 21054609 | 0.041375 | 107.346 | 4.522 | 0 | 4.522 | 0 | 915 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 1 | 1674 |  | 304 | 201 | 1674 | 304 | 201 | 567.14 | 0.00038544 | 0.00024 | 1811 | 0.020174 | 0.0004203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.020174 | 67.2273 | 67.2273 | 0%
Bay Area | PE_Peninsula | HALF MOON BAY 1103 | 6526 | HALF MOON BAY 1103695411 | 0.098456 | 194.4769 | 10.1074 | 0 | 10.1074 | 0 | 3284 | 0 | 0 | 0 | 0 | 0 | 0 | 474 | 1 | 5976 |  | 1080 | 712 | 5976 | 1080 | 712 | 2017.44 | 0.00050626 | 0.00114 | 1812 | 0.050425 | 0.00042021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.050425 | 106.8525 | 106.8525 | 0%
Central Valley | YO_Yosemite | MARIPOSA 2102 | 7052 | MARIPOSA 2102594143 | 1.8274 | 52.0868 | 2.2561 | 0 | 2.2561 | 0.34962 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 0.84503 | 150 |  | 29 | 20 | 150 | 29 | 20 | 53.23 | 0.035085 | 0.00212 | 1813 | 0.0037717 | 0.00041908 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0037717 | 12.8543 | 12.8543 | 0%
Central Valley | ST_Stockton | PINE GROVE 1101 | 3649 | PINE GROVE 110152088 | 0.013536 | 38.0081 | 1.8489 | 0 | 1.8489 | 0 | 448 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 1 | 826 |  | 151 | 100 | 826 | 151 | 100 | 281.21 | 0.00035613 | 0.00011 | 1814 | 0.017119 | 0.00041755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.017119 | 81.6718 | 81.6718 | 0%
North Valley | NV_North Valley | FRENCH GULCH 1101 | 8802 | FRENCH GULCH 11011892 | 0.021321 | 73.6236 | 2.825 | 0 | 2.825 | 0 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 1 | 156 |  | 30 | 21 | 156 | 30 | 21 | 55.14 | 0.00028959 | 2e-05 | 1815 | 0.0058216 | 0.00041583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0058216 | 10.6195 | 10.6195 | 0%
North Valley | NV_North Valley | PARADISE 1105 | 1120 | PARADISE 1105circuit_breaker | 0.18035 | 435.1398 | 28.6949 | 7.4301 | 21.265 | 20.4352 | 3415 | 4914 | 1421 | 1326 | 659 | 612 | 0 | 2207 | 0.28784 | 6703 |  | 1744 | 1539 | 1789 | 1085 | 927 | 1647.46 | 0.00041445 | 0.00094 | 1816 | 0.024939 | 0.00041564 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.018481 | 51.0229 | 60.7774 | 25.89%
North Coast | SO_Sonoma | MIRABEL 1102 | 7770 | MIRABEL 11021139 | 0.01842 | 82.9256 | 3.9042 | 0.53996 | 3.364 | 3.904 | 1961 | 536 | 531 | 220 | 153 | 0 | 0 | 323 | 4.8511e-05 | 536 |  | 531 | 220 | 0 | 378 | 220 | 517.86 | 0.00022213 | 0.00017 | 1817 | 0.0032926 | 0.00041158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0028371 | 112.3657 | 136.0085 | 13.83%
Bay Area | PE_Peninsula | HALF MOON BAY 1103 | 1341 | HALF MOON BAY 11036014 | 0.023497 | 81.299 | 6.3638 | 4.0521 | 2.3117 | 6.0451 | 382 | 450 | 129 | 53 | 54 | 29 | 0 | 182 | 0.050088 | 485 |  | 135 | 57 | 35 | 81 | 28 | 114.12 | 0.00028902 | 5e-05 | 1818 | 0.0089784 | 0.00040811 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0032615 | 35.0385 | 21.2137 | 63.67%
Sierra | SI_Sierra | BRUNSWICK 1105 | 5922 | BRUNSWICK 1105circuit_breaker | 0.075632 | 197.8254 | 9.032 | 0.62348 | 8.4085 | 5.7405 | 4750 | 1735 | 1595 | 1326 | 731 | 730 | 0 | 626 | 0.36442 | 4883 |  | 2163 | 1701 | 3148 | 1432 | 971 | 2245.16 | 0.00038232 | 0.00114 | 1819 | 0.023642 | 0.00040762 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.02201 | 170.3034 | 239.4816 | 6.903%
Central Coast | DA_De Anza | SARATOGA 1107 | 6997 | SARATOGA 1107167792 | 0.038948 | 90.1489 | 3.7447 | 0 | 3.7447 | 0 | 2622 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 1 | 4774 |  | 863 | 569 | 4774 | 863 | 569 | 1611.97 | 0.00043204 | 0.00078 | 1820 | 0.031739 | 0.00040691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.031739 | 230.4592 | 230.4592 | 0%
Bay Area | PE_Peninsula | HALF MOON BAY 1103 | 9083 | HALF MOON BAY 11036065 | 0.11393 | 163.137 | 6.6532 | 2.3712 | 4.282 | 3.117 | 1281 | 744 | 118 | 18 | 52 | 4 | 0 | 199 | 0.5315 | 1987 |  | 343 | 167 | 1243 | 291 | 163 | 510.54 | 0.00069836 | 0.00042 | 1821 | 0.025971 | 0.0004058 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.016715 | 67.9588 | 51.554 | 35.64%
Central Coast | CC_Central Coast | PANOCHE 1103 | 3024 | PANOCHE 11034016 | 0.007461 | 36.167 | 2.2218 | 0 | 2.2218 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1 | 16 |  | 5 | 4 | 16 | 5 | 4 | 8.29 | 0.00020629 | 0 | 1822 | 0.00040553 | 0.00040553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00040553 | 2.2504 | 2.2504 | 0%
Central Valley | YO_Yosemite | PEORIA 1701 | 6045 | PEORIA 170176030 | 0.064213 | 118.5744 | 4.6722 | 0 | 4.6722 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 1 | 121 |  | 24 | 17 | 121 | 24 | 17 | 43.77 | 0.00054154 | 3e-05 | 1823 | 0.0093245 | 0.00040541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0093245 | 5.1368 | 5.1368 | 0%
Central Coast | LP_Los Padres | CAMBRIA 1102 | 329 | CAMBRIA 1102circuit_breaker | 0.14045 | 326.5413 | 16.2027 | 0 | 16.2027 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 194 | 1 | 1374 |  | 250 | 165 | 1374 | 250 | 165 | 466.16 | 0.00043011 | 0.00022 | 1824 | 0.036053 | 0.00040509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.036053 | 15.4296 | 15.4296 | 0%
Bay Area | NB_North Bay | OLEMA 1101 | 6620 | OLEMA 11011686 | 0.013571 | 29.255 | 1.1422 | 0 | 1.1422 | 0 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1 | 245 |  | 46 | 31 | 245 | 46 | 31 | 85.07 | 0.00046389 | 4e-05 | 1825 | 0.0060761 | 0.00040507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0060761 | 40.2719 | 40.2719 | 0%
Bay Area | DI_Diablo | MORAGA 1101 | 6063 | MORAGA 110118216 | 0.041336 | 105.6965 | 5.2767 | 4.0669 | 1.2098 | 5.0417 | 990 | 3050 | 1732 | 840 | 1638 | 788 | 1 | 395 | 0.044543 | 3131 |  | 1747 | 850 | 81 | 109 | 62 | 156.62 | 0.00039108 | 9e-05 | 1826 | 0.027944 | 0.00040499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0064071 | 90.0939 | 331.0779 | 77.07%
Central Valley | ST_Stockton | SALT SPRINGS 2102 | 1009 | SALT SPRINGS 21023142 | 0.18804 | 434.5217 | 22.154 | 0 | 22.154 | 0 | 16304 | 0 | 0 | 0 | 0 | 0 | 0 | 604 | 1 | 29620 |  | 5344 | 3521 | 29620 | 5344 | 3521 | 9987.08 | 0.00043276 | 0.00481 | 1827 | 0.11247 | 0.00040456 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.11247 | 241.2208 | 241.2208 | 0%
North Valley | NV_North Valley | VOLTA 1102 | 1012 | VOLTA 110253130 | 0.15368 | 332.8303 | 14.2189 | 0 | 14.2189 | 0 | 8003 | 0 | 0 | 0 | 0 | 0 | 0 | 340 | 1 | 14545 |  | 2625 | 1730 | 14545 | 2625 | 1730 | 4905.3 | 0.00046173 | 0.00252 | 1828 | 0.082407 | 0.00040396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.082407 | 184.6129 | 184.6129 | 0%
North Coast | HU_Humboldt | GUALALA 1112 | 739 | GUALALA 1112662 | 0.037759 | 152.1303 | 6.7928 | 0 | 6.7928 | 0 | 4238 | 0 | 0 | 0 | 0 | 0 | 0 | 149 | 1 | 7708 |  | 1392 | 918 | 7708 | 1392 | 918 | 2600.76 | 0.0002482 | 0.00072 | 1829 | 0.037962 | 0.00040385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.037962 | 204.9228 | 204.9228 | 0%
Sierra | SI_Sierra | BRUNSWICK 1107 | 1625 | BRUNSWICK 110750010 | 0.076297 | 108.5898 | 5.0695 | 0 | 5.0695 | 0.047159 | 2317 | 188 | 83 | 72 | 72 | 62 | 0 | 181 | 0.9907 | 4369 |  | 839 | 571 | 4181 | 767 | 509 | 1427.08 | 0.00070262 | 0.00112 | 1830 | 0.031892 | 0.00040369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.031892 | 151.2967 | 165.4993 | 0%
North Coast | HU_Humboldt | GUALALA 1111 | 6126 | GUALALA 111135562 | 0.17872 | 352.8935 | 13.9966 | 0 | 13.9966 | 0 | 7868 | 0 | 0 | 0 | 0 | 0 | 0 | 272 | 1 | 14300 |  | 2581 | 1701 | 14300 | 2581 | 1701 | 4822.97 | 0.00050643 | 0.00272 | 1831 | 0.099045 | 0.00040099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.099045 | 184.402 | 184.402 | 0%
North Coast | SO_Sonoma | MONTE RIO 1113 | 674 | MONTE RIO 1113524 | 0.11013 | 163.589 | 7.6674 | 0.56288 | 7.1045 | 1.0445 | 3594 | 171 | 25 | 3 | 13 | 2 | 0 | 660 | 0.86377 | 5819 |  | 1045 | 676 | 5648 | 1032 | 674 | 1922.16 | 0.00067324 | 0.00144 | 1832 | 0.035215 | 0.00040017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.032629 | 145.2591 | 136.2909 | 7.341%
Central Coast | CC_Central Coast | POINT MORETTI 1101 | 5662 | POINT MORETTI 11015076 | 0.11168 | 133.6096 | 7.0549 | 0 | 7.0549 | 0 | 1207 | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 1 | 2204 |  | 399 | 264 | 2204 | 399 | 264 | 744.99 | 0.00083589 | 0.00069 | 1834 | 0.011107 | 0.00039666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.011107 | 56.5562 | 56.5562 | 0%
Bay Area | PE_Peninsula | MENLO 1102 | 1414 | MENLO 11028952 | 0.089547 | 162.4998 | 6.2301 | 0 | 6.2301 | 0 | 1773 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 1 | 3232 |  | 585 | 386 | 3232 | 585 | 386 | 1092.33 | 0.00055106 | 0.00067 | 1835 | 0.046373 | 0.00039635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.046373 | 93.8988 | 93.8988 | 0%
Sierra | SI_Sierra | SHADY GLEN 1101 | 3147 | SHADY GLEN 110151696 | 0.21476 | 392.9259 | 16.7816 | 0 | 16.7816 | 0 | 6476 | 0 | 0 | 0 | 0 | 0 | 0 | 414 | 1 | 11772 |  | 2125 | 1401 | 11772 | 2125 | 1401 | 3970.73 | 0.00054656 | 0.00242 | 1836 | 0.10765 | 0.00039005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.10765 | 126.6266 | 126.6266 | 0%
Central Coast | LP_Los Padres | PURISIMA 1101 | 8990 | PURISIMA 1101Y44 | 0.12738 | 202.1646 | 7.0187 | 0 | 7.0187 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 1 | 20 |  | 5 | 5 | 20 | 5 | 5 | 8.65 | 0.00063011 | 1e-05 | 1837 | 0.011688 | 0.00038961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.011688 | 0.71238 | 0.71238 | 0%
Bay Area | MI_Mission | SAN RAMON 2107 | 1464 | SAN RAMON 2107circuit_breaker | 0.001073 | 2.0512 | 0.071402 | 0 | 0.071402 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 14 |  | 5 | 4 | 14 | 5 | 4 | 8.11 | 0.00052311 | 1e-05 | 1838 | 0.002314 | 0.00038567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.002314 | 70.0265 | 70.0265 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2105 | 5960 | CAMP EVERS 2105circuit_breaker | 0.091468 | 136.9304 | 6.8881 | 0 | 6.8881 | 0 | 3089 | 0 | 0 | 0 | 0 | 0 | 0 | 179 | 1 | 5622 |  | 1016 | 670 | 5622 | 1016 | 670 | 1897.9 | 0.00066799 | 0.00141 | 1839 | 0.044631 | 0.00038475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.044631 | 147.5014 | 147.5014 | 0%
North Valley | NV_North Valley | PIT NO 5 1101 | 7522 | PIT NO 5 11011658 | 0.038742 | 92.6891 | 4.6733 | 0 | 4.6733 | 0 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 1 | 3608 |  | 653 | 431 | 3608 | 653 | 431 | 1219.33 | 0.00041798 | 0.00057 | 1840 | 0.018422 | 0.00038379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.018422 | 139.7301 | 139.7301 | 0%
North Coast | SO_Sonoma | RINCON 1101 | 4442 | RINCON 1101circuit_breaker | 0.032819 | 38.8102 | 1.8464 | 0.05625 | 1.7903 | 0.31837 | 102 | 14 | 14 | 2 | 13 | 1 | 0 | 63 | 0.82757 | 177 |  | 45 | 23 | 163 | 32 | 22 | 58.51 | 0.00084563 | 6e-05 | 1841 | 0.0099601 | 0.00038308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0096577 | 17.8737 | 24.3717 | 3.046%
Central Valley | FR_Fresno | DUNLAP 1102 | 8694 | DUNLAP 110239190 | 0.023434 | 29.8333 | 1.6568 | 0 | 1.6568 | 0 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1 | 256 |  | 48 | 33 | 256 | 48 | 33 | 88.8 | 0.0007855 | 8e-05 | 1842 | 0.005362 | 0.000383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.005362 | 28.9712 | 28.9712 | 0%
Central Valley | ST_Stockton | SALT SPRINGS 2102 | 869 | SALT SPRINGS 21024796 | 0.085559 | 132.9739 | 5.985 | 0 | 5.985 | 0 | 4341 | 0 | 0 | 0 | 0 | 0 | 0 | 162 | 1 | 7895 |  | 1426 | 940 | 7895 | 1426 | 940 | 2664.17 | 0.00064343 | 0.00191 | 1844 | 0.048155 | 0.00038218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.048155 | 238.2608 | 238.2608 | 0%
Bay Area | NB_North Bay | ALTO 1125 | 6457 | ALTO 11251158 | 3.5e-05 | 43.8077 | 2.7758 | 0 | 2.7758 | 0 | 286 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 1 | 532 |  | 98 | 65 | 532 | 98 | 65 | 182.14 | 7.9895e-07 | 0 | 1845 | 0.010459 | 0.00037354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.010459 | 35.3057 | 35.3057 | 0%
Central Coast | SJ_San Jose | EDENVALE 2107 | 2757 | EDENVALE 2107XR336 | 0.015918 | 49.5008 | 4.2095 | 0 | 4.2095 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 1 | 27 |  | 7 | 5 | 27 | 7 | 5 | 12.02 | 0.00032157 | 0 | 1846 | 0.0011107 | 0.00037024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0011107 | 1.6629 | 1.6629 | 0%
Central Coast | LP_Los Padres | CABRILLO 1104 | 1584 | CABRILLO 1104Y22 | 0.072123 | 246.4095 | 10.4816 | 0 | 10.4816 | 0 | 274 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 1 | 510 |  | 94 | 63 | 510 | 94 | 63 | 174.68 | 0.0002927 | 6e-05 | 1847 | 0.012932 | 0.00036949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.012932 | 8.9681 | 8.9681 | 0%
Central Valley | ST_Stockton | ELECTRA 1101 | 5418 | ELECTRA 110161816 | 0.17145 | 532.0618 | 23.1163 | 0 | 23.1163 | 0 | 5002 | 0 | 0 | 0 | 0 | 0 | 0 | 494 | 1 | 9096 |  | 1642 | 1083 | 9096 | 1642 | 1083 | 3068.18 | 0.00032223 | 0.0011 | 1848 | 0.12168 | 0.00036763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.12168 | 71.0322 | 71.0322 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2106 | 4155 | CAMP EVERS 21065302 | 0.038738 | 194.1541 | 10.5498 | 0 | 10.5498 | 0 | 7075 | 0 | 0 | 0 | 0 | 0 | 0 | 465 | 1 | 12860 |  | 2321 | 1530 | 12860 | 2321 | 1530 | 4337.17 | 0.00019952 | 0.00096 | 1849 | 0.032687 | 0.00036727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.032687 | 220.0039 | 220.0039 | 0%
North Coast | SO_Sonoma | MONTE RIO 1113 | 6236 | MONTE RIO 11131313 | 2.6e-05 | 6.5345 | 0.20208 | 0 | 0.20208 | 0 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1 | 252 |  | 47 | 32 | 252 | 47 | 32 | 87.07 | 3.9789e-06 | 0 | 1850 | 0.0088085 | 0.00036702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0088085 | 232.5773 | 232.5773 | 0%
North Coast | HU_Humboldt | HARRIS 1109 | 2427 | HARRIS 1109700 | 0.13231 | 374.8189 | 14.4833 | 0 | 14.4833 | 0 | 7657 | 0 | 0 | 0 | 0 | 0 | 0 | 353 | 1 | 13917 |  | 2512 | 1656 | 13917 | 2512 | 1656 | 4693.97 | 0.00035299 | 0.00184 | 1851 | 0.091921 | 0.00036622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.091921 | 173.4407 | 173.4407 | 0%
Bay Area | DI_Diablo | MORAGA 1101 | 2271 | MORAGA 1101108540 | 0.039622 | 96.8455 | 3.1693 | 1.8223 | 1.347 | 2.9356 | 566 | 933 | 436 | 218 | 400 | 194 | 1 | 117 | 0.073742 | 1010 |  | 450 | 227 | 77 | 50 | 33 | 75.43 | 0.00040913 | 4e-05 | 1853 | 0.026699 | 0.00036573 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.011347 | 37.1204 | 141.9864 | 57.5%
North Coast | HU_Humboldt | FORT BRAGG A 1102 | 1845 | FORT BRAGG A 110231304 | 0.24436 | 498.1725 | 21.3494 | 0 | 21.3494 | 0 | 15410 | 0 | 0 | 0 | 0 | 0 | 0 | 340 | 1 | 27996 |  | 5051 | 3328 | 27996 | 5051 | 3328 | 9439.51 | 0.00049051 | 0.00515 | 1854 | 0.09867 | 0.00036276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.09867 | 236.5871 | 236.5871 | 0%
Sierra | SI_Sierra | BRUNSWICK 1102 | 582 | BRUNSWICK 11021010 | 0.33447 | 1072.0683 | 44.7384 | 0 | 44.7384 | 0 | 24749 | 0 | 0 | 0 | 0 | 0 | 0 | 1175 | 1 | 44956 |  | 8110 | 5343 | 44956 | 8110 | 5343 | 15156.74 | 0.00031198 | 0.00526 | 1856 | 0.25474 | 0.00035578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.25474 | 181.2758 | 181.2758 | 0%
Central Valley | YO_Yosemite | INDIAN FLAT 1104 | 3663 | INDIAN FLAT 1104circuit_breaker | 0.17033 | 323.8387 | 11.9989 | 0 | 11.9989 | 0 | 1095 | 0 | 0 | 0 | 0 | 0 | 0 | 216 | 1 | 2001 |  | 363 | 240 | 2001 | 363 | 240 | 677.4 | 0.00052597 | 0.0004 | 1857 | 0.034794 | 0.00035504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.034794 | 30.2529 | 30.2529 | 0%
North Valley | NV_North Valley | BURNEY 1102 | 4948 | BURNEY 110297318 | 0.004679 | 16.2623 | 0.60208 | 0 | 0.60208 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1 | 147 |  | 28 | 20 | 147 | 28 | 20 | 51.59 | 0.00028772 | 2e-05 | 1858 | 0.0031884 | 0.00035426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0031884 | 46.5052 | 46.5052 | 0%
Central Valley | YO_Yosemite | CURTIS 1705 | 5118 | CURTIS 1705843 | 0.062398 | 155.5532 | 6.7598 | 3.5381 | 3.222 | 6.6487 | 1775 | 4214 | 1427 | 974 | 1311 | 879 | 0 | 341 | 0.016446 | 4267 |  | 1437 | 980 | 53 | 126 | 101 | 177.39 | 0.00040114 | 0.00011 | 1859 | 0.033784 | 0.00035192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.016103 | 39.1065 | 212.5787 | 52.34%
Central Valley | ST_Stockton | CALAVERAS CEMENT 1101 | 1671 | CALAVERAS CEMENT 110136880 | 0.038594 | 167.6187 | 5.7748 | 0 | 5.7748 | 0 | 466 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 1 | 859 |  | 157 | 104 | 859 | 157 | 104 | 292.4 | 0.00023025 | 8e-05 | 1860 | 0.023023 | 0.00034883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.023023 | 27.187 | 27.187 | 0%
Central Valley | YO_Yosemite | SAN JOAQUIN NO3 1101 | 1564 | SAN JOAQUIN #3 1101673480 | 0.19668 | 293.3576 | 13.7824 | 0.42557 | 13.3568 | 12.5275 | 4153 | 13 | 13 | 2 | 0 | 0 | 0 | 732 | 0.091053 | 701 |  | 137 | 84 | 688 | 137 | 84 | 249.61 | 0.00067045 | 0.00019 | 1861 | 0.013862 | 0.00034655 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.013434 | 10.2569 | 9.9402 | 3.088%
North Valley | NV_North Valley | BURNEY 1101 | 7916 | BURNEY 11029042 | 0.024898 | 39.2141 | 1.9595 | 0 | 1.9595 | 0 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 1 | 283 |  | 53 | 36 | 283 | 53 | 36 | 98.08 | 0.00063493 | 7e-05 | 1862 | 0.016269 | 0.00034614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.016269 | 27.0481 | 27.0481 | 0%
Central Coast | CC_Central Coast | POINT MORETTI 1101 | 3867 | POINT MORETTI 110112122 | 0.054471 | 123.9622 | 4.8723 | 0 | 4.8723 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 1 | 4007 |  | 725 | 478 | 4007 | 725 | 478 | 1353.88 | 0.00043942 | 0.00066 | 1863 | 0.010034 | 0.00034598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.010034 | 148.7989 | 148.7989 | 0%
Central Valley | ST_Stockton | SALT SPRINGS 2102 | 9051 | SALT SPRINGS 21028442 | 0.087757 | 249.5436 | 11.8413 | 0 | 11.8413 | 0 | 6804 | 0 | 0 | 0 | 0 | 0 | 0 | 317 | 1 | 12368 |  | 2233 | 1472 | 12368 | 2233 | 1472 | 4172.33 | 0.00035167 | 0.00163 | 1864 | 0.067574 | 0.00034477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.067574 | 188.5775 | 188.5775 | 0%
North Valley | NV_North Valley | RISING RIVER 1101 | 856 | RISING RIVER 1101circuit_breaker | 0.08614 | 216.4819 | 9.9153 | 0 | 9.9153 | 0 | 1147 | 0 | 0 | 0 | 0 | 0 | 0 | 227 | 1 | 2095 |  | 380 | 251 | 2095 | 380 | 251 | 709.15 | 0.00039791 | 0.00031 | 1865 | 0.026339 | 0.00034206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.026339 | 38.3245 | 38.3245 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2106 | 3703 | CAMP EVERS 210612518 | 0.1616 | 358.6804 | 15.7926 | 0 | 15.7926 | 0.93769 | 8847 | 300 | 298 | 243 | 0 | 0 | 0 | 924 | 0.94062 | 15424 |  | 3027 | 2042 | 15124 | 3027 | 2042 | 5508.15 | 0.00045054 | 0.00284 | 1866 | 0.091732 | 0.00033975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.091732 | 191.6719 | 191.6719 | 0%
Central Coast | CC_Central Coast | OTTER 1102 | 5879 | OTTER 110263868 | 0.14782 | 346.2949 | 15.1142 | 0 | 15.1142 | 0 | 3906 | 0 | 0 | 0 | 0 | 0 | 0 | 273 | 1 | 7105 |  | 1283 | 846 | 7105 | 1283 | 846 | 2397.16 | 0.00042686 | 0.00114 | 1867 | 0.065133 | 0.00033923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.065133 | 84.887 | 84.887 | 0%
North Valley | NV_North Valley | CLARK ROAD 1102 | 6299 | CLARK ROAD 110247006 | 0.019979 | 149.5323 | 5.6358 | 4.1758 | 1.4598 | 5.6356 | 471 | 694 | 235 | 208 | 166 | 154 | 0 | 317 | 3.3606e-05 | 694 |  | 235 | 208 | 0 | 69 | 54 | 94.53 | 0.00013361 | 2e-05 | 1869 | 0.01111 | 0.00033666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0028778 | 47.2652 | 41.6978 | 74.09%
Central Coast | LP_Los Padres | OCEANO 1102 | 3017 | V50 | 0.084549 | 181.7178 | 7.442 | 0 | 7.442 | 0 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 178 | 1 | 1047 |  | 191 | 127 | 1047 | 191 | 127 | 355.9 | 0.00046528 | 0.00018 | 1870 | 0.027081 | 0.00033026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.027081 | 25.665 | 25.665 | 0%
North Valley | NV_North Valley | RISING RIVER 1101 | 6009 | RISING RIVER 11019032 | 0.10915 | 468.7372 | 22.135 | 0 | 22.135 | 0 | 6248 | 0 | 0 | 0 | 0 | 0 | 0 | 488 | 1 | 11358 |  | 2050 | 1352 | 11358 | 2050 | 1352 | 3830.72 | 0.00023287 | 0.00099 | 1871 | 0.062709 | 0.00032832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.062709 | 92.6133 | 92.6133 | 0%
Central Valley | YO_Yosemite | MIWUK 1702 | 8659 | MIWUK 17021808 | 0.01772 | 108.6832 | 5.8665 | 0.20341 | 5.6629 | 1.3432 | 3001 | 649 | 159 | 111 | 81 | 52 | 0 | 625 | 0.77104 | 4860 |  | 920 | 613 | 4211 | 839 | 561 | 1528.42 | 0.00016304 | 0.00028 | 1872 | 0.0098005 | 0.00032668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0094603 | 148.1579 | 156.8232 | 3.467%
Sierra | SI_Sierra | PLACERVILLE 1111 | 4307 | PLACERVILLE 11118582 | 0.11696 | 210.1822 | 9.5286 | 0.12746 | 9.4011 | 0.32216 | 1123 | 181 | 105 | 102 | 105 | 102 | 0 | 268 | 0.96619 | 2163 |  | 464 | 340 | 1982 | 359 | 238 | 670.21 | 0.00055646 | 0.00042 | 1873 | 0.046977 | 0.00032398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.046348 | 38.1869 | 48.6955 | 1.338%
North Coast | SO_Sonoma | MONTE RIO 1112 | 7385 | MONTE RIO 111215401 | 0.45154 | 31.378 | 1.5373 | 0 | 1.5373 | 0 | 1006 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 1 | 1839 |  | 334 | 221 | 1839 | 334 | 221 | 623.09 | 0.01439 | 0.00999 | 1874 | 0.0045303 | 0.00032359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 4. >30 - 40% | 0.0045303 | 217.2625 | 217.2625 | 0%
Central Valley | YO_Yosemite | CURTIS 1703 | 588 | CURTIS 170356972 | 0.025383 | 183.3283 | 7.7286 | 4.9411 | 2.7875 | 7.2242 | 519 | 886 | 120 | 60 | 92 | 42 | 0 | 215 | 0.065258 | 948 |  | 131 | 68 | 62 | 39 | 26 | 59.01 | 0.00013846 | 1e-05 | 1875 | 0.0061394 | 0.00032313 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0022143 | 13.991 | 16.95 | 63.93%
Central Valley | YO_Yosemite | RACETRACK 1703 | 106 | RACETRACK 17038120 | 0.10385 | 196.067 | 7.2814 | 0.17841 | 7.1032 | 2.4129 | 2594 | 496 | 470 | 128 | 31 | 27 | 0 | 371 | 0.66863 | 3654 |  | 1041 | 505 | 3158 | 1010 | 478 | 1667.92 | 0.00052966 | 0.00111 | 1876 | 0.043341 | 0.00031868 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.04228 | 142.189 | 142.9662 | 2.45%
Central Coast | CC_Central Coast | CAMP EVERS 2103 | 1334 | CAMP EVERS 21035753 | 0.000122 | 32.7421 | 1.9481 | 0 | 1.9481 | 0 | 1062 | 0 | 0 | 0 | 0 | 0 | 0 | 204 | 1 | 1941 |  | 352 | 233 | 1941 | 352 | 233 | 656.93 | 3.7261e-06 | 0 | 1877 | 0.013054 | 0.00031839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.013054 | 180.6883 | 180.6883 | 0%
Central Valley | YO_Yosemite | PEORIA 1705 | 1168 | PEORIA 170575274 | 6.6e-05 | 11.2062 | 0.33977 | 0 | 0.33977 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 38 |  | 9 | 7 | 38 | 9 | 7 | 15.75 | 5.8896e-06 | 0 | 1878 | 0.0025458 | 0.00031822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0025458 | 26.4883 | 26.4883 | 0%
North Coast | HU_Humboldt | NEWBURG 1131 | 2145 | NEWBURG 1131circuit_breaker | 0.017291 | 78.6711 | 3.2 | 0.079167 | 3.121 | 3.2 | 1026 | 2481 | 467 | 231 | 1 | 1 | 0 | 72 | 0 | 2481 |  | 467 | 231 | 0 | 466 | 230 | 638.42 | 0.00021979 | 0.00021 | 1879 | 0.012925 | 0.00031524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.012606 | 149.31 | 145.9375 | 2.474%
Bay Area | EB_East Bay | EL CERRITO G 1105 | 3139 | EL CERRITO G 1105BR160 | 0.035304 | 136.7535 | 8.3634 | 0 | 8.3634 | 0 | 2043 | 0 | 0 | 0 | 0 | 0 | 0 | 290 | 1 | 3722 |  | 673 | 444 | 3722 | 673 | 444 | 1256.99 | 0.00025816 | 0.00036 | 1880 | 0.036383 | 0.00031365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.036383 | 80.4692 | 80.4692 | 0%
Bay Area | EB_East Bay | FRANKLIN 1104 | 9522 | FRANKLIN 1104P146 | 0.014214 | 96.0512 | 3.6934 | 0 | 3.6934 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 1 | 163 |  | 31 | 22 | 163 | 31 | 22 | 57.14 | 0.00014798 | 1e-05 | 1881 | 0.0093569 | 0.0003119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0093569 | 8.3934 | 8.3934 | 0%
Central Valley | YO_Yosemite | CURTIS 1705 | 3679 | CURTIS 170510590 | 0.06641 | 208.8304 | 8.9854 | 4.2443 | 4.7411 | 8.9006 | 2383 | 3944 | 1628 | 904 | 1331 | 798 | 0 | 421 | 0.0094429 | 3985 |  | 1635 | 909 | 41 | 304 | 111 | 420.17 | 0.00031801 | 0.0002 | 1882 | 0.042297 | 0.0003065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.022318 | 64.1202 | 181.9615 | 47.24%
Central Coast | LP_Los Padres | FOOTHILL 1102 | 7983 | FOOTHILL 1102circuit_breaker | 0.46698 | 228.3009 | 8.496 | 0 | 8.496 | 0 | 441 | 0 | 0 | 0 | 0 | 0 | 0 | 165 | 1 | 813 |  | 149 | 99 | 813 | 149 | 99 | 277.3 | 0.0020454 | 0.00063 | 1883 | 0.021441 | 0.0003063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.021441 | 17.5376 | 17.5376 | 0%
Bay Area | PE_Peninsula | HALF MOON BAY 1103 | 1950 | HALF MOON BAY 110369412 | 0.055158 | 282.2914 | 15.3511 | 7.4652 | 7.8858 | 9.4801 | 4434 | 713 | 246 | 39 | 144 | 33 | 0 | 479 | 0.38245 | 3797 |  | 803 | 406 | 3084 | 659 | 373 | 1180.39 | 0.00019539 | 0.00027 | 1884 | 0.043116 | 0.00030578 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.022148 | 83.568 | 52.3088 | 48.63%
North Valley | NV_North Valley | FRENCH GULCH 1101 | 6835 | FRENCH GULCH 11012905 | 0.045047 | 218.5164 | 9.4788 | 0 | 9.4788 | 0 | 1693 | 0 | 0 | 0 | 0 | 0 | 0 | 188 | 1 | 3087 |  | 559 | 369 | 3087 | 559 | 369 | 1043.66 | 0.00020615 | 0.00024 | 1885 | 0.035126 | 0.00030544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.035126 | 58.9738 | 58.9738 | 0%
Sierra | SI_Sierra | HIGGINS 1103 | 5585 | HIGGINS 1103995672 | 0.011071 | 52.2845 | 2.0169 | 0 | 2.0169 | 0 | 790 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 1 | 1447 |  | 263 | 174 | 1447 | 263 | 174 | 490.54 | 0.00021175 | 0.00012 | 1886 | 0.017077 | 0.00030495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.017077 | 130.401 | 130.401 | 0%
Central Coast | SJ_San Jose | LLAGAS 2101 | 4424 | LLAGAS 21011449 | 0.056932 | 185.2829 | 10.3081 | 0 | 10.3081 | 0 | 569 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 1 | 1046 |  | 191 | 126 | 1046 | 191 | 126 | 355.81 | 0.00030727 | 0.00012 | 1887 | 0.030034 | 0.00030337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.030034 | 18.529 | 18.529 | 0%
Central Coast | LP_Los Padres | OCEANO 1104 | 2244 | OCEANO 1104circuit_breaker | 0.081012 | 230.9062 | 7.267 | 0 | 7.267 | 0 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 289 | 1 | 237 |  | 45 | 30 | 237 | 45 | 30 | 82.98 | 0.00035084 | 3e-05 | 1888 | 0.016646 | 0.00030266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.016646 | 6.1923 | 6.1923 | 0%
North Valley | NV_North Valley | KANAKA 1101 | 3281 | KANAKA 11011406 | 0.18602 | 585.68 | 27.0396 | 0 | 27.0396 | 0 | 4880 | 0 | 0 | 0 | 0 | 0 | 0 | 534 | 1 | 8874 |  | 1602 | 1056 | 8874 | 1602 | 1056 | 2993.4 | 0.00031762 | 0.00106 | 1889 | 0.10795 | 0.00030238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.10795 | 59.2465 | 59.2465 | 0%
Central Valley | YO_Yosemite | MIWUK 1701 | 580 | MIWUK 170110600 | 0.052519 | 145.4356 | 10.4055 | 0.0039773 | 10.4015 | 0.072348 | 5075 | 92 | 4 | 0 | 0 | 0 | 0 | 741 | 0.99305 | 9256 |  | 1659 | 1091 | 9164 | 1659 | 1091 | 3097.59 | 0.00036112 | 0.00125 | 1890 | 0.040795 | 0.00030219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.040779 | 159.496 | 159.435 | 0.03822%
Sierra | SI_Sierra | DIAMOND SPRINGS 1104 | 2132 | DIAMOND SPRINGS 1104circuit_breaker | 0.051691 | 129.1613 | 5.6674 | 0 | 5.6674 | 0 | 1354 | 0 | 0 | 0 | 0 | 0 | 0 | 158 | 1 | 2471 |  | 448 | 296 | 2471 | 448 | 296 | 836.15 | 0.0004002 | 0.00037 | 1891 | 0.023684 | 0.00029979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.023684 | 79.0483 | 79.0483 | 0%
North Coast | HU_Humboldt | ELK 1101 | 1680 | ELK 110191336 | 0.070717 | 241.8361 | 8.7881 | 0 | 8.7881 | 0 | 5225 | 0 | 0 | 0 | 0 | 0 | 0 | 169 | 1 | 9501 |  | 1715 | 1131 | 9501 | 1715 | 1131 | 3204.64 | 0.00029242 | 0.00104 | 1892 | 0.02904 | 0.00029938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.02904 | 195.151 | 195.151 | 0%
North Coast | HU_Humboldt | FORT BRAGG A 1101 | 1791 | FORT BRAGG A 11014622 | 0.064967 | 395.1521 | 14.0843 | 0 | 14.0843 | 0 | 3215 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 1 | 5851 |  | 1057 | 697 | 5851 | 1057 | 697 | 1974.68 | 0.00016441 | 0.00036 | 1893 | 0.049687 | 0.00029753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.049687 | 75.0482 | 75.0482 | 0%
Central Valley | YO_Yosemite | MARIPOSA 2101 | 4077 | MARIPOSA 210110170 | 0.13105 | 407.5937 | 15.1229 | 9.3852 | 5.7375 | 14.9608 | 5203 | 7862 | 2192 | 1542 | 1862 | 1337 | 0 | 695 | 0.01072 | 7963 |  | 2210 | 1554 | 101 | 348 | 217 | 485.85 | 0.00032152 | 0.00023 | 1894 | 0.05292 | 0.0002973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.020077 | 60.6536 | 146.1358 | 62.06%
North Coast | SO_Sonoma | MONTE RIO 1111 | 3431 | MONTE RIO 1111256 | 0.1216 | 204.0486 | 9.6958 | 0.38826 | 9.3076 | 9.5258 | 5142 | 2930 | 1793 | 626 | 277 | 6 | 0 | 754 | 0.017541 | 3094 |  | 1823 | 646 | 164 | 1546 | 640 | 2132.78 | 0.00059594 | 0.00192 | 1895 | 0.024513 | 0.00029534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.023532 | 166.1013 | 188.0189 | 4.004%
Central Coast | LP_Los Padres | FOOTHILL 1101 | 6315 | FOOTHILL 1101549904 | 0.074501 | 176.1113 | 6.4286 | 0 | 6.4286 | 0 | 223 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 1 | 417 |  | 77 | 52 | 417 | 77 | 52 | 143.02 | 0.00042303 | 7e-05 | 1896 | 0.0020549 | 0.00029356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0020549 | 11.9777 | 11.9777 | 0%
Central Valley | ST_Stockton | PINE GROVE 1101 | 3533 | PINE GROVE 11013166 | 0.057895 | 227.8861 | 10.1676 | 0 | 10.1676 | 0 | 2534 | 0 | 0 | 0 | 0 | 0 | 0 | 243 | 1 | 4614 |  | 834 | 550 | 4614 | 834 | 550 | 1557.84 | 0.00025405 | 0.00044 | 1897 | 0.054521 | 0.00029156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.054521 | 82.0251 | 82.0251 | 0%
North Valley | NV_North Valley | VOLTA 1102 | 9034 | VOLTA 110280982 | 0.012577 | 10.8666 | 0.52576 | 0 | 0.52576 | 0 | 471 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 1 | 868 |  | 158 | 105 | 868 | 158 | 105 | 294.58 | 0.0011574 | 0.00038 | 1898 | 0.0026237 | 0.00029152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0026237 | 300.5187 | 300.5187 | 0%
North Coast | HU_Humboldt | KONOCTI 1108 | 3214 | KONOCTI 1108circuit_breaker | 0.062274 | 110.5276 | 5.7458 | 0 | 5.7458 | 0 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 1 | 357 |  | 66 | 45 | 357 | 66 | 45 | 122.55 | 0.00056342 | 8e-05 | 1899 | 0.01454 | 0.0002908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.01454 | 11.4866 | 11.4866 | 0%
Central Coast | CC_Central Coast | RESERVATION ROAD 1102 | 4408 | RESERVATION ROAD 1102circuit_breaker | 0.047593 | 200.8658 | 8.3597 | 0 | 8.3597 | 0 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 166 | 1 | 385 |  | 71 | 48 | 385 | 71 | 48 | 131.92 | 0.00023694 | 3e-05 | 1900 | 0.021173 | 0.00029004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.021173 | 8.4932 | 8.4932 | 0%
Central Coast | SJ_San Jose | SWIFT 2102 | 1988 | SWIFT 2102circuit_breaker | 0.003203 | 14.5416 | 0.50341 | 0 | 0.50341 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 61 |  | 13 | 10 | 61 | 13 | 10 | 23.3 | 0.00022027 | 1e-05 | 1901 | 0.00086869 | 0.00028956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00086869 | 25.8239 | 25.8239 | 0%
Sierra | SI_Sierra | BRUNSWICK 1105 | 3543 | BRUNSWICK 110532536 | 0.16662 | 532.1001 | 21.9136 | 0.15625 | 21.7574 | 5.0812 | 16235 | 744 | 569 | 520 | 195 | 186 | 0 | 1659 | 0.76812 | 23399 |  | 4656 | 3213 | 22655 | 4461 | 3027 | 8150.52 | 0.00031314 | 0.0029 | 1903 | 0.087446 | 0.0002886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.086822 | 205.0338 | 212.4704 | 0.713%
North Coast | HU_Humboldt | REDBUD 1101 | 6525 | REDBUD 1101400 | 0.017392 | 31.2915 | 1.5045 | 0.62045 | 0.8839 | 1.4064 | 142 | 329 | 86 | 54 | 37 | 16 | 0 | 83 | 0.065206 | 347 |  | 89 | 56 | 18 | 52 | 40 | 72.86 | 0.00055581 | 6e-05 | 1904 | 0.003704 | 0.00028492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.002176 | 58.8301 | 59.1541 | 41.24%
Central Coast | CC_Central Coast | OTTER 1102 | 8487 | OTTER 11022166 | 0.028636 | 89.3314 | 3.0661 | 0 | 3.0661 | 0 | 1422 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 1 | 2595 |  | 470 | 310 | 2595 | 470 | 310 | 877.45 | 0.00032056 | 0.00031 | 1905 | 0.019283 | 0.00028357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.019283 | 153.2893 | 153.2893 | 0%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1107 | 4931 | SAN LUIS OBISPO 1107V18 | 0.009068 | 65.4317 | 2.5782 | 0 | 2.5782 | 0 | 166 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 1 | 314 |  | 59 | 39 | 314 | 59 | 39 | 109.09 | 0.00013859 | 2e-05 | 1906 | 0.0070877 | 0.00028351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0070877 | 22.884 | 22.884 | 0%
Central Valley | YO_Yosemite | MARIPOSA 2101 | 1005 | MARIPOSA 2101439030 | 0.19174 | 484.5686 | 18.8519 | 0.00625 | 18.8456 | 18.6398 | 3773 | 493 | 448 | 92 | 334 | 66 | 0 | 1014 | 0.011252 | 570 |  | 462 | 101 | 77 | 128 | 35 | 182.29 | 0.0003957 | 0.00011 | 1907 | 0.007278 | 0.00027992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0072756 | 6.792 | 24.5068 | 0.03315%
North Valley | NV_North Valley | VOLTA 1102 | 2060 | VOLTA 11021648 | 0.001011 | 78.6687 | 3.704 | 0 | 3.704 | 0 | 2535 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 1 | 4616 |  | 834 | 551 | 4616 | 834 | 551 | 1558.02 | 1.2851e-05 | 2e-05 | 1908 | 0.011194 | 0.00027985 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.011194 | 225.1634 | 225.1634 | 0%
Central Coast | CC_Central Coast | BIG BASIN 1101 | 3882 | BIG BASIN 110112838 | 0.003796 | 32.1479 | 1.4756 | 0 | 1.4756 | 0.89167 | 841 | 135 | 135 | 81 | 0 | 0 | 0 | 95 | 0.39571 | 744 |  | 246 | 154 | 609 | 246 | 154 | 391.83 | 0.00011808 | 6e-05 | 1909 | 0.0089004 | 0.00027814 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0089004 | 166.7154 | 166.7154 | 0%
Central Valley | ST_Stockton | FROGTOWN 1702 | 5401 | FROGTOWN 170236870 | 0.021088 | 37.0697 | 2.4773 | 0 | 2.4773 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 1 | 150 |  | 29 | 20 | 150 | 29 | 20 | 53.23 | 0.00056887 | 3e-05 | 1910 | 0.0027611 | 0.00027611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0027611 | 11.7064 | 11.7064 | 0%
Central Valley | YO_Yosemite | MERCED FALLS 1102 | 1160 | MERCED FALLS 1102circuit_breaker | 0.019617 | 169.2744 | 8.6513 | 8.6513 | 0 | 8.6513 | 90 | 138 | 31 | 16 | 30 | 15 | 0 | 177 | 0 | 138 |  | 31 | 16 | 0 | 1 | 1 | 1.37 | 0.00011589 | 0 | 1911 | 0.0046872 | 0.00027572 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 3.5833 | 100%
North Valley | NV_North Valley | PIT NO 5 1101 | 2811 | PIT NO 5 11011660 | 0.021337 | 104.385 | 5.0561 | 0 | 5.0561 | 0 | 2331 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 1 | 4245 |  | 768 | 507 | 4245 | 768 | 507 | 1434.21 | 0.00020441 | 0.00033 | 1912 | 0.018465 | 0.00027559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.018465 | 151.8969 | 151.8969 | 0%
Central Valley | YO_Yosemite | PEORIA 1704 | 7605 | PEORIA 1704circuit_breaker | 0.059272 | 182.1739 | 8.4436 | 7.2081 | 1.2354 | 8.4436 | 120 | 431 | 190 | 164 | 147 | 124 | 0 | 152 | 0 | 431 |  | 190 | 164 | 0 | 43 | 40 | 58.91 | 0.00032536 | 3e-05 | 1913 | 0.0090534 | 0.00027435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0013246 | 34.8061 | 22.5024 | 85.37%
Bay Area | NB_North Bay | SAN RAFAEL 1108 | 3890 | SAN RAFAEL 1108322 | 0.000196 | 94.9544 | 5.2358 | 0 | 5.2358 | 0 | 1315 | 0 | 0 | 0 | 0 | 0 | 0 | 197 | 1 | 2400 |  | 435 | 287 | 2400 | 435 | 287 | 811.95 | 2.0641e-06 | 0 | 1914 | 0.026007 | 0.00027091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.026007 | 83.0819 | 83.0819 | 0%
Central Valley | YO_Yosemite | SPRING GAP 1702 | 1639 | 9690 | 0.065868 | 276.2213 | 16.1985 | 0 | 16.1985 | 0 | 8089 | 0 | 0 | 0 | 0 | 0 | 0 | 436 | 1 | 14702 |  | 2653 | 1749 | 14702 | 2653 | 1749 | 4957.79 | 0.00023846 | 0.00132 | 1915 | 0.064438 | 0.00027075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.064438 | 163.7808 | 163.7808 | 0%
Bay Area | PE_Peninsula | HALF MOON BAY 1103 | 6607 | HALF MOON BAY 110398440 | 0.04819 | 195.4028 | 8.1379 | 0 | 8.1379 | 0 | 4872 | 0 | 0 | 0 | 0 | 0 | 0 | 295 | 1 | 8860 |  | 1600 | 1055 | 8860 | 1600 | 1055 | 2989.4 | 0.00024662 | 0.00082 | 1916 | 0.032267 | 0.00026889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.032267 | 196.6114 | 196.6114 | 0%
Central Coast | DA_De Anza | LOS GATOS 1106 | 4121 | LOS GATOS 1106LA64 | 0.042542 | 275.0055 | 11.635 | 0 | 11.635 | 0.024242 | 5413 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 0.99792 | 9822 |  | 1773 | 1169 | 9822 | 1773 | 1169 | 3312.99 | 0.0001547 | 0.00057 | 1917 | 0.056688 | 0.00026739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.056688 | 152.3845 | 152.3845 | 0%
Bay Area | PE_Peninsula | SNEATH LANE 1106 | 3239 | SNEATH LANE 1106circuit_breaker | 0.006697 | 31.1556 | 2.9261 | 0 | 2.9261 | 0 | 347 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 1 | 642 |  | 118 | 79 | 642 | 118 | 79 | 219.44 | 0.00021495 | 5e-05 | 1918 | 0.0053163 | 0.00026582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0053163 | 40.3262 | 40.3262 | 0%
North Coast | HU_Humboldt | WILLOW CREEK 1103 | 2036 | WILLOW CREEK 11032936 | 0.16622 | 654.9955 | 32.3398 | 0.087121 | 32.2528 | 7.5352 | 11152 | 1319 | 1319 | 127 | 131 | 11 | 0 | 902 | 0.767 | 16861 |  | 4124 | 1975 | 15542 | 3993 | 1964 | 6869.19 | 0.00025377 | 0.00211 | 1919 | 0.10465 | 0.00026562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.10437 | 123.803 | 127.521 | 0.2694%
North Valley | NV_North Valley | PIT NO 3 2101 | 7598 | PIT NO 3 2101circuit_breaker | 0.033845 | 135.0015 | 6.6002 | 0 | 6.6002 | 0 | 3466 | 0 | 0 | 0 | 0 | 0 | 0 | 192 | 1 | 6306 |  | 1139 | 751 | 6306 | 1139 | 751 | 2127.97 | 0.0002507 | 0.00059 | 1920 | 0.024694 | 0.00026552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.024694 | 172.5708 | 172.5708 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2106 | 4066 | CAMP EVERS 210610718 | 0.10273 | 188.6706 | 8.011 | 0 | 8.011 | 0 | 2726 | 0 | 0 | 0 | 0 | 0 | 0 | 493 | 1 | 4963 |  | 897 | 592 | 4963 | 897 | 592 | 1675.56 | 0.0005445 | 0.00102 | 1921 | 0.037016 | 0.0002644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.037016 | 111.9713 | 111.9713 | 0%
Central Valley | YO_Yosemite | MIWUK 1701 | 2108 | MIWUK 170153038 | 0.024692 | 101.5258 | 5.5119 | 0 | 5.5119 | 0 | 3356 | 0 | 0 | 0 | 0 | 0 | 0 | 454 | 1 | 6107 |  | 1103 | 728 | 6107 | 1103 | 728 | 2060.74 | 0.00024321 | 0.00056 | 1922 | 0.027105 | 0.00026316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.027105 | 200.1113 | 200.1113 | 0%
Central Coast | CC_Central Coast | PAUL SWEET 2106 | 6723 | PAUL SWEET 2106428102 | 0.074249 | 290.4937 | 12.0784 | 0 | 12.0784 | 0 | 4487 | 0 | 0 | 0 | 0 | 0 | 0 | 309 | 1 | 8161 |  | 1474 | 972 | 8161 | 1474 | 972 | 2753.87 | 0.0002556 | 0.00078 | 1923 | 0.048126 | 0.00026155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.048126 | 122.0359 | 122.0359 | 0%
Bay Area | MI_Mission | CASTRO VALLEY 1108 | 6523 | CASTRO VALLEY 110810315 | 0.04482 | 137.4488 | 5.2642 | 0.55549 | 4.7087 | 5.2642 | 1178 | 520 | 124 | 76 | 3 | 2 | 0 | 286 | 0 | 520 |  | 124 | 76 | 0 | 121 | 74 | 165.77 | 0.00032609 | 8e-05 | 1924 | 0.023983 | 0.00026069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.021452 | 25.697 | 23.5553 | 10.55%
Bay Area | NB_North Bay | STAFFORD 1102 | 3207 | STAFFORD 1101circuit_breaker | 0.003731 | 38.9808 | 1.2559 | 0 | 1.2559 | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 1 | 172 |  | 33 | 23 | 172 | 33 | 23 | 60.69 | 9.5714e-05 | 1e-05 | 1925 | 0.0046746 | 0.0002597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0046746 | 26.2766 | 26.2766 | 0%
Central Valley | YO_Yosemite | CURTIS 1704 | 2907 | CURTIS 1704803 | 0.034741 | 196.8955 | 8.242 | 4.4415 | 3.8006 | 8.1085 | 1626 | 2530 | 1147 | 836 | 1129 | 830 | 0 | 309 | 0.0162 | 2578 |  | 1156 | 842 | 48 | 27 | 12 | 41.31 | 0.00017644 | 1e-05 | 1926 | 0.035133 | 0.00025459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.016201 | 7.1042 | 140.2564 | 53.89%
North Coast | HU_Humboldt | ARCATA 1122 | 7028 | ARCATA 11224218 | 0.05526 | 133.1021 | 4.9011 | 0 | 4.9011 | 0 | 1178 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1 | 2151 |  | 390 | 258 | 2151 | 390 | 258 | 727.89 | 0.00041517 | 0.00034 | 1927 | 0.022605 | 0.00025399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.022605 | 79.5734 | 79.5734 | 0%
Central Coast | CC_Central Coast | SAN BENITO 2104 | 2063 | SAN BENITO 210488772 | 0.68217 | 576.3932 | 49.5723 | 2.2634 | 47.3089 | 2.9095 | 2861 | 636 | 229 | 122 | 228 | 122 | 0 | 1512 | 0.94131 | 5538 |  | 1115 | 706 | 4902 | 887 | 584 | 1656.37 | 0.0011835 | 0.00218 | 1928 | 0.031685 | 0.00025348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.030238 | 18.7491 | 22.4924 | 4.566%
Central Valley | FR_Fresno | AUBERRY 1101 | 3745 | AUBERRY 1101D4982 | 0.019249 | 76.2745 | 2.847 | 0 | 2.847 | 2.8441 | 1092 | 29 | 29 | 27 | 0 | 0 | 0 | 146 | 0.00099787 | 31 |  | 29 | 27 | 2 | 29 | 27 | 39.91 | 0.00025236 | 2e-05 | 1929 | 0.010392 | 0.00025346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.010392 | 10.1863 | 10.1863 | 0%
Central Valley | YO_Yosemite | CURTIS 1703 | 3507 | CURTIS 17039330 | 0.26251 | 939.9333 | 37.8989 | 14.7057 | 23.1932 | 37.7807 | 10911 | 19782 | 3772 | 2749 | 2867 | 2007 | 0 | 1300 | 0.0031183 | 19844 |  | 3783 | 2756 | 62 | 916 | 749 | 1260.5 | 0.00027929 | 0.00053 | 1930 | 0.028092 | 0.00025082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.017192 | 39.4944 | 99.8183 | 38.8%
Bay Area | DI_Diablo | ALHAMBRA 1105 | 4938 | ALHAMBRA 110581514 | 0.062906 | 79.9854 | 3.7136 | 0 | 3.7136 | 0 | 714 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 1 | 1309 |  | 238 | 158 | 1309 | 238 | 158 | 443.87 | 0.00078647 | 0.00039 | 1931 | 0.013281 | 0.00025058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.013281 | 64.0881 | 64.0881 | 0%
Central Valley | YO_Yosemite | MIWUK 1702 | 5765 | MIWUK 17029270 | 0.018479 | 132.7046 | 5.7619 | 0.90473 | 4.8572 | 2.3979 | 1070 | 597 | 271 | 216 | 144 | 102 | 0 | 300 | 0.58383 | 1739 |  | 478 | 353 | 1142 | 334 | 251 | 560.36 | 0.00013925 | 0.0001 | 1932 | 0.020886 | 0.00024864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.017607 | 68.7639 | 82.9583 | 15.7%
Central Valley | YO_Yosemite | CURTIS 1703 | 3219 | CURTIS 170390320 | 0.08326 | 666.8037 | 26.9638 | 10.9545 | 16.0093 | 26.2778 | 5636 | 9325 | 1598 | 776 | 1417 | 676 | 0 | 872 | 0.025441 | 9586 |  | 1645 | 807 | 261 | 228 | 131 | 335.85 | 0.00012486 | 6e-05 | 1933 | 0.0024817 | 0.00024817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0014734 | 14.2417 | 61.0077 | 40.63%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1101 | 1538 | SAN LUIS OBISPO 1101483444 | 0.016705 | 50.8727 | 2.2157 | 0 | 2.2157 | 0 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 1 | 279 |  | 52 | 35 | 279 | 52 | 35 | 96.35 | 0.00032837 | 4e-05 | 1934 | 0.0041987 | 0.00024698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0041987 | 23.4687 | 23.4687 | 0%
Central Coast | CC_Central Coast | ROB ROY 2104 | 986 | ROB ROY 21045082 | 0.11696 | 459.6448 | 19.1182 | 0 | 19.1182 | 0 | 12198 | 0 | 0 | 0 | 0 | 0 | 0 | 430 | 1 | 22163 |  | 3999 | 2635 | 22163 | 3999 | 2635 | 7473.3 | 0.00025447 | 0.00212 | 1935 | 0.085342 | 0.00024665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.085342 | 209.1726 | 209.1726 | 0%
Sierra | SI_Sierra | SHADY GLEN 1101 | 1290 | SHADY GLEN 1101circuit_breaker | 0.000131 | 44.6036 | 2.7945 | 0 | 2.7945 | 0 | 781 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 1 | 1431 |  | 260 | 172 | 1431 | 260 | 172 | 484.99 | 2.937e-06 | 0 | 1936 | 0.012018 | 0.00024526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.012018 | 93.0396 | 93.0396 | 0%
North Coast | HU_Humboldt | BIG RIVER 1101 | 6067 | BIG RIVER 11011052 | 0.012691 | 55.5263 | 3.4816 | 0 | 3.4816 | 0 | 919 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 1 | 1681 |  | 305 | 202 | 1681 | 305 | 202 | 569.14 | 0.00022856 | 0.00014 | 1937 | 0.0094083 | 0.00024124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0094083 | 87.6027 | 87.6027 | 0%
Central Coast | LP_Los Padres | SISQUOC 1102 | 4653 | SISQUOC 1102M52 | 0.33794 | 735.4912 | 30.5843 | 29.911 | 0.67311 | 30.5843 | 316 | 851 | 139 | 17 | 139 | 17 | 0 | 649 | 0 | 851 |  | 139 | 17 | 0 | 0 | 0 | 0 | 0.00045948 | 0 | 1938 | 0.021921 | 0.00024089 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00048244 | 0 | 4.5448 | 97.8%
Central Valley | ST_Stockton | CALAVERAS CEMENT 1101 | 3903 | CALAVERAS CEMENT 11011419 | 0.12382 | 368.0238 | 14.9038 | 0 | 14.9038 | 0 | 2121 | 0 | 0 | 0 | 0 | 0 | 0 | 430 | 1 | 3864 |  | 699 | 461 | 3864 | 699 | 461 | 1305.39 | 0.00033645 | 0.00049 | 1939 | 0.046637 | 0.0002404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.046637 | 46.9008 | 46.9008 | 0%
Central Valley | YO_Yosemite | PEORIA 1705 | 894 | PEORIA 170590374 | 0.039285 | 81.3464 | 3.2275 | 0.26326 | 2.9642 | 0.26326 | 273 | 53 | 2 | 2 | 2 | 2 | 0 | 74 | 0.91843 | 520 |  | 88 | 59 | 467 | 86 | 57 | 159.85 | 0.00048293 | 9e-05 | 1940 | 0.014965 | 0.00023753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.013744 | 29.0128 | 27.266 | 8.157%
Bay Area | NB_North Bay | SAUSALITO 1101 | 420 | SAUSALITO 1101circuit_breaker | 0.00644 | 35.5544 | 1.1383 | 0 | 1.1383 | 0 | 181 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1 | 341 |  | 63 | 43 | 341 | 63 | 43 | 117 | 0.00018113 | 2e-05 | 1941 | 0.002605 | 0.00023681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.002605 | 55.3478 | 55.3478 | 0%
North Coast | HU_Humboldt | PHILO 1102 | 2968 | PHILO 11021308 | 0.18226 | 733.3929 | 26.185 | 0 | 26.185 | 0 | 11532 | 0 | 0 | 0 | 0 | 0 | 0 | 414 | 1 | 20954 |  | 3781 | 2492 | 20954 | 3781 | 2492 | 7065.83 | 0.00024852 | 0.00195 | 1943 | 0.086273 | 0.00023444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.086273 | 144.3954 | 144.3954 | 0%
Central Valley | YO_Yosemite | SPRING GAP 1702 | 4093 | 10720 | 0.017683 | 90.0579 | 4.5269 | 0 | 4.5269 | 0 | 2652 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 1 | 4828 |  | 873 | 576 | 4828 | 873 | 576 | 1630.53 | 0.00019635 | 0.00036 | 1944 | 0.014648 | 0.0002325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.014648 | 192.8475 | 192.8475 | 0%
North Coast | HU_Humboldt | NEWBURG 1131 | 8028 | NEWBURG 113190242 | 0.030377 | 75.0331 | 3.5231 | 0.11553 | 3.4078 | 3.4335 | 1976 | 3540 | 850 | 410 | 4 | 2 | 0 | 79 | 0.025427 | 3632 |  | 867 | 421 | 92 | 863 | 419 | 1190.59 | 0.00040485 | 0.00073 | 1945 | 0.014415 | 0.0002325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.013943 | 253.2452 | 246.0897 | 3.279%
Central Coast | CC_Central Coast | BIG BASIN 1101 | 5123 | BIG BASIN 11015000 | 0.022018 | 58.2805 | 2.5195 | 0 | 2.5195 | 1.182 | 1681 | 7 | 7 | 5 | 0 | 0 | 0 | 159 | 0.53086 | 1634 |  | 301 | 199 | 1627 | 301 | 199 | 558.8 | 0.00037779 | 0.00024 | 1946 | 0.0076645 | 0.00023226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0076645 | 119.4678 | 119.4678 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1108 | 1147 | SAN RAFAEL 11081210 | 0.053382 | 87.8525 | 3.932 | 0 | 3.932 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 1 | 2373 |  | 430 | 284 | 2373 | 430 | 284 | 802.67 | 0.00060763 | 0.00054 | 1947 | 0.01134 | 0.00023144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.01134 | 109.3589 | 109.3589 | 0%
Bay Area | NB_North Bay | OLEMA 1101 | 6077 | OLEMA 11011252 | 0.023896 | 91.8515 | 4.339 | 0 | 4.339 | 0 | 1449 | 0 | 0 | 0 | 0 | 0 | 0 | 189 | 1 | 2644 |  | 479 | 316 | 2644 | 479 | 316 | 894.19 | 0.00026016 | 0.00026 | 1948 | 0.015184 | 0.00023006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.015184 | 110.3937 | 110.3937 | 0%
Central Valley | YO_Yosemite | SPRING GAP 1702 | 8427 | 86032 | 0.00134 | 8.9842 | 0.4392 | 0 | 0.4392 | 0 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 539 |  | 99 | 66 | 539 | 99 | 66 | 184.14 | 0.00014915 | 3e-05 | 1949 | 0.0016072 | 0.0002296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0016072 | 225.4075 | 225.4075 | 0%
Bay Area | PE_Peninsula | HALF MOON BAY 1101 | 7045 | HALF MOON BAY 11018902 | 0.083519 | 309.0906 | 15.6146 | 0 | 15.6146 | 0 | 2265 | 0 | 0 | 0 | 0 | 0 | 0 | 309 | 1 | 4125 |  | 746 | 492 | 4125 | 746 | 492 | 1393.27 | 0.00027021 | 0.00042 | 1950 | 0.025359 | 0.00022846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.025359 | 47.7759 | 47.7759 | 0%
Central Valley | YO_Yosemite | INDIAN FLAT 1104 | 6538 | INDIAN FLAT 110410270 | 0.019702 | 90.2269 | 3.4373 | 0 | 3.4373 | 0 | 722 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 1 | 1323 |  | 241 | 159 | 1323 | 241 | 159 | 449.24 | 0.00021836 | 0.00011 | 1951 | 0.0075315 | 0.00022823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0075315 | 70.113 | 70.113 | 0%
Sierra | SI_Sierra | WEIMAR 1101 | 455 | WEIMAR 11012084 | 0.08435 | 447.494 | 19.0146 | 0 | 19.0146 | 0 | 6999 | 0 | 0 | 0 | 0 | 0 | 0 | 465 | 1 | 12722 |  | 2296 | 1514 | 12722 | 2296 | 1514 | 4290.5 | 0.00018849 | 0.0009 | 1952 | 0.06799 | 0.00022815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.06799 | 120.7494 | 120.7494 | 0%
Central Valley | ST_Stockton | CALAVERAS CEMENT 1101 | 4997 | CALAVERAS CEMENT 110111236 | 0.11059 | 476.1494 | 20.485 | 0 | 20.485 | 0 | 1266 | 0 | 0 | 0 | 0 | 0 | 0 | 546 | 1 | 2311 |  | 419 | 277 | 2311 | 419 | 277 | 782.02 | 0.00023227 | 0.0002 | 1953 | 0.048303 | 0.00022785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.048303 | 20.454 | 20.454 | 0%
Bay Area | DI_Diablo | MORAGA 1103 | 5710 | MORAGA 1103circuit_breaker | 0.006483 | 36.8892 | 2.0945 | 0.21212 | 1.8824 | 0.3322 | 200 | 59 | 20 | 19 | 20 | 19 | 0 | 87 | 0.8414 | 375 |  | 79 | 58 | 316 | 59 | 39 | 109.27 | 0.00017574 | 2e-05 | 1954 | 0.0050018 | 0.00022735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0044952 | 31.3432 | 37.7177 | 10.13%
Bay Area | NB_North Bay | ALTO 1125 | 1046 | ALTO 11251256 | 0.008707 | 81.3047 | 4.1828 | 0 | 4.1828 | 0 | 636 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 1 | 1167 |  | 212 | 141 | 1167 | 212 | 141 | 395.47 | 0.00010709 | 5e-05 | 1955 | 0.015882 | 0.00022689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.015882 | 50.6842 | 50.6842 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2108 | 875 | TEMPLETON 2108A64 | 0.1159 | 59.4176 | 2.3898 | 0 | 2.3898 | 0 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 1 | 321 |  | 60 | 40 | 321 | 60 | 40 | 111.09 | 0.0019507 | 0.00024 | 1956 | 0.0067619 | 0.0002254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0067619 | 25.107 | 25.107 | 0%
Central Valley | YO_Yosemite | PEORIA 1705 | 6047 | PEORIA 170587222 | 0.34706 | 148.8631 | 6.3886 | 0.076326 | 6.3123 | 0.076326 | 642 | 6 | 0 | 0 | 0 | 0 | 0 | 159 | 0.98805 | 1170 |  | 212 | 140 | 1164 | 212 | 140 | 395.2 | 0.0023314 | 0.00103 | 1957 | 0.014645 | 0.00022531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.01447 | 33.5852 | 33.1839 | 1.195%
Central Coast | CC_Central Coast | CAMP EVERS 2105 | 3012 | CAMP EVERS 210510728 | 0.045777 | 241.4033 | 13.2833 | 0 | 13.2833 | 0 | 4760 | 0 | 0 | 0 | 0 | 0 | 0 | 429 | 1 | 8656 |  | 1563 | 1031 | 8656 | 1563 | 1031 | 2920.35 | 0.00018963 | 0.00062 | 1958 | 0.033956 | 0.00022487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.033956 | 117.6662 | 117.6662 | 0%
North Coast | HU_Humboldt | ELK 1101 | 4596 | ELK 11018779 | 0.009023 | 101.5587 | 2.6064 | 0 | 2.6064 | 0 | 1662 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 1 | 3030 |  | 549 | 362 | 3030 | 549 | 362 | 1024.83 | 8.8845e-05 | 0.0001 | 1959 | 0.015045 | 0.00022455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.015045 | 210.6322 | 210.6322 | 0%
Sierra | SI_Sierra | SPAULDING 1101 | 4002 | SPAULDING 1101578852 | 0.11532 | 517.0685 | 20.558 | 0 | 20.558 | 0 | 5442 | 0 | 0 | 0 | 0 | 0 | 0 | 585 | 1 | 9895 |  | 1787 | 1178 | 9895 | 1787 | 1178 | 3338.74 | 0.00022303 | 0.00083 | 1960 | 0.0398 | 0.00022235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0398 | 86.925 | 86.925 | 0%
Central Coast | SJ_San Jose | MORGAN HILL 2111 | 8152 | MORGAN HILL 21114461 | 0.012975 | 46.7539 | 1.7487 | 0 | 1.7487 | 0 | 914 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 1 | 1672 |  | 304 | 201 | 1672 | 304 | 201 | 566.96 | 0.00027752 | 0.00018 | 1961 | 0.0052714 | 0.00021964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0052714 | 173.846 | 173.846 | 0%
Sierra | SI_Sierra | BRUNSWICK 1110 | 2492 | BRUNSWICK 111061602 | 0.05436 | 244.0776 | 11.5623 | 0.42841 | 11.1337 | 5.1278 | 4150 | 671 | 536 | 294 | 68 | 44 | 0 | 630 | 0.5565 | 4872 |  | 1295 | 794 | 4201 | 1227 | 750 | 2059.08 | 0.00022272 | 0.00057 | 1962 | 0.029644 | 0.00021958 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.028545 | 110.2058 | 112.0018 | 3.705%
Central Coast | CC_Central Coast | ROB ROY 2105 | 1189 | ROB ROY 21055166 | 0.047375 | 133.245 | 5.2083 | 0 | 5.2083 | 0 | 3028 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 1 | 5511 |  | 996 | 657 | 5511 | 996 | 657 | 1860.51 | 0.00035555 | 0.00074 | 1963 | 0.0211 | 0.00021753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0211 | 191.232 | 191.232 | 0%
Central Coast | LP_Los Padres | CAMBRIA 1102 | 58 | CAMBRIA 1102W50 | 0.00272 | 23.0541 | 1.4447 | 0 | 1.4447 | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 1 | 205 |  | 39 | 27 | 205 | 39 | 27 | 71.88 | 0.00011798 | 1e-05 | 1964 | 0.0013024 | 0.00021706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0013024 | 26.9953 | 26.9953 | 0%
North Coast | SO_Sonoma | MONTE RIO 1111 | 572 | MONTE RIO 111123916 | 0.112 | 191.7698 | 7.8735 | 0.0013258 | 7.8722 | 7.8733 | 6330 | 1959 | 1957 | 1104 | 34 | 3 | 0 | 513 | 2.4055e-05 | 1959 |  | 1957 | 1104 | 0 | 1923 | 1101 | 2634.51 | 0.00058404 | 0.00234 | 1965 | 0.016366 | 0.00021535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.016364 | 244.2786 | 248.5558 | 0.01684%
North Coast | SO_Sonoma | MONTE RIO 1112 | 438 | MONTE RIO 1112circuit_breaker | 0.032955 | 117.6611 | 5.9496 | 0.49905 | 5.4506 | 1.2333 | 2435 | 546 | 108 | 31 | 3 | 0 | 0 | 441 | 0.7927 | 4061 |  | 743 | 450 | 3515 | 740 | 450 | 1330.15 | 0.00028008 | 0.00043 | 1966 | 0.011195 | 0.00021528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.010256 | 135.7657 | 124.8819 | 8.388%
Central Valley | YO_Yosemite | PEORIA 1704 | 7490 | PEORIA 1704877670 | 0.030968 | 134.7377 | 5.989 | 3.7008 | 2.2883 | 5.8678 | 88 | 334 | 173 | 163 | 50 | 46 | 0 | 109 | 0.020239 | 337 |  | 174 | 163 | 3 | 124 | 117 | 170.15 | 0.00022984 | 6e-05 | 1967 | 0.004915 | 0.0002137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0018779 | 54.1897 | 29.0532 | 61.79%
Central Valley | FR_Fresno | AUBERRY 1101 | 2991 | AUBERRY 1101R324 | 0.086507 | 250.8926 | 10.8879 | 0.3392 | 10.5489 | 5.3102 | 3430 | 124 | 92 | 44 | 11 | 3 | 0 | 551 | 0.51228 | 3321 |  | 670 | 425 | 3197 | 659 | 422 | 1190.56 | 0.0003448 | 0.00047 | 1968 | 0.030952 | 0.00021346 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.029989 | 62.4712 | 61.5363 | 3.115%
Central Coast | LP_Los Padres | CAYUCOS 1102 | 951 | CAYUCOS 1102circuit_breaker | 0.12749 | 280.6733 | 13.0718 | 0 | 13.0718 | 0 | 1098 | 0 | 0 | 0 | 0 | 0 | 0 | 165 | 1 | 2006 |  | 364 | 241 | 2006 | 364 | 241 | 679.22 | 0.00045422 | 0.00034 | 1969 | 0.016314 | 0.00021187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.016314 | 27.8462 | 27.8462 | 0%
Sierra | SI_Sierra | GRASS VALLEY 1101 | 3406 | GRASS VALLEY 11012208 | 0.079256 | 258.8884 | 11.2237 | 0 | 11.2237 | 0 | 5802 | 0 | 0 | 0 | 0 | 0 | 0 | 309 | 1 | 10549 |  | 1904 | 1255 | 10549 | 1904 | 1255 | 3557.89 | 0.00030614 | 0.00121 | 1970 | 0.038641 | 0.00021115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.038641 | 169.6414 | 169.6414 | 0%
Central Coast | CC_Central Coast | SEACLIFF 0401 | 6585 | SEACLIFF 0401circuit_breaker | 0.052667 | 141.5128 | 4.3777 | 0 | 4.3777 | 0 | 2638 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 1 | 4803 |  | 868 | 573 | 4803 | 868 | 573 | 1621.43 | 0.00037217 | 0.00067 | 1971 | 0.019852 | 0.00020897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.019852 | 198.2798 | 198.2798 | 0%
Bay Area | NB_North Bay | IGNACIO 1101 | 2191 | IGNACIO 11011264 | 0.027712 | 70.0548 | 2.7799 | 0 | 2.7799 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 1 | 154 |  | 30 | 21 | 154 | 30 | 21 | 54.96 | 0.00039558 | 2e-05 | 1972 | 0.0049785 | 0.00020744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0049785 | 10.7917 | 10.7917 | 0%
North Coast | HU_Humboldt | HUMBOLDT BAY 1102 | 1475 | HUMBOLDT BAY 11024724 | 0.031048 | 146.503 | 6.5424 | 0 | 6.5424 | 0 | 3140 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 1 | 5714 |  | 1033 | 681 | 5714 | 1033 | 681 | 1929.47 | 0.00021193 | 0.00046 | 1973 | 0.02261 | 0.00020743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.02261 | 157.8925 | 157.8925 | 0%
North Coast | HU_Humboldt | BIG RIVER 1101 | 6880 | BIG RIVER 110169032 | 0.023736 | 187.552 | 8.3663 | 0 | 8.3663 | 0 | 5020 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 1 | 9128 |  | 1648 | 1087 | 9128 | 1648 | 1087 | 3079.28 | 0.00012656 | 0.00043 | 1974 | 0.030536 | 0.00020633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.030536 | 196.981 | 196.981 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2103 | 4193 | CAMP EVERS 210311056 | 0.008436 | 25.7465 | 1.1981 | 0 | 1.1981 | 0.3178 | 734 | 63 | 63 | 45 | 1 | 1 | 0 | 99 | 0.73475 | 1051 |  | 243 | 164 | 988 | 242 | 163 | 420.46 | 0.00032766 | 0.00016 | 1975 | 0.0047209 | 0.00020526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0047209 | 201.9855 | 202.8201 | 0%
Bay Area | NB_North Bay | STAFFORD 1101 | 1126 | STAFFORD 11011082 | 0.009708 | 22.3501 | 1.4945 | 0 | 1.4945 | 0 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 1 | 290 |  | 54 | 37 | 290 | 54 | 37 | 100.08 | 0.00043436 | 5e-05 | 1976 | 0.0032797 | 0.00020498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0032797 | 36.1323 | 36.1323 | 0%
Central Coast | LP_Los Padres | FOOTHILL 1102 | 2837 | FOOTHILL 110299432 | 0.005001 | 28.5693 | 1.4032 | 0 | 1.4032 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1 | 56 |  | 12 | 9 | 56 | 12 | 9 | 21.48 | 0.00017505 | 0 | 1977 | 0.0020405 | 0.00020405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0020405 | 8.5518 | 8.5518 | 0%
Sierra | SI_Sierra | WISE 1101 | 9699 | WISE 110163199 | 0.020501 | 23.8708 | 0.81269 | 0 | 0.81269 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 92 |  | 19 | 13 | 92 | 19 | 13 | 34.31 | 0.00085883 | 3e-05 | 1978 | 0.001832 | 0.00020355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.001832 | 23.3792 | 23.3792 | 0%
Central Valley | YO_Yosemite | RACETRACK 1703 | 621 | RACETRACK 170310870 | 0.02122 | 45.1755 | 1.6924 | 0 | 1.6924 | 0 | 273 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 1 | 508 |  | 94 | 63 | 508 | 94 | 63 | 174.5 | 0.00046972 | 9e-05 | 1979 | 0.0042644 | 0.00020307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0042644 | 55.5416 | 55.5416 | 0%
Central Coast | DA_De Anza | LOS GATOS 1107 | 6971 | LOS GATOS 11072917 | 0.05372 | 150.1983 | 5.9744 | 0 | 5.9744 | 0 | 2574 | 0 | 0 | 0 | 0 | 0 | 0 | 126 | 1 | 4687 |  | 847 | 559 | 4687 | 847 | 559 | 1582.22 | 0.00035766 | 0.00063 | 1980 | 0.024912 | 0.00020254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.024912 | 141.7708 | 141.7708 | 0%
Bay Area | DI_Diablo | MORAGA 1102 | 1761 | MORAGA 1102circuit_breaker | 0.036208 | 106.6668 | 6.8028 | 3.3009 | 3.5019 | 4.5409 | 984 | 2183 | 642 | 288 | 512 | 235 | 2 | 372 | 0.3325 | 2781 |  | 751 | 360 | 598 | 239 | 125 | 381.25 | 0.00033945 | 0.00017 | 1981 | 0.01055 | 0.00019906 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0054309 | 68.2488 | 110.3951 | 48.52%
Bay Area | NB_North Bay | OLEMA 1101 | 1124 | OLEMA 11011200 | 0.075882 | 101.5977 | 4.5903 | 0 | 4.5903 | 0 | 1092 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 1 | 1995 |  | 362 | 239 | 1995 | 362 | 239 | 675.49 | 0.00074689 | 0.00056 | 1982 | 0.010671 | 0.00019762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.010671 | 78.8612 | 78.8612 | 0%
North Coast | SO_Sonoma | MONTE RIO 1111 | 2853 | MONTE RIO 111153477 | 0.013615 | 19.0217 | 0.80095 | 0 | 0.80095 | 0.80095 | 599 | 282 | 282 | 182 | 0 | 0 | 0 | 21 | 0 | 282 |  | 282 | 182 | 0 | 282 | 182 | 386.34 | 0.00071576 | 0.00042 | 1983 | 0.006475 | 0.00019621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.006475 | 352.0832 | 352.0832 | 0%
Bay Area | DI_Diablo | ROSSMOOR 1108 | 2691 | ROSSMOOR 110845268 | 0.08198 | 63.8332 | 2.0845 | 0.37633 | 1.7083 | 1.9189 | 554 | 668 | 426 | 369 | 138 | 108 | 0 | 98 | 0.079411 | 749 |  | 441 | 379 | 81 | 303 | 271 | 422.4 | 0.0012843 | 0.00081 | 1984 | 0.008377 | 0.00019481 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0068654 | 177.3659 | 211.5646 | 18.05%
Central Valley | ST_Stockton | CORRAL 1102 | 3784 | CORRAL 110275622 | 0.020054 | 31.781 | 2.0941 | 0 | 2.0941 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 1 | 59 |  | 13 | 9 | 59 | 13 | 9 | 23.12 | 0.00063101 | 2e-05 | 1985 | 0.0013343 | 0.00019061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0013343 | 6.2078 | 6.2078 | 0%
Sierra | SI_Sierra | WEIMAR 1102 | 3648 | WEIMAR 1102circuit_breaker | 0.052116 | 258.8626 | 11.6087 | 0 | 11.6087 | 0 | 4353 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 1 | 7917 |  | 1430 | 943 | 7917 | 1430 | 943 | 2671.63 | 0.00020133 | 0.0006 | 1986 | 0.035075 | 0.0001846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.035075 | 123.1833 | 123.1833 | 0%
North Valley | NV_North Valley | ORO FINO 1101 | 1392 | ORO FINO 11012022 | 0.59885 | 380.542 | 19.5182 | 1.8479 | 17.6705 | 11.1405 | 12735 | 15243 | 6271 | 5594 | 2801 | 2547 | 2 | 1516 | 0.42922 | 25175 |  | 8063 | 6775 | 9932 | 5262 | 4228 | 8102.82 | 0.0015737 | 0.01722 | 1987 | 0.04772 | 0.00018425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 3. >20 - 30% | 0.043203 | 297.7852 | 413.102 | 9.468%
North Coast | HU_Humboldt | ELK 1101 | 2706 | ELK 1101900 | 0.052747 | 190.4451 | 8.9379 | 0 | 8.9379 | 0 | 917 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 1 | 1678 |  | 305 | 202 | 1678 | 305 | 202 | 568.87 | 0.00027697 | 0.00018 | 1988 | 0.00791 | 0.00018395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00791 | 34.1244 | 34.1244 | 0%
Central Valley | ST_Stockton | MARTELL 1101 | 1518 | MARTELL 110191216 | 0.25355 | 1012.6587 | 41.6252 | 1.1941 | 40.4311 | 12.4311 | 12252 | 1019 | 1019 | 797 | 1 | 1 | 5 | 1264 | 0.70136 | 16632 |  | 3836 | 2653 | 15613 | 3835 | 2652 | 6659.12 | 0.00025038 | 0.002 | 1989 | 0.11155 | 0.00018138 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.10835 | 94.8528 | 92.1557 | 2.869%
Central Coast | LP_Los Padres | DIVIDE 1103 | 3230 | DIVIDE 110348160 | 0.079392 | 53.9752 | 2.5078 | 0 | 2.5078 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 1 | 69 |  | 14 | 10 | 69 | 14 | 10 | 25.39 | 0.0014709 | 4e-05 | 1990 | 0.0023472 | 0.00018055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0023472 | 5.5827 | 5.5827 | 0%
Bay Area | NB_North Bay | BOLINAS 1101 | 1763 | BOLINAS 11011064 | 0.00025 | 7.1327 | 0.35833 | 0 | 0.35833 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 187 |  | 36 | 24 | 187 | 36 | 24 | 66.15 | 3.505e-05 | 0 | 1991 | 0.0010656 | 0.00017761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0010656 | 100.4651 | 100.4651 | 0%
Sierra | SI_Sierra | HALSEY 1101 | 2498 | HALSEY 1101circuit_breaker | 0.093396 | 313.9806 | 13.0417 | 0 | 13.0417 | 0 | 4524 | 0 | 0 | 0 | 0 | 0 | 0 | 336 | 1 | 8228 |  | 1486 | 980 | 8228 | 1486 | 980 | 2776.34 | 0.00029746 | 0.00092 | 1992 | 0.04785 | 0.00017657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.04785 | 113.9425 | 113.9425 | 0%
Bay Area | NB_North Bay | ALTO 1125 | 3106 | ALTO 11251226 | 0.08233 | 163.7664 | 9.1093 | 0 | 9.1093 | 0 | 3120 | 0 | 0 | 0 | 0 | 0 | 0 | 333 | 1 | 5678 |  | 1026 | 677 | 5678 | 1026 | 677 | 1916.64 | 0.00050273 | 0.00107 | 1993 | 0.018322 | 0.00017449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.018322 | 112.6324 | 112.6324 | 0%
Central Valley | YO_Yosemite | SAN JOAQUIN NO3 1101 | 8105 | SAN JOAQUIN #3 110110060 | 0.12738 | 159.7971 | 6.8405 | 0.11061 | 6.7299 | 5.6057 | 1822 | 445 | 45 | 28 | 2 | 2 | 0 | 304 | 0.18052 | 1044 |  | 153 | 100 | 599 | 151 | 98 | 260.78 | 0.00079715 | 0.00025 | 1994 | 0.0062769 | 0.00017436 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0061754 | 22.4371 | 22.3667 | 1.617%
Sierra | SI_Sierra | HIGGINS 1104 | 2555 | HIGGINS 1104533648 | 0.13536 | 263.3086 | 10.4939 | 0 | 10.4939 | 0 | 2885 | 0 | 0 | 0 | 0 | 0 | 0 | 277 | 1 | 5251 |  | 949 | 626 | 5251 | 949 | 626 | 1772.72 | 0.00051407 | 0.00101 | 1995 | 0.019668 | 0.00017405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.019668 | 90.4332 | 90.4332 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1107 | 8027 | SAN RAFAEL 11071276 | 0.016129 | 56.8503 | 2.7502 | 0 | 2.7502 | 0 | 601 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 1 | 1104 |  | 201 | 133 | 1104 | 201 | 133 | 374.73 | 0.00028371 | 0.00012 | 1996 | 0.0094899 | 0.00017254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0094899 | 73.0859 | 73.0859 | 0%
Bay Area | DI_Diablo | ALHAMBRA 1105 | 5332 | ALHAMBRA 11058302 | 0.054381 | 225.3754 | 7.5792 | 0 | 7.5792 | 0 | 666 | 0 | 0 | 0 | 0 | 0 | 0 | 178 | 1 | 1222 |  | 222 | 147 | 1222 | 222 | 147 | 414.12 | 0.00024129 | 0.00011 | 1997 | 0.016872 | 0.00017216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.016872 | 29.2908 | 29.2908 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2103 | 2810 | CAMP EVERS 210311046 | 0.057029 | 439.5067 | 17.1061 | 0 | 17.1061 | 0 | 7240 | 0 | 0 | 0 | 0 | 0 | 0 | 919 | 1 | 13160 |  | 2375 | 1566 | 13160 | 2375 | 1566 | 4438.15 | 0.00012976 | 0.00064 | 1998 | 0.044646 | 0.00017172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.044646 | 138.8397 | 138.8397 | 0%
Central Coast | LP_Los Padres | BAYWOOD 1101 | 5149 | BAYWOOD 1101circuit_breaker | 0.07065 | 56.7623 | 2.1169 | 0 | 2.1169 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1 | 61 |  | 13 | 10 | 61 | 13 | 10 | 23.3 | 0.0012447 | 3e-05 | 1999 | 0.0013693 | 0.00017116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0013693 | 6.1412 | 6.1412 | 0%
Bay Area | DI_Diablo | ROSSMOOR 1108 | 5291 | ROSSMOOR 1108circuit_breaker | 0.006374 | 56.6066 | 1.9538 | 0.71553 | 1.2383 | 1.9146 | 391 | 455 | 306 | 256 | 256 | 212 | 0 | 115 | 0.020066 | 469 |  | 309 | 258 | 14 | 53 | 46 | 73.87 | 0.0001126 | 1e-05 | 2000 | 0.0085631 | 0.0001679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0054271 | 42.8021 | 158.1543 | 36.62%
Central Coast | CC_Central Coast | ROB ROY 2104 | 8642 | ROB ROY 21045304 | 0.020988 | 78.3015 | 4.4432 | 0 | 4.4432 | 0 | 718 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 1 | 1316 |  | 239 | 159 | 1316 | 239 | 159 | 445.87 | 0.00026804 | 0.00013 | 2001 | 0.0082564 | 0.00016513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0082564 | 53.7903 | 53.7903 | 0%
Central Coast | CC_Central Coast | ROB ROY 2104 | 9289 | ROB ROY 21046577 | 0.009841 | 99.3564 | 3.3902 | 0 | 3.3902 | 0 | 1927 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 1 | 3512 |  | 635 | 419 | 3512 | 635 | 419 | 1186.03 | 9.9047e-05 | 0.00013 | 2002 | 0.007254 | 0.00016486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.007254 | 187.3073 | 187.3073 | 0%
Bay Area | DI_Diablo | ORINDA 0402 | 1460 | ORINDA 0401N545R | 0.021275 | 76.5127 | 8.0674 | 3.1422 | 4.9252 | 4.5019 | 1049 | 2018 | 516 | 222 | 416 | 176 | 1 | 598 | 0.44197 | 2865 |  | 670 | 324 | 847 | 254 | 148 | 424.21 | 0.00027806 | 0.00015 | 2003 | 0.0091894 | 0.0001641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0056102 | 51.5716 | 83.0501 | 38.95%
Central Valley | YO_Yosemite | CURTIS 1705 | 7339 | CURTIS 17058110 | 0.019003 | 176.9376 | 6.9633 | 3.3992 | 3.564 | 6.9633 | 1170 | 2650 | 995 | 731 | 871 | 675 | 0 | 290 | 0 | 2650 |  | 995 | 731 | 0 | 124 | 56 | 169.88 | 0.0001074 | 3e-05 | 2004 | 0.016828 | 0.00016337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0086129 | 34.7922 | 142.8929 | 48.82%
Central Coast | CC_Central Coast | SAN JUSTO 1101 | 7589 | SAN JUSTO 11014002 | 0.061998 | 423.5242 | 17.822 | 0 | 17.822 | 0 | 1568 | 0 | 0 | 0 | 0 | 0 | 0 | 289 | 1 | 2860 |  | 518 | 342 | 2860 | 518 | 342 | 967.06 | 0.00014639 | 0.00016 | 2005 | 0.025092 | 0.00016085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.025092 | 29.0652 | 29.0652 | 0%
Central Valley | FR_Fresno | DUNLAP 1102 | 893 | DUNLAP 11027050 | 0.023641 | 226.9067 | 9.9248 | 0 | 9.9248 | 0 | 4537 | 0 | 0 | 0 | 0 | 0 | 0 | 211 | 1 | 8251 |  | 1490 | 982 | 8251 | 1490 | 982 | 2783.89 | 0.00010419 | 0.00032 | 2006 | 0.016413 | 0.00015935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.016413 | 150.1288 | 150.1288 | 0%
Central Valley | YO_Yosemite | OAKHURST 1103 | 2161 | OAKHURST 11035470 | 0.037282 | 207.2078 | 9.6576 | 0 | 9.6576 | 0 | 5570 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 1 | 10127 |  | 1828 | 1205 | 10127 | 1828 | 1205 | 3415.79 | 0.00017993 | 0.00068 | 2007 | 0.02003 | 0.00015771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.02003 | 189.2815 | 189.2815 | 0%
Central Valley | YO_Yosemite | BEAR VALLEY 2101 | 4718 | BEAR VALLEY 2101circuit_breaker | 0.25069 | 492.5778 | 19.5977 | 13.8547 | 5.743 | 19.0602 | 513 | 1673 | 247 | 200 | 225 | 184 | 0 | 613 | 0.027427 | 1699 |  | 252 | 203 | 26 | 27 | 19 | 39.33 | 0.00050893 | 3e-05 | 2008 | 0.023048 | 0.00015679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0067541 | 4.7014 | 12.8586 | 70.7%
Central Valley | YO_Yosemite | RACETRACK 1703 | 138 | RACETRACK 1703circuit_breaker | 0.42989 | 389.2813 | 17.914 | 0.84962 | 17.0644 | 0.95833 | 2423 | 308 | 22 | 15 | 20 | 14 | 0 | 802 | 0.9465 | 4484 |  | 777 | 513 | 4176 | 757 | 499 | 1412.93 | 0.0011043 | 0.00174 | 2009 | 0.030943 | 0.00015394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.029475 | 44.3614 | 43.3739 | 4.743%
Bay Area | NB_North Bay | SAN RAFAEL 1107 | 2806 | SAN RAFAEL 11071166 | 0.49589 | 315.8834 | 13.4252 | 0 | 13.4252 | 0 | 4058 | 0 | 0 | 0 | 0 | 0 | 0 | 411 | 1 | 7381 |  | 1333 | 879 | 7381 | 1333 | 879 | 2490.5 | 0.0015699 | 0.00435 | 2010 | 0.03328 | 0.00015336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0.03328 | 99.291 | 99.291 | 0%
Central Valley | YO_Yosemite | CURTIS 1702 | 6081 | CURTIS 170268380 | 0.001224 | 129.3559 | 7.5756 | 0.0018939 | 7.5735 | 0.86042 | 2224 | 26 | 4 | 1 | 3 | 1 | 0 | 278 | 0.88642 | 3617 |  | 653 | 430 | 3591 | 650 | 429 | 1213.69 | 9.4623e-06 | 1e-05 | 2011 | 0.015476 | 0.00015323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.015472 | 85.8257 | 86.1982 | 0.025%
North Coast | HU_Humboldt | UKIAH 1114 | 2842 | UKIAH 1114544 | 0.006675 | 27.0328 | 0.46496 | 0 | 0.46496 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 112 |  | 22 | 16 | 112 | 22 | 16 | 40.22 | 0.00024692 | 1e-05 | 2012 | 0.0010548 | 0.00015069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0010548 | 47.3157 | 47.3157 | 0%
Bay Area | NB_North Bay | SAUSALITO 1102 | 6656 | SAUSALITO 11021224 | 0.000617 | 2.2362 | 0.18258 | 0 | 0.18258 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 18 |  | 5 | 4 | 18 | 5 | 4 | 8.47 | 0.00027592 | 0 | 2013 | 0.0010547 | 0.00015067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0010547 | 27.3859 | 27.3859 | 0%
Central Coast | SJ_San Jose | MORGAN HILL 2104 | 1097 | MORGAN HILL 2104XR018 | 0.013822 | 144.6131 | 7.9271 | 0 | 7.9271 | 0 | 715 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 1 | 1311 |  | 238 | 158 | 1311 | 238 | 158 | 444.05 | 9.5579e-05 | 5e-05 | 2014 | 0.013825 | 0.00015027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.013825 | 30.0237 | 30.0237 | 0%
North Coast | HU_Humboldt | BIG RIVER 1101 | 186 | BIG RIVER 110179628 | 0.045346 | 365.9025 | 14.5231 | 0 | 14.5231 | 0 | 8708 | 0 | 0 | 0 | 0 | 0 | 0 | 346 | 1 | 15826 |  | 2856 | 1882 | 15826 | 2856 | 1882 | 5337.06 | 0.00012393 | 0.00074 | 2015 | 0.034735 | 0.00014908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.034735 | 196.6521 | 196.6521 | 0%
Sierra | SI_Sierra | BRUNSWICK 1102 | 2099 | BRUNSWICK 1102circuit_breaker | 0.004927 | 88.6446 | 5.1513 | 0.90966 | 4.2415 | 1.6187 | 1901 | 812 | 618 | 617 | 611 | 610 | 0 | 144 | 0.68576 | 3188 |  | 1048 | 901 | 2376 | 437 | 291 | 812.53 | 5.5581e-05 | 5e-05 | 2016 | 0.011748 | 0.00014871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0096731 | 103.0301 | 203.4428 | 17.66%
Central Coast | SJ_San Jose | PIERCY 2110 | 1472 | PIERCY 2110XR258 | 0.080176 | 435.2924 | 22.6379 | 0 | 22.6379 | 0 | 1617 | 0 | 0 | 0 | 0 | 0 | 0 | 288 | 1 | 2949 |  | 534 | 353 | 2949 | 534 | 353 | 996.99 | 0.00018419 | 0.0002 | 2017 | 0.022118 | 0.00014648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.022118 | 23.5888 | 23.5888 | 0%
Central Valley | YO_Yosemite | SPRING GAP 1702 | 3135 | 9280 | 0.027261 | 138.1455 | 6.5992 | 0 | 6.5992 | 0 | 3787 | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 1 | 6889 |  | 1244 | 821 | 6889 | 1244 | 821 | 2324.29 | 0.00019734 | 0.00051 | 2018 | 0.016214 | 0.00014607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.016214 | 188.5065 | 188.5065 | 0%
Central Coast | DA_De Anza | LOS GATOS 1107 | 8988 | LOS GATOS 1107LA60 | 0.039767 | 179.4205 | 6.8875 | 0 | 6.8875 | 0 | 598 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 1 | 1098 |  | 200 | 133 | 1098 | 200 | 133 | 372.82 | 0.00022164 | 9e-05 | 2019 | 0.011089 | 0.00014591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.011089 | 29.0381 | 29.0381 | 0%
North Coast | HU_Humboldt | ELK 1101 | 2224 | ELK 1101circuit_breaker | 0.016084 | 321.0693 | 12.8655 | 0 | 12.8655 | 0 | 5032 | 0 | 0 | 0 | 0 | 0 | 0 | 211 | 1 | 9150 |  | 1652 | 1089 | 9150 | 1652 | 1089 | 3086.74 | 5.0095e-05 | 0.00017 | 2020 | 0.021193 | 0.00014417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.021193 | 128.4051 | 128.4051 | 0%
Bay Area | MI_Mission | SUNOL 1101 | 5254 | SUNOL 1101MR299 | 0.022211 | 141.4827 | 5.7097 | 1.1348 | 4.5748 | 5.5559 | 1621 | 1847 | 537 | 215 | 30 | 3 | 0 | 427 | 0.026935 | 1927 |  | 551 | 225 | 80 | 521 | 222 | 720.97 | 0.00015699 | 0.00017 | 2021 | 0.012647 | 0.0001421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.010133 | 113.8845 | 96.5031 | 19.88%
Bay Area | MI_Mission | SAN RAMON 2106 | 1190 | SAN RAMON 2106circuit_breaker | 0.007269 | 25.9136 | 0.28314 | 0 | 0.28314 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 1 | 16 |  | 5 | 4 | 16 | 5 | 4 | 8.29 | 0.00028051 | 0 | 2022 | 0.00056237 | 0.00014059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00056237 | 17.6589 | 17.6589 | 0%
Central Coast | CC_Central Coast | KING CITY 1103 | 174 | KING CITY 11037038 | 0.045343 | 429.4214 | 17.7608 | 0 | 17.7608 | 0 | 472 | 0 | 0 | 0 | 0 | 0 | 0 | 269 | 1 | 869 |  | 159 | 106 | 869 | 159 | 106 | 296.04 | 0.00010559 | 3e-05 | 2023 | 0.01824 | 0.00014031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.01824 | 8.9523 | 8.9523 | 0%
North Valley | NV_North Valley | GRAYS FLAT 0401 | 3860 | GRAYS FLAT 0401circuit_breaker | 0.06546 | 259.2002 | 10.6439 | 0 | 10.6439 | 0 | 5674 | 0 | 0 | 0 | 0 | 0 | 0 | 284 | 1 | 10316 |  | 1863 | 1228 | 10316 | 1863 | 1228 | 3480.75 | 0.00025255 | 0.00098 | 2024 | 0.02328 | 0.00014024 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.02328 | 175.0292 | 175.0292 | 0%
Central Valley | YO_Yosemite | PEORIA 1704 | 4865 | PEORIA 17048040 | 0.034424 | 134.5039 | 7.5252 | 4.5708 | 2.9544 | 7.5252 | 60 | 255 | 112 | 74 | 75 | 45 | 0 | 101 | 0 | 255 |  | 112 | 74 | 0 | 37 | 29 | 50.69 | 0.00025593 | 2e-05 | 2025 | 0.0025193 | 0.00013996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00098906 | 12.5239 | 14.8833 | 60.74%
Bay Area | EB_East Bay | FAIRVIEW 2207 | 5641 | FAIRVIEW 2207P150 | 0.009133 | 41.9027 | 1.5973 | 0 | 1.5973 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1 | 167 |  | 32 | 22 | 167 | 32 | 22 | 58.87 | 0.00021796 | 1e-05 | 2026 | 0.0034985 | 0.00013994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0034985 | 20.0332 | 20.0332 | 0%
Sierra | SI_Sierra | WEIMAR 1101 | 4468 | WEIMAR 11012058 | 0.16452 | 566.5868 | 23.8034 | 0 | 23.8034 | 0 | 8417 | 0 | 0 | 0 | 0 | 0 | 0 | 599 | 1 | 15297 |  | 2761 | 1820 | 15297 | 2761 | 1820 | 5159.3 | 0.00029037 | 0.00167 | 2027 | 0.045746 | 0.00013862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.045746 | 115.9918 | 115.9918 | 0%
Sierra | SI_Sierra | BRUNSWICK 1106 | 2562 | BRUNSWICK 11062104 | 0.045632 | 266.0502 | 10.2818 | 0 | 10.2818 | 1.2036 | 6516 | 169 | 169 | 134 | 0 | 0 | 0 | 756 | 0.88294 | 10628 |  | 2057 | 1378 | 10459 | 2057 | 1378 | 3759.4 | 0.00017152 | 0.00073 | 2028 | 0.022255 | 0.00013823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.022255 | 200.0619 | 200.0619 | 0%
Central Coast | CC_Central Coast | OTTER 1102 | 6840 | OTTER 11022002 | 0.02618 | 188.7743 | 8.8127 | 0 | 8.8127 | 0 | 957 | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 1 | 1750 |  | 318 | 210 | 1750 | 318 | 210 | 593.16 | 0.00013868 | 9e-05 | 2029 | 0.012257 | 0.00013772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.012257 | 36.0843 | 36.0843 | 0%
North Coast | HU_Humboldt | ELK 1101 | 7444 | ELK 11011260 | 0.036789 | 371.4357 | 14.9087 | 0 | 14.9087 | 0 | 7863 | 0 | 0 | 0 | 0 | 0 | 0 | 230 | 1 | 14291 |  | 2579 | 1700 | 14291 | 2579 | 1700 | 4819.42 | 9.9045e-05 | 0.00053 | 2031 | 0.03001 | 0.00013458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.03001 | 172.9861 | 172.9861 | 0%
Sierra | SI_Sierra | BRUNSWICK 1105 | 194 | BRUNSWICK 1105733408 | 0.056285 | 74.2585 | 2.4155 | 0 | 2.4155 | 0 | 1531 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 1 | 2793 |  | 506 | 334 | 2793 | 506 | 334 | 944.59 | 0.00075796 | 0.0008 | 2032 | 0.0042647 | 0.00013327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0042647 | 209.4778 | 209.4778 | 0%
North Valley | NV_North Valley | BIG MEADOWS 2101 | 7954 | BIG MEADOWS 21012476 | 0.018668 | 176.0566 | 8.9561 | 0 | 8.9561 | 0 | 6192 | 0 | 0 | 0 | 0 | 0 | 0 | 387 | 1 | 11257 |  | 2032 | 1340 | 11257 | 2032 | 1340 | 3796.97 | 0.00010603 | 0.00045 | 2033 | 0.014902 | 0.00013188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.014902 | 226.8855 | 226.8855 | 0%
Bay Area | NB_North Bay | IGNACIO 1105 | 6722 | IGNACIO 1101circuit_breaker | 0.002279 | 17.2364 | 0.79205 | 0 | 0.79205 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 27 |  | 7 | 5 | 27 | 7 | 5 | 12.02 | 0.00013222 | 0 | 2034 | 0.0023575 | 0.00013097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0023575 | 8.8379 | 8.8379 | 0%
Central Valley | ST_Stockton | SALT SPRINGS 2102 | 6703 | SALT SPRINGS 2102L491 | 0.006023 | 63.8629 | 3.4059 | 0 | 3.4059 | 0 | 2431 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 1 | 4427 |  | 800 | 528 | 4427 | 800 | 528 | 1494.43 | 9.4311e-05 | 0.00016 | 2035 | 0.005721 | 0.00013002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.005721 | 234.8885 | 234.8885 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2101 | 4927 | GREEN VALLEY 210112130 | 0.006612 | 41.1522 | 2.422 | 0 | 2.422 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 1 | 412 |  | 76 | 51 | 412 | 76 | 51 | 141.2 | 0.00016067 | 3e-05 | 2036 | 0.0013847 | 0.00012588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0013847 | 31.3794 | 31.3794 | 0%
Central Coast | CC_Central Coast | POINT MORETTI 1101 | 3711 | POINT MORETTI 110110726 | 0.035248 | 293.8714 | 12.3568 | 0 | 12.3568 | 0 | 8401 | 0 | 0 | 0 | 0 | 0 | 0 | 313 | 1 | 15268 |  | 2756 | 1816 | 15268 | 2756 | 1816 | 5149.84 | 0.00011994 | 0.00069 | 2037 | 0.022416 | 0.00012523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.022416 | 223.0348 | 223.0348 | 0%
North Coast | SO_Sonoma | MONTE RIO 1113 | 1481 | MONTE RIO 1113circuit_breaker | 0.086585 | 153.9653 | 7.5729 | 0 | 7.5729 | 0.93333 | 4100 | 52 | 22 | 15 | 2 | 0 | 0 | 591 | 0.87675 | 6591 |  | 1203 | 794 | 6539 | 1201 | 794 | 2233.88 | 0.00056237 | 0.0014 | 2038 | 0.0072556 | 0.00012298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0072556 | 158.5915 | 158.8556 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2101 | 313 | GREEN VALLEY 210112106 | 0.020747 | 136.1273 | 5.9373 | 0 | 5.9373 | 0 | 1051 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 1 | 1921 |  | 348 | 230 | 1921 | 348 | 230 | 649.65 | 0.00015241 | 0.00011 | 2039 | 0.0099233 | 0.00012102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0099233 | 58.6124 | 58.6124 | 0%
Central Valley | YO_Yosemite | TAR FLAT 0402 | 3226 | TAR FLAT 04023144 | 0.022552 | 64.3414 | 2.6765 | 0 | 2.6765 | 0 | 504 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 1 | 928 |  | 169 | 112 | 928 | 169 | 112 | 315.05 | 0.00035051 | 0.00012 | 2040 | 0.0087181 | 0.00011943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0087181 | 63.1418 | 63.1418 | 0%
North Valley | NV_North Valley | MC ARTHUR 1101 | 6142 | MC ARTHUR 11011490 | 0.29373 | 192.351 | 10.6858 | 0 | 10.6858 | 0 | 2642 | 0 | 0 | 0 | 0 | 0 | 0 | 239 | 1 | 4810 |  | 869 | 574 | 4810 | 869 | 574 | 1623.43 | 0.0015271 | 0.00276 | 2041 | 0.012501 | 0.00011793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.012501 | 81.3229 | 81.3229 | 0%
North Valley | NV_North Valley | VOLTA 1102 | 7900 | VOLTA 110254932 | 0.031464 | 106.3404 | 5.0625 | 0 | 5.0625 | 0 | 2687 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1 | 4892 |  | 884 | 583 | 4892 | 884 | 583 | 1651.36 | 0.00029588 | 0.00054 | 2042 | 0.0081164 | 0.00011763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0081164 | 174.6173 | 174.6173 | 0%
Bay Area | NB_North Bay | SAUSALITO 1102 | 8970 | SAUSALITO 110284278 | 0.004251 | 30.4662 | 1.5356 | 0 | 1.5356 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1 | 158 |  | 30 | 21 | 158 | 30 | 21 | 55.32 | 0.00013953 | 1e-05 | 2043 | 0.0016382 | 0.00011702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0016382 | 19.5363 | 19.5363 | 0%
Sierra | SI_Sierra | BRUNSWICK 1106 | 6422 | BRUNSWICK 11064639 | 0.003403 | 39.715 | 1.893 | 0 | 1.893 | 0 | 933 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 1 | 1707 |  | 310 | 205 | 1707 | 310 | 205 | 578.33 | 8.5685e-05 | 6e-05 | 2044 | 0.0063064 | 0.00011679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0063064 | 163.7619 | 163.7619 | 0%
North Coast | HU_Humboldt | LUCERNE 1106 | 2078 | LUCERNE 1106circuit_breaker | 0.007803 | 26.6237 | 1.9273 | 0 | 1.9273 | 0 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 1 | 286 |  | 54 | 36 | 286 | 54 | 36 | 99.72 | 0.00029309 | 3e-05 | 2046 | 0.0026676 | 0.00011598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0026676 | 28.0189 | 28.0189 | 0%
Central Valley | ST_Stockton | CLAY 1101 | 1396 | CLAY 110184572 | 0.004797 | 11.7744 | 0.52765 | 0.28428 | 0.24337 | 0.52765 | 31 | 75 | 10 | 0 | 0 | 0 | 0 | 16 | 0 | 75 |  | 10 | 0 | 0 | 10 | 0 | 13.7 | 0.00040741 | 1e-05 | 2047 | 0.00080407 | 0.00011487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00037087 | 41.0895 | 18.9519 | 53.88%
North Coast | SO_Sonoma | DUNBAR 1101 | 6394 | DUNBAR 1101234 | 0.020315 | 88.1985 | 3.5915 | 0.65152 | 2.9398 | 2.2663 | 427 | 460 | 146 | 8 | 85 | 4 | 0 | 159 | 0.36898 | 751 |  | 199 | 43 | 291 | 114 | 39 | 182.37 | 0.00023033 | 5e-05 | 2048 | 0.0055044 | 0.00011467 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0045055 | 38.7785 | 55.409 | 18.14%
Bay Area | EB_East Bay | OAKLAND X 1106 | 5658 | OAKLAND X 1106CR020 | 0.006855 | 111.4915 | 2.7991 | 0 | 2.7991 | 0 | 1275 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 1 | 2328 |  | 422 | 279 | 2328 | 422 | 279 | 787.66 | 6.1485e-05 | 5e-05 | 2049 | 0.0053494 | 0.00010917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0053494 | 150.7653 | 150.7653 | 0%
Central Coast | CC_Central Coast | PANOCHE 1103 | 9254 | PANOCHE 11034036 | 0.003043 | 129.6139 | 10.2256 | 0 | 10.2256 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 1 | 41 |  | 9 | 7 | 41 | 9 | 7 | 16.02 | 2.3477e-05 | 0 | 2050 | 0.00063911 | 0.00010652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00063911 | 0.88015 | 0.88015 | 0%
Central Valley | YO_Yosemite | PEORIA 1701 | 5946 | PEORIA 170169124 | 0.001375 | 35.6924 | 1.4877 | 0.027273 | 1.4604 | 0.027273 | 254 | 7 | 1 | 0 | 1 | 0 | 0 | 39 | 0.98167 | 472 |  | 87 | 57 | 465 | 86 | 57 | 159.67 | 3.8524e-05 | 1e-05 | 2051 | 0.0013731 | 0.00010562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0013479 | 58.8873 | 58.4799 | 1.833%
Central Coast | LP_Los Padres | CABRILLO 1104 | 1778 | CABRILLO 1104circuit_breaker | 0.027024 | 84.3041 | 4.5339 | 0 | 4.5339 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 1 | 136 |  | 26 | 18 | 136 | 26 | 18 | 47.86 | 0.00032055 | 2e-05 | 2052 | 0.0037888 | 0.00010524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0037888 | 5.7346 | 5.7346 | 0%
Central Coast | LP_Los Padres | CAMBRIA 1101 | 4579 | CAMBRIA 1101V76 | 0.098574 | 412.8279 | 19.6449 | 18.3032 | 1.3417 | 19.3153 | 377 | 574 | 62 | 2 | 19 | 1 | 0 | 443 | 0.016775 | 586 |  | 64 | 3 | 12 | 45 | 2 | 62.73 | 0.00023878 | 2e-05 | 2053 | 0.0048118 | 0.00010238 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00032863 | 33.5404 | 3.2578 | 93.17%
Central Coast | LP_Los Padres | MORRO BAY 1102 | 3709 | MORRO BAY 110247584 | 0.02243 | 177.6071 | 8.1989 | 0 | 8.1989 | 0 | 181 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 1 | 341 |  | 63 | 43 | 341 | 63 | 43 | 117 | 0.00012629 | 2e-05 | 2054 | 0.0034617 | 0.00010181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0034617 | 7.684 | 7.684 | 0%
Central Valley | YO_Yosemite | CURTIS 1703 | 6442 | CURTIS 17039210 | 0.093178 | 475.4767 | 21.8337 | 8.8307 | 13.003 | 21.8337 | 3961 | 7849 | 2152 | 1719 | 956 | 679 | 0 | 565 | 0 | 7849 |  | 2152 | 1719 | 0 | 1196 | 1040 | 1638.52 | 0.00019597 | 0.00049 | 2055 | 0.00070741 | 0.00010106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0004213 | 91.9786 | 98.5632 | 40.45%
Sierra | SI_Sierra | SUMMIT 1102 | 8515 | SUMMIT 110249484 | 0.007089 | 96.6142 | 3.7305 | 0 | 3.7305 | 0 | 824 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 1 | 1509 |  | 274 | 181 | 1509 | 274 | 181 | 511.19 | 7.3374e-05 | 4e-05 | 2056 | 0.0033616 | 9.887e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0033616 | 73.4487 | 73.4487 | 0%
Central Coast | CC_Central Coast | OTTER 1101 | 8903 | OTTER 11017611 | 0.009071 | 115.6563 | 4.6746 | 0 | 4.6746 | 0 | 1456 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 1 | 2656 |  | 481 | 318 | 2656 | 481 | 318 | 898.01 | 7.8431e-05 | 8e-05 | 2057 | 0.0037516 | 9.8725e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0037516 | 102.896 | 102.896 | 0%
Central Coast | CC_Central Coast | RESERVATION ROAD 1101 | 686 | RESERVATION ROAD 11013026 | 0.042838 | 559.3724 | 21.7265 | 21.7206 | 0.0060606 | 21.7265 | 1063 | 1840 | 717 | 93 | 716 | 92 | 0 | 899 | 0 | 1840 |  | 717 | 93 | 0 | 1 | 1 | 1.37 | 7.6582e-05 | 0 | 2058 | 0.020822 | 9.8215e-05 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.8082e-06 | 165 | 33.0012 | 99.97%
Bay Area | PE_Peninsula | SNEATH LANE 1107 | 79 | SNEATH LANE 1107circuit_breaker | 0.005376 | 19.4487 | 2.8443 | 0 | 2.8443 | 0 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 1 | 385 |  | 71 | 48 | 385 | 71 | 48 | 131.92 | 0.00027642 | 4e-05 | 2059 | 0.00086849 | 9.6499e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00086849 | 24.962 | 24.962 | 0%
Sierra | SI_Sierra | HALSEY 1102 | 6485 | HALSEY 1102circuit_breaker | 0.000672 | 172.2768 | 8.1006 | 0 | 8.1006 | 0 | 2287 | 0 | 0 | 0 | 0 | 0 | 0 | 202 | 1 | 4165 |  | 753 | 497 | 4165 | 753 | 497 | 1406.46 | 3.9007e-06 | 1e-05 | 2060 | 0.011477 | 9.4076e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.011477 | 92.9564 | 92.9564 | 0%
Central Coast | LP_Los Padres | CAMBRIA 1101 | 3027 | CAMBRIA 1101circuit_breaker | 0.020033 | 118.4048 | 4.9623 | 4.7964 | 0.16591 | 4.9623 | 157 | 320 | 7 | 1 | 1 | 1 | 0 | 124 | 0 | 320 |  | 7 | 1 | 0 | 6 | 0 | 8.22 | 0.00016919 | 0 | 2061 | 0.0019654 | 9.3591e-05 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.5711e-05 | 36.1644 | 1.4106 | 96.66%
North Valley | NV_North Valley | BIG MEADOWS 2101 | 5961 | BIG MEADOWS 2101circuit_breaker | 0.002204 | 58.1682 | 3.7134 | 0.16269 | 3.5508 | 0.50095 | 1436 | 390 | 41 | 41 | 0 | 0 | 0 | 214 | 0.8651 | 2657 |  | 451 | 312 | 2267 | 451 | 312 | 821.9 | 3.789e-05 | 4e-05 | 2062 | 0.0022603 | 9.0413e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0021613 | 127.0151 | 121.4505 | 4.381%
Bay Area | EB_East Bay | OAKLAND D 1112 | 6520 | OAKLAND D 1112CR192 | 0.002837 | 57.3227 | 1.5331 | 0 | 1.5331 | 0 | 347 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 1 | 642 |  | 118 | 79 | 642 | 118 | 79 | 219.44 | 4.9492e-05 | 1e-05 | 2063 | 0.0028762 | 8.9881e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0028762 | 76.966 | 76.966 | 0%
Bay Area | DI_Diablo | MORAGA 1101 | 7289 | SOBRANTE 1103circuit_breaker | 0.035633 | 157.3898 | 7.0953 | 2.418 | 4.6773 | 2.829 | 1104 | 1126 | 392 | 190 | 359 | 176 | 0 | 375 | 0.60129 | 2339 |  | 612 | 335 | 1213 | 253 | 159 | 455.78 | 0.0002264 | 0.00012 | 2064 | 0.0054294 | 8.9007e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0035791 | 54.0914 | 86.2547 | 34.08%
Central Valley | ST_Stockton | ELECTRA 1101 | 6731 | ELECTRA 1101L1697 | 0.036185 | 160.0139 | 6.7996 | 0 | 6.7996 | 0 | 1956 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 1 | 3564 |  | 645 | 426 | 3564 | 645 | 426 | 1204.41 | 0.00022614 | 0.0003 | 2065 | 0.0073707 | 8.8803e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0073707 | 94.8582 | 94.8582 | 0%
North Valley | NV_North Valley | HAMILTON BRANCH 1101 | 4977 | HAMILTON BRANCH 11012046 | 0.012864 | 195.84 | 8.8686 | 0 | 8.8686 | 0 | 3167 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 1 | 5763 |  | 1041 | 687 | 5763 | 1041 | 687 | 1944.84 | 6.5686e-05 | 0.00014 | 2066 | 0.0059115 | 8.6934e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0059115 | 117.3809 | 117.3809 | 0%
Central Coast | CC_Central Coast | HOLLISTER 2105 | 1967 | HOLLISTER 21054018 | 0.09514 | 1041.187 | 41.2511 | 0 | 41.2511 | 0 | 535 | 0 | 0 | 0 | 0 | 0 | 0 | 523 | 1 | 984 |  | 179 | 119 | 984 | 179 | 119 | 333.79 | 9.1376e-05 | 3e-05 | 2067 | 0.0075849 | 8.5223e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0075849 | 4.3393 | 4.3393 | 0%
North Coast | HU_Humboldt | FORT BRAGG A 1102 | 6186 | FORT BRAGG A 1102956 | 0.002127 | 255.5557 | 9.5345 | 0 | 9.5345 | 0 | 2961 | 0 | 0 | 0 | 0 | 0 | 0 | 212 | 1 | 5389 |  | 974 | 642 | 5389 | 974 | 642 | 1819.39 | 8.323e-06 | 2e-05 | 2068 | 0.013116 | 8.517e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.013116 | 102.1557 | 102.1557 | 0%
North Valley | NV_North Valley | BURNEY 1101 | 3988 | BURNEY 11021340 | 0.030671 | 419.7743 | 17.8165 | 0 | 17.8165 | 0 | 3477 | 0 | 0 | 0 | 0 | 0 | 0 | 458 | 1 | 6326 |  | 1143 | 754 | 6326 | 1143 | 754 | 2135.25 | 7.3065e-05 | 0.00017 | 2069 | 0.019916 | 8.5109e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.019916 | 64.1541 | 64.1541 | 0%
Central Coast | CC_Central Coast | ROB ROY 2105 | 259 | ROB ROY 21055090 | 0.046926 | 446.3012 | 18.9489 | 0 | 18.9489 | 0 | 10463 | 0 | 0 | 0 | 0 | 0 | 0 | 466 | 1 | 19013 |  | 3431 | 2261 | 19013 | 3431 | 2261 | 6411.64 | 0.00010514 | 0.00075 | 2070 | 0.026197 | 8.4236e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.026197 | 181.0663 | 181.0663 | 0%
Central Valley | YO_Yosemite | CURTIS 1704 | 320 | CURTIS 170463502 | 0.041568 | 250.248 | 10.679 | 6.0777 | 4.6015 | 10.679 | 1818 | 3151 | 889 | 473 | 815 | 455 | 0 | 436 | 0 | 3151 |  | 889 | 473 | 0 | 74 | 18 | 101.38 | 0.00016611 | 3e-05 | 2071 | 0.010831 | 8.205e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0046668 | 16.0817 | 83.2477 | 56.91%
Central Coast | CC_Central Coast | PAUL SWEET 2105 | 2890 | PAUL SWEET 2105circuit_breaker | 0.029921 | 196.1691 | 7.7602 | 0 | 7.7602 | 0.31364 | 2715 | 94 | 94 | 66 | 0 | 0 | 0 | 184 | 0.95958 | 4837 |  | 951 | 632 | 4743 | 951 | 632 | 1729.74 | 0.00015253 | 0.0003 | 2072 | 0.0082821 | 8.2001e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0082821 | 122.548 | 122.548 | 0%
Bay Area | PE_Peninsula | HALF MOON BAY 1103 | 3571 | HALF MOON BAY 11038089 | 0.005958 | 83.9926 | 2.7939 | 0 | 2.7939 | 0 | 2469 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 1 | 4496 |  | 813 | 536 | 4496 | 813 | 536 | 1518.45 | 7.0935e-05 | 0.00012 | 2073 | 0.0044539 | 8.098e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0044539 | 290.987 | 290.987 | 0%
North Valley | NV_North Valley | BURNEY 1101 | 1338 | BURNEY 11021322 | 0.022427 | 323.9983 | 16.0953 | 0 | 16.0953 | 0 | 3144 | 0 | 0 | 0 | 0 | 0 | 0 | 348 | 1 | 5722 |  | 1034 | 682 | 5722 | 1034 | 682 | 1931.56 | 6.922e-05 | 0.00015 | 2074 | 0.0095423 | 8.0867e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0095423 | 64.2425 | 64.2425 | 0%
Sierra | SI_Sierra | HORSESHOE 1104 | 5977 | HORSESHOE 110450142 | 0.013766 | 47.7684 | 2.2157 | 0 | 2.2157 | 0 | 358 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 1 | 662 |  | 121 | 81 | 662 | 121 | 81 | 225.35 | 0.00028818 | 7e-05 | 2075 | 0.0026525 | 8.038e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0026525 | 54.6098 | 54.6098 | 0%
Bay Area | PE_Peninsula | MENLO 1103 | 7554 | MENLO 11038982 | 0.074772 | 129.65 | 4.6201 | 0 | 4.6201 | 0 | 4704 | 0 | 0 | 0 | 0 | 0 | 0 | 142 | 1 | 8555 |  | 1545 | 1019 | 8555 | 1545 | 1019 | 2886.6 | 0.00057672 | 0.00185 | 2076 | 0.0055001 | 7.9712e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0055001 | 334.4101 | 334.4101 | 0%
North Valley | NV_North Valley | FRENCH GULCH 1101 | 3611 | FRENCH GULCH 1101circuit_breaker | 0.009598 | 70.5831 | 2.2674 | 0 | 2.2674 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 1 | 167 |  | 32 | 22 | 167 | 32 | 22 | 58.87 | 0.00013598 | 1e-05 | 2077 | 0.0015939 | 7.9697e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0015939 | 14.1129 | 14.1129 | 0%
North Coast | HU_Humboldt | ELK 1101 | 826 | ELK 11011272 | 0.088226 | 670.4345 | 23.2076 | 0 | 23.2076 | 0 | 14295 | 0 | 0 | 0 | 0 | 0 | 0 | 452 | 1 | 25972 |  | 4686 | 3088 | 25972 | 4686 | 3088 | 8757.3 | 0.0001316 | 0.00128 | 2078 | 0.027835 | 7.9078e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.027835 | 201.9168 | 201.9168 | 0%
Sierra | SI_Sierra | SUMMIT 1101 | 8935 | SUMMIT 110147786 | 0.003275 | 26.3413 | 1.3913 | 0 | 1.3913 | 0 | 342 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1 | 633 |  | 116 | 77 | 633 | 116 | 77 | 215.89 | 0.00012433 | 3e-05 | 2079 | 0.0018891 | 7.8714e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0018891 | 83.376 | 83.376 | 0%
Sierra | SI_Sierra | BRUNSWICK 1106 | 7774 | BRUNSWICK 1106circuit_breaker | 0.005927 | 189.0773 | 8.7436 | 0.036364 | 8.707 | 4.9714 | 4907 | 587 | 433 | 348 | 16 | 12 | 0 | 606 | 0.43142 | 4437 |  | 1128 | 806 | 3850 | 1112 | 794 | 1869.94 | 3.1347e-05 | 7e-05 | 2080 | 0.0094492 | 7.6823e-05 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0094097 | 127.7132 | 129.0092 | 0.4159%
Sierra | SI_Sierra | HALSEY 1102 | 2514 | HALSEY 11022514 | 0.026296 | 226.5796 | 10.9491 | 0 | 10.9491 | 0 | 1615 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 1 | 2945 |  | 533 | 352 | 2945 | 533 | 352 | 995.26 | 0.00011606 | 0.00013 | 2081 | 0.011265 | 7.6636e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.011265 | 48.68 | 48.68 | 0%
Central Coast | CC_Central Coast | HOLLISTER 2106 | 7092 | HOLLISTER 21064004 | 0.007224 | 188.2816 | 9.0443 | 0 | 9.0443 | 0 | 444 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 1 | 819 |  | 150 | 99 | 819 | 150 | 99 | 279.21 | 3.8368e-05 | 1e-05 | 2082 | 0.0038995 | 7.646e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0038995 | 16.585 | 16.585 | 0%
Central Coast | DA_De Anza | SARATOGA 1107 | 1902 | SARATOGA 1107LC12 | 0.000273 | 127.1408 | 5.4218 | 0 | 5.4218 | 0 | 1396 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 1 | 2547 |  | 461 | 305 | 2547 | 461 | 305 | 860.8 | 2.1472e-06 | 0 | 2083 | 0.009432 | 7.5456e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.009432 | 85.0274 | 85.0274 | 0%
Central Coast | CC_Central Coast | HOLLISTER 2105 | 6119 | HOLLISTER 21054048 | 0.027668 | 329.3 | 15.3386 | 0 | 15.3386 | 0 | 961 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 1 | 1757 |  | 319 | 211 | 1757 | 319 | 211 | 595.16 | 8.4021e-05 | 6e-05 | 2084 | 0.004208 | 7.5143e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.004208 | 20.7972 | 20.7972 | 0%
Central Coast | CC_Central Coast | SOLEDAD 2102 | 5624 | SOLEDAD 21027048 | 0.34553 | 140.5788 | 5.7739 | 0 | 5.7739 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 1 | 30 |  | 7 | 6 | 30 | 7 | 6 | 12.29 | 0.0024579 | 4e-05 | 2085 | 0.0011947 | 7.4669e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0011947 | 1.2124 | 1.2124 | 0%
Bay Area | EB_East Bay | OAKLAND K 1102 | 5711 | OAKLAND K 1102circuit_breaker | 0.000826 | 144.3577 | 2.0528 | 0.22689 | 1.8259 | 0.98693 | 246 | 379 | 86 | 58 | 5 | 1 | 0 | 37 | 0.51924 | 617 |  | 130 | 87 | 238 | 125 | 86 | 192.67 | 5.7219e-06 | 0 | 2086 | 0.0027249 | 7.3647e-05 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0024238 | 68.4576 | 63.3269 | 11.05%
Central Coast | CC_Central Coast | HOLLISTER 2104 | 3675 | HOLLISTER 210491424 | 0.000228 | 6.0017 | 0.21837 | 0 | 0.21837 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 43 |  | 10 | 7 | 43 | 10 | 7 | 17.57 | 3.7989e-05 | 0 | 2087 | 0.00021979 | 7.3262e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00021979 | 45.7936 | 45.7936 | 0%
North Valley | NV_North Valley | PIT NO 3 2101 | 2386 | PIT NO 3 21011360 | 0.025829 | 505.8013 | 21.7445 | 0 | 21.7445 | 0 | 8738 | 0 | 0 | 0 | 0 | 0 | 0 | 536 | 1 | 15880 |  | 2866 | 1889 | 15880 | 2866 | 1889 | 5355.62 | 5.1066e-05 | 0.0003 | 2088 | 0.016564 | 7.265e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.016564 | 131.8034 | 131.8034 | 0%
North Valley | NV_North Valley | ORO FINO 1102 | 3292 | ORO FINO 110276008 | 0.01944 | 403.9761 | 18.2487 | 0.57235 | 17.6763 | 11.6295 | 10801 | 7949 | 3130 | 2673 | 1370 | 1120 | 1 | 973 | 0.36272 | 15068 |  | 4415 | 3520 | 7119 | 3045 | 2400 | 4812.36 | 4.8122e-05 | 0.0003 | 2089 | 0.018671 | 7.1538e-05 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.018086 | 172.2643 | 241.9354 | 3.136%
Central Coast | CC_Central Coast | OTTER 1102 | 1783 | OTTER 110298036 | 0.013855 | 165.7372 | 7.8205 | 0 | 7.8205 | 0 | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 1 | 566 |  | 104 | 69 | 566 | 104 | 69 | 193.42 | 8.3596e-05 | 2e-05 | 2090 | 0.0039864 | 7.1186e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0039864 | 13.2985 | 13.2985 | 0%
North Coast | HU_Humboldt | FORT BRAGG A 1104 | 1816 | FORT BRAGG A 11044690 | 0.035438 | 293.2225 | 12.0994 | 0 | 12.0994 | 0 | 6881 | 0 | 0 | 0 | 0 | 0 | 0 | 261 | 1 | 12508 |  | 2258 | 1488 | 12508 | 2258 | 1488 | 4219.18 | 0.00012086 | 0.00057 | 2091 | 0.012803 | 7.0733e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.012803 | 186.6203 | 186.6203 | 0%
Central Valley | YO_Yosemite | PEORIA 1704 | 7364 | PEORIA 170413490 | 0.010601 | 96.3955 | 4.6746 | 3.9299 | 0.7447 | 4.6746 | 65 | 152 | 55 | 38 | 45 | 36 | 0 | 83 | 0 | 152 |  | 55 | 38 | 0 | 10 | 2 | 13.7 | 0.00010997 | 0 | 2092 | 0.0017198 | 6.8791e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00027397 | 13.4283 | 11.7657 | 84.07%
North Valley | NV_North Valley | VOLTA 1101 | 5681 | VOLTA 11011640 | 0.0129 | 215.9461 | 10.2356 | 0 | 10.2356 | 0 | 6812 | 0 | 0 | 0 | 0 | 0 | 0 | 261 | 1 | 12383 |  | 2235 | 1473 | 12383 | 2235 | 1473 | 4176.42 | 5.9737e-05 | 0.00028 | 2093 | 0.010028 | 6.7303e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.010028 | 218.3554 | 218.3554 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2108 | 3628 | TEMPLETON 2108A40 | 3.6e-05 | 74.0813 | 3.3239 | 0 | 3.3239 | 0 | 560 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 1 | 1029 |  | 188 | 124 | 1029 | 188 | 124 | 350.17 | 4.8595e-07 | 0 | 2094 | 0.0039443 | 6.5739e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0039443 | 56.5607 | 56.5607 | 0%
Central Coast | CC_Central Coast | OTTER 1101 | 7129 | OTTER 11012052 | 0.009215 | 105.4759 | 4.4934 | 0 | 4.4934 | 0 | 2693 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 1 | 4903 |  | 886 | 585 | 4903 | 886 | 585 | 1655.09 | 8.7366e-05 | 0.00016 | 2095 | 0.0045471 | 6.4044e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0045471 | 197.1793 | 197.1793 | 0%
Bay Area | EB_East Bay | FAIRVIEW 2207 | 6972 | FAIRVIEW 220799096 | 0.007779 | 227.5407 | 9.3854 | 0 | 9.3854 | 0 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 167 | 1 | 390 |  | 72 | 49 | 390 | 72 | 49 | 133.74 | 3.4187e-05 | 1e-05 | 2096 | 0.0039443 | 6.3618e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0039443 | 7.6715 | 7.6715 | 0%
North Coast | HU_Humboldt | BIG RIVER 1101 | 748 | BIG RIVER 1101952 | 0.052327 | 371.3175 | 15.4085 | 0 | 15.4085 | 0 | 8775 | 0 | 0 | 0 | 0 | 0 | 0 | 284 | 1 | 15947 |  | 2878 | 1897 | 15947 | 2878 | 1897 | 5378.09 | 0.00014092 | 0.00084 | 2097 | 0.012958 | 6.1703e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.012958 | 186.7797 | 186.7797 | 0%
Central Valley | YO_Yosemite | MERCED FALLS 1102 | 688 | MERCED FALLS 11029460 | 0.019794 | 171.925 | 8.5689 | 8.3479 | 0.22102 | 8.5689 | 39 | 352 | 51 | 47 | 51 | 47 | 0 | 248 | 0 | 352 |  | 51 | 47 | 0 | 0 | 0 | 0 | 0.00011513 | 0 | 2098 | 0.0029607 | 5.6936e-05 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.6366e-05 | 0 | 5.9517 | 97.42%
Central Valley | FR_Fresno | TULE POWER HOUSE 1101 | 892 | TULE POWER HOUSE 1101circuit_breaker | 0.00753 | 94.1612 | 4.0237 | 0 | 4.0237 | 0 | 266 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 1 | 495 |  | 91 | 61 | 495 | 91 | 61 | 169.22 | 7.9969e-05 | 2e-05 | 2099 | 0.0022435 | 5.6086e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0022435 | 22.6161 | 22.6161 | 0%
Bay Area | NB_North Bay | PUEBLO 2102 | 3727 | PUEBLO 2102698 | 9.2e-05 | 1.6855 | 0.11667 | 0.11667 | 0 | 0.11667 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5.4584e-05 | 0 | 2100 | 0.00010945 | 5.4726e-05 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0 | 100%
Bay Area | DI_Diablo | MORAGA 1105 | 644 | MORAGA 1105circuit_breaker | 0.008125 | 132.6328 | 5.2244 | 1.911 | 3.3134 | 5.2244 | 1608 | 2204 | 356 | 305 | 1 | 0 | 0 | 150 | 0 | 2204 |  | 356 | 305 | 0 | 355 | 305 | 486.35 | 6.1259e-05 | 5e-05 | 2101 | 0.0046 | 5.4118e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0029174 | 107.1392 | 68.1414 | 36.58%
Central Coast | CC_Central Coast | PAUL SWEET 2106 | 938 | PAUL SWEET 2106circuit_breaker | 0.000258 | 93.984 | 4.4358 | 0 | 4.4358 | 0 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 1 | 848 |  | 155 | 103 | 848 | 155 | 103 | 288.67 | 2.7451e-06 | 0 | 2102 | 0.0028044 | 5.393e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0028044 | 34.943 | 34.943 | 0%
Central Coast | LP_Los Padres | PERRY 1101 | 806 | PERRY 1101V74 | 0.003927 | 37.3678 | 2.7027 | 0 | 2.7027 | 0 | 265 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | 1 | 494 |  | 91 | 61 | 494 | 91 | 61 | 169.13 | 0.00010509 | 2e-05 | 2103 | 0.0024806 | 5.3926e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0024806 | 33.6706 | 33.6706 | 0%
Central Coast | DA_De Anza | LOS GATOS 1106 | 3780 | LOS GATOS 110660116 | 0.009827 | 231.4699 | 10.0432 | 0 | 10.0432 | 0 | 5465 | 0 | 0 | 0 | 0 | 0 | 0 | 298 | 1 | 9937 |  | 1794 | 1183 | 9937 | 1794 | 1183 | 3352.11 | 4.2455e-05 | 0.00016 | 2104 | 0.0095893 | 5.3872e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0095893 | 178.6286 | 178.6286 | 0%
Central Valley | ST_Stockton | CALAVERAS CEMENT 1101 | 1263 | CALAVERAS CEMENT 11012646 | 0.029795 | 469.9656 | 17.9869 | 0.30492 | 17.682 | 0.14811 | 1127 | 0 | 0 | 0 | 0 | 0 | 0 | 562 | 0.99177 | 2042 |  | 370 | 245 | 2042 | 370 | 245 | 690.68 | 6.3398e-05 | 5e-05 | 2105 | 0.0092904 | 5.3393e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0091329 | 20.9252 | 20.5705 | 1.695%
North Valley | NV_North Valley | HAMILTON BRANCH 1101 | 6983 | HAMILTON BRANCH 110190334 | 0.004482 | 55.8745 | 1.8587 | 0 | 1.8587 | 0 | 840 | 112 | 11 | 10 | 0 | 0 | 0 | 49 | 1 | 1650 |  | 290 | 195 | 1538 | 290 | 195 | 535.72 | 8.0216e-05 | 5e-05 | 2106 | 0.0014232 | 5.2711e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0014232 | 156.022 | 156.022 | 0%
Central Coast | CC_Central Coast | HOLLISTER 2102 | 5645 | HOLLISTER 2102855412 | 0.14242 | 518.393 | 26.3691 | 0 | 26.3691 | 0 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 284 | 1 | 374 |  | 69 | 47 | 374 | 69 | 47 | 128.19 | 0.00027473 | 4e-05 | 2107 | 0.0019318 | 5.221e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0019318 | 2.6167 | 2.6167 | 0%
Central Coast | CC_Central Coast | ROB ROY 2104 | 1912 | ROB ROY 210410930 | 2.8e-05 | 24.3078 | 1.3265 | 0 | 1.3265 | 0 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1 | 265 |  | 50 | 34 | 265 | 50 | 34 | 92.35 | 1.1519e-06 | 0 | 2108 | 0.00098475 | 5.1829e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00098475 | 37.6927 | 37.6927 | 0%
North Valley | NV_North Valley | CLARK ROAD 1102 | 7528 | CLARK ROAD 11022068 | 0.018394 | 294.5929 | 12.6218 | 4.2339 | 8.3881 | 5.4019 | 916 | 567 | 233 | 193 | 133 | 112 | 0 | 524 | 0.57202 | 1526 |  | 407 | 308 | 959 | 274 | 196 | 461.69 | 6.2439e-05 | 4e-05 | 2109 | 0.0068224 | 5.1296e-05 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0045339 | 32.6654 | 32.2458 | 33.54%
Sierra | SI_Sierra | BRUNSWICK 1106 | 406 | BRUNSWICK 11062796 | 0.067751 | 564.815 | 22.9354 | 0.05 | 22.8854 | 4.6059 | 13231 | 462 | 451 | 298 | 0 | 0 | 0 | 1594 | 0.79918 | 19674 |  | 3917 | 2582 | 19212 | 3917 | 2582 | 7095.37 | 0.00011995 | 0.00098 | 2110 | 0.017607 | 5.0163e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.017569 | 171.157 | 170.7839 | 0.218%
North Valley | NV_North Valley | FRENCH GULCH 1102 | 9005 | FRENCH GULCH 1102circuit_breaker | 0.000704 | 35.4288 | 1.9458 | 0 | 1.9458 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1 | 112 |  | 22 | 16 | 112 | 22 | 16 | 40.22 | 1.9871e-05 | 0 | 2111 | 0.00025069 | 5.0138e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00025069 | 11.3062 | 11.3062 | 0%
Central Valley | KE_Kern | CUYAMA 1103 | 7829 | CUYAMA 1103622728 | 0.040557 | 55.5168 | 3.0104 | 0 | 3.0104 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 1 | 14 |  | 5 | 4 | 14 | 5 | 4 | 8.11 | 0.00073054 | 1e-05 | 2112 | 0.00039992 | 4.999e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00039992 | 1.6609 | 1.6609 | 0%
Bay Area | PE_Peninsula | HALF MOON BAY 1103 | 6134 | HALF MOON BAY 11036012 | 0.004345 | 146.789 | 6.6989 | 3.5369 | 3.1619 | 4.4778 | 2158 | 370 | 106 | 24 | 39 | 10 | 0 | 239 | 0.33155 | 1673 |  | 342 | 180 | 1303 | 303 | 170 | 532.38 | 2.96e-05 | 2e-05 | 2113 | 0.0021516 | 4.89e-05 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0010156 | 95.8275 | 51.0534 | 52.8%
Central Valley | YO_Yosemite | PINECREST 0401 | 6376 | PINECREST 04011818 | 0.006082 | 93.2421 | 4.5905 | 0 | 4.5905 | 0 | 2702 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 1 | 4919 |  | 889 | 587 | 4919 | 889 | 587 | 1660.64 | 6.5228e-05 | 0.00012 | 2114 | 0.0024179 | 4.8358e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0024179 | 193.6595 | 193.6595 | 0%
Central Coast | CC_Central Coast | POINT MORETTI 1101 | 7302 | POINT MORETTI 110136516 | 0.012636 | 94.3184 | 4.0623 | 0 | 4.0623 | 0 | 2853 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 1 | 5193 |  | 939 | 619 | 5193 | 939 | 619 | 1753.8 | 0.00013397 | 0.00026 | 2115 | 0.003279 | 4.7521e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.003279 | 231.1492 | 231.1492 | 0%
Central Coast | SJ_San Jose | LLAGAS 2101 | 7300 | LLAGAS 21011451 | 0.00481 | 126.512 | 6.1492 | 0 | 6.1492 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 1 | 125 |  | 24 | 17 | 125 | 24 | 17 | 44.13 | 3.802e-05 | 0 | 2116 | 0.00079564 | 4.6802e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00079564 | 3.9029 | 3.9029 | 0%
North Valley | NV_North Valley | BIG MEADOWS 2101 | 4887 | BIG MEADOWS 21012474 | 0.008701 | 145.2481 | 8.0845 | 1.8973 | 6.1873 | 5.6591 | 2755 | 3336 | 184 | 181 | 1 | 1 | 0 | 332 | 0.3 | 4841 |  | 456 | 360 | 1505 | 455 | 359 | 758.8 | 5.9904e-05 | 6e-05 | 2117 | 0.0042833 | 4.6558e-05 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0032781 | 73.5376 | 56.4044 | 23.47%
Bay Area | EB_East Bay | VALLEY VIEW 1106 | 7853 | VALLEY VIEW 1106P166 | 0.045509 | 91.2811 | 3.268 | 2.064 | 1.2038 | 3.268 | 585 | 1035 | 760 | 639 | 681 | 583 | 0 | 130 | 0 | 1035 |  | 760 | 639 | 0 | 79 | 56 | 108.23 | 0.00049856 | 8e-05 | 2118 | 0.0022992 | 4.5984e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00084693 | 65.6262 | 232.5587 | 63.16%
Bay Area | NB_North Bay | SAUSALITO 1102 | 7759 | SAUSALITO 11021268 | 0.010629 | 102.7048 | 4.8517 | 0 | 4.8517 | 0 | 323 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 1 | 599 |  | 110 | 73 | 599 | 110 | 73 | 204.61 | 0.00010349 | 2e-05 | 2119 | 0.0019131 | 4.5551e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0019131 | 22.6724 | 22.6724 | 0%
Central Valley | FR_Fresno | DUNLAP 1102 | 9147 | DUNLAP 1102778286 | 0.002431 | 51.7495 | 2.0244 | 0 | 2.0244 | 0 | 1034 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 1 | 1890 |  | 343 | 227 | 1890 | 343 | 227 | 640.01 | 4.6976e-05 | 3e-05 | 2120 | 0.00035677 | 4.4597e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00035677 | 169.4303 | 169.4303 | 0%
Central Valley | YO_Yosemite | MIWUK 1702 | 2475 | MIWUK 17028090 | 0.017537 | 101.3951 | 4.2794 | 0.13636 | 4.1428 | 1.342 | 2491 | 571 | 60 | 49 | 3 | 0 | 0 | 398 | 0.68639 | 3684 |  | 623 | 420 | 3113 | 620 | 420 | 1129.57 | 0.00017296 | 0.00022 | 2121 | 0.0028775 | 4.3598e-05 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0027857 | 149.6571 | 145.5827 | 3.187%
Central Coast | CC_Central Coast | PANOCHE 1103 | 7253 | PANOCHE 11034008 | 0.020404 | 868.1583 | 35.0097 | 0 | 35.0097 | 0 | 278 | 0 | 0 | 0 | 0 | 0 | 0 | 471 | 1 | 517 |  | 95 | 64 | 517 | 95 | 64 | 176.68 | 2.3503e-05 | 0 | 2122 | 0.0019557 | 4.346e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0019557 | 2.7135 | 2.7135 | 0%
Central Valley | ST_Stockton | ELECTRA 1102 | 2429 | ELECTRA 11026014 | 0.016327 | 134.143 | 5.5812 | 0 | 5.5812 | 0 | 315 | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 1 | 584 |  | 107 | 72 | 584 | 107 | 72 | 199.15 | 0.00012171 | 3e-05 | 2123 | 0.001812 | 4.3142e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.001812 | 19.1713 | 19.1713 | 0%
North Valley | NV_North Valley | CRESCENT MILLS 2101 | 3422 | CRESCENT MILLS 21012232 | 0.015783 | 334.2328 | 15.2932 | 0 | 15.2932 | 0 | 7846 | 0 | 0 | 0 | 0 | 0 | 0 | 348 | 1 | 14260 |  | 2574 | 1696 | 14260 | 2574 | 1696 | 4809.78 | 4.7222e-05 | 0.00025 | 2124 | 0.0094184 | 4.3007e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0094184 | 168.3103 | 168.3103 | 0%
Sierra | SI_Sierra | BRUNSWICK 1110 | 6606 | BRUNSWICK 111063100 | 0.005427 | 64.1043 | 3.5799 | 0 | 3.5799 | 3.3538 | 1404 | 439 | 439 | 261 | 0 | 0 | 0 | 169 | 0.063168 | 601 |  | 468 | 280 | 162 | 468 | 280 | 655.74 | 8.4659e-05 | 8e-05 | 2125 | 0.0026702 | 4.2384e-05 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0026702 | 130.729 | 130.729 | 0%
Central Coast | CC_Central Coast | DEL MONTE 2104 | 6218 | DEL MONTE 21043088 | 0.014239 | 367.662 | 15.5419 | 7.7051 | 7.8367 | 12.1973 | 903 | 1534 | 47 | 27 | 10 | 3 | 0 | 324 | 0.21519 | 1890 |  | 112 | 70 | 356 | 102 | 67 | 171.78 | 3.8729e-05 | 1e-05 | 2126 | 0.0085907 | 4.1703e-05 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0043317 | 13.0156 | 7.2063 | 49.58%
Sierra | SI_Sierra | SUMMIT 1102 | 4963 | SUMMIT 11022302 | 0.000658 | 20.8861 | 0.95663 | 0 | 0.95663 | 0 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1 | 237 |  | 45 | 30 | 237 | 45 | 30 | 82.98 | 3.1504e-05 | 0 | 2127 | 0.00049113 | 4.0928e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00049113 | 47.0402 | 47.0402 | 0%
Central Coast | CC_Central Coast | ROB ROY 2104 | 219 | ROB ROY 210410960 | 0.027529 | 411.9951 | 20.0481 | 0 | 20.0481 | 0 | 4117 | 0 | 0 | 0 | 0 | 0 | 0 | 430 | 1 | 7489 |  | 1353 | 892 | 7489 | 1353 | 892 | 2527.62 | 6.6819e-05 | 0.00019 | 2128 | 0.010267 | 4.0107e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.010267 | 67.4877 | 67.4877 | 0%
Central Coast | CC_Central Coast | ROB ROY 2104 | 5636 | ROB ROY 210410954 | 0.005699 | 201.9916 | 6.9991 | 0 | 6.9991 | 0 | 1550 | 0 | 0 | 0 | 0 | 0 | 0 | 183 | 1 | 2827 |  | 512 | 338 | 2827 | 512 | 338 | 955.87 | 2.8214e-05 | 3e-05 | 2129 | 0.0045989 | 3.9646e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0045989 | 73.1528 | 73.1528 | 0%
Sierra | SI_Sierra | WEIMAR 1101 | 3387 | WEIMAR 11012740 | 0.021568 | 440.7675 | 18.7184 | 0 | 18.7184 | 0 | 7309 | 0 | 0 | 0 | 0 | 0 | 0 | 481 | 1 | 13285 |  | 2398 | 1581 | 13285 | 2398 | 1581 | 4480.91 | 4.8933e-05 | 0.00024 | 2130 | 0.011464 | 3.926e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.011464 | 128.1094 | 128.1094 | 0%
Central Valley | ST_Stockton | CALAVERAS CEMENT 1101 | 1216 | CALAVERAS CEMENT 110147968 | 0.025974 | 951.7467 | 41.1733 | 0 | 41.1733 | 0 | 3744 | 0 | 0 | 0 | 0 | 0 | 0 | 1147 | 1 | 6811 |  | 1230 | 811 | 6811 | 1230 | 811 | 2298.09 | 2.7291e-05 | 7e-05 | 2131 | 0.016492 | 3.8622e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.016492 | 29.8737 | 29.8737 | 0%
Central Coast | CC_Central Coast | OTTER 1102 | 7700 | OTTER 1102circuit_breaker | 0.004263 | 150.4449 | 5.9636 | 0 | 5.9636 | 0 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1 | 256 |  | 48 | 33 | 256 | 48 | 33 | 88.8 | 2.8336e-05 | 0 | 2132 | 0.0012667 | 3.8384e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0012667 | 8.0488 | 8.0488 | 0%
Bay Area | DI_Diablo | ROSSMOOR 1101 | 816 | ROSSMOOR 110168920 | 0.005588 | 186.0863 | 8.3951 | 0 | 8.3951 | 0 | 1505 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 1 | 2745 |  | 497 | 328 | 2745 | 497 | 328 | 927.94 | 3.0029e-05 | 3e-05 | 2133 | 0.0035139 | 3.8195e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0035139 | 59.2014 | 59.2014 | 0%
Central Coast | CC_Central Coast | ROB ROY 2105 | 2873 | ROB ROY 210538430 | 0.005661 | 96.8534 | 4.3184 | 0 | 4.3184 | 0 | 915 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 1 | 1674 |  | 304 | 201 | 1674 | 304 | 201 | 567.14 | 5.8449e-05 | 4e-05 | 2134 | 0.0023689 | 3.7601e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0023689 | 70.3969 | 70.3969 | 0%
Central Coast | CC_Central Coast | DEL MONTE 2104 | 5619 | DEL MONTE 21049500 | 0.003218 | 141.4547 | 6.5172 | 2.0983 | 4.4189 | 4.5229 | 351 | 676 | 26 | 17 | 2 | 2 | 0 | 139 | 0.30601 | 875 |  | 62 | 41 | 199 | 60 | 39 | 100.11 | 2.2749e-05 | 0 | 2135 | 0.0026112 | 3.6778e-05 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0017705 | 13.5779 | 9.5132 | 32.2%
Central Valley | YO_Yosemite | SPRING GAP 1702 | 5760 | 693441 | 0.002298 | 74.2271 | 3.6347 | 0 | 3.6347 | 0 | 2548 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 1 | 4639 |  | 839 | 553 | 4639 | 839 | 553 | 1566.94 | 3.0959e-05 | 5e-05 | 2136 | 0.0021602 | 3.429e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0021602 | 230.8332 | 230.8332 | 0%
Sierra | SI_Sierra | HALSEY 1102 | 2346 | HALSEY 110239104 | 0.018272 | 771.63 | 31.9398 | 0 | 31.9398 | 0 | 10776 | 0 | 0 | 0 | 0 | 0 | 0 | 835 | 1 | 19581 |  | 3533 | 2328 | 19581 | 3533 | 2328 | 6602.5 | 2.368e-05 | 0.00017 | 2137 | 0.016481 | 3.4122e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.016481 | 110.6144 | 110.6144 | 0%
Central Coast | SJ_San Jose | SWIFT 2110 | 571 | SWIFT 2110XR332 | 0.044438 | 923.5445 | 43.7547 | 0 | 43.7547 | 0 | 1329 | 0 | 0 | 0 | 0 | 0 | 0 | 578 | 1 | 2426 |  | 439 | 290 | 2426 | 439 | 290 | 819.77 | 4.8117e-05 | 4e-05 | 2138 | 0.0059967 | 3.4072e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0059967 | 10.0332 | 10.0332 | 0%
Bay Area | MI_Mission | JARVIS 1101 | 1047 | JARVIS 1101MR210 | 0.00015 | 11.3346 | 1.2377 | 0 | 1.2377 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 1 | 103 |  | 21 | 14 | 103 | 21 | 14 | 38.04 | 1.3234e-05 | 0 | 2139 | 6.7445e-05 | 3.3723e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.7445e-05 | 16.9671 | 16.9671 | 0%
Bay Area | EB_East Bay | VALLEY VIEW 1106 | 4450 | VALLEY VIEW 1106circuit_breaker | 0.002335 | 65.8872 | 2.7938 | 2.3943 | 0.39943 | 2.7938 | 174 | 361 | 60 | 50 | 3 | 0 | 0 | 76 | 0 | 361 |  | 60 | 50 | 0 | 57 | 50 | 78.09 | 3.5439e-05 | 0 | 2140 | 0.0012527 | 3.2967e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00017911 | 142.7027 | 21.4765 | 85.7%
North Valley | NV_North Valley | FRENCH GULCH 1102 | 4796 | FRENCH GULCH 11021462 | 0.005741 | 208.5013 | 9.6907 | 0 | 9.6907 | 0 | 233 | 0 | 0 | 0 | 0 | 0 | 0 | 197 | 1 | 435 |  | 81 | 54 | 435 | 81 | 54 | 150.12 | 2.7535e-05 | 0 | 2141 | 0.0021314 | 3.279e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0021314 | 8.3585 | 8.3585 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1107 | 3405 | SAN RAFAEL 1107circuit_breaker | 0.000182 | 97.6097 | 4.7996 | 0 | 4.7996 | 0 | 971 | 0 | 0 | 0 | 0 | 0 | 0 | 178 | 1 | 1776 |  | 322 | 213 | 1776 | 322 | 213 | 600.98 | 1.8646e-06 | 0 | 2142 | 0.0023541 | 3.2695e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0023541 | 67.0886 | 67.0886 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1108 | 5230 | SAN RAFAEL 1108circuit_breaker | 0.001479 | 88.748 | 3.9667 | 0 | 3.9667 | 0 | 1058 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 1 | 1934 |  | 351 | 232 | 1934 | 351 | 232 | 654.93 | 1.6665e-05 | 1e-05 | 2143 | 0.00232 | 3.0933e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00232 | 88.4874 | 88.4874 | 0%
Central Coast | CC_Central Coast | LAURELES 1111 | 2988 | LAURELES 1111432 | 0.031845 | 1144.3146 | 49.1449 | 46.6903 | 2.4545 | 49.0348 | 4012 | 4807 | 963 | 217 | 947 | 209 | 0 | 1192 | 0.0022391 | 4823 |  | 966 | 219 | 16 | 19 | 10 | 27.47 | 2.7829e-05 | 0 | 2144 | 0.012664 | 3.0887e-05 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00063248 | 7.7407 | 19.6562 | 95.01%
North Coast | HU_Humboldt | FORT BRAGG A 1102 | 2382 | FORT BRAGG A 110235592 | 0.013255 | 350.473 | 14.3513 | 0 | 14.3513 | 0 | 6872 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 1 | 12492 |  | 2255 | 1486 | 12492 | 2255 | 1486 | 4213.63 | 3.782e-05 | 0.00018 | 2145 | 0.0061655 | 2.8153e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0061655 | 157.1283 | 157.1283 | 0%
Sierra | SI_Sierra | SUMMIT 1102 | 147 | SUMMIT 1102circuit_breaker | 0.000571 | 31.1602 | 0.56951 | 0 | 0.56951 | 0 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1 | 615 |  | 113 | 75 | 615 | 113 | 75 | 210.16 | 1.8325e-05 | 0 | 2146 | 0.00058732 | 2.7968e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00058732 | 198.417 | 198.417 | 0%
Central Valley | YO_Yosemite | PEORIA 1704 | 9546 | PEORIA 170488630 | 0.0011 | 10.9436 | 0.5358 | 0.47027 | 0.065341 | 0.5358 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.00010052 | 0 | 2147 | 8.3796e-05 | 2.7932e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.0219e-05 | 0 | 0 | 87.77%
North Coast | HU_Humboldt | GUALALA 1111 | 6413 | GUALALA 1111887180 | 0.001729 | 114.6803 | 4.7994 | 0 | 4.7994 | 0 | 1911 | 0 | 0 | 0 | 0 | 0 | 0 | 79 | 1 | 3483 |  | 630 | 416 | 3483 | 630 | 416 | 1176.57 | 1.5077e-05 | 2e-05 | 2148 | 0.0017933 | 2.7171e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0017933 | 131.2655 | 131.2655 | 0%
Central Coast | CC_Central Coast | OTTER 1101 | 8206 | OTTER 1101circuit_breaker | 0.004486 | 112.5631 | 5.7203 | 0 | 5.7203 | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 1 | 241 |  | 45 | 31 | 241 | 45 | 31 | 83.34 | 3.9853e-05 | 0 | 2149 | 0.00059489 | 2.5865e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00059489 | 7.8668 | 7.8668 | 0%
North Valley | NV_North Valley | PIT NO 3 2101 | 5225 | PIT NO 3 21011386 | 0.002321 | 128.9301 | 6.7057 | 0 | 6.7057 | 0 | 2804 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 1 | 5104 |  | 923 | 609 | 5104 | 923 | 609 | 1723.87 | 1.8002e-05 | 3e-05 | 2150 | 0.0019902 | 2.5847e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0019902 | 137.6445 | 137.6445 | 0%
Bay Area | DI_Diablo | SOBRANTE 1102 | 3496 | SOBRANTE 1102circuit_breaker | 0.003738 | 260.0872 | 10.6581 | 0 | 10.6581 | 0 | 2155 | 1 | 1 | 1 | 0 | 0 | 0 | 313 | 1 | 3927 |  | 711 | 470 | 3926 | 711 | 470 | 1327.41 | 1.4372e-05 | 2e-05 | 2151 | 0.0038248 | 2.5498e-05 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 6. >50% | 6. >50% | 0.0038248 | 66.7096 | 66.7096 | 0%
Central Valley | ST_Stockton | FROGTOWN 1701 | 1876 | FROGTOWN 17016807 | 0.01411 | 119.7477 | 4.6744 | 0 | 4.6744 | 0 | 447 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 1 | 824 |  | 151 | 100 | 824 | 151 | 100 | 281.03 | 0.00011783 | 4e-05 | 2152 | 0.0018152 | 2.4865e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0018152 | 32.3034 | 32.3034 | 0%
Central Coast | CC_Central Coast | SAN ARDO 1101 | 6692 | SAN ARDO 110193072 | 0.000318 | 14.6032 | 0.85246 | 0 | 0.85246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 2.1776e-05 | 0 | 2153 | 2.4798e-05 | 2.4798e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.4798e-05 | 4.6923 | 4.6923 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2104 | 5099 | CAMP EVERS 2104circuit_breaker | 0.000208 | 11.5913 | 1.2517 | 0 | 1.2517 | 0 | 253 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1 | 472 |  | 87 | 58 | 472 | 87 | 58 | 161.67 | 1.7945e-05 | 0 | 2154 | 0.0003376 | 2.4115e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0003376 | 69.5052 | 69.5052 | 0%
North Coast | HU_Humboldt | GARBERVILLE 1102 | 9664 | GARBERVILLE 11022124 | 3.2231 | 33.1083 | 0.73598 | 0 | 0.73598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.097351 | 0.00081 | 2155 | 2.3974e-05 | 2.3974e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.3974e-05 | 5.4349 | 5.4349 | 0%
Bay Area | DI_Diablo | FAIRVIEW 2207 | 854 | FAIRVIEW 2207M501R | 0.0002 | 45.7553 | 3.865 | 0 | 3.865 | 0 | 324 | 0 | 0 | 0 | 0 | 0 | 0 | 177 | 1 | 601 |  | 110 | 74 | 601 | 110 | 74 | 204.79 | 4.3711e-06 | 0 | 2156 | 0.00076101 | 2.3782e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00076101 | 28.4608 | 28.4608 | 0%
Central Coast | CC_Central Coast | POINT MORETTI 1101 | 8613 | POINT MORETTI 11015074 | 0.10946 | 49.4307 | 2.1017 | 0 | 2.1017 | 0 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 1 | 297 |  | 56 | 38 | 297 | 56 | 38 | 103.45 | 0.0022143 | 0.00026 | 2157 | 0.00025504 | 2.3185e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00025504 | 26.645 | 26.645 | 0%
Central Coast | CC_Central Coast | DEL MONTE 2104 | 7628 | DEL MONTE 21042762 | 0.003351 | 254.2596 | 9.8426 | 5.8267 | 4.0159 | 8.843 | 805 | 1356 | 56 | 24 | 8 | 1 | 0 | 218 | 0.10156 | 1506 |  | 83 | 42 | 150 | 75 | 41 | 116.25 | 1.3179e-05 | 0 | 2158 | 0.0029222 | 2.283e-05 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0011923 | 18.6757 | 8.4327 | 59.2%
North Coast | SO_Sonoma | RINCON 1103 | 1532 | RINCON 1103472 | 0.003316 | 66.6413 | 2.8032 | 0.30379 | 2.4994 | 2.8032 | 250 | 61 | 61 | 4 | 61 | 4 | 0 | 140 | 0 | 61 |  | 61 | 4 | 0 | 0 | 0 | 0 | 4.9759e-05 | 0 | 2159 | 0.00097903 | 2.2768e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00087293 | 0 | 21.7607 | 10.84%
Central Coast | CC_Central Coast | LOS OSITOS 2103 | 1431 | LOS OSITOS 21033010 | 0.031023 | 701.8146 | 29.4297 | 0 | 29.4297 | 0 | 1194 | 16 | 1 | 0 | 1 | 0 | 0 | 416 | 1 | 2197 |  | 396 | 261 | 2181 | 395 | 261 | 737.44 | 4.4204e-05 | 4e-05 | 2160 | 0.0001064 | 2.1279e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0001064 | 13.4218 | 13.4558 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2106 | 7288 | CAMP EVERS 210616000 | 0.002995 | 59.1944 | 2.182 | 0 | 2.182 | 0 | 1332 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 1 | 2431 |  | 440 | 291 | 2431 | 440 | 291 | 821.59 | 5.0596e-05 | 5e-05 | 2161 | 0.00077994 | 2.1079e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00077994 | 201.6492 | 201.6492 | 0%
North Coast | HU_Humboldt | ELK 1101 | 5169 | ELK 11011300 | 0.001399 | 44.5297 | 4.3358 | 0 | 4.3358 | 0 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 1 | 406 |  | 75 | 50 | 406 | 75 | 50 | 139.29 | 3.1417e-05 | 0 | 2162 | 0.00039907 | 2.1004e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00039907 | 17.2979 | 17.2979 | 0%
Central Coast | CC_Central Coast | HOLLISTER 2105 | 606 | HOLLISTER 21054724 | 0.001404 | 88.4632 | 5.1339 | 0 | 5.1339 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 1 | 105 |  | 21 | 15 | 105 | 21 | 15 | 38.22 | 1.5871e-05 | 0 | 2163 | 0.00020605 | 2.0605e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00020605 | 4.0905 | 4.0905 | 0%
Central Coast | CC_Central Coast | COAST RD 0401 | 8776 | COAST RD 04015134 | 0.000446 | 9.867 | 0.49773 | 0 | 0.49773 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 21 |  | 6 | 5 | 21 | 6 | 5 | 10.11 | 4.5201e-05 | 0 | 2164 | 4.0025e-05 | 2.0012e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.0025e-05 | 12.0548 | 12.0548 | 0%
Central Valley | ST_Stockton | ELECTRA 1102 | 6856 | ELECTRA 1102circuit_breaker | 0.001439 | 57.0143 | 2.7307 | 0 | 2.7307 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 1 | 94 |  | 19 | 13 | 94 | 19 | 13 | 34.49 | 2.5239e-05 | 0 | 2165 | 0.00061191 | 1.9122e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00061191 | 6.958 | 6.958 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2105 | 4629 | CAMP EVERS 210574170 | 0.000397 | 82.3888 | 3.7261 | 0 | 3.7261 | 0 | 3031 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 1 | 5516 |  | 997 | 658 | 5516 | 997 | 658 | 1862.33 | 4.8186e-06 | 1e-05 | 2167 | 0.00089567 | 1.866e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00089567 | 267.5694 | 267.5694 | 0%
Bay Area | EB_East Bay | SPRUCE 0401 | 2007 | SPRUCE 0401BR316 | 0.000846 | 101.7675 | 6.1669 | 0 | 6.1669 | 0 | 424 | 0 | 0 | 0 | 0 | 0 | 0 | 262 | 1 | 782 |  | 143 | 95 | 782 | 143 | 95 | 266.29 | 8.3131e-06 | 0 | 2168 | 0.00088523 | 1.8066e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00088523 | 23.1885 | 23.1885 | 0%
North Valley | NV_North Valley | FRENCH GULCH 1101 | 7834 | FRENCH GULCH 11011464 | 0.025826 | 23.8288 | 1.1009 | 0 | 1.1009 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 1 | 56 |  | 12 | 9 | 56 | 12 | 9 | 21.48 | 0.0010838 | 3e-05 | 2169 | 0.00014311 | 1.7889e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00014311 | 10.8997 | 10.8997 | 0%
Sierra | SI_Sierra | HALSEY 1102 | 2075 | HALSEY 11025739 | 0.003169 | 167.9545 | 6.8191 | 0 | 6.8191 | 0 | 1308 | 0 | 0 | 0 | 0 | 0 | 0 | 162 | 1 | 2388 |  | 433 | 286 | 2388 | 433 | 286 | 808.13 | 1.8868e-05 | 2e-05 | 2170 | 0.0018105 | 1.775e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0018105 | 63.4978 | 63.4978 | 0%
Central Coast | CC_Central Coast | RESERVATION ROAD 1102 | 4261 | RESERVATION ROAD 110222136 | 0.000421 | 26.9435 | 2.1277 | 0 | 2.1277 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 1 | 165 |  | 32 | 22 | 165 | 32 | 22 | 58.69 | 1.5625e-05 | 0 | 2171 | 0.00017726 | 1.7726e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00017726 | 15.0401 | 15.0401 | 0%
Central Coast | CC_Central Coast | GABILAN 1101 | 732 | GABILAN 11013034 | 0.000236 | 5.0021 | 0.3947 | 0 | 0.3947 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 32 |  | 8 | 6 | 32 | 8 | 6 | 13.84 | 4.718e-05 | 0 | 2173 | 3.4746e-05 | 1.7373e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.4746e-05 | 20.2687 | 20.2687 | 0%
Central Coast | CC_Central Coast | BEN LOMOND 0401 | 5747 | BEN LOMOND 0401circuit_breaker | 0.000962 | 130.6891 | 5.9869 | 0 | 5.9869 | 0 | 3143 | 0 | 0 | 0 | 0 | 0 | 0 | 206 | 1 | 5720 |  | 1034 | 682 | 5720 | 1034 | 682 | 1931.38 | 7.361e-06 | 2e-05 | 2176 | 0.0013043 | 1.7162e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0013043 | 172.7095 | 172.7095 | 0%
Central Coast | SJ_San Jose | MILPITAS 1109 | 8949 | MILPITAS 1109XR044 | 3.8e-05 | 4.739 | 1.0206 | 0 | 1.0206 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1 | 128 |  | 25 | 17 | 128 | 25 | 17 | 45.77 | 8.0187e-06 | 0 | 2177 | 3.3191e-05 | 1.6595e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.3191e-05 | 24.4943 | 24.4943 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2105 | 923 | CAMP EVERS 210511384 | 0.000946 | 143.0849 | 7.6358 | 0 | 7.6358 | 0 | 3585 | 0 | 0 | 0 | 0 | 0 | 0 | 251 | 1 | 6523 |  | 1178 | 777 | 6523 | 1178 | 777 | 2200.93 | 6.6115e-06 | 2e-05 | 2180 | 0.00099352 | 1.6287e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00099352 | 154.2734 | 154.2734 | 0%
North Coast | NC_North Coast | RIO DELL 1102 | 9616 | RIO DELL 11027124 | 0.013901 | 13.0071 | 0.6089 | 0 | 0.6089 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1 | 40 |  | 9 | 7 | 40 | 9 | 7 | 15.93 | 0.0010687 | 2e-05 | 2182 | 1.5991e-05 | 1.5991e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.5991e-05 | 14.7807 | 14.7807 | 0%
Sierra | SI_Sierra | ALLEGHANY 1101 | 5464 | ALLEGHANY 1101978 | 0.005923 | 237.6354 | 13.8256 | 0 | 13.8256 | 0 | 6653 | 0 | 0 | 0 | 0 | 0 | 0 | 297 | 1 | 12094 |  | 2183 | 1439 | 12094 | 2183 | 1439 | 4079.17 | 2.4925e-05 | 0.00011 | 2184 | 0.0020436 | 1.5966e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0020436 | 157.8959 | 157.8959 | 0%
North Valley | NV_North Valley | CHESTER 1101 | 3444 | CHESTER 1101circuit_breaker | 0.001415 | 58.9502 | 2.2473 | 0 | 2.2473 | 0 | 710 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 1 | 1302 |  | 237 | 157 | 1302 | 237 | 157 | 441.87 | 2.4003e-05 | 1e-05 | 2185 | 0.00045133 | 1.5563e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00045133 | 105.4576 | 105.4576 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1106 | 16 | SAN RAFAEL 1106910 | 0.00118 | 77.8857 | 3.1051 | 0 | 3.1051 | 0 | 385 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 1 | 711 |  | 130 | 87 | 711 | 130 | 87 | 242.09 | 1.515e-05 | 0 | 2186 | 0.00031109 | 1.5554e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00031109 | 41.8664 | 41.8664 | 0%
Central Coast | DA_De Anza | SARATOGA 1105 | 3733 | SARATOGA 1105LC14 | 0.002617 | 247.7308 | 9.215 | 0 | 9.215 | 0 | 1186 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 1 | 2166 |  | 393 | 260 | 2166 | 393 | 260 | 733.35 | 1.0564e-05 | 1e-05 | 2187 | 0.0022075 | 1.5546e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0022075 | 42.648 | 42.648 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2105 | 6797 | CAMP EVERS 210510786 | 0.000391 | 87.3353 | 3.1983 | 0 | 3.1983 | 0 | 2908 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 1 | 5293 |  | 957 | 631 | 5293 | 957 | 631 | 1787.46 | 4.477e-06 | 1e-05 | 2188 | 0.0012064 | 1.5467e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0012064 | 299.2219 | 299.2219 | 0%
North Coast | HU_Humboldt | EEL RIVER 1103 | 5172 | EEL RIVER 11033820 | 0.007963 | 56.7351 | 3.2549 | 2.2701 | 0.98485 | 3.2549 | 407 | 791 | 187 | 89 | 133 | 63 | 0 | 51 | 0 | 791 |  | 187 | 89 | 0 | 54 | 26 | 73.98 | 0.00014035 | 2e-05 | 2189 | 1.5374e-05 | 1.5374e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.6517e-06 | 54.8308 | 57.4514 | 69.74%
Bay Area | EB_East Bay | WALDO 0402 | 898 | WALDO 0402circuit_breaker | 1e-06 | 8.5941 | 0.86345 | 0 | 0.86345 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 1 | 34 |  | 8 | 6 | 34 | 8 | 6 | 14.02 | 1.1636e-07 | 0 | 2190 | 0.00050542 | 1.5316e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00050542 | 9.2652 | 9.2652 | 0%
Central Coast | CC_Central Coast | DEL MONTE 2104 | 8058 | DEL MONTE 210436720 | 0.002763 | 121.9725 | 5.6638 | 0 | 5.6638 | 0 | 743 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 1 | 1362 |  | 248 | 164 | 1362 | 248 | 164 | 462.34 | 2.2653e-05 | 1e-05 | 2191 | 0.0012372 | 1.5088e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0012372 | 43.7867 | 43.7867 | 0%
Central Coast | CC_Central Coast | GONZALES 1101 | 2449 | GONZALES 11013094 | 0.004151 | 105.8662 | 4.0536 | 0 | 4.0536 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 1 | 87 |  | 18 | 13 | 87 | 18 | 13 | 32.49 | 3.921e-05 | 0 | 2192 | 0.00018099 | 1.5082e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00018099 | 4.4405 | 4.4405 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2105 | 7211 | CAMP EVERS 210611006 | 0.000397 | 53.4803 | 3.3256 | 0 | 3.3256 | 0 | 1293 | 0 | 0 | 0 | 0 | 0 | 0 | 179 | 1 | 2360 |  | 428 | 283 | 2360 | 428 | 283 | 798.76 | 7.4233e-06 | 1e-05 | 2193 | 0.00040085 | 1.4846e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00040085 | 128.6998 | 128.6998 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2105 | 3271 | CAMP EVERS 21055146 | 0.001198 | 136.7576 | 6.5027 | 0 | 6.5027 | 0 | 2029 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 1 | 3697 |  | 669 | 441 | 3697 | 669 | 441 | 1249.26 | 8.76e-06 | 1e-05 | 2196 | 0.0012694 | 1.459e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0012694 | 102.8811 | 102.8811 | 0%
Central Coast | CC_Central Coast | BIG BASIN 1101 | 463 | BIG BASIN 11015028 | 0.000741 | 120.6526 | 5.6926 | 0.027841 | 5.6648 | 4.2998 | 2990 | 260 | 249 | 102 | 26 | 13 | 0 | 395 | 0.24467 | 1591 |  | 490 | 261 | 1331 | 464 | 248 | 755.47 | 6.1416e-06 | 1e-05 | 2197 | 0.0010466 | 1.4337e-05 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0010415 | 81.9097 | 86.0765 | 0.4891%
North Valley | NV_North Valley | PARADISE 1101 | 3377 | PARADISE 11061212 | 0.000399 | 230.0341 | 10.2004 | 4.6259 | 5.5744 | 9.9485 | 1808 | 2404 | 634 | 607 | 391 | 371 | 0 | 703 | 0.024695 | 2485 |  | 649 | 617 | 81 | 258 | 246 | 360.75 | 1.7345e-06 | 0 | 2198 | 0.00012857 | 1.4286e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.0263e-05 | 46.2827 | 63.6251 | 45.35%
North Valley | NV_North Valley | VOLTA 1101 | 4273 | VOLTA 11011516 | 4.955 | 516.3093 | 25.4894 | 0 | 25.4894 | 0 | 1539 | 0 | 0 | 0 | 0 | 0 | 0 | 431 | 1 | 2807 |  | 508 | 336 | 2807 | 508 | 336 | 948.59 | 0.009597 | 0.01014 | 2199 | 2.8354e-05 | 1.4177e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 4. >30 - 40% | 2.8354e-05 | 19.9299 | 19.9299 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2106 | 5106 | CAMP EVERS 21061625 | 0.011059 | 28.0581 | 1.1201 | 0 | 1.1201 | 0 | 1053 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 1 | 1924 |  | 349 | 231 | 1924 | 349 | 231 | 651.29 | 0.00039415 | 0.00029 | 2200 | 0.00022095 | 1.3809e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00022095 | 311.5861 | 311.5861 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2105 | 125 | CAMP EVERS 21055232 | 0.000424 | 94.6851 | 4.8676 | 0 | 4.8676 | 0 | 2762 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 1 | 5028 |  | 909 | 600 | 5028 | 909 | 600 | 1697.85 | 4.478e-06 | 1e-05 | 2201 | 0.00090985 | 1.3786e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00090985 | 186.7445 | 186.7445 | 0%
North Coast | SO_Sonoma | MONTE RIO 1111 | 1735 | MONTE RIO 111264682 | 0.00614 | 41.2418 | 2.508 | 0.027841 | 2.4801 | 1.5428 | 1658 | 292 | 287 | 100 | 104 | 0 | 0 | 285 | 0.38484 | 1455 |  | 498 | 239 | 1163 | 394 | 239 | 644.45 | 0.00014888 | 0.00012 | 2202 | 0.00037406 | 1.3359e-05 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00036991 | 158.8637 | 198.5682 | 1.11%
Sierra | SI_Sierra | PLACERVILLE 2106 | 1440 | PLACERVILLE 210619732 | 0.001636 | 151.7326 | 7.9405 | 0 | 7.9405 | 0 | 1783 | 0 | 0 | 0 | 0 | 0 | 0 | 673 | 1 | 3250 |  | 588 | 388 | 3250 | 588 | 388 | 1098.06 | 1.0782e-05 | 1e-05 | 2203 | 0.0017725 | 1.3327e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0017725 | 74.0505 | 74.0505 | 0%
Bay Area | PE_Peninsula | HALF MOON BAY 1102 | 4517 | HALF MOON BAY 1102circuit_breaker | 0.000553 | 2.0929 | 0.88561 | 0 | 0.88561 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 1 | 14 |  | 5 | 4 | 14 | 5 | 4 | 8.11 | 0.00026423 | 0 | 2204 | 1.3323e-05 | 1.3323e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.3323e-05 | 5.6459 | 5.6459 | 0%
Central Coast | CC_Central Coast | SOLEDAD 2102 | 3806 | SOLEDAD 210242506 | 0.00416 | 210.5584 | 9.8985 | 0 | 9.8985 | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 142 | 1 | 248 |  | 47 | 32 | 248 | 47 | 32 | 86.71 | 1.9757e-05 | 0 | 2205 | 0.00046337 | 1.3239e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00046337 | 4.7482 | 4.7482 | 0%
Central Coast | CC_Central Coast | SAN ARDO 1101 | 8034 | SAN ARDO 11017094 | 0.000392 | 30.3036 | 2.0074 | 0 | 2.0074 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1 | 20 |  | 5 | 5 | 20 | 5 | 5 | 8.65 | 1.2936e-05 | 0 | 2206 | 9.262e-05 | 1.3231e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.262e-05 | 2.4908 | 2.4908 | 0%
Central Coast | CC_Central Coast | HOLLISTER 2104 | 6732 | HOLLISTER 21044403 | 0.003796 | 94.543 | 5.7886 | 0 | 5.7886 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 1 | 150 |  | 29 | 20 | 150 | 29 | 20 | 53.23 | 4.0151e-05 | 0 | 2207 | 0.00010574 | 1.3218e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00010574 | 5.0098 | 5.0098 | 0%
Central Coast | CC_Central Coast | LAURELES 1112 | 5667 | LAURELES 11122768 | 0.001741 | 108.1228 | 5.1744 | 0 | 5.1744 | 0 | 379 | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 1 | 701 |  | 128 | 85 | 701 | 128 | 85 | 238.45 | 1.6102e-05 | 0 | 2208 | 0.0011748 | 1.3053e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0011748 | 24.737 | 24.737 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2105 | 632 | CAMP EVERS 210511004 | 0.039442 | 152.1044 | 7.5638 | 0 | 7.5638 | 0 | 1340 | 0 | 0 | 0 | 0 | 0 | 0 | 183 | 1 | 2446 |  | 443 | 293 | 2446 | 443 | 293 | 827.05 | 0.00025931 | 0.00024 | 2209 | 0.00091536 | 1.2892e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00091536 | 58.5682 | 58.5682 | 0%
North Valley | NV_North Valley | PARADISE 1101 | 5274 | PARADISE 1106circuit_breaker | 0.000676 | 231.2939 | 11.6627 | 4.4193 | 7.2434 | 11.0875 | 1784 | 2573 | 982 | 950 | 554 | 529 | 0 | 816 | 0.049319 | 2733 |  | 1011 | 969 | 160 | 457 | 440 | 640.49 | 2.9227e-06 | 0 | 2210 | 0.00011587 | 1.2875e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.1966e-05 | 63.0922 | 86.6867 | 37.89%
Bay Area | NB_North Bay | CALISTOGA 1102 | 2058 | CALISTOGA 1102706 | 0.033076 | 13.4856 | 0.9839 | 0.21951 | 0.76458 | 0.44186 | 197 | 239 | 57 | 10 | 35 | 3 | 0 | 66 | 0.55091 | 443 |  | 95 | 35 | 204 | 60 | 32 | 100.56 | 0.0024527 | 0.00031 | 2211 | 5.0612e-05 | 1.2653e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.933e-05 | 78.4741 | 96.5544 | 22.31%
North Coast | SO_Sonoma | FULTON 1104 | 5186 | FULTON 1104466 | 0.040089 | 14.7839 | 0.32064 | 0 | 0.32064 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 30 |  | 7 | 6 | 30 | 7 | 6 | 12.29 | 0.0027117 | 4e-05 | 2212 | 3.7728e-05 | 1.2576e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.7728e-05 | 21.8311 | 21.8311 | 0%
North Valley | NV_North Valley | ANTLER 1101 | 5356 | ANTLER 11011384 | 0.001272 | 170.1127 | 8.8977 | 0 | 8.8977 | 0 | 2870 | 0 | 0 | 0 | 0 | 0 | 0 | 253 | 1 | 5224 |  | 944 | 623 | 5224 | 944 | 623 | 1763.44 | 7.4774e-06 | 1e-05 | 2214 | 0.0015406 | 1.2227e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0015406 | 106.0945 | 106.0945 | 0%
Bay Area | NB_North Bay | SILVERADO 2105 | 4394 | SILVERADO 2105circuit_breaker | 0.010057 | 36.6763 | 0.39223 | 0.30455 | 0.087689 | 0.39223 | 85 | 194 | 54 | 19 | 33 | 10 | 0 | 28 | 0 | 194 |  | 54 | 19 | 0 | 21 | 9 | 28.77 | 0.00027421 | 1e-05 | 2218 | 0.00012123 | 1.2123e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.7103e-05 | 239.4816 | 137.6726 | 77.64%
Central Coast | CC_Central Coast | CAMP EVERS 2106 | 5648 | CAMP EVERS 210611044 | 0.001215 | 194.1685 | 9.9686 | 0 | 9.9686 | 0.29981 | 4092 | 0 | 0 | 0 | 0 | 0 | 0 | 508 | 0.96992 | 7219 |  | 1304 | 860 | 7219 | 1304 | 860 | 2436.19 | 6.2575e-06 | 2e-05 | 2219 | 0.0012239 | 1.2118e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0012239 | 130.8113 | 130.8113 | 0%
Bay Area | PE_Peninsula | WOODSIDE 1104 | 6410 | WOODSIDE 11043583 | 0.003194 | 79.6369 | 2.558 | 0 | 2.558 | 0 | 1479 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 1 | 2698 |  | 489 | 323 | 2698 | 489 | 323 | 912.75 | 4.0107e-05 | 4e-05 | 2221 | 0.00045963 | 1.1785e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00045963 | 191.1684 | 191.1684 | 0%
North Valley | NV_North Valley | ANTLER 1101 | 3011 | ANTLER 1101circuit_breaker | 0.000151 | 22.0361 | 0.90038 | 0 | 0.90038 | 0 | 328 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 1 | 608 |  | 112 | 74 | 608 | 112 | 74 | 208.16 | 6.8524e-06 | 0 | 2222 | 0.00018747 | 1.1717e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00018747 | 124.3921 | 124.3921 | 0%
Sierra | SI_Sierra | SHINGLE SPRINGS 2108 | 1978 | SHINGLE SPRINGS 210851474 | 0.16103 | 8.7892 | 0.49697 | 0 | 0.49697 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1 | 110 |  | 22 | 15 | 110 | 22 | 15 | 40.04 | 0.018321 | 0.00084 | 2225 | 2.3182e-05 | 1.1591e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.3182e-05 | 44.2683 | 44.2683 | 0%
Bay Area | PE_Peninsula | WOODSIDE 1101 | 4979 | WOODSIDE 11018522 | 0.000303 | 52.0477 | 1.9278 | 1.304 | 0.62405 | 1.5106 | 1102 | 2026 | 675 | 331 | 616 | 317 | 1 | 162 | 0.21643 | 2462 |  | 754 | 383 | 436 | 138 | 66 | 228.3 | 5.8216e-06 | 0 | 2226 | 0.00035924 | 1.1588e-05 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00011629 | 221.1351 | 391.1111 | 67.64%
Bay Area | NB_North Bay | SAUSALITO 1102 | 6764 | SAUSALITO 11021500 | 0.010907 | 25.0189 | 1.657 | 0 | 1.657 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 1 | 150 |  | 29 | 20 | 150 | 29 | 20 | 53.23 | 0.00043595 | 3e-05 | 2227 | 6.9038e-05 | 1.1506e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.9038e-05 | 17.5014 | 17.5014 | 0%
North Coast | HU_Humboldt | FRUITLAND 1141 | 8385 | FRUITLAND 11418746 | 0.12398 | 20.9991 | 1.1326 | 0 | 1.1326 | 0.50114 | 517 | 173 | 173 | 39 | 93 | 18 | 0 | 33 | 0.55753 | 703 |  | 270 | 103 | 530 | 177 | 85 | 290.19 | 0.0059039 | 0.00217 | 2228 | 3.4329e-05 | 1.1443e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.4329e-05 | 156.2809 | 238.3946 | 0%
Bay Area | PE_Peninsula | WOODSIDE 1101 | 7215 | WOODSIDE 11012299 | 0.000263 | 38.8659 | 1.8223 | 1.3131 | 0.50909 | 1.5491 | 482 | 1185 | 368 | 151 | 343 | 149 | 0 | 136 | 0.14997 | 1318 |  | 392 | 167 | 133 | 49 | 18 | 79.1 | 6.7669e-06 | 0 | 2229 | 0.00036334 | 1.1354e-05 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0001015 | 96.25 | 215.107 | 72.05%
Central Coast | SJ_San Jose | LLAGAS 2106 | 3490 | LLAGAS 2106XR146 | 0.00026 | 26.4473 | 1.6955 | 0 | 1.6955 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1 | 38 |  | 9 | 7 | 38 | 9 | 7 | 15.75 | 9.8309e-06 | 0 | 2230 | 1.1152e-05 | 1.1152e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.1152e-05 | 5.3083 | 5.3083 | 0%
North Coast | SO_Sonoma | MONTE RIO 1111 | 2826 | MONTE RIO 11111701 | 0.000156 | 34.7648 | 1.0231 | 0.014962 | 1.0081 | 1.0231 | 686 | 237 | 228 | 77 | 105 | 9 | 0 | 102 | 0 | 237 |  | 228 | 77 | 0 | 123 | 68 | 168.51 | 4.4873e-06 | 0 | 2232 | 0.0002839 | 1.0919e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00027975 | 122.0064 | 222.8508 | 1.462%
Sierra | SI_Sierra | BRUNSWICK 1107 | 546 | BRUNSWICK 110750008 | 0.000187 | 67.093 | 3.3057 | 0.016667 | 3.289 | 0.13277 | 951 | 39 | 39 | 27 | 0 | 0 | 0 | 121 | 0.95984 | 1708 |  | 342 | 227 | 1669 | 342 | 227 | 618.75 | 2.7872e-06 | 0 | 2234 | 0.00042903 | 1.0726e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00042687 | 103.9825 | 103.4582 | 0.5042%
Central Coast | CC_Central Coast | CAMP EVERS 2106 | 8373 | CAMP EVERS 2106circuit_breaker | 5.8e-05 | 11.6941 | 0.42367 | 0 | 0.42367 | 0 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1 | 499 |  | 92 | 61 | 499 | 92 | 61 | 170.95 | 4.9598e-06 | 0 | 2235 | 0.00010592 | 1.0592e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00010592 | 217.148 | 217.148 | 0%
Central Coast | CC_Central Coast | POINT MORETTI 1101 | 5867 | POINT MORETTI 110139126 | 0.00043 | 94.989 | 3.5314 | 0 | 3.5314 | 0 | 2171 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 1 | 3955 |  | 715 | 472 | 3955 | 715 | 472 | 1335.5 | 4.5268e-06 | 1e-05 | 2236 | 0.00047994 | 1.0434e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00047994 | 202.467 | 202.467 | 0%
North Coast | HU_Humboldt | WILLOW CREEK 1103 | 7098 | WILLOW CREEK 1103circuit_breaker | 0.000378 | 62.8476 | 3.4231 | 0 | 3.4231 | 0 | 622 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 1 | 1142 |  | 208 | 138 | 1142 | 208 | 138 | 387.74 | 6.0145e-06 | 0 | 2237 | 0.00017537 | 1.0316e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00017537 | 60.7635 | 60.7635 | 0%
Sierra | SI_Sierra | CLARKSVILLE 2109 | 8182 | CLARKSVILLE 210951744 | 0.21827 | 34.0227 | 1.8841 | 0.5464 | 1.3377 | 0.5464 | 223 | 55 | 8 | 7 | 8 | 7 | 0 | 55 | 0.70999 | 351 |  | 63 | 44 | 296 | 55 | 37 | 101.99 | 0.0064155 | 0.00073 | 2238 | 0.00014301 | 1.0215e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00010154 | 41.1157 | 33.4379 | 29%
Central Coast | CC_Central Coast | CAMP EVERS 2103 | 3714 | CAMP EVERS 210355638 | 0.000201 | 32.069 | 1.142 | 0 | 1.142 | 0.41326 | 579 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0.63814 | 679 |  | 124 | 82 | 679 | 124 | 82 | 230.99 | 6.2677e-06 | 0 | 2239 | 0.00027507 | 1.0188e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00027507 | 108.5771 | 108.5771 | 0%
North Coast | SO_Sonoma | MONTE RIO 1113 | 6059 | MONTE RIO 1113250 | 0.013823 | 36.6657 | 1.6631 | 0.053788 | 1.6093 | 0.69735 | 900 | 2 | 2 | 1 | 0 | 0 | 0 | 106 | 0.58069 | 958 |  | 176 | 116 | 956 | 176 | 116 | 327.16 | 0.000377 | 0.00014 | 2240 | 0.00020365 | 1.0183e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00019707 | 109.3657 | 105.8285 | 3.234%
Central Valley | ST_Stockton | WEST POINT 1101 | 7192 | WEST POINT 1101L2219 | 0.00264 | 137.0314 | 5.6104 | 0 | 5.6104 | 0.32784 | 3424 | 62 | 62 | 52 | 38 | 29 | 0 | 404 | 0.94157 | 5928 |  | 1122 | 751 | 5866 | 1084 | 722 | 2013.02 | 1.9266e-05 | 4e-05 | 2241 | 1.0153e-05 | 1.0153e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.0153e-05 | 193.212 | 199.9851 | 0%
Bay Area | PE_Peninsula | WOODSIDE 1104 | 388 | WOODSIDE 11049032 | 0.026852 | 108.9404 | 5.9718 | 0 | 5.9718 | 0 | 2437 | 0 | 0 | 0 | 0 | 0 | 0 | 188 | 1 | 4438 |  | 802 | 529 | 4438 | 802 | 529 | 1498.16 | 0.00024648 | 0.00041 | 2242 | 0.0002828 | 1.01e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0002828 | 134.2983 | 134.2983 | 0%
North Coast | SO_Sonoma | MONTE RIO 1112 | 7484 | MONTE RIO 1112212 | 0.010001 | 35.7053 | 1.3206 | 0 | 1.3206 | 0.34583 | 812 | 78 | 78 | 23 | 0 | 0 | 0 | 83 | 0.73813 | 1175 |  | 277 | 155 | 1097 | 277 | 155 | 478.22 | 0.0002801 | 0.00016 | 2243 | 0.00035327 | 1.0093e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00035327 | 209.7462 | 209.7462 | 0%
North Valley | NV_North Valley | PARADISE 1104 | 3669 | PARADISE 1104920400 | 0.79561 | 187.1164 | 19.1756 | 2.7023 | 16.4731 | 7.9837 | 1092 | 1299 | 635 | 618 | 391 | 385 | 0 | 1179 | 0.58365 | 2464 |  | 846 | 758 | 1165 | 455 | 373 | 728.2 | 0.004252 | 0.00402 | 2245 | 2.9841e-05 | 9.9469e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 2.5635e-05 | 27.6208 | 44.1186 | 14.09%
North Coast | HU_Humboldt | BIG RIVER 1101 | 1812 | BIG RIVER 11013002 | 0.004154 | 187.7165 | 8.3284 | 0 | 8.3284 | 0 | 4009 | 0 | 0 | 0 | 0 | 0 | 0 | 174 | 1 | 7292 |  | 1317 | 869 | 7292 | 1317 | 869 | 2460.57 | 2.2129e-05 | 6e-05 | 2247 | 0.0010741 | 9.59e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0010741 | 158.1334 | 158.1334 | 0%
Central Valley | ST_Stockton | WEST POINT 1101 | 6857 | WEST POINT 1101L373 | 0.2301 | 230.2718 | 8.5504 | 0 | 8.5504 | 0 | 5610 | 0 | 0 | 0 | 0 | 0 | 0 | 512 | 1 | 10200 |  | 1842 | 1214 | 10200 | 1842 | 1214 | 3441.54 | 0.00099926 | 0.00383 | 2249 | 1.9067e-05 | 9.5334e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.9067e-05 | 215.4291 | 215.4291 | 0%
Bay Area | NB_North Bay | SILVERADO 2105 | 722 | SILVERADO 21051308 | 9.8e-05 | 14.1854 | 0.43712 | 0.29886 | 0.13845 | 0.43712 | 77 | 201 | 97 | 45 | 75 | 33 | 0 | 42 | 0 | 201 |  | 97 | 45 | 0 | 22 | 12 | 30.14 | 6.9085e-06 | 0 | 2250 | 7.6068e-05 | 9.5085e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.4093e-05 | 158.9056 | 221.9064 | 68.37%
Central Coast | CC_Central Coast | CAMPHORA 1101 | 3911 | CAMPHORA 110177978 | 0.000474 | 50.8284 | 3.7002 | 0 | 3.7002 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1 | 21 |  | 6 | 5 | 21 | 6 | 5 | 10.11 | 9.3255e-06 | 0 | 2251 | 5.6948e-05 | 9.4913e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.6948e-05 | 1.6215 | 1.6215 | 0%
Sierra | SI_Sierra | SHINGLE SPRINGS 2105 | 3631 | SHINGLE SPRINGS 210511172 | 0.35486 | 75.3164 | 3.1513 | 0 | 3.1513 | 0 | 313 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 1 | 581 |  | 107 | 71 | 581 | 107 | 71 | 198.88 | 0.0047115 | 0.00105 | 2252 | 0.0002814 | 9.3801e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0002814 | 33.954 | 33.954 | 0%
Sierra | SI_Sierra | BRUNSWICK 1104 | 8165 | BRUNSWICK 111094368 | 0.002197 | 31.5839 | 0.54318 | 0 | 0.54318 | 0.059659 | 166 | 10 | 10 | 7 | 0 | 0 | 0 | 24 | 0.89017 | 289 |  | 62 | 42 | 279 | 62 | 42 | 110.05 | 6.9561e-05 | 1e-05 | 2253 | 2.802e-05 | 9.3401e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.802e-05 | 114.1423 | 114.1423 | 0%
Central Valley | FR_Fresno | DUNLAP 1103 | 3927 | DUNLAP 11037080 | 0.001615 | 226.1486 | 9.6542 | 0 | 9.6542 | 0 | 4290 | 0 | 0 | 0 | 0 | 0 | 0 | 278 | 1 | 7803 |  | 1409 | 929 | 7803 | 1409 | 929 | 2632.6 | 7.1413e-06 | 2e-05 | 2254 | 0.00095088 | 9.3224e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00095088 | 145.9473 | 145.9473 | 0%
Central Coast | CC_Central Coast | PAUL SWEET 2102 | 6393 | PAUL SWEET 21025291 | 0.000239 | 61.6541 | 3.3477 | 0 | 3.3477 | 0 | 1675 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1 | 3054 |  | 553 | 365 | 3054 | 553 | 365 | 1032.47 | 3.8765e-06 | 0 | 2255 | 0.00051059 | 9.2835e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00051059 | 165.1867 | 165.1867 | 0%
North Valley | NV_North Valley | HAMILTON BRANCH 1101 | 1503 | HAMILTON BRANCH 1101circuit_breaker | 0.001031 | 69.1533 | 3.3593 | 0 | 3.3593 | 0 | 907 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 1 | 1659 |  | 301 | 199 | 1659 | 301 | 199 | 561.68 | 1.4909e-05 | 1e-05 | 2256 | 0.00026488 | 9.1338e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00026488 | 89.6025 | 89.6025 | 0%
North Coast | HU_Humboldt | WILLOW CREEK 1103 | 4802 | WILLOW CREEK 11035012 | 0.000949 | 223.5257 | 11.1765 | 0 | 11.1765 | 0.30057 | 4204 | 64 | 64 | 2 | 0 | 0 | 0 | 397 | 0.97311 | 7505 |  | 1408 | 888 | 7441 | 1408 | 888 | 2598.65 | 4.2456e-06 | 1e-05 | 2257 | 0.0015097 | 9.0946e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0015097 | 125.9784 | 125.9784 | 0%
Sierra | SI_Sierra | DIAMOND SPRINGS 1107 | 7583 | DIAMOND SPRINGS 110740353 | 3.9e-05 | 10.7658 | 0.29527 | 0.21326 | 0.082008 | 0.29527 | 150 | 140 | 73 | 59 | 73 | 59 | 0 | 11 | 0 | 140 |  | 73 | 59 | 0 | 0 | 0 | 0 | 3.6226e-06 | 0 | 2258 | 0.00020552 | 8.9357e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.7082e-05 | 0 | 247.2354 | 72.23%
Bay Area | PE_Peninsula | PACIFICA 1101 | 1395 | PACIFICA 1103circuit_breaker | 0.000805 | 2.1831 | 0.16288 | 0 | 0.16288 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 21 |  | 6 | 5 | 21 | 6 | 5 | 10.11 | 0.00036873 | 0 | 2259 | 2.6488e-05 | 8.8293e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.6488e-05 | 36.8372 | 36.8372 | 0%
Bay Area | PE_Peninsula | PACIFICA 1102 | 409 | PACIFICA 1102circuit_breaker | 0.000339 | 52.8083 | 2.704 | 0 | 2.704 | 0 | 187 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 1 | 352 |  | 65 | 44 | 352 | 65 | 44 | 120.73 | 6.4194e-06 | 0 | 2260 | 7.8596e-05 | 8.7329e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.8596e-05 | 24.0387 | 24.0387 | 0%
Central Valley | YO_Yosemite | PEORIA 1704 | 8305 | PEORIA 17046090 | 0.000741 | 8.5532 | 0.73371 | 0.51686 | 0.21705 | 0.73371 | 17 | 43 | 18 | 11 | 8 | 8 | 0 | 17 | 0 | 43 |  | 18 | 11 | 0 | 10 | 3 | 13.7 | 8.6635e-05 | 0 | 2261 | 3.4541e-05 | 8.6353e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.0218e-05 | 46.0733 | 24.5328 | 70.44%
North Coast | SO_Sonoma | MIRABEL 1102 | 8366 | MIRABEL 11027401 | 0.004083 | 39.0377 | 1.5384 | 0.0022727 | 1.5362 | 1.4072 | 1034 | 329 | 328 | 79 | 0 | 0 | 0 | 97 | 0.085313 | 490 |  | 357 | 98 | 161 | 357 | 98 | 503.58 | 0.00010459 | 8e-05 | 2262 | 6.0113e-05 | 8.5875e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.0024e-05 | 232.3955 | 232.0522 | 0.1477%
Central Coast | CC_Central Coast | DEL MONTE 2104 | 6609 | DEL MONTE 21042624 | 0.012581 | 440.1741 | 17.7625 | 5.3403 | 12.422 | 7.2559 | 371 | 657 | 31 | 24 | 9 | 8 | 0 | 337 | 0.59151 | 1063 |  | 105 | 74 | 406 | 96 | 66 | 168.06 | 2.8582e-05 | 1e-05 | 2263 | 0.0012456 | 8.4165e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00087113 | 7.7282 | 5.9113 | 30.07%
Bay Area | DI_Diablo | ROSSMOOR 1106 | 4302 | ROSSMOOR 1106circuit_breaker | 0.000683 | 53.6775 | 3.6562 | 0.30587 | 3.3502 | 0.59451 | 387 | 35 | 25 | 20 | 11 | 9 | 0 | 133 | 0.8374 | 634 |  | 135 | 93 | 599 | 124 | 84 | 223.79 | 1.2724e-05 | 0 | 2264 | 0.00020185 | 8.4103e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00018495 | 37.0128 | 36.9231 | 8.366%
North Valley | NV_North Valley | PARADISE 1106 | 1430 | ORO FINO 1101121988 | 0.010485 | 341.157 | 18.1216 | 5.3104 | 12.8114 | 18.1121 | 4579 | 8872 | 2249 | 2145 | 1001 | 947 | 0 | 1044 | 0.00052256 | 8876 |  | 2250 | 2146 | 4 | 1249 | 1199 | 1711.49 | 3.0734e-05 | 8e-05 | 2265 | 0.0020276 | 8.344e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0014334 | 97.4916 | 124.1613 | 29.3%
Central Valley | YO_Yosemite | TAR FLAT 0402 | 3210 | RACETRACK 170310850 | 0.000127 | 29.5336 | 2.593 | 0 | 2.593 | 0 | 353 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 1 | 653 |  | 120 | 80 | 653 | 120 | 80 | 223.17 | 4.3002e-06 | 0 | 2266 | 0.00011515 | 8.2252e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00011515 | 46.2786 | 46.2786 | 0%
Sierra | SI_Sierra | AUBURN 1101 | 661 | FLINT 110140666 | 0.000151 | 22.7209 | 1.3006 | 0 | 1.3006 | 0 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 1 | 366 |  | 68 | 46 | 366 | 68 | 46 | 126.1 | 6.6459e-06 | 0 | 2267 | 0.00015593 | 8.2066e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00015593 | 52.2848 | 52.2848 | 0%
North Coast | HU_Humboldt | GUALALA 1111 | 9142 | GUALALA 1111445166 | 0.000744 | 153.7602 | 8.1642 | 0 | 8.1642 | 0 | 2589 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 1 | 4714 |  | 852 | 562 | 4714 | 852 | 562 | 1591.5 | 4.8387e-06 | 1e-05 | 2268 | 0.00059806 | 8.1926e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00059806 | 104.358 | 104.358 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2103 | 3212 | CAMP EVERS 210310946 | 0.00035 | 108.0812 | 4.1265 | 0 | 4.1265 | 0.28788 | 1466 | 200 | 200 | 198 | 1 | 1 | 0 | 268 | 0.93024 | 2688 |  | 651 | 496 | 2488 | 650 | 495 | 1114.42 | 3.2383e-06 | 0 | 2269 | 0.0006466 | 8.1848e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0006466 | 157.5179 | 157.7602 | 0%
Sierra | SI_Sierra | HIGGINS 1104 | 6317 | HIGGINS 110432747 | 0.007545 | 59.6014 | 3.0426 | 0 | 3.0426 | 0 | 1912 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 1 | 3484 |  | 630 | 416 | 3484 | 630 | 416 | 1176.66 | 0.00012659 | 0.00017 | 2270 | 8.9903e-05 | 8.173e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.9903e-05 | 207.0588 | 207.0588 | 0%
North Coast | SO_Sonoma | SANTA ROSA A 1104 | 1534 | SANTA ROSA A 1104circuit_breaker | 4.5e-05 | 22.2488 | 0.64564 | 0.067424 | 0.57822 | 0.27936 | 80 | 7 | 7 | 2 | 0 | 0 | 0 | 42 | 0.56732 | 96 |  | 24 | 14 | 89 | 24 | 14 | 40.89 | 2.0226e-06 | 0 | 2271 | 4.8652e-05 | 8.1086e-06 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.3571e-05 | 41.5067 | 37.1722 | 10.44%
Bay Area | EB_East Bay | VALLEY VIEW 1106 | 6440 | VALLEY VIEW 1106P128 | 0.000189 | 25.3261 | 0.88049 | 0.65814 | 0.22235 | 0.88049 | 118 | 193 | 19 | 6 | 10 | 0 | 0 | 34 | 0 | 193 |  | 19 | 6 | 0 | 9 | 6 | 12.33 | 7.4626e-06 | 0 | 2272 | 4.0465e-05 | 8.0931e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.0219e-05 | 40.477 | 21.5788 | 74.75%
Sierra | SI_Sierra | SHINGLE SPRINGS 1103 | 4306 | SHINGLE SPRINGS 11038752 | 1.7801 | 92.6416 | 3.5265 | 0 | 3.5265 | 0 | 211 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 1 | 395 |  | 73 | 49 | 395 | 73 | 49 | 135.56 | 0.019214 | 0.00292 | 2273 | 0.00022468 | 8.0242e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00022468 | 20.7003 | 20.7003 | 0%
Bay Area | NB_North Bay | OLEMA 1101 | 8980 | OLEMA 110149756 | 0.002314 | 19.2371 | 1.1786 | 0 | 1.1786 | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 1 | 205 |  | 39 | 27 | 205 | 39 | 27 | 71.88 | 0.00012029 | 1e-05 | 2275 | 7.8955e-05 | 7.8955e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.8955e-05 | 33.0901 | 33.0901 | 0%
Sierra | SI_Sierra | BRUNSWICK 1104 | 817 | BRUNSWICK 110456468 | 0.010514 | 108.3039 | 5.208 | 0 | 5.208 | 0 | 2604 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 1 | 4741 |  | 857 | 565 | 4741 | 857 | 565 | 1600.78 | 9.7079e-05 | 0.00017 | 2276 | 7.8663e-05 | 7.8663e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.8663e-05 | 164.556 | 164.556 | 0%
North Coast | HU_Humboldt | BIG RIVER 1101 | 8089 | BIG RIVER 1101circuit_breaker | 0.000247 | 50.2078 | 1.6229 | 0 | 1.6229 | 0 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1 | 884 |  | 161 | 107 | 884 | 161 | 107 | 300.13 | 4.9196e-06 | 0 | 2277 | 0.00016498 | 7.8562e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00016498 | 99.2041 | 99.2041 | 0%
North Coast | SO_Sonoma | MONTE RIO 1113 | 5049 | MONTE RIO 11135026 | 0.001154 | 32.9574 | 1.6945 | 0 | 1.6945 | 0.39337 | 686 | 1 | 0 | 0 | 0 | 0 | 0 | 123 | 0.76786 | 967 |  | 176 | 116 | 966 | 176 | 116 | 328.06 | 3.5015e-05 | 1e-05 | 2278 | 0.00021968 | 7.8457e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00021968 | 103.865 | 103.865 | 0%
Central Coast | CC_Central Coast | POINT MORETTI 1101 | 8134 | POINT MORETTI 11015401 | 8.1e-05 | 33.6544 | 1.2583 | 0 | 1.2583 | 0 | 1117 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 1 | 2041 |  | 370 | 245 | 2041 | 370 | 245 | 690.59 | 2.4068e-06 | 0 | 2279 | 0.00031316 | 7.829e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00031316 | 294.0397 | 294.0397 | 0%
North Coast | HU_Humboldt | FORT BRAGG A 1101 | 5312 | FORT BRAGG A 11013100 | 0.067119 | 317.4141 | 11.8703 | 0 | 11.8703 | 0 | 3408 | 0 | 0 | 0 | 0 | 0 | 0 | 278 | 1 | 6201 |  | 1120 | 739 | 6201 | 1120 | 739 | 2092.49 | 0.00021146 | 0.00049 | 2280 | 0.0014694 | 7.7744e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0014694 | 94.3534 | 94.3534 | 0%
Sierra | SI_Sierra | HALSEY 1101 | 7519 | HALSEY 11015731 | 0.026527 | 39.2855 | 1.1977 | 0 | 1.1977 | 0 | 587 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 1 | 1078 |  | 196 | 130 | 1078 | 196 | 130 | 365.54 | 0.00067524 | 0.00028 | 2281 | 0.00039506 | 7.7463e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00039506 | 163.6433 | 163.6433 | 0%
Sierra | SI_Sierra | BRUNSWICK 1103 | 957 | BRUNSWICK 1103circuit_breaker | 0.004527 | 116.0535 | 5.4288 | 0.13939 | 5.2894 | 0.21894 | 2681 | 259 | 187 | 182 | 187 | 182 | 0 | 457 | 0.95967 | 4943 |  | 1034 | 741 | 4684 | 847 | 559 | 1581.95 | 3.9008e-05 | 7e-05 | 2282 | 2.3194e-05 | 7.7314e-06 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 6. >50% | 6. >50% | 2.2599e-05 | 160.1318 | 190.4661 | 2.568%
Sierra | SI_Sierra | AUBURN 1101 | 488 | AUBURN 1101circuit_breaker | 0.000286 | 50.4193 | 2.6883 | 0 | 2.6883 | 0 | 344 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 1 | 637 |  | 117 | 78 | 637 | 117 | 78 | 217.62 | 5.6724e-06 | 0 | 2284 | 0.00037547 | 7.6627e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00037547 | 43.5226 | 43.5226 | 0%
North Coast | SO_Sonoma | SANTA ROSA A 1107 | 685 | SANTA ROSA A 1107circuit_breaker | 0.000193 | 47.9249 | 2.4566 | 0 | 2.4566 | 0.047159 | 344 | 2 | 2 | 1 | 0 | 0 | 0 | 74 | 0.9808 | 627 |  | 117 | 77 | 625 | 117 | 77 | 216.54 | 4.0271e-06 | 0 | 2285 | 0.00032043 | 7.6293e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00032043 | 47.6262 | 47.6262 | 0%
Central Coast | DA_De Anza | LOS GATOS 1106 | 3696 | LOS GATOS 1106LA46 | 6.2e-05 | 55.759 | 3.2684 | 0 | 3.2684 | 0 | 1780 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 1 | 3245 |  | 587 | 388 | 3245 | 587 | 388 | 1096.24 | 1.1119e-06 | 0 | 2286 | 0.00022468 | 7.4892e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00022468 | 179.6002 | 179.6002 | 0%
Sierra | SI_Sierra | WEIMAR 1101 | 3409 | WEIMAR 1101circuit_breaker | 0.000986 | 170.6222 | 7.9415 | 0 | 7.9415 | 0 | 2604 | 0 | 0 | 0 | 0 | 0 | 0 | 211 | 1 | 4741 |  | 857 | 565 | 4741 | 857 | 565 | 1600.78 | 5.7789e-06 | 1e-05 | 2287 | 0.0010071 | 7.4601e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0010071 | 107.9144 | 107.9144 | 0%
North Coast | HU_Humboldt | REDBUD 1102 | 3013 | REDBUD 11022013 | 1.1064 | 12.5819 | 0.76345 | 0.16345 | 0.6 | 0.20606 | 5 | 3 | 2 | 2 | 0 | 0 | 0 | 30 | 0.73009 | 19 |  | 6 | 5 | 16 | 6 | 5 | 9.66 | 0.087939 | 0.0011 | 2290 | 7.4332e-06 | 7.4332e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.8418e-06 | 10 | 7.8591 | 21.41%
Central Coast | CC_Central Coast | CAMP EVERS 2103 | 1656 | CAMP EVERS 210312990 | 0.00105 | 378.2153 | 15.0061 | 0 | 15.0061 | 0.32348 | 5936 | 60 | 58 | 57 | 0 | 0 | 0 | 888 | 0.97844 | 10619 |  | 1964 | 1314 | 10559 | 1964 | 1314 | 3640.99 | 2.7762e-06 | 1e-05 | 2293 | 0.0016808 | 7.372e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0016808 | 130.8805 | 130.8805 | 0%
Sierra | SI_Sierra | HALSEY 1101 | 2859 | HALSEY 110176178 | 0.001324 | 494.0987 | 21.9576 | 0 | 21.9576 | 0 | 9919 | 0 | 0 | 0 | 0 | 0 | 0 | 565 | 1 | 18025 |  | 3253 | 2144 | 18025 | 3253 | 2144 | 6078.86 | 2.6796e-06 | 2e-05 | 2294 | 0.0026072 | 7.365e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0026072 | 148.1493 | 148.1493 | 0%
North Coast | SO_Sonoma | SANTA ROSA A 1104 | 1878 | SANTA ROSA A 110439786 | 7.9e-05 | 29.3377 | 1.2892 | 0.028788 | 1.2604 | 0.16098 | 216 | 4 | 4 | 0 | 0 | 0 | 0 | 115 | 0.87513 | 358 |  | 70 | 44 | 354 | 70 | 44 | 127.76 | 2.6928e-06 | 0 | 2295 | 0.00013219 | 7.344e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00012924 | 55.5372 | 54.297 | 2.233%
Bay Area | DI_Diablo | WAYNE 0401 | 2928 | TASSAJARA 210883368 | 3.6e-05 | 7.7129 | 0.83163 | 0 | 0.83163 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 1 | 194 |  | 37 | 25 | 194 | 37 | 25 | 68.15 | 4.6675e-06 | 0 | 2296 | 2.1851e-05 | 7.2838e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.1851e-05 | 44.491 | 44.491 | 0%
North Coast | HU_Humboldt | FORT BRAGG A 1102 | 1172 | FORT BRAGG A 1102418 | 0.000534 | 377.9279 | 14.8922 | 0 | 14.8922 | 0 | 6075 | 0 | 0 | 0 | 0 | 0 | 0 | 359 | 1 | 11044 |  | 1994 | 1314 | 11044 | 1994 | 1314 | 3725.74 | 1.413e-06 | 1e-05 | 2297 | 0.0016397 | 7.1917e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0016397 | 133.8953 | 133.8953 | 0%
Central Coast | DA_De Anza | LOS GATOS 1106 | 3862 | LOS GATOS 1106LA42 | 3.7e-05 | 33.3505 | 2.7491 | 0 | 2.7491 | 0 | 1179 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 1 | 2153 |  | 390 | 258 | 2153 | 390 | 258 | 728.07 | 1.1094e-06 | 0 | 2298 | 0.00025835 | 7.1765e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00025835 | 141.867 | 141.867 | 0%
Central Valley | YO_Yosemite | TAR FLAT 0401 | 4123 | TAR FLAT 0401circuit_breaker | 0.000197 | 49.7927 | 3.0403 | 0.14981 | 2.8905 | 0.14981 | 433 | 52 | 15 | 4 | 14 | 3 | 0 | 103 | 0.95073 | 811 |  | 154 | 96 | 759 | 140 | 93 | 260.11 | 3.9564e-06 | 0 | 2300 | 0.0002361 | 7.1547e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00022447 | 48.434 | 50.6522 | 4.927%
North Coast | HU_Humboldt | ELK 1101 | 4056 | ELK 11014628 | 0.002354 | 20.1745 | 1.7025 | 0 | 1.7025 | 0 | 506 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1 | 931 |  | 170 | 113 | 931 | 170 | 113 | 316.69 | 0.00011668 | 4e-05 | 2301 | 0.00024953 | 7.1293e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00024953 | 99.8554 | 99.8554 | 0%
North Coast | HU_Humboldt | HIGHLANDS 1102 | 5918 | HIGHLANDS 1102556 | 0.85269 | 10.2782 | 0.76686 | 0.66174 | 0.10511 | 0.76686 | 40 | 60 | 10 | 2 | 10 | 2 | 0 | 21 | 0 | 60 |  | 10 | 2 | 0 | 0 | 0 | 0 | 0.082961 | 0 | 2303 | 7.1087e-06 | 7.1087e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.7439e-07 | 0 | 13.0403 | 86.29%
Central Valley | YO_Yosemite | RACETRACK 1703 | 5808 | RACETRACK 17032553 | 0.010127 | 53.1788 | 2.1966 | 0 | 2.1966 | 0 | 381 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 1 | 704 |  | 129 | 86 | 704 | 129 | 86 | 240.09 | 0.00019043 | 5e-05 | 2305 | 0.00012024 | 7.0731e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00012024 | 58.7274 | 58.7274 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2101 | 9266 | GREEN VALLEY 21016601 | 7e-05 | 46.6064 | 1.7352 | 0 | 1.7352 | 0 | 662 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1 | 1214 |  | 221 | 146 | 1214 | 221 | 146 | 412.03 | 1.5019e-06 | 0 | 2306 | 0.00021863 | 7.0525e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00021863 | 127.3608 | 127.3608 | 0%
Bay Area | PE_Peninsula | PACIFICA 1102 | 550 | PACIFICA 110266732 | 2.4e-05 | 12.52 | 1.3646 | 0 | 1.3646 | 0 | 374 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 1 | 691 |  | 127 | 84 | 691 | 127 | 84 | 236.18 | 1.9169e-06 | 0 | 2307 | 7.7154e-05 | 7.014e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.7154e-05 | 93.0687 | 93.0687 | 0%
Bay Area | MI_Mission | SUNOL 1101 | 2696 | SUNOL 1101MR650 | 4.3e-05 | 12.4347 | 0.94564 | 0.29394 | 0.6517 | 0.89489 | 176 | 104 | 25 | 8 | 0 | 0 | 0 | 27 | 0.053675 | 122 |  | 28 | 10 | 18 | 28 | 10 | 39.98 | 3.4581e-06 | 0 | 2308 | 0.00011195 | 6.9968e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.7151e-05 | 42.9643 | 29.6095 | 31.08%
Bay Area | NB_North Bay | SAN RAFAEL 1108 | 4486 | SAN RAFAEL 11081262 | 0.000178 | 84.3721 | 5.1208 | 0 | 5.1208 | 0 | 1081 | 0 | 0 | 0 | 0 | 0 | 0 | 202 | 1 | 1975 |  | 358 | 237 | 1975 | 358 | 237 | 668.21 | 2.1097e-06 | 0 | 2309 | 0.00038458 | 6.9923e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00038458 | 69.9105 | 69.9105 | 0%
Sierra | SI_Sierra | BRUNSWICK 1104 | 4129 | BRUNSWICK 1104circuit_breaker | 0.008077 | 58.739 | 2.7269 | 0 | 2.7269 | 0.0011364 | 1045 | 2 | 0 | 0 | 0 | 0 | 0 | 93 | 0.99958 | 1911 |  | 346 | 229 | 1909 | 346 | 229 | 645.83 | 0.00013751 | 0.0001 | 2310 | 2.0939e-05 | 6.9796e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.0939e-05 | 126.8843 | 126.8843 | 0%
Sierra | SI_Sierra | BRUNSWICK 1106 | 4205 | BRUNSWICK 110633050 | 6.6e-05 | 51.3163 | 3.625 | 0 | 3.625 | 0.35985 | 1130 | 0 | 0 | 0 | 0 | 0 | 0 | 174 | 0.90073 | 1859 |  | 337 | 223 | 1859 | 337 | 223 | 629 | 1.2861e-06 | 0 | 2311 | 0.00015285 | 6.9479e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00015285 | 92.9655 | 92.9655 | 0%
Sierra | SI_Sierra | WEIMAR 1101 | 4891 | WEIMAR 11012764 | 0.00035 | 109.9962 | 4.564 | 0 | 4.564 | 0 | 1774 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 1 | 3234 |  | 585 | 386 | 3234 | 585 | 386 | 1092.51 | 3.1819e-06 | 0 | 2312 | 0.00066364 | 6.9129e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00066364 | 128.1766 | 128.1766 | 0%
Central Coast | CC_Central Coast | LAURELES 1111 | 617 | LAURELES 11112020 | 0.006787 | 834.9585 | 31.7631 | 30.7955 | 0.96742 | 31.7631 | 2355 | 3817 | 693 | 145 | 673 | 137 | 0 | 930 | 0 | 3817 |  | 693 | 145 | 0 | 20 | 8 | 27.4 | 8.1285e-06 | 0 | 2313 | 0.0026408 | 6.8951e-06 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.0432e-05 | 20.6735 | 21.8178 | 96.95%
North Coast | SO_Sonoma | SANTA ROSA A 1104 | 4230 | SANTA ROSA A 110432180 | 0.01423 | 63.964 | 2.5009 | 0.40038 | 2.1006 | 2.2782 | 374 | 275 | 83 | 52 | 4 | 0 | 0 | 210 | 0.089057 | 337 |  | 94 | 60 | 62 | 90 | 60 | 128.88 | 0.00022247 | 4e-05 | 2314 | 0.00022369 | 6.7786e-06 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00018788 | 42.8456 | 37.5858 | 16.01%
Central Coast | CC_Central Coast | CAMP EVERS 2103 | 4675 | CAMP EVERS 21035404 | 0.000153 | 61.2364 | 2.808 | 0 | 2.808 | 0.26098 | 893 | 84 | 82 | 79 | 0 | 0 | 0 | 160 | 0.90706 | 1566 |  | 351 | 257 | 1482 | 351 | 257 | 614.25 | 2.4985e-06 | 0 | 2315 | 0.00027106 | 6.7764e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00027106 | 125.002 | 125.002 | 0%
Bay Area | NB_North Bay | MONTICELLO 1101 | 8715 | MONTICELLO 1101circuit_breaker | 0.000957 | 13.7403 | 0.9464 | 0 | 0.9464 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 61 |  | 13 | 10 | 61 | 13 | 10 | 23.3 | 6.9649e-05 | 0 | 2316 | 4.6712e-05 | 6.6732e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.6712e-05 | 13.7362 | 13.7362 | 0%
North Coast | SO_Sonoma | MIRABEL 1102 | 4368 | MIRABEL 1102206 | 0.000201 | 43.0342 | 3.014 | 0.29053 | 2.7235 | 2.0797 | 388 | 101 | 101 | 70 | 0 | 0 | 0 | 115 | 0.30998 | 323 |  | 142 | 97 | 222 | 142 | 97 | 214.52 | 4.6707e-06 | 0 | 2317 | 0.00016639 | 6.6555e-06 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00015035 | 52.1391 | 47.1132 | 9.639%
North Coast | HU_Humboldt | KONOCTI 1108 | 636 | KONOCTI 11084039 | 6.9e-05 | 19.6372 | 1.0816 | 0 | 1.0816 | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 1 | 292 |  | 55 | 37 | 292 | 55 | 37 | 101.63 | 3.5137e-06 | 0 | 2318 | 0.00017256 | 6.6371e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00017256 | 50.8492 | 50.8492 | 0%
Sierra | SI_Sierra | AUBURN 1102 | 3558 | AUBURN 1102circuit_breaker | 0.000177 | 40.3153 | 2.2644 | 0 | 2.2644 | 0 | 183 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 1 | 345 |  | 64 | 43 | 345 | 64 | 43 | 118.73 | 4.3904e-06 | 0 | 2319 | 0.00015203 | 6.6098e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00015203 | 28.2636 | 28.2636 | 0%
Sierra | SI_Sierra | DIAMOND SPRINGS 1104 | 5199 | DIAMOND SPRINGS 1105circuit_breaker | 0.13153 | 36.6278 | 1.607 | 0 | 1.607 | 0 | 297 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 1 | 552 |  | 101 | 68 | 552 | 101 | 68 | 188.05 | 0.003591 | 0.00075 | 2320 | 9.8799e-05 | 6.5866e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.8799e-05 | 62.8497 | 62.8497 | 0%
Central Coast | CC_Central Coast | ROB ROY 2104 | 7115 | ROB ROY 210410298 | 0.003873 | 281.0551 | 11.4943 | 0 | 11.4943 | 0 | 4961 | 0 | 0 | 0 | 0 | 0 | 0 | 248 | 1 | 9021 |  | 1629 | 1074 | 9021 | 1629 | 1074 | 3043.62 | 1.378e-05 | 5e-05 | 2321 | 0.0010109 | 6.5644e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0010109 | 141.7222 | 141.7222 | 0%
Sierra | SI_Sierra | DIAMOND SPRINGS 1106 | 1048 | DIAMOND SPRINGS 110699658 | 0.000823 | 184.6902 | 7.0417 | 0 | 7.0417 | 0 | 1813 | 0 | 0 | 0 | 0 | 0 | 0 | 301 | 1 | 3305 |  | 598 | 395 | 3305 | 598 | 395 | 1116.71 | 4.4561e-06 | 1e-05 | 2322 | 0.0007539 | 6.5557e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0007539 | 84.9231 | 84.9231 | 0%
Sierra | SI_Sierra | HALSEY 1102 | 6385 | HALSEY 11026129 | 0.000242 | 71.8692 | 2.5468 | 0 | 2.5468 | 0 | 868 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 1 | 1589 |  | 288 | 191 | 1589 | 288 | 191 | 537.57 | 3.3672e-06 | 0 | 2323 | 0.00035384 | 6.5526e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00035384 | 113.084 | 113.084 | 0%
Central Valley | YO_Yosemite | CURTIS 1701 | 5467 | CURTIS 170190120 | 0.000453 | 105.1972 | 4.1784 | 0 | 4.1784 | 0 | 517 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 1 | 951 |  | 174 | 115 | 951 | 174 | 115 | 323.97 | 4.3062e-06 | 0 | 2324 | 0.00026162 | 6.5405e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00026162 | 41.6426 | 41.6426 | 0%
Bay Area | DI_Diablo | MORAGA 1104 | 1875 | MORAGA 1104circuit_breaker | 0.017646 | 445.5168 | 20.6203 | 0.067235 | 20.5528 | 0.12803 | 3480 | 61 | 1 | 0 | 0 | 0 | 0 | 661 | 0.99379 | 6354 |  | 1138 | 750 | 6293 | 1138 | 750 | 2125.43 | 3.9608e-05 | 9e-05 | 2325 | 0.0016097 | 6.5172e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0016045 | 55.3695 | 55.1884 | 0.3261%
Sierra | SI_Sierra | WEIMAR 1102 | 575 | WEIMAR 11022038 | 0.000698 | 315.2243 | 16.5036 | 0 | 16.5036 | 0 | 6097 | 0 | 0 | 0 | 0 | 0 | 0 | 424 | 1 | 11084 |  | 2001 | 1319 | 11084 | 2001 | 1319 | 3738.93 | 2.2143e-06 | 1e-05 | 2326 | 0.0013147 | 6.5083e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0013147 | 121.2463 | 121.2463 | 0%
Central Coast | CC_Central Coast | PAUL SWEET 2104 | 4947 | PAUL SWEET 21045394 | 0.008781 | 282.0989 | 12.7244 | 0 | 12.7244 | 0 | 2377 | 0 | 0 | 0 | 0 | 0 | 0 | 279 | 1 | 4329 |  | 783 | 516 | 4329 | 783 | 516 | 1462.32 | 3.1127e-05 | 5e-05 | 2327 | 0.0015572 | 6.4881e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0015572 | 61.5352 | 61.5352 | 0%
Central Coast | CC_Central Coast | POINT MORETTI 1101 | 9182 | POINT MORETTI 110183716 | 0.000314 | 53.0749 | 2.5348 | 0 | 2.5348 | 0 | 503 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 1 | 926 |  | 169 | 112 | 926 | 169 | 112 | 314.87 | 5.9162e-06 | 0 | 2329 | 8.3588e-05 | 6.4299e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.3588e-05 | 66.6707 | 66.6707 | 0%
Sierra | SI_Sierra | FLINT 1101 | 7131 | FLINT 1101circuit_breaker | 0.000225 | 30.2486 | 1.0786 | 0 | 1.0786 | 0 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 1 | 159 |  | 31 | 21 | 159 | 31 | 21 | 56.78 | 7.4384e-06 | 0 | 2330 | 5.1436e-05 | 6.4295e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.1436e-05 | 28.741 | 28.741 | 0%
North Coast | HU_Humboldt | FORT BRAGG A 1104 | 5217 | FORT BRAGG A 11041316 | 0.002365 | 339.35 | 11.9045 | 0 | 11.9045 | 0 | 3216 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 1 | 5852 |  | 1057 | 697 | 5852 | 1057 | 697 | 1974.77 | 6.9692e-06 | 2e-05 | 2331 | 0.0011755 | 6.4234e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0011755 | 88.7896 | 88.7896 | 0%
North Coast | SO_Sonoma | SANTA ROSA A 1104 | 1796 | SANTA ROSA A 1104210 | 0.016992 | 165.5688 | 5.7206 | 0.092235 | 5.6284 | 1.5369 | 2035 | 140 | 122 | 23 | 0 | 0 | 0 | 483 | 0.73134 | 2852 |  | 612 | 347 | 2712 | 612 | 347 | 1082.52 | 0.00010263 | 0.00013 | 2332 | 0.00066969 | 6.378e-06 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00065889 | 108.7341 | 106.981 | 1.612%
Sierra | SI_Sierra | BRUNSWICK 1107 | 4061 | GRASS VALLEY 1102circuit_breaker | 2.6e-05 | 7.865 | 0.79981 | 0 | 0.79981 | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 1 | 292 |  | 55 | 37 | 292 | 55 | 37 | 101.63 | 3.3058e-06 | 0 | 2333 | 6.3417e-06 | 6.3417e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.3417e-06 | 68.7663 | 68.7663 | 0%
Sierra | SI_Sierra | AUBURN 1102 | 9057 | AUBURN 11028611 | 0.000123 | 24.1454 | 0.86288 | 0 | 0.86288 | 0 | 117 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 1 | 225 |  | 43 | 29 | 225 | 43 | 29 | 79.16 | 5.0941e-06 | 0 | 2334 | 0.00015154 | 6.314e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00015154 | 49.8332 | 49.8332 | 0%
North Coast | HU_Humboldt | BIG RIVER 1101 | 5753 | BIG RIVER 11012183 | 0.022412 | 64.0384 | 2.5816 | 0 | 2.5816 | 0 | 633 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 1 | 1162 |  | 212 | 140 | 1162 | 212 | 140 | 395.02 | 0.00034998 | 0.00015 | 2336 | 0.0002117 | 6.2266e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0002117 | 82.1187 | 82.1187 | 0%
Central Valley | YO_Yosemite | BEAR VALLEY 2105 | 9867 | BEAR VALLEY 2105circuit_breaker | 0.000762 | 91.25 | 4.6803 | 0 | 4.6803 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 1 | 27 |  | 7 | 5 | 27 | 7 | 5 | 12.02 | 8.3507e-06 | 0 | 2337 | 4.9797e-05 | 6.2246e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.9797e-05 | 1.4956 | 1.4956 | 0%
North Coast | HU_Humboldt | FORT BRAGG A 1102 | 7454 | FORT BRAGG A 1102circuit_breaker | 0.000115 | 46.3592 | 2.2703 | 0 | 2.2703 | 0 | 962 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 1 | 1759 |  | 319 | 211 | 1759 | 319 | 211 | 595.34 | 2.4806e-06 | 0 | 2338 | 0.00015554 | 6.2217e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00015554 | 140.5122 | 140.5122 | 0%
Central Coast | CC_Central Coast | SEACLIFF 0401 | 3462 | SEACLIFF 0402circuit_breaker | 6e-06 | 1.5339 | 0.036742 | 0 | 0.036742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 3.9115e-06 | 0 | 2339 | 2.4741e-05 | 6.1854e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.4741e-05 | 108.866 | 108.866 | 0%
Central Coast | CC_Central Coast | ROB ROY 2104 | 6144 | ROB ROY 21049973 | 2.6e-05 | 13.6331 | 0.29754 | 0 | 0.29754 | 0 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 499 |  | 92 | 61 | 499 | 92 | 61 | 170.95 | 1.9071e-06 | 0 | 2340 | 8.644e-05 | 6.1743e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.644e-05 | 309.2043 | 309.2043 | 0%
North Coast | SO_Sonoma | MONTE RIO 1113 | 4805 | MONTE RIO 1113652 | 0.016801 | 25.4526 | 0.67064 | 0 | 0.67064 | 0.030871 | 587 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 0.95397 | 1029 |  | 187 | 124 | 1029 | 187 | 124 | 348.8 | 0.00066009 | 0.00026 | 2341 | 6.1642e-06 | 6.1642e-06 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.1642e-06 | 278.8365 | 278.8365 | 0%
Bay Area | EB_East Bay | FAIRVIEW 2207 | 3797 | FAIRVIEW 2207P304 | 0.001027 | 100.5518 | 4.4407 | 0 | 4.4407 | 0 | 274 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 1 | 510 |  | 94 | 63 | 510 | 94 | 63 | 174.68 | 1.0214e-05 | 0 | 2342 | 0.0002151 | 6.1457e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0002151 | 21.1677 | 21.1677 | 0%
North Coast | HU_Humboldt | NEWBURG 1131 | 2043 | NEWBURG 11313446 | 0.11982 | 4.5782 | 0.40473 | 0.11174 | 0.29299 | 0.29375 | 53 | 62 | 9 | 2 | 0 | 0 | 0 | 10 | 0.27422 | 92 |  | 15 | 6 | 30 | 15 | 6 | 23.25 | 0.026171 | 0.00082 | 2343 | 6.1144e-06 | 6.1144e-06 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.4263e-06 | 51.1959 | 37.0613 | 27.61%
Central Coast | CC_Central Coast | GREEN VALLEY 2101 | 9752 | GREEN VALLEY 21011645 | 6.7e-05 | 30.9051 | 1.3989 | 0 | 1.3989 | 0 | 636 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1 | 1167 |  | 212 | 141 | 1167 | 212 | 141 | 395.47 | 2.1679e-06 | 0 | 2344 | 4.8671e-05 | 6.0839e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.8671e-05 | 151.5516 | 151.5516 | 0%
North Coast | HU_Humboldt | FORT BRAGG A 1102 | 6706 | FORT BRAGG A 1102816 | 0.001899 | 23.9173 | 0.96686 | 0 | 0.96686 | 0 | 812 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1 | 1487 |  | 270 | 179 | 1487 | 270 | 179 | 503.73 | 7.9399e-05 | 4e-05 | 2345 | 0.00021262 | 6.075e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00021262 | 279.2556 | 279.2556 | 0%
Bay Area | PE_Peninsula | PACIFICA 1101 | 2319 | PACIFICA 11015001 | 0.000183 | 32.6429 | 1.4934 | 0 | 1.4934 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 1 | 21 |  | 6 | 5 | 21 | 6 | 5 | 10.11 | 5.6061e-06 | 0 | 2346 | 3.0284e-05 | 6.0567e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.0284e-05 | 4.0178 | 4.0178 | 0%
Central Valley | YO_Yosemite | CURTIS 1701 | 34 | CURTIS 17019230 | 0.000189 | 37.1181 | 1.7487 | 0 | 1.7487 | 0 | 238 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 1 | 444 |  | 82 | 55 | 444 | 82 | 55 | 152.3 | 5.0918e-06 | 0 | 2347 | 0.00014484 | 6.0352e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00014484 | 46.8927 | 46.8927 | 0%
Bay Area | NB_North Bay | CALISTOGA 1102 | 3357 | CALISTOGA 1102circuit_breaker | 0.49433 | 15.9673 | 0.48788 | 0.33201 | 0.15587 | 0.39848 | 33 | 59 | 46 | 34 | 42 | 32 | 0 | 20 | 0.18323 | 72 |  | 49 | 36 | 13 | 7 | 4 | 10.76 | 0.030959 | 0.00045 | 2348 | 2.9949e-05 | 5.9897e-06 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.5682e-06 | 44.9089 | 100.4348 | 68.05%
North Coast | NC_North Coast | RIO DELL 1102 | 7060 | RIO DELL 11028852 | 0.029521 | 104.9634 | 4.2025 | 0 | 4.2025 | 0 | 1349 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 1 | 2462 |  | 446 | 295 | 2462 | 446 | 295 | 832.6 | 0.00028125 | 0.00026 | 2349 | 0.00037125 | 5.9878e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00037125 | 106.1283 | 106.1283 | 0%
Bay Area | NB_North Bay | GREENBRAE 1103 | 4004 | GREENBRAE 1103circuit_breaker | 0.000115 | 39.1527 | 1.6847 | 0 | 1.6847 | 0 | 312 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 1 | 579 |  | 106 | 71 | 579 | 106 | 71 | 197.33 | 2.9372e-06 | 0 | 2352 | 9.4432e-05 | 5.902e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.4432e-05 | 62.9207 | 62.9207 | 0%
Sierra | SI_Sierra | BRUNSWICK 1102 | 6665 | BRUNSWICK 1102940 | 5.4e-05 | 12.1426 | 1.032 | 0 | 1.032 | 0 | 411 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 1 | 759 |  | 139 | 92 | 759 | 139 | 92 | 258.74 | 4.4471e-06 | 0 | 2353 | 7.0652e-05 | 5.8876e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.0652e-05 | 134.6889 | 134.6889 | 0%
Central Coast | CC_Central Coast | LAURELES 1111 | 7708 | LAURELES 111110141 | 0.000219 | 87.6958 | 3.4426 | 2.7477 | 0.69489 | 3.4426 | 1055 | 1614 | 309 | 104 | 309 | 104 | 0 | 112 | 0 | 1614 |  | 309 | 104 | 0 | 0 | 0 | 0 | 2.4973e-06 | 0 | 2354 | 0.00030603 | 5.8852e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.1771e-05 | 0 | 89.7574 | 79.82%
Sierra | SI_Sierra | PLACER 1101 | 2848 | PLACER 1101circuit_breaker | 0.002267 | 35.3385 | 1.6176 | 0 | 1.6176 | 0 | 219 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 1 | 410 |  | 76 | 51 | 410 | 76 | 51 | 141.02 | 6.4151e-05 | 1e-05 | 2355 | 0.0001174 | 5.8701e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0001174 | 46.9828 | 46.9828 | 0%
Central Coast | DA_De Anza | STELLING 1110 | 6318 | STELLING 111060090 | 0.004795 | 155.7671 | 6.9328 | 0 | 6.9328 | 0 | 591 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 1 | 1086 |  | 198 | 131 | 1086 | 198 | 131 | 369 | 3.0783e-05 | 1e-05 | 2357 | 0.00048152 | 5.8014e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00048152 | 28.56 | 28.56 | 0%
Central Valley | ST_Stockton | STANISLAUS 1702 | 525 | STANISLAUS 170237278 | 0.031756 | 141.6805 | 7.6386 | 0.68087 | 6.9578 | 7.5994 | 4633 | 2004 | 1078 | 493 | 1070 | 486 | 0 | 396 | 0.0051324 | 2047 |  | 1086 | 498 | 43 | 16 | 12 | 25.79 | 0.00022414 | 1e-05 | 2358 | 1.7396e-05 | 5.7986e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.5845e-05 | 2.2996 | 142.172 | 8.914%
Central Coast | LP_Los Padres | PURISIMA 1101 | 8605 | PURISIMA 110154728 | 0.002762 | 19.989 | 1.0258 | 0 | 1.0258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.00013818 | 0 | 2360 | 1.7299e-05 | 5.7663e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.7299e-05 | 3.8996 | 3.8996 | 0%
Sierra | SI_Sierra | BRUNSWICK 1103 | 3632 | BRUNSWICK 11032784 | 0.13245 | 342.2417 | 14.6102 | 0.076326 | 14.5339 | 1.9811 | 6921 | 527 | 512 | 389 | 140 | 114 | 0 | 988 | 0.86441 | 11402 |  | 2475 | 1683 | 10875 | 2335 | 1569 | 4177.7 | 0.00038701 | 0.00188 | 2361 | 0.00013833 | 5.7637e-06 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 6. >50% | 6. >50% | 0.00013761 | 160.6589 | 169.4019 | 0.5224%
Central Coast | DA_De Anza | LOS GATOS 1107 | 4068 | LOS GATOS 110760092 | 0.000486 | 250.1905 | 10.2646 | 0 | 10.2646 | 0 | 4286 | 0 | 0 | 0 | 0 | 0 | 0 | 282 | 1 | 7796 |  | 1408 | 928 | 7796 | 1408 | 928 | 2630.6 | 1.9425e-06 | 1e-05 | 2362 | 0.00085793 | 5.7579e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00085793 | 137.1707 | 137.1707 | 0%
North Coast | HU_Humboldt | FORT BRAGG A 1102 | 2184 | FORT BRAGG A 11021226 | 0.00027 | 48.5009 | 2.2157 | 0 | 2.2157 | 0 | 612 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 1 | 1124 |  | 205 | 136 | 1124 | 205 | 136 | 382.01 | 5.5669e-06 | 0 | 2363 | 0.00017819 | 5.7481e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00017819 | 92.5207 | 92.5207 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1101 | 6381 | SAN RAFAEL 110168970 | 6e-06 | 4.6465 | 0.067045 | 0 | 0.067045 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 52 |  | 11 | 8 | 52 | 11 | 8 | 19.75 | 1.2913e-06 | 0 | 2364 | 6.855e-05 | 5.7125e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.855e-05 | 164.0678 | 164.0678 | 0%
Central Valley | ST_Stockton | STANISLAUS 1702 | 832 | STANISLAUS 170237276 | 0.10144 | 235.4237 | 12.4799 | 1.4205 | 11.0597 | 12.4398 | 8095 | 7464 | 1907 | 828 | 1871 | 794 | 0 | 714 | 0.0032173 | 7511 |  | 1916 | 834 | 47 | 45 | 40 | 65.88 | 0.00043088 | 4e-05 | 2365 | 1.6897e-05 | 5.6323e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.4974e-05 | 4.0688 | 153.5266 | 11.38%
North Coast | HU_Humboldt | CARLOTTA 1121 | 7332 | CARLOTTA 11214045 | 0.03993 | 2.7582 | 0.49205 | 0 | 0.49205 | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 185 |  | 35 | 24 | 185 | 35 | 24 | 64.6 | 0.014477 | 0.00105 | 2366 | 5.6253e-06 | 5.6253e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.6253e-06 | 71.1316 | 71.1316 | 0%
Central Coast | DA_De Anza | SARATOGA 1106 | 1588 | SARATOGA 1106LC24 | 0.00027 | 122.1716 | 6.7473 | 0 | 6.7473 | 0 | 1746 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 1 | 3183 |  | 576 | 380 | 3183 | 576 | 380 | 1075.59 | 2.21e-06 | 0 | 2367 | 0.00067446 | 5.574e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00067446 | 85.3669 | 85.3669 | 0%
Sierra | SI_Sierra | PLACER 1102 | 6159 | PLACER 1102circuit_breaker | 7.1e-05 | 32.2786 | 1.3848 | 0 | 1.3848 | 0 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1 | 470 |  | 87 | 58 | 470 | 87 | 58 | 161.49 | 2.1996e-06 | 0 | 2368 | 0.00016159 | 5.5719e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00016159 | 62.8228 | 62.8228 | 0%
North Coast | HU_Humboldt | BIG RIVER 1101 | 8429 | BIG RIVER 1101954 | 0.013689 | 194.5134 | 8.2968 | 0 | 8.2968 | 0 | 3263 | 0 | 0 | 0 | 0 | 0 | 0 | 172 | 1 | 5938 |  | 1073 | 708 | 5938 | 1073 | 708 | 2004.43 | 7.0376e-05 | 0.00016 | 2369 | 0.00060716 | 5.5703e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00060716 | 129.3273 | 129.3273 | 0%
Central Valley | ST_Stockton | STANISLAUS 1702 | 4968 | STANISLAUS 17021850 | 0.075628 | 282.3336 | 15.1312 | 1.7608 | 13.3706 | 14.4413 | 8666 | 9361 | 2031 | 996 | 1999 | 969 | 0 | 1038 | 0.045598 | 10079 |  | 2161 | 1081 | 718 | 162 | 112 | 286.56 | 0.00026787 | 9e-05 | 2370 | 6.6547e-05 | 5.5456e-06 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.8804e-05 | 12.1161 | 142.817 | 11.64%
Central Coast | CC_Central Coast | BIG BASIN 1102 | 8313 | BIG BASIN 11026219 | 2.1e-05 | 18.4488 | 0.79754 | 0 | 0.79754 | 0.79754 | 603 | 194 | 193 | 33 | 0 | 0 | 0 | 64 | 0 | 194 |  | 193 | 33 | 0 | 193 | 33 | 264.41 | 1.1383e-06 | 0 | 2371 | 7.6368e-05 | 5.4549e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.6368e-05 | 241.9948 | 241.9948 | 0%
Central Coast | CC_Central Coast | CAMP EVERS 2103 | 1339 | CAMP EVERS 21035402 | 0.000122 | 44.3843 | 2.3716 | 0 | 2.3716 | 0 | 682 | 1 | 1 | 1 | 0 | 0 | 0 | 186 | 1 | 1252 |  | 229 | 152 | 1251 | 229 | 152 | 426.32 | 2.7487e-06 | 0 | 2373 | 0.00017336 | 5.4174e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00017336 | 96.5597 | 96.5597 | 0%
North Coast | HU_Humboldt | LUCERNE 1106 | 7418 | LUCERNE 11062355 | 0.048899 | 16.3147 | 1.8381 | 0 | 1.8381 | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 1 | 205 |  | 39 | 27 | 205 | 39 | 27 | 71.88 | 0.0029972 | 0.00024 | 2374 | 2.6937e-05 | 5.3873e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.6937e-05 | 21.2179 | 21.2179 | 0%
North Coast | HU_Humboldt | GUALALA 1111 | 1711 | GUALALA 1111402866 | 5e-05 | 30.0434 | 1.2381 | 0 | 1.2381 | 0 | 474 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 1 | 873 |  | 159 | 106 | 873 | 159 | 106 | 296.4 | 1.6643e-06 | 0 | 2375 | 0.00014421 | 5.3411e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00014421 | 128.4259 | 128.4259 | 0%
North Coast | HU_Humboldt | HARTLEY 1101 | 1776 | HARTLEY 1101738 | 0.015369 | 58.3939 | 3.354 | 0 | 3.354 | 0 | 491 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 1 | 904 |  | 165 | 110 | 904 | 165 | 110 | 307.41 | 0.0002632 | 9e-05 | 2376 | 0.00022757 | 5.2922e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00022757 | 49.1953 | 49.1953 | 0%
North Coast | HU_Humboldt | ARCATA 1122 | 361 | ARCATA 112233060 | 7e-06 | 19.4853 | 0.80625 | 0 | 0.80625 | 0 | 557 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 1024 |  | 187 | 124 | 1024 | 187 | 124 | 348.35 | 3.5925e-07 | 0 | 2377 | 4.7597e-05 | 5.2885e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.7597e-05 | 231.938 | 231.938 | 0%
North Coast | HU_Humboldt | GUALALA 1112 | 7979 | GUALALA 11124431 | 2.5e-05 | 29.7017 | 1.1778 | 0 | 1.1778 | 0 | 771 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 1 | 1412 |  | 257 | 170 | 1412 | 257 | 170 | 479.17 | 8.417e-07 | 0 | 2378 | 0.00014662 | 5.2364e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00014662 | 218.1959 | 218.1959 | 0%
Central Coast | CC_Central Coast | OTTER 1101 | 4324 | OTTER 1101440 | 0.00731 | 155.7291 | 8.067 | 0 | 8.067 | 0 | 1245 | 0 | 0 | 0 | 0 | 0 | 0 | 189 | 1 | 2273 |  | 412 | 272 | 2273 | 412 | 272 | 769.01 | 4.694e-05 | 4e-05 | 2380 | 0.00040238 | 5.2257e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00040238 | 51.072 | 51.072 | 0%
North Coast | HU_Humboldt | BIG RIVER 1101 | 7630 | BIG RIVER 11015065 | 1.7e-05 | 38.9958 | 1.4259 | 0 | 1.4259 | 0 | 623 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 1 | 1144 |  | 208 | 138 | 1144 | 208 | 138 | 387.92 | 4.3594e-07 | 0 | 2381 | 0.0001462 | 5.2216e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0001462 | 145.868 | 145.868 | 0%
Bay Area | DI_Diablo | RESEARCH 2102 | 4574 | RESEARCH 21029746 | 9.8e-05 | 30.7143 | 1.3644 | 0 | 1.3644 | 0 | 417 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 1 | 770 |  | 141 | 94 | 770 | 141 | 94 | 262.47 | 3.1907e-06 | 0 | 2384 | 8.6735e-05 | 5.102e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.6735e-05 | 103.3426 | 103.3426 | 0%
Bay Area | DI_Diablo | SOBRANTE 1101 | 1451 | SOBRANTE 1101circuit_breaker | 0.003945 | 286.5033 | 11.6383 | 0 | 11.6383 | 0 | 1896 | 0 | 0 | 0 | 0 | 0 | 0 | 349 | 1 | 3455 |  | 625 | 413 | 3455 | 625 | 413 | 1167.2 | 1.3769e-05 | 2e-05 | 2385 | 0.0011088 | 5.0631e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0011088 | 53.7022 | 53.7022 | 0%
Bay Area | DI_Diablo | TASSAJARA 2108 | 3285 | TASSAJARA 210812712 | 5.3e-05 | 19.7156 | 0.76383 | 0 | 0.76383 | 0 | 193 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1 | 363 |  | 67 | 45 | 363 | 67 | 45 | 124.46 | 2.6882e-06 | 0 | 2386 | 9.0181e-05 | 5.0101e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.0181e-05 | 87.7163 | 87.7163 | 0%
Central Coast | CC_Central Coast | ROB ROY 2105 | 6149 | ROB ROY 210571630 | 3.9e-05 | 34.1039 | 1.6288 | 0 | 1.6288 | 0 | 518 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 1 | 953 |  | 174 | 115 | 953 | 174 | 115 | 324.15 | 1.1436e-06 | 0 | 2387 | 7.5066e-05 | 5.0044e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.5066e-05 | 106.8279 | 106.8279 | 0%
Sierra | SI_Sierra | BRUNSWICK 1103 | 7769 | BRUNSWICK 11038918 | 0.009179 | 39.3281 | 1.3866 | 0 | 1.3866 | 0 | 864 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 1 | 1581 |  | 287 | 190 | 1581 | 287 | 190 | 535.48 | 0.0002334 | 0.00014 | 2388 | 9.9772e-06 | 4.9886e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.9772e-06 | 206.9881 | 206.9881 | 0%
North Coast | SO_Sonoma | PETALUMA C 1109 | 7309 | PETALUMA C 1109738866 | 0.8882 | 71.3795 | 2.022 | 0 | 2.022 | 0 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 1 | 259 |  | 49 | 33 | 259 | 49 | 33 | 90.44 | 0.012443 | 0.00127 | 2390 | 4.897e-06 | 4.897e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.897e-06 | 24.2338 | 24.2338 | 0%
Bay Area | DI_Diablo | ROSSMOOR 1106 | 391 | ROSSMOOR 1104circuit_breaker | 6e-06 | 2.9935 | 0.2322 | 0 | 0.2322 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 99 |  | 20 | 14 | 99 | 20 | 14 | 36.31 | 2.0044e-06 | 0 | 2391 | 9.7642e-06 | 4.8821e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.7642e-06 | 86.1338 | 86.1338 | 0%
Central Coast | DA_De Anza | SARATOGA 1107 | 429 | SARATOGA 1107LC26 | 0.000329 | 144.4696 | 6.1222 | 0 | 6.1222 | 0 | 1449 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 1 | 2644 |  | 479 | 316 | 2644 | 479 | 316 | 894.19 | 2.2773e-06 | 0 | 2392 | 0.00046741 | 4.8689e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00046741 | 78.2404 | 78.2404 | 0%
North Coast | HU_Humboldt | HIGHLANDS 1104 | 524 | HIGHLANDS 110439458 | 2.6e-05 | 14.0134 | 1.428 | 0 | 1.428 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1 | 103 |  | 21 | 14 | 103 | 21 | 14 | 38.04 | 1.8554e-06 | 0 | 2393 | 7.2926e-05 | 4.8617e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.2926e-05 | 14.7056 | 14.7056 | 0%
Central Coast | SJ_San Jose | HICKS 2101 | 2769 | HICKS 2101XR250 | 0.000473 | 176.433 | 7.5275 | 0 | 7.5275 | 0 | 1291 | 0 | 0 | 0 | 0 | 0 | 0 | 187 | 1 | 2357 |  | 427 | 282 | 2357 | 427 | 282 | 797.12 | 2.6809e-06 | 0 | 2394 | 0.00050767 | 4.7894e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00050767 | 56.7256 | 56.7256 | 0%
North Coast | NC_North Coast | RIO DELL 1102 | 2728 | RIO DELL 1102circuit_breaker | 0.003777 | 19.5063 | 0.85019 | 0 | 0.85019 | 0 | 241 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1 | 450 |  | 83 | 56 | 450 | 83 | 56 | 154.21 | 0.00019363 | 3e-05 | 2395 | 3.3498e-05 | 4.7855e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.3498e-05 | 97.6253 | 97.6253 | 0%
North Coast | HU_Humboldt | GUALALA 1111 | 5345 | GUALALA 1111circuit_breaker | 6.5e-05 | 82.6601 | 3.3388 | 0 | 3.3388 | 0 | 1813 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1 | 3305 |  | 598 | 395 | 3305 | 598 | 395 | 1116.71 | 7.8635e-07 | 0 | 2396 | 0.00032432 | 4.7003e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00032432 | 179.1049 | 179.1049 | 0%
North Coast | SO_Sonoma | DUNBAR 1101 | 625 | DUNBAR 1101160 | 0.15307 | 57.2028 | 2.6915 | 1.0155 | 1.6758 | 1.9339 | 235 | 171 | 63 | 32 | 6 | 3 | 0 | 87 | 0.28147 | 295 |  | 86 | 47 | 124 | 80 | 44 | 120.76 | 0.002676 | 0.00045 | 2397 | 0.0001075 | 4.6738e-06 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.6929e-05 | 47.7396 | 31.9527 | 37.73%
Central Coast | DA_De Anza | LOS GATOS 1108 | 751 | LOS GATOS 1108LB86 | 0.000197 | 81.4977 | 3.8398 | 0 | 3.8398 | 0 | 634 | 0 | 0 | 0 | 0 | 0 | 0 | 133 | 1 | 1164 |  | 212 | 140 | 1164 | 212 | 140 | 395.2 | 2.4172e-06 | 0 | 2398 | 0.00030371 | 4.6724e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00030371 | 55.2116 | 55.2116 | 0%
Bay Area | EB_East Bay | EL CERRITO G 1112 | 4900 | EL CERRITO G 1112BR178 | 9.6e-05 | 29.414 | 1.7956 | 0 | 1.7956 | 0 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 1 | 432 |  | 80 | 54 | 432 | 80 | 54 | 148.48 | 3.2637e-06 | 0 | 2399 | 9.6974e-05 | 4.6178e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.6974e-05 | 44.5523 | 44.5523 | 0%
Central Valley | ST_Stockton | WEST POINT 1102 | 5281 | WEST POINT 11025357 | 6e-05 | 33.5143 | 1.7417 | 0 | 1.7417 | 0 | 211 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 1 | 395 |  | 73 | 49 | 395 | 73 | 49 | 135.56 | 1.7903e-06 | 0 | 2400 | 0.0001938 | 4.6142e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0001938 | 41.9139 | 41.9139 | 0%
Central Coast | CC_Central Coast | ROB ROY 2105 | 3149 | ROB ROY 210512474 | 0.000138 | 68.0048 | 3.9299 | 0 | 3.9299 | 0 | 692 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 1 | 1269 |  | 231 | 153 | 1269 | 231 | 153 | 430.68 | 2.0293e-06 | 0 | 2402 | 0.00018694 | 4.5594e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00018694 | 58.7798 | 58.7798 | 0%
North Coast | SO_Sonoma | PETALUMA C 1108 | 5241 | PETALUMA C 1108600 | 4.2277 | 150.7313 | 5.4606 | 4.1892 | 1.2714 | 5.4606 | 422 | 669 | 210 | 101 | 169 | 77 | 0 | 290 | 0 | 669 |  | 210 | 101 | 0 | 41 | 24 | 56.17 | 0.028048 | 0.00239 | 2403 | 4.557e-06 | 4.557e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.061e-06 | 32.2479 | 38.4573 | 76.72%
North Coast | SO_Sonoma | FITCH MOUNTAIN 1111 | 9360 | 5060 | 9.9e-05 | 17.7187 | 0.38409 | 0 | 0.38409 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 132 |  | 26 | 18 | 132 | 26 | 18 | 47.5 | 5.5873e-06 | 0 | 2404 | 1.8011e-05 | 4.5029e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.8011e-05 | 67.6923 | 67.6923 | 0%
Sierra | SA_Sacramento | DOBBINS 1101 | 9013 | DOBBINS 1101circuit_breaker | 0.003574 | 40.7996 | 1.3884 | 0 | 1.3884 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1 | 114 |  | 23 | 16 | 114 | 23 | 16 | 41.77 | 8.7599e-05 | 0 | 2405 | 4.0462e-05 | 4.4957e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.0462e-05 | 16.5653 | 16.5653 | 0%
Central Coast | CC_Central Coast | LAURELES 1111 | 3917 | LAURELES 1111circuit_breaker | 0.001533 | 181.327 | 7.6019 | 6.9377 | 0.6642 | 7.6019 | 337 | 775 | 165 | 83 | 162 | 80 | 0 | 236 | 0 | 775 |  | 165 | 83 | 0 | 3 | 3 | 4.11 | 8.4543e-06 | 0 | 2406 | 0.00030109 | 4.4939e-06 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.6307e-05 | 4.5167 | 21.7051 | 91.26%
North Coast | HU_Humboldt | REDBUD 1102 | 395 | REDBUD 1102922 | 0.00788 | 120.8912 | 7.6883 | 0.25473 | 7.4335 | 0.59811 | 482 | 59 | 11 | 9 | 0 | 0 | 0 | 289 | 0.92221 | 878 |  | 160 | 108 | 819 | 160 | 108 | 292.91 | 6.5183e-05 | 2e-05 | 2407 | 0.00036705 | 4.4762e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00035489 | 21.5241 | 20.811 | 3.313%
Bay Area | PE_Peninsula | PACIFICA 1103 | 1360 | PACIFICA 110311153 | 0.000186 | 48.293 | 2.664 | 0 | 2.664 | 0 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 1 | 406 |  | 75 | 50 | 406 | 75 | 50 | 139.29 | 3.8515e-06 | 0 | 2408 | 6.6935e-05 | 4.4623e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.6935e-05 | 28.153 | 28.153 | 0%
North Valley | NV_North Valley | BOGARD 1101 | 9841 | BOGARD 1101circuit_breaker | 3.7e-05 | 20.9138 | 0.47424 | 0 | 0.47424 | 0 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1 | 299 |  | 56 | 38 | 299 | 56 | 38 | 103.63 | 1.7692e-06 | 0 | 2409 | 2.6759e-05 | 4.4599e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.6759e-05 | 118.0831 | 118.0831 | 0%
North Coast | SO_Sonoma | MONROE 2103 | 8330 | MONROE 210392868 | 8.1e-05 | 28.507 | 0.52557 | 0 | 0.52557 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1 | 79 |  | 16 | 12 | 79 | 16 | 12 | 29.03 | 2.8414e-06 | 0 | 2410 | 1.321e-05 | 4.4034e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.321e-05 | 30.4432 | 30.4432 | 0%
Bay Area | PE_Peninsula | HALF MOON BAY 1102 | 6675 | HALF MOON BAY 110148868 | 5.4e-05 | 17.9853 | 1.2125 | 0 | 1.2125 | 0 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1 | 245 |  | 46 | 31 | 245 | 46 | 31 | 85.07 | 3.0025e-06 | 0 | 2411 | 3.0794e-05 | 4.3991e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.0794e-05 | 37.9381 | 37.9381 | 0%
Bay Area | DI_Diablo | RESEARCH 2102 | 791 | RESEARCH 210263274 | 8e-05 | 31.3184 | 2.0705 | 0 | 2.0705 | 0 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 1 | 938 |  | 171 | 114 | 938 | 171 | 114 | 318.69 | 2.5544e-06 | 0 | 2412 | 9.6717e-05 | 4.3962e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.6717e-05 | 82.5906 | 82.5906 | 0%
North Coast | SO_Sonoma | FORT ROSS 1121 | 6333 | FORT ROSS 1121134 | 0.18992 | 186.631 | 8.2203 | 0 | 8.2203 | 0 | 4741 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 1 | 8622 |  | 1557 | 1026 | 8622 | 1557 | 1026 | 2909.07 | 0.0010176 | 0.00329 | 2413 | 1.3181e-05 | 4.3938e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.3181e-05 | 189.4099 | 189.4099 | 0%
Bay Area | DI_Diablo | ROSSMOOR 1107 | 7824 | ROSSMOOR 11077311 | 2.4e-05 | 14.4376 | 0.056439 | 0 | 0.056439 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 25 |  | 6 | 5 | 25 | 6 | 5 | 10.47 | 1.6623e-06 | 0 | 2414 | 4.3596e-06 | 4.3596e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.3596e-06 | 106.3087 | 106.3087 | 0%
Central Coast | CC_Central Coast | ROB ROY 2105 | 2056 | ROB ROY 210512586 | 7.4e-05 | 33.9572 | 2.5879 | 0 | 2.5879 | 0 | 381 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 1 | 704 |  | 129 | 86 | 704 | 129 | 86 | 240.09 | 2.1792e-06 | 0 | 2417 | 7.3658e-05 | 4.3328e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.3658e-05 | 49.8478 | 49.8478 | 0%
Central Coast | DA_De Anza | SARATOGA 1104 | 260 | SARATOGA 110413314 | 6.6e-05 | 28.1888 | 1.6066 | 0 | 1.6066 | 0 | 309 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 1 | 573 |  | 105 | 70 | 573 | 105 | 70 | 195.42 | 2.3414e-06 | 0 | 2418 | 0.00019847 | 4.3146e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00019847 | 65.3542 | 65.3542 | 0%
Bay Area | PE_Peninsula | WATERSHED 0402 | 8777 | WATERSHED 0402circuit_breaker | 7e-06 | 1.8463 | 0.37045 | 0 | 0.37045 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 47 |  | 10 | 8 | 47 | 10 | 8 | 17.93 | 3.7914e-06 | 0 | 2419 | 8.5873e-06 | 4.2937e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.5873e-06 | 26.9939 | 26.9939 | 0%
North Coast | SO_Sonoma | PETALUMA C 1109 | 4616 | PETALUMA C 110948000 | 0.57846 | 245.9367 | 9.4848 | 0 | 9.4848 | 0 | 288 | 0 | 0 | 0 | 0 | 0 | 0 | 179 | 1 | 535 |  | 99 | 66 | 535 | 99 | 66 | 183.78 | 0.0023521 | 0.00048 | 2420 | 3.8478e-05 | 4.2754e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.8478e-05 | 10.4377 | 10.4377 | 0%
Central Coast | CC_Central Coast | ROB ROY 2105 | 3894 | ROB ROY 210512584 | 0.000161 | 70.2543 | 3.4862 | 0 | 3.4862 | 0 | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 1 | 622 |  | 114 | 76 | 622 | 114 | 76 | 212.16 | 2.2917e-06 | 0 | 2421 | 0.00015787 | 4.2667e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00015787 | 32.7006 | 32.7006 | 0%
Central Coast | LP_Los Padres | ATASCADERO 1102 | 6777 | ATASCADERO 1102A26 | 0.080828 | 27.9028 | 1.2038 | 0 | 1.2038 | 0 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 1 | 178 |  | 34 | 23 | 178 | 34 | 23 | 62.6 | 0.0028968 | 0.0002 | 2422 | 1.7062e-05 | 4.2654e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.7062e-05 | 28.2442 | 28.2442 | 0%
North Coast | HU_Humboldt | ANNAPOLIS 1101 | 5237 | ANNAPOLIS 1101554 | 0.6933 | 580.3168 | 27.1212 | 0 | 27.1212 | 0 | 14053 | 0 | 0 | 0 | 0 | 0 | 0 | 469 | 1 | 25532 |  | 4607 | 3035 | 25532 | 4607 | 3035 | 8609.47 | 0.0011947 | 0.01144 | 2423 | 0.00021721 | 4.259e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 4. >30 - 40% | 0.00021721 | 169.867 | 169.867 | 0%
Central Coast | CC_Central Coast | ROB ROY 2105 | 4682 | ROB ROY 2105circuit_breaker | 3.5e-05 | 14.6403 | 1.0898 | 0 | 1.0898 | 0 | 171 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1 | 323 |  | 60 | 41 | 323 | 60 | 41 | 111.27 | 2.3907e-06 | 0 | 2424 | 2.5382e-05 | 4.2303e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.5382e-05 | 55.0574 | 55.0574 | 0%
Bay Area | EB_East Bay | OAKLAND K 1102 | 5659 | OAKLAND K 1102CR014 | 0.00023 | 250.8499 | 12.3305 | 4.0078 | 8.3225 | 9.1402 | 3173 | 4261 | 900 | 500 | 369 | 173 | 0 | 473 | 0.25874 | 5755 |  | 1170 | 678 | 1494 | 801 | 505 | 1231.83 | 9.1688e-07 | 0 | 2426 | 0.00062696 | 4.2078e-06 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00042317 | 96.2447 | 94.8867 | 32.5%
Sierra | SI_Sierra | CLARKSVILLE 2106 | 6973 | CLARKSVILLE 210619642 | 0.36086 | 9.0797 | 0.85208 | 0 | 0.85208 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1 | 74 |  | 15 | 11 | 74 | 15 | 11 | 27.21 | 0.039744 | 0.00124 | 2427 | 4.1877e-06 | 4.1877e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.1877e-06 | 17.6039 | 17.6039 | 0%
Central Coast | CC_Central Coast | PAUL SWEET 2109 | 2181 | PAUL SWEET 2109circuit_breaker | 0.000211 | 111.2254 | 4.8383 | 0 | 4.8383 | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 1 | 2101 |  | 381 | 252 | 2101 | 381 | 252 | 711.06 | 1.897e-06 | 0 | 2428 | 0.0001963 | 4.1765e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0001963 | 78.7474 | 78.7474 | 0%
North Coast | SO_Sonoma | RINCON 1102 | 839 | RINCON 1102644 | 2.4e-05 | 9.529 | 0.37405 | 0 | 0.37405 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1 | 56 |  | 12 | 9 | 56 | 12 | 9 | 21.48 | 2.5186e-06 | 0 | 2429 | 2.5057e-05 | 4.1761e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.5057e-05 | 32.081 | 32.081 | 0%
Bay Area | PE_Peninsula | PACIFICA 1101 | 5223 | PACIFICA 1101circuit_breaker | 0.004607 | 6.6018 | 0.15777 | 0 | 0.15777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.00069784 | 1e-05 | 2430 | 1.2515e-05 | 4.1715e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.2515e-05 | 25.3541 | 25.3541 | 0%
Sierra | SI_Sierra | BELL 1108 | 8784 | BELL 110880680 | 1.1e-05 | 8.8823 | 0.55568 | 0 | 0.55568 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 1 | 150 |  | 29 | 20 | 150 | 29 | 20 | 53.23 | 1.2384e-06 | 0 | 2431 | 2.5012e-05 | 4.1687e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.5012e-05 | 52.1881 | 52.1881 | 0%
Central Coast | DA_De Anza | LOS GATOS 1106 | 7508 | LOS GATOS 1106circuit_breaker | 0.000173 | 100.2341 | 5.2553 | 0 | 5.2553 | 0 | 833 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 1 | 1525 |  | 277 | 183 | 1525 | 277 | 183 | 516.74 | 1.726e-06 | 0 | 2432 | 0.00038737 | 4.1653e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00038737 | 52.7087 | 52.7087 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1109 | 946 | SAN RAFAEL 110991742 | 9.9e-05 | 84.9272 | 4.0392 | 0 | 4.0392 | 0 | 707 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 1 | 1296 |  | 236 | 156 | 1296 | 236 | 156 | 439.96 | 1.1657e-06 | 0 | 2433 | 0.00014567 | 4.1621e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00014567 | 58.4273 | 58.4273 | 0%
Central Coast | CC_Central Coast | SOLEDAD 2101 | 4391 | SOLEDAD 21017056 | 0.001044 | 81.7849 | 4.9369 | 0 | 4.9369 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 1 | 49 |  | 11 | 8 | 49 | 11 | 8 | 19.48 | 1.2765e-05 | 0 | 2434 | 8.2761e-06 | 4.1381e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.2761e-06 | 2.2281 | 2.2281 | 0%
Bay Area | DI_Diablo | LAKEWOOD 2107 | 2882 | LAKEWOOD 210769586 | 0.000243 | 133.1152 | 5.8561 | 0 | 5.8561 | 0 | 907 | 0 | 0 | 0 | 0 | 0 | 0 | 184 | 1 | 1659 |  | 301 | 199 | 1659 | 301 | 199 | 561.68 | 1.8255e-06 | 0 | 2435 | 0.00036586 | 4.1108e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00036586 | 51.3997 | 51.3997 | 0%
Bay Area | DI_Diablo | LAS AROMAS 0401 | 3836 | LAS AROMAS 04013342 | 5.5e-05 | 54.0453 | 3.1992 | 0 | 3.1992 | 0 | 671 | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 1 | 1231 |  | 224 | 148 | 1231 | 224 | 148 | 417.67 | 1.0177e-06 | 0 | 2436 | 0.00015188 | 4.1048e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00015188 | 70.0166 | 70.0166 | 0%
North Coast | NC_North Coast | RIO DELL 1102 | 193 | RIO DELL 11028768 | 0.001412 | 10.3754 | 0.82652 | 0 | 0.82652 | 0 | 242 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 1 | 452 |  | 83 | 56 | 452 | 83 | 56 | 154.39 | 0.00013609 | 2e-05 | 2437 | 2.0426e-05 | 4.0852e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.0426e-05 | 100.4216 | 100.4216 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1108 | 726 | SAN RAFAEL 1104circuit_breaker | 0.064904 | 158.8315 | 9.7896 | 0 | 9.7896 | 0 | 1254 | 0 | 0 | 0 | 0 | 0 | 0 | 384 | 1 | 2289 |  | 415 | 274 | 2289 | 415 | 274 | 774.56 | 0.00040863 | 0.00035 | 2439 | 0.0001956 | 4.0751e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0001956 | 42.392 | 42.392 | 0%
Bay Area | NB_North Bay | MONTICELLO 1101 | 8271 | MONTICELLO 110152910 | 0.018799 | 80.791 | 2.518 | 0 | 2.518 | 0 | 183 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 1 | 345 |  | 64 | 43 | 345 | 64 | 43 | 118.73 | 0.00023269 | 3e-05 | 2440 | 1.6221e-05 | 4.0553e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.6221e-05 | 25.4171 | 25.4171 | 0%
Central Coast | DA_De Anza | SARATOGA 1106 | 1259 | SARATOGA 1106LC22 | 0.000364 | 203.7133 | 10.0098 | 0 | 10.0098 | 0 | 1738 | 0 | 0 | 0 | 0 | 0 | 0 | 285 | 1 | 3168 |  | 573 | 379 | 3168 | 573 | 379 | 1070.13 | 1.7868e-06 | 0 | 2441 | 0.00048633 | 4.0527e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00048633 | 57.2436 | 57.2436 | 0%
Bay Area | DI_Diablo | LAS AROMAS 0401 | 3969 | LAS AROMAS 0401LA401R | 7.7e-05 | 66.4112 | 5.0386 | 0 | 5.0386 | 0 | 1052 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 1 | 1923 |  | 349 | 231 | 1923 | 349 | 231 | 651.2 | 1.1594e-06 | 0 | 2442 | 0.00017778 | 4.0405e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00017778 | 69.2648 | 69.2648 | 0%
Bay Area | NB_North Bay | ALTO 1124 | 2281 | ALTO 1124circuit_breaker | 2.4e-05 | 28.168 | 1.6746 | 0 | 1.6746 | 0 | 214 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 1 | 401 |  | 74 | 50 | 401 | 74 | 50 | 137.47 | 8.5203e-07 | 0 | 2443 | 0.00012115 | 4.0384e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00012115 | 44.1891 | 44.1891 | 0%
Sierra | SI_Sierra | DIAMOND SPRINGS 1106 | 5023 | DIAMOND SPRINGS 1106circuit_breaker | 5.2e-05 | 16.3394 | 0.31723 | 0 | 0.31723 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1 | 181 |  | 35 | 24 | 181 | 35 | 24 | 64.24 | 3.1825e-06 | 0 | 2444 | 1.2109e-05 | 4.0364e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.2109e-05 | 110.3284 | 110.3284 | 0%
North Coast | HU_Humboldt | KONOCTI 1102 | 180 | CLEAR LAKE 110192870 | 0.001319 | 2.1204 | 0.30322 | 0.21932 | 0.083902 | 0.30322 | 21 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.00062205 | 0 | 2445 | 1.2012e-05 | 4.0039e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.3236e-06 | 0 | 0 | 72.33%
Bay Area | EB_East Bay | OAKLAND K 1104 | 1418 | OAKLAND K 1104CR204 | 9.1e-05 | 67.0463 | 3.4002 | 0.20303 | 3.1972 | 0.64943 | 1113 | 371 | 61 | 43 | 25 | 10 | 0 | 122 | 0.809 | 2016 |  | 359 | 240 | 1645 | 334 | 230 | 605.63 | 1.3573e-06 | 0 | 2446 | 0.00020805 | 4.0009e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00019562 | 104.4677 | 105.5824 | 5.971%
North Coast | SO_Sonoma | LAKEVILLE 1102 | 5970 | LAKEVILLE 1102530 | 0.04903 | 16.0123 | 0.63144 | 0.48277 | 0.14848 | 0.63144 | 24 | 52 | 9 | 7 | 8 | 6 | 0 | 19 | 0 | 52 |  | 9 | 7 | 0 | 1 | 1 | 1.37 | 0.003062 | 1e-05 | 2447 | 3.9985e-06 | 3.9985e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.4027e-07 | 6.7347 | 14.2531 | 76.45%
Central Coast | SJ_San Jose | MORGAN HILL 2105 | 5792 | MORGAN HILL 2105circuit_breaker | 0.072558 | 18.5251 | 0.78087 | 0 | 0.78087 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1 | 114 |  | 23 | 16 | 114 | 23 | 16 | 41.77 | 0.0039167 | 0.00019 | 2448 | 3.1829e-05 | 3.9786e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.1829e-05 | 29.4543 | 29.4543 | 0%
Bay Area | MI_Mission | RADUM 1105 | 717 | RADUM 1105MR282 | 0.000231 | 83.4824 | 4.8742 | 0.19867 | 4.6756 | 0.44432 | 1178 | 127 | 9 | 2 | 0 | 0 | 0 | 166 | 0.90884 | 2082 |  | 363 | 236 | 1955 | 363 | 236 | 673.26 | 2.7671e-06 | 0 | 2449 | 0.00020274 | 3.9753e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00019448 | 77.6376 | 74.4731 | 4.076%
Bay Area | EB_East Bay | OAKLAND X 1106 | 9195 | OAKLAND X 1106CR266 | 1.9e-05 | 22.4046 | 0.84034 | 0 | 0.84034 | 0 | 487 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 897 |  | 164 | 109 | 897 | 164 | 109 | 305.41 | 8.4804e-07 | 0 | 2450 | 7.0871e-05 | 3.9373e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.0871e-05 | 195.1589 | 195.1589 | 0%
North Coast | HU_Humboldt | UKIAH 1114 | 7432 | UKIAH 111472990 | 3e-06 | 7.1019 | 0.25303 | 0 | 0.25303 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 83 |  | 17 | 12 | 83 | 17 | 12 | 30.76 | 4.2242e-07 | 0 | 2451 | 4.7197e-05 | 3.9331e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.7197e-05 | 67.1856 | 67.1856 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1105 | 5148 | SAN RAFAEL 1105534 | 2.4e-05 | 39.5617 | 1.722 | 0 | 1.722 | 0 | 456 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 1 | 840 |  | 154 | 102 | 840 | 154 | 102 | 286.58 | 6.0665e-07 | 0 | 2452 | 6.6803e-05 | 3.9296e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.6803e-05 | 89.4325 | 89.4325 | 0%
Central Valley | ST_Stockton | FROGTOWN 1702 | 4363 | FROGTOWN 170274648 | 0.003039 | 30.0119 | 3.0816 | 0 | 3.0816 | 0 | 203 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 1 | 381 |  | 71 | 47 | 381 | 71 | 47 | 131.56 | 0.00010126 | 1e-05 | 2453 | 3.9206e-05 | 3.9206e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.9206e-05 | 23.0398 | 23.0398 | 0%
Bay Area | NB_North Bay | BOLINAS 1101 | 1446 | BOLINAS 1101528 | 0.000969 | 34.6303 | 1.5449 | 0 | 1.5449 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 1 | 154 |  | 30 | 21 | 154 | 30 | 21 | 54.96 | 2.7981e-05 | 0 | 2454 | 7.4186e-05 | 3.9045e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.4186e-05 | 19.4189 | 19.4189 | 0%
Central Valley | ST_Stockton | STANISLAUS 1702 | 5484 | STANISLAUS 170275348 | 0.016065 | 153.888 | 7.4284 | 1.0021 | 6.4263 | 7.4284 | 4565 | 3084 | 1460 | 593 | 1442 | 578 | 0 | 384 | 0 | 3084 |  | 1460 | 593 | 0 | 18 | 15 | 24.66 | 0.00010439 | 0 | 2457 | 3.8878e-06 | 3.8878e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.3634e-06 | 2.801 | 196.5428 | 13.49%
Central Coast | CC_Central Coast | ROB ROY 2104 | 4545 | ROB ROY 210412596 | 0.000361 | 149.0991 | 8.9943 | 0 | 8.9943 | 0 | 1183 | 0 | 0 | 0 | 0 | 0 | 0 | 211 | 1 | 2161 |  | 392 | 259 | 2161 | 392 | 259 | 731.53 | 2.4212e-06 | 0 | 2458 | 0.00039621 | 3.8467e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00039621 | 43.5831 | 43.5831 | 0%
Central Valley | YO_Yosemite | MIWUK 1702 | 6304 | MIWUK 170247143 | 5.7e-05 | 50.7866 | 2.2051 | 0 | 2.2051 | 1.6996 | 671 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 0.22924 | 282 |  | 51 | 34 | 282 | 51 | 34 | 95.25 | 1.1223e-06 | 0 | 2459 | 0.00021775 | 3.8203e-06 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00021775 | 23.1281 | 23.1281 | 0%
Bay Area | EB_East Bay | OAKLAND X 1104 | 814 | OAKLAND X 1104CR022 | 8.2e-05 | 134.1429 | 9.0773 | 4.5625 | 4.5146 | 6.0786 | 2365 | 3124 | 1137 | 470 | 966 | 362 | 4 | 571 | 0.33035 | 4547 |  | 1394 | 640 | 1423 | 428 | 278 | 714.43 | 6.1129e-07 | 0 | 2461 | 0.00025745 | 3.786e-06 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00012804 | 94.8039 | 153.5704 | 50.26%
Central Valley | YO_Yosemite | CURTIS 1702 | 1279 | CURTIS 17028000 | 0.068003 | 321.7128 | 12.8792 | 0.092235 | 12.7869 | 0.48333 | 3451 | 75 | 44 | 22 | 38 | 16 | 0 | 335 | 0.96247 | 6119 |  | 1136 | 742 | 6044 | 1098 | 726 | 2048.22 | 0.00021138 | 0.00048 | 2462 | 0.00081584 | 3.7253e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00081 | 85.8689 | 88.2045 | 0.7162%
Bay Area | EB_East Bay | OAKLAND X 1104 | 4106 | OAKLAND X 1104CR214 | 3.6e-05 | 54.718 | 2.4619 | 2.0138 | 0.44811 | 2.4619 | 600 | 1245 | 499 | 221 | 455 | 198 | 0 | 197 | 0 | 1245 |  | 499 | 221 | 0 | 44 | 23 | 60.28 | 6.5792e-07 | 0 | 2463 | 0.00013778 | 3.7238e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.5078e-05 | 98.191 | 202.6864 | 81.8%
North Coast | HU_Humboldt | GUALALA 1111 | 9419 | GUALALA 1111498 | 6.8e-05 | 64.3485 | 3.0759 | 0 | 3.0759 | 0 | 814 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 1 | 1490 |  | 271 | 179 | 1490 | 271 | 179 | 505.37 | 1.0567e-06 | 0 | 2464 | 0.00011045 | 3.6816e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00011045 | 88.1029 | 88.1029 | 0%
North Coast | HU_Humboldt | KONOCTI 1108 | 4535 | KONOCTI 11084041 | 0.001218 | 32.8138 | 2.036 | 0 | 2.036 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 1 | 107 |  | 21 | 15 | 107 | 21 | 15 | 38.4 | 3.7119e-05 | 0 | 2466 | 5.507e-05 | 3.6713e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.507e-05 | 10.3144 | 10.3144 | 0%
Central Coast | DA_De Anza | LOS GATOS 1102 | 233 | LOS GATOS 1102circuit_breaker | 5.7e-05 | 53.138 | 2.9085 | 0 | 2.9085 | 0 | 562 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 1 | 1033 |  | 188 | 125 | 1033 | 188 | 125 | 350.53 | 1.0727e-06 | 0 | 2467 | 1.8234e-05 | 3.6469e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.8234e-05 | 64.6376 | 64.6376 | 0%
Bay Area | PE_Peninsula | PACIFICA 1102 | 69 | PACIFICA 11026783 | 0.000122 | 51.1755 | 1.9858 | 0 | 1.9858 | 0 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 1 | 321 |  | 60 | 40 | 321 | 60 | 40 | 111.09 | 2.384e-06 | 0 | 2468 | 4.7363e-05 | 3.6433e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.7363e-05 | 30.2146 | 30.2146 | 0%
Bay Area | NB_North Bay | GREENBRAE 1102 | 548 | GREENBRAE 11021254 | 0.00013 | 127.4592 | 7.0078 | 0 | 7.0078 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 1 | 1737 |  | 315 | 209 | 1737 | 315 | 209 | 587.88 | 1.0199e-06 | 0 | 2469 | 0.0003266 | 3.6289e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0003266 | 44.9501 | 44.9501 | 0%
Central Valley | YO_Yosemite | CURTIS 1702 | 52 | CURTIS 170234426 | 0.000297 | 104.2115 | 4.7994 | 0 | 4.7994 | 0 | 654 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 1 | 1200 |  | 218 | 145 | 1200 | 218 | 145 | 406.66 | 2.85e-06 | 0 | 2471 | 0.00020941 | 3.6106e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00020941 | 45.422 | 45.422 | 0%
Bay Area | EB_East Bay | OAKLAND X 1104 | 2971 | OAKLAND X 1104CR288 | 8e-06 | 62.709 | 2.6614 | 2.1703 | 0.4911 | 2.6614 | 515 | 1095 | 494 | 212 | 451 | 191 | 1 | 247 | 0 | 1095 |  | 494 | 212 | 0 | 43 | 21 | 58.91 | 1.2757e-07 | 0 | 2472 | 0.0001907 | 3.5981e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.5189e-05 | 87.5588 | 185.6191 | 81.55%
North Coast | HU_Humboldt | HARRIS 1108 | 7055 | HARRIS 11082062 | 9e-05 | 74.1669 | 1.7443 | 0 | 1.7443 | 0 | 833 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 1 | 1525 |  | 277 | 183 | 1525 | 277 | 183 | 516.74 | 1.2135e-06 | 0 | 2473 | 0.00010748 | 3.5825e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00010748 | 158.8013 | 158.8013 | 0%
Central Coast | DA_De Anza | LOYOLA 1102 | 7486 | LOYOLA 1102LL12 | 0 | 0 | 0.11705 | 0 | 0.11705 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 110 |  | 22 | 15 | 110 | 22 | 15 | 40.04 | 0 | 0 | 2474 | 7.1431e-06 | 3.5715e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.1431e-06 | 187.9612 | 187.9612 | 0%
Central Coast | CC_Central Coast | PAUL SWEET 2104 | 3681 | PAUL SWEET 210411074 | 9.5e-05 | 54.5231 | 2.8572 | 0 | 2.8572 | 0 | 146 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 1 | 277 |  | 52 | 35 | 277 | 52 | 35 | 96.17 | 1.7424e-06 | 0 | 2475 | 8.5271e-05 | 3.553e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.5271e-05 | 18.1997 | 18.1997 | 0%
North Coast | HU_Humboldt | EUREKA E 1104 | 2863 | EUREKA E 110435934 | 0 | 0.16393 | 3.5475 | 0 | 3.5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 2476 | 3.5303e-06 | 3.5303e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.5303e-06 | 1.1275 | 1.1275 | 0%
Bay Area | DI_Diablo | ROSSMOOR 1106 | 671 | ROSSMOOR 110676468 | 0.012359 | 23.93 | 1.9483 | 0 | 1.9483 | 0 | 201 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 1 | 377 |  | 70 | 47 | 377 | 70 | 47 | 129.83 | 0.00051647 | 8e-05 | 2478 | 3.5112e-05 | 3.5112e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.5112e-05 | 35.9288 | 35.9288 | 0%
Central Valley | YO_Yosemite | CURTIS 1703 | 1229 | CURTIS 17039240 | 0.019222 | 325.0985 | 15.2716 | 2.6455 | 12.6261 | 11.7748 | 5064 | 6921 | 1515 | 667 | 1339 | 545 | 0 | 650 | 0.22897 | 9029 |  | 1896 | 918 | 2108 | 557 | 373 | 952.81 | 5.9127e-05 | 7e-05 | 2479 | 0.00045651 | 3.4848e-06 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00037743 | 44.1148 | 124.1521 | 17.32%
Central Valley | YO_Yosemite | CURTIS 1705 | 6293 | CURTIS 17058170 | 0.000338 | 183.8028 | 7.8977 | 6.2119 | 1.6856 | 7.8148 | 775 | 2296 | 557 | 319 | 520 | 301 | 0 | 377 | 0.010504 | 2311 |  | 560 | 321 | 15 | 40 | 20 | 56.15 | 1.8389e-06 | 0 | 2480 | 0.00034755 | 3.4755e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.4177e-05 | 23.7303 | 70.9065 | 78.65%
Bay Area | DI_Diablo | ROSSMOOR 1101 | 4672 | ROSSMOOR 11018132 | 2.6e-05 | 21.3036 | 0.70682 | 0 | 0.70682 | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 1 | 241 |  | 45 | 31 | 241 | 45 | 31 | 83.34 | 1.2205e-06 | 0 | 2481 | 0.00015929 | 3.4629e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00015929 | 63.6656 | 63.6656 | 0%
North Valley | NV_North Valley | RED BLUFF 1105 | 3113 | RED BLUFF 1105161818 | 0.79096 | 4.0027 | 0.1322 | 0 | 0.1322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.19761 | 0.00164 | 2482 | 3.4538e-06 | 3.4538e-06 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.4538e-06 | 30.2579 | 30.2579 | 0%
Bay Area | DI_Diablo | ORINDA 0401 | 6909 | ORINDA 04013442 | 0.000136 | 120.5626 | 8.3407 | 3.2583 | 5.0826 | 5.0125 | 1637 | 2735 | 362 | 92 | 259 | 46 | 1 | 474 | 0.39903 | 3926 |  | 578 | 234 | 1191 | 319 | 188 | 544.22 | 1.128e-06 | 0 | 2483 | 0.0002585 | 3.4467e-06 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00015752 | 62.7635 | 69.2986 | 39.07%
Bay Area | DI_Diablo | ROSSMOOR 1106 | 5153 | ROSSMOOR 1106L522R | 6.1e-05 | 64.7493 | 4.0445 | 0.00056818 | 4.0439 | 0.79053 | 781 | 94 | 76 | 58 | 38 | 31 | 0 | 171 | 0.80454 | 1245 |  | 285 | 197 | 1151 | 247 | 166 | 441.98 | 9.4209e-07 | 0 | 2484 | 9.9712e-05 | 3.4383e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.9698e-05 | 61.0791 | 70.4659 | 0.01405%
Central Coast | CC_Central Coast | PAUL SWEET 2106 | 227 | PAUL SWEET 210612828 | 3.2e-05 | 22.9008 | 0.77292 | 0 | 0.77292 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 1 | 154 |  | 30 | 21 | 154 | 30 | 21 | 54.96 | 1.3973e-06 | 0 | 2485 | 5.4579e-05 | 3.4112e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.4579e-05 | 38.814 | 38.814 | 0%
North Coast | HU_Humboldt | HARRIS 1108 | 1354 | HARRIS 11084674 | 1.9e-05 | 12.9057 | 0.34659 | 0 | 0.34659 | 0 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 290 |  | 54 | 37 | 290 | 54 | 37 | 100.08 | 1.4722e-06 | 0 | 2486 | 1.7028e-05 | 3.4057e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.7028e-05 | 155.8033 | 155.8033 | 0%
North Coast | SO_Sonoma | COTATI 1104 | 2779 | COTATI 1104circuit_breaker | 0.018443 | 41.9364 | 2.461 | 0 | 2.461 | 0 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 1 | 357 |  | 66 | 45 | 357 | 66 | 45 | 122.55 | 0.00043978 | 6e-05 | 2487 | 0.00012937 | 3.4045e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00012937 | 26.8185 | 26.8185 | 0%
Central Coast | DA_De Anza | SARATOGA 1107 | 3318 | SARATOGA 1107circuit_breaker | 1.3e-05 | 12.6555 | 0.83504 | 0 | 0.83504 | 0 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1 | 299 |  | 56 | 38 | 299 | 56 | 38 | 103.63 | 1.0272e-06 | 0 | 2488 | 6.7959e-06 | 3.3979e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.7959e-06 | 67.0628 | 67.0628 | 0%
Bay Area | DI_Diablo | SOBRANTE 1101 | 5179 | SOBRANTE 110142914 | 1e-05 | 5.6078 | 0.67955 | 0 | 0.67955 | 0 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 1 | 243 |  | 46 | 31 | 243 | 46 | 31 | 84.89 | 1.7832e-06 | 0 | 2489 | 2.7113e-05 | 3.3892e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.7113e-05 | 67.6923 | 67.6923 | 0%
Bay Area | EB_East Bay | VALLEY VIEW 1103 | 4698 | VALLEY VIEW 1103P160 | 8e-06 | 10.0505 | 0.64754 | 0 | 0.64754 | 0 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 188 |  | 36 | 25 | 188 | 36 | 25 | 66.24 | 7.9598e-07 | 0 | 2491 | 2.0269e-05 | 3.3781e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.0269e-05 | 55.5952 | 55.5952 | 0%
Bay Area | DI_Diablo | BRYANT 0402 | 959 | BRYANT 0402circuit_breaker | 3.1e-05 | 16.9994 | 1.3066 | 0 | 1.3066 | 0.29905 | 240 | 83 | 16 | 8 | 6 | 1 | 0 | 42 | 0.77113 | 429 |  | 80 | 51 | 346 | 74 | 50 | 132.52 | 1.8236e-06 | 0 | 2492 | 0.00011321 | 3.3298e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00011321 | 56.6343 | 61.2263 | 0%
Bay Area | DI_Diablo | ROSSMOOR 1102 | 7330 | ROSSMOOR 1102circuit_breaker | 1.2e-05 | 4.9013 | 0.45 | 0 | 0.45 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 81 |  | 17 | 12 | 81 | 17 | 12 | 30.58 | 2.4483e-06 | 0 | 2493 | 2.3304e-05 | 3.3292e-06 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.3304e-05 | 37.7778 | 37.7778 | 0%
Central Valley | YO_Yosemite | CURTIS 1702 | 346 | CURTIS 170210940 | 0.000393 | 264.6348 | 10.8718 | 0.67121 | 10.2004 | 1.59 | 1552 | 494 | 96 | 56 | 72 | 40 | 0 | 330 | 0.85375 | 2911 |  | 534 | 345 | 2417 | 462 | 305 | 850.47 | 1.4851e-06 | 0 | 2495 | 0.00044499 | 3.2962e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00041751 | 45.2924 | 49.118 | 6.174%
Central Coast | DA_De Anza | SARATOGA 1107 | 7676 | SARATOGA 11075696 | 0.000147 | 109.5148 | 4.8364 | 0 | 4.8364 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 1 | 2555 |  | 463 | 306 | 2555 | 463 | 306 | 864.26 | 1.3423e-06 | 0 | 2496 | 0.00028323 | 3.2934e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00028323 | 95.7331 | 95.7331 | 0%
Bay Area | DI_Diablo | SOBRANTE 1102 | 2119 | SOBRANTE 1102L510R | 0.000129 | 108.8901 | 5.896 | 0 | 5.896 | 0 | 1201 | 0 | 0 | 0 | 0 | 0 | 0 | 206 | 1 | 2193 |  | 398 | 263 | 2193 | 398 | 263 | 742.63 | 1.1847e-06 | 0 | 2497 | 0.00046912 | 3.2578e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00046912 | 67.5031 | 67.5031 | 0%
North Coast | HU_Humboldt | HIGHLANDS 1104 | 2117 | HIGHLANDS 1104circuit_breaker | 0.00013 | 107.0203 | 7.4241 | 1.0985 | 6.3256 | 1.3653 | 335 | 185 | 29 | 3 | 25 | 1 | 0 | 226 | 0.81609 | 691 |  | 122 | 65 | 506 | 97 | 64 | 178.43 | 1.2147e-06 | 0 | 2498 | 0.00023075 | 3.2501e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00019661 | 15.3346 | 16.4331 | 14.8%
Central Valley | YO_Yosemite | PEORIA 1701 | 1297 | PEORIA 17013186 | 0.000135 | 192.0955 | 9.7917 | 0 | 9.7917 | 0 | 2687 | 0 | 0 | 0 | 0 | 0 | 0 | 285 | 1 | 4892 |  | 884 | 583 | 4892 | 884 | 583 | 1651.36 | 7.0278e-07 | 0 | 2499 | 0.00017543 | 3.2486e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00017543 | 90.2809 | 90.2809 | 0%
Bay Area | DI_Diablo | SOBRANTE 1102 | 421 | SOBRANTE 1102L520R | 0.000229 | 139.9294 | 5.9193 | 0 | 5.9193 | 0 | 1226 | 0 | 0 | 0 | 0 | 0 | 0 | 187 | 1 | 2239 |  | 406 | 268 | 2239 | 406 | 268 | 757.73 | 1.6365e-06 | 0 | 2500 | 0.00038981 | 3.2484e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00038981 | 68.589 | 68.589 | 0%
Central Coast | CC_Central Coast | HATTON 1102 | 6033 | HATTON 11022010 | 5.8e-05 | 130.149 | 5.8665 | 0 | 5.8665 | 0 | 1182 | 0 | 0 | 0 | 0 | 0 | 0 | 179 | 1 | 2159 |  | 391 | 259 | 2159 | 391 | 259 | 729.98 | 4.4564e-07 | 0 | 2502 | 0.00014188 | 3.2246e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00014188 | 66.6499 | 66.6499 | 0%
North Coast | SO_Sonoma | COTATI 1104 | 4496 | COTATI 1104426 | 0.007634 | 78.1337 | 3.3195 | 0 | 3.3195 | 0 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 1 | 474 |  | 87 | 58 | 474 | 87 | 58 | 161.85 | 9.7704e-05 | 2e-05 | 2503 | 6.7316e-05 | 3.2055e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.7316e-05 | 26.2087 | 26.2087 | 0%
Bay Area | DI_Diablo | MORAGA 1103 | 1202 | MORAGA 110381146 | 0.001078 | 20.6486 | 0.96686 | 0.082576 | 0.88428 | 0.19508 | 295 | 56 | 37 | 35 | 0 | 0 | 0 | 39 | 0.79824 | 493 |  | 117 | 89 | 437 | 117 | 89 | 199.62 | 5.2207e-05 | 1e-05 | 2504 | 4.1627e-05 | 3.2021e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.8072e-05 | 132.311 | 121.0108 | 8.541%
Bay Area | DI_Diablo | LAKEWOOD 2224 | 8711 | LAKEWOOD 2224568670 | 1.8e-05 | 6.9153 | 0.24205 | 0 | 0.24205 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 54 |  | 12 | 9 | 54 | 12 | 9 | 21.3 | 2.6029e-06 | 0 | 2505 | 4.1529e-05 | 3.1945e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.1529e-05 | 49.5775 | 49.5775 | 0%
Bay Area | DI_Diablo | MORAGA 1105 | 1136 | MORAGA 11058354 | 2.4e-05 | 15.2152 | 1.2983 | 0.63693 | 0.66155 | 1.2983 | 84 | 150 | 37 | 7 | 7 | 0 | 0 | 31 | 0 | 150 |  | 37 | 7 | 0 | 30 | 7 | 41.1 | 1.5774e-06 | 0 | 2506 | 1.2775e-05 | 3.1938e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.5098e-06 | 45.3478 | 28.4989 | 49.06%
Bay Area | EB_East Bay | FAIRVIEW 2207 | 2507 | FAIRVIEW 2207P148 | 0.000436 | 31.7414 | 1.5341 | 0 | 1.5341 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 1 | 176 |  | 34 | 23 | 176 | 34 | 23 | 62.42 | 1.3736e-05 | 0 | 2507 | 1.9108e-05 | 3.1846e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.9108e-05 | 22.163 | 22.163 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1109 | 522 | SAN RAFAEL 1109418 | 0.014806 | 103.2466 | 4.6144 | 0 | 4.6144 | 0 | 389 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 1 | 719 |  | 132 | 88 | 719 | 132 | 88 | 245.55 | 0.0001434 | 4e-05 | 2508 | 9.5465e-06 | 3.1822e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.5465e-06 | 28.6061 | 28.6061 | 0%
Central Coast | CC_Central Coast | DOLAN ROAD 1101 | 7461 | DOLAN ROAD 110122158 | 2.3e-05 | 15.4519 | 0.42216 | 0 | 0.42216 | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 185 |  | 35 | 24 | 185 | 35 | 24 | 64.6 | 1.4885e-06 | 0 | 2509 | 1.9013e-05 | 3.1688e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.9013e-05 | 82.9071 | 82.9071 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1101 | 1469 | SAN RAFAEL 1101circuit_breaker | 2.5e-05 | 40.5886 | 2.4011 | 0 | 2.4011 | 0 | 405 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 1 | 748 |  | 137 | 91 | 748 | 137 | 91 | 255.01 | 6.1594e-07 | 0 | 2510 | 0.00010888 | 3.1109e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00010888 | 57.0563 | 57.0563 | 0%
Central Coast | DA_De Anza | LOS GATOS 1107 | 1253 | LOS GATOS 1107circuit_breaker | 0.000328 | 273.8084 | 11.386 | 0 | 11.386 | 0 | 1576 | 0 | 0 | 0 | 0 | 0 | 0 | 296 | 1 | 2874 |  | 520 | 344 | 2874 | 520 | 344 | 971.06 | 1.1979e-06 | 0 | 2511 | 0.00058642 | 3.0703e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00058642 | 45.6702 | 45.6702 | 0%
Bay Area | NB_North Bay | STAFFORD 1102 | 7941 | 1943 | 0.015798 | 37.9185 | 3.0881 | 0 | 3.0881 | 0 | 238 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 1 | 444 |  | 82 | 55 | 444 | 82 | 55 | 152.3 | 0.00041663 | 7e-05 | 2512 | 3.0668e-06 | 3.0668e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.0668e-06 | 26.5538 | 26.5538 | 0%
Bay Area | NB_North Bay | NOVATO 1104 | 4226 | NOVATO 11041282 | 5.5e-05 | 33.0649 | 0.45057 | 0 | 0.45057 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 92 |  | 19 | 13 | 92 | 19 | 13 | 34.31 | 1.6634e-06 | 0 | 2513 | 2.4527e-05 | 3.0659e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.4527e-05 | 42.169 | 42.169 | 0%
Central Coast | DA_De Anza | SARATOGA 1115 | 7585 | SARATOGA 1115LC20 | 8.5e-05 | 63.8068 | 2.8131 | 0 | 2.8131 | 0 | 369 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 1 | 682 |  | 125 | 83 | 682 | 125 | 83 | 232.63 | 1.3321e-06 | 0 | 2514 | 0.0001379 | 3.0645e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0001379 | 44.4355 | 44.4355 | 0%
Bay Area | MI_Mission | CASTRO VALLEY 1108 | 7080 | CASTRO VALLEY 1108MR273 | 0.05181 | 20.8431 | 1.057 | 0 | 1.057 | 0.57576 | 79 | 12 | 11 | 4 | 0 | 0 | 0 | 49 | 0.45529 | 83 |  | 25 | 13 | 71 | 25 | 13 | 40.64 | 0.0024857 | 0.00013 | 2515 | 3.3274e-05 | 3.0249e-06 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.3274e-05 | 23.6517 | 23.6517 | 0%
Central Coast | DA_De Anza | LOS GATOS 1107 | 1701 | LOS GATOS 1101circuit_breaker | 4.6e-05 | 44.0389 | 3.5642 | 0 | 3.5642 | 0 | 565 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 1 | 1038 |  | 189 | 126 | 1038 | 189 | 126 | 352.35 | 1.0445e-06 | 0 | 2517 | 7.5336e-05 | 3.0134e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.5336e-05 | 53.0273 | 53.0273 | 0%
Central Coast | LP_Los Padres | FOOTHILL 1101 | 4981 | FOOTHILL 1101circuit_breaker | 3.1251 | 262.112 | 12.7337 | 0 | 12.7337 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 1 | 194 |  | 37 | 25 | 194 | 37 | 25 | 68.15 | 0.011923 | 0.00092 | 2518 | 5.9886e-06 | 2.9943e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.9886e-06 | 2.9057 | 2.9057 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1101 | 2962 | SAN RAFAEL 1101494 | 7.7e-05 | 76.1827 | 4.0146 | 0 | 4.0146 | 0 | 352 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 1 | 651 |  | 119 | 80 | 651 | 119 | 80 | 221.62 | 1.0107e-06 | 0 | 2519 | 0.00023918 | 2.9897e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00023918 | 29.6419 | 29.6419 | 0%
Bay Area | NB_North Bay | IGNACIO 1104 | 7223 | IGNACIO 1104450582 | 0.000122 | 82.2896 | 3.0955 | 0 | 3.0955 | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1 | 330 |  | 62 | 41 | 330 | 62 | 41 | 114.64 | 1.4826e-06 | 0 | 2520 | 0.00013143 | 2.9871e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00013143 | 20.0294 | 20.0294 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1105 | 4303 | SAN RAFAEL 1105344 | 5.6e-05 | 50.6443 | 1.5095 | 0 | 1.5095 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 1 | 145 |  | 28 | 19 | 145 | 28 | 19 | 51.41 | 1.1058e-06 | 0 | 2521 | 3.2584e-05 | 2.9622e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.2584e-05 | 18.5496 | 18.5496 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1105 | 5127 | SAN RAFAEL 1105circuit_breaker | 0 | 1.1798 | 0.050568 | 0 | 0.050568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 2522 | 8.8044e-06 | 2.9348e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.8044e-06 | 79.1011 | 79.1011 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1106 | 1380 | SAN RAFAEL 11061230 | 1.6e-05 | 19.2338 | 0.80114 | 0 | 0.80114 | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 1 | 241 |  | 45 | 31 | 241 | 45 | 31 | 83.34 | 8.3187e-07 | 0 | 2523 | 5.219e-05 | 2.8995e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.219e-05 | 56.1702 | 56.1702 | 0%
Central Coast | CC_Central Coast | HATTON 1101 | 5252 | HATTON 110137088 | 0.000269 | 222.7163 | 6.7883 | 0 | 6.7883 | 0 | 1559 | 0 | 0 | 0 | 0 | 0 | 0 | 149 | 1 | 2843 |  | 515 | 340 | 2843 | 515 | 340 | 961.42 | 1.2078e-06 | 0 | 2524 | 0.00034905 | 2.8847e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00034905 | 75.8663 | 75.8663 | 0%
Central Coast | CC_Central Coast | LAURELES 1111 | 5428 | LAURELES 11116617 | 5.9e-05 | 39.9474 | 1.882 | 1.765 | 0.11705 | 1.882 | 160 | 172 | 45 | 10 | 45 | 10 | 0 | 51 | 0 | 172 |  | 45 | 10 | 0 | 0 | 0 | 0 | 1.4769e-06 | 0 | 2525 | 6.7954e-05 | 2.8314e-06 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.2262e-06 | 0 | 23.9106 | 93.78%
Central Coast | CC_Central Coast | LAURELES 1112 | 6433 | LAURELES 1112438 | 0.000179 | 92.6547 | 4.8038 | 0 | 4.8038 | 0 | 117 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 1 | 225 |  | 43 | 29 | 225 | 43 | 29 | 79.16 | 1.9319e-06 | 0 | 2526 | 7.3616e-05 | 2.8314e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.3616e-05 | 8.9513 | 8.9513 | 0%
Bay Area | PE_Peninsula | PACIFICA 1104 | 761 | PACIFICA 1104circuit_breaker | 6.2e-05 | 18.5342 | 1.2769 | 0 | 1.2769 | 0 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1 | 270 |  | 51 | 34 | 270 | 51 | 34 | 94.17 | 3.3452e-06 | 0 | 2527 | 1.6968e-05 | 2.828e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.6968e-05 | 39.9407 | 39.9407 | 0%
Central Coast | CC_Central Coast | PRUNEDALE 1110 | 2563 | PRUNEDALE 11103716 | 1.4e-05 | 7.0032 | 0.70777 | 0 | 0.70777 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1 | 118 |  | 23 | 16 | 118 | 23 | 16 | 42.13 | 1.9991e-06 | 0 | 2528 | 1.1293e-05 | 2.8233e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.1293e-05 | 32.4967 | 32.4967 | 0%
Central Coast | LP_Los Padres | SANTA YNEZ 1102 | 5620 | SANTA YNEZ 1102320270 | 4e-06 | 2.6694 | 0.36818 | 0 | 0.36818 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 20 |  | 5 | 5 | 20 | 5 | 5 | 8.65 | 1.4985e-06 | 0 | 2529 | 1.1269e-05 | 2.8173e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.1269e-05 | 13.5802 | 13.5802 | 0%
Central Coast | CC_Central Coast | SAN BENITO 2104 | 1865 | SAN BENITO 2104circuit_breaker | 0.12739 | 42.8984 | 2.31 | 0 | 2.31 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 1 | 154 |  | 30 | 21 | 154 | 30 | 21 | 54.96 | 0.0029696 | 0.00019 | 2530 | 5.3294e-05 | 2.8049e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.3294e-05 | 12.9868 | 12.9868 | 0%
Bay Area | EB_East Bay | BERKELEY F 1103 | 1765 | BERKELEY F 1103BR110 | 3.4e-05 | 49.998 | 3.2604 | 0 | 3.2604 | 0 | 619 | 0 | 0 | 0 | 0 | 0 | 0 | 137 | 1 | 1136 |  | 207 | 137 | 1136 | 207 | 137 | 385.83 | 6.8003e-07 | 0 | 2531 | 7.5657e-05 | 2.8021e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.5657e-05 | 63.4888 | 63.4888 | 0%
Central Coast | DA_De Anza | STELLING 1110 | 8137 | STELLING 11102243 | 2.5e-05 | 50.9433 | 1.654 | 0 | 1.654 | 0 | 1162 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 1 | 2122 |  | 385 | 254 | 2122 | 385 | 254 | 718.43 | 4.9074e-07 | 0 | 2532 | 9.2395e-05 | 2.7998e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.2395e-05 | 232.7722 | 232.7722 | 0%
Bay Area | DI_Diablo | MORAGA 1101 | 9946 | MORAGA 110183424 | 0.001914 | 28.5647 | 0.82405 | 0.70701 | 0.11686 | 0.82405 | 18 | 75 | 25 | 12 | 1 | 0 | 0 | 28 | 0 | 75 |  | 25 | 12 | 0 | 24 | 12 | 32.88 | 6.7006e-05 | 0 | 2534 | 3.9116e-05 | 2.794e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.5469e-06 | 205.3809 | 30.3379 | 85.8%
Central Coast | DA_De Anza | LOS GATOS 1101 | 2627 | LOS GATOS 1101LB40 | 0.000208 | 191.5778 | 9.5047 | 0 | 9.5047 | 0 | 1410 | 0 | 0 | 0 | 0 | 0 | 0 | 281 | 1 | 2573 |  | 466 | 308 | 2573 | 466 | 308 | 869.99 | 1.0857e-06 | 0 | 2535 | 0.00033789 | 2.7925e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00033789 | 49.0282 | 49.0282 | 0%
North Coast | HU_Humboldt | HIGHLANDS 1104 | 6012 | HIGHLANDS 110448262 | 3.1e-05 | 49.7394 | 3.404 | 0.074242 | 3.3297 | 0.13295 | 223 | 92 | 7 | 2 | 6 | 2 | 0 | 92 | 0.96094 | 493 |  | 81 | 52 | 401 | 75 | 50 | 138.84 | 6.2325e-07 | 0 | 2537 | 0.00023095 | 2.7825e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00022591 | 22.5243 | 23.7957 | 2.181%
Bay Area | DI_Diablo | LAKEWOOD 2227 | 2118 | LAKEWOOD 2227W503R | 0.037928 | 9.3965 | 0.84735 | 0 | 0.84735 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1 | 127 |  | 25 | 17 | 127 | 25 | 17 | 45.68 | 0.0040364 | 0.00021 | 2538 | 5.529e-06 | 2.7645e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.529e-06 | 29.5038 | 29.5038 | 0%
Central Coast | LP_Los Padres | MORRO BAY 1102 | 8050 | MORRO BAY 1102circuit_breaker | 0.000195 | 35.3346 | 2.5191 | 0 | 2.5191 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 1 | 76 |  | 16 | 11 | 76 | 16 | 11 | 28.76 | 5.5187e-06 | 0 | 2539 | 5.8029e-05 | 2.7633e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.8029e-05 | 6.3514 | 6.3514 | 0%
Central Coast | CC_Central Coast | LAURELES 1112 | 4001 | LAURELES 11122142 | 0.000483 | 182.5781 | 7.0267 | 0.0028409 | 7.0239 | 1.8229 | 311 | 187 | 12 | 11 | 2 | 1 | 0 | 148 | 0.74057 | 614 |  | 91 | 63 | 427 | 89 | 62 | 160.36 | 2.6454e-06 | 0 | 2540 | 0.00022649 | 2.762e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0002264 | 12.6711 | 12.9506 | 0.04043%
North Valley | NV_North Valley | EAST QUINCY 1101 | 2588 | EAST QUINCY 1101circuit_breaker | 0.052714 | 92.2986 | 2.467 | 0.082386 | 2.3847 | 0.30341 | 950 | 298 | 97 | 80 | 0 | 0 | 0 | 68 | 0.87702 | 1822 |  | 374 | 263 | 1524 | 374 | 263 | 649.54 | 0.00057112 | 0.00044 | 2541 | 0.00012399 | 2.7554e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00011985 | 156.8358 | 151.5983 | 3.339%
Central Coast | DA_De Anza | LOS GATOS 1101 | 8223 | LOS GATOS 110160052 | 2.2e-05 | 31.5713 | 1.3214 | 0 | 1.3214 | 0 | 243 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 1 | 454 |  | 84 | 56 | 454 | 84 | 56 | 155.94 | 6.9683e-07 | 0 | 2542 | 7.6598e-05 | 2.7356e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.6598e-05 | 63.5689 | 63.5689 | 0%
Central Coast | LP_Los Padres | PERRY 1101 | 2600 | PERRY 1101V72 | 6.9e-05 | 115.427 | 9.3261 | 0 | 9.3261 | 0 | 1302 | 0 | 0 | 0 | 0 | 0 | 0 | 546 | 1 | 2377 |  | 431 | 285 | 2377 | 431 | 285 | 804.4 | 5.9778e-07 | 0 | 2544 | 0.00022926 | 2.7293e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00022926 | 46.2142 | 46.2142 | 0%
Bay Area | NB_North Bay | ALTO 1125 | 629 | ALTO 1125935 | 0.076009 | 66.2856 | 3.4275 | 0 | 3.4275 | 0 | 644 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 1 | 1182 |  | 215 | 143 | 1182 | 215 | 143 | 400.93 | 0.0011467 | 0.00051 | 2545 | 0.00010814 | 2.7035e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00010814 | 62.7286 | 62.7286 | 0%
Bay Area | DI_Diablo | MORAGA 1103 | 1961 | MORAGA 1103E510R | 0.001518 | 20.2064 | 1.1498 | 0 | 1.1498 | 0 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1 | 208 |  | 40 | 27 | 208 | 40 | 27 | 73.52 | 7.5125e-05 | 1e-05 | 2546 | 2.4247e-05 | 2.6941e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.4247e-05 | 34.7883 | 34.7883 | 0%
Central Coast | DA_De Anza | SARATOGA 1107 | 7016 | SARATOGA 11076867 | 3.9e-05 | 44.5629 | 1.7261 | 0 | 1.7261 | 0 | 315 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 1 | 584 |  | 107 | 72 | 584 | 107 | 72 | 199.15 | 8.7517e-07 | 0 | 2547 | 2.4211e-05 | 2.6901e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.4211e-05 | 61.9882 | 61.9882 | 0%
Bay Area | NB_North Bay | IGNACIO 1105 | 4743 | 84764 | 0.00432 | 32.099 | 3.2324 | 0 | 3.2324 | 0 | 117 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 1 | 225 |  | 43 | 29 | 225 | 43 | 29 | 79.16 | 0.00013458 | 1e-05 | 2548 | 2.667e-06 | 2.667e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.667e-06 | 13.3029 | 13.3029 | 0%
Bay Area | MI_Mission | CASTRO VALLEY 1106 | 2072 | CASTRO VALLEY 1106MR205 | 1.2e-05 | 14.9693 | 0.23239 | 0 | 0.23239 | 0.15492 | 25 | 5 | 5 | 0 | 0 | 0 | 0 | 18 | 0.33333 | 24 |  | 9 | 3 | 19 | 9 | 3 | 14.04 | 8.0164e-07 | 0 | 2549 | 2.6646e-06 | 2.6646e-06 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.6646e-06 | 38.7286 | 38.7286 | 0%
Central Coast | CC_Central Coast | LAURELES 1111 | 2253 | LAURELES 11112028 | 0.000166 | 189.7251 | 9.0017 | 8.4212 | 0.58049 | 9.0017 | 1470 | 3052 | 832 | 154 | 806 | 145 | 0 | 430 | 0 | 3052 |  | 832 | 154 | 0 | 26 | 9 | 35.62 | 8.7495e-07 | 0 | 2550 | 0.00036929 | 2.6568e-06 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.3814e-05 | 44.7896 | 92.4269 | 93.55%
Bay Area | DI_Diablo | LAKEWOOD 2107 | 2216 | LAKEWOOD 210738404 | 3.8e-05 | 29.7119 | 0.79962 | 0 | 0.79962 | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1 | 216 |  | 41 | 28 | 216 | 41 | 28 | 75.61 | 1.2789e-06 | 0 | 2551 | 5.2865e-05 | 2.6433e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.2865e-05 | 51.2743 | 51.2743 | 0%
North Coast | HU_Humboldt | HARTLEY 1101 | 4592 | HARTLEY 110194178 | 4.1e-05 | 40.0895 | 1.1998 | 0 | 1.1998 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 1 | 257 |  | 48 | 33 | 257 | 48 | 33 | 88.89 | 1.0227e-06 | 0 | 2552 | 7.3787e-05 | 2.6352e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.3787e-05 | 40.0063 | 40.0063 | 0%
Bay Area | EB_East Bay | RIDGE 0401 | 4949 | RIDGE 0401circuit_breaker | 4.2e-05 | 87.0735 | 4.3458 | 0 | 4.3458 | 0 | 677 | 0 | 0 | 0 | 0 | 0 | 0 | 188 | 1 | 1242 |  | 226 | 150 | 1242 | 226 | 150 | 421.4 | 4.8235e-07 | 0 | 2553 | 9.7348e-05 | 2.631e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.7348e-05 | 52.0038 | 52.0038 | 0%
Central Coast | SJ_San Jose | MORGAN HILL 2109 | 4378 | MORGAN HILL 2109XR246 | 4.1e-05 | 45.1997 | 2.0771 | 0 | 2.0771 | 0 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 1 | 357 |  | 66 | 45 | 357 | 66 | 45 | 122.55 | 9.0708e-07 | 0 | 2556 | 7.487e-05 | 2.5817e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.487e-05 | 31.7753 | 31.7753 | 0%
Central Valley | YO_Yosemite | PEORIA 1701 | 792 | PEORIA 17019250 | 0.000215 | 169.9081 | 7.447 | 0.070265 | 7.3767 | 0.18655 | 729 | 10 | 3 | 2 | 3 | 2 | 0 | 125 | 0.97495 | 1313 |  | 240 | 159 | 1303 | 237 | 157 | 441.96 | 1.2654e-06 | 0 | 2557 | 3.09e-05 | 2.575e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.0608e-05 | 32.1282 | 32.2279 | 0.9435%
Bay Area | EB_East Bay | OAKLAND K 1104 | 4524 | OAKLAND K 1104CR208 | 1.7e-05 | 65.1792 | 4.3373 | 0 | 4.3373 | 0 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 178 | 1 | 1131 |  | 206 | 137 | 1131 | 206 | 137 | 384.01 | 2.6082e-07 | 0 | 2558 | 9.2599e-05 | 2.5722e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.2599e-05 | 47.4949 | 47.4949 | 0%
Central Coast | LP_Los Padres | PERRY 1101 | 2952 | PERRY 1101W52 | 0.000124 | 70.2639 | 4.5491 | 0 | 4.5491 | 0 | 548 | 0 | 0 | 0 | 0 | 0 | 0 | 246 | 1 | 1007 |  | 184 | 122 | 1007 | 184 | 122 | 342.71 | 1.7648e-06 | 0 | 2559 | 9.1775e-05 | 2.5493e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.1775e-05 | 40.448 | 40.448 | 0%
Central Coast | LP_Los Padres | SANTA YNEZ 1104 | 1251 | SANTA YNEZ 1104Y30 | 0.020163 | 11.0526 | 1.3598 | 0 | 1.3598 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 1 | 34 |  | 8 | 6 | 34 | 8 | 6 | 14.02 | 0.0018243 | 3e-05 | 2560 | 1.2702e-05 | 2.5403e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.2702e-05 | 5.883 | 5.883 | 0%
Central Coast | CC_Central Coast | VIEJO 2204 | 1173 | VIEJO 2204circuit_breaker | 4e-06 | 20.498 | 1.0996 | 0 | 1.0996 | 0.070265 | 211 | 25 | 0 | 0 | 0 | 0 | 0 | 31 | 0.9361 | 395 |  | 69 | 46 | 370 | 69 | 46 | 127.83 | 1.9514e-07 | 0 | 2561 | 7.5743e-05 | 2.5248e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.5743e-05 | 62.7489 | 62.7489 | 0%
Bay Area | NB_North Bay | ALTO 1122 | 1814 | ALTO 1122circuit_breaker | 2.5e-05 | 28.1204 | 1.4508 | 0 | 1.4508 | 0 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 1 | 256 |  | 48 | 33 | 256 | 48 | 33 | 88.8 | 8.8904e-07 | 0 | 2562 | 6.057e-05 | 2.5237e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.057e-05 | 33.0862 | 33.0862 | 0%
Central Coast | CC_Central Coast | HATTON 1102 | 6591 | HATTON 1102648928 | 0.000114 | 76.8445 | 3.4595 | 0 | 3.4595 | 0 | 409 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 1 | 755 |  | 138 | 92 | 755 | 138 | 92 | 257.01 | 1.4835e-06 | 0 | 2563 | 0.00012861 | 2.5218e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00012861 | 39.8905 | 39.8905 | 0%
Bay Area | EB_East Bay | BERKELEY F 1105 | 5028 | BERKELEY F 1105BR100 | 1e-06 | 4.9848 | 0.64981 | 0 | 0.64981 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1 | 112 |  | 22 | 16 | 112 | 22 | 16 | 40.22 | 2.0061e-07 | 0 | 2564 | 2.7683e-05 | 2.5166e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.7683e-05 | 33.856 | 33.856 | 0%
Bay Area | NB_North Bay | IGNACIO 1104 | 5914 | IGNACIO 11041290 | 0.000118 | 90.5493 | 4.1381 | 0 | 4.1381 | 0 | 262 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 1 | 488 |  | 90 | 60 | 488 | 90 | 60 | 167.22 | 1.3032e-06 | 0 | 2566 | 0.00010987 | 2.497e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00010987 | 21.7493 | 21.7493 | 0%
Central Coast | CC_Central Coast | VIEJO 2203 | 6914 | VIEJO 2203circuit_breaker | 7e-06 | 51.9276 | 2.2462 | 0 | 2.2462 | 0.088258 | 683 | 44 | 4 | 4 | 0 | 0 | 0 | 60 | 0.96071 | 1247 |  | 223 | 149 | 1203 | 223 | 149 | 413.78 | 1.348e-07 | 0 | 2567 | 0.00010652 | 2.4773e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00010652 | 99.2782 | 99.2782 | 0%
Central Coast | DA_De Anza | HICKS 2103 | 2189 | HICKS 2103LB50 | 0.000227 | 212.2585 | 9.6455 | 0 | 9.6455 | 0 | 1292 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 1 | 2359 |  | 427 | 282 | 2359 | 427 | 282 | 797.3 | 1.0695e-06 | 0 | 2568 | 0.0002349 | 2.4726e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0002349 | 44.2696 | 44.2696 | 0%
Central Coast | CC_Central Coast | DEL MONTE 2103 | 6805 | DEL MONTE 21032000 | 4e-05 | 219.6077 | 8.7947 | 2.3089 | 6.4856 | 8.5511 | 2448 | 3764 | 395 | 343 | 110 | 90 | 0 | 232 | 0.027694 | 3887 |  | 417 | 358 | 123 | 307 | 268 | 431.66 | 1.8214e-07 | 0 | 2569 | 0.00029346 | 2.4661e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00021641 | 47.3356 | 47.4149 | 26.25%
Bay Area | NB_North Bay | ALTO 1122 | 6923 | ALTO 112265474 | 0.004466 | 44.0283 | 2.0087 | 0 | 2.0087 | 0 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 1 | 474 |  | 87 | 58 | 474 | 87 | 58 | 161.85 | 0.00010143 | 2e-05 | 2570 | 8.0874e-05 | 2.4507e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.0874e-05 | 43.3113 | 43.3113 | 0%
Central Coast | CC_Central Coast | LAURELES 1111 | 8738 | LAURELES 11116421 | 3.1e-05 | 35.6768 | 1.2693 | 1.2021 | 0.067235 | 1.2693 | 96 | 162 | 28 | 1 | 28 | 1 | 0 | 48 | 0 | 162 |  | 28 | 1 | 0 | 0 | 0 | 0 | 8.6891e-07 | 0 | 2571 | 6.3112e-05 | 2.4274e-06 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.343e-06 | 0 | 22.0591 | 94.7%
Central Coast | CC_Central Coast | LOS OSITOS 2102 | 6965 | LOS OSITOS 21027470 | 0.000186 | 73.9644 | 5.2824 | 0 | 5.2824 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 1 | 49 |  | 11 | 8 | 49 | 11 | 8 | 19.48 | 2.5147e-06 | 0 | 2572 | 1.4564e-05 | 2.4273e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.4564e-05 | 2.0824 | 2.0824 | 0%
Central Coast | CC_Central Coast | DEL MONTE 2103 | 2168 | DEL MONTE 21032654 | 6e-06 | 30.6851 | 0.54413 | 0.1303 | 0.41402 | 0.54413 | 89 | 101 | 9 | 6 | 1 | 0 | 0 | 13 | 0 | 101 |  | 9 | 6 | 0 | 8 | 6 | 10.96 | 1.9553e-07 | 0 | 2573 | 6.2951e-05 | 2.4212e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.7898e-05 | 19.323 | 16.5402 | 23.95%
Central Valley | YO_Yosemite | PEORIA 1701 | 4487 | PEORIA 170184318 | 0.008075 | 226.0399 | 9.8936 | 0.75682 | 9.1369 | 1.7492 | 1484 | 595 | 89 | 51 | 73 | 35 | 0 | 261 | 0.82319 | 2824 |  | 493 | 318 | 2229 | 420 | 283 | 776.01 | 3.5724e-05 | 3e-05 | 2574 | 9.6569e-06 | 2.4142e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.9184e-06 | 45.9673 | 49.8304 | 7.65%
Central Coast | DA_De Anza | SARATOGA 1105 | 2103 | SARATOGA 1105circuit_breaker | 1e-05 | 10.4949 | 0.33409 | 0 | 0.33409 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 56 |  | 12 | 9 | 56 | 12 | 9 | 21.48 | 9.5285e-07 | 0 | 2576 | 9.6344e-06 | 2.4086e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.6344e-06 | 35.9184 | 35.9184 | 0%
Bay Area | EB_East Bay | OAKLAND K 1101 | 1605 | OAKLAND K 1101CR172 | 1.1e-05 | 18.1174 | 1.9189 | 0 | 1.9189 | 0 | 202 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 1 | 379 |  | 70 | 47 | 379 | 70 | 47 | 130.01 | 6.0715e-07 | 0 | 2577 | 1.683e-05 | 2.4043e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.683e-05 | 36.4785 | 36.4785 | 0%
Central Coast | LP_Los Padres | PERRY 1101 | 5885 | PERRY 1101W12 | 2.6e-05 | 24.8475 | 1.5956 | 0 | 1.5956 | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 1 | 216 |  | 41 | 28 | 216 | 41 | 28 | 75.61 | 1.0464e-06 | 0 | 2578 | 9.1287e-05 | 2.4023e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.1287e-05 | 25.695 | 25.695 | 0%
Bay Area | EB_East Bay | OAKLAND K 1101 | 3182 | OAKLAND K 1101circuit_breaker | 0 | 1.7052 | 0.16326 | 0 | 0.16326 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 25 |  | 6 | 5 | 25 | 6 | 5 | 10.47 | 0 | 0 | 2579 | 2.1619e-05 | 2.4021e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.1619e-05 | 36.7517 | 36.7517 | 0%
Central Coast | CC_Central Coast | LAURELES 1112 | 1942 | LAURELES 111268454 | 0.000266 | 232.9693 | 9.5055 | 0 | 9.5055 | 1.0206 | 813 | 136 | 2 | 0 | 0 | 0 | 0 | 245 | 0.89263 | 1465 |  | 243 | 160 | 1329 | 243 | 160 | 452.52 | 1.1418e-06 | 0 | 2580 | 0.00032188 | 2.4021e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00032188 | 25.5642 | 25.5642 | 0%
Bay Area | EB_East Bay | FLORENCE 0401 | 6006 | WOOD 0401circuit_breaker | 3e-06 | 4.7386 | 0.18144 | 0 | 0.18144 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 34 |  | 8 | 6 | 34 | 8 | 6 | 14.02 | 6.331e-07 | 0 | 2582 | 7.1979e-06 | 2.3993e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.1979e-06 | 44.0919 | 44.0919 | 0%
Central Coast | DA_De Anza | SARATOGA 1103 | 4742 | SARATOGA 1103LC16 | 0.000117 | 105.6122 | 4.2847 | 0 | 4.2847 | 0 | 734 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 1 | 1345 |  | 245 | 162 | 1345 | 245 | 162 | 456.7 | 1.1078e-06 | 0 | 2583 | 7.399e-05 | 2.3868e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.399e-05 | 57.1807 | 57.1807 | 0%
North Valley | NV_North Valley | WYANDOTTE 1105 | 4640 | WYANDOTTE 110213914 | 0.069365 | 12.8822 | 0.5178 | 0 | 0.5178 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 1 | 32 |  | 8 | 6 | 32 | 8 | 6 | 13.84 | 0.0053846 | 9e-05 | 2584 | 2.3732e-06 | 2.3732e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.3732e-06 | 15.4499 | 15.4499 | 0%
Central Coast | CC_Central Coast | LAURELES 1112 | 1695 | LAURELES 1112circuit_breaker | 7e-06 | 5.9184 | 0.28523 | 0 | 0.28523 | 0.11496 | 32 | 39 | 2 | 1 | 0 | 0 | 0 | 9 | 0.59695 | 81 |  | 11 | 7 | 42 | 11 | 7 | 18.85 | 1.1828e-06 | 0 | 2585 | 9.49e-06 | 2.3725e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.49e-06 | 38.5657 | 38.5657 | 0%
North Coast | HU_Humboldt | KONOCTI 1108 | 5355 | KONOCTI 11084037 | 0.016942 | 15.0684 | 1.2731 | 0 | 1.2731 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1 | 36 |  | 8 | 6 | 36 | 8 | 6 | 14.2 | 0.0011243 | 2e-05 | 2586 | 2.1233e-05 | 2.3592e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.1233e-05 | 6.2838 | 6.2838 | 0%
Central Valley | YO_Yosemite | CURTIS 1702 | 7396 | CURTIS 1702S2123 | 0.010971 | 49.293 | 2.454 | 0 | 2.454 | 0.034091 | 843 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 0.98611 | 1522 |  | 276 | 183 | 1522 | 276 | 183 | 515.1 | 0.00022257 | 0.00013 | 2587 | 5.4139e-05 | 2.3539e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.4139e-05 | 112.4705 | 112.4705 | 0%
Central Coast | CC_Central Coast | DEL MONTE 2103 | 7069 | DEL MONTE 210342226 | 3e-06 | 7.0623 | 0.75852 | 0.19242 | 0.5661 | 0.75852 | 115 | 230 | 20 | 15 | 1 | 1 | 0 | 21 | 0 | 230 |  | 20 | 15 | 0 | 19 | 14 | 26.03 | 4.2479e-07 | 0 | 2589 | 1.393e-05 | 2.3216e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.0396e-05 | 33.5631 | 26.367 | 25.37%
Central Coast | CC_Central Coast | DOLAN ROAD 1101 | 3919 | DOLAN ROAD 11013012 | 0.000103 | 97.26 | 3.4191 | 0 | 3.4191 | 0 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1 | 394 |  | 73 | 49 | 394 | 73 | 49 | 135.47 | 1.059e-06 | 0 | 2590 | 0.00011588 | 2.3176e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00011588 | 21.3505 | 21.3505 | 0%
Bay Area | PE_Peninsula | HALF MOON BAY 1103 | 4148 | HALF MOON BAY 11038894 | 0.000127 | 316.9214 | 11.3663 | 3.0987 | 8.2676 | 5.315 | 5955 | 1750 | 454 | 75 | 267 | 50 | 0 | 458 | 0.53239 | 7514 |  | 1495 | 761 | 5764 | 1228 | 711 | 2201.12 | 4.0073e-07 | 0 | 2591 | 0.00041461 | 2.3163e-06 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00030158 | 148.5314 | 131.5293 | 27.26%
Bay Area | EB_East Bay | OAKLAND X 1106 | 3718 | OAKLAND X 1106CR006 | 8.1e-05 | 172.8788 | 2.8786 | 0 | 2.8786 | 0 | 567 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 1 | 1042 |  | 190 | 126 | 1042 | 190 | 126 | 354.08 | 4.6854e-07 | 0 | 2592 | 0.00010551 | 2.2938e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00010551 | 66.0043 | 66.0043 | 0%
North Coast | HU_Humboldt | HIGHLANDS 1102 | 2738 | HIGHLANDS 1102circuit_breaker | 3.4828 | 138.9789 | 7.7403 | 5.9511 | 1.789 | 6.9295 | 207 | 819 | 99 | 22 | 82 | 10 | 0 | 300 | 0.10475 | 860 |  | 107 | 27 | 41 | 25 | 17 | 37.94 | 0.02506 | 0.0013 | 2593 | 0.0001303 | 2.286e-06 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.0116e-05 | 13.9742 | 13.8237 | 76.88%
Central Coast | CC_Central Coast | CARMEL 0402 | 1269 | CARMEL 0405circuit_breaker | 5e-06 | 14.3541 | 0.55341 | 0 | 0.55341 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 230 |  | 43 | 30 | 230 | 43 | 30 | 79.61 | 3.4833e-07 | 0 | 2594 | 2.2637e-06 | 2.2637e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.2637e-06 | 77.7002 | 77.7002 | 0%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1101 | 1597 | SAN LUIS OBISPO 1105circuit_breaker | 0.16819 | 18.4979 | 0.93598 | 0 | 0.93598 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1 | 63 |  | 13 | 10 | 63 | 13 | 10 | 23.48 | 0.0090924 | 0.00025 | 2595 | 2.2516e-06 | 2.2516e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.2516e-06 | 13.8891 | 13.8891 | 0%
Bay Area | EB_East Bay | EDES 1112 | 4978 | EDES 1112CR312 | 5e-05 | 93.277 | 4.0856 | 0 | 4.0856 | 0 | 648 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 1 | 1189 |  | 216 | 143 | 1189 | 216 | 143 | 402.93 | 5.3604e-07 | 0 | 2597 | 9.6253e-05 | 2.2384e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.6253e-05 | 52.8685 | 52.8685 | 0%
Central Coast | CC_Central Coast | VIEJO 2202 | 4057 | VIEJO 22022606 | 0 | 3.6877 | 0.35871 | 0 | 0.35871 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 1 | 65 |  | 14 | 10 | 65 | 14 | 10 | 25.03 | 0 | 0 | 2598 | 2.678e-05 | 2.2317e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.678e-05 | 39.0285 | 39.0285 | 0%
North Valley | NV_North Valley | BURNEY 1101 | 4565 | BURNEY 110245984 | 5e-05 | 129.8441 | 4.875 | 0 | 4.875 | 0 | 1348 | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 1 | 2460 |  | 446 | 294 | 2460 | 446 | 294 | 832.42 | 3.8508e-07 | 0 | 2599 | 0.00015943 | 2.2143e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00015943 | 91.4872 | 91.4872 | 0%
Bay Area | PE_Peninsula | EMERALD LAKE 0402 | 6508 | EMERALD LAKE 04028858 | 1e-06 | 8.8757 | 0.40739 | 0 | 0.40739 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 112 |  | 22 | 16 | 112 | 22 | 16 | 40.22 | 1.1267e-07 | 0 | 2600 | 5.5314e-05 | 2.2126e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.5314e-05 | 54.0028 | 54.0028 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1101 | 6087 | SAN RAFAEL 1101310 | 3e-06 | 3.2077 | 0.14659 | 0 | 0.14659 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 25 |  | 6 | 5 | 25 | 6 | 5 | 10.47 | 9.3524e-07 | 0 | 2601 | 1.5432e-05 | 2.2046e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.5432e-05 | 40.9302 | 40.9302 | 0%
Bay Area | PE_Peninsula | SAN CARLOS 1104 | 6509 | SAN CARLOS 110475210 | 9e-06 | 9.4959 | 0.10777 | 0 | 0.10777 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 18 |  | 5 | 4 | 18 | 5 | 4 | 8.47 | 9.4778e-07 | 0 | 2602 | 6.5906e-06 | 2.1969e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.5906e-06 | 46.3972 | 46.3972 | 0%
Bay Area | PE_Peninsula | CAROLANDS 0404 | 5893 | CAROLANDS 04049024 | 2.4e-05 | 61.6791 | 3.1116 | 0 | 3.1116 | 0 | 487 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 1 | 897 |  | 164 | 109 | 897 | 164 | 109 | 305.41 | 3.8911e-07 | 0 | 2603 | 0.00011829 | 2.1906e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00011829 | 52.7068 | 52.7068 | 0%
Bay Area | EB_East Bay | VALLEY VIEW 1105 | 6362 | VALLEY VIEW 1106P180 | 1.1e-05 | 22.785 | 0.12519 | 0 | 0.12519 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 61 |  | 13 | 10 | 61 | 13 | 10 | 23.3 | 4.8277e-07 | 0 | 2608 | 2.1733e-06 | 2.1733e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.1733e-06 | 103.8427 | 103.8427 | 0%
Central Coast | CC_Central Coast | VIEJO 2201 | 6954 | VIEJO 22032634 | 7e-06 | 4.5799 | 0.059091 | 0 | 0.059091 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 76 |  | 16 | 11 | 76 | 16 | 11 | 28.76 | 1.5284e-06 | 0 | 2609 | 2.1662e-06 | 2.1662e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.1662e-06 | 270.7692 | 270.7692 | 0%
Central Coast | CC_Central Coast | VIEJO 2204 | 5852 | VIEJO 22049540 | 1e-05 | 70.0121 | 3.8216 | 0 | 3.8216 | 0.44489 | 914 | 333 | 213 | 195 | 0 | 0 | 0 | 112 | 0.88359 | 1810 |  | 481 | 372 | 1477 | 481 | 372 | 791.9 | 1.4283e-07 | 0 | 2611 | 5.3526e-05 | 2.141e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.3526e-05 | 125.8638 | 125.8638 | 0%
Bay Area | PE_Peninsula | WOODSIDE 1104 | 2893 | WOODSIDE 11049116 | 2.4e-05 | 12.8187 | 0.68693 | 0 | 0.68693 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1 | 92 |  | 19 | 13 | 92 | 19 | 13 | 34.31 | 1.8723e-06 | 0 | 2613 | 1.068e-05 | 2.136e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.068e-05 | 27.6592 | 27.6592 | 0%
Central Coast | DA_De Anza | HICKS 1116 | 3391 | LOS GATOS 110160136 | 4.2e-05 | 69.0602 | 4.6142 | 0 | 4.6142 | 0 | 578 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 1 | 1062 |  | 193 | 128 | 1062 | 193 | 128 | 359.99 | 6.0816e-07 | 0 | 2614 | 1.4923e-05 | 2.1318e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.4923e-05 | 41.8274 | 41.8274 | 0%
Bay Area | DI_Diablo | MORAGA 1105 | 7709 | MORAGA 110518396 | 3.4e-05 | 16.5113 | 0.36098 | 0.28958 | 0.071402 | 0.36098 | 16 | 54 | 3 | 0 | 1 | 0 | 0 | 11 | 0 | 54 |  | 3 | 0 | 0 | 2 | 0 | 2.74 | 2.0592e-06 | 0 | 2616 | 2.1302e-06 | 2.1302e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.2135e-07 | 28.0106 | 8.3106 | 80.22%
Central Coast | CC_Central Coast | DEL MONTE 2103 | 6806 | DEL MONTE 210332886 | 8e-06 | 46.1306 | 1.5303 | 0.23087 | 1.2994 | 1.5303 | 238 | 540 | 41 | 32 | 3 | 3 | 0 | 42 | 0 | 540 |  | 41 | 32 | 0 | 38 | 29 | 52.06 | 1.7342e-07 | 0 | 2617 | 5.4976e-05 | 2.1145e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.6682e-05 | 29.2436 | 26.7921 | 15.09%
Bay Area | DI_Diablo | MORAGA 1101 | 6644 | MORAGA 11017616 | 0.000302 | 59.0347 | 3.804 | 0.70701 | 3.0968 | 3.286 | 639 | 1012 | 193 | 131 | 13 | 4 | 0 | 193 | 0.13617 | 1172 |  | 222 | 150 | 160 | 209 | 146 | 300.73 | 5.1156e-06 | 0 | 2618 | 4.4308e-05 | 2.1099e-06 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.6071e-05 | 67.4895 | 58.36 | 18.59%
Bay Area | EB_East Bay | OAKLAND X 1106 | 283 | OAKLAND X 1106circuit_breaker | 1.9e-05 | 47.6657 | 3.2765 | 0.22386 | 3.0527 | 0.25095 | 324 | 146 | 54 | 28 | 46 | 27 | 0 | 142 | 0.92341 | 701 |  | 156 | 96 | 555 | 110 | 69 | 200.65 | 3.9861e-07 | 0 | 2619 | 8.3841e-05 | 2.096e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.8113e-05 | 36.0342 | 47.6116 | 6.832%
Central Coast | CC_Central Coast | VIEJO 2201 | 995 | VIEJO 22019490 | 5e-06 | 31.99 | 1.6513 | 0 | 1.6513 | 0 | 311 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1 | 577 |  | 106 | 71 | 577 | 106 | 71 | 197.15 | 1.563e-07 | 0 | 2620 | 4.1862e-05 | 2.0931e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.1862e-05 | 64.1908 | 64.1908 | 0%
North Valley | NV_North Valley | BURNEY 1101 | 5052 | BURNEY 1102circuit_breaker | 1.8e-05 | 26.6177 | 1.7045 | 0 | 1.7045 | 0 | 396 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 1 | 731 |  | 134 | 89 | 731 | 134 | 89 | 249.37 | 6.7624e-07 | 0 | 2621 | 3.1325e-05 | 2.0883e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.1325e-05 | 78.6133 | 78.6133 | 0%
Bay Area | EB_East Bay | RIDGE 0402 | 289 | RIDGE 0402circuit_breaker | 1.2e-05 | 45.3889 | 2.3534 | 0 | 2.3534 | 0 | 335 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 1 | 621 |  | 114 | 76 | 621 | 114 | 76 | 212.07 | 2.6438e-07 | 0 | 2622 | 4.3853e-05 | 2.0882e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.3853e-05 | 48.4404 | 48.4404 | 0%
Central Coast | CC_Central Coast | VIEJO 2201 | 1411 | VIEJO 22019114 | 4.5e-05 | 205.0267 | 9.7188 | 0 | 9.7188 | 0 | 3768 | 0 | 0 | 0 | 0 | 0 | 0 | 278 | 1 | 6855 |  | 1238 | 817 | 6855 | 1238 | 817 | 2313.01 | 2.1948e-07 | 0 | 2627 | 0.00016296 | 2.0371e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00016296 | 127.3826 | 127.3826 | 0%
Central Coast | LP_Los Padres | PERRY 1101 | 6135 | PERRY 1101W10 | 0.002344 | 41.4056 | 1.8608 | 0 | 1.8608 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 1 | 190 |  | 36 | 25 | 190 | 36 | 25 | 66.42 | 5.6611e-05 | 0 | 2628 | 3.4622e-05 | 2.0366e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.4622e-05 | 19.3466 | 19.3466 | 0%
Bay Area | PE_Peninsula | SAN CARLOS 1104 | 6936 | SAN CARLOS 11049052 | 4.9e-05 | 110.3869 | 4.3411 | 0 | 4.3411 | 0 | 391 | 0 | 0 | 0 | 0 | 0 | 0 | 137 | 1 | 722 |  | 132 | 88 | 722 | 132 | 88 | 245.82 | 4.4389e-07 | 0 | 2629 | 0.00014052 | 2.0366e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00014052 | 30.4071 | 30.4071 | 0%
Central Coast | DA_De Anza | STELLING 1109 | 931 | STELLING 110913228 | 0.000181 | 24.9802 | 1.0057 | 0 | 1.0057 | 0 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 1 | 247 |  | 46 | 32 | 247 | 46 | 32 | 85.25 | 7.2457e-06 | 0 | 2630 | 2.0361e-06 | 2.0361e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.0361e-06 | 45.7401 | 45.7401 | 0%
Bay Area | EB_East Bay | OAKLAND K 1101 | 6763 | OAKLAND K 1101CR170 | 3.8e-05 | 62.4245 | 1.3922 | 0 | 1.3922 | 0 | 221 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1 | 414 |  | 77 | 51 | 414 | 77 | 51 | 142.75 | 6.0874e-07 | 0 | 2634 | 3.0072e-05 | 2.0048e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.0072e-05 | 55.3068 | 55.3068 | 0%
Central Coast | DA_De Anza | HICKS 1116 | 6338 | HICKS 111660050 | 0.000106 | 208.7323 | 7.9973 | 0 | 7.9973 | 0 | 1398 | 0 | 0 | 0 | 0 | 0 | 0 | 188 | 1 | 2551 |  | 462 | 305 | 2551 | 462 | 305 | 862.53 | 5.0783e-07 | 0 | 2635 | 0.00025721 | 1.9939e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00025721 | 57.7691 | 57.7691 | 0%
Bay Area | EB_East Bay | PALO SECO 0401 | 1235 | PALO SECO 0401circuit_breaker | 1.7e-05 | 105.4589 | 6.2239 | 0.50985 | 5.714 | 1.0034 | 912 | 914 | 329 | 267 | 186 | 133 | 0 | 304 | 0.83878 | 2313 |  | 583 | 435 | 1399 | 397 | 302 | 669.8 | 1.612e-07 | 0 | 2637 | 9.2923e-05 | 1.9771e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.5311e-05 | 69.4783 | 93.6717 | 8.192%
Bay Area | EB_East Bay | OAKLAND K 1103 | 2423 | OAKLAND K 1103CR188 | 1e-05 | 66.9361 | 3.3208 | 0.17784 | 3.1432 | 0.49924 | 866 | 286 | 50 | 28 | 29 | 16 | 0 | 137 | 0.84966 | 1633 |  | 295 | 190 | 1347 | 266 | 174 | 485.65 | 1.494e-07 | 0 | 2638 | 0.00010113 | 1.9449e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.5723e-05 | 84.6276 | 88.8331 | 5.355%
Central Coast | LP_Los Padres | PURISIMA 1101 | 3744 | PURISIMA 1101circuit_breaker | 0.014089 | 48.6991 | 2.0862 | 0 | 2.0862 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 1 | 34 |  | 8 | 6 | 34 | 8 | 6 | 14.02 | 0.00028931 | 0 | 2639 | 6.3885e-05 | 1.9359e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.3885e-05 | 3.8348 | 3.8348 | 0%
Bay Area | EB_East Bay | OAKLAND K 1104 | 5480 | OAKLAND K 1104circuit_breaker | 8e-06 | 52.4527 | 2.0867 | 0 | 2.0867 | 0 | 316 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 1 | 586 |  | 108 | 72 | 586 | 108 | 72 | 200.7 | 1.5252e-07 | 0 | 2640 | 1.3549e-05 | 1.9356e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.3549e-05 | 51.7553 | 51.7553 | 0%
Bay Area | EB_East Bay | EL CERRITO G 1105 | 2068 | SPRUCE 0402BR304 | 2.7e-05 | 53.4794 | 6.3152 | 0 | 6.3152 | 0 | 314 | 0 | 0 | 0 | 0 | 0 | 0 | 369 | 1 | 582 |  | 107 | 71 | 582 | 107 | 71 | 198.97 | 5.0487e-07 | 0 | 2641 | 3.6767e-05 | 1.9351e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.6767e-05 | 16.9434 | 16.9434 | 0%
Central Coast | CC_Central Coast | HATTON 1101 | 1844 | HATTON 1102circuit_breaker | 1.6e-05 | 77.6207 | 3.1184 | 0.039205 | 3.079 | 0.34659 | 671 | 116 | 25 | 8 | 25 | 8 | 0 | 86 | 0.88886 | 1210 |  | 224 | 140 | 1094 | 199 | 132 | 371.09 | 2.0613e-07 | 0 | 2642 | 5.9602e-05 | 1.9227e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.8849e-05 | 64.6319 | 71.8324 | 1.257%
Central Coast | CC_Central Coast | VIEJO 2202 | 6323 | VIEJO 2202circuit_breaker | 6e-06 | 26.3912 | 0.62557 | 0 | 0.62557 | 0 | 197 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1 | 370 |  | 69 | 46 | 370 | 69 | 46 | 127.83 | 2.2735e-07 | 0 | 2643 | 5.37e-05 | 1.9179e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.37e-05 | 110.2997 | 110.2997 | 0%
Central Coast | SJ_San Jose | MC KEE 1103 | 542 | MC KEE 1103XR028 | 0.026027 | 14.3698 | 0.70038 | 0 | 0.70038 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 176 |  | 34 | 23 | 176 | 34 | 23 | 62.42 | 0.0018112 | 0.00013 | 2644 | 1.9085e-06 | 1.9085e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.9085e-06 | 48.5452 | 48.5452 | 0%
Bay Area | EB_East Bay | OAKLAND X 1105 | 63 | OAKLAND X 1105circuit_breaker | 1.6e-05 | 72.829 | 6.1672 | 0 | 6.1672 | 0 | 431 | 0 | 0 | 0 | 0 | 0 | 0 | 285 | 1 | 795 |  | 145 | 97 | 795 | 145 | 97 | 270.2 | 2.1969e-07 | 0 | 2646 | 5.8907e-05 | 1.9002e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.8907e-05 | 23.5113 | 23.5113 | 0%
North Valley | NV_North Valley | GANSNER 1101 | 1020 | GANSNER 110152664 | 2.5e-05 | 20.5255 | 0.67178 | 0 | 0.67178 | 0 | 465 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 857 |  | 156 | 104 | 857 | 156 | 104 | 290.85 | 1.218e-06 | 0 | 2648 | 3.7855e-05 | 1.8927e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.7855e-05 | 232.2188 | 232.2188 | 0%
Bay Area | NB_North Bay | STAFFORD 1102 | 3120 | STAFFORD 110242542 | 1.5e-05 | 28.5871 | 1.0695 | 0 | 1.0695 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 1 | 143 |  | 28 | 19 | 143 | 28 | 19 | 51.23 | 5.2471e-07 | 0 | 2649 | 1.3245e-05 | 1.8922e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.3245e-05 | 26.1803 | 26.1803 | 0%
North Coast | HU_Humboldt | HOPLAND 1101 | 7645 | HOPLAND 1101circuit_breaker | 0.00208 | 18.4755 | 2.7955 | 0 | 2.7955 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 1 | 116 |  | 23 | 16 | 116 | 23 | 16 | 41.95 | 0.00011258 | 1e-05 | 2650 | 7.5621e-06 | 1.8905e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.5621e-06 | 8.2276 | 8.2276 | 0%
Bay Area | PE_Peninsula | BERESFORD 0403 | 5759 | BERESFORD 04039154 | 4e-05 | 115.7928 | 5.3023 | 0 | 5.3023 | 0 | 993 | 0 | 0 | 0 | 0 | 0 | 0 | 184 | 1 | 1816 |  | 329 | 218 | 1816 | 329 | 218 | 614.17 | 3.4544e-07 | 0 | 2651 | 0.00011503 | 1.8858e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00011503 | 62.0489 | 62.0489 | 0%
Bay Area | EB_East Bay | SAN LEANDRO U 1109 | 5120 | SAN LEANDRO U 1109CR182 | 6.4e-05 | 95.5432 | 4.1492 | 0 | 4.1492 | 0 | 731 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 1 | 1340 |  | 244 | 161 | 1340 | 244 | 161 | 454.88 | 6.6985e-07 | 0 | 2652 | 9.7458e-05 | 1.8742e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.7458e-05 | 58.8059 | 58.8059 | 0%
Central Coast | CC_Central Coast | LAURELES 1111 | 9245 | LAURELES 111184523 | 1.6e-05 | 20.3914 | 0.80379 | 0.7428 | 0.060985 | 0.80379 | 27 | 38 | 10 | 2 | 8 | 0 | 0 | 15 | 0 | 38 |  | 10 | 2 | 0 | 2 | 2 | 2.74 | 7.8465e-07 | 0 | 2653 | 3.1778e-05 | 1.8693e-06 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.411e-06 | 32.795 | 12.4411 | 92.41%
Bay Area | EB_East Bay | OAKLAND K 1103 | 5517 | FLORENCE 0401circuit_breaker | 9e-06 | 56.8306 | 4.1623 | 0 | 4.1623 | 0 | 672 | 0 | 0 | 0 | 0 | 0 | 0 | 169 | 1 | 1233 |  | 224 | 149 | 1233 | 224 | 149 | 417.85 | 1.5837e-07 | 0 | 2654 | 1.3073e-05 | 1.8675e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.3073e-05 | 53.8163 | 53.8163 | 0%
Central Coast | DA_De Anza | HICKS 1116 | 249 | HICKS 1116circuit_breaker | 1.5e-05 | 25.9363 | 1.3199 | 0 | 1.3199 | 0 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1 | 201 |  | 38 | 26 | 201 | 38 | 26 | 70.15 | 5.7834e-07 | 0 | 2656 | 6.4663e-05 | 1.8475e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.4663e-05 | 28.7904 | 28.7904 | 0%
Bay Area | DI_Diablo | ROSSMOOR 1101 | 613 | ROSSMOOR 1101L503R | 0.000108 | 122.3984 | 5.3926 | 0 | 5.3926 | 0 | 938 | 0 | 0 | 0 | 0 | 0 | 0 | 174 | 1 | 1716 |  | 311 | 206 | 1716 | 311 | 206 | 580.51 | 8.8236e-07 | 0 | 2657 | 0.00012913 | 1.8447e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00012913 | 57.6715 | 57.6715 | 0%
Central Coast | LP_Los Padres | MORRO BAY 1101 | 4984 | MORRO BAY 1101W20 | 0.000429 | 47.3403 | 3.093 | 0 | 3.093 | 0 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 1 | 902 |  | 165 | 109 | 902 | 165 | 109 | 307.23 | 9.062e-06 | 0 | 2658 | 1.0985e-05 | 1.8308e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.0985e-05 | 53.3464 | 53.3464 | 0%
Bay Area | NB_North Bay | IGNACIO 1101 | 5085 | IGNACIO 1103circuit_breaker | 0.009971 | 19.3117 | 0.76231 | 0 | 0.76231 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 1 | 79 |  | 16 | 12 | 79 | 16 | 12 | 29.03 | 0.00051632 | 2e-05 | 2659 | 1.2791e-05 | 1.8273e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.2791e-05 | 20.9888 | 20.9888 | 0%
Central Coast | CC_Central Coast | DEL MONTE 2104 | 695 | DEL MONTE 21042760 | 1.7e-05 | 31.9791 | 1.6686 | 0.82386 | 0.8447 | 1.364 | 63 | 129 | 4 | 4 | 0 | 0 | 0 | 27 | 0.18252 | 152 |  | 9 | 7 | 23 | 9 | 7 | 14.4 | 5.316e-07 | 0 | 2660 | 4.7457e-05 | 1.8253e-06 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.4025e-05 | 10.6547 | 5.3939 | 49.38%
Central Coast | CC_Central Coast | VIEJO 2201 | 6876 | VIEJO 2201circuit_breaker | 1.9e-05 | 70.3241 | 2.9508 | 0 | 2.9508 | 0 | 1092 | 5 | 1 | 0 | 1 | 0 | 0 | 91 | 1 | 2000 |  | 363 | 239 | 1995 | 362 | 239 | 675.49 | 2.7018e-07 | 0 | 2661 | 3.4524e-05 | 1.817e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.4524e-05 | 122.6804 | 123.0193 | 0%
Central Coast | LP_Los Padres | PALMER 1101 | 3662 | PALMER 1101M82 | 5.3756 | 287.092 | 10.8422 | 0 | 10.8422 | 0 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 184 | 1 | 256 |  | 48 | 33 | 256 | 48 | 33 | 88.8 | 0.018724 | 0.00187 | 2662 | 5.4252e-06 | 1.8084e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.4252e-06 | 4.4271 | 4.4271 | 0%
Bay Area | MI_Mission | CASTRO VALLEY 1101 | 2509 | CASTRO VALLEY 1101MR204 | 2e-05 | 31.1245 | 1.5784 | 0 | 1.5784 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 1 | 103 |  | 21 | 14 | 103 | 21 | 14 | 38.04 | 6.4258e-07 | 0 | 2664 | 8.9111e-06 | 1.7822e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.9111e-06 | 13.3045 | 13.3045 | 0%
Bay Area | PE_Peninsula | WOODSIDE 1104 | 3426 | WOODSIDE 11049030 | 4e-06 | 55.1632 | 3.5386 | 0 | 3.5386 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 1 | 441 |  | 81 | 55 | 441 | 81 | 55 | 150.66 | 7.2512e-08 | 0 | 2665 | 4.9768e-05 | 1.7774e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.9768e-05 | 22.8902 | 22.8902 | 0%
North Valley | NV_North Valley | VOLTA 1101 | 2238 | VOLTA 110185234 | 0.001643 | 152.5097 | 7.5659 | 0 | 7.5659 | 0 | 3975 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 1 | 7231 |  | 1306 | 861 | 7231 | 1306 | 861 | 2440.01 | 1.0773e-05 | 3e-05 | 2666 | 0.0002139 | 1.7533e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0002139 | 172.6164 | 172.6164 | 0%
Bay Area | PE_Peninsula | SAN CARLOS 1103 | 1112 | SAN CARLOS 11039148 | 8e-06 | 67.113 | 4.4102 | 0 | 4.4102 | 0 | 294 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 1 | 546 |  | 100 | 67 | 546 | 100 | 67 | 186.14 | 1.192e-07 | 0 | 2667 | 9.4639e-05 | 1.7526e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.4639e-05 | 22.6746 | 22.6746 | 0%
Bay Area | PE_Peninsula | BELMONT 1103 | 386 | BELMONT 11038958 | 1.7e-05 | 64.7897 | 4.1534 | 0 | 4.1534 | 0 | 423 | 0 | 0 | 0 | 0 | 0 | 0 | 149 | 1 | 780 |  | 143 | 95 | 780 | 143 | 95 | 266.11 | 2.6239e-07 | 0 | 2668 | 6.9991e-05 | 1.7498e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.9991e-05 | 34.4295 | 34.4295 | 0%
Bay Area | EB_East Bay | BERKELEY F 0402 | 1757 | BERKELEY F 0402circuit_breaker | 1e-06 | 4.6835 | 0.65871 | 0 | 0.65871 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 1 | 85 |  | 17 | 12 | 85 | 17 | 12 | 30.94 | 2.1351e-07 | 0 | 2669 | 6.9961e-06 | 1.749e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.9961e-06 | 25.8079 | 25.8079 | 0%
Central Coast | SJ_San Jose | MORGAN HILL 2105 | 8948 | MORGAN HILL 2105XR602 | 0.004766 | 12.336 | 0.5 | 0 | 0.5 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 50 |  | 11 | 8 | 50 | 11 | 8 | 19.57 | 0.00038635 | 1e-05 | 2671 | 6.9545e-06 | 1.7386e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.9545e-06 | 22 | 22 | 0%
Bay Area | EB_East Bay | OAKLAND X 1106 | 6127 | OAKLAND X 1106CR008 | 7.5e-05 | 169.7028 | 4.5191 | 0.10341 | 4.4157 | 0.22803 | 638 | 140 | 67 | 35 | 56 | 26 | 0 | 172 | 0.94954 | 1252 |  | 269 | 169 | 1112 | 213 | 143 | 391.89 | 4.4195e-07 | 0 | 2672 | 0.00011646 | 1.7382e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.0001138 | 48.2368 | 59.5247 | 2.288%
Bay Area | NB_North Bay | ALTO 1125 | 3736 | ALTO 1120500 | 0 | 0.35528 | 0.02803 | 0 | 0.02803 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 16 |  | 5 | 4 | 16 | 5 | 4 | 8.29 | 0 | 0 | 2673 | 5.1903e-06 | 1.7301e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.1903e-06 | 178.3784 | 178.3784 | 0%
Central Coast | CC_Central Coast | VIEJO 2202 | 4406 | VIEJO 220285904 | 9e-06 | 35.3121 | 1.4379 | 0 | 1.4379 | 0 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1 | 615 |  | 113 | 75 | 615 | 113 | 75 | 210.16 | 2.5487e-07 | 0 | 2674 | 2.2484e-05 | 1.7296e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.2484e-05 | 78.588 | 78.588 | 0%
North Coast | SO_Sonoma | PETALUMA C 1109 | 197 | PETALUMA C 1109270 | 0.037424 | 49.8776 | 1.5773 | 0 | 1.5773 | 0 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 1 | 321 |  | 60 | 40 | 321 | 60 | 40 | 111.09 | 0.00075032 | 9e-05 | 2676 | 1.7129e-06 | 1.7129e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.7129e-06 | 38.0403 | 38.0403 | 0%
Central Coast | CC_Central Coast | RESERVATION ROAD 1102 | 6784 | RESERVATION ROAD 11023032 | 3.6e-05 | 84.9633 | 4.215 | 0 | 4.215 | 0 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 1 | 170 |  | 33 | 22 | 170 | 33 | 22 | 60.51 | 4.2371e-07 | 0 | 2677 | 4.9503e-05 | 1.707e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.9503e-05 | 7.8293 | 7.8293 | 0%
North Coast | HU_Humboldt | HARTLEY 1102 | 451 | HARTLEY 1102824 | 1.2e-05 | 5.2794 | 0.15606 | 0 | 0.15606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 2.273e-06 | 0 | 2679 | 1.7033e-06 | 1.7033e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.7033e-06 | 25.6311 | 25.6311 | 0%
Bay Area | EB_East Bay | VALLEY VIEW 1106 | 4110 | VALLEY VIEW 1106P176 | 1.9e-05 | 29.7744 | 1.0091 | 0.82424 | 0.18504 | 1.0091 | 98 | 213 | 14 | 6 | 3 | 2 | 0 | 50 | 0 | 213 |  | 14 | 6 | 0 | 11 | 4 | 15.07 | 6.3813e-07 | 0 | 2680 | 2.722e-05 | 1.7013e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.9914e-06 | 59.4473 | 13.8739 | 81.68%
Bay Area | EB_East Bay | EDES 1112 | 4813 | EDES 1112CR282 | 4.3e-05 | 118.7418 | 5.5652 | 0 | 5.5652 | 0 | 407 | 0 | 0 | 0 | 0 | 0 | 0 | 182 | 1 | 751 |  | 137 | 91 | 751 | 137 | 91 | 255.28 | 3.6213e-07 | 0 | 2683 | 8.2382e-05 | 1.6813e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.2382e-05 | 24.6175 | 24.6175 | 0%
Central Coast | CC_Central Coast | VIEJO 2201 | 1079 | VIEJO 22012064 | 7e-06 | 48.8529 | 1.6394 | 0.080114 | 1.5593 | 0.64489 | 718 | 631 | 240 | 196 | 237 | 193 | 0 | 46 | 0.60663 | 1429 |  | 385 | 292 | 798 | 148 | 99 | 274.58 | 1.4329e-07 | 0 | 2684 | 5.0151e-06 | 1.6717e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.77e-06 | 94.9156 | 234.8429 | 4.887%
North Coast | SO_Sonoma | CORONA 1103 | 160 | CORONA 11034446 | 0.002056 | 8.6487 | 0.26212 | 0 | 0.26193 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 49 |  | 11 | 8 | 49 | 11 | 8 | 19.48 | 0.00023772 | 1e-05 | 2685 | 8.3481e-06 | 1.6696e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.3421e-06 | 41.9957 | 41.9653 | 0%
Bay Area | PE_Peninsula | SAN CARLOS 1104 | 2447 | SAN CARLOS 11048846 | 1.8e-05 | 62.9097 | 3.7581 | 0 | 3.7581 | 0 | 226 | 0 | 0 | 0 | 0 | 0 | 0 | 137 | 1 | 423 |  | 78 | 52 | 423 | 78 | 52 | 144.93 | 2.8612e-07 | 0 | 2687 | 4.5816e-05 | 1.6363e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.5816e-05 | 20.7549 | 20.7549 | 0%
Bay Area | EB_East Bay | EL CERRITO G 1112 | 2724 | EL CERRITO G 1112BR180 | 1e-05 | 13.0349 | 0.6928 | 0 | 0.6928 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 1 | 36 |  | 8 | 6 | 36 | 8 | 6 | 14.2 | 7.6717e-07 | 0 | 2688 | 6.5228e-06 | 1.6307e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.5228e-06 | 11.5473 | 11.5473 | 0%
Bay Area | PE_Peninsula | CAROLANDS 0404 | 226 | CAROLANDS 04049026 | 1.3e-05 | 26.1356 | 1.5163 | 0 | 1.5163 | 0 | 265 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1 | 494 |  | 91 | 61 | 494 | 91 | 61 | 169.13 | 4.9741e-07 | 0 | 2689 | 1.9518e-05 | 1.6265e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.9518e-05 | 60.015 | 60.015 | 0%
Bay Area | PE_Peninsula | RALSTON 1102 | 1941 | RALSTON 11022028 | 0.001086 | 65.8801 | 2.5947 | 0 | 2.5947 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 1 | 109 |  | 22 | 15 | 109 | 22 | 15 | 39.95 | 1.6484e-05 | 0 | 2692 | 1.6072e-06 | 1.6072e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.6072e-06 | 8.4788 | 8.4788 | 0%
Central Coast | CC_Central Coast | DEL MONTE 2104 | 4930 | DEL MONTE 21049096 | 4.1e-05 | 74.866 | 3.1191 | 0 | 3.1191 | 0 | 133 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 1 | 254 |  | 48 | 32 | 254 | 48 | 32 | 88.62 | 5.4765e-07 | 0 | 2693 | 5.7473e-05 | 1.5965e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.7473e-05 | 15.3889 | 15.3889 | 0%
Bay Area | PE_Peninsula | EMERALD LAKE 0401 | 4178 | EMERALD LAKE 04028872 | 2.6e-05 | 65.9363 | 4.1744 | 0 | 4.1744 | 0 | 226 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 1 | 423 |  | 78 | 52 | 423 | 78 | 52 | 144.93 | 3.9432e-07 | 0 | 2695 | 7.1683e-05 | 1.593e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.1683e-05 | 18.6852 | 18.6852 | 0%
Central Coast | CC_Central Coast | DEL MONTE 2104 | 2515 | DEL MONTE 21042032 | 0 | 0.92921 | 0.1036 | 0 | 0.1036 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 20 |  | 5 | 5 | 20 | 5 | 5 | 8.65 | 0 | 0 | 2696 | 6.2748e-06 | 1.5687e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.2748e-06 | 48.2633 | 48.2633 | 0%
North Valley | NV_North Valley | EAST QUINCY 1101 | 5708 | EAST QUINCY 11012452 | 1e-05 | 25.3658 | 1.1002 | 0 | 1.1002 | 0.28655 | 692 | 365 | 93 | 73 | 0 | 0 | 0 | 29 | 0.73954 | 1303 |  | 264 | 186 | 938 | 264 | 186 | 446.1 | 3.9423e-07 | 0 | 2697 | 4.8583e-05 | 1.5672e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.8583e-05 | 239.9587 | 239.9587 | 0%
Central Coast | CC_Central Coast | VIEJO 2202 | 5032 | VIEJO 22029120 | 8e-06 | 19.4677 | 0.63845 | 0 | 0.63845 | 0 | 223 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 1 | 417 |  | 77 | 52 | 417 | 77 | 52 | 143.02 | 4.1094e-07 | 0 | 2698 | 1.4029e-05 | 1.5588e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.4029e-05 | 120.6052 | 120.6052 | 0%
Bay Area | EB_East Bay | HOLLYWOOD 0401 | 1306 | HOLLYWOOD 0401circuit_breaker | 2.1e-05 | 69.0853 | 6.0013 | 0.25625 | 5.7451 | 0.43788 | 189 | 152 | 70 | 68 | 3 | 2 | 0 | 298 | 0.92704 | 482 |  | 131 | 109 | 330 | 128 | 107 | 205.06 | 3.0397e-07 | 0 | 2699 | 3.2684e-05 | 1.5564e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.1289e-05 | 22.2799 | 21.8285 | 4.27%
Bay Area | NB_North Bay | GREENBRAE 1104 | 3308 | GREENBRAE 1104751 | 8e-06 | 7.8124 | 0.23125 | 0 | 0.23125 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 25 |  | 6 | 5 | 25 | 6 | 5 | 10.47 | 1.024e-06 | 0 | 2701 | 6.2216e-06 | 1.5554e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.2216e-06 | 25.9459 | 25.9459 | 0%
Central Coast | DA_De Anza | HICKS 1116 | 1993 | HICKS 1116LB16 | 2.2e-05 | 50.352 | 3.722 | 0 | 3.722 | 0 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 1 | 612 |  | 112 | 75 | 612 | 112 | 75 | 208.52 | 4.3692e-07 | 0 | 2702 | 6.8402e-05 | 1.5546e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.8402e-05 | 30.0916 | 30.0916 | 0%
Bay Area | PE_Peninsula | BERESFORD 0403 | 369 | BERESFORD 0403circuit_breaker | 1e-05 | 20.9203 | 0.82822 | 0 | 0.82822 | 0 | 166 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1 | 314 |  | 59 | 39 | 314 | 59 | 39 | 109.09 | 4.7801e-07 | 0 | 2703 | 3.5731e-05 | 1.5535e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.5731e-05 | 71.2371 | 71.2371 | 0%
Bay Area | EB_East Bay | PALO SECO 0401 | 4320 | OAKLAND X 1101CR224 | 1e-05 | 59.812 | 0.88712 | 0.22936 | 0.65777 | 0.28163 | 80 | 171 | 76 | 59 | 66 | 51 | 0 | 33 | 0.68254 | 279 |  | 97 | 73 | 108 | 31 | 22 | 52.19 | 1.6719e-07 | 0 | 2704 | 1.3889e-05 | 1.5432e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.0298e-05 | 47.1293 | 109.3424 | 25.85%
Bay Area | NB_North Bay | SAUSALITO 1102 | 543 | ALTO 112088190 | 0 | 1.7353 | 0.17727 | 0 | 0.17727 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 18 |  | 5 | 4 | 18 | 5 | 4 | 8.47 | 0 | 0 | 2705 | 7.6926e-06 | 1.5385e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.6926e-06 | 28.2051 | 28.2051 | 0%
Bay Area | PE_Peninsula | EMERALD LAKE 0402 | 40 | WOODSIDE 1104555372 | 4.8e-05 | 127.838 | 7.4464 | 0 | 7.4464 | 0 | 865 | 0 | 0 | 0 | 0 | 0 | 0 | 293 | 1 | 1583 |  | 287 | 190 | 1583 | 287 | 190 | 535.66 | 3.7548e-07 | 0 | 2707 | 8.1294e-05 | 1.5338e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.1294e-05 | 38.5421 | 38.5421 | 0%
Central Coast | LP_Los Padres | MORRO BAY 1102 | 136 | MORRO BAY 1102W34 | 0.0001 | 192.1291 | 7.7873 | 0 | 7.7873 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 1 | 693 |  | 127 | 85 | 693 | 127 | 85 | 236.36 | 5.2048e-07 | 0 | 2709 | 7.7636e-05 | 1.5223e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.7636e-05 | 16.3086 | 16.3086 | 0%
Central Coast | CC_Central Coast | VIEJO 2202 | 7806 | VIEJO 22029089 | 3e-06 | 26.8559 | 1.8934 | 0 | 1.8934 | 0 | 202 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 1 | 379 |  | 70 | 47 | 379 | 70 | 47 | 130.01 | 1.1171e-07 | 0 | 2710 | 1.3679e-05 | 1.5199e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.3679e-05 | 36.9711 | 36.9711 | 0%
Central Coast | CC_Central Coast | VIEJO 2202 | 3322 | VIEJO 22029104 | 1.3e-05 | 99.2765 | 4.253 | 0.020833 | 4.2322 | 0.3089 | 902 | 522 | 293 | 251 | 262 | 226 | 0 | 149 | 0.92737 | 2052 |  | 571 | 435 | 1530 | 309 | 209 | 561.03 | 1.3095e-07 | 0 | 2711 | 0.00011309 | 1.5079e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00011254 | 73.0117 | 134.2572 | 0.4898%
Bay Area | EB_East Bay | OAKLAND J 1102 | 7828 | OAKLAND J 1102CR254 | 1.5e-05 | 55.73 | 3.568 | 0 | 3.568 | 0 | 188 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 1 | 354 |  | 66 | 44 | 354 | 66 | 44 | 122.28 | 2.6915e-07 | 0 | 2712 | 1.6443e-05 | 1.4948e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.6443e-05 | 18.4978 | 18.4978 | 0%
Bay Area | PE_Peninsula | WOODSIDE 1104 | 5793 | WOODSIDE 11028862 | 2e-06 | 10.467 | 0.81913 | 0 | 0.81913 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 1 | 128 |  | 25 | 17 | 128 | 25 | 17 | 45.77 | 1.9108e-07 | 0 | 2713 | 2.9632e-06 | 1.4816e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.9632e-06 | 30.5202 | 30.5202 | 0%
Central Coast | CC_Central Coast | HATTON 1101 | 3771 | HATTON 11012026 | 5.5e-05 | 124.1919 | 4.942 | 0 | 4.942 | 0 | 321 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 1 | 595 |  | 109 | 73 | 595 | 109 | 73 | 202.88 | 4.4286e-07 | 0 | 2714 | 0.00011843 | 1.4803e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0.00011843 | 22.0556 | 22.0556 | 0%
Central Coast | CC_Central Coast | DEL MONTE 2103 | 1081 | DEL MONTE 210386496 | 1.6e-05 | 33.6848 | 1.9256 | 0.50739 | 1.4182 | 1.7422 | 284 | 532 | 56 | 45 | 5 | 4 | 0 | 56 | 0.09521 | 582 |  | 65 | 51 | 50 | 60 | 47 | 86.7 | 4.7499e-07 | 0 | 2716 | 2.1926e-05 | 1.4618e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.6149e-05 | 42.3077 | 33.7563 | 26.35%
Bay Area | MI_Mission | CASTRO VALLEY 1108 | 4812 | CASTRO VALLEY 1108circuit_breaker | 6.2e-05 | 100.861 | 1.503 | 0.12633 | 1.3767 | 0.33144 | 242 | 22 | 21 | 8 | 0 | 0 | 0 | 94 | 0.77949 | 374 |  | 86 | 52 | 352 | 86 | 52 | 149.5 | 6.1471e-07 | 0 | 2718 | 2.7611e-05 | 1.4532e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.529e-05 | 62.468 | 57.2177 | 8.405%
Bay Area | DI_Diablo | LAKEWOOD 1102 | 745 | LAKEWOOD 1102circuit_breaker | 0 | 0.63744 | 0.15606 | 0 | 0.15606 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 40 |  | 9 | 7 | 40 | 9 | 7 | 15.93 | 0 | 0 | 2719 | 2.8887e-06 | 1.4443e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.8887e-06 | 57.6699 | 57.6699 | 0%
Bay Area | EB_East Bay | OAKLAND J 1102 | 4871 | OAKLAND J 1102CR184 | 2.4e-05 | 76.1249 | 2.9362 | 0 | 2.9362 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 1 | 593 |  | 109 | 73 | 593 | 109 | 73 | 202.7 | 3.1527e-07 | 0 | 2720 | 5.9089e-05 | 1.4412e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.9089e-05 | 37.1231 | 37.1231 | 0%
Bay Area | EB_East Bay | BOSTON 0401 | 2647 | CR242 | 0 | 0 | 0.76648 | 0 | 0.76648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 2721 | 5.7634e-06 | 1.4409e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.7634e-06 | 5.2187 | 5.2187 | 0%
Bay Area | EB_East Bay | FRANKLIN 1104 | 4097 | FAIRVIEW 2207P142 | 4.2e-05 | 54.7354 | 3.2979 | 0 | 3.2979 | 0 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 1 | 152 |  | 29 | 20 | 152 | 29 | 20 | 53.41 | 7.6733e-07 | 0 | 2722 | 1.8718e-05 | 1.4398e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.8718e-05 | 8.7934 | 8.7934 | 0%
Central Coast | CC_Central Coast | VIEJO 2202 | 6234 | VIEJO 22029118 | 6e-06 | 6.9009 | 0.099242 | 0 | 0.099242 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 78 |  | 16 | 11 | 78 | 16 | 11 | 28.94 | 8.6945e-07 | 0 | 2723 | 1.1495e-05 | 1.4369e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.1495e-05 | 161.2214 | 161.2214 | 0%
Bay Area | MI_Mission | CASTRO VALLEY 1111 | 1645 | CASTRO VALLEY 1109circuit_breaker | 1.2e-05 | 20.7812 | 2.271 | 0 | 2.271 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 1 | 41 |  | 9 | 7 | 41 | 9 | 7 | 16.02 | 5.7744e-07 | 0 | 2724 | 1.4293e-06 | 1.4293e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.4293e-06 | 3.963 | 3.963 | 0%
Central Coast | LP_Los Padres | MORRO BAY 1102 | 822 | MORRO BAY 1102W22 | 1.7e-05 | 54.0648 | 2.3504 | 0 | 2.3504 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1 | 158 |  | 30 | 21 | 158 | 30 | 21 | 55.32 | 3.1444e-07 | 0 | 2727 | 4.2718e-05 | 1.378e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.2718e-05 | 12.7639 | 12.7639 | 0%
Bay Area | NB_North Bay | ALTO 1123 | 1013 | ALTO 1123circuit_breaker | 0.002513 | 26.4391 | 0.98674 | 0 | 0.98674 | 0 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1 | 245 |  | 46 | 31 | 245 | 46 | 31 | 85.07 | 9.5049e-05 | 1e-05 | 2728 | 1.1009e-05 | 1.3761e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.1009e-05 | 46.618 | 46.618 | 0%
Bay Area | EB_East Bay | EDES 1112 | 3926 | EDES 1112CR100 | 1.1e-05 | 51.2026 | 2.4269 | 0 | 2.4269 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 1 | 285 |  | 53 | 36 | 285 | 53 | 36 | 98.26 | 2.1483e-07 | 0 | 2730 | 4.7361e-05 | 1.3532e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.7361e-05 | 21.8386 | 21.8386 | 0%
Bay Area | MI_Mission | CASTRO VALLEY 1101 | 3626 | CASTRO VALLEY 1101MR359 | 8e-06 | 11.9203 | 1.0432 | 0 | 1.0432 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 1 | 25 |  | 6 | 5 | 25 | 6 | 5 | 10.47 | 6.7112e-07 | 0 | 2734 | 1.289e-05 | 1.289e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.289e-05 | 5.7516 | 5.7516 | 0%
Bay Area | PE_Peninsula | RALSTON 1101 | 410 | RALSTON 1101circuit_breaker | 8.7e-05 | 84.954 | 5.5032 | 0 | 5.5032 | 0 | 267 | 0 | 0 | 0 | 0 | 0 | 0 | 167 | 1 | 497 |  | 92 | 61 | 497 | 92 | 61 | 170.77 | 1.0241e-06 | 0 | 2736 | 7.1265e-05 | 1.2726e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.1265e-05 | 16.7175 | 16.7175 | 0%
Bay Area | MI_Mission | SAN LEANDRO U 1114 | 2000 | SAN LEANDRO U 1114MR218 | 3.1e-05 | 117.1191 | 20.8616 | 0 | 20.8616 | 0 | 464 | 0 | 0 | 0 | 0 | 0 | 0 | 952 | 1 | 855 |  | 156 | 104 | 855 | 156 | 104 | 290.67 | 2.6469e-07 | 0 | 2737 | 5.977e-05 | 1.2717e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.977e-05 | 7.4779 | 7.4779 | 0%
Central Coast | CC_Central Coast | VIEJO 2202 | 2334 | VIEJO 22049110 | 1e-06 | 40.8513 | 2.2388 | 0 | 2.2388 | 0 | 427 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 1 | 788 |  | 144 | 96 | 788 | 144 | 96 | 268.2 | 2.4479e-08 | 0 | 2738 | 1.2694e-06 | 1.2694e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.2694e-06 | 64.3194 | 64.3194 | 0%
Bay Area | NB_North Bay | STAFFORD 1101 | 2921 | STAFFORD 11011298 | 4.1e-05 | 68.3612 | 1.5475 | 0 | 1.5475 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 1 | 123 |  | 24 | 17 | 123 | 24 | 17 | 43.95 | 5.9976e-07 | 0 | 2740 | 2.5155e-05 | 1.2578e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.5155e-05 | 15.5085 | 15.5085 | 0%
Bay Area | EB_East Bay | EDES 1112 | 868 | EDES 1112CR308 | 3.3e-05 | 108.8594 | 2.7068 | 0 | 2.7068 | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 1 | 421 |  | 78 | 52 | 421 | 78 | 52 | 144.75 | 3.0314e-07 | 0 | 2741 | 4.258e-05 | 1.2523e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.258e-05 | 28.8161 | 28.8161 | 0%
Sierra | SI_Sierra | ECHO SUMMIT 1101 | 9061 | ECHO SUMMIT 1101344250 | 1e-06 | 17.219 | 1.1627 | 0 | 1.1627 | 0 | 619 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 1 | 1136 |  | 207 | 137 | 1136 | 207 | 137 | 385.83 | 5.8075e-08 | 0 | 2742 | 1.1161e-05 | 1.2401e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.1161e-05 | 178.0355 | 178.0355 | 0%
Central Coast | CC_Central Coast | HOLLISTER 2102 | 3597 | HOLLISTER 210441808 | 0.002433 | 5.8904 | 0.12784 | 0 | 0.12784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.00041304 | 0 | 2743 | 1.2376e-06 | 1.2376e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.2376e-06 | 31.2889 | 31.2889 | 0%
Bay Area | PE_Peninsula | SAN CARLOS 1104 | 5376 | SAN CARLOS 11048942 | 3.3e-05 | 91.2101 | 3.7134 | 0 | 3.7134 | 0 | 171 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 1 | 323 |  | 60 | 41 | 323 | 60 | 41 | 111.27 | 3.618e-07 | 0 | 2744 | 3.3394e-05 | 1.2368e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.3394e-05 | 16.1575 | 16.1575 | 0%
North Valley | NV_North Valley | BIG MEADOWS 2101 | 8763 | BIG MEADOWS 2101439 | 1e-06 | 14.268 | 0.69394 | 0 | 0.69394 | 0 | 419 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 1 | 773 |  | 141 | 94 | 773 | 141 | 94 | 262.74 | 7.0087e-08 | 0 | 2745 | 1.2258e-05 | 1.2258e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.2258e-05 | 203.1878 | 203.1878 | 0%
Sierra | SI_Sierra | ECHO SUMMIT 1101 | 1545 | ECHO SUMMIT 11012500 | 1e-06 | 50.3903 | 1.9004 | 0 | 1.9004 | 0 | 1008 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 1 | 1843 |  | 334 | 221 | 1843 | 334 | 221 | 623.45 | 1.9845e-08 | 0 | 2746 | 4.4048e-05 | 1.2236e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.4048e-05 | 175.7544 | 175.7544 | 0%
Central Coast | LP_Los Padres | MORRO BAY 1102 | 3814 | MORRO BAY 1102V84 | 0.000577 | 28.0604 | 1.5659 | 0 | 1.5659 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 1 | 27 |  | 7 | 5 | 27 | 7 | 5 | 12.02 | 2.0563e-05 | 0 | 2747 | 1.2196e-06 | 1.2196e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.2196e-06 | 4.4702 | 4.4702 | 0%
Bay Area | PE_Peninsula | EMERALD LAKE 0402 | 199 | LAS PULGAS 0401circuit_breaker | 1e-06 | 1.86 | 0.40227 | 0 | 0.40227 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1 | 36 |  | 8 | 6 | 36 | 8 | 6 | 14.2 | 5.3763e-07 | 0 | 2748 | 9.705e-06 | 1.2131e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.705e-06 | 19.887 | 19.887 | 0%
Central Coast | CC_Central Coast | SOLEDAD 2102 | 2513 | SOLEDAD 21027562 | 0.000559 | 18.792 | 1.3741 | 0 | 1.3741 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 1 | 45 |  | 10 | 8 | 45 | 10 | 8 | 17.75 | 2.9747e-05 | 0 | 2749 | 2.4237e-06 | 1.2119e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.4237e-06 | 7.2777 | 7.2777 | 0%
Bay Area | MI_Mission | CASTRO VALLEY 1104 | 2617 | CASTRO VALLEY 1104MR201 | 4e-06 | 32.321 | 2.4447 | 0 | 2.4447 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 1 | 103 |  | 21 | 14 | 103 | 21 | 14 | 38.04 | 1.2376e-07 | 0 | 2750 | 1.4518e-05 | 1.2099e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.4518e-05 | 8.59 | 8.59 | 0%
Central Coast | CC_Central Coast | FORT ORD 2106 | 8443 | FORT ORD 210637286 | 1.7e-05 | 66.2706 | 2.4451 | 0 | 2.4451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 2.5652e-07 | 0 | 2751 | 1.2096e-06 | 1.2096e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.2096e-06 | 1.6359 | 1.6359 | 0%
Bay Area | EB_East Bay | OAKLAND J 1105 | 42 | OAKLAND J 1105153228 | 0 | 3.594 | 0.36004 | 0 | 0.36004 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1 | 27 |  | 7 | 5 | 27 | 7 | 5 | 12.02 | 0 | 0 | 2752 | 2.391e-06 | 1.1955e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.391e-06 | 19.4424 | 19.4424 | 0%
Central Coast | CC_Central Coast | GONZALES 1103 | 2481 | GONZALES 11033096 | 5e-05 | 45.0102 | 2.1047 | 0 | 2.1047 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 1 | 54 |  | 12 | 9 | 54 | 12 | 9 | 21.3 | 1.1109e-06 | 0 | 2755 | 1.1589e-05 | 1.1589e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.1589e-05 | 5.7014 | 5.7014 | 0%
Central Coast | CC_Central Coast | SOLEDAD 2101 | 1286 | SOLEDAD 2101circuit_breaker | 4.8e-05 | 18.0047 | 1.1547 | 0 | 1.1547 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 49 |  | 11 | 8 | 49 | 11 | 8 | 19.48 | 2.666e-06 | 0 | 2756 | 4.6259e-06 | 1.1565e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.6259e-06 | 9.526 | 9.526 | 0%
North Valley | NV_North Valley | EAST QUINCY 1101 | 7483 | EAST QUINCY 11011319 | 6e-06 | 13.2989 | 0.61951 | 0 | 0.61951 | 0.58542 | 299 | 635 | 201 | 187 | 0 | 0 | 0 | 16 | 0.055029 | 666 |  | 207 | 191 | 31 | 207 | 191 | 286.38 | 4.5117e-07 | 0 | 2757 | 2.3127e-06 | 1.1563e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.3127e-06 | 334.1363 | 334.1363 | 0%
Bay Area | PE_Peninsula | SNEATH LANE 1101 | 4550 | SNEATH LANE 110134438 | 4e-06 | 30.9936 | 3.0235 | 0 | 3.0235 | 0 | 683 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 1 | 1253 |  | 228 | 151 | 1253 | 228 | 151 | 425.13 | 1.2906e-07 | 0 | 2758 | 2.7599e-05 | 1.1499e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.7599e-05 | 75.4097 | 75.4097 | 0%
Bay Area | EB_East Bay | EL CERRITO G 1105 | 474 | EL CERRITO G 1105circuit_breaker | 0.005971 | 117.024 | 4.9693 | 0 | 4.9693 | 0 | 315 | 0 | 0 | 0 | 0 | 0 | 0 | 201 | 1 | 584 |  | 107 | 72 | 584 | 107 | 72 | 199.15 | 5.1024e-05 | 1e-05 | 2759 | 8.8216e-05 | 1.1457e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.8216e-05 | 21.5321 | 21.5321 | 0%
Bay Area | EB_East Bay | VALLEY VIEW 1105 | 2622 | VALLEY VIEW 1105P190 | 7e-06 | 71.2596 | 3.3691 | 0 | 3.3691 | 0 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 1 | 762 |  | 139 | 93 | 762 | 139 | 93 | 259.01 | 9.8232e-08 | 0 | 2760 | 5.5953e-05 | 1.1419e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.5953e-05 | 41.257 | 41.257 | 0%
Bay Area | EB_East Bay | OAK 0401 | 3517 | OAK 0401circuit_breaker | 1e-06 | 33.5651 | 2.5551 | 0 | 2.5551 | 0 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 1 | 252 |  | 47 | 32 | 252 | 47 | 32 | 87.07 | 2.9793e-08 | 0 | 2761 | 4.4441e-05 | 1.1395e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.4441e-05 | 18.3945 | 18.3945 | 0%
Bay Area | PE_Peninsula | BAY MEADOWS 2102 | 6115 | BAY MEADOWS 210257886 | 3.2e-05 | 101.101 | 4.335 | 0 | 4.335 | 0 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 1 | 762 |  | 139 | 93 | 762 | 139 | 93 | 259.01 | 3.1652e-07 | 0 | 2762 | 7.4545e-05 | 1.1295e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.4545e-05 | 32.0643 | 32.0643 | 0%
Bay Area | EB_East Bay | SAN LEANDRO U 1109 | 3200 | SAN LEANDRO U 1109CR002 | 3.3e-05 | 138.2381 | 6.6377 | 0 | 6.6377 | 0 | 423 | 0 | 0 | 0 | 0 | 0 | 0 | 249 | 1 | 780 |  | 143 | 95 | 780 | 143 | 95 | 266.11 | 2.3872e-07 | 0 | 2763 | 8.2117e-05 | 1.1249e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.2117e-05 | 21.5436 | 21.5436 | 0%
Central Coast | CC_Central Coast | SOLEDAD 1114 | 8392 | SOLEDAD 111435306 | 0.001968 | 34.341 | 1.6367 | 0 | 1.6367 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1 | 18 |  | 5 | 4 | 18 | 5 | 4 | 8.47 | 5.7308e-05 | 0 | 2764 | 1.1231e-06 | 1.1231e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.1231e-06 | 3.0548 | 3.0548 | 0%
Bay Area | EB_East Bay | OAKLAND J 1106 | 3199 | OAKLAND J 1106CR330 | 4e-06 | 11.7889 | 0.78598 | 0 | 0.78598 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 1 | 74 |  | 15 | 11 | 74 | 15 | 11 | 27.21 | 3.393e-07 | 0 | 2765 | 5.552e-06 | 1.1104e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.552e-06 | 19.0843 | 19.0843 | 0%
Central Coast | LP_Los Padres | PURISIMA 1101 | 359 | PURISIMA 110149394 | 5e-06 | 19.5224 | 1.2098 | 0 | 1.2098 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 1 | 36 |  | 8 | 6 | 36 | 8 | 6 | 14.2 | 2.5612e-07 | 0 | 2766 | 1.1028e-05 | 1.1028e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.1028e-05 | 6.6124 | 6.6124 | 0%
Bay Area | DI_Diablo | ALHAMBRA 1105 | 5182 | ALHAMBRA 1105circuit_breaker | 6e-06 | 10.833 | 0.50758 | 0 | 0.50758 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 132 |  | 26 | 18 | 132 | 26 | 18 | 47.5 | 5.5386e-07 | 0 | 2767 | 9.8746e-06 | 1.0972e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.8746e-06 | 51.2239 | 51.2239 | 0%
North Valley | NV_North Valley | HAMILTON BRANCH 1101 | 9380 | HAMILTON BRANCH 11012436 | 3e-06 | 16.2032 | 1.0794 | 0 | 1.0794 | 0 | 311 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 577 |  | 106 | 71 | 577 | 106 | 71 | 197.15 | 1.8515e-07 | 0 | 2769 | 9.7145e-06 | 1.0794e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.7145e-06 | 98.2067 | 98.2067 | 0%
Central Coast | CC_Central Coast | DEL MONTE 1101 | 954 | DEL MONTE 110138582 | 3e-06 | 14.0074 | 5.1398 | 0 | 5.1398 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 264 | 1 | 20 |  | 5 | 5 | 20 | 5 | 5 | 8.65 | 2.1417e-07 | 0 | 2770 | 4.288e-06 | 1.072e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.288e-06 | 0.97281 | 0.97281 | 0%
Sierra | SI_Sierra | ECHO SUMMIT 1101 | 6441 | ECHO SUMMIT 11018922 | 5e-06 | 51.558 | 2.0036 | 0 | 2.0036 | 0 | 843 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 1 | 1543 |  | 280 | 186 | 1543 | 280 | 186 | 522.47 | 9.6978e-08 | 0 | 2773 | 1.994e-05 | 1.0495e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.994e-05 | 139.7486 | 139.7486 | 0%
Bay Area | EB_East Bay | OAKLAND J 1116 | 638 | OAKLAND J 1105CR130 | 2e-06 | 17.9112 | 2.9491 | 0 | 2.9491 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 1 | 112 |  | 22 | 16 | 112 | 22 | 16 | 40.22 | 1.1166e-07 | 0 | 2774 | 2.0529e-06 | 1.0264e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.0529e-06 | 7.46 | 7.46 | 0%
Bay Area | EB_East Bay | OAKLAND J 1106 | 1652 | OAKLAND J 1118CR198 | 1.4e-05 | 22.3951 | 1.197 | 0 | 1.197 | 0 | 141 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 1 | 268 |  | 50 | 34 | 268 | 50 | 34 | 92.62 | 6.2514e-07 | 0 | 2775 | 1.0225e-06 | 1.0225e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.0225e-06 | 41.7722 | 41.7722 | 0%
Bay Area | PE_Peninsula | SNEATH LANE 1107 | 7965 | SNEATH LANE 110715341 | 1.7e-05 | 11.9833 | 0.68163 | 0 | 0.68163 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1 | 121 |  | 24 | 17 | 121 | 24 | 17 | 43.77 | 1.4186e-06 | 0 | 2776 | 4.0413e-06 | 1.0103e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.0413e-06 | 35.2098 | 35.2098 | 0%
Bay Area | EB_East Bay | EL CERRITO G 1112 | 3699 | EL CERRITO G 1112circuit_breaker | 5e-06 | 13.4053 | 1.2277 | 0 | 1.2277 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 1 | 187 |  | 36 | 24 | 187 | 36 | 24 | 66.15 | 3.7299e-07 | 0 | 2777 | 3.0205e-06 | 1.0068e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.0205e-06 | 29.3243 | 29.3243 | 0%
Central Coast | CC_Central Coast | HATTON 1102 | 4475 | HATTON 11022070 | 9e-06 | 40.7392 | 1.2496 | 0.44129 | 0.80833 | 0.6 | 283 | 260 | 42 | 21 | 38 | 17 | 0 | 35 | 0.51985 | 534 |  | 92 | 55 | 274 | 54 | 38 | 98.64 | 2.2092e-07 | 0 | 2778 | 9.8727e-06 | 9.8727e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.3863e-06 | 66.8041 | 73.6223 | 35.31%
Sierra | SA_Sacramento | VACAVILLE 1112 | 2274 | VACAVILLE 1112circuit_breaker | 0 | 1.2005 | 0.13655 | 0 | 0.13655 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 27 |  | 7 | 5 | 27 | 7 | 5 | 12.02 | 0 | 0 | 2779 | 1.9678e-06 | 9.8392e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.9678e-06 | 51.2621 | 51.2621 | 0%
Bay Area | MI_Mission | CASTRO VALLEY 1108 | 141 | CASTRO VALLEY 1108MR379 | 5.7e-05 | 90.9927 | 2.3049 | 0.095076 | 2.21 | 1.4489 | 386 | 162 | 162 | 119 | 0 | 0 | 0 | 148 | 0.37141 | 427 |  | 211 | 151 | 265 | 211 | 151 | 312.92 | 6.2642e-07 | 0 | 2780 | 1.075e-05 | 9.7725e-07 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.0307e-05 | 95.4735 | 91.5431 | 4.125%
Central Coast | SJ_San Jose | MORGAN HILL 2111 | 6054 | MORGAN HILL 2111circuit_breaker | 0.095499 | 27.2032 | 0.85114 | 0 | 0.85114 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1 | 81 |  | 17 | 12 | 81 | 17 | 12 | 30.58 | 0.0035106 | 0.00012 | 2782 | 2.8904e-06 | 9.6346e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.8904e-06 | 19.9733 | 19.9733 | 0%
Bay Area | NB_North Bay | IGNACIO 1105 | 3401 | 318 | 0.003374 | 81.3843 | 14.197 | 0 | 14.197 | 0 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 681 | 1 | 252 |  | 47 | 32 | 252 | 47 | 32 | 87.07 | 4.1458e-05 | 0 | 2784 | 2.086e-05 | 9.4818e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.086e-05 | 3.3106 | 3.3106 | 0%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1108 | 4756 | SAN LUIS OBISPO 1108circuit_breaker | 0.046073 | 61.4735 | 2.3862 | 1.6684 | 0.7178 | 1.6684 | 12 | 94 | 26 | 1 | 26 | 1 | 0 | 56 | 0.30082 | 104 |  | 28 | 3 | 10 | 2 | 2 | 3.64 | 0.00074948 | 0 | 2785 | 8.4411e-06 | 9.379e-07 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.5392e-06 | 2.7863 | 11.7343 | 69.92%
Bay Area | EB_East Bay | EL CERRITO G 1105 | 4494 | EL CERRITO G 1105BR194 | 1.8e-05 | 107.9506 | 6.7612 | 0 | 6.7612 | 0 | 307 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 1 | 570 |  | 105 | 70 | 570 | 105 | 70 | 195.15 | 1.6674e-07 | 0 | 2786 | 3.6977e-05 | 9.2444e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.6977e-05 | 15.5298 | 15.5298 | 0%
Bay Area | EB_East Bay | EL CERRITO G 1111 | 1646 | EL CERRITO G 1111circuit_breaker | 0 | 2.3501 | 0.057386 | 0 | 0.057386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 2788 | 2.7259e-06 | 9.0864e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.7259e-06 | 69.703 | 69.703 | 0%
Central Coast | CC_Central Coast | VIEJO 2202 | 4313 | MONTEREY 04012642 | 2e-06 | 10.5091 | 0.79583 | 0 | 0.79583 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 1 | 181 |  | 35 | 24 | 181 | 35 | 24 | 64.24 | 1.9031e-07 | 0 | 2789 | 1.7668e-06 | 8.834e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.7668e-06 | 43.9791 | 43.9791 | 0%
Bay Area | PE_Peninsula | SNEATH LANE 1102 | 4623 | SNEATH LANE 11071277 | 1e-05 | 4.7981 | 0.43788 | 0 | 0.43788 | 0 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 210 |  | 40 | 27 | 210 | 40 | 27 | 73.7 | 2.0842e-06 | 0 | 2790 | 1.7559e-06 | 8.7797e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.7559e-06 | 91.3495 | 91.3495 | 0%
Bay Area | EB_East Bay | FAIRMOUNT 0401 | 3555 | FAIRMOUNT 0401circuit_breaker | 4e-06 | 56.8521 | 3.4473 | 0 | 3.4473 | 0 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 1 | 207 |  | 39 | 27 | 207 | 39 | 27 | 72.06 | 7.0358e-08 | 0 | 2791 | 7.0236e-06 | 8.7795e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.0236e-06 | 11.313 | 11.313 | 0%
North Valley | NV_North Valley | GANSNER 1101 | 6801 | GANSNER 110199388 | 2e-06 | 17.5565 | 0.84337 | 0 | 0.84337 | 0 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 630 |  | 116 | 77 | 630 | 116 | 77 | 215.62 | 1.1392e-07 | 0 | 2792 | 8.7699e-06 | 8.7699e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.7699e-06 | 137.5432 | 137.5432 | 0%
Central Coast | CC_Central Coast | VIEJO 2202 | 3855 | MONTEREY 04022644 | 3e-06 | 31.6022 | 2.2496 | 0 | 2.2496 | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 1 | 276 |  | 52 | 35 | 276 | 52 | 35 | 96.08 | 9.493e-08 | 0 | 2793 | 7.8719e-06 | 8.7465e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.8719e-06 | 23.115 | 23.115 | 0%
Bay Area | MI_Mission | CASTRO VALLEY 1101 | 1956 | CASTRO VALLEY 1101MR518 | 1e-06 | 9.6786 | 0.39811 | 0 | 0.39811 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 32 |  | 8 | 6 | 32 | 8 | 6 | 13.84 | 1.0332e-07 | 0 | 2794 | 2.5951e-06 | 8.6505e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.5951e-06 | 20.0951 | 20.0951 | 0%
Bay Area | EB_East Bay | EDES 1112 | 3585 | EDES 1112circuit_breaker | 5e-06 | 18.7911 | 0.83106 | 0 | 0.83106 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1 | 176 |  | 34 | 23 | 176 | 34 | 23 | 62.42 | 2.6608e-07 | 0 | 2795 | 1.6923e-06 | 8.4613e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.6923e-06 | 40.9116 | 40.9116 | 0%
North Valley | NV_North Valley | HAMILTON BRANCH 1101 | 9495 | HAMILTON BRANCH 110118205 | 0.00063 | 82.6361 | 4.1223 | 0 | 4.1223 | 0 | 974 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 1 | 1781 |  | 323 | 214 | 1781 | 323 | 214 | 602.8 | 7.6238e-06 | 1e-05 | 2796 | 1.8461e-05 | 8.3913e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.8461e-05 | 78.3534 | 78.3534 | 0%
Bay Area | EB_East Bay | FRANKLIN 1104 | 9208 | FRANKLIN 1104P136 | 0 | 13.7048 | 2.275 | 0 | 2.275 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 1 | 27 |  | 7 | 5 | 27 | 7 | 5 | 12.02 | 0 | 0 | 2797 | 2.0133e-05 | 8.3885e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.0133e-05 | 3.0769 | 3.0769 | 0%
Bay Area | PE_Peninsula | SNEATH LANE 1102 | 476 | SNEATH LANE 110210255 | 1e-06 | 5.1196 | 0.57405 | 0 | 0.57405 | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 241 |  | 45 | 31 | 241 | 45 | 31 | 83.34 | 1.9533e-07 | 0 | 2798 | 8.1308e-07 | 8.1308e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.1308e-07 | 78.39 | 78.39 | 0%
Bay Area | EB_East Bay | VALLEY VIEW 1105 | 3646 | VALLEY VIEW 1105P126 | 5e-06 | 32.3727 | 1.1129 | 0 | 1.1129 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1 | 105 |  | 21 | 15 | 105 | 21 | 15 | 38.22 | 1.5445e-07 | 0 | 2799 | 1.1382e-05 | 8.1299e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.1382e-05 | 18.87 | 18.87 | 0%
Bay Area | NB_North Bay | SAUSALITO 1102 | 7735 | SAUSALITO 1102410 | 0.022873 | 47.2333 | 2.1326 | 0 | 2.1326 | 0 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1 | 470 |  | 87 | 58 | 470 | 87 | 58 | 161.49 | 0.00048426 | 9e-05 | 2801 | 1.026e-05 | 7.892e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.026e-05 | 40.7957 | 40.7957 | 0%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1102 | 5474 | SAN LUIS OBISPO 1102597518 | 0.009544 | 0.91648 | 0.072917 | 0 | 0.072917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.010414 | 9e-05 | 2802 | 7.779e-07 | 7.779e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.779e-07 | 54.8571 | 54.8571 | 0%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1107 | 7161 | SAN LUIS OBISPO 1107circuit_breaker | 0.022018 | 33.936 | 1.3313 | 0.31856 | 1.0127 | 0.31856 | 25 | 20 | 2 | 0 | 2 | 0 | 0 | 36 | 0.76071 | 64 |  | 11 | 7 | 44 | 9 | 7 | 16.29 | 0.00064881 | 1e-05 | 2803 | 3.8471e-06 | 7.6941e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.9265e-06 | 8.8872 | 8.2629 | 23.93%
Bay Area | PE_Peninsula | RALSTON 1101 | 25 | RALSTON 110148936 | 9e-06 | 146.635 | 6.1241 | 0 | 6.1241 | 0 | 303 | 0 | 0 | 0 | 0 | 0 | 0 | 184 | 1 | 563 |  | 103 | 69 | 563 | 103 | 69 | 191.78 | 6.1377e-08 | 0 | 2804 | 4.6028e-05 | 7.6714e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.6028e-05 | 16.8189 | 16.8189 | 0%
Bay Area | MI_Mission | SAN LEANDRO U 1114 | 1040 | SAN LEANDRO U 1114MR545 | 1e-06 | 57.3275 | 7.1669 | 0 | 7.1669 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 384 | 1 | 112 |  | 22 | 16 | 112 | 22 | 16 | 40.22 | 1.7444e-08 | 0 | 2805 | 1.7398e-05 | 7.5645e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.7398e-05 | 3.0697 | 3.0697 | 0%
Bay Area | EB_East Bay | OAKLAND K 1103 | 196 | OAKLAND K 1103circuit_breaker | 1.6e-05 | 40.3661 | 0.84621 | 0 | 0.84621 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 167 |  | 32 | 22 | 167 | 32 | 22 | 58.87 | 3.9637e-07 | 0 | 2806 | 4.5348e-06 | 7.558e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.5348e-06 | 37.8156 | 37.8156 | 0%
Bay Area | MI_Mission | SAN LEANDRO U 1114 | 2371 | SAN LEANDRO U 1114MR544 | 2e-06 | 19.7837 | 8.3487 | 0 | 8.3487 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 509 | 1 | 145 |  | 28 | 19 | 145 | 28 | 19 | 51.41 | 1.0109e-07 | 0 | 2807 | 3.0195e-06 | 7.5488e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.0195e-06 | 3.3538 | 3.3538 | 0%
Bay Area | NB_North Bay | LAS GALLINAS A 1105 | 5766 | LAS GALLINAS A 11041220 | 0.000318 | 6.821 | 0.11799 | 0 | 0.11799 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 14 |  | 5 | 4 | 14 | 5 | 4 | 8.11 | 4.6621e-05 | 0 | 2808 | 7.2609e-07 | 7.2609e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.2609e-07 | 42.3756 | 42.3756 | 0%
North Valley | NV_North Valley | HAMILTON BRANCH 1101 | 6253 | HAMILTON BRANCH 11012082 | 0 | 49.9826 | 2.5682 | 0 | 2.5682 | 0 | 1473 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 1 | 2687 |  | 487 | 321 | 2687 | 487 | 321 | 909.02 | 0 | 0 | 2809 | 1.0847e-05 | 7.2314e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.0847e-05 | 189.6283 | 189.6283 | 0%
Bay Area | NB_North Bay | LAS GALLINAS A 1106 | 5600 | LAS GALLINAS A 11051218 | 5e-06 | 4.2233 | 0.099242 | 0 | 0.099242 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 16 |  | 5 | 4 | 16 | 5 | 4 | 8.29 | 1.1839e-06 | 0 | 2810 | 7.2039e-07 | 7.2039e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 7.2039e-07 | 50.3817 | 50.3817 | 0%
Sierra | SI_Sierra | ECHO SUMMIT 1101 | 8825 | ECHO SUMMIT 1101481660 | 3e-06 | 21.315 | 0.97386 | 0 | 0.97386 | 0 | 379 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 1 | 701 |  | 128 | 85 | 701 | 128 | 85 | 238.45 | 1.4075e-07 | 0 | 2811 | 3.5979e-06 | 7.1959e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.5979e-06 | 131.4352 | 131.4352 | 0%
North Valley | NV_North Valley | HAMILTON BRANCH 1101 | 3715 | HAMILTON BRANCH 11013049 | 0 | 13.756 | 0.70265 | 0 | 0.70265 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 920 |  | 168 | 112 | 920 | 168 | 112 | 312.96 | 0 | 0 | 2813 | 9.984e-06 | 7.1314e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.984e-06 | 239.0943 | 239.0943 | 0%
Central Coast | LP_Los Padres | OCEANO 1103 | 4257 | OCEANO 1103V22 | 0.22461 | 11.2047 | 0.52576 | 0 | 0.52576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.020046 | 0.00017 | 2814 | 6.989e-07 | 6.989e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.989e-07 | 7.6081 | 7.6081 | 0%
Central Coast | CC_Central Coast | VIEJO 2204 | 3165 | VIEJO 22049098 | 1e-06 | 6.2695 | 0.1661 | 0 | 0.1661 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 30 |  | 7 | 6 | 30 | 7 | 6 | 12.29 | 1.595e-07 | 0 | 2815 | 2.7941e-06 | 6.9853e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.7941e-06 | 42.1437 | 42.1437 | 0%
North Valley | NV_North Valley | HAMILTON BRANCH 1101 | 1494 | HAMILTON BRANCH 110187784 | 0 | 23.8031 | 0.58674 | 0 | 0.58674 | 0 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 548 |  | 101 | 67 | 548 | 101 | 67 | 187.69 | 0 | 0 | 2816 | 1.8736e-05 | 6.9392e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.8736e-05 | 172.1369 | 172.1369 | 0%
North Valley | NV_North Valley | BIG MEADOWS 2101 | 6355 | BIG MEADOWS 21012246 | 0 | 36.0482 | 1.6347 | 0 | 1.6347 | 0 | 1249 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 1 | 2280 |  | 413 | 273 | 2280 | 413 | 273 | 771.01 | 0 | 0 | 2817 | 2.1909e-05 | 6.8466e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.1909e-05 | 252.6521 | 252.6521 | 0%
Bay Area | DI_Diablo | ALHAMBRA 1105 | 342 | ALHAMBRA 1102circuit_breaker | 0.001149 | 30.1536 | 2.0756 | 0 | 2.0756 | 0 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 1 | 236 |  | 44 | 30 | 236 | 44 | 30 | 81.52 | 3.8105e-05 | 0 | 2818 | 6.8369e-07 | 6.8369e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.8369e-07 | 21.199 | 21.199 | 0%
Bay Area | EB_East Bay | WALDO 0401 | 737 | WALDO 0401circuit_breaker | 0.001414 | 39.4572 | 2.1549 | 0 | 2.1549 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 1 | 76 |  | 16 | 11 | 76 | 16 | 11 | 28.76 | 3.5836e-05 | 0 | 2819 | 1.2192e-05 | 6.7734e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.2192e-05 | 7.4249 | 7.4249 | 0%
Central Coast | CC_Central Coast | SOLEDAD 2102 | 4836 | SOLEDAD 21027008 | 3e-06 | 19.0054 | 1.7608 | 0 | 1.7608 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 1 | 34 |  | 8 | 6 | 34 | 8 | 6 | 14.02 | 1.5785e-07 | 0 | 2820 | 6.7393e-07 | 6.7393e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.7393e-07 | 4.5434 | 4.5434 | 0%
Bay Area | MI_Mission | SAN LEANDRO U 1114 | 5548 | SAN LEANDRO U 11149838 | 2e-06 | 19.3824 | 4.5816 | 0 | 4.5816 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 218 | 1 | 27 |  | 7 | 5 | 27 | 7 | 5 | 12.02 | 1.0319e-07 | 0 | 2821 | 4.0295e-06 | 6.7159e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.0295e-06 | 1.5278 | 1.5278 | 0%
Bay Area | PE_Peninsula | BELMONT 1110 | 486 | BELMONT 11109090 | 0 | 5.4122 | 0.20227 | 0 | 0.20227 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 61 |  | 13 | 10 | 61 | 13 | 10 | 23.3 | 0 | 0 | 2823 | 6.5519e-07 | 6.5519e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.5519e-07 | 64.2697 | 64.2697 | 0%
Bay Area | MI_Mission | CASTRO VALLEY 1104 | 418 | CASTRO VALLEY 1104MR236 | 3e-06 | 23.6031 | 1.9265 | 0 | 1.9265 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 1 | 83 |  | 17 | 12 | 83 | 17 | 12 | 30.76 | 1.271e-07 | 0 | 2825 | 9.1934e-06 | 6.1289e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 9.1934e-06 | 8.8242 | 8.8242 | 0%
Bay Area | EB_East Bay | FRANKLIN 1104 | 7712 | FRANKLIN 1101P138 | 1e-06 | 39.0219 | 2.2799 | 0 | 2.2799 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 1 | 61 |  | 13 | 10 | 61 | 13 | 10 | 23.3 | 2.5627e-08 | 0 | 2826 | 3.0467e-06 | 6.0933e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.0467e-06 | 5.7019 | 5.7019 | 0%
North Valley | NV_North Valley | BIG MEADOWS 2101 | 7348 | BIG MEADOWS 21012510 | 0.000449 | 118.9169 | 7.4593 | 0 | 7.4593 | 0 | 4177 | 0 | 0 | 0 | 0 | 0 | 0 | 233 | 1 | 7598 |  | 1372 | 905 | 7598 | 1372 | 905 | 2563.46 | 3.7757e-06 | 1e-05 | 2827 | 3.0357e-05 | 6.0715e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.0357e-05 | 183.932 | 183.932 | 0%
Central Coast | CC_Central Coast | FORT ORD 2107 | 2660 | FORT ORD 210736596 | 7e-06 | 115.4734 | 3.4566 | 0 | 3.4566 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 1 | 20 |  | 5 | 5 | 20 | 5 | 5 | 8.65 | 6.062e-08 | 0 | 2830 | 4.5031e-06 | 5.6289e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.5031e-06 | 1.4465 | 1.4465 | 0%
North Valley | NV_North Valley | HAMILTON BRANCH 1101 | 6179 | HAMILTON BRANCH 110153192 | 0 | 9.1698 | 0.43864 | 0 | 0.43864 | 0 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 236 |  | 44 | 30 | 236 | 44 | 30 | 81.52 | 0 | 0 | 2832 | 5.5275e-06 | 5.5275e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.5275e-06 | 100.3109 | 100.3109 | 0%
Central Coast | CC_Central Coast | DEL MONTE 1101 | 2576 | DEL MONTE 21029060 | 0 | 0 | 2.6068 | 0 | 2.6068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 2833 | 5.0594e-07 | 5.0594e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.0594e-07 | 1.5344 | 1.5344 | 0%
Sierra | SI_Sierra | SUMMIT 1101 | 8203 | SUMMIT 110186658 | 0 | 13.75 | 0.21458 | 0 | 0.21458 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 56 |  | 12 | 9 | 56 | 12 | 9 | 21.48 | 0 | 0 | 2834 | 2.722e-06 | 4.5367e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.722e-06 | 55.9223 | 55.9223 | 0%
Sierra | SI_Sierra | SUMMIT 1101 | 7328 | SUMMIT 110148632 | 0 | 78.4323 | 3.5498 | 0 | 3.5498 | 0 | 1619 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 1 | 2952 |  | 534 | 353 | 2952 | 534 | 353 | 997.26 | 0 | 0 | 2835 | 1.5794e-05 | 4.5126e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.5794e-05 | 150.4306 | 150.4306 | 0%
Bay Area | EB_East Bay | SAN LEANDRO U 1109 | 1275 | BANCROFT 0402circuit_breaker | 5e-06 | 31.8078 | 3.5627 | 0 | 3.5627 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 1 | 103 |  | 21 | 14 | 103 | 21 | 14 | 38.04 | 1.5719e-07 | 0 | 2838 | 8.6008e-07 | 4.3004e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.6008e-07 | 5.8944 | 5.8944 | 0%
Central Valley | ST_Stockton | SALT SPRINGS 2101 | 5721 | SALT SPRINGS 21011232 | 0 | 103.7069 | 6.5333 | 0 | 6.5333 | 0 | 2129 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 1 | 3878 |  | 701 | 463 | 3878 | 701 | 463 | 1309.39 | 0 | 0 | 2839 | 3.7458e-05 | 4.1162e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.7458e-05 | 107.2959 | 107.2959 | 0%
Sierra | SI_Sierra | SUMMIT 1101 | 5537 | SUMMIT 110148636 | 0 | 10.9068 | 0.55379 | 0 | 0.55379 | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1 | 221 |  | 42 | 28 | 221 | 42 | 28 | 77.43 | 0 | 0 | 2840 | 8.2218e-07 | 4.1109e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 8.2218e-07 | 75.8413 | 75.8413 | 0%
Sierra | SI_Sierra | SUMMIT 1101 | 6917 | SUMMIT 1101742 | 0.002287 | 32.6181 | 1.3068 | 0 | 1.3068 | 0 | 339 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 1 | 628 |  | 115 | 77 | 628 | 115 | 77 | 214.07 | 7.0115e-05 | 2e-05 | 2841 | 3.1154e-06 | 3.8943e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.1154e-06 | 88 | 88 | 0%
Central Valley | ST_Stockton | SALT SPRINGS 2101 | 7826 | SALT SPRINGS 21013116 | 0 | 13.3607 | 0.67235 | 0 | 0.67235 | 0 | 523 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 1 | 962 |  | 175 | 117 | 962 | 175 | 117 | 326.33 | 0 | 0 | 2842 | 4.7914e-06 | 3.6857e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.7914e-06 | 260.2817 | 260.2817 | 0%
Sierra | SI_Sierra | TAMARACK 1101 | 5387 | TAMARACK 1101circuit_breaker | 0.000438 | 348.0056 | 16.8352 | 0 | 16.8352 | 0 | 6406 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 1 | 11645 |  | 2102 | 1386 | 11645 | 2102 | 1386 | 3927.79 | 1.2586e-06 | 1e-05 | 2843 | 6.6001e-05 | 3.5676e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 6.6001e-05 | 124.8572 | 124.8572 | 0%
Central Valley | ST_Stockton | SALT SPRINGS 2101 | 7363 | SALT SPRINGS 21014913 | 0 | 90.0219 | 4.7867 | 0 | 4.7867 | 0 | 2542 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 1 | 4628 |  | 837 | 552 | 4628 | 837 | 552 | 1563.21 | 0 | 0 | 2844 | 2.3974e-05 | 3.5256e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.3974e-05 | 174.858 | 174.858 | 0%
Sierra | SI_Sierra | SUMMIT 1101 | 6918 | SUMMIT 110158642 | 0 | 29.8011 | 1.6028 | 0 | 1.6028 | 0 | 431 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1 | 795 |  | 145 | 97 | 795 | 145 | 97 | 270.2 | 0 | 0 | 2845 | 4.2459e-06 | 3.2661e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 4.2459e-06 | 90.4644 | 90.4644 | 0%
North Valley | NV_North Valley | HAMILTON BRANCH 1101 | 2421 | HAMILTON BRANCH 110137436 | 0 | 12.7449 | 0.7428 | 0 | 0.7428 | 0 | 415 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 1 | 766 |  | 140 | 93 | 766 | 140 | 93 | 260.74 | 0 | 0 | 2846 | 2.5776e-06 | 3.2221e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 2.5776e-06 | 188.4753 | 188.4753 | 0%
Bay Area | PE_Peninsula | BELMONT 1110 | 1305 | BELMONT 111039182 | 2e-06 | 19.4564 | 0.059848 | 0 | 0.059848 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 21 |  | 6 | 5 | 21 | 6 | 5 | 10.11 | 1.0279e-07 | 0 | 2847 | 3.1284e-07 | 3.1284e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.1284e-07 | 100.2532 | 100.2532 | 0%
Central Valley | FR_Fresno | DUNLAP 1103 | 1985 | DUNLAP 11037170 | 0.000124 | 118.3391 | 5.0303 | 0 | 5.0303 | 0 | 2334 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 1 | 4251 |  | 769 | 507 | 4251 | 769 | 507 | 1436.12 | 1.0478e-06 | 0 | 2848 | 1.1943e-05 | 2.8436e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.1943e-05 | 152.8735 | 152.8735 | 0%
North Valley | NV_North Valley | CHESTER 1102 | 4747 | CHESTER 11022564 | 0 | 43.7796 | 2.05 | 0 | 2.05 | 0 | 740 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 1 | 1356 |  | 247 | 163 | 1356 | 247 | 163 | 460.43 | 0 | 0 | 2849 | 5.3991e-06 | 2.571e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 5.3991e-06 | 120.4878 | 120.4878 | 0%
Bay Area | PE_Peninsula | BELMONT 1103 | 4237 | BELMONT 11038956 | 1e-06 | 21.2663 | 0.23693 | 0 | 0.23693 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 49 |  | 11 | 8 | 49 | 11 | 8 | 19.48 | 4.7023e-08 | 0 | 2850 | 3.607e-07 | 1.8035e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.607e-07 | 46.4269 | 46.4269 | 0%
North Valley | NV_North Valley | CHESTER 1102 | 5682 | CHESTER 1102circuit_breaker | 0 | 10.4642 | 0.43845 | 0 | 0.43845 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1 | 94 |  | 19 | 13 | 94 | 19 | 13 | 34.49 | 0 | 0 | 2851 | 3.2158e-07 | 1.6079e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 3.2158e-07 | 43.3348 | 43.3348 | 0%
Central Valley | FR_Fresno | DUNLAP 1102 | 9477 | DUNLAP 11027290 | 0 | 15.0245 | 0.59375 | 0 | 0.59375 | 0 | 324 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1 | 601 |  | 110 | 74 | 601 | 110 | 74 | 204.79 | 0 | 0 | 2852 | 1.5997e-06 | 1.4543e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 1.5997e-06 | 185.2632 | 185.2632 | 0%
Central Coast | LP_Los Padres | OILFIELDS 1103 | 7447 | OILFIELDS 11032757 | 0.15535 | 57.3403 | 2.7598 | 2.7598 | 0 | 2.7598 | 29 | 114 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 114 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.0027093 | 0 | 2854 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0 | 100%
Central Valley | YO_Yosemite | SAN JOAQUIN NO3 1101 | 9068 | SAN JOAQUIN #3 1101circuit_breaker | 0.19562 | 92.2203 | 4.397 | 0 | 4.397 | 4.3902 | 598 | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 0.0015507 | 2 |  | 0 | 0 | 2 | 0 | 0 | 0.18 | 0.0021213 | 0 | 2856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0 | 0%
Bay Area | DI_Diablo | CLAYTON 2215 | 9393 | CLAYTON 22159765 | 0.073806 | 1.4744 | 0.34337 | 0 | 0.34337 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 34 |  | 8 | 6 | 34 | 8 | 6 | 14.02 | 0.05006 | 0.00083 | 2858 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 23.2984 | 23.2984 | 0%
Bay Area | NB_North Bay | CALISTOGA 1102 | 9758 | CALISTOGA 110266730 | 0.73835 | 20.8706 | 0.75019 | 0.54943 | 0.20076 | 0.75019 | 4 | 21 | 4 | 2 | 4 | 2 | 0 | 19 | 0 | 21 |  | 4 | 2 | 0 | 0 | 0 | 0 | 0.035378 | 0 | 2859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 5.332 | 73.24%
Sierra | SA_Sacramento | PEABODY 2106 | 7313 | PEABODY 2106circuit_breaker | 0.42677 | 15.9957 | 0.60701 | 0 | 0.60701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.02668 | 0.00022 | 2860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 6.5897 | 6.5897 | 0%
Central Valley | KE_Kern | POSO MOUNTAIN 2103 | 9400 | POSO MOUNTAIN 2103circuit_breaker | 0.48179 | 39.3054 | 2.2561 | 0 | 2.2561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.012258 | 0.0001 | 2862 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.773 | 1.773 | 0%
North Coast | SO_Sonoma | DUNBAR 1101 | 9410 | DUNBAR 110113481 | 0.000102 | 8.2505 | 0.37064 | 0 | 0.37064 | 0 | 26 | 6 | 5 | 3 | 5 | 3 | 0 | 14 | 1 | 65 |  | 18 | 12 | 59 | 13 | 9 | 23.12 | 1.2363e-05 | 0 | 2866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 35.0741 | 48.5641 | 0%
North Coast | SO_Sonoma | PETALUMA C 1108 | 8116 | PETALUMA C 1108636 | 13.5416 | 295.0215 | 10.0439 | 8.8241 | 1.2199 | 9.9848 | 322 | 586 | 189 | 42 | 159 | 28 | 0 | 368 | 0.0058832 | 590 |  | 190 | 42 | 4 | 31 | 14 | 42.83 | 0.0459 | 0.00296 | 2868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 25.4122 | 18.9169 | 87.85%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1107 | 7241 | SAN LUIS OBISPO 1107V58 | 0.018606 | 3.8265 | 0.27576 | 0 | 0.27576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.0048624 | 4e-05 | 2871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 14.5055 | 14.5055 | 0%
Sierra | SI_Sierra | CLARKSVILLE 2104 | 7133 | SHINGLE SPRINGS 210551738 | 4.0302 | 15.9722 | 0.55852 | 0.54432 | 0.014394 | 0.55852 | 6 | 39 | 14 | 11 | 14 | 11 | 0 | 35 | 0 | 39 |  | 14 | 11 | 0 | 0 | 0 | 0 | 0.25233 | 0 | 2872 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 25.0661 | 97.46%
Central Coast | LP_Los Padres | PASO ROBLES 1103 | 9937 | PASO ROBLES 1103N04 | 1.2119 | 12.3202 | 0.40246 | 0.40246 | 0 | 0.40246 | 6 | 21 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.098364 | 0 | 2873 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0 | 100%
Central Coast | CC_Central Coast | LOS OSITOS 2103 | 7745 | LOS OSITOS 21037062 | 0.025303 | 266.2779 | 11.9737 | 0 | 11.9737 | 0 | 179 | 0 | 0 | 0 | 0 | 0 | 0 | 172 | 1 | 337 |  | 63 | 42 | 337 | 63 | 42 | 116.64 | 9.5025e-05 | 1e-05 | 2883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 5.2615 | 5.2615 | 0%
North Coast | HU_Humboldt | COVELO 1101 | 7381 | COVELO 110137328 | 0.24462 | 73.8531 | 4.4646 | 0 | 4.4646 | 0 | 408 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 1 | 753 |  | 138 | 92 | 753 | 138 | 92 | 256.83 | 0.0033122 | 0.00095 | 2885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 30.9099 | 30.9099 | 0%
North Coast | SO_Sonoma | FORT ROSS 1121 | 7967 | FORT ROSS 1121204 | 6.8841 | 515.3105 | 18.7595 | 0 | 18.7595 | 0 | 3592 | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 1 | 6535 |  | 1181 | 779 | 6535 | 1181 | 779 | 2206.12 | 0.013359 | 0.03281 | 2890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 6. >50% | 3. >20 - 30% | 0 | 62.9549 | 62.9549 | 0%
North Coast | HU_Humboldt | WILLITS 1104 | 7180 | WILLITS 11021270 | 0.62015 | 9.423 | 0.51269 | 0.25436 | 0.25833 | 0.32348 | 41 | 59 | 12 | 3 | 9 | 3 | 0 | 28 | 0.36904 | 91 |  | 19 | 8 | 32 | 10 | 5 | 16.58 | 0.065812 | 0.00137 | 2891 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 38.7097 | 37.0595 | 49.61%
Central Coast | LP_Los Padres | OILFIELDS 1103 | 7357 | OILFIELDS 11035175 | 0.63416 | 49.1618 | 2.135 | 2.135 | 0 | 2.135 | 50 | 105 | 6 | 1 | 6 | 1 | 0 | 48 | 0 | 105 |  | 6 | 1 | 0 | 0 | 0 | 0 | 0.012899 | 0 | 2893 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 2.8103 | 100%
Central Coast | LP_Los Padres | GOLDTREE 1107 | 7326 | GOLDTREE 1107circuit_breaker | 0.076434 | 11.999 | 0.63106 | 0.63106 | 0 | 0.63106 | 13 | 39 | 9 | 2 | 9 | 2 | 0 | 11 | 0 | 39 |  | 9 | 2 | 0 | 0 | 0 | 0 | 0.00637 | 0 | 2895 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 14.2617 | 100%
Bay Area | DI_Diablo | BRENTWOOD 2105 | 8019 | BRENTWOOD 2105502672 | 1.1332 | 24.117 | 1.4078 | 0 | 1.4078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.04699 | 0.00039 | 2899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.8414 | 2.8414 | 0%
Central Coast | LP_Los Padres | SCE VEGAS 1701 | 9490 | circuit_breaker | 0.001148 | 4.5756 | 0.064583 | 0 | 0.064583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.0002509 | 0 | 2901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 61.9355 | 61.9355 | 0%
Central Valley | KE_Kern | ANTELOPE 1101 | 8702 | ANTELOPE 11011631 | 1.7109 | 46.2735 | 2.0398 | 0 | 2.0398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.036973 | 0.00031 | 2903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.961 | 1.961 | 0%
Central Valley | KE_Kern | SCE TEHACHAPI 1101 | 9662 | SCE TEHACHAPI 1101circuit_breaker | 0.11105 | 42.6604 | 1.4564 | 0 | 1.4564 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 1 | 30 |  | 7 | 6 | 30 | 7 | 6 | 12.29 | 0.002603 | 4e-05 | 2906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 4.8062 | 4.8062 | 0%
Sierra | SI_Sierra | BRUNSWICK 1104 | 7896 | BRUNSWICK 1110circuit_breaker | 2e-05 | 2.0002 | 0.045076 | 0 | 0.045076 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 40 |  | 9 | 7 | 40 | 9 | 7 | 15.93 | 9.999e-06 | 0 | 2907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 199.6639 | 199.6639 | 0%
North Valley | NV_North Valley | GLENN 1101 | 8272 | GLENN 11012012 | 0.78088 | 7.0053 | 2.3053 | 0 | 2.3053 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1 | 14 |  | 5 | 4 | 14 | 5 | 4 | 8.11 | 0.11147 | 0.00116 | 2908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.1689 | 2.1689 | 0%
North Valley | NV_North Valley | CORNING 1101 | 9502 | CORNING 110135974 | 0 | 0 | 0.087121 | 0.087121 | 0 | 0.087121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2909 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0 | 100%
North Valley | NV_North Valley | VOLTA 1101 | 8310 | VOLTA 1101circuit_breaker | 10.5301 | 197.1483 | 8.5434 | 0 | 8.5434 | 0 | 279 | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 1 | 519 |  | 96 | 64 | 519 | 96 | 64 | 178.23 | 0.053412 | 0.01066 | 2910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 4. >30 - 40% | 0 | 11.2368 | 11.2368 | 0%
North Coast | SO_Sonoma | PETALUMA C 1109 | 9519 | PETALUMA C 1109664732 | 0.47099 | 8.7754 | 0.35019 | 0 | 0.35019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.053672 | 0.00045 | 2913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 11.4224 | 11.4224 | 0%
Bay Area | NB_North Bay | IGNACIO 1105 | 7406 | 908 | 0.000285 | 17.6763 | 2.2606 | 0 | 2.2606 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | 1 | 72 |  | 15 | 11 | 72 | 15 | 11 | 27.03 | 1.6123e-05 | 0 | 2914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 6.6354 | 6.6354 | 0%
Central Coast | CC_Central Coast | JOLON 1102 | 7009 | JOLON 11027004 | 1.3796 | 127.1162 | 8.9848 | 0 | 8.9848 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 1 | 116 |  | 23 | 16 | 116 | 23 | 16 | 41.95 | 0.010853 | 0.00052 | 2915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.5599 | 2.5599 | 0%
Bay Area | MI_Mission | SAN RAMON 2103 | 9031 | SAN RAMON 2103MR279 | 0 | 0 | 0.023295 | 0 | 0.023295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 2917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 171.7073 | 171.7073 | 0%
Central Coast | CC_Central Coast | TRES PINOS 1111 | 7391 | TRES PINOS 11114032 | 5.7e-05 | 2.0005 | 0.067803 | 0 | 0.067803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 2.8492e-05 | 0 | 2919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 58.9944 | 58.9944 | 0%
Bay Area | MI_Mission | SAN RAMON 2101 | 8333 | SAN RAMON 2101circuit_breaker | 0.000954 | 0.45912 | 0.6 | 0 | 0.6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 23 |  | 6 | 5 | 23 | 6 | 5 | 10.29 | 0.0020779 | 3e-05 | 2920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 10 | 10 | 0%
North Coast | HU_Humboldt | COVELO 1101 | 7902 | COVELO 110196896 | 0.29015 | 81.4758 | 3.7807 | 0 | 3.7807 | 0 | 967 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 1 | 1768 |  | 321 | 212 | 1768 | 321 | 212 | 598.89 | 0.0035612 | 0.00238 | 2921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 84.9053 | 84.9053 | 0%
Central Coast | CC_Central Coast | LOS OSITOS 2103 | 9047 | LOS OSITOS 21037468 | 0.000443 | 15.0029 | 0.99356 | 0 | 0.99356 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 18 |  | 5 | 4 | 18 | 5 | 4 | 8.47 | 2.9528e-05 | 0 | 2922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 5.0324 | 5.0324 | 0%
Bay Area | MI_Mission | SAN RAMON 2101 | 9776 | SAN RAMON 2102circuit_breaker | 0.15799 | 29.1918 | 2.718 | 0 | 2.718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.0054122 | 5e-05 | 2926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.4717 | 1.4717 | 0%
Central Valley | KE_Kern | POSO MOUNTAIN 2101 | 9578 | POSO MOUNTAIN 21011703 | 0.041399 | 12.0031 | 1.2114 | 1.2114 | 0 | 1.2114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.003449 | 0 | 2931 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0 | 100%
North Coast | SO_Sonoma | CALPINE 1144 | 9864 | CALPINE 1144962 | 0.18207 | 74.4888 | 3.911 | 0.80682 | 3.1042 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 1 | 25 |  | 6 | 5 | 25 | 6 | 5 | 10.47 | 0.0024442 | 3e-05 | 2934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.9329 | 1.5341 | 20.63%
Central Coast | LP_Los Padres | PASO ROBLES 1107 | 7938 | PASO ROBLES 1107circuit_breaker | 1.9317 | 11.1035 | 0.64659 | 0 | 0.64659 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1 | 14 |  | 5 | 4 | 14 | 5 | 4 | 8.11 | 0.17397 | 0.00181 | 2941 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 6. >50% | 6. >50% | 0 | 7.7329 | 7.7329 | 0%
Central Coast | CC_Central Coast | JOLON 1102 | 8915 | JOLON 11027068 | 0.037476 | 66.8502 | 3.3265 | 0 | 3.3265 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 1 | 30 |  | 7 | 6 | 30 | 7 | 6 | 12.29 | 0.0005606 | 1e-05 | 2944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.1043 | 2.1043 | 0%
Bay Area | DI_Diablo | BRENTWOOD 2105 | 8920 | BRENTWOOD 21056512 | 0.009705 | 10.4709 | 0.046023 | 0 | 0.046023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.00092686 | 1e-05 | 2946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 86.9136 | 86.9136 | 0%
Central Coast | LP_Los Padres | CMC 1101 | 9347 | CMC 1101circuit_breaker | 0.059288 | 31.8456 | 1.4682 | 0 | 1.4682 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 1 | 36 |  | 8 | 6 | 36 | 8 | 6 | 14.2 | 0.0018617 | 3e-05 | 2949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 5.4489 | 5.4489 | 0%
Sierra | SA_Sacramento | MADISON 2101 | 7912 | MADISON 21011969 | 1.0383 | 11.7834 | 0.55587 | 0 | 0.55587 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1 | 63 |  | 13 | 10 | 63 | 13 | 10 | 23.48 | 0.088118 | 0.00238 | 2955 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 23.3867 | 23.3867 | 0%
Central Coast | LP_Los Padres | PALMER 1101 | 7305 | PALMER 1101M88 | 0.021427 | 39.7505 | 3.1873 | 0 | 3.1873 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 1 | 20 |  | 5 | 5 | 20 | 5 | 5 | 8.65 | 0.00053904 | 1e-05 | 2958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.5687 | 1.5687 | 0%
Central Coast | LP_Los Padres | OILFIELDS 1103 | 8129 | OILFIELDS 1103N40 | 0.74874 | 14.1404 | 0.85966 | 0.85966 | 0 | 0.85966 | 3 | 6 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.052951 | 0 | 2968 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0 | 100%
Bay Area | NB_North Bay | STAFFORD 1102 | 7848 | STAFFORD 1102361952 | 2.9923 | 25.1602 | 1.3 | 0 | 1.3 | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 1 | 205 |  | 39 | 27 | 205 | 39 | 27 | 71.88 | 0.11893 | 0.00965 | 2969 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0 | 30 | 30 | 0%
Bay Area | DI_Diablo | TASSAJARA 2112 | 9439 | TASSAJARA 21123202 | 0.1934 | 12.5389 | 0.2858 | 0 | 0.2858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.015424 | 0.00013 | 2974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 13.996 | 13.996 | 0%
Central Valley | KE_Kern | KERN OIL 1106 | 8654 | KERN OIL 110646960 | 0.1014 | 14.5173 | 1.1229 | 1.1229 | 0 | 1.1229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.0069845 | 0 | 2975 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0 | 100%
Bay Area | PE_Peninsula | RALSTON 1102 | 5737 | RALSTON 1102circuit_breaker | 0.002535 | 28.9206 | 0.29148 | 0 | 0.29148 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 29 |  | 7 | 6 | 29 | 7 | 6 | 12.2 | 8.7654e-05 | 0 | 2976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 24.0156 | 24.0156 | 0%
Bay Area | DI_Diablo | TASSAJARA 2109 | 5746 | TASSAJARA 2104circuit_breaker | 0.003201 | 2.5406 | 0.042424 | 0 | 0.042424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.00126 | 1e-05 | 2977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 94.2857 | 94.2857 | 0%
Central Coast | LP_Los Padres | OILFIELDS 1103 | 5900 | OILFIELDS 1103N64 | 0.61228 | 213.9863 | 9.8839 | 9.8388 | 0.045076 | 9.8839 | 66 | 328 | 16 | 1 | 16 | 1 | 0 | 270 | 0 | 328 |  | 16 | 1 | 0 | 0 | 0 | 0 | 0.0028613 | 0 | 2978 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 1.6188 | 99.54%
Central Coast | CC_Central Coast | GREEN VALLEY 2101 | 6335 | GREEN VALLEY 210112824 | 0.075406 | 6.0027 | 1.0426 | 0 | 1.0426 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 34 |  | 8 | 6 | 34 | 8 | 6 | 14.02 | 0.012562 | 0.00021 | 2979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 7.673 | 7.673 | 0%
Central Coast | LP_Los Padres | OILFIELDS 1103 | 6911 | OILFIELDS 1103N42 | 0.82401 | 60.2949 | 3.6549 | 3.6549 | 0 | 3.6549 | 8 | 18 | 2 | 1 | 2 | 1 | 0 | 63 | 0 | 18 |  | 2 | 1 | 0 | 0 | 0 | 0 | 0.013666 | 0 | 2980 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0.54721 | 100%
North Coast | HU_Humboldt | EEL RIVER 1102 | 5861 | EEL RIVER 110249130 | 0.009538 | 56.4457 | 1.6991 | 0.094697 | 1.6042 | 1.6991 | 715 | 2819 | 809 | 570 | 11 | 9 | 0 | 35 | 0 | 2819 |  | 809 | 570 | 0 | 798 | 561 | 1093.26 | 0.00016898 | 0.00028 | 2982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 497.4545 | 476.1476 | 5.574%
Bay Area | EB_East Bay | FRANKLIN 1104 | 4873 | FRANKLIN 1104circuit_breaker | 0 | 3.6486 | 0.74943 | 0 | 0.74943 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1 | 20 |  | 5 | 5 | 20 | 5 | 5 | 8.65 | 0 | 0 | 2984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 6.6717 | 6.6717 | 0%
Bay Area | NB_North Bay | STAFFORD 1102 | 6212 | STAFFORD 11021048 | 0.29695 | 112.1239 | 4.0206 | 0 | 4.0206 | 0 | 481 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 1 | 886 |  | 162 | 107 | 886 | 162 | 107 | 301.68 | 0.0026484 | 0.00089 | 2985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 40.2921 | 40.2921 | 0%
Central Valley | ST_Stockton | STANISLAUS 1702 | 5126 | STANISLAUS 1702L611 | 0.01937 | 47.1871 | 2.4809 | 0.18163 | 2.2992 | 2.4625 | 1673 | 972 | 286 | 133 | 267 | 114 | 0 | 136 | 0.0074051 | 995 |  | 290 | 136 | 23 | 23 | 22 | 33.58 | 0.00041049 | 2e-05 | 2987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 10.0033 | 116.8944 | 7.321%
Central Valley | FR_Fresno | OROSI 1102 | 5152 | OROSI 11027948F | 0.009668 | 9.979 | 1.0402 | 0 | 1.0402 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 36 |  | 8 | 6 | 36 | 8 | 6 | 14.2 | 0.00096884 | 2e-05 | 2988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 7.6912 | 7.6912 | 0%
Central Valley | KE_Kern | LAMONT 1102 | 6633 | LAMONT 11024222 | 0.18065 | 24.4755 | 2.3277 | 0 | 2.3277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.007381 | 6e-05 | 2989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.7185 | 1.7185 | 0%
Central Coast | LP_Los Padres | MORRO BAY 1102 | 5482 | MORRO BAY 1102V80 | 3e-06 | 0.79199 | 0.16515 | 0 | 0.16515 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 52 |  | 11 | 8 | 52 | 11 | 8 | 19.75 | 3.7879e-06 | 0 | 2992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 66.6055 | 66.6055 | 0%
Sierra | SA_Sacramento | MADISON 1105 | 5253 | MADISON 11057712 | 0.10648 | 8.9764 | 0.57008 | 0 | 0.57008 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 20 |  | 5 | 5 | 20 | 5 | 5 | 8.65 | 0.011862 | 0.00012 | 2994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 8.7708 | 8.7708 | 0%
North Coast | HU_Humboldt | POINT ARENA 1101 | 6226 | POINT ARENA 11013702 | 0.83672 | 93.7553 | 4.7879 | 0 | 4.7879 | 0 | 531 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1 | 977 |  | 178 | 118 | 977 | 178 | 118 | 331.79 | 0.0089245 | 0.0033 | 2995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 37.1772 | 37.1772 | 0%
Central Valley | YO_Yosemite | WESTLEY 1103 | 4593 | WESTLEY 11039010 | 0.02192 | 13.003 | 34.5241 | 0 | 34.5241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.0016858 | 1e-05 | 2996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.11586 | 0.11586 | 0%
Central Coast | SJ_San Jose | HICKS 2103 | 6387 | HICKS 2103XR248 | 3e-06 | 3.0816 | 0.086932 | 0 | 0.086932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 9.7352e-07 | 0 | 2997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 46.0131 | 46.0131 | 0%
Central Valley | ST_Stockton | MARTELL 1102 | 6444 | MARTELL 110292172 | 0.018429 | 9.495 | 0.25682 | 0 | 0.25682 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 52 |  | 11 | 8 | 52 | 11 | 8 | 19.75 | 0.0019409 | 4e-05 | 2998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 42.8319 | 42.8319 | 0%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1104 | 4723 | OCEANO 1105V48 | 2e-06 | 9.4608 | 0.48598 | 0 | 0.48598 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1 | 14 |  | 5 | 4 | 14 | 5 | 4 | 8.11 | 2.114e-07 | 0 | 2999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 10.2884 | 10.2884 | 0%
North Coast | HU_Humboldt | FORT BRAGG A 1102 | 6003 | FORT BRAGG A 110233064 | 2e-05 | 3.8642 | 0.16553 | 0 | 0.16553 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 38 |  | 9 | 7 | 38 | 9 | 7 | 15.75 | 5.1757e-06 | 0 | 3004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 54.3707 | 54.3707 | 0%
North Valley | NV_North Valley | MC ARTHUR 1101 | 5100 | MC ARTHUR 110137344 | 0.051062 | 13.4297 | 0.77519 | 0 | 0.77519 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1 | 34 |  | 8 | 6 | 34 | 8 | 6 | 14.02 | 0.0038022 | 6e-05 | 3007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 10.3201 | 10.3201 | 0%
Central Valley | FR_Fresno | TIVY VALLEY 1107 | 5604 | TIVY VALLEY 110737522 | 0.10772 | 14.482 | 0.50777 | 0.50777 | 0 | 0.50777 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.007438 | 0 | 3008 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0 | 100%
Central Coast | SJ_San Jose | EDENVALE 2113 | 5908 | EDENVALE 2113circuit_breaker | 0 | 0 | 1.6237 | 0 | 1.6237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 3009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.4635 | 2.4635 | 0%
Central Coast | SJ_San Jose | SWIFT 2107 | 5528 | SWIFT 2107XR526 | 0.47094 | 61.3942 | 2.8333 | 0 | 2.8333 | 0 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1 | 245 |  | 46 | 31 | 245 | 46 | 31 | 85.07 | 0.0076708 | 0.00073 | 3010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 16.2353 | 16.2353 | 0%
North Coast | SO_Sonoma | PETALUMA C 1108 | 5514 | PETALUMA C 1108628 | 15.8017 | 284.2182 | 7.8871 | 6.8292 | 1.0578 | 7.8871 | 307 | 634 | 217 | 143 | 196 | 134 | 0 | 280 | 0 | 634 |  | 217 | 143 | 0 | 21 | 9 | 28.77 | 0.055597 | 0.00243 | 3011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 19.8532 | 27.5132 | 86.59%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1104 | 5181 | SAN LUIS OBISPO 1104circuit_breaker | 0.064038 | 33.8449 | 0.94527 | 0 | 0.94527 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 1 | 79 |  | 16 | 12 | 79 | 16 | 12 | 29.03 | 0.0018921 | 6e-05 | 3013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 16.9265 | 16.9265 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1109 | 4622 | SAN RAFAEL 110668694 | 9e-06 | 5.1995 | 0.11629 | 0 | 0.11629 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 25 |  | 6 | 5 | 25 | 6 | 5 | 10.47 | 1.7309e-06 | 0 | 3015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 51.5961 | 51.5961 | 0%
Bay Area | PE_Peninsula | SNEATH LANE 1102 | 2596 | SNEATH LANE 11061339 | 1e-06 | 11.1616 | 1.6809 | 0 | 1.6809 | 0 | 265 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 1 | 494 |  | 91 | 61 | 494 | 91 | 61 | 169.13 | 8.9593e-08 | 0 | 3016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 54.1386 | 54.1386 | 0%
North Coast | HU_Humboldt | EEL RIVER 1102 | 2444 | EEL RIVER 1102530 | 0.1307 | 114.2032 | 5.0186 | 1.8854 | 3.1331 | 5.0186 | 2256 | 5240 | 1688 | 1057 | 399 | 282 | 0 | 123 | 0 | 5240 |  | 1688 | 1057 | 0 | 1289 | 775 | 1765.93 | 0.0011445 | 0.00307 | 3017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 411.4078 | 336.3514 | 37.57%
Central Coast | LP_Los Padres | OILFIELDS 1103 | 3390 | OILFIELDS 11037006 | 0.37679 | 72.2716 | 4.3367 | 4.3367 | 0 | 4.3367 | 29 | 48 | 1 | 0 | 1 | 0 | 0 | 108 | 0 | 48 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0.0052135 | 0 | 3018 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0.23059 | 100%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1105 | 2676 | SAN LUIS OBISPO 1101592368 | 2e-06 | 1.5059 | 0.26288 | 0 | 0.26288 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 56 |  | 12 | 9 | 56 | 12 | 9 | 21.48 | 1.3281e-06 | 0 | 3019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 45.6484 | 45.6484 | 0%
Bay Area | DI_Diablo | KIRKER 2104 | 3048 | KIRKER 2104circuit_breaker | 0.072485 | 7.3402 | 0.16439 | 0 | 0.16439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.0098751 | 8e-05 | 3020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 24.3318 | 24.3318 | 0%
North Coast | SO_Sonoma | SONOMA 1104 | 4130 | SONOMA 1104914376 | 5.7e-05 | 10.9399 | 0.38201 | 0 | 0.38201 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 32 |  | 8 | 6 | 32 | 8 | 6 | 13.84 | 5.2103e-06 | 0 | 3021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 20.942 | 20.942 | 0%
Central Coast | DA_De Anza | SARATOGA 1105 | 3647 | SARATOGA 1103LC82 | 0 | 0 | 0.033523 | 0 | 0.033523 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 16 |  | 5 | 4 | 16 | 5 | 4 | 8.29 | 0 | 0 | 3022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 149.1525 | 149.1525 | 0%
Central Coast | DA_De Anza | SARATOGA 1103 | 3019 | SARATOGA 1103LC40 | 4e-06 | 4.4721 | 0.29432 | 0 | 0.29432 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 63 |  | 13 | 10 | 63 | 13 | 10 | 23.48 | 8.9444e-07 | 0 | 3023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 44.1699 | 44.1699 | 0%
North Coast | SO_Sonoma | SONOMA 1105 | 4309 | SONOMA 1105138 | 0.026601 | 16.8365 | 1.1754 | 0 | 1.1754 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 25 |  | 6 | 5 | 25 | 6 | 5 | 10.47 | 0.00158 | 2e-05 | 3024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 5.1047 | 5.1047 | 0%
Central Coast | LP_Los Padres | GOLDTREE 1108 | 2720 | GOLDTREE 1108circuit_breaker | 1.5375 | 62.128 | 2.4881 | 0.42292 | 2.0652 | 0.42292 | 63 | 34 | 6 | 6 | 6 | 6 | 0 | 49 | 0.83002 | 139 |  | 27 | 20 | 105 | 21 | 14 | 38.22 | 0.024748 | 0.00108 | 3025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 10.1687 | 10.8518 | 17%
Bay Area | DI_Diablo | WILLOW PASS 2108 | 2831 | WILLOW PASS 2108circuit_breaker | 0.096052 | 3.7268 | 0.10208 | 0 | 0.10208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.025773 | 0.00021 | 3026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 39.1837 | 39.1837 | 0%
Bay Area | EB_East Bay | VALLEY VIEW 1105 | 2715 | VALLEY VIEW 1105P124 | 0 | 2.8214 | 0.086553 | 0 | 0.086553 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 20 |  | 5 | 5 | 20 | 5 | 5 | 8.65 | 0 | 0 | 3028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 57.7681 | 57.7681 | 0%
Central Valley | KE_Kern | KERN OIL 1106 | 3577 | KERN OIL 11063301 | 0.028659 | 7.7382 | 0.83655 | 0.68333 | 0.15322 | 0.68333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0.18316 | 2 |  | 1 | 1 | 2 | 1 | 1 | 1.55 | 0.0037036 | 1e-05 | 3029 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 6.5266 | 1.1954 | 81.68%
Central Valley | KE_Kern | POSO MOUNTAIN 2101 | 4467 | POSO MOUNTAIN 2101circuit_breaker | 0.97777 | 107.836 | 5.1216 | 4.8009 | 0.32083 | 4.8009 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 0.062606 | 1 |  | 0 | 0 | 1 | 0 | 0 | 0.09 | 0.0090672 | 0 | 3030 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0 | 93.74%
Bay Area | NB_North Bay | MONTICELLO 1101 | 3225 | MONTICELLO 11011589 | 1.0036 | 101.905 | 5.2902 | 0 | 5.2902 | 0 | 962 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 1 | 1759 |  | 319 | 211 | 1759 | 319 | 211 | 595.34 | 0.009848 | 0.00653 | 3032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 5. >40 - 50% | 0 | 60.3007 | 60.3007 | 0%
Central Coast | CC_Central Coast | GABILAN 1101 | 4117 | GABILAN 11013722 | 1.5e-05 | 14.3141 | 0.76061 | 0 | 0.76061 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 18 |  | 5 | 4 | 18 | 5 | 4 | 8.47 | 1.0479e-06 | 0 | 3033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 6.5737 | 6.5737 | 0%
Sierra | SI_Sierra | BRUNSWICK 1103 | 4154 | BRUNSWICK 110378862 | 5.4e-05 | 31.9722 | 1.1062 | 0 | 1.1062 | 0 | 877 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 1 | 1605 |  | 291 | 193 | 1605 | 291 | 193 | 543.12 | 1.689e-06 | 0 | 3034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 263.0508 | 263.0508 | 0%
Central Coast | CC_Central Coast | LOS OSITOS 2103 | 3874 | LOS OSITOS 21037082 | 0.004518 | 38.5575 | 1.7708 | 0 | 1.7708 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 1 | 58 |  | 12 | 9 | 58 | 12 | 9 | 21.66 | 0.00011718 | 0 | 3035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 6.7765 | 6.7765 | 0%
North Coast | SO_Sonoma | PETALUMA C 1109 | 3835 | PETALUMA C 1109circuit_breaker | 0.16529 | 38.8703 | 1.3527 | 0 | 1.3527 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 1 | 141 |  | 27 | 19 | 141 | 27 | 19 | 49.68 | 0.0042525 | 0.00024 | 3036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 19.9608 | 19.9608 | 0%
Bay Area | NB_North Bay | ALTO 1122 | 2626 | GREENBRAE 11037315 | 2e-06 | 3.0562 | 0.030492 | 0 | 0.030492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 6.5441e-07 | 0 | 3037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 131.1801 | 131.1801 | 0%
Central Coast | CC_Central Coast | VIEJO 2201 | 4373 | VIEJO 22019704 | 1e-06 | 1.3907 | 0.04678 | 0 | 0.04678 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 49 |  | 11 | 8 | 49 | 11 | 8 | 19.48 | 7.1906e-07 | 0 | 3038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 235.1417 | 235.1417 | 0%
Central Coast | CC_Central Coast | JOLON 1102 | 2673 | JOLON 11027002 | 0.11329 | 185.934 | 7.7564 | 0 | 7.7564 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1 | 121 |  | 24 | 17 | 121 | 24 | 17 | 43.77 | 0.00060932 | 3e-05 | 3039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 3.0942 | 3.0942 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2101 | 3532 | GREEN VALLEY 210190860 | 0.00624 | 55.7982 | 3.3741 | 0 | 3.3741 | 0 | 401 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 1 | 740 |  | 136 | 90 | 740 | 136 | 90 | 252.92 | 0.00011183 | 3e-05 | 3041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 40.3076 | 40.3076 | 0%
Central Valley | KE_Kern | ARVIN 1101 | 2578 | ARVIN 110194892 | 0.049862 | 2.9917 | 0.29451 | 0 | 0.29451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.016667 | 0.00014 | 3042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 13.582 | 13.582 | 0%
North Valley | NV_North Valley | COTTONWOOD 1103 | 3767 | COTTONWOOD 1103circuit_breaker | 1.1255 | 17.2897 | 0.91742 | 0.91742 | 0 | 0.91742 | 3 | 3 | 1 | 1 | 1 | 1 | 0 | 20 | 0 | 3 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0.065097 | 0 | 3044 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 1.09 | 100%
Bay Area | MI_Mission | SAN RAMON 2119 | 4316 | SAN RAMON 2119circuit_breaker | 0.003058 | 8.4422 | 0.1053 | 0 | 0.1053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.00036223 | 0 | 3045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 37.9856 | 37.9856 | 0%
North Coast | HU_Humboldt | FORT BRAGG A 1104 | 3286 | FORT BRAGG A 110436526 | 1e-05 | 9.4845 | 0.37102 | 0 | 0.37102 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1 | 98 |  | 20 | 14 | 98 | 20 | 14 | 36.22 | 1.0544e-06 | 0 | 3046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 53.9051 | 53.9051 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1106 | 3602 | LAS GALLINAS A 1107554 | 3e-06 | 2.4469 | 0.10284 | 0 | 0.10284 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 61 |  | 13 | 10 | 61 | 13 | 10 | 23.3 | 1.226e-06 | 0 | 3047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 126.4088 | 126.4088 | 0%
North Coast | SO_Sonoma | SONOMA 1107 | 3576 | SONOMA 1107294 | 0.011282 | 3.7469 | 0.19432 | 0 | 0.19432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.003011 | 3e-05 | 3048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 20.5848 | 20.5848 | 0%
North Coast | SO_Sonoma | PETALUMA C 1108 | 3036 | PETALUMA C 1108630 | 2.7586 | 42.8553 | 1.521 | 1.0364 | 0.48466 | 1.521 | 151 | 241 | 104 | 47 | 96 | 41 | 0 | 65 | 0 | 241 |  | 104 | 47 | 0 | 8 | 6 | 10.96 | 0.064371 | 0.00107 | 3049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 16.5064 | 68.375 | 68.14%
North Valley | NV_North Valley | WYANDOTTE 1109 | 4206 | WYANDOTTE 11095973 | 0.055961 | 5.3501 | 0.20966 | 0 | 0.20966 | 0 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1 | 283 |  | 53 | 36 | 283 | 53 | 36 | 98.08 | 0.01046 | 0.00115 | 3050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 252.7913 | 252.7913 | 0%
Central Coast | LP_Los Padres | CAYUCOS 1101 | 2554 | CAYUCOS 11014701 | 0.045194 | 23.2215 | 0.88807 | 0 | 0.88807 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 45 |  | 10 | 8 | 45 | 10 | 8 | 17.75 | 0.0019462 | 4e-05 | 3051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 11.2604 | 11.2604 | 0%
North Coast | SO_Sonoma | PETALUMA C 1108 | 1981 | PETALUMA C 1108296 | 27.7996 | 433.0467 | 15.3883 | 12.6659 | 2.7223 | 15.153 | 866 | 1167 | 528 | 285 | 377 | 251 | 1 | 481 | 0.015286 | 1191 |  | 532 | 288 | 24 | 155 | 37 | 214.51 | 0.064195 | 0.02069 | 3052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 3. >20 - 30% | 0 | 56.9361 | 34.5718 | 82.31%
Bay Area | DI_Diablo | LAKEWOOD 2110 | 1629 | LAKEWOOD 2224W544R | 0 | 0.30486 | 2.7705 | 0 | 2.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 3053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.4438 | 1.4438 | 0%
North Coast | HU_Humboldt | FORT BRAGG A 1101 | 1196 | FORT BRAGG A 1101circuit_breaker | 3e-06 | 1.0069 | 0.085227 | 0 | 0.085227 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 29 |  | 7 | 6 | 29 | 7 | 6 | 12.2 | 2.9796e-06 | 0 | 3054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 82.1333 | 82.1333 | 0%
Central Coast | CC_Central Coast | HATTON 1102 | 461 | VIEJO 22039094 | 0 | 2.7153 | 0.21799 | 0 | 0.21799 | 0.076515 | 13 | 15 | 4 | 4 | 1 | 1 | 0 | 9 | 0.649 | 38 |  | 9 | 8 | 23 | 8 | 7 | 13.03 | 0 | 0 | 3055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 36.6985 | 41.2858 | 0%
North Coast | SO_Sonoma | SANTA ROSA A 1108 | 246 | SANTA ROSA A 1108626 | 0.008691 | 3.4602 | 0.14564 | 0 | 0.14564 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 52 |  | 11 | 8 | 52 | 11 | 8 | 19.75 | 0.0025117 | 6e-05 | 3057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 75.5267 | 75.5267 | 0%
Central Coast | LP_Los Padres | OILFIELDS 1103 | 2087 | OILFIELDS 1103N44 | 4.4299 | 388.3502 | 17.5369 | 16.9138 | 0.6233 | 17.5369 | 215 | 558 | 21 | 3 | 21 | 3 | 0 | 411 | 0 | 558 |  | 21 | 3 | 0 | 0 | 0 | 0 | 0.011407 | 0 | 3058 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 1.1975 | 96.45%
Central Coast | LP_Los Padres | OILFIELDS 1103 | 1007 | OILFIELDS 110383158 | 3.156 | 337.2598 | 16.0314 | 16.0314 | 0 | 16.0314 | 106 | 252 | 7 | 0 | 7 | 0 | 0 | 383 | 0 | 252 |  | 7 | 0 | 0 | 0 | 0 | 0 | 0.0093577 | 0 | 3059 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0.43664 | 100%
Central Coast | SJ_San Jose | EDENVALE 2107 | 1192 | EDENVALE 2107circuit_breaker | 0.032682 | 5.0025 | 0.34602 | 0 | 0.34602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.0065331 | 5e-05 | 3060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 11.5599 | 11.5599 | 0%
North Coast | SO_Sonoma | PETALUMA C 1108 | 384 | PETALUMA C 110856774 | 6e-06 | 4.3781 | 0.30568 | 0.13845 | 0.16742 | 0.21061 | 7 | 36 | 8 | 0 | 6 | 0 | 0 | 17 | 0.31103 | 44 |  | 10 | 2 | 8 | 4 | 2 | 6.2 | 1.3704e-06 | 0 | 3063 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 23.8914 | 32.7138 | 45.29%
North Coast | HU_Humboldt | COVELO 1101 | 1370 | COVELO 1101562360 | 5.7814 | 65.6973 | 2.8504 | 0 | 2.8504 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 1 | 441 |  | 81 | 55 | 441 | 81 | 55 | 150.66 | 0.088001 | 0.01482 | 3064 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 4. >30 - 40% | 0 | 28.4173 | 28.4173 | 0%
Central Coast | LP_Los Padres | CABRILLO 1103 | 657 | CABRILLO 1103circuit_breaker | 0.012309 | 5.6352 | 0.45739 | 0 | 0.45739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.0021843 | 2e-05 | 3065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 8.7453 | 8.7453 | 0%
North Coast | SO_Sonoma | SONOMA 1104 | 873 | SONOMA 1104414 | 2.7855 | 29.0219 | 1.2769 | 0 | 1.2769 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 1 | 49 |  | 11 | 8 | 49 | 11 | 8 | 19.48 | 0.095981 | 0.0022 | 3066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 8.6147 | 8.6147 | 0%
North Valley | NV_North Valley | LOS MOLINOS 1101 | 1372 | LOS MOLINOS 11011308 | 0.62694 | 6.0038 | 0.40133 | 0 | 0.40133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.10442 | 0.00087 | 3067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 9.967 | 9.967 | 0%
Central Coast | CC_Central Coast | PAUL SWEET 2102 | 1587 | PAUL SWEET 210510290 | 3.1e-05 | 14.5981 | 0.57595 | 0 | 0.57595 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 52 |  | 11 | 8 | 52 | 11 | 8 | 19.75 | 2.1236e-06 | 0 | 3068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 19.099 | 19.099 | 0%
North Coast | SO_Sonoma | SONOMA 1105 | 1298 | SONOMA 11054456 | 0.18742 | 46.1803 | 1.9998 | 0 | 1.9998 | 0 | 179 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 1 | 337 |  | 63 | 42 | 337 | 63 | 42 | 116.64 | 0.0040585 | 0.00053 | 3069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 31.503 | 31.503 | 0%
Bay Area | EB_East Bay | OAKLAND J 1116 | 504 | OAKLAND J 1116circuit_breaker | 0 | 0.28895 | 19.0066 | 0 | 19.0066 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1329 | 1 | 16 |  | 5 | 4 | 16 | 5 | 4 | 8.29 | 0 | 0 | 3070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.26307 | 0.26307 | 0%
Central Coast | SJ_San Jose | MILPITAS 1108 | 401 | MILPITAS 1108XR122 | 0.004548 | 1.0005 | 0.074242 | 0 | 0.074242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.0045455 | 4e-05 | 3071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 53.8776 | 53.8776 | 0%
North Valley | NV_North Valley | BIG MEADOWS 2101 | 1657 | BIG MEADOWS 21012016 | 0 | 0 | 0.28977 | 0 | 0.28977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 3072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 13.8039 | 13.8039 | 0%
Central Coast | CC_Central Coast | GONZALES 1104 | 1383 | GONZALES 110422418 | 0.00421 | 13.9802 | 1.2182 | 0 | 1.2182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.00030114 | 0 | 3074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 3.2836 | 3.2836 | 0%
Central Coast | CC_Central Coast | LOS COCHES 1101 | 1606 | LOS COCHES 1101circuit_breaker | 0.000997 | 46.1809 | 2.3867 | 0 | 2.3867 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1 | 194 |  | 37 | 25 | 194 | 37 | 25 | 68.15 | 2.1589e-05 | 0 | 3075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 15.5023 | 15.5023 | 0%
Bay Area | NB_North Bay | IGNACIO 1105 | 1457 | STAFFORD 11021258 | 0.006087 | 7.8092 | 2.093 | 0 | 2.093 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 1 | 76 |  | 16 | 11 | 76 | 16 | 11 | 28.76 | 0.00077946 | 3e-05 | 3076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 7.6446 | 7.6446 | 0%
Central Coast | LP_Los Padres | PASO ROBLES 1103 | 11 | PASO ROBLES 1103N50 | 1.361 | 53.8923 | 2.0778 | 2.0778 | 0 | 2.0778 | 27 | 79 | 8 | 7 | 8 | 7 | 0 | 33 | 0 | 79 |  | 8 | 7 | 0 | 0 | 0 | 0 | 0.025253 | 0 | 3077 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 3.8502 | 100%
North Coast | HU_Humboldt | EEL RIVER 1103 | 1267 | EEL RIVER 1103circuit_breaker | 1.6e-05 | 4.3126 | 0.13371 | 0.061174 | 0.072538 | 0.13371 | 17 | 29 | 13 | 8 | 9 | 4 | 0 | 2 | 0 | 29 |  | 13 | 8 | 0 | 4 | 4 | 5.48 | 3.71e-06 | 0 | 3078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 55.1436 | 97.2238 | 45.75%
Sierra | SI_Sierra | PENRYN 1106 | 6792 | DEL MAR 210584138 | 0.57231 | 5.7068 | 0.24564 | 0 | 0.24564 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 65 |  | 14 | 10 | 65 | 14 | 10 | 25.03 | 0.10029 | 0.00292 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 56.9931 | 56.9931 | 0%
Central Coast | LP_Los Padres | SANTA YNEZ 1102 | 270 | SANTA YNEZ 1101circuit_breaker | 0.77405 | 5.4923 | 0.35739 | 0.031629 | 0.32576 | 0.031629 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0.9115 | 23 |  | 6 | 5 | 23 | 6 | 5 | 10.29 | 0.14093 | 0.00176 | 999999 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 6. >50% | 6. >50% | 0 | 18.4186 | 16.7886 | 8.85%
North Coast | SO_Sonoma | COTATI 1103 | 8704 | COTATI 1103310 | 0.024949 | 0.41451 | 0.20114 | 0 | 0.20114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.060189 | 0.0005 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 19.887 | 19.887 | 0%
Central Coast | LP_Los Padres | SANTA YNEZ 1104 | 5558 | SANTA YNEZ 110488746 | 0.04671 | 0.99902 | 0.11212 | 0 | 0.11212 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 20 |  | 5 | 5 | 20 | 5 | 5 | 8.65 | 0.046756 | 0.00049 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 44.5946 | 44.5946 | 0%
Central Coast | LP_Los Padres | OCEANO 1106 | 1053 | OCEANO 1103circuit_breaker | 0.040615 | 0.99964 | 0.36742 | 0 | 0.36742 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 18 |  | 5 | 4 | 18 | 5 | 4 | 8.47 | 0.04063 | 0.00042 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 13.6082 | 13.6082 | 0%
Central Coast | LP_Los Padres | OCEANO 1102 | 7023 | MESA 1103M68 | 0.038945 | 12.5274 | 0.88201 | 0 | 0.88201 | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 292 |  | 55 | 37 | 292 | 55 | 37 | 101.63 | 0.0031088 | 0.00036 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 62.3577 | 62.3577 | 0%
Sierra | SA_Sacramento | VACAVILLE 1104 | 624 | VACAVILLE 1103circuit_breaker | 0.14663 | 8.8586 | 0.42765 | 0 | 0.42765 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 34 |  | 8 | 6 | 34 | 8 | 6 | 14.02 | 0.016552 | 0.00028 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 18.7068 | 18.7068 | 0%
North Coast | SO_Sonoma | PETALUMA C 1108 | 1288 | PETALUMA C 1108circuit_breaker | 0.38794 | 17.7451 | 0.26742 | 0.18201 | 0.085417 | 0.26742 | 12 | 50 | 10 | 0 | 6 | 0 | 0 | 22 | 0 | 50 |  | 10 | 0 | 0 | 4 | 0 | 5.48 | 0.021862 | 0.00018 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 46.8293 | 37.3938 | 68.06%
Bay Area | DI_Diablo | BRENTWOOD 2105 | 4792 | BRENTWOOD 210598606 | 0.14937 | 10.1187 | 0.16951 | 0 | 0.16951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0.014762 | 0.00012 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 23.5978 | 23.5978 | 0%
Central Coast | LP_Los Padres | ATASCADERO 1102 | 1483 | ATASCADERO 1102circuit_breaker | 0.025247 | 15.3024 | 1.0324 | 0 | 1.0324 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 1 | 128 |  | 25 | 17 | 128 | 25 | 17 | 45.77 | 0.0016499 | 9e-05 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 24.2157 | 24.2157 | 0%
Central Valley | YO_Yosemite | COARSEGOLD 2103 | 8238 | COARSEGOLD 210310300 | 0.042031 | 8.1809 | 0.17955 | 0 | 0.17955 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 34 |  | 8 | 6 | 34 | 8 | 6 | 14.02 | 0.0051377 | 9e-05 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 44.557 | 44.557 | 0%
Sierra | SI_Sierra | HORSESHOE 1104 | 3039 | HORSESHOE 1104circuit_breaker | 0.020149 | 7.6263 | 0.19545 | 0 | 0.19545 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 74 |  | 15 | 11 | 74 | 15 | 11 | 27.21 | 0.002642 | 8e-05 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 76.7442 | 76.7442 | 0%
Central Coast | LP_Los Padres | ATASCADERO 1103 | 2800 | ATASCADERO 1103A80 | 0.02281 | 3.501 | 0.16553 | 0 | 0.16553 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 16 |  | 5 | 4 | 16 | 5 | 4 | 8.29 | 0.0065153 | 7e-05 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 30.2059 | 30.2059 | 0%
Central Coast | LP_Los Padres | BUELLTON 1101 | 1455 | BUELLTON 1101circuit_breaker | 0.017842 | 1.5228 | 0.30246 | 0.10095 | 0.20152 | 0.10095 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0.66625 | 11 |  | 3 | 3 | 11 | 3 | 3 | 5.1 | 0.011716 | 7e-05 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 14.8872 | 9.9186 | 33.38%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1102 | 2387 | SAN LUIS OBISPO 1102V96 | 0.10312 | 23.3661 | 0.8089 | 0 | 0.8089 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 18 |  | 5 | 4 | 18 | 5 | 4 | 8.47 | 0.0044133 | 5e-05 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 6.1812 | 6.1812 | 0%
Central Coast | SJ_San Jose | MILPITAS 1105 | 5522 | MILPITAS 1105circuit_breaker | 0.00364 | 1.0006 | 0.2 | 0 | 0.2 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 21 |  | 6 | 5 | 21 | 6 | 5 | 10.11 | 0.003638 | 5e-05 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 30 | 30 | 0%
Central Valley | YO_Yosemite | OAKHURST 1101 | 7730 | OAKHURST 110311900 | 0.008734 | 28.0903 | 1.9153 | 0.75246 | 1.1629 | 1.0598 | 218 | 325 | 120 | 36 | 74 | 24 | 0 | 86 | 0.44665 | 507 |  | 154 | 59 | 182 | 80 | 35 | 125.98 | 0.00031093 | 5e-05 | 999999 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 68.7948 | 80.4034 | 39.29%
Sierra | SA_Sacramento | VACAVILLE 1111 | 1729 | VACAVILLE 1108circuit_breaker | 0.012245 | 4.8816 | 0.30284 | 0.18333 | 0.11951 | 0.21364 | 29 | 54 | 11 | 6 | 5 | 4 | 0 | 11 | 0.29456 | 73 |  | 15 | 9 | 19 | 10 | 5 | 15.41 | 0.0025084 | 5e-05 | 999999 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 83.6767 | 49.531 | 60.54%
Bay Area | NB_North Bay | BOLINAS 1101 | 3815 | BOLINAS 110146152 | 0.001805 | 1.7738 | 0.13201 | 0 | 0.13201 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 83 |  | 17 | 12 | 83 | 17 | 12 | 30.76 | 0.0010176 | 4e-05 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 128.7805 | 128.7805 | 0%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1101 | 4100 | SAN LUIS OBISPO 1102circuit_breaker | 0.003391 | 0.85577 | 0.18371 | 0 | 0.18371 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 16 |  | 5 | 4 | 16 | 5 | 4 | 8.29 | 0.0039625 | 4e-05 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 27.2165 | 27.2165 | 0%
Central Coast | SJ_San Jose | MORGAN HILL 2111 | 3802 | MORGAN HILL 2108circuit_breaker | 0.020729 | 8.5339 | 0.56761 | 0 | 0.56761 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 1 | 34 |  | 8 | 6 | 34 | 8 | 6 | 14.02 | 0.002429 | 4e-05 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 14.0941 | 14.0941 | 0%
Bay Area | DI_Diablo | TIDEWATER 2106 | 9370 | TIDEWATER 210695842 | 0.001674 | 1.6229 | 0.26193 | 0 | 0.26193 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 36 |  | 8 | 6 | 36 | 8 | 6 | 14.2 | 0.0010315 | 2e-05 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 30.5423 | 30.5423 | 0%
Bay Area | MI_Mission | SAN RAMON 2107 | 634 | SAN RAMON 2104circuit_breaker | 0.007398 | 19.307 | 0.23049 | 0 | 0.23049 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 59 |  | 13 | 9 | 59 | 13 | 9 | 23.12 | 0.00038318 | 1e-05 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 56.401 | 56.401 | 0%
North Coast | SO_Sonoma | COTATI 1104 | 3895 | COTATI 110494186 | 0.001623 | 3.9934 | 0.17311 | 0 | 0.17311 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 21 |  | 6 | 5 | 21 | 6 | 5 | 10.11 | 0.00040642 | 1e-05 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 34.6608 | 34.6608 | 0%
Bay Area | DI_Diablo | CLAYTON 2217 | 3336 | CLAYTON 2216circuit_breaker | 0 | 0 | 0.081629 | 0 | 0.081629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 49.0023 | 49.0023 | 0%
Bay Area | DI_Diablo | LAKEWOOD 1103 | 7895 | LAKEWOOD 1104circuit_breaker | 0 | 0 | 1.6595 | 0 | 1.6595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.4104 | 2.4104 | 0%
Bay Area | DI_Diablo | LAKEWOOD 1103 | 4081 | ROSSMOOR 110798488 | 2e-06 | 0.99639 | 0.53466 | 0 | 0.53466 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1 | 163 |  | 31 | 22 | 163 | 31 | 22 | 57.14 | 2.0072e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 57.9809 | 57.9809 | 0%
Bay Area | DI_Diablo | LAKEWOOD 2110 | 4358 | LAKEWOOD 211021345 | 0 | 0 | 0.35076 | 0 | 0.35076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 11.4039 | 11.4039 | 0%
Bay Area | DI_Diablo | LAKEWOOD 2110 | 1433 | LAKEWOOD 211090650 | 1e-06 | 0.69576 | 5.7792 | 0 | 5.7792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 1.4373e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.69214 | 0.69214 | 0%
Bay Area | DI_Diablo | LAKEWOOD 2110 | 8564 | LAKEWOOD 211093966 | 0 | 0 | 1.3292 | 0 | 1.3292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 3.0094 | 3.0094 | 0%
Bay Area | DI_Diablo | LAKEWOOD 2110 | 4044 | LAKEWOOD 211094814 | 0 | 0 | 3.1381 | 0 | 3.1381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.2747 | 1.2747 | 0%
Bay Area | DI_Diablo | LAKEWOOD 2110 | 4401 | LAKEWOOD 2110circuit_breaker | 0 | 0 | 5.2057 | 0 | 5.2057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 344 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.76839 | 0.76839 | 0%
Bay Area | DI_Diablo | LAKEWOOD 2110 | 5535 | LAKEWOOD 2110D578R | 1.4e-05 | 8.8842 | 0.36098 | 0 | 0.36098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 1.5758e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 11.0808 | 11.0808 | 0%
Bay Area | DI_Diablo | LAKEWOOD 2110 | 7744 | LAKEWOOD 2110W520R | 0 | 0 | 3.4655 | 0 | 3.4655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.1542 | 1.1542 | 0%
Bay Area | DI_Diablo | LAKEWOOD 2110 | 2233 | LAKEWOOD 222475242 | 0 | 0 | 0.74962 | 0 | 0.74962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 5.336 | 5.336 | 0%
Bay Area | DI_Diablo | LAKEWOOD 2110 | 3368 | LAKEWOOD 2224circuit_breaker | 0 | 0 | 1.7218 | 0 | 1.7218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.3232 | 2.3232 | 0%
Bay Area | DI_Diablo | LAKEWOOD 2224 | 1810 | ROBLES 0401circuit_breaker | 2.7e-05 | 16.2442 | 0.71383 | 0 | 0.71383 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 199 |  | 38 | 26 | 199 | 38 | 26 | 69.97 | 1.6621e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 53.2343 | 53.2343 | 0%
Bay Area | DI_Diablo | MEADOW LANE 2105 | 3889 | MEADOW LANE 2103circuit_breaker | 0 | 0 | 0.4089 | 0 | 0.4089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 9.7823 | 9.7823 | 0%
Bay Area | DI_Diablo | MEADOW LANE 2105 | 3951 | MEADOW LANE 2104circuit_breaker | 0 | 0 | 0.17992 | 0 | 0.17992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 22.2316 | 22.2316 | 0%
Bay Area | DI_Diablo | MEADOW LANE 2105 | 349 | MEADOW LANE 2105circuit_breaker | 0 | 0 | 13.0623 | 0 | 13.0623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 867 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.30622 | 0.30622 | 0%
Bay Area | DI_Diablo | MEADOW LANE 2105 | 4063 | MEADOW LANE 2107C589R | 0 | 0 | 0.24773 | 0 | 0.24773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 16.1468 | 16.1468 | 0%
Bay Area | DI_Diablo | MEADOW LANE 2105 | 7189 | MEADOW LANE 2107circuit_breaker | 0 | 0 | 0.098295 | 0 | 0.098295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 40.6936 | 40.6936 | 0%
Bay Area | DI_Diablo | MEADOW LANE 2105 | 2807 | TIDEWATER 210978302 | 0 | 0 | 0.41989 | 0 | 0.41989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 9.5264 | 9.5264 | 0%
Bay Area | DI_Diablo | ROSSMOOR 1101 | 5767 | ROSSMOOR 1101L501R | 0 | 0.55129 | 0.21364 | 0 | 0.21364 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 58 |  | 12 | 9 | 58 | 12 | 9 | 21.66 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 56.1702 | 56.1702 | 0%
Bay Area | DI_Diablo | ROSSMOOR 1102 | 1356 | ROSSMOOR 1103circuit_breaker | 2.2e-05 | 8.9767 | 1.0686 | 0.085985 | 0.98258 | 0.085985 | 29 | 3 | 3 | 3 | 1 | 1 | 0 | 45 | 0.91953 | 63 |  | 16 | 12 | 60 | 15 | 11 | 25.95 | 2.4508e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 15.266 | 14.9734 | 8.047%
Bay Area | DI_Diablo | TIDEWATER 2106 | 1648 | CLAYTON 1104C550R | 0 | 0 | 0.078788 | 0 | 0.078788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 50.7692 | 50.7692 | 0%
Bay Area | DI_Diablo | TIDEWATER 2106 | 4767 | TIDEWATER 2106C514R | 0 | 0.27236 | 0.6447 | 0 | 0.6447 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 1 | 50 |  | 11 | 8 | 50 | 11 | 8 | 19.57 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 17.0623 | 17.0623 | 0%
Bay Area | DI_Diablo | TIDEWATER 2110 | 7048 | MEADOW LANE 210611184 | 0 | 0 | 0.10928 | 0 | 0.10928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 36.6031 | 36.6031 | 0%
Bay Area | DI_Diablo | TIDEWATER 2110 | 6437 | MEADOW LANE 210865456 | 0 | 0 | 0.3089 | 0 | 0.3089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 12.9491 | 12.9491 | 0%
Bay Area | DI_Diablo | TIDEWATER 2110 | 2883 | TIDEWATER 2104circuit_breaker | 0 | 0 | 0.14735 | 0 | 0.14735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 27.1465 | 27.1465 | 0%
Bay Area | DI_Diablo | TIDEWATER 2110 | 5084 | TIDEWATER 2106circuit_breaker | 0 | 0 | 0.056818 | 0 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 70.4 | 70.4 | 0%
Bay Area | DI_Diablo | TIDEWATER 2110 | 1553 | TIDEWATER 210756052 | 0 | 0 | 1.1225 | 0 | 1.1225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 3.5634 | 3.5634 | 0%
Bay Area | DI_Diablo | TIDEWATER 2110 | 2029 | TIDEWATER 2107circuit_breaker | 0 | 0 | 0.66894 | 0 | 0.66894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 5.9796 | 5.9796 | 0%
Bay Area | DI_Diablo | TIDEWATER 2110 | 4665 | TIDEWATER 2110C561R | 0 | 0 | 2.8367 | 0 | 2.8367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.4101 | 1.4101 | 0%
Bay Area | DI_Diablo | TIDEWATER 2110 | 3216 | TIDEWATER 2110C594R | 0 | 0 | 1.4186 | 0 | 1.4186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.8198 | 2.8198 | 0%
Bay Area | DI_Diablo | TIDEWATER 2110 | 5864 | TIDEWATER 2110circuit_breaker | 0 | 0 | 3.4665 | 0 | 3.4665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.1539 | 1.1539 | 0%
Bay Area | DI_Diablo | WALNUT CREEK 0404 | 310 | WALNUT CREEK 0404circuit_breaker | 0 | 0 | 5.0634 | 0 | 5.0634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.78998 | 0.78998 | 0%
Bay Area | EB_East Bay | BOSTON 0401 | 620 | MAPLE 0401circuit_breaker | 0 | 0 | 0.46515 | 0 | 0.46515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 8.5993 | 8.5993 | 0%
Bay Area | EB_East Bay | OAKLAND J 1105 | 1199 | OAKLAND J 1105CR132 | 2e-06 | 27.6096 | 0.67462 | 0 | 0.67462 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 1 | 59 |  | 13 | 9 | 59 | 13 | 9 | 23.12 | 7.2439e-08 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 19.2701 | 19.2701 | 0%
Bay Area | EB_East Bay | OAKLAND J 1116 | 985 | OAKLAND J 1102circuit_breaker | 0 | 0 | 0.47197 | 0 | 0.47197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 8.4751 | 8.4751 | 0%
Bay Area | EB_East Bay | OAKLAND J 1116 | 495 | OAKLAND J 1104CR382 | 0 | 0 | 0.99413 | 0 | 0.99413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 4.0236 | 4.0236 | 0%
Bay Area | EB_East Bay | OAKLAND J 1116 | 1191 | OAKLAND J 1106circuit_breaker | 0 | 0 | 0.30985 | 0 | 0.30985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 12.9095 | 12.9095 | 0%
Bay Area | EB_East Bay | OAKLAND J 1116 | 4639 | OAKLAND J 1117CR190 | 0 | 0 | 0.69886 | 0 | 0.69886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 5.7236 | 5.7236 | 0%
Bay Area | EB_East Bay | OAKLAND K 1101 | 1582 | OAKLAND D 1133circuit_breaker | 9e-06 | 17.7803 | 0.076705 | 0 | 0.076705 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 14 |  | 5 | 4 | 14 | 5 | 4 | 8.11 | 5.0618e-07 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 65.1852 | 65.1852 | 0%
Bay Area | EB_East Bay | SAN LEANDRO U 1109 | 464 | BANCROFT 0401circuit_breaker | 0 | 1.5205 | 0.077652 | 0 | 0.077652 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 21 |  | 6 | 5 | 21 | 6 | 5 | 10.11 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 77.2683 | 77.2683 | 0%
Bay Area | EB_East Bay | VALLEY VIEW 1103 | 2010 | VALLEY VIEW 1103circuit_breaker | 7e-06 | 4.0463 | 0.7108 | 0 | 0.7108 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1 | 67 |  | 14 | 10 | 67 | 14 | 10 | 25.21 | 1.73e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 19.6962 | 19.6962 | 0%
Bay Area | MI_Mission | CASTRO VALLEY 1106 | 4664 | CASTRO VALLEY 1106MR578 | 3e-06 | 9.6094 | 0.23049 | 0 | 0.23049 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 25 |  | 6 | 5 | 25 | 6 | 5 | 10.47 | 3.1219e-07 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 26.0312 | 26.0312 | 0%
Bay Area | MI_Mission | CASTRO VALLEY 1111 | 7899 | CASTRO VALLEY 1101MR248 | 0 | 0 | 0.21174 | 0 | 0.21174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 18.8909 | 18.8909 | 0%
Bay Area | MI_Mission | ESTUDILLO 0401 | 3530 | WARD 0401circuit_breaker | 0 | 0 | 0.90928 | 0 | 0.90928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 4.3991 | 4.3991 | 0%
Bay Area | MI_Mission | SAN LEANDRO U 1114 | 3830 | SAN LEANDRO U 1102circuit_breaker | 0 | 0 | 0.65852 | 0 | 0.65852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 6.0742 | 6.0742 | 0%
Bay Area | MI_Mission | SAN LEANDRO U 1114 | 916 | SAN LEANDRO U 1105circuit_breaker | 0 | 0 | 1.1008 | 0 | 1.1008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 3.6339 | 3.6339 | 0%
Bay Area | MI_Mission | SAN LEANDRO U 1114 | 2329 | SAN LEANDRO U 1107MR560 | 0 | 0 | 0.30303 | 0 | 0.30303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 13.2 | 13.2 | 0%
Bay Area | MI_Mission | SAN LEANDRO U 1114 | 2089 | SAN LEANDRO U 1114circuit_breaker | 0 | 0 | 2.7032 | 0 | 2.7032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.4797 | 1.4797 | 0%
Bay Area | MI_Mission | SAN RAMON 2103 | 680 | SAN RAMON 2103circuit_breaker | 0 | 0 | 2.4623 | 0 | 2.4623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.6245 | 1.6245 | 0%
Bay Area | MI_Mission | SAN RAMON 2103 | 4158 | SAN RAMON 2104MR143 | 0 | 0 | 0.21534 | 0 | 0.21534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 18.5752 | 18.5752 | 0%
Bay Area | MI_Mission | SAN RAMON 2103 | 5333 | SAN RAMON 2111circuit_breaker | 0 | 0 | 0.096402 | 0 | 0.096402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 41.4931 | 41.4931 | 0%
Bay Area | MI_Mission | SAN RAMON 2103 | 6709 | SAN RAMON 2111MR673 | 0 | 0 | 0.34356 | 0 | 0.34356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 11.6428 | 11.6428 | 0%
Bay Area | MI_Mission | SAN RAMON 2119 | 5784 | SAN RAMON 2114circuit_breaker | 0 | 0 | 0.28428 | 0 | 0.28428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 14.0706 | 14.0706 | 0%
Bay Area | MI_Mission | SAN RAMON 2119 | 7935 | SAN RAMON 2119MR388 | 0 | 0 | 2.4862 | 0 | 2.4862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.6089 | 1.6089 | 0%
Bay Area | MI_Mission | TASSAJARA 2113 | 7525 | TASSAJARA 2113MR280 | 0 | 0 | 0.076894 | 0 | 0.076894 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 59 |  | 13 | 9 | 59 | 13 | 9 | 23.12 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 169.064 | 169.064 | 0%
Bay Area | NB_North Bay | IGNACIO 1105 | 7905 | IGNACIO 1102circuit_breaker | 0.000301 | 1.6498 | 0.42633 | 0 | 0.42633 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 14 |  | 5 | 4 | 14 | 5 | 4 | 8.11 | 0.00018245 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 11.7281 | 11.7281 | 0%
Bay Area | NB_North Bay | IGNACIO 1105 | 6267 | NOVATO 1103circuit_breaker | 0 | 0 | 0.67879 | 0 | 0.67879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 5.8929 | 5.8929 | 0%
Bay Area | NB_North Bay | NAPA 1102 | 112 | BASALT 1106circuit_breaker | 0 | 0 | 0.2697 | 0 | 0.2697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 14.8315 | 14.8315 | 0%
Bay Area | NB_North Bay | NAPA 1102 | 917 | NAPA 11021360 | 0 | 0 | 4.9928 | 0 | 4.9928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.80115 | 0.80115 | 0%
Bay Area | NB_North Bay | NAPA 1102 | 4489 | NAPA 11025057 | 0 | 0 | 2.7328 | 0 | 2.7328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.4637 | 1.4637 | 0%
Bay Area | NB_North Bay | NAPA 1102 | 2775 | NAPA 1102710 | 0 | 0 | 6.4072 | 0 | 6.4072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 433 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.6243 | 0.6243 | 0%
Bay Area | NB_North Bay | NAPA 1102 | 6114 | NAPA 1102942 | 0 | 0 | 10.9572 | 0 | 10.9572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.36506 | 0.36506 | 0%
Bay Area | NB_North Bay | NAPA 1102 | 4446 | NAPA 111048232 | 0 | 0 | 0.0056818 | 0 | 0.0056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 704 | 704 | 0%
Bay Area | NB_North Bay | NAPA 1102 | 6871 | NAPA 1110712 | 0 | 0 | 0.71515 | 0 | 0.71515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 5.5932 | 5.5932 | 0%
Bay Area | NB_North Bay | NAPA 1102 | 4750 | NAPA 1110944 | 0 | 0 | 0.21686 | 0 | 0.21686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 18.4454 | 18.4454 | 0%
Bay Area | NB_North Bay | NORTH TOWER 2101 | 652 | NORTH TOWER 1103circuit_breaker | 0 | 0 | 2.1837 | 0 | 2.1837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.8317 | 1.8317 | 0%
Bay Area | NB_North Bay | NORTH TOWER 2101 | 7597 | NORTH TOWER 1108circuit_breaker | 0 | 0 | 0.51345 | 0 | 0.51345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 7.7905 | 7.7905 | 0%
Bay Area | NB_North Bay | NORTH TOWER 2101 | 1292 | VALLEJO B 0412circuit_breaker | 0 | 0 | 0.14413 | 0 | 0.14413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 27.753 | 27.753 | 0%
Bay Area | NB_North Bay | NORTH TOWER 2101 | 3265 | VALLEJO B 0413circuit_breaker | 0 | 0 | 0.48902 | 0 | 0.48902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 8.1797 | 8.1797 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1101 | 5704 | SAN RAFAEL 1102circuit_breaker | 0 | 0 | 0.079735 | 0 | 0.079735 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 18 |  | 5 | 4 | 18 | 5 | 4 | 8.47 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 62.7078 | 62.7078 | 0%
Bay Area | NB_North Bay | SAN RAFAEL 1109 | 4250 | SAN RAFAEL 1109circuit_breaker | 0 | 2.2044 | 0.21742 | 0 | 0.21742 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 132 |  | 26 | 18 | 132 | 26 | 18 | 47.5 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 119.5819 | 119.5819 | 0%
Bay Area | PE_Peninsula | BELMONT 1103 | 663 | BELMONT 110347804 | 4e-06 | 10.3483 | 0.77216 | 0 | 0.77216 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 1 | 65 |  | 14 | 10 | 65 | 14 | 10 | 25.03 | 3.8654e-07 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 18.131 | 18.131 | 0%
Bay Area | PE_Peninsula | BELMONT 1103 | 2366 | BELMONT 11109088 | 0 | 0 | 0.24773 | 0 | 0.24773 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 23 |  | 6 | 5 | 23 | 6 | 5 | 10.29 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 24.2202 | 24.2202 | 0%
Bay Area | PE_Peninsula | HALF MOON BAY 1101 | 7618 | HALF MOON BAY 110265568 | 2.3e-05 | 3.2984 | 1.003 | 0 | 1.003 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1 | 192 |  | 37 | 25 | 192 | 37 | 25 | 67.97 | 6.9731e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 36.8882 | 36.8882 | 0%
Bay Area | PE_Peninsula | HALF MOON BAY 1102 | 2094 | HALF MOON BAY 11018940 | 0 | 0 | 0.096402 | 0 | 0.096402 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 14 |  | 5 | 4 | 14 | 5 | 4 | 8.11 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 51.8664 | 51.8664 | 0%
Bay Area | PE_Peninsula | HALF MOON BAY 1102 | 536 | HALF MOON BAY 11028910 | 0 | 0 | 0.1517 | 0 | 0.1517 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 34 |  | 8 | 6 | 34 | 8 | 6 | 14.02 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 52.7341 | 52.7341 | 0%
Bay Area | PE_Peninsula | PACIFICA 1104 | 778 | PACIFICA 110410195 | 0 | 0.11167 | 0.052273 | 0 | 0.052273 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 16 |  | 5 | 4 | 16 | 5 | 4 | 8.29 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 95.6522 | 95.6522 | 0%
Bay Area | PE_Peninsula | RALSTON 1102 | 5937 | BELMONT 11103975 | 1e-06 | 9.971 | 0.57633 | 0 | 0.57633 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 1 | 54 |  | 12 | 9 | 54 | 12 | 9 | 21.3 | 1.0029e-07 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 20.8216 | 20.8216 | 0%
Bay Area | PE_Peninsula | RALSTON 1102 | 2880 | RALSTON 11021601 | 0 | 11.6836 | 1.1983 | 0 | 1.1983 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 1 | 61 |  | 13 | 10 | 61 | 13 | 10 | 23.3 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 10.8487 | 10.8487 | 0%
Bay Area | PE_Peninsula | SAN CARLOS 1104 | 2167 | SAN CARLOS 11049010 | 0 | 4.0995 | 0.32746 | 0 | 0.32746 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1 | 50 |  | 11 | 8 | 50 | 11 | 8 | 19.57 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 33.5917 | 33.5917 | 0%
Bay Area | PE_Peninsula | SNEATH LANE 1102 | 1499 | SNEATH LANE 110796530 | 2e-06 | 7.2331 | 1.075 | 0 | 1.075 | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 1 | 330 |  | 62 | 41 | 330 | 62 | 41 | 114.64 | 2.7651e-07 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 57.6744 | 57.6744 | 0%
Central Coast | CC_Central Coast | DEL MONTE 1101 | 2633 | DEL MONTE 110138576 | 1.8e-05 | 6.5205 | 0.49848 | 0 | 0.49848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 2.7605e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 8.0243 | 8.0243 | 0%
Central Coast | CC_Central Coast | DEL MONTE 1101 | 823 | DEL MONTE 110172040 | 0 | 0 | 4.1275 | 0 | 4.1275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.96912 | 0.96912 | 0%
Central Coast | CC_Central Coast | DEL MONTE 1101 | 6976 | DEL MONTE 21022650 | 0 | 0 | 0.52027 | 0 | 0.52027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 7.6884 | 7.6884 | 0%
Central Coast | CC_Central Coast | DEL MONTE 1101 | 3939 | DEL MONTE 2103circuit_breaker | 0 | 0 | 0.020644 | 0 | 0.020644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 193.7615 | 193.7615 | 0%
Central Coast | CC_Central Coast | DEL MONTE 1101 | 5323 | DEL MONTE 210448004 | 0 | 0 | 1.4458 | 0 | 1.4458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.7666 | 2.7666 | 0%
Central Coast | CC_Central Coast | DEL MONTE 1101 | 2852 | FORT ORD 21069136 | 0 | 0 | 0.25966 | 0 | 0.25966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 15.4048 | 15.4048 | 0%
Central Coast | CC_Central Coast | DEL MONTE 1101 | 1707 | FORT ORD 21069138 | 0 | 0 | 1.2155 | 0 | 1.2155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 3.2907 | 3.2907 | 0%
Central Coast | CC_Central Coast | DEL MONTE 2103 | 1898 | VIEJO 220393964 | 2e-06 | 20.1077 | 1.2381 | 0.29716 | 0.94091 | 1.0835 | 145 | 200 | 20 | 9 | 5 | 4 | 0 | 34 | 0.12483 | 234 |  | 26 | 13 | 34 | 21 | 9 | 31.83 | 9.9465e-08 | 0 | 999999 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 22.3188 | 21.0005 | 24%
Central Coast | CC_Central Coast | FORT ORD 2106 | 8743 | FORT ORD 210633694 | 0 | 0 | 0.27027 | 0 | 0.27027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 14.8003 | 14.8003 | 0%
Central Coast | CC_Central Coast | FORT ORD 2107 | 5201 | CASTROVILLE 210436922 | 1e-06 | 8.7389 | 0.19261 | 0 | 0.19261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 1.1443e-07 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 20.767 | 20.767 | 0%
Central Coast | CC_Central Coast | GONZALES 1104 | 7786 | GONZALES 110422420 | 0 | 0 | 0.060227 | 0 | 0.060227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 66.4151 | 66.4151 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2103 | 7065 | ERTA 04045308 | 0 | 0 | 0.8339 | 0 | 0.8339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 4.7967 | 4.7967 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2103 | 8478 | ERTA 04046633 | 0 | 0 | 1.2652 | 0 | 1.2652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 3.1617 | 3.1617 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2103 | 1226 | ERTA 0404circuit_breaker | 0 | 0 | 0.0625 | 0 | 0.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 64 | 64 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2103 | 5515 | GREEN VALLEY 210210260 | 0 | 0 | 1.1642 | 0 | 1.1642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 3.4358 | 3.4358 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2103 | 458 | GREEN VALLEY 210211036 | 0 | 0 | 0.031061 | 0 | 0.031061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 128.7805 | 128.7805 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2103 | 134 | GREEN VALLEY 2102circuit_breaker | 0 | 0 | 0.70625 | 0 | 0.70625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 5.6637 | 5.6637 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2103 | 4271 | GREEN VALLEY 210310438 | 0 | 0 | 8.0973 | 0 | 8.0973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.49399 | 0.49399 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2103 | 1179 | GREEN VALLEY 210310932 | 0 | 0 | 7.1509 | 0 | 7.1509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.55937 | 0.55937 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2103 | 3786 | GREEN VALLEY 210312654 | 0 | 0 | 13.19 | 0 | 13.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.30326 | 0.30326 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2103 | 1750 | GREEN VALLEY 210312656 | 0 | 0 | 17.7621 | 0 | 17.7621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.2252 | 0.2252 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2103 | 2678 | GREEN VALLEY 2103186292 | 0 | 0 | 4.211 | 0 | 4.211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.9499 | 0.9499 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2103 | 9145 | GREEN VALLEY 21034929 | 0 | 0 | 1.7216 | 0 | 1.7216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.3234 | 2.3234 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2103 | 6594 | GREEN VALLEY 21035140 | 0 | 0 | 7.1718 | 0 | 7.1718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.55774 | 0.55774 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2103 | 4821 | GREEN VALLEY 21036661 | 0 | 0 | 1.1674 | 0 | 1.1674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 3.4263 | 3.4263 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2103 | 2273 | GREEN VALLEY 2103938286 | 0 | 0 | 2.5167 | 0 | 2.5167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.5894 | 1.5894 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2103 | 5818 | GREEN VALLEY 210395184 | 0 | 0 | 1.728 | 0 | 1.728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.3148 | 2.3148 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2103 | 3234 | GREEN VALLEY 210397492 | 0 | 0 | 4.0108 | 0 | 4.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.99731 | 0.99731 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2103 | 5466 | GREEN VALLEY 21039959 | 0 | 0 | 3.24 | 0 | 3.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.2346 | 1.2346 | 0%
Central Coast | CC_Central Coast | GREEN VALLEY 2103 | 3435 | GREEN VALLEY 2103circuit_breaker | 0 | 0 | 5.4475 | 0 | 5.4475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.73428 | 0.73428 | 0%
Central Coast | CC_Central Coast | HATTON 1102 | 4841 | HATTON 110240465 | 0 | 0.059642 | 0.04072 | 0 | 0.04072 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 27 |  | 7 | 5 | 27 | 7 | 5 | 12.02 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 171.907 | 171.907 | 0%
Central Coast | CC_Central Coast | HOLLISTER 2102 | 3875 | HOLLISTER 21024908 | 0 | 0 | 0.35833 | 0 | 0.35833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 11.1628 | 11.1628 | 0%
Central Coast | CC_Central Coast | PAUL SWEET 2104 | 2403 | PAUL SWEET 2104circuit_breaker | 1.7e-05 | 3.6228 | 0.066856 | 0 | 0.066856 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 98 |  | 20 | 14 | 98 | 20 | 14 | 36.22 | 4.6925e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 299.1501 | 299.1501 | 0%
Central Coast | CC_Central Coast | PAUL SWEET 2106 | 4476 | PAUL SWEET 2107circuit_breaker | 1e-06 | 0.39606 | 0.64886 | 0 | 0.64886 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 125 |  | 24 | 17 | 125 | 24 | 17 | 44.13 | 2.5249e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 36.9877 | 36.9877 | 0%
Central Coast | CC_Central Coast | PRUNEDALE 1107 | 8582 | CASTROVILLE 2103791564 | 0 | 0 | 0.46686 | 0 | 0.46686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 8.568 | 8.568 | 0%
Central Coast | CC_Central Coast | PRUNEDALE 1107 | 5411 | CASTROVILLE 210422428 | 0 | 0 | 0.28163 | 0 | 0.28163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 14.2031 | 14.2031 | 0%
Central Coast | CC_Central Coast | PRUNEDALE 1107 | 1649 | GABILAN 1102circuit_breaker | 0 | 0 | 0.31686 | 0 | 0.31686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 12.624 | 12.624 | 0%
Central Coast | CC_Central Coast | PRUNEDALE 1107 | 2026 | PRUNEDALE 110722232 | 0 | 0 | 2.0013 | 0 | 2.0013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.9987 | 1.9987 | 0%
Central Coast | CC_Central Coast | PRUNEDALE 1107 | 6682 | PRUNEDALE 110725695 | 0 | 0 | 1.5242 | 0 | 1.5242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.6243 | 2.6243 | 0%
Central Coast | CC_Central Coast | PRUNEDALE 1107 | 5568 | PRUNEDALE 11073062 | 0 | 0 | 7.9693 | 0 | 7.9693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.50192 | 0.50192 | 0%
Central Coast | CC_Central Coast | PRUNEDALE 1107 | 2825 | PRUNEDALE 110736920 | 0 | 0 | 4.5553 | 0 | 4.5553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.8781 | 0.8781 | 0%
Central Coast | CC_Central Coast | PRUNEDALE 1107 | 4098 | PRUNEDALE 11073712 | 0 | 0 | 13.5686 | 0 | 13.5686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 549 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.2948 | 0.2948 | 0%
Central Coast | CC_Central Coast | PRUNEDALE 1107 | 116 | PRUNEDALE 1107circuit_breaker | 0 | 0 | 14.2712 | 0 | 14.2712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.28028 | 0.28028 | 0%
Central Coast | CC_Central Coast | PRUNEDALE 1107 | 3129 | PRUNEDALE 111022104 | 0 | 0 | 0.31856 | 0 | 0.31856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 12.5565 | 12.5565 | 0%
Central Coast | CC_Central Coast | PRUNEDALE 1107 | 6960 | PRUNEDALE 11103080 | 0 | 0 | 0.53598 | 0 | 0.53598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 7.4629 | 7.4629 | 0%
Central Coast | CC_Central Coast | PRUNEDALE 1107 | 5389 | PRUNEDALE 1110826224 | 0 | 0 | 0.80322 | 0 | 0.80322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 4.98 | 4.98 | 0%
Central Coast | CC_Central Coast | PRUNEDALE 1107 | 3399 | PRUNEDALE 1110circuit_breaker | 0 | 0 | 0.25246 | 0 | 0.25246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 15.844 | 15.844 | 0%
Central Coast | CC_Central Coast | RIO DEL MAR 0402 | 1716 | PAUL SWEET 210910216 | 2e-05 | 7.0891 | 0.6661 | 0 | 0.6661 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1 | 167 |  | 32 | 22 | 167 | 32 | 22 | 58.87 | 2.8212e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 48.0409 | 48.0409 | 0%
Central Coast | CC_Central Coast | SAN BENITO 2102 | 8345 | HOLLISTER 2102circuit_breaker | 0 | 0 | 0.26989 | 0 | 0.26989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 14.8211 | 14.8211 | 0%
Central Coast | CC_Central Coast | SAN BENITO 2102 | 1042 | SAN BENITO 210163516 | 0 | 0 | 0.57727 | 0 | 0.57727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 6.9291 | 6.9291 | 0%
Central Coast | CC_Central Coast | SAN BENITO 2102 | 3833 | SAN BENITO 2101circuit_breaker | 0 | 0 | 0.46042 | 0 | 0.46042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 8.6878 | 8.6878 | 0%
Central Coast | CC_Central Coast | SAN BENITO 2102 | 8159 | SAN BENITO 21024918 | 0 | 0 | 5.942 | 0 | 5.942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.67317 | 0.67317 | 0%
Central Coast | CC_Central Coast | SAN BENITO 2102 | 7985 | SAN BENITO 210275262 | 0 | 0 | 2.7633 | 0 | 2.7633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.4476 | 1.4476 | 0%
Central Coast | CC_Central Coast | SAN BENITO 2102 | 7120 | SAN BENITO 2102circuit_breaker | 0 | 0 | 0.92614 | 0 | 0.92614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 4.319 | 4.319 | 0%
Central Coast | CC_Central Coast | SAN BENITO 2102 | 5475 | SAN JUSTO 1101circuit_breaker | 0 | 0 | 1.7873 | 0 | 1.7873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.238 | 2.238 | 0%
Central Coast | CC_Central Coast | SPENCE 1102 | 6641 | GABILAN 1101447724 | 0 | 0 | 2.5392 | 0 | 2.5392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.5753 | 1.5753 | 0%
Central Coast | CC_Central Coast | SPENCE 1102 | 2152 | SPENCE 1121circuit_breaker | 0 | 0 | 0.72765 | 0 | 0.72765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 5.4971 | 5.4971 | 0%
Central Coast | CC_Central Coast | SPENCE 1104 | 1575 | BUENA VISTA 1102555392 | 0 | 0 | 0.073295 | 0 | 0.073295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 54.5736 | 54.5736 | 0%
Central Coast | CC_Central Coast | SPENCE 1104 | 4330 | GONZALES 110436982 | 0 | 0 | 1.0305 | 0 | 1.0305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 3.8816 | 3.8816 | 0%
Central Coast | CC_Central Coast | VIEJO 2202 | 8342 | PACIFIC GROVE 04222608 | 0 | 0.94245 | 0.42708 | 0 | 0.42708 | 0 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1 | 288 |  | 54 | 36 | 288 | 54 | 36 | 99.9 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 126.439 | 126.439 | 0%
Central Coast | CC_Central Coast | VIEJO 2202 | 1715 | VIEJO 22029100 | 1e-06 | 2.6315 | 0.2303 | 0 | 0.2303 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 96 |  | 19 | 14 | 96 | 19 | 14 | 34.67 | 3.8001e-07 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 82.5 | 82.5 | 0%
Central Coast | CC_Central Coast | VIEJO 2204 | 6819 | MONTEREY 0402circuit_breaker | 0 | 1.2861 | 0.030492 | 0 | 0.030492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 131.1801 | 131.1801 | 0%
Central Coast | DA_De Anza | EL PATIO 1117 | 777 | EL PATIO 1112circuit_breaker | 0 | 0 | 0.36477 | 0 | 0.36477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 10.9657 | 10.9657 | 0%
Central Coast | DA_De Anza | EL PATIO 1117 | 2164 | EL PATIO 1116circuit_breaker | 0 | 0 | 0.2714 | 0 | 0.2714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 14.7383 | 14.7383 | 0%
Central Coast | DA_De Anza | EL PATIO 1117 | 6062 | EL PATIO 1117circuit_breaker | 0 | 0 | 2.5688 | 0 | 2.5688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.5572 | 1.5572 | 0%
Central Coast | DA_De Anza | EL PATIO 1117 | 130 | EL PATIO 1118circuit_breaker | 0 | 0 | 0.0079545 | 0 | 0.0079545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 502.8571 | 502.8571 | 0%
Central Coast | DA_De Anza | EL PATIO 1117 | 1498 | VASONA 1105LC32 | 0 | 0 | 0.086174 | 0 | 0.086174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 46.4176 | 46.4176 | 0%
Central Coast | DA_De Anza | HICKS 1116 | 2577 | VASONA 1108LC30 | 4e-06 | 10.7321 | 1.4428 | 0 | 1.4428 | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 1 | 172 |  | 33 | 23 | 172 | 33 | 23 | 60.69 | 3.7272e-07 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 22.8721 | 22.8721 | 0%
Central Coast | DA_De Anza | HICKS 2103 | 2891 | HICKS 2103circuit_breaker | 4e-06 | 5.4396 | 0.20133 | 0 | 0.20133 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 81 |  | 17 | 12 | 81 | 17 | 12 | 30.58 | 7.3535e-07 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 84.4403 | 84.4403 | 0%
Central Coast | DA_De Anza | SARATOGA 1109 | 1368 | SARATOGA 1104circuit_breaker | 0 | 0 | 0.92216 | 0 | 0.92216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 4.3376 | 4.3376 | 0%
Central Coast | DA_De Anza | SARATOGA 1109 | 2866 | SARATOGA 110860088 | 0 | 0 | 4.0252 | 0 | 4.0252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.99374 | 0.99374 | 0%
Central Coast | DA_De Anza | SARATOGA 1109 | 4377 | SARATOGA 1108circuit_breaker | 0 | 0 | 2.2074 | 0 | 2.2074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.8121 | 1.8121 | 0%
Central Coast | DA_De Anza | SARATOGA 1109 | 104 | SARATOGA 1108LC106 | 0 | 0 | 2.2415 | 0 | 2.2415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.7845 | 1.7845 | 0%
Central Coast | DA_De Anza | SARATOGA 1109 | 719 | SARATOGA 11091024 | 0 | 0 | 3.5485 | 0 | 3.5485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.1272 | 1.1272 | 0%
Central Coast | DA_De Anza | SARATOGA 1109 | 433 | SARATOGA 1109LC44 | 0 | 0 | 11.3795 | 0 | 11.3795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.35151 | 0.35151 | 0%
Central Coast | DA_De Anza | SARATOGA 1109 | 2760 | SARATOGA 1111circuit_breaker | 0 | 0 | 0.075189 | 0 | 0.075189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 53.199 | 53.199 | 0%
Central Coast | DA_De Anza | SARATOGA 1109 | 4421 | VASONA 110360132 | 0 | 0 | 1.4481 | 0 | 1.4481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.7622 | 2.7622 | 0%
Central Coast | DA_De Anza | SARATOGA 1109 | 4969 | VASONA 1103circuit_breaker | 0 | 0 | 0.051326 | 0 | 0.051326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 77.9336 | 77.9336 | 0%
Central Coast | DA_De Anza | SARATOGA 1109 | 1623 | VASONA 110548314 | 0 | 0 | 0.30985 | 0 | 0.30985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 12.9095 | 12.9095 | 0%
Central Coast | LP_Los Padres | DIVIDE 1101 | 6411 | DIVIDE 1101circuit_breaker | 0 | 0 | 2.222 | 0 | 2.222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.8002 | 1.8002 | 0%
Central Coast | LP_Los Padres | DIVIDE 1101 | 498 | DIVIDE 1101M78 | 0 | 0 | 12.8854 | 0 | 12.8854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.31043 | 0.31043 | 0%
Central Coast | LP_Los Padres | DIVIDE 1101 | 4349 | DIVIDE 1102circuit_breaker | 0 | 0 | 0.26326 | 0 | 0.26326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 15.1942 | 15.1942 | 0%
Central Coast | LP_Los Padres | DIVIDE 1101 | 1434 | SISQUOC 1101M96 | 0 | 0 | 0.16269 | 0 | 0.16269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 24.5867 | 24.5867 | 0%
Central Coast | LP_Los Padres | MORRO BAY 1102 | 5375 | MORRO BAY 1101circuit_breaker | 0.000934 | 11.6414 | 0.51761 | 0 | 0.51761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 8.0231e-05 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 7.7278 | 7.7278 | 0%
Central Coast | LP_Los Padres | MORRO BAY 1102 | 760 | MORRO BAY 1101V64 | 0 | 0.58674 | 0.35758 | 0 | 0.35758 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 40 |  | 9 | 7 | 40 | 9 | 7 | 15.93 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 25.1695 | 25.1695 | 0%
Central Coast | LP_Los Padres | MORRO BAY 1102 | 5203 | MORRO BAY 1101W02 | 0.000467 | 4.8733 | 0.49242 | 0 | 0.49242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 9.5829e-05 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 8.1231 | 8.1231 | 0%
Central Coast | LP_Los Padres | MORRO BAY 1102 | 3562 | MORRO BAY 1102V86 | 0 | 0.013498 | 0.056818 | 0 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 70.4 | 70.4 | 0%
Central Coast | LP_Los Padres | OCEANO 1103 | 5501 | OCEANO 110666476 | 2e-06 | 4.6345 | 0.16383 | 0 | 0.16383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 4.3154e-07 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 24.4162 | 24.4162 | 0%
Central Coast | LP_Los Padres | OCEANO 1105 | 3358 | OCEANO 1105V20 | 1e-06 | 2.0685 | 0.043182 | 0 | 0.043182 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 14 |  | 5 | 4 | 14 | 5 | 4 | 8.11 | 4.8345e-07 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 115.7895 | 115.7895 | 0%
Central Coast | LP_Los Padres | PALMER 1101 | 6850 | PALMER 1101circuit_breaker | 0 | 0 | 0.18068 | 0 | 0.18068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 22.1384 | 22.1384 | 0%
Central Coast | LP_Los Padres | SAN LUIS OBISPO 1108 | 6374 | SAN LUIS OBISPO 1108337126 | 0.032453 | 9.6916 | 0.19451 | 0.19451 | 0 | 0.19451 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.0033486 | 0 | 999999 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0 | 100%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 7346 | CHOLAME 1101R22 | 0 | 0 | 0.21345 | 0 | 0.21345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 18.74 | 18.74 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 4641 | PASO ROBLES 1106R70 | 0 | 0 | 0.21837 | 0 | 0.21837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 18.3174 | 18.3174 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 4157 | PASO ROBLES 1108circuit_breaker | 0 | 0 | 0.16061 | 0 | 0.16061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 24.9057 | 24.9057 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 7805 | PASO ROBLES 1108P28 | 0 | 0 | 0.39527 | 0 | 0.39527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 10.1198 | 10.1198 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 3948 | SAN MIGUEL 1104R54 | 0 | 0 | 0.095455 | 0 | 0.095455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 41.9048 | 41.9048 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 8042 | TEMPLETON 21096123 | 0 | 0 | 0.82973 | 0 | 0.82973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 4.8208 | 4.8208 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 6977 | TEMPLETON 21097049 | 0 | 0 | 2.4407 | 0 | 2.4407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.6389 | 1.6389 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 2284 | TEMPLETON 2109circuit_breaker | 0 | 0 | 13.8513 | 0 | 13.8513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 438 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.28878 | 0.28878 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 3564 | TEMPLETON 2109P14 | 0 | 0 | 25.3958 | 0 | 25.3958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 749 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.15751 | 0.15751 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 2459 | TEMPLETON 2109P32 | 0 | 0 | 11.1335 | 0 | 11.1335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.35928 | 0.35928 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 5826 | TEMPLETON 2109P60 | 0 | 0 | 2.5856 | 0 | 2.5856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.547 | 1.547 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 6346 | TEMPLETON 2109P68 | 0 | 0 | 22.6104 | 0 | 22.6104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 684 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.17691 | 0.17691 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 4564 | TEMPLETON 2109R34 | 0 | 0 | 30.3665 | 0 | 30.3665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 809 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.13172 | 0.13172 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 4338 | TEMPLETON 2109R50 | 0 | 0 | 26.3318 | 0 | 26.3318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 847 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.15191 | 0.15191 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 4164 | TEMPLETON 2109R52 | 0 | 0 | 25.993 | 0 | 25.993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.15389 | 0.15389 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 9315 | TEMPLETON 2109R74 | 0 | 0 | 4.8167 | 0 | 4.8167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.83045 | 0.83045 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 4133 | TEMPLETON 2109R78 | 0 | 0 | 10.9795 | 0 | 10.9795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.36431 | 0.36431 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 1946 | TEMPLETON 2109R92 | 0 | 0 | 33.4527 | 0 | 33.4527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1011 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.11957 | 0.11957 | 0%
Central Coast | LP_Los Padres | TEMPLETON 2109 | 7626 | TEMPLETON 2112circuit_breaker | 0 | 0 | 0.097727 | 0 | 0.097727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 40.9302 | 40.9302 | 0%
Central Coast | SJ_San Jose | ALMADEN 1111 | 1319 | ALMADEN 1101circuit_breaker | 0 | 0 | 0.17008 | 0 | 0.17008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 23.5189 | 23.5189 | 0%
Central Coast | SJ_San Jose | ALMADEN 1111 | 3310 | ALMADEN 1102722120 | 0 | 0 | 1.7256 | 0 | 1.7256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.3181 | 2.3181 | 0%
Central Coast | SJ_San Jose | ALMADEN 1111 | 1497 | ALMADEN 1102815266 | 0 | 0 | 0.038636 | 0 | 0.038636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 103.5294 | 103.5294 | 0%
Central Coast | SJ_San Jose | ALMADEN 1111 | 4142 | ALMADEN 1110XR408 | 0 | 0 | 0.16989 | 0 | 0.16989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 23.5452 | 23.5452 | 0%
Central Coast | SJ_San Jose | ALMADEN 1111 | 5643 | ALMADEN 111149936 | 0 | 0 | 1.5801 | 0 | 1.5801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.5315 | 2.5315 | 0%
Central Coast | SJ_San Jose | ALMADEN 1111 | 4766 | ALMADEN 111149970 | 0 | 0 | 0.59621 | 0 | 0.59621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 6.709 | 6.709 | 0%
Central Coast | SJ_San Jose | ALMADEN 1111 | 2768 | ALMADEN 1111circuit_breaker | 0 | 0 | 4.5492 | 0 | 4.5492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.87927 | 0.87927 | 0%
Central Coast | SJ_San Jose | ALMADEN 1111 | 7021 | ALMADEN 1111XR120 | 0 | 0 | 0.69602 | 0 | 0.69602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 5.7469 | 5.7469 | 0%
Central Coast | SJ_San Jose | ALMADEN 1111 | 6479 | EVERGREEN 2105XR170 | 0 | 0 | 0.45682 | 0 | 0.45682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 8.7562 | 8.7562 | 0%
Central Coast | SJ_San Jose | EDENVALE 2113 | 1217 | EDENVALE 1101XR184 | 0 | 0 | 0.0028409 | 0 | 0.0028409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1408 | 1408 | 0%
Central Coast | SJ_San Jose | EDENVALE 2113 | 1308 | EDENVALE 2106XR240 | 0 | 1.1036 | 0.53542 | 0 | 0.53542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 7.4708 | 7.4708 | 0%
Central Coast | SJ_San Jose | EDENVALE 2113 | 2095 | EDENVALE 2113XR106 | 0 | 0 | 0.24432 | 0 | 0.24432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 16.3721 | 16.3721 | 0%
Central Coast | SJ_San Jose | HICKS 1108 | 1798 | HICKS 1108circuit_breaker | 0 | 0 | 13.907 | 0 | 13.907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 913 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.28762 | 0.28762 | 0%
Central Coast | SJ_San Jose | HICKS 1108 | 2364 | HICKS 2105circuit_breaker | 0 | 0 | 0.24034 | 0 | 0.24034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 16.643 | 16.643 | 0%
Central Coast | SJ_San Jose | HICKS 1110 | 6173 | HICKS 1110circuit_breaker | 0 | 0 | 3.6331 | 0 | 3.6331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.101 | 1.101 | 0%
Central Coast | SJ_San Jose | HICKS 1110 | 4113 | HICKS 1110XR308 | 0 | 0 | 1.8725 | 0 | 1.8725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.1361 | 2.1361 | 0%
Central Coast | SJ_San Jose | HICKS 2101 | 6990 | HICKS 2105XR174 | 0 | 0 | 0.42841 | 0 | 0.42841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 9.3369 | 9.3369 | 0%
Central Coast | SJ_San Jose | MILPITAS 1109 | 2357 | MILPITAS 1109XR374 | 5.8e-05 | 4.8504 | 1.058 | 0 | 1.058 | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 294 |  | 55 | 37 | 294 | 55 | 37 | 101.81 | 1.1958e-05 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 51.9871 | 51.9871 | 0%
Central Coast | SJ_San Jose | MORGAN HILL 2106 | 3112 | MORGAN HILL 2110circuit_breaker | 1e-06 | 4.6449 | 0.16742 | 0 | 0.16742 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 16 |  | 5 | 4 | 16 | 5 | 4 | 8.29 | 2.1529e-07 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 29.8643 | 29.8643 | 0%
Central Coast | SJ_San Jose | MORGAN HILL 2110 | 6342 | MORGAN HILL 2110XR164 | 0 | 0.38742 | 0.12197 | 0 | 0.12197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 32.795 | 32.795 | 0%
Central Valley | FR_Fresno | COALINGA NO 1 1109 | 153 | COALINGA NO 1 1106circuit_breaker | 0 | 0 | 1.4814 | 0 | 1.4814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.7001 | 2.7001 | 0%
Central Valley | FR_Fresno | COALINGA NO 1 1109 | 7783 | COALINGA NO 1 1107circuit_breaker | 0 | 0 | 0.94527 | 0 | 0.94527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 4.2316 | 4.2316 | 0%
Central Valley | FR_Fresno | COALINGA NO 1 1109 | 6869 | COALINGA NO 1 11099210 | 0 | 0 | 10.8341 | 0 | 10.8341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.3692 | 0.3692 | 0%
Central Valley | FR_Fresno | COALINGA NO 1 1109 | 8701 | COALINGA NO 1 11099270 | 0 | 0 | 7.4087 | 0 | 7.4087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.5399 | 0.5399 | 0%
Central Valley | FR_Fresno | COALINGA NO 1 1109 | 5256 | COALINGA NO 1 11099870 | 0 | 0 | 3.0617 | 0 | 3.0617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.3064 | 1.3064 | 0%
Central Valley | FR_Fresno | COALINGA NO 1 1109 | 8196 | COALINGA NO 1 1109circuit_breaker | 0 | 0 | 3.5782 | 0 | 3.5782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.1179 | 1.1179 | 0%
Central Valley | FR_Fresno | COALINGA NO 2 1105 | 7929 | COALINGA NO 2 110541882 | 0 | 0 | 2.5025 | 0 | 2.5025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.5984 | 1.5984 | 0%
Central Valley | FR_Fresno | COALINGA NO 2 1105 | 4558 | COALINGA NO 2 110541954 | 0 | 0 | 38.4292 | 0 | 38.4292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 912 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.10409 | 0.10409 | 0%
Central Valley | FR_Fresno | COALINGA NO 2 1105 | 8336 | COALINGA NO 2 11059000 | 0 | 0 | 12.0172 | 0 | 12.0172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.33286 | 0.33286 | 0%
Central Valley | FR_Fresno | COALINGA NO 2 1105 | 9185 | COALINGA NO 2 11059260 | 0 | 0 | 11.6331 | 0 | 11.6331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.34385 | 0.34385 | 0%
Central Valley | FR_Fresno | COALINGA NO 2 1105 | 7982 | COALINGA NO 2 1105circuit_breaker | 0 | 0 | 3.543 | 0 | 3.543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.129 | 1.129 | 0%
Central Valley | FR_Fresno | COALINGA NO 2 1105 | 7200 | COALINGA NO 2 1107circuit_breaker | 0 | 0 | 0.19413 | 0 | 0.19413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 20.6049 | 20.6049 | 0%
Central Valley | FR_Fresno | WOODCHUCK 2101 | 7771 | WOODCHUCK 2101R1115 | 0 | 0 | 1.0504 | 0 | 1.0504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 3.8082 | 3.8082 | 0%
Central Valley | FR_Fresno | WOODCHUCK 2101 | 9830 | WOODCHUCK 2101R1790 | 0 | 0 | 1.1722 | 0 | 1.1722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 3.4125 | 3.4125 | 0%
Central Valley | FR_Fresno | WOODCHUCK 2101 | 9507 | WOODCHUCK 2101R2640 | 0 | 0 | 1.4428 | 0 | 1.4428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.7724 | 2.7724 | 0%
Central Valley | FR_Fresno | WOODCHUCK 2101 | 9505 | WOODCHUCK 2101R2770 | 0 | 0 | 1.8138 | 0 | 1.8138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.2053 | 2.2053 | 0%
Central Valley | ST_Stockton | ALPINE 1101 | 8290 | ALPINE 1101circuit_breaker | 0 | 0 | 0.8733 | 0 | 0.8733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 4.5804 | 4.5804 | 0%
Central Valley | ST_Stockton | WESTLEY 1103 | 5754 | WESTLEY 11018660 | 0 | 0 | 1.0322 | 0 | 1.0322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 3.8752 | 3.8752 | 0%
Central Valley | ST_Stockton | WESTLEY 1103 | 5233 | WESTLEY 11038640 | 0 | 0 | 25.3163 | 0 | 25.3163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 694 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.158 | 0.158 | 0%
Central Valley | YO_Yosemite | MERCED 1114 | 6492 | ATWATER 11027160 | 0 | 0 | 0.42367 | 0 | 0.42367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 9.4412 | 9.4412 | 0%
Central Valley | YO_Yosemite | MERCED 1114 | 509 | ATWATER 11064570 | 0 | 0 | 0.17197 | 0 | 0.17197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 23.2599 | 23.2599 | 0%
Central Valley | YO_Yosemite | MERCED 1114 | 651 | EL CAPITAN 11049610 | 0 | 0 | 0.14072 | 0 | 0.14072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 28.4253 | 28.4253 | 0%
Central Valley | YO_Yosemite | MERCED 1114 | 1203 | EL NIDO 110441394 | 0 | 0 | 0.050947 | 0 | 0.050947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 78.513 | 78.513 | 0%
Central Valley | YO_Yosemite | MERCED 1114 | 1809 | EL NIDO 1104circuit_breaker | 0 | 0 | 0.79962 | 0 | 0.79962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 5.0024 | 5.0024 | 0%
Central Valley | YO_Yosemite | MERCED 1114 | 4484 | MERCED 110890510 | 0 | 0 | 0.005303 | 0 | 0.005303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 754.2857 | 754.2857 | 0%
Central Valley | YO_Yosemite | MERCED 1114 | 3595 | MERCED 1108circuit_breaker | 0 | 0 | 0.042992 | 0 | 0.042992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 93.0396 | 93.0396 | 0%
Central Valley | YO_Yosemite | MERCED 1114 | 5644 | MERCED 11144320 | 0 | 0 | 20.0343 | 0 | 20.0343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 535 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.19966 | 0.19966 | 0%
Central Valley | YO_Yosemite | MERCED 1114 | 4347 | MERCED 111490220 | 0 | 0 | 15.7352 | 0 | 15.7352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.25421 | 0.25421 | 0%
Central Valley | YO_Yosemite | MERCED 1114 | 1122 | MERCED 11149040 | 0 | 0 | 7.9513 | 0 | 7.9513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.50306 | 0.50306 | 0%
Central Valley | YO_Yosemite | MERCED 1114 | 4432 | MERCED 11149200 | 0 | 0 | 22.8871 | 0 | 22.8871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.17477 | 0.17477 | 0%
Central Valley | YO_Yosemite | MERCED 1114 | 2662 | MERCED 11149990 | 0 | 0 | 32.7604 | 0 | 32.7604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 787 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.1221 | 0.1221 | 0%
Central Valley | YO_Yosemite | MERCED 1114 | 6281 | MERCED 1114circuit_breaker | 0 | 0 | 6.1025 | 0 | 6.1025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.65547 | 0.65547 | 0%
Central Valley | YO_Yosemite | MERCED 1114 | 604 | MERCED 11164380 | 0 | 0 | 0.22879 | 0 | 0.22879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 17.4834 | 17.4834 | 0%
Central Valley | YO_Yosemite | MERCED 1114 | 1893 | MERCED 21029740 | 0 | 0 | 0.0015152 | 0 | 0.0015152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2640 | 2640 | 0%
Central Valley | YO_Yosemite | MERCED 1114 | 8759 | MERCED 2102circuit_breaker | 0 | 0 | 0.032008 | 0 | 0.032008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 124.9704 | 124.9704 | 0%
Central Valley | YO_Yosemite | STOREY 1109 | 5202 | CHOWCHILLA 11045980 | 0 | 0 | 0.22102 | 0 | 0.22102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 18.0977 | 18.0977 | 0%
Central Valley | YO_Yosemite | STOREY 1109 | 6301 | CHOWCHILLA 110483552 | 0 | 0 | 0.13504 | 0 | 0.13504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 29.6213 | 29.6213 | 0%
Central Valley | YO_Yosemite | STOREY 1109 | 1549 | STOREY 11049300 | 0 | 0 | 0.24167 | 0 | 0.24167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 16.5517 | 16.5517 | 0%
Central Valley | YO_Yosemite | STOREY 1109 | 2354 | STOREY 1104circuit_breaker | 0 | 0 | 0.46799 | 0 | 0.46799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 8.5471 | 8.5471 | 0%
Central Valley | YO_Yosemite | STOREY 1109 | 1578 | STOREY 110741316 | 0 | 0 | 0.066477 | 0 | 0.066477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 60.1709 | 60.1709 | 0%
Central Valley | YO_Yosemite | STOREY 1109 | 441 | STOREY 1108circuit_breaker | 0 | 0 | 1.5792 | 0 | 1.5792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.533 | 2.533 | 0%
Central Valley | YO_Yosemite | STOREY 1109 | 8918 | STOREY 110921859 | 0 | 0 | 2.4375 | 0 | 2.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.641 | 1.641 | 0%
Central Valley | YO_Yosemite | STOREY 1109 | 2630 | STOREY 110934630 | 0 | 0 | 5.0136 | 0 | 5.0136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.79782 | 0.79782 | 0%
Central Valley | YO_Yosemite | STOREY 1109 | 4811 | STOREY 11095140 | 0 | 0 | 23.2152 | 0 | 23.2152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 643 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.1723 | 0.1723 | 0%
Central Valley | YO_Yosemite | STOREY 1109 | 9705 | STOREY 11095200 | 0 | 0 | 0.44564 | 0 | 0.44564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 8.9758 | 8.9758 | 0%
Central Valley | YO_Yosemite | STOREY 1109 | 2674 | STOREY 11095270 | 0 | 0 | 32.4837 | 0 | 32.4837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.12314 | 0.12314 | 0%
Central Valley | YO_Yosemite | STOREY 1109 | 618 | STOREY 11095580 | 0 | 0 | 31.4773 | 0 | 31.4773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 938 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.12708 | 0.12708 | 0%
Central Valley | YO_Yosemite | STOREY 1109 | 830 | STOREY 11095680 | 0 | 0 | 26.6956 | 0 | 26.6956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.14984 | 0.14984 | 0%
Central Valley | YO_Yosemite | STOREY 1109 | 8858 | STOREY 11096230 | 0 | 0 | 4.9034 | 0 | 4.9034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.81576 | 0.81576 | 0%
Central Valley | YO_Yosemite | STOREY 1109 | 956 | STOREY 11096250 | 0 | 0 | 31.8574 | 0 | 31.8574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 914 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.12556 | 0.12556 | 0%
Central Valley | YO_Yosemite | STOREY 1109 | 7694 | STOREY 1109circuit_breaker | 0 | 0 | 15.8951 | 0 | 15.8951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 431 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.25165 | 0.25165 | 0%
Central Valley | YO_Yosemite | WESTLEY 1103 | 2041 | WESTLEY 11019130 | 0 | 0 | 0.44299 | 0 | 0.44299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 9.0295 | 9.0295 | 0%
Central Valley | YO_Yosemite | WESTLEY 1103 | 5997 | WESTLEY 1103434305 | 0 | 0 | 4.4799 | 0 | 4.4799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.89287 | 0.89287 | 0%
Central Valley | YO_Yosemite | WESTLEY 1103 | 1924 | WESTLEY 11037150 | 0 | 0 | 11.1237 | 0 | 11.1237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.35959 | 0.35959 | 0%
Central Valley | YO_Yosemite | WESTLEY 1103 | 6150 | WESTLEY 11039900 | 0 | 0 | 12.5716 | 0 | 12.5716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.31818 | 0.31818 | 0%
Central Valley | YO_Yosemite | WESTLEY 1103 | 2264 | WESTLEY 1103circuit_breaker | 0 | 0 | 13.4227 | 0 | 13.4227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.298 | 0.298 | 0%
North Coast | HU_Humboldt | EUREKA E 1104 | 4912 | EUREKA A 1107circuit_breaker | 0 | 0 | 0.44773 | 0 | 0.44773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 8.934 | 8.934 | 0%
North Coast | HU_Humboldt | EUREKA E 1104 | 4808 | EUREKA E 11017104 | 0 | 0 | 1.3439 | 0 | 1.3439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.9763 | 2.9763 | 0%
North Coast | HU_Humboldt | EUREKA E 1104 | 2821 | EUREKA E 1101circuit_breaker | 0 | 0 | 0.78333 | 0 | 0.78333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 5.1064 | 5.1064 | 0%
North Coast | HU_Humboldt | EUREKA E 1104 | 5930 | EUREKA E 110429676 | 0 | 0 | 7.921 | 0 | 7.921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 508 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.50499 | 0.50499 | 0%
North Coast | HU_Humboldt | EUREKA E 1104 | 5664 | EUREKA E 110498682 | 5e-06 | 1.2157 | 1.6818 | 0 | 1.6818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 4.1128e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.3784 | 2.3784 | 0%
North Coast | HU_Humboldt | EUREKA E 1104 | 2661 | EUREKA E 1104circuit_breaker | 0 | 0 | 9.2585 | 0 | 9.2585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 593 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.43203 | 0.43203 | 0%
North Coast | HU_Humboldt | EUREKA E 1104 | 1939 | EUREKA E 1105circuit_breaker | 0 | 0 | 0.2142 | 0 | 0.2142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 18.6737 | 18.6737 | 0%
North Coast | HU_Humboldt | EUREKA E 1104 | 5448 | HARRIS 110866386 | 0 | 0 | 0.44375 | 0 | 0.44375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 9.0141 | 9.0141 | 0%
North Coast | HU_Humboldt | EUREKA E 1104 | 377 | HARRIS 11087920 | 0 | 0 | 0.051326 | 0 | 0.051326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 77.9336 | 77.9336 | 0%
North Coast | HU_Humboldt | EUREKA E 1104 | 2601 | HUMBOLDT BAY 11027598 | 0 | 0 | 1.1502 | 0 | 1.1502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 3.4777 | 3.4777 | 0%
North Coast | HU_Humboldt | FORT BRAGG A 1102 | 5547 | FORT BRAGG A 1104circuit_breaker | 2e-06 | 0.82424 | 0.14811 | 0 | 0.14811 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 92 |  | 19 | 13 | 92 | 19 | 13 | 34.31 | 2.4265e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 128.2864 | 128.2864 | 0%
North Coast | HU_Humboldt | HIGHLANDS 1104 | 5958 | HIGHLANDS 110487040 | 4e-06 | 1.4292 | 0.35682 | 0 | 0.35682 | 0 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 30 |  | 7 | 6 | 29 | 7 | 6 | 12.2 | 2.7988e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 19.6178 | 19.6178 | 0%
North Coast | HU_Humboldt | UKIAH 1115 | 7074 | UKIAH 1111circuit_breaker | 1e-06 | 0.31888 | 0.10455 | 0 | 0.10455 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 52 |  | 11 | 8 | 52 | 11 | 8 | 19.75 | 3.136e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 105.2174 | 105.2174 | 0%
North Coast | NC_North Coast | RIO DELL 1102 | 5774 | RIO DELL 1101circuit_breaker | 1e-06 | 0.70628 | 0.072348 | 0 | 0.072348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 1.4159e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 55.288 | 55.288 | 0%
North Coast | SO_Sonoma | COTATI 1105 | 5160 | COTATI 11052121 | 0.001181 | 1.1332 | 0.098106 | 0.098106 | 0 | 0.098106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.0010422 | 0 | 999999 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0 | 100%
North Coast | SO_Sonoma | COTATI 1105 | 8254 | COTATI 11058459 | 0.075705 | 2.7981 | 0.054356 | 0.054356 | 0 | 0.054356 | 15 | 7 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.027056 | 0 | 999999 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0 | 100%
North Coast | SO_Sonoma | FITCH MOUNTAIN 1113 | 3489 | FITCH MOUNTAIN 1113444 | 2.8e-05 | 3.9195 | 0.088258 | 0 | 0.088258 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 38 |  | 9 | 7 | 38 | 9 | 7 | 15.75 | 7.1438e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 101.9742 | 101.9742 | 0%
North Coast | SO_Sonoma | MOLINO 1103 | 809 | BELLEVUE 1102839 | 0 | 0 | 0.4197 | 0 | 0.4197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 9.5307 | 9.5307 | 0%
North Coast | SO_Sonoma | MOLINO 1103 | 3403 | BELLEVUE 1104564 | 0 | 0 | 0.30246 | 0 | 0.30246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 13.2248 | 13.2248 | 0%
North Coast | SO_Sonoma | MOLINO 1103 | 13 | FULTON 1105142 | 0 | 0 | 0.58466 | 0 | 0.58466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 6.8416 | 6.8416 | 0%
North Coast | SO_Sonoma | MOLINO 1103 | 2195 | MIRABEL 1101254 | 0 | 0 | 0.49318 | 0 | 0.49318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 8.1106 | 8.1106 | 0%
North Coast | SO_Sonoma | MOLINO 1103 | 3189 | MOLINO 1102384 | 0 | 0 | 13.7756 | 0 | 13.7756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.29037 | 0.29037 | 0%
North Coast | SO_Sonoma | MOLINO 1103 | 9227 | MOLINO 1102535 | 0 | 0 | 0.67216 | 0 | 0.67216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 5.951 | 5.951 | 0%
North Coast | SO_Sonoma | MOLINO 1103 | 4298 | MOLINO 1102circuit_breaker | 0 | 0 | 1.0917 | 0 | 1.0917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 3.6641 | 3.6641 | 0%
North Coast | SO_Sonoma | MOLINO 1103 | 5981 | MOLINO 110313219 | 0 | 0 | 2.0881 | 0 | 2.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.9156 | 1.9156 | 0%
North Coast | SO_Sonoma | MOLINO 1103 | 2310 | MOLINO 1103314 | 0 | 0 | 21.4384 | 0 | 21.4384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 846 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.18658 | 0.18658 | 0%
North Coast | SO_Sonoma | MOLINO 1103 | 3428 | MOLINO 11034676 | 0 | 0 | 14.5686 | 0 | 14.5686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.27456 | 0.27456 | 0%
North Coast | SO_Sonoma | MOLINO 1103 | 4826 | MOLINO 11034682 | 0 | 0 | 6.7555 | 0 | 6.7555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.59211 | 0.59211 | 0%
North Coast | SO_Sonoma | MOLINO 1103 | 5856 | MOLINO 110381008 | 0 | 0 | 5.6021 | 0 | 5.6021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.71402 | 0.71402 | 0%
North Coast | SO_Sonoma | MOLINO 1103 | 6300 | MOLINO 1103circuit_breaker | 0 | 0 | 7.1759 | 0 | 7.1759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.55742 | 0.55742 | 0%
North Coast | SO_Sonoma | MOLINO 1103 | 1869 | MOLINO 1104378 | 0 | 0 | 0.68447 | 0 | 0.68447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 5.8439 | 5.8439 | 0%
North Coast | SO_Sonoma | MOLINO 1103 | 5913 | MOLINO 1104circuit_breaker | 0 | 0 | 0.12462 | 0 | 0.12462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 32.0973 | 32.0973 | 0%
North Coast | SO_Sonoma | MOLINO 1103 | 2904 | SANTA ROSA A 1103258 | 0 | 0 | 1.0212 | 0 | 1.0212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 3.9169 | 3.9169 | 0%
North Coast | SO_Sonoma | PENNGROVE 1101 | 1038 | PENNGROVE 1101190 | 0 | 0 | 0.056061 | 0 | 0.056061 | 0.056061 | 2 | 5 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 5 |  | 3 | 0 | 0 | 3 | 0 | 4.11 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 53.5135 | 53.5135 | 0%
North Coast | SO_Sonoma | PETALUMA C 1109 | 5377 | PETALUMA A 0413circuit_breaker | 0 | 0.85158 | 0.16193 | 0 | 0.16193 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 36 |  | 8 | 6 | 36 | 8 | 6 | 14.2 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 49.4035 | 49.4035 | 0%
North Coast | SO_Sonoma | RINCON 1104 | 2796 | RINCON 1104326 | 5e-06 | 3.0764 | 0.30549 | 0 | 0.30549 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 79 |  | 16 | 12 | 79 | 16 | 12 | 29.03 | 1.6253e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 52.3745 | 52.3745 | 0%
North Coast | SO_Sonoma | SALMON CREEK 1101 | 460 | SALMON CREEK 1101circuit_breaker | 0 | 0 | 0.12992 | 0 | 0.12992 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 21 |  | 6 | 5 | 21 | 6 | 5 | 10.11 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 46.1808 | 46.1808 | 0%
North Coast | SO_Sonoma | SANTA ROSA A 1107 | 1176 | SANTA ROSA A 1110circuit_breaker | 4.7e-05 | 6.9783 | 0.50341 | 0 | 0.50341 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 134 |  | 26 | 18 | 134 | 26 | 18 | 47.68 | 6.7352e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 51.6479 | 51.6479 | 0%
North Valley | NV_North Valley | ANDERSON 1103 | 4231 | PANORAMA 11023320 | 0 | 0 | 0.19167 | 0 | 0.19167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 20.8696 | 20.8696 | 0%
North Valley | NV_North Valley | BURNEY 1101 | 5986 | BURNEY 1102circuit_breaker | 6e-06 | 23.9352 | 0.69962 | 0 | 0.69962 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 1 | 227 |  | 43 | 29 | 227 | 43 | 29 | 79.34 | 2.5068e-07 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 61.4618 | 61.4618 | 0%
North Valley | NV_North Valley | COTTONWOOD 1103 | 6401 | COTTONWOOD 110331548 | 0.004729 | 0.34369 | 0.13788 | 0.13788 | 0 | 0.13788 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.01376 | 0 | 999999 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0 | 100%
North Valley | NV_North Valley | HAMILTON BRANCH 1101 | 3976 | HAMILTON BRANCH 110137534 | 0 | 11.3063 | 0.58466 | 0 | 0.58466 | 0 | 261 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 1 | 486 |  | 90 | 60 | 486 | 90 | 60 | 167.04 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 153.9359 | 153.9359 | 0%
North Valley | NV_North Valley | JACINTO 1101 | 7233 | HAMILTON A 11022210 | 0 | 0 | 0.011553 | 0 | 0.011553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 346.2295 | 346.2295 | 0%
North Valley | NV_North Valley | JACINTO 1101 | 6847 | JACINTO 11012062 | 0 | 0 | 15.5015 | 0 | 15.5015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 432 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.25804 | 0.25804 | 0%
North Valley | NV_North Valley | JACINTO 1101 | 4443 | JACINTO 11012460 | 0 | 0 | 9.2917 | 0 | 9.2917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.43049 | 0.43049 | 0%
North Valley | NV_North Valley | JACINTO 1101 | 3519 | JACINTO 11012608 | 0 | 0 | 29.5589 | 0 | 29.5589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.13532 | 0.13532 | 0%
North Valley | NV_North Valley | JACINTO 1101 | 6481 | JACINTO 110163962 | 0 | 0 | 4.3777 | 0 | 4.3777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.91373 | 0.91373 | 0%
North Valley | NV_North Valley | JACINTO 1101 | 6884 | JACINTO 110194868 | 0 | 0 | 12.5506 | 0 | 12.5506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.31871 | 0.31871 | 0%
North Valley | NV_North Valley | JACINTO 1101 | 3983 | JACINTO 1101circuit_breaker | 0 | 0 | 7.6684 | 0 | 7.6684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.52162 | 0.52162 | 0%
North Valley | NV_North Valley | JACINTO 1102 | 24 | JACINTO 11022606 | 0 | 0 | 24.3939 | 0 | 24.3939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 729 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.16398 | 0.16398 | 0%
North Valley | NV_North Valley | JACINTO 1102 | 6574 | JACINTO 110237352 | 0 | 0 | 14.2487 | 0 | 14.2487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.28073 | 0.28073 | 0%
North Valley | NV_North Valley | JACINTO 1102 | 7493 | JACINTO 110245248 | 0 | 0 | 10.911 | 0 | 10.911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.3666 | 0.3666 | 0%
North Valley | NV_North Valley | JACINTO 1102 | 5655 | JACINTO 110247800 | 0 | 0 | 7.975 | 0 | 7.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.50157 | 0.50157 | 0%
North Valley | NV_North Valley | JACINTO 1102 | 3819 | JACINTO 110264198 | 0 | 0 | 9.814 | 0 | 9.814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.40758 | 0.40758 | 0%
North Valley | NV_North Valley | JACINTO 1102 | 234 | JACINTO 110285076 | 0 | 0 | 28.7388 | 0 | 28.7388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 708 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.13918 | 0.13918 | 0%
North Valley | NV_North Valley | JACINTO 1102 | 7816 | JACINTO 110287210 | 0 | 0 | 7.8733 | 0 | 7.8733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.50805 | 0.50805 | 0%
North Valley | NV_North Valley | JACINTO 1102 | 7051 | LOGAN CREEK 21012406 | 0 | 0 | 0.20227 | 0 | 0.20227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 19.7753 | 19.7753 | 0%
North Valley | NV_North Valley | JACINTO 1102 | 1928 | LOGAN CREEK 21012430 | 0 | 0 | 0.8661 | 0 | 0.8661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 4.6184 | 4.6184 | 0%
North Valley | NV_North Valley | JACINTO 1102 | 7107 | ORLAND B 11032204 | 0 | 0 | 0.26761 | 0 | 0.26761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 14.9469 | 14.9469 | 0%
North Valley | NV_North Valley | JACINTO 1102 | 7502 | ORLAND B 11032252 | 0 | 0 | 0.15947 | 0 | 0.15947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 25.0831 | 25.0831 | 0%
North Valley | NV_North Valley | LOS MOLINOS 1102 | 2732 | GERBER 110185172 | 0 | 0 | 0.60208 | 0 | 0.60208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 6.6436 | 6.6436 | 0%
North Valley | NV_North Valley | LOS MOLINOS 1102 | 1688 | LOS MOLINOS 1101circuit_breaker | 0 | 0 | 0.66212 | 0 | 0.66212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 6.0412 | 6.0412 | 0%
North Valley | NV_North Valley | LOS MOLINOS 1102 | 8160 | LOS MOLINOS 11022681 | 0 | 0 | 3.6939 | 0 | 3.6939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.0829 | 1.0829 | 0%
North Valley | NV_North Valley | LOS MOLINOS 1102 | 8051 | LOS MOLINOS 11023302 | 0 | 0 | 25.572 | 0 | 25.572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 686 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.15642 | 0.15642 | 0%
North Valley | NV_North Valley | LOS MOLINOS 1102 | 9124 | LOS MOLINOS 110235730 | 0 | 0 | 5.4572 | 0 | 5.4572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.73298 | 0.73298 | 0%
North Valley | NV_North Valley | LOS MOLINOS 1102 | 251 | LOS MOLINOS 1102circuit_breaker | 0 | 0 | 21.1456 | 0 | 21.1456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.18916 | 0.18916 | 0%
North Valley | NV_North Valley | LOS MOLINOS 1102 | 1230 | VINA 110198144 | 0 | 0 | 0.24924 | 0 | 0.24924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 16.0486 | 16.0486 | 0%
North Valley | NV_North Valley | PANORAMA 1101 | 919 | PANORAMA 1102circuit_breaker | 0 | 0 | 0.052083 | 0.052083 | 0 | 0.052083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 999999 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0 | 100%
North Valley | NV_North Valley | RAWSON 1103 | 902 | DAIRYVILLE 1101147562 | 0 | 0 | 0.086932 | 0 | 0.086932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 46.0131 | 46.0131 | 0%
North Valley | NV_North Valley | SYCAMORE CREEK 1109 | 3068 | SYCAMORE CREEK 1109circuit_breaker | 1.1e-05 | 1.0005 | 0.15568 | 0 | 0.15568 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 21 |  | 6 | 5 | 21 | 6 | 5 | 10.11 | 1.0994e-05 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 38.5401 | 38.5401 | 0%
North Valley | NV_North Valley | SYCAMORE CREEK 1111 | 7226 | ANITA 11062496 | 0 | 0 | 0.10038 | 0.049621 | 0.050758 | 0.10038 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0 | 49.43%
Sierra | SA_Sacramento | DIXON 1103 | 6826 | DAVIS 110712822 | 0 | 0 | 0.14697 | 0 | 0.14697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 27.2165 | 27.2165 | 0%
Sierra | SA_Sacramento | DIXON 1103 | 965 | DIXON 110315137 | 0 | 0 | 4.2271 | 0 | 4.2271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.94628 | 0.94628 | 0%
Sierra | SA_Sacramento | DIXON 1103 | 1872 | DIXON 11035932 | 0 | 0 | 17.6799 | 0 | 17.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.22625 | 0.22625 | 0%
Sierra | SA_Sacramento | DIXON 1103 | 8217 | DIXON 11038202 | 0 | 0 | 25.5373 | 0 | 25.5373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.15663 | 0.15663 | 0%
Sierra | SA_Sacramento | DIXON 1103 | 4245 | DIXON 11038782 | 0 | 0 | 37.4718 | 0 | 37.4718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 844 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.10675 | 0.10675 | 0%
Sierra | SA_Sacramento | DIXON 1103 | 3419 | DIXON 11039732 | 0 | 0 | 24.6415 | 0 | 24.6415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.16233 | 0.16233 | 0%
Sierra | SA_Sacramento | DIXON 1103 | 182 | DIXON 1103circuit_breaker | 0 | 0 | 15.9621 | 0 | 15.9621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.25059 | 0.25059 | 0%
Sierra | SA_Sacramento | DIXON 1103 | 6711 | DIXON 1104circuit_breaker | 0 | 0 | 0.90322 | 0 | 0.90322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 4.4286 | 4.4286 | 0%
Sierra | SA_Sacramento | MADISON 1103 | 9372 | MADISON 110320062 | 0 | 0 | 1.186 | 0 | 1.186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 3.3727 | 3.3727 | 0%
Sierra | SA_Sacramento | MADISON 1103 | 9221 | MADISON 110323452 | 0 | 0 | 4.9644 | 0 | 4.9644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.80574 | 0.80574 | 0%
Sierra | SA_Sacramento | MADISON 1103 | 5789 | MADISON 110353322 | 0 | 0 | 30.5517 | 0 | 30.5517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1067 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.13093 | 0.13093 | 0%
Sierra | SA_Sacramento | MADISON 1103 | 6050 | MADISON 11038822 | 0 | 0 | 20.6248 | 0 | 20.6248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 607 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.19394 | 0.19394 | 0%
Sierra | SA_Sacramento | MADISON 1103 | 4452 | MADISON 1103circuit_breaker | 0 | 0 | 12.0748 | 0 | 12.0748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 432 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.33127 | 0.33127 | 0%
Sierra | SA_Sacramento | MADISON 1103 | 2974 | MADISON 1105circuit_breaker | 0 | 0 | 2.421 | 0 | 2.421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.6522 | 1.6522 | 0%
Sierra | SA_Sacramento | MADISON 1103 | 3427 | MADISON 210134164 | 0 | 0 | 1.0612 | 0 | 1.0612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 3.7694 | 3.7694 | 0%
Sierra | SA_Sacramento | MADISON 1103 | 2290 | MADISON 2101circuit_breaker | 0 | 0 | 0.67216 | 0 | 0.67216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 5.951 | 5.951 | 0%
Sierra | SA_Sacramento | MADISON 2101 | 5079 | MADISON 210144634 | 0 | 0 | 0.17652 | 0 | 0.17652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 22.6609 | 22.6609 | 0%
Sierra | SA_Sacramento | RICE 1104 | 3289 | 133220 | 0 | 0 | 6.0095 | 0 | 6.0095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.66562 | 0.66562 | 0%
Sierra | SA_Sacramento | RICE 1104 | 7375 | 30010 | 0 | 0 | 16.7333 | 0 | 16.7333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 382 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.23904 | 0.23904 | 0%
Sierra | SA_Sacramento | RICE 1104 | 7610 | 3034 | 0 | 0 | 10.1767 | 0 | 10.1767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.39305 | 0.39305 | 0%
Sierra | SA_Sacramento | VACA DIXON 1103 | 5863 | DIXON 110212352 | 0 | 0 | 0.13428 | 0 | 0.13428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 29.7884 | 29.7884 | 0%
Sierra | SA_Sacramento | VACA DIXON 1103 | 6830 | DIXON 11056232 | 0 | 0 | 0.027841 | 0 | 0.027841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 143.6735 | 143.6735 | 0%
Sierra | SA_Sacramento | VACA DIXON 1103 | 3272 | DIXON 1106533554 | 0 | 0 | 0.51269 | 0 | 0.51269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 7.802 | 7.802 | 0%
Sierra | SA_Sacramento | VACA DIXON 1103 | 1971 | PEABODY 210515812 | 0 | 0 | 0.10871 | 0 | 0.10871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 36.7944 | 36.7944 | 0%
Sierra | SA_Sacramento | VACA DIXON 1103 | 4091 | PEABODY 21056313 | 0 | 0 | 0.63333 | 0 | 0.63333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 6.3158 | 6.3158 | 0%
Sierra | SA_Sacramento | VACA DIXON 1103 | 6715 | VACA DIXON 1102circuit_breaker | 0 | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 11.766 | 11.766 | 0%
Sierra | SA_Sacramento | VACA DIXON 1103 | 6686 | VACA DIXON 110339500 | 0 | 0 | 15.6381 | 0 | 15.6381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.25579 | 0.25579 | 0%
Sierra | SA_Sacramento | VACA DIXON 1103 | 849 | VACA DIXON 110340832 | 0 | 0 | 33.0371 | 0 | 33.0371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1087 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.12108 | 0.12108 | 0%
Sierra | SA_Sacramento | VACA DIXON 1103 | 507 | VACA DIXON 11035187 | 0 | 0 | 5.2633 | 0 | 5.2633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.75999 | 0.75999 | 0%
Sierra | SA_Sacramento | VACA DIXON 1103 | 6272 | VACA DIXON 110355570 | 0 | 0 | 3.7519 | 0 | 3.7519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 1.0661 | 1.0661 | 0%
Sierra | SA_Sacramento | VACA DIXON 1103 | 1110 | VACA DIXON 11035602 | 0 | 0 | 12.1008 | 0 | 12.1008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.33056 | 0.33056 | 0%
Sierra | SA_Sacramento | VACA DIXON 1103 | 6022 | VACA DIXON 110365434 | 0 | 0 | 10.983 | 0 | 10.983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.3642 | 0.3642 | 0%
Sierra | SA_Sacramento | VACA DIXON 1103 | 5228 | VACA DIXON 11036822 | 0 | 0 | 33.7725 | 0 | 33.7725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.11844 | 0.11844 | 0%
Sierra | SA_Sacramento | VACA DIXON 1103 | 5037 | VACA DIXON 110376158 | 0 | 0 | 6.9794 | 0 | 6.9794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.57312 | 0.57312 | 0%
Sierra | SA_Sacramento | VACA DIXON 1103 | 8692 | VACA DIXON 1103circuit_breaker | 0 | 0 | 1.9161 | 0 | 1.9161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 2.0876 | 2.0876 | 0%
Sierra | SA_Sacramento | VACA DIXON 1103 | 3930 | VACA DIXON 1105circuit_breaker | 0 | 0 | 0.64527 | 0 | 0.64527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 6.199 | 6.199 | 0%
Sierra | SA_Sacramento | VACA DIXON 1103 | 8968 | VACA DIXON 11065752 | 0 | 0 | 0.32519 | 0 | 0.32519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 12.3005 | 12.3005 | 0%
Sierra | SA_Sacramento | VACA DIXON 1103 | 630 | VACA DIXON 1106circuit_breaker | 0 | 0 | 0.14451 | 0 | 0.14451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 27.6802 | 27.6802 | 0%
Sierra | SA_Sacramento | VACA DIXON 1103 | 5993 | WINTERS 110223202 | 0 | 0 | 0.04053 | 0 | 0.04053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 98.6916 | 98.6916 | 0%
Sierra | SA_Sacramento | ZAMORA 1107 | 2573 | WOODLAND 1102circuit_breaker | 0 | 0 | 0.084091 | 0 | 0.084091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 47.5676 | 47.5676 | 0%
Sierra | SA_Sacramento | ZAMORA 1107 | 5306 | WOODLAND 111021288 | 0 | 0 | 1.0794 | 0 | 1.0794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 3.7059 | 3.7059 | 0%
Sierra | SA_Sacramento | ZAMORA 1107 | 4986 | ZAMORA 110536762 | 0 | 0 | 0.46155 | 0 | 0.46155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 8.6664 | 8.6664 | 0%
Sierra | SA_Sacramento | ZAMORA 1107 | 4420 | ZAMORA 1105circuit_breaker | 0 | 0 | 0.86174 | 0 | 0.86174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 4.6418 | 4.6418 | 0%
Sierra | SA_Sacramento | ZAMORA 1107 | 6130 | ZAMORA 1106circuit_breaker | 0 | 0 | 0.096591 | 0 | 0.096591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 41.4118 | 41.4118 | 0%
Sierra | SA_Sacramento | ZAMORA 1107 | 7913 | ZAMORA 110723345 | 0 | 0 | 4.3259 | 0 | 4.3259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.92465 | 0.92465 | 0%
Sierra | SA_Sacramento | ZAMORA 1107 | 7682 | ZAMORA 110723472 | 0 | 0 | 16.7771 | 0 | 16.7771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.23842 | 0.23842 | 0%
Sierra | SA_Sacramento | ZAMORA 1107 | 4685 | ZAMORA 110769308 | 0 | 0 | 21.7006 | 0 | 21.7006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 708 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.18433 | 0.18433 | 0%
Sierra | SA_Sacramento | ZAMORA 1107 | 4454 | ZAMORA 11078892 | 0 | 0 | 22.5973 | 0 | 22.5973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 761 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.17701 | 0.17701 | 0%
Sierra | SA_Sacramento | ZAMORA 1107 | 7939 | ZAMORA 1107circuit_breaker | 0 | 0 | 8.4284 | 0 | 8.4284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.47459 | 0.47459 | 0%
Sierra | SI_Sierra | BANGOR 1101 | 2517 | BANGOR 1101478754 | 0.22905 | 4.6073 | 0.14394 | 0.14394 | 0 | 0.14394 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.049715 | 0 | 999999 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0 | 0 | 100%
Sierra | SI_Sierra | BRUNSWICK 1110 | 4140 | BRUNSWICK 111095576 | 5.8e-05 | 13.4196 | 0.7089 | 0 | 0.7089 | 0.51705 | 178 | 49 | 49 | 36 | 0 | 0 | 0 | 35 | 0.27064 | 140 |  | 66 | 47 | 91 | 66 | 47 | 98.61 | 4.322e-06 | 0 | 999999 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 93.1018 | 93.1018 | 0%
Sierra | SI_Sierra | EL DORADO PH 2101 | 2522 | EL DORADO PH 210113362 | 0 | 0 | 0.38712 | 0 | 0.38712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 10.3327 | 10.3327 | 0%
Sierra | SI_Sierra | HORSESHOE 1101 | 3829 | HORSESHOE 110151538 | 0 | 0 | 0.066477 | 0 | 0.066477 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 18 |  | 5 | 4 | 18 | 5 | 4 | 8.47 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 75.2137 | 75.2137 | 0%
Sierra | SI_Sierra | PLACER 1103 | 4418 | BELL 111050182 | 6e-06 | 0.80784 | 0.023106 | 0 | 0.023106 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 20 |  | 5 | 5 | 20 | 5 | 5 | 8.65 | 7.4272e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 216.3934 | 216.3934 | 0%
Sierra | SI_Sierra | PLACER 1104 | 4652 | PLACER 110451734 | 6e-06 | 0.63592 | 0.035985 | 0 | 0.035985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 9.4351e-06 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 111.1579 | 111.1579 | 0%
Sierra | SI_Sierra | TAMARACK 1102 | 6554 | TAMARACK 1102circuit_breaker | 0 | 0 | 7.7777 | 0 | 7.7777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 1 | 12 |  | 4 | 4 | 12 | 4 | 4 | 6.56 | 0 | 0 | 999999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6. >50% | 6. >50% | 0 | 0.51429 | 0.51429 | 0%

## Groups of CPZ_'21 Only (hidden)
Change Group Names-> | Commitments for 2021 | Completed Work | WGC Approved Plan (1005 mi) | 1800 Mi Plan Balance | Group5
Central Coast | SOBRANTE 1102circuit_breaker | PUTAH CREEK 11033783 | AUBERRY 1101R2578 | PUEBLO 2103678
| SILVERADO 2104632 | PUTAH CREEK 11028352 | AUBERRY 1102circuit_breaker | MARIPOSA 210237282
| SILVERADO 210478268 | COARSEGOLD 21046288 | TIVY VALLEY 1107584840 | BRIDGEVILLE 1102circuit_breaker
| WOODSIDE 11018974 | COARSEGOLD 21045310 | COARSEGOLD 210310820 | FRUITLAND 114293234
| BIG BASIN 1102circuit_breaker | BANGOR 110155206 | MARIPOSA 210210880 | GARBERVILLE 110256048
| CAMP EVERS 210510912 | COARSEGOLD 21045525 | OAKHURST 110110090 | LAYTONVILLE 1102572
| PASO ROBLES 1103N58 | CLEAR LAKE 1101486 | OAKHURST 110363334 | WILLITS 110391810
| PASO ROBLES 1104P02 | OREGON TRAIL 110335002 | OAKHURST 1103circuit_breaker | FITCH MOUNTAIN 11136751
| PASO ROBLES 1107circuit_breaker | HIGHLANDS 1103828 | SAN JOAQUIN #2 110310320 | BIG BEND 11021972
| SAN LUIS OBISPO 1107V60 | PASO ROBLES 1103N58 | FORT SEWARD 11211690 | CEDAR CREEK 11011608
| SANTA YNEZ 1101circuit_breaker | PUTAH CREEK 110267858 | LAYTONVILLE 1102500 | CEDAR CREEK 11011656
| SANTA YNEZ 1104circuit_breaker | KESWICK 110148480 | MIDDLETOWN 1101622 | CHALLENGE 11021064
| ZACA 1102Y48 | CLARKSVILLE 2105circuit_breaker | PHILO 110137222 | APPLE HILL 21021532
| MORGAN HILL 2105XR564 | PUTAH CREEK 11033851 | UKIAH 1111534 | APPLE HILL 2102circuit_breaker
| GIRVAN 11011330 | COARSEGOLD 2104369777 | WILLITS 1102circuit_breaker | BANGOR 11017446
| GIRVAN 1101323094 | PANORAMA 1101circuit_breaker | RIO DELL 11024230 | DIAMOND SPRINGS 11057722
| OREGON TRAIL 11031500 | WOODWARD 2108R2860 | GEYSERVILLE 1101166 | PIKE CITY 1101circuit_breaker
| BRUNSWICK 11032784 | COTTONWOOD 11031344 | SALMON CREEK 110188998
| BRUNSWICK 1103circuit_breaker | PUTAH CREEK 1102circuit_breaker | CEDAR CREEK 11011664
| BRUNSWICK 11041020 | PASO ROBLES 1103N54 | COTTONWOOD 110168190
| BRUNSWICK 11042112 | PETALUMA C 1108618 | DESCHUTES 11011580
|  | COTTONWOOD 11031348 | DESCHUTES 11041370
|  | COARSEGOLD 21045300 | DESCHUTES 110449024
|  | PASO ROBLES 11032731 | DESCHUTES 11049726
|  | COARSEGOLD 210410400 | DESCHUTES 1104circuit_breaker
|  | VACAVILLE 111113652 | OREGON TRAIL 11041574
|  | BUELLTON 1102circuit_breaker | OREGON TRAIL 11041634
|  | COARSEGOLD 210410335 | OREGON TRAIL 1104circuit_breaker
|  | BANGOR 110182350 | RED BLUFF 11011334
|  | CLARK ROAD 1102circuit_breaker | STILLWATER 11021644
|  | BUELLTON 1102Y50 | STILLWATER 110248952
|  | CORRAL 110136652 | STILLWATER 1102circuit_breaker
|  | OREGON TRAIL 1103circuit_breaker | WYANDOTTE 110979932
|  | CLARK ROAD 11022582 | VACAVILLE 110838316
|  | CORRAL 1101circuit_breaker | BELL 11082202
|  | CORRAL 110112608 | BROWNS VALLEY 110193870
|  | CLAYTON 22122944 | DIAMOND SPRINGS 110519910
|  | COTATI 110536536 | HIGGINS 110950072
|  | CORNING 110182846 | HIGGINS 1109circuit_breaker
|  | COTTONWOOD 11039072 | LINCOLN 11042070
|  | VACAVILLE 1111circuit_breaker | MOUNTAIN QUARRIES 2101circuit_breaker
|  | CORRAL 110175204 | PENRYN 11032198
|  | COARSEGOLD 210490356 | SHINGLE SPRINGS 210912392
|  | COARSEGOLD 210410030 | SHINGLE SPRINGS 210913322
|  | COTTONWOOD 11031616 | WISE 11022054
|  | CORNING 110164090 | WISE 11022230
HIGHLANDS 1102628
RED BLUFF 110451238
PASO ROBLES 110355374
PASO ROBLES 110359763
CORRAL 110112612
CLARKSVILLE 210419632
SHINGLE SPRINGS 110419502
COTTONWOOD 110335470
CORNING 110185162
KESWICK 11011586
DIAMOND SPRINGS 1107circuit_breaker
OLETA 11011208
RED BLUFF 11041566
CORRAL 110112606
RACETRACK 1704circuit_breaker
CORNING 110185152
RED BLUFF 1104circuit_breaker
PUEBLO 2102618
CLARKSVILLE 210413352
HIGHLANDS 1103482
BANGOR 11011958
BANGOR 11011958
COTATI 1105616
PETALUMA C 1108208
GOLDTREE 1105circuit_breaker
SILVERADO 2104726
CLARK ROAD 110281296
MERCED FALLS 110238748
BRIDGEVILLE 110169866
CHOLAME 2102X06
OREGON TRAIL 11031448
OREGON TRAIL 11031448
COTATI 1102681
MERCED FALLS 11029470
PUTAH CREEK 110264044
PUTAH CREEK 110264044
COTATI 1105634
CLAYTON 2212Y504R
CORNING 110187304
CLARKSVILLE 210419772
CLAY 110113442
OILFIELDS 1103N46
POSO MOUNTAIN 21013990
HIGHLANDS 110275140
BRIDGEVILLE 1101circuit_breaker
WOODACRE 110191900
LAKEVILLE 1102280
POSO MOUNTAIN 21012181
WILLITS 11044650
MERCED FALLS 110287352
OAKHURST 11016220
KONOCTI 1102596
CLARK ROAD 11022584
RED BLUFF 11041302
REDBUD 1101454
WOODWARD 210878448
COTATI 1102circuit_breaker
KESWICK 11011590
NARROWS 2102circuit_breaker
CURTIS 17039180
PANORAMA 11019092
NARROWS 21022220
KESWICK 11019712
NARROWS 21022718
LAKEVILLE 11023341
PUEBLO 2102circuit_breaker
COTATI 1105328
CLARK ROAD 11022044
COARSEGOLD 21045516
MERCED FALLS 110285002
COTATI 1102260
CHOLAME 2102X10
COTATI 1102464
WILLITS 110434008
CURTIS 17036064
BELL 11082226
LAKEVILLE 110287432
OREGON TRAIL 110346860
EEL RIVER 11024814
COTATI 1102462
COTATI 11055156
PETALUMA C 1108632
RACETRACK 170455798
PASO ROBLES 1103N52
OLETA 110151740
BANGOR 11011806
FULTON 110777670
RESERVATION ROAD 1101circuit_breaker
PEORIA 170459596
OILFIELDS 1103N62
SISQUOC 1102M54
OILFIELDS 1103N48
MIDDLETOWN 11011079
POSO MOUNTAIN 21014456
CHOLAME 21025597
MERCED FALLS 110222774
FREMONT 1104MR707
SUNOL 1101circuit_breaker
TEJON 11022455
CURTIS 1703circuit_breaker
HALF MOON BAY 1103circuit_breaker
TEJON 11023751
BEAR VALLEY 210110000
CLAYTON 2212circuit_breaker
MERCED FALLS 110222772
TEJON 11023760
BEAR VALLEY 210110019
MORAGA 110531512
MERCED FALLS 1102circuit_breaker
PEORIA 1704circuit_breaker
SISQUOC 1102M52
CAMBRIA 1101V76
RESERVATION ROAD 11013026
CAMBRIA 1101circuit_breaker
PEORIA 170413490
MERCED FALLS 11029460
PUEBLO 2102698
VALLEY VIEW 1106circuit_breaker
LAURELES 1111432
PEORIA 170488630
HIGHLANDS 1102556
LAURELES 11112020
LAURELES 1111circuit_breaker
OAKLAND X 1104CR214
OAKLAND X 1104CR288
LAURELES 11116617
MORAGA 110183424
LAURELES 11112028
LAURELES 11116421
MORAGA 110518396
LAURELES 111184523
VALLEY VIEW 1106P176
OILFIELDS 11032757
PETALUMA C 1108636
SHINGLE SPRINGS 210551738
PASO ROBLES 1103N04
OILFIELDS 11035175
GOLDTREE 1107circuit_breaker
CORNING 110135974
POSO MOUNTAIN 21011703
OILFIELDS 1103N40
KERN OIL 110646960
OILFIELDS 1103N64
OILFIELDS 1103N42
TIVY VALLEY 110737522
PETALUMA C 1108628
OILFIELDS 11037006
KERN OIL 11063301
POSO MOUNTAIN 2101circuit_breaker
COTTONWOOD 1103circuit_breaker
PETALUMA C 1108296
OILFIELDS 1103N44
OILFIELDS 110383158
PASO ROBLES 1103N50

## Groups of CPZ_'21-'23 (hidden)
Change Group Names-> | Completed Work | 2021 | 2022 | 2023 | SH or >90% Complete | Change Control Proposal
Central Coast | PUTAH CREEK 11033783 | AUBERRY 1101R2578 | ANTLER 11011378 | ANTLER 11011376 | CLAYTON 22122944 | CALISTOGA 1101734
| PUTAH CREEK 11028352 | AUBERRY 1102circuit_breaker | APPLE HILL 210277546 | APPLE HILL 11038412 | CLAYTON 221296224 | CALISTOGA 1101736
| COARSEGOLD 21046288 | TIVY VALLEY 1107584840 | AUBERRY 1101circuit_breaker | APPLE HILL 2102186912 | CLAYTON 2212circuit_breaker | PUEBLO 210378504
| COARSEGOLD 21045310 | COARSEGOLD 210310820 | CALISTOGA 1101734 | APPLE HILL 21026552 | KIRKER 2104442850 | CALISTOGA 1101890
| BANGOR 110155206 | MARIPOSA 210210880 | CALISTOGA 1101736 | AUBERRY 110237466 | MORAGA 1101108540 | CALISTOGA 110189150
| COARSEGOLD 21045525 | OAKHURST 110110090 | CHALLENGE 1101circuit_breaker | AUBERRY 1102R1013 | ROSSMOOR 1102circuit_breaker | SANTA YNEZ 1104Y04
| CLEAR LAKE 1101486 | OAKHURST 110363334 | CHALLENGE 11025462 | AUBERRY 1102R2850 | TIDEWATER 210614072 | SANTA YNEZ 110477098
| OREGON TRAIL 110335002 | OAKHURST 1103circuit_breaker | CHALLENGE 1102circuit_breaker | BANGOR 110182350 | OAKLAND K 1102circuit_breaker | OCEANO 1104Q10
| HIGHLANDS 1103828 | SAN JOAQUIN #2 110310320 | COARSEGOLD 2103circuit_breaker | BELL 11085703 | NORTH DUBLIN 2101circuit_breaker | AUBERRY 1101circuit_breaker
| PASO ROBLES 1103N58 | FORT SEWARD 11211690 | COTTONWOOD 11011610 | BONNIE NOOK 1102circuit_breaker | CALISTOGA 1101734 | COARSEGOLD 21045310
| PUTAH CREEK 110267858 | LAYTONVILLE 1102500 | COTTONWOOD 11021578 | BRIDGEVILLE 110237486 | LAS GALLINAS A 110599904 | TIVY VALLEY 1107869946
| KESWICK 110148480 | MIDDLETOWN 1101622 | DESCHUTES 11011380 | BROWNS VALLEY 11011268 | PUEBLO 2102698 | COARSEGOLD 21045300
| CLARKSVILLE 2105circuit_breaker | PHILO 110137222 | DESCHUTES 1101circuit_breaker | BRUNSWICK 11052140 | SILVERADO 210258626 | WILLITS 1104934
| PUTAH CREEK 11033851 | UKIAH 1111534 | DESCHUTES 11041582 | CALISTOGA 110189150 | SILVERADO 2104722 | MOLINO 110266006
| COARSEGOLD 2104369777 | WILLITS 1102circuit_breaker | DOBBINS 11011264 | CALPELLA 11011204 | SILVERADO 2104726 | UPPER LAKE 1101412
| PANORAMA 1101circuit_breaker | RIO DELL 11024230 | EL DORADO PH 210126000 | CALPELLA 11013419 | SILVERADO 2105658898 | KONOCTI 1102circuit_breaker
| WOODWARD 2108R2860 | GEYSERVILLE 1101166 | ELK CREEK 11012106 | CEDAR CREEK 1101circuit_breaker | TULUCAY 1101628 | OREGON TRAIL 1102circuit_breaker
| COTTONWOOD 11031344 | SALMON CREEK 110188998 | FITCH MOUNTAIN 111324918 | CHALLENGE 11015460 | CAMP EVERS 21065020 | WYANDOTTE 11071026
| PUTAH CREEK 1102circuit_breaker | CEDAR CREEK 11011664 | FITCH MOUNTAIN 11134566 | CHALLENGE 11021902 | LAURELES 11112020 | WYANDOTTE 110777578
| PASO ROBLES 1103N54 | COTTONWOOD 110168190 | FORT ROSS 112170288 | CLOVERDALE 1101112 | LAURELES 11112028 | CLARK ROAD 11022582
| PETALUMA C 1108618 | DESCHUTES 11011580 | FORT SEWARD 11211602 | CLOVERDALE 1101circuit_breaker | LAURELES 1111432 | WYANDOTTE 110737472
| COTTONWOOD 11031348 | DESCHUTES 11041370 | FORT SEWARD 1122circuit_breaker | COLUMBIA HILL 11012212 | LAURELES 11116421 | KESWICK 110148480
| COARSEGOLD 21045300 | DESCHUTES 110449024 | FRUITLAND 114195324 | COTTONWOOD 11029026 | LAURELES 11116617 | BELL 110750172
| PASO ROBLES 11032731 | DESCHUTES 11049726 | FRUITLAND 11426054 | DIAMOND SPRINGS 110610587 | LAURELES 111184523 | PENRYN 1103circuit_breaker
| COARSEGOLD 210410400 | DESCHUTES 1104circuit_breaker | FRUITLAND 114263170 | DOBBINS 11011808 | LAURELES 1111circuit_breaker | BANGOR 110180670
| VACAVILLE 111113652 | OREGON TRAIL 11041574 | GARBERVILLE 11022500 | FITCH MOUNTAIN 1113356 | RESERVATION ROAD 11013026 | DIAMOND SPRINGS 1107circuit_breaker
| BUELLTON 1102circuit_breaker | OREGON TRAIL 11041634 | GARBERVILLE 11024744 | FITCH MOUNTAIN 1113583202 | RESERVATION ROAD 1101circuit_breaker | PUTAH CREEK 110267858
| COARSEGOLD 210410335 | OREGON TRAIL 1104circuit_breaker | GARBERVILLE 11028652 | FORESTHILL 11022106 | LOS GATOS 1106LB44 | BANGOR 110182350
| BANGOR 110182350 | RED BLUFF 11011334 | GEYSERVILLE 110179788 | FORT ROSS 1121204 | BUELLTON 1102circuit_breaker
| CLARK ROAD 1102circuit_breaker | STILLWATER 11021644 | GRASS VALLEY 11032180 | FORT ROSS 11214947 | BUELLTON 1102Y50
| BUELLTON 1102Y50 | STILLWATER 110248952 | HIGGINS 1103circuit_breaker | FORT ROSS 1121circuit_breaker | CAMBRIA 1101circuit_breaker
| CORRAL 110136652 | STILLWATER 1102circuit_breaker | HIGGINS 110950078 | FRUITLAND 114137410 | CAMBRIA 1101V76
| OREGON TRAIL 1103circuit_breaker | WYANDOTTE 110979932 | HOOPA 11013174 | FRUITLAND 1141circuit_breaker | CHOLAME 21025597
| CLARK ROAD 11022582 | VACAVILLE 110838316 | HOOPA 11013290 | FRUITLAND 11426064 | CHOLAME 2102X06
| CORRAL 1101circuit_breaker | BELL 11082202 | JESSUP 110276068 | FRUITLAND 1142circuit_breaker | CHOLAME 2102X10
| CORRAL 110112608 | BROWNS VALLEY 110193870 | KANAKA 110165606 | FULTON 1107214 | GOLDTREE 1105circuit_breaker
| CLAYTON 22122944 | DIAMOND SPRINGS 110519910 | KONOCTI 1102circuit_breaker | GARBERVILLE 11011514 | GOLDTREE 1107circuit_breaker
| COTATI 110536536 | HIGGINS 110950072 | LAYTONVILLE 110237586 | GARBERVILLE 11011604 | OILFIELDS 11032757
| CORNING 110182846 | HIGGINS 1109circuit_breaker | LAYTONVILLE 1102circuit_breaker | GARBERVILLE 11011750 | OILFIELDS 11035175
| COTTONWOOD 11039072 | LINCOLN 11042070 | MARIPOSA 210237282 | GARBERVILLE 11011770 | OILFIELDS 11037006
| VACAVILLE 1111circuit_breaker | MOUNTAIN QUARRIES 2101circuit_breaker | MARIPOSA 210237288 | GARBERVILLE 11012026 | OILFIELDS 110383158
| CORRAL 110175204 | PENRYN 11032198 | MARIPOSA 21029590 | GARBERVILLE 110135706 | OILFIELDS 1103N40
| COARSEGOLD 210490356 | SHINGLE SPRINGS 210912392 | MOLINO 110266006 | GARBERVILLE 110139524 | OILFIELDS 1103N42
| COARSEGOLD 210410030 | SHINGLE SPRINGS 210913322 | NARROWS 21011202 | GARBERVILLE 1101circuit_breaker | OILFIELDS 1103N44
| COTTONWOOD 11031616 | WISE 11022054 | NARROWS 21052228 | GARBERVILLE 11026084 | OILFIELDS 1103N46
| CORNING 110164090 | WISE 11022230 | NARROWS 21052748 | GARBERVILLE 1102circuit_breaker | OILFIELDS 1103N48
| HIGHLANDS 1102628 | LAS GALLINAS A 110599904 | NARROWS 21057203 | GRASS VALLEY 11032110 | OILFIELDS 1103N62
| RED BLUFF 110451238 | DESCHUTES 11049718 | PENRYN 11051342 | HALSEY 11012414 | OILFIELDS 1103N64
| PASO ROBLES 110355374 | VACA DIXON 110540092 | PHILO 11013700 | HARTLEY 1101698 | PASO ROBLES 11032731
| PASO ROBLES 110359763 | PUEBLO 2103678 | PHILO 1101circuit_breaker | HIGGINS 110332120 | PASO ROBLES 110355374
| CORRAL 110112612 | OAKHURST 11015490 | PIKE CITY 11011720 | HIGGINS 11077559 | PASO ROBLES 110359763
| CLARKSVILLE 210419632 | BRIDGEVILLE 1102circuit_breaker | PIKE CITY 1102circuit_breaker | HOOPA 11013304 | PASO ROBLES 1103N04
| SHINGLE SPRINGS 110419502 | FRUITLAND 114293234 | PLACERVILLE 21061104 | HOPLAND 11014626 | PASO ROBLES 1103N50
| COTTONWOOD 110335470 | GARBERVILLE 110256048 | PLACERVILLE 21067522 | JAMESON 11057652 | PASO ROBLES 1103N52
| CORNING 110185162 | LAYTONVILLE 1102572 | RED BLUFF 11031702 | JESSUP 11011496 | PASO ROBLES 1103N54
| KESWICK 11011586 | WILLITS 110391810 | RIO DELL 11021504 | JESSUP 110141356 | SAN LUIS OBISPO 1108337126
| DIAMOND SPRINGS 1107circuit_breaker | FITCH MOUNTAIN 11136751 | SAN JOAQUIN #2 1103circuit_breaker | JESSUP 11021550 | SISQUOC 1102M52
| OLETA 11011208 | BIG BEND 11021972 | SAND CREEK 110345190 | JESSUP 11023105 | SISQUOC 1102M54
| RED BLUFF 11041566 | CEDAR CREEK 11011608 | SHINGLE SPRINGS 210519522 | JESSUP 110296554 | TIVY VALLEY 110737522
| CORRAL 110112606 | CEDAR CREEK 11011656 | SHINGLE SPRINGS 21099372 | KANAKA 11011034 | WOODWARD 210878448
| RACETRACK 1704circuit_breaker | CHALLENGE 11021064 | SHINGLE SPRINGS 2109circuit_breaker | KANAKA 110183288 | WOODWARD 2108R2860
| CORNING 110185152 | APPLE HILL 21021532 | TIVY VALLEY 1107869946 | KONOCTI 110275382 | KERN OIL 110646960
| RED BLUFF 1104circuit_breaker | APPLE HILL 2102circuit_breaker | TIVY VALLEY 1107R1817 | LAYTONVILLE 110189606 | POSO MOUNTAIN 21011703
| PUEBLO 2102618 | BANGOR 11017446 | UKIAH 1114408 | LAYTONVILLE 110268436 | POSO MOUNTAIN 21012181
| CLARKSVILLE 210413352 | BELL 11072400 | VOLTA 110180454 | LINCOLN 110195756 | POSO MOUNTAIN 21013990
| HIGHLANDS 1103482 | DIAMOND SPRINGS 11057722 | VOLTA 110237350 | LINCOLN 110451756 | POSO MOUNTAIN 21014456
| BANGOR 11011958 | PIKE CITY 1101circuit_breaker | WEST POINT 11024788 | LOW GAP 11012094 | POSO MOUNTAIN 2101circuit_breaker
| BANGOR 11011958 | SOBRANTE 1102circuit_breaker | WHITMORE 11011598 | LOW GAP 110137498 | POSO MOUNTAIN 2103circuit_breaker
| COTATI 1105616 | SILVERADO 2104632 | WILLITS 1103826 | LOW GAP 11014086 | POSO MOUNTAIN 2104circuit_breaker
| PETALUMA C 1108208 | SILVERADO 210478268 | WISE 1102307494 | LOW GAP 11014160 | TEJON 11022455
| GOLDTREE 1105circuit_breaker | WOODSIDE 11018974 | WOODACRE 1102circuit_breaker | MARIPOSA 210110990 | TEJON 11023751
| SILVERADO 2104726 | BIG BASIN 1102circuit_breaker | WOODSIDE 11018884 | MARIPOSA 21019400 | TEJON 11023760
| CLARK ROAD 110281296 | CAMP EVERS 210510912 | WYANDOTTE 11031974 | MENDOCINO 110148750 | CORRAL 110112606
| MERCED FALLS 110238748 | PASO ROBLES 1103N58 | WYANDOTTE 11031976 | MIDDLETOWN 1101548 | CORRAL 110112612
| BRIDGEVILLE 110169866 | PASO ROBLES 1104P02 | WYANDOTTE 110913052 | MIDDLETOWN 1103830 | CORRAL 110136652
| CHOLAME 2102X06 | PASO ROBLES 1107circuit_breaker | ZACA 1102Y54 | MOLINO 1102104 | CORRAL 110175204
| OREGON TRAIL 11031448 | SAN LUIS OBISPO 1107V60 |  | MOUNTAIN QUARRIES 21011102 | CORRAL 1101circuit_breaker
| OREGON TRAIL 11031448 | SANTA YNEZ 1101circuit_breaker |  | NARROWS 21052216 | FROGTOWN 17011623
| COTATI 1102681 | SANTA YNEZ 1104circuit_breaker |  | NARROWS 2105circuit_breaker | PINE GROVE 11021222
| MERCED FALLS 11029470 | ZACA 1102Y48 |  | OREGON TRAIL 11021382 | SALT SPRINGS 21023142
| PUTAH CREEK 110264044 | MORGAN HILL 2105XR564 |  | ORO FINO 11022096 | WEST POINT 110113444
| PUTAH CREEK 110264044 | GIRVAN 11011330 |  | PENRYN 1103660 | BEAR VALLEY 210110019
| COTATI 1105634 | GIRVAN 11011636 |  | PENRYN 1103circuit_breaker | COARSEGOLD 2104circuit_breaker
| CLAYTON 2212Y504R | GIRVAN 1101323094 |  | PENRYN 11072706 | COARSEGOLD 210410030
| CORNING 110187304 | GIRVAN 11019732 |  | PINE GROVE 11023172 | COARSEGOLD 210410335
| CLARKSVILLE 210419772 | OREGON TRAIL 11031500 |  | PLACER 1103circuit_breaker | COARSEGOLD 210410400
| CLAY 110113442 | BRUNSWICK 11032784 |  | PUEBLO 210378504 | COARSEGOLD 21045516
| OILFIELDS 1103N46 | BRUNSWICK 1103circuit_breaker |  | REDBUD 1101323962 | COARSEGOLD 210490356
| POSO MOUNTAIN 21013990 | BRUNSWICK 11041020 |  | SAN JOAQUIN #3 1103circuit_breaker | MARIPOSA 210197142
| HIGHLANDS 110275140 | BRUNSWICK 11042112 |  | SANTA YNEZ 1104Y04 | MARIPOSA 2102241564
| BRIDGEVILLE 1101circuit_breaker |  |  | SHEPHERD 2111R1400 | MARIPOSA 2102594143
| WOODACRE 110191900 |  |  | SHINGLE SPRINGS 1103circuit_breaker | MARIPOSA 2102circuit_breaker
| LAKEVILLE 1102280 |  |  | SHINGLE SPRINGS 210851476 | MERCED FALLS 110222772
| POSO MOUNTAIN 21012181 |  |  | SHINGLE SPRINGS 210935598 | MERCED FALLS 110222774
| WILLITS 11044650 |  |  | SHINGLE SPRINGS 210961892 | MERCED FALLS 110238748
| MERCED FALLS 110287352 |  |  | SHINGLE SPRINGS 21107742 | MERCED FALLS 110285002
| OAKHURST 11016220 |  |  | STILLWATER 110148950 | MERCED FALLS 110287352
| KONOCTI 1102596 |  |  | STILLWATER 11021466 | MERCED FALLS 11029460
| CLARK ROAD 11022584 |  |  | TYLER 11051536 | MERCED FALLS 11029470
| RED BLUFF 11041302 |  |  | TYLER 11051704 | MERCED FALLS 1102circuit_breaker
| REDBUD 1101454 |  |  | TYLER 110585132 | MIWUK 1701953336
| WOODWARD 210878448 |  |  | VACAVILLE 11046542 | MIWUK 1701circuit_breaker
| COTATI 1102circuit_breaker |  |  | VACAVILLE 11088762 | MIWUK 170238218
| KESWICK 11011590 |  |  | VOLTA 11021646 | MIWUK 17026018
| NARROWS 2102circuit_breaker |  |  | WHITMORE 11011594 | MIWUK 17028090
| CURTIS 17039180 |  |  | WILLITS 11032500 | MIWUK 1702circuit_breaker
| PANORAMA 11019092 |  |  | WILLITS 11032506 | OAKHURST 11016220
| NARROWS 21022220 |  |  | WILLITS 110337506 | BRIDGEVILLE 1101circuit_breaker
| KESWICK 11019712 |  |  | WILLITS 1103968 | HIGHLANDS 1102628
| NARROWS 21022718 |  |  | WILLITS 1104934 | HIGHLANDS 110275140
| LAKEVILLE 11023341 |  |  | WISE 1102697216 | HIGHLANDS 1103482
| PUEBLO 2102circuit_breaker |  |  | WOODSIDE 110147872 | KONOCTI 1102532
| COTATI 1105328 |  |  |  | MIDDLETOWN 11014646
| CLARK ROAD 11022044 |  |  |  | MIDDLETOWN 110148212
| COARSEGOLD 21045516 |  |  |  | MIDDLETOWN 1101548
| MERCED FALLS 110285002 |  |  |  | MIDDLETOWN 1101circuit_breaker
| COTATI 1102260 |  |  |  | MIDDLETOWN 1103830
| CHOLAME 2102X10 |  |  |  | POTTER VALLEY P H 110564118
| COTATI 1102464 |  |  |  | UPPER LAKE 1101circuit_breaker
| WILLITS 110434008 |  |  |  | WILLITS 11044650
| CURTIS 17036064 |  |  |  | COTATI 1102circuit_breaker
| BELL 11082226 |  |  |  | COTATI 11052121
| LAKEVILLE 110287432 |  |  |  | COTATI 1105616
| OREGON TRAIL 110346860 |  |  |  | COTATI 11058459
| EEL RIVER 11024814 |  |  |  | FITCH MOUNTAIN 111324918
| COTATI 1102462 |  |  |  | LAKEVILLE 1102280
| COTATI 11055156 |  |  |  | LAKEVILLE 110287432
| PETALUMA C 1108632 |  |  |  | MONTE RIO 1113652
| RACETRACK 170455798 |  |  |  | PETALUMA C 1108208
| PASO ROBLES 1103N52 |  |  |  | RINCON 1103circuit_breaker
| OLETA 110151740 |  |  |  | BUCKS CREEK 1101circuit_breaker
| BANGOR 11011806 |  |  |  | CLARK ROAD 11022044
| FULTON 110777670 |  |  |  | CLARK ROAD 1102circuit_breaker
| RESERVATION ROAD 1101circuit_breaker |  |  |  | CORNING 110135974
| PEORIA 170459596 |  |  |  | CORNING 110164090
| OILFIELDS 1103N62 |  |  |  | CORNING 110182846
| SISQUOC 1102M54 |  |  |  | CORNING 110185152
| OILFIELDS 1103N48 |  |  |  | CORNING 110185162
| MIDDLETOWN 11011079 |  |  |  | CORNING 110187304
| POSO MOUNTAIN 21014456 |  |  |  | COTTONWOOD 11031344
| CHOLAME 21025597 |  |  |  | COTTONWOOD 11031348
| MERCED FALLS 110222774 |  |  |  | COTTONWOOD 11031616
| FREMONT 1104MR707 |  |  |  | COTTONWOOD 110331548
| SUNOL 1101circuit_breaker |  |  |  | COTTONWOOD 110335470
| TEJON 11022455 |  |  |  | COTTONWOOD 11039072
| CURTIS 1703circuit_breaker |  |  |  | COTTONWOOD 1103circuit_breaker
| HALF MOON BAY 1103circuit_breaker |  |  |  | DESCHUTES 11049718
| TEJON 11023751 |  |  |  | GRAYS FLAT 0401circuit_breaker
| BEAR VALLEY 210110000 |  |  |  | KESWICK 11011586
| CLAYTON 2212circuit_breaker |  |  |  | KESWICK 11011590
| MERCED FALLS 110222772 |  |  |  | OREGON TRAIL 110335002
| TEJON 11023760 |  |  |  | OREGON TRAIL 110346860
| BEAR VALLEY 210110019 |  |  |  | OREGON TRAIL 1103circuit_breaker
| MORAGA 110531512 |  |  |  | PANORAMA 11019092
| MERCED FALLS 1102circuit_breaker |  |  |  | PANORAMA 1101circuit_breaker
| PEORIA 1704circuit_breaker |  |  |  | PANORAMA 1102circuit_breaker
| SISQUOC 1102M52 |  |  |  | RED BLUFF 11041302
| CAMBRIA 1101V76 |  |  |  | RED BLUFF 110451238
| RESERVATION ROAD 11013026 |  |  |  | RED BLUFF 1104circuit_breaker
| CAMBRIA 1101circuit_breaker |  |  |  | VOLTA 110149742
| PEORIA 170413490 |  |  |  | VOLTA 11021648
| MERCED FALLS 11029460 |  |  |  | WYANDOTTE 110932586
| PUEBLO 2102698 |  |  |  | PUTAH CREEK 110246012
| VALLEY VIEW 1106circuit_breaker |  |  |  | PUTAH CREEK 110264044
| LAURELES 1111432 |  |  |  | PUTAH CREEK 1102circuit_breaker
| PEORIA 170488630 |  |  |  | PUTAH CREEK 11033783
| HIGHLANDS 1102556 |  |  |  | PUTAH CREEK 11033851
| LAURELES 11112020 |  |  |  | VACA DIXON 110540092
| LAURELES 1111circuit_breaker |  |  |  | VACAVILLE 11046542
| OAKLAND X 1104CR214 |  |  |  | VACAVILLE 110847860
| OAKLAND X 1104CR288 |  |  |  | VACAVILLE 111113652
| LAURELES 11116617 |  |  |  | BANGOR 1101478754
| MORAGA 110183424 |  |  |  | BRUNSWICK 110350070
| LAURELES 11112028 |  |  |  | CLARKSVILLE 210419632
| LAURELES 11116421 |  |  |  | CLARKSVILLE 210419772
| MORAGA 110518396 |  |  |  | CLARKSVILLE 2105circuit_breaker
| LAURELES 111184523 |  |  |  | SHINGLE SPRINGS 210551738
| VALLEY VIEW 1106P176 |  |  |  | COLUMBIA HILL 11012212
| OILFIELDS 11032757 |  |  |  | DIAMOND SPRINGS 11052102
| PETALUMA C 1108636 |  |  |  | EL DORADO PH 210119752
| SHINGLE SPRINGS 210551738 |  |  |  | EL DORADO PH 2101circuit_breaker
| PASO ROBLES 1103N04 |  |  |  | MOUNTAIN QUARRIES 21016953
| OILFIELDS 11035175 |  |  |  | NARROWS 21022718
| GOLDTREE 1107circuit_breaker |  |  |  | SHINGLE SPRINGS 210935598
| CORNING 110135974 |  |  |  | SHINGLE SPRINGS 21099372
POSO MOUNTAIN 21011703
OILFIELDS 1103N40
KERN OIL 110646960
OILFIELDS 1103N64
OILFIELDS 1103N42
TIVY VALLEY 110737522
PETALUMA C 1108628
OILFIELDS 11037006
KERN OIL 11063301
POSO MOUNTAIN 2101circuit_breaker
COTTONWOOD 1103circuit_breaker
PETALUMA C 1108296
OILFIELDS 1103N44
OILFIELDS 110383158
PASO ROBLES 1103N50

## Pivot of Risk Data (hidden)
Data
Central Coast | PZ_idx | circuit_protection_zone_id | mavf_core_risk | total pixel_count | total primary_length_m | total primary_length_m_hftd_23
1 | 190 | OREGON TRAIL 110335002 | 111.7647 | 624 | 92189.591 | 92189.591
2 | 4403 | VACA DIXON 110540092 | 57.9125 | 197 | 69249.133 | 37400.5677
3 | 2409 | COARSEGOLD 210410400 | 53.3043 | 473 | 71887.274 | 67877.1847
4 | 5783 | OREGON TRAIL 11041634 | 52.2161 | 224 | 29357.8519 | 28112.1395
5 | 3795 | MARIPOSA 210210880 | 51.8448 | 394 | 64121.2381 | 63141.8494
6 | 1665 | DESCHUTES 110449024 | 47.9874 | 216 | 26924.4497 | 25640.9937
7 | 192 | COARSEGOLD 21045300 | 46.3711 | 383 | 59987.7854 | 59987.7854
8 | 1601 | OREGON TRAIL 11041574 | 46.2816 | 235 | 30217.5794 | 26331.2246
9 | 2021 | COARSEGOLD 21045310 | 45.6473 | 225 | 28358.0547 | 28358.0547
10 | 864 | RED BLUFF 11011334 | 43.7155 | 408 | 89771.64 | 62500.9171
11 | 1571 | COTTONWOOD 11031348 | 43.6979 | 351 | 51202.5627 | 45791.5824
12 | 204 | AUBERRY 1102circuit_breaker | 43.659 | 307 | 55632.597 | 55632.597
13 | 5504 | HIGGINS 110950072 | 42.0939 | 676 | 82323.743 | 82323.743
14 | 2763 | OAKHURST 110110090 | 40.6671 | 540 | 71069.2859 | 71069.2859
15 | 1973 | OAKHURST 11015490 | 39.1235 | 304 | 39826.5176 | 39826.5176
16 | 3638 | DESCHUTES 11041370 | 38.7456 | 148 | 35731.175 | 19292.4005
17 | 819 | ZACA 1102Y54 | 38.7034 | 238 | 54621.7415 | 53471.0661
18 | 6356 | MIDDLETOWN 1101622 | 38.4777 | 240 | 32035.0118 | 25790.8227
19 | 3707 | DESCHUTES 11049726 | 35.4739 | 202 | 27044.9597 | 24438.8213
20 | 1577 | COARSEGOLD 210310820 | 35.3292 | 307 | 45979.4651 | 45523.6929
21 | 3716 | WISE 11022230 | 34.7369 | 266 | 39994.2491 | 36254.0831
22 | 2248 | SHINGLE SPRINGS 210913322 | 33.0717 | 586 | 66862.7414 | 66862.7414
23 | 1508 | BELL 11072400 | 32.6703 | 381 | 44455.198 | 40028.1973
24 | 1015 | CORRAL 110136652 | 32.3296 | 322 | 58059.3769 | 58059.3769
25 | 2360 | VACAVILLE 110838316 | 31.9111 | 177 | 37516.1668 | 25488.4092
26 | 5807 | COARSEGOLD 21046288 | 31.2372 | 141 | 16779.965 | 16779.965
27 | 5931 | COARSEGOLD 21045525 | 30.7671 | 166 | 20995.911 | 20995.911
28 | 6195 | HIGGINS 110950078 | 30.4436 | 504 | 77708.0128 | 77708.0128
29 | 1025 | MARIPOSA 210237282 | 30.1742 | 526 | 96120.2252 | 81850.6465
30 | 3079 | DIAMOND SPRINGS 11057722 | 28.5476 | 744 | 200061.3477 | 190536.6662
31 | 4798 | BELL 11082202 | 28.2975 | 416 | 53223.6255 | 51314.2889
32 | 2220 | COARSEGOLD 2104369777 | 28.1228 | 203 | 29945.6871 | 29945.6871
33 | 4967 | AUBERRY 1101R2578 | 27.8557 | 422 | 74321.3837 | 74321.3837
34 | 1789 | BELL 110750172 | 27.7939 | 243 | 29834.4703 | 27581.8653
35 | 1661 | DESCHUTES 11049718 | 27.7145 | 152 | 56953.3633 | 26275.4179
36 | 6616 | COTTONWOOD 110168190 | 27.6706 | 251 | 40765.2344 | 37929.7081
37 | 821 | DIAMOND SPRINGS 1107circuit_breaker | 27.067 | 618 | 90295.6562 | 81888.8347
38 | 4339 | SANTA YNEZ 1104Y04 | 26.7943 | 118 | 35646.7737 | 24112.9415
39 | 1366 | SAND CREEK 110345190 | 26.7484 | 367 | 58836.3475 | 58836.3475
40 | 466 | COTTONWOOD 11031616 | 26.3137 | 420 | 78749.1842 | 73500.8728
41 | 3848 | MOUNTAIN QUARRIES 2101circuit_breaker | 26.0302 | 331 | 40183.7682 | 40183.7682
42 | 698 | COARSEGOLD 2103circuit_breaker | 26.0295 | 422 | 61823.6709 | 61823.6709
43 | 3901 | APPLE HILL 2102circuit_breaker | 25.2589 | 643 | 66687.7451 | 66687.7451
44 | 4384 | BANGOR 110182350 | 25.231 | 241 | 35380.8633 | 30346.6456
45 | 1224 | PENRYN 11032198 | 25.0789 | 281 | 33526.3958 | 32169.4149
46 | 1486 | WYANDOTTE 110979932 | 23.4289 | 253 | 52503.3015 | 34098.0677
47 | 5985 | SHINGLE SPRINGS 210519522 | 23.1275 | 107 | 16493.1882 | 15477.8093
48 | 1817 | OAKHURST 1103circuit_breaker | 22.972 | 456 | 54035.2628 | 50881.3747
49 | 4431 | MARIPOSA 210237288 | 22.9229 | 827 | 136885.5796 | 136885.5796
50 | 105 | WISE 11022054 | 22.9035 | 170 | 20797.7702 | 20797.7702
51 | 3450 | AUBERRY 1102R2850 | 22.8722 | 177 | 41610.2357 | 41610.2357
52 | 1301 | DESCHUTES 1104circuit_breaker | 22.4208 | 135 | 39924.6145 | 19511.2444
53 | 5498 | SHEPHERD 2111R1400 | 21.9543 | 119 | 36919.6677 | 29130.6459
54 | 4317 | STILLWATER 1102circuit_breaker | 21.6253 | 334 | 40553.6845 | 40538.5999
55 | 890 | COTTONWOOD 1102circuit_breaker | 21.1966 | 162 | 37956.7799 | 25573.0555
56 | 2237 | DESCHUTES 11011580 | 20.4631 | 428 | 79522.8496 | 74786.9655
57 | 4268 | AUBERRY 110237466 | 20.3675 | 197 | 50914.8919 | 50295.1648
58 | 5388 | RED BLUFF 11031702 | 20.2222 | 180 | 29232.1064 | 26173.4534
59 | 6372 | TIVY VALLEY 1107584840 | 19.7021 | 338 | 72367.2531 | 72367.2531
60 | 7209 | BROWNS VALLEY 110193870 | 19.6578 | 192 | 54425.7608 | 28752.0223
61 | 733 | PUTAH CREEK 110267858 | 19.5736 | 124 | 18688.4623 | 18688.4623
62 | 2819 | NARROWS 21011202 | 19.5689 | 547 | 73260.5674 | 73260.5674
63 | 4646 | COTTONWOOD 11039072 | 19.5548 | 255 | 45954.2203 | 45954.2203
64 | 86 | TYLER 11051704 | 19.4232 | 156 | 74221.1596 | 18219.6369
65 | 3511 | VACAVILLE 11088762 | 19.3692 | 76 | 26864.0035 | 22706.5359
66 | 2593 | PASO ROBLES 1103N54 | 19.3286 | 151 | 34349.6665 | 30731.9341
67 | 3596 | UKIAH 1111534 | 18.9464 | 154 | 33746.6437 | 30274.4024
68 | 39 | CEDAR CREEK 11011664 | 18.9423 | 357 | 47829.7335 | 47829.7335
69 | 912 | CORRAL 1101circuit_breaker | 18.6718 | 200 | 44068.152 | 42004.2216
70 | 4729 | LINCOLN 11042070 | 18.6329 | 228 | 46656.6382 | 26390.3487
71 | 6060 | RIO DELL 11024230 | 18.5803 | 354 | 36927.9603 | 36847.6257
72 | 662 | OREGON TRAIL 1104circuit_breaker | 18.4455 | 143 | 24009.399 | 15260.0733
73 | 5121 | HIGGINS 1109circuit_breaker | 18.3144 | 344 | 37253.2271 | 35901.2045
74 | 759 | DIAMOND SPRINGS 11052102 | 18.2244 | 492 | 62924.1894 | 60433.983
75 | 5473 | BANGOR 110180670 | 18.1242 | 162 | 26656.2925 | 22220.3587
76 | 1410 | MARIPOSA 21019400 | 18.0755 | 815 | 101390.2805 | 101390.2805
77 | 1731 | RED BLUFF 110451238 | 17.968 | 301 | 63182.0088 | 63182.0088
78 | 4692 | OAKHURST 110363334 | 17.9641 | 183 | 27690.7454 | 27690.7454
79 | 3724 | DESCHUTES 11011380 | 17.8832 | 150 | 37711.3658 | 27539.9827
80 | 2148 | DIAMOND SPRINGS 110519910 | 17.8631 | 242 | 65623.9364 | 65623.9364
81 | 3665 | WILLITS 1104934 | 17.7005 | 409 | 49456.388 | 49456.388
82 | 3761 | SAND CREEK 11037140 | 17.3038 | 201 | 42354.6264 | 42354.6264
83 | 3393 | COTTONWOOD 11011610 | 17.1663 | 376 | 61705.5201 | 61705.5201
84 | 538 | STILLWATER 11021644 | 17.0159 | 309 | 36671.0244 | 36671.0244
85 | 2804 | SHINGLE SPRINGS 21099372 | 16.6995 | 219 | 28435.4313 | 28435.4313
86 | 129 | SAN JOAQUIN #2 1103circuit_breaker | 16.4981 | 389 | 109277.3995 | 109277.3995
87 | 3978 | VACAVILLE 11046542 | 16.4715 | 164 | 23785.8023 | 23785.8023
88 | 6222 | STILLWATER 110248952 | 16.2746 | 134 | 16989.9527 | 16989.9527
89 | 502 | COTTONWOOD 11029026 | 16.2213 | 127 | 38967.1548 | 19720.6221
90 | 1849 | PENRYN 1103circuit_breaker | 16.1209 | 397 | 47859.6372 | 45768.8176
91 | 1391 | MIDDLETOWN 1102998 | 16.1058 | 134 | 27688.0247 | 23041.0417
92 | 247 | CLARK ROAD 11022582 | 15.8251 | 166 | 33761.1198 | 32088.8606
93 | 2247 | JESSUP 11021550 | 15.5885 | 207 | 35586.9744 | 28670.4982
94 | 1458 | AUBERRY 1101circuit_breaker | 15.1058 | 151 | 29094.1652 | 29094.1652
95 | 749 | BANGOR 11017446 | 15.0101 | 589 | 139759.6192 | 139759.6192
96 | 1785 | COARSEGOLD 210410110 | 14.9256 | 656 | 79684.5808 | 79684.5808
97 | 1744 | TIVY VALLEY 1107869946 | 14.7751 | 126 | 48055.8133 | 48055.8133
98 | 930 | MARIPOSA 21029590 | 14.6437 | 506 | 58305.4261 | 58305.4261
99 | 5848 | TYLER 110585132 | 14.6211 | 259 | 50197.6466 | 50197.6466
100 | 6125 | PUTAH CREEK 11028352 | 14.5349 | 64 | 18999.2581 | 8943.386
101 | 1087 | BANGOR 11011958 | 14.4657 | 439 | 108052.4623 | 108052.4623
102 | 5017 | HIGHLANDS 1103circuit_breaker | 13.8949 | 109 | 19679.9672 | 16763.7621
103 | 4059 | COTTONWOOD 11031344 | 13.6725 | 101 | 20065.0071 | 15508.3048
104 | 1685 | BUELLTON 1102Y50 | 13.5803 | 134 | 20629.3397 | 17178.6356
105 | 508 | CLARKSVILLE 210413352 | 13.4695 | 376 | 58866.4594 | 54145.4284
106 | 133 | CLARKSVILLE 210319572 | 13.4518 | 334 | 69572.9299 | 49656.7912
107 | 3568 | PUEBLO 2103678 | 13.3968 | 570 | 56404.6012 | 56171.914
108 | 3175 | FULTON 1107214 | 13.3226 | 425 | 48113.355 | 48113.355
109 | 4022 | SAND CREEK 11037420 | 13.2578 | 178 | 38096.5412 | 38096.5412
110 | 81 | LINCOLN 110451756 | 13.1994 | 144 | 91590.9005 | 24962.2729
111 | 5665 | SILVERADO 2104632 | 13.0187 | 216 | 30072.3446 | 29545.0013
112 | 3287 | WISE 1102307494 | 12.965 | 272 | 54215.3663 | 49357.8411
113 | 84 | CORNING 110185152 | 12.8973 | 317 | 37238.3316 | 37238.3316
114 | 3510 | CEDAR CREEK 11011608 | 12.83 | 441 | 53533.2272 | 53533.2272
115 | 7507 | JESSUP 11023105 | 12.7904 | 65 | 10017.6158 | 9428.2851
116 | 2050 | COARSEGOLD 21035020 | 12.577 | 133 | 26968.3187 | 25953.2029
117 | 3982 | OREGON TRAIL 11021382 | 12.3855 | 81 | 8802.4775 | 8802.4775
118 | 2034 | PHILO 1101circuit_breaker | 12.3408 | 369 | 79786.4997 | 48254.7037
119 | 389 | CALISTOGA 1101734 | 12.2262 | 181 | 25385.1806 | 20110.861
120 | 6598 | SALMON CREEK 110188998 | 12.2196 | 78 | 22084.2262 | 9919.7992
121 | 49 | HIGHLANDS 1103520 | 12.2004 | 437 | 75802.3106 | 75802.3106
122 | 3481 | JAMESON 11057652 | 12.1773 | 173 | 70087.7329 | 21719.6282
123 | 1166 | PENRYN 11051342 | 12.1504 | 277 | 62210.7771 | 32719.8008
124 | 422 | COTTONWOOD 11021578 | 12.1173 | 281 | 56401.1925 | 45006.6873
125 | 2102 | CALISTOGA 1101736 | 11.914 | 474 | 56743.887 | 56743.887
126 | 3912 | OLETA 11011208 | 11.8256 | 274 | 61275.2844 | 52737.327
127 | 6517 | KESWICK 110148480 | 11.7286 | 75 | 17324.1107 | 17324.1107
128 | 6336 | DESCHUTES 1101circuit_breaker | 11.7062 | 47 | 17933.5448 | 6460.1699
129 | 1374 | SAN JOAQUIN #2 110310320 | 11.6645 | 146 | 18926.5803 | 18926.5803
130 | 4012 | JESSUP 110141356 | 11.5613 | 281 | 52454.1999 | 52454.1999
131 | 2424 | WOODWARD 2108R2860 | 11.4725 | 84 | 35474.6172 | 17727.1373
132 | 2440 | BROWNS VALLEY 11011268 | 11.4123 | 135 | 17550.3384 | 17547.6887
133 | 7203 | CORRAL 110112608 | 11.3441 | 124 | 27099.2397 | 27099.2397
134 | 6519 | PHILO 110137222 | 11.3077 | 197 | 40901.8789 | 40901.8789
135 | 1853 | REDBUD 1101323962 | 11.224 | 154 | 46324.5895 | 32521.6427
136 | 3269 | JESSUP 110276068 | 11.2051 | 244 | 30912.2445 | 26885.9006
137 | 1980 | SHINGLE SPRINGS 210912392 | 11.1292 | 180 | 23968.2562 | 23968.2562
138 | 4039 | GIRVAN 1101323094 | 11.098 | 286 | 58215.1727 | 58215.1727
139 | 5257 | KONOCTI 110264664 | 11.0602 | 270 | 46643.7092 | 43740.7498
140 | 2729 | WYANDOTTE 110913052 | 11.0495 | 240 | 31567.9238 | 31409.8673
141 | 2658 | COTATI 110536536 | 10.9762 | 133 | 31836.265 | 25960.937
142 | 4047 | SHINGLE SPRINGS 2109circuit_breaker | 10.9005 | 411 | 44889.6263 | 43399.3801
143 | 6600 | FORT SEWARD 11211690 | 10.8257 | 131 | 26202.8159 | 15633.7781
144 | 1069 | GRASS VALLEY 11032180 | 10.5904 | 597 | 70305.7957 | 70305.7957
145 | 2841 | WYANDOTTE 11071026 | 10.319 | 267 | 44780.2125 | 34466.4557
146 | 5513 | SHINGLE SPRINGS 210935598 | 10.2267 | 118 | 17564.7145 | 17564.7145
147 | 3008 | NARROWS 21052228 | 10.1756 | 262 | 34109.5496 | 33185.7143
148 | 992 | CALISTOGA 1101890 | 10.1513 | 251 | 39735.6 | 37703.1619
149 | 167 | NORTH BRANCH 110111206 | 10.0345 | 102 | 28777.6676 | 28150.1513
150 | 3817 | CORNING 110164090 | 10.0231 | 163 | 22037.5277 | 22037.5277
151 | 3587 | AUBERRY 1102R309 | 9.9592 | 76 | 13825.8859 | 13825.8859
152 | 4128 | CLAYTON 22122944 | 9.9585 | 118 | 23740.8312 | 23517.364
153 | 2778 | GEYSERVILLE 1101166 | 9.9522 | 160 | 25913.2012 | 18354.3619
154 | 3133 | AUBERRY 1101R314 | 9.8936 | 241 | 70887.9033 | 67647.5297
155 | 7546 | GEYSERVILLE 110179788 | 9.8744 | 341 | 67534.7693 | 63216.603
156 | 6785 | AUBERRY 1102R1013 | 9.8222 | 115 | 19936.8067 | 19936.8067
157 | 1329 | CORRAL 1102circuit_breaker | 9.7731 | 148 | 34251.1303 | 25529.3697
158 | 445 | GARBERVILLE 11011604 | 9.7685 | 53 | 27911.2836 | 6822.8212
159 | 5194 | TEMPLETON 2113A20 | 9.7196 | 66 | 12664.8988 | 10922.8343
160 | 1399 | ZACA 1102Y02 | 9.6937 | 79 | 21124.0364 | 15863.9802
161 | 5096 | SANTA YNEZ 110477098 | 9.6674 | 65 | 20978.2648 | 16911.4845
162 | 2963 | DESCHUTES 11041582 | 9.3758 | 69 | 24249.9571 | 9068.1485
163 | 837 | HIGGINS 1103circuit_breaker | 9.2424 | 431 | 45896.1812 | 45196.8083
164 | 442 | CLAYTON 221296224 | 9.2315 | 197 | 26353.3688 | 26353.3688
165 | 2529 | LAYTONVILLE 1102500 | 9.2215 | 194 | 47214.3808 | 32899.6268
166 | 5557 | CHALLENGE 11021064 | 9.1991 | 295 | 64329.1338 | 64329.1338
167 | 5334 | JESSUP 11011496 | 9.0763 | 197 | 26108.2459 | 23100.1991
168 | 3497 | JESSUP 110296554 | 9.0441 | 98 | 24227.1624 | 12714.8897
169 | 380 | CORRAL 110112606 | 8.9495 | 215 | 36019.0707 | 36019.0707
170 | 1807 | NARROWS 21057203 | 8.9301 | 224 | 30163.3265 | 29234.7991
171 | 4329 | HIGHLANDS 1103568 | 8.9233 | 82 | 14661.491 | 12324.8036
172 | 6138 | COARSEGOLD 210410335 | 8.9154 | 85 | 9369.0411 | 9369.0411
173 | 5352 | TYLER 11051536 | 8.8807 | 92 | 28821.608 | 27372.4849
174 | 2159 | RACETRACK 1704circuit_breaker | 8.431 | 207 | 36598.3736 | 36598.3736
175 | 64 | WOODACRE 1102circuit_breaker | 8.3115 | 295 | 34037.9756 | 33390.0506
176 | 6632 | CEDAR CREEK 1101circuit_breaker | 8.1369 | 157 | 24905.7197 | 24905.7197
177 | 1871 | TIVY VALLEY 1107R1817 | 8.0879 | 112 | 30917.6877 | 30260.3712
178 | 3547 | BIG BEND 11021972 | 8.028 | 307 | 33902.4073 | 33902.4073
179 | 1782 | CLOVERDALE 1101112 | 8.0196 | 247 | 43621.7134 | 30254.9758
180 | 5296 | ZACA 1102circuit_breaker | 8.015 | 109 | 33377.7518 | 24178.8119
181 | 7148 | FITCH MOUNTAIN 11136751 | 8.0144 | 318 | 35962.163 | 35962.163
182 | 6532 | MARIPOSA 21021960 | 8.0077 | 293 | 39674.5223 | 39674.5223
183 | 7890 | BANGOR 110131502 | 7.9408 | 148 | 38151.0582 | 38151.0582
184 | 5135 | HIGHLANDS 1103482 | 7.917 | 235 | 41526.8283 | 38824.923
185 | 6282 | MOLINO 110266006 | 7.7247 | 142 | 14413.6045 | 14413.6045
186 | 2065 | DOBBINS 11011808 | 7.6851 | 215 | 24893.8312 | 24893.8312
187 | 6306 | UPPER LAKE 1101412 | 7.671 | 103 | 29863.0456 | 17548.709
188 | 4708 | OREGON TRAIL 1102circuit_breaker | 7.6221 | 123 | 15715.8206 | 15165.9787
189 | 1926 | NARROWS 210534069 | 7.6062 | 153 | 25148.2731 | 25148.2731
190 | 1818 | KONOCTI 1102circuit_breaker | 7.5478 | 427 | 66951.8529 | 52446.7628
191 | 6227 | WISE 1102697216 | 7.5068 | 108 | 21260.5149 | 21260.5149
192 | 6910 | PASO ROBLES 1103N58 | 7.4845 | 47 | 12056.5272 | 7139.6018
193 | 2402 | CORRAL 110112612 | 7.4541 | 147 | 32323.3334 | 31361.0381
194 | 989 | TEMPLETON 2113A70 | 7.4104 | 163 | 107119.9327 | 39039.5646
195 | 5926 | GIRVAN 11011330 | 7.308 | 368 | 49991.4373 | 49037.4544
196 | 1019 | SILVERADO 2104726 | 7.3045 | 260 | 56572.5773 | 46009.8876
197 | 3119 | CHOLAME 2102X06 | 7.2765 | 290 | 84987.8121 | 53331.3621
198 | 7282 | SHINGLE SPRINGS 210851476 | 7.2751 | 66 | 10357.1601 | 7007.9313
199 | 6949 | WISE 11022234 | 7.2319 | 80 | 24231.786 | 24231.786
200 | 1140 | WYANDOTTE 110777578 | 7.2314 | 308 | 51812.8398 | 31530.7542
201 | 1194 | APPLE HILL 21021532 | 7.0586 | 558 | 67838.2746 | 60833.3699
202 | 2042 | POTTER VALLEY P H 11051904 | 6.9326 | 280 | 64539.5347 | 47497.3243
203 | 7386 | RED BLUFF 110176020 | 6.9278 | 82 | 23337.4414 | 14298.5591
204 | 2436 | CEDAR CREEK 11011656 | 6.9273 | 367 | 51035.8707 | 51035.8707
205 | 4896 | AUBERRY 1102R902 | 6.8827 | 127 | 24311.5038 | 24311.5038
206 | 322 | CORNING 110253184 | 6.8716 | 117 | 51349.7049 | 51349.7049
207 | 1419 | FORT SEWARD 1122circuit_breaker | 6.8517 | 203 | 35129.8817 | 28255.3669
208 | 375 | MOUNTAIN QUARRIES 21011102 | 6.825 | 508 | 71641.3725 | 71641.3725
209 | 1138 | LONE TREE 210521210 | 6.8077 | 34 | 25986.6286 | 16983.4147
210 | 934 | SANTA YNEZ 1104Y66 | 6.7651 | 88 | 28822.2697 | 25950.7807
211 | 7640 | LAYTONVILLE 1102572 | 6.721 | 296 | 34430.0284 | 34430.0284
212 | 3421 | DUNLAP 11037040 | 6.6149 | 197 | 39870.7942 | 39870.7942
213 | 2260 | SAN JOAQUIN #3 1103circuit_breaker | 6.6069 | 369 | 45356.6535 | 45356.6535
214 | 6839 | FITCH MOUNTAIN 1113356 | 6.5616 | 138 | 24401.1439 | 15672.6029
215 | 6034 | ANTLER 11011378 | 6.5397 | 324 | 40324.448 | 39346.0984
216 | 4876 | OREGON TRAIL 11031448 | 6.5355 | 265 | 98740.9676 | 98740.9676
217 | 56 | VACAVILLE 1111circuit_breaker | 6.5268 | 91 | 19505.0496 | 10814.1289
218 | 2908 | KONOCTI 110275382 | 6.5197 | 307 | 37575.1016 | 35775.2475
219 | 1615 | COTATI 110599720 | 6.4876 | 115 | 19787.8115 | 14251.5886
220 | 492 | DOBBINS 11011264 | 6.4814 | 464 | 55993.1456 | 55887.5598
221 | 6610 | BANGOR 110155206 | 6.4338 | 33 | 16572.7725 | 3897.0387
222 | 834 | PASO ROBLES 1104R56 | 6.4068 | 97 | 19912.9218 | 17514.7266
223 | 4241 | CORRAL 110236666 | 6.3948 | 151 | 58052.876 | 52553.7194
224 | 1911 | WILLITS 1104circuit_breaker | 6.3727 | 48 | 12252.1327 | 4814.9119
225 | 1207 | VOLTA 110237350 | 6.3663 | 333 | 39083.1019 | 39083.1019
226 | 6761 | VACAVILLE 111113652 | 6.3046 | 58 | 6983.1183 | 6983.1183
227 | 2710 | CALPELLA 11011204 | 6.2858 | 324 | 63297.3095 | 47939.0001
228 | 4752 | HARTLEY 1101698 | 6.2809 | 64 | 16608.1598 | 9794.4645
229 | 4570 | HIGHLANDS 1103828 | 6.2778 | 39 | 17124.6025 | 12064.542
230 | 1014 | HOOPA 11013290 | 6.2767 | 202 | 21820.8937 | 21820.8937
231 | 4636 | SHINGLE SPRINGS 210961892 | 6.2666 | 389 | 48517.9876 | 48517.9876
232 | 2080 | LUCERNE 11031280 | 6.2585 | 80 | 38046.2309 | 11811.7208
233 | 5213 | GARBERVILLE 11024744 | 6.2493 | 200 | 32668.2317 | 26935.3901
234 | 3127 | SAN MIGUEL 1104R58 | 6.1653 | 49 | 38699.3305 | 14371.1045
235 | 2520 | PENRYN 1103660 | 6.1116 | 155 | 31352.9096 | 16391.1944
236 | 7713 | LAS GALLINAS A 110599904 | 6.0985 | 90 | 8897.752 | 8897.752
237 | 4869 | MOUNTAIN QUARRIES 21016953 | 6.0045 | 59 | 9165.9911 | 9165.9911
238 | 4180 | FITCH MOUNTAIN 11134566 | 5.9751 | 198 | 27995.22 | 18477.8969
239 | 2292 | PLACERVILLE 21067522 | 5.9329 | 1034 | 108764.9416 | 108764.9416
240 | 4559 | SILVERADO 210478268 | 5.9 | 201 | 19338.5201 | 19338.5201
241 | 2581 | LINCOLN 11012310 | 5.8855 | 140 | 28409.3075 | 17598.5614
242 | 1827 | SHINGLE SPRINGS 2105circuit_breaker | 5.8423 | 252 | 31350.2151 | 31350.2151
243 | 2125 | HOPLAND 11014626 | 5.7917 | 176 | 49646.9813 | 40127.548
244 | 5211 | FITCH MOUNTAIN 111324918 | 5.7824 | 92 | 8527.9094 | 8527.9094
245 | 2559 | ELK CREEK 11012008 | 5.6936 | 21 | 29199.3162 | 8128.4527
246 | 2173 | MIDDLETOWN 1101circuit_breaker | 5.5864 | 78 | 30016.3762 | 13452.3274
247 | 3495 | WILLITS 1102circuit_breaker | 5.5057 | 66 | 15591.407 | 7444.0734
248 | 1057 | LINCOLN 110195756 | 5.4906 | 94 | 28755.3134 | 9885.2869
249 | 1463 | STILLWATER 110148950 | 5.4295 | 180 | 20085.728 | 20085.728
250 | 4809 | NARROWS 21052748 | 5.427 | 186 | 31525.9218 | 21028.293
251 | 5137 | GIRVAN 11011636 | 5.4261 | 211 | 29877.1164 | 24954.3397
252 | 1218 | SHINGLE SPRINGS 110419502 | 5.3952 | 109 | 92405.563 | 68814.3237
253 | 6490 | BELL 11085703 | 5.308 | 74 | 12591.8349 | 7165.6312
254 | 3249 | LAYTONVILLE 110237586 | 5.2932 | 132 | 21840.8846 | 21840.8846
255 | 1043 | MARIPOSA 210110990 | 5.2697 | 157 | 64117.5165 | 64117.5165
256 | 3437 | CLEAR LAKE 1101406 | 5.2455 | 75 | 52777.1485 | 17278.745
257 | 2668 | ELK CREEK 110137334 | 5.2022 | 55 | 15414.1675 | 15414.1675
258 | 5183 | HOOPA 11013174 | 5.1867 | 266 | 35383.1104 | 28229.9925
259 | 6980 | PENRYN 11072708 | 5.1482 | 126 | 17082.1753 | 15108.1749
260 | 1088 | COARSEGOLD 210410030 | 5.1287 | 81 | 28835.8758 | 23477.104
261 | 3080 | MOLINO 110279306 | 5.1143 | 39 | 13023.8596 | 5037.4953
262 | 7078 | MOUNTAIN QUARRIES 210151584 | 5.0571 | 290 | 35042.6767 | 35042.6767
263 | 1983 | SMARTVILLE 1101circuit_breaker | 5.0479 | 146 | 26180.464 | 26009.9248
264 | 4894 | CLOVERDALE 1102156 | 5.0391 | 69 | 18980.0369 | 8650.9367
265 | 5478 | CLOVERDALE 1102672 | 5.013 | 152 | 36513.5782 | 35674.8205
266 | 1830 | DIAMOND SPRINGS 110610587 | 4.9763 | 307 | 35174.8047 | 35174.8047
267 | 963 | WEST POINT 11024788 | 4.9705 | 734 | 113054.7153 | 113054.7153
268 | 2349 | WYANDOTTE 11091520 | 4.9654 | 51 | 31750.549 | 5746.3127
269 | 5653 | FLINT 1101750 | 4.9524 | 49 | 14953.9778 | 7461.0283
270 | 5059 | DIAMOND SPRINGS 110656026 | 4.9473 | 219 | 24259.9065 | 24259.9065
271 | 6934 | MARIPOSA 2102440236 | 4.9267 | 56 | 6819.7347 | 6786.4552
272 | 2644 | STILLWATER 11021466 | 4.9095 | 245 | 33018.7362 | 32904.1054
273 | 5927 | WYANDOTTE 110737472 | 4.8973 | 111 | 24045.3707 | 13224.7658
274 | 6021 | COTTONWOOD 110131500 | 4.8132 | 42 | 18970.9292 | 6089.5352
275 | 8370 | SHINGLE SPRINGS 1103circuit_breaker | 4.811 | 84 | 19101.7778 | 9623.2164
276 | 7659 | SILVERADO 210258626 | 4.7612 | 186 | 24429.8093 | 24429.8093
277 | 1768 | BANGOR 11011804 | 4.6192 | 593 | 69024.4911 | 69024.4911
278 | 5188 | WYANDOTTE 11095607 | 4.6188 | 58 | 10784.9193 | 6796.939
279 | 2628 | APPLE HILL 210277546 | 4.6133 | 524 | 138915.4591 | 138915.4591
280 | 4504 | SHINGLE SPRINGS 211051790 | 4.6123 | 123 | 13935.3436 | 12398.7678
281 | 2295 | CLAY 110113442 | 4.5666 | 240 | 49967.0249 | 40782.5793
282 | 6156 | UKIAH 1114408 | 4.5587 | 337 | 60895.2254 | 59693.1649
283 | 528 | FORT SEWARD 11211602 | 4.5297 | 242 | 36343.227 | 27815.4127
284 | 3366 | WYANDOTTE 11031974 | 4.4934 | 379 | 36746.286 | 36746.286
285 | 2491 | FULTON 1102287172 | 4.4509 | 236 | 42798.2234 | 29351.4047
286 | 338 | COTTONWOOD 1101circuit_breaker | 4.4498 | 60 | 36474.0618 | 7715.0522
287 | 4955 | PHILO 11013700 | 4.4475 | 152 | 29050.7038 | 29050.7038
288 | 3260 | NARROWS 21052216 | 4.4415 | 755 | 92843.3154 | 90284.175
289 | 4918 | BRIDGEVILLE 1102circuit_breaker | 4.4377 | 112 | 57957.1067 | 40164.6361
290 | 1520 | WILLITS 110391810 | 4.4256 | 404 | 47349.2019 | 47349.2019
291 | 1905 | NORTH BRANCH 1101TS1115 | 4.4229 | 191 | 28340.5083 | 28340.5083
292 | 3432 | MIDDLETOWN 1103830 | 4.3884 | 134 | 62352.3339 | 40504.507
293 | 3735 | HIGGINS 1109594 | 4.3783 | 195 | 23079.0602 | 23079.0602
294 | 7360 | HIGHLANDS 1102628 | 4.3771 | 73 | 22902.6806 | 22902.6806
295 | 7114 | CORRAL 110214026 | 4.3331 | 95 | 16308.5206 | 16308.5206
296 | 3166 | APPLE HILL 2102186912 | 4.3301 | 680 | 81658.6951 | 78311.5629
297 | 3075 | MOLINO 1102104 | 4.3192 | 339 | 34941.2444 | 34941.2444
298 | 2512 | COTTONWOOD 110335470 | 4.3162 | 93 | 40111.3744 | 31917.2696
299 | 2330 | GEYSERVILLE 1102484 | 4.312 | 218 | 78386.0012 | 50631.555
300 | 3864 | SILVERADO 210234959 | 4.3034 | 215 | 42790.9314 | 41070.2397
301 | 1268 | MIDDLETOWN 11014646 | 4.2902 | 196 | 29953.689 | 29953.689
302 | 4992 | CORNING 11021622 | 4.2244 | 110 | 54857.2254 | 54857.2254
303 | 5074 | SHINGLE SPRINGS 21092679 | 4.2186 | 82 | 11499.2833 | 11499.2833
304 | 4539 | LOW GAP 110137498 | 4.217 | 219 | 26210.4026 | 26210.4026
305 | 4578 | GIRVAN 110280726 | 4.2002 | 98 | 29678.7126 | 10897.7797
306 | 1312 | SILVERADO 210437632 | 4.1631 | 366 | 42656.5483 | 42656.5483
307 | 1466 | CLOVERDALE 1101circuit_breaker | 4.1223 | 67 | 14601.0166 | 7970.5303
308 | 7087 | OREGON TRAIL 1103circuit_breaker | 4.1072 | 43 | 4700.2679 | 4346.4203
309 | 284 | WHITMORE 11011598 | 4.1017 | 333 | 53639.2857 | 53639.2857
310 | 2495 | MOLINO 1101338 | 4.0819 | 100 | 23326.701 | 10257.7274
311 | 3211 | OCEANO 1104Q10 | 4.064 | 320 | 37945.3605 | 37945.3605
312 | 4162 | NARROWS 2105circuit_breaker | 4.0559 | 226 | 58146.9701 | 57069.9064
313 | 2154 | ATASCADERO 1101A02 | 4.0292 | 325 | 42537.755 | 42537.755
314 | 4207 | GIRVAN 1102circuit_breaker | 4.0129 | 49 | 33795.3586 | 5934.374
315 | 304 | MOUNTAIN QUARRIES 21011350 | 3.9709 | 250 | 34651.2737 | 34651.2737
316 | 1261 | CURTIS 17039180 | 3.9536 | 425 | 93135.0691 | 93135.0691
317 | 5869 | FITCH MOUNTAIN 1113583202 | 3.9458 | 82 | 15440.8422 | 7085.4902
318 | 2425 | JESSUP 11021314 | 3.8877 | 60 | 22635.4523 | 8285.2738
319 | 7563 | KONOCTI 1102716 | 3.87 | 138 | 27418.9124 | 21759.5686
320 | 6617 | LAYTONVILLE 110268436 | 3.8693 | 76 | 14642.1114 | 14642.1114
321 | 2632 | BUELLTON 1102circuit_breaker | 3.8574 | 36 | 20359.3308 | 8489.4268
322 | 2773 | SILVERADO 2104806 | 3.8424 | 149 | 52895.6546 | 29193.0346
323 | 6489 | MIDDLETOWN 1102circuit_breaker | 3.818 | 32 | 10581.2966 | 7090.0728
324 | 1496 | CHALLENGE 11025462 | 3.7989 | 374 | 37568.0951 | 37568.0951
325 | 3018 | PIKE CITY 1101circuit_breaker | 3.759 | 256 | 31954.3985 | 31954.3985
326 | 891 | PUTAH CREEK 1102circuit_breaker | 3.7245 | 28 | 21280.8935 | 7914.4674
327 | 3092 | CALISTOGA 1102634 | 3.7169 | 167 | 30755.7403 | 19084.7717
328 | 8090 | ELK CREEK 11012106 | 3.7058 | 47 | 21303.4581 | 21303.4581
329 | 2580 | AUBERRY 1101R2579 | 3.6868 | 255 | 55665.4542 | 55665.4542
330 | 5265 | PENRYN 110351658 | 3.6738 | 112 | 14037.6097 | 12333.3131
331 | 2756 | ZACA 1102Y48 | 3.6543 | 41 | 19086.044 | 6193.8861
332 | 1076 | HIGGINS 110332120 | 3.6409 | 603 | 65714.7916 | 64628.4099
333 | 8199 | ANDERSON 11012051 | 3.6235 | 45 | 8575.0635 | 8118.8203
334 | 4127 | POTTER VALLEY P H 110495878 | 3.6201 | 48 | 29933.3469 | 7653.5834
335 | 7841 | CLEAR LAKE 1102904 | 3.6032 | 38 | 5777.0339 | 5254.2064
336 | 3722 | PANORAMA 11021526 | 3.5987 | 86 | 28300.327 | 17981.687
337 | 6432 | CORNING 110182846 | 3.5848 | 44 | 8126.0049 | 7599.2356
338 | 786 | NARROWS 210248484 | 3.5745 | 551 | 66722.6758 | 66722.6758
339 | 4143 | REDBUD 1102circuit_breaker | 3.5676 | 105 | 32033.4913 | 26827.5429
340 | 6700 | WILLITS 1103966 | 3.5574 | 9 | 3603.2325 | 1339.7772
341 | 4587 | SHINGLE SPRINGS 210985766 | 3.557 | 206 | 29469.33 | 29469.33
342 | 4103 | CHALLENGE 1102circuit_breaker | 3.543 | 239 | 24978.1439 | 24978.1439
343 | 6987 | UPPER LAKE 11011276 | 3.5424 | 194 | 20671.4818 | 20671.4818
344 | 3539 | CAYETANO 2109circuit_breaker | 3.54 | 62 | 46595.6391 | 30595.1389
345 | 3794 | KANAKA 110165606 | 3.5245 | 212 | 20432.7894 | 20432.7894
346 | 7037 | SAN RAMON 2108circuit_breaker | 3.5237 | 111 | 15307.4292 | 13911.3335
347 | 7963 | CALPELLA 11013419 | 3.4974 | 56 | 12991.6223 | 12991.6223
348 | 2629 | PUEBLO 2102792 | 3.4973 | 236 | 67062.2216 | 60751.1606
349 | 6674 | GARBERVILLE 110139524 | 3.4903 | 59 | 24862.4083 | 7261.0619
350 | 6425 | GIRVAN 11021028 | 3.4886 | 255 | 28149.0621 | 28149.0621
351 | 1489 | DIAMOND SPRINGS 110518935 | 3.4873 | 80 | 10773.8274 | 10773.8274
352 | 7617 | WILLITS 1103826 | 3.4771 | 116 | 12450.1328 | 12450.1328
353 | 5540 | WOODSIDE 11018974 | 3.4676 | 207 | 21603.9606 | 21603.9606
354 | 1266 | MERCED FALLS 11029470 | 3.4217 | 140 | 36994.5762 | 36994.5762
355 | 539 | SHINGLE SPRINGS 21107742 | 3.4194 | 570 | 73601.743 | 73513.8191
356 | 6535 | PEORIA 170411232 | 3.4178 | 126 | 27614.6759 | 19016.7925
357 | 4789 | WYANDOTTE 11031976 | 3.4029 | 391 | 38602.5649 | 38602.5649
358 | 6989 | WYANDOTTE 110738438 | 3.3846 | 201 | 27120.5563 | 27120.5563
359 | 8471 | LAYTONVILLE 11022502 | 3.3788 | 197 | 27326.5363 | 27326.5363
360 | 4087 | MOLINO 1101322 | 3.3785 | 233 | 25513.0579 | 24774.6668
361 | 2683 | OREGON TRAIL 11031500 | 3.3774 | 294 | 41519.6675 | 41462.2575
362 | 1351 | CLARKSVILLE 210419772 | 3.3758 | 173 | 29518.3354 | 28983.153
363 | 3279 | OAKHURST 110310570 | 3.3736 | 103 | 15685.0936 | 15685.0936
364 | 4776 | RED BLUFF 110585632 | 3.3527 | 131 | 23855.6356 | 20457.0684
365 | 730 | MORGAN HILL 2105XR176 | 3.321 | 240 | 44144.6443 | 32979.6694
366 | 2279 | KANAKA 11011034 | 3.3103 | 94 | 21171.6713 | 21171.6713
367 | 8921 | ELK CREEK 11012032 | 3.3028 | 56 | 15248.6713 | 13755.3854
368 | 4477 | UPPER LAKE 1101660 | 3.2948 | 50 | 15466.5207 | 8469.2097
369 | 3701 | HIGGINS 11077559 | 3.2929 | 72 | 7116.1029 | 7109.6813
370 | 6566 | GARBERVILLE 1101circuit_breaker | 3.2592 | 77 | 14145.522 | 9321.3726
371 | 3191 | ANDERSON 1103circuit_breaker | 3.2314 | 56 | 33602.3141 | 5997.7664
372 | 4392 | GIRVAN 11019732 | 3.2288 | 288 | 33998.8263 | 33998.8263
373 | 5912 | AUBERRY 1101R2839 | 3.2266 | 129 | 20609.1212 | 20609.1212
374 | 3480 | SHINGLE SPRINGS 21092053 | 3.2207 | 88 | 9206.1637 | 9206.1637
375 | 888 | CORNING 110290036 | 3.2148 | 53 | 22997.6015 | 19887.703
376 | 5999 | ELK CREEK 11012004 | 3.2121 | 80 | 86740.0938 | 34785.4675
377 | 4382 | LOW GAP 11014086 | 3.1761 | 135 | 18494.205 | 18494.205
378 | 1883 | PANORAMA 1101circuit_breaker | 3.1611 | 23 | 30501.9872 | 4988.6634
379 | 5067 | MOLINO 1102658 | 3.1554 | 146 | 17538.0269 | 17538.0269
380 | 2591 | TEMPLETON 2111A66 | 3.1522 | 495 | 54317.8357 | 54317.8357
381 | 5210 | BEAR VALLEY 210511210 | 3.1464 | 103 | 27422.5497 | 27422.5497
382 | 5878 | PUEBLO 210378504 | 3.1314 | 124 | 19482.7251 | 12406.3687
383 | 6188 | MERCED FALLS 110238748 | 3.1264 | 115 | 24704.6356 | 24704.6356
384 | 1852 | OREGON TRAIL 110249144 | 3.1249 | 205 | 34141.3008 | 28540.0535
385 | 5512 | FORT SEWARD 1121circuit_breaker | 3.1199 | 74 | 11681.8525 | 11649.7657
386 | 1027 | GARBERVILLE 11028652 | 3.1063 | 217 | 21012.1269 | 21012.1269
387 | 603 | KERCKHOFF 1101circuit_breaker | 3.1027 | 42 | 27412.9116 | 27412.9116
388 | 8719 | CALISTOGA 110189150 | 3.0414 | 121 | 15360.2828 | 15360.2828
389 | 3223 | ANDERSON 11031600 | 3.0334 | 35 | 17298.4129 | 4989.8706
390 | 6065 | SAN MIGUEL 1104N60 | 3.0085 | 49 | 14225.5578 | 12563.9317
391 | 5157 | GARBERVILLE 11022500 | 3.0015 | 231 | 25786.904 | 25786.904
392 | 7292 | JAMESON 1103circuit_breaker | 2.9634 | 26 | 17445.1976 | 3720.1837
393 | 383 | VASCO 1102MR176 | 2.9401 | 152 | 68431.2769 | 62221.1335
394 | 4284 | CALISTOGA 1102769230 | 2.9316 | 96 | 27488.654 | 16210.9352
395 | 1703 | NARROWS 21022220 | 2.9277 | 329 | 45257.431 | 43302.8869
396 | 7319 | JAMESON 110265516 | 2.8975 | 116 | 36531.3564 | 24405.9769
397 | 5027 | HALSEY 11012414 | 2.8785 | 221 | 23778.9553 | 23778.9553
398 | 6814 | COTATI 1103circuit_breaker | 2.8651 | 54 | 19561.5616 | 19561.5616
399 | 1291 | MOLINO 1102178 | 2.8607 | 179 | 21902.7203 | 19242.2295
400 | 9323 | GARBERVILLE 110256048 | 2.8488 | 91 | 7998.8346 | 7998.8346
401 | 4552 | ELK CREEK 11012212 | 2.8289 | 72 | 53890.7637 | 17989.0535
402 | 7852 | ELK CREEK 11012002 | 2.7729 | 29 | 48388.1891 | 24592.8123
403 | 5431 | PUEBLO 11041304 | 2.7671 | 175 | 30920.9317 | 30920.9317
404 | 7733 | BANGOR 1101circuit_breaker | 2.7495 | 152 | 34104.446 | 28650.9927
405 | 7817 | DESCHUTES 11019722 | 2.7455 | 40 | 7564.9094 | 4975.6844
406 | 5091 | WILLITS 1104504 | 2.7258 | 288 | 36161.7196 | 36161.7196
407 | 2077 | GARBERVILLE 1102circuit_breaker | 2.7161 | 159 | 26078.7579 | 17301.6263
408 | 8475 | SAND CREEK 1103circuit_breaker | 2.6938 | 69 | 20610.8944 | 20610.8944
409 | 861 | FROGTOWN 170275252 | 2.6848 | 443 | 97052.7173 | 90444.8522
410 | 4380 | WILLITS 1103968 | 2.6769 | 361 | 44486.495 | 42022.0904
411 | 5902 | OAKHURST 110210100 | 2.6736 | 125 | 18754.034 | 16350.2682
412 | 952 | KANAKA 110183288 | 2.666 | 290 | 28024.1151 | 28024.1151
413 | 7656 | NORTH DUBLIN 2103circuit_breaker | 2.6565 | 75 | 24183.6175 | 20889.9745
414 | 1273 | DESCHUTES 11011652 | 2.6436 | 203 | 39313.9968 | 32556.3926
415 | 7419 | CLOVERDALE 11024646 | 2.6302 | 79 | 24017.6199 | 22119.9907
416 | 801 | CLOVERDALE 1102570 | 2.6177 | 182 | 34152.262 | 26431.4448
417 | 3065 | HORSESHOE 110150140 | 2.5933 | 56 | 10038.7802 | 6170.3672
418 | 5502 | HARTLEY 1101658 | 2.5796 | 15 | 21971.0708 | 4569.0388
419 | 514 | DUNLAP 11037220 | 2.5547 | 184 | 39952.2483 | 39952.2483
420 | 6968 | CLARKSVILLE 210575884 | 2.5391 | 78 | 18035.3275 | 17165.4943
421 | 5749 | HARTLEY 11011306 | 2.5372 | 80 | 20418.473 | 15400.0788
422 | 7153 | NORTH BRANCH 110111158 | 2.532 | 52 | 45851.8623 | 16351.0693
423 | 1215 | EL DORADO PH 210126000 | 2.53 | 517 | 55423.1935 | 55423.1935
424 | 4569 | WYANDOTTE 11031504 | 2.5217 | 139 | 23694.4018 | 16411.1206
425 | 6754 | CLARKSVILLE 210419632 | 2.5013 | 50 | 14659.9971 | 8385.252
426 | 915 | MIDDLETOWN 1101548 | 2.4782 | 239 | 39630.2884 | 36627.2391
427 | 7987 | CAYETANO 21099504 | 2.4769 | 62 | 23311.7324 | 23307.0461
428 | 7449 | BEAR VALLEY 21014160 | 2.4701 | 178 | 36553.6326 | 36553.6326
429 | 3014 | PLACERVILLE 21061104 | 2.4614 | 779 | 80528.8854 | 80528.8854
430 | 2624 | FROGTOWN 170212282 | 2.4605 | 406 | 58310.0701 | 58310.0701
431 | 589 | FORESTHILL 11022106 | 2.4513 | 453 | 45220.1977 | 45220.1977
432 | 5453 | CHALLENGE 1101circuit_breaker | 2.4502 | 273 | 26688.0859 | 26688.0859
433 | 3084 | HOPLAND 1101768 | 2.4461 | 134 | 32085.8687 | 26862.8023
434 | 1059 | CLAYTON 2212Y504R | 2.4403 | 115 | 18903.0653 | 18903.0653
435 | 7722 | MONTICELLO 1101718 | 2.4388 | 135 | 47865.0064 | 42515.7179
436 | 9243 | BOLINAS 1101530 | 2.4287 | 113 | 17644.1845 | 17644.1845
437 | 3082 | MORGAN HILL 2105XR564 | 2.4234 | 41 | 11614.6161 | 8673.0497
438 | 8695 | BROWNS VALLEY 110117011 | 2.4233 | 25 | 3005.3172 | 3005.3172
439 | 6595 | DESCHUTES 11011654 | 2.4192 | 227 | 28373.2901 | 28373.2901
440 | 2594 | APPLE HILL 21028372 | 2.4161 | 777 | 101166.6359 | 90180.3006
441 | 6073 | SALMON CREEK 1101196 | 2.4025 | 13 | 11722.7376 | 5757.7629
442 | 6431 | PUTAH CREEK 11033851 | 2.3961 | 16 | 8317.7311 | 6216.3391
443 | 1099 | MERCED FALLS 110287352 | 2.3721 | 161 | 42810.09 | 42562.7821
444 | 4267 | FRUITLAND 114195324 | 2.3645 | 139 | 14576.7142 | 14576.7142
445 | 5945 | COARSEGOLD 2104570682 | 2.3629 | 18 | 3262.933 | 3262.933
446 | 1668 | GARBERVILLE 11022010 | 2.3388 | 100 | 10929.7392 | 10929.7392
447 | 7256 | ATASCADERO 1103A06 | 2.3346 | 382 | 60068.7168 | 56511.8674
448 | 1932 | GARBERVILLE 11011514 | 2.3186 | 223 | 23737.6018 | 23737.6018
449 | 3525 | SANTA MARIA 1108M80 | 2.2952 | 344 | 94108.6643 | 94108.6643
450 | 1154 | HIGGINS 11044281 | 2.2943 | 188 | 21369.438 | 21369.438
451 | 3620 | MARIPOSA 210110070 | 2.2881 | 317 | 41751.638 | 41751.638
452 | 876 | MARIPOSA 210110240 | 2.2858 | 239 | 34426.9078 | 34426.9078
453 | 7909 | PEORIA 1705circuit_breaker | 2.2801 | 52 | 11472.2383 | 11339.1152
454 | 4340 | WILLITS 110337504 | 2.2681 | 10 | 5389.9576 | 1413.5779
455 | 9224 | WILLITS 1103circuit_breaker | 2.266 | 35 | 6322.4453 | 4233.1434
456 | 4643 | MORGAN HILL 2111XR398 | 2.263 | 410 | 63830.0009 | 59220.7716
457 | 6737 | POTTER VALLEY P H 110564118 | 2.2567 | 11 | 15416.9418 | 2045.917
458 | 1017 | MIDDLETOWN 11021312 | 2.2378 | 100 | 15846.2392 | 15846.2392
459 | 8315 | NORTH DUBLIN 210311101 | 2.2349 | 26 | 5926.9536 | 5926.9536
460 | 1212 | NARROWS 2102circuit_breaker | 2.229 | 234 | 39334.1146 | 36006.3008
461 | 4905 | LAYTONVILLE 1102circuit_breaker | 2.2274 | 114 | 20680.6827 | 16837.2871
462 | 6292 | GEYSERVILLE 110137454 | 2.2257 | 85 | 19682.6267 | 10482.9729
463 | 2318 | WHITMORE 11011594 | 2.2253 | 282 | 39015.2543 | 39015.2543
464 | 4582 | COPPERMINE 1104R755 | 2.2177 | 41 | 99071.0889 | 14117.8234
465 | 6887 | MIRABEL 1101116 | 2.2124 | 158 | 17803.3709 | 16655.9357
466 | 14 | MENDOCINO 110137462 | 2.2035 | 102 | 38310.1036 | 11379.0989
467 | 6626 | CLARKSVILLE 2104circuit_breaker | 2.1887 | 36 | 16768.2889 | 14071.4401
468 | 2790 | MENDOCINO 110148750 | 2.1767 | 206 | 28628.3227 | 28628.3227
469 | 8289 | ANTLER 11011376 | 2.1695 | 130 | 14477.8455 | 14477.8455
470 | 500 | CALISTOGA 110143924 | 2.1672 | 98 | 14779.5747 | 11371.1135
471 | 7091 | GARBERVILLE 11011770 | 2.1661 | 137 | 13857.9245 | 13857.9245
472 | 4785 | PANORAMA 11021342 | 2.1604 | 88 | 41106.3194 | 19597.5982
473 | 8031 | PIKE CITY 11011720 | 2.1584 | 89 | 9790.3862 | 9790.3862
474 | 7725 | PIKE CITY 1102circuit_breaker | 2.1559 | 104 | 15132.7411 | 15132.7411
475 | 5041 | COTATI 1103132 | 2.1508 | 83 | 40702.0776 | 40702.0776
476 | 5971 | GARBERVILLE 110135706 | 2.1352 | 158 | 16258.1269 | 16258.1269
477 | 6920 | LOW GAP 11014160 | 2.1226 | 319 | 34991.7062 | 34571.9467
478 | 2142 | GEYSERVILLE 110289714 | 2.1211 | 47 | 20357.282 | 4342.1142
479 | 865 | MORGAN HILL 2105XR152 | 2.1171 | 108 | 20565.0196 | 11909.7787
480 | 3782 | WILLITS 11032506 | 2.0878 | 164 | 19672.0333 | 19186.052
481 | 2816 | TEMPLETON 2110R90 | 2.0874 | 581 | 120177.2391 | 106123.5164
482 | 4620 | COTATI 110379140 | 2.0797 | 85 | 19876.9325 | 15556.81
483 | 3208 | KESWICK 11019712 | 2.0674 | 244 | 29985.2487 | 29985.2487
484 | 2480 | OCEANO 1104Q08 | 2.0619 | 180 | 19963.0067 | 19963.0067
485 | 640 | MIDDLETOWN 110148212 | 2.0586 | 145 | 34910.5992 | 34597.7705
486 | 156 | MOUNTAIN QUARRIES 21011346 | 2.0533 | 476 | 49477.6546 | 49477.6546
487 | 5941 | CALAVERAS CEMENT 110111188 | 2.0507 | 342 | 48300.9598 | 48300.9598
488 | 3414 | WILLITS 110434008 | 2.0475 | 370 | 36886.2403 | 36886.2403
489 | 6039 | WYANDOTTE 110796390 | 2.047 | 110 | 16389.5684 | 13317.923
490 | 9096 | COARSEGOLD 21046210 | 2.045 | 101 | 17177.2503 | 17177.2503
491 | 7064 | PUTAH CREEK 110246012 | 2.044 | 7 | 4686.2992 | 945.6535
492 | 2918 | TEMPLETON 2111R86 | 2.0361 | 152 | 23059.3782 | 17358.9842
493 | 1008 | LOW GAP 11012094 | 2.036 | 225 | 27430.2028 | 24081.2978
494 | 623 | BRUNSWICK 11062790 | 2.0356 | 132 | 17549.6884 | 15218.0635
495 | 5444 | ALHAMBRA 110582622 | 2.0351 | 293 | 41695.7116 | 41695.7116
496 | 3918 | CURTIS 1704circuit_breaker | 2.0278 | 206 | 22861.2714 | 22095.5217
497 | 2407 | SAN LUIS OBISPO 110342344 | 2.0277 | 69 | 17394.6877 | 14174.6452
498 | 3243 | OLETA 11011217 | 2.0261 | 93 | 55473.8409 | 42415.24
499 | 6371 | UPPER LAKE 110175370 | 2.0223 | 133 | 23613.6779 | 17069.5104
500 | 8339 | BRIDGEVILLE 110169866 | 2.0195 | 78 | 10521.7386 | 10521.7386
501 | 1062 | PLACER 1103circuit_breaker | 2.0012 | 185 | 47113.7621 | 20608.1987
502 | 3694 | BEAR VALLEY 21014500 | 1.9992 | 111 | 131623.5309 | 34089.7521
503 | 8745 | FRUITLAND 114137410 | 1.9989 | 80 | 8875.6069 | 7642.4024
504 | 1493 | RIO DELL 11021504 | 1.988 | 187 | 19231.7001 | 17338.0675
505 | 8455 | STAFFORD 11021202 | 1.9742 | 16 | 12713.8882 | 11742.1904
506 | 5406 | HIGHLANDS 110280660 | 1.9661 | 46 | 12052.2865 | 9091.4024
507 | 703 | ALTO 1124430 | 1.9653 | 120 | 11716.5372 | 11716.5372
508 | 6533 | OLETA 1102circuit_breaker | 1.9304 | 131 | 24558.1337 | 21808.3893
509 | 3425 | MOLINO 1102396 | 1.916 | 208 | 25719.6473 | 25719.6473
510 | 2131 | PUEBLO 1105696 | 1.9158 | 155 | 46972.3367 | 30001.1055
511 | 4605 | WYANDOTTE 11031508 | 1.9154 | 355 | 43569.7992 | 43569.7992
512 | 5574 | GARBERVILLE 11026084 | 1.9135 | 259 | 24635.362 | 24635.362
513 | 6351 | KANAKA 110175744 | 1.9104 | 180 | 17040.8886 | 17040.8886
514 | 7350 | PASO ROBLES 11032731 | 1.901 | 16 | 2616.6102 | 2616.6102
515 | 998 | APPLE HILL 21029722 | 1.8951 | 565 | 61644.8871 | 61644.8871
516 | 6262 | DUNLAP 11027060 | 1.8912 | 180 | 28682.1944 | 28682.1944
517 | 3171 | WISE 1102circuit_breaker | 1.8889 | 215 | 30515.1162 | 29505.5664
518 | 5262 | PENRYN 11052406 | 1.8821 | 50 | 19927.713 | 4637.0241
519 | 1326 | FULTON 11024522 | 1.86 | 118 | 19948.4708 | 13642.0128
520 | 1793 | BELL 11082226 | 1.8417 | 354 | 41003.1194 | 38840.6709
521 | 2693 | SAN BENITO 210136912 | 1.8411 | 23 | 20320.0338 | 7482.8922
522 | 6074 | FORT ROSS 112170288 | 1.8394 | 98 | 18893.0241 | 18893.0241
523 | 7578 | HOPLAND 110194006 | 1.8322 | 167 | 24484.3021 | 18955.1203
524 | 3793 | RINCON 1103474 | 1.828 | 286 | 29554.6121 | 29554.6121
525 | 2565 | JESSUP 11031540 | 1.823 | 25 | 24454.6209 | 2468.2792
526 | 1477 | GARBERVILLE 11011750 | 1.7905 | 201 | 23805.8246 | 23509.5028
527 | 2343 | BONNIE NOOK 1102circuit_breaker | 1.7863 | 555 | 55059.6809 | 55059.6809
528 | 3501 | PENRYN 1107346 | 1.778 | 210 | 40334.4226 | 22020.6709
529 | 4335 | ELK CREEK 11012228 | 1.773 | 24 | 16936.7028 | 4717.8323
530 | 3201 | BEAR VALLEY 21059480 | 1.7638 | 64 | 19971.3977 | 19971.3977
531 | 7857 | NAPA 11121723 | 1.7554 | 100 | 18404.557 | 15407.0792
532 | 5679 | CHALLENGE 11015460 | 1.7545 | 186 | 19026.207 | 19026.207
533 | 7240 | CLAYTON 22127758 | 1.7501 | 42 | 5210.7596 | 5210.7596
534 | 102 | WYANDOTTE 11101954 | 1.749 | 165 | 43471.4021 | 19698.3887
535 | 3548 | CHALLENGE 11021902 | 1.748 | 82 | 8106.7957 | 8106.7957
536 | 9239 | BRIDGEVILLE 1101circuit_breaker | 1.721 | 99 | 13703.3241 | 13703.3241
537 | 5326 | WYANDOTTE 1109circuit_breaker | 1.7162 | 27 | 15084.5037 | 3677.1991
538 | 2362 | WOODSIDE 11018884 | 1.6995 | 136 | 12455.5334 | 12455.5334
539 | 5242 | DUNBAR 1102261774 | 1.6915 | 171 | 21759.8537 | 21759.8537
540 | 4898 | WOODACRE 11011456 | 1.6794 | 62 | 6154.4242 | 6154.4242
541 | 2332 | GRASS VALLEY 11032110 | 1.6757 | 286 | 32324.9618 | 31856.0669
542 | 9493 | MIDDLETOWN 1101612 | 1.6703 | 37 | 12452.9617 | 12452.9617
543 | 6357 | HIGHLANDS 11031282 | 1.6676 | 160 | 26925.5772 | 23288.0926
544 | 3148 | WILLITS 11032500 | 1.6622 | 178 | 48289.254 | 48289.254
545 | 7448 | OAKHURST 11016220 | 1.6529 | 113 | 32301.3797 | 32301.3797
546 | 2860 | SHINGLE SPRINGS 210819762 | 1.6494 | 42 | 8714.0124 | 6558.8623
547 | 5408 | SANTA YNEZ 1101Y52 | 1.6408 | 92 | 38825.6098 | 36116.1135
548 | 8781 | BEAR VALLEY 21059570 | 1.6291 | 52 | 12951.7997 | 12951.7997
549 | 1907 | UKIAH 1113circuit_breaker | 1.6263 | 104 | 25541.5735 | 12034.1255
550 | 7191 | GARBERVILLE 110197300 | 1.6204 | 213 | 22729.2098 | 22729.2098
551 | 6679 | TEMPLETON 21136055 | 1.6183 | 58 | 63807.832 | 63807.832
552 | 9000 | PASO ROBLES 110359763 | 1.6161 | 31 | 4529.9707 | 4529.9707
553 | 6403 | LAYTONVILLE 11011760 | 1.6155 | 126 | 20359.96 | 15633.6438
554 | 7221 | KONOCTI 1102948 | 1.6146 | 71 | 12598.6341 | 9863.4507
555 | 4238 | APPLE HILL 11038412 | 1.6107 | 294 | 64897.3333 | 64897.3333
556 | 3296 | VOLTA 11021646 | 1.5942 | 330 | 38830.605 | 37561.3918
557 | 5290 | PENRYN 11072706 | 1.594 | 66 | 24016.257 | 7658.9338
558 | 1205 | TEMPLETON 2113A08 | 1.582 | 80 | 39393.6221 | 13880.8278
559 | 5797 | RISING RIVER 11011530 | 1.5819 | 103 | 28387.6321 | 16264.4687
560 | 2130 | CALPELLA 1101542 | 1.5815 | 220 | 37984.1313 | 37983.2329
561 | 6476 | HOOPA 11013304 | 1.578 | 232 | 27461.6659 | 27461.6659
562 | 3789 | BELLEVUE 2103478 | 1.5749 | 75 | 32688.1249 | 13352.3887
563 | 5259 | DUNBAR 1103534 | 1.5736 | 202 | 28145.853 | 25938.9873
564 | 3876 | FITCH MOUNTAIN 111324550 | 1.5669 | 113 | 35120.4777 | 12900.9804
565 | 4945 | SAN LUIS OBISPO 1107V60 | 1.5598 | 182 | 25701.6823 | 25701.6823
566 | 6264 | MORGAN HILL 2105XR070 | 1.5548 | 61 | 13816.8053 | 9521.4048
567 | 7373 | BUELLTON 1101Y26 | 1.5514 | 100 | 25494.2608 | 23209.1215
568 | 7594 | WILLITS 110337506 | 1.5375 | 177 | 18589.4866 | 18589.4866
569 | 6699 | PENRYN 110551676 | 1.537 | 116 | 18974.9476 | 11966.6651
570 | 6042 | OLETA 11014768 | 1.5211 | 77 | 21913.0144 | 18073.0157
571 | 1700 | LUCERNE 1106664 | 1.5203 | 136 | 17950.7499 | 15102.6309
572 | 2067 | WEST POINT 1102circuit_breaker | 1.5044 | 182 | 28676.4886 | 28676.4886
573 | 8735 | SAND CREEK 11037823F | 1.4976 | 26 | 7345.0348 | 7345.0348
574 | 6448 | DEL MAR 2109circuit_breaker | 1.4906 | 16 | 10524.7005 | 3009.0839
575 | 796 | DUNBAR 1102246 | 1.4905 | 209 | 21342.108 | 21342.108
576 | 1080 | HIGHLANDS 110275140 | 1.485 | 84 | 32224.2832 | 13187.2724
577 | 924 | WEST POINT 110293116 | 1.4767 | 642 | 137475.3807 | 137475.3807
578 | 590 | STAFFORD 1102524 | 1.4635 | 41 | 20662.3416 | 9046.5504
579 | 9084 | HARTLEY 11014710 | 1.459 | 14 | 2414.0517 | 2414.0517
580 | 1955 | ELECTRA 1101circuit_breaker | 1.451 | 377 | 51915.3729 | 51915.3729
581 | 2039 | SAN JUSTO 110136902 | 1.4509 | 116 | 23604.3976 | 19755.8941
582 | 4291 | HIGGINS 11071070 | 1.4434 | 122 | 13372.1867 | 11964.8264
583 | 6409 | CLARK ROAD 110281296 | 1.4416 | 53 | 21924.1005 | 10798.5955
584 | 600 | DIAMOND SPRINGS 11062100 | 1.4372 | 530 | 62659.5156 | 62659.5156
585 | 813 | ATASCADERO 1103A18 | 1.437 | 82 | 29119.0556 | 12533.7225
586 | 2655 | PINE GROVE 11023172 | 1.4243 | 526 | 59226.0308 | 59226.0308
587 | 7961 | FORT ROSS 1121circuit_breaker | 1.4149 | 114 | 20387.5307 | 20387.5307
588 | 7920 | CAYETANO 2111circuit_breaker | 1.4124 | 29 | 18775.78 | 8282.7924
589 | 4073 | GARBERVILLE 11021510 | 1.412 | 183 | 21228.5996 | 21228.5996
590 | 2312 | OLETA 11021204 | 1.4097 | 304 | 47208.0794 | 39941.6187
591 | 7388 | NORTH DUBLIN 21039473 | 1.4066 | 24 | 4731.0233 | 3725.6021
592 | 4667 | CLOVERDALE 1102674 | 1.4022 | 110 | 31757.8273 | 25986.6813
593 | 1336 | RED BLUFF 11051564 | 1.3953 | 10 | 17079.3867 | 1829.5964
594 | 3469 | WILLOW CREEK 11014904 | 1.3923 | 282 | 29923.3138 | 29923.3138
595 | 5934 | GEYSERVILLE 110135492 | 1.3877 | 94 | 34732.69 | 14162.9366
596 | 453 | KONOCTI 1102596 | 1.3865 | 97 | 21540.3672 | 15791.9595
597 | 5717 | TEMPLETON 2113A10 | 1.3839 | 273 | 49852.2593 | 49852.2593
598 | 5552 | PENRYN 11072704 | 1.3814 | 20 | 9132.2031 | 1994.2196
599 | 456 | WOODACRE 110196844 | 1.3671 | 83 | 9464.5637 | 9464.5637
600 | 6904 | SILVERADO 2104708 | 1.3627 | 61 | 7838.2779 | 5638.2492
601 | 4557 | PINE GROVE 11023168 | 1.3617 | 474 | 48743.192 | 48743.192
602 | 926 | CURTIS 17036064 | 1.3601 | 259 | 31678.1851 | 30178.8533
603 | 3038 | GARBERVILLE 11022540 | 1.3555 | 185 | 28743.4558 | 23928.4593
604 | 6402 | MIDDLETOWN 11011325 | 1.3499 | 132 | 13821.691 | 13821.691
605 | 2193 | MOLINO 1102318 | 1.3437 | 332 | 31101.718 | 31101.718
606 | 4009 | TEMPLETON 2113A60 | 1.3365 | 49 | 14423.3233 | 10180.3906
607 | 8908 | GARBERVILLE 110237054 | 1.3215 | 111 | 14832.6398 | 13349.1892
608 | 3986 | WEST POINT 110236676 | 1.3099 | 232 | 27353.6284 | 27353.6284
609 | 964 | HIGGINS 11102408 | 1.3081 | 532 | 57049.967 | 57049.967
610 | 3787 | COTATI 1102681 | 1.3041 | 53 | 6118.1742 | 6118.1742
611 | 7989 | PUTAH CREEK 110264044 | 1.2995 | 57 | 23984.3958 | 17799.2497
612 | 1151 | CORRAL 110336680 | 1.2973 | 87 | 32149.378 | 13725.8331
613 | 5748 | DOBBINS 110169722 | 1.2933 | 90 | 10673.4289 | 10673.4289
614 | 6091 | ELECTRA 11011238 | 1.2918 | 41 | 11276.5469 | 5695.7641
615 | 4618 | LAYTONVILLE 1101402 | 1.2901 | 230 | 37926.2925 | 37059.5588
616 | 6851 | UPPER LAKE 1101472084 | 1.29 | 50 | 11576.044 | 7182.4083
617 | 6642 | NAPA 11121302 | 1.2796 | 93 | 70942.9874 | 29080.6889
618 | 5007 | ALTO 1125902 | 1.2403 | 159 | 19412.9994 | 19412.9994
619 | 5882 | ANDERSON 1101circuit_breaker | 1.2353 | 40 | 14514.7271 | 4993.2396
620 | 5573 | SAN JOAQUIN #3 11035100 | 1.2288 | 330 | 42249.6443 | 42249.6443
621 | 8799 | DUNBAR 1102694641 | 1.2287 | 60 | 6527.852 | 6527.852
622 | 1921 | MESA 1103M72 | 1.2277 | 123 | 40398.8978 | 14559.7479
623 | 4183 | PUEBLO 2102618 | 1.2276 | 33 | 26675.4835 | 3904.0753
624 | 5597 | TEMPLETON 2110N32 | 1.2242 | 283 | 47441.6231 | 46049.4952
625 | 1490 | FROGTOWN 17021573 | 1.2224 | 182 | 28787.0124 | 28787.0124
626 | 6417 | POTTER VALLEY P H 110537476 | 1.2189 | 20 | 14076.6161 | 3321.5283
627 | 324 | WEST POINT 11024790 | 1.2181 | 452 | 53036.5916 | 53036.5916
628 | 2508 | PLACERVILLE 111019582 | 1.216 | 299 | 35889.5226 | 35889.5226
629 | 6718 | SYCAMORE CREEK 1111circuit_breaker | 1.21 | 77 | 28716.7912 | 12547.7716
630 | 4943 | APPLE HILL 210251792 | 1.2026 | 129 | 14681.2766 | 14681.2766
631 | 953 | BRUNSWICK 110651484 | 1.1964 | 314 | 40473.5667 | 32219.8738
632 | 7470 | MARIPOSA 210197142 | 1.1909 | 47 | 7406.0615 | 7406.0615
633 | 1169 | OCEANO 1104V36 | 1.1903 | 108 | 21377.0626 | 15485.8164
634 | 4497 | SAN LUIS OBISPO 1107V02 | 1.1855 | 219 | 29266.1548 | 29017.7252
635 | 810 | TASSAJARA 210419042 | 1.182 | 59 | 13671.8199 | 9296.9258
636 | 8636 | BUCKS CREEK 1102circuit_breaker | 1.1761 | 202 | 47507.7824 | 47507.7824
637 | 5956 | COARSEGOLD 210490356 | 1.1744 | 18 | 27329.0227 | 7895.0402
638 | 7013 | SILVERADO 2105658898 | 1.1742 | 239 | 27768.6234 | 27768.6234
639 | 519 | PLACERVILLE 210692012 | 1.1707 | 451 | 46683.5024 | 46683.5024
640 | 4289 | APPLE HILL 210297982 | 1.1695 | 157 | 15759.3574 | 15759.3574
641 | 710 | MONTE RIO 11125040 | 1.1664 | 67 | 6507.7866 | 6507.7866
642 | 2283 | BRUNSWICK 11052140 | 1.1607 | 306 | 55502.9271 | 55502.9271
643 | 5581 | TIDEWATER 210614072 | 1.1585 | 22 | 6206.8729 | 5897.3117
644 | 6145 | PHILO 1102circuit_breaker | 1.1574 | 98 | 20191.5402 | 10918.6301
645 | 2835 | VOLTA 11011596 | 1.1515 | 222 | 69371.8758 | 69371.8758
646 | 4543 | NARROWS 210551582 | 1.1483 | 130 | 15330.2671 | 15330.2671
647 | 5162 | SAN JOAQUIN #3 1102circuit_breaker | 1.1462 | 135 | 15601.4012 | 15601.4012
648 | 4466 | PHILO 1102928 | 1.1399 | 241 | 24804.6018 | 22042.0965
649 | 3315 | SILVERADO 2102714 | 1.1353 | 46 | 18049.585 | 5471.307
650 | 4254 | BELLEVUE 2103552 | 1.1351 | 78 | 24038.0516 | 11666.895
651 | 1888 | ALLEGHANY 1102circuit_breaker | 1.1338 | 258 | 29167.4333 | 29167.4333
652 | 7532 | FRUITLAND 11426064 | 1.132 | 44 | 13612.899 | 9593.2152
653 | 77 | WHEATLAND 110591170 | 1.1314 | 60 | 85775.1349 | 15619.5143
654 | 9040 | LAYTONVILLE 1102682 | 1.1306 | 229 | 23844.5349 | 23844.5349
655 | 1557 | COLUMBIA HILL 1101circuit_breaker | 1.1239 | 557 | 63408.1463 | 63408.1463
656 | 5266 | FORESTHILL 11011802 | 1.1194 | 359 | 35584.2456 | 35584.2456
657 | 512 | WILLITS 1103696 | 1.1132 | 31 | 15378.4562 | 8552.3738
658 | 3742 | STILLWATER 11011320 | 1.1067 | 263 | 32280.2887 | 31197.3185
659 | 5238 | SILVERADO 2105616 | 1.1045 | 98 | 29229.1132 | 11577.8412
660 | 4590 | FITCH MOUNTAIN 1113352 | 1.1004 | 81 | 19254.3259 | 9077.2683
661 | 2867 | JESSUP 110338864 | 1.0991 | 26 | 12088.203 | 2871.393
662 | 5847 | SONOMA 1102118 | 1.0988 | 78 | 12055.2085 | 9282.9853
663 | 6741 | BIG BEND 1102circuit_breaker | 1.0961 | 189 | 27533.9662 | 27533.9662
664 | 4203 | MESA 11016111 | 1.0942 | 164 | 41196.8537 | 37685.5687
665 | 7058 | KANAKA 11011044 | 1.0893 | 70 | 9870.7715 | 9870.7715
666 | 2016 | PUEBLO 11042802 | 1.0887 | 87 | 17054.4612 | 14988.5406
667 | 7787 | GARBERVILLE 11012026 | 1.0885 | 108 | 10220.4249 | 10220.4249
668 | 5815 | WOODWARD 210878448 | 1.0848 | 89 | 47714.7864 | 28435.4926
669 | 3416 | APPLE HILL 21027502 | 1.0827 | 361 | 37014.7956 | 37014.7956
670 | 7670 | PENRYN 110550550 | 1.0768 | 28 | 22728.582 | 3634.5722
671 | 8360 | KESWICK 11011586 | 1.0737 | 24 | 11919.3257 | 11919.3257
672 | 3522 | PIT NO 1 11011552 | 1.0695 | 137 | 42573.1939 | 20793.5873
673 | 3291 | PEORIA 17051834 | 1.0599 | 203 | 38348.1492 | 37631.0076
674 | 9469 | KIRKER 2104442850 | 1.0594 | 17 | 9153.4289 | 9153.4289
675 | 7126 | MARTELL 1102circuit_breaker | 1.0592 | 71 | 10830.1822 | 7916.9254
676 | 2772 | PENRYN 110651674 | 1.0583 | 12 | 19482.4094 | 1609.198
677 | 2254 | STANISLAUS 17011812 | 1.0536 | 316 | 31400.4893 | 31400.4893
678 | 1283 | RINCON 1101578 | 1.0535 | 168 | 30007.9481 | 27632.8586
679 | 5984 | SAN JUSTO 11014339 | 1.048 | 87 | 17685.5192 | 11461.6704
680 | 5420 | MIRABEL 1101298 | 1.0384 | 213 | 20371.1921 | 20135.0832
681 | 6107 | APPLE HILL 21026552 | 1.0355 | 178 | 20150.542 | 20150.542
682 | 1805 | VOLTA 11021650 | 1.0318 | 291 | 34674.2454 | 34674.2454
683 | 8297 | SANTA YNEZ 1104circuit_breaker | 1.0291 | 2 | 13829.7068 | 295.2522
684 | 4163 | SAN JOAQUIN #2 1103157026 | 1.0238 | 42 | 5166.9066 | 5166.9066
685 | 2439 | REDBUD 1101circuit_breaker | 1.0178 | 133 | 23104.2807 | 15284.1769
686 | 5104 | ANDERSON 11011752 | 1.0159 | 21 | 7452.6013 | 5082.8869
687 | 4411 | MERCED FALLS 110285002 | 1.0125 | 158 | 57333.7596 | 57333.7596
688 | 4875 | MOLINO 110241392 | 1.0103 | 64 | 23482.9452 | 6064.4075
689 | 883 | RACETRACK 170455798 | 1.0099 | 242 | 37898.11 | 37898.11
690 | 1325 | PENRYN 1107circuit_breaker | 1.0096 | 66 | 25919.7392 | 6429.3235
691 | 2019 | BUELLTON 1101Y06 | 1.0087 | 138 | 64675.3298 | 46315.0095
692 | 4890 | FROGTOWN 17028482 | 1.0035 | 150 | 23167.7877 | 23167.7877
693 | 8769 | CORNING 110185162 | 1.0007 | 22 | 9259.5842 | 9259.5842
694 | 8231 | COARSEGOLD 2104circuit_breaker | 0.99973 | 22 | 3906.143 | 3906.143
695 | 6701 | MOUNTAIN QUARRIES 21011180 | 0.9995 | 216 | 20702.9508 | 20702.9508
696 | 3118 | PENNGROVE 1101170 | 0.99434 | 235 | 36370.6977 | 31125.6451
697 | 444 | CALISTOGA 11011087 | 0.9936 | 30 | 3128.3884 | 3128.3884
698 | 4554 | UPPER LAKE 1101452 | 0.98998 | 47 | 31292.3538 | 4787.2263
699 | 142 | SHADY GLEN 11022232 | 0.98939 | 165 | 16796.8272 | 16796.8272
700 | 7795 | FRUITLAND 11413902 | 0.98791 | 77 | 8223.6344 | 4505.0192
701 | 631 | PENRYN 110550548 | 0.98781 | 25 | 19476.8877 | 2946.7985
702 | 2013 | LAYTONVILLE 1101518 | 0.9831 | 27 | 36002.4776 | 3441.5642
703 | 7295 | STANISLAUS 1702circuit_breaker | 0.98169 | 80 | 12811.6118 | 12811.6118
704 | 5769 | MONTICELLO 1101630 | 0.97368 | 90 | 31569.6011 | 28630.1876
705 | 9095 | HIGGINS 11097863 | 0.97068 | 56 | 6799.2947 | 6799.2947
706 | 2297 | JESSUP 1102circuit_breaker | 0.96923 | 18 | 8672.7914 | 1622.8923
707 | 6874 | WEST POINT 110234416 | 0.9618 | 103 | 16938.9243 | 16938.9243
708 | 7545 | JESSUP 11011993 | 0.95999 | 48 | 4781.8496 | 4413.0116
709 | 2379 | CLEAR LAKE 11011302 | 0.95848 | 103 | 28050.5504 | 11041.6679
710 | 3858 | JAMESON 11059472 | 0.95833 | 33 | 11815.4027 | 3577.3351
711 | 6602 | JESSUP 11019752 | 0.95594 | 58 | 6269.3077 | 6269.3077
712 | 5383 | VASCO 110211338 | 0.95564 | 27 | 30852.0505 | 8850.5675
713 | 1082 | HOOPA 110137202 | 0.95424 | 319 | 46502.2253 | 39996.9216
714 | 3635 | SILVERADO 2102636 | 0.94825 | 60 | 9140.7797 | 6273.2424
715 | 3215 | OAKHURST 1101circuit_breaker | 0.94705 | 31 | 4768.9067 | 3669.1128
716 | 2205 | FROGTOWN 170113412 | 0.94506 | 547 | 62186.2508 | 62186.2508
717 | 8331 | WOODACRE 110191900 | 0.94168 | 56 | 22248.6035 | 10288.938
718 | 8284 | FRUITLAND 114293234 | 0.94073 | 23 | 18464.5673 | 18464.5673
719 | 315 | PIKE CITY 11011730 | 0.93378 | 126 | 13838.6427 | 13838.6427
720 | 4913 | RED BLUFF 11041566 | 0.92933 | 22 | 24175.3198 | 15161.638
721 | 3340 | HIGGINS 1104324510 | 0.92912 | 233 | 20001.4265 | 20001.4265
722 | 4613 | WILLITS 110391948 | 0.9269 | 68 | 11902.8785 | 11264.7541
723 | 8415 | COLUMBIA HILL 11012212 | 0.92054 | 125 | 14778.7102 | 14778.7102
724 | 6166 | TASSAJARA 2113MR276 | 0.91393 | 49 | 6265.9535 | 6095.1274
725 | 6237 | CALAVERAS CEMENT 11014786 | 0.91303 | 205 | 28957.9323 | 28957.9323
726 | 4359 | LUCERNE 1106526 | 0.906 | 105 | 17455.0829 | 16072.0884
727 | 7715 | CLAYTON 2215W531R | 0.90415 | 72 | 17365.1124 | 10534.5095
728 | 2906 | SYCAMORE CREEK 11112014 | 0.89661 | 294 | 36436.0286 | 36180.8061
729 | 5980 | MONTICELLO 110193384 | 0.89297 | 136 | 27868.9866 | 25527.468
730 | 4035 | ORO FINO 11022096 | 0.89108 | 110 | 22689.7759 | 22689.7759
731 | 8365 | BRIDGEVILLE 110237486 | 0.89087 | 96 | 18386.8195 | 16908.281
732 | 7265 | VACA DIXON 110118292 | 0.88798 | 5 | 9364.4146 | 1339.9258
733 | 3488 | OLETA 110113478 | 0.88359 | 109 | 24622.6296 | 19228.1516
734 | 2206 | CORRAL 110313474 | 0.87484 | 28 | 11606.5963 | 3896.5378
735 | 1073 | COLUMBIA HILL 1101764 | 0.8743 | 228 | 23872.6753 | 23872.6753
736 | 5439 | NARROWS 2101circuit_breaker | 0.86756 | 97 | 25133.8252 | 25133.8252
737 | 1677 | HIGGINS 11039753 | 0.86597 | 38 | 3306.1166 | 3306.1166
738 | 7162 | PENRYN 110790970 | 0.86532 | 18 | 6824.705 | 1720.141
739 | 9283 | WYANDOTTE 110932586 | 0.86529 | 19 | 2438.1505 | 2312.4178
740 | 3850 | DOBBINS 11015202 | 0.86432 | 204 | 27474.7329 | 26082.7071
741 | 3229 | REDBUD 1102510 | 0.8588 | 47 | 12965.106 | 5477.4083
742 | 1141 | DUNBAR 1101302 | 0.85826 | 124 | 16689.601 | 13818.0912
743 | 7007 | JAMESON 11028842 | 0.8556 | 5 | 9062.7483 | 757.4983
744 | 4072 | MONTICELLO 1101666 | 0.85521 | 88 | 22466.5413 | 16769.5218
745 | 782 | MESA 1101M86 | 0.8536 | 115 | 33506.261 | 18124.1497
746 | 2172 | MONTICELLO 11014360 | 0.85304 | 39 | 14746.7227 | 11112.131
747 | 6611 | WOODSIDE 110147872 | 0.84471 | 72 | 7099.6124 | 7099.6124
748 | 5327 | BIG BEND 1101641808 | 0.8397 | 285 | 46360.2755 | 46054.2939
749 | 3005 | SHADY GLEN 1102circuit_breaker | 0.83108 | 333 | 34434.861 | 33414.9149
750 | 8244 | PUTAH CREEK 11033783 | 0.82757 | 2 | 17433.8941 | 329.1954
751 | 1085 | BRUNSWICK 11042112 | 0.82634 | 292 | 30961.8119 | 30961.8119
752 | 271 | GEYSERVILLE 1102350 | 0.81998 | 50 | 31239.3548 | 6355.4918
753 | 4647 | APPLE HILL 110412842 | 0.81722 | 259 | 26827.6373 | 24430.5416
754 | 2774 | ALTO 1124432 | 0.81193 | 90 | 12584.9285 | 12584.9285
755 | 208 | APPLE HILL 110313312 | 0.81174 | 186 | 29140.0447 | 19652.8137
756 | 2011 | FRUITLAND 1141circuit_breaker | 0.80968 | 52 | 4594.941 | 4594.941
757 | 4728 | CURTIS 1705circuit_breaker | 0.80941 | 154 | 21968.5837 | 21100.4775
758 | 3324 | PENRYN 11051378 | 0.80356 | 14 | 3002.3902 | 1299.5417
759 | 2618 | CLAY 11031230 | 0.80242 | 168 | 30392.9883 | 24532.2816
760 | 6799 | SANTA YNEZ 1102circuit_breaker | 0.8015 | 13 | 14333.2897 | 1351.6956
761 | 5948 | CLARK ROAD 110292622 | 0.7963 | 436 | 49506.0782 | 49506.0782
762 | 3798 | BONNIE NOOK 110186696 | 0.79438 | 144 | 15534.4182 | 15534.4182
763 | 2700 | WHITMORE 110145262 | 0.79248 | 303 | 46035.1045 | 46035.1045
764 | 9385 | LAS GALLINAS A 1105532 | 0.78498 | 38 | 7102.1777 | 7030.3171
765 | 140 | MOUNTAIN QUARRIES 21011130 | 0.78465 | 321 | 31854.654 | 31854.654
766 | 4799 | WILLITS 110434006 | 0.78067 | 53 | 9186.411 | 6444.3113
767 | 3652 | FORESTHILL 110150486 | 0.77858 | 205 | 18756.9603 | 18756.9603
768 | 1708 | FORT BRAGG A 110195294 | 0.77737 | 307 | 43705.7865 | 43187.6602
769 | 6896 | BRIDGEVILLE 110137484 | 0.77693 | 101 | 16191.138 | 12953.0865
770 | 7755 | KESWICK 11011588 | 0.77598 | 79 | 14089.0434 | 14089.0434
771 | 5010 | SILVERADO 21023010 | 0.77557 | 57 | 20812.5079 | 5441.3026
772 | 8070 | RED BLUFF 11041302 | 0.77517 | 57 | 22589.5236 | 21098.7836
773 | 7588 | RISING RIVER 11011532 | 0.77491 | 18 | 7838.859 | 4719.7178
774 | 7283 | PHILO 11022600 | 0.7735 | 265 | 32189.254 | 32189.254
775 | 7057 | TEMPLETON 2113A12 | 0.77108 | 173 | 65018.3777 | 65018.3777
776 | 5990 | PARADISE 1103circuit_breaker | 0.76716 | 104 | 59708.3774 | 53143.2931
777 | 1103 | COARSEGOLD 210210040 | 0.76472 | 238 | 28189.7477 | 28189.7477
778 | 3240 | RED BLUFF 1104circuit_breaker | 0.76134 | 20 | 16940.324 | 2365.4631
779 | 4321 | OCEANO 1104Q06 | 0.75429 | 170 | 19967.3254 | 19967.3254
780 | 788 | ALLEGHANY 1101806 | 0.75237 | 164 | 19005.4498 | 19005.4498
781 | 4726 | PLACERVILLE 21069712 | 0.7516 | 368 | 39873.7428 | 39873.7428
782 | 1107 | SAN MIGUEL 1106circuit_breaker | 0.75051 | 138 | 93802.1913 | 56840.9678
783 | 787 | circuit_breaker | 0.74869 | 211 | 44267.9262 | 32849.6375
784 | 6812 | WILDWOOD 11011454 | 0.74635 | 34 | 12434.0103 | 12434.0103
785 | 258 | CLARK ROAD 11022584 | 0.74119 | 54 | 15088.9555 | 13236.8465
786 | 3383 | WOODACRE 1102851 | 0.74053 | 22 | 2053.4749 | 2053.4749
787 | 1536 | LAYTONVILLE 110264908 | 0.73565 | 45 | 10255.6361 | 5371.196
788 | 6583 | COARSEGOLD 21036110 | 0.73399 | 66 | 47978.9803 | 16696.1653
789 | 6260 | PINE GROVE 11026080 | 0.73263 | 526 | 56095.9807 | 56095.9807
790 | 6849 | HIGGINS 1104circuit_breaker | 0.72959 | 138 | 18704.9095 | 16734.2321
791 | 6721 | MIRABEL 1102334 | 0.72948 | 79 | 14759.2293 | 7485.5189
792 | 1287 | MOUNTAIN QUARRIES 210192474 | 0.72716 | 228 | 25079.5665 | 23834.445
793 | 6032 | MOLINO 1101891 | 0.72638 | 59 | 5070.4899 | 5053.4192
794 | 6120 | MONTE RIO 11131991 | 0.72411 | 88 | 11352.1197 | 11352.1197
795 | 4283 | PLACERVILLE 210619552 | 0.72407 | 329 | 34224.6242 | 34224.6242
796 | 3071 | MORGAN HILL 210542348 | 0.72378 | 16 | 6767.0715 | 2297.9263
797 | 4334 | HIGGINS 11041006 | 0.71806 | 155 | 64324.0657 | 33324.4653
798 | 1751 | BUCKS CREEK 1101circuit_breaker | 0.71638 | 107 | 31149.9295 | 31149.9295
799 | 1211 | OAKHURST 11035480 | 0.71402 | 273 | 27507.5877 | 27507.5877
800 | 1610 | JESSUP 1101circuit_breaker | 0.71147 | 12 | 9377.0793 | 2330.0107
801 | 1867 | MOUNTAIN QUARRIES 21011184 | 0.7114 | 195 | 18954.6073 | 18770.5875
802 | 3498 | SAN RAFAEL 1108516 | 0.71062 | 169 | 17633.1443 | 17633.1443
803 | 66 | BROWNS VALLEY 110197188 | 0.70785 | 79 | 10687.565 | 10687.565
804 | 432 | HIGGINS 1110circuit_breaker | 0.70421 | 148 | 29132.7846 | 15857.3316
805 | 7539 | SONOMA 11033052 | 0.70408 | 129 | 26080.1016 | 21211.1693
806 | 2652 | OLETA 110163500 | 0.70315 | 29 | 12301.408 | 6425.1593
807 | 903 | RED BLUFF 11041630 | 0.70229 | 23 | 22734.8037 | 3396.4013
808 | 2368 | FROGTOWN 1702290609 | 0.69913 | 277 | 29095.2779 | 29095.2779
809 | 9108 | KANAKA 1101circuit_breaker | 0.69667 | 74 | 7526.6787 | 7526.6787
810 | 7830 | LOW GAP 110186816 | 0.69276 | 77 | 7103.5026 | 7103.5026
811 | 6109 | PLACERVILLE 2106935216 | 0.68972 | 268 | 33799.5586 | 33799.5586
812 | 2246 | PASO ROBLES 110355374 | 0.68967 | 13 | 17000.9166 | 3793.0347
813 | 1699 | TEMPLETON 2112R28 | 0.68918 | 18 | 39551.4346 | 3272.9638
814 | 3078 | WILLITS 11044650 | 0.6884 | 46 | 9494.7518 | 5679.3968
815 | 8880 | COARSEGOLD 21045516 | 0.6847 | 102 | 29689.925 | 29689.925
816 | 3022 | GEYSERVILLE 1102274 | 0.68286 | 57 | 30005.2502 | 7596.7493
817 | 5621 | APPLE HILL 110497086 | 0.67766 | 420 | 41232.2745 | 41232.2745
818 | 1846 | JESSUP 11019002 | 0.67709 | 109 | 24293.3556 | 12312.9538
819 | 5835 | SHINGLE SPRINGS 210981390 | 0.67607 | 251 | 30296.9721 | 30296.9721
820 | 8892 | DOBBINS 110191464 | 0.66921 | 94 | 11341.1652 | 11341.1652
821 | 3741 | APPLE HILL 110412832 | 0.66776 | 211 | 24725.6134 | 23528.5139
822 | 3615 | ALTO 11221212 | 0.66688 | 25 | 3797.0171 | 2589.3247
823 | 6771 | PINE GROVE 110235576 | 0.66654 | 116 | 12655.9114 | 12655.9114
824 | 4858 | BONNIE NOOK 1101circuit_breaker | 0.66546 | 234 | 23724.1813 | 23724.1813
825 | 4993 | SILVERADO 2104722 | 0.66491 | 37 | 11871.204 | 11871.204
826 | 1432 | GIRVAN 11029012 | 0.66427 | 159 | 25756.1785 | 25756.1785
827 | 7629 | BROWNS VALLEY 110136622 | 0.66343 | 35 | 13781.9233 | 6467.9583
828 | 2282 | COTTONWOOD 11011510 | 0.66143 | 3 | 5333.1807 | 494.2929
829 | 552 | GREENBRAE 11031260 | 0.66139 | 38 | 4352.5218 | 4080.5899
830 | 4588 | REDBUD 1101454 | 0.65628 | 50 | 8939.3598 | 8939.3598
831 | 4735 | DUNBAR 110179086 | 0.65343 | 99 | 11168.1456 | 10550.9054
832 | 3824 | LLAGAS 210740407 | 0.65143 | 60 | 10022.7174 | 6648.3182
833 | 3929 | CARLOTTA 1121circuit_breaker | 0.64987 | 35 | 37519.4983 | 3350.89
834 | 6713 | GOLDTREE 1105circuit_breaker | 0.6495 | 23 | 17789.9354 | 11071.7645
835 | 8923 | WILLOW CREEK 11033090 | 0.64873 | 147 | 16560.5655 | 16560.5655
836 | 6423 | POTTER VALLEY P H 110576498 | 0.64802 | 154 | 23931.4188 | 23931.4188
837 | 4507 | SAN LUIS OBISPO 1104V40 | 0.6446 | 82 | 37142.5765 | 22025.4599
838 | 2219 | SWIFT 2110XR366 | 0.64391 | 76 | 17763.6308 | 13196.8212
839 | 1882 | MOLINO 1104380 | 0.63424 | 30 | 45603.4304 | 4061.4593
840 | 3683 | ALTO 1125510 | 0.63256 | 87 | 11874.2275 | 11874.2275
841 | 997 | CORRAL 1103circuit_breaker | 0.63226 | 31 | 46165.5988 | 4196.3293
842 | 1717 | TEMPLETON 2111circuit_breaker | 0.62824 | 32 | 17899.6887 | 2988.8542
843 | 1346 | PINE GROVE 11021222 | 0.62601 | 241 | 27692.5615 | 27692.5615
844 | 2785 | MARTELL 11033152 | 0.61966 | 141 | 27364.6036 | 27174.8741
845 | 5197 | FORT SEWARD 11211663 | 0.6191 | 34 | 3125.6698 | 3125.6698
846 | 482 | TIVY VALLEY 1107circuit_breaker | 0.61822 | 55 | 68308.1954 | 19259.2253
847 | 6719 | WOODACRE 1101circuit_breaker | 0.61739 | 41 | 4553.3245 | 4013.0588
848 | 5286 | COTATI 1105634 | 0.61415 | 27 | 11162.845 | 11162.845
849 | 6036 | DUNBAR 1101416 | 0.61367 | 39 | 5219.9703 | 4032.4336
850 | 3997 | WYANDOTTE 11071510 | 0.6044 | 367 | 41028.1557 | 41028.1557
851 | 4734 | WOODSIDE 11018972 | 0.60385 | 105 | 9771.1957 | 9771.1957
852 | 9085 | WISHON 1101circuit_breaker | 0.60376 | 58 | 12397.8907 | 12397.8907
853 | 8418 | TEMPLETON 2110N30 | 0.60006 | 159 | 32940.3855 | 32940.3855
854 | 6804 | ANTLER 11011612 | 0.59914 | 93 | 14853.5972 | 14104.292
855 | 899 | WYANDOTTE 1105329930 | 0.59739 | 98 | 16828.9727 | 9878.9278
856 | 8885 | WILDWOOD 11011576 | 0.59736 | 116 | 13123.158 | 13123.158
857 | 4055 | WILLITS 1103538 | 0.59683 | 63 | 10337.071 | 10337.071
858 | 7679 | FORESTHILL 110175340 | 0.59533 | 88 | 8005.6151 | 8005.6151
859 | 6892 | PINE GROVE 110283098 | 0.5948 | 145 | 13034.6629 | 13034.6629
860 | 6140 | ORO FINO 11022040 | 0.59411 | 142 | 14724.8662 | 14724.8662
861 | 4687 | GRASS VALLEY 11031700 | 0.59243 | 296 | 34998.208 | 34777.5165
862 | 4409 | CALPELLA 1101circuit_breaker | 0.58788 | 116 | 32842.3149 | 17245.9403
863 | 2503 | BRUNSWICK 110651486 | 0.58486 | 947 | 91172.3296 | 91172.3296
864 | 5192 | FROGTOWN 17027108 | 0.58426 | 87 | 20569.8382 | 14176.7324
865 | 127 | APPLE HILL 1103circuit_breaker | 0.57849 | 464 | 107722.7084 | 94275.2086
866 | 2755 | PENRYN 11072410 | 0.57371 | 42 | 12099.1952 | 4627.9566
867 | 4601 | BRENTWOOD 2105B504R | 0.57211 | 25 | 18129.5072 | 12899.4497
868 | 578 | EL DORADO PH 21016852 | 0.56408 | 398 | 81053.6636 | 81053.6636
869 | 6975 | SANTA YNEZ 1101Y16 | 0.55943 | 45 | 23205.9514 | 12159.0407
870 | 1923 | CURTIS 170411290 | 0.55861 | 113 | 12662.0411 | 12662.0411
871 | 290 | MENDOCINO 110131322 | 0.55493 | 60 | 46258.8786 | 7456.8364
872 | 2053 | STELLING 111060094 | 0.55155 | 174 | 15898.3782 | 15898.3782
873 | 3023 | SHINGLE SPRINGS 210819622 | 0.54953 | 66 | 18790.9041 | 8713.308
874 | 4630 | OCEANO 1104Q12 | 0.54859 | 85 | 25898.4468 | 16245.9078
875 | 3506 | SANTA YNEZ 1101Y14 | 0.54749 | 11 | 26396.3962 | 7302.2086
876 | 8201 | PUTAH CREEK 110546162 | 0.54729 | 8 | 10784.3815 | 1002.572
877 | 6204 | MADISON 21011975 | 0.54719 | 2 | 3900.1165 | 127.6157
878 | 2781 | PANORAMA 11019092 | 0.54628 | 61 | 32236.0251 | 16503.8389
879 | 2199 | CURTIS 170247488 | 0.54593 | 220 | 33088.8899 | 29796.4907
880 | 8459 | MARIPOSA 2101circuit_breaker | 0.54574 | 36 | 4029.4321 | 4029.4321
881 | 3086 | CLEAR LAKE 1101486 | 0.54415 | 3 | 49197.9889 | 343.3545
882 | 26 | MENDOCINO 1101circuit_breaker | 0.54409 | 156 | 21845.6652 | 18680.8862
883 | 2229 | MIDDLETOWN 1102414 | 0.54106 | 14 | 18793.485 | 8076.5942
884 | 2548 | VOLTA 11021504 | 0.53742 | 138 | 13357.6434 | 13357.6434
885 | 1001 | EL DORADO PH 210119752 | 0.53689 | 546 | 61569.4579 | 61569.4579
886 | 8168 | BIG BASIN 110211062 | 0.53578 | 206 | 21172.9967 | 21172.9967
887 | 2384 | APPLE HILL 110413512 | 0.53023 | 419 | 49772.481 | 45529.6464
888 | 4033 | BRUNSWICK 11041020 | 0.53002 | 372 | 46114.191 | 46114.191
889 | 38 | REDBUD 1101708166 | 0.52582 | 70 | 32947.3958 | 13686.2588
890 | 8766 | SUNOL 11018721 | 0.52124 | 29 | 5007.3028 | 4212.4471
891 | 9535 | MIDDLETOWN 1103circuit_breaker | 0.51885 | 2 | 259.3908 | 85.2366
892 | 6478 | MAXWELL 11053008 | 0.51865 | 17 | 24475.225 | 5862.1498
893 | 1837 | TEMPLETON 2110R06 | 0.51773 | 58 | 41555.5333 | 8134.5668
894 | 128 | GEYSERVILLE 1102522 | 0.51054 | 95 | 33666.9876 | 23061.8182
895 | 4581 | DUNLAP 11027849F | 0.50774 | 92 | 13949.6344 | 13949.6344
896 | 21 | FITCH MOUNTAIN 1113154 | 0.50412 | 28 | 30573.1342 | 2751.1631
897 | 5903 | PETALUMA C 1108618 | 0.50087 | 4 | 17463.5088 | 13883.0282
898 | 627 | LAYTONVILLE 1101circuit_breaker | 0.50016 | 87 | 14777.2299 | 9592.9795
899 | 9027 | WILDWOOD 110198896 | 0.49702 | 39 | 15545.2226 | 15545.2226
900 | 5255 | FITCH MOUNTAIN 1113406 | 0.4966 | 39 | 15193.9016 | 3309.8931
901 | 3908 | COARSEGOLD 21025380 | 0.49551 | 188 | 22745.3926 | 22745.3926
902 | 4365 | WEST POINT 1101circuit_breaker | 0.49477 | 55 | 7549.0145 | 7549.0145
903 | 5251 | ALLEGHANY 1101804 | 0.49281 | 275 | 34767.038 | 34767.038
904 | 3747 | SAND CREEK 11037070 | 0.49271 | 125 | 28595.1882 | 28595.1882
905 | 1959 | SILVERADO 2103circuit_breaker | 0.48977 | 137 | 53273.3948 | 18626.4797
906 | 2615 | CAMP EVERS 210660124 | 0.48952 | 382 | 72474.4832 | 72474.4832
907 | 2744 | PINE GROVE 11013170 | 0.48865 | 589 | 64707.4468 | 64707.4468
908 | 4631 | COARSEGOLD 2102circuit_breaker | 0.48667 | 84 | 22592.2597 | 22592.2597
909 | 3424 | CLAYTON 2215circuit_breaker | 0.48593 | 7 | 17643.4387 | 3378.3697
910 | 7765 | DUNBAR 1102861496 | 0.48571 | 71 | 7248.9399 | 7248.9399
911 | 8114 | ANNAPOLIS 1101608 | 0.48487 | 97 | 28636.0357 | 28636.0357
912 | 1994 | V56 | 0.48304 | 93 | 15908.7859 | 14519.9082
913 | 2256 | VINEYARD 2107circuit_breaker | 0.48301 | 34 | 16402.2958 | 4200.246
914 | 1381 | ATASCADERO 1103A16 | 0.48294 | 199 | 31675.1523 | 28337.886
915 | 2020 | SHINGLE SPRINGS 210911092 | 0.48185 | 325 | 36166.6657 | 36166.6657
916 | 1879 | OLEMA 1101416 | 0.48038 | 158 | 26064.3398 | 25936.9304
917 | 8993 | VOLTA 110149742 | 0.47572 | 2 | 5593.8568 | 5593.8568
918 | 256 | BRUNSWICK 11067099 | 0.47272 | 108 | 12185.6359 | 12185.6359
919 | 161 | CHALLENGE 110198174 | 0.47006 | 286 | 31495.8005 | 31495.8005
920 | 3521 | OCEANO 1104V38 | 0.46929 | 119 | 27980.8002 | 18252.5164
921 | 8265 | MIDDLETOWN 1101614 | 0.46709 | 25 | 2239.5087 | 2239.5087
922 | 5451 | MOUNTAIN QUARRIES 21012422 | 0.46341 | 122 | 13951.5772 | 13951.5772
923 | 5006 | VACAVILLE 110941782 | 0.46241 | 6 | 2742.127 | 1089.8371
924 | 365 | CURTIS 1701circuit_breaker | 0.46227 | 103 | 19970.3298 | 13323.4289
925 | 700 | SILVERADO 21051306 | 0.46168 | 42 | 12596.1937 | 4731.2419
926 | 2338 | SAN LUIS OBISPO 1103circuit_breaker | 0.45971 | 18 | 22526.7494 | 4883.612
927 | 7552 | RINCON 1103568 | 0.45803 | 183 | 20662.4363 | 20662.4363
928 | 5193 | SUNOL 1101MR169 | 0.45435 | 14 | 14971.4355 | 4614.9374
929 | 2395 | KONOCTI 1102532 | 0.45268 | 96 | 15232.9913 | 15232.9913
930 | 4566 | WISE 1101circuit_breaker | 0.4472 | 57 | 14425.555 | 6518.1918
931 | 7359 | WEST POINT 11021369 | 0.44494 | 59 | 17175.8338 | 15950.4182
932 | 2066 | LINCOLN 11045391 | 0.44216 | 5 | 1530.1829 | 1530.1829
933 | 8242 | NOTRE DAME 11042408 | 0.44151 | 82 | 22043.6191 | 18145.7739
934 | 4870 | ALTO 11243121 | 0.44106 | 36 | 4421.122 | 4421.122
935 | 1316 | AUBERRY 1101R2838 | 0.4377 | 165 | 32678.392 | 32678.392
936 | 6929 | LAKEVILLE 11023341 | 0.43614 | 52 | 20071.3044 | 11684.2399
937 | 1949 | SAN MIGUEL 1105circuit_breaker | 0.43559 | 5 | 16697.3527 | 2410.7396
938 | 6921 | FORESTHILL 11011820 | 0.43218 | 76 | 8970.0583 | 8970.0583
939 | 8343 | WILLOW CREEK 11013050 | 0.43008 | 37 | 4461.1677 | 4461.1677
940 | 6757 | FRUITLAND 11426054 | 0.42997 | 36 | 16837.555 | 16837.555
941 | 3964 | WHITMORE 1101circuit_breaker | 0.42258 | 88 | 9527.4078 | 9527.4078
942 | 5422 | NARROWS 21052426 | 0.42154 | 135 | 27928.6656 | 12992.6156
943 | 6696 | ORO FINO 110238698 | 0.42033 | 273 | 25102.3894 | 25102.3894
944 | 8783 | CALAVERAS CEMENT 1101585 | 0.42004 | 128 | 22710.6586 | 22710.6586
945 | 5208 | PLACERVILLE 210611132 | 0.41986 | 544 | 69399.8401 | 69399.8401
946 | 6027 | WILLITS 1103964 | 0.41889 | 26 | 8651.6925 | 4036.5135
947 | 9487 | PIT NO 5 11011618 | 0.41889 | 49 | 9746.1598 | 9746.1598
948 | 4023 | VACAVILLE 1104circuit_breaker | 0.41706 | 16 | 4995.2075 | 1499.3098
949 | 4753 | PUEBLO 21031970 | 0.41542 | 48 | 13574.3858 | 5037.9118
950 | 4719 | BRUNSWICK 11052130 | 0.41327 | 196 | 23157.9038 | 23157.9038
951 | 5206 | MONTICELLO 110137384 | 0.41259 | 43 | 15055.0544 | 15055.0544
952 | 9280 | PANORAMA 11021632 | 0.41176 | 13 | 13751.6318 | 13751.6318
953 | 1850 | SHINGLE SPRINGS 211051800 | 0.41086 | 133 | 15648.3843 | 14770.4871
954 | 6521 | KESWICK 11011590 | 0.40915 | 37 | 10135.4927 | 10135.4927
955 | 4806 | BEAR VALLEY 210190550 | 0.40805 | 58 | 12881.7348 | 12881.7348
956 | 7336 | FROGTOWN 17027134 | 0.40683 | 103 | 36552.2416 | 28875.1403
957 | 8139 | MOLINO 11026917 | 0.40192 | 99 | 11483.727 | 11483.727
958 | 6331 | LLAGAS 2107XR188 | 0.39946 | 12 | 9907.5767 | 2228.2099
959 | 2533 | VACA DIXON 11059792 | 0.39784 | 2 | 46444.676 | 1598.1228
960 | 570 | POINT ARENA 1101circuit_breaker | 0.39755 | 108 | 18269.3482 | 18269.3482
961 | 5051 | BANGOR 11011806 | 0.39668 | 105 | 14483.9765 | 13609.8138
962 | 5939 | PEORIA 170190090 | 0.39534 | 199 | 48288.5394 | 46519.9218
963 | 3103 | BRUNSWICK 11062416 | 0.39379 | 447 | 49911.7707 | 45937.2563
964 | 7614 | MARIPOSA 2102circuit_breaker | 0.39332 | 48 | 8571.1084 | 8453.5074
965 | 3891 | MIDDLETOWN 1102878 | 0.39264 | 17 | 9248.9027 | 2592.1013
966 | 74 | ALTO 1124428 | 0.38649 | 60 | 9441.0665 | 6700.9234
967 | 3099 | MARTELL 110368192 | 0.3836 | 23 | 10120.6731 | 3980.4628
968 | 4990 | LOS GATOS 1106LB48 | 0.38252 | 239 | 23832.8123 | 23832.8123
969 | 7750 | CLARKSVILLE 2109circuit_breaker | 0.37879 | 4 | 1811.3753 | 1633.6693
970 | 6902 | ATASCADERO 1103A14 | 0.37741 | 218 | 40416.4237 | 40416.4237
971 | 1566 | MENLO 1102W80 | 0.37701 | 176 | 30438.0826 | 29528.8058
972 | 244 | RINCON 1103circuit_breaker | 0.37497 | 25 | 5989.4697 | 3908.5393
973 | 8575 | MIDDLETOWN 11011314 | 0.3733 | 14 | 1494.2319 | 1494.2319
974 | 457 | MOLINO 110251788 | 0.37168 | 87 | 23550.5125 | 9018.9359
975 | 2461 | EL DORADO PH 2101circuit_breaker | 0.36934 | 254 | 26755.9987 | 26755.9987
976 | 944 | MIDDLETOWN 1102514 | 0.36842 | 32 | 8514.884 | 5004.0934
977 | 5363 | WEST POINT 11021305 | 0.36763 | 59 | 18286.9662 | 18286.9662
978 | 4145 | DIAMOND SPRINGS 110676088 | 0.36612 | 175 | 17715.9929 | 17715.9929
979 | 1385 | SONOMA 1107126 | 0.36461 | 18 | 35906.1491 | 6523.4267
980 | 6733 | CALISTOGA 1101circuit_breaker | 0.36424 | 27 | 15415.3431 | 3212.9518
981 | 3145 | COTATI 110361736 | 0.363 | 52 | 26748.6696 | 18397.7495
982 | 8888 | PEABODY 2108circuit_breaker | 0.35909 | 4 | 4968.214 | 604.4135
983 | 4514 | OLETA 110241396 | 0.35878 | 79 | 23728.3159 | 21843.0978
984 | 6670 | CLOVERDALE 1102670 | 0.3577 | 26 | 9645.5215 | 4063.4864
985 | 7776 | VINEYARD 2110circuit_breaker | 0.35687 | 21 | 17792.5531 | 8669.9033
986 | 4609 | FRUITLAND 11418860 | 0.35573 | 24 | 6108.7785 | 3211.911
987 | 3972 | CLAYTON 2213circuit_breaker | 0.352 | 26 | 9977.7681 | 6236.8648
988 | 7100 | SAN RAMON 210853732 | 0.34857 | 89 | 12570.9742 | 12570.9742
989 | 6095 | WEST POINT 11021303 | 0.34713 | 56 | 25499.4036 | 25499.4036
990 | 3660 | MONTE RIO 11131137 | 0.34365 | 46 | 4563.9223 | 4563.9223
991 | 4941 | DUNBAR 110147964 | 0.34312 | 65 | 12211.6017 | 10130.7271
992 | 4076 | PASO ROBLES 1104R12 | 0.34206 | 207 | 64641.2434 | 42365.8362
993 | 637 | ORO FINO 11022090 | 0.34135 | 198 | 23596.9335 | 23596.9335
994 | 6831 | BIG BEND 1101circuit_breaker | 0.34069 | 254 | 35800.1144 | 35800.1144
995 | 5633 | OAKHURST 11035732 | 0.33912 | 39 | 5570.0761 | 5570.0761
996 | 7335 | DUNBAR 11014817 | 0.33905 | 41 | 4994.4292 | 4994.4292
997 | 6406 | UKIAH 11143606 | 0.33787 | 99 | 26641.1454 | 16376.8546
998 | 2222 | BELL 1108circuit_breaker | 0.33725 | 64 | 20105.7391 | 6935.3327
999 | 6650 | OLETA 110151740 | 0.33591 | 83 | 33990.1368 | 20448.965
1000 | 2817 | MONTE RIO 1113346 | 0.33548 | 132 | 16237.5238 | 16237.5238
1001 | 4469 | LOGAN CREEK 21022226 | 0.33546 | 6 | 56162.3689 | 5964.9276
1002 | 4817 | EL DORADO PH 210119612 | 0.33111 | 123 | 14689.1645 | 14689.1645
1003 | 7139 | ALTO 11243745 | 0.32825 | 58 | 7368.4316 | 7368.4316
1004 | 1156 | ORO FINO 1101circuit_breaker | 0.32811 | 378 | 39834.6591 | 39834.6591
1005 | 783 | DUNBAR 1101circuit_breaker | 0.32736 | 45 | 23582.0206 | 3778.218
1006 | 7740 | ZACA 1101circuit_breaker | 0.32604 | 29 | 17338.0564 | 11111.2282
1007 | 5536 | VOLTA 11029742 | 0.3253 | 135 | 14622.5954 | 14622.5954
1008 | 345 | PUEBLO 2102656 | 0.32525 | 9 | 27867.5616 | 592.9592
1009 | 1092 | PEORIA 17056697 | 0.32247 | 61 | 6657.3541 | 6657.3541
1010 | 1813 | MILPITAS 1109XR082 | 0.31906 | 133 | 32625.1795 | 30817.3767
1011 | 3803 | PEORIA 170510580 | 0.31862 | 66 | 18856.5854 | 11664.5509
1012 | 281 | PERRY 1101V78 | 0.31858 | 140 | 47298.9569 | 47298.9569
1013 | 8723 | WILLOW CREEK 1102circuit_breaker | 0.3183 | 101 | 11718.7349 | 11718.7349
1014 | 2722 | FORESTHILL 1101circuit_breaker | 0.31598 | 143 | 14707.8472 | 14707.8472
1015 | 7027 | TIVY VALLEY 11077380 | 0.31585 | 18 | 45102.1031 | 18290.2186
1016 | 715 | APPLE HILL 210212025 | 0.31448 | 149 | 14681.1435 | 14681.1435
1017 | 8930 | BEAR VALLEY 21054170 | 0.31398 | 36 | 15319.6375 | 15319.6375
1018 | 3347 | COTATI 1105616 | 0.31337 | 10 | 49321.001 | 2435.445
1019 | 6475 | HORSESHOE 11011682 | 0.31189 | 9 | 15688.8599 | 944.4917
1020 | 2009 | LINCOLN 11042072 | 0.31165 | 5 | 27455.4475 | 512.0053
1021 | 9107 | CALISTOGA 110135588 | 0.31037 | 14 | 4848.4058 | 4848.4058
1022 | 2486 | PHILO 1102920 | 0.31026 | 229 | 41958.9354 | 26207.5142
1023 | 9386 | CLARK ROAD 1102circuit_breaker | 0.30919 | 3 | 2454.6663 | 1038.6996
1024 | 413 | ARCATA 11225384 | 0.30908 | 277 | 28119.8007 | 24769.8423
1025 | 6664 | WILLOW CREEK 11037514 | 0.30868 | 119 | 16087.5864 | 13903.8607
1026 | 3883 | CAMP EVERS 210510214 | 0.30842 | 250 | 22399.2356 | 22399.2356
1027 | 7812 | MORGAN HILL 2105XR268 | 0.30662 | 113 | 12821.0297 | 12821.0297
1028 | 7324 | SILVERADO 2102808 | 0.30549 | 15 | 7848.6714 | 1683.2795
1029 | 5393 | BUELLTON 1101Y36 | 0.30479 | 202 | 72977.0065 | 59828.4788
1030 | 218 | DUNBAR 1102circuit_breaker | 0.30404 | 110 | 13793.3359 | 11754.0323
1031 | 2636 | SAN RAMON 2107MR284 | 0.30384 | 108 | 24164.9 | 23158.7135
1032 | 1060 | BIG MEADOWS 21012260 | 0.30293 | 196 | 36189.8598 | 22959.7746
1033 | 9191 | TASSAJARA 21126392 | 0.30271 | 42 | 8416.1442 | 8416.1442
1034 | 2182 | COTATI 1103148 | 0.30253 | 79 | 49905.0802 | 47981.5325
1035 | 9488 | CLARKSVILLE 2105circuit_breaker | 0.30213 | 2 | 1912.7297 | 759.3509
1036 | 5549 | MONTICELLO 110165454 | 0.30184 | 8 | 3019.3036 | 1332.2655
1037 | 47 | MARIPOSA 210135244 | 0.30172 | 202 | 27730.4872 | 27730.4872
1038 | 3035 | ATASCADERO 1103circuit_breaker | 0.30109 | 65 | 15502.9137 | 11975.6869
1039 | 3928 | MOLINO 11015042 | 0.30085 | 96 | 11223.364 | 9764.6994
1040 | 3408 | CURTIS 17026008 | 0.30077 | 230 | 28195.182 | 28195.182
1041 | 1239 | TEMPLETON 2113circuit_breaker | 0.30009 | 2 | 41923.3786 | 879.0751
1042 | 2538 | HARTLEY 110186876 | 0.29966 | 33 | 13541.1985 | 3441.3803
1043 | 1016 | FRUITLAND 1142circuit_breaker | 0.29881 | 27 | 24720.3786 | 16901.355
1044 | 857 | FULTON 110777670 | 0.29854 | 92 | 11040.0737 | 10408.8422
1045 | 7698 | CAYETANO 2109MR186 | 0.2959 | 2 | 4135.7533 | 547.3474
1046 | 1143 | BEAR VALLEY 21059560 | 0.29442 | 417 | 58396.3744 | 58396.3744
1047 | 1065 | CLARK ROAD 11022044 | 0.29419 | 41 | 20142.1338 | 13144.9091
1048 | 850 | PEORIA 170459596 | 0.29247 | 106 | 57857.723 | 32203.8416
1049 | 285 | MORGAN HILL 2110XR326 | 0.29243 | 20 | 33599.9303 | 3216.8739
1050 | 7575 | OCEANO 1106circuit_breaker | 0.29134 | 12 | 8076.9737 | 1811.9234
1051 | 7247 | WYANDOTTE 110213044 | 0.28926 | 57 | 9510.113 | 6256.4266
1052 | 8669 | LAKEVILLE 110287432 | 0.28885 | 57 | 22038.8573 | 15489.4062
1053 | 4699 | ELECTRA 11017104 | 0.28856 | 202 | 19862.8394 | 19862.8394
1054 | 1910 | SILVERADO 210298998 | 0.28731 | 15 | 45845.8745 | 4139.5096
1055 | 2234 | ORO FINO 11022560 | 0.28627 | 277 | 26913.6157 | 26913.6157
1056 | 2046 | ALTO 11201214 | 0.28374 | 54 | 7258.7621 | 5446.0036
1057 | 7173 | LAYTONVILLE 110189606 | 0.28372 | 106 | 19260.766 | 18642.295
1058 | 5635 | HOPLAND 11011100 | 0.2836 | 51 | 10708.6266 | 4021.7261
1059 | 3235 | BIG BEND 1101180398 | 0.28269 | 79 | 9616.0055 | 9616.0055
1060 | 727 | COTATI 1105circuit_breaker | 0.28211 | 29 | 4287.6063 | 4287.6063
1061 | 4371 | CALPELLA 1102496 | 0.28171 | 39 | 27009.544 | 5425.0881
1062 | 2791 | CAMP EVERS 210510294 | 0.2803 | 125 | 13600.6961 | 13600.6961
1063 | 1663 | BUCKS CREEK 1103338520 | 0.27946 | 127 | 12890.8329 | 12303.5892
1064 | 1986 | WOODACRE 11021280 | 0.27886 | 124 | 13839.6437 | 13606.7096
1065 | 3302 | GEYSERVILLE 1101circuit_breaker | 0.27838 | 13 | 13273.8152 | 1595.2814
1066 | 9682 | PEABODY 21065500 | 0.27703 | 6 | 2454.3356 | 589.7469
1067 | 1206 | RED BLUFF 1103circuit_breaker | 0.27693 | 3 | 31613.5881 | 126.6017
1068 | 9707 | GEYSERVILLE 1102756 | 0.27675 | 8 | 948.4078 | 948.4078
1069 | 5073 | HOOPA 110182542 | 0.27624 | 179 | 24434.1618 | 18590.2459
1070 | 8449 | HARTLEY 1102524 | 0.27561 | 8 | 7246.3624 | 2350.321
1071 | 4695 | SANTA ROSA A 1104642 | 0.27435 | 186 | 21539.3089 | 21539.3089
1072 | 4260 | MARIPOSA 21018030 | 0.27302 | 225 | 30213.4552 | 30213.4552
1073 | 6685 | KONOCTI 110264464 | 0.27201 | 35 | 4327.7045 | 3132.1045
1074 | 2888 | DIAMOND SPRINGS 1103circuit_breaker | 0.27111 | 509 | 82294.0421 | 52640.7509
1075 | 6981 | CORRAL 110213498 | 0.271 | 13 | 1603.6406 | 1585.9579
1076 | 4501 | BRUNSWICK 11052210 | 0.27011 | 345 | 36677.2724 | 36677.2724
1077 | 9379 | TEMPLETON 21132949 | 0.2701 | 5 | 766.5719 | 766.5719
1078 | 2473 | CLAY 110334338 | 0.26981 | 54 | 16836.8272 | 14279.384
1079 | 7780 | DUNBAR 1102528 | 0.26856 | 49 | 6520.0631 | 5365.7106
1080 | 5825 | RINCON 1103198 | 0.26772 | 71 | 10388.1795 | 10388.1795
1081 | 6208 | SALMON CREEK 110137368 | 0.26739 | 21 | 10726.7893 | 10726.7893
1082 | 286 | BIG BASIN 110169550 | 0.26467 | 312 | 28833.0726 | 28833.0726
1083 | 2336 | GUALALA 11121294 | 0.26352 | 335 | 32449.4042 | 31035.4817
1084 | 8727 | SAN MIGUEL 1106N34 | 0.26198 | 6 | 22008.9702 | 3289.5998
1085 | 5336 | MARIPOSA 2102241564 | 0.2611 | 7 | 1779.8257 | 874.7258
1086 | 7662 | COARSEGOLD 210210330 | 0.25952 | 149 | 15524.0665 | 15524.0665
1087 | 5112 | MIWUK 17026018 | 0.25816 | 260 | 31416.8747 | 31416.8747
1088 | 2401 | VOLTA 110180454 | 0.25694 | 14 | 51726.8369 | 50010.0284
1089 | 2069 | MIRABEL 110238514 | 0.25586 | 161 | 17032.4383 | 17032.4383
1090 | 8325 | GARBERVILLE 11028189 | 0.25477 | 16 | 1628.0781 | 1628.0781
1091 | 582 | BRUNSWICK 11021010 | 0.25474 | 716 | 70806.9227 | 70806.9227
1092 | 2433 | COLUMBIA HILL 110135424 | 0.25352 | 222 | 22222.0885 | 22222.0885
1093 | 2263 | CLEAR LAKE 1102circuit_breaker | 0.25352 | 12 | 36164.5483 | 1141.6054
1094 | 280 | SAN RAFAEL 1104802 | 0.25278 | 110 | 20343.1915 | 12060.44
1095 | 4730 | NARROWS 210276952 | 0.25262 | 33 | 18031.5566 | 3554.8483
1096 | 4253 | OREGON TRAIL 11021584 | 0.25106 | 180 | 20999.2286 | 20999.2286
1097 | 2432 | SANTA ROSA A 1104220 | 0.24998 | 90 | 30711.1102 | 30711.1102
1098 | 1596 | CLAY 11037124 | 0.24991 | 70 | 51668.2469 | 15711.1032
1099 | 8334 | FORESTHILL 110137238 | 0.2496 | 147 | 18519.0658 | 18519.0658
1100 | 3944 | FROGTOWN 170291134 | 0.24784 | 144 | 25769.8346 | 22498.6303
1101 | 4337 | CLARK ROAD 11022094 | 0.24692 | 19 | 5527.8648 | 5527.8648
1102 | 1058 | MC ARTHUR 11011492 | 0.24576 | 83 | 49518.5791 | 15180.4428
1103 | 3769 | UKIAH 111129452 | 0.24252 | 17 | 20265.329 | 5841.787
1104 | 4777 | RACETRACK 17039190 | 0.24229 | 126 | 14436.1267 | 14436.1267
1105 | 8245 | KERCKHOFF 1101R308 | 0.24214 | 25 | 6217.3701 | 6217.3701
1106 | 8014 | PIT NO 3 21011482 | 0.242 | 83 | 19365.2645 | 19365.2645
1107 | 9044 | 171410 | 0.24049 | 24 | 7764.5032 | 2859.7024
1108 | 8821 | FORESTHILL 1102circuit_breaker | 0.2398 | 21 | 2652.1639 | 2652.1639
1109 | 4787 | PINE GROVE 1102circuit_breaker | 0.23946 | 167 | 17217.3979 | 17217.3979
1110 | 3263 | VOLTA 110297816 | 0.23853 | 77 | 8457.2763 | 8457.2763
1111 | 7409 | HALF MOON BAY 11012500 | 0.23852 | 94 | 11167.0911 | 9460.9126
1112 | 7639 | MONTE RIO 1112120 | 0.23827 | 119 | 11062.7422 | 11062.7422
1113 | 714 | DIAMOND SPRINGS 110650324 | 0.23793 | 255 | 32529.5546 | 27285.9774
1114 | 5246 | CORNING 110187304 | 0.23607 | 12 | 23676.389 | 3402.7975
1115 | 4416 | LOS GATOS 110760118 | 0.23465 | 435 | 42371.3391 | 42371.3391
1116 | 3526 | BIG BASIN 110212992 | 0.23393 | 238 | 22897.5855 | 22897.5855
1117 | 8082 | SAN LUIS OBISPO 1104350030 | 0.2339 | 20 | 14694.3466 | 8366.5404
1118 | 7927 | PEORIA 1705999 | 0.23114 | 37 | 3715.0604 | 3715.0604
1119 | 2713 | AUBERRY 1101R2845 | 0.23003 | 227 | 28634.7335 | 28634.7335
1120 | 2794 | SAN LUIS OBISPO 1101circuit_breaker | 0.22971 | 36 | 10872.4454 | 5333.7243
1121 | 6862 | DIAMOND SPRINGS 11042093 | 0.22907 | 99 | 14031.1709 | 12960.3084
1122 | 3987 | MARTELL 1101circuit_breaker | 0.22898 | 51 | 21373.1568 | 8464.9135
1123 | 3185 | PLACERVILLE 111219712 | 0.22836 | 199 | 20954.5206 | 20689.2133
1124 | 3043 | NOTRE DAME 11042028 | 0.22824 | 151 | 17363.4694 | 17363.4694
1125 | 3152 | HALF MOON BAY 1103H82 | 0.22751 | 300 | 58188.2631 | 49003.1871
1126 | 335 | WOODACRE 1101404 | 0.22463 | 191 | 19975.081 | 19975.081
1127 | 2978 | BIG BASIN 110110296 | 0.22408 | 216 | 23203.6203 | 23203.6203
1128 | 976 | BUTTE 1105134600 | 0.22403 | 334 | 49696.2582 | 44940.5828
1129 | 108 | EL DORADO PH 2102circuit_breaker | 0.2237 | 306 | 32849.8127 | 32849.8127
1130 | 8205 | ELK CREEK 110193504 | 0.22351 | 2 | 4035.0912 | 3298.9383
1131 | 4455 | WEST POINT 11021341 | 0.22336 | 110 | 16262.9038 | 16262.9038
1132 | 5012 | CALAVERAS CEMENT 1101502 | 0.22332 | 392 | 66199.832 | 60118.0927
1133 | 276 | GEYSERVILLE 1101122 | 0.22246 | 35 | 30286.4801 | 7052.0878
1134 | 1390 | CURTIS 17048140 | 0.22079 | 350 | 84947.7125 | 84947.7125
1135 | 5056 | BELLEVUE 2103648 | 0.22065 | 47 | 26113.2457 | 5275.9485
1136 | 1084 | HOOPA 1101circuit_breaker | 0.22054 | 242 | 43677.3103 | 23835.3937
1137 | 1121 | BELL 1109circuit_breaker | 0.21999 | 202 | 27671.9197 | 22001.4253
1138 | 5292 | VACAVILLE 110847860 | 0.21922 | 6 | 6327.6617 | 451.5656
1139 | 1401 | ANTLER 11011520 | 0.21896 | 102 | 14269.0206 | 14269.0206
1140 | 3373 | LOS GATOS 110760114 | 0.21807 | 281 | 39175.9013 | 39175.9013
1141 | 7384 | FRUITLAND 11422006 | 0.21784 | 13 | 14130.0867 | 12367.8837
1142 | 1459 | CURTIS 1702circuit_breaker | 0.21689 | 310 | 36730.9251 | 35160.9523
1143 | 7389 | GANSNER 11012424 | 0.21656 | 280 | 30415.1727 | 30151.5298
1144 | 1730 | VINEYARD 2108MR172 | 0.21548 | 72 | 14260.3612 | 8979.3146
1145 | 5449 | MORGAN HILL 2111XR186 | 0.21547 | 8 | 25686.8585 | 2744.6855
1146 | 784 | HIGGINS 1107circuit_breaker | 0.2154 | 81 | 30542.9222 | 8142.9425
1147 | 6311 | ARBUCKLE 110447282 | 0.21469 | 7 | 19082.1088 | 3612.2461
1148 | 7124 | PUTAH CREEK 11058812 | 0.21253 | 5 | 103854.6628 | 1876.8402
1149 | 4628 | WYANDOTTE 1107circuit_breaker | 0.20999 | 20 | 24344.0332 | 1641.1081
1150 | 2127 | MC KEE 1111711900 | 0.2091 | 66 | 20149.4052 | 14114.2959
1151 | 6446 | SAN LUIS OBISPO 110788962 | 0.20809 | 15 | 6411.4652 | 3512.4168
1152 | 3842 | AUBERRY 1101R319 | 0.20759 | 249 | 33658.5688 | 33658.5688
1153 | 6947 | ARCATA 11211206 | 0.20728 | 115 | 25263.8878 | 11057.5552
1154 | 7501 | PIT NO 7 1101circuit_breaker | 0.20679 | 28 | 4357.8457 | 4357.8457
1155 | 669 | CAMP EVERS 210612760 | 0.2038 | 442 | 42950.8829 | 42934.8809
1156 | 8293 | WYANDOTTE 1105circuit_breaker | 0.20146 | 51 | 21689.0277 | 15173.6855
1157 | 1713 | MIWUK 1701circuit_breaker | 0.20132 | 271 | 28710.6531 | 28710.6531
1158 | 2092 | FROGTOWN 17011623 | 0.199 | 224 | 24542.3809 | 24542.3809
1159 | 6550 | DUNBAR 11033127 | 0.19799 | 59 | 15768.1584 | 14668.3464
1160 | 4292 | MC ARTHUR 110138998 | 0.19773 | 23 | 26238.7768 | 15389.4778
1161 | 7235 | CLOVERDALE 1102262 | 0.19731 | 11 | 9248.1499 | 947.9156
1162 | 9511 | TIGER CREEK 0201circuit_breaker | 0.19705 | 23 | 6272.7997 | 6272.7997
1163 | 5042 | EL DORADO PH 210163464 | 0.19665 | 97 | 21978.0825 | 21978.0825
1164 | 2933 | HICKS 2101XR548 | 0.1966 | 9 | 13934.1431 | 1925.3259
1165 | 3097 | SALMON CREEK 1101194 | 0.19646 | 26 | 13583.0049 | 7700.4518
1166 | 4265 | WOODSIDE 11011922 | 0.19646 | 76 | 7665.9565 | 7077.1681
1167 | 9421 | ALLEGHANY 1101808 | 0.19639 | 73 | 9882.4147 | 9882.4147
1168 | 7155 | FRUITLAND 114263170 | 0.19563 | 21 | 21723.3744 | 19693.2907
1169 | 2232 | BUTTE 11051243 | 0.19546 | 92 | 8294.0568 | 8294.0568
1170 | 2031 | OLETA 11021228 | 0.19528 | 77 | 69198.1694 | 12585.9936
1171 | 5394 | CURTIS 17029220 | 0.19485 | 133 | 17957.7628 | 17305.2505
1172 | 5525 | HALF MOON BAY 1101circuit_breaker | 0.19452 | 92 | 22337.572 | 12179.0697
1173 | 3329 | PINE GROVE 110213438 | 0.19393 | 241 | 26763.0781 | 26763.0781
1174 | 8158 | MENLO 11037902 | 0.19267 | 133 | 26240.481 | 18489.6466
1175 | 2372 | MARIPOSA 210190180 | 0.19218 | 46 | 7283.0829 | 7283.0829
1176 | 7844 | COTATI 110387402 | 0.19198 | 68 | 18214.2492 | 18214.2492
1177 | 2546 | PARADISE 1104circuit_breaker | 0.18935 | 124 | 59028.3032 | 47006.8323
1178 | 1114 | LOS GATOS 1106LB44 | 0.18913 | 287 | 30802.2438 | 30802.2438
1179 | 8700 | VOLTA 110165764 | 0.18905 | 3 | 16669.3981 | 16669.3981
1180 | 4624 | ALLEGHANY 1101circuit_breaker | 0.18769 | 73 | 6967.0605 | 6967.0605
1181 | 3958 | CALAVERAS CEMENT 110113424 | 0.18686 | 12 | 5801.6622 | 2488.4546
1182 | 711 | BIG BASIN 110296986 | 0.18639 | 104 | 9463.8689 | 9463.8689
1183 | 2640 | BEAR VALLEY 210110000 | 0.18632 | 189 | 53605.23 | 47046.2975
1184 | 6168 | MADISON 210137082 | 0.18622 | 7 | 29594.5517 | 1451.8754
1185 | 8624 | SAN RAFAEL 11081250 | 0.18514 | 41 | 5757.8877 | 5757.8877
1186 | 949 | DUNBAR 1102903030 | 0.18483 | 24 | 2345.7829 | 2345.7829
1187 | 5804 | COARSEGOLD 210210050 | 0.18258 | 99 | 11531.9078 | 11531.9078
1188 | 9603 | RIO DELL 110275970 | 0.18257 | 74 | 11373.8899 | 11373.8899
1189 | 2243 | BEAR VALLEY 210521160 | 0.18207 | 249 | 38250.3476 | 38250.3476
1190 | 882 | COTATI 11055156 | 0.18187 | 40 | 16005.1118 | 7460.4725
1191 | 9157 | DUNBAR 1101343 | 0.18167 | 67 | 7181.969 | 7034.2123
1192 | 7367 | MIWUK 17018050 | 0.18132 | 179 | 19483.5578 | 19483.5578
1193 | 6787 | SYCAMORE CREEK 11112268 | 0.17973 | 374 | 35773.7446 | 35773.7446
1194 | 6048 | DRUM 11011602 | 0.17932 | 207 | 26765.8492 | 26765.8492
1195 | 7683 | SANTA ROSA A 1104716 | 0.17721 | 128 | 14273.5878 | 14273.5878
1196 | 9082 | RINCON 11035152 | 0.17695 | 26 | 2561.9657 | 2561.9657
1197 | 1531 | WILLOW CREEK 11015002 | 0.1761 | 194 | 22363.0953 | 21536.2249
1198 | 6297 | SISQUOC 1103M14 | 0.17495 | 204 | 52362.2316 | 32732.59
1199 | 2076 | WYANDOTTE 11091040 | 0.17443 | 13 | 9730.261 | 1355.0481
1200 | 4541 | WEST POINT 110112256 | 0.17443 | 26 | 10485.7942 | 10485.7942
1201 | 1870 | SONOMA 1105404 | 0.17367 | 9 | 28928.7411 | 18092.5178
1202 | 2761 | PASO ROBLES 1104P02 | 0.17241 | 1 | 11384.6152 | 389.1275
1203 | 4389 | SILVERADO 2104circuit_breaker | 0.17237 | 31 | 8010.0912 | 2560.2139
1204 | 3702 | SAN LUIS OBISPO 1101V12 | 0.17217 | 154 | 33846.6296 | 33846.6296
1205 | 2714 | BURNEY 11021358 | 0.1719 | 69 | 14868.5059 | 12955.3272
1206 | 198 | RESERVATION ROAD 1101circuit_breaker | 0.17175 | 56 | 15082.891 | 7957.2831
1207 | 6214 | PAUL SWEET 21068091 | 0.17146 | 96 | 9677.9322 | 9677.9322
1208 | 371 | FROGTOWN 1702L5407 | 0.17089 | 179 | 29150.3712 | 29150.3712
1209 | 1559 | MARTELL 110111244 | 0.17084 | 290 | 35268.1557 | 33683.9339
1210 | 8869 | OLETA 1101circuit_breaker | 0.17051 | 20 | 5393.0771 | 5372.4907
1211 | 423 | TEJON 11023751 | 0.17031 | 172 | 41566.0587 | 32633.9479
1212 | 5821 | MARIPOSA 2101309438 | 0.16968 | 24 | 13018.6366 | 5630.6567
1213 | 7936 | CARLOTTA 112142896 | 0.16929 | 33 | 8736.3016 | 3183.4592
1214 | 4276 | CLARK ROAD 110290548 | 0.16899 | 213 | 29415.2854 | 29415.2854
1215 | 293 | TASSAJARA 2112D514R | 0.16865 | 45 | 7666.4167 | 4376.3944
1216 | 8943 | CLAY 11031821 | 0.16812 | 17 | 6061.921 | 4972.0887
1217 | 8661 | STANISLAUS 1701circuit_breaker | 0.16596 | 72 | 10963.5629 | 10963.5629
1218 | 8902 | POSO MOUNTAIN 2104circuit_breaker | 0.16595 | 4 | 11934.6881 | 5614.2654
1219 | 659 | CAMP EVERS 21045096 | 0.16573 | 317 | 33040.8953 | 32780.5456
1220 | 8967 | SAN RAFAEL 110863598 | 0.16547 | 30 | 3076.8023 | 3076.8023
1221 | 6483 | ATASCADERO 1101A50 | 0.16538 | 275 | 33670.734 | 30172.5253
1222 | 7428 | FORT BRAGG A 11013113 | 0.16449 | 131 | 16133.333 | 16133.333
1223 | 4425 | ALHAMBRA 110595016 | 0.16361 | 14 | 6423.8169 | 1054.2618
1224 | 8805 | CLAY 110359714 | 0.16343 | 42 | 7453.2846 | 7453.2846
1225 | 3896 | VOLTA 11021502 | 0.16267 | 87 | 11858.7407 | 11858.7407
1226 | 5030 | CAMP EVERS 21065020 | 0.16153 | 240 | 24453.2376 | 24453.2376
1227 | 8520 | SAN LUIS OBISPO 1107V62 | 0.16126 | 41 | 11135.8835 | 10856.7862
1228 | 2032 | BIG BASIN 11025066 | 0.15826 | 206 | 23248.0337 | 23248.0337
1229 | 1800 | CASTRO VALLEY 1108MR748 | 0.15774 | 97 | 10026.1125 | 10026.1125
1230 | 5452 | CORRAL 110214028 | 0.1572 | 36 | 12833.3324 | 5856.3944
1231 | 969 | OAKHURST 110310140 | 0.15555 | 260 | 27059.5406 | 27059.5406
1232 | 50 | DUNBAR 1102448 | 0.155 | 41 | 14544.1744 | 3456.1423
1233 | 1525 | CARLOTTA 11214914 | 0.15429 | 152 | 22809.6793 | 15711.3837
1234 | 8644 | PASO ROBLES 1103N52 | 0.15419 | 38 | 10495.5857 | 10495.5857
1235 | 2549 | MENLO 11031721 | 0.15412 | 117 | 10927.2973 | 10927.2973
1236 | 3123 | PINE GROVE 11011021 | 0.15408 | 73 | 6749.2717 | 6749.2717
1237 | 5880 | EEL RIVER 11024814 | 0.154 | 32 | 44419.8849 | 43150.0728
1238 | 4174 | SAN LUIS OBISPO 1103V82 | 0.15331 | 84 | 22412.6462 | 12932.1765
1239 | 3710 | CALAVERAS CEMENT 1101circuit_breaker | 0.15309 | 95 | 29364.3079 | 16524.9105
1240 | 3109 | LUCERNE 1103630 | 0.1528 | 134 | 21891.672 | 19624.8492
1241 | 7457 | MOUNTAIN QUARRIES 210135466 | 0.15266 | 78 | 11954.1294 | 11954.1294
1242 | 5725 | COTATI 1102260 | 0.15154 | 24 | 9537.0372 | 4171.7031
1243 | 2953 | RACETRACK 170311270 | 0.15107 | 117 | 19572.4814 | 19572.4814
1244 | 7358 | POINT MORETTI 110136514 | 0.15034 | 99 | 10964.1377 | 10964.1377
1245 | 6807 | MOLINO 1102982462 | 0.14981 | 21 | 2320.9625 | 2320.9625
1246 | 4387 | CAMP EVERS 210511010 | 0.14962 | 30 | 3577.8936 | 3577.8936
1247 | 5138 | PAUL SWEET 210610424 | 0.14925 | 72 | 11634.0857 | 9066.2649
1248 | 7533 | FULTON 11024994 | 0.14905 | 13 | 6942.8858 | 1753.9056
1249 | 1352 | FROGTOWN 170211212 | 0.14791 | 184 | 34480.8483 | 34480.8483
1250 | 8397 | STELLING 111060080 | 0.1467 | 109 | 16267.2425 | 15400.8729
1251 | 7850 | WEST POINT 110272036 | 0.1466 | 33 | 3794.583 | 3794.583
1252 | 1533 | PAUL SWEET 21065178 | 0.14566 | 118 | 11755.1342 | 11755.1342
1253 | 5033 | OLETA 11022642 | 0.14514 | 48 | 14995.7136 | 14995.7136
1254 | 5080 | VOLTA 11011568 | 0.14477 | 22 | 36682.0507 | 36682.0507
1255 | 3774 | HOOPA 11017468 | 0.14293 | 95 | 19602.473 | 10422.5231
1256 | 4724 | SISQUOC 1102M54 | 0.14271 | 58 | 48149.8206 | 30625.2961
1257 | 7999 | MONTICELLO 1101654 | 0.14251 | 52 | 14051.7969 | 12946.7956
1258 | 676 | STONE CORRAL 111075288 | 0.14235 | 5 | 47821.8592 | 1818.7235
1259 | 4400 | TIDEWATER 210665866 | 0.14191 | 13 | 14341.466 | 2331.7066
1260 | 8519 | SWIFT 2110XR254 | 0.14162 | 175 | 39910.094 | 39910.094
1261 | 1083 | MC KEE 1107XR010 | 0.1416 | 23 | 21796.6657 | 4483.0278
1262 | 3520 | HORSESHOE 1101circuit_breaker | 0.14153 | 7 | 8647.7105 | 1020.0278
1263 | 3937 | GANSNER 11012006 | 0.14132 | 260 | 27571.1883 | 27571.1883
1264 | 2664 | CHOLAME 2102X10 | 0.14047 | 25 | 70786.6402 | 32569.8267
1265 | 1362 | MIWUK 170193062 | 0.13963 | 98 | 13308.2221 | 13308.2221
1266 | 3752 | OLEMA 110150396 | 0.13922 | 221 | 21037.3757 | 20493.6346
1267 | 8904 | PIT NO 1 1101circuit_breaker | 0.13921 | 46 | 10477.1422 | 10477.1422
1268 | 1887 | WYANDOTTE 110641650 | 0.13876 | 2 | 25775.0399 | 1286.1146
1269 | 4034 | UKIAH 1114528 | 0.13839 | 34 | 19731.4227 | 4515.409
1270 | 317 | PLACERVILLE 1110circuit_breaker | 0.13652 | 181 | 20117.9419 | 18295.3344
1271 | 2315 | OLEMA 1101320 | 0.13384 | 36 | 21386.8301 | 5064.1889
1272 | 1416 | BIG BASIN 1102circuit_breaker | 0.13371 | 74 | 10031.5247 | 10031.5247
1273 | 1530 | HOPLAND 110180620 | 0.13322 | 20 | 9040.9556 | 1849.3413
1274 | 4707 | GUALALA 111223444 | 0.13312 | 71 | 23359.6524 | 23359.6524
1275 | 248 | MADISON 210189332 | 0.13195 | 2 | 36123.4333 | 1160.8504
1276 | 4045 | EL DORADO PH 210219542 | 0.13184 | 143 | 15104.0184 | 15104.0184
1277 | 6015 | GREENBRAE 110356884 | 0.13122 | 8 | 2392.4896 | 883.8137
1278 | 1003 | UKIAH 1114822 | 0.13047 | 20 | 22663.2714 | 3178.5328
1279 | 9320 | SILVERADO 2104645 | 0.1302 | 17 | 1626.8938 | 1626.8938
1280 | 689 | CAMP EVERS 210512590 | 0.12889 | 81 | 8909.0232 | 7908.9298
1281 | 6867 | MENLO 11038512 | 0.12814 | 232 | 26938.1265 | 26938.1265
1282 | 8095 | WEST POINT 1102L3733 | 0.1275 | 36 | 2820.1267 | 2820.1267
1283 | 7753 | CAMP EVERS 210660120 | 0.12748 | 76 | 7017.9486 | 7017.9486
1284 | 2028 | EL DORADO PH 21026645 | 0.12746 | 72 | 6883.7119 | 6883.7119
1285 | 2217 | EL DORADO PH 210152456 | 0.12663 | 158 | 16414.576 | 16414.576
1286 | 6503 | CABRILLO 1104Y24 | 0.12604 | 59 | 30947.8055 | 28736.9146
1287 | 2973 | HOPLAND 1101558 | 0.12521 | 18 | 15006.3279 | 2272.5532
1288 | 1655 | WILLOW CREEK 110347966 | 0.12502 | 214 | 27180.6372 | 27180.6372
1289 | 1456 | BEN LOMOND 1101BL 1101 | 0.12495 | 141 | 13712.9137 | 13712.9137
1290 | 7820 | LAS POSITAS 2108MR182 | 0.12479 | 44 | 11548.6884 | 10768.7759
1291 | 7505 | SILVERADO 21051421 | 0.12379 | 113 | 15928.1461 | 15418.6642
1292 | 5418 | ELECTRA 110161816 | 0.12168 | 331 | 37900.7563 | 37900.7563
1293 | 6623 | EL DORADO PH 210113532 | 0.12148 | 85 | 8511.6067 | 8511.6067
1294 | 2752 | TASSAJARA 211238868 | 0.12081 | 23 | 6910.3569 | 2492.9277
1295 | 1855 | ROB ROY 2104circuit_breaker | 0.12038 | 213 | 22978.5798 | 22978.5798
1296 | 7050 | CLARKSVILLE 21096502 | 0.1195 | 36 | 8746.5939 | 3563.6935
1297 | 853 | PEORIA 17019811 | 0.11916 | 17 | 14351.9195 | 4687.197
1298 | 4804 | TEMPLETON 2110R94 | 0.1184 | 100 | 33532.7028 | 21302.3977
1299 | 5846 | MILPITAS 1109XR524 | 0.11833 | 22 | 18154.4959 | 16623.6103
1300 | 4688 | SAN LUIS OBISPO 1104V46 | 0.11803 | 130 | 33475.4301 | 30343.0121
1301 | 8021 | BEAR VALLEY 210576694 | 0.118 | 48 | 7317.351 | 7317.351
1302 | 3594 | VASCO 1102MR178 | 0.11712 | 3 | 21484.5374 | 2230.6889
1303 | 7955 | CURTIS 1703circuit_breaker | 0.11614 | 103 | 17646.6229 | 13991.6786
1304 | 704 | LAKEVILLE 1102280 | 0.1157 | 7 | 14239.5056 | 3287.3324
1305 | 999 | HOPLAND 1101770 | 0.11554 | 18 | 21887.414 | 7603.6292
1306 | 4953 | CRESCENT MILLS 21012056 | 0.11542 | 59 | 10443.0868 | 5959.1083
1307 | 6270 | TULUCAY 1101628 | 0.1153 | 6 | 12014.0867 | 3826.9754
1308 | 7576 | STILLWATER 1101circuit_breaker | 0.11516 | 57 | 6895.2449 | 6237.7847
1309 | 5973 | MOLINO 1101152 | 0.11437 | 40 | 18334.7231 | 3850.1683
1310 | 8363 | RACETRACK 17036014 | 0.11412 | 88 | 11321.9024 | 11321.9024
1311 | 1265 | FROGTOWN 170232556 | 0.11388 | 50 | 10065.4499 | 7932.1339
1312 | 3420 | JESSUP 1103circuit_breaker | 0.11329 | 8 | 22946.415 | 998.4804
1313 | 5982 | POSO MOUNTAIN 21012181 | 0.11309 | 7 | 38091.8602 | 26885.9284
1314 | 4823 | WEST POINT 110136674 | 0.11294 | 47 | 15191.9661 | 15191.9661
1315 | 7202 | COLUMBIA HILL 11018233 | 0.11261 | 74 | 8056.6943 | 8056.6943
1316 | 1009 | SALT SPRINGS 21023142 | 0.11247 | 278 | 27128.7333 | 27128.7333
1317 | 5046 | SHADY GLEN 110248894 | 0.11194 | 148 | 16046.7548 | 13914.1946
1318 | 1518 | MARTELL 110191216 | 0.11155 | 615 | 66328.7264 | 66328.7264
1319 | 9321 | WILLOW CREEK 110237374 | 0.11144 | 18 | 2046.1835 | 2046.1835
1320 | 1117 | ELECTRA 110136816 | 0.11132 | 72 | 8016.99 | 8016.99
1321 | 4122 | NORTH BRANCH 1101circuit_breaker | 0.11124 | 99 | 32618.4392 | 23932.4889
1322 | 7802 | BEAR VALLEY 210513430 | 0.11121 | 133 | 21403.3287 | 21403.3287
1323 | 82 | HALSEY 11011704 | 0.11118 | 225 | 21258.1613 | 21258.1613
1324 | 7263 | IONE 1101L3141 | 0.11117 | 106 | 22463.5933 | 21707.6376
1325 | 1421 | MIWUK 1701953336 | 0.11084 | 187 | 19079.6137 | 19079.6137
1326 | 1947 | COTATI 1105328 | 0.10978 | 15 | 22174.0143 | 1823.3649
1327 | 6447 | CAMP EVERS 210637210 | 0.10952 | 110 | 10381.5121 | 10381.5121
1328 | 2497 | COTATI 1102825 | 0.10927 | 5 | 3371.6214 | 749.4567
1329 | 1683 | HALF MOON BAY 1103H80 | 0.10923 | 241 | 31887.8354 | 31887.8354
1330 | 3093 | EAST MARYSVILLE 11081706 | 0.10874 | 8 | 96667.4367 | 891.2903
1331 | 3281 | KANAKA 11011406 | 0.10795 | 357 | 44466.328 | 43311.9933
1332 | 362 | POINT MORETTI 11015078 | 0.10782 | 134 | 23596.4557 | 23596.4557
1333 | 3147 | SHADY GLEN 110151696 | 0.10765 | 276 | 33124.3103 | 28237.56
1334 | 8018 | COTATI 1102282 | 0.10732 | 29 | 8211.2885 | 4768.5619
1335 | 7140 | LLAGAS 2104XR294 | 0.10723 | 15 | 16899.7408 | 4685.9835
1336 | 9498 | BOLINAS 1101806 | 0.10612 | 40 | 4898.4533 | 4898.4533
1337 | 334 | COTATI 1102464 | 0.10565 | 19 | 13038.4156 | 2945.14
1338 | 9114 | CURTIS 170411300 | 0.10502 | 47 | 5848.9555 | 5848.9555
1339 | 2036 | WILLOW CREEK 11032936 | 0.10465 | 394 | 53467.3373 | 53467.3373
1340 | 4481 | SARATOGA 1107413816 | 0.10446 | 167 | 17947.1279 | 17947.1279
1341 | 4192 | RAWSON 110385334 | 0.10414 | 6 | 15285.8468 | 3724.4141
1342 | 3504 | MIRABEL 1101circuit_breaker | 0.10401 | 36 | 13652.7515 | 3875.2533
1343 | 3792 | PUEBLO 1105716 | 0.10344 | 44 | 31715.3368 | 4005.9439
1344 | 3233 | FULTON 1102circuit_breaker | 0.10338 | 5 | 7126.3044 | 646.4219
1345 | 5304 | SHADY GLEN 11012768 | 0.10235 | 109 | 12974.2233 | 11242.1065
1346 | 484 | BRUNSWICK 11102664 | 0.10232 | 123 | 17466.8136 | 12678.4586
1347 | 1184 | HOPLAND 1101960 | 0.10185 | 140 | 35106.288 | 23874.8083
1348 | 5720 | SANTA ROSA A 1111114 | 0.10163 | 79 | 18440.8581 | 9582.7736
1349 | 7229 | SHINGLE SPRINGS 2108circuit_breaker | 0.10127 | 20 | 2376.1029 | 2376.1029
1350 | 8364 | NAPA 11025039 | 0.10083 | 3 | 8769.8715 | 68.3438
1351 | 682 | PIT NO 1 11013312 | 0.10069 | 80 | 14682.7391 | 12918.6838
1352 | 510 | POINT ARENA 110147952 | 0.10064 | 31 | 16717.6297 | 16717.6297
1353 | 2954 | BIG MEADOWS 21012586 | 0.099126 | 100 | 17615.5168 | 8954.8757
1354 | 6126 | GUALALA 111135562 | 0.099045 | 247 | 22847.3348 | 22847.3348
1355 | 265 | MIRABEL 1102332 | 0.098904 | 86 | 9065.6252 | 9065.6252
1356 | 1845 | FORT BRAGG A 110231304 | 0.09867 | 272 | 34687.2851 | 34687.2851
1357 | 7811 | CRESCENT MILLS 21012562 | 0.097711 | 185 | 54701.1021 | 25377.9444
1358 | 5533 | UKIAH 1115circuit_breaker | 0.097118 | 213 | 40874.779 | 26755.7552
1359 | 9018 | PINE GROVE 11029145 | 0.09639 | 52 | 4703.8594 | 4703.8594
1360 | 8849 | LLAGAS 2105XR234 | 0.09573 | 9 | 3448.7535 | 1152.082
1361 | 7415 | LLAGAS 2101XR586 | 0.095685 | 32 | 21353.5124 | 7394.3416
1362 | 5572 | GREEN VALLEY 210111054 | 0.095583 | 183 | 40835.6292 | 38401.1556
1363 | 4304 | POSO MOUNTAIN 21014456 | 0.095012 | 58 | 37862.2156 | 37862.2156
1364 | 1067 | MORAGA 1101circuit_breaker | 0.093981 | 86 | 12067.7483 | 10864.992
1365 | 9020 | FRENCH GULCH 11022902 | 0.093136 | 86 | 11239.784 | 11239.784
1366 | 3827 | AUBERRY 110137536 | 0.093 | 60 | 8826.9707 | 8826.9707
1367 | 9129 | circuit_breaker | 0.092782 | 65 | 11948.6238 | 11948.6238
1368 | 2936 | SHADY GLEN 110132726 | 0.09262 | 200 | 20171.8595 | 20147.5271
1369 | 7975 | MARTELL 11016074 | 0.092143 | 52 | 5835.7283 | 5835.7283
1370 | 2427 | HARRIS 1109700 | 0.091921 | 251 | 47370.0595 | 23735.6051
1371 | 3703 | CAMP EVERS 210612518 | 0.091732 | 270 | 25588.9357 | 25588.9357
1372 | 4005 | CAMP EVERS 210410442 | 0.091626 | 96 | 16787.1434 | 8552.2815
1373 | 7267 | SONOMA 1106376 | 0.091552 | 9 | 8667.3641 | 1147.4391
1374 | 6103 | NORTH BRANCH 110113496 | 0.091309 | 11 | 8066.3398 | 2903.2847
1375 | 5891 | CALAVERAS CEMENT 110180930 | 0.091082 | 213 | 29611.6951 | 29611.6951
1376 | 5240 | MIRABEL 11014859 | 0.090574 | 36 | 2980.2139 | 2980.2139
1377 | 5011 | DUNLAP 11027360 | 0.090166 | 63 | 13675.786 | 13675.786
1378 | 491 | ALTO 112278672 | 0.089559 | 59 | 13243.554 | 5142.0354
1379 | 2458 | ROB ROY 210410714 | 0.089499 | 212 | 31415.4862 | 22255.4392
1380 | 7739 | CORNING 11021900 | 0.089467 | 3 | 29783.4957 | 3377.7597
1381 | 2795 | PLACERVILLE 111219742 | 0.089425 | 100 | 11949.352 | 9960.0097
1382 | 4774 | MONTICELLO 1101720 | 0.088816 | 2 | 13187.1947 | 11082.9735
1383 | 305 | CALPINE 1144circuit_breaker | 0.088245 | 8 | 42270.0145 | 42270.0145
1384 | 7477 | POINT ARENA 110183354 | 0.088104 | 20 | 8260.8147 | 8260.8147
1385 | 2681 | BIG BASIN 110212124 | 0.088081 | 69 | 6852.9075 | 6852.9075
1386 | 2960 | LUCERNE 110638632 | 0.0879 | 55 | 7546.5249 | 7104.2847
1387 | 3543 | BRUNSWICK 110532536 | 0.087446 | 303 | 34249.9271 | 34249.9271
1388 | 8909 | WYANDOTTE 110942650 | 0.087234 | 11 | 4239.6112 | 1091.021
1389 | 6999 | WILLOW CREEK 110129362 | 0.086372 | 108 | 18629.0665 | 11564.4444
1390 | 2968 | PHILO 11021308 | 0.086273 | 368 | 51499.148 | 51499.148
1391 | 5590 | CLARK ROAD 11022070 | 0.086172 | 59 | 17647.3936 | 15820.4099
1392 | 6273 | WEST POINT 110113444 | 0.085978 | 133 | 26771.8299 | 26771.8299
1393 | 2412 | OAKHURST 110310190 | 0.085952 | 166 | 18572.0473 | 18572.0473
1394 | 986 | ROB ROY 21045082 | 0.085342 | 346 | 33221.6065 | 32076.122
1395 | 4156 | LAS GALLINAS A 1104304 | 0.085197 | 8 | 4019.6637 | 683.5311
1396 | 65 | TEJON 11022455 | 0.085122 | 74 | 10444.6875 | 10444.6875
1397 | 6913 | ALLEGHANY 1101VR816 | 0.085027 | 65 | 6679.2994 | 6679.2994
1398 | 2592 | APPLE HILL 110412947 | 0.084889 | 60 | 5562.8913 | 5562.8913
1399 | 4482 | KERCKHOFF 1101R353 | 0.08415 | 39 | 22124.1321 | 22124.1321
1400 | 9481 | BIG MEADOWS 21012248 | 0.084149 | 94 | 14718.1001 | 14718.1001
1401 | 7128 | GEYSERVILLE 1102circuit_breaker | 0.083896 | 23 | 11834.3236 | 3579.9474
1402 | 4680 | ATASCADERO 1103A88 | 0.083425 | 9 | 4273.7537 | 1106.7141
1403 | 4775 | WEST POINT 110277204 | 0.083247 | 99 | 11906.8331 | 11906.8331
1404 | 5530 | APPLE HILL 1104circuit_breaker | 0.083174 | 65 | 6802.485 | 6802.485
1405 | 8547 | WEST POINT 11021535 | 0.0829 | 49 | 4933.5895 | 4933.5895
1406 | 2675 | SAN LUIS OBISPO 1104V10 | 0.082715 | 16 | 10945.8906 | 5741.8428
1407 | 1012 | VOLTA 110253130 | 0.082407 | 204 | 22286.621 | 22286.621
1408 | 8207 | OLEMA 1101602 | 0.082371 | 128 | 39506.2468 | 25492.7395
1409 | 9343 | 701650 | 0.082354 | 15 | 1191.4526 | 1191.4526
1410 | 8645 | WILDWOOD 110185112 | 0.082307 | 92 | 10853.0331 | 10853.0331
1411 | 5583 | BELLEVUE 2103646 | 0.082037 | 110 | 19879.4545 | 12247.7458
1412 | 2705 | HALF MOON BAY 11036018 | 0.082028 | 122 | 30588.369 | 24500.2785
1413 | 3314 | COTATI 1105734248 | 0.081908 | 7 | 774.6582 | 774.6582
1414 | 6055 | WILLOW CREEK 110191926 | 0.081905 | 77 | 17080.2643 | 7078.2935
1415 | 9163 | CEDAR CREEK 11011710 | 0.081775 | 2 | 117.4627 | 117.4627
1416 | 513 | MONTE RIO 1111292 | 0.08029 | 21 | 31768.7358 | 22117.1152
1417 | 5862 | CALPELLA 1102circuit_breaker | 0.080005 | 20 | 14778.125 | 3000.9026
1418 | 3 | HIGGINS 1104498932 | 0.07974 | 62 | 6861.4641 | 5868.3896
1419 | 8756 | REDBUD 110244119 | 0.079595 | 5 | 4510.2451 | 603.3084
1420 | 4861 | MONTE RIO 1113180 | 0.079529 | 32 | 3131.1085 | 3131.1085
1421 | 970 | FROGTOWN 1701circuit_breaker | 0.079219 | 93 | 17920.0747 | 16003.3182
1422 | 4720 | SUNOL 1101MR196 | 0.079191 | 17 | 20307.975 | 3630.319
1423 | 312 | DUNBAR 1103440 | 0.078811 | 39 | 22799.1788 | 4464.9005
1424 | 3317 | BOLINAS 1101504 | 0.078783 | 92 | 10763.1712 | 10456.414
1425 | 5660 | OLEMA 11011318 | 0.078571 | 159 | 16637.0018 | 13978.4041
1426 | 5551 | SANTA YNEZ 1102Y18 | 0.0785 | 37 | 12113.6185 | 7602.3972
1427 | 6493 | PALMER 1101M84 | 0.078441 | 34 | 39207.0427 | 34798.532
1428 | 3057 | BIG BASIN 1101circuit_breaker | 0.078261 | 84 | 7584.3674 | 7584.3674
1429 | 7643 | COARSEGOLD 210210207 | 0.07723 | 55 | 5760.3678 | 5760.3678
1430 | 9200 | BUCKS CREEK 1103circuit_breaker | 0.076361 | 21 | 3699.7995 | 3699.7995
1431 | 5942 | JESSUP 11013383 | 0.07635 | 24 | 3031.9376 | 1995.2743
1432 | 7702 | PINE GROVE 1101circuit_breaker | 0.07567 | 62 | 6897.7403 | 6897.7403
1433 | 4351 | ELECTRA 11024756 | 0.074716 | 72 | 19012.5154 | 15007.7986
1434 | 6088 | MIWUK 170219772 | 0.074328 | 64 | 6198.5938 | 6198.5938
1435 | 9374 | MADISON 210113372 | 0.073868 | 11 | 6130.2461 | 6078.9039
1436 | 5779 | MORGAN HILL 2111XR292 | 0.073232 | 134 | 19536.8147 | 17517.5113
1437 | 4877 | MARTELL 1103circuit_breaker | 0.073194 | 12 | 10088.6649 | 1549.4828
1438 | 2470 | HIGGINS 111051794 | 0.073168 | 46 | 6260.8685 | 6256.2965
1439 | 5777 | GEYSERVILLE 1101482 | 0.073031 | 4 | 6000.7291 | 352.7494
1440 | 2709 | FULTON 1107circuit_breaker | 0.072892 | 5 | 22107.5267 | 487.3016
1441 | 7680 | MONTE RIO 111137520 | 0.072826 | 32 | 3470.728 | 3470.728
1442 | 1561 | CORRAL 110359770 | 0.072287 | 54 | 11687.7898 | 6842.3899
1443 | 3578 | PLACERVILLE 2106circuit_breaker | 0.072068 | 40 | 10714.4314 | 10352.4951
1444 | 4928 | RIO DELL 110270960 | 0.071776 | 60 | 19246.0448 | 5431.663
1445 | 1746 | WEIMAR 11026175 | 0.071468 | 46 | 4390.4905 | 4390.4905
1446 | 8441 | SAN LUIS OBISPO 11042293 | 0.071445 | 95 | 14494.4535 | 14494.4535
1447 | 9369 | MONTE RIO 1113678 | 0.07122 | 27 | 2967.1836 | 2967.1836
1448 | 60 | CORRAL 110175204 | 0.071046 | 1 | 29877.8806 | 154.2541
1449 | 8169 | COTATI 1102462 | 0.070272 | 15 | 6310.2369 | 4359.8054
1450 | 937 | STANISLAUS 170179826 | 0.070253 | 152 | 16403.2639 | 16403.2639
1451 | 8197 | CARLOTTA 112144150 | 0.06969 | 63 | 5746.8082 | 5746.8082
1452 | 7479 | WILLOW PASS 2107P500R | 0.069642 | 1 | 5092.597 | 1031.3201
1453 | 2669 | MIWUK 1702circuit_breaker | 0.069568 | 142 | 16506.2205 | 16506.2205
1454 | 6865 | BRUNSWICK 110663124 | 0.069315 | 93 | 9428.9995 | 9428.9995
1455 | 9105 | BALCH NO 1 1101circuit_breaker | 0.069275 | 34 | 13497.4542 | 13497.4542
1456 | 5093 | SAND CREEK 11037110 | 0.068861 | 153 | 29837.817 | 29837.817
1457 | 5185 | BIG BASIN 110110720 | 0.068186 | 65 | 7531.494 | 7531.494
1458 | 6093 | MADISON 21011606 | 0.068058 | 1 | 26669.2024 | 1536.4017
1459 | 455 | WEIMAR 11012084 | 0.06799 | 298 | 29727.9123 | 29727.9123
1460 | 8995 | PIT NO 5 1101circuit_breaker | 0.067873 | 8 | 1162.2395 | 1162.2395
1461 | 214 | MADISON 21017702 | 0.067763 | 4 | 34431.5939 | 1421.2134
1462 | 7329 | COLUMBIA HILL 110190730 | 0.067619 | 115 | 13390.7322 | 13390.7322
1463 | 9051 | SALT SPRINGS 21028442 | 0.067574 | 196 | 19520.8754 | 19520.8754
1464 | 3438 | NARROWS 21022718 | 0.067495 | 8 | 11669.952 | 747.0941
1465 | 6815 | BELLEVUE 1102392 | 0.067165 | 3 | 10922.1116 | 223.0422
1466 | 1759 | CAMP EVERS 210510912 | 0.067156 | 92 | 8140.064 | 8140.064
1467 | 7948 | WISE 11011404 | 0.066999 | 12 | 5668.509 | 1996.1981
1468 | 177 | HIGGINS 11041374 | 0.06691 | 126 | 13460.5941 | 12504.4738
1469 | 4346 | RINCON 1102circuit_breaker | 0.066795 | 30 | 5733.5212 | 4493.3108
1470 | 4223 | PLACERVILLE 210623190 | 0.066453 | 64 | 5913.2611 | 5913.2611
1471 | 1108 | PETALUMA C 1109128 | 0.066191 | 4 | 60135.589 | 54365.1404
1472 | 2916 | CASTRO VALLEY 1109MR334 | 0.065212 | 59 | 10131.275 | 9273.2114
1473 | 5003 | HARTLEY 1102circuit_breaker | 0.065211 | 33 | 18689.97 | 4816.0328
1474 | 5879 | OTTER 110263868 | 0.065133 | 192 | 25330.6289 | 25330.6289
1475 | 9470 | VOLTA 1102circuit_breaker | 0.064946 | 26 | 5307.8332 | 5307.8332
1476 | 8666 | MIDDLETOWN 11011079 | 0.064932 | 37 | 5531.7956 | 5531.7956
1477 | 1580 | MONTE RIO 11133970 | 0.064828 | 117 | 11846.1263 | 11846.1263
1478 | 1639 | 9690 | 0.064438 | 238 | 27542.9968 | 27542.9968
1479 | 325 | MESA 1101circuit_breaker | 0.064216 | 45 | 41442.2698 | 18758.3645
1480 | 9115 | BOLINAS 110137034 | 0.063866 | 57 | 7287.0481 | 7287.0481
1481 | 5340 | MAPLE CREEK 1101circuit_breaker | 0.063615 | 130 | 23066.1262 | 15254.5949
1482 | 6966 | PEABODY 2113circuit_breaker | 0.063256 | 2 | 9790.3302 | 1530.5409
1483 | 5071 | WYANDOTTE 110313018 | 0.062831 | 4 | 2657.2717 | 201.9138
1484 | 6009 | RISING RIVER 11019032 | 0.062709 | 191 | 37315.5797 | 35634.3752
1485 | 7072 | CLAY 1103circuit_breaker | 0.062535 | 41 | 21666.9014 | 9300.035
1486 | 4731 | PLACERVILLE 1112circuit_breaker | 0.061911 | 112 | 15101.3483 | 13371.697
1487 | 4462 | COARSEGOLD 21025722 | 0.061392 | 39 | 3182.9469 | 3182.9469
1488 | 9177 | LLAGAS 21014523 | 0.06098 | 8 | 4420.7892 | 1169.9655
1489 | 7660 | CAMP EVERS 210612840 | 0.060901 | 69 | 6527.3425 | 6527.3425
1490 | 4944 | WOODSIDE 11018912 | 0.060752 | 71 | 6396.0491 | 6353.9227
1491 | 771 | MIRABEL 1102circuit_breaker | 0.060224 | 73 | 18129.1338 | 7538.7631
1492 | 8121 | ZACA 1101Y72 | 0.060174 | 13 | 10339.027 | 8576.3267
1493 | 3925 | GRASS VALLEY 11012766 | 0.060111 | 50 | 5407.6674 | 5321.5191
1494 | 8685 | FREMONT 1104MR339 | 0.059732 | 5 | 11193.7644 | 1796.5075
1495 | 9153 | MONTE RIO 11113891 | 0.059592 | 50 | 5703.541 | 5703.541
1496 | 3846 | ZACA 1101Y70 | 0.05957 | 21 | 13925.2647 | 8678.0315
1497 | 6662 | PETALUMA C 1108208 | 0.059522 | 2 | 19951.8799 | 19951.8799
1498 | 6613 | BEN LOMOND 110196738 | 0.0593 | 109 | 10935.49 | 10935.49
1499 | 3589 | SUNOL 1101MR297 | 0.059157 | 91 | 9725.4912 | 9415.923
1500 | 1527 | MEADOW LANE 2106C558R | 0.058743 | 8 | 22949.7629 | 1360.7806
1501 | 4519 | ANITA 11062418 | 0.058595 | 5 | 39339.8369 | 185.0114
1502 | 9009 | GUALALA 1112circuit_breaker | 0.058525 | 25 | 3460.0472 | 2540.8884
1503 | 6825 | PEORIA 1701circuit_breaker | 0.05837 | 46 | 14117.7933 | 14117.7933
1504 | 7724 | PIT NO 5 11011606 | 0.057743 | 84 | 8892.9459 | 8892.9459
1505 | 4356 | MIWUK 170238218 | 0.057725 | 89 | 17457.0622 | 17457.0622
1506 | 1412 | MIWUK 170111800 | 0.056971 | 114 | 15184.802 | 15184.802
1507 | 1364 | CURTIS 170539256 | 0.056842 | 45 | 42574.1624 | 42574.1624
1508 | 4121 | LOS GATOS 1106LA64 | 0.056688 | 212 | 20491.3377 | 20491.3377
1509 | 2551 | FORT ROSS 1121124 | 0.0563 | 60 | 29943.2023 | 29943.2023
1510 | 4414 | TASSAJARA 210865438 | 0.056223 | 11 | 6051.8729 | 1087.8821
1511 | 7068 | MARTELL 110299214 | 0.055938 | 24 | 3260.5607 | 2497.7197
1512 | 5092 | NEWBURG 1133circuit_breaker | 0.055322 | 44 | 14787.4934 | 3484.7774
1513 | 8716 | POSO MOUNTAIN 21013990 | 0.055169 | 3 | 8936.2242 | 6347.4219
1514 | 8884 | PACIFICA 11033907 | 0.05514 | 27 | 7747.6312 | 5462.3478
1515 | 1573 | RINCON 1104circuit_breaker | 0.055116 | 36 | 9046.3288 | 4001.0684
1516 | 8710 | CALPINE 1146circuit_breaker | 0.054802 | 5 | 4947.493 | 4947.493
1517 | 7960 | PINE GROVE 110194936 | 0.054724 | 130 | 14913.8447 | 14913.8447
1518 | 2726 | ANNAPOLIS 110176842 | 0.054597 | 30 | 9045.3441 | 9045.3441
1519 | 3533 | PINE GROVE 11013166 | 0.054521 | 187 | 20128.8983 | 20128.8983
1520 | 8106 | ORO FINO 1102127563 | 0.054333 | 98 | 11105.9314 | 11105.9314
1521 | 7949 | CAMP EVERS 210611533 | 0.053683 | 49 | 4271.438 | 4271.438
1522 | 9097 | SAND CREEK 110397354 | 0.053608 | 64 | 16295.7352 | 13531.0761
1523 | 8447 | CASTRO VALLEY 11068971 | 0.053341 | 126 | 12736.098 | 12641.384
1524 | 7746 | APPLE HILL 210289934 | 0.053239 | 71 | 9059.6456 | 9059.6456
1525 | 5890 | SALT SPRINGS 210237300 | 0.053159 | 41 | 11257.5171 | 11257.5171
1526 | 4077 | MARIPOSA 210110170 | 0.05292 | 178 | 26174.8185 | 26174.8185
1527 | 6725 | SALT SPRINGS 210297924 | 0.052773 | 80 | 8204.8506 | 8204.8506
1528 | 9122 | GIRVAN 1101circuit_breaker | 0.052634 | 18 | 5303.193 | 2142.1974
1529 | 9383 | CALPINE 1146400 | 0.052574 | 3 | 5057.3021 | 5057.3021
1530 | 8130 | JESSUP 11012839 | 0.05209 | 27 | 2364.3372 | 2364.3372
1531 | 9338 | COARSEGOLD 210210610 | 0.05183 | 24 | 2195.6315 | 2195.6315
1532 | 7085 | MENLO 110212249 | 0.051811 | 32 | 3776.3578 | 3776.3578
1533 | 5553 | CABRILLO 11031437 | 0.051561 | 9 | 7854.9148 | 4397.9316
1534 | 2833 | MC ARTHUR 110137388 | 0.051433 | 28 | 20103.5682 | 12648.9045
1535 | 6928 | CURTIS 17046060 | 0.051334 | 60 | 6649.044 | 6649.044
1536 | 5933 | CURTIS 17029111 | 0.051194 | 78 | 9135.0634 | 9135.0634
1537 | 4288 | COTATI 110475972 | 0.051118 | 42 | 7223.394 | 4863.4766
1538 | 3778 | FORT BRAGG A 11014698 | 0.050544 | 120 | 12907.3842 | 12907.3842
1539 | 1592 | SAN MIGUEL 1104R66 | 0.050459 | 15 | 71296.2907 | 11247.2619
1540 | 6526 | HALF MOON BAY 1103695411 | 0.050425 | 120 | 13109.0272 | 13109.0272
1541 | 5424 | FORT ROSS 112137326 | 0.050157 | 25 | 8318.589 | 8318.589
1542 | 8737 | CHOLAME 21025597 | 0.049822 | 34 | 8229.9238 | 8229.9238
1543 | 1791 | FORT BRAGG A 11014622 | 0.049687 | 167 | 21198.3263 | 21198.3263
1544 | 2552 | EMERALD LAKE 0401circuit_breaker | 0.049205 | 107 | 33996.9433 | 23419.0309
1545 | 8932 | BROWNS VALLEY 1101circuit_breaker | 0.049117 | 3 | 1309.7042 | 1061.2697
1546 | 7623 | LLAGAS 2107XR178 | 0.04906 | 10 | 10843.4754 | 1344.6176
1547 | 1866 | PLACERVILLE 1111circuit_breaker | 0.048914 | 96 | 10619.6052 | 10305.9598
1548 | 6026 | MONTE RIO 1113202 | 0.048804 | 88 | 8479.0365 | 8479.0365
1549 | 3569 | PENNGROVE 1101554 | 0.048649 | 16 | 20497.8694 | 1740.0436
1550 | 5794 | ROSSMOOR 110837848 | 0.048616 | 68 | 9580.5994 | 9580.5994
1551 | 994 | CASTRO VALLEY 1106MR337 | 0.0486 | 108 | 60886.6391 | 26387.8444
1552 | 7099 | LOW GAP 1101circuit_breaker | 0.048432 | 30 | 3490.2509 | 3490.2509
1553 | 4997 | CALAVERAS CEMENT 110111236 | 0.048303 | 212 | 31569.3587 | 31569.3587
1554 | 869 | SALT SPRINGS 21024796 | 0.048155 | 126 | 11537.3564 | 11537.3564
1555 | 4860 | MC ARTHUR 11021324 | 0.048146 | 4 | 41089.9508 | 3069.2847
1556 | 6723 | PAUL SWEET 2106428102 | 0.048126 | 184 | 20879.8446 | 19212.6145
1557 | 8574 | SPANISH CREEK 4401circuit_breaker | 0.047933 | 84 | 12760.2493 | 9502.8761
1558 | 2498 | HALSEY 1101circuit_breaker | 0.04785 | 271 | 27545.8987 | 27545.8987
1559 | 5657 | MESA 11016113 | 0.047802 | 5 | 15635.2421 | 1783.5868
1560 | 7276 | HARTLEY 1101circuit_breaker | 0.047745 | 17 | 4864.6418 | 2204.3614
1561 | 1392 | ORO FINO 11012022 | 0.04772 | 259 | 27985.9982 | 27985.9982
1562 | 4390 | SAN LUIS OBISPO 1104V14 | 0.04746 | 46 | 13129.632 | 13115.916
1563 | 574 | LUCERNE 110647198 | 0.04742 | 35 | 9365.4324 | 4671.7433
1564 | 8910 | COTATI 1102circuit_breaker | 0.047392 | 4 | 3229.2079 | 2904.3184
1565 | 2405 | MC ARTHUR 11011546 | 0.047265 | 62 | 37312.9087 | 20599.9851
1566 | 4407 | CRESCENT MILLS 21013113 | 0.047014 | 20 | 1919.7007 | 1853.1278
1567 | 4307 | PLACERVILLE 11118582 | 0.046977 | 145 | 18913.646 | 14528.3903
1568 | 3452 | HALF MOON BAY 11039112 | 0.046954 | 27 | 12911.7543 | 5442.5238
1569 | 5113 | FITCH MOUNTAIN 1111circuit_breaker | 0.046726 | 7 | 28044.9802 | 486.7283
1570 | 3903 | CALAVERAS CEMENT 11011419 | 0.046637 | 194 | 24046.9564 | 24046.9564
1571 | 1414 | MENLO 11028952 | 0.046373 | 117 | 21850.1909 | 21850.1909
1572 | 2815 | MOLINO 1102344 | 0.046318 | 17 | 9676.0469 | 1463.3176
1573 | 5248 | MIRABEL 1101228 | 0.046034 | 27 | 15637.442 | 3472.2526
1574 | 3556 | FROGTOWN 1702circuit_breaker | 0.045877 | 32 | 8323.2793 | 4274.7494
1575 | 4468 | WEIMAR 11012058 | 0.045746 | 330 | 33216.2606 | 33216.2606
1576 | 7473 | PUEBLO 2103694 | 0.045737 | 8 | 7674.026 | 1193.6984
1577 | 4594 | BIG RIVER 11011286 | 0.045707 | 75 | 12142.2229 | 6546.1056
1578 | 5809 | CAMP EVERS 210694770 | 0.045686 | 36 | 6436.7786 | 3595.9649
1579 | 296 | MONTE RIO 111164758 | 0.04552 | 52 | 17002.078 | 17002.078
1580 | 1833 | HIGGINS 1104842642 | 0.045422 | 97 | 9304.2839 | 9304.2839
1581 | 3255 | ORO FINO 110265932 | 0.045272 | 76 | 6996.2918 | 6996.2918
1582 | 2810 | CAMP EVERS 210311046 | 0.044646 | 260 | 26125.6746 | 26125.6746
1583 | 5960 | CAMP EVERS 2105circuit_breaker | 0.044631 | 116 | 16540.5741 | 12905.269
1584 | 5603 | PAUL SWEET 210710986 | 0.044334 | 89 | 31999.8278 | 13450.8089
1585 | 8383 | SUNOL 1101circuit_breaker | 0.043844 | 37 | 9328.3659 | 4242.1562
1586 | 5124 | STONE CORRAL 11087100 | 0.043472 | 12 | 29507.2094 | 3682.723
1587 | 106 | RACETRACK 17038120 | 0.043341 | 136 | 14368.0422 | 14368.0422
1588 | 6161 | DUNLAP 1102circuit_breaker | 0.043259 | 66 | 10788.4174 | 10788.4174
1589 | 1950 | HALF MOON BAY 110369412 | 0.043116 | 141 | 69043.3705 | 42522.6197
1590 | 8891 | BIG BASIN 11028403 | 0.043092 | 86 | 7917.119 | 7917.119
1591 | 5873 | GANSNER 110137550 | 0.043071 | 9 | 7302.7522 | 1056.3754
1592 | 8101 | STELLING 11109265 | 0.042974 | 62 | 9183.0563 | 9183.0563
1593 | 3679 | CURTIS 170510590 | 0.042297 | 138 | 15780.5647 | 15780.5647
1594 | 6123 | WOODACRE 11011238 | 0.042192 | 61 | 5891.9294 | 5891.9294
1595 | 4973 | PUEBLO 21021326 | 0.042172 | 2 | 19367.251 | 326.1269
1596 | 1363 | STANISLAUS 17011331 | 0.041407 | 65 | 7071.5091 | 7071.5091
1597 | 9639 | HIGGINS 1107746082 | 0.041016 | 11 | 1365.375 | 1365.375
1598 | 3459 | CORTINA 1101302192 | 0.040868 | 7 | 28675.233 | 1666.8417
1599 | 580 | MIWUK 170110600 | 0.040795 | 135 | 17528.1979 | 17528.1979
1600 | 4182 | MORGAN HILL 2105XR494 | 0.040455 | 7 | 11814.4524 | 485.8055
1601 | 3962 | KONOCTI 11081278 | 0.040363 | 71 | 12812.7853 | 7722.6194
1602 | 2656 | PEORIA 170567898 | 0.040318 | 51 | 9738.6344 | 5781.6377
1603 | 5770 | NOTRE DAME 1104circuit_breaker | 0.039974 | 4 | 11050.043 | 1372.1379
1604 | 8528 | BIG BASIN 11022253 | 0.03981 | 23 | 2352.4543 | 2352.4543
1605 | 4002 | SPAULDING 1101578852 | 0.0398 | 179 | 39043.058 | 33138.4596
1606 | 9434 | DEL MAR 210975802 | 0.039747 | 2 | 668.5307 | 547.5648
1607 | 7482 | OAKHURST 1102circuit_breaker | 0.039746 | 38 | 7704.6852 | 3940.8287
1608 | 3473 | DUNBAR 1103circuit_breaker | 0.039611 | 28 | 19663.038 | 3351.8236
1609 | 9247 | ORO FINO 11022236 | 0.03936 | 12 | 4120.4561 | 4120.4561
1610 | 6295 | MC ARTHUR 11011488 | 0.039044 | 17 | 53844.4679 | 2966.0846
1611 | 3406 | GRASS VALLEY 11012208 | 0.038641 | 183 | 20526.1791 | 18884.1728
1612 | 5215 | BRUNSWICK 11052100 | 0.03847 | 40 | 6320.6672 | 6320.6672
1613 | 739 | GUALALA 1112662 | 0.037962 | 94 | 13650.0311 | 8946.2004
1614 | 9319 | MONTE RIO 111159046 | 0.037933 | 33 | 6178.7733 | 5445.8416
1615 | 8732 | LAKEWOOD 210964992 | 0.03793 | 7 | 4200.5164 | 587.7906
1616 | 5072 | POINT ARENA 110137426 | 0.03786 | 5 | 8133.5264 | 776.126
1617 | 7251 | CASTRO VALLEY 1108MR341 | 0.03785 | 30 | 5102.7494 | 3784.8751
1618 | 5506 | BIG BASIN 110212758 | 0.037848 | 60 | 9878.3441 | 9878.3441
1619 | 150 | NEWBURG 11322074 | 0.037732 | 14 | 16861.3212 | 1527.0717
1620 | 8982 | LUCERNE 11034200 | 0.037615 | 15 | 7940.3444 | 6495.7462
1621 | 2478 | MIWUK 17028130 | 0.037592 | 68 | 15891.4897 | 15891.4897
1622 | 9466 | POINT ARENA 11014923 | 0.037358 | 21 | 4611.3164 | 4611.3164
1623 | 7075 | SANTA MARIA 1108M18 | 0.037275 | 42 | 28755.1345 | 23036.475
1624 | 5608 | HIGHLANDS 11034630 | 0.037028 | 8 | 5570.4953 | 963.0506
1625 | 4066 | CAMP EVERS 210610718 | 0.037016 | 140 | 13748.6879 | 13748.6879
1626 | 2001 | REEDLEY 1104274990 | 0.036799 | 5 | 66865.8982 | 2623.0001
1627 | 3139 | EL CERRITO G 1105BR160 | 0.036383 | 116 | 36928.2073 | 26237.4779
1628 | 841 | SALT SPRINGS 21011216 | 0.036328 | 69 | 8899.3047 | 8899.3047
1629 | 3487 | OAKHURST 110377384 | 0.036325 | 54 | 7607.5657 | 7607.5657
1630 | 329 | CAMBRIA 1102circuit_breaker | 0.036053 | 89 | 37393.8508 | 25658.8486
1631 | 6139 | GREEN VALLEY 210136820 | 0.03573 | 68 | 26572.8864 | 7189.3721
1632 | 6982 | NOVATO 110455398 | 0.035317 | 31 | 36300.9132 | 9657.1265
1633 | 674 | MONTE RIO 1113524 | 0.035215 | 88 | 10034.2173 | 10034.2173
1634 | 2907 | CURTIS 1704803 | 0.035133 | 138 | 15628.5101 | 15628.5101
1635 | 6835 | FRENCH GULCH 11012905 | 0.035126 | 115 | 15608.0555 | 15608.0555
1636 | 3648 | WEIMAR 1102circuit_breaker | 0.035075 | 190 | 19516.5086 | 19516.5086
1637 | 7943 | MONTE RIO 1111240 | 0.035066 | 33 | 4934.4459 | 4934.4459
1638 | 3663 | INDIAN FLAT 1104circuit_breaker | 0.034794 | 98 | 20602.0949 | 20602.0949
1639 | 3021 | MONTE RIO 1113320 | 0.034777 | 44 | 4416.0265 | 4416.0265
1640 | 186 | BIG RIVER 110179628 | 0.034735 | 233 | 23966.4375 | 23966.4375
1641 | 1425 | LAS GALLINAS A 1105904 | 0.034699 | 17 | 11479.983 | 1736.6554
1642 | 8709 | CAMP EVERS 210510225 | 0.034306 | 5 | 292.7321 | 292.7321
1643 | 5177 | FORT ROSS 1121560 | 0.03406 | 58 | 9208.7912 | 8402.379
1644 | 7298 | POINT ARENA 11012637 | 0.033982 | 54 | 6500.6025 | 6500.6025
1645 | 3012 | CAMP EVERS 210510728 | 0.033956 | 151 | 16827.1381 | 16827.1381
1646 | 374 | STANISLAUS 17021804 | 0.033923 | 17 | 13424.5046 | 13424.5046
1647 | 6031 | MONTE RIO 11131989 | 0.033813 | 15 | 1164.5069 | 1164.5069
1648 | 5118 | CURTIS 1705843 | 0.033784 | 96 | 10626.4913 | 10626.4913
1649 | 7758 | STANISLAUS 17017144 | 0.033781 | 78 | 7457.9017 | 7457.9017
1650 | 584 | GARBERVILLE 1103circuit_breaker | 0.033644 | 11 | 3592.4976 | 841.9717
1651 | 5834 | CRESCENT MILLS 21012230 | 0.033467 | 71 | 17863.1589 | 8832.0855
1652 | 7934 | CAL WATER 1102920714 | 0.033432 | 10 | 13869.7898 | 6508.6114
1653 | 2806 | SAN RAFAEL 11071166 | 0.03328 | 217 | 24108.9087 | 19693.934
1654 | 7469 | PIT NO 1 110170952 | 0.033125 | 22 | 2749.7949 | 2745.2229
1655 | 4155 | CAMP EVERS 21065302 | 0.032687 | 89 | 9619.5872 | 9619.5872
1656 | 7397 | MIRABEL 110257840 | 0.032498 | 35 | 4145.2916 | 4145.2916
1657 | 5700 | CASTRO VALLEY 1108MR243 | 0.03246 | 71 | 8931.2655 | 8931.2655
1658 | 8189 | MC ARTHUR 11011544 | 0.032419 | 59 | 44879.1507 | 22817.5943
1659 | 2984 | STANISLAUS 17021888 | 0.032406 | 25 | 30461.9306 | 30461.9306
1660 | 6607 | HALF MOON BAY 110398440 | 0.032267 | 120 | 13071.9471 | 13071.9471
1661 | 9446 | SILVERADO 2102circuit_breaker | 0.031956 | 8 | 2761.2179 | 345.0876
1662 | 932 | JARVIS 1108MR576 | 0.031924 | 3 | 9799.7281 | 434.201
1663 | 7752 | TASSAJARA 2106circuit_breaker | 0.031908 | 1 | 5000.9317 | 809.5956
1664 | 1625 | BRUNSWICK 110750010 | 0.031892 | 79 | 14946.7962 | 9532.5902
1665 | 6997 | SARATOGA 1107167792 | 0.031739 | 78 | 7328.1795 | 7328.1795
1666 | 2063 | SAN BENITO 210488772 | 0.031685 | 125 | 69280.8495 | 37629.3808
1667 | 1966 | SAN RAFAEL 110839156 | 0.031649 | 51 | 7673.7546 | 5556.6949
1668 | 4021 | MARIPOSA 21014410 | 0.031595 | 45 | 36631.6496 | 36631.6496
1669 | 4696 | SAN JOAQUIN #3 110210342 | 0.031479 | 26 | 2930.8819 | 2930.8819
1670 | 8696 | DUNBAR 11033135 | 0.031434 | 2 | 1214.2636 | 100.9792
1671 | 4706 | SEACLIFF 040112946 | 0.03127 | 38 | 5200.6844 | 3742.632
1672 | 9394 | BOLINAS 11011232 | 0.03113 | 19 | 3935.7724 | 3520.8723
1673 | 2135 | PUEBLO 2102circuit_breaker | 0.031073 | 4 | 25233.7086 | 802.3935
1674 | 2991 | AUBERRY 1101R324 | 0.030952 | 145 | 17331.696 | 17331.696
1675 | 138 | RACETRACK 1703circuit_breaker | 0.030943 | 201 | 28812.6661 | 24637.5385
1676 | 7400 | UPPER LAKE 11016663 | 0.030656 | 25 | 3763.6845 | 3763.6845
1677 | 6880 | BIG RIVER 110169032 | 0.030536 | 148 | 13621.9318 | 13621.9318
1678 | 2083 | IGNACIO 11011300 | 0.030228 | 43 | 9813.462 | 4134.7438
1679 | 973 | PEORIA 170413494 | 0.030167 | 17 | 12088.6323 | 3111.8752
1680 | 4424 | LLAGAS 21011449 | 0.030034 | 99 | 22615.7362 | 16208.7254
1681 | 7444 | ELK 11011260 | 0.03001 | 223 | 24924.6684 | 24474.7526
1682 | 2492 | BRUNSWICK 111061602 | 0.029644 | 135 | 20441.2599 | 14421.8376
1683 | 532 | TEMPLETON 2113R82 | 0.029288 | 11 | 111327.2051 | 60266.4888
1684 | 1680 | ELK 110191336 | 0.02904 | 97 | 13315.4628 | 11968.0294
1685 | 648 | GABILAN 1101579969 | 0.02898 | 28 | 10763.6377 | 5768.1438
1686 | 1146 | BIG BASIN 110195690 | 0.028798 | 63 | 6270.3435 | 6270.3435
1687 | 4538 | PURISIMA 1101Y42 | 0.028796 | 22 | 26927.883 | 2254.0917
1688 | 230 | KONOCTI 11022293 | 0.02848 | 24 | 2820.5709 | 2621.5628
1689 | 3689 | AUBERRY 1101R322 | 0.028431 | 31 | 12046.3509 | 12046.3509
1690 | 3304 | LUCERNE 110638436 | 0.028398 | 51 | 7720.9209 | 7130.3909
1691 | 6183 | PIT NO 1 11019702 | 0.028389 | 5 | 14797.5762 | 994.3298
1692 | 3198 | CRESCENT MILLS 2101circuit_breaker | 0.028253 | 27 | 9131.4478 | 3593.1531
1693 | 3507 | CURTIS 17039330 | 0.028092 | 112 | 66426.892 | 66426.892
1694 | 6063 | MORAGA 110118216 | 0.027944 | 69 | 7868.0142 | 7868.0142
1695 | 826 | ELK 11011272 | 0.027835 | 352 | 36075.8659 | 35495.0764
1696 | 1254 | ORO FINO 11022556 | 0.027772 | 9 | 10716.6127 | 10716.6127
1697 | 1861 | HALF MOON BAY 11028848 | 0.027681 | 49 | 16171.7557 | 4923.8197
1698 | 8011 | CLOVERDALE 1102circuit_breaker | 0.027641 | 3 | 4874.945 | 420.2416
1699 | 3938 | OAKHURST 11035120 | 0.027529 | 54 | 10236.3208 | 10236.3208
1700 | 1200 | SUNOL 1101MR298 | 0.027508 | 44 | 8594.3194 | 8010.2959
1701 | 2108 | MIWUK 170153038 | 0.027105 | 103 | 10691.9033 | 10691.9033
1702 | 3017 | V50 | 0.027081 | 82 | 16865.8166 | 10661.0029
1703 | 9599 | TEJON 11023760 | 0.026795 | 37 | 10548.2717 | 10548.2717
1704 | 2271 | MORAGA 1101108540 | 0.026699 | 73 | 7755.7349 | 7755.7349
1705 | 8291 | CLAY 11037142 | 0.026676 | 30 | 24816.4121 | 5016.468
1706 | 4765 | GEYSERVILLE 1101480 | 0.026348 | 13 | 25712.4856 | 1516.0203
1707 | 856 | RISING RIVER 1101circuit_breaker | 0.026339 | 77 | 21037.7324 | 14030.5414
1708 | 7719 | MIWUK 1702S1547 | 0.026326 | 40 | 4436.0854 | 4436.0854
1709 | 4225 | BOLINAS 11011236 | 0.026227 | 35 | 6557.8129 | 5655.0294
1710 | 259 | ROB ROY 21055090 | 0.026197 | 311 | 34034.3802 | 34034.3802
1711 | 7175 | BUCKS CREEK 11031131 | 0.026054 | 49 | 4424.1224 | 4424.1224
1712 | 3890 | SAN RAFAEL 1108322 | 0.026007 | 96 | 11886.0783 | 11483.9582
1713 | 9083 | HALF MOON BAY 11036065 | 0.025971 | 64 | 11019.2698 | 9622.0817
1714 | 9158 | VOLTA 110293418 | 0.025833 | 39 | 4264.808 | 4264.808
1715 | 9541 | OLEMA 110175686 | 0.0257 | 15 | 7759.3517 | 6456.4354
1716 | 7045 | HALF MOON BAY 11018902 | 0.025359 | 111 | 30497.3428 | 21140.1681
1717 | 2536 | BIG RIVER 110155402 | 0.025245 | 41 | 14975.0535 | 3203.2885
1718 | 7589 | SAN JUSTO 11014002 | 0.025092 | 156 | 30436.1969 | 29265.3642
1719 | 1120 | PARADISE 1105circuit_breaker | 0.024939 | 60 | 29169.3143 | 19516.665
1720 | 6971 | LOS GATOS 11072917 | 0.024912 | 123 | 12406.0821 | 12406.0821
1721 | 1670 | LUCERNE 110676850 | 0.024884 | 28 | 5965.4962 | 2991.9456
1722 | 8278 | CAMP EVERS 210533542 | 0.024875 | 39 | 3984.6462 | 3984.6462
1723 | 7598 | PIT NO 3 2101circuit_breaker | 0.024694 | 93 | 11059.9326 | 10857.4498
1724 | 984 | SANTA ROSA A 1111circuit_breaker | 0.024652 | 5 | 9029.1633 | 423.6161
1725 | 3431 | MONTE RIO 1111256 | 0.024513 | 83 | 11643.9499 | 11643.9499
1726 | 8986 | GARCIA 0401circuit_breaker | 0.024371 | 1 | 68.2264 | 68.2264
1727 | 8009 | PERRY 110185870 | 0.024359 | 40 | 26928.3914 | 14444.7623
1728 | 3122 | KONOCTI 1108950 | 0.024125 | 57 | 11930.8969 | 9061.9141
1729 | 6809 | MONTE RIO 11138299 | 0.024077 | 17 | 1927.3515 | 1927.3515
1730 | 7257 | RESERVATION ROAD 11023030 | 0.024009 | 54 | 41722.8305 | 10130.7204
1731 | 6523 | CASTRO VALLEY 110810315 | 0.023983 | 92 | 8831.8074 | 8831.8074
1732 | 6388 | NORTH DUBLIN 2101circuit_breaker | 0.023887 | 7 | 6326.3479 | 5815.8712
1733 | 2132 | DIAMOND SPRINGS 1104circuit_breaker | 0.023684 | 79 | 16049.1693 | 9049.1715
1734 | 5922 | BRUNSWICK 1105circuit_breaker | 0.023642 | 58 | 11223.4618 | 10665.1471
1735 | 3860 | GRAYS FLAT 0401circuit_breaker | 0.02328 | 166 | 17210.1208 | 17210.1208
1736 | 2055 | ATASCADERO 1103A46 | 0.023067 | 7 | 14964.2331 | 983.4741
1737 | 4718 | BEAR VALLEY 2101circuit_breaker | 0.023048 | 147 | 30106.3475 | 30106.3475
1738 | 340 | BRUNSWICK 11052204 | 0.023045 | 27 | 11642.89 | 11642.89
1739 | 1671 | CALAVERAS CEMENT 110136880 | 0.023023 | 66 | 13909.6582 | 9538.3272
1740 | 8214 | POSO MOUNTAIN 21033988 | 0.02298 | 19 | 29944.6558 | 26364.8424
1741 | 3984 | JOLON 11027040 | 0.022703 | 49 | 36880.7714 | 31780.5056
1742 | 1475 | HUMBOLDT BAY 11024724 | 0.02261 | 109 | 24851.4009 | 10436.2695
1743 | 7028 | ARCATA 11224218 | 0.022605 | 89 | 8162.5664 | 7920.8951
1744 | 3711 | POINT MORETTI 110110726 | 0.022416 | 179 | 17020.6225 | 17020.6225
1745 | 2562 | BRUNSWICK 11062104 | 0.022255 | 161 | 15655.9212 | 15655.9212
1746 | 1104 | LAS GALLINAS A 1106circuit_breaker | 0.022152 | 23 | 25166.3517 | 2059.9533
1747 | 8495 | ORO FINO 1102circuit_breaker | 0.022121 | 27 | 3368.9824 | 3368.9824
1748 | 1472 | PIERCY 2110XR258 | 0.022118 | 151 | 85030.9239 | 64524.1827
1749 | 4653 | SISQUOC 1102M52 | 0.021921 | 91 | 57351.1566 | 54915.488
1750 | 2187 | EL DORADO PH 210136764 | 0.021821 | 50 | 7038.7814 | 4920.5157
1751 | 7910 | GRASS VALLEY 110358498 | 0.021784 | 17 | 3648.0777 | 2050.6115
1752 | 9176 | ORO FINO 110239154 | 0.021568 | 11 | 1419.8889 | 1419.8889
1753 | 4319 | HALF MOON BAY 1103circuit_breaker | 0.021546 | 20 | 13492.7817 | 2489.4218
1754 | 7983 | FOOTHILL 1102circuit_breaker | 0.021441 | 70 | 15763.1114 | 12510.7066
1755 | 9136 | SUNOL 1101MR387 | 0.021284 | 41 | 8023.8265 | 7477.4807
1756 | 2224 | ELK 1101circuit_breaker | 0.021193 | 147 | 27400.2212 | 18644.2912
1757 | 4408 | RESERVATION ROAD 1102circuit_breaker | 0.021173 | 73 | 28859.6299 | 12102.7686
1758 | 3965 | REDBUD 1102432 | 0.021171 | 12 | 18069.9686 | 1279.6978
1759 | 1189 | ROB ROY 21055166 | 0.0211 | 97 | 8833.6807 | 8833.6807
1760 | 5765 | MIWUK 17029270 | 0.020886 | 84 | 9423.8186 | 9423.8186
1761 | 686 | RESERVATION ROAD 11013026 | 0.020822 | 212 | 36330.5251 | 34466.6969
1762 | 2994 | HIGGINS 11032194 | 0.020631 | 18 | 4329.2096 | 1734.1421
1763 | 9302 | BALCH NO 1 1101R372 | 0.020579 | 40 | 9846.4194 | 9846.4194
1764 | 7881 | BEAR VALLEY 21054609 | 0.020174 | 48 | 7321.9227 | 7321.9227
1765 | 2161 | OAKHURST 11035470 | 0.02003 | 127 | 15314.9972 | 15314.9972
1766 | 3988 | BURNEY 11021340 | 0.019916 | 234 | 28964.4993 | 28964.4993
1767 | 8087 | LOS GATOS 110760024 | 0.019915 | 31 | 6397.1295 | 6397.1295
1768 | 6585 | SEACLIFF 0401circuit_breaker | 0.019852 | 95 | 9677.833 | 9172.6769
1769 | 9262 | OREGON TRAIL 110346860 | 0.019814 | 4 | 5350.0868 | 1140.2586
1770 | 2555 | HIGGINS 1104533648 | 0.019668 | 113 | 10867.9062 | 10867.9062
1771 | 3465 | LUCERNE 1103circuit_breaker | 0.019474 | 18 | 13358.6173 | 3472.4667
1772 | 8487 | OTTER 11022166 | 0.019283 | 68 | 6559.0006 | 6559.0006
1773 | 5445 | CLEAR LAKE 11024708 | 0.019218 | 4 | 4509.6824 | 312.1287
1774 | 842 | SONOMA 1103418 | 0.018961 | 3 | 9496.5275 | 326.2189
1775 | 9539 | KONOCTI 11024421 | 0.018937 | 10 | 585.3593 | 585.3593
1776 | 6687 | PUEBLO 1104640 | 0.018784 | 8 | 4473.5204 | 1072.0071
1777 | 3996 | MONTE RIO 1111140 | 0.018751 | 35 | 4235.2908 | 4235.2908
1778 | 3292 | ORO FINO 110276008 | 0.018671 | 261 | 25688.6957 | 25688.6957
1779 | 3121 | SONOMA 110478372 | 0.01863 | 11 | 27765.3023 | 26611.5178
1780 | 2170 | MONROE 2103circuit_breaker | 0.018573 | 3 | 23628.7455 | 674.1153
1781 | 8874 | OILFIELDS 1103N46 | 0.018527 | 1 | 9360.626 | 9360.626
1782 | 5896 | OCEANO 1106V28 | 0.018506 | 18 | 14455.0675 | 2046.144
1783 | 2811 | PIT NO 5 11011660 | 0.018465 | 67 | 7855.6791 | 7855.6791
1784 | 7522 | PIT NO 5 11011658 | 0.018422 | 48 | 7306.3402 | 7306.3402
1785 | 7796 | WOODSIDE 11018601 | 0.018323 | 9 | 961.631 | 961.631
1786 | 3106 | ALTO 11251226 | 0.018322 | 105 | 12660.3361 | 12208.7235
1787 | 174 | KING CITY 11037038 | 0.01824 | 130 | 34883.787 | 28474.5458
1788 | 23 | TASSAJARA 2103circuit_breaker | 0.018193 | 9 | 28888.6491 | 651.7218
1789 | 9593 | BUTTE 1105244246 | 0.018084 | 8 | 885.0826 | 885.0826
1790 | 7183 | LUCERNE 11062327 | 0.018082 | 17 | 2038.5927 | 1891.7626
1791 | 5523 | POINT MORETTI 11015104 | 0.01784 | 2 | 3011.2994 | 3011.2994
1792 | 4383 | TIDEWATER 210657926 | 0.017735 | 1 | 18927.2283 | 0
1793 | 406 | BRUNSWICK 11062796 | 0.017607 | 351 | 31981.5846 | 31981.5846
1794 | 977 | HALF MOON BAY 11022032 | 0.017499 | 14 | 17402.7083 | 2245.4219
1795 | 5284 | FROGTOWN 1701L3361 | 0.017344 | 34 | 3015.6838 | 3015.6838
1796 | 2902 | BIG BASIN 110276752 | 0.017276 | 38 | 4328.6941 | 4328.6941
1797 | 7933 | MERCED FALLS 110222772 | 0.017154 | 20 | 3605.0516 | 3605.0516
1798 | 1077 | CABRILLO 1103Y12 | 0.017144 | 10 | 49554.7865 | 40069.4408
1799 | 3649 | PINE GROVE 110152088 | 0.017119 | 41 | 4068.7441 | 4068.7441
1800 | 5744 | SANTA ROSA A 110464565 | 0.017116 | 12 | 1301.8977 | 1301.8977
1801 | 5585 | HIGGINS 1103995672 | 0.017077 | 56 | 9263.8953 | 5336.5048
1802 | 9161 | DRUM 1101circuit_breaker | 0.016944 | 11 | 3389.5909 | 3389.5909
1803 | 5332 | ALHAMBRA 11058302 | 0.016872 | 98 | 13278.3332 | 13278.3332
1804 | 7339 | CURTIS 17058110 | 0.016828 | 103 | 13092.5709 | 13092.5709
1805 | 8273 | DUNLAP 1103circuit_breaker | 0.016793 | 34 | 8988.316 | 8988.316
1806 | 9046 | PIT NO 5 11011614 | 0.016792 | 11 | 3000.4112 | 3000.4112
1807 | 2244 | OCEANO 1104circuit_breaker | 0.016646 | 55 | 24379.2168 | 11912.9543
1808 | 2386 | PIT NO 3 21011360 | 0.016564 | 228 | 34538.882 | 33967.8078
1809 | 7345 | AUBERRY 110149122 | 0.016501 | 2 | 6376.7942 | 6376.7942
1810 | 1216 | CALAVERAS CEMENT 110147968 | 0.016492 | 427 | 65252.4191 | 65252.4191
1811 | 2346 | HALSEY 110239104 | 0.016481 | 483 | 48994.5328 | 48994.5328
1812 | 893 | DUNLAP 11027050 | 0.016413 | 103 | 14670.6683 | 14670.6683
1813 | 572 | MONTE RIO 111123916 | 0.016366 | 76 | 8839.5506 | 8839.5506
1814 | 1696 | BOLINAS 1101circuit_breaker | 0.016353 | 26 | 3500.023 | 3408.2951
1815 | 951 | CAYUCOS 1102circuit_breaker | 0.016314 | 77 | 46289.4977 | 20474.7402
1816 | 7916 | BURNEY 11029042 | 0.016269 | 47 | 5080.7921 | 5080.7921
1817 | 3135 | 9280 | 0.016214 | 111 | 10238.6401 | 10238.6401
1818 | 9742 | STAFFORD 1102circuit_breaker | 0.016045 | 3 | 993.1053 | 669.8914
1819 | 1046 | ALTO 11251256 | 0.015882 | 70 | 7051.2781 | 6410.4568
1820 | 8117 | HOOPA 110193038 | 0.015689 | 13 | 4553.13 | 1584.2405
1821 | 2359 | MONTE RIO 1113477 | 0.015562 | 35 | 2831.9084 | 2831.9084
1822 | 7553 | MESA 1103M92 | 0.015537 | 9 | 12733.2432 | 1573.0951
1823 | 6081 | CURTIS 170268380 | 0.015476 | 101 | 10695.6106 | 10695.6106
1824 | 3162 | WEST POINT 11014706 | 0.015202 | 9 | 18548.1318 | 18548.1318
1825 | 6077 | OLEMA 11011252 | 0.015184 | 66 | 6562.8215 | 6562.8215
1826 | 4596 | ELK 11018779 | 0.015045 | 67 | 6865.4129 | 6865.4129
1827 | 894 | PEORIA 170590374 | 0.014965 | 63 | 7135.3675 | 6578.4615
1828 | 7954 | BIG MEADOWS 21012476 | 0.014902 | 113 | 14000.8931 | 12812.7347
1829 | 8741 | WEST POINT 1101L3355 | 0.014759 | 9 | 3577.4455 | 3577.4455
1830 | 1201 | FORT ROSS 11212987 | 0.014718 | 15 | 3345.8187 | 3345.8187
1831 | 4093 | 10720 | 0.014648 | 63 | 7647.7028 | 7647.7028
1832 | 6047 | PEORIA 170587222 | 0.014645 | 65 | 8479.914 | 8240.0572
1833 | 2694 | JARVIS 1108MR368 | 0.014645 | 6 | 5392.0942 | 761.5311
1834 | 3924 | CABRILLO 1103Y10 | 0.01464 | 19 | 24484.6302 | 7083.7808
1835 | 7181 | CABRILLO 1103Y46 | 0.014619 | 22 | 76540.2703 | 37171.7089
1836 | 3214 | KONOCTI 1108circuit_breaker | 0.01454 | 50 | 14154.8598 | 9103.4044
1837 | 3772 | PINE GROVE 11021765 | 0.014495 | 22 | 2330.5339 | 2330.5339
1838 | 6605 | IONE 1101circuit_breaker | 0.014423 | 3 | 22553.5189 | 1810.1911
1839 | 8028 | NEWBURG 113190242 | 0.014415 | 62 | 7015.9838 | 5381.5662
1840 | 3904 | RINCON 1101576 | 0.014391 | 27 | 16916.5683 | 4105.0155
1841 | 7174 | EEL RIVER 11021902 | 0.01438 | 25 | 11921.8282 | 9656.571
1842 | 7210 | ROSSMOOR 110639424 | 0.01436 | 11 | 3992.9225 | 1232.955
1843 | 6453 | POINT ARENA 1101476 | 0.01399 | 26 | 24431.6786 | 4407.3314
1844 | 2938 | BURNEY 11022402 | 0.013963 | 8 | 6035.4639 | 2243.205
1845 | 1564 | SAN JOAQUIN #3 1101673480 | 0.013862 | 40 | 20465.7113 | 20465.7113
1846 | 1097 | MORGAN HILL 2104XR018 | 0.013825 | 92 | 17280.6805 | 9365.0904
1847 | 4312 | BRUNSWICK 11053611 | 0.013733 | 30 | 2597.3823 | 2597.3823
1848 | 8971 | POINT ARENA 11011296 | 0.013299 | 19 | 8913.723 | 4384.7382
1849 | 4938 | ALHAMBRA 110581514 | 0.013281 | 53 | 7693.8321 | 5038.5618
1850 | 6352 | CLAY 1101circuit_breaker | 0.013126 | 5 | 4411.9174 | 707.4258
1851 | 6186 | FORT BRAGG A 1102956 | 0.013116 | 154 | 19602.7346 | 18050.2005
1852 | 1334 | CAMP EVERS 21035753 | 0.013054 | 41 | 3895.5708 | 3895.5708
1853 | 748 | BIG RIVER 1101952 | 0.012958 | 210 | 26900.4145 | 26689.2485
1854 | 1584 | CABRILLO 1104Y22 | 0.012932 | 35 | 41421.5748 | 14759.1555
1855 | 2145 | NEWBURG 1131circuit_breaker | 0.012925 | 41 | 19977.4909 | 3684.9558
1856 | 1816 | FORT BRAGG A 11044690 | 0.012803 | 181 | 23032.9774 | 18031.2616
1857 | 2988 | LAURELES 1111432 | 0.012664 | 410 | 79055.4755 | 79055.4755
1858 | 5254 | SUNOL 1101MR299 | 0.012647 | 89 | 8022.9478 | 8022.9478
1859 | 8004 | NOTRE DAME 11042537 | 0.012588 | 26 | 8206.2423 | 8206.2423
1860 | 6142 | MC ARTHUR 11011490 | 0.012501 | 106 | 24194.4063 | 13967.782
1861 | 8974 | MONTE RIO 11131067 | 0.012373 | 12 | 1294.5528 | 1294.5528
1862 | 6506 | CAMP EVERS 21055188 | 0.012331 | 29 | 3191.7712 | 3191.7712
1863 | 6840 | OTTER 11022002 | 0.012257 | 89 | 13828.3943 | 13828.3943
1864 | 4597 | CAYUCOS 1102W18 | 0.012187 | 8 | 36681.1721 | 3816.311
1865 | 6546 | HOLLISTER 21024780 | 0.012035 | 8 | 24176.1189 | 2943.6622
1866 | 1290 | SHADY GLEN 1101circuit_breaker | 0.012018 | 49 | 8826.8608 | 5163.0926
1867 | 3335 | SAN BERNARD 1101circuit_breaker | 0.011924 | 1 | 71472.9513 | 1475.2454
1868 | 5959 | SAN RAFAEL 11081247 | 0.011787 | 3 | 414.4526 | 414.4526
1869 | 2099 | BRUNSWICK 1102circuit_breaker | 0.011748 | 79 | 10196.061 | 9785.3713
1870 | 8990 | PURISIMA 1101Y44 | 0.011688 | 30 | 18642.1512 | 16580.432
1871 | 5601 | PERRY 1101circuit_breaker | 0.011547 | 21 | 4085.1746 | 4085.1746
1872 | 6485 | HALSEY 1102circuit_breaker | 0.011477 | 122 | 12858.5938 | 12469.8674
1873 | 3387 | WEIMAR 11012740 | 0.011464 | 292 | 30589.1767 | 30589.1767
1874 | 1147 | SAN RAFAEL 11081210 | 0.01134 | 49 | 8753.0145 | 5233.0326
1875 | 5156 | CLAYTON 2212circuit_breaker | 0.011314 | 13 | 20442.1182 | 3174.2004
1876 | 2514 | HALSEY 11022514 | 0.011265 | 147 | 31410.9717 | 15960.9106
1877 | 438 | MONTE RIO 1112circuit_breaker | 0.011195 | 52 | 5973.9084 | 5973.9084
1878 | 2060 | VOLTA 11021648 | 0.011194 | 40 | 6728.2286 | 6728.2286
1879 | 6299 | CLARK ROAD 110247006 | 0.01111 | 33 | 7271.2685 | 7271.2685
1880 | 5662 | POINT MORETTI 11015076 | 0.011107 | 28 | 14517.5787 | 10957.7607
1881 | 8988 | LOS GATOS 1107LA60 | 0.011089 | 76 | 13828.9369 | 13828.9369
1882 | 7767 | BEN LOMOND 04015144 | 0.010883 | 15 | 6409.4899 | 6409.4899
1883 | 320 | CURTIS 170463502 | 0.010831 | 132 | 16791.7983 | 16791.7983
1884 | 8479 | OTTER 11022012 | 0.010828 | 24 | 16177.0749 | 14639.7556
1885 | 1124 | OLEMA 11011200 | 0.010671 | 54 | 4658.8808 | 4658.8808
1886 | 1761 | MORAGA 1102circuit_breaker | 0.01055 | 53 | 14952.4679 | 8031.17
1887 | 6457 | ALTO 11251158 | 0.010459 | 28 | 8797.5302 | 3766.7299
1888 | 3745 | AUBERRY 1101D4982 | 0.010392 | 41 | 4312.861 | 4312.861
1889 | 5429 | WYANDOTTE 1103circuit_breaker | 0.010316 | 2 | 11732.2478 | 375.8787
1890 | 219 | ROB ROY 210410960 | 0.010267 | 256 | 45185.3957 | 27847.2688
1891 | 8829 | VINEYARD 2107MR332 | 0.010203 | 7 | 5273.2666 | 460.8485
1892 | 1467 | BRUNSWICK 110350070 | 0.010059 | 9 | 44784.9902 | 44784.9902
1893 | 6572 | EDENVALE 1102XR064 | 0.010042 | 3 | 5786.1483 | 956.603
1894 | 3867 | POINT MORETTI 110112122 | 0.010034 | 29 | 12806.7268 | 9019.8604
1895 | 5681 | VOLTA 11011640 | 0.010028 | 149 | 16481.2885 | 16481.2885
1896 | 7480 | SONOMA 11045661 | 0.010025 | 4 | 8171.7539 | 3397.3315
1897 | 2375 | PINE GROVE 110245292 | 0.0099933 | 10 | 17509.1139 | 17509.1139
1898 | 4442 | RINCON 1101circuit_breaker | 0.0099601 | 26 | 7751.5983 | 2521.3047
1899 | 313 | GREEN VALLEY 210112106 | 0.0099233 | 82 | 30176.8092 | 9141.9925
1900 | 2139 | MERCED FALLS 110222774 | 0.0098346 | 7 | 5970.2453 | 1272.8669
1901 | 8659 | MIWUK 17021808 | 0.0098005 | 30 | 2945.2419 | 2945.2419
1902 | 8506 | PEORIA 170570198 | 0.0096704 | 19 | 5122.9043 | 3727.5999
1903 | 1786 | MORRO BAY 1101V66 | 0.0096664 | 18 | 26069.3739 | 5689.205
1904 | 8791 | CLAY 1102circuit_breaker | 0.0095983 | 7 | 3149.4821 | 1255.8462
1905 | 3780 | LOS GATOS 110660116 | 0.0095893 | 178 | 39794.9609 | 39794.9609
1906 | 7506 | OAKLAND K 110217430 | 0.0095491 | 20 | 2362.1685 | 2362.1685
1907 | 1338 | BURNEY 11021322 | 0.0095423 | 118 | 30035.9017 | 23390.5578
1908 | 8027 | SAN RAFAEL 11071276 | 0.0094899 | 55 | 6179.9373 | 5613.9148
1909 | 7774 | BRUNSWICK 1106circuit_breaker | 0.0094492 | 123 | 14188.8772 | 14079.7489
1910 | 1902 | SARATOGA 1107LC12 | 0.009432 | 125 | 12044.8193 | 12044.8193
1911 | 3422 | CRESCENT MILLS 21012232 | 0.0094184 | 219 | 32432.4236 | 22620.3804
1912 | 6067 | BIG RIVER 11011052 | 0.0094083 | 39 | 6204.7091 | 4296.6961
1913 | 9522 | FRANKLIN 1104P146 | 0.0093569 | 30 | 5929.8532 | 5649.6032
1914 | 6045 | PEORIA 170176030 | 0.0093245 | 23 | 9992.9255 | 8122.6361
1915 | 753 | SISQUOC 1103M98 | 0.0093097 | 19 | 15489.3429 | 11235.2762
1916 | 1263 | CALAVERAS CEMENT 11012646 | 0.0092904 | 174 | 28470.7774 | 28470.7774
1917 | 1460 | ORINDA 0401N545R | 0.0091894 | 56 | 8180.3467 | 7502.4589
1918 | 8296 | HICKS 2101circuit_breaker | 0.0090651 | 7 | 17493.6949 | 4105.0932
1919 | 7605 | PEORIA 1704circuit_breaker | 0.0090534 | 33 | 13354.1752 | 11652.3164
1920 | 1341 | HALF MOON BAY 11036014 | 0.0089784 | 22 | 19926.5393 | 6646.3728
1921 | 3882 | BIG BASIN 110112838 | 0.0089004 | 32 | 3775.6915 | 3775.6915
1922 | 1673 | SAN LUIS OBISPO 1105796050 | 0.0088838 | 6 | 7961.3272 | 2135.0041
1923 | 6236 | MONTE RIO 11131313 | 0.0088085 | 24 | 1981.3722 | 1981.3722
1924 | 3226 | TAR FLAT 04023144 | 0.0087181 | 73 | 8204.0408 | 7378.011
1925 | 6153 | MIWUK 1702S2247 | 0.0086771 | 24 | 2394.0014 | 2394.0014
1926 | 3395 | SO. CAL. EDISON #3 1101circuit_breaker | 0.0086536 | 7 | 13165.8307 | 13165.8307
1927 | 6218 | DEL MONTE 21043088 | 0.0085907 | 206 | 24826.2717 | 24826.2717
1928 | 5291 | ROSSMOOR 1108circuit_breaker | 0.0085631 | 51 | 9105.2713 | 5393.569
1929 | 7873 | MONTE RIO 1112999 | 0.0084844 | 16 | 1406.4428 | 1406.4428
1930 | 6694 | UKIAH 11112504 | 0.0084498 | 3 | 4779.0786 | 52.248
1931 | 7625 | PERRY 1101W26 | 0.0084163 | 19 | 4390.419 | 4390.419
1932 | 2691 | ROSSMOOR 110845268 | 0.008377 | 43 | 12359.2232 | 4023.0288
1933 | 7822 | COTATI 1105893 | 0.0083717 | 1 | 16957.7992 | 105.1251
1934 | 2890 | PAUL SWEET 2105circuit_breaker | 0.0082821 | 101 | 25766.2731 | 12715.3949
1935 | 8642 | ROB ROY 21045304 | 0.0082564 | 50 | 8039.9737 | 4973.8861
1936 | 7900 | VOLTA 110254932 | 0.0081164 | 69 | 6888.3237 | 6888.3237
1937 | 5722 | GARCIA 0401666 | 0.0081045 | 1 | 3911.285 | 3911.285
1938 | 6601 | SALT SPRINGS 210110416 | 0.0080821 | 10 | 928.207 | 928.207
1939 | 3016 | BELL 1107circuit_breaker | 0.0079817 | 5 | 6178.772 | 198.4714
1940 | 1854 | NAPA 1112circuit_breaker | 0.0079168 | 3 | 26219.4017 | 272.3504
1941 | 2706 | ELK 1101900 | 0.00791 | 43 | 33079.2876 | 9529.0573
1942 | 7781 | POSO MOUNTAIN 210448268 | 0.0077584 | 2 | 8339.3842 | 7515.6606
1943 | 9113 | MENLO 11028896 | 0.0077072 | 14 | 2488.0112 | 1013.7193
1944 | 8824 | FREMONT 1104MR707 | 0.0076763 | 6 | 14467.9261 | 2328.9027
1945 | 5123 | BIG BASIN 11015000 | 0.0076645 | 33 | 3211.5435 | 3211.5435
1946 | 2742 | JARVIS 1111MR121 | 0.007617 | 14 | 8355.9069 | 1635.8418
1947 | 1967 | HOLLISTER 21054018 | 0.0075849 | 89 | 84640.1679 | 69788.1445
1948 | 6538 | INDIAN FLAT 110410270 | 0.0075315 | 33 | 6119.8904 | 6119.8904
1949 | 2844 | TEJON 11032280 | 0.0075289 | 1 | 44165.0695 | 2624.0904
1950 | 8841 | BEAR VALLEY 210110019 | 0.007488 | 13 | 3187.4941 | 3187.4941
1951 | 5593 | OILFIELDS 1103N48 | 0.0074263 | 4 | 76455.2167 | 76392.1084
1952 | 6677 | BASALT 11065030 | 0.0073833 | 6 | 23881.4452 | 2570.7987
1953 | 6731 | ELECTRA 1101L1697 | 0.0073707 | 83 | 8779.0798 | 8779.0798
1954 | 3413 | MARTELL 110198374 | 0.0073527 | 9 | 6135.709 | 936.3607
1955 | 1005 | MARIPOSA 2101439030 | 0.007278 | 26 | 31566.7616 | 31566.7616
1956 | 1481 | MONTE RIO 1113circuit_breaker | 0.0072556 | 59 | 7159.5444 | 7159.5444
1957 | 9289 | ROB ROY 21046577 | 0.007254 | 44 | 5612.3201 | 5612.3201
1958 | 6735 | STANISLAUS 1702L3151 | 0.0071849 | 3 | 1598.9081 | 1598.9081
1959 | 4931 | SAN LUIS OBISPO 1107V18 | 0.0070877 | 25 | 6444.7052 | 4192.834
1960 | 1719 | CLAY 110113450 | 0.0069792 | 7 | 7994.7686 | 553.6801
1961 | 7528 | CLARK ROAD 11022068 | 0.0068224 | 133 | 17243.1435 | 16704.4746
1962 | 875 | TEMPLETON 2108A64 | 0.0067619 | 30 | 19026.8995 | 3063.2438
1963 | 2786 | WILLOW PASS 1101circuit_breaker | 0.0067338 | 1 | 11299.6182 | 2388.9792
1964 | 2853 | MONTE RIO 111153477 | 0.006475 | 33 | 3299.3477 | 3299.3477
1965 | 3089 | BRUNSWICK 11032200 | 0.0064186 | 6 | 8965.9105 | 8965.9105
1966 | 6422 | BRUNSWICK 11064639 | 0.0063064 | 54 | 5228.1955 | 5228.1955
1967 | 8105 | SAN JOAQUIN #3 110110060 | 0.0062769 | 36 | 10431.3936 | 10431.3936
1968 | 5561 | BIG BASIN 110210254 | 0.0062684 | 3 | 3441.3015 | 3441.3015
1969 | 3755 | REEDLEY 11127240 | 0.0062313 | 1 | 43589.6697 | 1451.4793
1970 | 2382 | FORT BRAGG A 110235592 | 0.0061655 | 219 | 21272.3021 | 21272.3021
1971 | 588 | CURTIS 170356972 | 0.0061394 | 19 | 13676.594 | 13676.594
1972 | 6620 | OLEMA 11011686 | 0.0060761 | 15 | 8105.6577 | 1962.0765
1973 | 571 | SWIFT 2110XR332 | 0.0059967 | 176 | 79862.0317 | 79862.0317
1974 | 4977 | HAMILTON BRANCH 11012046 | 0.0059115 | 68 | 14788.0543 | 14724.19
1975 | 6143 | BRUNSWICK 110584480 | 0.0058678 | 12 | 7615.7819 | 7615.7819
1976 | 8802 | FRENCH GULCH 11011892 | 0.0058216 | 14 | 4073.3832 | 4073.3832
1977 | 8007 | SALT SPRINGS 2102L7283 | 0.0057393 | 15 | 1066.8481 | 1066.8481
1978 | 6703 | SALT SPRINGS 2102L491 | 0.005721 | 44 | 3564.5514 | 3564.5514
1979 | 9730 | UPPER LAKE 1101circuit_breaker | 0.0057175 | 2 | 1791.2622 | 1791.2622
1980 | 4028 | CURTIS 170565908 | 0.0056485 | 8 | 26938.5587 | 21139.8755
1981 | 8127 | FELTON 0401circuit_breaker | 0.0056399 | 7 | 4116.7901 | 3781.4684
1982 | 8537 | SALT SPRINGS 2102L485 | 0.0055534 | 14 | 1339.4234 | 1339.4234
1983 | 3288 | GRASS VALLEY 1101circuit_breaker | 0.0055392 | 9 | 4306.6032 | 1152.0117
1984 | 6394 | DUNBAR 1101234 | 0.0055044 | 48 | 20899.3931 | 10423.4842
1985 | 7554 | MENLO 11038982 | 0.0055001 | 69 | 7297.022 | 7297.022
1986 | 2783 | MENLO 11029110 | 0.0054599 | 10 | 15093.0142 | 1403.503
1987 | 7289 | SOBRANTE 1103circuit_breaker | 0.0054294 | 61 | 6918.9418 | 6759.5318
1988 | 8694 | DUNLAP 110239190 | 0.005362 | 14 | 2902.8014 | 2902.8014
1989 | 5658 | OAKLAND X 1106CR020 | 0.0053494 | 49 | 3933.9507 | 3933.9507
1990 | 3239 | SNEATH LANE 1106circuit_breaker | 0.0053163 | 20 | 9891.2145 | 3587.2513
1991 | 8152 | MORGAN HILL 21114461 | 0.0052714 | 24 | 3633.9489 | 3633.9489
1992 | 2406 | FOOTHILL 1102V06 | 0.0051532 | 4 | 10520.855 | 1798.9532
1993 | 639 | RINCON 1101580 | 0.005088 | 6 | 4616.0468 | 541.3735
1994 | 6941 | COVELO 1101536 | 0.0050437 | 6 | 35716.0554 | 15104.7289
1995 | 4763 | BIG RIVER 11013019 | 0.0050035 | 6 | 1511.0833 | 423.4937
1996 | 5710 | MORAGA 1103circuit_breaker | 0.0050018 | 22 | 10266.3997 | 1860.265
1997 | 7638 | OILFIELDS 1103N62 | 0.0049929 | 2 | 8948.1922 | 8948.1922
1998 | 2191 | IGNACIO 11011264 | 0.0049785 | 24 | 5420.1776 | 3308.6659
1999 | 7490 | PEORIA 1704877670 | 0.004915 | 23 | 10595.2996 | 10595.2996
2000 | 2692 | VOLTA 110153118 | 0.0049102 | 6 | 15490.2629 | 15490.2629
2001 | 7441 | STONE CORRAL 11107784F | 0.0048132 | 2 | 7654.6568 | 586.0706
2002 | 4579 | CAMBRIA 1101V76 | 0.0048118 | 47 | 31109.7165 | 29392.3861
2003 | 4193 | CAMP EVERS 210311056 | 0.0047209 | 23 | 2992.2228 | 2611.1508
2004 | 1160 | MERCED FALLS 1102circuit_breaker | 0.0046872 | 17 | 40596.6604 | 11883.3184
2005 | 3207 | STAFFORD 1101circuit_breaker | 0.0046746 | 18 | 19354.556 | 1888.1069
2006 | 5738 | JOLON 1102circuit_breaker | 0.0046139 | 5 | 38579.7369 | 36119.0128
2007 | 644 | MORAGA 1105circuit_breaker | 0.0046 | 85 | 17363.7462 | 9314.4848
2008 | 5636 | ROB ROY 210410954 | 0.0045989 | 116 | 11322.6315 | 11322.6315
2009 | 2897 | HICKS 2101XR162 | 0.0045734 | 8 | 15349.8178 | 1339.293
2010 | 146 | STANISLAUS 17026028 | 0.0045666 | 6 | 8608.783 | 8608.783
2011 | 7129 | OTTER 11012052 | 0.0045471 | 71 | 7777.1247 | 7777.1247
2012 | 7385 | MONTE RIO 111215401 | 0.0045303 | 14 | 1388.1732 | 1388.1732
2013 | 5134 | PETALUMA C 1108632 | 0.0045132 | 1 | 23698.3277 | 23698.3277
2014 | 3571 | HALF MOON BAY 11038089 | 0.0044539 | 55 | 4645.2114 | 4645.2114
2015 | 9056 | MC KEE 110870535 | 0.0043297 | 6 | 5288.7742 | 1019.3465
2016 | 9418 | IGNACIO 11011779 | 0.0042854 | 4 | 677.0293 | 385.9886
2017 | 4887 | BIG MEADOWS 21012474 | 0.0042833 | 92 | 13446.528 | 12716.7551
2018 | 194 | BRUNSWICK 1105733408 | 0.0042647 | 32 | 5559.4271 | 5559.4271
2019 | 621 | RACETRACK 170310870 | 0.0042644 | 21 | 4188.8092 | 3188.0176
2020 | 6119 | HOLLISTER 21054048 | 0.004208 | 56 | 44906.9277 | 26554.045
2021 | 1538 | SAN LUIS OBISPO 1101483444 | 0.0041987 | 17 | 8577.8019 | 2987.6026
2022 | 1086 | PLACER 110451732 | 0.0040665 | 8 | 13388.5594 | 825.7758
2023 | 2210 | WYANDOTTE 11101952 | 0.0040571 | 5 | 13999.1345 | 417.0111
2024 | 3041 | JOLON 11027070 | 0.0039947 | 1 | 26486.1632 | 6723.3881
2025 | 1783 | OTTER 110298036 | 0.0039864 | 56 | 14861.2597 | 14861.2597
2026 | 43 | MONTE RIO 11111703 | 0.0039854 | 4 | 2219.017 | 2219.017
2027 | 7613 | MORAGA 110531512 | 0.0039498 | 9 | 7423.6865 | 2816.3842
2028 | 6972 | FAIRVIEW 220799096 | 0.0039443 | 62 | 15921.3049 | 15872.9643
2029 | 3628 | TEMPLETON 2108A40 | 0.0039443 | 60 | 20682.9125 | 5903.9832
2030 | 7092 | HOLLISTER 21064004 | 0.0038995 | 51 | 32627.9425 | 12351.5176
2031 | 3309 | NEWBURG 11323425 | 0.0038956 | 5 | 2438.8597 | 360.086
2032 | 3496 | SOBRANTE 1102circuit_breaker | 0.0038248 | 150 | 16784.222 | 16784.222
2033 | 2645 | PENRYN 1106circuit_breaker | 0.00381 | 1 | 22408.5903 | 70.2637
2034 | 1778 | CABRILLO 1104circuit_breaker | 0.0037888 | 36 | 27422.4738 | 5579.5239
2035 | 7052 | MARIPOSA 2102594143 | 0.0037717 | 9 | 6649.2174 | 751.6885
2036 | 8903 | OTTER 11017611 | 0.0037516 | 38 | 7068.0362 | 7068.0362
2037 | 6525 | REDBUD 1101400 | 0.003704 | 13 | 1637.3642 | 1401.7515
2038 | 5592 | BEN LOMOND 04015206 | 0.0036692 | 6 | 11401.1639 | 11401.1639
2039 | 4355 | CALISTOGA 1102705 | 0.0035158 | 2 | 2007.629 | 320.3013
2040 | 9592 | ANNAPOLIS 1101circuit_breaker | 0.0035147 | 1 | 1058.7166 | 1058.7166
2041 | 816 | ROSSMOOR 110168920 | 0.0035139 | 92 | 11657.1969 | 9481.3207
2042 | 5641 | FAIRVIEW 2207P150 | 0.0034985 | 25 | 3652.8381 | 3652.8381
2043 | 3709 | MORRO BAY 110247584 | 0.0034617 | 34 | 15483.3273 | 14612.5687
2044 | 6889 | SAN RAFAEL 11071415 | 0.0033735 | 10 | 1913.2696 | 1054.2427
2045 | 8544 | LAS GALLINAS A 1105circuit_breaker | 0.0033698 | 5 | 3345.6946 | 658.6815
2046 | 8515 | SUMMIT 110249484 | 0.0033616 | 34 | 4326.7918 | 4326.7918
2047 | 5899 | JOLON 1103circuit_breaker | 0.003332 | 1 | 29651.7983 | 18381.2801
2048 | 7770 | MIRABEL 11021139 | 0.0032926 | 8 | 2923.0188 | 2923.0188
2049 | 1126 | STAFFORD 11011082 | 0.0032797 | 16 | 4959.0869 | 1691.5237
2050 | 7302 | POINT MORETTI 110136516 | 0.003279 | 69 | 6707.2903 | 6707.2903
2051 | 6326 | MIRABEL 11027347 | 0.0031997 | 1 | 1145.4102 | 1145.4102
2052 | 4948 | BURNEY 110297318 | 0.0031884 | 9 | 2272.8877 | 1004.5656
2053 | 4353 | SPENCE 1122circuit_breaker | 0.002984 | 3 | 84675.007 | 14788.6218
2054 | 688 | MERCED FALLS 11029460 | 0.0029607 | 52 | 14365.6775 | 14069.7042
2055 | 7628 | DEL MONTE 21042762 | 0.0029222 | 128 | 17774.3075 | 14335.4933
2056 | 1347 | TASSAJARA 2112circuit_breaker | 0.002912 | 3 | 2118.6497 | 219.0837
2057 | 7116 | PALMER 110198478 | 0.0028986 | 2 | 7936.2417 | 7555.738
2058 | 2475 | MIWUK 17028090 | 0.0028775 | 66 | 6478.2235 | 6478.2235
2059 | 6520 | OAKLAND D 1112CR192 | 0.0028762 | 32 | 6807.0507 | 3810.1619
2060 | 938 | PAUL SWEET 2106circuit_breaker | 0.0028044 | 52 | 22673.5975 | 8257.1442
2061 | 5401 | FROGTOWN 170236870 | 0.0027611 | 10 | 5012.9466 | 1179.9136
2062 | 5711 | OAKLAND K 1102circuit_breaker | 0.0027249 | 37 | 4723.266 | 4723.266
2063 | 8617 | POINT MORETTI 110135874 | 0.0026979 | 1 | 440.1765 | 440.1765
2064 | 6606 | BRUNSWICK 111063100 | 0.0026702 | 63 | 6591.8915 | 6591.8915
2065 | 2078 | LUCERNE 1106circuit_breaker | 0.0026676 | 23 | 5806.4035 | 2265.0742
2066 | 5977 | HORSESHOE 110450142 | 0.0026525 | 33 | 6580.4443 | 3538.232
2067 | 617 | LAURELES 11112020 | 0.0026408 | 383 | 53149.3291 | 53149.3291
2068 | 9034 | VOLTA 110280982 | 0.0026237 | 9 | 836.5231 | 836.5231
2069 | 5619 | DEL MONTE 21049500 | 0.0026112 | 71 | 10897.0354 | 9189.3701
2070 | 2859 | HALSEY 110176178 | 0.0026072 | 354 | 32534.9057 | 32534.9057
2071 | 420 | SAUSALITO 1101circuit_breaker | 0.002605 | 11 | 9339.6058 | 1238.4516
2072 | 1168 | PEORIA 170575274 | 0.0025458 | 8 | 5362.5182 | 450.4418
2073 | 4865 | PEORIA 17048040 | 0.0025193 | 18 | 41434.2849 | 11308.8739
2074 | 9055 | BRENTWOOD 210596324 | 0.002489 | 2 | 775.7684 | 775.7684
2075 | 3219 | CURTIS 170390320 | 0.0024817 | 10 | 44739.8635 | 44739.8635
2076 | 806 | PERRY 1101V74 | 0.0024806 | 46 | 8183.4097 | 6365.4334
2077 | 6524 | SAN ARDO 11017632 | 0.0024798 | 1 | 13067.8012 | 668.3905
2078 | 6376 | PINECREST 04011818 | 0.0024179 | 50 | 5092.2491 | 5011.2665
2079 | 2824 | FORT ROSS 11214947 | 0.0023862 | 1 | 16678.3963 | 16678.3963
2080 | 2873 | ROB ROY 210538430 | 0.0023689 | 63 | 21756.9518 | 8878.6769
2081 | 6722 | IGNACIO 1101circuit_breaker | 0.0023575 | 18 | 2942.811 | 2568.3258
2082 | 3405 | SAN RAFAEL 1107circuit_breaker | 0.0023541 | 72 | 12784.0174 | 7424.3496
2083 | 3230 | DIVIDE 110348160 | 0.0023472 | 13 | 21090.6373 | 4025.5628
2084 | 5230 | SAN RAFAEL 1108circuit_breaker | 0.00232 | 75 | 11921.7427 | 6729.9719
2085 | 1464 | SAN RAMON 2107circuit_breaker | 0.002314 | 6 | 14479.3454 | 477.5582
2086 | 7853 | VALLEY VIEW 1106P166 | 0.0022992 | 50 | 7343.1116 | 7008.3242
2087 | 5961 | BIG MEADOWS 2101circuit_breaker | 0.0022603 | 25 | 3325.4736 | 3325.4736
2088 | 9833 | HALF MOON BAY 11038920 | 0.0022494 | 1 | 185.7819 | 185.7819
2089 | 892 | TULE POWER HOUSE 1101circuit_breaker | 0.0022435 | 40 | 6363.6748 | 6363.6748
2090 | 6836 | STANISLAUS 17024905 | 0.0022314 | 1 | 3770.3669 | 3770.3669
2091 | 3733 | SARATOGA 1105LC14 | 0.0022075 | 142 | 17941.3763 | 15716.535
2092 | 5760 | 693441 | 0.0021602 | 63 | 6840.8929 | 6840.8929
2093 | 6134 | HALF MOON BAY 11036012 | 0.0021516 | 44 | 15443.639 | 8085.8325
2094 | 4796 | FRENCH GULCH 11021462 | 0.0021314 | 65 | 16468.3781 | 14444.9129
2095 | 8952 | circuit_breaker | 0.0021179 | 3 | 7084.2306 | 305.1807
2096 | 593 | BELL 111056214 | 0.0020797 | 3 | 10701.9064 | 144.7507
2097 | 6315 | FOOTHILL 1101549904 | 0.0020549 | 7 | 28248.1164 | 12017.3608
2098 | 5464 | ALLEGHANY 1101978 | 0.0020436 | 128 | 46962.403 | 17657.6918
2099 | 2837 | FOOTHILL 110299432 | 0.0020405 | 10 | 14110.2866 | 2389.4026
2100 | 1430 | ORO FINO 1101121988 | 0.0020276 | 243 | 29450.0073 | 29450.0073
2101 | 5225 | PIT NO 3 21011386 | 0.0019902 | 77 | 11052.9537 | 10692.089
2102 | 3027 | CAMBRIA 1101circuit_breaker | 0.0019654 | 21 | 19513.1402 | 9200.2096
2103 | 7253 | PANOCHE 11034008 | 0.0019557 | 45 | 56762.8241 | 56762.8241
2104 | 5645 | HOLLISTER 2102855412 | 0.0019318 | 37 | 54939.02 | 42101.5076
2105 | 7759 | SAUSALITO 11021268 | 0.0019131 | 42 | 8059.3403 | 8059.3403
2106 | 8935 | SUMMIT 110147786 | 0.0018891 | 24 | 2854.4871 | 2854.4871
2107 | 8753 | MIWUK 170236888 | 0.0018831 | 8 | 990.9397 | 990.9397
2108 | 9699 | WISE 110163199 | 0.001832 | 9 | 1501.4082 | 989.41
2109 | 4885 | ATASCADERO 1101A22 | 0.0018308 | 5 | 21047.1239 | 209.5535
2110 | 1876 | FROGTOWN 17016807 | 0.0018152 | 73 | 7647.5853 | 7647.5853
2111 | 2429 | ELECTRA 11026014 | 0.001812 | 42 | 8101.0669 | 8101.0669
2112 | 2075 | HALSEY 11025739 | 0.0018105 | 102 | 10731.8696 | 10731.8696
2113 | 6413 | GUALALA 1111887180 | 0.0017933 | 66 | 8802.6895 | 7924.3024
2114 | 1440 | PLACERVILLE 210619732 | 0.0017725 | 133 | 14586.2182 | 14586.2182
2115 | 5174 | TEMPLETON 2113A32 | 0.0017684 | 13 | 9517.7168 | 2317.4886
2116 | 2996 | LAS POSITAS 2108MR190 | 0.0017498 | 3 | 17286.4534 | 1015.7929
2117 | 3550 | PERRY 1101V88 | 0.0017422 | 15 | 5002.9541 | 1316.7813
2118 | 7364 | PEORIA 170413490 | 0.0017198 | 25 | 8715.5754 | 6383.5889
2119 | 1656 | CAMP EVERS 210312990 | 0.0016808 | 228 | 21722.1338 | 21722.1338
2120 | 1172 | FORT BRAGG A 1102418 | 0.0016397 | 228 | 22747.0574 | 21780.1498
2121 | 8970 | SAUSALITO 110284278 | 0.0016382 | 14 | 2442.5589 | 2267.2637
2122 | 7366 | BRUNSWICK 110765574 | 0.00163 | 3 | 2799.3607 | 445.925
2123 | 1875 | MORAGA 1104circuit_breaker | 0.0016097 | 247 | 34925.1276 | 22579.2249
2124 | 8427 | 86032 | 0.0016072 | 7 | 4656.0497 | 1615.684
2125 | 3611 | FRENCH GULCH 1101circuit_breaker | 0.0015939 | 20 | 3697.5337 | 3697.5337
2126 | 4947 | PAUL SWEET 21045394 | 0.0015572 | 240 | 24535.8062 | 23022.1384
2127 | 5356 | ANTLER 11011384 | 0.0015406 | 126 | 14649.7542 | 14263.9901
2128 | 4802 | WILLOW CREEK 11035012 | 0.0015097 | 166 | 17863.1995 | 17863.1995
2129 | 9976 | TOCALOMA 0241circuit_breaker | 0.0015073 | 1 | 26.5151 | 26.5151
2130 | 5312 | FORT BRAGG A 11013100 | 0.0014694 | 189 | 23696.4521 | 19614.6509
2131 | 6983 | HAMILTON BRANCH 110190334 | 0.0014232 | 27 | 5434.6472 | 5355.1369
2132 | 4927 | GREEN VALLEY 210112130 | 0.0013847 | 11 | 27999.4589 | 2080.1983
2133 | 5946 | PEORIA 170169124 | 0.0013731 | 13 | 4347.2792 | 4347.2792
2134 | 5149 | BAYWOOD 1101circuit_breaker | 0.0013693 | 8 | 46581.9622 | 6577.3472
2135 | 3784 | CORRAL 110275622 | 0.0013343 | 7 | 9209.8908 | 1424.9314
2136 | 575 | WEIMAR 11022038 | 0.0013147 | 202 | 21541.6585 | 21541.6585
2137 | 5747 | BEN LOMOND 0401circuit_breaker | 0.0013043 | 76 | 12506.4618 | 12506.4618
2138 | 58 | CAMBRIA 1102W50 | 0.0013024 | 6 | 5728.406 | 779.9345
2139 | 3271 | CAMP EVERS 21055146 | 0.0012694 | 87 | 9692.8148 | 9692.8148
2140 | 7700 | OTTER 1102circuit_breaker | 0.0012667 | 33 | 10718.1318 | 10537.6394
2141 | 4450 | VALLEY VIEW 1106circuit_breaker | 0.0012527 | 38 | 8094.566 | 5669.0772
2142 | 6609 | DEL MONTE 21042624 | 0.0012456 | 148 | 30794.7643 | 29790.8638
2143 | 8058 | DEL MONTE 210436720 | 0.0012372 | 82 | 12840.8619 | 9052.9085
2144 | 7978 | VACAVILLE 111112342 | 0.0012273 | 2 | 1698.7343 | 237.1733
2145 | 5648 | CAMP EVERS 210611044 | 0.0012239 | 101 | 19987.9543 | 12091.4268
2146 | 6797 | CAMP EVERS 210510786 | 0.0012064 | 78 | 7281.933 | 7281.933
2147 | 5624 | SOLEDAD 21027048 | 0.0011947 | 16 | 55321.9809 | 25828.9181
2148 | 5217 | FORT BRAGG A 11041316 | 0.0011755 | 183 | 22356.1761 | 21724.3712
2149 | 5667 | LAURELES 11122768 | 0.0011748 | 90 | 12981.6665 | 9769.2909
2150 | 2757 | EDENVALE 2107XR336 | 0.0011107 | 3 | 47480.5961 | 2932.2246
2151 | 1451 | SOBRANTE 1101circuit_breaker | 0.0011088 | 219 | 24837.5413 | 22159.2029
2152 | 1812 | BIG RIVER 11013002 | 0.0010741 | 112 | 13203.7302 | 11691.8924
2153 | 1763 | BOLINAS 11011064 | 0.0010656 | 6 | 7144.3316 | 546.0033
2154 | 2842 | UKIAH 1114544 | 0.0010548 | 7 | 16090.1587 | 423.9084
2155 | 6656 | SAUSALITO 11021224 | 0.0010547 | 7 | 5029.3503 | 1179.0057
2156 | 463 | BIG BASIN 11015028 | 0.0010466 | 73 | 7931.4866 | 7931.4866
2157 | 7115 | ROB ROY 210410298 | 0.0010109 | 154 | 21488.8231 | 17304.3139
2158 | 3409 | WEIMAR 1101circuit_breaker | 0.0010071 | 135 | 14826.071 | 14826.071
2159 | 923 | CAMP EVERS 210511384 | 0.00099352 | 61 | 6564.1653 | 6564.1653
2160 | 1912 | ROB ROY 210410930 | 0.00098475 | 19 | 18179.3508 | 1570.0142
2161 | 1532 | RINCON 1103472 | 0.00097903 | 43 | 7702.3079 | 4843.5768
2162 | 3384 | SERRAMONTE 110412705 | 0.00095184 | 1 | 9361.8914 | 414.5607
2163 | 3927 | DUNLAP 11037080 | 0.00095088 | 102 | 17013.9683 | 17013.9683
2164 | 632 | CAMP EVERS 210511004 | 0.00091536 | 71 | 6906.8406 | 6906.8406
2165 | 125 | CAMP EVERS 21055232 | 0.00090985 | 66 | 7297.0471 | 7297.0471
2166 | 4629 | CAMP EVERS 210574170 | 0.00089567 | 48 | 5724.1198 | 5724.1198
2167 | 2007 | SPRUCE 0401BR316 | 0.00088523 | 49 | 6628.9852 | 6628.9852
2168 | 1988 | SWIFT 2102circuit_breaker | 0.00086869 | 3 | 3757.8955 | 706.8877
2169 | 79 | SNEATH LANE 1107circuit_breaker | 0.00086849 | 9 | 6226.1953 | 1051.9745
2170 | 4445 | TEMPLETON 2113A30 | 0.00086582 | 3 | 2568.4452 | 401.1046
2171 | 4068 | LOS GATOS 110760092 | 0.00085793 | 149 | 15505.8611 | 15505.8611
2172 | 1279 | CURTIS 17028000 | 0.00081584 | 219 | 23052.1801 | 23052.1801
2173 | 1396 | CLAY 110184572 | 0.00080407 | 7 | 3629.8323 | 598.9234
2174 | 7300 | LLAGAS 21011451 | 0.00079564 | 17 | 14798.7124 | 9962.9329
2175 | 7288 | CAMP EVERS 210616000 | 0.00077994 | 37 | 6294.2005 | 3279.9189
2176 | 854 | FAIRVIEW 2207M501R | 0.00076101 | 32 | 7472.5685 | 3375.143
2177 | 1048 | DIAMOND SPRINGS 110699658 | 0.0007539 | 115 | 20441.9062 | 12193.3312
2178 | 6442 | CURTIS 17039210 | 0.00070741 | 7 | 37044.9289 | 37044.9289
2179 | 1588 | SARATOGA 1106LC24 | 0.00067446 | 121 | 18692.0591 | 12995.8406
2180 | 1796 | SANTA ROSA A 1104210 | 0.00066969 | 105 | 12743.9815 | 10547.5245
2181 | 4891 | WEIMAR 11012764 | 0.00066364 | 96 | 9841.7615 | 9841.7615
2182 | 3212 | CAMP EVERS 210310946 | 0.0006466 | 79 | 13670.8285 | 8744.1235
2183 | 9254 | PANOCHE 11034036 | 0.00063911 | 6 | 40363.4485 | 13306.7166
2184 | 5659 | OAKLAND K 1102CR014 | 0.00062696 | 149 | 16905.4788 | 16905.4788
2185 | 6856 | ELECTRA 1102circuit_breaker | 0.00061191 | 32 | 4216.8732 | 4216.8732
2186 | 8429 | BIG RIVER 1101954 | 0.00060716 | 109 | 26190.1183 | 23944.8021
2187 | 9142 | GUALALA 1111445166 | 0.00059806 | 73 | 14711.3731 | 9193.5626
2188 | 8206 | OTTER 1101circuit_breaker | 0.00059489 | 23 | 10779.267 | 9899.5429
2189 | 147 | SUMMIT 1102circuit_breaker | 0.00058732 | 21 | 1626.5971 | 1626.5971
2190 | 1253 | LOS GATOS 1107circuit_breaker | 0.00058642 | 191 | 25321.013 | 24420.9564
2191 | 1190 | SAN RAMON 2106circuit_breaker | 0.00056237 | 4 | 3629.0684 | 655.1911
2192 | 9933 | PEORIA 170492888 | 0.0005296 | 1 | 765.3621 | 400.6025
2193 | 6393 | PAUL SWEET 21025291 | 0.00051059 | 55 | 6995.8694 | 5450.0475
2194 | 2769 | HICKS 2101XR250 | 0.00050767 | 106 | 21684.167 | 12241.6477
2195 | 898 | WALDO 0402circuit_breaker | 0.00050542 | 33 | 8248.2932 | 4721.9877
2196 | 4963 | SUMMIT 11022302 | 0.00049113 | 12 | 2346.259 | 2346.259
2197 | 1259 | SARATOGA 1106LC22 | 0.00048633 | 120 | 13269.339 | 11864.1721
2198 | 6318 | STELLING 111060090 | 0.00048152 | 83 | 10542.2205 | 10215.1138
2199 | 5867 | POINT MORETTI 110139126 | 0.00047994 | 46 | 3614.1844 | 3614.1844
2200 | 2119 | SOBRANTE 1102L510R | 0.00046912 | 144 | 15693.2972 | 14977.7338
2201 | 429 | SARATOGA 1107LC26 | 0.00046741 | 96 | 9086.0614 | 9086.0614
2202 | 3806 | SOLEDAD 210242506 | 0.00046337 | 35 | 45403.9219 | 13203.3163
2203 | 6410 | WOODSIDE 11043583 | 0.00045963 | 39 | 4480.4665 | 4480.4665
2204 | 1229 | CURTIS 17039240 | 0.00045651 | 131 | 17593.4022 | 17593.4022
2205 | 3444 | CHESTER 1101circuit_breaker | 0.00045133 | 29 | 12954.421 | 3248.2591
2206 | 346 | CURTIS 170210940 | 0.00044499 | 135 | 17011.7556 | 13795.9366
2207 | 546 | BRUNSWICK 110750008 | 0.00042903 | 40 | 12726.754 | 3726.9612
2208 | 4148 | HALF MOON BAY 11038894 | 0.00041461 | 179 | 18161.0155 | 18016.3153
2209 | 3024 | PANOCHE 11034016 | 0.00040553 | 1 | 20623.7001 | 3776.8409
2210 | 4324 | OTTER 1101440 | 0.00040238 | 77 | 17663.1455 | 9356.989
2211 | 7211 | CAMP EVERS 210611006 | 0.00040085 | 27 | 3330.3404 | 3330.3404
2212 | 7829 | CUYAMA 1103622728 | 0.00039992 | 8 | 61732.6363 | 3818.1464
2213 | 5169 | ELK 11011300 | 0.00039907 | 19 | 15972.3198 | 2515.6031
2214 | 4545 | ROB ROY 210412596 | 0.00039621 | 103 | 17006.0385 | 11237.3875
2215 | 7519 | HALSEY 11015731 | 0.00039506 | 51 | 5029.6194 | 5029.6194
2216 | 421 | SOBRANTE 1102L520R | 0.00038981 | 120 | 12086.0128 | 11876.5417
2217 | 7508 | LOS GATOS 1106circuit_breaker | 0.00038737 | 93 | 12300.8206 | 10732.6188
2218 | 4486 | SAN RAFAEL 11081262 | 0.00038458 | 55 | 7151.9325 | 6212.9384
2219 | 488 | AUBURN 1101circuit_breaker | 0.00037547 | 49 | 7895.4706 | 5202.5567
2220 | 1735 | MONTE RIO 111264682 | 0.00037406 | 28 | 2767.8678 | 2767.8678
2221 | 7060 | RIO DELL 11028852 | 0.00037125 | 62 | 7652.3134 | 6733.2314
2222 | 2253 | LAURELES 11112028 | 0.00036929 | 139 | 14061.7847 | 14048.0686
2223 | 395 | REDBUD 1102922 | 0.00036705 | 82 | 12463.6383 | 12117.314
2224 | 2882 | LAKEWOOD 210769586 | 0.00036586 | 89 | 19693.5361 | 8401.1793
2225 | 7215 | WOODSIDE 11012299 | 0.00036334 | 32 | 2949.4431 | 2949.4431
2226 | 4979 | WOODSIDE 11018522 | 0.00035924 | 31 | 15127.8447 | 3168.3928
2227 | 9147 | DUNLAP 1102778286 | 0.00035677 | 8 | 4188.0047 | 4188.0047
2228 | 6385 | HALSEY 11026129 | 0.00035384 | 54 | 5155.4944 | 5155.4944
2229 | 7484 | MONTE RIO 1112212 | 0.00035327 | 35 | 3618.1726 | 3618.1726
2230 | 5252 | HATTON 110137088 | 0.00034905 | 121 | 18049.2001 | 10725.9565
2231 | 6293 | CURTIS 17058170 | 0.00034755 | 100 | 12664.7539 | 12248.0291
2232 | 2627 | LOS GATOS 1101LB40 | 0.00033789 | 121 | 14924.9203 | 13423.6309
2233 | 5099 | CAMP EVERS 2104circuit_breaker | 0.0003376 | 14 | 7159.1448 | 1223.0517
2234 | 548 | GREENBRAE 11021254 | 0.0003266 | 90 | 15162.3612 | 9494.3832
2235 | 5345 | GUALALA 1111circuit_breaker | 0.00032432 | 69 | 6218.5195 | 5963.2451
2236 | 1942 | LAURELES 111268454 | 0.00032188 | 134 | 17632.0929 | 12588.4111
2237 | 685 | SANTA ROSA A 1107circuit_breaker | 0.00032043 | 42 | 9899.1863 | 4761.8386
2238 | 8134 | POINT MORETTI 11015401 | 0.00031316 | 40 | 4092.0757 | 4092.0757
2239 | 16 | SAN RAFAEL 1106910 | 0.00031109 | 20 | 11732.4333 | 2037.0021
2240 | 7708 | LAURELES 111110141 | 0.00030603 | 52 | 4696.5789 | 4696.5789
2241 | 2347 | CAMP EVERS 21059031 | 0.00030583 | 19 | 1758.1932 | 1758.1932
2242 | 751 | LOS GATOS 1108LB86 | 0.00030371 | 65 | 8579.3653 | 7195.675
2243 | 3917 | LAURELES 1111circuit_breaker | 0.00030109 | 67 | 13157.523 | 11332.9679
2244 | 6320 | CAMP EVERS 21055577 | 0.00029517 | 18 | 1864.9283 | 1864.9283
2245 | 2265 | BEN LOMOND 040116010 | 0.0002939 | 17 | 2728.9115 | 2728.9115
2246 | 6805 | DEL MONTE 21032000 | 0.00029346 | 119 | 14596.6085 | 14596.6085
2247 | 2826 | MONTE RIO 11111701 | 0.0002839 | 26 | 2197.6127 | 2197.6127
2248 | 7676 | SARATOGA 11075696 | 0.00028323 | 86 | 9783.8788 | 8008.7281
2249 | 388 | WOODSIDE 11049032 | 0.0002828 | 28 | 12668.8794 | 6850.4288
2250 | 3631 | SHINGLE SPRINGS 210511172 | 0.0002814 | 30 | 3921.2737 | 3051.051
2251 | 3714 | CAMP EVERS 210355638 | 0.00027507 | 27 | 5626.2533 | 2080.9167
2252 | 4675 | CAMP EVERS 21035404 | 0.00027106 | 40 | 7424.9094 | 3769.8779
2253 | 1503 | HAMILTON BRANCH 1101circuit_breaker | 0.00026488 | 29 | 5887.1186 | 3577.0016
2254 | 5467 | CURTIS 170190120 | 0.00026162 | 40 | 8306.5424 | 4659.8125
2255 | 6909 | ORINDA 04013442 | 0.0002585 | 75 | 10746.159 | 7643.0559
2256 | 3862 | LOS GATOS 1106LA42 | 0.00025835 | 36 | 4461.918 | 4461.918
2257 | 814 | OAKLAND X 1104CR022 | 0.00025745 | 68 | 9630.8273 | 9630.8273
2258 | 6338 | HICKS 111660050 | 0.00025721 | 129 | 13194.2857 | 13194.2857
2259 | 8613 | POINT MORETTI 11015074 | 0.00025504 | 11 | 4855.8147 | 2072.4094
2260 | 9005 | FRENCH GULCH 1102circuit_breaker | 0.00025069 | 5 | 2729.0129 | 2729.0129
2261 | 4056 | ELK 11014628 | 0.00024953 | 35 | 6684.5064 | 3351.298
2262 | 6747 | BURNS 2101circuit_breaker | 0.00024938 | 25 | 2668.3535 | 2668.3535
2263 | 2962 | SAN RAFAEL 1101494 | 0.00023918 | 80 | 14793.4066 | 8677.8794
2264 | 4123 | TAR FLAT 0401circuit_breaker | 0.0002361 | 33 | 5901.3044 | 5449.6774
2265 | 2189 | HICKS 2103LB50 | 0.0002349 | 95 | 42653.2304 | 37268.0856
2266 | 6012 | HIGHLANDS 110448262 | 0.00023095 | 83 | 9974.1543 | 9900.0196
2267 | 2117 | HIGHLANDS 1104circuit_breaker | 0.00023075 | 71 | 13342.2829 | 7426.3873
2268 | 2600 | PERRY 1101V72 | 0.00022926 | 84 | 14179.1577 | 9688.7012
2269 | 1776 | HARTLEY 1101738 | 0.00022757 | 43 | 12990.0963 | 3766.2764
2270 | 4001 | LAURELES 11122142 | 0.00022649 | 82 | 15527.4179 | 12390.3415
2271 | 4306 | SHINGLE SPRINGS 11038752 | 0.00022468 | 28 | 2987.221 | 2895.0362
2272 | 3696 | LOS GATOS 1106LA46 | 0.00022468 | 30 | 2467.6552 | 2467.6552
2273 | 4230 | SANTA ROSA A 110432180 | 0.00022369 | 33 | 3870.5139 | 3607.4547
2274 | 5106 | CAMP EVERS 21061625 | 0.00022095 | 16 | 1453.5601 | 1453.5601
2275 | 3675 | HOLLISTER 210491424 | 0.00021979 | 3 | 14085.1454 | 430.1131
2276 | 5049 | MONTE RIO 11135026 | 0.00021968 | 28 | 2955.8477 | 2955.8477
2277 | 9266 | GREEN VALLEY 21016601 | 0.00021863 | 31 | 3063.6094 | 3063.6094
2278 | 6304 | MIWUK 170247143 | 0.00021775 | 57 | 7868.7696 | 7868.7696
2279 | 5237 | ANNAPOLIS 1101554 | 0.00021721 | 51 | 43657.3063 | 43657.3063
2280 | 3797 | FAIRVIEW 2207P304 | 0.0002151 | 35 | 10027.5804 | 8495.039
2281 | 6649 | MONTE RIO 1111506 | 0.00021443 | 18 | 1987.3505 | 1987.3505
2282 | 2238 | VOLTA 110185234 | 0.0002139 | 122 | 12197.7117 | 12197.7117
2283 | 6706 | FORT BRAGG A 1102816 | 0.00021262 | 35 | 4123.7572 | 3663.972
2284 | 5753 | BIG RIVER 11012183 | 0.0002117 | 34 | 4246.8638 | 4246.8638
2285 | 52 | CURTIS 170234426 | 0.00020941 | 58 | 11088.7783 | 7090.4475
2286 | 1418 | OAKLAND K 1104CR204 | 0.00020805 | 52 | 6584.4717 | 6584.4717
2287 | 8862 | CAMP EVERS 2106834583 | 0.00020649 | 14 | 972.7555 | 972.7555
2288 | 606 | HOLLISTER 21054724 | 0.00020605 | 10 | 42311.0841 | 7277.4055
2289 | 7583 | DIAMOND SPRINGS 110740353 | 0.00020552 | 23 | 4132.0541 | 2152.3519
2290 | 6059 | MONTE RIO 1113250 | 0.00020365 | 20 | 3942.5285 | 3942.5285
2291 | 717 | RADUM 1105MR282 | 0.00020274 | 51 | 10192.3583 | 4954.2228
2292 | 4302 | ROSSMOOR 1106circuit_breaker | 0.00020185 | 24 | 7735.3967 | 2246.1308
2293 | 260 | SARATOGA 110413314 | 0.00019847 | 46 | 18413.6994 | 4930.3505
2294 | 2181 | PAUL SWEET 2109circuit_breaker | 0.0001963 | 47 | 20163.9647 | 4486.5579
2295 | 726 | SAN RAFAEL 1104circuit_breaker | 0.0001956 | 48 | 16837.4541 | 5364.6138
2296 | 7580 | CAMP EVERS 210411048 | 0.00019504 | 16 | 2200.0004 | 1365.3169
2297 | 5281 | WEST POINT 11025357 | 0.0001938 | 42 | 5289.0317 | 5289.0317
2298 | 2971 | OAKLAND X 1104CR288 | 0.0001907 | 53 | 4410.6695 | 4410.6695
2299 | 3011 | ANTLER 1101circuit_breaker | 0.00018747 | 16 | 2574.4725 | 2574.4725
2300 | 3149 | ROB ROY 210512474 | 0.00018694 | 41 | 13639.2736 | 4762.2826
2301 | 2449 | GONZALES 11013094 | 0.00018099 | 12 | 25186.6794 | 5968.4042
2302 | 2184 | FORT BRAGG A 11021226 | 0.00017819 | 31 | 12668.4441 | 2760.5742
2303 | 3969 | LAS AROMAS 0401LA401R | 0.00017778 | 44 | 6361.0626 | 4766.0601
2304 | 4261 | RESERVATION ROAD 110222136 | 0.00017726 | 10 | 8902.7374 | 1694.8476
2305 | 1297 | PEORIA 17013186 | 0.00017543 | 54 | 15920.2864 | 15920.2864
2306 | 7098 | WILLOW CREEK 1103circuit_breaker | 0.00017537 | 17 | 6235.9798 | 6235.9798
2307 | 7992 | CAMP EVERS 21067603 | 0.00017516 | 15 | 1504.5923 | 1504.5923
2308 | 1339 | CAMP EVERS 21035402 | 0.00017336 | 32 | 10811.0731 | 3816.6305
2309 | 636 | KONOCTI 11084039 | 0.00017256 | 26 | 3707.395 | 2945.2304
2310 | 4368 | MIRABEL 1102206 | 0.00016639 | 25 | 20489.8622 | 2879.3705
2311 | 8089 | BIG RIVER 1101circuit_breaker | 0.00016498 | 21 | 3058.0721 | 2894.9274
2312 | 1411 | VIEJO 22019114 | 0.00016296 | 80 | 10947.6406 | 10880.685
2313 | 6159 | PLACER 1102circuit_breaker | 0.00016159 | 29 | 3361.7302 | 2698.3238
2314 | 4565 | BURNEY 110245984 | 0.00015943 | 72 | 7772.5624 | 7772.5624
2315 | 4672 | ROSSMOOR 11018132 | 0.00015929 | 46 | 5907.1746 | 4210.4765
2316 | 3894 | ROB ROY 210512584 | 0.00015787 | 37 | 19455.512 | 5377.6554
2317 | 661 | FLINT 110140666 | 0.00015593 | 19 | 4596.6688 | 1886.431
2318 | 7454 | FORT BRAGG A 1102circuit_breaker | 0.00015554 | 25 | 9307.747 | 2547.229
2319 | 4205 | BRUNSWICK 110633050 | 0.00015285 | 22 | 6143.4432 | 1491.043
2320 | 3558 | AUBURN 1102circuit_breaker | 0.00015203 | 23 | 11240.5926 | 1981.8221
2321 | 3836 | LAS AROMAS 04013342 | 0.00015188 | 37 | 3654.0283 | 3654.0283
2322 | 9057 | AUBURN 11028611 | 0.00015154 | 24 | 2944.6304 | 2944.6304
2323 | 6165 | BIG BASIN 11029741 | 0.0001492 | 12 | 1047.536 | 1047.536
2324 | 7979 | GUALALA 11124431 | 0.00014662 | 28 | 2379.9343 | 2212.4234
2325 | 7630 | BIG RIVER 11015065 | 0.0001462 | 28 | 3543.5774 | 3543.5774
2326 | 946 | SAN RAFAEL 110991742 | 0.00014567 | 35 | 13838.4275 | 6806.4298
2327 | 34 | CURTIS 17019230 | 0.00014484 | 24 | 5067.8425 | 3602.8642
2328 | 1711 | GUALALA 1111402866 | 0.00014421 | 27 | 2560.4032 | 2022.5208
2329 | 7834 | FRENCH GULCH 11011464 | 0.00014311 | 8 | 1371.4854 | 1371.4854
2330 | 8182 | CLARKSVILLE 210951744 | 0.00014301 | 14 | 2887.7792 | 1413.2019
2331 | 6033 | HATTON 11022010 | 0.00014188 | 44 | 6466.4829 | 6466.4829
2332 | 6936 | SAN CARLOS 11049052 | 0.00014052 | 69 | 8312.0915 | 7726.2126
2333 | 3632 | BRUNSWICK 11032784 | 0.00013833 | 24 | 24636.8737 | 23108.4794
2334 | 7585 | SARATOGA 1115LC20 | 0.0001379 | 45 | 7847.8028 | 4697.8741
2335 | 4106 | OAKLAND X 1104CR214 | 0.00013778 | 37 | 4637.1496 | 4637.1496
2336 | 1878 | SANTA ROSA A 110439786 | 0.00013219 | 18 | 10862.9994 | 1494.4367
2337 | 7223 | IGNACIO 1104450582 | 0.00013143 | 44 | 6790.6191 | 4879.3488
2338 | 2738 | HIGHLANDS 1102circuit_breaker | 0.0001303 | 57 | 11973.99 | 11973.99
2339 | 2779 | COTATI 1104circuit_breaker | 0.00012937 | 38 | 12365.6799 | 5446.6395
2340 | 613 | ROSSMOOR 1101L503R | 0.00012913 | 70 | 6929.1359 | 6929.1359
2341 | 6591 | HATTON 1102648928 | 0.00012861 | 51 | 7661.8083 | 5792.882
2342 | 3377 | PARADISE 11061212 | 0.00012857 | 9 | 9245.4248 | 9061.9313
2343 | 2588 | EAST QUINCY 1101circuit_breaker | 0.00012399 | 45 | 12858.9233 | 4164.7046
2344 | 4394 | SILVERADO 2105circuit_breaker | 0.00012123 | 10 | 7383.7458 | 958.0432
2345 | 2281 | ALTO 1124circuit_breaker | 0.00012115 | 30 | 11198.0443 | 3322.8701
2346 | 5808 | RACETRACK 17032553 | 0.00012024 | 17 | 3989.867 | 1162.4255
2347 | 3771 | HATTON 11012026 | 0.00011843 | 80 | 16427.734 | 7951.2018
2348 | 5893 | CAROLANDS 04049024 | 0.00011829 | 54 | 6139.8959 | 5539.7321
2349 | 2848 | PLACER 1101circuit_breaker | 0.0001174 | 20 | 12115.2189 | 1809.155
2350 | 6127 | OAKLAND X 1106CR008 | 0.00011646 | 67 | 7102.0164 | 7102.0164
2351 | 3919 | DOLAN ROAD 11013012 | 0.00011588 | 50 | 33632.5258 | 5235.0908
2352 | 5274 | PARADISE 1106circuit_breaker | 0.00011587 | 9 | 18810.8302 | 16790.7997
2353 | 3210 | RACETRACK 170310850 | 0.00011515 | 14 | 3044.989 | 927.6524
2354 | 5759 | BERESFORD 04039154 | 0.00011503 | 61 | 10532.6812 | 6496.7789
2355 | 959 | BRYANT 0402circuit_breaker | 0.00011321 | 34 | 12542.5322 | 3304.7718
2356 | 3322 | VIEJO 22029104 | 0.00011309 | 75 | 9586.0766 | 9288.626
2357 | 2696 | SUNOL 1101MR650 | 0.00011195 | 16 | 4248.3171 | 1692.8493
2358 | 9419 | GUALALA 1111498 | 0.00011045 | 30 | 4821.7264 | 3498.0819
2359 | 5914 | IGNACIO 11041290 | 0.00010987 | 44 | 18840.8428 | 5098.9497
2360 | 3727 | PUEBLO 2102698 | 0.00010945 | 2 | 26431.9074 | 187.7325
2361 | 1469 | SAN RAFAEL 1101circuit_breaker | 0.00010888 | 35 | 6823.6578 | 3967.8905
2362 | 629 | ALTO 1125935 | 0.00010814 | 40 | 5180.4035 | 5180.4035
2363 | 625 | DUNBAR 1101160 | 0.0001075 | 23 | 10698.4424 | 3768.8878
2364 | 7055 | HARRIS 11082062 | 0.00010748 | 30 | 8481.5172 | 2687.4494
2365 | 6462 | BRUNSWICK 11103907 | 0.0001073 | 17 | 1437.9091 | 1437.9091
2366 | 6914 | VIEJO 2203circuit_breaker | 0.00010652 | 43 | 5468.3648 | 4363.1693
2367 | 1431 | LOS OSITOS 21033010 | 0.0001064 | 5 | 49974.2997 | 49533.9507
2368 | 8373 | CAMP EVERS 2106circuit_breaker | 0.00010592 | 10 | 3738.5003 | 828.2056
2369 | 6732 | HOLLISTER 21044403 | 0.00010574 | 8 | 30234.2388 | 9894.6539
2370 | 3718 | OAKLAND X 1106CR006 | 0.00010551 | 46 | 5810.9825 | 5810.9825
2371 | 6991 | BIG BASIN 110165444 | 0.00010328 | 7 | 738.7266 | 738.7266
2372 | 2423 | OAKLAND K 1103CR188 | 0.00010113 | 52 | 5757.5465 | 5757.5465
2373 | 5153 | ROSSMOOR 1106L522R | 9.9712e-05 | 29 | 6797.2077 | 3036.9141
2374 | 5661 | BIG BASIN 11019773 | 9.9609e-05 | 9 | 724.7249 | 724.7249
2375 | 5199 | DIAMOND SPRINGS 1105circuit_breaker | 9.8799e-05 | 15 | 7563.6203 | 2499.6007
2376 | 5120 | SAN LEANDRO U 1109CR182 | 9.7458e-05 | 52 | 7762.1289 | 7762.1289
2377 | 4949 | RIDGE 0401circuit_breaker | 9.7348e-05 | 37 | 8526.2661 | 8312.8257
2378 | 4900 | EL CERRITO G 1112BR178 | 9.6974e-05 | 21 | 12825.8849 | 2290.0818
2379 | 791 | RESEARCH 210263274 | 9.6717e-05 | 22 | 18111.0729 | 2064.5249
2380 | 4978 | EDES 1112CR312 | 9.6253e-05 | 43 | 5884.5739 | 5725.9493
2381 | 1112 | SAN CARLOS 11039148 | 9.4639e-05 | 54 | 14673.9555 | 6379.4044
2382 | 4004 | GREENBRAE 1103circuit_breaker | 9.4432e-05 | 16 | 8367.7567 | 1165.1033
2383 | 1235 | PALO SECO 0401circuit_breaker | 9.2923e-05 | 47 | 7522.627 | 7450.9364
2384 | 8034 | SAN ARDO 11017094 | 9.262e-05 | 7 | 26905.8115 | 1399.194
2385 | 4524 | OAKLAND K 1104CR208 | 9.2599e-05 | 36 | 3895.4111 | 3895.4111
2386 | 8137 | STELLING 11102243 | 9.2395e-05 | 33 | 3010.4448 | 3010.4448
2387 | 2952 | PERRY 1101W52 | 9.1775e-05 | 36 | 6677.88 | 4757.9409
2388 | 5885 | PERRY 1101W12 | 9.1287e-05 | 38 | 10253.6179 | 5951.1009
2389 | 3285 | TASSAJARA 210812712 | 9.0181e-05 | 18 | 5358.1983 | 1348.3115
2390 | 6317 | HIGGINS 110432747 | 8.9903e-05 | 11 | 5641.6217 | 1932.2977
2391 | 474 | EL CERRITO G 1105circuit_breaker | 8.8216e-05 | 77 | 11881.4228 | 11881.4228
2392 | 4574 | RESEARCH 21029746 | 8.6735e-05 | 17 | 4518.0632 | 1130.0389
2393 | 6144 | ROB ROY 21049973 | 8.644e-05 | 14 | 921.5182 | 921.5182
2394 | 3681 | PAUL SWEET 210411074 | 8.5271e-05 | 24 | 4925.4583 | 4575.9781
2395 | 9412 | SHINGLE SPRINGS 2110circuit_breaker | 8.4988e-05 | 7 | 2054.39 | 1202.0334
2396 | 283 | OAKLAND X 1106circuit_breaker | 8.3841e-05 | 40 | 18897.8572 | 6219.7565
2397 | 9546 | PEORIA 170488630 | 8.3796e-05 | 3 | 1252.5971 | 1252.5971
2398 | 9182 | POINT MORETTI 110183716 | 8.3588e-05 | 13 | 4270.6499 | 3791.8733
2399 | 4813 | EDES 1112CR282 | 8.2382e-05 | 49 | 6573.0208 | 6573.0208
2400 | 3200 | SAN LEANDRO U 1109CR002 | 8.2117e-05 | 73 | 12468.7643 | 10902.831
2401 | 40 | WOODSIDE 1104555372 | 8.1294e-05 | 53 | 6600.4202 | 6600.4202
2402 | 6923 | ALTO 112265474 | 8.0874e-05 | 33 | 5874.8397 | 4236.5189
2403 | 8980 | OLEMA 110149756 | 7.8955e-05 | 10 | 9480.1738 | 1000.1369
2404 | 774 | OAKLAND K 1104CR210 | 7.869e-05 | 36 | 4546.547 | 4546.547
2405 | 817 | BRUNSWICK 110456468 | 7.8663e-05 | 10 | 9624.4245 | 8462.4654
2406 | 409 | PACIFICA 1102circuit_breaker | 7.8596e-05 | 9 | 10933.7049 | 430.7272
2407 | 5191 | OAKLAND K 1104CR206 | 7.8019e-05 | 20 | 2883.3047 | 2883.3047
2408 | 136 | MORRO BAY 1102W34 | 7.7636e-05 | 51 | 15381.6099 | 11103.8333
2409 | 550 | PACIFICA 110266732 | 7.7154e-05 | 11 | 4716.4418 | 1010.3488
2410 | 8223 | LOS GATOS 110160052 | 7.6598e-05 | 28 | 3109.1853 | 3109.1853
2411 | 8313 | BIG BASIN 11026219 | 7.6368e-05 | 14 | 1442.8917 | 1442.8917
2412 | 722 | SILVERADO 21051308 | 7.6068e-05 | 8 | 8622.7598 | 812.0716
2413 | 1173 | VIEJO 2204circuit_breaker | 7.5743e-05 | 30 | 6373.9064 | 3591.9838
2414 | 1765 | BERKELEY F 1103BR110 | 7.5657e-05 | 27 | 9087.9005 | 3020.133
2415 | 9623 | CAMP EVERS 210595394 | 7.5431e-05 | 4 | 797.3729 | 797.3729
2416 | 1701 | LOS GATOS 1101circuit_breaker | 7.5336e-05 | 25 | 6310.1881 | 2776.4398
2417 | 6149 | ROB ROY 210571630 | 7.5066e-05 | 15 | 2893.6341 | 1881.1605
2418 | 4378 | MORGAN HILL 2109XR246 | 7.487e-05 | 29 | 10729.6078 | 4044.708
2419 | 6115 | BAY MEADOWS 210257886 | 7.4545e-05 | 66 | 8466.0843 | 6347.2399
2420 | 1446 | BOLINAS 1101528 | 7.4186e-05 | 19 | 4938.4038 | 2645.4949
2421 | 4742 | SARATOGA 1103LC16 | 7.399e-05 | 31 | 8155.3412 | 6890.8055
2422 | 4592 | HARTLEY 110194178 | 7.3787e-05 | 28 | 6647.1964 | 3325.1898
2423 | 2056 | ROB ROY 210512586 | 7.3658e-05 | 17 | 10478.2508 | 2805.9717
2424 | 6433 | LAURELES 1112438 | 7.3616e-05 | 26 | 9219.1151 | 7535.0705
2425 | 524 | HIGHLANDS 110439458 | 7.2926e-05 | 15 | 8594.1592 | 1626.6223
2426 | 9573 | POINT MORETTI 110110722 | 7.175e-05 | 10 | 974.5061 | 974.5061
2427 | 4178 | EMERALD LAKE 04028872 | 7.1683e-05 | 45 | 9034.3623 | 7185.3167
2428 | 410 | RALSTON 1101circuit_breaker | 7.1265e-05 | 56 | 13656.4798 | 7097.0963
2429 | 9195 | OAKLAND X 1106CR266 | 7.0871e-05 | 18 | 1901.6084 | 1901.6084
2430 | 6665 | BRUNSWICK 1102940 | 7.0652e-05 | 12 | 5596.7061 | 1331.1883
2431 | 386 | BELMONT 11038958 | 6.9991e-05 | 40 | 9587.299 | 5350.191
2432 | 6764 | SAUSALITO 11021500 | 6.9038e-05 | 6 | 2046.0654 | 1851.8444
2433 | 6381 | SAN RAFAEL 110168970 | 6.855e-05 | 12 | 6755.3309 | 1316.5192
2434 | 1993 | HICKS 1116LB16 | 6.8402e-05 | 44 | 14726.4924 | 4954.2992
2435 | 5428 | LAURELES 11116617 | 6.7954e-05 | 24 | 2923.677 | 2923.677
2436 | 1047 | JARVIS 1101MR210 | 6.7445e-05 | 2 | 12482.1347 | 567.7092
2437 | 4496 | COTATI 1104426 | 6.7316e-05 | 21 | 6253.9916 | 3056.6341
2438 | 1360 | PACIFICA 110311153 | 6.6935e-05 | 15 | 14450.2027 | 1394.6966
2439 | 5148 | SAN RAFAEL 1105534 | 6.6803e-05 | 17 | 2541.7011 | 1383.1216
2440 | 4968 | STANISLAUS 17021850 | 6.6547e-05 | 12 | 21674.5076 | 21674.5076
2441 | 3454 | OAKLAND K 1104432850 | 6.6413e-05 | 22 | 1972.5088 | 1972.5088
2442 | 5387 | TAMARACK 1101circuit_breaker | 6.6001e-05 | 185 | 28848.3085 | 28053.5786
2443 | 9376 | GREENBRAE 11036083 | 6.5e-05 | 6 | 549.3456 | 549.3456
2444 | 249 | HICKS 1116circuit_breaker | 6.4663e-05 | 35 | 27431.6264 | 4776.7233
2445 | 3790 | SAN RAFAEL 11081457 | 6.4374e-05 | 11 | 1229.3805 | 1229.3805
2446 | 9322 | WEIMAR 11016139 | 6.3917e-05 | 9 | 997.9281 | 997.9281
2447 | 3744 | PURISIMA 1101circuit_breaker | 6.3885e-05 | 33 | 7381.7293 | 5755.7195
2448 | 8738 | LAURELES 11116421 | 6.3112e-05 | 26 | 2777.3682 | 2777.3682
2449 | 2168 | DEL MONTE 21032654 | 6.2951e-05 | 26 | 2963.5999 | 2963.5999
2450 | 2249 | OAKLAND K 1104CR326 | 6.0829e-05 | 16 | 2098.9601 | 2098.9601
2451 | 1814 | ALTO 1122circuit_breaker | 6.057e-05 | 24 | 5576.1236 | 3067.3601
2452 | 8366 | MIRABEL 11027401 | 6.0113e-05 | 7 | 1171.4888 | 1171.4888
2453 | 2000 | SAN LEANDRO U 1114MR218 | 5.977e-05 | 47 | 18069.0511 | 8791.3954
2454 | 1844 | HATTON 1102circuit_breaker | 5.9602e-05 | 31 | 7851.6881 | 3118.5334
2455 | 3591 | MONROE 210765424 | 5.9296e-05 | 10 | 8210.9441 | 1114.9522
2456 | 4871 | OAKLAND J 1102CR184 | 5.9089e-05 | 41 | 5568.9906 | 5568.9906
2457 | 63 | OAKLAND X 1105circuit_breaker | 5.8907e-05 | 31 | 23764.1022 | 3428.0095
2458 | 8050 | MORRO BAY 1102circuit_breaker | 5.8029e-05 | 21 | 8911.8848 | 5907.9517
2459 | 4930 | DEL MONTE 21049096 | 5.7473e-05 | 36 | 10640.4265 | 4576.3876
2460 | 3911 | CAMPHORA 110177978 | 5.6948e-05 | 6 | 40895.7342 | 3393.7443
2461 | 2622 | VALLEY VIEW 1105P190 | 5.5953e-05 | 49 | 9490.8504 | 4841.3798
2462 | 6508 | EMERALD LAKE 04028858 | 5.5314e-05 | 25 | 3073.6226 | 3073.6226
2463 | 4535 | KONOCTI 11084041 | 5.507e-05 | 15 | 7544.3878 | 1537.6241
2464 | 6806 | DEL MONTE 210332886 | 5.4976e-05 | 26 | 6355.8295 | 2565.9589
2465 | 8536 | OAKLAND K 1103CR422 | 5.4675e-05 | 25 | 3299.6109 | 3148.3595
2466 | 227 | PAUL SWEET 210612828 | 5.4579e-05 | 16 | 8000.0514 | 1804.684
2467 | 7396 | CURTIS 1702S2123 | 5.4139e-05 | 23 | 2995.553 | 2995.553
2468 | 6323 | VIEJO 2202circuit_breaker | 5.37e-05 | 28 | 3355.2545 | 3355.2545
2469 | 7699 | HATTON 1101circuit_breaker | 5.3559e-05 | 27 | 2553.7001 | 2553.7001
2470 | 5852 | VIEJO 22049540 | 5.3526e-05 | 25 | 3592.089 | 2249.934
2471 | 1865 | SAN BENITO 2104circuit_breaker | 5.3294e-05 | 19 | 14632.0755 | 7728.5813
2472 | 9138 | WILLOW CREEK 1101circuit_breaker | 5.2886e-05 | 3 | 437.858 | 437.858
2473 | 2216 | LAKEWOOD 210738404 | 5.2865e-05 | 20 | 9331.7159 | 3768.6783
2474 | 1380 | SAN RAFAEL 11061230 | 5.219e-05 | 18 | 9947.7927 | 1200.481
2475 | 8571 | BEN LOMOND 04015400 | 5.2063e-05 | 3 | 712.5707 | 712.5707
2476 | 7131 | FLINT 1101circuit_breaker | 5.1436e-05 | 8 | 4181.0836 | 831.0934
2477 | 2058 | CALISTOGA 1102706 | 5.0612e-05 | 4 | 8027.0476 | 636.0356
2478 | 9867 | BEAR VALLEY 2105circuit_breaker | 4.9797e-05 | 8 | 6175.4075 | 6175.4075
2479 | 6283 | BIG BASIN 11015479 | 4.9772e-05 | 3 | 274.045 | 274.045
2480 | 3426 | WOODSIDE 11049030 | 4.9768e-05 | 28 | 4149.4333 | 3145.1983
2481 | 6784 | RESERVATION ROAD 11023032 | 4.9503e-05 | 29 | 15612.677 | 4109.0682
2482 | 9752 | GREEN VALLEY 21011645 | 4.8671e-05 | 8 | 777.8514 | 777.8514
2483 | 1534 | SANTA ROSA A 1104circuit_breaker | 4.8652e-05 | 6 | 9705.5931 | 380.5489
2484 | 5708 | EAST QUINCY 11012452 | 4.8583e-05 | 31 | 13369.3596 | 2653.0626
2485 | 361 | ARCATA 112233060 | 4.7597e-05 | 9 | 7913.5825 | 701.4158
2486 | 695 | DEL MONTE 21042760 | 4.7457e-05 | 26 | 4362.4601 | 4362.4601
2487 | 69 | PACIFICA 11026783 | 4.7363e-05 | 13 | 10342.1784 | 2227.3024
2488 | 3926 | EDES 1112CR100 | 4.7361e-05 | 35 | 5399.0675 | 5399.0675
2489 | 7432 | UKIAH 111472990 | 4.7197e-05 | 12 | 5262.4562 | 1032.2982
2490 | 8715 | MONTICELLO 1101circuit_breaker | 4.6712e-05 | 7 | 898.3339 | 898.3339
2491 | 6622 | MIRABEL 11022043 | 4.626e-05 | 8 | 914.8961 | 914.8961
2492 | 25 | RALSTON 110148936 | 4.6028e-05 | 60 | 9693.4724 | 7442.666
2493 | 2447 | SAN CARLOS 11048846 | 4.5816e-05 | 28 | 7060.9917 | 3326.5951
2494 | 3517 | OAK 0401circuit_breaker | 4.4441e-05 | 39 | 8444.2886 | 5406.3145
2495 | 6644 | MORAGA 11017616 | 4.4308e-05 | 21 | 2295.5196 | 2295.5196
2496 | 1409 | TAR FLAT 0402circuit_breaker | 4.4286e-05 | 6 | 2350.4406 | 1258.5471
2497 | 1545 | ECHO SUMMIT 11012500 | 4.4048e-05 | 36 | 3502.0827 | 3502.0827
2498 | 289 | RIDGE 0402circuit_breaker | 4.3853e-05 | 21 | 3848.2536 | 2818.3373
2499 | 7684 | EMERALD LAKE 0402circuit_breaker | 4.2739e-05 | 21 | 3052.0291 | 3052.0291
2500 | 822 | MORRO BAY 1102W22 | 4.2718e-05 | 31 | 10102.1991 | 3676.1403
2501 | 7349 | FORT BRAGG A 1103circuit_breaker | 4.2712e-05 | 6 | 4315.8195 | 271.1874
2502 | 6768 | HATTON 11029642 | 4.2607e-05 | 25 | 1925.8934 | 1925.8934
2503 | 868 | EDES 1112CR308 | 4.258e-05 | 34 | 5683.4055 | 5048.7285
2504 | 995 | VIEJO 22019490 | 4.1862e-05 | 20 | 3484.3168 | 2513.194
2505 | 1202 | MORAGA 110381146 | 4.1627e-05 | 13 | 9024.5516 | 1121.0612
2506 | 308 | PAUL SWEET 2102circuit_breaker | 4.1604e-05 | 8 | 9537.1446 | 590.0954
2507 | 8711 | LAKEWOOD 2224568670 | 4.1529e-05 | 13 | 4298.0796 | 1334.4522
2508 | 1996 | LUCERNE 11031663 | 4.1497e-05 | 16 | 1947.6462 | 1947.6462
2509 | 6440 | VALLEY VIEW 1106P128 | 4.0465e-05 | 5 | 4067.7934 | 184.0685
2510 | 9013 | DOBBINS 1101circuit_breaker | 4.0462e-05 | 9 | 1079.0936 | 1079.0936
2511 | 8776 | COAST RD 04015134 | 4.0025e-05 | 2 | 4886.1695 | 465.4637
2512 | 4363 | FROGTOWN 170274648 | 3.9206e-05 | 10 | 8485.2437 | 1211.7571
2513 | 7788 | HALF MOON BAY 11038898 | 3.9145e-05 | 9 | 2052.6488 | 2052.6488
2514 | 9946 | MORAGA 110183424 | 3.9116e-05 | 14 | 2600.0484 | 2587.2467
2515 | 4616 | PETALUMA C 110948000 | 3.8478e-05 | 9 | 21371.2273 | 15185.5394
2516 | 1020 | GANSNER 110152664 | 3.7855e-05 | 20 | 7524.9818 | 1440.8216
2517 | 5186 | FULTON 1104466 | 3.7728e-05 | 3 | 2367.9813 | 626.0978
2518 | 5721 | SALT SPRINGS 21011232 | 3.7458e-05 | 91 | 14525.4003 | 10582.3145
2519 | 4764 | MONTE RIO 1113532 | 3.7235e-05 | 5 | 836.4221 | 836.4221
2520 | 4494 | EL CERRITO G 1105BR194 | 3.6977e-05 | 40 | 8523.5207 | 5780.6278
2521 | 2068 | SPRUCE 0402BR304 | 3.6767e-05 | 19 | 5836.8583 | 2445.8736
2522 | 8302 | MONTE RIO 1111circuit_breaker | 3.6511e-05 | 3 | 425.3264 | 425.3264
2523 | 369 | BERESFORD 0403circuit_breaker | 3.5731e-05 | 23 | 8781.4305 | 1971.1564
2524 | 671 | ROSSMOOR 110676468 | 3.5112e-05 | 10 | 4734.8645 | 812.7944
2525 | 8417 | BIG BASIN 110212779 | 3.5032e-05 | 3 | 407.3922 | 407.3922
2526 | 732 | GABILAN 11013034 | 3.4746e-05 | 2 | 33368.5845 | 558.7507
2527 | 6135 | PERRY 1101W10 | 3.4622e-05 | 17 | 2977.5841 | 1609.5516
2528 | 8305 | PEORIA 17046090 | 3.4541e-05 | 4 | 1284.821 | 1011.0046
2529 | 6876 | VIEJO 2201circuit_breaker | 3.4524e-05 | 19 | 8262.6752 | 8158.9016
2530 | 8385 | FRUITLAND 11418746 | 3.4329e-05 | 3 | 1353.7785 | 895.774
2531 | 4136 | SAN RAFAEL 1106837 | 3.355e-05 | 12 | 2472.1334 | 1084.0764
2532 | 2728 | RIO DELL 1102circuit_breaker | 3.3498e-05 | 7 | 11413.6327 | 655.8803
2533 | 5376 | SAN CARLOS 11048942 | 3.3394e-05 | 27 | 4451.9839 | 3376.0521
2534 | 7080 | CASTRO VALLEY 1108MR273 | 3.3274e-05 | 11 | 1166.5861 | 1166.5861
2535 | 8949 | MILPITAS 1109XR044 | 3.3191e-05 | 2 | 3013.9349 | 77.0548
2536 | 1306 | HOLLYWOOD 0401circuit_breaker | 3.2684e-05 | 21 | 8515.2971 | 4478.6501
2537 | 4303 | SAN RAFAEL 1105344 | 3.2584e-05 | 11 | 12052.7047 | 796.0448
2538 | 9640 | CAMP EVERS 210510996 | 3.1949e-05 | 2 | 1226.2093 | 1226.2093
2539 | 5792 | MORGAN HILL 2105circuit_breaker | 3.1829e-05 | 8 | 2881.8434 | 791.0708
2540 | 9245 | LAURELES 111184523 | 3.1778e-05 | 17 | 1964.6047 | 1964.6047
2541 | 5052 | BURNEY 1102circuit_breaker | 3.1325e-05 | 15 | 3204.0009 | 1949.5939
2542 | 792 | PEORIA 17019250 | 3.09e-05 | 12 | 13421.5992 | 13421.5992
2543 | 6675 | HALF MOON BAY 110148868 | 3.0794e-05 | 7 | 4759.8895 | 1128.5857
2544 | 7348 | BIG MEADOWS 21012510 | 3.0357e-05 | 50 | 14131.8875 | 6780.2402
2545 | 2319 | PACIFICA 11015001 | 3.0284e-05 | 5 | 8433.2827 | 1174.8636
2546 | 6763 | OAKLAND K 1101CR170 | 3.0072e-05 | 15 | 2012.9178 | 2012.9178
2547 | 3357 | CALISTOGA 1102circuit_breaker | 2.9949e-05 | 5 | 4507.3331 | 862.9478
2548 | 3669 | PARADISE 1104920400 | 2.9841e-05 | 3 | 25870.0682 | 7211.2587
2549 | 2603 | OAKLAND J 1106CR164 | 2.9647e-05 | 17 | 10525.9253 | 2328.9296
2550 | 645 | OAKLAND J 1102CR252 | 2.8758e-05 | 16 | 9897.4043 | 1754.2398
2551 | 4273 | VOLTA 11011516 | 2.8354e-05 | 2 | 41402.7558 | 39161.809
2552 | 8165 | BRUNSWICK 111094368 | 2.802e-05 | 3 | 768.9303 | 431.1432
2553 | 526 | ATASCADERO 11012379 | 2.7786e-05 | 13 | 1171.3689 | 1171.3689
2554 | 5028 | BERKELEY F 1105BR100 | 2.7683e-05 | 11 | 4175.3412 | 1156.966
2555 | 4812 | CASTRO VALLEY 1108circuit_breaker | 2.7611e-05 | 19 | 4549.646 | 2110.9437
2556 | 4550 | SNEATH LANE 110134438 | 2.7599e-05 | 24 | 8258.7197 | 2524.5868
2557 | 4110 | VALLEY VIEW 1106P176 | 2.722e-05 | 16 | 6680.3499 | 1598.933
2558 | 5179 | SOBRANTE 110142914 | 2.7113e-05 | 8 | 6646.8405 | 755.7626
2559 | 7418 | LUCERNE 11062355 | 2.6937e-05 | 5 | 1676.4836 | 560.2517
2560 | 4057 | VIEJO 22022606 | 2.678e-05 | 12 | 5106.4294 | 1139.9059
2561 | 9841 | BOGARD 1101circuit_breaker | 2.6759e-05 | 6 | 830.5012 | 830.5012
2562 | 1395 | PACIFICA 1103circuit_breaker | 2.6488e-05 | 3 | 7914.1245 | 224.0976
2563 | 364 | UKIAH 1114circuit_breaker | 2.618e-05 | 5 | 13996.69 | 555.5725
2564 | 4682 | ROB ROY 2105circuit_breaker | 2.5382e-05 | 6 | 2115.1186 | 778.4452
2565 | 2921 | STAFFORD 11011298 | 2.5155e-05 | 20 | 10849.9389 | 2037.2045
2566 | 839 | RINCON 1102644 | 2.5057e-05 | 6 | 16240.3737 | 652.5483
2567 | 8784 | BELL 110880680 | 2.5012e-05 | 6 | 2866.5185 | 685.5234
2568 | 6692 | SAN ARDO 110193072 | 2.4798e-05 | 1 | 13409.0058 | 1004.5467
2569 | 3462 | SEACLIFF 0402circuit_breaker | 2.4741e-05 | 4 | 2486.9473 | 417.7951
2570 | 4226 | NOVATO 11041282 | 2.4527e-05 | 8 | 7339.7437 | 722.7771
2571 | 1961 | MORAGA 1103E510R | 2.4247e-05 | 9 | 9824.475 | 662.3347
2572 | 7016 | SARATOGA 11076867 | 2.4211e-05 | 9 | 1327.3586 | 985.9493
2573 | 2419 | BERKELEY F 1105circuit_breaker | 2.4094e-05 | 10 | 12969.5675 | 1678.7947
2574 | 9664 | GARBERVILLE 11022124 | 2.3974e-05 | 1 | 5026.2322 | 5026.2322
2575 | 7363 | SALT SPRINGS 21014913 | 2.3974e-05 | 68 | 6222.6929 | 6222.6929
2576 | 7330 | ROSSMOOR 1102circuit_breaker | 2.3304e-05 | 7 | 2145.2785 | 400.2166
2577 | 957 | BRUNSWICK 1103circuit_breaker | 2.3194e-05 | 3 | 16287.3875 | 8459.5799
2578 | 1978 | SHINGLE SPRINGS 210851474 | 2.3182e-05 | 2 | 7519.049 | 394.2246
2579 | 7206 | MIRABEL 1102841 | 2.3148e-05 | 3 | 1089.713 | 1089.713
2580 | 4406 | VIEJO 220285904 | 2.2484e-05 | 13 | 3179.0036 | 1316.0449
2581 | 836 | SHINGLE SPRINGS 1104circuit_breaker | 2.2305e-05 | 3 | 3786.907 | 901.8218
2582 | 1081 | DEL MONTE 210386496 | 2.1926e-05 | 15 | 11778.9092 | 1909.93
2583 | 6355 | BIG MEADOWS 21012246 | 2.1909e-05 | 32 | 2937.4924 | 2937.4924
2584 | 2928 | TASSAJARA 210883368 | 2.1851e-05 | 3 | 8729.1235 | 128.9574
2585 | 195 | ARLINGTON 0401circuit_breaker | 2.1838e-05 | 8 | 6391.7678 | 973.3919
2586 | 6172 | FORT BRAGG A 110465894 | 2.1739e-05 | 4 | 1933.4215 | 322.1994
2587 | 3182 | OAKLAND K 1101circuit_breaker | 2.1619e-05 | 9 | 7652.923 | 1118.3767
2588 | 5355 | KONOCTI 11084037 | 2.1233e-05 | 9 | 2770.5432 | 1312.7691
2589 | 4129 | BRUNSWICK 1104circuit_breaker | 2.0939e-05 | 3 | 4755.5689 | 2663.6104
2590 | 3401 | 318 | 2.086e-05 | 22 | 18521.3174 | 2707.537
2591 | 193 | RIO DELL 11028768 | 2.0426e-05 | 5 | 8376.3931 | 449.1583
2592 | 5814 | OAKLAND J 1105CR256 | 2.0391e-05 | 16 | 2967.1612 | 1245.6022
2593 | 4698 | VALLEY VIEW 1103P160 | 2.0269e-05 | 6 | 11104.7995 | 868.2348
2594 | 9208 | FRANKLIN 1104P136 | 2.0133e-05 | 24 | 9481.7884 | 6756.6357
2595 | 4062 | SAN RAFAEL 11042651 | 2.0026e-05 | 8 | 1244.9562 | 1083.7544
2596 | 6441 | ECHO SUMMIT 11018922 | 1.994e-05 | 19 | 1790.6655 | 1790.6655
2597 | 226 | CAROLANDS 04049026 | 1.9518e-05 | 12 | 8105.233 | 1254.4036
2598 | 2851 | WAYNE 040175010 | 1.9423e-05 | 3 | 4201.0119 | 282.8935
2599 | 2408 | VIEJO 22029112 | 1.9151e-05 | 13 | 5823.4278 | 1129.5145
2600 | 2507 | FAIRVIEW 2207P148 | 1.9108e-05 | 6 | 7362.5215 | 1241.4753
2601 | 6857 | WEST POINT 1101L373 | 1.9067e-05 | 2 | 12006.0598 | 12006.0598
2602 | 7461 | DOLAN ROAD 110122158 | 1.9013e-05 | 6 | 18873.0319 | 274.4783
2603 | 1494 | HAMILTON BRANCH 110187784 | 1.8736e-05 | 27 | 2328.7215 | 2328.7215
2604 | 4097 | FAIRVIEW 2207P142 | 1.8718e-05 | 13 | 4934.9724 | 1449.2328
2605 | 9495 | HAMILTON BRANCH 110118205 | 1.8461e-05 | 22 | 6497.5751 | 3707.1238
2606 | 233 | LOS GATOS 1102circuit_breaker | 1.8234e-05 | 5 | 9572.3733 | 1766.8106
2607 | 9360 | 5060 | 1.8011e-05 | 4 | 1112.8921 | 477.3134
2608 | 9133 | SAN RAFAEL 11073323 | 1.7855e-05 | 3 | 214.7286 | 214.7286
2609 | 1040 | SAN LEANDRO U 1114MR545 | 1.7398e-05 | 23 | 7220.0264 | 3494.5659
2610 | 525 | STANISLAUS 170237278 | 1.7396e-05 | 3 | 10956.0145 | 10956.0145
2611 | 8605 | PURISIMA 110154728 | 1.7299e-05 | 3 | 7210.7913 | 1017.1008
2612 | 6777 | ATASCADERO 1102A26 | 1.7062e-05 | 4 | 11312.8173 | 1034.6974
2613 | 1354 | HARRIS 11084674 | 1.7028e-05 | 5 | 13045.0322 | 465.5681
2614 | 761 | PACIFICA 1104circuit_breaker | 1.6968e-05 | 6 | 6746.3425 | 1298.4065
2615 | 832 | STANISLAUS 170237276 | 1.6897e-05 | 3 | 18919.7774 | 18919.7774
2616 | 1605 | OAKLAND K 1101CR172 | 1.683e-05 | 7 | 3350.0951 | 572.872
2617 | 5764 | VIEJO 22019698 | 1.6676e-05 | 8 | 1448.8828 | 912.5815
2618 | 7828 | OAKLAND J 1102CR254 | 1.6443e-05 | 11 | 2477.3187 | 1602.2826
2619 | 8271 | MONTICELLO 110152910 | 1.6221e-05 | 4 | 5053.4949 | 3504.9565
2620 | 7692 | WOODSIDE 110411555 | 1.6131e-05 | 10 | 1379.9837 | 1379.9837
2621 | 9616 | RIO DELL 11027124 | 1.5991e-05 | 1 | 1081.3743 | 1081.3743
2622 | 7328 | SUMMIT 110148632 | 1.5794e-05 | 35 | 4368.1754 | 4368.1754
2623 | 7858 | SAN RAFAEL 11042235 | 1.5607e-05 | 4 | 1389.3312 | 240.5368
2624 | 7151 | EDES 1112CR306 | 1.5555e-05 | 10 | 1619.5833 | 1619.5833
2625 | 6087 | SAN RAFAEL 1101310 | 1.5432e-05 | 7 | 5721.8801 | 395.8699
2626 | 5172 | EEL RIVER 11033820 | 1.5374e-05 | 1 | 31973.6142 | 5191.5083
2627 | 181 | ESTUDILLO 0401circuit_breaker | 1.5252e-05 | 9 | 7573.1193 | 1368.0825
2628 | 2322 | OAKLAND X 1104circuit_breaker | 1.5234e-05 | 8 | 3923.3157 | 2011.6074
2629 | 3391 | LOS GATOS 110160136 | 1.4923e-05 | 7 | 9049.3039 | 461.7186
2630 | 4662 | ALTO 1125circuit_breaker | 1.4836e-05 | 8 | 3665.4999 | 831.7602
2631 | 6965 | LOS OSITOS 21027470 | 1.4564e-05 | 6 | 43864.2595 | 6032.2925
2632 | 2617 | CASTRO VALLEY 1104MR201 | 1.4518e-05 | 12 | 15418.7744 | 1973.7097
2633 | 3642 | SOBRANTE 1101L534R | 1.4182e-05 | 11 | 2992.4353 | 1291.9266
2634 | 9585 | OAKLAND J 1102CR102 | 1.4051e-05 | 10 | 846.0426 | 846.0426
2635 | 5032 | VIEJO 22029120 | 1.4029e-05 | 9 | 11893.6537 | 2530.9244
2636 | 7069 | DEL MONTE 210342226 | 1.393e-05 | 6 | 4032.3201 | 616.5067
2637 | 4320 | OAKLAND X 1101CR224 | 1.3889e-05 | 9 | 1751.285 | 791.862
2638 | 7806 | VIEJO 22029089 | 1.3679e-05 | 9 | 2685.7224 | 2193.9182
2639 | 5480 | OAKLAND K 1104circuit_breaker | 1.3549e-05 | 7 | 2362.6398 | 2362.6398
2640 | 4517 | HALF MOON BAY 1102circuit_breaker | 1.3323e-05 | 1 | 6459.405 | 168.7519
2641 | 3120 | STAFFORD 110242542 | 1.3245e-05 | 7 | 5615.2121 | 623.2409
2642 | 8330 | MONROE 210392868 | 1.321e-05 | 3 | 1827.1241 | 437.4753
2643 | 6333 | FORT ROSS 1121134 | 1.3181e-05 | 3 | 12995.1583 | 12414.5774
2644 | 5517 | FLORENCE 0401circuit_breaker | 1.3073e-05 | 7 | 4654.0755 | 996.0372
2645 | 9104 | DEL MONTE 21032204 | 1.3064e-05 | 6 | 592.6413 | 592.6413
2646 | 9727 | MONTE RIO 11135024 | 1.3054e-05 | 3 | 545.8664 | 545.8664
2647 | 3626 | CASTRO VALLEY 1101MR359 | 1.289e-05 | 10 | 14100.5025 | 1462.9174
2648 | 5085 | IGNACIO 1103circuit_breaker | 1.2791e-05 | 7 | 4294.5405 | 849.0798
2649 | 1136 | MORAGA 11058354 | 1.2775e-05 | 4 | 4982.0059 | 320.2661
2650 | 1251 | SANTA YNEZ 1104Y30 | 1.2702e-05 | 5 | 21907.9147 | 984.7789
2651 | 4825 | PAUL SWEET 210212850 | 1.2637e-05 | 3 | 6534.2586 | 1087.1798
2652 | 5223 | PACIFICA 1101circuit_breaker | 1.2515e-05 | 3 | 4340.9857 | 222.8126
2653 | 5207 | CAROLANDS 040484797 | 1.2405e-05 | 6 | 2172.9793 | 159.0147
2654 | 8763 | BIG MEADOWS 2101439 | 1.2258e-05 | 10 | 1501.1745 | 1041.6607
2655 | 737 | WALDO 0401circuit_breaker | 1.2192e-05 | 18 | 9140.627 | 2562.0667
2656 | 5023 | DIAMOND SPRINGS 1106circuit_breaker | 1.2109e-05 | 3 | 3624.8586 | 305.3669
2657 | 180 | CLEAR LAKE 110192870 | 1.2012e-05 | 3 | 29084.561 | 859.6824
2658 | 1985 | DUNLAP 11037170 | 1.1943e-05 | 42 | 8635.1099 | 8635.1099
2659 | 2481 | GONZALES 11033096 | 1.1589e-05 | 10 | 29023.6121 | 2007.6917
2660 | 6234 | VIEJO 22029118 | 1.1495e-05 | 8 | 4750.7038 | 903.5074
2661 | 8717 | ECHO SUMMIT 1101741586 | 1.1407e-05 | 9 | 1137.7952 | 1137.7952
2662 | 3646 | VALLEY VIEW 1105P126 | 1.1382e-05 | 14 | 3297.3508 | 1553.9705
2663 | 2563 | PRUNEDALE 11103716 | 1.1293e-05 | 4 | 21171.4707 | 500.9046
2664 | 5620 | SANTA YNEZ 1102320270 | 1.1269e-05 | 4 | 4497.6237 | 464.6996
2665 | 9061 | ECHO SUMMIT 1101344250 | 1.1161e-05 | 9 | 1668.1837 | 1299.2708
2666 | 3490 | LLAGAS 2106XR146 | 1.1152e-05 | 1 | 32678.168 | 2566.3115
2667 | 359 | PURISIMA 110149394 | 1.1028e-05 | 10 | 14100.597 | 1434.279
2668 | 1013 | ALTO 1123circuit_breaker | 1.1009e-05 | 8 | 9495.092 | 1041.5153
2669 | 4984 | MORRO BAY 1101W20 | 1.0985e-05 | 6 | 5996.2896 | 3169.5643
2670 | 6253 | HAMILTON BRANCH 11012082 | 1.0847e-05 | 15 | 4925.5933 | 2146.9459
2671 | 141 | CASTRO VALLEY 1108MR379 | 1.075e-05 | 11 | 2536.0701 | 1604.9824
2672 | 8192 | VIEJO 22029488 | 1.0687e-05 | 8 | 2122.5518 | 1141.9334
2673 | 2893 | WOODSIDE 11049116 | 1.068e-05 | 5 | 6807.6296 | 1213.0994
2674 | 8987 | CAMP EVERS 2103circuit_breaker | 1.0347e-05 | 2 | 190.6576 | 146.1912
2675 | 8323 | SAN CARLOS 110436864 | 1.0278e-05 | 5 | 1364.5515 | 812.4562
2676 | 7735 | SAUSALITO 1102410 | 1.026e-05 | 13 | 3495.0118 | 1900.8841
2677 | 7192 | WEST POINT 1101L2219 | 1.0153e-05 | 1 | 5487.8839 | 5487.8839
2678 | 3715 | HAMILTON BRANCH 11013049 | 9.984e-06 | 14 | 2682.1998 | 1766.4723
2679 | 7769 | BRUNSWICK 11038918 | 9.9772e-06 | 2 | 3457.885 | 2321.7397
2680 | 9058 | HIGHLANDS 110484640 | 9.9409e-06 | 3 | 1219.5259 | 569.7278
2681 | 5182 | ALHAMBRA 1105circuit_breaker | 9.8746e-06 | 9 | 3045.0722 | 1107.679
2682 | 4475 | HATTON 11022070 | 9.8727e-06 | 10 | 3077.1708 | 797.8151
2683 | 9863 | PIT NO 5 110190846 | 9.8611e-06 | 1 | 149.205 | 149.205
2684 | 391 | ROSSMOOR 1104circuit_breaker | 9.7642e-06 | 2 | 17858.6714 | 0
2685 | 9380 | HAMILTON BRANCH 11012436 | 9.7145e-06 | 9 | 2038.321 | 2038.321
2686 | 199 | LAS PULGAS 0401circuit_breaker | 9.705e-06 | 8 | 9719.2183 | 583.9042
2687 | 2012 | VASONA 1102circuit_breaker | 9.6881e-06 | 3 | 24792.446 | 282.6401
2688 | 4487 | PEORIA 170184318 | 9.6569e-06 | 4 | 16239.9493 | 16239.9493
2689 | 2103 | SARATOGA 1105circuit_breaker | 9.6344e-06 | 4 | 8763.0473 | 514.5552
2690 | 9899 | GRASS VALLEY 1103circuit_breaker | 9.5707e-06 | 1 | 191.1806 | 191.1806
2691 | 522 | SAN RAFAEL 1109418 | 9.5465e-06 | 3 | 19644.7624 | 8200.6281
2692 | 1695 | LAURELES 1112circuit_breaker | 9.49e-06 | 4 | 3818.0634 | 334.2836
2693 | 5396 | SNEATH LANE 1102circuit_breaker | 9.2723e-06 | 14 | 4044.2651 | 1789.3661
2694 | 418 | CASTRO VALLEY 1104MR236 | 9.1934e-06 | 15 | 13504.2844 | 1927.0653
2695 | 2509 | CASTRO VALLEY 1101MR204 | 8.9111e-06 | 5 | 4709.4304 | 232.9604
2696 | 5127 | SAN RAFAEL 1105circuit_breaker | 8.8044e-06 | 3 | 15578.3001 | 373.6826
2697 | 6801 | GANSNER 110199388 | 8.7699e-06 | 10 | 3580.3836 | 1047.5058
2698 | 8777 | WATERSHED 0402circuit_breaker | 8.5873e-06 | 2 | 1752.4587 | 0
2699 | 4756 | SAN LUIS OBISPO 1108circuit_breaker | 8.4411e-06 | 9 | 13627.7483 | 2912.0068
2700 | 9544 | CURTIS 170349746 | 8.3675e-06 | 3 | 601.9007 | 601.9007
2701 | 160 | CORONA 11034446 | 8.3481e-06 | 5 | 19753.849 | 734.2401
2702 | 7417 | CARMEL 0402circuit_breaker | 8.3381e-06 | 4 | 2329.9611 | 461.4011
2703 | 4391 | SOLEDAD 21017056 | 8.2761e-06 | 2 | 44962.8575 | 6257.9858
2704 | 5974 | SAN CARLOS 110479774 | 8.2424e-06 | 9 | 2604.2837 | 1093.2973
2705 | 8674 | POTTER VALLEY P H 1105circuit_breaker | 7.9052e-06 | 1 | 296.5288 | 296.5288
2706 | 3855 | MONTEREY 04022644 | 7.8719e-06 | 9 | 2300.473 | 887.4818
2707 | 543 | ALTO 112088190 | 7.6926e-06 | 5 | 5023.293 | 530.6966
2708 | 7645 | HOPLAND 1101circuit_breaker | 7.5621e-06 | 4 | 9884.04 | 1104.2357
2709 | 3013 | REDBUD 11022013 | 7.4332e-06 | 1 | 7412.4545 | 125.6367
2710 | 9617 | POTTER VALLEY P H 1104circuit_breaker | 7.3847e-06 | 1 | 158.6806 | 158.6806
2711 | 7001 | OAKLAND K 1101CR346 | 7.2223e-06 | 2 | 301.378 | 301.378
2712 | 3378 | OAKLAND K 1101CR178 | 7.2008e-06 | 3 | 529.8862 | 529.8862
2713 | 6006 | WOOD 0401circuit_breaker | 7.1979e-06 | 3 | 5314.1763 | 198.8033
2714 | 7486 | LOYOLA 1102LL12 | 7.1431e-06 | 2 | 9731.1646 | 176.3756
2715 | 5918 | HIGHLANDS 1102556 | 7.1087e-06 | 1 | 12171.5187 | 0
2716 | 3555 | FAIRMOUNT 0401circuit_breaker | 7.0236e-06 | 8 | 9236.8516 | 2166.002
2717 | 1757 | BERKELEY F 0402circuit_breaker | 6.9961e-06 | 4 | 3376.7149 | 226.0238
2718 | 8948 | MORGAN HILL 2105XR602 | 6.9545e-06 | 4 | 1368.2778 | 356.9004
2719 | 3318 | SARATOGA 1107circuit_breaker | 6.7959e-06 | 2 | 15770.6513 | 273.8424
2720 | 8718 | COARSEGOLD 2102383092 | 6.7782e-06 | 2 | 613.1926 | 613.1926
2721 | 6509 | SAN CARLOS 110475210 | 6.5906e-06 | 3 | 618.926 | 618.926
2722 | 5151 | FAIRVIEW 2207circuit_breaker | 6.5645e-06 | 3 | 8087.0352 | 267.7583
2723 | 2724 | EL CERRITO G 1112BR180 | 6.5228e-06 | 4 | 3108.6276 | 850.589
2724 | 4061 | GRASS VALLEY 1102circuit_breaker | 6.3417e-06 | 1 | 6752.0314 | 284.9196
2725 | 2515 | DEL MONTE 21042032 | 6.2748e-06 | 4 | 9676.4913 | 253.941
2726 | 3308 | GREENBRAE 1104751 | 6.2216e-06 | 4 | 5014.0519 | 342.6723
2727 | 4805 | MONTE RIO 1113652 | 6.1642e-06 | 1 | 2244.0392 | 2244.0392
2728 | 2043 | NEWBURG 11313446 | 6.1144e-06 | 1 | 13140.8369 | 0
2729 | 4981 | FOOTHILL 1101circuit_breaker | 5.9886e-06 | 2 | 35204.2801 | 18495.1348
2730 | 2647 | CR242 | 5.7634e-06 | 4 | 7226.0562 | 362.7025
2731 | 7531 | SAN LEANDRO U 1109CR284 | 5.7552e-06 | 8 | 1501.5898 | 1126.0171
2732 | 3434 | FLORENCE 0401CR220 | 5.6899e-06 | 3 | 2216.0779 | 350.2675
2733 | 7033 | VIEJO 220235388 | 5.6503e-06 | 4 | 727.2974 | 676.3797
2734 | 7332 | CARLOTTA 11214045 | 5.6253e-06 | 1 | 3179.9108 | 0
2735 | 3199 | OAKLAND J 1106CR330 | 5.552e-06 | 5 | 3874.576 | 845.057
2736 | 2118 | LAKEWOOD 2227W503R | 5.529e-06 | 2 | 12249.2617 | 121.8736
2737 | 6179 | HAMILTON BRANCH 110153192 | 5.5275e-06 | 10 | 3316.9892 | 1145.8186
2738 | 8049 | ROSSMOOR 110479146 | 5.431e-06 | 5 | 3498.2633 | 400.4315
2739 | 3662 | PALMER 1101M82 | 5.4252e-06 | 3 | 24210.9534 | 16759.4337
2740 | 4747 | CHESTER 11022564 | 5.3991e-06 | 21 | 3603.0114 | 3485.5234
2741 | 3736 | ALTO 1120500 | 5.1903e-06 | 3 | 5126.8034 | 498.0083
2742 | 1079 | VIEJO 22012064 | 5.0151e-06 | 3 | 1409.3976 | 1409.3976
2743 | 1182 | PUEBLO 210398394 | 4.8973e-06 | 1 | 3363.933 | 20.0123
2744 | 7309 | PETALUMA C 1109738866 | 4.897e-06 | 1 | 4335.7412 | 2889.9768
2745 | 2301 | MORGAN HILL 2106circuit_breaker | 4.877e-06 | 3 | 6109.6825 | 0
2746 | 7826 | SALT SPRINGS 21013116 | 4.7914e-06 | 13 | 1616.0372 | 1222.9143
2747 | 1286 | SOLEDAD 2101circuit_breaker | 4.6259e-06 | 4 | 23674.2161 | 1217.4718
2748 | 8436 | ROSSMOOR 110181770 | 4.6135e-06 | 1 | 2254.8682 | 0
2749 | 6898 | PACIFIC GROVE 04222614 | 4.6114e-06 | 3 | 3446.6772 | 283.1092
2750 | 5241 | PETALUMA C 1108600 | 4.557e-06 | 1 | 13922.7445 | 8142.768
2751 | 196 | OAKLAND K 1103circuit_breaker | 4.5348e-06 | 6 | 7913.1284 | 859.4149
2752 | 2660 | FORT ORD 210736596 | 4.5031e-06 | 8 | 20177.9536 | 6277.7799
2753 | 7824 | ROSSMOOR 11077311 | 4.3596e-06 | 1 | 1914.4116 | 0
2754 | 954 | DEL MONTE 110138582 | 4.288e-06 | 4 | 8603.6462 | 792.5912
2755 | 6918 | SUMMIT 110158642 | 4.2459e-06 | 13 | 3078.8651 | 3078.8651
2756 | 6973 | CLARKSVILLE 210619642 | 4.1877e-06 | 1 | 2579.2739 | 618.1955
2757 | 2445 | LOYOLA 110260082 | 4.0796e-06 | 1 | 6524.9258 | 51.5332
2758 | 7965 | SNEATH LANE 110715341 | 4.0413e-06 | 4 | 2071.5108 | 518.827
2759 | 5548 | SAN LEANDRO U 11149838 | 4.0295e-06 | 6 | 3949.4877 | 1189.5493
2760 | 8419 | MARIPOSA 210210250 | 4.0128e-06 | 2 | 66.9649 | 66.9649
2761 | 5970 | LAKEVILLE 1102530 | 3.9985e-06 | 1 | 8337.7277 | 291.9883
2762 | 9118 | SUMMIT 11016627 | 3.9853e-06 | 9 | 903.7825 | 903.7825
2763 | 5484 | STANISLAUS 170275348 | 3.8878e-06 | 1 | 8681.8427 | 8681.8427
2764 | 7161 | SAN LUIS OBISPO 1107circuit_breaker | 3.8471e-06 | 5 | 2726.7982 | 1569.1089
2765 | 10015 | CURTIS 170511790 | 3.6783e-06 | 1 | 22.8988 | 22.8988
2766 | 8825 | ECHO SUMMIT 1101481660 | 3.5979e-06 | 5 | 905.9644 | 778.9778
2767 | 2863 | EUREKA E 110435934 | 3.5303e-06 | 1 | 5459.9113 | 163.1504
2768 | 3063 | SAN RAFAEL 110648752 | 3.5154e-06 | 1 | 3711.6115 | 44.4852
2769 | 3113 | RED BLUFF 1105161818 | 3.4538e-06 | 1 | 7665.1166 | 275.1903
2770 | 9368 | CASTRO VALLEY 1106MR233 | 3.3768e-06 | 2 | 1023.3375 | 164.9976
2771 | 4052 | EL CERRITO G 1110circuit_breaker | 3.1983e-06 | 3 | 4384.063 | 376.2535
2772 | 6917 | SUMMIT 1101742 | 3.1154e-06 | 8 | 2091.8057 | 2091.8057
2773 | 7941 | 1943 | 3.0668e-06 | 1 | 1959.963 | 1959.963
2774 | 6845 | EL CERRITO G 111257953 | 3.0603e-06 | 2 | 1217.1907 | 188.8354
2775 | 7712 | FRANKLIN 1101P138 | 3.0467e-06 | 5 | 2470.0232 | 2364.7362
2776 | 3699 | EL CERRITO G 1112circuit_breaker | 3.0205e-06 | 3 | 10601.0269 | 510.801
2777 | 2371 | SAN LEANDRO U 1114MR544 | 3.0195e-06 | 4 | 10049.3013 | 1064.9351
2778 | 5793 | WOODSIDE 11028862 | 2.9632e-06 | 2 | 6135.6911 | 97.31
2779 | 440 | OCEANO 1105V44 | 2.9303e-06 | 3 | 1804.253 | 1004.1237
2780 | 6054 | MORGAN HILL 2111circuit_breaker | 2.8904e-06 | 3 | 4339.1173 | 461.9266
2781 | 745 | LAKEWOOD 1102circuit_breaker | 2.8887e-06 | 2 | 15408.0523 | 153.4063
2782 | 7726 | OAKLAND J 1105CR150 | 2.8833e-06 | 3 | 755.1885 | 288.2243
2783 | 3165 | VIEJO 22049098 | 2.7941e-06 | 4 | 9682.1971 | 444.1507
2784 | 7297 | BURNEY 110237284 | 2.7368e-06 | 2 | 527.4707 | 11.2633
2785 | 1646 | EL CERRITO G 1111circuit_breaker | 2.7259e-06 | 3 | 20306.9192 | 521.1606
2786 | 8203 | SUMMIT 110186658 | 2.722e-06 | 6 | 1077.6311 | 1026.4158
2787 | 4743 | 84764 | 2.667e-06 | 1 | 6974.5934 | 2403.7519
2788 | 2072 | CASTRO VALLEY 1106MR205 | 2.6646e-06 | 1 | 8740.8691 | 143.1328
2789 | 6996 | ATASCADERO 1101circuit_breaker | 2.5957e-06 | 1 | 3297.1528 | 491.5839
2790 | 1956 | CASTRO VALLEY 1101MR518 | 2.5951e-06 | 3 | 3163.325 | 621.9183
2791 | 2421 | HAMILTON BRANCH 110137436 | 2.5776e-06 | 8 | 3303.8601 | 951.9489
2792 | 2513 | SOLEDAD 21027562 | 2.4237e-06 | 2 | 12110.2794 | 2922.6853
2793 | 42 | OAKLAND J 1105153228 | 2.391e-06 | 2 | 6680.4391 | 241.8819
2794 | 4640 | WYANDOTTE 110213914 | 2.3732e-06 | 1 | 2833.7582 | 43.1117
2795 | 9978 | CLARKSVILLE 210551478 | 2.3484e-06 | 1 | 90.198 | 81.0541
2796 | 7483 | EAST QUINCY 11011319 | 2.3127e-06 | 2 | 1710.625 | 230.1059
2797 | 1269 | CARMEL 0405circuit_breaker | 2.2637e-06 | 1 | 4990.6238 | 58.7067
2798 | 1597 | SAN LUIS OBISPO 1105circuit_breaker | 2.2516e-06 | 1 | 5631.4463 | 67.4906
2799 | 9756 | SAN RAFAEL 11092213 | 2.2389e-06 | 1 | 689.8513 | 666.4301
2800 | 6362 | VALLEY VIEW 1106P180 | 2.1733e-06 | 1 | 3522.4569 | 133.4076
2801 | 6954 | VIEJO 22032634 | 2.1662e-06 | 1 | 2626.604 | 0
2802 | 59 | BAY MEADOWS 2102circuit_breaker | 2.1437e-06 | 1 | 11130.4877 | 5.118
2803 | 9222 | DEL MONTE 21043066 | 2.1312e-06 | 1 | 26.0345 | 26.0345
2804 | 7709 | MORAGA 110518396 | 2.1302e-06 | 1 | 1810.5654 | 125.7014
2805 | 638 | OAKLAND J 1105CR130 | 2.0529e-06 | 2 | 7851.3017 | 753.2352
2806 | 931 | STELLING 110913228 | 2.0361e-06 | 1 | 13588.5968 | 1453.4738
2807 | 71 | HILLSDALE 040485812 | 2.0339e-06 | 1 | 9120.3733 | 0
2808 | 2274 | VACAVILLE 1112circuit_breaker | 1.9678e-06 | 2 | 5210.2483 | 207.005
2809 | 542 | MC KEE 1103XR028 | 1.9085e-06 | 1 | 16781.1982 | 1085.7736
2810 | 4313 | MONTEREY 04012642 | 1.7668e-06 | 2 | 4201.7426 | 395.9249
2811 | 4623 | SNEATH LANE 11071277 | 1.7559e-06 | 2 | 3471.3767 | 61.1173
2812 | 10107 | BRUNSWICK 1104761310 | 1.7279e-06 | 1 | 43.1053 | 43.1053
2813 | 197 | PETALUMA C 1109270 | 1.7129e-06 | 1 | 12322.9722 | 2986.7863
2814 | 451 | HARTLEY 1102824 | 1.7033e-06 | 1 | 12575.4803 | 137.5107
2815 | 3585 | EDES 1112circuit_breaker | 1.6923e-06 | 2 | 2377.7015 | 342.8746
2816 | 1767 | MORGAN HILL 2105XR578 | 1.6459e-06 | 1 | 1108.6732 | 251.9162
2817 | 3167 | VALLEY VIEW 1105circuit_breaker | 1.6195e-06 | 2 | 7478.2552 | 104.2614
2818 | 1941 | RALSTON 11022028 | 1.6072e-06 | 1 | 3748.0499 | 2900.1535
2819 | 9477 | DUNLAP 11027290 | 1.5997e-06 | 11 | 1178.1007 | 1178.1007
2820 | 4020 | BURNEY 110257046 | 1.5962e-06 | 1 | 1135.0639 | 77.1037
2821 | 6816 | HICKS 111512494 | 1.4548e-06 | 1 | 4186.1864 | 84.655
2822 | 1645 | CASTRO VALLEY 1109circuit_breaker | 1.4293e-06 | 1 | 3040.0219 | 222.2939
2823 | 6710 | VIEJO 220292792 | 1.3174e-06 | 1 | 2455.5037 | 0
2824 | 2334 | VIEJO 22049110 | 1.2694e-06 | 1 | 6943.3735 | 20.6903
2825 | 2477 | EL CERRITO G 1113circuit_breaker | 1.2534e-06 | 2 | 6919.0978 | 336.063
2826 | 3597 | HOLLISTER 210441808 | 1.2376e-06 | 1 | 17500.5057 | 4.0767
2827 | 3814 | MORRO BAY 1102V84 | 1.2196e-06 | 1 | 15814.6457 | 101.4196
2828 | 8443 | FORT ORD 210637286 | 1.2096e-06 | 1 | 5924.4605 | 3227.6123
2829 | 9773 | ECHO SUMMIT 110155262 | 1.1835e-06 | 1 | 266.534 | 266.534
2830 | 7884 | OLEMA 110137074 | 1.182e-06 | 1 | 506.0081 | 21.9456
2831 | 1096 | SNEATH LANE 110168070 | 1.1253e-06 | 2 | 3445.6939 | 175.9556
2832 | 8392 | SOLEDAD 111435306 | 1.1231e-06 | 1 | 11463.1003 | 1328.8876
2833 | 9984 | PINECREST 0401circuit_breaker | 1.0532e-06 | 1 | 20.6165 | 20.6165
2834 | 1652 | OAKLAND J 1118CR198 | 1.0225e-06 | 1 | 8427.7397 | 515.4771
2835 | 1275 | BANCROFT 0402circuit_breaker | 8.6008e-07 | 2 | 7332.1581 | 149.8171
2836 | 5537 | SUMMIT 110148636 | 8.2218e-07 | 2 | 4495.7508 | 42.0553
2837 | 476 | SNEATH LANE 110210255 | 8.1308e-07 | 1 | 4666.4719 | 0
2838 | 5474 | SAN LUIS OBISPO 1102597518 | 7.779e-07 | 1 | 3448.5717 | 881.7949
2839 | 5766 | LAS GALLINAS A 11041220 | 7.2609e-07 | 1 | 7696.9362 | 0
2840 | 5600 | LAS GALLINAS A 11051218 | 7.2039e-07 | 1 | 3755.6182 | 60.2784
2841 | 4257 | OCEANO 1103V22 | 6.989e-07 | 1 | 2481.8109 | 1804.8041
2842 | 342 | ALHAMBRA 1102circuit_breaker | 6.8369e-07 | 1 | 9246.0524 | 306.9084
2843 | 4836 | SOLEDAD 21027008 | 6.7393e-07 | 1 | 29112.5788 | 3543.9744
2844 | 486 | BELMONT 11109090 | 6.5519e-07 | 1 | 4185.121 | 0
2845 | 6261 | SNEATH LANE 110275844 | 5.6516e-07 | 1 | 865.0219 | 184.0425
2846 | 9903 | INDIAN FLAT 11044440 | 5.6405e-07 | 1 | 376.2849 | 376.2849
2847 | 2576 | DEL MONTE 21029060 | 5.0594e-07 | 1 | 16709.22 | 1038.0388
2848 | 5702 | SNEATH LANE 1101circuit_breaker | 4.451e-07 | 1 | 1546.1502 | 448.9693
2849 | 4237 | BELMONT 11038956 | 3.607e-07 | 2 | 2231.1917 | 228.0716
2850 | 5682 | CHESTER 1102circuit_breaker | 3.2158e-07 | 2 | 5127.9433 | 460.5923
2851 | 1305 | BELMONT 111039182 | 3.1284e-07 | 1 | 3455.5413 | 111.8017
2852 | 9662 | SCE TEHACHAPI 1101circuit_breaker | 0 |  | 1862.134 | 1862.134
2853 | 9337 | POTTER VALLEY P H 1105990354 | 0 |  | 6.5127 | 6.5127
2854 | 9400 | POSO MOUNTAIN 2103circuit_breaker | 0 |  | 3720.379 | 3720.379
2855 | 9410 | DUNBAR 110113481 | 0 |  | 1675.6333 | 0
2856 | 10158 | DIABLO CANYON 1101circuit_breaker | 0 |  | 0 | 0
2857 | 10118 | WASHINGTON CITY GEN. 11011101/2 | 0 |  | 5.7117 | 5.7117
2858 | 9588 | PLACERVILLE 1109circuit_breaker | 0 |  | 35.0819 | 25.9925
2859 | 9209 | WYANDOTTE 110366146 | 0 |  | 252.3083 | 252.3083
2860 | 10123 | OAKHURST 110310723 | 0 |  | 6.3415 | 6.3415
2861 | 9704 | EL CERRITO G 1105BR164 | 0 |  | 91.5845 | 91.5845
2862 | 9683 | PASO ROBLES 1103N02 | 0 |  | 70.9341 | 70.9341
2863 | 9681 | PASO ROBLES 1103451760 | 0 |  | 82.4454 | 82.4454
2864 | 9663 | STAFFORD 1102784704 | 0 |  | 43.8835 | 43.8835
2865 | 9594 | WYANDOTTE 11102590 | 0 |  | 928.8641 | 0
2866 | 10125 | NARROWS 2104circuit_breaker | 0 |  | 4.572 | 4.572
2867 | 9578 | POSO MOUNTAIN 21011703 | 0 |  | 3949.1387 | 1455.5285
2868 | 10128 | SIERRA CITY GEN 11011101/2 | 0 |  | 8.5137 | 8.5137
2869 | 9561 | DOWNIEVILLE DIESEL 1101circuit_breaker | 0 |  | 36.9839 | 36.9839
2870 | 9654 | KANAKA 11011036 | 0 |  | 979.1369 | 979.1369
2871 | 9340 | FULTON 110258990 | 0 |  | 901.0393 | 0
2872 | 9347 | CMC 1101circuit_breaker | 0 |  | 3293.5334 | 3293.5334
2873 | 9625 | CALPINE 1144962 | 0 |  | 63.3636 | 63.3636
2874 | 10133 | CALPINE 1146394G | 0 |  | 18.1683 | 18.1683
2875 | 9393 | CLAYTON 22159765 | 0 |  | 1507.3257 | 425.4979
2876 | 9648 | FORT ORD 21069658 | 0 |  | 156.0125 | 156.0125
2877 | 9403 | SALT SPRINGS 21023118 | 0 |  | 115.8501 | 115.8501
2878 | 10152 | CAMP EVERS 2105BL 2101 | 0 |  | 5.191 | 5.191
2879 | 9646 | CEDAR CREEK 11011362 | 0 |  | 24.9515 | 24.9515
2880 | 9344 | SPAULDING 1101circuit_breaker | 0 |  | 56.7484 | 56.7484
2881 | 9928 | SIERRA CITY GEN 1101circuit_breaker | 0 |  | 21.2814 | 21.2814
2882 | 9904 | BUELLTON 110163389 | 0 |  | 391.5938 | 0
2883 | 9905 | MILPITAS 110962157 | 0 |  | 72.1015 | 72.1015
2884 | 9906 | PETALUMA C 1109373772 | 0 |  | 28.6691 | 28.6691
2885 | 9918 | 188426 | 0 |  | 4.572 | 4.572
2886 | 10077 | HIGHLANDS 1101circuit_breaker | 0 |  | 42.5019 | 42.5019
2887 | 9927 | WILDWOOD 1101circuit_breaker | 0 |  | 96.3625 | 96.3625
2888 | 10074 | DOWNIEVILLE DIESEL 11011101/2 | 0 |  | 15.6648 | 15.6648
2889 | 10071 | CALPINE 1144276-G | 0 |  | 23.7478 | 23.7478
2890 | 10038 | ECHO SUMMIT 1101circuit_breaker | 0 |  | 49.1761 | 49.1761
2891 | 9450 | CLARKSVILLE 2103circuit_breaker | 0 |  | 2324.8024 | 239.3697
2892 | 9937 | PASO ROBLES 1103N04 | 0 |  | 858.0287 | 858.0287
2893 | 9948 | OAKLAND X 1104CR101 | 0 |  | 28.3921 | 28.3921
2894 | 9963 | CMC 1102circuit_breaker | 0 |  | 590.8612 | 590.8612
2895 | 9986 | CALPINE 1146200-G | 0 |  | 13.7161 | 13.7161
2896 | 10004 | WASHINGTON CITY GEN. 1101circuit_breaker | 0 |  | 20.3534 | 20.3534
2897 | 9987 | GOLDTREE 1105551904 | 0 |  | 35.7177 | 35.7177
2898 | 9995 | POINT MORETTI 1101circuit_breaker | 0 |  | 20.574 | 20.574
2899 | 9990 | FORT ORD 21069656 | 0 |  | 188.9883 | 188.9883
2900 | 9275 | MONTICELLO 11011780 | 0 |  | 105.9265 | 105.9265
2901 | 9439 | TASSAJARA 21123202 | 0 |  | 628.2778 | 628.2778
2902 | 9721 | SAN LUIS OBISPO 1107V08 | 0 |  | 39.9511 | 39.9511
2903 | 9989 | SCE REFUGIO 1101circuit_breaker | 0 |  | 3.6129 | 3.6129
2904 | 9519 | PETALUMA C 1109664732 | 0 |  | 1437.8147 | 1437.8147
2905 | 9735 | BERKELEY F 1105BR166 | 0 |  | 61.4345 | 61.4345
2906 | 10114 | NARROWS 21052214 | 0 |  | 4.5721 | 4.5721
2907 | 9758 | CALISTOGA 110266730 | 0 |  | 1883.757 | 1883.757
2908 | 9770 | MIWUK 170179118 | 0 |  | 31.1564 | 31.1564
2909 | 9776 | SAN RAMON 2102circuit_breaker | 0 |  | 3412.1639 | 2478.2008
2910 | 9794 | HARTLEY 110158095 | 0 |  | 251.9158 | 251.9158
2911 | 9714 | SAN CARLOS 11049048 | 0 |  | 24.5909 | 24.5909
2912 | 9803 | SUNOL 110148180 | 0 |  | 25.1925 | 13.6404
2913 | 9441 | ELK CREEK 1101circuit_breaker | 0 |  | 130.7379 | 130.7379
2914 | 9502 | CORNING 110135974 | 0 |  | 1338.0934 | 114.0493
2915 | 10104 | KESWICK 1101circuit_breaker | 0 |  | 26.6683 | 26.6683
2916 | 9837 | CASTRO VALLEY 11087742 | 0 |  | 4.5721 | 4.5721
2917 | 9490 | circuit_breaker | 0 |  | 168.4127 | 168.4127
2918 | 9849 | FLINT 1102circuit_breaker | 0 |  | 149.4178 | 149.4178
2919 | 10095 | CALPINE 1144304 | 0 |  | 74.6067 | 74.6067
2920 | 9864 | CALPINE 1144962 | 0 |  | 6465.1165 | 6465.1165
2921 | 3576 | SONOMA 1107294 | 0 |  | 14846.705 | 321.4105
2922 | 4154 | BRUNSWICK 110378862 | 0 |  | 2157.7055 | 423.5836
2923 | 4130 | SONOMA 1104914376 | 0 |  | 11215.1853 | 702.83
2924 | 4117 | GABILAN 11013722 | 0 |  | 30859.7242 | 1147.7092
2925 | 3874 | LOS OSITOS 21037082 | 0 |  | 33004.0765 | 1889.198
2926 | 3835 | PETALUMA C 1109circuit_breaker | 0 |  | 7864.725 | 1526.3367
2927 | 3767 | COTTONWOOD 1103circuit_breaker | 0 |  | 18019.9627 | 1201.9482
2928 | 3647 | SARATOGA 1103LC82 | 0 |  | 3440.1789 | 4.8945
2929 | 3602 | LAS GALLINAS A 1107554 | 0 |  | 4418.1736 | 200.8758
2930 | 3577 | KERN OIL 11063301 | 0 |  | 52237.9858 | 657.9886
2931 | 4206 | WYANDOTTE 11095973 | 0 |  | 3972.7876 | 0
2932 | 3553 | WOODSIDE 1104circuit_breaker | 0 |  | 11969.1918 | 246.681
2933 | 3532 | GREEN VALLEY 210190860 | 0 |  | 29488.5794 | 5419.4084
2934 | 3390 | OILFIELDS 11037006 | 0 |  | 24239.8026 | 5321.5914
2935 | 3286 | FORT BRAGG A 110436526 | 0 |  | 10589.3182 | 19.7226
2936 | 3245 | LLAGAS 2101XR244 | 0 |  | 22757.8317 | 321.7387
2937 | 3225 | MONTICELLO 11011589 | 0 |  | 6934.0024 | 6934.0024
2938 | 3104 | COTATI 1103252 | 0 |  | 9654.7077 | 0
2939 | 3048 | KIRKER 2104circuit_breaker | 0 |  | 16836.6678 | 74.5132
2940 | 3036 | PETALUMA C 1108630 | 0 |  | 6902.9174 | 2581.7965
2941 | 4723 | OCEANO 1105V48 | 0 |  | 4102.8714 | 142.1722
2942 | 5253 | MADISON 11057712 | 0 |  | 48161.6451 | 630.6114
2943 | 5219 | HARTLEY 1101471 | 0 |  | 2001.813 | 134.4299
2944 | 5196 | TASSAJARA 2109circuit_breaker | 0 |  | 3123.8712 | 1458.9789
2945 | 5181 | SAN LUIS OBISPO 1104circuit_breaker | 0 |  | 11106.7457 | 889.5466
2946 | 5152 | OROSI 11027948F | 0 |  | 13674.0277 | 423.4544
2947 | 5126 | STANISLAUS 1702L611 | 0 |  | 4813.9395 | 4813.9395
2948 | 5100 | MC ARTHUR 110137344 | 0 |  | 14267.9902 | 181.3406
2949 | 4873 | FRANKLIN 1104circuit_breaker | 0 |  | 8418.0901 | 233.9749
2950 | 4784 | BERKELEY T 0404circuit_breaker | 0 |  | 1941.7529 | 6.096
2951 | 3019 | SARATOGA 1103LC40 | 0 |  | 3059.9258 | 438.1448
2952 | 4721 | ALHAMBRA 110213333 | 0 |  | 480.3389 | 130.2273
2953 | 4674 | RALSTON 11029126 | 0 |  | 2944.7848 | 1709.1714
2954 | 4622 | SAN RAFAEL 110668694 | 0 |  | 4050.2895 | 0
2955 | 4593 | WESTLEY 11039010 | 0 |  | 55369.2735 | 1485.982
2956 | 4573 | VIEJO 220255787 | 0 |  | 58.9251 | 58.9251
2957 | 4467 | POSO MOUNTAIN 2101circuit_breaker | 0 |  | 6924.1001 | 6924.1001
2958 | 4373 | VIEJO 22019704 | 0 |  | 4088.1892 | 786.5986
2959 | 4316 | SAN RAMON 2119circuit_breaker | 0 |  | 2436.9887 | 757.1628
2960 | 4309 | SONOMA 1105138 | 0 |  | 27343.3572 | 615.5192
2961 | 873 | SONOMA 1104414 | 0 |  | 28754.2864 | 669.1199
2962 | 1372 | LOS MOLINOS 11011308 | 0 |  | 19434.6302 | 205.1097
2963 | 1370 | COVELO 1101562360 | 0 |  | 61312.0727 | 3783.6743
2964 | 1298 | SONOMA 11054456 | 0 |  | 11837.4512 | 2092.6975
2965 | 1267 | EEL RIVER 1103circuit_breaker | 0 |  | 64348.2732 | 0
2966 | 1213 | STAFFORD 11021019 | 0 |  | 1173.8689 | 191.5288
2967 | 1196 | FORT BRAGG A 1101circuit_breaker | 0 | 1 | 13059.0747 | 290.3604
2968 | 1192 | EDENVALE 2107circuit_breaker | 0 |  | 4245.231 | 293.9737
2969 | 1178 | RINCON 1102640 | 0 |  | 6850.8117 | 16.0031
2970 | 1007 | OILFIELDS 110383158 | 0 |  | 31398.3782 | 28457.0143
2971 | 1383 | GONZALES 110422418 | 0 |  | 19539.8718 | 1354.2941
2972 | 657 | CABRILLO 1103circuit_breaker | 0 |  | 7201.0303 | 423.065
2973 | 647 | EL CERRITO G 1112BR196 | 0 |  | 5817.7228 | 68.9404
2974 | 504 | OAKLAND J 1116circuit_breaker | 0 |  | 29949.9344 | 0
2975 | 461 | VIEJO 22039094 | 0 |  | 4020.7495 | 160.2742
2976 | 401 | MILPITAS 1108XR122 | 0 |  | 11983.0786 | 49.0072
2977 | 384 | PETALUMA C 110856774 | 0 |  | 4425.4323 | 259.5884
2978 | 246 | SANTA ROSA A 1108626 | 0 |  | 6415.5954 | 219.1314
2979 | 203 | PACIFICA 110252715 | 0 |  | 6045.392 | 0
2980 | 11 | PASO ROBLES 1103N50 | 0 |  | 3452.721 | 3452.721
2981 | 2554 | CAYUCOS 11014701 | 0 |  | 14292.3514 | 3147.6745
2982 | 2831 | WILLOW PASS 2108circuit_breaker | 0 |  | 14603.4136 | 235.7533
2983 | 2720 | GOLDTREE 1108circuit_breaker | 0 |  | 7797.4445 | 3288.9555
2984 | 2715 | VALLEY VIEW 1105P124 | 0 |  | 5089.5347 | 0
2985 | 2676 | SAN LUIS OBISPO 1101592368 | 0 |  | 7364.7529 | 0
2986 | 2673 | JOLON 11027002 | 0 |  | 29669.8562 | 11843.464
2987 | 2626 | GREENBRAE 11037315 | 0 |  | 3607.614 | 0
2988 | 2596 | SNEATH LANE 11061339 | 0 |  | 8419.6559 | 0
2989 | 2590 | MC ARTHUR 110153120 | 0 |  | 12732.032 | 0
2990 | 2578 | ARVIN 110194892 | 0 |  | 15531.7609 | 345.9853
2991 | 5309 | VIEJO 22049440 | 0 |  | 5512.2097 | 10.1911
2992 | 2444 | EEL RIVER 1102530 | 0 |  | 51915.2562 | 8758.0357
2993 | 2087 | OILFIELDS 1103N44 | 0 |  | 29033.0076 | 28861.9134
2994 | 1981 | PETALUMA C 1108296 | 0 |  | 23764.0701 | 23764.0701
2995 | 1657 | BIG MEADOWS 21012016 | 0 |  | 6821.8424 | 20.5741
2996 | 1629 | LAKEWOOD 2224W544R | 0 |  | 8566.8847 | 0
2997 | 1606 | LOS COCHES 1101circuit_breaker | 0 |  | 32032.637 | 3722.9416
2998 | 1587 | PAUL SWEET 210510290 | 0 |  | 27546.0728 | 4.572
2999 | 1457 | STAFFORD 11021258 | 0 |  | 7855.3012 | 110.3452
3000 | 7912 | MADISON 21011969 | 0 |  | 13351.3585 | 200.8341
3001 | 8310 | VOLTA 1101circuit_breaker | 0 |  | 14809.7042 | 14809.7042
3002 | 8272 | GLENN 11012012 | 0 |  | 48377.7244 | 480.0698
3003 | 8157 | OCEANO 110376678 | 0 |  | 597.8557 | 88.7522
3004 | 8129 | OILFIELDS 1103N40 | 0 |  | 1192.0163 | 1192.0163
3005 | 8116 | PETALUMA C 1108636 | 0 |  | 14844.2499 | 14844.2499
3006 | 8019 | BRENTWOOD 2105502672 | 0 |  | 29946.4669 | 1990.2405
3007 | 7970 | SWIFT 2109XR300 | 0 |  | 1305.5095 | 121.3159
3008 | 7967 | FORT ROSS 1121204 | 0 |  | 30176.1504 | 30176.1504
3009 | 7938 | PASO ROBLES 1107circuit_breaker | 0 |  | 22651.5162 | 447.6357
3010 | 8333 | SAN RAMON 2101circuit_breaker | 0 |  | 1579.2012 | 940.3742
3011 | 7908 | SAUSALITO 11011270 | 0 |  | 1585.1168 | 817.322
3012 | 7902 | COVELO 110196896 | 0 |  | 24604.3242 | 5810.2676
3013 | 7896 | BRUNSWICK 1110circuit_breaker | 0 |  | 2750.224 | 6.096
3014 | 7848 | STAFFORD 1102361952 | 0 |  | 2196.587 | 2196.587
3015 | 7745 | LOS OSITOS 21037062 | 0 |  | 19658.415 | 19658.415
3016 | 7742 | WEST POINT 1101L1969 | 0 |  | 1741.0416 | 1741.0416
3017 | 7710 | WOODSIDE 1101circuit_breaker | 0 |  | 7096.7537 | 16.0021
3018 | 7668 | SAN RAMON 2107MR441 | 0 |  | 350.4949 | 40.2016
3019 | 7590 | GREENBRAE 110182270 | 0 |  | 1202.9792 | 4.572
3020 | 8920 | BRENTWOOD 21056512 | 0 |  | 1047.7996 | 1047.7996
3021 | 9098 | WOODWARD 2108688294 | 0 |  | 24.3604 | 24.3604
3022 | 9092 | CAMP EVERS 210595050 | 0 |  | 223.2117 | 223.2117
3023 | 9068 | SAN JOAQUIN #3 1101circuit_breaker | 0 |  | 8550.0082 | 8550.0082
3024 | 9047 | LOS OSITOS 21037468 | 0 |  | 12232.8773 | 736.8159
3025 | 9035 | DEL MAR 210938684 | 0 |  | 1501.1576 | 0
3026 | 9031 | SAN RAMON 2103MR279 | 0 |  | 323.7748 | 4.572
3027 | 9001 | MARIPOSA 210190130 | 0 |  | 144.8101 | 144.8101
3028 | 8959 | DIAMOND SPRINGS 1106176130 | 0 |  | 32.0737 | 32.0737
3029 | 8946 | ANDERSON 11011390 | 0 |  | 1742.8128 | 15.3102
3030 | 7587 | PUEBLO 11053022 | 0 |  | 14664.2587 | 238.6731
3031 | 8915 | JOLON 11027068 | 0 |  | 6155.1451 | 5962.9889
3032 | 8771 | CASTRO VALLEY 1108MR525 | 0 |  | 98.2491 | 98.2491
3033 | 8702 | ANTELOPE 11011631 | 0 |  | 18929.4401 | 1210.7069
3034 | 8689 | SOBRANTE 1103N510R | 0 |  | 1406.1178 | 404.6092
3035 | 8654 | KERN OIL 110646960 | 0 |  | 3100.4181 | 1285.0343
3036 | 8404 | MIRABEL 110213597 | 0 |  | 625.9642 | 625.9642
3037 | 8351 | EL CERRITO G 1110BR236 | 0 |  | 850.4173 | 784.0637
3038 | 8335 | BRUNSWICK 11047181 | 0 |  | 1196.7092 | 1196.7092
3039 | 5861 | EEL RIVER 110249130 | 0 |  | 22331.5765 | 2552.3517
3040 | 6387 | HICKS 2103XR248 | 0 |  | 2561.3965 | 124.695
3041 | 6367 | STANISLAUS 1702L5381 | 0 |  | 1946.774 | 1946.774
3042 | 6363 | SAN RAMON 2117circuit_breaker | 0 |  | 2698.3212 | 735.1259
3043 | 6335 | GREEN VALLEY 210112824 | 0 |  | 19537.6008 | 107.6616
3044 | 6226 | POINT ARENA 11013702 | 0 |  | 7962.9538 | 7868.7714
3045 | 6212 | STAFFORD 11021048 | 0 |  | 8433.9926 | 8411.3678
3046 | 6003 | FORT BRAGG A 110233064 | 0 |  | 5911.1864 | 0
3047 | 5908 | EDENVALE 2113circuit_breaker | 0 |  | 2357.516 | 24.568
3048 | 5900 | OILFIELDS 1103N64 | 0 |  | 20163.8274 | 16233.6548
3049 | 6444 | MARTELL 110292172 | 0 |  | 5297.1108 | 186.9738
3050 | 5756 | SAN RAFAEL 1107434 | 0 |  | 1839.9407 | 4.572
3051 | 5746 | TASSAJARA 2104circuit_breaker | 0 |  | 1951.9546 | 118.3029
3052 | 5737 | RALSTON 1102circuit_breaker | 0 |  | 6824.2186 | 1520.1281
3053 | 5688 | ORINDA 0401circuit_breaker | 0 |  | 238.0325 | 160.4005
3054 | 5604 | TIVY VALLEY 110737522 | 0 |  | 4999.5623 | 731.9163
3055 | 5528 | SWIFT 2107XR526 | 0 |  | 8725.9112 | 3165.9502
3056 | 5514 | PETALUMA C 1108628 | 0 |  | 18094.7665 | 14935.6028
3057 | 5482 | MORRO BAY 1102V80 | 0 |  | 3197.8948 | 18.5609
3058 | 5400 | TULUCAY 1101circuit_breaker | 0 |  | 11604.5805 | 121.1978
3059 | 7180 | WILLITS 11021270 | 0 |  | 2454.7077 | 0
3060 | 7447 | OILFIELDS 11032757 | 0 |  | 4491.0736 | 4491.0736
3061 | 7406 | 908 | 0 |  | 3596.4627 | 1022.6867
3062 | 7391 | TRES PINOS 11114032 | 0 |  | 30056.8781 | 0
3063 | 7381 | COVELO 110137328 | 0 |  | 37925.6018 | 6550.0939
3064 | 7357 | OILFIELDS 11035175 | 0 |  | 3554.759 | 3372.5858
3065 | 7326 | GOLDTREE 1107circuit_breaker | 0 |  | 5718.1268 | 1525.8896
3066 | 7313 | PEABODY 2106circuit_breaker | 0 |  | 1663.2394 | 1514.2978
3067 | 7305 | PALMER 1101M88 | 0 |  | 24710.2481 | 3785.6453
3068 | 7241 | SAN LUIS OBISPO 1107V58 | 0 |  | 3598.077 | 1708.3239
3069 | 9197 | CLOVERDALE 110247214 | 0 |  | 43.972 | 43.972
3070 | 7133 | SHINGLE SPRINGS 210551738 | 0 |  | 1844.3225 | 26.6806
3071 | 7042 | circuit_breaker | 0 |  | 8832.9704 | 0
3072 | 7009 | JOLON 11027004 | 0 |  | 32508.6758 | 8688.0359
3073 | 7005 | SUMMIT 1101circuit_breaker | 0 |  | 200.821 | 200.821
3074 | 6911 | OILFIELDS 1103N42 | 0 |  | 9813.7199 | 4452.4168
3075 | 6717 | HALF MOON BAY 110376762 | 0 |  | 817.0088 | 0
3076 | 6633 | LAMONT 11024222 | 0 |  | 26105.5713 | 805.2366
3077 | 6474 | MORRO BAY 1101W04 | 0 |  | 3936.0015 | 0
3078 | Total Result |  | 5408.3373 | 273599 | 58321257.808 | 41945885.4693

## DPCache_VMD_trees_2019_pz_summa (hidden)
region | PZ_idx | priority_tree_count | priority_outage_score_total | tree_count | outage_score_total | pixel_count | mean_ignition_probability | mean_mavf_core | mean_reax_structure_impact | mean_reax_fire_area | mean_reax_fire_volume | mean_reax_structure_score | mean_technosylva_structure_impact | mean_technosylva_fire_area | mean_technosylva_fire_burn_index | mean_mavf_core_risk | mean_reax_structure_risk | fraction_of_trees_priority | fraction_of_outage_score_priority | device_global_id | feeder_id | feeder_name | device_operating_number | device_latitude | device_longitude | circuit_protection_zone_id | n_primary | n_secondary | length_m | primary_length_m | secondary_length_m | primary_length_m_hftd_23 | secondary_length_m_hftd_23 | total_reax_structure_risk | expected_ignitions | mean_priority_outage_score | mean_tree_count | reax_risk_rank | Total mavf_core_risk | mean_mavf_core_risk_RANK | Included In EVM_2021_Plan | EVM_Percent_Completed | primary_length_miles_hftd_232 | Total MAVF Core Risk Ranking | Completed Work?
Central Coast | 8297 | 7 | 14.1651 | 18 | 19.3367 | 2 | 7.8444e-05 | 5899.3655 |  |  |  |  | 179.583 | 739.5062 | 1.5752 | 0.51453 | 7.8444e-05 | 0.38889 | 0.73255 | {36F02C24-D26B-4B85-8C08-B8C39025E135} | 182721104 | SANTA YNEZ 1104 | circuit_breaker | 34.6253 | -120.119 | SANTA YNEZ 1104circuit_breaker | 227 | 212 | 26320.2426 | 13829.7068 | 12490.5358 | 295.2522 | 163.3852 | 0.00015689 | 0.00015689 | 2.0236 | 9 | 1995 | 1.0291 | 1 | 0 | 0 | 0.18346 | 678 | 0
Sierra | 8244 | 1 | 1.945 | 3 | 2.3718 | 2 | 4.7008e-05 | 8812.9603 |  |  |  |  | 206.2943 | 2236.7657 | 1.9945 | 0.41379 | 4.7008e-05 | 0.33333 | 0.82004 | {E3DDE34B-B9EB-4C18-8053-7900216FEAC5} | 63681103 | PUTAH CREEK 1103 | 3783 | 38.4964 | -121.9886 | PUTAH CREEK 11033783 | 147 | 160 | 28683.4424 | 17433.8941 | 11249.5483 | 329.1954 | 13.0819 | 9.4016e-05 | 9.4016e-05 | 1.945 | 1.5 | 2267 | 0.82757 | 2 | 0 | 0 | 0.20455 | 2536 | 0
North Coast | 6700 | 30 | 42.4147 | 47 | 51.272 | 9 | 0.00015481 | 1996.5905 | 33.3576 | 90.4034 | 236.8204 | 8.4585 | 23.4007 | 497.5986 | 1.3466 | 0.39527 | 0.00055556 | 0.6383 | 0.82725 | {BD0977E2-D82F-4AAC-B014-EDCBC19E0BA7} | 42661103 | WILLITS 1103 | 966 | 39.4133 | -123.3512 | WILLITS 1103966 | 68 | 83 | 6354.0436 | 3603.2325 | 2750.8111 | 1339.7772 | 855.4454 | 0.0050001 | 0.0013933 | 1.4138 | 5.2222 | 731 | 3.5574 | 3 | 0 | 0 | 0.8325 | 2609 | 0
Sierra | 4403 | 519 | 1033.0377 | 1259 | 1333.1306 | 197 | 4.748e-05 | 6349.7036 | 39.9322 | 338.9438 | 1936.6865 | 236.0497 | 185.5107 | 1433.3699 | 1.7252 | 0.29397 | 0.0010653 | 0.41223 | 0.7749 | {1D851C9B-9F5B-4DD5-BA25-9C3137B89393} | 63591105 | VACA DIXON 1105 | 40092 | 38.4159 | -121.9706 | VACA DIXON 110540092 | 717 | 559 | 118824.5099 | 69249.133 | 49575.3769 | 37400.5677 | 22520.4651 | 0.20987 | 0.0093536 | 1.9904 | 6.3909 | 378 | 57.9125 | 4 | 0 | 0 | 23.2396 | 1820 | 0
Sierra | 7064 | 27 | 55.8808 | 44 | 60.4493 | 7 | 4.7066e-05 | 5974.1548 | 0.0045815 | 0.11184 | 0.83299 | 7.5888e-06 | 133.6359 | 1453.2579 | 1.6997 | 0.292 | 3.4246e-05 | 0.61364 | 0.92442 | {8A0CE410-7B0B-44D2-93E6-B3B628B03752} | 63681102 | PUTAH CREEK 1102 | 46012 | 38.4831 | -122.0253 | PUTAH CREEK 110246012 | 51 | 41 | 7110.349 | 4686.2992 | 2424.0498 | 945.6535 | 878.7773 | 0.00023972 | 0.00032946 | 2.0697 | 6.2857 | 2411 | 2.044 | 5 | 0 | 0 | 0.5876 | 54 | 0
Sierra | 6204 | 1 | 1.2277 | 6 | 2.2948 | 2 | 3.7747e-05 | 7256.2249 | 24.8519 | 7893.8926 | 109398.1797 | 2718.7568 | 71.1693 | 2652.0748 | 2.0985 | 0.2736 | 0.00063941 | 0.16667 | 0.53501 | {9CF014D5-3FFD-4E2B-8F6C-03768622E19C} | 63172101 | MADISON 2101 | 1975 | 38.8441 | -122.2035 | MADISON 21011975 | 33 | 36 | 6707.2419 | 3900.1165 | 2807.1254 | 127.6157 | 1422.3865 | 0.0012788 | 7.5493e-05 | 1.2277 | 3 | 628 | 0.54719 | 6 | 0 | 0 | 0.079297 | 1427 | 0
North Valley | 2559 | 32 | 67.936 | 61 | 77.1089 | 21 | 5.005e-05 | 5953.2626 | 25.8096 | 3670.7837 | 37903.4197 | 785.8548 | 58.7049 | 2481.424 | 2.0798 | 0.27112 | 0.00089699 | 0.52459 | 0.88104 | {49F083FF-CCD6-4656-915A-45D76A900BBC} | 102781101 | ELK CREEK 1101 | 2008 | 39.3676 | -122.5485 | ELK CREEK 11012008 | 197 | 197 | 37775.8985 | 29199.3162 | 8576.5823 | 8128.4527 | 2985.6099 | 0.018837 | 0.001051 | 2.123 | 2.9048 | 447 | 5.6936 | 7 | 0 | 0 | 5.0508 | 1163 | 0
North Valley | 3638 | 271 | 424.7154 | 928 | 611.9846 | 148 | 7.5014e-05 | 3331.5258 | 42.3747 | 405.1187 | 2023.5752 | 278.1604 | 77.6439 | 598.8284 | 1.4674 | 0.26179 | 0.0013061 | 0.29203 | 0.694 | {7B256BE5-97E8-449E-A46C-21FA2871BA72} | 103351104 | DESCHUTES 1104 | 1370 | 40.573 | -122.2386 | DESCHUTES 11041370 | 449 | 423 | 56482.1946 | 35731.175 | 20751.0196 | 19292.4005 | 9763.2963 | 0.1933 | 0.011102 | 1.5672 | 6.2703 | 291 | 38.7456 | 8 | 0 | 0 | 11.9877 | 989 | 0
North Coast | 9535 | 4 | 4.9109 | 9 | 7.0451 | 2 | 0.00012048 | 2169.7237 | 5.6125 | 796.3947 | 2409.0154 | 13.5205 | 33.0188 | 1306.5457 | 1.7699 | 0.25943 | 0.00043689 | 0.44444 | 0.69706 | {EF7692CE-6490-45CF-89E0-AAC63F03AECA} | 43141103 | MIDDLETOWN 1103 | circuit_breaker | 38.7526 | -122.6085 | MIDDLETOWN 1103circuit_breaker | 11 | 0 | 259.3908 | 259.3908 | 0 | 85.2366 | 0 | 0.00087378 | 0.00024097 | 1.2277 | 4.5 | 885 | 0.51885 | 9 | 0 | 0 | 0.052964 | 1140 | 0
Sierra | 3511 | 224 | 330.916 | 457 | 437.1519 | 76 | 5.0112e-05 | 4736.0701 | 7.3269 | 351.0017 | 3102.5251 | 83.3569 | 71.5566 | 724.5764 | 1.6767 | 0.25486 | 0.00017767 | 0.49015 | 0.75698 | {ADB960B7-1B6C-413D-B1F8-E0FB7A88FA0F} | 63601108 | VACAVILLE 1108 | 8762 | 38.3617 | -122.0225 | VACAVILLE 11088762 | 199 | 151 | 38620.2876 | 26864.0035 | 11756.2841 | 22706.5359 | 8430.6661 | 0.013503 | 0.0038085 | 1.4773 | 6.0132 | 1496 | 19.3692 | 10 | 0 | 0 | 14.1092 | 1094 | 0
North Valley | 6336 | 243 | 339.1213 | 412 | 394.7643 | 47 | 7.9196e-05 | 2863.112 | 2.958 | 68.5972 | 257.5988 | 2.5959 | 46.3971 | 465.8986 | 1.4936 | 0.24907 | 0.00012034 | 0.58981 | 0.85905 | {FE5A37BD-E086-417E-B0C1-D984D30B636B} | 103351101 | DESCHUTES 1101 | circuit_breaker | 40.5553 | -122.2397 | DESCHUTES 1101circuit_breaker | 191 | 183 | 27520.5896 | 17933.5448 | 9587.0448 | 6460.1699 | 2099.646 | 0.0056559 | 0.0037222 | 1.3956 | 8.766 | 1746 | 11.7062 | 11 | 0 | 0 | 4.0142 | 2397 | 0
North Valley | 8993 | 2 | 3.89 | 3 | 4.1034 | 2 | 6.023e-05 | 3916.7482 | 11.6558 | 716.0426 | 5150.0979 | 59.0637 | 40.9591 | 1213.853 | 1.9569 | 0.23786 | 0.00072839 | 0.66667 | 0.94799 | {2B3F7DCA-485E-4940-AF70-C148286D4D0A} | 102541101 | VOLTA 1101 | 49742 | 40.4306 | -121.8716 | VOLTA 110149742 | 42 | 28 | 8109.3842 | 5593.8568 | 2515.5275 | 5593.8568 | 2515.5275 | 0.0014568 | 0.00012046 | 1.945 | 1.5 | 548 | 0.47572 | 12 | 0 | 0 | 3.4759 | 992 | 0
North Valley | 5783 | 279 | 479.8829 | 1281 | 803.3307 | 224 | 7.1027e-05 | 3743.715 | 46.3928 | 1171.2525 | 6625.3247 | 683.8055 | 57.8828 | 731.0249 | 1.5395 | 0.23311 | 0.0015184 | 0.2178 | 0.59737 | {6281842D-96D3-4641-90CC-4C58A4D89E7E} | 103521104 | OREGON TRAIL 1104 | 1634 | 40.5711 | -122.2997 | OREGON TRAIL 11041634 | 290 | 231 | 41109.0988 | 29357.8519 | 11751.2469 | 28112.1395 | 11713.738 | 0.34013 | 0.01591 | 1.72 | 5.7188 | 242 | 52.2161 | 13 | 0 | 0 | 17.4681 | 909 | 0
Sierra | 6125 | 135 | 269.3081 | 354 | 353.0823 | 64 | 4.7955e-05 | 5187.7744 | 40.4937 | 765.0739 | 4142.6864 | 605.8035 | 91.2093 | 1293.6357 | 1.7064 | 0.22711 | 0.00084801 | 0.38136 | 0.76273 | {89E381E1-F842-49C9-837A-CF37A4D6EF66} | 63681102 | PUTAH CREEK 1102 | 8352 | 38.5035 | -122.002 | PUTAH CREEK 11028352 | 184 | 120 | 30019.7444 | 18999.2581 | 11020.4863 | 8943.386 | 5704.6878 | 0.054273 | 0.0030691 | 1.9949 | 5.5312 | 472 | 14.5349 | 14 | 0 | 0 | 5.5572 | 704 | 0
Central Coast | 4339 | 324 | 807.425 | 692 | 983.5599 | 118 | 7.2031e-05 | 3166.0371 | 7.8753 | 355.4859 | 1005.5275 | 12.3844 | 51.0799 | 710.9219 | 1.5577 | 0.22707 | 0.00027613 | 0.46821 | 0.82092 | {1E768305-B6AF-4963-B2D5-92FDAB6A5028} | 182721104 | SANTA YNEZ 1104 | Y04 | 34.6354 | -120.0656 | SANTA YNEZ 1104Y04 | 343 | 182 | 55695.1663 | 35646.7737 | 20048.3926 | 24112.9415 | 9815.6324 | 0.032584 | 0.0084996 | 2.4921 | 5.8644 | 1183 | 26.7943 | 15 | 0 | 0 | 14.9831 | 2142 | 0
North Coast | 4340 | 31 | 48.7915 | 71 | 66.5382 | 10 | 0.00016092 | 1330.2523 | 0.0041685 | 0.40274 | 1.8655 | 3.8648e-05 | 16.854 | 217.6049 | 1.1487 | 0.22681 | 8.6289e-05 | 0.43662 | 0.73329 | {00459A21-49A7-4C9F-B533-C9081A2B5652} | 42661103 | WILLITS 1103 | 37504 | 39.4132 | -123.3273 | WILLITS 110337504 | 100 | 73 | 8185.5101 | 5389.9576 | 2795.5526 | 1413.5779 | 1019.3012 | 0.00086289 | 0.0016092 | 1.5739 | 7.1 | 1938 | 2.2681 | 16 | 0 | 0 | 0.87836 | 677 | 0
North Valley | 1665 | 238 | 544.8241 | 1164 | 762.3343 | 216 | 5.6552e-05 | 4141.4647 | 42.3704 | 432.6948 | 2386.9256 | 299.5991 | 97.5026 | 617.5515 | 1.4597 | 0.22216 | 0.0010856 | 0.20447 | 0.71468 | {271E2474-ABAF-41B6-966B-4F5B19FF11CA} | 103351104 | DESCHUTES 1104 | 49024 | 40.5929 | -122.2397 | DESCHUTES 110449024 | 308 | 298 | 42250.8098 | 26924.4497 | 15326.3601 | 25640.9937 | 14608.5195 | 0.23449 | 0.012215 | 2.2892 | 5.3889 | 368 | 47.9874 | 17 | 0 | 0 | 15.9326 | 2472 | 0
Central Valley | 5807 | 102 | 195.1263 | 495 | 329.3152 | 141 | 3.3961e-05 | 6362.0175 | 111.4587 | 5747.0161 | 54455.0363 | 7563.0141 | 77.1048 | 1580.331 | 1.8387 | 0.22154 | 0.0019083 | 0.20606 | 0.59252 | {98EBF873-A6B0-4247-9A49-69BFB2B9A30C} | 254432104 | COARSEGOLD 2104 | 6288 | 37.2638 | -119.7335 | COARSEGOLD 21046288 | 155 | 171 | 30435.1645 | 16779.965 | 13655.1995 | 16779.965 | 13655.1995 | 0.26907 | 0.0047885 | 1.913 | 3.5106 | 184 | 31.2372 | 18 | 0 | 0 | 10.4266 | 429 | 0
North Valley | 2282 | 4 | 8.6881 | 10 | 10.4245 | 3 | 5.333e-05 | 4222.0207 |  |  |  |  | 90.0111 | 566.2939 | 1.6453 | 0.22048 | 5.333e-05 | 0.4 | 0.83343 | {DB300DCA-6215-4B3C-914F-828156445EA8} | 102931101 | COTTONWOOD 1101 | 1510 | 40.3892 | -122.3413 | COTTONWOOD 11011510 | 56 | 38 | 8553.6084 | 5333.1807 | 3220.4278 | 494.2929 | 19.772 | 0.00015999 | 0.00015999 | 2.172 | 3.3333 | 2209 | 0.66143 | 19 | 0 | 0 | 0.30714 | 1645 | 0
Sierra | 5985 | 179 | 332.7556 | 623 | 522.4861 | 107 | 0.00012872 | 1841.9208 | 61.7415 | 286.8435 | 2374.6955 | 446.7126 | 26.0068 | 351.0238 | 1.5077 | 0.21615 | 0.0041332 | 0.28732 | 0.63687 | {8C6D6A40-340A-49FE-9A00-F50F1736F18B} | 153652105 | SHINGLE SPRINGS 2105 | 19522 | 38.6999 | -120.9922 | SHINGLE SPRINGS 210519522 | 173 | 181 | 29712.1003 | 16493.1882 | 13218.9121 | 15477.8093 | 12840.9009 | 0.44226 | 0.013773 | 1.859 | 5.8224 | 57 | 23.1275 | 20 | 0 | 0 | 9.6175 | 1912 | 0
North Coast | 6737 | 59 | 75.1104 | 103 | 88.9824 | 11 | 8.7817e-05 | 2068.7842 | 12.83 | 336.1431 | 1411.7481 | 37.5523 | 26.1205 | 359.8927 | 1.316 | 0.20515 | 0.00090158 | 0.57282 | 0.8441 | {BE94A233-F70C-44A4-9222-81B080FDD6FB} | 42281105 | POTTER VALLEY P H 1105 | 64118 | 39.362 | -123.1283 | POTTER VALLEY P H 110564118 | 158 | 214 | 28181.6044 | 15416.9418 | 12764.6627 | 2045.917 | 1781.6863 | 0.0099174 | 0.00096598 | 1.2731 | 9.3636 | 443 | 2.2567 | 21 | 0 | 0 | 1.2713 | 347 | 0
Central Valley | 2021 | 158 | 298.4741 | 873 | 536.184 | 225 | 4.2112e-05 | 5014.6219 | 120.4406 | 2374.0746 | 22896.3859 | 5768.1413 | 58.5576 | 767.3117 | 1.686 | 0.20288 | 0.0021853 | 0.18099 | 0.55666 | {43911212-3F90-4E9E-B3C9-DFE000FE6625} | 254432104 | COARSEGOLD 2104 | 5310 | 37.2286 | -119.7102 | COARSEGOLD 21045310 | 271 | 269 | 53194.7871 | 28358.0547 | 24836.7324 | 28358.0547 | 24836.7324 | 0.49168 | 0.0094753 | 1.8891 | 3.88 | 161 | 45.6473 | 22 | 0 | 0 | 17.6209 | 1073 | 0
Bay Area | 1138 | 161 | 451.6533 | 218 | 474.4617 | 34 | 3.8233e-05 | 5209.0646 | 38.4378 | 873.2237 | 3601.2143 | 257.1502 | 61.6342 | 1918.6983 | 1.9049 | 0.20023 | 0.00094354 | 0.73853 | 0.95193 | {175EAA06-BA71-4C85-BCC5-D0819BAB887B} | 13232105 | LONE TREE 2105 | 21210 | 37.9253 | -121.7602 | LONE TREE 210521210 | 132 | 56 | 31784.9767 | 25986.6286 | 5798.3481 | 16983.4147 | 5120.9116 | 0.03208 | 0.0012999 | 2.8053 | 6.4118 | 437 | 6.8077 | 23 | 0 | 0 | 10.553 | 2086 | 0
Sierra | 2533 | 1 | 1.2277 | 2 | 1.6834 | 2 | 2.2442e-05 | 8860.7085 | 4.3442 | 39.9796 | 176.1325 | 5.1508 | 307.4093 | 2007.6905 | 1.9889 | 0.19892 | 5.8168e-05 | 0.5 | 0.72928 | {E4D247B8-5AC2-4613-B16F-7A9DCBD633B8} | 63591105 | VACA DIXON 1105 | 9792 | 38.4197 | -121.9685 | VACA DIXON 11059792 | 508 | 468 | 79362.4338 | 46444.676 | 32917.7578 | 1598.1228 | 829.1409 | 0.00011634 | 4.4885e-05 | 1.2277 | 1 | 2159 | 0.39784 | 24 | 0 | 0 | 0.99303 | 648 | 0
North Valley | 1601 | 584 | 1203.661 | 2025 | 1630.4926 | 235 | 8.3583e-05 | 2479.9423 | 49.9714 | 589.5183 | 3924.2335 | 561.0251 | 52.6946 | 393.0651 | 1.365 | 0.19694 | 0.0020699 | 0.2884 | 0.73822 | {EE491565-D605-44EC-BC24-016AA03F899F} | 103521104 | OREGON TRAIL 1104 | 1574 | 40.5886 | -122.2985 | OREGON TRAIL 11041574 | 351 | 408 | 53022.1611 | 30217.5794 | 22804.5817 | 26331.2246 | 19714.3262 | 0.48642 | 0.019642 | 2.0611 | 8.617 | 170 | 46.2816 | 25 | 0 | 0 | 16.3615 | 1105 | 0
North Valley | 7507 | 130 | 259.2306 | 280 | 308.1453 | 65 | 6.0947e-05 | 3570.8117 | 71.8656 | 1249.3514 | 8152.54 | 880.5371 | 71.7534 | 645.9618 | 1.4495 | 0.19678 | 0.0023239 | 0.46429 | 0.84126 | {C6B7B820-7989-4630-B30E-94C5C9589FF6} | 103441102 | JESSUP 1102 | 3105 | 40.4392 | -122.3976 | JESSUP 11023105 | 103 | 136 | 18056.4058 | 10017.6158 | 8038.79 | 9428.2851 | 7609.8352 | 0.15105 | 0.0039616 | 1.9941 | 4.3077 | 147 | 12.7904 | 26 | 0 | 0 | 5.8585 | 247 | 0
Sierra | 6610 | 65 | 90.9873 | 194 | 142.7979 | 33 | 8.8737e-05 | 2219.1984 | 30.2076 | 434.4605 | 1554.1831 | 51.8146 | 39.8951 | 543.1292 | 1.3837 | 0.19496 | 0.0012772 | 0.33505 | 0.63718 | {95CFDCE9-A6F6-4428-B8F8-A23AC65977EB} | 103191101 | BANGOR 1101 | 55206 | 39.3091 | -121.4181 | BANGOR 110155206 | 178 | 158 | 30865.6981 | 16572.7725 | 14292.9256 | 3897.0387 | 2263.7029 | 0.042148 | 0.0029283 | 1.3998 | 5.8788 | 297 | 6.4338 | 27 | 0 | 0 | 2.4215 | 1393 | 0
Central Valley | 5931 | 165 | 337.0416 | 529 | 462.4703 | 166 | 4.0004e-05 | 4637.7171 | 80.8622 | 1119.5948 | 9213.7508 | 2740.3482 | 57.4695 | 935.7412 | 1.6075 | 0.18534 | 0.0013899 | 0.31191 | 0.72879 | {22973E9F-9F56-4D4C-A7E3-5FDC99C738ED} | 254432104 | COARSEGOLD 2104 | 5525 | 37.1933 | -119.7709 | COARSEGOLD 21045525 | 258 | 439 | 48322.2178 | 20995.911 | 27326.3069 | 20995.911 | 27326.3069 | 0.23072 | 0.0066407 | 2.0427 | 3.1867 | 276 | 30.7671 | 28 | 0 | 0 | 13.0463 | 1448 | 0
North Coast | 6073 | 18 | 26.1925 | 101 | 74.0954 | 13 | 9.3566e-05 | 1888.2695 | 11.1845 | 672.7682 | 2382.0717 | 35.1829 | 24.1778 | 757.2005 | 1.5026 | 0.18481 | 0.00044504 | 0.17822 | 0.3535 | {05737260-3AA4-4F7E-BF36-A5BD94AF80DD} | 43161101 | SALMON CREEK 1101 | 196 | 38.335 | -123.0444 | SALMON CREEK 1101196 | 45 | 23 | 13823.4611 | 11722.7376 | 2100.7234 | 5757.7629 | 1362.6699 | 0.0057855 | 0.0012164 | 1.4551 | 7.7692 | 872 | 2.4025 | 29 | 0 | 0 | 3.5777 | 1003 | 0
Central Valley | 5498 | 88 | 296.602 | 291 | 353.1958 | 119 | 4.0636e-05 | 4750.0677 | 116.8701 | 8760.8065 | 65955.6329 | 10034.0638 | 56.5475 | 1948.5018 | 1.7159 | 0.18449 | 0.0023965 | 0.30241 | 0.83977 | {98A05919-30C6-4E49-A2BF-93B102BA501D} | 252062111 | SHEPHERD 2111 | R1400 | 36.967 | -119.6264 | SHEPHERD 2111R1400 | 298 | 245 | 57252.3264 | 36919.6677 | 20332.6588 | 29130.6459 | 16893.8237 | 0.28518 | 0.0048357 | 3.3705 | 2.4454 | 138 | 21.9543 | 30 | 0 | 0 | 18.1009 | 140 | 0
North Coast | 445 | 405 | 568.1896 | 567 | 648.082 | 53 | 0.00033039 | 569.1774 | 11.3161 | 171.5635 | 1466.5018 | 33.9541 | 10.2396 | 112.9408 | 1.4303 | 0.18431 | 0.0023581 | 0.71429 | 0.87672 | {DBB8EF0C-28BA-4359-82ED-65DB4B560023} | 192221101 | GARBERVILLE 1101 | 1604 | 40.1029 | -123.7928 | GARBERVILLE 11011604 | 188 | 103 | 34130.1717 | 27911.2836 | 6218.8881 | 6822.8212 | 1569.8568 | 0.12498 | 0.017511 | 1.4029 | 10.6981 | 142 | 9.7685 | 31 | 0 | 0 | 4.2395 | 1044 | 0
North Valley | 1661 | 107 | 145.594 | 815 | 310.7628 | 152 | 4.165e-05 | 4126.3876 | 37.1429 | 938.9545 | 4513.7077 | 277.8877 | 80.5117 | 1158.7082 | 1.6734 | 0.18233 | 0.00066785 | 0.13129 | 0.46851 | {F164BF8B-3484-47A3-8EEF-5FFD77D4911A} | 103351104 | DESCHUTES 1104 | 9718 | 40.535 | -122.2392 | DESCHUTES 11049718 | 513 | 383 | 82682.5334 | 56953.3633 | 25729.1701 | 26275.4179 | 10637.7875 | 0.10151 | 0.0063308 | 1.3607 | 5.3618 | 599 | 27.7145 | 32 | 0 | 0 | 16.3268 | 583 | 0
North Coast | 3086 | 3 | 3.6831 | 36 | 17.5616 | 3 | 7.4618e-05 | 2673.0267 | 0 | 0 | 0 | 0 | 32.41 | 349.98 | 1.677 | 0.18138 | 4.8784e-05 | 0.083333 | 0.20973 | {168A101A-B40A-4107-A560-9FF95054D3E7} | 42141101 | CLEAR LAKE 1101 | 486 | 39.0026 | -122.8755 | CLEAR LAKE 1101486 | 508 | 677 | 98090.0725 | 49197.9889 | 48892.0836 | 343.3545 | 1187.1495 | 0.00014635 | 0.00022385 | 1.2277 | 12 | 2237 | 0.54415 | 33 | 0 | 0 | 0.21335 | 805 | 0
Sierra | 2360 | 423 | 670.0687 | 1019 | 929.3401 | 177 | 4.0343e-05 | 4627.8598 | 20.3187 | 689.403 | 5599.1376 | 293.3359 | 82.3964 | 1232.5768 | 1.6737 | 0.18029 | 0.00043725 | 0.41511 | 0.72102 | {05D49B9F-74A5-4524-8EF5-6986AE7D334D} | 63601108 | VACAVILLE 1108 | 38316 | 38.3844 | -122.0317 | VACAVILLE 110838316 | 292 | 231 | 59435.0065 | 37516.1668 | 21918.8396 | 25488.4092 | 13986.5844 | 0.077394 | 0.0071407 | 1.5841 | 5.7571 | 884 | 31.9111 | 34 | 0 | 0 | 15.8378 | 1111 | 0
North Valley | 190 | 1108 | 2120.38 | 3109 | 2678.243 | 624 | 6.7055e-05 | 2743.7932 | 41.1317 | 428.1777 | 2895.1742 | 411.8029 | 58.0124 | 506.2432 | 1.3789 | 0.17911 | 0.0013335 | 0.35638 | 0.79171 | {84FBA97C-0AC5-4C21-A8AB-84EEEE14C7B2} | 103521103 | OREGON TRAIL 1103 | 35002 | 40.6243 | -122.3039 | OREGON TRAIL 110335002 | 966 | 908 | 141184.3423 | 92189.591 | 48994.7513 | 92189.591 | 48994.7513 | 0.83208 | 0.041842 | 1.9137 | 4.9824 | 286 | 111.7647 | 35 | 0 | 0 | 57.2839 | 233 | 0
Sierra | 7265 | 1 | 1.4572 | 13 | 6.1334 | 5 | 3.0804e-05 | 5771.6029 | 126.4097 | 353.1624 | 1663.3052 | 210.2579 | 168.4748 | 907.4733 | 1.6469 | 0.1776 | 0.00071438 | 0.076923 | 0.23758 | {C14F8C7D-2418-4308-A5BD-32845AC90D2E} | 63591101 | VACA DIXON 1101 | 18292 | 38.4006 | -121.9626 | VACA DIXON 110118292 | 135 | 111 | 15813.9414 | 9364.4146 | 6449.5268 | 1339.9258 | 632.3378 | 0.0035719 | 0.00015402 | 1.4572 | 2.6 | 558 | 0.88798 | 36 | 0 | 0 | 0.83259 | 787 | 0
North Valley | 3707 | 144 | 302.2527 | 861 | 487.496 | 202 | 5.1006e-05 | 3385.3965 | 29.8756 | 409.2718 | 2194.6574 | 314.8625 | 72.7758 | 534.7804 | 1.4185 | 0.17561 | 0.00077454 | 0.16725 | 0.62001 | {B0D7961A-1F9D-4064-B96A-EFFD7ACCE4BD} | 103351104 | DESCHUTES 1104 | 9726 | 40.5639 | -122.2425 | DESCHUTES 11049726 | 280 | 295 | 42616.6841 | 27044.9597 | 15571.7244 | 24438.8213 | 13535.1402 | 0.15646 | 0.010303 | 2.099 | 4.2624 | 516 | 35.4739 | 37 | 0 | 0 | 15.1856 | 900 | 0
Central Coast | 2761 | 0 | 0 | 1 | 0.45574 | 1 | 2.3613e-05 | 7301.4863 |  |  |  |  | 82.6283 | 660.369 | 1.7633 | 0.17241 | 2.3613e-05 | 0 | 0 | {D032C5C8-0FC6-482A-9EC0-2FCD6D7C5C9E} | 182611104 | PASO ROBLES 1104 | P02 | 35.6406 | -120.695 | PASO ROBLES 1104P02 | 204 | 485 | 28069.3919 | 11384.6152 | 16684.7767 | 389.1275 | 126.479 | 2.3613e-05 | 2.3613e-05 |  | 1 | 2550 | 0.17241 | 38 | 0 | 0 | 0.24179 | 2310 | 0
North Coast | 5502 | 18 | 34.1016 | 59 | 46.3616 | 15 | 4.6812e-05 | 3787.4468 | 1.194 | 109.8835 | 1240.4871 | 7.3326 | 46.7982 | 661.9337 | 1.7128 | 0.17198 | 4.9393e-05 | 0.30508 | 0.73556 | {D05A5F97-BA6C-4210-AA67-0AC96ADACE28} | 43211101 | HARTLEY 1101 | 658 | 39.0609 | -122.9334 | HARTLEY 1101658 | 212 | 261 | 44398.9157 | 21971.0708 | 22427.8449 | 4569.0388 | 1696.5005 | 0.00074089 | 0.00070218 | 1.8945 | 3.9333 | 2233 | 2.5796 | 39 | 0 | 0 | 2.8391 | 692 | 0
Sierra | 7007 | 5 | 6.1386 | 16 | 11.2451 | 5 | 5.1307e-05 | 2929.086 | 7.6032 | 721.003 | 3887.2417 | 59.4141 | 34.3208 | 600.8503 | 1.9593 | 0.17112 | 0.00031327 | 0.3125 | 0.54589 | {A9A36598-2BF7-4270-99BF-EC9B9E23BB29} | 63801102 | JAMESON 1102 | 8842 | 38.2334 | -122.1508 | JAMESON 11028842 | 114 | 72 | 12806.1181 | 9062.7483 | 3743.3698 | 757.4983 | 188.7265 | 0.0015663 | 0.00025654 | 1.2277 | 3.2 | 1097 | 0.8556 | 40 | 0 | 0 | 0.47069 | 1112 | 0
North Valley | 1301 | 128 | 195.8303 | 690 | 338.7669 | 135 | 6.2983e-05 | 2453.887 | 26.9891 | 542.453 | 2917.9201 | 282.3076 | 49.1566 | 526.8177 | 1.3966 | 0.16608 | 0.00070167 | 0.18551 | 0.57807 | {D7FE7EC5-7478-43B3-9A24-52065EFA1755} | 103351104 | DESCHUTES 1104 | circuit_breaker | 40.5551 | -122.2396 | DESCHUTES 1104circuit_breaker | 522 | 632 | 73143.1858 | 39924.6145 | 33218.5713 | 19511.2444 | 11301.8154 | 0.094725 | 0.0085027 | 1.5299 | 5.1111 | 565 | 22.4208 | 41 | 0 | 0 | 12.1237 | 1529 | 0
Central Coast | 819 | 267 | 397.4217 | 924 | 767.7103 | 238 | 6.8282e-05 | 2529.3037 | 15.2243 | 503.6275 | 2063.7795 | 50.6441 | 38.1096 | 1063.3566 | 1.5498 | 0.16262 | 0.00054231 | 0.28896 | 0.51767 | {49C145C8-C8F5-459A-817E-3F37A5597C7A} | 182681102 | ZACA 1102 | Y54 | 34.6533 | -120.0714 | ZACA 1102Y54 | 435 | 142 | 71672.8706 | 54621.7415 | 17051.1291 | 53471.0661 | 15937.4697 | 0.12907 | 0.016251 | 1.4885 | 3.8824 | 746 | 38.7034 | 42 | 0 | 0 | 33.2254 | 2114 | 0
North Coast | 4570 | 101 | 157.1366 | 189 | 184.1195 | 39 | 8.1512e-05 | 1755.698 | 19.7011 | 1043.4857 | 9415.5063 | 313.2735 | 29.4754 | 449.2575 | 1.3364 | 0.16097 | 0.0011901 | 0.53439 | 0.85345 | {F617C2F6-F9CA-4233-ADD2-A5EEE40355DB} | 43361103 | HIGHLANDS 1103 | 828 | 38.9081 | -122.6006 | HIGHLANDS 1103828 | 168 | 173 | 37317.391 | 17124.6025 | 20192.7885 | 12064.542 | 13281.3679 | 0.046415 | 0.003179 | 1.5558 | 4.8462 | 326 | 6.2778 | 43 | 0 | 0 | 7.4966 | 514 | 0
North Coast | 6356 | 1863 | 2881.502 | 2379 | 3142.3342 | 240 | 0.00012823 | 1297.6626 | 3.6058 | 478.2908 | 7013.6785 | 40.7882 | 12.1051 | 205.5513 | 1.3714 | 0.16032 | 0.00027538 | 0.7831 | 0.91699 | {6C3387D7-E1FD-47EC-9629-A161F573B39E} | 43141101 | MIDDLETOWN 1101 | 622 | 38.7462 | -122.6206 | MIDDLETOWN 1101622 | 222 | 181 | 45500.0956 | 32035.0118 | 13465.0838 | 25790.8227 | 9001.687 | 0.06609 | 0.030775 | 1.5467 | 9.9125 | 1187 | 38.4777 | 44 | 0 | 0 | 16.0257 | 2416 | 0
Central Coast | 6910 | 103 | 325.5748 | 422 | 498.7574 | 47 | 4.1679e-05 | 3561.4984 | 8.0761 | 146.6115 | 662.0095 | 12.6968 | 48.2871 | 514.4975 | 1.436 | 0.15925 | 0.00013308 | 0.24408 | 0.65277 | {ABB59667-7D2C-427E-8CD5-70D7C7F4474B} | 182611103 | PASO ROBLES 1103 | N58 | 35.6286 | -120.6955 | PASO ROBLES 1103N58 | 158 | 234 | 24039.9352 | 12056.5272 | 11983.408 | 7139.6018 | 4492.0835 | 0.0062546 | 0.0019589 | 3.1609 | 8.9787 | 1683 | 7.4845 | 45 | 0 | 0 | 4.4363 | 2015 | 0
Sierra | 733 | 381 | 693.6009 | 898 | 915.8334 | 124 | 4.8331e-05 | 3555.5758 | 44.9832 | 1041.5656 | 6953.8683 | 827.904 | 54.5852 | 1530.0143 | 1.6827 | 0.15785 | 0.0011848 | 0.42428 | 0.75734 | {14F48B8C-8A8F-4490-B11D-9FE802AC416A} | 63681102 | PUTAH CREEK 1102 | 67858 | 38.4806 | -122.0273 | PUTAH CREEK 110267858 | 128 | 105 | 22758.0522 | 18688.4623 | 4069.5899 | 18688.4623 | 4069.5899 | 0.14691 | 0.0059931 | 1.8205 | 7.2419 | 329 | 19.5736 | 46 | 0 | 0 | 11.6125 | 2191 | 0
North Coast | 6598 | 215 | 310.4906 | 722 | 592.3693 | 78 | 0.00010887 | 1601.0989 | 21.9516 | 650.6357 | 3266.6954 | 185.0904 | 21.7664 | 604.8208 | 1.3184 | 0.15666 | 0.0014739 | 0.29778 | 0.52415 | {2FFE3F5E-20F1-4C4A-B741-4DF0040A4D91} | 43161101 | SALMON CREEK 1101 | 88998 | 38.3484 | -122.9804 | SALMON CREEK 110188998 | 165 | 180 | 31745.4349 | 22084.2262 | 9661.2087 | 9919.7992 | 4940.4832 | 0.11496 | 0.0084916 | 1.4441 | 9.2564 | 252 | 12.2196 | 47 | 0 | 0 | 6.1639 | 1248 | 0
North Valley | 6517 | 45 | 82.9477 | 339 | 222.54 | 75 | 9.7677e-05 | 1680.9711 | 28.8982 | 527.1071 | 8803.569 | 1444.9752 | 24.9338 | 284.5731 | 1.3586 | 0.15638 | 0.0016925 | 0.13274 | 0.37273 | {669572AC-0804-48DE-A3ED-77BF33DD2E29} | 103451101 | KESWICK 1101 | 48480 | 40.6238 | -122.4618 | KESWICK 110148480 | 214 | 172 | 25696.5893 | 17324.1107 | 8372.4786 | 17324.1107 | 8372.4786 | 0.12694 | 0.0073257 | 1.8433 | 4.52 | 209 | 11.7286 | 48 | 0 | 0 | 10.7647 | 1584 | 0
North Valley | 3982 | 205 | 386.5972 | 581 | 511.4282 | 81 | 8.0082e-05 | 1964.2021 | 36.2301 | 485.7562 | 3733.0039 | 306.0434 | 35.4716 | 367.4269 | 1.2858 | 0.15291 | 0.00089009 | 0.35284 | 0.75592 | {5E999E0A-FF01-4E2B-B970-E4BD7149EAE7} | 103521102 | OREGON TRAIL 1102 | 1382 | 40.6539 | -122.3334 | OREGON TRAIL 11021382 | 116 | 96 | 14284.8305 | 8802.4775 | 5482.353 | 8802.4775 | 5482.353 | 0.072097 | 0.0064866 | 1.8858 | 7.1728 | 451 | 12.3855 | 49 | 0 | 0 | 5.4696 | 2515 | 0
Sierra | 9488 | 1 | 0.97225 | 12 | 5.0877 | 2 | 7.3704e-05 | 2049.5865 | 0.023565 | 6.8834 | 28.1164 | 0.0084852 | 31.6726 | 847.0681 | 1.5442 | 0.15106 | 2.8013e-05 | 0.083333 | 0.1911 | {9208AF25-E3F3-4F0D-8CE3-550040B29414} | 153612105 | CLARKSVILLE 2105 | circuit_breaker | 38.6558 | -121.0598 | CLARKSVILLE 2105circuit_breaker | 17 | 1 | 2004.0454 | 1912.7297 | 91.3157 | 759.3509 | 91.3157 | 5.6026e-05 | 0.00014741 | 0.97225 | 6 | 2491 | 0.30213 | 50 | 0 | 0 | 0.47184 | 2384 | 0
Central Coast | 1239 | 6 | 7.3663 | 6 | 7.3663 | 2 | 2.7907e-05 | 5376.749 | 46.0331 | 572.1687 | 2562.0087 | 119.2535 | 69.1969 | 1243.4613 | 1.7743 | 0.15005 | 0.0012605 | 1 | 1 | {DD694EAA-A9BC-4C03-B675-60DCE9DF4147} | 183052113 | TEMPLETON 2113 | circuit_breaker | 35.5554 | -120.6799 | TEMPLETON 2113circuit_breaker | 477 | 1084 | 88569.9542 | 41923.3786 | 46646.5756 | 879.0751 | 254.7108 | 0.002521 | 5.5813e-05 | 1.2277 | 3 | 302 | 0.30009 | 51 | 0 | 0 | 0.54623 | 1692 | 0
Sierra | 6431 | 3 | 7.6513 | 69 | 27.1089 | 16 | 2.5506e-05 | 6141.0894 | 25.286 | 291.709 | 1295.0323 | 261.1329 | 128.2687 | 2165.2628 | 1.7973 | 0.14976 | 0.00058083 | 0.043478 | 0.28224 | {C8D6AD52-3FC7-4093-8F21-C9B9A6CB67BA} | 63681103 | PUTAH CREEK 1103 | 3851 | 38.4779 | -121.9895 | PUTAH CREEK 11033851 | 39 | 52 | 12953.9513 | 8317.7311 | 4636.2202 | 6216.3391 | 1846.0861 | 0.0092933 | 0.0004081 | 2.5504 | 4.3125 | 695 | 2.3961 | 52 | 0 | 0 | 3.8627 | 252 | 0
Central Coast | 5096 | 41 | 61.8156 | 389 | 258.5281 | 65 | 4.0023e-05 | 3709.2748 | 43.0929 | 743.1852 | 2353.9917 | 190.8792 | 47.0862 | 612.3226 | 1.5518 | 0.14873 | 0.00081965 | 0.1054 | 0.23911 | {30375F5B-5F9A-4C1C-992C-DEDED43F1FC3} | 182721104 | SANTA YNEZ 1104 | 77098 | 34.6323 | -120.1186 | SANTA YNEZ 110477098 | 146 | 101 | 28673.1744 | 20978.2648 | 7694.9096 | 16911.4845 | 6901.673 | 0.053277 | 0.0026015 | 1.5077 | 5.9846 | 486 | 9.6674 | 53 | 0 | 0 | 10.5083 | 1743 | 0
Bay Area | 7698 | 2 | 7.6323 | 4 | 8.5438 | 2 | 2.5275e-05 | 5781.2322 | 0.042779 | 3.6283 | 6.4733 | 0.0029025 | 59.6062 | 4174.6785 | 1.7909 | 0.14795 | 1.6249e-05 | 0.5 | 0.89332 | {96E83343-B1D6-4373-84A9-0E60E5A945BA} | 14422109 | CAYETANO 2109 | MR186 | 37.7324 | -121.7123 | CAYETANO 2109MR186 | 37 | 15 | 4752.4141 | 4135.7533 | 616.6608 | 547.3474 | 153.7843 | 3.2498e-05 | 5.055e-05 | 3.8162 | 2 | 2680 | 0.2959 | 54 | 0 | 0 | 0.34011 | 2752 | 0
Central Coast | 5194 | 127 | 225.5629 | 251 | 278.1792 | 66 | 4.1704e-05 | 3481.1402 | 6.3602 | 36.8302 | 133.5042 | 3.4751 | 60.6223 | 647.9008 | 1.4331 | 0.14727 | 0.0001474 | 0.50598 | 0.81085 | {63FF5E85-7320-4916-95DB-09A821D7A9F8} | 183052113 | TEMPLETON 2113 | A20 | 35.5005 | -120.6607 | TEMPLETON 2113A20 | 128 | 115 | 18021.8207 | 12664.8988 | 5356.9218 | 10922.8343 | 4831.4112 | 0.0097283 | 0.0027525 | 1.7761 | 3.803 | 1606 | 9.7196 | 55 | 0 | 0 | 6.7871 | 1114 | 0
Central Valley | 204 | 189 | 393.9523 | 1169 | 718.9774 | 307 | 2.5311e-05 | 5819.7271 | 143.5512 | 3887.5747 | 34856.5241 | 8611.3666 | 77.5673 | 959.0718 | 1.7032 | 0.14221 | 0.0016138 | 0.16168 | 0.54793 | {004C66A4-EFD9-4F4F-AA71-77719D3D9AC9} | 254151102 | AUBERRY 1102 | circuit_breaker | 37.0683 | -119.4966 | AUBERRY 1102circuit_breaker | 543 | 529 | 99480.059 | 55632.597 | 43847.4619 | 55632.597 | 43847.4619 | 0.49543 | 0.0077704 | 2.0844 | 3.8078 | 226 | 43.659 | 56 | 0 | 0 | 34.5685 | 709 | 0
North Valley | 1336 | 2 | 3.7899 | 31 | 10.8472 | 10 | 6.1657e-05 | 2307.2196 | 13.4104 | 134.1716 | 445.441 | 14.1628 | 48.8796 | 890.0033 | 1.6544 | 0.13953 | 0.00031447 | 0.064516 | 0.34939 | {9D2C06EE-ACC3-496B-9742-675775229618} | 103541105 | RED BLUFF 1105 | 1564 | 40.2052 | -122.2077 | RED BLUFF 11051564 | 269 | 288 | 31652.1248 | 17079.3867 | 14572.7381 | 1829.5964 | 1072.6957 | 0.0031447 | 0.00061657 | 1.8949 | 3.1 | 1095 | 1.3953 | 57 | 0 | 0 | 1.1369 | 2806 | 0
Central Valley | 2220 | 153 | 329.5239 | 824 | 553.7891 | 203 | 4.1023e-05 | 3521.4804 | 66.8121 | 1799.7615 | 16251.4939 | 3181.4693 | 44.5278 | 604.7162 | 1.5082 | 0.13854 | 0.0014063 | 0.18568 | 0.59504 | {298036AF-0EED-4E31-B15F-AFDA3D1D605E} | 254432104 | COARSEGOLD 2104 | 369777 | 37.2293 | -119.7354 | COARSEGOLD 2104369777 | 221 | 227 | 46896.9794 | 29945.6871 | 16951.2923 | 29945.6871 | 16951.2923 | 0.28548 | 0.0083277 | 2.1538 | 4.0591 | 273 | 28.1228 | 58 | 0 | 0 | 18.6074 | 1314 | 0
North Valley | 1883 | 11 | 27.247 | 128 | 56.4687 | 23 | 4.8441e-05 | 2690.9227 | 33.4375 | 455.2778 | 1849.1389 | 122.5782 | 53.2055 | 790.7256 | 1.4544 | 0.13744 | 0.00073322 | 0.085938 | 0.48251 | {39175FAF-A6C7-4043-8D47-1A655E22AF59} | 103461101 | PANORAMA 1101 | circuit_breaker | 40.4343 | -122.2675 | PANORAMA 1101circuit_breaker | 325 | 375 | 47085.3055 | 30501.9872 | 16583.3183 | 4988.6634 | 1347.4285 | 0.016864 | 0.0011141 | 2.477 | 5.5652 | 545 | 3.1611 | 59 | 0 | 0 | 3.0998 | 305 | 0
Central Valley | 2424 | 234 | 455.8566 | 345 | 493.9998 | 84 | 7.0501e-05 | 2087.2695 | 24.8252 | 1227.7913 | 8241.2296 | 986.8736 | 32.8567 | 1264.0033 | 1.808 | 0.13658 | 0.0006823 | 0.67826 | 0.92279 | {41DA8C6A-A66B-4741-8630-05B8383240D3} | 255292108 | WOODWARD 2108 | R2860 | 36.9932 | -119.6991 | WOODWARD 2108R2860 | 279 | 195 | 53539.1747 | 35474.6172 | 18064.5575 | 17727.1373 | 8246.0845 | 0.057314 | 0.005922 | 1.9481 | 4.1071 | 583 | 11.4725 | 60 | 0 | 0 | 11.0151 | 2274 | 0
North Valley | 2963 | 163 | 234.6642 | 446 | 321.5683 | 69 | 8.4152e-05 | 1691.8212 | 8.5917 | 240.5001 | 1093.7779 | 15.6117 | 43.221 | 372.6762 | 1.3664 | 0.13588 | 0.0003564 | 0.36547 | 0.72975 | {1467DC6C-6C30-498B-9696-60E37D99774A} | 103351104 | DESCHUTES 1104 | 1582 | 40.5725 | -122.2381 | DESCHUTES 11041582 | 256 | 241 | 39154.068 | 24249.9571 | 14904.1109 | 9068.1485 | 3062.9838 | 0.024592 | 0.0058065 | 1.4397 | 6.4638 | 1005 | 9.3758 | 61 | 0 | 0 | 5.6347 | 1869 | 0
North Valley | 4059 | 203 | 374.7606 | 684 | 518.624 | 101 | 7.7176e-05 | 1889.5546 | 47.9294 | 1536.4471 | 10329.0097 | 759.2911 | 30.2053 | 502.4618 | 1.3334 | 0.13537 | 0.0015056 | 0.29678 | 0.72261 | {6D96391D-7B6F-4C91-8B77-363C23EC443F} | 102931103 | COTTONWOOD 1103 | 1344 | 40.3671 | -122.2982 | COTTONWOOD 11031344 | 233 | 260 | 32829.4244 | 20065.0071 | 12764.4173 | 15508.3048 | 9623.7731 | 0.15207 | 0.0077948 | 1.8461 | 6.7723 | 245 | 13.6725 | 62 | 0 | 0 | 9.6364 | 363 | 0
Sierra | 105 | 427 | 826.9283 | 1198 | 1143.9054 | 170 | 6.6275e-05 | 2148.5752 | 19.4196 | 185.3214 | 746.7561 | 28.7646 | 37.3113 | 357.8926 | 1.2667 | 0.13473 | 0.0006795 | 0.35643 | 0.7229 | {E6EC7043-C8B2-457F-AB90-031C70C010CA} | 152271102 | WISE 1102 | 2054 | 38.8963 | -121.1201 | WISE 11022054 | 221 | 201 | 32657.1333 | 20797.7702 | 11859.3631 | 20797.7702 | 11859.3631 | 0.11551 | 0.011267 | 1.9366 | 7.0471 | 588 | 22.9035 | 63 | 0 | 0 | 12.9231 | 611 | 0
Sierra | 891 | 5 | 9.7249 | 99 | 32.3605 | 28 | 2.1637e-05 | 6017.8189 | 11.3052 | 762.6842 | 3483.4675 | 64.6195 | 82.7445 | 1537.2641 | 1.8214 | 0.13302 | 0.0001581 | 0.050505 | 0.30052 | {EC7E3E82-534C-45F0-825C-A06402B7C3CE} | 63681102 | PUTAH CREEK 1102 | circuit_breaker | 38.5228 | -121.9941 | PUTAH CREEK 1102circuit_breaker | 161 | 136 | 33368.8045 | 21280.8935 | 12087.9109 | 7914.4674 | 5557.3799 | 0.0044269 | 0.00060583 | 1.945 | 3.5357 | 1551 | 3.7245 | 64 | 0 | 0 | 4.9178 | 832 | 0
North Coast | 1911 | 309 | 402.7171 | 367 | 431.0376 | 48 | 0.00017713 | 712.5295 | 28.0385 | 878.794 | 15885.9951 | 2417.2898 | 10.8572 | 124.326 | 1.4128 | 0.13276 | 0.0019856 | 0.84196 | 0.9343 | {19EB4414-DC45-4E37-BE88-7022C918AAEC} | 42661104 | WILLITS 1104 | circuit_breaker | 39.4056 | -123.3268 | WILLITS 1104circuit_breaker | 244 | 242 | 24276.4523 | 12252.1327 | 12024.3196 | 4814.9119 | 3155.6754 | 0.095308 | 0.0085021 | 1.3033 | 7.6458 | 177 | 6.3727 | 65 | 0 | 0 | 2.9918 | 768 | 0
Central Valley | 3795 | 248 | 417.5557 | 2140 | 1057.8789 | 394 | 3.7004e-05 | 3589.9841 | 31.0319 | 2693.3676 | 23025.2698 | 1112.081 | 40.7561 | 874.8396 | 1.6609 | 0.13159 | 0.00057243 | 0.11589 | 0.39471 | {7717B878-CAFD-4AC4-8B78-BDBB8F6365D2} | 254452102 | MARIPOSA 2102 | 10880 | 37.4617 | -119.9507 | MARIPOSA 210210880 | 459 | 428 | 106316.5002 | 64121.2381 | 42195.2621 | 63141.8494 | 40793.3135 | 0.22554 | 0.01458 | 1.6837 | 5.4315 | 705 | 51.8448 | 66 | 0 | 0 | 39.2345 | 1081 | 0
Central Valley | 5945 | 17 | 39.3195 | 83 | 55.7544 | 18 | 4.8328e-05 | 2514.4885 | 35.7549 | 516.896 | 5603.8977 | 741.873 | 37.1556 | 403.3665 | 1.5163 | 0.13127 | 0.00058515 | 0.20482 | 0.70523 | {9485A7D0-401F-403C-A8F4-B704232548DB} | 254432104 | COARSEGOLD 2104 | 570682 | 37.264 | -119.7128 | COARSEGOLD 2104570682 | 42 | 37 | 5108.267 | 3262.933 | 1845.3341 | 3262.933 | 1845.3341 | 0.010533 | 0.00086991 | 2.3129 | 4.6111 | 687 | 2.3629 | 67 | 0 | 0 | 2.0275 | 976 | 0
North Coast | 3080 | 139 | 296.7558 | 276 | 372.7259 | 39 | 8.6769e-05 | 1883.8555 | 16.1766 | 578.7212 | 2591.5659 | 122.1618 | 26.3478 | 399.5914 | 1.3168 | 0.13114 | 0.00078468 | 0.50362 | 0.79618 | {B81A8616-55B2-41F9-9829-B699E6A06290} | 42571102 | MOLINO 1102 | 79306 | 38.3722 | -122.9117 | MOLINO 110279306 | 93 | 97 | 21034.1108 | 13023.8596 | 8010.2512 | 5037.4953 | 3666.2135 | 0.030602 | 0.003384 | 2.1349 | 7.0769 | 506 | 5.1143 | 68 | 0 | 0 | 3.1302 | 1322 | 0
Central Valley | 3587 | 69 | 186.6006 | 280 | 247.313 | 76 | 2.6331e-05 | 4716.9608 | 145.1776 | 12320.4442 | 101228.5864 | 18708.4397 | 46.0421 | 1009.8873 | 1.697 | 0.13104 | 0.0021618 | 0.24643 | 0.75451 | {6CB8407B-8DEC-4DDB-A06C-70CFC4C2C27B} | 254151102 | AUBERRY 1102 | R309 | 37.0114 | -119.5301 | AUBERRY 1102R309 | 135 | 122 | 22869.4238 | 13825.8859 | 9043.5379 | 13825.8859 | 9043.5379 | 0.1643 | 0.0020011 | 2.7044 | 3.6842 | 164 | 9.9592 | 69 | 0 | 0 | 8.591 | 410 | 0
North Valley | 890 | 43 | 95.3745 | 814 | 289.3832 | 162 | 4.6035e-05 | 3045.9203 | 26.7635 | 228.3451 | 1121.4638 | 71.5444 | 56.5558 | 572.66 | 1.5112 | 0.13084 | 0.00061744 | 0.052826 | 0.32958 | {7F728486-5D30-4578-BA26-525DB688C650} | 102931102 | COTTONWOOD 1102 | circuit_breaker | 40.3969 | -122.2674 | COTTONWOOD 1102circuit_breaker | 505 | 695 | 71161.0822 | 37956.7799 | 33204.3024 | 25573.0555 | 16828.1751 | 0.10002 | 0.0074577 | 2.218 | 5.0247 | 652 | 21.1966 | 70 | 0 | 0 | 15.8904 | 1693 | 0
Sierra | 3716 | 470 | 845.3569 | 1465 | 1235.8494 | 266 | 5.9669e-05 | 2114.6543 | 29.1149 | 251.1371 | 1253.1238 | 68.7907 | 40.1888 | 392.5621 | 1.2863 | 0.13059 | 0.00088919 | 0.32082 | 0.68403 | {46E702EC-9F9A-49D3-8D4F-660BC1315D70} | 152271102 | WISE 1102 | 2230 | 38.8961 | -121.1374 | WISE 11022230 | 406 | 392 | 66967.2093 | 39994.2491 | 26972.9602 | 36254.0831 | 24452.4066 | 0.23652 | 0.015872 | 1.7986 | 5.5075 | 453 | 34.7369 | 71 | 0 | 0 | 22.5272 | 368 | 0
Central Valley | 3450 | 142 | 320.1987 | 548 | 445.7216 | 177 | 3.246e-05 | 4051.0455 | 138.9158 | 8822.1621 | 70830.8244 | 12625.9257 | 53.1187 | 1223.4568 | 1.7947 | 0.12922 | 0.0024772 | 0.25912 | 0.71838 | {CFE5622E-640A-4701-B25A-30E645D814D9} | 254151102 | AUBERRY 1102 | R2850 | 37.0358 | -119.5229 | AUBERRY 1102R2850 | 294 | 239 | 67886.0863 | 41610.2357 | 26275.8505 | 41610.2357 | 26275.8505 | 0.43847 | 0.0057454 | 2.2549 | 3.096 | 127 | 22.8722 | 72 | 0 | 0 | 25.8554 | 1146 | 0
North Valley | 662 | 364 | 643.204 | 1185 | 933.4167 | 143 | 8.942e-05 | 1318.5472 | 23.4954 | 160.496 | 1150.4219 | 105.655 | 27.6519 | 214.0257 | 1.2837 | 0.12899 | 0.00097551 | 0.30717 | 0.68909 | {8048141D-B1E9-414C-85DA-8DE818EBAD4F} | 103521104 | OREGON TRAIL 1104 | circuit_breaker | 40.6191 | -122.3223 | OREGON TRAIL 1104circuit_breaker | 326 | 352 | 40533.3055 | 24009.399 | 16523.9065 | 15260.0733 | 10899.3941 | 0.1395 | 0.012787 | 1.767 | 8.2867 | 422 | 18.4455 | 73 | 0 | 0 | 9.4822 | 1972 | 0
Central Valley | 1973 | 530 | 714.0093 | 1634 | 1197.5703 | 304 | 5.3116e-05 | 2670.1707 | 23.9205 | 248.4856 | 1797.7076 | 72.8972 | 34.4547 | 336.1249 | 1.3822 | 0.1287 | 0.00065339 | 0.32436 | 0.59621 | {19617CFD-32A5-4AA4-9E54-43F64E95D667} | 254421101 | OAKHURST 1101 | 5490 | 37.3403 | -119.676 | OAKHURST 11015490 | 442 | 574 | 72516.2806 | 39826.5176 | 32689.763 | 39826.5176 | 32689.763 | 0.19863 | 0.016147 | 1.3472 | 5.375 | 612 | 39.1235 | 74 | 0 | 0 | 24.747 | 2360 | 0
Central Coast | 2593 | 142 | 314.2026 | 648 | 515.5908 | 151 | 3.5484e-05 | 3682.9975 | 12.1966 | 298.1261 | 1410.7724 | 47.4963 | 48.8081 | 795.6018 | 1.5552 | 0.128 | 0.00019812 | 0.21914 | 0.6094 | {3D8A845E-016A-4676-A95E-AFB35541512A} | 182611103 | PASO ROBLES 1103 | N54 | 35.6544 | -120.7258 | PASO ROBLES 1103N54 | 299 | 223 | 49268.661 | 34349.6665 | 14918.9945 | 30731.9341 | 14025.413 | 0.029916 | 0.005358 | 2.2127 | 4.2914 | 1422 | 19.3286 | 75 | 0 | 0 | 19.0959 | 2660 | 0
North Valley | 502 | 90 | 221.2743 | 561 | 350.6362 | 127 | 5.1266e-05 | 2774.6504 | 39.2025 | 630.3007 | 3422.7378 | 254.4532 | 47.9553 | 699.444 | 1.495 | 0.12773 | 0.0010426 | 0.16043 | 0.63107 | {BD544C17-FF5A-4B33-BB2A-02C4080D2F78} | 102931102 | COTTONWOOD 1102 | 9026 | 40.3895 | -122.3431 | COTTONWOOD 11029026 | 409 | 377 | 60465.9563 | 38967.1548 | 21498.8015 | 19720.6221 | 9410.8376 | 0.13241 | 0.0065108 | 2.4586 | 4.4173 | 388 | 16.2213 | 76 | 0 | 0 | 12.2538 | 352 | 0
North Coast | 5017 | 254 | 402.6341 | 557 | 496.79 | 109 | 8.584e-05 | 1527.7165 | 28.7023 | 145.879 | 715.3227 | 51.3963 | 22.8158 | 184.4716 | 1.3534 | 0.12748 | 0.0014102 | 0.45601 | 0.81047 | {F4CEECFF-9688-4F5E-82B6-98F3F42878F8} | 43361103 | HIGHLANDS 1103 | circuit_breaker | 38.937 | -122.6089 | HIGHLANDS 1103circuit_breaker | 296 | 541 | 43901.148 | 19679.9672 | 24221.1808 | 16763.7621 | 17632.8429 | 0.15372 | 0.0093566 | 1.5852 | 5.1101 | 270 | 13.8949 | 77 | 0 | 0 | 10.4165 | 2768 | 0
Central Coast | 3127 | 63 | 156.7322 | 163 | 184.7613 | 49 | 3.3226e-05 | 3847.7615 | 17.6862 | 449.8026 | 2148.735 | 114.2992 | 47.1518 | 809.3316 | 1.6496 | 0.12582 | 0.00036865 | 0.3865 | 0.8483 | {7FF6A461-1CB2-4D3B-BBDC-5839761BEAE7} | 182661104 | SAN MIGUEL 1104 | R58 | 35.7208 | -120.6846 | SAN MIGUEL 1104R58 | 311 | 268 | 54720.2906 | 38699.3305 | 16020.96 | 14371.1045 | 3302.8724 | 0.018064 | 0.0016281 | 2.4878 | 3.3265 | 985 | 6.1653 | 78 | 0 | 0 | 8.9298 | 1413 | 0
North Coast | 5903 | 3 | 9.1113 | 6 | 10.2854 | 4 | 8.0985e-05 | 1655.7072 | 132.488 | 2538.4912 | 9917.5176 | 1200.5496 | 23.5763 | 504.8237 | 1.542 | 0.12522 | 0.0018133 | 0.5 | 0.88585 | {F9D85BA5-F081-4C89-8A4E-6F66CE119492} | 42631108 | PETALUMA C 1108 | 618 | 38.2276 | -122.6634 | PETALUMA C 1108618 | 205 | 260 | 38879.5062 | 17463.5088 | 21415.9974 | 13883.0282 | 13251.2423 | 0.0072531 | 0.00032394 | 3.0371 | 1.5 | 192 | 0.50087 | 79 | 0 | 0 | 8.6265 | 853 | 0
North Valley | 86 | 65 | 224.931 | 951 | 476.0686 | 156 | 4.1124e-05 | 3115.2311 | 16.1567 | 566.9002 | 2950.7503 | 104.837 | 48.3745 | 1203.842 | 1.4997 | 0.12451 | 0.00039466 | 0.068349 | 0.47248 | {E58E84BF-2C2E-494E-AE66-0D141BD137C3} | 103571105 | TYLER 1105 | 1704 | 40.1553 | -122.2755 | TYLER 11051704 | 619 | 609 | 117058.0485 | 74221.1596 | 42836.8889 | 18219.6369 | 12069.9757 | 0.061566 | 0.0064154 | 3.4605 | 6.0962 | 951 | 19.4232 | 80 | 0 | 0 | 11.3212 | 498 | 0
North Valley | 1571 | 237 | 480.7323 | 2173 | 1082.6111 | 351 | 8.4765e-05 | 1912.5049 | 77.6145 | 1123.6035 | 9187 | 1680.9918 | 33.2884 | 458.1153 | 1.4206 | 0.1245 | 0.003191 | 0.10907 | 0.44405 | {C223429B-0181-4823-A81C-029389E1A395} | 102931103 | COTTONWOOD 1103 | 1348 | 40.3592 | -122.3378 | COTTONWOOD 11031348 | 535 | 624 | 87935.7971 | 51202.5627 | 36733.2344 | 45791.5824 | 32482.8312 | 1.12 | 0.029752 | 2.0284 | 6.1909 | 90 | 43.6979 | 81 | 0 | 0 | 28.4536 | 467 | 0
Bay Area | 8455 | 5 | 6.2694 | 55 | 34.2037 | 16 | 7.1118e-05 | 1563.364 | 16.0952 | 974.6007 | 8640.421 | 232.8013 | 21.7571 | 401.1028 | 1.3811 | 0.12339 | 0.00054287 | 0.090909 | 0.1833 | {07D78386-6A73-46DA-81CA-B20D2445579F} | 43201102 | STAFFORD 1102 | 1202 | 38.1221 | -122.6224 | STAFFORD 11021202 | 53 | 37 | 25331.2148 | 12713.8882 | 12617.3266 | 11742.1904 | 12617.3266 | 0.008686 | 0.0011379 | 1.2539 | 3.4375 | 745 | 1.9742 | 82 | 0 | 0 | 7.2963 | 1657 | 0
North Coast | 3596 | 819 | 1180.0149 | 989 | 1265.491 | 154 | 0.00010426 | 1014.9627 | 32.697 | 3630.9528 | 73429.9939 | 4113.2308 | 4.3728 | 396.7122 | 1.6251 | 0.12303 | 0.0015729 | 0.82811 | 0.93246 | {CD599840-F925-4A8F-AC72-601D0F3A1898} | 42771111 | UKIAH 1111 | 534 | 39.1765 | -123.2122 | UKIAH 1111534 | 181 | 143 | 49479.8994 | 33746.6437 | 15733.2557 | 30274.4024 | 12477.0499 | 0.24223 | 0.016056 | 1.4408 | 6.4221 | 233 | 18.9464 | 83 | 0 | 0 | 18.8116 | 908 | 0
Central Coast | 1399 | 150 | 259.3459 | 310 | 347.6461 | 79 | 3.7563e-05 | 3284.8028 | 21.7462 | 350.0515 | 1085.0227 | 52.5606 | 56.9766 | 688.608 | 1.3761 | 0.12271 | 0.00037113 | 0.48387 | 0.74601 | {615A0700-A424-4825-ACAC-C9AB34833626} | 182681102 | ZACA 1102 | Y02 | 34.6503 | -120.0946 | ZACA 1102Y02 | 245 | 116 | 32802.069 | 21124.0364 | 11678.0325 | 15863.9802 | 7724.9951 | 0.029319 | 0.0029675 | 1.729 | 3.9241 | 982 | 9.6937 | 84 | 0 | 0 | 9.8574 | 2390 | 0
North Valley | 6222 | 191 | 364.9452 | 903 | 602.8757 | 134 | 8.87e-05 | 1511.5076 | 51.5062 | 536.6434 | 3942.6976 | 570.2218 | 33.0946 | 287.4305 | 1.2147 | 0.12145 | 0.0023826 | 0.21152 | 0.60534 | {096694C8-1954-4FED-B3CE-6072F54B2C4B} | 103561102 | STILLWATER 1102 | 48952 | 40.6808 | -122.2985 | STILLWATER 110248952 | 184 | 137 | 25663.8872 | 16989.9527 | 8673.9345 | 16989.9527 | 8673.9345 | 0.31927 | 0.011886 | 1.9107 | 6.7388 | 140 | 16.2746 | 85 | 0 | 0 | 10.5571 | 1237 | 0
Central Valley | 192 | 178 | 351.5821 | 1203 | 659.751 | 383 | 3.2265e-05 | 4067.0084 | 95.0742 | 4305.1803 | 35736.9993 | 5896.8978 | 48.9639 | 902.6347 | 1.6685 | 0.12107 | 0.0016849 | 0.14796 | 0.5329 | {756F4B6A-7251-46F3-9B2C-93A003B98431} | 254432104 | COARSEGOLD 2104 | 5300 | 37.227 | -119.7102 | COARSEGOLD 21045300 | 439 | 426 | 93924.2635 | 59987.7854 | 33936.4781 | 59987.7854 | 33936.4781 | 0.64532 | 0.012357 | 1.9752 | 3.141 | 211 | 46.3711 | 86 | 0 | 0 | 37.2747 | 1966 | 0
North Coast | 1391 | 95 | 168.0715 | 556 | 295.6891 | 134 | 6.3778e-05 | 2008.9145 | 22.5479 | 224.1565 | 1717.8943 | 118.322 | 27.6867 | 467.696 | 1.5045 | 0.12019 | 0.00076404 | 0.17086 | 0.56841 | {5F8C3D5E-6EE2-44BA-8DAB-1423918270D0} | 43141102 | MIDDLETOWN 1102 | 998 | 38.7941 | -122.5663 | MIDDLETOWN 1102998 | 349 | 682 | 68478.8559 | 27688.0247 | 40790.8311 | 23041.0417 | 34832.7993 | 0.10238 | 0.0085463 | 1.7692 | 4.1493 | 526 | 16.1058 | 87 | 0 | 0 | 14.317 | 494 | 0
North Coast | 6489 | 52 | 78.6744 | 115 | 95.6063 | 32 | 5.6959e-05 | 2165.7235 | 7.9779 | 1187.0814 | 5410.3148 | 81.1515 | 25.5296 | 1102.1314 | 1.5946 | 0.11931 | 0.00022275 | 0.45217 | 0.8229 | {7E69B413-A223-4CCD-AF98-CC3C74EA7FDA} | 43141102 | MIDDLETOWN 1102 | circuit_breaker | 38.7528 | -122.6088 | MIDDLETOWN 1102circuit_breaker | 115 | 49 | 15060.3621 | 10581.2966 | 4479.0656 | 7090.0728 | 2534.4495 | 0.007128 | 0.0018227 | 1.513 | 3.5938 | 1334 | 3.818 | 88 | 0 | 0 | 4.4056 | 573 | 0
North Valley | 3724 | 271 | 440.0412 | 848 | 621.6249 | 150 | 6.7061e-05 | 1700.2912 | 7.3752 | 325.2799 | 1304.9714 | 24.8109 | 25.1367 | 777.7153 | 1.4693 | 0.11922 | 0.00030692 | 0.31958 | 0.70789 | {53F1163A-2879-44DA-A8DC-132948A94C1B} | 103351101 | DESCHUTES 1101 | 1380 | 40.5607 | -122.1889 | DESCHUTES 11011380 | 301 | 288 | 57729.1725 | 37711.3658 | 20017.8067 | 27539.9827 | 11316.7995 | 0.046039 | 0.010059 | 1.6238 | 5.6533 | 1105 | 17.8832 | 89 | 0 | 0 | 17.1125 | 2611 | 0
Central Coast | 7350 | 17 | 27.8392 | 70 | 45.0775 | 16 | 4.2933e-05 | 2719.485 | 30.9377 | 571.2051 | 2710.0383 | 203.2722 | 42.1484 | 826.4503 | 1.3928 | 0.11881 | 0.00076833 | 0.24286 | 0.61759 | {9CF1253B-D8D6-49C7-BA9B-F1C1932CEBBE} | 182611103 | PASO ROBLES 1103 | 2731 | 35.6845 | -120.73 | PASO ROBLES 11032731 | 15 | 13 | 3624.073 | 2616.6102 | 1007.4628 | 2616.6102 | 1007.4628 | 0.012293 | 0.00068693 | 1.6376 | 4.375 | 521 | 1.901 | 90 | 0 | 0 | 1.6259 | 2302 | 0
Central Valley | 1744 | 135 | 265.5548 | 360 | 333.2096 | 126 | 2.4375e-05 | 4832.9923 | 42.5801 | 5533.3975 | 32339.252 | 1377.0084 | 75.9927 | 1399.5812 | 1.7227 | 0.11726 | 3.0861e-05 | 0.375 | 0.79696 | {8685FED6-DA63-4202-8ADA-3D58BFE83B0E} | 252941107 | TIVY VALLEY 1107 | 869946 | 36.8179 | -119.3396 | TIVY VALLEY 1107869946 | 286 | 299 | 64046.4293 | 48055.8133 | 15990.616 | 48055.8133 | 15990.616 | 0.0038885 | 0.0030712 | 1.9671 | 2.8571 | 2459 | 14.7751 | 91 | 0 | 0 | 29.8605 | 1423 | 0
Central Valley | 1577 | 382 | 808.2699 | 1044 | 1049.0729 | 307 | 3.9755e-05 | 3259.1031 | 34.6108 | 2569.4179 | 19541.7487 | 1713.8384 | 44.2108 | 807.1604 | 1.5329 | 0.11508 | 0.00059963 | 0.3659 | 0.77046 | {87310FC6-15ED-48C6-A2E1-D0212614AC1A} | 254432103 | COARSEGOLD 2103 | 10820 | 37.155 | -119.7343 | COARSEGOLD 210310820 | 495 | 803 | 109378.8823 | 45979.4651 | 63399.4172 | 45523.6929 | 63177.5372 | 0.18409 | 0.012205 | 2.1159 | 3.4007 | 673 | 35.3292 | 92 | 0 | 0 | 28.2871 | 389 | 0
North Valley | 6021 | 26 | 44.69 | 206 | 90.5944 | 42 | 6.8517e-05 | 1906.519 | 29.6792 | 921.7707 | 6215.9426 | 391.496 | 34.663 | 528.9978 | 1.5557 | 0.1146 | 0.0010385 | 0.12621 | 0.4933 | {29DB4A9A-9909-45FE-9CC1-C3F1A6A44799} | 102931101 | COTTONWOOD 1101 | 31500 | 40.3697 | -122.3442 | COTTONWOOD 110131500 | 152 | 113 | 29022.517 | 18970.9292 | 10051.5878 | 6089.5352 | 2482.4302 | 0.043619 | 0.0028777 | 1.7188 | 4.9048 | 390 | 4.8132 | 93 | 0 | 0 | 3.7839 | 1034 | 0
Sierra | 1789 | 311 | 529.114 | 1707 | 952.9045 | 243 | 4.1304e-05 | 2725.4684 | 31.7791 | 933.7562 | 6696.0849 | 402.4538 | 43.2453 | 464.093 | 1.3594 | 0.11438 | 0.00070486 | 0.18219 | 0.55526 | {33D208FF-CBCA-4936-9E53-DB6042F9491A} | 152701107 | BELL 1107 | 50172 | 38.9459 | -121.1228 | BELL 110750172 | 301 | 356 | 54503.7994 | 29834.4703 | 24669.3291 | 27581.8653 | 20252.7453 | 0.17128 | 0.010037 | 1.7013 | 7.0247 | 563 | 27.7939 | 94 | 0 | 0 | 17.1386 | 269 | 0
Sierra | 7292 | 158 | 515.2773 | 288 | 584.1177 | 26 | 3.4505e-05 | 3840.7981 | 1.0172 | 780.4489 | 4025.5318 | 9.2414 | 40.1343 | 1100.9895 | 1.6546 | 0.11398 | 3.221e-05 | 0.54861 | 0.88215 | {D66EDA38-27E9-4939-96F7-B9EFA1F3B789} | 63801103 | JAMESON 1103 | circuit_breaker | 38.2056 | -122.1476 | JAMESON 1103circuit_breaker | 126 | 74 | 24284.7793 | 17445.1976 | 6839.5817 | 3720.1837 | 3480.0243 | 0.00083747 | 0.00089713 | 3.2612 | 11.0769 | 2438 | 2.9634 | 95 | 0 | 0 | 2.3116 | 235 | 0
Central Valley | 2409 | 422 | 921.6403 | 1591 | 1311.9781 | 473 | 3.5475e-05 | 3465.7844 | 86.5552 | 3272.1076 | 24017.7721 | 4605.1771 | 49.4588 | 675.1924 | 1.593 | 0.11269 | 0.0016085 | 0.26524 | 0.70248 | {7CAE9E3D-9A6E-4166-92A3-E494C4AA002D} | 254432104 | COARSEGOLD 2104 | 10400 | 37.2216 | -119.7687 | COARSEGOLD 210410400 | 747 | 1107 | 145028.9512 | 71887.274 | 73141.6772 | 67877.1847 | 72299.439 | 0.7608 | 0.01678 | 2.184 | 3.3636 | 228 | 53.3043 | 96 | 0 | 0 | 42.1769 | 2095 | 0
North Valley | 5388 | 29 | 72.8743 | 889 | 310.9714 | 180 | 4.4221e-05 | 2751.5793 | 10.3871 | 349.3117 | 1885.1373 | 51.2507 | 48.587 | 952.5859 | 1.4742 | 0.11235 | 0.00018503 | 0.032621 | 0.23434 | {A3CC161F-1B95-41A3-B30A-2B1FE8B4155F} | 103541103 | RED BLUFF 1103 | 1702 | 40.1649 | -122.2812 | RED BLUFF 11031702 | 242 | 218 | 46166.2792 | 29232.1064 | 16934.1727 | 26173.4534 | 13601.0083 | 0.033305 | 0.0079598 | 2.5129 | 4.9389 | 1465 | 20.2222 | 97 | 0 | 0 | 16.2634 | 822 | 0
North Valley | 5473 | 161 | 284.2182 | 641 | 417.996 | 162 | 5.0314e-05 | 2231.3693 | 45.3779 | 2497.6498 | 14757.2368 | 1069.1807 | 33.2325 | 548.0506 | 1.4446 | 0.11188 | 0.0012401 | 0.25117 | 0.67995 | {CB9FA698-E2B3-4923-A1DA-DA7C548C122C} | 103191101 | BANGOR 1101 | 80670 | 39.3883 | -121.4056 | BANGOR 110180670 | 205 | 210 | 36819.1235 | 26656.2925 | 10162.831 | 22220.3587 | 8471.2546 | 0.20089 | 0.0081509 | 1.7653 | 3.9568 | 310 | 18.1242 | 98 | 0 | 0 | 13.8071 | 2586 | 0
North Valley | 8205 | 1 | 1.945 | 2 | 2.4007 | 2 | 0.00010832 | 1324.8647 |  |  |  |  | 14.5055 | 1547.6884 | 1.9314 | 0.11176 | 0.00010832 | 0.5 | 0.81017 | {10DD30DF-F524-4738-873E-62FD1482AC8A} | 102781101 | ELK CREEK 1101 | 93504 | 39.593 | -122.5444 | ELK CREEK 110193504 | 23 | 11 | 4309.3871 | 4035.0912 | 274.296 | 3298.9383 | 234.6564 | 0.00021663 | 0.00021663 | 1.945 | 1 | 1812 | 0.22351 | 99 | 0 | 0 | 2.0499 | 378 | 0
North Valley | 6616 | 162 | 309.7671 | 1501 | 667.7438 | 251 | 5.9271e-05 | 1819.1409 | 88.2202 | 2038.06 | 20422.5427 | 3041.5224 | 29.4327 | 464.2851 | 1.4708 | 0.11024 | 0.0023456 | 0.10793 | 0.4639 | {B9D0806A-E952-4DB8-821A-8A74AB16F016} | 102931101 | COTTONWOOD 1101 | 68190 | 40.3649 | -122.4063 | COTTONWOOD 110168190 | 302 | 266 | 60538.5389 | 40765.2344 | 19773.3045 | 37929.7081 | 18487.6623 | 0.58874 | 0.014877 | 1.9121 | 5.9801 | 144 | 27.6706 | 100 | 0 | 0 | 23.5684 | 534 | 0
Sierra | 7282 | 53 | 81.7479 | 348 | 196.6707 | 66 | 0.00013475 | 808.6415 | 27.2373 | 473.8729 | 4314.4652 | 327.9218 | 15.8475 | 224.8214 | 1.3582 | 0.11023 | 0.0021594 | 0.1523 | 0.41566 | {5930D652-4C2C-456B-9C55-1601828B7C0A} | 153652108 | SHINGLE SPRINGS 2108 | 51476 | 38.6554 | -120.9934 | SHINGLE SPRINGS 210851476 | 113 | 58 | 14262.1466 | 10357.1601 | 3904.9865 | 7007.9313 | 2985.4971 | 0.14252 | 0.0088934 | 1.5424 | 5.2727 | 165 | 7.2751 | 101 | 0 | 0 | 4.3545 | 1391 | 0
North Coast | 4329 | 247 | 381.6576 | 487 | 457.8588 | 82 | 9.9826e-05 | 1068.1571 | 32.591 | 208.5491 | 875.1854 | 108.9793 | 21.6632 | 325.4825 | 1.6423 | 0.10882 | 0.001575 | 0.50719 | 0.83357 | {DE7AF2D5-E911-47A4-AE78-DD80A28A5D4B} | 43361103 | HIGHLANDS 1103 | 568 | 38.925 | -122.6069 | HIGHLANDS 1103568 | 174 | 389 | 36092.6725 | 14661.491 | 21431.1815 | 12324.8036 | 17253.5398 | 0.12915 | 0.0081858 | 1.5452 | 5.939 | 232 | 8.9233 | 102 | 0 | 0 | 7.6583 | 492 | 0
Sierra | 6761 | 221 | 331.3744 | 321 | 377.8091 | 58 | 5.2197e-05 | 2009.5893 | 7.9374 | 35.5483 | 148.8669 | 3.9612 | 37.0201 | 323.8098 | 1.2335 | 0.1087 | 0.00022232 | 0.68847 | 0.87709 | {DFD32DD3-B5D6-49B6-B12C-FD19CB6A2A45} | 63601111 | VACAVILLE 1111 | 13652 | 38.3801 | -121.9987 | VACAVILLE 111113652 | 90 | 74 | 12049.6083 | 6983.1183 | 5066.49 | 6983.1183 | 5066.49 | 0.012894 | 0.0030274 | 1.4994 | 5.5345 | 1335 | 6.3046 | 103 | 0 | 0 | 4.3391 | 720 | 0
Central Coast | 2632 | 14 | 34.7457 | 182 | 135.2156 | 36 | 3.6091e-05 | 2505.7275 | 33.398 | 308.7592 | 1023.3772 | 63.8123 | 39.2439 | 409.9625 | 1.4206 | 0.10715 | 0.00065373 | 0.076923 | 0.25696 | {2D7A19FE-1388-4016-A42B-7364F42C4D40} | 183041102 | BUELLTON 1102 | circuit_breaker | 34.625 | -120.1858 | BUELLTON 1102circuit_breaker | 244 | 375 | 41538.6655 | 20359.3308 | 21179.3347 | 8489.4268 | 3070.6037 | 0.023534 | 0.0012993 | 2.4818 | 5.0556 | 610 | 3.8574 | 104 | 0 | 0 | 5.2751 | 2062 | 0
North Valley | 864 | 108 | 274.9483 | 1994 | 762.8687 | 408 | 4.6528e-05 | 2635.7038 | 40.0752 | 1091.8506 | 6850.9303 | 774.8674 | 42.4766 | 999.3242 | 1.4646 | 0.10715 | 0.00077883 | 0.054162 | 0.36041 | {0CEFEC1C-E5A7-4802-97C4-53CDE555B5DF} | 103541101 | RED BLUFF 1101 | 1334 | 40.1792 | -122.2601 | RED BLUFF 11011334 | 743 | 676 | 130331.2465 | 89771.64 | 40559.6065 | 62500.9171 | 29801.0565 | 0.31776 | 0.018983 | 2.5458 | 4.8873 | 511 | 43.7155 | 105 | 0 | 0 | 38.8363 | 1431 | 0
Central Valley | 6138 | 55 | 120.9027 | 431 | 254.3043 | 85 | 4.6097e-05 | 2102.2275 | 4.1739 | 25.7901 | 200.6948 | 4.1199 | 30.8665 | 365.0295 | 1.6446 | 0.10489 | 0.00010652 | 0.12761 | 0.47543 | {2A4EBD50-37BC-4DE9-AE49-98B293AB7234} | 254432104 | COARSEGOLD 2104 | 10335 | 37.2274 | -119.7033 | COARSEGOLD 210410335 | 89 | 129 | 18762.0001 | 9369.0411 | 9392.959 | 9369.0411 | 9392.959 | 0.0090541 | 0.0039182 | 2.1982 | 5.0706 | 1822 | 8.9154 | 106 | 0 | 0 | 5.8217 | 90 | 0
Sierra | 4384 | 212 | 485.6519 | 1503 | 902.7604 | 241 | 7.8988e-05 | 1279.1459 | 29.7714 | 366.5287 | 1551.5977 | 78.8183 | 25.8289 | 287.5601 | 1.3164 | 0.10469 | 0.0010951 | 0.14105 | 0.53796 | {61206052-9537-4FFD-A305-D8F681D781BF} | 103191101 | BANGOR 1101 | 82350 | 39.3222 | -121.3949 | BANGOR 110182350 | 395 | 336 | 62243.5619 | 35380.8633 | 26862.6986 | 30346.6456 | 20482.9611 | 0.26393 | 0.019036 | 2.2908 | 6.2365 | 364 | 25.231 | 107 | 0 | 0 | 18.8565 | 216 | 0
North Coast | 9084 | 42 | 56.6299 | 98 | 74.5322 | 14 | 4.9139e-05 | 1893.0432 | 0.10902 | 3.7982 | 47.4389 | 0.39007 | 34.4033 | 213.7731 | 1.4346 | 0.10421 | 2.478e-05 | 0.42857 | 0.7598 | {801F0074-FB1F-4C52-9EC5-EE9281D564FB} | 43211101 | HARTLEY 1101 | 4710 | 39.0402 | -122.9314 | HARTLEY 11014710 | 22 | 10 | 2920.5126 | 2414.0517 | 506.461 | 2414.0517 | 506.461 | 0.00034691 | 0.00068794 | 1.3483 | 7 | 2537 | 1.459 | 108 | 0 | 0 | 1.5 | 369 | 0
Central Valley | 4268 | 168 | 368.839 | 629 | 521.8383 | 197 | 2.0014e-05 | 5306.7069 | 99.7682 | 8082.4835 | 64538.5956 | 8739.4188 | 67.9298 | 1373.5313 | 1.7778 | 0.10339 | 0.00089813 | 0.26709 | 0.70681 | {72B3FD6E-4E00-4CD9-8668-70733AC266B2} | 254151102 | AUBERRY 1102 | 37466 | 37.012 | -119.5269 | AUBERRY 110237466 | 448 | 366 | 85086.0453 | 50914.8919 | 34171.1534 | 50295.1648 | 34016.001 | 0.17693 | 0.0039428 | 2.1955 | 3.1929 | 446 | 20.3675 | 109 | 0 | 0 | 31.252 | 1805 | 0
North Valley | 9386 | 13 | 17.4314 | 25 | 22.5658 | 3 | 7.0784e-05 | 1366.5155 | 0.014791 | 0.45413 | 1.0715 | 0.0024206 | 24.5789 | 552.9987 | 1.2493 | 0.10306 | 4.3649e-05 | 0.52 | 0.77247 | {E6C812B7-52C7-47F0-B595-32AF66AB7A9D} | 103091102 | CLARK ROAD 1102 | circuit_breaker | 39.6546 | -121.6352 | CLARK ROAD 1102circuit_breaker | 32 | 14 | 3132.7397 | 2454.6663 | 678.0734 | 1038.6996 | 103.8186 | 0.00013095 | 0.00021235 | 1.3409 | 8.3333 | 2293 | 0.30919 | 110 | 0 | 0 | 0.64542 | 1640 | 0
Sierra | 7209 | 382 | 703.726 | 1309 | 983.3752 | 192 | 6.5e-05 | 1668.4657 | 18.5867 | 436.5298 | 1886.6257 | 60.8051 | 25.4042 | 483.4252 | 1.3364 | 0.10238 | 0.00052224 | 0.29183 | 0.71562 | {77D006A2-E276-4C22-A5B0-EE84D8EA3177} | 152921101 | BROWNS VALLEY 1101 | 93870 | 39.2279 | -121.4142 | BROWNS VALLEY 110193870 | 473 | 411 | 83886.0385 | 54425.7608 | 29460.2777 | 28752.0223 | 15923.8956 | 0.10027 | 0.01248 | 1.8422 | 6.8177 | 773 | 19.6578 | 111 | 0 | 0 | 17.8657 | 1714 | 0
Sierra | 4869 | 108 | 211.0516 | 284 | 277.2858 | 59 | 5.0442e-05 | 1901.238 | 49.7221 | 447.7067 | 2367.7386 | 161.662 | 26.8018 | 492.0508 | 1.56 | 0.10177 | 0.0011289 | 0.38028 | 0.76113 | {FD236456-FD03-4755-9CCD-003D8F61CBAE} | 152282101 | MOUNTAIN QUARRIES 2101 | 6953 | 38.8983 | -120.9827 | MOUNTAIN QUARRIES 21016953 | 77 | 80 | 17193.7085 | 9165.9911 | 8027.7174 | 9165.9911 | 8027.7174 | 0.066604 | 0.0029761 | 1.9542 | 4.8136 | 351 | 6.0045 | 112 | 0 | 0 | 5.6955 | 1330 | 0
Central Coast | 1685 | 308 | 711.7761 | 1032 | 1127.3588 | 134 | 3.1436e-05 | 3059.859 | 63.1596 | 420.4057 | 1272.9016 | 157.2141 | 50.371 | 354.9901 | 1.354 | 0.10135 | 0.00098062 | 0.29845 | 0.63137 | {BE22BF5B-77AE-4173-893E-2D7D15CAA658} | 183041102 | BUELLTON 1102 | Y50 | 34.6125 | -120.1757 | BUELLTON 1102Y50 | 288 | 326 | 40304.2685 | 20629.3397 | 19674.9288 | 17178.6356 | 12460.4514 | 0.1314 | 0.0042125 | 2.311 | 7.7015 | 418 | 13.5803 | 113 | 0 | 0 | 10.6743 | 33 | 0
Sierra | 5653 | 110 | 185.898 | 368 | 285.31 | 49 | 6.164e-05 | 1773.9617 | 18.7242 | 174.9025 | 893.1002 | 32.6475 | 26.8544 | 197.1261 | 1.3698 | 0.10107 | 0.00060858 | 0.29891 | 0.65156 | {070C906B-0802-4429-8F7B-A68007FED9B4} | 152531101 | FLINT 1101 | 750 | 38.8694 | -121.0803 | FLINT 1101750 | 171 | 226 | 29048.0032 | 14953.9778 | 14094.0255 | 7461.0283 | 4660.2429 | 0.02982 | 0.0030204 | 1.69 | 7.5102 | 660 | 4.9524 | 114 | 0 | 0 | 4.6361 | 860 | 0
Sierra | 3978 | 562 | 822.1551 | 1193 | 1108.0498 | 164 | 3.4601e-05 | 3406.1104 | 52.4525 | 492.753 | 3063.4389 | 397.9707 | 42.5248 | 789.4242 | 1.6533 | 0.10044 | 0.00058541 | 0.47108 | 0.74198 | {82F07A4A-6ADB-4C33-B8E8-182597EEA877} | 63601104 | VACAVILLE 1104 | 6542 | 38.3422 | -122.0077 | VACAVILLE 11046542 | 197 | 153 | 35644.5975 | 23785.8023 | 11858.7951 | 23785.8023 | 11858.7951 | 0.096008 | 0.0056746 | 1.4629 | 7.2744 | 685 | 16.4715 | 115 | 0 | 0 | 14.7798 | 1749 | 0
Central Valley | 1015 | 239 | 641.7124 | 1137 | 919.9794 | 322 | 3.8448e-05 | 2672.3237 | 50.0085 | 1069.8761 | 5702.7172 | 761.6869 | 38.0922 | 696.1031 | 1.4671 | 0.1004 | 0.00091195 | 0.2102 | 0.69753 | {B537B104-D44A-45F9-BCC9-AE639B2EEDC6} | 162991101 | CORRAL 1101 | 36652 | 38.1784 | -120.9257 | CORRAL 110136652 | 479 | 524 | 76483.8468 | 58059.3769 | 18424.4699 | 58059.3769 | 18424.4699 | 0.29365 | 0.01238 | 2.685 | 3.5311 | 440 | 32.3296 | 116 | 0 | 0 | 36.0764 | 2002 | 0
Central Valley | 1458 | 117 | 204.8869 | 598 | 349.9863 | 151 | 3.0127e-05 | 3418.1518 | 80.3116 | 1588.9636 | 13859.0931 | 3328.9196 | 51.8204 | 636.7029 | 1.5375 | 0.10004 | 0.0012117 | 0.19565 | 0.58541 | {50F15232-B267-496F-ACCD-C66670CD5E1D} | 254151101 | AUBERRY 1101 | circuit_breaker | 37.0683 | -119.4966 | AUBERRY 1101circuit_breaker | 337 | 301 | 47926.6633 | 29094.1652 | 18832.4981 | 29094.1652 | 18832.4981 | 0.18296 | 0.0045491 | 1.7512 | 3.9603 | 322 | 15.1058 | 117 | 0 | 0 | 18.0783 | 2143 | 0
Central Valley | 167 | 97 | 247.9289 | 293 | 305.1923 | 102 | 8.5364e-05 | 984.301 | 98.0134 | 795.6317 | 4878.9291 | 542.0731 | 13.5625 | 575.5548 | 1.6537 | 0.098378 | 0.0043761 | 0.33106 | 0.81237 | {964B7091-3309-4D13-897C-3C72D5D00A0F} | 163231101 | NORTH BRANCH 1101 | 11206 | 38.1859 | -120.8251 | NORTH BRANCH 110111206 | 181 | 192 | 41331.3902 | 28777.6676 | 12553.7227 | 28150.1513 | 12540.8205 | 0.44636 | 0.0087071 | 2.556 | 2.8725 | 48 | 10.0345 | 118 | 0 | 0 | 17.4917 | 2000 | 0
Central Valley | 4692 | 195 | 284.2025 | 761 | 517.8409 | 183 | 3.4712e-05 | 2932.7749 | 48.0033 | 470.6577 | 3545.4048 | 272.661 | 35.6727 | 665.2995 | 1.6131 | 0.098165 | 0.00085657 | 0.25624 | 0.54882 | {778182E4-2AE7-465E-B2C9-C1ED6A0D9207} | 254421103 | OAKHURST 1103 | 63334 | 37.3839 | -119.6785 | OAKHURST 110363334 | 221 | 224 | 39160.3036 | 27690.7454 | 11469.5582 | 27690.7454 | 11469.5582 | 0.15675 | 0.0063522 | 1.4574 | 4.1585 | 468 | 17.9641 | 119 | 0 | 0 | 17.2062 | 1709 | 0
North Coast | 4752 | 98 | 130.8479 | 249 | 183.5884 | 64 | 6.7509e-05 | 1415.4395 | 1.4845 | 86.8475 | 854.6517 | 3.5026 | 19.9333 | 742.9544 | 1.6218 | 0.098139 | 8.6812e-05 | 0.39357 | 0.71272 | {14B018BB-E4F3-4418-8464-262A2B2FE900} | 43211101 | HARTLEY 1101 | 698 | 39.0803 | -122.9513 | HARTLEY 1101698 | 117 | 118 | 28812.8788 | 16608.1598 | 12204.719 | 9794.4645 | 7405.3166 | 0.005556 | 0.0043206 | 1.3352 | 3.8906 | 1933 | 6.2809 | 120 | 0 | 0 | 6.086 | 980 | 0
North Valley | 2349 | 76 | 131.4034 | 319 | 203.2759 | 51 | 4.7288e-05 | 2536.0683 | 33.824 | 217.3008 | 753.201 | 33.821 | 51.2717 | 404.224 | 1.3624 | 0.097361 | 0.00084643 | 0.23824 | 0.64643 | {FC542AC7-29DE-47A0-A073-41001E21B2E1} | 102911109 | WYANDOTTE 1109 | 1520 | 39.4583 | -121.5318 | WYANDOTTE 11091520 | 392 | 694 | 68729.8516 | 31750.549 | 36979.3026 | 5746.3127 | 4012.8665 | 0.043168 | 0.0024117 | 1.729 | 6.2549 | 473 | 4.9654 | 121 | 0 | 0 | 3.5706 | 87 | 0
Sierra | 8695 | 39 | 53.9806 | 158 | 99.4697 | 25 | 7.3577e-05 | 1286.319 | 24.92 | 584.5518 | 2605.0054 | 103.3673 | 23.667 | 640.4992 | 1.5706 | 0.096932 | 0.0010301 | 0.24684 | 0.54268 | {C1372A39-5F1C-45B4-BF7F-8FD49647E669} | 152921101 | BROWNS VALLEY 1101 | 17011 | 39.2691 | -121.3691 | BROWNS VALLEY 110117011 | 26 | 38 | 5527.9465 | 3005.3172 | 2522.6293 | 3005.3172 | 2522.6293 | 0.025753 | 0.0018394 | 1.3841 | 6.32 | 397 | 2.4233 | 122 | 0 | 0 | 1.8674 | 1411 | 0
North Valley | 5352 | 34 | 51.1687 | 353 | 136.7563 | 92 | 4.2469e-05 | 2265.1496 | 35.133 | 2843.8354 | 18426.5354 | 1320.2916 | 23.3861 | 2250.1425 | 1.7424 | 0.096529 | 0.00061638 | 0.096317 | 0.37416 | {8FC5AABE-9067-41E2-B562-CCB95292040F} | 103571105 | TYLER 1105 | 1536 | 40.158 | -122.3539 | TYLER 11051536 | 84 | 62 | 35906.0445 | 28821.608 | 7084.4365 | 27372.4849 | 5970.6509 | 0.056707 | 0.0039071 | 1.505 | 3.837 | 654 | 8.8807 | 123 | 0 | 0 | 17.0085 | 811 | 0
North Valley | 7852 | 64 | 103.5882 | 92 | 112.1328 | 29 | 7.7835e-05 | 1156.7767 | 0 | 0 | 0 | 0 | 11.2843 | 1867.15 | 1.7991 | 0.095618 | 7.532e-05 | 0.69565 | 0.9238 | {5BD647F3-321C-4EB8-8B86-BFCBA1FC85D4} | 102781101 | ELK CREEK 1101 | 2002 | 39.5905 | -122.5402 | ELK CREEK 11012002 | 127 | 78 | 50566.1659 | 48388.1891 | 2177.9768 | 24592.8123 | 1071.479 | 0.0021843 | 0.0022572 | 1.6186 | 3.1724 | 2017 | 2.7729 | 124 | 0 | 0 | 15.2813 | 592 | 0
North Valley | 7087 | 157 | 216.2442 | 259 | 254.2449 | 43 | 8.9968e-05 | 947.6039 | 45.9782 | 438.1427 | 3576.4482 | 360.8654 | 18.0648 | 218.7449 | 1.2614 | 0.095517 | 0.0021355 | 0.60618 | 0.85054 | {57A4B509-FD84-475C-B34A-463055A0DAF6} | 103521103 | OREGON TRAIL 1103 | circuit_breaker | 40.6191 | -122.3222 | OREGON TRAIL 1103circuit_breaker | 59 | 44 | 7714.7114 | 4700.2679 | 3014.4434 | 4346.4203 | 3014.4434 | 0.091826 | 0.0038686 | 1.3774 | 6.0233 | 168 | 4.1072 | 125 | 0 | 0 | 2.7007 | 2524 | 0
North Valley | 247 | 470 | 943.7882 | 868 | 1072.6813 | 166 | 4.7232e-05 | 2125.1514 | 33.8972 | 1456.1519 | 8346.2117 | 499.8238 | 30.7559 | 718.9246 | 1.5247 | 0.095332 | 0.00077059 | 0.54147 | 0.87984 | {E681E40E-5ECE-4E9E-921D-C13E15C00CCA} | 103091102 | CLARK ROAD 1102 | 2582 | 39.657 | -121.6312 | CLARK ROAD 11022582 | 269 | 196 | 48916.7155 | 33761.1198 | 15155.5957 | 32088.8606 | 13553.944 | 0.12792 | 0.0078405 | 2.0081 | 5.2289 | 518 | 15.8251 | 126 | 0 | 0 | 19.9391 | 1135 | 0
North Coast | 7841 | 40 | 50.419 | 254 | 101.1376 | 38 | 5.9237e-05 | 1598.1563 | 1.4886 | 36.5937 | 420.2469 | 2.8515 | 30.3641 | 220.7792 | 1.3773 | 0.094821 | 7.6167e-05 | 0.15748 | 0.49852 | {270933AB-36E0-4F19-9FD5-2CA707CDE013} | 42141102 | CLEAR LAKE 1102 | 904 | 39.0183 | -122.9168 | CLEAR LAKE 1102904 | 46 | 48 | 9139.0864 | 5777.0339 | 3362.0525 | 5254.2064 | 3010.6144 | 0.0028943 | 0.002251 | 1.2605 | 6.6842 | 2010 | 3.6032 | 127 | 0 | 0 | 3.2648 | 2558 | 0
Sierra | 7750 | 15 | 29.0167 | 29 | 34.4117 | 4 | 9.7034e-05 | 1999.3364 | 0.11318 | 0.22239 | 0.7207 | 8.1808e-05 | 28.2566 | 319.7348 | 1.2948 | 0.094696 | 6.0984e-05 | 0.51724 | 0.84322 | {7686CD28-0AD3-49A6-802B-4CD3DF814107} | 153612109 | CLARKSVILLE 2109 | circuit_breaker | 38.6558 | -121.0599 | CLARKSVILLE 2109circuit_breaker | 33 | 7 | 2062.0432 | 1811.3753 | 250.6679 | 1633.6693 | 190.7949 | 0.00024394 | 0.00038813 | 1.9344 | 7.25 | 2125 | 0.37879 | 128 | 0 | 0 | 1.0151 | 2499 | 0
North Valley | 2668 | 44 | 131.2366 | 168 | 164.7956 | 55 | 6.0309e-05 | 1943.8445 | 22.948 | 160.124 | 712.2418 | 16.3445 | 18.3665 | 1972.462 | 1.7283 | 0.094586 | 0.00012657 | 0.2619 | 0.79636 | {D0CAFA51-0A62-4D26-BA1A-5435FD46CC21} | 102781101 | ELK CREEK 1101 | 37334 | 39.5937 | -122.5444 | ELK CREEK 110137334 | 114 | 179 | 19829.3101 | 15414.1675 | 4415.1426 | 15414.1675 | 4415.1426 | 0.0069612 | 0.003317 | 2.9826 | 3.0545 | 1714 | 5.2022 | 129 | 0 | 0 | 9.5779 | 2830 | 0
Central Valley | 2050 | 100 | 204.7189 | 508 | 351.5657 | 133 | 4.6504e-05 | 2072.4119 | 81.6494 | 1067.2872 | 9353.6101 | 3005.784 | 28.7919 | 728.7502 | 1.6273 | 0.094564 | 0.0016449 | 0.19685 | 0.58231 | {19623F95-3D51-435E-B42C-17FE4878C880} | 254432103 | COARSEGOLD 2103 | 5020 | 37.2065 | -119.7141 | COARSEGOLD 21035020 | 209 | 190 | 41345.6206 | 26968.3187 | 14377.3019 | 25953.2029 | 13841.9547 | 0.21878 | 0.006185 | 2.0472 | 3.8195 | 217 | 12.577 | 130 | 0 | 0 | 16.1266 | 1365 | 0
Central Valley | 912 | 103 | 300.4785 | 655 | 463.6836 | 200 | 3.1636e-05 | 2995.4199 | 43.4083 | 2051.0832 | 10277.5082 | 571.9188 | 46.175 | 819.2795 | 1.4427 | 0.093359 | 0.00068418 | 0.15725 | 0.64802 | {67B48D0E-E0F7-48F9-B3C0-C31311AFB61B} | 162991101 | CORRAL 1101 | circuit_breaker | 38.1015 | -120.9263 | CORRAL 1101circuit_breaker | 390 | 342 | 57479.9694 | 44068.152 | 13411.8174 | 42004.2216 | 13265.2758 | 0.13684 | 0.0063271 | 2.9173 | 3.275 | 582 | 18.6718 | 131 | 0 | 0 | 26.1002 | 560 | 0
Sierra | 6448 | 5 | 10.1423 | 56 | 28.9048 | 16 | 6.2621e-05 | 1260.9933 | 39.5458 | 180.0658 | 793.3118 | 45.0106 | 28.7688 | 320.8026 | 1.2674 | 0.093164 | 0.0004427 | 0.089286 | 0.35089 | {A3D1D6B2-C2DB-46A7-9A60-CC55ABB31E62} | 152582109 | DEL MAR 2109 | circuit_breaker | 38.7989 | -121.2209 | DEL MAR 2109circuit_breaker | 134 | 110 | 18273.7512 | 10524.7005 | 7749.0507 | 3009.0839 | 1086.1462 | 0.0070831 | 0.0010019 | 2.0285 | 3.5 | 877 | 1.4906 | 132 | 0 | 0 | 1.8698 | 304 | 0
North Valley | 1486 | 414 | 1017.2703 | 1596 | 1336.6516 | 253 | 4.7023e-05 | 2110.0806 | 54.612 | 1269.6359 | 7060.8352 | 704.5353 | 41.1153 | 503.4244 | 1.3445 | 0.092604 | 0.0011409 | 0.2594 | 0.76106 | {67B8C4D8-FEA1-4243-99E7-B5C8BD7D2FA9} | 102911109 | WYANDOTTE 1109 | 79932 | 39.4313 | -121.5348 | WYANDOTTE 110979932 | 475 | 471 | 85198.4115 | 52503.3015 | 32695.11 | 34098.0677 | 19567.5529 | 0.28866 | 0.011897 | 2.4572 | 6.3083 | 347 | 23.4289 | 133 | 0 | 0 | 21.1876 | 188 | 0
North Valley | 1206 | 1 | 1.2277 | 5 | 2.5086 | 3 | 3.7751e-05 | 3000.7677 | 0.81025 | 1.7792 | 4.0377 | 0.0065431 | 44.4801 | 875.9762 | 1.4897 | 0.09231 | 3.2397e-05 | 0.2 | 0.4894 | {7FAC2369-AB0B-45B1-8121-0A58A05D1C75} | 103541103 | RED BLUFF 1103 | circuit_breaker | 40.1823 | -122.2446 | RED BLUFF 1103circuit_breaker | 576 | 1856 | 97907.6357 | 31613.5881 | 66294.0476 | 126.6017 | 70.7651 | 9.7192e-05 | 0.00011325 | 1.2277 | 1.6667 | 2434 | 0.27693 | 134 | 0 | 0 | 0.078667 | 2394 | 0
North Valley | 3497 | 146 | 312.0504 | 432 | 399.944 | 98 | 6.2598e-05 | 1653.0311 | 33.3673 | 609.1502 | 3873.5739 | 320.9599 | 40.8575 | 380.6115 | 1.3267 | 0.092286 | 0.0010932 | 0.33796 | 0.78024 | {14C3CF81-5A6E-4ADC-BDB6-EF5B849D6F19} | 103441102 | JESSUP 1102 | 96554 | 40.4389 | -122.4076 | JESSUP 110296554 | 270 | 347 | 45430.7583 | 24227.1624 | 21203.5959 | 12714.8897 | 8617.4202 | 0.10713 | 0.0061346 | 2.1373 | 4.4082 | 365 | 9.0441 | 135 | 0 | 0 | 7.9007 | 2370 | 0
Sierra | 81 | 193 | 394.8585 | 592 | 517.9431 | 144 | 3.2671e-05 | 2514.2942 | 45.6742 | 1401.9901 | 6157.2896 | 521.8995 | 47.5706 | 1101.0673 | 1.5274 | 0.091663 | 0.00060199 | 0.32601 | 0.76236 | {302C4176-4830-4D29-8953-2FECE7A076EF} | 153701104 | LINCOLN 1104 | 51756 | 38.9268 | -121.2933 | LINCOLN 110451756 | 639 | 427 | 127223.0021 | 91590.9005 | 35632.1016 | 24962.2729 | 11343.8679 | 0.086686 | 0.0047046 | 2.0459 | 4.1111 | 667 | 13.1994 | 136 | 0 | 0 | 15.5108 | 212 | 0
Central Valley | 7203 | 95 | 290.2529 | 427 | 392.5125 | 124 | 3.6728e-05 | 2460.316 | 59.5906 | 2509.0811 | 14443.6625 | 1943.1817 | 37.1112 | 614.8876 | 1.407 | 0.091485 | 0.0010828 | 0.22248 | 0.73947 | {BB1AB0D8-04B4-4BAF-B0BB-9DFA5174A1E7} | 162991101 | CORRAL 1101 | 12608 | 38.1339 | -120.9255 | CORRAL 110112608 | 246 | 268 | 36355.7135 | 27099.2397 | 9256.4738 | 27099.2397 | 9256.4738 | 0.13426 | 0.0045543 | 3.0553 | 3.4435 | 371 | 11.3441 | 137 | 0 | 0 | 16.8387 | 1144 | 0
Sierra | 6949 | 75 | 147.5402 | 416 | 287.0962 | 80 | 5.6399e-05 | 1702.0971 | 33.6348 | 232.7704 | 1378.8486 | 77.1565 | 38.077 | 249.4701 | 1.2283 | 0.090399 | 0.00098133 | 0.18029 | 0.51391 | {2EBA7959-7933-4246-BD38-55C2DE2602D7} | 152271102 | WISE 1102 | 2234 | 38.8955 | -121.1358 | WISE 11022234 | 257 | 280 | 40412.5812 | 24231.786 | 16180.7952 | 24231.786 | 16180.7952 | 0.078507 | 0.0045119 | 1.9672 | 5.2 | 417 | 7.2319 | 138 | 0 | 0 | 15.0569 | 124 | 0
Sierra | 8888 | 1 | 1.2277 | 9 | 4.584 | 4 | 1.6355e-05 | 5450.1776 | 114.657 | 436.9584 | 2142.1054 | 245.9743 | 59.1256 | 1982.2803 | 2.1117 | 0.089773 | 0.00097103 | 0.11111 | 0.26783 | {BC2B156B-5F07-4313-BE60-34EF88AFE911} | 63642108 | PEABODY 2108 | circuit_breaker | 38.2853 | -121.9704 | PEABODY 2108circuit_breaker | 52 | 23 | 6627.7078 | 4968.214 | 1659.4938 | 604.4135 | 779.7385 | 0.0038841 | 6.5421e-05 | 1.2277 | 2.25 | 426 | 0.35909 | 139 | 0 | 0 | 0.37556 | 451 | 0
Sierra | 1224 | 975 | 1585.4656 | 2769 | 2314.6614 | 281 | 6.8462e-05 | 1483.2119 | 15.3175 | 73.5946 | 319.6389 | 13.1773 | 29.8801 | 186.1792 | 1.1945 | 0.089249 | 0.00046415 | 0.35211 | 0.68497 | {15328E03-B147-4A5F-A6DD-FF57B3032B26} | 152561103 | PENRYN 1103 | 2198 | 38.8637 | -121.1286 | PENRYN 11032198 | 404 | 409 | 57566.5525 | 33526.3958 | 24040.1567 | 32169.4149 | 23145.2757 | 0.13043 | 0.019238 | 1.6261 | 9.8541 | 840 | 25.0789 | 140 | 0 | 0 | 19.9891 | 42 | 0
Central Coast | 2756 | 53 | 88.1955 | 341 | 237.2304 | 41 | 5.4061e-05 | 1738.1186 | 34.1427 | 139.2262 | 403.7672 | 69.0672 | 57.4115 | 256.7444 | 1.6069 | 0.089128 | 0.00079389 | 0.15543 | 0.37177 | {6170E12A-002A-40B3-A4BB-42077F0D87F0} | 182681102 | ZACA 1102 | Y48 | 34.6653 | -120.1182 | ZACA 1102Y48 | 263 | 210 | 34334.512 | 19086.044 | 15248.468 | 6193.8861 | 3105.3463 | 0.032549 | 0.0022165 | 1.6641 | 8.3171 | 502 | 3.6543 | 141 | 0 | 0 | 3.8487 | 2206 | 0
Sierra | 2066 | 2 | 5.0295 | 10 | 8.0185 | 5 | 5.4989e-05 | 1963.6216 | 24.9366 | 682.3538 | 3881.0645 | 100.6795 | 40.2314 | 815.8776 | 1.3115 | 0.088432 | 0.00083564 | 0.2 | 0.62724 | {C124863D-A80A-417C-8673-B1FFE62E6401} | 153701104 | LINCOLN 1104 | 5391 | 38.9449 | -121.2375 | LINCOLN 11045391 | 9 | 2 | 1836.0694 | 1530.1829 | 305.8865 | 1530.1829 | 305.8865 | 0.0041782 | 0.00027494 | 2.5148 | 2 | 484 | 0.44216 | 142 | 0 | 0 | 0.95081 | 194 | 0
Sierra | 2772 | 21 | 25.782 | 54 | 38.1028 | 12 | 6.2217e-05 | 1443.2754 | 43.0318 | 174.7103 | 629.1784 | 38.2172 | 32.7627 | 349.1657 | 1.2745 | 0.088193 | 0.00088329 | 0.38889 | 0.67664 | {2BBB97CC-A78B-43EC-BEB0-66A2E29BC2E3} | 152561106 | PENRYN 1106 | 51674 | 38.8252 | -121.1919 | PENRYN 110651674 | 327 | 631 | 49160.5507 | 19482.4094 | 29678.1413 | 1609.198 | 399.2346 | 0.0106 | 0.0007466 | 1.2277 | 4.5 | 455 | 1.0583 | 143 | 0 | 0 | 0.99991 | 1389 | 0
Central Valley | 6934 | 61 | 107.4614 | 312 | 204.1544 | 56 | 7.2587e-05 | 1662.0001 | 11.2868 | 393.8047 | 3200.6156 | 150.7955 | 15.9691 | 443.8513 | 1.426 | 0.087976 | 0.00030048 | 0.19551 | 0.52637 | {D55632F8-2CFE-45BD-8046-185433E1F9AE} | 254452102 | MARIPOSA 2102 | 440236 | 37.4867 | -119.9603 | MARIPOSA 2102440236 | 62 | 53 | 12924.3418 | 6819.7347 | 6104.6071 | 6786.4552 | 6040.5207 | 0.016827 | 0.0040648 | 1.7617 | 5.5714 | 1124 | 4.9267 | 144 | 0 | 0 | 4.2169 | 1 | 0
Central Coast | 1949 | 3 | 9.3442 | 21 | 17.5474 | 5 | 2.6621e-05 | 3289.6308 | 22.4903 | 786.4778 | 4193.856 | 105.0312 | 51.281 | 884.1833 | 1.8058 | 0.087117 | 0.00039998 | 0.14286 | 0.53251 | {9DE0BAA2-B8C4-4631-BEBA-CFB3AF750506} | 182661105 | SAN MIGUEL 1105 | circuit_breaker | 35.7522 | -120.6844 | SAN MIGUEL 1105circuit_breaker | 181 | 535 | 34348.9156 | 16697.3527 | 17651.5629 | 2410.7396 | 426.9832 | 0.0019999 | 0.0001331 | 3.1147 | 4.2 | 944 | 0.43559 | 145 | 0 | 0 | 1.498 | 2688 | 0
North Valley | 3223 | 12 | 25.5799 | 171 | 68.2282 | 35 | 4.7133e-05 | 1631.492 | 10.0338 | 197.3484 | 775.2394 | 18.6113 | 24.5824 | 727.4241 | 1.4831 | 0.086668 | 0.00037894 | 0.070175 | 0.37492 | {38F7B678-11EB-498C-AD48-774BD4B8786F} | 103261103 | ANDERSON 1103 | 1600 | 40.4764 | -122.243 | ANDERSON 11031600 | 140 | 152 | 26459.6908 | 17298.4129 | 9161.2779 | 4989.8706 | 2292.2732 | 0.013263 | 0.0016496 | 2.1317 | 4.8857 | 970 | 3.0334 | 146 | 0 | 0 | 3.1006 | 1855 | 0
Sierra | 5513 | 110 | 205.7792 | 650 | 389.9501 | 118 | 8.2724e-05 | 1237.4509 | 14.8651 | 239.182 | 2192.2298 | 100.8096 | 23.0462 | 290.472 | 1.3942 | 0.086667 | 0.00066754 | 0.16923 | 0.52771 | {4BF4ABD1-69F5-49AA-B8C3-8117FD378308} | 153652109 | SHINGLE SPRINGS 2109 | 35598 | 38.7638 | -120.9265 | SHINGLE SPRINGS 210935598 | 194 | 152 | 29114.3025 | 17564.7145 | 11549.588 | 17564.7145 | 11549.588 | 0.078769 | 0.0097615 | 1.8707 | 5.5085 | 600 | 10.2267 | 147 | 0 | 0 | 10.9142 | 464 | 0
Central Valley | 3761 | 178 | 470.3165 | 647 | 616.8412 | 201 | 1.6582e-05 | 5317.5439 | 60.7229 | 7316.2442 | 46094.343 | 3057.24 | 62.4398 | 1295.3542 | 1.7202 | 0.086089 | 0.00044968 | 0.27512 | 0.76246 | {2D5FBF93-4F75-44A4-A3B6-356A65A990D3} | 254601103 | SAND CREEK 1103 | 7140 | 36.6751 | -119.1899 | SAND CREEK 11037140 | 402 | 365 | 69561.5423 | 42354.6264 | 27206.9158 | 42354.6264 | 27206.9158 | 0.090385 | 0.0033331 | 2.6422 | 3.2189 | 863 | 17.3038 | 148 | 0 | 0 | 26.3179 | 18 | 0
Bay Area | 8315 | 40 | 71.6689 | 140 | 119.8892 | 26 | 2.306e-05 | 4126.9244 | 6.2041 | 1360.1749 | 8580.1532 | 83.4794 | 49.4767 | 1669.4983 | 1.5208 | 0.085959 | 7.3662e-05 | 0.28571 | 0.59779 | {4726E885-2A0B-4F7A-A1C6-DDA1FAC8240F} | 14052103 | NORTH DUBLIN 2103 | 11101 | 37.7941 | -121.8385 | NORTH DUBLIN 210311101 | 52 | 61 | 9570.9042 | 5926.9536 | 3643.9506 | 5926.9536 | 3643.9506 | 0.0019152 | 0.00059956 | 1.7917 | 5.3846 | 2031 | 2.2349 | 149 | 0 | 0 | 3.6828 | 2428 | 0
Sierra | 1508 | 1247 | 1978.4214 | 3437 | 2826.3228 | 381 | 6.3826e-05 | 1454.5313 | 25.1185 | 208.4954 | 867.3815 | 48.0643 | 30.3275 | 232.1896 | 1.2142 | 0.085749 | 0.00069166 | 0.36282 | 0.7 | {85595727-53BD-4D84-AD35-800A5DE277DF} | 152701107 | BELL 1107 | 2400 | 38.9452 | -121.1222 | BELL 11072400 | 477 | 559 | 81344.1814 | 44455.198 | 36888.9834 | 40028.1973 | 32617.4711 | 0.26352 | 0.024318 | 1.5865 | 9.021 | 573 | 32.6703 | 150 | 0 | 0 | 24.8724 | 2209 | 0
Central Valley | 6785 | 53 | 114.8452 | 472 | 244.9692 | 115 | 3.1356e-05 | 2684.3156 | 97.8851 | 3756.2191 | 33902.609 | 7057.5035 | 38.7239 | 536.4042 | 1.5175 | 0.08541 | 0.0014984 | 0.11229 | 0.46881 | {71E8F95F-8504-4520-9C3B-8AB71CD7CDDD} | 254151102 | AUBERRY 1102 | R1013 | 37.0452 | -119.4864 | AUBERRY 1102R1013 | 169 | 144 | 30632.0954 | 19936.8067 | 10695.2887 | 19936.8067 | 10695.2887 | 0.17232 | 0.003606 | 2.1669 | 4.1043 | 246 | 9.8222 | 151 | 0 | 0 | 12.3882 | 64 | 0
Sierra | 2440 | 106 | 219.4927 | 795 | 453.368 | 135 | 8.1428e-05 | 1049.7606 | 25.5111 | 371.6119 | 1624.8058 | 81.7182 | 21.2373 | 398.4935 | 1.4051 | 0.084535 | 0.0010273 | 0.13333 | 0.48414 | {868A573A-DC6D-45C3-92E0-27ABE99A6BF7} | 152921101 | BROWNS VALLEY 1101 | 1268 | 39.2871 | -121.3894 | BROWNS VALLEY 11011268 | 158 | 130 | 26840.259 | 17550.3384 | 9289.9206 | 17547.6887 | 9289.9206 | 0.13869 | 0.010993 | 2.0707 | 5.8889 | 400 | 11.4123 | 152 | 0 | 0 | 10.9036 | 1360 | 0
North Valley | 7386 | 22 | 69.7086 | 353 | 146.0689 | 82 | 3.8849e-05 | 2171.0386 | 21.4223 | 242.2161 | 1302.7749 | 95.494 | 35.3192 | 625.7471 | 1.5133 | 0.084485 | 0.00039454 | 0.062323 | 0.47723 | {737A9C64-4C75-4B29-81A5-32595FB9B2D8} | 103541101 | RED BLUFF 1101 | 76020 | 40.2103 | -122.2705 | RED BLUFF 110176020 | 204 | 156 | 37114.1263 | 23337.4414 | 13776.6849 | 14298.5591 | 8520.2828 | 0.032352 | 0.0031856 | 3.1686 | 4.3049 | 952 | 6.9278 | 153 | 0 | 0 | 8.8847 | 366 | 0
Bay Area | 4128 | 222 | 520.868 | 672 | 712.4157 | 118 | 3.8139e-05 | 2507.6221 | 36.749 | 703.6139 | 3359.296 | 449.3418 | 33.2837 | 1400.3778 | 1.5836 | 0.084394 | 0.00055085 | 0.33036 | 0.73113 | {1E6D2AC0-4EEF-47FA-8309-E46E41F6921D} | 12022212 | CLAYTON 2212 | 2944 | 37.897 | -121.8596 | CLAYTON 22122944 | 185 | 137 | 30989.2604 | 23740.8312 | 7248.4292 | 23517.364 | 7090.2635 | 0.065001 | 0.0045004 | 2.3463 | 5.6949 | 736 | 9.9585 | 154 | 0 | 0 | 14.613 | 182 | 0
North Coast | 3495 | 421 | 543.5225 | 635 | 651.1332 | 66 | 0.000152 | 568.2139 | 32.681 | 537.7084 | 7473.6929 | 1013.6099 | 15.0991 | 148.5526 | 1.3823 | 0.08342 | 0.0028047 | 0.66299 | 0.83473 | {9734DBF0-6F90-4CE9-BF04-F2CD4B5AEADC} | 42661102 | WILLITS 1102 | circuit_breaker | 39.4056 | -123.3271 | WILLITS 1102circuit_breaker | 297 | 786 | 46137.706 | 15591.407 | 30546.299 | 7444.0734 | 13342.8543 | 0.18511 | 0.010032 | 1.291 | 9.6212 | 113 | 5.5057 | 155 | 0 | 0 | 4.6255 | 2078 | 0
North Coast | 6600 | 1140 | 2158.4975 | 1307 | 2240.192 | 131 | 0.00016375 | 494.3519 | 22.5304 | 1854.4434 | 37596.0423 | 1585.6084 | 1.5241 | 159.3912 | 1.287 | 0.082639 | 0.0016493 | 0.87223 | 0.96353 | {E448EB4C-7ECC-4C43-A720-97024B873C96} | 192321121 | FORT SEWARD 1121 | 1690 | 40.1677 | -123.6109 | FORT SEWARD 11211690 | 91 | 77 | 30371.5109 | 26202.8159 | 4168.695 | 15633.7781 | 2859.303 | 0.21606 | 0.021451 | 1.8934 | 9.9771 | 216 | 10.8257 | 156 | 0 | 0 | 9.7144 | 2291 | 0
North Coast | 2658 | 474 | 1388.2961 | 758 | 1527.1056 | 133 | 7.6043e-05 | 1045.6834 | 42.8448 | 1502.4649 | 7340.2017 | 835.3985 | 24.5294 | 265.6137 | 1.1788 | 0.082528 | 0.0017241 | 0.62533 | 0.9091 | {554E4D6F-0779-4CD2-B95F-DB489BEA9C8F} | 42271105 | COTATI 1105 | 36536 | 38.3142 | -122.7365 | COTATI 110536536 | 305 | 358 | 60809.5371 | 31836.265 | 28973.2721 | 25960.937 | 24566.2063 | 0.2293 | 0.010114 | 2.9289 | 5.6992 | 206 | 10.9762 | 157 | 0 | 0 | 16.1314 | 2405 | 0
North Valley | 4207 | 39 | 82.5598 | 346 | 204.2468 | 49 | 9.6205e-05 | 806.5998 | 43.1971 | 275.2324 | 1241.0599 | 136.5259 | 22.5597 | 165.6615 | 1.2157 | 0.081896 | 0.0016227 | 0.11272 | 0.40422 | {F8758432-B450-4943-97B4-52B80EF2F512} | 103401102 | GIRVAN 1102 | circuit_breaker | 40.5132 | -122.3787 | GIRVAN 1102circuit_breaker | 246 | 251 | 45913.478 | 33795.3586 | 12118.1193 | 5934.374 | 2513.4362 | 0.079514 | 0.004714 | 2.1169 | 7.0612 | 225 | 4.0129 | 158 | 0 | 0 | 3.6874 | 2356 | 0
Sierra | 4729 | 406 | 683.6154 | 1644 | 1142.8878 | 228 | 4.389e-05 | 1876.5104 | 18.2609 | 1256.9672 | 6909.303 | 246.9507 | 34.2102 | 689.4754 | 1.3349 | 0.081723 | 0.00032624 | 0.24696 | 0.59815 | {FDA2EA55-8785-46E8-B115-1C92328E3E9B} | 153701104 | LINCOLN 1104 | 2070 | 38.9276 | -121.2469 | LINCOLN 11042070 | 441 | 338 | 78873.1868 | 46656.6382 | 32216.5486 | 26390.3487 | 19272.3183 | 0.074383 | 0.010007 | 1.6838 | 7.2105 | 1063 | 18.6329 | 159 | 0 | 0 | 16.3982 | 539 | 0
North Valley | 6432 | 48 | 95.7276 | 156 | 133.0204 | 44 | 4.5241e-05 | 1953.7097 | 10.4549 | 1176.9335 | 6990.906 | 167.3451 | 36.7511 | 1537.8267 | 1.316 | 0.081472 | 0.00027194 | 0.30769 | 0.71965 | {0237A482-F336-4387-BDDB-C855D376A309} | 103331101 | CORNING 1101 | 82846 | 40.0149 | -122.3976 | CORNING 110182846 | 90 | 157 | 14961.1843 | 8126.0049 | 6835.1794 | 7599.2356 | 6175.1189 | 0.011966 | 0.0019906 | 1.9943 | 3.5455 | 1199 | 3.5848 | 160 | 0 | 0 | 4.7219 | 807 | 0
North Valley | 8199 | 14 | 43.2033 | 225 | 90.1941 | 45 | 4.3634e-05 | 1852.51 | 37.6918 | 296.0263 | 1321.4558 | 80.8453 | 42.0759 | 510.2164 | 1.4003 | 0.080522 | 0.00060149 | 0.062222 | 0.479 | {B2DB7CB9-0EE4-43E1-8597-CA558B8247E5} | 103261101 | ANDERSON 1101 | 2051 | 40.4188 | -122.2867 | ANDERSON 11012051 | 81 | 96 | 12418.4302 | 8575.0635 | 3843.3667 | 8118.8203 | 3843.3667 | 0.027067 | 0.0019635 | 3.086 | 5 | 669 | 3.6235 | 161 | 0 | 0 | 5.0448 | 250 | 0
Central Coast | 2693 | 61 | 92.7845 | 124 | 133.4033 | 23 | 4.1553e-05 | 1811.1586 | 0.062883 | 6.3656 | 10.6055 | 0.0052609 | 17.4744 | 190.9969 | 1.3083 | 0.080049 | 2.8948e-05 | 0.49194 | 0.69552 | {90A67B0B-7B04-4738-A6BC-63EA48062380} | 182742101 | SAN BENITO 2101 | 36912 | 36.8384 | -121.5204 | SAN BENITO 210136912 | 130 | 128 | 27401.1585 | 20320.0338 | 7081.1247 | 7482.8922 | 2275.3579 | 0.00066581 | 0.00095572 | 1.5211 | 5.3913 | 2475 | 1.8411 | 162 | 0 | 0 | 4.6497 | 1803 | 0
Central Valley | 1374 | 250 | 359.9316 | 1084 | 765.9584 | 146 | 6.5306e-05 | 1270.8678 | 14.9528 | 205.3256 | 1475.3361 | 67.8381 | 20.9327 | 377.4187 | 1.5131 | 0.079894 | 0.00059824 | 0.23063 | 0.46991 | {6E730337-737F-4AF4-89D0-F209BD78A056} | 252521103 | SAN JOAQUIN #2 1103 | 10320 | 37.2141 | -119.5525 | SAN JOAQUIN #2 110310320 | 182 | 192 | 30937.0179 | 18926.5803 | 12010.4376 | 18926.5803 | 12010.4376 | 0.087343 | 0.0095347 | 1.4397 | 7.4247 | 674 | 11.6645 | 163 | 0 | 0 | 11.7604 | 1369 | 0
North Valley | 5188 | 66 | 174.9321 | 369 | 261.0366 | 58 | 4.1402e-05 | 2587.3304 | 59.8339 | 481.5632 | 2384.7664 | 242.9104 | 38.2353 | 364.2982 | 1.4184 | 0.079634 | 0.0010053 | 0.17886 | 0.67014 | {E88498F1-1B51-48DF-A92A-A9C03D92520C} | 102911109 | WYANDOTTE 1109 | 5607 | 39.458 | -121.5132 | WYANDOTTE 11095607 | 99 | 92 | 17097.4634 | 10784.9193 | 6312.5442 | 6796.939 | 5342.6418 | 0.058309 | 0.0024013 | 2.6505 | 6.3621 | 410 | 4.6188 | 164 | 0 | 0 | 4.2234 | 1602 | 0
North Valley | 8090 | 19 | 30.9876 | 81 | 54.6513 | 47 | 4.2172e-05 | 1978.4634 | 9.7485 | 2802.6783 | 23480.2839 | 348.9237 | 15.3809 | 1643.4484 | 1.7385 | 0.078846 | 0.00020859 | 0.23457 | 0.56701 | {9C349921-70C5-4A1B-82FC-D82E641B2142} | 102781101 | ELK CREEK 1101 | 2106 | 39.6064 | -122.5416 | ELK CREEK 11012106 | 72 | 34 | 22285.0947 | 21303.4581 | 981.6366 | 21303.4581 | 981.6366 | 0.0098035 | 0.0019821 | 1.6309 | 1.7234 | 1384 | 3.7058 | 165 | 0 | 0 | 13.2374 | 1613 | 0
Sierra | 3848 | 709 | 1334.091 | 2025 | 1856.5522 | 331 | 5.904e-05 | 1525.4341 | 17.5296 | 250.8326 | 2296.5744 | 69.2392 | 23.3956 | 304.0353 | 1.4199 | 0.078641 | 0.00056626 | 0.35012 | 0.71859 | {D8BA8AE4-C717-4377-92D2-0F59CC0A31DF} | 152282101 | MOUNTAIN QUARRIES 2101 | circuit_breaker | 38.9141 | -121.0189 | MOUNTAIN QUARRIES 2101circuit_breaker | 395 | 390 | 64500.1773 | 40183.7682 | 24316.4092 | 40183.7682 | 24316.4092 | 0.18743 | 0.019542 | 1.8817 | 6.1178 | 717 | 26.0302 | 166 | 0 | 0 | 24.969 | 83 | 0
North Coast | 2080 | 186 | 267.6129 | 385 | 326.3005 | 80 | 6.6535e-05 | 994.3546 | 8.324 | 567.3058 | 5384.0943 | 183.1413 | 15.7848 | 312.3052 | 1.4471 | 0.078231 | 0.00036284 | 0.48312 | 0.82014 | {A05AE75B-B8B1-4EF0-A327-427A302D4FDB} | 43351103 | LUCERNE 1103 | 1280 | 39.1273 | -122.8651 | LUCERNE 11031280 | 359 | 450 | 68381.874 | 38046.2309 | 30335.6431 | 11811.7208 | 7582.8687 | 0.029027 | 0.0053228 | 1.4388 | 4.8125 | 993 | 6.2585 | 167 | 0 | 0 | 7.3395 | 1293 | 0
Sierra | 5006 | 5 | 8.7045 | 12 | 11.3813 | 6 | 1.3034e-05 | 5730.2781 | 248.7911 | 2523.5104 | 15548.4385 | 3868.2858 | 57.743 | 760.0864 | 1.8857 | 0.077068 | 0.0014645 | 0.41667 | 0.76481 | {D12E3D2F-1998-4DA6-942A-7BE316909F83} | 63601109 | VACAVILLE 1109 | 41782 | 38.3384 | -121.9865 | VACAVILLE 110941782 | 61 | 34 | 3585.114 | 2742.127 | 842.987 | 1089.8371 | 99.6171 | 0.0087869 | 7.8205e-05 | 1.7409 | 2 | 255 | 0.46241 | 168 | 0 | 0 | 0.67719 | 793 | 0
Central Coast | 934 | 194 | 338.4582 | 345 | 427.894 | 88 | 7.3065e-05 | 1047.9759 | 5.577 | 1379.399 | 4512.8523 | 29.895 | 19.0517 | 1935.6681 | 1.8356 | 0.076876 | 0.00022069 | 0.56232 | 0.79099 | {B46D742B-3DDA-4738-A51C-19ABAD3AA23C} | 182721104 | SANTA YNEZ 1104 | Y66 | 34.6111 | -120.0203 | SANTA YNEZ 1104Y66 | 157 | 105 | 40590.9362 | 28822.2697 | 11768.6666 | 25950.7807 | 10680.2681 | 0.019421 | 0.0064297 | 1.7446 | 3.9205 | 1340 | 6.7651 | 169 | 0 | 0 | 16.1251 | 1713 | 0
North Valley | 4646 | 97 | 209.4453 | 862 | 425.1634 | 255 | 5.7284e-05 | 1365.1036 | 48.7138 | 1549.0354 | 12555.3433 | 1161.4434 | 24.4745 | 698.728 | 1.5747 | 0.076685 | 0.0015256 | 0.11253 | 0.49262 | {A71E6943-6B14-4439-9642-365560E75664} | 102931103 | COTTONWOOD 1103 | 9072 | 40.3378 | -122.3717 | COTTONWOOD 11039072 | 347 | 337 | 71579.4708 | 45954.2203 | 25625.2505 | 45954.2203 | 25625.2505 | 0.38903 | 0.014607 | 2.1592 | 3.3804 | 239 | 19.5548 | 170 | 0 | 0 | 28.5546 | 2535 | 0
Sierra | 2804 | 287 | 525.0377 | 1096 | 824.9571 | 219 | 9.9013e-05 | 797.5228 | 45.5531 | 585.233 | 5954.1404 | 716.8433 | 16.6538 | 340.833 | 1.4105 | 0.076254 | 0.0018696 | 0.26186 | 0.63644 | {8A46F925-4164-4C6A-BCD9-45A3449DD786} | 153652109 | SHINGLE SPRINGS 2109 | 9372 | 38.714 | -120.9394 | SHINGLE SPRINGS 21099372 | 271 | 223 | 44217.0152 | 28435.4313 | 15781.5839 | 28435.4313 | 15781.5839 | 0.40945 | 0.021684 | 1.8294 | 5.0046 | 188 | 16.6995 | 171 | 0 | 0 | 17.669 | 777 | 0
North Coast | 4127 | 156 | 237.6021 | 269 | 277.2146 | 48 | 9.0688e-05 | 681.5182 | 11.1245 | 1436.8712 | 17904.8538 | 632.1906 | 10.8547 | 252.3881 | 1.4078 | 0.075419 | 0.00046767 | 0.57993 | 0.85711 | {8D4490B9-6B4D-4F2D-8A60-88D879FECDA8} | 42281104 | POTTER VALLEY P H 1104 | 95878 | 39.3618 | -123.1272 | POTTER VALLEY P H 110495878 | 261 | 360 | 63197.0579 | 29933.3469 | 33263.711 | 7653.5834 | 7733.5092 | 0.022448 | 0.004353 | 1.5231 | 5.6042 | 834 | 3.6201 | 172 | 0 | 0 | 4.7557 | 2189 | 0
Central Valley | 2763 | 828 | 1138.125 | 3724 | 2439.2495 | 540 | 4.7849e-05 | 2120.0797 | 14.7835 | 412.6977 | 3378.1387 | 125.4693 | 31.7288 | 492.4818 | 1.4803 | 0.075309 | 0.00032804 | 0.22234 | 0.46659 | {2F234991-7E43-4D60-8350-25C731139A77} | 254421101 | OAKHURST 1101 | 10090 | 37.364 | -119.7252 | OAKHURST 110110090 | 626 | 672 | 123090.4941 | 71069.2859 | 52021.2082 | 71069.2859 | 52021.2082 | 0.17714 | 0.025839 | 1.3745 | 6.8963 | 1060 | 40.6671 | 173 | 0 | 0 | 44.1604 | 2139 | 0
North Valley | 2247 | 413 | 988.4792 | 1078 | 1196.4143 | 207 | 6.308e-05 | 1242.6142 | 49.3099 | 766.7056 | 5621.6442 | 726.2991 | 26.2642 | 395.6931 | 1.334 | 0.075307 | 0.0016663 | 0.38312 | 0.8262 | {5AFC8D8B-3E76-4032-9E9C-44E621C60A00} | 103441102 | JESSUP 1102 | 1550 | 40.4471 | -122.3186 | JESSUP 11021550 | 372 | 381 | 61424.3748 | 35586.9744 | 25837.4004 | 28670.4982 | 17691.8341 | 0.34493 | 0.013058 | 2.3934 | 5.2077 | 213 | 15.5885 | 174 | 0 | 0 | 17.815 | 2290 | 0
Central Valley | 4022 | 235 | 638.3711 | 670 | 787.0189 | 178 | 1.6998e-05 | 4159.274 | 63.5383 | 6881.2014 | 49964.659 | 3909.3186 | 51.0018 | 1147.7437 | 1.664 | 0.074482 | 0.0004301 | 0.35075 | 0.81113 | {6360CE1E-0CA2-4404-B100-BE673F561AC1} | 254601103 | SAND CREEK 1103 | 7420 | 36.6759 | -119.1869 | SAND CREEK 11037420 | 376 | 399 | 65458.4399 | 38096.5412 | 27361.8987 | 38096.5412 | 27361.8987 | 0.076558 | 0.0030256 | 2.7165 | 3.764 | 889 | 13.2578 | 175 | 0 | 0 | 23.6721 | 1834 | 0
North Coast | 6306 | 214 | 282.2808 | 482 | 384.9407 | 103 | 6.0686e-05 | 1154.4624 | 9.9338 | 771.7836 | 9019.4081 | 242.1138 | 19.4477 | 431.2919 | 1.3805 | 0.074476 | 0.00033016 | 0.44398 | 0.73331 | {CEA08BFB-7016-4016-B5B7-B9CA2EAF8E9F} | 42871101 | UPPER LAKE 1101 | 412 | 39.1825 | -122.9619 | UPPER LAKE 1101412 | 193 | 197 | 55030.4791 | 29863.0456 | 25167.4335 | 17548.709 | 10619.9279 | 0.034007 | 0.0062506 | 1.3191 | 4.6796 | 1055 | 7.671 | 176 | 0 | 0 | 10.9043 | 133 | 0
North Valley | 338 | 96 | 183.6457 | 540 | 372.0869 | 60 | 0.00010059 | 698.7916 | 13.0372 | 155.199 | 950.5711 | 61.8313 | 17.8509 | 158.1561 | 1.1435 | 0.074164 | 0.00070526 | 0.17778 | 0.49356 | {509EDC5C-5C13-447D-BAA5-6AE957D846E4} | 102931101 | COTTONWOOD 1101 | circuit_breaker | 40.397 | -122.2674 | COTTONWOOD 1101circuit_breaker | 512 | 912 | 75641.5877 | 36474.0618 | 39167.5259 | 7715.0522 | 8282.4766 | 0.042316 | 0.0060357 | 1.913 | 9 | 561 | 4.4498 | 177 | 0 | 0 | 4.7939 | 2396 | 0
North Valley | 4335 | 64 | 96.4759 | 89 | 105.446 | 24 | 0.00013221 | 801.0186 |  |  |  |  | 13.096 | 1096.2598 | 1.5745 | 0.073876 | 0.00013221 | 0.7191 | 0.91493 | {AC290F88-25E1-47EB-BF8A-1F1AD055C84D} | 102781101 | ELK CREEK 1101 | 2228 | 39.3929 | -122.5495 | ELK CREEK 11012228 | 115 | 172 | 22540.0768 | 16936.7028 | 5603.374 | 4717.8323 | 486.9609 | 0.003173 | 0.003173 | 1.5074 | 3.7083 | 1689 | 1.773 | 178 | 0 | 0 | 2.9315 | 91 | 0
Central Valley | 603 | 24 | 44.2631 | 146 | 91.2159 | 42 | 2.8078e-05 | 2370.2217 | 75.1023 | 1890.2183 | 17646.7482 | 2894.2194 | 31.0639 | 722.2921 | 1.679 | 0.073873 | 0.00098555 | 0.16438 | 0.48526 | {5CEBE369-1234-4C2E-B50B-4FF49A63CB11} | 252561101 | KERCKHOFF 1101 | circuit_breaker | 37.0919 | -119.5525 | KERCKHOFF 1101circuit_breaker | 237 | 206 | 40921.5971 | 27412.9116 | 13508.6855 | 27412.9116 | 13508.6855 | 0.041393 | 0.0011793 | 1.8443 | 3.4762 | 416 | 3.1027 | 179 | 0 | 0 | 17.0336 | 663 | 0
Sierra | 2148 | 262 | 575.9327 | 1199 | 866.4302 | 241 | 9.2227e-05 | 859.461 | 14.249 | 591.3408 | 3463.1727 | 94.4228 | 16.5259 | 188.3381 | 1.4041 | 0.074121 | 0.00062035 | 0.21852 | 0.66472 | {B086CF84-D2F5-42B5-8FBA-007201735811} | 152261105 | DIAMOND SPRINGS 1105 | 19910 | 38.6313 | -120.8543 | DIAMOND SPRINGS 110519910 | 338 | 438 | 66869.8412 | 32811.9682 | 34057.873 | 32811.9682 | 34057.873 | 0.1495 | 0.022227 | 2.1982 | 4.9751 | 650 | 17.8631 | 180 | 0 | 0 | 20.3884 | 531 | 0
Central Valley | 2148 | 0 | 0 | 2 | 0.91147 | 1 | 7.383e-05 | 0.066432 |  |  |  |  | 0.23451 | 8.6834 | 1.0066 | 4.9046e-06 | 7.383e-05 | 0 | 0 | {B086CF84-D2F5-42B5-8FBA-007201735811} | 152261105 | DIAMOND SPRINGS 1105 | 19910 | 38.6313 | -120.8543 | DIAMOND SPRINGS 110519910 | 338 | 438 | 66869.8412 | 32811.9682 | 34057.873 | 32811.9682 | 34057.873 | 7.383e-05 | 7.383e-05 |  | 2 | 2028 | 4.9046e-06 | 180 | 0 | 0 | 20.3884 | 1718 | 0
Central Coast | 5296 | 107 | 188.697 | 630 | 499.5452 | 109 | 5.6631e-05 | 1484.6271 | 10.0422 | 213.5207 | 647.9633 | 17.515 | 27.6227 | 515.1939 | 1.3051 | 0.073532 | 0.0003092 | 0.16984 | 0.37774 | {06AE963E-8682-491C-931E-D311BC02A28D} | 182681102 | ZACA 1102 | circuit_breaker | 34.6967 | -120.1515 | ZACA 1102circuit_breaker | 291 | 348 | 52894.6664 | 33377.7518 | 19516.9147 | 24178.8119 | 8041.2705 | 0.033703 | 0.0061728 | 1.7635 | 5.7798 | 1101 | 8.015 | 181 | 0 | 0 | 15.024 | 1950 | 0
North Coast | 4894 | 327 | 490.2404 | 578 | 644.2148 | 69 | 7.7106e-05 | 852.6822 | 5.1491 | 108.6791 | 1508.8258 | 20.3283 | 4.3805 | 85.8756 | 1.3835 | 0.07303 | 0.00027637 | 0.56574 | 0.76099 | {0AFDFC2C-BE93-4295-B473-DFD529280FFF} | 42821102 | CLOVERDALE 1102 | 156 | 38.7991 | -122.9913 | CLOVERDALE 1102156 | 180 | 258 | 39176.2158 | 18980.0369 | 20196.1789 | 8650.9367 | 7616.5751 | 0.01907 | 0.0053203 | 1.4992 | 8.3768 | 1182 | 5.0391 | 182 | 0 | 0 | 5.3754 | 1090 | 0
North Valley | 2565 | 27 | 50.1619 | 166 | 103.5479 | 25 | 7.8977e-05 | 1080.5631 | 15.4903 | 157.4865 | 738.5795 | 20.4422 | 26.9876 | 497.2551 | 1.3132 | 0.072922 | 0.00062925 | 0.16265 | 0.48443 | {47DC31DB-63D1-4B41-9B4B-82351A2B9DE8} | 103441103 | JESSUP 1103 | 1540 | 40.4984 | -122.3248 | JESSUP 11031540 | 328 | 613 | 51190.2256 | 24454.6209 | 26735.6047 | 2468.2792 | 2104.9501 | 0.015731 | 0.0019744 | 1.8578 | 6.64 | 640 | 1.823 | 183 | 0 | 0 | 1.5337 | 344 | 0
Central Valley | 1366 | 275 | 515.7094 | 1546 | 981.895 | 367 | 2.1016e-05 | 3490.9051 | 71.6712 | 4537.5982 | 38918.6357 | 3912.4187 | 39.414 | 926.6089 | 1.768 | 0.072884 | 0.00077685 | 0.17788 | 0.52522 | {688E42B7-A82A-4FB4-A2CB-EF444C8907DE} | 254601103 | SAND CREEK 1103 | 45190 | 36.692 | -119.1544 | SAND CREEK 110345190 | 554 | 625 | 105265.8773 | 58836.3475 | 46429.5298 | 58836.3475 | 46429.5298 | 0.2851 | 0.0077128 | 1.8753 | 4.2125 | 513 | 26.7484 | 184 | 0 | 0 | 36.5592 | 2288 | 0
North Coast | 1853 | 470 | 891.8685 | 921 | 1052.211 | 154 | 8.5839e-05 | 823.313 | 15.4726 | 1157.1855 | 13684.3023 | 366.4891 | 15.695 | 501.0925 | 1.4701 | 0.072883 | 0.00075201 | 0.51031 | 0.84761 | {9F8ACCEF-B036-4FB1-850C-B401BE3A4651} | 43191101 | REDBUD 1101 | 323962 | 39.0663 | -122.6111 | REDBUD 1101323962 | 427 | 642 | 87325.9479 | 46324.5895 | 41001.3585 | 32521.6427 | 20804.5105 | 0.11581 | 0.013219 | 1.8976 | 5.9805 | 531 | 11.224 | 185 | 0 | 0 | 20.208 | 361 | 0
Central Valley | 1871 | 49 | 77.7768 | 485 | 205.375 | 112 | 2.2192e-05 | 3457.9578 | 104.7267 | 1710.822 | 10341.0905 | 2070.1769 | 38.4722 | 895.902 | 1.6816 | 0.072213 | 0.0010631 | 0.10103 | 0.37871 | {8C528F18-9D07-401C-90F8-07B202001D80} | 252941107 | TIVY VALLEY 1107 | R1817 | 36.8245 | -119.3652 | TIVY VALLEY 1107R1817 | 182 | 224 | 56560.0475 | 30917.6877 | 25642.3598 | 30260.3712 | 25619.9728 | 0.11906 | 0.0024854 | 1.5873 | 4.3304 | 380 | 8.0879 | 186 | 0 | 0 | 18.8029 | 1916 | 0
Sierra | 6490 | 168 | 240.3836 | 717 | 455.0763 | 74 | 6.5437e-05 | 1402.5218 | 14.5658 | 140.2398 | 620.0481 | 16.1036 | 19.3039 | 164.3971 | 1.2428 | 0.07173 | 0.00053503 | 0.23431 | 0.52823 | {6D8436AE-2EAD-41A9-BD49-F6A605A312D4} | 152701108 | BELL 1108 | 5703 | 38.9965 | -121.1079 | BELL 11085703 | 137 | 155 | 21881.4414 | 12591.8349 | 9289.6065 | 7165.6312 | 6240.4949 | 0.039593 | 0.0048424 | 1.4309 | 9.6892 | 751 | 5.308 | 187 | 0 | 0 | 4.4525 | 1470 | 0
Sierra | 56 | 291 | 468.5794 | 581 | 597.2845 | 91 | 3.6139e-05 | 1478.6443 | 9.9496 | 54.3299 | 270.3336 | 7.6884 | 33.3498 | 275.8991 | 1.2714 | 0.071723 | 0.00021497 | 0.50086 | 0.78452 | {1F08C74E-1D18-453D-9F09-2E91ADE9AFB1} | 63601111 | VACAVILLE 1111 | circuit_breaker | 38.3568 | -121.9806 | VACAVILLE 1111circuit_breaker | 283 | 547 | 45304.1261 | 19505.0496 | 25799.0765 | 10814.1289 | 11722.0733 | 0.019562 | 0.0032887 | 1.6102 | 6.3846 | 1361 | 6.5268 | 188 | 0 | 0 | 6.7196 | 2454 | 0
North Coast | 2173 | 222 | 295.3008 | 383 | 355.4612 | 78 | 9.1585e-05 | 840.8833 | 20.6706 | 340.4703 | 1577.2827 | 107.1345 | 14.1563 | 592.3219 | 1.3614 | 0.071621 | 0.001003 | 0.57963 | 0.83075 | {302C19E7-740B-49C6-83EC-9E70AC44D5CB} | 43141101 | MIDDLETOWN 1101 | circuit_breaker | 38.7527 | -122.6087 | MIDDLETOWN 1101circuit_breaker | 383 | 618 | 68780.4081 | 30016.3762 | 38764.0319 | 13452.3274 | 15586.5774 | 0.078233 | 0.0071436 | 1.3302 | 4.9103 | 412 | 5.5864 | 189 | 0 | 0 | 8.3589 | 783 | 0
Central Valley | 60 | 0 | 0 | 1 | 0.45574 | 1 | 2.8673e-05 | 2477.7606 |  |  |  |  | 33.6991 | 937.6827 | 1.5288 | 0.071046 | 2.8673e-05 | 0 | 0 | {C6783DDC-8CCC-4EFE-8097-5CE8336375DE} | 162991101 | CORRAL 1101 | 75204 | 38.1006 | -120.9283 | CORRAL 110175204 | 176 | 107 | 36461.9814 | 29877.8806 | 6584.1008 | 154.2541 | 87.807 | 2.8673e-05 | 2.8673e-05 |  | 1 | 2483 | 0.071046 | 190 | 0 | 0 | 0.095849 | 1300 | 0
Sierra | 3481 | 166 | 251.5696 | 1128 | 616.278 | 173 | 4.2626e-05 | 1710.4728 | 7.7187 | 206.4304 | 1219.1976 | 41.4436 | 24.2175 | 506.7542 | 1.4626 | 0.070389 | 0.00017453 | 0.14716 | 0.40821 | {44C9B622-8B72-4A96-9463-A27F202016A7} | 63801105 | JAMESON 1105 | 7652 | 38.2509 | -122.12 | JAMESON 11057652 | 630 | 655 | 114486.8312 | 70087.7329 | 44399.0983 | 21719.6282 | 13009.1978 | 0.030194 | 0.0073743 | 1.5155 | 6.5202 | 1505 | 12.1773 | 191 | 0 | 0 | 13.4959 | 65 | 0
North Coast | 3437 | 131 | 204.4506 | 323 | 252.5441 | 75 | 5.0494e-05 | 1493.2421 | 3.2019 | 1197.9606 | 24815.8908 | 283.8734 | 18.5959 | 563.0209 | 1.4443 | 0.06994 | 8.5039e-05 | 0.40557 | 0.80956 | {3FE0C1F5-EB90-4962-9A26-B07537415DC7} | 42141101 | CLEAR LAKE 1101 | 406 | 39.0046 | -122.8941 | CLEAR LAKE 1101406 | 454 | 424 | 95794.4897 | 52777.1485 | 43017.3412 | 17278.745 | 11086.4083 | 0.006378 | 0.0037871 | 1.5607 | 4.3067 | 1950 | 5.2455 | 192 | 0 | 0 | 10.7365 | 1250 | 0
Bay Area | 7479 | 0 | 0 | 2 | 0.91147 | 1 | 1.1525e-05 | 6042.587 | 40.999 | 300.2772 | 735.3701 | 32.11 | 89.9425 | 1216.2942 | 1.7965 | 0.069642 | 0.00047252 | 0 | 0 | {330BFDB0-6988-4176-BABE-C83B83D4EDBE} | 13912107 | WILLOW PASS 2107 | P500R | 38.022 | -121.942 | WILLOW PASS 2107P500R | 101 | 112 | 10027.2155 | 5092.597 | 4934.6186 | 1031.3201 | 38.1262 | 0.00047252 | 1.1525e-05 |  | 2 | 820 | 0.069642 | 193 | 0 | 0 | 0.64083 | 1086 | 0
Sierra | 6227 | 245 | 395.7924 | 704 | 568.923 | 108 | 5.5807e-05 | 1226.9571 | 15.1125 | 135.3983 | 604.8123 | 23.1123 | 23.784 | 236.1928 | 1.1803 | 0.069507 | 0.00039517 | 0.34801 | 0.69569 | {64620CA8-4B52-4298-8F14-91A606AD81F8} | 152271102 | WISE 1102 | 697216 | 38.9364 | -121.1762 | WISE 1102697216 | 221 | 187 | 34631.6261 | 21260.5149 | 13371.1112 | 21260.5149 | 13371.1112 | 0.042679 | 0.0060271 | 1.6155 | 6.5185 | 950 | 7.5068 | 194 | 0 | 0 | 13.2107 | 586 | 0
Bay Area | 3424 | 12 | 16.9649 | 20 | 21.0588 | 7 | 1.8906e-05 | 3286.7988 | 58.2784 | 2005.5727 | 10712.6852 | 553.9702 | 38.8025 | 622.3879 | 1.5073 | 0.069419 | 0.00080765 | 0.6 | 0.80559 | {17D49159-2A99-4FB5-B2DC-0815D2D13280} | 12022215 | CLAYTON 2215 | circuit_breaker | 37.9447 | -121.9698 | CLAYTON 2215circuit_breaker | 266 | 713 | 49765.704 | 17643.4387 | 32122.2652 | 3378.3697 | 10.9722 | 0.0056536 | 0.00013234 | 1.4137 | 2.8571 | 496 | 0.48593 | 195 | 0 | 0 | 2.0992 | 2639 | 0
North Valley | 1887 | 0 | 0 | 3 | 0.64023 | 2 | 2.1905e-05 | 3167.2498 | 0.002804 | 0.22239 | 1.7851 | 5.0056e-06 | 60.1283 | 1157.4852 | 1.469 | 0.06938 | 1.1085e-05 | 0 | 0 | {87BD5616-A670-4B3C-B36B-8B72CB70DFA6} | 102911106 | WYANDOTTE 1106 | 41650 | 39.3864 | -121.5762 | WYANDOTTE 110641650 | 191 | 233 | 44992.8953 | 25775.0399 | 19217.8554 | 1286.1146 | 776.8073 | 2.2169e-05 | 4.3811e-05 |  | 1.5 | 2775 | 0.13876 | 196 | 0 | 0 | 0.79915 | 971 | 0
Sierra | 5552 | 149 | 200.5253 | 232 | 235.4815 | 20 | 0.00010898 | 658.0738 | 3.3917 | 12.2298 | 27.8014 | 0.15425 | 12.158 | 87.2876 | 1.1361 | 0.06907 | 0.00026274 | 0.64224 | 0.85155 | {3C765F3F-8878-4C34-98CF-2D3F31F6AD44} | 152561107 | PENRYN 1107 | 2704 | 38.8107 | -121.1647 | PENRYN 11072704 | 137 | 186 | 19729.8361 | 9132.2031 | 10597.633 | 1994.2196 | 2012.535 | 0.0052548 | 0.0021796 | 1.3458 | 11.6 | 1215 | 1.3814 | 197 | 0 | 0 | 1.2392 | 550 | 0
North Valley | 7817 | 47 | 101.6432 | 258 | 149.8378 | 40 | 4.4656e-05 | 1393.0295 | 6.668 | 136.4258 | 734.0523 | 14.5714 | 26.8514 | 479.6193 | 1.4413 | 0.068637 | 0.00012806 | 0.18217 | 0.67835 | {02E1E6D5-2F65-4901-878D-9181104BB0F8} | 103351101 | DESCHUTES 1101 | 9722 | 40.5633 | -122.2012 | DESCHUTES 11019722 | 94 | 54 | 10259.1806 | 7564.9094 | 2694.2712 | 4975.6844 | 1658.3402 | 0.0051223 | 0.0017862 | 2.1626 | 6.45 | 1707 | 2.7455 | 198 | 0 | 0 | 3.0917 | 1670 | 0
Sierra | 8201 | 1 | 1.945 | 28 | 12.8578 | 8 | 4.8398e-05 | 1378.0855 | 70.9989 | 3045.0484 | 15403.8451 | 1262.0142 | 21.2176 | 1826.4923 | 1.9082 | 0.068411 | 0.0015521 | 0.035714 | 0.15127 | {B44C5067-6D0E-4713-9558-13070DEDA962} | 63681105 | PUTAH CREEK 1105 | 46162 | 38.5254 | -121.9983 | PUTAH CREEK 110546162 | 57 | 42 | 14746.6191 | 10784.3815 | 3962.2376 | 1002.572 | 1141.0852 | 0.012417 | 0.00038718 | 1.945 | 3.5 | 235 | 0.54729 | 199 | 0 | 0 | 0.62297 | 803 | 0
Sierra | 6093 | 0 | 0 | 1 | 0.45574 | 1 | 2.1015e-05 | 3238.6181 |  |  |  |  | 41.4934 | 2975.2253 | 2.0774 | 0.068058 | 2.1015e-05 | 0 | 0 | {892EE518-0261-403B-AEBB-DE522B481F93} | 63172101 | MADISON 2101 | 1606 | 38.8017 | -122.18 | MADISON 21011606 | 249 | 238 | 38410.3339 | 26669.2024 | 11741.1315 | 1536.4017 | 48.0601 | 2.1015e-05 | 2.1015e-05 |  | 1 | 2590 | 0.068058 | 200 | 0 | 0 | 0.95468 | 277 | 0
Sierra | 4798 | 678 | 1303.9452 | 2784 | 1955.58 | 416 | 4.7937e-05 | 1677.4532 | 20.542 | 468.7104 | 2779.4484 | 150.3313 | 26.5548 | 322.2935 | 1.3641 | 0.068023 | 0.00042668 | 0.24353 | 0.66678 | {C705CC3B-4CE7-4574-9451-1595DBBA258B} | 152701108 | BELL 1108 | 2202 | 38.9716 | -121.1058 | BELL 11082202 | 524 | 444 | 95819.3385 | 53223.6255 | 42595.713 | 51314.2889 | 41117.51 | 0.1775 | 0.019942 | 1.9232 | 6.6923 | 899 | 28.2975 | 201 | 0 | 0 | 31.8852 | 555 | 0
Bay Area | 7713 | 359 | 512.2656 | 1072 | 930.2587 | 90 | 9.1539e-05 | 732.6786 | 9.8636 | 429.317 | 7538.0488 | 271.0995 | 1.1377 | 85.6399 | 1.2663 | 0.067762 | 0.0004904 | 0.33489 | 0.55067 | {C483C6B2-63CC-448F-80AD-EB7838DB89B8} | 42991105 | LAS GALLINAS A 1105 | 99904 | 38.0443 | -122.6155 | LAS GALLINAS A 110599904 | 78 | 46 | 14887.5888 | 8897.752 | 5989.8368 | 8897.752 | 5989.8368 | 0.044136 | 0.0082385 | 1.4269 | 11.9111 | 797 | 6.0985 | 202 | 0 | 0 | 5.5288 | 962 | 0
Bay Area | 389 | 1103 | 1667.552 | 2002 | 2192.8633 | 181 | 0.00014696 | 447.8171 | 4.5566 | 126.092 | 1987.7469 | 37.7442 | 2.3821 | 77.008 | 1.2284 | 0.067548 | 0.00045993 | 0.55095 | 0.76045 | {F066D46E-68CF-473C-8A1D-A024587DFB27} | 42711101 | CALISTOGA 1101 | 734 | 38.5894 | -122.6078 | CALISTOGA 1101734 | 241 | 251 | 43968.8379 | 25385.1806 | 18583.6574 | 20110.861 | 14434.4965 | 0.083248 | 0.026601 | 1.5118 | 11.0608 | 847 | 12.2262 | 203 | 0 | 0 | 12.4963 | 340 | 0
Central Coast | 834 | 80 | 182.8975 | 695 | 533.3119 | 97 | 3.7517e-05 | 1737.2077 | 5.1098 | 122.994 | 617.0962 | 11.5254 | 25.8219 | 352.7402 | 1.3227 | 0.06605 | 0.00010805 | 0.11511 | 0.34295 | {C24AC45E-3D92-48D3-91B1-E09F9F7B86E3} | 182611104 | PASO ROBLES 1104 | R56 | 35.6443 | -120.7067 | PASO ROBLES 1104R56 | 164 | 148 | 29668.4386 | 19912.9218 | 9755.5168 | 17514.7266 | 8800.5126 | 0.010481 | 0.0036392 | 2.2862 | 7.1649 | 1815 | 6.4068 | 204 | 0 | 0 | 10.8831 | 2507 | 0
Central Valley | 1329 | 132 | 308.2611 | 560 | 445.4964 | 148 | 4.8976e-05 | 1686.0175 | 27.6516 | 1377.4188 | 7376.9521 | 446.0209 | 33.0439 | 393.4819 | 1.3714 | 0.066034 | 0.00062468 | 0.23571 | 0.69195 | {A70761E3-E888-44FB-B083-651B5C823F25} | 162991102 | CORRAL 1102 | circuit_breaker | 38.1015 | -120.9263 | CORRAL 1102circuit_breaker | 348 | 455 | 53371.3284 | 34251.1303 | 19120.1981 | 25529.3697 | 15812.1298 | 0.092453 | 0.0072484 | 2.3353 | 3.7838 | 646 | 9.7731 | 205 | 0 | 0 | 15.8632 | 576 | 0
Central Valley | 4967 | 543 | 1043.1548 | 1927 | 1517.6765 | 422 | 2.1289e-05 | 3411.8103 | 39.542 | 2001.0827 | 17592.0782 | 1241.2025 | 52.9054 | 776.8098 | 1.6358 | 0.066009 | 0.00042075 | 0.28179 | 0.68734 | {E7B58C7C-DEE3-44AF-9DC1-540E49CB1676} | 254151101 | AUBERRY 1101 | R2578 | 37.0177 | -119.4272 | AUBERRY 1101R2578 | 724 | 671 | 124970.8915 | 74321.3837 | 50649.5078 | 74321.3837 | 50649.5078 | 0.17756 | 0.0089838 | 1.9211 | 4.5664 | 910 | 27.8557 | 206 | 0 | 0 | 46.1812 | 736 | 0
Sierra | 248 | 3 | 5.1177 | 4 | 5.5447 | 2 | 7.2374e-05 | 977.663 |  |  |  |  | 16.1106 | 781.9087 | 1.4347 | 0.065976 | 7.2374e-05 | 0.75 | 0.92298 | {D7243FB0-38B4-4640-8C10-2CD25C9CD868} | 63172101 | MADISON 2101 | 89332 | 38.7354 | -122.1449 | MADISON 210189332 | 242 | 191 | 48170.6677 | 36123.4333 | 12047.2344 | 1160.8504 | 25.5802 | 0.00014475 | 0.00014475 | 1.7059 | 2 | 2040 | 0.13195 | 207 | 0 | 0 | 0.72132 | 266 | 0
North Coast | 4477 | 99 | 136.4092 | 195 | 170.6319 | 50 | 6.7136e-05 | 1003.5386 | 6.3347 | 202.257 | 1740.5162 | 62.547 | 21.6741 | 356.6323 | 1.5386 | 0.065896 | 0.00021494 | 0.50769 | 0.79944 | {541E85BD-7389-44DB-A5D1-1B9283DDEB83} | 42871101 | UPPER LAKE 1101 | 660 | 39.1641 | -122.9236 | UPPER LAKE 1101660 | 114 | 116 | 27211.1828 | 15466.5207 | 11744.6621 | 8469.2097 | 5986.6834 | 0.010747 | 0.0033568 | 1.3779 | 3.9 | 1362 | 3.2948 | 208 | 0 | 0 | 5.2625 | 52 | 0
Central Valley | 5956 | 1 | 1.2277 | 33 | 11.2899 | 18 | 3.6916e-05 | 2229.8647 | 4.1688 | 336.637 | 1295.9309 | 5.3643 | 30.4601 | 1675.8778 | 1.8013 | 0.065242 | 7.3997e-05 | 0.030303 | 0.10874 | {B3FDA245-0020-4744-99E0-2E32EA3113C6} | 254432104 | COARSEGOLD 2104 | 90356 | 37.2198 | -119.9043 | COARSEGOLD 210490356 | 195 | 267 | 45105.0757 | 27329.0227 | 17776.0529 | 7895.0402 | 4775.9978 | 0.0013319 | 0.00066448 | 1.2277 | 1.8333 | 2025 | 1.1744 | 209 | 0 | 0 | 4.9057 | 620 | 0
North Valley | 2425 | 104 | 202.7034 | 231 | 244.8309 | 60 | 6.0756e-05 | 1118.0974 | 117.368 | 1140.6535 | 9573.9677 | 2509.9965 | 28.4796 | 289.3929 | 1.2733 | 0.064794 | 0.0039506 | 0.45022 | 0.82793 | {05CEA4F2-3636-4573-A883-9C548FA0A079} | 103441102 | JESSUP 1102 | 1314 | 40.4467 | -122.4097 | JESSUP 11021314 | 242 | 270 | 40228.1488 | 22635.4523 | 17592.6965 | 8285.2738 | 4307.0382 | 0.23703 | 0.0036454 | 1.9491 | 3.85 | 60 | 3.8877 | 210 | 0 | 0 | 5.1482 | 888 | 0
North Valley | 4317 | 708 | 1269.899 | 2783 | 1948.898 | 334 | 9.6501e-05 | 754.6546 | 38.071 | 372.135 | 2828.6656 | 421.2258 | 20.7162 | 175.7863 | 1.1494 | 0.064746 | 0.0018042 | 0.2544 | 0.6516 | {942A5D01-90B2-440A-92F6-C8D3C90D4346} | 103561102 | STILLWATER 1102 | circuit_breaker | 40.6779 | -122.3497 | STILLWATER 1102circuit_breaker | 465 | 434 | 63313.9788 | 40553.6845 | 22760.2943 | 40538.5999 | 22760.2943 | 0.60259 | 0.032231 | 1.7936 | 8.3323 | 193 | 21.6253 | 211 | 0 | 0 | 25.1895 | 1547 | 0
North Coast | 9224 | 275 | 357.1122 | 324 | 382.1248 | 35 | 9.6438e-05 | 719.4096 | 83.6546 | 1556.1189 | 26972.824 | 4312.3908 | 14.5834 | 174.4825 | 1.1802 | 0.064742 | 0.004524 | 0.84877 | 0.93454 | {30B0A48E-C3E5-42AA-9273-8BF1B6001968} | 42661103 | WILLITS 1103 | circuit_breaker | 39.4056 | -123.3269 | WILLITS 1103circuit_breaker | 78 | 101 | 15608.9653 | 6322.4453 | 9286.5201 | 4233.1434 | 7737.1244 | 0.15834 | 0.0033753 | 1.2986 | 9.2571 | 43 | 2.266 | 212 | 0 | 0 | 2.6304 | 1873 | 0
North Valley | 5326 | 44 | 77.3951 | 218 | 126.9282 | 27 | 4.6214e-05 | 1488.53 | 26.6985 | 164.4359 | 799.4558 | 50.3364 | 25.92 | 231.5567 | 1.3335 | 0.063562 | 0.00044683 | 0.20183 | 0.60975 | {A372AD67-1459-47B8-8964-55AFC8B0D599} | 102911109 | WYANDOTTE 1109 | circuit_breaker | 39.4915 | -121.5411 | WYANDOTTE 1109circuit_breaker | 254 | 430 | 35534.6898 | 15084.5037 | 20450.1862 | 3677.1991 | 2444.5703 | 0.012064 | 0.0012478 | 1.759 | 8.0741 | 867 | 1.7162 | 213 | 0 | 0 | 2.2849 | 314 | 0
Central Valley | 1088 | 42 | 89.0641 | 188 | 135.0779 | 81 | 2.9563e-05 | 2396.8492 | 84.797 | 5312.6152 | 37605.3229 | 5905.3646 | 26.341 | 1724.1254 | 1.9642 | 0.063318 | 0.0010772 | 0.2234 | 0.65935 | {81F65546-748C-422D-A853-780F9DAF978A} | 254432104 | COARSEGOLD 2104 | 10030 | 37.2233 | -119.7692 | COARSEGOLD 210410030 | 159 | 149 | 40042.3627 | 28835.8758 | 11206.4869 | 23477.104 | 7722.0997 | 0.08725 | 0.0023946 | 2.1206 | 2.321 | 374 | 5.1287 | 214 | 0 | 0 | 14.588 | 1355 | 0
North Valley | 8700 | 2 | 3.9241 | 7 | 5.632 | 3 | 7.0591e-05 | 940.7647 | 3.8843 | 3803.1321 | 26975.6855 | 107.9574 | 14.1327 | 1922.4246 | 1.9823 | 0.063015 | 0.00012199 | 0.28571 | 0.69675 | {375728DD-644E-4E4B-9A8F-230DD2D4E917} | 102541101 | VOLTA 1101 | 65764 | 40.4014 | -121.8771 | VOLTA 110165764 | 52 | 20 | 18309.952 | 16669.3981 | 1640.5539 | 16669.3981 | 1640.5539 | 0.00036597 | 0.00021177 | 1.9621 | 2.3333 | 1742 | 0.18905 | 215 | 0 | 0 | 10.3579 | 455 | 0
North Coast | 5211 | 696 | 1210.3587 | 1075 | 1412.9565 | 92 | 0.00015082 | 483.009 | 9.3691 | 508.2918 | 9322.1379 | 271.8644 | 0.84374 | 37.7612 | 1.2032 | 0.062852 | 0.00070159 | 0.64744 | 0.85661 | {30AC1F79-37C1-4981-9C64-81FC3670878D} | 42751113 | FITCH MOUNTAIN 1113 | 24918 | 38.5914 | -122.92 | FITCH MOUNTAIN 111324918 | 63 | 45 | 13406.7479 | 8527.9094 | 4878.8385 | 8527.9094 | 4878.8385 | 0.064546 | 0.013875 | 1.739 | 11.6848 | 566 | 5.7824 | 216 | 0 | 0 | 5.299 | 414 | 0
North Valley | 466 | 227 | 792.8153 | 1878 | 1181.887 | 420 | 4.2912e-05 | 1424.8276 | 30.6839 | 941.8697 | 6767.381 | 385.1089 | 23.55 | 598.4017 | 1.4921 | 0.062652 | 0.00057747 | 0.12087 | 0.6708 | {DB1CB0BF-953F-4047-B280-2F768227CB6A} | 102931103 | COTTONWOOD 1103 | 1616 | 40.3561 | -122.3264 | COTTONWOOD 11031616 | 590 | 594 | 113625.6123 | 78749.1842 | 34876.4281 | 73500.8728 | 30035.3587 | 0.24254 | 0.018023 | 3.4926 | 4.4714 | 703 | 26.3137 | 217 | 0 | 0 | 45.6713 | 791 | 0
North Coast | 7963 | 138 | 169.2778 | 270 | 231.2141 | 56 | 8.0154e-05 | 982.3864 |  |  |  |  | 11.7113 | 240.9409 | 1.229 | 0.062453 | 8.0154e-05 | 0.51111 | 0.73213 | {1B6A9064-674E-4151-B148-004CA8DBD66C} | 43411101 | CALPELLA 1101 | 3419 | 39.3191 | -123.2998 | CALPELLA 11013419 | 49 | 40 | 15225.2571 | 12991.6223 | 2233.6349 | 12991.6223 | 2233.6349 | 0.0044886 | 0.0044886 | 1.2267 | 4.8214 | 1981 | 3.4974 | 218 | 0 | 0 | 8.0726 | 61 | 0
Sierra | 2009 | 10 | 15.7863 | 20 | 19.7442 | 5 | 9.9625e-05 | 381.3977 | 12.7383 | 520.2805 | 3897.5417 | 49.5729 | 12.9894 | 154.8675 | 1.1549 | 0.062331 | 0.00017302 | 0.5 | 0.79954 | {A71D3F90-1807-4414-8E54-A388088D7CB1} | 153701104 | LINCOLN 1104 | 2072 | 38.9256 | -121.2469 | LINCOLN 11042072 | 293 | 339 | 51528.0315 | 27455.4475 | 24072.584 | 512.0053 | 336.4531 | 0.00086512 | 0.00049813 | 1.5786 | 4 | 1513 | 0.31165 | 219 | 0 | 0 | 0.31815 | 2115 | 0
Bay Area | 9469 | 25 | 51.5391 | 78 | 82.9195 | 17 | 1.5624e-05 | 3548.7657 | 43.9605 | 1725.5389 | 6810.2495 | 543.48 | 46.309 | 1695.1898 | 1.8286 | 0.062315 | 0.00039051 | 0.32051 | 0.62156 | {46301E96-9614-4B53-A8A4-29FAA9DC1F0B} | 14452104 | KIRKER 2104 | 442850 | 37.9909 | -121.8962 | KIRKER 2104442850 | 26 | 18 | 11132.8365 | 9153.4289 | 1979.4076 | 9153.4289 | 1979.4076 | 0.0066387 | 0.00026561 | 2.0616 | 4.5882 | 958 | 1.0594 | 220 | 0 | 0 | 5.6877 | 1559 | 0
Sierra | 5504 | 1190 | 2066.461 | 4351 | 3300.3003 | 676 | 5.0697e-05 | 1246.1156 | 12.9347 | 271.829 | 2073.0489 | 55.0658 | 20.8685 | 343.7288 | 1.4165 | 0.062269 | 0.0003289 | 0.2735 | 0.62614 | {740DE1B6-71C4-4F89-BFF6-C379E023E99F} | 152691109 | HIGGINS 1109 | 50072 | 39.0757 | -121.1143 | HIGGINS 110950072 | 688 | 578 | 129864.4027 | 82323.743 | 47540.6597 | 82323.743 | 47540.6597 | 0.22233 | 0.034271 | 1.7365 | 6.4364 | 1058 | 42.0939 | 221 | 0 | 0 | 51.1536 | 554 | 0
North Coast | 2778 | 860 | 1164.135 | 1710 | 1613.6055 | 160 | 9.6561e-05 | 603.7009 | 6.2078 | 320.5028 | 6748.3779 | 165.9876 | 1.8839 | 49.9071 | 1.2884 | 0.062201 | 0.00029827 | 0.50292 | 0.72145 | {BFE1D441-2168-4D90-8012-C988D5F78BF2} | 42891101 | GEYSERVILLE 1101 | 166 | 38.7162 | -122.9206 | GEYSERVILLE 1101166 | 225 | 174 | 43513.8511 | 25913.2012 | 17600.6499 | 18354.3619 | 12104.1387 | 0.047723 | 0.01545 | 1.3536 | 10.6875 | 1128 | 9.9522 | 222 | 0 | 0 | 11.4049 | 1341 | 0
North Valley | 4708 | 164 | 345.4882 | 865 | 535.4391 | 123 | 5.2179e-05 | 1288.2056 | 28.6254 | 152.5349 | 1250.2933 | 89.9452 | 22.2691 | 257.7573 | 1.4512 | 0.061968 | 0.0007648 | 0.1896 | 0.64524 | {D8B4A6F8-9874-47E2-910D-F4C8426E6854} | 103521102 | OREGON TRAIL 1102 | circuit_breaker | 40.6191 | -122.3222 | OREGON TRAIL 1102circuit_breaker | 140 | 102 | 20636.336 | 15715.8206 | 4920.5154 | 15165.9787 | 4746.7588 | 0.094071 | 0.006418 | 2.1066 | 7.0325 | 524 | 7.6221 | 223 | 0 | 0 | 9.4237 | 933 | 0
Sierra | 1980 | 475 | 727.8651 | 1526 | 1094.024 | 180 | 0.0001314 | 545.3873 | 53.1034 | 289.0618 | 2487.1797 | 500.8057 | 11.8159 | 108.1755 | 1.2705 | 0.061829 | 0.0031698 | 0.31127 | 0.66531 | {45D8F3A6-BB8E-411A-86FA-8F2AAEC54597} | 153652109 | SHINGLE SPRINGS 2109 | 12392 | 38.711 | -120.9434 | SHINGLE SPRINGS 210912392 | 303 | 422 | 49163.1865 | 23968.2562 | 25194.9303 | 23968.2562 | 25194.9303 | 0.57056 | 0.023651 | 1.5323 | 8.4778 | 97 | 11.1292 | 224 | 0 | 0 | 14.8932 | 164 | 0
Central Valley | 698 | 355 | 667.2623 | 1772 | 1193.8619 | 422 | 4.8497e-05 | 1366.0095 | 19.7324 | 511.3592 | 4846.1646 | 417.684 | 19.0095 | 365.1999 | 1.4427 | 0.061681 | 0.00048333 | 0.20034 | 0.55891 | {2E4BA31C-6FC8-4D7D-B79B-DB347A05F67C} | 254432103 | COARSEGOLD 2103 | circuit_breaker | 37.2273 | -119.6902 | COARSEGOLD 2103circuit_breaker | 610 | 847 | 113630.6641 | 61823.6709 | 51806.9932 | 61823.6709 | 51806.9932 | 0.20397 | 0.020466 | 1.8796 | 4.1991 | 807 | 26.0295 | 225 | 0 | 0 | 38.4154 | 1464 | 0
Central Coast | 6799 | 28 | 54.5031 | 71 | 78.8973 | 13 | 4.133e-05 | 1538.8319 | 88.0882 | 420.1032 | 1146.8059 | 130.6274 | 31.3918 | 179.7376 | 1.2631 | 0.061653 | 0.0008777 | 0.39437 | 0.69081 | {248D5525-98DB-494D-8A88-8F5511E7C8B0} | 182721102 | SANTA YNEZ 1102 | circuit_breaker | 34.6252 | -120.119 | SANTA YNEZ 1102circuit_breaker | 297 | 391 | 30440.5735 | 14333.2897 | 16107.2838 | 1351.6956 | 445.0694 | 0.01141 | 0.00053729 | 1.9465 | 5.4615 | 460 | 0.8015 | 226 | 0 | 0 | 0.8399 | 1819 | 0
North Coast | 1466 | 356 | 491.3357 | 515 | 587.3068 | 67 | 7.5273e-05 | 764.1475 | 10.5428 | 311.9728 | 4281.1192 | 61.511 | 3.86 | 82.4458 | 1.3953 | 0.061527 | 0.00043686 | 0.69126 | 0.83659 | {1FD9348C-4D4E-4981-80D7-DF41347DC4BB} | 42821101 | CLOVERDALE 1101 | circuit_breaker | 38.7973 | -123.0106 | CLOVERDALE 1101circuit_breaker | 212 | 474 | 39790.7548 | 14601.0166 | 25189.7381 | 7970.5303 | 4893.9246 | 0.029269 | 0.0050433 | 1.3802 | 7.6866 | 886 | 4.1223 | 227 | 0 | 0 | 4.9527 | 1265 | 0
North Valley | 3817 | 208 | 554.21 | 765 | 693.0394 | 163 | 3.375e-05 | 1930.6145 | 7.2215 | 327.3058 | 1899.1193 | 63.109 | 33.4579 | 1046.7695 | 1.2991 | 0.061492 | 0.000149 | 0.2719 | 0.79968 | {A95819FE-BBB2-462E-B600-5672D7BA2538} | 103331101 | CORNING 1101 | 64090 | 39.9967 | -122.4058 | CORNING 110164090 | 243 | 302 | 29129.3413 | 22037.5277 | 7091.8135 | 22037.5277 | 7091.8135 | 0.024288 | 0.0055013 | 2.6645 | 4.6933 | 1597 | 10.0231 | 228 | 0 | 0 | 13.6935 | 831 | 0
Central Coast | 6065 | 14 | 17.7115 | 279 | 90.4 | 49 | 2.9906e-05 | 2118.366 | 3.3103 | 149.2187 | 667.1464 | 5.769 | 27.2028 | 858.1109 | 1.6162 | 0.061398 | 6.0933e-05 | 0.050179 | 0.19592 | {4F9BDDE8-58A1-4E37-A7DD-695333A57C0E} | 182661104 | SAN MIGUEL 1104 | N60 | 35.6957 | -120.7406 | SAN MIGUEL 1104N60 | 86 | 49 | 17901.2402 | 14225.5578 | 3675.6824 | 12563.9317 | 3023.699 | 0.0029857 | 0.0014654 | 1.2651 | 5.6939 | 2126 | 3.0085 | 229 | 0 | 0 | 7.8069 | 2154 | 0
North Coast | 6417 | 114 | 138.6281 | 186 | 173.8917 | 20 | 0.00011551 | 535.0615 | 4.1607 | 310.483 | 1564.3949 | 34.6121 | 9.3035 | 203.644 | 1.2121 | 0.060947 | 0.00021714 | 0.6129 | 0.79721 | {216E9E12-5043-456A-946D-A8BF7CCC2C71} | 42281105 | POTTER VALLEY P H 1105 | 37476 | 39.3171 | -123.1131 | POTTER VALLEY P H 110537476 | 102 | 98 | 25121.9056 | 14076.6161 | 11045.2894 | 3321.5283 | 3655.9073 | 0.0043428 | 0.0023103 | 1.216 | 9.3 | 1351 | 1.2189 | 230 | 0 | 0 | 2.0639 | 817 | 0
Sierra | 6626 | 69 | 116.2896 | 163 | 147.6649 | 36 | 6.2693e-05 | 1332.7841 | 25.4716 | 143.1114 | 707.0686 | 40.3302 | 22.464 | 342.9624 | 1.3844 | 0.060796 | 0.00048915 | 0.42331 | 0.78752 | {24BA7214-EA0E-4940-8D9A-B12BFFD010BB} | 153612104 | CLARKSVILLE 2104 | circuit_breaker | 38.6558 | -121.0597 | CLARKSVILLE 2104circuit_breaker | 166 | 75 | 21215.497 | 16768.2889 | 4447.208 | 14071.4401 | 3833.106 | 0.017609 | 0.002257 | 1.6854 | 4.5278 | 799 | 2.1887 | 231 | 0 | 0 | 8.7436 | 644 | 0
North Valley | 888 | 63 | 113.4286 | 157 | 142.9125 | 53 | 3.1231e-05 | 1940.0278 | 11.3741 | 3191.3806 | 18605.9282 | 328.3425 | 20.2129 | 2547.8488 | 1.7346 | 0.060656 | 0.0002202 | 0.40127 | 0.79369 | {3333A9F4-A222-4545-831F-9DC4F4A4E477} | 103331102 | CORNING 1102 | 90036 | 39.9149 | -122.4287 | CORNING 110290036 | 120 | 82 | 24689.3486 | 22997.6015 | 1691.7471 | 19887.703 | 1559.6427 | 0.011671 | 0.0016552 | 1.8005 | 2.9623 | 1343 | 3.2148 | 232 | 0 | 0 | 12.3576 | 1188 | 0
Sierra | 6195 | 349 | 681.0113 | 2006 | 1221.2096 | 504 | 3.5101e-05 | 1606.8678 | 12.679 | 789.947 | 4208.9863 | 88.1022 | 24.3214 | 504.6026 | 1.5085 | 0.060404 | 0.00022808 | 0.17398 | 0.55765 | {13205944-27DE-4E69-8D25-637FC945A119} | 152691109 | HIGGINS 1109 | 50078 | 39.0539 | -121.1137 | HIGGINS 110950078 | 542 | 402 | 122683.1141 | 77708.0128 | 44975.1013 | 77708.0128 | 44975.1013 | 0.11495 | 0.017691 | 1.9513 | 3.9802 | 1318 | 30.4436 | 233 | 0 | 0 | 48.2855 | 446 | 0
Bay Area | 5665 | 2163 | 3848.7491 | 2800 | 4186.1865 | 216 | 0.0001389 | 454.1326 | 2.8915 | 40.6041 | 292.5065 | 4.3735 | 1.6644 | 31.4247 | 1.1603 | 0.060272 | 0.00031007 | 0.7725 | 0.91939 | {841AD544-FFC0-4D92-904D-46B27F7D9430} | 43432104 | SILVERADO 2104 | 632 | 38.574 | -122.4444 | SILVERADO 2104632 | 280 | 254 | 54137.9478 | 30072.3446 | 24065.6032 | 29545.0013 | 24010.4515 | 0.066975 | 0.030002 | 1.7794 | 12.963 | 1099 | 13.0187 | 234 | 0 | 0 | 18.3584 | 2595 | 0
North Coast | 7360 | 113 | 217.9581 | 190 | 242.1588 | 73 | 5.9889e-05 | 987.8948 | 3.8523 | 759.8467 | 7166.1066 | 113.8593 | 4.908 | 1220.8528 | 1.8782 | 0.059961 | 0.00018538 | 0.59474 | 0.90006 | {805F8CD4-618B-4641-8C2C-AEC1BF35DB49} | 43361102 | HIGHLANDS 1102 | 628 | 38.9823 | -122.603 | HIGHLANDS 1102628 | 58 | 31 | 29074.0249 | 22902.6806 | 6171.3443 | 22902.6806 | 6171.3443 | 0.013533 | 0.0043719 | 1.9288 | 2.6027 | 1463 | 4.3771 | 235 | 0 | 0 | 14.2311 | 2538 | 0
North Valley | 1731 | 60 | 118.9571 | 1008 | 353.9105 | 301 | 3.7901e-05 | 1513.5376 | 22.184 | 546.428 | 3617.8469 | 170.2027 | 26.016 | 624.6629 | 1.4216 | 0.059694 | 0.00045153 | 0.059524 | 0.33612 | {E9A98F80-2CD6-4193-969F-CD417879D03A} | 103541104 | RED BLUFF 1104 | 51238 | 40.2385 | -122.2597 | RED BLUFF 110451238 | 418 | 367 | 87550.541 | 63182.0088 | 24368.5322 | 63182.0088 | 24368.5322 | 0.13591 | 0.011408 | 1.9826 | 3.3488 | 859 | 17.968 | 236 | 0 | 0 | 39.2595 | 1395 | 0
North Valley | 1610 | 20 | 38.4552 | 36 | 44.8604 | 12 | 0.0001001 | 570.7031 | 59.8252 | 1241.8901 | 9058.6948 | 663.2262 | 15.4417 | 269.2824 | 1.3101 | 0.059289 | 0.0010745 | 0.55556 | 0.85722 | {A7720DBE-D298-421E-A3B2-FE12C335EE16} | 103441101 | JESSUP 1101 | circuit_breaker | 40.4616 | -122.3279 | JESSUP 1101circuit_breaker | 120 | 283 | 23493.9506 | 9377.0793 | 14116.8713 | 2330.0107 | 873.851 | 0.012893 | 0.0012012 | 1.9228 | 3 | 375 | 0.71147 | 237 | 0 | 0 | 1.4478 | 1598 | 0
North Coast | 6674 | 245 | 421.7964 | 401 | 497.506 | 59 | 0.00025008 | 244.1615 | 3.8233 | 200.6768 | 2400.1608 | 35.9513 | 1.5676 | 75.9335 | 1.205 | 0.059158 | 0.0006168 | 0.61097 | 0.84782 | {4FAFA82B-3330-476C-B978-ABE18A7516EA} | 192221101 | GARBERVILLE 1101 | 39524 | 40.0751 | -123.788 | GARBERVILLE 110139524 | 202 | 234 | 36408.3051 | 24862.4083 | 11545.8968 | 7261.0619 | 2681.9641 | 0.036391 | 0.014755 | 1.7216 | 6.7966 | 653 | 3.4903 | 238 | 0 | 0 | 4.5118 | 1353 | 0
Central Coast | 3082 | 157 | 281.5543 | 248 | 326.8607 | 41 | 3.8061e-05 | 1757.8932 | 15.5353 | 36.2395 | 104.6734 | 11.4197 | 28.0662 | 340.8271 | 1.2532 | 0.059107 | 0.00018318 | 0.63306 | 0.86139 | {10BA1E2F-8A72-4CA0-9D11-9A4EEB187DC3} | 83242105 | MORGAN HILL 2105 | XR564 | 37.0455 | -121.6522 | MORGAN HILL 2105XR564 | 142 | 100 | 19488.0815 | 11614.6161 | 7873.4654 | 8673.0497 | 6093.6115 | 0.0075103 | 0.0015605 | 1.7933 | 6.0488 | 1471 | 2.4234 | 239 | 0 | 0 | 5.3892 | 1700 | 0
North Valley | 8921 | 68 | 129.8421 | 161 | 152.2509 | 56 | 7.5001e-05 | 773.0667 | 6.77 | 2158.2178 | 17439.7314 | 315.3551 | 11.0753 | 1169.8647 | 1.7036 | 0.058979 | 0.00028136 | 0.42236 | 0.85282 | {93B1D857-8A90-4B8A-BADD-0500DBB7E745} | 102781101 | ELK CREEK 1101 | 2032 | 39.3759 | -122.5504 | ELK CREEK 11012032 | 65 | 55 | 19688.5308 | 15248.6713 | 4439.8595 | 13755.3854 | 4439.8595 | 0.015756 | 0.0042001 | 1.9094 | 2.875 | 1173 | 3.3028 | 240 | 0 | 0 | 8.5472 | 1443 | 0
North Valley | 322 | 110 | 199.5808 | 290 | 252.7968 | 117 | 2.9727e-05 | 1816.7712 | 3.1 | 3193.4431 | 21335.5593 | 166.9699 | 9.8725 | 2286.9105 | 1.8028 | 0.058732 | 7.8711e-05 | 0.37931 | 0.78949 | {15DF5EF9-6694-4A35-B7F3-919A8A286CFC} | 103331102 | CORNING 1102 | 53184 | 39.9132 | -122.4295 | CORNING 110253184 | 156 | 152 | 56957.8324 | 51349.7049 | 5608.1275 | 51349.7049 | 5608.1275 | 0.0092091 | 0.0034781 | 1.8144 | 2.4786 | 1994 | 6.8716 | 241 | 0 | 0 | 31.9072 | 1054 | 0
Bay Area | 7388 | 101 | 211.1202 | 205 | 257.0338 | 24 | 2.8628e-05 | 2278.3061 | 4.0624 | 354.552 | 1839.0672 | 51.0241 | 31.0923 | 1090.0188 | 1.2946 | 0.058607 | 5.7507e-05 | 0.49268 | 0.82137 | {74227EDF-7C62-40BA-8814-7C9EED050025} | 14052103 | NORTH DUBLIN 2103 | 9473 | 37.7863 | -121.8632 | NORTH DUBLIN 21039473 | 39 | 37 | 6104.3672 | 4731.0233 | 1373.3439 | 3725.6021 | 1271.7098 | 0.0013802 | 0.00068707 | 2.0903 | 8.5417 | 2161 | 1.4066 | 242 | 0 | 0 | 2.315 | 2895 | 0
Sierra | 1057 | 267 | 484.0289 | 1220 | 882.0193 | 94 | 8.2006e-05 | 690.811 | 14.574 | 249.1943 | 1356.663 | 32.5259 | 20.1033 | 233.2 | 1.1271 | 0.05841 | 0.00048394 | 0.21885 | 0.54877 | {46334C59-6E86-4DFA-8790-B3204A43F682} | 153701101 | LINCOLN 1101 | 95756 | 38.887 | -121.2381 | LINCOLN 110195756 | 302 | 307 | 47236.9443 | 28755.3134 | 18481.6309 | 9885.2869 | 5026.9633 | 0.04549 | 0.0077085 | 1.8128 | 12.9787 | 805 | 5.4906 | 243 | 0 | 0 | 6.1424 | 542 | 0
Central Valley | 6372 | 343 | 570.6989 | 1417 | 932.0087 | 338 | 2.1013e-05 | 2723.2734 | 152.5642 | 7259.2902 | 57400.7864 | 11397.9314 | 35.8012 | 1097.6056 | 1.7647 | 0.05829 | 0.0015993 | 0.24206 | 0.61233 | {69DA4F1C-E07E-4189-8040-902C89E5A469} | 252941107 | TIVY VALLEY 1107 | 584840 | 36.7262 | -119.2563 | TIVY VALLEY 1107584840 | 596 | 565 | 118294.5311 | 72367.2531 | 45927.278 | 72367.2531 | 45927.278 | 0.54056 | 0.0071023 | 1.6638 | 4.1923 | 229 | 19.7021 | 244 | 0 | 0 | 44.9669 | 1295 | 0
North Valley | 3191 | 58 | 90.1987 | 410 | 213.7727 | 56 | 9.6673e-05 | 602.178 | 4.8485 | 31.2576 | 155.5513 | 2.7406 | 19.725 | 176.1613 | 1.2981 | 0.057704 | 0.00028693 | 0.14146 | 0.42194 | {87B1630C-320C-4426-9018-625251B99E73} | 103261103 | ANDERSON 1103 | circuit_breaker | 40.4497 | -122.3047 | ANDERSON 1103circuit_breaker | 431 | 568 | 60215.3064 | 33602.3141 | 26612.9923 | 5997.7664 | 5012.1515 | 0.016068 | 0.0054137 | 1.5552 | 7.3214 | 1156 | 3.2314 | 245 | 0 | 0 | 3.7268 | 913 | 0
Central Valley | 8735 | 1 | 1.2277 | 66 | 17.8055 | 26 | 2.4836e-05 | 2470.766 | 145.2595 | 7790.9524 | 49993.8391 | 7290.6651 | 35.4202 | 1179.7103 | 1.7592 | 0.057599 | 0.002471 | 0.015152 | 0.068952 | {50C5ADB6-0C49-498A-ACD5-0AA4887D7C48} | 254601103 | SAND CREEK 1103 | 7823F | 36.7004 | -119.2516 | SAND CREEK 11037823F | 62 | 66 | 10783.9957 | 7345.0348 | 3438.9609 | 7345.0348 | 3438.9609 | 0.064245 | 0.00064573 | 1.2277 | 2.5385 | 128 | 1.4976 | 246 | 0 | 0 | 4.564 | 570 | 0
North Coast | 6519 | 652 | 996.0855 | 1054 | 1178.2012 | 197 | 5.8694e-05 | 952.4342 | 1.865 | 558.8897 | 9372.3482 | 47.2367 | 4.8869 | 328.5425 | 1.531 | 0.0574 | 8.2306e-05 | 0.6186 | 0.84543 | {B4EDF571-A5E6-4473-9456-D58C67AB0D1F} | 42601101 | PHILO 1101 | 37222 | 38.9147 | -123.272 | PHILO 110137222 | 174 | 134 | 54185.1953 | 40901.8789 | 13283.3164 | 40901.8789 | 13283.3164 | 0.016214 | 0.011563 | 1.5277 | 5.3503 | 1968 | 11.3077 | 247 | 0 | 0 | 25.4152 | 828 | 0
Sierra | 3324 | 14 | 24.6824 | 104 | 61.5483 | 14 | 6.844e-05 | 769.0023 | 4.4738 | 22.239 | 97.4789 | 0.7191 | 25.1367 | 233.5081 | 1.2042 | 0.057397 | 0.00023558 | 0.13462 | 0.40103 | {1E1BA976-38CE-4912-807F-3A5F3BFF5CD1} | 152561105 | PENRYN 1105 | 1378 | 38.8751 | -121.134 | PENRYN 11051378 | 62 | 155 | 8616.3077 | 3002.3902 | 5613.9175 | 1299.5417 | 722.5883 | 0.0032981 | 0.00095815 | 1.763 | 7.4286 | 1294 | 0.80356 | 248 | 0 | 0 | 0.8075 | 442 | 0
Central Valley | 1025 | 502 | 857.2938 | 2804 | 1748.66 | 526 | 4.4762e-05 | 1324.2958 | 14.1771 | 932.5873 | 7549.0418 | 262.3316 | 20.9753 | 561.3944 | 1.6236 | 0.057365 | 0.00029202 | 0.17903 | 0.49026 | {9C7CA36A-A220-4889-B18C-7665D5C736E3} | 254452102 | MARIPOSA 2102 | 37282 | 37.4622 | -119.9482 | MARIPOSA 210237282 | 635 | 638 | 161618.8021 | 96120.2252 | 65498.577 | 81850.6465 | 57628.3858 | 0.1536 | 0.023545 | 1.7078 | 5.3308 | 1147 | 30.1742 | 249 | 0 | 0 | 50.8596 | 354 | 0
Sierra | 8370 | 115 | 203.9957 | 570 | 373.5756 | 84 | 0.00014617 | 400.6444 | 22.8049 | 300.3179 | 3133.4025 | 116.6023 | 10.4358 | 81.738 | 1.1314 | 0.057274 | 0.0015165 | 0.20175 | 0.54606 | {21717BF3-E14B-476C-94A8-5495C36BA027} | 153651103 | SHINGLE SPRINGS 1103 | circuit_breaker | 38.6593 | -120.9471 | SHINGLE SPRINGS 1103circuit_breaker | 239 | 148 | 28585.51 | 19101.7778 | 9483.7322 | 9623.2164 | 4542.9944 | 0.12738 | 0.012278 | 1.7739 | 6.7857 | 243 | 4.811 | 250 | 0 | 0 | 5.9796 | 781 | 0
Bay Area | 3539 | 109 | 253.6916 | 196 | 293.4562 | 62 | 1.8782e-05 | 2819.2666 | 1.2214 | 349.9836 | 2554.948 | 45.2495 | 32.6822 | 2471.9527 | 1.6276 | 0.057097 | 1.9625e-05 | 0.55612 | 0.8645 | {CB1F79C6-162B-44E7-BDF1-619119F35335} | 14422109 | CAYETANO 2109 | circuit_breaker | 37.7382 | -121.7709 | CAYETANO 2109circuit_breaker | 275 | 177 | 64446.1331 | 46595.6391 | 17850.4941 | 30595.1389 | 13259.5773 | 0.0012168 | 0.0011645 | 2.3274 | 3.1613 | 2617 | 3.54 | 251 | 0 | 0 | 19.0109 | 2809 | 0
North Valley | 5848 | 220 | 469.1974 | 1047 | 685.7859 | 259 | 3.2958e-05 | 1753.5626 | 8.6489 | 2176.705 | 13533.4112 | 257.9132 | 17.0603 | 2185.5982 | 1.6498 | 0.056452 | 0.00013586 | 0.21012 | 0.68417 | {C22EF53B-7E85-45CF-AC1D-13B919BBB848} | 103571105 | TYLER 1105 | 85132 | 40.1198 | -122.3334 | TYLER 110585132 | 262 | 185 | 64583.1856 | 50197.6466 | 14385.539 | 50197.6466 | 14385.539 | 0.035187 | 0.0085362 | 2.1327 | 4.0425 | 1659 | 14.6211 | 252 | 0 | 0 | 31.1914 | 428 | 0
Sierra | 2248 | 812 | 1465.3928 | 4046 | 2516.4268 | 586 | 7.4923e-05 | 887.2942 | 37.403 | 469.4738 | 4290.843 | 300.4156 | 17.5819 | 151.4082 | 1.272 | 0.056436 | 0.0014082 | 0.20069 | 0.58233 | {C2386B39-9DEB-4629-9750-D5EE983424AF} | 153652109 | SHINGLE SPRINGS 2109 | 13322 | 38.7691 | -120.9274 | SHINGLE SPRINGS 210913322 | 725 | 666 | 121513.8986 | 66862.7414 | 54651.1572 | 66862.7414 | 54651.1572 | 0.8252 | 0.043905 | 1.8047 | 6.9044 | 272 | 33.0717 | 253 | 0 | 0 | 41.5466 | 1080 | 0
North Coast | 1615 | 518 | 1278.0699 | 814 | 1414.764 | 115 | 7.9814e-05 | 726.0333 | 53.092 | 1220.7162 | 6389.3669 | 685.8052 | 27.2327 | 159.0658 | 1.0972 | 0.056414 | 0.0022529 | 0.63636 | 0.90338 | {D9AD31E8-B05C-4E93-8F8E-12B049A59011} | 42271105 | COTATI 1105 | 99720 | 38.3457 | -122.7784 | COTATI 110599720 | 215 | 355 | 43470.3251 | 19787.8115 | 23682.5136 | 14251.5886 | 18723.0603 | 0.25908 | 0.0091786 | 2.4673 | 7.0783 | 156 | 6.4876 | 254 | 0 | 0 | 8.8555 | 1069 | 0
North Valley | 4469 | 9 | 12.9366 | 15 | 14.9153 | 6 | 5.6335e-05 | 1098.5156 | 0.88834 | 3365.9259 | 18816.9557 | 35.0101 | 4.5911 | 2552.2412 | 1.7994 | 0.05591 | 6.0332e-05 | 0.6 | 0.86734 | {0DB23F18-2307-44BE-917D-7278F1DC4733} | 103142102 | LOGAN CREEK 2102 | 2226 | 39.4804 | -122.2506 | LOGAN CREEK 21022226 | 132 | 91 | 60370.0905 | 56162.3689 | 4207.7216 | 5964.9276 | 266.8638 | 0.00036199 | 0.00033801 | 1.4374 | 2.5 | 2136 | 0.33546 | 255 | 0 | 0 | 3.7064 | 1981 | 0
North Valley | 538 | 470 | 901.2947 | 1908 | 1356.4294 | 309 | 8.1193e-05 | 807.9456 | 71.7794 | 1009.7377 | 7564.5973 | 1520.6041 | 18.673 | 336.4882 | 1.2315 | 0.055068 | 0.0023957 | 0.24633 | 0.66446 | {2295AFD6-60F9-4656-92BA-00A16BCFB50A} | 103561102 | STILLWATER 1102 | 1644 | 40.6905 | -122.2786 | STILLWATER 11021644 | 345 | 349 | 57566.2314 | 36671.0244 | 20895.2071 | 36671.0244 | 20895.2071 | 0.74027 | 0.025089 | 1.9176 | 6.1748 | 139 | 17.0159 | 256 | 0 | 0 | 22.7863 | 2414 | 0
North Coast | 6282 | 575 | 948.8006 | 1394 | 1369.856 | 142 | 0.00015062 | 425.3165 | 8.8847 | 181.0335 | 1168.9884 | 28.1227 | 8.5349 | 103.9769 | 1.1789 | 0.054399 | 0.00064483 | 0.41248 | 0.69263 | {4AE7AB5F-C633-47AF-9F7F-61FE17B35998} | 42571102 | MOLINO 1102 | 66006 | 38.4055 | -122.9478 | MOLINO 110266006 | 156 | 157 | 23731.1845 | 14413.6045 | 9317.5799 | 14413.6045 | 9317.5799 | 0.091566 | 0.021389 | 1.6501 | 9.8169 | 621 | 7.7247 | 257 | 0 | 0 | 8.9562 | 321 | 0
Central Valley | 4896 | 112 | 253.2845 | 486 | 386.3562 | 127 | 2.5833e-05 | 2160.2403 | 144.4929 | 9163.2615 | 78181.5784 | 13977.9317 | 30.9397 | 725.691 | 1.6844 | 0.054194 | 0.0018416 | 0.23045 | 0.65557 | {5ED2B13E-98E4-45F9-A6A0-57DA496030DD} | 254151102 | AUBERRY 1102 | R902 | 37.0347 | -119.5181 | AUBERRY 1102R902 | 236 | 176 | 39784.1113 | 24311.5038 | 15472.6074 | 24311.5038 | 15472.6074 | 0.23388 | 0.0032808 | 2.2615 | 3.8268 | 189 | 6.8827 | 258 | 0 | 0 | 15.1065 | 759 | 0
Central Valley | 4582 | 36 | 64.4942 | 145 | 102.9682 | 41 | 1.9684e-05 | 3188.2502 | 127.1577 | 9068.6416 | 65485.8703 | 11964.3273 | 40.4181 | 2220.8767 | 1.8774 | 0.05409 | 0.0011781 | 0.24828 | 0.62635 | {7AEDC5DF-B44F-49B0-91EC-479413610904} | 252411104 | COPPERMINE 1104 | R755 | 36.8683 | -119.5573 | COPPERMINE 1104R755 | 540 | 416 | 156133.8384 | 99071.0889 | 57062.7495 | 14117.8234 | 11732.5414 | 0.048303 | 0.00080704 | 1.7915 | 3.5366 | 332 | 2.2177 | 259 | 0 | 0 | 8.7724 | 1901 | 0
Central Coast | 9379 | 3 | 3.6831 | 35 | 18.2667 | 5 | 2.1709e-05 | 2849.3711 | 7.0301 | 75.1988 | 254.4974 | 3.2322 | 42.2996 | 376.0218 | 1.2752 | 0.054019 | 7.948e-05 | 0.085714 | 0.20163 | {E103D17D-C161-441C-8C05-D72D4B887C7A} | 183052113 | TEMPLETON 2113 | 2949 | 35.5063 | -120.646 | TEMPLETON 21132949 | 7 | 15 | 1555.8998 | 766.5719 | 789.328 | 766.5719 | 789.328 | 0.0003974 | 0.00010854 | 1.2277 | 7 | 1986 | 0.2701 | 260 | 0 | 0 | 0.47633 | 1350 | 0
North Valley | 2297 | 16 | 26.1672 | 119 | 63.0005 | 18 | 0.00011325 | 376.1145 | 5.7138 | 71.5234 | 383.4624 | 8.1377 | 10.3374 | 86.3092 | 1.0725 | 0.053846 | 0.00046038 | 0.13445 | 0.41535 | {232A469F-DE89-4EE3-AC4B-F74419E6464C} | 103441102 | JESSUP 1102 | circuit_breaker | 40.4616 | -122.3278 | JESSUP 1102circuit_breaker | 175 | 319 | 22373.067 | 8672.7914 | 13700.2756 | 1622.8923 | 2921.7214 | 0.0082868 | 0.0020384 | 1.6355 | 6.6111 | 845 | 0.96923 | 261 | 0 | 0 | 1.0084 | 1199 | 0
North Valley | 7890 | 222 | 332.1943 | 727 | 506.6447 | 143 | 6.7986e-05 | 887.479 | 18.4349 | 844.8268 | 4861.0419 | 223.395 | 14.8563 | 402.8876 | 1.3808 | 0.054413 | 0.00058984 | 0.30536 | 0.65568 | {6925CBA3-93E0-44A7-B2DC-50805D93ECF4} | 103191101 | BANGOR 1101 | 31502 | 39.3864 | -121.4016 | BANGOR 110131502 | 141 | 86 | 26804.8794 | 19075.5291 | 7729.3503 | 19075.5291 | 7729.3503 | 0.084347 | 0.0097221 | 1.4964 | 5.0839 | 683 | 7.7811 | 262 | 0 | 0 | 11.853 | 419 | 0
Sierra | 7890 | 1 | 1.246 | 22 | 11.6943 | 5 | 8.694e-05 | 329.4537 | 8.5759 | 448.3333 | 2589.2529 | 44.1566 | 0.73496 | 208.8348 | 1.1487 | 0.03194 | 0.00073799 | 0.045455 | 0.10655 | {6925CBA3-93E0-44A7-B2DC-50805D93ECF4} | 103191101 | BANGOR 1101 | 31502 | 39.3864 | -121.4016 | BANGOR 110131502 | 141 | 86 | 26804.8794 | 19075.5291 | 7729.3503 | 19075.5291 | 7729.3503 | 0.0036899 | 0.0004347 | 1.246 | 4.4 | 540 | 0.1597 | 262 | 0 | 0 | 11.853 | 2581 | 0
Sierra | 5121 | 1005 | 1686.875 | 2801 | 2392.506 | 344 | 6.5991e-05 | 1114.2052 | 11.1358 | 209.5738 | 938.1438 | 33.8177 | 17.1854 | 199.4737 | 1.3482 | 0.05324 | 0.00033876 | 0.3588 | 0.70507 | {97806AE4-5D72-4FCC-8179-00CDE6E08736} | 152691109 | HIGGINS 1109 | circuit_breaker | 39.0439 | -121.0906 | HIGGINS 1109circuit_breaker | 410 | 334 | 63000.3389 | 37253.2271 | 25747.1118 | 35901.2045 | 25298.9299 | 0.11653 | 0.022701 | 1.6785 | 8.1424 | 1034 | 18.3144 | 263 | 0 | 0 | 22.308 | 1385 | 0
North Valley | 39 | 1301 | 1705.3279 | 2379 | 2196.9426 | 357 | 0.00012167 | 464.0291 | 10.4312 | 2504.3497 | 59023.2824 | 978.3669 | 8.7293 | 219.2115 | 1.2215 | 0.05306 | 0.00065722 | 0.54687 | 0.77623 | {81F58F11-9F6E-4CC2-A527-0CBBB670DE91} | 103321101 | CEDAR CREEK 1101 | 1664 | 40.7945 | -121.9419 | CEDAR CREEK 11011664 | 346 | 288 | 62342.7797 | 47829.7335 | 14513.0462 | 47829.7335 | 14513.0462 | 0.23463 | 0.043437 | 1.3108 | 6.6639 | 605 | 18.9423 | 264 | 0 | 0 | 29.72 | 1049 | 0
North Coast | 6814 | 133 | 296.5072 | 264 | 351.7987 | 54 | 6.3765e-05 | 860.8526 | 26.5295 | 794.1751 | 3030.2008 | 134.3102 | 17.7841 | 299.6351 | 1.169 | 0.053057 | 0.000586 | 0.50379 | 0.84283 | {181E81CC-8A10-40D6-ABD4-3AD397DDF786} | 42271103 | COTATI 1103 | circuit_breaker | 38.3094 | -122.7318 | COTATI 1103circuit_breaker | 145 | 114 | 35705.8476 | 19561.5616 | 16144.286 | 19561.5616 | 16144.286 | 0.031644 | 0.0034433 | 2.2294 | 4.8889 | 684 | 2.8651 | 265 | 0 | 0 | 12.155 | 1633 | 0
Central Coast | 2246 | 2 | 2.5863 | 23 | 13.3704 | 13 | 2.9218e-05 | 1551.274 | 7.5422 | 179.7994 | 837.253 | 13.9123 | 29.0284 | 344.134 | 1.373 | 0.053052 | 0.00017543 | 0.086957 | 0.19343 | {7E3660A3-92BC-4694-A2D5-248E2793B9A8} | 182611103 | PASO ROBLES 1103 | 55374 | 35.6203 | -120.6962 | PASO ROBLES 110355374 | 174 | 417 | 39635.5094 | 17000.9166 | 22634.5927 | 3793.0347 | 4346.0958 | 0.0022806 | 0.00037984 | 1.2931 | 1.7692 | 1500 | 0.68967 | 266 | 0 | 0 | 2.3569 | 897 | 0
Bay Area | 5581 | 26 | 34.4946 | 55 | 47.8524 | 22 | 1.4003e-05 | 3837.9077 | 7.4282 | 607.1425 | 2356.0859 | 100.179 | 54.1428 | 2095.0008 | 1.7293 | 0.052661 | 5.4922e-05 | 0.47273 | 0.72085 | {A74482B6-4F98-4489-A417-0B9C2832ACBF} | 14652106 | TIDEWATER 2106 | 14072 | 37.9632 | -121.9407 | TIDEWATER 210614072 | 44 | 22 | 8226.7 | 6206.8729 | 2019.8271 | 5897.3117 | 1670.9562 | 0.0012083 | 0.00030806 | 1.3267 | 2.5 | 2193 | 1.1585 | 267 | 0 | 0 | 3.6644 | 2214 | 0
North Coast | 6060 | 3250 | 5521.661 | 3704 | 5731.1924 | 354 | 0.00024093 | 211.5052 | 0.47408 | 147.1612 | 1780.0594 | 2.0431 | 0.1489 | 24.9448 | 1.1532 | 0.052487 | 0.00018315 | 0.87743 | 0.96344 | {83499CD2-C0F0-4DE8-A7FA-CECB9345AEE8} | 192251102 | RIO DELL 1102 | 4230 | 40.4172 | -124.0895 | RIO DELL 11024230 | 68 | 32 | 37599.7998 | 36927.9603 | 671.8395 | 36847.6257 | 671.8395 | 0.064835 | 0.08529 | 1.699 | 10.4633 | 1472 | 18.5803 | 268 | 0 | 0 | 22.896 | 846 | 0
Central Coast | 9000 | 57 | 98.5496 | 216 | 181.6799 | 31 | 4.2241e-05 | 1136.005 | 18.2035 | 418.2328 | 2356.8931 | 64.6126 | 20.044 | 382.3693 | 1.3704 | 0.052132 | 0.00037007 | 0.26389 | 0.54244 | {3ECF96B8-05BC-4EC8-8FE4-68D9EB247E43} | 182611103 | PASO ROBLES 1103 | 59763 | 35.6415 | -120.7259 | PASO ROBLES 110359763 | 36 | 43 | 7322.4927 | 4529.9707 | 2792.522 | 4529.9707 | 2792.522 | 0.011472 | 0.0013095 | 1.7289 | 6.9677 | 983 | 1.6161 | 269 | 0 | 0 | 2.8148 | 1264 | 0
North Valley | 6632 | 438 | 603.5877 | 732 | 740.6182 | 157 | 0.00010246 | 548.1315 | 20.4444 | 1128.1956 | 15274.0429 | 747.9639 | 11.5945 | 313.5054 | 1.2669 | 0.051828 | 0.00097288 | 0.59836 | 0.81498 | {4A950894-EB8D-4B95-B3B2-200DB270C21B} | 103321101 | CEDAR CREEK 1101 | circuit_breaker | 40.791 | -121.9382 | CEDAR CREEK 1101circuit_breaker | 173 | 114 | 31176.2249 | 24905.7197 | 6270.5052 | 24905.7197 | 6270.5052 | 0.15274 | 0.016086 | 1.3781 | 4.6624 | 424 | 8.1369 | 270 | 0 | 0 | 15.4757 | 1445 | 0
Sierra | 5074 | 119 | 189.3344 | 573 | 339.7047 | 82 | 0.00010864 | 472.545 | 172.4297 | 1270.7829 | 13794.2204 | 3261.8625 | 12.9068 | 317.3092 | 1.4331 | 0.051446 | 0.0096633 | 0.20768 | 0.55735 | {0017B0F9-2631-44BD-B55C-C025ECD5CA5A} | 153652109 | SHINGLE SPRINGS 2109 | 2679 | 38.7077 | -120.9708 | SHINGLE SPRINGS 21092679 | 88 | 57 | 18065.034 | 11499.2833 | 6565.7507 | 11499.2833 | 6565.7507 | 0.79239 | 0.0089087 | 1.591 | 6.9878 | 10 | 4.2186 | 271 | 0 | 0 | 7.1453 | 2074 | 0
North Coast | 6617 | 420 | 538.1973 | 660 | 645.1091 | 76 | 0.00016133 | 299.4839 | 13.101 | 786.1441 | 7764.7077 | 235.1971 | 3.5166 | 289.3092 | 1.4775 | 0.050912 | 0.0011177 | 0.63636 | 0.83427 | {24BBFADC-BA16-476A-B9B9-40CAD0BAAB16} | 42681102 | LAYTONVILLE 1102 | 68436 | 39.5523 | -123.4252 | LAYTONVILLE 110268436 | 67 | 34 | 20806.3805 | 14642.1114 | 6164.2691 | 14642.1114 | 6164.2691 | 0.084945 | 0.012261 | 1.2814 | 8.6842 | 355 | 3.8693 | 272 | 0 | 0 | 9.0982 | 1306 | 0
Central Valley | 2402 | 138 | 340.788 | 477 | 447.685 | 147 | 3.7443e-05 | 1420.184 | 49.849 | 930.5918 | 3181.05 | 343.7985 | 25.2588 | 446.3489 | 1.2393 | 0.050708 | 0.00097262 | 0.28931 | 0.76122 | {C39B67B3-F0FA-469A-B248-D7E581E2EE7B} | 162991101 | CORRAL 1101 | 12612 | 38.1783 | -120.9273 | CORRAL 110112612 | 282 | 234 | 42941.2158 | 32323.3334 | 10617.8824 | 31361.0381 | 10315.5023 | 0.14298 | 0.0055042 | 2.4695 | 3.2449 | 425 | 7.4541 | 273 | 0 | 0 | 19.4868 | 2477 | 0
Central Valley | 1817 | 761 | 1151.9438 | 3407 | 2217.223 | 456 | 7.8869e-05 | 656.8459 | 11.6309 | 94.821 | 610.0211 | 21.323 | 13.2237 | 114.2245 | 1.2576 | 0.050377 | 0.00042721 | 0.22336 | 0.51954 | {0FC43676-7F71-4151-8B57-A856F18A7815} | 254421103 | OAKHURST 1103 | circuit_breaker | 37.322 | -119.6345 | OAKHURST 1103circuit_breaker | 760 | 845 | 106522.0728 | 54035.2628 | 52486.81 | 50881.3747 | 46600.722 | 0.19481 | 0.035964 | 1.5137 | 7.4715 | 897 | 22.972 | 274 | 0 | 0 | 31.6162 | 1468 | 0
Sierra | 6754 | 44 | 102.6644 | 274 | 182.8528 | 50 | 0.00012401 | 365.8363 | 46.5167 | 280.4642 | 2233.0428 | 271.2716 | 12.9735 | 174.2144 | 1.09 | 0.050025 | 0.0021936 | 0.16058 | 0.56146 | {E10F57CA-31E3-4642-897F-6FA410857C1A} | 153612104 | CLARKSVILLE 2104 | 19632 | 38.6874 | -121.0088 | CLARKSVILLE 210419632 | 194 | 118 | 22243.9997 | 14659.9971 | 7584.0025 | 8385.252 | 5551.7167 | 0.10968 | 0.0062006 | 2.3333 | 5.48 | 158 | 2.5013 | 275 | 0 | 0 | 5.2104 | 1826 | 0
Central Coast | 3506 | 12 | 24.074 | 48 | 48.2273 | 11 | 5.5063e-05 | 1224.5234 | 7.3377 | 801.5959 | 2390.4379 | 25.0818 | 19.355 | 840.8615 | 1.5358 | 0.049772 | 0.00023708 | 0.25 | 0.49918 | {B38CEC4B-CE5C-427A-839C-FFC2B2AF9000} | 182721101 | SANTA YNEZ 1101 | Y14 | 34.5993 | -120.0979 | SANTA YNEZ 1101Y14 | 203 | 153 | 35864.8287 | 26396.3962 | 9468.4325 | 7302.2086 | 1454.937 | 0.0026078 | 0.00060569 | 2.0062 | 4.3636 | 1287 | 0.54749 | 276 | 0 | 0 | 4.5374 | 1312 | 0
Sierra | 1926 | 235 | 456.2561 | 660 | 578.1573 | 153 | 3.1404e-05 | 1491.9795 | 17.62 | 703.6077 | 3682.0801 | 97.3746 | 23.9917 | 542.072 | 1.5984 | 0.049714 | 0.00030666 | 0.35606 | 0.78916 | {B346A86D-8E49-4897-9613-64FF9116BF2F} | 153132105 | NARROWS 2105 | 34069 | 39.2029 | -121.2766 | NARROWS 210534069 | 196 | 186 | 38937.5966 | 25148.2731 | 13789.3236 | 25148.2731 | 13789.3236 | 0.04692 | 0.0048049 | 1.9415 | 4.3137 | 1106 | 7.6062 | 277 | 0 | 0 | 15.6264 | 1885 | 0
Sierra | 1218 | 143 | 277.2343 | 722 | 511.5374 | 109 | 0.00012121 | 507.0888 | 12.3342 | 121.5237 | 757.9144 | 21.5287 | 10.7698 | 129.3833 | 1.2228 | 0.049497 | 0.00068206 | 0.19806 | 0.54196 | {68D0B16F-430E-46D7-92D4-FB0EB0D57376} | 153651104 | SHINGLE SPRINGS 1104 | 19502 | 38.6581 | -120.9359 | SHINGLE SPRINGS 110419502 | 969 | 950 | 155960.8566 | 92405.563 | 63555.2935 | 68814.3237 | 44768.0012 | 0.074345 | 0.013211 | 1.9387 | 6.6239 | 585 | 5.3952 | 278 | 0 | 0 | 42.7592 | 499 | 0
Bay Area | 7920 | 25 | 78.1941 | 70 | 98.2525 | 29 | 1.9438e-05 | 2414.1827 | 5.2624 | 658.5141 | 3728.9087 | 63.7805 | 30.7175 | 1819.8554 | 1.6042 | 0.048702 | 5.5487e-05 | 0.35714 | 0.79585 | {439ED568-0BDE-4626-B59A-7C48F17E3B78} | 14422111 | CAYETANO 2111 | circuit_breaker | 37.7382 | -121.7708 | CAYETANO 2111circuit_breaker | 127 | 65 | 23961.3578 | 18775.78 | 5185.5777 | 8282.7924 | 2523.3749 | 0.0016091 | 0.00056371 | 3.1278 | 2.4138 | 2186 | 1.4124 | 279 | 0 | 0 | 5.1467 | 1542 | 0
Central Valley | 7153 | 34 | 79.2557 | 203 | 126.6759 | 52 | 4.0274e-05 | 1625.2997 | 32.2906 | 1783.1227 | 9803.7251 | 381.4266 | 24.034 | 550.8745 | 1.4739 | 0.048693 | 0.00042948 | 0.16749 | 0.62566 | {9F95EC4F-532B-46F3-B204-91F26FFADEE3} | 163231101 | NORTH BRANCH 1101 | 11158 | 38.2012 | -120.8274 | NORTH BRANCH 110111158 | 276 | 310 | 72516.0234 | 45851.8623 | 26664.1612 | 16351.0693 | 9112.5896 | 0.022333 | 0.0020943 | 2.331 | 3.9038 | 894 | 2.532 | 280 | 0 | 0 | 10.1601 | 99 | 0
North Valley | 5104 | 0 | 0 | 73 | 18.627 | 21 | 3.6978e-05 | 1252.8842 | 27.7525 | 181.7788 | 671.9732 | 55.5194 | 25.0622 | 333.198 | 1.327 | 0.048375 | 0.00048405 | 0 | 0 | {ABE6F062-1CE8-44B2-8445-67D100174B10} | 103261101 | ANDERSON 1101 | 1752 | 40.4316 | -122.2918 | ANDERSON 11011752 | 57 | 41 | 9784.8006 | 7452.6013 | 2332.1993 | 5082.8869 | 538.9259 | 0.010165 | 0.00077653 |  | 3.4762 | 804 | 1.0159 | 281 | 0 | 0 | 3.1584 | 2443 | 0
North Coast | 5869 | 285 | 360.1674 | 773 | 651.5388 | 82 | 8.6731e-05 | 568.9679 | 10.1948 | 446.1564 | 6253.1678 | 94.3214 | 4.8636 | 99.0364 | 1.2756 | 0.048119 | 0.00043111 | 0.36869 | 0.5528 | {426BF604-696E-47F3-AC03-51DD52DEC8DF} | 42751113 | FITCH MOUNTAIN 1113 | 583202 | 38.5954 | -122.8597 | FITCH MOUNTAIN 1113583202 | 167 | 171 | 34739.7464 | 15440.8422 | 19298.9043 | 7085.4902 | 9626.0246 | 0.035351 | 0.0071119 | 1.2637 | 9.4268 | 888 | 3.9458 | 282 | 0 | 0 | 4.4027 | 2653 | 0
Sierra | 7162 | 105 | 140.5825 | 195 | 180.9806 | 18 | 0.000132 | 389.9762 | 8.7891 | 45.6226 | 169.8432 | 1.6771 | 13.2439 | 105.3185 | 1.1595 | 0.048073 | 0.0005567 | 0.53846 | 0.77678 | {9DF5CB55-1623-4B4B-9F53-43CFDE7622F1} | 152561107 | PENRYN 1107 | 90970 | 38.8253 | -121.1699 | PENRYN 110790970 | 101 | 152 | 14078.0074 | 6824.705 | 7253.3024 | 1720.141 | 1359.0253 | 0.010021 | 0.002376 | 1.3389 | 10.8333 | 730 | 0.86532 | 283 | 0 | 0 | 1.0688 | 2372 | 0
North Valley | 2237 | 1155 | 1718.7441 | 2574 | 2234.479 | 428 | 9.8142e-05 | 703.0814 | 5.0927 | 340.9208 | 1864.7173 | 21.1729 | 14.3661 | 494.2324 | 1.3097 | 0.047811 | 0.00026594 | 0.44872 | 0.76919 | {064EA007-8A62-40F7-BDB2-55C9C2572F4C} | 103351101 | DESCHUTES 1101 | 1580 | 40.5648 | -122.1913 | DESCHUTES 11011580 | 509 | 405 | 122995.8255 | 79522.8496 | 43472.9759 | 74786.9655 | 39390.9316 | 0.11382 | 0.042005 | 1.4881 | 6.014 | 1207 | 20.4631 | 284 | 0 | 0 | 46.4705 | 1792 | 0
Sierra | 3287 | 542 | 889.6012 | 1585 | 1255.9885 | 272 | 4.646e-05 | 897.1675 | 28.4077 | 885.9539 | 5086.2514 | 224.5833 | 20.8821 | 449.6494 | 1.3193 | 0.047665 | 0.00060558 | 0.34196 | 0.70829 | {DAD370F0-D502-456B-9D6C-C04B93F7ABC9} | 152271102 | WISE 1102 | 307494 | 38.9339 | -121.1791 | WISE 1102307494 | 373 | 256 | 76871.5966 | 54215.3663 | 22656.2302 | 49357.8411 | 19613.2181 | 0.16472 | 0.012637 | 1.6413 | 5.8272 | 663 | 12.965 | 285 | 0 | 0 | 30.6695 | 1424 | 0
North Coast | 6839 | 657 | 834.7258 | 1505 | 1323.77 | 138 | 0.00011123 | 411.538 | 6.7232 | 275.6879 | 5151.3118 | 113.4419 | 3.0764 | 62.0415 | 1.2147 | 0.047548 | 0.00044561 | 0.43654 | 0.63057 | {F1192C47-0912-4CBD-BF6E-19925F71459A} | 42751113 | FITCH MOUNTAIN 1113 | 356 | 38.5838 | -122.8803 | FITCH MOUNTAIN 1113356 | 197 | 177 | 44437.6908 | 24401.1439 | 20036.5469 | 15672.6029 | 13870.9457 | 0.061495 | 0.015349 | 1.2705 | 10.9058 | 870 | 6.5616 | 286 | 0 | 0 | 9.7385 | 794 | 0
North Coast | 2529 | 1179 | 1576.4328 | 1441 | 1713.82 | 194 | 0.00012713 | 384.6935 | 10.2783 | 1367.9899 | 15020.9963 | 331.0543 | 2.6956 | 207.7998 | 1.337 | 0.047533 | 0.00073776 | 0.81818 | 0.91984 | {9FACD320-0A6B-4701-A9D9-81FE9755F114} | 42681102 | LAYTONVILLE 1102 | 500 | 39.6658 | -123.4763 | LAYTONVILLE 1102500 | 285 | 211 | 63469.3836 | 47214.3808 | 16255.0028 | 32899.6268 | 12434.1125 | 0.14312 | 0.024664 | 1.3371 | 7.4278 | 542 | 9.2215 | 287 | 0 | 0 | 20.4429 | 336 | 0
Bay Area | 442 | 663 | 1084.8755 | 2193 | 1866.659 | 197 | 4.3363e-05 | 1254.1496 | 1.9203 | 45.719 | 266.1578 | 2.4319 | 16.3721 | 374.2943 | 1.2716 | 0.04686 | 7.6008e-05 | 0.30233 | 0.58119 | {3D0FC142-36D5-4662-84E1-74BFFF12E068} | 12022212 | CLAYTON 2212 | 96224 | 37.9039 | -121.8741 | CLAYTON 221296224 | 254 | 206 | 44100.5024 | 26353.3688 | 17747.1336 | 26353.3688 | 17747.1336 | 0.014974 | 0.0085425 | 1.6363 | 11.132 | 2012 | 9.2315 | 288 | 0 | 0 | 16.3752 | 1930 | 0
North Valley | 2512 | 88 | 122.9133 | 305 | 183.7954 | 93 | 4.6999e-05 | 983.6967 | 23.2965 | 799.0678 | 5144.5219 | 258.6595 | 17.7302 | 655.2408 | 1.386 | 0.046411 | 0.00033618 | 0.28852 | 0.66875 | {E7F7F25C-AE9C-459D-9EB5-32BCE8602EF6} | 102931103 | COTTONWOOD 1103 | 35470 | 40.3732 | -122.2826 | COTTONWOOD 110335470 | 308 | 113 | 43306.9123 | 40111.3744 | 3195.5379 | 31917.2696 | 2830.0893 | 0.031265 | 0.0043709 | 1.3967 | 3.2796 | 1040 | 4.3162 | 289 | 0 | 0 | 19.8325 | 126 | 0
Sierra | 3065 | 147 | 258.8765 | 515 | 398.4624 | 56 | 0.00010021 | 649.6911 | 11.0392 | 54.1715 | 162.9662 | 3.8287 | 13.1657 | 92.4856 | 1.0982 | 0.046308 | 0.00058332 | 0.28544 | 0.64969 | {223CF293-20C5-4942-B371-E6A6292ECAF4} | 152571101 | HORSESHOE 1101 | 50140 | 38.7673 | -121.1571 | HORSESHOE 110150140 | 136 | 94 | 15618.043 | 10038.7802 | 5579.2628 | 6170.3672 | 2653.7413 | 0.032666 | 0.0056118 | 1.7611 | 9.1964 | 690 | 2.5933 | 290 | 0 | 0 | 3.8341 | 325 | 0
Sierra | 9682 | 14 | 24.9871 | 17 | 26.3543 | 6 | 1.1704e-05 | 3596.7894 | 144.698 | 1128.3355 | 6126.1267 | 1181.5384 | 41.2098 | 508.0791 | 1.8311 | 0.046172 | 0.001367 | 0.82353 | 0.94812 | {C266F189-74C8-46FA-BDF3-9DE2CEE825D5} | 63642106 | PEABODY 2106 | 5500 | 38.3251 | -121.9708 | PEABODY 21065500 | 22 | 9 | 2800.7836 | 2454.3356 | 346.448 | 589.7469 | 35.0045 | 0.0082021 | 7.0223e-05 | 1.7848 | 2.8333 | 279 | 0.27703 | 291 | 0 | 0 | 0.36645 | 1830 | 0
North Valley | 5334 | 513 | 975.3299 | 1303 | 1252.5269 | 197 | 8.1999e-05 | 579.2368 | 60.4852 | 578.2223 | 5913.9463 | 1217.7118 | 18.2198 | 128.9093 | 1.1905 | 0.046073 | 0.0023516 | 0.39371 | 0.77869 | {326CEA2F-D61B-41C8-B48B-A09EBFE7F47D} | 103441101 | JESSUP 1101 | 1496 | 40.478 | -122.3995 | JESSUP 11011496 | 348 | 346 | 44978.6984 | 26108.2459 | 18870.4525 | 23100.1991 | 14861.4468 | 0.46327 | 0.016154 | 1.9012 | 6.6142 | 143 | 9.0763 | 292 | 0 | 0 | 14.3538 | 296 | 0
North Valley | 2729 | 709 | 1628.5971 | 2024 | 2039.4806 | 240 | 3.8974e-05 | 1300.9551 | 43.6809 | 660.8611 | 3511.0681 | 530.5481 | 23.9722 | 308.0956 | 1.3718 | 0.04604 | 0.00072202 | 0.3503 | 0.79854 | {790FA841-FFAA-4636-AEC1-FF360B754DBB} | 102911109 | WYANDOTTE 1109 | 13052 | 39.459 | -121.5107 | WYANDOTTE 110913052 | 293 | 284 | 54400.5255 | 31567.9238 | 22832.6017 | 31409.8673 | 22462.3373 | 0.17329 | 0.0093537 | 2.297 | 8.4333 | 556 | 11.0495 | 293 | 0 | 0 | 19.5172 | 2437 | 0
North Valley | 3269 | 682 | 1408.4418 | 1719 | 1771.3828 | 244 | 8.9079e-05 | 671.2558 | 118.5809 | 1588.1134 | 17804.6531 | 4589.7687 | 20.9564 | 157.4016 | 1.1318 | 0.045923 | 0.0050655 | 0.39674 | 0.79511 | {B75A956B-8FBE-4735-92D0-A851A9ED4A9E} | 103441102 | JESSUP 1102 | 76068 | 40.4472 | -122.4069 | JESSUP 110276068 | 368 | 422 | 56763.5161 | 30912.2445 | 25851.2716 | 26885.9006 | 21427.8567 | 1.236 | 0.021735 | 2.0652 | 7.0451 | 35 | 11.2051 | 294 | 0 | 0 | 16.7061 | 725 | 0
Sierra | 3701 | 182 | 293.2167 | 542 | 455.1015 | 72 | 7.7081e-05 | 836.0961 | 12.3838 | 86.2268 | 381.6012 | 7.6278 | 16.0738 | 117.2364 | 1.3515 | 0.045735 | 0.00058307 | 0.33579 | 0.64429 | {4F07E24C-1232-45AE-9D5A-3EBBDB1BA1EF} | 152691107 | HIGGINS 1107 | 7559 | 39.0202 | -121.0624 | HIGGINS 11077559 | 79 | 83 | 13740.5877 | 7116.1029 | 6624.4848 | 7109.6813 | 6624.4848 | 0.041981 | 0.0055499 | 1.6111 | 7.5278 | 692 | 3.2929 | 295 | 0 | 0 | 4.4177 | 2373 | 0
North Valley | 3393 | 430 | 807.8791 | 1873 | 1228.0034 | 376 | 5.9347e-05 | 804.4207 | 79.8142 | 3151.6147 | 29930.1088 | 3921.653 | 14.0369 | 710.6856 | 1.5785 | 0.045655 | 0.0023125 | 0.22958 | 0.65788 | {FD19D23C-6A96-40C9-9542-F7EF9A6AB34E} | 102931101 | COTTONWOOD 1101 | 1610 | 40.3261 | -122.4253 | COTTONWOOD 11011610 | 295 | 222 | 78207.0411 | 61705.5201 | 16501.521 | 61705.5201 | 16501.521 | 0.86952 | 0.022315 | 1.8788 | 4.9814 | 149 | 17.1663 | 296 | 0 | 0 | 38.342 | 1277 | 0
Central Valley | 7114 | 29 | 81.6013 | 325 | 172.0101 | 95 | 3.2242e-05 | 1454.0731 | 53.1809 | 2376.4798 | 13469.9788 | 1453.8359 | 24.7286 | 627.0439 | 1.4687 | 0.045612 | 0.00090304 | 0.089231 | 0.4744 | {C54A0C3F-F840-49B9-80B1-CFAA5E138643} | 162991102 | CORRAL 1102 | 14026 | 38.1167 | -120.8907 | CORRAL 110214026 | 124 | 102 | 21362.6911 | 16308.5206 | 5054.1706 | 16308.5206 | 5054.1706 | 0.085789 | 0.003063 | 2.8138 | 3.4211 | 442 | 4.3331 | 297 | 0 | 0 | 10.1336 | 2503 | 0
North Valley | 9283 | 8 | 19.4608 | 92 | 44.9066 | 19 | 4.1527e-05 | 1078.2009 | 22.1222 | 152.9542 | 702.4587 | 24.4682 | 25.1564 | 346.9813 | 1.6036 | 0.045542 | 0.00029181 | 0.086957 | 0.43336 | {81BB6A5C-2DB9-49AA-A7A4-75F68838201B} | 102911109 | WYANDOTTE 1109 | 32586 | 39.4631 | -121.5149 | WYANDOTTE 110932586 | 22 | 6 | 2721.7238 | 2438.1505 | 283.5734 | 2312.4178 | 283.5734 | 0.0055444 | 0.00078902 | 2.4326 | 4.8421 | 1149 | 0.86529 | 298 | 0 | 0 | 1.4369 | 341 | 0
North Valley | 8769 | 0 | 0 | 88 | 18.9937 | 22 | 2.3178e-05 | 2013.6027 | 0.18688 | 67.2039 | 206.8862 | 0.075288 | 18.7137 | 2833.9262 | 1.9074 | 0.045486 | 1.8101e-05 | 0 | 0 | {9C401B14-4A54-4DA8-B9DB-3EDB68F74D1D} | 103331101 | CORNING 1101 | 85162 | 39.9385 | -122.4044 | CORNING 110185162 | 45 | 18 | 9561.9318 | 9259.5842 | 302.3476 | 9259.5842 | 302.3476 | 0.00039822 | 0.00050992 |  | 4 | 2647 | 1.0007 | 299 | 0 | 0 | 5.7536 | 761 | 0
Central Coast | 989 | 188 | 417.2517 | 689 | 609.5516 | 163 | 2.691e-05 | 1770.1332 | 26.2497 | 594.1106 | 3171.9218 | 101.1459 | 33.3223 | 508.0744 | 1.2903 | 0.045463 | 0.00034814 | 0.27286 | 0.68452 | {7937BCC6-E91C-41D5-AE9E-FB212F98DDB6} | 183052113 | TEMPLETON 2113 | A70 | 35.5024 | -120.649 | TEMPLETON 2113A70 | 851 | 710 | 153188.0406 | 107119.9327 | 46068.1078 | 39039.5646 | 20971.0588 | 0.056748 | 0.0043863 | 2.2194 | 4.227 | 1016 | 7.4104 | 300 | 0 | 0 | 24.2581 | 1451 | 0
Central Valley | 8231 | 10 | 19.4498 | 80 | 45.575 | 22 | 4.3392e-05 | 819.831 | 59.4493 | 492.3072 | 4888.9431 | 841.6143 | 24.048 | 537.3171 | 1.7078 | 0.045442 | 0.0014485 | 0.125 | 0.42676 | {9126AC99-906D-4CEE-8034-3EECC4C90F16} | 254432104 | COARSEGOLD 2104 | circuit_breaker | 37.2275 | -119.6902 | COARSEGOLD 2104circuit_breaker | 49 | 28 | 5467.1255 | 3906.143 | 1560.9825 | 3906.143 | 1560.9825 | 0.031868 | 0.00095462 | 1.945 | 3.6364 | 260 | 0.99973 | 301 | 0 | 0 | 2.4272 | 355 | 0
Central Coast | 3071 | 24 | 64.9981 | 82 | 93.0955 | 16 | 2.663e-05 | 1460.4681 | 10.4076 | 98.175 | 334.886 | 6.1545 | 23.809 | 159.9293 | 1.2266 | 0.045236 | 0.00014958 | 0.29268 | 0.69819 | {2DBAAA9C-8985-4692-9A1B-CC370D239D9B} | 83242105 | MORGAN HILL 2105 | 42348 | 37.1254 | -121.6615 | MORGAN HILL 210542348 | 145 | 292 | 21249.4569 | 6767.0715 | 14482.3855 | 2297.9263 | 2586.4713 | 0.0023933 | 0.00042609 | 2.7083 | 5.125 | 1593 | 0.72378 | 302 | 0 | 0 | 1.4279 | 1942 | 0
Bay Area | 9493 | 107 | 186.0668 | 139 | 201.4756 | 36 | 0.00011795 | 391.7086 | 1.9693 | 197.1325 | 2479.5134 | 21.6456 | 1.076 | 82.7056 | 1.229 | 0.046397 | 0.00017134 | 0.76978 | 0.92352 | {E7C5D89B-64E1-4E8D-A11F-B21BB10A3931} | 43141101 | MIDDLETOWN 1101 | 612 | 38.6742 | -122.5875 | MIDDLETOWN 1101612 | 31 | 29 | 19701.1136 | 6226.4809 | 13474.6328 | 6226.4809 | 13474.6328 | 0.0061681 | 0.0042461 | 1.7389 | 3.8611 | 1519 | 1.6703 | 303 | 0 | 0 | 3.869 | 751 | 0
North Coast | 9493 | 0 | 0 | 1 | 0.35094 | 1 | 0.00014301 | 0.14273 | 1.27 | 113.5378 | 1014.3189 | 4.8416 | 0.0088496 | 29.0538 | 1.0022 | 2.0413e-05 | 0.00018163 | 0 | 0 | {E7C5D89B-64E1-4E8D-A11F-B21BB10A3931} | 43141101 | MIDDLETOWN 1101 | 612 | 38.6742 | -122.5875 | MIDDLETOWN 1101612 | 31 | 29 | 19701.1136 | 6226.4809 | 13474.6328 | 6226.4809 | 13474.6328 | 0.00018163 | 0.00014301 |  | 1 | 1482 | 2.0413e-05 | 303 | 0 | 0 | 3.869 | 1703 | 0
North Coast | 2142 | 306 | 389.3103 | 642 | 580.1434 | 47 | 0.00011006 | 386.1308 | 4.3007 | 215.8704 | 5207.7022 | 104.9853 | 1.2641 | 32.094 | 1.1469 | 0.04513 | 0.00028816 | 0.47664 | 0.67106 | {0D0AF9DD-E748-4197-8438-68854D1A85E5} | 42891102 | GEYSERVILLE 1102 | 89714 | 38.7078 | -122.9013 | GEYSERVILLE 110289714 | 180 | 137 | 28976.2143 | 20357.282 | 8618.9323 | 4342.1142 | 2058.7258 | 0.013543 | 0.0051729 | 1.2723 | 13.6596 | 1153 | 2.1211 | 304 | 0 | 0 | 2.6981 | 969 | 0
North Valley | 8360 | 19 | 34.5591 | 95 | 73.7023 | 24 | 9.5909e-05 | 474.8161 | 38.1027 | 1490.6081 | 28435.8593 | 3771.0154 | 3.089 | 573.5862 | 1.8215 | 0.044737 | 0.003365 | 0.2 | 0.4689 | {89760509-9943-408B-8BC5-66753273219C} | 103451101 | KESWICK 1101 | 1586 | 40.6253 | -122.4632 | KESWICK 11011586 | 53 | 37 | 13345.0843 | 11919.3257 | 1425.7586 | 11919.3257 | 1425.7586 | 0.08076 | 0.0023018 | 1.8189 | 3.9583 | 83 | 1.0737 | 305 | 0 | 0 | 7.4063 | 903 | 0
Bay Area | 4774 | 0 | 0 | 5 | 1.8925 | 2 | 6.5894e-05 | 669.7815 | 0.31366 | 52.2152 | 207.4655 | 0.066186 | 13.7069 | 397.537 | 1.5177 | 0.044408 | 4.7144e-05 | 0 | 0 | {07BF8128-F528-4070-AA6F-0E3ACF3A793A} | 43051101 | MONTICELLO 1101 | 720 | 38.4556 | -122.2107 | MONTICELLO 1101720 | 88 | 71 | 30985.2299 | 13187.1947 | 17798.0352 | 11082.9735 | 16529.4297 | 9.4289e-05 | 0.00013179 |  | 2.5 | 2263 | 0.088816 | 306 | 0 | 0 | 6.8866 | 1934 | 0
North Valley | 5927 | 258 | 482.4622 | 885 | 713.7709 | 111 | 4.5304e-05 | 1101.4398 | 32.8117 | 472.1392 | 2461.488 | 144.286 | 21.2661 | 268.049 | 1.356 | 0.04412 | 0.00060101 | 0.29153 | 0.67593 | {B3E100DA-AA63-42D1-94E1-A7F9E0DF29D9} | 102911107 | WYANDOTTE 1107 | 37472 | 39.4824 | -121.5036 | WYANDOTTE 110737472 | 231 | 208 | 37673.5477 | 24045.3707 | 13628.177 | 13224.7658 | 6003.8792 | 0.066712 | 0.0050287 | 1.87 | 7.973 | 670 | 4.8973 | 307 | 0 | 0 | 8.2175 | 1066 | 0
Sierra | 1166 | 760 | 1302.68 | 2605 | 2082.5732 | 277 | 7.052e-05 | 637.0892 | 17.496 | 189.6518 | 996.4261 | 53.4164 | 15.4747 | 147.9166 | 1.1183 | 0.043864 | 0.00056849 | 0.29175 | 0.62551 | {762D243C-6AD0-4B84-8BCE-EACF0C197C40} | 152561105 | PENRYN 1105 | 1342 | 38.8767 | -121.1347 | PENRYN 11051342 | 703 | 654 | 104551.8899 | 62210.7771 | 42341.1128 | 32719.8008 | 14903.879 | 0.15747 | 0.019534 | 1.7141 | 9.4043 | 713 | 12.1504 | 308 | 0 | 0 | 20.3311 | 738 | 0
Central Valley | 7909 | 49 | 69.8481 | 276 | 149.2332 | 52 | 4.8437e-05 | 784.0938 | 38.2797 | 929.8031 | 5350.4657 | 184.9421 | 8.9543 | 311.2799 | 1.5962 | 0.043849 | 0.0010562 | 0.17754 | 0.46805 | {7B5B2CF8-2901-483C-B55E-83E22B23519F} | 163781705 | PEORIA 1705 | circuit_breaker | 37.9037 | -120.4973 | PEORIA 1705circuit_breaker | 49 | 25 | 13356.6736 | 11472.2383 | 1884.4353 | 11339.1152 | 1884.4353 | 0.05492 | 0.0025187 | 1.4255 | 5.3077 | 384 | 2.2801 | 309 | 0 | 0 | 7.0458 | 2192 | 0
Sierra | 821 | 1264 | 2106.8885 | 4207 | 3197.1338 | 618 | 0.0001133 | 455.6485 | 22.2199 | 148.1816 | 1080.5448 | 69.5811 | 11.7811 | 113.1686 | 1.2029 | 0.043798 | 0.0011637 | 0.30045 | 0.65899 | {01A8C6BD-323D-44E5-A686-1246351A46F2} | 152261107 | DIAMOND SPRINGS 1107 | circuit_breaker | 38.693 | -120.8257 | DIAMOND SPRINGS 1107circuit_breaker | 1083 | 914 | 143684.4336 | 90295.6562 | 53388.7775 | 81888.8347 | 45058.7965 | 0.7192 | 0.07002 | 1.6668 | 6.8074 | 337 | 27.067 | 310 | 0 | 0 | 50.8833 | 118 | 0
Central Coast | 8727 | 0 | 0 | 8 | 1.7073 | 6 | 5.0064e-05 | 809.9211 | 0 | 6.8876 | 28.7721 | 0 | 2.9672 | 275.939 | 1.3274 | 0.043664 | 1.8074e-05 | 0 | 0 | {19CBB8DD-B0DD-40C9-99D6-9DC6A38717ED} | 182661106 | SAN MIGUEL 1106 | N34 | 35.8138 | -120.755 | SAN MIGUEL 1106N34 | 91 | 118 | 25588.8955 | 22008.9702 | 3579.9252 | 3289.5998 | 43.9553 | 0.00010845 | 0.00030038 |  | 1.3333 | 2650 | 0.26198 | 311 | 0 | 0 | 2.0441 | 2423 | 0
Sierra | 1489 | 143 | 243.8494 | 551 | 384.5564 | 80 | 0.000108 | 401.2502 | 7.403 | 51.1195 | 360.9911 | 7.9606 | 7.1868 | 143.6321 | 1.1728 | 0.043592 | 0.00035206 | 0.25953 | 0.63411 | {C35B7B84-D418-41DB-BA63-E9DFFDA08709} | 152261105 | DIAMOND SPRINGS 1105 | 18935 | 38.6729 | -120.8939 | DIAMOND SPRINGS 110518935 | 100 | 97 | 18602.1379 | 10773.8274 | 7828.3104 | 10773.8274 | 7828.3104 | 0.028165 | 0.0086396 | 1.7052 | 6.8875 | 1010 | 3.4873 | 312 | 0 | 0 | 6.6945 | 774 | 0
North Coast | 3665 | 3046 | 4037.0361 | 4029 | 4510.0366 | 409 | 0.00011988 | 431.9083 | 59.4937 | 3551.639 | 62639.0034 | 6090.6447 | 6.4952 | 134.4255 | 1.299 | 0.043277 | 0.0031794 | 0.75602 | 0.89512 | {62A0A3F9-A1CB-414A-866A-2AE63E42851C} | 42661104 | WILLITS 1104 | 934 | 39.3818 | -123.3425 | WILLITS 1104934 | 377 | 356 | 77906.0752 | 49456.388 | 28449.6871 | 49456.388 | 28449.6871 | 1.3004 | 0.049029 | 1.3254 | 9.8509 | 94 | 17.7005 | 313 | 0 | 0 | 30.7308 | 106 | 0
Central Valley | 3912 | 227 | 414.5259 | 949 | 634.1356 | 274 | 3.8617e-05 | 1435.9214 | 25.788 | 944.5572 | 4159.5988 | 180.8922 | 22.8435 | 778.017 | 1.5238 | 0.043159 | 0.00046032 | 0.2392 | 0.65369 | {5372D86A-A2C3-481F-93D2-142C67A2BDD1} | 163541101 | OLETA 1101 | 1208 | 38.4373 | -120.8358 | OLETA 11011208 | 416 | 415 | 101267.2382 | 61275.2844 | 39991.9538 | 52737.327 | 37574.5641 | 0.12613 | 0.010581 | 1.8261 | 3.4635 | 846 | 11.8256 | 314 | 0 | 0 | 32.7694 | 819 | 0
North Valley | 422 | 209 | 394.3193 | 1728 | 873.1647 | 281 | 5.4444e-05 | 818.3612 | 22.8368 | 1229.2941 | 9801.3926 | 577.0588 | 15.1588 | 547.7733 | 1.4177 | 0.043122 | 0.00052552 | 0.12095 | 0.4516 | {0E682A09-C0D8-404A-8B27-2B967048024C} | 102931102 | COTTONWOOD 1102 | 1578 | 40.3885 | -122.4079 | COTTONWOOD 11021578 | 347 | 272 | 83467.5925 | 56401.1925 | 27066.4 | 45006.6873 | 24834.5106 | 0.14767 | 0.015299 | 1.8867 | 6.1495 | 764 | 12.1173 | 315 | 0 | 0 | 27.9659 | 896 | 0
North Valley | 7588 | 8 | 13.6398 | 51 | 37.4896 | 18 | 1.4509e-05 | 2911.4696 | 2.2255 | 840.2386 | 3848.167 | 14.1752 | 19.6257 | 1861.7748 | 2.0429 | 0.04305 | 2.0089e-05 | 0.15686 | 0.36383 | {D3F18D5E-2734-47E6-AA3E-0F1256C05891} | 103551101 | RISING RIVER 1101 | 1532 | 40.8229 | -121.5021 | RISING RIVER 11011532 | 29 | 30 | 9763.6072 | 7838.859 | 1924.7483 | 4719.7178 | 1581.3351 | 0.0003616 | 0.00026115 | 1.705 | 2.8333 | 2605 | 0.77491 | 316 | 0 | 0 | 2.9327 | 1173 | 0
North Valley | 4578 | 143 | 281.8202 | 812 | 491.9364 | 98 | 7.0002e-05 | 716.3153 | 13.3388 | 126.0544 | 678.2896 | 48.4803 | 17.1161 | 163.5393 | 1.3412 | 0.042859 | 0.00059034 | 0.17611 | 0.57288 | {1C2C814F-78D0-401D-8386-69906E2875F3} | 103401102 | GIRVAN 1102 | 80726 | 40.522 | -122.3336 | GIRVAN 110280726 | 372 | 437 | 50671.9174 | 29678.7126 | 20993.2048 | 10897.7797 | 6310.4303 | 0.057853 | 0.0068602 | 1.9708 | 8.2857 | 681 | 4.2002 | 317 | 0 | 0 | 6.7716 | 1494 | 0
North Coast | 5406 | 64 | 102.1653 | 188 | 131.6635 | 46 | 4.4862e-05 | 833.0519 | 7.9593 | 90.6788 | 517.5294 | 10.7311 | 17.9824 | 579.537 | 1.5971 | 0.042741 | 0.00020984 | 0.34043 | 0.77596 | {C2104F3A-E916-4650-9AAE-B23FDDC60033} | 43361102 | HIGHLANDS 1102 | 80660 | 38.9546 | -122.608 | HIGHLANDS 110280660 | 98 | 82 | 20717.5416 | 12052.2865 | 8665.2551 | 9091.4024 | 6606.6395 | 0.0096527 | 0.0020637 | 1.5963 | 4.087 | 1380 | 1.9661 | 318 | 0 | 0 | 5.6491 | 607 | 0
Sierra | 7124 | 6 | 7.5957 | 11 | 9.546 | 5 | 2.9624e-05 | 1487.6175 | 72.5588 | 4855.4667 | 26432.9632 | 2739.8566 | 11.715 | 1482.8443 | 1.8257 | 0.042507 | 0.0020567 | 0.54545 | 0.7957 | {25987CE1-F207-449C-AFDA-F7A284EF81E2} | 63681105 | PUTAH CREEK 1105 | 8812 | 38.5606 | -121.9713 | PUTAH CREEK 11058812 | 478 | 376 | 126309.6987 | 103854.6628 | 22455.0359 | 1876.8402 | 1363.7034 | 0.010283 | 0.00014812 | 1.266 | 2.2 | 171 | 0.21253 | 319 | 0 | 0 | 1.1662 | 520 | 0
Central Valley | 129 | 533 | 836.8074 | 2064 | 1429.0126 | 389 | 5.6004e-05 | 808.6466 | 7.6122 | 743.3766 | 6393.1955 | 140.2714 | 14.6013 | 399.7011 | 1.577 | 0.042412 | 0.00020573 | 0.25824 | 0.58558 | {65F04F88-77E2-416B-8718-E84D34A90738} | 252521103 | SAN JOAQUIN #2 1103 | circuit_breaker | 37.2039 | -119.4966 | SAN JOAQUIN #2 1103circuit_breaker | 761 | 839 | 162156.2756 | 109277.3995 | 52878.8762 | 109277.3995 | 52878.8762 | 0.08003 | 0.021785 | 1.57 | 5.3059 | 1395 | 16.4981 | 320 | 0 | 0 | 67.9018 | 729 | 0
Central Valley | 4241 | 99 | 230.6831 | 486 | 349.5964 | 149 | 5.8715e-05 | 1023.9531 | 50.157 | 656.9095 | 3634.9213 | 488.4318 | 18.3104 | 242.9303 | 1.3677 | 0.042918 | 0.001096 | 0.2037 | 0.65986 | {D6BA7AB0-BD1E-4258-B5D5-B64D6E99400B} | 162991102 | CORRAL 1102 | 36666 | 38.1605 | -120.8481 | CORRAL 110236666 | 281 | 463 | 58313.2129 | 29026.438 | 29286.7749 | 26276.8597 | 26433.4525 | 0.16331 | 0.0087486 | 2.3301 | 3.2617 | 363 | 6.3947 | 321 | 0 | 0 | 16.3277 | 1183 | 0
Central Coast | 4241 | 1 | 1.2277 | 9 | 7.2552 | 2 | 5.6504e-05 | 0.066431 |  |  |  |  | 0.23119 | 0.22909 | 1 | 3.7537e-06 | 5.6504e-05 | 0.11111 | 0.16922 | {D6BA7AB0-BD1E-4258-B5D5-B64D6E99400B} | 162991102 | CORRAL 1102 | 36666 | 38.1605 | -120.8481 | CORRAL 110236666 | 281 | 463 | 58313.2129 | 29026.438 | 29286.7749 | 26276.8597 | 26433.4525 | 0.00011301 | 0.00011301 | 1.2277 | 4.5 | 2178 | 7.5073e-06 | 321 | 0 | 0 | 16.3277 | 2027 | 0
North Coast | 6566 | 508 | 717.2952 | 716 | 824.0617 | 77 | 0.00030486 | 137.8388 | 7.2894 | 117.4174 | 790.9797 | 14.9051 | 3.8282 | 53.217 | 1.1424 | 0.042327 | 0.0012227 | 0.7095 | 0.87044 | {E1AC8377-8E8C-4414-AED8-68291E68F4CE} | 192221101 | GARBERVILLE 1101 | circuit_breaker | 40.103 | -123.7929 | GARBERVILLE 1101circuit_breaker | 139 | 127 | 21021.2303 | 14145.522 | 6875.7083 | 9321.3726 | 3051.365 | 0.094148 | 0.023474 | 1.412 | 9.2987 | 313 | 3.2592 | 322 | 0 | 0 | 5.792 | 772 | 0
North Valley | 2867 | 43 | 68.9908 | 219 | 136.7286 | 26 | 0.00010915 | 264.6867 | 12.4005 | 43.2124 | 196.2948 | 8.4513 | 12.2782 | 53.5281 | 1.1424 | 0.042274 | 0.00099325 | 0.19635 | 0.50458 | {05238085-585C-432C-A137-934EA80FC572} | 103441103 | JESSUP 1103 | 38864 | 40.4831 | -122.3225 | JESSUP 110338864 | 162 | 207 | 21867.5658 | 12088.203 | 9779.3628 | 2871.393 | 1938.5203 | 0.025824 | 0.0028378 | 1.6044 | 8.4231 | 414 | 1.0991 | 323 | 0 | 0 | 1.7842 | 1241 | 0
North Valley | 4913 | 63 | 76.835 | 102 | 90.635 | 22 | 3.7368e-05 | 1225.1139 | 1.8388 | 531.0449 | 2332.7102 | 5.1381 | 16.3002 | 1097.2014 | 1.6881 | 0.042242 | 3.9962e-05 | 0.61765 | 0.84774 | {EFAF3860-6049-4F8E-AF4B-3D1B6758C8FE} | 103541104 | RED BLUFF 1104 | 1566 | 40.2653 | -122.2257 | RED BLUFF 11041566 | 107 | 59 | 31831.1322 | 24175.3198 | 7655.8123 | 15161.638 | 3463.7088 | 0.00087915 | 0.00082209 | 1.2196 | 4.6364 | 2342 | 0.92933 | 324 | 0 | 0 | 9.421 | 1123 | 0
North Coast | 5512 | 319 | 377.454 | 460 | 445.2276 | 74 | 0.00014159 | 272.1881 | 11.9179 | 837.2046 | 13883.1889 | 520.5689 | 2.6448 | 221.2945 | 1.328 | 0.042161 | 0.00094653 | 0.69348 | 0.84778 | {9D061223-5B52-4134-9A27-9EB1E4A74BC8} | 192321121 | FORT SEWARD 1121 | circuit_breaker | 40.2134 | -123.5965 | FORT SEWARD 1121circuit_breaker | 59 | 25 | 12132.2393 | 11681.8525 | 450.3868 | 11649.7657 | 450.3868 | 0.070044 | 0.010478 | 1.1832 | 6.2162 | 436 | 3.1199 | 325 | 0 | 0 | 7.2388 | 2103 | 0
Sierra | 2581 | 247 | 436.6686 | 795 | 647.3773 | 140 | 5.9456e-05 | 780.21 | 38.9301 | 201.907 | 1088.8504 | 71.3022 | 17.4129 | 248.5869 | 1.1617 | 0.042039 | 0.00073645 | 0.31069 | 0.67452 | {6C821003-D04C-4AF6-8BAB-34ADD719F265} | 153701101 | LINCOLN 1101 | 2310 | 38.889 | -121.276 | LINCOLN 11012310 | 296 | 188 | 39404.2027 | 28409.3075 | 10994.8952 | 17598.5614 | 7119.8754 | 0.1031 | 0.0083239 | 1.7679 | 5.6786 | 543 | 5.8855 | 326 | 0 | 0 | 10.9352 | 1397 | 0
North Valley | 3722 | 166 | 213.613 | 370 | 273.9116 | 86 | 6.4234e-05 | 650.6654 | 2.8723 | 315.4119 | 1207.1906 | 6.2032 | 10.3248 | 1039.0532 | 1.561 | 0.041845 | 0.00011066 | 0.44865 | 0.77986 | {D4F4CD74-DB1C-49F4-9D89-1A434E6A2652} | 103461102 | PANORAMA 1102 | 1526 | 40.4175 | -122.2109 | PANORAMA 11021526 | 154 | 96 | 35934.5073 | 28300.327 | 7634.1803 | 17981.687 | 2715.8391 | 0.009517 | 0.0055241 | 1.2868 | 4.3023 | 1796 | 3.5987 | 327 | 0 | 0 | 11.1733 | 1006 | 0
Bay Area | 7240 | 98 | 146.084 | 283 | 237.021 | 42 | 3.0144e-05 | 1662.0097 | 5.5785 | 97.4034 | 611.4205 | 9.0847 | 19.0346 | 427.3561 | 1.4694 | 0.041669 | 0.00010575 | 0.34629 | 0.61633 | {D423A3F7-280A-4662-8630-3491AC2B7D20} | 12022212 | CLAYTON 2212 | 7758 | 37.8794 | -121.868 | CLAYTON 22127758 | 27 | 28 | 10109.6541 | 5210.7596 | 4898.8945 | 5210.7596 | 4898.8945 | 0.0044413 | 0.0012661 | 1.4907 | 6.7381 | 1828 | 1.7501 | 328 | 0 | 0 | 3.2378 | 2226 | 0
Central Valley | 380 | 274 | 764.7668 | 1002 | 991.9045 | 215 | 4.9221e-05 | 863.1185 | 31.1765 | 650.8218 | 2517.7585 | 170.7406 | 19.657 | 362.9446 | 1.2651 | 0.041626 | 0.00069083 | 0.27345 | 0.77101 | {34B49956-28BF-4C3F-BBD0-326423DCC642} | 162991101 | CORRAL 1101 | 12606 | 38.1805 | -120.9263 | CORRAL 110112606 | 276 | 226 | 49842.2655 | 36019.0707 | 13823.1948 | 36019.0707 | 13823.1948 | 0.14853 | 0.010583 | 2.7911 | 4.6605 | 574 | 8.9495 | 329 | 0 | 0 | 22.3812 | 1852 | 0
Central Valley | 8902 | 2 | 4.3169 | 6 | 5.9468 | 4 | 2.0839e-05 | 1996.08 | 1.9304 | 574.2226 | 4997.3657 | 19.2935 | 2.8451 | 2816.5243 | 2.1278 | 0.041486 | 3.0572e-05 | 0.33333 | 0.72593 | {AA81189C-0FB0-446B-B000-4E0A59F32937} | 253642104 | POSO MOUNTAIN 2104 | circuit_breaker | 35.5591 | -118.9575 | POSO MOUNTAIN 2104circuit_breaker | 45 | 5 | 12272.8813 | 11934.6881 | 338.1932 | 5614.2654 | 289.9345 | 0.00012229 | 8.3356e-05 | 2.1585 | 1.5 | 2464 | 0.16595 | 330 | 0 | 0 | 3.4885 | 225 | 0
North Valley | 4012 | 469 | 1009.9195 | 1306 | 1271.5367 | 281 | 5.0291e-05 | 1047.5051 | 71.5656 | 1278.0494 | 10976.6852 | 1536.7827 | 18.7515 | 475.4575 | 1.3264 | 0.041144 | 0.0014511 | 0.35911 | 0.79425 | {7C8CD245-F5C5-41C8-8C39-1CC5C953323C} | 103441101 | JESSUP 1101 | 41356 | 40.4772 | -122.4548 | JESSUP 110141356 | 440 | 440 | 81196.4014 | 52454.1999 | 28742.2014 | 52454.1999 | 28742.2014 | 0.40777 | 0.014132 | 2.1533 | 4.6477 | 259 | 11.5613 | 331 | 0 | 0 | 32.5935 | 950 | 0
Central Valley | 3133 | 277 | 620.0697 | 818 | 783.9222 | 241 | 1.7103e-05 | 2237.7689 | 108.4249 | 10074.1572 | 79096.8576 | 12033.41 | 31.5725 | 1552.4027 | 1.7999 | 0.041052 | 0.00098023 | 0.33863 | 0.79098 | {4F5EBE36-6D68-4A47-AF49-0D6F0830F1BC} | 254151101 | AUBERRY 1101 | R314 | 36.9954 | -119.4087 | AUBERRY 1101R314 | 497 | 416 | 116570.7813 | 70887.9033 | 45682.878 | 67647.5297 | 44505.8052 | 0.23624 | 0.0041219 | 2.2385 | 3.3942 | 419 | 9.8936 | 332 | 0 | 0 | 42.0342 | 1500 | 0
North Coast | 5257 | 811 | 1405.3648 | 1810 | 1726.9236 | 270 | 6.5129e-05 | 724.5634 | 5.5618 | 964.3371 | 20051.919 | 297.893 | 12.0524 | 426.3832 | 1.4607 | 0.040964 | 0.00020693 | 0.44807 | 0.8138 | {03F8A00F-736A-4732-8784-8918754D1A39} | 43311102 | KONOCTI 1102 | 64664 | 38.9435 | -122.7976 | KONOCTI 110264664 | 379 | 329 | 79284.2138 | 46643.7092 | 32640.5046 | 43740.7498 | 31832.9869 | 0.05587 | 0.017585 | 1.7329 | 6.7037 | 1392 | 11.0602 | 333 | 0 | 0 | 27.1792 | 319 | 0
North Coast | 8284 | 89 | 152.0664 | 108 | 162.0934 | 23 | 0.00051332 | 73.4444 | 1.6032 | 157.7234 | 1781.6521 | 11.5481 | 0.38649 | 14.7366 | 1.0266 | 0.040901 | 0.00072398 | 0.82407 | 0.93814 | {F2F5CD46-ED54-485C-8E9F-F1D6186FA89B} | 192311142 | FRUITLAND 1142 | 93234 | 40.2355 | -123.8346 | FRUITLAND 114293234 | 114 | 108 | 21024.4027 | 18464.5673 | 2559.8354 | 18464.5673 | 2559.8354 | 0.016651 | 0.011806 | 1.7086 | 4.6957 | 553 | 0.94073 | 334 | 0 | 0 | 11.4733 | 147 | 0
North Valley | 9163 | 4 | 5.4343 | 10 | 9.1895 | 2 | 0.00011186 | 382.3447 | 0.010651 | 0.22239 | 0.34346 | 3.6924e-06 | 8.8584 | 286.1377 | 1.4303 | 0.040887 | 3.7122e-05 | 0.4 | 0.59136 | {34DFECF9-249D-4DDC-B44C-DC57837D8615} | 103321101 | CEDAR CREEK 1101 | 1710 | 40.7868 | -121.9018 | CEDAR CREEK 11011710 | 7 | 2 | 1582.6832 | 117.4627 | 1465.2205 | 117.4627 | 1465.2205 | 7.4245e-05 | 0.00022373 | 1.3586 | 5 | 2375 | 0.081775 | 335 | 0 | 0 | 0.072988 | 1089 | 0
Sierra | 6980 | 565 | 925.7891 | 1423 | 1266.3588 | 126 | 0.00010409 | 357.2714 | 12.5082 | 59.6461 | 197.8649 | 5.1227 | 10.9698 | 84.9227 | 1.0737 | 0.040859 | 0.00054956 | 0.39705 | 0.73106 | {B656F43A-A721-479D-8405-E771FFE89131} | 152561107 | PENRYN 1107 | 2708 | 38.7961 | -121.1633 | PENRYN 11072708 | 225 | 152 | 26351.6956 | 17082.1753 | 9269.5204 | 15108.1749 | 7585.103 | 0.069245 | 0.013116 | 1.6386 | 11.2937 | 739 | 5.1482 | 336 | 0 | 0 | 9.3878 | 2375 | 0
North Coast | 2495 | 581 | 1220.6003 | 937 | 1410.3119 | 100 | 9.7189e-05 | 452.0632 | 38.5967 | 445.5424 | 2024.6439 | 202.4697 | 12.4531 | 119.4873 | 1.1775 | 0.040819 | 0.001779 | 0.62006 | 0.86548 | {4502A0E5-A181-4FD0-A72F-EAB91B5F9EA1} | 42571101 | MOLINO 1101 | 338 | 38.3959 | -122.8512 | MOLINO 1101338 | 300 | 366 | 48051.516 | 23326.701 | 24724.815 | 10257.7274 | 9233.47 | 0.1779 | 0.0097189 | 2.1009 | 9.37 | 200 | 4.0819 | 337 | 0 | 0 | 6.3739 | 6 | 0
Central Valley | 2159 | 251 | 466.0877 | 997 | 734.904 | 207 | 5.0239e-05 | 868.5568 | 41.9051 | 551.1609 | 3672.6955 | 302.6262 | 10.6103 | 254.8067 | 1.461 | 0.04073 | 0.0011217 | 0.25176 | 0.63422 | {128383E7-96CF-4707-8041-13E4B9B7C999} | 163761704 | RACETRACK 1704 | circuit_breaker | 37.9799 | -120.4138 | RACETRACK 1704circuit_breaker | 257 | 254 | 54908.4625 | 36598.3736 | 18310.089 | 36598.3736 | 18310.089 | 0.23219 | 0.010399 | 1.8569 | 4.8164 | 354 | 8.431 | 338 | 0 | 0 | 22.7412 | 1534 | 0
North Valley | 84 | 326 | 680.535 | 1259 | 914.9265 | 317 | 4.7844e-05 | 907.0264 | 12.6563 | 803.5313 | 5234.6282 | 183.678 | 17.8205 | 650.6451 | 1.2606 | 0.040685 | 0.00030416 | 0.25894 | 0.74381 | {789DE4DB-ACCC-46BB-B059-D9142CE79F75} | 103331101 | CORNING 1101 | 85152 | 40.0157 | -122.4005 | CORNING 110185152 | 378 | 617 | 53501.6144 | 37238.3316 | 16263.2828 | 37238.3316 | 16263.2828 | 0.096418 | 0.015167 | 2.0875 | 3.9716 | 1112 | 12.8973 | 339 | 0 | 0 | 23.1388 | 479 | 0
Sierra | 1849 | 1087 | 1803.0109 | 3671 | 2862.7388 | 397 | 6.7128e-05 | 614.6583 | 11.0202 | 121.8053 | 683.7183 | 9.8751 | 14.4992 | 197.1485 | 1.2152 | 0.040607 | 0.00044566 | 0.2961 | 0.62982 | {87180880-8EB9-4F8B-82CC-028E4C7029F0} | 152561103 | PENRYN 1103 | circuit_breaker | 38.8446 | -121.167 | PENRYN 1103circuit_breaker | 467 | 378 | 68516.4596 | 47859.6372 | 20656.8224 | 45768.8176 | 20332.9382 | 0.17693 | 0.02665 | 1.6587 | 9.2469 | 869 | 16.1209 | 340 | 0 | 0 | 28.4394 | 222 | 0
Bay Area | 992 | 1425 | 1775.7951 | 2243 | 2256.6694 | 251 | 8.3184e-05 | 436.1364 | 1.9631 | 150.8968 | 2150.3586 | 31.0917 | 3.5257 | 229.7075 | 1.2475 | 0.040443 | 0.00011714 | 0.63531 | 0.78691 | {209A9D81-9C3D-4AF8-829C-32C96BA3EBD0} | 42711101 | CALISTOGA 1101 | 890 | 38.6158 | -122.6585 | CALISTOGA 1101890 | 226 | 158 | 45254.4585 | 39735.6 | 5518.8585 | 37703.1619 | 5155.8219 | 0.029401 | 0.020879 | 1.2462 | 8.9363 | 1761 | 10.1513 | 341 | 0 | 0 | 23.4277 | 2491 | 0
Sierra | 133 | 281 | 613.3777 | 1399 | 988.1507 | 334 | 6.0491e-05 | 882.6016 | 16.6544 | 1019.6569 | 5328.1933 | 137.5055 | 14.9146 | 415.7663 | 1.3708 | 0.040275 | 0.00049935 | 0.20086 | 0.62073 | {AE109701-21ED-44EA-AA47-DDDDD6EEFB68} | 153612103 | CLARKSVILLE 2103 | 19572 | 38.6041 | -121.0553 | CLARKSVILLE 210319572 | 425 | 304 | 99924.985 | 69572.9299 | 30352.0551 | 49656.7912 | 24741.73 | 0.16678 | 0.020204 | 2.1828 | 4.1886 | 786 | 13.4518 | 342 | 0 | 0 | 30.8553 | 420 | 0
North Valley | 5999 | 71 | 132.2646 | 255 | 179.3599 | 80 | 4.3681e-05 | 957.0556 | 1.7718 | 6433.3486 | 42262.6302 | 124.1258 | 5.2973 | 1718.629 | 1.7339 | 0.040151 | 4.4954e-05 | 0.27843 | 0.73743 | {DECCC899-88C1-4943-B78C-B486089CB76D} | 102781101 | ELK CREEK 1101 | 2004 | 39.6105 | -122.5319 | ELK CREEK 11012004 | 188 | 164 | 91382.3908 | 86740.0938 | 4642.297 | 34785.4675 | 1064.6535 | 0.0035963 | 0.0034945 | 1.8629 | 3.1875 | 2284 | 3.2121 | 343 | 0 | 0 | 21.6147 | 1286 | 0
North Coast | 3249 | 837 | 1305.7932 | 1219 | 1479.296 | 132 | 0.00013175 | 311.3615 | 10.1715 | 1270.6689 | 16731.0573 | 359.2005 | 0.40296 | 76.8239 | 1.2726 | 0.0401 | 0.00070379 | 0.68663 | 0.88271 | {389365FD-B3C9-4F63-9935-3457B5B05A11} | 42681102 | LAYTONVILLE 1102 | 37586 | 39.6174 | -123.4629 | LAYTONVILLE 110237586 | 101 | 47 | 26173.1755 | 21840.8846 | 4332.2909 | 21840.8846 | 4332.2909 | 0.0929 | 0.017392 | 1.5601 | 9.2348 | 564 | 5.2932 | 344 | 0 | 0 | 13.5713 | 1732 | 0
Bay Area | 7987 | 74 | 192.0933 | 241 | 272.3903 | 62 | 2.4311e-05 | 1426.3979 | 1.1868 | 768.555 | 5724.9753 | 23.5 | 14.243 | 1190.8724 | 1.5857 | 0.039949 | 2.0289e-05 | 0.30705 | 0.70521 | {30969EAF-1760-452C-8E13-34A8BE0709A9} | 14422109 | CAYETANO 2109 | 9504 | 37.7526 | -121.779 | CAYETANO 21099504 | 137 | 74 | 29441.9519 | 23311.7324 | 6130.2194 | 23307.0461 | 6118.6833 | 0.0012579 | 0.0015073 | 2.5959 | 3.8871 | 2604 | 2.4769 | 345 | 0 | 0 | 14.4823 | 2756 | 0
Sierra | 1807 | 383 | 581.1372 | 1580 | 1014.7227 | 224 | 5.1603e-05 | 806.1179 | 7.7557 | 95.1842 | 485.5324 | 7.8689 | 15.509 | 166.6599 | 1.3185 | 0.039866 | 0.000223 | 0.24241 | 0.57271 | {1991DBE6-DAB3-4866-AE61-C7296F9425C8} | 153132105 | NARROWS 2105 | 7203 | 39.1808 | -121.1894 | NARROWS 21057203 | 285 | 225 | 49100.59 | 30163.3265 | 18937.2635 | 29234.7991 | 16504.4172 | 0.049951 | 0.011559 | 1.5173 | 7.0536 | 1332 | 8.9301 | 346 | 0 | 0 | 18.1657 | 585 | 0
North Coast | 4918 | 535 | 728.1104 | 604 | 766.6389 | 112 | 0.00024908 | 151.3447 | 1.3066 | 1285.2038 | 32216.411 | 77.6595 | 0.83089 | 85.6672 | 1.1789 | 0.039623 | 0.0002819 | 0.88576 | 0.94974 | {5393CBB1-CE75-4399-B6C7-25EB732D48AF} | 192461102 | BRIDGEVILLE 1102 | circuit_breaker | 40.4795 | -123.7801 | BRIDGEVILLE 1102circuit_breaker | 193 | 176 | 65019.0666 | 57957.1067 | 7061.96 | 40164.6361 | 3494.1439 | 0.031573 | 0.027897 | 1.361 | 5.3929 | 1169 | 4.4377 | 347 | 0 | 0 | 24.9571 | 981 | 0
Sierra | 631 | 100 | 232.1555 | 220 | 276.9438 | 25 | 7.0661e-05 | 511.5949 | 20.9431 | 232.9347 | 1222.3978 | 42.7925 | 18.7181 | 252.7698 | 1.1658 | 0.039513 | 0.00074451 | 0.45455 | 0.83828 | {51FD1214-1DA9-48E9-81B5-DF5A14DDC488} | 152561105 | PENRYN 1105 | 50548 | 38.8541 | -121.1806 | PENRYN 110550548 | 257 | 236 | 33885.4646 | 19476.8877 | 14408.5769 | 2946.7985 | 1779.707 | 0.018613 | 0.0017665 | 2.3216 | 8.8 | 536 | 0.98781 | 348 | 0 | 0 | 1.8311 | 177 | 0
Sierra | 2520 | 308 | 491.887 | 1342 | 925.5256 | 155 | 7.8194e-05 | 567.2182 | 16.9709 | 81.8421 | 342.6101 | 14.5933 | 17.074 | 103.0456 | 1.0819 | 0.03943 | 0.00065296 | 0.22951 | 0.53147 | {E80D319C-D01D-4A69-9210-7A23DDD13D1F} | 152561103 | PENRYN 1103 | 660 | 38.8495 | -121.1596 | PENRYN 1103660 | 401 | 434 | 55812.0896 | 31352.9096 | 24459.18 | 16391.1944 | 11583.8143 | 0.10121 | 0.01212 | 1.597 | 8.6581 | 613 | 6.1116 | 349 | 0 | 0 | 10.185 | 1518 | 0
North Valley | 4552 | 109 | 175.823 | 312 | 222.942 | 72 | 4.8315e-05 | 707.328 | 3.0576 | 2921.2514 | 20453.1805 | 86.6335 | 8.5652 | 1313.8255 | 1.7171 | 0.039291 | 9.124e-05 | 0.34936 | 0.78865 | {812EE935-23AB-45F1-A410-24F4ACD87AAD} | 102781101 | ELK CREEK 1101 | 2212 | 39.3011 | -122.4941 | ELK CREEK 11012212 | 157 | 157 | 62003.6437 | 53890.7637 | 8112.88 | 17989.0535 | 1526 | 0.0065693 | 0.0034787 | 1.6131 | 4.3333 | 1901 | 2.8289 | 350 | 0 | 0 | 11.1779 | 854 | 0
Sierra | 3901 | 2804 | 3775.6208 | 5429 | 5065.0156 | 643 | 0.00012377 | 400.6898 | 247.3851 | 2785.0039 | 50310.6516 | 24836.3107 | 9.0079 | 86.9248 | 1.2147 | 0.039283 | 0.013352 | 0.51649 | 0.74543 | {5DC9E720-795B-432E-BA68-667FD0BD630A} | 153662102 | APPLE HILL 2102 | circuit_breaker | 38.7393 | -120.6769 | APPLE HILL 2102circuit_breaker | 702 | 772 | 112930.1257 | 66687.7451 | 46242.3805 | 66687.7451 | 46242.3805 | 8.5851 | 0.079585 | 1.3465 | 8.4432 | 2 | 25.2589 | 351 | 0 | 0 | 41.4378 | 3061 | 0
Sierra | 2860 | 61 | 104.4473 | 164 | 143.0152 | 42 | 0.00011434 | 349.4024 | 27.9865 | 526.9842 | 4648.262 | 262.9235 | 11.8401 | 141.5761 | 1.2171 | 0.039271 | 0.0011784 | 0.37195 | 0.73032 | {37338E68-AEEA-49C6-B1EE-76E1EAD86B81} | 153652108 | SHINGLE SPRINGS 2108 | 19762 | 38.6602 | -120.9714 | SHINGLE SPRINGS 210819762 | 115 | 74 | 12220.1289 | 8714.0124 | 3506.1165 | 6558.8623 | 3456.9669 | 0.049493 | 0.0048022 | 1.7123 | 3.9048 | 331 | 1.6494 | 352 | 0 | 0 | 4.0755 | 1839 | 0
Central Valley | 8475 | 59 | 142.3717 | 189 | 187.1244 | 69 | 9.9941e-06 | 3311.5378 | 25.2511 | 6627.5921 | 41002.5708 | 1220.3535 | 40.2623 | 1654.8022 | 1.8448 | 0.039041 | 0.0001647 | 0.31217 | 0.76084 | {E54C0E82-949E-4C90-9607-A30CD2E7D9C4} | 254601103 | SAND CREEK 1103 | circuit_breaker | 36.6443 | -119.1595 | SAND CREEK 1103circuit_breaker | 105 | 67 | 24265.835 | 20610.8944 | 3654.9406 | 20610.8944 | 3654.9406 | 0.011364 | 0.00068959 | 2.4131 | 2.7391 | 1533 | 2.6938 | 353 | 0 | 0 | 12.807 | 1262 | 0
Bay Area | 3594 | 3 | 9.5553 | 5 | 9.9821 | 3 | 1.7689e-05 | 2206.1161 |  |  |  |  | 30.8097 | 1241.9613 | 1.4366 | 0.03904 | 1.7689e-05 | 0.6 | 0.95724 | {C757B1E5-E864-41C5-8F1F-450BE13C3852} | 13751102 | VASCO 1102 | MR178 | 37.6665 | -121.6967 | VASCO 1102MR178 | 167 | 89 | 31044.3224 | 21484.5374 | 9559.7851 | 2230.6889 | 1010.539 | 5.3068e-05 | 5.3068e-05 | 3.1851 | 1.6667 | 2654 | 0.11712 | 354 | 0 | 0 | 1.3861 | 2338 | 0
Sierra | 3008 | 676 | 1004.7655 | 1973 | 1566.1909 | 262 | 6.5426e-05 | 795.4997 | 9.0132 | 336.4564 | 1907.8475 | 35.7512 | 14.9964 | 299.3875 | 1.3178 | 0.038838 | 0.00033382 | 0.34263 | 0.64153 | {460117C5-52D5-4539-942E-65301ACAACE9} | 153132105 | NARROWS 2105 | 2228 | 39.2009 | -121.2091 | NARROWS 21052228 | 286 | 294 | 66019.7996 | 34109.5496 | 31910.25 | 33185.7143 | 30792.1565 | 0.087462 | 0.017142 | 1.4863 | 7.5305 | 1047 | 10.1756 | 355 | 0 | 0 | 20.6206 | 2069 | 0
North Valley | 4039 | 714 | 1109.0151 | 1872 | 1532.8945 | 286 | 4.977e-05 | 848.6121 | 12.2128 | 1568.5716 | 13212.1614 | 457.0949 | 8.5074 | 837.3823 | 1.5571 | 0.038804 | 0.0002482 | 0.38141 | 0.72348 | {82F08C11-2D8C-48A8-99CC-7F0954F836A6} | 103401101 | GIRVAN 1101 | 323094 | 40.4984 | -122.5727 | GIRVAN 1101323094 | 239 | 206 | 78433.4178 | 58215.1727 | 20218.2451 | 58215.1727 | 20218.2451 | 0.070985 | 0.014234 | 1.5532 | 6.5455 | 1255 | 11.098 | 356 | 0 | 0 | 36.1732 | 1057 | 0
North Valley | 2841 | 526 | 977.5627 | 2056 | 1481.5684 | 267 | 3.8106e-05 | 1149.1578 | 27.542 | 592.8456 | 3275.2435 | 207.6515 | 19.477 | 340.7761 | 1.4755 | 0.038648 | 0.00056041 | 0.25584 | 0.65982 | {F4C4052A-4712-4518-990B-FE0E43960860} | 102911107 | WYANDOTTE 1107 | 1026 | 39.4568 | -121.4618 | WYANDOTTE 11071026 | 369 | 319 | 71399.7906 | 44780.2125 | 26619.578 | 34466.4557 | 18829.7136 | 0.14963 | 0.010174 | 1.8585 | 7.7004 | 722 | 10.319 | 357 | 0 | 0 | 21.4165 | 1326 | 0
North Coast | 2229 | 14 | 25.9061 | 35 | 32.5217 | 14 | 6.1829e-05 | 838.6254 | 11.9255 | 1497.0238 | 9639.756 | 182.1785 | 11.7762 | 583.5853 | 1.4068 | 0.038647 | 0.00046801 | 0.4 | 0.79658 | {01278228-324E-4DE9-A0E4-67F4CFACFDAB} | 43141102 | MIDDLETOWN 1102 | 414 | 38.7829 | -122.5657 | MIDDLETOWN 1102414 | 185 | 501 | 53082.0293 | 18793.485 | 34288.5443 | 8076.5942 | 11913.405 | 0.0065521 | 0.00086561 | 1.8504 | 2.5 | 832 | 0.54106 | 358 | 0 | 0 | 5.0186 | 965 | 0
Sierra | 7670 | 59 | 119.629 | 221 | 183.9517 | 28 | 5.995e-05 | 610.5667 | 29.9906 | 206.977 | 985.4963 | 65.7161 | 17.1413 | 262.8315 | 1.2143 | 0.038455 | 0.0011762 | 0.26697 | 0.65033 | {58251FB2-5D98-4B8D-BEC3-F95636B42578} | 152561105 | PENRYN 1105 | 50550 | 38.8511 | -121.1794 | PENRYN 110550550 | 262 | 289 | 40488.5314 | 22728.582 | 17759.9495 | 3634.5722 | 2897.3531 | 0.032934 | 0.0016786 | 2.0276 | 7.8929 | 333 | 1.0768 | 359 | 0 | 0 | 2.2584 | 515 | 0
North Valley | 4992 | 129 | 203.105 | 270 | 247.5278 | 110 | 3.6453e-05 | 1106.405 | 5.6582 | 3651.3966 | 28725.0888 | 301.8604 | 10.6008 | 1862.4875 | 1.7287 | 0.038404 | 0.00013482 | 0.47778 | 0.82053 | {96C223CD-EECE-427E-9B50-0567153A92FD} | 103331102 | CORNING 1102 | 1622 | 39.8904 | -122.5369 | CORNING 11021622 | 135 | 100 | 63478.8301 | 54857.2254 | 8621.6047 | 54857.2254 | 8621.6047 | 0.01483 | 0.0040099 | 1.5745 | 2.4545 | 1667 | 4.2244 | 360 | 0 | 0 | 34.0867 | 821 | 0
Bay Area | 3079 | 1 | 1.2277 | 5 | 6.6984 | 1 | 0.00012265 | 2429.1768 |  |  |  |  | 34.2013 | 386.4345 | 1.6062 | 0.29793 | 0.00012265 | 0.2 | 0.18328 | {9B3053D4-0FCD-415D-AE49-1C1AC44BB827} | 152261105 | DIAMOND SPRINGS 1105 | 7722 | 38.6778 | -120.8497 | DIAMOND SPRINGS 11057722 | 807 | 822 | 160711.8744 | 100030.6738 | 60681.2005 | 95268.3331 | 57109.0073 | 0.00012265 | 0.00012265 | 1.2277 | 5 | 1739 | 0.29793 | 361 | 0 | 0 | 59.197 | 1532 | 0
Sierra | 3079 | 972 | 1622.5374 | 5005 | 3255.5862 | 743 | 9.2762e-05 | 405.7984 | 17.3995 | 361.342 | 3282.4418 | 103.8943 | 8.3778 | 119.5534 | 1.2352 | 0.038021 | 0.00077768 | 0.19421 | 0.49839 | {9B3053D4-0FCD-415D-AE49-1C1AC44BB827} | 152261105 | DIAMOND SPRINGS 1105 | 7722 | 38.6778 | -120.8497 | DIAMOND SPRINGS 11057722 | 807 | 822 | 160711.8744 | 100030.6738 | 60681.2005 | 95268.3331 | 57109.0073 | 0.57782 | 0.068922 | 1.6693 | 6.7362 | 512 | 28.2497 | 361 | 0 | 0 | 59.197 | 1875 | 0
Central Coast | 1699 | 2 | 4.3073 | 78 | 51.7605 | 18 | 4.1785e-05 | 956.2289 | 1.6085 | 116.9932 | 486.3455 | 1.08 | 13.2368 | 242.261 | 1.2019 | 0.038288 | 5.7123e-05 | 0.025641 | 0.083217 | {D016C3BB-2E2C-416D-87C1-82B4CA16BCAB} | 183052112 | TEMPLETON 2112 | R28 | 35.5899 | -120.6934 | TEMPLETON 2112R28 | 345 | 206 | 53924.2204 | 39551.4346 | 14372.7858 | 3272.9638 | 1387.2363 | 0.0010282 | 0.00075213 | 2.1537 | 4.3333 | 2172 | 0.68918 | 362 | 0 | 0 | 2.0337 | 313 | 0
North Valley | 3240 | 2 | 2.2 | 80 | 24.9869 | 20 | 4.6523e-05 | 951.1009 | 3.907 | 13.1787 | 37.1062 | 0.53049 | 22.2602 | 98.0431 | 1.1846 | 0.038067 | 0.0001093 | 0.025 | 0.088045 | {2E1FA774-5A9F-4570-9AF6-F0EFBD272BA5} | 103541104 | RED BLUFF 1104 | circuit_breaker | 40.1823 | -122.2446 | RED BLUFF 1104circuit_breaker | 232 | 461 | 32104.578 | 16940.324 | 15164.2539 | 2365.4631 | 2300.5787 | 0.002186 | 0.00093046 | 1.1 | 4 | 1805 | 0.76134 | 363 | 0 | 0 | 1.4698 | 2403 | 0
Bay Area | 5549 | 24 | 32.9457 | 62 | 52.4398 | 8 | 4.4584e-05 | 807.367 | 0.00023107 | 0.0029483 | 0.0062793 | 1.0945e-07 | 22.573 | 188.9364 | 1.4463 | 0.037729 | 3.8326e-05 | 0.3871 | 0.62826 | {9E39C048-EF22-4DAE-9CE9-DEC0330A8321} | 43051101 | MONTICELLO 1101 | 65454 | 38.4489 | -122.1955 | MONTICELLO 110165454 | 34 | 33 | 7634.7595 | 3019.3036 | 4615.4559 | 1332.2655 | 2442.5597 | 0.00030661 | 0.00035667 | 1.3727 | 7.75 | 2359 | 0.30184 | 364 | 0 | 0 | 0.82783 | 1763 | 0
Sierra | 5262 | 242 | 341.5984 | 546 | 473.3208 | 50 | 7.9564e-05 | 407.9301 | 21.3567 | 116.9509 | 487.4647 | 26.0435 | 11.6201 | 116.0124 | 1.0953 | 0.037642 | 0.00097582 | 0.44322 | 0.72171 | {EB4C43F2-5A6C-4135-94F6-89D7E69DB625} | 152561105 | PENRYN 1105 | 2406 | 38.8519 | -121.1656 | PENRYN 11052406 | 269 | 436 | 41610.1168 | 19927.713 | 21682.4038 | 4637.0241 | 3868.4688 | 0.048791 | 0.0039782 | 1.4116 | 10.92 | 421 | 1.8821 | 365 | 0 | 0 | 2.8813 | 667 | 0
Sierra | 4504 | 260 | 385.8932 | 937 | 644.5386 | 123 | 0.00013596 | 270.2105 | 15.3571 | 87.8084 | 622.9107 | 22.9525 | 9.5732 | 82.2939 | 1.2222 | 0.037498 | 0.0013044 | 0.27748 | 0.59871 | {189FDEE6-C0C8-4312-8E54-D1B717348AC0} | 153652110 | SHINGLE SPRINGS 2110 | 51790 | 38.6639 | -120.931 | SHINGLE SPRINGS 211051790 | 175 | 153 | 23210.7859 | 13935.3436 | 9275.4423 | 12398.7678 | 8085.7463 | 0.16045 | 0.016723 | 1.4842 | 7.6179 | 293 | 4.6123 | 366 | 0 | 0 | 7.7042 | 166 | 0
Central Valley | 5336 | 4 | 7.7799 | 11 | 10.3706 | 7 | 6.0197e-05 | 700.0424 | 7.7823 | 146.6408 | 1139.1021 | 11.8487 | 13.391 | 683.7084 | 1.6852 | 0.037301 | 0.00020136 | 0.36364 | 0.75019 | {96707C24-07B2-408B-B719-59181F4D3F8C} | 254452102 | MARIPOSA 2102 | 241564 | 37.4871 | -119.9619 | MARIPOSA 2102241564 | 43 | 13 | 2371.1669 | 1779.8257 | 591.3412 | 874.7258 | 209.6462 | 0.0014095 | 0.00042138 | 1.945 | 1.5714 | 1406 | 0.2611 | 367 | 0 | 0 | 0.54353 | 254 | 0
Bay Area | 4183 | 52 | 64.2289 | 188 | 143.3304 | 33 | 9.8692e-05 | 333.1711 | 0.44498 | 58.4898 | 1290.3002 | 1.1483 | 0.2502 | 68.4888 | 1.4527 | 0.037201 | 9.5202e-05 | 0.2766 | 0.44812 | {2D821F7B-3CD2-4C8D-9060-9FD2240F0305} | 43292102 | PUEBLO 2102 | 618 | 38.4081 | -122.3695 | PUEBLO 2102618 | 265 | 196 | 32044.8878 | 26675.4835 | 5369.4043 | 3904.0753 | 501.4495 | 0.0031417 | 0.0032568 | 1.2352 | 5.697 | 1878 | 1.2276 | 368 | 0 | 0 | 2.4259 | 2273 | 0
Sierra | 759 | 1406 | 2192.2337 | 4573 | 3389.5498 | 492 | 0.00013354 | 345.443 | 10.3793 | 106.1921 | 801.5924 | 21.0173 | 8.8553 | 117.6032 | 1.2229 | 0.037041 | 0.00065714 | 0.30746 | 0.64676 | {429BE041-BFDB-4BDA-8A2A-CC28CF49B6B2} | 152261105 | DIAMOND SPRINGS 1105 | 2102 | 38.6825 | -120.8523 | DIAMOND SPRINGS 11052102 | 680 | 674 | 104079.284 | 62924.1894 | 41155.0946 | 60433.983 | 37939.9899 | 0.32331 | 0.065702 | 1.5592 | 9.2947 | 606 | 18.2244 | 369 | 0 | 0 | 37.5519 | 937 | 0
Sierra | 3480 | 125 | 231.6192 | 745 | 448.6638 | 88 | 0.00012022 | 272.2979 | 13.4432 | 38.1113 | 120.7563 | 3.0166 | 6.7327 | 67.6293 | 1.1223 | 0.036598 | 0.00072582 | 0.16779 | 0.51624 | {6D7EDEBC-3FBC-46B9-8C4A-F91AD5A5BEDF} | 153652109 | SHINGLE SPRINGS 2109 | 2053 | 38.72 | -120.9392 | SHINGLE SPRINGS 21092053 | 128 | 159 | 20735.4804 | 9206.1637 | 11529.3167 | 9206.1637 | 11529.3167 | 0.063872 | 0.01058 | 1.853 | 8.4659 | 551 | 3.2207 | 370 | 0 | 0 | 5.7204 | 764 | 0
Sierra | 5292 | 30 | 37.7801 | 53 | 46.7816 | 6 | 1.8126e-05 | 1796.6057 | 0.0012351 | 0.22239 | 0.071279 | 1.7268e-07 | 37.3193 | 263.1211 | 1.2898 | 0.036536 | 1.4703e-05 | 0.56604 | 0.80758 | {54E0D9F0-5A0E-4C2B-BA84-938E576B6A76} | 63601108 | VACAVILLE 1108 | 47860 | 38.3593 | -122.0011 | VACAVILLE 110847860 | 134 | 422 | 24865.4716 | 6327.6617 | 18537.8099 | 451.5656 | 308.1809 | 8.8216e-05 | 0.00010876 | 1.2593 | 8.8333 | 2710 | 0.21922 | 371 | 0 | 0 | 0.28059 | 825 | 0
North Coast | 2013 | 113 | 171.8867 | 165 | 195.7122 | 27 | 7.7799e-05 | 442.5679 | 7.1947 | 1509.5108 | 18025.8777 | 160.1493 | 0.97427 | 105.2274 | 1.311 | 0.036411 | 0.0003172 | 0.68485 | 0.87826 | {48D8AB29-32BE-434B-A269-6B6F081BC956} | 42681101 | LAYTONVILLE 1101 | 518 | 39.7981 | -123.5405 | LAYTONVILLE 1101518 | 191 | 127 | 49486.031 | 36002.4776 | 13483.5535 | 3441.5642 | 1189.9084 | 0.0085645 | 0.0021006 | 1.5211 | 6.1111 | 1086 | 0.9831 | 372 | 0 | 0 | 2.1385 | 425 | 0
Bay Area | 345 | 16 | 20.2554 | 57 | 42.5233 | 9 | 8.6632e-05 | 362.16 | 13.7687 | 660.0113 | 7632.1899 | 420.3429 | 0.32448 | 28.7016 | 1.1384 | 0.036139 | 0.00062481 | 0.2807 | 0.47634 | {95F0930E-F4E9-4090-B429-18E6DA1F891D} | 43292102 | PUEBLO 2102 | 656 | 38.3886 | -122.318 | PUEBLO 2102656 | 260 | 313 | 43957.8417 | 27867.5616 | 16090.2801 | 592.9592 | 121.6404 | 0.0056233 | 0.00077969 | 1.266 | 6.3333 | 645 | 0.32525 | 373 | 0 | 0 | 0.36845 | 984 | 0
North Coast | 512 | 67 | 86.5299 | 113 | 107.6118 | 31 | 9.5194e-05 | 526.9792 | 95.8978 | 2532.8601 | 34514.8783 | 6628.2803 | 13.0057 | 361.3679 | 1.4838 | 0.03591 | 0.0026153 | 0.59292 | 0.80409 | {EC79F2BF-D405-4EF8-A570-37C7BDE7D1BE} | 42661103 | WILLITS 1103 | 696 | 39.4145 | -123.3264 | WILLITS 1103696 | 130 | 87 | 27464.4203 | 15378.4562 | 12085.9642 | 8552.3738 | 3468.5893 | 0.081074 | 0.002951 | 1.2915 | 3.6452 | 123 | 1.1132 | 374 | 0 | 0 | 5.3142 | 864 | 0
Sierra | 508 | 423 | 834.9601 | 2333 | 1512.1478 | 376 | 9.5874e-05 | 416.5337 | 46.9693 | 549.7478 | 4733.3142 | 538.4672 | 12.82 | 197.8256 | 1.202 | 0.035823 | 0.0024242 | 0.18131 | 0.55217 | {76CF34A1-3FD0-4E72-BAFC-6CFED61FA5FB} | 153612104 | CLARKSVILLE 2104 | 13352 | 38.6855 | -121.0118 | CLARKSVILLE 210413352 | 591 | 435 | 92513.6422 | 58866.4594 | 33647.1828 | 54145.4284 | 30739.3832 | 0.91151 | 0.036049 | 1.9739 | 6.2048 | 133 | 13.4695 | 375 | 0 | 0 | 33.6444 | 460 | 0
Sierra | 2819 | 738 | 1299.4053 | 3420 | 2154.6462 | 547 | 6.191e-05 | 592.263 | 14.3204 | 350.5251 | 1925.7453 | 49.2729 | 12.2573 | 288.074 | 1.3936 | 0.035775 | 0.00045404 | 0.21579 | 0.60307 | {63551680-2169-45C3-BF85-1608C868FCAF} | 153132101 | NARROWS 2101 | 1202 | 39.2105 | -121.3108 | NARROWS 21011202 | 636 | 543 | 110950.8145 | 73260.5674 | 37690.2472 | 73260.5674 | 37690.2472 | 0.24836 | 0.033865 | 1.7607 | 6.2523 | 855 | 19.5689 | 376 | 0 | 0 | 45.522 | 629 | 0
Sierra | 2065 | 593 | 856.7663 | 1625 | 1301.933 | 215 | 6.4667e-05 | 552.1358 | 9.1347 | 158.5129 | 1185.9763 | 21.9696 | 12.585 | 242.4922 | 1.4351 | 0.035745 | 0.0002833 | 0.36492 | 0.65807 | {D289A671-DB97-4331-A89A-832836F9DE82} | 153741101 | DOBBINS 1101 | 1808 | 39.3745 | -121.2339 | DOBBINS 11011808 | 230 | 191 | 31444.308 | 24893.8312 | 6550.4768 | 24893.8312 | 6550.4768 | 0.060909 | 0.013903 | 1.4448 | 7.5581 | 1165 | 7.6851 | 377 | 0 | 0 | 15.4683 | 1935 | 0
Bay Area | 590 | 66 | 96.6565 | 266 | 216.2325 | 41 | 8.8421e-05 | 447.2531 | 7.8373 | 20.4765 | 63.6182 | 1.2416 | 7.3726 | 72.5944 | 1.2901 | 0.035696 | 0.00040986 | 0.24812 | 0.447 | {890FBE04-45F2-477D-ABCA-3FF18127DAFA} | 43201102 | STAFFORD 1102 | 524 | 38.1072 | -122.5941 | STAFFORD 1102524 | 326 | 810 | 67912.0003 | 20662.3416 | 47249.6586 | 9046.5504 | 11648.9007 | 0.016804 | 0.0036253 | 1.4645 | 6.4878 | 929 | 1.4635 | 378 | 0 | 0 | 5.6213 | 1219 | 0
Bay Area | 7656 | 235 | 426.7285 | 524 | 563.5076 | 75 | 2.2084e-05 | 1826.1121 | 6.8743 | 790.0492 | 4404.9781 | 139.9032 | 24.0184 | 1290.9183 | 1.401 | 0.03542 | 0.00012417 | 0.44847 | 0.75727 | {7713D0FD-BB09-40ED-B7D7-E260577647D4} | 14052103 | NORTH DUBLIN 2103 | circuit_breaker | 37.7445 | -121.857 | NORTH DUBLIN 2103circuit_breaker | 221 | 155 | 32695.429 | 24183.6175 | 8511.8114 | 20889.9745 | 8082.7173 | 0.0093128 | 0.0016563 | 1.8159 | 6.9867 | 1731 | 2.6565 | 379 | 0 | 0 | 12.9804 | 1235 | 0
Bay Area | 5383 | 51 | 103.0956 | 129 | 135.7625 | 27 | 1.0126e-05 | 3274.3056 | 28.4546 | 3576.6015 | 18831.292 | 577.7157 | 36.4921 | 3367.0272 | 1.7037 | 0.035394 | 8.2776e-05 | 0.39535 | 0.75938 | {5BDCF064-976E-49BF-91E3-AF71A40D145E} | 13751102 | VASCO 1102 | 11338 | 37.6634 | -121.6804 | VASCO 110211338 | 210 | 144 | 47738.2476 | 30852.0505 | 16886.1971 | 8850.5675 | 9821.1471 | 0.002235 | 0.00027341 | 2.0215 | 4.7778 | 1964 | 0.95564 | 380 | 0 | 0 | 5.4995 | 2652 | 0
North Valley | 2279 | 170 | 225.922 | 456 | 362.0761 | 94 | 8.4395e-05 | 400.4077 | 87.257 | 6428.4981 | 170087.1629 | 18132.1808 | 1.0729 | 58.8077 | 1.2036 | 0.035216 | 0.0036241 | 0.37281 | 0.62396 | {2918771D-6581-42EC-9677-9556A91AF88E} | 103221101 | KANAKA 1101 | 1034 | 39.5763 | -121.3024 | KANAKA 11011034 | 109 | 71 | 25228.0571 | 21171.6713 | 4056.3858 | 21171.6713 | 4056.3858 | 0.34067 | 0.0079331 | 1.329 | 4.8511 | 73 | 3.3103 | 381 | 0 | 0 | 13.1555 | 1043 | 0
Sierra | 6475 | 31 | 54.8968 | 115 | 88.0865 | 9 | 8.9459e-05 | 513.1483 | 7.6669 | 47.0416 | 151.3801 | 1.4316 | 12.811 | 92.807 | 1.0824 | 0.034655 | 0.00030263 | 0.26957 | 0.62322 | {346A62D2-9F89-49F3-B966-B00C57570576} | 152571101 | HORSESHOE 1101 | 1682 | 38.7707 | -121.1643 | HORSESHOE 11011682 | 222 | 176 | 26742.8626 | 15688.8599 | 11054.0027 | 944.4917 | 1140.3256 | 0.0027237 | 0.00080513 | 1.7709 | 12.7778 | 1114 | 0.31189 | 382 | 0 | 0 | 0.58688 | 504 | 0
North Coast | 9707 | 28 | 38.6586 | 41 | 46.043 | 8 | 7.7213e-05 | 422.3591 | 0.53578 | 30.935 | 290.9604 | 0.27566 | 0.63551 | 17.7302 | 1.1123 | 0.034594 | 6.162e-05 | 0.68293 | 0.83962 | {5A3AA98B-24A2-41A0-8E61-B5A0B5E2F3E7} | 42891102 | GEYSERVILLE 1102 | 756 | 38.6973 | -122.8549 | GEYSERVILLE 1102756 | 8 | 6 | 1028.8029 | 948.4078 | 80.3951 | 948.4078 | 80.3951 | 0.00049296 | 0.0006177 | 1.3807 | 5.125 | 2118 | 0.27675 | 383 | 0 | 0 | 0.58931 | 535 | 0
Sierra | 1983 | 342 | 595.9149 | 723 | 732.2071 | 146 | 4.8084e-05 | 845.7627 | 12.8753 | 306.2617 | 1469.5247 | 52.3035 | 15.8407 | 341.4668 | 1.4072 | 0.034575 | 0.00029039 | 0.47303 | 0.81386 | {90A2FAB3-9517-4F41-ABE9-643E537A58ED} | 153791101 | SMARTVILLE 1101 | circuit_breaker | 39.2085 | -121.3027 | SMARTVILLE 1101circuit_breaker | 218 | 234 | 37252.8383 | 26180.464 | 11072.3743 | 26009.9248 | 10888.2359 | 0.042398 | 0.0070202 | 1.7424 | 4.9521 | 1151 | 5.0479 | 384 | 0 | 0 | 16.1618 | 1521 | 0
North Coast | 8449 | 9 | 14.4629 | 33 | 20.7964 | 8 | 7.0281e-05 | 402.6672 | 1.0993 | 25.8118 | 146.6172 | 6.3336 | 10.0893 | 244.2513 | 1.2475 | 0.034451 | 5.988e-05 | 0.27273 | 0.69545 | {45C1901D-E49E-428E-8B0F-B20AF66CAD20} | 43211102 | HARTLEY 1102 | 524 | 39.0788 | -122.9339 | HARTLEY 1102524 | 52 | 43 | 10994.4761 | 7246.3624 | 3748.1136 | 2350.321 | 348.8739 | 0.00047904 | 0.00056225 | 1.607 | 4.125 | 2142 | 0.27561 | 385 | 0 | 0 | 1.4604 | 11 | 0
North Coast | 4143 | 206 | 378.6966 | 500 | 497.0715 | 105 | 5.8449e-05 | 484.8243 | 3.5437 | 196.3114 | 1657.6672 | 21.4412 | 6.9187 | 424.2987 | 1.3448 | 0.033977 | 0.00012352 | 0.412 | 0.76186 | {5D4D8690-5B01-4EDA-9ADD-A0F82EE8F0D4} | 43191102 | REDBUD 1102 | circuit_breaker | 39.0271 | -122.6628 | REDBUD 1102circuit_breaker | 248 | 194 | 60758.469 | 32033.4913 | 28724.9778 | 26827.5429 | 21672.9137 | 0.01297 | 0.0061372 | 1.8383 | 4.7619 | 1733 | 3.5676 | 386 | 0 | 0 | 16.6699 | 689 | 0
North Coast | 1419 | 890 | 1207.0373 | 1305 | 1408.6827 | 203 | 0.00012924 | 245.378 | 2.8621 | 804.8587 | 12526.6361 | 107.9833 | 1.6149 | 112.1458 | 1.1593 | 0.033752 | 0.0002446 | 0.68199 | 0.85686 | {DDBF5221-9BD5-419F-9A17-E9260A89D7CD} | 192321122 | FORT SEWARD 1122 | circuit_breaker | 40.2136 | -123.5964 | FORT SEWARD 1122circuit_breaker | 119 | 139 | 47276.8254 | 35129.8817 | 12146.9437 | 28255.3669 | 11501.226 | 0.049654 | 0.026236 | 1.3562 | 6.4286 | 1264 | 6.8517 | 387 | 0 | 0 | 17.5571 | 1477 | 0
North Coast | 5135 | 549 | 930.574 | 1246 | 1149.922 | 235 | 6.6248e-05 | 465.4042 | 33.2962 | 2714.3395 | 28618.1422 | 1331.6516 | 9.7145 | 584.1753 | 1.5688 | 0.033689 | 0.0010277 | 0.44061 | 0.80925 | {4496154F-1DB9-4FB1-A431-4CE20A572B84} | 43361103 | HIGHLANDS 1103 | 482 | 38.908 | -122.5961 | HIGHLANDS 1103482 | 235 | 159 | 60613.0273 | 41526.8283 | 19086.199 | 38824.923 | 15555.1559 | 0.24151 | 0.015568 | 1.695 | 5.3021 | 399 | 7.917 | 388 | 0 | 0 | 24.1247 | 1503 | 0
Bay Area | 3383 | 85 | 120.5563 | 443 | 337.1361 | 22 | 0.00016604 | 186.1757 | 5.2084 | 287.9022 | 4140.3903 | 59.3986 | 0.92558 | 19.2317 | 1.0554 | 0.033661 | 0.00042961 | 0.19187 | 0.35759 | {C0D404A9-516B-476A-9629-EE9B990B6FDA} | 43021102 | WOODACRE 1102 | 851 | 38.0057 | -122.638 | WOODACRE 1102851 | 26 | 139 | 8471.5859 | 2053.4749 | 6418.111 | 2053.4749 | 6418.111 | 0.0094514 | 0.0036529 | 1.4183 | 20.1364 | 891 | 0.74053 | 389 | 0 | 0 | 1.276 | 966 | 0
Bay Area | 8364 | 0 | 0 | 17 | 9.4117 | 3 | 4.5324e-05 | 741.4562 | 7.0093 | 385.5315 | 1311.5419 | 14.9319 | 11.7611 | 697.2445 | 1.5678 | 0.033609 | 0.00022786 | 0 | 0 | {8556DC30-45DF-483E-A1A0-A7C23CC64830} | 42021102 | NAPA 1102 | 5039 | 38.2581 | -122.3383 | NAPA 11025039 | 60 | 39 | 11754.3615 | 8769.8715 | 2984.4901 | 68.3438 | 57.5931 | 0.00068359 | 0.00013597 |  | 5.6667 | 1319 | 0.10083 | 390 | 0 | 0 | 0.042467 | 1137 | 0
Central Valley | 3421 | 162 | 247.232 | 957 | 507.001 | 197 | 1.8706e-05 | 1707.5751 | 98.0109 | 4145.2701 | 37770.2156 | 6509.3121 | 25.9701 | 821.5405 | 1.7477 | 0.033578 | 0.00096599 | 0.16928 | 0.48764 | {079BD93C-880F-493A-A5F3-34E94A52D05E} | 254061103 | DUNLAP 1103 | 7040 | 36.7388 | -119.1217 | DUNLAP 11037040 | 311 | 302 | 58875.061 | 39870.7942 | 19004.2668 | 39870.7942 | 19004.2668 | 0.1903 | 0.0036851 | 1.5261 | 4.8579 | 428 | 6.6149 | 391 | 0 | 0 | 24.7746 | 1754 | 0
Central Valley | 1043 | 161 | 224.5105 | 627 | 435.4779 | 157 | 4.85e-05 | 754.3293 | 15.9042 | 362.6192 | 3046.5201 | 124.2139 | 14.6241 | 308.9836 | 1.4809 | 0.033565 | 0.00042948 | 0.25678 | 0.51555 | {A16C1879-E924-48DF-A54B-36A49902B835} | 254452101 | MARIPOSA 2101 | 10990 | 37.4965 | -119.8112 | MARIPOSA 210110990 | 491 | 498 | 113771.1759 | 64117.5165 | 49653.6594 | 64117.5165 | 49653.6594 | 0.067429 | 0.0076145 | 1.3945 | 3.9936 | 893 | 5.2697 | 392 | 0 | 0 | 39.8408 | 1721 | 0
North Coast | 2034 | 2259 | 4104.3522 | 3630 | 4739.851 | 369 | 9.6651e-05 | 296.1743 | 3.3642 | 235.5646 | 1793.2102 | 9.7378 | 4.5829 | 138.013 | 1.1884 | 0.033444 | 0.00020357 | 0.62231 | 0.86592 | {A45E0124-BCF3-4DBF-9317-CD21317A326D} | 42601101 | PHILO 1101 | circuit_breaker | 39.064 | -123.4378 | PHILO 1101circuit_breaker | 712 | 903 | 135354.5622 | 79786.4997 | 55568.0625 | 48254.7037 | 22956.1468 | 0.075119 | 0.035664 | 1.8169 | 9.8374 | 1401 | 12.3408 | 393 | 0 | 0 | 29.9841 | 775 | 0
North Coast | 7419 | 133 | 181.9369 | 290 | 273.9298 | 79 | 7.5743e-05 | 428.2337 | 1.2282 | 273.3662 | 3360.2093 | 9.9607 | 1.5029 | 254.5438 | 1.4179 | 0.033293 | 7.7111e-05 | 0.45862 | 0.66417 | {08D74C7F-8D6E-4EDB-8355-DEA79828121D} | 42821102 | CLOVERDALE 1102 | 4646 | 38.7891 | -123.0171 | CLOVERDALE 11024646 | 75 | 40 | 27348.2217 | 24017.6199 | 3330.6019 | 22119.9907 | 3120.9534 | 0.0060918 | 0.0059837 | 1.3679 | 3.6709 | 2003 | 2.6302 | 394 | 0 | 0 | 13.7447 | 1323 | 0
Central Coast | 6331 | 36 | 64.391 | 87 | 95.8138 | 12 | 5.8145e-05 | 795.4099 | 2.2433 | 25.1372 | 65.3024 | 0.22206 | 16.2684 | 149.0892 | 1.1165 | 0.033289 | 7.0378e-05 | 0.41379 | 0.67204 | {1B5D7998-B20D-4848-BE59-22884992869D} | 83182107 | LLAGAS 2107 | XR188 | 37.0127 | -121.6026 | LLAGAS 2107XR188 | 150 | 106 | 18709.0395 | 9907.5767 | 8801.4629 | 2228.2099 | 1043.639 | 0.00084454 | 0.00069774 | 1.7886 | 7.25 | 2054 | 0.39946 | 395 | 0 | 0 | 1.3845 | 2131 | 0
Bay Area | 444 | 95 | 111.5951 | 243 | 196.479 | 30 | 0.00012723 | 248.9164 | 7.499 | 231.7322 | 3313.4155 | 85.5391 | 7.087 | 137.9278 | 1.2651 | 0.03312 | 0.00052024 | 0.39095 | 0.56797 | {20AC1997-FDD9-4119-81FC-6AC3608237B2} | 42711101 | CALISTOGA 1101 | 1087 | 38.5846 | -122.6722 | CALISTOGA 11011087 | 24 | 32 | 4177.5465 | 3128.3884 | 1049.1581 | 3128.3884 | 1049.1581 | 0.015607 | 0.0038168 | 1.1747 | 8.1 | 775 | 0.9936 | 396 | 0 | 0 | 1.9439 | 1932 | 0
North Coast | 5478 | 430 | 605.4348 | 723 | 762.678 | 152 | 7.8539e-05 | 393.0805 | 4.568 | 735.6137 | 9921.5759 | 100.6197 | 2.4346 | 237.343 | 1.4612 | 0.03298 | 0.00022126 | 0.59474 | 0.79383 | {B86F1274-5A5C-436E-B792-43E98848CB75} | 42821102 | CLOVERDALE 1102 | 672 | 38.8238 | -123.0032 | CLOVERDALE 1102672 | 168 | 162 | 55257.6564 | 36513.5782 | 18744.0782 | 35674.8205 | 17482.1716 | 0.033631 | 0.011938 | 1.408 | 4.7566 | 1339 | 5.013 | 397 | 0 | 0 | 22.1673 | 1207 | 0
Sierra | 1087 | 570 | 1008.9996 | 2859 | 1715.5928 | 411 | 7.5788e-05 | 479.5684 | 23.7596 | 299.8507 | 1583.3563 | 72.2357 | 12.2322 | 161.1978 | 1.2493 | 0.03466 | 0.00080499 | 0.19937 | 0.58813 | {4EADDDA4-9026-4CB9-B9C4-03D97B5E8FF0} | 103191101 | BANGOR 1101 | 1958 | 39.3568 | -121.3667 | BANGOR 11011958 | 532 | 401 | 78091.4744 | 54026.2311 | 24065.2432 | 54026.2311 | 24065.2432 | 0.33085 | 0.031149 | 1.7702 | 6.9562 | 497 | 14.2451 | 398 | 0 | 0 | 33.5703 | 1828 | 0
North Valley | 1087 | 50 | 67.0499 | 160 | 107.8283 | 28 | 7.6549e-05 | 129.7249 | 4.6434 | 160.1901 | 696.5607 | 8.2746 | 3.7887 | 92.1038 | 1.0692 | 0.0078783 | 0.00026406 | 0.3125 | 0.62182 | {4EADDDA4-9026-4CB9-B9C4-03D97B5E8FF0} | 103191101 | BANGOR 1101 | 1958 | 39.3568 | -121.3667 | BANGOR 11011958 | 532 | 401 | 78091.4744 | 54026.2311 | 24065.2432 | 54026.2311 | 24065.2432 | 0.0073937 | 0.0021434 | 1.341 | 5.7143 | 1210 | 0.22059 | 398 | 0 | 0 | 33.5703 | 1761 | 0
North Coast | 2125 | 330 | 448.0538 | 665 | 574.5816 | 176 | 5.268e-05 | 770.1769 | 5.5475 | 961.6825 | 12908.4686 | 154.4839 | 10.5617 | 411.2355 | 1.4414 | 0.032907 | 0.00017897 | 0.49624 | 0.77979 | {03A33F3F-5506-459A-89E7-ACD76DFFDD38} | 42251101 | HOPLAND 1101 | 4626 | 38.9711 | -123.1134 | HOPLAND 11014626 | 315 | 318 | 78618.1891 | 49646.9813 | 28971.2078 | 40127.548 | 18922.3364 | 0.031498 | 0.0092716 | 1.3577 | 3.7784 | 1491 | 5.7917 | 399 | 0 | 0 | 24.9341 | 1092 | 0
Sierra | 5265 | 336 | 582.5949 | 1145 | 909.6429 | 112 | 7.2373e-05 | 467.9316 | 15.1931 | 72.089 | 312.1037 | 10.8951 | 16.0398 | 105.4061 | 1.2683 | 0.032801 | 0.00056678 | 0.29345 | 0.64047 | {9E584244-489D-49B0-8EC4-8B40DD374169} | 152561103 | PENRYN 1103 | 51658 | 38.8547 | -121.1505 | PENRYN 110351658 | 187 | 145 | 22936.6149 | 14037.6097 | 8899.0053 | 12333.3131 | 8390.1455 | 0.063479 | 0.0081058 | 1.7339 | 10.2232 | 716 | 3.6738 | 400 | 0 | 0 | 7.6636 | 640 | 0
Central Valley | 3279 | 113 | 178.8636 | 433 | 313.9264 | 103 | 5.3229e-05 | 566.4036 | 11.5682 | 253.4587 | 1756.075 | 42.8779 | 12.6293 | 294.8594 | 1.4914 | 0.032753 | 0.00027581 | 0.26097 | 0.56976 | {3D247DD8-C725-4A26-BE65-60FA26890CB2} | 254421103 | OAKHURST 1103 | 10570 | 37.3708 | -119.633 | OAKHURST 110310570 | 129 | 112 | 24532.8722 | 15685.0936 | 8847.7786 | 15685.0936 | 8847.7786 | 0.028408 | 0.0054826 | 1.5829 | 4.2039 | 1185 | 3.3736 | 401 | 0 | 0 | 9.7463 | 839 | 0
North Coast | 3432 | 188 | 300.6509 | 525 | 389.5273 | 134 | 8.3306e-05 | 506.9242 | 2.6209 | 880.5887 | 6535.4578 | 38.9419 | 8.4421 | 800.7203 | 1.5484 | 0.03275 | 0.00015827 | 0.3581 | 0.77184 | {F5CA881C-11A8-4857-9165-F7C1423FEF9F} | 43141103 | MIDDLETOWN 1103 | 830 | 38.7561 | -122.6052 | MIDDLETOWN 1103830 | 254 | 187 | 83433.1222 | 62352.3339 | 21080.7883 | 40504.507 | 12641.1256 | 0.021208 | 0.011163 | 1.5992 | 3.9179 | 1550 | 4.3884 | 402 | 0 | 0 | 25.1683 | 513 | 0
Sierra | 6968 | 64 | 164.4469 | 323 | 247.1262 | 78 | 6.64e-05 | 451.4722 | 114.4456 | 349.5346 | 1928.6731 | 440.6016 | 13.1199 | 323.3325 | 1.2488 | 0.032553 | 0.0040496 | 0.19814 | 0.66544 | {398A55C4-A233-41E8-986A-9CEE99885341} | 153612105 | CLARKSVILLE 2105 | 75884 | 38.6553 | -121.0511 | CLARKSVILLE 210575884 | 132 | 73 | 24976.812 | 18035.3275 | 6941.4845 | 17165.4943 | 6941.4845 | 0.31587 | 0.0051792 | 2.5695 | 4.141 | 58 | 2.5391 | 403 | 0 | 0 | 10.6661 | 1240 | 0
North Coast | 1782 | 995 | 1334.4846 | 1767 | 1787.86 | 247 | 6.3248e-05 | 470.1991 | 3.7735 | 196.8119 | 2393.7681 | 19.571 | 2.9542 | 146.1327 | 1.3354 | 0.032468 | 0.00016479 | 0.5631 | 0.74641 | {EFFBC73B-5CF0-4391-8D52-00A9D7379A46} | 42821101 | CLOVERDALE 1101 | 112 | 38.8021 | -123.0182 | CLOVERDALE 1101112 | 444 | 1077 | 99513.9079 | 43621.7134 | 55892.1945 | 30254.9758 | 14059.7954 | 0.040704 | 0.015622 | 1.3412 | 7.1538 | 1532 | 8.0196 | 404 | 0 | 0 | 18.7996 | 812 | 0
Bay Area | 5193 | 19 | 23.473 | 73 | 49.8773 | 14 | 1.9449e-05 | 1321.3621 | 0.18787 | 86.71 | 260.8153 | 0.025807 | 16.0299 | 944.5892 | 1.5074 | 0.032454 | 1.5809e-05 | 0.26027 | 0.47062 | {61DFA90A-EDB2-455B-85E4-E1B3C2D31605} | 14241101 | SUNOL 1101 | MR169 | 37.5892 | -121.8701 | SUNOL 1101MR169 | 128 | 43 | 16562.7011 | 14971.4355 | 1591.2656 | 4614.9374 | 280.7859 | 0.00022132 | 0.00027229 | 1.2354 | 5.2143 | 2687 | 0.45435 | 405 | 0 | 0 | 2.8676 | 2014 | 0
Bay Area | 7752 | 1 | 1.2277 | 1 | 1.2277 | 1 | 1.5376e-05 | 2075.1509 | 25.0078 | 631.378 | 3258.5164 | 81.4883 | 22.9204 | 1152.3638 | 1.6416 | 0.031908 | 0.00038453 | 1 | 1 | {0F972632-618F-44CB-A965-3BB4F6195935} | 14662106 | TASSAJARA 2106 | circuit_breaker | 37.7998 | -121.9079 | TASSAJARA 2106circuit_breaker | 103 | 60 | 10639.7542 | 5000.9317 | 5638.8225 | 809.5956 | 1676.0663 | 0.00038453 | 1.5376e-05 | 1.2277 | 1 | 962 | 0.031908 | 406 | 0 | 0 | 0.50306 | 2692 | 0
Bay Area | 7037 | 154 | 252.3196 | 1226 | 900.4035 | 111 | 6.4226e-05 | 581.9439 | 2.4437 | 85.728 | 370.8161 | 2.3516 | 9.7497 | 252.5462 | 1.1899 | 0.031745 | 9.4956e-05 | 0.12561 | 0.28023 | {B814E637-1BB9-4F04-B0A4-F99C92D5342E} | 14232108 | SAN RAMON 2108 | circuit_breaker | 37.745 | -121.9376 | SAN RAMON 2108circuit_breaker | 175 | 159 | 28492.3846 | 15307.4292 | 13184.9554 | 13911.3335 | 13074.7692 | 0.01054 | 0.0071291 | 1.6384 | 11.045 | 1881 | 3.5237 | 407 | 0 | 0 | 8.6441 | 2748 | 0
North Coast | 5749 | 225 | 372.5213 | 441 | 456.7112 | 80 | 5.7404e-05 | 538.4672 | 2.1161 | 307.4969 | 5208.024 | 63.8391 | 12.0858 | 158.8319 | 1.2737 | 0.031715 | 9.3708e-05 | 0.5102 | 0.81566 | {CE237446-8B77-4B6F-A151-0796DF2727A1} | 43211101 | HARTLEY 1101 | 1306 | 39.0609 | -122.9322 | HARTLEY 11011306 | 187 | 142 | 31619.325 | 20418.473 | 11200.852 | 15400.0788 | 8155.67 | 0.0074966 | 0.0045923 | 1.6557 | 5.5125 | 1887 | 2.5372 | 408 | 0 | 0 | 9.5692 | 57 | 0
North Valley | 9280 | 19 | 28.6066 | 38 | 34.9124 | 13 | 6.1601e-05 | 615.9563 | 0.059894 | 1693.1371 | 6767.0807 | 0.43157 | 2.0157 | 1686.1767 | 1.6431 | 0.031674 | 1.7141e-05 | 0.5 | 0.81938 | {CE87ED54-B441-462F-AE1C-C4DF9A1FDFBB} | 103461102 | PANORAMA 1102 | 1632 | 40.4045 | -122.1217 | PANORAMA 11021632 | 23 | 17 | 14347.7308 | 13751.6318 | 596.0991 | 13751.6318 | 596.0991 | 0.00022283 | 0.00080081 | 1.5056 | 2.9231 | 2664 | 0.41176 | 409 | 0 | 0 | 8.5449 | 1257 | 0
Sierra | 6966 | 2 | 5.2733 | 12 | 9.8307 | 2 | 1.4425e-05 | 2192.6381 | 25.8402 | 105.6374 | 410.434 | 10.6057 | 28.9115 | 1620.1892 | 1.9115 | 0.031628 | 0.00015016 | 0.16667 | 0.53641 | {463CEDCD-A864-4BE7-A495-4562C479EEC4} | 63642113 | PEABODY 2113 | circuit_breaker | 38.2855 | -121.9704 | PEABODY 2113circuit_breaker | 103 | 67 | 12520.9952 | 9790.3302 | 2730.665 | 1530.5409 | 310.0206 | 0.00030032 | 2.8849e-05 | 2.6367 | 6 | 1591 | 0.063256 | 410 | 0 | 0 | 0.95103 | 158 | 0
Central Valley | 6091 | 56 | 82.5722 | 145 | 120.1323 | 41 | 7.6755e-05 | 405.9463 | 55.0319 | 393.0595 | 2626.8666 | 298.2998 | 12.5448 | 261.6162 | 1.2912 | 0.031508 | 0.0017972 | 0.38621 | 0.68734 | {79D3DE13-EDFE-4798-9C48-8D9438D496D5} | 162161101 | ELECTRA 1101 | 1238 | 38.3572 | -120.7593 | ELECTRA 11011238 | 170 | 388 | 26947.2988 | 11276.5469 | 15670.7519 | 5695.7641 | 2446.8284 | 0.073686 | 0.0031469 | 1.4745 | 3.5366 | 196 | 1.2918 | 411 | 0 | 0 | 3.5392 | 1091 | 0
North Coast | 3175 | 1923 | 2589.1202 | 4267 | 3848.1096 | 425 | 8.7693e-05 | 529.1724 | 13.0862 | 215.2246 | 1841.6535 | 90.2822 | 9.1903 | 157.2873 | 1.2025 | 0.031347 | 0.00062812 | 0.45067 | 0.67283 | {82FFCF9A-29C9-4CD0-A5CE-AFFBFF95F55A} | 42561107 | FULTON 1107 | 214 | 38.5031 | -122.7355 | FULTON 1107214 | 490 | 506 | 86068.3292 | 48113.355 | 37954.9742 | 48113.355 | 37954.9742 | 0.26695 | 0.037269 | 1.3464 | 10.04 | 642 | 13.3226 | 412 | 0 | 0 | 29.8962 | 1348 | 0
North Coast | 3347 | 6 | 18.8887 | 17 | 23.1294 | 10 | 5.6693e-05 | 639.1239 | 17.5215 | 2187.6669 | 8905.5914 | 234.9781 | 13.4854 | 390.7253 | 1.2635 | 0.031337 | 0.00075654 | 0.35294 | 0.81665 | {4B1C4FCD-287E-4417-8568-2D11E983B37F} | 42271105 | COTATI 1105 | 616 | 38.3102 | -122.8518 | COTATI 1105616 | 248 | 281 | 70168.4428 | 49321.001 | 20847.4418 | 2435.445 | 2413.2035 | 0.0075654 | 0.00056693 | 3.1481 | 1.7 | 529 | 0.31337 | 413 | 0 | 0 | 1.5133 | 334 | 0
Central Valley | 8781 | 19 | 36.2761 | 140 | 78.8247 | 52 | 2.3838e-05 | 1331.8405 | 18.5145 | 1638.1005 | 16602.2179 | 1003.0518 | 6.4587 | 1127.9384 | 1.7761 | 0.03133 | 0.00019177 | 0.13571 | 0.46021 | {C6F77565-3ECF-49F4-A49E-50D716B67BE9} | 252192105 | BEAR VALLEY 2105 | 9570 | 37.7156 | -120.2026 | BEAR VALLEY 21059570 | 78 | 58 | 20050.174 | 12951.7997 | 7098.3743 | 12951.7997 | 7098.3743 | 0.0099721 | 0.0012396 | 1.9093 | 2.6923 | 1443 | 1.6291 | 414 | 0 | 0 | 8.0479 | 168 | 0
North Coast | 9323 | 972 | 1905.5172 | 1054 | 1941.5118 | 91 | 0.00029378 | 99.5798 | 0.29037 | 149.7419 | 2248.8447 | 2.1119 | 0.21042 | 20.6969 | 1.0766 | 0.031305 | 0.0001902 | 0.9222 | 0.98146 | {BF5AD074-5FDE-42FF-9EE4-EC1E7EF14392} | 192221102 | GARBERVILLE 1102 | 56048 | 40.1477 | -124.0196 | GARBERVILLE 110256048 | 32 | 13 | 9253.7445 | 7998.8346 | 1254.9099 | 7998.8346 | 1254.9099 | 0.017308 | 0.026734 | 1.9604 | 11.5824 | 1450 | 2.8488 | 415 | 0 | 0 | 4.9702 | 297 | 0
North Coast | 5213 | 663 | 1078.7348 | 1764 | 1624.5479 | 200 | 0.00020039 | 202.0841 | 2.2084 | 264.2488 | 3066.7039 | 11.6897 | 2.7097 | 98.9463 | 1.175 | 0.031247 | 0.00027998 | 0.37585 | 0.66402 | {221BC5D9-51C0-467D-BFB7-19AAD7C5E6CD} | 192221102 | GARBERVILLE 1102 | 4744 | 40.2786 | -124.2442 | GARBERVILLE 11024744 | 212 | 265 | 42826.3406 | 32668.2317 | 10158.1089 | 26935.3901 | 7920.6505 | 0.055995 | 0.040078 | 1.6271 | 8.82 | 1177 | 6.2493 | 416 | 0 | 0 | 16.7369 | 5 | 0
Central Valley | 2206 | 38 | 98.6815 | 166 | 132.7997 | 28 | 9.3101e-05 | 459.5849 | 3.3111 | 13.2324 | 62.5532 | 1.3337 | 10.1916 | 247.0461 | 1.1666 | 0.031244 | 0.00013165 | 0.22892 | 0.74309 | {6748E8F4-5236-4133-9E21-482CCE2EC069} | 162991103 | CORRAL 1103 | 13474 | 38.1118 | -120.8661 | CORRAL 110313474 | 153 | 327 | 29718.9933 | 11606.5963 | 18112.3971 | 3896.5378 | 7338.3067 | 0.0036861 | 0.0026068 | 2.5969 | 5.9286 | 1693 | 0.87484 | 417 | 0 | 0 | 2.4212 | 1035 | 0
Sierra | 5557 | 281 | 385.5924 | 519 | 495.3762 | 51 | 0.00012888 | 885.5324 | 11.9209 | 766.5823 | 10182.7037 | 282.0473 | 1.9192 | 349.9696 | 1.6552 | 0.10861 | 0.00083773 | 0.54143 | 0.77838 | {B35DE979-0877-4DCD-A99D-B482E8F19A15} | 103201102 | CHALLENGE 1102 | 1064 | 39.482 | -121.2419 | CHALLENGE 11021064 | 266 | 224 | 47056.516 | 32164.5669 | 14891.9492 | 32164.5669 | 14891.9492 | 0.042724 | 0.0065731 | 1.3722 | 10.1765 | 478 | 5.5392 | 418 | 0 | 0 | 19.9861 | 484 | 0
North Valley | 5557 | 1456 | 2141.343 | 2922 | 2785.7249 | 244 | 0.00012038 | 127.0101 | 78.0322 | 1445.6624 | 22765.8833 | 3042.5615 | 1.7462 | 59.648 | 1.1505 | 0.015 | 0.003859 | 0.49829 | 0.76868 | {B35DE979-0877-4DCD-A99D-B482E8F19A15} | 103201102 | CHALLENGE 1102 | 1064 | 39.482 | -121.2419 | CHALLENGE 11021064 | 266 | 224 | 47056.516 | 32164.5669 | 14891.9492 | 32164.5669 | 14891.9492 | 0.94159 | 0.029373 | 1.4707 | 11.9754 | 65 | 3.6599 | 418 | 0 | 0 | 19.9861 | 1631 | 0
North Coast | 1014 | 1449 | 2367.312 | 2336 | 2817.438 | 202 | 0.00026101 | 115.2856 | 3.164 | 315.4758 | 7257.4421 | 65.9063 | 0.82635 | 24.6163 | 1.1075 | 0.031073 | 0.00055737 | 0.62029 | 0.84024 | {FBCD7012-56B0-4DB8-BFD1-768DDA012D1B} | 192401101 | HOOPA 1101 | 3290 | 41.3028 | -123.537 | HOOPA 11013290 | 236 | 210 | 27125.952 | 21820.8937 | 5305.0583 | 21820.8937 | 5305.0583 | 0.11259 | 0.052724 | 1.6338 | 11.5644 | 728 | 6.2767 | 419 | 0 | 0 | 13.5589 | 316 | 0
North Valley | 5882 | 31 | 46.4278 | 273 | 139.4264 | 40 | 5.1424e-05 | 650.8815 | 71.4673 | 383.6209 | 1880.9561 | 332.9127 | 16.509 | 305.6625 | 1.4423 | 0.030883 | 0.0014766 | 0.11355 | 0.33299 | {4FF91FEF-C966-4E36-B08B-C812EFC4BE16} | 103261101 | ANDERSON 1101 | circuit_breaker | 40.4497 | -122.3048 | ANDERSON 1101circuit_breaker | 253 | 902 | 45875.9485 | 14514.7271 | 31361.2214 | 4993.2396 | 5086.6229 | 0.059065 | 0.002057 | 1.4977 | 6.825 | 251 | 1.2353 | 420 | 0 | 0 | 3.1027 | 196 | 0
Sierra | 6311 | 4 | 7.7799 | 15 | 10.1274 | 7 | 2.8644e-05 | 1072.051 | 5.1662 | 3806.234 | 26741.8667 | 275.2669 | 10.4744 | 1926.1214 | 1.9709 | 0.03067 | 6.9398e-05 | 0.26667 | 0.7682 | {44D6ED2F-777A-4FEB-A593-3F9A2FF8D4A7} | 62081104 | ARBUCKLE 1104 | 47282 | 38.9512 | -122.062 | ARBUCKLE 110447282 | 115 | 103 | 26450.0122 | 19082.1088 | 7367.9034 | 3612.2461 | 1696.1957 | 0.00048578 | 0.00020051 | 1.945 | 2.1429 | 2062 | 0.21469 | 421 | 0 | 0 | 2.2445 | 543 | 0
Central Valley | 3215 | 15 | 20.9849 | 200 | 90.4922 | 31 | 6.2199e-05 | 556.4901 | 9.8241 | 119.6666 | 666.5912 | 22.4112 | 7.6983 | 72.8108 | 1.1437 | 0.03055 | 0.00031829 | 0.075 | 0.2319 | {2CDF7848-B063-4FC4-9C52-AE29AA49D3FF} | 254421101 | OAKHURST 1101 | circuit_breaker | 37.322 | -119.6343 | OAKHURST 1101circuit_breaker | 122 | 87 | 9005.6506 | 4768.9067 | 4236.7439 | 3669.1128 | 3595.9802 | 0.0098669 | 0.0019282 | 1.399 | 6.4516 | 1082 | 0.94705 | 422 | 0 | 0 | 2.2799 | 60 | 0
Central Valley | 5210 | 137 | 275.8999 | 357 | 338.4326 | 103 | 3.6251e-05 | 833.7524 | 19.1732 | 1460.8962 | 10083.2832 | 325.5025 | 7.0717 | 1009.5408 | 1.7104 | 0.030547 | 0.00022907 | 0.38375 | 0.81523 | {2D0A47C1-BF15-45C3-84C2-EF93E7A58095} | 252192105 | BEAR VALLEY 2105 | 11210 | 37.7228 | -120.2741 | BEAR VALLEY 210511210 | 184 | 132 | 39622.712 | 27422.5497 | 12200.1623 | 27422.5497 | 12200.1623 | 0.023594 | 0.0037338 | 2.0139 | 3.466 | 1312 | 3.1464 | 423 | 0 | 0 | 17.0396 | 1699 | 0
Bay Area | 4284 | 482 | 672.396 | 957 | 961.3293 | 96 | 0.00011516 | 284.3914 | 1.038 | 53.2414 | 680.5904 | 3.3076 | 1.5721 | 33.7314 | 1.1321 | 0.030538 | 0.0001163 | 0.50366 | 0.69944 | {3F9D2397-C923-47B2-B02D-BB46163B7124} | 42711102 | CALISTOGA 1102 | 769230 | 38.5678 | -122.5383 | CALISTOGA 1102769230 | 229 | 219 | 49354.0336 | 27488.654 | 21865.3796 | 16210.9352 | 14440.1129 | 0.011165 | 0.011055 | 1.395 | 9.9688 | 1768 | 2.9316 | 424 | 0 | 0 | 10.073 | 2614 | 0
North Valley | 903 | 12 | 14.9943 | 90 | 38.8105 | 23 | 3.5154e-05 | 966.9441 | 6.9287 | 332.5888 | 1369.2105 | 18.3254 | 13.9902 | 1056.8117 | 1.5706 | 0.030534 | 0.00012524 | 0.13333 | 0.38635 | {BFF4B959-67E4-4578-A961-731179E6F4E2} | 103541104 | RED BLUFF 1104 | 1630 | 40.2645 | -122.2255 | RED BLUFF 11041630 | 231 | 314 | 41658.3318 | 22734.8037 | 18923.5281 | 3396.4013 | 649.9233 | 0.0028804 | 0.00080854 | 1.2495 | 3.913 | 1723 | 0.70229 | 425 | 0 | 0 | 2.1104 | 1015 | 0
Sierra | 6478 | 8 | 27.2073 | 47 | 38.6805 | 17 | 3.8352e-05 | 803.7606 | 0.9753 | 645.3597 | 3324.5001 | 12.299 | 2.9473 | 1171.861 | 1.5402 | 0.030509 | 3.922e-05 | 0.17021 | 0.70338 | {3FFCF8AB-2F3C-40D6-BE9B-68EE284722AE} | 62881105 | MAXWELL 1105 | 3008 | 39.276 | -122.2733 | MAXWELL 11053008 | 68 | 61 | 26134.778 | 24475.225 | 1659.553 | 5862.1498 | 418.2875 | 0.00066674 | 0.00065198 | 3.4009 | 2.7647 | 2353 | 0.51865 | 426 | 0 | 0 | 3.6426 | 2354 | 0
North Coast | 4180 | 1074 | 1395.8808 | 1935 | 1898.1982 | 198 | 0.0001093 | 258.2386 |  |  |  |  | 2.1627 | 31.8418 | 1.1208 | 0.030178 | 0.0001093 | 0.55504 | 0.73537 | {E3F69DF5-8A62-4068-9DEE-C082DBE7414E} | 42751113 | FITCH MOUNTAIN 1113 | 4566 | 38.6063 | -122.8864 | FITCH MOUNTAIN 11134566 | 243 | 313 | 56471.943 | 27995.22 | 28476.723 | 18477.8969 | 14246.0865 | 0.021641 | 0.021641 | 1.2997 | 9.7727 | 1806 | 5.9751 | 427 | 0 | 0 | 11.4816 | 1108 | 0
North Valley | 1463 | 557 | 1061.098 | 1615 | 1451.4751 | 180 | 0.00010142 | 348.3252 | 15.2311 | 112.8087 | 774.3775 | 50.8276 | 14.7741 | 94.447 | 1.0807 | 0.030164 | 0.00081485 | 0.34489 | 0.73105 | {2473E4CF-72E3-4517-88B6-37E3090DCE92} | 103561101 | STILLWATER 1101 | 48950 | 40.7038 | -122.3364 | STILLWATER 110148950 | 260 | 286 | 34867.5311 | 20085.728 | 14781.8032 | 20085.728 | 14781.8032 | 0.14667 | 0.018256 | 1.905 | 8.9722 | 491 | 5.4295 | 428 | 0 | 0 | 12.4807 | 2605 | 0
North Coast | 7617 | 1017 | 1534.8295 | 1128 | 1591.2107 | 116 | 0.00015029 | 207.0371 | 39.253 | 408.6047 | 5220.1835 | 871.6782 | 6.3182 | 98.8593 | 1.228 | 0.029975 | 0.002447 | 0.9016 | 0.96457 | {72556B33-F33B-4E33-8959-39723007B093} | 42661103 | WILLITS 1103 | 826 | 39.4204 | -123.3599 | WILLITS 1103826 | 160 | 212 | 23989.6466 | 12450.1328 | 11539.5138 | 12450.1328 | 11539.5138 | 0.28385 | 0.017434 | 1.5092 | 9.7241 | 131 | 3.4771 | 429 | 0 | 0 | 7.7362 | 1784 | 0
North Valley | 7739 | 0 | 0 | 3 | 0.64023 | 3 | 2.0719e-05 | 1440.5856 | 7.2673 | 5697.167 | 32985.5742 | 244.4115 | 14.2684 | 2422.7322 | 1.7832 | 0.029822 | 6.3038e-05 | 0 | 0 | {097280CB-BBAB-443B-A213-61E2653EB02B} | 103331102 | CORNING 1102 | 1900 | 39.9429 | -122.2177 | CORNING 11021900 | 151 | 87 | 37849.9256 | 29783.4957 | 8066.4299 | 3377.7597 | 143.2344 | 0.00018912 | 6.2156e-05 |  | 1 | 2111 | 0.089467 | 430 | 0 | 0 | 2.0988 | 418 | 0
North Coast | 6662 | 2 | 5.8611 | 2 | 5.8611 | 2 | 4.2902e-05 | 681.0971 | 2.3515 | 442.6015 | 2283.2075 | 34.4093 | 16.1007 | 535.755 | 1.3673 | 0.029761 | 7.1145e-05 | 1 | 1 | {D6A4485E-AC24-4E5F-8B68-E6B52EAE7CCB} | 42631108 | PETALUMA C 1108 | 208 | 38.2261 | -122.7213 | PETALUMA C 1108208 | 119 | 105 | 34108.4807 | 19951.8799 | 14156.6007 | 19951.8799 | 14156.6007 | 0.00014229 | 8.5804e-05 | 2.9305 | 1 | 2048 | 0.059522 | 431 | 0 | 0 | 12.3975 | 1079 | 0
Central Coast | 2407 | 259 | 747.5499 | 451 | 843.7731 | 69 | 1.6788e-05 | 1842.8286 | 12.8649 | 578.6636 | 3199.7409 | 104.0701 | 31.8146 | 329.3733 | 1.3603 | 0.029387 | 0.00014108 | 0.57428 | 0.88596 | {EB029C6B-1104-4127-A12F-6B1C6DB20B5A} | 182631103 | SAN LUIS OBISPO 1103 | 42344 | 35.2316 | -120.6362 | SAN LUIS OBISPO 110342344 | 193 | 215 | 30153.5443 | 17394.6877 | 12758.8566 | 14174.6452 | 11562.9101 | 0.0097347 | 0.0011584 | 2.8863 | 6.5362 | 1629 | 2.0277 | 432 | 0 | 0 | 8.8077 | 1033 | 0
Bay Area | 4559 | 1627 | 2745.5274 | 2954 | 3538.1265 | 201 | 0.00012119 | 255.1232 | 2.812 | 56.0173 | 701.9661 | 5.7301 | 1.3501 | 19.659 | 1.102 | 0.029353 | 0.00023675 | 0.55078 | 0.77598 | {49BFB9F2-5C6B-4B7C-8CFC-569E7EA29701} | 43432104 | SILVERADO 2104 | 78268 | 38.5534 | -122.4562 | SILVERADO 210478268 | 238 | 359 | 44682.0804 | 19338.5201 | 25343.5603 | 19338.5201 | 25343.5603 | 0.047587 | 0.024359 | 1.6875 | 14.6965 | 1289 | 5.9 | 433 | 0 | 0 | 12.0164 | 1973 | 0
North Coast | 4955 | 271 | 388.8741 | 645 | 562.5945 | 152 | 8.0194e-05 | 333.5327 | 1.128 | 429.7678 | 5484.1862 | 16.2697 | 2.189 | 212.705 | 1.2739 | 0.02926 | 8.7628e-05 | 0.42016 | 0.69122 | {1642E076-5F84-4CD5-A49F-E61735A3F10D} | 42601101 | PHILO 1101 | 3700 | 38.9969 | -123.357 | PHILO 11013700 | 138 | 89 | 40113.5488 | 29050.7038 | 11062.845 | 29050.7038 | 11062.845 | 0.013319 | 0.012189 | 1.435 | 4.2434 | 1927 | 4.4475 | 434 | 0 | 0 | 18.0513 | 2435 | 0
Sierra | 4809 | 404 | 564.7916 | 1336 | 951.3096 | 186 | 8.9981e-05 | 337.6903 | 6.0584 | 79.4472 | 543.0485 | 12.5834 | 8.4135 | 76.5764 | 1.2254 | 0.029177 | 0.0002434 | 0.3024 | 0.5937 | {EEAC938D-675B-4361-87B7-7942FA5DF8E7} | 153132105 | NARROWS 2105 | 2748 | 39.2081 | -121.2033 | NARROWS 21052748 | 440 | 302 | 52721.117 | 31525.9218 | 21195.1952 | 21028.293 | 17121.314 | 0.045272 | 0.016736 | 1.398 | 7.1828 | 1269 | 5.427 | 435 | 0 | 0 | 13.0664 | 2576 | 0
North Valley | 3510 | 1189 | 1577.2986 | 2603 | 2222.0356 | 441 | 0.00014429 | 222.7255 | 8.0633 | 959.5578 | 14795.895 | 365.6207 | 4.3862 | 171.242 | 1.1835 | 0.029093 | 0.00060754 | 0.45678 | 0.70984 | {578FE3D8-350C-4FA5-8070-C7453CE4838E} | 103321101 | CEDAR CREEK 1101 | 1608 | 40.7859 | -121.9488 | CEDAR CREEK 11011608 | 300 | 234 | 67094.8518 | 53533.2272 | 13561.6246 | 53533.2272 | 13561.6246 | 0.26793 | 0.063632 | 1.3266 | 5.9025 | 661 | 12.83 | 436 | 0 | 0 | 33.264 | 1134 | 0
Sierra | 3858 | 20 | 60.3618 | 227 | 158.1329 | 33 | 3.9285e-05 | 709.0765 | 14.1097 | 60.5717 | 432.771 | 44.3647 | 12.864 | 306.5085 | 1.3574 | 0.02904 | 0.00041744 | 0.088106 | 0.38172 | {4372CAAD-3581-4B8A-AB27-A49D177EEFCE} | 63801105 | JAMESON 1105 | 9472 | 38.2486 | -122.1207 | JAMESON 11059472 | 131 | 131 | 18375.9973 | 11815.4027 | 6560.5946 | 3577.3351 | 1856.0875 | 0.013776 | 0.0012964 | 3.0181 | 6.8788 | 915 | 0.95833 | 437 | 0 | 0 | 2.2229 | 590 | 0
North Coast | 7546 | 1424 | 2026.2401 | 2060 | 2371.1794 | 341 | 7.9152e-05 | 366.6565 | 0.63212 | 274.6792 | 2981.046 | 10.4247 | 0.83682 | 191.6036 | 1.4066 | 0.028957 | 6.4465e-05 | 0.69126 | 0.85453 | {CD516753-E346-488C-8A28-4021B3A7E490} | 42891101 | GEYSERVILLE 1101 | 79788 | 38.6993 | -122.9708 | GEYSERVILLE 110179788 | 208 | 114 | 78233.136 | 67534.7693 | 10698.3666 | 63216.603 | 6747.0925 | 0.021983 | 0.026991 | 1.4229 | 6.0411 | 2098 | 9.8744 | 438 | 0 | 0 | 39.281 | 2525 | 0
Central Valley | 930 | 485 | 728.1394 | 2804 | 1694.3624 | 506 | 4.439e-05 | 720.9459 | 14.8907 | 177.4742 | 1368.7115 | 46.8915 | 14.9575 | 189.4183 | 1.4368 | 0.02894 | 0.00033256 | 0.17297 | 0.42974 | {43662797-F521-40C6-867F-8BCF69F03BE0} | 254452102 | MARIPOSA 2102 | 9590 | 37.4594 | -119.8997 | MARIPOSA 21029590 | 546 | 501 | 109969.815 | 58305.4261 | 51664.3888 | 58305.4261 | 51664.3888 | 0.16827 | 0.022461 | 1.5013 | 5.5415 | 1050 | 14.6437 | 439 | 0 | 0 | 36.2293 | 2749 | 0
Central Valley | 676 | 9 | 26.5801 | 27 | 34.7833 | 5 | 1.1065e-05 | 3298.7915 | 6.0662 | 840.6066 | 3180.5289 | 53.6059 | 37.4004 | 1862.0068 | 1.6606 | 0.02847 | 5.2323e-05 | 0.33333 | 0.76416 | {2BE56CEB-D130-4F64-98EE-3834ECE93155} | 252921110 | STONE CORRAL 1110 | 75288 | 36.4717 | -119.1604 | STONE CORRAL 111075288 | 403 | 496 | 72904.2223 | 47821.8592 | 25082.3631 | 1818.7235 | 446.3773 | 0.00026161 | 5.5327e-05 | 2.9533 | 5.4 | 2217 | 0.14235 | 440 | 0 | 0 | 1.1301 | 2638 | 0
Central Coast | 6713 | 45 | 102.3626 | 101 | 129.1144 | 23 | 3.1636e-05 | 825.425 | 0.70177 | 124.3138 | 588.5642 | 1.3695 | 13.4457 | 404.0035 | 1.2738 | 0.028239 | 2.3564e-05 | 0.44554 | 0.7928 | {2BB441D5-FA7B-41CB-B4C4-3BB6BA3702C5} | 182581105 | GOLDTREE 1105 | circuit_breaker | 35.32 | -120.6926 | GOLDTREE 1105circuit_breaker | 232 | 423 | 32216.5359 | 17789.9354 | 14426.6004 | 11071.7645 | 1422.7085 | 0.00054198 | 0.00072762 | 2.2747 | 4.3913 | 2551 | 0.6495 | 441 | 0 | 0 | 6.8797 | 2041 | 0
Bay Area | 64 | 1618 | 2522.7464 | 4937 | 4467.51 | 295 | 0.00011637 | 216.4112 | 2.1711 | 28.6059 | 468.2526 | 12.1476 | 1.1405 | 26.0052 | 1.2887 | 0.028175 | 0.00018466 | 0.32773 | 0.56469 | {61FE98E8-80EF-4BDB-989C-5A04CDB81F15} | 43021102 | WOODACRE 1102 | circuit_breaker | 38.0122 | -122.6538 | WOODACRE 1102circuit_breaker | 507 | 2003 | 130664.2108 | 34037.9756 | 96626.2351 | 33390.0506 | 95576.2155 | 0.054474 | 0.034329 | 1.5592 | 16.7356 | 1467 | 8.3115 | 442 | 0 | 0 | 20.7476 | 1110 | 0
Bay Area | 1019 | 828 | 1311.2389 | 1372 | 1523.7004 | 260 | 6.5549e-05 | 436.481 | 1.9272 | 249.6217 | 2134.2737 | 20.053 | 8.6033 | 383.2852 | 1.4106 | 0.028094 | 0.00010267 | 0.6035 | 0.86056 | {8A2A1266-ADC7-4421-959B-BF4457BE3602} | 43432104 | SILVERADO 2104 | 726 | 38.6151 | -122.4295 | SILVERADO 2104726 | 329 | 409 | 99162.2988 | 56572.5773 | 42589.7215 | 46009.8876 | 29043.5154 | 0.026693 | 0.017043 | 1.5836 | 5.2769 | 1842 | 7.3045 | 443 | 0 | 0 | 28.5892 | 2899 | 0
North Coast | 7563 | 737 | 1182.3639 | 1110 | 1308.3713 | 138 | 8.7835e-05 | 360.6471 | 3.128 | 181.3914 | 1538.5856 | 32.7069 | 5.6877 | 217.0194 | 1.4098 | 0.028043 | 0.00019354 | 0.66396 | 0.90369 | {D5E7700A-E368-40EA-8C45-A0E9AA2F6F54} | 43311102 | KONOCTI 1102 | 716 | 38.924 | -122.7205 | KONOCTI 1102716 | 127 | 69 | 37440.2847 | 27418.9124 | 10021.3723 | 21759.5686 | 5163.8409 | 0.026708 | 0.012121 | 1.6043 | 8.0435 | 1436 | 3.87 | 444 | 0 | 0 | 13.5208 | 1854 | 0
North Coast | 49 | 1019 | 1935.8702 | 1938 | 2282.3743 | 437 | 7.8825e-05 | 407.1195 | 82.6414 | 930.5719 | 8754.3255 | 1203.3687 | 9.9443 | 370.5787 | 1.4831 | 0.027919 | 0.0037664 | 0.5258 | 0.84818 | {20B5CFDD-9238-415D-BF03-7EE0B92100FE} | 43361103 | HIGHLANDS 1103 | 520 | 38.8827 | -122.5913 | HIGHLANDS 1103520 | 623 | 1028 | 138149.4665 | 75802.3106 | 62347.1559 | 75802.3106 | 62347.1559 | 1.6459 | 0.034447 | 1.8998 | 4.4348 | 66 | 12.2004 | 445 | 0 | 0 | 47.1014 | 1400 | 0
Central Coast | 6679 | 116 | 237.6666 | 216 | 291.9629 | 58 | 0.00010495 | 272.4342 | 6.2019 | 525.7595 | 3485.5522 | 59.9421 | 11.2269 | 380.9942 | 1.4424 | 0.027902 | 0.00041907 | 0.53704 | 0.81403 | {B7E378B5-33FB-4A39-80EA-4BDF85CF7D40} | 183052113 | TEMPLETON 2113 | 6055 | 35.4549 | -120.4869 | TEMPLETON 21136055 | 310 | 326 | 87605.9313 | 63807.832 | 23798.0993 | 63807.832 | 23798.0993 | 0.024306 | 0.0060873 | 2.0489 | 3.7241 | 912 | 1.6183 | 446 | 0 | 0 | 39.6483 | 2185 | 0
Central Valley | 4431 | 404 | 653.9833 | 3473 | 1736.848 | 827 | 2.8977e-05 | 977.3568 | 16.0171 | 1578.5062 | 13538.9946 | 368.2771 | 18.7403 | 658.3623 | 1.6946 | 0.027718 | 0.00022045 | 0.11633 | 0.37653 | {38642A96-8776-4716-B709-CC59463C3DA7} | 254452102 | MARIPOSA 2102 | 37288 | 37.4205 | -119.8772 | MARIPOSA 210237288 | 829 | 666 | 212726.8733 | 136885.5796 | 75841.2937 | 136885.5796 | 75841.2937 | 0.18231 | 0.023964 | 1.6188 | 4.1995 | 1341 | 22.9229 | 447 | 0 | 0 | 85.0567 | 1683 | 0
Central Valley | 3201 | 35 | 77.4301 | 181 | 122.7758 | 64 | 3.8744e-05 | 584.4173 | 3.9296 | 820.334 | 7137.0005 | 84.753 | 3.9931 | 349.6041 | 1.4711 | 0.027559 | 0.00012497 | 0.19337 | 0.63066 | {F72524F5-D5B1-4F6F-9F15-809009991306} | 252192105 | BEAR VALLEY 2105 | 9480 | 37.6317 | -120.1547 | BEAR VALLEY 21059480 | 131 | 59 | 25199.6753 | 19971.3977 | 5228.2776 | 19971.3977 | 5228.2776 | 0.0079981 | 0.0024796 | 2.2123 | 2.8281 | 1724 | 1.7638 | 448 | 0 | 0 | 12.4096 | 93 | 0
Central Valley | 6532 | 193 | 307.5106 | 1246 | 698.9669 | 293 | 4.7174e-05 | 591.1728 | 13.681 | 731.0252 | 7729.0301 | 223.6185 | 16.2707 | 420.1688 | 1.6242 | 0.02733 | 0.00032706 | 0.1549 | 0.43995 | {C88CD342-0019-4371-8FA7-CA6CF25A5380} | 254452102 | MARIPOSA 2102 | 1960 | 37.4586 | -119.9003 | MARIPOSA 21021960 | 288 | 249 | 65100.4989 | 39674.5223 | 25425.9765 | 39674.5223 | 25425.9765 | 0.095828 | 0.013822 | 1.5933 | 4.2526 | 1062 | 8.0077 | 449 | 0 | 0 | 24.6526 | 2369 | 0
Central Coast | 4009 | 71 | 116.8437 | 205 | 168.1425 | 49 | 3.7857e-05 | 870.7793 | 9.2536 | 185.2922 | 867.2822 | 21.3186 | 17.736 | 427.048 | 1.2754 | 0.027276 | 0.00016049 | 0.34634 | 0.69491 | {B0A0DAD0-3674-4CD8-8437-87CE246C1A79} | 183052113 | TEMPLETON 2113 | A60 | 35.4894 | -120.6389 | TEMPLETON 2113A60 | 130 | 102 | 21175.7158 | 14423.3233 | 6752.3925 | 10180.3906 | 4388.4633 | 0.0078642 | 0.001855 | 1.6457 | 4.1837 | 1544 | 1.3365 | 450 | 0 | 0 | 6.3258 | 1894 | 0
North Valley | 6409 | 108 | 156.858 | 317 | 230.8907 | 53 | 4.543e-05 | 691.0923 | 27.7059 | 1338.4197 | 7404.4819 | 381.5048 | 13.8036 | 416.285 | 1.29 | 0.0272 | 0.00049847 | 0.34069 | 0.67936 | {154C476C-5A31-47D9-B01B-5C020A5462D1} | 103091102 | CLARK ROAD 1102 | 81296 | 39.6478 | -121.6298 | CLARK ROAD 110281296 | 161 | 133 | 34481.0957 | 21924.1005 | 12556.9951 | 10798.5955 | 5952.0867 | 0.026419 | 0.0024078 | 1.4524 | 5.9811 | 788 | 1.4416 | 451 | 0 | 0 | 6.7099 | 299 | 0
Central Valley | 6188 | 133 | 273.9291 | 383 | 346.2956 | 115 | 2.9265e-05 | 997.0909 | 19.0043 | 241.8214 | 837.8923 | 29.7075 | 15.0993 | 149.2044 | 1.2817 | 0.027186 | 0.00026254 | 0.34726 | 0.79103 | {E473F3E7-4790-4E95-BFB6-2DFAB51C8E70} | 252811102 | MERCED FALLS 1102 | 38748 | 37.7018 | -120.3396 | MERCED FALLS 110238748 | 282 | 297 | 43267.9508 | 24704.6356 | 18563.3152 | 24704.6356 | 18563.3152 | 0.030192 | 0.0033655 | 2.0596 | 3.3304 | 1217 | 3.1264 | 452 | 0 | 0 | 15.3507 | 1808 | 0
Central Valley | 6535 | 104 | 217.4005 | 432 | 311.2808 | 126 | 2.9599e-05 | 1011.0641 | 40.8341 | 463.2757 | 2511.6404 | 183.3226 | 21.5383 | 149.2168 | 1.2734 | 0.027125 | 0.00059139 | 0.24074 | 0.69841 | {320BFDAF-F5A8-4096-BB62-ECF18634253B} | 163781704 | PEORIA 1704 | 11232 | 37.9376 | -120.6091 | PEORIA 170411232 | 291 | 496 | 55130.4727 | 27614.6759 | 27515.7968 | 19016.7925 | 17834.7804 | 0.074515 | 0.0037294 | 2.0904 | 3.4286 | 680 | 3.4178 | 453 | 0 | 0 | 11.8165 | 2262 | 0
Bay Area | 4898 | 424 | 635.6891 | 957 | 959.4659 | 62 | 8.7082e-05 | 314.6673 | 17.773 | 434.9315 | 7745.0947 | 341.0029 | 2.5936 | 68.9588 | 1.2443 | 0.027087 | 0.00061396 | 0.44305 | 0.66254 | {1ACD7F45-5073-4366-9697-A511E06B0768} | 43021101 | WOODACRE 1101 | 1456 | 38.0541 | -122.6917 | WOODACRE 11011456 | 66 | 75 | 13713.4893 | 6154.4242 | 7559.0652 | 6154.4242 | 7559.0652 | 0.038065 | 0.0053991 | 1.4993 | 15.4355 | 656 | 1.6794 | 454 | 0 | 0 | 3.8242 | 2669 | 0
Central Coast | 5449 | 22 | 55.8684 | 40 | 64.8243 | 8 | 1.3324e-05 | 1738.2593 | 13.1252 | 590.7591 | 2090.7489 | 38.2049 | 29.3634 | 554.1184 | 1.3747 | 0.026934 | 8.3499e-05 | 0.55 | 0.86184 | {3D42DADD-B930-4BCB-8FA8-10BD1514503A} | 83242111 | MORGAN HILL 2111 | XR186 | 37.1456 | -121.6707 | MORGAN HILL 2111XR186 | 321 | 351 | 41959.107 | 25686.8585 | 16272.2486 | 2744.6855 | 138.4815 | 0.00066799 | 0.00010659 | 2.5395 | 5 | 1961 | 0.21547 | 455 | 0 | 0 | 1.7055 | 1192 | 0
Bay Area | 3615 | 355 | 566.4263 | 714 | 762.5924 | 25 | 0.00012467 | 204.5499 | 0.20813 | 0.056121 | 0.0011099 | 8.5283e-07 | 1.0273 | 3.7345 | 0.82062 | 0.026675 | 9.5719e-05 | 0.4972 | 0.74276 | {480E1BDA-E928-4338-A7BA-DDA1B7A106EF} | 42031122 | ALTO 1122 | 1212 | 37.9258 | -122.5308 | ALTO 11221212 | 74 | 362 | 18359.3634 | 3797.0171 | 14562.3463 | 2589.3247 | 10088.3628 | 0.002393 | 0.0031168 | 1.5956 | 28.56 | 1874 | 0.66688 | 456 | 0 | 0 | 1.6089 | 907 | 0
North Coast | 8575 | 93 | 121.6819 | 158 | 153.0749 | 14 | 0.00012978 | 224.8704 | 5.342 | 40.2336 | 254.5429 | 1.9856 | 8.5501 | 97.4791 | 1.1421 | 0.026665 | 0.00054646 | 0.58861 | 0.79492 | {6605C9B9-1E01-4CAA-B9F4-139E3DFEC103} | 43141101 | MIDDLETOWN 1101 | 1314 | 38.7312 | -122.6231 | MIDDLETOWN 11011314 | 22 | 26 | 2040.9996 | 1494.2319 | 546.7677 | 1494.2319 | 530.0446 | 0.0076504 | 0.0018169 | 1.3084 | 11.2857 | 741 | 0.3733 | 457 | 0 | 0 | 0.92847 | 2873 | 0
Sierra | 6168 | 23 | 44.3514 | 41 | 52.1896 | 7 | 6.5623e-05 | 538.4184 | 0.96789 | 309.6973 | 2081.9556 | 6.4973 | 7.4741 | 364.2437 | 1.3138 | 0.026603 | 6.8878e-05 | 0.56098 | 0.84981 | {8E6B668B-C3B5-476E-8081-82E065E91883} | 63172101 | MADISON 2101 | 37082 | 38.8566 | -122.2123 | MADISON 210137082 | 238 | 247 | 45155.2748 | 29594.5517 | 15560.7232 | 1451.8754 | 1229.1003 | 0.00048214 | 0.00045936 | 1.9283 | 5.8571 | 2069 | 0.18622 | 458 | 0 | 0 | 0.90215 | 935 | 0
Sierra | 4047 | 1077 | 1780.663 | 4468 | 2986.565 | 411 | 0.00013918 | 206.605 | 8.4918 | 46.972 | 314.3006 | 7.9843 | 9.0413 | 57.6327 | 1.2074 | 0.026522 | 0.00059172 | 0.24105 | 0.59622 | {8CA8A29D-825E-4F83-82F2-58C55E66E077} | 153652109 | SHINGLE SPRINGS 2109 | circuit_breaker | 38.6593 | -120.9466 | SHINGLE SPRINGS 2109circuit_breaker | 580 | 557 | 78773.4916 | 44889.6263 | 33883.8652 | 43399.3801 | 32851.464 | 0.2432 | 0.057202 | 1.6534 | 10.871 | 679 | 10.9005 | 459 | 0 | 0 | 26.9671 | 827 | 0
North Coast | 6292 | 270 | 402.3284 | 655 | 591.8702 | 85 | 9.1257e-05 | 274.7602 | 2.4708 | 344.8639 | 6565.7703 | 35.3405 | 1.7241 | 48.1099 | 1.1754 | 0.026185 | 0.00013875 | 0.41221 | 0.67976 | {8E06DD08-111B-4D73-B845-1ABBADC77B32} | 42891101 | GEYSERVILLE 1101 | 37454 | 38.7047 | -122.9592 | GEYSERVILLE 110137454 | 174 | 105 | 32079.7363 | 19682.6267 | 12397.1096 | 10482.9729 | 8155.9463 | 0.011794 | 0.0077568 | 1.4901 | 7.7059 | 1636 | 2.2257 | 460 | 0 | 0 | 6.5138 | 544 | 0
North Valley | 3547 | 1897 | 3987.7976 | 3283 | 4655.6406 | 307 | 9.3492e-05 | 298.7898 | 145.943 | 5170.0033 | 158158.9598 | 32627.2225 | 0.76433 | 35.284 | 1.1038 | 0.02615 | 0.0055555 | 0.57783 | 0.85655 | {2D141325-C090-4FCF-8D95-50CB00DE9095} | 103751102 | BIG BEND 1102 | 1972 | 39.6444 | -121.4313 | BIG BEND 11021972 | 253 | 310 | 48758.1892 | 33902.4073 | 14855.7819 | 33902.4073 | 14855.7819 | 1.7055 | 0.028702 | 2.1022 | 10.6938 | 29 | 8.028 | 461 | 0 | 0 | 21.066 | 2539 | 0
Sierra | 4023 | 210 | 265.1737 | 235 | 275.7771 | 16 | 7.4727e-06 | 3708.4608 | 206.4227 | 2166.1303 | 13953.4132 | 4358.0137 | 52.1424 | 655.4161 | 1.7167 | 0.026066 | 0.00045964 | 0.89362 | 0.96155 | {CBB1E17F-BE5D-42E9-AB86-48D61CF7F4ED} | 63601104 | VACAVILLE 1104 | circuit_breaker | 38.3565 | -121.9805 | VACAVILLE 1104circuit_breaker | 117 | 386 | 19566.7097 | 4995.2075 | 14571.5022 | 1499.3098 | 411.2994 | 0.0073542 | 0.00011956 | 1.2627 | 14.6875 | 848 | 0.41706 | 462 | 0 | 0 | 0.93163 | 1822 | 0
North Coast | 5041 | 188 | 576.355 | 227 | 592.8277 | 83 | 5.6968e-05 | 417.9445 | 12.0636 | 1651.774 | 7885.612 | 257.7009 | 11.8786 | 305.143 | 1.1788 | 0.025913 | 0.00035774 | 0.82819 | 0.97221 | {D681E6AF-06CA-4983-B4FB-ED08B0DAD260} | 42271103 | COTATI 1103 | 132 | 38.2647 | -122.8057 | COTATI 1103132 | 216 | 164 | 62732.9904 | 40702.0776 | 22030.9128 | 40702.0776 | 22030.9128 | 0.029693 | 0.0047283 | 3.0657 | 2.7349 | 1001 | 2.1508 | 463 | 0 | 0 | 25.2911 | 1853 | 0
North Coast | 8339 | 268 | 270.4033 | 357 | 314.4826 | 78 | 0.00016278 | 150.6082 | 2.8081 | 768.0967 | 13241.1679 | 80.5687 | 1.0058 | 98.1548 | 1.1542 | 0.025891 | 0.00028633 | 0.7507 | 0.85984 | {3BB5B038-4064-4F43-B944-1BDE53135960} | 192461101 | BRIDGEVILLE 1101 | 69866 | 40.4693 | -123.7011 | BRIDGEVILLE 110169866 | 53 | 23 | 14027.5247 | 10521.7386 | 3505.7862 | 10521.7386 | 3505.7862 | 0.022334 | 0.012697 | 1.009 | 4.5769 | 1157 | 2.0195 | 464 | 0 | 0 | 6.5379 | 1609 | 0
North Coast | 6851 | 81 | 102.09 | 312 | 186.224 | 50 | 8.2254e-05 | 405.3018 | 4.6727 | 850.2686 | 10996.5337 | 172.8155 | 12.104 | 223.2812 | 1.3616 | 0.025801 | 0.00026239 | 0.25962 | 0.54821 | {0F086603-31D0-422E-BBA1-3A12831F4713} | 42871101 | UPPER LAKE 1101 | 472084 | 39.1456 | -122.9162 | UPPER LAKE 1101472084 | 97 | 109 | 24077.9703 | 11576.044 | 12501.9263 | 7182.4083 | 2822.8782 | 0.013119 | 0.0041127 | 1.2604 | 6.24 | 1218 | 1.29 | 465 | 0 | 0 | 4.4629 | 1244 | 0
Bay Area | 2773 | 543 | 860.1107 | 958 | 1050.6149 | 149 | 5.7342e-05 | 432.1395 | 1.6268 | 360.0566 | 2848.4099 | 15.3133 | 3.5477 | 569.4563 | 1.4713 | 0.025788 | 7.0305e-05 | 0.56681 | 0.81867 | {B06F68AD-C4A0-4C48-AC8B-ACB86AC8FCA9} | 43432104 | SILVERADO 2104 | 806 | 38.6169 | -122.4244 | SILVERADO 2104806 | 249 | 162 | 66122.818 | 52895.6546 | 13227.1635 | 29193.0346 | 8922.4069 | 0.010475 | 0.008544 | 1.584 | 6.4295 | 2055 | 3.8424 | 466 | 0 | 0 | 18.1397 | 1705 | 0
North Coast | 7532 | 286 | 432.4377 | 434 | 510.4991 | 44 | 0.00021072 | 143.229 | 0.99982 | 132.789 | 1210.7834 | 2.2668 | 0.40698 | 34.8151 | 1.1318 | 0.025728 | 0.00021436 | 0.65899 | 0.84709 | {4A1EC5D3-CF7E-4E3A-B115-9A4757B7DAC6} | 192311142 | FRUITLAND 1142 | 6064 | 40.2943 | -123.8195 | FRUITLAND 11426064 | 83 | 82 | 21625.1905 | 13612.899 | 8012.2914 | 9593.2152 | 7060.6858 | 0.009432 | 0.0092718 | 1.512 | 9.8636 | 1365 | 1.132 | 467 | 0 | 0 | 5.9609 | 881 | 0
North Valley | 5137 | 409 | 764.0876 | 1233 | 1026.9547 | 211 | 0.00010011 | 258.1915 | 10.3916 | 240.8335 | 2686.83 | 139.4762 | 9.3012 | 180.6133 | 1.2575 | 0.025716 | 0.00047215 | 0.33171 | 0.74403 | {2A2FAB19-EBE2-405E-9DCE-8FB9750FB831} | 103401101 | GIRVAN 1101 | 1636 | 40.5159 | -122.3824 | GIRVAN 11011636 | 303 | 218 | 41191.1792 | 29877.1164 | 11314.0628 | 24954.3397 | 10993.0784 | 0.099624 | 0.021124 | 1.8682 | 5.8436 | 821 | 5.4261 | 468 | 0 | 0 | 15.5059 | 1649 | 0
Bay Area | 7659 | 636 | 896.6119 | 1621 | 1416.2754 | 186 | 7.313e-05 | 370.0321 | 1.3912 | 102.7718 | 1062.1508 | 4.8439 | 3.102 | 151.8027 | 1.2559 | 0.025598 | 8.2639e-05 | 0.39235 | 0.63308 | {05AC1C5B-D6E1-429E-A072-263D6E199803} | 43432102 | SILVERADO 2102 | 58626 | 38.5071 | -122.4061 | SILVERADO 210258626 | 164 | 135 | 46940.5784 | 24429.8093 | 22510.7691 | 24429.8093 | 22510.7691 | 0.015371 | 0.013602 | 1.4098 | 8.7151 | 1966 | 4.7612 | 469 | 0 | 0 | 15.18 | 2800 | 0
North Valley | 4776 | 52 | 98.4736 | 490 | 212.748 | 131 | 4.7549e-05 | 630.477 | 3.9246 | 21.0624 | 74.1199 | 1.0953 | 18.469 | 100.1279 | 1.1465 | 0.025593 | 9.5926e-05 | 0.10612 | 0.46286 | {2E98A968-0F7D-44C0-B9F5-8D4D032F12CD} | 103541105 | RED BLUFF 1105 | 85632 | 40.19 | -122.2383 | RED BLUFF 110585632 | 301 | 243 | 34883.6018 | 23855.6356 | 11027.9663 | 20457.0684 | 8802.0472 | 0.012566 | 0.006229 | 1.8937 | 3.7405 | 1872 | 3.3527 | 470 | 0 | 0 | 12.7114 | 48 | 0
Central Coast | 2338 | 9 | 16.7985 | 86 | 54.2234 | 18 | 2.1289e-05 | 1194.8997 | 3.2837 | 150.5359 | 642.455 | 3.223 | 17.2566 | 670.6104 | 1.3024 | 0.025539 | 4.3171e-05 | 0.10465 | 0.3098 | {80BB619F-1520-4563-BF62-E97585F4D6B9} | 182631103 | SAN LUIS OBISPO 1103 | circuit_breaker | 35.2613 | -120.6347 | SAN LUIS OBISPO 1103circuit_breaker | 205 | 197 | 38575.2126 | 22526.7494 | 16048.4631 | 4883.612 | 4633.9069 | 0.00077707 | 0.00038321 | 1.8665 | 4.7778 | 2299 | 0.45971 | 471 | 0 | 0 | 3.0345 | 1832 | 0
Central Coast | 6264 | 216 | 297.9505 | 538 | 487.8195 | 61 | 5.1427e-05 | 659.219 | 1.2079 | 35.4748 | 103.7076 | 0.30016 | 15.3968 | 187.7766 | 1.3289 | 0.025489 | 5.6372e-05 | 0.40149 | 0.61078 | {D4E598FB-500D-4E86-913F-DD1E461E4E23} | 83242105 | MORGAN HILL 2105 | XR070 | 37.0427 | -121.6547 | MORGAN HILL 2105XR070 | 141 | 86 | 21044.7544 | 13816.8053 | 7227.9492 | 9521.4048 | 3423.9409 | 0.0034387 | 0.003137 | 1.3794 | 8.8197 | 2180 | 1.5548 | 472 | 0 | 0 | 5.9163 | 2225 | 0
Sierra | 749 | 1732 | 2763.8907 | 4357 | 3873.0745 | 588 | 7.6704e-05 | 364.4266 | 16.4295 | 489.1372 | 5157.0232 | 163.4672 | 8.577 | 143.8898 | 1.2878 | 0.025511 | 0.00063407 | 0.39752 | 0.71362 | {1FB07492-7817-4281-B458-54D457C1DE65} | 103191101 | BANGOR 1101 | 7446 | 39.3518 | -121.3275 | BANGOR 11017446 | 624 | 557 | 104276.5358 | 69879.8096 | 34396.7262 | 69879.8096 | 34396.7262 | 0.37283 | 0.045102 | 1.5958 | 7.4099 | 633 | 15.0002 | 473 | 0 | 0 | 43.4213 | 1907 | 0
Bay Area | 749 | 1 | 4.0491 | 7 | 6.3976 | 1 | 6.9326e-05 | 142.7997 |  |  |  |  | 5.9867 | 122.5323 | 1.542 | 0.0098998 | 6.9326e-05 | 0.14286 | 0.6329 | {1FB07492-7817-4281-B458-54D457C1DE65} | 103191101 | BANGOR 1101 | 7446 | 39.3518 | -121.3275 | BANGOR 11017446 | 624 | 557 | 104276.5358 | 69879.8096 | 34396.7262 | 69879.8096 | 34396.7262 | 6.9326e-05 | 6.9326e-05 | 4.0491 | 7 | 2064 | 0.0098998 | 473 | 0 | 0 | 43.4213 | 2038 | 0
Central Valley | 7470 | 32 | 60.5241 | 191 | 117.3752 | 47 | 3.0712e-05 | 873.2316 | 14.4128 | 530.0099 | 5018.4012 | 478.7902 | 17.9181 | 390.2266 | 1.5857 | 0.025339 | 0.00022165 | 0.16754 | 0.51565 | {88D20852-6A01-4C0A-B81E-35A0065BE6FB} | 254452101 | MARIPOSA 2101 | 97142 | 37.5066 | -120.0082 | MARIPOSA 210197142 | 54 | 49 | 13415.2676 | 7406.0615 | 6009.2061 | 7406.0615 | 6009.2061 | 0.010417 | 0.0014435 | 1.8914 | 4.0638 | 1338 | 1.1909 | 474 | 0 | 0 | 4.6019 | 119 | 0
Bay Area | 5878 | 1344 | 1892.323 | 2910 | 2789.7407 | 124 | 9.9103e-05 | 228.9384 | 9.5852 | 258.9601 | 3260.3733 | 121.2428 | 0.95133 | 29.0152 | 1.0835 | 0.025253 | 0.00050659 | 0.46186 | 0.67831 | {EDE87926-F33E-4FF5-A8C5-E53D4266C7FF} | 43292103 | PUEBLO 2103 | 78504 | 38.3469 | -122.3299 | PUEBLO 210378504 | 200 | 177 | 34643.0098 | 19482.7251 | 15160.2847 | 12406.3687 | 8433.4802 | 0.062817 | 0.012289 | 1.408 | 23.4677 | 782 | 3.1314 | 475 | 0 | 0 | 7.709 | 2137 | 0
North Coast | 7148 | 2019 | 3179.4618 | 3050 | 3733.2395 | 318 | 0.00014526 | 180.6567 | 6.3342 | 546.7194 | 10620.6347 | 182.1536 | 0.53639 | 39.157 | 1.157 | 0.025203 | 0.00055728 | 0.66197 | 0.85166 | {A0E5F0B2-0FDE-4EFD-91DF-F0E385B1FA8B} | 42751113 | FITCH MOUNTAIN 1113 | 6751 | 38.592 | -122.9622 | FITCH MOUNTAIN 11136751 | 161 | 157 | 53997.9402 | 35962.163 | 18035.7772 | 35962.163 | 18035.7772 | 0.17721 | 0.046192 | 1.5748 | 9.5912 | 729 | 8.0144 | 476 | 0 | 0 | 22.3458 | 685 | 0
Bay Area | 8719 | 995 | 1453.6581 | 1716 | 1865.9954 | 121 | 0.0001268 | 197.364 | 1.2217 | 61.2251 | 572.538 | 3.1862 | 2.0694 | 69.0185 | 1.1945 | 0.025136 | 0.00013965 | 0.57984 | 0.77903 | {58845AAB-F485-40BF-95E3-3DEA7E272B5E} | 42711101 | CALISTOGA 1101 | 89150 | 38.6092 | -122.5912 | CALISTOGA 110189150 | 128 | 119 | 23119.5087 | 15360.2828 | 7759.2259 | 15360.2828 | 7759.2259 | 0.016898 | 0.015342 | 1.461 | 14.1818 | 1633 | 3.0414 | 477 | 0 | 0 | 9.5444 | 367 | 0
Bay Area | 2102 | 2812 | 4113.934 | 4746 | 5189.424 | 474 | 0.0001156 | 209.3679 | 8.1266 | 260.7079 | 3853.7596 | 124.3115 | 3.816 | 70.5345 | 1.1799 | 0.025135 | 0.00052232 | 0.5925 | 0.79275 | {C2E51B1B-3D1A-41AD-8F70-366CE643D28F} | 42711101 | CALISTOGA 1101 | 736 | 38.5803 | -122.5979 | CALISTOGA 1101736 | 491 | 445 | 84934.2958 | 56743.887 | 28190.4087 | 56743.887 | 28190.4087 | 0.24758 | 0.054795 | 1.463 | 10.0127 | 772 | 11.914 | 478 | 0 | 0 | 35.259 | 293 | 0
Central Coast | 3119 | 453 | 819.5012 | 867 | 957.1422 | 290 | 4.8362e-05 | 427.6492 | 1.3225 | 1677.943 | 11612.6068 | 41.8916 | 8.37 | 1268.0192 | 1.5514 | 0.025091 | 5.4472e-05 | 0.52249 | 0.8562 | {7C7DB9EE-BC4D-48A6-99E0-8802DB262ED8} | 182562102 | CHOLAME 2102 | X06 | 35.7373 | -120.2882 | CHOLAME 2102X06 | 218 | 179 | 94539.7609 | 84987.8121 | 9551.9489 | 53331.3621 | 7351.9486 | 0.015797 | 0.014025 | 1.8091 | 2.9897 | 2198 | 7.2765 | 479 | 0 | 0 | 33.1386 | 711 | 0
Central Valley | 5912 | 203 | 392.7738 | 741 | 585.9564 | 129 | 2.4822e-05 | 1019.877 | 18.7672 | 824.1181 | 7702.7261 | 487.5348 | 18.804 | 456.9031 | 1.535 | 0.025012 | 0.00023476 | 0.27395 | 0.67031 | {31E3CA9D-D54E-4B12-BCD7-9DB740FF58FA} | 254151101 | AUBERRY 1101 | R2839 | 37.0368 | -119.4516 | AUBERRY 1101R2839 | 165 | 143 | 30008.3567 | 20609.1212 | 9399.2355 | 20609.1212 | 9399.2355 | 0.030284 | 0.003202 | 1.9348 | 5.7442 | 1299 | 3.2266 | 480 | 0 | 0 | 12.8059 | 1506 | 0
North Coast | 8745 | 620 | 1128.805 | 830 | 1224.0498 | 80 | 0.00023095 | 113.2612 | 1.4482 | 91.2475 | 668.9874 | 1.6208 | 0.19696 | 19.8337 | 1.089 | 0.024987 | 0.00029807 | 0.74699 | 0.92219 | {CF682344-0C1A-411D-B173-CAE04AD6EAA0} | 192311141 | FRUITLAND 1141 | 37410 | 40.3263 | -123.9227 | FRUITLAND 114137410 | 50 | 46 | 10500.5907 | 8875.6069 | 1624.9838 | 7642.4024 | 1299.6336 | 0.023845 | 0.018476 | 1.8207 | 10.375 | 1130 | 1.9989 | 481 | 0 | 0 | 4.7488 | 1024 | 0
Sierra | 7319 | 255 | 478.8608 | 1087 | 915.7286 | 114 | 4.62e-05 | 600.4411 | 4.2627 | 35.8722 | 213.2335 | 3.536 | 11.2727 | 372.5127 | 1.3138 | 0.025417 | 0.0001082 | 0.23459 | 0.52293 | {10AF2AF5-0312-4499-B6B7-F90BCDC56FEE} | 63801102 | JAMESON 1102 | 65516 | 38.2496 | -122.1606 | JAMESON 110265516 | 280 | 488 | 44601.527 | 18265.6782 | 26335.8488 | 12202.9885 | 15670.3248 | 0.012335 | 0.0052668 | 1.8779 | 9.5351 | 1814 | 2.8975 | 482 | 0 | 0 | 7.5826 | 2779 | 0
Bay Area | 7319 | 2 | 2.7172 | 29 | 18.6764 | 2 | 2.4544e-05 | 0.066431 | 0.045277 | 0.22239 | 0.069221 | 2.8463e-07 | 0.4646 | 0.04646 | 1 | 1.6305e-06 | 1.3052e-06 | 0.068966 | 0.14549 | {10AF2AF5-0312-4499-B6B7-F90BCDC56FEE} | 63801102 | JAMESON 1102 | 65516 | 38.2496 | -122.1606 | JAMESON 110265516 | 280 | 488 | 44601.527 | 18265.6782 | 26335.8488 | 12202.9885 | 15670.3248 | 2.6104e-06 | 4.9087e-05 | 1.3586 | 14.5 | 2874 | 3.2609e-06 | 482 | 0 | 0 | 7.5826 | 1782 | 0
North Coast | 2042 | 562 | 767.245 | 1497 | 1191.5935 | 280 | 7.7328e-05 | 253.7802 | 6.9123 | 825.9201 | 10889.3913 | 243.194 | 5.4102 | 240.117 | 1.2663 | 0.024759 | 0.00029449 | 0.37542 | 0.64388 | {99C448A1-95CE-4373-846C-DC41955DCE78} | 42281105 | POTTER VALLEY P H 1105 | 1904 | 39.3217 | -123.095 | POTTER VALLEY P H 11051904 | 418 | 389 | 96960.159 | 64539.5347 | 32420.6243 | 47497.3243 | 20016.0873 | 0.082457 | 0.021652 | 1.3652 | 5.3464 | 1139 | 6.9326 | 483 | 0 | 0 | 29.5135 | 1226 | 0
Bay Area | 3315 | 230 | 300.2242 | 612 | 534.2272 | 46 | 7.0784e-05 | 338.6597 | 0.6255 | 35.0616 | 425.8495 | 0.97998 | 0.8119 | 20.2463 | 0.96484 | 0.024681 | 5.7453e-05 | 0.37582 | 0.56198 | {65C50E41-4A19-4EF0-8E02-55AD7C68E0C7} | 43432102 | SILVERADO 2102 | 714 | 38.5063 | -122.4411 | SILVERADO 2102714 | 210 | 221 | 33589.1166 | 18049.585 | 15539.5316 | 5471.307 | 2570.4065 | 0.0026429 | 0.0032561 | 1.3053 | 13.3043 | 2164 | 1.1353 | 484 | 0 | 0 | 3.3997 | 2216 | 0
North Valley | 4876 | 479 | 793.4215 | 1457 | 1100.8885 | 264 | 6.7646e-05 | 463.1661 | 9.4714 | 835.5485 | 5437.5079 | 140.8599 | 10.0678 | 372.1371 | 1.1971 | 0.02471 | 0.00029547 | 0.32876 | 0.72071 | {0C0482CD-DD8D-411C-9735-C68EC442433B} | 103521103 | OREGON TRAIL 1103 | 1448 | 40.6477 | -122.2216 | OREGON TRAIL 11031448 | 293 | 210 | 63315.1998 | 49370.4838 | 13944.716 | 49370.4838 | 13944.716 | 0.078004 | 0.017859 | 1.6564 | 5.5189 | 1134 | 6.5234 | 485 | 0 | 0 | 30.6774 | 356 | 0
Sierra | 4876 | 2 | 1.9482 | 2 | 1.9482 | 1 | 2.8107e-05 | 431.3336 | 2.4948 | 177.85 | 667.9915 | 1.6824 | 10.4336 | 486.0411 | 1.1327 | 0.012123 | 7.0121e-05 | 1 | 1 | {0C0482CD-DD8D-411C-9735-C68EC442433B} | 103521103 | OREGON TRAIL 1103 | 1448 | 40.6477 | -122.2216 | OREGON TRAIL 11031448 | 293 | 210 | 63315.1998 | 49370.4838 | 13944.716 | 49370.4838 | 13944.716 | 7.0121e-05 | 2.8107e-05 | 0.97408 | 2 | 2057 | 0.012123 | 485 | 0 | 0 | 30.6774 | 601 | 0
North Coast | 3787 | 95 | 217.8664 | 426 | 392.782 | 53 | 7.8837e-05 | 318.5635 | 12.927 | 139.2907 | 694.5654 | 32.4773 | 17.2972 | 102.3879 | 1.0437 | 0.024606 | 0.00042603 | 0.223 | 0.55468 | {80668D9B-77B5-47D8-83CC-0D502F20CB37} | 42271102 | COTATI 1102 | 681 | 38.2838 | -122.7101 | COTATI 1102681 | 75 | 147 | 15399.9783 | 6118.1742 | 9281.8041 | 6118.1742 | 9281.8041 | 0.02258 | 0.0041783 | 2.2933 | 8.0377 | 902 | 1.3041 | 486 | 0 | 0 | 3.8017 | 952 | 0
North Valley | 4785 | 70 | 110.1528 | 274 | 161.8586 | 88 | 3.9875e-05 | 598.0428 | 2.3894 | 320.6889 | 1330.9157 | 8.6567 | 14.0347 | 1034.4454 | 1.6047 | 0.024551 | 7.8863e-05 | 0.25547 | 0.68055 | {33F0E676-CC76-4272-99EB-E4EC15B2860E} | 103461102 | PANORAMA 1102 | 1342 | 40.4475 | -122.2559 | PANORAMA 11021342 | 301 | 320 | 71782.5467 | 41106.3194 | 30676.2273 | 19597.5982 | 11105.0042 | 0.0069399 | 0.003509 | 1.5736 | 3.1136 | 1989 | 2.1604 | 487 | 0 | 0 | 12.1774 | 1016 | 0
North Coast | 4620 | 257 | 741.5327 | 547 | 906.0405 | 85 | 7.4853e-05 | 361.6441 | 76.8369 | 877.9235 | 4525.5636 | 742.5279 | 24.7829 | 117.3335 | 1.0596 | 0.024467 | 0.0024926 | 0.46984 | 0.81843 | {8B07F2D1-E8C2-46BF-BEB1-6EA256DCFEAC} | 42271103 | COTATI 1103 | 79140 | 38.2826 | -122.7557 | COTATI 110379140 | 270 | 340 | 43485.4274 | 19876.9325 | 23608.4948 | 15556.81 | 17832.895 | 0.21187 | 0.0063625 | 2.8853 | 6.4353 | 126 | 2.0797 | 488 | 0 | 0 | 9.6666 | 2550 | 0
Central Valley | 1266 | 67 | 151.1889 | 441 | 238.6958 | 140 | 2.7182e-05 | 632.4473 | 14.6982 | 191.1753 | 772.7287 | 20.3785 | 13.4091 | 164.0552 | 1.2872 | 0.024441 | 0.00025334 | 0.15193 | 0.6334 | {C35DFEFE-AAAB-47B8-ACD8-3B6A331D2855} | 252811102 | MERCED FALLS 1102 | 9470 | 37.646 | -120.3111 | MERCED FALLS 11029470 | 390 | 384 | 66956.1566 | 36994.5762 | 29961.5805 | 36994.5762 | 29961.5805 | 0.035468 | 0.0038054 | 2.2566 | 3.15 | 1241 | 3.4217 | 489 | 0 | 0 | 22.9874 | 2109 | 0
Central Valley | 4163 | 80 | 106.9652 | 292 | 215.3758 | 42 | 6.0144e-05 | 394.1911 | 7.4842 | 84.7161 | 429.0031 | 8.0378 | 15.6394 | 203.2695 | 1.4948 | 0.024376 | 0.00022879 | 0.27397 | 0.49664 | {5512EE79-F6AF-4543-8A7B-B7E11740B6C7} | 252521103 | SAN JOAQUIN #2 1103 | 157026 | 37.2401 | -119.5576 | SAN JOAQUIN #2 1103157026 | 64 | 66 | 9734.3319 | 5166.9066 | 4567.4252 | 5166.9066 | 4567.4252 | 0.0096094 | 0.002526 | 1.3371 | 6.9524 | 1315 | 1.0238 | 490 | 0 | 0 | 3.2106 | 46 | 0
North Coast | 8986 | 1 | 2.9829 | 1 | 2.9829 | 1 | 8.5429e-05 | 285.2803 |  |  |  |  | 3.0088 | 11.3765 | 1.3053 | 0.024371 | 8.5429e-05 | 1 | 1 | {0E59589A-491E-4CA0-BA48-3E1B533591BC} | 43040401 | GARCIA 0401 | circuit_breaker | 38.8891 | -123.5504 | GARCIA 0401circuit_breaker | 5 | 0 | 68.2264 | 68.2264 | 0 | 68.2264 | 0 | 8.5429e-05 | 8.5429e-05 | 2.9829 | 1 | 1943 | 0.024371 | 491 | 0 | 0 | 0.042394 | 485 | 0
Central Coast | 7575 | 94 | 304.6577 | 142 | 330.9608 | 12 | 2.3019e-05 | 889.9451 | 19.3073 | 91.0128 | 441.2497 | 9.1127 | 21.6991 | 109.2042 | 1.1866 | 0.024278 | 0.00017388 | 0.66197 | 0.92052 | {2FEE1CE0-BC95-467C-8CDD-CAD4D3CD2579} | 182601106 | OCEANO 1106 | circuit_breaker | 35.1012 | -120.5814 | OCEANO 1106circuit_breaker | 173 | 344 | 21108.4269 | 8076.9737 | 13031.4532 | 1811.9234 | 125.9887 | 0.0020866 | 0.00027622 | 3.241 | 11.8333 | 1509 | 0.29134 | 492 | 0 | 0 | 1.1259 | 2745 | 0
Sierra | 8031 | 395 | 886.0073 | 519 | 943.8534 | 89 | 8.3955e-05 | 295.6289 | 15.1033 | 1767.2217 | 31832.119 | 872.9969 | 0.60876 | 53.7377 | 1.165 | 0.024252 | 0.0007305 | 0.76108 | 0.93871 | {07E52C28-7426-408F-9FC2-C4593A9ACBA6} | 152201101 | PIKE CITY 1101 | 1720 | 39.455 | -121.0529 | PIKE CITY 11011720 | 41 | 31 | 11370.7863 | 9790.3862 | 1580.4001 | 9790.3862 | 1580.4001 | 0.065015 | 0.007472 | 2.2431 | 5.8315 | 546 | 2.1584 | 493 | 0 | 0 | 6.0835 | 562 | 0
Central Valley | 2652 | 45 | 83.239 | 154 | 121.8188 | 29 | 5.7377e-05 | 472.5256 | 26.7838 | 1263.6678 | 6818.811 | 316.4159 | 13.5954 | 394.1857 | 1.3946 | 0.024246 | 0.00083646 | 0.29221 | 0.6833 | {0DE3898A-1208-4EC8-ABE1-FA05111C0DC6} | 163541101 | OLETA 1101 | 63500 | 38.4802 | -120.8458 | OLETA 110163500 | 192 | 416 | 26445.3396 | 12301.408 | 14143.9316 | 6425.1593 | 2551.58 | 0.024257 | 0.0016639 | 1.8498 | 5.3103 | 480 | 0.70315 | 494 | 0 | 0 | 3.9924 | 1368 | 0
Sierra | 5290 | 283 | 417.6397 | 613 | 553.0207 | 66 | 9.1935e-05 | 378.6157 | 10.2894 | 35.2668 | 89.8025 | 1.8153 | 9.7312 | 66.3792 | 1.055 | 0.024152 | 0.00063751 | 0.46166 | 0.7552 | {A3F26B0A-1692-42C7-87B6-33C42D499946} | 152561107 | PENRYN 1107 | 2706 | 38.8101 | -121.1629 | PENRYN 11072706 | 304 | 342 | 43976.489 | 24016.257 | 19960.232 | 7658.9338 | 3874.9624 | 0.042075 | 0.0060677 | 1.4758 | 9.2879 | 630 | 1.594 | 495 | 0 | 0 | 4.759 | 190 | 0
North Coast | 4382 | 634 | 808.2243 | 965 | 971.356 | 135 | 0.00012575 | 130.3756 | 1.0039 | 490.2626 | 9029.4935 | 17.5557 | 1.7283 | 126.8407 | 1.1996 | 0.023527 | 0.00013465 | 0.65699 | 0.83206 | {71DE392B-20E6-4124-9FFE-851197719244} | 192411101 | LOW GAP 1101 | 4086 | 40.3025 | -123.3539 | LOW GAP 11014086 | 87 | 69 | 19778.9957 | 18494.205 | 1284.7907 | 18494.205 | 1284.7907 | 0.018178 | 0.016976 | 1.2748 | 7.1481 | 1670 | 3.1761 | 496 | 0 | 0 | 11.4918 | 922 | 0
Bay Area | 3568 | 4060 | 5493.9395 | 7879 | 7705.8994 | 570 | 0.00011023 | 208.7774 | 0.0035081 | 0.22239 | 1.635 | 5.7359e-06 | 1.3196 | 47.4208 | 1.1438 | 0.023503 | 0.00011001 | 0.51529 | 0.71295 | {80E79C4D-3B76-415E-BA02-A8236360DA4C} | 43292103 | PUEBLO 2103 | 678 | 38.3155 | -122.3423 | PUEBLO 2103678 | 453 | 372 | 104015.0972 | 56404.6012 | 47610.4961 | 56171.914 | 46797.5902 | 0.062707 | 0.062829 | 1.3532 | 13.8228 | 1801 | 13.3968 | 497 | 0 | 0 | 34.9036 | 2597 | 0
North Valley | 1140 | 738 | 1311.8953 | 2454 | 1974.8413 | 308 | 5.7119e-05 | 512.0053 | 19.3385 | 142.7901 | 660.6048 | 30.1147 | 14.4659 | 109.7034 | 1.1796 | 0.023479 | 0.0004626 | 0.30073 | 0.6643 | {E0470028-6FEE-4E7A-BA03-DFBD06B93819} | 102911107 | WYANDOTTE 1107 | 77578 | 39.4832 | -121.5031 | WYANDOTTE 110777578 | 680 | 861 | 105369.0547 | 51812.8398 | 53556.2148 | 31530.7542 | 30457.677 | 0.14248 | 0.017593 | 1.7776 | 7.9675 | 843 | 7.2314 | 498 | 0 | 0 | 19.5923 | 2661 | 0
North Coast | 1668 | 492 | 629.9467 | 883 | 829.7175 | 100 | 0.00029044 | 67.4047 | 3.4952 | 550.2453 | 5542.0983 | 60.4753 | 0.62912 | 42.5516 | 1.09 | 0.023388 | 0.00084348 | 0.55719 | 0.75923 | {0FD31FD2-8045-433E-9D12-C8669CFF0383} | 192221102 | GARBERVILLE 1102 | 2010 | 40.1419 | -123.8077 | GARBERVILLE 11022010 | 51 | 43 | 11776.1763 | 10929.7392 | 846.437 | 10929.7392 | 846.437 | 0.084348 | 0.029044 | 1.2804 | 8.83 | 476 | 2.3388 | 499 | 0 | 0 | 6.7914 | 1059 | 0
Sierra | 1827 | 758 | 1249.9292 | 1899 | 1690.4498 | 252 | 0.00014599 | 172.6906 | 19.5273 | 52.9424 | 338.3109 | 32.114 | 6.0177 | 47.9841 | 1.2288 | 0.023184 | 0.0014899 | 0.39916 | 0.73941 | {F8F7136D-4B7B-4975-BCB7-4503BD4299E2} | 153652105 | SHINGLE SPRINGS 2105 | circuit_breaker | 38.6593 | -120.9469 | SHINGLE SPRINGS 2105circuit_breaker | 459 | 583 | 66260.6121 | 31350.2151 | 34910.3969 | 31350.2151 | 34910.3969 | 0.37546 | 0.03679 | 1.649 | 7.5357 | 247 | 5.8423 | 500 | 0 | 0 | 19.4801 | 427 | 0
Central Valley | 1905 | 194 | 410.0131 | 721 | 570.7039 | 191 | 6.2956e-05 | 335.3476 | 10.0969 | 289.9033 | 1026.3829 | 20.372 | 10.6356 | 553.2159 | 1.4226 | 0.023156 | 0.00035496 | 0.26907 | 0.71843 | {FA75516B-A711-4173-9090-FC27FCF4EADC} | 163231101 | NORTH BRANCH 1101 | TS1115 | 38.2444 | -120.8446 | NORTH BRANCH 1101TS1115 | 185 | 183 | 38855.9439 | 28340.5083 | 10515.4356 | 28340.5083 | 10515.4356 | 0.067797 | 0.012025 | 2.1135 | 3.7749 | 1009 | 4.4229 | 501 | 0 | 0 | 17.61 | 1779 | 0
North Coast | 3891 | 23 | 36.0119 | 58 | 46.2169 | 17 | 5.4152e-05 | 517.4608 | 2.1656 | 362.1673 | 1643.6631 | 7.6173 | 12.4693 | 750.6844 | 1.5204 | 0.023096 | 9.2342e-05 | 0.39655 | 0.77919 | {EAAE6801-22BE-4013-9B3B-D2D2C906D6CC} | 43141102 | MIDDLETOWN 1102 | 878 | 38.7862 | -122.5678 | MIDDLETOWN 1102878 | 96 | 75 | 12817.5786 | 9248.9027 | 3568.676 | 2592.1013 | 2856.7708 | 0.0015698 | 0.00092059 | 1.5657 | 3.4118 | 1893 | 0.39264 | 502 | 0 | 0 | 1.6107 | 1947 | 0
Bay Area | 4601 | 56 | 192.214 | 80 | 200.9478 | 25 | 2.6937e-05 | 895.8504 | 3.4005 | 224.196 | 1072.9477 | 21.532 | 18.6583 | 977.3608 | 1.5938 | 0.022885 | 6.3004e-05 | 0.7 | 0.95654 | {9A8233B7-234B-46CF-8EEF-6B74776F9D38} | 14592105 | BRENTWOOD 2105 | B504R | 37.8951 | -121.6965 | BRENTWOOD 2105B504R | 131 | 66 | 21006.1139 | 18129.5072 | 2876.6067 | 12899.4497 | 1629.8507 | 0.0015751 | 0.00067344 | 3.4324 | 3.2 | 2114 | 0.57211 | 503 | 0 | 0 | 8.0153 | 2064 | 0
Sierra | 7989 | 62 | 120.0739 | 245 | 190.9597 | 52 | 5.258e-05 | 816.6228 | 8.78 | 336.2541 | 1800.3732 | 160.384 | 11.6977 | 515.5025 | 1.4134 | 0.024111 | 0.0001362 | 0.25306 | 0.62879 | {17B7D6FE-5F00-4D1F-ABC4-4972705BA2FB} | 63681102 | PUTAH CREEK 1102 | 64044 | 38.4944 | -122.0341 | PUTAH CREEK 110264044 | 58 | 43 | 13605.0908 | 11992.1979 | 1612.8929 | 8899.6249 | 1038.6404 | 0.0070826 | 0.0027341 | 1.9367 | 4.7115 | 1657 | 1.2537 | 504 | 0 | 0 | 5.53 | 2058 | 0
Bay Area | 7989 | 10 | 16.7116 | 43 | 31.239 | 5 | 7.7605e-05 | 215.8449 | 0.096642 | 1.0026 | 1.2419 | 0.0010826 | 2.1385 | 272.5782 | 1.2779 | 0.0091459 | 7.0498e-05 | 0.23256 | 0.53496 | {17B7D6FE-5F00-4D1F-ABC4-4972705BA2FB} | 63681102 | PUTAH CREEK 1102 | 64044 | 38.4944 | -122.0341 | PUTAH CREEK 110264044 | 58 | 43 | 13605.0908 | 11992.1979 | 1612.8929 | 8899.6249 | 1038.6404 | 0.00035249 | 0.00038803 | 1.6712 | 8.6 | 2053 | 0.04573 | 504 | 0 | 0 | 5.53 | 2076 | 0
Sierra | 1677 | 101 | 145.5733 | 213 | 186.5665 | 38 | 5.4954e-05 | 480.2587 | 16.6256 | 83.3901 | 257.7536 | 5.8188 | 19.1763 | 249.2636 | 1.5047 | 0.022789 | 0.00037463 | 0.47418 | 0.78028 | {E7E117D2-097F-4861-BB68-A88E0DF34298} | 152691103 | HIGGINS 1103 | 9753 | 39.0732 | -121.0861 | HIGGINS 11039753 | 34 | 43 | 6134.4041 | 3306.1166 | 2828.2875 | 3306.1166 | 2828.2875 | 0.014236 | 0.0020882 | 1.4413 | 5.6053 | 976 | 0.86597 | 505 | 0 | 0 | 2.0543 | 1568 | 0
Central Valley | 1785 | 1218 | 1729.3495 | 4535 | 3087.9548 | 656 | 6.5605e-05 | 400.2306 | 32.266 | 366.7435 | 3400.508 | 714.2567 | 11.445 | 211.0995 | 1.3505 | 0.022752 | 0.00096475 | 0.26858 | 0.56003 | {B491FAF3-D57C-4407-A408-814947D65184} | 254432104 | COARSEGOLD 2104 | 10110 | 37.2673 | -119.7126 | COARSEGOLD 210410110 | 750 | 782 | 136664.1753 | 79684.5808 | 56979.5945 | 79684.5808 | 56979.5945 | 0.63288 | 0.043037 | 1.4198 | 6.9131 | 429 | 14.9256 | 506 | 0 | 0 | 49.5137 | 2720 | 0
North Coast | 5286 | 25 | 77.4371 | 77 | 97.6597 | 27 | 6.0232e-05 | 352.9174 | 34.4315 | 1206.99 | 5769.5142 | 487.1509 | 9.3136 | 384.9397 | 1.2316 | 0.022746 | 0.00057158 | 0.32468 | 0.79293 | {D07BAC6A-6F88-48C4-A1B1-54FEC9739EF1} | 42271105 | COTATI 1105 | 634 | 38.2982 | -122.8208 | COTATI 1105634 | 58 | 58 | 19573.4881 | 11162.845 | 8410.6431 | 11162.845 | 8410.6431 | 0.015433 | 0.0016263 | 3.0975 | 2.8519 | 707 | 0.61415 | 507 | 0 | 0 | 6.9363 | 521 | 0
North Coast | 7221 | 282 | 452.6152 | 508 | 539.0876 | 71 | 9.433e-05 | 227.1014 | 2.5473 | 215.4384 | 2075.1854 | 10.1477 | 2.2553 | 93.437 | 1.3552 | 0.02274 | 0.00015912 | 0.55512 | 0.83959 | {3EE95B4C-7440-4D46-99D3-576CFD7E946C} | 43311102 | KONOCTI 1102 | 948 | 38.9109 | -122.6462 | KONOCTI 1102948 | 111 | 169 | 22389.5005 | 12598.6341 | 9790.8664 | 9863.4507 | 8767.2857 | 0.011298 | 0.0066975 | 1.605 | 7.1549 | 1546 | 1.6146 | 508 | 0 | 0 | 6.1289 | 602 | 0
North Coast | 7640 | 2089 | 3445.1413 | 2951 | 3884.4402 | 296 | 0.00014249 | 160.6944 | 5.1781 | 376.84 | 4233.4207 | 62.1798 | 1.2639 | 94.5353 | 1.1815 | 0.022706 | 0.00046906 | 0.7079 | 0.88691 | {33062E2A-6001-4611-8363-46C244F6285A} | 42681102 | LAYTONVILLE 1102 | 572 | 39.6732 | -123.506 | LAYTONVILLE 1102572 | 203 | 164 | 46924.3949 | 34430.0284 | 12494.3665 | 34430.0284 | 12494.3665 | 0.13884 | 0.042176 | 1.6492 | 9.9696 | 830 | 6.721 | 509 | 0 | 0 | 21.3938 | 2635 | 0
Sierra | 5059 | 1297 | 1775.8222 | 2273 | 2261.0537 | 219 | 0.00010173 | 233.0709 | 91.9005 | 792.3553 | 11804.6971 | 2230.8572 | 8.2015 | 74.3795 | 1.1576 | 0.02259 | 0.0042035 | 0.57061 | 0.7854 | {95AAF818-10A5-460C-909E-8A1D81C4AEC8} | 152261106 | DIAMOND SPRINGS 1106 | 56026 | 38.6915 | -120.7656 | DIAMOND SPRINGS 110656026 | 255 | 258 | 43851.0487 | 24259.9065 | 19591.1423 | 24259.9065 | 19449.8749 | 0.92057 | 0.02228 | 1.3692 | 10.379 | 56 | 4.9473 | 510 | 0 | 0 | 15.0744 | 141 | 0
Sierra | 3735 | 346 | 612.334 | 1338 | 961.9025 | 195 | 6.3136e-05 | 398.0085 | 6.8385 | 92.8286 | 510.6784 | 7.0379 | 12.62 | 180.2042 | 1.3338 | 0.022453 | 0.00022725 | 0.25859 | 0.63659 | {824F13D7-3113-4AA8-8BC2-89229A42D634} | 152691109 | HIGGINS 1109 | 594 | 39.0351 | -121.0957 | HIGGINS 1109594 | 239 | 246 | 40674.5308 | 23079.0602 | 17595.4706 | 23079.0602 | 17595.4706 | 0.044314 | 0.012311 | 1.7698 | 6.8615 | 1323 | 4.3783 | 511 | 0 | 0 | 14.3407 | 1438 | 0
North Coast | 6815 | 2 | 2.4554 | 4 | 3.2621 | 3 | 5.4128e-05 | 341.3674 | 3.1417 | 27.7456 | 70.5576 | 0.22186 | 8.9447 | 53.9635 | 1.1003 | 0.022388 | 8.9344e-05 | 0.5 | 0.75271 | {47939910-AA8B-4A65-8C1D-0E8F25841F0A} | 43181102 | BELLEVUE 1102 | 392 | 38.3665 | -122.7415 | BELLEVUE 1102392 | 110 | 163 | 20890.093 | 10922.1116 | 9967.9814 | 223.0422 | 1352.2848 | 0.00026803 | 0.00016238 | 1.2277 | 1.3333 | 1913 | 0.067165 | 512 | 0 | 0 | 0.13859 | 2602 | 0
North Coast | 1017 | 138 | 291.796 | 312 | 351.4481 | 100 | 6.9353e-05 | 420.0914 | 14.1376 | 23.3389 | 94.1633 | 8.0819 | 7.9095 | 104.9 | 1.1287 | 0.022378 | 0.0003498 | 0.44231 | 0.83027 | {EAE1C088-E6A0-4B00-80D2-C64BBF575702} | 43141102 | MIDDLETOWN 1102 | 1312 | 38.8089 | -122.5709 | MIDDLETOWN 11021312 | 207 | 853 | 62789.1721 | 15846.2392 | 46942.9329 | 15846.2392 | 46942.9329 | 0.03498 | 0.0069353 | 2.1145 | 3.12 | 1012 | 2.2378 | 513 | 0 | 0 | 9.8464 | 1324 | 0
Bay Area | 6904 | 454 | 724.8309 | 973 | 1025.8917 | 61 | 0.00013326 | 153.6535 | 1.815 | 12.9381 | 99.7546 | 0.37122 | 1.0372 | 7.8066 | 1.0426 | 0.02234 | 0.0001892 | 0.4666 | 0.70654 | {65E252BA-B6AF-41C8-8302-CDA75AAEE4FD} | 43432104 | SILVERADO 2104 | 708 | 38.5146 | -122.4742 | SILVERADO 2104708 | 109 | 167 | 16614.2851 | 7838.2779 | 8776.0072 | 5638.2492 | 5955.9207 | 0.011541 | 0.0081287 | 1.5965 | 15.9508 | 1453 | 1.3627 | 514 | 0 | 0 | 3.5034 | 2151 | 0
Bay Area | 3092 | 1151 | 1628.4047 | 1732 | 1943.9434 | 167 | 0.00013465 | 146.701 | 2.9679 | 136.3856 | 2217.3777 | 25.8244 | 0.98518 | 19.2795 | 1.0212 | 0.022257 | 0.00029184 | 0.66455 | 0.83768 | {1AD33002-13F2-40BB-9E7F-A659676EE415} | 42711102 | CALISTOGA 1102 | 634 | 38.5859 | -122.5715 | CALISTOGA 1102634 | 339 | 286 | 57976.5334 | 30755.7403 | 27220.7931 | 19084.7717 | 18157.0478 | 0.048737 | 0.022487 | 1.4148 | 10.3713 | 1148 | 3.7169 | 515 | 0 | 0 | 11.8587 | 306 | 0
Central Valley | 1410 | 1416 | 1924.7548 | 4886 | 3528.345 | 815 | 4.5771e-05 | 470.4323 | 16.3012 | 240.774 | 2208.0615 | 100.4681 | 11.0176 | 163.9128 | 1.3509 | 0.022179 | 0.00037976 | 0.28981 | 0.54551 | {5BCEC129-10D0-4B20-A658-76CA792FBB41} | 254452101 | MARIPOSA 2101 | 9400 | 37.5219 | -119.917 | MARIPOSA 21019400 | 941 | 1040 | 181888.2181 | 101390.2805 | 80497.9375 | 101390.2805 | 80497.9375 | 0.30951 | 0.037303 | 1.3593 | 5.9951 | 968 | 18.0755 | 516 | 0 | 0 | 63.001 | 1742 | 0
Bay Area | 9107 | 30 | 49.8099 | 39 | 54.646 | 14 | 0.00010621 | 200.7479 | 1.9419 | 137.4493 | 1709.9081 | 6.9267 | 0.0433 | 80.6221 | 1.3387 | 0.022169 | 0.00015454 | 0.76923 | 0.9115 | {D6C28B55-DE54-4F6F-8030-4A9A0C2CC1E1} | 42711101 | CALISTOGA 1101 | 35588 | 38.6577 | -122.5952 | CALISTOGA 110135588 | 25 | 7 | 4951.7392 | 4848.4058 | 103.3334 | 4848.4058 | 103.3334 | 0.0021636 | 0.001487 | 1.6603 | 2.7857 | 1568 | 0.31037 | 517 | 0 | 0 | 3.0127 | 2368 | 0
Bay Area | 500 | 895 | 1301.2987 | 1354 | 1554.5092 | 98 | 0.00016868 | 133.3626 | 3.7509 | 62.7279 | 1004.9837 | 14.9482 | 3.0079 | 17.8596 | 1.0886 | 0.022114 | 0.00041821 | 0.661 | 0.83711 | {C9B98E7E-238C-4FD6-BD54-6425F9378BA6} | 42711101 | CALISTOGA 1101 | 43924 | 38.5951 | -122.6023 | CALISTOGA 110143924 | 207 | 285 | 36562.9148 | 14779.5747 | 21783.3401 | 11371.1135 | 14720.5357 | 0.040985 | 0.016531 | 1.454 | 13.8163 | 914 | 2.1672 | 518 | 0 | 0 | 7.0657 | 2790 | 0
North Valley | 6812 | 36 | 68.2435 | 96 | 85.4868 | 34 | 3.7765e-05 | 599.8459 | 1.0304 | 1498.7958 | 16385.7397 | 88.4066 | 7.9498 | 1308.6404 | 1.8067 | 0.021951 | 4.9615e-05 | 0.375 | 0.79829 | {E8D8BCF8-6452-443E-AE6E-F4CFFAE760DF} | 103611101 | WILDWOOD 1101 | 1454 | 40.3591 | -122.8923 | WILDWOOD 11011454 | 36 | 22 | 14975.6572 | 12434.0103 | 2541.6468 | 12434.0103 | 2541.6468 | 0.0016869 | 0.001284 | 1.8957 | 2.8235 | 2231 | 0.74635 | 519 | 0 | 0 | 7.7261 | 1409 | 0
North Coast | 1268 | 866 | 1162.7187 | 1546 | 1543.6132 | 196 | 0.00013043 | 195.1344 | 21.3691 | 1261.5595 | 21579.7183 | 496.6493 | 5.3891 | 238.982 | 1.362 | 0.021889 | 0.0012414 | 0.56016 | 0.75324 | {9CD0DE6C-67D0-4975-9926-0CEC6137D8E0} | 43141101 | MIDDLETOWN 1101 | 4646 | 38.8289 | -122.7294 | MIDDLETOWN 11014646 | 222 | 250 | 44102.1646 | 29953.689 | 14148.4756 | 29953.689 | 14148.4756 | 0.24332 | 0.025565 | 1.3426 | 7.8878 | 309 | 4.2902 | 520 | 0 | 0 | 18.6124 | 412 | 0
Bay Area | 2172 | 111 | 185.378 | 317 | 300.375 | 39 | 5.6911e-05 | 423.1444 | 6.0554 | 319.6893 | 4978.6809 | 233.3644 | 2.1991 | 171.5642 | 1.3644 | 0.021873 | 0.00019895 | 0.35016 | 0.61716 | {5B3909F8-EEF1-46D6-9827-15D3DCA91BD0} | 43051101 | MONTICELLO 1101 | 4360 | 38.4042 | -122.2043 | MONTICELLO 11014360 | 103 | 80 | 38897.7176 | 14746.7227 | 24150.995 | 11112.131 | 21310.944 | 0.0077592 | 0.0022195 | 1.6701 | 8.1282 | 1417 | 0.85304 | 521 | 0 | 0 | 6.9048 | 371 | 0
North Coast | 2497 | 33 | 54.9225 | 46 | 62.9622 | 5 | 6.9287e-05 | 271.6031 | 4.3135 | 29.7533 | 97.8886 | 0.79013 | 30.4301 | 94.5291 | 1.0611 | 0.021854 | 0.00027526 | 0.71739 | 0.87231 | {A29DEF0E-FE5C-45F9-AF88-EA9CD50596F5} | 42271102 | COTATI 1102 | 825 | 38.3081 | -122.6907 | COTATI 1102825 | 45 | 107 | 9785.8003 | 3371.6214 | 6414.1789 | 749.4567 | 568.1816 | 0.0013763 | 0.00034644 | 1.6643 | 9.2 | 1188 | 0.10927 | 522 | 0 | 0 | 0.46569 | 2098 | 0
Central Coast | 2933 | 11 | 16.9 | 29 | 28.2912 | 9 | 2.7976e-05 | 672.366 | 14.7164 | 1126.2522 | 4804.0118 | 102.5108 | 12.1504 | 203.225 | 1 | 0.021844 | 0.00019458 | 0.37931 | 0.59736 | {21823ADE-60D1-49AF-96C7-A6BCD78F0512} | 83432101 | HICKS 2101 | XR548 | 37.2021 | -121.8332 | HICKS 2101XR548 | 171 | 152 | 25675.3901 | 13934.1431 | 11741.247 | 1925.3259 | 518.2523 | 0.0017512 | 0.00025178 | 1.5364 | 3.2222 | 1427 | 0.1966 | 523 | 0 | 0 | 1.1963 | 1176 | 0
Central Valley | 3243 | 46 | 92.5631 | 151 | 130.904 | 48 | 3.9624e-05 | 540.1497 | 4.6544 | 318.3773 | 1434.8198 | 10.9189 | 7.8694 | 1132.6116 | 1.7461 | 0.024972 | 9.7322e-05 | 0.30464 | 0.70711 | {F1BA8416-91DD-4B99-927A-83F7EBAF42CF} | 163541101 | OLETA 1101 | 1217 | 38.4881 | -120.9102 | OLETA 11011217 | 128 | 108 | 40122.9894 | 27736.9205 | 12386.069 | 21207.62 | 6809.7221 | 0.0046715 | 0.0019019 | 2.0122 | 3.1458 | 1866 | 1.1987 | 524 | 0 | 0 | 13.1778 | 1831 | 0
Sierra | 3243 | 57 | 115.7407 | 124 | 141.0487 | 45 | 7.3584e-05 | 231.4492 | 3.1861 | 230.8828 | 1224.0184 | 22.084 | 7.9312 | 839.476 | 1.5962 | 0.018387 | 0.00013517 | 0.45968 | 0.82057 | {F1BA8416-91DD-4B99-927A-83F7EBAF42CF} | 163541101 | OLETA 1101 | 1217 | 38.4881 | -120.9102 | OLETA 11011217 | 128 | 108 | 40122.9894 | 27736.9205 | 12386.069 | 21207.62 | 6809.7221 | 0.0060827 | 0.0033113 | 2.0305 | 2.7556 | 1664 | 0.82741 | 524 | 0 | 0 | 13.1778 | 786 | 0
North Coast | 5067 | 713 | 1001.577 | 1502 | 1441.0066 | 146 | 0.00011891 | 173.5154 | 22.2398 | 270.0154 | 3457.0724 | 235.709 | 3.3384 | 52.3725 | 1.146 | 0.021613 | 0.0012469 | 0.4747 | 0.69505 | {F138D9D4-46B7-40FF-98A4-3E0C55CB9A57} | 42571102 | MOLINO 1102 | 658 | 38.4451 | -122.9104 | MOLINO 1102658 | 153 | 128 | 25689.6107 | 17538.0269 | 8151.5838 | 17538.0269 | 8151.5838 | 0.18205 | 0.017361 | 1.4047 | 10.2877 | 307 | 3.1554 | 525 | 0 | 0 | 10.8976 | 1174 | 0
North Coast | 14 | 381 | 507.7768 | 785 | 692.502 | 102 | 0.00015878 | 136.3345 | 12.7142 | 278.9352 | 3250.0561 | 147.0457 | 4.4278 | 77.2884 | 1.0978 | 0.021603 | 0.0011806 | 0.48535 | 0.73325 | {CBF297F1-D8F4-467D-B156-4EC62C764040} | 42951101 | MENDOCINO 1101 | 37462 | 39.2651 | -123.2054 | MENDOCINO 110137462 | 503 | 547 | 70254.4538 | 38310.1036 | 31944.3502 | 11379.0989 | 6136.6581 | 0.12042 | 0.016196 | 1.3327 | 7.6961 | 330 | 2.2035 | 526 | 0 | 0 | 7.0706 | 1103 | 0
Bay Area | 9243 | 752 | 1154.7365 | 1209 | 1422.0878 | 113 | 0.00011542 | 156.405 | 1.1393 | 280.0545 | 4657.0145 | 50.7269 | 0.041311 | 66.197 | 1.2233 | 0.021493 | 0.00013252 | 0.622 | 0.812 | {2BEF64F2-FC8F-447E-AB5E-08962A1289FE} | 42261101 | BOLINAS 1101 | 530 | 37.9426 | -122.7025 | BOLINAS 1101530 | 33 | 4 | 17862.3416 | 17644.1845 | 218.1571 | 17644.1845 | 218.1571 | 0.014975 | 0.013043 | 1.5356 | 10.6991 | 1688 | 2.4287 | 527 | 0 | 0 | 10.9636 | 121 | 0
Sierra | 837 | 1353 | 2114.6073 | 4294 | 3271.45 | 431 | 8.2443e-05 | 376.1593 | 10.2854 | 103.0366 | 699.9919 | 19.3661 | 8.3503 | 99.6616 | 1.2689 | 0.021444 | 0.00041352 | 0.31509 | 0.64638 | {5963F19C-E1BE-46EC-9E26-B117A913E935} | 152691103 | HIGGINS 1103 | circuit_breaker | 39.0438 | -121.0912 | HIGGINS 1103circuit_breaker | 486 | 510 | 79011.4579 | 45896.1812 | 33115.2767 | 45196.8083 | 32440.4555 | 0.17823 | 0.035533 | 1.5629 | 9.9629 | 923 | 9.2424 | 528 | 0 | 0 | 28.084 | 224 | 0
North Coast | 3302 | 61 | 77.9434 | 113 | 107.9893 | 13 | 0.000112 | 186.8326 | 3.0585 | 103.3716 | 2058.4835 | 18.4535 | 0.86232 | 23.4785 | 1.0963 | 0.021414 | 0.00023774 | 0.53982 | 0.72177 | {377EDE62-95BF-4247-B5CE-2FDAD489198A} | 42891101 | GEYSERVILLE 1101 | circuit_breaker | 38.7096 | -122.9079 | GEYSERVILLE 1101circuit_breaker | 170 | 287 | 24940.337 | 13273.8152 | 11666.5218 | 1595.2814 | 697.0736 | 0.0030906 | 0.001456 | 1.2778 | 8.6923 | 1284 | 0.27838 | 529 | 0 | 0 | 0.99126 | 635 | 0
Central Valley | 5902 | 252 | 348.5017 | 629 | 529.08 | 125 | 8.9249e-05 | 276.632 | 13.0855 | 218.4914 | 1771.4932 | 103.2807 | 9.7499 | 122.7847 | 1.2923 | 0.021389 | 0.00053401 | 0.40064 | 0.65869 | {97C68D50-1C62-46F3-99B5-57378B7629BD} | 254421102 | OAKHURST 1102 | 10100 | 37.3272 | -119.6493 | OAKHURST 110210100 | 259 | 308 | 36808.859 | 18754.034 | 18054.825 | 16350.2682 | 11587.4436 | 0.066752 | 0.011156 | 1.3829 | 5.032 | 752 | 2.6736 | 530 | 0 | 0 | 10.1596 | 1745 | 0
North Valley | 3548 | 694 | 1350.6054 | 1024 | 1511.2644 | 82 | 9.3585e-05 | 234.1335 | 105.5488 | 3309.5933 | 57639.3853 | 9638.4346 | 0.99242 | 32.6748 | 1.112 | 0.021317 | 0.004252 | 0.67773 | 0.89369 | {1446E22C-05D8-4F82-9637-10F46D2B1E35} | 103201102 | CHALLENGE 1102 | 1902 | 39.484 | -121.2454 | CHALLENGE 11021902 | 58 | 55 | 11330.7926 | 8106.7957 | 3223.9969 | 8106.7957 | 3223.9969 | 0.34866 | 0.007674 | 1.9461 | 12.4878 | 53 | 1.748 | 531 | 0 | 0 | 5.0373 | 1386 | 0
North Coast | 2908 | 1603 | 2195.3807 | 2620 | 2751.841 | 307 | 0.00013276 | 230.4767 | 21.913 | 312.4257 | 2732.844 | 281.5972 | 7.7641 | 224.3574 | 1.2311 | 0.021237 | 0.001324 | 0.61183 | 0.79779 | {3635FD5D-8230-40C4-B52D-81B9839A55A9} | 43311102 | KONOCTI 1102 | 75382 | 38.9065 | -122.6735 | KONOCTI 110275382 | 280 | 539 | 67660.3249 | 37575.1016 | 30085.2233 | 35775.2475 | 29767.2205 | 0.40646 | 0.040758 | 1.3695 | 8.5342 | 288 | 6.5197 | 532 | 0 | 0 | 22.2297 | 214 | 0
Bay Area | 1059 | 242 | 408.1535 | 831 | 668.9368 | 115 | 2.6495e-05 | 821.4368 | 1.1947 | 140.8587 | 727.7403 | 8.0543 | 11.8741 | 619.116 | 1.5081 | 0.02122 | 3.0537e-05 | 0.29122 | 0.61015 | {7A7A6CFC-A0E9-4695-9248-8391EE3DF390} | 12022212 | CLAYTON 2212 | Y504R | 37.9245 | -121.9125 | CLAYTON 2212Y504R | 187 | 222 | 39040.8466 | 18903.0653 | 20137.7813 | 18903.0653 | 19929.2571 | 0.0035117 | 0.0030469 | 1.6866 | 7.2261 | 2465 | 2.4403 | 533 | 0 | 0 | 11.7458 | 2625 | 0
North Coast | 1882 | 98 | 191.3185 | 224 | 268.113 | 30 | 8.9912e-05 | 236.6105 | 42.4083 | 339.3793 | 1329.9188 | 170.7261 | 9.7035 | 83.5587 | 1.1441 | 0.021141 | 0.0016234 | 0.4375 | 0.71357 | {5465105C-2E1E-47CE-8A44-120776A3EE22} | 42571104 | MOLINO 1104 | 380 | 38.3783 | -122.8063 | MOLINO 1104380 | 618 | 1222 | 112907.0342 | 45603.4304 | 67303.6038 | 4061.4593 | 3486.3271 | 0.048701 | 0.0026974 | 1.9522 | 7.4667 | 224 | 0.63424 | 534 | 0 | 0 | 2.5237 | 1634 | 0
North Coast | 2263 | 94 | 141.5067 | 114 | 149.6 | 12 | 4.2643e-05 | 353.5797 | 0.036352 | 0.13939 | 0.0678 | 3.9323e-06 | 9.6921 | 133.061 | 1.1707 | 0.021126 | 2.859e-05 | 0.82456 | 0.9459 | {35CE18CF-0731-4236-B455-551D76E65366} | 42141102 | CLEAR LAKE 1102 | circuit_breaker | 39.0078 | -122.8941 | CLEAR LAKE 1102circuit_breaker | 457 | 688 | 77495.013 | 36164.5483 | 41330.4648 | 1141.6054 | 818.8811 | 0.00034308 | 0.00051172 | 1.5054 | 9.5 | 2484 | 0.25352 | 535 | 0 | 0 | 0.70936 | 2235 | 0
Bay Area | 4973 | 0 | 0 | 4 | 2.4951 | 2 | 4.6317e-05 | 432.3787 |  |  |  |  | 3.7622 | 484.5864 | 1.7942 | 0.021086 | 4.6317e-05 | 0 | 0 | {F776B1CF-724B-4DB6-A87F-FF45F4D5AD0B} | 43292102 | PUEBLO 2102 | 1326 | 38.3917 | -122.3195 | PUEBLO 21021326 | 191 | 133 | 41794.0304 | 19367.251 | 22426.7794 | 326.1269 | 876.7851 | 9.2634e-05 | 9.2634e-05 |  | 2 | 2273 | 0.042172 | 536 | 0 | 0 | 0.20265 | 2795 | 0
North Coast | 4554 | 170 | 259.1168 | 304 | 312.6133 | 47 | 7.2809e-05 | 341.4736 | 27.6267 | 625.0498 | 5799.4127 | 347.2668 | 9.5542 | 259.4756 | 1.5027 | 0.021063 | 0.0011333 | 0.55921 | 0.82887 | {ED5E8DEC-3645-43AF-9022-699123418821} | 42871101 | UPPER LAKE 1101 | 452 | 39.1644 | -122.9083 | UPPER LAKE 1101452 | 293 | 492 | 66638.5819 | 31292.3538 | 35346.2281 | 4787.2263 | 2993.3321 | 0.053264 | 0.003422 | 1.5242 | 6.4681 | 350 | 0.98998 | 537 | 0 | 0 | 2.9746 | 842 | 0
North Coast | 3789 | 188 | 438.0339 | 592 | 683.1769 | 75 | 6.3737e-05 | 368.1564 | 18.9024 | 297.7877 | 1997.834 | 94.8056 | 10.0607 | 165.3915 | 1.1373 | 0.020998 | 0.00058456 | 0.31757 | 0.64117 | {105045E7-1917-46B4-B5AB-FC5617125FFB} | 43182103 | BELLEVUE 2103 | 478 | 38.38 | -122.6858 | BELLEVUE 2103478 | 332 | 318 | 60949.7506 | 32688.1249 | 28261.6257 | 13352.3887 | 9380.8271 | 0.043842 | 0.0047803 | 2.33 | 7.8933 | 688 | 1.5749 | 538 | 0 | 0 | 8.2968 | 1242 | 0
Central Valley | 6981 | 1 | 1.2277 | 59 | 20.8849 | 13 | 3.6503e-05 | 586.2177 | 129.9599 | 1393.1967 | 8528.0774 | 1170.2502 | 10.1156 | 136.9966 | 1.3174 | 0.020846 | 0.0013927 | 0.016949 | 0.058785 | {A0B72D64-342D-4CD8-B398-D7C01DA365B3} | 162991102 | CORRAL 1102 | 13498 | 38.172 | -120.8366 | CORRAL 110213498 | 21 | 14 | 2759.8685 | 1603.6406 | 1156.2279 | 1585.9579 | 983.4109 | 0.018105 | 0.00047454 | 1.2277 | 4.5385 | 275 | 0.271 | 539 | 0 | 0 | 0.98547 | 1495 | 0
Sierra | 7725 | 431 | 764.4922 | 841 | 988.8135 | 104 | 6.1114e-05 | 345.8639 | 8.8141 | 911.5194 | 18180.6381 | 590.9065 | 0.28321 | 42.7431 | 1.1574 | 0.02073 | 0.0002364 | 0.51249 | 0.77314 | {C855B1F9-E043-4F7B-B17F-9A4E0F007042} | 152201102 | PIKE CITY 1102 | circuit_breaker | 39.4384 | -120.9958 | PIKE CITY 1102circuit_breaker | 54 | 34 | 16077.7751 | 15132.7411 | 945.0339 | 15132.7411 | 945.0339 | 0.024585 | 0.0063558 | 1.7738 | 8.0865 | 1291 | 2.1559 | 540 | 0 | 0 | 9.403 | 96 | 0
North Coast | 3233 | 251 | 301.4389 | 423 | 390.7873 | 5 | 0.00012027 | 190.4357 | 9.6383 | 38.3631 | 228.9718 | 3.3437 | 1.8075 | 80.059 | 1.4686 | 0.020676 | 0.00052781 | 0.59338 | 0.77136 | {6ABCE308-047E-4F2E-99AB-65F7E6BEAD99} | 42561102 | FULTON 1102 | circuit_breaker | 38.497 | -122.7616 | FULTON 1102circuit_breaker | 144 | 256 | 20953.5814 | 7126.3044 | 13827.277 | 646.4219 | 444.5029 | 0.002639 | 0.00060134 | 1.201 | 84.6 | 762 | 0.10338 | 541 | 0 | 0 | 0.40167 | 303 | 0
Bay Area | 9385 | 21 | 29.7087 | 330 | 210.6758 | 38 | 6.8458e-05 | 332.8976 | 5.25 | 171.2468 | 2105.975 | 202.9397 | 3.8964 | 91.4837 | 1.2184 | 0.020657 | 0.00018218 | 0.063636 | 0.14102 | {B4DFAE90-941A-416C-9750-49FB5BAA5F55} | 42991105 | LAS GALLINAS A 1105 | 532 | 38.0249 | -122.5589 | LAS GALLINAS A 1105532 | 52 | 25 | 10569.2733 | 7102.1777 | 3467.0956 | 7030.3171 | 3229.0784 | 0.0069229 | 0.0026014 | 1.4147 | 8.6842 | 1477 | 0.78498 | 542 | 0 | 0 | 4.3684 | 2666 | 0
North Coast | 8799 | 272 | 363.3117 | 571 | 536.9186 | 60 | 0.0001065 | 156.731 | 10.6705 | 362.8295 | 4146.1235 | 289.2665 | 1.9128 | 19.3286 | 1.1027 | 0.020479 | 0.00061085 | 0.47636 | 0.67666 | {946410D9-CB53-4C0F-8ECA-3A3B9551D58C} | 43071102 | DUNBAR 1102 | 694641 | 38.328 | -122.5222 | DUNBAR 1102694641 | 78 | 51 | 8292.9342 | 6527.852 | 1765.0823 | 6527.852 | 1765.0823 | 0.036651 | 0.00639 | 1.3357 | 9.5167 | 659 | 1.2287 | 543 | 0 | 0 | 4.0562 | 1751 | 0
Central Valley | 997 | 35 | 95.0562 | 114 | 117.3244 | 31 | 5.7081e-05 | 321.7902 | 5.7408 | 25.5193 | 102.893 | 2.1456 | 14.0656 | 270.5184 | 1.2014 | 0.020396 | 0.00015435 | 0.30702 | 0.8102 | {03D991AF-6109-4C4F-9E0E-284738E05B02} | 162991103 | CORRAL 1103 | circuit_breaker | 38.1015 | -120.9263 | CORRAL 1103circuit_breaker | 538 | 1107 | 101206.9579 | 46165.5988 | 55041.3591 | 4196.3293 | 8098.016 | 0.004785 | 0.0017695 | 2.7159 | 3.6774 | 1569 | 0.63226 | 544 | 0 | 0 | 2.6075 | 879 | 0
Bay Area | 7324 | 23 | 38.9853 | 47 | 51.0433 | 15 | 5.4493e-05 | 295.7539 | 0.4989 | 122.735 | 1718.4336 | 2.1259 | 1.9344 | 138.534 | 1.3795 | 0.020366 | 4.2459e-05 | 0.48936 | 0.76377 | {F03C5A67-D53B-453A-A832-9C316BDAD400} | 43432102 | SILVERADO 2102 | 808 | 38.5191 | -122.3111 | SILVERADO 2102808 | 46 | 31 | 16019 | 7848.6714 | 8170.3286 | 1683.2795 | 4805.3945 | 0.00063689 | 0.0008174 | 1.695 | 3.1333 | 2304 | 0.30549 | 545 | 0 | 0 | 1.0459 | 2717 | 0
North Coast | 1385 | 21 | 38.0109 | 64 | 60.4145 | 18 | 6.2363e-05 | 366.0999 | 6.7437 | 625.2401 | 3628.7542 | 99.8082 | 6.802 | 417.3384 | 1.4186 | 0.020256 | 0.00010781 | 0.32812 | 0.62917 | {8F27A86E-670B-4331-ABF1-9BA9A6222879} | 42721107 | SONOMA 1107 | 126 | 38.2596 | -122.483 | SONOMA 1107126 | 312 | 344 | 60352.5483 | 35906.1491 | 24446.3992 | 6523.4267 | 1703.7072 | 0.0019405 | 0.0011225 | 1.81 | 3.5556 | 1817 | 0.36461 | 546 | 0 | 0 | 4.0535 | 2243 | 0
Central Valley | 9096 | 70 | 130.6721 | 279 | 205.2378 | 101 | 3.8304e-05 | 559.2191 | 80.7514 | 2942.8907 | 29518.8268 | 4232.1129 | 9.1247 | 1068.5163 | 1.7588 | 0.020247 | 0.0015348 | 0.2509 | 0.63669 | {37CEC619-9FFE-4BA7-9FD0-D8641CD59BBA} | 254432104 | COARSEGOLD 2104 | 6210 | 37.269 | -119.7137 | COARSEGOLD 21046210 | 61 | 29 | 20595.8109 | 17177.2503 | 3418.5606 | 17177.2503 | 3418.5606 | 0.15501 | 0.0038687 | 1.8667 | 2.7624 | 238 | 2.045 | 547 | 0 | 0 | 10.6734 | 1883 | 0
Sierra | 3520 | 23 | 32.4158 | 68 | 50.9633 | 7 | 8.8791e-05 | 207.4428 | 3.8447 | 26.1221 | 77.6529 | 0.43232 | 7.8856 | 55.6223 | 1.0528 | 0.020219 | 0.00020522 | 0.33824 | 0.63606 | {88F5CEC0-E8A5-4F1C-9B7B-06545C0D954B} | 152571101 | HORSESHOE 1101 | circuit_breaker | 38.744 | -121.1618 | HORSESHOE 1101circuit_breaker | 153 | 250 | 20426.3991 | 8647.7105 | 11778.6885 | 1020.0278 | 371.4493 | 0.0014365 | 0.00062153 | 1.4094 | 9.7143 | 1397 | 0.14153 | 548 | 0 | 0 | 0.63382 | 537 | 0
North Valley | 6034 | 1991 | 2680.0965 | 3683 | 3627.0818 | 324 | 0.00020775 | 91.9633 | 29.2929 | 1790.3589 | 35499.9828 | 1739.4449 | 1.1907 | 28.2265 | 1.1054 | 0.020184 | 0.0030859 | 0.54059 | 0.73891 | {C885D848-026E-4C6E-A0E7-D886450B2EC9} | 103271101 | ANTLER 1101 | 1378 | 40.8486 | -122.3311 | ANTLER 11011378 | 262 | 256 | 49680.0677 | 40324.448 | 9355.6197 | 39346.0984 | 9215.0767 | 0.99983 | 0.06731 | 1.3461 | 11.3673 | 102 | 6.5397 | 549 | 0 | 0 | 24.4485 | 1601 | 0
North Valley | 2644 | 474 | 819.2645 | 1585 | 1252.6172 | 245 | 0.00012556 | 405.0064 | 33.402 | 928.4822 | 6989.0793 | 765.2512 | 8.886 | 292.4599 | 1.1328 | 0.020039 | 0.0014338 | 0.29905 | 0.65404 | {430AA5A2-7BC0-4425-A05E-76360F269642} | 103561102 | STILLWATER 1102 | 1466 | 40.7127 | -122.2534 | STILLWATER 11021466 | 330 | 603 | 55260.4432 | 33018.7362 | 22241.707 | 32904.1054 | 22156.6955 | 0.35128 | 0.030762 | 1.7284 | 6.4694 | 263 | 4.9095 | 550 | 0 | 0 | 20.4457 | 415 | 0
Bay Area | 810 | 127 | 272.5372 | 441 | 468.0295 | 59 | 3.4691e-05 | 706.2158 | 3.7335 | 403.6859 | 2330.3423 | 48.2712 | 15.7303 | 682.553 | 1.439 | 0.020034 | 5.4849e-05 | 0.28798 | 0.58231 | {8DD57FAC-0D20-4DE3-898A-E73074144CC8} | 14662104 | TASSAJARA 2104 | 19042 | 37.7985 | -121.8732 | TASSAJARA 210419042 | 148 | 124 | 16368.1668 | 13671.8199 | 2696.3469 | 9296.9258 | 1449.7713 | 0.0032361 | 0.0020468 | 2.146 | 7.4746 | 2194 | 1.182 | 551 | 0 | 0 | 5.7768 | 2764 | 0
Bay Area | 3864 | 580 | 920.1154 | 1625 | 1514.6439 | 215 | 5.3097e-05 | 422.8087 | 2.1795 | 266.9258 | 2653.586 | 13.0073 | 1.5695 | 187.5113 | 1.4454 | 0.020016 | 8.9063e-05 | 0.35692 | 0.60748 | {D04F5483-38A6-4223-B65A-38F70E05486F} | 43432102 | SILVERADO 2102 | 34959 | 38.508 | -122.3749 | SILVERADO 210234959 | 271 | 160 | 69199.4418 | 42790.9314 | 26408.5104 | 41070.2397 | 24690.8187 | 0.019149 | 0.011416 | 1.5864 | 7.5581 | 1917 | 4.3034 | 552 | 0 | 0 | 25.5199 | 2253 | 0
North Valley | 7545 | 121 | 231.789 | 306 | 300.4702 | 48 | 0.00010528 | 174.2089 | 16.2848 | 73.3458 | 446.2405 | 17.6227 | 7.1424 | 49.6172 | 1.0389 | 0.02 | 0.0010061 | 0.39542 | 0.77142 | {D3D42978-28B3-47F8-B294-9DF0B2986540} | 103441101 | JESSUP 1101 | 1993 | 40.478 | -122.4215 | JESSUP 11011993 | 57 | 101 | 10617.8594 | 4781.8496 | 5836.0098 | 4413.0116 | 5611.4561 | 0.048293 | 0.0050533 | 1.9156 | 6.375 | 409 | 0.95999 | 553 | 0 | 0 | 2.7421 | 1589 | 0
Sierra | 9434 | 0 | 0 | 2 | 0.78622 | 2 | 6.5155e-05 | 429.2555 |  |  |  |  | 14.7732 | 187.9516 | 1.1582 | 0.019873 | 6.5155e-05 | 0 | 0 | {AAD63AEA-E006-40EA-8F1E-5C283AEC521A} | 152582109 | DEL MAR 2109 | 75802 | 38.8487 | -121.2314 | DEL MAR 210975802 | 20 | 1 | 687.5993 | 668.5307 | 19.0686 | 547.5648 | 19.0686 | 0.00013031 | 0.00013031 |  | 1 | 2090 | 0.039747 | 554 | 0 | 0 | 0.34024 | 636 | 0
North Valley | 5926 | 723 | 1218.591 | 2364 | 1837.4805 | 368 | 7.6117e-05 | 321.0537 | 38.9169 | 1692.7578 | 25921.9546 | 2282.706 | 6.2497 | 250.5688 | 1.2492 | 0.019859 | 0.0015814 | 0.30584 | 0.66319 | {614F599C-8E41-4F43-93F2-0A1EC10532ED} | 103401101 | GIRVAN 1101 | 1330 | 40.5176 | -122.5059 | GIRVAN 11011330 | 331 | 251 | 65368.2375 | 49991.4373 | 15376.8001 | 49037.4544 | 15352.9722 | 0.58196 | 0.028011 | 1.6855 | 6.4239 | 230 | 7.308 | 555 | 0 | 0 | 30.4705 | 2063 | 0
North Coast | 2330 | 547 | 750.6926 | 1148 | 1085.1174 | 218 | 6.0167e-05 | 339.435 | 1.2525 | 538.8175 | 9065.1433 | 47.9211 | 2.0641 | 155.7598 | 1.354 | 0.01978 | 7.4142e-05 | 0.47648 | 0.69181 | {C8D83F3A-CD64-4875-8687-B98C0D29D9E1} | 42891102 | GEYSERVILLE 1102 | 484 | 38.7132 | -122.8848 | GEYSERVILLE 1102484 | 491 | 442 | 131296.913 | 78386.0012 | 52910.9118 | 50631.555 | 26279.6906 | 0.016163 | 0.013116 | 1.3724 | 5.2661 | 2023 | 4.312 | 556 | 0 | 0 | 31.461 | 926 | 0
Central Coast | 1205 | 212 | 433.0356 | 407 | 529.7102 | 80 | 4.3236e-05 | 543.0371 | 24.3212 | 889.7018 | 4478.3208 | 142.8077 | 17.4761 | 392.8692 | 1.4895 | 0.019775 | 0.00052331 | 0.52088 | 0.8175 | {ED2FD62D-73A2-48E2-BABA-F5CBA9685A6D} | 183052113 | TEMPLETON 2113 | A08 | 35.4621 | -120.6221 | TEMPLETON 2113A08 | 399 | 474 | 68913.6396 | 39393.6221 | 29520.0175 | 13880.8278 | 5946.6161 | 0.041865 | 0.0034589 | 2.0426 | 5.0875 | 768 | 1.582 | 557 | 0 | 0 | 8.6251 | 2126 | 0
Central Valley | 6042 | 75 | 108.5498 | 240 | 166.5734 | 77 | 4.9752e-05 | 459.353 | 14.4003 | 896.9333 | 4781.6219 | 104.7738 | 11.3934 | 707.2752 | 1.4818 | 0.019755 | 0.0003262 | 0.3125 | 0.65166 | {5BFA9C05-674E-46C3-BAEE-B85172DBDA5E} | 163541101 | OLETA 1101 | 4768 | 38.4804 | -120.8599 | OLETA 11014768 | 133 | 85 | 35145.841 | 21913.0144 | 13232.8265 | 18073.0157 | 10972.6771 | 0.025117 | 0.0038309 | 1.4473 | 3.1169 | 1066 | 1.5211 | 558 | 0 | 0 | 11.23 | 1790 | 0
North Valley | 5246 | 7 | 13.4703 | 22 | 16.8173 | 12 | 2.7113e-05 | 811.2818 | 0.25635 | 50.1847 | 183.5414 | 0.14714 | 13.5524 | 2231.3302 | 1.549 | 0.019672 | 1.4456e-05 | 0.31818 | 0.80098 | {A9C774C3-1428-4B46-A99D-50AD5766C649} | 103331101 | CORNING 1101 | 87304 | 39.958 | -122.2908 | CORNING 110187304 | 115 | 90 | 31545.0017 | 23676.389 | 7868.6127 | 3402.7975 | 987.0215 | 0.00017348 | 0.00032536 | 1.9243 | 1.8333 | 2716 | 0.23607 | 559 | 0 | 0 | 2.1144 | 278 | 0
Central Coast | 1717 | 99 | 199.1291 | 378 | 377.771 | 32 | 5.6205e-05 | 334.8256 | 13.926 | 61.211 | 207.1131 | 5.2168 | 20.4096 | 117.5958 | 1.167 | 0.019633 | 0.00041198 | 0.2619 | 0.52712 | {1A1B9828-BB7B-4831-9B29-12F7B7720C90} | 183052111 | TEMPLETON 2111 | circuit_breaker | 35.5555 | -120.6799 | TEMPLETON 2111circuit_breaker | 199 | 101 | 23715.5624 | 17899.6887 | 5815.8737 | 2988.8542 | 2459.7263 | 0.013183 | 0.0017986 | 2.0114 | 11.8125 | 925 | 0.62824 | 560 | 0 | 0 | 1.8572 | 1841 | 0
Central Coast | 865 | 294 | 495.7452 | 931 | 882.6611 | 108 | 4.6771e-05 | 486.0912 | 4.7861 | 54.9 | 192.8356 | 2.7652 | 11.9522 | 110.7326 | 1.1412 | 0.019603 | 0.00011063 | 0.31579 | 0.56165 | {08118DBC-B5A1-4A52-A349-C7CD96194E0D} | 83242105 | MORGAN HILL 2105 | XR152 | 37.1047 | -121.6625 | MORGAN HILL 2105XR152 | 298 | 261 | 39509.2949 | 20565.0196 | 18944.2753 | 11909.7787 | 12103.3536 | 0.011948 | 0.0050513 | 1.6862 | 8.6204 | 1797 | 2.1171 | 561 | 0 | 0 | 7.4004 | 2286 | 0
North Coast | 4905 | 1089 | 1608.2837 | 1384 | 1757.1742 | 114 | 0.00012997 | 158.431 | 9.963 | 619.648 | 7243.3953 | 146.481 | 0.7695 | 53.8115 | 1.1978 | 0.019538 | 0.0007837 | 0.78685 | 0.91527 | {90C83132-41C0-4461-99CD-C9A5052731EB} | 42681102 | LAYTONVILLE 1102 | circuit_breaker | 39.6846 | -123.4772 | LAYTONVILLE 1102circuit_breaker | 128 | 89 | 25024.5852 | 20680.6827 | 4343.9025 | 16837.2871 | 1648.7 | 0.089342 | 0.014817 | 1.4768 | 12.1404 | 507 | 2.2274 | 562 | 0 | 0 | 10.4622 | 829 | 0
Sierra | 1351 | 405 | 769.5134 | 888 | 944.988 | 173 | 9.9747e-05 | 194.346 | 21.5189 | 279.2155 | 2161.9533 | 113.457 | 8.1113 | 315.9004 | 1.3009 | 0.019513 | 0.0010238 | 0.45608 | 0.81431 | {DB6EB455-6355-4800-B389-6B10D5AE927B} | 153612104 | CLARKSVILLE 2104 | 19772 | 38.7131 | -121.0456 | CLARKSVILLE 210419772 | 268 | 189 | 44802.9098 | 29518.3354 | 15284.5744 | 28983.153 | 14611.2219 | 0.17712 | 0.017256 | 1.9 | 5.1329 | 401 | 3.3758 | 563 | 0 | 0 | 18.0093 | 1444 | 0
North Coast | 5183 | 1050 | 1685.3123 | 1665 | 1981.07 | 266 | 0.00026427 | 65.1422 | 1.704 | 617.7544 | 15120.0288 | 70.4057 | 0.61 | 28.4166 | 1.1313 | 0.019499 | 0.0003781 | 0.63063 | 0.85071 | {6AEB3C8E-8034-4470-96BF-E9E68C89B3AC} | 192401101 | HOOPA 1101 | 3174 | 41.2232 | -123.6551 | HOOPA 11013174 | 247 | 311 | 46007.0698 | 35383.1104 | 10623.9593 | 28229.9925 | 3854.9879 | 0.10058 | 0.070295 | 1.6051 | 6.2594 | 971 | 5.1867 | 564 | 0 | 0 | 17.5413 | 549 | 0
North Coast | 2710 | 1301 | 1883.4748 | 2474 | 2409.736 | 324 | 0.00011483 | 163.2765 | 9.5203 | 669.7274 | 9547.6997 | 389.0182 | 4.5325 | 118.9915 | 1.1949 | 0.019401 | 0.0003139 | 0.52587 | 0.78161 | {48F0B79D-EE60-460B-8BC5-9B5CCB492CAC} | 43411101 | CALPELLA 1101 | 1204 | 39.2478 | -123.2086 | CALPELLA 11011204 | 513 | 573 | 107024.9456 | 63297.3095 | 43727.636 | 47939.0001 | 31388.122 | 0.1017 | 0.037205 | 1.4477 | 7.6358 | 1096 | 6.2858 | 565 | 0 | 0 | 29.7879 | 1824 | 0
Bay Area | 383 | 152 | 312.7216 | 555 | 449.1355 | 152 | 1.2097e-05 | 922.9927 | 3.0279 | 732.6563 | 3826.1913 | 31.1999 | 14.2912 | 1124.6078 | 1.5705 | 0.019343 | 3.3666e-05 | 0.27387 | 0.69627 | {F2B446A8-3224-4354-BA23-539A5AFE1F0F} | 13751102 | VASCO 1102 | MR176 | 37.6642 | -121.7329 | VASCO 1102MR176 | 327 | 222 | 87611.3455 | 68431.2769 | 19180.0686 | 62221.1335 | 18126.4336 | 0.0051173 | 0.0018387 | 2.0574 | 3.6513 | 2418 | 2.9401 | 566 | 0 | 0 | 38.6624 | 2555 | 0
North Coast | 1870 | 15 | 35.4314 | 56 | 61.5474 | 9 | 9.7112e-05 | 192.934 | 1.4741 | 35.5137 | 313.1463 | 1.008 | 4.0364 | 32.6394 | 1.0959 | 0.019297 | 0.00011659 | 0.26786 | 0.57568 | {A0925B55-2E02-42A8-B141-C53A4CA4086F} | 42721105 | SONOMA 1105 | 404 | 38.2708 | -122.4182 | SONOMA 1105404 | 303 | 374 | 56778.6675 | 28928.7411 | 27849.9265 | 18092.5178 | 16993.358 | 0.0010493 | 0.00087401 | 2.3621 | 6.2222 | 1765 | 0.17367 | 567 | 0 | 0 | 11.2422 | 610 | 0
North Coast | 4539 | 790 | 916.5778 | 1429 | 1247.497 | 219 | 0.00010531 | 218.7182 | 1.2074 | 238.2843 | 3845.9585 | 15.2935 | 3.1857 | 107.0842 | 1.3112 | 0.019256 | 0.00011423 | 0.55283 | 0.73473 | {BD574B29-15C8-4B0E-8A1E-85F74B10E15F} | 192411101 | LOW GAP 1101 | 37498 | 40.2998 | -123.3426 | LOW GAP 110137498 | 168 | 170 | 29623.6668 | 26210.4026 | 3413.2642 | 26210.4026 | 3413.2642 | 0.025017 | 0.023064 | 1.1602 | 6.5251 | 1778 | 4.217 | 568 | 0 | 0 | 16.2864 | 1013 | 0
Bay Area | 6270 | 11 | 35.5826 | 13 | 36.6894 | 6 | 2.3357e-05 | 945.0197 | 0.34195 | 61.9031 | 211.9595 | 0.14432 | 11.2496 | 580.3122 | 1.2618 | 0.019216 | 1.6689e-05 | 0.84615 | 0.96983 | {E6EA8FFD-93FC-4EE2-B4B3-05C67BB86274} | 42301101 | TULUCAY 1101 | 628 | 38.2231 | -122.256 | TULUCAY 1101628 | 95 | 33 | 12736.4589 | 12014.0867 | 722.3722 | 3826.9754 | 189.8043 | 0.00010014 | 0.00014014 | 3.2348 | 2.1667 | 2668 | 0.1153 | 569 | 0 | 0 | 2.378 | 402 | 0
Bay Area | 1910 | 8 | 14.2093 | 56 | 40.9766 | 15 | 4.2422e-05 | 497.022 | 2.2205 | 61.9968 | 363.8628 | 1.5477 | 7.7966 | 305.6446 | 1.6323 | 0.019154 | 6.0518e-05 | 0.14286 | 0.34677 | {B9DFD3D4-5938-44FA-A6FD-F2608641C707} | 43432102 | SILVERADO 2102 | 98998 | 38.4714 | -122.3993 | SILVERADO 210298998 | 475 | 408 | 59450.9185 | 45845.8745 | 13605.044 | 4139.5096 | 1309.1575 | 0.00090777 | 0.00063633 | 1.7762 | 3.7333 | 2135 | 0.28731 | 570 | 0 | 0 | 2.5722 | 2569 | 0
North Valley | 1207 | 1316 | 1977.6025 | 2185 | 2433.693 | 333 | 0.00017955 | 148.5152 | 14.4419 | 571.8732 | 4047.1845 | 154.7957 | 7.3184 | 144.2183 | 1.1306 | 0.019118 | 0.0011752 | 0.60229 | 0.81259 | {9F446B40-007A-417C-9085-68FA864397E1} | 102541102 | VOLTA 1102 | 37350 | 40.5093 | -121.9584 | VOLTA 110237350 | 376 | 342 | 61202.8976 | 39083.1019 | 22119.7957 | 39083.1019 | 22119.7957 | 0.39133 | 0.059791 | 1.5027 | 6.5616 | 335 | 6.3663 | 571 | 0 | 0 | 24.2851 | 2147 | 0
Central Valley | 2295 | 115 | 199.9183 | 933 | 433.7359 | 240 | 3.8007e-05 | 504.2386 | 8.4183 | 768.4821 | 4501.0725 | 95.4193 | 11.5364 | 538.8131 | 1.4955 | 0.019027 | 0.00015506 | 0.12326 | 0.46092 | {31882BA6-5D81-4512-9217-A61120B12235} | 163341101 | CLAY 1101 | 13442 | 38.3516 | -120.9352 | CLAY 110113442 | 404 | 684 | 84710.1098 | 49967.0249 | 34743.085 | 40782.5793 | 18451.3525 | 0.037214 | 0.0091218 | 1.7384 | 3.8875 | 1565 | 4.5666 | 572 | 0 | 0 | 25.3411 | 1472 | 0
Sierra | 7629 | 90 | 243.4262 | 244 | 299.3282 | 35 | 3.6065e-05 | 524.0932 | 5.1391 | 702.6842 | 3585.2412 | 70.2104 | 6.5282 | 474.2023 | 1.2628 | 0.018955 | 9.1081e-05 | 0.36885 | 0.81324 | {EF947682-77F0-46FF-B597-C974CCFEC84A} | 152921101 | BROWNS VALLEY 1101 | 36622 | 39.225 | -121.4231 | BROWNS VALLEY 110136622 | 49 | 20 | 17869.6508 | 13781.9233 | 4087.7275 | 6467.9583 | 1258.9452 | 0.0031878 | 0.0012623 | 2.7047 | 6.9714 | 1902 | 0.66343 | 573 | 0 | 0 | 4.019 | 180 | 0
North Valley | 2436 | 1260 | 1567.3287 | 3016 | 2396.5278 | 367 | 9.1842e-05 | 207.029 | 5.2485 | 2306.685 | 53995.815 | 444.5567 | 1.6644 | 65.343 | 1.1308 | 0.018875 | 0.00027475 | 0.41777 | 0.654 | {383E38F1-9CAC-409E-B20B-DAC5E1331447} | 103321101 | CEDAR CREEK 1101 | 1656 | 40.8458 | -121.9095 | CEDAR CREEK 11011656 | 261 | 266 | 63628.849 | 51035.8707 | 12592.9783 | 51035.8707 | 12592.9783 | 0.10083 | 0.033706 | 1.2439 | 8.218 | 1189 | 6.9273 | 574 | 0 | 0 | 31.7122 | 2494 | 0
North Coast | 2491 | 609 | 832.9259 | 1521 | 1300.6495 | 236 | 6.4422e-05 | 288.4864 | 4.1433 | 170.8942 | 1866.2169 | 26.4906 | 3.911 | 137.1031 | 1.2379 | 0.01886 | 0.00013815 | 0.40039 | 0.64039 | {1B09A511-4056-470A-B00D-4FB4522380B2} | 42561102 | FULTON 1102 | 287172 | 38.579 | -122.7705 | FULTON 1102287172 | 352 | 295 | 73018.0479 | 42798.2234 | 30219.8245 | 29351.4047 | 21099.6148 | 0.032604 | 0.015204 | 1.3677 | 6.4449 | 1642 | 4.4509 | 575 | 0 | 0 | 18.2381 | 1652 | 0
Sierra | 77 | 45 | 106.0275 | 160 | 133.0653 | 60 | 2.1378e-05 | 900.0325 | 17.0308 | 567.4237 | 1947.3447 | 59.4663 | 20.3128 | 607.0981 | 1.3551 | 0.018856 | 0.00013661 | 0.28125 | 0.79681 | {B814ECD9-6160-4057-8AF0-345725EF4AA1} | 152811105 | WHEATLAND 1105 | 91170 | 39.0237 | -121.4018 | WHEATLAND 110591170 | 524 | 390 | 126919.0223 | 85775.1349 | 41143.8874 | 15619.5143 | 8888.3689 | 0.0081968 | 0.0012827 | 2.3562 | 2.6667 | 1655 | 1.1314 | 576 | 0 | 0 | 9.7055 | 865 | 0
North Coast | 6074 | 761 | 1264.235 | 1154 | 1468.4177 | 98 | 0.00017187 | 106.1931 | 5.5379 | 205.682 | 1744.8009 | 17.4102 | 0.4802 | 34.4295 | 1.0784 | 0.01877 | 0.00053339 | 0.65945 | 0.86095 | {19BB688C-7539-4331-8ED9-2B0221333B05} | 42851121 | FORT ROSS 1121 | 70288 | 38.5287 | -123.1574 | FORT ROSS 112170288 | 129 | 100 | 28474.6239 | 18893.0241 | 9581.5998 | 18893.0241 | 9581.5998 | 0.052272 | 0.016844 | 1.6613 | 11.7755 | 753 | 1.8394 | 577 | 0 | 0 | 11.7396 | 2357 | 0
North Coast | 528 | 1145 | 1384.5232 | 1702 | 1661.514 | 242 | 0.00010946 | 153.3613 | 2.623 | 554.1834 | 8382.0297 | 98.0731 | 0.61413 | 56.6275 | 1.1597 | 0.018718 | 0.00020779 | 0.67274 | 0.83329 | {F3EC175B-7845-4CA9-AB09-DEC2A3B40256} | 192321121 | FORT SEWARD 1121 | 1602 | 40.1834 | -123.5765 | FORT SEWARD 11211602 | 122 | 100 | 38973.1362 | 36343.227 | 2629.9092 | 27815.4127 | 2021.7032 | 0.050286 | 0.02649 | 1.2092 | 7.0331 | 1388 | 4.5297 | 578 | 0 | 0 | 17.2837 | 1701 | 0
North Coast | 8265 | 214 | 248.8204 | 313 | 298.7616 | 25 | 0.00018714 | 103.7822 | 9.1719 | 51.8899 | 450.7217 | 5.3181 | 1.9187 | 15.8661 | 1.0338 | 0.018684 | 0.0010357 | 0.68371 | 0.83284 | {BEE7985F-2DE6-4F21-8751-BD293BFF69B9} | 43141101 | MIDDLETOWN 1101 | 614 | 38.8266 | -122.7269 | MIDDLETOWN 1101614 | 39 | 132 | 9225.1851 | 2239.5087 | 6985.6764 | 2239.5087 | 6985.6764 | 0.025894 | 0.0046784 | 1.1627 | 12.52 | 391 | 0.46709 | 579 | 0 | 0 | 1.3916 | 1720 | 0
Bay Area | 6166 | 82 | 189.0716 | 508 | 430.1462 | 49 | 7.0809e-05 | 462.9243 | 6.0666 | 101.0276 | 437.6594 | 21.732 | 9.7037 | 242.1428 | 1.1732 | 0.018652 | 0.00012642 | 0.16142 | 0.43955 | {3C13801D-CC64-4F61-AF69-C39F394BB25E} | 14662113 | TASSAJARA 2113 | MR276 | 37.7625 | -121.984 | TASSAJARA 2113MR276 | 68 | 59 | 9345.4855 | 6265.9535 | 3079.532 | 6095.1274 | 2863.1031 | 0.0061945 | 0.0034697 | 2.3058 | 10.3673 | 1717 | 0.91393 | 580 | 0 | 0 | 3.7873 | 2039 | 0
North Valley | 6039 | 172 | 314.8227 | 818 | 538.0956 | 110 | 4.1295e-05 | 528.8748 | 17.9506 | 150.6512 | 789.1488 | 35.3276 | 17.29 | 100.0631 | 1.158 | 0.018609 | 0.00035763 | 0.21027 | 0.58507 | {B74488FF-9B39-410B-9AAC-30106EC9509F} | 102911107 | WYANDOTTE 1107 | 96390 | 39.4921 | -121.4557 | WYANDOTTE 110796390 | 207 | 252 | 33201.8595 | 16389.5684 | 16812.2911 | 13317.923 | 13741.73 | 0.039339 | 0.0045424 | 1.8304 | 7.4364 | 1003 | 2.047 | 581 | 0 | 0 | 8.2754 | 730 | 0
North Coast | 3929 | 117 | 164.4554 | 258 | 234.2937 | 35 | 7.6448e-05 | 244.9438 | 38.4168 | 359.9087 | 1406.3478 | 112.516 | 12.3362 | 95.3345 | 1.0686 | 0.018568 | 0.0013205 | 0.45349 | 0.70192 | {3CA4A42E-51F1-49B1-95E4-11CB39229D26} | 192291121 | CARLOTTA 1121 | circuit_breaker | 40.541 | -124.0638 | CARLOTTA 1121circuit_breaker | 385 | 525 | 58229.7983 | 37519.4983 | 20710.3 | 3350.89 | 1209.1025 | 0.046217 | 0.0026757 | 1.4056 | 7.3714 | 289 | 0.64987 | 582 | 0 | 0 | 2.0821 | 566 | 0
Central Coast | 8874 | 0 | 0 | 3 | 0.88256 | 1 | 0.00038903 | 47.6244 | 22.6129 | 298.8874 | 2114.3518 | 48.2119 | 16.0907 | 76.3723 | 1.5133 | 0.018527 | 0.008797 | 0 | 0 | {CBB88C85-EC74-4A88-A152-9F1C6F5CED0E} | 182391103 | OILFIELDS 1103 | N46 | 35.7811 | -120.9892 | OILFIELDS 1103N46 | 59 | 13 | 9591.7121 | 9360.626 | 231.0861 | 9360.626 | 231.0861 | 0.008797 | 0.00038903 |  | 3 | 13 | 0.018527 | 583 | 0 | 0 | 5.8164 | 1702 | 0
Central Valley | 8716 | 0 | 0 | 35 | 14.406 | 3 | 1.679e-05 | 1462.2239 |  |  |  |  | 3.2323 | 1980.0798 | 1.6888 | 0.01839 | 1.679e-05 | 0 | 0 | {00D1CA6B-BA0D-48A2-AF6B-44F02D16A6FD} | 253642101 | POSO MOUNTAIN 2101 | 3990 | 35.5581 | -118.9767 | POSO MOUNTAIN 21013990 | 29 | 18 | 9949.8183 | 8936.2242 | 1013.5942 | 6347.4219 | 159.886 | 5.037e-05 | 5.037e-05 |  | 11.6667 | 2665 | 0.055169 | 584 | 0 | 0 | 3.9441 | 847 | 0
North Valley | 2401 | 20 | 29.9728 | 43 | 42.8009 | 14 | 5.077e-05 | 388.1201 | 20.641 | 723.1341 | 6156.7852 | 214.315 | 10.3611 | 351.5078 | 1.5616 | 0.018353 | 0.00058529 | 0.46512 | 0.70028 | {8854FD88-45EB-44A4-AE38-EE1BF37E09D7} | 102541101 | VOLTA 1101 | 80454 | 40.4341 | -121.8714 | VOLTA 110180454 | 325 | 292 | 71849.0246 | 51726.8369 | 20122.1876 | 50010.0284 | 18900.802 | 0.0081941 | 0.00071078 | 1.4986 | 3.0714 | 686 | 0.25694 | 585 | 0 | 0 | 31.0748 | 806 | 0
North Coast | 3229 | 50 | 94.7063 | 199 | 143.5513 | 47 | 8.5857e-05 | 173.3227 | 1.5134 | 6.7479 | 29.6788 | 0.45499 | 4.3771 | 64.0482 | 1.2144 | 0.018272 | 0.00011862 | 0.25126 | 0.65974 | {01484F25-B16D-4119-BFC6-A19899DBC158} | 43191102 | REDBUD 1102 | 510 | 38.97 | -122.6643 | REDBUD 1102510 | 179 | 693 | 41891.7718 | 12965.106 | 28926.6658 | 5477.4083 | 10966.2121 | 0.005575 | 0.0040353 | 1.8941 | 4.234 | 1751 | 0.8588 | 586 | 0 | 0 | 3.4035 | 2409 | 0
North Coast | 6987 | 625 | 783.8629 | 1493 | 1208.1798 | 194 | 5.5924e-05 | 275.5323 | 4.1949 | 986.6344 | 13052.0058 | 132.0261 | 5.6937 | 303.6633 | 1.3759 | 0.01826 | 0.0001515 | 0.41862 | 0.6488 | {5F898AAB-A822-418A-A7D3-2566EAF134B5} | 42871101 | UPPER LAKE 1101 | 1276 | 39.1586 | -122.989 | UPPER LAKE 11011276 | 151 | 278 | 42234.7914 | 20671.4818 | 21563.3096 | 20671.4818 | 21563.3096 | 0.029391 | 0.010849 | 1.2542 | 7.6959 | 1584 | 3.5424 | 587 | 0 | 0 | 12.8447 | 2599 | 0
North Coast | 5777 | 6 | 8.1824 | 20 | 16.8733 | 4 | 0.00013934 | 136.8961 | 0.034584 | 2.2011 | 35.9391 | 0.003008 | 2.4148 | 21.5903 | 1.0636 | 0.018258 | 7.1203e-05 | 0.3 | 0.48493 | {FC698F49-08CB-4375-B278-3C062280B4C5} | 42891101 | GEYSERVILLE 1101 | 482 | 38.7004 | -122.9575 | GEYSERVILLE 1101482 | 63 | 65 | 12220.2853 | 6000.7291 | 6219.5562 | 352.7494 | 209.1756 | 0.00028481 | 0.00055736 | 1.3637 | 5 | 2047 | 0.073031 | 588 | 0 | 0 | 0.21919 | 2166 | 0
North Coast | 3084 | 263 | 398.2348 | 561 | 507.1548 | 134 | 5.0476e-05 | 379.6181 | 2.6249 | 1338.9317 | 17806.6492 | 131.1331 | 4.6935 | 620.2841 | 1.6657 | 0.018254 | 9.1729e-05 | 0.46881 | 0.78523 | {CF814E69-077B-44BB-9617-D51226ABE508} | 42251101 | HOPLAND 1101 | 768 | 38.9695 | -123.1026 | HOPLAND 1101768 | 125 | 119 | 45042.5623 | 32085.8687 | 12956.6937 | 26862.8023 | 7068.0495 | 0.012292 | 0.0067638 | 1.5142 | 4.1866 | 1899 | 2.4461 | 589 | 0 | 0 | 16.6918 | 599 | 0
North Coast | 5197 | 375 | 507.9902 | 571 | 601.6454 | 34 | 0.00016911 | 89.5945 | 1.7502 | 18.3805 | 129.1631 | 0.46273 | 2.151 | 21.2934 | 1.0501 | 0.018209 | 0.00025029 | 0.65674 | 0.84433 | {9C63EAAD-55B5-4DD4-BF3E-81AFCB311847} | 192321121 | FORT SEWARD 1121 | 1663 | 40.172 | -123.607 | FORT SEWARD 11211663 | 33 | 106 | 6313.6789 | 3125.6698 | 3188.0092 | 3125.6698 | 3188.0092 | 0.0085098 | 0.0057496 | 1.3546 | 16.7941 | 1248 | 0.6191 | 590 | 0 | 0 | 1.9422 | 1227 | 0
North Valley | 4569 | 371 | 686.9137 | 953 | 895.9277 | 139 | 5.4338e-05 | 332.3281 | 11.5954 | 40.5381 | 172.0254 | 5.6693 | 11.7607 | 64.1465 | 1.1331 | 0.018142 | 0.00028605 | 0.3893 | 0.76671 | {260D122D-D38C-484D-AE9F-D25E4FA8C6F8} | 102911103 | WYANDOTTE 1103 | 1504 | 39.5047 | -121.4985 | WYANDOTTE 11031504 | 368 | 415 | 45421.4614 | 23694.4018 | 21727.0595 | 16411.1206 | 15842.5971 | 0.039762 | 0.007553 | 1.8515 | 6.8561 | 1159 | 2.5217 | 591 | 0 | 0 | 10.1974 | 1096 | 0
North Valley | 7733 | 199 | 340.5584 | 731 | 488.3767 | 152 | 5.0098e-05 | 390.372 | 15.9656 | 951.6164 | 5841.186 | 381.7978 | 12.4307 | 331.7229 | 1.3241 | 0.018089 | 0.0003025 | 0.27223 | 0.69733 | {C9648835-EB5A-442A-856F-5456F572C3DC} | 103191101 | BANGOR 1101 | circuit_breaker | 39.3877 | -121.4033 | BANGOR 1101circuit_breaker | 225 | 204 | 46265.3946 | 34104.446 | 12160.9486 | 28650.9927 | 10889.924 | 0.045979 | 0.0076148 | 1.7113 | 4.8092 | 1115 | 2.7495 | 592 | 0 | 0 | 17.8029 | 1648 | 0
Bay Area | 7722 | 233 | 333.2899 | 896 | 626.4334 | 135 | 4.7025e-05 | 426.6515 | 8.5442 | 323.4837 | 2253.3727 | 53.1135 | 8.9751 | 286.2525 | 1.3024 | 0.018065 | 0.00021512 | 0.26004 | 0.53204 | {CFFE2061-0111-499A-9D10-C50262E92A10} | 43051101 | MONTICELLO 1101 | 718 | 38.3768 | -122.1841 | MONTICELLO 1101718 | 324 | 262 | 71594.1578 | 47865.0064 | 23729.1514 | 42515.7179 | 22168.2875 | 0.029041 | 0.0063484 | 1.4304 | 6.637 | 1360 | 2.4388 | 593 | 0 | 0 | 26.418 | 1132 | 0
Central Valley | 3694 | 12 | 37.0613 | 325 | 114.1476 | 111 | 3.1582e-05 | 552.4749 | 22.1639 | 10054.4978 | 64670.329 | 2004.8101 | 15.4548 | 578.5411 | 1.3563 | 0.018011 | 0.00034896 | 0.036923 | 0.32468 | {D468A32E-4500-4D2C-80DA-85F74A9A6EF3} | 252192101 | BEAR VALLEY 2101 | 4500 | 37.4304 | -120.0991 | BEAR VALLEY 21014500 | 587 | 508 | 190154.7833 | 131623.5309 | 58531.2523 | 34089.7521 | 21160.2163 | 0.038734 | 0.0035056 | 3.0884 | 2.9279 | 1013 | 1.9992 | 594 | 0 | 0 | 21.1824 | 778 | 0
North Coast | 21 | 79 | 142.2526 | 176 | 185.0663 | 28 | 6.8827e-05 | 247.0451 | 27.472 | 186.7329 | 2500.5361 | 133.374 | 9.1205 | 105.6973 | 1.1896 | 0.018004 | 0.00011855 | 0.44886 | 0.76866 | {E5E424DC-C8C0-4A20-B0C0-11A950F19719} | 42751113 | FITCH MOUNTAIN 1113 | 154 | 38.6306 | -122.8728 | FITCH MOUNTAIN 1113154 | 329 | 432 | 57698.5807 | 30573.1342 | 27125.4465 | 2751.1631 | 4777.2046 | 0.0033194 | 0.0019272 | 1.8007 | 6.2857 | 1753 | 0.50412 | 595 | 0 | 0 | 1.7095 | 1553 | 0
Bay Area | 8766 | 61 | 171.7224 | 219 | 269.6028 | 29 | 2.0171e-05 | 798.2279 | 12.11 | 648.9137 | 2555.4344 | 40.3507 | 16.8722 | 437.3276 | 1.4749 | 0.017974 | 0.0001003 | 0.27854 | 0.63695 | {771EB351-5AA3-41C4-91D1-E5FF75A7272A} | 14241101 | SUNOL 1101 | 8721 | 37.5663 | -121.8831 | SUNOL 11018721 | 37 | 27 | 7283.932 | 5007.3028 | 2276.6292 | 4212.4471 | 1119.8836 | 0.0029086 | 0.00058497 | 2.8151 | 7.5517 | 1848 | 0.52124 | 596 | 0 | 0 | 2.6175 | 1697 | 0
Bay Area | 4993 | 265 | 425.2647 | 618 | 623.7388 | 37 | 0.00011221 | 152.6312 | 19.1318 | 187.6845 | 3048.1657 | 158.6163 | 2.875 | 32.2444 | 1.1034 | 0.017971 | 0.0012571 | 0.4288 | 0.6818 | {B6278051-6E54-4737-9502-59CAD0AD2394} | 43432104 | SILVERADO 2104 | 722 | 38.5448 | -122.4757 | SILVERADO 2104722 | 139 | 245 | 25316.2935 | 11871.204 | 13445.0895 | 11871.204 | 13445.0895 | 0.046512 | 0.0041518 | 1.6048 | 16.7027 | 303 | 0.66491 | 597 | 0 | 0 | 7.3764 | 343 | 0
Sierra | 4162 | 477 | 848.3527 | 1131 | 1114.8379 | 226 | 5.1602e-05 | 413.4979 | 16.3961 | 203.3338 | 1056.1792 | 39.7933 | 11.9344 | 124.6382 | 1.3122 | 0.017946 | 0.00033425 | 0.42175 | 0.76097 | {2611646A-C593-4185-9486-0AA063D164D0} | 153132105 | NARROWS 2105 | circuit_breaker | 39.2358 | -121.269 | NARROWS 2105circuit_breaker | 565 | 548 | 96713.169 | 58146.9701 | 38566.199 | 57069.9064 | 38050.4633 | 0.07554 | 0.011662 | 1.7785 | 5.0044 | 1046 | 4.0559 | 598 | 0 | 0 | 35.4616 | 1412 | 0
North Coast | 7235 | 38 | 48.4094 | 64 | 62.8247 | 11 | 6.0186e-05 | 372.329 | 0.22707 | 5.6691 | 35.1866 | 0.053603 | 5.4767 | 59.7471 | 1.2166 | 0.017937 | 3.2059e-05 | 0.59375 | 0.77055 | {CC976BA1-8774-4271-B2E6-D5339363F132} | 42821102 | CLOVERDALE 1102 | 262 | 38.7977 | -122.991 | CLOVERDALE 1102262 | 108 | 96 | 21879.6251 | 9248.1499 | 12631.4751 | 947.9156 | 1778.124 | 0.00035265 | 0.00066204 | 1.2739 | 5.8182 | 2441 | 0.19731 | 599 | 0 | 0 | 0.58901 | 1405 | 0
Central Valley | 2260 | 1075 | 1508.6024 | 2719 | 2280.5469 | 369 | 6.3031e-05 | 285.8664 | 6.3441 | 74.1551 | 519.8638 | 10.0227 | 7.8084 | 106.9377 | 1.2929 | 0.017905 | 0.00021688 | 0.39537 | 0.66151 | {A6A3BCCC-F462-4ECA-85D9-4927341E1902} | 252531103 | SAN JOAQUIN #3 1103 | circuit_breaker | 37.2539 | -119.5194 | SAN JOAQUIN #3 1103circuit_breaker | 408 | 451 | 70440.3232 | 45356.6535 | 25083.6697 | 45356.6535 | 25083.6697 | 0.080027 | 0.023258 | 1.4034 | 7.3686 | 1353 | 6.6069 | 600 | 0 | 0 | 28.1833 | 113 | 0
Central Coast | 5408 | 109 | 162.3491 | 533 | 440.1982 | 92 | 0.00021254 | 73.6615 | 1.5415 | 564.4303 | 3468.5497 | 15.1873 | 6.042 | 356.2167 | 1.286 | 0.017835 | 0.00035146 | 0.2045 | 0.36881 | {CDC11A25-DBD9-42BE-AA95-70647385571E} | 182721101 | SANTA YNEZ 1101 | Y52 | 34.5981 | -120.0296 | SANTA YNEZ 1101Y52 | 209 | 161 | 44112.512 | 38825.6098 | 5286.9022 | 36116.1135 | 4717.4034 | 0.032335 | 0.019554 | 1.4894 | 5.7935 | 1011 | 1.6408 | 601 | 0 | 0 | 22.4415 | 710 | 0
Sierra | 1069 | 1225 | 2001.1535 | 4418 | 3254.3564 | 597 | 6.5407e-05 | 378.7488 | 19.2778 | 382.9197 | 3858.7428 | 250.9516 | 8.8167 | 198.3156 | 1.2938 | 0.017739 | 0.00068651 | 0.27727 | 0.61492 | {5AF8F290-EBD8-4203-A9EE-DEB7B6BE68A5} | 152031103 | GRASS VALLEY 1103 | 2180 | 39.1524 | -121.0775 | GRASS VALLEY 11032180 | 632 | 552 | 117192.0527 | 70305.7957 | 46886.257 | 70305.7957 | 46886.257 | 0.40985 | 0.039048 | 1.6336 | 7.4003 | 577 | 10.5904 | 602 | 0 | 0 | 43.686 | 1479 | 0
Bay Area | 4383 | 0 | 0 | 2 | 0.91147 | 1 | 2.119e-05 | 836.9413 |  |  |  |  | 16.4403 | 730.7745 | 1.5774 | 0.017735 | 2.119e-05 | 0 | 0 | {7B2B399A-3CEE-4766-BF6E-D0BC89205982} | 14652106 | TIDEWATER 2106 | 57926 | 38.0335 | -122.0731 | TIDEWATER 210657926 | 197 | 278 | 29296.938 | 18927.2283 | 10369.7097 | 0 | 12.9316 | 2.119e-05 | 2.119e-05 |  | 2 | 2584 | 0.017735 | 603 | 0 | 0 | 0 | 2254 | 0
North Coast | 1080 | 77 | 156.6974 | 394 | 244.2569 | 84 | 3.7568e-05 | 528.4012 | 7.5497 | 8.9765 | 23.0206 | 1.6019 | 8.645 | 192.8906 | 0.86612 | 0.017678 | 0.00011733 | 0.19543 | 0.64153 | {D71C2E21-7CE4-4721-8677-0076FC6B52D7} | 43361102 | HIGHLANDS 1102 | 75140 | 38.9543 | -122.6103 | HIGHLANDS 110275140 | 527 | 1901 | 120117.0637 | 32224.2832 | 87892.7805 | 13187.2724 | 35318.5253 | 0.009856 | 0.0031557 | 2.035 | 4.6905 | 1759 | 1.485 | 604 | 0 | 0 | 8.1942 | 1951 | 0
North Coast | 1818 | 2965 | 3824.3683 | 4584 | 4675.8286 | 427 | 0.00013602 | 137.7046 | 60.9664 | 1702.1564 | 34665.6592 | 3108.7084 | 3.3045 | 104.0722 | 1.1977 | 0.017676 | 0.0043276 | 0.64682 | 0.8179 | {CB616978-006D-49B9-885E-104BFB9EEDAF} | 43311102 | KONOCTI 1102 | circuit_breaker | 38.9324 | -122.741 | KONOCTI 1102circuit_breaker | 592 | 642 | 121536.3559 | 66951.8529 | 54584.5029 | 52446.7628 | 38572.9962 | 1.8479 | 0.058081 | 1.2898 | 10.7354 | 51 | 7.5478 | 605 | 0 | 0 | 32.5889 | 2588 | 0
Bay Area | 7857 | 111 | 203.6559 | 589 | 506.2237 | 100 | 5.8264e-05 | 369.185 | 3.8886 | 176.1789 | 2233.9491 | 24.3688 | 1.6863 | 131.2425 | 1.2463 | 0.017554 | 0.00013436 | 0.18846 | 0.4023 | {72A0B7D1-514D-4E97-9F9E-307ABD8141BA} | 42021112 | NAPA 1112 | 1723 | 38.2972 | -122.2283 | NAPA 11121723 | 128 | 127 | 32676.1691 | 18404.557 | 14271.6121 | 15407.0792 | 11764.9153 | 0.013436 | 0.0058264 | 1.8347 | 5.89 | 1675 | 1.7554 | 606 | 0 | 0 | 9.5735 | 2348 | 0
Central Valley | 7027 | 0 | 0 | 40 | 10.6865 | 18 | 1.5589e-05 | 1033.3453 | 19.4719 | 2108.7728 | 13318.624 | 1070.3202 | 14.3698 | 1030.7694 | 1.808 | 0.017547 | 0.00020791 | 0 | 0 | {755777FC-6215-430E-868E-B21D92A14A1A} | 252941107 | TIVY VALLEY 1107 | 7380 | 36.7051 | -119.3751 | TIVY VALLEY 11077380 | 309 | 293 | 62776.0426 | 45102.1031 | 17673.9395 | 18290.2186 | 8734.3587 | 0.0037424 | 0.0002806 |  | 2.2222 | 1387 | 0.31585 | 607 | 0 | 0 | 11.365 | 798 | 0
North Coast | 9383 | 19 | 29.441 | 20 | 29.8681 | 3 | 0.00010495 | 166.9859 | 0.78052 | 3311.2317 | 51560.2695 | 40.2438 | 1.8894 | 127.8982 | 1.0531 | 0.017525 | 9.5639e-05 | 0.95 | 0.9857 | {5598BC99-B84D-494C-B070-C710E85A4555} | 48011146 | CALPINE 1146 | 400 | 38.8266 | -122.8043 | CALPINE 1146400 | 9 | 0 | 5057.3021 | 5057.3021 | 0 | 5057.3021 | 0 | 0.00028692 | 0.00031484 | 1.5495 | 6.6667 | 1876 | 0.052574 | 608 | 0 | 0 | 3.1425 | 228 | 0
Central Coast | 813 | 232 | 375.9466 | 499 | 509.216 | 82 | 4.5196e-05 | 423.8401 | 3.8645 | 553.2857 | 2738.9449 | 7.7455 | 25.3854 | 204.2695 | 1.133 | 0.017525 | 8.9596e-05 | 0.46493 | 0.73828 | {1D2DA1C9-B2A9-4713-BA25-DD6CA0F657BB} | 182541103 | ATASCADERO 1103 | A18 | 35.4489 | -120.6491 | ATASCADERO 1103A18 | 287 | 273 | 43891.8224 | 29119.0556 | 14772.7668 | 12533.7225 | 3539.2795 | 0.0073469 | 0.0037061 | 1.6205 | 6.0854 | 1911 | 1.437 | 609 | 0 | 0 | 7.7881 | 1953 | 0
Sierra | 7078 | 624 | 1077.4352 | 1980 | 1605.7565 | 290 | 7.0625e-05 | 279.3237 | 14.1472 | 454.6175 | 4562.9399 | 112.3581 | 8.5463 | 136.521 | 1.2566 | 0.017438 | 0.00049751 | 0.31515 | 0.67098 | {0BE1E4C9-DDDF-49C0-980B-2AA7763D326F} | 152282101 | MOUNTAIN QUARRIES 2101 | 51584 | 38.8415 | -121.0155 | MOUNTAIN QUARRIES 210151584 | 315 | 288 | 56156.4337 | 35042.6767 | 21113.7569 | 35042.6767 | 21113.7569 | 0.14428 | 0.020481 | 1.7267 | 6.8276 | 792 | 5.0571 | 610 | 0 | 0 | 21.7745 | 556 | 0
North Coast | 710 | 583 | 903.3094 | 1208 | 1254.7622 | 67 | 0.00016988 | 95.1992 | 9.477 | 51.9337 | 526.7256 | 20.232 | 1.9564 | 26.901 | 1.1699 | 0.017409 | 0.0010675 | 0.48262 | 0.7199 | {2864C93C-BF52-4E0B-A5D1-FA5019DBF7C4} | 42811112 | MONTE RIO 1112 | 5040 | 38.4322 | -122.967 | MONTE RIO 11125040 | 78 | 304 | 20180.4929 | 6507.7866 | 13672.7062 | 6507.7866 | 13672.7062 | 0.071519 | 0.011382 | 1.5494 | 18.0299 | 377 | 1.1664 | 611 | 0 | 0 | 4.0437 | 2060 | 0
Bay Area | 552 | 293 | 511.7309 | 805 | 783.9003 | 38 | 0.00014272 | 114.5732 | 0.37498 | 0.13915 | 0.0020759 | 1.2705e-06 | 1.0648 | 5.6075 | 0.96524 | 0.017405 | 0.00010333 | 0.36398 | 0.6528 | {7808A995-1603-4DBC-94EF-C3DF7EAAE7DD} | 43091103 | GREENBRAE 1103 | 1260 | 37.9345 | -122.5375 | GREENBRAE 11031260 | 88 | 420 | 21867.1499 | 4352.5218 | 17514.6281 | 4080.5899 | 16590.2885 | 0.0039264 | 0.0054233 | 1.7465 | 21.1842 | 1839 | 0.66139 | 612 | 0 | 0 | 2.5356 | 1296 | 0
North Coast | 9239 | 1016 | 1659.545 | 1142 | 1721.912 | 99 | 0.00017269 | 101.0494 | 3.4629 | 599.1042 | 7899.6578 | 63.1749 | 1.0452 | 53.5343 | 1.172 | 0.017383 | 0.00034614 | 0.88967 | 0.96378 | {FC8DA5F1-E256-452E-840A-DB2CC55A41C4} | 192461101 | BRIDGEVILLE 1101 | circuit_breaker | 40.4796 | -123.7798 | BRIDGEVILLE 1101circuit_breaker | 69 | 34 | 16439.5653 | 13703.3241 | 2736.2412 | 13703.3241 | 2736.2412 | 0.034268 | 0.017096 | 1.6334 | 11.5354 | 1020 | 1.721 | 613 | 0 | 0 | 8.5148 | 1758 | 0
North Valley | 4192 | 0 | 0 | 10 | 2.1341 | 6 | 2.0752e-05 | 841.9121 | 0 | 34.3924 | 56.5291 | 0 | 8.0269 | 1930.1145 | 1.7301 | 0.017356 | 3.5777e-06 | 0 | 0 | {4FE71C2A-D73C-4875-8301-3BC6248AF0F6} | 103531103 | RAWSON 1103 | 85334 | 40.1852 | -122.179 | RAWSON 110385334 | 104 | 197 | 26101.9116 | 15285.8468 | 10816.0648 | 3724.4141 | 71.9921 | 2.1466e-05 | 0.00012451 |  | 1.6667 | 2858 | 0.10414 | 614 | 0 | 0 | 2.3142 | 2349 | 0
Sierra | 9095 | 87 | 166.1741 | 321 | 266.8904 | 56 | 6.2009e-05 | 271.7385 | 11.8227 | 448.5188 | 4370.8753 | 82.8426 | 8.686 | 111.1674 | 1.2781 | 0.017334 | 0.00041825 | 0.27103 | 0.62263 | {FE7E7A2D-4697-4EEC-AD93-CC71825AA942} | 152691109 | HIGGINS 1109 | 7863 | 39.0916 | -121.1772 | HIGGINS 11097863 | 56 | 39 | 10090.2028 | 6799.2947 | 3290.9081 | 6799.2947 | 3290.9081 | 0.023422 | 0.0034725 | 1.91 | 5.7321 | 913 | 0.97068 | 615 | 0 | 0 | 4.2249 | 1964 | 0
Sierra | 4587 | 235 | 443.7443 | 1334 | 887.1205 | 206 | 5.9751e-05 | 308.3081 | 4.8111 | 144.9881 | 1017.4594 | 16.2505 | 8.7489 | 358.5594 | 1.3982 | 0.017267 | 0.00013862 | 0.17616 | 0.50021 | {762F5F25-9174-4408-84A6-399ADE39F207} | 153652109 | SHINGLE SPRINGS 2109 | 85766 | 38.8026 | -120.9065 | SHINGLE SPRINGS 210985766 | 251 | 238 | 38300.0598 | 29469.33 | 8830.7298 | 29469.33 | 8830.7298 | 0.028555 | 0.012309 | 1.8883 | 6.4757 | 1638 | 3.557 | 616 | 0 | 0 | 18.3114 | 1428 | 0
North Coast | 8471 | 848 | 1105.9393 | 1448 | 1377.9467 | 197 | 0.0001277 | 125.4814 | 8.1627 | 2198.0984 | 48189.5933 | 787.3522 | 0.75535 | 158.1349 | 1.3064 | 0.017151 | 0.00062724 | 0.58564 | 0.8026 | {71012A72-9F3A-4416-A409-5A697A15AF1C} | 42681102 | LAYTONVILLE 1102 | 2502 | 39.5665 | -123.3983 | LAYTONVILLE 11022502 | 89 | 56 | 31795.347 | 27326.5363 | 4468.8107 | 27326.5363 | 4468.8107 | 0.12357 | 0.025157 | 1.3042 | 7.3503 | 644 | 3.3788 | 617 | 0 | 0 | 16.9799 | 983 | 0
North Coast | 2077 | 992 | 1534.4291 | 1569 | 1825.5928 | 159 | 0.00032112 | 48.2097 | 5.5478 | 39.5997 | 218.1921 | 1.1878 | 1.3596 | 17.2204 | 1.0667 | 0.017082 | 0.00094806 | 0.63225 | 0.84051 | {76599403-EF2F-43B7-895E-85F706D26E36} | 192221102 | GARBERVILLE 1102 | circuit_breaker | 40.103 | -123.7929 | GARBERVILLE 1102circuit_breaker | 392 | 856 | 49878.4617 | 26078.7579 | 23799.7038 | 17301.6263 | 9858.6943 | 0.15074 | 0.051058 | 1.5468 | 9.8679 | 434 | 2.7161 | 618 | 0 | 0 | 10.7507 | 1655 | 0
North Coast | 4267 | 1094 | 1789.6025 | 1276 | 1879.1243 | 139 | 0.00030072 | 59.572 | 1.9362 | 66.2585 | 499.3207 | 1.6457 | 0.099526 | 11.4099 | 1.0226 | 0.017011 | 0.00042399 | 0.85737 | 0.95236 | {270A551E-565A-4C78-BA5D-427CE889B75E} | 192311141 | FRUITLAND 1141 | 95324 | 40.284 | -123.8723 | FRUITLAND 114195324 | 140 | 229 | 20457.736 | 14576.7142 | 5881.0218 | 14576.7142 | 5881.0218 | 0.058935 | 0.0418 | 1.6358 | 9.1799 | 905 | 2.3645 | 619 | 0 | 0 | 9.0575 | 997 | 0
Bay Area | 7776 | 39 | 98.9006 | 101 | 126.7413 | 21 | 1.7636e-05 | 969.9885 | 5.1741 | 417.095 | 2003.6285 | 65.7292 | 17.4307 | 1130.1897 | 1.4458 | 0.016994 | 4.4697e-05 | 0.38614 | 0.78033 | {14A8794B-8A75-4FC8-9957-3059A6D6C76B} | 14502110 | VINEYARD 2110 | circuit_breaker | 37.67 | -121.8548 | VINEYARD 2110circuit_breaker | 115 | 60 | 21524.9407 | 17792.5531 | 3732.3876 | 8669.9033 | 1720.2413 | 0.00093864 | 0.00037036 | 2.5359 | 4.8095 | 2285 | 0.35687 | 620 | 0 | 0 | 5.3872 | 2849 | 0
Sierra | 214 | 0 | 0 | 8 | 3.3562 | 4 | 4.6997e-05 | 360.4686 | 0.031457 | 24.1902 | 72.3966 | 0.0025665 | 1.8053 | 586.3522 | 1.7655 | 0.016941 | 2.3019e-05 | 0 | 0 | {EAEA950F-88E9-428E-9D1A-43A64741EC71} | 63172101 | MADISON 2101 | 7702 | 38.7075 | -122.0497 | MADISON 21017702 | 242 | 275 | 51634.9054 | 34431.5939 | 17203.3115 | 1421.2134 | 149.4195 | 9.2077e-05 | 0.00018799 |  | 2 | 2568 | 0.067763 | 621 | 0 | 0 | 0.8831 | 2562 | 0
North Valley | 6989 | 354 | 691.2214 | 1298 | 1032.578 | 201 | 6.5324e-05 | 304.0046 | 101.8875 | 2491.324 | 34735.2769 | 5451.7663 | 9.7057 | 98.1117 | 1.3158 | 0.016839 | 0.003188 | 0.27273 | 0.66941 | {112CEC5D-7594-450C-A06E-88C65F1E5892} | 102911107 | WYANDOTTE 1107 | 38438 | 39.4933 | -121.372 | WYANDOTTE 110738438 | 250 | 234 | 43440.8496 | 27120.5563 | 16320.2934 | 27120.5563 | 16320.2934 | 0.64078 | 0.01313 | 1.9526 | 6.4577 | 91 | 3.3846 | 622 | 0 | 0 | 16.8519 | 365 | 0
Bay Area | 8331 | 85 | 156.1733 | 410 | 336.448 | 56 | 6.3787e-05 | 228.9134 | 18.4082 | 907.051 | 14534.6207 | 632.9788 | 4.1402 | 160.5208 | 1.183 | 0.016816 | 0.00055976 | 0.20732 | 0.46418 | {315B41A4-2763-4241-B96A-998B94A74075} | 43021101 | WOODACRE 1101 | 91900 | 38.0551 | -122.6933 | WOODACRE 110191900 | 116 | 93 | 36682.8096 | 22248.6035 | 14434.206 | 10288.938 | 10417.8139 | 0.031347 | 0.0035721 | 1.8373 | 7.3214 | 724 | 0.94168 | 623 | 0 | 0 | 6.3932 | 1980 | 0
North Coast | 7384 | 54 | 86.1235 | 66 | 92.2732 | 13 | 0.00042303 | 42.2492 | 4.2021 | 50.6417 | 518.3612 | 1.6763 | 0.45048 | 25.8449 | 1.0448 | 0.016757 | 0.0011027 | 0.81818 | 0.93335 | {44188CC0-DB48-4329-AD0B-C1A6BD23A8F4} | 192311142 | FRUITLAND 1142 | 2006 | 40.2235 | -123.8263 | FRUITLAND 11422006 | 125 | 260 | 20457.9992 | 14130.0867 | 6327.9125 | 12367.8837 | 4734.8498 | 0.014334 | 0.0054993 | 1.5949 | 5.0769 | 360 | 0.21784 | 624 | 0 | 0 | 7.685 | 574 | 0
Bay Area | 5540 | 3620 | 7034.1625 | 4591 | 7612.388 | 207 | 0.00011844 | 164.5788 | 1.9929 | 30.2466 | 215.6578 | 0.59462 | 0.71707 | 12.2174 | 1.0738 | 0.016752 | 0.00018342 | 0.7885 | 0.92404 | {95843233-31DE-4B8A-A7FD-7E8E48EA1CD1} | 24251101 | WOODSIDE 1101 | 8974 | 37.3881 | -122.2669 | WOODSIDE 11018974 | 232 | 390 | 42834.2262 | 21603.9606 | 21230.2656 | 21603.9606 | 21230.2656 | 0.037968 | 0.024517 | 1.9431 | 22.1787 | 1470 | 3.4676 | 625 | 0 | 0 | 13.4241 | 1925 | 0
North Valley | 8289 | 788 | 959.2241 | 1393 | 1280.133 | 130 | 0.00012939 | 129.2235 | 34.1136 | 2690.8051 | 57460.1525 | 4313.7437 | 0.90698 | 31.7395 | 1.151 | 0.016688 | 0.0026282 | 0.56569 | 0.74932 | {96A0A843-7251-461B-B57C-57ECCA82B23A} | 103271101 | ANTLER 1101 | 1376 | 40.8524 | -122.3324 | ANTLER 11011376 | 96 | 64 | 18472.8325 | 14477.8455 | 3994.987 | 14477.8455 | 3994.987 | 0.34167 | 0.016821 | 1.2173 | 10.7154 | 122 | 2.1695 | 626 | 0 | 0 | 8.9961 | 769 | 0
Central Valley | 3099 | 14 | 27.8024 | 73 | 47.0597 | 23 | 5.0757e-05 | 310.4056 | 5.2899 | 493.2279 | 3326.5359 | 43.0455 | 10.787 | 222.2047 | 1.2347 | 0.016678 | 0.00012739 | 0.19178 | 0.59079 | {2D2F9EB5-C573-4256-A9F2-6087D93C70C6} | 163011103 | MARTELL 1103 | 68192 | 38.3585 | -120.7899 | MARTELL 110368192 | 174 | 404 | 25896.583 | 10120.6731 | 15775.9099 | 3980.4628 | 1526.6958 | 0.00293 | 0.0011674 | 1.9859 | 3.1739 | 1708 | 0.3836 | 627 | 0 | 0 | 2.4733 | 998 | 0
North Valley | 3794 | 1090 | 1926.4894 | 2240 | 2468.9658 | 212 | 0.0001002 | 173.0656 | 122.1879 | 3504.2806 | 79526.3484 | 20019.8705 | 1.589 | 27.3528 | 1.0934 | 0.016625 | 0.0054569 | 0.48661 | 0.78028 | {342DEF5A-AA53-475D-8D7B-ABE1A3F6B4E9} | 103221101 | KANAKA 1101 | 65606 | 39.5291 | -121.2838 | KANAKA 110165606 | 245 | 265 | 35314.5628 | 20432.7894 | 14881.7734 | 20432.7894 | 14881.7734 | 1.1569 | 0.021242 | 1.7674 | 10.566 | 31 | 3.5245 | 628 | 0 | 0 | 12.6963 | 1224 | 0
Bay Area | 1108 | 0 | 0 | 9 | 4.7412 | 4 | 3.0815e-05 | 489.7816 | 0.030017 | 205.9282 | 2550.2406 | 0.14852 | 2.3938 | 267.836 | 1.3905 | 0.016548 | 1.4472e-05 | 0 | 0 | {003177BD-8A4D-4A57-8E37-AC044D50D3EA} | 42631109 | PETALUMA C 1109 | 128 | 38.2201 | -122.6439 | PETALUMA C 1109128 | 361 | 217 | 85484.5203 | 60135.589 | 25348.9313 | 54365.1404 | 24533.3868 | 5.7888e-05 | 0.00012326 |  | 2.25 | 2715 | 0.066191 | 629 | 0 | 0 | 33.7809 | 2792 | 0
North Coast | 704 | 2 | 2.5863 | 23 | 16.0114 | 7 | 3.8209e-05 | 388.4355 | 10.5293 | 1034.1311 | 5901.882 | 106.9407 | 10.3157 | 701.0153 | 1.6934 | 0.016529 | 0.00031849 | 0.086957 | 0.16153 | {F573D52A-B881-4B76-BAE1-75A508AA556E} | 43371102 | LAKEVILLE 1102 | 280 | 38.2544 | -122.5754 | LAKEVILLE 1102280 | 73 | 52 | 26362.8265 | 14239.5056 | 12123.3209 | 3287.3324 | 468.5223 | 0.0022294 | 0.00026746 | 1.2931 | 3.2857 | 1081 | 0.1157 | 630 | 0 | 0 | 2.0427 | 702 | 0
North Valley | 6602 | 103 | 188.3684 | 294 | 257.0969 | 58 | 0.00011286 | 157.3559 | 37.8299 | 366.0575 | 4359.1769 | 780.5108 | 5.4316 | 52.9131 | 1.0624 | 0.016482 | 0.0018858 | 0.35034 | 0.73267 | {A6F4671E-7001-4E04-8749-D198C4CDD6BE} | 103441101 | JESSUP 1101 | 9752 | 40.4804 | -122.3972 | JESSUP 11019752 | 58 | 55 | 12215.199 | 6269.3077 | 5945.8913 | 6269.3077 | 5892.5072 | 0.10937 | 0.0065456 | 1.8288 | 5.069 | 186 | 0.95594 | 631 | 0 | 0 | 3.8956 | 1608 | 0
Bay Area | 456 | 229 | 359.8371 | 577 | 563.2041 | 83 | 7.4451e-05 | 213.8579 | 13.6973 | 238.1893 | 4171.7901 | 282.4095 | 3.0512 | 100.817 | 1.1879 | 0.016471 | 0.00028799 | 0.39688 | 0.63891 | {829ACA47-635E-4880-92A0-8C929EC179A6} | 43021101 | WOODACRE 1101 | 96844 | 38.0192 | -122.6631 | WOODACRE 110196844 | 109 | 72 | 19763.3609 | 9464.5637 | 10298.7972 | 9464.5637 | 10298.7972 | 0.023903 | 0.0061795 | 1.5713 | 6.9518 | 1154 | 1.3671 | 632 | 0 | 0 | 5.881 | 2637 | 0
Bay Area | 6015 | 56 | 85.7808 | 116 | 118.5585 | 8 | 0.00014632 | 107.0636 | 0.56976 | 0.21531 | 0.083338 | 3.3863e-05 | 0.63993 | 5.8947 | 0.7807 | 0.016402 | 0.00012335 | 0.48276 | 0.72353 | {CF195E6A-F6FE-4BB4-BB47-B64B021C49FD} | 43091103 | GREENBRAE 1103 | 56884 | 37.9334 | -122.5319 | GREENBRAE 110356884 | 73 | 274 | 13312.4166 | 2392.4896 | 10919.927 | 883.8137 | 3302.4057 | 0.00098682 | 0.0011705 | 1.5318 | 14.5 | 1734 | 0.13122 | 633 | 0 | 0 | 0.54918 | 2626 | 0
North Coast | 271 | 145 | 203.0496 | 368 | 334.3142 | 50 | 6.8259e-05 | 270.797 | 8.6052 | 385.5009 | 4175.0745 | 70.9 | 3.9302 | 91.2615 | 1.2757 | 0.0164 | 0.00033501 | 0.39402 | 0.60736 | {95D38DE9-E8FF-48E8-A441-5433C36DE660} | 42891102 | GEYSERVILLE 1102 | 350 | 38.6706 | -122.8117 | GEYSERVILLE 1102350 | 250 | 216 | 55341.9565 | 31239.3548 | 24102.6017 | 6355.4918 | 7644.5753 | 0.016751 | 0.0034129 | 1.4003 | 7.36 | 1044 | 0.81998 | 634 | 0 | 0 | 3.9491 | 1573 | 0
Bay Area | 703 | 1286 | 2296.0658 | 2512 | 2974.2534 | 120 | 0.00010061 | 141.1301 | 4.8615 | 3.1762 | 14.6069 | 0.32478 | 0.30186 | 1.7408 | 0.45612 | 0.016377 | 0.00026848 | 0.51194 | 0.77198 | {5B9950E9-6C0C-44EE-B414-F2773560C367} | 42031124 | ALTO 1124 | 430 | 37.906 | -122.5504 | ALTO 1124430 | 221 | 803 | 46219.6832 | 11716.5372 | 34503.146 | 11716.5372 | 34503.146 | 0.032217 | 0.012073 | 1.7854 | 20.9333 | 1206 | 1.9653 | 635 | 0 | 0 | 7.2803 | 1939 | 0
Sierra | 8932 | 0 | 0 | 18 | 4.055 | 3 | 3.3652e-05 | 503.2214 | 2.1624 | 177.9156 | 1078.0463 | 2.3311 | 12.0147 | 472.1928 | 1.3392 | 0.016372 | 4.2075e-05 | 0 | 0 | {3F3AA0D2-CD3D-432D-9160-6EFA10A51D9D} | 152921101 | BROWNS VALLEY 1101 | circuit_breaker | 39.2259 | -121.4234 | BROWNS VALLEY 1101circuit_breaker | 34 | 3 | 1417.6098 | 1309.7042 | 107.9056 | 1061.2697 | 6.096 | 0.00012622 | 0.00010095 |  | 6 | 2307 | 0.049117 | 636 | 0 | 0 | 0.65944 | 396 | 0
North Coast | 1536 | 469 | 667.1353 | 619 | 749.8742 | 45 | 0.00016845 | 102.6669 | 4.7901 | 79.5439 | 800.1943 | 24.8724 | 2.4054 | 27.5143 | 1.0871 | 0.016348 | 0.00044436 | 0.75767 | 0.88966 | {9B107EC7-49C5-413B-94F9-4B15782C698B} | 42681102 | LAYTONVILLE 1102 | 64908 | 39.6812 | -123.4774 | LAYTONVILLE 110264908 | 168 | 226 | 21107.4693 | 10255.6361 | 10851.8333 | 5371.196 | 5773.7114 | 0.019996 | 0.0075803 | 1.4225 | 13.7556 | 873 | 0.73565 | 637 | 0 | 0 | 3.3375 | 134 | 0
Sierra | 1830 | 679 | 1078.4445 | 2587 | 1939.8306 | 307 | 8.4575e-05 | 203.7055 | 36.4581 | 925.922 | 11606.4346 | 992.211 | 7.8762 | 126.1986 | 1.2662 | 0.016209 | 0.0014798 | 0.26247 | 0.55595 | {F8F940BE-2186-4D6A-A878-43A27FC49FB8} | 152261106 | DIAMOND SPRINGS 1106 | 10587 | 38.6699 | -120.7753 | DIAMOND SPRINGS 110610587 | 295 | 255 | 58754.8518 | 35174.8047 | 23580.0471 | 35174.8047 | 23580.0471 | 0.4543 | 0.025965 | 1.5883 | 8.4267 | 249 | 4.9763 | 638 | 0 | 0 | 21.8566 | 2364 | 0
Central Valley | 5982 | 6 | 16.3078 | 14 | 20.2939 | 7 | 1.0259e-05 | 1564.0697 | 3.1822 | 6166.874 | 29574.453 | 104.6784 | 6.1855 | 3071.0426 | 2.0117 | 0.016156 | 2.5399e-05 | 0.42857 | 0.80358 | {908C371E-60A0-479A-AB4A-419AF9711AF4} | 253642101 | POSO MOUNTAIN 2101 | 2181 | 35.5943 | -118.9584 | POSO MOUNTAIN 21012181 | 137 | 59 | 41370.7977 | 38091.8602 | 3278.9375 | 26885.9284 | 3016.2973 | 0.00017779 | 7.1816e-05 | 2.718 | 2 | 2531 | 0.11309 | 639 | 0 | 0 | 16.7061 | 1722 | 0
North Coast | 6027 | 101 | 127.5738 | 133 | 142.8099 | 26 | 0.0001027 | 140.5634 | 38.9159 | 677.7888 | 5659.9059 | 709.9942 | 4.4663 | 298.902 | 1.2015 | 0.016111 | 0.0026387 | 0.7594 | 0.89331 | {B6068DE4-2B76-4559-A97F-83EC4465ECB7} | 42661103 | WILLITS 1103 | 964 | 39.4236 | -123.3536 | WILLITS 1103964 | 56 | 23 | 13368.0259 | 8651.6925 | 4716.3335 | 4036.5135 | 2436.7184 | 0.068606 | 0.0026702 | 1.2631 | 5.1154 | 121 | 0.41889 | 640 | 0 | 0 | 2.5082 | 741 | 0
Sierra | 4636 | 752 | 1313.8521 | 2725 | 1998.3606 | 389 | 0.00012128 | 139.9542 | 45.0161 | 762.5201 | 7766.8237 | 877.4163 | 8.7029 | 150.3159 | 1.296 | 0.01611 | 0.0029591 | 0.27596 | 0.65746 | {FE625157-4A14-40D2-B1D3-1A0A93F86C88} | 153652109 | SHINGLE SPRINGS 2109 | 61892 | 38.712 | -120.9497 | SHINGLE SPRINGS 210961892 | 458 | 380 | 81723.7659 | 48517.9876 | 33205.7783 | 48517.9876 | 33205.7783 | 1.1511 | 0.047177 | 1.7471 | 7.0051 | 108 | 6.2666 | 641 | 0 | 0 | 30.1477 | 1851 | 0
North Coast | 1291 | 1365 | 2312.0561 | 2245 | 2784.8384 | 179 | 0.00015825 | 98.1169 | 9.1268 | 81.2492 | 510.9872 | 12.2257 | 5.4972 | 33.6939 | 1.103 | 0.015982 | 0.00077032 | 0.60802 | 0.83023 | {E011217D-F6B4-46C8-AC6E-B5F7ADEBD850} | 42571102 | MOLINO 1102 | 178 | 38.4194 | -122.876 | MOLINO 1102178 | 330 | 395 | 48370.5445 | 21902.7203 | 26467.8242 | 19242.2295 | 23183.8669 | 0.13789 | 0.028327 | 1.6938 | 12.5419 | 519 | 2.8607 | 642 | 0 | 0 | 11.9566 | 2514 | 0
North Coast | 8325 | 112 | 178.1187 | 163 | 203.8345 | 16 | 0.0002067 | 78.8093 | 3.4192 | 688.0287 | 8775.8126 | 24.7295 | 1.141 | 55.8446 | 1.2647 | 0.015923 | 0.000455 | 0.68712 | 0.87384 | {1B1B8E92-3F52-4768-9081-CBB4EFF42E21} | 192221102 | GARBERVILLE 1102 | 8189 | 40.27 | -124.2241 | GARBERVILLE 11028189 | 14 | 14 | 2781.1302 | 1628.0781 | 1153.0521 | 1628.0781 | 1153.0521 | 0.00728 | 0.0033072 | 1.5903 | 10.1875 | 854 | 0.25477 | 643 | 0 | 0 | 1.0116 | 1567 | 0
North Coast | 8756 | 14 | 24.3606 | 44 | 36.5881 | 5 | 9.7072e-05 | 123.9173 | 0.26248 | 0.85003 | 3.8916 | 0.0022049 | 5.0796 | 39.0494 | 1.0265 | 0.015919 | 6.4933e-05 | 0.31818 | 0.66581 | {782709DA-4B4D-4F76-8D74-6294980C1957} | 43191102 | REDBUD 1102 | 44119 | 38.9672 | -122.6525 | REDBUD 110244119 | 62 | 199 | 12889.4056 | 4510.2451 | 8379.1605 | 603.3084 | 909.872 | 0.00032466 | 0.00048536 | 1.74 | 8.8 | 2094 | 0.079595 | 644 | 0 | 0 | 0.37488 | 1581 | 0
Sierra | 304 | 373 | 590.3361 | 1559 | 1068.8851 | 250 | 6.9872e-05 | 249.9358 | 36.6442 | 713.9661 | 5594.3045 | 366.4645 | 9.5918 | 257.8974 | 1.3735 | 0.015884 | 0.0011882 | 0.23926 | 0.55229 | {6752B4B6-FF0C-4C57-ADC9-D57090816B6D} | 152282101 | MOUNTAIN QUARRIES 2101 | 1350 | 38.8931 | -120.9966 | MOUNTAIN QUARRIES 21011350 | 305 | 224 | 55500.1447 | 34651.2737 | 20848.871 | 34651.2737 | 20848.871 | 0.29704 | 0.017468 | 1.5827 | 6.236 | 328 | 3.9709 | 645 | 0 | 0 | 21.5313 | 792 | 0
Bay Area | 5431 | 614 | 941.071 | 1240 | 1316.3579 | 175 | 4.9017e-05 | 378.6981 | 29.2824 | 420.7777 | 5949.8842 | 662.0128 | 5.381 | 201.369 | 1.296 | 0.015812 | 0.00064145 | 0.49516 | 0.71491 | {07E5B1CE-7E3B-4E08-B657-89EC574C92A0} | 43291104 | PUEBLO 1104 | 1304 | 38.3634 | -122.2651 | PUEBLO 11041304 | 234 | 160 | 44764.0175 | 30920.9317 | 13843.0858 | 30920.9317 | 13843.0858 | 0.11225 | 0.0085781 | 1.5327 | 7.0857 | 626 | 2.7671 | 646 | 0 | 0 | 19.2134 | 123 | 0
North Coast | 7091 | 809 | 1321.8705 | 1194 | 1500.9388 | 137 | 0.0001091 | 148.9587 | 0.65929 | 64.6195 | 729.2974 | 1.6733 | 0.37808 | 17.888 | 1.1139 | 0.015811 | 8.8602e-05 | 0.67755 | 0.8807 | {BBD56973-ABAA-4951-A1EE-E863C47010B2} | 192221101 | GARBERVILLE 1101 | 1770 | 39.9153 | -123.7634 | GARBERVILLE 11011770 | 95 | 96 | 18630.6348 | 13857.9245 | 4772.7102 | 13857.9245 | 4772.7102 | 0.012138 | 0.014947 | 1.634 | 8.7153 | 1923 | 2.1661 | 647 | 0 | 0 | 8.6109 | 379 | 0
Bay Area | 3635 | 500 | 751.145 | 854 | 953.5407 | 60 | 0.00010753 | 132.4282 | 1.0791 | 17.2119 | 177.8321 | 0.4301 | 1.3421 | 15.2205 | 1.0631 | 0.015804 | 0.00011557 | 0.58548 | 0.78774 | {163BDA39-807E-4AA9-AD15-91460635EEBA} | 43432102 | SILVERADO 2102 | 636 | 38.5088 | -122.4473 | SILVERADO 2102636 | 168 | 244 | 20415.645 | 9140.7797 | 11274.8654 | 6273.2424 | 2997.261 | 0.0069344 | 0.0064518 | 1.5023 | 14.2333 | 1772 | 0.94825 | 648 | 0 | 0 | 3.898 | 1641 | 0
North Coast | 4875 | 318 | 433.4894 | 679 | 630.4362 | 64 | 8.8744e-05 | 200.074 | 9.479 | 62.8647 | 684.4756 | 33.3376 | 11.5482 | 61.1269 | 1.1504 | 0.015786 | 0.000457 | 0.46834 | 0.6876 | {447B8131-1050-400E-81F0-E893F64CB384} | 42571102 | MOLINO 1102 | 41392 | 38.4457 | -122.868 | MOLINO 110241392 | 296 | 377 | 46341.6638 | 23482.9452 | 22858.7186 | 6064.4075 | 3939.5257 | 0.029248 | 0.0056796 | 1.3632 | 10.6094 | 853 | 1.0103 | 649 | 0 | 0 | 3.7682 | 1211 | 0
North Coast | 1326 | 314 | 428.566 | 926 | 737.355 | 118 | 5.7196e-05 | 270.9409 | 9.3768 | 134.7985 | 1059.778 | 19.8593 | 9.7942 | 165.7349 | 1.3348 | 0.015762 | 0.00031723 | 0.33909 | 0.58122 | {4783296A-689D-4C7A-9F23-C015688BF301} | 42561102 | FULTON 1102 | 4522 | 38.5424 | -122.7746 | FULTON 11024522 | 207 | 139 | 31031.6434 | 19948.4708 | 11083.1726 | 13642.0128 | 6523.4143 | 0.037433 | 0.0067491 | 1.3649 | 7.8475 | 1085 | 1.86 | 650 | 0 | 0 | 8.4768 | 25 | 0
North Coast | 6036 | 106 | 117.3224 | 302 | 229.9532 | 39 | 0.00010977 | 142.8809 | 3.2704 | 173.1199 | 2290.4907 | 15.2813 | 0.41468 | 47.1677 | 1.1609 | 0.015735 | 0.00025436 | 0.35099 | 0.5102 | {E1077E4E-022A-4658-906D-61D41C4EF125} | 43071101 | DUNBAR 1101 | 416 | 38.4361 | -122.5779 | DUNBAR 1101416 | 35 | 33 | 6194.0842 | 5219.9703 | 974.1139 | 4032.4336 | 855.4724 | 0.0099199 | 0.004281 | 1.1068 | 7.7436 | 1237 | 0.61367 | 651 | 0 | 0 | 2.5056 | 2657 | 0
North Coast | 8696 | 2 | 2.5863 | 8 | 5.4691 | 2 | 0.00017431 | 95.2372 | 0.40399 | 0.22239 | 0.41058 | 0.0001857 | 0.8219 | 4.2969 | 1.0177 | 0.015717 | 7.2916e-05 | 0.25 | 0.4729 | {F631AD16-DB0B-45CF-9124-A221CF5B6E01} | 43071103 | DUNBAR 1103 | 3135 | 38.3259 | -122.4879 | DUNBAR 11033135 | 27 | 132 | 6523.8449 | 1214.2636 | 5309.5812 | 100.9792 | 858.1802 | 0.00014583 | 0.00034861 | 1.2931 | 4 | 2037 | 0.031434 | 652 | 0 | 0 | 0.062746 | 788 | 0
North Valley | 6718 | 215 | 319.5765 | 428 | 391.4311 | 77 | 6.056e-05 | 554.1553 | 7.9353 | 1619.5883 | 11264.8477 | 263.47 | 7.573 | 439.1156 | 1.3444 | 0.015714 | 0.00027259 | 0.50234 | 0.81643 | {D9A2A699-962C-4607-98AB-EA01299FAAB8} | 102971111 | SYCAMORE CREEK 1111 | circuit_breaker | 39.7688 | -121.824 | SYCAMORE CREEK 1111circuit_breaker | 275 | 164 | 40622.3978 | 28716.7912 | 11905.6066 | 12547.7716 | 6652.9502 | 0.020989 | 0.0046631 | 1.4864 | 5.5584 | 1195 | 1.21 | 653 | 0 | 0 | 7.7968 | 567 | 0
North Valley | 5071 | 5 | 9.7249 | 15 | 12.9271 | 4 | 5.8091e-05 | 232.0423 | 39.2289 | 103.191 | 430.8847 | 18.287 | 7.5066 | 71.1381 | 1.1416 | 0.015708 | 0.0010774 | 0.33333 | 0.75229 | {FD9CCA92-C052-4A36-88EE-05418588C974} | 102911103 | WYANDOTTE 1103 | 13018 | 39.508 | -121.4643 | WYANDOTTE 110313018 | 40 | 27 | 3786.7711 | 2657.2717 | 1129.4993 | 201.9138 | 98.8432 | 0.0043096 | 0.00023236 | 1.945 | 3.75 | 373 | 0.062831 | 654 | 0 | 0 | 0.12546 | 2120 | 0
North Coast | 1907 | 889 | 1363.4895 | 1083 | 1454.532 | 104 | 8.1462e-05 | 161.7389 | 17.7921 | 243.9793 | 2561.5285 | 142.2559 | 3.0036 | 71.0231 | 1.1552 | 0.015638 | 0.00074681 | 0.82087 | 0.93741 | {57AE83F3-7C35-4A08-BEA4-B10AAC4F4015} | 42771113 | UKIAH 1113 | circuit_breaker | 39.1432 | -123.1916 | UKIAH 1113circuit_breaker | 339 | 845 | 66265.1165 | 25541.5735 | 40723.543 | 12034.1255 | 15604.9247 | 0.077669 | 0.008472 | 1.5337 | 10.4135 | 534 | 1.6263 | 655 | 0 | 0 | 7.4777 | 987 | 0
Central Valley | 3958 | 6 | 8.8008 | 26 | 14.8354 | 12 | 5.8941e-05 | 329.9469 | 1.3625 | 92.6916 | 782.8541 | 0.19908 | 8.4735 | 137.2256 | 1.1106 | 0.015572 | 6.467e-05 | 0.23077 | 0.59323 | {B1720971-4842-488B-929E-F65E96985B19} | 162211101 | CALAVERAS CEMENT 1101 | 13424 | 38.1964 | -120.6879 | CALAVERAS CEMENT 110113424 | 74 | 214 | 16217.4245 | 5801.6622 | 10415.7622 | 2488.4546 | 3152.8742 | 0.00077604 | 0.00070729 | 1.4668 | 2.1667 | 2097 | 0.18686 | 656 | 0 | 0 | 1.5463 | 1367 | 0
North Coast | 2011 | 471 | 802.402 | 508 | 820.092 | 52 | 0.00036801 | 42.5748 | 1.0454 | 96.9561 | 641.7958 | 1.3565 | 0.052204 | 13.5876 | 1.0241 | 0.015571 | 0.00035669 | 0.92717 | 0.97843 | {2690968B-84D3-4326-843B-7CB873856615} | 192311141 | FRUITLAND 1141 | circuit_breaker | 40.2861 | -123.8369 | FRUITLAND 1141circuit_breaker | 26 | 11 | 5136.4087 | 4594.941 | 541.4677 | 4594.941 | 541.4677 | 0.018548 | 0.019137 | 1.7036 | 9.7692 | 1004 | 0.80968 | 657 | 0 | 0 | 2.8552 | 1204 | 0
North Valley | 7058 | 293 | 531.4502 | 563 | 661.2378 | 70 | 8.5961e-05 | 182.8642 | 124.9575 | 5090.4667 | 128218.8713 | 23076.0161 | 0.26751 | 40.8222 | 1.2118 | 0.015561 | 0.0050427 | 0.52043 | 0.80372 | {E4FC9EAA-4CD2-4F52-B772-B3074E0DD303} | 103221101 | KANAKA 1101 | 1044 | 39.5749 | -121.3056 | KANAKA 11011044 | 31 | 10 | 10290.6789 | 9870.7715 | 419.9074 | 9870.7715 | 419.9074 | 0.35299 | 0.0060173 | 1.8138 | 8.0429 | 36 | 1.0893 | 658 | 0 | 0 | 6.1334 | 333 | 0
Central Coast | 7373 | 175 | 494.0017 | 571 | 712.7418 | 100 | 2.6903e-05 | 706.0318 | 14.0905 | 463.3843 | 1471.7372 | 49.2617 | 11.2585 | 360.9421 | 1.3321 | 0.015514 | 0.00015329 | 0.30648 | 0.6931 | {4514D6A6-77B8-4164-AACC-ADDF4E8C95FD} | 183041101 | BUELLTON 1101 | Y26 | 34.625 | -120.1892 | BUELLTON 1101Y26 | 190 | 122 | 44349.1331 | 25494.2608 | 18854.8724 | 23209.1215 | 17729.3441 | 0.015329 | 0.0026903 | 2.8229 | 5.71 | 1574 | 1.5514 | 659 | 0 | 0 | 14.4215 | 2467 | 0
Sierra | 623 | 634 | 945.6254 | 1256 | 1221.6753 | 132 | 7.4752e-05 | 287.1274 | 70.8733 | 896.8436 | 12382.5359 | 2010.7605 | 8.3339 | 91.5383 | 1.2486 | 0.015421 | 0.0030043 | 0.50478 | 0.77404 | {6A9220E4-A8F8-420E-B213-484BC56BD3B4} | 152481106 | BRUNSWICK 1106 | 2790 | 39.145 | -120.9719 | BRUNSWICK 11062790 | 173 | 173 | 33048.1385 | 17549.6884 | 15498.4501 | 15218.0635 | 13169.6679 | 0.39656 | 0.0098673 | 1.4915 | 9.5152 | 106 | 2.0356 | 660 | 0 | 0 | 9.4561 | 525 | 0
North Valley | 5797 | 84 | 134.3204 | 389 | 286.8394 | 103 | 2.0958e-05 | 647.3148 | 4.3909 | 343.3144 | 1378.1764 | 20.3468 | 13.325 | 761.0178 | 1.3494 | 0.015358 | 4.703e-05 | 0.21594 | 0.46828 | {BE242D62-FFF6-4E73-8F41-DCC9F0527F50} | 103551101 | RISING RIVER 1101 | 1530 | 40.8713 | -121.5539 | RISING RIVER 11011530 | 222 | 204 | 39764.4567 | 28387.6321 | 11376.8246 | 16264.4687 | 6672.7303 | 0.0048441 | 0.0021587 | 1.5991 | 3.7767 | 2266 | 1.5819 | 661 | 0 | 0 | 10.1063 | 2351 | 0
Sierra | 1325 | 305 | 488.1988 | 668 | 642.6379 | 66 | 9.97e-05 | 191.8364 | 8.9288 | 43.826 | 158.7242 | 2.7382 | 10.5778 | 50.7895 | 1.0473 | 0.015296 | 0.00053291 | 0.45659 | 0.75968 | {44D8E601-5E0A-4B0D-A783-27A4770DE5A5} | 152561107 | PENRYN 1107 | circuit_breaker | 38.8445 | -121.1668 | PENRYN 1107circuit_breaker | 385 | 346 | 46278.2851 | 25919.7392 | 20358.5459 | 6429.3235 | 5043.9505 | 0.035172 | 0.0065802 | 1.6007 | 10.1212 | 754 | 1.0096 | 662 | 0 | 0 | 3.995 | 2431 | 0
North Valley | 1852 | 269 | 522.6793 | 963 | 727.6481 | 205 | 3.8854e-05 | 395.6694 | 10.8349 | 66.5376 | 477.5122 | 34.6779 | 12.0012 | 140.6177 | 1.6562 | 0.015243 | 0.00023747 | 0.27934 | 0.71831 | {C5CBE785-E536-4CC4-8B58-7E4F16DB8A71} | 103521102 | OREGON TRAIL 1102 | 49144 | 40.6589 | -122.341 | OREGON TRAIL 110249144 | 267 | 356 | 49923.5305 | 34141.3008 | 15782.2297 | 28540.0535 | 15777.0665 | 0.048682 | 0.007965 | 1.943 | 4.6976 | 1286 | 3.1249 | 663 | 0 | 0 | 17.734 | 580 | 0
North Coast | 6371 | 501 | 657.0422 | 682 | 742.8247 | 133 | 8.8914e-05 | 195.8082 | 11.5588 | 1904.3172 | 34606.5189 | 1039.6822 | 7.1937 | 226.9621 | 1.2598 | 0.015206 | 0.00066962 | 0.7346 | 0.88452 | {5002339C-3B44-461E-A16D-6DB263D4D731} | 42871101 | UPPER LAKE 1101 | 75370 | 39.1894 | -122.9009 | UPPER LAKE 110175370 | 170 | 176 | 42224.8777 | 23613.6779 | 18611.1998 | 17069.5104 | 10269.9747 | 0.089059 | 0.011826 | 1.3115 | 5.1278 | 596 | 2.0223 | 664 | 0 | 0 | 10.6065 | 1361 | 0
Central Valley | 8459 | 21 | 35.7696 | 166 | 88.7984 | 36 | 3.9121e-05 | 378.7581 | 9.5959 | 269.7713 | 2799.5151 | 204.8896 | 10.0755 | 228.6332 | 1.4197 | 0.015159 | 0.00016158 | 0.12651 | 0.40282 | {050E06AF-91BE-429B-BDFE-3EAD80F24863} | 254452101 | MARIPOSA 2101 | circuit_breaker | 37.5047 | -120.0077 | MARIPOSA 2101circuit_breaker | 65 | 43 | 6979.1883 | 4029.4321 | 2949.7561 | 4029.4321 | 2949.7561 | 0.0058169 | 0.0014084 | 1.7033 | 4.6111 | 1542 | 0.54574 | 665 | 0 | 0 | 2.5038 | 1522 | 0
Bay Area | 6719 | 128 | 204.6318 | 409 | 363.6746 | 41 | 0.00012061 | 112.2596 | 1.2699 | 28.1569 | 718.9615 | 8.7845 | 1.5662 | 34.0315 | 1.0548 | 0.015058 | 0.00013875 | 0.31296 | 0.56268 | {0C1EAF38-D291-4410-BD5A-7EDE35C497EC} | 43021101 | WOODACRE 1101 | circuit_breaker | 38.0121 | -122.6539 | WOODACRE 1101circuit_breaker | 71 | 131 | 10355.8676 | 4553.3245 | 5802.5431 | 4013.0588 | 5668.065 | 0.0056887 | 0.0049449 | 1.5987 | 9.9756 | 1637 | 0.61739 | 666 | 0 | 0 | 2.4936 | 2642 | 0
North Coast | 244 | 117 | 174.7089 | 347 | 315.4457 | 25 | 8.4435e-05 | 166.6411 | 20.4342 | 150.0378 | 894.0961 | 29.295 | 1.898 | 46.0102 | 1.1089 | 0.014999 | 0.00076985 | 0.33718 | 0.55385 | {2A534FE3-EF17-402C-9700-8C33AB455C66} | 43321103 | RINCON 1103 | circuit_breaker | 38.4899 | -122.6662 | RINCON 1103circuit_breaker | 76 | 94 | 13108.5488 | 5989.4697 | 7119.0791 | 3908.5393 | 3713.5655 | 0.019246 | 0.0021109 | 1.4932 | 13.88 | 520 | 0.37497 | 667 | 0 | 0 | 2.4287 | 1014 | 0
North Coast | 3078 | 201 | 271.8075 | 323 | 328.0249 | 46 | 0.00012067 | 113.4014 | 26.723 | 878.9573 | 15249.2219 | 2116.8225 | 10.4681 | 69.1983 | 1.2357 | 0.014965 | 0.0014276 | 0.62229 | 0.82862 | {CBE7DCF1-ECDA-4517-A76B-79D934ABEB82} | 42661104 | WILLITS 1104 | 4650 | 39.3985 | -123.3516 | WILLITS 11044650 | 165 | 426 | 28173.4193 | 9494.7518 | 18678.6675 | 5679.3968 | 10214.3831 | 0.065669 | 0.0055508 | 1.3523 | 7.0217 | 266 | 0.6884 | 668 | 0 | 0 | 3.529 | 862 | 0
Central Valley | 7126 | 120 | 168.6802 | 420 | 286.4925 | 71 | 7.7007e-05 | 205.9168 | 25.4679 | 226.0128 | 1459.0966 | 88.0889 | 12.0511 | 217.1819 | 1.4499 | 0.014918 | 0.0012316 | 0.28571 | 0.58878 | {74DC8F54-4589-4421-89BC-E98BD5920B33} | 163011102 | MARTELL 1102 | circuit_breaker | 38.3691 | -120.7968 | MARTELL 1102circuit_breaker | 119 | 123 | 19260.22 | 10830.1822 | 8430.0378 | 7916.9254 | 5510.9411 | 0.087446 | 0.0054675 | 1.4057 | 5.9155 | 312 | 1.0592 | 669 | 0 | 0 | 4.9193 | 1610 | 0
Central Valley | 1151 | 63 | 174.9086 | 283 | 231.5987 | 87 | 5.6334e-05 | 266.3716 | 6.7761 | 24.1519 | 91.4446 | 3.2663 | 10.0839 | 165.9997 | 1.1534 | 0.014912 | 0.00019822 | 0.22261 | 0.75522 | {EB467927-3D28-42DC-B202-516334CB2DF4} | 162991103 | CORRAL 1103 | 36680 | 38.1245 | -120.8473 | CORRAL 110336680 | 430 | 886 | 77894.271 | 32149.378 | 45744.8931 | 13725.8331 | 15814.5755 | 0.017245 | 0.0049011 | 2.7763 | 3.2529 | 1421 | 1.2973 | 670 | 0 | 0 | 8.5288 | 2245 | 0
North Valley | 4103 | 1213 | 2236.1671 | 2209 | 2712.3022 | 239 | 9.8847e-05 | 149.595 | 53.1578 | 1835.3001 | 31394.6244 | 3392.1457 | 0.54561 | 22.9306 | 1.046 | 0.014824 | 0.0023089 | 0.54912 | 0.82445 | {C71A58EE-DA31-4CE3-8F9B-4D615671BE3A} | 103201102 | CHALLENGE 1102 | circuit_breaker | 39.4855 | -121.2201 | CHALLENGE 1102circuit_breaker | 214 | 185 | 35336.699 | 24978.1439 | 10358.5551 | 24978.1439 | 10358.5551 | 0.55184 | 0.023625 | 1.8435 | 9.2427 | 151 | 3.543 | 671 | 0 | 0 | 15.5207 | 1545 | 0
North Coast | 4609 | 89 | 158.2543 | 92 | 159.7224 | 24 | 0.00042559 | 34.7278 | 0.11714 | 31.8318 | 119.8626 | 0.022668 | 0.17008 | 8.7675 | 1.0115 | 0.014822 | 0.00019996 | 0.96739 | 0.99081 | {901979A9-33A5-4FBB-9019-2CBDDF98F849} | 192311141 | FRUITLAND 1141 | 8860 | 40.2829 | -123.8726 | FRUITLAND 11418860 | 61 | 149 | 10329.406 | 6108.7785 | 4220.6275 | 3211.911 | 478.6548 | 0.004799 | 0.010214 | 1.7781 | 3.8333 | 1413 | 0.35573 | 672 | 0 | 0 | 1.9958 | 2359 | 0
North Coast | 2629 | 4 | 3.9072 | 27 | 24.2856 | 1 | 5.9643e-05 | 476.0262 |  |  |  |  | 0.061947 | 31.3035 | 1.1482 | 0.028392 | 5.9643e-05 | 0.14815 | 0.16089 | {EBBE0A29-2908-46ED-BB26-43BABD7BEC2A} | 43292102 | PUEBLO 2102 | 792 | 38.433 | -122.4021 | PUEBLO 2102792 | 221 | 193 | 53493.2008 | 33531.1108 | 19962.09 | 30375.5803 | 19611.8188 | 5.9643e-05 | 5.9643e-05 | 0.9768 | 27 | 2147 | 0.028392 | 673 | 0 | 0 | 18.8745 | 800 | 0
Bay Area | 2629 | 1142 | 1496.3535 | 2640 | 2377.26 | 235 | 0.00010051 | 144.8414 | 12.2725 | 495.5295 | 9445.8336 | 375.1404 | 0.56233 | 48.3509 | 1.1802 | 0.014761 | 0.00066054 | 0.43258 | 0.62944 | {EBBE0A29-2908-46ED-BB26-43BABD7BEC2A} | 43292102 | PUEBLO 2102 | 792 | 38.433 | -122.4021 | PUEBLO 2102792 | 221 | 193 | 53493.2008 | 33531.1108 | 19962.09 | 30375.5803 | 19611.8188 | 0.15523 | 0.02362 | 1.3103 | 11.234 | 603 | 3.4689 | 673 | 0 | 0 | 18.8745 | 130 | 0
North Coast | 5934 | 426 | 604.8587 | 947 | 917.9915 | 94 | 9.7707e-05 | 140.874 | 8.4367 | 545.2359 | 11413.5699 | 328.1302 | 2.3742 | 57.0645 | 1.2518 | 0.014763 | 0.00046441 | 0.44984 | 0.65889 | {A4A124EA-8920-4709-8090-23E3A2E000DC} | 42891101 | GEYSERVILLE 1101 | 35492 | 38.693 | -122.9625 | GEYSERVILLE 110135492 | 310 | 255 | 60120.6187 | 34732.69 | 25387.9287 | 14162.9366 | 9522.0117 | 0.043655 | 0.0091845 | 1.4199 | 10.0745 | 839 | 1.3877 | 674 | 0 | 0 | 8.8004 | 2479 | 0
Central Valley | 6533 | 181 | 324.2683 | 725 | 516.7034 | 131 | 5.1492e-05 | 297.117 | 5.8427 | 232.0438 | 1206.6737 | 13.7332 | 11.1213 | 300.1173 | 1.4803 | 0.014736 | 0.00017581 | 0.24966 | 0.62757 | {23616425-EB34-423E-9DF9-30BB0AE7795F} | 163541102 | OLETA 1102 | circuit_breaker | 38.4807 | -120.8451 | OLETA 1102circuit_breaker | 190 | 146 | 34746.1334 | 24558.1337 | 10187.9997 | 21808.3893 | 8879.1301 | 0.023031 | 0.0067455 | 1.7915 | 5.5344 | 1499 | 1.9304 | 675 | 0 | 0 | 13.5511 | 1592 | 0
Central Valley | 1099 | 189 | 370.2314 | 683 | 523.4584 | 161 | 2.6749e-05 | 571.4674 | 7.7861 | 356.9249 | 2080.1353 | 18.7892 | 8.4381 | 543.9782 | 1.3913 | 0.014734 | 0.00011135 | 0.27672 | 0.70728 | {4F2BC5E5-BD35-4490-9CFD-1F5D23517497} | 252811102 | MERCED FALLS 1102 | 87352 | 37.7031 | -120.3373 | MERCED FALLS 110287352 | 296 | 338 | 67319.688 | 42810.09 | 24509.598 | 42562.7821 | 24457.6589 | 0.017928 | 0.0043066 | 1.9589 | 4.2422 | 1793 | 2.3721 | 676 | 0 | 0 | 26.4473 | 856 | 0
North Coast | 4799 | 198 | 259.159 | 309 | 315.9164 | 53 | 0.00011905 | 136.658 | 10.5622 | 293.1786 | 4123.1885 | 122.2522 | 8.4441 | 63.4628 | 0.98034 | 0.01473 | 0.0006291 | 0.64078 | 0.82034 | {EF9398DB-0F7B-497E-B310-02727CA6D6C0} | 42661104 | WILLITS 1104 | 34006 | 39.402 | -123.3549 | WILLITS 110434006 | 170 | 440 | 26640.4771 | 9186.411 | 17454.066 | 6444.3113 | 10157.6994 | 0.033343 | 0.0063099 | 1.3089 | 5.8302 | 641 | 0.78067 | 677 | 0 | 0 | 4.0043 | 270 | 0
Sierra | 3018 | 1675 | 2356.8769 | 3682 | 3401.0957 | 256 | 8.3976e-05 | 186.7997 | 28.9573 | 1411.8548 | 29350.705 | 2925.7246 | 0.62506 | 28.6053 | 1.0785 | 0.014683 | 0.0011236 | 0.45492 | 0.69298 | {1B4AEF1E-3888-4CF0-B5B2-91A85959940F} | 152201101 | PIKE CITY 1101 | circuit_breaker | 39.4384 | -120.996 | PIKE CITY 1101circuit_breaker | 227 | 301 | 49313.7889 | 31954.3985 | 17359.3904 | 31954.3985 | 17359.3904 | 0.28764 | 0.021498 | 1.4071 | 14.3828 | 353 | 3.759 | 678 | 0 | 0 | 19.8555 | 1439 | 0
Central Valley | 7448 | 41 | 70.2459 | 349 | 174.7151 | 113 | 3.2047e-05 | 602.6027 | 14.3258 | 1790.3104 | 15963.9222 | 636.0625 | 15.0594 | 934.8578 | 1.7876 | 0.014628 | 0.00028434 | 0.11748 | 0.40206 | {E1B28A54-7ECA-4BC3-8221-20371DB8BAC6} | 254421101 | OAKHURST 1101 | 6220 | 37.3599 | -119.7394 | OAKHURST 11016220 | 176 | 107 | 42607.1977 | 32301.3797 | 10305.8181 | 32301.3797 | 10305.8181 | 0.032131 | 0.0036213 | 1.7133 | 3.0885 | 1160 | 1.6529 | 679 | 0 | 0 | 20.0711 | 2483 | 0
Central Coast | 285 | 40 | 84.4402 | 98 | 113.9807 | 20 | 2.7732e-05 | 733.1388 | 8.3744 | 161.1115 | 666.1974 | 26.7304 | 17.4102 | 188.7638 | 1.1366 | 0.014622 | 8.6601e-05 | 0.40816 | 0.74083 | {FEA8F80B-51AF-4084-A9B9-47D11430DD95} | 83242110 | MORGAN HILL 2110 | XR326 | 37.1072 | -121.6348 | MORGAN HILL 2110XR326 | 444 | 556 | 64363.006 | 33599.9303 | 30763.0758 | 3216.8739 | 3341.2808 | 0.001732 | 0.00055464 | 2.111 | 4.9 | 1935 | 0.29243 | 680 | 0 | 0 | 1.9989 | 708 | 0
North Coast | 2709 | 29 | 35.6037 | 86 | 68.4072 | 5 | 7.4423e-05 | 229.7985 | 3.5965 | 61.2944 | 249.0106 | 1.2979 | 8.354 | 202.226 | 1.2708 | 0.014578 | 0.00017187 | 0.33721 | 0.52047 | {72AE5EDE-AC15-4265-AF32-67B0F370C217} | 42561107 | FULTON 1107 | circuit_breaker | 38.497 | -122.7619 | FULTON 1107circuit_breaker | 508 | 788 | 59910.99 | 22107.5267 | 37803.4632 | 487.3016 | 748.4625 | 0.00085933 | 0.00037212 | 1.2277 | 17.2 | 1517 | 0.072892 | 681 | 0 | 0 | 0.3028 | 56 | 0
North Coast | 4254 | 247 | 673.2911 | 510 | 834.318 | 78 | 6.7763e-05 | 277.6236 | 13.3935 | 250.8884 | 1573.9 | 68.0719 | 10.649 | 99.6649 | 1.1655 | 0.014552 | 0.00030416 | 0.48431 | 0.807 | {5DA68EF3-5901-4088-9DDE-761BE1716E65} | 43182103 | BELLEVUE 2103 | 552 | 38.3652 | -122.6659 | BELLEVUE 2103552 | 314 | 234 | 44356.7669 | 24038.0516 | 20318.7153 | 11666.895 | 11628.4154 | 0.023725 | 0.0052855 | 2.7259 | 6.5385 | 1111 | 1.1351 | 682 | 0 | 0 | 7.2495 | 73 | 0
North Coast | 4087 | 1663 | 2807.6585 | 3123 | 3602.8398 | 233 | 0.00013731 | 111.1291 | 16.9167 | 235.297 | 1157.4902 | 64.5607 | 8.0537 | 59.7422 | 1.1836 | 0.0145 | 0.0013135 | 0.5325 | 0.77929 | {87C4E1DE-229A-456D-853B-731F9308D34F} | 42571101 | MOLINO 1101 | 322 | 38.3868 | -122.8901 | MOLINO 1101322 | 327 | 398 | 52233.4484 | 25513.0579 | 26720.3905 | 24774.6668 | 26144.891 | 0.30604 | 0.031994 | 1.6883 | 13.4034 | 290 | 3.3785 | 683 | 0 | 0 | 15.3943 | 2803 | 0
Central Valley | 2580 | 203 | 311.1321 | 991 | 538.9257 | 255 | 1.7628e-05 | 762.1612 | 38.6804 | 3743.7987 | 29819.6624 | 1758.2361 | 17.7672 | 1024.2958 | 1.7715 | 0.014458 | 0.00029501 | 0.20484 | 0.57732 | {1328D5B4-6BC6-4A19-8B7D-C1E2266894DF} | 254151101 | AUBERRY 1101 | R2579 | 36.9726 | -119.3782 | AUBERRY 1101R2579 | 358 | 341 | 91289.9833 | 55665.4542 | 35624.5291 | 55665.4542 | 35624.5291 | 0.075227 | 0.0044952 | 1.5327 | 3.8863 | 1136 | 3.6868 | 684 | 0 | 0 | 34.5889 | 1833 | 0
North Coast | 801 | 547 | 825.1527 | 1206 | 1208.8362 | 182 | 8.3549e-05 | 178.19 | 3.4601 | 41.2301 | 393.1104 | 4.3292 | 4.4506 | 96.6344 | 1.2587 | 0.014383 | 0.00021386 | 0.45357 | 0.6826 | {32B34880-BC93-4771-BC39-2E887BB96BE8} | 42821102 | CLOVERDALE 1102 | 570 | 38.7762 | -122.981 | CLOVERDALE 1102570 | 268 | 301 | 64680.3055 | 34152.262 | 30528.0435 | 26431.4448 | 20545.4163 | 0.038923 | 0.015206 | 1.5085 | 6.6264 | 1370 | 2.6177 | 685 | 0 | 0 | 16.4237 | 453 | 0
Sierra | 5748 | 284 | 399.5638 | 710 | 575.2378 | 90 | 0.00011298 | 137.0826 | 11.0185 | 235.3552 | 2407.9359 | 144.2409 | 4.1997 | 115.4274 | 1.3205 | 0.01437 | 0.00067271 | 0.4 | 0.69461 | {DCD6C7A6-BCDE-42A2-9036-021FA6ED047F} | 153741101 | DOBBINS 1101 | 69722 | 39.341 | -121.1952 | DOBBINS 110169722 | 93 | 67 | 12664.8247 | 10673.4289 | 1991.3958 | 10673.4289 | 1991.3958 | 0.060544 | 0.010168 | 1.4069 | 7.8889 | 592 | 1.2933 | 686 | 0 | 0 | 6.6322 | 89 | 0
North Coast | 1027 | 2198 | 3896.353 | 2783 | 4196.022 | 217 | 0.00028869 | 50.0128 | 1.959 | 123.916 | 1497.2223 | 5.8189 | 0.70818 | 16.282 | 1.0898 | 0.014315 | 0.00042089 | 0.7898 | 0.92858 | {8E27DD26-ACA7-40A3-8328-F2AB9AB9A4A2} | 192221102 | GARBERVILLE 1102 | 8652 | 40.1065 | -123.9278 | GARBERVILLE 11028652 | 164 | 111 | 27071.644 | 21012.1269 | 6059.5171 | 21012.1269 | 6059.5171 | 0.091333 | 0.062647 | 1.7727 | 12.8249 | 909 | 3.1063 | 687 | 0 | 0 | 13.0563 | 40 | 0
North Coast | 453 | 188 | 337.2087 | 535 | 447.2233 | 97 | 5.8922e-05 | 259.2182 | 3.9318 | 539.3647 | 11765.0303 | 287.2037 | 8.9055 | 338.1351 | 1.7149 | 0.014294 | 0.00014109 | 0.3514 | 0.75401 | {6139DC48-33A9-4D2F-A5A3-F8FF5CADADDE} | 43311102 | KONOCTI 1102 | 596 | 38.9406 | -122.78 | KONOCTI 1102596 | 275 | 516 | 45927.7718 | 21540.3672 | 24387.4045 | 15791.9595 | 15501.9019 | 0.013686 | 0.0057154 | 1.7937 | 5.5155 | 1628 | 1.3865 | 688 | 0 | 0 | 9.8127 | 2600 | 0
North Coast | 3769 | 60 | 86.5583 | 87 | 99.3311 | 17 | 6.8801e-05 | 183.4309 | 33.9204 | 1174.2187 | 22247.5254 | 4049.0928 | 8.0833 | 72.0403 | 1.2426 | 0.014266 | 0.0010043 | 0.68966 | 0.87141 | {B04BF7D5-ADED-43AC-BEDB-9FDE2335B752} | 42771111 | UKIAH 1111 | 29452 | 39.1594 | -123.2023 | UKIAH 111129452 | 242 | 173 | 31582.7741 | 20265.329 | 11317.4451 | 5841.787 | 2021.0565 | 0.017073 | 0.0011696 | 1.4426 | 5.1176 | 411 | 0.24252 | 689 | 0 | 0 | 3.6299 | 486 | 0
Bay Area | 2256 | 277 | 400.608 | 365 | 441.357 | 34 | 3.798e-05 | 368.7811 | 25.055 | 446.4729 | 2178.5806 | 157.8971 | 10.3695 | 287.3888 | 1.1074 | 0.014206 | 0.00030792 | 0.7589 | 0.90767 | {E0DA3FA9-134E-46BA-BA63-A138252A7798} | 14502107 | VINEYARD 2107 | circuit_breaker | 37.6701 | -121.8544 | VINEYARD 2107circuit_breaker | 372 | 635 | 40312.1815 | 16402.2958 | 23909.8858 | 4200.246 | 4571.1313 | 0.010469 | 0.0012913 | 1.4462 | 10.7353 | 1103 | 0.48301 | 690 | 0 | 0 | 2.6099 | 335 | 0
North Coast | 640 | 889 | 1326.0367 | 1286 | 1479.2637 | 144 | 0.00013578 | 104.0096 | 4.8441 | 163.8804 | 2155.235 | 15.9124 | 3.8475 | 211.4224 | 1.2691 | 0.014295 | 0.00034833 | 0.69129 | 0.89642 | {87D28769-5329-4925-BD5B-DA686EE4E76D} | 43141101 | MIDDLETOWN 1101 | 48212 | 38.725 | -122.619 | MIDDLETOWN 110148212 | 164 | 176 | 30903.1345 | 17455.2996 | 13447.8349 | 17298.8853 | 13410.8034 | 0.050159 | 0.019552 | 1.4916 | 8.9306 | 1015 | 2.0585 | 691 | 0 | 0 | 10.749 | 977 | 0
Bay Area | 640 | 2 | 3.89 | 2 | 3.89 | 1 | 0.00014164 | 0.9439 |  |  |  |  | 0 | 163.6657 | 1.0841 | 0.00013369 | 0.00014164 | 1 | 1 | {87D28769-5329-4925-BD5B-DA686EE4E76D} | 43141101 | MIDDLETOWN 1101 | 48212 | 38.725 | -122.619 | MIDDLETOWN 110148212 | 164 | 176 | 30903.1345 | 17455.2996 | 13447.8349 | 17298.8853 | 13410.8034 | 0.00014164 | 0.00014164 | 1.945 | 2 | 1624 | 0.00013369 | 691 | 0 | 0 | 10.749 | 2436 | 0
North Valley | 3420 | 9 | 17.9222 | 31 | 25.6496 | 8 | 7.3443e-05 | 178.6824 | 0.02897 | 0.17524 | 0.38283 | 2.0548e-05 | 5.7372 | 85.5777 | 1.5415 | 0.014161 | 3.9306e-05 | 0.29032 | 0.69873 | {995D3FA2-A637-43AE-9B3D-DDCFC4316118} | 103441103 | JESSUP 1103 | circuit_breaker | 40.4616 | -122.3279 | JESSUP 1103circuit_breaker | 307 | 419 | 38785.5388 | 22946.415 | 15839.1237 | 998.4804 | 1319.7574 | 0.00031445 | 0.00058754 | 1.9914 | 3.875 | 2352 | 0.11329 | 692 | 0 | 0 | 0.62043 | 1023 | 0
North Coast | 5847 | 380 | 528.9637 | 961 | 819.2327 | 78 | 0.00010132 | 132.4635 | 4.6176 | 23.5046 | 160.5766 | 1.3588 | 1.9378 | 15.209 | 1.0312 | 0.014087 | 0.00033216 | 0.39542 | 0.64568 | {4BCD6EE2-7FEC-4152-907C-A38A16D3BF51} | 42721102 | SONOMA 1102 | 118 | 38.3089 | -122.4781 | SONOMA 1102118 | 134 | 220 | 23354.4912 | 12055.2085 | 11299.2827 | 9282.9853 | 7223.1118 | 0.025908 | 0.0079028 | 1.392 | 12.3205 | 1051 | 1.0988 | 693 | 0 | 0 | 5.7682 | 1569 | 0
North Coast | 6887 | 953 | 1255.6033 | 1992 | 1826.0972 | 158 | 0.00011085 | 138.8692 | 11.6935 | 127.6977 | 1689.4989 | 88.5793 | 3.396 | 36.1359 | 1.0885 | 0.014003 | 0.00069477 | 0.47841 | 0.68759 | {1FA8A5B8-216C-48A5-8B5C-D037DBE66063} | 42091101 | MIRABEL 1101 | 116 | 38.4736 | -122.8977 | MIRABEL 1101116 | 173 | 173 | 30587.0663 | 17803.3709 | 12783.6955 | 16655.9357 | 11869.8742 | 0.10977 | 0.017514 | 1.3175 | 12.6076 | 570 | 2.2124 | 694 | 0 | 0 | 10.3495 | 789 | 0
Sierra | 492 | 2060 | 2981.4538 | 4115 | 3932.7957 | 464 | 0.00010463 | 179.0756 | 19.4104 | 396.2177 | 3961.4831 | 201.2686 | 5.9944 | 135.1831 | 1.2745 | 0.013969 | 0.0010101 | 0.50061 | 0.7581 | {81A1F156-C98B-4850-992A-A7159456D080} | 153741101 | DOBBINS 1101 | 1264 | 39.374 | -121.2054 | DOBBINS 11011264 | 438 | 363 | 76561.1273 | 55993.1456 | 20567.9817 | 55887.5598 | 20440.4865 | 0.46868 | 0.048548 | 1.4473 | 8.8685 | 407 | 6.4814 | 695 | 0 | 0 | 34.7269 | 849 | 0
Central Valley | 514 | 174 | 235.8489 | 689 | 427.8949 | 184 | 1.5807e-05 | 1035.2324 | 100.1648 | 3104.7931 | 30229.0943 | 5824.7488 | 18.4341 | 816.5858 | 1.7024 | 0.013884 | 0.00058234 | 0.25254 | 0.55118 | {5755A55C-8127-474D-99F5-38E2401D21A6} | 254061103 | DUNLAP 1103 | 7220 | 36.7161 | -119.0342 | DUNLAP 11037220 | 237 | 179 | 56067.9923 | 39952.2483 | 16115.744 | 39952.2483 | 16115.744 | 0.10715 | 0.0029084 | 1.3555 | 3.7446 | 693 | 2.5547 | 696 | 0 | 0 | 24.8252 | 9 | 0
Central Valley | 7449 | 92 | 180.8019 | 611 | 349.3584 | 178 | 4.3457e-05 | 284.0589 | 32.2332 | 3128.5567 | 22567.8433 | 2008.143 | 9.0174 | 342.3343 | 1.3864 | 0.013877 | 0.00062244 | 0.15057 | 0.51753 | {D05BF1A7-CDA9-471C-9C8C-324F680AD3F8} | 252192101 | BEAR VALLEY 2101 | 4160 | 37.4958 | -120.0437 | BEAR VALLEY 21014160 | 236 | 246 | 61984.9577 | 36553.6326 | 25431.3251 | 36553.6326 | 25431.3251 | 0.11079 | 0.0077354 | 1.9652 | 3.4326 | 647 | 2.4701 | 697 | 0 | 0 | 22.7134 | 2753 | 0
Central Coast | 6446 | 22 | 54.4299 | 94 | 82.3152 | 15 | 2.0692e-05 | 440.0675 | 5.3864 | 188.6296 | 768.4594 | 7.9071 | 14.3909 | 359.7552 | 1.3465 | 0.013873 | 4.8437e-05 | 0.23404 | 0.66124 | {A665CE56-6C65-40F6-B673-46690B88E477} | 182631107 | SAN LUIS OBISPO 1107 | 88962 | 35.244 | -120.6751 | SAN LUIS OBISPO 110788962 | 89 | 90 | 10180.5306 | 6411.4652 | 3769.0654 | 3512.4168 | 1723.2062 | 0.00072656 | 0.00031038 | 2.4741 | 6.2667 | 2241 | 0.20809 | 698 | 0 | 0 | 2.1825 | 2629 | 0
North Coast | 3876 | 412 | 571.1409 | 1019 | 930.6513 | 113 | 6.5112e-05 | 204.4054 | 3.8532 | 253.002 | 3004.5307 | 50.959 | 4.6924 | 140.8501 | 1.3058 | 0.013866 | 0.00014767 | 0.40432 | 0.6137 | {C4DDBB89-4E15-4D06-A02D-161343869D3B} | 42751113 | FITCH MOUNTAIN 1113 | 24550 | 38.5793 | -122.878 | FITCH MOUNTAIN 111324550 | 290 | 240 | 62439.0172 | 35120.4777 | 27318.5394 | 12900.9804 | 9735.9263 | 0.016687 | 0.0073576 | 1.3863 | 9.0177 | 1604 | 1.5669 | 699 | 0 | 0 | 8.0163 | 1704 | 0
Central Coast | 730 | 908 | 1789.5793 | 2076 | 2476.5842 | 240 | 4.9374e-05 | 391.9578 | 2.1879 | 30.1354 | 96.0408 | 1.4632 | 10.721 | 93.5328 | 1.1416 | 0.013837 | 6.5417e-05 | 0.43738 | 0.7226 | {33647C9D-A594-482D-97B0-F9F1AC5928F8} | 83242105 | MORGAN HILL 2105 | XR176 | 37.0929 | -121.6472 | MORGAN HILL 2105XR176 | 558 | 400 | 79197.8253 | 44144.6443 | 35053.181 | 32979.6694 | 25994.2998 | 0.0157 | 0.01185 | 1.9709 | 8.65 | 2086 | 3.321 | 700 | 0 | 0 | 20.4926 | 2001 | 0
Sierra | 6642 | 18 | 22.9994 | 228 | 156.0003 | 11 | 5.8409e-05 | 255.5051 | 15.4911 | 2039.0464 | 13790.7716 | 365.0034 | 1.9871 | 126.0387 | 1.1999 | 0.015895 | 0.00026339 | 0.078947 | 0.14743 | {605680BF-CE15-4E43-86C0-2D915CDAFCDB} | 42021112 | NAPA 1112 | 1302 | 38.2948 | -122.2444 | NAPA 11121302 | 378 | 504 | 64949.8628 | 35471.4937 | 29478.3691 | 14540.3445 | 6684.6247 | 0.0028973 | 0.0006425 | 1.2777 | 20.7273 | 1213 | 0.17484 | 701 | 0 | 0 | 9.0349 | 1520 | 0
Bay Area | 6642 | 67 | 106.5291 | 881 | 601.3027 | 82 | 4.6943e-05 | 286.4209 | 5.5026 | 620.8789 | 3955.1104 | 134.432 | 2.666 | 204.2994 | 1.3013 | 0.013473 | 0.00013485 | 0.07605 | 0.17716 | {605680BF-CE15-4E43-86C0-2D915CDAFCDB} | 42021112 | NAPA 1112 | 1302 | 38.2948 | -122.2444 | NAPA 11121302 | 378 | 504 | 64949.8628 | 35471.4937 | 29478.3691 | 14540.3445 | 6684.6247 | 0.011058 | 0.0038493 | 1.59 | 10.7439 | 1666 | 1.1048 | 701 | 0 | 0 | 9.0349 | 2097 | 0
North Coast | 6670 | 147 | 189.1691 | 257 | 253.7322 | 26 | 8.6758e-05 | 174.0163 | 2.305 | 63.6739 | 719.4713 | 4.8654 | 3.5648 | 48.1736 | 1.1371 | 0.013758 | 0.00012853 | 0.57198 | 0.74555 | {40B1E31D-7977-4CD1-A0DB-03E15686CC3E} | 42821102 | CLOVERDALE 1102 | 670 | 38.7831 | -123.0115 | CLOVERDALE 1102670 | 137 | 99 | 15970.1655 | 9645.5215 | 6324.644 | 4063.4864 | 2783.4503 | 0.0033419 | 0.0022557 | 1.2869 | 9.8846 | 1705 | 0.3577 | 702 | 0 | 0 | 2.5249 | 2672 | 0
North Valley | 258 | 52 | 77.2744 | 188 | 110.8386 | 54 | 3.2904e-05 | 482.5909 | 14.2849 | 804.4373 | 3509.5273 | 77.5383 | 14.359 | 780.0261 | 1.5177 | 0.013726 | 0.00026298 | 0.2766 | 0.69718 | {CF12C406-6CA2-4C76-9872-006022544058} | 103091102 | CLARK ROAD 1102 | 2584 | 39.647 | -121.6345 | CLARK ROAD 11022584 | 98 | 69 | 21095.2204 | 15088.9555 | 6006.2649 | 13236.8465 | 5751.5685 | 0.014201 | 0.0017768 | 1.486 | 3.4815 | 1214 | 0.74119 | 703 | 0 | 0 | 8.225 | 540 | 0
North Valley | 6425 | 589 | 1185.0476 | 1890 | 1559.89 | 255 | 0.00010553 | 123.2361 | 42.1553 | 541.4944 | 7770.146 | 1744.3864 | 6.0508 | 67.2385 | 1.1013 | 0.013681 | 0.0021546 | 0.31164 | 0.7597 | {F99AC090-1DE1-40AB-890A-9A8208858415} | 103401102 | GIRVAN 1102 | 1028 | 40.5709 | -122.4263 | GIRVAN 11021028 | 342 | 357 | 46648.8261 | 28149.0621 | 18499.7641 | 28149.0621 | 18499.7641 | 0.54941 | 0.026909 | 2.012 | 7.4118 | 166 | 3.4886 | 704 | 0 | 0 | 17.491 | 2439 | 0
Sierra | 2755 | 69 | 116.5815 | 512 | 294.1205 | 42 | 7.0713e-05 | 283.9589 | 5.0585 | 35.3987 | 125.5042 | 2.1176 | 10.3844 | 58.0013 | 1.0366 | 0.01366 | 0.00021651 | 0.13477 | 0.39637 | {88D11C1E-94DA-491E-B166-BE630EDE0741} | 152561107 | PENRYN 1107 | 2410 | 38.7953 | -121.1642 | PENRYN 11072410 | 166 | 136 | 21289.9141 | 12099.1952 | 9190.7189 | 4627.9566 | 3798.1414 | 0.0090932 | 0.0029699 | 1.6896 | 12.1905 | 1355 | 0.57371 | 705 | 0 | 0 | 2.8757 | 1987 | 0
North Coast | 4613 | 418 | 542.0231 | 618 | 652.9043 | 68 | 0.00011173 | 137.8638 | 68.1535 | 2303.7237 | 47098.5191 | 6865.5406 | 8.5852 | 192.9842 | 1.3488 | 0.013631 | 0.0037217 | 0.67638 | 0.83017 | {69FCB8B8-95BC-4541-BD6A-BC578FAA27C9} | 42661103 | WILLITS 1103 | 91948 | 39.4275 | -123.3154 | WILLITS 110391948 | 90 | 85 | 17830.6584 | 11902.8785 | 5927.7798 | 11264.7541 | 5574.3088 | 0.25308 | 0.007598 | 1.2967 | 9.0882 | 68 | 0.9269 | 706 | 0 | 0 | 6.9996 | 2358 | 0
Bay Area | 5010 | 263 | 450.1249 | 562 | 620.9524 | 57 | 7.1562e-05 | 236.4391 | 0.83167 | 52.0084 | 313.4371 | 0.82562 | 1.5234 | 77.901 | 1.1569 | 0.013606 | 5.8465e-05 | 0.46797 | 0.72489 | {B9FC928F-6B55-4781-A3B8-3405DC4F241D} | 43432102 | SILVERADO 2102 | 3010 | 38.4921 | -122.416 | SILVERADO 21023010 | 229 | 171 | 29353.5887 | 20812.5079 | 8541.0809 | 5441.3026 | 273.3049 | 0.0033325 | 0.004079 | 1.7115 | 9.8596 | 2156 | 0.77557 | 707 | 0 | 0 | 3.3811 | 2566 | 0
North Valley | 8070 | 15 | 28.4574 | 208 | 79.8889 | 57 | 4.5316e-05 | 329.5263 | 17.8097 | 364.6773 | 2397.5826 | 142.2941 | 8.0868 | 265.8507 | 1.2748 | 0.0136 | 0.00029372 | 0.072115 | 0.35621 | {D6DFAF59-685A-49A8-AAFF-CFC87952A858} | 103541104 | RED BLUFF 1104 | 1302 | 40.2058 | -122.2533 | RED BLUFF 11041302 | 144 | 94 | 29347.4953 | 22589.5236 | 6757.9717 | 21098.7836 | 6442.5334 | 0.016742 | 0.002583 | 1.8972 | 3.6491 | 1141 | 0.77517 | 708 | 0 | 0 | 13.1102 | 591 | 0
Sierra | 3093 | 0 | 0 | 32 | 6.8291 | 8 | 4.3876e-05 | 333.7425 | 1.9629 | 185.2947 | 802.624 | 2.5254 | 6.8294 | 470.8172 | 1.3374 | 0.013593 | 5.3972e-05 | 0 | 0 | {52DF98AE-4F53-4A02-A20B-FB744471A897} | 152331108 | EAST MARYSVILLE 1108 | 1706 | 39.182 | -121.5434 | EAST MARYSVILLE 11081706 | 787 | 701 | 146892.557 | 96667.4367 | 50225.1203 | 891.2903 | 45.1189 | 0.00043178 | 0.00035101 |  | 4 | 2205 | 0.10874 | 709 | 0 | 0 | 0.55382 | 100 | 0
North Coast | 4590 | 234 | 316.7225 | 769 | 641.2167 | 81 | 7.39e-05 | 179.9395 |  |  |  |  | 3.6636 | 142.7654 | 1.1529 | 0.013585 | 7.39e-05 | 0.30429 | 0.49394 | {F0A897EB-747B-40C7-9836-35FB75DF52B9} | 42751113 | FITCH MOUNTAIN 1113 | 352 | 38.6126 | -122.8546 | FITCH MOUNTAIN 1113352 | 172 | 564 | 48895.8583 | 19254.3259 | 29641.5324 | 9077.2683 | 7619.9555 | 0.0059859 | 0.0059859 | 1.3535 | 9.4938 | 2027 | 1.1004 | 710 | 0 | 0 | 5.6404 | 2500 | 0
Bay Area | 3972 | 87 | 106.8111 | 103 | 113.8679 | 26 | 1.4065e-05 | 1153.374 | 52.2424 | 1782.2967 | 6199.6621 | 341.0244 | 17.1383 | 2343.1849 | 1.5969 | 0.013538 | 0.00045013 | 0.84466 | 0.93803 | {BE7BFFAE-6862-4503-AA75-EA4658F3F71F} | 12022213 | CLAYTON 2213 | circuit_breaker | 37.9448 | -121.9697 | CLAYTON 2213circuit_breaker | 112 | 156 | 17446.3163 | 9977.7681 | 7468.5482 | 6236.8648 | 296.1869 | 0.011703 | 0.00036569 | 1.2277 | 3.9615 | 861 | 0.352 | 711 | 0 | 0 | 3.8754 | 241 | 0
North Coast | 6156 | 1187 | 1629.8098 | 2172 | 2087.3557 | 337 | 7.1457e-05 | 190.8825 | 9.4187 | 831.0548 | 11793.4232 | 267.6037 | 1.745 | 151.7331 | 1.3128 | 0.013527 | 0.00033663 | 0.5465 | 0.7808 | {51D9F3E7-D9FC-4F6D-B9B5-400B76D74D25} | 42771114 | UKIAH 1114 | 408 | 39.1065 | -123.1981 | UKIAH 1114408 | 336 | 298 | 102476.0339 | 60895.2254 | 41580.8085 | 59693.1649 | 39387.6184 | 0.11344 | 0.024081 | 1.373 | 6.4451 | 1037 | 4.5587 | 712 | 0 | 0 | 37.0916 | 2255 | 0
North Coast | 5971 | 1598 | 2620.2255 | 2068 | 2848.3503 | 158 | 9.7142e-05 | 143.6149 | 1.9811 | 51.6355 | 558.7525 | 2.3551 | 0.70843 | 12.4771 | 1.0677 | 0.013514 | 0.00013739 | 0.77273 | 0.91991 | {7CD25D9B-B7BF-4806-8728-687CBA0C8188} | 192221101 | GARBERVILLE 1101 | 35706 | 39.8714 | -123.7119 | GARBERVILLE 110135706 | 162 | 252 | 24034.4148 | 16258.1269 | 7776.2879 | 16258.1269 | 7776.2879 | 0.021708 | 0.015349 | 1.6397 | 13.0886 | 1651 | 2.1352 | 713 | 0 | 0 | 10.1023 | 1415 | 0
Bay Area | 6733 | 116 | 186.2714 | 205 | 236.6396 | 27 | 9.8532e-05 | 157.8538 | 2.6833 | 60.0501 | 561.299 | 5.2358 | 2.0892 | 63.5447 | 1.2407 | 0.013491 | 0.00013365 | 0.56585 | 0.78715 | {07D5D1F0-E088-492A-95F0-C51ED4C7A4B4} | 42711101 | CALISTOGA 1101 | circuit_breaker | 38.5922 | -122.5789 | CALISTOGA 1101circuit_breaker | 188 | 194 | 32486.6549 | 15415.3431 | 17071.3117 | 3212.9518 | 2572.8827 | 0.0036087 | 0.0026604 | 1.6058 | 7.5926 | 1679 | 0.36424 | 714 | 0 | 0 | 1.9964 | 2452 | 0
Sierra | 375 | 740 | 1258.4363 | 2710 | 1968.7141 | 508 | 6.2806e-05 | 229.2764 | 9.2039 | 333.0982 | 2130.2973 | 38.3249 | 9.7994 | 197.6444 | 1.3228 | 0.013435 | 0.00030224 | 0.27306 | 0.63922 | {B62D2B6F-534A-4DA4-BEF0-CD31B9D7374D} | 152282101 | MOUNTAIN QUARRIES 2101 | 1102 | 38.8698 | -121.0202 | MOUNTAIN QUARRIES 21011102 | 621 | 450 | 102796.2725 | 71641.3725 | 31154.9 | 71641.3725 | 31154.9 | 0.15354 | 0.031905 | 1.7006 | 5.3346 | 1118 | 6.825 | 715 | 0 | 0 | 44.5159 | 7 | 0
North Valley | 2076 | 53 | 76.1359 | 116 | 97.9941 | 13 | 7.0534e-05 | 286.5534 | 35.6587 | 178.2282 | 730.9795 | 27.2035 | 13.9295 | 157.1268 | 1.0425 | 0.013418 | 0.00173 | 0.4569 | 0.77694 | {10790C99-0AC4-4885-95AD-50DB99DD62BD} | 102911109 | WYANDOTTE 1109 | 1040 | 39.4591 | -121.5322 | WYANDOTTE 11091040 | 93 | 109 | 16501.2518 | 9730.261 | 6770.9908 | 1355.0481 | 50.9292 | 0.02249 | 0.00091694 | 1.4365 | 8.9231 | 204 | 0.17443 | 716 | 0 | 0 | 0.84199 | 1977 | 0
Central Coast | 2918 | 282 | 430.6075 | 1226 | 1020.1207 | 152 | 5.6737e-05 | 231.0853 | 1.9628 | 60.0353 | 219.4803 | 1.0908 | 9.0569 | 105.8573 | 1.1268 | 0.013396 | 7.692e-05 | 0.23002 | 0.42211 | {C1DF3268-8D83-469E-AB38-F1D09D72570E} | 183052111 | TEMPLETON 2111 | R86 | 35.5357 | -120.7225 | TEMPLETON 2111R86 | 236 | 198 | 36369.6536 | 23059.3782 | 13310.2754 | 17358.9842 | 7985.8358 | 0.011692 | 0.008624 | 1.527 | 8.0658 | 2004 | 2.0361 | 717 | 0 | 0 | 10.7864 | 2804 | 0
Sierra | 6699 | 301 | 536.2493 | 1004 | 845.7837 | 116 | 7.978e-05 | 185.0407 | 12.9772 | 53.4339 | 210.4102 | 6.3652 | 13.2856 | 80.3111 | 1.1087 | 0.01325 | 0.00053023 | 0.2998 | 0.63403 | {6FA4A1F6-3AB8-4114-8002-DF4E0174192B} | 152561105 | PENRYN 1105 | 51676 | 38.8519 | -121.1638 | PENRYN 110551676 | 260 | 352 | 36741.2074 | 18974.9476 | 17766.2599 | 11966.6651 | 12450.1185 | 0.061507 | 0.0092545 | 1.7816 | 8.6552 | 759 | 1.537 | 718 | 0 | 0 | 7.4357 | 1087 | 0
North Coast | 4588 | 57 | 102.5553 | 152 | 138.3884 | 50 | 5.7719e-05 | 250.4046 | 5.0184 | 1005.8448 | 13237.7208 | 199.4608 | 10.7631 | 486.7053 | 1.5428 | 0.013126 | 0.00020408 | 0.375 | 0.74107 | {ADA3ACDD-1F23-47D9-8D0C-75E817018764} | 43191101 | REDBUD 1101 | 454 | 39.0839 | -122.6601 | REDBUD 1101454 | 66 | 44 | 13036.2188 | 8939.3598 | 4096.859 | 8939.3598 | 4096.859 | 0.010204 | 0.002886 | 1.7992 | 3.04 | 1400 | 0.65628 | 719 | 0 | 0 | 5.5547 | 1179 | 0
Sierra | 5027 | 486 | 799.728 | 2469 | 1608.3402 | 221 | 8.3935e-05 | 224.4732 | 8.2108 | 42.472 | 207.4762 | 5.1908 | 4.6608 | 41.0722 | 1.0713 | 0.013025 | 0.00033887 | 0.19684 | 0.49724 | {C7CE8EEC-BFCB-464B-A0B6-4DE95EE01B52} | 152241101 | HALSEY 1101 | 2414 | 38.9661 | -121.0355 | HALSEY 11012414 | 277 | 380 | 46338.0186 | 23778.9553 | 22559.0633 | 23778.9553 | 22559.0633 | 0.074891 | 0.01855 | 1.6455 | 11.1719 | 1033 | 2.8785 | 720 | 0 | 0 | 14.7756 | 884 | 0
North Valley | 1273 | 337 | 591.2331 | 834 | 743.228 | 203 | 5.3489e-05 | 222.9973 | 5.4262 | 834.5292 | 4521.6409 | 43.0601 | 6.3082 | 384.455 | 1.3226 | 0.013023 | 0.0001519 | 0.40408 | 0.79549 | {EEFE9838-86A6-45F2-A82C-8153A8246E80} | 103351101 | DESCHUTES 1101 | 1652 | 40.5339 | -122.1437 | DESCHUTES 11011652 | 215 | 181 | 63034.7696 | 39313.9968 | 23720.7728 | 32556.3926 | 22242.7765 | 0.030836 | 0.010858 | 1.7544 | 4.1084 | 1582 | 2.6436 | 721 | 0 | 0 | 20.2296 | 339 | 0
North Valley | 4337 | 52 | 99.7384 | 165 | 141.8977 | 19 | 4.8733e-05 | 225.3598 | 12.6401 | 491.4691 | 2453.1991 | 126.18 | 6.9757 | 215.7136 | 1.3142 | 0.012996 | 0.00039103 | 0.31515 | 0.70289 | {FB82AB7C-AC69-4B2A-A438-BEFDB6C26140} | 103091102 | CLARK ROAD 1102 | 2094 | 39.6569 | -121.576 | CLARK ROAD 11022094 | 30 | 1 | 5553.0721 | 5527.8648 | 25.2072 | 5527.8648 | 25.2072 | 0.0074296 | 0.00092593 | 1.918 | 8.6842 | 957 | 0.24692 | 722 | 0 | 0 | 3.4349 | 1256 | 0
North Coast | 5157 | 2232 | 4000.3574 | 2718 | 4233.6 | 231 | 0.00025005 | 53.029 | 2.3237 | 189.1926 | 1449.4726 | 6.2309 | 0.48575 | 42.2129 | 1.075 | 0.012993 | 0.00040694 | 0.82119 | 0.94491 | {37DB383D-2CA0-40C2-9028-FCF646539713} | 192221102 | GARBERVILLE 1102 | 2500 | 40.1079 | -123.9289 | GARBERVILLE 11022500 | 133 | 82 | 31045.2848 | 25786.904 | 5258.3808 | 25786.904 | 5258.3808 | 0.094003 | 0.057761 | 1.7923 | 11.7662 | 934 | 3.0015 | 723 | 0 | 0 | 16.0232 | 1616 | 0
North Coast | 7795 | 532 | 899.7737 | 613 | 939.7021 | 77 | 0.00016234 | 75.074 | 0.10917 | 72.0098 | 483.2568 | 0.10113 | 0.00045972 | 14.0763 | 1.0351 | 0.01283 | 9.3253e-05 | 0.86786 | 0.95751 | {7FB18F66-61A5-4984-9B43-02F544D8F8C8} | 192311141 | FRUITLAND 1141 | 3902 | 40.3428 | -123.9157 | FRUITLAND 11413902 | 15 | 4 | 8305.404 | 8223.6344 | 81.7696 | 4505.0192 | 81.7696 | 0.0071804 | 0.0125 | 1.6913 | 7.961 | 1889 | 0.98791 | 724 | 0 | 0 | 2.7993 | 541 | 0
North Coast | 6403 | 858 | 1445.3692 | 1180 | 1589.5806 | 126 | 8.9832e-05 | 149.8857 | 0.95027 | 229.8964 | 3934.6536 | 10.1251 | 0.26456 | 24.558 | 1.1842 | 0.012822 | 8.8075e-05 | 0.72712 | 0.90928 | {A82CFD07-C2CE-4724-B78F-F024AA45842E} | 42681101 | LAYTONVILLE 1101 | 1760 | 39.8255 | -123.5937 | LAYTONVILLE 11011760 | 87 | 89 | 25141.5739 | 20359.96 | 4781.6139 | 15633.6438 | 3906.3779 | 0.011097 | 0.011319 | 1.6846 | 9.3651 | 1925 | 1.6155 | 725 | 0 | 0 | 9.7143 | 3 | 0
North Coast | 4667 | 392 | 555.2262 | 658 | 708.0456 | 110 | 6.4645e-05 | 213.2163 | 5.3656 | 933.8197 | 12636.2963 | 206.1376 | 1.522 | 155.4561 | 1.2988 | 0.012748 | 0.00021893 | 0.59574 | 0.78417 | {D3629DD4-F83C-4237-B37C-A36F4F11F0E0} | 42821102 | CLOVERDALE 1102 | 674 | 38.8294 | -123.0064 | CLOVERDALE 1102674 | 171 | 231 | 45952.6285 | 31757.8273 | 14194.8012 | 25986.6813 | 7825.4838 | 0.024082 | 0.007111 | 1.4164 | 5.9818 | 1345 | 1.4022 | 726 | 0 | 0 | 16.1474 | 927 | 0
North Valley | 9027 | 67 | 99.8341 | 131 | 127.825 | 39 | 4.4439e-05 | 300.0928 | 7.8935 | 3130.1756 | 49762.2405 | 610.2281 | 3.2787 | 463.4736 | 1.6238 | 0.012744 | 0.00019958 | 0.51145 | 0.78102 | {BF76B4C8-9530-427B-8649-806B9F48C554} | 103611101 | WILDWOOD 1101 | 98896 | 40.3609 | -122.9517 | WILDWOOD 110198896 | 36 | 35 | 16825.3737 | 15545.2226 | 1280.1512 | 15545.2226 | 1280.1512 | 0.0077837 | 0.0017331 | 1.4901 | 3.359 | 1414 | 0.49702 | 727 | 0 | 0 | 9.6594 | 2770 | 0
North Coast | 3075 | 2010 | 3193.9748 | 3899 | 4254.4346 | 339 | 0.00014604 | 81.4639 | 16.5029 | 274.3105 | 2523.9023 | 176.076 | 4.6105 | 68.4647 | 1.1694 | 0.012741 | 0.0014298 | 0.51552 | 0.75074 | {7D5BEB0A-06FF-4975-900C-BDCD4AFAA92D} | 42571102 | MOLINO 1102 | 104 | 38.403 | -122.9214 | MOLINO 1102104 | 444 | 420 | 64861.2629 | 34941.2444 | 29920.0185 | 34941.2444 | 29920.0185 | 0.48469 | 0.049509 | 1.589 | 11.5015 | 265 | 4.3192 | 728 | 0 | 0 | 21.7115 | 1316 | 0
North Coast | 5255 | 193 | 233.8099 | 526 | 441.69 | 39 | 0.00010746 | 112.9379 |  |  |  |  | 5.296 | 22.5299 | 1.128 | 0.012733 | 0.00010746 | 0.36692 | 0.52935 | {31A95017-FE64-4D4F-A4CA-39176F23B79F} | 42751113 | FITCH MOUNTAIN 1113 | 406 | 38.6211 | -122.8757 | FITCH MOUNTAIN 1113406 | 176 | 237 | 37235.0823 | 15193.9016 | 22041.1806 | 3309.8931 | 2891.7978 | 0.0041908 | 0.0041908 | 1.2115 | 13.4872 | 1819 | 0.4966 | 729 | 0 | 0 | 2.0567 | 1788 | 0
North Coast | 6208 | 72 | 159.3117 | 87 | 165.8351 | 21 | 8.6308e-05 | 173.0493 | 9.3879 | 139.931 | 402.0524 | 15.2991 | 3.185 | 183.2363 | 1.1612 | 0.012733 | 0.00032875 | 0.82759 | 0.96066 | {05266111-8CFD-418B-8046-91385E641AA2} | 43161101 | SALMON CREEK 1101 | 37368 | 38.381 | -123.079 | SALMON CREEK 110137368 | 82 | 78 | 14140.2064 | 10726.7893 | 3413.4171 | 10726.7893 | 3413.4171 | 0.0069038 | 0.0018125 | 2.2127 | 4.1429 | 1059 | 0.26739 | 730 | 0 | 0 | 6.6653 | 1560 | 0
North Coast | 3782 | 1484 | 2134.236 | 2002 | 2392.5034 | 164 | 0.00010258 | 127.7458 | 50.6735 | 1491.8332 | 16145.2048 | 1720.6429 | 1.9375 | 86.2572 | 1.1555 | 0.012731 | 0.0022896 | 0.74126 | 0.89205 | {3B860DB0-A747-4B2B-900E-A58BF536B758} | 42661103 | WILLITS 1103 | 2506 | 39.4625 | -123.3374 | WILLITS 11032506 | 112 | 81 | 25751.8107 | 19672.0333 | 6079.7774 | 19186.052 | 6059.8007 | 0.37549 | 0.016823 | 1.4382 | 12.2073 | 155 | 2.0878 | 731 | 0 | 0 | 11.9217 | 183 | 0
Central Coast | 3211 | 700 | 1931.1792 | 2528 | 2961.5752 | 320 | 1.9309e-05 | 757.4431 | 21.798 | 93.701 | 443.3042 | 20.3839 | 20.4456 | 112.099 | 1.1844 | 0.0127 | 0.00020581 | 0.2769 | 0.65208 | {5BBBE0D2-FA05-4DE6-8C44-4E21C5EC4C80} | 182601104 | OCEANO 1104 | Q10 | 35.1351 | -120.5694 | OCEANO 1104Q10 | 485 | 551 | 73760.325 | 37945.3605 | 35814.9645 | 37945.3605 | 35814.9645 | 0.065858 | 0.0061789 | 2.7588 | 7.9 | 1394 | 4.064 | 732 | 0 | 0 | 23.5781 | 1903 | 0
Sierra | 1194 | 2238 | 3148.9905 | 4834 | 4337.917 | 558 | 9.9557e-05 | 140.4893 | 118.9501 | 1637.1338 | 24203.6698 | 5915.4376 | 8.3295 | 97.8856 | 1.2989 | 0.01265 | 0.0055105 | 0.46297 | 0.72592 | {4A1B7FA4-9EA2-489A-952B-02F0D69E191E} | 153662102 | APPLE HILL 2102 | 1532 | 38.6944 | -120.6779 | APPLE HILL 21021532 | 714 | 682 | 115648.0401 | 67838.2746 | 47809.7655 | 60833.3699 | 44361.8137 | 3.0749 | 0.055553 | 1.4071 | 8.6631 | 30 | 7.0586 | 733 | 0 | 0 | 37.8001 | 471 | 0
Bay Area | 7715 | 129 | 217.3456 | 421 | 356.9131 | 72 | 2.7825e-05 | 605.7807 | 50.667 | 533.8631 | 3104.2982 | 388.2035 | 9.2632 | 567.7943 | 1.3161 | 0.012558 | 0.00072732 | 0.30641 | 0.60896 | {32128C45-30E5-4BD3-83C6-38B6DDD0B832} | 12022215 | CLAYTON 2215 | W531R | 37.9176 | -121.9968 | CLAYTON 2215W531R | 243 | 185 | 27693.5137 | 17365.1124 | 10328.4014 | 10534.5095 | 5494.0159 | 0.052367 | 0.0020034 | 1.6848 | 5.8472 | 549 | 0.90415 | 734 | 0 | 0 | 6.5458 | 2448 | 0
Bay Area | 2016 | 236 | 303.6468 | 810 | 650.3328 | 87 | 4.6384e-05 | 269.0528 | 47.2248 | 675.3968 | 10476.0615 | 1380.2083 | 2.1652 | 109.4107 | 1.2355 | 0.012514 | 0.0010567 | 0.29136 | 0.46691 | {EB87F1B0-DF58-4672-B521-8B7DD265BE37} | 43291104 | PUEBLO 1104 | 2802 | 38.338 | -122.2607 | PUEBLO 11042802 | 166 | 179 | 30285.6579 | 17054.4612 | 13231.1967 | 14988.5406 | 9714.5131 | 0.091929 | 0.0040354 | 1.2866 | 9.3103 | 383 | 1.0887 | 735 | 0 | 0 | 9.3134 | 1541 | 0
Central Coast | 2039 | 207 | 653.3445 | 857 | 999.8182 | 116 | 3.8602e-05 | 418.7643 | 2.3039 | 30.128 | 144.1097 | 1.9891 | 10.0788 | 85.3885 | 1.1376 | 0.012507 | 6.3036e-05 | 0.24154 | 0.65346 | {37C0E6FA-9A39-4134-9B6F-8111077BFC3C} | 183181101 | SAN JUSTO 1101 | 36902 | 36.8686 | -121.5543 | SAN JUSTO 110136902 | 187 | 243 | 37082.0704 | 23604.3976 | 13477.6728 | 19755.8941 | 11421.7518 | 0.0073122 | 0.0044779 | 3.1563 | 7.3879 | 2113 | 1.4509 | 736 | 0 | 0 | 12.2757 | 2592 | 0
Bay Area | 2362 | 1915 | 3398.6959 | 2579 | 3812.9211 | 136 | 9.821e-05 | 137.852 | 0.84954 | 24.1008 | 157.6085 | 0.37206 | 0.73998 | 17.694 | 1.1155 | 0.012496 | 9.6566e-05 | 0.74254 | 0.89136 | {E37F33F6-1C0A-4C76-AC62-7F0B65A2F196} | 24251101 | WOODSIDE 1101 | 8884 | 37.3895 | -122.2687 | WOODSIDE 11018884 | 115 | 67 | 16158.595 | 12455.5334 | 3703.0616 | 12455.5334 | 3703.0616 | 0.013133 | 0.013357 | 1.7748 | 18.9632 | 1871 | 1.6995 | 737 | 0 | 0 | 7.7395 | 1340 | 0
Central Coast | 6975 | 103 | 132.4058 | 355 | 299.8773 | 45 | 2.7185e-05 | 221.3862 | 2.0879 | 362.0941 | 1744.0427 | 19.4661 | 4.6424 | 271.864 | 1.2707 | 0.012432 | 2.8208e-05 | 0.29014 | 0.44153 | {2B5B2782-BD1A-416F-A256-E14A66306210} | 182721101 | SANTA YNEZ 1101 | Y16 | 34.5994 | -120.0995 | SANTA YNEZ 1101Y16 | 142 | 70 | 28439.0414 | 23205.9514 | 5233.09 | 12159.0407 | 1806.243 | 0.0012694 | 0.0012233 | 1.2855 | 7.8889 | 2487 | 0.55943 | 738 | 0 | 0 | 7.5553 | 1801 | 0
North Coast | 7961 | 1484 | 2979.5676 | 1549 | 3013.4592 | 114 | 9.902e-05 | 118.7665 | 1.3044 | 110.6445 | 667.3039 | 1.7485 | 1.4508 | 112.3183 | 1.1862 | 0.012411 | 0.00011367 | 0.95804 | 0.98875 | {6432AE5E-F371-470F-8E71-1BA304A7A433} | 42851121 | FORT ROSS 1121 | circuit_breaker | 38.5405 | -123.2243 | FORT ROSS 1121circuit_breaker | 156 | 128 | 32261.3871 | 20387.5307 | 11873.8564 | 20387.5307 | 11873.8564 | 0.012958 | 0.011288 | 2.0078 | 13.5877 | 1782 | 1.4149 | 739 | 0 | 0 | 12.6682 | 1283 | 0
Central Coast | 2154 | 727 | 1247.2999 | 2079 | 2056.408 | 325 | 7.0952e-05 | 215.4011 | 10.3398 | 54.1904 | 217.4709 | 4.1083 | 10.1879 | 62.8299 | 1.159 | 0.012398 | 0.00040356 | 0.34969 | 0.60654 | {C51913E0-1635-4DCE-BB82-7AF8898196AC} | 182541101 | ATASCADERO 1101 | A02 | 35.4838 | -120.6842 | ATASCADERO 1101A02 | 364 | 425 | 67048.6252 | 42537.755 | 24510.8703 | 42537.755 | 24510.8703 | 0.13116 | 0.023059 | 1.7157 | 6.3969 | 939 | 4.0292 | 740 | 0 | 0 | 26.4317 | 1630 | 0
Bay Area | 2131 | 510 | 809.9322 | 1648 | 1499.8396 | 155 | 4.3211e-05 | 302.1091 | 2.4257 | 121.6466 | 1154.5011 | 13.1033 | 3.7046 | 148.1125 | 1.237 | 0.01236 | 6.9785e-05 | 0.30947 | 0.54001 | {78AAB710-6DDE-407F-827D-71666B977FA6} | 43291105 | PUEBLO 1105 | 696 | 38.3575 | -122.2867 | PUEBLO 1105696 | 371 | 285 | 89022.1429 | 46972.3367 | 42049.8062 | 30001.1055 | 22222.3267 | 0.010817 | 0.0066977 | 1.5881 | 10.6323 | 2060 | 1.9158 | 741 | 0 | 0 | 18.6418 | 2951 | 0
North Valley | 284 | 943 | 1182.9395 | 3003 | 2240.1802 | 333 | 0.00011677 | 103.1462 | 11.7251 | 1437.7359 | 18330.7412 | 451.4462 | 2.3184 | 154.0576 | 1.173 | 0.012317 | 0.00074632 | 0.31402 | 0.52806 | {0A7498D4-3D67-421B-B0F9-EE472ACD2B71} | 103601101 | WHITMORE 1101 | 1598 | 40.6208 | -121.9332 | WHITMORE 11011598 | 303 | 195 | 71002.8329 | 53639.2857 | 17363.5472 | 53639.2857 | 17363.5472 | 0.24852 | 0.038884 | 1.2544 | 9.018 | 535 | 4.1017 | 742 | 0 | 0 | 33.3299 | 20 | 0
North Coast | 6032 | 380 | 640.5256 | 829 | 894.9778 | 59 | 0.00015602 | 79.5228 | 11.7037 | 44.1472 | 164.4931 | 4.2985 | 6.6641 | 24.7749 | 1.0271 | 0.012311 | 0.0008617 | 0.45838 | 0.71569 | {1AA340F3-9B5E-42DA-A4FD-20D0C36458DA} | 42571101 | MOLINO 1101 | 891 | 38.3901 | -122.8854 | MOLINO 1101891 | 72 | 111 | 12604.6859 | 5070.4899 | 7534.196 | 5053.4192 | 6791.6859 | 0.05084 | 0.0092053 | 1.6856 | 14.0508 | 465 | 0.72638 | 743 | 0 | 0 | 3.14 | 433 | 0
Central Valley | 7295 | 336 | 499.717 | 902 | 784.4258 | 80 | 5.1762e-05 | 360.5163 | 54.791 | 826.4773 | 12578.0109 | 1575.7778 | 1.0099 | 122.1533 | 1.3566 | 0.012271 | 0.0014084 | 0.37251 | 0.63705 | {5ACF71BC-5CB9-4FB2-84D8-E7796B319ECF} | 162821702 | STANISLAUS 1702 | circuit_breaker | 38.1398 | -120.3703 | STANISLAUS 1702circuit_breaker | 123 | 114 | 17893.8584 | 12811.6118 | 5082.2466 | 12811.6118 | 5082.2466 | 0.11268 | 0.004141 | 1.4873 | 11.275 | 271 | 0.98169 | 744 | 0 | 0 | 7.9608 | 2676 | 0
Bay Area | 4870 | 564 | 959.7839 | 1194 | 1317.152 | 36 | 0.00011984 | 101.0874 | 9.2722 | 6.6799 | 27.5413 | 0.49137 | 1.9263 | 2.4552 | 1.0277 | 0.012252 | 0.00060296 | 0.47236 | 0.72868 | {9A8B6C23-4C04-4C78-BA0B-C933E8EB9B64} | 42031124 | ALTO 1124 | 3121 | 37.905 | -122.5579 | ALTO 11243121 | 81 | 230 | 14524.1499 | 4421.122 | 10103.0278 | 4421.122 | 10103.0278 | 0.021706 | 0.0043141 | 1.7017 | 33.1667 | 666 | 0.44106 | 745 | 0 | 0 | 2.7472 | 1217 | 0
Sierra | 1154 | 347 | 495.0202 | 1301 | 912.3605 | 188 | 6.9042e-05 | 240.9561 | 30.5654 | 387.0809 | 3551.1884 | 305.1098 | 6.3767 | 119.5597 | 1.2769 | 0.012204 | 0.0012201 | 0.26672 | 0.54257 | {09764360-E1BF-4969-86D7-B4D769F58355} | 152691104 | HIGGINS 1104 | 4281 | 39.0915 | -121.0564 | HIGGINS 11044281 | 177 | 105 | 31759.1064 | 21369.438 | 10389.6685 | 21369.438 | 10389.6685 | 0.22938 | 0.01298 | 1.4266 | 6.9202 | 315 | 2.2943 | 746 | 0 | 0 | 13.2783 | 649 | 0
Central Valley | 5815 | 94 | 217.8925 | 203 | 252.7654 | 89 | 4.0957e-05 | 216.5313 |  |  |  |  | 12.624 | 1013.2413 | 1.715 | 0.012189 | 4.0957e-05 | 0.46305 | 0.86203 | {F84D57DC-FE09-4A90-9BFD-E1132269D500} | 255292108 | WOODWARD 2108 | 78448 | 37.0197 | -119.7297 | WOODWARD 210878448 | 226 | 155 | 57025.9223 | 47714.7864 | 9311.1359 | 28435.4926 | 6650.7299 | 0.0036451 | 0.0036451 | 2.318 | 2.2809 | 2329 | 1.0848 | 747 | 0 | 0 | 17.669 | 1922 | 0
Central Coast | 5984 | 164 | 377.9688 | 596 | 645.1812 | 87 | 3.806e-05 | 469.4239 | 3.6369 | 50.1276 | 208.7772 | 3.2984 | 10.4678 | 93.6826 | 1.1303 | 0.012046 | 7.5168e-05 | 0.27517 | 0.58583 | {E9AA9F27-D8AA-4BDE-8886-2873D43D7B19} | 183181101 | SAN JUSTO 1101 | 4339 | 36.8681 | -121.5544 | SAN JUSTO 11014339 | 137 | 149 | 27454.8643 | 17685.5192 | 9769.3451 | 11461.6704 | 8123.0157 | 0.0065396 | 0.0033112 | 2.3047 | 6.8506 | 2019 | 1.048 | 748 | 0 | 0 | 7.1219 | 1531 | 0
North Valley | 4860 | 0 | 0 | 12 | 4.4995 | 4 | 1.0497e-05 | 1068.3213 | 0.64012 | 143.3333 | 578.4624 | 0.44207 | 16.948 | 1016.3264 | 1.5785 | 0.012037 | 9.7704e-06 | 0 | 0 | {76F913B6-6D49-4D3C-ACC8-2AE24DFE45A2} | 103491102 | MC ARTHUR 1102 | 1324 | 41.0453 | -121.4035 | MC ARTHUR 11021324 | 217 | 172 | 49263.6463 | 41089.9508 | 8173.6955 | 3069.2847 | 186.0193 | 3.9082e-05 | 4.1986e-05 |  | 3 | 2792 | 0.048146 | 749 | 0 | 0 | 1.9072 | 1083 | 0
North Coast | 3022 | 171 | 225.3711 | 368 | 333.057 | 57 | 7.0164e-05 | 169.8959 | 23.2734 | 227.5896 | 2551.9417 | 169.3177 | 5.4693 | 137.0102 | 1.094 | 0.01198 | 0.00074128 | 0.46467 | 0.67667 | {F335CD9B-C6EC-489A-8E1A-57248916AA35} | 42891102 | GEYSERVILLE 1102 | 274 | 38.6627 | -122.8694 | GEYSERVILLE 1102274 | 234 | 212 | 50940.8906 | 30005.2502 | 20935.6403 | 7596.7493 | 3939.4874 | 0.042253 | 0.0039993 | 1.318 | 6.4561 | 539 | 0.68286 | 750 | 0 | 0 | 4.7204 | 274 | 0
Bay Area | 8685 | 18 | 68.6909 | 22 | 70.9619 | 5 | 2.5523e-05 | 438.3306 | 5.1802 | 346.4165 | 1037.7211 | 7.2282 | 16.0783 | 1044.7228 | 1.7673 | 0.011946 | 8.8855e-05 | 0.81818 | 0.968 | {02184DCE-4986-4759-8E54-71AE9F6D44F7} | 14351104 | FREMONT 1104 | MR339 | 37.5421 | -121.9222 | FREMONT 1104MR339 | 97 | 62 | 17399.0262 | 11193.7644 | 6205.2619 | 1796.5075 | 1767.6303 | 0.00044427 | 0.00012762 | 3.8162 | 4.4 | 1921 | 0.059732 | 751 | 0 | 0 | 1.1163 | 2018 | 0
North Coast | 6757 | 167 | 273.3026 | 178 | 278.8671 | 36 | 0.00038466 | 32.4206 | 2.2169 | 57.2661 | 338.133 | 1.0797 | 0.12107 | 10.8162 | 1.0192 | 0.011943 | 0.00066807 | 0.9382 | 0.98005 | {AFC4D0E6-261E-40B5-B86E-B68528CD28DE} | 192311142 | FRUITLAND 1142 | 6054 | 40.2854 | -123.8367 | FRUITLAND 11426054 | 122 | 105 | 19236.7856 | 16837.555 | 2399.2306 | 16837.555 | 2399.2306 | 0.024051 | 0.013848 | 1.6365 | 4.9444 | 598 | 0.42997 | 752 | 0 | 0 | 10.4624 | 659 | 0
Central Valley | 3335 | 2 | 5.7063 | 2 | 5.7063 | 1 | 4.8596e-06 | 2453.6252 |  |  |  |  | 1.4226 | 3087.4749 | 2.1969 | 0.011924 | 4.8596e-06 | 1 | 1 | {A1011A88-A66E-4DA3-B03F-1383046CA8FD} | 253191101 | SAN BERNARD 1101 | circuit_breaker | 35.0924 | -118.8783 | SAN BERNARD 1101circuit_breaker | 335 | 138 | 79753.7282 | 71472.9513 | 8280.7768 | 1475.2454 | 37.9107 | 4.8596e-06 | 4.8596e-06 | 2.8532 | 2 | 2848 | 0.011924 | 753 | 0 | 0 | 0.91667 | 785 | 0
North Coast | 8908 | 1471 | 2424.5379 | 1791 | 2577.7861 | 111 | 0.00029233 | 37.5589 | 0.96425 | 148.8173 | 1898.3052 | 5.4434 | 0.54637 | 21.6654 | 1.2198 | 0.011905 | 0.0002765 | 0.82133 | 0.94055 | {C4977E7A-7767-4DD5-83E3-B05622B35B40} | 192221102 | GARBERVILLE 1102 | 37054 | 40.1653 | -124.0816 | GARBERVILLE 110237054 | 89 | 56 | 17833.7237 | 14832.6398 | 3001.0839 | 13349.1892 | 2946.837 | 0.030692 | 0.032449 | 1.6482 | 16.1351 | 1181 | 1.3215 | 754 | 0 | 0 | 8.2948 | 1182 | 0
North Valley | 3366 | 2668 | 3870.5617 | 5456 | 5187.657 | 379 | 0.00012994 | 92.979 | 166.7117 | 4329.1482 | 95033.3378 | 19540.59 | 1.9304 | 30.8285 | 1.0411 | 0.011856 | 0.0089418 | 0.489 | 0.74611 | {BE69E74E-458C-4AC6-80FE-4A8477C787AD} | 102911103 | WYANDOTTE 1103 | 1974 | 39.6395 | -121.4297 | WYANDOTTE 11031974 | 397 | 403 | 63043.1062 | 36746.286 | 26296.8203 | 36746.286 | 26296.8203 | 3.3889 | 0.049248 | 1.4507 | 14.3958 | 12 | 4.4934 | 755 | 0 | 0 | 22.8331 | 2819 | 0
North Coast | 8910 | 5 | 16.5312 | 7 | 17.6667 | 4 | 6.5175e-05 | 190.8909 | 51.4942 | 409.873 | 2133.343 | 109.8548 | 12.8037 | 133.0728 | 1.1162 | 0.011848 | 0.00086134 | 0.71429 | 0.93573 | {991C05ED-971F-4D32-B6E6-51948C4F329B} | 42271102 | COTATI 1102 | circuit_breaker | 38.3094 | -122.7318 | COTATI 1102circuit_breaker | 28 | 17 | 4312.2274 | 3229.2079 | 1083.0195 | 2904.3184 | 917.0955 | 0.0034453 | 0.0002607 | 3.3062 | 1.75 | 466 | 0.047392 | 756 | 0 | 0 | 1.8047 | 632 | 0
Sierra | 4291 | 374 | 589.8089 | 1247 | 1038.0146 | 122 | 8.3568e-05 | 256.7899 | 17.6293 | 113.8459 | 560.4711 | 15.4232 | 6.5237 | 63.0742 | 1.1086 | 0.011831 | 0.0006416 | 0.29992 | 0.56821 | {735D1686-195C-449F-AFF7-F3F9879F6190} | 152691107 | HIGGINS 1107 | 1070 | 39.0212 | -121.0599 | HIGGINS 11071070 | 167 | 138 | 21394.838 | 13372.1867 | 8022.6513 | 11964.8264 | 7396.5735 | 0.078275 | 0.010195 | 1.577 | 10.2213 | 625 | 1.4434 | 757 | 0 | 0 | 7.4346 | 524 | 0
North Coast | 6145 | 515 | 877.9064 | 1261 | 1284.1188 | 98 | 0.0001121 | 100.0179 | 3.5297 | 51.5798 | 186.2188 | 1.1931 | 2.8822 | 27.5058 | 1.0803 | 0.01181 | 0.00023541 | 0.40841 | 0.68366 | {47D11162-DBA1-4478-BDF3-B67846D21C32} | 42601102 | PHILO 1102 | circuit_breaker | 39.0641 | -123.4379 | PHILO 1102circuit_breaker | 216 | 196 | 43061.5326 | 20191.5402 | 22869.9923 | 10918.6301 | 8461.0097 | 0.023071 | 0.010985 | 1.7047 | 12.8673 | 1295 | 1.1574 | 758 | 0 | 0 | 6.7845 | 638 | 0
Bay Area | 6611 | 1020 | 2095.6109 | 1109 | 2145.4155 | 72 | 9.8668e-05 | 115.3346 | 0.71253 | 9.9527 | 40.8217 | 0.087192 | 0.52246 | 12.8361 | 1.0684 | 0.011732 | 8.7535e-05 | 0.91975 | 0.97679 | {3F2B4E81-3F76-4F92-B31C-17D1A0284314} | 24251101 | WOODSIDE 1101 | 47872 | 37.4182 | -122.3194 | WOODSIDE 110147872 | 110 | 120 | 13710.4609 | 7099.6124 | 6610.8485 | 7099.6124 | 6610.8485 | 0.0063025 | 0.0071041 | 2.0545 | 15.4028 | 1928 | 0.84471 | 759 | 0 | 0 | 4.4115 | 2636 | 0
North Valley | 4519 | 18 | 23.7664 | 36 | 31.2554 | 5 | 0.00010418 | 103.5627 | 30.6573 | 3327.6147 | 21863.9199 | 994.583 | 3.9513 | 642.8478 | 1.3146 | 0.011719 | 0.0019405 | 0.5 | 0.76039 | {BF1D640B-1AB6-49FB-AB3D-0A09BCB77224} | 102841106 | ANITA 1106 | 2418 | 39.822 | -121.923 | ANITA 11062418 | 201 | 182 | 58882.9555 | 39339.8369 | 19543.1186 | 185.0114 | 326.0208 | 0.0097026 | 0.00052088 | 1.3204 | 7.2 | 182 | 0.058595 | 760 | 0 | 0 | 0.11496 | 1867 | 0
North Coast | 3314 | 13 | 27.1716 | 40 | 37.7506 | 7 | 8.7136e-05 | 95.5143 | 53.9495 | 315.1002 | 1191.492 | 178.8398 | 5.4565 | 89.271 | 3.3322 | 0.011701 | 0.0024656 | 0.325 | 0.71977 | {B535D722-73FE-4291-8971-8A55B8A8D2FE} | 42271105 | COTATI 1105 | 734248 | 38.3039 | -122.7371 | COTATI 1105734248 | 11 | 38 | 2800.557 | 774.6582 | 2025.8988 | 774.6582 | 2025.8988 | 0.01726 | 0.00060995 | 2.0901 | 5.7143 | 129 | 0.081908 | 761 | 0 | 0 | 0.48135 | 877 | 0
Central Coast | 8082 | 24 | 55.394 | 99 | 99.7281 | 20 | 1.3609e-05 | 892.4606 | 8.1846 | 85.1286 | 404.022 | 12.6122 | 15.5265 | 342.582 | 1.2096 | 0.011695 | 5.827e-05 | 0.24242 | 0.55545 | {5E4CECE6-B405-46DF-AB3E-BC23B1171AD2} | 182631104 | SAN LUIS OBISPO 1104 | 350030 | 35.214 | -120.5914 | SAN LUIS OBISPO 1104350030 | 140 | 0 | 14694.3466 | 14694.3466 | 0 | 8366.5404 | 0 | 0.0011654 | 0.00027218 | 2.3081 | 4.95 | 2158 | 0.2339 | 762 | 0 | 0 | 5.1987 | 2492 | 0
Bay Area | 4425 | 49 | 106.1592 | 159 | 171.1952 | 14 | 5.9099e-05 | 192.9084 | 3.0459 | 41.8188 | 152.8325 | 1.895 | 7.693 | 137.9671 | 1.1613 | 0.011686 | 9.8609e-05 | 0.30818 | 0.62011 | {9A4542AE-EE8F-4BB7-BE2E-76002D6DCF25} | 14101105 | ALHAMBRA 1105 | 95016 | 37.967 | -122.1249 | ALHAMBRA 110595016 | 117 | 391 | 24011.4742 | 6423.8169 | 17587.6573 | 1054.2618 | 1681.7452 | 0.0013805 | 0.00082739 | 2.1665 | 11.3571 | 1857 | 0.16361 | 763 | 0 | 0 | 0.65509 | 2522 | 0
North Coast | 8343 | 271 | 324.7132 | 304 | 340.166 | 37 | 0.00027297 | 38.6121 | 4.3645 | 3233.3925 | 67086.8163 | 369.2174 | 0.086702 | 20.4005 | 1.0331 | 0.011624 | 0.00077389 | 0.89145 | 0.95457 | {91A00852-9832-43D1-A31D-4D51B95ED53F} | 192171101 | WILLOW CREEK 1101 | 3050 | 40.8857 | -123.7719 | WILLOW CREEK 11013050 | 24 | 12 | 4820.8119 | 4461.1677 | 359.6442 | 4461.1677 | 359.6442 | 0.028634 | 0.0101 | 1.1982 | 8.2162 | 517 | 0.43008 | 764 | 0 | 0 | 2.772 | 940 | 0
North Coast | 944 | 20 | 43.4116 | 87 | 61.0814 | 32 | 5.2245e-05 | 247.1142 | 1.103 | 0.98694 | 2.1781 | 0.029462 | 10.7616 | 56.9325 | 1.3401 | 0.011513 | 5.7337e-05 | 0.22989 | 0.71072 | {51EF8730-4C17-4517-B094-A50393B56842} | 43141102 | MIDDLETOWN 1102 | 514 | 38.807 | -122.5689 | MIDDLETOWN 1102514 | 112 | 597 | 43245.579 | 8514.884 | 34730.6949 | 5004.0934 | 19340.9831 | 0.0018348 | 0.0016718 | 2.1706 | 2.7188 | 2168 | 0.36842 | 765 | 0 | 0 | 3.1094 | 81 | 0
North Valley | 2683 | 722 | 1286.345 | 2271 | 1858.0728 | 294 | 5.8253e-05 | 261.3395 | 27.8183 | 190.26 | 2819.2756 | 543.7406 | 6.5699 | 75.6546 | 1.2789 | 0.011488 | 0.0008449 | 0.31792 | 0.6923 | {31065709-9564-4E9B-B7A7-65368041A59F} | 103521103 | OREGON TRAIL 1103 | 1500 | 40.6121 | -122.3836 | OREGON TRAIL 11031500 | 428 | 511 | 66362.7013 | 41519.6675 | 24843.0339 | 41462.2575 | 24843.0339 | 0.2484 | 0.017126 | 1.7816 | 7.7245 | 474 | 3.3774 | 766 | 0 | 0 | 25.7634 | 1539 | 0
North Coast | 7533 | 31 | 72.6396 | 90 | 108.4917 | 13 | 6.0399e-05 | 175.8355 | 0.91251 | 26.3737 | 83.4554 | 0.16335 | 4.5146 | 76.2589 | 1.2297 | 0.011465 | 5.7135e-05 | 0.34444 | 0.66954 | {EA9B2479-0C7B-4A59-82AF-47AD3E8F521E} | 42561102 | FULTON 1102 | 4994 | 38.5278 | -122.7651 | FULTON 11024994 | 80 | 68 | 12682.9096 | 6942.8858 | 5740.0238 | 1753.9056 | 1818.9799 | 0.00074275 | 0.00078518 | 2.3432 | 6.9231 | 2171 | 0.14905 | 767 | 0 | 0 | 1.0898 | 318 | 0
Central Coast | 2480 | 468 | 1487.9 | 1592 | 2150.4167 | 180 | 1.7803e-05 | 805.5082 | 32.8802 | 193.2557 | 1122.2298 | 101.0691 | 22.1938 | 112.5226 | 1.1575 | 0.011455 | 0.00028424 | 0.29397 | 0.69191 | {7C50129A-5CE2-426F-8AEE-1DAC2E3B9D18} | 182601104 | OCEANO 1104 | Q08 | 35.1481 | -120.5893 | OCEANO 1104Q08 | 236 | 269 | 35577.1662 | 19963.0067 | 15614.1595 | 19963.0067 | 15614.1595 | 0.051163 | 0.0032046 | 3.1793 | 8.8444 | 1161 | 2.0619 | 768 | 0 | 0 | 12.4044 | 2487 | 0
Sierra | 8821 | 361 | 389.4186 | 429 | 417.552 | 21 | 8.4738e-05 | 128.0673 | 226.0351 | 4099.0875 | 94802.9082 | 34580.2454 | 0.86884 | 47.1767 | 1.1716 | 0.011419 | 0.0098628 | 0.84149 | 0.93262 | {D5AE9DC8-C124-4C49-BB35-C0CDE45BC05E} | 152181102 | FORESTHILL 1102 | circuit_breaker | 39.0197 | -120.8298 | FORESTHILL 1102circuit_breaker | 23 | 6 | 3445.2613 | 2652.1639 | 793.0973 | 2652.1639 | 793.0973 | 0.20712 | 0.0017795 | 1.0787 | 20.4286 | 8 | 0.2398 | 769 | 0 | 0 | 1.648 | 2967 | 0
Bay Area | 1312 | 1854 | 3195.4486 | 3408 | 4077.0808 | 366 | 0.00012901 | 104.1145 | 2.9956 | 22.4037 | 251.1039 | 3.4785 | 1.1109 | 13.4151 | 1.0536 | 0.011375 | 0.00025289 | 0.54401 | 0.78376 | {13A712E3-B547-41AB-8639-0CAD4756D0FC} | 43432104 | SILVERADO 2104 | 37632 | 38.5349 | -122.4754 | SILVERADO 210437632 | 531 | 1126 | 104849.6578 | 42656.5483 | 62193.1095 | 42656.5483 | 62193.1095 | 0.092556 | 0.047216 | 1.7235 | 9.3115 | 1242 | 4.1631 | 770 | 0 | 0 | 26.5055 | 1570 | 0
Bay Area | 5238 | 633 | 948.0788 | 1214 | 1272.1979 | 98 | 0.00012397 | 85.9609 | 2.3078 | 29.1554 | 390.5735 | 5.9668 | 0.38496 | 8.8251 | 0.98162 | 0.01127 | 0.00019313 | 0.52142 | 0.74523 | {5A345DA5-99DA-441B-8BB7-B6EB811524C1} | 43432105 | SILVERADO 2105 | 616 | 38.5114 | -122.4765 | SILVERADO 2105616 | 395 | 359 | 52337.1897 | 29229.1132 | 23108.0765 | 11577.8412 | 11609.5905 | 0.018927 | 0.012149 | 1.4978 | 12.3878 | 1439 | 1.1045 | 771 | 0 | 0 | 7.1941 | 2758 | 0
Central Coast | 7740 | 41 | 50.0991 | 114 | 96.81 | 29 | 2.1546e-05 | 499.1589 | 0.52355 | 323.5507 | 1400.8719 | 2.9898 | 7.4268 | 1166.3629 | 1.5307 | 0.011243 | 1.4638e-05 | 0.35965 | 0.5175 | {84844AA6-33FE-4B77-BE7F-2142383F94DA} | 182681101 | ZACA 1101 | circuit_breaker | 34.697 | -120.1515 | ZACA 1101circuit_breaker | 83 | 49 | 20189.5727 | 17338.0564 | 2851.5163 | 11111.2282 | 733.0805 | 0.00042449 | 0.00062484 | 1.2219 | 3.931 | 2712 | 0.32604 | 772 | 0 | 0 | 6.9042 | 279 | 0
Central Valley | 482 | 48 | 72.3196 | 224 | 127.6117 | 55 | 3.3786e-05 | 176.0617 | 29.8348 | 2770.2849 | 18781.9445 | 1333.448 | 11.0717 | 1085.4295 | 1.7711 | 0.01124 | 0.00018279 | 0.21429 | 0.56672 | {B007F88B-9403-4642-A8D2-16BDDDACB785} | 252941107 | TIVY VALLEY 1107 | circuit_breaker | 36.7704 | -119.3932 | TIVY VALLEY 1107circuit_breaker | 384 | 292 | 86765.2136 | 68308.1954 | 18457.0183 | 19259.2253 | 4091.3705 | 0.010054 | 0.0018582 | 1.5067 | 4.0727 | 1474 | 0.61822 | 773 | 0 | 0 | 11.9671 | 456 | 0
North Valley | 4392 | 427 | 864.7921 | 1510 | 1198.8142 | 288 | 0.00010793 | 136.5247 | 20.6791 | 292.0364 | 3834.0335 | 543.1423 | 6.4992 | 55.7306 | 1.079 | 0.011211 | 0.0010343 | 0.28278 | 0.72137 | {AC347828-D402-4D52-85C5-6B49A3874218} | 103401101 | GIRVAN 1101 | 9732 | 40.5211 | -122.4785 | GIRVAN 11019732 | 434 | 288 | 50011.2491 | 33998.8263 | 16012.4228 | 33998.8263 | 16012.4228 | 0.29787 | 0.031085 | 2.0253 | 5.2431 | 393 | 3.2288 | 774 | 0 | 0 | 21.1259 | 2619 | 0
North Coast | 1700 | 428 | 647.0173 | 1472 | 1035.1954 | 136 | 0.00010593 | 87.8222 | 8.9303 | 154.9274 | 3589.6586 | 277.5349 | 2.9603 | 14.1713 | 1.0688 | 0.011178 | 0.0005499 | 0.29076 | 0.62502 | {7BCF996F-5D44-49DD-8430-629850EC151D} | 43351106 | LUCERNE 1106 | 664 | 39.021 | -122.7488 | LUCERNE 1106664 | 317 | 658 | 49857.3949 | 17950.7499 | 31906.645 | 15102.6309 | 25670.2895 | 0.074786 | 0.014407 | 1.5117 | 10.8235 | 738 | 1.5203 | 775 | 0 | 0 | 9.3843 | 934 | 0
Central Valley | 6583 | 22 | 53.1902 | 195 | 103.7945 | 66 | 3.3886e-05 | 336.6277 | 36.2173 | 9757.0414 | 84883.1249 | 4061.4784 | 13.1277 | 1436.5512 | 1.7786 | 0.011121 | 0.00062984 | 0.11282 | 0.51246 | {04B6E7EF-7D58-4AD6-8C95-F9DC0FD8A439} | 254432103 | COARSEGOLD 2103 | 6110 | 37.128 | -119.7352 | COARSEGOLD 21036110 | 211 | 169 | 59805.8956 | 47978.9803 | 11826.9153 | 16696.1653 | 7078.8169 | 0.041569 | 0.0022365 | 2.4177 | 2.9545 | 639 | 0.73399 | 776 | 0 | 0 | 10.3745 | 1507 | 0
North Coast | 1016 | 110 | 167.018 | 123 | 174.1472 | 27 | 0.00028518 | 41.4541 | 1.9594 | 199.2703 | 2274.8221 | 6.626 | 0.77098 | 27.014 | 1.065 | 0.011067 | 0.00044966 | 0.89431 | 0.95906 | {C08075C5-E7BA-4353-AF25-7A00C76C5CA3} | 192311142 | FRUITLAND 1142 | circuit_breaker | 40.286 | -123.8369 | FRUITLAND 1142circuit_breaker | 157 | 145 | 35281.744 | 24720.3786 | 10561.3653 | 16901.355 | 7393.593 | 0.012141 | 0.0076999 | 1.5183 | 4.5556 | 864 | 0.29881 | 777 | 0 | 0 | 10.502 | 1170 | 0
North Valley | 6521 | 34 | 70.5096 | 155 | 106.5899 | 37 | 8.8933e-05 | 132.5455 | 46.9845 | 224.7962 | 3046.5574 | 534.5477 | 4.6555 | 102.2354 | 1.1173 | 0.011058 | 0.002403 | 0.21935 | 0.6615 | {F2F9B8C7-DF20-4B0C-A519-3E0E16F2B19B} | 103451101 | KESWICK 1101 | 1590 | 40.6174 | -122.4621 | KESWICK 11011590 | 91 | 66 | 13553.2751 | 10135.4927 | 3417.7824 | 10135.4927 | 3417.7824 | 0.08891 | 0.0032905 | 2.0738 | 4.1892 | 137 | 0.40915 | 778 | 0 | 0 | 6.2979 | 1997 | 0
North Coast | 305 | 160 | 227.9445 | 248 | 263.7793 | 8 | 9.5792e-05 | 92.4828 | 0.21187 | 659.7188 | 11949.1299 | 5.5658 | 1.4212 | 65.6795 | 1.172 | 0.011031 | 8.0533e-05 | 0.64516 | 0.86415 | {A76B3C85-A928-4A11-8CC5-E0ACBE412C66} | 48011144 | CALPINE 1144 | circuit_breaker | 38.8153 | -122.8003 | CALPINE 1144circuit_breaker | 170 | 30 | 43565.052 | 42270.0145 | 1295.0375 | 42270.0145 | 1295.0375 | 0.00064426 | 0.00076633 | 1.4247 | 31 | 1978 | 0.088245 | 779 | 0 | 0 | 26.2654 | 1333 | 0
Central Coast | 1169 | 128 | 416.088 | 795 | 831.7814 | 108 | 1.8106e-05 | 659.9024 | 33.3559 | 183.1297 | 943.1779 | 67.6054 | 18.0267 | 184.8561 | 1.2227 | 0.011021 | 0.00033349 | 0.16101 | 0.50024 | {612579F3-BEE6-43F6-ABF9-9C9C3F31A5CF} | 182601104 | OCEANO 1104 | V36 | 35.145 | -120.53 | OCEANO 1104V36 | 234 | 272 | 39866.8172 | 21377.0626 | 18489.7546 | 15485.8164 | 12119.5095 | 0.036017 | 0.0019554 | 3.2507 | 7.3611 | 1048 | 1.1903 | 780 | 0 | 0 | 9.6224 | 1902 | 0
Bay Area | 700 | 396 | 533.9856 | 582 | 630.5869 | 42 | 9.3766e-05 | 103.6882 | 6.6937 | 117.2916 | 1944.4823 | 28.1935 | 0.11218 | 12.7993 | 1.1293 | 0.010992 | 0.00042659 | 0.68041 | 0.84681 | {1ED35AB0-76EC-4B55-BA7D-30E8BB237D98} | 43432105 | SILVERADO 2105 | 1306 | 38.5099 | -122.4785 | SILVERADO 21051306 | 192 | 156 | 24673.8774 | 12596.1937 | 12077.6838 | 4731.2419 | 4374.1876 | 0.017917 | 0.0039382 | 1.3484 | 13.8571 | 900 | 0.46168 | 781 | 0 | 0 | 2.9399 | 1965 | 0
North Coast | 7578 | 510 | 665.3973 | 671 | 731.3388 | 167 | 6.1455e-05 | 176.9461 | 12.9652 | 742.3943 | 8486.3906 | 265.2313 | 3.3778 | 180.4221 | 1.051 | 0.010971 | 0.00029813 | 0.76006 | 0.90983 | {8550FAE9-8660-4D0D-A46A-9FC5A8080BAF} | 42251101 | HOPLAND 1101 | 94006 | 39.044 | -123.1536 | HOPLAND 110194006 | 126 | 119 | 39908.712 | 24484.3021 | 15424.4099 | 18955.1203 | 13190.4317 | 0.049788 | 0.010263 | 1.3047 | 4.018 | 1129 | 1.8322 | 782 | 0 | 0 | 11.7782 | 2239 | 0
North Coast | 8710 | 10 | 9.7408 | 81 | 41.2186 | 5 | 6.5074e-05 | 173.0616 | 1.2278 | 1796.7138 | 31719.7854 | 130.5907 | 7.4301 | 250.13 | 1.9243 | 0.01096 | 4.0968e-05 | 0.12346 | 0.23632 | {8DC366D2-489B-4862-83DA-61BC167BAFAF} | 48011146 | CALPINE 1146 | circuit_breaker | 38.815 | -122.8021 | CALPINE 1146circuit_breaker | 37 | 4 | 5016.6421 | 4947.493 | 69.1491 | 4947.493 | 69.1491 | 0.00020484 | 0.00032537 | 0.97408 | 16.2 | 2328 | 0.054802 | 783 | 0 | 0 | 3.0742 | 1462 | 0
North Coast | 1520 | 3386 | 5495.8367 | 4015 | 5820.065 | 404 | 0.00014615 | 69.1134 | 9.3786 | 156.7228 | 1593.1097 | 85.6649 | 1.4003 | 36.0893 | 1.1256 | 0.010955 | 0.00075006 | 0.84334 | 0.94429 | {75E7E1B3-D461-49A0-A0AB-E84CDEE528DF} | 42661103 | WILLITS 1103 | 91810 | 39.4456 | -123.3807 | WILLITS 110391810 | 478 | 648 | 88704.1689 | 47349.2019 | 41354.967 | 47349.2019 | 41354.967 | 0.30302 | 0.059046 | 1.6231 | 9.9381 | 533 | 4.4256 | 784 | 0 | 0 | 29.4214 | 1974 | 0
Bay Area | 4400 | 36 | 81.094 | 72 | 97.5005 | 13 | 2.5034e-05 | 604.7195 | 0 | 0.1112 | 0.0009448 | 0 | 10.5793 | 522.7547 | 1.1537 | 0.010916 | 2.1259e-05 | 0.5 | 0.83173 | {8551839C-1867-4078-846B-9A7378D90E53} | 14652106 | TIDEWATER 2106 | 65866 | 38.0106 | -122.0041 | TIDEWATER 210665866 | 192 | 309 | 29277.6611 | 14341.466 | 14936.1951 | 2331.7066 | 1562.7128 | 0.00027637 | 0.00032544 | 2.2526 | 5.5385 | 2582 | 0.14191 | 785 | 0 | 0 | 1.4489 | 2231 | 0
Central Coast | 3824 | 225 | 365.6786 | 532 | 551.6329 | 60 | 5.8251e-05 | 227.156 | 2.7013 | 19.9072 | 54.2764 | 0.2974 | 6.9183 | 41.4788 | 1.1311 | 0.010857 | 0.00011688 | 0.42293 | 0.6629 | {53582C8A-D41B-4282-A67B-535B2AA3B79C} | 83182107 | LLAGAS 2107 | 40407 | 37.0136 | -121.6512 | LLAGAS 210740407 | 111 | 108 | 19742.8739 | 10022.7174 | 9720.1566 | 6648.3182 | 4870.8096 | 0.0070125 | 0.003495 | 1.6252 | 8.8667 | 1763 | 0.65143 | 786 | 0 | 0 | 4.1311 | 2649 | 0
Bay Area | 5769 | 409 | 835.0724 | 681 | 958.9207 | 90 | 3.3375e-05 | 389.1026 | 0.89384 | 286.4999 | 3741.9476 | 36.6701 | 1.1298 | 343.5014 | 1.5548 | 0.010819 | 3.5096e-05 | 0.60059 | 0.87085 | {BF770A1D-B814-4B5E-BA39-314F43484812} | 43051101 | MONTICELLO 1101 | 630 | 38.5733 | -122.2442 | MONTICELLO 1101630 | 130 | 179 | 47418.0808 | 31569.6011 | 15848.4797 | 28630.1876 | 15032.0459 | 0.0031586 | 0.0030037 | 2.0417 | 7.5667 | 2397 | 0.97368 | 787 | 0 | 0 | 17.79 | 2560 | 0
Sierra | 1062 | 659 | 973.5662 | 1980 | 1512.0219 | 185 | 7.9704e-05 | 168.0651 | 12.1646 | 65.9308 | 379.6921 | 11.1836 | 7.2076 | 58.7728 | 1.1466 | 0.010817 | 0.00053043 | 0.33283 | 0.64388 | {E0134993-C6C7-47B2-B903-8846B3C865A5} | 152461103 | PLACER 1103 | circuit_breaker | 38.9009 | -121.088 | PLACER 1103circuit_breaker | 728 | 1433 | 116038.4223 | 47113.7621 | 68924.6602 | 20608.1987 | 15725.6193 | 0.09813 | 0.014745 | 1.4773 | 10.7027 | 758 | 2.0012 | 788 | 0 | 0 | 12.8053 | 362 | 0
North Valley | 6595 | 966 | 1718.8136 | 1384 | 1849.9236 | 227 | 8.2623e-05 | 131.5708 | 7.4109 | 614.2949 | 4093.259 | 62.2698 | 9.3889 | 251.1952 | 1.2468 | 0.010657 | 0.00036834 | 0.69798 | 0.92913 | {1A40C8BC-051A-4DE6-8C9D-412DD5FF54A2} | 103351101 | DESCHUTES 1101 | 1654 | 40.5019 | -122.0408 | DESCHUTES 11011654 | 215 | 219 | 44717.8899 | 28373.2901 | 16344.5999 | 28373.2901 | 16344.5999 | 0.083614 | 0.018755 | 1.7793 | 6.0969 | 986 | 2.4192 | 789 | 0 | 0 | 17.6303 | 1549 | 0
Bay Area | 4156 | 13 | 28.0344 | 24 | 33.4417 | 8 | 2.9985e-05 | 273.51 | 0.1193 | 0.11919 | 0.0020019 | 4.856e-07 | 2.2862 | 8.79 | 1.0799 | 0.01065 | 1.762e-05 | 0.54167 | 0.83831 | {7112559E-7269-4FF3-BE61-B0339A94698E} | 42991104 | LAS GALLINAS A 1104 | 304 | 38.0027 | -122.5527 | LAS GALLINAS A 1104304 | 62 | 395 | 24459.4041 | 4019.6637 | 20439.7405 | 683.5311 | 2786.884 | 0.00014096 | 0.00023988 | 2.1565 | 3 | 2655 | 0.085197 | 790 | 0 | 0 | 0.42473 | 2888 | 0
Bay Area | 932 | 0 | 0 | 6 | 2.9585 | 3 | 1.1312e-05 | 810.434 | 27.4729 | 18.5334 | 33.8173 | 2.1362 | 25.7013 | 290.6131 | 1.087 | 0.010641 | 0.00018206 | 0 | 0 | {F271313B-5D1D-49E6-80E5-E9B726A3CF7F} | 13501108 | JARVIS 1108 | MR576 | 37.6164 | -122.0319 | JARVIS 1108MR576 | 164 | 1194 | 58020.8958 | 9799.7281 | 48221.1677 | 434.201 | 1872.35 | 0.00054619 | 3.3937e-05 |  | 2 | 1478 | 0.031924 | 791 | 0 | 0 | 0.2698 | 1723 | 0
Central Coast | 8849 | 15 | 22.3996 | 57 | 48.1699 | 9 | 4.9665e-05 | 402.0344 | 6.0761 | 107.087 | 281.7205 | 2.8031 | 15.5639 | 121.1439 | 1.1003 | 0.010637 | 0.00014023 | 0.26316 | 0.46501 | {90264C2C-3ED3-42D6-BFF5-F41E927FBBE3} | 83182105 | LLAGAS 2105 | XR234 | 36.9919 | -121.5618 | LLAGAS 2105XR234 | 51 | 25 | 6040.3678 | 3448.7535 | 2591.6143 | 1152.082 | 171.2646 | 0.0012621 | 0.00044698 | 1.4933 | 6.3333 | 1631 | 0.09573 | 792 | 0 | 0 | 0.71587 | 1738 | 0
North Coast | 1493 | 1458 | 2384.4623 | 1876 | 2575.5854 | 187 | 0.00017051 | 70.9879 | 0.47194 | 74.4901 | 554.6964 | 0.2036 | 0.26797 | 13.4127 | 1.1161 | 0.010631 | 0.0001267 | 0.77719 | 0.92579 | {A72343AE-8C2E-4D3F-9541-799C96B3BB35} | 192251102 | RIO DELL 1102 | 1504 | 40.4538 | -124.0477 | RIO DELL 11021504 | 86 | 106 | 22115.6549 | 19231.7001 | 2883.9548 | 17338.0675 | 2092.1149 | 0.023693 | 0.031886 | 1.6354 | 10.0321 | 1712 | 1.988 | 793 | 0 | 0 | 10.7734 | 178 | 0
North Valley | 6351 | 740 | 1221.5419 | 1827 | 1720.4604 | 180 | 0.0001234 | 76.6874 | 172.1331 | 4420.8482 | 82132.6081 | 19181.2863 | 1.1973 | 35.1722 | 1.1522 | 0.010613 | 0.010937 | 0.40504 | 0.71001 | {C9F32A9F-4742-4955-A09A-5F71A664491E} | 103221101 | KANAKA 1101 | 75744 | 39.4965 | -121.3223 | KANAKA 110175744 | 121 | 88 | 24423.4394 | 17040.8886 | 7382.5508 | 17040.8886 | 7382.5508 | 1.9687 | 0.022212 | 1.6507 | 10.15 | 5 | 1.9104 | 794 | 0 | 0 | 10.5887 | 1130 | 0
North Valley | 102 | 393 | 891.3303 | 1106 | 1148.8978 | 165 | 6.481e-05 | 186.5366 | 8.0333 | 53.8343 | 337.116 | 9.3825 | 9.6726 | 62.8804 | 1.1597 | 0.0106 | 0.00019176 | 0.35533 | 0.77581 | {652E0C25-B4E5-4F56-A678-A27ED9716769} | 102911110 | WYANDOTTE 1110 | 1954 | 39.4985 | -121.5285 | WYANDOTTE 11101954 | 658 | 984 | 90596.8345 | 43471.4021 | 47125.4324 | 19698.3887 | 12153.243 | 0.031641 | 0.010694 | 2.268 | 6.703 | 1444 | 1.749 | 795 | 0 | 0 | 12.24 | 1222 | 0
North Coast | 2790 | 1264 | 1767.8544 | 1714 | 1998.9769 | 206 | 0.00015632 | 65.6448 | 32.9488 | 3327.1796 | 65999.844 | 3799.0749 | 1.4339 | 84.5998 | 1.2058 | 0.010566 | 0.0022952 | 0.73746 | 0.88438 | {EF680142-96BC-4632-8839-A0A3D923AC61} | 42951101 | MENDOCINO 1101 | 48750 | 39.3315 | -123.2248 | MENDOCINO 110148750 | 198 | 175 | 47335.8824 | 28628.3227 | 18707.5597 | 28628.3227 | 18707.5597 | 0.4728 | 0.032203 | 1.3986 | 8.3204 | 153 | 2.1767 | 796 | 0 | 0 | 17.7888 | 838 | 0
Central Valley | 6262 | 401 | 531.3001 | 908 | 742.8149 | 180 | 2.3778e-05 | 425.0355 | 30.1306 | 1923.9174 | 18120.8783 | 886.9629 | 15.634 | 690.9193 | 1.6616 | 0.010507 | 0.00033257 | 0.44163 | 0.71525 | {DC0C9AE9-E0EC-4108-AF9E-4DDFE694FC71} | 254061102 | DUNLAP 1102 | 7060 | 36.6878 | -119.0223 | DUNLAP 11027060 | 201 | 214 | 46155.7833 | 28682.1944 | 17473.5889 | 28682.1944 | 17473.5889 | 0.059863 | 0.0042801 | 1.3249 | 5.0444 | 1049 | 1.8912 | 797 | 0 | 0 | 17.8223 | 1120 | 0
North Valley | 4628 | 89 | 138.5822 | 204 | 182.117 | 20 | 8.7707e-05 | 117.8314 | 26.9138 | 53.7553 | 208.3188 | 11.9514 | 11.7618 | 48.1311 | 1.0887 | 0.010499 | 0.00078259 | 0.43627 | 0.76095 | {0E127264-C3E4-4550-BC79-8854D7BB9B29} | 102911107 | WYANDOTTE 1107 | circuit_breaker | 39.4916 | -121.5411 | WYANDOTTE 1107circuit_breaker | 394 | 867 | 69452.217 | 24344.0332 | 45108.1838 | 1641.1081 | 2586.7106 | 0.015652 | 0.0017541 | 1.5571 | 10.2 | 509 | 0.20999 | 798 | 0 | 0 | 1.0197 | 256 | 0
North Coast | 6357 | 462 | 768.254 | 790 | 859.6285 | 160 | 6.3359e-05 | 177.9385 | 5.182 | 420.719 | 2125.2663 | 18.677 | 8.9802 | 425.6158 | 1.4351 | 0.010423 | 0.00019734 | 0.58481 | 0.8937 | {ADF7CDB1-D7EE-4238-AD1F-3FDE0907FF69} | 43361103 | HIGHLANDS 1103 | 1282 | 38.8802 | -122.6125 | HIGHLANDS 11031282 | 218 | 251 | 52001.2191 | 26925.5772 | 25075.6419 | 23288.0926 | 20569.3659 | 0.031575 | 0.010137 | 1.6629 | 4.9375 | 1423 | 1.6676 | 799 | 0 | 0 | 14.4705 | 2481 | 0
Central Valley | 9085 | 25 | 42.8863 | 179 | 102.604 | 58 | 3.9756e-05 | 176.654 | 0.48109 | 129.9274 | 752.1857 | 1.0062 | 2.039 | 498.9572 | 1.642 | 0.01041 | 2.8542e-05 | 0.13966 | 0.41798 | {F4E4D8BC-9659-4439-88C6-265319222D40} | 251511101 | WISHON 1101 | circuit_breaker | 37.1509 | -119.5046 | WISHON 1101circuit_breaker | 46 | 23 | 14779.2774 | 12397.8907 | 2381.3867 | 12397.8907 | 2381.3867 | 0.0016554 | 0.0023059 | 1.7155 | 3.0862 | 2485 | 0.60376 | 800 | 0 | 0 | 7.7037 | 1063 | 0
North Coast | 1932 | 2142 | 3774.26 | 3120 | 4246.6714 | 223 | 0.0003447 | 30.0179 | 0.96522 | 76.4918 | 722.6871 | 1.9227 | 0.47605 | 15.5413 | 1.0491 | 0.010397 | 0.00033934 | 0.68654 | 0.88876 | {7F9C85EF-487B-454C-8489-CDBA87D32E67} | 192221101 | GARBERVILLE 1101 | 1514 | 40.0477 | -123.7896 | GARBERVILLE 11011514 | 166 | 131 | 28532.833 | 23737.6018 | 4795.2313 | 23737.6018 | 4795.2313 | 0.075673 | 0.076868 | 1.762 | 13.991 | 1031 | 2.3186 | 801 | 0 | 0 | 14.7499 | 885 | 0
North Coast | 915 | 1693 | 2057.459 | 2885 | 2677.6636 | 239 | 0.00013899 | 116.9348 | 10.8962 | 79.8747 | 224.9829 | 2.7748 | 4.592 | 138.2539 | 1.0705 | 0.010369 | 0.00083568 | 0.58683 | 0.76838 | {D90B87B5-4140-4452-85E8-38B08B9DC56F} | 43141101 | MIDDLETOWN 1101 | 548 | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | 396 | 880 | 81764.7701 | 39630.2884 | 42134.4816 | 36627.2391 | 41510.3442 | 0.19973 | 0.033218 | 1.2153 | 12.0711 | 483 | 2.4782 | 802 | 0 | 0 | 22.7591 | 1215 | 0
North Coast | 6402 | 687 | 892.3038 | 1261 | 1230.524 | 132 | 0.00014924 | 71.5204 | 62.1056 | 2994.9135 | 53729.5601 | 3177.6196 | 1.3355 | 90.3074 | 1.1733 | 0.010226 | 0.0053044 | 0.54481 | 0.72514 | {0BF8011B-9B4A-4DA0-A70F-0F3D2BC39AD4} | 43141101 | MIDDLETOWN 1101 | 1325 | 38.876 | -122.7753 | MIDDLETOWN 11011325 | 103 | 114 | 23907.6947 | 13821.691 | 10086.0037 | 13821.691 | 10086.0037 | 0.70017 | 0.019699 | 1.2988 | 9.553 | 33 | 1.3499 | 803 | 0 | 0 | 8.5884 | 1194 | 0
North Coast | 7267 | 60 | 77.4886 | 88 | 95.9555 | 9 | 0.00012037 | 92.602 | 42.0413 | 105.598 | 619.872 | 49.5182 | 0.53392 | 8.3858 | 0.80383 | 0.010172 | 0.00083613 | 0.68182 | 0.80755 | {3704160C-56F4-464C-949D-B0353C9BFECB} | 42721106 | SONOMA 1106 | 376 | 38.2952 | -122.4677 | SONOMA 1106376 | 169 | 587 | 37828.2658 | 8667.3641 | 29160.9017 | 1147.4391 | 1012.4437 | 0.0075252 | 0.0010833 | 1.2915 | 9.7778 | 481 | 0.091552 | 804 | 0 | 0 | 0.71299 | 979 | 0
North Valley | 1496 | 1332 | 1916.9897 | 3287 | 2817.4045 | 374 | 0.00011968 | 92.3526 | 48.3196 | 1513.431 | 26467.2876 | 3059.8256 | 2.4174 | 41.4587 | 1.0795 | 0.010158 | 0.0021746 | 0.40523 | 0.68041 | {9343C558-C255-4E56-87AF-7724333414B9} | 103201102 | CHALLENGE 1102 | 5462 | 39.4829 | -121.2465 | CHALLENGE 11025462 | 401 | 477 | 69529.0172 | 37568.0951 | 31960.9221 | 37568.0951 | 31960.9221 | 0.81331 | 0.044759 | 1.4392 | 8.7888 | 162 | 3.7989 | 805 | 0 | 0 | 23.3437 | 2242 | 0
North Coast | 7787 | 802 | 1507.3717 | 882 | 1542.093 | 108 | 9.5206e-05 | 104.6234 | 0.11684 | 109.9509 | 1083.2571 | 0.26142 | 0.1081 | 19.8552 | 1.0608 | 0.010079 | 4.7659e-05 | 0.9093 | 0.97748 | {E7486DD4-0A7D-467A-B7E3-9401480FC5B2} | 192221101 | GARBERVILLE 1101 | 2026 | 39.8515 | -123.7182 | GARBERVILLE 11012026 | 29 | 27 | 11495.2611 | 10220.4249 | 1274.8362 | 10220.4249 | 1274.8362 | 0.0051472 | 0.010282 | 1.8795 | 8.1667 | 2252 | 1.0885 | 806 | 0 | 0 | 6.3507 | 2327 | 0
North Coast | 9044 | 49 | 84.6024 | 189 | 164.7804 | 24 | 5.2761e-05 | 200.3346 | 2.8994 | 73.0073 | 407.5452 | 3.12 | 5.6376 | 134.6855 | 1.1444 | 0.01002 | 8.9444e-05 | 0.25926 | 0.51343 | {CF3D4281-EA2F-4415-B4CD-AC674F9B4864} | 43501103 |  | 171410 | 38.5687 | -122.7991 | 171410 | 47 | 35 | 10940.4528 | 7764.5032 | 3175.9497 | 2859.7024 | 607.8964 | 0.0021467 | 0.0012663 | 1.7266 | 7.875 | 1912 | 0.24049 | 807 | 0 | 0 | 1.7769 | 1093 | 0
North Valley | 5770 | 5 | 5.9197 | 16 | 10.7458 | 4 | 5.259e-05 | 198.6823 | 30.4417 | 1774.191 | 11996.8389 | 365.1647 | 3.4635 | 406.4018 | 1.2196 | 0.0099935 | 0.00032933 | 0.3125 | 0.55089 | {4C7176B3-82BB-4EC7-9074-E6E03166E224} | 102041104 | NOTRE DAME 1104 | circuit_breaker | 39.7301 | -121.7961 | NOTRE DAME 1104circuit_breaker | 158 | 83 | 15272.1384 | 11050.043 | 4222.0954 | 1372.1379 | 32.3225 | 0.0013173 | 0.00021036 | 1.1839 | 4 | 1057 | 0.039974 | 808 | 0 | 0 | 0.85261 | 2709 | 0
Central Coast | 1921 | 361 | 1031.311 | 1004 | 1430.4492 | 123 | 1.6167e-05 | 647.5595 | 73.5254 | 217.1701 | 1063.8346 | 126.1869 | 15.6417 | 121.59 | 1.1102 | 0.009981 | 8.4379e-05 | 0.35956 | 0.72097 | {C0ABDB73-42C4-4D60-9BB1-4077EF0BE355} | 182821103 | MESA 1103 | M72 | 35.0398 | -120.5225 | MESA 1103M72 | 516 | 455 | 64760.9658 | 40398.8978 | 24362.068 | 14559.7479 | 7469.5999 | 0.010379 | 0.0019885 | 2.8568 | 8.1626 | 1957 | 1.2277 | 809 | 0 | 0 | 9.047 | 223 | 0
North Coast | 5242 | 572 | 824.407 | 1867 | 1566.7716 | 171 | 0.00010992 | 73.4308 | 22.5841 | 824.5042 | 7442.377 | 601.6469 | 2.5099 | 33.5386 | 1.0221 | 0.0098919 | 0.0014851 | 0.30637 | 0.52618 | {8D2AE911-21EF-4120-9FA6-1DB73A9C79A1} | 43071102 | DUNBAR 1102 | 261774 | 38.3787 | -122.5531 | DUNBAR 1102261774 | 205 | 179 | 31981.2424 | 21759.8537 | 10221.3888 | 21759.8537 | 10221.3888 | 0.25395 | 0.018796 | 1.4413 | 10.9181 | 248 | 1.6915 | 810 | 0 | 0 | 13.5209 | 944 | 0
Central Valley | 8943 | 10 | 18.0152 | 52 | 31.6181 | 17 | 5.402e-05 | 223.0782 | 3.0225 | 57.2516 | 188.8367 | 1.5242 | 7.6788 | 344.922 | 1.4473 | 0.0098895 | 6.7092e-05 | 0.19231 | 0.56978 | {0FF7F9F0-B4F2-4330-AF41-9981039A3994} | 163341103 | CLAY 1103 | 1821 | 38.302 | -120.8981 | CLAY 11031821 | 42 | 28 | 12275.9017 | 6061.921 | 6213.9807 | 4972.0887 | 5395.9406 | 0.0011406 | 0.00091835 | 1.8015 | 3.0588 | 2077 | 0.16812 | 811 | 0 | 0 | 3.0895 | 1707 | 0
Central Valley | 3918 | 665 | 1008.9243 | 1953 | 1478.018 | 206 | 7.9361e-05 | 131.4282 | 10.9069 | 52.6183 | 306.2663 | 20.4613 | 5.2725 | 40.7944 | 1.0989 | 0.0098439 | 0.0004859 | 0.3405 | 0.68262 | {6CFF4874-9416-4562-8168-A66869F04B91} | 163351704 | CURTIS 1704 | circuit_breaker | 37.9745 | -120.3203 | CURTIS 1704circuit_breaker | 295 | 408 | 50888.8195 | 22861.2714 | 28027.5481 | 22095.5217 | 25890.7597 | 0.1001 | 0.016348 | 1.5172 | 9.4806 | 801 | 2.0278 | 812 | 0 | 0 | 13.7295 | 1453 | 0
North Valley | 7755 | 118 | 170.1749 | 319 | 267.7126 | 79 | 0.00012112 | 111.5814 | 17.1261 | 1166.1845 | 26304.3445 | 1391.2386 | 0.18979 | 73.4337 | 1.1236 | 0.0098226 | 0.00067014 | 0.36991 | 0.63566 | {E337A679-257A-4862-A121-8FE4E1C11ADC} | 103451101 | KESWICK 1101 | 1588 | 40.617 | -122.496 | KESWICK 11011588 | 41 | 37 | 14930.2445 | 14089.0434 | 841.2012 | 14089.0434 | 841.2012 | 0.052941 | 0.0095683 | 1.4422 | 4.038 | 595 | 0.77598 | 813 | 0 | 0 | 8.7545 | 683 | 0
North Coast | 727 | 72 | 178.7377 | 109 | 197.8201 | 29 | 7.5572e-05 | 125.1761 | 31.9109 | 364.4986 | 1821.3854 | 232.4789 | 8.9246 | 84.9984 | 1.8742 | 0.009728 | 0.0017937 | 0.66055 | 0.90354 | {03190DAD-5324-4E1C-86DE-04D88D55A9A0} | 42271105 | COTATI 1105 | circuit_breaker | 38.3096 | -122.7319 | COTATI 1105circuit_breaker | 68 | 130 | 11951.9544 | 4287.6063 | 7664.3481 | 4287.6063 | 7664.3481 | 0.052019 | 0.0021916 | 2.4825 | 3.7586 | 197 | 0.28211 | 814 | 0 | 0 | 2.6642 | 509 | 0
Bay Area | 4072 | 209 | 334.8369 | 465 | 446.3944 | 88 | 5.3242e-05 | 162.9247 | 2.5229 | 352.4697 | 3749.2168 | 28.4621 | 2.1098 | 145.4908 | 1.2802 | 0.0097183 | 9.0253e-05 | 0.44946 | 0.75009 | {77EAEB31-2A5F-4667-AEF2-E5A85CE88B8F} | 43051101 | MONTICELLO 1101 | 666 | 38.51 | -122.2128 | MONTICELLO 1101666 | 126 | 83 | 30370.8337 | 22466.5413 | 7904.2923 | 16769.5218 | 6275.5814 | 0.0079423 | 0.0046853 | 1.6021 | 5.2841 | 1907 | 0.85521 | 815 | 0 | 0 | 10.4201 | 2559 | 0
Central Valley | 8245 | 12 | 22.6225 | 99 | 58.3795 | 25 | 2.2576e-05 | 462.3299 | 45.5726 | 1597.3636 | 15360.1429 | 2291.7812 | 8.7151 | 516.5747 | 1.667 | 0.0096857 | 0.000613 | 0.12121 | 0.38751 | {88F7D35A-B742-45DC-AA55-32394737AD92} | 252561101 | KERCKHOFF 1101 | R308 | 37.0988 | -119.5187 | KERCKHOFF 1101R308 | 33 | 20 | 7792.7166 | 6217.3701 | 1575.3465 | 6217.3701 | 1575.3465 | 0.015325 | 0.00056439 | 1.8852 | 3.96 | 658 | 0.24214 | 816 | 0 | 0 | 3.8633 | 2659 | 0
Bay Area | 5206 | 94 | 150.5469 | 233 | 198.8353 | 43 | 4.2517e-05 | 217.6514 | 1.6044 | 224.925 | 2076.378 | 9.2289 | 7.3794 | 232.8024 | 1.3968 | 0.0095951 | 4.8293e-05 | 0.40343 | 0.75714 | {9EBC498A-4473-4FB2-A278-0770D844069B} | 43051101 | MONTICELLO 1101 | 37384 | 38.4453 | -122.1966 | MONTICELLO 110137384 | 93 | 60 | 22917.2341 | 15055.0544 | 7862.1797 | 15055.0544 | 7862.1797 | 0.0020766 | 0.0018282 | 1.6016 | 5.4186 | 2245 | 0.41259 | 817 | 0 | 0 | 9.3548 | 1991 | 0
Central Valley | 876 | 827 | 1142.362 | 1758 | 1553.7542 | 239 | 3.7104e-05 | 228.2007 | 7.9161 | 143.4698 | 1364.4798 | 26.8764 | 4.5264 | 160.6817 | 1.3086 | 0.0095641 | 0.00014718 | 0.47042 | 0.73523 | {4272B914-DD96-40AD-9866-404625A4A67D} | 254452101 | MARIPOSA 2101 | 10240 | 37.5245 | -119.9173 | MARIPOSA 210110240 | 237 | 315 | 55285.3492 | 34426.9078 | 20858.4414 | 34426.9078 | 20858.4414 | 0.035176 | 0.008868 | 1.3813 | 7.3556 | 1608 | 2.2858 | 818 | 0 | 0 | 21.3919 | 496 | 0
Central Coast | 5657 | 1 | 3.8162 | 63 | 32.2958 | 5 | 8.6879e-06 | 1221.5357 | 42.3259 | 686.1359 | 2835.6089 | 120.0364 | 19.7381 | 1018.5477 | 1.6814 | 0.0095603 | 6.0541e-05 | 0.015873 | 0.11816 | {68BC2399-53D6-47DA-8B41-03AA4D509643} | 182821101 | MESA 1101 | 6113 | 35.0529 | -120.4864 | MESA 11016113 | 117 | 121 | 24317.9725 | 15635.2421 | 8682.7304 | 1783.5868 | 1804.2141 | 0.0003027 | 4.3439e-05 | 3.8162 | 12.6 | 2133 | 0.047802 | 819 | 0 | 0 | 1.1083 | 1617 | 0
Sierra | 1212 | 439 | 803.5123 | 1266 | 1136.2855 | 234 | 5.9699e-05 | 166.16 | 4.1322 | 177.2292 | 1119.0274 | 12.7154 | 7.3132 | 138.2032 | 1.3147 | 0.0095256 | 0.00013123 | 0.34676 | 0.70714 | {30B38EC8-F2E7-47AF-8BC7-D7EB75673131} | 153132102 | NARROWS 2102 | circuit_breaker | 39.2351 | -121.2689 | NARROWS 2102circuit_breaker | 396 | 298 | 60558.8238 | 39334.1146 | 21224.7092 | 36006.3008 | 19638.068 | 0.030709 | 0.01397 | 1.8303 | 5.4103 | 1696 | 2.229 | 820 | 0 | 0 | 22.3733 | 238 | 0
North Coast | 4055 | 281 | 363.0959 | 378 | 410.5291 | 63 | 0.0001268 | 83.3713 | 32.7551 | 2772.7901 | 64013.1968 | 3853.9865 | 3.7426 | 135.7697 | 1.3878 | 0.0094734 | 0.0019473 | 0.74339 | 0.88446 | {0092EF79-68EA-4B6C-8B69-750DA296468A} | 42661103 | WILLITS 1103 | 538 | 39.4236 | -123.3017 | WILLITS 1103538 | 56 | 48 | 15130.1623 | 10337.071 | 4793.0913 | 10337.071 | 4793.0913 | 0.12268 | 0.0079882 | 1.2922 | 6 | 180 | 0.59683 | 821 | 0 | 0 | 6.4232 | 2528 | 0
North Coast | 5091 | 2530 | 3804.3543 | 2859 | 3964.4104 | 288 | 0.00015238 | 67.215 | 6.2496 | 260.0471 | 2468.7758 | 31.5548 | 0.78666 | 40.3847 | 1.0843 | 0.0094647 | 0.00052271 | 0.88492 | 0.95963 | {A1E50B4A-662D-4B26-9A77-844EAB929468} | 42661104 | WILLITS 1104 | 504 | 39.4048 | -123.3854 | WILLITS 1104504 | 321 | 372 | 55554.793 | 36161.7196 | 19393.0733 | 36161.7196 | 19393.0733 | 0.15054 | 0.043886 | 1.5037 | 9.9271 | 769 | 2.7258 | 822 | 0 | 0 | 22.4698 | 1067 | 0
North Valley | 5679 | 729 | 943.4236 | 1672 | 1354.6721 | 186 | 7.0489e-05 | 133.0225 | 33.6437 | 2360.9358 | 67553.2885 | 5594.7511 | 0.5069 | 14.5362 | 1.0479 | 0.0094328 | 0.0011929 | 0.436 | 0.69642 | {7527FF71-24F2-49E2-97D3-F63D8D86A42D} | 103201101 | CHALLENGE 1101 | 5460 | 39.5444 | -121.1478 | CHALLENGE 11015460 | 126 | 117 | 24812.0744 | 19026.207 | 5785.8674 | 19026.207 | 5785.8674 | 0.22188 | 0.013111 | 1.2941 | 8.9892 | 324 | 1.7545 | 823 | 0 | 0 | 11.8223 | 2564 | 0
North Valley | 9108 | 139 | 222.9187 | 373 | 339.68 | 74 | 0.00010381 | 99.4074 | 65.1605 | 3711.3502 | 78387.9953 | 7258.4785 | 1.5632 | 52.9134 | 1.1301 | 0.0094145 | 0.002845 | 0.37265 | 0.65626 | {0C0686BD-4FFD-40DF-98D5-F53EB4C7C859} | 103221101 | KANAKA 1101 | circuit_breaker | 39.5752 | -121.3056 | KANAKA 1101circuit_breaker | 63 | 25 | 9321.2728 | 7526.6787 | 1794.594 | 7526.6787 | 1794.594 | 0.21053 | 0.0076822 | 1.6037 | 5.0405 | 111 | 0.69667 | 824 | 0 | 0 | 4.6769 | 380 | 0
North Coast | 3148 | 677 | 831.3789 | 1128 | 1042.5629 | 178 | 9.068e-05 | 105.4426 | 30.5471 | 4478.8901 | 101974.7226 | 4510.5424 | 1.6989 | 142.6933 | 1.3001 | 0.009338 | 0.0012321 | 0.60018 | 0.79744 | {8AA8B63D-CAA4-4D23-B89B-112BF8794298} | 42661103 | WILLITS 1103 | 2500 | 39.4485 | -123.3141 | WILLITS 11032500 | 162 | 124 | 69275.8647 | 48289.254 | 20986.6107 | 48289.254 | 20986.6107 | 0.21931 | 0.016141 | 1.228 | 6.3371 | 311 | 1.6622 | 825 | 0 | 0 | 30.0055 | 619 | 0
Central Valley | 6874 | 502 | 672.5858 | 857 | 853.8665 | 103 | 0.00012046 | 78.1111 | 79.9711 | 1195.0684 | 20233.5658 | 5147.6424 | 2.7254 | 49.496 | 1.1362 | 0.0093379 | 0.0039796 | 0.58576 | 0.78769 | {0EFB4216-A177-4018-B731-828073FEC64E} | 163201102 | WEST POINT 1102 | 34416 | 38.3988 | -120.5256 | WEST POINT 110234416 | 165 | 174 | 28281.6607 | 16938.9243 | 11342.7364 | 16938.9243 | 11342.7364 | 0.4099 | 0.012407 | 1.3398 | 8.3204 | 59 | 0.9618 | 826 | 0 | 0 | 10.5254 | 24 | 0
Sierra | 4943 | 286 | 408.3093 | 1449 | 926.2805 | 129 | 0.0001398 | 88.9276 | 25.8192 | 375.1265 | 3945.5094 | 259.8232 | 4.3354 | 173.9391 | 1.2644 | 0.0093223 | 0.0016362 | 0.19738 | 0.44081 | {60540539-B6BA-4E80-BC6C-988DA579218B} | 153662102 | APPLE HILL 2102 | 51792 | 38.6435 | -120.6959 | APPLE HILL 210251792 | 170 | 171 | 25611.8387 | 14681.2766 | 10930.5622 | 14681.2766 | 10877.0793 | 0.21107 | 0.018035 | 1.4277 | 11.2326 | 220 | 1.2026 | 827 | 0 | 0 | 9.1225 | 1371 | 0
North Coast | 7155 | 67 | 93.276 | 114 | 118.9717 | 21 | 0.00028437 | 38.5507 | 0.86163 | 71.7956 | 623.3242 | 1.1278 | 0.3465 | 12.4166 | 1.018 | 0.0093157 | 0.00024785 | 0.58772 | 0.78402 | {BDFC6231-C003-4BB6-9C95-EEAEA882FC5D} | 192311142 | FRUITLAND 1142 | 63170 | 40.2219 | -123.8199 | FRUITLAND 114263170 | 119 | 181 | 27138.1892 | 21723.3744 | 5414.8148 | 19693.2907 | 2750.2215 | 0.0052049 | 0.0059717 | 1.3922 | 5.4286 | 1256 | 0.19563 | 828 | 0 | 0 | 12.2368 | 1615 | 0
North Coast | 2379 | 371 | 600.2441 | 793 | 758.3967 | 103 | 9.2402e-05 | 139.1858 | 10.06 | 297.6511 | 5077.3959 | 503.8911 | 3.1198 | 45.7179 | 1.1612 | 0.0093057 | 0.00037307 | 0.46784 | 0.79146 | {4A405FCD-64B2-4AE1-B455-764875D385D0} | 42141101 | CLEAR LAKE 1101 | 1302 | 39.0041 | -122.8437 | CLEAR LAKE 11011302 | 294 | 562 | 71475.111 | 28050.5504 | 43424.5606 | 11041.6679 | 23663.2364 | 0.038426 | 0.0095174 | 1.6179 | 7.699 | 977 | 0.95848 | 829 | 0 | 0 | 6.861 | 2553 | 0
Central Valley | 1261 | 395 | 611.5587 | 2421 | 1333.7002 | 425 | 4.7374e-05 | 173.1043 | 11.729 | 507.9509 | 3614.5848 | 80.4718 | 5.5994 | 120.2211 | 1.2756 | 0.0093027 | 0.00032619 | 0.16316 | 0.45854 | {B98EC037-8B2E-4659-97E2-613B4380C532} | 163351703 | CURTIS 1703 | 9180 | 37.9527 | -120.3681 | CURTIS 17039180 | 551 | 476 | 144190.2304 | 93135.0691 | 51055.1613 | 93135.0691 | 51055.1613 | 0.13863 | 0.020134 | 1.5482 | 5.6965 | 1067 | 3.9536 | 830 | 0 | 0 | 57.8714 | 834 | 0
North Coast | 8365 | 1376 | 1907.5397 | 1455 | 1944.7777 | 96 | 0.0001042 | 91.435 | 0.99373 | 136.8561 | 1023.9036 | 1.244 | 0.82621 | 21.2049 | 1.0647 | 0.0092799 | 9.8973e-05 | 0.9457 | 0.98085 | {DC0A7D01-2EED-443F-A8C6-2C05CEB2611C} | 192461102 | BRIDGEVILLE 1102 | 37486 | 40.4615 | -123.8396 | BRIDGEVILLE 110237486 | 153 | 157 | 28756.9481 | 18386.8195 | 10370.1286 | 16908.281 | 9994.8234 | 0.0095014 | 0.010003 | 1.3863 | 15.1562 | 1855 | 0.89087 | 831 | 0 | 0 | 10.5063 | 2276 | 0
Central Coast | 4680 | 16 | 35.6368 | 23 | 39.9471 | 9 | 3.1203e-05 | 269.7778 | 43.4763 | 182.7202 | 706.1638 | 39.8032 | 20.6271 | 103.6313 | 1.046 | 0.0092694 | 0.00067674 | 0.69565 | 0.8921 | {553C693F-FB0A-403F-AF7B-DFD04F0B4035} | 182541103 | ATASCADERO 1103 | A88 | 35.4581 | -120.6456 | ATASCADERO 1103A88 | 97 | 47 | 6488.0985 | 4273.7537 | 2214.3447 | 1106.7141 | 842.0094 | 0.0060907 | 0.00028083 | 2.2273 | 2.5556 | 591 | 0.083425 | 832 | 0 | 0 | 0.68768 | 1911 | 0
North Coast | 290 | 320 | 427.0972 | 581 | 550.4299 | 60 | 9.2128e-05 | 113.9302 | 14.4351 | 715.8711 | 7376.0489 | 292.5582 | 4.8832 | 178.7224 | 1.1834 | 0.0092488 | 0.00070525 | 0.55077 | 0.77593 | {DE700694-1BC1-42F0-BD3F-498F1D5E0950} | 42951101 | MENDOCINO 1101 | 31322 | 39.2656 | -123.2041 | MENDOCINO 110131322 | 533 | 630 | 95020.7406 | 46258.8786 | 48761.862 | 7456.8364 | 6513.4506 | 0.042315 | 0.0055277 | 1.3347 | 9.6833 | 562 | 0.55493 | 833 | 0 | 0 | 4.6335 | 285 | 0
North Coast | 6721 | 245 | 322.042 | 1046 | 760.5569 | 79 | 9.8206e-05 | 103.6072 | 1.3732 | 68.0639 | 750.9749 | 2.9387 | 2.9677 | 38.0306 | 1.1564 | 0.009234 | 0.00011059 | 0.23423 | 0.42343 | {0A4816B0-BB69-491B-8E9D-476A9DF6F15C} | 42091102 | MIRABEL 1102 | 334 | 38.5009 | -122.9052 | MIRABEL 1102334 | 136 | 100 | 20100.5939 | 14759.2293 | 5341.3646 | 7485.5189 | 3183.5448 | 0.0087363 | 0.0077583 | 1.3145 | 13.2405 | 1798 | 0.72948 | 834 | 0 | 0 | 4.6513 | 1978 | 0
North Coast | 8011 | 33 | 42.1174 | 52 | 52.524 | 3 | 5.3451e-05 | 135.0261 | 0.50124 | 12.5076 | 110.2346 | 0.10905 | 4.5737 | 53.5312 | 1.115 | 0.0092136 | 3.725e-05 | 0.63462 | 0.80187 | {A0D136BC-BED5-4E61-825E-2EC84D15BD33} | 42821102 | CLOVERDALE 1102 | circuit_breaker | 38.7973 | -123.0109 | CLOVERDALE 1102circuit_breaker | 74 | 187 | 16137.4995 | 4874.945 | 11262.5545 | 420.2416 | 569.7847 | 0.00011175 | 0.00016035 | 1.2763 | 17.3333 | 2374 | 0.027641 | 835 | 0 | 0 | 0.26113 | 2736 | 0
North Coast | 3425 | 1295 | 2107.928 | 2248 | 2662.417 | 208 | 0.00015668 | 57.1186 | 10.7254 | 97.7594 | 919.016 | 42.0449 | 5.378 | 50.9074 | 1.1074 | 0.0092116 | 0.00096834 | 0.57607 | 0.79173 | {20117F3E-B95A-44FF-848A-F718B3011E5C} | 42571102 | MOLINO 1102 | 396 | 38.4096 | -122.9355 | MOLINO 1102396 | 278 | 388 | 50493.3718 | 25719.6473 | 24773.7245 | 25719.6473 | 24773.7245 | 0.20141 | 0.032589 | 1.6277 | 10.8077 | 427 | 1.916 | 836 | 0 | 0 | 15.9814 | 1474 | 0
North Valley | 952 | 1017 | 1773.5824 | 2333 | 2402.7346 | 290 | 0.00010732 | 90.6554 | 234.7936 | 6378.7441 | 140671.2286 | 38610.7291 | 1.2491 | 49.3895 | 1.1518 | 0.0091932 | 0.011652 | 0.43592 | 0.73815 | {A419DB79-B16D-4DB7-B7A8-B2FF0808C0AC} | 103221101 | KANAKA 1101 | 83288 | 39.5275 | -121.2862 | KANAKA 110183288 | 187 | 155 | 37611.0769 | 28024.1151 | 9586.9619 | 28024.1151 | 9586.9619 | 3.379 | 0.031123 | 1.7439 | 8.0448 | 4 | 2.666 | 837 | 0 | 0 | 17.4134 | 22 | 0
North Coast | 2538 | 40 | 73.424 | 174 | 112.3642 | 33 | 4.9508e-05 | 202.6238 | 0.51373 | 2.0017 | 4.5014 | 0.026933 | 4.9639 | 34.8667 | 0.99155 | 0.0090807 | 4.1121e-05 | 0.22989 | 0.65345 | {0628807D-B297-4343-8118-F7F853EA05DA} | 43211101 | HARTLEY 1101 | 86876 | 39.0405 | -122.939 | HARTLEY 110186876 | 275 | 926 | 50601.1902 | 13541.1985 | 37059.9917 | 3441.3803 | 3984.1394 | 0.001357 | 0.0016338 | 1.8356 | 5.2727 | 2326 | 0.29966 | 838 | 0 | 0 | 2.1384 | 1673 | 0
North Coast | 1008 | 1927 | 2149.3899 | 2522 | 2434.1887 | 225 | 0.00016068 | 58.1065 | 5.5961 | 251.8267 | 2761.663 | 29.7703 | 1.3862 | 51.3821 | 1.1609 | 0.0090491 | 0.00046118 | 0.76408 | 0.883 | {7F4B9844-ADF3-422F-9AC4-7D66BD72A184} | 192411101 | LOW GAP 1101 | 2094 | 40.436 | -123.4882 | LOW GAP 11012094 | 192 | 192 | 34621.0821 | 27430.2028 | 7190.8793 | 24081.2978 | 4639.0065 | 0.10377 | 0.036152 | 1.1154 | 11.2089 | 844 | 2.036 | 839 | 0 | 0 | 14.9634 | 473 | 0
Bay Area | 2774 | 990 | 1577.3592 | 2130 | 2219.4053 | 90 | 0.00012153 | 57.6665 | 0.99355 | 0.50622 | 1.5984 | 0.026187 | 0.49931 | 7.205 | 0.79373 | 0.0090214 | 0.0001101 | 0.46479 | 0.71071 | {5A7E1969-E475-4A2E-A5C6-85EFB5802FE4} | 42031124 | ALTO 1124 | 432 | 37.9088 | -122.5475 | ALTO 1124432 | 174 | 622 | 38990.9764 | 12584.9285 | 26406.0479 | 12584.9285 | 26168.5291 | 0.0099089 | 0.010938 | 1.5933 | 23.6667 | 1800 | 0.81193 | 840 | 0 | 0 | 7.8199 | 2174 | 0
North Coast | 7830 | 461 | 593.6672 | 717 | 719.0362 | 77 | 0.00014664 | 82.648 | 4.5784 | 195.0576 | 2204.3614 | 21.9517 | 5.066 | 54.84 | 1.2026 | 0.0089969 | 0.00032076 | 0.64296 | 0.82564 | {35FAF06A-E239-4015-A854-21F6A4EC4F03} | 192411101 | LOW GAP 1101 | 86816 | 40.4621 | -123.5304 | LOW GAP 110186816 | 81 | 140 | 10733.617 | 7103.5026 | 3630.1144 | 7103.5026 | 3630.1144 | 0.024699 | 0.011291 | 1.2878 | 9.3117 | 1073 | 0.69276 | 841 | 0 | 0 | 4.4139 | 374 | 0
Central Valley | 4365 | 90 | 124.6888 | 458 | 286.0339 | 55 | 9.6825e-05 | 95.2191 | 100.7413 | 1864.0558 | 33060.6727 | 6190.8779 | 0.48359 | 46.8852 | 1.2217 | 0.0089959 | 0.0045317 | 0.19651 | 0.43592 | {B92F58F2-6135-47A4-8467-3E84B6151393} | 163201101 | WEST POINT 1101 | circuit_breaker | 38.4213 | -120.5492 | WEST POINT 1101circuit_breaker | 30 | 6 | 8056.4146 | 7549.0145 | 507.4002 | 7549.0145 | 507.4002 | 0.24924 | 0.0053254 | 1.3854 | 8.3273 | 42 | 0.49477 | 842 | 0 | 0 | 4.6907 | 307 | 0
North Valley | 5453 | 1849 | 3555.5785 | 3192 | 4185.837 | 273 | 9.2953e-05 | 95.8099 | 23.4044 | 923.7409 | 19435.244 | 2257.1893 | 0.48772 | 21.1943 | 1.0394 | 0.0089751 | 0.0010297 | 0.57926 | 0.84943 | {6A653745-C5CA-4E78-9C62-82F0E53CCD59} | 103201101 | CHALLENGE 1101 | circuit_breaker | 39.4855 | -121.22 | CHALLENGE 1101circuit_breaker | 231 | 263 | 37599.7439 | 26688.0859 | 10911.658 | 26688.0859 | 10911.658 | 0.28112 | 0.025376 | 1.923 | 11.6923 | 398 | 2.4502 | 843 | 0 | 0 | 16.5832 | 581 | 0
Sierra | 66 | 150 | 266.5997 | 646 | 403.1314 | 79 | 5.161e-05 | 149.2325 | 4.0704 | 83.1702 | 269.6225 | 4.9467 | 5.1898 | 120.6012 | 1.0765 | 0.0089602 | 0.00014853 | 0.2322 | 0.66132 | {D76845FE-B268-426A-A73C-E770602E73F9} | 152921101 | BROWNS VALLEY 1101 | 97188 | 39.2279 | -121.414 | BROWNS VALLEY 110197188 | 83 | 79 | 17072.464 | 10687.565 | 6384.8991 | 10687.565 | 6384.8991 | 0.011734 | 0.0040772 | 1.7773 | 8.1772 | 1599 | 0.70785 | 844 | 0 | 0 | 6.6409 | 647 | 0
North Valley | 2781 | 22 | 56.7274 | 101 | 79.7782 | 61 | 3.827e-05 | 229.3793 | 27.2158 | 81.7253 | 307.9517 | 26.1191 | 9.9588 | 77.9692 | 1.0859 | 0.0089554 | 0.00054536 | 0.21782 | 0.71106 | {18BCFDD7-AD26-4B95-9A8E-1B5EFFBCB7AF} | 103461101 | PANORAMA 1101 | 9092 | 40.4036 | -122.2335 | PANORAMA 11019092 | 527 | 436 | 57361.5092 | 32236.0251 | 25125.4841 | 16503.8389 | 8983.9154 | 0.033267 | 0.0023345 | 2.5785 | 1.6557 | 743 | 0.54628 | 845 | 0 | 0 | 10.255 | 816 | 0
Sierra | 5439 | 146 | 271.9813 | 571 | 427.4982 | 97 | 4.6544e-05 | 220.7262 | 2.3715 | 221.1346 | 923.2116 | 5.0339 | 3.1221 | 332.8962 | 1.4339 | 0.0089439 | 7.3953e-05 | 0.25569 | 0.63622 | {7B0321EB-AC29-4857-8514-66B11EFDEF70} | 153132101 | NARROWS 2101 | circuit_breaker | 39.2351 | -121.2689 | NARROWS 2101circuit_breaker | 89 | 38 | 26194.4059 | 25133.8252 | 1060.5807 | 25133.8252 | 1060.5807 | 0.0071734 | 0.0045148 | 1.8629 | 5.8866 | 2026 | 0.86756 | 846 | 0 | 0 | 15.6174 | 2802 | 0
Central Coast | 1837 | 57 | 74.1158 | 545 | 383.8273 | 58 | 7.9751e-05 | 142.1287 | 1.0508 | 44.3856 | 183.2816 | 0.91227 | 6.1194 | 129.7181 | 1.1344 | 0.0089264 | 7.0538e-05 | 0.10459 | 0.1931 | {29732AB3-8644-4D02-B399-63E828AF790C} | 183052110 | TEMPLETON 2110 | R06 | 35.5543 | -120.7222 | TEMPLETON 2110R06 | 388 | 190 | 53315.3469 | 41555.5333 | 11759.8137 | 8134.5668 | 3868.8241 | 0.0040912 | 0.0046256 | 1.3003 | 9.3966 | 2052 | 0.51773 | 847 | 0 | 0 | 5.0546 | 1643 | 0
Central Coast | 5523 | 7 | 26.7131 | 7 | 26.7131 | 2 | 2.0189e-05 | 466.0392 | 21.5007 | 352.9401 | 1031.9193 | 22.187 | 16.7257 | 263.5069 | 1.3783 | 0.00892 | 0.00016709 | 1 | 1 | {2D522AA5-8F8F-4B96-B755-D0E01134E6CB} | 82931101 | POINT MORETTI 1101 | 5104 | 37.0302 | -122.1868 | POINT MORETTI 11015104 | 21 | 2 | 3055.1591 | 3011.2994 | 43.8597 | 3011.2994 | 43.8597 | 0.00033417 | 4.0379e-05 | 3.8162 | 3.5 | 1528 | 0.01784 | 848 | 0 | 0 | 1.8711 | 1141 | 0
North Coast | 1477 | 1330 | 2146.5432 | 1833 | 2391.2546 | 201 | 0.00025011 | 32.564 | 2.1422 | 160.967 | 1124.1137 | 5.2658 | 0.41397 | 32.6279 | 1.0685 | 0.0089078 | 0.00036073 | 0.72559 | 0.89766 | {793DCBEA-5781-44DD-9297-E7975A642482} | 192221101 | GARBERVILLE 1101 | 1750 | 40.0853 | -123.8075 | GARBERVILLE 11011750 | 92 | 116 | 31216.1738 | 23805.8246 | 7410.3492 | 23509.5028 | 7410.3492 | 0.072507 | 0.050273 | 1.6139 | 9.1194 | 998 | 1.7905 | 849 | 0 | 0 | 14.6081 | 1036 | 0
Sierra | 1703 | 868 | 1315.0039 | 2190 | 1864.5851 | 329 | 6.3862e-05 | 142.6016 | 9.7531 | 218.7499 | 1917.6234 | 53.6627 | 8.3302 | 132.5721 | 1.292 | 0.0088988 | 0.00031448 | 0.39635 | 0.70525 | {15BB893C-861D-4514-BB53-2456F70C5D54} | 153132102 | NARROWS 2102 | 2220 | 39.2538 | -121.1981 | NARROWS 21022220 | 372 | 287 | 71662.1252 | 45257.431 | 26404.6941 | 43302.8869 | 25447.2495 | 0.10346 | 0.021011 | 1.515 | 6.6565 | 1094 | 2.9277 | 850 | 0 | 0 | 26.9072 | 2627 | 0
Sierra | 4543 | 267 | 472.9472 | 934 | 715.8332 | 130 | 4.6039e-05 | 221.8596 | 6.955 | 143.8343 | 800.7484 | 13.1144 | 9.9258 | 190.9306 | 1.3929 | 0.0088328 | 0.00014472 | 0.28587 | 0.66069 | {D508D44B-0B7F-43CB-B9DA-F37161CA8F62} | 153132105 | NARROWS 2105 | 51582 | 39.2065 | -121.263 | NARROWS 210551582 | 144 | 136 | 24814.8402 | 15330.2671 | 9484.5731 | 15330.2671 | 9484.5731 | 0.018813 | 0.0059851 | 1.7713 | 7.1846 | 1618 | 1.1483 | 851 | 0 | 0 | 9.5258 | 1454 | 0
Sierra | 2628 | 1014 | 1468.3172 | 3154 | 2398.2473 | 523 | 9.1234e-05 | 126.2515 | 18.6423 | 556.2881 | 5315.3842 | 196.3317 | 6.0123 | 120.587 | 1.3089 | 0.0088141 | 0.00080945 | 0.3215 | 0.61225 | {71852C93-FB23-454D-AA22-159ABBF0F364} | 153662102 | APPLE HILL 2102 | 77546 | 38.5701 | -120.7327 | APPLE HILL 210277546 | 540 | 433 | 91653.5791 | 69457.7296 | 22195.8495 | 69457.7296 | 22195.8495 | 0.42334 | 0.047715 | 1.448 | 6.0306 | 495 | 4.6098 | 852 | 0 | 0 | 43.159 | 231 | 0
Central Valley | 2628 | 3 | 4.0758 | 11 | 9.6899 | 1 | 0.00014702 | 23.8786 |  |  |  |  | 0.56416 | 24.3338 | 1.0066 | 0.0035106 | 0.00014702 | 0.27273 | 0.42062 | {71852C93-FB23-454D-AA22-159ABBF0F364} | 153662102 | APPLE HILL 2102 | 77546 | 38.5701 | -120.7327 | APPLE HILL 210277546 | 540 | 433 | 91653.5791 | 69457.7296 | 22195.8495 | 69457.7296 | 22195.8495 | 0.00014702 | 0.00014702 | 1.3586 | 11 | 1610 | 0.0035106 | 852 | 0 | 0 | 43.159 | 626 | 0
Sierra | 3171 | 598 | 960.2487 | 1975 | 1504.9227 | 215 | 7.6503e-05 | 125.0098 | 7.5501 | 46.9549 | 221.5208 | 10.0576 | 6.7107 | 39.8378 | 1.0665 | 0.0087857 | 0.00028104 | 0.30278 | 0.63807 | {605358FE-4007-4349-A521-8A072F22F69A} | 152271102 | WISE 1102 | circuit_breaker | 38.8897 | -121.0985 | WISE 1102circuit_breaker | 400 | 499 | 59126.3645 | 30515.1162 | 28611.2483 | 29505.5664 | 27810.8239 | 0.060425 | 0.016448 | 1.6058 | 9.186 | 1175 | 1.8889 | 853 | 0 | 0 | 18.3339 | 171 | 0
Central Valley | 8930 | 28 | 45.6635 | 108 | 74.9405 | 36 | 2.2651e-05 | 345.0789 | 3.5429 | 796.8495 | 5141.6287 | 22.7918 | 1.6544 | 405.7811 | 1.4744 | 0.0087216 | 5.2122e-05 | 0.25926 | 0.60933 | {ABA71BA3-C71D-490E-AEB5-C37239F168A1} | 252192105 | BEAR VALLEY 2105 | 4170 | 37.6103 | -120.1339 | BEAR VALLEY 21054170 | 53 | 19 | 18937.3255 | 15319.6375 | 3617.688 | 15319.6375 | 3617.688 | 0.0018764 | 0.00081544 | 1.6308 | 3 | 2219 | 0.31398 | 854 | 0 | 0 | 9.5192 | 1975 | 0
North Valley | 4789 | 1554 | 2389.9562 | 3667 | 3397.4836 | 391 | 0.00010236 | 88.9736 | 203.0166 | 4518.9703 | 111514.7389 | 31611.8737 | 1.7748 | 54.1068 | 1.1616 | 0.008703 | 0.0086662 | 0.42378 | 0.70345 | {792CA981-4B7A-4CA2-BE90-3F8181AF2243} | 102911103 | WYANDOTTE 1103 | 1976 | 39.6349 | -121.3918 | WYANDOTTE 11031976 | 313 | 278 | 59677.2926 | 38602.5649 | 21074.7277 | 38602.5649 | 21074.7277 | 3.3885 | 0.040022 | 1.5379 | 9.3785 | 14 | 3.4029 | 855 | 0 | 0 | 23.9865 | 2389 | 0
Central Valley | 5633 | 48 | 79.3636 | 276 | 177.6805 | 39 | 4.4262e-05 | 253.5329 | 19.8089 | 295.1163 | 2079.1077 | 71.5746 | 16.4527 | 362.6094 | 1.7023 | 0.0086954 | 0.00044556 | 0.17391 | 0.44666 | {045D9164-1EA4-4D2F-BCF3-8AA3EF9C5F1E} | 254421103 | OAKHURST 1103 | 5732 | 37.3991 | -119.7005 | OAKHURST 11035732 | 46 | 53 | 7948.6554 | 5570.0761 | 2378.5793 | 5570.0761 | 2378.5793 | 0.017377 | 0.0017262 | 1.6534 | 7.0769 | 871 | 0.33912 | 856 | 0 | 0 | 3.4611 | 290 | 0
North Coast | 7594 | 1422 | 2248.0345 | 2354 | 2702.6926 | 177 | 0.00010894 | 78.6478 | 34.1083 | 1665.9172 | 26256.3044 | 2177.8118 | 0.32873 | 38.3732 | 1.2495 | 0.0086865 | 0.0016532 | 0.60408 | 0.83178 | {58B05117-AB7A-45AA-AA55-0723582FB8F1} | 42661103 | WILLITS 1103 | 37506 | 39.4831 | -123.3611 | WILLITS 110337506 | 100 | 63 | 25729.8459 | 18589.4866 | 7140.3593 | 18589.4866 | 7140.3593 | 0.29262 | 0.019282 | 1.5809 | 13.2994 | 215 | 1.5375 | 857 | 0 | 0 | 11.551 | 2434 | 0
Bay Area | 4753 | 98 | 194.7521 | 648 | 488.2884 | 48 | 5.8092e-05 | 209.8877 | 8.0182 | 401.197 | 3883.7339 | 87.3145 | 3.9757 | 171.5008 | 1.2791 | 0.0086545 | 0.0001739 | 0.15123 | 0.39885 | {D374E70A-F10D-42BF-BFC9-DC52D8E99DC6} | 43292103 | PUEBLO 2103 | 1970 | 38.3156 | -122.3419 | PUEBLO 21031970 | 228 | 490 | 40241.9657 | 13574.3858 | 26667.5799 | 5037.9118 | 4479.3839 | 0.008347 | 0.0027884 | 1.9873 | 13.5 | 1508 | 0.41542 | 858 | 0 | 0 | 3.1304 | 2167 | 0
North Coast | 4359 | 172 | 303.4395 | 496 | 418.507 | 105 | 6.8581e-05 | 137.0023 | 5.1825 | 77.1084 | 799.3103 | 13.4772 | 4.796 | 159.2246 | 1.3886 | 0.0086285 | 0.00015746 | 0.34677 | 0.72505 | {BFEEA045-A307-47A2-9C2E-0B69ACE24065} | 43351106 | LUCERNE 1106 | 526 | 39.0763 | -122.783 | LUCERNE 1106526 | 173 | 366 | 34906.4402 | 17455.0829 | 17451.3574 | 16072.0884 | 13994.239 | 0.016534 | 0.007201 | 1.7642 | 4.7238 | 1554 | 0.906 | 859 | 0 | 0 | 9.9867 | 1497 | 0
North Valley | 4292 | 0 | 0 | 60 | 27.7497 | 23 | 6.7216e-06 | 1173.9084 | 11.1428 | 2045.7167 | 12474.9023 | 238.4755 | 27.0664 | 1289.4999 | 1.6464 | 0.0085969 | 3.666e-05 | 0 | 0 | {FAF0B739-3196-4C1D-A8BD-B6B12F707FEC} | 103491101 | MC ARTHUR 1101 | 38998 | 41.0562 | -121.383 | MC ARTHUR 110138998 | 221 | 179 | 32651.9155 | 26238.7768 | 6413.1387 | 15389.4778 | 2109.3525 | 0.00084319 | 0.0001546 |  | 2.6087 | 2378 | 0.19773 | 860 | 0 | 0 | 9.5626 | 175 | 0
Central Coast | 4945 | 380 | 775.0187 | 2056 | 1750.9572 | 182 | 6.839e-05 | 129.9332 | 1.5727 | 30.235 | 152.5161 | 0.78324 | 4.3327 | 47.9997 | 1.0881 | 0.0085705 | 8.5311e-05 | 0.18482 | 0.44263 | {331D14B2-6B0F-4273-9F56-8DD687C4B860} | 182631107 | SAN LUIS OBISPO 1107 | V60 | 35.1846 | -120.7043 | SAN LUIS OBISPO 1107V60 | 200 | 226 | 41845.6362 | 25701.6823 | 16143.9538 | 25701.6823 | 16143.9538 | 0.015527 | 0.012447 | 2.0395 | 11.2967 | 1945 | 1.5598 | 861 | 0 | 0 | 15.9703 | 2570 | 0
Central Valley | 9511 | 13 | 12.9167 | 49 | 31.8514 | 23 | 9.8801e-05 | 80.7183 | 84.2108 | 952.7619 | 16832.5552 | 2805.2488 | 0.25789 | 34.4834 | 1.3237 | 0.0085676 | 0.0043474 | 0.26531 | 0.40553 | {42CE80CD-1575-4D75-9DA9-13CC191BD6F8} | 161380201 | TIGER CREEK 0201 | circuit_breaker | 38.4489 | -120.4922 | TIGER CREEK 0201circuit_breaker | 23 | 21 | 6804.8389 | 6272.7997 | 532.0392 | 6272.7997 | 532.0392 | 0.09999 | 0.0022724 | 0.99359 | 2.1304 | 49 | 0.19705 | 862 | 0 | 0 | 3.8977 | 1896 | 0
North Valley | 9487 | 146 | 154.5197 | 218 | 193.9663 | 49 | 9.7867e-05 | 90.8249 | 0.80911 | 3168.7331 | 81637.261 | 133.1685 | 0.00013545 | 48.7805 | 1.1276 | 0.0085488 | 8.5139e-05 | 0.66972 | 0.79663 | {83B8DDA8-0AE6-4FAA-9DFB-D57952CAA5C2} | 101321101 | PIT NO 5 1101 | 1618 | 40.9885 | -121.9742 | PIT NO 5 11011618 | 24 | 0 | 9746.1598 | 9746.1598 | 0 | 9746.1598 | 0 | 0.0041718 | 0.0047955 | 1.0584 | 4.449 | 1948 | 0.41889 | 863 | 0 | 0 | 6.056 | 109 | 0
Central Valley | 8869 | 24 | 44.9778 | 100 | 72.0228 | 20 | 5.3018e-05 | 123.8353 | 6.6414 | 399.7794 | 1855.0134 | 42.0044 | 7.3713 | 523.8288 | 1.5997 | 0.0085256 | 0.00014057 | 0.24 | 0.62449 | {3D156343-1F71-46EE-A300-26BD3EB64071} | 163541101 | OLETA 1101 | circuit_breaker | 38.4807 | -120.8451 | OLETA 1101circuit_breaker | 25 | 3 | 5694.3587 | 5393.0771 | 301.2817 | 5372.4907 | 301.2817 | 0.0028114 | 0.0010604 | 1.8741 | 5 | 1630 | 0.17051 | 864 | 0 | 0 | 3.3383 | 2256 | 0
Central Valley | 5162 | 364 | 524.3108 | 970 | 813.0102 | 135 | 6.5424e-05 | 130.0365 | 13.3771 | 118.2101 | 798.4892 | 20.1207 | 7.2478 | 107.404 | 1.2334 | 0.0084906 | 0.00040732 | 0.37526 | 0.6449 | {F2F4DFE2-A71E-4AEB-AA05-9FF7D56E28F8} | 252531102 | SAN JOAQUIN #3 1102 | circuit_breaker | 37.2539 | -119.5194 | SAN JOAQUIN #3 1102circuit_breaker | 133 | 232 | 26617.2245 | 15601.4012 | 11015.8233 | 15601.4012 | 11015.8233 | 0.054988 | 0.0088323 | 1.4404 | 7.1852 | 933 | 1.1462 | 865 | 0 | 0 | 9.6943 | 1212 | 0
North Valley | 8995 | 25 | 25.89 | 50 | 40.7225 | 8 | 0.00011283 | 68.4363 | 0.015316 | 582.7861 | 16855.4062 | 0.75687 | 0.080752 | 22.6092 | 1.0702 | 0.0084841 | 6.7282e-05 | 0.5 | 0.63577 | {B85628F4-AFE8-455E-8E14-4DB09FEDE759} | 101321101 | PIT NO 5 1101 | circuit_breaker | 40.9869 | -121.9763 | PIT NO 5 1101circuit_breaker | 21 | 15 | 1569.9399 | 1162.2395 | 407.7004 | 1162.2395 | 407.7004 | 0.00053826 | 0.00090268 | 1.0356 | 6.25 | 2076 | 0.067873 | 866 | 0 | 0 | 0.72218 | 487 | 0
North Valley | 3208 | 416 | 700.3923 | 1516 | 1168.4502 | 244 | 0.00015999 | 50.8698 | 33.7472 | 294.0643 | 4771.2965 | 1095.6048 | 2.0216 | 31.8032 | 1.0319 | 0.0084732 | 0.0029506 | 0.27441 | 0.59942 | {7666B122-2C0C-4302-93AF-84BE4CAB5B18} | 103451101 | KESWICK 1101 | 9712 | 40.6166 | -122.4955 | KESWICK 11019712 | 358 | 409 | 45946.1588 | 29985.2487 | 15960.9101 | 29985.2487 | 15960.9101 | 0.71994 | 0.039038 | 1.6836 | 6.2131 | 109 | 2.0674 | 867 | 0 | 0 | 18.632 | 643 | 0
Central Coast | 2219 | 112 | 289.9432 | 336 | 413.1055 | 76 | 1.786e-05 | 469.5024 | 9.0676 | 93.5847 | 288.1584 | 11.8209 | 16.4369 | 297.8648 | 1.099 | 0.0084724 | 8.2155e-05 | 0.33333 | 0.70186 | {10854A52-7EF2-416D-830E-BF803A6482A0} | 83392110 | SWIFT 2110 | XR366 | 37.3326 | -121.7785 | SWIFT 2110XR366 | 226 | 233 | 31991.0305 | 17763.6308 | 14227.3997 | 13196.8212 | 6836.1856 | 0.0062437 | 0.0013573 | 2.5888 | 4.4211 | 1970 | 0.64391 | 868 | 0 | 0 | 8.2001 | 743 | 0
Sierra | 3501 | 1091 | 1821.1209 | 2782 | 2515.204 | 210 | 9.7683e-05 | 85.0818 | 11.7022 | 58.5428 | 232.5588 | 6.1797 | 5.7909 | 53.6935 | 1.1065 | 0.0084667 | 0.00063574 | 0.39216 | 0.72404 | {CD96B61F-E4EC-4F93-8ED7-3657DC7B6074} | 152561107 | PENRYN 1107 | 346 | 38.8253 | -121.1633 | PENRYN 1107346 | 616 | 563 | 71444.504 | 40334.4226 | 31110.0815 | 22020.6709 | 13346.9322 | 0.13351 | 0.020513 | 1.6692 | 13.2476 | 631 | 1.778 | 869 | 0 | 0 | 13.683 | 1715 | 0
Sierra | 3438 | 21 | 32.7907 | 70 | 51.6207 | 8 | 8.4174e-05 | 110.0389 | 13.0203 | 221.2392 | 2618.2644 | 38.8163 | 2.4071 | 30.5344 | 1.1485 | 0.0084369 | 0.00018845 | 0.3 | 0.63522 | {484AFB5A-CE87-4795-AA87-E15AE760BDD4} | 153132102 | NARROWS 2102 | 2718 | 39.2354 | -121.2209 | NARROWS 21022718 | 241 | 111 | 16944.4571 | 11669.952 | 5274.5052 | 747.0941 | 206.4792 | 0.0015076 | 0.00067339 | 1.5615 | 8.75 | 1454 | 0.067495 | 870 | 0 | 0 | 0.46422 | 762 | 0
North Coast | 6929 | 75 | 127.8185 | 237 | 221.6727 | 52 | 4.8603e-05 | 155.3977 | 104.1643 | 1528.7726 | 9007.3127 | 1264.3592 | 6.9849 | 246.5722 | 1.0822 | 0.0083873 | 0.0017828 | 0.31646 | 0.57661 | {65D2A24B-53D1-4E2C-BACD-455AAC4417E6} | 43371102 | LAKEVILLE 1102 | 3341 | 38.2866 | -122.6389 | LAKEVILLE 11023341 | 121 | 89 | 30351.4679 | 20071.3044 | 10280.1635 | 11684.2399 | 7202.4896 | 0.092706 | 0.0025273 | 1.7042 | 4.5577 | 198 | 0.43614 | 871 | 0 | 0 | 7.2602 | 1289 | 0
North Coast | 7822 | 7 | 22.9268 | 13 | 25.6612 | 1 | 0.00011659 | 71.8048 |  |  |  |  | 1.8982 | 88.9321 | 1.0221 | 0.0083717 | 0.00011659 | 0.53846 | 0.89344 | {7FAC07ED-E166-44B1-881F-FAD3AE3EA85D} | 42271105 | COTATI 1105 | 893 | 38.3203 | -122.8513 | COTATI 1105893 | 120 | 125 | 31178.1547 | 16957.7992 | 14220.3556 | 105.1251 | 680.8944 | 0.00011659 | 0.00011659 | 3.2753 | 13 | 1766 | 0.0083717 | 872 | 0 | 0 | 0.065322 | 1366 | 0
Sierra | 3023 | 186 | 299.0206 | 752 | 511.6932 | 66 | 0.00015033 | 86.2423 | 2.6444 | 5.2844 | 22.3891 | 0.51217 | 2.6648 | 16.1519 | 0.97992 | 0.0083262 | 0.00032252 | 0.24734 | 0.58437 | {95880633-835C-41AD-A217-FF4EBDC70BBD} | 153652108 | SHINGLE SPRINGS 2108 | 19622 | 38.6569 | -120.9928 | SHINGLE SPRINGS 210819622 | 385 | 771 | 43646.8098 | 18790.9041 | 24855.9057 | 8713.308 | 8953.124 | 0.021286 | 0.009922 | 1.6076 | 11.3939 | 1069 | 0.54953 | 873 | 0 | 0 | 5.4142 | 408 | 0
Central Valley | 6103 | 7 | 12.8976 | 25 | 17.8071 | 11 | 0.00011628 | 62.79 | 99.2644 | 1356.2044 | 8086.3135 | 1182.0527 | 5.2039 | 270.9259 | 1.1965 | 0.0083008 | 0.0066837 | 0.28 | 0.7243 | {931E0ACF-1FAB-493D-95FA-FA513D1003B5} | 163231101 | NORTH BRANCH 1101 | 13496 | 38.1994 | -120.8282 | NORTH BRANCH 110113496 | 150 | 332 | 21521.2704 | 8066.3398 | 13454.9306 | 2903.2847 | 1341.2127 | 0.073521 | 0.0012791 | 1.8425 | 2.2727 | 24 | 0.091309 | 874 | 0 | 0 | 1.804 | 1498 | 0
North Coast | 7335 | 193 | 248.819 | 395 | 361.4239 | 41 | 0.00012005 | 67.4077 | 5.0819 | 67.394 | 594.5557 | 5.8409 | 1.9496 | 20.1367 | 1.0339 | 0.0082695 | 0.00036824 | 0.48861 | 0.68844 | {D409FD83-0B7E-49F1-B258-94C24ABDABA1} | 43071101 | DUNBAR 1101 | 4817 | 38.4 | -122.5697 | DUNBAR 11014817 | 71 | 70 | 9534.9529 | 4994.4292 | 4540.5237 | 4994.4292 | 4540.5237 | 0.015098 | 0.0049219 | 1.2892 | 9.6341 | 987 | 0.33905 | 875 | 0 | 0 | 3.1034 | 497 | 0
Central Valley | 2067 | 973 | 1287.4556 | 2175 | 1855.7715 | 182 | 0.00011337 | 71.5473 | 90.0543 | 1408.9632 | 22089.0127 | 4395.3694 | 2.1049 | 38.0523 | 1.1079 | 0.008266 | 0.0052866 | 0.44736 | 0.69376 | {EC11255E-1283-4994-89AE-376C709CBC76} | 163201102 | WEST POINT 1102 | circuit_breaker | 38.4212 | -120.5493 | WEST POINT 1102circuit_breaker | 343 | 479 | 50164.9275 | 28676.4886 | 21488.4389 | 28676.4886 | 21488.4389 | 0.96217 | 0.020633 | 1.3232 | 11.9505 | 34 | 1.5044 | 876 | 0 | 0 | 17.8187 | 530 | 0
Central Valley | 7345 | 0 | 0 | 3 | 0.85385 | 2 | 2.5807e-05 | 394.9883 |  |  |  |  | 18.5376 | 372.4893 | 1.6482 | 0.0082504 | 2.5807e-05 | 0 | 0 | {6985CB9B-1F8C-4CB7-A5AE-AEFA2BA7C828} | 254151101 | AUBERRY 1101 | 49122 | 37.0811 | -119.4877 | AUBERRY 110149122 | 75 | 47 | 9022.3102 | 6376.7942 | 2645.516 | 6376.7942 | 2645.516 | 5.1613e-05 | 5.1613e-05 |  | 1.5 | 2518 | 0.016501 | 877 | 0 | 0 | 3.9624 | 2855 | 0
North Coast | 6120 | 333 | 508.1614 | 581 | 656.4557 | 88 | 0.00011796 | 66.5918 | 12.674 | 263.6548 | 3767.8305 | 85.9124 | 1.2298 | 50.056 | 1.1892 | 0.0082285 | 0.00077553 | 0.57315 | 0.7741 | {DDD005A1-4733-4F2A-A213-96BA207EE134} | 42811113 | MONTE RIO 1113 | 1991 | 38.5445 | -122.9849 | MONTE RIO 11131991 | 57 | 43 | 15186.7781 | 11352.1197 | 3834.6584 | 11352.1197 | 3834.6584 | 0.068246 | 0.010381 | 1.526 | 6.6023 | 515 | 0.72411 | 878 | 0 | 0 | 7.0539 | 1315 | 0
Central Valley | 7614 | 31 | 59.4433 | 157 | 106.7349 | 48 | 6.8032e-05 | 189.0874 | 20.2626 | 925.1922 | 8833.4988 | 503.1753 | 7.1841 | 418.186 | 1.4717 | 0.0081941 | 0.00053913 | 0.19745 | 0.55692 | {D6398899-238B-49AC-A776-D1F3468DFF9B} | 254452102 | MARIPOSA 2102 | circuit_breaker | 37.5046 | -120.0078 | MARIPOSA 2102circuit_breaker | 49 | 49 | 13162.5579 | 8571.1084 | 4591.4495 | 8453.5074 | 4433.9535 | 0.025878 | 0.0032655 | 1.9175 | 3.2708 | 748 | 0.39332 | 879 | 0 | 0 | 5.2528 | 1052 | 0
Central Valley | 3488 | 62 | 104.0426 | 248 | 169.6506 | 109 | 5.7855e-05 | 155.7403 | 7.4422 | 266.8481 | 1422.33 | 15.165 | 8.3532 | 335.4793 | 1.325 | 0.0081063 | 0.00018429 | 0.25 | 0.61328 | {C597D1DF-05AF-4117-9139-6F79BFFC0A15} | 163541101 | OLETA 1101 | 13478 | 38.4364 | -120.8347 | OLETA 110113478 | 309 | 508 | 44804.9946 | 24622.6296 | 20182.365 | 19228.1516 | 8262.8231 | 0.020088 | 0.0063062 | 1.6781 | 2.2752 | 1468 | 0.88359 | 880 | 0 | 0 | 11.9478 | 2833 | 0
North Coast | 5722 | 1 | 2.9829 | 1 | 2.9829 | 1 | 8.5187e-05 | 95.1377 |  |  |  |  | 0.5 | 17.3856 | 1.0243 | 0.0081045 | 8.5187e-05 | 1 | 1 | {2B626DC9-13BD-4F58-BFDD-9C1FE143AC91} | 43040401 | GARCIA 0401 | 666 | 38.8887 | -123.5506 | GARCIA 0401666 | 14 | 11 | 4207.344 | 3911.285 | 296.059 | 3911.285 | 296.059 | 8.5187e-05 | 8.5187e-05 | 2.9829 | 1 | 1947 | 0.0081045 | 881 | 0 | 0 | 2.4304 | 623 | 0
North Valley | 4035 | 516 | 1184.5477 | 903 | 1375.693 | 110 | 6.9253e-05 | 120.7188 | 107.1921 | 2281.3248 | 52026.5087 | 7849.1617 | 1.1308 | 27.8573 | 1.0667 | 0.0081008 | 0.0039393 | 0.57143 | 0.86106 | {458FC9CE-4CFA-459C-BFC4-3FAD1C0058BF} | 103031102 | ORO FINO 1102 | 2096 | 39.8789 | -121.6116 | ORO FINO 11022096 | 191 | 177 | 33267.0161 | 22689.7759 | 10577.2402 | 22689.7759 | 10577.2402 | 0.43333 | 0.0076178 | 2.2956 | 8.2091 | 61 | 0.89108 | 882 | 0 | 0 | 14.0988 | 858 | 0
North Valley | 8909 | 31 | 71.119 | 72 | 84.6502 | 11 | 5.977e-05 | 125.6497 | 15.14 | 42.5449 | 148.0271 | 5.4826 | 6.7212 | 57.2496 | 1.0545 | 0.0079304 | 0.00072881 | 0.43056 | 0.84015 | {DC072A52-F5DE-4BA4-8BCD-F573BF64066B} | 102911109 | WYANDOTTE 1109 | 42650 | 39.4807 | -121.5296 | WYANDOTTE 110942650 | 78 | 140 | 11710.0919 | 4239.6112 | 7470.4807 | 1091.021 | 904.7032 | 0.0080169 | 0.00065747 | 2.2942 | 6.5455 | 547 | 0.087234 | 883 | 0 | 0 | 0.67793 | 1230 | 0
North Valley | 2318 | 651 | 936.7532 | 2183 | 1660.7478 | 282 | 8.2146e-05 | 108.3666 | 1.9036 | 197.5987 | 2319.5033 | 13.33 | 2.6333 | 103.4984 | 1.2265 | 0.0078911 | 0.00011758 | 0.29821 | 0.56406 | {CA013557-36E2-4043-ADB2-0CAC45D0FC29} | 103601101 | WHITMORE 1101 | 1594 | 40.6313 | -121.9036 | WHITMORE 11011594 | 192 | 145 | 49813.1834 | 39015.2543 | 10797.9291 | 39015.2543 | 10797.9291 | 0.033157 | 0.023165 | 1.4389 | 7.7411 | 1757 | 2.2253 | 884 | 0 | 0 | 24.2429 | 2498 | 0
Central Coast | 4507 | 209 | 568.5441 | 466 | 717.6145 | 82 | 2.1702e-05 | 438.6926 | 10.4828 | 122.8867 | 630.5799 | 20.5228 | 10.444 | 186.1452 | 1.1898 | 0.0078609 | 9.7183e-05 | 0.4485 | 0.79227 | {84A17C4B-1356-4E5D-9790-C7A137661BEE} | 182631104 | SAN LUIS OBISPO 1104 | V40 | 35.2197 | -120.5967 | SAN LUIS OBISPO 1104V40 | 259 | 186 | 51478.2393 | 37142.5765 | 14335.6628 | 22025.4599 | 8522.9959 | 0.007969 | 0.0017795 | 2.7203 | 5.6829 | 1867 | 0.6446 | 885 | 0 | 0 | 13.686 | 2171 | 0
Sierra | 4566 | 191 | 328.0872 | 585 | 495.9459 | 57 | 7.7038e-05 | 121.9499 | 4.9884 | 46.481 | 228.738 | 4.2458 | 5.7986 | 54.3515 | 1.2803 | 0.0078457 | 0.00019856 | 0.3265 | 0.66154 | {919A8A04-B874-4A68-AF90-D4143250C76A} | 152271101 | WISE 1101 | circuit_breaker | 38.8897 | -121.0985 | WISE 1101circuit_breaker | 214 | 282 | 26992.8115 | 14425.555 | 12567.2565 | 6518.1918 | 5647.7215 | 0.011318 | 0.0043912 | 1.7177 | 10.2632 | 1419 | 0.4472 | 886 | 0 | 0 | 4.0502 | 1425 | 0
North Valley | 3522 | 241 | 341.82 | 836 | 632.5846 | 137 | 2.4139e-05 | 327.7783 | 2.9823 | 192.5966 | 836.6084 | 6.0677 | 9.361 | 218.8331 | 1.1216 | 0.0078069 | 4.7529e-05 | 0.28828 | 0.54035 | {47AA609B-0BD3-40D9-878F-3D1F5D334A7D} | 103721101 | PIT NO 1 1101 | 1552 | 41.0152 | -121.4689 | PIT NO 1 11011552 | 295 | 307 | 65193.7785 | 42573.1939 | 22620.5846 | 20793.5873 | 10045.3684 | 0.0065114 | 0.003307 | 1.4183 | 6.1022 | 2256 | 1.0695 | 887 | 0 | 0 | 12.9205 | 447 | 0
Bay Area | 5007 | 682 | 1326.9592 | 1676 | 1857.8265 | 159 | 7.6929e-05 | 85.8704 | 0.53781 | 77.2127 | 759.2377 | 2.5622 | 0.51059 | 39.0561 | 1.0819 | 0.0078006 | 6.0694e-05 | 0.40692 | 0.71425 | {0D5489FC-3A6E-4BAE-918E-36EE08559B7E} | 42031125 | ALTO 1125 | 902 | 37.8891 | -122.5553 | ALTO 1125902 | 127 | 181 | 29378.8558 | 19412.9994 | 9965.8564 | 19412.9994 | 9965.8564 | 0.0096504 | 0.012232 | 1.9457 | 10.5409 | 2132 | 1.2403 | 888 | 0 | 0 | 12.0627 | 2548 | 0
North Coast | 5259 | 724 | 972.0383 | 1483 | 1400.5444 | 202 | 0.00010226 | 68.1929 | 14.4741 | 468.3917 | 8343.0252 | 348.6573 | 1.3553 | 44.253 | 1.1243 | 0.0077899 | 0.00087892 | 0.4882 | 0.69404 | {5426272A-AD0A-4461-A119-14316B37A620} | 43071103 | DUNBAR 1103 | 534 | 38.3792 | -122.5191 | DUNBAR 1103534 | 220 | 190 | 40640.681 | 28145.853 | 12494.828 | 25938.9873 | 10873.6194 | 0.17754 | 0.020656 | 1.3426 | 7.3416 | 458 | 1.5736 | 889 | 0 | 0 | 16.1177 | 820 | 0
North Valley | 1768 | 1178 | 1783.1511 | 5285 | 3420.758 | 593 | 7.36e-05 | 100.0594 | 23.1802 | 1092.7579 | 14727.4332 | 1136.3265 | 3.1636 | 81.7359 | 1.1426 | 0.0077896 | 0.00086033 | 0.22289 | 0.52127 | {F430F9BA-4822-49EF-972E-D271E55910BA} | 103191101 | BANGOR 1101 | 1804 | 39.39 | -121.4043 | BANGOR 11011804 | 522 | 481 | 97918.2627 | 69024.4911 | 28893.7716 | 69024.4911 | 28893.7716 | 0.51018 | 0.043645 | 1.5137 | 8.9123 | 467 | 4.6192 | 890 | 0 | 0 | 42.8898 | 553 | 0
North Coast | 6685 | 208 | 322.7614 | 340 | 378.1506 | 35 | 6.7309e-05 | 164.6885 | 16.3129 | 479.2387 | 6503.8068 | 390.4216 | 1.3257 | 139.296 | 1.2664 | 0.0077718 | 0.00046856 | 0.61176 | 0.85353 | {8A5CF734-63C5-45CD-9511-BDF8DA98EA25} | 43311102 | KONOCTI 1102 | 64464 | 38.9443 | -122.6752 | KONOCTI 110264464 | 51 | 146 | 10663.8346 | 4327.7045 | 6336.1301 | 3132.1045 | 3041.1003 | 0.0164 | 0.0023558 | 1.5517 | 9.7143 | 831 | 0.27201 | 891 | 0 | 0 | 1.9462 | 1056 | 0
Bay Area | 2135 | 5 | 7.2826 | 18 | 14.9342 | 4 | 3.1033e-05 | 251.9201 | 0.053962 | 2.59 | 13.9515 | 0.013804 | 4.2992 | 252.7671 | 1.2909 | 0.0077682 | 8.2225e-06 | 0.27778 | 0.48765 | {EB7314AB-7754-4D90-B11B-A641443B251F} | 43292102 | PUEBLO 2102 | circuit_breaker | 38.3452 | -122.2997 | PUEBLO 2102circuit_breaker | 273 | 213 | 50327.4693 | 25233.7086 | 25093.7608 | 802.3935 | 26.0889 | 3.289e-05 | 0.00012413 | 1.4565 | 4.5 | 2808 | 0.031073 | 892 | 0 | 0 | 0.49858 | 2858 | 0
North Coast | 4073 | 1479 | 2350.0208 | 2375 | 2802.5076 | 183 | 0.00027965 | 28.9276 | 2.7283 | 151.4599 | 1274.2769 | 6.9156 | 0.60879 | 25.9207 | 1.0914 | 0.0077156 | 0.00052156 | 0.62274 | 0.83854 | {1339ADD4-8465-4C5F-ADF0-25D79054621F} | 192221102 | GARBERVILLE 1102 | 1510 | 40.1222 | -123.8352 | GARBERVILLE 11021510 | 175 | 164 | 26458.8864 | 21228.5996 | 5230.2868 | 21228.5996 | 5230.2868 | 0.095445 | 0.051176 | 1.5889 | 12.9781 | 774 | 1.412 | 893 | 0 | 0 | 13.1908 | 823 | 0
North Coast | 949 | 127 | 173.3252 | 328 | 286.3691 | 24 | 0.00010627 | 70.5733 | 3.0046 | 52.8531 | 591.3813 | 5.093 | 2.7566 | 42.5435 | 1.0558 | 0.0077012 | 0.000224 | 0.3872 | 0.60525 | {E5FC257A-973F-414F-A273-EE859A543B23} | 43071102 | DUNBAR 1102 | 903030 | 38.382 | -122.5549 | DUNBAR 1102903030 | 25 | 28 | 4351.2867 | 2345.7829 | 2005.5038 | 2345.7829 | 2005.5038 | 0.005376 | 0.0025504 | 1.3648 | 13.6667 | 1329 | 0.18483 | 894 | 0 | 0 | 1.4576 | 1294 | 0
North Coast | 6896 | 761 | 932.5375 | 885 | 989.5998 | 101 | 0.00016499 | 45.131 | 4.9264 | 701.5984 | 12718.8273 | 196.6385 | 0.92951 | 71.6995 | 1.2256 | 0.0076923 | 0.00042805 | 0.85989 | 0.94234 | {24C71D6A-46DB-4BB7-8807-9800CAD347CE} | 192461101 | BRIDGEVILLE 1101 | 37484 | 40.4523 | -123.6539 | BRIDGEVILLE 110137484 | 90 | 45 | 19197.4071 | 16191.138 | 3006.2692 | 12953.0865 | 2424.305 | 0.043233 | 0.016664 | 1.2254 | 8.7624 | 896 | 0.77693 | 895 | 0 | 0 | 8.0487 | 972 | 0
Bay Area | 9320 | 193 | 347.439 | 342 | 438.2377 | 17 | 0.00015661 | 49.0248 | 6.5293 | 39.0591 | 633.2349 | 11.0986 | 0.42348 | 7.4714 | 1.0139 | 0.0076587 | 0.00061349 | 0.56433 | 0.79281 | {4E7059E5-B496-4153-B6AF-F578ED348327} | 43432104 | SILVERADO 2104 | 645 | 38.5378 | -122.4705 | SILVERADO 2104645 | 22 | 37 | 3337.0089 | 1626.8938 | 1710.1151 | 1626.8938 | 1710.1151 | 0.010429 | 0.0026623 | 1.8002 | 20.1176 | 657 | 0.1302 | 896 | 0 | 0 | 1.0109 | 1287 | 0
Sierra | 4730 | 49 | 84.3288 | 219 | 156.2881 | 33 | 7.4879e-05 | 129.2384 | 5.6328 | 18.2194 | 43.3876 | 0.59902 | 5.8298 | 54.0686 | 1.0577 | 0.0076551 | 0.00022969 | 0.22374 | 0.53957 | {070E580D-ED42-47CA-BF5A-6C96D8E39FC5} | 153132102 | NARROWS 2102 | 76952 | 39.253 | -121.1971 | NARROWS 210276952 | 350 | 206 | 28806.7305 | 18031.5566 | 10775.1739 | 3554.8483 | 1998.5316 | 0.0075797 | 0.002471 | 1.721 | 6.6364 | 1311 | 0.25262 | 897 | 0 | 0 | 2.2089 | 200 | 0
North Coast | 2439 | 314 | 577.5669 | 831 | 754.2676 | 133 | 4.6112e-05 | 122.1252 | 3.0332 | 12.4287 | 81.7771 | 1.0912 | 3.2401 | 47.88 | 1.2775 | 0.007653 | 8.9262e-05 | 0.37786 | 0.76573 | {3ED5FB3A-A2CD-4F13-ABBF-430305FFB318} | 43191101 | REDBUD 1101 | circuit_breaker | 39.0271 | -122.6629 | REDBUD 1101circuit_breaker | 413 | 1499 | 90748.6992 | 23104.2807 | 67644.4184 | 15284.1769 | 34165.9766 | 0.011872 | 0.0061328 | 1.8394 | 6.2481 | 1915 | 1.0178 | 898 | 0 | 0 | 9.4971 | 735 | 0
Central Coast | 9177 | 15 | 25.3283 | 55 | 47.6626 | 8 | 3.2506e-05 | 226.9189 | 0.79919 | 8.8751 | 28.4148 | 0.52553 | 14.3421 | 570.7733 | 1.3042 | 0.0076224 | 2.889e-05 | 0.27273 | 0.53141 | {9CF012F9-04AA-46D1-BCF0-338A1EC7E054} | 83182101 | LLAGAS 2101 | 4523 | 37.0193 | -121.5204 | LLAGAS 21014523 | 44 | 52 | 8826.1169 | 4420.7892 | 4405.3277 | 1169.9655 | 1078.7883 | 0.00023112 | 0.00026005 | 1.6886 | 6.875 | 2477 | 0.06098 | 899 | 0 | 0 | 0.72698 | 1815 | 0
North Coast | 7191 | 1587 | 2452.3319 | 2403 | 2844.775 | 213 | 0.0001981 | 39.1267 | 1.3365 | 75.71 | 594.2045 | 1.4664 | 0.21807 | 16.7401 | 1.0513 | 0.0076073 | 0.00023633 | 0.66042 | 0.86205 | {BA71994D-6A0B-4F0B-9E44-79C1DD5F42DD} | 192221101 | GARBERVILLE 1101 | 97300 | 39.9723 | -123.8008 | GARBERVILLE 110197300 | 134 | 100 | 27385.8509 | 22729.2098 | 4656.641 | 22729.2098 | 4656.641 | 0.050338 | 0.042195 | 1.5453 | 11.2817 | 1292 | 1.6204 | 900 | 0 | 0 | 14.1233 | 1983 | 0
North Coast | 5072 | 7 | 12.797 | 11 | 14.5234 | 5 | 6.8255e-05 | 105.4739 | 30.1721 | 657.0175 | 3567.2873 | 163.7571 | 2.835 | 117.1315 | 1.1695 | 0.0075719 | 0.0010432 | 0.63636 | 0.88113 | {92C865B2-0C37-47A7-A1CF-103D45B5F3C3} | 43381101 | POINT ARENA 1101 | 37426 | 38.912 | -123.6807 | POINT ARENA 110137426 | 136 | 309 | 19677.258 | 8133.5264 | 11543.7316 | 776.126 | 285.6046 | 0.005216 | 0.00034128 | 1.8281 | 2.2 | 387 | 0.03786 | 901 | 0 | 0 | 0.48226 | 795 | 0
North Coast | 3097 | 70 | 107.4043 | 95 | 122.0623 | 26 | 9.0877e-05 | 91.2365 | 4.4556 | 527.1476 | 3276.1489 | 33.146 | 1.6197 | 154.2926 | 1.1723 | 0.0075562 | 0.00024782 | 0.73684 | 0.87991 | {4BB38AE8-B760-4E43-B459-E75BDA0EF348} | 43161101 | SALMON CREEK 1101 | 194 | 38.3487 | -123.0613 | SALMON CREEK 1101194 | 110 | 203 | 21877.0573 | 13583.0049 | 8294.0524 | 7700.4518 | 5551.2443 | 0.0064434 | 0.0023628 | 1.5343 | 3.6538 | 1257 | 0.19646 | 902 | 0 | 0 | 4.7848 | 2604 | 0
Central Valley | 7359 | 217 | 296.1217 | 504 | 441.6505 | 59 | 7.2139e-05 | 105.3799 | 73.5032 | 2192.8742 | 32694.1953 | 3558.302 | 4.7223 | 153.1008 | 1.472 | 0.0075413 | 0.002673 | 0.43056 | 0.67049 | {CA439F72-C503-4E1D-A7E3-1CE4E62334DD} | 163201102 | WEST POINT 1102 | 1369 | 38.4058 | -120.5359 | WEST POINT 11021369 | 91 | 81 | 26175.6152 | 17175.8338 | 8999.7814 | 15950.4182 | 8642.9879 | 0.15771 | 0.0042562 | 1.3646 | 8.5424 | 119 | 0.44494 | 903 | 0 | 0 | 9.9111 | 2624 | 0
Central Valley | 2844 | 1 | 2.8532 | 35 | 18.3482 | 1 | 5.8341e-06 | 1290.4875 |  |  |  |  | 8.2168 | 2561.0579 | 1.9425 | 0.0075289 | 5.8341e-06 | 0.028571 | 0.1555 | {391E65C1-AEAE-49D7-9726-5DDBC48D6DA9} | 252931103 | TEJON 1103 | 2280 | 35.0162 | -118.8709 | TEJON 11032280 | 164 | 86 | 46226.6054 | 44165.0695 | 2061.5359 | 2624.0904 | 90.7142 | 5.8341e-06 | 5.8341e-06 | 2.8532 | 35 | 2839 | 0.0075289 | 904 | 0 | 0 | 1.6305 | 227 | 0
North Coast | 38 | 101 | 172.5293 | 251 | 227.1447 | 70 | 5.8139e-05 | 134.2296 | 19.5878 | 1482.3809 | 19548.3321 | 1201.6537 | 7.7181 | 412.3085 | 1.4413 | 0.0075118 | 0.00047448 | 0.40239 | 0.75956 | {3492968E-3545-4212-B771-A444F5766479} | 43191101 | REDBUD 1101 | 708166 | 39.0231 | -122.678 | REDBUD 1101708166 | 208 | 159 | 61014.3982 | 32947.3958 | 28067.0024 | 13686.2588 | 11445.8545 | 0.033213 | 0.0040697 | 1.7082 | 3.5857 | 818 | 0.52582 | 905 | 0 | 0 | 8.5042 | 1010 | 0
North Coast | 3660 | 236 | 371.26 | 469 | 497.5837 | 46 | 8.3977e-05 | 81.7358 | 10.3709 | 113.7619 | 1340.8563 | 34.1343 | 0.78025 | 29.9854 | 1.2546 | 0.0074706 | 0.00041074 | 0.5032 | 0.74613 | {AC5E1196-E1A0-4AEB-87C6-E671E2DDECCF} | 42811113 | MONTE RIO 1113 | 1137 | 38.5277 | -122.9999 | MONTE RIO 11131137 | 36 | 38 | 8876.2051 | 4563.9223 | 4312.2828 | 4563.9223 | 4312.2828 | 0.018894 | 0.0038629 | 1.5731 | 10.1957 | 926 | 0.34365 | 906 | 0 | 0 | 2.8359 | 358 | 0
Sierra | 4289 | 605 | 774.2422 | 1324 | 1133.1188 | 157 | 0.00012324 | 58.8302 | 146.4516 | 4185.3083 | 73627.3018 | 16465.1029 | 1.2742 | 27.7996 | 1.0625 | 0.0074491 | 0.0082237 | 0.45695 | 0.68328 | {1FCD571D-957E-4FF9-863E-0126FD4A401D} | 153662102 | APPLE HILL 2102 | 97982 | 38.6216 | -120.5867 | APPLE HILL 210297982 | 150 | 125 | 25339.7862 | 15759.3574 | 9580.4288 | 15759.3574 | 9580.4288 | 1.2911 | 0.019349 | 1.2797 | 8.4331 | 16 | 1.1695 | 907 | 0 | 0 | 9.7924 | 375 | 0
Central Coast | 782 | 73 | 176.0624 | 656 | 560.7716 | 115 | 1.4959e-05 | 470.4799 | 25.4366 | 108.3809 | 571.7051 | 69.495 | 13.6606 | 175.5821 | 1.1278 | 0.0074226 | 0.00019412 | 0.11128 | 0.31396 | {9476F86E-2EE0-4DDC-B659-7AD569267F21} | 182821101 | MESA 1101 | M86 | 35.0492 | -120.4827 | MESA 1101M86 | 327 | 324 | 55844.2973 | 33506.261 | 22338.0363 | 18124.1497 | 16040.224 | 0.022324 | 0.0017203 | 2.4118 | 5.7043 | 1431 | 0.8536 | 908 | 0 | 0 | 11.2618 | 2081 | 0
North Coast | 4380 | 3281 | 4349.8388 | 4094 | 4794.9478 | 361 | 0.00013725 | 51.4512 | 62.0355 | 3663.1802 | 81058.2971 | 8347.9857 | 3.034 | 72.1249 | 1.154 | 0.0074151 | 0.0042438 | 0.80142 | 0.90717 | {7E4735B5-33E8-4CD6-9F8D-A9385ABC1901} | 42661103 | WILLITS 1103 | 968 | 39.406 | -123.3251 | WILLITS 1103968 | 439 | 457 | 81519.9922 | 44486.495 | 37033.4972 | 42022.0904 | 33917.9059 | 1.532 | 0.049548 | 1.3258 | 11.3407 | 54 | 2.6769 | 909 | 0 | 0 | 26.1113 | 519 | 0
Sierra | 315 | 481 | 726.7854 | 947 | 966.7603 | 126 | 0.0001015 | 70.2886 | 36.3636 | 2065.6828 | 42718.6431 | 3167.3121 | 2.6786 | 41.8193 | 1.1203 | 0.0074109 | 0.0019038 | 0.50792 | 0.75177 | {17868210-FE0A-4C1E-968A-924A3CB32589} | 152201101 | PIKE CITY 1101 | 1730 | 39.452 | -121.0541 | PIKE CITY 11011730 | 112 | 108 | 19126.9343 | 13838.6427 | 5288.2916 | 13838.6427 | 5288.2916 | 0.23988 | 0.012789 | 1.511 | 7.5159 | 185 | 0.93378 | 910 | 0 | 0 | 8.5989 | 332 | 0
North Coast | 5574 | 3515 | 6294.5558 | 4191 | 6625.4316 | 259 | 0.00025644 | 30.4421 | 1.5302 | 93.7639 | 1062.8824 | 2.7755 | 0.33027 | 13.3551 | 1.0347 | 0.0073881 | 0.00032971 | 0.8387 | 0.95006 | {0A529EA6-6476-4FE6-9A4C-9E2DBC5F560C} | 192221102 | GARBERVILLE 1102 | 6084 | 40.0621 | -123.9619 | GARBERVILLE 11026084 | 165 | 163 | 32920.4248 | 24635.362 | 8285.0629 | 24635.362 | 8285.0629 | 0.085396 | 0.066418 | 1.7908 | 16.1815 | 1056 | 1.9135 | 911 | 0 | 0 | 15.3077 | 13 | 0
North Valley | 7501 | 150 | 202.4707 | 181 | 216.9177 | 28 | 0.00012991 | 55.5699 | 2.2845 | 3690.43 | 96416.1702 | 287.7704 | 0.039981 | 121.7339 | 1.3639 | 0.0073855 | 0.00018793 | 0.82873 | 0.9334 | {E4590054-53CD-4399-A96C-42C934E0E3BE} | 103501101 | PIT NO 7 1101 | circuit_breaker | 40.8485 | -121.9911 | PIT NO 7 1101circuit_breaker | 4 | 2 | 4407.9495 | 4357.8457 | 50.1039 | 4357.8457 | 50.1039 | 0.0052619 | 0.0036374 | 1.3498 | 6.4643 | 1456 | 0.20679 | 912 | 0 | 0 | 2.7078 | 220 | 0
North Valley | 5990 | 575 | 862.2023 | 944 | 1055.3982 | 104 | 0.00013531 | 149.6746 | 12.9242 | 275.1631 | 1474.8168 | 47.5124 | 3.862 | 51.978 | 1.0646 | 0.0073765 | 0.00081026 | 0.60911 | 0.81695 | {916B572F-25AB-43E4-8DCE-50B2436F4EE2} | 102831103 | PARADISE 1103 | circuit_breaker | 39.7607 | -121.619 | PARADISE 1103circuit_breaker | 816 | 481 | 87190.2158 | 59708.3774 | 27481.8385 | 53143.2931 | 26499.5112 | 0.084267 | 0.014072 | 1.4995 | 9.0769 | 494 | 0.76716 | 913 | 0 | 0 | 33.0217 | 342 | 0
Sierra | 8415 | 641 | 847.5831 | 1179 | 1107.9197 | 125 | 9.6739e-05 | 77.1142 | 53.482 | 1508.0026 | 24685.6968 | 3833.3105 | 1.4213 | 30.8305 | 1.1049 | 0.0073643 | 0.0028465 | 0.54368 | 0.76502 | {EFF2FC24-77B3-4DE1-917B-4B897E42E100} | 152471101 | COLUMBIA HILL 1101 | 2212 | 39.3844 | -121.0318 | COLUMBIA HILL 11012212 | 87 | 90 | 22611.0259 | 14778.7102 | 7832.3157 | 14778.7102 | 7832.3157 | 0.35581 | 0.012092 | 1.3223 | 9.432 | 110 | 0.92054 | 914 | 0 | 0 | 9.1831 | 936 | 0
Central Valley | 2001 | 4 | 7.6302 | 10 | 9.8434 | 5 | 3.0985e-05 | 248.0673 | 13.2378 | 2853.3252 | 10111.3281 | 134.6816 | 8.9336 | 2308.2647 | 1.7894 | 0.0073597 | 5.9253e-05 | 0.4 | 0.77516 | {1B9CB438-3D64-400D-8827-441645AF1444} | 252341104 | REEDLEY 1104 | 274990 | 36.603 | -119.3214 | REEDLEY 1104274990 | 528 | 711 | 94819.4526 | 66865.8982 | 27953.5544 | 2623.0001 | 117.1379 | 0.00029626 | 0.00015492 | 1.9075 | 2 | 2149 | 0.036799 | 915 | 0 | 0 | 1.6299 | 1526 | 0
Bay Area | 1527 | 11 | 13.6357 | 50 | 31.0352 | 8 | 6.0879e-05 | 133.8979 | 0.49591 | 44.9 | 146.1271 | 0.1284 | 11.5868 | 116.9276 | 1.2309 | 0.0073429 | 5.4001e-05 | 0.22 | 0.43936 | {D76FC532-158A-4F2C-85C2-26FC0B6C05CB} | 14302106 | MEADOW LANE 2106 | C558R | 37.9558 | -122.0851 | MEADOW LANE 2106C558R | 460 | 1333 | 85642.736 | 22949.7629 | 62692.9731 | 1360.7806 | 90.4582 | 0.00043201 | 0.00048703 | 1.2396 | 6.25 | 2204 | 0.058743 | 916 | 0 | 0 | 0.84555 | 701 | 0
North Coast | 3038 | 1270 | 1926.3027 | 1911 | 2250.6448 | 185 | 0.00023609 | 28.6146 | 1.2521 | 266.046 | 3545.7485 | 11.7358 | 0.65558 | 56.7838 | 1.1078 | 0.0073272 | 0.00025038 | 0.66457 | 0.85589 | {09BB38E4-7FE7-4BD1-9CFE-F62698521734} | 192221102 | GARBERVILLE 1102 | 2540 | 40.2432 | -124.127 | GARBERVILLE 11022540 | 169 | 128 | 37102.0705 | 28743.4558 | 8358.6148 | 23928.4593 | 7558.7709 | 0.046321 | 0.043678 | 1.5168 | 10.3297 | 1247 | 1.3555 | 917 | 0 | 0 | 14.8685 | 1626 | 0
North Coast | 1947 | 73 | 222.1605 | 83 | 227.2313 | 15 | 8.0923e-05 | 93.7478 | 21.2684 | 84.5117 | 197.4076 | 12.2483 | 11.2956 | 37.9052 | 1.0211 | 0.0073186 | 0.00041419 | 0.87952 | 0.97768 | {711CF875-45FB-4C9E-91F5-632D204CB23D} | 42271105 | COTATI 1105 | 328 | 38.3457 | -122.7606 | COTATI 1105328 | 323 | 780 | 62371.0187 | 22174.0143 | 40197.0044 | 1823.3649 | 4065.6396 | 0.0062129 | 0.0012138 | 3.0433 | 5.5333 | 921 | 0.10978 | 918 | 0 | 0 | 1.133 | 1578 | 0
Central Coast | 2019 | 162 | 486.6543 | 583 | 725.5642 | 138 | 1.8074e-05 | 447.9099 | 2.9953 | 223.7388 | 735.3356 | 4.7537 | 9.8252 | 325.5945 | 1.3503 | 0.0073091 | 3.2922e-05 | 0.27787 | 0.67073 | {B215B9B7-F7F3-4553-8BC7-ED531B03358B} | 183041101 | BUELLTON 1101 | Y06 | 34.6201 | -120.2103 | BUELLTON 1101Y06 | 402 | 359 | 97752.0286 | 64675.3298 | 33076.6988 | 46315.0095 | 22714.0827 | 0.0045432 | 0.0024942 | 3.004 | 4.2246 | 2426 | 1.0087 | 919 | 0 | 0 | 28.7788 | 2136 | 0
North Coast | 783 | 189 | 241.1481 | 366 | 342.5043 | 45 | 0.00011571 | 68.2845 | 3.5497 | 58.5175 | 577.3206 | 5.2032 | 0.91593 | 15.7751 | 1.023 | 0.0072747 | 0.00027222 | 0.51639 | 0.70407 | {099221CD-5C0A-49E5-8576-2B334B5F477C} | 43071101 | DUNBAR 1101 | circuit_breaker | 38.3835 | -122.5281 | DUNBAR 1101circuit_breaker | 340 | 611 | 52116.7121 | 23582.0206 | 28534.6915 | 3778.218 | 4134.6012 | 0.01225 | 0.0052068 | 1.2759 | 8.1333 | 1198 | 0.32736 | 920 | 0 | 0 | 2.3477 | 563 | 0
Bay Area | 3683 | 800 | 1574.115 | 1469 | 1929.8033 | 87 | 0.00010649 | 70.33 | 1.6776 | 5.6407 | 45.6379 | 0.23762 | 1.0333 | 5.6205 | 1.0303 | 0.0072708 | 0.00013767 | 0.54459 | 0.81569 | {5443BEB4-FACA-473E-BC79-5158E049D910} | 42031125 | ALTO 1125 | 510 | 37.8896 | -122.5552 | ALTO 1125510 | 167 | 425 | 30982.1013 | 11874.2275 | 19107.8738 | 11874.2275 | 19107.8738 | 0.011977 | 0.0092644 | 1.9676 | 16.8851 | 1649 | 0.63256 | 921 | 0 | 0 | 7.3783 | 2331 | 0
North Coast | 4371 | 68 | 99.4157 | 249 | 175.0787 | 39 | 9.5417e-05 | 67.7558 | 1.0385 | 15.2816 | 109.5087 | 0.35134 | 1.2136 | 22.5665 | 0.98162 | 0.0072232 | 0.00010083 | 0.27309 | 0.56783 | {1767BA94-AAFE-4694-A170-90C49EF279A2} | 43411102 | CALPELLA 1102 | 496 | 39.1947 | -123.2066 | CALPELLA 1102496 | 322 | 417 | 48826.3573 | 27009.544 | 21816.8133 | 5425.0881 | 5771.2147 | 0.0039325 | 0.0037212 | 1.462 | 6.3846 | 1846 | 0.28171 | 922 | 0 | 0 | 3.371 | 1165 | 0
Central Valley | 3620 | 297 | 472.0371 | 1533 | 895.1686 | 317 | 3.8727e-05 | 267.6984 | 14.8357 | 423.383 | 3848.6941 | 128.0731 | 10.3165 | 303.5694 | 1.5259 | 0.0072179 | 0.00029223 | 0.19374 | 0.52732 | {26575688-884D-4CC7-8C04-F1F692E3F0D5} | 254452101 | MARIPOSA 2101 | 10070 | 37.5077 | -119.996 | MARIPOSA 210110070 | 306 | 253 | 69302.8537 | 41751.638 | 27551.2157 | 41751.638 | 27551.2157 | 0.092637 | 0.012276 | 1.5894 | 4.836 | 1145 | 2.2881 | 923 | 0 | 0 | 25.9433 | 2374 | 0
Bay Area | 9191 | 97 | 188.7006 | 259 | 271.0747 | 42 | 2.1743e-05 | 410.6841 | 0.015255 | 12.4239 | 64.1497 | 0.0032255 | 2.8374 | 385.7799 | 1.334 | 0.0072075 | 1.1376e-05 | 0.37452 | 0.69612 | {AAB781C7-68E3-444A-B651-9C4DDE030346} | 14662112 | TASSAJARA 2112 | 6392 | 37.8434 | -121.9462 | TASSAJARA 21126392 | 51 | 22 | 9696.2868 | 8416.1442 | 1280.1427 | 8416.1442 | 1280.1427 | 0.00047778 | 0.00091323 | 1.9454 | 6.1667 | 2770 | 0.30271 | 924 | 0 | 0 | 5.2295 | 2872 | 0
North Coast | 2130 | 423 | 655.2545 | 1065 | 920.8382 | 220 | 6.7414e-05 | 122.9655 | 5.1974 | 1201.492 | 18945.4114 | 47.4111 | 5.4374 | 193.0394 | 1.3365 | 0.0071888 | 0.00013055 | 0.39718 | 0.71158 | {C7347FC3-B613-4AAE-82AC-3F7111D01C04} | 43411101 | CALPELLA 1101 | 542 | 39.2357 | -123.1787 | CALPELLA 1101542 | 233 | 206 | 59838.372 | 37984.1313 | 21854.2407 | 37983.2329 | 21825.0099 | 0.02872 | 0.014831 | 1.5491 | 4.8409 | 1698 | 1.5815 | 925 | 0 | 0 | 23.6017 | 330 | 0
North Valley | 1065 | 36 | 58.6119 | 115 | 91.4986 | 41 | 4.8556e-05 | 140.1869 | 6.7027 | 967.8473 | 6075.6792 | 71.9214 | 6.7018 | 500.7807 | 1.5118 | 0.0071754 | 0.00021434 | 0.31304 | 0.64058 | {62022298-C96E-4026-AE43-0F12DB277F1C} | 103091102 | CLARK ROAD 1102 | 2044 | 39.6514 | -121.5888 | CLARK ROAD 11022044 | 87 | 49 | 22483.1626 | 20142.1338 | 2341.0288 | 13144.9091 | 1030.9587 | 0.008788 | 0.0019908 | 1.6281 | 2.8049 | 1366 | 0.29419 | 926 | 0 | 0 | 8.1679 | 265 | 0
Central Coast | 7140 | 20 | 40.5988 | 65 | 66.8879 | 15 | 3.663e-05 | 210.1896 | 0.17416 | 415.4146 | 1653.2475 | 0.53143 | 7.5968 | 649.9258 | 1.3727 | 0.0071484 | 2.2659e-05 | 0.30769 | 0.60697 | {F11F1581-106D-4267-B291-AD8060715445} | 83182104 | LLAGAS 2104 | XR294 | 36.9675 | -121.5525 | LLAGAS 2104XR294 | 166 | 94 | 24930.3383 | 16899.7408 | 8030.5974 | 4685.9835 | 205.4585 | 0.00033989 | 0.00054945 | 2.0299 | 4.3333 | 2570 | 0.10723 | 927 | 0 | 0 | 2.9117 | 1269 | 0
North Coast | 6807 | 160 | 256.9324 | 273 | 314.2136 | 21 | 0.00014789 | 45.3593 | 28.8235 | 170.9771 | 1083.8583 | 50.3366 | 4.5158 | 23.6649 | 1.0278 | 0.0071336 | 0.0015415 | 0.58608 | 0.8177 | {52846ED2-3EF3-4ACD-B861-D51B3045E38F} | 42571102 | MOLINO 1102 | 982462 | 38.4047 | -122.8964 | MOLINO 1102982462 | 35 | 46 | 4812.3362 | 2320.9625 | 2491.3736 | 2320.9625 | 2491.3736 | 0.032372 | 0.0031056 | 1.6058 | 13 | 236 | 0.14981 | 928 | 0 | 0 | 1.4422 | 1469 | 0
North Coast | 796 | 810 | 1155.4233 | 2503 | 1992.162 | 209 | 0.00010903 | 65.3043 | 5.1589 | 45.7603 | 360.0764 | 3.9994 | 2.6892 | 21.6823 | 1.0463 | 0.0071315 | 0.0003366 | 0.32361 | 0.57998 | {ECF0597E-C523-4664-9DE2-2ED0EC5C00F2} | 43071102 | DUNBAR 1102 | 246 | 38.3657 | -122.5275 | DUNBAR 1102246 | 234 | 391 | 40835.9461 | 21342.108 | 19493.8381 | 21342.108 | 19493.8381 | 0.070349 | 0.022787 | 1.4264 | 11.9761 | 1038 | 1.4905 | 929 | 0 | 0 | 13.2614 | 2032 | 0
Sierra | 8892 | 429 | 633.9188 | 995 | 896.881 | 94 | 9.9222e-05 | 73.2539 | 20.6533 | 330.568 | 3263.0409 | 165.9069 | 4.024 | 55.4931 | 1.2172 | 0.0071193 | 0.00092147 | 0.43116 | 0.7068 | {93C56D43-333C-4331-959E-24C064CB9C39} | 153741101 | DOBBINS 1101 | 91464 | 39.3719 | -121.2077 | DOBBINS 110191464 | 129 | 120 | 18238.3552 | 11341.1652 | 6897.19 | 11341.1652 | 6897.19 | 0.086618 | 0.0093269 | 1.4777 | 10.5851 | 439 | 0.66921 | 930 | 0 | 0 | 7.0471 | 1254 | 0
Central Valley | 5821 | 16 | 29.9469 | 116 | 68.9027 | 24 | 3.9364e-05 | 136.8253 | 17.5217 | 306.8703 | 3382.5907 | 87.931 | 7.0805 | 186.2068 | 1.2919 | 0.0070701 | 0.00027899 | 0.13793 | 0.43463 | {50B1E436-CAE2-4BB7-88C4-FB7945F4E49E} | 254452101 | MARIPOSA 2101 | 309438 | 37.5025 | -119.9884 | MARIPOSA 2101309438 | 194 | 298 | 26916.2796 | 13018.6366 | 13897.643 | 5630.6567 | 2421.3467 | 0.0066958 | 0.00094473 | 1.8717 | 4.8333 | 1180 | 0.16968 | 931 | 0 | 0 | 3.4987 | 1127 | 0
Central Valley | 4806 | 34 | 64.8994 | 143 | 98.1487 | 58 | 4.9834e-05 | 160.7408 | 9.1719 | 889.1647 | 8096.8072 | 237.9342 | 3.9575 | 346.6525 | 1.5973 | 0.0070354 | 0.00022781 | 0.23776 | 0.66124 | {CE2E0286-475F-4451-81F2-51329124240C} | 252192101 | BEAR VALLEY 2101 | 90550 | 37.5158 | -120.0525 | BEAR VALLEY 210190550 | 60 | 52 | 17171.0018 | 12881.7348 | 4289.267 | 12881.7348 | 4289.267 | 0.013213 | 0.0028904 | 1.9088 | 2.4655 | 1320 | 0.40805 | 932 | 0 | 0 | 8.0043 | 1842 | 0
Central Valley | 853 | 18 | 33.8139 | 59 | 46.9255 | 17 | 2.5762e-05 | 185.3151 | 0.62469 | 91.3001 | 280.0143 | 0.48286 | 7.6309 | 233.2273 | 1.3237 | 0.0070095 | 1.8097e-05 | 0.30508 | 0.72059 | {1961711E-F220-4B05-9528-34A575D6B44D} | 163781701 | PEORIA 1701 | 9811 | 37.8773 | -120.4486 | PEORIA 17019811 | 115 | 135 | 19765.9812 | 14351.9195 | 5414.0618 | 4687.197 | 882.181 | 0.00030765 | 0.00043795 | 1.8785 | 3.4706 | 2648 | 0.11916 | 933 | 0 | 0 | 2.9125 | 875 | 0
North Coast | 3145 | 143 | 439.0299 | 242 | 476.1653 | 52 | 4.6799e-05 | 160.6588 | 6.4434 | 1078.4956 | 5239.3267 | 108.0752 | 5.4362 | 217.7815 | 1.2609 | 0.0069807 | 0.00015686 | 0.59091 | 0.92201 | {BCD422E2-9AE0-44D1-BF49-26A0E5D7C844} | 42271103 | COTATI 1103 | 61736 | 38.2767 | -122.8912 | COTATI 110361736 | 184 | 267 | 40790.8251 | 26748.6696 | 14042.1555 | 18397.7495 | 6698.3068 | 0.0081567 | 0.0024335 | 3.0701 | 4.6538 | 1556 | 0.363 | 934 | 0 | 0 | 11.4318 | 1358 | 0
North Coast | 2973 | 38 | 58.2014 | 59 | 65.7059 | 18 | 5.5155e-05 | 123.4196 | 1.4016 | 220.6586 | 2661.0272 | 18.4312 | 1.9703 | 113.9139 | 1.37 | 0.0069559 | 7.1204e-05 | 0.64407 | 0.88579 | {7D091198-DCC2-4EA1-AD83-C691E4F808C9} | 42251101 | HOPLAND 1101 | 558 | 38.9989 | -123.1172 | HOPLAND 1101558 | 98 | 76 | 18464.6908 | 15006.3279 | 3458.3628 | 2272.5532 | 1234.4749 | 0.0012817 | 0.00099279 | 1.5316 | 3.2778 | 2046 | 0.12521 | 935 | 0 | 0 | 1.4121 | 1352 | 0
Bay Area | 5444 | 508 | 1116.8117 | 2911 | 2522.8125 | 293 | 4.6656e-05 | 173.9992 | 1.0253 | 34.6587 | 104.4508 | 0.93469 | 6.2631 | 127.9164 | 1.1251 | 0.0069456 | 4.5513e-05 | 0.17451 | 0.44269 | {43B3FCFC-E570-42A3-9958-1934EF46169A} | 14101105 | ALHAMBRA 1105 | 82622 | 37.9665 | -122.127 | ALHAMBRA 110582622 | 417 | 290 | 72920.8604 | 41695.7116 | 31225.1488 | 41695.7116 | 31225.1488 | 0.013335 | 0.01367 | 2.1984 | 9.9352 | 2278 | 2.0351 | 936 | 0 | 0 | 25.9085 | 2866 | 0
North Coast | 1141 | 602 | 888.4787 | 1124 | 1165.5076 | 124 | 0.00011785 | 49.2025 | 5.4407 | 57.5945 | 566.8636 | 8.9092 | 2.1706 | 19.7735 | 1.0397 | 0.0069215 | 0.00040048 | 0.53559 | 0.76231 | {34794EA8-41B0-4C58-A267-88FB7ED2F311} | 43071101 | DUNBAR 1101 | 302 | 38.4284 | -122.565 | DUNBAR 1101302 | 206 | 159 | 25257.9159 | 16689.601 | 8568.315 | 13818.0912 | 7142.8928 | 0.04966 | 0.014613 | 1.4759 | 9.0645 | 943 | 0.85826 | 937 | 0 | 0 | 8.5862 | 1307 | 0
Central Coast | 8709 | 190 | 324.8899 | 234 | 349.1985 | 5 | 0.00017694 | 38.1148 | 3.9495 | 9.5702 | 35.0866 | 0.21556 | 0.63894 | 5.7557 | 1.0088 | 0.0068611 | 0.00057046 | 0.81197 | 0.93039 | {C47E0BEE-F56F-4DA1-AE1E-FD70A4E33128} | 83622105 | CAMP EVERS 2105 | 10225 | 37.0995 | -122.0495 | CAMP EVERS 210510225 | 6 | 12 | 665.995 | 292.7321 | 373.2628 | 292.7321 | 373.2628 | 0.0028523 | 0.00088472 | 1.7099 | 46.8 | 711 | 0.034306 | 938 | 0 | 0 | 0.1819 | 1735 | 0
North Coast | 7765 | 424 | 871.6718 | 955 | 1156.8241 | 71 | 7.9425e-05 | 76.8335 | 9.6089 | 199.842 | 2341.7989 | 81.5691 | 3.065 | 29.8783 | 0.90085 | 0.0068409 | 0.00044326 | 0.44398 | 0.7535 | {200F9B52-1051-48E9-985E-1C9F81A1D6A9} | 43071102 | DUNBAR 1102 | 861496 | 38.358 | -122.5256 | DUNBAR 1102861496 | 70 | 114 | 15273.8676 | 7248.9399 | 8024.9278 | 7248.9399 | 8024.9278 | 0.031471 | 0.0056392 | 2.0558 | 13.4507 | 876 | 0.48571 | 939 | 0 | 0 | 4.5043 | 1603 | 0
North Coast | 9082 | 208 | 250.3645 | 365 | 343.1358 | 26 | 0.00010427 | 65.9584 | 5.6052 | 176.3562 | 2274.0677 | 25.9714 | 1.9952 | 74.5269 | 1.287 | 0.0068059 | 0.00029986 | 0.56986 | 0.72964 | {1D81D8F5-A042-428A-8894-895D8E08C89E} | 43321103 | RINCON 1103 | 5152 | 38.5499 | -122.6678 | RINCON 11035152 | 24 | 8 | 2986.5025 | 2561.9657 | 424.5368 | 2561.9657 | 424.5368 | 0.0077963 | 0.0027111 | 1.2037 | 14.0385 | 1125 | 0.17695 | 940 | 0 | 0 | 1.5919 | 745 | 0
North Coast | 6476 | 1091 | 1654.7697 | 1975 | 2094.782 | 232 | 0.00018325 | 34.2863 | 3.0244 | 408.1888 | 9133.8726 | 92.7657 | 0.15958 | 16.4762 | 1.0571 | 0.0068018 | 0.00034386 | 0.55241 | 0.78995 | {40D83712-E530-4392-B692-30F2EF646603} | 192401101 | HOOPA 1101 | 3304 | 41.1053 | -123.6888 | HOOPA 11013304 | 113 | 80 | 29489.9979 | 27461.6659 | 2028.3321 | 27461.6659 | 2028.3321 | 0.079776 | 0.042514 | 1.5167 | 8.5129 | 1023 | 1.578 | 941 | 0 | 0 | 17.0639 | 1344 | 0
Central Valley | 963 | 1588 | 2270.6216 | 4483 | 3681.1833 | 734 | 8.9318e-05 | 86.3872 | 18.5997 | 487.3251 | 5440.2703 | 299.2138 | 2.728 | 128.2279 | 1.2283 | 0.0067718 | 0.00081397 | 0.35423 | 0.61682 | {7DA2EEB5-1A19-437C-8020-DD813277F9CC} | 163201102 | WEST POINT 1102 | 4788 | 38.3314 | -120.5187 | WEST POINT 11024788 | 847 | 686 | 160327.1528 | 113054.7153 | 47272.4375 | 113054.7153 | 47272.4375 | 0.59745 | 0.065559 | 1.4299 | 6.1076 | 492 | 4.9705 | 942 | 0 | 0 | 70.2489 | 951 | 0
Sierra | 7679 | 545 | 679.6143 | 1091 | 911.0395 | 88 | 0.00011348 | 63.0393 | 63.9543 | 797.6901 | 14769.107 | 3872.8666 | 1.9341 | 24.5537 | 1.0401 | 0.0067652 | 0.0031858 | 0.49954 | 0.74598 | {8414F562-3617-4BAD-BBB4-DAC100815794} | 152181101 | FORESTHILL 1101 | 75340 | 39.0023 | -120.8592 | FORESTHILL 110175340 | 104 | 73 | 12607.2916 | 8005.6151 | 4601.6765 | 8005.6151 | 4601.6765 | 0.28035 | 0.0099861 | 1.247 | 12.3977 | 93 | 0.59533 | 943 | 0 | 0 | 4.9745 | 242 | 0
Bay Area | 2786 | 0 | 0 | 1 | 0.45574 | 1 | 8.0457e-06 | 836.9413 |  |  |  |  | 16.4403 | 730.7745 | 1.5774 | 0.0067338 | 8.0457e-06 | 0 | 0 | {7CF27098-3028-4D6C-96BA-430FB7E80045} | 13911101 | WILLOW PASS 1101 | circuit_breaker | 38.0248 | -121.9613 | WILLOW PASS 1101circuit_breaker | 145 | 535 | 36191.3938 | 11299.6182 | 24891.7756 | 2388.9792 | 82.0953 | 8.0457e-06 | 8.0457e-06 |  | 1 | 2811 | 0.0067338 | 944 | 0 | 0 | 1.4844 | 2891 | 0
Central Valley | 1490 | 151 | 238.2489 | 590 | 384.7947 | 182 | 3.846e-05 | 156.611 | 14.4906 | 2103.1751 | 15941.7151 | 436.3623 | 5.7309 | 306.6802 | 1.4931 | 0.0067166 | 0.00027406 | 0.25593 | 0.61916 | {04098A19-988D-4276-8D0E-8060BEC56ABE} | 163451702 | FROGTOWN 1702 | 1573 | 38.0465 | -120.63 | FROGTOWN 17021573 | 162 | 166 | 46234.1126 | 28787.0124 | 17447.1002 | 28787.0124 | 17447.1002 | 0.049878 | 0.0069998 | 1.5778 | 3.2418 | 1191 | 1.2224 | 945 | 0 | 0 | 17.8874 | 1800 | 0
Central Valley | 5192 | 16 | 32.1238 | 260 | 95.5912 | 87 | 2.1958e-05 | 321.3073 | 26.6392 | 5148.6259 | 32056.1826 | 1069.3103 | 12.8843 | 492.7963 | 1.4998 | 0.0067157 | 0.0002727 | 0.061538 | 0.33605 | {8E69B2F0-EC1C-4178-9E4E-64B5D7938362} | 163451702 | FROGTOWN 1702 | 7108 | 37.9743 | -120.6588 | FROGTOWN 17027108 | 119 | 79 | 26985.9929 | 20569.8382 | 6416.1547 | 14176.7324 | 2638.8954 | 0.023725 | 0.0019104 | 2.0077 | 2.9885 | 1194 | 0.58426 | 946 | 0 | 0 | 8.809 | 588 | 0
Sierra | 9374 | 0 | 0 | 12 | 2.5609 | 11 | 1.8059e-05 | 372.4789 | 10.838 | 6285.4323 | 40014.0396 | 439.1103 | 3.5026 | 1467.6605 | 1.7637 | 0.0067153 | 8.0665e-05 | 0 | 0 | {522A389A-AB26-4856-B015-C925A695BEA6} | 63172101 | MADISON 2101 | 13372 | 38.7946 | -122.0621 | MADISON 210113372 | 7 | 13 | 6530.1023 | 6130.2461 | 399.8562 | 6078.9039 | 373.0647 | 0.00088732 | 0.00019865 |  | 1.0909 | 1977 | 0.073868 | 947 | 0 | 0 | 3.7773 | 2 | 0
Central Valley | 8880 | 25 | 48.6244 | 240 | 120.4706 | 102 | 3.4804e-05 | 226.9765 | 15.9577 | 2506.2778 | 18275.7091 | 646.4602 | 12.6655 | 1290.0257 | 1.7784 | 0.0067128 | 0.00025896 | 0.10417 | 0.40362 | {5DA2A1D7-0688-4867-AAF9-609471332BF9} | 254432104 | COARSEGOLD 2104 | 5516 | 37.2282 | -119.8706 | COARSEGOLD 21045516 | 117 | 125 | 45926.549 | 29689.925 | 16236.624 | 29689.925 | 16236.624 | 0.026414 | 0.00355 | 1.945 | 2.3529 | 1230 | 0.6847 | 948 | 0 | 0 | 18.4485 | 2112 | 0
Central Valley | 4541 | 23 | 33.7072 | 135 | 84.6913 | 26 | 0.00014761 | 48.5545 | 75.1419 | 910.4151 | 15825.2241 | 3560.7697 | 1.2612 | 10.7381 | 1.013 | 0.0067088 | 0.0048535 | 0.17037 | 0.398 | {10618A90-ED86-44CD-8B76-773E3BF2AE42} | 163201101 | WEST POINT 1101 | 12256 | 38.4438 | -120.5087 | WEST POINT 110112256 | 172 | 260 | 22317.18 | 10485.7942 | 11831.3858 | 10485.7942 | 11831.3858 | 0.12619 | 0.0038378 | 1.4655 | 5.1923 | 38 | 0.17443 | 949 | 0 | 0 | 6.5156 | 2048 | 0
North Valley | 1751 | 105 | 150.2791 | 263 | 225.1261 | 107 | 4.351e-05 | 229.5468 | 9.1825 | 1585.0189 | 32189.1669 | 573.8515 | 0.14732 | 227.1607 | 1.4428 | 0.0066952 | 0.00032166 | 0.39924 | 0.66753 | {107EABE7-3B5B-4826-B3E5-C69B941080D5} | 102211101 | BUCKS CREEK 1101 | circuit_breaker | 39.9114 | -121.3271 | BUCKS CREEK 1101circuit_breaker | 68 | 34 | 32196.4584 | 31149.9295 | 1046.5289 | 31149.9295 | 1046.5289 | 0.034417 | 0.0046556 | 1.4312 | 2.4579 | 1070 | 0.71638 | 950 | 0 | 0 | 19.3557 | 1190 | 0
Central Valley | 4890 | 130 | 263.152 | 547 | 396.2168 | 150 | 4.414e-05 | 108.4751 | 11.7538 | 1279.4315 | 8995.1437 | 212.472 | 4.5839 | 256.5671 | 1.5226 | 0.0066901 | 0.00021373 | 0.23766 | 0.66416 | {C6F5EE82-3D4A-4852-9595-AF1157128635} | 163451702 | FROGTOWN 1702 | 8482 | 38.0749 | -120.5687 | FROGTOWN 17028482 | 139 | 140 | 34353.058 | 23167.7877 | 11185.2703 | 23167.7877 | 11185.2703 | 0.032059 | 0.0066211 | 2.0242 | 3.6467 | 1371 | 1.0035 | 951 | 0 | 0 | 14.3958 | 2287 | 0
North Coast | 5113 | 33 | 50.0525 | 48 | 58.9854 | 7 | 5.644e-05 | 85.847 | 0.70538 | 15.3963 | 138.4902 | 0.3754 | 2.0831 | 143.0905 | 1.0613 | 0.0066751 | 4.76e-05 | 0.6875 | 0.84856 | {AA2E97C7-3759-4D9E-BC19-D9ED237F5DA1} | 42751111 | FITCH MOUNTAIN 1111 | circuit_breaker | 38.6065 | -122.8528 | FITCH MOUNTAIN 1111circuit_breaker | 331 | 472 | 59720.9361 | 28044.9802 | 31675.9559 | 486.7283 | 1187.0121 | 0.0003332 | 0.00039508 | 1.5167 | 6.8571 | 2253 | 0.046726 | 952 | 0 | 0 | 0.30244 | 1220 | 0
Central Coast | 3525 | 346 | 665.1856 | 2032 | 1713.9719 | 344 | 5.5276e-05 | 131.2503 | 3.4676 | 381.3619 | 2071.8168 | 15.4528 | 5.7401 | 209.4215 | 1.1976 | 0.006672 | 0.0001096 | 0.17028 | 0.3881 | {D0FCA825-EE19-45C5-82C2-01947841A1DF} | 182671108 | SANTA MARIA 1108 | M80 | 35.0164 | -120.3591 | SANTA MARIA 1108M80 | 470 | 429 | 137837.0158 | 94108.6643 | 43728.3514 | 94108.6643 | 43728.3514 | 0.037701 | 0.019015 | 1.9225 | 5.907 | 1804 | 2.2952 | 953 | 0 | 0 | 58.4764 | 2371 | 0
Central Coast | 4203 | 209 | 414.4469 | 1211 | 1016.4069 | 164 | 3.3802e-05 | 477.132 | 14.2351 | 418.0818 | 2237.2947 | 60.9252 | 9.7444 | 252.8701 | 1.1866 | 0.0066719 | 0.00021623 | 0.17258 | 0.40776 | {C5AAF8EB-A62D-4527-870A-FE6B41EEDAF4} | 182821101 | MESA 1101 | 6111 | 35.0643 | -120.4971 | MESA 11016111 | 250 | 225 | 59762.5242 | 41196.8537 | 18565.6705 | 37685.5687 | 17769.4909 | 0.035462 | 0.0055435 | 1.983 | 7.3841 | 1356 | 1.0942 | 954 | 0 | 0 | 23.4167 | 1582 | 0
North Coast | 1530 | 103 | 129.7654 | 135 | 143.6913 | 20 | 9.264e-05 | 79.7832 | 11.5778 | 117.0231 | 1248.5203 | 22.7237 | 3.9815 | 40.4169 | 1.171 | 0.006661 | 0.00068177 | 0.76296 | 0.90308 | {E40AF6DD-8BB8-44B0-9133-5EE5D793A9BC} | 42251101 | HOPLAND 1101 | 80620 | 38.9943 | -123.1181 | HOPLAND 110180620 | 62 | 69 | 14826.9531 | 9040.9556 | 5785.9974 | 1849.3413 | 2703.3724 | 0.013635 | 0.0018528 | 1.2599 | 6.75 | 586 | 0.13322 | 955 | 0 | 0 | 1.1491 | 1138 | 0
North Coast | 6920 | 1747 | 1886.0665 | 2410 | 2196.1519 | 319 | 0.00012959 | 51.1189 | 1.3014 | 95.4374 | 927.5278 | 5.1828 | 0.56195 | 33.0488 | 1.116 | 0.006654 | 0.00014652 | 0.7249 | 0.85881 | {8F7144B3-988A-433A-A6F7-A1F0E4529E41} | 192411101 | LOW GAP 1101 | 4160 | 40.4272 | -123.481 | LOW GAP 11014160 | 283 | 250 | 39514.7953 | 34991.7062 | 4523.0891 | 34571.9467 | 4492.3741 | 0.046739 | 0.041339 | 1.0796 | 7.5549 | 1612 | 2.1226 | 956 | 0 | 0 | 21.482 | 1744 | 0
North Coast | 4735 | 499 | 672.1137 | 939 | 916.1895 | 99 | 0.0001071 | 69.2926 | 4.9372 | 34.6206 | 247.1726 | 3.985 | 1.2985 | 18.3445 | 1.0502 | 0.0066003 | 0.0003008 | 0.53142 | 0.7336 | {D51477E9-479D-4F9C-8092-33C149C77422} | 43071101 | DUNBAR 1101 | 79086 | 38.4096 | -122.5436 | DUNBAR 110179086 | 130 | 198 | 22874.2109 | 11168.1456 | 11706.0653 | 10550.9054 | 11637.5898 | 0.029779 | 0.010603 | 1.3469 | 9.4848 | 1122 | 0.65343 | 957 | 0 | 0 | 6.556 | 50 | 0
North Valley | 5080 | 18 | 23.1024 | 180 | 82.6271 | 22 | 6.3934e-05 | 81.4628 | 15.1252 | 2127.642 | 16071.6382 | 340.7826 | 3.2327 | 545.3515 | 1.5352 | 0.0065807 | 0.00049778 | 0.1 | 0.2796 | {34779DE5-8611-43F9-82BD-96A7D918E1B2} | 102541101 | VOLTA 1101 | 1568 | 40.4583 | -121.8673 | VOLTA 11011568 | 145 | 112 | 44205.3868 | 36682.0507 | 7523.3361 | 36682.0507 | 7523.3361 | 0.010951 | 0.0014065 | 1.2835 | 8.1818 | 790 | 0.14477 | 958 | 0 | 0 | 22.7932 | 914 | 0
Bay Area | 5980 | 305 | 533.4719 | 756 | 758.5109 | 136 | 4.5715e-05 | 135.3243 | 3.6982 | 865.7277 | 12984.7601 | 131.905 | 0.94679 | 119.3237 | 1.355 | 0.0065659 | 8.7146e-05 | 0.40344 | 0.70331 | {6F11C840-A229-4E10-BAF7-56043B23CA9B} | 43051101 | MONTICELLO 1101 | 93384 | 38.4789 | -122.1867 | MONTICELLO 110193384 | 109 | 99 | 33731.271 | 27868.9866 | 5862.2844 | 25527.468 | 4383.3043 | 0.011852 | 0.0062173 | 1.7491 | 5.5588 | 1930 | 0.89297 | 959 | 0 | 0 | 15.862 | 2578 | 0
North Coast | 1003 | 71 | 99.3522 | 113 | 116.4172 | 20 | 6.2935e-05 | 104.8731 | 3.2354 | 290.6404 | 3164.0954 | 22.7468 | 2.9451 | 65.5012 | 1.1174 | 0.0065233 | 8.8617e-05 | 0.62832 | 0.85342 | {2D9FE14A-68D2-46A5-B4CD-1EF83FC0FBCE} | 42771114 | UKIAH 1114 | 822 | 39.1182 | -123.1943 | UKIAH 1114822 | 250 | 402 | 42913.467 | 22663.2714 | 20250.1955 | 3178.5328 | 2374.3329 | 0.0017723 | 0.0012587 | 1.3993 | 5.65 | 1922 | 0.13047 | 960 | 0 | 0 | 1.975 | 1664 | 0
Sierra | 786 | 1746 | 2576.6749 | 4493 | 3918.711 | 551 | 8.6156e-05 | 116.936 | 47.7548 | 826.8587 | 10005.5041 | 944.0563 | 5.7038 | 85.7722 | 1.2112 | 0.0064873 | 0.0019406 | 0.3886 | 0.65753 | {F3B439DF-7706-4C2F-8999-BCA70EF18266} | 153132102 | NARROWS 2102 | 48484 | 39.2544 | -121.1459 | NARROWS 210248484 | 691 | 651 | 118003.1571 | 66722.6758 | 51280.4812 | 66722.6758 | 51280.4812 | 1.0693 | 0.047472 | 1.4758 | 8.1543 | 181 | 3.5745 | 961 | 0 | 0 | 41.4595 | 172 | 0
Central Coast | 4630 | 57 | 80.4 | 388 | 287.4415 | 85 | 3.2406e-05 | 420.9646 | 1.7623 | 54.1328 | 211.513 | 1.3529 | 7.8868 | 261.2987 | 1.2613 | 0.006454 | 3.6625e-05 | 0.14691 | 0.27971 | {3D2C3694-7F26-47C8-A8D1-149DBF4B8BEA} | 182601104 | OCEANO 1104 | Q12 | 35.1396 | -120.5208 | OCEANO 1104Q12 | 172 | 179 | 43273.232 | 25898.4468 | 17374.7852 | 16245.9078 | 12149.0705 | 0.0031131 | 0.0027545 | 1.4105 | 4.5647 | 2379 | 0.54859 | 962 | 0 | 0 | 10.0947 | 251 | 0
North Valley | 6804 | 666 | 874.309 | 929 | 1011.5701 | 93 | 0.00015593 | 38.4222 | 14.0666 | 975.9594 | 17072.3447 | 456.8565 | 1.8956 | 30.274 | 1.0586 | 0.0064424 | 0.0010094 | 0.7169 | 0.86431 | {EAAD5F12-9AE3-4341-A497-B18C1046E2B5} | 103271101 | ANTLER 1101 | 1612 | 40.8916 | -122.3765 | ANTLER 11011612 | 129 | 112 | 19036.0064 | 14853.5972 | 4182.4092 | 14104.292 | 4182.4092 | 0.093871 | 0.014502 | 1.3128 | 9.9892 | 408 | 0.59914 | 963 | 0 | 0 | 8.764 | 767 | 0
Bay Area | 74 | 353 | 690.1697 | 979 | 1051.7717 | 60 | 8.1011e-05 | 73.7756 | 2.5695 | 5.0304 | 39.4925 | 0.98957 | 0.59001 | 3.6183 | 0.98853 | 0.0064415 | 0.00013929 | 0.36057 | 0.6562 | {84CE664B-0611-4200-83BA-04B0E42A1B56} | 42031124 | ALTO 1124 | 428 | 37.9069 | -122.5437 | ALTO 1124428 | 164 | 683 | 41570.626 | 9441.0665 | 32129.5595 | 6700.9234 | 19121.2519 | 0.0083576 | 0.0048606 | 1.9552 | 16.3167 | 1634 | 0.38649 | 964 | 0 | 0 | 4.1638 | 1949 | 0
North Coast | 999 | 49 | 68.0908 | 108 | 90.5028 | 18 | 3.6937e-05 | 232.7009 | 2.4326 | 238.3234 | 1276.2525 | 6.7217 | 4.2565 | 338.6219 | 1.2357 | 0.0064187 | 5.5077e-05 | 0.4537 | 0.75236 | {D2D369CA-0917-4B7E-9B23-ECC7D27E5D79} | 42251101 | HOPLAND 1101 | 770 | 38.978 | -123.0986 | HOPLAND 1101770 | 133 | 84 | 26404.6199 | 21887.414 | 4517.2059 | 7603.6292 | 1757.7495 | 0.00099139 | 0.00066487 | 1.3896 | 6 | 2190 | 0.11554 | 965 | 0 | 0 | 4.7247 | 1210 | 0
Central Valley | 4411 | 63 | 161.9817 | 367 | 237.049 | 158 | 2.5904e-05 | 237.5477 | 20.5859 | 1197.467 | 5750.1696 | 207.9949 | 8.4843 | 112.416 | 1.0888 | 0.006408 | 0.0002415 | 0.17166 | 0.68333 | {9E750160-198E-4DE4-9B67-A39CCFF98BD9} | 252811102 | MERCED FALLS 1102 | 85002 | 37.6444 | -120.3123 | MERCED FALLS 110285002 | 548 | 572 | 98412.904 | 57333.7596 | 41079.1443 | 57333.7596 | 41079.1443 | 0.038157 | 0.0040929 | 2.5711 | 2.3228 | 1273 | 1.0125 | 966 | 0 | 0 | 35.6255 | 1807 | 0
North Coast | 3793 | 1592 | 2067.4849 | 2760 | 2714.5906 | 286 | 9.5507e-05 | 64.4555 | 5.4128 | 217.4786 | 2925.7603 | 77.8023 | 1.1608 | 33.7805 | 1.1015 | 0.0063917 | 0.00029221 | 0.57681 | 0.76162 | {6A5817A5-7FC3-45B7-8DC9-2BBA0FD82034} | 43321103 | RINCON 1103 | 474 | 38.5056 | -122.646 | RINCON 1103474 | 207 | 222 | 52918.1401 | 29554.6121 | 23363.528 | 29554.6121 | 23363.528 | 0.083572 | 0.027315 | 1.2987 | 9.6503 | 1146 | 1.828 | 967 | 0 | 0 | 18.3644 | 2462 | 0
Central Coast | 2794 | 42 | 97.6163 | 262 | 212.1581 | 36 | 2.3696e-05 | 318.3223 | 26.1501 | 42.2268 | 156.5673 | 7.8935 | 8.125 | 200.9337 | 1.2313 | 0.0063809 | 0.00015083 | 0.16031 | 0.46011 | {AD6746AA-B778-4E12-B7CD-DBCB8C9B3412} | 182631101 | SAN LUIS OBISPO 1101 | circuit_breaker | 35.2615 | -120.6349 | SAN LUIS OBISPO 1101circuit_breaker | 161 | 556 | 38860.1952 | 10872.4454 | 27987.7497 | 5333.7243 | 8927.6571 | 0.00543 | 0.00085305 | 2.3242 | 7.2778 | 1587 | 0.22971 | 968 | 0 | 0 | 3.3142 | 2674 | 0
Central Coast | 2591 | 1005 | 1752.7482 | 3969 | 3611.0933 | 495 | 6.6435e-05 | 178.0072 | 15.4859 | 52.2491 | 187.2399 | 7.1039 | 11.4087 | 45.7332 | 1.1891 | 0.006368 | 0.00053272 | 0.25321 | 0.48538 | {B94710C5-B1CB-42E6-AC57-91B01B723998} | 183052111 | TEMPLETON 2111 | A66 | 35.5213 | -120.7126 | TEMPLETON 2111A66 | 682 | 773 | 101958.408 | 54317.8357 | 47640.5724 | 54317.8357 | 47640.5724 | 0.2637 | 0.032885 | 1.744 | 8.0182 | 755 | 3.1522 | 969 | 0 | 0 | 33.7515 | 2334 | 0
Sierra | 3166 | 993 | 1540.1416 | 4843 | 3237.9116 | 680 | 9.5836e-05 | 66.4337 | 21.2453 | 378.1359 | 3739.3576 | 157.2397 | 3.9359 | 100.7114 | 1.2033 | 0.0063679 | 0.0010132 | 0.20504 | 0.47566 | {FB182C0F-B71E-4B89-801E-E64DB8A5CDBB} | 153662102 | APPLE HILL 2102 | 186912 | 38.641 | -120.7043 | APPLE HILL 2102186912 | 717 | 789 | 138854.3015 | 81658.6951 | 57195.6064 | 78311.5629 | 56097.4344 | 0.68896 | 0.065168 | 1.551 | 7.1221 | 405 | 4.3301 | 970 | 0 | 0 | 48.6605 | 1238 | 0
North Coast | 276 | 92 | 165.6868 | 185 | 213.1244 | 35 | 6.805e-05 | 109.6584 | 1.8539 | 90.9054 | 2097.5086 | 35.4625 | 3.3081 | 59.8531 | 1.1761 | 0.0063559 | 0.00010535 | 0.4973 | 0.77742 | {69EA27A3-0D2B-4A2D-A229-63A3090F6AF6} | 42891101 | GEYSERVILLE 1101 | 122 | 38.7347 | -122.9441 | GEYSERVILLE 1101122 | 226 | 214 | 51090.5345 | 30286.4801 | 20804.0544 | 7052.0878 | 5557.9441 | 0.0036871 | 0.0023817 | 1.8009 | 5.2857 | 1831 | 0.22246 | 971 | 0 | 0 | 4.382 | 2021 | 0
North Coast | 842 | 0 | 0 | 8 | 2.8432 | 3 | 4.7403e-05 | 142.7293 | 0.14645 | 2.9685 | 18.1673 | 0.018734 | 2.4867 | 18.436 | 1.0634 | 0.0063204 | 3.4311e-05 | 0 | 0 | {989A9D45-A06C-4EF7-99F0-5A8D5A73FF7C} | 42721103 | SONOMA 1103 | 418 | 38.2916 | -122.4548 | SONOMA 1103418 | 230 | 591 | 36885.6166 | 9496.5275 | 27389.0891 | 326.2189 | 85.0245 | 0.00010293 | 0.00014221 |  | 2.6667 | 2410 | 0.018961 | 972 | 0 | 0 | 0.2027 | 945 | 0
North Coast | 5725 | 99 | 325.4077 | 214 | 385.5019 | 24 | 5.6002e-05 | 107.2735 | 14.3914 | 138.5329 | 529.3026 | 15.3281 | 19.3454 | 67.3931 | 1.0303 | 0.006314 | 0.00028361 | 0.46262 | 0.84411 | {7C56E936-196E-400D-91F9-D03DA82672AE} | 42271102 | COTATI 1102 | 260 | 38.314 | -122.6938 | COTATI 1102260 | 113 | 204 | 21926.0301 | 9537.0372 | 12388.9929 | 4171.7031 | 2862.4822 | 0.0068067 | 0.001344 | 3.2869 | 8.9167 | 1163 | 0.15154 | 973 | 0 | 0 | 2.5922 | 2400 | 0
North Coast | 1283 | 915 | 1144.8808 | 1631 | 1569.1248 | 168 | 8.7974e-05 | 69.6216 | 8.6031 | 224.4627 | 2556.2591 | 47.3659 | 1.235 | 37.6369 | 1.1668 | 0.0062707 | 0.0003811 | 0.56101 | 0.72963 | {CDD6FD47-53A2-4B6C-945C-140CC31348B2} | 43321101 | RINCON 1101 | 578 | 38.4587 | -122.6337 | RINCON 1101578 | 249 | 246 | 48550.6523 | 30007.9481 | 18542.7041 | 27632.8586 | 15162.62 | 0.064025 | 0.01478 | 1.2512 | 9.7083 | 965 | 1.0535 | 974 | 0 | 0 | 17.1703 | 1026 | 0
Central Valley | 7927 | 121 | 206.6584 | 352 | 301.6769 | 37 | 0.00011056 | 64.3979 | 5.9877 | 8.4603 | 32.8955 | 0.42299 | 6.1678 | 52.0169 | 1.1761 | 0.0062471 | 0.000305 | 0.34375 | 0.68503 | {5171DE14-7E8C-4AB0-AFB6-B769B1D84873} | 163781705 | PEORIA 1705 | 999 | 37.9614 | -120.4177 | PEORIA 1705999 | 33 | 78 | 8817.1915 | 3715.0604 | 5102.1311 | 3715.0604 | 5102.1311 | 0.011285 | 0.0040908 | 1.7079 | 9.5135 | 1109 | 0.23114 | 975 | 0 | 0 | 2.3084 | 1637 | 0
Central Valley | 3755 | 2 | 1.9445 | 3 | 2.4002 | 1 | 1.8413e-05 | 338.4274 |  |  |  |  | 9.8982 | 2137.8477 | 1.8473 | 0.0062313 | 1.8413e-05 | 0.66667 | 0.81013 | {0ED60982-9EAF-4A20-AAB0-618C5740E1E9} | 252341112 | REEDLEY 1112 | 7240 | 36.6254 | -119.3048 | REEDLEY 11127240 | 338 | 333 | 57776.7368 | 43589.6697 | 14187.067 | 1451.4793 | 294.5902 | 1.8413e-05 | 1.8413e-05 | 0.97225 | 3 | 2640 | 0.0062313 | 976 | 0 | 0 | 0.90191 | 1957 | 0
Central Valley | 5363 | 192 | 257.7257 | 395 | 348.076 | 59 | 0.00010464 | 58.9196 | 186.1764 | 2377.3152 | 40124.2322 | 14609.7355 | 1.5509 | 54.9857 | 1.147 | 0.006231 | 0.0080817 | 0.48608 | 0.74043 | {2513FD67-0D09-4828-9017-8366EEBFD1A3} | 163201102 | WEST POINT 1102 | 1305 | 38.4009 | -120.5045 | WEST POINT 11021305 | 134 | 121 | 24858.4685 | 18286.9662 | 6571.5023 | 18286.9662 | 6571.5023 | 0.47682 | 0.006174 | 1.3423 | 6.6949 | 17 | 0.36763 | 977 | 0 | 0 | 11.363 | 38 | 0
North Valley | 1846 | 219 | 346.8087 | 678 | 521.5817 | 109 | 0.00010756 | 77.5689 | 43.7998 | 413.6006 | 5207.1506 | 923.794 | 5.8365 | 58.3565 | 1.2336 | 0.0062118 | 0.0027532 | 0.32301 | 0.66492 | {94370961-147A-42F3-9849-8A0C21F665DA} | 103441101 | JESSUP 1101 | 9002 | 40.4719 | -122.3331 | JESSUP 11019002 | 334 | 416 | 45146.4456 | 24293.3556 | 20853.0899 | 12312.9538 | 11684.2663 | 0.3001 | 0.011725 | 1.5836 | 6.2202 | 115 | 0.67709 | 978 | 0 | 0 | 7.6509 | 511 | 0
Central Valley | 6095 | 150 | 197.414 | 342 | 297.0631 | 56 | 0.00010708 | 56.9889 | 130.6917 | 1943.5462 | 33815.6016 | 8909.6531 | 1.0782 | 19.5633 | 1.0345 | 0.0061987 | 0.0074421 | 0.4386 | 0.66455 | {C67356BD-8CAD-4F56-A2F4-79BA30858021} | 163201102 | WEST POINT 1102 | 1303 | 38.4044 | -120.5058 | WEST POINT 11021303 | 204 | 274 | 42414.8318 | 25499.4036 | 16915.4282 | 25499.4036 | 16915.4282 | 0.41676 | 0.0059964 | 1.3161 | 6.1071 | 20 | 0.34713 | 979 | 0 | 0 | 15.8446 | 625 | 0
North Coast | 9321 | 70 | 124.5484 | 81 | 129.5615 | 18 | 0.00015263 | 41.0026 | 10.4282 | 813.2906 | 19529.7192 | 592.4063 | 0.029376 | 37.7531 | 1.3153 | 0.0061911 | 0.00064311 | 0.8642 | 0.96131 | {E5474BC9-1FBC-47D7-924C-371BAFB1C79B} | 192171102 | WILLOW CREEK 1102 | 37374 | 40.9887 | -123.6397 | WILLOW CREEK 110237374 | 6 | 1 | 2060.1155 | 2046.1835 | 13.932 | 2046.1835 | 13.932 | 0.011576 | 0.0027473 | 1.7793 | 4.5 | 623 | 0.11144 | 980 | 0 | 0 | 1.2714 | 784 | 0
North Coast | 2170 | 1 | 1.2277 | 4 | 1.8679 | 3 | 2.73e-05 | 223.0871 | 10.269 | 176.1364 | 1279.8713 | 13.143 | 15.6158 | 209.0047 | 1.6209 | 0.0061911 | 0.00012407 | 0.25 | 0.65725 | {D546C25E-2665-4E0F-83E6-19A6D0D70A7D} | 43302103 | MONROE 2103 | circuit_breaker | 38.4531 | -122.7437 | MONROE 2103circuit_breaker | 544 | 611 | 49029.0217 | 23628.7455 | 25400.2762 | 674.1153 | 230.8668 | 0.00037222 | 8.1899e-05 | 1.2277 | 1.3333 | 1732 | 0.018573 | 981 | 0 | 0 | 0.41888 | 1255 | 0
Central Coast | 1083 | 41 | 126.5191 | 69 | 140.5723 | 23 | 2.1796e-05 | 263.3347 |  |  |  |  | 9.669 | 157.7495 | 1.1898 | 0.0061563 | 2.1796e-05 | 0.5942 | 0.90003 | {450C95A5-CC86-42A5-8643-E83181385ECD} | 83531107 | MC KEE 1107 | XR010 | 37.3857 | -121.813 | MC KEE 1107XR010 | 292 | 405 | 45816.0465 | 21796.6657 | 24019.3808 | 4483.0278 | 3749.8513 | 0.00050131 | 0.00050131 | 3.0858 | 3 | 2579 | 0.1416 | 982 | 0 | 0 | 2.7856 | 2450 | 0
Central Coast | 7256 | 523 | 957.3015 | 3075 | 2364.314 | 382 | 5.5369e-05 | 155.1925 | 3.5941 | 39.1097 | 180.837 | 1.4064 | 5.8864 | 47.1806 | 1.1332 | 0.0061114 | 0.00010882 | 0.17008 | 0.4049 | {850B41E6-E885-4F34-842C-9B877CC07C7A} | 182541103 | ATASCADERO 1103 | A06 | 35.4634 | -120.6701 | ATASCADERO 1103A06 | 521 | 510 | 94076.5338 | 60068.7168 | 34007.817 | 56511.8674 | 29845.8269 | 0.041571 | 0.021151 | 1.8304 | 8.0497 | 1809 | 2.3346 | 983 | 0 | 0 | 35.1148 | 2019 | 0
Central Valley | 4877 | 8 | 18.1282 | 36 | 28.2029 | 12 | 4.6247e-05 | 139.6325 | 12.7287 | 757.2717 | 4744.289 | 206.4932 | 9.9491 | 173.9831 | 2.226 | 0.0060995 | 0.00036111 | 0.22222 | 0.64278 | {4DC1CEF2-A050-43F8-AD47-CFA46D056F9F} | 163011103 | MARTELL 1103 | circuit_breaker | 38.369 | -120.7967 | MARTELL 1103circuit_breaker | 185 | 317 | 20672.2648 | 10088.6649 | 10583.5999 | 1549.4828 | 442.4965 | 0.0043334 | 0.00055497 | 2.266 | 3 | 995 | 0.073194 | 984 | 0 | 0 | 0.9628 | 1620 | 0
North Valley | 899 | 221 | 440.4011 | 1088 | 696.0943 | 98 | 6.5677e-05 | 95.4919 | 6.5045 | 42.3624 | 172.3241 | 2.1689 | 6.994 | 51.2612 | 1.1137 | 0.0060958 | 0.00025876 | 0.20312 | 0.63267 | {C09D41C2-6107-4911-B847-897C1DB6C91E} | 102911105 | WYANDOTTE 1105 | 329930 | 39.5184 | -121.5401 | WYANDOTTE 1105329930 | 217 | 455 | 35662.1174 | 16828.9727 | 18833.1447 | 9878.9278 | 6996.558 | 0.025359 | 0.0064363 | 1.9928 | 11.102 | 1231 | 0.59739 | 985 | 0 | 0 | 6.1385 | 1149 | 0
Central Valley | 861 | 413 | 746.7921 | 2117 | 1266.0452 | 443 | 4.0394e-05 | 177.1827 | 13.6171 | 2970.1932 | 23373.0003 | 616.5851 | 7.722 | 300.4605 | 1.3802 | 0.0060605 | 0.00028288 | 0.19509 | 0.58986 | {169946F8-2E71-42DA-9D83-785B4AD4F476} | 163451702 | FROGTOWN 1702 | 75252 | 38.0522 | -120.6226 | FROGTOWN 170275252 | 480 | 446 | 131378.6154 | 97052.7173 | 34325.8981 | 90444.8522 | 29293.955 | 0.12532 | 0.017895 | 1.8082 | 4.7788 | 1167 | 2.6848 | 986 | 0 | 0 | 56.1998 | 2691 | 0
Central Valley | 2624 | 549 | 877.6025 | 2258 | 1503.0796 | 406 | 5.1699e-05 | 113.0448 | 12.2953 | 229.7914 | 1297.7472 | 32.6436 | 3.0576 | 96.9017 | 1.2787 | 0.0060603 | 0.00029073 | 0.24314 | 0.58387 | {6471EAF8-C6B2-4BBF-898D-F4AC5320ACCB} | 163451702 | FROGTOWN 1702 | 12282 | 38.088 | -120.5377 | FROGTOWN 170212282 | 365 | 487 | 84660.5535 | 58310.0701 | 26350.4834 | 58310.0701 | 26350.4834 | 0.11804 | 0.02099 | 1.5985 | 5.5616 | 1150 | 2.4605 | 987 | 0 | 0 | 36.2322 | 724 | 0
Sierra | 1076 | 2192 | 3303.1309 | 5571 | 4707.954 | 603 | 8.8395e-05 | 91.3974 | 8.4304 | 105.7646 | 973.3517 | 42.2467 | 4.5598 | 62.4508 | 1.138 | 0.006038 | 0.00038386 | 0.39347 | 0.70161 | {42C0044E-B495-4983-9439-0351AC9E28F8} | 152691103 | HIGGINS 1103 | 32120 | 39.1048 | -121.0851 | HIGGINS 110332120 | 799 | 977 | 127000.5581 | 65714.7916 | 61285.7665 | 64628.4099 | 60411.0579 | 0.23147 | 0.053302 | 1.5069 | 9.2388 | 963 | 3.6409 | 988 | 0 | 0 | 40.1582 | 1372 | 0
Sierra | 539 | 1285 | 2314.2055 | 5232 | 3882.1667 | 570 | 0.0001354 | 50.2054 | 15.0626 | 151.3299 | 964.0837 | 34.5415 | 4.544 | 97.9586 | 1.1711 | 0.005999 | 0.00095428 | 0.2456 | 0.59611 | {3C509C6A-BB81-43C3-A023-21038DF3E84A} | 153652110 | SHINGLE SPRINGS 2110 | 7742 | 38.6615 | -120.911 | SHINGLE SPRINGS 21107742 | 748 | 756 | 125290.8053 | 73601.743 | 51689.0623 | 73513.8191 | 51584.5207 | 0.54394 | 0.077177 | 1.8009 | 9.1789 | 433 | 3.4194 | 989 | 0 | 0 | 45.6794 | 517 | 0
Sierra | 142 | 833 | 952.4616 | 1831 | 1444.0771 | 165 | 9.4039e-05 | 59.8857 | 124.1436 | 2373.5006 | 51880.9234 | 13527.9699 | 0.38516 | 18.0499 | 1.03 | 0.0059963 | 0.0057807 | 0.45494 | 0.65956 | {362CB776-12CD-4A6D-89F4-5301B9D37C1F} | 152431102 | SHADY GLEN 1102 | 2232 | 39.1442 | -120.9082 | SHADY GLEN 11022232 | 144 | 223 | 29226.5602 | 16796.8272 | 12429.733 | 16796.8272 | 12429.733 | 0.95382 | 0.015516 | 1.1434 | 11.097 | 28 | 0.98939 | 990 | 0 | 0 | 10.4371 | 506 | 0
Central Valley | 5941 | 402 | 704.5829 | 1807 | 1259.5403 | 342 | 8.05e-05 | 45.9527 | 7.3405 | 241.6541 | 1482.3807 | 26.9578 | 4.2332 | 102.1293 | 1.2379 | 0.0059962 | 0.00030124 | 0.22247 | 0.5594 | {65DFE4A7-A5B5-488E-A5EA-F56668120457} | 162211101 | CALAVERAS CEMENT 1101 | 11188 | 38.2136 | -120.6961 | CALAVERAS CEMENT 110111188 | 439 | 681 | 84138.787 | 48300.9598 | 35837.8271 | 48300.9598 | 35837.8271 | 0.10303 | 0.027531 | 1.7527 | 5.2836 | 1120 | 2.0507 | 991 | 0 | 0 | 30.0128 | 2106 | 0
Sierra | 3260 | 1941 | 2989.0518 | 6396 | 4776.2334 | 755 | 7.2045e-05 | 88.983 | 8.1034 | 82.5015 | 666.4724 | 21.525 | 7.2223 | 65.7912 | 1.1636 | 0.0058828 | 0.00031746 | 0.30347 | 0.62582 | {94CC379D-BE20-48E1-8496-01F284C7FE9E} | 153132105 | NARROWS 2105 | 2216 | 39.1998 | -121.1729 | NARROWS 21052216 | 1016 | 1124 | 160856.7521 | 92843.3154 | 68013.4367 | 90284.175 | 66239.4 | 0.23968 | 0.054394 | 1.54 | 8.4715 | 1083 | 4.4415 | 992 | 0 | 0 | 56.1 | 1968 | 0
Sierra | 2332 | 1093 | 1602.4496 | 2340 | 2273.4478 | 286 | 9.4723e-05 | 74.5977 | 28.1442 | 450.7842 | 5090.8191 | 359.4034 | 3.8153 | 73.3395 | 1.1147 | 0.005859 | 0.0015644 | 0.46709 | 0.70485 | {B3488AFC-B0D0-44AE-ACC7-3FB60ED8C1AA} | 152031103 | GRASS VALLEY 1103 | 2110 | 39.2015 | -121.0784 | GRASS VALLEY 11032110 | 357 | 323 | 53626.717 | 32324.9618 | 21301.7552 | 31856.0669 | 20570.0712 | 0.44743 | 0.027091 | 1.4661 | 8.1818 | 234 | 1.6757 | 993 | 0 | 0 | 19.7944 | 490 | 0
Sierra | 3459 | 2 | 5.2733 | 10 | 6.9806 | 7 | 2.9488e-05 | 198.0239 | 8.9731 | 12640.458 | 130071.8984 | 1167.1472 | 6.897 | 1416.4974 | 1.6552 | 0.0058383 | 5.0961e-05 | 0.2 | 0.75543 | {911A51D5-0E8C-48D3-9524-67CE9063723E} | 63121101 | CORTINA 1101 | 302192 | 39.12 | -122.2239 | CORTINA 1101302192 | 126 | 80 | 36531.4264 | 28675.233 | 7856.1933 | 1666.8417 | 197.0824 | 0.00035673 | 0.00020641 | 2.6367 | 1.4286 | 2223 | 0.040868 | 994 | 0 | 0 | 1.0357 | 1624 | 0
North Valley | 8636 | 426 | 547.9622 | 1157 | 889.6174 | 202 | 2.4901e-05 | 186.2158 | 1.1797 | 1115.2695 | 23049.3985 | 94.8981 | 0.49877 | 99.4618 | 1.3523 | 0.0058222 | 3.4643e-05 | 0.36819 | 0.61595 | {777DE2C4-ED25-41C9-82DD-E42386BC34EE} | 102211102 | BUCKS CREEK 1102 | circuit_breaker | 39.9115 | -121.327 | BUCKS CREEK 1102circuit_breaker | 159 | 174 | 53280.1728 | 47507.7824 | 5772.3904 | 47507.7824 | 5772.3904 | 0.0069979 | 0.0050299 | 1.2863 | 5.7277 | 2404 | 1.1761 | 995 | 0 | 0 | 29.52 | 1157 | 0
Sierra | 6107 | 507 | 750.5221 | 1388 | 1161.3483 | 178 | 0.00010564 | 54.2889 | 78.1959 | 1310.174 | 19378.9863 | 4428.0703 | 7.7485 | 76.6524 | 1.1921 | 0.0058175 | 0.0038908 | 0.36527 | 0.64625 | {4065F493-7B96-40A7-8EE5-29CF10B90CA4} | 153662102 | APPLE HILL 2102 | 6552 | 38.6813 | -120.6634 | APPLE HILL 21026552 | 219 | 242 | 46694.0604 | 20150.542 | 26543.5184 | 20150.542 | 26543.5184 | 0.69256 | 0.018804 | 1.4803 | 7.7978 | 64 | 1.0355 | 996 | 0 | 0 | 12.521 | 680 | 0
North Valley | 6741 | 653 | 963.6799 | 1019 | 1165.0322 | 189 | 0.00012885 | 49.6669 | 53.5576 | 3229.6167 | 60434.8822 | 4712.0417 | 1.6241 | 53.062 | 1.1657 | 0.0057992 | 0.0033883 | 0.64082 | 0.82717 | {05EF3BA2-F04A-49CF-AF87-10424EDE6926} | 103751102 | BIG BEND 1102 | circuit_breaker | 39.6771 | -121.4917 | BIG BEND 1102circuit_breaker | 172 | 136 | 37624.4249 | 27533.9662 | 10090.4587 | 27533.9662 | 10090.4587 | 0.64039 | 0.024352 | 1.4758 | 5.3915 | 82 | 1.0961 | 997 | 0 | 0 | 17.1088 | 674 | 0
Central Valley | 4631 | 156 | 215.9429 | 445 | 343.4058 | 84 | 4.6883e-05 | 134.1305 | 12.1112 | 229.8807 | 1997.2031 | 39.5345 | 10.0855 | 335.737 | 1.6036 | 0.0057937 | 0.00028193 | 0.35056 | 0.62883 | {5FCD3F70-B3EF-41B7-B59A-4AF393BD948D} | 254432102 | COARSEGOLD 2102 | circuit_breaker | 37.2272 | -119.6902 | COARSEGOLD 2102circuit_breaker | 110 | 59 | 27338.6768 | 22592.2597 | 4746.4171 | 22592.2597 | 4746.4171 | 0.023682 | 0.0039382 | 1.3842 | 5.2976 | 1168 | 0.48667 | 998 | 0 | 0 | 14.0382 | 104 | 0
Central Coast | 4182 | 24 | 39.9105 | 57 | 60.037 | 7 | 3.5733e-05 | 190.3373 | 33.4427 | 155.1812 | 608.5769 | 33.4615 | 11.2876 | 76.4354 | 1.091 | 0.0057792 | 0.00085549 | 0.42105 | 0.66476 | {2C2A0D1B-C427-42CC-B24E-D58836D68BB9} | 83242105 | MORGAN HILL 2105 | XR494 | 37.1066 | -121.6618 | MORGAN HILL 2105XR494 | 279 | 302 | 27383.7291 | 11814.4524 | 15569.2766 | 485.8055 | 271.1166 | 0.0059884 | 0.00025013 | 1.6629 | 8.1429 | 469 | 0.040455 | 999 | 0 | 0 | 0.30187 | 2705 | 0
Bay Area | 4734 | 1382 | 2875.3162 | 1480 | 2934.3416 | 105 | 5.888e-05 | 95.4518 | 1.2725 | 57.7307 | 304.2193 | 0.83322 | 0.79857 | 25.591 | 1.1062 | 0.005751 | 6.7775e-05 | 0.93378 | 0.97988 | {31C2E01B-7B87-407B-9DC8-52C242320576} | 24251101 | WOODSIDE 1101 | 8972 | 37.4185 | -122.3224 | WOODSIDE 11018972 | 81 | 96 | 16007.339 | 9771.1957 | 6236.1433 | 9771.1957 | 6236.1433 | 0.0071164 | 0.0061824 | 2.0805 | 14.0952 | 2071 | 0.60385 | 1000 | 0 | 0 | 6.0715 | 2146 | 0
North Coast | 627 | 663 | 811.0529 | 905 | 943.5063 | 87 | 0.00013453 | 42.5347 | 10.6358 | 189.0851 | 1984.8035 | 41.6055 | 2.6891 | 38.1027 | 1.1219 | 0.005749 | 0.00080139 | 0.7326 | 0.85962 | {65E5FC7F-8C6A-45F6-95D3-74B8F1E3F473} | 42681101 | LAYTONVILLE 1101 | circuit_breaker | 39.6846 | -123.4773 | LAYTONVILLE 1101circuit_breaker | 150 | 193 | 26169.5365 | 14777.2299 | 11392.3066 | 9592.9795 | 5242.833 | 0.069721 | 0.011704 | 1.2233 | 10.4023 | 499 | 0.50016 | 1001 | 0 | 0 | 5.9608 | 1836 | 0
Central Valley | 6771 | 434 | 538.4041 | 1041 | 806.4946 | 116 | 0.00012269 | 46.4006 | 164.5351 | 1448.1546 | 29089.7323 | 12492.5306 | 0.92259 | 21.6809 | 1.0393 | 0.005746 | 0.0093048 | 0.41691 | 0.66759 | {C8B6F5A4-B7EB-4267-93EF-866DFF4F4584} | 163751102 | PINE GROVE 1102 | 35576 | 38.4176 | -120.6137 | PINE GROVE 110235576 | 102 | 95 | 17024.1828 | 12655.9114 | 4368.2714 | 12655.9114 | 4368.2714 | 1.0794 | 0.014232 | 1.2406 | 8.9741 | 11 | 0.66654 | 1002 | 0 | 0 | 7.864 | 1408 | 0
Sierra | 2292 | 3836 | 5432.2418 | 9364 | 7925.3257 | 1034 | 8.4349e-05 | 118.2063 | 38.6355 | 857.2031 | 9870.6485 | 1477.0101 | 4.1054 | 60.1421 | 1.1239 | 0.0057379 | 0.0017982 | 0.40965 | 0.68543 | {A7A5500C-8FAC-46D4-9BD4-7B5D3F1E7024} | 153082106 | PLACERVILLE 2106 | 7522 | 38.8155 | -120.8221 | PLACERVILLE 21067522 | 1138 | 1257 | 187588.8656 | 108764.9416 | 78823.924 | 108764.9416 | 78823.924 | 1.8594 | 0.087217 | 1.4161 | 9.0561 | 195 | 5.9329 | 1003 | 0 | 0 | 67.5834 | 1481 | 0
Central Coast | 5553 | 3 | 12.1472 | 28 | 28.2763 | 9 | 1.9394e-05 | 454.4231 | 5.0692 | 340.6697 | 1025.8418 | 20.7505 | 16.0887 | 405.9212 | 1.1212 | 0.005729 | 3.1646e-05 | 0.10714 | 0.42959 | {F7BA05AD-8E42-4B6D-9E07-B1C94132C1D1} | 183101103 | CABRILLO 1103 | 1437 | 34.6008 | -120.2786 | CABRILLO 11031437 | 47 | 53 | 9893.9554 | 7854.9148 | 2039.0405 | 4397.9316 | 1548.8938 | 0.00028481 | 0.00017455 | 4.0491 | 3.1111 | 2446 | 0.051561 | 1004 | 0 | 0 | 2.7327 | 2333 | 0
Bay Area | 7473 | 22 | 27.0097 | 37 | 37.2063 | 8 | 3.1558e-05 | 142.777 | 2.7383 | 67.4156 | 485.2905 | 2.8073 | 3.5777 | 100.9726 | 1.1529 | 0.0057172 | 7.022e-05 | 0.59459 | 0.72594 | {37307117-7712-4B70-890E-D9B3D42408D3} | 43292103 | PUEBLO 2103 | 694 | 38.3346 | -122.3317 | PUEBLO 2103694 | 120 | 65 | 12391.1085 | 7674.026 | 4717.0824 | 1193.6984 | 50.4458 | 0.00056176 | 0.00025246 | 1.2277 | 4.625 | 2056 | 0.045737 | 1005 | 0 | 0 | 0.74173 | 1321 | 0
Sierra | 6921 | 373 | 489.1737 | 702 | 629.3431 | 76 | 6.3006e-05 | 94.2666 | 79.9902 | 5722.063 | 146580.3899 | 16942.6568 | 0.34784 | 25.2544 | 1.0318 | 0.0056866 | 0.0028053 | 0.53134 | 0.77728 | {D7E3765B-F7D8-4BEF-8206-669D15220FDF} | 152181101 | FORESTHILL 1101 | 1820 | 39.0337 | -120.7963 | FORESTHILL 11011820 | 68 | 25 | 11268.0103 | 8970.0583 | 2297.952 | 8970.0583 | 2297.952 | 0.2132 | 0.0047885 | 1.3115 | 9.2368 | 112 | 0.43218 | 1006 | 0 | 0 | 5.5737 | 1048 | 0
North Valley | 6183 | 2 | 3.3036 | 16 | 10.5998 | 5 | 1.9056e-05 | 547.7184 | 0.27305 | 49.3513 | 177.8281 | 0.16781 | 9.3925 | 180.9886 | 1.1341 | 0.0056778 | 5.2093e-06 | 0.125 | 0.31166 | {240B9597-FDF1-4E00-A581-05E13375E11A} | 103721101 | PIT NO 1 1101 | 9702 | 41.0049 | -121.447 | PIT NO 1 11019702 | 165 | 125 | 18660.7465 | 14797.5762 | 3863.1703 | 994.3298 | 212.6304 | 2.6047e-05 | 9.5282e-05 | 1.6518 | 3.2 | 2841 | 0.028389 | 1007 | 0 | 0 | 0.61785 | 1011 | 0
Bay Area | 7139 | 634 | 1178.1825 | 1327 | 1574.2943 | 58 | 0.00011616 | 49.7128 | 1.2037 | 1.3521 | 9.1155 | 0.040727 | 0.34117 | 11.4936 | 1.064 | 0.0056595 | 0.00012529 | 0.47777 | 0.74839 | {52C6D739-68AD-4B43-8573-6FBDC1C9EC3B} | 42031124 | ALTO 1124 | 3745 | 37.9154 | -122.5534 | ALTO 11243745 | 110 | 237 | 19710.8952 | 7368.4316 | 12342.4637 | 7368.4316 | 12342.4637 | 0.0072668 | 0.0067371 | 1.8583 | 22.8793 | 1722 | 0.32825 | 1008 | 0 | 0 | 4.5785 | 2670 | 0
Central Valley | 3986 | 919 | 1228.7931 | 2152 | 1852.9088 | 232 | 0.00010314 | 55.1066 | 214.0696 | 3489.1303 | 62703.5333 | 20427.9701 | 1.9935 | 41.6149 | 1.1332 | 0.0056462 | 0.0097224 | 0.42704 | 0.66317 | {1445490F-C0B5-460E-8F6D-3B7658CD2546} | 163201102 | WEST POINT 1102 | 36676 | 38.3724 | -120.5066 | WEST POINT 110236676 | 250 | 225 | 43497.762 | 27353.6284 | 16144.1336 | 27353.6284 | 16144.1336 | 2.2556 | 0.023929 | 1.3371 | 9.2759 | 9 | 1.3099 | 1009 | 0 | 0 | 16.9968 | 1327 | 0
Central Coast | 2664 | 13 | 30.6076 | 44 | 39.1146 | 25 | 3.56e-05 | 161.173 | 0.39782 | 2626.3186 | 18488.941 | 9.3279 | 3.4091 | 2027.2155 | 1.7452 | 0.0056186 | 2.3721e-05 | 0.29545 | 0.78251 | {56A881E4-0AE5-488C-A412-AABDAC51819A} | 182562102 | CHOLAME 2102 | X10 | 35.5847 | -120.3364 | CHOLAME 2102X10 | 182 | 140 | 75645.7569 | 70786.6402 | 4859.1167 | 32569.8267 | 1821.5999 | 0.00059303 | 0.00089 | 2.3544 | 1.76 | 2547 | 0.14047 | 1010 | 0 | 0 | 20.2379 | 2320 | 0
North Coast | 4618 | 716 | 846.6686 | 1158 | 1090.3789 | 230 | 0.00010732 | 46.389 | 5.2041 | 406.939 | 3815.6452 | 27.3805 | 1.1848 | 94.0525 | 1.161 | 0.0056093 | 0.00030361 | 0.61831 | 0.77649 | {03DB1220-E098-4294-96C0-8000CD99CD41} | 42681101 | LAYTONVILLE 1101 | 402 | 39.7033 | -123.4875 | LAYTONVILLE 1101402 | 190 | 149 | 59046.9739 | 37926.2925 | 21120.6814 | 37059.5588 | 20241.7019 | 0.06983 | 0.024684 | 1.1825 | 5.0348 | 1113 | 1.2901 | 1011 | 0 | 0 | 23.0277 | 2197 | 0
Sierra | 7948 | 7 | 15.0017 | 24 | 21.6364 | 12 | 6.0961e-05 | 87.3035 | 14.6239 | 65.1566 | 285.3184 | 10.2414 | 7.3591 | 43.4299 | 1.132 | 0.0055833 | 0.00056329 | 0.29167 | 0.69335 | {D8BA1097-151A-4C27-86A3-35B90FB447B4} | 152271101 | WISE 1101 | 1404 | 38.8743 | -121.1171 | WISE 11011404 | 101 | 109 | 10988.4795 | 5668.509 | 5319.9705 | 1996.1981 | 1257.0413 | 0.0067595 | 0.00073153 | 2.1431 | 2 | 720 | 0.066999 | 1012 | 0 | 0 | 1.2404 | 243 | 0
North Coast | 5635 | 118 | 225.6037 | 255 | 286.0929 | 51 | 5.7729e-05 | 74.0692 | 3.2452 | 56.1179 | 444.5254 | 2.4724 | 4.8038 | 75.1309 | 1.1796 | 0.0055607 | 9.2964e-05 | 0.46275 | 0.78857 | {49DD2761-248F-4D1E-809D-C19E1A64F359} | 42251101 | HOPLAND 1101 | 1100 | 39.0267 | -123.133 | HOPLAND 11011100 | 94 | 133 | 20094.6484 | 10708.6266 | 9386.0218 | 4021.7261 | 6182.0039 | 0.0047412 | 0.0029442 | 1.9119 | 5 | 1890 | 0.2836 | 1013 | 0 | 0 | 2.499 | 263 | 0
North Coast | 334 | 43 | 140.8306 | 58 | 148.1114 | 19 | 6.1298e-05 | 94.0955 | 70.2625 | 728.6914 | 3951.5719 | 523.1944 | 10.067 | 45.5496 | 1.0158 | 0.0055606 | 0.0031725 | 0.74138 | 0.95084 | {052E7662-01A4-4535-9504-141A4B8BDCED} | 42271102 | COTATI 1102 | 464 | 38.3002 | -122.7116 | COTATI 1102464 | 195 | 303 | 30495.6554 | 13038.4156 | 17457.2398 | 2945.14 | 1822.1824 | 0.060278 | 0.0011647 | 3.2751 | 3.0526 | 96 | 0.10565 | 1014 | 0 | 0 | 1.83 | 1740 | 0
Bay Area | 4389 | 166 | 237.2966 | 443 | 390.7529 | 31 | 0.00010848 | 39.9533 | 1.6123 | 7.1184 | 59.0534 | 0.32452 | 0.34463 | 4.704 | 1.0114 | 0.0055603 | 0.00015459 | 0.37472 | 0.60728 | {BCC000F2-427B-4C85-BE86-EBEAE729A62B} | 43432104 | SILVERADO 2104 | circuit_breaker | 38.4999 | -122.4594 | SILVERADO 2104circuit_breaker | 196 | 379 | 24759.5043 | 8010.0912 | 16749.413 | 2560.2139 | 3388.8696 | 0.0047922 | 0.0033629 | 1.4295 | 14.2903 | 1567 | 0.17237 | 1015 | 0 | 0 | 1.5908 | 2042 | 0
North Coast | 3414 | 4059 | 6669.631 | 4233 | 6749.5317 | 370 | 0.00015984 | 34.744 | 4.3851 | 50.1572 | 657.1612 | 4.9941 | 0.81176 | 12.3712 | 1.02 | 0.0055337 | 0.00040992 | 0.95889 | 0.98816 | {5B3D2F2F-DF90-45C0-963C-1589633A1498} | 42661104 | WILLITS 1104 | 34008 | 39.4366 | -123.3893 | WILLITS 110434008 | 424 | 572 | 60308.2261 | 36886.2403 | 23421.9859 | 36886.2403 | 23421.9859 | 0.15167 | 0.05914 | 1.6432 | 11.4405 | 928 | 2.0475 | 1016 | 0 | 0 | 22.92 | 1354 | 0
Central Coast | 4643 | 1514 | 2260.0699 | 3861 | 3603.4934 | 410 | 3.5833e-05 | 226.1311 | 2.0735 | 74.0631 | 307.5962 | 3.1394 | 6.4509 | 167.6404 | 1.1731 | 0.0055194 | 4.7465e-05 | 0.39213 | 0.62719 | {27D41C21-61BA-4495-BB53-0AA4F98E2A0B} | 83242111 | MORGAN HILL 2111 | XR398 | 37.1263 | -121.7285 | MORGAN HILL 2111XR398 | 441 | 344 | 95670.7544 | 63830.0009 | 31840.7535 | 59220.7716 | 29463.2727 | 0.019461 | 0.014692 | 1.4928 | 9.4171 | 2258 | 2.263 | 1017 | 0 | 0 | 36.7981 | 2541 | 0
Central Valley | 4581 | 168 | 256.881 | 461 | 358.7177 | 92 | 1.829e-05 | 338.834 | 18.7328 | 3542.7259 | 31113.3027 | 894.9516 | 15.2267 | 866.2732 | 1.7927 | 0.0055189 | 0.00021961 | 0.36443 | 0.71611 | {29E98E36-5623-4DDD-B302-D78235AF2960} | 254061102 | DUNLAP 1102 | 7849F | 36.6937 | -119.0524 | DUNLAP 11027849F | 68 | 53 | 20673.5046 | 13949.6344 | 6723.8703 | 13949.6344 | 6723.8703 | 0.020204 | 0.0016827 | 1.5291 | 5.0109 | 1344 | 0.50774 | 1018 | 0 | 0 | 8.6679 | 1860 | 0
Sierra | 3798 | 554 | 675.5783 | 1785 | 1318.6016 | 144 | 8.9648e-05 | 69.275 | 101.5134 | 2964.1761 | 77486.1984 | 17134.5584 | 1.0712 | 23.9228 | 1.0595 | 0.0055165 | 0.0032606 | 0.31036 | 0.51234 | {EF597DB9-B0BE-45C9-ADE4-3C3FDCE717C6} | 152301101 | BONNIE NOOK 1101 | 86696 | 39.1829 | -120.8565 | BONNIE NOOK 110186696 | 143 | 168 | 28058.7328 | 15534.4182 | 12524.3147 | 15534.4182 | 12524.3147 | 0.46952 | 0.012909 | 1.2195 | 12.3958 | 86 | 0.79438 | 1019 | 0 | 0 | 9.6526 | 1376 | 0
Bay Area | 8967 | 292 | 468.3918 | 585 | 642.5397 | 30 | 0.00014576 | 37.3258 | 2.6974 | 13.9027 | 43.6622 | 0.45109 | 1.7115 | 17.0836 | 1.0353 | 0.0055157 | 0.00028029 | 0.49915 | 0.72897 | {62B0F5C5-018B-42C2-9DA1-D8CCE6714B61} | 42011108 | SAN RAFAEL 1108 | 63598 | 37.9725 | -122.6032 | SAN RAFAEL 110863598 | 44 | 70 | 6464.7024 | 3076.8023 | 3387.9002 | 3076.8023 | 3387.9002 | 0.0084087 | 0.0043729 | 1.6041 | 19.5 | 1176 | 0.16547 | 1020 | 0 | 0 | 1.9118 | 970 | 0
North Coast | 9343 | 55 | 100.3155 | 87 | 114.8565 | 15 | 8.0731e-05 | 84.5184 | 10.2586 | 20.9121 | 163.3834 | 15.3336 | 6.014 | 80.7341 | 1.1084 | 0.0054903 | 0.00037195 | 0.63218 | 0.8734 | {4CA5D300-8532-4AF9-BD85-CE58373188C7} | 43501103 |  | 701650 | 38.5636 | -122.8037 | 701650 | 27 | 11 | 1548.8036 | 1191.4526 | 357.351 | 1191.4526 | 357.351 | 0.0055792 | 0.001211 | 1.8239 | 5.8 | 981 | 0.082354 | 1021 | 0 | 0 | 0.74033 | 69 | 0
North Coast | 7780 | 280 | 377.987 | 589 | 549.5818 | 49 | 7.6859e-05 | 71.4645 | 1.9187 | 30.3965 | 468.7264 | 12.0373 | 3.037 | 23.324 | 1.056 | 0.0054807 | 9.4594e-05 | 0.47538 | 0.68777 | {BA29ADD5-B1B1-47E7-B854-EFD7521B0E94} | 43071102 | DUNBAR 1102 | 528 | 38.3295 | -122.5096 | DUNBAR 1102528 | 99 | 66 | 10886.5186 | 6520.0631 | 4366.4555 | 5365.7106 | 3634.4631 | 0.0046351 | 0.0037661 | 1.35 | 12.0204 | 1883 | 0.26856 | 1022 | 0 | 0 | 3.3341 | 27 | 0
Sierra | 4238 | 1767 | 2256.0795 | 3147 | 2960.7144 | 293 | 0.00012422 | 40.7301 | 167.3192 | 1544.0196 | 27021.6169 | 9918.3292 | 2.7518 | 39.0302 | 1.1404 | 0.0054872 | 0.0099329 | 0.56149 | 0.76201 | {C334FDD7-2F74-4DEB-B23B-81054BF72A46} | 153661103 | APPLE HILL 1103 | 8412 | 38.7272 | -120.738 | APPLE HILL 11038412 | 301 | 300 | 57090.4583 | 32448.6667 | 24641.7917 | 32448.6667 | 24641.7917 | 2.9103 | 0.036397 | 1.2768 | 10.7406 | 7 | 1.6077 | 1023 | 0 | 0 | 20.1627 | 3027 | 0
North Coast | 4238 | 3 | 6.8145 | 23 | 28.5 | 1 | 0.00012286 | 23.8659 |  |  |  |  | 4.7566 | 45.5976 | 1.0088 | 0.0029321 | 0.00012286 | 0.13043 | 0.23911 | {C334FDD7-2F74-4DEB-B23B-81054BF72A46} | 153661103 | APPLE HILL 1103 | 8412 | 38.7272 | -120.738 | APPLE HILL 11038412 | 301 | 300 | 57090.4583 | 32448.6667 | 24641.7917 | 32448.6667 | 24641.7917 | 0.00012286 | 0.00012286 | 2.2715 | 23 | 1737 | 0.0029321 | 1023 | 0 | 0 | 20.1627 | 1770 | 0
North Coast | 7539 | 276 | 368.6451 | 1256 | 913.8785 | 129 | 7.5064e-05 | 64.2603 | 4.6414 | 69.1308 | 733.9653 | 12.5547 | 1.7678 | 28.9838 | 1.0672 | 0.005458 | 0.00021358 | 0.21975 | 0.40339 | {4B7DC187-5EE3-45A7-A2F4-3F80A5EC9C80} | 42721103 | SONOMA 1103 | 3052 | 38.2911 | -122.4394 | SONOMA 11033052 | 238 | 278 | 53420.248 | 26080.1016 | 27340.1464 | 21211.1693 | 20130.945 | 0.027551 | 0.0096833 | 1.3357 | 9.7364 | 1372 | 0.70408 | 1024 | 0 | 0 | 13.18 | 1595 | 0
Central Coast | 1107 | 125 | 283.0131 | 461 | 377.7701 | 138 | 4.3566e-05 | 108.0691 | 4.6206 | 1464.4276 | 9865.4665 | 148.2776 | 3.8944 | 1079.1119 | 1.5134 | 0.0054385 | 0.0001432 | 0.27115 | 0.74917 | {DC9AC6DA-C366-497D-A431-13D5888CCACE} | 182661106 | SAN MIGUEL 1106 | circuit_breaker | 35.7522 | -120.6844 | SAN MIGUEL 1106circuit_breaker | 315 | 226 | 115043.6157 | 93802.1913 | 21241.4243 | 56840.9678 | 13174.5428 | 0.019762 | 0.0060121 | 2.2641 | 3.3406 | 1622 | 0.75051 | 1025 | 0 | 0 | 35.3193 | 174 | 0
Bay Area | 8732 | 22 | 54.183 | 51 | 68.2816 | 7 | 4.9565e-05 | 102.1786 | 4.7336 | 8.7846 | 25.4753 | 0.4718 | 4.1659 | 52.2826 | 1.0468 | 0.0054186 | 0.0002327 | 0.43137 | 0.79352 | {C65A3889-43E9-4E24-9131-D549D4446C2C} | 13532109 | LAKEWOOD 2109 | 64992 | 37.912 | -122.0445 | LAKEWOOD 210964992 | 103 | 81 | 7631.1352 | 4200.5164 | 3430.6188 | 587.7906 | 784.5439 | 0.0016289 | 0.00034695 | 2.4629 | 7.2857 | 1305 | 0.03793 | 1026 | 0 | 0 | 0.36524 | 1142 | 0
Central Coast | 4497 | 276 | 738.9613 | 1687 | 1452.4016 | 219 | 3.172e-05 | 214.6194 | 2.6367 | 36.4595 | 160.2004 | 1.3233 | 6.3336 | 64.2986 | 1.1202 | 0.0054134 | 6.1073e-05 | 0.1636 | 0.50879 | {1413E321-0BD6-4E14-989C-C8FF6A4A6DD1} | 182631107 | SAN LUIS OBISPO 1107 | V02 | 35.2383 | -120.6792 | SAN LUIS OBISPO 1107V02 | 292 | 260 | 45397.322 | 29266.1548 | 16131.1672 | 29017.7252 | 16131.1672 | 0.013375 | 0.0069466 | 2.6774 | 7.7032 | 2122 | 1.1855 | 1027 | 0 | 0 | 18.0308 | 661 | 0
Sierra | 589 | 3410 | 4160.4015 | 5414 | 5111.0093 | 453 | 9.0094e-05 | 60.9172 | 77.4753 | 1830.4261 | 35495.4564 | 8628.2264 | 1.27 | 41.5964 | 1.108 | 0.0054111 | 0.0036005 | 0.62985 | 0.81401 | {01403AE6-90D4-4B19-983B-B7AD8BDC29F6} | 152181102 | FORESTHILL 1102 | 2106 | 39.0197 | -120.8514 | FORESTHILL 11022106 | 390 | 316 | 68717.264 | 45220.1977 | 23497.0662 | 45220.1977 | 23497.0662 | 1.631 | 0.040813 | 1.2201 | 11.9514 | 74 | 2.4513 | 1028 | 0 | 0 | 28.0985 | 2345 | 0
North Valley | 4605 | 760 | 1194.7171 | 2534 | 1966.4874 | 355 | 0.00010304 | 56.6426 | 6.9487 | 442.3957 | 7002.4526 | 134.9989 | 1.8931 | 53.4287 | 1.1994 | 0.0053954 | 0.00039141 | 0.29992 | 0.60754 | {C16C1929-96C3-43F4-BC03-230CA41480EC} | 102911103 | WYANDOTTE 1103 | 1508 | 39.5046 | -121.4527 | WYANDOTTE 11031508 | 336 | 179 | 56905.6699 | 43569.7992 | 13335.8707 | 43569.7992 | 13335.8707 | 0.13895 | 0.036579 | 1.572 | 7.138 | 956 | 1.9154 | 1029 | 0 | 0 | 27.073 | 463 | 0
North Valley | 8242 | 223 | 404.5871 | 359 | 469.0468 | 82 | 6.2932e-05 | 99.5613 | 6.3135 | 378.4569 | 2450.3911 | 46.6186 | 3.3942 | 169.0626 | 1.4776 | 0.0053843 | 0.00016258 | 0.62117 | 0.86257 | {BE4941E8-75D1-4DE2-AD8F-78922C143536} | 102041104 | NOTRE DAME 1104 | 2408 | 39.7393 | -121.7854 | NOTRE DAME 11042408 | 96 | 66 | 27404.1309 | 22043.6191 | 5360.5118 | 18145.7739 | 5303.6304 | 0.013331 | 0.0051604 | 1.8143 | 4.378 | 1540 | 0.44151 | 1030 | 0 | 0 | 11.2753 | 996 | 0
Central Coast | 5846 | 19 | 23.3815 | 79 | 57.6201 | 22 | 1.7481e-05 | 303.4623 | 8.1771 | 377.4403 | 1694.4659 | 68.5242 | 5.9187 | 422.9086 | 1.3244 | 0.0053788 | 3.5254e-05 | 0.24051 | 0.40579 | {648B5D01-67D3-492E-989C-FF81490722DD} | 82831109 | MILPITAS 1109 | XR524 | 37.4496 | -121.8476 | MILPITAS 1109XR524 | 78 | 21 | 20105.5574 | 18154.4959 | 1951.0615 | 16623.6103 | 1164.4222 | 0.00077558 | 0.00038458 | 1.2306 | 3.5909 | 2394 | 0.11833 | 1031 | 0 | 0 | 10.3294 | 1147 | 0
North Coast | 128 | 313 | 611.9111 | 627 | 789.6335 | 94 | 6.4602e-05 | 88.7523 | 1.748 | 18.2391 | 111.6357 | 0.6671 | 4.4123 | 57.3576 | 1.0845 | 0.0054062 | 8.4948e-05 | 0.4992 | 0.77493 | {C28A65D7-37D3-4F6C-9C48-AF74AD2858BE} | 42891102 | GEYSERVILLE 1102 | 522 | 38.7163 | -122.8936 | GEYSERVILLE 1102522 | 142 | 176 | 29664.6273 | 16833.4938 | 12831.1335 | 11530.9091 | 9911.0113 | 0.0079851 | 0.0060726 | 1.955 | 6.6702 | 1952 | 0.50819 | 1032 | 0 | 0 | 7.165 | 681 | 0
Bay Area | 128 | 0 | 0 | 10 | 21.3399 | 1 | 9.8263e-05 | 23.9113 |  |  |  |  | 5.4137 | 27.1788 | 1.0708 | 0.0023496 | 9.8263e-05 | 0 | 0 | {C28A65D7-37D3-4F6C-9C48-AF74AD2858BE} | 42891102 | GEYSERVILLE 1102 | 522 | 38.7163 | -122.8936 | GEYSERVILLE 1102522 | 142 | 176 | 29664.6273 | 16833.4938 | 12831.1335 | 11530.9091 | 9911.0113 | 9.8263e-05 | 9.8263e-05 |  | 10 | 1862 | 0.0023496 | 1032 | 0 | 0 | 7.165 | 443 | 0
Bay Area | 9742 | 6 | 7.3663 | 13 | 11.8413 | 3 | 4.4565e-05 | 206.5166 |  |  |  |  | 10.8643 | 70.0442 | 1.0855 | 0.0053485 | 4.4565e-05 | 0.46154 | 0.62208 | {C9CC8490-6E43-45D4-87C2-A85ACD7797AC} | 43201102 | STAFFORD 1102 | circuit_breaker | 38.1198 | -122.6141 | STAFFORD 1102circuit_breaker | 17 | 0 | 993.1053 | 993.1053 | 0 | 669.8914 | 0 | 0.0001337 | 0.0001337 | 1.2277 | 4.3333 | 2287 | 0.016045 | 1033 | 0 | 0 | 0.41625 | 2722 | 0
Sierra | 6849 | 206 | 329.9636 | 905 | 573.5625 | 138 | 6.4632e-05 | 85.6279 | 10.8831 | 97.1407 | 544.6865 | 10.6282 | 5.0806 | 113.8625 | 1.2776 | 0.0052869 | 0.00036752 | 0.22762 | 0.57529 | {46E9257A-F9DC-47D6-A72D-7B5FD7E2E022} | 152691104 | HIGGINS 1104 | circuit_breaker | 39.0438 | -121.091 | HIGGINS 1104circuit_breaker | 189 | 105 | 26726.735 | 18704.9095 | 8021.8255 | 16734.2321 | 7824.5038 | 0.050717 | 0.0089192 | 1.6018 | 6.558 | 990 | 0.72959 | 1034 | 0 | 0 | 10.3982 | 2786 | 0
Central Valley | 1092 | 120 | 188.4849 | 518 | 339.1843 | 61 | 8.3086e-05 | 77.7037 | 5.5364 | 59.8079 | 396.6003 | 26.2672 | 2.7202 | 35.8053 | 1.1288 | 0.0052863 | 0.00020034 | 0.23166 | 0.5557 | {290F2F85-BD8F-4301-9FF5-97DAAF38092F} | 163781705 | PEORIA 1705 | 6697 | 37.9607 | -120.4259 | PEORIA 17056697 | 72 | 85 | 13257.4547 | 6657.3541 | 6600.1006 | 6657.3541 | 6600.1006 | 0.012221 | 0.0050683 | 1.5707 | 8.4918 | 1411 | 0.32247 | 1035 | 0 | 0 | 4.1367 | 1325 | 0
North Coast | 4941 | 253 | 322.5855 | 646 | 557.1921 | 65 | 9.1447e-05 | 55.7036 | 1.0739 | 53.1587 | 625.3594 | 2.1595 | 0.31076 | 20.2698 | 1.041 | 0.0052788 | 9.273e-05 | 0.39164 | 0.57895 | {565357B0-3D43-4998-81C7-7EBC74E038B1} | 43071101 | DUNBAR 1101 | 47964 | 38.3919 | -122.53 | DUNBAR 110147964 | 94 | 54 | 18132.6868 | 12211.6017 | 5921.0851 | 10130.7271 | 5777.9586 | 0.0060274 | 0.0059441 | 1.275 | 9.9385 | 1891 | 0.34312 | 1036 | 0 | 0 | 6.2949 | 679 | 0
Sierra | 2222 | 77 | 144.4889 | 427 | 255.6261 | 64 | 5.9158e-05 | 84.7484 | 9.6939 | 80.3906 | 296.7173 | 13.4743 | 9.4276 | 78.0455 | 1.0367 | 0.0052695 | 0.00026222 | 0.18033 | 0.56524 | {35B30399-E588-44B0-B481-56F6CD9688B5} | 152701108 | BELL 1108 | circuit_breaker | 38.9467 | -121.0916 | BELL 1108circuit_breaker | 376 | 424 | 39704.1787 | 20105.7391 | 19598.4396 | 6935.3327 | 5823.5542 | 0.016782 | 0.0037861 | 1.8765 | 6.6719 | 1220 | 0.33725 | 1037 | 0 | 0 | 4.3094 | 956 | 0
Central Valley | 4728 | 448 | 644.2802 | 1202 | 942.3475 | 154 | 6.7735e-05 | 51.6159 | 6.4272 | 28.0392 | 99.0491 | 1.443 | 3.6147 | 32.3959 | 1.2107 | 0.0052559 | 0.0002142 | 0.37271 | 0.6837 | {87827028-00DC-43D6-989D-C6C9D1E3E860} | 163351705 | CURTIS 1705 | circuit_breaker | 37.9745 | -120.3204 | CURTIS 1705circuit_breaker | 290 | 299 | 42466.3542 | 21968.5837 | 20497.7706 | 21100.4775 | 19805.2621 | 0.032986 | 0.010431 | 1.4381 | 7.8052 | 1368 | 0.80941 | 1038 | 0 | 0 | 13.1112 | 813 | 0
Bay Area | 2046 | 121 | 350.3338 | 681 | 656.0245 | 54 | 4.6845e-05 | 66.6538 | 1.0714 | 6.4987 | 43.6571 | 0.50171 | 0.85364 | 27.7372 | 1.0973 | 0.0052545 | 6.3581e-05 | 0.17768 | 0.53403 | {B3DBF89F-E691-4A93-8B05-2E162DB10E10} | 42031120 | ALTO 1120 | 1214 | 37.8784 | -122.5342 | ALTO 11201214 | 91 | 430 | 27179.6011 | 7258.7621 | 19920.839 | 5446.0036 | 10972.68 | 0.0034334 | 0.0025296 | 2.8953 | 12.6111 | 2107 | 0.28374 | 1039 | 0 | 0 | 3.384 | 2336 | 0
Bay Area | 2752 | 124 | 169.8714 | 240 | 234.6955 | 23 | 3.9314e-05 | 206.1372 | 24.0089 | 70.4877 | 334.1484 | 66.6267 | 4.5408 | 71.2968 | 1.0511 | 0.0052524 | 0.00022868 | 0.51667 | 0.72379 | {05770147-61C5-4F9A-BFD5-5491F913B539} | 14662112 | TASSAJARA 2112 | 38868 | 37.8321 | -121.9571 | TASSAJARA 211238868 | 162 | 221 | 15052.9547 | 6910.3569 | 8142.5978 | 2492.9277 | 2822.9718 | 0.0052595 | 0.00090422 | 1.3699 | 10.4348 | 1316 | 0.12081 | 1040 | 0 | 0 | 1.549 | 1177 | 0
Central Valley | 926 | 294 | 505.0596 | 2085 | 1197.0852 | 259 | 8.5864e-05 | 79.8258 | 15.5569 | 179.4231 | 841.1921 | 35.7535 | 4.5639 | 60.9363 | 1.1585 | 0.0052515 | 0.00060072 | 0.14101 | 0.42191 | {1D6F2813-1DE7-4CF3-9F1D-B6618158D284} | 163351703 | CURTIS 1703 | 6064 | 37.9604 | -120.3764 | CURTIS 17036064 | 303 | 367 | 58935.168 | 31678.1851 | 27256.9829 | 30178.8533 | 26589.7843 | 0.15559 | 0.022239 | 1.7179 | 8.0502 | 671 | 1.3601 | 1041 | 0 | 0 | 18.7523 | 1684 | 0
Central Valley | 3291 | 251 | 581.9174 | 1343 | 927.6367 | 203 | 3.85e-05 | 131.3946 | 13.5054 | 472.5672 | 2830.467 | 86.1968 | 6.4577 | 141.8769 | 1.1929 | 0.0052213 | 0.00026258 | 0.1869 | 0.62731 | {843F968C-C902-4C08-BE12-AD0D025C5DF3} | 163781705 | PEORIA 1705 | 1834 | 37.9479 | -120.4202 | PEORIA 17051834 | 305 | 381 | 71158.0797 | 38348.1492 | 32809.9305 | 37631.0076 | 32010.5179 | 0.053303 | 0.0078155 | 2.3184 | 6.6158 | 1216 | 1.0599 | 1042 | 0 | 0 | 23.3828 | 1642 | 0
Sierra | 1793 | 651 | 1135.715 | 3135 | 2067.46 | 354 | 7.0253e-05 | 88.883 | 7.3164 | 35.9664 | 164.7565 | 3.4462 | 4.5191 | 34.3074 | 1.0932 | 0.0052026 | 0.00031962 | 0.20766 | 0.54933 | {FF6B966D-B6C9-448E-9EAD-BA4CD433B469} | 152701108 | BELL 1108 | 2226 | 38.9598 | -121.1016 | BELL 11082226 | 535 | 854 | 87392.1734 | 41003.1194 | 46389.054 | 38840.6709 | 42802.3067 | 0.11315 | 0.02487 | 1.7446 | 8.8559 | 1077 | 1.8417 | 1043 | 0 | 0 | 24.1345 | 894 | 0
Central Coast | 1994 | 351 | 1135.5186 | 719 | 1363.2139 | 93 | 1.4934e-05 | 334.9849 | 33.5976 | 145.6098 | 731.0991 | 58.2076 | 12.6704 | 79.0951 | 1.1016 | 0.005194 | 0.00022478 | 0.48818 | 0.83297 | {6A98D8AD-262A-4E43-B52C-E7FA164E1E31} | 182601102 |  | V56 | 35.0804 | -120.5538 | V56 | 167 | 133 | 23195.3437 | 15908.7859 | 7286.5578 | 14519.9082 | 6848.0801 | 0.020904 | 0.0013889 | 3.2351 | 7.7312 | 1328 | 0.48304 | 1044 | 0 | 0 | 9.0222 | 597 | 0
North Valley | 2835 | 286 | 382.9462 | 1004 | 769.7264 | 221 | 4.1138e-05 | 115.2067 | 7.2348 | 1386.1435 | 17431.835 | 487.8874 | 2.3984 | 99.3215 | 1.1544 | 0.0052051 | 0.00013566 | 0.28486 | 0.49751 | {2F8DBBAA-A379-4ECE-8007-F482E8F75EAA} | 102541101 | VOLTA 1101 | 1596 | 40.3514 | -121.7815 | VOLTA 11011596 | 187 | 273 | 51670.2753 | 34685.9379 | 16984.3374 | 34685.9379 | 16984.3374 | 0.029981 | 0.0090914 | 1.339 | 4.543 | 1660 | 1.1503 | 1045 | 0 | 0 | 21.5528 | 2361 | 0
Central Coast | 2835 | 0 | 0 | 7 | 3.7005 | 1 | 5.0149e-05 | 23.8485 | 0.00010372 | 0.0038342 | 0.01067 | 3.2098e-07 | 0.47566 | 11.9779 | 1.0111 | 0.001196 | 5.2016e-09 | 0 | 0 | {2F8DBBAA-A379-4ECE-8007-F482E8F75EAA} | 102541101 | VOLTA 1101 | 1596 | 40.3514 | -121.7815 | VOLTA 11011596 | 187 | 273 | 51670.2753 | 34685.9379 | 16984.3374 | 34685.9379 | 16984.3374 | 5.2016e-09 | 5.0149e-05 |  | 7 | 2887 | 0.001196 | 1045 | 0 | 0 | 21.5528 | 2399 | 0
Central Coast | 2675 | 20 | 43.6233 | 96 | 88.1483 | 16 | 2.3311e-05 | 334.9885 | 11.7184 | 344.7851 | 1775.4052 | 36.2478 | 5.7081 | 117.8135 | 1.1164 | 0.0051697 | 0.00015124 | 0.20833 | 0.49489 | {AF824FE0-092F-4984-80E3-6C6BE36268BB} | 182631104 | SAN LUIS OBISPO 1104 | V10 | 35.215 | -120.6143 | SAN LUIS OBISPO 1104V10 | 112 | 46 | 13139.1496 | 10945.8906 | 2193.259 | 5741.8428 | 385.8005 | 0.0024199 | 0.00037297 | 2.1812 | 6 | 1585 | 0.082715 | 1046 | 0 | 0 | 3.5678 | 136 | 0
North Valley | 5429 | 3 | 5.8349 | 4 | 6.0483 | 2 | 4.043e-05 | 119.0172 |  |  |  |  | 21.74 | 75.5043 | 1.1438 | 0.0051578 | 4.043e-05 | 0.75 | 0.96472 | {729134BB-0DFA-4145-807F-650A6E064048} | 102911103 | WYANDOTTE 1103 | circuit_breaker | 39.4917 | -121.5411 | WYANDOTTE 1103circuit_breaker | 231 | 432 | 26621.3822 | 11732.2478 | 14889.1344 | 375.8787 | 167.4875 | 8.086e-05 | 8.086e-05 | 1.945 | 2 | 2334 | 0.010316 | 1047 | 0 | 0 | 0.23356 | 2055 | 0
North Valley | 8885 | 309 | 414.8628 | 608 | 578.8746 | 116 | 4.3858e-05 | 118.932 | 4.8419 | 1718.0146 | 31636.1174 | 402.3551 | 1.4246 | 174.4102 | 1.2865 | 0.0051496 | 0.00013291 | 0.50822 | 0.71667 | {57B8A89B-DB5A-4A47-A82F-ABC7F06A8571} | 103611101 | WILDWOOD 1101 | 1576 | 40.3851 | -123.0294 | WILDWOOD 11011576 | 59 | 43 | 14473.3676 | 13123.158 | 1350.2096 | 13123.158 | 1350.2096 | 0.015417 | 0.0050875 | 1.3426 | 5.2414 | 1685 | 0.59736 | 1048 | 0 | 0 | 8.1543 | 436 | 0
North Coast | 7936 | 125 | 267.8189 | 277 | 341.3688 | 33 | 8.4376e-05 | 57.7397 | 29.2868 | 185.9478 | 710.82 | 43.224 | 3.5508 | 25.9053 | 1.0358 | 0.0051299 | 0.0014517 | 0.45126 | 0.78454 | {98A83A4A-2877-4301-8F63-D1E33C62F68A} | 192291121 | CARLOTTA 1121 | 42896 | 40.5485 | -124.1008 | CARLOTTA 112142896 | 123 | 124 | 14438.4442 | 8736.3016 | 5702.1426 | 3183.4592 | 1533.6483 | 0.047906 | 0.0027844 | 2.1426 | 8.3939 | 258 | 0.16929 | 1049 | 0 | 0 | 1.9781 | 2381 | 0
Bay Area | 4414 | 31 | 53.3294 | 69 | 73.9526 | 11 | 6.5118e-05 | 64.9259 | 6.3614 | 36.8651 | 124.7058 | 1.1236 | 0.82864 | 14.437 | 1.0282 | 0.0051112 | 0.00040356 | 0.44928 | 0.72113 | {22FCC67B-2F67-4BDC-A189-C3D042C3C23F} | 14662108 | TASSAJARA 2108 | 65438 | 37.8355 | -122.0207 | TASSAJARA 210865438 | 117 | 257 | 17931.4974 | 6051.8729 | 11879.6246 | 1087.8821 | 438.7801 | 0.0044391 | 0.0007163 | 1.7203 | 6.2727 | 940 | 0.056223 | 1050 | 0 | 0 | 0.67598 | 1085 | 0
North Valley | 7247 | 71 | 135.2195 | 327 | 212.9111 | 57 | 4.2254e-05 | 131.6256 | 5.4034 | 341.3228 | 1596.1108 | 31.7103 | 4.2788 | 488.8282 | 1.4721 | 0.0050747 | 0.00012737 | 0.21713 | 0.6351 | {6DDE6DFF-A5B7-42A5-A5E6-915A880E38B9} | 102911102 | WYANDOTTE 1102 | 13044 | 39.5308 | -121.554 | WYANDOTTE 110213044 | 61 | 42 | 12343.8187 | 9510.113 | 2833.7057 | 6256.4266 | 2311.9676 | 0.00726 | 0.0024085 | 1.9045 | 5.7368 | 1709 | 0.28926 | 1051 | 0 | 0 | 3.8876 | 416 | 0
Central Coast | 5717 | 775 | 1534.7533 | 1848 | 2124.917 | 273 | 9.9332e-05 | 54.875 | 10.2118 | 1146.9022 | 7569.3643 | 120.0361 | 9.6529 | 323.0637 | 1.4365 | 0.0050692 | 0.00055138 | 0.41937 | 0.72227 | {E6F3FB48-7B73-44A2-9D22-75A3F05024E8} | 183052113 | TEMPLETON 2113 | A10 | 35.4107 | -120.5657 | TEMPLETON 2113A10 | 320 | 285 | 70409.867 | 49852.2593 | 20557.6077 | 49852.2593 | 20557.6077 | 0.15053 | 0.027118 | 1.9803 | 6.7692 | 734 | 1.3839 | 1052 | 0 | 0 | 30.9767 | 298 | 0
North Coast | 4409 | 281 | 457.198 | 737 | 657.7024 | 116 | 8.7197e-05 | 60.7325 | 4.1597 | 41.584 | 434.4238 | 3.4503 | 2.5105 | 18.997 | 1.1587 | 0.0050679 | 0.00015334 | 0.38128 | 0.69514 | {C851DF07-17A8-4945-A053-68AC77422563} | 43411101 | CALPELLA 1101 | circuit_breaker | 39.1969 | -123.1927 | CALPELLA 1101circuit_breaker | 398 | 552 | 59702.5655 | 32842.3149 | 26860.2506 | 17245.9403 | 10008.7228 | 0.017787 | 0.010115 | 1.627 | 6.3534 | 1573 | 0.58788 | 1053 | 0 | 0 | 10.7161 | 830 | 0
North Coast | 8669 | 182 | 268.6039 | 632 | 518.5409 | 57 | 4.2705e-05 | 177.3041 | 31.7531 | 1871.5541 | 12450.783 | 755.0238 | 6.966 | 525.7975 | 1.3163 | 0.0050676 | 0.00060019 | 0.28797 | 0.518 | {F16EF0FE-506D-4026-9FF6-A9B4826F67BC} | 43371102 | LAKEVILLE 1102 | 87432 | 38.2562 | -122.5858 | LAKEVILLE 110287432 | 96 | 77 | 29530.1399 | 22038.8573 | 7491.2826 | 15489.4062 | 4653.4923 | 0.034211 | 0.0024342 | 1.4758 | 11.0877 | 672 | 0.28885 | 1054 | 0 | 0 | 9.6247 | 852 | 0
Sierra | 7229 | 41 | 82.4207 | 80 | 98.6263 | 20 | 0.00013377 | 65.4919 | 2.8291 | 5.2321 | 32.909 | 0.29083 | 2.2141 | 27.9425 | 1.2499 | 0.0050637 | 0.00019553 | 0.5125 | 0.83569 | {31F15014-5008-45D5-9481-1A850055776D} | 153652108 | SHINGLE SPRINGS 2108 | circuit_breaker | 38.6593 | -120.9467 | SHINGLE SPRINGS 2108circuit_breaker | 44 | 48 | 3892.3441 | 2376.1029 | 1516.2412 | 2376.1029 | 1454.537 | 0.0039107 | 0.0026754 | 2.0103 | 4 | 1426 | 0.10127 | 1055 | 0 | 0 | 1.4764 | 114 | 0
North Coast | 8114 | 461 | 841.5788 | 546 | 886.6893 | 97 | 7.7972e-05 | 57.1681 | 0.3893 | 232.1813 | 2159.2416 | 1.6002 | 0.2315 | 51.0056 | 1.1096 | 0.0049987 | 5.4228e-05 | 0.84432 | 0.94912 | {4E7F584A-58CA-4FD0-89EA-914007B3A7FD} | 42861101 | ANNAPOLIS 1101 | 608 | 38.6772 | -123.3138 | ANNAPOLIS 1101608 | 92 | 58 | 31086.955 | 28636.0357 | 2450.9193 | 28636.0357 | 2450.9193 | 0.0052601 | 0.0075632 | 1.8256 | 5.6289 | 2201 | 0.48487 | 1056 | 0 | 0 | 17.7936 | 1533 | 0
Central Valley | 2473 | 45 | 94.2946 | 223 | 150.6688 | 54 | 3.7772e-05 | 134.7793 | 9.8863 | 574.2608 | 3572.2957 | 76.4204 | 7.6089 | 642.304 | 1.6158 | 0.0049965 | 0.00011708 | 0.20179 | 0.62584 | {AE111B59-4073-4BA6-A6F7-C46E4FCA24F4} | 163341103 | CLAY 1103 | 34338 | 38.2944 | -120.9095 | CLAY 110334338 | 75 | 48 | 23409.9025 | 16836.8272 | 6573.0753 | 14279.384 | 5450.3293 | 0.0063222 | 0.0020397 | 2.0954 | 4.1296 | 1762 | 0.26981 | 1057 | 0 | 0 | 8.8728 | 219 | 0
Central Coast | 4387 | 492 | 922.519 | 619 | 991.0771 | 30 | 0.00018497 | 24.6394 | 14.6838 | 35.6127 | 154.9755 | 1.6412 | 0.35782 | 5.9809 | 1.0139 | 0.0049874 | 0.0010194 | 0.79483 | 0.93082 | {F21FA11B-160D-41F2-AA17-7452280F39DA} | 83622105 | CAMP EVERS 2105 | 11010 | 37.1053 | -122.0518 | CAMP EVERS 210511010 | 54 | 171 | 11506.1747 | 3577.8936 | 7928.2811 | 3577.8936 | 7928.2811 | 0.030581 | 0.0055491 | 1.875 | 20.6333 | 402 | 0.14962 | 1058 | 0 | 0 | 2.2232 | 1382 | 0
North Valley | 9262 | 10 | 21.7637 | 18 | 24.1692 | 4 | 2.7844e-05 | 178.6049 | 24.5551 | 26.6873 | 117.6424 | 5.7737 | 6.6991 | 67.4356 | 1.1233 | 0.0049535 | 0.00033445 | 0.55556 | 0.90047 | {4F1FF48F-FF8A-488F-A383-0E93A88F3890} | 103521103 | OREGON TRAIL 1103 | 46860 | 40.6171 | -122.334 | OREGON TRAIL 110346860 | 26 | 1 | 5356.1828 | 5350.0868 | 6.096 | 1140.2586 | 0 | 0.0013378 | 0.00011137 | 2.1764 | 4.5 | 1045 | 0.019814 | 1059 | 0 | 0 | 0.70852 | 1019 | 0
Central Valley | 1923 | 204 | 303.0191 | 798 | 532.3025 | 113 | 3.5291e-05 | 175.6712 | 29.6878 | 784.648 | 9013.5739 | 458.3794 | 7.1399 | 152.0753 | 1.3586 | 0.0049435 | 0.00057852 | 0.25564 | 0.56926 | {5B03EFF1-F12F-4656-8D60-84D55FFB9841} | 163351704 | CURTIS 1704 | 11290 | 38.0065 | -120.347 | CURTIS 170411290 | 113 | 109 | 22972.4339 | 12662.0411 | 10310.3929 | 12662.0411 | 10310.3929 | 0.065373 | 0.0039878 | 1.4854 | 7.0619 | 699 | 0.55861 | 1060 | 0 | 0 | 7.8678 | 1662 | 0
North Coast | 9040 | 2273 | 3531.4678 | 2713 | 3741.3223 | 229 | 0.00010448 | 48.135 | 1.0521 | 113.5416 | 1528.3447 | 2.5393 | 0.4854 | 17.8278 | 1.041 | 0.0049372 | 0.000105 | 0.83782 | 0.94391 | {9C0210C9-FBB0-4C91-A32D-9DD4D26081CB} | 42681102 | LAYTONVILLE 1102 | 682 | 39.6298 | -123.5825 | LAYTONVILLE 1102682 | 121 | 96 | 29044.7107 | 23844.5349 | 5200.1758 | 23844.5349 | 5200.1758 | 0.024044 | 0.023925 | 1.5537 | 11.8472 | 1835 | 1.1306 | 1061 | 0 | 0 | 14.8163 | 1148 | 0
North Coast | 3469 | 2578 | 3987.759 | 3357 | 4340.893 | 282 | 0.00019903 | 27.2955 | 4.1271 | 1371.8035 | 34822.223 | 263.0603 | 0.18725 | 19.7406 | 1.0763 | 0.0049372 | 0.00047696 | 0.76795 | 0.91865 | {2D4A5008-1C90-406A-A2B7-E4FA7A353F8A} | 192171101 | WILLOW CREEK 1101 | 4904 | 40.9469 | -123.6427 | WILLOW CREEK 11014904 | 146 | 81 | 32420.4304 | 29923.3138 | 2497.1166 | 29923.3138 | 2497.1166 | 0.1345 | 0.056127 | 1.5468 | 11.9043 | 815 | 1.3923 | 1062 | 0 | 0 | 18.5935 | 70 | 0
North Coast | 984 | 26 | 47.0223 | 40 | 56.5392 | 5 | 8.2503e-05 | 62.1095 | 52.3899 | 351.3016 | 2774.6799 | 146.1722 | 1.7066 | 81.6779 | 1.0367 | 0.0049303 | 0.0011275 | 0.65 | 0.83168 | {4D91C141-515F-4F14-8290-C8268E13D106} | 42151111 | SANTA ROSA A 1111 | circuit_breaker | 38.4368 | -122.7131 | SANTA ROSA A 1111circuit_breaker | 193 | 753 | 43710.1311 | 9029.1633 | 34680.9678 | 423.6161 | 995.7306 | 0.0056376 | 0.00041252 | 1.8086 | 8 | 352 | 0.024652 | 1063 | 0 | 0 | 0.26322 | 449 | 0
Bay Area | 7013 | 1682 | 2140.6061 | 2316 | 2510.2449 | 239 | 0.00011302 | 42.6753 | 1.3111 | 92.2217 | 1516.5364 | 24.7964 | 0.87747 | 22.3843 | 1.1651 | 0.0049131 | 0.00013275 | 0.72625 | 0.85275 | {991CF770-C017-4F1E-B905-05B063249BE8} | 43432105 | SILVERADO 2105 | 658898 | 38.5072 | -122.4911 | SILVERADO 2105658898 | 208 | 141 | 48126.6819 | 27768.6234 | 20358.0585 | 27768.6234 | 20358.0585 | 0.031727 | 0.027011 | 1.2727 | 9.6904 | 1687 | 1.1742 | 1064 | 0 | 0 | 17.2546 | 2687 | 0
Central Coast | 7623 | 45 | 101.2294 | 68 | 114.0426 | 10 | 6.6037e-05 | 92.8108 | 0.065196 | 11.6496 | 37.9177 | 0.0041087 | 4.5989 | 36.4414 | 1.0865 | 0.004906 | 4.7769e-05 | 0.66176 | 0.88765 | {C8FCB7D2-DBC0-45C1-8CE7-98B72CD50084} | 83182107 | LLAGAS 2107 | XR178 | 37.0134 | -121.6311 | LLAGAS 2107XR178 | 111 | 117 | 18135.2535 | 10843.4754 | 7291.7781 | 1344.6176 | 1309.3484 | 0.00047769 | 0.00066037 | 2.2495 | 6.8 | 2250 | 0.04906 | 1065 | 0 | 0 | 0.83551 | 2607 | 0
Sierra | 1215 | 1065 | 1207.2919 | 4273 | 2723.793 | 517 | 0.00010534 | 51.959 | 52.1655 | 1303.1125 | 25186.6683 | 5280.7494 | 0.36525 | 13.0858 | 1.0327 | 0.0048935 | 0.0025643 | 0.24924 | 0.44324 | {563CD71D-CD80-49B9-9B00-20025334D5E0} | 152762101 | EL DORADO PH 2101 | 26000 | 38.7525 | -120.5549 | EL DORADO PH 210126000 | 561 | 812 | 82318.6507 | 55423.1935 | 26895.4572 | 55423.1935 | 26895.4572 | 1.3258 | 0.054461 | 1.1336 | 8.265 | 124 | 2.53 | 1066 | 0 | 0 | 34.4384 | 110 | 0
North Coast | 5420 | 1172 | 1825.7679 | 2282 | 2432.266 | 213 | 0.00012262 | 40.9245 | 10.4267 | 167.9035 | 2091.6751 | 61.0011 | 0.50723 | 23.5398 | 1.0922 | 0.0048752 | 0.00065265 | 0.51358 | 0.75064 | {1B23A4BA-CD57-4FC0-AB6D-FA127475AD96} | 42091101 | MIRABEL 1101 | 298 | 38.4725 | -122.9106 | MIRABEL 1101298 | 175 | 206 | 33997.7844 | 20371.1921 | 13626.5923 | 20135.0832 | 13521.1575 | 0.13902 | 0.026118 | 1.5578 | 10.7136 | 615 | 1.0384 | 1067 | 0 | 0 | 12.5114 | 432 | 0
North Valley | 3296 | 999 | 1378.856 | 2753 | 2190.2756 | 330 | 0.00015234 | 37.4986 | 25.9546 | 680.5615 | 5782.3061 | 309.7551 | 2.3217 | 107.2139 | 1.1712 | 0.0048308 | 0.0020531 | 0.36288 | 0.62954 | {83913AD6-2C7D-48AE-A167-C6DEFED9C1DC} | 102541102 | VOLTA 1102 | 1646 | 40.5007 | -121.9162 | VOLTA 11021646 | 304 | 210 | 51842.2655 | 38830.605 | 13011.6605 | 37561.3918 | 12729.3503 | 0.67752 | 0.050271 | 1.3802 | 8.3424 | 172 | 1.5942 | 1068 | 0 | 0 | 23.3396 | 760 | 0
Central Valley | 3803 | 82 | 185.4272 | 489 | 328.2119 | 66 | 5.2562e-05 | 122.3404 | 9.5836 | 296.107 | 1780.3029 | 55.0077 | 7.736 | 94.0171 | 1.099 | 0.0048275 | 0.00024453 | 0.16769 | 0.56496 | {59D5B837-86E5-4FF6-AEF5-91D544FDF3B9} | 163781705 | PEORIA 1705 | 10580 | 37.9489 | -120.4258 | PEORIA 170510580 | 207 | 406 | 48817.2793 | 18856.5854 | 29960.6939 | 11664.5509 | 18011.3703 | 0.016139 | 0.0034691 | 2.2613 | 7.4091 | 1265 | 0.31862 | 1069 | 0 | 0 | 7.248 | 995 | 0
North Coast | 5880 | 129 | 184.4372 | 306 | 269.8409 | 32 | 0.00013707 | 33.4911 | 0.47035 | 514.299 | 6473.045 | 19.8069 | 0.0011062 | 10.1156 | 1.0124 | 0.0048125 | 9.5654e-05 | 0.42157 | 0.6835 | {CCE91D7C-BCE4-4F01-BD5F-6C83E3A409D2} | 192381102 | EEL RIVER 1102 | 4814 | 40.482 | -124.2289 | EEL RIVER 11024814 | 114 | 89 | 50730.9589 | 44419.8849 | 6311.074 | 43150.0728 | 6189.3968 | 0.0030609 | 0.0043862 | 1.4297 | 9.5625 | 1875 | 0.154 | 1070 | 0 | 0 | 26.8122 | 906 | 0
Central Valley | 6605 | 1 | 1.2277 | 13 | 6.4255 | 3 | 2.8417e-05 | 179.7007 | 5.3222 | 521.2927 | 1402.1766 | 7.4626 | 10.5524 | 1094.497 | 1.7633 | 0.0048076 | 7.6153e-05 | 0.076923 | 0.19107 | {9D5BFE02-DE54-49D0-8A6C-80BCABF7CBD7} | 163881101 | IONE 1101 | circuit_breaker | 38.3737 | -120.9575 | IONE 1101circuit_breaker | 119 | 60 | 30175.8828 | 22553.5189 | 7622.3639 | 1810.1911 | 266.5436 | 0.00022846 | 8.5251e-05 | 1.2277 | 4.3333 | 2011 | 0.014423 | 1071 | 0 | 0 | 1.1248 | 1660 | 0
North Coast | 5445 | 10 | 13.5802 | 17 | 15.5587 | 4 | 4.6693e-05 | 136.9172 | 0 | 0 | 0 | 0 | 8.1056 | 54.2814 | 1.0586 | 0.0048044 | 2.7356e-05 | 0.58824 | 0.87283 | {7C347C2A-D137-4C7B-9A15-013D3BAB11C4} | 42141102 | CLEAR LAKE 1102 | 4708 | 39.0258 | -122.9167 | CLEAR LAKE 11024708 | 64 | 80 | 8302.2434 | 4509.6824 | 3792.5609 | 312.1287 | 461.1137 | 0.00010942 | 0.00018677 | 1.358 | 4.25 | 2501 | 0.019218 | 1072 | 0 | 0 | 0.19395 | 1364 | 0
North Valley | 3964 | 323 | 451.066 | 982 | 787.7137 | 88 | 0.0001172 | 40.9459 | 3.0199 | 139.8019 | 1193.7541 | 10.1217 | 1.8671 | 35.9728 | 1.0398 | 0.004802 | 0.00021837 | 0.32892 | 0.57263 | {E0835FD3-053C-4202-87EB-465B52D17969} | 103601101 | WHITMORE 1101 | circuit_breaker | 40.6291 | -121.9158 | WHITMORE 1101circuit_breaker | 117 | 87 | 14358.2278 | 9527.4078 | 4830.82 | 9527.4078 | 4830.82 | 0.019216 | 0.010314 | 1.3965 | 11.1591 | 1347 | 0.42258 | 1073 | 0 | 0 | 5.9201 | 2527 | 0
North Valley | 5873 | 40 | 56.6028 | 81 | 79.4963 | 9 | 2.412e-05 | 182.8381 | 0.38473 | 141.7207 | 2730.8225 | 9.079 | 3.9712 | 74.1054 | 1.1952 | 0.0047857 | 1.5789e-05 | 0.49383 | 0.71202 | {2D495744-1EEC-4B5A-AB6C-8BE5D83F4E62} | 103021101 | GANSNER 1101 | 37550 | 39.939 | -120.9524 | GANSNER 110137550 | 95 | 74 | 11600.7899 | 7302.7522 | 4298.0377 | 1056.3754 | 57.5331 | 0.0001421 | 0.00021708 | 1.4151 | 9 | 2688 | 0.043071 | 1074 | 0 | 0 | 0.6564 | 1002 | 0
Central Valley | 2618 | 132 | 247.1731 | 513 | 364.8196 | 168 | 4.2117e-05 | 125.3636 | 3.5281 | 351.6733 | 1937.4356 | 21.5237 | 5.0982 | 537.7782 | 1.545 | 0.0047763 | 8.9031e-05 | 0.25731 | 0.67752 | {D62CDDF4-E093-4960-B995-54A7DAF191D3} | 163341103 | CLAY 1103 | 1230 | 38.2942 | -120.9112 | CLAY 11031230 | 156 | 100 | 43770.1388 | 30392.9883 | 13377.1505 | 24532.2816 | 10362.9357 | 0.014957 | 0.0070756 | 1.8725 | 3.0536 | 1920 | 0.80242 | 1075 | 0 | 0 | 15.2436 | 1669 | 0
Sierra | 432 | 233 | 411.6654 | 1267 | 812.8486 | 148 | 7.6488e-05 | 80.432 | 3.3576 | 34.5696 | 189.8431 | 2.2595 | 5.8054 | 53.4074 | 1.1866 | 0.0047581 | 0.00018177 | 0.1839 | 0.50645 | {E56A3B9A-F6B2-438C-8FDC-DFADF12A0423} | 152691110 | HIGGINS 1110 | circuit_breaker | 39.044 | -121.0905 | HIGGINS 1110circuit_breaker | 384 | 491 | 56542.0884 | 29132.7846 | 27409.3038 | 15857.3316 | 9944.4789 | 0.026902 | 0.01132 | 1.7668 | 8.5608 | 1481 | 0.70421 | 1076 | 0 | 0 | 9.8533 | 716 | 0
North Coast | 4466 | 1628 | 2664.6934 | 2029 | 2877.7114 | 241 | 6.9663e-05 | 64.5127 | 2.6437 | 119.831 | 595.5162 | 3.1755 | 0.89217 | 31.7174 | 1.1419 | 0.0047299 | 0.00012428 | 0.80237 | 0.92598 | {40E0DF85-5967-47AC-89F5-066590299710} | 42601102 | PHILO 1102 | 928 | 39.1176 | -123.5175 | PHILO 1102928 | 167 | 145 | 41285.7739 | 24804.6018 | 16481.1721 | 22042.0965 | 14704.8906 | 0.029952 | 0.016789 | 1.6368 | 8.4191 | 1730 | 1.1399 | 1077 | 0 | 0 | 13.6963 | 10 | 0
North Coast | 2395 | 441 | 593.9707 | 846 | 829.2079 | 96 | 0.00019297 | 26.3175 | 21.4067 | 52.6836 | 343.1123 | 17.3451 | 3.1328 | 13.2664 | 1.143 | 0.0047155 | 0.002193 | 0.52128 | 0.71631 | {43499343-6FDA-499A-9065-0F9A4F778AB9} | 43311102 | KONOCTI 1102 | 532 | 38.8577 | -122.7221 | KONOCTI 1102532 | 203 | 515 | 39122.9363 | 15232.9913 | 23889.945 | 15232.9913 | 23889.945 | 0.21053 | 0.018525 | 1.3469 | 8.8125 | 159 | 0.45268 | 1078 | 0 | 0 | 9.4653 | 2552 | 0
North Coast | 5056 | 121 | 193.6279 | 409 | 353.8536 | 47 | 6.133e-05 | 122.7496 | 48.6913 | 934.3059 | 6078.1615 | 469.549 | 7.5645 | 173.4354 | 1.2068 | 0.0046946 | 0.0012131 | 0.29584 | 0.5472 | {BB094C57-2223-469C-ABF0-9ADC89223899} | 43182103 | BELLEVUE 2103 | 648 | 38.3967 | -122.6247 | BELLEVUE 2103648 | 299 | 249 | 43548.1265 | 26113.2457 | 17434.8809 | 5275.9485 | 2234.5727 | 0.057016 | 0.0028825 | 1.6002 | 8.7021 | 321 | 0.22065 | 1079 | 0 | 0 | 3.2783 | 1544 | 0
North Coast | 8169 | 45 | 102.7149 | 103 | 136.9777 | 15 | 5.2198e-05 | 95.4593 | 21.5033 | 177.7263 | 809.5422 | 73.9432 | 8.0811 | 54.3139 | 1.0202 | 0.0046848 | 0.00051122 | 0.43689 | 0.74987 | {2E0FB866-9F6A-4839-A968-F9A8CD3FA6CE} | 42271102 | COTATI 1102 | 462 | 38.2988 | -122.7115 | COTATI 1102462 | 55 | 60 | 10178.0846 | 6310.2369 | 3867.8477 | 4359.8054 | 2252.9522 | 0.0076682 | 0.00078297 | 2.2826 | 6.8667 | 779 | 0.070272 | 1080 | 0 | 0 | 2.7091 | 1370 | 0
Bay Area | 4720 | 12 | 14.9001 | 64 | 46.216 | 17 | 2.4101e-05 | 172.0858 | 37.695 | 1232.0627 | 5211.2456 | 302.4655 | 5.5411 | 233.2772 | 1.2086 | 0.0046583 | 0.00060178 | 0.1875 | 0.3224 | {14F1F6DE-8209-477C-B956-E44E09281D3F} | 14241101 | SUNOL 1101 | MR196 | 37.575 | -121.8795 | SUNOL 1101MR196 | 149 | 73 | 26230.9898 | 20307.975 | 5923.0148 | 3630.319 | 1497.9962 | 0.01023 | 0.00040972 | 1.2417 | 3.7647 | 668 | 0.079191 | 1081 | 0 | 0 | 2.2558 | 268 | 0
Central Valley | 2312 | 688 | 967.398 | 2897 | 1919.5922 | 304 | 8.1841e-05 | 55.4917 | 14.0961 | 874.7424 | 7312.1078 | 147.7649 | 3.7591 | 178.6032 | 1.3345 | 0.0046373 | 0.00057093 | 0.23749 | 0.50396 | {147F14E5-BECB-490C-A00E-B83A5C57F64C} | 163541102 | OLETA 1102 | 1204 | 38.5326 | -120.7653 | OLETA 11021204 | 295 | 272 | 71239.8668 | 47208.0794 | 24031.7874 | 39941.6187 | 20539.6126 | 0.17356 | 0.02488 | 1.4061 | 9.5296 | 709 | 1.4097 | 1082 | 0 | 0 | 24.8186 | 1612 | 0
Sierra | 4334 | 622 | 873.6777 | 1454 | 1243.4042 | 154 | 9.5308e-05 | 51.178 | 16.9691 | 104.0582 | 1092.4324 | 83.5123 | 2.0713 | 29.4093 | 1.1107 | 0.0046627 | 0.00064524 | 0.42779 | 0.70265 | {6831EC63-2DE1-4FA9-8E52-ECEB96F95CDF} | 152691104 | HIGGINS 1104 | 1006 | 39.0996 | -121.05 | HIGGINS 11041006 | 536 | 1004 | 82584.6846 | 32162.0329 | 50422.6517 | 16662.2327 | 19291.7254 | 0.099366 | 0.014677 | 1.4046 | 9.4416 | 620 | 0.71805 | 1083 | 0 | 0 | 10.3534 | 1009 | 0
Bay Area | 4334 | 1 | 1.3586 | 6 | 6.4243 | 1 | 0.00013712 | 0.066432 |  |  |  |  | 1.4801 | 0.66881 | 1 | 9.1091e-06 | 0.00013712 | 0.16667 | 0.21148 | {6831EC63-2DE1-4FA9-8E52-ECEB96F95CDF} | 152691104 | HIGGINS 1104 | 1006 | 39.0996 | -121.05 | HIGGINS 11041006 | 536 | 1004 | 82584.6846 | 32162.0329 | 50422.6517 | 16662.2327 | 19291.7254 | 0.00013712 | 0.00013712 | 1.3586 | 6 | 1654 | 9.1091e-06 | 1083 | 0 | 0 | 10.3534 | 2531 | 0
Central Coast | 3035 | 180 | 314.0661 | 535 | 500.0137 | 65 | 5.9107e-05 | 91.7515 | 16.2725 | 115.4507 | 487.9997 | 10.1368 | 17.276 | 100.5354 | 1.6982 | 0.0046321 | 0.00053196 | 0.33645 | 0.62812 | {80C03548-09A3-4516-9CD7-A85242729AF9} | 182541103 | ATASCADERO 1103 | circuit_breaker | 35.4656 | -120.6713 | ATASCADERO 1103circuit_breaker | 174 | 306 | 30826.337 | 15502.9137 | 15323.4233 | 11975.6869 | 6797.5022 | 0.034578 | 0.003842 | 1.7448 | 8.2308 | 756 | 0.30109 | 1084 | 0 | 0 | 7.4413 | 1685 | 0
Central Coast | 8121 | 9 | 11.0494 | 29 | 24.4208 | 13 | 2.638e-05 | 286.3357 | 13.3101 | 602.7447 | 2560.0922 | 127.3097 | 8.0647 | 638.7638 | 1.4426 | 0.0046288 | 0.00012833 | 0.31034 | 0.45246 | {1D20AD79-1B20-4BDE-B0E8-CF4AA41EFB2A} | 182681101 | ZACA 1101 | Y72 | 34.7208 | -120.1303 | ZACA 1101Y72 | 48 | 51 | 12917.6888 | 10339.027 | 2578.6619 | 8576.3267 | 2508.5385 | 0.0016682 | 0.00034294 | 1.2277 | 2.2308 | 1706 | 0.060174 | 1085 | 0 | 0 | 5.3291 | 1476 | 0
North Coast | 5608 | 20 | 26.1797 | 33 | 31.2647 | 8 | 6.5336e-05 | 199.4197 | 5.9264 | 53.6063 | 156.5316 | 5.5208 | 5.6563 | 53.9464 | 1.6164 | 0.0046285 | 0.00039315 | 0.60606 | 0.83736 | {C0802380-5040-4C58-8433-9FF2FB3282BB} | 43361103 | HIGHLANDS 1103 | 4630 | 38.9098 | -122.6174 | HIGHLANDS 11034630 | 91 | 183 | 15328.041 | 5570.4953 | 9757.5457 | 963.0506 | 1874.5388 | 0.0031452 | 0.00052269 | 1.309 | 4.125 | 954 | 0.037028 | 1086 | 0 | 0 | 0.59841 | 873 | 0
Sierra | 6701 | 837 | 1029.8073 | 2115 | 1631.7854 | 216 | 9.0609e-05 | 48.8334 | 35.0422 | 1506.4809 | 18867.5953 | 1499.6732 | 1.4932 | 33.58 | 1.071 | 0.0046273 | 0.001821 | 0.39574 | 0.63109 | {32A5B84F-F8E0-4F0E-B3CD-BEC3B55A0617} | 152282101 | MOUNTAIN QUARRIES 2101 | 1180 | 38.8952 | -120.9116 | MOUNTAIN QUARRIES 21011180 | 182 | 172 | 32146.7186 | 20702.9508 | 11443.7678 | 20702.9508 | 11443.7678 | 0.39333 | 0.019572 | 1.2304 | 9.7917 | 191 | 0.9995 | 1087 | 0 | 0 | 12.8642 | 1488 | 0
Sierra | 788 | 372 | 521.3959 | 860 | 739.131 | 164 | 3.7006e-05 | 132.3232 | 15.2967 | 3814.9743 | 120243.2094 | 3080.0654 | 0.49726 | 44.6173 | 1.3549 | 0.0045876 | 0.00024085 | 0.43256 | 0.70542 | {A90B9AA9-7F37-4154-B2B2-B43A5EF8D800} | 152101101 | ALLEGHANY 1101 | 806 | 39.4878 | -120.8572 | ALLEGHANY 1101806 | 93 | 114 | 21734.175 | 19005.4498 | 2728.7252 | 19005.4498 | 2728.7252 | 0.039499 | 0.006069 | 1.4016 | 5.2439 | 1275 | 0.75237 | 1088 | 0 | 0 | 11.8094 | 571 | 0
North Coast | 882 | 145 | 287.4479 | 208 | 317.6017 | 40 | 5.534e-05 | 78.1417 | 10.0186 | 130.0803 | 628.1201 | 72.1489 | 7.8998 | 53.6385 | 1.0592 | 0.0045467 | 0.00031679 | 0.69712 | 0.90506 | {ACC3FA28-9FAB-4AE9-AABE-1ABF0B659322} | 42271105 | COTATI 1105 | 5156 | 38.3157 | -122.7354 | COTATI 11055156 | 199 | 336 | 33688.7823 | 16005.1118 | 17683.6704 | 7460.4725 | 5403.2756 | 0.012671 | 0.0022136 | 1.9824 | 5.2 | 1088 | 0.18187 | 1089 | 0 | 0 | 4.6357 | 1574 | 0
Central Valley | 4514 | 352 | 484.7763 | 1060 | 809.7385 | 64 | 0.00012384 | 57.5317 | 3.1754 | 158.8755 | 1480.3355 | 14.9654 | 1.2448 | 78.7022 | 1.1368 | 0.0056035 | 0.00025119 | 0.33208 | 0.59868 | {6992FFBA-72E0-4D3C-898B-1A95BB5A0A16} | 163541102 | OLETA 1102 | 41396 | 38.5329 | -120.7649 | OLETA 110241396 | 147 | 342 | 26267.6988 | 11864.1579 | 14403.5408 | 10921.5489 | 13820.0136 | 0.016076 | 0.0079259 | 1.3772 | 16.5625 | 1245 | 0.35863 | 1090 | 0 | 0 | 6.7863 | 1665 | 0
Sierra | 4514 | 12 | 18.0626 | 167 | 92.7798 | 15 | 0.00015222 | 0.066432 | 6.7449 | 112.4829 | 1399.1768 | 12.0084 | 0.44705 | 6.9968 | 1 | 1.0112e-05 | 0.0005777 | 0.071856 | 0.19468 | {6992FFBA-72E0-4D3C-898B-1A95BB5A0A16} | 163541102 | OLETA 1102 | 41396 | 38.5329 | -120.7649 | OLETA 110241396 | 147 | 342 | 26267.6988 | 11864.1579 | 14403.5408 | 10921.5489 | 13820.0136 | 0.0086655 | 0.0022833 | 1.5052 | 11.1333 | 702 | 0.00015168 | 1090 | 0 | 0 | 6.7863 | 2347 | 0
Bay Area | 8624 | 200 | 337.0534 | 311 | 404.6467 | 41 | 0.00012881 | 32.5456 | 0.21001 | 30.1886 | 184.3886 | 0.074057 | 0.43536 | 14.5334 | 1.0337 | 0.0045155 | 9.4996e-05 | 0.64309 | 0.83296 | {0DD641FC-11BF-40FB-8EF7-3A88160AB0B4} | 42011108 | SAN RAFAEL 1108 | 1250 | 37.961 | -122.571 | SAN RAFAEL 11081250 | 38 | 21 | 6484.0136 | 5757.8877 | 726.1259 | 5757.8877 | 726.1259 | 0.0038948 | 0.0052811 | 1.6853 | 7.5854 | 1880 | 0.18514 | 1091 | 0 | 0 | 3.5778 | 1678 | 0
North Coast | 5134 | 0 | 0 | 3 | 1.2707 | 1 | 6.0713e-05 | 74.3354 | 13.1716 | 2822.3542 | 23007.4434 | 314.0968 | 9.6195 | 419.6122 | 1.2987 | 0.0045132 | 0.00079969 | 0 | 0 | {276EDBF0-4288-4842-B2CC-B94871DC6986} | 42631108 | PETALUMA C 1108 | 632 | 38.2572 | -122.801 | PETALUMA C 1108632 | 90 | 74 | 36948.1164 | 23698.3277 | 13249.7887 | 23698.3277 | 13249.7887 | 0.00079969 | 6.0713e-05 |  | 3 | 500 | 0.0045132 | 1092 | 0 | 0 | 14.7255 | 867 | 0
Central Valley | 3987 | 100 | 154.9411 | 228 | 206.1607 | 51 | 8.692e-05 | 48.705 | 6.0558 | 152.8976 | 921.5566 | 22.6108 | 4.0117 | 110.2898 | 1.1306 | 0.0044898 | 0.00023423 | 0.4386 | 0.75156 | {2C34AC51-01A3-44C9-B45A-F5786A7BA8F0} | 163011101 | MARTELL 1101 | circuit_breaker | 38.3691 | -120.7969 | MARTELL 1101circuit_breaker | 399 | 748 | 53779.4966 | 21373.1568 | 32406.3398 | 8464.9135 | 6217.4051 | 0.011946 | 0.0044329 | 1.5494 | 4.4706 | 1301 | 0.22898 | 1093 | 0 | 0 | 5.2599 | 650 | 0
Central Valley | 365 | 109 | 200.0198 | 785 | 407.2133 | 103 | 5.8733e-05 | 60.2955 | 9.9473 | 43.8126 | 145.9661 | 2.3673 | 2.4484 | 29.8907 | 1.1454 | 0.004488 | 0.00025267 | 0.13885 | 0.49119 | {74641153-5847-4D3C-B484-25FD29972F96} | 163351701 | CURTIS 1701 | circuit_breaker | 37.9745 | -120.3199 | CURTIS 1701circuit_breaker | 325 | 464 | 39610.9096 | 19970.3298 | 19640.5798 | 13323.4289 | 11023.2343 | 0.026025 | 0.0060495 | 1.835 | 7.6214 | 1243 | 0.46227 | 1094 | 0 | 0 | 8.2788 | 1122 | 0
Central Coast | 7057 | 338 | 637.8423 | 884 | 902.8561 | 173 | 3.1369e-05 | 125.6247 | 2.4267 | 687.4727 | 4096.0601 | 25.6708 | 6.0483 | 591.9649 | 1.4825 | 0.0044571 | 6.4421e-05 | 0.38235 | 0.70647 | {0BD3EAE8-A4C6-457C-A510-61EFBAEC688F} | 183052113 | TEMPLETON 2113 | A12 | 35.3806 | -120.4432 | TEMPLETON 2113A12 | 211 | 139 | 73929.3785 | 65018.3777 | 8911.0008 | 65018.3777 | 8911.0008 | 0.011145 | 0.0054268 | 1.8871 | 5.1098 | 2099 | 0.77108 | 1095 | 0 | 0 | 40.4005 | 315 | 0
Central Valley | 6237 | 293 | 449.081 | 1113 | 773.8987 | 205 | 6.1624e-05 | 56.8377 | 1.928 | 56.857 | 373.565 | 3.0188 | 3.7942 | 151.1787 | 1.2745 | 0.0044538 | 8.6678e-05 | 0.26325 | 0.58028 | {CF62E6C3-07CA-4DD5-8099-332BF3F2B85C} | 162211101 | CALAVERAS CEMENT 1101 | 4786 | 38.232 | -120.5345 | CALAVERAS CEMENT 11014786 | 233 | 195 | 45830.3614 | 28957.9323 | 16872.4291 | 28957.9323 | 16872.4291 | 0.017769 | 0.012633 | 1.5327 | 5.4293 | 1934 | 0.91303 | 1096 | 0 | 0 | 17.9936 | 1501 | 0
Central Valley | 7850 | 154 | 207.6402 | 240 | 252.0601 | 33 | 8.3174e-05 | 52.0039 | 211.9694 | 3827.1921 | 61867.0187 | 16151.0876 | 4.3064 | 39.9812 | 1.0647 | 0.0044423 | 0.0068369 | 0.64167 | 0.82377 | {4D3D5180-6A6C-4C43-B692-915E3881962C} | 163201102 | WEST POINT 1102 | 72036 | 38.4129 | -120.5501 | WEST POINT 110272036 | 52 | 62 | 5795.9687 | 3794.583 | 2001.3857 | 3794.583 | 2001.3857 | 0.22562 | 0.0027448 | 1.3483 | 7.2727 | 22 | 0.1466 | 1097 | 0 | 0 | 2.3578 | 1502 | 0
Central Coast | 4321 | 606 | 1664.5382 | 1466 | 2109.4602 | 170 | 1.4287e-05 | 330.938 | 18.0879 | 56.6715 | 249.5651 | 14.833 | 10.9641 | 53.2402 | 1.1127 | 0.004437 | 0.00015111 | 0.41337 | 0.78908 | {766BCAEB-8E30-4C4C-8834-E815A7569457} | 182601104 | OCEANO 1104 | Q06 | 35.1341 | -120.5702 | OCEANO 1104Q06 | 288 | 367 | 43622.9598 | 19967.3254 | 23655.6344 | 19967.3254 | 23655.6344 | 0.025688 | 0.0024288 | 2.7468 | 8.6235 | 1586 | 0.75429 | 1098 | 0 | 0 | 12.4071 | 1689 | 0
North Coast | 8923 | 1113 | 1768.9978 | 1612 | 1992.9651 | 147 | 0.00014323 | 31.6078 | 2.2181 | 315.7443 | 4777.2398 | 23.8507 | 0.50446 | 40.1988 | 1.2084 | 0.0044131 | 0.00021119 | 0.69045 | 0.88762 | {999C3E0D-1E31-46AC-B115-3B4EB4A2A32A} | 192171103 | WILLOW CREEK 1103 | 3090 | 40.8889 | -123.5928 | WILLOW CREEK 11033090 | 63 | 42 | 17734.3923 | 16560.5655 | 1173.8268 | 16560.5655 | 1173.8268 | 0.031045 | 0.021055 | 1.5894 | 10.966 | 1377 | 0.64873 | 1099 | 0 | 0 | 10.2903 | 1710 | 0
North Coast | 7477 | 71 | 114.6706 | 79 | 118.0742 | 20 | 0.00016989 | 25.0513 | 1.862 | 74.5279 | 463.0277 | 1.3906 | 0.44878 | 28.732 | 1.0272 | 0.0044052 | 0.00022724 | 0.89873 | 0.97117 | {B01D0AA7-5805-4227-AB93-F941564BB56C} | 43381101 | POINT ARENA 1101 | 83354 | 38.8808 | -123.6621 | POINT ARENA 110183354 | 48 | 21 | 10174.0447 | 8260.8147 | 1913.23 | 8260.8147 | 1913.23 | 0.0045448 | 0.0033977 | 1.6151 | 3.95 | 1324 | 0.088104 | 1100 | 0 | 0 | 5.133 | 892 | 0
Central Valley | 2785 | 132 | 239.8996 | 455 | 346.5072 | 141 | 3.5959e-05 | 123.51 | 15.7465 | 1155.9913 | 8137.6587 | 208.8578 | 8.6804 | 588.8731 | 1.5601 | 0.0043948 | 0.00029363 | 0.29011 | 0.69234 | {138F1A45-4EE4-407C-9580-B6FBC2BCEC83} | 163011103 | MARTELL 1103 | 3152 | 38.3598 | -120.8199 | MARTELL 11033152 | 159 | 150 | 35857.5642 | 27364.6036 | 8492.9605 | 27174.8741 | 8338.0357 | 0.041402 | 0.0050702 | 1.8174 | 3.227 | 1142 | 0.61966 | 1101 | 0 | 0 | 16.8857 | 2411 | 0
Sierra | 1888 | 791 | 904.1466 | 1843 | 1396.6407 | 258 | 3.094e-05 | 141.2866 | 12.4851 | 1873.1058 | 48095.0953 | 1411.2125 | 0.62678 | 29.0563 | 1.1906 | 0.0043945 | 0.00020766 | 0.42919 | 0.64737 | {303E53EF-22EF-468F-BD54-C029D47A56AA} | 152101102 | ALLEGHANY 1102 | circuit_breaker | 39.4656 | -120.8448 | ALLEGHANY 1102circuit_breaker | 155 | 184 | 35009.5358 | 29167.4333 | 5842.1025 | 29167.4333 | 5842.1025 | 0.053576 | 0.0079825 | 1.143 | 7.1434 | 1389 | 1.1338 | 1102 | 0 | 0 | 18.1238 | 426 | 0
Sierra | 256 | 384 | 542.2083 | 1064 | 884.0562 | 108 | 9.2413e-05 | 47.6401 | 60.9468 | 618.5693 | 8618.7157 | 890.0169 | 3.7277 | 45.1648 | 1.1476 | 0.004377 | 0.0023359 | 0.3609 | 0.61332 | {26BF93E0-3094-4C38-AD52-FBEDF4E08E5A} | 152481106 | BRUNSWICK 1106 | 7099 | 39.1699 | -120.9932 | BRUNSWICK 11067099 | 126 | 117 | 23109.8383 | 12185.6359 | 10924.2024 | 12185.6359 | 10924.2024 | 0.25228 | 0.0099806 | 1.412 | 9.8519 | 146 | 0.47272 | 1103 | 0 | 0 | 7.5718 | 386 | 0
Central Valley | 5452 | 17 | 32.9023 | 134 | 63.1028 | 36 | 5.4073e-05 | 89.3402 | 7.3488 | 90.0336 | 462.1828 | 43.7443 | 8.593 | 51.8466 | 1.1963 | 0.0043667 | 0.00020306 | 0.12687 | 0.52141 | {03406AFB-92D3-4CE9-B7EA-72DA34AFA832} | 162991102 | CORRAL 1102 | 14028 | 38.1461 | -120.8611 | CORRAL 110214028 | 184 | 284 | 26243.5371 | 12833.3324 | 13410.2047 | 5856.3944 | 5472.8552 | 0.00731 | 0.0019466 | 1.9354 | 3.7222 | 1403 | 0.1572 | 1104 | 0 | 0 | 3.639 | 658 | 0
Sierra | 208 | 895 | 1252.2243 | 1678 | 1597.75 | 186 | 0.00011584 | 35.9317 | 43.1076 | 455.0847 | 6027.0185 | 706.4348 | 2.7625 | 45.8278 | 1.0945 | 0.0043642 | 0.0021361 | 0.53337 | 0.78374 | {7EA84B2A-124B-4428-A9E1-34C82D90BA62} | 153661103 | APPLE HILL 1103 | 13312 | 38.7437 | -120.7327 | APPLE HILL 110313312 | 286 | 337 | 53470.6898 | 29140.0447 | 24330.6452 | 19652.8137 | 18183.7602 | 0.39732 | 0.021546 | 1.3991 | 9.0215 | 167 | 0.81174 | 1105 | 0 | 0 | 12.2117 | 577 | 0
Central Coast | 5597 | 681 | 1234.4428 | 1938 | 1741.4855 | 283 | 0.00012136 | 37.5811 | 4.3052 | 184.844 | 1024.0466 | 7.6404 | 4.3386 | 86.2975 | 1.1222 | 0.0043257 | 0.00027245 | 0.35139 | 0.70884 | {33400389-0E2B-42A8-BC66-48CCE49F1F75} | 183052110 | TEMPLETON 2110 | N32 | 35.6817 | -120.9365 | TEMPLETON 2110N32 | 318 | 430 | 77756.4228 | 47441.6231 | 30314.7997 | 46049.4952 | 29814.3015 | 0.077104 | 0.034346 | 1.8127 | 6.8481 | 1197 | 1.2242 | 1106 | 0 | 0 | 28.6138 | 2782 | 0
Sierra | 156 | 1084 | 1919.926 | 3079 | 2814.4875 | 476 | 8.7791e-05 | 63.5093 | 13.6473 | 86.2055 | 827.1725 | 38.7411 | 4.266 | 34.7513 | 1.0652 | 0.0043136 | 0.00065592 | 0.35206 | 0.68216 | {B959CC4A-E894-449B-BBA9-D2734BD80359} | 152282101 | MOUNTAIN QUARRIES 2101 | 1346 | 38.8931 | -120.9977 | MOUNTAIN QUARRIES 21011346 | 703 | 477 | 73328.0209 | 49477.6546 | 23850.3663 | 49477.6546 | 23850.3663 | 0.31222 | 0.041788 | 1.7711 | 6.4685 | 608 | 2.0533 | 1107 | 0 | 0 | 30.744 | 1546 | 0
North Coast | 457 | 607 | 972.6774 | 983 | 1177.5397 | 87 | 0.00010661 | 37.7894 | 10.8078 | 81.7634 | 589.9105 | 26.4604 | 4.0097 | 24.9079 | 1.0633 | 0.0042722 | 0.00068222 | 0.6175 | 0.82603 | {E88FFA7F-5F70-49D0-8DB1-373E7BB1124C} | 42571102 | MOLINO 1102 | 51788 | 38.4361 | -122.8721 | MOLINO 110251788 | 300 | 420 | 46660.1471 | 23550.5125 | 23109.6346 | 9018.9359 | 7725.1243 | 0.059353 | 0.0092753 | 1.6024 | 11.2989 | 584 | 0.37168 | 1108 | 0 | 0 | 5.6041 | 2451 | 0
Sierra | 3850 | 835 | 1248.6591 | 1883 | 1720.8235 | 204 | 7.64e-05 | 57.2927 | 20.1547 | 551.5826 | 6700.7791 | 204.9725 | 3.3339 | 133.3559 | 1.2367 | 0.0042368 | 0.00072658 | 0.44344 | 0.72562 | {65B27162-E2B7-4CEC-9138-2917B0C9553F} | 153741101 | DOBBINS 1101 | 5202 | 39.3396 | -121.1946 | DOBBINS 11015202 | 236 | 173 | 37629.3775 | 27474.7329 | 10154.6446 | 26082.7071 | 7078.3099 | 0.14822 | 0.015586 | 1.4954 | 9.2304 | 550 | 0.86432 | 1109 | 0 | 0 | 16.207 | 2363 | 0
North Coast | 3118 | 459 | 974.7208 | 1629 | 1655.4636 | 235 | 7.1492e-05 | 78.6084 | 32.93 | 594.1864 | 4427.7802 | 473.4757 | 5.1544 | 104.542 | 1.1048 | 0.0042313 | 0.0011612 | 0.28177 | 0.58879 | {1A72E14C-38B8-4F2E-A8C3-6BC5686CFD94} | 43471101 | PENNGROVE 1101 | 170 | 38.3288 | -122.6658 | PENNGROVE 1101170 | 382 | 347 | 66019.6613 | 36370.6977 | 29648.9636 | 31125.6451 | 26343.4548 | 0.27289 | 0.016801 | 2.1236 | 6.9319 | 338 | 0.99434 | 1110 | 0 | 0 | 19.3406 | 1750 | 0
North Valley | 3742 | 932 | 1367.4112 | 2235 | 1952.515 | 263 | 0.00021018 | 20.6381 | 25.5027 | 403.9705 | 5678.094 | 871.6527 | 1.9536 | 26.9505 | 1.049 | 0.0042081 | 0.0024069 | 0.417 | 0.70033 | {7010B5A1-248E-4D8C-92BA-99C3D3CD7971} | 103561101 | STILLWATER 1101 | 1320 | 40.6959 | -122.3427 | STILLWATER 11011320 | 313 | 369 | 47079.1986 | 32280.2887 | 14798.9099 | 31197.3185 | 14654.2879 | 0.633 | 0.055278 | 1.4672 | 8.4981 | 136 | 1.1067 | 1111 | 0 | 0 | 19.3851 | 1267 | 0
North Coast | 6423 | 912 | 1142.9966 | 1267 | 1320.0029 | 154 | 9.5537e-05 | 43.1405 | 13.2716 | 3104.3688 | 63176.3223 | 1765.4698 | 0.964 | 47.5077 | 1.0825 | 0.0042079 | 0.00071399 | 0.71981 | 0.8659 | {0A0C5F0B-CE32-47C8-9E33-CC208CAF8F95} | 42281105 | POTTER VALLEY P H 1105 | 76498 | 39.3624 | -123.128 | POTTER VALLEY P H 110576498 | 141 | 168 | 41877.9576 | 23931.4188 | 17946.5388 | 23931.4188 | 17946.5388 | 0.10995 | 0.014713 | 1.2533 | 8.2273 | 559 | 0.64802 | 1112 | 0 | 0 | 14.8703 | 1656 | 0
Bay Area | 3498 | 803 | 1166.5378 | 2694 | 2275.2422 | 169 | 0.00013328 | 30.5956 | 2.7704 | 12.7147 | 85.9174 | 1.0632 | 1.1228 | 6.8001 | 1.269 | 0.0042048 | 0.00024748 | 0.29807 | 0.51271 | {F2E5D603-195F-45A5-9636-597C9B053516} | 42011108 | SAN RAFAEL 1108 | 516 | 37.9861 | -122.5875 | SAN RAFAEL 1108516 | 291 | 1523 | 86695.5688 | 17633.1443 | 69062.4245 | 17633.1443 | 69062.4245 | 0.041825 | 0.022525 | 1.4527 | 15.9408 | 1258 | 0.71062 | 1113 | 0 | 0 | 10.9567 | 1246 | 0
North Valley | 6140 | 825 | 1735.404 | 1563 | 2062.2996 | 142 | 6.3186e-05 | 65.0449 | 6.1283 | 1659.4607 | 34860.5029 | 682.5647 | 0.0096597 | 18.8315 | 1.0528 | 0.0041839 | 0.00023792 | 0.52783 | 0.84149 | {A0DF0310-E76F-4503-848A-EC07BD6D9878} | 103031102 | ORO FINO 1102 | 2040 | 39.935 | -121.6468 | ORO FINO 11022040 | 28 | 6 | 15020.7329 | 14724.8662 | 295.8667 | 14724.8662 | 295.8667 | 0.033785 | 0.0089723 | 2.1035 | 11.007 | 1283 | 0.59411 | 1114 | 0 | 0 | 9.1496 | 587 | 0
North Valley | 1432 | 315 | 557.5161 | 1001 | 791.0839 | 159 | 0.00012119 | 36.4415 | 16.4578 | 135.9631 | 2070.4669 | 235.4098 | 4.0522 | 54.7835 | 1.0436 | 0.0041778 | 0.00078865 | 0.31469 | 0.70475 | {10010FC4-3D49-44D1-8CB1-63E2C5CA1480} | 103401102 | GIRVAN 1102 | 9012 | 40.5805 | -122.4282 | GIRVAN 11029012 | 330 | 259 | 35768.0164 | 25756.1785 | 10011.8379 | 25756.1785 | 10011.8379 | 0.1254 | 0.019269 | 1.7699 | 6.2956 | 505 | 0.66427 | 1115 | 0 | 0 | 16.0041 | 2585 | 0
Central Valley | 2372 | 18 | 28.826 | 156 | 84.192 | 46 | 4.3408e-05 | 97.9686 | 17.0744 | 1200.0504 | 10361.336 | 282.8104 | 7.1216 | 582.7921 | 1.6061 | 0.0041778 | 0.00031864 | 0.11538 | 0.34238 | {DD0025EB-B991-46AA-8D21-AE164B513DA5} | 254452101 | MARIPOSA 2101 | 90180 | 37.558 | -120.0133 | MARIPOSA 210190180 | 56 | 53 | 13610.5644 | 7283.0829 | 6327.4815 | 7283.0829 | 6327.4815 | 0.014657 | 0.0019968 | 1.6014 | 3.3913 | 1080 | 0.19218 | 1116 | 0 | 0 | 4.5255 | 84 | 0
Central Valley | 883 | 604 | 975.8831 | 1778 | 1448.3578 | 242 | 6.4309e-05 | 82.3949 | 17.2255 | 234.3577 | 1272.8275 | 47.9399 | 4.7665 | 65.9829 | 1.1635 | 0.004173 | 0.00052883 | 0.33971 | 0.67379 | {7E0EED7A-2775-40CE-B357-57739361FC2E} | 163761704 | RACETRACK 1704 | 55798 | 37.9759 | -120.4466 | RACETRACK 170455798 | 353 | 432 | 73815.3425 | 37898.11 | 35917.2325 | 37898.11 | 35917.2325 | 0.12798 | 0.015563 | 1.6157 | 7.3471 | 761 | 1.0099 | 1117 | 0 | 0 | 23.5488 | 2101 | 0
Central Valley | 6892 | 636 | 871.4134 | 1860 | 1432.3966 | 145 | 0.00013917 | 32.8865 | 89.0589 | 568.7646 | 8429.1079 | 2418.5313 | 2.1484 | 30.4112 | 1.1124 | 0.004102 | 0.0044127 | 0.34194 | 0.60836 | {6F523CC1-7B62-49B9-AAF8-BD03742BA043} | 163751102 | PINE GROVE 1102 | 83098 | 38.4174 | -120.5969 | PINE GROVE 110283098 | 148 | 254 | 25603.3963 | 13034.6629 | 12568.7334 | 13034.6629 | 12568.7334 | 0.63985 | 0.02018 | 1.3701 | 12.8276 | 46 | 0.5948 | 1118 | 0 | 0 | 8.0994 | 32 | 0
North Coast | 4034 | 153 | 196.8848 | 226 | 224.4966 | 34 | 5.7583e-05 | 57.7221 | 0.43176 | 236.0028 | 2721.0825 | 2.379 | 2.1488 | 70.3488 | 1.2093 | 0.0040704 | 4.6823e-05 | 0.67699 | 0.87701 | {7CFF91C6-6122-459F-BD71-B9F17BE39EB0} | 42771114 | UKIAH 1114 | 528 | 39.0975 | -123.1724 | UKIAH 1114528 | 147 | 150 | 27619.9851 | 19731.4227 | 7888.5624 | 4515.409 | 2727.9786 | 0.001592 | 0.0019578 | 1.2868 | 6.6471 | 2269 | 0.13839 | 1119 | 0 | 0 | 2.8057 | 108 | 0
Sierra | 2508 | 721 | 1267.9499 | 2803 | 2100.256 | 299 | 8.2094e-05 | 63.0643 | 19.0396 | 148.7128 | 925.1378 | 56.724 | 6.1415 | 96.2303 | 1.3088 | 0.0040668 | 0.00088255 | 0.25722 | 0.60371 | {0B887AE7-B7B8-4CE1-A4B2-3FC68E0D65B0} | 153081110 | PLACERVILLE 1110 | 19582 | 38.7528 | -120.8225 | PLACERVILLE 111019582 | 412 | 370 | 62066.9272 | 35889.5226 | 26177.4046 | 35889.5226 | 26177.4046 | 0.26388 | 0.024546 | 1.7586 | 9.3746 | 456 | 1.216 | 1120 | 0 | 0 | 22.3007 | 1458 | 0
North Coast | 8139 | 255 | 382.5605 | 559 | 569.4987 | 99 | 0.00013259 | 30.7228 | 32.432 | 642.1906 | 4847.6797 | 435.1433 | 2.3977 | 68.654 | 1.0993 | 0.0040598 | 0.0017991 | 0.45617 | 0.67175 | {648AAC1E-48AF-43F7-8E9A-745D399294ED} | 42571102 | MOLINO 1102 | 6917 | 38.3873 | -122.9728 | MOLINO 11026917 | 74 | 85 | 19600.5838 | 11483.727 | 8116.8567 | 11483.727 | 8116.8567 | 0.17811 | 0.013127 | 1.5002 | 5.6465 | 194 | 0.40192 | 1121 | 0 | 0 | 7.1357 | 1288 | 0
Central Coast | 8644 | 9 | 12.6749 | 210 | 63.9648 | 38 | 5.3402e-05 | 87.2144 | 8.1575 | 393.8174 | 2586.9109 | 71.5173 | 4.9677 | 372.2876 | 1.2502 | 0.0040576 | 0.00034422 | 0.042857 | 0.19815 | {35122D11-1E93-423C-905C-FD3596B054C4} | 182611103 | PASO ROBLES 1103 | N52 | 35.6885 | -120.7653 | PASO ROBLES 1103N52 | 44 | 21 | 12177.5719 | 10495.5857 | 1681.9862 | 10495.5857 | 1681.9862 | 0.01308 | 0.0020293 | 1.4083 | 5.5263 | 1022 | 0.15419 | 1122 | 0 | 0 | 6.5217 | 1695 | 0
North Coast | 2193 | 2947 | 5240.1495 | 4195 | 5972.0337 | 332 | 0.00014596 | 28.9969 | 12.8521 | 200.4073 | 1638.6405 | 81.0167 | 1.893 | 34.29 | 1.0486 | 0.0040474 | 0.00096149 | 0.7025 | 0.87745 | {937FE0BF-1949-4B31-99B0-C96DCB7F5DAB} | 42571102 | MOLINO 1102 | 318 | 38.4048 | -122.9485 | MOLINO 1102318 | 351 | 366 | 57496.3603 | 31101.718 | 26394.6423 | 31101.718 | 26394.6423 | 0.31921 | 0.04846 | 1.7781 | 12.6355 | 430 | 1.3437 | 1123 | 0 | 0 | 19.3257 | 2645 | 0
Central Valley | 6650 | 54 | 98.2871 | 264 | 171.9147 | 83 | 3.5176e-05 | 100.7369 | 5.2291 | 544.4415 | 1892.7008 | 15.4304 | 9.9111 | 649.1659 | 1.4655 | 0.0040471 | 0.00012288 | 0.20455 | 0.57172 | {FCFE42BE-9C18-409B-9916-4C477F3B3051} | 163541101 | OLETA 1101 | 51740 | 38.4525 | -120.9131 | OLETA 110151740 | 140 | 101 | 43359.9292 | 33990.1368 | 9369.7924 | 20448.965 | 6872.9231 | 0.010199 | 0.0029196 | 1.8201 | 3.1807 | 1736 | 0.33591 | 1124 | 0 | 0 | 12.7064 | 686 | 0
North Coast | 5862 | 36 | 46.5894 | 142 | 93.1303 | 20 | 6.1862e-05 | 94.323 | 4.0526 | 31.0419 | 263.238 | 3.2188 | 3.7967 | 46.2551 | 1.1439 | 0.0040003 | 0.00015589 | 0.25352 | 0.50026 | {2993BF9E-90A5-4634-AB04-8D39B8C96792} | 43411102 | CALPELLA 1102 | circuit_breaker | 39.197 | -123.1926 | CALPELLA 1102circuit_breaker | 219 | 252 | 27584.2787 | 14778.125 | 12806.1537 | 3000.9026 | 1821.8261 | 0.0031178 | 0.0012372 | 1.2942 | 7.1 | 1562 | 0.080005 | 1125 | 0 | 0 | 1.8647 | 782 | 0
Central Coast | 3041 | 1 | 1.2277 | 1 | 1.2277 | 1 | 2.351e-05 | 169.9145 |  |  |  |  | 14.5376 | 425.8354 | 1.7788 | 0.0039947 | 2.351e-05 | 1 | 1 | {3C29C0B2-611E-468C-9FBC-81B8ED82FB52} | 182981102 | JOLON 1102 | 7070 | 35.9643 | -121.1174 | JOLON 11027070 | 160 | 120 | 37107.4896 | 26486.1632 | 10621.3264 | 6723.3881 | 2319.5448 | 2.351e-05 | 2.351e-05 | 1.2277 | 1 | 2555 | 0.0039947 | 1126 | 0 | 0 | 4.1777 | 616 | 0
Bay Area | 9446 | 14 | 21.0134 | 95 | 67.617 | 8 | 6.5089e-05 | 59.5093 | 1.0254 | 5.4222 | 24.7577 | 0.036183 | 3.1574 | 37.8287 | 1.3791 | 0.0039945 | 6.4858e-05 | 0.14737 | 0.31077 | {E417384C-CD10-4D00-B136-62F02EAF1C4A} | 43432102 | SILVERADO 2102 | circuit_breaker | 38.5 | -122.4594 | SILVERADO 2102circuit_breaker | 35 | 25 | 4341.412 | 2761.2179 | 1580.1941 | 345.0876 | 358.181 | 0.00051887 | 0.00052071 | 1.501 | 11.875 | 2095 | 0.031956 | 1127 | 0 | 0 | 0.21443 | 2677 | 0
Sierra | 3340 | 1128 | 1682.9183 | 2532 | 2328.1145 | 233 | 8.3938e-05 | 45.0751 | 75.9748 | 717.4848 | 9051.0444 | 1371.3663 | 2.643 | 44.7921 | 1.15 | 0.0039877 | 0.0031775 | 0.4455 | 0.72287 | {477268D6-DE4E-4795-ABA6-DB4CC4C4808D} | 152691104 | HIGGINS 1104 | 324510 | 39.1033 | -121.0435 | HIGGINS 1104324510 | 213 | 193 | 39073.6592 | 20001.4265 | 19072.2327 | 20001.4265 | 19072.2327 | 0.74036 | 0.019558 | 1.4919 | 10.867 | 95 | 0.92912 | 1128 | 0 | 0 | 12.4283 | 470 | 0
North Valley | 8293 | 49 | 92.1102 | 170 | 148.2955 | 51 | 5.5279e-05 | 95.6176 | 24.1895 | 1518.8597 | 18437.8827 | 897.4777 | 3.4805 | 232.8631 | 1.4641 | 0.0039502 | 0.00065902 | 0.28824 | 0.62113 | {2426BD3B-3A69-4A04-A051-7581B14322B3} | 102911105 | WYANDOTTE 1105 | circuit_breaker | 39.4917 | -121.5411 | WYANDOTTE 1105circuit_breaker | 27 | 1 | 21713.0262 | 21689.0277 | 23.9985 | 15173.6855 | 0 | 0.03361 | 0.0028192 | 1.8798 | 3.3333 | 604 | 0.20146 | 1129 | 0 | 0 | 9.4285 | 2430 | 0
Central Valley | 7336 | 72 | 114.8531 | 505 | 278.3503 | 103 | 4.9478e-05 | 68.6501 | 2.8261 | 578.3191 | 2615.2951 | 13.1339 | 2.7766 | 150.3275 | 1.3471 | 0.0039498 | 8.5218e-05 | 0.14257 | 0.41262 | {0486726A-698F-459A-9224-3E1921E2AC68} | 163451702 | FROGTOWN 1702 | 7134 | 38.0554 | -120.5345 | FROGTOWN 17027134 | 208 | 142 | 46171.8287 | 36552.2416 | 9619.5871 | 28875.1403 | 7367.5521 | 0.0087775 | 0.0050963 | 1.5952 | 4.9029 | 1946 | 0.40683 | 1130 | 0 | 0 | 17.9422 | 173 | 0
Central Coast | 3521 | 133 | 303.4133 | 873 | 720.5578 | 119 | 1.662e-05 | 257.7338 | 25.0729 | 82.3811 | 377.3165 | 22.3652 | 13.564 | 88.8938 | 1.1199 | 0.0039437 | 0.00018598 | 0.15235 | 0.42108 | {F2D88342-EA4A-4DE6-A5A2-0FD601C586EE} | 182601104 | OCEANO 1104 | V38 | 35.1274 | -120.5692 | OCEANO 1104V38 | 351 | 609 | 60078.4462 | 27980.8002 | 32097.646 | 18252.5164 | 16012.1022 | 0.022132 | 0.0019778 | 2.2813 | 7.3361 | 1461 | 0.46929 | 1131 | 0 | 0 | 11.3416 | 2610 | 0
Central Valley | 3747 | 150 | 205.0853 | 611 | 382.9644 | 125 | 1.1045e-05 | 286.5405 | 4.6689 | 1767.8612 | 11591.9038 | 74.0452 | 10.1717 | 930.4681 | 1.7438 | 0.0039417 | 3.1699e-05 | 0.2455 | 0.53552 | {863BED83-C87B-4B95-B9B9-262F78012E12} | 254601103 | SAND CREEK 1103 | 7070 | 36.6464 | -119.1499 | SAND CREEK 11037070 | 127 | 108 | 34640.0169 | 28595.1882 | 6044.8287 | 28595.1882 | 6044.8287 | 0.0039624 | 0.0013806 | 1.3672 | 4.888 | 2445 | 0.49271 | 1132 | 0 | 0 | 17.7682 | 1585 | 0
Central Coast | 8520 | 45 | 77.2406 | 362 | 281.3325 | 41 | 4.5217e-05 | 95.2177 | 11.4899 | 45.6291 | 202.2384 | 5.4915 | 4.2588 | 38.6184 | 1.0977 | 0.0039331 | 0.00042823 | 0.12431 | 0.27455 | {A107EF70-1BBB-446A-BE85-B69D29852E35} | 182631107 | SAN LUIS OBISPO 1107 | V62 | 35.1889 | -120.7189 | SAN LUIS OBISPO 1107V62 | 107 | 92 | 14439.5935 | 11135.8835 | 3303.71 | 10856.7862 | 2903.6967 | 0.017558 | 0.0018539 | 1.7165 | 8.8293 | 895 | 0.16126 | 1133 | 0 | 0 | 6.7461 | 2474 | 0
Bay Area | 5959 | 24 | 39.052 | 65 | 63.1399 | 3 | 0.00016476 | 23.8478 | 3.7685 | 74.0574 | 154.8059 | 0.58338 | 1.0118 | 7.0137 | 1.0052 | 0.0039291 | 0.00031739 | 0.36923 | 0.6185 | {0DCD5A2D-5C30-407E-83E1-35F7DE42F7D2} | 42011108 | SAN RAFAEL 1108 | 1247 | 37.9737 | -122.6127 | SAN RAFAEL 11081247 | 8 | 28 | 1830.2617 | 414.4526 | 1415.809 | 414.4526 | 1415.809 | 0.00095216 | 0.00049427 | 1.6272 | 21.6667 | 1084 | 0.011787 | 1134 | 0 | 0 | 0.25753 | 974 | 0
Bay Area | 7100 | 74 | 145.5218 | 726 | 554.8732 | 89 | 6.9078e-05 | 57.2067 | 0.83898 | 104.1991 | 500.9189 | 2.0885 | 3.3918 | 89.7409 | 1.0962 | 0.0039165 | 6.4694e-05 | 0.10193 | 0.26226 | {009FED72-F984-488A-870A-FBDD7926AC29} | 14232108 | SAN RAMON 2108 | 53732 | 37.7758 | -121.9974 | SAN RAMON 210853732 | 121 | 102 | 22722.0138 | 12570.9742 | 10151.0396 | 12570.9742 | 10151.0396 | 0.0057578 | 0.0061479 | 1.9665 | 8.1573 | 2096 | 0.34857 | 1135 | 0 | 0 | 7.8112 | 1995 | 0
North Valley | 2548 | 372 | 495.0369 | 1304 | 914.073 | 138 | 8.6001e-05 | 45.3708 | 11.606 | 262.3886 | 3291.6952 | 93.0734 | 0.57181 | 14.9259 | 1.0193 | 0.0038943 | 0.00055186 | 0.28528 | 0.54157 | {2D79CCBE-1B8B-472A-B9BB-B34254CCD666} | 102541102 | VOLTA 1102 | 1504 | 40.4937 | -121.8736 | VOLTA 11021504 | 146 | 94 | 18445.4404 | 13357.6434 | 5087.797 | 13357.6434 | 5087.797 | 0.076157 | 0.011868 | 1.3307 | 9.4493 | 733 | 0.53742 | 1136 | 0 | 0 | 8.3001 | 2651 | 0
Central Valley | 8805 | 31 | 72.3784 | 281 | 175.2443 | 42 | 5.9937e-05 | 63.8939 | 4.6851 | 168.7275 | 834.837 | 8.1979 | 4.5074 | 446.1832 | 1.5886 | 0.0038911 | 0.00015067 | 0.11032 | 0.41301 | {CC378BAE-BD49-4ABE-8599-52019F7E517A} | 163341103 | CLAY 1103 | 59714 | 38.3395 | -120.9268 | CLAY 110359714 | 36 | 25 | 9476.6353 | 7453.2846 | 2023.3507 | 7453.2846 | 2023.3507 | 0.0063282 | 0.0025174 | 2.3348 | 6.6905 | 1589 | 0.16343 | 1137 | 0 | 0 | 4.6313 | 1446 | 0
Central Valley | 7781 | 1 | 1.246 | 13 | 5.5563 | 2 | 8.0582e-06 | 481.4026 | 0.58465 | 638.9394 | 2708.7876 | 1.5837 | 3.2876 | 2004.3556 | 1.896 | 0.0038792 | 6.2953e-06 | 0.076923 | 0.22425 | {59412086-F782-4166-B6FC-4A718057E9E9} | 253642104 | POSO MOUNTAIN 2104 | 48268 | 35.4995 | -118.9051 | POSO MOUNTAIN 210448268 | 42 | 8 | 8811.4991 | 8339.3842 | 472.1149 | 7515.6606 | 472.1149 | 1.2591e-05 | 1.6116e-05 | 1.246 | 6.5 | 2837 | 0.0077584 | 1138 | 0 | 0 | 4.67 | 2270 | 0
Central Valley | 1955 | 462 | 704.121 | 2146 | 1484.3959 | 377 | 8.5149e-05 | 45.436 | 30.759 | 489.2061 | 3682.0587 | 206.4929 | 4.9568 | 134.999 | 1.2858 | 0.0038488 | 0.0011511 | 0.21528 | 0.47435 | {0D0FEEBA-0BD3-4962-B35B-0A3278052F45} | 162161101 | ELECTRA 1101 | circuit_breaker | 38.3309 | -120.6721 | ELECTRA 1101circuit_breaker | 383 | 279 | 75175.9153 | 51915.3729 | 23260.5424 | 51915.3729 | 23260.5424 | 0.43396 | 0.032101 | 1.5241 | 5.6923 | 342 | 1.451 | 1139 | 0 | 0 | 32.2587 | 478 | 0
Sierra | 1073 | 1084 | 1535.0462 | 2318 | 2111.1 | 228 | 0.00014735 | 26.572 | 49.6798 | 1762.1525 | 29671.0967 | 2492.524 | 1.9283 | 36.0039 | 1.0792 | 0.0038346 | 0.0035539 | 0.46764 | 0.72713 | {9DC430E4-865B-40A1-B9ED-F689C9145BC5} | 152471101 | COLUMBIA HILL 1101 | 764 | 39.367 | -121.0461 | COLUMBIA HILL 1101764 | 203 | 212 | 38960.5283 | 23872.6753 | 15087.853 | 23872.6753 | 15087.853 | 0.81029 | 0.033595 | 1.4161 | 10.1667 | 77 | 0.8743 | 1140 | 0 | 0 | 14.8338 | 452 | 0
North Coast | 2182 | 253 | 658.835 | 262 | 663.3429 | 41 | 3.9638e-05 | 156.3145 | 2.2808 | 158.4569 | 514.5425 | 2.9767 | 6.6418 | 370.6 | 1.2894 | 0.0069651 | 6.2032e-05 | 0.96565 | 0.9932 | {26714021-3ECA-430A-89F2-F363DC8CF00F} | 42271103 | COTATI 1103 | 148 | 38.2415 | -122.9053 | COTATI 1103148 | 145 | 154 | 29440.6349 | 24952.5401 | 4488.0948 | 23990.7662 | 4324.6019 | 0.0025433 | 0.0016252 | 2.6041 | 6.3902 | 2116 | 0.28557 | 1141 | 0 | 0 | 14.9072 | 1618 | 0
Bay Area | 2182 | 143 | 393.8806 | 243 | 437.3886 | 38 | 3.4151e-05 | 15.1703 | 1.1095 | 9.1884 | 34.9914 | 0.27652 | 1.7393 | 122.3926 | 1.2746 | 0.0004463 | 3.963e-05 | 0.58848 | 0.90053 | {26714021-3ECA-430A-89F2-F363DC8CF00F} | 42271103 | COTATI 1103 | 148 | 38.2415 | -122.9053 | COTATI 1103148 | 145 | 154 | 29440.6349 | 24952.5401 | 4488.0948 | 23990.7662 | 4324.6019 | 0.0015059 | 0.0012977 | 2.7544 | 6.3947 | 2347 | 0.01696 | 1141 | 0 | 0 | 14.9072 | 2788 | 0
North Coast | 513 | 61 | 108.2065 | 91 | 123.5811 | 21 | 9.8398e-05 | 30.8509 | 4.8408 | 117.8209 | 457.6375 | 3.6828 | 1.1321 | 66.9625 | 1.1411 | 0.0038233 | 0.00049818 | 0.67033 | 0.87559 | {E76F208E-D030-4954-AE4B-2E5BE9D9580C} | 42811111 | MONTE RIO 1111 | 292 | 38.4614 | -123.0424 | MONTE RIO 1111292 | 229 | 380 | 50430.3708 | 31768.7358 | 18661.6349 | 22117.1152 | 12102.8451 | 0.010462 | 0.0020664 | 1.7739 | 4.3333 | 789 | 0.08029 | 1142 | 0 | 0 | 13.7429 | 928 | 0
Sierra | 953 | 1602 | 2227.2118 | 3936 | 3330.069 | 314 | 7.9424e-05 | 58.1182 | 33.4467 | 330.3454 | 4690.1949 | 500.9602 | 4.7986 | 43.8437 | 1.1058 | 0.0038102 | 0.0013532 | 0.40701 | 0.66882 | {D517BDE5-67A5-45A9-903B-DF9F687C44D8} | 152481106 | BRUNSWICK 1106 | 51484 | 39.1908 | -120.9998 | BRUNSWICK 110651484 | 519 | 551 | 76781.2555 | 40473.5667 | 36307.6889 | 32219.8738 | 31081.3069 | 0.4249 | 0.024939 | 1.3903 | 12.535 | 281 | 1.1964 | 1143 | 0 | 0 | 20.0205 | 1747 | 0
Sierra | 2645 | 0 | 0 | 4 | 1.5806 | 1 | 4.0018e-05 | 95.2072 | 6.8998 | 27.1321 | 58.0209 | 0.40033 | 9.4602 | 52.0666 | 1.0398 | 0.00381 | 0.00027611 | 0 | 0 | {C3E0B410-F242-443E-BF4E-9C519E692FDB} | 152561106 | PENRYN 1106 | circuit_breaker | 38.8445 | -121.1669 | PENRYN 1106circuit_breaker | 423 | 656 | 50250.0928 | 22408.5903 | 27841.5025 | 70.2637 | 13.3203 | 0.00027611 | 4.0018e-05 |  | 4 | 1184 | 0.00381 | 1144 | 0 | 0 | 0.04366 | 2598 | 0
Sierra | 5451 | 446 | 620.0252 | 1175 | 969.2878 | 122 | 8.341e-05 | 44.4981 | 66.9987 | 1430.0036 | 17479.6594 | 2086.3659 | 1.6298 | 36.497 | 1.1091 | 0.0037984 | 0.0026712 | 0.37957 | 0.63967 | {D7F1D14A-5B2A-48EF-B12A-9197AE3BCA5E} | 152282101 | MOUNTAIN QUARRIES 2101 | 2422 | 38.9 | -120.9075 | MOUNTAIN QUARRIES 21012422 | 117 | 86 | 19076.4853 | 13951.5772 | 5124.908 | 13951.5772 | 5124.908 | 0.32588 | 0.010176 | 1.3902 | 9.6311 | 120 | 0.46341 | 1145 | 0 | 0 | 8.6691 | 2006 | 0
Sierra | 3652 | 1322 | 1685.0243 | 2912 | 2406.8555 | 205 | 0.00014476 | 27.2035 | 25.7206 | 244.6546 | 3612.7214 | 266.8833 | 0.44664 | 8.8028 | 1.0666 | 0.0037979 | 0.0017078 | 0.45398 | 0.70009 | {FE85142D-4AEA-430F-BD77-45CC919584AA} | 152181101 | FORESTHILL 1101 | 50486 | 38.9928 | -120.8827 | FORESTHILL 110150486 | 319 | 610 | 51377.1243 | 18756.9603 | 32620.164 | 18756.9603 | 32620.164 | 0.3501 | 0.029675 | 1.2746 | 14.2049 | 207 | 0.77858 | 1146 | 0 | 0 | 11.655 | 1380 | 0
Sierra | 2283 | 1105 | 1436.7814 | 2445 | 2061.424 | 306 | 6.1018e-05 | 65.8113 | 183.7127 | 2498.1765 | 51998.2294 | 22411.4541 | 0.65958 | 20.9799 | 1.047 | 0.0037933 | 0.0049886 | 0.45194 | 0.69698 | {2D25C954-D426-4ADF-B1A4-921B2F2ACD48} | 152481105 | BRUNSWICK 1105 | 2140 | 39.2895 | -120.9863 | BRUNSWICK 11052140 | 589 | 507 | 96782.3022 | 55502.9271 | 41279.3751 | 55502.9271 | 41279.3751 | 1.5265 | 0.018671 | 1.3003 | 7.9902 | 37 | 1.1607 | 1147 | 0 | 0 | 34.4879 | 954 | 0
North Coast | 50 | 128 | 172.7769 | 381 | 297.8793 | 41 | 6.5468e-05 | 49.3997 | 12.5352 | 270.1636 | 3450.2643 | 160.5624 | 1.5692 | 19.3143 | 1.2338 | 0.0037804 | 0.00032623 | 0.33596 | 0.58002 | {19F00F46-8DF2-4369-8C23-B78BEB3B793E} | 43071102 | DUNBAR 1102 | 448 | 38.3443 | -122.5145 | DUNBAR 1102448 | 222 | 448 | 37309.5847 | 14544.1744 | 22765.4103 | 3456.1423 | 4298.9074 | 0.013375 | 0.0026842 | 1.3498 | 9.2927 | 1064 | 0.155 | 1148 | 0 | 0 | 2.1475 | 273 | 0
Sierra | 5051 | 250 | 478.4029 | 962 | 691.1174 | 105 | 6.792e-05 | 62.8702 | 4.4595 | 241.9204 | 1905.6681 | 15.7709 | 3.671 | 108.8192 | 1.3285 | 0.0037779 | 0.0001674 | 0.25988 | 0.69222 | {ABE5C26B-A76B-46B8-A04C-0EC15FF8F909} | 103191101 | BANGOR 1101 | 1806 | 39.364 | -121.3602 | BANGOR 11011806 | 106 | 68 | 17961.6544 | 14483.9765 | 3477.678 | 13609.8138 | 3477.678 | 0.017577 | 0.0071316 | 1.9136 | 9.1619 | 1526 | 0.39668 | 1149 | 0 | 0 | 8.4567 | 501 | 0
Central Coast | 8418 | 350 | 571.0463 | 732 | 805.6644 | 159 | 0.00018055 | 26.313 | 0.27587 | 117.1299 | 569.0038 | 0.37094 | 2.0057 | 189.4758 | 1.2037 | 0.0037739 | 0.00011646 | 0.47814 | 0.70879 | {3A07B299-3D05-42C7-8DB9-4F2F009C8698} | 183052110 | TEMPLETON 2110 | N30 | 35.6261 | -120.8962 | TEMPLETON 2110N30 | 132 | 82 | 39132.1201 | 32940.3855 | 6191.7346 | 32940.3855 | 6191.7346 | 0.018517 | 0.028707 | 1.6316 | 4.6038 | 1767 | 0.60006 | 1150 | 0 | 0 | 20.4682 | 2551 | 0
North Coast | 5825 | 224 | 268.1539 | 481 | 412.8203 | 71 | 7.8671e-05 | 54.0292 | 7.566 | 113.3601 | 785.6081 | 18.4757 | 1.6054 | 37.9998 | 1.0737 | 0.0037707 | 0.00030882 | 0.4657 | 0.64957 | {7F16B5BC-4060-4BCC-9EE1-D9EAFE5FD541} | 43321103 | RINCON 1103 | 198 | 38.4982 | -122.6537 | RINCON 1103198 | 96 | 65 | 20370.9662 | 10388.1795 | 9982.7867 | 10388.1795 | 9982.7867 | 0.021926 | 0.0055856 | 1.1971 | 6.7746 | 1102 | 0.26772 | 1151 | 0 | 0 | 6.4549 | 845 | 0
Bay Area | 293 | 278 | 443.6166 | 535 | 577.8656 | 45 | 4.0402e-05 | 104.1009 | 1.0903 | 8.9113 | 38.6545 | 0.43903 | 3.1314 | 57.8624 | 1.0673 | 0.0037478 | 4.0936e-05 | 0.51963 | 0.76768 | {3FFF1795-1315-4A71-8E91-178B9A0CCDE5} | 14662112 | TASSAJARA 2112 | D514R | 37.8226 | -121.9235 | TASSAJARA 2112D514R | 217 | 206 | 14840.8915 | 7666.4167 | 7174.4748 | 4376.3944 | 4392.6153 | 0.0018421 | 0.0018181 | 1.5957 | 11.8889 | 2330 | 0.16865 | 1152 | 0 | 0 | 2.7194 | 699 | 0
Sierra | 9639 | 21 | 33.6769 | 101 | 65.8006 | 11 | 4.6074e-05 | 78.4839 | 21.584 | 195.0317 | 810.8556 | 20.5934 | 8.9224 | 170.1772 | 1.3878 | 0.0037287 | 0.00066207 | 0.20792 | 0.5118 | {8C53EC31-B3AB-4E33-B852-46094C79DBC8} | 152691107 | HIGGINS 1107 | 746082 | 39.035 | -121.0819 | HIGGINS 1107746082 | 11 | 3 | 1689.7348 | 1365.375 | 324.3599 | 1365.375 | 324.3599 | 0.0072828 | 0.00050682 | 1.6037 | 9.1818 | 601 | 0.041016 | 1153 | 0 | 0 | 0.8484 | 71 | 0
Central Valley | 5573 | 874 | 1194.009 | 2332 | 1829.9309 | 330 | 4.9052e-05 | 74.668 | 4.4368 | 123.4842 | 1117.1243 | 14.5014 | 4.8592 | 101.6711 | 1.2267 | 0.0037235 | 0.00013786 | 0.37479 | 0.65249 | {B247F56B-7C52-4365-95E5-8882465CCCBA} | 252531103 | SAN JOAQUIN #3 1103 | 5100 | 37.2311 | -119.4942 | SAN JOAQUIN #3 11035100 | 367 | 538 | 71356.1394 | 42249.6443 | 29106.4951 | 42249.6443 | 29106.4951 | 0.045495 | 0.016187 | 1.3661 | 7.0667 | 1644 | 1.2288 | 1154 | 0 | 0 | 26.2527 | 1814 | 0
Bay Area | 2315 | 16 | 18.8421 | 243 | 148.3989 | 36 | 5.6492e-05 | 64.9809 | 14.8258 | 883.847 | 11165.7369 | 328.4257 | 0.27538 | 47.78 | 1.0675 | 0.0037177 | 0.00042952 | 0.065844 | 0.12697 | {53821A46-8FEE-4585-B4C8-79B31D43CD6A} | 42291101 | OLEMA 1101 | 320 | 38.0644 | -122.8051 | OLEMA 1101320 | 218 | 350 | 47659.3119 | 21386.8301 | 26272.4819 | 5064.1889 | 460.262 | 0.015463 | 0.0020337 | 1.1776 | 6.75 | 892 | 0.13384 | 1155 | 0 | 0 | 3.1467 | 1928 | 0
North Coast | 8018 | 59 | 96.7544 | 163 | 152.5933 | 29 | 5.5131e-05 | 102.2365 | 18.6778 | 84.8914 | 471.529 | 80.0102 | 7.6506 | 77.6087 | 1.3035 | 0.0037007 | 0.00084416 | 0.36196 | 0.63407 | {25F749B3-A74D-4E71-A304-4CB2AAD2E132} | 42271102 | COTATI 1102 | 282 | 38.2844 | -122.6892 | COTATI 1102282 | 114 | 142 | 16741.3161 | 8211.2885 | 8530.0276 | 4768.5619 | 3860.0292 | 0.024481 | 0.0015988 | 1.6399 | 5.6207 | 475 | 0.10732 | 1156 | 0 | 0 | 2.963 | 78 | 0
North Coast | 570 | 961 | 1564.7043 | 1129 | 1645.9978 | 108 | 7.6256e-05 | 45.2676 | 3.3607 | 113.1407 | 687.5226 | 6.6988 | 0.58096 | 25.3638 | 1.0531 | 0.003681 | 0.00016439 | 0.8512 | 0.95061 | {72A22D65-E2E8-42C5-897F-8C8D23CE5089} | 43381101 | POINT ARENA 1101 | circuit_breaker | 38.9123 | -123.6794 | POINT ARENA 1101circuit_breaker | 145 | 105 | 29465.8404 | 18269.3482 | 11196.4922 | 18269.3482 | 11196.4922 | 0.017754 | 0.0082357 | 1.6282 | 10.4537 | 1535 | 0.39755 | 1157 | 0 | 0 | 11.352 | 438 | 0
Sierra | 1867 | 1162 | 1451.268 | 2929 | 2214.5557 | 195 | 0.00015799 | 24.4519 | 116.2195 | 1850.3268 | 29116.0943 | 8117.0557 | 1.2988 | 21.282 | 1.1733 | 0.0036482 | 0.0071947 | 0.39672 | 0.65533 | {955B96CF-04BC-4DDA-A99C-F3551BD93482} | 152282101 | MOUNTAIN QUARRIES 2101 | 1184 | 38.8993 | -120.8546 | MOUNTAIN QUARRIES 21011184 | 241 | 317 | 36232.4138 | 18954.6073 | 17277.8065 | 18770.5875 | 17277.8065 | 1.403 | 0.030809 | 1.2489 | 15.0205 | 21 | 0.7114 | 1158 | 0 | 0 | 11.6635 | 120 | 0
North Coast | 7128 | 34 | 50.4324 | 110 | 99.2575 | 23 | 5.3141e-05 | 64.5116 | 1.786 | 69.9774 | 656.3895 | 2.2023 | 2.0909 | 86.6901 | 1.1446 | 0.0036476 | 7.4298e-05 | 0.30909 | 0.5081 | {B7169D14-D576-4EBC-83AD-DD429DE5E777} | 42891102 | GEYSERVILLE 1102 | circuit_breaker | 38.7097 | -122.9079 | GEYSERVILLE 1102circuit_breaker | 133 | 168 | 21764.22 | 11834.3236 | 9929.8964 | 3579.9474 | 2383.0886 | 0.0017089 | 0.0012223 | 1.4833 | 4.7826 | 2022 | 0.083896 | 1159 | 0 | 0 | 2.2245 | 1139 | 0
North Valley | 9200 | 18 | 21.9239 | 61 | 42.8421 | 21 | 3.727e-05 | 96.3025 | 4.2302 | 1781.8534 | 38946.1402 | 161.1129 | 0.038875 | 48.4885 | 1.3082 | 0.0036362 | 4.3807e-05 | 0.29508 | 0.51174 | {2C93052B-CAB6-4039-91C2-ECB9C837F00A} | 102211103 | BUCKS CREEK 1103 | circuit_breaker | 39.9115 | -121.327 | BUCKS CREEK 1103circuit_breaker | 57 | 6 | 3820.3163 | 3699.7995 | 120.5168 | 3699.7995 | 120.5168 | 0.00091994 | 0.00078266 | 1.218 | 2.9048 | 2292 | 0.076361 | 1160 | 0 | 0 | 2.2989 | 939 | 0
Central Valley | 5124 | 12 | 14.7326 | 37 | 23.6343 | 12 | 1.1119e-05 | 324.017 | 1.0157 | 292.7622 | 1143.4438 | 5.5748 | 5.7764 | 1251.5019 | 1.4873 | 0.0036227 | 1.0189e-05 | 0.32432 | 0.62335 | {7C3F27CE-B3FE-4A3A-A517-4F1EC2F3B587} | 252921108 | STONE CORRAL 1108 | 7100 | 36.4928 | -119.1764 | STONE CORRAL 11087100 | 142 | 175 | 36307.0589 | 29507.2094 | 6799.8495 | 3682.723 | 766.1549 | 0.00012227 | 0.00013343 | 1.2277 | 3.0833 | 2785 | 0.043472 | 1161 | 0 | 0 | 2.2883 | 2138 | 0
Central Coast | 2816 | 1079 | 1555.6818 | 4190 | 3524.1602 | 581 | 6.6349e-05 | 61.9825 | 0.54594 | 67.0522 | 302.5704 | 0.85407 | 2.8157 | 103.2784 | 1.1557 | 0.0035928 | 5.1373e-05 | 0.25752 | 0.44143 | {F2DB4641-1C59-4A03-8B1A-285CBA9763E2} | 183052110 | TEMPLETON 2110 | R90 | 35.5581 | -120.7772 | TEMPLETON 2110R90 | 693 | 471 | 150657.1596 | 120177.2391 | 30479.9205 | 106123.5164 | 25635.5656 | 0.029848 | 0.038549 | 1.4418 | 7.2117 | 2221 | 2.0874 | 1162 | 0 | 0 | 65.9421 | 1129 | 0
North Valley | 3235 | 424 | 564.8987 | 661 | 681.4943 | 79 | 0.00010085 | 28.4282 | 37.365 | 702.3216 | 7768.3565 | 450.5816 | 3.1169 | 48.9498 | 1.0686 | 0.0035783 | 0.0017241 | 0.64145 | 0.82891 | {8A0E1297-B2C6-4E29-9AF9-DF1E115646B0} | 103751101 | BIG BEND 1101 | 180398 | 39.734 | -121.4965 | BIG BEND 1101180398 | 76 | 66 | 13940.9378 | 9616.0055 | 4324.9323 | 9616.0055 | 4324.9323 | 0.13621 | 0.0079674 | 1.3323 | 8.3671 | 205 | 0.28269 | 1163 | 0 | 0 | 5.9751 | 548 | 0
Bay Area | 1959 | 557 | 991.3411 | 1159 | 1337.2833 | 137 | 0.00013186 | 27.5052 | 2.6859 | 220.66 | 3397.7368 | 39.1271 | 0.87724 | 29.5212 | 1.0419 | 0.003575 | 0.00024393 | 0.48059 | 0.74131 | {66AAADD9-54A2-4D43-B82B-F401906AF14B} | 43432103 | SILVERADO 2103 | circuit_breaker | 38.5 | -122.4594 | SILVERADO 2103circuit_breaker | 628 | 744 | 94570.4731 | 53273.3948 | 41297.0783 | 18626.4797 | 12688.0886 | 0.033418 | 0.018065 | 1.7798 | 8.4599 | 1266 | 0.48977 | 1164 | 0 | 0 | 11.574 | 653 | 0
Central Valley | 1596 | 29 | 58.0107 | 195 | 109.8686 | 70 | 3.8366e-05 | 84.3628 | 25.3214 | 530.3999 | 2139.8835 | 151.4015 | 6.4397 | 424.9934 | 1.4353 | 0.0035702 | 0.00031495 | 0.14872 | 0.528 | {90124199-1243-4A62-BE12-797EFE6331CC} | 163341103 | CLAY 1103 | 7124 | 38.2898 | -120.9278 | CLAY 11037124 | 403 | 396 | 86564.599 | 51668.2469 | 34896.3521 | 15711.1032 | 12352.2434 | 0.022047 | 0.0026856 | 2.0004 | 2.7857 | 1093 | 0.24991 | 1165 | 0 | 0 | 9.7624 | 1198 | 0
Central Coast | 787 | 790 | 2430.2701 | 1519 | 2814.4087 | 211 | 1.624e-05 | 202.8093 | 22.4512 | 99.4355 | 497.6655 | 38.0636 | 8.4473 | 77.1689 | 1.1422 | 0.0035483 | 0.00020665 | 0.52008 | 0.86351 | {53EA2B69-06B5-416F-96AE-9EC7627A84C5} | 182601102 |  | circuit_breaker | 35.1011 | -120.5814 | circuit_breaker | 564 | 558 | 73277.5191 | 44267.9262 | 29009.5929 | 32849.6375 | 20341.9793 | 0.043604 | 0.0034267 | 3.0763 | 7.1991 | 1393 | 0.74869 | 1166 | 0 | 0 | 20.4118 | 705 | 0
North Valley | 1805 | 479 | 533.7157 | 2975 | 1706.7902 | 291 | 3.4486e-05 | 110.8592 | 11.3516 | 498.6962 | 7322.5831 | 222.3681 | 1.3119 | 31.6028 | 1.0614 | 0.0035458 | 0.00021222 | 0.16101 | 0.3127 | {FEE27DB0-3817-4D7E-9EF5-189449263C1D} | 102541102 | VOLTA 1102 | 1650 | 40.517 | -121.7462 | VOLTA 11021650 | 204 | 239 | 46137.1161 | 34674.2454 | 11462.8707 | 34674.2454 | 11462.8707 | 0.061756 | 0.010035 | 1.1142 | 10.2234 | 1374 | 1.0318 | 1167 | 0 | 0 | 21.5456 | 2482 | 0
Central Valley | 8095 | 332 | 433.083 | 572 | 542.722 | 36 | 0.00010237 | 35.0656 | 71.9947 | 675.3309 | 11120.2292 | 2634.9978 | 1.8641 | 31.454 | 1.0596 | 0.0035418 | 0.0031649 | 0.58042 | 0.79798 | {73E08A33-0EC5-4395-9E83-FEAACBFDC6EC} | 163201102 | WEST POINT 1102 | L3733 | 38.3892 | -120.5256 | WEST POINT 1102L3733 | 39 | 68 | 6223.3121 | 2820.1267 | 3403.1854 | 2820.1267 | 3403.1854 | 0.11394 | 0.0036852 | 1.3045 | 15.8889 | 98 | 0.1275 | 1168 | 0 | 0 | 1.7523 | 2485 | 0
North Coast | 9592 | 9 | 9.4062 | 21 | 17.469 | 1 | 7.3567e-05 | 47.7756 | 2.1792 | 678.0563 | 8061.876 | 17.5689 | 0.10841 | 64.8042 | 1.25 | 0.0035147 | 0.00016032 | 0.42857 | 0.53845 | {26E5272A-CBC3-4332-B0D6-5C00B9086880} | 42861101 | ANNAPOLIS 1101 | circuit_breaker | 38.6801 | -123.311 | ANNAPOLIS 1101circuit_breaker | 16 | 3 | 1119.422 | 1058.7166 | 60.7054 | 1058.7166 | 60.7054 | 0.00016032 | 7.3567e-05 | 1.0451 | 21 | 1545 | 0.0035147 | 1169 | 0 | 0 | 0.65786 | 2406 | 0
North Coast | 26 | 583 | 868.9375 | 1294 | 1206.1208 | 156 | 0.00010262 | 41.1933 | 5.462 | 68.2523 | 517.2039 | 10.1862 | 5.2504 | 53.6917 | 1.054 | 0.0034877 | 0.00032548 | 0.45054 | 0.72044 | {D8D35F92-2CE4-473E-A048-B7A252678CA3} | 42951101 | MENDOCINO 1101 | circuit_breaker | 39.2507 | -123.1977 | MENDOCINO 1101circuit_breaker | 246 | 314 | 40803.539 | 21845.6652 | 18957.8738 | 18680.8862 | 15894.7201 | 0.050775 | 0.016009 | 1.4905 | 8.2949 | 1068 | 0.54409 | 1170 | 0 | 0 | 11.6078 | 82 | 0
North Coast | 6406 | 381 | 475.9006 | 754 | 641.42 | 99 | 4.4245e-05 | 64.4118 | 2.2254 | 2097.9349 | 35656.1821 | 112.272 | 1.7856 | 150.8653 | 1.3404 | 0.0034129 | 6.1376e-05 | 0.50531 | 0.74195 | {4A3EF433-B8F9-4C76-92D7-D30553832B68} | 42771114 | UKIAH 1114 | 3606 | 39.1316 | -123.1661 | UKIAH 11143606 | 186 | 273 | 37494.1557 | 26641.1454 | 10853.0103 | 16376.8546 | 4955.8971 | 0.0060762 | 0.0043803 | 1.2491 | 7.6162 | 2121 | 0.33787 | 1171 | 0 | 0 | 10.1761 | 2053 | 0
Bay Area | 6388 | 25 | 67.3418 | 48 | 78.164 | 7 | 2.4329e-05 | 136.0509 | 0.058225 | 2.5584 | 8.0312 | 0.00096227 | 13.1182 | 911.1909 | 1.135 | 0.0034124 | 1.0396e-05 | 0.52083 | 0.86155 | {298F8E6C-8C4E-4458-91EA-603E3295125F} | 14052101 | NORTH DUBLIN 2101 | circuit_breaker | 37.7446 | -121.8569 | NORTH DUBLIN 2101circuit_breaker | 57 | 12 | 6581.648 | 6326.3479 | 255.3001 | 5815.8712 | 245.9062 | 7.2772e-05 | 0.00017031 | 2.6937 | 6.8571 | 2780 | 0.023887 | 1172 | 0 | 0 | 3.6138 | 2892 | 0
Central Coast | 1592 | 25 | 50.7285 | 43 | 54.5699 | 15 | 3.7334e-05 | 103.931 | 22.5983 | 7205.484 | 49934.0091 | 1708.5202 | 9.0777 | 1845.7361 | 1.3425 | 0.0033639 | 0.00015907 | 0.5814 | 0.92961 | {3F83E7A1-428B-491F-A667-31D49B0E1C27} | 182661104 | SAN MIGUEL 1104 | R66 | 35.7252 | -120.6553 | SAN MIGUEL 1104R66 | 343 | 217 | 94616.94 | 71296.2907 | 23320.6493 | 11247.2619 | 6856.3582 | 0.0023861 | 0.00056 | 2.0291 | 2.8667 | 1548 | 0.050459 | 1173 | 0 | 0 | 6.9887 | 2572 | 0
North Coast | 6550 | 120 | 184.62 | 363 | 312.194 | 59 | 8.3252e-05 | 41.6194 | 2.9287 | 53.5278 | 779.4191 | 9.719 | 1.3238 | 31.0999 | 1.1129 | 0.0033558 | 0.00018981 | 0.33058 | 0.59136 | {9217337C-879F-471A-BA6E-83EA099544C5} | 43071103 | DUNBAR 1103 | 3127 | 38.3329 | -122.49 | DUNBAR 11033127 | 104 | 102 | 23989.0554 | 15768.1584 | 8220.8969 | 14668.3464 | 7724.8153 | 0.011199 | 0.0049119 | 1.5385 | 6.1525 | 1451 | 0.19799 | 1174 | 0 | 0 | 9.1145 | 1018 | 0
Sierra | 998 | 1617 | 2190.2762 | 4669 | 3709.9163 | 565 | 0.00012838 | 28.9267 | 78.1553 | 2120.6168 | 32094.6564 | 5452.8847 | 2.2598 | 97.83 | 1.2077 | 0.0033541 | 0.0045893 | 0.34633 | 0.59038 | {CD700C3D-374F-40E3-8624-DAD7800FADA7} | 153662102 | APPLE HILL 2102 | 9722 | 38.6401 | -120.6566 | APPLE HILL 21029722 | 490 | 424 | 98911.2315 | 61644.8871 | 37266.3444 | 61644.8871 | 37266.3444 | 2.593 | 0.072535 | 1.3545 | 8.2637 | 41 | 1.8951 | 1175 | 0 | 0 | 38.3043 | 324 | 0
Central Coast | 6572 | 1 | 1.2277 | 8 | 5.314 | 3 | 2.8425e-05 | 105.8596 | 0 | 0 | 0 | 0 | 6.8982 | 470.0968 | 1.5081 | 0.0033473 | 2.3518e-05 | 0.125 | 0.23103 | {7567099C-0C78-4F90-B664-1299D6F2A2C9} | 82951102 | EDENVALE 1102 | XR064 | 37.2239 | -121.7797 | EDENVALE 1102XR064 | 45 | 19 | 6711.6547 | 5786.1483 | 925.5064 | 956.603 | 65.3624 | 7.0555e-05 | 8.5275e-05 | 1.2277 | 2.6667 | 2554 | 0.010042 | 1176 | 0 | 0 | 0.59441 | 1187 | 0
Central Valley | 7934 | 9 | 11.5729 | 23 | 19.6594 | 10 | 1.7176e-06 | 942.8614 | 0.29871 | 446.9017 | 1552.6106 | 0.92756 | 2.5896 | 2192.5936 | 2.0456 | 0.0033432 | 1.0888e-06 | 0.3913 | 0.58867 | {75FA50A9-2878-4633-B714-48E51CCA6E1E} | 255451102 | CAL WATER 1102 | 920714 | 35.4217 | -118.8326 | CAL WATER 1102920714 | 76 | 43 | 16000.4531 | 13869.7898 | 2130.6633 | 6508.6114 | 260.9894 | 1.0888e-05 | 1.7176e-05 | 1.2859 | 2.3 | 2877 | 0.033432 | 1177 | 0 | 0 | 4.0443 | 2016 | 0
Central Valley | 2254 | 957 | 1330.7365 | 4090 | 2953.9714 | 316 | 0.00012307 | 27.9085 | 27.5119 | 339.9495 | 5456.2328 | 1098.2292 | 0.77682 | 13.139 | 1.092 | 0.003334 | 0.0016125 | 0.23399 | 0.45049 | {34B1CFFF-1F43-44C3-AF15-E50BDC16F6A4} | 162821701 | STANISLAUS 1701 | 1812 | 38.183 | -120.3756 | STANISLAUS 17011812 | 408 | 617 | 54617.4285 | 31400.4893 | 23216.9392 | 31400.4893 | 23216.9392 | 0.50956 | 0.03889 | 1.3905 | 12.943 | 227 | 1.0536 | 1178 | 0 | 0 | 19.5114 | 618 | 0
Central Coast | 5899 | 1 | 1.945 | 1 | 1.945 | 1 | 6.927e-05 | 48.1011 |  |  |  |  | 0.55088 | 80.256 | 1.0332 | 0.003332 | 6.927e-05 | 1 | 1 | {13EB3903-13F9-40C3-94BE-AF1022EEB8B5} | 182981103 | JOLON 1103 | circuit_breaker | 36.0132 | -121.1676 | JOLON 1103circuit_breaker | 115 | 20 | 30468.1902 | 29651.7983 | 816.3919 | 18381.2801 | 663.2295 | 6.927e-05 | 6.927e-05 | 1.945 | 1 | 2065 | 0.003332 | 1179 | 0 | 0 | 11.4216 | 2301 | 0
Sierra | 7050 | 27 | 44.8148 | 221 | 102.5477 | 36 | 8.2961e-05 | 50.3259 | 11.0021 | 46.851 | 211.8306 | 5.8984 | 4.8328 | 62.1024 | 1.085 | 0.0033193 | 0.00035576 | 0.12217 | 0.43701 | {A0936C28-A756-47FA-9C1E-76F4B7CFFF7E} | 153612109 | CLARKSVILLE 2109 | 6502 | 38.7127 | -121.0782 | CLARKSVILLE 21096502 | 169 | 163 | 14951.7263 | 8746.5939 | 6205.1323 | 3563.6935 | 1419.52 | 0.012808 | 0.0029866 | 1.6598 | 6.1389 | 1008 | 0.1195 | 1180 | 0 | 0 | 2.2144 | 94 | 0
Central Coast | 2055 | 13 | 19.7307 | 31 | 28.7725 | 7 | 3.2594e-05 | 110.6869 | 8.991 | 267.6426 | 1166.8003 | 29.5747 | 3.6179 | 325.4547 | 1.2393 | 0.0032953 | 0.00011806 | 0.41935 | 0.68575 | {614AFF73-1972-445B-AB78-45C825B90AEF} | 182541103 | ATASCADERO 1103 | A46 | 35.4018 | -120.6222 | ATASCADERO 1103A46 | 196 | 611 | 36486.3047 | 14964.2331 | 21522.0716 | 983.4741 | 273.0205 | 0.00082639 | 0.00022816 | 1.5177 | 4.4286 | 1755 | 0.023067 | 1181 | 0 | 0 | 0.6111 | 2222 | 0
Central Valley | 8783 | 73 | 131.1386 | 362 | 215.4489 | 128 | 5.0577e-05 | 62.306 | 16.1413 | 4645.1744 | 46009.2688 | 900.7781 | 6.4531 | 383.238 | 1.4351 | 0.0032816 | 0.00041527 | 0.20166 | 0.60868 | {3CAC56CD-7B8A-420C-A5B0-8853D3551182} | 162211101 | CALAVERAS CEMENT 1101 | 585 | 38.1398 | -120.6624 | CALAVERAS CEMENT 1101585 | 101 | 80 | 31102.2057 | 22710.6586 | 8391.547 | 22710.6586 | 8391.547 | 0.053155 | 0.0064738 | 1.7964 | 2.8281 | 918 | 0.42004 | 1182 | 0 | 0 | 14.1117 | 1025 | 0
North Valley | 9247 | 18 | 25.8075 | 30 | 32.1062 | 12 | 0.0001043 | 31.7693 | 3.4173 | 205.5182 | 2388.209 | 15.9898 | 0.48838 | 44.1277 | 1.2437 | 0.00328 | 0.00014836 | 0.6 | 0.80382 | {C813897C-7FF0-4426-960C-CC77387AFFF1} | 103031102 | ORO FINO 1102 | 2236 | 39.8719 | -121.6119 | ORO FINO 11022236 | 21 | 5 | 4362.7432 | 4120.4561 | 242.2871 | 4120.4561 | 242.2871 | 0.0017803 | 0.0012515 | 1.4337 | 2.5 | 1602 | 0.03936 | 1183 | 0 | 0 | 2.5603 | 2655 | 0
North Coast | 510 | 225 | 386.2481 | 234 | 391.2004 | 31 | 0.00010195 | 33.8014 | 1.7985 | 62.0202 | 345.7738 | 0.84075 | 0.35327 | 12.6498 | 1.0223 | 0.0032464 | 0.00015182 | 0.96154 | 0.98734 | {6151271A-BC5B-476A-8700-C63C19F32AF9} | 43381101 | POINT ARENA 1101 | 47952 | 38.9145 | -123.6392 | POINT ARENA 110147952 | 116 | 81 | 23668.8231 | 16717.6297 | 6951.1934 | 16717.6297 | 6951.1934 | 0.0047065 | 0.0031603 | 1.7167 | 7.5484 | 1583 | 0.10064 | 1184 | 0 | 0 | 10.3879 | 2244 | 0
North Coast | 857 | 275 | 529.5786 | 786 | 848.7404 | 92 | 0.0001172 | 28.7746 | 5.5291 | 15.7194 | 50.2467 | 0.56454 | 1.605 | 6.7262 | 1.5771 | 0.003245 | 0.00039671 | 0.34987 | 0.62396 | {5B55A465-FAC4-48C8-B9A5-F80EA4DBED38} | 42561107 | FULTON 1107 | 77670 | 38.5022 | -122.737 | FULTON 110777670 | 158 | 308 | 27773.2994 | 11040.0737 | 16733.2257 | 10408.8422 | 15870.5723 | 0.036497 | 0.010783 | 1.9257 | 8.5435 | 947 | 0.29854 | 1185 | 0 | 0 | 6.4678 | 2031 | 0
Sierra | 2343 | 2514 | 2888.6973 | 6641 | 4790.5005 | 555 | 5.5317e-05 | 57.9543 | 77.2408 | 1910.6727 | 51113.6462 | 10199.2195 | 0.57381 | 17.7662 | 1.0373 | 0.0032185 | 0.0019831 | 0.37856 | 0.60301 | {3EE03E8E-7174-416B-B7B0-D49DC8F3C48B} | 152301102 | BONNIE NOOK 1102 | circuit_breaker | 39.2146 | -120.8094 | BONNIE NOOK 1102circuit_breaker | 506 | 578 | 92197.3842 | 55059.6809 | 37137.7033 | 55059.6809 | 37137.7033 | 1.1006 | 0.030701 | 1.149 | 11.9658 | 179 | 1.7863 | 1186 | 0 | 0 | 34.2125 | 466 | 0
Central Valley | 1103 | 483 | 654.5968 | 2169 | 1409.5377 | 238 | 9.1538e-05 | 33.7749 | 11.015 | 65.8035 | 461.6016 | 8.1665 | 2.9252 | 31.5096 | 1.085 | 0.0032131 | 0.00056684 | 0.22268 | 0.46441 | {68513B5A-56EB-4D19-97D2-4A9509C9FEBC} | 254432102 | COARSEGOLD 2102 | 10040 | 37.3092 | -119.5843 | COARSEGOLD 210210040 | 314 | 397 | 51897.4477 | 28189.7477 | 23707.7 | 28189.7477 | 23707.7 | 0.13491 | 0.021786 | 1.3553 | 9.1134 | 715 | 0.76472 | 1187 | 0 | 0 | 17.5163 | 1527 | 0
North Coast | 6326 | 10 | 24.3513 | 10 | 24.3513 | 1 | 0.00013419 | 23.8436 |  |  |  |  | 0.0022124 | 8.196 | 1.0044 | 0.0031997 | 0.00013419 | 1 | 1 | {8CA524F1-8D7D-4618-99D9-A20A89A3DB89} | 42091102 | MIRABEL 1102 | 7347 | 38.5035 | -122.9486 | MIRABEL 11027347 | 17 | 94 | 3253.1792 | 1145.4102 | 2107.769 | 1145.4102 | 2107.769 | 0.00013419 | 0.00013419 | 2.4351 | 10 | 1677 | 0.0031997 | 1188 | 0 | 0 | 0.71172 | 286 | 0
Sierra | 1287 | 886 | 1188.5465 | 2335 | 1861.8945 | 228 | 0.00011348 | 31.0428 | 74.6335 | 1683.3701 | 24401.4189 | 4045.8497 | 2.5741 | 42.4368 | 1.1944 | 0.0031893 | 0.004306 | 0.37944 | 0.63835 | {B1828264-E942-4507-AD5A-E7D1D60A066A} | 152282101 | MOUNTAIN QUARRIES 2101 | 92474 | 38.8957 | -120.8791 | MOUNTAIN QUARRIES 210192474 | 258 | 229 | 39957.917 | 25079.5665 | 14878.3505 | 23834.445 | 13934.0092 | 0.98176 | 0.025874 | 1.3415 | 10.2412 | 52 | 0.72716 | 1189 | 0 | 0 | 14.81 | 465 | 0
North Valley | 5942 | 108 | 161.747 | 279 | 225.2745 | 24 | 0.00012523 | 21.9115 | 42.6493 | 379.2134 | 5061.3518 | 836.4235 | 2.7629 | 26.626 | 1.0235 | 0.0031813 | 0.0022919 | 0.3871 | 0.718 | {3A867C43-90D5-4AF5-884D-4817C90B9FCF} | 103441101 | JESSUP 1101 | 3383 | 40.4888 | -122.358 | JESSUP 11013383 | 41 | 109 | 6999.5291 | 3031.9376 | 3967.5915 | 1995.2743 | 2810.7459 | 0.055006 | 0.0030056 | 1.4977 | 11.625 | 154 | 0.07635 | 1190 | 0 | 0 | 1.2398 | 1731 | 0
Central Coast | 2053 | 1434 | 1932.2552 | 2314 | 2360.4727 | 174 | 6.1564e-05 | 51.7284 | 3.3217 | 99.0175 | 1530.5867 | 23.4804 | 0.34961 | 14.2551 | 1.0945 | 0.0031698 | 0.00013049 | 0.61971 | 0.81859 | {635AB06E-6FE6-4F3C-85D2-7DF03CF41311} | 83481110 | STELLING 1110 | 60094 | 37.2574 | -122.1202 | STELLING 111060094 | 126 | 93 | 26404.6016 | 15898.3782 | 10506.2234 | 15898.3782 | 10506.2234 | 0.022705 | 0.010712 | 1.3475 | 13.2989 | 1699 | 0.55155 | 1191 | 0 | 0 | 9.8788 | 2251 | 0
Central Coast | 2127 | 74 | 168.6524 | 399 | 353.7637 | 66 | 1.8177e-05 | 198.2629 | 0.29643 | 35.1932 | 77.1253 | 0.022819 | 8.7283 | 163.1197 | 1.1352 | 0.0031681 | 1.7996e-05 | 0.18546 | 0.47674 | {E158EBD1-D391-40F7-8D5C-4284F51B8199} | 83531111 | MC KEE 1111 | 711900 | 37.3561 | -121.8052 | MC KEE 1111711900 | 226 | 330 | 40334.2221 | 20149.4052 | 20184.8169 | 14114.2959 | 8751.0581 | 0.0011877 | 0.0011997 | 2.2791 | 6.0455 | 2651 | 0.2091 | 1192 | 0 | 0 | 8.7702 | 1650 | 0
Sierra | 3741 | 1431 | 1883.7046 | 2639 | 2419.0796 | 211 | 0.00010122 | 31.2127 | 46.5324 | 647.2104 | 9311.0265 | 1427.6904 | 3.6657 | 54.6764 | 1.0981 | 0.0031648 | 0.0020454 | 0.54225 | 0.77869 | {0010E3CC-5B34-4785-98D9-D2D98BC731B3} | 153661104 | APPLE HILL 1104 | 12832 | 38.7523 | -120.682 | APPLE HILL 110412832 | 277 | 201 | 39088.1034 | 24725.6134 | 14362.49 | 23528.5139 | 13817.533 | 0.43158 | 0.021357 | 1.3164 | 12.5071 | 173 | 0.66776 | 1193 | 0 | 0 | 14.6199 | 1459 | 0
Sierra | 3014 | 4243 | 5513.4021 | 8666 | 7557.049 | 779 | 8.5928e-05 | 37.6758 | 66.9877 | 1190.132 | 21636.2098 | 7090.7799 | 0.73354 | 17.7557 | 1.0383 | 0.0031597 | 0.0031561 | 0.48961 | 0.72957 | {DC8F828A-9D78-4250-9936-BA54E6245EA8} | 153082106 | PLACERVILLE 2106 | 1104 | 38.9124 | -120.8201 | PLACERVILLE 21061104 | 685 | 661 | 127799.0356 | 80528.8854 | 47270.1502 | 80528.8854 | 47270.1502 | 2.4586 | 0.066938 | 1.2994 | 11.1245 | 99 | 2.4614 | 1194 | 0 | 0 | 50.0383 | 516 | 0
Sierra | 4647 | 1384 | 1911.5485 | 3369 | 2787.6917 | 259 | 0.00011808 | 33.506 | 22.8113 | 228.2462 | 3384.5662 | 596.4982 | 2.922 | 27.827 | 1.0497 | 0.0031553 | 0.0013359 | 0.4108 | 0.68571 | {04FA73EB-B797-476B-86A7-C1CFAD605BCA} | 153661104 | APPLE HILL 1104 | 12842 | 38.7537 | -120.6796 | APPLE HILL 110412842 | 383 | 643 | 63105.1251 | 26827.6373 | 36277.4878 | 24430.5416 | 33083.1888 | 0.346 | 0.030582 | 1.3812 | 13.0077 | 285 | 0.81722 | 1195 | 0 | 0 | 15.1804 | 1478 | 0
North Coast | 8723 | 590 | 978.7518 | 927 | 1135.9875 | 101 | 0.000152 | 17.4841 | 14.3389 | 343.2786 | 6271.3834 | 191.0632 | 2.1776 | 19.3149 | 1.0602 | 0.0031515 | 0.00125 | 0.63646 | 0.86159 | {0F7FFA32-0648-474C-B64E-A51E578D757F} | 192171102 | WILLOW CREEK 1102 | circuit_breaker | 40.9477 | -123.6402 | WILLOW CREEK 1102circuit_breaker | 126 | 128 | 14701.4852 | 11718.7349 | 2982.7503 | 11718.7349 | 2982.7503 | 0.12625 | 0.015352 | 1.6589 | 9.1782 | 306 | 0.3183 | 1196 | 0 | 0 | 7.2817 | 1998 | 0
North Coast | 3928 | 476 | 918.0614 | 1493 | 1470.828 | 96 | 0.0001188 | 27.8221 | 7.7911 | 28.8677 | 67.4507 | 1.1087 | 3.6894 | 18.2673 | 1.0134 | 0.0031339 | 0.00055112 | 0.31882 | 0.62418 | {D5D881FC-5E37-43D0-8EE8-25189C47D57C} | 42571101 | MOLINO 1101 | 5042 | 38.3905 | -122.8789 | MOLINO 11015042 | 168 | 196 | 23907.4405 | 11223.364 | 12684.0765 | 9764.6994 | 10492.5289 | 0.052908 | 0.011405 | 1.9287 | 15.5521 | 735 | 0.30085 | 1197 | 0 | 0 | 6.0675 | 836 | 0
Sierra | 5422 | 525 | 746.0772 | 1589 | 1190.1606 | 135 | 8.8632e-05 | 45.02 | 10.9351 | 63.3483 | 440.9541 | 13.0257 | 2.2208 | 33.8485 | 1.0755 | 0.0031226 | 0.00047776 | 0.3304 | 0.62687 | {8D49CCC1-AF4C-4146-915D-64772DC7F3D1} | 153132105 | NARROWS 2105 | 2426 | 39.2042 | -121.2004 | NARROWS 21052426 | 434 | 642 | 64135.3655 | 27928.6656 | 36206.6998 | 12992.6156 | 14564.3549 | 0.064498 | 0.011965 | 1.4211 | 11.7704 | 814 | 0.42154 | 1198 | 0 | 0 | 8.0732 | 267 | 0
Sierra | 5266 | 1934 | 2417.6333 | 4113 | 3477.0579 | 359 | 0.00011017 | 28.4813 | 77.08 | 1120.7483 | 23823.4956 | 7121.9097 | 1.1021 | 19.508 | 1.0601 | 0.003118 | 0.0036645 | 0.47022 | 0.69531 | {9A3F5548-F595-4F3F-89FC-9574388096DE} | 152181101 | FORESTHILL 1101 | 1802 | 39.0161 | -120.8354 | FORESTHILL 11011802 | 474 | 645 | 73711.6508 | 35584.2456 | 38127.4052 | 35584.2456 | 38127.4052 | 1.3156 | 0.03955 | 1.2501 | 11.4568 | 70 | 1.1194 | 1199 | 0 | 0 | 22.111 | 833 | 0
Sierra | 2594 | 1636 | 2412.6574 | 6311 | 4592.297 | 777 | 0.00011422 | 28.6132 | 43.5046 | 884.2337 | 10517.1086 | 1053.7272 | 3.4335 | 75.9215 | 1.2374 | 0.0031095 | 0.0023168 | 0.25923 | 0.52537 | {87934A6A-C9D7-420E-9278-5C4F8DB79DED} | 153662102 | APPLE HILL 2102 | 8372 | 38.6092 | -120.7025 | APPLE HILL 21028372 | 845 | 759 | 166228.2055 | 101166.6359 | 65061.5696 | 90180.3006 | 58569.1701 | 1.8001 | 0.088751 | 1.4747 | 8.1223 | 148 | 2.4161 | 1200 | 0 | 0 | 56.0354 | 1804 | 0
North Valley | 3263 | 131 | 130.9353 | 674 | 349.8998 | 77 | 5.2815e-05 | 57.6586 | 21.098 | 228.0986 | 2711.5846 | 112.3299 | 1.1881 | 34.7979 | 1.0564 | 0.0030978 | 0.00058028 | 0.19436 | 0.37421 | {48E1615C-C71C-4D0B-8D4E-00E5F51687F9} | 102541102 | VOLTA 1102 | 97816 | 40.5351 | -121.7276 | VOLTA 110297816 | 89 | 74 | 12262.4116 | 8457.2763 | 3805.1353 | 8457.2763 | 3805.1353 | 0.044682 | 0.0040667 | 0.99951 | 8.7532 | 696 | 0.23853 | 1201 | 0 | 0 | 5.2551 | 2724 | 0
Sierra | 1850 | 469 | 756.0171 | 1317 | 1077.6045 | 133 | 0.00013986 | 23.5413 | 5.1378 | 37.1116 | 200.7247 | 2.2674 | 4.4506 | 42.9605 | 1.1043 | 0.0030892 | 0.00034632 | 0.35611 | 0.70157 | {027EA52B-9771-4584-AAFD-2CA838E196C2} | 153652110 | SHINGLE SPRINGS 2110 | 51800 | 38.6635 | -120.9307 | SHINGLE SPRINGS 211051800 | 213 | 208 | 26704.456 | 15648.3843 | 11056.0718 | 14770.4871 | 10021.4093 | 0.04606 | 0.018602 | 1.612 | 9.9023 | 1019 | 0.41086 | 1202 | 0 | 0 | 9.178 | 673 | 0
North Valley | 1254 | 29 | 68.7222 | 55 | 81.7745 | 9 | 6.4059e-05 | 47.6521 | 0 | 0 | 0 | 0 | 0.30678 | 14.5695 | 1.0219 | 0.0030858 | 5.6932e-05 | 0.52727 | 0.84039 | {6018A7D7-F178-44F7-B593-CA41A45039FD} | 103031102 | ORO FINO 1102 | 2556 | 39.8902 | -121.5778 | ORO FINO 11022556 | 70 | 251 | 25119.1074 | 10716.6127 | 14402.4947 | 10716.6127 | 14402.4947 | 0.00051238 | 0.00057653 | 2.3697 | 6.1111 | 2176 | 0.027772 | 1203 | 0 | 0 | 6.659 | 876 | 0
Central Coast | 198 | 111 | 261.4302 | 396 | 415.3785 | 56 | 2.1116e-05 | 140.9311 | 21.6457 | 101.9085 | 327.7096 | 78.9315 | 1.9998 | 61.256 | 1.0486 | 0.0030669 | 0.0002119 | 0.2803 | 0.62938 | {D8F287F2-9F47-4079-84BA-BB2B78537313} | 182731101 | RESERVATION ROAD 1101 | circuit_breaker | 36.6242 | -121.6881 | RESERVATION ROAD 1101circuit_breaker | 200 | 392 | 33277.6377 | 15082.891 | 18194.7467 | 7957.2831 | 1954.6503 | 0.011866 | 0.0011825 | 2.3552 | 7.0714 | 1375 | 0.17175 | 1204 | 0 | 0 | 4.9444 | 2561 | 0
North Coast | 584 | 93 | 140.7576 | 118 | 152.4866 | 11 | 0.00033593 | 8.7093 | 0 | 0 | 0 | 0 | 1.6645 | 4.5918 | 1.006 | 0.0030585 | 0.00019829 | 0.78814 | 0.92308 | {81BF210B-E399-451E-B158-93FB561813DD} | 192221103 | GARBERVILLE 1103 | circuit_breaker | 40.1031 | -123.7928 | GARBERVILLE 1103circuit_breaker | 99 | 404 | 15687.2267 | 3592.4976 | 12094.7291 | 841.9717 | 2305.5852 | 0.0021811 | 0.0036953 | 1.5135 | 10.7273 | 1420 | 0.033644 | 1205 | 0 | 0 | 0.52318 | 1489 | 0
North Valley | 2906 | 1136 | 1717.5039 | 2093 | 2206.3525 | 294 | 7.7713e-05 | 71.9273 | 5.0842 | 376.3342 | 2971.9921 | 38.188 | 2.2799 | 116.8346 | 1.1675 | 0.0030497 | 0.00025393 | 0.54276 | 0.77844 | {9FD8CC5B-B764-4FC0-90D0-B9293DA570EE} | 102971111 | SYCAMORE CREEK 1111 | 2014 | 39.8317 | -121.8444 | SYCAMORE CREEK 11112014 | 249 | 232 | 60859.5235 | 36436.0286 | 24423.4949 | 36180.8061 | 24039.2234 | 0.074654 | 0.022848 | 1.5119 | 7.119 | 1239 | 0.89661 | 1206 | 0 | 0 | 22.4817 | 1266 | 0
North Coast | 3569 | 30 | 96.0253 | 80 | 126.6865 | 16 | 5.0177e-05 | 43.2213 | 13.7789 | 80.1698 | 264.8222 | 7.5616 | 7.6488 | 27.152 | 1.0176 | 0.0030406 | 0.00020993 | 0.375 | 0.75798 | {29853D86-D10B-44F9-9B31-548850DBE0F0} | 43471101 | PENNGROVE 1101 | 554 | 38.3126 | -122.6667 | PENNGROVE 1101554 | 289 | 554 | 50627.8866 | 20497.8694 | 30130.0172 | 1740.0436 | 3061.9494 | 0.0033589 | 0.00080283 | 3.2008 | 5 | 1379 | 0.048649 | 1207 | 0 | 0 | 1.0812 | 1328 | 0
Bay Area | 1879 | 557 | 886.6295 | 1543 | 1451.4799 | 158 | 8.0569e-05 | 35.7832 | 0.76809 | 347.8444 | 6283.6262 | 21.6949 | 0.4125 | 59.0307 | 1.099 | 0.0030404 | 6.4306e-05 | 0.36099 | 0.61085 | {ED6FC814-3841-4AC9-A379-44E5BC33C241} | 42291101 | OLEMA 1101 | 416 | 38.0421 | -122.7868 | OLEMA 1101416 | 101 | 74 | 31150.6448 | 26064.3398 | 5086.305 | 25936.9304 | 5086.305 | 0.01016 | 0.01273 | 1.5918 | 9.7658 | 2102 | 0.48038 | 1208 | 0 | 0 | 16.1165 | 1245 | 0
North Valley | 8904 | 62 | 113.5519 | 125 | 142.6035 | 46 | 1.2074e-05 | 413.2735 | 2.0975 | 219.8536 | 987.5826 | 1.0903 | 6.4923 | 426.2322 | 1.5242 | 0.0030262 | 1.3286e-05 | 0.496 | 0.79628 | {185974AB-4212-4B5F-B111-C93E97C24964} | 103721101 | PIT NO 1 1101 | circuit_breaker | 40.9904 | -121.4961 | PIT NO 1 1101circuit_breaker | 67 | 24 | 11736.4796 | 10477.1422 | 1259.3374 | 10477.1422 | 1259.3374 | 0.00061115 | 0.00055541 | 1.8315 | 2.7174 | 2738 | 0.13921 | 1209 | 0 | 0 | 6.5102 | 259 | 0
Central Valley | 5033 | 51 | 83.3029 | 215 | 153.5281 | 46 | 6.3238e-05 | 51.4002 | 3.093 | 386.2614 | 2616.6096 | 13.6313 | 1.3858 | 138.8888 | 1.3568 | 0.0031093 | 0.00013196 | 0.23721 | 0.54259 | {2ADCBD92-66F4-407E-9ADA-EA48C32C4604} | 163541102 | OLETA 1102 | 2642 | 38.5013 | -120.8481 | OLETA 11022642 | 29 | 24 | 9076.656 | 7497.8568 | 1578.7992 | 7497.8568 | 1578.7992 | 0.0060703 | 0.0029089 | 1.6334 | 4.6739 | 1691 | 0.14303 | 1210 | 0 | 0 | 4.659 | 1535 | 0
Sierra | 5033 | 4 | 7.7799 | 35 | 20.4057 | 2 | 8.5424e-05 | 12.0488 | 0.0017495 | 0.22239 | 2.0009 | 3.5006e-06 | 1.2511 | 57.693 | 1.2135 | 0.0010588 | 4.1555e-05 | 0.11429 | 0.38126 | {2ADCBD92-66F4-407E-9ADA-EA48C32C4604} | 163541102 | OLETA 1102 | 2642 | 38.5013 | -120.8481 | OLETA 11022642 | 29 | 24 | 9076.656 | 7497.8568 | 1578.7992 | 7497.8568 | 1578.7992 | 8.3109e-05 | 0.00017085 | 1.945 | 17.5 | 2315 | 0.0021177 | 1210 | 0 | 0 | 4.659 | 1017 | 0
Sierra | 3416 | 1986 | 2528.9197 | 4358 | 3656.4546 | 361 | 0.00012724 | 23.1303 | 184.7553 | 1923.0165 | 35057.238 | 15715.4142 | 3.3507 | 38.7935 | 1.127 | 0.0029991 | 0.010127 | 0.45571 | 0.69163 | {9A017637-BE00-49D7-B59C-C46979127E1F} | 153662102 | APPLE HILL 2102 | 7502 | 38.6828 | -120.6611 | APPLE HILL 21027502 | 395 | 436 | 70172.2775 | 37014.7956 | 33157.4819 | 37014.7956 | 33157.4819 | 3.6558 | 0.045935 | 1.2734 | 12.072 | 6 | 1.0827 | 1211 | 0 | 0 | 22.9999 | 2978 | 0
Bay Area | 1730 | 131 | 199.317 | 478 | 394.2102 | 72 | 6.5283e-05 | 62.5085 | 4.8258 | 31.8225 | 89.5528 | 1.8555 | 2.8748 | 31.5192 | 1.08 | 0.0029928 | 0.00019288 | 0.27406 | 0.50561 | {D247C9D4-2385-4C86-98D9-FAEFF0DAB6B3} | 14502108 | VINEYARD 2108 | MR172 | 37.657 | -121.9009 | VINEYARD 2108MR172 | 193 | 104 | 20255.3499 | 14260.3612 | 5994.9887 | 8979.3146 | 3664.0241 | 0.013887 | 0.0047004 | 1.5215 | 6.6389 | 1442 | 0.21548 | 1212 | 0 | 0 | 5.5795 | 2121 | 0
North Coast | 1082 | 836 | 1120.7275 | 2255 | 1816.8959 | 319 | 0.00023188 | 13.0315 | 2.1535 | 654.9348 | 15840.7937 | 71.8121 | 0.10882 | 14.9292 | 1.0154 | 0.0029914 | 0.00037223 | 0.37073 | 0.61684 | {8651217A-D767-4452-8107-AA225147083B} | 192401101 | HOOPA 1101 | 37202 | 41.1894 | -123.7104 | HOOPA 110137202 | 234 | 116 | 50083.7922 | 46502.2253 | 3581.5668 | 39996.9216 | 3465.8951 | 0.11874 | 0.073968 | 1.3406 | 7.069 | 978 | 0.95424 | 1213 | 0 | 0 | 24.8529 | 1232 | 0
Central Coast | 7415 | 31 | 42.1504 | 154 | 117.6659 | 32 | 3.2485e-05 | 88.914 | 20.1727 | 356.429 | 1394.8192 | 45.207 | 7.482 | 380.5217 | 1.3674 | 0.0029901 | 0.00030097 | 0.2013 | 0.35822 | {07E209B8-80A2-40A5-8228-12D4DFF42801} | 83182101 | LLAGAS 2101 | XR586 | 37.0279 | -121.5275 | LLAGAS 2101XR586 | 239 | 237 | 42193.3388 | 21353.5124 | 20839.8264 | 7394.3416 | 7123.5991 | 0.0096311 | 0.0010395 | 1.3597 | 4.8125 | 1121 | 0.095685 | 1214 | 0 | 0 | 4.5946 | 1078 | 0
North Valley | 1058 | 86 | 119.5062 | 512 | 344.2575 | 83 | 1.2367e-05 | 245.7927 | 7.7398 | 617.459 | 4997.0204 | 56.3642 | 10.9115 | 438.9225 | 1.2451 | 0.002961 | 5.9112e-05 | 0.16797 | 0.34714 | {4752BF93-70F8-42FC-8D3A-033549B0C98A} | 103491101 | MC ARTHUR 1101 | 1492 | 41.0527 | -121.3984 | MC ARTHUR 11011492 | 305 | 290 | 60311.6372 | 49518.5791 | 10793.0581 | 15180.4428 | 4930.4434 | 0.0049063 | 0.0010265 | 1.3896 | 6.1687 | 2150 | 0.24576 | 1215 | 0 | 0 | 9.4327 | 213 | 0
North Valley | 5327 | 649 | 922.5185 | 1920 | 1554.3229 | 285 | 5.6602e-05 | 46.995 | 43.3121 | 1366.5846 | 21902.5637 | 2234.429 | 2.5807 | 68.3304 | 1.079 | 0.0029463 | 0.0010872 | 0.33802 | 0.59352 | {043BC0AF-FD34-4233-9280-D3D38FCAFD0A} | 103751101 | BIG BEND 1101 | 641808 | 39.7404 | -121.4965 | BIG BEND 1101641808 | 339 | 361 | 69754.1936 | 46360.2755 | 23393.9181 | 46054.2939 | 23393.9181 | 0.30986 | 0.016132 | 1.4214 | 6.7368 | 367 | 0.8397 | 1216 | 0 | 0 | 28.6168 | 904 | 0
North Valley | 9122 | 28 | 40.0755 | 88 | 63.9703 | 18 | 6.4543e-05 | 79.4048 | 2.8512 | 15.8314 | 139.1841 | 1.4537 | 1.7071 | 15.3554 | 1.0377 | 0.0029241 | 0.00016918 | 0.31818 | 0.62647 | {DEF16B60-E22C-4BAF-BEFC-F4B0E169B38F} | 103401101 | GIRVAN 1101 | circuit_breaker | 40.5132 | -122.3787 | GIRVAN 1101circuit_breaker | 46 | 29 | 7073.6118 | 5303.193 | 1770.4187 | 2142.1974 | 1770.4187 | 0.0030453 | 0.0011618 | 1.4313 | 4.8889 | 1521 | 0.052634 | 1217 | 0 | 0 | 1.3311 | 2523 | 0
North Coast | 7283 | 2678 | 4494.2758 | 2867 | 4589.7134 | 265 | 9.6114e-05 | 28.774 | 0.60986 | 59.8736 | 279.1789 | 0.25511 | 0.56907 | 19.1525 | 1.0355 | 0.0029189 | 7.9892e-05 | 0.93408 | 0.97921 | {AD82FA7A-9F47-4C04-A20C-1CCF257103DF} | 42601102 | PHILO 1102 | 2600 | 39.0853 | -123.485 | PHILO 11022600 | 150 | 102 | 38964.6117 | 32189.254 | 6775.3578 | 32189.254 | 6775.3578 | 0.021171 | 0.02547 | 1.6782 | 10.8189 | 1982 | 0.7735 | 1218 | 0 | 0 | 20.0015 | 2240 | 0
North Valley | 8014 | 172 | 194.1287 | 378 | 284.1348 | 83 | 7.5536e-05 | 38.4602 | 0.32519 | 136.9698 | 2419.4857 | 6.3642 | 0.079273 | 14.2017 | 1.0659 | 0.0029157 | 4.9943e-05 | 0.45503 | 0.68323 | {23C4AB75-7BD7-4D2C-8DD3-FAC1E53F0F0D} | 103732101 | PIT NO 3 2101 | 1482 | 40.9986 | -121.7471 | PIT NO 3 21011482 | 56 | 17 | 19689.2817 | 19365.2645 | 324.0173 | 19365.2645 | 324.0173 | 0.0041453 | 0.0062695 | 1.1287 | 4.5542 | 2230 | 0.242 | 1219 | 0 | 0 | 12.033 | 802 | 0
North Coast | 3504 | 156 | 269.7472 | 263 | 327.1341 | 36 | 0.00010057 | 27.1509 | 4.3912 | 16.5386 | 90.3245 | 1.7723 | 6.2216 | 26.1437 | 1.5954 | 0.0028891 | 0.00030433 | 0.59316 | 0.82458 | {0DAF681A-D0A6-472F-BDFE-814CD10BFA9B} | 42091101 | MIRABEL 1101 | circuit_breaker | 38.4893 | -122.8941 | MIRABEL 1101circuit_breaker | 261 | 569 | 39505.6399 | 13652.7515 | 25852.8884 | 3875.2533 | 5873.6035 | 0.010956 | 0.0036206 | 1.7291 | 7.3056 | 1110 | 0.10401 | 1220 | 0 | 0 | 2.408 | 1342 | 0
Central Valley | 4557 | 1464 | 1909.6946 | 5018 | 3574.9768 | 474 | 8.844e-05 | 32.4869 | 105.7852 | 1586.142 | 28364.6488 | 6469.1967 | 2.239 | 50.1393 | 1.107 | 0.0028728 | 0.0044035 | 0.29175 | 0.53418 | {EAFDD43F-F7FF-4388-8EDB-D22261F3737C} | 163751102 | PINE GROVE 1102 | 3168 | 38.4142 | -120.6538 | PINE GROVE 11023168 | 402 | 422 | 71876.6683 | 48743.192 | 23133.4763 | 48743.192 | 23133.4763 | 2.0873 | 0.041921 | 1.3044 | 10.5865 | 47 | 1.3617 | 1221 | 0 | 0 | 30.2876 | 26 | 0
North Coast | 5973 | 209 | 335.1133 | 475 | 484.6593 | 40 | 0.00013333 | 20.3034 | 18.2121 | 51.3292 | 107.7787 | 3.2952 | 6.1069 | 27.8913 | 1.0091 | 0.0028593 | 0.00099352 | 0.44 | 0.69144 | {366DDD05-C36C-4018-8E0C-E1718F820EB6} | 42571101 | MOLINO 1101 | 152 | 38.3962 | -122.8626 | MOLINO 1101152 | 267 | 457 | 46710.6775 | 18334.7231 | 28375.9544 | 3850.1683 | 6279.2101 | 0.039741 | 0.0053332 | 1.6034 | 11.875 | 413 | 0.11437 | 1222 | 0 | 0 | 2.3924 | 2545 | 0
North Coast | 9730 | 1 | 1.2277 | 5 | 2.0814 | 2 | 3.7068e-05 | 61.9328 | 0.30965 | 21.4728 | 55.1893 | 0.017287 | 10.0343 | 260.7652 | 1.4491 | 0.0028588 | 2.113e-05 | 0.2 | 0.58986 | {6A48DD4C-8096-4848-9316-CAF03427E24D} | 42871101 | UPPER LAKE 1101 | circuit_breaker | 39.1458 | -122.9171 | UPPER LAKE 1101circuit_breaker | 7 | 0 | 1791.2622 | 1791.2622 | 0 | 1791.2622 | 0 | 4.226e-05 | 7.4136e-05 | 1.2277 | 2.5 | 2587 | 0.0057175 | 1223 | 0 | 0 | 1.113 | 1475 | 0
Sierra | 4858 | 793 | 1006.6511 | 2505 | 1841.2462 | 234 | 7.1896e-05 | 38.2785 | 66.2045 | 1678.6547 | 47751.4 | 11567.2535 | 0.81303 | 12.8942 | 1.0302 | 0.0028438 | 0.0021647 | 0.31657 | 0.54672 | {9FFB5CDC-505F-4B8E-9B6D-E79E68D9EC60} | 152301101 | BONNIE NOOK 1101 | circuit_breaker | 39.2146 | -120.8094 | BONNIE NOOK 1101circuit_breaker | 276 | 448 | 50338.4744 | 23724.1813 | 26614.2931 | 23724.1813 | 26614.2931 | 0.50653 | 0.016824 | 1.2694 | 10.7051 | 163 | 0.66546 | 1224 | 0 | 0 | 14.7415 | 1990 | 0
Central Coast | 3846 | 56 | 99.3496 | 113 | 129.0274 | 21 | 3.0534e-05 | 70.4563 | 0.51607 | 67.9137 | 310.4878 | 1.0669 | 3.5553 | 403.2891 | 1.2437 | 0.0028366 | 2.3615e-05 | 0.49558 | 0.76999 | {C56ADC1A-9E36-443A-A4AD-EABCB05C5CD5} | 182681101 | ZACA 1101 | Y70 | 34.7339 | -120.1265 | ZACA 1101Y70 | 75 | 46 | 15790.7707 | 13925.2647 | 1865.5061 | 8678.0315 | 1479.4401 | 0.00049591 | 0.00064122 | 1.7741 | 5.381 | 2549 | 0.05957 | 1225 | 0 | 0 | 5.3923 | 2309 | 0
Bay Area | 7820 | 74 | 144.2125 | 217 | 224.0177 | 44 | 2.7927e-05 | 109.7275 | 0.70192 | 977.5608 | 4167.4309 | 6.2434 | 5.0798 | 403.4698 | 1.2281 | 0.0028362 | 2.3084e-05 | 0.34101 | 0.64376 | {84C96F20-C20B-4D7E-B330-63B67A3A8540} | 14402108 | LAS POSITAS 2108 | MR182 | 37.6445 | -121.7679 | LAS POSITAS 2108MR182 | 92 | 95 | 18077.4684 | 11548.6884 | 6528.78 | 10768.7759 | 6272.4728 | 0.0010157 | 0.0012288 | 1.9488 | 4.9318 | 2565 | 0.12479 | 1226 | 0 | 0 | 6.6914 | 2173 | 0
Sierra | 1085 | 1080 | 1665.259 | 3014 | 2515.5317 | 292 | 9.6376e-05 | 39.1965 | 57.8801 | 614.5865 | 7443.202 | 1178.9626 | 5.6784 | 67.2658 | 1.1885 | 0.0028299 | 0.0031868 | 0.35833 | 0.66199 | {5D7A1019-73A7-4921-AA73-859EBCF0FBCE} | 152481104 | BRUNSWICK 1104 | 2112 | 39.2416 | -121.0566 | BRUNSWICK 11042112 | 365 | 444 | 64046.6818 | 30961.8119 | 33084.8699 | 30961.8119 | 33084.8699 | 0.93055 | 0.028142 | 1.5419 | 10.3219 | 92 | 0.82634 | 1227 | 0 | 0 | 19.2388 | 1304 | 0
Bay Area | 7844 | 121 | 308.0577 | 276 | 392.7666 | 68 | 4.891e-05 | 60.5303 | 14.6049 | 1809.0746 | 20355.0966 | 750.4117 | 4.6686 | 281.84 | 1.1892 | 0.0028233 | 0.00044854 | 0.43841 | 0.78433 | {EEE52A91-AF03-4B18-9CCC-F7F6825D7052} | 42271103 | COTATI 1103 | 87402 | 38.1632 | -122.8902 | COTATI 110387402 | 54 | 30 | 19924.8475 | 18214.2492 | 1710.5983 | 18214.2492 | 1710.5983 | 0.0305 | 0.0033259 | 2.5459 | 4.0588 | 866 | 0.19198 | 1228 | 0 | 0 | 11.3178 | 1765 | 0
North Coast | 6694 | 2 | 3.7585 | 8 | 5.4662 | 3 | 5.0753e-05 | 63.5741 | 0.013966 | 0.40627 | 2.046 | 0.0027926 | 8.8223 | 71.1518 | 1.2522 | 0.0028166 | 3.5047e-05 | 0.25 | 0.68759 | {3A01C04B-1C28-4E51-9D30-D6AD9F524D9D} | 42771111 | UKIAH 1111 | 2504 | 39.1732 | -123.2131 | UKIAH 11112504 | 73 | 164 | 12412.1247 | 4779.0786 | 7633.046 | 52.248 | 97.7229 | 0.00010514 | 0.00015226 | 1.8792 | 2.6667 | 2398 | 0.0084498 | 1229 | 0 | 0 | 0.032465 | 2671 | 0
Bay Area | 2636 | 42 | 99.233 | 914 | 631.9963 | 108 | 6.2912e-05 | 78.1574 | 1.1492 | 26.7601 | 84.8718 | 0.39737 | 4.3123 | 209.7025 | 1.1042 | 0.0028133 | 6.5291e-05 | 0.045952 | 0.15702 | {1E4505DC-D80E-4F9F-A5C6-1B2DD1F7142B} | 14232107 | SAN RAMON 2107 | MR284 | 37.6977 | -121.9421 | SAN RAMON 2107MR284 | 234 | 192 | 42915.0228 | 24164.9 | 18750.1228 | 23158.7135 | 17335.7746 | 0.0070514 | 0.0067945 | 2.3627 | 8.463 | 2089 | 0.30384 | 1230 | 0 | 0 | 14.3902 | 2675 | 0
North Coast | 7276 | 47 | 138.6758 | 109 | 153.1188 | 17 | 7.3053e-05 | 53.3463 | 3.07 | 71.8399 | 285.6409 | 2.5294 | 6.3218 | 53.5568 | 1.3157 | 0.0028085 | 0.00015716 | 0.43119 | 0.90567 | {9A7B1854-4374-4D14-BB43-EA4EAD6446AB} | 43211101 | HARTLEY 1101 | circuit_breaker | 39.0767 | -122.933 | HARTLEY 1101circuit_breaker | 57 | 44 | 8035.3779 | 4864.6418 | 3170.7361 | 2204.3614 | 1366.8608 | 0.0026718 | 0.0012419 | 2.9505 | 6.4118 | 1555 | 0.047745 | 1231 | 0 | 0 | 1.3697 | 1861 | 0
Bay Area | 2432 | 0 | 0 | 17 | 20.4819 | 1 | 0.00012013 | 24.42 |  |  |  |  | 17.2279 | 107.5102 | 1.0155 | 0.0029335 | 0.00012013 | 0 | 0 | {97A379E6-C657-4B3B-9AC8-B4B0F3BA119F} | 42151104 | SANTA ROSA A 1104 | 220 | 38.4864 | -122.6771 | SANTA ROSA A 1104220 | 188 | 143 | 24753.6696 | 15355.5551 | 9398.1144 | 15355.5551 | 9398.1144 | 0.00012013 | 0.00012013 |  | 17 | 1747 | 0.0029335 | 1232 | 0 | 0 | 9.5415 | 2769 | 0
North Coast | 2432 | 567 | 786.6906 | 912 | 991.9579 | 89 | 7.2688e-05 | 42.7412 | 15.5326 | 76.6093 | 412.9576 | 15.5782 | 4.9586 | 35.9934 | 1.0145 | 0.0027758 | 0.00047991 | 0.62171 | 0.79307 | {97A379E6-C657-4B3B-9AC8-B4B0F3BA119F} | 42151104 | SANTA ROSA A 1104 | 220 | 38.4864 | -122.6771 | SANTA ROSA A 1104220 | 188 | 143 | 24753.6696 | 15355.5551 | 9398.1144 | 15355.5551 | 9398.1144 | 0.042712 | 0.0064693 | 1.3875 | 10.2472 | 812 | 0.24705 | 1232 | 0 | 0 | 9.5415 | 758 | 0
North Coast | 218 | 653 | 898.0622 | 1353 | 1242.874 | 110 | 0.00010604 | 30.3622 | 9.6518 | 186.3185 | 2121.8149 | 157.3875 | 1.1362 | 12.8735 | 1.0211 | 0.002764 | 0.00046486 | 0.48263 | 0.72257 | {46D8BBC2-519D-4FA1-BC3E-5FF3581AAFDB} | 43071102 | DUNBAR 1102 | circuit_breaker | 38.3834 | -122.5279 | DUNBAR 1102circuit_breaker | 225 | 634 | 42535.3129 | 13793.3359 | 28741.977 | 11754.0323 | 24605.0551 | 0.051134 | 0.011664 | 1.3753 | 12.3 | 838 | 0.30404 | 1233 | 0 | 0 | 7.3036 | 1317 | 0
Central Valley | 850 | 108 | 239.0891 | 412 | 328.7385 | 106 | 4.093e-05 | 74.2124 | 52.2242 | 655.0809 | 2530.2675 | 261.3897 | 9.9499 | 210.1147 | 1.3394 | 0.0027591 | 0.00068661 | 0.26214 | 0.72729 | {73788ED7-3EB0-46BC-B768-F67E7458E32E} | 163781704 | PEORIA 1704 | 59596 | 37.9009 | -120.5804 | PEORIA 170459596 | 484 | 864 | 98173.9533 | 57857.723 | 40316.2304 | 32203.8416 | 16983.1868 | 0.072781 | 0.0043386 | 2.2138 | 3.8868 | 576 | 0.29247 | 1234 | 0 | 0 | 20.0105 | 12 | 0
Bay Area | 7999 | 172 | 348.3955 | 376 | 425.9709 | 52 | 4.0906e-05 | 59.7873 | 4.7266 | 310.5121 | 3684.662 | 57.2026 | 2.6242 | 67.6059 | 1.2679 | 0.0027405 | 0.00011262 | 0.45745 | 0.81789 | {8D627439-1B8D-41BC-A6EE-EC8800086E69} | 43051101 | MONTICELLO 1101 | 654 | 38.5116 | -122.2134 | MONTICELLO 1101654 | 97 | 99 | 17417.2276 | 14051.7969 | 3365.4307 | 12946.7956 | 3035.6454 | 0.005856 | 0.0021271 | 2.0256 | 7.2308 | 1786 | 0.14251 | 1235 | 0 | 0 | 8.0448 | 2408 | 0
North Coast | 2815 | 114 | 198.3175 | 181 | 232.7014 | 17 | 0.00013145 | 19.6521 | 22.3237 | 60.527 | 153.5289 | 5.8974 | 3.6046 | 10.9839 | 1.0105 | 0.0027246 | 0.0016853 | 0.62983 | 0.85224 | {A98FD5E2-DDE3-4E25-9F0F-483626AE2A81} | 42571102 | MOLINO 1102 | 344 | 38.406 | -122.8918 | MOLINO 1102344 | 135 | 214 | 23378.245 | 9676.0469 | 13702.1981 | 1463.3176 | 2664.7041 | 0.02865 | 0.0022346 | 1.7396 | 10.6471 | 210 | 0.046318 | 1236 | 0 | 0 | 0.90926 | 899 | 0
Central Coast | 7812 | 407 | 586.1098 | 1270 | 1087.8228 | 113 | 5.93e-05 | 61.4167 | 0.21973 | 14.8186 | 76.1587 | 0.060408 | 2.6211 | 42.6019 | 1.1255 | 0.0027135 | 3.471e-05 | 0.32047 | 0.53879 | {4F22013A-C8F8-4C93-9CF0-829946636F4D} | 83242105 | MORGAN HILL 2105 | XR268 | 37.0328 | -121.6835 | MORGAN HILL 2105XR268 | 100 | 61 | 16662.9009 | 12821.0297 | 3841.8712 | 12821.0297 | 3841.8712 | 0.0039222 | 0.0067009 | 1.4401 | 11.2389 | 2402 | 0.30662 | 1237 | 0 | 0 | 7.9666 | 651 | 0
Sierra | 600 | 2626 | 3592.3593 | 6190 | 5256.8696 | 530 | 0.00010866 | 28.3757 | 64.0484 | 903.134 | 12303.1625 | 2165.505 | 3.0652 | 44.9642 | 1.1202 | 0.0027117 | 0.0030693 | 0.42423 | 0.68336 | {6647B708-EB30-40C8-9FB8-1AD5D9953BA6} | 152261106 | DIAMOND SPRINGS 1106 | 2100 | 38.6935 | -120.7678 | DIAMOND SPRINGS 11062100 | 624 | 642 | 111071.5262 | 62659.5156 | 48412.0106 | 62659.5156 | 48412.0106 | 1.6267 | 0.057588 | 1.368 | 11.6792 | 103 | 1.4372 | 1238 | 0 | 0 | 38.9348 | 1303 | 0
North Coast | 9157 | 243 | 357.3013 | 594 | 543.0146 | 67 | 8.8044e-05 | 31.6996 | 5.6878 | 224.4872 | 3247.2718 | 33.1464 | 0.94888 | 47.2669 | 1.1413 | 0.0027114 | 0.00028621 | 0.40909 | 0.658 | {2DE576B0-9ADE-465B-8612-83446037B4D3} | 43071101 | DUNBAR 1101 | 343 | 38.4315 | -122.5537 | DUNBAR 1101343 | 51 | 115 | 16343.1272 | 7181.969 | 9161.1582 | 7034.2123 | 9161.1582 | 0.019176 | 0.0058989 | 1.4704 | 8.8657 | 1158 | 0.18167 | 1239 | 0 | 0 | 4.3709 | 36 | 0
Central Valley | 2655 | 2313 | 3036.2826 | 6790 | 5092.1367 | 526 | 0.00012952 | 20.0018 | 91.9793 | 928.3792 | 18552.2033 | 5980.8894 | 1.3082 | 16.711 | 1.0291 | 0.0027079 | 0.0053917 | 0.34065 | 0.59627 | {0A126708-7779-4E45-A8D5-6CB2B8C285C8} | 163751102 | PINE GROVE 1102 | 3172 | 38.4101 | -120.6517 | PINE GROVE 11023172 | 740 | 1122 | 112871.0756 | 59226.0308 | 53645.0448 | 59226.0308 | 53645.0448 | 2.836 | 0.068128 | 1.3127 | 12.9087 | 32 | 1.4243 | 1240 | 0 | 0 | 36.8013 | 2199 | 0
Central Coast | 8617 | 20 | 27.5167 | 24 | 30.2358 | 1 | 3.7616e-05 | 71.7213 |  |  |  |  | 0.97788 | 71.3843 | 1.0332 | 0.0026979 | 3.7616e-05 | 0.83333 | 0.91007 | {7580C145-BC76-4DF0-BE7D-C5FC1E8761E1} | 82931101 | POINT MORETTI 1101 | 35874 | 37.0312 | -122.1871 | POINT MORETTI 110135874 | 16 | 2 | 490.7539 | 440.1765 | 50.5775 | 440.1765 | 50.5775 | 3.7616e-05 | 3.7616e-05 | 1.3758 | 24 | 2368 | 0.0026979 | 1241 | 0 | 0 | 0.27351 | 1879 | 0
North Coast | 150 | 75 | 117.1139 | 143 | 145.3288 | 14 | 6.3043e-05 | 42.509 | 4.5125 | 38.3538 | 189.2972 | 0.93994 | 0.98436 | 8.3729 | 1.0169 | 0.0026951 | 0.00022334 | 0.52448 | 0.80585 | {61AD59B6-3DE5-4155-9391-74B53A84E200} | 192151132 | NEWBURG 1132 | 2074 | 40.5946 | -124.1427 | NEWBURG 11322074 | 343 | 1281 | 65515.4362 | 16861.3212 | 48654.115 | 1527.0717 | 1850.4272 | 0.0031268 | 0.00088261 | 1.5615 | 10.2143 | 1331 | 0.037732 | 1242 | 0 | 0 | 0.94888 | 1816 | 0
Central Valley | 324 | 2246 | 2989.2726 | 4911 | 4347.5938 | 452 | 9.5249e-05 | 29.5254 | 58.7187 | 1365.4632 | 20783.441 | 3226.5573 | 1.252 | 36.492 | 1.1555 | 0.0026949 | 0.0024371 | 0.45734 | 0.68757 | {7C8CD214-E17A-42EE-B431-70BEE1692D64} | 163201102 | WEST POINT 1102 | 4790 | 38.3868 | -120.5244 | WEST POINT 11024790 | 458 | 542 | 76730.7191 | 53036.5916 | 23694.1275 | 53036.5916 | 23694.1275 | 1.1016 | 0.043053 | 1.3309 | 10.865 | 132 | 1.2181 | 1243 | 0 | 0 | 32.9554 | 53 | 0
Sierra | 5835 | 562 | 994.8368 | 2277 | 1702.1108 | 251 | 7.681e-05 | 35.1345 | 12.6381 | 145.4778 | 1306.9108 | 48.602 | 4.1644 | 80.9894 | 1.1305 | 0.0026935 | 0.00049927 | 0.24682 | 0.58447 | {26B90757-99A6-4B30-9CD9-107B9465AA3E} | 153652109 | SHINGLE SPRINGS 2109 | 81390 | 38.8002 | -120.9086 | SHINGLE SPRINGS 210981390 | 318 | 329 | 53715.0439 | 30296.9721 | 23418.0718 | 30296.9721 | 23418.0718 | 0.12532 | 0.019279 | 1.7702 | 9.0717 | 787 | 0.67607 | 1244 | 0 | 0 | 18.8257 | 457 | 0
Sierra | 4817 | 590 | 671.2274 | 1519 | 1083.7133 | 123 | 9.3841e-05 | 30.4303 | 38.6337 | 530.2037 | 11757.9175 | 4140.2051 | 0.57434 | 11.2206 | 1.0108 | 0.002692 | 0.0017438 | 0.38841 | 0.61938 | {5BE9A1BF-757A-4781-BCE2-C4049CA25F7D} | 152762101 | EL DORADO PH 2101 | 19612 | 38.7621 | -120.5586 | EL DORADO PH 210119612 | 176 | 224 | 27003.4259 | 14689.1645 | 12314.2614 | 14689.1645 | 12314.2614 | 0.21448 | 0.011542 | 1.1377 | 12.3496 | 202 | 0.33111 | 1245 | 0 | 0 | 9.1274 | 848 | 0
Sierra | 9421 | 152 | 154.9811 | 490 | 307.9271 | 73 | 3.3628e-05 | 75.6382 | 3.2031 | 1681.5991 | 45773.4752 | 574.6912 | 0.0056067 | 23.1431 | 1.1194 | 0.0026902 | 6.7378e-05 | 0.3102 | 0.5033 | {FD2262BF-C160-4434-8E95-55FF0A0B15F6} | 152101101 | ALLEGHANY 1101 | 808 | 39.4879 | -120.8571 | ALLEGHANY 1101808 | 31 | 4 | 9939.4884 | 9882.4147 | 57.0736 | 9882.4147 | 57.0736 | 0.0049186 | 0.0024548 | 1.0196 | 6.7123 | 2075 | 0.19639 | 1246 | 0 | 0 | 6.1406 | 112 | 0
North Coast | 7173 | 1151 | 1468.7323 | 1525 | 1675.2604 | 106 | 0.00015218 | 18.0757 | 6.0613 | 88.3206 | 592.8539 | 5.1262 | 1.8968 | 47.3833 | 1.0626 | 0.0026766 | 0.00047098 | 0.75475 | 0.87672 | {17A00714-8A49-49C0-B860-6006F3A8F3AD} | 42681101 | LAYTONVILLE 1101 | 89606 | 39.6878 | -123.4891 | LAYTONVILLE 110189606 | 178 | 245 | 32872.5808 | 19260.766 | 13611.8147 | 18642.295 | 13156.2942 | 0.049923 | 0.016131 | 1.276 | 14.3868 | 823 | 0.28372 | 1247 | 0 | 0 | 11.5838 | 512 | 0
Central Coast | 532 | 29 | 60.0919 | 44 | 67.099 | 11 | 4.8941e-05 | 60.0595 | 10.625 | 803.8135 | 4563.7817 | 79.7759 | 5.6221 | 292.1311 | 1.1211 | 0.0026625 | 0.00022779 | 0.65909 | 0.89557 | {F7BD212B-7F44-4A16-B423-2BCFB7829D6C} | 183052113 | TEMPLETON 2113 | R82 | 35.5299 | -120.523 | TEMPLETON 2113R82 | 683 | 548 | 155125.0644 | 111327.2051 | 43797.8593 | 60266.4888 | 18150.6235 | 0.0025057 | 0.00053836 | 2.0721 | 4 | 1321 | 0.029288 | 1248 | 0 | 0 | 37.4478 | 1465 | 0
Sierra | 784 | 148 | 256.8096 | 639 | 452.9971 | 81 | 8.1165e-05 | 35.0165 | 7.754 | 58.7641 | 346.1535 | 5.449 | 3.2216 | 28.3201 | 1.1161 | 0.0026592 | 0.00029668 | 0.23161 | 0.56691 | {AD1702BF-568D-4020-87DE-29F495495BCD} | 152691107 | HIGGINS 1107 | circuit_breaker | 39.0439 | -121.0909 | HIGGINS 1107circuit_breaker | 442 | 798 | 69196.7005 | 30542.9222 | 38653.7784 | 8142.9425 | 7225.3692 | 0.024031 | 0.0065744 | 1.7352 | 7.8889 | 1132 | 0.2154 | 1249 | 0 | 0 | 5.0598 | 1429 | 0
Bay Area | 9498 | 161 | 237.4514 | 429 | 405.0073 | 40 | 0.00010352 | 23.8617 | 0.010477 | 26.4225 | 159.2082 | 0.003247 | 0.091759 | 49.4607 | 1.0855 | 0.0026529 | 5.566e-05 | 0.37529 | 0.58629 | {52879B9D-A33B-4D4E-99FA-0487B37405B8} | 42261101 | BOLINAS 1101 | 806 | 37.9559 | -122.6176 | BOLINAS 1101806 | 21 | 7 | 5085.6474 | 4898.4533 | 187.1941 | 4898.4533 | 187.1941 | 0.0022264 | 0.0041407 | 1.4749 | 10.725 | 2183 | 0.10612 | 1250 | 0 | 0 | 3.0438 | 2314 | 0
Central Valley | 1316 | 188 | 272.116 | 900 | 602.8256 | 165 | 2.8491e-05 | 98.2013 | 19.0836 | 354.0024 | 3031.3249 | 275.6403 | 5.3534 | 108.1911 | 1.2383 | 0.0026527 | 0.00027112 | 0.20889 | 0.4514 | {48B8D134-2217-4EE4-BD7C-3270CBBFB37D} | 254151101 | AUBERRY 1101 | R2838 | 37.0876 | -119.4688 | AUBERRY 1101R2838 | 328 | 524 | 61751.2327 | 32678.392 | 29072.8407 | 32678.392 | 29072.8407 | 0.044735 | 0.004701 | 1.4474 | 5.4545 | 1202 | 0.4377 | 1251 | 0 | 0 | 20.3054 | 1517 | 0
Bay Area | 1854 | 11 | 18.7304 | 42 | 34.0902 | 3 | 3.5484e-05 | 63.4722 | 2.7425 | 18.7923 | 69.3461 | 0.38037 | 4.941 | 48.8801 | 1.1084 | 0.0026389 | 0.0001026 | 0.2619 | 0.54944 | {C2E68366-657D-4902-BBD7-D59A6C76C29A} | 42021112 | NAPA 1112 | circuit_breaker | 38.2956 | -122.2786 | NAPA 1112circuit_breaker | 486 | 1377 | 86337.1008 | 26219.4017 | 60117.6991 | 272.3504 | 248.1578 | 0.00030781 | 0.00010645 | 1.7028 | 14 | 1843 | 0.0079168 | 1252 | 0 | 0 | 0.16923 | 2365 | 0
North Coast | 9369 | 214 | 321.28 | 494 | 483.1557 | 27 | 0.00012247 | 19.4554 | 3.0842 | 46.3779 | 344.8257 | 1.1076 | 0.17549 | 13.5074 | 1.0105 | 0.0026378 | 0.00023506 | 0.4332 | 0.66496 | {F763F6AF-FC97-4F89-AD25-F9455AF541C2} | 42811113 | MONTE RIO 1113 | 678 | 38.4867 | -123.0158 | MONTE RIO 1113678 | 25 | 62 | 5741.2654 | 2967.1836 | 2774.0818 | 2967.1836 | 2774.0818 | 0.0063467 | 0.0033068 | 1.5013 | 18.2963 | 1297 | 0.07122 | 1253 | 0 | 0 | 1.8437 | 2386 | 0
Central Valley | 3908 | 179 | 270.6088 | 1275 | 727.8389 | 188 | 7.9835e-05 | 34.1779 | 10.454 | 70.2772 | 506.9598 | 11.4742 | 3.7543 | 61.4267 | 1.1949 | 0.0026357 | 0.00047003 | 0.14039 | 0.3718 | {2F9F4A6E-5722-4460-BD68-D94825E8F2C8} | 254432102 | COARSEGOLD 2102 | 5380 | 37.3089 | -119.5849 | COARSEGOLD 21025380 | 218 | 211 | 39217.1306 | 22745.3926 | 16471.738 | 22745.3926 | 16471.738 | 0.088365 | 0.015009 | 1.5118 | 6.7819 | 828 | 0.49551 | 1254 | 0 | 0 | 14.1333 | 1509 | 0
Central Valley | 6352 | 3 | 3.6831 | 15 | 8.1954 | 5 | 9.1402e-05 | 24.5053 | 2.2908 | 50.187 | 194.3789 | 1.2977 | 5.3889 | 174.843 | 1.4584 | 0.0026253 | 0.00020804 | 0.2 | 0.44942 | {CC3A7F8F-5717-4639-B6A5-ECE8361467E4} | 163341101 | CLAY 1101 | circuit_breaker | 38.3423 | -120.9347 | CLAY 1101circuit_breaker | 103 | 201 | 11121.7933 | 4411.9174 | 6709.8759 | 707.4258 | 67.6469 | 0.0010402 | 0.00045701 | 1.2277 | 3 | 1386 | 0.013126 | 1255 | 0 | 0 | 0.43957 | 1759 | 0
North Valley | 2700 | 1179 | 1655.7042 | 1967 | 2032.0391 | 303 | 0.00011256 | 51.876 | 10.1272 | 802.7638 | 4937.7926 | 83.5674 | 4.1173 | 298.952 | 1.2448 | 0.0026155 | 0.00060688 | 0.59939 | 0.8148 | {D9E3C410-A0BF-4EA8-96F2-E696EF9ADFFA} | 103601101 | WHITMORE 1101 | 45262 | 40.6173 | -121.9334 | WHITMORE 110145262 | 251 | 189 | 61043.2137 | 46035.1045 | 15008.1093 | 46035.1045 | 15008.1093 | 0.18388 | 0.034105 | 1.4043 | 6.4917 | 662 | 0.79248 | 1256 | 0 | 0 | 28.6049 | 2490 | 0
Central Valley | 1211 | 552 | 810.3465 | 2651 | 1780.2598 | 273 | 5.8637e-05 | 50.8358 | 6.5615 | 110.4035 | 961.3205 | 22.9496 | 3.917 | 51.048 | 1.0538 | 0.0026154 | 0.00019448 | 0.20822 | 0.45518 | {194E4857-C055-4CC4-9616-06A060725A90} | 254421103 | OAKHURST 1103 | 5480 | 37.3754 | -119.6293 | OAKHURST 11035480 | 287 | 542 | 57261.8501 | 27507.5877 | 29754.2625 | 27507.5877 | 29754.2625 | 0.053093 | 0.016008 | 1.468 | 9.7106 | 1428 | 0.71402 | 1257 | 0 | 0 | 17.0924 | 1799 | 0
Central Coast | 8168 | 1982 | 3250.6954 | 2970 | 3803.4397 | 206 | 5.9844e-05 | 43.5874 | 2.1246 | 118.8246 | 1509.947 | 17.885 | 0.82321 | 17.3897 | 1.0948 | 0.0026009 | 8.7352e-05 | 0.66734 | 0.85467 | {6C8A015E-28D9-4A6C-B2B8-20363D966398} | 82841102 | BIG BASIN 1102 | 11062 | 37.1989 | -122.1537 | BIG BASIN 110211062 | 118 | 81 | 27187.9206 | 21172.9967 | 6014.9239 | 21172.9967 | 6014.9239 | 0.017994 | 0.012328 | 1.6401 | 14.4175 | 1929 | 0.53578 | 1258 | 0 | 0 | 13.1563 | 2887 | 0
Central Valley | 1346 | 1029 | 1294.516 | 3579 | 2391.229 | 241 | 0.00016012 | 17.9408 | 35.0211 | 383.7835 | 6688.8319 | 1629.224 | 0.63373 | 13.8933 | 1.0186 | 0.0025975 | 0.0024092 | 0.28751 | 0.54136 | {B84BB2A7-38F5-4777-ACCF-AE61211F946D} | 163751102 | PINE GROVE 1102 | 1222 | 38.436 | -120.5561 | PINE GROVE 11021222 | 400 | 707 | 63090.2564 | 27692.5615 | 35397.6949 | 27692.5615 | 35397.6949 | 0.58061 | 0.038588 | 1.258 | 14.8506 | 135 | 0.62601 | 1259 | 0 | 0 | 17.2074 | 886 | 0
Sierra | 519 | 1921 | 2546.3852 | 5372 | 4216.7886 | 451 | 0.00014345 | 19.2937 | 112.0574 | 1763.4195 | 28461.6814 | 8935.4614 | 2.624 | 37.6703 | 1.11 | 0.0025958 | 0.0066997 | 0.35759 | 0.60387 | {724A4FDA-4A16-48BB-BCFD-6B70230700BB} | 153082106 | PLACERVILLE 2106 | 92012 | 38.8585 | -120.8331 | PLACERVILLE 210692012 | 560 | 673 | 87706.2034 | 46683.5024 | 41022.701 | 46683.5024 | 41022.701 | 3.0216 | 0.064696 | 1.3256 | 11.9113 | 23 | 1.1707 | 1260 | 0 | 0 | 29.0078 | 382 | 0
North Coast | 6664 | 936 | 1393.7472 | 1339 | 1576.6802 | 119 | 0.00013526 | 19.4454 | 20.5476 | 1017.76 | 20990.8737 | 762.6592 | 2.3242 | 23.9276 | 1.1486 | 0.002594 | 0.0014321 | 0.69903 | 0.88398 | {2ADAB335-F68D-4E0E-93A5-403C7C54DA76} | 192171103 | WILLOW CREEK 1103 | 7514 | 40.9334 | -123.6249 | WILLOW CREEK 11037514 | 177 | 300 | 22428.986 | 16087.5864 | 6341.3996 | 13903.8607 | 5402.1943 | 0.17042 | 0.016096 | 1.489 | 11.2521 | 264 | 0.30868 | 1261 | 0 | 0 | 8.6395 | 1031 | 0
Bay Area | 4265 | 443 | 700.1975 | 1177 | 1158.6266 | 76 | 0.00014272 | 18.2046 | 1.1015 | 3.1913 | 9.465 | 0.032604 | 0.23705 | 2.7847 | 1.0075 | 0.0025849 | 0.00015414 | 0.37638 | 0.60433 | {26E85C09-0B57-42B9-B352-ED273600E95D} | 24251101 | WOODSIDE 1101 | 1922 | 37.3972 | -122.2475 | WOODSIDE 11011922 | 132 | 132 | 15294.8241 | 7665.9565 | 7628.8675 | 7077.1681 | 7268.3917 | 0.011714 | 0.010847 | 1.5806 | 15.4868 | 1571 | 0.19646 | 1262 | 0 | 0 | 4.3975 | 2896 | 0
Sierra | 6109 | 530 | 823.8515 | 1822 | 1369.8623 | 268 | 0.00010509 | 26.2345 | 30.3677 | 616.9933 | 8634.7441 | 1012.0492 | 3.8042 | 61.0397 | 1.1622 | 0.0025736 | 0.0016304 | 0.29089 | 0.60141 | {2AFE09FA-88B1-4B78-BACA-DA079C6170B5} | 153082106 | PLACERVILLE 2106 | 935216 | 38.7574 | -120.7681 | PLACERVILLE 2106935216 | 288 | 281 | 55117.9672 | 33799.5586 | 21318.4086 | 33799.5586 | 21318.4086 | 0.43694 | 0.028163 | 1.5544 | 6.7985 | 223 | 0.68972 | 1263 | 0 | 0 | 21.0021 | 1955 | 0
Sierra | 4624 | 208 | 255.6777 | 1385 | 912.5156 | 73 | 3.2035e-05 | 83.7918 | 12.0537 | 1127.323 | 30764.7279 | 1558.1704 | 2.5364 | 21.2203 | 1.055 | 0.0025712 | 0.00019417 | 0.15018 | 0.28019 | {326E3BAE-F690-4463-8FFC-C774FBAA59CE} | 152101101 | ALLEGHANY 1101 | circuit_breaker | 39.4657 | -120.8448 | ALLEGHANY 1101circuit_breaker | 90 | 169 | 12544.4698 | 6967.0605 | 5577.4092 | 6967.0605 | 5577.4092 | 0.014174 | 0.0023385 | 1.2292 | 18.9726 | 1430 | 0.18769 | 1264 | 0 | 0 | 4.3291 | 2275 | 0
North Coast | 2817 | 805 | 1341.9839 | 1480 | 1680.5243 | 132 | 0.00012558 | 25.1154 | 5.7688 | 102.3839 | 1145.3754 | 26.8202 | 0.69015 | 21.7574 | 1.1661 | 0.0025415 | 0.00043827 | 0.54392 | 0.79855 | {EA690835-9E38-4D73-A546-B5676BCE1BEA} | 42811113 | MONTE RIO 1113 | 346 | 38.5044 | -122.9975 | MONTE RIO 1113346 | 177 | 484 | 42485.3909 | 16237.5238 | 26247.867 | 16237.5238 | 26247.867 | 0.057852 | 0.016577 | 1.6671 | 11.2121 | 883 | 0.33548 | 1265 | 0 | 0 | 10.0895 | 1760 | 0
Bay Area | 7409 | 889 | 1965.5841 | 1066 | 2049.533 | 94 | 7.9344e-05 | 28.6578 | 1.071 | 18.9615 | 84.33 | 0.36546 | 1.2123 | 19.4396 | 1.0744 | 0.0025375 | 9.0292e-05 | 0.83396 | 0.95904 | {75B0B322-68D2-4160-BC4E-E90092A2B4DE} | 24101101 | HALF MOON BAY 1101 | 2500 | 37.4946 | -122.3687 | HALF MOON BAY 11012500 | 138 | 159 | 20786.8726 | 11167.0911 | 9619.7815 | 9460.9126 | 9466.5039 | 0.0084875 | 0.0074583 | 2.211 | 11.3404 | 1906 | 0.23852 | 1266 | 0 | 0 | 5.8787 | 2141 | 0
Central Valley | 2031 | 107 | 155.662 | 658 | 393.4169 | 77 | 7.0985e-05 | 48.8171 | 3.2881 | 263.5195 | 2036.6378 | 14.2311 | 3.3204 | 169.4608 | 1.4433 | 0.0025361 | 0.00015605 | 0.16261 | 0.39567 | {C6E29021-78E0-4CE1-AD84-6C3DE1BD57E9} | 163541102 | OLETA 1102 | 1228 | 38.5137 | -120.825 | OLETA 11021228 | 498 | 344 | 107856.612 | 69198.1694 | 38658.4425 | 12585.9936 | 8245.9928 | 0.012016 | 0.0054659 | 1.4548 | 8.5455 | 1560 | 0.19528 | 1267 | 0 | 0 | 7.8206 | 1768 | 0
North Coast | 1708 | 1825 | 3176.1979 | 3104 | 3732.2598 | 307 | 9.1712e-05 | 36.0145 | 1.2508 | 123.67 | 1057.4854 | 2.5251 | 0.20595 | 18.5735 | 1.0727 | 0.0025321 | 0.00010242 | 0.58795 | 0.85101 | {68CC0E2F-7024-44BE-85E9-7639B7540AB9} | 42761101 | FORT BRAGG A 1101 | 95294 | 39.5748 | -123.7698 | FORT BRAGG A 110195294 | 240 | 222 | 62745.5101 | 43705.7865 | 19039.7236 | 43187.6602 | 19039.7236 | 0.031443 | 0.028155 | 1.7404 | 10.1107 | 1844 | 0.77737 | 1268 | 0 | 0 | 26.8356 | 1490 | 0
Central Valley | 2368 | 628 | 972.7724 | 2876 | 2022.1635 | 277 | 6.8984e-05 | 47.6691 | 9.5523 | 243.1636 | 1851.0192 | 35.419 | 3.2827 | 65.4538 | 1.2142 | 0.0025239 | 0.00037536 | 0.21836 | 0.48106 | {F6CDB784-D217-4455-8CED-BCD020F0A7C6} | 163451702 | FROGTOWN 1702 | 290609 | 38.1112 | -120.5088 | FROGTOWN 1702290609 | 232 | 299 | 48513.0069 | 29095.2779 | 19417.729 | 29095.2779 | 19417.729 | 0.10398 | 0.019108 | 1.549 | 10.3827 | 975 | 0.69913 | 1269 | 0 | 0 | 18.079 | 882 | 0
North Coast | 5240 | 549 | 1071.4449 | 709 | 1154.4375 | 36 | 0.00012583 | 19.8807 | 8.7191 | 273.8064 | 3696.3042 | 71.4448 | 0.49545 | 20.8195 | 1.0231 | 0.0025159 | 0.00052339 | 0.77433 | 0.92811 | {A8069B35-D465-4FFC-9D93-424130BEE74D} | 42091101 | MIRABEL 1101 | 4859 | 38.4755 | -122.9526 | MIRABEL 11014859 | 31 | 56 | 8529.7555 | 2980.2139 | 5549.5416 | 2980.2139 | 5549.5416 | 0.018842 | 0.0045299 | 1.9516 | 19.6944 | 767 | 0.090574 | 1270 | 0 | 0 | 1.8518 | 2210 | 0
North Coast | 8982 | 51 | 70.8715 | 73 | 77.8563 | 15 | 5.9849e-05 | 55.5267 | 4.0717 | 106.698 | 946.4753 | 7.6674 | 4.8128 | 260.7048 | 1.3956 | 0.0025076 | 0.00023519 | 0.69863 | 0.91029 | {0AEE71D0-17A5-4B33-BC11-93FDB3F0422F} | 43351103 | LUCERNE 1103 | 4200 | 39.1173 | -122.902 | LUCERNE 11034200 | 49 | 18 | 9230.5783 | 7940.3444 | 1290.2339 | 6495.7462 | 791.9514 | 0.0035278 | 0.00089773 | 1.3896 | 4.8667 | 1296 | 0.037615 | 1271 | 0 | 0 | 4.0363 | 799 | 0
North Coast | 7480 | 2 | 2.4554 | 5 | 4.3058 | 4 | 7.7265e-05 | 29.8685 | 0.0046088 | 0.22239 | 0.0063376 | 2.9208e-08 | 9.7926 | 72.0705 | 1.1388 | 0.0025063 | 4.829e-05 | 0.4 | 0.57026 | {40D7F055-E8F9-4650-B226-FC76BC481B62} | 42721104 | SONOMA 1104 | 5661 | 38.3044 | -122.5031 | SONOMA 11045661 | 100 | 106 | 16194.9632 | 8171.7539 | 8023.2093 | 3397.3315 | 4091.3512 | 0.00019316 | 0.00030906 | 1.2277 | 1.25 | 2246 | 0.010025 | 1272 | 0 | 0 | 2.111 | 1484 | 0
North Coast | 7552 | 1199 | 1578.7258 | 2089 | 2084.513 | 183 | 0.00010967 | 22.2728 | 7.4158 | 157.5728 | 1904.3576 | 54.4666 | 1.444 | 40.9687 | 1.0633 | 0.0025029 | 0.00047215 | 0.57396 | 0.75736 | {A91227FD-6BAA-4D3E-82C2-58CC21F46A65} | 43321103 | RINCON 1103 | 568 | 38.5173 | -122.655 | RINCON 1103568 | 186 | 186 | 38664.056 | 20662.4363 | 18001.6197 | 20662.4363 | 18001.6197 | 0.086403 | 0.02007 | 1.3167 | 11.4153 | 822 | 0.45803 | 1273 | 0 | 0 | 12.839 | 621 | 0
North Valley | 9470 | 42 | 55.0071 | 219 | 130.197 | 26 | 8.3022e-05 | 23.9562 | 8.7739 | 218.9727 | 2409.3017 | 29.4258 | 0.40376 | 40.6146 | 1.0099 | 0.0024979 | 0.00035603 | 0.19178 | 0.42249 | {DC239059-B1DA-4C89-A482-3310C8764DA5} | 102541102 | VOLTA 1102 | circuit_breaker | 40.4594 | -121.8676 | VOLTA 1102circuit_breaker | 36 | 13 | 5670.844 | 5307.8332 | 363.0108 | 5307.8332 | 363.0108 | 0.0092569 | 0.0021586 | 1.3097 | 8.4231 | 1006 | 0.064946 | 1274 | 0 | 0 | 3.2981 | 2030 | 0
Central Coast | 7638 | 1 | 1.2277 | 7 | 2.5082 | 2 | 4.7778e-05 | 52.253 | 0.66279 | 668.5179 | 4537.0205 | 3.0071 | 2.3883 | 832.4893 | 1.5509 | 0.0024964 | 3.9121e-05 | 0.14286 | 0.48949 | {8F3B3809-0943-44A3-BEB7-992AA87124DA} | 182391103 | OILFIELDS 1103 | N62 | 35.7884 | -120.9562 | OILFIELDS 1103N62 | 47 | 25 | 9622.3276 | 8948.1922 | 674.1354 | 8948.1922 | 674.1354 | 7.8242e-05 | 9.5555e-05 | 1.2277 | 3.5 | 2354 | 0.0049929 | 1275 | 0 | 0 | 5.5601 | 2007 | 0
Sierra | 3005 | 1874 | 2372.7992 | 3661 | 3360.4915 | 333 | 8.9625e-05 | 28.5663 | 71.9805 | 983.6686 | 17121.645 | 4626.052 | 2.2245 | 23.4534 | 1.06 | 0.0024957 | 0.0032337 | 0.51188 | 0.70609 | {A8C871E9-A558-4EBE-96DF-EF0BB9E9DE44} | 152431102 | SHADY GLEN 1102 | circuit_breaker | 39.1152 | -120.9537 | SHADY GLEN 1102circuit_breaker | 363 | 365 | 56041.9434 | 34434.861 | 21607.0824 | 33414.9149 | 21573.6595 | 1.0768 | 0.029845 | 1.2662 | 10.994 | 88 | 0.83108 | 1276 | 0 | 0 | 20.7631 | 770 | 0
North Valley | 2714 | 110 | 151.7214 | 350 | 274.1033 | 69 | 3.7145e-05 | 70.584 | 1.033 | 226.9325 | 2048.8056 | 2.163 | 2.691 | 107.7909 | 1.1425 | 0.0024913 | 4.1932e-05 | 0.31429 | 0.55352 | {2A928B3F-2AFB-4E95-9D5F-1D4611A31405} | 103311101 | BURNEY 1102 | 1358 | 40.8795 | -121.6747 | BURNEY 11021358 | 69 | 67 | 17489.638 | 14868.5059 | 2621.1321 | 12955.3272 | 1692.8533 | 0.0028933 | 0.002563 | 1.3793 | 5.0725 | 2309 | 0.1719 | 1277 | 0 | 0 | 8.0501 | 887 | 0
North Coast | 4861 | 253 | 417.5019 | 434 | 513.1087 | 32 | 0.00013434 | 20.8719 | 19.7321 | 49.3321 | 454.9744 | 13.6004 | 0.7285 | 6.9008 | 1.0064 | 0.0024853 | 0.0013438 | 0.58295 | 0.81367 | {1D7AE122-66AC-404A-82FF-2ECB27492940} | 42811113 | MONTE RIO 1113 | 180 | 38.4967 | -123.007 | MONTE RIO 1113180 | 61 | 312 | 14634.6703 | 3131.1085 | 11503.5618 | 3131.1085 | 11503.5618 | 0.043001 | 0.0042988 | 1.6502 | 13.5625 | 284 | 0.079529 | 1278 | 0 | 0 | 1.9456 | 2698 | 0
Central Valley | 2199 | 462 | 694.8033 | 1644 | 1126.4613 | 220 | 4.6852e-05 | 45.8264 | 25.8128 | 363.6173 | 2714.387 | 130.9534 | 5.615 | 74.9328 | 1.2456 | 0.0024815 | 0.00057943 | 0.28102 | 0.6168 | {A13891AD-BB5A-427E-8F5C-CEB24021177B} | 163351702 | CURTIS 1702 | 47488 | 37.9649 | -120.2507 | CURTIS 170247488 | 324 | 673 | 72960.1433 | 33088.8899 | 39871.2534 | 29796.4907 | 28840.9557 | 0.12748 | 0.010307 | 1.5039 | 7.4727 | 698 | 0.54593 | 1279 | 0 | 0 | 18.5147 | 23 | 0
Central Coast | 6524 | 2 | 1.9572 | 2 | 1.9572 | 1 | 2.5339e-05 | 97.8655 | 0.14063 | 169.8713 | 1014.8099 | 1.5974 | 5.7434 | 556.5856 | 1.2058 | 0.0024798 | 3.5634e-06 | 1 | 1 | {05828C1E-8E18-466B-88E7-9FC0E3CD182B} | 182191101 | SAN ARDO 1101 | 7632 | 36.0712 | -120.9813 | SAN ARDO 11017632 | 43 | 28 | 13680.8151 | 13067.8012 | 613.0139 | 668.3905 | 199.8475 | 3.5634e-06 | 2.5339e-05 | 0.97861 | 2 | 2859 | 0.0024798 | 1280 | 0 | 0 | 0.41532 | 851 | 0
North Coast | 9603 | 400 | 575.1854 | 590 | 663.6224 | 74 | 0.00015712 | 13.5901 | 0.096965 | 292.7379 | 3427.0247 | 0.48541 | 0.085476 | 37.0474 | 1.1222 | 0.0024672 | 9.787e-05 | 0.67797 | 0.86674 | {C155999E-0638-4738-B652-2E7910103A63} | 192251102 | RIO DELL 1102 | 75970 | 40.4708 | -124.1362 | RIO DELL 110275970 | 48 | 13 | 11619.6657 | 11373.8899 | 245.7759 | 11373.8899 | 245.7759 | 0.0072424 | 0.011627 | 1.438 | 7.973 | 1864 | 0.18257 | 1281 | 0 | 0 | 7.0674 | 810 | 0
Central Coast | 4724 | 38 | 59.1981 | 225 | 160.8347 | 58 | 1.8309e-05 | 144.6958 | 1.7252 | 1100.243 | 4755.4761 | 18.1214 | 3.8592 | 891.9861 | 1.476 | 0.0024604 | 2.2627e-05 | 0.16889 | 0.36807 | {96906956-5C77-4774-B51C-564876632563} | 182811102 | SISQUOC 1102 | M54 | 34.8627 | -120.2773 | SISQUOC 1102M54 | 190 | 144 | 57881.5824 | 48149.8206 | 9731.7618 | 30625.2961 | 5692.0749 | 0.0013124 | 0.0010619 | 1.5578 | 3.8793 | 2572 | 0.14271 | 1282 | 0 | 0 | 19.0297 | 2377 | 0
Sierra | 964 | 1795 | 2743.3323 | 4669 | 3990.3108 | 532 | 8.7024e-05 | 28.444 | 28.1583 | 370.1161 | 3925.1572 | 403.8652 | 5.3039 | 63.1437 | 1.1977 | 0.0024588 | 0.0011907 | 0.38445 | 0.6875 | {71CA17E4-B079-4EB2-8611-562BAD82EEBD} | 152691110 | HIGGINS 1110 | 2408 | 39.0472 | -121.0488 | HIGGINS 11102408 | 555 | 502 | 95382.6509 | 57049.967 | 38332.6839 | 57049.967 | 38332.6839 | 0.63347 | 0.046297 | 1.5283 | 8.7763 | 325 | 1.3081 | 1283 | 0 | 0 | 35.4492 | 62 | 0
Central Valley | 8021 | 90 | 135.6216 | 236 | 213.5725 | 48 | 3.459e-05 | 90.5898 | 7.2573 | 426.3518 | 4254.0305 | 84.4888 | 1.0253 | 188.2264 | 1.2875 | 0.0024584 | 0.00012447 | 0.38136 | 0.63501 | {DBF29453-0B03-42AD-A97A-1CA961543977} | 252192105 | BEAR VALLEY 2105 | 76694 | 37.741 | -120.128 | BEAR VALLEY 210576694 | 51 | 36 | 10282.5742 | 7317.351 | 2965.2231 | 7317.351 | 2965.2231 | 0.0059747 | 0.0016603 | 1.5069 | 4.9167 | 1728 | 0.118 | 1284 | 0 | 0 | 4.5468 | 1005 | 0
Sierra | 140 | 1689 | 2314.543 | 3927 | 3318.8857 | 321 | 8.2425e-05 | 29.3818 | 107.0556 | 1459.1637 | 22496.0496 | 3954.3662 | 3.9141 | 65.2439 | 1.1691 | 0.0024444 | 0.0045037 | 0.4301 | 0.69739 | {289FE0E9-9F49-4A41-845E-1E9AE4F19427} | 152282101 | MOUNTAIN QUARRIES 2101 | 1130 | 38.9131 | -120.9155 | MOUNTAIN QUARRIES 21011130 | 355 | 301 | 53141.9894 | 31854.654 | 21287.3354 | 31854.654 | 21287.3354 | 1.4457 | 0.026459 | 1.3704 | 12.2336 | 44 | 0.78465 | 1285 | 0 | 0 | 19.7936 | 645 | 0
Bay Area | 2694 | 26 | 59.9492 | 31 | 62.2279 | 6 | 9.307e-06 | 294.4533 | 0 | 0 | 0 | 0 | 8.9919 | 167.1724 | 1.052 | 0.0024408 | 6.9452e-06 | 0.83871 | 0.96338 | {C29E1CFF-9B01-49C8-A70D-1B966DB72A34} | 13501108 | JARVIS 1108 | MR368 | 37.6226 | -122.039 | JARVIS 1108MR368 | 136 | 462 | 23394.7973 | 5392.0942 | 18002.7031 | 761.5311 | 986.4007 | 4.1671e-05 | 5.5842e-05 | 2.3057 | 5.1667 | 2824 | 0.014645 | 1286 | 0 | 0 | 0.47319 | 2718 | 0
Central Coast | 1381 | 805 | 1216.9618 | 1480 | 1561.5391 | 199 | 7.5976e-05 | 39.0486 | 1.501 | 403.6512 | 2239.1952 | 6.5793 | 4.3306 | 358.0962 | 1.3749 | 0.0024268 | 0.00012257 | 0.54392 | 0.77933 | {DCD0DC19-914F-4CFB-A070-C04552F2A497} | 182541103 | ATASCADERO 1103 | A16 | 35.392 | -120.5978 | ATASCADERO 1103A16 | 138 | 76 | 38898.0633 | 31675.1523 | 7222.911 | 28337.886 | 7118.4482 | 0.02439 | 0.015119 | 1.5118 | 7.4372 | 1740 | 0.48294 | 1287 | 0 | 0 | 17.6083 | 244 | 0
North Valley | 5536 | 495 | 506.4285 | 1903 | 1075.8209 | 135 | 6.0066e-05 | 40.3873 | 41.1834 | 503.2807 | 6639.8055 | 445.5465 | 0.73602 | 15.0893 | 1.02 | 0.0024096 | 0.0011365 | 0.26012 | 0.47074 | {AB82846E-3FC2-48BC-9399-AD766892B309} | 102541102 | VOLTA 1102 | 9742 | 40.518 | -121.7552 | VOLTA 11029742 | 185 | 229 | 23878.6309 | 14622.5954 | 9256.0355 | 14622.5954 | 9256.0355 | 0.15342 | 0.0081089 | 1.0231 | 14.0963 | 349 | 0.3253 | 1288 | 0 | 0 | 9.0861 | 2590 | 0
Central Valley | 7441 | 0 | 0 | 4 | 1.5806 | 2 | 1.1789e-05 | 158.7562 | 12.0269 | 1177.2453 | 4238.1564 | 56.7996 | 5.1781 | 1245.2499 | 1.4646 | 0.0024066 | 0.00012432 | 0 | 0 | {7B4CCB47-4C77-4503-81B9-A825A72EAF0C} | 252921110 | STONE CORRAL 1110 | 7784F | 36.479 | -119.1188 | STONE CORRAL 11107784F | 50 | 85 | 11801.3721 | 7654.6568 | 4146.7153 | 586.0706 | 30.0986 | 0.00024863 | 2.3578e-05 |  | 2 | 1729 | 0.0048132 | 1289 | 0 | 0 | 0.36417 | 2003 | 0
Central Valley | 4823 | 49 | 50.6442 | 175 | 101.8678 | 47 | 0.00012999 | 19.7965 | 8.0496 | 40.5363 | 348.5107 | 8.6061 | 0.73467 | 6.8494 | 1.1896 | 0.0024029 | 0.00064545 | 0.28 | 0.49716 | {B0AD76E8-C8B6-4D91-BE40-831E99BE5659} | 163201101 | WEST POINT 1101 | 36674 | 38.4875 | -120.5197 | WEST POINT 110136674 | 195 | 291 | 33176.4199 | 15191.9661 | 17984.4538 | 15191.9661 | 17984.4538 | 0.030336 | 0.0061095 | 1.0336 | 3.7234 | 619 | 0.11294 | 1290 | 0 | 0 | 9.4398 | 815 | 0
Central Coast | 1813 | 244 | 574.5209 | 579 | 771.9567 | 133 | 1.7111e-05 | 190.0604 | 9.8617 | 150.186 | 530.9915 | 30.9392 | 7.7888 | 199.0391 | 1.166 | 0.002399 | 0.00011269 | 0.42142 | 0.74424 | {4C792319-919C-4A4D-9290-FB2E69D483E5} | 82831109 | MILPITAS 1109 | XR082 | 37.4483 | -121.8462 | MILPITAS 1109XR082 | 246 | 190 | 53044.2184 | 32625.1795 | 20419.0389 | 30817.3767 | 17168.5701 | 0.014987 | 0.0022758 | 2.3546 | 4.3534 | 1785 | 0.31906 | 1291 | 0 | 0 | 19.149 | 1919 | 0
Central Valley | 6735 | 1 | 1.3586 | 16 | 7.4611 | 3 | 7.6219e-05 | 31.7819 | 8.984 | 122.5329 | 1405.698 | 15.9551 | 0.068584 | 7.8552 | 0.67625 | 0.002395 | 0.00068547 | 0.0625 | 0.18209 | {FC8E042C-D542-4C57-BDAA-B0EC45E15E40} | 162821702 | STANISLAUS 1702 | L3151 | 38.2565 | -120.3521 | STANISLAUS 1702L3151 | 21 | 40 | 3570.5113 | 1598.9081 | 1971.6032 | 1598.9081 | 1971.6032 | 0.0020564 | 0.00022866 | 1.3586 | 5.3333 | 579 | 0.0071849 | 1292 | 0 | 0 | 0.99352 | 1994 | 0
North Coast | 2824 | 1 | 2.9829 | 1 | 2.9829 | 1 | 9.9991e-05 | 23.8638 |  |  |  |  | 0.0044248 | 10.3325 | 1.0044 | 0.0023862 | 9.9991e-05 | 1 | 1 | {765C457F-F3C6-4599-8CF0-4576582D7DD5} | 42851121 | FORT ROSS 1121 | 4947 | 38.5577 | -123.0969 | FORT ROSS 11214947 | 63 | 62 | 32593.415 | 16678.3963 | 15915.0186 | 16678.3963 | 15915.0186 | 9.9991e-05 | 9.9991e-05 | 2.9829 | 1 | 1850 | 0.0023862 | 1293 | 0 | 0 | 10.3635 | 448 | 0
Bay Area | 3792 | 166 | 243.5716 | 558 | 461.1629 | 44 | 5.1107e-05 | 45.4959 | 4.191 | 29.5467 | 133.4481 | 0.76325 | 1.3839 | 18.8242 | 0.98497 | 0.0023509 | 7.0935e-05 | 0.29749 | 0.52817 | {A6A5315D-8A62-41D0-A9DC-ABFF612B9C6E} | 43291105 | PUEBLO 1105 | 716 | 38.3232 | -122.2534 | PUEBLO 1105716 | 405 | 619 | 71624.3254 | 31715.3368 | 39908.9886 | 4005.9439 | 4066.8832 | 0.0031211 | 0.0022487 | 1.4673 | 12.6818 | 2049 | 0.10344 | 1294 | 0 | 0 | 2.4892 | 2784 | 0
North Valley | 4407 | 79 | 109.2241 | 125 | 128.8896 | 20 | 1.627e-05 | 146.7644 | 79.5255 | 3057.8458 | 53512.8103 | 4828.09 | 3.2473 | 118.1274 | 1.3624 | 0.0023507 | 0.0010776 | 0.632 | 0.84742 | {D5CA112C-3EC7-4528-9692-3AB30AFB57CC} | 103132101 | CRESCENT MILLS 2101 | 3113 | 40.092 | -120.9139 | CRESCENT MILLS 21013113 | 11 | 12 | 3154.2144 | 1919.7007 | 1234.5137 | 1853.1278 | 1234.5137 | 0.021553 | 0.00032541 | 1.3826 | 6.25 | 372 | 0.047014 | 1295 | 0 | 0 | 1.1515 | 2366 | 0
Bay Area | 6687 | 19 | 32.0108 | 56 | 52.7594 | 8 | 4.8617e-05 | 92.5669 | 0.0085751 | 0.11803 | 0.44426 | 7.3702e-06 | 8.8042 | 89.428 | 1.1197 | 0.002348 | 4.1131e-05 | 0.33929 | 0.60673 | {425E28B1-6940-4649-A8D4-A58D56D174C1} | 43291104 | PUEBLO 1104 | 640 | 38.3496 | -122.268 | PUEBLO 1104640 | 111 | 109 | 10933.3546 | 4473.5204 | 6459.8342 | 1072.0071 | 531.9602 | 0.00032905 | 0.00038894 | 1.6848 | 7 | 2325 | 0.018784 | 1296 | 0 | 0 | 0.66611 | 2163 | 0
North Coast | 9009 | 171 | 309.7101 | 195 | 320.6477 | 25 | 8.046e-05 | 28.5878 | 7.8688 | 55.6376 | 346.1954 | 3.3919 | 0.49558 | 9.3743 | 1.0218 | 0.002341 | 0.00044946 | 0.87692 | 0.96589 | {8A730939-42F5-47D3-8D16-1FB3EEA2BAEF} | 42841112 | GUALALA 1112 | circuit_breaker | 38.7861 | -123.5221 | GUALALA 1112circuit_breaker | 45 | 44 | 5487.8185 | 3460.0472 | 2027.7713 | 2540.8884 | 785.2921 | 0.011237 | 0.0020115 | 1.8112 | 7.8 | 865 | 0.058525 | 1297 | 0 | 0 | 1.5788 | 609 | 0
Central Valley | 7068 | 27 | 35.5618 | 122 | 71.9139 | 24 | 8.2483e-05 | 28.8432 | 29.1988 | 33.3898 | 140.7084 | 6.8758 | 3.9968 | 72.2927 | 1.1612 | 0.0023307 | 0.0013325 | 0.22131 | 0.49451 | {9F8CA5FE-A9BA-4EDC-994E-2CFB4235B5A0} | 163011102 | MARTELL 1102 | 99214 | 38.3629 | -120.7749 | MARTELL 110299214 | 53 | 16 | 4493.687 | 3260.5607 | 1233.1264 | 2497.7197 | 131.5957 | 0.031981 | 0.0019796 | 1.3171 | 5.0833 | 287 | 0.055938 | 1298 | 0 | 0 | 1.552 | 1291 | 0
Sierra | 6862 | 176 | 281.03 | 839 | 511.5634 | 99 | 7.8606e-05 | 33.3686 | 10.8848 | 116.5035 | 529.8664 | 11.5435 | 1.9139 | 53.5614 | 1.1219 | 0.0023138 | 0.00041929 | 0.20977 | 0.54936 | {9366522C-3019-4FFC-ADFF-E56D90FBBE46} | 152261104 | DIAMOND SPRINGS 1104 | 2093 | 38.6813 | -120.836 | DIAMOND SPRINGS 11042093 | 122 | 134 | 21671.4272 | 14031.1709 | 7640.2563 | 12960.3084 | 6033.0526 | 0.04151 | 0.007782 | 1.5968 | 8.4747 | 911 | 0.22907 | 1299 | 0 | 0 | 8.0532 | 890 | 0
Central Coast | 6493 | 46 | 73.7122 | 116 | 120.8482 | 34 | 2.9118e-05 | 93.7731 | 1.2487 | 339.6919 | 1503.1974 | 4.7332 | 4.1976 | 741.3812 | 1.6564 | 0.0023071 | 2.4797e-05 | 0.39655 | 0.60996 | {F73EB641-FFE0-4811-B0D3-9263F0EA89B1} | 183031101 | PALMER 1101 | M84 | 34.8206 | -120.2892 | PALMER 1101M84 | 188 | 61 | 42374.9741 | 39207.0427 | 3167.9314 | 34798.532 | 2468.9787 | 0.0008431 | 0.00099001 | 1.6024 | 3.4118 | 2536 | 0.078441 | 1300 | 0 | 0 | 21.6228 | 1857 | 0
Central Valley | 8661 | 176 | 263.6808 | 493 | 414.6028 | 72 | 5.921e-05 | 67.8106 | 105.5637 | 1412.1104 | 21630.3907 | 4479.015 | 1.5559 | 108.6493 | 1.304 | 0.002305 | 0.003333 | 0.357 | 0.63598 | {918E0B8F-0C42-4226-8DC0-E78B4BED7E6D} | 162821701 | STANISLAUS 1701 | circuit_breaker | 38.1394 | -120.3704 | STANISLAUS 1701circuit_breaker | 80 | 57 | 14863.8642 | 10963.5629 | 3900.3013 | 10963.5629 | 3900.3013 | 0.23998 | 0.0042631 | 1.4982 | 6.8472 | 84 | 0.16596 | 1301 | 0 | 0 | 6.8124 | 2793 | 0
Central Valley | 924 | 2239 | 2970.0655 | 5885 | 4756.4663 | 641 | 0.00010071 | 23.8005 | 52.174 | 978.3825 | 14011.3427 | 1496.6792 | 1.9155 | 35.3776 | 1.123 | 0.0023037 | 0.0023614 | 0.38046 | 0.62443 | {2DE74D61-95A1-4D32-9CCA-28AB5E692CE7} | 163201102 | WEST POINT 1102 | 93116 | 38.3838 | -120.527 | WEST POINT 110293116 | 621 | 607 | 100726.0382 | 68737.6903 | 31988.3478 | 68737.6903 | 31988.3478 | 1.5137 | 0.064553 | 1.3265 | 9.181 | 141 | 1.4767 | 1302 | 0 | 0 | 42.7116 | 1483 | 0
Sierra | 924 | 1 | 1.945 | 8 | 4.7206 | 1 | 6.0928e-05 | 0.066432 |  |  |  |  | 3.8717 | 44.4095 | 1.2566 | 4.0476e-06 | 6.0928e-05 | 0.125 | 0.41202 | {2DE74D61-95A1-4D32-9CCA-28AB5E692CE7} | 163201102 | WEST POINT 1102 | 93116 | 38.3838 | -120.527 | WEST POINT 110293116 | 621 | 607 | 100726.0382 | 68737.6903 | 31988.3478 | 68737.6903 | 31988.3478 | 6.0928e-05 | 6.0928e-05 | 1.945 | 8 | 2127 | 4.0476e-06 | 1302 | 0 | 0 | 42.7116 | 2113 | 0
Bay Area | 280 | 313 | 732.5962 | 974 | 1106.9644 | 110 | 4.7765e-05 | 42.4637 | 0.53446 | 0.35071 | 0.81723 | 0.021625 | 1.6994 | 9.688 | 1.0145 | 0.002298 | 4.1394e-05 | 0.32136 | 0.66181 | {E7743FFE-2947-47FD-B4E6-A754209900CE} | 42011104 | SAN RAFAEL 1104 | 802 | 37.9885 | -122.5779 | SAN RAFAEL 1104802 | 338 | 1642 | 101359.0292 | 20343.1915 | 81015.8377 | 12060.44 | 38609.2134 | 0.0045534 | 0.0052541 | 2.3406 | 8.8545 | 2318 | 0.25278 | 1303 | 0 | 0 | 7.494 | 2066 | 0
North Valley | 6295 | 24 | 27.2491 | 127 | 77.3993 | 17 | 3.0285e-05 | 59.3458 | 1.893 | 103.0862 | 549.0157 | 2.1333 | 3.6961 | 89.9758 | 1.0984 | 0.0022967 | 4.8188e-05 | 0.18898 | 0.35206 | {62976FAC-DE1E-4247-A5CB-A153442821DF} | 103491101 | MC ARTHUR 1101 | 1488 | 41.0513 | -121.4105 | MC ARTHUR 11011488 | 267 | 230 | 67457.7554 | 53844.4679 | 13613.2875 | 2966.0846 | 476.3576 | 0.0008192 | 0.00051485 | 1.1354 | 7.4706 | 2247 | 0.039044 | 1304 | 0 | 0 | 1.843 | 1628 | 0
Central Valley | 1265 | 57 | 88.055 | 327 | 196.1669 | 50 | 6.8067e-05 | 33.975 | 16.9108 | 676.323 | 2934.5492 | 104.1332 | 5.5974 | 105.0692 | 1.1938 | 0.0022776 | 0.00060479 | 0.17431 | 0.44888 | {9BE6D037-BD8E-46AF-A32B-7F2BB00D9E6A} | 163451702 | FROGTOWN 1702 | 32556 | 38.0683 | -120.5387 | FROGTOWN 170232556 | 119 | 242 | 19482.1061 | 10065.4499 | 9416.6562 | 7932.1339 | 5143.0187 | 0.030239 | 0.0034033 | 1.5448 | 6.54 | 664 | 0.11388 | 1305 | 0 | 0 | 4.9288 | 1374 | 0
North Coast | 7680 | 159 | 271.8189 | 269 | 333.4906 | 32 | 0.00014071 | 14.1961 | 4.0011 | 68.7384 | 417.5929 | 2.948 | 0.60958 | 18.8707 | 1.1097 | 0.0022758 | 0.00034103 | 0.59108 | 0.81507 | {C0868086-2AE3-4A05-90EB-BF1D6E5F34F7} | 42811111 | MONTE RIO 1111 | 37520 | 38.5088 | -123.0693 | MONTE RIO 111137520 | 28 | 56 | 7254.2682 | 3470.728 | 3783.5401 | 3470.728 | 3783.5401 | 0.010913 | 0.0045026 | 1.7096 | 8.4062 | 1027 | 0.072826 | 1306 | 0 | 0 | 2.1566 | 1346 | 0
Central Coast | 281 | 275 | 474.5734 | 1045 | 938.2189 | 140 | 3.5465e-05 | 62.3106 | 2.0924 | 558.8938 | 3532.0307 | 49.5673 | 1.5324 | 247.6908 | 1.1659 | 0.0022756 | 6.6664e-05 | 0.26316 | 0.50582 | {99D427D2-40DF-4D58-B940-8F78EEDA8ECD} | 183071101 | PERRY 1101 | V78 | 35.5731 | -121.0412 | PERRY 1101V78 | 197 | 133 | 54955.0865 | 47298.9569 | 7656.1296 | 47298.9569 | 7656.1296 | 0.0093329 | 0.0049651 | 1.7257 | 7.4643 | 2081 | 0.31858 | 1307 | 0 | 0 | 29.3902 | 2093 | 0
North Valley | 9593 | 26 | 46.3156 | 89 | 71.7561 | 8 | 0.00012961 | 20.9668 | 11.6905 | 301.1947 | 2570.7781 | 56.9875 | 3.93 | 57.1615 | 1.135 | 0.0022605 | 0.0012134 | 0.29213 | 0.64546 | {E1E224E8-4D68-45CA-957D-E9490EC41D38} | 103081105 | BUTTE 1105 | 244246 | 39.7868 | -121.6591 | BUTTE 1105244246 | 14 | 11 | 1416.8737 | 885.0826 | 531.7911 | 885.0826 | 531.7911 | 0.0097074 | 0.0010369 | 1.7814 | 11.125 | 320 | 0.018084 | 1308 | 0 | 0 | 0.54996 | 552 | 0
North Coast | 6031 | 173 | 323.1219 | 237 | 358.9515 | 15 | 0.00011364 | 20.6733 | 18.6736 | 71.4208 | 809.2033 | 18.8645 | 0.5531 | 12.8237 | 1.2066 | 0.0022542 | 0.0013812 | 0.72996 | 0.90018 | {6914B0C9-AD95-4BD6-8886-EFD48C40F335} | 42811113 | MONTE RIO 1113 | 1989 | 38.5219 | -122.9971 | MONTE RIO 11131989 | 11 | 59 | 4854.8074 | 1164.5069 | 3690.3005 | 1164.5069 | 3690.3005 | 0.020718 | 0.0017046 | 1.8678 | 15.8 | 278 | 0.033813 | 1309 | 0 | 0 | 0.72359 | 2022 | 0
Bay Area | 9833 | 1 | 1.812 | 1 | 1.812 | 1 | 3.1334e-05 | 71.7887 | 7.658 | 137.551 | 650.6501 | 5.9212 | 6.115 | 133.8261 | 1.3385 | 0.0022494 | 0.00023996 | 1 | 1 | {326D13C2-6BC0-4D12-9CFE-64D0722362EA} | 24101103 | HALF MOON BAY 1103 | 8920 | 37.3237 | -122.2789 | HALF MOON BAY 11038920 | 6 | 3 | 328.6868 | 185.7819 | 142.905 | 185.7819 | 142.905 | 0.00023996 | 3.1334e-05 | 1.812 | 1 | 1278 | 0.0022494 | 1310 | 0 | 0 | 0.11544 | 1917 | 0
Bay Area | 1986 | 510 | 1057.599 | 1357 | 1550.383 | 124 | 5.2396e-05 | 37.8754 | 0.1273 | 0.14607 | 0.098551 | 0.00010194 | 1.8031 | 9.6287 | 0.96548 | 0.0022488 | 3.176e-05 | 0.37583 | 0.68215 | {2D7883CD-6608-4310-8AB5-FA60A939C766} | 43021102 | WOODACRE 1102 | 1280 | 37.9962 | -122.5956 | WOODACRE 11021280 | 213 | 927 | 63841.2572 | 13839.6437 | 50001.6135 | 13606.7096 | 49335.0056 | 0.0039383 | 0.0064971 | 2.0737 | 10.9435 | 2442 | 0.27886 | 1311 | 0 | 0 | 8.4548 | 2778 | 0
Central Coast | 2791 | 2719 | 5106.005 | 3690 | 5639.1553 | 125 | 0.00018433 | 13.1931 | 8.8197 | 29.2293 | 110.4285 | 1.1017 | 0.54956 | 5.4478 | 1.0045 | 0.0022424 | 0.00088979 | 0.73686 | 0.90546 | {9A213A9A-1023-49F7-ABDF-C909666FFA23} | 83622105 | CAMP EVERS 2105 | 10294 | 37.0992 | -122.0531 | CAMP EVERS 210510294 | 252 | 448 | 34698.2525 | 13600.6961 | 21097.5563 | 13600.6961 | 21097.5563 | 0.11122 | 0.023042 | 1.8779 | 29.52 | 452 | 0.2803 | 1312 | 0 | 0 | 8.4511 | 2456 | 0
Central Valley | 9114 | 74 | 137.0278 | 560 | 320.9442 | 47 | 8.1907e-05 | 29.7032 | 8.0998 | 183.4228 | 1414.57 | 22.6381 | 3.1206 | 53.9376 | 1.1273 | 0.0022344 | 0.00032109 | 0.13214 | 0.42695 | {1342493A-4682-4997-B671-32B9B4D877B0} | 163351704 | CURTIS 1704 | 11300 | 38.0057 | -120.3478 | CURTIS 170411300 | 65 | 78 | 11521.3963 | 5848.9555 | 5672.4408 | 5848.9555 | 5672.4408 | 0.015091 | 0.0038496 | 1.8517 | 11.9149 | 1072 | 0.10502 | 1313 | 0 | 0 | 3.6344 | 1202 | 0
Central Valley | 6836 | 0 | 0 | 1 | 0.62586 | 1 | 9.3571e-05 | 23.8467 | 13.4182 | 18.3367 | 80.8411 | 1.2071 | 2.9978 | 15.2033 | 1.0088 | 0.0022314 | 0.0012556 | 0 | 0 | {D1304657-02FA-4D1D-AEC4-81E74D24E4EB} | 162821702 | STANISLAUS 1702 | 4905 | 38.2626 | -120.3289 | STANISLAUS 17024905 | 70 | 147 | 9450.9551 | 3770.3669 | 5680.5883 | 3770.3669 | 5680.5883 | 0.0012556 | 9.3571e-05 |  | 1 | 304 | 0.0022314 | 1314 | 0 | 0 | 2.3428 | 718 | 0
North Coast | 4346 | 130 | 235.4407 | 240 | 291.3628 | 30 | 5.2991e-05 | 46.2784 | 5.6899 | 69.0257 | 181.5625 | 4.2199 | 2.5364 | 33.0928 | 1.0304 | 0.0022265 | 0.00023337 | 0.54167 | 0.80807 | {5988784C-46D2-4999-AEE8-C136D520A366} | 43321102 | RINCON 1102 | circuit_breaker | 38.4899 | -122.666 | RINCON 1102circuit_breaker | 110 | 152 | 14494.0741 | 5733.5212 | 8760.5529 | 4493.3108 | 7756.5018 | 0.007001 | 0.0015897 | 1.8111 | 8 | 1304 | 0.066795 | 1315 | 0 | 0 | 2.792 | 641 | 0
Sierra | 2722 | 494 | 615.0848 | 1320 | 983.4667 | 143 | 9.4978e-05 | 24.1742 | 78.4907 | 1324.3412 | 32185.8674 | 8782.6621 | 1.0272 | 14.7034 | 1.0269 | 0.0022096 | 0.0032127 | 0.37424 | 0.62543 | {ED9435F9-E06B-4A98-B053-EB0C1DC8369F} | 152181101 | FORESTHILL 1101 | circuit_breaker | 39.0197 | -120.8297 | FORESTHILL 1101circuit_breaker | 212 | 455 | 35790.3095 | 14707.8472 | 21082.4623 | 14707.8472 | 21082.4623 | 0.45941 | 0.013582 | 1.2451 | 9.2308 | 89 | 0.31598 | 1316 | 0 | 0 | 9.139 | 589 | 0
Sierra | 4283 | 1615 | 2227.0438 | 3576 | 3231.7322 | 329 | 0.00016378 | 14.7418 | 14.5704 | 142.2871 | 1859.2961 | 109.778 | 2.4566 | 28.1605 | 1.1896 | 0.0022008 | 0.0012164 | 0.45162 | 0.68912 | {2C5406F6-FB2B-4C0B-9360-BB5A1B2BA52D} | 153082106 | PLACERVILLE 2106 | 19552 | 38.7437 | -120.7816 | PLACERVILLE 210619552 | 437 | 597 | 73896.1375 | 34224.6242 | 39671.5133 | 34224.6242 | 39671.5133 | 0.40019 | 0.053882 | 1.379 | 10.8693 | 318 | 0.72407 | 1317 | 0 | 0 | 21.2662 | 444 | 0
North Valley | 1663 | 135 | 312.3776 | 868 | 646.4837 | 127 | 2.7458e-05 | 66.1444 | 10.4093 | 828.5173 | 20414.5824 | 358.3617 | 0.2754 | 18.3036 | 0.98169 | 0.0022005 | 0.00016174 | 0.15553 | 0.48319 | {788A24F0-B95A-4429-91A6-A78EF0DB40D4} | 102211103 | BUCKS CREEK 1103 | 338520 | 39.8921 | -121.2043 | BUCKS CREEK 1103338520 | 126 | 241 | 23519.8263 | 12890.8329 | 10628.9934 | 12303.5892 | 9682.1978 | 0.020541 | 0.0034872 | 2.3139 | 6.8346 | 1541 | 0.27946 | 1318 | 0 | 0 | 7.6451 | 749 | 0
Central Valley | 9338 | 30 | 49.4742 | 153 | 101.3112 | 24 | 9.3191e-05 | 24.823 | 11.2925 | 53.1347 | 350.2731 | 8.3402 | 6.1215 | 62.5512 | 1.339 | 0.0021596 | 0.00049993 | 0.19608 | 0.48834 | {8FCA88A2-5287-4980-B557-B7704EA7B310} | 254432102 | COARSEGOLD 2102 | 10610 | 37.3222 | -119.6174 | COARSEGOLD 210210610 | 34 | 26 | 4019.3991 | 2195.6315 | 1823.7676 | 2195.6315 | 1823.7676 | 0.011998 | 0.0022366 | 1.6491 | 6.375 | 785 | 0.05183 | 1319 | 0 | 0 | 1.3643 | 284 | 0
Central Valley | 4482 | 30 | 53.8816 | 125 | 89.4972 | 39 | 2.5343e-05 | 85.4918 | 39.9393 | 7765.2931 | 76877.1826 | 4024.1123 | 5.067 | 1318.0764 | 1.6869 | 0.0021577 | 0.00052372 | 0.24 | 0.60205 | {3339FEFA-4C2B-4E1B-B838-4C72937EBB52} | 252561101 | KERCKHOFF 1101 | R353 | 37.0927 | -119.5519 | KERCKHOFF 1101R353 | 60 | 48 | 24619.5739 | 22124.1321 | 2495.4418 | 22124.1321 | 2495.4418 | 0.020425 | 0.0009884 | 1.7961 | 3.2051 | 765 | 0.08415 | 1320 | 0 | 0 | 13.7473 | 431 | 0
North Valley | 1401 | 413 | 555.9652 | 778 | 754.0095 | 102 | 0.00016992 | 11.2571 | 26.6669 | 3405.8831 | 92488.0697 | 5712.5109 | 0.95547 | 17.018 | 1.0321 | 0.0021466 | 0.0027652 | 0.53085 | 0.73735 | {258D8B59-7667-45E3-B6CC-D85F766C4568} | 103271101 | ANTLER 1101 | 1520 | 40.8994 | -122.3862 | ANTLER 11011520 | 106 | 142 | 19077.3412 | 14269.0206 | 4808.3206 | 14269.0206 | 4808.3206 | 0.28205 | 0.017332 | 1.3462 | 7.6275 | 114 | 0.21896 | 1321 | 0 | 0 | 8.8664 | 1197 | 0
Bay Area | 1566 | 546 | 1159.9007 | 1767 | 1877.3438 | 176 | 3.9801e-05 | 51.4735 | 3.3628 | 106.4441 | 806.9395 | 11.5356 | 1.5983 | 107.7676 | 1.2769 | 0.0021421 | 9.4599e-05 | 0.309 | 0.61784 | {82B72724-3F36-4DE0-AF4C-310E9BC3E997} | 24131102 | MENLO 1102 | W80 | 37.3636 | -122.2132 | MENLO 1102W80 | 173 | 117 | 41047.3258 | 30438.0826 | 10609.2432 | 29528.8058 | 10609.2432 | 0.016649 | 0.007005 | 2.1244 | 10.0398 | 1882 | 0.37701 | 1322 | 0 | 0 | 18.3483 | 2460 | 0
Central Coast | 6503 | 100 | 328.2331 | 423 | 507.6839 | 59 | 4.0521e-05 | 56.7274 | 0.77772 | 194.5475 | 985.3905 | 1.5794 | 1.0837 | 138.1314 | 1.1331 | 0.0021363 | 3.1354e-05 | 0.23641 | 0.64653 | {A2EAD6B1-6208-4216-A913-DC206F2BE25D} | 183101104 | CABRILLO 1104 | Y24 | 34.633 | -120.4541 | CABRILLO 1104Y24 | 97 | 84 | 34860.1905 | 30947.8055 | 3912.385 | 28736.9146 | 3853.7668 | 0.0018499 | 0.0023907 | 3.2823 | 7.1695 | 2452 | 0.12604 | 1323 | 0 | 0 | 17.8563 | 1963 | 0
North Valley | 2232 | 396 | 545.5489 | 1273 | 892.8577 | 92 | 0.00011379 | 19.2624 | 10.3137 | 241.6724 | 2176.9426 | 37.0706 | 2.6101 | 64.7081 | 1.0909 | 0.0021246 | 0.0006438 | 0.31108 | 0.61101 | {E9C7EDD9-37A2-4E13-9D63-C852227DDB63} | 103081105 | BUTTE 1105 | 1243 | 39.79 | -121.6559 | BUTTE 11051243 | 67 | 60 | 12837.5218 | 8294.0568 | 4543.4649 | 8294.0568 | 4543.4649 | 0.059229 | 0.010469 | 1.3776 | 13.837 | 622 | 0.19546 | 1324 | 0 | 0 | 5.1537 | 1958 | 0
Central Coast | 5551 | 120 | 178.1587 | 311 | 304.5382 | 37 | 5.6755e-05 | 42.7064 | 3.0807 | 223.6284 | 764.7954 | 6.0698 | 5.3112 | 155.0227 | 1.0695 | 0.0021216 | 9.0948e-05 | 0.38585 | 0.58501 | {CB331419-4415-4607-87D8-B05BBD8C7F9E} | 182721102 | SANTA YNEZ 1102 | Y18 | 34.5941 | -120.1409 | SANTA YNEZ 1102Y18 | 118 | 382 | 29501.2964 | 12113.6185 | 17387.6779 | 7602.3972 | 1630.6225 | 0.0033651 | 0.0020999 | 1.4847 | 8.4054 | 1904 | 0.0785 | 1325 | 0 | 0 | 4.7239 | 2280 | 0
Bay Area | 5525 | 608 | 1622.3442 | 813 | 1711.1769 | 92 | 5.9607e-05 | 43.0313 | 3.9641 | 71.1585 | 413.0248 | 3.5429 | 1.4748 | 63.3176 | 1.2947 | 0.0021144 | 0.00013771 | 0.74785 | 0.94809 | {D114DA17-C3D8-4F00-837D-4551FAA55B77} | 24101101 | HALF MOON BAY 1101 | circuit_breaker | 37.469 | -122.4303 | HALF MOON BAY 1101circuit_breaker | 241 | 289 | 36403.8885 | 22337.572 | 14066.3165 | 12179.0697 | 4310.1534 | 0.012669 | 0.0054839 | 2.6683 | 8.837 | 1647 | 0.19452 | 1326 | 0 | 0 | 7.5677 | 2679 | 0
Central Valley | 3123 | 282 | 372.8904 | 925 | 672.0018 | 73 | 0.00011586 | 18.6323 | 117.8529 | 1192.0935 | 18659.9671 | 3808.7548 | 1.175 | 13.4295 | 1.0072 | 0.0021107 | 0.0063876 | 0.30486 | 0.55489 | {0922D0E7-0574-453E-909E-0FA0DA849831} | 163751101 | PINE GROVE 1101 | 1021 | 38.414 | -120.6755 | PINE GROVE 11011021 | 75 | 114 | 13222.1917 | 6749.2717 | 6472.9199 | 6749.2717 | 6472.9199 | 0.4663 | 0.0084576 | 1.3223 | 12.6712 | 26 | 0.15408 | 1327 | 0 | 0 | 4.1938 | 2540 | 0
Sierra | 715 | 218 | 394.7397 | 949 | 718.4205 | 149 | 7.6807e-05 | 25.307 | 4.9159 | 142.6758 | 1466.6455 | 18.9103 | 4.8972 | 69.8074 | 1.2193 | 0.0021106 | 0.00021788 | 0.22972 | 0.54945 | {3C06DAA7-6742-4F51-AEED-CE425B9A549D} | 153662102 | APPLE HILL 2102 | 12025 | 38.6276 | -120.7439 | APPLE HILL 210212025 | 129 | 127 | 26110.0194 | 14681.1435 | 11428.8759 | 14681.1435 | 11428.8759 | 0.032463 | 0.011444 | 1.8107 | 6.3691 | 1350 | 0.31448 | 1328 | 0 | 0 | 9.1224 | 1399 | 0
Sierra | 4719 | 1241 | 1599.8632 | 1931 | 1902.4783 | 196 | 5.5564e-05 | 39.7366 | 120.4902 | 1148.37 | 20546.887 | 3722.0916 | 0.6361 | 18.2384 | 1.0169 | 0.0021085 | 0.0035446 | 0.64267 | 0.84094 | {12398A09-47B6-4618-B7A8-07F9B9DF4D2E} | 152481105 | BRUNSWICK 1105 | 2130 | 39.2741 | -120.9695 | BRUNSWICK 11052130 | 239 | 185 | 44481.1936 | 23157.9038 | 21323.2898 | 23157.9038 | 21323.2898 | 0.69475 | 0.010891 | 1.2892 | 9.852 | 78 | 0.41327 | 1329 | 0 | 0 | 14.3896 | 445 | 0
Sierra | 4145 | 935 | 1202.2909 | 2091 | 1745.1948 | 175 | 0.00011323 | 17.324 | 70.6758 | 1251.5785 | 18204.3911 | 2364.0039 | 1.7033 | 24.5601 | 1.0332 | 0.0020921 | 0.0037317 | 0.44715 | 0.68892 | {423A8C76-9A51-45A6-B374-FEBC31B925B4} | 152261106 | DIAMOND SPRINGS 1106 | 76088 | 38.6738 | -120.7597 | DIAMOND SPRINGS 110676088 | 182 | 176 | 28855.1915 | 17715.9929 | 11139.1986 | 17715.9929 | 11139.1986 | 0.65305 | 0.019816 | 1.2859 | 11.9486 | 67 | 0.36612 | 1330 | 0 | 0 | 11.0082 | 21 | 0
Central Coast | 5561 | 11 | 22.4628 | 14 | 24.5021 | 3 | 8.7622e-05 | 23.8467 | 1.7472 | 552.2557 | 7279.3745 | 25.4649 | 1.8296 | 26.1407 | 1.0288 | 0.0020895 | 0.00013785 | 0.78571 | 0.91677 | {4260F392-8CF2-458A-B972-28FCF38AA586} | 82841102 | BIG BASIN 1102 | 10254 | 37.1391 | -122.1786 | BIG BASIN 110210254 | 18 | 3 | 3468.7391 | 3441.3015 | 27.4376 | 3441.3015 | 27.4376 | 0.00041356 | 0.00026286 | 2.0421 | 4.6667 | 1645 | 0.0062684 | 1331 | 0 | 0 | 2.1383 | 2152 | 0
Central Coast | 5138 | 273 | 548.2251 | 943 | 921.4679 | 72 | 0.00012106 | 14.5906 | 4.4725 | 37.2819 | 249.7534 | 2.8468 | 1.1767 | 10.2536 | 1.008 | 0.0020729 | 0.00033813 | 0.2895 | 0.59495 | {8F9FCAA5-1D1B-42BE-8E3D-F2DBA5211C02} | 83252106 | PAUL SWEET 2106 | 10424 | 37.0123 | -121.953 | PAUL SWEET 210610424 | 168 | 187 | 25057.9022 | 11634.0857 | 13423.8165 | 9066.2649 | 10287.2786 | 0.024345 | 0.0087165 | 2.0082 | 13.0972 | 1036 | 0.14925 | 1332 | 0 | 0 | 5.6335 | 676 | 0
Sierra | 4726 | 1545 | 1955.4957 | 3772 | 3079.9797 | 368 | 0.00011212 | 19.4548 | 81.9501 | 1118.1368 | 15399.9348 | 2380.8042 | 1.622 | 39.7293 | 1.0864 | 0.0020424 | 0.003891 | 0.4096 | 0.63491 | {C89C3F78-8047-4151-A21B-FC3CD22D755E} | 153082106 | PLACERVILLE 2106 | 9712 | 38.8326 | -120.8178 | PLACERVILLE 21069712 | 321 | 248 | 60163.921 | 39873.7428 | 20290.1782 | 39873.7428 | 20290.1782 | 1.4319 | 0.04126 | 1.2657 | 10.25 | 63 | 0.7516 | 1333 | 0 | 0 | 24.7764 | 1383 | 0
Bay Area | 8884 | 373 | 1281.5567 | 395 | 1290.3555 | 27 | 9.3737e-05 | 20.5477 | 7.3236 | 69.0989 | 304.7383 | 6.3089 | 0.45854 | 47.5705 | 1.0679 | 0.0020422 | 0.00040873 | 0.9443 | 0.99318 | {1B478AA0-B298-4B7B-A396-0BA13AEAC7E0} | 22811103 | PACIFICA 1103 | 3907 | 37.5844 | -122.4997 | PACIFICA 11033907 | 32 | 18 | 8180.7857 | 7747.6312 | 433.1545 | 5462.3478 | 149.0846 | 0.011036 | 0.0025309 | 3.4358 | 14.6296 | 931 | 0.05514 | 1334 | 0 | 0 | 3.3941 | 1999 | 0
Bay Area | 1425 | 34 | 70.4016 | 76 | 93.7632 | 17 | 2.381e-05 | 77.0247 | 0.15531 | 0.17792 | 0.0022378 | 4.2524e-07 | 13.2592 | 50.9422 | 1.1162 | 0.0020411 | 1.9122e-05 | 0.44737 | 0.75084 | {BA4CC229-6FEC-4C97-A427-8049E1A3A120} | 42991105 | LAS GALLINAS A 1105 | 904 | 38.0257 | -122.5737 | LAS GALLINAS A 1105904 | 143 | 1243 | 70862.9397 | 11479.983 | 59382.9567 | 1736.6554 | 6212.5481 | 0.00032508 | 0.00040478 | 2.0706 | 4.4706 | 2630 | 0.034699 | 1335 | 0 | 0 | 1.0791 | 2740 | 0
Central Valley | 9105 | 6 | 8.874 | 97 | 47.4547 | 34 | 4.1718e-05 | 86.095 | 0.025935 | 238.6962 | 2034.6801 | 0.084259 | 2.463 | 368.8076 | 1.6369 | 0.0020375 | 2.5228e-05 | 0.061856 | 0.187 | {BE20DD4B-6661-46C1-A7C9-992DA1F66AB7} | 252501101 | BALCH NO 1 1101 | circuit_breaker | 36.9082 | -119.0866 | BALCH NO 1 1101circuit_breaker | 42 | 41 | 14908.6363 | 13497.4542 | 1411.1821 | 13497.4542 | 1411.1821 | 0.00085774 | 0.0014184 | 1.479 | 2.8529 | 2535 | 0.069275 | 1336 | 0 | 0 | 8.3869 | 1275 | 0
Bay Area | 7796 | 106 | 231.5332 | 119 | 238.0333 | 9 | 9.8253e-05 | 21.2044 | 1.6081 | 3.8137 | 14.2777 | 0.053415 | 1.6114 | 3.2808 | 1.0143 | 0.0020359 | 0.00013475 | 0.89076 | 0.97269 | {B7EA2BCC-1301-4AEA-B933-67DD1492700E} | 24251101 | WOODSIDE 1101 | 8601 | 37.4388 | -122.3234 | WOODSIDE 11018601 | 18 | 25 | 1620.6745 | 961.631 | 659.0435 | 961.631 | 659.0435 | 0.0012127 | 0.00088428 | 2.1843 | 13.2222 | 1668 | 0.018323 | 1337 | 0 | 0 | 0.59753 | 2726 | 0
Central Valley | 4455 | 289 | 390.8415 | 837 | 671.3035 | 110 | 9.1313e-05 | 20.1597 | 9.2354 | 387.8317 | 4309.1576 | 96.4166 | 0.40394 | 19.1582 | 1.039 | 0.0020305 | 0.0004839 | 0.34528 | 0.58221 | {889F53E6-7F0E-4AD7-A387-533DAB6CF47B} | 163201102 | WEST POINT 1102 | 1341 | 38.3173 | -120.5209 | WEST POINT 11021341 | 109 | 99 | 19478.1073 | 16262.9038 | 3215.2035 | 16262.9038 | 3215.2035 | 0.053229 | 0.010044 | 1.3524 | 7.6091 | 806 | 0.22336 | 1338 | 0 | 0 | 10.1053 | 2353 | 0
Sierra | 5042 | 141 | 173.0995 | 372 | 288.4995 | 97 | 6.3194e-05 | 37.1519 | 39.7057 | 824.1977 | 19908.3886 | 5180.1182 | 0.22213 | 53.7625 | 1.1211 | 0.0020274 | 0.0014473 | 0.37903 | 0.6 | {9722F7CD-905A-4FAD-885D-DF51D2B7EB29} | 152762101 | EL DORADO PH 2101 | 63464 | 38.7607 | -120.5049 | EL DORADO PH 210163464 | 89 | 112 | 27141.3787 | 21978.0825 | 5163.2962 | 21978.0825 | 5163.2962 | 0.14039 | 0.0061298 | 1.2277 | 3.8351 | 262 | 0.19665 | 1339 | 0 | 0 | 13.6565 | 1388 | 0
North Coast | 4765 | 22 | 32.7975 | 52 | 47.9167 | 13 | 7.792e-05 | 34.8524 | 0.39899 | 21.215 | 196.762 | 0.29117 | 1.6401 | 46.0141 | 1.1234 | 0.0020268 | 6.5354e-05 | 0.42308 | 0.68447 | {106A3CC8-ABBB-4312-91E3-1D68E8BAE7A2} | 42891101 | GEYSERVILLE 1101 | 480 | 38.7001 | -122.9516 | GEYSERVILLE 1101480 | 241 | 216 | 65304.0341 | 25712.4856 | 39591.5485 | 1516.0203 | 2449.8043 | 0.0008496 | 0.001013 | 1.4908 | 4 | 2087 | 0.026348 | 1340 | 0 | 0 | 0.94201 | 1941 | 0
Bay Area | 23 | 21 | 29.7608 | 29 | 34.0066 | 9 | 2.1259e-05 | 63.5742 | 18.0653 | 78.0397 | 396.9436 | 7.1728 | 8.0268 | 65.0415 | 1.1042 | 0.0020215 | 5.5601e-05 | 0.72414 | 0.87515 | {C740351C-623B-4A79-8F81-B59FA4E58E72} | 14662103 | TASSAJARA 2103 | circuit_breaker | 37.7998 | -121.9083 | TASSAJARA 2103circuit_breaker | 660 | 1216 | 84106.1872 | 28888.6491 | 55217.5381 | 651.7218 | 971.8755 | 0.00050041 | 0.00019133 | 1.4172 | 3.2222 | 2184 | 0.018193 | 1341 | 0 | 0 | 0.40496 | 2105 | 0
North Coast | 312 | 90 | 142.2041 | 259 | 222.6493 | 39 | 0.0001205 | 14.098 | 1.8667 | 13.3621 | 104.4433 | 0.47388 | 0.79811 | 5.7302 | 1.005 | 0.0020208 | 0.00015262 | 0.34749 | 0.63869 | {5AA0A9EA-0FB6-4230-B4CC-9462B9350D46} | 43071103 | DUNBAR 1103 | 440 | 38.3424 | -122.4968 | DUNBAR 1103440 | 330 | 1047 | 72072.2813 | 22799.1788 | 49273.1024 | 4464.9005 | 7184.3592 | 0.0059522 | 0.0046996 | 1.58 | 6.641 | 1577 | 0.078811 | 1342 | 0 | 0 | 2.7744 | 1674 | 0
North Valley | 7576 | 111 | 205.085 | 392 | 316.6393 | 57 | 0.00010222 | 17.7493 | 5.6997 | 47.6453 | 386.7621 | 22.7246 | 4.4436 | 41.7536 | 1.0245 | 0.0020204 | 0.00034106 | 0.28316 | 0.64769 | {05FAE411-CB1F-4ADD-9163-2A2B0A61C7F7} | 103561101 | STILLWATER 1101 | circuit_breaker | 40.6779 | -122.3498 | STILLWATER 1101circuit_breaker | 68 | 54 | 9825.3206 | 6895.2449 | 2930.0756 | 6237.7847 | 2930.0756 | 0.019441 | 0.0058263 | 1.8476 | 6.8772 | 1026 | 0.11516 | 1343 | 0 | 0 | 3.876 | 850 | 0
Sierra | 1557 | 1466 | 2166.6158 | 4871 | 4008.6104 | 557 | 0.0001347 | 15.3734 | 39.7411 | 1217.0615 | 17356.224 | 1656.6122 | 3.2841 | 61.4072 | 1.1946 | 0.0020177 | 0.0025464 | 0.30096 | 0.54049 | {472D2B95-5CE0-4AF5-93B6-7762ECA68067} | 152471101 | COLUMBIA HILL 1101 | circuit_breaker | 39.3318 | -121.1013 | COLUMBIA HILL 1101circuit_breaker | 505 | 480 | 99012.0847 | 63408.1463 | 35603.9384 | 63408.1463 | 35603.9384 | 1.4183 | 0.075029 | 1.4779 | 8.7451 | 125 | 1.1239 | 1344 | 0 | 0 | 39.4 | 797 | 0
North Coast | 5424 | 120 | 189.723 | 125 | 192.6822 | 25 | 7.5193e-05 | 23.6257 | 0.67328 | 86.2036 | 302.4581 | 0.33327 | 1.681 | 100.7092 | 1.1699 | 0.0020063 | 6.7742e-05 | 0.96 | 0.98464 | {56EC8BE0-B402-4A7D-9076-C44EBD9A9DDD} | 42851121 | FORT ROSS 1121 | 37326 | 38.5346 | -123.2751 | FORT ROSS 112137326 | 48 | 59 | 10300.4294 | 8318.589 | 1981.8404 | 8318.589 | 1919.6703 | 0.0016935 | 0.0018798 | 1.581 | 5 | 2072 | 0.050157 | 1345 | 0 | 0 | 5.1689 | 74 | 0
North Coast | 7639 | 1111 | 1701.4265 | 1747 | 2056.1948 | 119 | 0.00017818 | 10.921 | 6.0686 | 153.6848 | 1617.6598 | 32.4403 | 0.65431 | 32.9142 | 1.0508 | 0.0020022 | 0.00063116 | 0.63595 | 0.82746 | {A3E8D9EB-1B5A-4CFD-AE2F-C1E7C6E04114} | 42811112 | MONTE RIO 1112 | 120 | 38.4637 | -123.0083 | MONTE RIO 1112120 | 109 | 132 | 16707.1302 | 11062.7422 | 5644.3879 | 11062.7422 | 5644.3879 | 0.075108 | 0.021203 | 1.5314 | 14.6807 | 638 | 0.23827 | 1346 | 0 | 0 | 6.8741 | 1191 | 0
Sierra | 4687 | 959 | 1472.7463 | 2313 | 2154.0635 | 296 | 8.3762e-05 | 39.2137 | 18.8386 | 406.9604 | 4750.8325 | 300.407 | 4.84 | 56.2679 | 1.1415 | 0.0020014 | 0.00086676 | 0.41461 | 0.68371 | {C9DADD85-14AA-43BF-A515-5A40BF95056F} | 152031103 | GRASS VALLEY 1103 | 1700 | 39.2032 | -121.0791 | GRASS VALLEY 11031700 | 397 | 467 | 63950.989 | 34998.208 | 28952.7811 | 34777.5165 | 28952.7811 | 0.25656 | 0.024794 | 1.5357 | 7.8142 | 463 | 0.59243 | 1347 | 0 | 0 | 21.6097 | 481 | 0
Central Valley | 374 | 13 | 17.6616 | 100 | 61.5094 | 17 | 7.8135e-05 | 28.0354 | 12.0976 | 33.32 | 198.3959 | 6.2496 | 0.48767 | 14.0868 | 1.4784 | 0.0019955 | 0.00057993 | 0.13 | 0.28714 | {4D82DC58-585D-41B0-ABBC-3515C39508AD} | 162821702 | STANISLAUS 1702 | 1804 | 38.2589 | -120.3477 | STANISLAUS 17021804 | 248 | 562 | 34605.3878 | 13424.5046 | 21180.8832 | 13424.5046 | 21180.8832 | 0.0098588 | 0.0013283 | 1.3586 | 5.8824 | 697 | 0.033923 | 1348 | 0 | 0 | 8.3416 | 1356 | 0
Central Valley | 5939 | 323 | 621.7082 | 1123 | 957.5431 | 199 | 3.6191e-05 | 82.6697 | 4.4334 | 384.3139 | 3240.2195 | 33.019 | 2.8118 | 164.9577 | 1.3574 | 0.0019866 | 7.9224e-05 | 0.28762 | 0.64927 | {CA1036D4-6988-4718-9A58-7F114C1260AF} | 163781701 | PEORIA 1701 | 90090 | 37.9026 | -120.4551 | PEORIA 170190090 | 209 | 205 | 60119.0478 | 48288.5394 | 11830.5085 | 46519.9218 | 11830.5085 | 0.015766 | 0.007202 | 1.9248 | 5.6432 | 1988 | 0.39534 | 1349 | 0 | 0 | 28.9061 | 2404 | 0
North Coast | 5003 | 59 | 105.4154 | 180 | 136.1511 | 33 | 7.2574e-05 | 39.1237 | 8.7009 | 7.4848 | 21.0423 | 1.6981 | 4.2229 | 29.7331 | 1.0837 | 0.0019761 | 0.00023046 | 0.32778 | 0.77425 | {60D33697-692D-4938-96CD-E53257AEC032} | 43211102 | HARTLEY 1102 | circuit_breaker | 39.0769 | -122.9331 | HARTLEY 1102circuit_breaker | 220 | 206 | 33457.4511 | 18689.97 | 14767.4811 | 4816.0328 | 4847.6507 | 0.0076051 | 0.0023949 | 1.7867 | 5.4545 | 1309 | 0.065211 | 1350 | 0 | 0 | 2.9925 | 1850 | 0
North Valley | 9176 | 50 | 62.1616 | 91 | 80.6596 | 11 | 0.00011405 | 17.3589 | 138.2674 | 3845.5229 | 68658.24 | 14098.0928 | 0.49095 | 20.7243 | 1.004 | 0.0019607 | 0.011669 | 0.54945 | 0.77067 | {A92F717F-76F6-4DE3-9FB1-FEA02A2BC227} | 103031102 | ORO FINO 1102 | 39154 | 39.8872 | -121.6654 | ORO FINO 110239154 | 25 | 10 | 2190.8246 | 1419.8889 | 770.9357 | 1419.8889 | 770.9357 | 0.12836 | 0.0012545 | 1.2432 | 8.2727 | 3 | 0.021568 | 1351 | 0 | 0 | 0.88228 | 1136 | 0
Sierra | 7457 | 162 | 213.0138 | 484 | 366.0408 | 78 | 8.2641e-05 | 25.9848 | 14.1611 | 364.7321 | 3430.3283 | 101.3101 | 4.8076 | 59.855 | 1.2242 | 0.0019572 | 0.00053648 | 0.33471 | 0.58194 | {F283C4DF-68EA-4D46-BF4A-0E3EBCA0E4FA} | 152282101 | MOUNTAIN QUARRIES 2101 | 35466 | 38.9124 | -120.932 | MOUNTAIN QUARRIES 210135466 | 156 | 119 | 18090.191 | 11954.1294 | 6136.0617 | 11954.1294 | 6136.0617 | 0.041846 | 0.006446 | 1.3149 | 6.2051 | 750 | 0.15266 | 1352 | 0 | 0 | 7.4279 | 2034 | 0
North Valley | 4953 | 234 | 347.1323 | 415 | 434.9199 | 59 | 1.619e-05 | 123.685 | 18.3655 | 870.1773 | 9741.3785 | 509.4027 | 3.4111 | 124.9891 | 1.1656 | 0.0019563 | 0.00019445 | 0.56386 | 0.79815 | {BEDEF3DF-E1F0-4BAB-9E81-90CA4240CF80} | 103132101 | CRESCENT MILLS 2101 | 2056 | 40.1084 | -120.9082 | CRESCENT MILLS 21012056 | 108 | 165 | 19554.653 | 10443.0868 | 9111.5662 | 5959.1083 | 5918.1464 | 0.011472 | 0.00095521 | 1.4835 | 7.0339 | 1429 | 0.11542 | 1353 | 0 | 0 | 3.7028 | 1189 | 0
North Valley | 8130 | 64 | 93.5894 | 177 | 138.2357 | 27 | 0.00010011 | 29.1558 | 73.2452 | 584.7657 | 7357.6434 | 1931.0409 | 7.0247 | 29.2594 | 1.0676 | 0.0019292 | 0.0031519 | 0.36158 | 0.67703 | {8AE8ED41-96D0-4F80-9766-8898FDCEAF96} | 103441101 | JESSUP 1101 | 2839 | 40.4926 | -122.3677 | JESSUP 11012839 | 38 | 107 | 6466.4002 | 2364.3372 | 4102.0631 | 2364.3372 | 4102.0631 | 0.085102 | 0.002703 | 1.4623 | 6.5556 | 100 | 0.05209 | 1354 | 0 | 0 | 1.4691 | 1552 | 0
Central Valley | 4777 | 434 | 651.9195 | 1135 | 970.7871 | 126 | 7.568e-05 | 35.9184 | 7.6484 | 58.1912 | 276.7362 | 6.6902 | 4.6802 | 33.4914 | 1.1463 | 0.0019229 | 0.00027391 | 0.38238 | 0.67154 | {FFD203AA-6234-4925-9391-F490E508E718} | 163761703 | RACETRACK 1703 | 9190 | 38.0049 | -120.4056 | RACETRACK 17039190 | 196 | 309 | 30443.9774 | 14436.1267 | 16007.8507 | 14436.1267 | 16007.8507 | 0.034512 | 0.0095357 | 1.5021 | 9.0079 | 1193 | 0.24229 | 1355 | 0 | 0 | 8.9702 | 1734 | 0
North Coast | 9539 | 137 | 187.0718 | 219 | 234.1053 | 10 | 0.00020106 | 9.5754 | 41.6226 | 397.7615 | 6150.7056 | 357.6915 | 1.3507 | 19.0698 | 1.0064 | 0.0018937 | 0.0042391 | 0.62557 | 0.79909 | {59775851-0838-4E2D-9E7C-B84B6CE27B4A} | 43311102 | KONOCTI 1102 | 4421 | 38.8649 | -122.7182 | KONOCTI 11024421 | 6 | 25 | 1746.5159 | 585.3593 | 1161.1566 | 585.3593 | 1161.1566 | 0.042391 | 0.0020106 | 1.3655 | 21.9 | 55 | 0.018937 | 1356 | 0 | 0 | 0.36373 | 837 | 0
North Coast | 4707 | 601 | 983.009 | 672 | 1015.218 | 71 | 0.00014046 | 13.4568 | 2.4468 | 50.7838 | 231.2899 | 0.79337 | 0.20435 | 16.4696 | 1.0297 | 0.0018749 | 0.00021125 | 0.89435 | 0.96827 | {CAD50E3B-E1AA-4BD0-B856-9F05498FC7E2} | 42841112 | GUALALA 1112 | 23444 | 38.849 | -123.644 | GUALALA 111223444 | 195 | 155 | 36723.3513 | 23359.6524 | 13363.6989 | 23359.6524 | 13363.6989 | 0.014999 | 0.0099729 | 1.6356 | 9.4648 | 1376 | 0.13312 | 1357 | 0 | 0 | 14.515 | 1221 | 0
North Valley | 3896 | 302 | 372.406 | 1099 | 722.0648 | 87 | 7.4998e-05 | 24.9287 | 11.3098 | 148.4879 | 1716.2216 | 29.8019 | 1.1201 | 15.7598 | 1.0123 | 0.0018698 | 0.00043991 | 0.2748 | 0.51575 | {B45A6841-43BC-4B7E-A835-22D4DCD838F8} | 102541102 | VOLTA 1102 | 1502 | 40.4948 | -121.873 | VOLTA 11021502 | 130 | 157 | 19104.9374 | 11858.7407 | 7246.1967 | 11858.7407 | 7246.1967 | 0.038272 | 0.0065248 | 1.2331 | 12.6322 | 882 | 0.16267 | 1358 | 0 | 0 | 7.3687 | 430 | 0
Central Coast | 5593 | 7 | 12.1803 | 10 | 13.7716 | 4 | 6.7231e-05 | 25.6892 | 3.0074 | 934.7241 | 8871.1709 | 53.3591 | 6.0996 | 275.2379 | 0.95022 | 0.0018566 | 0.00017966 | 0.7 | 0.88445 | {63E72A21-A36A-4936-B748-71270400CC57} | 182391103 | OILFIELDS 1103 | N48 | 35.7984 | -120.9743 | OILFIELDS 1103N48 | 339 | 238 | 101596.5373 | 76455.2167 | 25141.3205 | 76392.1084 | 25141.3205 | 0.00071865 | 0.00026892 | 1.74 | 2.5 | 1487 | 0.0074263 | 1359 | 0 | 0 | 47.4678 | 1936 | 0
Central Valley | 9018 | 252 | 332.032 | 502 | 453.1377 | 52 | 0.00011914 | 15.611 | 62.8369 | 330.1677 | 5058 | 604.036 | 0.78506 | 10.0874 | 1.0046 | 0.0018537 | 0.0032519 | 0.50199 | 0.73274 | {94C99AB4-12AC-4B39-8DBB-EDDC32F126DD} | 163751102 | PINE GROVE 1102 | 9145 | 38.4082 | -120.6204 | PINE GROVE 11029145 | 46 | 48 | 7464.3327 | 4703.8594 | 2760.4733 | 4703.8594 | 2760.4733 | 0.1691 | 0.0061954 | 1.3176 | 9.6538 | 87 | 0.09639 | 1360 | 0 | 0 | 2.9228 | 1753 | 0
Central Valley | 5804 | 192 | 262.5425 | 1114 | 768.2939 | 99 | 7.9711e-05 | 22.4024 | 7.4923 | 32.6214 | 259.9655 | 4.7419 | 1.6685 | 17.8731 | 1.0539 | 0.0018443 | 0.00038199 | 0.17235 | 0.34172 | {246AEE64-BD98-43AF-876E-DF5040419CD3} | 254432102 | COARSEGOLD 2102 | 10050 | 37.3092 | -119.5842 | COARSEGOLD 210210050 | 138 | 261 | 24726.2745 | 11531.9078 | 13194.3668 | 11531.9078 | 13194.3668 | 0.037817 | 0.0078914 | 1.3674 | 11.2525 | 964 | 0.18258 | 1361 | 0 | 0 | 7.1656 | 2857 | 0
North Valley | 2833 | 19 | 25.8131 | 105 | 75.527 | 28 | 1.0338e-05 | 173.6053 | 4.1247 | 1973.5194 | 12938.4337 | 87.8128 | 3.9099 | 819.6356 | 1.4715 | 0.0018369 | 2.8809e-05 | 0.18095 | 0.34177 | {94162D16-0097-44C8-A147-FCAA580DD744} | 103491101 | MC ARTHUR 1101 | 37388 | 41.1 | -121.1865 | MC ARTHUR 110137388 | 68 | 56 | 21260.0481 | 20103.5682 | 1156.4799 | 12648.9045 | 737.5626 | 0.00080664 | 0.00028947 | 1.3586 | 3.75 | 2480 | 0.051433 | 1362 | 0 | 0 | 7.8597 | 1482 | 0
North Valley | 5948 | 597 | 1136.8187 | 3274 | 2110.0435 | 436 | 4.7352e-05 | 37.0235 | 8.4465 | 786.0554 | 6559.5297 | 143.0975 | 5.02 | 210.1306 | 1.3248 | 0.0018264 | 0.00019302 | 0.18235 | 0.53877 | {381D7853-5A02-4486-A50E-C31E33DE4E4C} | 103091102 | CLARK ROAD 1102 | 92622 | 39.6565 | -121.5745 | CLARK ROAD 110292622 | 316 | 316 | 76227.3915 | 49506.0782 | 26721.3133 | 49506.0782 | 26721.3133 | 0.084158 | 0.020646 | 1.9042 | 7.5092 | 1440 | 0.7963 | 1363 | 0 | 0 | 30.7616 | 1619 | 0
Central Coast | 4174 | 154 | 324.8083 | 342 | 419.7693 | 84 | 2.0601e-05 | 135.989 | 6.9732 | 148.5024 | 885.4263 | 18.6288 | 5.4297 | 67.7818 | 1.0872 | 0.0018251 | 6.3287e-05 | 0.45029 | 0.77378 | {1CF1F40F-51DA-4763-B407-DDAB0EF0C4E4} | 182631103 | SAN LUIS OBISPO 1103 | V82 | 35.2151 | -120.615 | SAN LUIS OBISPO 1103V82 | 308 | 489 | 49102.3457 | 22412.6462 | 26689.6996 | 12932.1765 | 13043.636 | 0.0053161 | 0.0017305 | 2.1091 | 4.0714 | 2110 | 0.15331 | 1364 | 0 | 0 | 8.0357 | 2620 | 0
North Coast | 2726 | 82 | 194.4612 | 100 | 203.8568 | 30 | 6.6426e-05 | 27.0639 | 0.60156 | 102.7053 | 735.1029 | 1.048 | 0.61298 | 37.4755 | 1.0614 | 0.0018199 | 5.362e-05 | 0.82 | 0.95391 | {2E3AB06D-E271-44D1-BCDE-8DE501692F34} | 42861101 | ANNAPOLIS 1101 | 76842 | 38.6803 | -123.3125 | ANNAPOLIS 110176842 | 43 | 21 | 10860.6465 | 9045.3441 | 1815.3024 | 9045.3441 | 1815.3024 | 0.0016086 | 0.0019928 | 2.3715 | 3.3333 | 2208 | 0.054597 | 1365 | 0 | 0 | 5.6205 | 916 | 0
Central Coast | 1416 | 579 | 1128.0805 | 752 | 1230.4116 | 74 | 8.9438e-05 | 21.2764 | 8.1551 | 343.9313 | 5998.2718 | 37.1472 | 1.2401 | 23.9959 | 1.1101 | 0.0018069 | 0.00037218 | 0.76995 | 0.91683 | {7DF78B7A-3D58-4011-B365-74BA17A842F7} | 82841102 | BIG BASIN 1102 | circuit_breaker | 37.131 | -122.1722 | BIG BASIN 1102circuit_breaker | 100 | 62 | 14256.5773 | 10031.5247 | 4225.0526 | 10031.5247 | 4225.0526 | 0.027541 | 0.0066184 | 1.9483 | 10.1622 | 979 | 0.13371 | 1366 | 0 | 0 | 6.2333 | 1848 | 0
North Coast | 6947 | 719 | 1227.247 | 950 | 1337.9055 | 115 | 0.00015549 | 8.7469 | 1.2277 | 46.0638 | 235.1419 | 0.55156 | 0.18138 | 8.3254 | 1.0116 | 0.0018025 | 0.00018197 | 0.75684 | 0.91729 | {AF459D89-AFC9-4CD3-8D0B-AF684DED3FA0} | 192021121 | ARCATA 1121 | 1206 | 40.8684 | -124.0707 | ARCATA 11211206 | 237 | 269 | 43650.5109 | 25263.8878 | 18386.6231 | 11057.5552 | 3843.368 | 0.020927 | 0.017881 | 1.7069 | 8.2609 | 1479 | 0.20728 | 1367 | 0 | 0 | 6.8708 | 2092 | 0
Sierra | 3578 | 216 | 289.9067 | 334 | 348.8203 | 40 | 0.00014263 | 13.1447 | 26.684 | 364.3965 | 5188.9589 | 274.8938 | 1.7527 | 28.7612 | 1.0817 | 0.0018017 | 0.002078 | 0.64671 | 0.83111 | {86E99440-83ED-4726-A6BC-38E34FEB5B33} | 153082106 | PLACERVILLE 2106 | circuit_breaker | 38.731 | -120.7832 | PLACERVILLE 2106circuit_breaker | 47 | 30 | 13918.2751 | 10714.4314 | 3203.8437 | 10352.4951 | 2702.7103 | 0.083119 | 0.0057052 | 1.3422 | 8.35 | 169 | 0.072068 | 1368 | 0 | 0 | 6.4327 | 1401 | 0
Central Coast | 711 | 1635 | 3362.0951 | 1912 | 3528.0261 | 104 | 0.00011174 | 16.7583 | 7.5215 | 61.5722 | 522.8562 | 6.6725 | 0.56503 | 11.5593 | 1.0182 | 0.0017922 | 0.00048981 | 0.85513 | 0.95297 | {87B7E394-3606-4372-9564-36FE0E57DA45} | 82841102 | BIG BASIN 1102 | 96986 | 37.172 | -122.1648 | BIG BASIN 110296986 | 96 | 93 | 17195.3678 | 9463.8689 | 7731.4989 | 9463.8689 | 7731.4989 | 0.050941 | 0.011621 | 2.0563 | 18.3846 | 798 | 0.18639 | 1369 | 0 | 0 | 5.8806 | 1653 | 0
Sierra | 5251 | 1035 | 1357.5816 | 2325 | 1941.4733 | 275 | 1.3683e-05 | 114.6486 | 12.1965 | 3270.5509 | 105694.0001 | 2267.6399 | 0.40782 | 22.481 | 1.1235 | 0.001792 | 9.2003e-05 | 0.44516 | 0.69925 | {B02385C8-6373-4D81-ABD4-7C98960F9245} | 152101101 | ALLEGHANY 1101 | 804 | 39.5598 | -120.8239 | ALLEGHANY 1101804 | 288 | 471 | 48831.2033 | 34767.038 | 14064.1653 | 34767.038 | 14064.1653 | 0.025301 | 0.0037629 | 1.3117 | 8.4545 | 1897 | 0.49281 | 1370 | 0 | 0 | 21.6032 | 154 | 0
Central Coast | 6214 | 521 | 942.143 | 1333 | 1441.1759 | 96 | 0.00012459 | 14.1786 | 12.17 | 61.1605 | 512.5577 | 12.9957 | 1.0259 | 10.5239 | 1.0252 | 0.001786 | 0.00086609 | 0.39085 | 0.65373 | {11174DFD-907B-47BB-8CC5-096C12F9E27C} | 83252106 | PAUL SWEET 2106 | 8091 | 37.0477 | -121.9389 | PAUL SWEET 21068091 | 106 | 126 | 17874.9693 | 9677.9322 | 8197.0371 | 9677.9322 | 8197.0371 | 0.083145 | 0.011961 | 1.8083 | 13.8854 | 464 | 0.17146 | 1371 | 0 | 0 | 6.0136 | 1906 | 0
North Coast | 9466 | 54 | 94.5197 | 174 | 147.831 | 21 | 6.6787e-05 | 27.2297 | 0.29817 | 46.5186 | 284.6702 | 0.10904 | 0.19711 | 18.7646 | 1.0572 | 0.0017789 | 4.1209e-05 | 0.31034 | 0.63938 | {59886564-6CA1-4F45-A988-019BCC3E66E5} | 43381101 | POINT ARENA 1101 | 4923 | 38.9464 | -123.6449 | POINT ARENA 11014923 | 12 | 14 | 5274.0717 | 4611.3164 | 662.7553 | 4611.3164 | 662.7553 | 0.00086538 | 0.0014025 | 1.7504 | 8.2857 | 2324 | 0.037358 | 1372 | 0 | 0 | 2.8653 | 482 | 0
Central Valley | 973 | 8 | 16.7681 | 49 | 28.5899 | 17 | 3.1846e-05 | 80.0224 | 31.4352 | 163.9105 | 616.1348 | 64.8982 | 5.7577 | 55.205 | 1.0945 | 0.0017745 | 0.00053046 | 0.16327 | 0.5865 | {1EA8CF8C-ECB4-4CEA-BCE6-3A74137F1411} | 163781704 | PEORIA 1704 | 13494 | 37.9346 | -120.6385 | PEORIA 170413494 | 149 | 289 | 28325.4492 | 12088.6323 | 16236.8168 | 3111.8752 | 3682.3162 | 0.0090179 | 0.00054138 | 2.096 | 2.8824 | 757 | 0.030167 | 1373 | 0 | 0 | 1.9336 | 1178 | 0
Central Valley | 7975 | 180 | 237.2763 | 425 | 339.7231 | 52 | 9.5147e-05 | 19.394 | 18.1097 | 89.6216 | 522.3367 | 19.5795 | 2.7414 | 72.4378 | 1.1007 | 0.001772 | 0.00081049 | 0.42353 | 0.69844 | {52B817B8-3607-4215-94CE-6DB0D80039B6} | 163011101 | MARTELL 1101 | 6074 | 38.3928 | -120.7927 | MARTELL 11016074 | 45 | 40 | 7979.5112 | 5835.7283 | 2143.7828 | 5835.7283 | 2143.7828 | 0.042145 | 0.0049476 | 1.3182 | 8.1731 | 493 | 0.092143 | 1374 | 0 | 0 | 3.6262 | 331 | 0
Sierra | 2028 | 434 | 494.6544 | 1372 | 910.2416 | 72 | 0.00010347 | 17.5685 | 16.3709 | 256.9366 | 4531.561 | 677.4647 | 0.55722 | 6.8569 | 1.2282 | 0.0017702 | 0.00081798 | 0.31633 | 0.54343 | {E2D02A33-8746-4464-A366-79BFD6EADB5B} | 152762102 | EL DORADO PH 2102 | 6645 | 38.7648 | -120.5895 | EL DORADO PH 21026645 | 93 | 147 | 14407.0674 | 6883.7119 | 7523.3555 | 6883.7119 | 7523.3555 | 0.058895 | 0.0074498 | 1.1398 | 19.0556 | 488 | 0.12746 | 1375 | 0 | 0 | 4.2773 | 129 | 0
North Coast | 3965 | 5 | 9.7249 | 42 | 23.3888 | 12 | 7.4177e-05 | 25.821 | 0.26024 | 0.13507 | 0.1586 | 0.00020388 | 1.4124 | 5.3462 | 1.0258 | 0.0017643 | 5.624e-05 | 0.11905 | 0.41579 | {D29B0306-223B-4BFF-9389-253396BA7A0F} | 43191102 | REDBUD 1102 | 432 | 38.9803 | -122.6634 | REDBUD 1102432 | 292 | 1350 | 77507.4088 | 18069.9686 | 59437.4402 | 1279.6978 | 3634.9092 | 0.00067488 | 0.00089012 | 1.945 | 3.5 | 2181 | 0.021171 | 1376 | 0 | 0 | 0.79517 | 2544 | 0
Bay Area | 4355 | 2 | 2.2201 | 9 | 5.9776 | 2 | 0.00014652 | 11.962 |  |  |  |  | 0.012168 | 6.8466 | 1.0232 | 0.0017579 | 0.00014652 | 0.22222 | 0.37141 | {E69E0EDF-3BE3-421A-B55B-BE689105FC5C} | 42711102 | CALISTOGA 1102 | 705 | 38.577 | -122.5827 | CALISTOGA 1102705 | 41 | 218 | 10393.8054 | 2007.629 | 8386.1764 | 320.3013 | 1925.2744 | 0.00029304 | 0.00029304 | 1.1101 | 4.5 | 1611 | 0.0035158 | 1377 | 0 | 0 | 0.19903 | 2266 | 0
North Coast | 8666 | 152 | 196.5502 | 337 | 301.6665 | 37 | 0.00020995 | 9.7161 | 13.1616 | 36.872 | 123.5385 | 3.4103 | 1.7928 | 11.129 | 1.0036 | 0.0017549 | 0.001277 | 0.45104 | 0.65155 | {CA1929FB-954F-421C-A276-7ADA46AE0B27} | 43141101 | MIDDLETOWN 1101 | 1079 | 38.8145 | -122.7088 | MIDDLETOWN 11011079 | 80 | 207 | 15089.0321 | 5531.7956 | 9557.2364 | 5531.7956 | 9557.2364 | 0.047248 | 0.007768 | 1.2931 | 9.1081 | 298 | 0.064932 | 1378 | 0 | 0 | 3.4373 | 2444 | 0
North Valley | 2938 | 0 | 0 | 25 | 15.6466 | 8 | 3.4121e-05 | 104.6949 | 0 | 0.0063586 | 0.0061715 | 0 | 4.0136 | 128.6855 | 1.1668 | 0.0017453 | 1.9519e-05 | 0 | 0 | {2E555E2F-D45B-427A-941D-A906BDE558FE} | 103311101 | BURNEY 1102 | 2402 | 40.8884 | -121.6712 | BURNEY 11022402 | 34 | 5 | 6171.6526 | 6035.4639 | 136.1888 | 2243.205 | 41.7017 | 0.00015615 | 0.00027297 |  | 3.125 | 2618 | 0.013963 | 1379 | 0 | 0 | 1.3939 | 450 | 0
Central Valley | 7662 | 306 | 416.4181 | 1044 | 778.8956 | 149 | 6.7972e-05 | 28.0224 | 4.698 | 105.1385 | 1011.6224 | 15.2819 | 2.5767 | 38.8252 | 1.0747 | 0.0017417 | 0.0002188 | 0.2931 | 0.53463 | {FE7641C5-7812-4FD4-8B21-6308923D8DFD} | 254432102 | COARSEGOLD 2102 | 10330 | 37.2515 | -119.562 | COARSEGOLD 210210330 | 124 | 96 | 21945.6196 | 15524.0665 | 6421.5532 | 15524.0665 | 6421.5532 | 0.032602 | 0.010128 | 1.3608 | 7.0067 | 1346 | 0.25952 | 1380 | 0 | 0 | 9.6462 | 2838 | 0
Bay Area | 3452 | 172 | 506.7819 | 199 | 516.8662 | 27 | 3.7372e-05 | 54.3592 | 10.0495 | 211.3691 | 1282.15 | 30.2165 | 2.4966 | 96.1455 | 1.0928 | 0.001739 | 8.0892e-05 | 0.86432 | 0.98049 | {F951C9B5-DFF6-4F18-959A-6543A104D243} | 24101103 | HALF MOON BAY 1103 | 9112 | 37.4533 | -122.4297 | HALF MOON BAY 11039112 | 173 | 101 | 21054.252 | 12911.7543 | 8142.4977 | 5442.5238 | 1401.7517 | 0.0021841 | 0.001009 | 2.9464 | 7.3704 | 1976 | 0.046954 | 1381 | 0 | 0 | 3.3818 | 2673 | 0
Central Coast | 6902 | 848 | 1217.5232 | 1571 | 1580.0925 | 218 | 4.5639e-05 | 34.8964 | 0.86929 | 238.208 | 1282.3479 | 4.059 | 5.7222 | 321.4582 | 1.29 | 0.0017313 | 4.5188e-05 | 0.53978 | 0.77054 | {3081AC44-490C-41E8-9095-7905CD98E81E} | 182541103 | ATASCADERO 1103 | A14 | 35.3237 | -120.5163 | ATASCADERO 1103A14 | 170 | 158 | 48649.5509 | 40416.4237 | 8233.1271 | 40416.4237 | 8233.1271 | 0.0098509 | 0.0099492 | 1.4358 | 7.2064 | 2281 | 0.37741 | 1382 | 0 | 0 | 25.1136 | 715 | 0
Central Coast | 8528 | 246 | 441.7818 | 304 | 475.6777 | 23 | 0.00010055 | 16.6092 | 5.2222 | 38.2072 | 223.45 | 1.9954 | 1.0384 | 17.106 | 1.0628 | 0.0017309 | 0.00031971 | 0.80921 | 0.92874 | {A307E01D-38BD-458E-A0F5-C1940DA0A5B2} | 82841102 | BIG BASIN 1102 | 2253 | 37.1711 | -122.1653 | BIG BASIN 11022253 | 17 | 16 | 3716.5479 | 2352.4543 | 1364.0936 | 2352.4543 | 1364.0936 | 0.0073533 | 0.0023127 | 1.7959 | 13.2174 | 1076 | 0.03981 | 1383 | 0 | 0 | 1.4617 | 2125 | 0
Central Valley | 2205 | 1301 | 1867.4792 | 4292 | 3248.0564 | 547 | 6.2567e-05 | 31.212 | 17.151 | 447.9876 | 6240.7251 | 481.0387 | 2.3059 | 52.5671 | 1.2208 | 0.0017277 | 0.00045927 | 0.30312 | 0.57495 | {32DE7714-2265-4DEA-9044-817FFC428BF4} | 163451701 | FROGTOWN 1701 | 13412 | 38.1336 | -120.4621 | FROGTOWN 170113412 | 579 | 908 | 120654.5216 | 62186.2508 | 58468.2708 | 62186.2508 | 58468.2708 | 0.25122 | 0.034224 | 1.4354 | 7.8464 | 849 | 0.94506 | 1384 | 0 | 0 | 38.6407 | 229 | 0
Central Coast | 7553 | 12 | 38.7169 | 22 | 45.0666 | 9 | 3.0463e-05 | 68.0902 |  |  |  |  | 5.7062 | 396.5175 | 1.2321 | 0.0017264 | 3.0463e-05 | 0.54545 | 0.85911 | {2DBCA866-9F0D-46E8-B9B3-4863FA94560D} | 182821103 | MESA 1103 | M92 | 35.0168 | -120.4802 | MESA 1103M92 | 230 | 351 | 28394.1427 | 12733.2432 | 15660.8996 | 1573.0951 | 959.5422 | 0.00027417 | 0.00027417 | 3.2264 | 2.4444 | 2466 | 0.015537 | 1385 | 0 | 0 | 0.97748 | 1846 | 0
North Valley | 637 | 807 | 1013.1999 | 1647 | 1404.8514 | 198 | 0.00013855 | 12.6755 | 15.7514 | 292.6787 | 4552.872 | 156.1955 | 0.68268 | 9.3264 | 1.0102 | 0.001724 | 0.0011895 | 0.48998 | 0.72121 | {E257A63A-542E-454C-A7F1-D1C2484C4152} | 103031102 | ORO FINO 1102 | 2090 | 39.858 | -121.6135 | ORO FINO 11022090 | 304 | 546 | 59641.5997 | 23596.9335 | 36044.6662 | 23596.9335 | 36044.6662 | 0.23553 | 0.027432 | 1.2555 | 8.3182 | 327 | 0.34135 | 1386 | 0 | 0 | 14.6625 | 655 | 0
Central Valley | 3944 | 204 | 288.3663 | 803 | 548.8093 | 144 | 5.5719e-05 | 29.9918 | 15.4188 | 435.5522 | 1592.4495 | 34.7338 | 4.6891 | 93.7129 | 1.1636 | 0.0017211 | 0.00037195 | 0.25405 | 0.52544 | {D96B1841-141B-4A05-91C1-D6709B1FFA78} | 163451702 | FROGTOWN 1702 | 91134 | 38.0722 | -120.5399 | FROGTOWN 170291134 | 241 | 272 | 41470.356 | 25769.8346 | 15700.5214 | 22498.6303 | 12556.3719 | 0.053561 | 0.0080235 | 1.4136 | 5.5764 | 980 | 0.24784 | 1387 | 0 | 0 | 13.98 | 1378 | 0
Central Coast | 1077 | 55 | 175.0543 | 63 | 180.2685 | 10 | 3.37e-05 | 48.1305 | 0.5642 | 54.0419 | 156.6975 | 0.17682 | 9.5031 | 95.7898 | 1.3142 | 0.0017144 | 2.7167e-05 | 0.87302 | 0.97108 | {723FB00A-7C12-42CB-85FE-70F2D7BE445E} | 183101103 | CABRILLO 1103 | Y12 | 34.6648 | -120.4223 | CABRILLO 1103Y12 | 344 | 295 | 78123.816 | 49554.7865 | 28569.0295 | 40069.4408 | 24697.5294 | 0.00027167 | 0.000337 | 3.1828 | 6.3 | 2503 | 0.017144 | 1388 | 0 | 0 | 24.898 | 1837 | 0
Bay Area | 9541 | 14 | 24.7013 | 103 | 81.0563 | 15 | 5.0132e-05 | 48.1037 | 4.6509 | 1896.5326 | 27752.9215 | 190.5576 | 1.2273 | 84.1854 | 1.0991 | 0.0017133 | 9.5051e-05 | 0.13592 | 0.30474 | {702CCB2B-B1B0-4591-B980-760D81375AFB} | 42291101 | OLEMA 1101 | 75686 | 38.0487 | -122.7435 | OLEMA 110175686 | 44 | 11 | 10084.2217 | 7759.3517 | 2324.87 | 6456.4354 | 2324.87 | 0.0014258 | 0.00075199 | 1.7644 | 6.8667 | 1879 | 0.0257 | 1389 | 0 | 0 | 4.0118 | 2516 | 0
North Coast | 5248 | 155 | 347.931 | 466 | 528.8405 | 27 | 8.4155e-05 | 21.2102 | 1.8776 | 14.9827 | 63.3552 | 0.302 | 5.4902 | 20.0654 | 1.1115 | 0.001705 | 0.0001198 | 0.33262 | 0.65791 | {8AED6124-82F9-4968-B1CD-29F6C223DBAE} | 42091101 | MIRABEL 1101 | 228 | 38.4615 | -122.8806 | MIRABEL 1101228 | 186 | 271 | 30794.9489 | 15637.442 | 15157.5069 | 3472.2526 | 3889.0134 | 0.0032346 | 0.0022722 | 2.2447 | 17.2593 | 1749 | 0.046034 | 1390 | 0 | 0 | 2.1576 | 2123 | 0
Sierra | 8334 | 559 | 665.718 | 1417 | 1077.4205 | 147 | 5.1871e-05 | 34.8468 | 49.1996 | 3129.6309 | 86630.8346 | 9871.5043 | 0.91087 | 20.2771 | 1.1138 | 0.001698 | 0.0011092 | 0.3945 | 0.61788 | {05132EF1-E962-492C-8CE4-DD542C3B3D15} | 152181101 | FORESTHILL 1101 | 37238 | 39.0472 | -120.7859 | FORESTHILL 110137238 | 112 | 116 | 27233.8309 | 18519.0658 | 8714.7652 | 18519.0658 | 8714.7652 | 0.16306 | 0.007625 | 1.1909 | 9.6395 | 357 | 0.2496 | 1391 | 0 | 0 | 11.5072 | 690 | 0
North Coast | 3121 | 10 | 15.2774 | 39 | 31.6109 | 11 | 9.9028e-05 | 15.675 | 2.2151 | 97.7231 | 697.0297 | 25.6937 | 5.3741 | 106.684 | 1.1018 | 0.0016936 | 0.00015533 | 0.25641 | 0.4833 | {883C1192-DE93-49B0-9D61-992A9165A32C} | 42721104 | SONOMA 1104 | 78372 | 38.2972 | -122.5041 | SONOMA 110478372 | 289 | 333 | 50691.8189 | 27765.3023 | 22926.5166 | 26611.5178 | 21270.6772 | 0.0017086 | 0.0010893 | 1.5277 | 3.5455 | 1563 | 0.01863 | 1392 | 0 | 0 | 16.5356 | 1892 | 0
Central Valley | 8547 | 462 | 599.5522 | 799 | 780.2612 | 49 | 9.8385e-05 | 17.0423 | 105.9252 | 1315.1232 | 23027.8992 | 6579.684 | 1.3592 | 31.227 | 1.0425 | 0.0016918 | 0.0047423 | 0.57822 | 0.7684 | {A62A472C-6B1A-4D7F-BCA4-027FEE815FC1} | 163201102 | WEST POINT 1102 | 1535 | 38.3844 | -120.513 | WEST POINT 11021535 | 46 | 68 | 6904.4385 | 4933.5895 | 1970.8491 | 4933.5895 | 1970.8491 | 0.23238 | 0.0048209 | 1.2977 | 16.3061 | 39 | 0.0829 | 1393 | 0 | 0 | 3.0656 | 2478 | 0
Central Valley | 3162 | 3 | 3.3067 | 19 | 11.3308 | 9 | 0.00014005 | 13.2796 | 83.9539 | 1866.5334 | 38651.401 | 13087.7091 | 0.79105 | 6.7197 | 1.0037 | 0.0016891 | 0.0065012 | 0.15789 | 0.29184 | {E8E54876-15CA-4535-8C00-844AA0076F05} | 163201101 | WEST POINT 1101 | 4706 | 38.4647 | -120.5292 | WEST POINT 11014706 | 260 | 438 | 43003.2953 | 18548.1318 | 24455.1635 | 18548.1318 | 24455.1635 | 0.058511 | 0.0012605 | 1.1022 | 2.1111 | 25 | 0.015202 | 1394 | 0 | 0 | 11.5253 | 434 | 0
Central Coast | 7753 | 775 | 1261.5307 | 1238 | 1530.7628 | 76 | 0.00010828 | 13.8339 | 4.1728 | 32.7242 | 235.3024 | 2.074 | 1.2041 | 14.3682 | 1.0298 | 0.0016774 | 0.00027149 | 0.62601 | 0.82412 | {CCDF3A25-AE56-4EB7-B245-ECC2A1643713} | 83622106 | CAMP EVERS 2106 | 60120 | 37.1305 | -121.9785 | CAMP EVERS 210660120 | 68 | 59 | 11018.134 | 7017.9486 | 4000.1854 | 7017.9486 | 4000.1854 | 0.020633 | 0.008229 | 1.6278 | 16.2895 | 1201 | 0.12748 | 1395 | 0 | 0 | 4.3607 | 239 | 0
Central Coast | 4076 | 410 | 546.0728 | 1678 | 1329.5867 | 207 | 4.5113e-05 | 44.6572 | 0.67737 | 110.6461 | 490.3432 | 1.066 | 2.1445 | 175.342 | 1.1397 | 0.0016525 | 3.2622e-05 | 0.24434 | 0.41071 | {DABFD7CD-8833-44A0-9DBA-3E8A3AC2C2CC} | 182611104 | PASO ROBLES 1104 | R12 | 35.6607 | -120.7652 | PASO ROBLES 1104R12 | 344 | 216 | 80249.7772 | 64641.2434 | 15608.5338 | 42365.8362 | 12283.4585 | 0.0067527 | 0.0093385 | 1.3319 | 8.1063 | 2432 | 0.34206 | 1396 | 0 | 0 | 26.3249 | 1299 | 0
North Valley | 3997 | 670 | 1122.1436 | 2731 | 1902.7194 | 367 | 6.7023e-05 | 29.3027 | 33.952 | 1023.3646 | 13493.7452 | 1012.295 | 3.9342 | 70.7302 | 1.2457 | 0.0016469 | 0.0011556 | 0.24533 | 0.58976 | {0429E1C1-6AB0-4F59-A5C2-5CBC7A378110} | 102911107 | WYANDOTTE 1107 | 1510 | 39.497 | -121.4452 | WYANDOTTE 11071510 | 334 | 273 | 62658.4921 | 41028.1557 | 21630.3364 | 41028.1557 | 21630.3364 | 0.42412 | 0.024597 | 1.6748 | 7.4414 | 340 | 0.6044 | 1397 | 0 | 0 | 25.4937 | 2116 | 0
North Valley | 161 | 100 | 191.1955 | 1677 | 911.8608 | 286 | 3.4883e-05 | 41.4621 | 3.4865 | 647.0693 | 18798.7685 | 201.2788 | 0.17059 | 10.1042 | 1.0132 | 0.0016436 | 8.1408e-05 | 0.05963 | 0.20968 | {CC6E361B-CB3E-4B40-BF58-ADB4E431D8DD} | 103201101 | CHALLENGE 1101 | 98174 | 39.6081 | -121.0754 | CHALLENGE 110198174 | 253 | 359 | 42021.1259 | 31495.8005 | 10525.3254 | 31495.8005 | 10525.3254 | 0.023283 | 0.0099765 | 1.912 | 5.8636 | 1972 | 0.47006 | 1398 | 0 | 0 | 19.5706 | 941 | 0
Central Valley | 8741 | 2 | 2.6363 | 22 | 10.4146 | 9 | 0.00012084 | 13.2768 | 5.8477 | 21.8562 | 52.7174 | 0.31845 | 0.96411 | 6.6459 | 1.0054 | 0.0016398 | 0.00050882 | 0.090909 | 0.25314 | {2737D8E9-06AE-4808-BE80-BDF76249D619} | 163201101 | WEST POINT 1101 | L3355 | 38.5061 | -120.4938 | WEST POINT 1101L3355 | 34 | 50 | 6042.7096 | 3577.4455 | 2465.2642 | 3577.4455 | 2465.2642 | 0.0045794 | 0.0010875 | 1.3182 | 2.4444 | 780 | 0.014759 | 1399 | 0 | 0 | 2.2229 | 2750 | 0
Bay Area | 9394 | 19 | 54.044 | 80 | 91.4376 | 19 | 5.809e-05 | 32.6944 | 3.287 | 212.6742 | 1986.5934 | 12.0377 | 1.2867 | 45.8505 | 1.1106 | 0.0016384 | 0.00013821 | 0.2375 | 0.59105 | {6FB5348B-5DA9-49B1-98A7-B3620A483016} | 42261101 | BOLINAS 1101 | 1232 | 37.9365 | -122.7035 | BOLINAS 11011232 | 30 | 13 | 6602.698 | 3935.7724 | 2666.9256 | 3520.8723 | 632.7638 | 0.002626 | 0.0011037 | 2.8444 | 4.2105 | 1641 | 0.03113 | 1400 | 0 | 0 | 2.1878 | 2082 | 0
Central Valley | 4304 | 71 | 96.8181 | 198 | 157.1807 | 58 | 5.0975e-06 | 287.0739 | 8.5496 | 8634.2874 | 47950.3381 | 476.787 | 12.5322 | 2511.6663 | 1.7919 | 0.0016381 | 2.1167e-05 | 0.35859 | 0.61597 | {80FE859C-5651-4408-BF07-1945D67AD54A} | 253642101 | POSO MOUNTAIN 2101 | 4456 | 35.5878 | -118.958 | POSO MOUNTAIN 21014456 | 111 | 75 | 44264.304 | 37862.2156 | 6402.0884 | 37862.2156 | 6402.0884 | 0.0012277 | 0.00029565 | 1.3636 | 3.4138 | 2585 | 0.095012 | 1401 | 0 | 0 | 23.5265 | 1940 | 0
Bay Area | 1800 | 134 | 267.9707 | 842 | 683.1342 | 97 | 4.611e-05 | 36.8336 | 0.15256 | 8.0644 | 26.3069 | 0.02825 | 2.8158 | 126.7631 | 1.1141 | 0.0016262 | 3.1609e-05 | 0.15914 | 0.39227 | {4396A44C-BE29-48A2-B592-2211E388C99B} | 14091108 | CASTRO VALLEY 1108 | MR748 | 37.6953 | -122.024 | CASTRO VALLEY 1108MR748 | 148 | 149 | 21801.289 | 10026.1125 | 11775.1765 | 10026.1125 | 11775.1765 | 0.003066 | 0.0044727 | 1.9998 | 8.6804 | 2447 | 0.15774 | 1402 | 0 | 0 | 6.2299 | 2821 | 0
Bay Area | 7085 | 98 | 173.8963 | 369 | 336.7233 | 32 | 4.0636e-05 | 49.5885 | 1.1797 | 49.7394 | 209.6519 | 0.59359 | 7.0759 | 249.1353 | 1.2938 | 0.0016191 | 4.5254e-05 | 0.26558 | 0.51644 | {787A6620-F35C-455C-956E-13AAB9DBEE49} | 24131102 | MENLO 1102 | 12249 | 37.3532 | -122.2644 | MENLO 110212249 | 33 | 32 | 6938.7116 | 3776.3578 | 3162.3538 | 3776.3578 | 3162.3538 | 0.0014481 | 0.0013003 | 1.7745 | 11.5312 | 2280 | 0.051811 | 1403 | 0 | 0 | 2.3465 | 2754 | 0
North Coast | 7099 | 156 | 167.0111 | 260 | 217.1555 | 30 | 0.00010054 | 19.098 | 3.7353 | 104.0198 | 1048.7543 | 5.8682 | 0.94727 | 42.4669 | 1.0844 | 0.0016144 | 0.00025407 | 0.6 | 0.76909 | {5346AC49-CDE1-40C3-A681-DA76F08A9FA4} | 192411101 | LOW GAP 1101 | circuit_breaker | 40.4336 | -123.473 | LOW GAP 1101circuit_breaker | 34 | 35 | 4417.3744 | 3490.2509 | 927.1235 | 3490.2509 | 927.1235 | 0.0076222 | 0.0030163 | 1.0706 | 8.6667 | 1238 | 0.048432 | 1404 | 0 | 0 | 2.1687 | 258 | 0
Sierra | 5621 | 1912 | 2606.1839 | 3746 | 3564.8777 | 420 | 0.00012208 | 14.1119 | 61.1225 | 1158.739 | 18754.8159 | 3055.2398 | 2.1616 | 29.1879 | 1.0858 | 0.0016135 | 0.0035734 | 0.51041 | 0.73107 | {E9B2D551-2CAF-489B-9D1C-4D1BCFDB0559} | 153661104 | APPLE HILL 1104 | 97086 | 38.7653 | -120.7046 | APPLE HILL 110497086 | 439 | 539 | 76470.8405 | 41232.2745 | 35238.566 | 41232.2745 | 35238.566 | 1.5008 | 0.051274 | 1.3631 | 8.919 | 76 | 0.67766 | 1405 | 0 | 0 | 25.6205 | 370 | 0
Central Valley | 3710 | 68 | 109.7319 | 316 | 194.1311 | 95 | 7.196e-05 | 29.5123 | 6.2392 | 101.4786 | 528.9607 | 3.9571 | 7.4268 | 168.8223 | 1.2698 | 0.0016115 | 0.00022275 | 0.21519 | 0.56525 | {16B948B9-B372-45A4-B29D-56B8F2A70B74} | 162211101 | CALAVERAS CEMENT 1101 | circuit_breaker | 38.1697 | -120.6679 | CALAVERAS CEMENT 1101circuit_breaker | 491 | 801 | 69356.2814 | 29364.3079 | 39991.9735 | 16524.9105 | 8049.6131 | 0.021161 | 0.0068362 | 1.6137 | 3.3263 | 1333 | 0.15309 | 1406 | 0 | 0 | 10.2681 | 2634 | 0
Central Coast | 4990 | 1609 | 2503.3768 | 3141 | 3394.5723 | 239 | 8.0005e-05 | 20.3646 | 2.4947 | 63.9161 | 686.9349 | 4.6098 | 1.1632 | 18.653 | 1.0762 | 0.0016005 | 0.00013492 | 0.51226 | 0.73746 | {ED4FFAA8-32ED-4B25-8B3D-9D1525DB179F} | 82021106 | LOS GATOS 1106 | LB48 | 37.19 | -121.9942 | LOS GATOS 1106LB48 | 220 | 140 | 35690.519 | 23832.8123 | 11857.7067 | 23832.8123 | 11857.7067 | 0.032246 | 0.019121 | 1.5559 | 13.1423 | 1665 | 0.38252 | 1407 | 0 | 0 | 14.809 | 1948 | 0
North Coast | 2960 | 88 | 175.8807 | 254 | 254.0624 | 55 | 8.4472e-05 | 20.8175 | 1.8382 | 122.1642 | 2830.6212 | 91.4668 | 0.38126 | 3.9458 | 1.0188 | 0.0015982 | 0.00010352 | 0.34646 | 0.69227 | {11292177-63B4-4D1D-9B97-B2A90B30A4AD} | 43351106 | LUCERNE 1106 | 38632 | 38.9913 | -122.7481 | LUCERNE 110638632 | 111 | 299 | 20944.6858 | 7546.5249 | 13398.1608 | 7104.2847 | 12570.3829 | 0.0056934 | 0.004646 | 1.9986 | 4.6182 | 1838 | 0.0879 | 1408 | 0 | 0 | 4.4144 | 973 | 0
Sierra | 3016 | 3 | 3.9449 | 27 | 11.909 | 5 | 5.6241e-05 | 33.373 | 5.9431 | 24.4634 | 43.4238 | 0.25849 | 2.9912 | 25.6665 | 1.0314 | 0.0015963 | 0.00017918 | 0.11111 | 0.33125 | {CD565697-14B6-4AA0-954C-46CA84031737} | 152701107 | BELL 1107 | circuit_breaker | 38.9469 | -121.0915 | BELL 1107circuit_breaker | 146 | 243 | 16925.0372 | 6178.772 | 10746.2652 | 198.4714 | 322.4944 | 0.00089591 | 0.00028121 | 1.315 | 5.4 | 1489 | 0.0079817 | 1409 | 0 | 0 | 0.12332 | 538 | 0
Central Coast | 689 | 752 | 1442.005 | 1418 | 1819.0173 | 81 | 0.00022391 | 6.8188 | 10.1214 | 23.5208 | 112.5997 | 2.1415 | 0.08967 | 3.6218 | 0.99047 | 0.0015912 | 0.0012164 | 0.53032 | 0.79274 | {9C7B2B92-FC22-48B4-B1A3-9DC57E45ACA3} | 83622105 | CAMP EVERS 2105 | 12590 | 37.0634 | -122.0799 | CAMP EVERS 210512590 | 131 | 465 | 30878.3126 | 8909.0232 | 21969.2893 | 7908.9298 | 18075.9252 | 0.098529 | 0.018136 | 1.9176 | 17.5062 | 317 | 0.12889 | 1410 | 0 | 0 | 4.9144 | 2263 | 0
Sierra | 2470 | 127 | 197.8568 | 328 | 289.3266 | 46 | 9.5532e-05 | 19.7609 | 8.8537 | 64.5414 | 334.9253 | 4.9626 | 0.64082 | 50.1616 | 1.1984 | 0.0015906 | 0.00046351 | 0.3872 | 0.68385 | {B86F1700-5A54-45AD-BE5A-60237D0F62CD} | 152691110 | HIGGINS 1110 | 51794 | 39.0441 | -121.0499 | HIGGINS 111051794 | 52 | 17 | 8096.5365 | 6260.8685 | 1835.668 | 6256.2965 | 1835.668 | 0.021321 | 0.0043945 | 1.5579 | 7.1304 | 841 | 0.073168 | 1411 | 0 | 0 | 3.8875 | 1505 | 0
North Coast | 2069 | 675 | 1062.213 | 1804 | 1641.2832 | 161 | 0.00010357 | 16.46 | 5.6579 | 49.3373 | 619.2414 | 14.1444 | 0.99985 | 14.1325 | 1.0828 | 0.0015892 | 0.00035773 | 0.37417 | 0.64718 | {76DCCACD-E9DC-40E0-8CEA-2EC1A63EA736} | 42091102 | MIRABEL 1102 | 38514 | 38.5056 | -122.9307 | MIRABEL 110238514 | 172 | 459 | 47110.8914 | 17032.4383 | 30078.4531 | 17032.4383 | 30078.4531 | 0.057595 | 0.016675 | 1.5736 | 11.205 | 1002 | 0.25586 | 1412 | 0 | 0 | 10.5835 | 127 | 0
Central Valley | 4462 | 47 | 68.8458 | 390 | 212.8505 | 39 | 8.9063e-05 | 17.1675 | 10.6412 | 31.0981 | 137.4759 | 2.3564 | 1.5361 | 19.9057 | 1.1061 | 0.0015741 | 0.00047091 | 0.12051 | 0.32345 | {07357E95-1494-460D-BB24-62F7136594F4} | 254432102 | COARSEGOLD 2102 | 5722 | 37.3156 | -119.6083 | COARSEGOLD 21025722 | 39 | 85 | 7441.1521 | 3182.9469 | 4258.2052 | 3182.9469 | 4258.2052 | 0.018365 | 0.0034735 | 1.4648 | 10 | 824 | 0.061392 | 1413 | 0 | 0 | 1.9778 | 1954 | 0
Sierra | 1746 | 300 | 401.0864 | 605 | 560.4235 | 46 | 9.5874e-05 | 15.5723 | 11.4559 | 101.7112 | 1080.6459 | 26.552 | 4.3621 | 33.5601 | 1.0452 | 0.0015536 | 0.00064089 | 0.49587 | 0.71568 | {53D34BC5-1233-4716-BDCB-367F4AA95C1A} | 152491102 | WEIMAR 1102 | 6175 | 39.0361 | -121.0041 | WEIMAR 11026175 | 49 | 72 | 8451.1655 | 4390.4905 | 4060.6749 | 4390.4905 | 4060.6749 | 0.029481 | 0.0044102 | 1.337 | 13.1522 | 627 | 0.071468 | 1414 | 0 | 0 | 2.7281 | 639 | 0
Central Valley | 3827 | 168 | 236.6854 | 396 | 351.6868 | 60 | 2.5491e-05 | 59.3816 | 5.2149 | 70.473 | 369.9556 | 5.3176 | 7.2054 | 109.1033 | 1.3845 | 0.00155 | 7.6342e-05 | 0.42424 | 0.673 | {3F7F0AF6-C0C2-4150-988F-57E9FF4DC9A3} | 254151101 | AUBERRY 1101 | 37536 | 37.059 | -119.3877 | AUBERRY 110137536 | 103 | 84 | 14936.3596 | 8826.9707 | 6109.3889 | 8826.9707 | 6109.3889 | 0.0045805 | 0.0015295 | 1.4088 | 6.6 | 2007 | 0.093 | 1415 | 0 | 0 | 5.4848 | 1874 | 0
Central Valley | 1117 | 231 | 312.9638 | 646 | 497.4519 | 72 | 9.8291e-05 | 14.704 | 48.5068 | 236.8174 | 2199.4918 | 220.1384 | 1.0887 | 30.1502 | 1.0692 | 0.0015461 | 0.0027313 | 0.35759 | 0.62913 | {7E08659E-39A5-4373-949B-319BDC171EA7} | 162161101 | ELECTRA 1101 | 36816 | 38.3603 | -120.7527 | ELECTRA 110136816 | 82 | 85 | 13326.8832 | 8016.99 | 5309.8931 | 8016.99 | 5309.8931 | 0.19666 | 0.0070769 | 1.3548 | 8.9722 | 117 | 0.11132 | 1416 | 0 | 0 | 4.9815 | 92 | 0
North Valley | 1060 | 525 | 724.3417 | 1114 | 1035.5627 | 196 | 1.2362e-05 | 148.5883 | 20.3114 | 930.1475 | 17976.1266 | 748.9317 | 3.1109 | 81.3286 | 1.1831 | 0.0015455 | 0.00013346 | 0.47127 | 0.69947 | {18489341-7942-4EE1-95D9-22D6837A669D} | 102812101 | BIG MEADOWS 2101 | 2260 | 40.1562 | -120.9431 | BIG MEADOWS 21012260 | 378 | 775 | 71231.4387 | 36189.8598 | 35041.5789 | 22959.7746 | 14018.6344 | 0.026158 | 0.0024229 | 1.3797 | 5.6837 | 1680 | 0.30293 | 1417 | 0 | 0 | 14.2665 | 2441 | 0
North Coast | 5073 | 1232 | 1757.3941 | 1700 | 1970.6499 | 179 | 0.0001583 | 9.4981 | 3.5173 | 278.5327 | 6084.8733 | 84.3838 | 0.93636 | 21.5933 | 1.0695 | 0.0015432 | 0.00044406 | 0.72471 | 0.89178 | {AF113D3A-C32B-4AE6-9683-F0B931A2BCC2} | 192401101 | HOOPA 1101 | 82542 | 41.058 | -123.6861 | HOOPA 110182542 | 214 | 288 | 36995.3836 | 24434.1618 | 12561.2219 | 18590.2459 | 4168.8744 | 0.079487 | 0.028335 | 1.4265 | 9.4972 | 874 | 0.27624 | 1418 | 0 | 0 | 11.5514 | 1576 | 0
Sierra | 9161 | 28 | 27.6587 | 48 | 39.5608 | 11 | 2.0051e-05 | 86.5518 | 22.7775 | 3660.7167 | 86659.6572 | 2643.7871 | 0.10459 | 38.8828 | 1.4716 | 0.0015403 | 0.00016104 | 0.58333 | 0.69914 | {4FA3034C-CC34-47A2-AF7A-8A1D1515E919} | 152321101 | DRUM 1101 | circuit_breaker | 39.2565 | -120.7668 | DRUM 1101circuit_breaker | 32 | 6 | 3516.2484 | 3389.5909 | 126.6575 | 3389.5909 | 126.6575 | 0.0017714 | 0.00022056 | 0.98781 | 4.3636 | 1543 | 0.016944 | 1419 | 0 | 0 | 2.1062 | 697 | 0
North Valley | 6696 | 312 | 613.3618 | 1960 | 1405.5013 | 273 | 2.5594e-05 | 64.9409 | 13.7871 | 1871.8185 | 43066.5832 | 1056.8314 | 0.24676 | 13.2375 | 1.0177 | 0.0015397 | 0.00014942 | 0.15918 | 0.4364 | {B0E99E01-0D27-4597-A594-1741A25A99A7} | 103031102 | ORO FINO 1102 | 38698 | 40.0376 | -121.6179 | ORO FINO 110238698 | 154 | 424 | 45718.6779 | 25102.3894 | 20616.2885 | 25102.3894 | 20616.2885 | 0.040791 | 0.0069871 | 1.9659 | 7.1795 | 1594 | 0.42033 | 1420 | 0 | 0 | 15.5979 | 889 | 0
North Coast | 1573 | 143 | 233.7391 | 297 | 320.0253 | 36 | 0.00010264 | 18.5643 | 3.412 | 2.5083 | 9.0707 | 0.18953 | 0.19998 | 0.45237 | 2.032 | 0.001531 | 0.00019996 | 0.48148 | 0.73038 | {DDE06CFF-C1C8-453E-9DCE-C51203C62E9C} | 43321104 | RINCON 1104 | circuit_breaker | 38.4899 | -122.6663 | RINCON 1104circuit_breaker | 194 | 442 | 28028.1891 | 9046.3288 | 18981.8603 | 4001.0684 | 7544.2171 | 0.0071987 | 0.0036952 | 1.6345 | 8.25 | 1412 | 0.055116 | 1421 | 0 | 0 | 2.4861 | 920 | 0
North Valley | 2546 | 452 | 747.3488 | 848 | 954.2561 | 124 | 0.00011537 | 20.9723 | 14.0457 | 609.1989 | 4313.5825 | 152.7089 | 2.9451 | 50.1667 | 0.98321 | 0.001527 | 0.00069069 | 0.53302 | 0.78317 | {60D04F67-B0A9-4BD6-8DCF-759CBE65FF11} | 102831104 | PARADISE 1104 | circuit_breaker | 39.7606 | -121.6189 | PARADISE 1104circuit_breaker | 750 | 468 | 89629.6454 | 59028.3032 | 30601.3422 | 47006.8323 | 30601.3422 | 0.085645 | 0.014306 | 1.6534 | 6.8387 | 575 | 0.18935 | 1422 | 0 | 0 | 29.2087 | 2383 | 0
North Valley | 9046 | 23 | 25.4799 | 28 | 27.6724 | 11 | 7.6993e-05 | 19.523 | 1.4611 | 4709.8705 | 117130.6309 | 179.7413 | 0 | 67.9788 | 1.2395 | 0.0015266 | 8.4643e-05 | 0.82143 | 0.92077 | {1BEC31F5-3F54-4C7C-921A-7E6673591BD6} | 101321101 | PIT NO 5 1101 | 1614 | 40.9971 | -121.9654 | PIT NO 5 11011614 | 7 | 1 | 3006.5072 | 3000.4112 | 6.096 | 3000.4112 | 6.096 | 0.00093107 | 0.00084692 | 1.1078 | 2.5455 | 1956 | 0.016792 | 1423 | 0 | 0 | 1.8644 | 2352 | 0
Central Valley | 7072 | 90 | 153.5427 | 309 | 247.7979 | 41 | 5.0625e-05 | 40.3157 | 1.1103 | 17.7501 | 72.4807 | 0.27067 | 2.1389 | 192.7235 | 1.2169 | 0.0015252 | 4.4349e-05 | 0.29126 | 0.61963 | {12C9081C-95BF-4D8B-9422-8F9EBEEF2908} | 163341103 | CLAY 1103 | circuit_breaker | 38.3422 | -120.9347 | CLAY 1103circuit_breaker | 168 | 85 | 31649.8516 | 21666.9014 | 9982.9502 | 9300.035 | 1397.5644 | 0.0018183 | 0.0020756 | 1.706 | 7.5366 | 2288 | 0.062535 | 1424 | 0 | 0 | 5.7788 | 925 | 0
Central Coast | 4597 | 7 | 8.7222 | 19 | 15.5703 | 8 | 3.0556e-05 | 49.6129 | 24.8548 | 2715.0147 | 14808.5847 | 478.1219 | 4.0354 | 368.4348 | 1.1825 | 0.0015233 | 0.00053753 | 0.36842 | 0.56018 | {D1A948DB-B3D6-469B-ACB6-5B79CAB78401} | 182551102 | CAYUCOS 1102 | W18 | 35.4245 | -120.8785 | CAYUCOS 1102W18 | 399 | 2424 | 129020.9626 | 36681.1721 | 92339.7905 | 3816.311 | 1467.0553 | 0.0043002 | 0.00024445 | 1.246 | 2.375 | 749 | 0.012187 | 1425 | 0 | 0 | 2.3713 | 2517 | 0
Sierra | 7202 | 545 | 744.4439 | 830 | 898.2914 | 74 | 0.00014012 | 10.3471 | 91.0044 | 2889.2259 | 39903.6033 | 4908.7724 | 2.2197 | 49.0844 | 1.0654 | 0.0015217 | 0.0063288 | 0.65663 | 0.82873 | {A7973262-E6C4-49FC-ACE4-AD992FBBA2FC} | 152471101 | COLUMBIA HILL 1101 | 8233 | 39.3421 | -121.0616 | COLUMBIA HILL 11018233 | 68 | 58 | 13449.8419 | 8056.6943 | 5393.1476 | 8056.6943 | 5393.1476 | 0.46833 | 0.010369 | 1.366 | 11.2162 | 27 | 0.11261 | 1426 | 0 | 0 | 5.0062 | 185 | 0
Central Coast | 7358 | 1498 | 3142.9821 | 1784 | 3302.6282 | 99 | 7.9978e-05 | 18.0882 | 2.6902 | 74.8093 | 500.5629 | 1.8704 | 0.93839 | 29.8526 | 1.0324 | 0.0015186 | 0.00014311 | 0.83969 | 0.95166 | {6B3803C4-78D9-4845-848A-F16561C51AFC} | 82931101 | POINT MORETTI 1101 | 36514 | 37.0393 | -122.1518 | POINT MORETTI 110136514 | 88 | 57 | 15762.9086 | 10964.1377 | 4798.7709 | 10964.1377 | 4798.7709 | 0.014168 | 0.0079178 | 2.0981 | 18.0202 | 1623 | 0.15034 | 1427 | 0 | 0 | 6.8128 | 1877 | 0
Bay Area | 491 | 292 | 602.8622 | 925 | 952.0414 | 59 | 8.2921e-05 | 17.3877 | 4.0779 | 5.8489 | 66.0535 | 2.901 | 0.19856 | 1.105 | 1.2932 | 0.0015179 | 0.0002154 | 0.31568 | 0.63323 | {792237E5-EE75-4319-AAE8-4FDB93CD8345} | 42031122 | ALTO 1122 | 78672 | 37.9249 | -122.5212 | ALTO 112278672 | 260 | 1330 | 70030.8212 | 13243.554 | 56787.2671 | 5142.0354 | 21599.6061 | 0.012709 | 0.0048923 | 2.0646 | 15.678 | 1359 | 0.089559 | 1428 | 0 | 0 | 3.1951 | 2079 | 0
North Valley | 3043 | 398 | 609.4255 | 1115 | 967.3457 | 151 | 0.00013003 | 13.6108 | 5.002 | 182.8119 | 1552.1357 | 39.0933 | 1.494 | 33.0138 | 1.0768 | 0.0015116 | 0.00039855 | 0.35695 | 0.63 | {68FC6E44-EFD8-4B52-B283-8EF4B688F460} | 102041104 | NOTRE DAME 1104 | 2028 | 39.8391 | -121.7018 | NOTRE DAME 11042028 | 102 | 92 | 25354.0465 | 17363.4694 | 7990.5771 | 17363.4694 | 7990.5771 | 0.06018 | 0.019634 | 1.5312 | 7.3841 | 945 | 0.22824 | 1429 | 0 | 0 | 10.7892 | 2549 | 0
Central Coast | 5393 | 192 | 384.101 | 1157 | 968.4528 | 202 | 2.1319e-05 | 80.4004 | 0.88087 | 303.5188 | 1401.1923 | 3.408 | 2.124 | 162.189 | 1.1281 | 0.0015089 | 1.8889e-05 | 0.16595 | 0.39661 | {9CBEE47E-1598-4921-97C7-5CC747F89863} | 183041101 | BUELLTON 1101 | Y36 | 34.6026 | -120.1931 | BUELLTON 1101Y36 | 333 | 294 | 100634.9865 | 72977.0065 | 27657.98 | 59828.4788 | 20717.4648 | 0.0038155 | 0.0043064 | 2.0005 | 5.7277 | 2635 | 0.30479 | 1430 | 0 | 0 | 37.1757 | 1876 | 0
Bay Area | 9976 | 0 | 0 | 4 | 1.8229 | 1 | 6.1475e-05 | 24.5194 | 9.5952 | 717.6671 | 7354.6841 | 70.5695 | 0.25664 | 157.1066 | 1.635 | 0.0015073 | 0.00058986 | 0 | 0 | {D9246407-D8E8-4A85-808E-1B1964384F7E} | 43150241 | TOCALOMA 0241 | circuit_breaker | 38.055 | -122.7608 | TOCALOMA 0241circuit_breaker | 1 | 1 | 62.9054 | 26.5151 | 36.3903 | 26.5151 | 36.3903 | 0.00058986 | 6.1475e-05 |  | 4 | 682 | 0.0015073 | 1431 | 0 | 0 | 0.016476 | 264 | 0
North Valley | 7469 | 7 | 9.1637 | 106 | 53.4686 | 22 | 1.4444e-05 | 84.6004 | 0.86808 | 3.6128 | 13.7155 | 0.037031 | 3.0859 | 44.9137 | 1.0046 | 0.0015057 | 1.5021e-05 | 0.066038 | 0.17138 | {8AC91F5C-D86E-4B8D-B342-7C652EFA0FA1} | 103721101 | PIT NO 1 1101 | 70952 | 41.004 | -121.4472 | PIT NO 1 110170952 | 58 | 144 | 7342.9956 | 2749.7949 | 4593.2007 | 2745.2229 | 4593.2007 | 0.00033046 | 0.00031776 | 1.3091 | 4.8182 | 2705 | 0.033125 | 1432 | 0 | 0 | 1.7058 | 1159 | 0
North Coast | 3774 | 646 | 986.9258 | 1089 | 1190.1106 | 95 | 0.00021032 | 7.0693 | 11.1039 | 299.2562 | 6600.9323 | 232.6749 | 0.94984 | 12.3623 | 1.1878 | 0.0015045 | 0.0011433 | 0.5932 | 0.82927 | {DF7E4408-5549-4590-B379-A48092E06D58} | 192401101 | HOOPA 1101 | 7468 | 41.0515 | -123.6752 | HOOPA 11017468 | 259 | 414 | 28561.5576 | 19602.473 | 8959.0846 | 10422.5231 | 4203.3066 | 0.10861 | 0.01998 | 1.5277 | 11.4632 | 346 | 0.14293 | 1433 | 0 | 0 | 6.4763 | 754 | 0
Central Coast | 6546 | 21 | 27.8299 | 27 | 30.5643 | 8 | 2.2847e-05 | 82.5869 | 0.16344 | 40.5334 | 91.06 | 0.029529 | 2.9585 | 290.7874 | 1.2616 | 0.0015044 | 9.5725e-06 | 0.77778 | 0.91054 | {97FCD4F4-D4FA-4E54-B458-40505BE0F481} | 182492102 | HOLLISTER 2102 | 4780 | 36.9425 | -121.4435 | HOLLISTER 21024780 | 212 | 270 | 44286.8616 | 24176.1189 | 20110.7427 | 2943.6622 | 306.201 | 7.658e-05 | 0.00018278 | 1.3252 | 3.375 | 2794 | 0.012035 | 1434 | 0 | 0 | 1.8291 | 1184 | 0
Central Valley | 47 | 251 | 384.8813 | 1144 | 744.2446 | 202 | 4.1259e-05 | 39.7668 | 16.8431 | 376.3516 | 3708.671 | 174.6371 | 4.3015 | 126.33 | 1.334 | 0.0014936 | 0.00029795 | 0.21941 | 0.51714 | {5F6C2DBD-A6A7-42E4-BABA-B899CFDCE0DB} | 254452101 | MARIPOSA 2101 | 35244 | 37.4927 | -119.9657 | MARIPOSA 210135244 | 176 | 167 | 42550.923 | 27730.4872 | 14820.4358 | 27730.4872 | 14820.4358 | 0.060186 | 0.0083344 | 1.5334 | 5.6634 | 1131 | 0.30172 | 1435 | 0 | 0 | 17.2309 | 1282 | 0
Sierra | 2020 | 593 | 956.0837 | 2717 | 1818.8671 | 325 | 7.3271e-05 | 24.6864 | 21.221 | 344.9399 | 2787.0037 | 101.3913 | 4.3132 | 63.0781 | 1.1128 | 0.0014826 | 0.00073778 | 0.21826 | 0.52565 | {AE69F8EF-4AC2-40EB-85B9-DBE37E3684F9} | 153652109 | SHINGLE SPRINGS 2109 | 11092 | 38.7741 | -120.9201 | SHINGLE SPRINGS 210911092 | 343 | 320 | 57879.5459 | 36166.6657 | 21712.8802 | 36166.6657 | 21712.8802 | 0.23978 | 0.023813 | 1.6123 | 8.36 | 541 | 0.48185 | 1436 | 0 | 0 | 22.4729 | 169 | 0
Central Coast | 1673 | 5 | 5.9197 | 28 | 16.8497 | 6 | 2.8479e-05 | 115.5704 | 9.8225 | 19.9684 | 65.926 | 1.7882 | 3.3547 | 77.6734 | 1.1154 | 0.0014806 | 0.00012951 | 0.17857 | 0.35132 | {7FC31E1C-DBD5-4F97-9DB8-E6AAAE06E52A} | 182631105 | SAN LUIS OBISPO 1105 | 796050 | 35.2724 | -120.6446 | SAN LUIS OBISPO 1105796050 | 188 | 793 | 39675.2323 | 7961.3272 | 31713.9051 | 2135.0041 | 6588.3773 | 0.00077708 | 0.00017088 | 1.1839 | 4.6667 | 1703 | 0.0088838 | 1437 | 0 | 0 | 1.3266 | 237 | 0
North Coast | 4695 | 897 | 1478.5114 | 1663 | 1920.4622 | 186 | 8.286e-05 | 20.161 | 5.4828 | 30.4521 | 143.1562 | 2.209 | 2.074 | 21.6868 | 1.1322 | 0.001475 | 0.00027046 | 0.53939 | 0.76987 | {D3082F6C-C528-49AC-BBCA-64C476BB2FE2} | 42151104 | SANTA ROSA A 1104 | 642 | 38.5039 | -122.6866 | SANTA ROSA A 1104642 | 308 | 287 | 38902.8686 | 21539.3089 | 17363.5597 | 21539.3089 | 17363.5597 | 0.050305 | 0.015412 | 1.6483 | 8.9409 | 1203 | 0.27435 | 1438 | 0 | 0 | 13.3839 | 624 | 0
Central Coast | 8737 | 43 | 68.6179 | 87 | 79.7778 | 34 | 2.9183e-05 | 49.1002 | 1.2775 | 806.8025 | 5048.678 | 17.2948 | 6.0006 | 1216.9892 | 1.6314 | 0.0014654 | 3.2095e-05 | 0.49425 | 0.86011 | {A0B1EC87-107D-4315-9E85-F1BAB9E02281} | 182562102 | CHOLAME 2102 | 5597 | 35.9123 | -120.4394 | CHOLAME 21025597 | 22 | 20 | 9173.0617 | 8229.9238 | 943.1379 | 8229.9238 | 943.1379 | 0.0010912 | 0.00099224 | 1.5958 | 2.5588 | 2440 | 0.049822 | 1439 | 0 | 0 | 5.1138 | 1794 | 0
Central Valley | 5394 | 452 | 634.6356 | 1427 | 1051.1106 | 133 | 5.4073e-05 | 29.7766 | 22.4507 | 168.5863 | 1354.9197 | 122.5112 | 3.391 | 39.1195 | 1.1626 | 0.0014651 | 0.00047305 | 0.31675 | 0.60378 | {54A77FF2-7A52-4D36-BA6B-B455CC7DC4A6} | 163351702 | CURTIS 1702 | 9220 | 37.9795 | -120.2763 | CURTIS 17029220 | 204 | 170 | 28625.8599 | 17957.7628 | 10668.0971 | 17305.2505 | 10611.1376 | 0.062915 | 0.0071918 | 1.4041 | 10.7293 | 819 | 0.19485 | 1440 | 0 | 0 | 10.753 | 1632 | 0
North Valley | 5590 | 104 | 180.167 | 482 | 345.0048 | 59 | 4.4347e-05 | 48.7617 | 17.8254 | 674.2973 | 4586.9762 | 205.5249 | 4.235 | 131.8533 | 1.2142 | 0.0014605 | 0.00031585 | 0.21577 | 0.52222 | {DBD4B653-AFBF-40EB-8724-1790AF913C8C} | 103091102 | CLARK ROAD 1102 | 2070 | 39.6565 | -121.5762 | CLARK ROAD 11022070 | 116 | 55 | 20642.2086 | 17647.3936 | 2994.8149 | 15820.4099 | 2982.6229 | 0.018635 | 0.0026165 | 1.7324 | 8.1695 | 1090 | 0.086172 | 1441 | 0 | 0 | 9.8303 | 1193 | 0
Bay Area | 8829 | 9 | 33.6089 | 18 | 36.4989 | 7 | 1.7371e-05 | 95.5745 | 2.8197 | 9.563 | 19.7961 | 0.16294 | 9.8094 | 130.9805 | 1.0487 | 0.0014576 | 2.3999e-05 | 0.5 | 0.92082 | {5E4EB8F1-F20C-4A10-9616-09E586C03349} | 14502107 | VINEYARD 2107 | MR332 | 37.6659 | -121.8416 | VINEYARD 2107MR332 | 72 | 20 | 6038.8453 | 5273.2666 | 765.5787 | 460.8485 | 25.0266 | 0.00016799 | 0.0001216 | 3.7343 | 2.5714 | 2543 | 0.010203 | 1442 | 0 | 0 | 0.28636 | 2846 | 0
Sierra | 2461 | 975 | 1192.1604 | 3141 | 2120.4192 | 254 | 0.00011646 | 13.0781 | 10.6885 | 93.8857 | 1410.6944 | 48.6323 | 0.3672 | 9.3587 | 1.1224 | 0.0014541 | 0.0007005 | 0.31041 | 0.56223 | {9026688D-0DDE-43F9-BDC1-1D8B37EA23F4} | 152762101 | EL DORADO PH 2101 | circuit_breaker | 38.7935 | -120.6195 | EL DORADO PH 2101circuit_breaker | 326 | 590 | 57521.0022 | 26755.9987 | 30765.0035 | 26755.9987 | 30765.0035 | 0.17793 | 0.029581 | 1.2227 | 12.3661 | 567 | 0.36934 | 1443 | 0 | 0 | 16.6254 | 593 | 0
Central Coast | 7116 | 1 | 1.2277 | 3 | 2.3632 | 2 | 2.8704e-05 | 50.4982 | 0.17824 | 30.915 | 98.8224 | 0.035225 | 1.6991 | 344.3721 | 1.8385 | 0.0014493 | 5.1639e-06 | 0.33333 | 0.51951 | {68615336-79DC-4EC6-9727-806E7A643D26} | 183031101 | PALMER 1101 | 98478 | 34.7403 | -120.2269 | PALMER 110198478 | 41 | 18 | 8897.6588 | 7936.2417 | 961.4171 | 7555.738 | 579.3179 | 1.0328e-05 | 5.7409e-05 | 1.2277 | 1.5 | 2842 | 0.0028986 | 1444 | 0 | 0 | 4.6949 | 301 | 0
Bay Area | 8158 | 531 | 860.2449 | 1446 | 1422.4518 | 133 | 4.3165e-05 | 31.4371 | 1.3807 | 83.0253 | 731.5768 | 3.8651 | 0.96061 | 42.8947 | 1.1246 | 0.0014487 | 4.3865e-05 | 0.36722 | 0.60476 | {8A15255F-3865-4264-A6D3-8F9EE2AA73EF} | 24131103 | MENLO 1103 | 7902 | 37.3835 | -122.1662 | MENLO 11037902 | 257 | 116 | 32534.5685 | 26240.481 | 6294.0875 | 18489.6466 | 2556.5641 | 0.005834 | 0.005741 | 1.62 | 10.8722 | 2291 | 0.19267 | 1445 | 0 | 0 | 11.4889 | 2715 | 0
Central Valley | 4787 | 477 | 648.3556 | 2023 | 1339.8207 | 167 | 9.0743e-05 | 16.4381 | 54.7916 | 369.8156 | 5400.6766 | 686.3493 | 1.5781 | 17.9313 | 1.0731 | 0.0014339 | 0.002416 | 0.23579 | 0.48391 | {29253623-89FE-435D-961C-4E4487404246} | 163751102 | PINE GROVE 1102 | circuit_breaker | 38.4126 | -120.6604 | PINE GROVE 1102circuit_breaker | 249 | 328 | 34183.2668 | 17217.3979 | 16965.8689 | 17217.3979 | 16965.8689 | 0.40348 | 0.015154 | 1.3592 | 12.1138 | 134 | 0.23946 | 1446 | 0 | 0 | 10.6984 | 1270 | 0
Central Valley | 3556 | 10 | 13.8425 | 155 | 62.9836 | 32 | 5.954e-05 | 27.2195 | 15.4531 | 152.7094 | 539.9778 | 13.02 | 5.1611 | 138.2626 | 1.2137 | 0.0014337 | 0.00054806 | 0.064516 | 0.21978 | {646B02DA-833B-4BEB-8A59-9FDCAF947841} | 163451702 | FROGTOWN 1702 | circuit_breaker | 38.0569 | -120.5339 | FROGTOWN 1702circuit_breaker | 166 | 214 | 15864.3796 | 8323.2793 | 7541.1002 | 4274.7494 | 737.4345 | 0.017538 | 0.0019053 | 1.3843 | 4.8438 | 740 | 0.045877 | 1447 | 0 | 0 | 2.6562 | 1435 | 0
Central Valley | 5011 | 116 | 166.3391 | 299 | 245.3031 | 63 | 1.5449e-05 | 97.3397 | 17.8056 | 826.5046 | 6856.1203 | 165.2222 | 9.5282 | 536.7015 | 1.7083 | 0.0014312 | 0.00011339 | 0.38796 | 0.6781 | {81D716EF-AF38-46F5-8FD2-48383247DE01} | 254061102 | DUNLAP 1102 | 7360 | 36.6765 | -119.0165 | DUNLAP 11027360 | 115 | 81 | 19844.8704 | 13675.786 | 6169.0845 | 13675.786 | 6169.0845 | 0.0071436 | 0.00097328 | 1.434 | 4.746 | 1784 | 0.090166 | 1448 | 0 | 0 | 8.4977 | 79 | 0
Sierra | 6623 | 162 | 220.6706 | 493 | 363.9356 | 85 | 1.7302e-05 | 82.0498 | 1.5039 | 120.088 | 1852.5631 | 8.3187 | 0.13136 | 24.4265 | 1.1276 | 0.0014292 | 2.1886e-05 | 0.3286 | 0.60635 | {EE38B856-B2BC-49D4-8C11-7E26D08321B4} | 152762101 | EL DORADO PH 2101 | 13532 | 38.7731 | -120.2934 | EL DORADO PH 210113532 | 62 | 192 | 14064.4785 | 8511.6067 | 5552.8718 | 8511.6067 | 5552.8718 | 0.0018603 | 0.0014707 | 1.3622 | 5.8 | 2578 | 0.12148 | 1449 | 0 | 0 | 5.2889 | 422 | 0
Central Valley | 4699 | 795 | 1085.0151 | 3171 | 2231.188 | 202 | 9.5763e-05 | 15.366 | 55.3343 | 458.18 | 5938.8528 | 723.9146 | 1.3592 | 23.1351 | 1.1561 | 0.0014285 | 0.0026937 | 0.25071 | 0.48629 | {21E26CE5-9BFF-45A6-8272-2A9D442E9691} | 162161101 | ELECTRA 1101 | 7104 | 38.3637 | -120.6466 | ELECTRA 11017104 | 276 | 418 | 40947.6446 | 19862.8394 | 21084.8052 | 19862.8394 | 21084.8052 | 0.54412 | 0.019344 | 1.3648 | 15.698 | 118 | 0.28856 | 1450 | 0 | 0 | 12.3422 | 1273 | 0
Central Valley | 9129 | 36 | 81.5788 | 253 | 205.3352 | 65 | 2.7284e-05 | 51.6658 | 8.1493 | 1320.7822 | 31603.4566 | 715.738 | 0.31617 | 50.8939 | 1.1898 | 0.0014274 | 0.00011744 | 0.14229 | 0.3973 | {64CDB5CA-B54E-4043-BB09-802AFEE142DC} | 162831702 |  | circuit_breaker | 38.1865 | -120.1118 | circuit_breaker | 36 | 17 | 12530.3694 | 11948.6238 | 581.7455 | 11948.6238 | 581.7455 | 0.0076333 | 0.0017735 | 2.2661 | 3.8923 | 1758 | 0.092782 | 1451 | 0 | 0 | 7.4245 | 2648 | 0
Central Coast | 325 | 30 | 90.23 | 630 | 319.5542 | 45 | 1.5446e-05 | 68.1506 | 1.2633 | 261.6671 | 1351.1001 | 2.9926 | 4.9071 | 741.8926 | 1.3773 | 0.001427 | 1.9954e-05 | 0.047619 | 0.28236 | {C61DB78B-3364-4B90-90AD-4E89668B63A7} | 182821101 | MESA 1101 | circuit_breaker | 35.0077 | -120.4542 | MESA 1101circuit_breaker | 399 | 750 | 82508.3813 | 41442.2698 | 41066.1115 | 18758.3645 | 9023.5944 | 0.00089794 | 0.00069506 | 3.0077 | 14 | 2609 | 0.064216 | 1452 | 0 | 0 | 11.6559 | 1218 | 0
North Coast | 5744 | 131 | 193.4261 | 242 | 257.1961 | 12 | 0.0001007 | 13.9537 | 5.3443 | 3.453 | 12.2833 | 0.15106 | 0.15185 | 0.42723 | 1.0031 | 0.0014263 | 0.00038464 | 0.54132 | 0.75206 | {7A325237-8BF6-4A6F-9F21-89C867E6F89A} | 42151104 | SANTA ROSA A 1104 | 64565 | 38.4716 | -122.6831 | SANTA ROSA A 110464565 | 24 | 55 | 4272.6876 | 1301.8977 | 2970.7899 | 1301.8977 | 2970.7899 | 0.0046157 | 0.0012084 | 1.4765 | 20.1667 | 960 | 0.017116 | 1453 | 0 | 0 | 0.80896 | 1154 | 0
Sierra | 4033 | 1620 | 2401.4749 | 4062 | 3507.6733 | 372 | 0.00012683 | 15.758 | 119.035 | 1626.7303 | 21899.889 | 4987.0529 | 3.3537 | 45.199 | 1.118 | 0.0014248 | 0.007874 | 0.39882 | 0.68463 | {DBDF15C5-1C5A-46A1-9C80-FCF08A12927F} | 152481104 | BRUNSWICK 1104 | 1020 | 39.2471 | -121.0378 | BRUNSWICK 11041020 | 487 | 447 | 72647.5417 | 46114.191 | 26533.3507 | 46114.191 | 26533.3507 | 2.9291 | 0.047182 | 1.4824 | 10.9194 | 18 | 0.53002 | 1454 | 0 | 0 | 28.654 | 905 | 0
Central Valley | 1362 | 462 | 667.6762 | 1695 | 1278.3511 | 98 | 4.7363e-05 | 31.3776 | 224.2812 | 1448.2997 | 24101.5304 | 9041.0656 | 2.239 | 28.5031 | 1.1551 | 0.0014248 | 0.004681 | 0.27257 | 0.52229 | {B18F77BC-A9DA-4B29-AB14-C0D1FCA97447} | 163661701 | MIWUK 1701 | 93062 | 38.0212 | -120.222 | MIWUK 170193062 | 138 | 192 | 26095.1635 | 13308.2221 | 12786.9414 | 13308.2221 | 12786.9414 | 0.45873 | 0.0046416 | 1.4452 | 17.2959 | 40 | 0.13963 | 1455 | 0 | 0 | 8.2693 | 1351 | 0
Sierra | 578 | 1546 | 2002.6339 | 6020 | 3984.417 | 397 | 0.00011105 | 14.9854 | 74.9557 | 702.5297 | 13919.1349 | 6208.6194 | 0.47228 | 10.9403 | 1.0346 | 0.0014208 | 0.0039252 | 0.25681 | 0.50262 | {550714A4-7303-4842-936D-572C7CE200C4} | 152762101 | EL DORADO PH 2101 | 6852 | 38.7612 | -120.5582 | EL DORADO PH 21016852 | 577 | 1140 | 95692.4307 | 40526.8318 | 55165.5989 | 40526.8318 | 55165.5989 | 1.5583 | 0.044086 | 1.2954 | 15.1637 | 62 | 0.56407 | 1456 | 0 | 0 | 25.1822 | 477 | 0
Central Valley | 578 | 0 | 0 | 7 | 3.569 | 1 | 0.00013564 | 0.066431 |  |  |  |  | 0 | 0.09469 | 1 | 9.0108e-06 | 0.00013564 | 0 | 0 | {550714A4-7303-4842-936D-572C7CE200C4} | 152762101 | EL DORADO PH 2101 | 6852 | 38.7612 | -120.5582 | EL DORADO PH 21016852 | 577 | 1140 | 95692.4307 | 40526.8318 | 55165.5989 | 40526.8318 | 55165.5989 | 0.00013564 | 0.00013564 |  | 7 | 1661 | 9.0108e-06 | 1456 | 0 | 0 | 25.1822 | 1343 | 0
North Coast | 6809 | 170 | 334.7622 | 266 | 386.0106 | 17 | 0.00012111 | 16.8503 | 12.838 | 42.6774 | 337.013 | 7.3073 | 0.98425 | 22.0815 | 1.1054 | 0.0014163 | 0.00083602 | 0.6391 | 0.86724 | {BD415B0D-9627-498A-917B-E8CC6D68ECA3} | 42811113 | MONTE RIO 1113 | 8299 | 38.5034 | -123.0284 | MONTE RIO 11138299 | 24 | 70 | 5686.3782 | 1927.3515 | 3759.0267 | 1927.3515 | 3759.0267 | 0.014212 | 0.0020588 | 1.9692 | 15.6471 | 482 | 0.024077 | 1457 | 0 | 0 | 1.1976 | 1550 | 0
Sierra | 2592 | 687 | 860.6496 | 1197 | 1111.3392 | 60 | 0.00010847 | 13.542 | 16.1987 | 126.4684 | 1595.1239 | 58.7954 | 0.83603 | 12.4076 | 1.013 | 0.0014148 | 0.00074286 | 0.57393 | 0.77443 | {7677B076-AE2A-476E-8765-2A5E3BB73FF1} | 153661104 | APPLE HILL 1104 | 12947 | 38.7515 | -120.693 | APPLE HILL 110412947 | 77 | 96 | 11948.009 | 5562.8913 | 6385.1177 | 5562.8913 | 6385.1177 | 0.044572 | 0.006508 | 1.2528 | 19.95 | 537 | 0.084889 | 1458 | 0 | 0 | 3.4566 | 1514 | 0
North Coast | 3473 | 62 | 79.1115 | 250 | 181.2736 | 28 | 8.0653e-05 | 17.9296 | 5.7866 | 98.9109 | 1040.4065 | 41.7342 | 1.8329 | 33.2747 | 1.0262 | 0.0014147 | 0.00022201 | 0.248 | 0.43642 | {587017B7-CF95-40B8-A31E-326EDAB4E012} | 43071103 | DUNBAR 1103 | circuit_breaker | 38.3834 | -122.528 | DUNBAR 1103circuit_breaker | 249 | 305 | 32998.968 | 19663.038 | 13335.93 | 3351.8236 | 2239.2224 | 0.0062162 | 0.0022583 | 1.276 | 8.9286 | 1336 | 0.039611 | 1459 | 0 | 0 | 2.0827 | 1485 | 0
Central Valley | 2139 | 0 | 0 | 24 | 5.3355 | 7 | 1.4468e-05 | 99.2442 | 21.2506 | 1007.2251 | 2808.7225 | 52.1459 | 5.9106 | 136.356 | 1.0664 | 0.0014049 | 0.00021817 | 0 | 0 | {CFC21754-99CF-4E36-A5A0-12F128F562A8} | 252811102 | MERCED FALLS 1102 | 22774 | 37.5883 | -120.2764 | MERCED FALLS 110222774 | 35 | 31 | 6578.4576 | 5970.2453 | 608.2123 | 1272.8669 | 169.6124 | 0.0015272 | 0.00010127 |  | 3.4286 | 1349 | 0.0098346 | 1460 | 0 | 0 | 0.79092 | 1278 | 0
Central Valley | 7643 | 171 | 228.1186 | 385 | 337.1184 | 55 | 0.00011048 | 13.8945 | 6.4751 | 72.2785 | 552.1181 | 8.1838 | 2.4044 | 23.6562 | 1.1228 | 0.0014042 | 0.00040302 | 0.44416 | 0.67667 | {04FAB232-49CB-424E-BFDC-D01D068BCF02} | 254432102 | COARSEGOLD 2102 | 10207 | 37.2984 | -119.6165 | COARSEGOLD 210210207 | 48 | 41 | 8330.1103 | 5760.3678 | 2569.7425 | 5760.3678 | 2569.7425 | 0.022166 | 0.0060762 | 1.334 | 7 | 942 | 0.07723 | 1461 | 0 | 0 | 3.5793 | 1336 | 0
North Valley | 4253 | 641 | 1063.7772 | 1695 | 1522.4436 | 180 | 7.8987e-05 | 18.3202 | 53.0557 | 620.401 | 11297.0197 | 2565.6708 | 1.2935 | 25.1358 | 1.0635 | 0.0013948 | 0.0024483 | 0.37817 | 0.69873 | {A1D13A32-B522-454E-9EB3-1DBA73C91901} | 103521102 | OREGON TRAIL 1102 | 1584 | 40.6653 | -122.3867 | OREGON TRAIL 11021584 | 198 | 286 | 34912.9317 | 20999.2286 | 13913.7031 | 20999.2286 | 13913.7031 | 0.4407 | 0.014218 | 1.6596 | 9.4167 | 130 | 0.25106 | 1462 | 0 | 0 | 13.0483 | 672 | 0
Central Valley | 6260 | 1004 | 1412.6036 | 4115 | 2857.0337 | 526 | 9.0249e-05 | 15.9651 | 19.515 | 727.1967 | 7653.4835 | 328.019 | 2.7731 | 83.0653 | 1.2773 | 0.0013928 | 0.0009302 | 0.24399 | 0.49443 | {B48DDE03-609C-4554-A3F2-3D029A190740} | 163751102 | PINE GROVE 1102 | 6080 | 38.4615 | -120.6577 | PINE GROVE 11026080 | 413 | 312 | 86369.7127 | 56095.9807 | 30273.7319 | 56095.9807 | 30273.7319 | 0.48928 | 0.047471 | 1.407 | 7.8232 | 438 | 0.73263 | 1463 | 0 | 0 | 34.8564 | 1606 | 0
North Coast | 7683 | 412 | 568.5999 | 1037 | 926.825 | 128 | 7.7008e-05 | 17.555 | 6.6446 | 94.0032 | 728.5469 | 11.7174 | 2.6214 | 36.1533 | 1.0663 | 0.0013845 | 0.0002634 | 0.3973 | 0.61349 | {F8BEFC4B-3D6B-4BB7-B77D-7582CBA169BE} | 42151104 | SANTA ROSA A 1104 | 716 | 38.5043 | -122.6864 | SANTA ROSA A 1104716 | 170 | 94 | 20185.2974 | 14273.5878 | 5911.7096 | 14273.5878 | 5911.7096 | 0.033716 | 0.009857 | 1.3801 | 8.1016 | 1212 | 0.17721 | 1464 | 0 | 0 | 8.8692 | 2529 | 0
Central Valley | 8791 | 1 | 1.945 | 31 | 15.1291 | 7 | 4.2447e-05 | 27.6964 | 0 | 0 | 0 | 0 | 0.53951 | 92.5702 | 1.1514 | 0.0013712 | 3.1446e-05 | 0.032258 | 0.12856 | {D868AF66-93C2-4B3E-8187-2C428023C31E} | 163341102 | CLAY 1102 | circuit_breaker | 38.3423 | -120.9347 | CLAY 1102circuit_breaker | 37 | 5 | 3343.7829 | 3149.4821 | 194.3008 | 1255.8462 | 13.5503 | 0.00022012 | 0.00029713 | 1.945 | 4.4286 | 2449 | 0.0095983 | 1465 | 0 | 0 | 0.78035 | 424 | 0
North Coast | 2486 | 1714 | 2639.9331 | 2350 | 2950.449 | 229 | 7.8564e-05 | 17.776 | 2.3602 | 128.0383 | 619.5166 | 2.5846 | 1.2448 | 42.1048 | 1.0909 | 0.0013549 | 0.00012468 | 0.72936 | 0.89476 | {BC0A2CA4-638F-47ED-8CA5-834F5A792974} | 42601102 | PHILO 1102 | 920 | 39.0924 | -123.4814 | PHILO 1102920 | 328 | 242 | 61313.5338 | 41958.9354 | 19354.5984 | 26207.5142 | 12876.6647 | 0.028551 | 0.017991 | 1.5402 | 10.262 | 1727 | 0.31026 | 1466 | 0 | 0 | 16.2846 | 1131 | 0
North Coast | 574 | 100 | 218.2857 | 238 | 273.7185 | 35 | 5.9753e-05 | 24.5245 | 4.8706 | 47.6086 | 580.8557 | 22.8645 | 1.666 | 103.2398 | 1.109 | 0.0013549 | 0.00018044 | 0.42017 | 0.79748 | {DA9B8D37-5C46-437A-B55A-1CC1BE987A25} | 43351106 | LUCERNE 1106 | 47198 | 39.0936 | -122.7958 | LUCERNE 110647198 | 163 | 717 | 40903.9032 | 9365.4324 | 31538.4708 | 4671.7433 | 9758.2107 | 0.0063153 | 0.0020913 | 2.1829 | 6.8 | 1485 | 0.04742 | 1467 | 0 | 0 | 2.9029 | 1347 | 0
Central Coast | 8397 | 585 | 990.1451 | 1751 | 1670.1245 | 109 | 4.0047e-05 | 30.4379 | 1.9061 | 75.0698 | 1217.9216 | 28.8631 | 0.84481 | 32.0609 | 1.1691 | 0.0013459 | 6.0857e-05 | 0.33409 | 0.59286 | {CE315338-5526-427E-BFD9-C9F38F5865EC} | 83481110 | STELLING 1110 | 60080 | 37.3221 | -122.0795 | STELLING 111060080 | 87 | 36 | 20589.5298 | 16267.2425 | 4322.2873 | 15400.8729 | 4322.2873 | 0.0066334 | 0.0043651 | 1.6926 | 16.0642 | 2129 | 0.1467 | 1468 | 0 | 0 | 9.5697 | 670 | 0
North Valley | 6831 | 1761 | 2253.7851 | 2727 | 2782.258 | 254 | 0.00011614 | 11.9704 | 49.6528 | 2438.7353 | 43719.9887 | 3685.8416 | 1.372 | 39.2426 | 1.0681 | 0.0013413 | 0.0029979 | 0.64576 | 0.81006 | {25C4070D-0704-4FE8-B250-876F6C426225} | 103751101 | BIG BEND 1101 | circuit_breaker | 39.6771 | -121.4918 | BIG BEND 1101circuit_breaker | 224 | 178 | 51030.1458 | 35800.1144 | 15230.0314 | 35800.1144 | 15230.0314 | 0.76147 | 0.0295 | 1.2798 | 10.7362 | 107 | 0.34069 | 1469 | 0 | 0 | 22.2452 | 2502 | 0
Central Valley | 1561 | 90 | 197.5377 | 294 | 246.8157 | 54 | 6.0002e-05 | 26.0783 | 5.1236 | 14.9196 | 49.4519 | 0.93336 | 7.6325 | 43.5779 | 1.1115 | 0.0013387 | 0.00018142 | 0.30612 | 0.80034 | {A87A01D7-FDFF-4B8F-B41F-FAA11796C3AB} | 162991103 | CORRAL 1103 | 59770 | 38.1188 | -120.8616 | CORRAL 110359770 | 149 | 297 | 27913.6581 | 11687.7898 | 16225.8683 | 6842.3899 | 8186.6604 | 0.0097965 | 0.0032401 | 2.1949 | 5.4444 | 1483 | 0.072287 | 1470 | 0 | 0 | 4.2517 | 360 | 0
Bay Area | 2549 | 481 | 812.667 | 1269 | 1280.4651 | 117 | 3.1443e-05 | 40.5236 | 0.41809 | 27.8015 | 292.0788 | 0.74989 | 0.78477 | 34.3583 | 1.1376 | 0.0013173 | 2.5241e-05 | 0.37904 | 0.63467 | {581F1941-5575-42E1-A523-6A9EC3F9CF9A} | 24131103 | MENLO 1103 | 1721 | 37.3152 | -122.1879 | MENLO 11031721 | 58 | 46 | 17688.3933 | 10927.2973 | 6761.096 | 10927.2973 | 6761.096 | 0.0029532 | 0.0036789 | 1.6895 | 10.8462 | 2534 | 0.15412 | 1471 | 0 | 0 | 6.7899 | 559 | 0
Central Coast | 4538 | 23 | 51.05 | 82 | 83.2915 | 22 | 2.8897e-05 | 43.1397 | 5.1553 | 1492.2886 | 5273.6654 | 32.7955 | 6.0531 | 310.4794 | 1.3898 | 0.0013089 | 7.628e-05 | 0.28049 | 0.61291 | {13C66FE2-04FC-416E-B77A-7B686717A2B5} | 182971101 | PURISIMA 1101 | Y42 | 34.759 | -120.4018 | PURISIMA 1101Y42 | 158 | 134 | 33591.5653 | 26927.883 | 6663.6822 | 2254.0917 | 584.0634 | 0.0016782 | 0.00063573 | 2.2196 | 3.7273 | 2008 | 0.028796 | 1472 | 0 | 0 | 1.4006 | 271 | 0
Sierra | 6913 | 298 | 343.1271 | 775 | 560.892 | 65 | 4.2696e-05 | 32.2613 | 13.8191 | 1764.1153 | 58175.2274 | 1962.1519 | 1.0578 | 15.7719 | 1.056 | 0.0013081 | 0.00028172 | 0.38452 | 0.61175 | {C309DB72-5D9A-4AC9-886D-5F718B64DFF4} | 152101101 | ALLEGHANY 1101 | VR816 | 39.5572 | -120.8285 | ALLEGHANY 1101VR816 | 115 | 340 | 14972.6855 | 6679.2994 | 8293.386 | 6679.2994 | 8293.386 | 0.018312 | 0.0027753 | 1.1514 | 11.9231 | 1172 | 0.085027 | 1473 | 0 | 0 | 4.1503 | 276 | 0
Central Valley | 3408 | 798 | 1116.707 | 3035 | 2159.5024 | 230 | 4.9159e-05 | 35.0031 | 32.0633 | 462.6014 | 5353.5761 | 464.8314 | 3.6799 | 37.9856 | 1.2583 | 0.0013077 | 0.00071474 | 0.26293 | 0.51711 | {EC5957DB-4019-4BE8-BED9-1CDB082F6FD9} | 163351702 | CURTIS 1702 | 6008 | 38.0085 | -120.3034 | CURTIS 17026008 | 246 | 315 | 53229.4153 | 28195.182 | 25034.2333 | 28195.182 | 25034.2333 | 0.16439 | 0.011307 | 1.3994 | 13.1957 | 557 | 0.30077 | 1474 | 0 | 0 | 17.5197 | 1737 | 0
Bay Area | 7210 | 41 | 93.9213 | 64 | 106.6023 | 11 | 4.708e-05 | 28.2881 | 140.4787 | 570.2195 | 2685.175 | 377.2099 | 1.5907 | 25.5242 | 1.0066 | 0.0013055 | 0.00062747 | 0.64062 | 0.88104 | {F43D5D09-9904-4503-827D-15E6F8524BEA} | 14161106 | ROSSMOOR 1106 | 39424 | 37.8713 | -122.0963 | ROSSMOOR 110639424 | 82 | 254 | 16624.2612 | 3992.9225 | 12631.3387 | 1232.955 | 1514.5518 | 0.0069021 | 0.00051788 | 2.2908 | 5.8182 | 643 | 0.01436 | 1475 | 0 | 0 | 0.76612 | 2110 | 0
Central Valley | 8363 | 431 | 567.6107 | 837 | 732.9863 | 88 | 9.3926e-05 | 17.0955 | 16.1767 | 264.2518 | 1680.009 | 54.6388 | 3.811 | 58.3669 | 1.1274 | 0.0012968 | 0.00063935 | 0.51493 | 0.77438 | {97ACC61C-80B7-431D-B04B-B9076E222D13} | 163761703 | RACETRACK 1703 | 6014 | 38.0049 | -120.4064 | RACETRACK 17036014 | 107 | 145 | 20729.6692 | 11321.9024 | 9407.7669 | 11321.9024 | 9407.7669 | 0.056263 | 0.0082654 | 1.317 | 9.5114 | 629 | 0.11412 | 1476 | 0 | 0 | 7.0351 | 1563 | 0
Central Valley | 5890 | 15 | 22.8467 | 426 | 201.9708 | 41 | 4.8448e-05 | 23.2692 | 3.9285 | 28.9716 | 171.6156 | 0.36044 | 0.89737 | 9.239 | 1.0179 | 0.0012966 | 9.2445e-05 | 0.035211 | 0.11312 | {635F8134-C2A6-4C23-A242-6F5A1291D1C6} | 163692102 | SALT SPRINGS 2102 | 37300 | 38.3004 | -120.279 | SALT SPRINGS 210237300 | 79 | 75 | 20438.6005 | 11257.5171 | 9181.0834 | 11257.5171 | 9181.0834 | 0.0037902 | 0.0019863 | 1.5231 | 10.3902 | 1892 | 0.053159 | 1477 | 0 | 0 | 6.9951 | 1555 | 0
Central Valley | 2984 | 13 | 18.9662 | 142 | 77.0199 | 25 | 7.1422e-05 | 27.6622 | 9.1177 | 92.2702 | 1065.5801 | 30.3705 | 0.34044 | 13.5735 | 1.0182 | 0.0012963 | 0.00018607 | 0.091549 | 0.24625 | {63080617-6586-4F7A-B820-64DDE42B59AD} | 162821702 | STANISLAUS 1702 | 1888 | 38.2367 | -120.3628 | STANISLAUS 17021888 | 425 | 698 | 57798.7161 | 30461.9306 | 27336.7854 | 30461.9306 | 27336.7854 | 0.0046517 | 0.0017855 | 1.4589 | 5.68 | 1460 | 0.032406 | 1478 | 0 | 0 | 18.9282 | 931 | 0
Central Coast | 8296 | 5 | 6.1752 | 15 | 12.0402 | 7 | 1.921e-05 | 78.2719 | 19.508 | 103.0816 | 312.639 | 6.8393 | 15.6122 | 107.8421 | 1.1444 | 0.001295 | 0.00019913 | 0.33333 | 0.51288 | {29DF4083-4850-493D-A17C-7E1454C0761F} | 83432101 | HICKS 2101 | circuit_breaker | 37.2338 | -121.9007 | HICKS 2101circuit_breaker | 44 | 0 | 17493.6949 | 17493.6949 | 0 | 4105.0932 | 0 | 0.0013939 | 0.00013447 | 1.235 | 2.1429 | 1416 | 0.0090651 | 1479 | 0 | 0 | 2.5508 | 1900 | 0
Central Valley | 2953 | 198 | 305.1706 | 1031 | 664.063 | 117 | 7.7866e-05 | 12.7661 | 12.3922 | 226.3523 | 1971.0924 | 56.715 | 2.1024 | 38.3379 | 1.1154 | 0.0012912 | 0.00046639 | 0.19205 | 0.45955 | {542EB99D-D4C9-4D12-B28C-42F86055BDF5} | 163761703 | RACETRACK 1703 | 11270 | 38.022 | -120.4318 | RACETRACK 170311270 | 175 | 172 | 31879.4365 | 19572.4814 | 12306.9551 | 19572.4814 | 12306.9551 | 0.054567 | 0.0091103 | 1.5413 | 8.812 | 837 | 0.15107 | 1480 | 0 | 0 | 12.1618 | 2324 | 0
Central Coast | 2406 | 10 | 34.2315 | 16 | 36.6661 | 4 | 1.2671e-05 | 108.0574 | 0.01723 | 7.4016 | 18.6834 | 0.00072545 | 5.3247 | 150.3686 | 1.1283 | 0.0012883 | 4.9777e-06 | 0.625 | 0.9336 | {C6602F48-3A87-4830-B316-DED5C966EF46} | 182951102 | FOOTHILL 1102 | V06 | 35.2854 | -120.7014 | FOOTHILL 1102V06 | 131 | 566 | 34970.3514 | 10520.855 | 24449.4964 | 1798.9532 | 180.3113 | 1.9911e-05 | 5.0684e-05 | 3.4231 | 4 | 2845 | 0.0051532 | 1481 | 0 | 0 | 1.1178 | 1155 | 0
North Coast | 5720 | 210 | 344.5017 | 566 | 521.2114 | 79 | 6.5815e-05 | 16.0308 | 36.8434 | 586.2467 | 6196.3785 | 493.4129 | 3.1933 | 73.0205 | 1.0452 | 0.0012865 | 0.0011152 | 0.37102 | 0.66096 | {7B87BD32-83E4-4831-8C0E-079887A90817} | 42151111 | SANTA ROSA A 1111 | 114 | 38.4282 | -122.6766 | SANTA ROSA A 1111114 | 259 | 373 | 43288.8385 | 18440.8581 | 24847.9804 | 9582.7736 | 9804.7997 | 0.088104 | 0.0051994 | 1.6405 | 7.1646 | 356 | 0.10163 | 1482 | 0 | 0 | 5.9545 | 1229 | 0
Sierra | 3 | 105 | 183.164 | 477 | 347.7327 | 62 | 0.00010463 | 12.3369 | 6.0858 | 14.0092 | 43.546 | 0.60877 | 1.3171 | 10.7293 | 1.0034 | 0.0012861 | 0.00047538 | 0.22013 | 0.52674 | {D5E00AD4-7C48-4E87-BBB1-92F5DE277EEA} | 152691104 | HIGGINS 1104 | 498932 | 39.1181 | -121.0392 | HIGGINS 1104498932 | 116 | 169 | 17004.3437 | 6861.4641 | 10142.8797 | 5868.3896 | 8845.2382 | 0.029474 | 0.0064873 | 1.7444 | 7.6935 | 816 | 0.07974 | 1483 | 0 | 0 | 3.6464 | 1030 | 0
Central Coast | 2615 | 3374 | 5556.8201 | 6366 | 7318.3843 | 381 | 0.00011072 | 12.6743 | 7.0709 | 57.6826 | 558.0222 | 9.3036 | 1.2604 | 13.185 | 1.0642 | 0.0012848 | 0.00038822 | 0.53 | 0.7593 | {498D8DB9-5CC7-45E0-BE16-B8DB75429782} | 83622106 | CAMP EVERS 2106 | 60124 | 37.1462 | -121.9823 | CAMP EVERS 210660124 | 468 | 644 | 70920.5845 | 36237.2416 | 34683.3429 | 36237.2416 | 34683.3429 | 0.14791 | 0.042183 | 1.647 | 16.7087 | 959 | 0.48951 | 1484 | 0 | 0 | 22.5168 | 1887 | 0
Bay Area | 2615 | 17 | 51.1378 | 58 | 101.0209 | 1 | 0.00014624 | 0.066431 |  |  |  |  | 0.10619 | 3.7482 | 1 | 9.7149e-06 | 0.00014624 | 0.2931 | 0.50621 | {498D8DB9-5CC7-45E0-BE16-B8DB75429782} | 83622106 | CAMP EVERS 2106 | 60124 | 37.1462 | -121.9823 | CAMP EVERS 210660124 | 468 | 644 | 70920.5845 | 36237.2416 | 34683.3429 | 36237.2416 | 34683.3429 | 0.00014624 | 0.00014624 | 3.0081 | 58 | 1614 | 9.7149e-06 | 1484 | 0 | 0 | 22.5168 | 2067 | 0
Sierra | 7910 | 78 | 148.9124 | 304 | 252.9829 | 17 | 0.00015117 | 8.4618 | 50.7892 | 703.2536 | 7075.2671 | 1005.8484 | 1.9223 | 13.3689 | 1.0051 | 0.0012814 | 0.0043355 | 0.25658 | 0.58863 | {F4833127-5C39-470B-A2CB-DF77602CD67E} | 152031103 | GRASS VALLEY 1103 | 58498 | 39.2089 | -121.0617 | GRASS VALLEY 110358498 | 85 | 93 | 7155.0247 | 3648.0777 | 3506.947 | 2050.6115 | 1554.4895 | 0.073703 | 0.0025698 | 1.9091 | 17.8824 | 50 | 0.021784 | 1485 | 0 | 0 | 1.2742 | 522 | 0
Sierra | 5530 | 216 | 289.763 | 618 | 461.2975 | 65 | 0.00010646 | 13.2376 | 4.7978 | 18.2201 | 97.4746 | 1.969 | 1.8232 | 15.7486 | 1.242 | 0.0012796 | 0.00026173 | 0.34951 | 0.62815 | {C95685B7-B649-4BB7-AFD8-6C20EE89F893} | 153661104 | APPLE HILL 1104 | circuit_breaker | 38.7394 | -120.677 | APPLE HILL 1104circuit_breaker | 120 | 294 | 17638.2405 | 6802.485 | 10835.7556 | 6802.485 | 10835.7556 | 0.017012 | 0.00692 | 1.3415 | 9.5077 | 1222 | 0.083174 | 1486 | 0 | 0 | 4.2269 | 209 | 0
Bay Area | 8824 | 18 | 22.6223 | 26 | 27.1174 | 6 | 1.2669e-05 | 113.9785 | 1.2375 | 1170.2273 | 4685.7187 | 8.1491 | 5.7736 | 787.698 | 1.2378 | 0.0012794 | 1.4082e-05 | 0.69231 | 0.83424 | {C3E4270B-E62A-43D8-B1E2-6AFA491A42A5} | 14351104 | FREMONT 1104 | MR707 | 37.5484 | -121.9379 | FREMONT 1104MR707 | 17 | 0 | 14467.9261 | 14467.9261 | 0 | 2328.9027 | 0 | 8.4494e-05 | 7.6014e-05 | 1.2568 | 4.3333 | 2721 | 0.0076763 | 1487 | 0 | 0 | 1.4471 | 2827 | 0
Central Coast | 2681 | 713 | 1192.3901 | 1015 | 1380.9468 | 69 | 0.00015032 | 9.7164 | 5.8051 | 49.2411 | 582.1972 | 10.3433 | 0.79322 | 15.6181 | 1.0675 | 0.0012765 | 0.00044156 | 0.70246 | 0.86346 | {5E67FDC7-6621-4E4B-BC49-469EB29666B6} | 82841102 | BIG BASIN 1102 | 12124 | 37.1678 | -122.1661 | BIG BASIN 110212124 | 107 | 117 | 15143.4295 | 6852.9075 | 8290.5219 | 6852.9075 | 8290.5219 | 0.030468 | 0.010372 | 1.6724 | 14.7101 | 879 | 0.088081 | 1488 | 0 | 0 | 4.2582 | 2094 | 0
Central Coast | 5809 | 188 | 340.7805 | 415 | 470.037 | 36 | 0.00015924 | 9.3302 | 10.904 | 18.8537 | 79.7204 | 4.1949 | 2.962 | 19.7439 | 1.0063 | 0.0012691 | 0.00069485 | 0.45301 | 0.72501 | {58DC126F-C9E2-47DB-AFA1-8FE0FF5A0DFD} | 83622106 | CAMP EVERS 2106 | 94770 | 37.0632 | -122.0057 | CAMP EVERS 210694770 | 125 | 215 | 18412.2252 | 6436.7786 | 11975.4466 | 3595.9649 | 9723.1688 | 0.025015 | 0.0057328 | 1.8127 | 11.5278 | 569 | 0.045686 | 1489 | 0 | 0 | 2.2344 | 1390 | 0
Central Valley | 6825 | 22 | 30.9939 | 179 | 82.0577 | 46 | 3.5324e-05 | 56.5936 | 2.8467 | 286.6867 | 1145.3824 | 6.2889 | 2.2799 | 318.8139 | 1.4798 | 0.0012689 | 6.5879e-05 | 0.12291 | 0.37771 | {3B5F2B21-B073-4B15-A884-38AC36D267F6} | 163781701 | PEORIA 1701 | circuit_breaker | 37.9036 | -120.4974 | PEORIA 1701circuit_breaker | 85 | 57 | 19505.6694 | 14117.7933 | 5387.8761 | 14117.7933 | 5387.8761 | 0.0030304 | 0.0016249 | 1.4088 | 3.8913 | 2083 | 0.05837 | 1490 | 0 | 0 | 8.7724 | 2546 | 0
Sierra | 2384 | 2071 | 2674.3929 | 5807 | 4324.7007 | 419 | 0.00012766 | 9.8298 | 21.0371 | 213.413 | 4099.6904 | 1416.0508 | 1.2989 | 21.1069 | 1.111 | 0.0012655 | 0.0013059 | 0.35664 | 0.6184 | {54AAD7CE-E934-4821-993C-6E306524E68C} | 153661104 | APPLE HILL 1104 | 13512 | 38.7391 | -120.6678 | APPLE HILL 110413512 | 629 | 1006 | 98402.7826 | 49772.481 | 48630.3017 | 45529.6464 | 44057.5936 | 0.54718 | 0.05349 | 1.2914 | 13.8592 | 292 | 0.53023 | 1491 | 0 | 0 | 28.2908 | 491 | 0
Central Valley | 1364 | 99 | 133.6372 | 275 | 204.3379 | 45 | 6.2077e-05 | 23.8635 | 19.2555 | 81.9986 | 252.2575 | 5.3958 | 10.7794 | 53.8692 | 1.2202 | 0.0012632 | 0.00063121 | 0.36 | 0.654 | {60313232-3855-4646-B9A6-D03E4546E4FB} | 163351705 | CURTIS 1705 | 39256 | 37.9571 | -120.3085 | CURTIS 170539256 | 443 | 471 | 77821.3957 | 42574.1624 | 35247.2333 | 42574.1624 | 35247.2333 | 0.028404 | 0.0027935 | 1.3499 | 6.1111 | 637 | 0.056842 | 1492 | 0 | 0 | 26.4543 | 2194 | 0
Bay Area | 7251 | 89 | 288.5681 | 261 | 394.3975 | 30 | 3.1123e-05 | 69.8664 | 0.12 | 0.28478 | 0.53206 | 0.0092084 | 8.1421 | 46.4952 | 1.0362 | 0.0012617 | 2.0697e-05 | 0.341 | 0.73167 | {A785A044-2D61-4F74-B02F-A90F8B32D4AB} | 14091108 | CASTRO VALLEY 1108 | MR341 | 37.6973 | -122.0469 | CASTRO VALLEY 1108MR341 | 78 | 104 | 11176.5508 | 5102.7494 | 6073.8015 | 3784.8751 | 5454.1466 | 0.00062092 | 0.00093368 | 3.2423 | 8.7 | 2594 | 0.03785 | 1493 | 0 | 0 | 2.3518 | 2433 | 0
North Valley | 682 | 33 | 62.2596 | 217 | 153.9339 | 80 | 1.0871e-05 | 124.1635 | 1.5457 | 120.282 | 703.605 | 1.6178 | 4.3999 | 218.676 | 1.139 | 0.0012586 | 1.2498e-05 | 0.15207 | 0.40446 | {603720E6-C08C-4450-9A1D-FFFC2D98E7C9} | 103721101 | PIT NO 1 1101 | 3312 | 41.0022 | -121.4383 | PIT NO 1 11013312 | 133 | 204 | 23575.5634 | 14682.7391 | 8892.8243 | 12918.6838 | 5295.7871 | 0.00099985 | 0.00086965 | 1.8867 | 2.7125 | 2753 | 0.10069 | 1494 | 0 | 0 | 8.0273 | 627 | 0
North Coast | 5092 | 516 | 755.6324 | 634 | 807.7679 | 44 | 7.0268e-05 | 16.8122 | 10.2514 | 54.9142 | 278.6 | 2.4199 | 0.55848 | 7.6519 | 1.0247 | 0.0012573 | 0.00030239 | 0.81388 | 0.93546 | {DD9AEFE6-8781-45D2-A01C-A8D7D2CCC603} | 192151133 | NEWBURG 1133 | circuit_breaker | 40.5946 | -124.1352 | NEWBURG 1133circuit_breaker | 169 | 256 | 27275.3857 | 14787.4934 | 12487.8923 | 3484.7774 | 1516.747 | 0.013305 | 0.0030918 | 1.4644 | 14.4091 | 1116 | 0.055322 | 1495 | 0 | 0 | 2.1653 | 2587 | 0
North Coast | 7428 | 808 | 1301.7238 | 1203 | 1475.5997 | 131 | 7.3273e-05 | 16.2206 | 1.8446 | 76.205 | 392.2074 | 1.1754 | 0.72301 | 15.6094 | 0.99823 | 0.0012556 | 9.9998e-05 | 0.67165 | 0.88217 | {E2A5C9D1-0F72-4324-B0EF-35BCFDBA6824} | 42761101 | FORT BRAGG A 1101 | 3113 | 39.5073 | -123.7645 | FORT BRAGG A 11013113 | 91 | 111 | 25812.3522 | 16133.333 | 9679.0193 | 16133.333 | 9679.0193 | 0.0131 | 0.0095988 | 1.611 | 9.1832 | 1849 | 0.16449 | 1496 | 0 | 0 | 10.0248 | 19 | 0
Bay Area | 977 | 53 | 175.1646 | 97 | 191.162 | 14 | 6.3543e-05 | 22.7255 | 6.3849 | 119.8358 | 684.6413 | 10.2475 | 0.74257 | 91.7751 | 1.0512 | 0.00125 | 0.00016692 | 0.54639 | 0.91632 | {04338CCA-7EF9-409D-9ECF-B4834D579CE2} | 24101102 | HALF MOON BAY 1102 | 2032 | 37.498 | -122.4633 | HALF MOON BAY 11022032 | 271 | 1140 | 45944.3252 | 17402.7083 | 28541.6169 | 2245.4219 | 3516.6026 | 0.0023369 | 0.0008896 | 3.305 | 6.9286 | 1529 | 0.017499 | 1497 | 0 | 0 | 1.3952 | 1206 | 0
Sierra | 127 | 2389 | 3306.6889 | 5040 | 4507.6875 | 463 | 0.00010646 | 11.787 | 32.7571 | 196.1334 | 2728.8552 | 583.3105 | 2.3431 | 32.0322 | 1.0948 | 0.0012494 | 0.0016589 | 0.47401 | 0.73357 | {DD461B3A-397C-4A3A-A4DD-6F0A05715903} | 153661103 | APPLE HILL 1103 | circuit_breaker | 38.7394 | -120.6769 | APPLE HILL 1103circuit_breaker | 727 | 1120 | 109916.7446 | 53861.3542 | 56055.3904 | 47137.6043 | 52133.033 | 0.76806 | 0.049292 | 1.3841 | 10.8855 | 214 | 0.57849 | 1498 | 0 | 0 | 29.2899 | 532 | 0
North Coast | 127 | 3 | 2.9222 | 8 | 7.4881 | 1 | 7.2778e-05 | 0.066432 | 0.097929 | 0.3067 | 0.63039 | 0.00026188 | 0 | 0.0030973 | 1 | 4.8348e-06 | 7.1271e-06 | 0.375 | 0.39025 | {DD461B3A-397C-4A3A-A4DD-6F0A05715903} | 153661103 | APPLE HILL 1103 | circuit_breaker | 38.7394 | -120.6769 | APPLE HILL 1103circuit_breaker | 727 | 1120 | 109916.7446 | 53861.3542 | 56055.3904 | 47137.6043 | 52133.033 | 7.1271e-06 | 7.2778e-05 | 0.97408 | 8 | 2820 | 4.8348e-06 | 1498 | 0 | 0 | 29.2899 | 475 | 0
Bay Area | 9055 | 11 | 29.3025 | 17 | 31.4576 | 2 | 2.5805e-05 | 48.2283 | 0 | 0.19076 | 0.0015275 | 0 | 2.3451 | 77.6095 | 1.0066 | 0.0012445 | 1.1831e-05 | 0.64706 | 0.93149 | {8B109078-C964-45C9-BF00-4904308EBFAE} | 14592105 | BRENTWOOD 2105 | 96324 | 37.8624 | -121.6734 | BRENTWOOD 210596324 | 12 | 2 | 841.0537 | 775.7684 | 65.2852 | 775.7684 | 65.2852 | 2.3663e-05 | 5.1609e-05 | 2.6639 | 8.5 | 2765 | 0.002489 | 1499 | 0 | 0 | 0.48204 | 2326 | 0
Central Valley | 3395 | 2 | 3.89 | 13 | 7.5974 | 7 | 1.9387e-05 | 63.6284 | 6.3678 | 861.4103 | 6537.1685 | 42.3276 | 4.7102 | 382.6126 | 1.1539 | 0.0012362 | 3.6843e-05 | 0.15385 | 0.51201 | {FEFF3CD8-2343-48D8-93C4-6004850FEF87} | 258861101 | SO. CAL. EDISON #3 1101 | circuit_breaker | 37.1585 | -119.4059 | SO. CAL. EDISON #3 1101circuit_breaker | 33 | 27 | 13827.0084 | 13165.8307 | 661.1777 | 13165.8307 | 661.1777 | 0.0002579 | 0.00013571 | 1.945 | 1.8571 | 2376 | 0.0086536 | 1500 | 0 | 0 | 8.1809 | 2283 | 0
Central Coast | 1533 | 675 | 1289.8367 | 2020 | 2067.098 | 118 | 0.00013458 | 9.1312 | 4.4994 | 40.5183 | 339.178 | 5.7654 | 0.37451 | 7.5887 | 1.0218 | 0.0012344 | 0.00036106 | 0.33416 | 0.62398 | {7E071814-6E26-47AC-8D93-17E4616D1F83} | 83252106 | PAUL SWEET 2106 | 5178 | 37.0326 | -121.9462 | PAUL SWEET 21065178 | 164 | 164 | 22492.3945 | 11755.1342 | 10737.2603 | 11755.1342 | 10737.2603 | 0.042605 | 0.01588 | 1.9109 | 17.1186 | 996 | 0.14566 | 1501 | 0 | 0 | 7.3043 | 1767 | 0
Central Coast | 3883 | 2818 | 4830.4781 | 4669 | 5859.637 | 250 | 0.00011871 | 10.2444 | 6.3509 | 71.7828 | 403.1794 | 5.6655 | 0.54919 | 15.2999 | 1.0582 | 0.0012337 | 0.00037801 | 0.60356 | 0.82436 | {F835FBEC-BE60-4F27-B7FA-FBF03B1492E9} | 83622105 | CAMP EVERS 2105 | 10214 | 37.0909 | -122.0441 | CAMP EVERS 210510214 | 214 | 272 | 37954.1099 | 22399.2356 | 15554.8743 | 22399.2356 | 15554.8743 | 0.094503 | 0.029677 | 1.7142 | 18.676 | 972 | 0.30842 | 1502 | 0 | 0 | 13.9182 | 1209 | 0
Bay Area | 6677 | 4 | 9.8459 | 12 | 15.1896 | 6 | 3.9907e-05 | 59.5241 |  |  |  |  | 1.4945 | 20.8212 | 1.146 | 0.0012306 | 3.9907e-05 | 0.33333 | 0.6482 | {31C38397-CC97-43EB-A38A-D18D8FE5AEB7} | 42461106 | BASALT 1106 | 5030 | 38.2596 | -122.3051 | BASALT 11065030 | 207 | 140 | 38839.3611 | 23881.4452 | 14957.9159 | 2570.7987 | 2065.125 | 0.00023944 | 0.00023944 | 2.4615 | 2 | 2344 | 0.0073833 | 1503 | 0 | 0 | 1.5974 | 2061 | 0
North Coast | 7400 | 45 | 54.8639 | 95 | 85.9059 | 25 | 9.3143e-05 | 12.9738 | 17.4763 | 1747.0935 | 24565.5854 | 998.1478 | 3.3907 | 107.6545 | 1.0443 | 0.0012262 | 0.00065068 | 0.47368 | 0.63865 | {0750A711-A5D3-4DF4-B033-0C5E7ED06920} | 42871101 | UPPER LAKE 1101 | 6663 | 39.2126 | -122.9314 | UPPER LAKE 11016663 | 21 | 21 | 4581.7264 | 3763.6845 | 818.0419 | 3763.6845 | 818.0419 | 0.016267 | 0.0023286 | 1.2192 | 3.8 | 617 | 0.030656 | 1504 | 0 | 0 | 2.3386 | 2065 | 0
Central Valley | 7702 | 171 | 230.9196 | 573 | 408.3333 | 62 | 0.000102 | 11.1872 | 33.6587 | 242.3849 | 3985.4559 | 705.3113 | 1.3657 | 9.943 | 1.0038 | 0.0012205 | 0.0022385 | 0.29843 | 0.56552 | {5E0ECFE9-34C5-4F2B-8405-6E29B71598DF} | 163751101 | PINE GROVE 1101 | circuit_breaker | 38.4127 | -120.6604 | PINE GROVE 1101circuit_breaker | 118 | 178 | 14825.456 | 6897.7403 | 7927.7157 | 6897.7403 | 7927.7157 | 0.13879 | 0.0063241 | 1.3504 | 9.2419 | 157 | 0.07567 | 1505 | 0 | 0 | 4.2861 | 1706 | 0
North Coast | 4288 | 136 | 207.0186 | 208 | 239.0353 | 42 | 4.008e-05 | 30.1102 | 15.1919 | 84.3174 | 282.5381 | 16.125 | 6.4234 | 23.6842 | 1.2036 | 0.0012171 | 0.00027442 | 0.65385 | 0.86606 | {A8AFA199-8340-4CFB-8F0F-27828B093B75} | 42271104 | COTATI 1104 | 75972 | 38.3319 | -122.7191 | COTATI 110475972 | 100 | 231 | 20257.6269 | 7223.394 | 13034.2329 | 4863.4766 | 9137.0381 | 0.011526 | 0.0016834 | 1.5222 | 4.9524 | 1190 | 0.051118 | 1506 | 0 | 0 | 3.022 | 29 | 0
Central Valley | 4260 | 220 | 336.8734 | 1122 | 687.0245 | 225 | 3.8931e-05 | 40.7263 | 10.6956 | 451.1878 | 3714.3694 | 107.7361 | 4.53 | 172.8714 | 1.3599 | 0.0012134 | 0.00020741 | 0.19608 | 0.49034 | {FABC253B-2AB5-4209-985F-A0BF3DABCFE0} | 254452101 | MARIPOSA 2101 | 8030 | 37.5701 | -119.9416 | MARIPOSA 21018030 | 192 | 160 | 45373.7027 | 30213.4552 | 15160.2474 | 30213.4552 | 15160.2474 | 0.046666 | 0.0087595 | 1.5312 | 4.9867 | 1390 | 0.27302 | 1507 | 0 | 0 | 18.7738 | 2134 | 0
Central Valley | 4696 | 108 | 154.1148 | 294 | 241.1466 | 26 | 6.1246e-05 | 22.947 | 18.4671 | 208.4218 | 1943.0791 | 58.352 | 6.6146 | 36.2192 | 1.2479 | 0.0012107 | 0.00052241 | 0.36735 | 0.63909 | {08D111B3-1350-4552-9BBA-E44861C6A6AD} | 252531102 | SAN JOAQUIN #3 1102 | 10342 | 37.2706 | -119.5344 | SAN JOAQUIN #3 110210342 | 36 | 96 | 7138.3813 | 2930.8819 | 4207.4994 | 2930.8819 | 4207.4994 | 0.013583 | 0.0015924 | 1.427 | 11.3077 | 771 | 0.031479 | 1508 | 0 | 0 | 1.8212 | 1635 | 0
Central Valley | 8214 | 27 | 36.2196 | 82 | 64.9219 | 19 | 2.9401e-06 | 327.1621 | 3.8138 | 8599.4675 | 63486.5183 | 305.9161 | 5.4952 | 2466.5958 | 1.7755 | 0.0012095 | 6.8711e-06 | 0.32927 | 0.55789 | {CEAE967B-3953-4836-B34C-F08811987B2A} | 253642103 | POSO MOUNTAIN 2103 | 3988 | 35.5532 | -118.9349 | POSO MOUNTAIN 21033988 | 80 | 35 | 31719.7098 | 29944.6558 | 1775.054 | 26364.8424 | 1421.739 | 0.00013055 | 5.5861e-05 | 1.3415 | 4.3158 | 2826 | 0.02298 | 1509 | 0 | 0 | 16.3823 | 878 | 0
North Coast | 8117 | 29 | 65.638 | 96 | 96.0575 | 13 | 0.00021454 | 3.7233 | 14.0619 | 568.7131 | 11997.7478 | 348.1381 | 0.37338 | 9.0077 | 1.0044 | 0.0012068 | 0.0019838 | 0.30208 | 0.68332 | {1C7B29C1-9766-4E63-AFC2-ED97D59270C9} | 192401101 | HOOPA 1101 | 93038 | 41.0453 | -123.6742 | HOOPA 110193038 | 76 | 134 | 7436.6714 | 4553.13 | 2883.5414 | 1584.2405 | 1034.4196 | 0.025789 | 0.002789 | 2.2634 | 7.3846 | 178 | 0.015689 | 1510 | 0 | 0 | 0.9844 | 2108 | 0
Sierra | 3925 | 139 | 189.8184 | 346 | 286.1969 | 50 | 0.00010493 | 10.0523 | 45.4441 | 387.5411 | 4786.0511 | 480.6311 | 0.71124 | 27.7433 | 1.04 | 0.0012022 | 0.003397 | 0.40173 | 0.66324 | {B420824B-DD3F-4FE1-8D52-CD4BC6F64A66} | 152031101 | GRASS VALLEY 1101 | 2766 | 39.198 | -121.0559 | GRASS VALLEY 11012766 | 45 | 55 | 9560.6495 | 5407.6674 | 4152.9822 | 5321.5191 | 4152.9822 | 0.16985 | 0.0052463 | 1.3656 | 6.92 | 80 | 0.060111 | 1511 | 0 | 0 | 3.3066 | 1403 | 0
North Coast | 4928 | 566 | 971.6965 | 889 | 1113.3287 | 60 | 0.00014566 | 8.7864 | 0.86634 | 53.5861 | 245.5274 | 0.40122 | 1.0902 | 23.8152 | 1.053 | 0.0011963 | 0.00013004 | 0.63667 | 0.87278 | {B2A085D5-4C4C-4026-B04B-46CF38E6CB2B} | 192251102 | RIO DELL 1102 | 70960 | 40.4163 | -123.9613 | RIO DELL 110270960 | 129 | 199 | 33044.5453 | 19246.0448 | 13798.5006 | 5431.663 | 4863.7866 | 0.0078026 | 0.0087395 | 1.7168 | 14.8167 | 1701 | 0.071776 | 1512 | 0 | 0 | 3.3751 | 1021 | 0
North Coast | 9153 | 299 | 426.2815 | 462 | 524.3944 | 50 | 0.00011236 | 11.0091 | 1.6315 | 64.1766 | 426.1781 | 2.0853 | 0.26438 | 39.2366 | 1.1087 | 0.0011918 | 0.0001494 | 0.64719 | 0.8129 | {FA640947-6357-4303-A243-055CFBFA4C89} | 42811111 | MONTE RIO 1111 | 3891 | 38.5162 | -123.0644 | MONTE RIO 11113891 | 25 | 36 | 8962.1332 | 5703.541 | 3258.5922 | 5703.541 | 3258.5922 | 0.0074702 | 0.005618 | 1.4257 | 9.24 | 1595 | 0.059592 | 1513 | 0 | 0 | 3.544 | 528 | 0
North Coast | 230 | 108 | 169.4895 | 219 | 213.4896 | 24 | 9.8188e-05 | 20.888 | 2.5933 | 38.4327 | 273.7937 | 3.1829 | 2.3854 | 12.4191 | 1.0099 | 0.0011867 | 0.00017537 | 0.49315 | 0.7939 | {4082A2F1-8D28-4818-ADB2-9A809F438C96} | 43311102 | KONOCTI 1102 | 2293 | 38.9455 | -122.6673 | KONOCTI 11022293 | 44 | 81 | 6782.8665 | 2820.5709 | 3962.2956 | 2621.5628 | 3870.2605 | 0.0042089 | 0.0023565 | 1.5693 | 9.125 | 1501 | 0.02848 | 1514 | 0 | 0 | 1.629 | 1075 | 0
Bay Area | 8383 | 39 | 49.4522 | 196 | 132.0017 | 37 | 1.8418e-05 | 46.4585 | 0.69865 | 88.332 | 253.8411 | 0.47761 | 3.9769 | 588.971 | 1.3957 | 0.001185 | 2.5267e-05 | 0.19898 | 0.37463 | {6830085F-FF28-4A85-9104-F5B6CFD24479} | 14241101 | SUNOL 1101 | circuit_breaker | 37.587 | -121.8695 | SUNOL 1101circuit_breaker | 85 | 45 | 10668.6366 | 9328.3659 | 1340.2707 | 4242.1562 | 356.3029 | 0.00093489 | 0.00068146 | 1.268 | 5.2973 | 2533 | 0.043844 | 1515 | 0 | 0 | 2.636 | 2329 | 0
Central Coast | 4804 | 127 | 170.0639 | 900 | 681.67 | 100 | 4.1297e-05 | 29.6013 | 1.1786 | 51.9335 | 214.3995 | 2.5496 | 3.2268 | 125.9873 | 1.1904 | 0.001184 | 4.6902e-05 | 0.14111 | 0.24948 | {2D4980B0-FA10-4F37-8CCC-A52F852CF913} | 183052110 | TEMPLETON 2110 | R94 | 35.5605 | -120.7743 | TEMPLETON 2110R94 | 218 | 156 | 45922.7187 | 33532.7028 | 12390.0159 | 21302.3977 | 6939.6036 | 0.0046902 | 0.0041297 | 1.3391 | 9 | 2268 | 0.1184 | 1516 | 0 | 0 | 13.2367 | 2124 | 0
Bay Area | 335 | 1045 | 1802.9319 | 2960 | 2907.0017 | 191 | 0.00011425 | 10.5293 | 9.3094 | 105.13 | 2063.6078 | 74.9218 | 0.48914 | 5.426 | 1.2498 | 0.0011761 | 0.00051751 | 0.35304 | 0.6202 | {9E6A6B97-69AF-4332-A126-23324C3DC522} | 43021101 | WOODACRE 1101 | 404 | 38.0131 | -122.6677 | WOODACRE 1101404 | 318 | 866 | 62554.8185 | 19975.081 | 42579.7375 | 19975.081 | 42579.7375 | 0.098844 | 0.021821 | 1.7253 | 15.4974 | 776 | 0.22463 | 1517 | 0 | 0 | 12.4119 | 2391 | 0
Central Valley | 6088 | 188 | 268.5287 | 1079 | 674.5107 | 64 | 6.3974e-05 | 20.138 | 53.3001 | 274.1422 | 4475.1258 | 1033.7426 | 3.1225 | 36.2657 | 1.3719 | 0.0011614 | 0.0014599 | 0.17424 | 0.39811 | {EB9C8400-DD80-4F71-B217-2C3080AFE151} | 163661702 | MIWUK 1702 | 19772 | 38.0261 | -120.2523 | MIWUK 170219772 | 66 | 140 | 12024.5877 | 6198.5938 | 5825.9939 | 6198.5938 | 5825.9939 | 0.093434 | 0.0040944 | 1.4283 | 16.8594 | 256 | 0.074328 | 1518 | 0 | 0 | 3.8516 | 1858 | 0
Central Valley | 65 | 187 | 322.7227 | 387 | 413.0457 | 74 | 6.2885e-07 | 1880.0512 | 0 | 0 | 0 | 0 | 24.1239 | 548.4674 | 1.4409 | 0.0011503 | 6.2199e-07 | 0.4832 | 0.78132 | {86F94E18-E480-4E12-9A1F-F90D460B947B} | 252931102 | TEJON 1102 | 2455 | 34.8574 | -118.8835 | TEJON 11022455 | 132 | 307 | 31287.6816 | 10444.6875 | 20842.9941 | 10444.6875 | 20842.9941 | 4.6027e-05 | 4.6535e-05 | 1.7258 | 5.2297 | 2879 | 0.085122 | 1519 | 0 | 0 | 6.49 | 2025 | 0
North Coast | 265 | 495 | 755.4844 | 1184 | 1140.4011 | 86 | 0.00013171 | 10.5707 | 12.8314 | 116.9848 | 1506.6687 | 39.2364 | 1.2545 | 11.3428 | 1.1559 | 0.0011501 | 0.00089847 | 0.41807 | 0.66247 | {98884EB6-8FFE-4527-976C-FBFB7D667FB9} | 42091102 | MIRABEL 1102 | 332 | 38.509 | -122.9241 | MIRABEL 1102332 | 100 | 331 | 27226.5067 | 9065.6252 | 18160.8815 | 9065.6252 | 18160.8815 | 0.077268 | 0.011327 | 1.5262 | 13.7674 | 445 | 0.098904 | 1520 | 0 | 0 | 5.6331 | 779 | 0
North Coast | 9319 | 89 | 176.7449 | 255 | 246.0199 | 33 | 6.4362e-05 | 15.2236 | 1.7799 | 473.7304 | 3000.0199 | 14.8302 | 0.44228 | 34.6862 | 1.0536 | 0.0011495 | 0.00010621 | 0.34902 | 0.71842 | {CD0E4DDB-0ADE-4475-B99A-1BAA95E110A8} | 42811111 | MONTE RIO 1111 | 59046 | 38.4385 | -123.1041 | MONTE RIO 111159046 | 21 | 23 | 6888.9071 | 6178.7733 | 710.1339 | 5445.8416 | 710.1339 | 0.0035048 | 0.0021239 | 1.9859 | 7.7273 | 1824 | 0.037933 | 1521 | 0 | 0 | 3.3839 | 2085 | 0
Sierra | 3185 | 666 | 976.5076 | 1974 | 1591.039 | 199 | 0.0001005 | 12.0196 | 56.2868 | 464.0665 | 6775.488 | 1200.0206 | 2.2977 | 32.6373 | 1.0475 | 0.0011475 | 0.0023103 | 0.33739 | 0.61375 | {E3DC7090-B1A0-4812-A562-44F0E2AEC108} | 153081112 | PLACERVILLE 1112 | 19712 | 38.7219 | -120.7905 | PLACERVILLE 111219712 | 233 | 362 | 41850.801 | 20954.5206 | 20896.2804 | 20689.2133 | 20629.0178 | 0.45975 | 0.02 | 1.4662 | 9.9196 | 150 | 0.22836 | 1522 | 0 | 0 | 12.8557 | 201 | 0
Sierra | 2994 | 140 | 187.7826 | 213 | 225.5327 | 18 | 0.00013792 | 7.9911 | 26.4367 | 21.0252 | 126.7946 | 6.3553 | 2.8316 | 13.4696 | 1.0152 | 0.0011462 | 0.0015349 | 0.65728 | 0.83262 | {04FFA86D-12A8-4DCB-A786-7ABADD4FCF1A} | 152691103 | HIGGINS 1103 | 2194 | 39.1529 | -121.0613 | HIGGINS 11032194 | 70 | 164 | 10895.1873 | 4329.2096 | 6565.9777 | 1734.1421 | 2109.6758 | 0.027629 | 0.0024825 | 1.3413 | 11.8333 | 237 | 0.020631 | 1523 | 0 | 0 | 1.0775 | 1886 | 0
Sierra | 2433 | 830 | 1193.2216 | 1797 | 1645.3357 | 222 | 0.00016295 | 6.84 | 26.188 | 1104.677 | 18089.1198 | 1119.309 | 2.4477 | 41.8773 | 1.1067 | 0.001142 | 0.0021904 | 0.46188 | 0.72521 | {474A8BDA-95BF-4717-B362-885E409D4F7A} | 152471101 | COLUMBIA HILL 1101 | 35424 | 39.3431 | -121.1212 | COLUMBIA HILL 110135424 | 213 | 290 | 38870.9973 | 22222.0885 | 16648.9089 | 22222.0885 | 16648.9089 | 0.48627 | 0.036175 | 1.4376 | 8.0946 | 160 | 0.25352 | 1524 | 0 | 0 | 13.8082 | 2815 | 0
North Coast | 3109 | 238 | 441.802 | 1038 | 751.2709 | 134 | 6.714e-05 | 16.6968 | 2.1726 | 3.0975 | 11.5166 | 0.19982 | 1.2116 | 37.7426 | 1.28 | 0.0011403 | 0.00010859 | 0.22929 | 0.58807 | {F34B7A71-9435-4BB4-952A-AC8430FF4984} | 43351103 | LUCERNE 1103 | 630 | 39.1185 | -122.8329 | LUCERNE 1103630 | 348 | 1045 | 64140.9829 | 21891.672 | 42249.3109 | 19624.8492 | 35913.2319 | 0.014551 | 0.0089968 | 1.8563 | 7.7463 | 1810 | 0.1528 | 1525 | 0 | 0 | 12.1943 | 16 | 0
North Coast | 6982 | 1 | 1.2277 | 1 | 1.2277 | 1 | 3.0165e-05 | 75.5689 | 0 | 0 | 0 | 0 | 3.0575 | 403.0051 | 1.7146 | 0.0022795 | 0 | 1 | 1 | {335D8DF9-D334-4C80-A8EC-F250AAC0E6C3} | 42211104 | NOVATO 1104 | 55398 | 38.1171 | -122.5642 | NOVATO 110455398 | 119 | 33 | 22960.02 | 18150.4566 | 4809.5634 | 4828.5632 | 3903.2018 | 0 | 3.0165e-05 | 1.2277 | 1 | 2893 | 0.0022795 | 1526 | 0 | 0 | 3.0003 | 2719 | 0
Bay Area | 6982 | 45 | 60.934 | 254 | 184.4463 | 30 | 6.481e-05 | 17.779 | 66.0686 | 548.0353 | 4676.4389 | 787.7901 | 2.668 | 152.6855 | 1.2257 | 0.0011013 | 0.0017715 | 0.17717 | 0.33036 | {335D8DF9-D334-4C80-A8EC-F250AAC0E6C3} | 42211104 | NOVATO 1104 | 55398 | 38.1171 | -122.5642 | NOVATO 110455398 | 119 | 33 | 22960.02 | 18150.4566 | 4809.5634 | 4828.5632 | 3903.2018 | 0.053145 | 0.0019443 | 1.3541 | 8.4667 | 201 | 0.033038 | 1526 | 0 | 0 | 3.0003 | 1001 | 0
Central Valley | 7955 | 233 | 387.1563 | 747 | 596.1711 | 103 | 7.7705e-05 | 20.1612 | 6.0614 | 50.7929 | 219.2199 | 1.5252 | 3.4153 | 38.9677 | 1.1341 | 0.0011276 | 0.000241 | 0.31191 | 0.6494 | {C4B116D3-EE04-4D0A-96A8-6CF57FE78721} | 163351703 | CURTIS 1703 | circuit_breaker | 37.9745 | -120.3201 | CURTIS 1703circuit_breaker | 209 | 251 | 30303.9317 | 17646.6229 | 12657.3088 | 13991.6786 | 7649.5708 | 0.024823 | 0.0080036 | 1.6616 | 7.2524 | 1274 | 0.11614 | 1527 | 0 | 0 | 8.694 | 2259 | 0
Central Valley | 4122 | 101 | 165.838 | 328 | 238.8106 | 99 | 6.3417e-05 | 20.6504 | 6.172 | 477.6009 | 2214.9791 | 47.4903 | 3.8023 | 465.2355 | 1.5394 | 0.0011237 | 0.00017913 | 0.30793 | 0.69443 | {BE4CA008-D653-4EED-9B85-D4D7237516F5} | 163231101 | NORTH BRANCH 1101 | circuit_breaker | 38.1998 | -120.7197 | NORTH BRANCH 1101circuit_breaker | 187 | 96 | 40371.1588 | 32618.4392 | 7752.7196 | 23932.4889 | 5098.8029 | 0.017734 | 0.0062782 | 1.642 | 3.3131 | 1490 | 0.11124 | 1528 | 0 | 0 | 14.871 | 2234 | 0
Bay Area | 9115 | 487 | 803.5938 | 847 | 1003.2079 | 57 | 7.584e-05 | 12.5832 | 2.7171 | 136.8172 | 1607.9535 | 18.3828 | 0.13926 | 27.3028 | 1.056 | 0.0011205 | 9.7794e-05 | 0.57497 | 0.80102 | {92DF57CB-130C-4B97-B59B-998A6C49E6E1} | 42261101 | BOLINAS 1101 | 37034 | 37.9442 | -122.7035 | BOLINAS 110137034 | 21 | 29 | 9075.2447 | 7287.0481 | 1788.1965 | 7287.0481 | 1788.1965 | 0.0055743 | 0.0043229 | 1.6501 | 14.8596 | 1865 | 0.063866 | 1529 | 0 | 0 | 4.528 | 2582 | 0
Central Coast | 3702 | 169 | 277.0933 | 747 | 614.8683 | 154 | 4.9408e-05 | 28.655 | 2.0822 | 187.8369 | 954.29 | 6.546 | 2.1607 | 128.8823 | 1.1436 | 0.001118 | 5.9492e-05 | 0.22624 | 0.45065 | {D3B095E1-F799-4165-8E63-ACB7F609DF06} | 182631101 | SAN LUIS OBISPO 1101 | V12 | 35.2948 | -120.637 | SAN LUIS OBISPO 1101V12 | 162 | 176 | 43571.9495 | 33846.6296 | 9725.32 | 33846.6296 | 9725.32 | 0.0091617 | 0.0076089 | 1.6396 | 4.8506 | 2148 | 0.17217 | 1530 | 0 | 0 | 21.0313 | 696 | 0
Sierra | 1467 | 8 | 13.3366 | 20 | 20.6768 | 9 | 0.00010349 | 10.6327 | 326.0621 | 4691.5653 | 76669.5148 | 28097.6857 | 1.3048 | 29.434 | 1.0465 | 0.0011177 | 0.019938 | 0.4 | 0.645 | {DB1F9D2B-D359-4F2E-9F3F-F43B886E9D0B} | 152481103 | BRUNSWICK 1103 | 50070 | 39.2755 | -121.022 | BRUNSWICK 110350070 | 502 | 468 | 79895.604 | 44784.9902 | 35110.6138 | 44784.9902 | 35110.6138 | 0.17944 | 0.0009314 | 1.6671 | 2.2222 | 1 | 0.010059 | 1531 | 0 | 0 | 27.8281 | 2991 | 0
North Coast | 413 | 3251 | 5303.6364 | 4181 | 5717.6514 | 277 | 8.9054e-05 | 12.8513 | 3.6493 | 76.6337 | 440.8674 | 2.5525 | 0.54862 | 7.4001 | 1.008 | 0.0011158 | 0.00019152 | 0.77757 | 0.92759 | {F8ACD64A-30F6-4E37-A172-24BA9176BE45} | 192021122 | ARCATA 1122 | 5384 | 40.8273 | -124.0389 | ARCATA 11225384 | 315 | 391 | 57674.1355 | 28119.8007 | 29554.3348 | 24769.8423 | 26626.5889 | 0.053051 | 0.024668 | 1.6314 | 15.0939 | 1446 | 0.30908 | 1532 | 0 | 0 | 15.3913 | 975 | 0
North Coast | 8197 | 677 | 924.4501 | 800 | 981.8801 | 63 | 9.7842e-05 | 9.8754 | 0.23941 | 48.6172 | 226.8695 | 0.069607 | 0.10216 | 12.9858 | 1.0265 | 0.0011062 | 6.1384e-05 | 0.84625 | 0.94151 | {47D7E27E-F1F2-4AFA-B2C6-25B11F5B475A} | 192291121 | CARLOTTA 1121 | 44150 | 40.4947 | -123.9878 | CARLOTTA 112144150 | 16 | 12 | 6054.0922 | 5746.8082 | 307.284 | 5746.8082 | 307.284 | 0.0038672 | 0.0061641 | 1.3655 | 12.6984 | 2120 | 0.06969 | 1533 | 0 | 0 | 3.5709 | 1629 | 0
Bay Area | 2916 | 102 | 290.1226 | 325 | 425.3618 | 59 | 2.9436e-05 | 19.8652 | 1.3558 | 18.8953 | 40.9394 | 0.39145 | 1.192 | 20.1348 | 1.0508 | 0.0011053 | 4.8715e-05 | 0.31385 | 0.68206 | {144B3CD2-37D4-4FA9-8973-1F3A9C9CD174} | 14091109 | CASTRO VALLEY 1109 | MR334 | 37.6745 | -122.0317 | CASTRO VALLEY 1109MR334 | 165 | 217 | 21558.19 | 10131.275 | 11426.9149 | 9273.2114 | 10690.4871 | 0.0028742 | 0.0017367 | 2.8443 | 5.5085 | 2238 | 0.065212 | 1534 | 0 | 0 | 5.7621 | 1332 | 0
Central Coast | 7949 | 439 | 671.4125 | 974 | 986.259 | 49 | 9.7966e-05 | 11.7139 | 14.7075 | 114.8101 | 1071.6472 | 28.8092 | 1.9375 | 15.029 | 1.1085 | 0.0010956 | 0.00072259 | 0.45072 | 0.68077 | {08B6165C-ACFB-44A0-A794-D2E73EAB3B33} | 83622106 | CAMP EVERS 2106 | 11533 | 37.1429 | -121.9939 | CAMP EVERS 210611533 | 36 | 34 | 6338.1156 | 4271.438 | 2066.6776 | 4271.438 | 2066.6776 | 0.035407 | 0.0048003 | 1.5294 | 19.8776 | 554 | 0.053683 | 1535 | 0 | 0 | 2.6541 | 376 | 0
Bay Area | 7505 | 702 | 923.0182 | 1419 | 1339.5554 | 113 | 0.00010764 | 11.0208 | 3.437 | 161.7187 | 2202.6373 | 26.9599 | 0.88149 | 30.2704 | 1.074 | 0.0010955 | 0.00024243 | 0.49471 | 0.68905 | {72EECE85-CF40-4400-84B0-964539FAE729} | 43432105 | SILVERADO 2105 | 1421 | 38.5018 | -122.4771 | SILVERADO 21051421 | 100 | 94 | 31210.6146 | 15928.1461 | 15282.4685 | 15418.6642 | 14199.2368 | 0.027394 | 0.012164 | 1.3148 | 12.5575 | 1272 | 0.12379 | 1536 | 0 | 0 | 9.5807 | 1691 | 0
Bay Area | 1067 | 242 | 581.2985 | 1171 | 1139.6969 | 86 | 6.0564e-05 | 17.5296 | 13.0893 | 81.5931 | 228.7636 | 10.1798 | 2.0645 | 20.9884 | 0.99496 | 0.0010928 | 0.00046767 | 0.20666 | 0.51005 | {6B23A69C-24B9-4566-AFFA-1FAEC2B2E50D} | 13801101 | MORAGA 1101 | circuit_breaker | 37.8489 | -122.1621 | MORAGA 1101circuit_breaker | 168 | 291 | 26965.0848 | 12067.7483 | 14897.3365 | 10864.992 | 13579.6613 | 0.04022 | 0.0052085 | 2.4021 | 13.6163 | 835 | 0.093981 | 1537 | 0 | 0 | 6.7512 | 409 | 0
Sierra | 1121 | 712 | 1021.0112 | 1957 | 1500.9344 | 202 | 8.4555e-05 | 17.4251 | 2.9986 | 15.3038 | 72.9455 | 0.57124 | 3.0847 | 31.8005 | 1.0684 | 0.0010891 | 9.5435e-05 | 0.36382 | 0.68025 | {4EF25014-B554-454F-9BE5-F3AB9DDDB6E9} | 152701109 | BELL 1109 | circuit_breaker | 38.9466 | -121.0916 | BELL 1109circuit_breaker | 396 | 390 | 48499.3672 | 27671.9197 | 20827.4475 | 22001.4253 | 17249.2172 | 0.019278 | 0.01708 | 1.434 | 9.6881 | 1877 | 0.21999 | 1538 | 0 | 0 | 13.671 | 1041 | 0
North Valley | 9020 | 119 | 134.7891 | 454 | 292.8803 | 86 | 3.0529e-05 | 45.4978 | 0.09367 | 1349.9065 | 25152.5615 | 7.8864 | 0.21576 | 86.8632 | 1.3118 | 0.001083 | 1.7263e-05 | 0.26211 | 0.46022 | {CBEFA52C-F905-473F-B9BB-602279DBF4B7} | 103381102 | FRENCH GULCH 1102 | 2902 | 40.6671 | -122.6345 | FRENCH GULCH 11022902 | 12 | 4 | 11324.9967 | 11239.784 | 85.2126 | 11239.784 | 85.2126 | 0.0014847 | 0.0026255 | 1.1327 | 5.2791 | 2662 | 0.093136 | 1539 | 0 | 0 | 6.9841 | 373 | 0
North Coast | 3465 | 13 | 21.1249 | 55 | 36.3285 | 18 | 8.0291e-05 | 14.9056 | 0.22998 | 21.7404 | 153.0433 | 0.07712 | 1.0087 | 52.5954 | 1.1308 | 0.0010819 | 5.7082e-05 | 0.23636 | 0.5815 | {F830099C-EEA2-4CF4-B68F-D2F012925468} | 43351103 | LUCERNE 1103 | circuit_breaker | 39.1102 | -122.8131 | LUCERNE 1103circuit_breaker | 170 | 419 | 27761.1735 | 13358.6173 | 14402.5562 | 3472.4667 | 1684.9341 | 0.0010275 | 0.0014452 | 1.625 | 3.0556 | 2174 | 0.019474 | 1540 | 0 | 0 | 2.1577 | 953 | 0
Bay Area | 4319 | 95 | 288.7347 | 131 | 302.4149 | 20 | 5.0282e-05 | 25.2544 | 3.9103 | 167.5004 | 580.4006 | 1.8282 | 0.90796 | 53.5933 | 1.0893 | 0.0010773 | 0.00013631 | 0.72519 | 0.95476 | {D0EDFCD8-2A8A-490D-A06D-0BAFCCC6E362} | 24101103 | HALF MOON BAY 1103 | circuit_breaker | 37.4689 | -122.4303 | HALF MOON BAY 1103circuit_breaker | 276 | 892 | 45830.292 | 13492.7817 | 32337.5103 | 2489.4218 | 120.0432 | 0.0027262 | 0.0010056 | 3.0393 | 6.55 | 1656 | 0.021546 | 1541 | 0 | 0 | 1.5469 | 1297 | 0
Bay Area | 9418 | 5 | 11.9693 | 14 | 17.7687 | 4 | 5.8565e-05 | 17.8993 | 0.21449 | 0.88958 | 1.8488 | 0.00069354 | 0.091814 | 2.4266 | 1.0066 | 0.0010714 | 3.7499e-05 | 0.35714 | 0.67361 | {A1F417AE-CB88-4BF5-A5DF-07DA5F529B12} | 42481101 | IGNACIO 1101 | 1779 | 38.0634 | -122.5623 | IGNACIO 11011779 | 13 | 19 | 1581.6706 | 677.0293 | 904.6413 | 385.9886 | 763.5808 | 0.00014999 | 0.00023426 | 2.3939 | 3.5 | 2369 | 0.0042854 | 1542 | 0 | 0 | 0.23984 | 2204 | 0
Sierra | 3089 | 17 | 20.1619 | 40 | 29.491 | 6 | 0.00010812 | 7.9911 | 22.0953 | 197.4532 | 3570.7164 | 274.2717 | 0.89122 | 11.2871 | 1.0022 | 0.0010698 | 0.001245 | 0.425 | 0.68366 | {8832E15C-A8F3-49CE-9AF2-19EADE479033} | 152481103 | BRUNSWICK 1103 | 2200 | 39.275 | -121.0207 | BRUNSWICK 11032200 | 109 | 123 | 16879.8855 | 8965.9105 | 7913.975 | 8965.9105 | 7913.975 | 0.00747 | 0.0006487 | 1.186 | 6.6667 | 308 | 0.0064186 | 1543 | 0 | 0 | 5.5712 | 474 | 0
North Coast | 6055 | 323 | 503.356 | 679 | 685.6411 | 77 | 0.000169 | 7.7838 | 1.0554 | 300.6395 | 4588.4675 | 8.9138 | 0.093064 | 16.8444 | 1.0249 | 0.0010637 | 0.00017139 | 0.4757 | 0.73414 | {ABEF63BB-FD93-485F-8439-718A3A0F3B42} | 192171101 | WILLOW CREEK 1101 | 91926 | 40.9382 | -123.8461 | WILLOW CREEK 110191926 | 57 | 59 | 21047.6068 | 17080.2643 | 3967.3425 | 7078.2935 | 2362.0353 | 0.013197 | 0.013013 | 1.5584 | 8.8182 | 1518 | 0.081905 | 1544 | 0 | 0 | 4.3982 | 1623 | 0
North Coast | 7183 | 22 | 32.2481 | 59 | 48.3545 | 17 | 9.0325e-05 | 12.6586 | 2.5335 | 22.6024 | 233.21 | 4.9048 | 0.42634 | 12.142 | 1.0056 | 0.0010637 | 0.00016763 | 0.37288 | 0.66691 | {A3F717BF-A7F9-4D6D-9334-FEB4D4CA058B} | 43351106 | LUCERNE 1106 | 2327 | 39.0672 | -122.7833 | LUCERNE 11062327 | 30 | 103 | 6578.3575 | 2038.5927 | 4539.7648 | 1891.7626 | 3406.5386 | 0.0028498 | 0.0015355 | 1.4658 | 3.4706 | 1525 | 0.018082 | 1545 | 0 | 0 | 1.1755 | 181 | 0
North Coast | 7943 | 183 | 308.2358 | 305 | 376.3744 | 33 | 0.00016995 | 7.2777 | 9.5883 | 98.1082 | 712.4835 | 14.9252 | 1.1214 | 15.7371 | 1.0325 | 0.0010626 | 0.00084915 | 0.6 | 0.81896 | {561B7435-E1A2-417A-BAD2-8DB925A728A4} | 42811111 | MONTE RIO 1111 | 240 | 38.4715 | -123.0471 | MONTE RIO 1111240 | 82 | 182 | 16097.1097 | 4934.4459 | 11162.6638 | 4934.4459 | 11162.6638 | 0.028022 | 0.0056083 | 1.6843 | 9.2424 | 471 | 0.035066 | 1546 | 0 | 0 | 3.0661 | 1362 | 0
Central Coast | 5185 | 767 | 1457.1326 | 1232 | 1728.4731 | 65 | 0.00018181 | 5.92 | 15.776 | 141.5323 | 2064.3816 | 72.9115 | 0.53033 | 15.0296 | 1.0658 | 0.001049 | 0.0014134 | 0.62256 | 0.84302 | {1594C1F1-1EBD-4EB0-9A76-086953E0C574} | 82841101 | BIG BASIN 1101 | 10720 | 37.1086 | -122.1439 | BIG BASIN 110110720 | 96 | 260 | 19352.137 | 7531.494 | 11820.643 | 7531.494 | 11820.643 | 0.091874 | 0.011818 | 1.8998 | 18.9538 | 269 | 0.068186 | 1547 | 0 | 0 | 4.6799 | 1440 | 0
Central Valley | 7263 | 58 | 96.819 | 374 | 209.9089 | 106 | 3.0401e-05 | 48.3854 | 2.3932 | 497.8503 | 2014.1732 | 8.8148 | 4.7734 | 602.7607 | 1.3775 | 0.0010488 | 5.0394e-05 | 0.15508 | 0.46124 | {3DF9BEB2-B457-42A9-8B28-26A87305BFB7} | 163881101 | IONE 1101 | L3141 | 38.4093 | -121.0098 | IONE 1101L3141 | 101 | 93 | 38698.9617 | 22463.5933 | 16235.3684 | 21707.6376 | 13642.839 | 0.0053418 | 0.0032225 | 1.6693 | 3.5283 | 2227 | 0.11117 | 1548 | 0 | 0 | 13.4885 | 2662 | 0
North Valley | 3198 | 111 | 178.6475 | 207 | 225.8551 | 27 | 1.7465e-05 | 53.8133 | 27.21 | 1107.0298 | 17535.2375 | 1388.9525 | 0.97845 | 27.5703 | 1.0411 | 0.0010464 | 0.00028178 | 0.53623 | 0.79098 | {13C79B20-35FA-46F6-90D1-7123E115130F} | 103132101 | CRESCENT MILLS 2101 | circuit_breaker | 40.0938 | -120.9109 | CRESCENT MILLS 2101circuit_breaker | 112 | 168 | 15244.7508 | 9131.4478 | 6113.303 | 3593.1531 | 2269.6701 | 0.0076082 | 0.00047154 | 1.6094 | 7.6667 | 1170 | 0.028253 | 1549 | 0 | 0 | 2.2327 | 824 | 0
Central Valley | 7482 | 68 | 108.8211 | 326 | 226.4302 | 38 | 0.00011185 | 11.3278 | 5.6926 | 13.3162 | 65.0268 | 1.9169 | 1.7828 | 13.6308 | 1.0146 | 0.001046 | 0.00044034 | 0.20859 | 0.48059 | {D0015396-1CC9-4783-A5A2-48EC4AF3208B} | 254421102 | OAKHURST 1102 | circuit_breaker | 37.322 | -119.6342 | OAKHURST 1102circuit_breaker | 146 | 292 | 24613.5971 | 7704.6852 | 16908.9118 | 3940.8287 | 9441.4855 | 0.016733 | 0.0042502 | 1.6003 | 8.5789 | 881 | 0.039746 | 1550 | 0 | 0 | 2.4487 | 1864 | 0
Sierra | 4223 | 482 | 677.9153 | 848 | 861.8546 | 64 | 0.00013309 | 8.2388 | 7.2589 | 15.2642 | 147.5945 | 4.1051 | 1.5584 | 11.2758 | 1.0099 | 0.0010383 | 0.00056352 | 0.5684 | 0.78658 | {83B5D9E2-BFF1-452F-91D8-11E4F5A6B453} | 153082106 | PLACERVILLE 2106 | 23190 | 38.7385 | -120.7795 | PLACERVILLE 210623190 | 96 | 113 | 11677.3668 | 5913.2611 | 5764.1057 | 5913.2611 | 5764.1057 | 0.036065 | 0.0085177 | 1.4065 | 13.25 | 719 | 0.066453 | 1551 | 0 | 0 | 3.6743 | 390 | 0
Central Valley | 4351 | 65 | 96.8964 | 324 | 195.2828 | 72 | 5.9957e-05 | 19.8992 | 5.5194 | 1658.247 | 12599.0741 | 144.0307 | 3.9551 | 267.9446 | 1.3261 | 0.0010377 | 0.00017089 | 0.20062 | 0.49618 | {73BBABA3-6CA4-41B8-A40A-89CE8D63C8FE} | 162161102 | ELECTRA 1102 | 4756 | 38.3164 | -120.713 | ELECTRA 11024756 | 186 | 233 | 30649.0725 | 19012.5154 | 11636.5571 | 15007.7986 | 5834.5065 | 0.012304 | 0.0043169 | 1.4907 | 4.5 | 1520 | 0.074716 | 1552 | 0 | 0 | 9.3254 | 1554 | 0
Central Coast | 2978 | 2965 | 5091.8298 | 4736 | 6087.7026 | 216 | 0.00017418 | 6.1197 | 12.974 | 33.7842 | 146.5309 | 2.5842 | 0.37614 | 5.5745 | 1.1171 | 0.0010374 | 0.0011585 | 0.62606 | 0.83641 | {024E8502-820B-436F-9464-D294850FDD35} | 82841101 | BIG BASIN 1101 | 10296 | 37.1333 | -122.1258 | BIG BASIN 110110296 | 373 | 1026 | 74246.8942 | 23203.6203 | 51043.2739 | 23203.6203 | 51043.2739 | 0.25023 | 0.037623 | 1.7173 | 21.9259 | 339 | 0.22408 | 1553 | 0 | 0 | 14.4181 | 139 | 0
Central Coast | 648 | 18 | 30.3353 | 76 | 63.1757 | 28 | 3.2857e-05 | 36.3262 | 3.8205 | 166.6644 | 685.4548 | 3.0721 | 4.4172 | 241.0612 | 1.3133 | 0.001035 | 7.9835e-05 | 0.23684 | 0.48017 | {ADF3EA9A-D7F8-418F-A55E-68471A89896D} | 182331101 | GABILAN 1101 | 579969 | 36.7777 | -121.5971 | GABILAN 1101579969 | 44 | 42 | 15366.7341 | 10763.6377 | 4603.0963 | 5768.1438 | 4286.7835 | 0.0022354 | 0.00091998 | 1.6853 | 2.7143 | 1983 | 0.02898 | 1554 | 0 | 0 | 3.5842 | 2202 | 0
North Valley | 2234 | 1716 | 2770.9862 | 3536 | 3574.0906 | 277 | 8.9776e-05 | 12.1713 | 88.4091 | 1893.3827 | 36779.162 | 5742.0718 | 0.87852 | 21.3028 | 1.0455 | 0.0010335 | 0.0036283 | 0.48529 | 0.7753 | {B1149BFB-EDFA-46D1-B822-44352980F037} | 103031102 | ORO FINO 1102 | 2560 | 39.8888 | -121.6648 | ORO FINO 11022560 | 258 | 220 | 43849.957 | 26913.6157 | 16936.3413 | 26913.6157 | 16936.3413 | 1.005 | 0.024868 | 1.6148 | 12.7653 | 72 | 0.28627 | 1555 | 0 | 0 | 16.7233 | 1107 | 0
Central Coast | 4390 | 29 | 70.7862 | 189 | 157.2011 | 46 | 2.1718e-05 | 31.1958 | 2.9899 | 43.0859 | 226.7874 | 2.5167 | 0.99885 | 24.3758 | 1.0156 | 0.0010317 | 5.7145e-05 | 0.15344 | 0.45029 | {25830136-A5D5-4A08-9B85-05018D7569FD} | 182631104 | SAN LUIS OBISPO 1104 | V14 | 35.1791 | -120.6181 | SAN LUIS OBISPO 1104V14 | 139 | 381 | 29955.5318 | 13129.632 | 16825.8998 | 13115.916 | 16560.1393 | 0.0026287 | 0.00099903 | 2.4409 | 4.1087 | 2170 | 0.04746 | 1556 | 0 | 0 | 8.1498 | 191 | 0
North Coast | 8974 | 87 | 150.2151 | 184 | 203.5163 | 12 | 0.0001119 | 6.0107 | 9.5067 | 51.7229 | 245.3624 | 3.6349 | 1.4572 | 18.7267 | 1.01 | 0.0010311 | 0.00075083 | 0.47283 | 0.7381 | {CBD25292-9F23-4669-82FC-DDD3751DA0D4} | 42811113 | MONTE RIO 1113 | 1067 | 38.4934 | -123.0059 | MONTE RIO 11131067 | 17 | 148 | 6562.6591 | 1294.5528 | 5268.1063 | 1294.5528 | 5268.1063 | 0.0090099 | 0.0013427 | 1.7266 | 15.3333 | 532 | 0.012373 | 1557 | 0 | 0 | 0.8044 | 2083 | 0
Central Coast | 5896 | 71 | 245.8978 | 185 | 292.1599 | 18 | 1.6306e-05 | 50.2842 | 4.0736 | 15.9902 | 80.7003 | 1.2768 | 4.9484 | 23.9557 | 1.0302 | 0.0010281 | 5.75e-05 | 0.38378 | 0.84165 | {5A21115A-46BA-4632-AD7D-E9A81D89A695} | 182601106 | OCEANO 1106 | V28 | 35.0973 | -120.6074 | OCEANO 1106V28 | 179 | 503 | 35061.5426 | 14455.0675 | 20606.4751 | 2046.144 | 2978.2286 | 0.001035 | 0.00029351 | 3.4633 | 10.2778 | 2162 | 0.018506 | 1558 | 0 | 0 | 1.2714 | 693 | 0
North Coast | 1525 | 1682 | 2634.1225 | 2365 | 2957.877 | 152 | 9.2735e-05 | 12.105 | 2.4177 | 63.7156 | 420.2283 | 0.74822 | 0.22484 | 5.9832 | 1.1141 | 0.0010151 | 0.0001724 | 0.71121 | 0.89054 | {909F40E6-1D12-4BBB-BCCE-5ABCF3C59E2F} | 192291121 | CARLOTTA 1121 | 4914 | 40.5335 | -124.0415 | CARLOTTA 11214914 | 220 | 419 | 42898.8658 | 22809.6793 | 20089.1865 | 15711.3837 | 10003.2935 | 0.026204 | 0.014096 | 1.5661 | 15.5592 | 1516 | 0.15429 | 1559 | 0 | 0 | 9.7626 | 312 | 0
Central Valley | 2713 | 378 | 532.8719 | 1652 | 1130.3153 | 227 | 2.4589e-05 | 41.7457 | 9.4889 | 173.9163 | 1560.0221 | 104.308 | 2.838 | 77.2097 | 1.187 | 0.0010134 | 0.0001317 | 0.22881 | 0.47144 | {AF3C9CC3-4B67-4003-BBC4-2AADCCAC2E66} | 254151101 | AUBERRY 1101 | R2845 | 37.0536 | -119.4614 | AUBERRY 1101R2845 | 244 | 306 | 50780.4756 | 28634.7335 | 22145.7421 | 28634.7335 | 22145.7421 | 0.029896 | 0.0055816 | 1.4097 | 7.2775 | 1692 | 0.23003 | 1560 | 0 | 0 | 17.7928 | 357 | 0
Central Valley | 7367 | 509 | 699.3245 | 3970 | 2511.3726 | 179 | 5.0755e-05 | 21.0568 | 68.2879 | 425.6293 | 7832.6 | 2104.1442 | 0.81878 | 13.6862 | 1.2389 | 0.0010129 | 0.0013477 | 0.12821 | 0.27846 | {EC1F55C2-465D-4546-BC4C-2AD9B6897358} | 163661701 | MIWUK 1701 | 8050 | 38.0569 | -120.203 | MIWUK 17018050 | 224 | 405 | 38125.2197 | 19483.5578 | 18641.6619 | 19483.5578 | 18641.6619 | 0.24124 | 0.0090851 | 1.3739 | 22.1788 | 282 | 0.18132 | 1561 | 0 | 0 | 12.1065 | 145 | 0
Central Valley | 2375 | 9 | 12.8826 | 26 | 20.7731 | 10 | 0.00016441 | 7.2037 | 59.3107 | 1258.6859 | 28017.2967 | 8634.0798 | 0.49668 | 8.8933 | 1.0024 | 0.00099933 | 0.0077938 | 0.34615 | 0.62016 | {EB0CF7B2-4A78-45DE-8AED-51D903B9E71F} | 163751102 | PINE GROVE 1102 | 45292 | 38.4536 | -120.53 | PINE GROVE 110245292 | 239 | 432 | 40214.6535 | 17509.1139 | 22705.5396 | 17509.1139 | 22705.5396 | 0.077938 | 0.0016441 | 1.4314 | 2.6 | 19 | 0.0099933 | 1562 | 0 | 0 | 10.8797 | 107 | 0
Central Valley | 1719 | 11 | 14.2221 | 16 | 15.5028 | 7 | 4.1188e-05 | 28.7464 | 0.29329 | 80.8609 | 267.2515 | 0.11588 | 3.4415 | 223.1864 | 1.2803 | 0.00099704 | 2.1164e-05 | 0.6875 | 0.91739 | {27131A9E-D142-4A6D-93D0-301DB39F0FC8} | 163341101 | CLAY 1101 | 13450 | 38.3494 | -120.9384 | CLAY 110113450 | 105 | 158 | 17707.8557 | 7994.7686 | 9713.0871 | 553.6801 | 2393.4024 | 0.00014815 | 0.00028832 | 1.2929 | 2.2857 | 2586 | 0.0069792 | 1563 | 0 | 0 | 0.34404 | 712 | 0
North Coast | 43 | 32 | 59.2998 | 48 | 68.4057 | 4 | 0.00015358 | 6.0158 | 3.6597 | 3.656 | 20.7145 | 0.17455 | 1.0254 | 7.2469 | 1.0017 | 0.00099634 | 0.00034709 | 0.66667 | 0.86688 | {25648DD1-14CD-4635-B4A3-2CF9AF96E6F4} | 42811111 | MONTE RIO 1111 | 1703 | 38.4835 | -123.0538 | MONTE RIO 11111703 | 29 | 67 | 5819.929 | 2219.017 | 3600.912 | 2219.017 | 3600.912 | 0.0013884 | 0.00061432 | 1.8531 | 12 | 1017 | 0.0039854 | 1564 | 0 | 0 | 1.3788 | 1557 | 0
Central Coast | 6447 | 1296 | 2346.4288 | 2285 | 2899.8923 | 110 | 0.0001793 | 5.2549 | 11.8133 | 54.5813 | 232.1919 | 4.2987 | 1.3546 | 14.2347 | 1.012 | 0.00099565 | 0.0011979 | 0.56718 | 0.80914 | {4EC0C5CA-D3E9-47E9-809A-55A51CA9C021} | 83622106 | CAMP EVERS 2106 | 37210 | 37.0808 | -122.0044 | CAMP EVERS 210637210 | 105 | 137 | 20956.4186 | 10381.5121 | 10574.9064 | 10381.5121 | 10574.9064 | 0.13177 | 0.019723 | 1.8105 | 20.7727 | 323 | 0.10952 | 1565 | 0 | 0 | 6.4508 | 1260 | 0
Central Coast | 4353 | 2 | 5.2951 | 3 | 5.9749 | 3 | 1.2118e-05 | 119.3132 | 2.4458 | 98.5203 | 492.7938 | 1.1913 | 5.6504 | 74.9987 | 1.1468 | 0.00099468 | 2.0319e-05 | 0.66667 | 0.88623 | {42FF0C87-DE5F-4AA1-BC1C-B5945FF34356} | 182201122 | SPENCE 1122 | circuit_breaker | 36.6138 | -121.5672 | SPENCE 1122circuit_breaker | 600 | 533 | 108171.3265 | 84675.007 | 23496.3195 | 14788.6218 | 8592.0069 | 6.0956e-05 | 3.6354e-05 | 2.6475 | 1 | 2602 | 0.002984 | 1566 | 0 | 0 | 9.1892 | 326 | 0
Central Valley | 5112 | 1751 | 2418.0013 | 6527 | 4928.8604 | 260 | 6.2661e-05 | 16.6152 | 17.0683 | 149.4278 | 2006.2273 | 208.0322 | 0.93669 | 11.8498 | 1.4636 | 0.00099292 | 0.00048056 | 0.26827 | 0.49058 | {268BA793-4C12-4947-B776-6DA4E26F1686} | 163661702 | MIWUK 1702 | 6018 | 38.0441 | -120.2479 | MIWUK 17026018 | 409 | 762 | 67799.5957 | 31416.8747 | 36382.721 | 31416.8747 | 36382.721 | 0.12495 | 0.016292 | 1.3809 | 25.1038 | 810 | 0.25816 | 1567 | 0 | 0 | 19.5215 | 1698 | 0
North Valley | 2954 | 460 | 624.6734 | 802 | 817.2801 | 100 | 1.1033e-05 | 110.0643 | 14.7108 | 1719.0746 | 35586.3509 | 874.7852 | 4.3145 | 116.2869 | 1.2217 | 0.00099126 | 0.00010588 | 0.57357 | 0.76433 | {55B88B02-B20F-4205-B6F5-A65D9680200A} | 102812101 | BIG MEADOWS 2101 | 2586 | 40.1493 | -120.9355 | BIG MEADOWS 21012586 | 132 | 135 | 26667.0595 | 17615.5168 | 9051.5428 | 8954.8757 | 5275.0693 | 0.010588 | 0.0011033 | 1.358 | 8.02 | 1827 | 0.099126 | 1568 | 0 | 0 | 5.5643 | 949 | 0
Central Valley | 423 | 434 | 706.1687 | 1141 | 999.4036 | 172 | 9.0378e-07 | 1429.9879 | 3.8584 | 1352.0802 | 9725.0776 | 99.5351 | 17.0429 | 956.9699 | 1.5685 | 0.00099015 | 1.2754e-06 | 0.38037 | 0.70659 | {F982DA9B-E6B3-4123-BDDF-635E01BF398E} | 252931102 | TEJON 1102 | 3751 | 34.9325 | -118.9281 | TEJON 11023751 | 335 | 388 | 71736.383 | 41566.0587 | 30170.3243 | 32633.9479 | 28296.8396 | 0.00021936 | 0.00015545 | 1.6271 | 6.6337 | 2875 | 0.17031 | 1569 | 0 | 0 | 20.2778 | 1771 | 0
Central Valley | 2640 | 105 | 214.9168 | 449 | 314.2748 | 189 | 3.3219e-05 | 33.9249 | 5.4564 | 1254.6627 | 7848.0699 | 72.9306 | 4.4952 | 221.5103 | 1.3169 | 0.00098584 | 9.1044e-05 | 0.23385 | 0.68385 | {0D159A34-F101-472F-9F8B-631446B0CF4C} | 252192101 | BEAR VALLEY 2101 | 10000 | 37.5694 | -120.1175 | BEAR VALLEY 210110000 | 271 | 225 | 82820.9502 | 53605.23 | 29215.7202 | 47046.2975 | 28714.6348 | 0.017207 | 0.0062784 | 2.0468 | 2.3757 | 1903 | 0.18632 | 1570 | 0 | 0 | 29.2332 | 2382 | 0
Sierra | 1001 | 2451 | 3075.1814 | 6438 | 5153.7764 | 546 | 0.00014909 | 7.3021 | 47.0927 | 453.4131 | 6819.5175 | 2580.8633 | 1.0445 | 17.097 | 1.0417 | 0.00098331 | 0.003014 | 0.38071 | 0.59669 | {7A0E2E82-E0E4-419F-B82C-B7D27ED17F2C} | 152762101 | EL DORADO PH 2101 | 19752 | 38.7149 | -120.5815 | EL DORADO PH 210119752 | 818 | 1270 | 139203.4044 | 61569.4579 | 77633.9465 | 61569.4579 | 77633.9465 | 1.6456 | 0.081401 | 1.2547 | 11.7912 | 105 | 0.53689 | 1571 | 0 | 0 | 38.2575 | 275 | 0
Central Coast | 3526 | 2682 | 4535.9656 | 4287 | 5473.9697 | 238 | 0.00010479 | 10.6576 | 9.54 | 48.4361 | 288.2535 | 5.0091 | 0.8762 | 12.3707 | 1.0272 | 0.00098292 | 0.00058123 | 0.62561 | 0.82864 | {1695E978-9BD4-42EE-A017-6DD99E4F027F} | 82841102 | BIG BASIN 1102 | 12992 | 37.1987 | -122.1536 | BIG BASIN 110212992 | 294 | 654 | 60432.8982 | 22897.5855 | 37535.3127 | 22897.5855 | 37535.3127 | 0.13833 | 0.024939 | 1.6913 | 18.0126 | 694 | 0.23393 | 1572 | 0 | 0 | 14.2279 | 1625 | 0
North Coast | 1201 | 29 | 32.7707 | 104 | 73.872 | 15 | 0.00010782 | 9.5888 | 1.6658 | 97.2974 | 765.4384 | 1.6883 | 1.9957 | 48.8628 | 1.1398 | 0.00098117 | 0.00013736 | 0.27885 | 0.44361 | {CBE456DC-501B-4A85-8947-55FFB864F380} | 42851121 | FORT ROSS 1121 | 2987 | 38.5419 | -123.09 | FORT ROSS 11212987 | 24 | 27 | 7211.3871 | 3345.8187 | 3865.5684 | 3345.8187 | 3865.5684 | 0.0020604 | 0.0016172 | 1.13 | 6.9333 | 1652 | 0.014718 | 1573 | 0 | 0 | 2.079 | 31 | 0
Bay Area | 1347 | 21 | 34.354 | 29 | 39.7922 | 3 | 2.6875e-05 | 31.8345 |  |  |  |  | 5.708 | 69.454 | 1.2522 | 0.00097066 | 2.6875e-05 | 0.72414 | 0.86334 | {4D869EED-AD00-4E5D-B02B-0CB786403D3A} | 14662112 | TASSAJARA 2112 | circuit_breaker | 37.7998 | -121.9076 | TASSAJARA 2112circuit_breaker | 60 | 11 | 2508.158 | 2118.6497 | 389.5083 | 219.0837 | 95.7358 | 8.0624e-05 | 8.0624e-05 | 1.6359 | 9.6667 | 2508 | 0.002912 | 1574 | 0 | 0 | 0.13613 | 1251 | 0
Bay Area | 1104 | 35 | 71.8425 | 66 | 86.8689 | 23 | 3.794e-05 | 19.7112 | 2.4151 | 2.7779 | 12.4375 | 0.20222 | 2.4907 | 7.6641 | 1.0607 | 0.00096311 | 5.4067e-05 | 0.5303 | 0.82702 | {0EC84767-A265-4D35-8CD0-07F4DBFC6169} | 42991106 | LAS GALLINAS A 1106 | circuit_breaker | 38.0223 | -122.538 | LAS GALLINAS A 1106circuit_breaker | 366 | 1739 | 110513.6289 | 25166.3517 | 85347.2773 | 2059.9533 | 13100.8008 | 0.0012435 | 0.00087261 | 2.0526 | 2.8696 | 2203 | 0.022152 | 1575 | 0 | 0 | 1.28 | 2238 | 0
Sierra | 5215 | 634 | 717.2178 | 858 | 812.1068 | 40 | 7.8345e-05 | 13.1422 | 28.482 | 135.9055 | 1554.5815 | 76.273 | 0.33335 | 18.5607 | 1.0036 | 0.00096175 | 0.001084 | 0.73893 | 0.88316 | {EB9602B6-3B78-44B7-9264-163222D3097C} | 152481105 | BRUNSWICK 1105 | 2100 | 39.2417 | -121.0262 | BRUNSWICK 11052100 | 100 | 63 | 9479.0887 | 6320.6672 | 3158.4215 | 6320.6672 | 3158.4215 | 0.043359 | 0.0031338 | 1.1313 | 21.45 | 370 | 0.03847 | 1576 | 0 | 0 | 3.9275 | 115 | 0
Central Valley | 371 | 66 | 125.1387 | 555 | 273.8117 | 179 | 2.4537e-05 | 41.1755 | 9.6176 | 6340.1655 | 37832.934 | 498.744 | 8.8304 | 433.0091 | 1.4497 | 0.0009547 | 0.00011464 | 0.11892 | 0.45702 | {6AB13959-ED93-4600-8F98-FD0154A29E48} | 163451702 | FROGTOWN 1702 | L5407 | 37.9775 | -120.6771 | FROGTOWN 1702L5407 | 169 | 148 | 44825.0653 | 29150.3712 | 15674.694 | 29150.3712 | 15674.694 | 0.02052 | 0.0043921 | 1.896 | 3.1006 | 1777 | 0.17089 | 1577 | 0 | 0 | 18.1132 | 2183 | 0
Central Coast | 4005 | 1007 | 1844.0465 | 1855 | 2345.0403 | 96 | 0.00018038 | 4.7723 | 4.7276 | 26.1772 | 99.1701 | 0.79029 | 0.41653 | 8.3825 | 1.0091 | 0.00095444 | 0.00047075 | 0.54286 | 0.78636 | {51C72ADA-5E33-425F-A574-21BEA172A863} | 83622104 | CAMP EVERS 2104 | 10442 | 37.0612 | -122.0029 | CAMP EVERS 210410442 | 240 | 573 | 44973.2002 | 16787.1434 | 28186.0568 | 8552.2815 | 8774.9518 | 0.045192 | 0.017316 | 1.8312 | 19.3229 | 825 | 0.091626 | 1578 | 0 | 0 | 5.3141 | 1020 | 0
Bay Area | 3384 | 1 | 4.0491 | 1 | 4.0491 | 1 | 3.9917e-05 | 23.8454 | 0.33744 | 0.22239 | 0.002369 | 7.994e-07 | 3.7013 | 20.246 | 1.0575 | 0.00095184 | 1.347e-05 | 1 | 1 | {5AC2A44E-A5CE-4631-A5D0-59B8F85FCDA2} | 22861104 | SERRAMONTE 1104 | 12705 | 37.6486 | -122.4713 | SERRAMONTE 110412705 | 166 | 1068 | 54531.6491 | 9361.8914 | 45169.7577 | 414.5607 | 1489.1674 | 1.347e-05 | 3.9917e-05 | 4.0491 | 1 | 2735 | 0.00095184 | 1579 | 0 | 0 | 0.2576 | 2839 | 0
Sierra | 5304 | 423 | 573.1518 | 929 | 804.0236 | 109 | 9.2062e-05 | 11.8504 | 52.5683 | 682.5703 | 10020.9194 | 2221.2141 | 2.2108 | 34.9826 | 1.1139 | 0.000939 | 0.0020159 | 0.45533 | 0.71285 | {CDB0DAC7-54D4-481D-AA9B-BDB5A3BBD3C1} | 152431101 | SHADY GLEN 1101 | 2768 | 39.1031 | -120.9603 | SHADY GLEN 11012768 | 159 | 206 | 23677.1532 | 12974.2233 | 10702.9299 | 11242.1065 | 9505.7362 | 0.21973 | 0.010035 | 1.355 | 8.5229 | 175 | 0.10235 | 1580 | 0 | 0 | 6.9855 | 568 | 0
North Coast | 2551 | 365 | 546.7828 | 384 | 556.6308 | 60 | 6.8441e-05 | 13.5584 | 0.86117 | 62.5016 | 409.7276 | 0.58385 | 1.2077 | 23.2385 | 1.0435 | 0.00093833 | 6.4148e-05 | 0.95052 | 0.98231 | {228A6257-66FD-4F4F-AA34-7D22FE084DBC} | 42851121 | FORT ROSS 1121 | 124 | 38.5657 | -123.2723 | FORT ROSS 1121124 | 125 | 90 | 43684.2668 | 29943.2023 | 13741.0645 | 29943.2023 | 13741.0645 | 0.0038489 | 0.0041064 | 1.498 | 6.4 | 2105 | 0.0563 | 1581 | 0 | 0 | 18.6058 | 1071 | 0
Sierra | 714 | 1187 | 1642.5111 | 2841 | 2457.1553 | 255 | 0.00012028 | 7.6198 | 19.5771 | 113.7204 | 1178.2142 | 81.4235 | 1.7515 | 20.2062 | 1.0366 | 0.00093306 | 0.0011757 | 0.41781 | 0.66846 | {DCB9D4A3-4396-4AF7-B5A4-4405D20B6E8E} | 152261106 | DIAMOND SPRINGS 1106 | 50324 | 38.6953 | -120.818 | DIAMOND SPRINGS 110650324 | 420 | 479 | 59350.5472 | 32529.5546 | 26820.9925 | 27285.9774 | 22030.9722 | 0.2998 | 0.030671 | 1.3837 | 11.1412 | 334 | 0.23793 | 1582 | 0 | 0 | 16.9547 | 1690 | 0
Central Coast | 3057 | 497 | 822.5658 | 930 | 1101.6407 | 84 | 0.00011044 | 7.9914 | 4.6759 | 296.5496 | 4684.1352 | 32.153 | 1.8409 | 27.877 | 1.1877 | 0.00093168 | 0.00030166 | 0.53441 | 0.74667 | {94CF54F7-C6CD-4453-B5AE-8C10C6BEE2CA} | 82841101 | BIG BASIN 1101 | circuit_breaker | 37.131 | -122.1722 | BIG BASIN 1101circuit_breaker | 77 | 65 | 14048.1866 | 7584.3674 | 6463.8192 | 7584.3674 | 6463.8192 | 0.025339 | 0.0092771 | 1.6551 | 11.0714 | 1119 | 0.078261 | 1583 | 0 | 0 | 4.7127 | 1384 | 0
North Coast | 7397 | 201 | 267.1981 | 596 | 498.6915 | 35 | 0.00015162 | 5.5012 | 14.6609 | 63.0819 | 1077.5433 | 45.8683 | 1.1772 | 2.8011 | 1.002 | 0.00092851 | 0.0011498 | 0.33725 | 0.5358 | {BDF5B432-76F8-4E7C-875F-0CD4088812BE} | 42091102 | MIRABEL 1102 | 57840 | 38.5027 | -122.9093 | MIRABEL 110257840 | 71 | 191 | 12919.4883 | 4145.2916 | 8774.1966 | 4145.2916 | 8774.1966 | 0.040245 | 0.0053067 | 1.3293 | 17.0286 | 343 | 0.032498 | 1584 | 0 | 0 | 2.5758 | 1000 | 0
Central Coast | 5738 | 9 | 12.9366 | 43 | 25.1389 | 5 | 2.3506e-05 | 39.5013 | 0.012926 | 14.0516 | 96.3022 | 0.21521 | 2.7628 | 226.0565 | 1.1345 | 0.00092277 | 1.5001e-05 | 0.2093 | 0.5146 | {370C8631-3D98-4FD6-A4A1-B8DD1604CB6A} | 182981102 | JOLON 1102 | circuit_breaker | 36.0134 | -121.1676 | JOLON 1102circuit_breaker | 229 | 122 | 50618.2914 | 38579.7369 | 12038.5546 | 36119.0128 | 11659.8838 | 7.5006e-05 | 0.00011753 | 1.4374 | 8.6 | 2706 | 0.0046139 | 1585 | 0 | 0 | 22.4433 | 2328 | 0
Sierra | 4045 | 517 | 671.9173 | 2239 | 1413.0411 | 143 | 0.00012942 | 7.5498 | 12.6122 | 40.7912 | 598.132 | 38.7975 | 0.409 | 3.6083 | 0.99664 | 0.00092196 | 0.00079161 | 0.23091 | 0.47551 | {62F80FAB-48ED-40CA-B9E7-9219C832B45F} | 152762102 | EL DORADO PH 2102 | 19542 | 38.7615 | -120.5801 | EL DORADO PH 210219542 | 259 | 556 | 38046.911 | 15104.0184 | 22942.8925 | 15104.0184 | 22942.8925 | 0.1132 | 0.018507 | 1.2996 | 15.6573 | 503 | 0.13184 | 1586 | 0 | 0 | 9.3852 | 137 | 0
Central Valley | 3689 | 19 | 37.3912 | 82 | 60.9819 | 31 | 1.6111e-05 | 63.1485 | 1.1228 | 188.1605 | 1199.8013 | 2.0727 | 4.4963 | 232.339 | 1.6166 | 0.00091714 | 1.8355e-05 | 0.23171 | 0.61315 | {BA3893C1-711D-4BF6-9767-7C0EC1B0CA4D} | 254151101 | AUBERRY 1101 | R322 | 37.0906 | -119.4686 | AUBERRY 1101R322 | 45 | 39 | 20602.1306 | 12046.3509 | 8555.7798 | 12046.3509 | 8555.7798 | 0.00056902 | 0.00049944 | 1.968 | 2.6452 | 2642 | 0.028431 | 1587 | 0 | 0 | 7.4853 | 2480 | 0
North Coast | 1084 | 1426 | 2128.3304 | 2387 | 2580.683 | 242 | 0.00017953 | 4.9764 | 13.5611 | 440.9895 | 10535.28 | 513.5714 | 1.0725 | 14.8506 | 1.0907 | 0.00091133 | 0.0014696 | 0.5974 | 0.82472 | {4A886E07-73B5-4AA1-9DE8-067CBFCADF10} | 192401101 | HOOPA 1101 | circuit_breaker | 41.0564 | -123.6824 | HOOPA 1101circuit_breaker | 536 | 829 | 66558.2244 | 43677.3103 | 22880.9141 | 23835.3937 | 8089.1245 | 0.35563 | 0.043445 | 1.4925 | 9.8636 | 254 | 0.22054 | 1588 | 0 | 0 | 14.8106 | 1897 | 0
Central Coast | 4688 | 231 | 423.692 | 1018 | 858.1909 | 130 | 6.0713e-05 | 17.9039 | 0.91717 | 121.4374 | 602.2011 | 7.7833 | 1.6363 | 85.963 | 1.0933 | 0.00090795 | 4.7531e-05 | 0.22692 | 0.4937 | {73F7E742-5FE2-48F8-9BFF-7AB912085CD1} | 182631104 | SAN LUIS OBISPO 1104 | V46 | 35.1754 | -120.5259 | SAN LUIS OBISPO 1104V46 | 313 | 124 | 40839.1116 | 33475.4301 | 7363.6815 | 30343.0121 | 6606.7419 | 0.006179 | 0.0078927 | 1.8342 | 7.8308 | 2255 | 0.11803 | 1589 | 0 | 0 | 18.8543 | 2824 | 0
North Coast | 1531 | 1272 | 1792.2402 | 2033 | 2154.5115 | 194 | 0.00014548 | 5.8253 | 12.9143 | 428.6072 | 11561.7138 | 643.9622 | 1.6853 | 15.5627 | 1.0561 | 0.00090774 | 0.0011454 | 0.62568 | 0.83185 | {99F2526F-2899-4B39-B406-E2CDF8F64831} | 192171101 | WILLOW CREEK 1101 | 5002 | 40.9462 | -123.6409 | WILLOW CREEK 11015002 | 291 | 458 | 32479.0456 | 22363.0953 | 10115.9503 | 21536.2249 | 9476.6482 | 0.22221 | 0.028222 | 1.409 | 10.4794 | 345 | 0.1761 | 1590 | 0 | 0 | 13.382 | 844 | 0
North Valley | 9481 | 91 | 112.2619 | 290 | 212.6983 | 94 | 8.9039e-06 | 80.5449 | 1.7733 | 203.9505 | 2723.5418 | 16.9665 | 1.2697 | 56.323 | 1.1067 | 0.0008952 | 1.47e-05 | 0.31379 | 0.5278 | {1667C171-4E6E-402D-B45F-3BA2B8FB113A} | 102812101 | BIG MEADOWS 2101 | 2248 | 40.1705 | -121.0807 | BIG MEADOWS 21012248 | 41 | 17 | 15626.8117 | 14718.1001 | 908.7116 | 14718.1001 | 908.7116 | 0.0013818 | 0.00083697 | 1.2336 | 3.0851 | 2711 | 0.084149 | 1591 | 0 | 0 | 9.1454 | 2488 | 0
North Valley | 8645 | 260 | 334.71 | 586 | 501.9296 | 92 | 4.4914e-05 | 20.2302 | 3.2066 | 322.8642 | 6026.6879 | 163.7485 | 1.5518 | 37.377 | 1.118 | 0.00089464 | 8.5439e-05 | 0.44369 | 0.66685 | {DBAB12BB-6159-4B5E-9921-C1747473FB98} | 103611101 | WILDWOOD 1101 | 85112 | 40.3872 | -123.0458 | WILDWOOD 110185112 | 72 | 67 | 12621.3495 | 10853.0331 | 1768.3163 | 10853.0331 | 1768.3163 | 0.0078604 | 0.0041321 | 1.2873 | 6.3696 | 1942 | 0.082307 | 1592 | 0 | 0 | 6.7438 | 1276 | 0
Sierra | 2795 | 490 | 740.7061 | 1134 | 1015.2322 | 100 | 0.00013601 | 6.0033 | 4.7314 | 5.799 | 17.5863 | 0.30296 | 0.73467 | 2.655 | 1.3131 | 0.00089425 | 0.00038097 | 0.4321 | 0.72959 | {38A00224-A460-485C-A9CC-938D2D423308} | 153081112 | PLACERVILLE 1112 | 19742 | 38.731 | -120.8097 | PLACERVILLE 111219742 | 225 | 555 | 34467.9615 | 11949.352 | 22518.6095 | 9960.0097 | 19855.5409 | 0.038097 | 0.013601 | 1.5116 | 11.34 | 966 | 0.089425 | 1593 | 0 | 0 | 6.1889 | 1247 | 0
Central Valley | 8291 | 34 | 51.556 | 147 | 89.3628 | 30 | 3.4259e-05 | 30.8235 | 11.0606 | 560.9518 | 2244.7851 | 116.3366 | 4.4782 | 201.6621 | 1.2029 | 0.00088921 | 0.00020709 | 0.23129 | 0.57693 | {9E89ADDE-355B-4153-8A3A-140410223CE4} | 163341103 | CLAY 1103 | 7142 | 38.3168 | -120.9416 | CLAY 11037142 | 112 | 100 | 31804.4007 | 24816.4121 | 6987.9887 | 5016.468 | 1745.2618 | 0.0062127 | 0.0010278 | 1.5164 | 4.9 | 1391 | 0.026676 | 1594 | 0 | 0 | 3.1171 | 814 | 0
North Coast | 1670 | 53 | 104.7344 | 168 | 153.3234 | 28 | 7.0398e-05 | 13.9459 | 0.18074 | 0.23969 | 1.8002 | 0.00082883 | 1.1685 | 40.1293 | 1.0936 | 0.00088871 | 2.875e-05 | 0.31548 | 0.68309 | {97FE1380-8BE3-42D2-B6E3-D4904D2C8F20} | 43351106 | LUCERNE 1106 | 76850 | 39.0915 | -122.797 | LUCERNE 110676850 | 108 | 524 | 28247.9491 | 5965.4962 | 22282.4529 | 2991.9456 | 8445.1915 | 0.00080501 | 0.0019711 | 1.9761 | 6 | 2481 | 0.024884 | 1595 | 0 | 0 | 1.8591 | 245 | 0
Central Valley | 2092 | 445 | 650.675 | 1708 | 1197.0365 | 224 | 5.8988e-05 | 14.8101 | 41.2019 | 535.6255 | 5710.851 | 612.651 | 3.7973 | 118.6069 | 1.3038 | 0.0008884 | 0.0012638 | 0.26054 | 0.54357 | {BB6FF44B-32EF-4B9B-B3A4-B0CE69F543D6} | 163451701 | FROGTOWN 1701 | 1623 | 38.1247 | -120.45 | FROGTOWN 17011623 | 196 | 181 | 38467.1418 | 24542.3809 | 13924.761 | 24542.3809 | 13924.761 | 0.28309 | 0.013213 | 1.4622 | 7.625 | 300 | 0.199 | 1596 | 0 | 0 | 15.2499 | 809 | 0
Central Coast | 7075 | 31 | 47.8434 | 103 | 89.3651 | 42 | 3.5256e-05 | 31.5952 | 0.37163 | 572.7532 | 2964.3707 | 3.0124 | 2.489 | 272.4367 | 1.42 | 0.00088751 | 2.3431e-05 | 0.30097 | 0.53537 | {D648C2D0-CEEA-4B72-A49B-959B06BED9AA} | 182671108 | SANTA MARIA 1108 | M18 | 34.9721 | -120.4019 | SANTA MARIA 1108M18 | 99 | 88 | 32573.8488 | 28755.1345 | 3818.7143 | 23036.475 | 2867.6798 | 0.00098412 | 0.0014807 | 1.5433 | 2.4524 | 2558 | 0.037275 | 1597 | 0 | 0 | 14.3142 | 2459 | 0
Central Coast | 1456 | 1691 | 3417.3028 | 2453 | 3834.7185 | 141 | 0.00024451 | 3.7768 | 12.0567 | 22.689 | 104.3199 | 1.6357 | 0.56482 | 5.9116 | 0.99551 | 0.00088617 | 0.0014736 | 0.68936 | 0.89115 | {97243609-0190-4CA4-910D-8656166A7529} | 83041101 | BEN LOMOND 1101 | BL 1101 | 37.0926 | -122.0966 | BEN LOMOND 1101BL 1101 | 199 | 614 | 41287.4724 | 13712.9137 | 27574.5587 | 13712.9137 | 27574.5587 | 0.20778 | 0.034475 | 2.0209 | 17.3972 | 253 | 0.12495 | 1598 | 0 | 0 | 8.5208 | 1866 | 0
Central Coast | 7660 | 419 | 719.628 | 1004 | 1048.015 | 69 | 0.00013807 | 6.2663 | 3.9535 | 33.7112 | 227.4847 | 1.5552 | 1.1999 | 12.5059 | 1.0646 | 0.00088263 | 0.0003156 | 0.41733 | 0.68666 | {F761DD80-845B-4F29-ADA0-4CE9C4A1F615} | 83622106 | CAMP EVERS 2106 | 12840 | 37.0539 | -121.9547 | CAMP EVERS 210612840 | 78 | 66 | 10925.1046 | 6527.3425 | 4397.7621 | 6527.3425 | 4397.7621 | 0.021777 | 0.0095267 | 1.7175 | 14.5507 | 1092 | 0.060901 | 1599 | 0 | 0 | 4.0559 | 1716 | 0
Sierra | 3103 | 2166 | 3026.1431 | 4903 | 4376.1313 | 447 | 0.00010769 | 10.7826 | 16.3546 | 114.9846 | 1441.3331 | 197.5413 | 1.9346 | 24.4712 | 1.0646 | 0.00088095 | 0.00069465 | 0.44177 | 0.69151 | {EDF4431E-F5AF-4806-91E5-400DCB7DFCFA} | 152481106 | BRUNSWICK 1106 | 2416 | 39.159 | -121.0398 | BRUNSWICK 11062416 | 638 | 930 | 105830.275 | 49911.7707 | 55918.5043 | 45937.2563 | 49988.2518 | 0.31051 | 0.048136 | 1.3971 | 10.9687 | 571 | 0.39379 | 1600 | 0 | 0 | 28.5441 | 536 | 0
North Coast | 296 | 329 | 488.181 | 708 | 694.3695 | 52 | 0.00015349 | 6.0158 | 5.2021 | 54.6117 | 373.8506 | 2.9352 | 0.77204 | 19.0671 | 1.0517 | 0.00087538 | 0.00047037 | 0.46469 | 0.70306 | {173229A0-9A6C-4AB5-8BBC-51112D47DF20} | 42811111 | MONTE RIO 1111 | 64758 | 38.5089 | -123.0696 | MONTE RIO 111164758 | 175 | 353 | 33862.5503 | 17002.078 | 16860.4724 | 17002.078 | 16860.4724 | 0.024459 | 0.0079817 | 1.4838 | 13.6154 | 827 | 0.04552 | 1601 | 0 | 0 | 10.5646 | 49 | 0
Bay Area | 5156 | 17 | 34.5482 | 66 | 61.3705 | 13 | 1.2811e-05 | 111.2336 | 2.0256 | 47.889 | 160.0139 | 1.5839 | 7.5713 | 317.8952 | 1.2287 | 0.00087029 | 1.3862e-05 | 0.25758 | 0.56295 | {E96A0569-DCDE-4681-A6D1-E506A3CBE6D9} | 12022212 | CLAYTON 2212 | circuit_breaker | 37.9443 | -121.9699 | CLAYTON 2212circuit_breaker | 375 | 731 | 56935.6901 | 20442.1182 | 36493.572 | 3174.2004 | 989.104 | 0.00018021 | 0.00016654 | 2.0322 | 5.0769 | 2725 | 0.011314 | 1602 | 0 | 0 | 1.9724 | 395 | 0
North Valley | 1156 | 3142 | 4439.5766 | 6443 | 5821.072 | 378 | 0.0001161 | 11.6393 | 39.6948 | 234.5195 | 3842.8223 | 572.2162 | 0.51139 | 7.3731 | 1.0854 | 0.000868 | 0.0018359 | 0.48766 | 0.76267 | {4F055C2B-F555-47EE-931F-D64958E5EDAE} | 103031101 | ORO FINO 1101 | circuit_breaker | 39.8717 | -121.6109 | ORO FINO 1101circuit_breaker | 635 | 1571 | 121427.8922 | 39834.6591 | 81593.2331 | 39834.6591 | 81593.2331 | 0.69398 | 0.043886 | 1.413 | 17.045 | 190 | 0.32811 | 1603 | 0 | 0 | 24.7521 | 1671 | 0
Sierra | 6048 | 295 | 382.5831 | 1951 | 1148.8615 | 207 | 1.9286e-05 | 44.7579 | 7.2364 | 424.8216 | 8789.2573 | 249.5638 | 0.56265 | 13.6586 | 1.0209 | 0.0008663 | 7.8029e-05 | 0.1512 | 0.33301 | {3CE7580A-70EA-45BB-B025-A0DE44571BB4} | 152321101 | DRUM 1101 | 1602 | 39.2517 | -120.75 | DRUM 11011602 | 165 | 229 | 37214.9146 | 26765.8492 | 10449.0655 | 26765.8492 | 10449.0655 | 0.016152 | 0.0039922 | 1.2969 | 9.4251 | 1999 | 0.17932 | 1604 | 0 | 0 | 16.6315 | 1644 | 0
Central Valley | 7933 | 6 | 15.1475 | 73 | 29.4459 | 20 | 3.2138e-05 | 29.9256 | 15.6855 | 1617.6414 | 8043.0663 | 178.6548 | 7.0501 | 162.5637 | 1.2976 | 0.00085771 | 0.00022481 | 0.082192 | 0.51442 | {E4D16BCD-AE1D-4E84-9AC4-94D1A6F08214} | 252811102 | MERCED FALLS 1102 | 22772 | 37.6288 | -120.308 | MERCED FALLS 110222772 | 37 | 42 | 8090.2848 | 3605.0516 | 4485.2332 | 3605.0516 | 4485.2332 | 0.0044963 | 0.00064277 | 2.5246 | 3.65 | 1327 | 0.017154 | 1605 | 0 | 0 | 2.2401 | 2738 | 0
Central Coast | 6297 | 110 | 169.4783 | 1014 | 740.7668 | 204 | 2.5576e-05 | 33.9681 |  |  |  |  | 4.3934 | 220.5243 | 1.2602 | 0.00085758 | 2.5576e-05 | 0.10848 | 0.22879 | {BE479CE6-8809-4A3B-A6FB-86A2FCDE06C2} | 182811103 | SISQUOC 1103 | M14 | 34.8831 | -120.2779 | SISQUOC 1103M14 | 287 | 244 | 79997.4768 | 52362.2316 | 27635.2452 | 32732.59 | 21409.7734 | 0.0052176 | 0.0052176 | 1.5407 | 4.9706 | 2527 | 0.17495 | 1606 | 0 | 0 | 20.3391 | 1802 | 0
Bay Area | 3317 | 407 | 787.6426 | 1059 | 1158.002 | 92 | 7.1193e-05 | 12.7563 | 3.4675 | 34.1851 | 263.1622 | 4.6747 | 0.30454 | 23.5258 | 1.0841 | 0.00085633 | 0.00013823 | 0.38432 | 0.68017 | {24FD9F9F-3AE5-44A3-85E5-C29F5C852455} | 42261101 | BOLINAS 1101 | 504 | 37.9343 | -122.6968 | BOLINAS 1101504 | 86 | 42 | 16220.4768 | 10763.1712 | 5457.3056 | 10456.414 | 5457.3056 | 0.012717 | 0.0065497 | 1.9352 | 11.5109 | 1640 | 0.078783 | 1607 | 0 | 0 | 6.4973 | 199 | 0
Bay Area | 4944 | 431 | 795.656 | 1294 | 1329.6989 | 71 | 0.00014019 | 5.0904 | 1.9714 | 25.5647 | 138.9975 | 1.6572 | 0.6854 | 3.4423 | 1.0036 | 0.00085566 | 0.00021264 | 0.33308 | 0.59837 | {429461DA-3754-40D0-8283-6B07C0ED0208} | 24251101 | WOODSIDE 1101 | 8912 | 37.3899 | -122.2394 | WOODSIDE 11018912 | 97 | 65 | 9766.539 | 6396.0491 | 3370.4899 | 6353.9227 | 3370.4899 | 0.015098 | 0.0099533 | 1.8461 | 18.2254 | 1373 | 0.060752 | 1608 | 0 | 0 | 3.9481 | 1835 | 0
Central Valley | 6928 | 122 | 201.5965 | 514 | 343.6936 | 60 | 7.2299e-05 | 15.5497 | 8.2663 | 128.7172 | 1012.2822 | 28.4183 | 0.80029 | 16.6195 | 1.0471 | 0.00085557 | 0.0002498 | 0.23735 | 0.58656 | {677BC4CE-74C4-4870-9B50-45491FB41EEF} | 163351704 | CURTIS 1704 | 6060 | 37.9892 | -120.3331 | CURTIS 17046060 | 89 | 179 | 15197.4302 | 6649.044 | 8548.3862 | 6649.044 | 8548.3862 | 0.014988 | 0.0043379 | 1.6524 | 8.5667 | 1249 | 0.051334 | 1609 | 0 | 0 | 4.1315 | 1404 | 0
Sierra | 340 | 75 | 96.7545 | 187 | 146.6925 | 27 | 7.0528e-05 | 12.3937 | 31.0028 | 257.0959 | 3709.3372 | 296.3803 | 0.12021 | 20.5317 | 1.0188 | 0.00085352 | 0.0010303 | 0.40107 | 0.65957 | {EDC3C6AA-B200-49D0-AFDA-73B9844EB8E4} | 152481105 | BRUNSWICK 1105 | 2204 | 39.2643 | -120.9858 | BRUNSWICK 11052204 | 167 | 137 | 21910.8094 | 11642.89 | 10267.9193 | 11642.89 | 10267.9193 | 0.027819 | 0.0019043 | 1.2901 | 6.9259 | 395 | 0.023045 | 1610 | 0 | 0 | 7.2346 | 197 | 0
Central Valley | 970 | 123 | 194.283 | 598 | 400.8969 | 93 | 5.4731e-05 | 16.5731 | 8.7836 | 194.7422 | 993.5464 | 23.6717 | 3.0574 | 93.1375 | 1.2338 | 0.00085182 | 0.00030768 | 0.20569 | 0.48462 | {CC00F970-8F13-4247-87D9-81AC67764BAD} | 163451701 | FROGTOWN 1701 | circuit_breaker | 38.057 | -120.5335 | FROGTOWN 1701circuit_breaker | 119 | 108 | 22564.5999 | 17920.0747 | 4644.5253 | 16003.3182 | 2624.6453 | 0.028614 | 0.00509 | 1.5795 | 6.4301 | 1104 | 0.079219 | 1611 | 0 | 0 | 9.944 | 2340 | 0
Central Coast | 286 | 2357 | 4009.689 | 4209 | 5071.2866 | 312 | 0.00013922 | 6.2402 | 4.8744 | 39.3826 | 165.9645 | 1.2929 | 0.63319 | 13.9105 | 1.0289 | 0.00084831 | 0.00038463 | 0.55999 | 0.79067 | {6AB8FDF6-DF60-4669-94F5-76C04F7F5767} | 82841101 | BIG BASIN 1101 | 69550 | 37.1319 | -122.1095 | BIG BASIN 110169550 | 328 | 398 | 52726.391 | 28833.0726 | 23893.3184 | 28833.0726 | 23893.3184 | 0.12 | 0.043435 | 1.7012 | 13.4904 | 961 | 0.26467 | 1612 | 0 | 0 | 17.916 | 958 | 0
North Coast | 639 | 7 | 8.7465 | 38 | 26.436 | 6 | 9.9074e-05 | 8.0253 | 0.27281 | 175.4693 | 1505.0988 | 0.82122 | 1.6645 | 13.917 | 1.0173 | 0.000848 | 7.2833e-05 | 0.18421 | 0.33086 | {45DAEF94-8CBC-41FA-B3AC-23C4DF1DF209} | 43321101 | RINCON 1101 | 580 | 38.464 | -122.6514 | RINCON 1101580 | 91 | 201 | 14190.6461 | 4616.0468 | 9574.5993 | 541.3735 | 113.5355 | 0.000437 | 0.00059445 | 1.2495 | 6.3333 | 2039 | 0.005088 | 1613 | 0 | 0 | 0.33639 | 2182 | 0
Central Valley | 4775 | 270 | 356.7391 | 869 | 617.6007 | 99 | 9.8669e-05 | 9.1046 | 6.6691 | 276.0237 | 3097.5837 | 55.551 | 1.5692 | 53.6056 | 1.1718 | 0.00084088 | 0.00042679 | 0.3107 | 0.57762 | {6211F369-8BB0-4A6F-AF12-1490B4F377A4} | 163201102 | WEST POINT 1102 | 77204 | 38.3444 | -120.5828 | WEST POINT 110277204 | 100 | 80 | 14499.0762 | 11906.8331 | 2592.2431 | 11906.8331 | 2592.2431 | 0.042253 | 0.0097682 | 1.3213 | 8.7778 | 898 | 0.083247 | 1614 | 0 | 0 | 7.3986 | 2774 | 0
North Coast | 6941 | 15 | 29.127 | 17 | 29.981 | 6 | 9.9586e-05 | 8.1431 | 0 | 0.15103 | 0.43481 | 0 | 8.384e-16 | 83.8853 | 1.2146 | 0.00084062 | 4.5387e-05 | 0.88235 | 0.97151 | {7897A070-7C30-42E9-B1B0-EB5E015E733B} | 43061101 | COVELO 1101 | 536 | 39.7439 | -123.2485 | COVELO 1101536 | 85 | 70 | 40352.1853 | 35716.0554 | 4636.1299 | 15104.7289 | 499.5351 | 0.00027232 | 0.00059752 | 1.9418 | 2.8333 | 2279 | 0.0050437 | 1615 | 0 | 0 | 9.3856 | 17 | 0
Central Valley | 9097 | 25 | 34.2823 | 204 | 84.8514 | 64 | 9.0138e-06 | 107.3868 | 2.4472 | 1533.107 | 7570.0928 | 27.9672 | 4.9002 | 1262.036 | 1.8379 | 0.00083763 | 1.4587e-05 | 0.12255 | 0.40403 | {1C32E9CE-3898-49FE-891B-A309867CC97B} | 254601103 | SAND CREEK 1103 | 97354 | 36.6098 | -119.0982 | SAND CREEK 110397354 | 76 | 50 | 18909.0102 | 16295.7352 | 2613.275 | 13531.0761 | 1321.1137 | 0.00093356 | 0.00057689 | 1.3713 | 3.1875 | 2714 | 0.053608 | 1616 | 0 | 0 | 8.4078 | 2230 | 0
Central Valley | 7802 | 130 | 187.8389 | 604 | 427.4 | 133 | 3.4315e-05 | 27.2673 | 35.5523 | 1668.4932 | 22565.1261 | 1186.912 | 1.4151 | 50.4235 | 1.1475 | 0.00083616 | 0.00062137 | 0.21523 | 0.43949 | {F76AEDBB-91E0-4407-A41D-F6794405D1E1} | 252192105 | BEAR VALLEY 2105 | 13430 | 37.7501 | -120.1363 | BEAR VALLEY 210513430 | 180 | 126 | 35348.794 | 21403.3287 | 13945.4653 | 21403.3287 | 13945.4653 | 0.082642 | 0.0045638 | 1.4449 | 4.5414 | 648 | 0.11121 | 1617 | 0 | 0 | 13.2994 | 167 | 0
North Coast | 4763 | 13 | 24.9055 | 34 | 34.6174 | 6 | 0.00010446 | 7.989 | 8.7976 | 212.2182 | 2624.8534 | 55.8804 | 0.96165 | 6.3393 | 1.0107 | 0.00083392 | 0.00065507 | 0.38235 | 0.71945 | {271E7E9C-640A-4CFE-9B9C-B8B9EB8F49E3} | 43081101 | BIG RIVER 1101 | 3019 | 39.3431 | -123.8124 | BIG RIVER 11013019 | 18 | 20 | 2840.743 | 1511.0833 | 1329.6597 | 423.4937 | 281.5124 | 0.0039304 | 0.00062676 | 1.9158 | 5.6667 | 609 | 0.0050035 | 1618 | 0 | 0 | 0.26315 | 1524 | 0
Central Valley | 3842 | 529 | 732.8682 | 1784 | 1313.3206 | 249 | 3.1991e-05 | 25.9937 | 5.2661 | 107.8394 | 813.2379 | 11.8544 | 2.4344 | 77.5457 | 1.2526 | 0.00083369 | 9.5794e-05 | 0.29652 | 0.55803 | {CC22620A-5BA3-4EC5-B4A7-D508D0CFED84} | 254151101 | AUBERRY 1101 | R319 | 37.053 | -119.3706 | AUBERRY 1101R319 | 225 | 205 | 47861.3808 | 33658.5688 | 14202.812 | 33658.5688 | 14202.812 | 0.023853 | 0.0079657 | 1.3854 | 7.1647 | 1873 | 0.20759 | 1619 | 0 | 0 | 20.9145 | 1791 | 0
Sierra | 484 | 456 | 688.6478 | 1333 | 1098.8789 | 123 | 9.9539e-05 | 9.1624 | 68.4607 | 611.4961 | 8099.4875 | 1074.3164 | 2.7447 | 27.34 | 1.064 | 0.00083188 | 0.0033286 | 0.34209 | 0.62668 | {52CBF115-6640-4F98-9743-613A61123F02} | 152481110 | BRUNSWICK 1110 | 2664 | 39.235 | -121.0604 | BRUNSWICK 11102664 | 224 | 591 | 44616.6772 | 17466.8136 | 27149.8636 | 12678.4586 | 10071.9876 | 0.40942 | 0.012243 | 1.5102 | 10.8374 | 85 | 0.10232 | 1620 | 0 | 0 | 7.878 | 948 | 0
Central Valley | 2744 | 1981 | 2780.9639 | 5646 | 4469.276 | 589 | 9.5028e-05 | 8.6196 | 16.4593 | 199.6767 | 2417.7091 | 152.5636 | 2.2817 | 33.4189 | 1.081 | 0.00082963 | 0.00081683 | 0.35087 | 0.62224 | {207F56DE-FF3F-4FB6-9F25-8FC555D28285} | 163751101 | PINE GROVE 1101 | 3170 | 38.415 | -120.6852 | PINE GROVE 11013170 | 686 | 618 | 98232.0449 | 64707.4468 | 33524.5981 | 64707.4468 | 33524.5981 | 0.48112 | 0.055971 | 1.4038 | 9.5857 | 489 | 0.48865 | 1621 | 0 | 0 | 40.2073 | 637 | 0
North Coast | 771 | 627 | 873.3133 | 1313 | 1257.4352 | 73 | 0.00014943 | 5.2779 | 4.4339 | 10.6671 | 41.536 | 0.67795 | 0.66302 | 1.9282 | 0.98964 | 0.00082499 | 0.00046978 | 0.47753 | 0.69452 | {C5E1652A-2EB6-4FD0-B328-E1AC1FDEB33B} | 42091102 | MIRABEL 1102 | circuit_breaker | 38.4893 | -122.894 | MIRABEL 1102circuit_breaker | 313 | 1038 | 65251.8776 | 18129.1338 | 47122.7438 | 7538.7631 | 24518.3358 | 0.034294 | 0.010908 | 1.3928 | 17.9863 | 829 | 0.060224 | 1622 | 0 | 0 | 4.6844 | 1725 | 0
Central Coast | 4706 | 186 | 329.5683 | 494 | 519.249 | 38 | 6.085e-05 | 13.8259 | 29.0248 | 92.491 | 1427.6532 | 115.6056 | 0.36755 | 3.8333 | 1.0031 | 0.0008229 | 0.0010877 | 0.37652 | 0.6347 | {9DDD43C5-588F-4D1E-AFA3-8A122C419F83} | 83500401 | SEACLIFF 0401 | 12946 | 36.9876 | -121.9186 | SEACLIFF 040112946 | 68 | 434 | 28208.1591 | 5200.6844 | 23007.4747 | 3742.632 | 13642.9675 | 0.041333 | 0.0023123 | 1.7719 | 13 | 366 | 0.03127 | 1623 | 0 | 0 | 2.3256 | 691 | 0
North Valley | 8495 | 149 | 174.3507 | 341 | 256.2518 | 27 | 9.5984e-05 | 7.9921 | 22.914 | 597.4002 | 9416.4579 | 287.2795 | 0.49615 | 12.51 | 1.0075 | 0.00081928 | 0.0010123 | 0.43695 | 0.68039 | {4BB60C53-9CA3-4098-8B28-FE44C4ECF9D3} | 103031102 | ORO FINO 1102 | circuit_breaker | 39.8717 | -121.6109 | ORO FINO 1102circuit_breaker | 54 | 46 | 5340.436 | 3368.9824 | 1971.4536 | 3368.9824 | 1971.4536 | 0.027333 | 0.0025916 | 1.1701 | 12.6296 | 406 | 0.022121 | 1624 | 0 | 0 | 2.0934 | 664 | 0
North Valley | 2692 | 6 | 10.1235 | 9 | 11.4185 | 6 | 2.1247e-05 | 45.3449 | 12.4938 | 3550.1125 | 36435.5006 | 817.7172 | 0.88459 | 289.6134 | 1.4406 | 0.00081837 | 0.00015775 | 0.66667 | 0.88659 | {0F8042BD-810A-4C9D-833A-F377AF6EE4DF} | 102541101 | VOLTA 1101 | 53118 | 40.4011 | -121.875 | VOLTA 110153118 | 63 | 44 | 18856.5276 | 15490.2629 | 3366.2647 | 15490.2629 | 3366.2647 | 0.00094649 | 0.00012748 | 1.6872 | 1.5 | 1553 | 0.0049102 | 1625 | 0 | 0 | 9.6252 | 246 | 0
Central Valley | 3413 | 1 | 0.97225 | 50 | 13.623 | 9 | 5.257e-05 | 13.9538 | 7.5355 | 1219.4983 | 8313.9973 | 130.2013 | 5.7672 | 141.453 | 1.1192 | 0.00081696 | 0.00036073 | 0.02 | 0.071368 | {277F84D3-A270-449A-A58E-FDC1A84261F4} | 163011101 | MARTELL 1101 | 98374 | 38.3904 | -120.804 | MARTELL 110198374 | 113 | 279 | 15281.5346 | 6135.709 | 9145.8256 | 936.3607 | 334.2878 | 0.0032465 | 0.00047313 | 0.97225 | 5.5556 | 999 | 0.0073527 | 1626 | 0 | 0 | 0.58183 | 1499 | 0
North Valley | 2210 | 1 | 1.945 | 13 | 6.0012 | 5 | 4.7209e-05 | 19.0894 | 25.1551 | 41.3654 | 93.1017 | 2.342 | 5.8956 | 78.6614 | 1.2146 | 0.00081142 | 0.0002335 | 0.076923 | 0.3241 | {7E65FB86-04AD-4769-9FF1-1417B3FD7311} | 102911110 | WYANDOTTE 1110 | 1952 | 39.499 | -121.5301 | WYANDOTTE 11101952 | 206 | 702 | 43160.7297 | 13999.1345 | 29161.5951 | 417.0111 | 153.9474 | 0.0011675 | 0.00023604 | 1.945 | 2.6 | 1302 | 0.0040571 | 1627 | 0 | 0 | 0.25912 | 1540 | 0
Central Coast | 8519 | 299 | 530.492 | 740 | 771.0477 | 175 | 1.7078e-05 | 41.362 | 1.8405 | 193.6551 | 889.6906 | 3.3905 | 2.1672 | 207.3159 | 1.237 | 0.00080925 | 2.0883e-05 | 0.40405 | 0.68801 | {D078310A-A59A-4DF4-876C-B326130655F6} | 83392110 | SWIFT 2110 | XR254 | 37.334 | -121.7559 | SWIFT 2110XR254 | 158 | 93 | 45771.9089 | 39910.094 | 5861.8149 | 39910.094 | 5861.8149 | 0.0036546 | 0.0029886 | 1.7742 | 4.2286 | 2591 | 0.14162 | 1628 | 0 | 0 | 24.799 | 584 | 0
Central Valley | 6601 | 4 | 7.0341 | 34 | 21.1478 | 10 | 1.2441e-05 | 105.1047 | 0.031745 | 512.0186 | 10175.949 | 1.2357 | 0.30044 | 63.5711 | 1.1341 | 0.00080821 | 6.9037e-06 | 0.11765 | 0.33262 | {3B618A90-1F99-49FA-8702-76A28A158E81} | 163692101 | SALT SPRINGS 2101 | 10416 | 38.4983 | -120.2183 | SALT SPRINGS 210110416 | 15 | 13 | 1591.5 | 928.207 | 663.293 | 928.207 | 663.293 | 6.9037e-05 | 0.00012441 | 1.7585 | 3.4 | 2825 | 0.0080821 | 1629 | 0 | 0 | 0.57676 | 1923 | 0
Central Coast | 8127 | 34 | 58.8042 | 50 | 67.2864 | 7 | 0.00021546 | 3.4636 | 13.7632 | 33.9758 | 212.3526 | 5.5554 | 0.18995 | 3.5262 | 1.0136 | 0.0008057 | 0.0010575 | 0.68 | 0.87394 | {B2DB007C-B536-4565-AFB8-FF22CE3BFDE5} | 83140401 | FELTON 0401 | circuit_breaker | 37.0489 | -122.0646 | FELTON 0401circuit_breaker | 48 | 55 | 6269.6055 | 4116.7901 | 2152.8154 | 3781.4684 | 1784.8535 | 0.0074023 | 0.0015082 | 1.7295 | 7.1429 | 382 | 0.0056399 | 1630 | 0 | 0 | 2.3497 | 2249 | 0
Central Valley | 3329 | 546 | 670.4547 | 3728 | 2129.3142 | 241 | 0.00012542 | 7.0708 | 125.7497 | 3082.2327 | 52858.6781 | 11288.5653 | 1.6476 | 27.4157 | 1.1587 | 0.00080471 | 0.0084954 | 0.14646 | 0.31487 | {D284AD02-1208-4AE0-8968-E88D8134BCC9} | 163751102 | PINE GROVE 1102 | 13438 | 38.4738 | -120.6266 | PINE GROVE 110213438 | 267 | 311 | 48149.6017 | 26763.0781 | 21386.5236 | 26763.0781 | 21386.5236 | 2.0474 | 0.030226 | 1.2279 | 15.4689 | 15 | 0.19393 | 1631 | 0 | 0 | 16.6298 | 1072 | 0
Central Coast | 362 | 1474 | 2678.087 | 1964 | 2951.0847 | 134 | 8.1138e-05 | 11.7822 | 7.0894 | 68.6297 | 425.7762 | 5.6807 | 1.3083 | 20.1319 | 1.0416 | 0.00080462 | 0.000316 | 0.75051 | 0.90749 | {FA346406-A3D0-4066-8116-4806F77ED4DD} | 82931101 | POINT MORETTI 1101 | 5078 | 37.0315 | -122.1867 | POINT MORETTI 11015078 | 256 | 239 | 38071.4107 | 23596.4557 | 14474.955 | 23596.4557 | 14474.955 | 0.042344 | 0.010872 | 1.8169 | 14.6567 | 1089 | 0.10782 | 1632 | 0 | 0 | 14.6622 | 311 | 0
Central Valley | 1352 | 130 | 194.6026 | 751 | 413.1885 | 184 | 4.6196e-05 | 14.1783 | 18.8866 | 1813.238 | 12724.6379 | 428.8351 | 2.5712 | 138.162 | 1.183 | 0.00080384 | 0.00036558 | 0.1731 | 0.47098 | {275411B9-F65E-4C2D-AC92-04E91C75A810} | 163451702 | FROGTOWN 1702 | 11212 | 38.0863 | -120.5718 | FROGTOWN 170211212 | 190 | 153 | 45775.7705 | 34480.8483 | 11294.9223 | 34480.8483 | 11294.9223 | 0.067267 | 0.0085001 | 1.4969 | 4.0815 | 991 | 0.14791 | 1633 | 0 | 0 | 21.4254 | 1046 | 0
Sierra | 2217 | 331 | 438.5849 | 1248 | 860.1938 | 158 | 3.172e-05 | 24.9614 | 3.8718 | 421.1493 | 10044.3599 | 297.9483 | 0.35919 | 34.0242 | 1.1979 | 0.00080147 | 8.4836e-05 | 0.26522 | 0.50987 | {20EA6D57-AE8A-4389-B5E9-F8A1FC109811} | 152762101 | EL DORADO PH 2101 | 52456 | 38.7754 | -120.4024 | EL DORADO PH 210152456 | 169 | 426 | 30388.3486 | 16414.576 | 13973.7727 | 16414.576 | 13973.7727 | 0.013404 | 0.0050118 | 1.325 | 7.8987 | 1954 | 0.12663 | 1634 | 0 | 0 | 10.1995 | 656 | 0
North Coast | 6999 | 700 | 956.4631 | 1147 | 1184.8525 | 108 | 0.00020804 | 3.3755 | 2.0617 | 440.2922 | 8366.3742 | 83.6638 | 0.18791 | 24.1525 | 1.0742 | 0.00079974 | 0.00029429 | 0.61029 | 0.80724 | {1D151194-CF04-464D-9004-1F697BF4DA48} | 192171101 | WILLOW CREEK 1101 | 29362 | 40.8941 | -123.7726 | WILLOW CREEK 110129362 | 96 | 47 | 22014.7507 | 18629.0665 | 3385.6842 | 11564.4444 | 2190.593 | 0.031784 | 0.022468 | 1.3664 | 10.6204 | 1140 | 0.086372 | 1635 | 0 | 0 | 7.1858 | 763 | 0
North Valley | 4276 | 641 | 848.8815 | 1403 | 1203.9037 | 213 | 8.7817e-05 | 8.9809 | 25.1239 | 531.5638 | 4683.0757 | 237.1672 | 5.1566 | 92.1331 | 1.1492 | 0.00079338 | 0.0013018 | 0.45688 | 0.70511 | {1DE99E4E-7765-44B0-9832-275F1EB7F7A4} | 103091102 | CLARK ROAD 1102 | 90548 | 39.6945 | -121.5252 | CLARK ROAD 110290548 | 249 | 217 | 44185.45 | 29415.2854 | 14770.1647 | 29415.2854 | 14770.1647 | 0.27728 | 0.018705 | 1.3243 | 6.5869 | 295 | 0.16899 | 1636 | 0 | 0 | 18.2778 | 1040 | 0
Central Valley | 2656 | 114 | 172.6968 | 376 | 280.6755 | 51 | 9.7234e-05 | 8.0132 | 18.0058 | 147.0177 | 702.8108 | 41.0969 | 2.7774 | 29.7745 | 1.1108 | 0.00079055 | 0.00065227 | 0.30319 | 0.61529 | {50E0B9CF-D877-44E3-8923-B1CAE75FDAA7} | 163781705 | PEORIA 1705 | 67898 | 37.9582 | -120.4385 | PEORIA 170567898 | 130 | 168 | 18622.9986 | 9738.6344 | 8884.3642 | 5781.6377 | 4501.9575 | 0.033266 | 0.0049589 | 1.5149 | 7.3725 | 616 | 0.040318 | 1637 | 0 | 0 | 3.5925 | 728 | 0
North Coast | 3021 | 698 | 1554.9762 | 911 | 1668.7521 | 44 | 0.0001241 | 6.0107 | 8.3704 | 68.8731 | 578.7183 | 11.6756 | 1.1358 | 15.8358 | 1.0397 | 0.00079038 | 0.00057134 | 0.76619 | 0.93182 | {EF630F9A-72E2-42EA-B074-23D3C9859856} | 42811113 | MONTE RIO 1113 | 320 | 38.4989 | -123.0211 | MONTE RIO 1113320 | 52 | 125 | 9822.8228 | 4416.0265 | 5406.7963 | 4416.0265 | 5406.7963 | 0.025139 | 0.0054604 | 2.2278 | 20.7045 | 708 | 0.034777 | 1638 | 0 | 0 | 2.744 | 646 | 0
North Coast | 2336 | 4013 | 6979.5674 | 4396 | 7156.8916 | 335 | 0.00011087 | 7.3741 | 5.2813 | 50.375 | 358.8172 | 3.6288 | 0.51817 | 10.5294 | 1.021 | 0.00078662 | 0.00034139 | 0.91288 | 0.97522 | {6177229C-DB60-448B-B309-D4C2F1A2330C} | 42841112 | GUALALA 1112 | 1294 | 38.8037 | -123.5835 | GUALALA 11121294 | 407 | 415 | 55846.0538 | 32449.4042 | 23396.6496 | 31035.4817 | 21998.6753 | 0.11437 | 0.03714 | 1.7392 | 13.1224 | 1025 | 0.26352 | 1639 | 0 | 0 | 19.2845 | 435 | 0
Sierra | 4501 | 2666 | 4338.4594 | 5317 | 5561.4463 | 345 | 4.9305e-05 | 16.1928 | 66.9304 | 505.1276 | 9595.3953 | 2514.6694 | 0.57515 | 12.4386 | 1.085 | 0.00078293 | 0.001423 | 0.50141 | 0.7801 | {061B0891-9632-4691-9CF7-EFB012B2AC41} | 152481105 | BRUNSWICK 1105 | 2210 | 39.261 | -120.9817 | BRUNSWICK 11052210 | 474 | 648 | 73620.5601 | 36677.2724 | 36943.2876 | 36677.2724 | 36943.2876 | 0.49092 | 0.01701 | 1.6273 | 15.4116 | 267 | 0.27011 | 1640 | 0 | 0 | 22.7902 | 857 | 0
North Coast | 3309 | 38 | 63.3082 | 62 | 74.538 | 5 | 7.9711e-05 | 9.6442 | 6.3815 | 43.7172 | 168.1873 | 1.8811 | 6.7898 | 60.27 | 1.8102 | 0.00077912 | 0.00033506 | 0.6129 | 0.84934 | {1EA5CD6B-83B6-4AB6-830D-FD93A0E7328B} | 192151132 | NEWBURG 1132 | 3425 | 40.5951 | -124.1333 | NEWBURG 11323425 | 25 | 29 | 3957.953 | 2438.8597 | 1519.0933 | 360.086 | 357.2269 | 0.0016753 | 0.00039856 | 1.666 | 12.4 | 1043 | 0.0038956 | 1641 | 0 | 0 | 0.22375 | 598 | 0
Central Coast | 3373 | 1464 | 2313.5057 | 2849 | 3097.705 | 281 | 6.1538e-05 | 15.8127 | 2.9701 | 66.53 | 598.0548 | 4.2627 | 1.7762 | 29.9824 | 1.1066 | 0.00077604 | 0.00013455 | 0.51386 | 0.74685 | {E0F39461-5FDF-4E75-995C-8A6CC288C11A} | 82021107 | LOS GATOS 1107 | 60114 | 37.1188 | -121.9201 | LOS GATOS 110760114 | 335 | 300 | 64833.1622 | 39175.9013 | 25657.2609 | 39175.9013 | 25657.2609 | 0.037809 | 0.017292 | 1.5803 | 10.1388 | 1672 | 0.21807 | 1642 | 0 | 0 | 24.3428 | 2606 | 0
North Valley | 7389 | 1219 | 1684.9553 | 2308 | 2267.4685 | 280 | 1.5355e-05 | 55.4721 | 5.285 | 1245.0928 | 27676.0352 | 294.2864 | 0.70116 | 44.8419 | 1.1227 | 0.00077341 | 4.7205e-05 | 0.52816 | 0.7431 | {7FF9C2B4-7885-497B-BE5B-64337D7948AA} | 103021101 | GANSNER 1101 | 2424 | 39.9569 | -120.9553 | GANSNER 11012424 | 198 | 224 | 44390.1403 | 30415.1727 | 13974.9676 | 30151.5298 | 13788.4936 | 0.013217 | 0.0042995 | 1.3822 | 8.2429 | 2261 | 0.21656 | 1643 | 0 | 0 | 18.7353 | 1101 | 0
Sierra | 5208 | 1520 | 2121.4386 | 4865 | 3682.1162 | 544 | 0.00010097 | 9.6479 | 43.1985 | 745.3423 | 8830.938 | 891.6861 | 1.4602 | 43.4733 | 1.1651 | 0.00077179 | 0.0023448 | 0.31244 | 0.57615 | {23693049-039B-4514-94EB-4E3AE6138ACB} | 153082106 | PLACERVILLE 2106 | 11132 | 38.772 | -120.8138 | PLACERVILLE 210611132 | 564 | 480 | 105370.0715 | 69399.8401 | 35970.2313 | 69399.8401 | 35970.2313 | 1.2756 | 0.05493 | 1.3957 | 8.943 | 145 | 0.41986 | 1644 | 0 | 0 | 43.123 | 507 | 0
Central Coast | 3924 | 12 | 44.6556 | 39 | 60.1476 | 19 | 2.148e-05 | 33.7171 | 7.9508 | 192.3108 | 754.945 | 18.8208 | 4.7145 | 146.7555 | 1.2627 | 0.00077054 | 0.00011528 | 0.30769 | 0.74243 | {133D318F-822E-44D3-9638-08188E1B8D58} | 183101103 | CABRILLO 1103 | Y10 | 34.6655 | -120.4224 | CABRILLO 1103Y10 | 177 | 1081 | 76448.8655 | 24484.6302 | 51964.2353 | 7083.7808 | 5997.6344 | 0.0021904 | 0.00040813 | 3.7213 | 2.0526 | 1774 | 0.01464 | 1645 | 0 | 0 | 4.4017 | 309 | 0
Central Coast | 2032 | 2293 | 4569.9839 | 2859 | 4920.682 | 206 | 7.3759e-05 | 9.9931 | 3.994 | 126.4687 | 1583.8141 | 21.0894 | 0.21017 | 15.4152 | 1.0846 | 0.00076827 | 0.00017504 | 0.80203 | 0.92873 | {A725B58B-37EB-4147-83B3-63635BC09A1B} | 82841102 | BIG BASIN 1102 | 5066 | 37.1707 | -122.1655 | BIG BASIN 11025066 | 154 | 100 | 30993.8002 | 23248.0337 | 7745.7665 | 23248.0337 | 7745.7665 | 0.036057 | 0.015194 | 1.993 | 13.8786 | 1503 | 0.15826 | 1646 | 0 | 0 | 14.4457 | 1696 | 0
North Valley | 2405 | 23 | 37.3939 | 286 | 176.5666 | 62 | 6.6872e-06 | 143.2852 | 0.62819 | 126.2753 | 923.8286 | 3.352 | 2.0223 | 316.5517 | 1.292 | 0.00076233 | 5.0375e-06 | 0.08042 | 0.21178 | {F58DF78A-C4B0-4969-9413-98D7022EFF8F} | 103491101 | MC ARTHUR 1101 | 1546 | 41.0477 | -121.3122 | MC ARTHUR 11011546 | 134 | 169 | 40427.6671 | 37312.9087 | 3114.7583 | 20599.9851 | 2256.7904 | 0.00031232 | 0.00041461 | 1.6258 | 4.6129 | 2844 | 0.047265 | 1647 | 0 | 0 | 12.8002 | 773 | 0
Central Valley | 146 | 0 | 0 | 11 | 4.8947 | 6 | 7.9543e-05 | 7.9821 | 16.8549 | 626.9395 | 12505.924 | 643.6176 | 0.073451 | 1.0088 | 1.6685 | 0.0007611 | 0.001107 | 0 | 0 | {0ADE0ABE-2B1D-4CB6-BB2E-0E310321E755} | 162821702 | STANISLAUS 1702 | 6028 | 38.2369 | -120.3646 | STANISLAUS 17026028 | 174 | 349 | 21533.4054 | 8608.783 | 12924.6224 | 8608.783 | 12924.6224 | 0.0066422 | 0.00047726 |  | 1.8333 | 358 | 0.0045666 | 1648 | 0 | 0 | 5.3492 | 2221 | 0
Bay Area | 3152 | 1419 | 3854.8819 | 2255 | 4294.76 | 300 | 2.7185e-05 | 34.639 | 3.5462 | 248.8243 | 1118.5111 | 16.149 | 1.4635 | 118.2494 | 1.1215 | 0.00075835 | 4.7062e-05 | 0.62927 | 0.89758 | {F16AFC51-9F55-4551-9DB1-F4A71B7DE6A1} | 24101103 | HALF MOON BAY 1103 | H82 | 37.4176 | -122.4247 | HALF MOON BAY 1103H82 | 336 | 319 | 87378.844 | 58188.2631 | 29190.581 | 49003.1871 | 26288.8558 | 0.014119 | 0.0081555 | 2.7166 | 7.5167 | 2265 | 0.22751 | 1649 | 0 | 0 | 30.4492 | 2701 | 0
Sierra | 5046 | 1298 | 1736.551 | 2133 | 2109.7395 | 148 | 8.7279e-05 | 9.5502 | 15.8006 | 158.5296 | 2118.1415 | 320.1783 | 2.5124 | 22.38 | 1.1157 | 0.00075636 | 0.00078347 | 0.60853 | 0.82311 | {1F323A0D-3C08-4F07-A424-801F7C955EF5} | 152431102 | SHADY GLEN 1102 | 48894 | 39.119 | -120.9515 | SHADY GLEN 110248894 | 200 | 194 | 27301.1838 | 16046.7548 | 11254.429 | 13914.1946 | 10190.8589 | 0.11595 | 0.012917 | 1.3379 | 14.4122 | 508 | 0.11194 | 1650 | 0 | 0 | 8.6459 | 1561 | 0
Sierra | 317 | 915 | 1358.7209 | 2021 | 1820.0302 | 181 | 0.0001426 | 4.7942 | 8.1974 | 50.9675 | 459.2377 | 33.3078 | 0.66458 | 10.1223 | 1.0122 | 0.00075423 | 0.00049769 | 0.45275 | 0.74654 | {8F8EF18B-7E0A-4A9F-9597-8CCBE4E9FBDC} | 153081110 | PLACERVILLE 1110 | circuit_breaker | 38.731 | -120.7833 | PLACERVILLE 1110circuit_breaker | 354 | 882 | 55856.8276 | 20117.9419 | 35738.8857 | 18295.3344 | 31153.717 | 0.090082 | 0.02581 | 1.4849 | 11.1657 | 791 | 0.13652 | 1651 | 0 | 0 | 11.3682 | 755 | 0
Central Coast | 8441 | 335 | 580.8764 | 1246 | 1097.8784 | 95 | 5.8335e-05 | 18.0365 | 0.13758 | 30.3359 | 122.2413 | 0.027215 | 1.1405 | 57.7266 | 1.2181 | 0.00075205 | 3.4517e-05 | 0.26886 | 0.52909 | {6CBB7AC4-B511-49AC-B596-895EB516C2D9} | 182631104 | SAN LUIS OBISPO 1104 | 2293 | 35.192 | -120.4565 | SAN LUIS OBISPO 11042293 | 58 | 44 | 17418.3223 | 14494.4535 | 2923.8688 | 14494.4535 | 2923.8688 | 0.0032791 | 0.0055418 | 1.734 | 13.1158 | 2408 | 0.071445 | 1652 | 0 | 0 | 9.0064 | 2554 | 0
Sierra | 7746 | 142 | 217.9964 | 414 | 345.029 | 71 | 0.0001044 | 10.8177 | 32.0693 | 674.481 | 8105.2313 | 561.7293 | 3.6817 | 106.9083 | 1.202 | 0.00074984 | 0.0016342 | 0.343 | 0.63182 | {94D1A3AD-4895-43D5-80BA-F27D9B67BD20} | 153662102 | APPLE HILL 2102 | 89934 | 38.6493 | -120.6761 | APPLE HILL 210289934 | 95 | 82 | 14616.5765 | 9059.6456 | 5556.9309 | 9059.6456 | 5556.9309 | 0.11603 | 0.0074125 | 1.5352 | 5.831 | 221 | 0.053239 | 1653 | 0 | 0 | 5.6294 | 502 | 0
Bay Area | 4225 | 151 | 336.8431 | 323 | 441.0898 | 35 | 4.6882e-05 | 16.61 | 1.5541 | 23.6198 | 133.1459 | 0.16403 | 1.262 | 50.7506 | 1.0514 | 0.00074936 | 5.658e-05 | 0.46749 | 0.76366 | {6AEEBA49-CC4B-431B-92AA-34EB4CB9F64F} | 42261101 | BOLINAS 1101 | 1236 | 37.9316 | -122.6979 | BOLINAS 11011236 | 62 | 35 | 9204.0695 | 6557.8129 | 2646.2566 | 5655.0294 | 2321.1169 | 0.0019803 | 0.0016409 | 2.2307 | 9.2286 | 2177 | 0.026227 | 1654 | 0 | 0 | 3.5139 | 2739 | 0
North Coast | 5583 | 515 | 769.4459 | 1475 | 1331.1061 | 110 | 0.00011506 | 6.1574 | 12.6484 | 200.281 | 1753.7036 | 120.3283 | 1.5966 | 23.4674 | 1.0527 | 0.00074579 | 0.00076412 | 0.34915 | 0.57805 | {BEA97E4E-CFBB-4EAF-9EAB-B9D9096C26BD} | 43182103 | BELLEVUE 2103 | 646 | 38.3992 | -122.6217 | BELLEVUE 2103646 | 269 | 363 | 42939.7565 | 19879.4545 | 23060.302 | 12247.7458 | 13884.0043 | 0.084053 | 0.012656 | 1.4941 | 13.4091 | 525 | 0.082037 | 1655 | 0 | 0 | 7.6104 | 1357 | 0
Sierra | 6865 | 464 | 616.2235 | 1201 | 936.1708 | 93 | 0.00013003 | 4.9238 | 22.5794 | 219.422 | 2999.9612 | 287.3063 | 0.59187 | 10.6657 | 1.0108 | 0.00074533 | 0.0016337 | 0.38634 | 0.65824 | {C847E025-6E0A-40C2-B74F-54E4CBC5EB88} | 152481106 | BRUNSWICK 1106 | 63124 | 39.1984 | -121.0295 | BRUNSWICK 110663124 | 129 | 260 | 21201.9858 | 9428.9995 | 11772.9863 | 9428.9995 | 11772.9863 | 0.15193 | 0.012093 | 1.3281 | 12.914 | 222 | 0.069315 | 1656 | 0 | 0 | 5.8589 | 1460 | 0
Central Valley | 1713 | 769 | 1196.4054 | 6714 | 4223.8457 | 271 | 4.8423e-05 | 16.6522 | 88.4584 | 609.4464 | 12786.2006 | 3765.0133 | 0.77115 | 11.783 | 1.2346 | 0.00074288 | 0.0017059 | 0.11454 | 0.28325 | {E8F5F8AF-6EC9-4C69-835B-E53C764AC834} | 163661701 | MIWUK 1701 | circuit_breaker | 38.0528 | -120.2169 | MIWUK 1701circuit_breaker | 385 | 762 | 51076.8221 | 28710.6531 | 22366.169 | 28710.6531 | 22366.169 | 0.4623 | 0.013123 | 1.5558 | 24.7749 | 208 | 0.20132 | 1657 | 0 | 0 | 17.84 | 557 | 0
Central Valley | 2243 | 341 | 501.0243 | 1430 | 976.6099 | 249 | 2.6369e-05 | 27.8713 | 22.9354 | 893.2984 | 10197.5486 | 623.0746 | 1.9954 | 114.6649 | 1.2765 | 0.00073122 | 0.00030229 | 0.23846 | 0.51302 | {BAB6581B-1DEF-4E8B-AEF9-096FA24A0638} | 252192105 | BEAR VALLEY 2105 | 21160 | 37.7155 | -120.1934 | BEAR VALLEY 210521160 | 243 | 263 | 62081.3117 | 38250.3476 | 23830.9641 | 38250.3476 | 23830.9641 | 0.075271 | 0.0065658 | 1.4693 | 5.743 | 1117 | 0.18207 | 1658 | 0 | 0 | 23.7677 | 2530 | 0
Sierra | 108 | 967 | 1194.0524 | 4285 | 2560.9048 | 306 | 0.00011729 | 6.8274 | 26.3231 | 258.9372 | 5676.5893 | 2013.2251 | 0.34755 | 6.7705 | 1.0116 | 0.00073103 | 0.0014556 | 0.22567 | 0.46626 | {876266AC-37EA-414C-92FC-94A2ACD4EB2D} | 152762102 | EL DORADO PH 2102 | circuit_breaker | 38.7935 | -120.6191 | EL DORADO PH 2102circuit_breaker | 457 | 977 | 77480.6638 | 32849.8127 | 44630.851 | 32849.8127 | 44630.851 | 0.44541 | 0.035892 | 1.2348 | 14.0033 | 257 | 0.2237 | 1659 | 0 | 0 | 20.4119 | 1884 | 0
Central Coast | 1759 | 1483 | 3065.4607 | 1720 | 3192.9187 | 92 | 0.0002305 | 3.4267 | 7.7452 | 109.2514 | 981.7904 | 14.0965 | 0.34987 | 17.6121 | 1.0296 | 0.00072996 | 0.00098828 | 0.86221 | 0.96008 | {62DB6A1E-C643-412E-AD78-478695BE02E4} | 83622105 | CAMP EVERS 2105 | 10912 | 37.0913 | -122.096 | CAMP EVERS 210510912 | 91 | 75 | 13261.3053 | 8140.064 | 5121.2412 | 8140.064 | 5121.2412 | 0.090921 | 0.021206 | 2.0671 | 18.6957 | 415 | 0.067156 | 1660 | 0 | 0 | 5.058 | 2667 | 0
North Coast | 1184 | 367 | 486.6118 | 868 | 683.0299 | 140 | 4.6996e-05 | 18.7208 | 3.9197 | 1262.8391 | 22658.5233 | 189.0096 | 2.3679 | 120.066 | 1.2318 | 0.0007275 | 9.9854e-05 | 0.42281 | 0.71243 | {1163B195-EACD-43BD-86EC-77A4B82C1934} | 42251101 | HOPLAND 1101 | 960 | 38.973 | -123.0808 | HOPLAND 1101960 | 194 | 161 | 49052.8468 | 35106.288 | 13946.5588 | 23874.8083 | 12309.7229 | 0.013979 | 0.0065794 | 1.3259 | 6.2 | 1851 | 0.10185 | 1661 | 0 | 0 | 14.8351 | 2008 | 0
Central Coast | 7767 | 59 | 93.2696 | 128 | 128.8087 | 15 | 0.00018693 | 3.2371 | 10.7861 | 69.8419 | 302.5989 | 3.266 | 0.072566 | 9.3877 | 1.0024 | 0.00072555 | 0.00076187 | 0.46094 | 0.72409 | {8CE26437-AB3D-4CA1-B3DD-136FBC93120B} | 83040401 | BEN LOMOND 0401 | 5144 | 37.0912 | -122.0774 | BEN LOMOND 04015144 | 52 | 33 | 8936.2601 | 6409.4899 | 2526.7702 | 6409.4899 | 2526.7702 | 0.011428 | 0.0028039 | 1.5808 | 8.5333 | 527 | 0.010883 | 1662 | 0 | 0 | 3.9827 | 2246 | 0
Central Valley | 9599 | 36 | 46.8151 | 177 | 106.6508 | 37 | 5.7103e-07 | 1220.2855 | 0.15178 | 1484.0215 | 8215.245 | 2.3133 | 0.84519 | 1419.8683 | 1.8456 | 0.00072418 | 3.1386e-07 | 0.20339 | 0.43896 | {6C424A0E-18F6-4E95-BDD7-E63E2F8C4F83} | 252931102 | TEJON 1102 | 3760 | 34.846 | -118.8707 | TEJON 11023760 | 12 | 1 | 10658.214 | 10548.2717 | 109.9423 | 10548.2717 | 109.9423 | 1.1613e-05 | 2.1128e-05 | 1.3004 | 4.7838 | 2882 | 0.026795 | 1663 | 0 | 0 | 6.5544 | 2883 | 0
Central Coast | 9056 | 6 | 22.897 | 19 | 29.2696 | 6 | 1.2867e-05 | 73.5666 | 0.72828 | 23.6189 | 91.0756 | 0.21158 | 1.4163 | 216.4928 | 1.1051 | 0.00072162 | 1.3489e-05 | 0.31579 | 0.78228 | {A168C8D5-2E1D-4B22-A42C-F22CB609C9B9} | 83531108 | MC KEE 1108 | 70535 | 37.4 | -121.8463 | MC KEE 110870535 | 67 | 89 | 9976.8804 | 5288.7742 | 4688.1062 | 1019.3465 | 417.2131 | 8.0936e-05 | 7.7202e-05 | 3.8162 | 3.1667 | 2733 | 0.0043297 | 1664 | 0 | 0 | 0.63339 | 322 | 0
Bay Area | 5794 | 132 | 201.2826 | 961 | 710.4946 | 68 | 8.9726e-05 | 9.2395 | 0.6571 | 39.126 | 158.422 | 0.34693 | 1.026 | 33.5599 | 1.0382 | 0.00071494 | 7.6572e-05 | 0.13736 | 0.2833 | {3141710D-4E1F-480A-88B2-BC542204BF63} | 14161108 | ROSSMOOR 1108 | 37848 | 37.8464 | -122.1084 | ROSSMOOR 110837848 | 91 | 40 | 12736.3577 | 9580.5994 | 3155.7583 | 9580.5994 | 3155.7583 | 0.0052069 | 0.0061014 | 1.5249 | 14.1324 | 2005 | 0.048616 | 1665 | 0 | 0 | 5.9531 | 2130 | 0
Central Valley | 4028 | 37 | 50.7957 | 56 | 58.6278 | 8 | 9.3674e-05 | 20.8619 | 9.9897 | 29.7737 | 73.6854 | 1.1487 | 3.0619 | 26.2746 | 1.0918 | 0.00070606 | 0.00072212 | 0.66071 | 0.86641 | {2ED0FFD8-DF5F-45A0-8687-5F34F37A5A97} | 163351705 | CURTIS 1705 | 65908 | 37.9575 | -120.3133 | CURTIS 170565908 | 355 | 339 | 48772.1113 | 26938.5587 | 21833.5526 | 21139.8755 | 18447.0315 | 0.0057769 | 0.00074939 | 1.3729 | 7 | 555 | 0.0056485 | 1666 | 0 | 0 | 13.1357 | 660 | 0
Central Valley | 1143 | 837 | 1148.2139 | 3499 | 2570.212 | 417 | 4.2764e-05 | 21.3362 | 15.9469 | 495.7799 | 6464.7358 | 448.8678 | 1.6545 | 61.5633 | 1.2179 | 0.00070604 | 0.00030662 | 0.23921 | 0.44674 | {F0D5CE6E-E57F-49E9-90E4-51B561A47925} | 252192105 | BEAR VALLEY 2105 | 9560 | 37.6978 | -120.1162 | BEAR VALLEY 21059560 | 491 | 450 | 96474.2811 | 58396.3744 | 38077.9068 | 58396.3744 | 38077.9068 | 0.12786 | 0.017832 | 1.3718 | 8.3909 | 1107 | 0.29442 | 1667 | 0 | 0 | 36.2858 | 1339 | 0
Bay Area | 8952 | 0 | 0 | 6 | 3.1602 | 3 | 7.4275e-05 | 8.2524 | 13.2646 | 397.8617 | 1573.0303 | 23.4905 | 1.6055 | 79.4083 | 1.0273 | 0.00070597 | 0.00042587 | 0 | 0 | {17DE99B2-61AF-4462-979F-1C1B612D667F} | 42042101 |  | circuit_breaker | 38.0676 | -122.1957 | circuit_breaker | 52 | 2 | 7237.8234 | 7084.2306 | 153.5927 | 305.1807 | 153.5927 | 0.0012776 | 0.00022282 |  | 2 | 903 | 0.0021179 | 1668 | 0 | 0 | 0.18963 | 835 | 0
Bay Area | 2083 | 107 | 249.3875 | 250 | 328.0946 | 43 | 6.0179e-05 | 7.8072 | 1.1667 | 2.6409 | 9.8891 | 0.16165 | 0.47113 | 3.8521 | 1.1149 | 0.00070297 | 7.62e-05 | 0.428 | 0.76011 | {64639A8A-2672-4BE4-8EBB-2985CB356A36} | 42481101 | IGNACIO 1101 | 1300 | 38.0662 | -122.5482 | IGNACIO 11011300 | 121 | 708 | 51963.5339 | 9813.462 | 42150.0719 | 4134.7438 | 18449.3358 | 0.0032766 | 0.0025877 | 2.3307 | 5.814 | 2009 | 0.030228 | 1669 | 0 | 0 | 2.5692 | 2071 | 0
Central Valley | 4021 | 79 | 125.8724 | 191 | 179.3633 | 45 | 4.1273e-05 | 19.2804 | 4.1561 | 139.532 | 1093.8571 | 8.3851 | 3.2108 | 70.9549 | 1.3456 | 0.00070211 | 0.00012913 | 0.41361 | 0.70177 | {6FC28AC3-D7E2-4D2C-9C34-2FD4A55CB839} | 254452101 | MARIPOSA 2101 | 4410 | 37.5011 | -119.809 | MARIPOSA 21014410 | 316 | 285 | 64876.2008 | 36631.6496 | 28244.5512 | 36631.6496 | 28244.5512 | 0.0058109 | 0.0018573 | 1.5933 | 4.2444 | 1704 | 0.031595 | 1670 | 0 | 0 | 22.7618 | 901 | 0
North Coast | 8971 | 72 | 116.6724 | 106 | 132.363 | 19 | 5.6969e-05 | 11.3557 | 1.4452 | 186.7144 | 993.865 | 1.5804 | 0.89043 | 37.257 | 1.0555 | 0.00069997 | 6.5997e-05 | 0.67925 | 0.88146 | {827A54D0-0188-46E1-B6F0-E7D696DF4D89} | 43381101 | POINT ARENA 1101 | 1296 | 38.9513 | -123.6846 | POINT ARENA 11011296 | 43 | 48 | 11330.5583 | 8913.723 | 2416.8353 | 4384.7382 | 1394.1682 | 0.001254 | 0.0010824 | 1.6204 | 5.5789 | 2082 | 0.013299 | 1671 | 0 | 0 | 2.7245 | 930 | 0
Central Valley | 1459 | 992 | 1488.4632 | 2991 | 2255.7192 | 310 | 6.5999e-05 | 10.8823 | 17.0402 | 92.9041 | 636.569 | 45.278 | 6.2722 | 35.956 | 1.129 | 0.00069965 | 0.00050578 | 0.33166 | 0.65986 | {7226EEDE-AAEC-45AB-A41D-23DA3572485A} | 163351702 | CURTIS 1702 | circuit_breaker | 37.9745 | -120.32 | CURTIS 1702circuit_breaker | 524 | 742 | 79338.0532 | 36730.9251 | 42607.1281 | 35160.9523 | 40104.3156 | 0.15679 | 0.02046 | 1.5005 | 9.6484 | 783 | 0.21689 | 1672 | 0 | 0 | 21.848 | 2442 | 0
Sierra | 593 | 4 | 4.9109 | 23 | 12.5836 | 3 | 7.2492e-05 | 8.0547 | 14.8339 | 68.2967 | 199.5332 | 2.9584 | 6.2109 | 25.6715 | 1.0066 | 0.00069322 | 0.00067758 | 0.17391 | 0.39026 | {377FA4E5-D94D-4CB5-9E3D-4B59D89DE43B} | 152701110 | BELL 1110 | 56214 | 38.9329 | -121.0923 | BELL 111056214 | 176 | 225 | 20935.461 | 10701.9064 | 10233.5547 | 144.7507 | 409.3643 | 0.0020327 | 0.00021748 | 1.2277 | 7.6667 | 589 | 0.0020797 | 1673 | 0 | 0 | 0.089944 | 206 | 0
Central Coast | 8101 | 82 | 166.9661 | 702 | 517.9773 | 62 | 3.6884e-05 | 18.9216 | 0.8542 | 37.2064 | 426.4165 | 4.0879 | 2.8959 | 47.8641 | 1.2954 | 0.00069313 | 2.6104e-05 | 0.11681 | 0.32234 | {80D44D26-A5B1-4132-A46C-9B3A91131779} | 83481110 | STELLING 1110 | 9265 | 37.2937 | -122.1021 | STELLING 11109265 | 58 | 42 | 13575.0432 | 9183.0563 | 4391.9869 | 9183.0563 | 4391.9869 | 0.0016184 | 0.0022868 | 2.0362 | 11.3226 | 2514 | 0.042974 | 1674 | 0 | 0 | 5.7061 | 1827 | 0
Bay Area | 6123 | 527 | 937.9695 | 1190 | 1305.6212 | 61 | 0.0001001 | 7.8691 | 4.3348 | 191.685 | 3564.6186 | 23.7246 | 0.43983 | 14.1598 | 1.0367 | 0.00069166 | 0.00026238 | 0.44286 | 0.71841 | {6D66BCD7-D73E-47DE-AD9E-4F226AFB1323} | 43021101 | WOODACRE 1101 | 1238 | 38.0111 | -122.7023 | WOODACRE 11011238 | 60 | 126 | 11912.9226 | 5891.9294 | 6020.9932 | 5891.9294 | 6020.9932 | 0.016005 | 0.0061061 | 1.7798 | 19.5082 | 1219 | 0.042192 | 1675 | 0 | 0 | 3.6611 | 1537 | 0
North Valley | 7724 | 281 | 354.9966 | 618 | 509.9739 | 84 | 0.00010664 | 7.3305 | 12.0293 | 2179.2986 | 44029.0092 | 800.8716 | 1.9506 | 101.373 | 1.1274 | 0.00068742 | 0.00069418 | 0.45469 | 0.69611 | {5AC50D45-C367-48C6-98B5-2430D82E7CB7} | 101321101 | PIT NO 5 1101 | 1606 | 41.0191 | -121.9095 | PIT NO 5 11011606 | 69 | 73 | 10909.3305 | 8892.9459 | 2016.3847 | 8892.9459 | 2016.3847 | 0.058311 | 0.0089579 | 1.2633 | 7.3571 | 572 | 0.057743 | 1676 | 0 | 0 | 5.5258 | 2463 | 0
Bay Area | 8544 | 1 | 3.0796 | 19 | 13.1061 | 5 | 3.9609e-05 | 14.3327 | 0.066975 | 0.069399 | 0.00083214 | 1.786e-07 | 3.4602 | 8.2979 | 1.0265 | 0.00067396 | 1.9258e-05 | 0.052632 | 0.23498 | {90D8A356-6EF7-43D5-832C-D86D9C80D726} | 42991105 | LAS GALLINAS A 1105 | circuit_breaker | 38.0222 | -122.5381 | LAS GALLINAS A 1105circuit_breaker | 58 | 148 | 10244.7008 | 3345.6946 | 6899.0062 | 658.6815 | 697.0062 | 9.6289e-05 | 0.00019805 | 3.0796 | 3.8 | 2628 | 0.0033698 | 1677 | 0 | 0 | 0.40929 | 2227 | 0
Central Coast | 5030 | 3896 | 6759.7987 | 6179 | 8061.4795 | 240 | 0.00011928 | 5.7142 | 5.9704 | 31.3335 | 151.7479 | 1.7468 | 0.81736 | 10.5373 | 1.0321 | 0.00067305 | 0.00040324 | 0.63052 | 0.83853 | {012CDBC3-48FF-4297-A5D2-4E50EE81B775} | 83622106 | CAMP EVERS 2106 | 5020 | 37.1025 | -121.9847 | CAMP EVERS 21065020 | 321 | 336 | 42076.3788 | 24453.2376 | 17623.1412 | 24453.2376 | 17623.1412 | 0.096778 | 0.028627 | 1.7351 | 25.7458 | 941 | 0.16153 | 1678 | 0 | 0 | 15.1945 | 1677 | 0
Central Valley | 3487 | 180 | 249.3732 | 724 | 546.126 | 54 | 7.5065e-05 | 7.1097 | 2.8731 | 6.5274 | 45.7007 | 0.47033 | 1.0985 | 8.9062 | 1.03 | 0.00067269 | 0.00013809 | 0.24862 | 0.45662 | {B3D10DC1-455E-4DDF-8795-B604423C3B61} | 254421103 | OAKHURST 1103 | 77384 | 37.3389 | -119.5843 | OAKHURST 110377384 | 159 | 554 | 26182.3972 | 7607.5657 | 18574.8315 | 7607.5657 | 18574.8315 | 0.0074569 | 0.0040535 | 1.3854 | 13.4074 | 1643 | 0.036325 | 1679 | 0 | 0 | 4.7271 | 1778 | 0
Bay Area | 2705 | 385 | 1206.5066 | 851 | 1411.0491 | 122 | 2.0219e-05 | 40.0037 | 2.1449 | 159.6907 | 844.9487 | 3.858 | 2.4093 | 99.2696 | 1.1613 | 0.00067236 | 3.2779e-05 | 0.45241 | 0.85504 | {2DDD3645-3AB5-4B35-8936-1A369FDDE7B2} | 24101103 | HALF MOON BAY 1103 | 6018 | 37.3265 | -122.3875 | HALF MOON BAY 11036018 | 230 | 321 | 51975.904 | 30588.369 | 21387.535 | 24500.2785 | 11457.7686 | 0.0039991 | 0.0024668 | 3.1338 | 6.9754 | 2428 | 0.082028 | 1680 | 0 | 0 | 15.2238 | 2187 | 0
North Valley | 976 | 1019 | 1692.6205 | 2944 | 2468.0342 | 334 | 0.00010089 | 9.1741 | 19.6062 | 499.78 | 3002.7133 | 98.5551 | 3.8624 | 117.1386 | 1.1331 | 0.00067074 | 0.0010486 | 0.34613 | 0.68582 | {444ADEBA-E6AE-44E6-8A3E-6A09732B697D} | 103081105 | BUTTE 1105 | 134600 | 39.7117 | -121.7735 | BUTTE 1105134600 | 438 | 409 | 81744.7469 | 49696.2582 | 32048.4887 | 44940.5828 | 30261.6058 | 0.35023 | 0.033697 | 1.6611 | 8.8144 | 386 | 0.22403 | 1681 | 0 | 0 | 27.9248 | 2893 | 0
Central Coast | 7181 | 3 | 6.3702 | 127 | 74.2231 | 22 | 2.0263e-05 | 39.7006 | 0.67749 | 477.9771 | 1911.4052 | 2.2231 | 2.8819 | 132.0064 | 1.1632 | 0.00066452 | 1.5248e-05 | 0.023622 | 0.085825 | {02264660-E3C6-4806-AC6E-28401EBDA58A} | 183101103 | CABRILLO 1103 | Y46 | 34.6448 | -120.429 | CABRILLO 1103Y46 | 330 | 257 | 111317.7012 | 76540.2703 | 34777.4309 | 37171.7089 | 16350.3342 | 0.00033546 | 0.00044578 | 2.1234 | 5.7727 | 2700 | 0.014619 | 1682 | 0 | 0 | 23.0974 | 1463 | 0
North Valley | 9158 | 44 | 46.4809 | 253 | 138.2254 | 39 | 4.2608e-05 | 16.5225 | 9.4284 | 510.0789 | 7194.2416 | 117.4064 | 0.1838 | 17.86 | 1.0287 | 0.00066238 | 0.00018939 | 0.17391 | 0.33627 | {6FF82506-9D44-457C-9D08-D3108198D9B3} | 102541102 | VOLTA 1102 | 93418 | 40.5138 | -121.7868 | VOLTA 110293418 | 36 | 13 | 4703.696 | 4264.808 | 438.888 | 4264.808 | 438.888 | 0.0073862 | 0.0016617 | 1.0564 | 6.4872 | 1452 | 0.025833 | 1683 | 0 | 0 | 2.65 | 2050 | 0
Central Valley | 6725 | 53 | 75.181 | 858 | 432.5183 | 80 | 4.0041e-05 | 16.1181 | 2.6393 | 18.3312 | 116.8249 | 0.59573 | 0.63233 | 7.9586 | 1.0072 | 0.00065967 | 6.9824e-05 | 0.061772 | 0.17382 | {77733CA8-C469-4656-B2CC-06892BE8F14F} | 163692102 | SALT SPRINGS 2102 | 97924 | 38.3232 | -120.2538 | SALT SPRINGS 210297924 | 101 | 186 | 14585.0896 | 8204.8506 | 6380.2391 | 8204.8506 | 6380.2391 | 0.0055859 | 0.0032033 | 1.4185 | 10.725 | 2059 | 0.052773 | 1684 | 0 | 0 | 5.0983 | 1420 | 0
Central Coast | 1114 | 1623 | 2473.7884 | 3614 | 3583.4158 | 287 | 6.6102e-05 | 10.0126 | 6.637 | 78.6038 | 750.7686 | 10.2967 | 1.8467 | 21.7537 | 1.0683 | 0.00065898 | 0.00024056 | 0.44909 | 0.69034 | {5D70BF4D-C1AE-452C-84AB-8E4767458B84} | 82021106 | LOS GATOS 1106 | LB44 | 37.1938 | -121.9959 | LOS GATOS 1106LB44 | 337 | 351 | 57668.6855 | 30802.2438 | 26866.4417 | 30802.2438 | 26866.4417 | 0.069039 | 0.018971 | 1.5242 | 12.5923 | 1276 | 0.18913 | 1685 | 0 | 0 | 19.1396 | 2248 | 0
Central Valley | 3772 | 83 | 107.1104 | 366 | 225.9947 | 22 | 0.00016863 | 5.4736 | 5.4047 | 6.6734 | 17.0722 | 0.12364 | 0.20525 | 1.8503 | 1.0015 | 0.00065886 | 0.00059432 | 0.22678 | 0.47395 | {7B183002-426A-4DA8-873E-9A518FB69116} | 163751102 | PINE GROVE 1102 | 1765 | 38.4433 | -120.5355 | PINE GROVE 11021765 | 40 | 100 | 6075.3039 | 2330.5339 | 3744.77 | 2330.5339 | 3744.77 | 0.013075 | 0.0037098 | 1.2905 | 16.6364 | 675 | 0.014495 | 1686 | 0 | 0 | 1.4481 | 1680 | 0
Central Valley | 7719 | 177 | 250.0282 | 873 | 626.0533 | 40 | 6.4053e-05 | 10.173 | 32.3786 | 433.0577 | 6450.7886 | 1112.553 | 1.0544 | 9.6019 | 1.0038 | 0.00065815 | 0.0010842 | 0.20275 | 0.39937 | {231BEE73-587D-46B7-AD5A-EAD10C3B8AAD} | 163661702 | MIWUK 1702 | S1547 | 38.0579 | -120.2706 | MIWUK 1702S1547 | 71 | 139 | 11213.5358 | 4436.0854 | 6777.4504 | 4436.0854 | 6777.4504 | 0.04337 | 0.0025621 | 1.4126 | 21.825 | 369 | 0.026326 | 1687 | 0 | 0 | 2.7565 | 117 | 0
Central Valley | 5933 | 205 | 316.4649 | 1060 | 678.4898 | 78 | 4.6653e-05 | 12.8602 | 40.0274 | 357.0365 | 3237.7823 | 308.9956 | 2.7844 | 28.854 | 1.3674 | 0.00065633 | 0.00087788 | 0.1934 | 0.46643 | {1AB89EBD-4C74-4F17-AC51-C67FA279FE6D} | 163351702 | CURTIS 1702 | 9111 | 38.0127 | -120.3073 | CURTIS 17029111 | 130 | 268 | 21198.7616 | 9135.0634 | 12063.6983 | 9135.0634 | 12063.6983 | 0.068475 | 0.003639 | 1.5437 | 13.5897 | 459 | 0.051194 | 1688 | 0 | 0 | 5.6763 | 1508 | 0
Central Valley | 6161 | 192 | 292.1486 | 427 | 414.7148 | 66 | 1.8427e-05 | 38.275 | 9.9832 | 202.8477 | 1879.0628 | 67.9236 | 3.9723 | 169.67 | 1.3425 | 0.00065544 | 7.8161e-05 | 0.44965 | 0.70446 | {A6D1F5C5-C503-4CFC-844D-2877BC97AA39} | 254061102 | DUNLAP 1102 | circuit_breaker | 36.7096 | -119.0299 | DUNLAP 1102circuit_breaker | 128 | 153 | 18350.5771 | 10788.4174 | 7562.1596 | 10788.4174 | 7562.1596 | 0.0051586 | 0.0012162 | 1.5216 | 6.4697 | 1998 | 0.043259 | 1689 | 0 | 0 | 6.7036 | 526 | 0
Bay Area | 3589 | 170 | 257.4593 | 732 | 605.3576 | 91 | 3.8358e-05 | 31.1679 | 3.9322 | 61.8474 | 203.211 | 2.0954 | 3.3336 | 84.9149 | 1.0833 | 0.00065008 | 8.9986e-05 | 0.23224 | 0.4253 | {144B98B4-D8D8-4444-BA16-D1CC613F7105} | 14241101 | SUNOL 1101 | MR297 | 37.5946 | -121.8882 | SUNOL 1101MR297 | 99 | 140 | 17541.7543 | 9725.4912 | 7816.2631 | 9415.923 | 6966.5106 | 0.0081887 | 0.0034906 | 1.5145 | 8.044 | 1909 | 0.059157 | 1690 | 0 | 0 | 5.8508 | 1320 | 0
Central Valley | 4356 | 516 | 699.2871 | 1952 | 1434.2065 | 89 | 6.5274e-05 | 9.4099 | 34.9092 | 94.5152 | 862.603 | 78.2737 | 0.36365 | 4.1094 | 1.4976 | 0.00064859 | 0.00090312 | 0.26434 | 0.48758 | {ED3657AD-4222-47A8-B914-D4A507DC3692} | 163661702 | MIWUK 1702 | 38218 | 38.0486 | -120.2438 | MIWUK 170238218 | 264 | 503 | 42025.0145 | 17457.0622 | 24567.9522 | 17457.0622 | 24567.9522 | 0.080377 | 0.0058094 | 1.3552 | 21.9326 | 441 | 0.057725 | 1691 | 0 | 0 | 10.8473 | 1208 | 0
Central Valley | 6273 | 97 | 124.53 | 1423 | 763.0851 | 133 | 0.00013911 | 4.7127 | 43.7527 | 801.7083 | 15823.029 | 3501.9592 | 0.86171 | 11.8575 | 1.136 | 0.00064645 | 0.0030623 | 0.068166 | 0.16319 | {1F21142A-72EE-4D4A-A8F0-E9702D60226C} | 163201101 | WEST POINT 1101 | 13444 | 38.487 | -120.5231 | WEST POINT 110113444 | 327 | 413 | 49975.2895 | 26771.8299 | 23203.4596 | 26771.8299 | 23203.4596 | 0.40728 | 0.018502 | 1.2838 | 10.6992 | 104 | 0.085978 | 1692 | 0 | 0 | 16.6352 | 1504 | 0
Bay Area | 8207 | 703 | 2067.4921 | 1778 | 2629.3855 | 128 | 4.6841e-05 | 12.7216 | 9.7362 | 1725.0027 | 17556.1858 | 334.3533 | 0.39823 | 18.7007 | 1.0133 | 0.00064352 | 0.00020434 | 0.39539 | 0.7863 | {B7FC1F3D-8C95-48C1-8180-E56EBBA37A96} | 42291101 | OLEMA 1101 | 602 | 38.1094 | -122.8698 | OLEMA 1101602 | 137 | 109 | 49843.8167 | 39506.2468 | 10337.5699 | 25492.7395 | 3010.2029 | 0.026156 | 0.0059957 | 2.941 | 13.8906 | 1399 | 0.082371 | 1693 | 0 | 0 | 15.8404 | 2557 | 0
Central Coast | 8087 | 78 | 161.4295 | 199 | 228.7067 | 31 | 3.7376e-05 | 13.8756 | 3.1777 | 515.6306 | 9273.9023 | 53.1971 | 2.0759 | 40.0879 | 1.1487 | 0.00064242 | 6.074e-05 | 0.39196 | 0.70584 | {2F7A50CF-9F3D-4DF2-877E-9D53DE1B982A} | 82021107 | LOS GATOS 1107 | 60024 | 37.1696 | -121.939 | LOS GATOS 110760024 | 34 | 27 | 8703.6188 | 6397.1295 | 2306.4893 | 6397.1295 | 2306.4893 | 0.0018829 | 0.0011587 | 2.0696 | 6.4194 | 2131 | 0.019915 | 1694 | 0 | 0 | 3.975 | 1969 | 0
Central Coast | 8278 | 656 | 1098.0036 | 1118 | 1379.2181 | 39 | 0.00017394 | 3.7249 | 12.8163 | 26.0472 | 92.8941 | 2.3296 | 1.4801 | 7.2781 | 1.0068 | 0.00063781 | 0.0010172 | 0.58676 | 0.79611 | {7CFF45FB-01BE-445B-B5D9-024236B07470} | 83622105 | CAMP EVERS 2105 | 33542 | 37.0905 | -122.0456 | CAMP EVERS 210533542 | 73 | 112 | 9737.8527 | 3984.6462 | 5753.2065 | 3984.6462 | 5753.2065 | 0.039669 | 0.0067837 | 1.6738 | 28.6667 | 404 | 0.024875 | 1695 | 0 | 0 | 2.4759 | 1878 | 0
Central Valley | 1363 | 199 | 277.9325 | 1406 | 824.4602 | 65 | 8.2627e-05 | 7.7466 | 7.8391 | 49.7712 | 968.7275 | 30.6067 | 0.26036 | 2.4903 | 1.1718 | 0.00063702 | 0.00040446 | 0.14154 | 0.33711 | {0E73709C-125E-45DC-B07D-3894E7D59501} | 162821701 | STANISLAUS 1701 | 1331 | 38.2329 | -120.3655 | STANISLAUS 17011331 | 117 | 296 | 18663.8274 | 7071.5091 | 11592.3184 | 7071.5091 | 11592.3184 | 0.02629 | 0.0053708 | 1.3966 | 21.6308 | 936 | 0.041407 | 1696 | 0 | 0 | 4.394 | 76 | 0
Central Coast | 1390 | 2 | 4.2117 | 98 | 81.5171 | 3 | 9.001e-05 | 23.8327 | 16.2147 | 189.6149 | 2496.5033 | 141.5003 | 0.95206 | 16.225 | 1.0088 | 0.0024739 | 0.0011008 | 0.020408 | 0.051667 | {44BC81C9-8540-477A-9326-99FB3CD481E2} | 163351704 | CURTIS 1704 | 8140 | 38.0068 | -120.3479 | CURTIS 17048140 | 394 | 469 | 70369.299 | 42473.8563 | 27895.4428 | 42473.8563 | 27895.4428 | 0.0033025 | 0.00027003 | 2.1059 | 32.6667 | 362 | 0.0074216 | 1697 | 0 | 0 | 26.392 | 2716 | 0
Central Valley | 1390 | 1515 | 2114.6621 | 5711 | 4181.2607 | 347 | 9.4886e-05 | 9.2982 | 18.8636 | 281.4754 | 3543.6665 | 211.7924 | 1.4958 | 31.7587 | 1.0752 | 0.00061488 | 0.00094736 | 0.26528 | 0.50575 | {44BC81C9-8540-477A-9326-99FB3CD481E2} | 163351704 | CURTIS 1704 | 8140 | 38.0068 | -120.3479 | CURTIS 17048140 | 394 | 469 | 70369.299 | 42473.8563 | 27895.4428 | 42473.8563 | 27895.4428 | 0.32874 | 0.032925 | 1.3958 | 16.4582 | 435 | 0.21336 | 1697 | 0 | 0 | 26.392 | 30 | 0
Central Coast | 5506 | 649 | 1237.499 | 856 | 1350.578 | 60 | 0.00016404 | 4.8225 | 7.0804 | 86.1927 | 1588.9216 | 20.8658 | 0.31689 | 5.9716 | 1.0177 | 0.00063079 | 0.00057075 | 0.75818 | 0.91627 | {BEA4FE88-D817-444C-8617-83661CE5A408} | 82841102 | BIG BASIN 1102 | 12758 | 37.1485 | -122.1748 | BIG BASIN 110212758 | 146 | 393 | 27849.9662 | 9878.3441 | 17971.6221 | 9878.3441 | 17971.6221 | 0.034245 | 0.0098426 | 1.9068 | 14.2667 | 710 | 0.037848 | 1698 | 0 | 0 | 6.1381 | 2556 | 0
Bay Area | 3752 | 1428 | 3683.8613 | 4509 | 5378.757 | 221 | 5.6614e-05 | 10.4977 | 8.3865 | 552.9355 | 10032.6723 | 226.9188 | 0.54872 | 4.498 | 1.1267 | 0.00062993 | 0.00025655 | 0.3167 | 0.68489 | {F7C05161-6A07-4797-A2B5-C7A055E43654} | 42291101 | OLEMA 1101 | 50396 | 38.0771 | -122.8316 | OLEMA 110150396 | 269 | 438 | 47079.2396 | 21037.3757 | 26041.8638 | 20493.6346 | 26023.5433 | 0.056698 | 0.012512 | 2.5797 | 20.4027 | 1235 | 0.13922 | 1699 | 0 | 0 | 12.7342 | 2563 | 0
North Coast | 7298 | 524 | 911.5069 | 566 | 930.6458 | 54 | 7.5252e-05 | 9.3095 | 0.36022 | 35.9358 | 241.0227 | 0.090436 | 0.13164 | 10.7723 | 0.96169 | 0.00062929 | 5.2312e-05 | 0.9258 | 0.97943 | {9A2A59D4-79DC-47CE-A757-850979A9B368} | 43381101 | POINT ARENA 1101 | 2637 | 38.9563 | -123.6415 | POINT ARENA 11012637 | 34 | 29 | 12746.0537 | 6500.6025 | 6245.4512 | 6500.6025 | 6245.4512 | 0.0028249 | 0.0040636 | 1.7395 | 10.4815 | 2218 | 0.033982 | 1700 | 0 | 0 | 4.0393 | 929 | 0
Bay Area | 1696 | 87 | 176.7694 | 692 | 456.3494 | 26 | 6.5377e-05 | 9.2112 | 0.13347 | 8.4616 | 57.647 | 0.067526 | 0.86487 | 17.9652 | 1.0194 | 0.00062895 | 5.2654e-05 | 0.12572 | 0.38736 | {86BA3963-96A5-4181-83CD-FA7B5EC47222} | 42261101 | BOLINAS 1101 | circuit_breaker | 37.9408 | -122.7068 | BOLINAS 1101circuit_breaker | 51 | 13 | 4103.0472 | 3500.023 | 603.0242 | 3408.2951 | 565.7352 | 0.001369 | 0.0016998 | 2.0318 | 26.6154 | 2215 | 0.016353 | 1701 | 0 | 0 | 2.1178 | 1562 | 0
Central Coast | 4481 | 1067 | 2021.5817 | 2521 | 2808.4453 | 167 | 6.7703e-05 | 9.8991 | 3.7992 | 187.3704 | 2655.0669 | 33.4115 | 1.3266 | 38.0536 | 1.2304 | 0.0006255 | 0.00016463 | 0.42324 | 0.71982 | {717BE6DE-1A86-4939-B958-630A186C1AF4} | 83371107 | SARATOGA 1107 | 413816 | 37.2524 | -122.0611 | SARATOGA 1107413816 | 168 | 100 | 26276.6617 | 17947.1279 | 8329.5338 | 17947.1279 | 8329.5338 | 0.027493 | 0.011306 | 1.8946 | 15.0958 | 1534 | 0.10446 | 1702 | 0 | 0 | 11.1518 | 1711 | 0
Bay Area | 1200 | 44 | 76.81 | 229 | 178.5917 | 44 | 4.8711e-05 | 15.5098 | 0.79464 | 17.5258 | 39.8412 | 0.1311 | 1.9995 | 61.1764 | 1.0864 | 0.00062518 | 4.2046e-05 | 0.19214 | 0.43009 | {90446565-9C4E-4EC0-BE56-9B48C2C5DA8B} | 14241101 | SUNOL 1101 | MR298 | 37.5944 | -121.8891 | SUNOL 1101MR298 | 60 | 75 | 13185.4608 | 8594.3194 | 4591.1414 | 8010.2959 | 4106.9876 | 0.00185 | 0.0021433 | 1.7457 | 5.2045 | 2308 | 0.027508 | 1703 | 0 | 0 | 4.9774 | 2077 | 0
Bay Area | 1966 | 306 | 466.2396 | 975 | 832.0104 | 51 | 0.0001255 | 4.2494 | 0.26002 | 0.32929 | 0.59723 | 0.0013016 | 0.1366 | 1.8101 | 1.6485 | 0.00062056 | 8.9908e-05 | 0.31385 | 0.56038 | {332AA22A-A859-478E-AF82-419A23B67FF8} | 42011108 | SAN RAFAEL 1108 | 39156 | 37.9669 | -122.5589 | SAN RAFAEL 110839156 | 176 | 486 | 29509.8554 | 7673.7546 | 21836.1008 | 5556.6949 | 18202.6999 | 0.0045853 | 0.0064003 | 1.5237 | 19.1176 | 1910 | 0.031649 | 1704 | 0 | 0 | 3.4528 | 1575 | 0
Sierra | 2503 | 5462 | 7185.7682 | 11698 | 10145.485 | 947 | 8.7061e-05 | 6.871 | 85.6668 | 780.1213 | 12594.3588 | 4690.2448 | 1.7259 | 25.6299 | 1.0663 | 0.00061759 | 0.0036449 | 0.46692 | 0.70827 | {20D517CB-EFEF-4E5D-A065-4994CEAE6929} | 152481106 | BRUNSWICK 1106 | 51486 | 39.1909 | -120.9967 | BRUNSWICK 110651486 | 1025 | 1033 | 163128.0367 | 91172.3296 | 71955.7071 | 91172.3296 | 71955.7071 | 3.4518 | 0.082447 | 1.3156 | 12.3527 | 71 | 0.58486 | 1705 | 0 | 0 | 56.6518 | 1379 | 0
North Coast | 2536 | 253 | 511.5036 | 497 | 624.9314 | 41 | 0.00011167 | 5.8618 | 7.3595 | 125.1183 | 1369.9533 | 36.7745 | 0.63883 | 5.6652 | 1.1051 | 0.00061574 | 0.00048506 | 0.50905 | 0.8185 | {2D8E8FC7-3A5C-40AE-8F67-02A91CEAEC16} | 43081101 | BIG RIVER 1101 | 55402 | 39.3394 | -123.8093 | BIG RIVER 110155402 | 181 | 223 | 27214.707 | 14975.0535 | 12239.6535 | 3203.2885 | 2341.2323 | 0.019887 | 0.0045784 | 2.0218 | 12.122 | 803 | 0.025245 | 1706 | 0 | 0 | 1.9904 | 1959 | 0
Sierra | 3288 | 31 | 46.3519 | 82 | 71.8837 | 9 | 0.0001037 | 5.351 | 3.1932 | 20.9234 | 249.7244 | 17.1505 | 1.2203 | 15.0657 | 0.80851 | 0.00061547 | 0.0001858 | 0.37805 | 0.64482 | {B0F41A34-F762-41B4-ACDB-9C11F27E225A} | 152031101 | GRASS VALLEY 1101 | circuit_breaker | 39.2089 | -121.0612 | GRASS VALLEY 1101circuit_breaker | 133 | 147 | 9203.4325 | 4306.6032 | 4896.8293 | 1152.0117 | 1749.5501 | 0.0016722 | 0.00093329 | 1.4952 | 9.1111 | 1462 | 0.0055392 | 1707 | 0 | 0 | 0.71583 | 546 | 0
Sierra | 7978 | 13 | 22.0571 | 18 | 24.2497 | 2 | 2.5741e-05 | 23.8389 |  |  |  |  | 15.6283 | 30.4055 | 1.0044 | 0.00061364 | 2.5741e-05 | 0.72222 | 0.90958 | {3A0CCFE3-C12C-4384-B593-6A5D6B4AD5AF} | 63601111 | VACAVILLE 1111 | 12342 | 38.3689 | -121.9938 | VACAVILLE 111112342 | 26 | 20 | 4202.5385 | 1698.7343 | 2503.8042 | 237.1733 | 0 | 5.1482e-05 | 5.1482e-05 | 1.6967 | 9 | 2520 | 0.0012273 | 1708 | 0 | 0 | 0.14737 | 2497 | 0
Central Coast | 5592 | 38 | 66.7378 | 57 | 76.0689 | 6 | 0.00017561 | 4.0298 | 3.3296 | 11.9052 | 54.8513 | 0.23856 | 0.34255 | 7.2058 | 1.0015 | 0.00061154 | 0.00026051 | 0.66667 | 0.87733 | {93B6E3D2-A180-4B48-A34A-CC6FAF84E787} | 83040401 | BEN LOMOND 0401 | 5206 | 37.0955 | -122.0857 | BEN LOMOND 04015206 | 129 | 144 | 20497.1751 | 11401.1639 | 9096.0112 | 11401.1639 | 9096.0112 | 0.001563 | 0.0010537 | 1.7563 | 9.5 | 1225 | 0.0036692 | 1709 | 0 | 0 | 7.0844 | 1128 | 0
North Coast | 4594 | 548 | 990.4819 | 853 | 1130.1158 | 75 | 8.5739e-05 | 7.0383 | 3.9573 | 45.0939 | 340.3908 | 4.3488 | 0.25496 | 6.5716 | 1.005 | 0.00060942 | 0.00019363 | 0.64244 | 0.87644 | {DFBBBB18-D02D-419D-977F-28C5BC8837E8} | 43081101 | BIG RIVER 1101 | 1286 | 39.3191 | -123.8002 | BIG RIVER 11011286 | 162 | 195 | 24471.5803 | 12142.2229 | 12329.3575 | 6546.1056 | 4985.4612 | 0.014522 | 0.0064304 | 1.8074 | 11.3733 | 1435 | 0.045707 | 1710 | 0 | 0 | 4.0676 | 2425 | 0
Central Coast | 8009 | 50 | 162.117 | 180 | 224.4624 | 40 | 1.6606e-05 | 46.314 | 0.4689 | 56.821 | 218.7884 | 0.20871 | 2.2222 | 372.7652 | 1.1545 | 0.00060897 | 1.5738e-05 | 0.27778 | 0.72225 | {EA98B02D-6B86-41AE-8783-1ADC45A8F561} | 183071101 | PERRY 1101 | 85870 | 35.5669 | -121.0747 | PERRY 110185870 | 165 | 121 | 33741.7069 | 26928.3914 | 6813.3154 | 14444.7623 | 4316.2773 | 0.0006295 | 0.00066425 | 3.2423 | 4.5 | 2689 | 0.024359 | 1711 | 0 | 0 | 8.9756 | 893 | 0
Central Coast | 6483 | 802 | 1467.8922 | 2458 | 2355.0408 | 275 | 4.7217e-05 | 13.1145 | 8.4256 | 24.4763 | 86.1697 | 1.8709 | 7.0603 | 28.597 | 1.5166 | 0.0006014 | 0.00024903 | 0.32628 | 0.6233 | {C74334F6-C157-4384-BFB7-ED7E4C2B59D6} | 182541101 | ATASCADERO 1101 | A50 | 35.4654 | -120.6712 | ATASCADERO 1101A50 | 463 | 907 | 78714.6125 | 33670.734 | 45043.8785 | 30172.5253 | 40379.3349 | 0.068484 | 0.012985 | 1.8303 | 8.9382 | 1251 | 0.16538 | 1712 | 0 | 0 | 18.7483 | 1279 | 0
Central Valley | 969 | 560 | 788.4834 | 2134 | 1494.5634 | 260 | 8.3027e-05 | 7.3822 | 5.3961 | 28.0127 | 169.3234 | 3.025 | 2.1905 | 23.8325 | 1.0596 | 0.00059828 | 0.00025993 | 0.26242 | 0.52757 | {9D3389CA-CFE2-49B7-8B13-3D1B7ACB399D} | 254421103 | OAKHURST 1103 | 10140 | 37.3666 | -119.6296 | OAKHURST 110310140 | 315 | 437 | 52361.1591 | 27059.5406 | 25301.6184 | 27059.5406 | 25301.6184 | 0.067581 | 0.021587 | 1.408 | 8.2077 | 1226 | 0.15555 | 1713 | 0 | 0 | 16.814 | 2068 | 0
North Valley | 3255 | 244 | 311.971 | 675 | 518.6178 | 76 | 0.00012777 | 5.0768 | 53.9649 | 932.7046 | 17170.7152 | 2676.3055 | 0.60078 | 21.508 | 1.0763 | 0.00059569 | 0.0033935 | 0.36148 | 0.60154 | {EE93E5CE-FD33-44EC-A329-FBA8C511073C} | 103031102 | ORO FINO 1102 | 65932 | 39.8708 | -121.6504 | ORO FINO 110265932 | 77 | 61 | 11700.8582 | 6996.2918 | 4704.5664 | 6996.2918 | 4704.5664 | 0.25791 | 0.0097108 | 1.2786 | 8.8816 | 81 | 0.045272 | 1714 | 0 | 0 | 4.3473 | 142 | 0
Central Valley | 1421 | 230 | 384.8321 | 4270 | 2424.1768 | 187 | 3.8152e-05 | 16.2208 | 75.522 | 586.1455 | 13273.7944 | 5586.1925 | 1.03 | 12.2854 | 1.0217 | 0.00059275 | 0.0010402 | 0.053864 | 0.15875 | {778380F2-BA49-477B-8F0F-740FAC39A283} | 163661701 | MIWUK 1701 | 953336 | 38.0681 | -120.1866 | MIWUK 1701953336 | 267 | 649 | 38818.7116 | 19079.6137 | 19739.0979 | 19079.6137 | 19739.0979 | 0.19451 | 0.0071343 | 1.6732 | 22.8342 | 389 | 0.11084 | 1715 | 0 | 0 | 11.8555 | 480 | 0
Central Valley | 1559 | 497 | 704.2658 | 2095 | 1452.1313 | 290 | 9.3546e-05 | 6.4705 | 22.423 | 862.4798 | 9542.859 | 565.3446 | 1.2875 | 26.7708 | 1.0981 | 0.00058909 | 0.0010646 | 0.23723 | 0.48499 | {E154310E-F1E3-4CE7-BE08-29FE6DF23F68} | 163011101 | MARTELL 1101 | 11244 | 38.391 | -120.7692 | MARTELL 110111244 | 304 | 252 | 58230.0108 | 35268.1557 | 22961.8551 | 33683.9339 | 21316.9034 | 0.30873 | 0.027128 | 1.417 | 7.2241 | 379 | 0.17084 | 1716 | 0 | 0 | 20.9302 | 1349 | 0
Sierra | 7329 | 234 | 379.1073 | 635 | 546.1249 | 115 | 7.441e-05 | 9.3419 | 8.4233 | 469.2824 | 6797.6387 | 239.9446 | 3.6139 | 96.88 | 1.2122 | 0.00058799 | 0.00048332 | 0.3685 | 0.69418 | {8D36000E-CB6A-4063-B9B3-E1FA6651AB85} | 152471101 | COLUMBIA HILL 1101 | 90730 | 39.3426 | -121.1226 | COLUMBIA HILL 110190730 | 108 | 125 | 24412.3835 | 13390.7322 | 11021.6513 | 13390.7322 | 11021.6513 | 0.055582 | 0.0085571 | 1.6201 | 5.5217 | 808 | 0.067619 | 1717 | 0 | 0 | 8.3206 | 1249 | 0
North Coast | 5177 | 714 | 1618.1587 | 735 | 1628.8993 | 58 | 7.4333e-05 | 7.0392 | 0.26423 | 68.2048 | 836.6958 | 0.73599 | 0.059544 | 15.8044 | 1.0053 | 0.00058724 | 5.026e-05 | 0.97143 | 0.99341 | {C44E173D-32C1-4900-92A5-AD54BFE2000C} | 42851121 | FORT ROSS 1121 | 560 | 38.5562 | -123.3034 | FORT ROSS 1121560 | 37 | 24 | 12832.5354 | 9208.7912 | 3623.7443 | 8402.379 | 3076.3906 | 0.0029151 | 0.0043113 | 2.2663 | 12.6724 | 2228 | 0.03406 | 1718 | 0 | 0 | 5.221 | 2161 | 0
North Coast | 1655 | 1352 | 2047.9636 | 2027 | 2356.186 | 214 | 0.00012702 | 6.0879 | 2.7972 | 183.909 | 3421.2035 | 26.9093 | 1.2694 | 18.7007 | 1.0734 | 0.00058422 | 0.00024289 | 0.667 | 0.86919 | {17DD54A2-E0AC-4BEA-A392-1296720E1866} | 192171103 | WILLOW CREEK 1103 | 47966 | 40.9003 | -123.6119 | WILLOW CREEK 110347966 | 290 | 344 | 35725.1302 | 27180.6372 | 8544.493 | 27180.6372 | 8544.493 | 0.051979 | 0.027183 | 1.5148 | 9.472 | 1271 | 0.12502 | 1719 | 0 | 0 | 16.8893 | 272 | 0
Bay Area | 2996 | 11 | 13.1404 | 17 | 16.0988 | 3 | 1.602e-05 | 40.657 | 0 | 17.118 | 38.5353 | 0 | 2.1364 | 190.6305 | 1.101 | 0.00058327 | 1.217e-05 | 0.64706 | 0.81623 | {BBAD7CA8-9930-4EC0-8393-CDE6447A6BA4} | 14402108 | LAS POSITAS 2108 | MR190 | 37.6652 | -121.7354 | LAS POSITAS 2108MR190 | 223 | 126 | 24406.3976 | 17286.4534 | 7119.9442 | 1015.7929 | 1334.3457 | 3.651e-05 | 4.8061e-05 | 1.1946 | 5.6667 | 2761 | 0.0017498 | 1720 | 0 | 0 | 0.63118 | 2847 | 0
Central Valley | 8841 | 1 | 3.0796 | 46 | 16.9256 | 13 | 4.0319e-05 | 14.9393 | 5.1483 | 1024.1148 | 9642.2905 | 51.3814 | 6.1333 | 78.263 | 1.2907 | 0.000576 | 6.5321e-05 | 0.021739 | 0.18195 | {853B9DFF-FC32-431D-BEC5-8F7218514F74} | 252192101 | BEAR VALLEY 2101 | 10019 | 37.5353 | -120.0874 | BEAR VALLEY 210110019 | 12 | 10 | 3898.1903 | 3187.4941 | 710.6962 | 3187.4941 | 710.6962 | 0.00084917 | 0.00052415 | 3.0796 | 3.5385 | 2088 | 0.007488 | 1721 | 0 | 0 | 1.9806 | 1437 | 0
North Coast | 7174 | 60 | 72.7571 | 247 | 156.0482 | 25 | 8.4567e-05 | 6.7214 | 0.35635 | 150.8764 | 1139.3527 | 0.51363 | 0.16593 | 17.2748 | 1.0405 | 0.00057521 | 6.5021e-05 | 0.24291 | 0.46625 | {AD459C08-CBDF-43AA-86A2-CD8C1B5B6101} | 192381102 | EEL RIVER 1102 | 1902 | 40.5279 | -124.1646 | EEL RIVER 11021902 | 53 | 32 | 17655.559 | 11921.8282 | 5733.7308 | 9656.571 | 4971.7217 | 0.0016255 | 0.0021142 | 1.2126 | 9.88 | 2093 | 0.01438 | 1722 | 0 | 0 | 6.0003 | 2623 | 0
Central Coast | 2897 | 3 | 4.069 | 31 | 21.4295 | 8 | 2.4179e-05 | 11.9639 | 8.668 | 57.2628 | 191.5995 | 2.8186 | 11.1963 | 50.0704 | 1.0091 | 0.00057168 | 0.00022899 | 0.096774 | 0.18988 | {4BEE9D9E-BAC4-46AE-B4EA-D5A6948A1B98} | 83432101 | HICKS 2101 | XR162 | 37.2123 | -121.836 | HICKS 2101XR162 | 312 | 478 | 37529.8469 | 15349.8178 | 22180.0291 | 1339.293 | 3306.0968 | 0.0018319 | 0.00019343 | 1.3563 | 3.875 | 1313 | 0.0045734 | 1723 | 0 | 0 | 0.8322 | 1813 | 0
North Valley | 8574 | 584 | 738.9492 | 786 | 834.9239 | 84 | 1.061e-05 | 69.5836 | 3.7067 | 1127.9836 | 24004.2075 | 235.7902 | 0.62482 | 61.9785 | 1.2055 | 0.00057063 | 2.3555e-05 | 0.743 | 0.88505 | {685CF79F-C4BB-4361-A8EF-28010425513E} | 103104401 | SPANISH CREEK 4401 | circuit_breaker | 40.0271 | -120.963 | SPANISH CREEK 4401circuit_breaker | 38 | 43 | 14276.9382 | 12760.2493 | 1516.6889 | 9502.8761 | 1516.6889 | 0.0019786 | 0.00089125 | 1.2653 | 9.3571 | 2552 | 0.047933 | 1724 | 0 | 0 | 5.9048 | 1152 | 0
Central Valley | 5012 | 447 | 732.8868 | 2135 | 1454.6571 | 392 | 5.8891e-05 | 10.7596 | 11.9918 | 246.0316 | 1735.617 | 44.197 | 2.8158 | 108.5478 | 1.3677 | 0.00056968 | 0.00045834 | 0.20937 | 0.50382 | {1D87D320-3344-47D1-AB52-86F36B13B2E4} | 162211101 | CALAVERAS CEMENT 1101 | 502 | 38.1894 | -120.6651 | CALAVERAS CEMENT 1101502 | 424 | 350 | 97818.6924 | 66199.832 | 31618.8605 | 60118.0927 | 28858.2958 | 0.17967 | 0.023085 | 1.6396 | 5.4464 | 852 | 0.22332 | 1725 | 0 | 0 | 37.3556 | 1880 | 0
North Coast | 3962 | 257 | 507.6454 | 572 | 648.9157 | 71 | 6.5838e-05 | 8.1069 | 2.2149 | 5.5552 | 36.6986 | 0.16858 | 2.1785 | 6.8086 | 1.0127 | 0.0005685 | 0.00013098 | 0.4493 | 0.7823 | {7B7F4A99-FA71-47CD-9812-ECE462607E94} | 43311108 | KONOCTI 1108 | 1278 | 38.9559 | -122.7274 | KONOCTI 11081278 | 165 | 389 | 33303.222 | 12812.7853 | 20490.4368 | 7722.6194 | 12123.2999 | 0.0092997 | 0.0046745 | 1.9753 | 8.0563 | 1697 | 0.040363 | 1726 | 0 | 0 | 4.7986 | 1012 | 0
Central Coast | 1855 | 1314 | 2534.0358 | 3581 | 3863.648 | 213 | 9.2079e-05 | 5.0875 | 3.1177 | 17.6519 | 91.3324 | 0.44463 | 0.6696 | 6.1011 | 1.01 | 0.00056517 | 0.0001959 | 0.36694 | 0.65587 | {869A1D07-AF0C-4C1B-B4FB-3299F6D51C09} | 83692104 | ROB ROY 2104 | circuit_breaker | 36.9791 | -121.867 | ROB ROY 2104circuit_breaker | 296 | 308 | 42341.1842 | 22978.5798 | 19362.6044 | 22978.5798 | 19362.6044 | 0.041726 | 0.019613 | 1.9285 | 16.8122 | 1425 | 0.12038 | 1727 | 0 | 0 | 14.2782 | 1414 | 0
Bay Area | 1861 | 386 | 1138.768 | 425 | 1154.4255 | 49 | 0.00010696 | 5.4912 | 2.1064 | 20.0822 | 97.5753 | 0.18539 | 0.44528 | 21.712 | 1.0286 | 0.00056491 | 0.00013758 | 0.90824 | 0.98644 | {B38DB0B8-9B03-4771-A545-1316F725B1B3} | 24101102 | HALF MOON BAY 1102 | 8848 | 37.5278 | -122.5105 | HALF MOON BAY 11028848 | 226 | 412 | 31602.7362 | 16171.7557 | 15430.9805 | 4923.8197 | 2090.8513 | 0.0067415 | 0.0052411 | 2.9502 | 8.6735 | 1650 | 0.027681 | 1728 | 0 | 0 | 3.0595 | 2407 | 0
North Coast | 3304 | 117 | 223.7475 | 208 | 269.3231 | 51 | 8.5483e-05 | 5.6639 | 14.6532 | 677.1514 | 15632.7579 | 1768.8185 | 1.1685 | 19.2828 | 1.0305 | 0.00055682 | 0.00067026 | 0.5625 | 0.83078 | {790F1996-ADCE-423E-BD1D-F157FD535C39} | 43351106 | LUCERNE 1106 | 38436 | 39.0088 | -122.7771 | LUCERNE 110638436 | 127 | 356 | 24732.461 | 7720.9209 | 17011.5401 | 7130.3909 | 16058.8826 | 0.034183 | 0.0043596 | 1.9124 | 4.0784 | 594 | 0.028398 | 1729 | 0 | 0 | 4.4306 | 2057 | 0
North Coast | 6026 | 471 | 761.1769 | 1023 | 1062.8406 | 88 | 0.00013115 | 4.3895 | 10.4977 | 72.5839 | 835.1355 | 13.8945 | 0.67709 | 12.3144 | 1.0098 | 0.00055459 | 0.00079072 | 0.46041 | 0.71617 | {06C5DDF3-68CB-4362-94D6-24163B7FDD9B} | 42811113 | MONTE RIO 1113 | 202 | 38.4984 | -122.9914 | MONTE RIO 1113202 | 87 | 145 | 14088.2023 | 8479.0365 | 5609.1658 | 8479.0365 | 5609.1658 | 0.069584 | 0.011541 | 1.6161 | 11.625 | 504 | 0.048804 | 1730 | 0 | 0 | 5.2686 | 1196 | 0
North Valley | 8106 | 345 | 474.0236 | 715 | 661.1697 | 98 | 0.00013842 | 5.1938 | 11.8294 | 443.6464 | 6001.4353 | 548.541 | 2.0391 | 82.9078 | 1.1746 | 0.00055442 | 0.00089991 | 0.48252 | 0.71695 | {A3DF42BE-4227-4966-A42C-A1B07E133552} | 103031102 | ORO FINO 1102 | 127563 | 39.8707 | -121.6562 | ORO FINO 1102127563 | 84 | 80 | 19674.7456 | 11105.9314 | 8568.8141 | 11105.9314 | 8568.8141 | 0.088191 | 0.013565 | 1.374 | 7.2959 | 444 | 0.054333 | 1731 | 0 | 0 | 6.9009 | 186 | 0
North Coast | 1580 | 744 | 1365.9965 | 1414 | 1700.9229 | 117 | 0.00014688 | 3.7165 | 4.5511 | 21.4357 | 185.871 | 1.5291 | 0.32112 | 6.512 | 1.4773 | 0.00055409 | 0.0004917 | 0.52617 | 0.80309 | {53EC2261-1200-4127-A3BA-F52DA74219E3} | 42811113 | MONTE RIO 1113 | 3970 | 38.4997 | -123.0053 | MONTE RIO 11133970 | 192 | 615 | 36345.8656 | 11846.1263 | 24499.7393 | 11846.1263 | 24499.7393 | 0.057528 | 0.017185 | 1.836 | 12.0855 | 795 | 0.064828 | 1732 | 0 | 0 | 7.3608 | 8 | 0
Central Valley | 2478 | 315 | 453.5232 | 1465 | 1054.5117 | 68 | 7.3347e-05 | 8.1008 | 11.8277 | 36.7374 | 360.5817 | 10.0695 | 0.4201 | 4.7171 | 1.3992 | 0.00055283 | 0.00045179 | 0.21502 | 0.43008 | {9663063B-48E8-470B-AC65-CDCDAD31AE00} | 163661702 | MIWUK 1702 | 8130 | 38.0282 | -120.2571 | MIWUK 17028130 | 225 | 404 | 33840.5844 | 15891.4897 | 17949.0947 | 15891.4897 | 17949.0947 | 0.030722 | 0.0049876 | 1.4398 | 21.5441 | 858 | 0.037592 | 1733 | 0 | 0 | 9.8745 | 2470 | 0
Sierra | 4731 | 405 | 621.6617 | 1067 | 920.6832 | 112 | 0.00014695 | 4.5247 | 3.0059 | 15.468 | 82.7549 | 1.0337 | 1.9455 | 18.4432 | 0.96332 | 0.00055278 | 0.00028393 | 0.37957 | 0.67522 | {69C7055C-8321-466E-890B-DA1A435F5398} | 153081112 | PLACERVILLE 1112 | circuit_breaker | 38.7309 | -120.7834 | PLACERVILLE 1112circuit_breaker | 260 | 687 | 42800.9643 | 15101.3483 | 27699.6161 | 13371.697 | 24617.6335 | 0.031801 | 0.016458 | 1.535 | 9.5268 | 1162 | 0.061911 | 1734 | 0 | 0 | 8.3088 | 59 | 0
Bay Area | 6867 | 1617 | 2604.4199 | 2947 | 3415.953 | 232 | 4.6848e-05 | 12.2672 | 1.3021 | 34.5695 | 155.9252 | 0.36397 | 0.35401 | 14.5475 | 1.0272 | 0.00055231 | 5.4526e-05 | 0.54869 | 0.76243 | {8F9D0578-4CB4-4781-89AC-7B1C36D45FF0} | 24131103 | MENLO 1103 | 8512 | 37.2892 | -122.2132 | MENLO 11038512 | 198 | 143 | 46118.1544 | 26938.1265 | 19180.028 | 26938.1265 | 19180.028 | 0.01265 | 0.010869 | 1.6106 | 12.7026 | 2195 | 0.12814 | 1735 | 0 | 0 | 16.7386 | 2160 | 0
Bay Area | 9113 | 55 | 117.6552 | 244 | 227.5127 | 14 | 8.4453e-05 | 6.8608 | 0.79492 | 4.3617 | 13.3099 | 0.072385 | 0.17383 | 23.0812 | 1.0738 | 0.00055052 | 7.5675e-05 | 0.22541 | 0.51714 | {2F5A2527-DBAC-4BD9-A20F-08237C05AB99} | 24131102 | MENLO 1102 | 8896 | 37.3662 | -122.2136 | MENLO 11028896 | 19 | 15 | 3426.0735 | 2488.0112 | 938.0622 | 1013.7193 | 431.9207 | 0.0010595 | 0.0011823 | 2.1392 | 17.4286 | 2014 | 0.0077072 | 1736 | 0 | 0 | 0.6299 | 2684 | 0
Central Coast | 5601 | 24 | 73.8393 | 144 | 123.4969 | 21 | 2.9155e-05 | 18.492 | 0.87515 | 278.9159 | 1719.5841 | 7.144 | 1.1535 | 60.3903 | 1.0252 | 0.00054983 | 2.6028e-05 | 0.16667 | 0.5979 | {30D7373B-D31B-4D5D-82BF-42F5B4929DAA} | 183071101 | PERRY 1101 | circuit_breaker | 35.571 | -121.0556 | PERRY 1101circuit_breaker | 45 | 25 | 5600.52 | 4085.1746 | 1515.3454 | 4085.1746 | 1515.3454 | 0.0005466 | 0.00061225 | 3.0766 | 6.8571 | 2515 | 0.011547 | 1737 | 0 | 0 | 2.5384 | 1899 | 0
North Valley | 8189 | 19 | 29.5221 | 187 | 120.2839 | 59 | 7.4365e-06 | 115.2704 | 1.5988 | 554.5201 | 3575.6385 | 12.3035 | 3.6095 | 535.8455 | 1.4281 | 0.00054947 | 9.7758e-06 | 0.1016 | 0.24544 | {2548B457-03C9-4EEF-9E95-D0AA3CBA5A67} | 103491101 | MC ARTHUR 1101 | 1544 | 41.0574 | -121.2773 | MC ARTHUR 11011544 | 168 | 143 | 47799.1249 | 44879.1507 | 2919.9742 | 22817.5943 | 756.8792 | 0.00057677 | 0.00043875 | 1.5538 | 3.1695 | 2791 | 0.032419 | 1738 | 0 | 0 | 14.1782 | 1234 | 0
Central Coast | 5779 | 386 | 592.0541 | 1117 | 990.756 | 134 | 3.7794e-05 | 11.9987 | 1.5313 | 15.9554 | 47.3729 | 0.39921 | 2.4792 | 44.2875 | 1.0361 | 0.00054651 | 4.7182e-05 | 0.34557 | 0.59758 | {7A50E1CD-B005-4744-BD76-86E8006C9FCE} | 83242111 | MORGAN HILL 2111 | XR292 | 37.1335 | -121.6754 | MORGAN HILL 2111XR292 | 230 | 148 | 32551.9108 | 19536.8147 | 13015.0961 | 17517.5113 | 11201.7442 | 0.0063224 | 0.0050644 | 1.5338 | 8.3358 | 2262 | 0.073232 | 1739 | 0 | 0 | 10.8849 | 703 | 0
Bay Area | 2783 | 21 | 26.8154 | 108 | 78.997 | 10 | 4.7479e-05 | 16.9177 | 0.034897 | 0.22239 | 0.15842 | 6.9486e-06 | 2.017 | 30.9986 | 1.0084 | 0.00054599 | 2.7728e-05 | 0.19444 | 0.33945 | {2ADB84B9-4752-4713-BF49-15F96D94E1DF} | 24131102 | MENLO 1102 | 9110 | 37.3873 | -122.1919 | MENLO 11029110 | 259 | 294 | 28980.9799 | 15093.0142 | 13887.9657 | 1403.503 | 253.3889 | 0.00027728 | 0.00047479 | 1.2769 | 10.8 | 2494 | 0.0054599 | 1740 | 0 | 0 | 0.8721 | 2573 | 0
Bay Area | 2742 | 22 | 60.7698 | 192 | 162.1503 | 14 | 5.2597e-05 | 10.7808 | 0.11981 | 15.3611 | 31.9784 | 0.0064989 | 0.33613 | 81.1897 | 1.0085 | 0.00054407 | 3.9973e-05 | 0.11458 | 0.37477 | {F5BF7E7D-4C96-4918-ABEF-C33B63B5DD64} | 13501111 | JARVIS 1111 | MR121 | 37.5756 | -121.9726 | JARVIS 1111MR121 | 110 | 380 | 22019.9547 | 8355.9069 | 13664.0477 | 1635.8418 | 144.3716 | 0.00055962 | 0.00073636 | 2.7623 | 13.7143 | 2341 | 0.007617 | 1741 | 0 | 0 | 1.0165 | 2785 | 0
Central Coast | 6613 | 1384 | 2424.441 | 2319 | 2970.0962 | 109 | 0.00023387 | 2.6844 | 12.1807 | 26.0587 | 133.3915 | 2.182 | 0.85498 | 7.2789 | 1.0412 | 0.00054403 | 0.0015242 | 0.59681 | 0.81628 | {EA87785F-FD13-47C1-AD0C-AE56EB6FAE60} | 83041101 | BEN LOMOND 1101 | 96738 | 37.1112 | -122.1143 | BEN LOMOND 110196738 | 162 | 296 | 24126.4963 | 10935.49 | 13191.0063 | 10935.49 | 13191.0063 | 0.16614 | 0.025492 | 1.7518 | 21.2752 | 240 | 0.0593 | 1742 | 0 | 0 | 6.795 | 345 | 0
North Valley | 3937 | 526 | 745.7726 | 1783 | 1407.1738 | 260 | 1.6392e-05 | 39.5233 | 10.8953 | 1096.4302 | 27893.4502 | 689.2425 | 1.3997 | 40.6083 | 1.1228 | 0.00054352 | 0.00010131 | 0.29501 | 0.52998 | {AD16C82F-076B-43F6-B112-51D5058EB123} | 103021101 | GANSNER 1101 | 2006 | 39.9449 | -121.0011 | GANSNER 11012006 | 247 | 364 | 47830.6304 | 27571.1883 | 20259.4422 | 27571.1883 | 20259.4422 | 0.02634 | 0.0042618 | 1.4178 | 6.8577 | 1845 | 0.14132 | 1743 | 0 | 0 | 17.1319 | 765 | 0
Sierra | 7366 | 11 | 15.1382 | 19 | 18.3253 | 3 | 0.00011876 | 7.9911 | 0.0037577 | 0.22239 | 0.97944 | 3.6804e-06 | 0.10988 | 30.985 | 1.2434 | 0.00054333 | 7.8251e-05 | 0.57895 | 0.82608 | {7CD5E23A-1FEF-4DD4-B696-6D5E8A5A222C} | 152481107 | BRUNSWICK 1107 | 65574 | 39.2305 | -121.0346 | BRUNSWICK 110765574 | 92 | 43 | 4339.6091 | 2799.3607 | 1540.2484 | 445.925 | 33.7326 | 0.00023475 | 0.00035629 | 1.3762 | 6.3333 | 1997 | 0.00163 | 1744 | 0 | 0 | 0.27708 | 111 | 0
Central Coast | 4416 | 3968 | 7298.6859 | 6487 | 8772.82 | 435 | 9.2013e-05 | 5.6972 | 4.4292 | 31.0082 | 168.0874 | 1.8905 | 1.6507 | 13.1042 | 1.0366 | 0.00053943 | 0.00025971 | 0.61168 | 0.83197 | {996F801A-49DB-4E12-9C16-86F37BF363D7} | 82021107 | LOS GATOS 1107 | 60118 | 37.1246 | -121.9354 | LOS GATOS 110760118 | 495 | 527 | 84272.9187 | 42371.3391 | 41901.5797 | 42371.3391 | 41901.5797 | 0.11297 | 0.040026 | 1.8394 | 14.9126 | 1229 | 0.23465 | 1745 | 0 | 0 | 26.3283 | 1646 | 0
North Coast | 6453 | 59 | 110.4288 | 93 | 124.0894 | 26 | 7.3718e-05 | 11.2441 | 13.7291 | 258.8751 | 1442.3735 | 71.5228 | 1.6418 | 44.1694 | 1.049 | 0.00053807 | 0.00056028 | 0.63441 | 0.88991 | {E7660F7E-BB9F-4573-B70D-C3EB843F48E4} | 43381101 | POINT ARENA 1101 | 476 | 38.9201 | -123.695 | POINT ARENA 1101476 | 126 | 110 | 30873.9322 | 24431.6786 | 6442.2536 | 4407.3314 | 1531.5138 | 0.014567 | 0.0019167 | 1.8717 | 3.5769 | 723 | 0.01399 | 1746 | 0 | 0 | 2.7386 | 2044 | 0
Central Coast | 1786 | 11 | 23.8461 | 69 | 59.9167 | 18 | 3.7615e-05 | 23.1383 | 8.1464 | 970.3787 | 5531.0588 | 120.1854 | 1.4918 | 101.5991 | 1.028 | 0.00053702 | 0.00025983 | 0.15942 | 0.39799 | {DC1CD14A-C73E-417C-A65E-B1AE2FBC8341} | 183011101 | MORRO BAY 1101 | V66 | 35.3761 | -120.8525 | MORRO BAY 1101V66 | 196 | 213 | 39237.2783 | 26069.3739 | 13167.9044 | 5689.205 | 2706.6441 | 0.004677 | 0.00067706 | 2.1678 | 3.8333 | 1228 | 0.0096664 | 1747 | 0 | 0 | 3.5351 | 1268 | 0
North Coast | 3996 | 405 | 752.6059 | 733 | 932.1195 | 35 | 0.0001515 | 2.1045 | 6.2993 | 23.5803 | 109.2618 | 0.75586 | 0.59779 | 4.5518 | 1.0012 | 0.00053574 | 0.00066065 | 0.55252 | 0.80741 | {C6591A95-C17A-4B6F-BCDF-C2C9AE4418F5} | 42811111 | MONTE RIO 1111 | 140 | 38.4668 | -123.0158 | MONTE RIO 1111140 | 76 | 219 | 10144.4325 | 4235.2908 | 5909.1417 | 4235.2908 | 5909.1417 | 0.023123 | 0.0053026 | 1.8583 | 20.9429 | 602 | 0.018751 | 1748 | 0 | 0 | 2.6317 | 1659 | 0
North Coast | 3904 | 192 | 230.9111 | 359 | 314.0174 | 27 | 9.8899e-05 | 6.239 | 2.2767 | 57.9024 | 506.8226 | 2.4561 | 2.004 | 14.6545 | 0.97108 | 0.00053301 | 0.00019099 | 0.53482 | 0.73534 | {F4C78492-32F9-47FB-AA37-4818CAE3C60E} | 43321101 | RINCON 1101 | 576 | 38.4647 | -122.6512 | RINCON 1101576 | 281 | 371 | 33656.7823 | 16916.5683 | 16740.214 | 4105.0155 | 2103.8446 | 0.0051566 | 0.0026703 | 1.2027 | 13.2963 | 1449 | 0.014391 | 1749 | 0 | 0 | 2.5507 | 72 | 0
Sierra | 2888 | 1181 | 1882.465 | 5198 | 3443.537 | 509 | 0.00012032 | 5.0674 | 7.3114 | 34.3037 | 219.9398 | 5.8387 | 2.5907 | 23.924 | 1.1602 | 0.00053262 | 0.00048004 | 0.2272 | 0.54667 | {F21436B1-06B1-4781-A6B4-F2B85E06831B} | 152261103 | DIAMOND SPRINGS 1103 | circuit_breaker | 38.6929 | -120.826 | DIAMOND SPRINGS 1103circuit_breaker | 1221 | 1717 | 167473.4056 | 82294.0421 | 85179.3635 | 52640.7509 | 49274.1125 | 0.24434 | 0.06124 | 1.594 | 10.2122 | 811 | 0.27111 | 1750 | 0 | 0 | 32.7094 | 2388 | 0
North Valley | 7175 | 80 | 161.3362 | 435 | 323.8765 | 49 | 2.7285e-05 | 22.3808 | 14.2013 | 523.3377 | 10259.3474 | 286.1863 | 0.23316 | 26.4396 | 1.0428 | 0.00053172 | 0.00020346 | 0.18391 | 0.49814 | {40490190-B706-4F2D-B025-20A71CF73A68} | 102211103 | BUCKS CREEK 1103 | 1131 | 39.8684 | -121.1742 | BUCKS CREEK 11031131 | 49 | 71 | 8567.9493 | 4424.1224 | 4143.827 | 4424.1224 | 4143.827 | 0.0099696 | 0.001337 | 2.0167 | 8.8776 | 1402 | 0.026054 | 1751 | 0 | 0 | 2.749 | 1889 | 0
Sierra | 177 | 296 | 466.3644 | 1001 | 848.2917 | 126 | 0.00010533 | 5.1543 | 6.2962 | 11.6479 | 35.8906 | 0.65377 | 2.2991 | 9.1885 | 1.423 | 0.00053103 | 0.00036778 | 0.2957 | 0.54977 | {5975A3D8-5B89-4D93-9C6D-113094290849} | 152691104 | HIGGINS 1104 | 1374 | 39.0988 | -121.0521 | HIGGINS 11041374 | 213 | 414 | 34992.808 | 13460.5941 | 21532.2139 | 12504.4738 | 19850.0149 | 0.04634 | 0.013272 | 1.5756 | 7.9444 | 988 | 0.06691 | 1752 | 0 | 0 | 7.7699 | 85 | 0
North Coast | 7873 | 111 | 153.91 | 243 | 229.4237 | 16 | 0.00015423 | 3.0366 | 26.9273 | 159.4183 | 1473.2813 | 89.8316 | 1.2565 | 17.0478 | 1.5268 | 0.00053027 | 0.0017822 | 0.45679 | 0.67086 | {26F9807C-D309-4EC8-8DD1-024F50CB1287} | 42811112 | MONTE RIO 1112 | 999 | 38.4221 | -122.954 | MONTE RIO 1112999 | 19 | 113 | 6159.4933 | 1406.4428 | 4753.0505 | 1406.4428 | 4753.0505 | 0.028515 | 0.0024676 | 1.3866 | 15.1875 | 199 | 0.0084844 | 1753 | 0 | 0 | 0.87392 | 1910 | 0
Central Valley | 9933 | 0 | 0 | 1 | 0.21341 | 1 | 1.9378e-05 | 27.3296 |  |  |  |  | 1.7412 | 352.452 | 1.2942 | 0.0005296 | 1.9378e-05 | 0 | 0 | {885453EE-C081-4617-8ED9-DAFDFB250BE8} | 163781704 | PEORIA 1704 | 92888 | 37.8883 | -120.522 | PEORIA 170492888 | 7 | 0 | 765.3621 | 765.3621 | 0 | 400.6025 | 0 | 1.9378e-05 | 1.9378e-05 |  | 1 | 2623 | 0.0005296 | 1754 | 0 | 0 | 0.24892 | 1512 | 0
North Valley | 7811 | 936 | 1241.3916 | 1462 | 1548.5214 | 185 | 7.4214e-06 | 94.507 | 2.6704 | 489.5529 | 5203.3442 | 53.2414 | 2.8653 | 192.4125 | 1.2577 | 0.00052817 | 1.4228e-05 | 0.64022 | 0.80166 | {50FC30D9-9631-47C1-AB52-87E3C16BC0D9} | 103132101 | CRESCENT MILLS 2101 | 2562 | 40.1081 | -120.9068 | CRESCENT MILLS 21012562 | 293 | 254 | 74966.102 | 54701.1021 | 20264.9999 | 25377.9444 | 10433.0671 | 0.0026323 | 0.001373 | 1.3263 | 7.9027 | 2718 | 0.097711 | 1755 | 0 | 0 | 15.7691 | 458 | 0
Central Valley | 841 | 8 | 10.6451 | 314 | 146.8359 | 69 | 1.3678e-05 | 39.1282 | 0.52412 | 70.6025 | 352.9451 | 0.14721 | 0.012152 | 22.5345 | 1.0501 | 0.0005265 | 9.8851e-06 | 0.025478 | 0.072497 | {CFBBFBB1-419F-4DD9-BB1F-9B2617993BDF} | 163692101 | SALT SPRINGS 2101 | 1216 | 38.4989 | -120.2177 | SALT SPRINGS 21011216 | 40 | 80 | 11657.793 | 8899.3047 | 2758.4883 | 8899.3047 | 2758.4883 | 0.00068207 | 0.00094377 | 1.3306 | 4.5507 | 2790 | 0.036328 | 1756 | 0 | 0 | 5.5298 | 2732 | 0
Central Coast | 6139 | 577 | 1189.7097 | 930 | 1403.8208 | 68 | 8.1418e-05 | 7.0859 | 2.4188 | 41.7243 | 184.3348 | 1.1708 | 0.74896 | 29.6342 | 1.0614 | 0.00052544 | 0.00012271 | 0.62043 | 0.84748 | {1058939C-63D6-4E6A-BE26-51405BD3A77F} | 83192101 | GREEN VALLEY 2101 | 36820 | 36.958 | -121.7297 | GREEN VALLEY 210136820 | 255 | 335 | 50417.1229 | 26572.8864 | 23844.2365 | 7189.3721 | 1883.2912 | 0.0083439 | 0.0055364 | 2.0619 | 13.6765 | 1738 | 0.03573 | 1757 | 0 | 0 | 4.4673 | 1530 | 0
Central Coast | 659 | 2951 | 5292.0488 | 5306 | 6609.6387 | 317 | 0.00017039 | 3.9673 | 4.3111 | 30.148 | 140.988 | 0.98532 | 0.94932 | 12.0274 | 1.046 | 0.00052282 | 0.00045881 | 0.55616 | 0.80066 | {8DE472F3-E517-45DB-B3CD-7520098E73B7} | 83622104 | CAMP EVERS 2104 | 5096 | 37.0511 | -122.037 | CAMP EVERS 21045096 | 350 | 603 | 68309.7589 | 33040.8953 | 35268.8636 | 32780.5456 | 35268.8636 | 0.14544 | 0.054014 | 1.7933 | 16.7382 | 850 | 0.16573 | 1758 | 0 | 0 | 20.3689 | 2149 | 0
Central Coast | 5572 | 1592 | 3037.4115 | 2416 | 3461.01 | 183 | 9.2622e-05 | 5.4173 | 1.4825 | 32.2457 | 140.2821 | 0.43326 | 1.8411 | 31.707 | 1.0843 | 0.00052231 | 0.00011614 | 0.65894 | 0.87761 | {C405C907-DA8C-4647-B06E-C99DEABE607F} | 83192101 | GREEN VALLEY 2101 | 11054 | 36.9775 | -121.7415 | GREEN VALLEY 210111054 | 339 | 286 | 76130.1436 | 40835.6292 | 35294.5144 | 38401.1556 | 31336.6718 | 0.021254 | 0.01695 | 1.9079 | 13.2022 | 1770 | 0.095583 | 1759 | 0 | 0 | 23.8614 | 1681 | 0
Bay Area | 9136 | 60 | 79.1424 | 179 | 155.8 | 41 | 1.2966e-05 | 42.1378 | 0.067079 | 83.8739 | 314.6278 | 0.20361 | 1.2556 | 526.8407 | 1.5895 | 0.00051912 | 6.5082e-06 | 0.3352 | 0.50797 | {475B4CFB-84F1-46E3-9FF3-409BD1FA54D8} | 14241101 | SUNOL 1101 | MR387 | 37.5735 | -121.864 | SUNOL 1101MR387 | 35 | 11 | 8208.0016 | 8023.8265 | 184.1751 | 7477.4807 | 159.0432 | 0.00026683 | 0.00053159 | 1.319 | 4.3659 | 2831 | 0.021284 | 1760 | 0 | 0 | 4.6463 | 1773 | 0
Central Valley | 2412 | 304 | 708.7118 | 1861 | 1377.2903 | 166 | 3.012e-05 | 17.2502 | 5.7222 | 415.945 | 7565.0012 | 82.1417 | 0.57084 | 18.2897 | 1.0159 | 0.00051779 | 8.8139e-05 | 0.16335 | 0.51457 | {15EFA531-A43D-4849-828D-DC9485A13753} | 254421103 | OAKHURST 1103 | 10190 | 37.4144 | -119.6272 | OAKHURST 110310190 | 208 | 358 | 45339.2171 | 18572.0473 | 26767.1698 | 18572.0473 | 26767.1698 | 0.014631 | 0.0049999 | 2.3313 | 11.2108 | 1924 | 0.085952 | 1761 | 0 | 0 | 11.5401 | 1272 | 0
Central Valley | 9302 | 32 | 46.378 | 170 | 112.9711 | 40 | 1.4774e-05 | 25.2518 | 0.028315 | 119.7271 | 968.0347 | 0.06114 | 0.35404 | 197.6379 | 1.584 | 0.00051449 | 7.5484e-06 | 0.18824 | 0.41053 | {75BFEF05-1988-4830-B09E-C95373B77F35} | 252501101 | BALCH NO 1 1101 | R372 | 36.9129 | -119.081 | BALCH NO 1 1101R372 | 18 | 2 | 9913.6989 | 9846.4194 | 67.2795 | 9846.4194 | 67.2795 | 0.00030194 | 0.00059096 | 1.4493 | 4.25 | 2816 | 0.020579 | 1762 | 0 | 0 | 6.1183 | 359 | 0
Central Valley | 5284 | 81 | 126.9682 | 293 | 219.231 | 34 | 6.3274e-05 | 11.2532 | 25.1342 | 217.0313 | 1593.0225 | 46.9682 | 4.0276 | 42.7232 | 1.1577 | 0.00051011 | 0.00063187 | 0.27645 | 0.57915 | {24E78F9F-8085-415C-92D5-690939A42C94} | 163451701 | FROGTOWN 1701 | L3361 | 38.131 | -120.4373 | FROGTOWN 1701L3361 | 40 | 77 | 6637.4584 | 3015.6838 | 3621.7746 | 3015.6838 | 3621.7746 | 0.021483 | 0.0021513 | 1.5675 | 8.6176 | 636 | 0.017344 | 1763 | 0 | 0 | 1.8739 | 1050 | 0
Central Valley | 3938 | 66 | 205.6603 | 266 | 298.2803 | 54 | 2.3894e-05 | 22.5168 | 8.8847 | 926.0071 | 19707.2724 | 302.8411 | 0.0014749 | 18.0703 | 1.0529 | 0.0005098 | 0.00012239 | 0.24812 | 0.68949 | {F8BEC349-F596-4C98-AE0E-999ADE59AE2E} | 254421103 | OAKHURST 1103 | 5120 | 37.4809 | -119.6372 | OAKHURST 11035120 | 29 | 5 | 10315.4166 | 10236.3208 | 79.0958 | 10236.3208 | 79.0958 | 0.0066088 | 0.0012903 | 3.1161 | 4.9259 | 1741 | 0.027529 | 1764 | 0 | 0 | 6.3606 | 55 | 0
Sierra | 1866 | 468 | 741.9201 | 1332 | 1139.4634 | 96 | 0.00017547 | 5.2642 | 4.9768 | 9.1529 | 35.1588 | 0.5733 | 1.0039 | 5.7609 | 1.1853 | 0.00050952 | 0.00047467 | 0.35135 | 0.65111 | {15D1F2F0-3D88-4B18-AFEC-B03FE833977B} | 153081111 | PLACERVILLE 1111 | circuit_breaker | 38.731 | -120.7833 | PLACERVILLE 1111circuit_breaker | 218 | 503 | 28628.5409 | 10619.6052 | 18008.9358 | 10305.9598 | 17342.4627 | 0.045569 | 0.016845 | 1.5853 | 13.875 | 817 | 0.048914 | 1765 | 0 | 0 | 6.4038 | 518 | 0
Central Valley | 8506 | 13 | 23.8966 | 117 | 65.3313 | 19 | 7.7098e-05 | 8.8318 | 2.0927 | 65.4346 | 230.1041 | 0.79635 | 2.2542 | 39.7203 | 1.1579 | 0.00050897 | 0.00013417 | 0.11111 | 0.36578 | {21D2A9B2-3258-44D7-A4FD-EDFB8BC88DE8} | 163781705 | PEORIA 1705 | 70198 | 37.9573 | -120.4383 | PEORIA 170570198 | 84 | 85 | 8397.8451 | 5122.9043 | 3274.9408 | 3727.5999 | 779.5944 | 0.0025493 | 0.0014649 | 1.8382 | 6.1579 | 1678 | 0.0096704 | 1766 | 0 | 0 | 2.3162 | 1904 | 0
Sierra | 1086 | 36 | 68.2492 | 70 | 81.591 | 8 | 9.1484e-05 | 11.9285 | 3.8339 | 5.2133 | 22.2134 | 0.40848 | 5.5127 | 15.7753 | 2.6142 | 0.00050831 | 0.0001347 | 0.51429 | 0.83648 | {F20DF12E-C49B-40A8-AAFB-7DBBC88F8ED9} | 152461104 | PLACER 1104 | 51732 | 38.9058 | -121.0824 | PLACER 110451732 | 317 | 415 | 29938.2724 | 13388.5594 | 16549.713 | 825.7758 | 519.6115 | 0.0010776 | 0.00073188 | 1.8958 | 8.75 | 1669 | 0.0040665 | 1767 | 0 | 0 | 0.51311 | 1416 | 0
Central Coast | 8891 | 937 | 1634.3704 | 1542 | 1968.7677 | 86 | 9.1996e-05 | 5.5967 | 6.2015 | 57.1158 | 239.5435 | 1.8156 | 0.21416 | 18.104 | 1.0049 | 0.00050107 | 0.00042277 | 0.60765 | 0.83015 | {C935E616-2A18-4E49-AA77-D9A22DDDA4F7} | 82841102 | BIG BASIN 1102 | 8403 | 37.1548 | -122.1333 | BIG BASIN 11028403 | 56 | 130 | 16583.4124 | 7917.119 | 8666.2934 | 7917.119 | 8666.2934 | 0.036359 | 0.0079117 | 1.7443 | 17.9302 | 906 | 0.043092 | 1768 | 0 | 0 | 4.9195 | 163 | 0
Central Valley | 1412 | 663 | 936.7879 | 2929 | 2031.3087 | 114 | 5.5427e-05 | 9.6636 | 32.9761 | 138.5463 | 2345.2904 | 476.9763 | 1.1577 | 13.7178 | 1.1466 | 0.00049975 | 0.0008966 | 0.22636 | 0.46117 | {CA297791-685C-4EDD-BB53-30F381A39ACF} | 163661701 | MIWUK 1701 | 11800 | 38.0253 | -120.2212 | MIWUK 170111800 | 237 | 612 | 44060.2079 | 15184.802 | 28875.4059 | 15184.802 | 28875.4059 | 0.10221 | 0.0063187 | 1.413 | 25.693 | 448 | 0.056971 | 1769 | 0 | 0 | 9.4354 | 232 | 0
Central Coast | 5603 | 464 | 747.4391 | 1020 | 1086.9529 | 89 | 8.6529e-05 | 6.7067 | 1.0698 | 20.8763 | 70.3469 | 0.17256 | 1.5638 | 45.9425 | 1.0869 | 0.00049813 | 9.2162e-05 | 0.4549 | 0.68765 | {281B3385-4F71-4EC0-B77E-390E15EC23C1} | 83252107 | PAUL SWEET 2107 | 10986 | 36.9615 | -122.0627 | PAUL SWEET 210710986 | 251 | 202 | 48380.3787 | 31999.8278 | 16380.5509 | 13450.8089 | 8321.0868 | 0.0082024 | 0.007701 | 1.6109 | 11.4607 | 1894 | 0.044334 | 1770 | 0 | 0 | 8.3579 | 329 | 0
Bay Area | 5660 | 909 | 1841.3605 | 2892 | 2927.3389 | 159 | 6.5147e-05 | 7.5406 | 7.1311 | 328.4517 | 7135.031 | 92.9018 | 0.25852 | 4.3082 | 0.99969 | 0.00049416 | 0.00029274 | 0.31432 | 0.62902 | {48696EF7-D14F-4A4B-98EA-50D58AFE2188} | 42291101 | OLEMA 1101 | 1318 | 38.0643 | -122.8056 | OLEMA 11011318 | 183 | 310 | 28341.497 | 16637.0018 | 11704.4953 | 13978.4041 | 10574.1892 | 0.046546 | 0.010358 | 2.0257 | 18.1887 | 1144 | 0.078571 | 1771 | 0 | 0 | 8.6858 | 2128 | 0
Sierra | 82 | 1112 | 1593.549 | 2449 | 2246.7603 | 225 | 0.00010217 | 5.2459 | 8.3546 | 40.4841 | 261.6878 | 5.9157 | 0.94188 | 13.3759 | 1.1387 | 0.00049415 | 0.00045192 | 0.45406 | 0.70927 | {58053B57-CF0F-4598-8422-637942A9C73B} | 152241101 | HALSEY 1101 | 1704 | 38.9946 | -121.0261 | HALSEY 11011704 | 285 | 442 | 47706.8355 | 21258.1613 | 26448.6742 | 21258.1613 | 26314.5605 | 0.10168 | 0.022988 | 1.433 | 10.8844 | 856 | 0.11118 | 1772 | 0 | 0 | 13.2092 | 2099 | 0
Central Valley | 8273 | 49 | 70.4075 | 140 | 118.6676 | 34 | 1.1191e-05 | 40.1716 | 18.05 | 629.6745 | 6147.8036 | 211.5341 | 2.7683 | 298.2226 | 1.5197 | 0.0004939 | 9.8435e-05 | 0.35 | 0.59332 | {2C485712-3D09-43E6-B47A-A2006FA28A66} | 254061103 | DUNLAP 1103 | circuit_breaker | 36.7097 | -119.0297 | DUNLAP 1103circuit_breaker | 50 | 21 | 11208.8511 | 8988.316 | 2220.5351 | 8988.316 | 2220.5351 | 0.0033468 | 0.00038048 | 1.4369 | 4.1176 | 1859 | 0.016793 | 1773 | 0 | 0 | 5.5851 | 1214 | 0
Central Coast | 753 | 2 | 2.492 | 45 | 30.8571 | 19 | 3.6162e-05 | 22.1377 | 0.056188 | 28.6933 | 92.4444 | 0.017946 | 0.60806 | 105.487 | 1.3173 | 0.00048998 | 1.9935e-05 | 0.044444 | 0.080761 | {72D51786-0F19-4A21-BD91-493BA8FA331E} | 182811103 | SISQUOC 1103 | M98 | 34.8946 | -120.3018 | SISQUOC 1103M98 | 76 | 40 | 16378.9039 | 15489.3429 | 889.5611 | 11235.2762 | 726.5219 | 0.00037876 | 0.00068708 | 1.246 | 2.3684 | 2610 | 0.0093097 | 1774 | 0 | 0 | 6.9813 | 2466 | 0
Central Valley | 2669 | 554 | 774.8252 | 3602 | 2389.0706 | 142 | 6.1163e-05 | 7.4341 | 46.4608 | 139.5552 | 2117.2476 | 760.0654 | 0.72592 | 7.7647 | 1.146 | 0.00048991 | 0.0012171 | 0.1538 | 0.32432 | {5DE457D9-5E7A-46A3-820A-688DCA33A9BB} | 163661702 | MIWUK 1702 | circuit_breaker | 38.0528 | -120.2169 | MIWUK 1702circuit_breaker | 226 | 380 | 32124.8788 | 16506.2205 | 15618.6583 | 16506.2205 | 15618.6583 | 0.17283 | 0.0086852 | 1.3986 | 25.3662 | 316 | 0.069568 | 1775 | 0 | 0 | 10.2565 | 2568 | 0
North Coast | 5340 | 530 | 771.5963 | 1043 | 1024.3157 | 130 | 0.00011343 | 4.4565 | 0.30564 | 91.755 | 480.5504 | 0.28481 | 0.096801 | 17.0284 | 1.009 | 0.00048935 | 7.3495e-05 | 0.50815 | 0.75328 | {D3EDA1A2-8AF8-4A2A-853E-161161439812} | 192101101 | MAPLE CREEK 1101 | circuit_breaker | 40.7681 | -123.8739 | MAPLE CREEK 1101circuit_breaker | 84 | 50 | 25203.5646 | 23066.1262 | 2137.4384 | 15254.5949 | 1348.0661 | 0.0095544 | 0.014746 | 1.4558 | 8.0231 | 2033 | 0.063615 | 1776 | 0 | 0 | 9.4788 | 2510 | 0
Sierra | 6143 | 52 | 64.496 | 139 | 105.5021 | 12 | 7.6667e-05 | 6.0099 | 16.4594 | 112.3873 | 1854.5994 | 81.3972 | 0.28226 | 4.4563 | 1.0017 | 0.00048899 | 0.00088184 | 0.3741 | 0.61132 | {BE84EF6E-6642-4AA6-9D64-6402D1C22F4F} | 152481105 | BRUNSWICK 1105 | 84480 | 39.2462 | -121.0032 | BRUNSWICK 110584480 | 101 | 70 | 12921.2096 | 7615.7819 | 5305.4277 | 7615.7819 | 5305.4277 | 0.010582 | 0.00092 | 1.2403 | 11.5833 | 457 | 0.0058678 | 1777 | 0 | 0 | 4.7322 | 240 | 0
North Valley | 8004 | 33 | 52.8487 | 73 | 67.55 | 26 | 6.7426e-05 | 7.0329 | 6.7818 | 557.0489 | 4265.3377 | 52.226 | 2.7444 | 134.7027 | 1.2708 | 0.00048416 | 0.0001933 | 0.45205 | 0.78236 | {2B40E2E2-0FAB-45BB-A860-E69F414C038B} | 102041104 | NOTRE DAME 1104 | 2537 | 39.7912 | -121.7218 | NOTRE DAME 11042537 | 43 | 60 | 11375.6747 | 8206.2423 | 3169.4323 | 8206.2423 | 3169.4323 | 0.0050259 | 0.0017531 | 1.6015 | 2.8077 | 1437 | 0.012588 | 1778 | 0 | 0 | 5.0991 | 2486 | 0
North Valley | 6787 | 1722 | 2530.0753 | 3586 | 3445.1145 | 374 | 8.4666e-05 | 6.0471 | 19.2744 | 456.4818 | 6479.4807 | 328.2952 | 0.35912 | 17.2495 | 1.0221 | 0.00048057 | 0.0008508 | 0.4802 | 0.7344 | {BCBFDCD7-6D09-427B-8565-FE77C2D532E0} | 102971111 | SYCAMORE CREEK 1111 | 2268 | 39.9032 | -121.7421 | SYCAMORE CREEK 11112268 | 327 | 330 | 61567.0341 | 35773.7446 | 25793.2895 | 35773.7446 | 25793.2895 | 0.3182 | 0.031665 | 1.4693 | 9.5882 | 470 | 0.17973 | 1779 | 0 | 0 | 22.2288 | 841 | 0
Bay Area | 7506 | 46 | 104.977 | 99 | 138.8007 | 20 | 5.0063e-05 | 9.5854 | 0.19326 | 23.5024 | 99.7122 | 0.035079 | 0.54469 | 42.0649 | 1.1584 | 0.00047746 | 3.2362e-05 | 0.46465 | 0.75631 | {47119C60-3B98-4B39-982B-BF99BDAD5FAA} | 12101102 | OAKLAND K 1102 | 17430 | 37.8611 | -122.209 | OAKLAND K 110217430 | 24 | 4 | 2434.0428 | 2362.1685 | 71.8742 | 2362.1685 | 71.8742 | 0.00064725 | 0.0010013 | 2.2821 | 4.95 | 2436 | 0.0095491 | 1780 | 0 | 0 | 1.4678 | 2706 | 0
North Valley | 5834 | 286 | 409.5237 | 508 | 526.6929 | 71 | 8.3584e-06 | 49.6529 | 9.6709 | 1327.0002 | 25981.9201 | 421.9377 | 2.5368 | 94.1236 | 1.0848 | 0.00047137 | 4.3639e-05 | 0.56299 | 0.77754 | {729A138E-F406-4953-BD8A-A6BF7C82CC1C} | 103132101 | CRESCENT MILLS 2101 | 2230 | 40.0847 | -120.9178 | CRESCENT MILLS 21012230 | 171 | 279 | 29790.9216 | 17863.1589 | 11927.7627 | 8832.0855 | 3561.2292 | 0.0030984 | 0.00059344 | 1.4319 | 7.1549 | 2294 | 0.033467 | 1781 | 0 | 0 | 5.488 | 1686 | 0
Sierra | 1833 | 288 | 417.0428 | 777 | 668.2753 | 97 | 0.00011563 | 3.7408 | 6.6426 | 17.7464 | 112.1845 | 2.3628 | 1.9655 | 8.9638 | 1.1224 | 0.00046827 | 0.00056766 | 0.37066 | 0.62406 | {77DD24A4-3555-45C1-AFB0-D6E3B0D6C267} | 152691104 | HIGGINS 1104 | 842642 | 39.1268 | -121.056 | HIGGINS 1104842642 | 144 | 249 | 21534.8183 | 9304.2839 | 12230.5344 | 9304.2839 | 12230.5344 | 0.055063 | 0.011216 | 1.4481 | 8.0103 | 714 | 0.045422 | 1782 | 0 | 0 | 5.7814 | 288 | 0
Central Coast | 3984 | 25 | 35.0166 | 190 | 109.5748 | 49 | 2.141e-05 | 24.8068 | 1.5112 | 493.1973 | 3165.8983 | 18.9477 | 1.4524 | 135.4333 | 1.1146 | 0.00046333 | 2.2699e-05 | 0.13158 | 0.31957 | {15367F9D-D171-45F6-9CB4-6F5003394A6D} | 182981102 | JOLON 1102 | 7040 | 36.0453 | -121.1755 | JOLON 11027040 | 149 | 100 | 45573.1098 | 36880.7714 | 8692.3385 | 31780.5056 | 8570.7075 | 0.0011123 | 0.0010491 | 1.4007 | 3.8776 | 2569 | 0.022703 | 1783 | 0 | 0 | 19.7475 | 1961 | 0
Sierra | 2936 | 903 | 1246.2674 | 1862 | 1708.882 | 200 | 7.8027e-05 | 6.1291 | 44.6206 | 531.5653 | 6914.7903 | 1041.3614 | 2.3747 | 23.1907 | 1.0691 | 0.0004631 | 0.0016391 | 0.48496 | 0.72929 | {486AA3F8-488C-4B89-9A1D-60C9962E4FCD} | 152431101 | SHADY GLEN 1101 | 32726 | 39.1012 | -120.9597 | SHADY GLEN 110132726 | 241 | 265 | 37785.8331 | 20171.8595 | 17613.9736 | 20147.5271 | 17578.2081 | 0.32782 | 0.015605 | 1.3801 | 9.31 | 219 | 0.09262 | 1784 | 0 | 0 | 12.5191 | 135 | 0
Central Valley | 937 | 296 | 412.9011 | 1260 | 878.9219 | 152 | 7.4188e-05 | 6.6336 | 45.5524 | 498.4755 | 7285.3666 | 718.0429 | 0.59838 | 23.8425 | 1.1044 | 0.00046219 | 0.0019271 | 0.23492 | 0.46978 | {2EBFCB83-8CD9-4937-9DF1-5F0721235A72} | 162821701 | STANISLAUS 1701 | 79826 | 38.1699 | -120.4067 | STANISLAUS 170179826 | 150 | 142 | 25547.8218 | 16403.2639 | 9144.5579 | 16403.2639 | 9144.5579 | 0.29292 | 0.011277 | 1.3949 | 8.2895 | 183 | 0.070253 | 1785 | 0 | 0 | 10.1925 | 615 | 0
Central Coast | 669 | 4317 | 7686.3689 | 8153 | 9892.788 | 442 | 0.00015477 | 2.9174 | 3.9296 | 25.5861 | 108.3694 | 0.86129 | 0.7976 | 10.6125 | 1.0225 | 0.00046108 | 0.00039668 | 0.5295 | 0.77697 | {77218484-2483-4A3A-8ACC-0336A0ABECA8} | 83622106 | CAMP EVERS 2106 | 12760 | 37.0676 | -121.9966 | CAMP EVERS 210612760 | 464 | 459 | 70236.8628 | 42950.8829 | 27285.9799 | 42934.8809 | 27285.9799 | 0.17533 | 0.068406 | 1.7805 | 18.4457 | 948 | 0.2038 | 1786 | 0 | 0 | 26.6785 | 2107 | 0
Bay Area | 2552 | 684 | 1189.9152 | 1267 | 1548.748 | 107 | 7.6376e-05 | 4.0653 | 0.15454 | 8.2115 | 20.5381 | 0.003312 | 0.43677 | 10.392 | 0.9113 | 0.00045986 | 4.1431e-05 | 0.53986 | 0.76831 | {BF748DD1-7EA7-463E-91B5-1F0876DD9BB0} | 24080401 | EMERALD LAKE 0401 | circuit_breaker | 37.4617 | -122.2772 | EMERALD LAKE 0401circuit_breaker | 400 | 747 | 65451.3985 | 33996.9433 | 31454.4551 | 23419.0309 | 28782.2307 | 0.0044331 | 0.0081723 | 1.7396 | 11.8411 | 2317 | 0.049205 | 1787 | 0 | 0 | 14.5519 | 2799 | 0
Sierra | 4312 | 289 | 406.4129 | 581 | 532.5356 | 30 | 4.5077e-05 | 10.3705 | 152.558 | 777.2427 | 16995.9961 | 4224.8683 | 1.5767 | 8.4995 | 0.93614 | 0.00045777 | 0.0034666 | 0.49742 | 0.76317 | {CA8C5C3E-040A-472D-90D3-B9F88671ADCD} | 152481105 | BRUNSWICK 1105 | 3611 | 39.2642 | -120.9099 | BRUNSWICK 11053611 | 44 | 116 | 7695.3966 | 2597.3823 | 5098.0143 | 2597.3823 | 5098.0143 | 0.104 | 0.0013523 | 1.4063 | 19.3667 | 79 | 0.013733 | 1788 | 0 | 0 | 1.6139 | 102 | 0
Bay Area | 5700 | 98 | 255.7335 | 545 | 504.3555 | 71 | 4.3724e-05 | 17.6552 | 8.2288 | 18.0341 | 65.4636 | 3.3196 | 2.9816 | 36.9301 | 0.99685 | 0.00045718 | 0.00016336 | 0.17982 | 0.50705 | {58409F43-908C-4F7B-B13E-65AE96367D27} | 14091108 | CASTRO VALLEY 1108 | MR243 | 37.7022 | -122.0452 | CASTRO VALLEY 1108MR243 | 116 | 469 | 32884.9613 | 8931.2655 | 23953.6958 | 8931.2655 | 23953.6958 | 0.011598 | 0.0031044 | 2.6095 | 7.6761 | 1538 | 0.03246 | 1789 | 0 | 0 | 5.5496 | 2432 | 0
Central Coast | 1146 | 508 | 866.4424 | 1021 | 1148.2574 | 63 | 0.0002348 | 1.9538 | 6.0573 | 8.671 | 72.8373 | 1.1728 | 0.4481 | 4.2056 | 1.0006 | 0.00045711 | 0.00086846 | 0.49755 | 0.75457 | {0F585841-A965-44FC-98CB-5C72CA920770} | 82841101 | BIG BASIN 1101 | 95690 | 37.1249 | -122.125 | BIG BASIN 110195690 | 144 | 426 | 23842.8408 | 6270.3435 | 17572.4973 | 6270.3435 | 17572.4973 | 0.054713 | 0.014792 | 1.7056 | 16.2063 | 461 | 0.028798 | 1790 | 0 | 0 | 3.8962 | 1150 | 0
North Coast | 5533 | 534 | 914.5176 | 1918 | 1438.4777 | 213 | 5.4599e-05 | 9.0374 | 4.9331 | 392.332 | 6458.3093 | 69.0527 | 1.3172 | 42.5396 | 1.1929 | 0.00045595 | 0.00015002 | 0.27842 | 0.63575 | {A99474C6-C1F9-4A19-8465-2D8ED25CEFB7} | 42771115 | UKIAH 1115 | circuit_breaker | 39.1433 | -123.1916 | UKIAH 1115circuit_breaker | 433 | 536 | 75254.8118 | 40874.779 | 34380.0328 | 26755.7552 | 28626.4167 | 0.031955 | 0.01163 | 1.7126 | 9.0047 | 1592 | 0.097118 | 1791 | 0 | 0 | 16.6253 | 41 | 0
Central Coast | 2902 | 455 | 794.3162 | 611 | 885.3264 | 38 | 0.00015931 | 3.1937 | 2.8391 | 23.0686 | 251.3579 | 1.6933 | 1.6884 | 7.5013 | 1.0478 | 0.00045464 | 0.00031578 | 0.74468 | 0.8972 | {7395FFA4-03E8-4D80-A8FA-546880E8DDC7} | 82841102 | BIG BASIN 1102 | 76752 | 37.1535 | -122.1612 | BIG BASIN 110276752 | 76 | 169 | 11898.3747 | 4328.6941 | 7569.6806 | 4328.6941 | 7569.6806 | 0.012 | 0.0060538 | 1.7457 | 16.0789 | 1091 | 0.017276 | 1792 | 0 | 0 | 2.6897 | 771 | 0
Bay Area | 1683 | 1045 | 2102.2775 | 2683 | 3015.3247 | 241 | 2.9225e-05 | 21.9422 | 1.3412 | 87.7827 | 419.4893 | 1.5107 | 1.2652 | 50.129 | 1.0523 | 0.00045324 | 3.4109e-05 | 0.38949 | 0.6972 | {196D5A62-8277-4556-8937-1330E86D299E} | 24101103 | HALF MOON BAY 1103 | H80 | 37.3302 | -122.375 | HALF MOON BAY 1103H80 | 245 | 246 | 51130.2847 | 31887.8354 | 19242.4494 | 31887.8354 | 19242.4494 | 0.0082203 | 0.0070433 | 2.0117 | 11.1328 | 2412 | 0.10923 | 1793 | 0 | 0 | 19.8142 | 2218 | 0
Central Coast | 8479 | 57 | 86.0566 | 154 | 135.1506 | 24 | 2.0556e-05 | 22.8253 | 0.70679 | 165.5707 | 1074.7475 | 3.3312 | 0.61173 | 147.3656 | 1.1949 | 0.00045118 | 1.9276e-05 | 0.37013 | 0.63675 | {5AD0F47A-1149-4BBD-8A9C-C835B4E34DD9} | 182941102 | OTTER 1102 | 2012 | 36.3314 | -121.8829 | OTTER 11022012 | 73 | 21 | 16686.3654 | 16177.0749 | 509.2905 | 14639.7556 | 462.2856 | 0.00046262 | 0.00049334 | 1.5098 | 6.4167 | 2626 | 0.010828 | 1794 | 0 | 0 | 9.0967 | 2468 | 0
Central Valley | 5093 | 187 | 266.4217 | 729 | 487.0694 | 153 | 1.2994e-05 | 43.9333 | 3.5321 | 530.9316 | 3835.0041 | 21.4606 | 4.1433 | 488.3268 | 1.506 | 0.00045007 | 3.309e-05 | 0.25652 | 0.54699 | {D40D6BB9-1863-4357-9803-EF56709C4086} | 254601103 | SAND CREEK 1103 | 7110 | 36.6347 | -118.9966 | SAND CREEK 11037110 | 159 | 236 | 42989.5878 | 29837.817 | 13151.7708 | 29837.817 | 13151.7708 | 0.0050628 | 0.0019881 | 1.4247 | 4.7647 | 2424 | 0.068861 | 1795 | 0 | 0 | 18.5404 | 1929 | 0
Bay Area | 994 | 142 | 381.3298 | 809 | 767.519 | 107 | 3.5385e-05 | 10.9489 | 0.21221 | 5.1284 | 18.0105 | 0.006986 | 0.35315 | 16.1353 | 1.1243 | 0.00045418 | 2.3504e-05 | 0.17553 | 0.49683 | {3ECE28A7-9E9D-4AFE-8619-84A42C55B001} | 14091106 | CASTRO VALLEY 1106 | MR337 | 37.7052 | -122.0623 | CASTRO VALLEY 1106MR337 | 453 | 2862 | 149629.9495 | 30443.3196 | 119186.6299 | 13193.9222 | 26359.1951 | 0.0025149 | 0.0037862 | 2.6854 | 7.5607 | 2556 | 0.048598 | 1796 | 0 | 0 | 8.1983 | 2707 | 0
Central Coast | 994 | 7 | 11.2947 | 8 | 11.9744 | 1 | 3.065e-05 | 0.066432 |  |  |  |  | 0 | 0 | 0 | 2.0361e-06 | 3.065e-05 | 0.875 | 0.94323 | {3ECE28A7-9E9D-4AFE-8619-84A42C55B001} | 14091106 | CASTRO VALLEY 1106 | MR337 | 37.7052 | -122.0623 | CASTRO VALLEY 1106MR337 | 453 | 2862 | 149629.9495 | 30443.3196 | 119186.6299 | 13193.9222 | 26359.1951 | 3.065e-05 | 3.065e-05 | 1.6135 | 8 | 2461 | 2.0361e-06 | 1796 | 0 | 0 | 8.1983 | 2232 | 0
North Coast | 2359 | 108 | 171.729 | 362 | 306.7022 | 35 | 0.00015493 | 4.1368 | 5.7688 | 8.6921 | 47.0091 | 0.79908 | 0.4444 | 13.1411 | 1.3547 | 0.00044463 | 0.00054196 | 0.29834 | 0.55992 | {F17BD51F-053C-4103-8B04-3625671BC676} | 42811113 | MONTE RIO 1113 | 477 | 38.4925 | -123.0081 | MONTE RIO 1113477 | 36 | 372 | 19550.9416 | 2831.9084 | 16719.0332 | 2831.9084 | 16719.0332 | 0.018969 | 0.0054225 | 1.5901 | 10.3429 | 747 | 0.015562 | 1797 | 0 | 0 | 1.7597 | 957 | 0
Central Coast | 7257 | 47 | 146.8105 | 241 | 247.4472 | 54 | 1.5293e-05 | 29.9703 | 0.621 | 125.6164 | 478.9768 | 0.91178 | 4.3862 | 71.6575 | 1.0777 | 0.00044462 | 1.2703e-05 | 0.19502 | 0.5933 | {B5391BD5-06CA-49EB-98DD-175A1FD20C36} | 182731102 | RESERVATION ROAD 1102 | 3030 | 36.5854 | -121.6002 | RESERVATION ROAD 11023030 | 212 | 200 | 54764.5126 | 41722.8305 | 13041.6821 | 10130.7204 | 7964.3819 | 0.00068597 | 0.0008258 | 3.1236 | 4.463 | 2752 | 0.024009 | 1798 | 0 | 0 | 6.2949 | 2051 | 0
Central Coast | 7625 | 22 | 81.6102 | 114 | 125.1227 | 19 | 1.9936e-05 | 23.0651 | 2.3631 | 746.6154 | 4746.2255 | 29.6027 | 1.6517 | 93.2763 | 0.91488 | 0.00044296 | 2.3425e-05 | 0.19298 | 0.65224 | {07DF4B2B-054C-4E25-84AF-DE6FF88C6FF3} | 183071101 | PERRY 1101 | W26 | 35.5714 | -121.0553 | PERRY 1101W26 | 31 | 17 | 7908.9573 | 4390.419 | 3518.5384 | 4390.419 | 3518.5384 | 0.00044507 | 0.00037879 | 3.7096 | 6 | 2559 | 0.0084163 | 1799 | 0 | 0 | 2.7281 | 796 | 0
Bay Area | 7613 | 18 | 39.5949 | 40 | 50.6288 | 9 | 3.3395e-05 | 8.7835 | 0.0099915 | 38.0006 | 141.9201 | 1.8719e-06 | 1.3938 | 97.6212 | 1.0612 | 0.00043887 | 1.6132e-05 | 0.45 | 0.78206 | {412508C2-76EC-400C-8C7E-53EB1141C78F} | 13801105 | MORAGA 1105 | 31512 | 37.8264 | -122.1299 | MORAGA 110531512 | 121 | 148 | 18958.6375 | 7423.6865 | 11534.9511 | 2816.3842 | 5664.3107 | 0.00014519 | 0.00030056 | 2.1997 | 4.4444 | 2682 | 0.0039498 | 1800 | 0 | 0 | 1.75 | 2850 | 0
Sierra | 2187 | 25 | 34.8945 | 194 | 106.5299 | 50 | 1.4445e-05 | 30.0393 | 6.0258 | 36.4988 | 298.0811 | 2.4222 | 0.27403 | 11.9893 | 1.062 | 0.00043641 | 4.4042e-05 | 0.12887 | 0.32756 | {4869E28B-32E6-4BF0-B134-B967D290269A} | 152762101 | EL DORADO PH 2101 | 36764 | 38.7871 | -120.2059 | EL DORADO PH 210136764 | 74 | 290 | 15530.3089 | 7038.7814 | 8491.5275 | 4920.5157 | 3574.7541 | 0.0022021 | 0.00072223 | 1.3958 | 3.88 | 2289 | 0.021821 | 1801 | 0 | 0 | 3.0575 | 179 | 0
Central Valley | 7758 | 401 | 584.0668 | 954 | 841.1464 | 78 | 5.9895e-05 | 7.3791 | 66.8302 | 649.124 | 11909.9494 | 2016.2791 | 2.1232 | 23.2938 | 1.1291 | 0.00043309 | 0.0016407 | 0.42034 | 0.69437 | {EBD937A8-0F05-49AA-848E-8FB362E60B61} | 162821701 | STANISLAUS 1701 | 7144 | 38.1744 | -120.3835 | STANISLAUS 17017144 | 96 | 140 | 15763.8748 | 7457.9017 | 8305.973 | 7457.9017 | 8305.973 | 0.12797 | 0.0046718 | 1.4565 | 12.2308 | 218 | 0.033781 | 1802 | 0 | 0 | 4.6341 | 1528 | 0
Central Valley | 5891 | 446 | 584.4199 | 1126 | 891.2278 | 213 | 5.9563e-05 | 11.4346 | 2.0894 | 73.0313 | 455.2058 | 3.4952 | 2.9368 | 54.7009 | 1.1653 | 0.00042761 | 7.6506e-05 | 0.39609 | 0.65575 | {31F34B0C-04AD-46C5-88A1-857D16F62C5A} | 162211101 | CALAVERAS CEMENT 1101 | 80930 | 38.1945 | -120.5851 | CALAVERAS CEMENT 110180930 | 256 | 228 | 46398.7045 | 29611.6951 | 16787.0094 | 29611.6951 | 16787.0094 | 0.016296 | 0.012687 | 1.3104 | 5.2864 | 2006 | 0.091082 | 1803 | 0 | 0 | 18.3998 | 2791 | 0
Central Coast | 6506 | 52 | 115.5904 | 277 | 252.9297 | 29 | 0.00018213 | 3.3465 | 2.3298 | 21.7158 | 112.0647 | 0.4221 | 1.323 | 29.5181 | 1.0298 | 0.00042521 | 0.00027938 | 0.18773 | 0.45701 | {8C44BEAB-509E-4818-A7FB-FBD552205E02} | 83622105 | CAMP EVERS 2105 | 5188 | 37.0759 | -122.0571 | CAMP EVERS 21055188 | 26 | 23 | 5146.9112 | 3191.7712 | 1955.14 | 3191.7712 | 1955.14 | 0.008102 | 0.0052819 | 2.2229 | 9.5517 | 1179 | 0.012331 | 1804 | 0 | 0 | 1.9833 | 1363 | 0
Bay Area | 8447 | 155 | 334.5998 | 1849 | 1381.6378 | 126 | 4.7462e-05 | 8.7859 | 1.3122 | 27.4336 | 120.4912 | 0.24684 | 1.3801 | 96.6942 | 1.0942 | 0.00042334 | 5.9804e-05 | 0.083829 | 0.24218 | {DB5E4E66-9EE6-4B14-84A9-0971764E1D9E} | 14091106 | CASTRO VALLEY 1106 | 8971 | 37.7114 | -122.0551 | CASTRO VALLEY 11068971 | 94 | 93 | 24595.7152 | 12736.098 | 11859.6172 | 12641.384 | 11769.5658 | 0.0075353 | 0.0059802 | 2.1587 | 14.6746 | 2143 | 0.053341 | 1805 | 0 | 0 | 7.855 | 2727 | 0
North Coast | 3122 | 192 | 386.4223 | 295 | 433.9106 | 57 | 7.6964e-05 | 8.0598 | 11.4621 | 230.3539 | 3665.2426 | 563.0363 | 1.919 | 14.1817 | 1.0222 | 0.00042324 | 0.00052719 | 0.65085 | 0.89056 | {D3BC4C4A-6AD6-4D57-ADFE-ACA0E6607A3B} | 43311108 | KONOCTI 1108 | 950 | 38.954 | -122.7265 | KONOCTI 1108950 | 136 | 444 | 32675.6268 | 11930.8969 | 20744.7299 | 9061.9141 | 14659.3562 | 0.03005 | 0.0043869 | 2.0126 | 5.1754 | 763 | 0.024125 | 1806 | 0 | 0 | 5.6308 | 1231 | 0
Central Coast | 2458 | 801 | 1961.0452 | 2088 | 2686.1147 | 212 | 5.9795e-05 | 10.3866 | 1.8875 | 15.8102 | 45.8305 | 0.22683 | 1.8897 | 11.8376 | 1.0151 | 0.00042216 | 8.3788e-05 | 0.38362 | 0.73007 | {0A7E84D0-9946-4059-AC56-BD0EC9107E3A} | 83692104 | ROB ROY 2104 | 10714 | 36.9779 | -121.8666 | ROB ROY 210410714 | 361 | 392 | 58753.4704 | 31415.4862 | 27337.9842 | 22255.4392 | 14870.169 | 0.017763 | 0.012676 | 2.4482 | 9.8491 | 1960 | 0.089499 | 1807 | 0 | 0 | 13.8289 | 2133 | 0
North Coast | 3778 | 826 | 1680.4048 | 1188 | 1848.1732 | 120 | 0.00014928 | 2.441 | 3.6408 | 19.6119 | 67.6393 | 0.37368 | 0.32866 | 4.2451 | 1.136 | 0.0004212 | 0.00041055 | 0.69529 | 0.90922 | {C40FEC6C-4399-4FDE-8ABD-E729D917D61E} | 42761101 | FORT BRAGG A 1101 | 4698 | 39.4911 | -123.7844 | FORT BRAGG A 11014698 | 151 | 196 | 27822.1469 | 12907.3842 | 14914.7627 | 12907.3842 | 14914.7627 | 0.049266 | 0.017914 | 2.0344 | 9.9 | 927 | 0.050544 | 1808 | 0 | 0 | 8.0203 | 1587 | 0
Central Valley | 7960 | 228 | 311.17 | 741 | 540.1414 | 130 | 8.3241e-05 | 5.3703 | 12.6735 | 180.8387 | 1502.4924 | 41.7293 | 1.8544 | 32.4662 | 1.0962 | 0.00042095 | 0.0005524 | 0.30769 | 0.57609 | {0F46298C-BD7C-494E-910E-FE65C6C90770} | 163751101 | PINE GROVE 1101 | 94936 | 38.3851 | -120.6921 | PINE GROVE 110194936 | 114 | 78 | 21129.1813 | 14913.8447 | 6215.3367 | 14913.8447 | 6215.3367 | 0.071812 | 0.010821 | 1.3648 | 5.7 | 732 | 0.054724 | 1809 | 0 | 0 | 9.267 | 437 | 0
Central Valley | 7881 | 47 | 64.4398 | 163 | 127.774 | 48 | 3.3026e-05 | 12.5369 | 11.2516 | 607.7303 | 5132.6676 | 82.121 | 3.6348 | 189.0835 | 1.3105 | 0.0004203 | 0.00020046 | 0.28834 | 0.50433 | {A8F5C818-FC4E-4829-9378-1203403CDD9C} | 252192105 | BEAR VALLEY 2105 | 4609 | 37.713 | -120.0988 | BEAR VALLEY 21054609 | 49 | 52 | 12030.0497 | 7321.9227 | 4708.127 | 7321.9227 | 4708.127 | 0.0096222 | 0.0015852 | 1.3711 | 3.3958 | 1410 | 0.020174 | 1810 | 0 | 0 | 4.5496 | 1621 | 0
Bay Area | 6526 | 667 | 1160.1255 | 1891 | 1855.7979 | 120 | 4.7963e-05 | 10.7736 | 2.4274 | 20.8341 | 103.893 | 0.90775 | 1.2526 | 18.3939 | 1.4112 | 0.00042021 | 8.5683e-05 | 0.35272 | 0.62514 | {67D16658-7393-469A-A583-1CF4002F525A} | 24101103 | HALF MOON BAY 1103 | 695411 | 37.3225 | -122.2781 | HALF MOON BAY 1103695411 | 167 | 478 | 33127.3569 | 13109.0272 | 20018.3297 | 13109.0272 | 20018.3297 | 0.010282 | 0.0057556 | 1.7393 | 15.7583 | 1940 | 0.050425 | 1811 | 0 | 0 | 8.1456 | 2440 | 0
Central Valley | 7052 | 13 | 16.0906 | 50 | 32.9993 | 9 | 7.351e-05 | 5.3704 | 0.00040865 | 0.006007 | 0.026768 | 4.0498e-07 | 0.58137 | 19.5593 | 1.0074 | 0.00041908 | 4.8407e-05 | 0.26 | 0.48761 | {ECC5358A-3849-4B2A-9964-68FBF1B8D64E} | 254452102 | MARIPOSA 2102 | 594143 | 37.4858 | -119.9694 | MARIPOSA 2102594143 | 179 | 430 | 20453.4883 | 6649.2174 | 13804.2709 | 751.6885 | 1440.7724 | 0.00043567 | 0.00066159 | 1.2377 | 5.5556 | 2242 | 0.0037717 | 1812 | 0 | 0 | 0.46708 | 2547 | 0
Central Valley | 3649 | 149 | 232.651 | 447 | 368.8398 | 41 | 0.00011587 | 4.1307 | 3.2957 | 45.6855 | 476.7125 | 5.3137 | 1.333 | 18.4979 | 1.0075 | 0.00041755 | 0.00024596 | 0.33333 | 0.63076 | {1330A2A7-6F05-480E-914F-CD520FD996F9} | 163751101 | PINE GROVE 1101 | 52088 | 38.3994 | -120.7339 | PINE GROVE 110152088 | 58 | 60 | 6713.6706 | 4068.7441 | 2644.9265 | 4068.7441 | 2644.9265 | 0.010084 | 0.0047507 | 1.5614 | 10.9024 | 1261 | 0.017119 | 1813 | 0 | 0 | 2.5282 | 1755 | 0
North Valley | 8802 | 7 | 12.903 | 57 | 34.6669 | 14 | 2.6593e-05 | 11.5269 | 0.63101 | 3262.9122 | 48629.4117 | 40.1702 | 0.2402 | 548.4478 | 1.5612 | 0.00041583 | 2.2435e-05 | 0.12281 | 0.3722 | {D4D9BD9F-69B8-49BE-A9F7-A13A4AD2C53C} | 103381101 | FRENCH GULCH 1101 | 1892 | 40.7017 | -122.6404 | FRENCH GULCH 11011892 | 13 | 4 | 4783.858 | 4073.3832 | 710.4748 | 4073.3832 | 710.4748 | 0.00031409 | 0.0003723 | 1.8433 | 4.0714 | 2574 | 0.0058216 | 1814 | 0 | 0 | 2.5311 | 2090 | 0
North Valley | 1120 | 384 | 517.2876 | 678 | 674.4329 | 60 | 0.00016185 | 2.0479 | 9.3927 | 17.8386 | 55.0544 | 1.3166 | 0.34148 | 0.92711 | 0.98477 | 0.00041564 | 0.0010309 | 0.56637 | 0.767 | {4E875C07-9BF0-416D-8352-B1380CD2F62E} | 102831105 | PARADISE 1105 | circuit_breaker | 39.7606 | -121.6188 | PARADISE 1105circuit_breaker | 539 | 346 | 47148.7335 | 29169.3143 | 17979.4192 | 19516.665 | 12961.3741 | 0.061852 | 0.0097108 | 1.3471 | 11.3 | 394 | 0.024939 | 1815 | 0 | 0 | 12.1271 | 4 | 0
North Coast | 7770 | 52 | 77.3116 | 92 | 100.7088 | 8 | 0.00015283 | 3.0386 | 6.7613 | 41.0975 | 432.7008 | 8.7561 | 2.0158 | 5.1578 | 1.0025 | 0.00041158 | 0.00044634 | 0.56522 | 0.76767 | {4A44046C-0EA0-4681-BB3C-B702268C5A42} | 42091102 | MIRABEL 1102 | 1139 | 38.5091 | -122.9195 | MIRABEL 11021139 | 56 | 183 | 11826.5043 | 2923.0188 | 8903.4855 | 2923.0188 | 8903.4855 | 0.0035707 | 0.0012226 | 1.4868 | 11.5 | 868 | 0.0032926 | 1816 | 0 | 0 | 1.8163 | 2250 | 0
Bay Area | 1341 | 95 | 336.5798 | 173 | 366.235 | 22 | 2.0391e-05 | 18.6972 | 0.84526 | 60.3297 | 222.3738 | 0.42591 | 1.1308 | 50.3703 | 1.0601 | 0.00040811 | 1.7985e-05 | 0.54913 | 0.91903 | {C9FA3CBF-AF0B-40A6-8062-0EE0474AC48A} | 24101103 | HALF MOON BAY 1103 | 6014 | 37.2511 | -122.3872 | HALF MOON BAY 11036014 | 145 | 141 | 25975.7545 | 19926.5393 | 6049.2152 | 6646.3728 | 612.6365 | 0.00039567 | 0.00044861 | 3.5429 | 7.8636 | 2652 | 0.0089784 | 1817 | 0 | 0 | 4.1299 | 2874 | 0
Sierra | 5922 | 206 | 301.9075 | 644 | 508.3716 | 58 | 9.7456e-05 | 3.7555 | 3.794 | 10.7732 | 53.1593 | 0.45666 | 0.67007 | 6.1453 | 0.98871 | 0.00040762 | 0.00023758 | 0.31988 | 0.59387 | {E1779AD2-4579-4092-9EC8-FEE4F5C13371} | 152481105 | BRUNSWICK 1105 | circuit_breaker | 39.2311 | -121.0351 | BRUNSWICK 1105circuit_breaker | 230 | 334 | 28391.3995 | 11223.4618 | 17167.9378 | 10665.1471 | 17167.9378 | 0.01378 | 0.0056524 | 1.4656 | 11.1034 | 1285 | 0.023642 | 1818 | 0 | 0 | 6.627 | 198 | 0
Central Coast | 6997 | 420 | 687.8454 | 998 | 990.8607 | 78 | 4.8109e-05 | 8.6046 | 1.4018 | 96.4673 | 1787.9501 | 16.9578 | 0.8455 | 34.7407 | 1.2269 | 0.00040691 | 5.6966e-05 | 0.42084 | 0.69419 | {E731F6BE-8220-43FF-B403-4FCE65138051} | 83371107 | SARATOGA 1107 | 167792 | 37.2482 | -122.0709 | SARATOGA 1107167792 | 64 | 34 | 8786.8725 | 7328.1795 | 1458.693 | 7328.1795 | 1458.693 | 0.0044433 | 0.0037525 | 1.6377 | 12.7949 | 2175 | 0.031739 | 1819 | 0 | 0 | 4.5535 | 2269 | 0
Bay Area | 9083 | 311 | 920.5396 | 423 | 966.797 | 64 | 3.5682e-05 | 12.9288 | 5.1104 | 153.0913 | 603.7132 | 11.6773 | 1.1821 | 51.6275 | 1.0715 | 0.0004058 | 0.00010985 | 0.73522 | 0.95215 | {841D987A-954B-4FC0-9C79-A3D82BBD4123} | 24101103 | HALF MOON BAY 1103 | 6065 | 37.4506 | -122.4288 | HALF MOON BAY 11036065 | 67 | 55 | 16311.777 | 11019.2698 | 5292.5072 | 9622.0817 | 5036.833 | 0.0070306 | 0.0022836 | 2.9599 | 6.6094 | 1803 | 0.025971 | 1820 | 0 | 0 | 5.9789 | 2699 | 0
Central Coast | 3024 | 0 | 0 | 2 | 0.91147 | 1 | 1.5547e-05 | 26.0834 | 0.00079184 | 0.39608 | 2.4717 | 0.019372 | 1.6549 | 400.5361 | 1.1394 | 0.00040553 | 1.2311e-08 | 0 | 0 | {C8B3CC69-B9EC-4FE8-B218-4BFA09031AD1} | 253671103 | PANOCHE 1103 | 4016 | 36.6026 | -120.839 | PANOCHE 11034016 | 69 | 44 | 22822.0385 | 20623.7001 | 2198.3385 | 3776.8409 | 958.0787 | 1.2311e-08 | 1.5547e-05 |  | 2 | 2886 | 0.00040553 | 1821 | 0 | 0 | 2.3468 | 982 | 0
Central Valley | 6045 | 5 | 9.9158 | 46 | 20.2323 | 23 | 2.8712e-05 | 20.1622 | 6.1717 | 602.1129 | 2544.4618 | 29.2507 | 3.2469 | 179.8757 | 1.2159 | 0.00040541 | 0.00011137 | 0.1087 | 0.4901 | {ABA7C635-5CFB-4061-A207-A842A0C4AD30} | 163781701 | PEORIA 1701 | 76030 | 37.8992 | -120.4551 | PEORIA 170176030 | 69 | 51 | 11799.3536 | 9992.9255 | 1806.4282 | 8122.6361 | 1174.0528 | 0.0025615 | 0.00066039 | 1.9832 | 2 | 1792 | 0.0093245 | 1822 | 0 | 0 | 5.0472 | 2621 | 0
Central Coast | 329 | 299 | 942.845 | 659 | 1141.1855 | 89 | 2.7374e-05 | 23.9006 | 1.8612 | 91.7403 | 448.1856 | 0.61969 | 0.78846 | 99.7059 | 1.0945 | 0.00040509 | 4.8627e-05 | 0.45372 | 0.8262 | {A36DF7B8-003C-42F6-A33B-327B9F3DECA5} | 182771102 | CAMBRIA 1102 | circuit_breaker | 35.6002 | -121.115 | CAMBRIA 1102circuit_breaker | 251 | 488 | 57562.9767 | 37393.8508 | 20169.1259 | 25658.8486 | 6871.9207 | 0.0043278 | 0.0024363 | 3.1533 | 7.4045 | 2239 | 0.036053 | 1823 | 0 | 0 | 15.9437 | 1989 | 0
Bay Area | 6620 | 21 | 34.0179 | 325 | 178.1274 | 15 | 6.2453e-05 | 6.4677 | 0 | 0 | 0 | 0 | 0.18525 | 17.6422 | 1.0142 | 0.00040507 | 5.7564e-05 | 0.064615 | 0.19098 | {701C0938-AA90-48C8-9BEF-CBE33E0DD08B} | 42291101 | OLEMA 1101 | 1686 | 38.0428 | -122.787 | OLEMA 11011686 | 82 | 111 | 13309.6561 | 8105.6577 | 5203.9985 | 1962.0765 | 1309.4437 | 0.00086347 | 0.00093679 | 1.6199 | 21.6667 | 2160 | 0.0060761 | 1824 | 0 | 0 | 1.2192 | 2181 | 0
Bay Area | 6063 | 288 | 600.8778 | 1062 | 1002.9739 | 69 | 8.6685e-05 | 6.2911 | 2.7536 | 9.6683 | 35.5519 | 0.16045 | 0.72233 | 13.3204 | 1.3199 | 0.00040499 | 0.00017864 | 0.27119 | 0.5991 | {8C718E02-B293-4F3E-A85B-44B4CAD6C2F4} | 13801101 | MORAGA 1101 | 18216 | 37.8836 | -122.2009 | MORAGA 110118216 | 119 | 279 | 20848.5365 | 7868.0142 | 12980.5222 | 7868.0142 | 12980.5222 | 0.012326 | 0.0059813 | 2.0864 | 15.3913 | 1493 | 0.027944 | 1825 | 0 | 0 | 4.889 | 1118 | 0
Central Valley | 1009 | 259 | 395.8358 | 6033 | 2862.6304 | 278 | 4.3055e-05 | 8.8744 | 6.5727 | 15.9375 | 163.7091 | 2.4625 | 0.49262 | 3.6968 | 1.2618 | 0.00040456 | 0.00014926 | 0.042931 | 0.13828 | {11FD881F-3901-4F70-8CA9-73ABCE362AB7} | 163692102 | SALT SPRINGS 2102 | 3142 | 38.3018 | -120.277 | SALT SPRINGS 21023142 | 449 | 923 | 62767.5331 | 27128.7333 | 35638.7997 | 27128.7333 | 35638.7997 | 0.041495 | 0.011969 | 1.5283 | 21.7014 | 1596 | 0.11247 | 1826 | 0 | 0 | 16.857 | 932 | 0
North Valley | 1012 | 645 | 792.0839 | 2412 | 1554.9939 | 204 | 5.6594e-05 | 6.5921 | 15.7683 | 321.052 | 4331.5871 | 99.0831 | 1.3218 | 18.6745 | 1.0245 | 0.00040396 | 0.00050046 | 0.26741 | 0.50938 | {1E454211-6D5E-4E85-8098-0CF68E01A8DA} | 102541102 | VOLTA 1102 | 53130 | 40.4989 | -121.8385 | VOLTA 110253130 | 264 | 242 | 33320.65 | 22286.621 | 11034.029 | 22286.621 | 11034.029 | 0.10209 | 0.011545 | 1.228 | 11.8235 | 784 | 0.082407 | 1827 | 0 | 0 | 13.8483 | 1402 | 0
North Coast | 739 | 1240 | 2211.4567 | 1424 | 2296.7249 | 94 | 0.00010087 | 3.1006 | 4.3374 | 29.0705 | 171.6263 | 1.466 | 0.47472 | 7.23 | 1.0046 | 0.00040385 | 0.00030956 | 0.87079 | 0.96287 | {A14F3892-7C26-42AD-BDDE-906FEDC3E74D} | 42841112 | GUALALA 1112 | 662 | 38.7751 | -123.5383 | GUALALA 1112662 | 193 | 239 | 25535.677 | 13650.0311 | 11885.6459 | 8946.2004 | 8389.2888 | 0.029099 | 0.0094819 | 1.7834 | 15.1489 | 1100 | 0.037962 | 1828 | 0 | 0 | 5.5589 | 2594 | 0
Sierra | 1625 | 233 | 349.3364 | 773 | 598.4461 | 79 | 0.00015672 | 3.3777 | 7.2812 | 16.3428 | 153.8073 | 4.0717 | 1.3249 | 14.4289 | 0.95161 | 0.00040369 | 0.00063263 | 0.30142 | 0.58374 | {7B1613F1-BF60-43A3-B696-FC7878E4336D} | 152481107 | BRUNSWICK 1107 | 50010 | 39.2219 | -121.0498 | BRUNSWICK 110750010 | 296 | 943 | 51099.4288 | 14946.7962 | 36152.6326 | 9532.5902 | 19409.1143 | 0.049978 | 0.012381 | 1.4993 | 9.7848 | 635 | 0.031892 | 1829 | 0 | 0 | 5.9233 | 1045 | 0
North Coast | 6126 | 3024 | 5250.4539 | 3285 | 5371.9 | 247 | 9.4008e-05 | 3.8192 | 3.745 | 37.0204 | 184.3735 | 1.0005 | 0.39484 | 8.7881 | 1.0102 | 0.00040099 | 0.00020838 | 0.92055 | 0.97739 | {FD400AC6-30E3-4FB9-965E-48825707A861} | 42841111 | GUALALA 1111 | 35562 | 38.7868 | -123.5217 | GUALALA 111135562 | 240 | 336 | 42565.7157 | 22847.3348 | 19718.3809 | 22847.3348 | 19718.3809 | 0.05147 | 0.02322 | 1.7363 | 13.2996 | 1385 | 0.099045 | 1830 | 0 | 0 | 14.1967 | 727 | 0
North Coast | 674 | 446 | 755.9786 | 1086 | 1098.1917 | 88 | 9.0502e-05 | 4.6567 | 13.4188 | 25.0118 | 221.1511 | 8.8569 | 1.254 | 4.9836 | 1.1754 | 0.00040017 | 0.00069699 | 0.41068 | 0.68838 | {8C8983C8-884C-4E70-BBB6-36F59CD80D78} | 42811113 | MONTE RIO 1113 | 524 | 38.5037 | -122.9936 | MONTE RIO 1113524 | 159 | 890 | 41818.1192 | 10034.2173 | 31783.9019 | 10034.2173 | 31783.9019 | 0.061335 | 0.0079642 | 1.695 | 12.3409 | 568 | 0.035215 | 1831 | 0 | 0 | 6.235 | 1515 | 0
Central Valley | 8537 | 16 | 24.2053 | 248 | 125.3578 | 14 | 3.5169e-05 | 13.6551 | 7.8287 | 7.5988 | 16.5948 | 0.20034 | 0.43521 | 6.057 | 1.0032 | 0.00039667 | 0.00014862 | 0.064516 | 0.19309 | {99944090-D986-4C85-A635-DE641A326023} | 163692102 | SALT SPRINGS 2102 | L485 | 38.2974 | -120.2742 | SALT SPRINGS 2102L485 | 24 | 52 | 3455.5812 | 1339.4234 | 2116.1578 | 1339.4234 | 2116.1578 | 0.0020806 | 0.00049236 | 1.5128 | 17.7143 | 1598 | 0.0055534 | 1832 | 0 | 0 | 0.83228 | 1812 | 0
Central Coast | 5662 | 177 | 386.0115 | 342 | 472.3296 | 28 | 3.6995e-05 | 11.9605 | 1.3293 | 96.6512 | 368.8746 | 1.0896 | 0.215 | 22.1155 | 1.1164 | 0.00039666 | 4.2778e-05 | 0.51754 | 0.81725 | {EF958110-BB67-48F0-BCC0-A7C84F7DFFDE} | 82931101 | POINT MORETTI 1101 | 5076 | 37.0321 | -122.1892 | POINT MORETTI 11015076 | 93 | 55 | 17840.2787 | 14517.5787 | 3322.7 | 10957.7607 | 2768.3393 | 0.0011978 | 0.0010359 | 2.1809 | 12.2143 | 2301 | 0.011107 | 1833 | 0 | 0 | 6.8088 | 737 | 0
Central Coast | 1414 | 0 | 0 | 102 | 80.5708 | 2 | 6.3304e-05 | 35.7368 |  |  |  |  | 0.84403 | 34.5341 | 1.0111 | 0.0021111 | 6.3304e-05 | 0 | 0 | {56C84CD8-CFAF-4218-882A-B93134A396EB} | 24131102 | MENLO 1102 | 8952 | 37.3512 | -122.1983 | MENLO 11028952 | 158 | 299 | 28965.322 | 10925.0954 | 18040.2265 | 10925.0954 | 18040.2265 | 0.00012661 | 0.00012661 |  | 51 | 2109 | 0.0042223 | 1834 | 0 | 0 | 6.7885 | 739 | 0
Bay Area | 1414 | 644 | 1048.4891 | 1683 | 1674.6967 | 115 | 5.5045e-05 | 6.4803 | 4.1216 | 37.1579 | 387.336 | 6.2557 | 1.7891 | 21.8612 | 1.0813 | 0.00036653 | 0.00013894 | 0.38265 | 0.62608 | {56C84CD8-CFAF-4218-882A-B93134A396EB} | 24131102 | MENLO 1102 | 8952 | 37.3512 | -122.1983 | MENLO 11028952 | 158 | 299 | 28965.322 | 10925.0954 | 18040.2265 | 10925.0954 | 18040.2265 | 0.015979 | 0.0063302 | 1.6281 | 14.6348 | 1635 | 0.042151 | 1834 | 0 | 0 | 6.7885 | 1308 | 0
Sierra | 3147 | 1566 | 1877.0411 | 3314 | 2808.2004 | 276 | 8.0412e-05 | 4.3721 | 18.2232 | 175.2592 | 2227.8799 | 249.5396 | 2.2036 | 22.5417 | 1.198 | 0.00039005 | 0.00072455 | 0.47254 | 0.66841 | {0FE524F2-DA0B-43E6-AE33-7B106122C864} | 152431101 | SHADY GLEN 1101 | 51696 | 39.1003 | -120.9524 | SHADY GLEN 110151696 | 435 | 616 | 69280.468 | 33124.3103 | 36156.1577 | 28237.56 | 27907.503 | 0.19998 | 0.022194 | 1.1986 | 12.0072 | 552 | 0.10765 | 1835 | 0 | 0 | 17.546 | 790 | 0
Central Coast | 8990 | 33 | 84.5544 | 196 | 179.6766 | 30 | 3.0186e-05 | 16.927 | 1.4942 | 603.5075 | 2113.8128 | 5.7684 | 0.81047 | 258.65 | 1.408 | 0.00038961 | 3.3727e-05 | 0.16837 | 0.47059 | {867AA1B1-4446-48B6-9D80-8E314456C23F} | 182971101 | PURISIMA 1101 | Y44 | 34.7193 | -120.4307 | PURISIMA 1101Y44 | 56 | 24 | 22910.8277 | 18642.1512 | 4268.6765 | 16580.432 | 4115.6873 | 0.0010118 | 0.00090558 | 2.5623 | 6.5333 | 2416 | 0.011688 | 1836 | 0 | 0 | 10.3026 | 2295 | 0
Bay Area | 1464 | 25 | 47.3355 | 46 | 59.7137 | 6 | 2.4894e-05 | 19.9082 | 0.098474 | 0.15557 | 0.093372 | 0.00085744 | 7.5914 | 30.5196 | 1.0265 | 0.00038567 | 1.2967e-05 | 0.54348 | 0.79271 | {772B9C3A-4112-4E6C-8E48-73C0CBC8A027} | 14232107 | SAN RAMON 2107 | circuit_breaker | 37.745 | -121.9376 | SAN RAMON 2107circuit_breaker | 238 | 1155 | 65956.1053 | 14479.3454 | 51476.7599 | 477.5582 | 541.0621 | 7.7801e-05 | 0.00014936 | 1.8934 | 7.6667 | 2743 | 0.002314 | 1837 | 0 | 0 | 0.29674 | 2322 | 0
Central Coast | 5960 | 1026 | 1915.5378 | 2091 | 2545.9768 | 116 | 0.00020468 | 1.9115 | 4.0159 | 14.3133 | 67.6873 | 0.86628 | 0.24962 | 4.8332 | 1.008 | 0.00038475 | 0.00058423 | 0.49067 | 0.75238 | {EE077F7F-8175-4265-8512-03731CF3E11C} | 83622105 | CAMP EVERS 2105 | circuit_breaker | 37.0419 | -122.0251 | CAMP EVERS 2105circuit_breaker | 237 | 353 | 35304.7095 | 16540.5741 | 18764.1354 | 12905.269 | 13680.8998 | 0.067771 | 0.023743 | 1.867 | 18.0259 | 689 | 0.044631 | 1838 | 0 | 0 | 8.019 | 1491 | 0
North Valley | 7522 | 106 | 124.7773 | 226 | 181.2618 | 48 | 7.7106e-05 | 5.0237 | 1.3168 | 772.2436 | 12980.9113 | 30.1373 | 0.14677 | 38.6569 | 1.3279 | 0.00038379 | 8.227e-05 | 0.46903 | 0.68838 | {B21A40B5-551B-4708-A4A5-34576C3781E9} | 101321101 | PIT NO 5 1101 | 1658 | 40.9922 | -121.9705 | PIT NO 5 11011658 | 30 | 13 | 8090.3108 | 7306.3402 | 783.9705 | 7306.3402 | 783.9705 | 0.0039489 | 0.0037011 | 1.1771 | 4.7083 | 1969 | 0.018422 | 1839 | 0 | 0 | 4.5399 | 2506 | 0
North Coast | 4442 | 95 | 155.3847 | 207 | 225.3341 | 26 | 6.4328e-05 | 6.4923 | 9.8824 | 33.9564 | 161.373 | 7.524 | 1.1186 | 22.5835 | 0.90521 | 0.00038308 | 0.00033129 | 0.45894 | 0.68957 | {F102360D-42FF-446F-88B4-F431C95B2DC4} | 43321101 | RINCON 1101 | circuit_breaker | 38.4899 | -122.6659 | RINCON 1101circuit_breaker | 152 | 340 | 23865.1212 | 7751.5983 | 16113.5229 | 2521.3047 | 4573.7389 | 0.0086135 | 0.0016725 | 1.6356 | 7.9615 | 1052 | 0.0099601 | 1840 | 0 | 0 | 1.5667 | 253 | 0
Central Valley | 8694 | 47 | 72.4821 | 77 | 89.213 | 14 | 1.8423e-05 | 23.4103 | 6.9382 | 870.2153 | 8732.1577 | 159.1852 | 3.821 | 308.4714 | 1.3707 | 0.000383 | 4.7518e-05 | 0.61039 | 0.81246 | {03B91929-B748-41B7-BED2-9D46A08F08B1} | 254061102 | DUNLAP 1102 | 39190 | 36.6873 | -119.02 | DUNLAP 110239190 | 23 | 24 | 3894.7605 | 2902.8014 | 991.9591 | 2902.8014 | 991.9591 | 0.00066525 | 0.00025792 | 1.5422 | 5.5 | 2257 | 0.005362 | 1841 | 0 | 0 | 1.8037 | 28 | 0
Central Valley | 8007 | 9 | 12.2273 | 135 | 66.9621 | 15 | 4.0066e-05 | 9.5564 | 6.6614 | 6.0352 | 16.9855 | 0.15686 | 0.056637 | 4.8135 | 2.336 | 0.00038262 | 0.00019292 | 0.066667 | 0.1826 | {5BC70572-47B3-4492-B9B0-A912C8860F45} | 163692102 | SALT SPRINGS 2102 | L7283 | 38.314 | -120.2557 | SALT SPRINGS 2102L7283 | 18 | 52 | 3175.3975 | 1066.8481 | 2108.5494 | 1066.8481 | 2108.5494 | 0.0028938 | 0.00060099 | 1.3586 | 9 | 1441 | 0.0057393 | 1842 | 0 | 0 | 0.66291 | 1905 | 0
Central Valley | 869 | 91 | 145.2598 | 2441 | 1121.5757 | 126 | 4.0185e-05 | 9.8776 | 5.4171 | 7.6495 | 29.5679 | 0.28413 | 0.21602 | 2.9752 | 1.2097 | 0.00038218 | 0.00012008 | 0.03728 | 0.12951 | {62775B3C-DB61-48AD-B027-A91400EE7920} | 163692102 | SALT SPRINGS 2102 | 4796 | 38.3199 | -120.2524 | SALT SPRINGS 21024796 | 205 | 431 | 29124.6969 | 11537.3564 | 17587.3405 | 11537.3564 | 17587.3405 | 0.01513 | 0.0050633 | 1.5963 | 19.373 | 1748 | 0.048155 | 1843 | 0 | 0 | 7.169 | 1970 | 0
Bay Area | 6457 | 78 | 226.5693 | 341 | 373.0799 | 28 | 5.2877e-05 | 3.4648 | 0.15958 | 0.062952 | 0.0012345 | 6.7486e-07 | 0.6295 | 3.2095 | 0.90202 | 0.00037354 | 3.7798e-05 | 0.22874 | 0.60729 | {DC93F2BF-1FFD-4AAB-B042-E35ACAAAB3A8} | 42031125 | ALTO 1125 | 1158 | 37.8961 | -122.538 | ALTO 11251158 | 190 | 754 | 42633.3356 | 8797.5302 | 33835.8054 | 3766.7299 | 12002.4446 | 0.0010583 | 0.0014805 | 2.9047 | 12.1786 | 2364 | 0.010459 | 1844 | 0 | 0 | 2.3405 | 2020 | 0
Central Coast | 2757 | 1 | 1.2277 | 5 | 2.9196 | 3 | 1.1181e-05 | 36.0226 |  |  |  |  | 3.7869 | 950.3073 | 1.469 | 0.00037024 | 1.1181e-05 | 0.2 | 0.4205 | {2039711E-7AA5-4D64-B713-BB2955894DC0} | 82952107 | EDENVALE 2107 | XR336 | 37.2316 | -121.7616 | EDENVALE 2107XR336 | 395 | 357 | 61503.5557 | 47480.5961 | 14022.9597 | 2932.2246 | 65.4219 | 3.3542e-05 | 3.3542e-05 | 1.2277 | 1.6667 | 2773 | 0.0011107 | 1845 | 0 | 0 | 1.822 | 351 | 0
Central Coast | 1584 | 57 | 174.8937 | 282 | 296.7805 | 35 | 3.2486e-05 | 16.198 | 1.2893 | 107.9242 | 464.3218 | 2.5981 | 0.0017699 | 77.809 | 1.0749 | 0.00036949 | 5.8511e-05 | 0.20213 | 0.5893 | {961ADDB9-D321-4ADD-9D3F-D89CD78AE625} | 183101104 | CABRILLO 1104 | Y22 | 34.6455 | -120.4614 | CABRILLO 1104Y22 | 230 | 214 | 55283.4176 | 41421.5748 | 13861.8428 | 14759.1555 | 9689.5952 | 0.0020479 | 0.001137 | 3.0683 | 8.0571 | 2155 | 0.012932 | 1846 | 0 | 0 | 9.1709 | 320 | 0
Central Valley | 5418 | 522 | 809.1646 | 3371 | 2153.6016 | 331 | 9.1523e-05 | 4.6038 | 12.623 | 172.9113 | 1554.3815 | 58.7354 | 2.9082 | 49.2595 | 1.1392 | 0.00036763 | 0.00057822 | 0.15485 | 0.37573 | {467D6E51-4EB9-458F-952D-00686C463F1F} | 162161101 | ELECTRA 1101 | 61816 | 38.3634 | -120.6486 | ELECTRA 110161816 | 335 | 324 | 60561.0339 | 37900.7563 | 22660.2775 | 37900.7563 | 22660.2775 | 0.19139 | 0.030294 | 1.5501 | 10.1843 | 700 | 0.12168 | 1847 | 0 | 0 | 23.5504 | 843 | 0
Central Coast | 4155 | 656 | 1149.3825 | 1126 | 1406.6881 | 89 | 0.00016045 | 2.4674 | 4.0743 | 22.9666 | 141.9989 | 0.65589 | 0.13978 | 4.2396 | 1.2144 | 0.00036727 | 0.00036329 | 0.58259 | 0.81708 | {3F3C2221-BBAC-4E4F-9E04-666D69CECF1F} | 83622106 | CAMP EVERS 2106 | 5302 | 37.0438 | -122.0755 | CAMP EVERS 21065302 | 102 | 248 | 20903.8556 | 9619.5872 | 11284.2684 | 9619.5872 | 11284.2684 | 0.032333 | 0.01428 | 1.7521 | 12.6517 | 992 | 0.032687 | 1848 | 0 | 0 | 5.9773 | 44 | 0
North Coast | 6236 | 191 | 317.8358 | 298 | 375.6578 | 24 | 7.4761e-05 | 6.008 | 8.5024 | 16.7469 | 96.5988 | 1.5358 | 0.20736 | 7.7512 | 1.1684 | 0.00036702 | 0.00042644 | 0.64094 | 0.84608 | {DC5D373F-83D4-48BB-B919-0674685FB4AD} | 42811113 | MONTE RIO 1113 | 1313 | 38.504 | -122.9884 | MONTE RIO 11131313 | 26 | 162 | 8534.2879 | 1981.3722 | 6552.9157 | 1981.3722 | 6552.9157 | 0.010234 | 0.0017943 | 1.6641 | 12.4167 | 901 | 0.0088085 | 1849 | 0 | 0 | 1.2312 | 1844 | 0
North Coast | 2427 | 2294 | 3630.9951 | 3500 | 4147.3296 | 251 | 4.7411e-05 | 7.8312 | 3.5824 | 32.351 | 169.2129 | 0.84567 | 0.46614 | 4.952 | 1.0042 | 0.00036622 | 0.00010275 | 0.65543 | 0.8755 | {076F886F-3F6B-4035-B7B1-0BE70152A7F4} | 192431109 | HARRIS 1109 | 700 | 40.7805 | -124.1253 | HARRIS 1109700 | 560 | 926 | 96754.7407 | 47370.0595 | 49384.6813 | 23735.6051 | 25024.2724 | 0.025791 | 0.0119 | 1.5828 | 13.9442 | 1841 | 0.091921 | 1850 | 0 | 0 | 14.7486 | 68 | 0
Central Coast | 4885 | 5 | 7.6275 | 18 | 15.7741 | 5 | 3.3779e-05 | 9.6543 | 21.0657 | 186.7372 | 662.8054 | 23.7421 | 3.6686 | 22.3196 | 1.0018 | 0.00036615 | 0.00055901 | 0.27778 | 0.48354 | {1A2AEC20-7798-471E-990E-3BD9D80801FA} | 182541101 | ATASCADERO 1101 | A22 | 35.4741 | -120.6661 | ATASCADERO 1101A22 | 363 | 1253 | 86163.0987 | 21047.1239 | 65115.9748 | 209.5535 | 3172.162 | 0.002795 | 0.00016889 | 1.5255 | 3.6 | 725 | 0.0018308 | 1851 | 0 | 0 | 0.13021 | 946 | 0
Bay Area | 2271 | 123 | 253.2786 | 720 | 585.4927 | 73 | 8.1049e-05 | 4.9446 | 7.2022 | 16.9467 | 55.6115 | 0.60794 | 0.44995 | 9.9085 | 1.3935 | 0.00036573 | 0.0003559 | 0.17083 | 0.43259 | {372C45CD-D068-4E6E-9903-0ED38EA6950C} | 13801101 | MORAGA 1101 | 108540 | 37.8837 | -122.1987 | MORAGA 1101108540 | 71 | 158 | 14643.6529 | 7755.7349 | 6887.918 | 7755.7349 | 6887.918 | 0.025981 | 0.0059166 | 2.0592 | 9.863 | 1007 | 0.026699 | 1852 | 0 | 0 | 4.8192 | 1076 | 0
North Coast | 1845 | 2457 | 3954.098 | 2723 | 4073.8362 | 272 | 7.7197e-05 | 4.8817 | 0.84378 | 48.474 | 222.6376 | 0.2981 | 0.23569 | 13.5252 | 1.081 | 0.00036276 | 7.1405e-05 | 0.90231 | 0.97061 | {BF12DE8B-4E1C-4761-B900-F5DD3C822515} | 42761102 | FORT BRAGG A 1102 | 31304 | 39.415 | -123.7704 | FORT BRAGG A 110231304 | 153 | 128 | 43579.2277 | 34687.2851 | 8891.9427 | 34687.2851 | 8891.9427 | 0.019422 | 0.020998 | 1.6093 | 10.011 | 2043 | 0.09867 | 1853 | 0 | 0 | 21.5537 | 1039 | 0
Central Valley | 6153 | 207 | 287.9527 | 1262 | 792.3036 | 24 | 5.7271e-05 | 6.006 | 42.8303 | 34.1735 | 252.6777 | 14.8 | 0.019006 | 2.3295 | 1.3355 | 0.00036155 | 0.0011674 | 0.16403 | 0.36344 | {CA0E971D-5831-4DB9-9A57-0D7C43C8EF35} | 163661702 | MIWUK 1702 | S2247 | 38.0369 | -120.2384 | MIWUK 1702S2247 | 40 | 262 | 12915.5879 | 2394.0014 | 10521.5865 | 2394.0014 | 10521.5865 | 0.028018 | 0.0013745 | 1.3911 | 52.5833 | 336 | 0.0086771 | 1854 | 0 | 0 | 1.4876 | 1511 | 0
Sierra | 582 | 4174 | 5211.9057 | 7808 | 6974.7637 | 716 | 6.7135e-05 | 5.8442 | 102.9442 | 1051.7236 | 20230.8508 | 8792.3656 | 1.4663 | 26.1096 | 1.0818 | 0.00035578 | 0.0031309 | 0.53458 | 0.74725 | {CA5C38FD-CE12-4872-96AA-D926F4220C4F} | 152481102 | BRUNSWICK 1102 | 1010 | 39.2129 | -121.0129 | BRUNSWICK 11021010 | 740 | 635 | 115163.3937 | 70806.9227 | 44356.471 | 70806.9227 | 44356.471 | 2.2417 | 0.048069 | 1.2487 | 10.905 | 101 | 0.25474 | 1855 | 0 | 0 | 43.9974 | 2241 | 0
Central Valley | 3663 | 168 | 273.4634 | 491 | 415.3886 | 98 | 1.1929e-05 | 47.4586 | 2.155 | 103.0637 | 786.5032 | 2.969 | 2.8145 | 188.1208 | 1.3105 | 0.00035504 | 1.5089e-05 | 0.34216 | 0.65833 | {8FE2B2A5-53AD-4D02-8B28-25A33ED98DCB} | 252691104 | INDIAN FLAT 1104 | circuit_breaker | 37.6655 | -119.8416 | INDIAN FLAT 1104circuit_breaker | 155 | 267 | 30939.222 | 20602.0949 | 10337.1271 | 20602.0949 | 10337.1271 | 0.0014788 | 0.001169 | 1.6278 | 5.0102 | 2704 | 0.034794 | 1856 | 0 | 0 | 12.8015 | 2577 | 0
North Valley | 4948 | 4 | 4.6762 | 28 | 17.9888 | 9 | 2.7313e-05 | 8.0291 | 0.98098 | 0.66191 | 1.2347 | 0.0064475 | 0.59596 | 8.7022 | 0.55728 | 0.00035426 | 2.7758e-05 | 0.14286 | 0.25995 | {C4DDB13D-8C8F-4D3D-860D-833D982C6826} | 103311102 | BURNEY 1102 | 97318 | 40.8829 | -121.6643 | BURNEY 110297318 | 71 | 113 | 6858.8034 | 2272.8877 | 4585.9157 | 1004.5656 | 2282.2468 | 0.00024982 | 0.00024582 | 1.1691 | 3.1111 | 2493 | 0.0031884 | 1857 | 0 | 0 | 0.62421 | 1471 | 0
Central Valley | 5118 | 396 | 570.024 | 2083 | 1485.2847 | 96 | 7.2711e-05 | 5.5091 | 25.6325 | 160.8182 | 2117.9276 | 409.4321 | 0.91178 | 11.1212 | 1.3941 | 0.00035192 | 0.00076707 | 0.19011 | 0.38378 | {E3EB2F7C-142F-4854-915A-45E737E9415A} | 163351705 | CURTIS 1705 | 843 | 37.9988 | -120.2321 | CURTIS 1705843 | 153 | 405 | 28575.7276 | 10626.4913 | 17949.2363 | 10626.4913 | 17949.2363 | 0.073639 | 0.0069802 | 1.4395 | 21.6979 | 522 | 0.033784 | 1858 | 0 | 0 | 6.603 | 527 | 0
Central Valley | 1671 | 63 | 95.5141 | 385 | 226.7553 | 66 | 8.8848e-05 | 4.1814 | 31.049 | 304.048 | 1828.6556 | 103.9808 | 3.7225 | 116.0009 | 1.3135 | 0.00034883 | 0.0011069 | 0.16364 | 0.42122 | {2CE7DA92-EEC1-4680-BEC4-A1E05BA2B50C} | 162211101 | CALAVERAS CEMENT 1101 | 36880 | 38.2019 | -120.6895 | CALAVERAS CEMENT 110136880 | 149 | 248 | 28701.2955 | 13909.6582 | 14791.6373 | 9538.3272 | 7956.1837 | 0.073053 | 0.005864 | 1.5161 | 5.8333 | 359 | 0.023023 | 1859 | 0 | 0 | 5.9268 | 2537 | 0
Central Valley | 1564 | 51 | 71.4393 | 238 | 159.5648 | 40 | 4.4923e-05 | 6.6034 | 3.0759 | 16.022 | 106.224 | 0.32876 | 0.61692 | 8.5996 | 1.0034 | 0.00034655 | 9.3987e-05 | 0.21429 | 0.44771 | {1AD6607D-F312-473D-9241-E313EE11C5E3} | 252531101 | SAN JOAQUIN #3 1101 | 673480 | 37.2881 | -119.5197 | SAN JOAQUIN #3 1101673480 | 174 | 643 | 41250.8571 | 20465.7113 | 20785.1458 | 20465.7113 | 20785.1458 | 0.0037595 | 0.0017969 | 1.4008 | 5.95 | 1884 | 0.013862 | 1860 | 0 | 0 | 12.7168 | 2297 | 0
North Valley | 7916 | 57 | 80.5039 | 223 | 179.4362 | 47 | 3.0011e-05 | 11.1855 | 2.7176 | 20.2016 | 85.9309 | 0.16744 | 0.97691 | 36.2303 | 1.293 | 0.00034614 | 6.7026e-05 | 0.25561 | 0.44865 | {76D3EBDD-5C29-47DF-9912-445D8BE3DBA6} | 103311101 | BURNEY 1102 | 9042 | 40.8787 | -121.6574 | BURNEY 11029042 | 75 | 129 | 9729.0301 | 5080.7921 | 4648.238 | 5080.7921 | 4648.238 | 0.0031502 | 0.0014105 | 1.4123 | 4.7447 | 2078 | 0.016269 | 1861 | 0 | 0 | 3.1571 | 863 | 0
Central Coast | 3867 | 146 | 373.7153 | 307 | 462.2095 | 29 | 3.5193e-05 | 9.2001 | 1.3492 | 83.3026 | 341.2132 | 0.87124 | 0.81172 | 40.4796 | 1.0917 | 0.00034598 | 4.0216e-05 | 0.47557 | 0.80854 | {9CD1A9B9-F6CA-4FBA-A861-B1CC3280E49B} | 82931101 | POINT MORETTI 1101 | 12122 | 37.0664 | -122.2286 | POINT MORETTI 110112122 | 87 | 50 | 17133.8971 | 12806.7268 | 4327.1703 | 9019.8604 | 4267.5221 | 0.0011663 | 0.0010206 | 2.5597 | 10.5862 | 2337 | 0.010034 | 1862 | 0 | 0 | 5.6047 | 1988 | 0
Central Valley | 9051 | 24 | 38.1283 | 1562 | 727.0168 | 196 | 1.9311e-05 | 13.9 | 11.4788 | 270.8849 | 6516.1794 | 867.6597 | 0.089455 | 5.3592 | 1.0043 | 0.00034477 | 0.00015203 | 0.015365 | 0.052445 | {02C4638B-890A-4131-8AEF-2E0622DB34D6} | 163692102 | SALT SPRINGS 2102 | 8442 | 38.4156 | -120.1341 | SALT SPRINGS 21028442 | 80 | 61 | 21783.4381 | 19520.8754 | 2262.5627 | 19520.8754 | 2262.5627 | 0.029799 | 0.0037849 | 1.5887 | 7.9694 | 1581 | 0.067574 | 1863 | 0 | 0 | 12.1297 | 35 | 0
North Valley | 856 | 62 | 114.345 | 253 | 207.1363 | 77 | 2.3273e-05 | 16.4404 | 3.7504 | 390.8615 | 2808.037 | 10.9382 | 6.886 | 390.623 | 1.5939 | 0.00034206 | 5.9659e-05 | 0.24506 | 0.55203 | {9F15BDD3-391E-4F68-AFF5-FA940D11CF0D} | 103551101 | RISING RIVER 1101 | circuit_breaker | 40.9286 | -121.5434 | RISING RIVER 1101circuit_breaker | 180 | 249 | 31407.6343 | 21037.7324 | 10369.9019 | 14030.5414 | 9224.629 | 0.0045937 | 0.001792 | 1.8443 | 3.2857 | 2146 | 0.026339 | 1864 | 0 | 0 | 8.7182 | 687 | 0
Central Coast | 3703 | 3392 | 6398.7305 | 5006 | 7315.0327 | 270 | 0.00012409 | 3.3252 | 4.3975 | 36.5466 | 155.6782 | 1.5849 | 0.60249 | 12.8351 | 1.0334 | 0.00033975 | 0.00031896 | 0.67759 | 0.87474 | {B2736A5B-2643-4CB6-B3B5-18538EA2774B} | 83622106 | CAMP EVERS 2106 | 12518 | 37.079 | -122.0037 | CAMP EVERS 210612518 | 249 | 234 | 38887.1638 | 25588.9357 | 13298.228 | 25588.9357 | 13298.228 | 0.086119 | 0.033504 | 1.8864 | 18.5407 | 1079 | 0.091732 | 1865 | 0 | 0 | 15.9002 | 707 | 0
Central Coast | 5879 | 1547 | 2799.5298 | 3099 | 3708.258 | 192 | 3.8871e-05 | 9.2068 | 4.4986 | 62 | 404.4523 | 5.5989 | 1.099 | 41.0196 | 1.0987 | 0.00033923 | 0.00010669 | 0.49919 | 0.75494 | {11A5B6DF-81F1-427D-A78C-DE7EF2F392AC} | 182941102 | OTTER 1102 | 63868 | 36.2641 | -121.7954 | OTTER 110263868 | 257 | 218 | 33727.4484 | 25330.6289 | 8396.8195 | 25330.6289 | 8396.8195 | 0.020484 | 0.0074633 | 1.8097 | 16.1406 | 1821 | 0.065133 | 1866 | 0 | 0 | 15.7397 | 2215 | 0
Bay Area | 6889 | 12 | 19.5137 | 134 | 90.4492 | 10 | 8.6862e-05 | 4.8219 | 0.04918 | 0.031045 | 0.00036582 | 1.2891e-07 | 0.86173 | 2.7222 | 1.0031 | 0.00033735 | 2.882e-05 | 0.089552 | 0.21574 | {D3D9A372-719E-4A04-B8A6-E8D2724FA93F} | 42011107 | SAN RAFAEL 1107 | 1415 | 37.9673 | -122.5378 | SAN RAFAEL 11071415 | 41 | 225 | 12418.1603 | 1913.2696 | 10504.8908 | 1054.2427 | 7130.0122 | 0.0002882 | 0.00086862 | 1.6261 | 13.4 | 2479 | 0.0033735 | 1867 | 0 | 0 | 0.65508 | 2312 | 0
North Valley | 6299 | 110 | 177.1064 | 223 | 233.2864 | 33 | 9.1514e-05 | 6.6043 | 3.4556 | 36.7996 | 301.0347 | 9.3955 | 1.646 | 32.0272 | 1.0475 | 0.00033666 | 0.00021457 | 0.49327 | 0.75918 | {6FBCFF19-8461-4946-AD7D-C380516CF011} | 103091102 | CLARK ROAD 1102 | 47006 | 39.6987 | -121.5742 | CLARK ROAD 110247006 | 101 | 95 | 14376.2888 | 7271.2685 | 7105.0203 | 7271.2685 | 7105.0203 | 0.0070809 | 0.00302 | 1.6101 | 6.7576 | 1364 | 0.01111 | 1868 | 0 | 0 | 4.5182 | 2343 | 0
Central Coast | 3017 | 270 | 820.4171 | 508 | 918.0393 | 82 | 1.9907e-05 | 14.2908 | 3.4866 | 63.8979 | 445.6804 | 2.1871 | 2.8458 | 12.126 | 1.1207 | 0.00033026 | 4.8845e-05 | 0.5315 | 0.89366 | {0CDA8136-A503-4AA7-BC0A-B92F08FF6749} | 182601102 |  | V50 | 35.0771 | -120.5828 | V50 | 193 | 270 | 34609.3641 | 16865.8166 | 17743.5474 | 10661.0029 | 13639.8627 | 0.0040053 | 0.0016324 | 3.0386 | 6.1951 | 2236 | 0.027081 | 1869 | 0 | 0 | 6.6244 | 666 | 0
North Valley | 6009 | 60 | 124.444 | 1174 | 730.8768 | 191 | 1.356e-05 | 18.178 | 3.8122 | 94.4201 | 394.4453 | 5.1794 | 2.7166 | 82.663 | 1.0777 | 0.00032832 | 3.0014e-05 | 0.051107 | 0.17027 | {8F4CC463-393C-4538-A842-1BB0282A8F17} | 103551101 | RISING RIVER 1101 | 9032 | 40.7801 | -121.5032 | RISING RIVER 11019032 | 243 | 340 | 50929.046 | 37315.5797 | 13613.4663 | 35634.3752 | 12189.4552 | 0.0057327 | 0.00259 | 2.0741 | 6.1466 | 2469 | 0.062709 | 1870 | 0 | 0 | 22.1422 | 698 | 0
Central Valley | 8659 | 166 | 228.9636 | 1129 | 712.9275 | 30 | 5.6853e-05 | 5.6107 | 44.1365 | 24.9727 | 109.1391 | 6.7255 | 0.60016 | 2.6065 | 1.2687 | 0.00032668 | 0.00095882 | 0.14703 | 0.32116 | {F7C0AC68-FB70-41DD-B222-3064175EA9BE} | 163661702 | MIWUK 1702 | 1808 | 38.0301 | -120.245 | MIWUK 17021808 | 62 | 308 | 16929.7344 | 2945.2419 | 13984.4925 | 2945.2419 | 13984.4925 | 0.028765 | 0.0017056 | 1.3793 | 37.6333 | 431 | 0.0098005 | 1871 | 0 | 0 | 1.8301 | 2654 | 0
Sierra | 4307 | 344 | 581.3304 | 1440 | 1005.6297 | 145 | 0.00011188 | 2.6861 | 2.9095 | 9.9944 | 40.542 | 0.41422 | 2.7185 | 17.4007 | 1.2565 | 0.00032398 | 0.00021397 | 0.23889 | 0.57808 | {3783BA8A-4769-47A2-BDB8-6B31F03E9521} | 153081111 | PLACERVILLE 1111 | 8582 | 38.7245 | -120.802 | PLACERVILLE 11118582 | 346 | 517 | 42572.4187 | 18913.646 | 23658.7727 | 14528.3903 | 21755.2755 | 0.031026 | 0.016223 | 1.6899 | 9.931 | 1369 | 0.046977 | 1872 | 0 | 0 | 9.0275 | 1037 | 0
North Coast | 7385 | 163 | 275.303 | 206 | 298.0095 | 14 | 0.00016567 | 1.7648 | 33.1665 | 175.7396 | 1874.2263 | 125.3498 | 0.42288 | 1.5183 | 1.0008 | 0.00032359 | 0.0023017 | 0.79126 | 0.92381 | {1CC83EB3-42D9-4ECB-9D96-55AF2CB567FA} | 42811112 | MONTE RIO 1112 | 15401 | 38.4246 | -122.9613 | MONTE RIO 111215401 | 19 | 147 | 7436.3167 | 1388.1732 | 6048.1435 | 1388.1732 | 6048.1435 | 0.032223 | 0.0023194 | 1.689 | 14.7143 | 152 | 0.0045303 | 1873 | 0 | 0 | 0.86257 | 413 | 0
Central Valley | 588 | 13 | 21.2619 | 123 | 74.5258 | 19 | 2.8552e-05 | 10.4173 | 5.1156 | 105.0916 | 1046.4436 | 15.2558 | 1.8456 | 68.3898 | 1.2639 | 0.00032313 | 7.3165e-05 | 0.10569 | 0.2853 | {F49F720E-0E74-44F4-A395-CBFF584836C4} | 163351703 | CURTIS 1703 | 56972 | 37.8853 | -120.3061 | CURTIS 170356972 | 84 | 78 | 17477.0678 | 13676.594 | 3800.4738 | 13676.594 | 3800.4738 | 0.0013901 | 0.00054249 | 1.6355 | 6.4737 | 2035 | 0.0061394 | 1874 | 0 | 0 | 8.4982 | 1931 | 0
Central Valley | 106 | 585 | 840.2645 | 2131 | 1610.4662 | 136 | 0.00011637 | 2.6877 | 3.9894 | 20.6629 | 124.8338 | 1.9517 | 0.96955 | 7.5862 | 1.0195 | 0.00031868 | 0.00025837 | 0.27452 | 0.52175 | {B167BE1C-A9FE-47A6-A4DC-3662D3CE2EC1} | 163761703 | RACETRACK 1703 | 8120 | 38.0253 | -120.405 | RACETRACK 17038120 | 219 | 239 | 28488.8815 | 14368.0422 | 14120.8393 | 14368.0422 | 14120.8393 | 0.035138 | 0.015826 | 1.4363 | 15.6691 | 1232 | 0.043341 | 1875 | 0 | 0 | 8.9279 | 861 | 0
Central Coast | 1334 | 452 | 755.6356 | 705 | 884.8113 | 41 | 0.00016759 | 2.3851 | 1.9417 | 4.3217 | 21.6037 | 0.097011 | 0.35905 | 3.7246 | 1.0128 | 0.00031839 | 0.00020874 | 0.64113 | 0.85401 | {7A9AA471-3E06-41F0-A2F5-E0382CC26D52} | 83622103 | CAMP EVERS 2103 | 5753 | 37.0019 | -122.0379 | CAMP EVERS 21035753 | 62 | 437 | 19682.5441 | 3895.5708 | 15786.9733 | 3895.5708 | 15786.9733 | 0.0085585 | 0.0068712 | 1.6718 | 17.1951 | 1383 | 0.013054 | 1876 | 0 | 0 | 2.4206 | 1074 | 0
Central Valley | 1168 | 8 | 15.1477 | 40 | 30.8884 | 8 | 0.00010607 | 3.0388 | 23.9631 | 46.9966 | 132.4559 | 5.2486 | 4.0653 | 32.887 | 1.1264 | 0.00031822 | 0.00187 | 0.2 | 0.4904 | {EA8957E8-4D9E-4768-B294-C26CA1256456} | 163781705 | PEORIA 1705 | 75274 | 37.9488 | -120.4192 | PEORIA 170575274 | 111 | 406 | 21052.6899 | 5362.5182 | 15690.1717 | 450.4418 | 831.729 | 0.01496 | 0.00084852 | 1.8935 | 5 | 187 | 0.0025458 | 1877 | 0 | 0 | 0.27989 | 1579 | 0
North Coast | 2145 | 258 | 422.3339 | 342 | 460.7547 | 41 | 7.733e-05 | 3.5459 | 4.0263 | 52.5185 | 181.3488 | 1.0851 | 1.8042 | 16.7823 | 1.0267 | 0.00031524 | 0.00022387 | 0.75439 | 0.91661 | {C04ABA60-50E1-4D28-B0FC-7F9C72775B5F} | 192151131 | NEWBURG 1131 | circuit_breaker | 40.5944 | -124.1353 | NEWBURG 1131circuit_breaker | 305 | 693 | 52153.1542 | 19977.4909 | 32175.6633 | 3684.9558 | 3558.8108 | 0.0091787 | 0.0031705 | 1.637 | 8.3415 | 1330 | 0.012925 | 1878 | 0 | 0 | 2.2897 | 1682 | 0
Bay Area | 3139 | 454 | 1233.1458 | 1043 | 1554.8138 | 115 | 5.6467e-05 | 4.4069 | 1.2085 | 11.7248 | 45.5627 | 0.02379 | 0.80932 | 14.1271 | 0.99454 | 0.00031635 | 5.4418e-05 | 0.43528 | 0.79311 | {473DFDCA-EA19-476B-B0A4-B163B0B91B7F} | 12501105 | EL CERRITO G 1105 | BR160 | 37.8981 | -122.2615 | EL CERRITO G 1105BR160 | 253 | 1494 | 77267.8975 | 18464.1036 | 58803.7939 | 13118.739 | 33026.1297 | 0.0062581 | 0.0064937 | 2.7162 | 9.0696 | 2199 | 0.03638 | 1879 | 0 | 0 | 8.1516 | 2742 | 0
Central Coast | 3139 | 0 | 0 | 8 | 6.5435 | 1 | 4.2938e-05 | 0.066432 |  |  |  |  | 4.5274e-13 | 4.8996e-14 | 4.5475e-13 | 2.8524e-06 | 4.2938e-05 | 0 | 0 | {473DFDCA-EA19-476B-B0A4-B163B0B91B7F} | 12501105 | EL CERRITO G 1105 | BR160 | 37.8981 | -122.2615 | EL CERRITO G 1105BR160 | 253 | 1494 | 77267.8975 | 18464.1036 | 58803.7939 | 13118.739 | 33026.1297 | 4.2938e-05 | 4.2938e-05 |  | 8 | 2300 | 2.8524e-06 | 1879 | 0 | 0 | 8.1516 | 2300 | 0
Bay Area | 9522 | 44 | 106.4881 | 170 | 170.5461 | 30 | 4.5537e-05 | 12.3703 | 6.9493 | 56.0175 | 108.9177 | 3.6608 | 0.80435 | 73.446 | 1.0293 | 0.0003119 | 0.00013429 | 0.25882 | 0.62439 | {4B04C7BE-F037-4E43-AD43-455E3B1A9C74} | 13921104 | FRANKLIN 1104 | P146 | 38.013 | -122.2522 | FRANKLIN 1104P146 | 53 | 30 | 7314.5058 | 5929.8532 | 1384.6526 | 5649.6032 | 1140.8468 | 0.0040286 | 0.0013661 | 2.4202 | 5.6667 | 1676 | 0.0093569 | 1880 | 0 | 0 | 3.5105 | 2119 | 0
Central Valley | 3679 | 686 | 950.488 | 1740 | 1442.02 | 138 | 5.7725e-05 | 5.9202 | 137.7443 | 851.5566 | 12055.9268 | 3189.3304 | 2.0945 | 27.5378 | 1.2541 | 0.0003065 | 0.0036972 | 0.39425 | 0.65914 | {EA84943C-5C73-4028-8D85-A074BC119CA8} | 163351705 | CURTIS 1705 | 10590 | 37.9742 | -120.2382 | CURTIS 170510590 | 181 | 235 | 27387.7035 | 15780.5647 | 11607.1388 | 15780.5647 | 11607.1388 | 0.51021 | 0.0079661 | 1.3856 | 12.6087 | 69 | 0.042297 | 1881 | 0 | 0 | 9.8056 | 2385 | 0
Central Coast | 7983 | 138 | 331.2929 | 652 | 644.7233 | 70 | 3.9938e-05 | 12.3054 | 1.5325 | 23.9317 | 121.9485 | 1.0435 | 2.3444 | 63.1166 | 1.0509 | 0.0003063 | 4.589e-05 | 0.21166 | 0.51385 | {CF5272DC-8419-42E3-A72F-BD395166C5DF} | 182951102 | FOOTHILL 1102 | circuit_breaker | 35.2862 | -120.7061 | FOOTHILL 1102circuit_breaker | 175 | 150 | 23606.8594 | 15763.1114 | 7843.748 | 12510.7066 | 7155.7253 | 0.0032123 | 0.0027957 | 2.4007 | 9.3143 | 2276 | 0.021441 | 1882 | 0 | 0 | 7.7738 | 176 | 0
Central Coast | 1950 | 1 | 4.0491 | 24 | 43.523 | 1 | 3.6762e-05 | 95.1875 |  |  |  |  | 0.0066372 | 16.042 | 1.0332 | 0.0034993 | 3.6762e-05 | 0.041667 | 0.093033 | {CB6D4D73-6698-4949-92C3-C35EC9D09543} | 24101103 | HALF MOON BAY 1103 | 69412 | 37.2032 | -122.401 | HALF MOON BAY 110369412 | 203 | 158 | 40214.2392 | 34521.6852 | 5692.5539 | 21261.3098 | 3166.6716 | 3.6762e-05 | 3.6762e-05 | 4.0491 | 24 | 2377 | 0.0034993 | 1883 | 0 | 0 | 13.2112 | 1730 | 0
Bay Area | 1950 | 947 | 2051.567 | 1289 | 2217.5552 | 140 | 2.4746e-05 | 9.1808 | 0.62329 | 73.502 | 415.0725 | 0.73198 | 0.55149 | 32.3826 | 1.0642 | 0.00028297 | 1.9799e-05 | 0.73468 | 0.92515 | {CB6D4D73-6698-4949-92C3-C35EC9D09543} | 24101103 | HALF MOON BAY 1103 | 69412 | 37.2032 | -122.401 | HALF MOON BAY 110369412 | 203 | 158 | 40214.2392 | 34521.6852 | 5692.5539 | 21261.3098 | 3166.6716 | 0.0027719 | 0.0034644 | 2.1664 | 9.2071 | 2613 | 0.039616 | 1883 | 0 | 0 | 13.2112 | 726 | 0
North Valley | 6835 | 292 | 430.4387 | 598 | 585.6235 | 115 | 4.7678e-05 | 5.9333 | 6.4595 | 1526.9707 | 26715.8313 | 336.0621 | 1.6833 | 104.2591 | 1.2164 | 0.00030544 | 0.00014627 | 0.48829 | 0.73501 | {B0EE660F-07F5-4C10-A48E-D83518A24C12} | 103381101 | FRENCH GULCH 1101 | 2905 | 40.7199 | -122.6295 | FRENCH GULCH 11012905 | 101 | 102 | 23359.3837 | 15608.0555 | 7751.3281 | 15608.0555 | 7751.3281 | 0.016821 | 0.005483 | 1.4741 | 5.2 | 1613 | 0.035126 | 1884 | 0 | 0 | 9.6984 | 388 | 0
Sierra | 5585 | 325 | 469.9111 | 625 | 605.1682 | 56 | 0.00011107 | 3.4627 | 5.4196 | 14.1615 | 56.1542 | 0.75111 | 1.6929 | 9.4588 | 1.0033 | 0.00030495 | 0.0004436 | 0.52 | 0.7765 | {FCC40ADF-1FB7-4F80-97A9-6981FCDC8244} | 152691103 | HIGGINS 1103 | 995672 | 39.1337 | -121.0716 | HIGGINS 1103995672 | 146 | 195 | 19946.0049 | 9263.8953 | 10682.1097 | 5336.5048 | 5488.4306 | 0.024841 | 0.0062197 | 1.4459 | 11.1607 | 875 | 0.017077 | 1885 | 0 | 0 | 3.3159 | 606 | 0
Central Coast | 4424 | 128 | 183.508 | 567 | 461.6409 | 99 | 2.6408e-05 | 15.7458 | 4.7623 | 124.8999 | 566.9387 | 11.7833 | 3.4087 | 69.0265 | 1.0982 | 0.00030337 | 7.8821e-05 | 0.22575 | 0.39751 | {494B4DF8-9782-49DD-876E-C17DBB5295CE} | 83182101 | LLAGAS 2101 | 1449 | 37.0418 | -121.5418 | LLAGAS 21011449 | 152 | 110 | 30783.2305 | 22615.7362 | 8167.4943 | 16208.7254 | 2414.0266 | 0.0078033 | 0.0026144 | 1.4337 | 5.7273 | 1991 | 0.030034 | 1886 | 0 | 0 | 10.0716 | 1600 | 0
Central Coast | 2244 | 90 | 217.7725 | 304 | 335.2702 | 55 | 1.3093e-05 | 56.1684 | 6.3444 | 67.6231 | 332.6853 | 4.4858 | 2.7398 | 56.5382 | 0.94952 | 0.00030266 | 3.3966e-05 | 0.29605 | 0.64954 | {EF084BAC-E8B6-45D7-885C-1A50430DEB23} | 182601104 | OCEANO 1104 | circuit_breaker | 35.1013 | -120.5814 | OCEANO 1104circuit_breaker | 379 | 1013 | 69991.1235 | 24379.2168 | 45611.9066 | 11912.9543 | 16961.5498 | 0.0018681 | 0.00072013 | 2.4197 | 5.5273 | 2413 | 0.016646 | 1887 | 0 | 0 | 7.4024 | 1525 | 0
North Valley | 3281 | 501 | 825.4945 | 2400 | 1715.2114 | 357 | 8.7829e-05 | 2.6678 | 22.6921 | 1302.6281 | 23329.6433 | 1061.3873 | 1.2594 | 37.4646 | 1.1252 | 0.00030238 | 0.0010189 | 0.20875 | 0.48128 | {A8F5D900-0ACF-447E-AA7A-C456EDB7D112} | 103221101 | KANAKA 1101 | 1406 | 39.5731 | -121.3176 | KANAKA 11011406 | 270 | 199 | 60283.2304 | 44466.328 | 15816.9024 | 43311.9933 | 15816.9024 | 0.36375 | 0.031355 | 1.6477 | 6.7227 | 403 | 0.10795 | 1888 | 0 | 0 | 26.9128 | 959 | 0
Central Valley | 580 | 387 | 648.0206 | 5653 | 3334.3381 | 135 | 4.8476e-05 | 6.2287 | 31.1546 | 29.2331 | 133.5997 | 6.5607 | 0.8225 | 3.2334 | 1.1424 | 0.00030219 | 0.00063364 | 0.068459 | 0.19435 | {38AAAE1F-7053-4022-8941-265790AA8F13} | 163661701 | MIWUK 1701 | 10600 | 38.066 | -120.1888 | MIWUK 170110600 | 305 | 961 | 40826.3466 | 17528.1979 | 23298.1487 | 17528.1979 | 23298.1487 | 0.085541 | 0.0065443 | 1.6745 | 41.8741 | 634 | 0.040795 | 1889 | 0 | 0 | 10.8915 | 2009 | 0
Sierra | 2132 | 306 | 445.7378 | 958 | 688.7623 | 79 | 0.00015596 | 4.2801 | 20.8261 | 44.8614 | 155.5209 | 7.4704 | 2.9767 | 18.6175 | 1.1429 | 0.00029979 | 0.0013947 | 0.31942 | 0.64716 | {6872443C-7FE4-416F-92B9-65D58A293737} | 152261104 | DIAMOND SPRINGS 1104 | circuit_breaker | 38.693 | -120.8259 | DIAMOND SPRINGS 1104circuit_breaker | 308 | 519 | 37060.6626 | 16049.1693 | 21011.4933 | 9049.1715 | 10941.4968 | 0.11018 | 0.012321 | 1.4567 | 12.1266 | 274 | 0.023684 | 1890 | 0 | 0 | 5.6229 | 578 | 0
North Coast | 1680 | 1115 | 2249.3483 | 1515 | 2432.304 | 97 | 7.412e-05 | 4.477 | 3.3622 | 56.626 | 330.4761 | 1.9803 | 0.41869 | 10.1002 | 1.0201 | 0.00029938 | 0.00016718 | 0.73597 | 0.92478 | {51F158BA-B081-4FAF-A03B-EC569F9C35AD} | 42981101 | ELK 1101 | 91336 | 39.2238 | -123.7688 | ELK 110191336 | 119 | 116 | 21915.3013 | 13315.4628 | 8599.8385 | 11968.0294 | 6758.5078 | 0.016216 | 0.0071896 | 2.0174 | 15.6186 | 1527 | 0.02904 | 1891 | 0 | 0 | 7.4366 | 872 | 0
North Coast | 1791 | 1489 | 3047.4516 | 2346 | 3430.2087 | 167 | 7.831e-05 | 3.2264 | 0.76159 | 74.696 | 390.4412 | 0.48634 | 0.37979 | 17.6922 | 1.1048 | 0.00029753 | 7.0602e-05 | 0.6347 | 0.88842 | {FD379B27-6785-4E43-84D1-7E22C4EB286F} | 42761101 | FORT BRAGG A 1101 | 4622 | 39.5153 | -123.7634 | FORT BRAGG A 11014622 | 153 | 150 | 37166.6829 | 21198.3263 | 15968.3566 | 21198.3263 | 15968.3566 | 0.01179 | 0.013078 | 2.0466 | 14.0479 | 2051 | 0.049687 | 1892 | 0 | 0 | 13.172 | 1373 | 0
Central Valley | 4077 | 198 | 264.2514 | 1053 | 662.2253 | 178 | 4.2397e-05 | 6.3627 | 6.2394 | 262.3479 | 3582.5977 | 30.3251 | 1.0397 | 46.2687 | 1.0961 | 0.0002973 | 0.00015907 | 0.18803 | 0.39904 | {36E417A9-B355-4038-92B6-BA6B805D598D} | 254452101 | MARIPOSA 2101 | 10170 | 37.5164 | -119.8354 | MARIPOSA 210110170 | 204 | 269 | 50113.7807 | 26174.8185 | 23938.9622 | 26174.8185 | 23938.9622 | 0.028315 | 0.0075467 | 1.3346 | 5.9157 | 1547 | 0.05292 | 1893 | 0 | 0 | 16.2643 | 1311 | 0
North Coast | 3431 | 567 | 1004.4077 | 1014 | 1240.7194 | 83 | 0.00013405 | 2.6392 | 3.3016 | 34.7103 | 198.3351 | 0.94284 | 0.42078 | 15.3706 | 1.5533 | 0.00029534 | 0.00029947 | 0.55917 | 0.80954 | {7E7B289D-4C56-4E03-B7F0-62BB352D64F7} | 42811111 | MONTE RIO 1111 | 256 | 38.4698 | -123.0145 | MONTE RIO 1111256 | 165 | 408 | 27297.8886 | 11643.9499 | 15653.9386 | 11643.9499 | 15653.9386 | 0.024856 | 0.011126 | 1.7714 | 12.2169 | 1126 | 0.024513 | 1894 | 0 | 0 | 7.2352 | 2496 | 0
Central Coast | 6315 | 10 | 18.0663 | 37 | 35.1378 | 7 | 3.1377e-05 | 13.9051 | 1.0989 | 126.9569 | 733.3425 | 1.2288 | 1.7626 | 51.0885 | 1.0619 | 0.00029356 | 2.6925e-05 | 0.27027 | 0.51416 | {BEF6045A-3518-436C-A876-62625F5A4B60} | 182951101 | FOOTHILL 1101 | 549904 | 35.2965 | -120.7659 | FOOTHILL 1101549904 | 207 | 227 | 48545.8649 | 28248.1164 | 20297.7485 | 12017.3608 | 7935.1372 | 0.00018848 | 0.00021964 | 1.8066 | 5.2857 | 2506 | 0.0020549 | 1895 | 0 | 0 | 7.4672 | 2686 | 0
Central Valley | 3533 | 766 | 1034.0885 | 2850 | 1961.1381 | 187 | 9.7449e-05 | 2.9909 | 18.6763 | 133.663 | 1207.6399 | 47.4996 | 2.423 | 22.9153 | 1.0737 | 0.00029156 | 0.00095841 | 0.26877 | 0.52729 | {EAC612D6-99B1-40C4-9814-8599E5819D52} | 163751101 | PINE GROVE 1101 | 3166 | 38.4065 | -120.6704 | PINE GROVE 11013166 | 234 | 263 | 31547.5015 | 20128.8983 | 11418.6031 | 20128.8983 | 11418.6031 | 0.17922 | 0.018223 | 1.35 | 15.2406 | 432 | 0.054521 | 1896 | 0 | 0 | 12.5075 | 1055 | 0
North Valley | 9034 | 34 | 45.4228 | 110 | 80.6972 | 9 | 0.0001214 | 2.7083 | 14.4069 | 53.5814 | 583.9839 | 9.5391 | 0.070059 | 2.4164 | 1.0005 | 0.00029152 | 0.00047805 | 0.30909 | 0.56288 | {54D27D9E-5ABC-4BF1-A8D9-EE091D3344C3} | 102541102 | VOLTA 1102 | 80982 | 40.4959 | -121.9103 | VOLTA 110280982 | 22 | 7 | 1106.4574 | 836.5231 | 269.9343 | 836.5231 | 269.9343 | 0.0043025 | 0.0010926 | 1.336 | 12.2222 | 813 | 0.0026237 | 1897 | 0 | 0 | 0.51979 | 891 | 0
North Coast | 3214 | 62 | 127.0805 | 165 | 167.206 | 50 | 5.7698e-05 | 4.6025 | 1.1292 | 46.6101 | 471.0799 | 3.0526 | 1.5359 | 100.1267 | 1.1075 | 0.0002908 | 6.3427e-05 | 0.37576 | 0.76002 | {E3192F4B-E306-4B2D-9341-C84584505AEB} | 43311108 | KONOCTI 1108 | circuit_breaker | 38.9324 | -122.741 | KONOCTI 1108circuit_breaker | 185 | 659 | 46677.5588 | 14154.8598 | 32522.6989 | 9103.4044 | 16624.5352 | 0.0031714 | 0.0028849 | 2.0497 | 3.3 | 2108 | 0.01454 | 1898 | 0 | 0 | 5.6566 | 2277 | 0
Central Coast | 4408 | 147 | 336.693 | 402 | 486.3411 | 73 | 2.2035e-05 | 12.4982 | 14.738 | 68.0587 | 194.716 | 21.2545 | 3.693 | 36.8749 | 1.0456 | 0.00029004 | 0.00017764 | 0.36567 | 0.6923 | {FE25DCBF-8FD2-4D0B-8589-850A3EE5ED4C} | 182731102 | RESERVATION ROAD 1102 | circuit_breaker | 36.6243 | -121.6884 | RESERVATION ROAD 1102circuit_breaker | 320 | 358 | 47129.6684 | 28859.6299 | 18270.0386 | 12102.7686 | 7481.1939 | 0.012967 | 0.0016085 | 2.2904 | 5.5068 | 1497 | 0.021173 | 1899 | 0 | 0 | 7.5203 | 149 | 0
Central Coast | 1988 | 2 | 2.4554 | 7 | 5.7598 | 3 | 2.307e-05 | 9.8112 |  |  |  |  | 2.0413 | 248.1484 | 1.1659 | 0.00028956 | 2.307e-05 | 0.28571 | 0.4263 | {BE64DC1C-3443-4966-940E-5A564C032974} | 83392102 | SWIFT 2102 | circuit_breaker | 37.3223 | -121.7966 | SWIFT 2102circuit_breaker | 45 | 75 | 7298.1738 | 3757.8955 | 3540.2783 | 706.8877 | 1136.9514 | 6.9211e-05 | 6.9211e-05 | 1.2277 | 2.3333 | 2566 | 0.00086869 | 1900 | 0 | 0 | 0.43924 | 558 | 0
Central Coast | 4445 | 13 | 29.4452 | 39 | 40.3375 | 3 | 1.6254e-05 | 15.9191 |  |  |  |  | 3.958 | 20.6107 | 1.0088 | 0.00028861 | 1.6254e-05 | 0.33333 | 0.72997 | {982A8403-6DD7-4479-B96A-84BF654A0654} | 183052113 | TEMPLETON 2113 | A30 | 35.4889 | -120.6645 | TEMPLETON 2113A30 | 61 | 146 | 7860.0523 | 2568.4452 | 5291.6071 | 401.1046 | 291.136 | 4.8763e-05 | 4.8763e-05 | 2.265 | 13 | 2679 | 0.00086582 | 1901 | 0 | 0 | 0.24923 | 503 | 0
Sierra | 3543 | 1806 | 2172.868 | 3327 | 2790.9155 | 303 | 6.8452e-05 | 4.0669 | 18.7096 | 123.9521 | 1792.689 | 99.3172 | 0.93612 | 8.1488 | 1.0679 | 0.0002886 | 0.00059311 | 0.54283 | 0.77855 | {547CB5AE-3FC8-46F0-9836-780E7F4C0AE3} | 152481105 | BRUNSWICK 1105 | 32536 | 39.2391 | -120.9998 | BRUNSWICK 110532536 | 539 | 741 | 75577.4302 | 34249.9271 | 41327.5031 | 34249.9271 | 41327.5031 | 0.17971 | 0.020741 | 1.2031 | 10.9802 | 677 | 0.087446 | 1902 | 0 | 0 | 21.2819 | 310 | 0
North Coast | 6525 | 33 | 60.3181 | 88 | 79.9852 | 13 | 6.5065e-05 | 3.7922 | 0 | 0 | 0 | 0 | 0.70507 | 13.0266 | 1.0325 | 0.00028492 | 4.3589e-05 | 0.375 | 0.75412 | {928EDF6A-AE60-4D52-BF0A-EE27518314CC} | 43191101 | REDBUD 1101 | 400 | 39.0262 | -122.7314 | REDBUD 1101400 | 31 | 114 | 6049.8422 | 1637.3642 | 4412.4779 | 1401.7515 | 2490.499 | 0.00056665 | 0.00084584 | 1.8278 | 6.7692 | 2295 | 0.003704 | 1903 | 0 | 0 | 0.87101 | 2880 | 0
Central Coast | 8487 | 488 | 778.3169 | 941 | 1019.7053 | 68 | 2.7955e-05 | 10.2001 | 10.5447 | 234.846 | 2078.798 | 40.1883 | 1.0167 | 64.0038 | 1.1567 | 0.00028357 | 0.00016387 | 0.5186 | 0.76328 | {C47B4B77-9CC6-4665-96AD-097EBCE52988} | 182941102 | OTTER 1102 | 2166 | 36.2769 | -121.8264 | OTTER 11022166 | 84 | 74 | 8488.7732 | 6559.0006 | 1929.7726 | 6559.0006 | 1929.7726 | 0.011143 | 0.001901 | 1.5949 | 13.8382 | 1537 | 0.019283 | 1904 | 0 | 0 | 4.0756 | 1065 | 0
Central Coast | 4931 | 26 | 47.3659 | 163 | 114.3284 | 25 | 2.9929e-05 | 6.8375 | 0.8297 | 17.3553 | 76.3537 | 0.10427 | 1.1245 | 30.6598 | 1.0946 | 0.00028351 | 2.6656e-05 | 0.15951 | 0.4143 | {196F79B3-5D9F-4F99-B311-272A909D0DD7} | 182631107 | SAN LUIS OBISPO 1107 | V18 | 35.1831 | -120.7039 | SAN LUIS OBISPO 1107V18 | 91 | 199 | 14330.2897 | 6444.7052 | 7885.5845 | 4192.834 | 1240.3861 | 0.00066641 | 0.00074821 | 1.8218 | 6.52 | 2509 | 0.0070877 | 1905 | 0 | 0 | 2.6053 | 2193 | 0
Central Valley | 1005 | 9 | 12.2964 | 58 | 38.514 | 26 | 5.1052e-05 | 6.4654 | 7.6752 | 38.9282 | 238.2688 | 2.5809 | 0.76464 | 20.6264 | 1.0756 | 0.00027992 | 0.00017816 | 0.15517 | 0.31927 | {B1C3BF34-DFE5-420F-B7AD-C0CAC681FC7D} | 254452101 | MARIPOSA 2101 | 439030 | 37.4657 | -119.7562 | MARIPOSA 2101439030 | 314 | 470 | 58722.1343 | 31566.7616 | 27155.3727 | 31566.7616 | 27155.3727 | 0.0046321 | 0.0013274 | 1.3663 | 2.2308 | 1494 | 0.007278 | 1906 | 0 | 0 | 19.6147 | 2424 | 0
North Valley | 2060 | 127 | 136.7812 | 405 | 262.4934 | 40 | 4.7031e-05 | 6.0091 | 14.299 | 102.2051 | 1183.6789 | 23.9635 | 0.65852 | 17.9972 | 1.0101 | 0.00027985 | 0.00033525 | 0.31358 | 0.52108 | {16F7FCB4-7137-4ADD-B98B-6145D8BC444D} | 102541102 | VOLTA 1102 | 1648 | 40.5069 | -121.8183 | VOLTA 11021648 | 104 | 172 | 14953.1937 | 6728.2286 | 8224.9651 | 6728.2286 | 8224.9651 | 0.01341 | 0.0018812 | 1.077 | 10.125 | 1042 | 0.011194 | 1907 | 0 | 0 | 4.1807 | 978 | 0
Central Coast | 3882 | 239 | 454.3635 | 625 | 671.7554 | 32 | 0.00019632 | 1.5527 | 9.2875 | 31.201 | 359.2462 | 15.53 | 0.28637 | 3.2684 | 1.0017 | 0.00027814 | 0.0010614 | 0.3824 | 0.67638 | {CC60F8EB-8583-4463-B38C-D2F869F171F0} | 82841101 | BIG BASIN 1101 | 12838 | 37.1272 | -122.1236 | BIG BASIN 110112838 | 64 | 190 | 12297.8637 | 3775.6915 | 8522.1722 | 3775.6915 | 8522.1722 | 0.033965 | 0.0062822 | 1.9011 | 19.5312 | 381 | 0.0089004 | 1908 | 0 | 0 | 2.3461 | 204 | 0
Central Valley | 5401 | 3 | 6.6116 | 36 | 16.7414 | 10 | 6.6013e-05 | 4.8413 | 12.2556 | 274.9994 | 1232.893 | 53.3182 | 2.25 | 21.4711 | 1.0814 | 0.00027611 | 0.00063572 | 0.083333 | 0.39493 | {94EE7076-462E-4300-BB9C-E1B2A1AE599F} | 163451702 | FROGTOWN 1702 | 36870 | 38.0806 | -120.5562 | FROGTOWN 170236870 | 102 | 176 | 15285.0756 | 5012.9466 | 10272.129 | 1179.9136 | 2374.2193 | 0.0063572 | 0.00066013 | 2.2039 | 3.6 | 632 | 0.0027611 | 1909 | 0 | 0 | 0.73316 | 157 | 0
Central Valley | 1160 | 7 | 21.0996 | 44 | 31.916 | 17 | 2.6644e-05 | 6.4499 | 1.4375 | 1937.2663 | 9588.3026 | 20.0869 | 0.7828 | 277.2825 | 1.4827 | 0.00027572 | 4.1231e-05 | 0.15909 | 0.6611 | {3C66AA6E-AAFB-4AC9-BCE9-F89CAFA6091F} | 252811102 | MERCED FALLS 1102 | circuit_breaker | 37.5233 | -120.3306 | MERCED FALLS 1102circuit_breaker | 279 | 342 | 58748.2899 | 40596.6604 | 18151.6295 | 11883.3184 | 292.1017 | 0.00070093 | 0.00045295 | 3.0142 | 2.5882 | 2323 | 0.0046872 | 1910 | 0 | 0 | 7.3839 | 387 | 0
North Valley | 2811 | 249 | 290.2731 | 457 | 380.9562 | 67 | 8.4306e-05 | 3.2608 | 5.7381 | 932.6848 | 20072.977 | 353.0927 | 1.5468 | 27.5623 | 1.0421 | 0.00027559 | 0.00026157 | 0.54486 | 0.76196 | {06EBCEE6-C636-4CF7-B3B5-D5C157499FDB} | 101321101 | PIT NO 5 1101 | 1660 | 40.9966 | -121.9188 | PIT NO 5 11011660 | 76 | 69 | 10253.0692 | 7855.6791 | 2397.3901 | 7855.6791 | 2397.3901 | 0.017525 | 0.0056485 | 1.1658 | 6.8209 | 1223 | 0.018465 | 1911 | 0 | 0 | 4.8813 | 1185 | 0
Central Valley | 7605 | 32 | 60.8499 | 116 | 84.3302 | 33 | 3.6055e-05 | 11.1647 | 4.2236 | 580.9572 | 2274.6092 | 18.4988 | 5.5064 | 327.8444 | 1.4462 | 0.00027435 | 7.4635e-05 | 0.27586 | 0.72157 | {57BF0C33-990B-4465-98B9-17EDC5A10F72} | 163781704 | PEORIA 1704 | circuit_breaker | 37.9034 | -120.4975 | PEORIA 1704circuit_breaker | 91 | 35 | 17837.9513 | 13354.1752 | 4483.7761 | 11652.3164 | 4461.0104 | 0.002463 | 0.0011898 | 1.9016 | 3.5152 | 2021 | 0.0090534 | 1912 | 0 | 0 | 7.2404 | 2285 | 0
Bay Area | 3890 | 470 | 699.4777 | 1631 | 1358.3463 | 96 | 9.4882e-05 | 3.5342 | 2.0826 | 2.5845 | 15.235 | 1.1188 | 0.67766 | 1.3684 | 0.59557 | 0.00027091 | 0.00015482 | 0.28817 | 0.51495 | {9D9542F3-BF28-42DE-B61B-60FE0E01870B} | 42011108 | SAN RAFAEL 1108 | 322 | 37.9774 | -122.5654 | SAN RAFAEL 1108322 | 224 | 1312 | 69160.7589 | 11886.0783 | 57274.6806 | 11483.9582 | 56180.2835 | 0.014862 | 0.0091087 | 1.4883 | 16.9896 | 1566 | 0.026007 | 1913 | 0 | 0 | 7.1358 | 2088 | 0
Central Valley | 1639 | 187 | 385.885 | 3994 | 2197.128 | 238 | 2.741e-05 | 10.0549 | 18.4756 | 462.8182 | 12431.3349 | 836.639 | 0.3079 | 6.0321 | 1.2218 | 0.00027075 | 0.00026372 | 0.04682 | 0.17563 | {06F65D45-2D82-470F-9B27-5D880652F1A1} | 162831702 |  | 9690 | 38.1885 | -120.0082 | 9690 | 343 | 812 | 44783.7765 | 27542.9968 | 17240.7797 | 27542.9968 | 17240.7797 | 0.062766 | 0.0065235 | 2.0636 | 16.7815 | 1211 | 0.064438 | 1914 | 0 | 0 | 17.1144 | 207 | 0
Bay Area | 6607 | 941 | 1728.8449 | 1548 | 2047.928 | 120 | 5.5644e-05 | 4.6243 | 2.0764 | 32.609 | 119.1674 | 0.41255 | 0.14978 | 9.9389 | 1.031 | 0.00026889 | 8.4026e-05 | 0.60788 | 0.84419 | {0D33DD6E-C54D-4E64-89FF-46D8E0E605B6} | 24101103 | HALF MOON BAY 1103 | 98440 | 37.2667 | -122.3224 | HALF MOON BAY 110398440 | 126 | 186 | 26295.7648 | 13071.9471 | 13223.8177 | 13071.9471 | 13223.8177 | 0.010083 | 0.0066773 | 1.8372 | 12.9 | 1958 | 0.032267 | 1915 | 0 | 0 | 8.1225 | 2885 | 0
Central Coast | 4121 | 1528 | 2849.5306 | 3201 | 3845.9534 | 212 | 0.00011453 | 2.7585 | 3.2705 | 12.3479 | 50.6141 | 0.41127 | 0.80501 | 7.4927 | 1.0122 | 0.00026739 | 0.00025361 | 0.47735 | 0.74092 | {CFFA07B9-8209-4D21-824C-C9A2945C083F} | 82021106 | LOS GATOS 1106 | LA64 | 37.1373 | -121.9674 | LOS GATOS 1106LA64 | 259 | 402 | 45605.1006 | 20491.3377 | 25113.7629 | 20491.3377 | 25113.7629 | 0.053766 | 0.024281 | 1.8649 | 15.0991 | 1240 | 0.056688 | 1916 | 0 | 0 | 12.7327 | 2223 | 0
Bay Area | 3239 | 154 | 546.7087 | 199 | 568.9442 | 20 | 2.5375e-05 | 3.6961 | 0.14224 | 0.13911 | 0.0013514 | 3.7882e-07 | 0.40647 | 18.783 | 1.2221 | 0.00026582 | 1.8614e-05 | 0.77387 | 0.96092 | {66ED3CF0-2002-44E6-BE2F-18363B4298A8} | 22721106 | SNEATH LANE 1106 | circuit_breaker | 37.6221 | -122.447 | SNEATH LANE 1106circuit_breaker | 144 | 896 | 48107.178 | 9891.2145 | 38215.9635 | 3587.2513 | 6682.0129 | 0.00037227 | 0.0005075 | 3.5501 | 9.95 | 2638 | 0.0053163 | 1917 | 0 | 0 | 2.229 | 2339 | 0
North Coast | 2036 | 1754 | 2440.995 | 3084 | 3045.1523 | 394 | 0.00015335 | 2.1338 | 1.7379 | 98.6992 | 640.6977 | 1.1214 | 0.95918 | 34.9115 | 1.1814 | 0.00026562 | 0.0002282 | 0.56874 | 0.8016 | {264668B8-73DE-4037-AA66-7B299329D5F2} | 192171103 | WILLOW CREEK 1103 | 2936 | 40.8666 | -123.5145 | WILLOW CREEK 11032936 | 323 | 297 | 59465.3482 | 53467.3373 | 5998.0109 | 53467.3373 | 5998.0109 | 0.089911 | 0.060419 | 1.3917 | 7.8274 | 1317 | 0.10465 | 1918 | 0 | 0 | 33.2231 | 1145 | 0
North Valley | 7598 | 287 | 336.3218 | 504 | 438.9653 | 93 | 2.8565e-05 | 10.8188 | 1.1043 | 222.2624 | 2525.5114 | 9.237 | 0.13845 | 59.5435 | 1.2464 | 0.00026552 | 3.2373e-05 | 0.56944 | 0.76617 | {5C4A4B21-8DC0-4DD4-BD69-EB88E21328E5} | 103732101 | PIT NO 3 2101 | circuit_breaker | 40.9981 | -121.7474 | PIT NO 3 2101circuit_breaker | 54 | 15 | 13252.2607 | 11059.9326 | 2192.3281 | 10857.4498 | 1533.1179 | 0.0030107 | 0.0026565 | 1.1719 | 5.4194 | 2435 | 0.024694 | 1919 | 0 | 0 | 6.7465 | 2471 | 0
Central Coast | 4066 | 1395 | 2522.6969 | 1932 | 2793.1904 | 140 | 0.0002021 | 1.2554 | 2.3081 | 22.9556 | 168.4312 | 2.2034 | 0.45292 | 4.8648 | 1.0046 | 0.0002644 | 0.00031682 | 0.72205 | 0.90316 | {B4068132-26FE-4389-8AFD-3CC1F1A1FF98} | 83622106 | CAMP EVERS 2106 | 10718 | 37.0361 | -122.107 | CAMP EVERS 210610718 | 162 | 159 | 25549.9185 | 13748.6879 | 11801.2306 | 13748.6879 | 11801.2306 | 0.044355 | 0.028295 | 1.8084 | 13.8 | 1087 | 0.037016 | 1920 | 0 | 0 | 8.543 | 1432 | 0
Central Valley | 2108 | 60 | 87.3134 | 1913 | 991.7095 | 103 | 3.4527e-05 | 7.4561 | 75.0849 | 611.1436 | 14746.3616 | 5872.0903 | 0.37819 | 8.8739 | 1.0172 | 0.00026316 | 0.0012696 | 0.031364 | 0.088043 | {AA9722DD-9A20-411C-A91B-FCD027C3242A} | 163661701 | MIWUK 1701 | 53038 | 38.087 | -120.1534 | MIWUK 170153038 | 143 | 426 | 22831.9294 | 10691.9033 | 12140.026 | 10691.9033 | 12140.026 | 0.13077 | 0.0035563 | 1.4552 | 18.5728 | 299 | 0.027105 | 1921 | 0 | 0 | 6.6436 | 2469 | 0
Central Coast | 6723 | 1669 | 3182.9107 | 3201 | 4076.0645 | 184 | 9.8305e-05 | 2.2622 | 5.6357 | 21.5217 | 74.4265 | 0.87871 | 1.1893 | 8.0224 | 1.0025 | 0.00026155 | 0.00032118 | 0.5214 | 0.78088 | {20C18C61-423B-413F-AE41-A93513864053} | 83252106 | PAUL SWEET 2106 | 428102 | 36.9976 | -121.9515 | PAUL SWEET 2106428102 | 256 | 356 | 41269.6868 | 20879.8446 | 20389.8422 | 19212.6145 | 16930.9581 | 0.059098 | 0.018088 | 1.9071 | 17.3967 | 1071 | 0.048126 | 1922 | 0 | 0 | 11.9382 | 608 | 0
Bay Area | 6523 | 218 | 444.6225 | 1333 | 1056.8618 | 92 | 5.3373e-05 | 7.6134 | 0.59424 | 66.8074 | 214.255 | 0.73657 | 0.8599 | 24.8434 | 1.0297 | 0.00026069 | 4.252e-05 | 0.16354 | 0.4207 | {C69D7D8E-BEEA-4B6B-B6A4-19985ED0E309} | 14091108 | CASTRO VALLEY 1108 | 10315 | 37.6517 | -121.9818 | CASTRO VALLEY 110810315 | 74 | 67 | 12973.0615 | 8831.8074 | 4141.2541 | 8831.8074 | 4141.2541 | 0.0039119 | 0.0049104 | 2.0396 | 14.4891 | 2303 | 0.023983 | 1923 | 0 | 0 | 5.4878 | 2318 | 0
Bay Area | 3207 | 41 | 110.9899 | 129 | 163.5186 | 18 | 3.7455e-05 | 5.3517 | 4.4128 | 9.2187 | 29.7653 | 0.99292 | 1.9081 | 8.1532 | 1.0305 | 0.0002597 | 0.00011147 | 0.31783 | 0.67876 | {42AA63AD-C552-4EF9-BEF2-2D7A46307F74} | 43201101 | STAFFORD 1101 | circuit_breaker | 38.1197 | -122.6142 | STAFFORD 1101circuit_breaker | 360 | 1280 | 90219.5585 | 19354.556 | 70865.0024 | 1888.1069 | 3969.3966 | 0.0020064 | 0.00067419 | 2.7071 | 7.1667 | 1790 | 0.0046746 | 1924 | 0 | 0 | 1.1732 | 1058 | 0
Central Valley | 2907 | 597 | 860.2284 | 2097 | 1571.3441 | 138 | 9.255e-05 | 3.3386 | 22.6122 | 292.4054 | 3167.782 | 196.1587 | 1.6364 | 24.4259 | 1.0707 | 0.00025459 | 0.0011543 | 0.28469 | 0.54745 | {A3304E07-DDA8-4961-A6C8-06DAE01202AE} | 163351704 | CURTIS 1704 | 803 | 38.0417 | -120.3867 | CURTIS 1704803 | 120 | 126 | 22792.508 | 15628.5101 | 7163.9979 | 15628.5101 | 7163.9979 | 0.1593 | 0.012772 | 1.4409 | 15.1957 | 341 | 0.035133 | 1925 | 0 | 0 | 9.7111 | 2208 | 0
North Coast | 7028 | 1967 | 3197.4626 | 2114 | 3264.4048 | 89 | 0.00010464 | 2.7347 | 1.596 | 135.8488 | 727.9864 | 1.5126 | 0.10543 | 11.4092 | 1.1387 | 0.00025399 | 0.0001262 | 0.93046 | 0.97949 | {BD7155EF-64EF-4144-9B75-F7FC5FD58146} | 192021122 | ARCATA 1122 | 4218 | 40.7595 | -123.9934 | ARCATA 11224218 | 43 | 29 | 12075.4887 | 8162.5664 | 3912.9223 | 7920.8951 | 3912.9223 | 0.011232 | 0.0093129 | 1.6256 | 23.7528 | 1719 | 0.022605 | 1926 | 0 | 0 | 4.9218 | 2380 | 0
Central Coast | 2063 | 361 | 1082.7081 | 997 | 1452.1431 | 125 | 4.2457e-05 | 6.8169 | 2.6043 | 9.2927 | 23.8041 | 0.26239 | 2.6541 | 33.9095 | 1.0318 | 0.00025348 | 7.2861e-05 | 0.36209 | 0.74559 | {1ED2FD17-894E-4836-A934-5237FD5BF8EA} | 182742104 | SAN BENITO 2104 | 88772 | 36.904 | -121.6087 | SAN BENITO 210488772 | 793 | 1201 | 138066.9539 | 69280.8495 | 68786.1045 | 37629.3808 | 38687.4655 | 0.0091076 | 0.0053071 | 2.9992 | 7.976 | 2038 | 0.031685 | 1927 | 0 | 0 | 23.3818 | 2647 | 0
Central Valley | 3745 | 43 | 60.8871 | 166 | 115.4651 | 41 | 2.2614e-05 | 11.0815 | 21.9071 | 190.7121 | 1581.8904 | 54.5158 | 0.16107 | 21.3782 | 1.0426 | 0.00025346 | 0.00025986 | 0.25904 | 0.52732 | {13369490-DD2C-4AB6-AA03-426047B13A3E} | 254151101 | AUBERRY 1101 | D4982 | 37.0783 | -119.3479 | AUBERRY 1101D4982 | 34 | 26 | 6659.0275 | 4312.861 | 2346.1664 | 4312.861 | 2346.1664 | 0.010654 | 0.00092718 | 1.416 | 4.0488 | 1227 | 0.010392 | 1928 | 0 | 0 | 2.6799 | 421 | 0
Central Valley | 3507 | 130 | 175.7662 | 1168 | 724.3585 | 112 | 3.353e-05 | 8.557 | 42.0589 | 968.4946 | 12005.0444 | 1052.9905 | 2.1009 | 35.0931 | 1.1517 | 0.00025082 | 0.00068495 | 0.1113 | 0.24265 | {BE967458-9C2E-4DBF-9D1D-857D10B2BFD4} | 163351703 | CURTIS 1703 | 9330 | 37.8312 | -120.2368 | CURTIS 17039330 | 461 | 478 | 101244.2805 | 66426.892 | 34817.3884 | 66426.892 | 34817.3884 | 0.076714 | 0.0037554 | 1.352 | 10.4286 | 581 | 0.028092 | 1929 | 0 | 0 | 41.2757 | 2421 | 0
Bay Area | 4938 | 221 | 469.8251 | 523 | 636.1639 | 53 | 6.2173e-05 | 3.248 | 0.91461 | 7.2222 | 16.7131 | 0.12832 | 1.8048 | 28.2443 | 0.96832 | 0.00025058 | 6.0539e-05 | 0.42256 | 0.73853 | {AC26085C-F280-4A6A-A0D9-361E1E9983F9} | 14101105 | ALHAMBRA 1105 | 81514 | 37.9871 | -122.1282 | ALHAMBRA 110581514 | 157 | 468 | 32064.0989 | 7693.8321 | 24370.2669 | 5038.5618 | 12231.5089 | 0.0032086 | 0.0032951 | 2.1259 | 9.8679 | 2134 | 0.013281 | 1930 | 0 | 0 | 3.1308 | 2111 | 0
Central Valley | 5765 | 554 | 763.4044 | 1412 | 1146.407 | 84 | 6.6262e-05 | 3.1738 | 5.7366 | 17.6403 | 46.8543 | 0.39482 | 0.5168 | 6.2732 | 1.2748 | 0.00024864 | 0.00022746 | 0.39235 | 0.66591 | {AA0F2742-8D52-435A-9889-3CD8160159B6} | 163661702 | MIWUK 1702 | 9270 | 38.0261 | -120.2543 | MIWUK 17029270 | 119 | 140 | 16690.9395 | 9423.8186 | 7267.1209 | 9423.8186 | 7267.1209 | 0.019106 | 0.005566 | 1.378 | 16.8095 | 1322 | 0.020886 | 1931 | 0 | 0 | 5.8557 | 1160 | 0
Central Valley | 3219 | 1 | 1.945 | 38 | 22.0594 | 10 | 3.7262e-05 | 5.9196 | 3.2998 | 91.461 | 613.9497 | 2.2161 | 1.6704 | 154.8347 | 1.5934 | 0.00024817 | 8.9339e-05 | 0.026316 | 0.08817 | {419BA50F-A9D8-4C0B-BAD7-EA55841BE036} | 163351703 | CURTIS 1703 | 90320 | 37.8474 | -120.2022 | CURTIS 170390320 | 448 | 1122 | 103656.3964 | 44739.8635 | 58916.5329 | 44739.8635 | 58916.5329 | 0.00089339 | 0.00037262 | 1.945 | 3.8 | 1914 | 0.0024817 | 1932 | 0 | 0 | 27.8001 | 2575 | 0
Central Coast | 1538 | 48 | 104.1568 | 141 | 150.4278 | 17 | 3.6799e-05 | 9.0641 | 2.3356 | 6.7567 | 19.831 | 0.077348 | 1.8679 | 82.9631 | 1.0593 | 0.00024698 | 7.307e-05 | 0.34043 | 0.6924 | {6095BEE0-0C36-47E1-939F-BFF38B2ABD81} | 182631101 | SAN LUIS OBISPO 1101 | 483444 | 35.2892 | -120.6524 | SAN LUIS OBISPO 1101483444 | 170 | 494 | 30709.7507 | 8577.8019 | 22131.9488 | 2987.6026 | 5496.9939 | 0.0012422 | 0.00062559 | 2.1699 | 8.2941 | 2036 | 0.0041987 | 1933 | 0 | 0 | 1.8564 | 2402 | 0
Central Coast | 986 | 3997 | 7795.5731 | 6877 | 9335.091 | 346 | 9.8496e-05 | 2.4724 | 3.3508 | 35.167 | 142.4527 | 0.95127 | 0.56334 | 14.1623 | 1.0279 | 0.00024665 | 0.00023705 | 0.58121 | 0.83508 | {EF6C4CB7-A789-4591-89F4-A27F2C5BBE61} | 83692104 | ROB ROY 2104 | 5082 | 36.9907 | -121.8064 | ROB ROY 21045082 | 321 | 286 | 51579.4437 | 33221.6065 | 18357.8372 | 32076.122 | 17153.0608 | 0.08202 | 0.03408 | 1.9504 | 19.8757 | 1288 | 0.085342 | 1934 | 0 | 0 | 19.9312 | 1976 | 0
Sierra | 1290 | 233 | 321.3267 | 421 | 414.9261 | 49 | 0.00010508 | 2.0017 | 15.7348 | 60.6102 | 603.2829 | 43.5889 | 2.2746 | 15.3721 | 1.3371 | 0.00024526 | 0.00079748 | 0.55344 | 0.77442 | {2295C6B5-DB5C-485B-935E-32BBB76DDD81} | 152431101 | SHADY GLEN 1101 | circuit_breaker | 39.1152 | -120.9537 | SHADY GLEN 1101circuit_breaker | 183 | 542 | 28751.7545 | 8826.8608 | 19924.8936 | 5163.0926 | 8268.8424 | 0.039076 | 0.0051488 | 1.3791 | 8.5918 | 501 | 0.012018 | 1935 | 0 | 0 | 3.2082 | 143 | 0
North Coast | 6067 | 178 | 328.9153 | 310 | 391.6013 | 39 | 0.00014812 | 1.2836 | 5.8274 | 53.0599 | 328.4337 | 5.8999 | 1.8009 | 10.7967 | 1.1245 | 0.00024124 | 0.00057402 | 0.57419 | 0.83992 | {774F8E82-5627-4004-BA65-1CFB3311B274} | 43081101 | BIG RIVER 1101 | 1052 | 39.3099 | -123.7938 | BIG RIVER 11011052 | 85 | 76 | 9867.4788 | 6204.7091 | 3662.7697 | 4296.6961 | 3237.1304 | 0.022387 | 0.0057767 | 1.8478 | 7.9487 | 704 | 0.0094083 | 1936 | 0 | 0 | 2.6698 | 105 | 0
Central Coast | 4653 | 87 | 168.4011 | 337 | 283.0088 | 91 | 4.3967e-05 | 6.5731 | 1.0068 | 339.8565 | 1896.0069 | 4.0256 | 1.5136 | 148.831 | 1.2403 | 0.00024089 | 4.1006e-05 | 0.25816 | 0.59504 | {762B78C6-15BB-49D8-AF4E-4B3C32E16EAE} | 182811102 | SISQUOC 1102 | M52 | 34.9255 | -120.3465 | SISQUOC 1102M52 | 143 | 68 | 66954.0693 | 57351.1566 | 9602.9127 | 54915.488 | 9571.1508 | 0.0037315 | 0.004001 | 1.9356 | 3.7033 | 2327 | 0.021921 | 1937 | 0 | 0 | 34.1229 | 1593 | 0
Central Valley | 3903 | 405 | 570.3296 | 1510 | 1075.006 | 194 | 5.9596e-05 | 4.5418 | 2.7206 | 85.8225 | 490.5196 | 4.7471 | 2.1153 | 55.5775 | 1.2225 | 0.0002404 | 9.3727e-05 | 0.26821 | 0.53054 | {E42BF1E0-70DF-4CCB-A84B-A568AFC83C89} | 162211101 | CALAVERAS CEMENT 1101 | 1419 | 38.2128 | -120.5592 | CALAVERAS CEMENT 11011419 | 153 | 124 | 35424.374 | 24046.9564 | 11377.4177 | 24046.9564 | 11377.4177 | 0.018183 | 0.011562 | 1.4082 | 7.7835 | 1886 | 0.046637 | 1938 | 0 | 0 | 14.9421 | 2574 | 0
Central Valley | 894 | 56 | 121.909 | 453 | 280.336 | 63 | 9.9956e-05 | 2.7071 | 3.3052 | 7.8418 | 23.1324 | 0.16396 | 2.3582 | 9.6706 | 1.0063 | 0.00023753 | 0.00018096 | 0.12362 | 0.43487 | {8B476FB2-9EFB-4231-AA3D-ADAA150B87C8} | 163781705 | PEORIA 1705 | 90374 | 37.9593 | -120.4019 | PEORIA 170590374 | 79 | 96 | 13098.3959 | 7135.3675 | 5963.0284 | 6578.4615 | 5919.9231 | 0.011401 | 0.0062972 | 2.1769 | 7.1905 | 1484 | 0.014965 | 1939 | 0 | 0 | 4.0877 | 1605 | 0
Bay Area | 420 | 37 | 92.9695 | 166 | 169.6088 | 11 | 3.1689e-05 | 4.3899 | 0.57291 | 0.067495 | 0.0013565 | 2.401e-06 | 0.17961 | 3.4369 | 1.0012 | 0.00023681 | 2.5524e-05 | 0.22289 | 0.54814 | {89972505-5E8F-4A2D-AA5C-D59B16608028} | 42491101 | SAUSALITO 1101 | circuit_breaker | 37.8635 | -122.4986 | SAUSALITO 1101circuit_breaker | 299 | 841 | 37940.5679 | 9339.6058 | 28600.9621 | 1238.4516 | 2959.4765 | 0.00028076 | 0.00034858 | 2.5127 | 15.0909 | 2528 | 0.002605 | 1940 | 0 | 0 | 0.76954 | 2860 | 0
Central Valley | 8753 | 46 | 64.1832 | 139 | 114.1128 | 8 | 6.5668e-05 | 3.039 | 21.702 | 52.9047 | 248.8358 | 8.1778 | 0.77129 | 10.3778 | 1.0022 | 0.00023539 | 0.0006212 | 0.33094 | 0.56245 | {5E0E9C3F-102B-4736-867B-523AEBC69611} | 163661702 | MIWUK 1702 | 36888 | 38.0286 | -120.2516 | MIWUK 170236888 | 21 | 8 | 1302.2065 | 990.9397 | 311.2667 | 990.9397 | 311.2667 | 0.0049696 | 0.00052534 | 1.3953 | 17.375 | 649 | 0.0018831 | 1941 | 0 | 0 | 0.61574 | 2323 | 0
North Coast | 2968 | 3393 | 5396.4147 | 3794 | 5599.3687 | 368 | 6.6159e-05 | 3.8316 | 3.9723 | 122.3677 | 558.0082 | 2.7793 | 1.0256 | 34.574 | 1.0771 | 0.00023444 | 0.00015671 | 0.89431 | 0.96375 | {EADE9BC7-FA33-4E78-987B-E6772CEF7A88} | 42601102 | PHILO 1102 | 1308 | 39.1863 | -123.5804 | PHILO 11021308 | 310 | 276 | 82076.1543 | 51499.148 | 30577.0062 | 51499.148 | 30577.0062 | 0.057668 | 0.024346 | 1.5905 | 10.3098 | 1558 | 0.086273 | 1942 | 0 | 0 | 32.0001 | 1309 | 0
Central Valley | 4093 | 2 | 2.7172 | 526 | 241.8686 | 63 | 1.5731e-05 | 14.4101 | 9.8006 | 154.544 | 2504.1998 | 89.581 | 0.34629 | 12.037 | 1.0075 | 0.0002325 | 7.5449e-05 | 0.0038023 | 0.011234 | {A2735C5A-AC0C-48E2-9CB7-2F6A791B6D33} | 162831702 |  | 10720 | 38.1994 | -120.0206 | 10720 | 37 | 122 | 11582.144 | 7647.7028 | 3934.4412 | 7647.7028 | 3934.4412 | 0.0047533 | 0.00099107 | 1.3586 | 8.3492 | 2015 | 0.014648 | 1943 | 0 | 0 | 4.7521 | 2714 | 0
North Coast | 8028 | 518 | 968.3855 | 1043 | 1208.5682 | 62 | 8.6259e-05 | 2.7606 | 4.6721 | 84.6828 | 225.1647 | 1.6966 | 0.76966 | 23.5578 | 1.0227 | 0.0002325 | 0.00023978 | 0.49664 | 0.80127 | {3A3BBF86-310F-432E-A06D-A8536237FB4D} | 192151131 | NEWBURG 1131 | 90242 | 40.5703 | -124.1254 | NEWBURG 113190242 | 75 | 106 | 13221.9215 | 7015.9838 | 6205.9377 | 5381.5662 | 2871.4966 | 0.014866 | 0.005348 | 1.8695 | 16.8226 | 1279 | 0.014415 | 1944 | 0 | 0 | 3.3439 | 2335 | 0
Central Coast | 5123 | 398 | 792.0395 | 649 | 947.498 | 33 | 0.00015167 | 1.5077 | 4.7107 | 11.2187 | 43.4554 | 0.38878 | 0.29264 | 3.8534 | 1.0004 | 0.00023226 | 0.00034009 | 0.61325 | 0.83593 | {CD17E58D-2AE5-429A-8116-FD0D2E9FA263} | 82841101 | BIG BASIN 1101 | 5000 | 37.1028 | -122.1413 | BIG BASIN 11015000 | 47 | 61 | 6943.3772 | 3211.5435 | 3731.8337 | 3211.5435 | 3731.8337 | 0.011223 | 0.0050052 | 1.99 | 19.6667 | 1029 | 0.0076645 | 1945 | 0 | 0 | 1.9956 | 2158 | 0
Bay Area | 1147 | 234 | 334.5255 | 894 | 696.4838 | 49 | 0.00012125 | 1.523 | 0.23908 | 1.1601 | 4.0865 | 0.064886 | 0.12516 | 1.957 | 0.74923 | 0.00023144 | 7.8797e-05 | 0.26174 | 0.48031 | {C15D2B27-11D0-43EC-9B15-374D2297640F} | 42011108 | SAN RAFAEL 1108 | 1210 | 37.9627 | -122.569 | SAN RAFAEL 11081210 | 175 | 590 | 34929.1817 | 8753.0145 | 26176.1672 | 5233.0326 | 13185.556 | 0.003861 | 0.0059415 | 1.4296 | 18.2449 | 1993 | 0.01134 | 1946 | 0 | 0 | 3.2517 | 2643 | 0
Bay Area | 6077 | 840 | 1991.3553 | 1828 | 2580.8577 | 66 | 6.4492e-05 | 3.3033 | 5.4246 | 52.8818 | 760.9522 | 7.7491 | 0.3267 | 1.5968 | 1.2436 | 0.00023006 | 0.00020444 | 0.45952 | 0.77159 | {46D411EC-386C-4DB1-B30F-D2D2AC060A49} | 42291101 | OLEMA 1101 | 1252 | 38.0779 | -122.8329 | OLEMA 11011252 | 89 | 122 | 12444.4488 | 6562.8215 | 5881.6272 | 6562.8215 | 5881.6272 | 0.013493 | 0.0042565 | 2.3707 | 27.697 | 1398 | 0.015184 | 1947 | 0 | 0 | 4.0779 | 2417 | 0
Central Valley | 8427 | 1 | 3.8265 | 74 | 36.099 | 7 | 9.4846e-06 | 30.641 | 0.72819 | 1188.3613 | 34404.8827 | 66.0272 | 0.018331 | 13.8163 | 1.0066 | 0.0002296 | 8.3208e-06 | 0.013514 | 0.106 | {17340C5D-4E9A-414F-A76B-922497EBB75D} | 162831702 |  | 86032 | 38.1849 | -119.9915 | 86032 | 34 | 15 | 4952.4347 | 4656.0497 | 296.385 | 1615.684 | 203.3681 | 5.8245e-05 | 6.6392e-05 | 3.8265 | 10.5714 | 2807 | 0.0016072 | 1948 | 0 | 0 | 1.0039 | 654 | 0
Bay Area | 7045 | 450 | 1429.6209 | 1140 | 1718.0339 | 111 | 4.9321e-05 | 5.3475 | 5.2096 | 106.3688 | 483.7449 | 9.0871 | 1.1124 | 67.3415 | 1.1348 | 0.00022846 | 0.00015021 | 0.39474 | 0.83213 | {C41F4E5E-7BB3-4EF6-9D85-B639632114A4} | 24101101 | HALF MOON BAY 1101 | 8902 | 37.4745 | -122.4166 | HALF MOON BAY 11018902 | 199 | 160 | 41004.9967 | 30497.3428 | 10507.6539 | 21140.1681 | 7110.5983 | 0.016673 | 0.0054746 | 3.1769 | 10.2703 | 1590 | 0.025359 | 1949 | 0 | 0 | 13.1359 | 2172 | 0
Central Valley | 6538 | 32 | 43.0902 | 127 | 95.2809 | 33 | 9.1435e-06 | 30.1063 | 12.9633 | 463.1477 | 2730.7199 | 55.35 | 2.6054 | 103.5843 | 1.0489 | 0.00022823 | 5.4382e-05 | 0.25197 | 0.45224 | {85C573CB-6CAC-4BD3-9BAE-88F4FB8F62BB} | 252691104 | INDIAN FLAT 1104 | 10270 | 37.6973 | -119.7607 | INDIAN FLAT 110410270 | 57 | 64 | 12058.9196 | 6119.8904 | 5939.0292 | 6119.8904 | 5939.0292 | 0.0017946 | 0.00030173 | 1.3466 | 3.8485 | 2200 | 0.0075315 | 1950 | 0 | 0 | 3.8027 | 2346 | 0
Sierra | 455 | 1772 | 2215.2197 | 3443 | 3138.1694 | 298 | 8.1375e-05 | 3.0537 | 22.2202 | 204.6751 | 2641.0351 | 253.0364 | 2.4805 | 33.0345 | 1.1017 | 0.00022815 | 0.00088737 | 0.51467 | 0.7059 | {1AAC91CD-F390-4834-9229-DA9482F10795} | 152491101 | WEIMAR 1101 | 2084 | 39.0318 | -120.9741 | WEIMAR 11012084 | 335 | 339 | 49412.7367 | 29727.9123 | 19684.8245 | 29727.9123 | 19684.8245 | 0.26444 | 0.02425 | 1.2501 | 11.5537 | 454 | 0.06799 | 1951 | 0 | 0 | 18.4721 | 642 | 0
Central Valley | 4997 | 167 | 281.171 | 1086 | 591.1724 | 212 | 4.3832e-05 | 4.8601 | 5.1237 | 518.8084 | 3931.6508 | 41.5481 | 3.3981 | 203.4812 | 1.3353 | 0.00022785 | 0.00010896 | 0.15378 | 0.47562 | {765E2074-110B-4FD6-8019-AD09D7431DAB} | 162211101 | CALAVERAS CEMENT 1101 | 11236 | 38.1697 | -120.6677 | CALAVERAS CEMENT 110111236 | 161 | 117 | 44070.9262 | 31569.3587 | 12501.5675 | 31569.3587 | 12501.5675 | 0.0231 | 0.0092924 | 1.6837 | 5.1226 | 1808 | 0.048303 | 1952 | 0 | 0 | 19.6163 | 1558 | 0
Bay Area | 5710 | 46 | 102.7719 | 214 | 202.1094 | 22 | 4.2281e-05 | 6.5496 | 0.84539 | 1.2515 | 3.9217 | 0.017347 | 0.63496 | 4.1544 | 1.0019 | 0.00022735 | 4.0344e-05 | 0.21495 | 0.5085 | {A7850717-18DF-4BF5-B934-11A86FF92EB5} | 13801103 | MORAGA 1103 | circuit_breaker | 37.8488 | -122.1615 | MORAGA 1103circuit_breaker | 174 | 837 | 49475.0274 | 10266.3997 | 39208.6278 | 1860.265 | 6615.948 | 0.00088756 | 0.00093018 | 2.2342 | 9.7273 | 2335 | 0.0050018 | 1953 | 0 | 0 | 1.1559 | 1918 | 0
Bay Area | 1046 | 300 | 786.6368 | 1081 | 1204.0104 | 70 | 4.0972e-05 | 3.1223 | 0.90523 | 1.4308 | 10.0102 | 0.58874 | 0.47835 | 0.75875 | 0.60259 | 0.00022689 | 5.4084e-05 | 0.27752 | 0.65335 | {68422AE1-2121-4A4F-B961-26CF0C3DA27B} | 42031125 | ALTO 1125 | 1256 | 37.8866 | -122.5368 | ALTO 11251256 | 123 | 520 | 31860.8874 | 7051.2781 | 24809.6093 | 6410.4568 | 22052.0856 | 0.0037859 | 0.002868 | 2.6221 | 15.4429 | 2202 | 0.015882 | 1954 | 0 | 0 | 3.9833 | 2703 | 0
Central Coast | 875 | 61 | 131.9719 | 173 | 195.4945 | 30 | 3.7387e-05 | 6.4044 | 8.9172 | 23.3264 | 89.6782 | 3.2938 | 3.0347 | 8.1149 | 1.1566 | 0.0002254 | 0.00022596 | 0.3526 | 0.67507 | {FFDFCD62-3D83-4DB1-8291-20A4384347C8} | 183052108 | TEMPLETON 2108 | A64 | 35.5233 | -120.6936 | TEMPLETON 2108A64 | 288 | 351 | 35505.8137 | 19026.8995 | 16478.9142 | 3063.2438 | 3911.7888 | 0.0067787 | 0.0011216 | 2.1635 | 5.7667 | 1325 | 0.0067619 | 1955 | 0 | 0 | 1.9034 | 1739 | 0
Central Valley | 6047 | 158 | 330.1034 | 760 | 591.3936 | 65 | 0.00010991 | 2.2604 | 5.7726 | 20.8405 | 126.9342 | 2.6602 | 1.452 | 7.8214 | 1.0046 | 0.00022531 | 0.00033622 | 0.20789 | 0.55818 | {08C43BB5-02C4-4FB7-9500-39371503D9F3} | 163781705 | PEORIA 1705 | 87222 | 37.9608 | -120.4061 | PEORIA 170587222 | 115 | 224 | 18660.1903 | 8479.914 | 10180.2764 | 8240.0572 | 10111.1171 | 0.021855 | 0.0071444 | 2.0893 | 11.6923 | 1039 | 0.014645 | 1956 | 0 | 0 | 5.1201 | 1151 | 0
Central Coast | 3012 | 798 | 1512.3885 | 2132 | 2246.546 | 151 | 0.00021421 | 1.0113 | 5.0614 | 11.7928 | 64.547 | 1.3561 | 0.38567 | 2.8441 | 0.99577 | 0.00022487 | 0.00059242 | 0.3743 | 0.67321 | {61BEE218-5ECD-4073-AA08-F1DB60558A8D} | 83622105 | CAMP EVERS 2105 | 10728 | 37.0665 | -122.0797 | CAMP EVERS 210510728 | 273 | 1013 | 65013.8357 | 16827.1381 | 48186.6976 | 16827.1381 | 48186.6976 | 0.089455 | 0.032346 | 1.8952 | 14.1192 | 678 | 0.033956 | 1957 | 0 | 0 | 10.4559 | 968 | 0
North Coast | 4596 | 674 | 1175.3089 | 857 | 1261.0901 | 67 | 8.3596e-05 | 2.5486 | 3.3176 | 40.7449 | 221.2824 | 1.0235 | 0.26907 | 7.5691 | 1.0606 | 0.00022455 | 0.00018226 | 0.78646 | 0.93198 | {A53E45F3-3435-4AAC-A0E8-0F3C42F17E7B} | 42981101 | ELK 1101 | 8779 | 39.2234 | -123.7339 | ELK 11018779 | 52 | 45 | 15071.2918 | 6865.4129 | 8205.8789 | 6865.4129 | 8205.8789 | 0.012212 | 0.0056009 | 1.7438 | 12.791 | 1476 | 0.015045 | 1958 | 0 | 0 | 4.266 | 1590 | 0
Sierra | 4002 | 134 | 182.3353 | 1322 | 681.8174 | 179 | 9.5704e-06 | 21.7364 | 0.57754 | 50.9333 | 493.8052 | 0.64402 | 0.5605 | 24.1121 | 1.0547 | 0.00022235 | 8.0795e-06 | 0.10136 | 0.26743 | {4B4ECB86-924B-4487-850F-9E73F5ADEBBF} | 152251101 | SPAULDING 1101 | 578852 | 39.3251 | -120.6428 | SPAULDING 1101578852 | 247 | 201 | 47186.8935 | 39043.058 | 8143.8355 | 33138.4596 | 6516.192 | 0.0014462 | 0.0017131 | 1.3607 | 7.3855 | 2810 | 0.0398 | 1959 | 0 | 0 | 20.5913 | 2084 | 0
Central Coast | 8152 | 309 | 498.3118 | 608 | 653.2951 | 24 | 6.6874e-05 | 3.039 | 0.22128 | 21.8645 | 115.9597 | 0.033708 | 0.19091 | 12.3023 | 1.0842 | 0.00021964 | 3.6468e-05 | 0.50822 | 0.76277 | {208B7AA1-3DC7-4A8B-92C8-2F0419B8F695} | 83242111 | MORGAN HILL 2111 | 4461 | 37.0838 | -121.7754 | MORGAN HILL 21114461 | 35 | 85 | 6953.9073 | 3633.9489 | 3319.9584 | 3633.9489 | 3319.9584 | 0.00087523 | 0.001605 | 1.6127 | 25.3333 | 2381 | 0.0052714 | 1960 | 0 | 0 | 2.258 | 2212 | 0
Sierra | 2492 | 461 | 665.9465 | 1184 | 1002.0984 | 135 | 0.00011765 | 2.5283 | 15.6225 | 249.3777 | 3067.8001 | 197.7532 | 3.2228 | 30.4221 | 1.2865 | 0.00021958 | 0.00067723 | 0.38936 | 0.66455 | {A298B0D8-C9B9-4411-92EE-D00915B8BD24} | 152481110 | BRUNSWICK 1110 | 61602 | 39.2254 | -121.0789 | BRUNSWICK 111061602 | 370 | 802 | 55740.795 | 20441.2599 | 35299.5352 | 14421.8376 | 20948.9054 | 0.091425 | 0.015883 | 1.4446 | 8.7704 | 590 | 0.029644 | 1961 | 0 | 0 | 8.9613 | 985 | 0
Central Coast | 1189 | 1037 | 1776.2855 | 2397 | 2603.1697 | 97 | 7.356e-05 | 3.2516 | 10.2745 | 40.1278 | 366.5724 | 7.4988 | 0.52929 | 6.4535 | 1.0007 | 0.00021753 | 0.00039792 | 0.43262 | 0.68235 | {45408D73-5C26-471E-9488-9F6B0D601D29} | 83692105 | ROB ROY 2105 | 5166 | 36.9818 | -121.901 | ROB ROY 21055166 | 177 | 281 | 22536.5679 | 8833.6807 | 13702.8872 | 8833.6807 | 13702.8872 | 0.038598 | 0.0071353 | 1.7129 | 24.7113 | 946 | 0.0211 | 1962 | 0 | 0 | 5.489 | 2304 | 0
Central Coast | 58 | 27 | 88.892 | 200 | 152.3612 | 6 | 2.5777e-05 | 15.9191 | 29.5558 | 78.2829 | 407.6203 | 36.1034 | 1.7083 | 15.155 | 1.028 | 0.00021706 | 0.00017502 | 0.135 | 0.58343 | {98891E8E-A196-4377-815F-B850671211F6} | 182771102 | CAMBRIA 1102 | W50 | 35.567 | -121.1052 | CAMBRIA 1102W50 | 105 | 637 | 31711.7627 | 5728.406 | 25983.3567 | 779.9345 | 1576.7096 | 0.0010501 | 0.00015466 | 3.2923 | 33.3333 | 1504 | 0.0013024 | 1963 | 0 | 0 | 0.48463 | 1636 | 0
North Coast | 572 | 644 | 1066.9993 | 880 | 1194.4822 | 76 | 0.0001503 | 1.3189 | 5.2266 | 49.7639 | 327.448 | 4.1213 | 0.64404 | 16.0653 | 0.9899 | 0.00021535 | 0.00041591 | 0.73182 | 0.89327 | {928C2523-6FDC-42B7-8EE9-33FA426DCF79} | 42811111 | MONTE RIO 1111 | 23916 | 38.49 | -123.0599 | MONTE RIO 111123916 | 111 | 205 | 21104.3687 | 8839.5506 | 12264.8181 | 8839.5506 | 12264.8181 | 0.031609 | 0.011423 | 1.6568 | 11.5789 | 916 | 0.016366 | 1964 | 0 | 0 | 5.4926 | 2875 | 0
North Coast | 438 | 225 | 355.1839 | 524 | 514.006 | 52 | 0.00016012 | 1.4382 | 2.3323 | 6.1624 | 19.8196 | 0.1386 | 0.43282 | 3.3361 | 0.98115 | 0.00021528 | 0.00029486 | 0.42939 | 0.69101 | {78AB2FDD-E1CA-4DC9-8362-0759A43BD212} | 42811112 | MONTE RIO 1112 | circuit_breaker | 38.4712 | -123.0121 | MONTE RIO 1112circuit_breaker | 104 | 455 | 23206.52 | 5973.9084 | 17232.6116 | 5973.9084 | 17232.6116 | 0.015333 | 0.0083261 | 1.5786 | 10.0769 | 1137 | 0.011195 | 1965 | 0 | 0 | 3.712 | 208 | 0
Central Valley | 7490 | 18 | 30.1379 | 53 | 43.4293 | 23 | 3.5402e-05 | 9.3818 | 2.1339 | 1067.2781 | 6633.9427 | 23.0511 | 3.4418 | 426.8989 | 1.3699 | 0.0002137 | 4.3491e-05 | 0.33962 | 0.69395 | {2FC56DAF-3BEA-4D4D-AF4F-08FDD13FFBA2} | 163781704 | PEORIA 1704 | 877670 | 37.9037 | -120.5087 | PEORIA 1704877670 | 41 | 16 | 11182.6139 | 10595.2996 | 587.3143 | 10595.2996 | 587.3143 | 0.0010003 | 0.00081424 | 1.6743 | 2.3043 | 2296 | 0.004915 | 1966 | 0 | 0 | 6.5836 | 323 | 0
Central Valley | 2991 | 100 | 146.8638 | 724 | 428.0714 | 145 | 2.6147e-05 | 7.9358 | 8.1077 | 84.8555 | 617.8466 | 12.0627 | 0.70636 | 17.4743 | 1.0434 | 0.00021346 | 0.0001215 | 0.13812 | 0.34308 | {CF478BAD-B068-4DDA-83F7-95633906AC62} | 254151101 | AUBERRY 1101 | R324 | 37.0552 | -119.3699 | AUBERRY 1101R324 | 177 | 126 | 24817.7055 | 17331.696 | 7486.0095 | 17331.696 | 7486.0095 | 0.017617 | 0.0037913 | 1.4686 | 4.9931 | 1743 | 0.030952 | 1967 | 0 | 0 | 10.7694 | 2026 | 0
Central Coast | 951 | 169 | 256.691 | 938 | 735.2101 | 77 | 6.166e-05 | 6.045 | 0.45305 | 50.8177 | 240.3165 | 0.42569 | 0.55117 | 34.086 | 1.0554 | 0.00021187 | 4.2127e-05 | 0.18017 | 0.34914 | {80B87962-AD85-4936-A71D-968069A54623} | 182551102 | CAYUCOS 1102 | circuit_breaker | 35.4488 | -120.8708 | CAYUCOS 1102circuit_breaker | 230 | 307 | 66910.3029 | 46289.4977 | 20620.8052 | 20474.7402 | 5336.0325 | 0.0032438 | 0.0047478 | 1.5189 | 12.1818 | 2306 | 0.016314 | 1968 | 0 | 0 | 12.7224 | 1769 | 0
Sierra | 3406 | 786 | 1117.3372 | 2182 | 1849.9077 | 183 | 0.00010878 | 2.1512 | 25.0981 | 284.9238 | 3549.1907 | 251.2068 | 2.33 | 20.3896 | 1.0459 | 0.00021115 | 0.0012622 | 0.36022 | 0.604 | {15B21A5E-7758-402F-AB04-357FA8BC8C24} | 152031101 | GRASS VALLEY 1101 | 2208 | 39.1988 | -121.0634 | GRASS VALLEY 11012208 | 270 | 280 | 37691.518 | 20526.1791 | 17165.3389 | 18884.1728 | 15307.3667 | 0.23098 | 0.019906 | 1.4215 | 11.9235 | 301 | 0.038641 | 1969 | 0 | 0 | 11.7341 | 622 | 0
Central Coast | 6585 | 761 | 1303.3729 | 1708 | 1882.3978 | 95 | 8.5133e-05 | 2.318 | 4.0321 | 21.0792 | 82.7573 | 0.53895 | 0.63204 | 5.9279 | 1.0036 | 0.00020897 | 0.00021064 | 0.44555 | 0.6924 | {4EF4529F-4E08-426D-A25B-A1F6BCFED593} | 83500401 | SEACLIFF 0401 | circuit_breaker | 36.9842 | -121.9155 | SEACLIFF 0401circuit_breaker | 113 | 125 | 17488.9606 | 9677.833 | 7811.1276 | 9172.6769 | 7730.9606 | 0.02001 | 0.0080877 | 1.7127 | 17.9789 | 1378 | 0.019852 | 1970 | 0 | 0 | 5.6996 | 1926 | 0
Bay Area | 2191 | 62 | 111.2494 | 176 | 174.6235 | 24 | 3.2101e-05 | 6.9836 | 1.6162 | 3.4025 | 13.7937 | 0.21131 | 0.87737 | 7.4394 | 2.1724 | 0.00020744 | 6.2223e-05 | 0.35227 | 0.63708 | {2723FD74-E215-4B66-BA9E-051AE21C4595} | 42481101 | IGNACIO 1101 | 1264 | 38.0748 | -122.5654 | IGNACIO 11011264 | 120 | 541 | 32774.7125 | 5420.1776 | 27354.5349 | 3308.6659 | 15170.3432 | 0.0014933 | 0.00077042 | 1.7943 | 7.3333 | 2115 | 0.0049785 | 1971 | 0 | 0 | 2.0559 | 1271 | 0
North Coast | 1475 | 612 | 947.3109 | 1111 | 1162.756 | 109 | 6.0132e-05 | 4.2085 | 1.3892 | 43.4298 | 261.1532 | 0.67843 | 0.41541 | 8.7854 | 1.0697 | 0.00020743 | 7.1589e-05 | 0.55086 | 0.81471 | {CE95A09E-74FB-479F-845B-A7A77A530903} | 192341102 | HUMBOLDT BAY 1102 | 4724 | 40.7546 | -124.1875 | HUMBOLDT BAY 11024724 | 230 | 462 | 51442.125 | 24851.4009 | 26590.7241 | 10436.2695 | 8877.6229 | 0.0078032 | 0.0065544 | 1.5479 | 10.1927 | 2042 | 0.02261 | 1972 | 0 | 0 | 6.4848 | 45 | 0
North Coast | 6880 | 1735 | 3032.6773 | 2009 | 3165.4128 | 148 | 9.4104e-05 | 2.6328 | 1.8749 | 28.0014 | 150.8017 | 0.47454 | 0.19505 | 7.0199 | 1.1903 | 0.00020633 | 0.00013456 | 0.86361 | 0.95807 | {B18E180C-39A4-4EFB-8DCB-B1B629947F6E} | 43081101 | BIG RIVER 1101 | 69032 | 39.2995 | -123.789 | BIG RIVER 110169032 | 141 | 141 | 18347.6236 | 13621.9318 | 4725.6918 | 13621.9318 | 4725.6918 | 0.019915 | 0.013927 | 1.7479 | 13.5743 | 1671 | 0.030536 | 1973 | 0 | 0 | 8.4643 | 97 | 0
Central Coast | 4193 | 102 | 175.6929 | 343 | 309.6076 | 23 | 9.3095e-05 | 2.1331 | 1.5223 | 2.0316 | 3.7804 | 0.028381 | 0.42237 | 4.0367 | 1.0012 | 0.00020526 | 0.00012327 | 0.29738 | 0.56747 | {C4E0B9E0-CB11-4C51-9BF2-0A1F8C067741} | 83622103 | CAMP EVERS 2103 | 11056 | 36.9937 | -122.0299 | CAMP EVERS 210311056 | 49 | 114 | 8082.4332 | 2992.2228 | 5090.2103 | 2611.1508 | 3987.5529 | 0.0028352 | 0.0021412 | 1.7225 | 14.913 | 1735 | 0.0047209 | 1974 | 0 | 0 | 1.6225 | 2401 | 0
Bay Area | 1126 | 53 | 122.9885 | 163 | 188.2134 | 16 | 3.9565e-05 | 6.0187 | 17.7357 | 74.5208 | 223.3212 | 7.9395 | 2.8059 | 18.3717 | 1.0376 | 0.00020498 | 0.00055803 | 0.32515 | 0.65345 | {FF138367-96EF-4586-B73C-AE42FDD878F0} | 43201101 | STAFFORD 1101 | 1082 | 38.1102 | -122.6132 | STAFFORD 11011082 | 56 | 417 | 25826.4016 | 4959.0869 | 20867.3147 | 1691.5237 | 4461.243 | 0.0089284 | 0.00063304 | 2.3205 | 10.1875 | 726 | 0.0032797 | 1975 | 0 | 0 | 1.0511 | 159 | 0
Central Coast | 2837 | 6 | 12.2609 | 116 | 68.0455 | 10 | 2.6005e-05 | 11.9763 | 0.35795 | 41.2532 | 192.6938 | 0.80393 | 0.44049 | 17.4266 | 1.023 | 0.00020405 | 2.2655e-05 | 0.051724 | 0.18019 | {7C9F6E98-6AD1-45C0-AA12-C5A39FC092A4} | 182951102 | FOOTHILL 1102 | 99432 | 35.2603 | -120.6947 | FOOTHILL 110299432 | 290 | 865 | 53260.2196 | 14110.2866 | 39149.933 | 2389.4026 | 660.5738 | 0.00022655 | 0.00026005 | 2.0435 | 11.6 | 2571 | 0.0020405 | 1976 | 0 | 0 | 1.4847 | 338 | 0
Sierra | 9699 | 11 | 21.3948 | 60 | 42.7125 | 9 | 6.7948e-05 | 2.7801 | 13.1404 | 138.4714 | 744.9574 | 23.4115 | 3.03 | 88.1254 | 1.3218 | 0.00020355 | 0.00045133 | 0.18333 | 0.5009 | {7331B61B-2EF4-4C3D-921E-59545C577918} | 152271101 | WISE 1101 | 63199 | 38.8837 | -121.1021 | WISE 110163199 | 12 | 17 | 2188.5536 | 1501.4082 | 687.1454 | 989.41 | 219.6024 | 0.0040619 | 0.00061153 | 1.945 | 6.6667 | 860 | 0.001832 | 1977 | 0 | 0 | 0.61479 | 1084 | 0
Central Valley | 621 | 90 | 129.333 | 251 | 200.3073 | 21 | 0.00011895 | 2.3299 | 11.2246 | 61.6018 | 767.9002 | 28.8046 | 2.2611 | 6.6857 | 1.1185 | 0.00020307 | 0.00060421 | 0.35857 | 0.64567 | {2C817939-22E6-4D0A-962C-2F9F458E8593} | 163761703 | RACETRACK 1703 | 10870 | 37.9807 | -120.3916 | RACETRACK 170310870 | 71 | 143 | 12386.6003 | 4188.8092 | 8197.7911 | 3188.0176 | 6978.9043 | 0.012688 | 0.0024979 | 1.437 | 11.9524 | 665 | 0.0042644 | 1978 | 0 | 0 | 1.9809 | 1492 | 0
Central Coast | 6971 | 875 | 1579.5272 | 1702 | 2073.8782 | 123 | 7.9274e-05 | 2.1931 | 3.7116 | 29.887 | 152.3713 | 0.93718 | 2.4346 | 23.3493 | 1.0571 | 0.00020254 | 0.00019124 | 0.5141 | 0.76163 | {0FCDB678-0B45-409C-87BF-C304E827F93C} | 82021107 | LOS GATOS 1107 | 2917 | 37.1092 | -121.9355 | LOS GATOS 11072917 | 123 | 140 | 22132.7664 | 12406.0821 | 9726.6844 | 12406.0821 | 9726.6844 | 0.023522 | 0.0097507 | 1.8052 | 13.8374 | 1447 | 0.024912 | 1979 | 0 | 0 | 7.7088 | 1586 | 0
Bay Area | 1761 | 216 | 505.0491 | 669 | 760.241 | 53 | 6.3688e-05 | 4.1037 | 4.2371 | 9.163 | 27.0438 | 0.78752 | 1.7172 | 5.9245 | 0.99436 | 0.00019906 | 0.00021679 | 0.32287 | 0.66433 | {882C20B1-4F53-4E74-914C-118DECC8B0F8} | 13801102 | MORAGA 1102 | circuit_breaker | 37.8491 | -122.1619 | MORAGA 1102circuit_breaker | 221 | 693 | 51629.0242 | 14952.4679 | 36676.5563 | 8031.17 | 20413.7385 | 0.01149 | 0.0033755 | 2.3382 | 12.6226 | 1354 | 0.01055 | 1980 | 0 | 0 | 4.9903 | 1062 | 0
Bay Area | 1124 | 508 | 1285.6882 | 1482 | 1831.3882 | 54 | 5.3843e-05 | 3.5844 | 22.4032 | 743.5846 | 14646.0686 | 693.1668 | 0.49492 | 1.8635 | 1.2232 | 0.00019762 | 0.00068507 | 0.34278 | 0.70203 | {A8B14B0D-3BCA-44F1-B75C-F9F858D43D86} | 42291101 | OLEMA 1101 | 1200 | 38.0971 | -122.8526 | OLEMA 11011200 | 69 | 301 | 19942.9854 | 4658.8808 | 15284.1046 | 4658.8808 | 15284.1046 | 0.036994 | 0.0029075 | 2.5309 | 27.4444 | 580 | 0.010671 | 1981 | 0 | 0 | 2.8949 | 353 | 0
North Coast | 2853 | 343 | 677.2616 | 440 | 728.1863 | 33 | 0.00014684 | 1.5087 | 5.1397 | 61.6136 | 414.4067 | 2.9086 | 0.70354 | 11.5148 | 1.0116 | 0.00019621 | 0.00045183 | 0.77955 | 0.93007 | {9DEA7C0C-988A-45A0-A22A-FD3B61FBF719} | 42811111 | MONTE RIO 1111 | 53477 | 38.4961 | -123.0693 | MONTE RIO 111153477 | 28 | 81 | 8409.6407 | 3299.3477 | 5110.293 | 3299.3477 | 5110.293 | 0.01491 | 0.0048457 | 1.9745 | 13.3333 | 857 | 0.006475 | 1982 | 0 | 0 | 2.0501 | 2861 | 0
Bay Area | 2691 | 159 | 297.3989 | 522 | 509.9078 | 43 | 5.4118e-05 | 4.5353 | 10.6301 | 11.8697 | 31.3255 | 0.68923 | 1.1742 | 17.9493 | 1.8943 | 0.00019481 | 0.00027966 | 0.3046 | 0.58324 | {AEA0E426-7AE2-48C6-9626-CB9218FF1143} | 14161108 | ROSSMOOR 1108 | 45268 | 37.8465 | -122.1101 | ROSSMOOR 110845268 | 270 | 495 | 38033.654 | 12359.2232 | 25674.4308 | 4023.0288 | 5183.5022 | 0.012026 | 0.0023271 | 1.8704 | 12.1395 | 1178 | 0.008377 | 1983 | 0 | 0 | 2.4998 | 2305 | 0
Central Valley | 3784 | 5 | 7.6119 | 21 | 14.2181 | 7 | 7.5796e-05 | 3.7974 | 6.125 | 19.3244 | 91.6481 | 1.1808 | 2.6738 | 65.0512 | 1.0367 | 0.00019061 | 0.00037968 | 0.2381 | 0.53537 | {C5570B1A-B071-4827-88D1-68633BB92AFE} | 162991102 | CORRAL 1102 | 75622 | 38.1582 | -120.8455 | CORRAL 110275622 | 136 | 337 | 25226.9871 | 9209.8908 | 16017.0963 | 1424.9314 | 2191.9856 | 0.0026578 | 0.00053057 | 1.5224 | 3 | 969 | 0.0013343 | 1984 | 0 | 0 | 0.88541 | 1888 | 0
Sierra | 3648 | 1171 | 1666.197 | 2141 | 2146.1294 | 190 | 0.00010303 | 1.696 | 7.6079 | 32.7937 | 223.4216 | 4.852 | 2.1433 | 17.5425 | 1.0072 | 0.0001846 | 0.00042186 | 0.54694 | 0.77637 | {576CF59E-86D2-4E41-A7A3-27CEB8B77F40} | 152491102 | WEIMAR 1102 | circuit_breaker | 39.036 | -120.9879 | WEIMAR 1102circuit_breaker | 268 | 330 | 37732.9815 | 19516.5086 | 18216.473 | 19516.5086 | 18216.473 | 0.080153 | 0.019575 | 1.4229 | 11.2684 | 907 | 0.035075 | 1985 | 0 | 0 | 12.127 | 489 | 0
North Valley | 1392 | 1695 | 2104.2735 | 4453 | 3251.601 | 259 | 0.00011623 | 2.8203 | 16.4636 | 37.4426 | 487.2425 | 55.8251 | 0.30721 | 4.6035 | 0.94507 | 0.00018425 | 0.0008405 | 0.38064 | 0.64715 | {81205B01-8688-4570-8F47-B08F18EDCF16} | 103031101 | ORO FINO 1101 | 2022 | 39.8542 | -121.6059 | ORO FINO 11012022 | 395 | 1163 | 83825.4014 | 27985.9982 | 55839.4032 | 27985.9982 | 55839.4032 | 0.21769 | 0.030103 | 1.2415 | 17.1931 | 477 | 0.04772 | 1986 | 0 | 0 | 17.3897 | 1228 | 0
North Coast | 2706 | 134 | 253.9346 | 284 | 320.7858 | 43 | 5.9904e-05 | 3.2746 | 4.1625 | 230.0337 | 909.2048 | 6.6654 | 1.208 | 84.3947 | 1.1043 | 0.00018395 | 0.00017282 | 0.47183 | 0.7916 | {32CDF0E8-BDA5-4E37-8B42-CD1492E2A580} | 42981101 | ELK 1101 | 900 | 39.0468 | -123.685 | ELK 1101900 | 262 | 226 | 48739.9082 | 33079.2876 | 15660.6206 | 9529.0573 | 2869.2154 | 0.0074313 | 0.0025759 | 1.895 | 6.6047 | 1515 | 0.00791 | 1987 | 0 | 0 | 5.9211 | 1566 | 0
Central Valley | 1518 | 1845 | 2598.4967 | 5063 | 4140.476 | 615 | 0.00010319 | 1.9514 | 20.8594 | 1114.1707 | 11757.9118 | 694.2701 | 1.2518 | 47.4672 | 1.1154 | 0.00018138 | 0.0008955 | 0.36441 | 0.62758 | {111B8F03-A7A2-4ADC-B553-BFBB68F5B187} | 163011101 | MARTELL 1101 | 91216 | 38.4349 | -120.7501 | MARTELL 110191216 | 503 | 459 | 103941.1045 | 66328.7264 | 37612.3781 | 66328.7264 | 37612.3781 | 0.55073 | 0.063462 | 1.4084 | 8.2325 | 449 | 0.11155 | 1988 | 0 | 0 | 41.2147 | 990 | 0
Central Coast | 3230 | 14 | 42.5782 | 53 | 59.0312 | 13 | 1.6641e-05 | 11.7075 | 1.9051 | 81.2159 | 271.745 | 2.3429 | 2.1162 | 100.395 | 1.0727 | 0.00018055 | 2.7074e-05 | 0.26415 | 0.72128 | {6ECC9377-E065-4FCE-971C-2036CD830EDE} | 182571103 | DIVIDE 1103 | 48160 | 34.8293 | -120.4499 | DIVIDE 110348160 | 101 | 133 | 25738.7088 | 21090.6373 | 4648.0716 | 4025.5628 | 4268.3111 | 0.00035197 | 0.00021634 | 3.0413 | 4.0769 | 2504 | 0.0023472 | 1989 | 0 | 0 | 2.5014 | 1216 | 0
Bay Area | 1763 | 28 | 64.992 | 63 | 85.5595 | 6 | 7.3024e-05 | 4.0296 | 0.039745 | 0.1112 | 0.00035236 | 2.801e-08 | 0.50221 | 6.1041 | 1.0026 | 0.00017761 | 4.6612e-05 | 0.44444 | 0.75961 | {196072E3-9BAD-4649-BDA0-FE3AF88F88C8} | 42261101 | BOLINAS 1101 | 1064 | 37.9253 | -122.6982 | BOLINAS 11011064 | 115 | 316 | 24373.3143 | 7144.3316 | 17228.9828 | 546.0033 | 1233.6391 | 0.00027967 | 0.00043815 | 2.3211 | 10.5 | 2271 | 0.0010656 | 1990 | 0 | 0 | 0.33927 | 2186 | 0
Sierra | 2498 | 1878 | 2647.6315 | 3282 | 3319.7 | 271 | 0.000106 | 1.7336 | 7.1635 | 25.4448 | 107.0815 | 1.834 | 1.4947 | 13.6431 | 1.0128 | 0.00017657 | 0.00045849 | 0.57221 | 0.79755 | {FA7F836A-C8A0-42D3-8E43-389B5B7AEC7D} | 152241101 | HALSEY 1101 | circuit_breaker | 38.9568 | -121.0432 | HALSEY 1101circuit_breaker | 423 | 542 | 56543.1776 | 27545.8987 | 28997.2789 | 27545.8987 | 28997.2789 | 0.12425 | 0.028725 | 1.4098 | 12.1107 | 851 | 0.04785 | 1991 | 0 | 0 | 17.1162 | 955 | 0
Bay Area | 3106 | 768 | 1542.7634 | 2324 | 2387.4634 | 105 | 6.3841e-05 | 1.8773 | 1.4342 | 0.77831 | 2.5798 | 0.03298 | 0.061905 | 0.38868 | 0.48633 | 0.00017449 | 8.769e-05 | 0.33046 | 0.64619 | {E82C2F97-5C09-4976-BD47-A486EC875FA4} | 42031125 | ALTO 1125 | 1226 | 37.8966 | -122.5394 | ALTO 11251226 | 238 | 1017 | 58919.2608 | 12660.3361 | 46258.9248 | 12208.7235 | 43916.5464 | 0.0092074 | 0.0067033 | 2.0088 | 22.1333 | 1926 | 0.018322 | 1992 | 0 | 0 | 7.5861 | 1166 | 0
Central Valley | 8105 | 32 | 42.1848 | 161 | 99.1414 | 36 | 6.1919e-05 | 2.0473 | 2.5716 | 58.5988 | 863.5079 | 10.086 | 0.27624 | 4.9834 | 1.0006 | 0.00017436 | 0.00011724 | 0.19876 | 0.4255 | {1A848C40-E8B2-462D-A943-C318AC9886BA} | 252531101 | SAN JOAQUIN #3 1101 | 10060 | 37.2927 | -119.5325 | SAN JOAQUIN #3 110110060 | 84 | 172 | 17677.3382 | 10431.3936 | 7245.9446 | 10431.3936 | 7245.9446 | 0.0042205 | 0.0022291 | 1.3183 | 4.4722 | 1760 | 0.0062769 | 1993 | 0 | 0 | 6.4818 | 151 | 0
Sierra | 2555 | 375 | 612.4303 | 1238 | 1039.5181 | 113 | 0.00010552 | 1.749 | 3.1218 | 8.6239 | 25.7691 | 0.2699 | 1.154 | 4.6838 | 1.0408 | 0.00017405 | 0.00021565 | 0.30291 | 0.58915 | {7316CABA-ACE0-4406-9BB2-A4017DAD0078} | 152691104 | HIGGINS 1104 | 533648 | 39.1044 | -121.0553 | HIGGINS 1104533648 | 159 | 373 | 28782.7184 | 10867.9062 | 17914.8122 | 10867.9062 | 17914.8122 | 0.024368 | 0.011923 | 1.6331 | 10.9558 | 1357 | 0.019668 | 1994 | 0 | 0 | 6.753 | 1116 | 0
Bay Area | 8027 | 176 | 275.2613 | 695 | 564.8594 | 55 | 0.00011585 | 1.7957 | 0.21268 | 0.40691 | 1.1017 | 0.0035211 | 0.099891 | 0.88142 | 0.67349 | 0.00017254 | 7.4029e-05 | 0.25324 | 0.48731 | {78640A7E-4385-4C01-A0A7-78496A91C391} | 42011107 | SAN RAFAEL 1107 | 1276 | 37.9544 | -122.5405 | SAN RAFAEL 11071276 | 132 | 345 | 24098.0141 | 6179.9373 | 17918.0768 | 5613.9148 | 14761.6415 | 0.0040716 | 0.0063717 | 1.564 | 12.6364 | 2024 | 0.0094899 | 1995 | 0 | 0 | 3.4883 | 2205 | 0
Bay Area | 5332 | 258 | 503.0631 | 906 | 837.545 | 98 | 3.8092e-05 | 5.3246 | 0.4539 | 25.2657 | 58.837 | 0.26188 | 3.9474 | 62.6892 | 1.0464 | 0.00017216 | 2.9157e-05 | 0.28477 | 0.60064 | {EAE1D7B0-E463-4F79-B04B-CDCA7EEEF36C} | 14101105 | ALHAMBRA 1105 | 8302 | 37.989 | -122.1345 | ALHAMBRA 11058302 | 134 | 155 | 25821.2504 | 13278.3332 | 12542.9172 | 13278.3332 | 12542.9172 | 0.0028573 | 0.003733 | 1.9499 | 9.2449 | 2473 | 0.016872 | 1996 | 0 | 0 | 8.2508 | 1329 | 0
Central Coast | 2810 | 1607 | 2950.6588 | 4129 | 4384.8936 | 260 | 0.00010049 | 1.7118 | 4.0009 | 26.2943 | 141.3167 | 1.1648 | 0.68115 | 9.9501 | 1.0162 | 0.00017172 | 0.00026588 | 0.3892 | 0.67291 | {DC46DF0C-E79C-47C3-8E88-AF56F3C9F267} | 83622103 | CAMP EVERS 2103 | 11046 | 36.9995 | -122.0079 | CAMP EVERS 210311046 | 322 | 381 | 55708.761 | 26125.6746 | 29583.0863 | 26125.6746 | 29583.0863 | 0.069128 | 0.026129 | 1.8361 | 15.8808 | 1208 | 0.044646 | 1997 | 0 | 0 | 16.2337 | 495 | 0
Central Coast | 5149 | 4 | 16.1963 | 31 | 29.2933 | 8 | 1.8901e-05 | 9.001 | 0.16556 | 168.5134 | 1075.7778 | 0.53522 | 0.056139 | 6.5469 | 1.0033 | 0.00017116 | 1.5101e-05 | 0.12903 | 0.5529 | {82D72170-020E-4DD7-9C9F-960EDB0862CE} | 182801101 | BAYWOOD 1101 | circuit_breaker | 35.3611 | -120.8113 | BAYWOOD 1101circuit_breaker | 291 | 226 | 58304.6686 | 46581.9622 | 11722.7064 | 6577.3472 | 1140.7996 | 0.00012081 | 0.00015121 | 4.0491 | 3.875 | 2702 | 0.0013693 | 1998 | 0 | 0 | 4.087 | 2413 | 0
Bay Area | 5291 | 114 | 229.5961 | 615 | 538.6043 | 51 | 9.0516e-05 | 2.414 | 11.9945 | 58.7568 | 202.5908 | 6.402 | 1.4989 | 25.6182 | 1.0323 | 0.0001679 | 0.00049132 | 0.18537 | 0.42628 | {812F7F32-99CA-4B11-A2F5-E536332A91A6} | 14161108 | ROSSMOOR 1108 | circuit_breaker | 37.8651 | -122.0809 | ROSSMOOR 1108circuit_breaker | 153 | 360 | 26091.4873 | 9105.2713 | 16986.216 | 5393.569 | 3377.7009 | 0.025057 | 0.0046163 | 2.014 | 12.0588 | 796 | 0.0085631 | 1999 | 0 | 0 | 3.3514 | 255 | 0
Central Coast | 8642 | 163 | 488.0905 | 644 | 718.2227 | 50 | 5.0522e-05 | 2.4463 | 4.5844 | 36.5713 | 123.4878 | 1.7059 | 1.7812 | 22.5219 | 1.1763 | 0.00016513 | 0.00012062 | 0.25311 | 0.67958 | {B079AC67-F69E-4839-9DB7-69A2C23DFB56} | 83692104 | ROB ROY 2104 | 5304 | 36.973 | -121.8204 | ROB ROY 21045304 | 86 | 131 | 16394.478 | 8039.9737 | 8354.5043 | 4973.8861 | 3109.0585 | 0.0060311 | 0.0025261 | 2.9944 | 12.88 | 1745 | 0.0082564 | 2000 | 0 | 0 | 3.0906 | 1121 | 0
Central Coast | 9289 | 430 | 783.9491 | 540 | 840.5865 | 44 | 7.0715e-05 | 2.2291 | 6.2462 | 88.7567 | 909.2858 | 10.0293 | 0.99824 | 31.0734 | 1.1126 | 0.00016486 | 0.00025086 | 0.7963 | 0.93262 | {6BAAEACD-1C65-48C0-90AE-AACABE567607} | 83692104 | ROB ROY 2104 | 6577 | 37.048 | -121.8081 | ROB ROY 21046577 | 46 | 51 | 12596.4359 | 5612.3201 | 6984.1158 | 5612.3201 | 6984.1158 | 0.011038 | 0.0031115 | 1.8231 | 12.2727 | 1246 | 0.007254 | 2001 | 0 | 0 | 3.4873 | 1433 | 0
Bay Area | 1460 | 384 | 755.7426 | 1303 | 1317.6871 | 56 | 6.8976e-05 | 2.6058 | 2.2056 | 2.3457 | 8.5813 | 0.064448 | 0.53473 | 3.9403 | 1.5742 | 0.0001641 | 0.00011552 | 0.2947 | 0.57354 | {28DA4EFF-D25B-42D5-8BBC-019BF0512D2C} | 12350401 | ORINDA 0401 | N545R | 37.8844 | -122.1929 | ORINDA 0401N545R | 148 | 559 | 32818.6324 | 8180.3467 | 24638.2857 | 7502.4589 | 23172.5038 | 0.006469 | 0.0038627 | 1.9681 | 23.2679 | 1773 | 0.0091894 | 2002 | 0 | 0 | 4.6618 | 2446 | 0
Central Valley | 7339 | 235 | 395.15 | 1264 | 756.9847 | 103 | 4.2663e-05 | 2.8472 | 74.9029 | 580.6814 | 6982.8725 | 1688.4456 | 3.8224 | 33.2844 | 1.2119 | 0.00016337 | 0.0015209 | 0.18592 | 0.52201 | {09598188-CE5A-44C7-8CBD-CFBA0AA34580} | 163351705 | CURTIS 1705 | 8110 | 37.9861 | -120.2613 | CURTIS 17058110 | 150 | 181 | 26031.2998 | 13092.5709 | 12938.7288 | 13092.5709 | 12938.7288 | 0.15666 | 0.0043943 | 1.6815 | 12.2718 | 241 | 0.016828 | 2003 | 0 | 0 | 8.1353 | 1115 | 0
Central Coast | 7589 | 213 | 320.7349 | 1048 | 836.1248 | 156 | 3.627e-05 | 3.4537 | 0.404 | 183.4407 | 1377.2923 | 0.22184 | 1.3455 | 44.9998 | 1.0703 | 0.00016085 | 2.7922e-05 | 0.20324 | 0.3836 | {3BA4B8C1-556E-4444-9F96-4ADCA52FD345} | 183181101 | SAN JUSTO 1101 | 4002 | 36.8322 | -121.5312 | SAN JUSTO 11014002 | 189 | 160 | 44028.8944 | 30436.1969 | 13592.6975 | 29265.3642 | 13289.9151 | 0.0043559 | 0.0056581 | 1.5058 | 6.7179 | 2492 | 0.025092 | 2004 | 0 | 0 | 18.1846 | 1098 | 0
Central Valley | 893 | 54 | 93.1909 | 621 | 336.1906 | 103 | 9.0511e-06 | 13.4569 | 8.373 | 258.3427 | 2912.0194 | 90.0511 | 0.11833 | 18.3554 | 1.0136 | 0.00015935 | 5.5477e-05 | 0.086957 | 0.2772 | {1A4C84BC-5487-41C8-8DEF-67BCD120C5BE} | 254061102 | DUNLAP 1102 | 7050 | 36.6985 | -119.0118 | DUNLAP 11027050 | 102 | 369 | 27533.8299 | 14670.6683 | 12863.1616 | 14670.6683 | 12863.1616 | 0.0057142 | 0.00093226 | 1.7258 | 6.0291 | 2187 | 0.016413 | 2005 | 0 | 0 | 9.1159 | 1843 | 0
Central Valley | 2161 | 187 | 259.0549 | 1256 | 772.5305 | 127 | 1.6684e-05 | 8.6827 | 6.2566 | 174.4151 | 3518.13 | 31.2894 | 0.5766 | 13.2662 | 1.038 | 0.00015771 | 5.7391e-05 | 0.14889 | 0.33533 | {CE6F4624-7696-4753-9F9E-95B6D73CFD1A} | 254421103 | OAKHURST 1103 | 5470 | 37.5302 | -119.6369 | OAKHURST 11035470 | 206 | 571 | 32650.203 | 15314.9972 | 17335.2058 | 15314.9972 | 17335.2058 | 0.0072886 | 0.0021189 | 1.3853 | 9.8898 | 2166 | 0.02003 | 2006 | 0 | 0 | 9.5163 | 1811 | 0
Central Valley | 4718 | 102 | 185.8746 | 544 | 334.7509 | 147 | 4.5576e-05 | 3.1881 | 2.8077 | 138.2954 | 1101.0044 | 17.0809 | 2.4719 | 97.4701 | 1.1006 | 0.00015679 | 7.5023e-05 | 0.1875 | 0.55526 | {01E04AB3-4BC7-461C-86D6-3A3D5CD166F9} | 252192101 | BEAR VALLEY 2101 | circuit_breaker | 37.586 | -120.1254 | BEAR VALLEY 2101circuit_breaker | 219 | 211 | 50420.8258 | 30106.3475 | 20314.4784 | 30106.3475 | 20314.4784 | 0.011028 | 0.0066996 | 1.8223 | 3.7007 | 2020 | 0.023048 | 2007 | 0 | 0 | 18.7072 | 756 | 0
Central Valley | 138 | 726 | 1066.838 | 2291 | 1716.0273 | 201 | 9.6444e-05 | 1.4859 | 6.3973 | 28.6546 | 134.2538 | 8.9221 | 1.1345 | 8.9978 | 1.0082 | 0.00015394 | 0.00030573 | 0.31689 | 0.62169 | {155070BB-C96B-485B-99BD-6B770FC28FA3} | 163761703 | RACETRACK 1703 | circuit_breaker | 37.98 | -120.4138 | RACETRACK 1703circuit_breaker | 475 | 951 | 75998.9491 | 28812.6661 | 47186.283 | 24637.5385 | 40300.4618 | 0.061453 | 0.019385 | 1.4695 | 11.398 | 1108 | 0.030943 | 2008 | 0 | 0 | 15.3091 | 1597 | 0
Bay Area | 2806 | 1769 | 2945.3433 | 4239 | 4349.094 | 217 | 0.00014778 | 1.7051 | 0.19465 | 0.18002 | 0.1886 | 0.0004547 | 0.13025 | 0.50157 | 1.0328 | 0.00015336 | 9.1738e-05 | 0.41732 | 0.67723 | {64A83390-336F-46D2-AA1C-9D91A30B0162} | 42011107 | SAN RAFAEL 1107 | 1166 | 37.9545 | -122.537 | SAN RAFAEL 11071166 | 472 | 1329 | 85500.9304 | 24108.9087 | 61392.0217 | 19693.934 | 42138.9696 | 0.019907 | 0.032068 | 1.665 | 19.5346 | 1898 | 0.03328 | 2009 | 0 | 0 | 12.2372 | 1516 | 0
Central Valley | 6081 | 491 | 682.521 | 1653 | 1229.9155 | 101 | 6.311e-05 | 1.9436 | 5.1922 | 6.46 | 18.7162 | 0.20178 | 0.72906 | 3.7901 | 1.1793 | 0.00015323 | 0.00021467 | 0.29704 | 0.55493 | {45D5D58B-80DE-4D2E-89C9-FED8B8DCC26F} | 163351702 | CURTIS 1702 | 68380 | 38.0151 | -120.2744 | CURTIS 170268380 | 175 | 406 | 29573.1738 | 10695.6106 | 18877.5632 | 10695.6106 | 18877.5632 | 0.021682 | 0.0063741 | 1.3901 | 16.3663 | 1363 | 0.015476 | 2010 | 0 | 0 | 6.6459 | 1908 | 0
North Coast | 2842 | 29 | 38.399 | 53 | 47.1215 | 7 | 2.8678e-05 | 7.1915 | 5.8552 | 861.5389 | 15252.6245 | 253.9543 | 2.1887 | 87.243 | 1.1846 | 0.00015069 | 0.00012669 | 0.54717 | 0.81489 | {4F4D60A8-18DF-4AD7-9533-2FDA5C5224B4} | 42771114 | UKIAH 1114 | 544 | 39.123 | -123.1811 | UKIAH 1114544 | 143 | 147 | 21655.4821 | 16090.1587 | 5565.3234 | 423.9084 | 460.9537 | 0.00088684 | 0.00020075 | 1.3241 | 7.5714 | 1713 | 0.0010548 | 2011 | 0 | 0 | 0.2634 | 1661 | 0
Bay Area | 6656 | 31 | 109.2831 | 72 | 133.5595 | 7 | 1.2848e-05 | 10.252 | 0.21932 | 0.1112 | 0.0020455 | 8.9726e-07 | 0.52434 | 1.4377 | 1.0041 | 0.00015067 | 1.1331e-05 | 0.43056 | 0.81824 | {BE77E89E-D575-4124-AA7C-BF07ADE3CD3D} | 42491102 | SAUSALITO 1102 | 1224 | 37.8662 | -122.5 | SAUSALITO 11021224 | 144 | 146 | 10812.662 | 5029.3503 | 5783.3117 | 1179.0057 | 378.0186 | 7.9316e-05 | 8.9934e-05 | 3.5253 | 10.2857 | 2771 | 0.0010547 | 2012 | 0 | 0 | 0.7326 | 2863 | 0
Central Coast | 1097 | 167 | 378.3717 | 795 | 777.3106 | 92 | 2.8035e-05 | 5.4518 | 1.4667 | 27.2846 | 176.2483 | 0.32363 | 0.96109 | 30.8649 | 0.98663 | 0.00015027 | 3.6452e-05 | 0.21006 | 0.48677 | {98ADBEF9-BACB-4586-BAAB-FCF78599AE57} | 83242104 | MORGAN HILL 2104 | XR018 | 37.1274 | -121.6483 | MORGAN HILL 2104XR018 | 293 | 270 | 39263.152 | 17280.6805 | 21982.4715 | 9365.0904 | 13609.1975 | 0.0033536 | 0.0025792 | 2.2657 | 8.6413 | 2382 | 0.013825 | 2013 | 0 | 0 | 5.8192 | 2532 | 0
North Coast | 186 | 2137 | 3613.4952 | 2915 | 3969.4246 | 233 | 0.00011236 | 1.6977 | 3.4522 | 29.2331 | 147.8233 | 0.83238 | 0.55113 | 4.9615 | 1.055 | 0.00014908 | 0.00026495 | 0.7331 | 0.91033 | {20E18CC8-D4A7-4B74-B6A8-456036AC47A2} | 43081101 | BIG RIVER 1101 | 79628 | 39.312 | -123.7861 | BIG RIVER 110179628 | 266 | 355 | 47890.4214 | 23966.4375 | 23923.9839 | 23966.4375 | 23923.9839 | 0.061733 | 0.026179 | 1.6909 | 12.5107 | 1209 | 0.034735 | 2014 | 0 | 0 | 14.892 | 2177 | 0
Sierra | 2099 | 259 | 356.1829 | 580 | 498.1006 | 79 | 8.8299e-05 | 1.8721 | 2.9863 | 14.8311 | 102.467 | 0.39751 | 0.86289 | 14.7119 | 1.035 | 0.00014871 | 0.0001689 | 0.44655 | 0.71508 | {0BF84A9F-DBEC-4CA7-98FB-695194286708} | 152481102 | BRUNSWICK 1102 | circuit_breaker | 39.2313 | -121.0352 | BRUNSWICK 1102circuit_breaker | 137 | 124 | 16223.9191 | 10196.061 | 6027.8582 | 9785.3713 | 5824.4339 | 0.013343 | 0.0069756 | 1.3752 | 7.3418 | 1522 | 0.011748 | 2015 | 0 | 0 | 6.0803 | 780 | 0
Central Coast | 1472 | 162 | 234.1858 | 963 | 718.1713 | 150 | 1.8559e-05 | 12.365 | 0.93706 | 272.799 | 1269.511 | 4.4907 | 1.0706 | 221.1506 | 1.2131 | 0.00014745 | 1.6584e-05 | 0.16822 | 0.32609 | {EB657CB8-596F-4421-86E3-2C8A72D44EE1} | 83912110 | PIERCY 2110 | XR258 | 37.2803 | -121.7577 | PIERCY 2110XR258 | 165 | 89 | 49305.7146 | 42515.4619 | 6790.2527 | 32262.0914 | 4527.8817 | 0.0024876 | 0.0027838 | 1.4456 | 6.42 | 2669 | 0.022117 | 2016 | 0 | 0 | 20.0467 | 1845 | 0
Central Valley | 1472 | 0 | 0 | 1 | 0.35919 | 1 | 1.5254e-05 | 0.066431 |  |  |  |  | 0 | 2.1186 | 1 | 1.0133e-06 | 1.5254e-05 | 0 | 0 | {EB657CB8-596F-4421-86E3-2C8A72D44EE1} | 83912110 | PIERCY 2110 | XR258 | 37.2803 | -121.7577 | PIERCY 2110XR258 | 165 | 89 | 49305.7146 | 42515.4619 | 6790.2527 | 32262.0914 | 4527.8817 | 1.5254e-05 | 1.5254e-05 |  | 1 | 2699 | 1.0133e-06 | 2016 | 0 | 0 | 20.0467 | 2630 | 0
Central Valley | 3135 | 46 | 125.5443 | 1878 | 954.8411 | 111 | 2.1143e-05 | 6.9228 | 16.1785 | 164.1443 | 3539.6768 | 210.9148 | 0.53641 | 4.7817 | 1.0065 | 0.00014607 | 0.00017877 | 0.024494 | 0.13148 | {EF855D85-A8A9-46E0-809B-873120E44CEB} | 162831702 |  | 9280 | 38.1992 | -120.0197 | 9280 | 159 | 432 | 22009.2787 | 10238.6401 | 11770.6386 | 10238.6401 | 11770.6386 | 0.019844 | 0.0023469 | 2.7292 | 16.9189 | 1492 | 0.016214 | 2017 | 0 | 0 | 6.362 | 2476 | 0
Central Coast | 8988 | 126 | 237.5205 | 813 | 645.0699 | 76 | 4.9328e-05 | 3.1962 | 6.2732 | 240.7168 | 3501.026 | 39.0183 | 0.85107 | 29.9301 | 1.1405 | 0.00014591 | 0.0002013 | 0.15498 | 0.36821 | {D42EB516-2D37-4D0C-8D56-AE34D1571A30} | 82021107 | LOS GATOS 1107 | LA60 | 37.1839 | -121.9823 | LOS GATOS 1107LA60 | 101 | 56 | 19485.2758 | 13828.9369 | 5656.3389 | 13828.9369 | 5656.3389 | 0.015299 | 0.0037489 | 1.8851 | 10.6974 | 1407 | 0.011089 | 2018 | 0 | 0 | 8.5929 | 1406 | 0
North Coast | 2224 | 943 | 1484.4941 | 1185 | 1596.0125 | 147 | 9.3933e-05 | 1.3654 | 2.1335 | 81.8937 | 435.6361 | 1.7894 | 0.71632 | 16.6654 | 1.01 | 0.00014417 | 0.00014729 | 0.79578 | 0.93013 | {73B4F2ED-84BD-4C50-9DB1-F9DAD696FAA9} | 42981101 | ELK 1101 | circuit_breaker | 39.1293 | -123.7117 | ELK 1101circuit_breaker | 189 | 172 | 40768.3596 | 27400.2212 | 13368.1384 | 18644.2912 | 7124.5177 | 0.021651 | 0.013808 | 1.5742 | 8.0612 | 1607 | 0.021193 | 2019 | 0 | 0 | 11.585 | 1962 | 0
Bay Area | 5254 | 371 | 494.8047 | 1329 | 1057.6664 | 89 | 6.1141e-05 | 2.5426 | 1.5066 | 14.0576 | 32.463 | 0.1657 | 1.5189 | 63.6137 | 1.0729 | 0.0001421 | 7.0751e-05 | 0.27916 | 0.46783 | {266E069D-C6A8-4558-8F2F-10A212B5E8EA} | 14241101 | SUNOL 1101 | MR299 | 37.5957 | -121.8896 | SUNOL 1101MR299 | 110 | 277 | 19510.6861 | 8022.9478 | 11487.7383 | 8022.9478 | 11487.7383 | 0.0062969 | 0.0054415 | 1.3337 | 14.9326 | 2050 | 0.012647 | 2020 | 0 | 0 | 4.9852 | 2465 | 0
Bay Area | 1190 | 7 | 8.594 | 24 | 19.4493 | 4 | 1.0542e-05 | 11.9543 | 0 | 0.10209 | 0.00020262 | 0 | 1.1781 | 19.3718 | 1.0105 | 0.00014059 | 4.6579e-06 | 0.29167 | 0.44187 | {9140C526-29BF-4637-A62D-8BE823C11E2E} | 14232106 | SAN RAMON 2106 | circuit_breaker | 37.745 | -121.9375 | SAN RAMON 2106circuit_breaker | 69 | 35 | 4481.1807 | 3629.0684 | 852.1123 | 655.1911 | 384.2721 | 1.8632e-05 | 4.2167e-05 | 1.2277 | 6 | 2850 | 0.00056237 | 2021 | 0 | 0 | 0.40712 | 2316 | 0
Central Coast | 174 | 132 | 226.3166 | 585 | 466.997 | 130 | 1.6382e-05 | 11.6886 | 1.9034 | 137.8601 | 884.3737 | 5.3067 | 3.4373 | 81.7372 | 1.1009 | 0.00014031 | 1.9455e-05 | 0.22564 | 0.48462 | {6DF33D7E-A953-44F1-82DC-C36E39D2281E} | 182031103 | KING CITY 1103 | 7038 | 36.1935 | -121.1442 | KING CITY 11037038 | 279 | 316 | 56798.0571 | 34883.787 | 21914.27 | 28474.5458 | 13562.6764 | 0.0025292 | 0.0021296 | 1.7145 | 4.5 | 2619 | 0.01824 | 2022 | 0 | 0 | 17.6933 | 1795 | 0
North Valley | 3860 | 922 | 1212.7833 | 1385 | 1463.0771 | 166 | 1.7835e-05 | 9.8488 | 2.1457 | 1231.8805 | 24735.0439 | 57.299 | 0.69856 | 56.586 | 1.2321 | 0.00014024 | 2.9126e-05 | 0.6657 | 0.82893 | {0DD81C15-0750-470B-8405-5D786A5E8465} | 102530401 | GRAYS FLAT 0401 | circuit_breaker | 40.0221 | -121.0642 | GRAYS FLAT 0401circuit_breaker | 96 | 126 | 23918.2906 | 17210.1208 | 6708.1698 | 17210.1208 | 6708.1698 | 0.004835 | 0.0029606 | 1.3154 | 8.3434 | 2474 | 0.02328 | 2023 | 0 | 0 | 10.6939 | 1007 | 0
Central Valley | 4865 | 11 | 24.3444 | 70 | 42.7982 | 18 | 2.3885e-05 | 7.3888 | 2.7043 | 606.5367 | 2290.452 | 9.0507 | 1.8922 | 225.7256 | 1.297 | 0.00013996 | 3.9353e-05 | 0.15714 | 0.56882 | {B68E2FC5-9A54-49EB-9258-EB6EA1DB9D61} | 163781704 | PEORIA 1704 | 8040 | 37.8996 | -120.5039 | PEORIA 17048040 | 174 | 126 | 54900.0158 | 41434.2849 | 13465.7309 | 11308.8739 | 3781.9841 | 0.00070835 | 0.00042992 | 2.2131 | 3.8889 | 2351 | 0.0025193 | 2024 | 0 | 0 | 7.027 | 1104 | 0
Bay Area | 5641 | 39 | 91.9585 | 300 | 214.3245 | 25 | 5.0196e-05 | 3.0225 | 1.8762 | 47.0755 | 150.3919 | 1.0802 | 2.2578 | 43.6764 | 1.0318 | 0.00013994 | 8.0457e-05 | 0.13 | 0.42906 | {0F676DC3-CFF5-456D-B8E2-CAA231B3A90A} | 13432207 | FAIRVIEW 2207 | P150 | 38.0454 | -122.1903 | FAIRVIEW 2207P150 | 35 | 158 | 10109.209 | 3652.8381 | 6456.3709 | 3652.8381 | 6189.8522 | 0.0020114 | 0.0012549 | 2.3579 | 12 | 1980 | 0.0034985 | 2025 | 0 | 0 | 2.2698 | 2640 | 0
Sierra | 4468 | 1714 | 2346.6172 | 3276 | 3136.9978 | 330 | 9.8117e-05 | 1.9515 | 27.3401 | 222.1798 | 2662.0106 | 214.1055 | 3.29 | 33.9015 | 1.1488 | 0.00013862 | 0.0012812 | 0.5232 | 0.74805 | {88BE1133-9496-494A-BFE3-FDF017C4AFD5} | 152491101 | WEIMAR 1101 | 2058 | 39.0444 | -120.9858 | WEIMAR 11012058 | 399 | 412 | 59991.061 | 33216.2606 | 26774.8003 | 33216.2606 | 26774.8003 | 0.42278 | 0.032379 | 1.3691 | 9.9273 | 296 | 0.045746 | 2026 | 0 | 0 | 20.6396 | 383 | 0
Sierra | 2562 | 745 | 1217.3381 | 2092 | 1778.9608 | 161 | 0.00010834 | 1.3954 | 7.6073 | 25.8991 | 195.0169 | 3.7509 | 3.1181 | 19.0075 | 1.0192 | 0.00013823 | 0.00048886 | 0.35612 | 0.6843 | {BDBA1A41-9235-4F2C-87B2-104E0BB64232} | 152481106 | BRUNSWICK 1106 | 2104 | 39.1994 | -121.0173 | BRUNSWICK 11062104 | 225 | 305 | 32922.7417 | 15655.9212 | 17266.8205 | 15655.9212 | 17266.8205 | 0.078707 | 0.017442 | 1.634 | 12.9938 | 800 | 0.022255 | 2027 | 0 | 0 | 9.7281 | 869 | 0
Central Coast | 6840 | 333 | 655.5165 | 929 | 1014.6237 | 89 | 2.1389e-05 | 6.1449 | 2.3618 | 52.3364 | 248.9468 | 1.6047 | 1.1764 | 77.9415 | 1.1992 | 0.00013772 | 3.1302e-05 | 0.35845 | 0.64607 | {BF5568ED-9C16-497C-B05F-AE0C967E64B7} | 182941102 | OTTER 1102 | 2002 | 36.2249 | -121.759 | OTTER 11022002 | 105 | 77 | 16530.0941 | 13828.3943 | 2701.6998 | 13828.3943 | 2701.6998 | 0.0027859 | 0.0019036 | 1.9685 | 10.4382 | 2453 | 0.012257 | 2028 | 0 | 0 | 8.5926 | 1797 | 0
Central Coast | 5174 | 25 | 36.368 | 189 | 110.56 | 13 | 5.4714e-05 | 3.7335 | 0.76675 | 2.0833 | 5.494 | 0.012671 | 1.3348 | 17.0658 | 1.0534 | 0.00013603 | 4.7702e-05 | 0.13228 | 0.32894 | {B5262924-E8BA-494C-94F2-552AF4F4F88E} | 183052113 | TEMPLETON 2113 | A32 | 35.501 | -120.6621 | TEMPLETON 2113A32 | 185 | 530 | 34175.624 | 9517.7168 | 24657.9072 | 2317.4886 | 1106.3293 | 0.00062013 | 0.00071129 | 1.4547 | 14.5385 | 2251 | 0.0017684 | 2029 | 0 | 0 | 1.44 | 1872 | 0
North Coast | 7444 | 2065 | 3511.7282 | 2271 | 3608.5798 | 223 | 0.00010076 | 1.2399 | 1.1988 | 60.8464 | 210.018 | 0.44859 | 0.55818 | 21.4335 | 1.0424 | 0.00013458 | 0.00011478 | 0.90929 | 0.97316 | {AE0E521E-C3FF-493C-8531-F1F586FF92F5} | 42981101 | ELK 1101 | 1260 | 39.1293 | -123.7112 | ELK 11011260 | 149 | 106 | 31135.2865 | 24924.6684 | 6210.6181 | 24474.7526 | 6210.6181 | 0.025595 | 0.02247 | 1.7006 | 10.1839 | 1776 | 0.03001 | 2030 | 0 | 0 | 15.2079 | 1133 | 0
Sierra | 194 | 114 | 175.7812 | 400 | 306.8902 | 32 | 9.7448e-05 | 1.5523 | 7.0754 | 23.1365 | 179.1297 | 2.6266 | 0.80773 | 8.0432 | 0.9747 | 0.00013327 | 0.00049356 | 0.285 | 0.57278 | {B8FC5083-3BB9-4DC9-857E-167142C974FD} | 152481105 | BRUNSWICK 1105 | 733408 | 39.2615 | -120.9897 | BRUNSWICK 1105733408 | 94 | 194 | 17679.7678 | 5559.4271 | 12120.3407 | 5559.4271 | 11825.4355 | 0.015794 | 0.0031183 | 1.5419 | 12.5 | 794 | 0.0042647 | 2031 | 0 | 0 | 3.4545 | 1422 | 0
North Valley | 7954 | 117 | 151.0492 | 556 | 351.6455 | 113 | 9.6965e-06 | 13.5287 | 0.32586 | 44.3695 | 537.9381 | 0.24409 | 0.24747 | 11.7133 | 1.0435 | 0.00013188 | 6.4157e-06 | 0.21043 | 0.42955 | {A5EA53CA-65A7-43BC-BB3E-43041FB8E51A} | 102812101 | BIG MEADOWS 2101 | 2476 | 40.1712 | -121.0871 | BIG MEADOWS 21012476 | 150 | 190 | 19305.6267 | 14000.8931 | 5304.7336 | 12812.7347 | 2877.3939 | 0.00072497 | 0.0010957 | 1.291 | 4.9204 | 2835 | 0.014902 | 2032 | 0 | 0 | 7.9615 | 801 | 0
Bay Area | 6722 | 53 | 70.9124 | 175 | 146.8573 | 18 | 2.3828e-05 | 5.3502 | 18.598 | 13.3351 | 41.6402 | 2.9568 | 5.0281 | 20.5316 | 1.0788 | 0.00013097 | 0.00018488 | 0.30286 | 0.48287 | {A57172F7-A24B-4226-8C15-DA9E4C31AFEB} | 42481101 | IGNACIO 1101 | circuit_breaker | 38.0755 | -122.5399 | IGNACIO 1101circuit_breaker | 51 | 2 | 3100.4423 | 2942.811 | 157.6313 | 2568.3258 | 33.7521 | 0.0033278 | 0.00042891 | 1.338 | 9.7222 | 1466 | 0.0023575 | 2033 | 0 | 0 | 1.5959 | 1004 | 0
Central Valley | 6703 | 32 | 43.4747 | 564 | 267.4049 | 44 | 3.9252e-05 | 3.3062 | 5.7801 | 6.6349 | 17.7227 | 0.14972 | 0.097561 | 2.7402 | 1.1828 | 0.00013002 | 0.00014128 | 0.056738 | 0.16258 | {935356E3-FEB4-4879-A7C1-1F4676D9B041} | 163692102 | SALT SPRINGS 2102 | L491 | 38.3076 | -120.2664 | SALT SPRINGS 2102L491 | 56 | 114 | 8083.4089 | 3564.5514 | 4518.8575 | 3564.5514 | 4518.8575 | 0.0062161 | 0.0017271 | 1.3586 | 12.8182 | 1626 | 0.005721 | 2034 | 0 | 0 | 2.2149 | 605 | 0
Central Coast | 4927 | 36 | 97.1668 | 95 | 134.1575 | 11 | 4.138e-05 | 3.5055 | 0.67578 | 70.3423 | 248.2973 | 0.88081 | 2.8825 | 161.2975 | 1.1044 | 0.00012588 | 3.1215e-05 | 0.37895 | 0.72427 | {A0B73F98-66D4-44F0-A30D-DD6726111A66} | 83192101 | GREEN VALLEY 2101 | 12130 | 36.939 | -121.7423 | GREEN VALLEY 210112130 | 263 | 316 | 55330.631 | 27999.4589 | 27331.1721 | 2080.1983 | 1853.6105 | 0.00034337 | 0.00045518 | 2.6991 | 8.6364 | 2455 | 0.0013847 | 2035 | 0 | 0 | 1.2926 | 706 | 0
Central Coast | 3711 | 2630 | 5416.7331 | 3530 | 5956.043 | 179 | 9.802e-05 | 1.4018 | 9.0325 | 65.0236 | 568.1545 | 14.7246 | 0.70512 | 11.5558 | 1.0185 | 0.00012523 | 0.00047065 | 0.74504 | 0.90945 | {F7013B1A-D0D7-4319-B5E7-A5441451D41D} | 82931101 | POINT MORETTI 1101 | 10726 | 37.0614 | -122.1489 | POINT MORETTI 110110726 | 226 | 233 | 31898.8207 | 17020.6225 | 14878.1981 | 17020.6225 | 14878.1981 | 0.084246 | 0.017546 | 2.0596 | 19.7207 | 826 | 0.022416 | 2036 | 0 | 0 | 10.5761 | 189 | 0
North Coast | 1481 | 717 | 1410.871 | 1073 | 1603.7072 | 59 | 0.00013225 | 0.87244 | 7.1804 | 7.4111 | 32.3723 | 0.3676 | 0.82237 | 2.9524 | 1.0012 | 0.00012298 | 0.00042582 | 0.66822 | 0.87976 | {C3FAC8CF-A105-47CA-BAFD-6A205D726950} | 42811113 | MONTE RIO 1113 | circuit_breaker | 38.4713 | -123.012 | MONTE RIO 1113circuit_breaker | 114 | 426 | 27250.8532 | 7159.5444 | 20091.3088 | 7159.5444 | 20091.3088 | 0.025124 | 0.0078029 | 1.9677 | 18.1864 | 904 | 0.0072556 | 2037 | 0 | 0 | 4.4487 | 1027 | 0
Central Coast | 313 | 316 | 703.7125 | 809 | 984.2389 | 82 | 7.389e-05 | 2.1072 | 1.8722 | 39.825 | 124.9965 | 0.70572 | 1.5402 | 22.8442 | 1.0163 | 0.00012102 | 0.00011364 | 0.39061 | 0.71498 | {C8470ABD-D047-4E6E-A601-35B08D6D1BD2} | 83192101 | GREEN VALLEY 2101 | 12106 | 36.9718 | -121.7649 | GREEN VALLEY 210112106 | 338 | 399 | 60778.3318 | 30176.8092 | 30601.5226 | 9141.9925 | 5136.2014 | 0.0093189 | 0.006059 | 2.2269 | 9.8659 | 1783 | 0.0099233 | 2038 | 0 | 0 | 5.6806 | 2728 | 0
Central Valley | 3226 | 308 | 420.2329 | 880 | 662.8215 | 73 | 0.00011726 | 1.2295 | 3.0574 | 9.7835 | 43.1227 | 0.20273 | 2.0311 | 36.1016 | 1.0506 | 0.00011943 | 0.00023003 | 0.35 | 0.63401 | {C73A5D7F-692C-413A-8D72-DC21C7152C9F} | 163240402 | TAR FLAT 0402 | 3144 | 37.9906 | -120.3838 | TAR FLAT 04023144 | 95 | 248 | 19085.8712 | 8204.0408 | 10881.8304 | 7378.011 | 8049.0182 | 0.016792 | 0.0085603 | 1.3644 | 12.0548 | 1310 | 0.0087181 | 2039 | 0 | 0 | 4.5845 | 1787 | 0
North Valley | 6142 | 135 | 167.7027 | 496 | 370.6411 | 106 | 3.55e-05 | 3.7176 | 2.0267 | 171.6461 | 774.5134 | 3.4532 | 3.1666 | 134.1907 | 1.1484 | 0.00011793 | 5.8421e-05 | 0.27218 | 0.45247 | {BA152E71-0C87-4C15-81C5-18C97756BF06} | 103491101 | MC ARTHUR 1101 | 1490 | 41.0943 | -121.5157 | MC ARTHUR 11011490 | 152 | 134 | 29931.1103 | 24194.4063 | 5736.7039 | 13967.782 | 3988.7475 | 0.0061927 | 0.003763 | 1.2422 | 4.6792 | 2157 | 0.012501 | 2040 | 0 | 0 | 8.6792 | 603 | 0
North Valley | 7900 | 124 | 144.2189 | 814 | 437.0211 | 69 | 5.3872e-05 | 2.1333 | 29.9796 | 449.876 | 5837.7568 | 285.5149 | 0.25523 | 14.3321 | 1.0094 | 0.00011763 | 0.0011013 | 0.15233 | 0.33 | {3AA926AF-5D59-48E9-968A-65279153CE9D} | 102541102 | VOLTA 1102 | 54932 | 40.514 | -121.7875 | VOLTA 110254932 | 75 | 44 | 9262.8201 | 6888.3237 | 2374.4964 | 6888.3237 | 2374.4964 | 0.075989 | 0.0037172 | 1.1631 | 11.7971 | 361 | 0.0081164 | 2041 | 0 | 0 | 4.2802 | 1607 | 0
Bay Area | 8970 | 110 | 327.84 | 164 | 352.3018 | 14 | 2.9369e-05 | 6.8859 | 0.0055807 | 0.077295 | 0.0017993 | 3.0103e-08 | 4.3619 | 18.4295 | 1.0555 | 0.00011702 | 1.7493e-05 | 0.67073 | 0.93057 | {EEE9A4DD-4FFF-4813-917D-2CD2DA44AB21} | 42491102 | SAUSALITO 1102 | 84278 | 37.8514 | -122.4893 | SAUSALITO 110284278 | 43 | 39 | 4827.9717 | 2442.5589 | 2385.4128 | 2267.2637 | 2385.4128 | 0.0002449 | 0.00041116 | 2.9804 | 11.7143 | 2656 | 0.0016382 | 2042 | 0 | 0 | 1.4088 | 1868 | 0
Sierra | 6422 | 378 | 530.4635 | 669 | 692.0819 | 54 | 0.00011575 | 0.94695 | 4.0465 | 12.5489 | 82.0999 | 0.92934 | 1.5412 | 9.3176 | 1.0002 | 0.00011679 | 0.00031996 | 0.56502 | 0.76648 | {94B9AF22-8864-4989-8A91-A669E5CFF969} | 152481106 | BRUNSWICK 1106 | 4639 | 39.1731 | -121.0453 | BRUNSWICK 11064639 | 76 | 128 | 12796.7945 | 5228.1955 | 7568.599 | 5228.1955 | 7568.599 | 0.017278 | 0.0062505 | 1.4033 | 12.3889 | 1074 | 0.0063064 | 2043 | 0 | 0 | 3.2486 | 529 | 0
Central Coast | 3550 | 45 | 155.2998 | 98 | 177.0945 | 15 | 3.8691e-05 | 3.4862 | 16.1648 | 41.9993 | 250.9041 | 23.6886 | 1.0718 | 49.6935 | 1.0161 | 0.00011615 | 0.00023465 | 0.45918 | 0.87693 | {081215BD-B859-40D1-BF5E-3B29C95FC4FD} | 183071101 | PERRY 1101 | V88 | 35.5597 | -121.0765 | PERRY 1101V88 | 102 | 240 | 13771.1853 | 5002.9541 | 8768.2313 | 1316.7813 | 1715.9486 | 0.0035198 | 0.00058037 | 3.4511 | 6.5333 | 1300 | 0.0017422 | 2044 | 0 | 0 | 0.81821 | 1639 | 0
North Coast | 2078 | 70 | 103.7082 | 152 | 132.3298 | 23 | 6.1861e-05 | 1.1 | 0.32086 | 2.4481 | 4.531 | 0.0034493 | 0.53857 | 8.3 | 0.9672 | 0.00011598 | 3.9833e-05 | 0.46053 | 0.78371 | {64C6F4FE-9745-4B83-9BA2-6905B1D464FF} | 43351106 | LUCERNE 1106 | circuit_breaker | 39.1101 | -122.8129 | LUCERNE 1106circuit_breaker | 108 | 398 | 23744.9936 | 5806.4035 | 17938.5901 | 2265.0742 | 4440.2717 | 0.00091616 | 0.0014228 | 1.4815 | 6.6087 | 2345 | 0.0026676 | 2045 | 0 | 0 | 1.4075 | 1456 | 0
Central Valley | 1396 | 8 | 9.8217 | 38 | 22.6738 | 7 | 6.2516e-05 | 1.3362 | 21.6242 | 137.1776 | 425.2823 | 18.0974 | 4.6865 | 182.5024 | 1.141 | 0.00011487 | 0.00037657 | 0.21053 | 0.43317 | {537E07C0-FB8F-462B-87E9-2D8AA468190F} | 163341101 | CLAY 1101 | 84572 | 38.3515 | -120.9323 | CLAY 110184572 | 90 | 223 | 11783.2288 | 3629.8323 | 8153.3966 | 598.9234 | 1343.5774 | 0.002636 | 0.00043761 | 1.2277 | 5.4286 | 973 | 0.00080407 | 2046 | 0 | 0 | 0.37215 | 1882 | 0
North Coast | 6394 | 205 | 306.904 | 316 | 359.1432 | 47 | 7.2795e-05 | 1.586 | 2.2844 | 30.5464 | 141.1349 | 0.7671 | 1.7057 | 11.0727 | 0.99779 | 0.00011702 | 0.00013545 | 0.64873 | 0.85454 | {C88ECF07-A349-4E08-B534-12AB1E3B3B9B} | 43071101 | DUNBAR 1101 | 234 | 38.4218 | -122.5538 | DUNBAR 1101234 | 158 | 174 | 20026.4151 | 10449.6965 | 9576.7185 | 5211.7421 | 4174.5166 | 0.0063662 | 0.0034214 | 1.4971 | 6.7234 | 1663 | 0.0054998 | 2047 | 0 | 0 | 3.2384 | 1280 | 0
Bay Area | 6394 | 0 | 0 | 6 | 6.5943 | 1 | 6.795e-05 | 0.066431 | 4.0319 | 21.7555 | 84.3855 | 0.35636 | 11.4912 | 31.8285 | 1.0177 | 4.514e-06 | 0.00027397 | 0 | 0 | {C88ECF07-A349-4E08-B534-12AB1E3B3B9B} | 43071101 | DUNBAR 1101 | 234 | 38.4218 | -122.5538 | DUNBAR 1101234 | 158 | 174 | 20026.4151 | 10449.6965 | 9576.7185 | 5211.7421 | 4174.5166 | 0.00027397 | 6.795e-05 |  | 6 | 1192 | 4.514e-06 | 2047 | 0 | 0 | 3.2384 | 302 | 0
Bay Area | 5658 | 388 | 676.4325 | 877 | 953.8181 | 49 | 6.3652e-05 | 2.0088 | 0.51914 | 4.0265 | 14.7406 | 0.03324 | 0.2444 | 2.5853 | 1.0005 | 0.00010917 | 4.7139e-05 | 0.44242 | 0.70918 | {6992E765-02F8-45C7-B571-2F9E479DE26D} | 12541106 | OAKLAND X 1106 | CR020 | 37.8 | -122.1706 | OAKLAND X 1106CR020 | 29 | 25 | 4898.3401 | 3933.9507 | 964.3895 | 3933.9507 | 964.3895 | 0.0023098 | 0.0031189 | 1.7434 | 17.898 | 2264 | 0.0053494 | 2048 | 0 | 0 | 2.4444 | 2708 | 0
Central Coast | 9254 | 11 | 30.7208 | 26 | 36.9427 | 6 | 6.0954e-06 | 13.3801 | 0.0018282 | 1.575 | 21.999 | 0.0031009 | 0.2618 | 219.9439 | 1.3392 | 0.00010652 | 4.8603e-06 | 0.42308 | 0.83158 | {AD986AF1-07AD-469F-94A3-573792C7B7E5} | 253671103 | PANOCHE 1103 | 4036 | 36.5855 | -120.8158 | PANOCHE 11034036 | 57 | 49 | 58181.2474 | 40363.4485 | 17817.7989 | 13306.7166 | 4188.2516 | 2.9162e-05 | 3.6573e-05 | 2.7928 | 4.3333 | 2847 | 0.00063911 | 2049 | 0 | 0 | 8.2684 | 1856 | 0
Central Valley | 5946 | 32 | 49.3285 | 74 | 69.474 | 13 | 5.3363e-05 | 1.8946 | 6.6492 | 124.5611 | 1230.6068 | 16.2836 | 0.27997 | 6.2369 | 1.0116 | 0.00010562 | 0.00016517 | 0.43243 | 0.71003 | {8AAD3A20-76BA-4DD7-9403-7AA47644DC04} | 163781701 | PEORIA 1701 | 69124 | 37.8554 | -120.2251 | PEORIA 170169124 | 60 | 106 | 8511.5167 | 4347.2792 | 4164.2375 | 4347.2792 | 4164.2375 | 0.0021472 | 0.00069371 | 1.5415 | 5.6923 | 1531 | 0.0013731 | 2050 | 0 | 0 | 2.7013 | 1881 | 0
Central Coast | 1778 | 33 | 88.608 | 205 | 172.9605 | 36 | 1.5687e-05 | 8.0051 | 6.5759 | 16.347 | 51.363 | 1.334 | 2.3805 | 21.3674 | 1.0127 | 0.00010524 | 4.8361e-05 | 0.16098 | 0.5123 | {C2088C0A-8EBB-40EA-8088-14055CC416B4} | 183101104 | CABRILLO 1104 | circuit_breaker | 34.6432 | -120.4377 | CABRILLO 1104circuit_breaker | 200 | 684 | 59234.3562 | 27422.4738 | 31811.8823 | 5579.5239 | 1074.775 | 0.001741 | 0.00056475 | 2.6851 | 5.6944 | 2244 | 0.0037888 | 2051 | 0 | 0 | 3.467 | 1668 | 0
Central Coast | 4579 | 249 | 615.4978 | 290 | 633.6088 | 47 | 2.1337e-05 | 10.4727 | 0.24419 | 30.0931 | 121.4275 | 0.048474 | 1.3185 | 130.7313 | 1.1648 | 0.00010238 | 1.2724e-05 | 0.85862 | 0.97142 | {E6C5781A-7190-407F-9EDA-B9DCCCBA229C} | 182771101 | CAMBRIA 1101 | V76 | 35.647 | -121.1906 | CAMBRIA 1101V76 | 79 | 60 | 32755.6105 | 31109.7165 | 1645.8941 | 29392.3861 | 1645.8941 | 0.00059801 | 0.0010028 | 2.4719 | 6.1702 | 2751 | 0.0048118 | 2052 | 0 | 0 | 18.2636 | 993 | 0
Central Coast | 3709 | 81 | 256.338 | 134 | 280.7779 | 34 | 3.1026e-05 | 3.6505 | 0.75033 | 67.5933 | 484.3357 | 3.6967 | 0.51425 | 16.6549 | 1.0273 | 0.00010181 | 2.7438e-05 | 0.60448 | 0.91296 | {0C127574-7596-4A86-A384-D65556DA9180} | 183011102 | MORRO BAY 1102 | 47584 | 35.3115 | -120.8535 | MORRO BAY 110247584 | 93 | 138 | 21189.9911 | 15483.3273 | 5706.6638 | 14612.5687 | 4924.865 | 0.0009329 | 0.0010549 | 3.1647 | 3.9412 | 2500 | 0.0034617 | 2053 | 0 | 0 | 9.0798 | 2593 | 0
Central Valley | 6442 | 0 | 0 | 9 | 3.9003 | 7 | 1.2404e-05 | 6.8568 | 0.03033 | 415.133 | 2645.7361 | 0.068684 | 0.5 | 18.1675 | 1.0066 | 0.00010106 | 7.4986e-06 | 0 | 0 | {28A07299-BAB6-4846-84FA-366E13AEFEE9} | 163351703 | CURTIS 1703 | 9210 | 37.8183 | -120.0961 | CURTIS 17039210 | 178 | 152 | 45576.8121 | 37044.9289 | 8531.8832 | 37044.9289 | 8531.8832 | 5.249e-05 | 8.6828e-05 |  | 1.2857 | 2817 | 0.00070741 | 2054 | 0 | 0 | 23.0186 | 1924 | 0
Sierra | 8515 | 2 | 5.7715 | 145 | 71.282 | 34 | 6.7394e-06 | 16.9374 | 4.1669 | 24.3202 | 90.7652 | 1.8573 | 2.3912 | 59.4044 | 1.1271 | 9.887e-05 | 1.399e-05 | 0.013793 | 0.080967 | {4D17090F-B031-42D9-8E52-3D09021DC1AB} | 152591102 | SUMMIT 1102 | 49484 | 39.3174 | -120.329 | SUMMIT 110249484 | 53 | 75 | 5935.8193 | 4326.7918 | 1609.0276 | 4326.7918 | 1609.0276 | 0.00047567 | 0.00022914 | 2.8858 | 4.2647 | 2722 | 0.0033616 | 2055 | 0 | 0 | 2.6885 | 2379 | 0
Central Coast | 8903 | 211 | 429.361 | 392 | 542.2695 | 38 | 5.1326e-05 | 2.0126 | 1.4574 | 120.9278 | 661.0031 | 1.9507 | 1.049 | 46.032 | 1.1315 | 9.8725e-05 | 6.3706e-05 | 0.53827 | 0.79179 | {B894D21F-E8FF-4DD8-9F13-7F70E0655206} | 182941101 | OTTER 1101 | 7611 | 36.3864 | -121.8708 | OTTER 11017611 | 48 | 44 | 15261.1952 | 7068.0362 | 8193.1589 | 7068.0362 | 8193.1589 | 0.0024208 | 0.0019504 | 2.0349 | 10.3158 | 2106 | 0.0037516 | 2056 | 0 | 0 | 4.3919 | 2298 | 0
Central Coast | 686 | 564 | 1652.2275 | 1780 | 2316.6514 | 212 | 3.4711e-05 | 2.7041 | 7.614 | 178.2245 | 884.9337 | 23.2217 | 3.5458 | 59.0126 | 1.2145 | 9.8215e-05 | 0.00013714 | 0.31685 | 0.7132 | {900275D8-44B8-45C0-ADC0-5DBF17ADDB8A} | 182731101 | RESERVATION ROAD 1101 | 3026 | 36.5788 | -121.7199 | RESERVATION ROAD 11013026 | 446 | 625 | 77013.1086 | 36330.5251 | 40682.5835 | 34466.6969 | 34078.4388 | 0.029074 | 0.0073586 | 2.9295 | 8.3962 | 1653 | 0.020822 | 2057 | 0 | 0 | 21.4166 | 103 | 0
Bay Area | 79 | 115 | 351.514 | 178 | 375.7612 | 9 | 2.8062e-05 | 5.4086 | 0.30376 | 0.1668 | 0.0025733 | 5.9433e-07 | 2.4558 | 38.1942 | 1.076 | 9.6499e-05 | 1.3972e-05 | 0.64607 | 0.93547 | {88158706-37CE-4050-9559-5A1E15835B03} | 22721107 | SNEATH LANE 1107 | circuit_breaker | 37.6221 | -122.447 | SNEATH LANE 1107circuit_breaker | 92 | 643 | 33661.0176 | 6226.1953 | 27434.8223 | 1051.9745 | 3496.3199 | 0.00012575 | 0.00025256 | 3.0566 | 19.7778 | 2723 | 0.00086849 | 2058 | 0 | 0 | 0.65367 | 2023 | 0
Sierra | 6485 | 521 | 738.2648 | 1377 | 1166.0891 | 122 | 0.00010422 | 0.65271 | 2.4895 | 14.3743 | 80.678 | 0.4726 | 0.86548 | 13.9202 | 1.0549 | 9.4076e-05 | 0.00019869 | 0.37836 | 0.63311 | {0961801B-845E-4B14-847B-854C50E3739F} | 152241102 | HALSEY 1102 | circuit_breaker | 38.9567 | -121.0431 | HALSEY 1102circuit_breaker | 141 | 157 | 20202.4061 | 12858.5938 | 7343.8123 | 12469.8674 | 7285.752 | 0.02424 | 0.012715 | 1.417 | 11.2869 | 1418 | 0.011477 | 2059 | 0 | 0 | 7.7484 | 203 | 0
Central Coast | 3027 | 42 | 99.6815 | 179 | 184.4094 | 21 | 2.2149e-05 | 5.8201 | 0.2672 | 37.4935 | 133.6903 | 0.066066 | 0.75158 | 180.1318 | 1.0806 | 9.3591e-05 | 1.3483e-05 | 0.23464 | 0.54054 | {5CB94E28-BCD0-4946-A0EA-D8080443F8CB} | 182771101 | CAMBRIA 1101 | circuit_breaker | 35.6002 | -121.1151 | CAMBRIA 1101circuit_breaker | 124 | 131 | 26305.702 | 19513.1402 | 6792.5618 | 9200.2096 | 1156.0948 | 0.00028313 | 0.00046513 | 2.3734 | 8.5238 | 2734 | 0.0019654 | 2060 | 0 | 0 | 5.7167 | 2565 | 0
North Valley | 5961 | 19 | 23.0925 | 158 | 93.7144 | 25 | 7.8859e-06 | 12.4265 | 1.9518 | 245.5962 | 5283.328 | 36.2018 | 0.87726 | 11.9019 | 1.0039 | 9.0413e-05 | 1.0137e-05 | 0.12025 | 0.24641 | {48DFC761-81AC-4E6E-A815-DEA2190E6576} | 102812101 | BIG MEADOWS 2101 | circuit_breaker | 40.1714 | -121.0843 | BIG MEADOWS 2101circuit_breaker | 75 | 51 | 5517.7346 | 3325.4736 | 2192.2611 | 3325.4736 | 2192.2611 | 0.00025342 | 0.00019715 | 1.2154 | 6.32 | 2788 | 0.0022603 | 2061 | 0 | 0 | 2.0664 | 1225 | 0
Bay Area | 6520 | 104 | 204.8918 | 431 | 391.1114 | 32 | 4.3818e-05 | 1.5473 | 1.7225 | 3.7803 | 10.8236 | 0.037489 | 0.37021 | 3.3999 | 1.4116 | 8.9881e-05 | 5.7418e-05 | 0.2413 | 0.52387 | {D247477D-6B8D-41FB-AD66-DBEF58C5249C} | 12041112 | OAKLAND D 1112 | CR192 | 37.8514 | -122.2508 | OAKLAND D 1112CR192 | 128 | 688 | 33568.3572 | 6807.0507 | 26761.3066 | 3810.1619 | 8404.9927 | 0.0018374 | 0.0014022 | 1.9701 | 13.4688 | 2165 | 0.0028762 | 2062 | 0 | 0 | 2.3675 | 2122 | 0
Bay Area | 7289 | 273 | 468.2303 | 836 | 799.4087 | 61 | 5.8196e-05 | 2.4003 | 1.2101 | 4.3313 | 12.3629 | 0.019627 | 0.13563 | 8.1618 | 1.2649 | 8.9007e-05 | 6.8949e-05 | 0.32656 | 0.58572 | {D5F18742-859C-45AE-BB95-2396135F0809} | 14671103 | SOBRANTE 1103 | circuit_breaker | 37.9051 | -122.2076 | SOBRANTE 1103circuit_breaker | 110 | 146 | 14586.6856 | 6918.9418 | 7667.7438 | 6759.5318 | 7163.2029 | 0.0042059 | 0.00355 | 1.7151 | 13.7049 | 2068 | 0.0054294 | 2063 | 0 | 0 | 4.2002 | 2157 | 0
Central Valley | 6731 | 316 | 456.3048 | 1139 | 896.299 | 83 | 9.1156e-05 | 1.211 | 46.3968 | 341.2339 | 4835.9692 | 544.8255 | 0.60905 | 10.8262 | 1.1677 | 8.8803e-05 | 0.0020255 | 0.27744 | 0.5091 | {B2C7A4F4-BED5-4E31-A9B4-8AA354D418D1} | 162161101 | ELECTRA 1101 | L1697 | 38.3794 | -120.638 | ELECTRA 1101L1697 | 115 | 288 | 22345.155 | 8779.0798 | 13566.0753 | 8779.0798 | 13566.0753 | 0.16812 | 0.007566 | 1.444 | 13.7229 | 174 | 0.0073707 | 2064 | 0 | 0 | 5.4551 | 211 | 0
North Valley | 4977 | 27 | 72.5066 | 326 | 215.3258 | 68 | 7.1433e-06 | 12.6543 | 21.2186 | 54.9266 | 530.9277 | 10.5476 | 1.4509 | 28.5824 | 1.0928 | 8.6934e-05 | 8.347e-05 | 0.082822 | 0.33673 | {385C1178-1E10-4C92-A2B8-B11436713899} | 102361101 | HAMILTON BRANCH 1101 | 2046 | 40.2694 | -121.0878 | HAMILTON BRANCH 11012046 | 101 | 225 | 20019.7034 | 14788.0543 | 5231.6491 | 14724.19 | 5178.7163 | 0.005676 | 0.00048574 | 2.6854 | 4.7941 | 1962 | 0.0059115 | 2065 | 0 | 0 | 9.1492 | 1233 | 0
Central Coast | 1967 | 136 | 261.7719 | 293 | 339.2869 | 89 | 5.4381e-05 | 2.3125 | 0.91905 | 670.1793 | 4257.1147 | 16.1383 | 2.1865 | 132.0121 | 1.1016 | 8.5223e-05 | 4.1845e-05 | 0.46416 | 0.77154 | {201D4860-5BDE-4AE7-B543-F824A85004DC} | 182492105 | HOLLISTER 2105 | 4018 | 36.6885 | -121.2715 | HOLLISTER 21054018 | 311 | 245 | 124533.03 | 84640.1679 | 39892.8621 | 69788.1445 | 34802.2853 | 0.0037242 | 0.0048399 | 1.9248 | 3.2921 | 2312 | 0.0075849 | 2066 | 0 | 0 | 43.3643 | 2179 | 0
North Coast | 6186 | 1217 | 2099.6702 | 1478 | 2222.8125 | 154 | 8.4668e-05 | 0.99245 | 6.1439 | 34.2022 | 274.219 | 5.8718 | 0.4909 | 3.9997 | 1.0007 | 8.517e-05 | 0.00028756 | 0.82341 | 0.9446 | {63294CD0-4D7E-4FB1-9784-991B87B370C8} | 42761102 | FORT BRAGG A 1102 | 956 | 39.4015 | -123.8082 | FORT BRAGG A 1102956 | 247 | 329 | 40155.1104 | 19602.7346 | 20552.3758 | 18050.2005 | 17349.8801 | 0.044284 | 0.013039 | 1.7253 | 9.5974 | 1155 | 0.013116 | 2067 | 0 | 0 | 11.2159 | 2135 | 0
North Valley | 3988 | 317 | 439.9347 | 1626 | 1228.6703 | 234 | 2.6825e-05 | 3.696 | 4.1697 | 413.1824 | 3094.2941 | 30.53 | 4.7745 | 185.8602 | 1.203 | 8.5109e-05 | 6.4341e-05 | 0.19496 | 0.35806 | {9FEEDD46-3D3C-44E2-AC09-40EF72D10F0B} | 103311101 | BURNEY 1102 | 1340 | 40.9126 | -121.6455 | BURNEY 11021340 | 286 | 535 | 52904.0632 | 28964.4993 | 23939.5639 | 28964.4993 | 23939.5639 | 0.015056 | 0.0062771 | 1.3878 | 6.9487 | 2101 | 0.019916 | 2068 | 0 | 0 | 17.9977 | 1301 | 0
Central Coast | 259 | 2836 | 5246.8473 | 5735 | 6932.48 | 311 | 9.0667e-05 | 1.1365 | 3.315 | 27.3037 | 127.5851 | 1.4385 | 0.56225 | 7.9013 | 1.0125 | 8.4236e-05 | 0.00017508 | 0.49451 | 0.75685 | {97F0E264-6757-4E01-B858-9C73FC0BF875} | 83692105 | ROB ROY 2105 | 5090 | 36.9802 | -121.8922 | ROB ROY 21055090 | 423 | 347 | 55602.2415 | 34034.3802 | 21567.8613 | 34034.3802 | 21567.8613 | 0.05445 | 0.028197 | 1.8501 | 18.4405 | 1502 | 0.026197 | 2069 | 0 | 0 | 21.148 | 2155 | 0
Central Valley | 320 | 492 | 712.3969 | 1645 | 1219.5681 | 132 | 7.4138e-05 | 1.1467 | 5.0711 | 56.5571 | 419.215 | 5.896 | 1.374 | 12.9543 | 1.0173 | 8.205e-05 | 0.00020963 | 0.29909 | 0.58414 | {A5122D22-FC3B-40AD-B1C9-1922AC7D5EB3} | 163351704 | CURTIS 1704 | 63502 | 38.0455 | -120.3925 | CURTIS 170463502 | 192 | 260 | 31137.1787 | 16791.7983 | 14345.3804 | 16791.7983 | 14345.3804 | 0.027672 | 0.0097862 | 1.448 | 12.4621 | 1381 | 0.010831 | 2070 | 0 | 0 | 10.4339 | 150 | 0
Central Coast | 2890 | 369 | 712.8018 | 1230 | 1187.3328 | 101 | 7.8333e-05 | 1.0077 | 3.106 | 23.8135 | 150.664 | 1.5547 | 0.7721 | 9.7076 | 1.007 | 8.2001e-05 | 0.00014444 | 0.3 | 0.60034 | {8D1DF0FB-6A31-4B98-9D74-0EE015EF8A6D} | 83252105 | PAUL SWEET 2105 | circuit_breaker | 36.9922 | -121.9822 | PAUL SWEET 2105circuit_breaker | 422 | 720 | 59149.9602 | 25766.2731 | 33383.6871 | 12715.3949 | 6603.9993 | 0.014588 | 0.0079116 | 1.9317 | 12.1782 | 1619 | 0.0082821 | 2071 | 0 | 0 | 7.901 | 2170 | 0
Bay Area | 3571 | 483 | 859.2221 | 684 | 955.448 | 55 | 3.4402e-05 | 1.7959 | 5.3227 | 66.1927 | 279.0658 | 2.0171 | 0.049839 | 16.5162 | 1.012 | 8.098e-05 | 0.00011498 | 0.70614 | 0.89929 | {525B2EF0-7EB8-48BA-86A2-CA5740BCAD7C} | 24101103 | HALF MOON BAY 1103 | 8089 | 37.2191 | -122.3424 | HALF MOON BAY 11038089 | 45 | 164 | 10971.3703 | 4645.2114 | 6326.1589 | 4645.2114 | 6326.1589 | 0.0063239 | 0.0018921 | 1.7789 | 12.4364 | 1775 | 0.0044539 | 2072 | 0 | 0 | 2.8864 | 2520 | 0
North Valley | 1338 | 60 | 84.0367 | 403 | 262.2048 | 118 | 2.5997e-05 | 2.9451 | 2.2177 | 324.7392 | 1494.4379 | 7.4396 | 3.8735 | 121.8936 | 1.1114 | 8.0867e-05 | 3.7382e-05 | 0.14888 | 0.3205 | {A45048C4-5E06-4803-9C40-C46808E3753F} | 103311101 | BURNEY 1102 | 1322 | 40.913 | -121.6469 | BURNEY 11021322 | 105 | 84 | 42442.7916 | 30035.9017 | 12406.8899 | 23390.5578 | 10886.7206 | 0.004411 | 0.0030676 | 1.4006 | 3.4153 | 2373 | 0.0095423 | 2073 | 0 | 0 | 14.5342 | 1565 | 0
Sierra | 5977 | 72 | 126.0368 | 421 | 268.4997 | 33 | 8.6749e-05 | 0.78278 | 3.3223 | 20.0393 | 63.172 | 0.5314 | 1.2861 | 10.8768 | 1.1946 | 8.038e-05 | 0.00019376 | 0.17102 | 0.46941 | {72194304-B9B5-4008-9268-F14D384C2205} | 152571104 | HORSESHOE 1104 | 50142 | 38.767 | -121.1548 | HORSESHOE 110450142 | 111 | 190 | 15652.8647 | 6580.4443 | 9072.4204 | 3538.232 | 2265.7491 | 0.0063942 | 0.0028627 | 1.7505 | 12.7576 | 1434 | 0.0026525 | 2074 | 0 | 0 | 2.1986 | 262 | 0
Bay Area | 7554 | 815 | 1540.5174 | 969 | 1634.2655 | 69 | 4.8769e-05 | 1.445 | 4.6083 | 58.6575 | 189.5643 | 1.1377 | 0.00404 | 8.3194 | 1.0089 | 7.9712e-05 | 0.00012683 | 0.84107 | 0.94264 | {122C7DAC-AC52-4005-A738-CAEFD4E1581A} | 24131103 | MENLO 1103 | 8982 | 37.2682 | -122.2113 | MENLO 11038982 | 63 | 81 | 10527.0404 | 7297.022 | 3230.0184 | 7297.022 | 3230.0184 | 0.008751 | 0.0033651 | 1.8902 | 14.0435 | 1711 | 0.0055001 | 2075 | 0 | 0 | 4.5342 | 2512 | 0
North Valley | 3611 | 34 | 50.3245 | 85 | 72.2476 | 20 | 3.0345e-05 | 3.2291 | 1.5986 | 194.1875 | 3147.4004 | 34.5757 | 2.0961 | 106.9438 | 1.1041 | 7.9697e-05 | 4.1323e-05 | 0.4 | 0.69656 | {20DFFDEF-5135-4324-A022-CDDC3E81B3A6} | 103381101 | FRENCH GULCH 1101 | circuit_breaker | 40.6865 | -122.6405 | FRENCH GULCH 1101circuit_breaker | 53 | 42 | 5707.0956 | 3697.5337 | 2009.5619 | 3697.5337 | 2009.5619 | 0.00082645 | 0.0006069 | 1.4801 | 4.25 | 2321 | 0.0015939 | 2076 | 0 | 0 | 2.2975 | 116 | 0
North Coast | 826 | 3795 | 6299.4267 | 4698 | 6716.8403 | 352 | 7.8074e-05 | 0.80657 | 2.4899 | 57.1192 | 337.7235 | 1.3747 | 0.50643 | 9.4498 | 1.2171 | 7.9078e-05 | 0.0001334 | 0.80779 | 0.93786 | {62C9F82C-9B7A-4C03-B528-D0CC602C0334} | 42981101 | ELK 1101 | 1272 | 39.2233 | -123.768 | ELK 11011272 | 354 | 365 | 75878.311 | 36075.8659 | 39802.445 | 35495.0764 | 39652.5067 | 0.046958 | 0.027482 | 1.6599 | 13.3466 | 1682 | 0.027835 | 2077 | 0 | 0 | 22.0556 | 75 | 0
Sierra | 8935 | 0 | 0 | 116 | 53.2792 | 24 | 6.201e-06 | 14.7321 | 5.1176 | 125.14 | 518.0822 | 2.9852 | 3.6755 | 156.3064 | 1.3673 | 7.8714e-05 | 1.3065e-05 | 0 | 0 | {787994D9-582B-4D9D-9242-5F59A8A95135} | 152591101 | SUMMIT 1101 | 47786 | 39.3289 | -120.3427 | SUMMIT 110147786 | 21 | 8 | 2952.8874 | 2854.4871 | 98.4002 | 2854.4871 | 98.4002 | 0.00031355 | 0.00014882 |  | 4.8333 | 2741 | 0.0018891 | 2078 | 0 | 0 | 1.7737 | 1430 | 0
Sierra | 7774 | 399 | 517.3358 | 1357 | 924.5701 | 123 | 0.00010442 | 0.83957 | 9.8691 | 34.7814 | 292.4719 | 17.184 | 1.3132 | 15.7369 | 1.0169 | 7.6823e-05 | 0.00061489 | 0.29403 | 0.55954 | {05FDE184-0042-4792-8C58-B7C18CC19C9C} | 152481106 | BRUNSWICK 1106 | circuit_breaker | 39.2311 | -121.0351 | BRUNSWICK 1106circuit_breaker | 170 | 290 | 29294.1635 | 14188.8772 | 15105.2863 | 14079.7489 | 15105.2863 | 0.075632 | 0.012844 | 1.2966 | 11.0325 | 655 | 0.0094492 | 2079 | 0 | 0 | 8.7487 | 1450 | 0
Sierra | 2514 | 424 | 653.1504 | 1656 | 1149.6742 | 147 | 8.786e-05 | 1.2035 | 4.0862 | 19.3164 | 110.0784 | 1.0329 | 1.2872 | 17.48 | 1.0529 | 7.6636e-05 | 0.0002055 | 0.25604 | 0.56812 | {D24FE68D-C3B0-43F0-8A16-C357F1C466D0} | 152241102 | HALSEY 1102 | 2514 | 38.9503 | -121.0492 | HALSEY 11022514 | 473 | 912 | 71806.6383 | 31410.9717 | 40395.6665 | 15960.9106 | 14175.393 | 0.030208 | 0.012915 | 1.5404 | 11.2653 | 1396 | 0.011265 | 2080 | 0 | 0 | 9.9176 | 2646 | 0
Central Coast | 7092 | 38 | 56.6703 | 189 | 139.7874 | 51 | 3.34e-05 | 1.9831 | 0.26444 | 45.2163 | 267.932 | 0.39708 | 3.126 | 98.129 | 1.186 | 7.646e-05 | 1.8821e-05 | 0.20106 | 0.4054 | {95C4B2EA-7339-48DF-9F61-FADDFD6FCDFA} | 182492106 | HOLLISTER 2106 | 4004 | 36.8168 | -121.3906 | HOLLISTER 21064004 | 261 | 180 | 45020.0275 | 32627.9425 | 12392.0849 | 12351.5176 | 3883.5908 | 0.00095988 | 0.0017034 | 1.4913 | 3.7059 | 2636 | 0.0038995 | 2081 | 0 | 0 | 7.6749 | 919 | 0
Central Coast | 1902 | 310 | 663.5361 | 1677 | 1461.9302 | 125 | 7.3432e-05 | 1.2064 | 1.9316 | 21.2496 | 228.0522 | 3.8593 | 0.61256 | 11.8725 | 1.1501 | 7.5456e-05 | 0.00011397 | 0.18485 | 0.45388 | {574B3F5C-C8A6-43BF-A24C-78D062C2D75A} | 83371107 | SARATOGA 1107 | LC12 | 37.255 | -122.0354 | SARATOGA 1107LC12 | 170 | 184 | 21123.4666 | 12044.8193 | 9078.6473 | 12044.8193 | 9078.6473 | 0.014247 | 0.009179 | 2.1404 | 13.416 | 1779 | 0.009432 | 2082 | 0 | 0 | 7.4843 | 2579 | 0
Central Coast | 6119 | 83 | 110.3541 | 245 | 196.8869 | 56 | 3.478e-05 | 3.6903 | 0.60754 | 592.9452 | 4371.2381 | 5.1134 | 1.2569 | 44.4748 | 0.9874 | 7.5143e-05 | 2.646e-05 | 0.33878 | 0.56049 | {522758DC-D04C-45F3-86B0-6920B5847932} | 182492105 | HOLLISTER 2105 | 4048 | 36.719 | -121.2811 | HOLLISTER 21054048 | 181 | 145 | 59691.2096 | 44906.9277 | 14784.2819 | 26554.045 | 8787.7332 | 0.0014817 | 0.0019477 | 1.3296 | 4.375 | 2510 | 0.004208 | 2083 | 0 | 0 | 16.4999 | 2293 | 0
Central Coast | 5624 | 14 | 32.6579 | 52 | 49.6613 | 16 | 9.9436e-06 | 12.5234 | 0.85783 | 125.8159 | 687.6908 | 5.2255 | 1.0169 | 117.64 | 1.0001 | 7.4669e-05 | 1.3694e-05 | 0.26923 | 0.65761 | {820718CC-7467-4DD2-B2F8-381F3D5B3CFD} | 182052102 | SOLEDAD 2102 | 7048 | 36.4253 | -121.3075 | SOLEDAD 21027048 | 235 | 176 | 67480.0826 | 55321.9809 | 12158.1017 | 25828.9181 | 1685.3834 | 0.00021911 | 0.0001591 | 2.3327 | 3.25 | 2727 | 0.0011947 | 2084 | 0 | 0 | 16.0493 | 923 | 0
Bay Area | 5711 | 171 | 535.6829 | 386 | 668.9917 | 37 | 5.0951e-05 | 1.3526 | 1.6847 | 2.6377 | 6.6014 | 0.02956 | 0.24791 | 6.3419 | 1.0052 | 7.3647e-05 | 6.4375e-05 | 0.44301 | 0.80073 | {D1E9CD4E-4BC6-42D5-802C-68BF9527A1E0} | 12101102 | OAKLAND K 1102 | circuit_breaker | 37.8479 | -122.2292 | OAKLAND K 1102circuit_breaker | 91 | 152 | 12889.6005 | 4723.266 | 8166.3346 | 4723.266 | 8166.3346 | 0.0023819 | 0.0018852 | 3.1326 | 10.4324 | 2100 | 0.0027249 | 2085 | 0 | 0 | 2.9349 | 2589 | 0
Central Coast | 3675 | 12 | 15.7795 | 23 | 21.6888 | 3 | 2.328e-05 | 2.8472 | 0.00050513 | 0.1112 | 1.0026 | 1.0129e-06 | 0.86283 | 405.8959 | 1.4808 | 7.3262e-05 | 7.1741e-06 | 0.52174 | 0.72754 | {951B1516-4326-49B7-849D-E72573882819} | 182492104 | HOLLISTER 2104 | 91424 | 36.9335 | -121.3885 | HOLLISTER 210491424 | 139 | 121 | 19500.8151 | 14085.1454 | 5415.6697 | 430.1131 | 78.0393 | 2.1522e-05 | 6.9841e-05 | 1.315 | 7.6667 | 2819 | 0.00021979 | 2086 | 0 | 0 | 0.26726 | 910 | 0
North Valley | 2386 | 262 | 319.6884 | 933 | 656.6179 | 228 | 2.485e-05 | 3.9115 | 1.1118 | 320.9111 | 3430.9341 | 26.3089 | 1.0408 | 98.9747 | 1.0738 | 7.265e-05 | 2.434e-05 | 0.28081 | 0.48687 | {060881A6-D014-4A68-9103-99AC74B02ACB} | 103732101 | PIT NO 3 2101 | 1360 | 41.0315 | -121.6704 | PIT NO 3 21011360 | 106 | 61 | 40452.7074 | 34538.882 | 5913.8254 | 33967.8078 | 4802.0358 | 0.0055495 | 0.0056659 | 1.2202 | 4.0921 | 2542 | 0.016564 | 2087 | 0 | 0 | 21.1066 | 2129 | 0
North Valley | 3292 | 1096 | 1460.4674 | 3207 | 2432.0532 | 261 | 0.00015216 | 0.52193 | 12.6933 | 117.6308 | 1195.8846 | 32.0386 | 1.1272 | 14.3001 | 1.0248 | 7.1538e-05 | 0.0010738 | 0.34175 | 0.60051 | {EEE4445E-754A-4610-952B-CBD9BE00EDE8} | 103031102 | ORO FINO 1102 | 76008 | 39.8877 | -121.6655 | ORO FINO 110276008 | 263 | 326 | 44443.3487 | 25688.6957 | 18754.653 | 25688.6957 | 18754.653 | 0.28026 | 0.039713 | 1.3325 | 12.2874 | 376 | 0.018671 | 2088 | 0 | 0 | 15.9622 | 1032 | 0
Central Coast | 1783 | 121 | 303.5417 | 285 | 386.1933 | 56 | 2.024e-05 | 3.2599 | 0.81145 | 59.3428 | 403.9999 | 1.643 | 0.58364 | 92.3257 | 1.3348 | 7.1186e-05 | 1.7189e-05 | 0.42456 | 0.78598 | {05EEF29D-5376-4D63-9244-FB865CD63617} | 182941102 | OTTER 1102 | 98036 | 36.1795 | -121.6955 | OTTER 110298036 | 86 | 39 | 15910.3483 | 14861.2597 | 1049.0886 | 14861.2597 | 1049.0886 | 0.00096261 | 0.0011334 | 2.5086 | 5.0893 | 2663 | 0.0039864 | 2089 | 0 | 0 | 9.2344 | 911 | 0
North Coast | 1816 | 1560 | 2352.7391 | 1986 | 2544.6 | 181 | 7.176e-05 | 0.97829 | 3.7588 | 44.5556 | 207.8023 | 0.90054 | 0.6908 | 9.093 | 1.4449 | 7.0733e-05 | 0.00016526 | 0.7855 | 0.9246 | {9AB01B94-B2A5-4A8A-9109-9F42C093DB3E} | 42761104 | FORT BRAGG A 1104 | 4690 | 39.4417 | -123.7902 | FORT BRAGG A 11044690 | 290 | 494 | 42832.0952 | 23032.9774 | 19799.1178 | 18031.2616 | 11461.9409 | 0.029912 | 0.012988 | 1.5082 | 10.9724 | 1530 | 0.012803 | 2090 | 0 | 0 | 11.2041 | 161 | 0
Central Valley | 7364 | 12 | 21.3183 | 50 | 31.0093 | 25 | 2.4643e-05 | 2.7073 | 9.48 | 343.0973 | 1344.3515 | 13.5059 | 1.3353 | 309.1285 | 1.395 | 6.8791e-05 | 0.00013146 | 0.24 | 0.68748 | {D6A9F596-51F2-4D36-A52E-B2F47C72F950} | 163781704 | PEORIA 1704 | 13490 | 37.902 | -120.5808 | PEORIA 170413490 | 97 | 34 | 11268.7456 | 8715.5754 | 2553.1702 | 6383.5889 | 1485.7612 | 0.0032865 | 0.00061608 | 1.7765 | 2 | 1694 | 0.0017198 | 2091 | 0 | 0 | 3.9666 | 472 | 0
North Valley | 5681 | 78 | 85.906 | 688 | 351.2199 | 149 | 1.761e-05 | 4.2128 | 7.3413 | 409.5479 | 7126.3665 | 111.2964 | 0.50637 | 19.8832 | 1.0951 | 6.7303e-05 | 7.7924e-05 | 0.11337 | 0.24459 | {DF67F6ED-C0C1-4634-A8E7-5650468AFAD4} | 102541101 | VOLTA 1101 | 1640 | 40.3543 | -121.5766 | VOLTA 11011640 | 88 | 150 | 20194.2738 | 16481.2885 | 3712.9853 | 16481.2885 | 3712.9853 | 0.011611 | 0.0026239 | 1.1014 | 4.6174 | 2000 | 0.010028 | 2092 | 0 | 0 | 10.241 | 1261 | 0
Central Coast | 3628 | 124 | 216.2317 | 517 | 433.4457 | 60 | 3.0739e-05 | 0.84778 | 7.5016 | 8.5016 | 26.8035 | 0.68918 | 0.90517 | 1.7421 | 1.6515 | 6.5739e-05 | 0.00014758 | 0.23985 | 0.49887 | {4E56AABA-E208-4168-987C-AD9B6E34D222} | 183052108 | TEMPLETON 2108 | A40 | 35.5065 | -120.6939 | TEMPLETON 2108A40 | 401 | 1178 | 74829.6341 | 20682.9125 | 54146.7216 | 5903.9832 | 10843.3586 | 0.0088545 | 0.0018444 | 1.7438 | 8.6167 | 1605 | 0.0039443 | 2093 | 0 | 0 | 3.6686 | 1840 | 0
Central Coast | 7129 | 492 | 976.0234 | 612 | 1046.4863 | 71 | 3.9381e-05 | 1.4682 | 4.6269 | 166.4827 | 1227.2076 | 10.7729 | 2.1283 | 72.9257 | 1.3379 | 6.4044e-05 | 0.00010793 | 0.80392 | 0.93267 | {64CB4C99-55F9-4CDD-8DE2-173258603853} | 182941101 | OTTER 1101 | 2052 | 36.3999 | -121.902 | OTTER 11012052 | 75 | 136 | 13462.9804 | 7777.1247 | 5685.8557 | 7777.1247 | 5685.8557 | 0.0076631 | 0.002796 | 1.9838 | 8.6197 | 1816 | 0.0045471 | 2094 | 0 | 0 | 4.8325 | 1396 | 0
Bay Area | 6972 | 65 | 116.0692 | 419 | 297.7154 | 62 | 3.8925e-05 | 1.7027 | 1.7249 | 102.3493 | 235.7471 | 0.76382 | 0.81155 | 35.5147 | 1.0188 | 6.3618e-05 | 5.5361e-05 | 0.15513 | 0.38987 | {55278842-270D-4261-9B21-666405A19DF7} | 13432207 | FAIRVIEW 2207 | 99096 | 38.0167 | -122.1453 | FAIRVIEW 220799096 | 80 | 37 | 16737.4697 | 15921.3049 | 816.1649 | 15872.9643 | 734.25 | 0.0034324 | 0.0024134 | 1.7857 | 6.7581 | 2188 | 0.0039443 | 2095 | 0 | 0 | 9.863 | 2542 | 0
North Coast | 748 | 2276 | 3426.7689 | 2518 | 3544.681 | 210 | 8.6701e-05 | 0.62977 | 2.1406 | 23.1064 | 74.4089 | 0.20074 | 0.49507 | 9.6207 | 1.2016 | 6.1703e-05 | 0.00013036 | 0.90389 | 0.96674 | {1DB69746-E909-4FD7-90E8-E346F8AB657A} | 43081101 | BIG RIVER 1101 | 952 | 39.2695 | -123.7812 | BIG RIVER 1101952 | 262 | 319 | 35867.9595 | 26900.4145 | 8967.545 | 26689.2485 | 8764.0926 | 0.027375 | 0.018207 | 1.5056 | 11.9905 | 1700 | 0.012958 | 2096 | 0 | 0 | 16.5839 | 2024 | 0
Central Valley | 688 | 23 | 39.3193 | 180 | 74.5327 | 52 | 2.8629e-05 | 2.435 | 9.3954 | 850.5128 | 4312.4015 | 98.9677 | 2.0321 | 156.6929 | 1.3719 | 5.6936e-05 | 0.00012994 | 0.12778 | 0.52754 | {0E4DE50B-9CB6-46AA-9EAF-66A90C70B824} | 252811102 | MERCED FALLS 1102 | 9460 | 37.591 | -120.3071 | MERCED FALLS 11029460 | 77 | 43 | 16142.5063 | 14365.6775 | 1776.8289 | 14069.7042 | 1694.0007 | 0.0067568 | 0.0014887 | 1.7095 | 3.4615 | 1702 | 0.0029607 | 2097 | 0 | 0 | 8.7425 | 1461 | 0
Central Valley | 892 | 27 | 35.8206 | 232 | 122.4448 | 40 | 6.7437e-06 | 9.3993 | 0.24614 | 328.2137 | 2667.5282 | 4.2467 | 0.14856 | 150.4326 | 1.2181 | 5.6086e-05 | 3.8696e-06 | 0.11638 | 0.29254 | {35723AC1-565E-4787-875F-B05907FDAE4F} | 258591101 | TULE POWER HOUSE 1101 | circuit_breaker | 36.1623 | -118.7065 | TULE POWER HOUSE 1101circuit_breaker | 12 | 8 | 6674.0759 | 6363.6748 | 310.401 | 6363.6748 | 310.401 | 0.00015478 | 0.00026975 | 1.3267 | 5.8 | 2856 | 0.0022435 | 2098 | 0 | 0 | 3.9542 | 1756 | 0
Bay Area | 3727 | 1 | 1.2277 | 9 | 6.4132 | 2 | 5.891e-05 | 0.92479 |  |  |  |  | 0.63717 | 176.6629 | 1.0619 | 5.4726e-05 | 5.891e-05 | 0.11111 | 0.19144 | {EFBE7067-1C69-45D8-A9C8-472AE1406928} | 43292102 | PUEBLO 2102 | 698 | 38.4222 | -122.3373 | PUEBLO 2102698 | 325 | 474 | 49709.1467 | 26431.9074 | 23277.2393 | 187.7325 | 84.6958 | 0.00011782 | 0.00011782 | 1.2277 | 4.5 | 2152 | 0.00010945 | 2099 | 0 | 0 | 0.11665 | 2775 | 0
Bay Area | 644 | 266 | 459.3029 | 1460 | 1180.6316 | 85 | 5.7632e-05 | 0.91386 | 1.1351 | 10.3445 | 30.6177 | 0.07071 | 0.45042 | 8.9476 | 1.0031 | 5.4118e-05 | 6.1027e-05 | 0.18219 | 0.38903 | {40049C8F-DAE2-4759-A9B6-0D8AA42C6AC2} | 13801105 | MORAGA 1105 | circuit_breaker | 37.8488 | -122.1615 | MORAGA 1105circuit_breaker | 238 | 501 | 39550.3838 | 17363.7462 | 22186.6376 | 9314.4848 | 2986.362 | 0.0051873 | 0.0048987 | 1.7267 | 17.1765 | 2124 | 0.0046 | 2100 | 0 | 0 | 5.7878 | 2104 | 0
Central Coast | 938 | 248 | 621.3492 | 898 | 987.4999 | 52 | 7.2795e-05 | 0.97924 | 10.8088 | 16.9754 | 64.0566 | 1.2905 | 0.75102 | 5.9136 | 1.0788 | 5.393e-05 | 0.00040425 | 0.27617 | 0.62921 | {3E23A7A3-C33C-44B7-A4F6-DB4402C4D050} | 83252106 | PAUL SWEET 2106 | circuit_breaker | 36.9923 | -121.9823 | PAUL SWEET 2106circuit_breaker | 420 | 728 | 55127.9216 | 22673.5975 | 32454.3241 | 8257.1442 | 4436.543 | 0.021021 | 0.0037853 | 2.5054 | 17.2692 | 938 | 0.0028044 | 2101 | 0 | 0 | 5.1307 | 1736 | 0
Central Coast | 806 | 466 | 1661.374 | 754 | 1841.1245 | 46 | 4.782e-05 | 1.102 | 2.5056 | 5.4999 | 28.5898 | 0.12861 | 0.29689 | 1.9143 | 1.0108 | 5.3926e-05 | 9.8345e-05 | 0.61804 | 0.90237 | {143A069F-7F91-455A-9FDE-B811B4FD5E5E} | 183071101 | PERRY 1101 | V74 | 35.5457 | -121.0679 | PERRY 1101V74 | 149 | 396 | 22499.2839 | 8183.4097 | 14315.8743 | 6365.4334 | 10961.2269 | 0.0045239 | 0.0021997 | 3.5652 | 16.3913 | 1861 | 0.0024806 | 2102 | 0 | 0 | 3.9553 | 2862 | 0
Central Coast | 3780 | 1489 | 2625.4241 | 3153 | 3568.0588 | 177 | 9.4073e-05 | 0.60384 | 6.9349 | 27.0935 | 164.707 | 1.9273 | 0.97233 | 7.8305 | 1.0132 | 5.4141e-05 | 0.00033067 | 0.47225 | 0.73581 | {86E17BC0-A879-45C0-9429-4A0FD02BA21E} | 82021106 | LOS GATOS 1106 | 60116 | 37.1734 | -121.9929 | LOS GATOS 110660116 | 301 | 359 | 41854.1705 | 19897.4804 | 21956.6901 | 19897.4804 | 21956.6901 | 0.058529 | 0.016651 | 1.7632 | 17.8136 | 1053 | 0.0095829 | 2103 | 0 | 0 | 12.3637 | 2036 | 0
Bay Area | 3780 | 1 | 1.6135 | 26 | 21.4819 | 1 | 9.5912e-05 | 0.066431 | 0.97817 | 12.0692 | 79.0511 | 0.34115 | 0.15487 | 9.4173 | 1 | 6.3716e-06 | 9.3818e-05 | 0.038462 | 0.075111 | {86E17BC0-A879-45C0-9429-4A0FD02BA21E} | 82021106 | LOS GATOS 1106 | 60116 | 37.1734 | -121.9929 | LOS GATOS 110660116 | 301 | 359 | 41854.1705 | 19897.4804 | 21956.6901 | 19897.4804 | 21956.6901 | 9.3818e-05 | 9.5912e-05 | 1.6135 | 26 | 1885 | 6.3716e-06 | 2103 | 0 | 0 | 12.3637 | 2342 | 0
Central Valley | 1263 | 180 | 273.4119 | 905 | 602.1127 | 174 | 7.2716e-05 | 0.85263 | 4.4308 | 123.3208 | 644.7599 | 9.0164 | 2.1925 | 53.2167 | 1.1434 | 5.3393e-05 | 0.00019953 | 0.1989 | 0.45409 | {3FB47D58-B406-4320-8238-19B8B73E9349} | 162211101 | CALAVERAS CEMENT 1101 | 2646 | 38.2992 | -120.6982 | CALAVERAS CEMENT 11012646 | 212 | 162 | 46705.3583 | 28470.7774 | 18234.5809 | 28470.7774 | 18234.5809 | 0.034718 | 0.012653 | 1.519 | 5.2011 | 1415 | 0.0092904 | 2104 | 0 | 0 | 17.6909 | 1407 | 0
North Valley | 6983 | 19 | 32.1077 | 150 | 92.8232 | 27 | 7.1713e-06 | 5.3485 | 9.0551 | 276.4411 | 4926.2764 | 75.3543 | 1.0398 | 20.5291 | 1.0097 | 5.2711e-05 | 3.2769e-05 | 0.12667 | 0.3459 | {6FA22C4C-B16C-4BDC-8F70-7E0F32F87C45} | 102361101 | HAMILTON BRANCH 1101 | 90334 | 40.2684 | -121.0877 | HAMILTON BRANCH 110190334 | 74 | 96 | 8996.4682 | 5434.6472 | 3561.821 | 5355.1369 | 3489.1915 | 0.00088478 | 0.00019363 | 1.6899 | 5.5556 | 2429 | 0.0014232 | 2105 | 0 | 0 | 3.3275 | 826 | 0
Central Coast | 5645 | 45 | 69.6094 | 193 | 152.0295 | 37 | 2.5131e-05 | 2.3854 | 4.0252 | 448.6301 | 2514.0898 | 23.925 | 3.1592 | 357.1654 | 1.4167 | 5.221e-05 | 5.0847e-05 | 0.23316 | 0.45787 | {1326B156-0483-47A9-A035-C6F98F761263} | 182492102 | HOLLISTER 2102 | 855412 | 36.9523 | -121.4743 | HOLLISTER 2102855412 | 157 | 103 | 60455.1832 | 54939.02 | 5516.1632 | 42101.5076 | 3000.0058 | 0.0018813 | 0.00092984 | 1.5469 | 5.2162 | 2225 | 0.0019318 | 2106 | 0 | 0 | 26.1607 | 1667 | 0
Central Coast | 1912 | 57 | 212.8082 | 147 | 259.2547 | 19 | 5.273e-05 | 1.304 | 1.335 | 5.9382 | 28.8122 | 0.074903 | 3.8579 | 21.7961 | 1.878 | 5.1829e-05 | 5.5518e-05 | 0.38776 | 0.82085 | {6FDB7B55-5D84-4478-9719-37334B4F5477} | 83692104 | ROB ROY 2104 | 10930 | 36.964 | -121.8086 | ROB ROY 210410930 | 253 | 502 | 47627.0553 | 18179.3508 | 29447.7046 | 1570.0142 | 2818.0171 | 0.0010548 | 0.0010019 | 3.7335 | 7.7368 | 2185 | 0.00098475 | 2107 | 0 | 0 | 0.97556 | 2296 | 0
North Valley | 7528 | 149 | 290.9187 | 773 | 536.8779 | 133 | 6.7699e-05 | 0.961 | 7.6911 | 286.6457 | 2907.4103 | 64.9936 | 1.5602 | 75.7478 | 1.1574 | 5.1296e-05 | 0.00023661 | 0.19276 | 0.54187 | {A1256FE3-B033-4F99-92CE-F0CE386BDB02} | 103091102 | CLARK ROAD 1102 | 2068 | 39.6983 | -121.571 | CLARK ROAD 11022068 | 116 | 77 | 25186.4794 | 17243.1435 | 7943.3359 | 16704.4746 | 7943.3359 | 0.031469 | 0.009004 | 1.9525 | 5.812 | 1290 | 0.0068224 | 2108 | 0 | 0 | 10.3797 | 2422 | 0
Sierra | 406 | 2195 | 3065.9196 | 4950 | 4385.6543 | 351 | 0.00011525 | 0.40509 | 10.6603 | 52.6371 | 526.1927 | 42.1561 | 1.6173 | 12.3427 | 1.008 | 5.0163e-05 | 0.00066812 | 0.44343 | 0.69908 | {EF5B06D7-E629-41B9-B306-6C2CC9919130} | 152481106 | BRUNSWICK 1106 | 2796 | 39.1981 | -121.0287 | BRUNSWICK 11062796 | 425 | 552 | 67980.7371 | 31981.5846 | 35999.1525 | 31981.5846 | 35999.1525 | 0.23451 | 0.040452 | 1.3968 | 14.1026 | 597 | 0.017607 | 2109 | 0 | 0 | 19.8724 | 1944 | 0
North Valley | 9005 | 3 | 3.6831 | 10 | 6.9712 | 5 | 3.3812e-05 | 1.9358 | 0 | 0 | 0 | 0 | 3.6473 | 229.9829 | 1.1345 | 5.0138e-05 | 2.0454e-05 | 0.3 | 0.52834 | {68ED899E-4033-413B-A72A-EE83BDC8B804} | 103381102 | FRENCH GULCH 1102 | circuit_breaker | 40.6864 | -122.6405 | FRENCH GULCH 1102circuit_breaker | 20 | 5 | 2859.074 | 2729.0129 | 130.0611 | 2729.0129 | 130.0611 | 0.00010227 | 0.00016906 | 1.2277 | 2 | 2601 | 0.00025069 | 2110 | 0 | 0 | 1.6957 | 287 | 0
Central Valley | 7829 | 4 | 5.0417 | 17 | 11.0676 | 8 | 1.2138e-05 | 3.84 | 0.055983 | 2110.9799 | 19181.8253 | 1.939 | 0.08656 | 501.5877 | 1.7945 | 4.999e-05 | 7.3556e-06 | 0.23529 | 0.45554 | {EC646814-C576-4C16-B414-32B05AD6EA11} | 253141103 | CUYAMA 1103 | 622728 | 35.0056 | -119.808 | CUYAMA 1103622728 | 124 | 82 | 63541.8101 | 61732.6363 | 1809.1738 | 3818.1464 | 99.0569 | 5.8845e-05 | 9.7103e-05 | 1.2604 | 2.125 | 2818 | 0.00039992 | 2111 | 0 | 0 | 2.3725 | 902 | 0
Bay Area | 6134 | 190 | 423.3604 | 508 | 564.8531 | 44 | 1.8947e-05 | 4.5751 | 1.1532 | 152.5921 | 620.4233 | 2.3816 | 0.82537 | 38.7765 | 1.0356 | 4.89e-05 | 1.6362e-05 | 0.37402 | 0.74951 | {36477985-18D9-4EA3-B6F2-3100FB0B3657} | 24101103 | HALF MOON BAY 1103 | 6012 | 37.2428 | -122.3663 | HALF MOON BAY 11036012 | 100 | 63 | 23308.849 | 15443.639 | 7865.21 | 8085.8325 | 5491.2938 | 0.00071993 | 0.00083366 | 2.2282 | 11.5455 | 2673 | 0.0021516 | 2112 | 0 | 0 | 5.0243 | 721 | 0
Central Valley | 6376 | 40 | 54.3434 | 779 | 392.7332 | 50 | 9.096e-06 | 10.0541 | 9.391 | 527.5984 | 12061.358 | 67.7262 | 0.20845 | 17.7029 | 0.92102 | 4.8358e-05 | 6.2031e-05 | 0.051348 | 0.13837 | {D8E71690-B481-4860-BE72-8B484DD0017D} | 163160401 | PINECREST 0401 | 1818 | 38.1883 | -119.9936 | PINECREST 04011818 | 40 | 260 | 13450.7827 | 5092.2491 | 8358.5336 | 5011.2665 | 8179.3979 | 0.0031015 | 0.0004548 | 1.3586 | 15.58 | 2117 | 0.0024179 | 2113 | 0 | 0 | 3.1139 | 2427 | 0
Central Coast | 7302 | 1776 | 3589.4485 | 2451 | 3945.1367 | 69 | 0.00013262 | 0.41107 | 9.8478 | 64.7873 | 689.6628 | 16.2393 | 0.86636 | 6.8703 | 1.0061 | 4.7521e-05 | 0.00075992 | 0.7246 | 0.90984 | {6763B940-A4FC-4294-830C-EA07CE726C5F} | 82931101 | POINT MORETTI 1101 | 36516 | 37.0789 | -122.1338 | POINT MORETTI 110136516 | 95 | 118 | 13904.473 | 6707.2903 | 7197.1827 | 6707.2903 | 7197.1827 | 0.052434 | 0.0091506 | 2.0211 | 35.5217 | 528 | 0.003279 | 2114 | 0 | 0 | 4.1677 | 2816 | 0
Central Coast | 7300 | 9 | 11.0494 | 52 | 30.6371 | 17 | 1.4962e-05 | 3.2891 | 1.1268 | 154.3111 | 583.295 | 1.2478 | 8.3714 | 434.8308 | 1.3894 | 4.6802e-05 | 1.2757e-05 | 0.17308 | 0.36065 | {97435072-7F09-4357-A9C1-20AF42401B11} | 83182101 | LLAGAS 2101 | 1451 | 37.006 | -121.5107 | LLAGAS 21011451 | 88 | 70 | 20751.1809 | 14798.7124 | 5952.4685 | 9962.9329 | 2549.2646 | 0.00021686 | 0.00025435 | 1.2277 | 3.0588 | 2749 | 0.00079564 | 2115 | 0 | 0 | 6.1907 | 1719 | 0
North Valley | 4887 | 139 | 185.2732 | 649 | 421.7364 | 92 | 5.4511e-06 | 11.176 | 3.4554 | 612.2788 | 12286.864 | 68.9728 | 0.4786 | 15.8652 | 1.0451 | 4.6558e-05 | 1.1152e-05 | 0.21418 | 0.43931 | {CAAE778D-9C35-4E23-898C-4B832CDD3B89} | 102812101 | BIG MEADOWS 2101 | 2474 | 40.1714 | -121.0848 | BIG MEADOWS 21012474 | 146 | 216 | 23480.9608 | 13446.528 | 10034.4328 | 12716.7551 | 7940.5101 | 0.001026 | 0.0005015 | 1.3329 | 7.0543 | 2774 | 0.0042833 | 2116 | 0 | 0 | 7.9018 | 564 | 0
Bay Area | 7853 | 58 | 117.9633 | 315 | 263.7724 | 50 | 6.4258e-05 | 1.4946 | 0.0026111 | 6.2541 | 25.7899 | 7.9135e-05 | 0 | 4.7547 | 1.0041 | 4.5984e-05 | 3.6377e-05 | 0.18413 | 0.44722 | {064EA0EC-DFDE-4FA8-8393-49958A6F3357} | 14341106 | VALLEY VIEW 1106 | P166 | 37.9495 | -122.2693 | VALLEY VIEW 1106P166 | 39 | 26 | 8127.8774 | 7343.1116 | 784.7657 | 7008.3242 | 526.3287 | 0.0018189 | 0.0032129 | 2.0339 | 6.3 | 2383 | 0.0022992 | 2117 | 0 | 0 | 4.3548 | 2075 | 0
Bay Area | 7759 | 118 | 316.0349 | 192 | 344.5308 | 42 | 5.5989e-05 | 0.76188 | 0.0087775 | 0.61223 | 3.4025 | 3.4933e-05 | 0.73825 | 27.612 | 1.037 | 4.5551e-05 | 3.1536e-05 | 0.61458 | 0.91729 | {8F1701AB-AC20-48A5-8989-61140107D373} | 42491102 | SAUSALITO 1102 | 1268 | 37.8422 | -122.4943 | SAUSALITO 11021268 | 75 | 117 | 10945.5556 | 8059.3403 | 2886.2153 | 8059.3403 | 2886.2153 | 0.0013245 | 0.0023515 | 2.6783 | 4.5714 | 2448 | 0.0019131 | 2118 | 0 | 0 | 5.0078 | 2829 | 0
Central Valley | 9147 | 1 | 1.3586 | 21 | 9.4814 | 8 | 7.8972e-06 | 6.0096 | 1.9934 | 292.7453 | 3501.043 | 20.9313 | 0 | 17.5155 | 1.0025 | 4.4597e-05 | 1.1943e-05 | 0.047619 | 0.14329 | {3E72B6B4-2ACF-4DC3-9DE3-FC6C6A9FFD94} | 254061102 | DUNLAP 1102 | 778286 | 36.717 | -118.9672 | DUNLAP 1102778286 | 6 | 4 | 4223.2815 | 4188.0047 | 35.2768 | 4188.0047 | 35.2768 | 9.5548e-05 | 6.3177e-05 | 1.3586 | 2.625 | 2764 | 0.00035677 | 2119 | 0 | 0 | 2.6023 | 740 | 0
Central Valley | 2475 | 600 | 850.0222 | 2159 | 1577.805 | 66 | 5.8512e-05 | 0.76893 | 26.488 | 21.7049 | 93.0064 | 4.7724 | 0.24013 | 2.5686 | 2.076 | 4.3598e-05 | 0.00080344 | 0.27791 | 0.53874 | {140F24BC-87D9-4984-9742-733B7440732D} | 163661702 | MIWUK 1702 | 8090 | 38.0489 | -120.2345 | MIWUK 17028090 | 128 | 489 | 28900.9097 | 6478.2235 | 22422.6863 | 6478.2235 | 22422.6863 | 0.053027 | 0.0038618 | 1.4167 | 32.7121 | 498 | 0.0028775 | 2120 | 0 | 0 | 4.0254 | 628 | 0
Central Coast | 7253 | 55 | 92.405 | 154 | 138.7694 | 45 | 2.4754e-05 | 2.6031 | 2.0278 | 1723.7955 | 12336.9298 | 45.1975 | 1.0414 | 144.2674 | 1.1084 | 4.346e-05 | 3.5171e-05 | 0.35714 | 0.66589 | {0C7E1298-8ED7-4AF4-8E12-9D89E23F7125} | 253671103 | PANOCHE 1103 | 4008 | 36.6115 | -120.929 | PANOCHE 11034008 | 143 | 133 | 79611.2831 | 56762.8241 | 22848.459 | 56762.8241 | 22848.459 | 0.0015827 | 0.0011139 | 1.6801 | 3.4222 | 2396 | 0.0019557 | 2121 | 0 | 0 | 35.2708 | 1746 | 0
Central Valley | 2429 | 26 | 48.7719 | 216 | 126.6574 | 42 | 7.8905e-05 | 0.97805 | 7.3213 | 262.7314 | 1641.6333 | 15.8866 | 6.5601 | 99.1345 | 1.2679 | 4.3142e-05 | 0.00024893 | 0.12037 | 0.38507 | {FA05D50A-B4CD-4B2A-B744-6E94BBCBA43A} | 162161102 | ELECTRA 1102 | 6014 | 38.3158 | -120.7132 | ELECTRA 11026014 | 65 | 37 | 10545.4756 | 8101.0669 | 2444.4087 | 8101.0669 | 2444.4087 | 0.010455 | 0.003314 | 1.8758 | 5.1429 | 1252 | 0.001812 | 2122 | 0 | 0 | 5.0338 | 1345 | 0
North Valley | 3422 | 1319 | 1787.6937 | 1981 | 2128.3396 | 219 | 7.572e-06 | 7.1263 | 3.1807 | 853.8659 | 18304.4491 | 191.615 | 0.37988 | 52.663 | 1.0874 | 4.3007e-05 | 1.7313e-05 | 0.66583 | 0.83995 | {6FD1FEB7-53BB-4905-92FA-6BF228EE659D} | 103132101 | CRESCENT MILLS 2101 | 2232 | 40.0718 | -120.828 | CRESCENT MILLS 21012232 | 177 | 150 | 45259.2985 | 32432.4236 | 12826.8749 | 22620.3804 | 12026.3735 | 0.0037915 | 0.0016583 | 1.3553 | 9.0457 | 2660 | 0.0094184 | 2123 | 0 | 0 | 14.0556 | 582 | 0
Sierra | 6606 | 375 | 544.4818 | 736 | 708.8555 | 63 | 0.00011594 | 0.4438 | 14.8131 | 131.385 | 1527.1218 | 123.3771 | 1.1269 | 9.9379 | 1.0012 | 4.2384e-05 | 0.0008295 | 0.50951 | 0.76811 | {F62664EC-2775-4F42-885E-6C5354881CBF} | 152481110 | BRUNSWICK 1110 | 63100 | 39.2282 | -121.1005 | BRUNSWICK 111063100 | 112 | 258 | 18804.8282 | 6591.8915 | 12212.9367 | 6591.8915 | 12212.9367 | 0.052259 | 0.007304 | 1.452 | 11.6825 | 485 | 0.0026702 | 2124 | 0 | 0 | 4.096 | 1421 | 0
Central Coast | 6218 | 319 | 657.3792 | 1546 | 1382.7766 | 206 | 3.3714e-05 | 1.5943 | 9.2802 | 255.0532 | 1115.1564 | 33.4224 | 2.9055 | 89.8327 | 1.1156 | 4.1703e-05 | 0.00014809 | 0.20634 | 0.47541 | {FB7A8750-C967-4B2F-BC27-F33BBB5DCEFD} | 182222104 | DEL MONTE 2104 | 3088 | 36.5492 | -121.7318 | DEL MONTE 21043088 | 280 | 229 | 41642.8175 | 24826.2717 | 16816.5458 | 24826.2717 | 16816.5458 | 0.030506 | 0.006945 | 2.0607 | 7.5049 | 1603 | 0.0085907 | 2125 | 0 | 0 | 15.4263 | 1543 | 0
Sierra | 4963 | 0 | 0 | 126 | 57.4227 | 12 | 8.0148e-06 | 11.959 | 0.20731 | 18.3353 | 49.5092 | 0.014506 | 1.927 | 43.6081 | 1.1309 | 4.0928e-05 | 5.161e-06 | 0 | 0 | {7BFD764A-1749-4CCB-A9E4-5D452AEF3E36} | 152591102 | SUMMIT 1102 | 2302 | 39.31 | -120.3389 | SUMMIT 11022302 | 35 | 22 | 2810.8983 | 2346.259 | 464.6394 | 2346.259 | 464.6394 | 6.1932e-05 | 9.6177e-05 |  | 10.5 | 2843 | 0.00049113 | 2126 | 0 | 0 | 1.4579 | 1082 | 0
Central Coast | 219 | 1089 | 2795.2412 | 3296 | 4018.1367 | 256 | 6.9514e-05 | 0.81052 | 2.2713 | 13.3814 | 35.8742 | 0.22168 | 0.99476 | 7.4753 | 1.0085 | 4.0107e-05 | 0.00010629 | 0.3304 | 0.69566 | {2E6975B3-903D-45C9-9C7D-960FEDF8E472} | 83692104 | ROB ROY 2104 | 10960 | 36.9866 | -121.8582 | ROB ROY 210410960 | 596 | 821 | 92994.5172 | 45185.3957 | 47809.1214 | 27847.2688 | 27559.3127 | 0.02721 | 0.017796 | 2.5668 | 12.875 | 1823 | 0.010267 | 2127 | 0 | 0 | 17.3035 | 1728 | 0
Central Coast | 5636 | 790 | 1661.394 | 1551 | 2086.8994 | 116 | 7.0387e-05 | 0.67592 | 2.4052 | 4.2358 | 11.3556 | 0.081967 | 0.33744 | 1.7294 | 1.3113 | 3.9646e-05 | 0.0001314 | 0.50935 | 0.79611 | {A588ED32-95D8-43A3-8FC4-5077DBA91F77} | 83692104 | ROB ROY 2104 | 10954 | 36.9873 | -121.86 | ROB ROY 210410954 | 210 | 346 | 28821.3975 | 11322.6315 | 17498.766 | 11322.6315 | 17498.766 | 0.015242 | 0.0081649 | 2.103 | 13.3707 | 1695 | 0.0045989 | 2128 | 0 | 0 | 7.0356 | 2362 | 0
Sierra | 3387 | 1989 | 2384.7418 | 3507 | 3188.105 | 292 | 0.00010292 | 0.3921 | 13.713 | 86.6874 | 923.3888 | 48.2145 | 1.9342 | 14.5618 | 1.0305 | 3.926e-05 | 0.00076609 | 0.56715 | 0.74801 | {DA254098-CE2F-4B1D-8DCD-E2A142ECA867} | 152491101 | WEIMAR 1101 | 2740 | 39.0343 | -120.9746 | WEIMAR 11012740 | 393 | 527 | 58050.1275 | 30589.1767 | 27460.9508 | 30589.1767 | 27460.9508 | 0.2237 | 0.030051 | 1.199 | 12.0103 | 523 | 0.011464 | 2129 | 0 | 0 | 19.0072 | 565 | 0
Central Valley | 1216 | 662 | 890.3762 | 2184 | 1596.4185 | 427 | 5.9143e-05 | 0.88577 | 1.3326 | 83.2237 | 466.1156 | 6.6535 | 0.96937 | 57.8419 | 1.1916 | 3.8622e-05 | 7.1313e-05 | 0.30311 | 0.55773 | {AFAF5A37-E0AD-4142-ABDE-E616F0022060} | 162211101 | CALAVERAS CEMENT 1101 | 47968 | 38.2323 | -120.5512 | CALAVERAS CEMENT 110147968 | 387 | 299 | 90192.9449 | 65252.4191 | 24940.5258 | 65252.4191 | 24940.5258 | 0.030451 | 0.025254 | 1.345 | 5.1148 | 2044 | 0.016492 | 2130 | 0 | 0 | 40.546 | 1480 | 0
Central Coast | 7700 | 149 | 300.2807 | 324 | 394.4037 | 33 | 4.5357e-05 | 0.81322 | 0.48328 | 231.5263 | 1539.278 | 1.4498 | 1.1407 | 136.6257 | 1.3785 | 3.8384e-05 | 3.9642e-05 | 0.45988 | 0.76135 | {D42BED5F-FA94-4772-B8B5-334F2629EC25} | 182941102 | OTTER 1102 | circuit_breaker | 36.3802 | -121.8989 | OTTER 1102circuit_breaker | 50 | 39 | 11969.4387 | 10718.1318 | 1251.307 | 10537.6394 | 1251.307 | 0.0013082 | 0.0014968 | 2.0153 | 9.8182 | 2346 | 0.0012667 | 2131 | 0 | 0 | 6.5478 | 403 | 0
Bay Area | 816 | 427 | 886.216 | 1205 | 1348.4531 | 92 | 7.5295e-05 | 0.57824 | 1.5143 | 4.2854 | 12.2478 | 0.067301 | 0.83383 | 5.669 | 1.3052 | 3.8195e-05 | 0.00010064 | 0.35436 | 0.65721 | {167EB25B-4A6A-4910-B109-DED2BEFF695B} | 14161101 | ROSSMOOR 1101 | 68920 | 37.8957 | -122.1117 | ROSSMOOR 110168920 | 211 | 385 | 30995.3314 | 11657.1969 | 19338.1345 | 9481.3207 | 17362.7188 | 0.0092587 | 0.0069271 | 2.0754 | 13.0978 | 1847 | 0.0035139 | 2132 | 0 | 0 | 5.8914 | 1548 | 0
Central Coast | 2873 | 255 | 489.2235 | 771 | 778.2711 | 63 | 6.8535e-05 | 0.44367 | 8.1878 | 22.9776 | 218.6467 | 10.4125 | 0.48047 | 2.1366 | 0.93665 | 3.7601e-05 | 0.00039393 | 0.33074 | 0.6286 | {337FC985-3DD3-4483-BEDA-15F859835747} | 83692105 | ROB ROY 2105 | 38430 | 36.9756 | -121.8885 | ROB ROY 210538430 | 481 | 1487 | 77980.3059 | 21756.9518 | 56223.3541 | 8878.6769 | 14071.5162 | 0.024817 | 0.0043177 | 1.9185 | 12.2381 | 953 | 0.0023689 | 2133 | 0 | 0 | 5.517 | 1486 | 0
Central Coast | 5619 | 247 | 723.0786 | 736 | 1018.6066 | 71 | 3.6895e-05 | 1.426 | 5.9703 | 82.2539 | 318.1096 | 4.2036 | 2.4653 | 21.2059 | 1.0326 | 3.6778e-05 | 0.00015214 | 0.3356 | 0.70987 | {9F487EDE-1254-4232-B1F0-1B8CB4720B05} | 182222104 | DEL MONTE 2104 | 9500 | 36.5582 | -121.7507 | DEL MONTE 21049500 | 152 | 137 | 18852.0321 | 10897.0354 | 7954.9966 | 9189.3701 | 6215.35 | 0.010802 | 0.0026196 | 2.9274 | 10.3662 | 1579 | 0.0026112 | 2134 | 0 | 0 | 5.71 | 1729 | 0
Central Valley | 5760 | 28 | 75.83 | 1254 | 613.7737 | 63 | 1.8716e-05 | 1.9538 | 6.0963 | 110.07 | 2653.7967 | 18.7404 | 0.65216 | 3.6285 | 1.0018 | 3.429e-05 | 5.2792e-05 | 0.022329 | 0.12355 | {F823B297-BE7E-454D-B946-D904DF33E9F1} | 162831702 |  | 693441 | 38.1877 | -120.0028 | 693441 | 111 | 288 | 14065.8803 | 6840.8929 | 7224.9874 | 6840.8929 | 7224.9874 | 0.0033259 | 0.0011791 | 2.7082 | 19.9048 | 2214 | 0.0021602 | 2135 | 0 | 0 | 4.2507 | 1298 | 0
Sierra | 2346 | 2674 | 3662.7047 | 5766 | 5279.4995 | 483 | 9.0239e-05 | 0.41098 | 8.4252 | 59.8392 | 554.8192 | 14.6245 | 2.9277 | 19.6873 | 1.0445 | 3.4122e-05 | 0.0004132 | 0.46375 | 0.69376 | {033C2E2D-A850-40FA-9417-37D899E25ED1} | 152241102 | HALSEY 1102 | 39104 | 38.9734 | -121.014 | HALSEY 110239104 | 573 | 856 | 94663.5081 | 48994.5328 | 45668.9753 | 48994.5328 | 45668.9753 | 0.19957 | 0.043585 | 1.3697 | 11.9379 | 924 | 0.016481 | 2136 | 0 | 0 | 30.4438 | 1394 | 0
Central Coast | 571 | 231 | 436.2099 | 501 | 527.186 | 176 | 1.7342e-05 | 2.3874 | 2.2928 | 856.2027 | 5414.514 | 19.544 | 2.1921 | 286.7768 | 1.3727 | 3.4072e-05 | 2.8457e-05 | 0.46108 | 0.82743 | {1C274C9D-0345-4C36-BC5D-8A798BD2686F} | 83392110 | SWIFT 2110 | XR332 | 37.3488 | -121.6156 | SWIFT 2110XR332 | 231 | 130 | 87615.8963 | 79862.0317 | 7753.8646 | 79862.0317 | 7753.8646 | 0.0050085 | 0.0030523 | 1.8884 | 2.8466 | 2486 | 0.0059967 | 2137 | 0 | 0 | 49.624 | 1825 | 0
Bay Area | 1047 | 1 | 3.8162 | 9 | 8.2989 | 2 | 1.7281e-05 | 1.7958 | 12.5359 | 42.6997 | 180.8086 | 2.2666 | 10.3993 | 221.7392 | 1.0188 | 3.3723e-05 | 9.6628e-05 | 0.11111 | 0.45984 | {EC0EDAE1-4E21-4E4A-934D-53BE5B16B2F9} | 13501101 | JARVIS 1101 | MR210 | 37.6189 | -122.0448 | JARVIS 1101MR210 | 298 | 869 | 41912.0278 | 12482.1347 | 29429.8931 | 567.7092 | 443.5853 | 0.00019326 | 3.4562e-05 | 3.8162 | 4.5 | 1870 | 6.7445e-05 | 2138 | 0 | 0 | 0.35276 | 1870 | 0
Bay Area | 4450 | 19 | 34.0329 | 296 | 179.2105 | 38 | 3.8177e-05 | 0.93883 | 1.7884 | 31.1962 | 105.0904 | 2.9575 | 0.88956 | 128.7619 | 1.0895 | 3.2967e-05 | 7.8819e-05 | 0.064189 | 0.1899 | {D9DED303-0FA6-4611-A466-91E33B741947} | 14341106 | VALLEY VIEW 1106 | circuit_breaker | 37.9665 | -122.279 | VALLEY VIEW 1106circuit_breaker | 109 | 111 | 13525.1658 | 8094.566 | 5430.5998 | 5669.0772 | 3290.6448 | 0.0029951 | 0.0014507 | 1.7912 | 7.7895 | 1992 | 0.0012527 | 2139 | 0 | 0 | 3.5226 | 2656 | 0
North Valley | 4796 | 77 | 113.9882 | 203 | 170.6692 | 65 | 9.5512e-05 | 0.4894 | 0.094615 | 430.7703 | 7766.4506 | 2.8376 | 0.3758 | 85.8138 | 1.0519 | 3.279e-05 | 5.0787e-05 | 0.37931 | 0.66789 | {673B1BD0-3EFA-4599-AB2C-B37C28829526} | 103381102 | FRENCH GULCH 1102 | 1462 | 40.6673 | -122.6341 | FRENCH GULCH 11021462 | 59 | 47 | 17366.6565 | 16468.3781 | 898.2784 | 14444.9129 | 690.4935 | 0.0033012 | 0.0062083 | 1.4804 | 3.1231 | 2226 | 0.0021314 | 2140 | 0 | 0 | 8.9756 | 855 | 0
Bay Area | 3405 | 295 | 512.6137 | 1324 | 1096.3479 | 72 | 9.8537e-05 | 0.39667 | 0.37508 | 0.2015 | 0.23951 | 0.0092282 | 0.20993 | 0.77944 | 0.8891 | 3.2695e-05 | 6.4282e-05 | 0.22281 | 0.46756 | {AC6B2CFB-8470-47A8-8CFF-360D120857F5} | 42011107 | SAN RAFAEL 1107 | circuit_breaker | 37.9709 | -122.5273 | SAN RAFAEL 1107circuit_breaker | 239 | 1281 | 63725.3847 | 12784.0174 | 50941.3672 | 7424.3496 | 19460.6246 | 0.0046283 | 0.0070946 | 1.7377 | 18.3889 | 2103 | 0.0023541 | 2141 | 0 | 0 | 4.6133 | 2533 | 0
Bay Area | 5230 | 341 | 527.1403 | 1394 | 1134.7986 | 75 | 9.4978e-05 | 0.37903 | 0.63261 | 0.28465 | 1.1968 | 0.0048879 | 0.087076 | 0.49981 | 0.88021 | 3.0933e-05 | 8.1081e-05 | 0.24462 | 0.46452 | {8BC2020E-62FB-478E-A2C9-53FD6549A421} | 42011108 | SAN RAFAEL 1108 | circuit_breaker | 37.9709 | -122.5273 | SAN RAFAEL 1108circuit_breaker | 250 | 998 | 52093.8696 | 11921.7427 | 40172.1269 | 6729.9719 | 23161.4338 | 0.006081 | 0.0071233 | 1.5459 | 18.5867 | 1974 | 0.00232 | 2142 | 0 | 0 | 4.1818 | 1891 | 0
Central Coast | 2988 | 666 | 875.0203 | 2573 | 1972.6813 | 410 | 2.3368e-05 | 1.6359 | 1.7543 | 241.6035 | 1991.4568 | 6.441 | 0.66113 | 38.5818 | 1.0908 | 3.0887e-05 | 3.1222e-05 | 0.25884 | 0.44357 | {C78621C3-DA62-4FAA-872F-5C934F1DDE39} | 182371111 | LAURELES 1111 | 432 | 36.3975 | -121.6492 | LAURELES 1111432 | 375 | 363 | 106473.6415 | 79055.4755 | 27418.166 | 79055.4755 | 27418.166 | 0.012801 | 0.0095807 | 1.3138 | 6.2756 | 2454 | 0.012664 | 2143 | 0 | 0 | 49.1228 | 2733 | 0
North Coast | 2382 | 1875 | 3209.0354 | 2429 | 3464.228 | 219 | 9.7152e-05 | 0.27469 | 2.1261 | 23.5275 | 131.6704 | 0.50759 | 0.26317 | 3.8387 | 1.5319 | 2.8153e-05 | 0.00015213 | 0.77192 | 0.92633 | {88ABC052-C1CA-454C-9520-7292289269D5} | 42761102 | FORT BRAGG A 1102 | 35592 | 39.3941 | -123.7793 | FORT BRAGG A 110235592 | 268 | 398 | 47830.408 | 21272.3021 | 26558.1059 | 21272.3021 | 26558.1059 | 0.033316 | 0.021276 | 1.7115 | 11.0913 | 1580 | 0.0061655 | 2144 | 0 | 0 | 13.218 | 1143 | 0
Sierra | 147 | 0 | 0 | 154 | 70.3534 | 21 | 8.5367e-06 | 3.4943 | 10.0169 | 20.8464 | 48.5756 | 0.82704 | 4.0764 | 27.5317 | 1.0335 | 2.7968e-05 | 5.7103e-05 | 0 | 0 | {5BBF8789-23F7-470F-B0A3-CCE750BDABFE} | 152591102 | SUMMIT 1102 | circuit_breaker | 39.3194 | -120.379 | SUMMIT 1102circuit_breaker | 58 | 97 | 3657.3155 | 1626.5971 | 2030.7183 | 1626.5971 | 2030.7183 | 0.0011992 | 0.00017927 |  | 7.3333 | 2173 | 0.00058732 | 2145 | 0 | 0 | 1.0107 | 131 | 0
Central Valley | 9546 | 1 | 1.9791 | 7 | 4.1343 | 3 | 4.6587e-05 | 0.60051 | 0.00040594 | 0.10668 | 0.24211 | 8.1959e-07 | 0.081121 | 111.1671 | 0.91445 | 2.7932e-05 | 3.101e-05 | 0.14286 | 0.47871 | {6F5293E8-A883-45E5-9872-AC9FAE469C47} | 163781704 | PEORIA 1704 | 88630 | 37.9006 | -120.5169 | PEORIA 170488630 | 9 | 1 | 1274.0013 | 1252.5971 | 21.4042 | 1252.5971 | 21.4042 | 9.3029e-05 | 0.00013976 | 1.9791 | 2.3333 | 2458 | 8.3796e-05 | 2146 | 0 | 0 | 0.77833 | 1426 | 0
North Coast | 6413 | 352 | 588.9928 | 461 | 639.0589 | 66 | 6.1531e-05 | 0.42653 | 3.1544 | 15.2056 | 111.3041 | 1.2979 | 1.5476 | 11.1906 | 1.0061 | 2.7171e-05 | 0.00013277 | 0.76356 | 0.92166 | {F1237B34-AE98-483F-8E45-6E7314FDEDD2} | 42841111 | GUALALA 1111 | 887180 | 38.7284 | -123.4702 | GUALALA 1111887180 | 113 | 43 | 10398.3199 | 8802.6895 | 1595.6304 | 7924.3024 | 1595.6304 | 0.0087629 | 0.004061 | 1.6733 | 6.9848 | 1686 | 0.0017933 | 2147 | 0 | 0 | 4.9239 | 15 | 0
Central Coast | 8206 | 67 | 175.4048 | 85 | 184.9132 | 23 | 4.0161e-05 | 1.2917 | 0.59189 | 17.71 | 79.2144 | 0.082131 | 0.42343 | 62.0148 | 1.1492 | 2.5865e-05 | 3.3022e-05 | 0.78824 | 0.94858 | {BB161BB9-B628-4038-939A-BDBCD448B75E} | 182941101 | OTTER 1101 | circuit_breaker | 36.3804 | -121.8989 | OTTER 1101circuit_breaker | 84 | 58 | 12237.2257 | 10779.267 | 1457.9587 | 9899.5429 | 1022.5664 | 0.00075951 | 0.00092371 | 2.618 | 3.6957 | 2425 | 0.00059489 | 2148 | 0 | 0 | 6.1513 | 2696 | 0
North Valley | 5225 | 101 | 114.7554 | 342 | 247.1712 | 77 | 2.9471e-05 | 1.3894 | 0.96839 | 341.3386 | 3634.4122 | 3.028 | 1.0135 | 69.682 | 1.08 | 2.5847e-05 | 2.893e-05 | 0.29532 | 0.46428 | {4A0A56A3-602B-4EA0-9D5D-4F9EBD3DE945} | 103732101 | PIT NO 3 2101 | 1386 | 41.0214 | -121.6772 | PIT NO 3 21011386 | 68 | 72 | 15022.9856 | 11052.9537 | 3970.0319 | 10692.089 | 3578.5981 | 0.0022276 | 0.0022692 | 1.1362 | 4.4416 | 2476 | 0.0019902 | 2149 | 0 | 0 | 6.6438 | 871 | 0
Bay Area | 3496 | 424 | 963.9251 | 1373 | 1542.2523 | 150 | 6.6276e-05 | 0.36872 | 1.5055 | 3.0402 | 9.8414 | 0.10566 | 0.27239 | 4.4883 | 1.9079 | 2.5498e-05 | 8.6879e-05 | 0.30881 | 0.62501 | {FAE87638-3327-4270-9C08-0DC3E3B13CC0} | 14671102 | SOBRANTE 1102 | circuit_breaker | 37.905 | -122.2076 | SOBRANTE 1102circuit_breaker | 279 | 490 | 42694.1847 | 16784.222 | 25909.9627 | 16784.222 | 25909.9627 | 0.013032 | 0.0099414 | 2.2734 | 9.1533 | 1932 | 0.0038248 | 2150 | 0 | 0 | 10.4292 | 2504 | 0
Central Valley | 1876 | 219 | 311.5383 | 539 | 434.4491 | 73 | 6.6427e-05 | 0.43258 | 11.0992 | 134.5106 | 637.6348 | 30.5108 | 2.4204 | 65.9486 | 1.111 | 2.4865e-05 | 0.0004051 | 0.40631 | 0.71709 | {90E79228-756C-4E01-AE14-296DCF1179DF} | 163451701 | FROGTOWN 1701 | 6807 | 38.1241 | -120.4507 | FROGTOWN 17016807 | 77 | 112 | 12375.6152 | 7647.5853 | 4728.03 | 7647.5853 | 4728.03 | 0.029572 | 0.0048492 | 1.4225 | 7.3836 | 935 | 0.0018152 | 2151 | 0 | 0 | 4.752 | 2455 | 0
Central Coast | 6692 | 0 | 0 | 1 | 0.45574 | 1 | 1.4211e-05 | 1.7449 |  |  |  |  | 0.5531 | 245.3142 | 1.1372 | 2.4798e-05 | 1.4211e-05 | 0 | 0 | {9864CC4F-02FB-49D3-9AAF-29D5DA95F673} | 182191101 | SAN ARDO 1101 | 93072 | 36.0739 | -120.979 | SAN ARDO 110193072 | 61 | 45 | 14918.0752 | 13409.0058 | 1509.0694 | 1004.5467 | 133.605 | 1.4211e-05 | 1.4211e-05 |  | 1 | 2719 | 2.4798e-05 | 2152 | 0 | 0 | 0.6242 | 734 | 0
Central Coast | 5099 | 114 | 192.6103 | 217 | 250.8514 | 14 | 0.000363 | 0.066431 | 9.6544 | 5.8268 | 24.2076 | 0.3014 | 0.20923 | 1.1725 | 1 | 2.4115e-05 | 0.0016815 | 0.52535 | 0.76783 | {84EE2558-0006-42C6-8836-08F2D7F2DAA3} | 83622104 | CAMP EVERS 2104 | circuit_breaker | 37.0418 | -122.025 | CAMP EVERS 2104circuit_breaker | 237 | 257 | 16251.644 | 7159.1448 | 9092.4992 | 1223.0517 | 1122.4718 | 0.023541 | 0.005082 | 1.6896 | 15.5 | 212 | 0.0003376 | 2153 | 0 | 0 | 0.75997 | 230 | 0
North Coast | 9664 | 1 | 0.97408 | 2 | 1.4011 | 1 | 0.00036089 | 0.066432 |  |  |  |  | 0.081858 | 1.1723 | 1 | 2.3974e-05 | 0.00036089 | 0.5 | 0.69522 | {9A5A8C62-A4BB-4303-B428-2F196D68F00D} | 192221102 | GARBERVILLE 1102 | 2124 | 40.0569 | -123.9756 | GARBERVILLE 11022124 | 8 | 3 | 5591.7393 | 5026.2322 | 565.5071 | 5026.2322 | 565.5071 | 0.00036089 | 0.00036089 | 0.97408 | 2 | 997 | 2.3974e-05 | 2154 | 0 | 0 | 3.1232 | 1596 | 0
Bay Area | 854 | 60 | 154.2443 | 223 | 231.6897 | 32 | 2.2999e-05 | 2.3202 | 1.2823 | 16.1281 | 49.0938 | 0.69312 | 2.1953 | 11.6181 | 1.5431 | 2.3782e-05 | 3.6107e-05 | 0.26906 | 0.66574 | {9F1312F5-B448-48CC-A9C3-FC2DE03C4391} | 13432207 | FAIRVIEW 2207 | M501R | 38.0169 | -122.1409 | FAIRVIEW 2207M501R | 163 | 1093 | 47322.1655 | 7472.5685 | 39849.597 | 3375.143 | 14223.8913 | 0.0011554 | 0.00073598 | 2.5707 | 6.9688 | 2386 | 0.00076101 | 2155 | 0 | 0 | 2.0972 | 2211 | 0
Central Coast | 8613 | 50 | 96.2485 | 202 | 154.8872 | 11 | 4.0585e-05 | 0.59357 | 1.2229 | 106.531 | 343.2977 | 0.91181 | 3.8347 | 85.4889 | 1.0752 | 2.3185e-05 | 4.7207e-05 | 0.24752 | 0.62141 | {744CBA45-CA46-417A-809B-2361EA738493} | 82931101 | POINT MORETTI 1101 | 5074 | 37.0208 | -122.2072 | POINT MORETTI 11015074 | 49 | 85 | 8540.9335 | 4855.8147 | 3685.1187 | 2072.4094 | 1396.896 | 0.00051927 | 0.00044643 | 1.925 | 18.3636 | 2259 | 0.00025504 | 2156 | 0 | 0 | 1.2877 | 1898 | 0
Central Coast | 7628 | 402 | 997.0483 | 1254 | 1473.7268 | 128 | 3.9983e-05 | 0.46937 | 3.3629 | 43.7383 | 181.2486 | 1.4589 | 1.8229 | 25.6602 | 1.0352 | 2.283e-05 | 7.8838e-05 | 0.32057 | 0.67655 | {32A9C949-424C-43B5-963D-82C15E14F50A} | 182222104 | DEL MONTE 2104 | 2762 | 36.558 | -121.7504 | DEL MONTE 21042762 | 270 | 215 | 32363.8604 | 17774.3075 | 14589.5529 | 14335.4933 | 10720.6878 | 0.010091 | 0.0051178 | 2.4802 | 9.7969 | 1990 | 0.0029222 | 2157 | 0 | 0 | 8.9077 | 2028 | 0
North Coast | 1532 | 183 | 359.0439 | 398 | 462.259 | 43 | 5.7813e-05 | 0.61544 | 1.4337 | 2.2753 | 7.163 | 0.12038 | 0.68166 | 5.1671 | 1.1415 | 2.2768e-05 | 5.0987e-05 | 0.4598 | 0.77672 | {003E8DD3-C7CE-4179-B86D-B637E24AA54E} | 43321103 | RINCON 1103 | 472 | 38.4722 | -122.653 | RINCON 1103472 | 149 | 435 | 29642.2125 | 7702.3079 | 21939.9046 | 4843.5768 | 12903.6518 | 0.0021924 | 0.0024859 | 1.962 | 9.2558 | 2222 | 0.00097903 | 2158 | 0 | 0 | 3.0097 | 569 | 0
Central Coast | 1431 | 0 | 0 | 13 | 8.613 | 5 | 3.2985e-05 | 0.69461 | 0 | 0 | 0 | 0 | 1.5168 | 109.684 | 1.1027 | 2.1279e-05 | 2.758e-05 | 0 | 0 | {528CF887-3009-4BDA-941C-23A6FE9B29B6} | 182082103 | LOS OSITOS 2103 | 3010 | 36.2805 | -121.3061 | LOS OSITOS 21033010 | 288 | 442 | 74452.0659 | 49974.2997 | 24477.7662 | 49533.9507 | 24477.7662 | 0.0001379 | 0.00016493 |  | 2.6 | 2498 | 0.0001064 | 2159 | 0 | 0 | 30.779 | 384 | 0
Central Coast | 7288 | 397 | 702.856 | 606 | 820.8174 | 37 | 0.00031731 | 0.066431 | 16.3889 | 12.495 | 41.2189 | 1.136 | 0.10261 | 1.4003 | 1 | 2.1079e-05 | 0.0027505 | 0.65512 | 0.85629 | {A44012CD-0861-4778-ABC7-FDA4AFEB10EB} | 83622106 | CAMP EVERS 2106 | 16000 | 37.0464 | -122.0243 | CAMP EVERS 210616000 | 139 | 220 | 16742.5634 | 6294.2005 | 10448.3628 | 3279.9189 | 5274.3917 | 0.10177 | 0.011741 | 1.7704 | 16.3784 | 116 | 0.00077994 | 2160 | 0 | 0 | 2.038 | 1467 | 0
North Coast | 5169 | 106 | 171.0213 | 193 | 211.7312 | 19 | 9.3527e-05 | 0.22505 | 1.2089 | 121.259 | 794.9627 | 1.6119 | 0.33104 | 42.9802 | 1.0739 | 2.1004e-05 | 0.00010606 | 0.54922 | 0.80773 | {731B8D8A-0D26-4FAC-B904-5F57E7A23907} | 42981101 | ELK 1101 | 1300 | 39.129 | -123.7111 | ELK 11011300 | 79 | 48 | 21302.8938 | 15972.3198 | 5330.574 | 2515.6031 | 1391.9739 | 0.0020152 | 0.001777 | 1.6134 | 10.1579 | 1826 | 0.00039907 | 2161 | 0 | 0 | 1.5631 | 261 | 0
Central Coast | 606 | 7 | 14.6213 | 23 | 22.2786 | 10 | 2.8194e-05 | 0.71241 | 0.40652 | 856.2188 | 4905.334 | 1.9941 | 0.37323 | 79.8245 | 0.92412 | 2.0605e-05 | 2.6115e-05 | 0.30435 | 0.6563 | {8EF9C157-EB82-4F95-9143-D4D285784E19} | 182492105 | HOLLISTER 2105 | 4724 | 36.7269 | -121.2708 | HOLLISTER 21054724 | 188 | 148 | 55281.9322 | 42311.0841 | 12970.848 | 7277.4055 | 321.0405 | 0.00026115 | 0.00028194 | 2.0888 | 2.3 | 2513 | 0.00020605 | 2162 | 0 | 0 | 4.522 | 1806 | 0
Central Coast | 8776 | 0 | 0 | 8 | 3.1631 | 2 | 2.4504e-05 | 0.81668 | 0.0089648 | 1.8993 | 3.7817 | 0.0014245 | 0.33186 | 124.4188 | 1.0243 | 2.0012e-05 | 2.895e-07 | 0 | 0 | {A3EE8121-F4DD-4843-8E3D-4FC7281FCDB4} | 88820401 | COAST RD 0401 | 5134 | 36.9884 | -122.1587 | COAST RD 04015134 | 31 | 18 | 5295.9341 | 4886.1695 | 409.7646 | 465.4637 | 73.695 | 5.7901e-07 | 4.9009e-05 |  | 4 | 2883 | 4.0025e-05 | 2163 | 0 | 0 | 0.28923 | 226 | 0
Central Valley | 6856 | 11 | 17.8084 | 151 | 77.7237 | 32 | 3.9888e-05 | 0.60091 | 4.3776 | 161.0218 | 791.6169 | 4.7341 | 0.1456 | 104.8708 | 1.2658 | 1.9122e-05 | 0.0001109 | 0.072848 | 0.22913 | {F6B2F362-298B-4DEB-8C9E-04B14858212A} | 162161102 | ELECTRA 1102 | circuit_breaker | 38.331 | -120.6727 | ELECTRA 1102circuit_breaker | 17 | 1 | 4246.5703 | 4216.8732 | 29.6971 | 4216.8732 | 29.6971 | 0.0035489 | 0.0012764 | 1.6189 | 4.7188 | 1795 | 0.00061191 | 2164 | 0 | 0 | 2.6202 | 80 | 0
Central Coast | 9623 | 72 | 119.8876 | 123 | 145.6939 | 4 | 0.00028387 | 0.066431 | 0.32181 | 0.37614 | 1.9367 | 0.041396 | 0.0033186 | 0.32976 | 1 | 1.8858e-05 | 0.00018509 | 0.58537 | 0.82287 | {F1794D00-AFE7-4C35-B1DB-EC5AFB91B7A9} | 83622105 | CAMP EVERS 2105 | 95394 | 37.0895 | -122.0928 | CAMP EVERS 210595394 | 28 | 19 | 1633.8847 | 797.3729 | 836.5118 | 797.3729 | 836.5118 | 0.00074037 | 0.0011355 | 1.6651 | 30.75 | 1464 | 7.5431e-05 | 2165 | 0 | 0 | 0.49546 | 1604 | 0
Central Coast | 4629 | 920 | 1884.4079 | 1076 | 1963.2982 | 48 | 0.00028089 | 0.066431 | 11.4666 | 14.4903 | 46.1257 | 0.80169 | 0.33518 | 2.8725 | 1 | 1.866e-05 | 0.0015794 | 0.85502 | 0.95982 | {BA541186-8D15-43B9-BDFB-BAD6936C2F64} | 83622105 | CAMP EVERS 2105 | 74170 | 37.0883 | -122.0885 | CAMP EVERS 210574170 | 91 | 337 | 22627.3489 | 5724.1198 | 16903.2291 | 5724.1198 | 16903.2291 | 0.07581 | 0.013483 | 2.0483 | 22.4167 | 231 | 0.00089567 | 2166 | 0 | 0 | 3.5568 | 1663 | 0
Bay Area | 2007 | 143 | 325.2965 | 336 | 433.6931 | 49 | 2.91e-05 | 0.54332 | 0.52496 | 0.19331 | 0.9317 | 0.0020753 | 0.15702 | 0.90972 | 1.1023 | 1.8066e-05 | 2.7697e-05 | 0.4256 | 0.75006 | {3F882A80-2491-48FC-AFA8-BDC3FFEA4D12} | 13340401 | SPRUCE 0401 | BR316 | 37.9038 | -122.2662 | SPRUCE 0401BR316 | 111 | 960 | 46873.8702 | 6628.9852 | 40244.885 | 6628.9852 | 39980.9131 | 0.0013571 | 0.0014259 | 2.2748 | 6.8571 | 2495 | 0.00088523 | 2167 | 0 | 0 | 4.1191 | 2763 | 0
North Valley | 7834 | 12 | 24.2479 | 30 | 31.4592 | 8 | 3.1248e-05 | 0.75471 | 0.64672 | 135.6064 | 2041.6301 | 23.508 | 1.3241 | 127.8227 | 1.1477 | 1.7889e-05 | 3.032e-05 | 0.4 | 0.77077 | {CEDB41D0-D0A4-4C87-B076-5057F893A246} | 103381101 | FRENCH GULCH 1101 | 1464 | 40.7131 | -122.6357 | FRENCH GULCH 11011464 | 12 | 6 | 1709.0703 | 1371.4854 | 337.585 | 1371.4854 | 337.585 | 0.00024256 | 0.00024998 | 2.0207 | 3.75 | 2468 | 0.00014311 | 2168 | 0 | 0 | 0.8522 | 994 | 0
Sierra | 2075 | 352 | 578.0383 | 922 | 830.4575 | 102 | 6.809e-05 | 0.3035 | 6.3279 | 62.2451 | 571.9677 | 7.4216 | 3.1643 | 31.003 | 1.091 | 1.775e-05 | 0.00025211 | 0.38178 | 0.69605 | {BE1F8937-5DA4-4110-B598-43072F2A4D02} | 152241102 | HALSEY 1102 | 5739 | 38.9696 | -121.0157 | HALSEY 11025739 | 124 | 115 | 18166.7465 | 10731.8696 | 7434.8769 | 10731.8696 | 7434.8769 | 0.025715 | 0.0069452 | 1.6422 | 9.0392 | 1244 | 0.0018105 | 2169 | 0 | 0 | 6.6685 | 947 | 0
Central Coast | 4261 | 46 | 74.5608 | 99 | 107.3031 | 10 | 2.6169e-05 | 0.6501 | 1.4739 | 140.1641 | 665.8318 | 2.9442 | 0.6458 | 102.6544 | 1.0173 | 1.7726e-05 | 3.1751e-05 | 0.46465 | 0.69486 | {C1E68105-3858-4273-9D69-DD27BF248870} | 182731102 | RESERVATION ROAD 1102 | 22136 | 36.5969 | -121.6245 | RESERVATION ROAD 110222136 | 93 | 79 | 14610.5881 | 8902.7374 | 5707.8507 | 1694.8476 | 766.7552 | 0.00031751 | 0.00026169 | 1.6209 | 9.9 | 2443 | 0.00017726 | 2170 | 0 | 0 | 1.0531 | 1203 | 0
North Coast | 9138 | 13 | 16.4075 | 16 | 17.7747 | 3 | 0.00026537 | 0.066432 | 7.6377 | 104.4578 | 1489.8605 | 19.6236 | 0.14971 | 5.6528 | 1.0007 | 1.7629e-05 | 0.0019941 | 0.8125 | 0.92308 | {D8B02D5B-6C13-4C05-89BB-FB46690FC150} | 192171101 | WILLOW CREEK 1101 | circuit_breaker | 40.9477 | -123.6402 | WILLOW CREEK 1101circuit_breaker | 17 | 3 | 563.168 | 437.858 | 125.3101 | 437.858 | 125.3101 | 0.0059824 | 0.0007961 | 1.2621 | 5.3333 | 176 | 5.2886e-05 | 2171 | 0 | 0 | 0.27207 | 454 | 0
Central Coast | 732 | 1 | 1.812 | 3 | 3.1716 | 2 | 3.4185e-05 | 0.39069 | 0.21512 | 4.8927 | 11.7546 | 0.0025287 | 0.099558 | 70.0585 | 1.1405 | 1.7373e-05 | 2.5631e-05 | 0.33333 | 0.57133 | {D9D7498B-EECD-46C9-B5F7-8D9ED4F7E924} | 182331101 | GABILAN 1101 | 3034 | 36.7317 | -121.613 | GABILAN 11013034 | 295 | 497 | 60880.288 | 33368.5845 | 27511.7036 | 558.7507 | 0 | 5.1262e-05 | 6.837e-05 | 1.812 | 1.5 | 2524 | 3.4746e-05 | 2172 | 0 | 0 | 0.34719 | 423 | 0
Central Coast | 8571 | 29 | 45.3648 | 65 | 65.3756 | 3 | 0.00026124 | 0.066431 |  |  |  |  | 0.082596 | 3.8469 | 1 | 1.7354e-05 | 0.00026124 | 0.44615 | 0.69391 | {81F477DE-A079-435A-9F55-2410FEC944BA} | 83040401 | BEN LOMOND 0401 | 5400 | 37.08 | -122.0838 | BEN LOMOND 04015400 | 10 | 12 | 1200.1564 | 712.5707 | 487.5856 | 712.5707 | 487.5856 | 0.00078371 | 0.00078371 | 1.5643 | 21.6667 | 1224 | 5.2063e-05 | 2173 | 0 | 0 | 0.44277 | 95 | 0
Central Coast | 2265 | 38 | 79.0042 | 206 | 176.3747 | 17 | 0.00026024 | 0.066431 | 3.7739 | 2.4036 | 6.6806 | 0.12978 | 0.25534 | 0.37659 | 1 | 1.7288e-05 | 0.00056618 | 0.18447 | 0.44793 | {52BA473C-1BA5-4952-86A7-343CF045CF65} | 83040401 | BEN LOMOND 0401 | 16010 | 37.0886 | -122.0874 | BEN LOMOND 040116010 | 40 | 162 | 10465.0564 | 2728.9115 | 7736.1449 | 2728.9115 | 7736.1449 | 0.009625 | 0.0044242 | 2.0791 | 12.1176 | 718 | 0.0002939 | 2174 | 0 | 0 | 1.6957 | 713 | 0
Central Coast | 5747 | 681 | 1289.5539 | 1207 | 1570.602 | 76 | 0.00025834 | 0.066431 | 9.5831 | 15.8437 | 65.7196 | 1.237 | 0.29908 | 2.568 | 0.98757 | 1.7162e-05 | 0.0013445 | 0.56421 | 0.82106 | {DC9501E4-F6F2-46C0-8391-ADD21969AEDD} | 83040401 | BEN LOMOND 0401 | circuit_breaker | 37.0924 | -122.0964 | BEN LOMOND 0401circuit_breaker | 220 | 570 | 37756.8034 | 12506.4618 | 25250.3416 | 12506.4618 | 25250.3416 | 0.10219 | 0.019634 | 1.8936 | 15.8816 | 283 | 0.0013043 | 2175 | 0 | 0 | 7.7712 | 236 | 0
Central Coast | 8949 | 4 | 4.9841 | 25 | 16.1714 | 2 | 4.05e-05 | 0.40977 | 41.8808 | 853.1053 | 3526.3394 | 147.6861 | 0.48673 | 77.8695 | 1 | 1.6595e-05 | 0.0010509 | 0.16 | 0.3082 | {AAFA242E-CE7C-45BF-A927-201DEB4735C4} | 82831109 | MILPITAS 1109 | XR044 | 37.4385 | -121.8718 | MILPITAS 1109XR044 | 40 | 23 | 3772.893 | 3013.9349 | 758.9582 | 77.0548 | 0 | 0.0021018 | 8.1e-05 | 1.246 | 12.5 | 385 | 3.3191e-05 | 2176 | 0 | 0 | 0.04788 | 77 | 0
Central Coast | 6283 | 57 | 93.377 | 98 | 117.6247 | 3 | 0.00024974 | 0.066431 | 17.9576 | 62.1116 | 305.1102 | 6.2361 | 0.0014749 | 0.5865 | 1 | 1.6591e-05 | 0.0044672 | 0.58163 | 0.79385 | {1F190D24-49B1-4525-8708-03EC335995FB} | 82841101 | BIG BASIN 1101 | 5479 | 37.1292 | -122.113 | BIG BASIN 11015479 | 6 | 13 | 957.6921 | 274.045 | 683.6471 | 274.045 | 683.6471 | 0.013402 | 0.00074923 | 1.6382 | 32.6667 | 45 | 4.9772e-05 | 2177 | 0 | 0 | 0.17028 | 1775 | 0
Central Coast | 6320 | 216 | 438.7536 | 442 | 578.9476 | 18 | 0.00024684 | 0.066431 | 7.6359 | 8.7257 | 32.8188 | 0.37577 | 0.27704 | 1.3685 | 1 | 1.6398e-05 | 0.00083716 | 0.48869 | 0.75785 | {B6D66A77-B522-44A7-B0D4-0D26D50F0307} | 83622105 | CAMP EVERS 2105 | 5577 | 37.0487 | -122.0616 | CAMP EVERS 21055577 | 24 | 130 | 7544.1719 | 1864.9283 | 5679.2435 | 1864.9283 | 5679.2435 | 0.015069 | 0.0044432 | 2.0313 | 24.5556 | 479 | 0.00029517 | 2178 | 0 | 0 | 1.1588 | 2267 | 0
Central Coast | 923 | 715 | 1392.9049 | 1376 | 1761.2377 | 61 | 0.00024517 | 0.066431 | 10.3466 | 7.7935 | 32.3971 | 0.54477 | 0.52314 | 1.3753 | 1 | 1.6287e-05 | 0.0013849 | 0.51962 | 0.79087 | {8B06F25F-237B-4FE8-8F99-17C1FF96A7BD} | 83622105 | CAMP EVERS 2105 | 11384 | 37.0536 | -122.0439 | CAMP EVERS 210511384 | 121 | 422 | 24570.1426 | 6564.1653 | 18005.9773 | 6564.1653 | 18005.9773 | 0.084481 | 0.014956 | 1.9481 | 22.5574 | 277 | 0.00099352 | 2179 | 0 | 0 | 4.0788 | 2046 | 0
Central Coast | 2347 | 240 | 458.8491 | 316 | 502.2225 | 19 | 0.0002423 | 0.066431 | 9.1231 | 13.3441 | 53.3807 | 0.7517 | 0.13484 | 3.2418 | 1.0003 | 1.6097e-05 | 0.0011402 | 0.75949 | 0.91364 | {45C3786B-AE79-4338-94ED-DE73E8F27992} | 83622105 | CAMP EVERS 2105 | 9031 | 37.0726 | -122.0742 | CAMP EVERS 21059031 | 29 | 65 | 5424.3947 | 1758.1932 | 3666.2015 | 1758.1932 | 3666.2015 | 0.021664 | 0.0046038 | 1.9119 | 16.6316 | 348 | 0.00030583 | 2180 | 0 | 0 | 1.0925 | 500 | 0
North Coast | 9616 | 1 | 2.9829 | 1 | 2.9829 | 1 | 0.00020204 | 0.079148 |  |  |  |  | 0 | 17.9854 | 1.0066 | 1.5991e-05 | 0.00020204 | 1 | 1 | {AA9B3AC3-107D-4281-A065-CEC882DC5747} | 192251102 | RIO DELL 1102 | 7124 | 40.4469 | -124.1399 | RIO DELL 11027124 | 6 | 0 | 1081.3743 | 1081.3743 | 0 | 1081.3743 | 0 | 0.00020204 | 0.00020204 | 2.9829 | 1 | 1405 | 1.5991e-05 | 2181 | 0 | 0 | 0.67193 | 895 | 0
Central Coast | 9640 | 7 | 10.7457 | 9 | 11.5444 | 2 | 0.00024047 | 0.066431 | 2.6865 | 5.1148 | 16.0568 | 0.083206 | 0.8208 | 5.9274 | 1 | 1.5975e-05 | 0.00065694 | 0.77778 | 0.93081 | {9C524D92-A5C3-4391-A08F-2E5640BEA3EC} | 83622105 | CAMP EVERS 2105 | 10996 | 37.0748 | -122.0846 | CAMP EVERS 210510996 | 10 | 1 | 1252.9999 | 1226.2093 | 26.7906 | 1226.2093 | 26.7906 | 0.0013139 | 0.00048094 | 1.5351 | 4.5 | 607 | 3.1949e-05 | 2182 | 0 | 0 | 0.76193 | 915 | 0
Sierra | 5464 | 116 | 339.379 | 795 | 653.0742 | 128 | 7.1283e-06 | 1.7388 | 1.3979 | 85.0365 | 964.1601 | 4.4547 | 0.29992 | 17.7038 | 1.0076 | 1.5966e-05 | 8.8163e-06 | 0.14591 | 0.51966 | {3479738B-50FC-4140-94A7-E159A76AE25B} | 152101101 | ALLEGHANY 1101 | 978 | 39.608 | -120.6068 | ALLEGHANY 1101978 | 175 | 224 | 52574.3479 | 46962.403 | 5611.9448 | 17657.6918 | 3049.8644 | 0.0011285 | 0.00091242 | 2.9257 | 6.2109 | 2799 | 0.0020436 | 2183 | 0 | 0 | 10.972 | 1100 | 0
North Valley | 3444 | 48 | 105.1785 | 184 | 168.7551 | 29 | 8.5553e-06 | 1.6805 | 2.9327 | 41.0855 | 210.1452 | 2.9822 | 0.32585 | 15.9816 | 2.5237 | 1.5563e-05 | 1.396e-05 | 0.26087 | 0.62326 | {F5B87947-B1CF-4B32-AB2B-95DA61D92836} | 103181101 | CHESTER 1101 | circuit_breaker | 40.3025 | -121.227 | CHESTER 1101circuit_breaker | 260 | 916 | 49899.8508 | 12954.421 | 36945.4298 | 3248.2591 | 7556.8788 | 0.00040485 | 0.0002481 | 2.1912 | 6.3448 | 2724 | 0.00045133 | 2184 | 0 | 0 | 2.0184 | 215 | 0
Bay Area | 16 | 76 | 129.7141 | 217 | 208.4723 | 20 | 3.4848e-05 | 1.2553 | 3.4374 | 5.3257 | 31.675 | 0.83384 | 2.541 | 6.9427 | 1.0111 | 1.5554e-05 | 6.8837e-05 | 0.35023 | 0.62221 | {5D059BF5-F769-4312-8893-6A2C828C685C} | 42011106 | SAN RAFAEL 1106 | 910 | 37.9752 | -122.5379 | SAN RAFAEL 1106910 | 179 | 1064 | 59384.547 | 11732.4333 | 47652.1137 | 2037.0021 | 6547.9324 | 0.0013767 | 0.00069697 | 1.7068 | 10.85 | 2070 | 0.00031109 | 2185 | 0 | 0 | 1.2657 | 2518 | 0
Central Coast | 3733 | 381 | 753.5169 | 1528 | 1449.9688 | 142 | 4.1495e-05 | 0.74122 | 0.52696 | 1.0182 | 2.9482 | 0.033297 | 1.9401 | 19.8501 | 1.0667 | 1.5546e-05 | 3.4804e-05 | 0.24935 | 0.51968 | {D8F111B1-64B9-41D7-9211-8173FEC05653} | 83371105 | SARATOGA 1105 | LC14 | 37.2814 | -122.0335 | SARATOGA 1105LC14 | 287 | 323 | 36606.4966 | 17941.3763 | 18665.1203 | 15716.535 | 13460.3012 | 0.0049422 | 0.0058923 | 1.9777 | 10.7606 | 2400 | 0.0022075 | 2186 | 0 | 0 | 9.7658 | 1168 | 0
Central Coast | 6797 | 1305 | 2886.1333 | 1392 | 2929.3308 | 78 | 0.00023283 | 0.066431 | 4.8319 | 30.5524 | 226.6338 | 2.5568 | 0.40084 | 6.0427 | 1.0055 | 1.5467e-05 | 0.00067271 | 0.9375 | 0.98525 | {5510A025-B5B2-46F0-8DC5-ADBD6BE8276E} | 83622105 | CAMP EVERS 2105 | 10786 | 37.0927 | -122.097 | CAMP EVERS 210510786 | 119 | 110 | 13530.5337 | 7281.933 | 6248.6007 | 7281.933 | 6248.6007 | 0.052471 | 0.018161 | 2.2116 | 17.8462 | 593 | 0.0012064 | 2187 | 0 | 0 | 4.5248 | 2613 | 0
North Coast | 5172 | 1 | 0.97408 | 1 | 0.97408 | 1 | 9.8902e-05 | 0.15544 |  |  |  |  | 0.51106 | 31.4201 | 1.0155 | 1.5374e-05 | 9.8902e-05 | 1 | 1 | {A8C66523-6BAD-4410-B093-1D69B3A4DEED} | 192381103 | EEL RIVER 1103 | 3820 | 40.578 | -124.2691 | EEL RIVER 11033820 | 182 | 230 | 47604.5207 | 31973.6142 | 15630.9065 | 5191.5083 | 1978.2795 | 9.8902e-05 | 9.8902e-05 | 0.97408 | 1 | 1856 | 1.5374e-05 | 2188 | 0 | 0 | 3.2259 | 66 | 0
Bay Area | 898 | 64 | 159.5387 | 157 | 204.683 | 33 | 1.9799e-05 | 0.77052 | 2.7292 | 3.1178 | 13.2615 | 0.30774 | 0.55334 | 0.24216 | 1.6062 | 1.5316e-05 | 3.8242e-05 | 0.40764 | 0.77944 | {7A791997-7726-43CB-896D-E2720D3FF37F} | 13350402 | WALDO 0402 | circuit_breaker | 37.9094 | -122.3068 | WALDO 0402circuit_breaker | 141 | 1223 | 57299.8729 | 8248.2932 | 49051.5797 | 4721.9877 | 25437.5677 | 0.001262 | 0.00065338 | 2.4928 | 4.7576 | 2361 | 0.00050542 | 2189 | 0 | 0 | 2.9341 | 2695 | 0
Central Coast | 8058 | 190 | 364.1094 | 953 | 841.5652 | 82 | 3.1918e-05 | 0.64997 | 1.0215 | 14.8837 | 43.8937 | 0.11038 | 2.4508 | 13.4139 | 1.0226 | 1.5088e-05 | 3.246e-05 | 0.19937 | 0.43266 | {2B443255-954D-4EC2-B244-9180B8A8FF9D} | 182222104 | DEL MONTE 2104 | 36720 | 36.5217 | -121.7921 | DEL MONTE 210436720 | 181 | 206 | 22281.7997 | 12840.8619 | 9440.9378 | 9052.9085 | 4096.6561 | 0.0026617 | 0.0026173 | 1.9164 | 11.622 | 2433 | 0.0012372 | 2190 | 0 | 0 | 5.6252 | 2217 | 0
Central Coast | 2449 | 16 | 22.5809 | 29 | 28.9971 | 12 | 1.0969e-05 | 1.3476 | 2.3102 | 2032.1237 | 9592.5312 | 32.9046 | 1.3311 | 198.2921 | 1.1849 | 1.5082e-05 | 1.4624e-05 | 0.55172 | 0.77873 | {B8E5DB63-2FB3-475E-A16D-C9AC460D90A7} | 182131101 | GONZALES 1101 | 3094 | 36.5164 | -121.4331 | GONZALES 11013094 | 147 | 105 | 32423.4562 | 25186.6794 | 7236.7767 | 5968.4042 | 5602.0956 | 0.00017549 | 0.00013163 | 1.4113 | 2.4167 | 2713 | 0.00018099 | 2191 | 0 | 0 | 3.7086 | 1772 | 0
Central Coast | 7211 | 204 | 368.0944 | 745 | 679.2958 | 27 | 0.00022348 | 0.066431 | 0.8782 | 1.3667 | 8.6076 | 0.03974 | 0.59546 | 2.2366 | 1.0001 | 1.4846e-05 | 0.00019595 | 0.27383 | 0.54188 | {386E8549-812B-4BD5-AF30-4B8F8F3211D4} | 83622106 | CAMP EVERS 2106 | 11006 | 37.05 | -122.0657 | CAMP EVERS 210611006 | 56 | 138 | 8638.4998 | 3330.3404 | 5308.1594 | 3330.3404 | 5308.1594 | 0.0052906 | 0.0060341 | 1.8044 | 27.5926 | 1424 | 0.00040085 | 2192 | 0 | 0 | 2.0694 | 2511 | 0
Central Coast | 6991 | 65 | 118.9776 | 130 | 156.8221 | 7 | 0.00022211 | 0.066431 | 9.3552 | 23.7465 | 101.0601 | 1.4213 | 0.55468 | 4.1315 | 1 | 1.4755e-05 | 0.0012142 | 0.5 | 0.75868 | {E247FC6E-157B-4272-AEDD-8C777FFAAD92} | 82841101 | BIG BASIN 1101 | 65444 | 37.1278 | -122.1229 | BIG BASIN 110165444 | 15 | 46 | 2594.9274 | 738.7266 | 1856.2008 | 738.7266 | 1856.2008 | 0.0084997 | 0.0015547 | 1.8304 | 18.5714 | 319 | 0.00010328 | 2193 | 0 | 0 | 0.45902 | 1410 | 0
Central Coast | 8862 | 123 | 210.1596 | 250 | 282.505 | 14 | 0.00022202 | 0.066431 | 6.9207 | 11.8203 | 45.0626 | 0.49265 | 0.26802 | 1.2662 | 1 | 1.4749e-05 | 0.00081848 | 0.492 | 0.74391 | {698941ED-3342-4B1B-9444-3C9E83DD3184} | 83622106 | CAMP EVERS 2106 | 834583 | 37.0442 | -122.0777 | CAMP EVERS 2106834583 | 12 | 43 | 3134.546 | 972.7555 | 2161.7905 | 972.7555 | 2161.7905 | 0.011459 | 0.0031083 | 1.7086 | 17.8571 | 487 | 0.00020649 | 2194 | 0 | 0 | 0.60444 | 2757 | 0
Central Coast | 3271 | 441 | 796.3517 | 1595 | 1403.0188 | 87 | 0.00021963 | 0.066431 | 2.1292 | 6.6745 | 25.1 | 0.10848 | 0.18838 | 2.0046 | 1.0007 | 1.459e-05 | 0.0003303 | 0.27649 | 0.5676 | {592F5AE1-0E6F-42C9-A6FF-0D40652C51A7} | 83622105 | CAMP EVERS 2105 | 5146 | 37.0577 | -122.0595 | CAMP EVERS 21055146 | 139 | 235 | 21486.6028 | 9692.8148 | 11793.788 | 9692.8148 | 11793.788 | 0.028736 | 0.019108 | 1.8058 | 18.3333 | 1054 | 0.0012694 | 2195 | 0 | 0 | 6.0228 | 2729 | 0
Central Coast | 463 | 636 | 1108.3336 | 1292 | 1482.077 | 73 | 0.00022322 | 0.064611 | 3.1733 | 7.8433 | 28.7804 | 0.23164 | 0.28703 | 2.1403 | 1.1096 | 1.4337e-05 | 0.00040429 | 0.49226 | 0.74782 | {2110F054-7B33-4168-8EE0-C9A95CFC1232} | 82841101 | BIG BASIN 1101 | 5028 | 37.1284 | -122.1222 | BIG BASIN 11015028 | 119 | 338 | 25127.7627 | 7931.4866 | 17196.2761 | 7931.4866 | 17196.2761 | 0.029513 | 0.016295 | 1.7427 | 17.6986 | 937 | 0.0010466 | 2196 | 0 | 0 | 4.9284 | 1008 | 0
North Valley | 3377 | 55 | 77.0689 | 95 | 97.182 | 9 | 0.00021504 | 0.066431 | 45.8425 | 18.8988 | 83.0469 | 5.8529 | 0.014749 | 0.27168 | 0.88889 | 1.4286e-05 | 0.0035859 | 0.57895 | 0.79304 | {3A3C4FDA-6EA3-4A05-AE15-F95A09F30BC3} | 102831106 | PARADISE 1106 | 1212 | 39.7704 | -121.6136 | PARADISE 11061212 | 97 | 88 | 14157.1519 | 9245.4248 | 4911.7271 | 9061.9313 | 4701.2217 | 0.032273 | 0.0019354 | 1.4013 | 10.5556 | 75 | 0.00012857 | 2197 | 0 | 0 | 5.6308 | 1666 | 0
North Valley | 4273 | 0 | 0 | 2 | 0.71838 | 2 | 6.0294e-05 | 0.18724 |  |  |  |  | 0.49558 | 24.0882 | 1 | 1.4177e-05 | 6.0294e-05 | 0 | 0 | {3F11AD42-8CBD-4A85-ACAE-76F96892C309} | 102541101 | VOLTA 1101 | 1516 | 40.3456 | -121.8925 | VOLTA 11011516 | 146 | 166 | 47565.4635 | 41402.7558 | 6162.7077 | 39161.809 | 5813.2524 | 0.00012059 | 0.00012059 |  | 1 | 2138 | 2.8354e-05 | 2198 | 0 | 0 | 24.334 | 47 | 0
Central Coast | 5106 | 268 | 557.6047 | 286 | 566.7172 | 16 | 0.00020787 | 0.066431 | 11.9149 | 22.788 | 65.8075 | 0.81275 | 0.48382 | 2.4849 | 1 | 1.3809e-05 | 0.001356 | 0.93706 | 0.98392 | {3B4F48D2-D2BA-4DFD-AA73-9AA05B8A162C} | 83622106 | CAMP EVERS 2106 | 1625 | 37.0415 | -122.0901 | CAMP EVERS 21061625 | 19 | 21 | 2309.2116 | 1453.5601 | 855.6514 | 1453.5601 | 855.6514 | 0.021697 | 0.003326 | 2.0806 | 17.875 | 280 | 0.00022095 | 2199 | 0 | 0 | 0.9032 | 2395 | 0
Central Coast | 125 | 649 | 1025.3291 | 1582 | 1563.8966 | 66 | 0.00020752 | 0.066431 | 5.6183 | 26.8751 | 91.7645 | 0.90064 | 0.72308 | 9.0221 | 0.98817 | 1.3786e-05 | 0.00051698 | 0.41024 | 0.65562 | {7121682A-B3AC-4974-A685-FFAEF4CE6C69} | 83622105 | CAMP EVERS 2105 | 5232 | 37.0751 | -122.0541 | CAMP EVERS 21055232 | 111 | 238 | 19670.1579 | 7297.0471 | 12373.1108 | 7297.0471 | 12373.1108 | 0.034121 | 0.013696 | 1.5799 | 23.9697 | 777 | 0.00090985 | 2200 | 0 | 0 | 4.5342 | 2447 | 0
North Coast | 1735 | 416 | 762.1617 | 649 | 883.9308 | 28 | 0.00022853 | 0.059314 | 5.0392 | 12.7266 | 43.3959 | 0.42844 | 0.37976 | 3.9355 | 1.4286 | 1.3359e-05 | 0.00065014 | 0.64099 | 0.86224 | {DD8BA615-FFBA-48E9-84EA-5D20532CD959} | 42811112 | MONTE RIO 1112 | 64682 | 38.4646 | -123.0101 | MONTE RIO 111264682 | 58 | 236 | 10568.603 | 2767.8678 | 7800.7353 | 2767.8678 | 7800.7353 | 0.018204 | 0.0063988 | 1.8321 | 23.1786 | 618 | 0.00037406 | 2201 | 0 | 0 | 1.7199 | 187 | 0
Sierra | 1440 | 633 | 924.8458 | 1532 | 1357.2319 | 133 | 0.00020062 | 0.066432 | 2.2653 | 1.8957 | 6.3166 | 0.11654 | 0.40876 | 1.951 | 0.83462 | 1.3327e-05 | 0.00036249 | 0.41319 | 0.68142 | {A0663868-57FC-4799-ACA3-0DE33205B8E0} | 153082106 | PLACERVILLE 2106 | 19732 | 38.7368 | -120.7839 | PLACERVILLE 210619732 | 326 | 990 | 49915.2263 | 14586.2182 | 35329.0081 | 14586.2182 | 35285.1254 | 0.048211 | 0.026682 | 1.4611 | 11.5188 | 994 | 0.0017725 | 2202 | 0 | 0 | 9.0635 | 634 | 0
Bay Area | 4517 | 13 | 49.6101 | 13 | 49.6101 | 1 | 6.0829e-05 | 0.21902 |  |  |  |  | 1.9358 | 51.0192 | 1.0664 | 1.3323e-05 | 6.0829e-05 | 1 | 1 | {EC65686F-B15A-4CBF-8005-BF1274876E69} | 24101102 | HALF MOON BAY 1102 | circuit_breaker | 37.4689 | -122.4302 | HALF MOON BAY 1102circuit_breaker | 113 | 216 | 13286.4452 | 6459.405 | 6827.0402 | 168.7519 | 61.3025 | 6.0829e-05 | 6.0829e-05 | 3.8162 | 13 | 2130 | 1.3323e-05 | 2203 | 0 | 0 | 0.10486 | 1724 | 0
Central Coast | 3806 | 51 | 115.3907 | 134 | 165.8595 | 35 | 9.7125e-06 | 1.4441 | 0.025635 | 8.143 | 35.9509 | 0.0033979 | 0.95853 | 30.98 | 1.2154 | 1.3239e-05 | 6.7045e-06 | 0.3806 | 0.69571 | {28A92BFD-4CB5-418D-AD6F-813F50DE65A4} | 182052102 | SOLEDAD 2102 | 42506 | 36.4135 | -121.319 | SOLEDAD 210242506 | 295 | 321 | 63718.022 | 45403.9219 | 18314.1 | 13203.3163 | 5144.5021 | 0.00023466 | 0.00033994 | 2.2626 | 3.8286 | 2828 | 0.00046337 | 2204 | 0 | 0 | 8.2042 | 248 | 0
Central Coast | 8034 | 11 | 14.1592 | 35 | 26.6334 | 7 | 1.0132e-05 | 1.4161 | 1.1442 | 1294.1135 | 8749.0625 | 10.0109 | 0.84735 | 193.2588 | 0.8189 | 1.3231e-05 | 1.0295e-05 | 0.31429 | 0.53163 | {27DDD5EE-54A2-4E5E-9658-0DB34C83F134} | 182191101 | SAN ARDO 1101 | 7094 | 36.1124 | -121.038 | SAN ARDO 11017094 | 82 | 63 | 33044.4774 | 26905.8115 | 6138.6659 | 1399.194 | 1588.122 | 7.2068e-05 | 7.0924e-05 | 1.2872 | 5 | 2783 | 9.262e-05 | 2205 | 0 | 0 | 0.86942 | 86 | 0
Central Coast | 6732 | 4 | 4.9109 | 19 | 14.9185 | 8 | 1.1943e-05 | 1.5272 | 0.15069 | 2192.8331 | 16741.5206 | 3.0604 | 1.2862 | 222.1342 | 1.0655 | 1.3218e-05 | 1.0147e-05 | 0.21053 | 0.32918 | {2368E455-7639-40D5-A504-6B0E7FC0F145} | 182492104 | HOLLISTER 2104 | 4403 | 36.8756 | -121.3633 | HOLLISTER 21044403 | 127 | 133 | 45543.881 | 30234.2388 | 15309.6422 | 9894.6539 | 1041.6259 | 8.1173e-05 | 9.554e-05 | 1.2277 | 2.375 | 2786 | 0.00010574 | 2206 | 0 | 0 | 6.1483 | 1047 | 0
Central Coast | 5667 | 460 | 1195.4168 | 981 | 1474.2239 | 90 | 3.3271e-05 | 0.59504 | 4.7594 | 31.6316 | 104.977 | 1.8918 | 1.3191 | 19.4469 | 1.1647 | 1.3053e-05 | 9.9773e-05 | 0.46891 | 0.81088 | {30178FDC-BE0A-4074-95F8-23AFFDDFE15C} | 182371112 | LAURELES 1112 | 2768 | 36.5029 | -121.759 | LAURELES 11122768 | 155 | 204 | 22458.5922 | 12981.6665 | 9476.9257 | 9769.2909 | 5955.8093 | 0.0089796 | 0.0029943 | 2.5987 | 10.9 | 1852 | 0.0011748 | 2207 | 0 | 0 | 6.0704 | 2543 | 0
Central Coast | 632 | 147 | 314.5403 | 563 | 560.8324 | 71 | 0.00019407 | 0.066431 | 1.9574 | 5.1371 | 16.4904 | 0.16236 | 0.40474 | 4.3611 | 1.0079 | 1.2892e-05 | 0.00029544 | 0.2611 | 0.56085 | {91583C6E-961C-4B38-9535-F88F266F69EA} | 83622105 | CAMP EVERS 2105 | 11004 | 37.0792 | -122.0772 | CAMP EVERS 210511004 | 104 | 270 | 20158.5441 | 6906.8406 | 13251.7036 | 6906.8406 | 13251.7036 | 0.020976 | 0.013779 | 2.1397 | 7.9296 | 1135 | 0.00091536 | 2208 | 0 | 0 | 4.2917 | 2632 | 0
North Valley | 5274 | 60 | 81.8169 | 104 | 105.5586 | 9 | 0.00019381 | 0.066431 | 1.0093 | 1.0428 | 3.0587 | 0.037258 | 0.87021 | 4.3459 | 1.0039 | 1.2875e-05 | 0.00019386 | 0.57692 | 0.77508 | {54AC0ECA-BD93-49A2-9B30-909ADBE15177} | 102831106 | PARADISE 1106 | circuit_breaker | 39.7608 | -121.619 | PARADISE 1106circuit_breaker | 189 | 17 | 19716.5439 | 18810.8302 | 905.7138 | 16790.7997 | 905.7138 | 0.0017448 | 0.0017443 | 1.3636 | 11.5556 | 1433 | 0.00011587 | 2209 | 0 | 0 | 10.4333 | 757 | 0
Bay Area | 2058 | 18 | 26.8873 | 47 | 39.4884 | 4 | 0.00019047 | 0.066431 | 0 | 0 | 0 | 0 | 2.2942 | 6.2205 | 1 | 1.2653e-05 | 0.00015589 | 0.38298 | 0.68089 | {0F6B53D0-9013-4B98-984A-58093E66AEF9} | 42711102 | CALISTOGA 1102 | 706 | 38.5851 | -122.5806 | CALISTOGA 1102706 | 211 | 685 | 39396.6725 | 8027.0476 | 31369.6249 | 636.0356 | 847.4083 | 0.00062357 | 0.00076187 | 1.4937 | 11.75 | 1561 | 5.0612e-05 | 2210 | 0 | 0 | 0.39521 | 1064 | 0
North Coast | 5186 | 0 | 0 | 12 | 4.0792 | 3 | 5.8924e-05 | 0.34621 | 28.3596 | 51.2412 | 388.1893 | 20.2638 | 5.2028 | 109.065 | 1.2249 | 1.2576e-05 | 0.0014777 | 0 | 0 | {D876FA1B-2690-498B-84F5-B5DE7D70B75D} | 42561104 | FULTON 1104 | 466 | 38.5441 | -122.8003 | FULTON 1104466 | 45 | 59 | 5216.5808 | 2367.9813 | 2848.5994 | 626.0978 | 322.6202 | 0.0044332 | 0.00017677 |  | 4 | 250 | 3.7728e-05 | 2211 | 0 | 0 | 0.38904 | 439 | 0
Central Coast | 6165 | 91 | 141.4944 | 297 | 259.6625 | 12 | 0.00018716 | 0.066431 | 8.5249 | 6.702 | 21.7143 | 0.43068 | 0.96681 | 1.5474 | 1 | 1.2433e-05 | 0.00078123 | 0.3064 | 0.54492 | {706177F8-BA6A-42DD-94DE-1F1DD0F84610} | 82841102 | BIG BASIN 1102 | 9741 | 37.157 | -122.1289 | BIG BASIN 11029741 | 17 | 55 | 3452.6554 | 1047.536 | 2405.1194 | 1047.536 | 2405.1194 | 0.0093748 | 0.0022459 | 1.5549 | 24.75 | 510 | 0.0001492 | 2212 | 0 | 0 | 0.65091 | 912 | 0
North Valley | 5356 | 741 | 1006.6954 | 1394 | 1387.7368 | 126 | 0.00018248 | 0.068124 | 3.7828 | 731.2796 | 17285.8278 | 374.9738 | 1.9597 | 17.0632 | 1.0656 | 1.2227e-05 | 0.00043383 | 0.53156 | 0.72542 | {C5E3EE8D-D562-41BA-8596-EEF5987F2F11} | 103271101 | ANTLER 1101 | 1384 | 40.8937 | -122.3819 | ANTLER 11011384 | 226 | 432 | 29194.4316 | 14649.7542 | 14544.6774 | 14263.9901 | 14467.7672 | 0.054663 | 0.022993 | 1.3586 | 11.0635 | 887 | 0.0015406 | 2213 | 0 | 0 | 8.8632 | 469 | 0
Central Coast | 7580 | 51 | 115.7589 | 146 | 169.423 | 16 | 0.0001835 | 0.066431 | 1.3291 | 1.3028 | 6.0206 | 0.0062441 | 0.26148 | 1.2226 | 1 | 1.219e-05 | 0.00018786 | 0.34932 | 0.68325 | {3BCDAF7C-1C90-48AD-8ECA-3702D1B4C97A} | 83622104 | CAMP EVERS 2104 | 11048 | 37.0482 | -122.0339 | CAMP EVERS 210411048 | 50 | 24 | 3576.7177 | 2200.0004 | 1376.7173 | 1365.3169 | 1312.859 | 0.0030057 | 0.002936 | 2.2698 | 9.125 | 1457 | 0.00019504 | 2214 | 0 | 0 | 0.84837 | 1457 | 0
North Coast | 8302 | 9 | 20.9959 | 30 | 31.7962 | 3 | 0.00023547 | 0.044288 | 0.097419 | 0.11738 | 0.41623 | 0.0010094 | 0 | 0.042035 | 2.3333 | 1.217e-05 | 7.0058e-05 | 0.3 | 0.66033 | {149DEC4B-D1C4-4F4B-922B-9B5C5A4AE0D1} | 42811111 | MONTE RIO 1111 | circuit_breaker | 38.4712 | -123.012 | MONTE RIO 1111circuit_breaker | 12 | 24 | 1188.0287 | 425.3264 | 762.7023 | 425.3264 | 762.7023 | 0.00021017 | 0.00070641 | 2.3329 | 10 | 2058 | 3.6511e-05 | 2215 | 0 | 0 | 0.26429 | 218 | 0
Sierra | 9412 | 20 | 32.5397 | 36 | 38.1088 | 7 | 0.00018276 | 0.066432 | 0.12908 | 0.22239 | 0.52812 | 6.8171e-05 | 0.439 | 1.6225 | 1 | 1.2141e-05 | 0.00014008 | 0.55556 | 0.85386 | {064C2459-8C22-4F74-A2C9-18905DBD3086} | 153652110 | SHINGLE SPRINGS 2110 | circuit_breaker | 38.6593 | -120.9466 | SHINGLE SPRINGS 2110circuit_breaker | 36 | 14 | 2632.7038 | 2054.39 | 578.3139 | 1202.0334 | 578.3139 | 0.00098058 | 0.0012793 | 1.627 | 5.1429 | 1632 | 8.4988e-05 | 2216 | 0 | 0 | 0.74691 | 468 | 0
Bay Area | 4394 | 47 | 66.7779 | 87 | 88.9445 | 10 | 0.00018249 | 0.066431 | 4.8031 | 475.7763 | 6509.9808 | 89.1453 | 0.50332 | 4.5126 | 1 | 1.2123e-05 | 0.00045007 | 0.54023 | 0.75078 | {6A947491-FB60-4043-BF5D-F50FFBCF57D9} | 43432105 | SILVERADO 2105 | circuit_breaker | 38.4999 | -122.4593 | SILVERADO 2105circuit_breaker | 197 | 581 | 29424.63 | 7383.7458 | 22040.8843 | 958.0432 | 2117.6431 | 0.0045007 | 0.0018249 | 1.4208 | 8.7 | 862 | 0.00012123 | 2217 | 0 | 0 | 0.5953 | 1125 | 0
Central Coast | 5648 | 477 | 919.0326 | 1694 | 1626.7743 | 101 | 0.00018241 | 0.066431 | 3.1118 | 16.9015 | 64.6718 | 0.27384 | 0.20805 | 4.1518 | 0.99054 | 1.2118e-05 | 0.00034024 | 0.28158 | 0.56494 | {90D97D29-641D-4D44-ABC6-DEB499FDF2DF} | 83622106 | CAMP EVERS 2106 | 11044 | 37.0405 | -122.0294 | CAMP EVERS 210611044 | 322 | 797 | 56362.609 | 19987.9543 | 36374.6547 | 12091.4268 | 16910.0847 | 0.034364 | 0.018423 | 1.9267 | 16.7723 | 1028 | 0.0012239 | 2218 | 0 | 0 | 7.5133 | 669 | 0
North Coast | 6649 | 194 | 358.5503 | 383 | 459.2055 | 18 | 0.00017933 | 0.066431 | 7.0997 | 4.1746 | 10.845 | 0.2173 | 0.89356 | 2.1249 | 1.0048 | 1.1913e-05 | 0.00075303 | 0.50653 | 0.78081 | {C4F8319D-D897-4280-8AA8-30DB11490475} | 42811111 | MONTE RIO 1111 | 506 | 38.4692 | -123.0135 | MONTE RIO 1111506 | 45 | 152 | 7522.5812 | 1987.3505 | 5535.2308 | 1987.3505 | 5535.2308 | 0.013555 | 0.0032279 | 1.8482 | 21.2778 | 530 | 0.00021443 | 2219 | 0 | 0 | 1.2349 | 545 | 0
Bay Area | 6410 | 369 | 732.544 | 698 | 925.6833 | 39 | 0.00017741 | 0.066431 | 1.0597 | 11.2977 | 36.522 | 0.19707 | 0.66462 | 4.5651 | 1.0081 | 1.1785e-05 | 0.00017596 | 0.52865 | 0.79135 | {F1CBF452-B2BE-49AF-B311-31158BD82F54} | 24251104 | WOODSIDE 1104 | 3583 | 37.4245 | -122.2736 | WOODSIDE 11043583 | 50 | 109 | 10835.27 | 4480.4665 | 6354.8035 | 4480.4665 | 6354.8035 | 0.0068623 | 0.0069189 | 1.9852 | 17.8974 | 1498 | 0.00045963 | 2220 | 0 | 0 | 2.784 | 377 | 0
North Valley | 3011 | 54 | 71.8983 | 85 | 89.8529 | 16 | 0.00017638 | 0.066431 | 2.2274 | 72.4274 | 841.8227 | 7.9152 | 9.6015 | 25.3308 | 1.021 | 1.1717e-05 | 0.00029292 | 0.63529 | 0.80018 | {5E7DC64A-0B4A-4299-87CB-EE1D39916B3F} | 103271101 | ANTLER 1101 | circuit_breaker | 40.8947 | -122.3808 | ANTLER 1101circuit_breaker | 43 | 14 | 2966.6041 | 2574.4725 | 392.1316 | 2574.4725 | 392.1316 | 0.0046868 | 0.0028221 | 1.3314 | 5.3125 | 1143 | 0.00018747 | 2221 | 0 | 0 | 1.5997 | 1823 | 0
Central Coast | 8417 | 62 | 107.2384 | 69 | 111.5304 | 3 | 0.00017578 | 0.066431 | 0.56286 | 4.0977 | 18.2671 | 0.08751 | 0.75811 | 8.1171 | 1.0015 | 1.1677e-05 | 0.00015082 | 0.89855 | 0.96152 | {DEE9C36C-2C34-4C19-A8C9-7EC73800B8AC} | 82841102 | BIG BASIN 1102 | 12779 | 37.16 | -122.1553 | BIG BASIN 110212779 | 6 | 22 | 1486.4982 | 407.3922 | 1079.1059 | 407.3922 | 1079.1059 | 0.00045246 | 0.00052734 | 1.7297 | 23 | 1588 | 3.5032e-05 | 2222 | 0 | 0 | 0.25314 | 2633 | 0
Central Coast | 7992 | 112 | 192.4066 | 328 | 318.8141 | 15 | 0.00017578 | 0.066431 | 0.39088 | 3.5733 | 19.9924 | 0.021751 | 0.053392 | 0.98074 | 1 | 1.1677e-05 | 0.00012644 | 0.34146 | 0.60351 | {74ADD149-328D-4200-BB7E-7652CB379BD2} | 83622106 | CAMP EVERS 2106 | 7603 | 37.0844 | -122.0048 | CAMP EVERS 21067603 | 16 | 26 | 2861.1452 | 1504.5923 | 1356.5528 | 1504.5923 | 1356.5528 | 0.0018966 | 0.0026367 | 1.7179 | 21.8667 | 1716 | 0.00017516 | 2223 | 0 | 0 | 0.93491 | 1960 | 0
Sierra | 1978 | 10 | 13.7117 | 10 | 13.7117 | 2 | 0.00017448 | 0.066432 |  |  |  |  | 1.4271e-12 | 0.11062 | 1 | 1.1591e-05 | 0.00017448 | 1 | 1 | {D915D781-6781-4960-807E-BD1A4FE75E6E} | 153652108 | SHINGLE SPRINGS 2108 | 51474 | 38.657 | -120.9942 | SHINGLE SPRINGS 210851474 | 170 | 353 | 20581.2914 | 7519.049 | 13062.2424 | 394.2246 | 0 | 0.00034896 | 0.00034896 | 1.3712 | 5 | 1506 | 2.3182e-05 | 2224 | 0 | 0 | 0.24496 | 1622 | 0
Bay Area | 4979 | 136 | 226.3775 | 501 | 441.1842 | 31 | 0.00017444 | 0.066432 | 1.4995 | 8.3494 | 18.542 | 0.10016 | 0.51513 | 5.7056 | 1.0011 | 1.1588e-05 | 0.00020109 | 0.27146 | 0.51311 | {0C4874FF-D222-478C-B9D7-BED0F08FA35C} | 24251101 | WOODSIDE 1101 | 8522 | 37.3955 | -122.2467 | WOODSIDE 11018522 | 270 | 303 | 32017.8039 | 15127.8447 | 16889.9592 | 3168.3928 | 2399.6585 | 0.0062339 | 0.0054076 | 1.6645 | 16.1613 | 1409 | 0.00035924 | 2225 | 0 | 0 | 1.9687 | 1933 | 0
Bay Area | 6764 | 28 | 87.4257 | 70 | 110.1334 | 6 | 8.1644e-05 | 0.18723 | 0 | 0.22239 | 0.058114 | 0 | 0.12058 | 41.3417 | 1.2529 | 1.1506e-05 | 4.1795e-05 | 0.4 | 0.79382 | {7E93EFF6-2E9C-40C7-BE6F-763B6DBD01F0} | 42491102 | SAUSALITO 1102 | 1500 | 37.8626 | -122.4996 | SAUSALITO 11021500 | 10 | 20 | 3433.3767 | 2046.0654 | 1387.3113 | 1851.8444 | 0 | 0.00025077 | 0.00048986 | 3.1223 | 11.6667 | 2313 | 6.9038e-05 | 2226 | 0 | 0 | 1.1507 | 2760 | 0
North Coast | 8385 | 3 | 3.558 | 7 | 5.2209 | 3 | 0.00017225 | 0.066432 | 0 | 0 | 0 | 0 | 0 | 0.64572 | 1 | 1.1443e-05 | 9.8026e-05 | 0.42857 | 0.6815 | {D79DDEF4-123C-4149-A834-7D55A5080178} | 192311141 | FRUITLAND 1141 | 8746 | 40.3969 | -123.943 | FRUITLAND 11418746 | 18 | 7 | 1621.1382 | 1353.7785 | 267.3597 | 895.774 | 249.973 | 0.00029408 | 0.00051676 | 1.186 | 2.3333 | 1863 | 3.4329e-05 | 2227 | 0 | 0 | 0.55661 | 98 | 0
Bay Area | 7215 | 99 | 181.8472 | 447 | 390.8123 | 32 | 0.00017092 | 0.066432 | 0.71045 | 0.89641 | 2.2618 | 0.010478 | 0.20866 | 2.0244 | 1.0003 | 1.1354e-05 | 0.00015247 | 0.22148 | 0.46531 | {BBE63A51-7F9A-46A0-A46D-25679A3F93F8} | 24251101 | WOODSIDE 1101 | 2299 | 37.387 | -122.2372 | WOODSIDE 11012299 | 40 | 134 | 8106.4187 | 2949.4431 | 5156.9757 | 2949.4431 | 5156.9757 | 0.004879 | 0.0054694 | 1.8368 | 13.9688 | 1578 | 0.00036334 | 2228 | 0 | 0 | 1.8327 | 2047 | 0
Central Coast | 3490 | 3 | 9.2389 | 4 | 9.9187 | 1 | 6.6834e-06 | 1.6687 |  |  |  |  | 7.5509 | 250.3416 | 1.2235 | 1.1152e-05 | 6.6834e-06 | 0.75 | 0.93147 | {B73F7608-4D30-4162-A279-F1B71A76D86D} | 83182106 | LLAGAS 2106 | XR146 | 36.9737 | -121.5188 | LLAGAS 2106XR146 | 188 | 152 | 46729.0956 | 32678.168 | 14050.9276 | 2566.3115 | 511.184 | 6.6834e-06 | 6.6834e-06 | 3.0796 | 4 | 2830 | 1.1152e-05 | 2229 | 0 | 0 | 1.5946 | 291 | 0
Central Coast | 5661 | 123 | 238.3254 | 164 | 257.9818 | 9 | 0.00025466 | 0.044287 | 14.0397 | 31.0397 | 83.4897 | 1.55 | 0.0011062 | 8.3105 | 2.382 | 1.1068e-05 | 0.0017315 | 0.75 | 0.92381 | {A37409D5-7086-445E-AAD3-796DE84F477C} | 82841101 | BIG BASIN 1101 | 9773 | 37.1288 | -122.1141 | BIG BASIN 11019773 | 11 | 38 | 2296.2089 | 724.7249 | 1571.484 | 724.7249 | 1571.484 | 0.015584 | 0.0022919 | 1.9376 | 18.2222 | 203 | 9.9609e-05 | 2230 | 0 | 0 | 0.45032 | 1675 | 0
North Coast | 2826 | 301 | 558.6786 | 355 | 589.3616 | 26 | 0.00018754 | 0.058765 | 6.4751 | 22.2073 | 92.5323 | 0.70101 | 1.5064 | 3.5662 | 1.4617 | 1.0919e-05 | 0.00068146 | 0.84789 | 0.94794 | {8E83A400-F142-4678-B5FC-E0505BD0823D} | 42811111 | MONTE RIO 1111 | 1701 | 38.4728 | -123.0474 | MONTE RIO 11111701 | 25 | 88 | 9391.7922 | 2197.6127 | 7194.1794 | 2197.6127 | 7194.1794 | 0.017718 | 0.004876 | 1.8561 | 13.6538 | 587 | 0.0002839 | 2231 | 0 | 0 | 1.3655 | 700 | 0
Bay Area | 9376 | 35 | 64.6748 | 95 | 95.477 | 6 | 0.00016308 | 0.066431 | 0.42523 | 0.22239 | 0.0031646 | 1.3457e-06 | 0.7017 | 0.071313 | 1 | 1.0833e-05 | 0.00014706 | 0.36842 | 0.67739 | {43C4E506-67D9-4305-AA7A-65C3BF977D22} | 43091103 | GREENBRAE 1103 | 6083 | 37.9316 | -122.5427 | GREENBRAE 11036083 | 9 | 72 | 3396.9482 | 549.3456 | 2847.6026 | 549.3456 | 2847.6026 | 0.00088235 | 0.00097846 | 1.8479 | 15.8333 | 1609 | 6.5e-05 | 2232 | 0 | 0 | 0.34135 | 1284 | 0
Sierra | 546 | 105 | 170.5093 | 267 | 250.2726 | 40 | 0.00016146 | 0.066432 | 4.2396 | 1.7321 | 7.7338 | 0.17367 | 0.52467 | 1.8233 | 0.975 | 1.0726e-05 | 0.00041514 | 0.39326 | 0.68129 | {779A3152-24AF-4508-86CF-CDD542CFE4FC} | 152481107 | BRUNSWICK 1107 | 50008 | 39.2226 | -121.0515 | BRUNSWICK 110750008 | 309 | 1183 | 62065.3926 | 12726.754 | 49338.6386 | 3726.9612 | 13172.9611 | 0.016606 | 0.0064583 | 1.6239 | 6.675 | 919 | 0.00042903 | 2233 | 0 | 0 | 2.3158 | 2618 | 0
Central Coast | 8373 | 70 | 92.3644 | 136 | 130.6363 | 10 | 0.00015944 | 0.066432 | 10.8361 | 14.3715 | 53.8672 | 0.96409 | 0.29956 | 2.0654 | 1 | 1.0592e-05 | 0.0011462 | 0.51471 | 0.70703 | {F50933AC-5B82-417B-BA6F-799563320ECE} | 83622106 | CAMP EVERS 2106 | circuit_breaker | 37.0419 | -122.0251 | CAMP EVERS 2106circuit_breaker | 91 | 171 | 10540.9442 | 3738.5003 | 6802.4439 | 828.2056 | 359.1482 | 0.011462 | 0.0015944 | 1.3195 | 13.6 | 344 | 0.00010592 | 2234 | 0 | 0 | 0.51462 | 617 | 0
Central Coast | 5867 | 826 | 1620.1312 | 1048 | 1757.3154 | 46 | 0.00015706 | 0.066431 | 6.0029 | 31.3681 | 171.1196 | 1.7149 | 0.63948 | 5.1897 | 1.0031 | 1.0434e-05 | 0.00046792 | 0.78817 | 0.92194 | {1E00CF74-EEE2-4457-A6AF-F5C49F5CE48D} | 82931101 | POINT MORETTI 1101 | 39126 | 37.0778 | -122.1326 | POINT MORETTI 110139126 | 58 | 77 | 8714.3148 | 3614.1844 | 5100.1303 | 3614.1844 | 5100.1303 | 0.021524 | 0.0072246 | 1.9614 | 22.7826 | 833 | 0.00047994 | 2235 | 0 | 0 | 2.2457 | 1095 | 0
North Coast | 7098 | 64 | 87.5223 | 108 | 108.4653 | 17 | 0.00015529 | 0.066432 | 3.1093 | 106.4949 | 2313.5278 | 45.3134 | 0.20243 | 5.4681 | 1.0016 | 1.0316e-05 | 0.00051204 | 0.59259 | 0.80692 | {A739E4CD-6027-447C-8193-CB877EF24141} | 192171103 | WILLOW CREEK 1103 | circuit_breaker | 40.9477 | -123.6401 | WILLOW CREEK 1103circuit_breaker | 118 | 220 | 12197.3112 | 6235.9798 | 5961.3313 | 6235.9798 | 5961.3313 | 0.0087048 | 0.0026399 | 1.3675 | 6.3529 | 778 | 0.00017537 | 2236 | 0 | 0 | 3.8749 | 1061 | 0
Sierra | 8182 | 30 | 51.6736 | 121 | 82.8796 | 14 | 0.00013912 | 0.073698 | 2.3243 | 3.7362 | 12.4142 | 0.081903 | 1.2808 | 17.1439 | 1.0107 | 1.0215e-05 | 0.00024544 | 0.24793 | 0.62348 | {D119674C-FF38-4F45-A342-82E8B18FF02E} | 153612109 | CLARKSVILLE 2109 | 51744 | 38.7105 | -121.0745 | CLARKSVILLE 210951744 | 56 | 33 | 4367.807 | 2887.7792 | 1480.0277 | 1413.2019 | 853.9468 | 0.0034361 | 0.0019477 | 1.7225 | 8.6429 | 1262 | 0.00014301 | 2237 | 0 | 0 | 0.87812 | 1186 | 0
Central Coast | 3714 | 186 | 271.8139 | 841 | 684.78 | 27 | 0.00015336 | 0.066432 | 0.90443 | 18.6943 | 53.2618 | 0.027741 | 0.11607 | 0.92192 | 1 | 1.0188e-05 | 0.00014118 | 0.22117 | 0.39694 | {4C9A65DC-55B1-4CE2-AD64-FA340511DC8F} | 83622103 | CAMP EVERS 2103 | 55638 | 37.0139 | -122.0341 | CAMP EVERS 210355638 | 82 | 234 | 16225.6931 | 5626.2533 | 10599.4398 | 2080.9167 | 2069.4858 | 0.0038118 | 0.0041406 | 1.4614 | 31.1481 | 1627 | 0.00027507 | 2238 | 0 | 0 | 1.293 | 964 | 0
Bay Area | 6059 | 1 | 1.945 | 1 | 1.945 | 1 | 0.00021421 | 0.066431 |  |  |  |  | 0 | 0.092257 | 1 | 1.423e-05 | 0.00021421 | 1 | 1 | {F3C44BD4-C837-40EB-9584-B17B6404063F} | 42811113 | MONTE RIO 1113 | 250 | 38.4816 | -123.0112 | MONTE RIO 1113250 | 24 | 81 | 5141.508 | 1971.2642 | 3170.2438 | 1971.2642 | 3170.2438 | 0.00021421 | 0.00021421 | 1.945 | 1 | 1367 | 1.423e-05 | 2239 | 0 | 0 | 1.2249 | 1937 | 0
North Coast | 6059 | 212 | 408.029 | 355 | 485.3214 | 19 | 0.00015007 | 0.066431 | 3.8449 | 8.3034 | 39.3114 | 0.31344 | 0.29099 | 2.2715 | 1 | 9.9696e-06 | 0.00036003 | 0.59718 | 0.84074 | {F3C44BD4-C837-40EB-9584-B17B6404063F} | 42811113 | MONTE RIO 1113 | 250 | 38.4816 | -123.0112 | MONTE RIO 1113250 | 24 | 81 | 5141.508 | 1971.2642 | 3170.2438 | 1971.2642 | 3170.2438 | 0.0068406 | 0.0028514 | 1.9247 | 18.6842 | 1000 | 0.00018942 | 2239 | 0 | 0 | 1.2249 | 1985 | 0
Central Valley | 7192 | 0 | 0 | 2 | 0.70188 | 1 | 0.00015283 | 0.066431 |  |  |  |  | 0.0044248 | 3.3405 | 1 | 1.0153e-05 | 0.00015283 | 0 | 0 | {76B6EBA6-803A-40C7-99AD-9AD455E44C8B} | 163201101 | WEST POINT 1101 | L2219 | 38.4909 | -120.5268 | WEST POINT 1101L2219 | 58 | 88 | 10125.0934 | 5487.8839 | 4637.2094 | 5487.8839 | 4637.2094 | 0.00015283 | 0.00015283 |  | 2 | 1575 | 1.0153e-05 | 2240 | 0 | 0 | 3.41 | 1694 | 0
Bay Area | 388 | 111 | 210.5198 | 464 | 422.8435 | 28 | 0.00015204 | 0.066432 | 0.39327 | 1.2246 | 3.2164 | 0.014351 | 0.19793 | 1.4698 | 1 | 1.01e-05 | 0.00011567 | 0.23922 | 0.49787 | {4CEFDA18-FC78-4DED-AF3C-6DA953E1658C} | 24251104 | WOODSIDE 1104 | 9032 | 37.4292 | -122.2559 | WOODSIDE 11049032 | 216 | 253 | 24686.643 | 12668.8794 | 12017.7637 | 6850.4288 | 6199.2336 | 0.0032387 | 0.0042571 | 1.8966 | 16.5714 | 1771 | 0.0002828 | 2241 | 0 | 0 | 4.2567 | 2004 | 0
North Coast | 7484 | 244 | 425.8028 | 371 | 491.9836 | 35 | 0.00015194 | 0.066431 | 8.1166 | 10.5015 | 31.538 | 0.5476 | 0.65904 | 2.8147 | 0.97212 | 1.0093e-05 | 0.00054364 | 0.65768 | 0.86548 | {C70CA0FD-CD6F-47B4-AE85-ADF07161D721} | 42811112 | MONTE RIO 1112 | 212 | 38.475 | -123.0028 | MONTE RIO 1112212 | 49 | 208 | 13631.031 | 3618.1726 | 10012.8583 | 3618.1726 | 10012.8583 | 0.019027 | 0.0053178 | 1.7451 | 10.6 | 744 | 0.00035327 | 2242 | 0 | 0 | 2.2482 | 1077 | 0
Central Coast | 6747 | 432 | 899.1287 | 623 | 1014.113 | 25 | 0.00015016 | 0.066431 | 5.3269 | 31.4729 | 236.4087 | 2.6497 | 0.41965 | 9.63 | 1.0094 | 9.9751e-06 | 0.00056953 | 0.69342 | 0.88662 | {77124F72-2A10-485B-AF25-5FB9845AECBA} | 183582101 | BURNS 2101 | circuit_breaker | 37.0952 | -122.1442 | BURNS 2101circuit_breaker | 44 | 41 | 5159.4392 | 2668.3535 | 2491.0858 | 2668.3535 | 2491.0858 | 0.014238 | 0.0037539 | 2.0813 | 24.92 | 712 | 0.00024938 | 2243 | 0 | 0 | 1.658 | 1594 | 0
North Valley | 3669 | 5 | 6.7929 | 44 | 25.3556 | 3 | 0.00014973 | 0.066431 | 10.9931 | 24.5865 | 134.2216 | 2.0219 | 1.0347 | 1.55 | 1.0007 | 9.9469e-06 | 0.00097545 | 0.11364 | 0.26791 | {1341CA63-432E-4CD8-BB46-467A27C9C55D} | 102831104 | PARADISE 1104 | 920400 | 39.7561 | -121.5721 | PARADISE 1104920400 | 409 | 45 | 27929.6183 | 25870.0682 | 2059.5501 | 7211.2587 | 70.7206 | 0.0029263 | 0.0004492 | 1.3586 | 14.6667 | 423 | 2.9841e-05 | 2244 | 0 | 0 | 4.4809 | 160 | 0
North Valley | 9863 | 2 | 1.9445 | 3 | 2.5704 | 1 | 0.00014844 | 0.066431 |  |  |  |  | 0 | 28.1217 | 1 | 9.8611e-06 | 0.00014844 | 0.66667 | 0.75651 | {B00B32D2-7E6B-47E8-9895-8153D924AA94} | 101321101 | PIT NO 5 1101 | 90846 | 41.0351 | -121.9299 | PIT NO 5 110190846 | 4 | 0 | 149.205 | 149.205 | 0 | 149.205 | 0 | 0.00014844 | 0.00014844 | 0.97225 | 3 | 1600 | 9.8611e-06 | 2245 | 0 | 0 | 0.092712 | 961 | 0
North Coast | 1812 | 1179 | 2164.0166 | 1538 | 2334.4338 | 112 | 0.00014792 | 0.064652 | 6.8859 | 85.2961 | 559.5499 | 6.4514 | 0.85094 | 11.0351 | 1.1133 | 9.59e-06 | 0.0005933 | 0.76658 | 0.927 | {2480EF39-65DB-49E5-BB32-DE1887FC85E8} | 43081101 | BIG RIVER 1101 | 3002 | 39.2856 | -123.7932 | BIG RIVER 11013002 | 144 | 124 | 21264.4571 | 13203.7302 | 8060.7269 | 11691.8924 | 6989.8074 | 0.06645 | 0.016567 | 1.8355 | 13.7321 | 676 | 0.0010741 | 2246 | 0 | 0 | 7.265 | 1493 | 0
Sierra | 9899 | 2 | 3.89 | 19 | 11.99 | 1 | 0.00014407 | 0.066432 |  |  |  |  | 0 | 0 | 0 | 9.5707e-06 | 0.00014407 | 0.10526 | 0.32443 | {EB087661-42A5-46E0-BB53-1DC1A49FC6AA} | 152031103 | GRASS VALLEY 1103 | circuit_breaker | 39.209 | -121.0611 | GRASS VALLEY 1103circuit_breaker | 11 | 10 | 433.4571 | 191.1806 | 242.2765 | 191.1806 | 242.2765 | 0.00014407 | 0.00014407 | 1.945 | 19 | 1621 | 9.5707e-06 | 2247 | 0 | 0 | 0.11879 | 1748 | 0
Central Valley | 6857 | 0 | 0 | 3 | 1.8776 | 2 | 0.00014351 | 0.066431 | 7.9806 | 25.8884 | 49.1845 | 0.39275 | 2.7113 | 14.6852 | 1.0033 | 9.5334e-06 | 0.00064291 | 0 | 0 | {716EEA07-8EC7-426F-AA45-1CEE92CFA700} | 163201101 | WEST POINT 1101 | L373 | 38.489 | -120.5365 | WEST POINT 1101L373 | 129 | 182 | 24287.5257 | 12006.0598 | 12281.4659 | 12006.0598 | 12281.4659 | 0.0012858 | 0.00028702 |  | 1.5 | 624 | 1.9067e-05 | 2248 | 0 | 0 | 7.4602 | 2313 | 0
Bay Area | 722 | 48 | 78.6202 | 79 | 97.8806 | 8 | 0.00014313 | 0.066431 | 1.7242 | 3.497 | 17.3752 | 0.10578 | 0.0011062 | 0.080033 | 1 | 9.5085e-06 | 0.00023817 | 0.60759 | 0.80323 | {E61E149E-984B-41E5-BBE8-57BFA4C46C56} | 43432105 | SILVERADO 2105 | 1308 | 38.505 | -122.4747 | SILVERADO 21051308 | 160 | 520 | 33548.4745 | 8622.7598 | 24925.7147 | 812.0716 | 1516.6492 | 0.0019053 | 0.0011451 | 1.6379 | 9.875 | 1281 | 7.6068e-05 | 2249 | 0 | 0 | 0.5046 | 1068 | 0
Central Coast | 3911 | 3 | 3.6831 | 17 | 11.9937 | 6 | 1.2661e-05 | 0.63654 | 0.074059 | 163.2172 | 934.0762 | 0.14434 | 0.93252 | 86.2042 | 1.115 | 9.4913e-06 | 3.2812e-06 | 0.17647 | 0.30709 | {267BC564-377B-4324-BC73-A7BED7B71D6E} | 182071101 | CAMPHORA 1101 | 77978 | 36.4795 | -121.4142 | CAMPHORA 110177978 | 196 | 178 | 47160.0672 | 40895.7342 | 6264.333 | 3393.7443 | 1023.1771 | 1.9687e-05 | 7.5964e-05 | 1.2277 | 2.8333 | 2861 | 5.6948e-05 | 2250 | 0 | 0 | 2.1088 | 350 | 0
Sierra | 3631 | 106 | 214.6689 | 361 | 319.1471 | 30 | 0.00016263 | 0.059788 | 0.52436 | 0.30039 | 2.1811 | 0.0076625 | 0.021062 | 0.16312 | 1.2667 | 9.3801e-06 | 0.000133 | 0.29363 | 0.67263 | {91D53CD4-6008-41E0-B5BC-B59F60B0DDAC} | 153652105 | SHINGLE SPRINGS 2105 | 11172 | 38.6791 | -120.981 | SHINGLE SPRINGS 210511172 | 93 | 165 | 9798.1168 | 3921.2737 | 5876.8431 | 3051.051 | 4960.7277 | 0.0039899 | 0.0048788 | 2.0252 | 12.0333 | 1684 | 0.0002814 | 2251 | 0 | 0 | 1.8958 | 579 | 0
Sierra | 8165 | 18 | 23.8436 | 32 | 31.4119 | 3 | 0.0001406 | 0.066432 | 4.2225 | 15.3452 | 114.6334 | 0.48404 | 4.2729 | 20.8841 | 1.0147 | 9.3401e-06 | 0.00030052 | 0.5625 | 0.75906 | {BCC579AC-C459-46FE-9298-10C2B7376879} | 152481110 | BRUNSWICK 1110 | 94368 | 39.2341 | -121.0598 | BRUNSWICK 111094368 | 33 | 11 | 1100.4887 | 768.9303 | 331.5584 | 431.1432 | 331.5584 | 0.00090156 | 0.00042179 | 1.3246 | 10.6667 | 1123 | 2.802e-05 | 2252 | 0 | 0 | 0.2679 | 818 | 0
Central Valley | 3927 | 24 | 60.9052 | 568 | 301.331 | 102 | 3.5482e-06 | 3.3289 | 3.9422 | 59.946 | 502.8208 | 1.917 | 0.37771 | 10.7255 | 1.009 | 9.3224e-06 | 8.8981e-06 | 0.042254 | 0.20212 | {3474C71F-C417-4DFD-9033-1EBD72D1A9BF} | 254061103 | DUNLAP 1103 | 7080 | 36.7433 | -118.9608 | DUNLAP 11037080 | 111 | 424 | 29854.1139 | 17013.9683 | 12840.1456 | 17013.9683 | 12840.1456 | 0.00090761 | 0.00036192 | 2.5377 | 5.5686 | 2798 | 0.00095088 | 2253 | 0 | 0 | 10.572 | 2678 | 0
Central Coast | 6393 | 394 | 723.0299 | 776 | 930.7601 | 55 | 0.00013974 | 0.066432 | 5.7532 | 15.7246 | 50.4041 | 0.56854 | 3.7671 | 11.1834 | 1.0001 | 9.2835e-06 | 0.000463 | 0.50773 | 0.77682 | {9E68327F-3BBC-4F71-B18E-5E0E2432F769} | 83252102 | PAUL SWEET 2102 | 5291 | 36.9756 | -122.0584 | PAUL SWEET 21025291 | 119 | 103 | 11822.3314 | 6995.8694 | 4826.462 | 5450.0475 | 2065.9615 | 0.025465 | 0.007686 | 1.8351 | 14.1091 | 842 | 0.00051059 | 2254 | 0 | 0 | 3.3865 | 1654 | 0
North Valley | 1503 | 19 | 45.838 | 180 | 120.725 | 29 | 9.164e-06 | 0.88607 | 2.6487 | 19.7093 | 188.0227 | 3.0892 | 0.768 | 6.5025 | 0.95163 | 9.1338e-06 | 1.3318e-05 | 0.10556 | 0.37969 | {CF1292FF-09D7-4946-B3C9-5DF5A5CB48C9} | 102361101 | HAMILTON BRANCH 1101 | circuit_breaker | 40.2692 | -121.0879 | HAMILTON BRANCH 1101circuit_breaker | 145 | 321 | 20873.4192 | 5887.1186 | 14986.3006 | 3577.0016 | 8192.448 | 0.00038623 | 0.00026576 | 2.4125 | 6.2069 | 2737 | 0.00026488 | 2255 | 0 | 0 | 2.2226 | 1099 | 0
North Coast | 4802 | 1261 | 1954.098 | 1889 | 2236.9758 | 166 | 0.00015341 | 0.060029 | 5.2892 | 42.8199 | 236.6849 | 1.8595 | 1.0396 | 12.9505 | 1.4547 | 9.0946e-06 | 0.00049499 | 0.66755 | 0.87354 | {66330EE0-007E-454B-A909-6B12AA6DF153} | 192171103 | WILLOW CREEK 1103 | 5012 | 40.8894 | -123.5579 | WILLOW CREEK 11035012 | 199 | 271 | 25994.6207 | 17863.1995 | 8131.4212 | 17863.1995 | 8131.4212 | 0.082168 | 0.025466 | 1.5496 | 11.3795 | 793 | 0.0015097 | 2256 | 0 | 0 | 11.0997 | 967 | 0
Sierra | 7583 | 85 | 122.4161 | 245 | 192.2813 | 23 | 0.00014095 | 0.063543 | 1.6383 | 6.0364 | 15.3422 | 0.08141 | 1.0629 | 4.5852 | 1.1776 | 8.9357e-06 | 0.00018651 | 0.34694 | 0.63665 | {3255A524-F15F-4D09-B1CC-57364FA652CB} | 152261107 | DIAMOND SPRINGS 1107 | 40353 | 38.7106 | -120.8371 | DIAMOND SPRINGS 110740353 | 67 | 110 | 8540.781 | 4132.0541 | 4408.7269 | 2152.3519 | 2317.1972 | 0.0042897 | 0.0032418 | 1.4402 | 10.6522 | 1459 | 0.00020552 | 2257 | 0 | 0 | 1.3374 | 1510 | 0
Bay Area | 1395 | 12 | 47.1914 | 17 | 49.4701 | 3 | 0.00013291 | 0.066432 | 0 | 0 | 0 | 0 | 1.1268 | 11.4442 | 1.0015 | 8.8293e-06 | 8.2359e-05 | 0.70588 | 0.95394 | {5EC3A666-1799-428B-8C0E-2A981579542E} | 22811103 | PACIFICA 1103 | circuit_breaker | 37.5947 | -122.4888 | PACIFICA 1103circuit_breaker | 123 | 913 | 54127.0233 | 7914.1245 | 46212.8988 | 224.0976 | 1043.486 | 0.00024708 | 0.00039872 | 3.9326 | 5.6667 | 1967 | 2.6488e-05 | 2258 | 0 | 0 | 0.13925 | 2458 | 0
Bay Area | 409 | 12 | 23.2373 | 21 | 27.339 | 9 | 0.00013146 | 0.066432 | 0.12349 | 0.1112 | 0.0013987 | 3.4544e-07 | 0.41323 | 0.32507 | 1 | 8.7329e-06 | 0.0001085 | 0.57143 | 0.84997 | {3BE78651-BE87-4B28-8A48-F46DBB91FDDB} | 22811102 | PACIFICA 1102 | circuit_breaker | 37.5946 | -122.4889 | PACIFICA 1102circuit_breaker | 198 | 1333 | 68867.6794 | 10933.7049 | 57933.9745 | 430.7272 | 7978.8793 | 0.00097646 | 0.0011831 | 1.9364 | 2.3333 | 1811 | 7.8596e-05 | 2259 | 0 | 0 | 0.26764 | 2513 | 0
Central Valley | 8305 | 4 | 9.5372 | 17 | 14.2214 | 4 | 7.5725e-05 | 0.098222 | 0 | 0 | 0 | 0 | 0.33462 | 57.4192 | 1.2235 | 8.6353e-06 | 6.9398e-05 | 0.23529 | 0.67062 | {7EE01833-70BE-4E5D-9E9A-D8D904929AC9} | 163781704 | PEORIA 1704 | 6090 | 37.8973 | -120.5719 | PEORIA 17046090 | 25 | 9 | 2226.2031 | 1284.821 | 941.3821 | 1011.0046 | 279.8856 | 0.00027759 | 0.0003029 | 2.3843 | 4.25 | 2063 | 3.4541e-05 | 2260 | 0 | 0 | 0.62821 | 1442 | 0
North Coast | 8366 | 22 | 30.0607 | 90 | 62.7048 | 7 | 0.00012927 | 0.066431 | 4.7182 | 17.4469 | 100.3425 | 0.95466 | 0.0012642 | 1.844 | 0.57143 | 8.5875e-06 | 0.00034853 | 0.24444 | 0.4794 | {7A5B68F2-6534-44D1-AA3E-9D90FAA18095} | 42091102 | MIRABEL 1102 | 7401 | 38.5037 | -122.9487 | MIRABEL 11027401 | 16 | 102 | 4122.4888 | 1171.4888 | 2951 | 1171.4888 | 2951 | 0.0024397 | 0.00090488 | 1.3664 | 12.8571 | 1014 | 6.0113e-05 | 2261 | 0 | 0 | 0.72793 | 1236 | 0
Central Coast | 6609 | 374 | 1197.4125 | 1284 | 1724.4175 | 148 | 2.4427e-05 | 0.51158 | 6.8064 | 136.3967 | 523.4404 | 13.2738 | 1.1545 | 29.316 | 1.0321 | 8.4165e-06 | 8.9062e-05 | 0.29128 | 0.69439 | {F5363A17-6294-4FBA-A5E9-297DB437E9E9} | 182222104 | DEL MONTE 2104 | 2624 | 36.569 | -121.7951 | DEL MONTE 21042624 | 262 | 179 | 42192.47 | 30794.7643 | 11397.7057 | 29790.8638 | 11397.7057 | 0.013181 | 0.0036152 | 3.2016 | 8.6757 | 1918 | 0.0012456 | 2262 | 0 | 0 | 18.5112 | 1153 | 0
Bay Area | 4302 | 51 | 79.7323 | 135 | 128.5594 | 24 | 9.5028e-05 | 0.085506 | 14.0077 | 24.9389 | 78.8815 | 2.2904 | 0.76217 | 7.6534 | 0.83416 | 8.4103e-06 | 0.0006197 | 0.37778 | 0.6202 | {DFA21900-F572-4D0B-90D6-E67080E9EF87} | 14161106 | ROSSMOOR 1106 | circuit_breaker | 37.8651 | -122.0809 | ROSSMOOR 1106circuit_breaker | 111 | 487 | 33024.9665 | 7735.3967 | 25289.5699 | 2246.1308 | 8984.2253 | 0.014873 | 0.0022807 | 1.5634 | 5.625 | 651 | 0.00020185 | 2263 | 0 | 0 | 1.3957 | 1979 | 0
North Valley | 1430 | 2095 | 2694.3771 | 4331 | 3663.6997 | 243 | 0.0001256 | 0.066431 | 20.3085 | 15.5626 | 150.7614 | 6.5061 | 0.20384 | 0.64518 | 0.99196 | 8.344e-06 | 0.0012215 | 0.48372 | 0.73543 | {BE2BD7AC-D920-438D-9D8D-1EC5AAEC4CAF} | 103031101 | ORO FINO 1101 | 121988 | 39.812 | -121.5914 | ORO FINO 1101121988 | 523 | 1899 | 115171.1305 | 29450.0073 | 85721.1232 | 29450.0073 | 85721.1232 | 0.29682 | 0.030522 | 1.2861 | 17.823 | 314 | 0.0020276 | 2264 | 0 | 0 | 18.2994 | 1088 | 0
Central Valley | 3210 | 30 | 40.7196 | 156 | 93.8883 | 14 | 0.00012381 | 0.066432 | 0.87717 | 0.85282 | 2.3131 | 0.0059938 | 2.2157 | 1.6053 | 1.0057 | 8.2252e-06 | 0.00011802 | 0.19231 | 0.4337 | {56B3B60A-49BB-43A9-9EE8-443CF9005AA3} | 163761703 | RACETRACK 1703 | 10850 | 37.9807 | -120.3901 | RACETRACK 170310850 | 76 | 329 | 17453.0071 | 3044.989 | 14408.0181 | 927.6524 | 3247.6159 | 0.0016523 | 0.0017334 | 1.3573 | 11.1429 | 1756 | 0.00011515 | 2265 | 0 | 0 | 0.57642 | 1417 | 0
Sierra | 661 | 39 | 67.1329 | 184 | 129.1053 | 19 | 0.00011047 | 0.091714 | 1.0593 | 1.7793 | 4.9715 | 0.021804 | 0.61543 | 9.0983 | 1.2153 | 8.2066e-06 | 0.00011187 | 0.21196 | 0.51999 | {F60C4C6E-928C-45EE-B5E3-FE18B260D743} | 152531101 | FLINT 1101 | 40666 | 38.8868 | -121.0708 | FLINT 110140666 | 90 | 288 | 14473.2839 | 4596.6688 | 9876.6151 | 1886.431 | 3986.1711 | 0.0021255 | 0.002099 | 1.7214 | 9.6842 | 1789 | 0.00015593 | 2266 | 0 | 0 | 1.1722 | 868 | 0
North Coast | 9142 | 481 | 869.8701 | 567 | 910.182 | 73 | 0.00010419 | 0.082767 | 1.4653 | 52.9056 | 505.2276 | 1.451 | 0.16618 | 15.3832 | 1.0272 | 8.1926e-06 | 0.00014439 | 0.84832 | 0.95571 | {69ECBFC6-9041-42D6-B70D-8E6BF5F8976F} | 42841111 | GUALALA 1111 | 445166 | 38.6937 | -123.4238 | GUALALA 1111445166 | 115 | 38 | 16207.7717 | 14711.3731 | 1496.3986 | 9193.5626 | 454.3565 | 0.010541 | 0.0076058 | 1.8085 | 7.7671 | 1620 | 0.00059806 | 2267 | 0 | 0 | 5.7126 | 2392 | 0
Central Coast | 3212 | 478 | 1064.0049 | 1395 | 1551.1859 | 79 | 0.00012321 | 0.066432 | 3.6322 | 6.8332 | 23.4093 | 0.24029 | 0.55159 | 1.9565 | 1 | 8.1848e-06 | 0.00026176 | 0.34265 | 0.68593 | {A1366627-BA9B-4DAB-8067-98E47F041CB9} | 83622103 | CAMP EVERS 2103 | 10946 | 37.0342 | -122.0227 | CAMP EVERS 210310946 | 219 | 320 | 29567.1859 | 13670.8285 | 15896.3574 | 8744.1235 | 7612.6191 | 0.020679 | 0.0097332 | 2.226 | 17.6582 | 1221 | 0.0006466 | 2268 | 0 | 0 | 5.4333 | 1466 | 0
Bay Area | 6317 | 1 | 1.3586 | 20 | 25.7062 | 1 | 0.00013425 | 0.066432 | 10.5335 | 5.6109 | 24.0922 | 0.2583 | 1.4801 | 0.66881 | 1 | 8.9187e-06 | 0.0014142 | 0.05 | 0.05285 | {3E0AE845-0CE4-470C-9DE4-D6AA20E33FFC} | 152691104 | HIGGINS 1104 | 32747 | 39.1426 | -121.0612 | HIGGINS 110432747 | 52 | 171 | 10460.0825 | 2820.8108 | 7639.2717 | 966.1489 | 3477.6876 | 0.0014142 | 0.00013425 | 1.3586 | 20 | 268 | 8.9187e-06 | 2269 | 0 | 0 | 0.60034 | 1113 | 0
Sierra | 6317 | 71 | 109.9644 | 114 | 136.2852 | 10 | 0.00013534 | 0.059788 | 12.3542 | 7.6114 | 28.529 | 0.52963 | 1.0351 | 1.9622 | 1.4 | 8.0984e-06 | 0.0015114 | 0.62281 | 0.80687 | {3E0AE845-0CE4-470C-9DE4-D6AA20E33FFC} | 152691104 | HIGGINS 1104 | 32747 | 39.1426 | -121.0612 | HIGGINS 110432747 | 52 | 171 | 10460.0825 | 2820.8108 | 7639.2717 | 966.1489 | 3477.6876 | 0.015114 | 0.0013534 | 1.5488 | 11.4 | 244 | 8.0984e-05 | 2269 | 0 | 0 | 0.60034 | 561 | 0
North Coast | 1534 | 6 | 12.3584 | 33 | 28.8567 | 6 | 0.00014931 | 0.055358 | 3.3315 | 2.2692 | 12.2397 | 0.086996 | 0.99779 | 0.10066 | 1.6667 | 8.1086e-06 | 0.00027544 | 0.18182 | 0.42827 | {BAA473AF-66C6-4355-8E90-0CDB40A98A03} | 42151104 | SANTA ROSA A 1104 | circuit_breaker | 38.4366 | -122.7137 | SANTA ROSA A 1104circuit_breaker | 179 | 1016 | 54258.7277 | 9705.5931 | 44553.1345 | 380.5489 | 1043.5698 | 0.0016526 | 0.00089585 | 2.0597 | 5.5 | 1186 | 4.8652e-05 | 2270 | 0 | 0 | 0.23646 | 1993 | 0
Bay Area | 6440 | 7 | 11.6143 | 27 | 20.8157 | 5 | 4.2322e-05 | 0.15799 | 0.50347 | 0.22239 | 0.0016296 | 8.2047e-07 | 0.76062 | 22.5188 | 1.0119 | 8.0931e-06 | 3.768e-05 | 0.25926 | 0.55796 | {30491B06-175D-4B50-9477-0E42FFDBA4F5} | 14341106 | VALLEY VIEW 1106 | P128 | 37.9792 | -122.2639 | VALLEY VIEW 1106P128 | 85 | 300 | 18303.7745 | 4067.7934 | 14235.9812 | 184.0685 | 138.2088 | 0.0001884 | 0.00021161 | 1.6592 | 5.4 | 2365 | 4.0465e-05 | 2271 | 0 | 0 | 0.11437 | 2741 | 0
Sierra | 4306 | 52 | 105.0189 | 209 | 164.4888 | 28 | 0.00013451 | 0.061686 | 0.71171 | 0.63024 | 3.7069 | 0.074344 | 0.098281 | 0.19221 | 0.89286 | 8.0242e-06 | 0.00012718 | 0.2488 | 0.63846 | {531CAA3C-3DF7-4333-B737-30C384999892} | 153651103 | SHINGLE SPRINGS 1103 | 8752 | 38.6587 | -120.976 | SHINGLE SPRINGS 11038752 | 69 | 178 | 9323.2573 | 2987.221 | 6336.0363 | 2895.0362 | 6336.0363 | 0.0035611 | 0.0037662 | 2.0196 | 7.4643 | 1710 | 0.00022468 | 2272 | 0 | 0 | 1.7989 | 2501 | 0
North Coast | 8674 | 5 | 6.7229 | 17 | 11.1975 | 1 | 0.000119 | 0.066431 |  |  |  |  | 0 | 2.1909 | 1 | 7.9052e-06 | 0.000119 | 0.29412 | 0.60039 | {95AA1DFC-C5A4-4057-BBAE-EB51A3C8494D} | 42281105 | POTTER VALLEY P H 1105 | circuit_breaker | 39.361 | -123.1277 | POTTER VALLEY P H 1105circuit_breaker | 23 | 0 | 296.5288 | 296.5288 | 0 | 296.5288 | 0 | 0.000119 | 0.000119 | 1.3446 | 17 | 1750 | 7.9052e-06 | 2273 | 0 | 0 | 0.18425 | 459 | 0
Bay Area | 8980 | 32 | 93.6635 | 41 | 97.8635 | 10 | 3.11e-05 | 0.30931 | 0.066955 | 0.35328 | 0.63291 | 8.9659e-05 | 1.1473 | 37.771 | 1.0115 | 7.8955e-06 | 1.9376e-05 | 0.78049 | 0.95708 | {D3A0D229-F80C-49CB-8DD0-3A6BB24AE00B} | 42291101 | OLEMA 1101 | 49756 | 38.109 | -122.844 | OLEMA 110149756 | 69 | 76 | 11899.1331 | 9480.1738 | 2418.9593 | 1000.1369 | 750.9165 | 0.00019376 | 0.000311 | 2.927 | 4.1 | 2624 | 7.8955e-05 | 2274 | 0 | 0 | 0.62146 | 2870 | 0
Sierra | 817 | 13 | 17.5146 | 57 | 36.2686 | 10 | 0.00013023 | 0.059788 | 0 | 0 | 0 | 0 | 0.060472 | 0.52249 | 1.4 | 7.8663e-06 | 0.0001137 | 0.22807 | 0.48291 | {A316ED50-5AA1-4ED8-AC7C-24B23FF6CC3D} | 152481104 | BRUNSWICK 1104 | 56468 | 39.2412 | -121.0378 | BRUNSWICK 110456468 | 190 | 385 | 27783.8624 | 9624.4245 | 18159.4379 | 8462.4654 | 16433.6469 | 0.001137 | 0.0013023 | 1.3473 | 5.7 | 1781 | 7.8663e-05 | 2275 | 0 | 0 | 5.2583 | 217 | 0
North Coast | 8089 | 73 | 120.9519 | 141 | 149.5169 | 21 | 0.00013313 | 0.060105 | 0.81563 | 2.871 | 7.737 | 0.022742 | 0.035398 | 1.127 | 1.381 | 7.8562e-06 | 0.00013607 | 0.51773 | 0.80895 | {BCC029FE-B790-4D1A-9B12-5D2C7AA3930D} | 43081101 | BIG RIVER 1101 | circuit_breaker | 39.3116 | -123.7865 | BIG RIVER 1101circuit_breaker | 71 | 120 | 9378.586 | 3058.0721 | 6320.5139 | 2894.9274 | 6320.5139 | 0.0028575 | 0.0027958 | 1.6569 | 6.7143 | 1658 | 0.00016498 | 2276 | 0 | 0 | 1.7988 | 2681 | 0
North Coast | 5049 | 208 | 347.6452 | 335 | 419.4256 | 28 | 0.00013688 | 0.054569 | 6.8529 | 6.8285 | 26.2842 | 0.43904 | 0.37537 | 2.2525 | 1.7143 | 7.8457e-06 | 0.00054596 | 0.6209 | 0.82886 | {2E6DCA70-6B36-4F65-B853-AA4AC3CF0E30} | 42811113 | MONTE RIO 1113 | 5026 | 38.5 | -122.9924 | MONTE RIO 11135026 | 53 | 229 | 12030.1674 | 2955.8477 | 9074.3197 | 2955.8477 | 9074.3197 | 0.015287 | 0.0038327 | 1.6714 | 11.9643 | 742 | 0.00021968 | 2277 | 0 | 0 | 1.8367 | 918 | 0
Central Coast | 8134 | 869 | 1935.2911 | 1145 | 2101.9941 | 40 | 0.00011785 | 0.066431 | 9.5476 | 41.4967 | 208.5041 | 3.5509 | 0.31294 | 3.6713 | 1.0001 | 7.829e-06 | 0.00056123 | 0.75895 | 0.92069 | {1E15AF20-63CE-4AE7-884A-DD7A02307129} | 82931101 | POINT MORETTI 1101 | 5401 | 37.0648 | -122.1233 | POINT MORETTI 11015401 | 59 | 62 | 7198.6471 | 4092.0757 | 3106.5715 | 4092.0757 | 3106.5715 | 0.022449 | 0.0047141 | 2.227 | 28.625 | 721 | 0.00031316 | 2278 | 0 | 0 | 2.5427 | 493 | 0
North Coast | 5312 | 1439 | 2955.1472 | 2050 | 3233.58 | 189 | 0.00012557 | 0.061862 | 7.0972 | 48.4202 | 284.9801 | 12.061 | 0.24854 | 2.0998 | 1.2759 | 7.7744e-06 | 0.00050667 | 0.70195 | 0.91389 | {0D62503E-67CB-4A8E-BC3C-093230B8FF31} | 42761101 | FORT BRAGG A 1101 | 3100 | 39.4525 | -123.7989 | FORT BRAGG A 11013100 | 381 | 495 | 52192.8224 | 23696.4521 | 28496.3702 | 19614.6509 | 26237.748 | 0.095761 | 0.023733 | 2.0536 | 10.8466 | 781 | 0.0014694 | 2279 | 0 | 0 | 12.188 | 1781 | 0
Sierra | 7519 | 406 | 546.2541 | 723 | 711.4071 | 51 | 0.00011661 | 0.066432 | 6.7188 | 22.0073 | 92.6273 | 1.3 | 1.4741 | 5.7925 | 1.0084 | 7.7463e-06 | 0.0004153 | 0.56155 | 0.76785 | {D460FB8F-F4FD-44BA-8600-4D3642AC6BA8} | 152241101 | HALSEY 1101 | 5731 | 38.9857 | -121.0221 | HALSEY 11015731 | 69 | 96 | 10018.4138 | 5029.6194 | 4988.7944 | 5029.6194 | 4988.7944 | 0.02118 | 0.0059469 | 1.3455 | 14.1765 | 917 | 0.00039506 | 2280 | 0 | 0 | 3.1253 | 665 | 0
Sierra | 957 | 0 | 0 | 5 | 2.2787 | 3 | 0.00011638 | 0.066432 | 4.7611 | 8.7987 | 29.1375 | 0.14004 | 0.92183 | 2.4797 | 1 | 7.7314e-06 | 0.00025825 | 0 | 0 | {D972EC75-3864-4C3E-9FB0-5B538887AB46} | 152481103 | BRUNSWICK 1103 | circuit_breaker | 39.2312 | -121.0351 | BRUNSWICK 1103circuit_breaker | 429 | 867 | 49106.6306 | 16287.3875 | 32819.2431 | 8459.5799 | 15055.3259 | 0.00077475 | 0.00034914 |  | 1.6667 | 1233 | 2.3194e-05 | 2281 | 0 | 0 | 5.2565 | 594 | 0
North Coast | 7206 | 19 | 31.8714 | 38 | 42.9924 | 3 | 0.00011615 | 0.066431 | 0.19648 | 0.62326 | 5.5082 | 0.1067 | 1.7058 | 4.8235 | 1 | 7.716e-06 | 8.6349e-05 | 0.5 | 0.74133 | {09497714-C1FB-4002-AD16-E7091A7FE67A} | 42091102 | MIRABEL 1102 | 841 | 38.5087 | -122.9261 | MIRABEL 1102841 | 22 | 130 | 7515.4202 | 1089.713 | 6425.7072 | 1089.713 | 6425.7072 | 0.00025905 | 0.00034845 | 1.6774 | 12.6667 | 1937 | 2.3148e-05 | 2282 | 0 | 0 | 0.67712 | 1909 | 0
Sierra | 488 | 117 | 215.0769 | 546 | 397.74 | 49 | 0.00012697 | 0.068763 | 2.5515 | 3.6684 | 13.9831 | 0.19066 | 1.7147 | 10.4408 | 1.7023 | 7.6627e-06 | 0.00023175 | 0.21429 | 0.54075 | {0654A595-233E-4128-BBD6-123F6D88D1DE} | 152161101 | AUBURN 1101 | circuit_breaker | 38.9035 | -121.0697 | AUBURN 1101circuit_breaker | 147 | 700 | 30031.3186 | 7895.4706 | 22135.8479 | 5202.5567 | 11781.3694 | 0.011356 | 0.0062215 | 1.8383 | 11.1429 | 1307 | 0.00037547 | 2283 | 0 | 0 | 3.2327 | 523 | 0
North Coast | 685 | 307 | 519.1677 | 641 | 716.4731 | 42 | 0.00013574 | 0.05694 | 1.2236 | 0.90638 | 4.8449 | 0.015906 | 0.36005 | 0.17257 | 1.4048 | 7.6293e-06 | 0.00014603 | 0.47894 | 0.72462 | {66A6713B-EEF9-4672-883A-89D2D2628FA8} | 42151107 | SANTA ROSA A 1107 | circuit_breaker | 38.4367 | -122.7133 | SANTA ROSA A 1107circuit_breaker | 212 | 674 | 40010.5296 | 9899.1863 | 30111.3433 | 4761.8386 | 10891.6551 | 0.0061331 | 0.005701 | 1.6911 | 15.2619 | 1615 | 0.00032043 | 2284 | 0 | 0 | 2.9589 | 1865 | 0
Central Coast | 3696 | 266 | 461.745 | 568 | 626.2123 | 30 | 0.00011274 | 0.066431 | 10.5381 | 12.84 | 42.119 | 0.65602 | 0.58525 | 2.2506 | 1.0007 | 7.4892e-06 | 0.00052263 | 0.46831 | 0.73736 | {1AF8FBF6-3836-4778-B451-B0D01E1343B6} | 82021106 | LOS GATOS 1106 | LA46 | 37.1615 | -121.9817 | LOS GATOS 1106LA46 | 40 | 196 | 12539.8682 | 2467.6552 | 10072.213 | 2467.6552 | 10072.213 | 0.015679 | 0.0033821 | 1.7359 | 18.9333 | 770 | 0.00022468 | 2285 | 0 | 0 | 1.5333 | 2617 | 0
Sierra | 3409 | 911 | 1336.9139 | 1459 | 1646.1725 | 135 | 0.00011004 | 0.068127 | 12.558 | 79.8135 | 794.6474 | 35.5792 | 2.3087 | 17.2585 | 1.0139 | 7.4601e-06 | 0.00071214 | 0.6244 | 0.81213 | {C6D2DBB1-9437-46D3-8E37-6D1AD2333690} | 152491101 | WEIMAR 1101 | circuit_breaker | 39.0361 | -120.9879 | WEIMAR 1101circuit_breaker | 259 | 271 | 26991.4552 | 14826.071 | 12165.3841 | 14826.071 | 12165.3841 | 0.096139 | 0.014856 | 1.4675 | 10.8074 | 560 | 0.0010071 | 2286 | 0 | 0 | 9.2125 | 462 | 0
North Coast | 4764 | 59 | 105.6813 | 92 | 123.6638 | 5 | 0.0001121 | 0.066431 | 15.2824 | 13.3532 | 36.782 | 0.55245 | 0.7646 | 0.72465 | 1 | 7.447e-06 | 0.00077607 | 0.6413 | 0.85459 | {3A330D41-F506-49D1-A8AC-21EA6FC6FDFA} | 42811113 | MONTE RIO 1113 | 532 | 38.4949 | -123.0109 | MONTE RIO 1113532 | 11 | 47 | 2867.1636 | 836.4221 | 2030.7415 | 836.4221 | 2030.7415 | 0.0038803 | 0.0005605 | 1.7912 | 18.4 | 514 | 3.7235e-05 | 2287 | 0 | 0 | 0.51973 | 411 | 0
Sierra | 836 | 3 | 4.6621 | 20 | 10.8536 | 3 | 0.00011192 | 0.066432 |  |  |  |  | 0.48673 | 6.1688 | 0.33407 | 7.4351e-06 | 0.00011192 | 0.15 | 0.42955 | {40341932-C636-415B-BE6F-5D9D8CD0A383} | 153651104 | SHINGLE SPRINGS 1104 | circuit_breaker | 38.6593 | -120.947 | SHINGLE SPRINGS 1104circuit_breaker | 92 | 80 | 7145.2903 | 3786.907 | 3358.3833 | 901.8218 | 1215.5155 | 0.00033576 | 0.00033576 | 1.554 | 6.6667 | 1787 | 2.2305e-05 | 2288 | 0 | 0 | 0.56037 | 688 | 0
North Coast | 3013 | 0 | 0 | 6 | 2.5909 | 1 | 0.00011189 | 0.066432 |  |  |  |  | 0.64823 | 1.4586 | 1 | 7.4332e-06 | 0.00011189 | 0 | 0 | {9CDBB67A-2B35-4338-A3A3-91CFC4E574D6} | 43191102 | REDBUD 1102 | 2013 | 38.9791 | -122.6633 | REDBUD 11022013 | 98 | 406 | 29064.5038 | 7412.4545 | 21652.0493 | 125.6367 | 823.9851 | 0.00011189 | 0.00011189 |  | 6 | 1788 | 7.4332e-06 | 2289 | 0 | 0 | 0.078067 | 2864 | 0
North Coast | 9617 | 4 | 5.0412 | 7 | 6.3119 | 1 | 0.00011116 | 0.066431 | 0 | 0 | 0 | 0 | 0 | 2.1909 | 1 | 7.3847e-06 | 0 | 0.57143 | 0.79869 | {57F4EFFD-9C20-4F14-986D-FBD228591C36} | 42281104 | POTTER VALLEY P H 1104 | circuit_breaker | 39.3614 | -123.1279 | POTTER VALLEY P H 1104circuit_breaker | 9 | 0 | 158.6806 | 158.6806 | 0 | 158.6806 | 0 | 0 | 0.00011116 | 1.2603 | 7 | 2888 | 7.3847e-06 | 2290 | 0 | 0 | 0.0986 | 2412 | 0
Central Valley | 1409 | 27 | 39.3781 | 149 | 93.3516 | 6 | 0.00011111 | 0.066432 | 0.92813 | 0.33462 | 1.778 | 0.0033171 | 0.25184 | 0.13934 | 1 | 7.3809e-06 | 0.00011042 | 0.18121 | 0.42183 | {15F62F46-8DEB-4CCA-80E4-1A07793D2B95} | 163240402 | TAR FLAT 0402 | circuit_breaker | 37.9844 | -120.3795 | TAR FLAT 0402circuit_breaker | 54 | 201 | 10517.8159 | 2350.4406 | 8167.3754 | 1258.5471 | 4603.0644 | 0.00066253 | 0.00066663 | 1.4584 | 24.8333 | 1799 | 4.4286e-05 | 2291 | 0 | 0 | 0.78202 | 1387 | 0
Central Coast | 1656 | 1968 | 3593.5372 | 4477 | 4980.531 | 228 | 0.00011097 | 0.066432 | 4.3072 | 21.9859 | 69.4862 | 0.49078 | 0.59668 | 9.3987 | 1.0181 | 7.372e-06 | 0.00027248 | 0.43958 | 0.72152 | {EA67021F-EC51-4B91-B55C-AC9EF715A21B} | 83622103 | CAMP EVERS 2103 | 12990 | 37.039 | -122.0215 | CAMP EVERS 210312990 | 278 | 339 | 43900.5547 | 21722.1338 | 22178.4209 | 21722.1338 | 22178.4209 | 0.062126 | 0.025301 | 1.826 | 19.636 | 1196 | 0.0016808 | 2292 | 0 | 0 | 13.4975 | 2168 | 0
Sierra | 2859 | 2268 | 3159.466 | 4262 | 4185.095 | 354 | 0.00011087 | 0.066432 | 7.1009 | 22.2103 | 67.8641 | 0.85474 | 0.8635 | 7.6314 | 1.0018 | 7.365e-06 | 0.00048165 | 0.53214 | 0.75493 | {8FFD9B25-93B3-48FD-97D3-DCFDDA587230} | 152241101 | HALSEY 1101 | 76178 | 39.0015 | -121.0224 | HALSEY 110176178 | 471 | 624 | 67847.3756 | 32534.9057 | 35312.4699 | 32534.9057 | 35312.4699 | 0.1705 | 0.039246 | 1.3931 | 12.0395 | 809 | 0.0026072 | 2293 | 0 | 0 | 20.2162 | 328 | 0
North Coast | 1878 | 94 | 200.4906 | 196 | 252.2756 | 18 | 0.0001324 | 0.055359 | 3.6128 | 2.0643 | 11.7323 | 0.10143 | 0.22975 | 0.023485 | 1.1111 | 7.344e-06 | 0.00036982 | 0.47959 | 0.79473 | {697A1F90-C46B-4A32-BA8E-838CA80BD5D2} | 42151104 | SANTA ROSA A 1104 | 39786 | 38.4527 | -122.7009 | SANTA ROSA A 110439786 | 197 | 942 | 52604.0124 | 10862.9994 | 41741.013 | 1494.4367 | 4461.2883 | 0.0066568 | 0.0023832 | 2.1329 | 10.8889 | 984 | 0.00013219 | 2294 | 0 | 0 | 0.9286 | 2169 | 0
Bay Area | 2928 | 5 | 13.5462 | 11 | 17.1768 | 3 | 0.00010964 | 0.066432 | 3.2681 | 3.2337 | 13.5781 | 0.089125 | 0.13864 | 1.2102 | 0.66667 | 7.2838e-06 | 0.00028293 | 0.45455 | 0.78864 | {F3272220-83F6-47EF-AA10-7270133DA2ED} | 14662108 | TASSAJARA 2108 | 83368 | 37.8375 | -122.0229 | TASSAJARA 210883368 | 182 | 453 | 28840.8303 | 8729.1235 | 20111.7068 | 128.9574 | 825.602 | 0.00084879 | 0.00032893 | 2.7092 | 3.6667 | 1166 | 2.1851e-05 | 2295 | 0 | 0 | 0.08013 | 1496 | 0
North Coast | 1172 | 2515 | 4239.4893 | 3039 | 4479.483 | 228 | 0.00011108 | 0.064392 | 2.4141 | 9.0187 | 34.5953 | 0.15157 | 0.1262 | 2.0069 | 1.0879 | 7.1917e-06 | 0.00019152 | 0.82757 | 0.94642 | {2F10EC8A-D66D-41A3-A96A-C091A52D1815} | 42761102 | FORT BRAGG A 1102 | 418 | 39.419 | -123.7976 | FORT BRAGG A 1102418 | 338 | 561 | 59721.3376 | 22747.0574 | 36974.2802 | 21780.1498 | 36489.3689 | 0.043667 | 0.025327 | 1.6857 | 13.3289 | 1445 | 0.0016397 | 2296 | 0 | 0 | 13.5336 | 2010 | 0
Central Coast | 3862 | 163 | 277.6082 | 646 | 548.1336 | 36 | 0.00010803 | 0.066431 | 1.677 | 1.9685 | 11.714 | 0.068242 | 0.29204 | 1.5595 | 1.0002 | 7.1765e-06 | 0.00013444 | 0.25232 | 0.50646 | {07C3F785-A0A2-4537-8DD2-EA76577441A5} | 82021106 | LOS GATOS 1106 | LA42 | 37.1551 | -121.9818 | LOS GATOS 1106LA42 | 73 | 228 | 10745.6547 | 4461.918 | 6283.7367 | 4461.918 | 6283.7367 | 0.00484 | 0.003889 | 1.7031 | 17.9444 | 1674 | 0.00025835 | 2297 | 0 | 0 | 2.7725 | 1164 | 0
Central Coast | 9573 | 145 | 315.845 | 175 | 332.4157 | 10 | 0.00010801 | 0.066431 | 8.0515 | 28.9232 | 66.8006 | 0.62121 | 0.53473 | 3.0334 | 1 | 7.175e-06 | 0.00055765 | 0.82857 | 0.95015 | {2158531F-B7B5-4ECE-803F-B5BAD865C4B6} | 82931101 | POINT MORETTI 1101 | 10722 | 37.0777 | -122.1332 | POINT MORETTI 110110722 | 21 | 20 | 1949.1397 | 974.5061 | 974.6337 | 974.5061 | 974.6337 | 0.0055765 | 0.0010801 | 2.1782 | 17.5 | 727 | 7.175e-05 | 2298 | 0 | 0 | 0.60553 | 2801 | 0
Central Valley | 4123 | 79 | 112.719 | 459 | 271.4528 | 33 | 0.0001077 | 0.066432 | 2.671 | 2.4809 | 10.2196 | 0.096963 | 1.8907 | 4.218 | 1.0001 | 7.1547e-06 | 0.00021827 | 0.17211 | 0.41524 | {EA023699-472E-4198-908E-801A3A6750F5} | 163240401 | TAR FLAT 0401 | circuit_breaker | 37.9845 | -120.3795 | TAR FLAT 0401circuit_breaker | 107 | 418 | 22670.0405 | 5901.3044 | 16768.7361 | 5449.6774 | 14684.8851 | 0.0072029 | 0.0035541 | 1.4268 | 13.9091 | 1348 | 0.0002361 | 2299 | 0 | 0 | 3.3863 | 67 | 0
North Coast | 4056 | 238 | 439.5379 | 429 | 526.1973 | 35 | 0.00010732 | 0.066432 | 6.3124 | 108.516 | 718.2836 | 7.235 | 1.0678 | 13.3333 | 1.0252 | 7.1293e-06 | 0.0003389 | 0.55478 | 0.83531 | {C82DD836-B8DD-4D46-90CF-6BDF1D75C42C} | 42981101 | ELK 1101 | 4628 | 39.24 | -123.7713 | ELK 11014628 | 102 | 106 | 12264.7248 | 6684.5064 | 5580.2184 | 3351.298 | 2281.7429 | 0.011862 | 0.0037561 | 1.8468 | 12.2571 | 1032 | 0.00024953 | 2300 | 0 | 0 | 2.0824 | 1180 | 0
North Coast | 7349 | 19 | 32.6175 | 30 | 37.5341 | 6 | 0.00010716 | 0.066432 | 2.1861 | 6.7215 | 19.7386 | 0.046629 | 1.7017 | 3.663 | 1.0022 | 7.1186e-06 | 0.00018276 | 0.63333 | 0.86901 | {C8B7B79F-9539-45C9-8977-9A8FC5806A25} | 42761103 | FORT BRAGG A 1103 | circuit_breaker | 39.4351 | -123.7995 | FORT BRAGG A 1103circuit_breaker | 141 | 235 | 13605.6687 | 4315.8195 | 9289.8492 | 271.1874 | 523.4882 | 0.0010965 | 0.00064294 | 1.7167 | 5 | 1475 | 4.2712e-05 | 2301 | 0 | 0 | 0.16851 | 1599 | 0
North Coast | 5918 | 5 | 9.7249 | 7 | 10.6364 | 1 | 0.00010701 | 0.066432 |  |  |  |  | 0 | 6.1144 | 1 | 7.1087e-06 | 0.00010701 | 0.71429 | 0.91431 | {36BC008E-75DD-4032-9E44-5DB50949C39A} | 43361102 | HIGHLANDS 1102 | 556 | 38.9691 | -122.6211 | HIGHLANDS 1102556 | 199 | 461 | 35440.0273 | 12171.5187 | 23268.5085 | 0 | 32.6295 | 0.00010701 | 0.00010701 | 1.945 | 7 | 1820 | 7.1087e-06 | 2302 | 0 | 0 | 0 | 1392 | 0
Sierra | 9322 | 38 | 53.8897 | 114 | 98.8251 | 9 | 0.00010691 | 0.066432 | 1.8273 | 7.9468 | 18.4226 | 0.085818 | 3.8658 | 10.7149 | 1.0049 | 7.1019e-06 | 0.00013563 | 0.33333 | 0.5453 | {C6FEDD77-5A06-4484-8B32-F0F200B7AB81} | 152491101 | WEIMAR 1101 | 6139 | 39.066 | -120.9804 | WEIMAR 11016139 | 12 | 19 | 2252.2247 | 997.9281 | 1254.2966 | 997.9281 | 1254.2966 | 0.0012206 | 0.00096216 | 1.4181 | 12.6667 | 1662 | 6.3917e-05 | 2303 | 0 | 0 | 0.62008 | 210 | 0
Central Valley | 5808 | 16 | 27.9533 | 151 | 81.7558 | 17 | 0.00010647 | 0.066432 | 6.7509 | 9.4752 | 19.4145 | 0.16084 | 0.53397 | 3.7281 | 1 | 7.0731e-06 | 0.00034525 | 0.10596 | 0.34191 | {20D6DAD8-1EAB-401A-8690-BA00488AD19D} | 163761703 | RACETRACK 1703 | 2553 | 37.9919 | -120.4016 | RACETRACK 17032553 | 66 | 224 | 14140.9954 | 3989.867 | 10151.1283 | 1162.4255 | 2937.1921 | 0.0058692 | 0.00181 | 1.7471 | 8.8824 | 1021 | 0.00012024 | 2304 | 0 | 0 | 0.7223 | 34 | 0
Central Coast | 9266 | 145 | 290.2079 | 299 | 382.7126 | 31 | 0.00010616 | 0.066431 | 0.22239 | 16.4572 | 97.6617 | 0.036768 | 2.8335 | 21.6696 | 1.0712 | 7.0525e-06 | 6.9194e-05 | 0.48495 | 0.75829 | {E4165A82-7E13-4532-9E5E-AB5D693EB3C8} | 83192101 | GREEN VALLEY 2101 | 6601 | 36.9941 | -121.7172 | GREEN VALLEY 21016601 | 28 | 40 | 6530.0038 | 3063.6094 | 3466.3944 | 3063.6094 | 3466.3944 | 0.002145 | 0.003291 | 2.0014 | 9.6452 | 2066 | 0.00021863 | 2305 | 0 | 0 | 1.9036 | 2219 | 0
Bay Area | 550 | 166 | 520.0269 | 169 | 521.3941 | 11 | 0.00010558 | 0.066432 | 0.047239 | 0.18533 | 0.1574 | 8.5502e-06 | 0.034191 | 7.5214 | 1 | 7.014e-06 | 5.2343e-05 | 0.98225 | 0.99738 | {2E2285AC-DBD4-4A01-BBCE-F25D437434C6} | 22811102 | PACIFICA 1102 | 66732 | 37.6147 | -122.486 | PACIFICA 110266732 | 63 | 374 | 20860.1707 | 4716.4418 | 16143.7289 | 1010.3488 | 589.3384 | 0.00057577 | 0.0011614 | 3.1327 | 15.3636 | 2216 | 7.7154e-05 | 2306 | 0 | 0 | 0.6278 | 381 | 0
Bay Area | 2696 | 26 | 54.0584 | 105 | 97.1746 | 16 | 3.7184e-05 | 0.17452 | 1.3683 | 327.46 | 1027.8062 | 2.2564 | 2.2161 | 36.6543 | 1.0639 | 6.9968e-06 | 4.1897e-05 | 0.24762 | 0.5563 | {531B9791-D7B4-4DAF-8D61-5A68DAA7C3F6} | 14241101 | SUNOL 1101 | MR650 | 37.5933 | -121.8844 | SUNOL 1101MR650 | 66 | 79 | 7054.858 | 4248.3171 | 2806.5409 | 1692.8493 | 836.9295 | 0.00067035 | 0.00059494 | 2.0792 | 6.5625 | 2310 | 0.00011195 | 2307 | 0 | 0 | 1.0519 | 2012 | 0
Bay Area | 4486 | 258 | 432.8179 | 746 | 709.9511 | 55 | 0.00010526 | 0.066431 | 2.3998 | 9.968 | 112.3359 | 2.2978 | 0.01243 | 0.28875 | 0.63636 | 6.9923e-06 | 0.00017804 | 0.34584 | 0.60964 | {B486F4D0-4246-4914-B521-4CE6A759247F} | 42011108 | SAN RAFAEL 1108 | 1262 | 37.9759 | -122.5638 | SAN RAFAEL 11081262 | 136 | 572 | 30941.3607 | 7151.9325 | 23789.4282 | 6212.9384 | 19542.1132 | 0.0097924 | 0.0057891 | 1.6776 | 13.5636 | 1495 | 0.00038458 | 2308 | 0 | 0 | 3.8605 | 1302 | 0
Sierra | 4129 | 1 | 1.3586 | 8 | 5.4647 | 3 | 0.00010506 | 0.066432 |  |  |  |  | 0.63938 | 0.16475 | 1 | 6.9796e-06 | 0.00010506 | 0.125 | 0.24861 | {BEA0A501-B4D2-4CC0-BAE4-F7EC8C1D8A1B} | 152481104 | BRUNSWICK 1104 | circuit_breaker | 39.2312 | -121.0351 | BRUNSWICK 1104circuit_breaker | 114 | 226 | 15715.118 | 4755.5689 | 10959.549 | 2663.6104 | 8132.6618 | 0.00031519 | 0.00031519 | 1.3586 | 2.6667 | 1834 | 2.0939e-05 | 2309 | 0 | 0 | 1.6551 | 292 | 0
Sierra | 4205 | 88 | 119.9534 | 271 | 207.7548 | 22 | 0.00010459 | 0.066432 | 14.427 | 14.7571 | 83.8336 | 3.0037 | 1.294 | 10.3238 | 1.0244 | 6.9479e-06 | 0.00097777 | 0.32472 | 0.57738 | {C51D56F7-8B75-4353-BFFF-B24BA2EBAE80} | 152481106 | BRUNSWICK 1106 | 33050 | 39.1499 | -121.0366 | BRUNSWICK 110633050 | 119 | 304 | 20191.425 | 6143.4432 | 14047.9818 | 1491.043 | 2968.8036 | 0.021511 | 0.0023009 | 1.3631 | 12.3182 | 420 | 0.00015285 | 2310 | 0 | 0 | 0.92649 | 533 | 0
Sierra | 4891 | 517 | 701.6601 | 1042 | 994.7689 | 96 | 0.00010406 | 0.066432 | 18.8318 | 139.5004 | 1517.5061 | 78.4831 | 1.7858 | 11.5571 | 1.0186 | 6.9129e-06 | 0.0010303 | 0.49616 | 0.70535 | {CBE676E4-58AB-460F-8EF4-93AB8DD21D9C} | 152491101 | WEIMAR 1101 | 2764 | 39.035 | -120.9793 | WEIMAR 11012764 | 133 | 152 | 17574.148 | 9841.7615 | 7732.3865 | 9841.7615 | 7732.3865 | 0.098911 | 0.0099898 | 1.3572 | 10.8542 | 396 | 0.00066364 | 2311 | 0 | 0 | 6.1154 | 1436 | 0
Central Coast | 617 | 674 | 1320.79 | 3119 | 2651.5251 | 383 | 3.6028e-05 | 0.24649 | 2.5411 | 100.7849 | 374.4023 | 2.0594 | 1.6111 | 55.9586 | 1.0812 | 6.8951e-06 | 5.7383e-05 | 0.21609 | 0.49812 | {03861487-35BB-45AB-853E-5E8CD2B590E5} | 182371111 | LAURELES 1111 | 2020 | 36.4633 | -121.712 | LAURELES 11112020 | 354 | 305 | 76619.2324 | 53149.3291 | 23469.9033 | 53149.3291 | 23469.9033 | 0.021978 | 0.013799 | 1.9596 | 8.1436 | 2167 | 0.0026408 | 2312 | 0 | 0 | 33.0255 | 1167 | 0
North Coast | 4230 | 159 | 309.4463 | 241 | 357.0888 | 33 | 9.8516e-05 | 0.071054 | 5.5908 | 20.7647 | 88.9591 | 1.6011 | 0.75261 | 4.8777 | 1.0017 | 6.7786e-06 | 0.00036756 | 0.65975 | 0.86658 | {B37312AE-80D7-4090-A893-C81D3025336C} | 42151104 | SANTA ROSA A 1104 | 32180 | 38.4782 | -122.679 | SANTA ROSA A 110432180 | 77 | 137 | 11548.8893 | 3870.5139 | 7678.3754 | 3607.4547 | 7520.1905 | 0.012129 | 0.003251 | 1.9462 | 7.303 | 989 | 0.00022369 | 2313 | 0 | 0 | 2.2416 | 2473 | 0
Central Coast | 4675 | 262 | 530.979 | 933 | 887.728 | 40 | 0.00010201 | 0.066432 | 1.8602 | 3.6017 | 10.237 | 0.062826 | 0.56637 | 2.0469 | 1 | 6.7764e-06 | 0.00015416 | 0.28081 | 0.59813 | {08861202-71CD-43A7-A4E9-A7647717C791} | 83622103 | CAMP EVERS 2103 | 5404 | 37.0156 | -122.0254 | CAMP EVERS 21035404 | 123 | 259 | 20529.4484 | 7424.9094 | 13104.539 | 3769.8779 | 5953.0121 | 0.0061665 | 0.0040802 | 2.0266 | 23.325 | 1570 | 0.00027106 | 2314 | 0 | 0 | 2.3425 | 2426 | 0
Bay Area | 8715 | 25 | 47.3208 | 29 | 49.0002 | 7 | 5.3626e-05 | 0.13365 | 0.55842 | 141.7798 | 1515.9567 | 16.4761 | 0.29962 | 68.1425 | 1.3467 | 6.6732e-06 | 4.1344e-05 | 0.86207 | 0.96573 | {CCC05F57-600B-48FA-93EA-7CC307C90265} | 43051101 | MONTICELLO 1101 | circuit_breaker | 38.509 | -122.2142 | MONTICELLO 1101circuit_breaker | 12 | 1 | 908.7874 | 898.3339 | 10.4536 | 898.3339 | 10.4536 | 0.0002894 | 0.00037538 | 1.8928 | 4.1429 | 2320 | 4.6712e-05 | 2315 | 0 | 0 | 0.5582 | 2683 | 0
North Coast | 4368 | 244 | 314.0387 | 422 | 418.1051 | 25 | 7.5127e-05 | 0.088813 | 0.6944 | 11.5694 | 112.2819 | 0.22406 | 1.9154 | 43.3308 | 1.1908 | 6.6555e-06 | 5.9039e-05 | 0.5782 | 0.7511 | {3FDFEE62-2564-4B56-8AC9-FC80D427FADF} | 42091102 | MIRABEL 1102 | 206 | 38.4907 | -122.8886 | MIRABEL 1102206 | 247 | 273 | 39580.3282 | 20489.8622 | 19090.466 | 2879.3705 | 1476.4703 | 0.001476 | 0.0018782 | 1.287 | 16.88 | 2151 | 0.00016639 | 2316 | 0 | 0 | 1.7892 | 2464 | 0
North Coast | 636 | 80 | 149.7785 | 180 | 192.7952 | 26 | 9.9908e-05 | 0.066432 | 1.1117 | 1.7612 | 5.5469 | 0.013399 | 2.2126 | 4.1619 | 1.0002 | 6.6371e-06 | 9.8389e-05 | 0.44444 | 0.77688 | {6CC0AC14-D9A2-4DF6-8158-C7F692F1F8D5} | 43311108 | KONOCTI 1108 | 4039 | 38.9545 | -122.7186 | KONOCTI 11084039 | 46 | 185 | 12452.101 | 3707.395 | 8744.7059 | 2945.2304 | 5641.5661 | 0.0025581 | 0.0025976 | 1.8722 | 6.9231 | 1860 | 0.00017256 | 2317 | 0 | 0 | 1.8301 | 43 | 0
Sierra | 3558 | 21 | 37.3317 | 151 | 93.0599 | 23 | 0.00013513 | 0.046213 | 2.2307 | 2.1489 | 5.3744 | 0.052368 | 1.8531 | 6.4394 | 2.1766 | 6.6098e-06 | 0.00032765 | 0.13907 | 0.40116 | {8B190E99-2FFD-4283-B3F1-C9A94DD8C8D7} | 152161102 | AUBURN 1102 | circuit_breaker | 38.9035 | -121.0697 | AUBURN 1102circuit_breaker | 253 | 859 | 39857.9828 | 11240.5926 | 28617.3902 | 1981.8221 | 4529.0995 | 0.007536 | 0.0031079 | 1.7777 | 6.5652 | 1061 | 0.00015203 | 2318 | 0 | 0 | 1.2314 | 156 | 0
Sierra | 5199 | 46 | 84.3327 | 161 | 126.3891 | 15 | 0.00011329 | 0.057574 | 15.6578 | 71.6476 | 400.9042 | 34.5625 | 1.0865 | 9.577 | 1.5336 | 6.5866e-06 | 0.00034345 | 0.28571 | 0.66725 | {76BB324A-98B3-4C58-A6D4-32DC864FAEB9} | 152261105 | DIAMOND SPRINGS 1105 | circuit_breaker | 38.693 | -120.8258 | DIAMOND SPRINGS 1105circuit_breaker | 104 | 269 | 17199.2943 | 7563.6203 | 9635.674 | 2499.6007 | 1536.8699 | 0.0051518 | 0.0016994 | 1.8333 | 10.7333 | 1024 | 9.8799e-05 | 2319 | 0 | 0 | 1.5532 | 440 | 0
Central Coast | 7115 | 1122 | 2060.102 | 2081 | 2557.896 | 154 | 9.8739e-05 | 0.066514 | 1.8718 | 27.5853 | 117.9282 | 0.61672 | 0.90471 | 19.7558 | 1.0763 | 6.5644e-06 | 0.00015347 | 0.53916 | 0.80539 | {F407D1C7-AF54-4B98-B726-B5AC300E0031} | 83692104 | ROB ROY 2104 | 10298 | 36.9935 | -121.7994 | ROB ROY 210410298 | 205 | 234 | 38480.3999 | 21488.8231 | 16991.5768 | 17304.3139 | 11693.6514 | 0.023635 | 0.015206 | 1.8361 | 13.513 | 1572 | 0.0010109 | 2320 | 0 | 0 | 10.7524 | 1774 | 0
Sierra | 1048 | 449 | 681.8853 | 1501 | 1120.8474 | 115 | 0.00010196 | 0.064121 | 12.6477 | 27.286 | 104.9744 | 3.037 | 0.70323 | 11.0135 | 1.125 | 6.5557e-06 | 0.0007357 | 0.29913 | 0.60837 | {AE525890-6C02-4814-857B-4FEF1E7D58A9} | 152261106 | DIAMOND SPRINGS 1106 | 99658 | 38.6947 | -120.8146 | DIAMOND SPRINGS 110699658 | 346 | 591 | 51459.0595 | 20441.9062 | 31017.1533 | 12193.3312 | 18084.702 | 0.084605 | 0.011726 | 1.5187 | 13.0522 | 544 | 0.0007539 | 2321 | 0 | 0 | 7.5766 | 125 | 0
Sierra | 6385 | 217 | 310.7363 | 644 | 527.152 | 54 | 9.8637e-05 | 0.066432 | 9.9109 | 56.8242 | 513.7497 | 21.1636 | 0.28839 | 2.438 | 1 | 6.5526e-06 | 0.00065351 | 0.33696 | 0.58946 | {2907BFC6-6471-42FA-915F-D557946D20D1} | 152241102 | HALSEY 1102 | 6129 | 38.9855 | -121.0049 | HALSEY 11026129 | 67 | 115 | 10408.9165 | 5155.4944 | 5253.4221 | 5155.4944 | 5253.4221 | 0.03529 | 0.0053264 | 1.432 | 11.9259 | 611 | 0.00035384 | 2322 | 0 | 0 | 3.2035 | 461 | 0
Central Valley | 5467 | 72 | 99.8059 | 480 | 269.6757 | 40 | 9.8453e-05 | 0.066432 | 1.6069 | 5.3165 | 10.2147 | 0.04908 | 1.4289 | 8.2313 | 0.97677 | 6.5405e-06 | 0.00014559 | 0.15 | 0.3701 | {9E6CCAD4-16BF-438A-8FB8-933F07D27C09} | 163351701 | CURTIS 1701 | 90120 | 37.9736 | -120.3748 | CURTIS 170190120 | 186 | 477 | 31034.2008 | 8306.5424 | 22727.6584 | 4659.8125 | 11656.5568 | 0.0058235 | 0.0039381 | 1.3862 | 12 | 1616 | 0.00026162 | 2323 | 0 | 0 | 2.8955 | 1538 | 0
Bay Area | 1875 | 1093 | 2553.8657 | 2680 | 3506.7202 | 247 | 6.0591e-05 | 0.25357 | 7.2171 | 9.8752 | 25.1493 | 0.57652 | 1.3933 | 9.1897 | 1.2967 | 6.5172e-06 | 0.00024379 | 0.40784 | 0.72828 | {65BF29A6-90D7-4E9D-9D0F-0B463AE68E56} | 13801104 | MORAGA 1104 | circuit_breaker | 37.8489 | -122.1616 | MORAGA 1104circuit_breaker | 599 | 1994 | 133068.7819 | 34925.1276 | 98143.6543 | 22579.2249 | 62314.8408 | 0.060217 | 0.014966 | 2.3366 | 10.8502 | 1267 | 0.0016097 | 2324 | 0 | 0 | 14.0301 | 1109 | 0
Sierra | 575 | 1327 | 1869.9546 | 2591 | 2515.91 | 202 | 9.8624e-05 | 0.066103 | 4.572 | 17.8013 | 82.8764 | 1.1095 | 2.0424 | 13.4917 | 1.0441 | 6.5083e-06 | 0.00025664 | 0.51216 | 0.74325 | {BD845FF4-9DE1-4881-9265-8047FD3823B1} | 152491102 | WEIMAR 1102 | 2038 | 39.0315 | -121.0046 | WEIMAR 11022038 | 260 | 326 | 34488.7744 | 21541.6585 | 12947.1159 | 21541.6585 | 12947.1159 | 0.051842 | 0.019922 | 1.4092 | 12.8267 | 1234 | 0.0013147 | 2325 | 0 | 0 | 13.3854 | 193 | 0
Central Coast | 4947 | 1223 | 2579.7422 | 4198 | 4243.8896 | 240 | 9.7666e-05 | 0.066432 | 6.1085 | 21.9196 | 87.7722 | 0.98193 | 1.0993 | 10.0919 | 1.0137 | 6.4881e-06 | 0.00029453 | 0.29133 | 0.60787 | {D6E3B990-3B6A-4843-9D6C-590EB1D40E85} | 83252104 | PAUL SWEET 2104 | 5394 | 36.9884 | -121.9697 | PAUL SWEET 21045394 | 310 | 244 | 39103.2411 | 24535.8062 | 14567.4349 | 23022.1384 | 13536.8874 | 0.070688 | 0.02344 | 2.1094 | 17.4917 | 1138 | 0.0015572 | 2326 | 0 | 0 | 14.3053 | 2148 | 0
Bay Area | 2851 | 27 | 49.7979 | 38 | 55.2591 | 3 | 9.7457e-05 | 0.066432 | 9.4292 | 9.2878 | 30.8484 | 0.29253 | 0.28761 | 2.2035 | 1 | 6.4742e-06 | 0.0003198 | 0.71053 | 0.90117 | {626A33F5-DB74-4A90-9B40-B8EBDFF91330} | 13810401 | WAYNE 0401 | 75010 | 37.8344 | -122.0198 | WAYNE 040175010 | 43 | 170 | 12048.5767 | 4201.0119 | 7847.5648 | 282.8935 | 328.8002 | 0.00095941 | 0.00029237 | 1.8444 | 12.6667 | 1075 | 1.9423e-05 | 2327 | 0 | 0 | 0.17578 | 2622 | 0
Central Coast | 9182 | 13 | 33.8216 | 135 | 88.5977 | 13 | 4.8956e-05 | 0.1349 | 0.79278 | 11.3987 | 34.2937 | 0.072608 | 0.6855 | 20.2301 | 1.0199 | 6.4299e-06 | 4.7206e-05 | 0.096296 | 0.38174 | {BDB273FE-3F8C-49DE-9FCD-F1023DEEBFB9} | 82931101 | POINT MORETTI 1101 | 83716 | 37.0863 | -122.261 | POINT MORETTI 110183716 | 28 | 18 | 7780.9482 | 4270.6499 | 3510.2983 | 3791.8733 | 3510.2983 | 0.00061368 | 0.00063643 | 2.6017 | 10.3846 | 2260 | 8.3588e-05 | 2328 | 0 | 0 | 2.3562 | 1627 | 0
Sierra | 7131 | 15 | 26.2903 | 30 | 33.2964 | 8 | 9.6785e-05 | 0.066432 | 12.1774 | 13.3934 | 55.7945 | 1.3538 | 0.74723 | 5.8707 | 1.0088 | 6.4295e-06 | 0.00038069 | 0.5 | 0.78958 | {68DF9E12-6736-4943-BDEF-9FA6962872B3} | 152531101 | FLINT 1101 | circuit_breaker | 38.8851 | -121.0671 | FLINT 1101circuit_breaker | 89 | 260 | 13483.6798 | 4181.0836 | 9302.5962 | 831.0934 | 458.9801 | 0.0030455 | 0.00077428 | 1.7527 | 3.75 | 967 | 5.1436e-05 | 2329 | 0 | 0 | 0.51642 | 300 | 0
North Coast | 5217 | 941 | 1780.7154 | 1422 | 1991.938 | 183 | 8.3523e-05 | 0.074366 | 8.3422 | 51.8202 | 216.7384 | 4.7929 | 0.6747 | 5.4381 | 1.3755 | 6.4234e-06 | 0.00042111 | 0.66174 | 0.89396 | {BC4F0196-621B-4CEE-9F22-55FAA9EB12A8} | 42761104 | FORT BRAGG A 1104 | 1316 | 39.4439 | -123.7909 | FORT BRAGG A 11041316 | 315 | 492 | 52894.9484 | 22356.1761 | 30538.7724 | 21724.3712 | 29312.4564 | 0.077063 | 0.015285 | 1.8924 | 7.7705 | 908 | 0.0011755 | 2330 | 0 | 0 | 13.4989 | 1447 | 0
North Coast | 1796 | 598 | 922.9625 | 1119 | 1220.5382 | 105 | 0.00010354 | 0.061369 | 3.1231 | 3.072 | 12.2374 | 0.1467 | 0.031579 | 0.11204 | 0.70476 | 6.378e-06 | 0.0002154 | 0.53441 | 0.75619 | {53C74AF7-2A69-47CF-8DFD-9E70E0E39334} | 42151104 | SANTA ROSA A 1104 | 210 | 38.4571 | -122.6979 | SANTA ROSA A 1104210 | 287 | 547 | 39862.5454 | 12743.9815 | 27118.5639 | 10547.5245 | 22521.0613 | 0.022617 | 0.010871 | 1.5434 | 10.6571 | 1358 | 0.00066969 | 2331 | 0 | 0 | 6.5539 | 2132 | 0
Sierra | 4061 | 0 | 0 | 2 | 0.9768 | 1 | 9.5462e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3417e-06 | 0 | 0 | 0 | {343B25CA-8FEF-457F-8025-88904C29692A} | 152031102 | GRASS VALLEY 1102 | circuit_breaker | 39.209 | -121.0612 | GRASS VALLEY 1102circuit_breaker | 202 | 717 | 29463.1636 | 6752.0314 | 22711.1322 | 284.9196 | 366.8712 | 0 | 9.5462e-05 |  | 2 | 2890 | 6.3417e-06 | 2332 | 0 | 0 | 0.17704 | 1577 | 0
Sierra | 9057 | 27 | 50.7498 | 214 | 127.4867 | 24 | 0.00011183 | 0.05536 | 1.242 | 1.6989 | 8.9261 | 0.025163 | 1.7301 | 8.1263 | 1.6704 | 6.314e-06 | 0.00013775 | 0.12617 | 0.39808 | {2450AEE7-F575-4F58-91A2-1411AECC8344} | 152161102 | AUBURN 1102 | 8611 | 38.9083 | -121.0618 | AUBURN 11028611 | 51 | 194 | 10112.7193 | 2944.6304 | 7168.0889 | 2944.6304 | 7168.0889 | 0.0033061 | 0.0026838 | 1.8796 | 8.9167 | 1646 | 0.00015154 | 2333 | 0 | 0 | 1.8297 | 1097 | 0
Sierra | 6462 | 51 | 68.6733 | 150 | 113.3815 | 17 | 0.00014806 | 0.042985 | 5.1316 | 7.6465 | 27.4707 | 0.24343 | 0.20852 | 3.3435 | 2.4118 | 6.3118e-06 | 0.00044046 | 0.34 | 0.60568 | {3EFAA303-A7DE-4E0F-A383-778B2D3996D4} | 152481110 | BRUNSWICK 1110 | 3907 | 39.2224 | -121.0816 | BRUNSWICK 11103907 | 26 | 149 | 7687.1182 | 1437.9091 | 6249.2092 | 1437.9091 | 6249.2092 | 0.0074878 | 0.0025169 | 1.3465 | 8.8235 | 880 | 0.0001073 | 2334 | 0 | 0 | 0.89347 | 2393 | 0
North Coast | 5753 | 297 | 453.4226 | 346 | 480.6873 | 34 | 9.3729e-05 | 0.066432 | 2.2355 | 64.6539 | 665.1945 | 3.4525 | 0.47697 | 5.2973 | 1 | 6.2266e-06 | 0.00016812 | 0.85838 | 0.94328 | {69363607-FF8E-409A-B5BD-8D40D2F4E07A} | 43081101 | BIG RIVER 1101 | 2183 | 39.3445 | -123.7782 | BIG RIVER 11012183 | 42 | 45 | 5944.8098 | 4246.8638 | 1697.9459 | 4246.8638 | 1697.9459 | 0.0057161 | 0.0031868 | 1.5267 | 10.1765 | 1523 | 0.0002117 | 2335 | 0 | 0 | 2.6389 | 63 | 0
Central Valley | 9867 | 14 | 28.1379 | 18 | 30.0735 | 8 | 2.7833e-05 | 0.42089 | 0.15298 | 831.9038 | 4526.746 | 0.94293 | 0.1474 | 111.955 | 1.1867 | 6.2246e-06 | 1.5708e-05 | 0.77778 | 0.93564 | {3A07F3B8-E9B8-45C5-8744-6792C16A4186} | 252192105 | BEAR VALLEY 2105 | circuit_breaker | 37.5861 | -120.1255 | BEAR VALLEY 2105circuit_breaker | 17 | 4 | 7018.3692 | 6175.4075 | 842.9617 | 6175.4075 | 842.9617 | 0.00012567 | 0.00022266 | 2.0098 | 2.25 | 2690 | 4.9797e-05 | 2336 | 0 | 0 | 3.8372 | 282 | 0
North Coast | 7454 | 220 | 386.6892 | 261 | 405.448 | 25 | 9.3655e-05 | 0.066432 | 7.2685 | 23.0226 | 57.0816 | 0.48571 | 1.2827 | 4.8511 | 1.0023 | 6.2217e-06 | 0.00041357 | 0.84291 | 0.95373 | {A11A44BE-5FF6-4EAE-B643-DC3914767492} | 42761102 | FORT BRAGG A 1102 | circuit_breaker | 39.4351 | -123.7995 | FORT BRAGG A 1102circuit_breaker | 158 | 231 | 24023.6809 | 9307.747 | 14715.9339 | 2547.229 | 2327.4184 | 0.010339 | 0.0023414 | 1.7577 | 10.44 | 922 | 0.00015554 | 2337 | 0 | 0 | 1.5828 | 1580 | 0
Central Coast | 3462 | 2 | 2.7861 | 19 | 13.4174 | 4 | 9.3108e-05 | 0.066432 | 3.5587 | 2.9654 | 7.3261 | 0.028182 | 0.58241 | 1.8663 | 0.75 | 6.1854e-06 | 0.00024929 | 0.10526 | 0.20765 | {F85FD245-E951-4FD5-89D8-9A5F2519071F} | 83500402 | SEACLIFF 0402 | circuit_breaker | 36.9842 | -121.9154 | SEACLIFF 0402circuit_breaker | 46 | 229 | 12860.1259 | 2486.9473 | 10373.1786 | 417.7951 | 669.3148 | 0.00099714 | 0.00037243 | 1.3931 | 4.75 | 1250 | 2.4741e-05 | 2338 | 0 | 0 | 0.25961 | 551 | 0
Central Coast | 6144 | 358 | 804.6415 | 431 | 839.606 | 14 | 9.2943e-05 | 0.066431 | 3.2336 | 53.0178 | 183.8797 | 0.68518 | 0.07854 | 11.9475 | 1 | 6.1743e-06 | 0.00018291 | 0.83063 | 0.95836 | {E8501414-249C-40BD-935F-69A6CB98996A} | 83692104 | ROB ROY 2104 | 9973 | 37.025 | -121.8205 | ROB ROY 21049973 | 5 | 6 | 1511.1258 | 921.5182 | 589.6075 | 921.5182 | 589.6075 | 0.0025607 | 0.0013012 | 2.2476 | 30.7857 | 1473 | 8.644e-05 | 2339 | 0 | 0 | 0.5726 | 2080 | 0
North Coast | 4805 | 8 | 12.2688 | 13 | 14.9362 | 1 | 9.279e-05 | 0.066431 | 9.6497 | 33.2084 | 170.9604 | 1.7391 | 1 | 0.1 | 1 | 6.1642e-06 | 0.00089539 | 0.61538 | 0.82141 | {7C1CBDE8-4F9F-4F23-AED7-897BEA3B5B02} | 42811113 | MONTE RIO 1113 | 652 | 38.5199 | -122.9782 | MONTE RIO 1113652 | 61 | 372 | 9873.0436 | 2244.0392 | 7629.0044 | 2244.0392 | 7629.0044 | 0.00089539 | 9.279e-05 | 1.5336 | 13 | 450 | 6.1642e-06 | 2340 | 0 | 0 | 1.3944 | 917 | 0
Bay Area | 3797 | 34 | 124.3499 | 256 | 256.3399 | 35 | 3.6246e-05 | 0.19759 | 0.93601 | 25.7176 | 49.4658 | 0.135 | 1.4016 | 36.4998 | 1.0258 | 6.1457e-06 | 1.9268e-05 | 0.13281 | 0.4851 | {31523F0A-9FD2-41D0-8A36-117080631D88} | 13432207 | FAIRVIEW 2207 | P304 | 38.0478 | -122.2054 | FAIRVIEW 2207P304 | 157 | 176 | 18581.7049 | 10027.5804 | 8554.1245 | 8495.039 | 8423.1743 | 0.00067436 | 0.0012686 | 3.6573 | 7.3143 | 2627 | 0.0002151 | 2341 | 0 | 0 | 5.2786 | 2851 | 0
North Coast | 2043 | 0 | 0 | 1 | 0.45574 | 1 | 9.204e-05 | 0.066432 |  |  |  |  | 0.011062 | 0.44159 | 1 | 6.1144e-06 | 9.204e-05 | 0 | 0 | {8A80C7E5-86DA-415B-A0BF-702ACAC61E9A} | 192151131 | NEWBURG 1131 | 3446 | 40.5488 | -124.1425 | NEWBURG 11313446 | 122 | 180 | 22023.6885 | 13140.8369 | 8882.8516 | 0 | 163.4304 | 9.204e-05 | 9.204e-05 |  | 1 | 1896 | 6.1144e-06 | 2342 | 0 | 0 | 0 | 1102 | 0
Central Coast | 9752 | 132 | 213.7163 | 152 | 224.5288 | 8 | 8.9474e-05 | 0.068021 | 2.4615 | 48.8974 | 222.4786 | 0.83465 | 2.3266 | 24.942 | 1.0476 | 6.0839e-06 | 0.00013828 | 0.86842 | 0.95184 | {0AA45AF7-C211-4B8E-8C0A-4D0687522BE1} | 83192101 | GREEN VALLEY 2101 | 1645 | 37.0218 | -121.7653 | GREEN VALLEY 21011645 | 11 | 7 | 1811.2353 | 777.8514 | 1033.3839 | 777.8514 | 1033.3839 | 0.0011062 | 0.0007158 | 1.6191 | 19 | 1639 | 4.8671e-05 | 2343 | 0 | 0 | 0.48333 | 1676 | 0
North Coast | 6706 | 268 | 503.5228 | 319 | 526.541 | 35 | 9.6879e-05 | 0.062636 | 4.0897 | 21.6953 | 70.7215 | 0.29065 | 0.099903 | 2.1853 | 1.2286 | 6.075e-06 | 0.00021702 | 0.84013 | 0.95628 | {DCB2091F-52D0-405B-8DDE-82750DB61471} | 42761102 | FORT BRAGG A 1102 | 816 | 39.4119 | -123.7985 | FORT BRAGG A 1102816 | 54 | 71 | 8375.0865 | 4123.7572 | 4251.3292 | 3663.972 | 3892.9012 | 0.0075959 | 0.0033907 | 1.8788 | 9.1143 | 1352 | 0.00021262 | 2344 | 0 | 0 | 2.2767 | 2489 | 0
Bay Area | 2319 | 3 | 6.4548 | 9 | 9.1893 | 5 | 5.4295e-05 | 0.11221 | 0.034142 | 0.1112 | 0.12046 | 8.2255e-06 | 2.6071 | 12.4541 | 1.0044 | 6.0567e-06 | 2.2233e-05 | 0.33333 | 0.70243 | {4118C23A-F427-46E8-85D2-FD56A1055C29} | 22811101 | PACIFICA 1101 | 5001 | 37.5925 | -122.4741 | PACIFICA 11015001 | 147 | 349 | 21321.7311 | 8433.2827 | 12888.4483 | 1174.8636 | 1671.262 | 0.00011117 | 0.00027147 | 2.1516 | 1.8 | 2576 | 3.0284e-05 | 2345 | 0 | 0 | 0.73003 | 2834 | 0
Central Valley | 34 | 27 | 42.528 | 245 | 131.9305 | 24 | 9.0848e-05 | 0.066432 | 8.8868 | 13.6328 | 32.6996 | 0.64837 | 0.87583 | 6.799 | 1.0024 | 6.0352e-06 | 0.00031911 | 0.1102 | 0.32235 | {BD6EE575-4256-4E66-B07C-5D3BE152301A} | 163351701 | CURTIS 1701 | 9230 | 37.9737 | -120.3716 | CURTIS 17019230 | 84 | 189 | 14068.9438 | 5067.8425 | 9001.1013 | 3602.8642 | 5014.3448 | 0.0076586 | 0.0021803 | 1.5751 | 10.2083 | 1078 | 0.00014484 | 2346 | 0 | 0 | 2.2387 | 58 | 0
Bay Area | 3357 | 17 | 33.5638 | 67 | 58.3917 | 5 | 9.0165e-05 | 0.066431 | 0.044093 | 4.9682 | 31.0069 | 0.0028852 | 0 | 0.0058407 | 0.2 | 5.9897e-06 | 3.7469e-05 | 0.25373 | 0.5748 | {B6480B23-3B7E-4A3F-9C7B-82F910A25330} | 42711102 | CALISTOGA 1102 | circuit_breaker | 38.5921 | -122.5788 | CALISTOGA 1102circuit_breaker | 95 | 198 | 13787.7035 | 4507.3331 | 9280.3704 | 862.9478 | 717.3783 | 0.00018735 | 0.00045082 | 1.9743 | 13.4 | 2371 | 2.9949e-05 | 2347 | 0 | 0 | 0.53621 | 2591 | 0
North Coast | 7060 | 995 | 1625.1915 | 1273 | 1754.894 | 62 | 9.0135e-05 | 0.066432 | 4.1168 | 57.9356 | 167.3373 | 1.499 | 0.78925 | 20.77 | 1.0303 | 5.9878e-06 | 0.00022577 | 0.78162 | 0.92609 | {5E0A571A-4E57-4C9B-881D-B7EA8F011B21} | 192251102 | RIO DELL 1102 | 8852 | 40.4932 | -124.1078 | RIO DELL 11028852 | 65 | 57 | 11998.5658 | 7652.3134 | 4346.2524 | 6733.2314 | 4232.9276 | 0.013998 | 0.0055884 | 1.6334 | 20.5323 | 1326 | 0.00037125 | 2348 | 0 | 0 | 4.1838 | 317 | 0
Bay Area | 9133 | 9 | 18.4775 | 28 | 28.9045 | 3 | 8.9593e-05 | 0.066431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.9518e-06 | 5.6394e-05 | 0.32143 | 0.63926 | {BDEB9DF5-5559-414A-A4C0-A31B6D586A57} | 42011107 | SAN RAFAEL 1107 | 3323 | 37.9574 | -122.5415 | SAN RAFAEL 11073323 | 4 | 29 | 1320.5965 | 214.7286 | 1105.8679 | 214.7286 | 1105.8679 | 0.00016918 | 0.00026878 | 2.0531 | 9.3333 | 2179 | 1.7855e-05 | 2349 | 0 | 0 | 0.13343 | 2190 | 0
North Coast | 3591 | 86 | 107.4592 | 159 | 149.3785 | 10 | 8.9261e-05 | 0.06643 | 6.5704 | 7.7145 | 20.6373 | 0.29324 | 0.41637 | 2.7673 | 1 | 5.9296e-06 | 0.00039612 | 0.54088 | 0.71938 | {3D15A0FB-7F79-449E-9100-AEDACD615B82} | 43302107 | MONROE 2107 | 65424 | 38.4692 | -122.7337 | MONROE 210765424 | 229 | 424 | 26680.8981 | 8210.9441 | 18469.954 | 1114.9522 | 1002.473 | 0.0039612 | 0.00089261 | 1.2495 | 15.9 | 949 | 5.9296e-05 | 2350 | 0 | 0 | 0.6928 | 1946 | 0
Bay Area | 4004 | 33 | 58.7989 | 192 | 147.1119 | 16 | 8.8843e-05 | 0.066431 | 0.16425 | 0.085901 | 0.0010314 | 4.3857e-07 | 0.15238 | 0.27277 | 1 | 5.902e-06 | 6.7662e-05 | 0.17188 | 0.39969 | {9E4C5477-E966-43D5-8E24-BB781F7AED7E} | 43091103 | GREENBRAE 1103 | circuit_breaker | 37.938 | -122.5144 | GREENBRAE 1103circuit_breaker | 195 | 529 | 29052.8511 | 8367.7567 | 20685.0944 | 1165.1033 | 3911.8523 | 0.0010826 | 0.0014215 | 1.7818 | 12 | 2073 | 9.4432e-05 | 2351 | 0 | 0 | 0.72396 | 2457 | 0
Sierra | 6665 | 46 | 63.2024 | 139 | 102.1257 | 12 | 8.8627e-05 | 0.066432 | 2.4482 | 13.852 | 107.2568 | 0.62023 | 1.1556 | 10.4763 | 1.0184 | 5.8876e-06 | 0.00014837 | 0.33094 | 0.61887 | {8A1F3383-8C42-4458-990C-2355B321D3F3} | 152481102 | BRUNSWICK 1102 | 940 | 39.2191 | -121.0227 | BRUNSWICK 1102940 | 138 | 113 | 9056.2054 | 5596.7061 | 3459.4993 | 1331.1883 | 719.0227 | 0.0017804 | 0.0010635 | 1.374 | 11.5833 | 1601 | 7.0652e-05 | 2352 | 0 | 0 | 0.82716 | 2521 | 0
Central Coast | 7708 | 214 | 291.3697 | 769 | 627.7358 | 52 | 8.8589e-05 | 0.066432 | 0.19204 | 57.1029 | 319.7454 | 0.15675 | 0.09994 | 17.5085 | 1.1068 | 5.8852e-06 | 4.8137e-05 | 0.27828 | 0.46416 | {6B92ED0F-B7EF-410B-BAC6-F6F35DBFC4A1} | 182371111 | LAURELES 1111 | 10141 | 36.423 | -121.7328 | LAURELES 111110141 | 29 | 77 | 6725.2735 | 4696.5789 | 2028.6946 | 4696.5789 | 2028.6946 | 0.0025031 | 0.0046066 | 1.3615 | 14.7885 | 2248 | 0.00030603 | 2353 | 0 | 0 | 2.9183 | 1785 | 0
Sierra | 2848 | 71 | 120.0514 | 221 | 186.6344 | 20 | 8.8363e-05 | 0.066432 | 7.0665 | 112.9465 | 955.4909 | 22.8072 | 0.84137 | 12.0041 | 1.0074 | 5.8701e-06 | 0.00022167 | 0.32127 | 0.64324 | {D36692F8-5845-4D8F-B564-14537DDF3E03} | 152461101 | PLACER 1101 | circuit_breaker | 38.9009 | -121.0878 | PLACER 1101circuit_breaker | 247 | 767 | 37225.5733 | 12115.2189 | 25110.3544 | 1809.155 | 1094.872 | 0.0044334 | 0.0017673 | 1.6909 | 11.05 | 1337 | 0.0001174 | 2354 | 0 | 0 | 1.1242 | 1890 | 0
Bay Area | 3790 | 45 | 64.9297 | 106 | 97.4968 | 11 | 8.8094e-05 | 0.066431 | 0.1797 | 0.043297 | 0.00085438 | 7.8864e-07 | 0.050885 | 0.01601 | 0.090909 | 5.8522e-06 | 5.3675e-05 | 0.42453 | 0.66597 | {2F8A55EE-31E9-4610-BC55-DCCDEAC8DCB6} | 42011108 | SAN RAFAEL 1108 | 1457 | 37.9823 | -122.5776 | SAN RAFAEL 11081457 | 20 | 206 | 9640.8883 | 1229.3805 | 8411.5078 | 1229.3805 | 8411.5078 | 0.00059042 | 0.00096904 | 1.4429 | 9.6364 | 2207 | 6.4374e-05 | 2355 | 0 | 0 | 0.7639 | 1331 | 0
Central Coast | 6318 | 73 | 131.3634 | 735 | 527.0305 | 83 | 3.2407e-05 | 0.17812 | 0.25663 | 10.2442 | 86.4744 | 0.73419 | 2.3992 | 45.1355 | 1.1453 | 5.8014e-06 | 2.0587e-05 | 0.09932 | 0.24925 | {1AB7CEED-5C4C-4BB2-AA34-33FF777E7C4A} | 83481110 | STELLING 1110 | 60090 | 37.2932 | -122.0984 | STELLING 111060090 | 103 | 58 | 16657.0456 | 10542.2205 | 6114.825 | 10215.1138 | 6107.196 | 0.0017087 | 0.0026898 | 1.7995 | 8.8554 | 2596 | 0.00048152 | 2356 | 0 | 0 | 6.3474 | 2011 | 0
Central Valley | 525 | 0 | 0 | 6 | 3.0352 | 3 | 8.7288e-05 | 0.066431 | 5.5527 | 165.655 | 3353.8958 | 398.5653 | 0.44027 | 0.78407 | 0.66667 | 5.7986e-06 | 0.00052962 | 0 | 0 | {DBBC669E-53C3-46F8-B180-51E0DC203C00} | 162821702 | STANISLAUS 1702 | 37278 | 38.2465 | -120.3643 | STANISLAUS 170237278 | 210 | 460 | 27570.4484 | 10956.0145 | 16614.4339 | 10956.0145 | 16614.4339 | 0.0015888 | 0.00026186 |  | 2 | 760 | 1.7396e-05 | 2357 | 0 | 0 | 6.8077 | 1117 | 0
North Coast | 6622 | 70 | 133.873 | 98 | 150.0621 | 8 | 0.00013426 | 0.04152 | 3.7368 | 6.395 | 51.1371 | 1.0283 | 0.3326 | 0.31261 | 2.5 | 5.7824e-06 | 0.00040829 | 0.71429 | 0.89212 | {CF6DCD50-9D01-424C-A63A-95836ADA2180} | 42091102 | MIRABEL 1102 | 2043 | 38.5038 | -122.9457 | MIRABEL 11022043 | 11 | 102 | 3983.4628 | 914.8961 | 3068.5667 | 914.8961 | 3068.5667 | 0.0032663 | 0.0010741 | 1.9125 | 12.25 | 932 | 4.626e-05 | 2358 | 0 | 0 | 0.56849 | 575 | 0
Central Coast | 8605 | 0 | 0 | 4 | 2.3903 | 3 | 1.1283e-05 | 0.49454 |  |  |  |  | 0.71386 | 106.1849 | 1.0015 | 5.7663e-06 | 1.1283e-05 | 0 | 0 | {B456B97B-6207-41D3-9457-CFE202A63FCC} | 182971101 | PURISIMA 1101 | 54728 | 34.7596 | -120.4087 | PURISIMA 110154728 | 37 | 18 | 7672.2464 | 7210.7913 | 461.455 | 1017.1008 | 278.46 | 3.3848e-05 | 3.3848e-05 |  | 1.3333 | 2772 | 1.7299e-05 | 2359 | 0 | 0 | 0.632 | 1679 | 0
Sierra | 3632 | 9 | 12.7641 | 48 | 31.0543 | 24 | 9.0648e-05 | 0.063664 | 5.1611 | 3.7811 | 10.2896 | 0.14234 | 1.9228 | 3.7099 | 1.1669 | 5.7637e-06 | 0.00023064 | 0.1875 | 0.41102 | {A034BC39-5C36-44F2-830F-5D5EFC9DEDAA} | 152481103 | BRUNSWICK 1103 | 2784 | 39.2593 | -121.0188 | BRUNSWICK 11032784 | 471 | 1175 | 76990.2656 | 24636.8737 | 52353.3919 | 23108.4794 | 49616.363 | 0.0055353 | 0.0021755 | 1.4182 | 2 | 1308 | 0.00013833 | 2360 | 0 | 0 | 14.3589 | 417 | 0
Central Coast | 4068 | 556 | 984.0559 | 2103 | 1862.9746 | 149 | 8.6674e-05 | 0.066431 | 4.1254 | 28.964 | 124.1958 | 0.80464 | 0.84981 | 9.8649 | 1.009 | 5.7579e-06 | 0.00023258 | 0.26438 | 0.52822 | {FE58AABB-4F2E-4F6C-8A2E-70A2F4BDC1F4} | 82021107 | LOS GATOS 1107 | 60092 | 37.1825 | -121.985 | LOS GATOS 110760092 | 184 | 254 | 29029.3203 | 15505.8611 | 13523.4592 | 15505.8611 | 13523.4592 | 0.034654 | 0.012914 | 1.7699 | 14.1141 | 1306 | 0.00085793 | 2361 | 0 | 0 | 9.6349 | 572 | 0
North Coast | 2184 | 275 | 618.6151 | 395 | 674.6357 | 31 | 8.6526e-05 | 0.066432 | 4.5901 | 19.5007 | 151.3529 | 3.0331 | 0.28654 | 1.3778 | 1.0006 | 5.7481e-06 | 0.00024334 | 0.6962 | 0.91696 | {75E57175-6FC2-4C18-9858-49FEBB55AE91} | 42761102 | FORT BRAGG A 1102 | 1226 | 39.4116 | -123.8087 | FORT BRAGG A 11021226 | 202 | 288 | 30428.6582 | 12668.4441 | 17760.2141 | 2760.5742 | 3664.4609 | 0.0075435 | 0.0026823 | 2.2495 | 12.7419 | 1270 | 0.00017819 | 2362 | 0 | 0 | 1.7153 | 1583 | 0
Bay Area | 6381 | 22 | 34.8966 | 231 | 146.2579 | 12 | 8.5992e-05 | 0.066431 | 0.94714 | 0.58522 | 2.0878 | 0.0070499 | 0 | 1.3331e-15 | 3.7896e-14 | 5.7125e-06 | 8.2686e-05 | 0.095238 | 0.2386 | {0E23B264-3DB8-4CEC-B1FE-F1CB20A30CF5} | 42011101 | SAN RAFAEL 1101 | 68970 | 37.9735 | -122.5333 | SAN RAFAEL 110168970 | 170 | 620 | 32701.6885 | 6755.3309 | 25946.3575 | 1316.5192 | 4305.1866 | 0.00099224 | 0.0010319 | 1.5862 | 19.25 | 1965 | 6.855e-05 | 2363 | 0 | 0 | 0.81805 | 2237 | 0
Central Valley | 832 | 0 | 0 | 3 | 1.7075 | 3 | 8.4784e-05 | 0.066431 | 4.9599 | 7.2085 | 16.1131 | 0.1245 | 1.1084 | 2.5183 | 1 | 5.6323e-06 | 0.00029025 | 0 | 0 | {C3619A95-0ECC-48A6-ABDA-B7A0B8AC9A76} | 162821702 | STANISLAUS 1702 | 37276 | 38.2391 | -120.3364 | STANISLAUS 170237276 | 370 | 878 | 53313.8764 | 18919.7774 | 34394.099 | 18919.7774 | 34394.099 | 0.00087076 | 0.00025435 |  | 1 | 1152 | 1.6897e-05 | 2364 | 0 | 0 | 11.7562 | 1290 | 0
North Coast | 7332 | 0 | 0 | 1 | 0.58532 | 1 | 8.4678e-05 | 0.066432 |  |  |  |  | 0.43805 | 1.2372 | 1 | 5.6253e-06 | 8.4678e-05 | 0 | 0 | {309A17EE-FDB5-41A4-BAF3-151B6AAED517} | 192291121 | CARLOTTA 1121 | 4045 | 40.5452 | -124.0718 | CARLOTTA 11214045 | 20 | 26 | 3926.1986 | 3179.9108 | 746.2877 | 0 | 64.6967 | 8.4678e-05 | 8.4678e-05 |  | 1 | 1955 | 5.6253e-06 | 2365 | 0 | 0 | 0 | 1359 | 0
Central Coast | 1588 | 466 | 1181.3899 | 1932 | 2051.5051 | 121 | 8.3906e-05 | 0.066432 | 1.3737 | 12.1088 | 124.4353 | 1.9706 | 0.15225 | 1.9821 | 0.92657 | 5.574e-06 | 0.0001083 | 0.2412 | 0.57586 | {27F30433-27B7-407B-8F57-C7D8C59F953A} | 83371106 | SARATOGA 1106 | LC24 | 37.2571 | -122.0139 | SARATOGA 1106LC24 | 337 | 438 | 39631.6916 | 18692.0591 | 20939.6325 | 12995.8406 | 13855.8345 | 0.013104 | 0.010153 | 2.5352 | 15.9669 | 1813 | 0.00067446 | 2366 | 0 | 0 | 8.0752 | 1927 | 0
Sierra | 6159 | 111 | 166.3191 | 368 | 275.1712 | 29 | 8.3875e-05 | 0.066432 | 3.4414 | 9.8504 | 24.9527 | 0.35271 | 1.9935 | 19.5535 | 1.0384 | 5.5719e-06 | 0.00017411 | 0.30163 | 0.60442 | {498BEDF6-2946-45C8-8A10-174F646330D4} | 152461102 | PLACER 1102 | circuit_breaker | 38.9009 | -121.0879 | PLACER 1102circuit_breaker | 46 | 40 | 6365.3783 | 3361.7302 | 3003.6481 | 2698.3238 | 3003.6481 | 0.0050491 | 0.0024324 | 1.4984 | 12.6897 | 1507 | 0.00016159 | 2367 | 0 | 0 | 1.6767 | 1419 | 0
North Valley | 8429 | 5 | 5.5419 | 20 | 21.9365 | 1 | 0.0001042 | 0.066432 |  |  |  |  | 0 | 7.1321 | 1 | 6.9219e-06 | 0.0001042 | 0.25 | 0.25263 | {A36BE560-E1CB-4559-8E7E-01132EBA1D0A} | 43081101 | BIG RIVER 1101 | 954 | 39.363 | -123.8129 | BIG RIVER 1101954 | 122 | 136 | 20965.4038 | 13095.0592 | 7870.3447 | 11972.4011 | 7353.557 | 0.0001042 | 0.0001042 | 1.1084 | 20 | 1837 | 6.9219e-06 | 2368 | 0 | 0 | 7.4393 | 1752 | 0
North Coast | 8429 | 1007 | 1571.9157 | 1229 | 1686.0588 | 108 | 8.591e-05 | 0.064587 | 3.5197 | 51.3736 | 478.358 | 3.5848 | 0.32432 | 5.7896 | 1.1152 | 5.5578e-06 | 0.00018842 | 0.81937 | 0.9323 | {A36BE560-E1CB-4559-8E7E-01132EBA1D0A} | 43081101 | BIG RIVER 1101 | 954 | 39.363 | -123.8129 | BIG RIVER 1101954 | 122 | 136 | 20965.4038 | 13095.0592 | 7870.3447 | 11972.4011 | 7353.557 | 0.020349 | 0.0092782 | 1.561 | 11.3796 | 1455 | 0.00060024 | 2368 | 0 | 0 | 7.4393 | 1591 | 0
Central Valley | 4968 | 2 | 2.7172 | 57 | 30.4244 | 12 | 9.0131e-05 | 0.060895 | 1.0802 | 0.50252 | 2.9416 | 0.013273 | 0.14381 | 2.6264 | 1.25 | 5.5456e-06 | 9.856e-05 | 0.035088 | 0.089309 | {B87C881C-26C5-430F-BDD9-C06CB7701154} | 162821702 | STANISLAUS 1702 | 1850 | 38.2415 | -120.3611 | STANISLAUS 17021850 | 451 | 928 | 57071.7401 | 21674.5076 | 35397.2324 | 21674.5076 | 35397.2324 | 0.0011827 | 0.0010816 | 1.3586 | 4.75 | 1858 | 6.6547e-05 | 2369 | 0 | 0 | 13.4679 | 1818 | 0
Central Coast | 8313 | 291 | 515.195 | 329 | 535.6573 | 14 | 8.2113e-05 | 0.066431 | 6.3851 | 41.7046 | 162.8304 | 1.1282 | 0.78698 | 11.9909 | 1.0028 | 5.4549e-06 | 0.00026889 | 0.8845 | 0.9618 | {4939E3FC-0C7B-45BF-A34E-F13CD4603449} | 82841102 | BIG BASIN 1102 | 6219 | 37.184 | -122.1408 | BIG BASIN 11026219 | 16 | 28 | 3479.2897 | 1442.8917 | 2036.3981 | 1442.8917 | 2036.3981 | 0.0037645 | 0.0011496 | 1.7704 | 23.5 | 1204 | 7.6368e-05 | 2370 | 0 | 0 | 0.89657 | 2073 | 0
North Coast | 6172 | 21 | 33.9745 | 28 | 37.3347 | 4 | 8.1809e-05 | 0.066432 | 3.5306 | 8.9051 | 22.987 | 0.11319 | 0.0022124 | 0.99082 | 1 | 5.4347e-06 | 0.00023633 | 0.75 | 0.91 | {DDA08885-FEC3-49A8-9C1B-A5CDAFE21444} | 42761104 | FORT BRAGG A 1104 | 65894 | 39.4364 | -123.7895 | FORT BRAGG A 110465894 | 41 | 58 | 5121.936 | 1933.4215 | 3188.5145 | 322.1994 | 395.4321 | 0.0009453 | 0.00032724 | 1.6178 | 7 | 1293 | 2.1739e-05 | 2371 | 0 | 0 | 0.20021 | 695 | 0
Central Coast | 1339 | 154 | 283.6519 | 687 | 582.403 | 32 | 8.1548e-05 | 0.066432 | 3.2968 | 4.4505 | 15.4034 | 0.096624 | 0.84251 | 4.3325 | 1.0019 | 5.4174e-06 | 0.0001732 | 0.22416 | 0.48704 | {CEB97A6E-057E-4617-8BF5-91D85F0FC1F8} | 83622103 | CAMP EVERS 2103 | 5402 | 37.0103 | -122.0341 | CAMP EVERS 21035402 | 204 | 392 | 27473.3577 | 10811.0731 | 16662.2846 | 3816.6305 | 2929.5374 | 0.0055424 | 0.0026095 | 1.8419 | 21.4688 | 1512 | 0.00017336 | 2372 | 0 | 0 | 2.3715 | 1473 | 0
North Coast | 7418 | 11 | 31.5815 | 38 | 43.2538 | 5 | 8.1096e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0.26504 | 0.37664 | 1 | 5.3873e-06 | 6.5113e-05 | 0.28947 | 0.73014 | {078E6937-4C7E-4DCA-8920-0F03CEE6AF5C} | 43351106 | LUCERNE 1106 | 2355 | 39.0393 | -122.7643 | LUCERNE 11062355 | 31 | 96 | 5053.5421 | 1676.4836 | 3377.0586 | 560.2517 | 817.0359 | 0.00032556 | 0.00040548 | 2.871 | 7.6 | 2091 | 2.6937e-05 | 2373 | 0 | 0 | 0.34812 | 280 | 0
North Coast | 1711 | 184 | 296.3565 | 249 | 325.8394 | 27 | 8.0399e-05 | 0.066432 | 2.737 | 21.527 | 104.116 | 0.59024 | 0.68084 | 4.8021 | 1.0097 | 5.3411e-06 | 0.00015661 | 0.73896 | 0.90952 | {DDD68DD3-36B2-4580-BE12-D96815D31D50} | 42841111 | GUALALA 1111 | 402866 | 38.7594 | -123.5129 | GUALALA 1111402866 | 27 | 15 | 3146.271 | 2560.4032 | 585.8677 | 2022.5208 | 585.8677 | 0.0042284 | 0.0021708 | 1.6106 | 9.2222 | 1559 | 0.00014421 | 2374 | 0 | 0 | 1.2567 | 138 | 0
North Coast | 1776 | 195 | 282.9636 | 348 | 325.1812 | 43 | 7.9665e-05 | 0.066432 | 2.6996 | 6.2209 | 38.4833 | 1.0271 | 4.6213 | 15.5532 | 0.98096 | 5.2922e-06 | 0.0001678 | 0.56034 | 0.87017 | {7E2F1938-FEBF-4ABD-86B8-56A7EC0C222F} | 43211101 | HARTLEY 1101 | 738 | 39.0621 | -122.9311 | HARTLEY 1101738 | 229 | 701 | 45344.7705 | 12990.0963 | 32354.6742 | 3766.2764 | 7619.9811 | 0.0072154 | 0.0034256 | 1.4511 | 8.093 | 1524 | 0.00022757 | 2375 | 0 | 0 | 2.3403 | 1914 | 0
North Coast | 361 | 37 | 55.2243 | 107 | 86.7479 | 9 | 7.9608e-05 | 0.066432 | 2.7774 | 25.7912 | 231.1542 | 1.0137 | 0.026057 | 0.67989 | 1 | 5.2885e-06 | 0.00012473 | 0.34579 | 0.63661 | {21ADCA93-F696-42D2-B9AB-0580CBDEB386} | 192021122 | ARCATA 1122 | 33060 | 40.8419 | -124.0626 | ARCATA 112233060 | 122 | 211 | 18720.6982 | 7913.5825 | 10807.1157 | 701.4158 | 1090.1638 | 0.0011226 | 0.00071647 | 1.4925 | 11.8889 | 1726 | 4.7597e-05 | 2376 | 0 | 0 | 0.43584 | 840 | 0
North Coast | 7979 | 241 | 417.3748 | 290 | 439.6093 | 28 | 7.8824e-05 | 0.066432 | 3.3426 | 27.4153 | 113.2948 | 0.51559 | 0.02323 | 2.5982 | 1 | 5.2364e-06 | 0.00015799 | 0.83103 | 0.94942 | {C5260397-7BFE-45E3-969A-B60D6BAD6CE0} | 42841112 | GUALALA 1112 | 4431 | 38.7872 | -123.5577 | GUALALA 11124431 | 27 | 41 | 5171.4033 | 2379.9343 | 2791.469 | 2212.4234 | 2755.6991 | 0.0044238 | 0.0022071 | 1.7318 | 10.3571 | 1552 | 0.00014662 | 2377 | 0 | 0 | 1.3747 | 1551 | 0
North Coast | 364 | 23 | 27.4776 | 61 | 43.5507 | 5 | 7.8817e-05 | 0.066432 | 7.4345 | 5.1007 | 15.7971 | 0.13787 | 0.97434 | 0.12133 | 1 | 5.236e-06 | 0.00024533 | 0.37705 | 0.63093 | {D98BCE06-B639-4635-9566-7FA7CFE5BC8F} | 42771114 | UKIAH 1114 | circuit_breaker | 39.1433 | -123.1915 | UKIAH 1114circuit_breaker | 194 | 356 | 27706.5225 | 13996.69 | 13709.8325 | 555.5725 | 402.0448 | 0.0012267 | 0.00039409 | 1.1947 | 12.2 | 1263 | 2.618e-05 | 2378 | 0 | 0 | 0.34522 | 2418 | 0
Central Coast | 4324 | 1169 | 2927.2915 | 1439 | 3085.1443 | 77 | 3.678e-05 | 0.16858 | 3.599 | 52.9546 | 326.3057 | 3.7263 | 0.13283 | 21.7331 | 1.0974 | 5.2257e-06 | 7.3226e-05 | 0.81237 | 0.94883 | {9B3F8B66-8E8D-4C3E-B30C-F806C7A06324} | 182941101 | OTTER 1101 | 440 | 36.4379 | -121.9198 | OTTER 1101440 | 183 | 309 | 34766.8649 | 17663.1455 | 17103.7194 | 9356.989 | 10535.8941 | 0.0056384 | 0.002832 | 2.5041 | 18.6883 | 2034 | 0.00040238 | 2379 | 0 | 0 | 5.8142 | 1162 | 0
North Coast | 7630 | 285 | 463.2831 | 355 | 497.481 | 28 | 7.8601e-05 | 0.066432 | 3.7933 | 21.2541 | 201.7608 | 1.3466 | 0.39215 | 2.8159 | 1.0002 | 5.2216e-06 | 0.00016291 | 0.80282 | 0.93126 | {B849FFAE-ED7D-4C30-A59F-EE2E39484950} | 43081101 | BIG RIVER 1101 | 5065 | 39.3644 | -123.7985 | BIG RIVER 11015065 | 35 | 38 | 6743.9921 | 3543.5774 | 3200.4147 | 3543.5774 | 3200.4147 | 0.0045614 | 0.0022008 | 1.6256 | 12.6786 | 1539 | 0.0001462 | 2380 | 0 | 0 | 2.2019 | 866 | 0
Central Coast | 308 | 18 | 44.9523 | 69 | 72.131 | 8 | 7.8282e-05 | 0.066432 | 5.7392 | 4.8856 | 10.9513 | 0.17985 | 1.1117 | 8.0926 | 1.0014 | 5.2004e-06 | 0.00023481 | 0.26087 | 0.6232 | {E84E756D-50CD-4E19-9CC3-E6F7306D45B8} | 83252102 | PAUL SWEET 2102 | circuit_breaker | 36.9923 | -121.9824 | PAUL SWEET 2102circuit_breaker | 167 | 465 | 29640.6139 | 9537.1446 | 20103.4694 | 590.0954 | 95.8621 | 0.0018785 | 0.00062626 | 2.4974 | 8.625 | 1298 | 4.1604e-05 | 2381 | 0 | 0 | 0.36667 | 2224 | 0
Central Coast | 8987 | 13 | 24.2512 | 24 | 29.9364 | 2 | 7.7873e-05 | 0.066432 | 7.1969 | 1.2232 | 11.8561 | 0.17066 | 0 | 0.10951 | 1 | 5.1733e-06 | 0.00068556 | 0.54167 | 0.81009 | {22D220C5-2768-4212-BADC-DEEFF16BE912} | 83622103 | CAMP EVERS 2103 | circuit_breaker | 37.0418 | -122.025 | CAMP EVERS 2103circuit_breaker | 16 | 4 | 392.8412 | 190.6576 | 202.1836 | 146.1912 | 202.1836 | 0.0013711 | 0.00015575 | 1.8655 | 12 | 578 | 1.0347e-05 | 2382 | 0 | 0 | 0.090839 | 1708 | 0
Bay Area | 4574 | 77 | 138.5759 | 227 | 231.3336 | 17 | 9.7635e-05 | 0.051548 | 3.7266 | 17.7161 | 91.5936 | 1.2108 | 0.37772 | 2.5554 | 1.9477 | 5.102e-06 | 0.00022886 | 0.33921 | 0.59903 | {E4DE7199-7E8D-4B24-BE88-94D626280805} | 14692102 | RESEARCH 2102 | 9746 | 37.8214 | -122.0047 | RESEARCH 21029746 | 80 | 124 | 11268.394 | 4518.0632 | 6750.3308 | 1130.0389 | 1684.7186 | 0.0038907 | 0.0016598 | 1.7997 | 13.3529 | 1314 | 8.6735e-05 | 2383 | 0 | 0 | 0.70217 | 1126 | 0
Bay Area | 1451 | 1071 | 2422.401 | 3039 | 3609.685 | 219 | 5.6348e-05 | 0.16829 | 1.9604 | 4.8321 | 16.8307 | 0.064487 | 0.31664 | 6.0255 | 1.2703 | 5.0631e-06 | 8.5677e-05 | 0.35242 | 0.67108 | {AC34AADC-41EC-4F75-A750-22A938BF80E6} | 14671101 | SOBRANTE 1101 | circuit_breaker | 37.9051 | -122.2077 | SOBRANTE 1101circuit_breaker | 443 | 936 | 66650.0216 | 24837.5413 | 41812.4804 | 22159.2029 | 36243.1072 | 0.018763 | 0.01234 | 2.2618 | 13.8767 | 1941 | 0.0011088 | 2384 | 0 | 0 | 13.7691 | 2087 | 0
Bay Area | 3285 | 51 | 68.0963 | 151 | 129.0262 | 18 | 7.5417e-05 | 0.066432 | 4.7047 | 19.0018 | 86.8367 | 0.55934 | 0.2264 | 2.4754 | 1.0002 | 5.0101e-06 | 0.0001641 | 0.33775 | 0.52777 | {99848A3D-3AE5-4D01-A9C7-8BD9676BEFEE} | 14662108 | TASSAJARA 2108 | 12712 | 37.8471 | -122.0327 | TASSAJARA 210812712 | 97 | 224 | 16097.1475 | 5358.1983 | 10738.9492 | 1348.3115 | 555.7853 | 0.0029538 | 0.0013575 | 1.3352 | 8.3889 | 1536 | 9.0181e-05 | 2385 | 0 | 0 | 0.8378 | 2859 | 0
Central Coast | 6149 | 39 | 63.7912 | 149 | 125.0207 | 15 | 7.5331e-05 | 0.066432 | 5.7533 | 4.8198 | 14.8163 | 0.14626 | 1.1867 | 1.4633 | 0.86667 | 5.0044e-06 | 0.00023942 | 0.26174 | 0.51025 | {7097C41D-4FD9-4503-BEF9-0B96E72F7C88} | 83692105 | ROB ROY 2105 | 71630 | 36.976 | -121.8947 | ROB ROY 210571630 | 52 | 222 | 14008.4418 | 2893.6341 | 11114.8077 | 1881.1605 | 5371.6035 | 0.0035912 | 0.00113 | 1.6357 | 9.9333 | 1280 | 7.5066e-05 | 2386 | 0 | 0 | 1.1689 | 2281 | 0
Sierra | 7769 | 1 | 1.3586 | 2 | 1.8143 | 2 | 7.5094e-05 | 0.066432 | 0.53537 | 2.0905 | 10.5366 | 0.010332 | 4.2699 | 18.1757 | 1 | 4.9886e-06 | 5.7497e-05 | 0.5 | 0.74881 | {D34CE8D2-4E63-4899-B49E-7C6D0FD502F0} | 152481103 | BRUNSWICK 1103 | 8918 | 39.2477 | -121.0255 | BRUNSWICK 11038918 | 63 | 71 | 7235.0576 | 3457.885 | 3777.1726 | 2321.7397 | 2865.1686 | 0.00011499 | 0.00015019 | 1.3586 | 1 | 2163 | 9.9772e-06 | 2387 | 0 | 0 | 1.4427 | 2685 | 0
Bay Area | 1182 | 2 | 2.2127 | 15 | 9.1101 | 1 | 7.3719e-05 | 0.066431 |  |  |  |  | 0.36504 | 3.1515 | 1 | 4.8973e-06 | 7.3719e-05 | 0.13333 | 0.24288 | {49549F40-A326-4458-963A-8F0223D6E156} | 43292103 | PUEBLO 2103 | 98394 | 38.3211 | -122.3305 | PUEBLO 210398394 | 92 | 146 | 10249.6767 | 3363.933 | 6885.7438 | 20.0123 | 0 | 7.3719e-05 | 7.3719e-05 | 1.1063 | 15 | 2029 | 4.8973e-06 | 2388 | 0 | 0 | 0.012435 | 2176 | 0
North Coast | 7309 | 1 | 1.6135 | 1 | 1.6135 | 1 | 7.3716e-05 | 0.066431 |  |  |  |  | 0 | 0.028097 | 1 | 4.897e-06 | 7.3716e-05 | 1 | 1 | {0A86DDE1-72D3-4AA4-946A-5E91F4735FDF} | 42631109 | PETALUMA C 1109 | 738866 | 38.2166 | -122.6308 | PETALUMA C 1109738866 | 57 | 95 | 10241.7174 | 4335.7412 | 5905.9762 | 2889.9768 | 3419.009 | 7.3716e-05 | 7.3716e-05 | 1.6135 | 1 | 2030 | 4.897e-06 | 2389 | 0 | 0 | 1.7957 | 938 | 0
Bay Area | 391 | 3 | 4.7307 | 4 | 5.1864 | 2 | 7.3491e-05 | 0.066432 | 0.31631 | 0.11247 | 0.2901 | 0.00018145 | 0 | 0 | 0 | 4.8821e-06 | 2.3487e-05 | 0.75 | 0.91213 | {2B644C8A-1232-4056-B6E3-B09CD0D7D415} | 14161104 | ROSSMOOR 1104 | circuit_breaker | 37.8652 | -122.0807 | ROSSMOOR 1104circuit_breaker | 360 | 984 | 60297.3811 | 17858.6714 | 42438.7097 | 0 | 77.9051 | 4.6975e-05 | 0.00014698 | 1.5769 | 2 | 2557 | 9.7642e-06 | 2390 | 0 | 0 | 0 | 2852 | 0
Central Coast | 429 | 434 | 914.6697 | 1447 | 1518.4447 | 96 | 7.3291e-05 | 0.066432 | 0.45825 | 0.93143 | 3.4741 | 0.010321 | 0.25611 | 2.5204 | 0.9796 | 4.8689e-06 | 5.2884e-05 | 0.29993 | 0.60237 | {AB3D61A8-2047-43B4-8648-838CA93AAC23} | 83371107 | SARATOGA 1107 | LC26 | 37.2495 | -122.0193 | SARATOGA 1107LC26 | 179 | 230 | 20415.1182 | 9086.0614 | 11329.0568 | 9086.0614 | 11329.0568 | 0.0050769 | 0.0070359 | 2.1075 | 15.0729 | 2211 | 0.00046741 | 2391 | 0 | 0 | 5.6458 | 488 | 0
North Coast | 524 | 28 | 39.5077 | 75 | 59.0267 | 15 | 7.3045e-05 | 0.067279 | 12.7676 | 13.2678 | 40.0848 | 2.3883 | 0.90074 | 2.4138 | 1 | 4.8617e-06 | 0.00065282 | 0.37333 | 0.66932 | {F73918F2-BDFA-403D-8839-D569F0C45575} | 43361104 | HIGHLANDS 1104 | 39458 | 38.9376 | -122.628 | HIGHLANDS 110439458 | 157 | 456 | 29741.7477 | 8594.1592 | 21147.5885 | 1626.6223 | 2480.402 | 0.0097923 | 0.0010957 | 1.411 | 5 | 614 | 7.2926e-05 | 2392 | 0 | 0 | 1.0107 | 668 | 0
Central Coast | 2769 | 269 | 389.6621 | 1126 | 883.5749 | 106 | 4.2337e-05 | 0.12366 | 0.83222 | 15.6279 | 59.1989 | 0.21806 | 1.0943 | 20.4538 | 1.0367 | 4.7894e-06 | 4.2173e-05 | 0.2389 | 0.44101 | {7AD08992-20DE-491C-B310-C51F11D11659} | 83432101 | HICKS 2101 | XR250 | 37.2022 | -121.8329 | HICKS 2101XR250 | 325 | 474 | 47264.8254 | 21684.167 | 25580.6584 | 12241.6477 | 14826.2195 | 0.0044703 | 0.0044877 | 1.4486 | 10.6226 | 2305 | 0.00050767 | 2393 | 0 | 0 | 7.6066 | 2721 | 0
North Coast | 2728 | 84 | 207.9531 | 132 | 231.6426 | 7 | 7.2036e-05 | 0.066432 | 4.5081 | 16.6287 | 47.2445 | 0.75226 | 0.24905 | 2.9371 | 1.0009 | 4.7855e-06 | 0.00033603 | 0.63636 | 0.89773 | {68D3E51B-D82F-468F-8693-722B02390473} | 192251102 | RIO DELL 1102 | circuit_breaker | 40.4954 | -124.0995 | RIO DELL 1102circuit_breaker | 253 | 870 | 34873.0283 | 11413.6327 | 23459.3956 | 655.8803 | 2252.3764 | 0.0023522 | 0.00050425 | 2.4756 | 18.8571 | 1041 | 3.3498e-05 | 2394 | 0 | 0 | 0.40754 | 1536 | 0
North Coast | 5345 | 515 | 846.8463 | 601 | 886.3444 | 69 | 7.0754e-05 | 0.066432 | 4.5196 | 42.5211 | 251.0266 | 2.6816 | 0.75519 | 8.6742 | 1.0067 | 4.7003e-06 | 0.00018781 | 0.85691 | 0.95544 | {73132ABD-89F1-46DF-ADF4-0148C2A7C9B0} | 42841111 | GUALALA 1111 | circuit_breaker | 38.7862 | -123.5219 | GUALALA 1111circuit_breaker | 92 | 76 | 9335.4727 | 6218.5195 | 3116.9531 | 5963.2451 | 3116.9531 | 0.012959 | 0.004882 | 1.6444 | 8.7101 | 1458 | 0.00032432 | 2395 | 0 | 0 | 3.7054 | 202 | 0
North Coast | 625 | 108 | 148.0746 | 156 | 174.9041 | 23 | 7.0357e-05 | 0.06643 | 1.3037 | 42.1186 | 141.1308 | 0.33229 | 1.7497 | 22.5185 | 1.0127 | 4.6738e-06 | 7.3585e-05 | 0.69231 | 0.8466 | {98861C56-51D3-43DB-9804-E460E1D0C1F4} | 43071101 | DUNBAR 1101 | 160 | 38.436 | -122.5796 | DUNBAR 1101160 | 151 | 295 | 26232.2292 | 10698.4424 | 15533.7867 | 3768.8878 | 1626.8369 | 0.0016924 | 0.0016182 | 1.3711 | 6.7826 | 2032 | 0.0001075 | 2396 | 0 | 0 | 2.3419 | 1455 | 0
Central Coast | 751 | 170 | 320.6186 | 853 | 735.876 | 65 | 7.0334e-05 | 0.066432 | 4.7106 | 4.3815 | 12.9986 | 0.24543 | 0.34731 | 1.7445 | 0.87692 | 4.6724e-06 | 0.00025593 | 0.1993 | 0.4357 | {179FE519-944E-4835-9C33-84ABCACF7D82} | 82021108 | LOS GATOS 1108 | LB86 | 37.2261 | -121.9826 | LOS GATOS 1108LB86 | 209 | 650 | 35376.9904 | 8579.3653 | 26797.6251 | 7195.675 | 19015.1766 | 0.016635 | 0.0045717 | 1.886 | 13.1231 | 1236 | 0.00030371 | 2397 | 0 | 0 | 4.4712 | 1029 | 0
Bay Area | 4900 | 25 | 55.6608 | 262 | 200.8817 | 21 | 3.0515e-05 | 0.12093 | 1.7067 | 1.5877 | 3.4207 | 0.014406 | 0.31384 | 14.6793 | 1.0175 | 4.6178e-06 | 4.15e-05 | 0.09542 | 0.27708 | {65654596-3A5A-40BB-834A-0960D61641E3} | 12501112 | EL CERRITO G 1112 | BR178 | 37.9467 | -122.3193 | EL CERRITO G 1112BR178 | 235 | 1410 | 71456.8666 | 12825.8849 | 58630.9818 | 2290.0818 | 8059.2112 | 0.00087149 | 0.00064082 | 2.2264 | 12.4762 | 2316 | 9.6974e-05 | 2398 | 0 | 0 | 1.423 | 2319 | 0
Central Valley | 5281 | 26 | 35.3232 | 309 | 161.1528 | 42 | 6.9457e-05 | 0.066432 | 0.57212 | 11.8956 | 24.2239 | 0.033204 | 0.1899 | 5.994 | 1.0008 | 4.6142e-06 | 6.1069e-05 | 0.084142 | 0.21919 | {34FFF0A8-2671-4464-AC38-1EA19A472934} | 163201102 | WEST POINT 1102 | 5357 | 38.2816 | -120.5422 | WEST POINT 11025357 | 50 | 67 | 7747.8131 | 5289.0317 | 2458.7814 | 5289.0317 | 2458.7814 | 0.0025649 | 0.0029172 | 1.3586 | 7.3571 | 2123 | 0.0001938 | 2399 | 0 | 0 | 3.2865 | 2102 | 0
Bay Area | 8436 | 0 | 0 | 2 | 0.91147 | 1 | 6.9447e-05 | 0.066432 | 4.0831 | 2.2834 | 17.4666 | 0.076626 | 0.37389 | 0.29049 | 1 | 4.6135e-06 | 0.00028356 | 0 | 0 | {4CA94395-6849-4C23-B9A9-BA346C47AF36} | 14161101 | ROSSMOOR 1101 | 81770 | 37.9095 | -122.0997 | ROSSMOOR 110181770 | 43 | 121 | 7362.2695 | 2254.8682 | 5107.4013 | 0 | 308.2338 | 0.00028356 | 6.9447e-05 |  | 2 | 1164 | 4.6135e-06 | 2400 | 0 | 0 | 0 | 2258 | 0
Central Coast | 3149 | 136 | 262.2137 | 572 | 516.1231 | 41 | 6.8633e-05 | 0.066432 | 7.6348 | 5.9459 | 19.3403 | 0.4702 | 0.061245 | 0.082182 | 0.36585 | 4.5594e-06 | 0.00027161 | 0.23776 | 0.50804 | {FFC04C14-5557-4FC3-9795-3587569ECB50} | 83692105 | ROB ROY 2105 | 12474 | 36.9713 | -121.8735 | ROB ROY 210512474 | 229 | 605 | 41838.1603 | 13639.2736 | 28198.8867 | 4762.2826 | 12450.4122 | 0.011136 | 0.002814 | 1.928 | 13.9512 | 1200 | 0.00018694 | 2401 | 0 | 0 | 2.9591 | 633 | 0
North Coast | 5241 | 0 | 0 | 1 | 0.45574 | 1 | 6.8599e-05 | 0.066431 | 2.6196 | 49.0659 | 317.9757 | 7.381 | 1.294e-11 | 0.022124 | 1 | 4.557e-06 | 0.0001797 | 0 | 0 | {B9E22F01-648D-4F6F-B1E0-311BE99AC492} | 42631108 | PETALUMA C 1108 | 600 | 38.2425 | -122.6796 | PETALUMA C 1108600 | 249 | 380 | 38359.4799 | 13922.7445 | 24436.7354 | 8142.768 | 12827.0764 | 0.0001797 | 6.8599e-05 |  | 1 | 1486 | 4.557e-06 | 2402 | 0 | 0 | 5.0597 | 1984 | 0
North Coast | 9360 | 7 | 8.8557 | 17 | 14.2727 | 4 | 6.7783e-05 | 0.066431 | 0 | 0 | 0 | 0 | 3.8473 | 4.7431 | 1 | 4.5029e-06 | 4.9533e-05 | 0.41176 | 0.62047 | {5C89CE05-2636-4AC9-BAFC-5707AC921B94} | 43501103 |  | 5060 | 38.5618 | -122.8169 | 5060 | 31 | 17 | 1766.5578 | 1112.8921 | 653.6657 | 477.3134 | 359.0567 | 0.00019813 | 0.00027113 | 1.2651 | 4.25 | 2232 | 1.8011e-05 | 2403 | 0 | 0 | 0.29659 | 37 | 0
Sierra | 9013 | 7 | 13.646 | 31 | 21.6597 | 9 | 6.7675e-05 | 0.066432 | 0.48857 | 13.3083 | 53.2717 | 0.03376 | 0.2028 | 10.532 | 1.0162 | 4.4957e-06 | 4.3352e-05 | 0.22581 | 0.63002 | {3EEFA179-0D60-4808-A6C9-A2D8F6C0C66D} | 153741101 | DOBBINS 1101 | circuit_breaker | 39.3397 | -121.1952 | DOBBINS 1101circuit_breaker | 21 | 14 | 1813.0501 | 1079.0936 | 733.9565 | 1079.0936 | 733.9565 | 0.00039017 | 0.00060907 | 1.9494 | 3.4444 | 2298 | 4.0462e-05 | 2404 | 0 | 0 | 0.67052 | 162 | 0
Central Coast | 3917 | 162 | 332.7948 | 617 | 579.1125 | 67 | 3.8763e-05 | 0.16234 | 1.2595 | 38.2965 | 129.6204 | 1.093 | 1.37 | 29.9917 | 1.2221 | 4.4939e-06 | 3.7478e-05 | 0.26256 | 0.57466 | {6ADA1603-F38C-494F-A594-401AD43EFE67} | 182371111 | LAURELES 1111 | circuit_breaker | 36.4777 | -121.7272 | LAURELES 1111circuit_breaker | 131 | 223 | 30691.2071 | 13157.523 | 17533.6841 | 11332.9679 | 7370.0132 | 0.002511 | 0.0025971 | 2.0543 | 9.209 | 2370 | 0.00030109 | 2405 | 0 | 0 | 7.042 | 1982 | 0
North Coast | 395 | 163 | 299.7803 | 500 | 401.4284 | 82 | 6.738e-05 | 0.066432 | 1.3031 | 5.2862 | 32.7438 | 0.14243 | 2.1396 | 10.0636 | 1.0597 | 4.4762e-06 | 7.8255e-05 | 0.326 | 0.74678 | {72AB9BE6-2DAD-47AD-B1E1-28EC23582566} | 43191102 | REDBUD 1102 | 922 | 38.999 | -122.6721 | REDBUD 1102922 | 128 | 364 | 27664.3751 | 12463.6383 | 15200.7368 | 12117.314 | 11870.1596 | 0.0064169 | 0.0055252 | 1.8391 | 6.0976 | 1996 | 0.00036705 | 2406 | 0 | 0 | 7.5293 | 2378 | 0
Bay Area | 1360 | 35 | 90.1565 | 48 | 95.8245 | 15 | 6.6025e-05 | 0.068127 | 0.29561 | 2.9596 | 28.8024 | 0.18061 | 0.54499 | 1.0665 | 1 | 4.4623e-06 | 3.4705e-05 | 0.72917 | 0.94085 | {F8848040-3D71-4E27-A6C9-8113D150CFEE} | 22811103 | PACIFICA 1103 | 11153 | 37.5845 | -122.4797 | PACIFICA 110311153 | 216 | 1806 | 98696.4674 | 14450.2027 | 84246.2647 | 1394.6966 | 6678.3188 | 0.00052058 | 0.00099037 | 2.5759 | 3.2 | 2403 | 6.6935e-05 | 2407 | 0 | 0 | 0.86662 | 600 | 0
North Valley | 9841 | 0 | 0 | 61 | 37.8374 | 6 | 4.7813e-06 | 0.93962 | 0.036556 | 99.5836 | 811.123 | 0.050752 | 2.2942 | 140.2779 | 1.1394 | 4.4599e-06 | 2.4083e-06 | 0 | 0 | {5CFCF023-4A49-452A-9B13-3F245544233B} | 103301101 | BOGARD 1101 | circuit_breaker | 40.588 | -121.0914 | BOGARD 1101circuit_breaker | 12 | 5 | 955.3189 | 830.5012 | 124.8177 | 830.5012 | 124.8177 | 1.445e-05 | 2.8688e-05 |  | 10.1667 | 2870 | 2.6759e-05 | 2408 | 0 | 0 | 0.51605 | 2096 | 0
North Coast | 8330 | 5 | 6.4084 | 15 | 12.7339 | 3 | 0.00010518 | 0.044287 | [6 empty] | 2.3333 | 4.4034e-06 | 0.00010518 | 0.33333 | 0.50326 | {18B04DCD-9DDD-4C1C-AC8D-731B4880D7B2} | 43302103 | MONROE 2103 | 92868 | 38.4799 | -122.7328 | MONROE 210392868 | 75 | 46 | 4101.8281 | 1827.1241 | 2274.7039 | 437.4753 | 234.8764 | 0.00031555 | 0.00031555 | 1.2817 | 5 | 1833 | 1.321e-05 | 2409 | 0 | 0 | 0.27183 | 631 | 0
Bay Area | 6675 | 17 | 55.118 | 22 | 57.5668 | 7 | 6.622e-05 | 0.066432 | 0.04387 | 0.21522 | 0.74517 | 0.0022925 | 0.92509 | 1.0574 | 1.0009 | 4.3991e-06 | 1.1632e-05 | 0.77273 | 0.95746 | {0C9E66AB-FF7E-4958-AED9-234BEE09CC6F} | 24101101 | HALF MOON BAY 1101 | 48868 | 37.5034 | -122.4688 | HALF MOON BAY 110148868 | 88 | 422 | 16122.918 | 4759.8895 | 11363.0285 | 1128.5857 | 2609.6917 | 8.1424e-05 | 0.00046354 | 3.2422 | 3.1429 | 2768 | 3.0794e-05 | 2410 | 0 | 0 | 0.70127 | 2876 | 0
Bay Area | 791 | 94 | 166.3701 | 295 | 284.4123 | 22 | 6.7685e-05 | 0.064568 | 3.8093 | 32.7182 | 156.4532 | 1.7479 | 0.22212 | 1.8533 | 1.1868 | 4.3962e-06 | 0.00019391 | 0.31864 | 0.58496 | {17B0EA25-D73F-4786-903D-45184AAF8053} | 14692102 | RESEARCH 2102 | 63274 | 37.8151 | -122 | RESEARCH 210263274 | 399 | 997 | 59074.1013 | 18111.0729 | 40963.0285 | 2064.5249 | 3394.4584 | 0.0042661 | 0.0014891 | 1.7699 | 13.4091 | 1432 | 9.6717e-05 | 2411 | 0 | 0 | 1.2828 | 2580 | 0
North Coast | 6333 | 1 | 0.97408 | 4 | 2.3413 | 3 | 6.614e-05 | 0.066432 | 0.040725 | 0.22239 | 1.1176 | 4.5515e-05 | 0.04646 | 1.3131 | 1 | 4.3938e-06 | 4.0038e-05 | 0.25 | 0.41604 | {D2E66D36-59AC-4BEC-BEE9-31C660B6B4ED} | 42851121 | FORT ROSS 1121 | 134 | 38.5588 | -123.2702 | FORT ROSS 1121134 | 162 | 98 | 20594.695 | 12995.1583 | 7599.5367 | 12414.5774 | 7199.4291 | 0.00012011 | 0.00019842 | 0.97408 | 1.3333 | 2340 | 1.3181e-05 | 2412 | 0 | 0 | 7.7141 | 2029 | 0
Bay Area | 7824 | 3 | 5.9209 | 4 | 6.3766 | 1 | 6.5625e-05 | 0.066432 |  |  |  |  | 11.7456 | 27.5429 | 1.0553 | 4.3596e-06 | 6.5625e-05 | 0.75 | 0.92853 | {37FBA5E9-EB7C-4A63-A4B5-288CF8FB512F} | 14161107 | ROSSMOOR 1107 | 7311 | 37.8753 | -122.0573 | ROSSMOOR 11077311 | 40 | 85 | 5389.1068 | 1914.4116 | 3474.6952 | 0 | 137.1155 | 6.5625e-05 | 6.5625e-05 | 1.9736 | 4 | 2084 | 4.3596e-06 | 2413 | 0 | 0 | 0 | 2743 | 0
North Coast | 9727 | 17 | 28.7993 | 42 | 42.5251 | 3 | 6.55e-05 | 0.066431 | 6.2941 | 4.9237 | 16.8386 | 0.11407 | 0.0022124 | 0.10376 | 1 | 4.3513e-06 | 0.00024021 | 0.40476 | 0.67723 | {3F69DD3E-C46A-485A-8A4E-8252A760746F} | 42811113 | MONTE RIO 1113 | 5024 | 38.4955 | -123.0075 | MONTE RIO 11135024 | 7 | 3 | 668.1635 | 545.8664 | 122.2971 | 545.8664 | 122.2971 | 0.00072063 | 0.0001965 | 1.6941 | 14 | 1277 | 1.3054e-05 | 2414 | 0 | 0 | 0.33919 | 1943 | 0
Central Coast | 7788 | 1 | 2.9829 | 29 | 29.7686 | 1 | 6.6728e-05 | 0.066431 |  |  |  |  | 0.11726 | 0.36128 | 1 | 4.4328e-06 | 6.6728e-05 | 0.034483 | 0.1002 | {F439C87D-AAE9-43A5-B8D6-BA1AB4C5C362} | 24101103 | HALF MOON BAY 1103 | 8898 | 37.3135 | -122.2756 | HALF MOON BAY 11038898 | 17 | 31 | 2159.5164 | 1026.3244 | 1133.192 | 1026.3244 | 1133.192 | 6.6728e-05 | 6.6728e-05 | 2.9829 | 29 | 2080 | 4.4328e-06 | 2415 | 0 | 0 | 0.63773 | 397 | 0
Bay Area | 7788 | 76 | 114.5413 | 182 | 169.5649 | 8 | 6.5317e-05 | 0.066431 | 0.23513 | 2.2441 | 9.9999 | 0.0089936 | 0.11062 | 0.9865 | 1 | 4.3391e-06 | 3.3624e-05 | 0.41758 | 0.6755 | {F439C87D-AAE9-43A5-B8D6-BA1AB4C5C362} | 24101103 | HALF MOON BAY 1103 | 8898 | 37.3135 | -122.2756 | HALF MOON BAY 11038898 | 17 | 31 | 2159.5164 | 1026.3244 | 1133.192 | 1026.3244 | 1133.192 | 0.00026899 | 0.00052253 | 1.5071 | 22.75 | 2419 | 3.4713e-05 | 2415 | 0 | 0 | 0.63773 | 2260 | 0
Central Coast | 2056 | 71 | 168.4734 | 244 | 259.0832 | 17 | 6.5222e-05 | 0.066432 | 2.5032 | 1.0804 | 4.164 | 0.031371 | 0.00091098 | 0.039081 | 0.41176 | 4.3328e-06 | 9.9244e-05 | 0.29098 | 0.65027 | {ABFDD865-4FD2-4A37-B95C-CF3A9E9EFA30} | 83692105 | ROB ROY 2105 | 12586 | 36.9733 | -121.8879 | ROB ROY 210512586 | 189 | 971 | 56977.54 | 10478.2508 | 46499.2892 | 2805.9717 | 10973.9588 | 0.0016871 | 0.0011088 | 2.3729 | 14.3529 | 1853 | 7.3658e-05 | 2416 | 0 | 0 | 1.7435 | 1614 | 0
Central Coast | 260 | 240 | 583.694 | 660 | 824.0329 | 46 | 6.4947e-05 | 0.066432 | 0.35916 | 0.54166 | 1.2589 | 0.0033497 | 0 | 0.0043767 | 0.13043 | 4.3146e-06 | 4.8116e-05 | 0.36364 | 0.70834 | {DAB08854-D3B6-4F8F-8E8C-51427B3E01B1} | 83371104 | SARATOGA 1104 | 13314 | 37.2626 | -121.9924 | SARATOGA 110413314 | 420 | 545 | 41607.4614 | 18413.6994 | 23193.7619 | 4930.3505 | 4954.9306 | 0.0022133 | 0.0029876 | 2.4321 | 14.3478 | 2249 | 0.00019847 | 2417 | 0 | 0 | 3.0636 | 2615 | 0
Bay Area | 8777 | 0 | 0 | 9 | 3.2327 | 2 | 6.4632e-05 | 0.066432 | 0.00016744 | 0.22239 | 0.0010858 | 1.5828e-10 | 0 | 0.66681 | 1 | 4.2937e-06 | 1.5367e-08 | 0 | 0 | {1B6353F3-7152-4A32-A40C-9970C5A62BA9} | 24240402 | WATERSHED 0402 | circuit_breaker | 37.4874 | -122.3103 | WATERSHED 0402circuit_breaker | 15 | 7 | 1910.473 | 1752.4587 | 158.0143 | 0 | 23.5094 | 3.0733e-08 | 0.00012926 |  | 4.5 | 2885 | 8.5873e-06 | 2418 | 0 | 0 | 0 | 1786 | 0
North Coast | 4616 | 12 | 26.7058 | 21 | 30.4522 | 9 | 6.4357e-05 | 0.066431 | 0.18186 | 22.3342 | 68.2808 | 0.038512 | 0.053343 | 0.81497 | 1 | 4.2754e-06 | 4.5704e-05 | 0.57143 | 0.87698 | {762F2724-D687-4C14-8C14-CCCD968810AC} | 42631109 | PETALUMA C 1109 | 48000 | 38.2262 | -122.6131 | PETALUMA C 110948000 | 167 | 126 | 30741.3375 | 21371.2273 | 9370.1102 | 15185.5394 | 7055.7401 | 0.00041134 | 0.00057922 | 2.2255 | 2.3333 | 2277 | 3.8478e-05 | 2419 | 0 | 0 | 9.4359 | 1672 | 0
Central Coast | 3894 | 134 | 289.5717 | 433 | 458.2935 | 37 | 6.4226e-05 | 0.066432 | 1.6966 | 3.1458 | 10.2969 | 0.031112 | 0.50634 | 2.6763 | 0.94864 | 4.2667e-06 | 9.1257e-05 | 0.30947 | 0.63185 | {12D75819-A6BC-4E85-B057-219FF075B3A4} | 83692105 | ROB ROY 2105 | 12584 | 36.9707 | -121.8718 | ROB ROY 210512584 | 292 | 694 | 49439.7401 | 19455.512 | 29984.2281 | 5377.6554 | 3624.1185 | 0.0033765 | 0.0023764 | 2.161 | 11.7027 | 1900 | 0.00015787 | 2420 | 0 | 0 | 3.3415 | 1766 | 0
Central Coast | 6777 | 0 | 0 | 15 | 6.708 | 4 | 5.0242e-05 | 0.079148 | 0.22938 | 1.5375 | 7.048 | 0.14779 | 2.9712 | 10.842 | 1.0011 | 4.2654e-06 | 3.6186e-05 | 0 | 0 | {DA2C7B5E-6C7B-401F-B35E-CA8BB5D3B738} | 182541102 | ATASCADERO 1102 | A26 | 35.4647 | -120.6506 | ATASCADERO 1102A26 | 228 | 363 | 31386.7503 | 11312.8173 | 20073.9331 | 1034.6974 | 2502.23 | 0.00014475 | 0.00020097 |  | 3.75 | 2385 | 1.7062e-05 | 2421 | 0 | 0 | 0.64293 | 2571 | 0
North Coast | 5237 | 74 | 134.0013 | 91 | 142.1444 | 51 | 5.9408e-05 | 0.071916 | 0.97065 | 108.3156 | 788.1751 | 1.8975 | 0.5809 | 26.6709 | 1.0075 | 4.259e-06 | 6.009e-05 | 0.81319 | 0.94271 | {4E55E7CE-52B3-47DC-8A51-FD5ED3230884} | 42861101 | ANNAPOLIS 1101 | 554 | 38.711 | -123.3384 | ANNAPOLIS 1101554 | 227 | 145 | 50761.5079 | 43657.3063 | 7104.2016 | 43657.3063 | 7104.2016 | 0.0030646 | 0.0030298 | 1.8108 | 1.7843 | 2141 | 0.00021721 | 2422 | 0 | 0 | 27.1274 | 1375 | 0
Central Coast | 4682 | 8 | 18.5733 | 19 | 24.4538 | 6 | 6.3679e-05 | 0.066432 | 0.0026775 | 0.078665 | 0.38113 | 6.6078e-05 | 0.027655 | 1.0085 | 1 | 4.2303e-06 | 1.9383e-05 | 0.42105 | 0.75952 | {65F8EE18-25DB-48C0-8EE8-63D74E373DA3} | 83692105 | ROB ROY 2105 | circuit_breaker | 36.9792 | -121.867 | ROB ROY 2105circuit_breaker | 49 | 31 | 3877.1626 | 2115.1186 | 1762.044 | 778.4452 | 784.63 | 0.0001163 | 0.00038208 | 2.3217 | 3.1667 | 2622 | 2.5382e-05 | 2423 | 0 | 0 | 0.4837 | 874 | 0
Central Coast | 4825 | 8 | 11.7749 | 31 | 25.1807 | 3 | 6.341e-05 | 0.066432 | 1.7077 | 13.4238 | 41.5734 | 0.077315 | 1.0383 | 25.1912 | 1.0752 | 4.2125e-06 | 8.0918e-05 | 0.25806 | 0.46762 | {F743E5C1-4CE6-4D65-B6FE-D0B8E82E2CBD} | 83252102 | PAUL SWEET 2102 | 12850 | 36.9887 | -122.0069 | PAUL SWEET 210212850 | 118 | 211 | 15001.2443 | 6534.2586 | 8466.9857 | 1087.1798 | 174.004 | 0.00024275 | 0.00019023 | 1.4719 | 10.3333 | 1975 | 1.2637e-05 | 2424 | 0 | 0 | 0.67554 | 1658 | 0
Bay Area | 5659 | 719 | 1942.1552 | 1802 | 2545.764 | 149 | 6.4119e-05 | 0.064808 | 5.7641 | 2.8562 | 8.6949 | 0.1086 | 0.60428 | 2.0043 | 1.0823 | 4.2078e-06 | 0.00019109 | 0.399 | 0.7629 | {CDF93CEC-24EF-42DF-9C21-4B412C432F20} | 12101102 | OAKLAND K 1102 | CR014 | 37.8517 | -122.2053 | OAKLAND K 1102CR014 | 286 | 1513 | 85879.464 | 16905.4788 | 68973.9851 | 16905.4788 | 68973.9851 | 0.028472 | 0.0095537 | 2.7012 | 12.094 | 1448 | 0.00062696 | 2425 | 0 | 0 | 10.5046 | 880 | 0
Sierra | 6973 | 5 | 9.5791 | 6 | 10.0348 | 1 | 6.3038e-05 | 0.066432 |  |  |  |  | 0 | 0.04469 | 1 | 4.1877e-06 | 6.3038e-05 | 0.83333 | 0.95458 | {6458AB58-DA5E-4D0A-95E1-69BD6C7E0EA2} | 153612106 | CLARKSVILLE 2106 | 19642 | 38.6832 | -121.0684 | CLARKSVILLE 210619642 | 53 | 2 | 2595.0664 | 2579.2739 | 15.7925 | 618.1955 | 0 | 6.3038e-05 | 6.3038e-05 | 1.9158 | 6 | 2112 | 4.1877e-06 | 2426 | 0 | 0 | 0.38413 | 152 | 0
Central Coast | 2181 | 144 | 299.9388 | 589 | 554.7476 | 47 | 6.2869e-05 | 0.066432 | 5.0327 | 6.7405 | 27.7329 | 0.29476 | 0.56284 | 1.6932 | 0.97872 | 4.1765e-06 | 0.00020886 | 0.24448 | 0.54068 | {8C8A8C09-E52E-42BB-8F77-24A43F9E99B3} | 83252109 | PAUL SWEET 2109 | circuit_breaker | 36.9922 | -121.982 | PAUL SWEET 2109circuit_breaker | 431 | 1083 | 70567.0846 | 20163.9647 | 50403.1199 | 4486.5579 | 9738.533 | 0.0098166 | 0.0029549 | 2.0829 | 12.5319 | 1382 | 0.0001963 | 2427 | 0 | 0 | 2.7878 | 2796 | 0
North Coast | 839 | 4 | 11.3946 | 14 | 17.2962 | 6 | 6.2865e-05 | 0.06643 | 0.0023987 | 0.0072783 | 0.024191 | 1.7731e-06 | 0.65339 | 2.019 | 1 | 4.1761e-06 | 4.7567e-05 | 0.28571 | 0.65879 | {A2A06826-B5AC-4037-94EC-F135DC826294} | 43321102 | RINCON 1102 | 644 | 38.4691 | -122.6669 | RINCON 1102644 | 348 | 821 | 54056.4855 | 16240.3737 | 37816.1118 | 652.5483 | 1279.2397 | 0.0002854 | 0.00037719 | 2.8486 | 2.3333 | 2254 | 2.5057e-05 | 2428 | 0 | 0 | 0.40547 | 2252 | 0
Bay Area | 5223 | 13 | 43.2584 | 15 | 44.3939 | 3 | 6.2794e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0.29056 | 0.014971 | 1 | 4.1715e-06 | 4.9389e-05 | 0.86667 | 0.97442 | {0685C5F8-0970-41C6-89BD-EFB0337B96FB} | 22811101 | PACIFICA 1101 | circuit_breaker | 37.5947 | -122.4889 | PACIFICA 1101circuit_breaker | 63 | 263 | 17964.1419 | 4340.9857 | 13623.1562 | 222.8126 | 779.173 | 0.00014817 | 0.00018838 | 3.3276 | 5 | 2234 | 1.2515e-05 | 2429 | 0 | 0 | 0.13845 | 2682 | 0
Sierra | 8784 | 18 | 29.5168 | 47 | 38.2726 | 6 | 6.2751e-05 | 0.066432 | 15.36 | 19.5597 | 56.0737 | 1.1547 | 1.604 | 6.5147 | 1 | 4.1687e-06 | 0.00058324 | 0.38298 | 0.77122 | {901652B5-3616-44F2-8390-6A226575133C} | 152701108 | BELL 1108 | 80680 | 38.9639 | -121.105 | BELL 110880680 | 53 | 55 | 5735.4226 | 2866.5185 | 2868.9041 | 685.5234 | 941.1063 | 0.0034994 | 0.00037651 | 1.6398 | 7.8333 | 691 | 2.5012e-05 | 2430 | 0 | 0 | 0.42596 | 1243 | 0
Central Coast | 7508 | 211 | 354.4562 | 1029 | 859.1918 | 93 | 6.2701e-05 | 0.066431 | 1.1656 | 7.2996 | 59.5261 | 0.56443 | 0.63588 | 7.6273 | 1.0145 | 4.1653e-06 | 7.2355e-05 | 0.20505 | 0.41255 | {D03187F3-5053-4E30-B164-D057F0065569} | 82021106 | LOS GATOS 1106 | circuit_breaker | 37.2262 | -121.9774 | LOS GATOS 1106circuit_breaker | 166 | 182 | 20904.047 | 12300.8206 | 8603.2264 | 10732.6188 | 7819.5435 | 0.006729 | 0.0058312 | 1.6799 | 11.0645 | 2041 | 0.00038737 | 2431 | 0 | 0 | 6.6689 | 2325 | 0
Bay Area | 946 | 88 | 214.9035 | 244 | 298.5104 | 35 | 6.4623e-05 | 0.064533 | 0.12835 | 0.18921 | 0.19038 | 0.001789 | 0.68148 | 1.3515 | 0.92099 | 4.1621e-06 | 3.9941e-05 | 0.36066 | 0.71992 | {BFF521B9-A860-4F51-B554-94546E79EB8D} | 42011109 | SAN RAFAEL 1109 | 91742 | 37.9747 | -122.5184 | SAN RAFAEL 110991742 | 268 | 964 | 57500.6984 | 13838.4275 | 43662.2709 | 6806.4298 | 22511.785 | 0.0013979 | 0.0022618 | 2.4421 | 6.9714 | 2343 | 0.00014567 | 2432 | 0 | 0 | 4.2293 | 2127 | 0
Central Coast | 4391 | 1 | 1.3586 | 3 | 2.2701 | 2 | 6.4534e-06 | 0.70859 | 0 | 0.66718 | 2.0108 | 0 | 0.96903 | 108.1924 | 0.56637 | 4.1381e-06 | 2.8882e-06 | 0.33333 | 0.59848 | {36177CF1-DF55-4FEE-893C-1AD0F53C4183} | 182052101 | SOLEDAD 2101 | 7056 | 36.4675 | -121.391 | SOLEDAD 21017056 | 198 | 174 | 52101.1958 | 44962.8575 | 7138.3383 | 6257.9858 | 2347.6948 | 5.7764e-06 | 1.2907e-05 | 1.3586 | 1.5 | 2866 | 8.2761e-06 | 2433 | 0 | 0 | 3.8885 | 1688 | 0
Bay Area | 2882 | 428 | 894.5062 | 1079 | 1246.8721 | 89 | 6.1881e-05 | 0.066431 | 7.3629 | 13.8516 | 26.4856 | 0.84103 | 1.1316 | 5.7243 | 0.97785 | 4.1108e-06 | 0.00024712 | 0.39666 | 0.7174 | {9E806E71-872A-40DE-ABFF-C0053F485B27} | 13532107 | LAKEWOOD 2107 | 69586 | 37.9274 | -122.0864 | LAKEWOOD 210769586 | 382 | 1038 | 70402.5179 | 19693.5361 | 50708.9819 | 8401.1793 | 12841.6417 | 0.021994 | 0.0055074 | 2.09 | 12.1236 | 1259 | 0.00036586 | 2434 | 0 | 0 | 5.2202 | 2033 | 0
Bay Area | 3836 | 165 | 351.46 | 498 | 546.5481 | 37 | 6.179e-05 | 0.066431 | 1.8676 | 1.4674 | 5.4712 | 0.028567 | 0.44523 | 0.64999 | 0.91892 | 4.1048e-06 | 9.7103e-05 | 0.33133 | 0.64305 | {4892CAAF-65E7-4660-A10F-F15BB35B52DD} | 13600401 | LAS AROMAS 0401 | 3342 | 37.8986 | -122.1769 | LAS AROMAS 04013342 | 64 | 237 | 14481.2281 | 3654.0283 | 10827.1997 | 3654.0283 | 10827.1997 | 0.0035928 | 0.0022862 | 2.1301 | 13.4595 | 1869 | 0.00015188 | 2435 | 0 | 0 | 2.2705 | 2415 | 0
North Coast | 193 | 29 | 45.5133 | 32 | 47.0507 | 5 | 9.1968e-05 | 0.053145 | 0.42245 | 57.8226 | 403.3561 | 0.35912 | 0 | 1.1358 | 1.8 | 4.0852e-06 | 5.2874e-05 | 0.90625 | 0.96733 | {F40CB029-270F-46C5-9305-F30A68FC7241} | 192251102 | RIO DELL 1102 | 8768 | 40.4765 | -124.1008 | RIO DELL 11028768 | 61 | 57 | 11528.6614 | 8376.3931 | 3152.2684 | 449.1583 | 458.7294 | 0.00026437 | 0.00045984 | 1.5694 | 6.4 | 2212 | 2.0426e-05 | 2436 | 0 | 0 | 0.27909 | 1305 | 0
Central Coast | 2445 | 7 | 11.2947 | 9 | 12.4302 | 1 | 6.1411e-05 | 0.066432 |  |  |  |  | 0.050885 | 0.63916 | 1 | 4.0796e-06 | 6.1411e-05 | 0.77778 | 0.90865 | {8ED769A0-FD6A-439C-A794-36AC054AC7B8} | 82161102 | LOYOLA 1102 | 60082 | 37.3483 | -122.1143 | LOYOLA 110260082 | 109 | 134 | 13024.4833 | 6524.9258 | 6499.5575 | 51.5332 | 234.8024 | 6.1411e-05 | 6.1411e-05 | 1.6135 | 9 | 2119 | 4.0796e-06 | 2437 | 0 | 0 | 0.032021 | 1381 | 0
Bay Area | 726 | 141 | 280.723 | 370 | 407.8233 | 48 | 6.1343e-05 | 0.066431 | 0.071902 | 0.017148 | 0.00029956 | 2.9414e-07 | 0.18308 | 0.24453 | 0.625 | 4.0751e-06 | 2.9746e-05 | 0.38108 | 0.68834 | {33CCC2F4-F827-4C07-9171-27096EF33E3C} | 42011104 | SAN RAFAEL 1104 | circuit_breaker | 37.9708 | -122.5271 | SAN RAFAEL 1104circuit_breaker | 337 | 2111 | 103250.0015 | 16837.4541 | 86412.5474 | 5364.6138 | 30453.6797 | 0.0014278 | 0.0029445 | 1.9909 | 7.7083 | 2470 | 0.0001956 | 2438 | 0 | 0 | 3.3334 | 2150 | 0
Bay Area | 8271 | 17 | 48.831 | 31 | 56.8453 | 4 | 6.1046e-05 | 0.06643 | 19.4055 | 48.0372 | 235.8557 | 9.1456 | 0 | 0.19712 | 1 | 4.0553e-06 | 0.00074209 | 0.54839 | 0.85902 | {151C0216-83E8-4EAF-9D71-0D50917A8A0E} | 43051101 | MONTICELLO 1101 | 52910 | 38.5062 | -122.202 | MONTICELLO 110152910 | 75 | 17 | 5937.1917 | 5053.4949 | 883.6968 | 3504.9565 | 443.9052 | 0.0029684 | 0.00024418 | 2.8724 | 7.75 | 538 | 1.6221e-05 | 2439 | 0 | 0 | 2.1779 | 2663 | 0
Central Coast | 1259 | 542 | 1149.7179 | 1736 | 1840.6206 | 120 | 6.1006e-05 | 0.066432 | 0.76109 | 1.0363 | 3.5958 | 0.011396 | 0.13538 | 0.73081 | 0.75 | 4.0527e-06 | 5.4509e-05 | 0.31221 | 0.62464 | {798C7F9A-11E4-4951-9A2B-A99559D5AAA3} | 83371106 | SARATOGA 1106 | LC22 | 37.24 | -121.9965 | SARATOGA 1106LC22 | 240 | 474 | 40970.0604 | 13269.339 | 27700.7214 | 11864.1721 | 15892.6774 | 0.0065411 | 0.0073207 | 2.1213 | 14.4667 | 2197 | 0.00048633 | 2440 | 0 | 0 | 7.3721 | 2317 | 0
Bay Area | 3969 | 197 | 402.1167 | 681 | 678.7637 | 44 | 6.0823e-05 | 0.066431 | 3.5117 | 2.4414 | 6.5937 | 0.053394 | 0.051086 | 0.042709 | 0.47727 | 4.0405e-06 | 0.00017363 | 0.28928 | 0.59243 | {6DF01F7D-D94B-4655-BAF6-B3A3B3F7FF40} | 13600401 | LAS AROMAS 0401 | LA401R | 37.8941 | -122.1785 | LAS AROMAS 0401LA401R | 108 | 347 | 22192.5327 | 6361.0626 | 15831.4702 | 4766.0601 | 11667.1739 | 0.0076399 | 0.0026762 | 2.0412 | 15.4773 | 1511 | 0.00017778 | 2441 | 0 | 0 | 2.9615 | 1252 | 0
Bay Area | 2281 | 119 | 202.8492 | 372 | 341.904 | 30 | 6.0791e-05 | 0.066431 | 0.15214 | 0.031723 | 0.00065665 | 7.1949e-07 | 0.094395 | 0.61566 | 0.33341 | 4.0384e-06 | 3.8072e-05 | 0.31989 | 0.59329 | {2C543D7C-5902-4DC9-BE9B-719A66315791} | 42031124 | ALTO 1124 | circuit_breaker | 37.8987 | -122.525 | ALTO 1124circuit_breaker | 271 | 1425 | 69792.5132 | 11198.0443 | 58594.4688 | 3322.8701 | 14051.4662 | 0.0011422 | 0.0018237 | 1.7046 | 12.4 | 2363 | 0.00012115 | 2442 | 0 | 0 | 2.0647 | 2156 | 0
Sierra | 5023 | 20 | 26.1197 | 24 | 27.9139 | 3 | 6.076e-05 | 0.066432 | 25.7804 | 19.6123 | 82.2252 | 4.1041 | 2.1726 | 46.5531 | 1 | 4.0364e-06 | 0.0010357 | 0.83333 | 0.93572 | {C99F1365-4BA0-493A-A0A5-5D7F7D14700C} | 152261106 | DIAMOND SPRINGS 1106 | circuit_breaker | 38.693 | -120.8258 | DIAMOND SPRINGS 1106circuit_breaker | 94 | 160 | 8914.417 | 3624.8586 | 5289.5583 | 305.3669 | 422.6889 | 0.0031072 | 0.00018228 | 1.306 | 8 | 392 | 1.2109e-05 | 2443 | 0 | 0 | 0.18975 | 192 | 0
North Coast | 180 | 3 | 3.6831 | 4 | 3.8966 | 3 | 5.5072e-05 | 0.074909 | 0.0024582 | 0.22446 | 0.97125 | 4.3726e-06 | 0.0014749 | 16.1367 | 1 | 4.0039e-06 | 1.3679e-05 | 0.75 | 0.94523 | {91E6CF65-65E6-49D9-99AE-7F739C671773} | 42141101 | CLEAR LAKE 1101 | 92870 | 38.9894 | -122.8469 | CLEAR LAKE 110192870 | 341 | 654 | 66268.9305 | 29084.561 | 37184.3695 | 859.6824 | 1058.2594 | 4.1036e-05 | 0.00016522 | 1.2277 | 1.3333 | 2729 | 1.2012e-05 | 2444 | 0 | 0 | 0.53418 | 999 | 0
Bay Area | 1418 | 389 | 955.0589 | 889 | 1246.7144 | 52 | 6.8821e-05 | 0.058765 | 2.4945 | 1.1532 | 3.9125 | 0.037956 | 0.20486 | 0.60637 | 1.3077 | 4.0009e-06 | 0.0001114 | 0.43757 | 0.76606 | {269CD2EB-7EB5-49D9-B9E1-2226E15FD282} | 12101104 | OAKLAND K 1104 | CR204 | 37.8317 | -122.1948 | OAKLAND K 1104CR204 | 130 | 468 | 28837.9686 | 6584.4717 | 22253.4969 | 6584.4717 | 22253.4969 | 0.0057928 | 0.0035787 | 2.4552 | 17.0962 | 1791 | 0.00020805 | 2445 | 0 | 0 | 4.0914 | 1762 | 0
North Coast | 5970 | 5 | 8.9599 | 10 | 12.3049 | 1 | 6.0192e-05 | 0.06643 | 0.0061901 | 0.66718 | 4.4005 | 2.724e-05 | 0.40929 | 2.2062 | 1.0066 | 3.9985e-06 | 3.7259e-07 | 0.5 | 0.72816 | {20EEDFE7-15DE-4AF7-B5E5-DDB50839E523} | 43371102 | LAKEVILLE 1102 | 530 | 38.2561 | -122.5866 | LAKEVILLE 1102530 | 102 | 59 | 16139.9664 | 8337.7277 | 7802.2387 | 291.9883 | 1391.0937 | 3.7259e-07 | 6.0192e-05 | 1.792 | 10 | 2881 | 3.9985e-06 | 2446 | 0 | 0 | 0.18143 | 804 | 0
Central Coast | 5792 | 10 | 14.876 | 66 | 44.4443 | 8 | 2.1444e-05 | 0.14909 | 7.6842 | 7.8964 | 18.0058 | 0.66697 | 3.4549 | 22.8689 | 1.0531 | 3.9786e-06 | 0.00010556 | 0.15152 | 0.33471 | {30C139BA-309C-45BA-85AD-14DDE6598AF6} | 83242105 | MORGAN HILL 2105 | circuit_breaker | 37.1267 | -121.6592 | MORGAN HILL 2105circuit_breaker | 69 | 235 | 13416.7767 | 2881.8434 | 10534.9333 | 791.0708 | 1456.8174 | 0.00084447 | 0.00017155 | 1.4876 | 8.25 | 1829 | 3.1829e-05 | 2447 | 0 | 0 | 0.49155 | 1712 | 0
Bay Area | 717 | 246 | 415.1437 | 746 | 727.6737 | 51 | 6.647e-05 | 0.057507 | 3.6451 | 8.9101 | 20.9571 | 0.26571 | 1.3926 | 13.1611 | 1.6319 | 3.9753e-06 | 0.00018182 | 0.32976 | 0.57051 | {AFD202FA-B4DE-44FF-BED9-22B6EABBD39F} | 13151105 | RADUM 1105 | MR282 | 37.6491 | -121.8809 | RADUM 1105MR282 | 211 | 288 | 21680.9107 | 10192.3583 | 11488.5524 | 4954.2228 | 6931.9392 | 0.0092727 | 0.00339 | 1.6876 | 14.6275 | 1480 | 0.00020274 | 2448 | 0 | 0 | 3.0784 | 2398 | 0
Bay Area | 9195 | 193 | 346.0887 | 356 | 443.3271 | 18 | 5.9269e-05 | 0.066431 | 0.30486 | 8.2287 | 32.0787 | 0.024019 | 5.3769e-14 | 2.9999 | 1 | 3.9373e-06 | 4.1263e-05 | 0.54213 | 0.78066 | {9B2F70E2-3822-4ABC-9A9F-F92985EE671F} | 12541106 | OAKLAND X 1106 | CR266 | 37.8051 | -122.1711 | OAKLAND X 1106CR266 | 14 | 7 | 2141.3055 | 1901.6084 | 239.6971 | 1901.6084 | 239.6971 | 0.00074273 | 0.0010668 | 1.7932 | 19.7778 | 2322 | 7.0871e-05 | 2449 | 0 | 0 | 1.1816 | 2697 | 0
North Coast | 7432 | 51 | 66.4796 | 100 | 87.5877 | 12 | 9.0998e-05 | 0.044288 | 0.68562 | 0.49713 | 2.3473 | 0.010079 | 0.27686 | 0.084608 | 2.3333 | 3.9331e-06 | 7.9495e-05 | 0.51 | 0.75901 | {7D69F374-F9B0-4F64-806B-E0305A606677} | 42771114 | UKIAH 1114 | 72990 | 39.1339 | -123.1661 | UKIAH 111472990 | 67 | 147 | 10042.6879 | 5262.4562 | 4780.2317 | 1032.2982 | 3184.3535 | 0.00095394 | 0.001092 | 1.3035 | 8.3333 | 1985 | 4.7197e-05 | 2450 | 0 | 0 | 0.64144 | 39 | 0
Bay Area | 5148 | 106 | 299.766 | 276 | 390.094 | 17 | 6.6422e-05 | 0.058616 | 0.5722 | 0.87011 | 3.1909 | 0.0097993 | 0.34087 | 0.89501 | 1.3639 | 3.9296e-06 | 5.5025e-05 | 0.38406 | 0.76845 | {6C0139D5-EF28-447A-8798-DD6F8DC2F6B3} | 42011105 | SAN RAFAEL 1105 | 534 | 37.9763 | -122.4968 | SAN RAFAEL 1105534 | 53 | 88 | 6953.6009 | 2541.7011 | 4411.8997 | 1383.1216 | 2219.7337 | 0.00093543 | 0.0011292 | 2.828 | 16.2353 | 2192 | 6.6803e-05 | 2451 | 0 | 0 | 0.85943 | 2761 | 0
Central Valley | 4363 | 11 | 20.3776 | 88 | 52.3426 | 10 | 5.9016e-05 | 0.066432 | 11.644 | 18.547 | 52.928 | 1.697 | 9.685 | 33.6238 | 1.033 | 3.9206e-06 | 0.00037569 | 0.125 | 0.38931 | {C985F098-6ECF-4C69-B902-1B5157262ED5} | 163451702 | FROGTOWN 1702 | 74648 | 38.071 | -120.539 | FROGTOWN 170274648 | 196 | 646 | 30921.0275 | 8485.2437 | 22435.7839 | 1211.7571 | 706.2512 | 0.0037569 | 0.00059016 | 1.8525 | 8.8 | 974 | 3.9206e-05 | 2452 | 0 | 0 | 0.75295 | 2680 | 0
Bay Area | 1446 | 51 | 112.735 | 114 | 143.0105 | 19 | 5.8776e-05 | 0.066431 | 0.0081293 | 0.19359 | 0.87361 | 7.3427e-05 | 0.4674 | 0.40865 | 0.89474 | 3.9045e-06 | 2.1243e-05 | 0.44737 | 0.7883 | {E52E3AA8-626F-4DCF-BFEC-F21E6141C71E} | 42261101 | BOLINAS 1101 | 528 | 37.8993 | -122.6347 | BOLINAS 1101528 | 124 | 458 | 21723.4685 | 4938.4038 | 16785.0647 | 2645.4949 | 7166.2039 | 0.00040362 | 0.0011167 | 2.2105 | 6 | 2583 | 7.4186e-05 | 2453 | 0 | 0 | 1.6438 | 2140 | 0
Bay Area | 7858 | 14 | 18.0232 | 55 | 41.7747 | 4 | 5.8734e-05 | 0.066431 | 2.1974 | 0.68063 | 1.7032 | 0.014667 | 0.28485 | 1.703 | 1 | 3.9018e-06 | 0.00013209 | 0.25455 | 0.43144 | {B57323AB-C84A-4096-B877-0C808916375A} | 42011104 | SAN RAFAEL 1104 | 2235 | 37.9839 | -122.5713 | SAN RAFAEL 11042235 | 27 | 149 | 8262.1431 | 1389.3312 | 6872.8118 | 240.5368 | 972.4334 | 0.00052837 | 0.00023493 | 1.2874 | 13.75 | 1690 | 1.5607e-05 | 2454 | 0 | 0 | 0.14946 | 1334 | 0
Bay Area | 5191 | 276 | 741.2595 | 581 | 911.869 | 20 | 5.8722e-05 | 0.066431 | 1.1232 | 0.2926 | 1.3744 | 0.0061663 | 0.3802 | 0.44004 | 0.65 | 3.9009e-06 | 5.8807e-05 | 0.47504 | 0.8129 | {FDBE20C4-A243-4218-824C-85EFE8D9D967} | 12101104 | OAKLAND K 1104 | CR206 | 37.8317 | -122.197 | OAKLAND K 1104CR206 | 49 | 279 | 15090.9485 | 2883.3047 | 12207.6439 | 2883.3047 | 12207.6439 | 0.0011761 | 0.0011744 | 2.6857 | 29.05 | 2153 | 7.8019e-05 | 2455 | 0 | 0 | 1.7916 | 2734 | 0
Central Valley | 5484 | 0 | 0 | 3 | 1.6027 | 1 | 5.8524e-05 | 0.066431 |  |  |  |  | 1.0221 | 1.3637 | 1 | 3.8878e-06 | 5.8524e-05 | 0 | 0 | {763723A0-FD03-42C3-9B8B-0F105886147F} | 162821702 | STANISLAUS 1702 | 75348 | 38.2622 | -120.3292 | STANISLAUS 170275348 | 165 | 389 | 23232.9488 | 8681.8427 | 14551.1061 | 8681.8427 | 14551.1061 | 5.8524e-05 | 5.8524e-05 |  | 3 | 2154 | 3.8878e-06 | 2456 | 0 | 0 | 5.3946 | 1434 | 0
Central Coast | 4545 | 372 | 1049.2514 | 954 | 1385.3376 | 103 | 5.8351e-05 | 0.06591 | 3.4827 | 15.164 | 58.7714 | 0.82 | 0.55358 | 4.2155 | 1.0421 | 3.8467e-06 | 0.00013446 | 0.38994 | 0.7574 | {272F711A-D76D-479D-B7FF-5C57D964944A} | 83692104 | ROB ROY 2104 | 12596 | 36.9871 | -121.8328 | ROB ROY 210412596 | 230 | 305 | 36227.9432 | 17006.0385 | 19221.9047 | 11237.3875 | 11832.9675 | 0.013849 | 0.0060102 | 2.8206 | 9.2621 | 1673 | 0.00039621 | 2457 | 0 | 0 | 6.9826 | 1263 | 0
Central Valley | 6304 | 461 | 664.3118 | 947 | 896.9965 | 57 | 6.94e-05 | 0.054777 | 4.8041 | 4.8671 | 12.9359 | 0.20406 | 0.53503 | 2.5334 | 1.6319 | 3.8203e-06 | 0.00017364 | 0.4868 | 0.7406 | {976CA043-61DE-4F22-87BA-0696E25C4DF1} | 163661702 | MIWUK 1702 | 47143 | 38.0045 | -120.2628 | MIWUK 170247143 | 150 | 375 | 24675.5978 | 7868.7696 | 16806.8282 | 7868.7696 | 16806.8282 | 0.0098975 | 0.0039558 | 1.441 | 16.614 | 1510 | 0.00021775 | 2458 | 0 | 0 | 4.8894 | 122 | 0
Bay Area | 2249 | 99 | 315.2846 | 208 | 374.4653 | 16 | 5.7229e-05 | 0.066431 | 9.5907 | 2.7649 | 8.8944 | 0.19652 | 0.76383 | 0.57882 | 1 | 3.8018e-06 | 0.0001793 | 0.47596 | 0.84196 | {993BD642-B43F-4A07-B618-DAD20FD40FEE} | 12101104 | OAKLAND K 1104 | CR326 | 37.8309 | -122.1963 | OAKLAND K 1104CR326 | 42 | 157 | 8977.2003 | 2098.9601 | 6878.2403 | 2098.9601 | 6878.2403 | 0.0028688 | 0.00091567 | 3.1847 | 13 | 1488 | 6.0829e-05 | 2459 | 0 | 0 | 1.3042 | 1915 | 0
Bay Area | 814 | 419 | 1011.1651 | 889 | 1274.9832 | 68 | 5.6992e-05 | 0.066431 | 2.956 | 1.1402 | 4.7577 | 0.046447 | 0.78276 | 1.3728 | 0.88235 | 3.786e-06 | 0.00010764 | 0.47132 | 0.79308 | {2A115028-6F68-4B14-BB47-6F364E8C5941} | 12541104 | OAKLAND X 1104 | CR022 | 37.8218 | -122.2 | OAKLAND X 1104CR022 | 158 | 896 | 49359.2038 | 9630.8273 | 39728.3766 | 9630.8273 | 39728.3766 | 0.0073198 | 0.0038754 | 2.4133 | 13.0735 | 1818 | 0.00025745 | 2460 | 0 | 0 | 5.9843 | 1158 | 0
Central Valley | 1279 | 1151 | 1619.1467 | 3622 | 2820.9563 | 219 | 5.7846e-05 | 0.064309 | 22.3471 | 178.1171 | 1809.9509 | 239.7093 | 0.76365 | 9.3118 | 1.1208 | 3.7253e-06 | 0.00057789 | 0.31778 | 0.57397 | {C413BF51-2D4A-4E14-8A5C-AF93355185D2} | 163351702 | CURTIS 1702 | 8000 | 38.0084 | -120.301 | CURTIS 17028000 | 299 | 529 | 57186.6958 | 23052.1801 | 34134.5157 | 23052.1801 | 34134.5157 | 0.12656 | 0.012668 | 1.4067 | 16.5388 | 701 | 0.00081584 | 2461 | 0 | 0 | 14.324 | 155 | 0
Bay Area | 4106 | 238 | 574.9004 | 394 | 662.4941 | 37 | 5.6056e-05 | 0.066431 | 7.5086 | 4.1771 | 11.8692 | 0.25593 | 0.64171 | 2.2462 | 1 | 3.7238e-06 | 0.00024625 | 0.60406 | 0.86778 | {A4D00FB7-3066-4764-B528-AB78985E682B} | 12541104 | OAKLAND X 1104 | CR214 | 37.819 | -122.1999 | OAKLAND X 1104CR214 | 72 | 407 | 23133.8979 | 4637.1496 | 18496.7484 | 4637.1496 | 18496.7484 | 0.0091114 | 0.0020741 | 2.4155 | 10.6486 | 1260 | 0.00013778 | 2462 | 0 | 0 | 2.8814 | 327 | 0
North Coast | 9419 | 123 | 197.0529 | 152 | 210.6141 | 30 | 5.5419e-05 | 0.066432 | 7.8936 | 64.0022 | 398.3081 | 7.0009 | 0.24196 | 9.2084 | 1.0084 | 3.6816e-06 | 0.00024885 | 0.80921 | 0.93561 | {DEA0AB0F-3AB6-4F54-9C8C-03D0C01BC917} | 42841111 | GUALALA 1111 | 498 | 38.7543 | -123.5097 | GUALALA 1111498 | 45 | 2 | 4947.8039 | 4821.7264 | 126.0774 | 3498.0819 | 11.7636 | 0.0074656 | 0.0016626 | 1.6021 | 5.0667 | 1253 | 0.00011045 | 2463 | 0 | 0 | 2.1736 | 289 | 0
Central Valley | 10015 | 4 | 4.9109 | 15 | 9.8655 | 1 | 5.537e-05 | 0.066432 | 0.30314 | 2.8685 | 23.9501 | 0.8055 | 0.71903 | 19.4558 | 1.0044 | 3.6783e-06 | 1.6785e-05 | 0.26667 | 0.49778 | {705B5A79-F7F3-41CE-925F-797105088580} | 163351705 | CURTIS 1705 | 11790 | 37.9746 | -120.2392 | CURTIS 170511790 | 4 | 0 | 22.8988 | 22.8988 | 0 | 22.8988 | 0 | 1.6785e-05 | 5.537e-05 | 1.2277 | 15 | 2666 | 3.6783e-06 | 2464 | 0 | 0 | 0.014229 | 505 | 0
North Coast | 4535 | 42 | 79.2358 | 72 | 94.7554 | 15 | 5.5265e-05 | 0.066432 | 10.0823 | 71.4685 | 833.7027 | 24.6183 | 3.7535 | 12.4046 | 1.051 | 3.6713e-06 | 0.00028126 | 0.58333 | 0.83621 | {55873172-8DD8-4C14-AA30-FE38E0573859} | 43311108 | KONOCTI 1108 | 4041 | 38.9539 | -122.7257 | KONOCTI 11084041 | 101 | 459 | 31063.9383 | 7544.3878 | 23519.5505 | 1537.6241 | 4653.2786 | 0.004219 | 0.00082897 | 1.8866 | 4.8 | 1174 | 5.507e-05 | 2465 | 0 | 0 | 0.95544 | 1223 | 0
Central Coast | 233 | 3 | 5.5351 | 8 | 8.4858 | 5 | 5.4897e-05 | 0.066432 | 0.1846 | 0.14168 | 0.38754 | 0.00096911 | 0 | 0.01854 | 0.2 | 3.6469e-06 | 3.5672e-05 | 0.375 | 0.65227 | {9CE095E8-15BC-49D7-95AC-553D14C8CC1F} | 82021102 | LOS GATOS 1102 | circuit_breaker | 37.2263 | -121.9775 | LOS GATOS 1102circuit_breaker | 263 | 853 | 42940.2549 | 9572.3733 | 33367.8815 | 1766.8106 | 6793.8321 | 0.00017836 | 0.00027448 | 1.845 | 1.6 | 2390 | 1.8234e-05 | 2466 | 0 | 0 | 1.0978 | 2603 | 0
Bay Area | 69 | 109 | 274.7163 | 110 | 275.0754 | 13 | 5.4843e-05 | 0.066432 | 0.95643 | 0.9898 | 2.8519 | 0.027676 | 1.152 | 7.4265 | 1.0095 | 3.6433e-06 | 6.5523e-05 | 0.99091 | 0.99869 | {19E4E8D4-9C4C-4C6B-8FB5-CC59DB118DCE} | 22811102 | PACIFICA 1102 | 6783 | 37.6243 | -122.4867 | PACIFICA 11026783 | 162 | 855 | 45396.43 | 10342.1784 | 35054.2516 | 2227.3024 | 1848.4492 | 0.0008518 | 0.00071296 | 2.5203 | 8.4615 | 2085 | 4.7363e-05 | 2467 | 0 | 0 | 1.384 | 2203 | 0
Bay Area | 548 | 461 | 1076.4716 | 1902 | 1909.8771 | 90 | 5.4626e-05 | 0.066431 | 0.14434 | 0.060939 | 0.22493 | 0.00022884 | 0.34907 | 0.11031 | 0.6 | 3.6289e-06 | 3.4427e-05 | 0.24238 | 0.56363 | {343DAC73-DC1A-4C06-8C35-1C7245E7BB91} | 43091102 | GREENBRAE 1102 | 1254 | 37.9451 | -122.5185 | GREENBRAE 11021254 | 285 | 1800 | 93085.23 | 15162.3612 | 77922.8688 | 9494.3832 | 37359.3343 | 0.0030984 | 0.0049163 | 2.3351 | 21.1333 | 2409 | 0.0003266 | 2468 | 0 | 0 | 5.8995 | 2746 | 0
Bay Area | 7001 | 20 | 36.6792 | 39 | 45.7862 | 2 | 5.4359e-05 | 0.066432 | 0.24563 | 0.12238 | 0.55979 | 0.001999 | 0 | 0 | 0 | 3.6112e-06 | 3.493e-05 | 0.51282 | 0.8011 | {DDAEA41C-A887-4E18-B3DF-4A90221F1904} | 12101101 | OAKLAND K 1101 | CR346 | 37.8534 | -122.2371 | OAKLAND K 1101CR346 | 16 | 25 | 1411.5429 | 301.378 | 1110.1649 | 301.378 | 1110.1649 | 6.9859e-05 | 0.00010872 | 1.834 | 19.5 | 2399 | 7.2223e-06 | 2469 | 0 | 0 | 0.18727 | 2781 | 0
Central Valley | 52 | 139 | 191.5158 | 559 | 357.7985 | 58 | 5.8876e-05 | 0.060705 | 10.8167 | 43.9939 | 338.3635 | 11.8071 | 2.8179 | 18.596 | 1.3734 | 3.6106e-06 | 0.00029598 | 0.24866 | 0.53526 | {897848FB-F125-46A8-B9E9-7A6CE5229B91} | 163351702 | CURTIS 1702 | 34426 | 37.9665 | -120.2389 | CURTIS 170234426 | 165 | 631 | 36886.6337 | 11088.7783 | 25797.8554 | 7090.4475 | 9677.4323 | 0.017167 | 0.0034148 | 1.3778 | 9.6379 | 1133 | 0.00020941 | 2470 | 0 | 0 | 4.4058 | 2644 | 0
Bay Area | 2971 | 235 | 590.0575 | 779 | 885.4562 | 53 | 5.4162e-05 | 0.066431 | 2.9566 | 1.8557 | 6.079 | 0.051809 | 0.50718 | 1.3526 | 0.92453 | 3.5981e-06 | 0.00011095 | 0.30167 | 0.66639 | {E0AFB0D0-4FAA-4A38-B181-558E89FECB34} | 12541104 | OAKLAND X 1104 | CR288 | 37.8186 | -122.2054 | OAKLAND X 1104CR288 | 100 | 394 | 21336.9617 | 4410.6695 | 16926.2922 | 4410.6695 | 16926.2922 | 0.0058803 | 0.0028706 | 2.5109 | 14.6981 | 1794 | 0.0001907 | 2471 | 0 | 0 | 2.7407 | 1042 | 0
North Coast | 7055 | 227 | 373.3084 | 358 | 431.9726 | 30 | 5.3928e-05 | 0.066432 | 4.8761 | 13.0815 | 44.0926 | 0.33839 | 0.33901 | 1.4357 | 1 | 3.5825e-06 | 0.00013771 | 0.63408 | 0.86419 | {0E0C2894-9F4C-4F14-AF8A-F5A44822C594} | 192431108 | HARRIS 1108 | 2062 | 40.7571 | -124.1469 | HARRIS 11082062 | 177 | 585 | 34770.7108 | 8481.5172 | 26289.1937 | 2687.4494 | 7345.5165 | 0.0041312 | 0.0016178 | 1.6445 | 11.9333 | 1648 | 0.00010748 | 2472 | 0 | 0 | 1.6699 | 1780 | 0
Central Coast | 7486 | 0 | 0 | 23 | 12.0018 | 2 | 5.3763e-05 | 0.066431 | 0 | 0 | 0 | 0 | 0.10398 | 62.0774 | 1 | 3.5715e-06 | 2.6235e-05 | 0 | 0 | {FC7EF3C1-E676-4F19-A408-525DCCC4AA40} | 82161102 | LOYOLA 1102 | LL12 | 37.3578 | -122.1331 | LOYOLA 1102LL12 | 165 | 141 | 18434.3177 | 9731.1646 | 8703.1531 | 176.3756 | 170.7533 | 5.2471e-05 | 0.00010753 |  | 11.5 | 2512 | 7.1431e-06 | 2473 | 0 | 0 | 0.10959 | 1956 | 0
Central Coast | 3681 | 88 | 265.0534 | 170 | 311.574 | 24 | 5.4449e-05 | 0.063664 | 2.1775 | 2.0198 | 5.6341 | 0.053353 | 0.55348 | 1.1598 | 1.1667 | 3.553e-06 | 9.0399e-05 | 0.51765 | 0.85069 | {C52D5D52-9044-49A2-A14C-4D5315EB34ED} | 83252104 | PAUL SWEET 2104 | 11074 | 36.9941 | -121.9775 | PAUL SWEET 210411074 | 83 | 331 | 17896.0498 | 4925.4583 | 12970.5915 | 4575.9781 | 12564.1363 | 0.0021696 | 0.0013068 | 3.012 | 7.0833 | 1905 | 8.5271e-05 | 2474 | 0 | 0 | 2.8434 | 1638 | 0
North Coast | 2863 | 9 | 14.5217 | 10 | 14.9775 | 1 | 5.3142e-05 | 0.066432 |  |  |  |  | 0 | 0.27146 | 1 | 3.5303e-06 | 5.3142e-05 | 0.9 | 0.96957 | {B435E505-091B-4464-AF4F-65421296FB23} | 192331104 | EUREKA E 1104 | 35934 | 40.7712 | -124.1618 | EUREKA E 110435934 | 110 | 348 | 22454.402 | 5459.9113 | 16994.4906 | 163.1504 | 185.6536 | 5.3142e-05 | 5.3142e-05 | 1.6135 | 10 | 2210 | 3.5303e-06 | 2475 | 0 | 0 | 0.10138 | 1070 | 0
Bay Area | 3063 | 1 | 1.6135 | 12 | 6.6266 | 1 | 5.2918e-05 | 0.066431 | 0 | 0 | 0 | 0 | 0.13274 | 0.0066372 | 1 | 3.5154e-06 | 0 | 0.083333 | 0.24349 | {85056666-4A2B-4DAF-B399-DC93301E78AA} | 42011106 | SAN RAFAEL 1106 | 48752 | 37.9743 | -122.5239 | SAN RAFAEL 110648752 | 102 | 440 | 20377.6271 | 3711.6115 | 16666.0157 | 44.4852 | 522.1383 | 0 | 5.2918e-05 | 1.6135 | 12 | 2894 | 3.5154e-06 | 2476 | 0 | 0 | 0.027642 | 407 | 0
Bay Area | 671 | 23 | 54.5335 | 33 | 59.8925 | 10 | 5.1345e-05 | 0.068975 | 15.0378 | 86.5421 | 250.184 | 11.5571 | 1.858 | 10.8344 | 1.0055 | 3.5112e-06 | 0.00052359 | 0.69697 | 0.91052 | {C85608A6-E764-4BFF-96A3-04B105997205} | 14161106 | ROSSMOOR 1106 | 76468 | 37.8692 | -122.0987 | ROSSMOOR 110676468 | 56 | 388 | 23774.5938 | 4734.8645 | 19039.7293 | 812.7944 | 4679.4636 | 0.0052359 | 0.00051345 | 2.371 | 3.3 | 766 | 3.5112e-05 | 2477 | 0 | 0 | 0.50505 | 2410 | 0
Central Valley | 1229 | 336 | 448.5233 | 1900 | 1291.0901 | 131 | 5.5943e-05 | 0.062375 | 10.7833 | 75.4459 | 800.7236 | 54.4012 | 0.61923 | 6.8198 | 1.2244 | 3.4848e-06 | 0.00032621 | 0.17684 | 0.3474 | {11F969DC-9C50-4BBE-BE33-15DB7CEEDE86} | 163351703 | CURTIS 1703 | 9240 | 37.8315 | -120.2371 | CURTIS 17039240 | 294 | 838 | 55786.2546 | 17593.4022 | 38192.8523 | 17593.4022 | 38192.8523 | 0.042734 | 0.0073285 | 1.3349 | 14.5038 | 1065 | 0.00045651 | 2478 | 0 | 0 | 10.932 | 1398 | 0
Central Valley | 6293 | 309 | 480.5718 | 903 | 710.1767 | 100 | 5.1377e-05 | 0.066629 | 2.3909 | 6.235 | 28.3781 | 0.26559 | 0.70259 | 9.9767 | 1.0413 | 3.4755e-06 | 9.3413e-05 | 0.34219 | 0.67669 | {944E3EC7-4285-4D17-99A0-D6960B77E4D2} | 163351705 | CURTIS 1705 | 8170 | 37.987 | -120.2611 | CURTIS 17058170 | 220 | 554 | 36627.9268 | 12664.7539 | 23963.1729 | 12248.0291 | 23671.1998 | 0.0093413 | 0.0051377 | 1.5552 | 9.03 | 1888 | 0.00034755 | 2479 | 0 | 0 | 7.6106 | 1452 | 0
Bay Area | 4672 | 121 | 277.7155 | 301 | 378.952 | 46 | 6.1251e-05 | 0.056323 | 2.442 | 3.7413 | 12.0101 | 0.12608 | 0.99288 | 4.8111 | 1.5877 | 3.4629e-06 | 0.00010448 | 0.40199 | 0.73285 | {71494031-9F05-4CC0-A953-4E31E51E28B7} | 14161101 | ROSSMOOR 1101 | 8132 | 37.911 | -122.1008 | ROSSMOOR 11018132 | 97 | 239 | 18570.1599 | 5907.1746 | 12662.9853 | 4210.4765 | 9317.2345 | 0.0048062 | 0.0028175 | 2.2952 | 6.5435 | 1836 | 0.00015929 | 2480 | 0 | 0 | 2.6163 | 2049 | 0
North Valley | 3113 | 0 | 0 | 1 | 0.45574 | 1 | 5.1992e-05 | 0.066431 |  |  |  |  | 0.019912 | 0.10929 | 1 | 3.4538e-06 | 5.1992e-05 | 0 | 0 | {31D1DD7F-CFDD-44BD-88FD-B9B13228B34E} | 103541105 | RED BLUFF 1105 | 161818 | 40.215 | -122.1905 | RED BLUFF 1105161818 | 102 | 160 | 14496.1053 | 7665.1166 | 6830.9887 | 275.1903 | 162.3442 | 5.1992e-05 | 5.1992e-05 |  | 1 | 2220 | 3.4538e-06 | 2481 | 0 | 0 | 0.171 | 2475 | 0
Bay Area | 6909 | 513 | 769.2811 | 1437 | 1344.8748 | 75 | 5.557e-05 | 0.062889 | 1.3549 | 1.6291 | 5.4058 | 0.034604 | 0.28581 | 2.3198 | 1.2135 | 3.4467e-06 | 7.1235e-05 | 0.35699 | 0.57201 | {5E439C6C-9351-476C-9634-FD9D0D59EEC5} | 12350401 | ORINDA 0401 | 3442 | 37.8866 | -122.1911 | ORINDA 04013442 | 199 | 485 | 31866.7094 | 10746.159 | 21120.5504 | 7643.0559 | 14866.523 | 0.0053426 | 0.0041677 | 1.4996 | 19.16 | 2045 | 0.0002585 | 2482 | 0 | 0 | 4.7492 | 2220 | 0
Bay Area | 5153 | 262 | 357.4281 | 455 | 455.1639 | 29 | 5.1757e-05 | 0.066432 | 7.4778 | 6.7928 | 25.8037 | 0.61894 | 0.16211 | 0.081569 | 0.41379 | 3.4383e-06 | 0.00023345 | 0.57582 | 0.78527 | {35E6FC31-93E6-466C-8E12-BDEF19C3F3E9} | 14161106 | ROSSMOOR 1106 | L522R | 37.8878 | -122.1163 | ROSSMOOR 1106L522R | 183 | 658 | 29323.1851 | 6797.2077 | 22525.9774 | 3036.9141 | 8384.6241 | 0.0067702 | 0.001501 | 1.3642 | 15.6897 | 1303 | 9.9712e-05 | 2483 | 0 | 0 | 1.8871 | 1274 | 0
Central Coast | 227 | 42 | 83.9053 | 171 | 156.0836 | 16 | 5.1348e-05 | 0.066432 | 12.1741 | 9.5096 | 26.8622 | 0.60064 | 1.102 | 6.2563 | 1 | 3.4112e-06 | 0.0004098 | 0.24561 | 0.53757 | {35A821AF-CADB-4929-9F1D-038A70D8EFD3} | 83252106 | PAUL SWEET 2106 | 12828 | 36.9874 | -121.949 | PAUL SWEET 210612828 | 156 | 462 | 28182.328 | 8000.0514 | 20182.2766 | 1804.684 | 3092.1649 | 0.0065567 | 0.00082157 | 1.9977 | 10.6875 | 930 | 5.4579e-05 | 2484 | 0 | 0 | 1.1214 | 662 | 0
North Coast | 1354 | 6 | 9.6812 | 27 | 18.8984 | 5 | 5.1266e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0.010619 | 1.291 | 1 | 3.4057e-06 | 0 | 0.22222 | 0.51227 | {1983F28A-08C9-48B3-9CC8-597EC6A45F0E} | 192431108 | HARRIS 1108 | 4674 | 40.7798 | -124.1445 | HARRIS 11084674 | 250 | 1059 | 56377.1915 | 13045.0322 | 43332.1593 | 465.5681 | 953.6292 | 0 | 0.00025633 | 1.6135 | 5.4 | 2896 | 1.7028e-05 | 2485 | 0 | 0 | 0.28929 | 1821 | 0
North Coast | 2779 | 152 | 363.8317 | 207 | 389.8293 | 38 | 6.3626e-05 | 0.055942 | 12.5536 | 43.2555 | 164.868 | 10.0005 | 5.1892 | 15.7344 | 1.5809 | 3.4045e-06 | 0.0005504 | 0.7343 | 0.93331 | {D0082608-F94E-4A4E-A9EF-A114F6AAC5C3} | 42271104 | COTATI 1104 | circuit_breaker | 38.3095 | -122.7318 | COTATI 1104circuit_breaker | 210 | 326 | 29191.1107 | 12365.6799 | 16825.4308 | 5446.6395 | 4892.6221 | 0.020915 | 0.0024178 | 2.3936 | 5.4474 | 737 | 0.00012937 | 2486 | 0 | 0 | 3.3844 | 508 | 0
Central Coast | 3318 | 6 | 9.4799 | 10 | 12.1451 | 2 | 5.1149e-05 | 0.066432 | 0.27215 | 0.079653 | 0.00080561 | 6.1215e-07 | 0 | 0.099115 | 1 | 3.3979e-06 | 1.8196e-05 | 0.6 | 0.78056 | {1EECCE5A-2560-4A1B-BCA1-BF5B03357FA1} | 83371107 | SARATOGA 1107 | circuit_breaker | 37.2811 | -122.0151 | SARATOGA 1107circuit_breaker | 325 | 1042 | 61567.5674 | 15770.6513 | 45796.9161 | 273.8424 | 631.6017 | 3.6392e-05 | 0.0001023 | 1.58 | 5 | 2644 | 6.7959e-06 | 2487 | 0 | 0 | 0.17016 | 988 | 0
Bay Area | 5179 | 28 | 55.7486 | 63 | 77.8927 | 8 | 5.1018e-05 | 0.066431 | 2.8878 | 2.4219 | 8.0804 | 0.035575 | 0 | 0 | 0 | 3.3892e-06 | 0.00010995 | 0.44444 | 0.71571 | {D5713EAC-4361-483E-B20A-724A36C5F247} | 14671101 | SOBRANTE 1101 | 42914 | 37.8928 | -122.1697 | SOBRANTE 110142914 | 96 | 379 | 27308.6593 | 6646.8405 | 20661.8188 | 755.7626 | 1581.9622 | 0.00087959 | 0.00040815 | 1.991 | 7.875 | 1802 | 2.7113e-05 | 2488 | 0 | 0 | 0.46961 | 2704 | 0
Central Valley | 8718 | 2 | 2.7172 | 3 | 3.1442 | 2 | 5.1016e-05 | 0.066432 | 2.8335 | 48.7293 | 530.3801 | 7.4075 | 0 | 0.81084 | 1 | 3.3891e-06 | 0.00011826 | 0.66667 | 0.86418 | {96EF7A8C-C5F4-4169-B851-BA4324B1FDB9} | 254432102 | COARSEGOLD 2102 | 383092 | 37.3087 | -119.5844 | COARSEGOLD 2102383092 | 27 | 1 | 620.6322 | 613.1926 | 7.4396 | 613.1926 | 7.4396 | 0.00023651 | 0.00010203 | 1.3586 | 1.5 | 1754 | 6.7782e-06 | 2489 | 0 | 0 | 0.38102 | 746 | 0
Bay Area | 4698 | 34 | 106.968 | 59 | 119.9811 | 6 | 5.0334e-05 | 0.068551 | 0.12561 | 139.5438 | 381.8267 | 0.058659 | 0.098083 | 10.0169 | 1.0059 | 3.3781e-06 | 2.5287e-05 | 0.57627 | 0.89154 | {2371EFC2-B46C-4698-931C-537DFFB0D5A5} | 14341103 | VALLEY VIEW 1103 | P160 | 37.9667 | -122.3058 | VALLEY VIEW 1103P160 | 236 | 1152 | 59568.8823 | 11104.7995 | 48464.0828 | 868.2348 | 0 | 0.00015172 | 0.000302 | 3.1461 | 9.8333 | 2532 | 2.0269e-05 | 2490 | 0 | 0 | 0.5395 | 2808 | 0
Bay Area | 959 | 197 | 391.6389 | 523 | 590.3431 | 34 | 5.5249e-05 | 0.060944 | 5.5825 | 5.712 | 13.5697 | 0.18629 | 0.38953 | 1.5137 | 1.2942 | 3.3298e-06 | 0.0001552 | 0.37667 | 0.66341 | {0C454A4D-2638-47F8-A6A3-CB153585DC8C} | 13090402 | BRYANT 0402 | circuit_breaker | 37.8765 | -122.1796 | BRYANT 0402circuit_breaker | 212 | 813 | 53799.5825 | 12542.5322 | 41257.0503 | 3304.7718 | 9503.4695 | 0.0052768 | 0.0018785 | 1.988 | 15.3824 | 1564 | 0.00011321 | 2491 | 0 | 0 | 2.0535 | 2710 | 0
Bay Area | 7330 | 36 | 48.5895 | 69 | 67.5334 | 7 | 5.0115e-05 | 0.066431 | 66.1707 | 44.7437 | 166.3602 | 12.7131 | 1.4608 | 11.2105 | 1.0057 | 3.3292e-06 | 0.0013019 | 0.52174 | 0.71949 | {92F6E341-F0BC-4716-8F01-EF905EEF4BF1} | 14161102 | ROSSMOOR 1102 | circuit_breaker | 37.8653 | -122.0805 | ROSSMOOR 1102circuit_breaker | 37 | 10 | 2518.1697 | 2145.2785 | 372.8912 | 400.2166 | 0 | 0.009113 | 0.0003508 | 1.3497 | 9.8571 | 294 | 2.3304e-05 | 2492 | 0 | 0 | 0.24868 | 1201 | 0
North Coast | 9058 | 3 | 8.5595 | 9 | 11.2217 | 3 | 4.988e-05 | 0.066432 | 0.21489 | 0.33974 | 0.44501 | 0.00025039 | 0 | 0.1045 | 1 | 3.3136e-06 | 8.7338e-06 | 0.33333 | 0.76276 | {E2438D63-9836-48BB-91BE-1736CBE6A21A} | 43361104 | HIGHLANDS 1104 | 84640 | 38.9359 | -122.6186 | HIGHLANDS 110484640 | 42 | 17 | 2519.028 | 1219.5259 | 1299.5021 | 569.7278 | 106.4988 | 2.6201e-05 | 0.00014964 | 2.8532 | 3 | 2801 | 9.9409e-06 | 2493 | 0 | 0 | 0.35401 | 2089 | 0
Central Valley | 346 | 472 | 672.4307 | 973 | 860.2019 | 135 | 5.1602e-05 | 0.063479 | 17.9327 | 74.3957 | 472.3731 | 40.566 | 5.1641 | 24.0177 | 1.2268 | 3.2962e-06 | 0.00044244 | 0.4851 | 0.78171 | {B8932F39-9144-47B8-8698-4C980B6BF57A} | 163351702 | CURTIS 1702 | 10940 | 37.9883 | -120.2831 | CURTIS 170210940 | 239 | 414 | 42693.4236 | 17011.7556 | 25681.668 | 13795.9366 | 20161.0379 | 0.05973 | 0.0069662 | 1.4246 | 7.2074 | 878 | 0.00044499 | 2494 | 0 | 0 | 8.5724 | 2831 | 0
Central Coast | 7676 | 439 | 880.0426 | 1286 | 1370.769 | 86 | 5.0987e-05 | 0.064114 | 0.78568 | 3.1029 | 18.5488 | 0.43978 | 0.026949 | 0.50033 | 1.0116 | 3.2934e-06 | 4.5921e-05 | 0.34137 | 0.64201 | {01343684-2E22-4CD1-B45D-70EFDFE53735} | 83371107 | SARATOGA 1107 | 5696 | 37.2552 | -122.0274 | SARATOGA 11075696 | 222 | 310 | 26313.3305 | 9783.8788 | 16529.4517 | 8008.7281 | 12826.0284 | 0.0039492 | 0.0043849 | 2.0047 | 14.9535 | 2275 | 0.00028323 | 2495 | 0 | 0 | 4.9764 | 604 | 0
Bay Area | 2119 | 699 | 1554.3832 | 1787 | 2203.8462 | 144 | 5.6848e-05 | 0.057666 | 2.0031 | 2.5996 | 7.7765 | 0.065687 | 0.33285 | 1.6818 | 1.4722 | 3.2578e-06 | 8.5339e-05 | 0.39116 | 0.7053 | {2F07459D-47C1-4462-B0ED-65839CB76ED4} | 14671102 | SOBRANTE 1102 | L510R | 37.9063 | -122.1529 | SOBRANTE 1102L510R | 296 | 669 | 44770.848 | 15693.2972 | 29077.5508 | 14977.7338 | 28369.6805 | 0.012289 | 0.0081861 | 2.2237 | 12.4097 | 1944 | 0.00046912 | 2496 | 0 | 0 | 9.3067 | 2693 | 0
North Coast | 2117 | 83 | 159.3695 | 496 | 269.9737 | 71 | 4.8923e-05 | 0.066432 | 0.56786 | 0.78627 | 2.0088 | 0.01704 | 0.0043001 | 0.090206 | 0.47887 | 3.2501e-06 | 3.8327e-05 | 0.16734 | 0.59032 | {EC0CBAAC-D25D-4166-8326-CC1A005227F9} | 43361104 | HIGHLANDS 1104 | circuit_breaker | 38.937 | -122.6091 | HIGHLANDS 1104circuit_breaker | 248 | 617 | 44096.0597 | 13342.2829 | 30753.7768 | 7426.3873 | 20046.973 | 0.0027212 | 0.0034736 | 1.9201 | 6.9859 | 2358 | 0.00023075 | 2497 | 0 | 0 | 4.6145 | 1213 | 0
Central Valley | 1297 | 96 | 137.4595 | 431 | 323.2273 | 54 | 5.6687e-05 | 0.05782 | 9.7513 | 8.0823 | 16.5392 | 0.30743 | 0.3733 | 3.5038 | 1.4815 | 3.2486e-06 | 0.00028174 | 0.22274 | 0.42527 | {52FB3514-9C62-49DD-A158-2A9A7CF95D5B} | 163781701 | PEORIA 1701 | 3186 | 37.8621 | -120.2265 | PEORIA 17013186 | 253 | 756 | 47996.3252 | 15920.2864 | 32076.0387 | 15920.2864 | 32076.0387 | 0.015214 | 0.0030611 | 1.4319 | 7.9815 | 1171 | 0.00017543 | 2498 | 0 | 0 | 9.8924 | 1124 | 0
Bay Area | 421 | 661 | 1377.512 | 1360 | 1749.1254 | 120 | 5.4334e-05 | 0.062003 | 1.2899 | 2.0027 | 7.2378 | 0.056406 | 0.7304 | 5.9285 | 1.2122 | 3.2484e-06 | 6.032e-05 | 0.48603 | 0.78754 | {66A7CBF7-CC15-453E-8CD9-FF5746466C31} | 14671102 | SOBRANTE 1102 | L520R | 37.9064 | -122.1519 | SOBRANTE 1102L520R | 263 | 498 | 33440.9335 | 12086.0128 | 21354.9207 | 11876.5417 | 21020.2948 | 0.0072384 | 0.0065201 | 2.084 | 11.3333 | 2137 | 0.00038981 | 2499 | 0 | 0 | 7.3797 | 2144 | 0
Central Coast | 2012 | 3 | 3.8318 | 18 | 11.788 | 3 | 4.8612e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2294e-06 | 2.2576e-05 | 0.16667 | 0.32506 | {8811ADA4-0D4D-4B1D-A0EC-DFD7E2D2F011} | 83771102 | VASONA 1102 | circuit_breaker | 37.254 | -121.9662 | VASONA 1102circuit_breaker | 578 | 1509 | 86892.9615 | 24792.446 | 62100.5155 | 282.6401 | 296.6694 | 6.7729e-05 | 0.00014583 | 1.2773 | 6 | 2573 | 9.6881e-06 | 2500 | 0 | 0 | 0.17562 | 1893 | 0
Central Coast | 6033 | 357 | 973.6192 | 538 | 1082.8591 | 44 | 4.842e-05 | 0.066721 | 4.3201 | 58.5881 | 468.7185 | 9.3141 | 0.1611 | 3.3794 | 1.0123 | 3.2246e-06 | 0.00012106 | 0.66357 | 0.89912 | {07CA7935-70B1-4CBA-B069-3C5BAF9F4438} | 182291102 | HATTON 1102 | 2010 | 36.506 | -121.936 | HATTON 11022010 | 96 | 140 | 12325.9614 | 6466.4829 | 5859.4785 | 6466.4829 | 5859.4785 | 0.0053264 | 0.0021305 | 2.7272 | 12.2273 | 1744 | 0.00014188 | 2501 | 0 | 0 | 4.0181 | 510 | 0
North Coast | 4496 | 56 | 110.0776 | 69 | 116.0331 | 21 | 4.8254e-05 | 0.066431 | 6.4089 | 19.1416 | 39.5267 | 0.43771 | 3.3607 | 12.0234 | 1.0015 | 3.2055e-06 | 0.00013341 | 0.81159 | 0.94867 | {B13BE392-390E-4E3B-A432-5336348FF9E8} | 42271104 | COTATI 1104 | 426 | 38.3265 | -122.7095 | COTATI 1104426 | 105 | 263 | 20085.5549 | 6253.9916 | 13831.5634 | 3056.6341 | 4201.2071 | 0.0028016 | 0.0010133 | 1.9657 | 3.2857 | 1681 | 6.7316e-05 | 2502 | 0 | 0 | 1.8993 | 51 | 0
Bay Area | 1202 | 26 | 77.0496 | 132 | 140.2369 | 13 | 5.0243e-05 | 0.061322 | 1.2314 | 1.2851 | 6.2755 | 0.025409 | 2.2 | 5.2607 | 1.3079 | 3.2021e-06 | 5.3877e-05 | 0.19697 | 0.54942 | {14C57C49-3FAA-493A-A967-CDA87ADFA83B} | 13801103 | MORAGA 1103 | 81146 | 37.8431 | -122.1459 | MORAGA 110381146 | 181 | 442 | 31772.0157 | 9024.5516 | 22747.464 | 1121.0612 | 4869.5574 | 0.0007004 | 0.00065316 | 2.9634 | 10.1538 | 2206 | 4.1627e-05 | 2503 | 0 | 0 | 0.69659 | 2178 | 0
Bay Area | 8711 | 13 | 27.7746 | 112 | 63.1497 | 13 | 4.8087e-05 | 0.066432 | 2.2206 | 4.9218 | 21.9312 | 0.077051 | 1.4946 | 4.6504 | 1 | 3.1945e-06 | 7.5273e-05 | 0.11607 | 0.43982 | {6C96515F-B6CE-4B5E-91AB-166552C2F0C4} | 13532224 | LAKEWOOD 2224 | 568670 | 37.8676 | -122.0459 | LAKEWOOD 2224568670 | 50 | 43 | 6583.5758 | 4298.0796 | 2285.4962 | 1334.4522 | 1233.4773 | 0.00097855 | 0.00062513 | 2.1365 | 8.6154 | 2018 | 4.1529e-05 | 2504 | 0 | 0 | 0.82919 | 2268 | 0
Bay Area | 1136 | 5 | 17.7576 | 29 | 30.5867 | 4 | 4.8078e-05 | 0.066431 | 2.9859 | 6.9585 | 14.3877 | 0.075972 | 0.42146 | 0.17793 | 1 | 3.1938e-06 | 0.00011617 | 0.17241 | 0.58057 | {3479FEFA-1861-4D8C-A938-95A0471F292B} | 13801105 | MORAGA 1105 | 8354 | 37.82 | -122.122 | MORAGA 11058354 | 69 | 246 | 17339.3845 | 4982.0059 | 12357.3786 | 320.2661 | 528.2862 | 0.00046468 | 0.00019231 | 3.5515 | 7.25 | 1769 | 1.2775e-05 | 2505 | 0 | 0 | 0.199 | 1726 | 0
Bay Area | 2507 | 3 | 4.8406 | 32 | 19.5204 | 6 | 3.8282e-05 | 0.091864 | 2.0392 | 2.0162 | 3.1737 | 0.012848 | 0.42662 | 10.186 | 0.83407 | 3.1846e-06 | 4.6385e-05 | 0.09375 | 0.24798 | {61CE2DCB-0D53-494B-8C34-3F4D665DD273} | 13432207 | FAIRVIEW 2207 | P148 | 38.0562 | -122.2169 | FAIRVIEW 2207P148 | 154 | 879 | 38818.4823 | 7362.5215 | 31455.9608 | 1241.4753 | 3160.2007 | 0.00027831 | 0.00022969 | 1.6135 | 5.3333 | 2272 | 1.9108e-05 | 2506 | 0 | 0 | 0.77142 | 652 | 0
Bay Area | 522 | 6 | 6.7555 | 8 | 7.9261 | 3 | 4.7902e-05 | 0.066431 | 8.7393 | 10.6343 | 36.576 | 0.32087 | 0.0014749 | 1.0949 | 1 | 3.1822e-06 | 0.00018372 | 0.75 | 0.85231 | {466136A5-5029-445B-8434-F48A32643962} | 42011109 | SAN RAFAEL 1109 | 418 | 37.9912 | -122.5094 | SAN RAFAEL 1109418 | 234 | 1121 | 71378.7742 | 19644.7624 | 51734.0118 | 8200.6281 | 5549.2493 | 0.00055115 | 0.00014371 | 1.1259 | 2.6667 | 1469 | 9.5465e-06 | 2507 | 0 | 0 | 5.0956 | 1259 | 0
Central Coast | 7461 | 33 | 122.416 | 41 | 126.958 | 6 | 4.77e-05 | 0.066432 | 3.5076 | 9.3406 | 22.6297 | 0.079375 | 0.066372 | 0.93754 | 1 | 3.1688e-06 | 6.7568e-05 | 0.80488 | 0.96422 | {95DA73C9-4DB4-4C31-AFD8-C43A5BC36425} | 182381101 | DOLAN ROAD 1101 | 22158 | 36.7999 | -121.6992 | DOLAN ROAD 110122158 | 281 | 472 | 48156.5512 | 18873.0319 | 29283.5193 | 274.4783 | 465.3061 | 0.00040541 | 0.0002862 | 3.7096 | 6.8333 | 2074 | 1.9013e-05 | 2508 | 0 | 0 | 0.17055 | 1776 | 0
Bay Area | 1469 | 130 | 243.5913 | 782 | 604.2826 | 35 | 4.6828e-05 | 0.066431 | 0.55541 | 0.25055 | 0.83175 | 0.0045716 | 0.25891 | 0.31831 | 0.8 | 3.1109e-06 | 3.6517e-05 | 0.16624 | 0.40311 | {14F4E9ED-4B21-4FDE-817D-55ADC93A3192} | 42011101 | SAN RAFAEL 1101 | circuit_breaker | 37.9708 | -122.5268 | SAN RAFAEL 1101circuit_breaker | 184 | 659 | 31974.9702 | 6823.6578 | 25151.3124 | 3967.8905 | 15454.6274 | 0.0012781 | 0.001639 | 1.8738 | 22.3429 | 2380 | 0.00010888 | 2509 | 0 | 0 | 2.4655 | 2731 | 0
Central Coast | 1253 | 463 | 935.4878 | 2519 | 2177.8672 | 191 | 4.6217e-05 | 0.066432 | 2.636 | 9.0714 | 39.1069 | 0.14696 | 0.51572 | 5.5549 | 0.92169 | 3.0703e-06 | 8.6909e-05 | 0.1838 | 0.42954 | {F9DF48B9-C722-406C-B401-60189B57E89A} | 82021107 | LOS GATOS 1107 | circuit_breaker | 37.2262 | -121.9773 | LOS GATOS 1107circuit_breaker | 396 | 762 | 61099.6228 | 25321.013 | 35778.6098 | 24420.9564 | 35026.4523 | 0.0166 | 0.0088274 | 2.0205 | 13.1885 | 1931 | 0.00058642 | 2510 | 0 | 0 | 15.1745 | 2265 | 0
Bay Area | 7941 | 1 | 1.2277 | 1 | 1.2277 | 1 | 4.6165e-05 | 0.066431 | 0.13957 | 0.22239 | 0.0054679 | 7.7125e-07 | 0 | 0.031416 | 1 | 3.0668e-06 | 6.4433e-06 | 1 | 1 | {2C2CFF8C-6FFC-491F-805A-E0EE63DF4C2A} | 42481105 |  | 1943 | 38.097 | -122.588 | 1943 | 26 | 75 | 6396.4345 | 1959.963 | 4436.4715 | 1959.963 | 4436.4715 | 6.4433e-06 | 4.6165e-05 | 1.2277 | 1 | 2834 | 3.0668e-06 | 2511 | 0 | 0 | 1.2179 | 2890 | 0
Bay Area | 4226 | 3 | 4.0758 | 28 | 19.4 | 8 | 4.6152e-05 | 0.066431 |  |  |  |  | 6.0113 | 41.6972 | 1.0669 | 3.0659e-06 | 4.6152e-05 | 0.10714 | 0.21009 | {3B8D2573-46CC-4384-8812-825E9555364D} | 42211104 | NOVATO 1104 | 1282 | 38.1164 | -122.5632 | NOVATO 11041282 | 120 | 144 | 17488.2796 | 7339.7437 | 10148.5359 | 722.7771 | 907.2047 | 0.00036921 | 0.00036921 | 1.3586 | 3.5 | 2274 | 2.4527e-05 | 2512 | 0 | 0 | 0.44911 | 2712 | 0
Central Coast | 7585 | 49 | 102.1617 | 494 | 369.7352 | 45 | 4.5998e-05 | 0.066997 | 0.037498 | 0.17353 | 0.057242 | 2.989e-06 | 0.70585 | 5.2862 | 1.0049 | 3.0645e-06 | 2.4711e-05 | 0.09919 | 0.27631 | {3FC7657A-E97F-4835-8F9A-E34BACD9F92C} | 83371115 | SARATOGA 1115 | LC20 | 37.294 | -122.0324 | SARATOGA 1115LC20 | 135 | 383 | 22682.2858 | 7847.8028 | 14834.483 | 4697.8741 | 2754.2127 | 0.001112 | 0.0020699 | 2.0849 | 10.9778 | 2539 | 0.0001379 | 2513 | 0 | 0 | 2.9191 | 260 | 0
Bay Area | 7080 | 5 | 10.8346 | 96 | 63.8018 | 11 | 4.1376e-05 | 0.071056 | 0.064395 | 0.12798 | 0.046564 | 2.0259e-06 | 0.55853 | 7.1683 | 1 | 3.0249e-06 | 1.8087e-05 | 0.052083 | 0.16982 | {C6807FEA-40B3-41BE-80F1-095A0F67FBA5} | 14091108 | CASTRO VALLEY 1108 | MR273 | 37.6978 | -122.0278 | CASTRO VALLEY 1108MR273 | 22 | 26 | 2646.4262 | 1166.5861 | 1479.8401 | 1166.5861 | 1479.8401 | 0.00019896 | 0.00045514 | 2.1669 | 8.7273 | 2649 | 3.3274e-05 | 2514 | 0 | 0 | 0.72488 | 2272 | 0
Bay Area | 3454 | 139 | 438.03 | 312 | 536.9411 | 22 | 4.5442e-05 | 0.066431 | 4.3985 | 2.6847 | 6.8205 | 0.1427 | 1.1443 | 2.8214 | 1 | 3.0188e-06 | 0.00015681 | 0.44551 | 0.81579 | {14CA8224-5AC7-4834-81C3-26558D7F85B9} | 12101104 | OAKLAND K 1104 | 432850 | 37.826 | -122.207 | OAKLAND K 1104432850 | 55 | 129 | 6808.9734 | 1972.5088 | 4836.4646 | 1972.5088 | 4836.4646 | 0.0034499 | 0.00099972 | 3.1513 | 14.1818 | 1557 | 6.6413e-05 | 2515 | 0 | 0 | 1.2257 | 2596 | 0
Central Coast | 1701 | 45 | 90.118 | 250 | 207.723 | 25 | 4.5361e-05 | 0.066432 | 3.2726 | 2.4798 | 6.5341 | 0.091405 | 0.032301 | 0.44505 | 0.28 | 3.0134e-06 | 0.00012616 | 0.18 | 0.43384 | {168FAC6E-221A-4D80-AD26-79821278B765} | 82021101 | LOS GATOS 1101 | circuit_breaker | 37.2263 | -121.9776 | LOS GATOS 1101circuit_breaker | 145 | 505 | 28538.0456 | 6310.1881 | 22227.8575 | 2776.4398 | 11430.3244 | 0.0031539 | 0.001134 | 2.0026 | 10 | 1720 | 7.5336e-05 | 2516 | 0 | 0 | 1.7252 | 2350 | 0
Central Coast | 4981 | 2 | 5.6282 | 4 | 6.5397 | 2 | 2.2693e-05 | 0.12365 | 12.7207 | 118.11 | 527.3902 | 2.9184 | 0.37611 | 7.9517 | 1 | 2.9943e-06 | 0.00034692 | 0.5 | 0.86062 | {A0154153-BF56-4706-9955-FEBD0CFAAAA7} | 182951101 | FOOTHILL 1101 | circuit_breaker | 35.2862 | -120.7061 | FOOTHILL 1101circuit_breaker | 192 | 171 | 47278.0836 | 35204.2801 | 12073.8035 | 18495.1348 | 7447.7525 | 0.00069384 | 4.5385e-05 | 2.8141 | 2 | 1018 | 5.9886e-06 | 2517 | 0 | 0 | 11.4923 | 1418 | 0
Bay Area | 2962 | 227 | 457.5817 | 1005 | 898.3202 | 80 | 4.5005e-05 | 0.066431 | 0.64263 | 0.38009 | 1.4895 | 0.014532 | 0.74248 | 1.0512 | 0.8125 | 2.9897e-06 | 4.0888e-05 | 0.22587 | 0.50937 | {946048CE-AA9C-41AF-93CE-2A93327AB590} | 42011101 | SAN RAFAEL 1101 | 494 | 37.9634 | -122.5217 | SAN RAFAEL 1101494 | 253 | 1121 | 62068.4903 | 14793.4066 | 47275.0836 | 8677.8794 | 28513.3315 | 0.003271 | 0.0036004 | 2.0158 | 12.5625 | 2331 | 0.00023918 | 2518 | 0 | 0 | 5.3922 | 2509 | 0
Bay Area | 7223 | 104 | 172.8864 | 325 | 299.2943 | 44 | 4.4965e-05 | 0.066431 | 1.725 | 4.0568 | 9.405 | 0.10806 | 3.2833 | 14.0254 | 1.0042 | 2.9871e-06 | 5.0955e-05 | 0.32 | 0.57765 | {F91156C0-E294-4BD1-9245-277084BD5819} | 42481104 | IGNACIO 1104 | 450582 | 38.1046 | -122.5132 | IGNACIO 1104450582 | 88 | 132 | 14523.4719 | 6790.6191 | 7732.8529 | 4879.3488 | 7154.4209 | 0.002242 | 0.0019785 | 1.6624 | 7.3864 | 2224 | 0.00013143 | 2519 | 0 | 0 | 3.0319 | 2162 | 0
Bay Area | 4303 | 17 | 44.1101 | 37 | 53.5497 | 11 | 4.459e-05 | 0.066431 |  |  |  |  | 0.44449 | 0.16506 | 1 | 2.9622e-06 | 4.459e-05 | 0.45946 | 0.82372 | {73B969AA-9422-4313-8799-666FFF6134B7} | 42011105 | SAN RAFAEL 1105 | 344 | 37.976 | -122.4898 | SAN RAFAEL 1105344 | 199 | 1009 | 64707.8649 | 12052.7047 | 52655.1602 | 796.0448 | 5540.5998 | 0.00049049 | 0.00049049 | 2.5947 | 3.3636 | 2286 | 3.2584e-05 | 2520 | 0 | 0 | 0.49464 | 2755 | 0
Bay Area | 5127 | 10 | 27.8546 | 26 | 37.2819 | 3 | 4.4178e-05 | 0.066431 | 1.2884 | 1.3071 | 2.2818 | 0.016202 | 0 | 0 | 0 | 2.9348e-06 | 4.9388e-05 | 0.38462 | 0.74713 | {BA67EE88-1E6D-48B2-9DBA-46721926CAE7} | 42011105 | SAN RAFAEL 1105 | circuit_breaker | 37.9708 | -122.527 | SAN RAFAEL 1105circuit_breaker | 292 | 791 | 52260.1431 | 15578.3001 | 36681.843 | 373.6826 | 480.8512 | 0.00014817 | 0.00013253 | 2.7855 | 8.6667 | 2235 | 8.8044e-06 | 2521 | 0 | 0 | 0.2322 | 2735 | 0
Bay Area | 1380 | 40 | 65.0485 | 151 | 132.067 | 18 | 4.3646e-05 | 0.066431 | 0.14167 | 0.22239 | 0.0032982 | 4.6726e-07 | 0.73107 | 2.2578 | 1 | 2.8995e-06 | 4.1773e-05 | 0.2649 | 0.49254 | {CDB467EB-0C7C-4750-A7F9-34F28A41CB6F} | 42011106 | SAN RAFAEL 1106 | 1230 | 37.982 | -122.5234 | SAN RAFAEL 11061230 | 170 | 734 | 44027.4042 | 9947.7927 | 34079.6116 | 1200.481 | 4807.1942 | 0.00075191 | 0.00078563 | 1.6262 | 8.3889 | 2314 | 5.219e-05 | 2522 | 0 | 0 | 0.74594 | 2292 | 0
Central Coast | 5252 | 521 | 1100.0922 | 980 | 1379.8823 | 121 | 4.3342e-05 | 0.066852 | 1.8331 | 125.4752 | 1341.6557 | 0.81254 | 0.51247 | 10.8804 | 0.96879 | 2.8847e-06 | 4.8395e-05 | 0.53163 | 0.79724 | {C7A22305-CC6A-494A-88D7-7F9AE8676071} | 182291101 | HATTON 1101 | 37088 | 36.5464 | -121.8985 | HATTON 110137088 | 225 | 540 | 44588.8325 | 18049.2001 | 26539.6324 | 10725.9565 | 16541.7626 | 0.0058558 | 0.0052444 | 2.1115 | 8.0992 | 2243 | 0.00034905 | 2523 | 0 | 0 | 6.6648 | 1171 | 0
Central Coast | 5428 | 33 | 44.3985 | 118 | 95.5125 | 24 | 4.1983e-05 | 0.067491 | 2.5033 | 98.2754 | 556.4046 | 1.3249 | 1.6449 | 15.1278 | 1.0026 | 2.8314e-06 | 7.9472e-05 | 0.27966 | 0.46484 | {D3A9B0CE-EEFF-4BC6-8121-8BA08D5105E9} | 182371111 | LAURELES 1111 | 6617 | 36.4027 | -121.6573 | LAURELES 11116617 | 17 | 79 | 6234.4064 | 2923.677 | 3310.7294 | 2923.677 | 3310.7294 | 0.0019073 | 0.0010076 | 1.3454 | 4.9167 | 1987 | 6.7954e-05 | 2524 | 0 | 0 | 1.8167 | 960 | 0
Central Coast | 6433 | 68 | 200.5837 | 125 | 234.8583 | 26 | 3.4178e-05 | 0.087952 | 15.9472 | 85.3295 | 399.9291 | 23.7205 | 1.2028 | 17.0987 | 1.0368 | 2.8314e-06 | 0.00024347 | 0.544 | 0.85406 | {1F7CD2D0-886C-4D05-8112-AF25ABC480A2} | 182371112 | LAURELES 1112 | 438 | 36.4967 | -121.7313 | LAURELES 1112438 | 85 | 115 | 15791.681 | 9219.1151 | 6572.566 | 7535.0705 | 3480.3802 | 0.0063302 | 0.00088862 | 2.9498 | 4.8077 | 1268 | 7.3616e-05 | 2525 | 0 | 0 | 4.6821 | 1967 | 0
Bay Area | 761 | 41 | 138.5155 | 50 | 142.0378 | 6 | 3.9104e-05 | 0.07279 |  |  |  |  | 0.3632 | 8.6485 | 1.0136 | 2.828e-06 | 3.9104e-05 | 0.82 | 0.9752 | {EC3F19B1-655E-438D-8AA0-F3D32FED5878} | 22811104 | PACIFICA 1104 | circuit_breaker | 37.5947 | -122.4889 | PACIFICA 1104circuit_breaker | 106 | 816 | 46900.1113 | 6746.3425 | 40153.7688 | 1298.4065 | 978.3386 | 0.00023463 | 0.00023463 | 3.3784 | 8.3333 | 2355 | 1.6968e-05 | 2526 | 0 | 0 | 0.80679 | 2723 | 0
Central Coast | 2563 | 5 | 9.6463 | 38 | 28.4337 | 4 | 4.25e-05 | 0.066432 | 0.03011 | 0.55599 | 2.4707 | 0.00014878 | 0.79646 | 1.9397 | 1 | 2.8233e-06 | 1.9114e-05 | 0.13158 | 0.33926 | {7B756F98-069D-434F-A340-DDF69576DD23} | 182961110 | PRUNEDALE 1110 | 3716 | 36.8245 | -121.6753 | PRUNEDALE 11103716 | 293 | 418 | 48519.2363 | 21171.4707 | 27347.7656 | 500.9046 | 134.7346 | 7.6457e-05 | 0.00017 | 1.9293 | 9.5 | 2631 | 1.1293e-05 | 2527 | 0 | 0 | 0.31125 | 249 | 0
Central Coast | 5620 | 9 | 13.8708 | 70 | 53.7771 | 4 | 4.2409e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0.59845 | 0.59137 | 1 | 2.8173e-06 | 3.084e-05 | 0.12857 | 0.25793 | {5627B063-B665-4EAB-9B4A-39C8A753C0BC} | 182721102 | SANTA YNEZ 1102 | 320270 | 34.5995 | -120.1277 | SANTA YNEZ 1102320270 | 69 | 121 | 10570.9207 | 4497.6237 | 6073.297 | 464.6996 | 249.4747 | 0.00012336 | 0.00016964 | 1.5412 | 17.5 | 2460 | 1.1269e-05 | 2528 | 0 | 0 | 0.28875 | 776 | 0
Central Coast | 1865 | 67 | 159.1159 | 149 | 200.1642 | 19 | 3.7239e-05 | 0.083833 | 0.895 | 14.1775 | 80.7755 | 0.59567 | 0.40626 | 6.0566 | 1.0016 | 2.8049e-06 | 3.5291e-05 | 0.44966 | 0.79493 | {BECA105B-BD3C-4CFB-85DF-E12EFB68ADA7} | 182742104 | SAN BENITO 2104 | circuit_breaker | 36.8688 | -121.5491 | SAN BENITO 2104circuit_breaker | 87 | 53 | 19055.6115 | 14632.0755 | 4423.536 | 7728.5813 | 2254.6308 | 0.00067054 | 0.00070754 | 2.3749 | 7.8421 | 2393 | 5.3294e-05 | 2529 | 0 | 0 | 4.8023 | 2201 | 0
Bay Area | 1765 | 86 | 263.4847 | 407 | 443.7472 | 27 | 4.218e-05 | 0.066432 | 9.5188 | 4.0478 | 10.2008 | 0.28199 | 1.5167 | 5.3708 | 1 | 2.8021e-06 | 0.00020249 | 0.2113 | 0.59377 | {C6EF6B66-22B5-4479-8720-12455A79DA2B} | 12061103 | BERKELEY F 1103 | BR110 | 37.8683 | -122.2562 | BERKELEY F 1103BR110 | 231 | 1029 | 45954.8517 | 9087.9005 | 36866.9512 | 3020.133 | 9193.4495 | 0.0054673 | 0.0011389 | 3.0638 | 15.0741 | 1404 | 7.5657e-05 | 2530 | 0 | 0 | 1.8766 | 2449 | 0
Central Coast | 8137 | 154 | 186.8199 | 627 | 442.051 | 33 | 3.5844e-05 | 0.077221 | 0.61681 | 25.4463 | 195.603 | 0.91843 | 0.32388 | 38.2813 | 1.1746 | 2.7998e-06 | 2.7305e-05 | 0.24561 | 0.42262 | {0BEAB8A7-7BDA-4BC0-A9A3-2A5F9C79AF1D} | 83481110 | STELLING 1110 | 2243 | 37.2777 | -122.1116 | STELLING 11102243 | 19 | 45 | 7731.4026 | 3010.4448 | 4720.9578 | 3010.4448 | 4720.9578 | 0.00090107 | 0.0011829 | 1.2131 | 19 | 2502 | 9.2395e-05 | 2531 | 0 | 0 | 1.8706 | 2180 | 0
Bay Area | 4136 | 23 | 35.7873 | 85 | 70.9707 | 12 | 4.2086e-05 | 0.066431 | 0.16667 | 0.15118 | 0.0024327 | 5.4635e-07 | 0.5826 | 1.2692 | 1 | 2.7958e-06 | 1.9701e-05 | 0.27059 | 0.50425 | {817C2475-7154-4157-877D-5C42AEE35A70} | 42011106 | SAN RAFAEL 1106 | 837 | 37.9876 | -122.5272 | SAN RAFAEL 1106837 | 42 | 155 | 9221.601 | 2472.1334 | 6749.4676 | 1084.0764 | 2450.774 | 0.00023642 | 0.00050503 | 1.556 | 7.0833 | 2615 | 3.355e-05 | 2532 | 0 | 0 | 0.67361 | 2233 | 0
Bay Area | 9946 | 31 | 57.4626 | 208 | 163.4648 | 14 | 3.2226e-05 | 0.085506 | 9.1162 | 30.079 | 120.1954 | 2.034 | 0.24858 | 25.1232 | 1.0997 | 2.794e-06 | 0.00015273 | 0.14904 | 0.35153 | {E1CFB432-A326-40CC-8BB1-1B7A06DF46E8} | 13801101 | MORAGA 1101 | 83424 | 37.8741 | -122.1869 | MORAGA 110183424 | 12 | 2 | 2619.5028 | 2600.0484 | 19.4544 | 2587.2467 | 19.4544 | 0.0021382 | 0.00045116 | 1.8536 | 14.8571 | 1576 | 3.9116e-05 | 2533 | 0 | 0 | 1.6076 | 1310 | 0
Central Coast | 2627 | 298 | 578.9892 | 1618 | 1356.5994 | 121 | 4.2035e-05 | 0.066432 | 2.5599 | 4.268 | 13.9823 | 0.074875 | 0.42803 | 1.9365 | 0.79811 | 2.7925e-06 | 7.5784e-05 | 0.18418 | 0.42679 | {2E2463B4-F331-472F-B632-0DB9F9C1E4AF} | 82021101 | LOS GATOS 1101 | LB40 | 37.2271 | -121.9666 | LOS GATOS 1101LB40 | 292 | 617 | 46820.6801 | 14924.9203 | 31895.7598 | 13423.6309 | 26545.6171 | 0.0091698 | 0.0050863 | 1.9429 | 13.3719 | 2013 | 0.00033789 | 2534 | 0 | 0 | 8.3411 | 1938 | 0
Central Valley | 9544 | 0 | 0 | 6 | 2.677 | 3 | 4.1985e-05 | 0.066432 | 2.0288 | 202.4264 | 975.8207 | 2.1272 | 0.071534 | 21.4708 | 1.0347 | 2.7892e-06 | 8.0457e-05 | 0 | 0 | {7D0477A1-3B70-4629-B0DA-1E96F8ADF8DC} | 163351703 | CURTIS 1703 | 49746 | 37.9653 | -120.3627 | CURTIS 170349746 | 6 | 1 | 632.3808 | 601.9007 | 30.4801 | 601.9007 | 30.4801 | 0.00024137 | 0.00012596 |  | 2 | 1979 | 8.3675e-06 | 2535 | 0 | 0 | 0.374 | 2229 | 0
North Coast | 6012 | 104 | 205.3 | 704 | 357.6836 | 83 | 4.1886e-05 | 0.066432 | 0.66146 | 0.77443 | 1.775 | 0.017736 | 2.1819e-16 | 1.5855e-15 | 5.4789e-15 | 2.7825e-06 | 3.7423e-05 | 0.14773 | 0.57397 | {05A2F271-E60C-4560-A544-2497E351C8FC} | 43361104 | HIGHLANDS 1104 | 48262 | 38.9395 | -122.6189 | HIGHLANDS 110448262 | 148 | 564 | 35426.5084 | 9974.1543 | 25452.3541 | 9900.0196 | 25297.0398 | 0.0031061 | 0.0034765 | 1.974 | 8.4819 | 2372 | 0.00023095 | 2536 | 0 | 0 | 6.1516 | 2583 | 0
Bay Area | 2118 | 1 | 1.6135 | 8 | 4.5144 | 2 | 4.1614e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0.48451 | 0.97732 | 1 | 2.7645e-06 | 0 | 0.125 | 0.35742 | {0052F236-02DD-4D59-831D-9E6CA4EBFC49} | 13532227 | LAKEWOOD 2227 | W503R | 37.9192 | -122.0371 | LAKEWOOD 2227W503R | 230 | 1036 | 58734.8644 | 12249.2617 | 46485.6027 | 121.8736 | 239.1504 | 0 | 8.3229e-05 | 1.6135 | 4 | 2902 | 5.529e-06 | 2537 | 0 | 0 | 0.075729 | 1783 | 0
Central Coast | 8050 | 54 | 189.6921 | 171 | 232.4975 | 21 | 3.308e-05 | 0.15544 | 1.6968 | 53.3948 | 315.0344 | 1.3166 | 2.922 | 21.0072 | 1.0858 | 2.7633e-06 | 4.4999e-05 | 0.31579 | 0.81589 | {4C9F3CAE-E991-4EA7-BCAB-BA03C4CEAE92} | 183011102 | MORRO BAY 1102 | circuit_breaker | 35.3752 | -120.855 | MORRO BAY 1102circuit_breaker | 65 | 111 | 13007.4844 | 8911.8848 | 4095.5997 | 5907.9517 | 995.491 | 0.00094498 | 0.00069468 | 3.5128 | 8.1429 | 2283 | 5.8029e-05 | 2538 | 0 | 0 | 3.671 | 2810 | 0
Central Coast | 4001 | 341 | 887.1003 | 810 | 1161.3384 | 82 | 3.3837e-05 | 0.10618 | 5.2217 | 22.4716 | 88.5134 | 1.88 | 2.134 | 22.2132 | 1.6184 | 2.762e-06 | 0.00010616 | 0.42099 | 0.76386 | {5E20B311-BB0A-4C97-B880-E9EFFB1FD21F} | 182371112 | LAURELES 1112 | 2142 | 36.4806 | -121.7292 | LAURELES 11122142 | 185 | 382 | 38205.8611 | 15527.4179 | 22678.4431 | 12390.3415 | 15542.7422 | 0.0087052 | 0.0027746 | 2.6015 | 9.878 | 1825 | 0.00022649 | 2539 | 0 | 0 | 7.699 | 1727 | 0
North Valley | 2588 | 228 | 303.3126 | 340 | 365.6929 | 45 | 2.2003e-05 | 0.14621 | 12.6194 | 151.8199 | 2972.7161 | 249.7908 | 1.1748 | 23.2362 | 1.2883 | 2.7554e-06 | 0.00020124 | 0.67059 | 0.82942 | {7BDDAA75-E6EC-4597-A704-7B9866E3D480} | 102551101 | EAST QUINCY 1101 | circuit_breaker | 39.9385 | -120.9107 | EAST QUINCY 1101circuit_breaker | 220 | 404 | 34494.17 | 12858.9233 | 21635.2467 | 4164.7046 | 7526.1674 | 0.0090558 | 0.00099012 | 1.3303 | 7.5556 | 1408 | 0.00012399 | 2540 | 0 | 0 | 2.5878 | 170 | 0
Central Coast | 8223 | 62 | 96.933 | 347 | 272.7391 | 28 | 4.118e-05 | 0.066432 | 1.3127 | 6.636 | 17.2922 | 0.05881 | 0.57238 | 4.5644 | 1.0002 | 2.7356e-06 | 4.0217e-05 | 0.17867 | 0.35541 | {851CDBBF-9DCD-4F7B-BBC9-AC14EA44A837} | 82021101 | LOS GATOS 1101 | 60052 | 37.2186 | -121.9525 | LOS GATOS 110160052 | 47 | 25 | 4623.0667 | 3109.1853 | 1513.8814 | 3109.1853 | 1513.8814 | 0.0011261 | 0.001153 | 1.5634 | 12.3929 | 2336 | 7.6598e-05 | 2541 | 0 | 0 | 1.932 | 144 | 0
Bay Area | 195 | 22 | 43.8829 | 47 | 56.2076 | 8 | 4.1092e-05 | 0.066432 | 4.1301 | 0.83025 | 2.2741 | 0.03145 | 0 | 0 | 0 | 2.7298e-06 | 0.0001091 | 0.46809 | 0.78073 | {B0F9DF73-E5FE-4D63-9A97-F698C647DBAA} | 13700401 | ARLINGTON 0401 | circuit_breaker | 37.8888 | -122.2729 | ARLINGTON 0401circuit_breaker | 123 | 914 | 43123.4648 | 6391.7678 | 36731.697 | 973.3919 | 4677.7507 | 0.00087281 | 0.00032873 | 1.9947 | 5.875 | 1807 | 2.1838e-05 | 2542 | 0 | 0 | 0.60484 | 1564 | 0
Central Coast | 2600 | 730 | 2688.4705 | 1268 | 3037.9448 | 84 | 4.1084e-05 | 0.066432 | 1.0269 | 0.9539 | 3.5846 | 0.022333 | 0.15231 | 0.15594 | 0.91667 | 2.7293e-06 | 4.3473e-05 | 0.57571 | 0.88496 | {1BFCD1F7-4819-470E-B6A4-C94657DF3551} | 183071101 | PERRY 1101 | V72 | 35.5505 | -121.0724 | PERRY 1101V72 | 266 | 906 | 53060.0769 | 14179.1577 | 38880.9192 | 9688.7012 | 30601.4913 | 0.0036517 | 0.0034511 | 3.6828 | 15.0952 | 2297 | 0.00022926 | 2543 | 0 | 0 | 6.0203 | 1733 | 0
Bay Area | 629 | 154 | 415.5496 | 579 | 647.7504 | 40 | 4.2103e-05 | 0.06311 | 4.8568 | 8.9039 | 132.1193 | 12.1814 | 0.5744 | 0.12169 | 0.975 | 2.7035e-06 | 0.00015864 | 0.26598 | 0.64153 | {8EF016F0-1EE5-4AEA-B654-4E375979814E} | 42031125 | ALTO 1125 | 935 | 37.8792 | -122.5383 | ALTO 1125935 | 94 | 402 | 23365.0536 | 5180.4035 | 18184.6501 | 5180.4035 | 18184.6501 | 0.0063456 | 0.0016841 | 2.6984 | 14.475 | 1549 | 0.00010814 | 2544 | 0 | 0 | 3.219 | 1318 | 0
Bay Area | 1961 | 14 | 38.4531 | 40 | 50.1975 | 9 | 4.0555e-05 | 0.066432 | 0.14601 | 0.1852 | 2.501 | 0.001795 | 3.2694 | 18.213 | 1.0401 | 2.6941e-06 | 2.5687e-05 | 0.35 | 0.76604 | {4C3B8436-25B4-4A62-8D40-AF9B1B8FB54A} | 13801103 | MORAGA 1103 | E510R | 37.8411 | -122.1419 | MORAGA 1103E510R | 145 | 478 | 33394.1093 | 9824.475 | 23569.6343 | 662.3347 | 970.6053 | 0.00023118 | 0.00036499 | 2.7467 | 4.4444 | 2523 | 2.4247e-05 | 2545 | 0 | 0 | 0.41156 | 1945 | 0
Central Coast | 7016 | 32 | 85.8559 | 125 | 136.6158 | 9 | 4.0494e-05 | 0.066432 | 0.14525 | 0.078703 | 0.00076723 | 3.1402e-07 | 0.00024582 | 0.63284 | 0.33382 | 2.6901e-06 | 3.108e-05 | 0.256 | 0.62845 | {91797B82-A1A4-4508-99A7-6356F1982129} | 83371107 | SARATOGA 1107 | 6867 | 37.2545 | -122.0332 | SARATOGA 11076867 | 22 | 92 | 5582.5847 | 1327.3586 | 4255.2261 | 985.9493 | 3348.1273 | 0.00027972 | 0.00036445 | 2.683 | 13.8889 | 2456 | 2.4211e-05 | 2546 | 0 | 0 | 0.61264 | 294 | 0
Bay Area | 4743 | 0 | 0 | 2 | 0.85406 | 1 | 4.0146e-05 | 0.066431 |  |  |  |  | 0 | 0.059071 | 1 | 2.667e-06 | 4.0146e-05 | 0 | 0 | {E1F2559F-5071-40B5-BFDE-D70EABF698BC} | 42481105 |  | 84764 | 38.0926 | -122.5694 | 84764 | 92 | 656 | 43607.9081 | 6974.5934 | 36633.3147 | 2403.7519 | 14020.6052 | 4.0146e-05 | 4.0146e-05 |  | 2 | 2338 | 2.667e-06 | 2547 | 0 | 0 | 1.4936 | 2198 | 0
Bay Area | 2072 | 1 | 1.6135 | 4 | 3.6528 | 1 | 4.011e-05 | 0.066432 |  |  |  |  | 0.97345 | 0.098009 | 1 | 2.6646e-06 | 4.011e-05 | 0.25 | 0.44172 | {E6DE5FA6-EF94-448F-BB17-EE24C05283D8} | 14091106 | CASTRO VALLEY 1106 | MR205 | 37.7059 | -122.0615 | CASTRO VALLEY 1106MR205 | 159 | 1132 | 54643.327 | 8740.8691 | 45902.4579 | 143.1328 | 1211.2623 | 4.011e-05 | 4.011e-05 | 1.6135 | 4 | 2339 | 2.6646e-06 | 2548 | 0 | 0 | 0.088939 | 2767 | 0
Central Coast | 2253 | 560 | 1034.1266 | 2140 | 1996.2592 | 139 | 4.3806e-05 | 0.060219 | 5.284 | 15.5673 | 41.9005 | 0.42721 | 0.69564 | 5.4687 | 1.3674 | 2.6568e-06 | 0.00014131 | 0.26168 | 0.51803 | {F252A13D-948A-43C3-954E-C03439B944E1} | 182371111 | LAURELES 1111 | 2028 | 36.4728 | -121.7178 | LAURELES 11112028 | 178 | 596 | 40716.3022 | 14061.7847 | 26654.5175 | 14048.0686 | 26654.5175 | 0.019642 | 0.0060891 | 1.8467 | 15.3957 | 1625 | 0.00036929 | 2549 | 0 | 0 | 8.7291 | 1971 | 0
Bay Area | 2216 | 67 | 165.3983 | 134 | 202.9303 | 20 | 4.1641e-05 | 0.06311 | 2.5622 | 5.1105 | 13.8538 | 0.086775 | 1.6176 | 4.1185 | 1.2023 | 2.6433e-06 | 6.9654e-05 | 0.5 | 0.81505 | {E6E0CE7A-9AFF-4A02-92C6-B06263224357} | 13532107 | LAKEWOOD 2107 | 38404 | 37.9253 | -122.0875 | LAKEWOOD 210738404 | 97 | 70 | 12705.3318 | 9331.7159 | 3373.6159 | 3768.6783 | 2459.9756 | 0.0013931 | 0.00083282 | 2.4686 | 6.7 | 2061 | 5.2865e-05 | 2550 | 0 | 0 | 2.3417 | 2145 | 0
North Coast | 4592 | 48 | 77.1523 | 167 | 111.2521 | 28 | 3.9203e-05 | 0.06734 | 3.7749 | 4.9209 | 12.7676 | 0.26389 | 1.3206 | 4.6032 | 1.0114 | 2.6352e-06 | 8.488e-05 | 0.28743 | 0.69349 | {33AF121E-F118-4B6E-94DA-FB39FA49A86E} | 43211101 | HARTLEY 1101 | 94178 | 39.0514 | -122.9372 | HARTLEY 110194178 | 120 | 258 | 17214.9349 | 6647.1964 | 10567.7385 | 3325.1898 | 2723.5185 | 0.0023766 | 0.0010977 | 1.6073 | 5.9643 | 1953 | 7.3787e-05 | 2551 | 0 | 0 | 2.0662 | 1022 | 0
Central Coast | 4949 | 1 | 1.246 | 11 | 6.6812 | 1 | 4.5948e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0 | 0.099336 | 1 | 3.0524e-06 | 0 | 0.090909 | 0.1865 | {A69D2BA4-3D74-416C-A5CD-5CA28C67DFB5} | 12840401 | RIDGE 0401 | circuit_breaker | 37.8851 | -122.255 | RIDGE 0401circuit_breaker | 82 | 520 | 25479.4182 | 4263.1331 | 21216.2852 | 4156.4129 | 20588.0897 | 0 | 4.5948e-05 | 1.246 | 11 | 2891 | 3.0524e-06 | 2552 | 0 | 0 | 2.5827 | 1106 | 0
Bay Area | 4949 | 124 | 266.5087 | 361 | 393.3428 | 36 | 3.9429e-05 | 0.066432 | 1.9073 | 0.6513 | 2.7669 | 0.021476 | 0.1207 | 0.072554 | 0.61111 | 2.6193e-06 | 5.9778e-05 | 0.34349 | 0.67755 | {A69D2BA4-3D74-416C-A5CD-5CA28C67DFB5} | 12840401 | RIDGE 0401 | circuit_breaker | 37.8851 | -122.255 | RIDGE 0401circuit_breaker | 82 | 520 | 25479.4182 | 4263.1331 | 21216.2852 | 4156.4129 | 20588.0897 | 0.002152 | 0.0014194 | 2.1493 | 10.0278 | 2144 | 9.4296e-05 | 2552 | 0 | 0 | 2.5827 | 2164 | 0
Central Coast | 6996 | 0 | 0 | 2 | 1.3595 | 1 | 3.9074e-05 | 0.066432 | 2.1275 | 1.2994 | 4.1713 | 0.033413 | 0.097345 | 0.0097345 | 1 | 2.5957e-06 | 8.3128e-05 | 0 | 0 | {98F44516-A7DA-4F88-98E1-7BF277BBBD67} | 182541101 | ATASCADERO 1101 | circuit_breaker | 35.4656 | -120.6715 | ATASCADERO 1101circuit_breaker | 65 | 319 | 17312.8724 | 3297.1528 | 14015.7196 | 491.5839 | 2605.6032 | 8.3128e-05 | 3.9074e-05 |  | 2 | 1963 | 2.5957e-06 | 2553 | 0 | 0 | 0.30546 | 221 | 0
North Coast | 1996 | 21 | 39.3853 | 95 | 62.0227 | 16 | 5.1543e-05 | 0.049824 | 1.4766 | 0.63116 | 1.0975 | 0.015335 | 1.0463e-14 | 5.2316e-16 | 1.5625 | 2.5936e-06 | 6.6791e-05 | 0.22105 | 0.63501 | {0343042E-9F65-47DD-BA69-5192F97A36BA} | 43351103 | LUCERNE 1103 | 1663 | 39.1233 | -122.8477 | LUCERNE 11031663 | 27 | 111 | 6206.6347 | 1947.6462 | 4258.9885 | 1947.6462 | 4258.9885 | 0.0010687 | 0.00082469 | 1.8755 | 5.9375 | 2079 | 4.1497e-05 | 2554 | 0 | 0 | 1.2102 | 364 | 0
Central Coast | 4378 | 76 | 150.5624 | 220 | 239.2486 | 29 | 3.3669e-05 | 0.080902 | 2.2885 | 2.1686 | 7.6254 | 0.077334 | 0.40601 | 5.108 | 0.96552 | 2.5817e-06 | 6.0095e-05 | 0.34545 | 0.62931 | {601835A0-060D-478B-8A86-7129055F5CF4} | 83242109 | MORGAN HILL 2109 | XR246 | 37.1237 | -121.641 | MORGAN HILL 2109XR246 | 224 | 243 | 23376.2637 | 10729.6078 | 12646.6559 | 4044.708 | 4691.5599 | 0.0017428 | 0.00097641 | 1.9811 | 7.5862 | 2140 | 7.487e-05 | 2555 | 0 | 0 | 2.5133 | 1992 | 0
Central Valley | 792 | 16 | 25.6248 | 100 | 68.8593 | 12 | 3.8761e-05 | 0.066432 | 2.8583 | 63.2426 | 666.4793 | 4.2418 | 0.29369 | 2.2202 | 1 | 2.575e-06 | 6.026e-05 | 0.16 | 0.37213 | {FB848303-D5D3-4EED-8986-7FB32C443F1F} | 163781701 | PEORIA 1701 | 9250 | 37.8373 | -120.2615 | PEORIA 17019250 | 93 | 93 | 19477.3758 | 13421.5992 | 6055.7767 | 13421.5992 | 6055.7767 | 0.00072312 | 0.00046514 | 1.6016 | 8.3333 | 2139 | 3.09e-05 | 2556 | 0 | 0 | 8.3398 | 1817 | 0
Bay Area | 4524 | 172 | 518.982 | 597 | 763.7843 | 36 | 4.1205e-05 | 0.060895 | 3.1279 | 1.4062 | 4.6784 | 0.050434 | 0.56837 | 1.5606 | 1.1389 | 2.5722e-06 | 8.9148e-05 | 0.28811 | 0.67949 | {61E67233-CD4F-4206-8138-63FBDA895D1D} | 12101104 | OAKLAND K 1104 | CR208 | 37.8279 | -122.2072 | OAKLAND K 1104CR208 | 60 | 458 | 23817.9544 | 3895.4111 | 19922.5434 | 3895.4111 | 19922.5434 | 0.0032093 | 0.0014834 | 3.0173 | 16.5833 | 1916 | 9.2599e-05 | 2557 | 0 | 0 | 2.4205 | 2612 | 0
Central Coast | 2952 | 193 | 641.4278 | 368 | 737.7188 | 36 | 3.8375e-05 | 0.066432 | 1.5841 | 1.7327 | 5.1616 | 0.033455 | 0.20188 | 0.40597 | 1 | 2.5493e-06 | 5.7224e-05 | 0.52446 | 0.86947 | {ACE1BC6A-035E-4494-A0B8-B5F90D3DC126} | 183071101 | PERRY 1101 | W52 | 35.5577 | -121.0774 | PERRY 1101W52 | 116 | 398 | 24081.7395 | 6677.88 | 17403.8595 | 4757.9409 | 14869.7219 | 0.0020601 | 0.0013815 | 3.3235 | 10.2222 | 2169 | 9.1775e-05 | 2558 | 0 | 0 | 2.9564 | 399 | 0
Central Coast | 1251 | 4 | 7.4993 | 33 | 20.9397 | 5 | 3.8239e-05 | 0.066432 | 20.7983 | 840.2064 | 2776.3416 | 66.1457 | 0.028319 | 0.014071 | 1 | 2.5403e-06 | 0.00031159 | 0.12121 | 0.35814 | {1B8DB8B3-1D13-4E12-A58F-43F8C34F8820} | 182721104 | SANTA YNEZ 1104 | Y30 | 34.6353 | -120.0891 | SANTA YNEZ 1104Y30 | 356 | 873 | 65202.251 | 21907.9147 | 43294.3363 | 984.7789 | 1028.1417 | 0.0015579 | 0.0001912 | 1.8748 | 6.6 | 1098 | 1.2702e-05 | 2559 | 0 | 0 | 0.61191 | 1588 | 0
Central Coast | 1173 | 256 | 920.4871 | 686 | 1200.2518 | 30 | 3.8005e-05 | 0.066432 | 1.2394 | 8.5621 | 18.0533 | 0.033978 | 0.12382 | 1.6378 | 1 | 2.5248e-06 | 4.5033e-05 | 0.37318 | 0.76691 | {DB34AA1E-C0F6-41DF-BFC5-43E5CD8E6B2B} | 182852204 | VIEJO 2204 | circuit_breaker | 36.5784 | -121.9081 | VIEJO 2204circuit_breaker | 113 | 189 | 14669.3383 | 6373.9064 | 8295.4319 | 3591.9838 | 780.1248 | 0.001351 | 0.0011402 | 3.5957 | 22.8667 | 2282 | 7.5743e-05 | 2560 | 0 | 0 | 2.232 | 1777 | 0
Bay Area | 1814 | 125 | 367.0919 | 284 | 452.4298 | 24 | 4.4758e-05 | 0.058127 | 0.076395 | 0.092977 | 0.05073 | 9.9907e-06 | 0.40954 | 0.47533 | 1.5 | 2.5237e-06 | 2.9467e-05 | 0.44014 | 0.81138 | {F8F75874-EBBE-4BAE-AEB7-B4201B2B809B} | 42031122 | ALTO 1122 | circuit_breaker | 37.8986 | -122.525 | ALTO 1122circuit_breaker | 80 | 257 | 21085.3392 | 5576.1236 | 15509.2157 | 3067.3601 | 9199.1511 | 0.0007072 | 0.0010742 | 2.9367 | 11.8333 | 2472 | 6.057e-05 | 2561 | 0 | 0 | 1.906 | 146 | 0
Central Coast | 6591 | 220 | 751.7578 | 357 | 820.3251 | 51 | 3.7831e-05 | 0.066931 | 1.0293 | 43.8834 | 158.9342 | 0.15321 | 1.0653 | 5.8361 | 1.0003 | 2.5218e-06 | 3.8256e-05 | 0.61625 | 0.91641 | {96F3BFFE-8B25-45FE-9E94-B3CC1506798D} | 182291102 | HATTON 1102 | 648928 | 36.5332 | -121.9152 | HATTON 1102648928 | 78 | 50 | 8783.1151 | 7661.8083 | 1121.3068 | 5792.882 | 993.354 | 0.0019511 | 0.0019294 | 3.4171 | 7 | 2360 | 0.00012861 | 2562 | 0 | 0 | 3.5995 | 2159 | 0
Bay Area | 5028 | 35 | 50.1267 | 74 | 70.5192 | 11 | 3.7883e-05 | 0.066432 | 0.09649 | 0.039193 | 0.023189 | 1.2696e-05 | 0.075422 | 0.45201 | 1 | 2.5166e-06 | 2.0571e-05 | 0.47297 | 0.71082 | {6816024C-0E2E-41A0-ACBC-61D5029F7695} | 12061105 | BERKELEY F 1105 | BR100 | 37.883 | -122.2663 | BERKELEY F 1105BR100 | 110 | 783 | 36358.4589 | 4175.3412 | 32183.1177 | 1156.966 | 6505.2272 | 0.00022628 | 0.00041671 | 1.4322 | 6.7273 | 2597 | 2.7683e-05 | 2563 | 0 | 0 | 0.71891 | 2641 | 0
Bay Area | 4062 | 16 | 26.7823 | 48 | 45.2942 | 8 | 3.7681e-05 | 0.066431 | 0 | 0 | 0 | 0 | 0 | 0.027793 | 1 | 2.5032e-06 | 2.7675e-05 | 0.33333 | 0.5913 | {B741A95F-002E-44D0-A60B-EBC8CDB18CCD} | 42011104 | SAN RAFAEL 1104 | 2651 | 37.999 | -122.5776 | SAN RAFAEL 11042651 | 16 | 133 | 7511.0197 | 1244.9562 | 6266.0634 | 1083.7544 | 4852.9809 | 0.0002214 | 0.00030145 | 1.6739 | 6 | 2497 | 2.0026e-05 | 2564 | 0 | 0 | 0.67341 | 2747 | 0
Bay Area | 5914 | 200 | 365.9298 | 543 | 551.8233 | 44 | 4.3669e-05 | 0.055863 | 1.7184 | 4.5746 | 16.22 | 0.22394 | 1.4656 | 11.4272 | 1.6559 | 2.497e-06 | 8.1107e-05 | 0.36832 | 0.66313 | {EEF03FEE-E315-4DF5-BC12-E5292370248B} | 42481104 | IGNACIO 1104 | 1290 | 38.0853 | -122.5364 | IGNACIO 11041290 | 227 | 377 | 37228.0609 | 18840.8428 | 18387.2181 | 5098.9497 | 7244.1898 | 0.0035687 | 0.0019215 | 1.8296 | 12.3409 | 1973 | 0.00010987 | 2565 | 0 | 0 | 3.1683 | 2013 | 0
Central Coast | 6914 | 339 | 1254.5606 | 465 | 1329.6849 | 43 | 3.8e-05 | 0.064887 | 0.79588 | 4.7677 | 10.9153 | 0.013934 | 0.0028972 | 0.81473 | 1.093 | 2.4773e-06 | 3.4715e-05 | 0.72903 | 0.9435 | {4DC9724F-62CE-4CE8-B9B2-FC8D42753B78} | 182852203 | VIEJO 2203 | circuit_breaker | 36.5784 | -121.9082 | VIEJO 2203circuit_breaker | 83 | 148 | 11813.8652 | 5468.3648 | 6345.5004 | 4363.1693 | 2444.4219 | 0.0014927 | 0.001634 | 3.7008 | 10.814 | 2401 | 0.00010652 | 2566 | 0 | 0 | 2.7111 | 2188 | 0
Bay Area | 2189 | 8 | 25.2156 | 12 | 27.8402 | 1 | 5.0986e-05 | 0.066431 | 0.00052635 | 0.22239 | 1.353 | 7.1215e-07 | 0.26991 | 18.4392 | 1 | 3.3871e-06 | 2.6836e-08 | 0.66667 | 0.90573 | {ED3D87A2-B26D-4CB8-8B3D-56CD442881C5} | 83432103 | HICKS 2103 | LB50 | 37.2216 | -121.9083 | HICKS 2103LB50 | 91 | 42 | 26450.5229 | 21326.6152 | 5123.9077 | 18634.0428 | 4468.185 | 2.6836e-08 | 5.0986e-05 | 3.152 | 12 | 2884 | 3.3871e-06 | 2567 | 0 | 0 | 11.5787 | 404 | 0
Central Coast | 2189 | 334 | 422.9901 | 1311 | 1032.2025 | 94 | 3.7074e-05 | 0.066431 | 0.77288 | 11.9276 | 38.3455 | 0.070852 | 0.32529 | 12.0889 | 0.99355 | 2.4629e-06 | 2.7679e-05 | 0.25477 | 0.40979 | {ED3D87A2-B26D-4CB8-8B3D-56CD442881C5} | 83432103 | HICKS 2103 | LB50 | 37.2216 | -121.9083 | HICKS 2103LB50 | 91 | 42 | 26450.5229 | 21326.6152 | 5123.9077 | 18634.0428 | 4468.185 | 0.0026018 | 0.0034849 | 1.2664 | 13.9468 | 2496 | 0.00023151 | 2567 | 0 | 0 | 11.5787 | 1838 | 0
Central Coast | 6805 | 960 | 3070.7398 | 1804 | 3581.4465 | 119 | 3.7658e-05 | 0.065315 | 1.8937 | 8.0732 | 16.6105 | 0.086724 | 0.30374 | 1.0861 | 1.0672 | 2.4661e-06 | 5.287e-05 | 0.53215 | 0.8574 | {A7511424-C0A7-4DC4-BAD6-B60505BBA431} | 182222103 | DEL MONTE 2103 | 2000 | 36.5851 | -121.8743 | DEL MONTE 21032000 | 182 | 122 | 19328.9978 | 14596.6085 | 4732.3893 | 14596.6085 | 4732.3893 | 0.0062916 | 0.0044813 | 3.1987 | 15.1597 | 2213 | 0.00029346 | 2568 | 0 | 0 | 9.0699 | 2279 | 0
Bay Area | 6923 | 244 | 524.3508 | 756 | 809.2481 | 33 | 3.6891e-05 | 0.066431 | 0.35536 | 1.4886 | 7.0077 | 0.019065 | 0.027586 | 0.16144 | 1 | 2.4507e-06 | 2.643e-05 | 0.32275 | 0.64795 | {C2F314B0-1B7A-4CC5-862B-042BD22A1A33} | 42031122 | ALTO 1122 | 65474 | 37.9126 | -122.5226 | ALTO 112265474 | 143 | 214 | 15827.669 | 5874.8397 | 9952.8293 | 4236.5189 | 7614.2458 | 0.0008722 | 0.0012174 | 2.149 | 22.9091 | 2511 | 8.0874e-05 | 2569 | 0 | 0 | 2.6324 | 2236 | 0
Central Coast | 8738 | 49 | 77.0078 | 305 | 223.7507 | 26 | 3.6539e-05 | 0.066432 | 0.80169 | 32.2249 | 100.4949 | 0.079952 | 0.45967 | 15.279 | 1.0514 | 2.4274e-06 | 3.2708e-05 | 0.16066 | 0.34417 | {10DE6DA0-CA5B-473A-800A-83AA9ED5A37C} | 182371111 | LAURELES 1111 | 6421 | 36.4545 | -121.6954 | LAURELES 11116421 | 24 | 23 | 3999.3276 | 2777.3682 | 1221.9594 | 2777.3682 | 1221.9594 | 0.00085041 | 0.00095002 | 1.5716 | 11.7308 | 2431 | 6.3112e-05 | 2570 | 0 | 0 | 1.7258 | 2072 | 0
Central Coast | 6965 | 3 | 3.814 | 23 | 13.676 | 6 | 8.6282e-06 | 0.30168 |  |  |  |  | 0.40007 | 60.1574 | 1.0527 | 2.4273e-06 | 8.6282e-06 | 0.13043 | 0.27888 | {D0772DC9-F8FF-4FD1-BF38-1CDC8034D04A} | 182082102 | LOS OSITOS 2102 | 7470 | 36.29 | -121.1966 | LOS OSITOS 21027470 | 218 | 203 | 48769.0899 | 43864.2595 | 4904.8303 | 6032.2925 | 457.2787 | 5.1769e-05 | 5.1769e-05 | 1.2713 | 3.8333 | 2803 | 1.4564e-05 | 2571 | 0 | 0 | 3.7483 | 2789 | 0
Central Coast | 2168 | 161 | 488.4578 | 381 | 624.6165 | 26 | 3.6446e-05 | 0.066432 | 2.0764 | 2.3725 | 6.6594 | 0.063008 | 0.26838 | 1.7611 | 1 | 2.4212e-06 | 5.9709e-05 | 0.42257 | 0.78201 | {38794799-8756-4269-B41E-6206BA101157} | 182222103 | DEL MONTE 2103 | 2654 | 36.5571 | -121.9039 | DEL MONTE 21032654 | 52 | 119 | 9601.523 | 2963.5999 | 6637.9232 | 2963.5999 | 6252.9116 | 0.0015524 | 0.0009476 | 3.0339 | 14.6538 | 2145 | 6.2951e-05 | 2572 | 0 | 0 | 1.8415 | 2508 | 0
Central Valley | 4487 | 1 | 1.945 | 4 | 3.4536 | 4 | 5.1232e-05 | 0.049824 | 21.5172 | 23.8087 | 56.343 | 1.2124 | 0.68584 | 1.5945 | 2 | 2.4142e-06 | 0.00033851 | 0.25 | 0.56317 | {CB8A5610-26AF-406C-A01C-6D3A6199376B} | 163781701 | PEORIA 1701 | 84318 | 37.8548 | -120.2069 | PEORIA 170184318 | 250 | 617 | 44791.1473 | 16239.9493 | 28551.198 | 16239.9493 | 28551.198 | 0.001354 | 0.00020493 | 1.945 | 1 | 1035 | 9.6569e-06 | 2573 | 0 | 0 | 10.091 | 1172 | 0
Bay Area | 2419 | 46 | 144.2152 | 129 | 187.5023 | 10 | 3.6269e-05 | 0.066432 | 4.5033 | 1.0624 | 3.8241 | 0.023902 | 0 | 3.4207e-16 | 4.5475e-14 | 2.4094e-06 | 9.2081e-05 | 0.35659 | 0.76914 | {34B1FBA6-E642-41FD-8BD2-ADAC657BB906} | 12061105 | BERKELEY F 1105 | circuit_breaker | 37.8725 | -122.278 | BERKELEY F 1105circuit_breaker | 317 | 1837 | 73102.0537 | 12969.5675 | 60132.4862 | 1678.7947 | 5887.9164 | 0.00092081 | 0.00036269 | 3.1351 | 12.9 | 1895 | 2.4094e-05 | 2574 | 0 | 0 | 1.0432 | 1335 | 0
Central Coast | 2103 | 10 | 21.503 | 27 | 32.6111 | 4 | 3.6257e-05 | 0.066432 | 0.1526 | 0.22239 | 0.0011503 | 1.7808e-07 | 0.44912 | 0.47931 | 1 | 2.4086e-06 | 1.9975e-05 | 0.37037 | 0.65938 | {0AC2A538-D1DE-4BF0-89DD-0FB685A31962} | 83371105 | SARATOGA 1105 | circuit_breaker | 37.281 | -122.0151 | SARATOGA 1105circuit_breaker | 178 | 442 | 28405.9242 | 8763.0473 | 19642.8769 | 514.5552 | 353.5658 | 7.9898e-05 | 0.00014503 | 2.1503 | 6.75 | 2607 | 9.6344e-06 | 2575 | 0 | 0 | 0.31973 | 2664 | 0
Bay Area | 1605 | 21 | 32.4011 | 51 | 47.858 | 7 | 3.6192e-05 | 0.066432 | 0.41997 | 0.21098 | 1.2572 | 0.0027828 | 0 | 0 | 0 | 2.4043e-06 | 2.3113e-05 | 0.41176 | 0.67703 | {2F486204-BB5C-45FC-9D31-305D5B069E7B} | 12101101 | OAKLAND K 1101 | CR172 | 37.8506 | -122.2437 | OAKLAND K 1101CR172 | 63 | 557 | 23757.4928 | 3350.0951 | 20407.3977 | 572.872 | 4578.4239 | 0.00016179 | 0.00025334 | 1.5429 | 7.2857 | 2564 | 1.683e-05 | 2576 | 0 | 0 | 0.35597 | 2787 | 0
Central Coast | 5885 | 232 | 754.5545 | 357 | 827.4904 | 38 | 3.4953e-05 | 0.06844 | 0.39144 | 2.4802 | 9.1302 | 0.042719 | 0.056649 | 0.62594 | 0.73684 | 2.4023e-06 | 2.8156e-05 | 0.64986 | 0.91186 | {743AA0A1-467D-436E-BBF0-31F00EC2544E} | 183071101 | PERRY 1101 | W12 | 35.5488 | -121.0891 | PERRY 1101W12 | 183 | 677 | 37403.451 | 10253.6179 | 27149.8331 | 5951.1009 | 16275.189 | 0.0010699 | 0.0013282 | 3.2524 | 9.3947 | 2489 | 9.1287e-05 | 2577 | 0 | 0 | 3.6978 | 1810 | 0
Central Coast | 3182 | 1 | 1.246 | 20 | 18.2155 | 1 | 3.9475e-05 | 0.066432 |  |  |  |  | 0 | 0 | 0 | 2.6224e-06 | 3.9475e-05 | 0.05 | 0.068404 | {BAD456A1-64C0-4C58-9244-4CB0B49EFF5E} | 12101101 | OAKLAND K 1101 | circuit_breaker | 37.8479 | -122.2291 | OAKLAND K 1101circuit_breaker | 105 | 514 | 24145.6711 | 3826.4615 | 20319.2096 | 559.1884 | 538.1577 | 3.9475e-05 | 3.9475e-05 | 1.246 | 20 | 2350 | 2.6224e-06 | 2578 | 0 | 0 | 0.34746 | 2037 | 0
Bay Area | 3182 | 23 | 39.3608 | 63 | 61.9364 | 8 | 3.5745e-05 | 0.066432 | 0.02669 | 0.021216 | 0.15619 | 0.00030255 | 0.12694 | 0.014353 | 0.125 | 2.3746e-06 | 2.2353e-05 | 0.36508 | 0.6355 | {BAD456A1-64C0-4C58-9244-4CB0B49EFF5E} | 12101101 | OAKLAND K 1101 | circuit_breaker | 37.8479 | -122.2291 | OAKLAND K 1101circuit_breaker | 105 | 514 | 24145.6711 | 3826.4615 | 20319.2096 | 559.1884 | 538.1577 | 0.00017882 | 0.00028596 | 1.7113 | 7.875 | 2575 | 1.8997e-05 | 2578 | 0 | 0 | 0.34746 | 2091 | 0
Central Coast | 1942 | 544 | 1379.1615 | 1522 | 1984.0127 | 134 | 4.1969e-05 | 0.056021 | 3.3433 | 10.797 | 32.2571 | 0.31264 | 0.87604 | 5.7819 | 1.6279 | 2.4021e-06 | 9.7172e-05 | 0.35742 | 0.69514 | {2A037456-E4D6-4133-B41E-0D0ADCC9AA87} | 182371112 | LAURELES 1112 | 68454 | 36.4832 | -121.7379 | LAURELES 111268454 | 239 | 585 | 52868.6546 | 17632.0929 | 35236.5616 | 12588.4111 | 28343.7768 | 0.013021 | 0.0056239 | 2.5352 | 11.3582 | 1868 | 0.00032188 | 2579 | 0 | 0 | 7.8221 | 1051 | 0
Bay Area | 3378 | 18 | 36.0641 | 51 | 52.0243 | 3 | 3.6131e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4003e-06 | 2.5728e-05 | 0.35294 | 0.69322 | {3AC71A95-3DF9-478B-ACCE-8AC300269CEA} | 12101101 | OAKLAND K 1101 | CR178 | 37.8541 | -122.2365 | OAKLAND K 1101CR178 | 21 | 20 | 1455.1302 | 529.8862 | 925.244 | 529.8862 | 925.244 | 7.7185e-05 | 0.00010839 | 2.0036 | 17 | 2521 | 7.2008e-06 | 2580 | 0 | 0 | 0.32926 | 2725 | 0
Bay Area | 6006 | 8 | 30.4084 | 10 | 31.3199 | 3 | 3.6116e-05 | 0.066432 | 0.93463 | 0.36467 | 0.88931 | 0.0069552 | 0 | 0 | 0 | 2.3993e-06 | 3.4547e-05 | 0.8 | 0.9709 | {8F0A48D9-A322-4FA2-98F5-9BA99B0B225E} | 13380401 | WOOD 0401 | circuit_breaker | 37.8265 | -122.2162 | WOOD 0401circuit_breaker | 109 | 780 | 37630.7224 | 5314.1763 | 32316.5461 | 198.8033 | 1735.2481 | 0.00010364 | 0.00010835 | 3.8011 | 3.3333 | 2407 | 7.1979e-06 | 2581 | 0 | 0 | 0.12353 | 2794 | 0
Central Coast | 4742 | 95 | 236.2774 | 341 | 375.7164 | 31 | 3.5928e-05 | 0.066432 | 0.11131 | 0.12918 | 0.031907 | 6.4809e-06 | 0.14288 | 0.93941 | 0.96774 | 2.3868e-06 | 2.3882e-05 | 0.27859 | 0.62887 | {D8FA53F1-4F5D-4A3B-A2ED-DEA75FD0EA10} | 83371103 | SARATOGA 1103 | LC16 | 37.264 | -122.0333 | SARATOGA 1103LC16 | 157 | 453 | 28092.8404 | 8155.3412 | 19937.4992 | 6890.8055 | 15856.2825 | 0.00074035 | 0.0011138 | 2.4871 | 11 | 2545 | 7.399e-05 | 2582 | 0 | 0 | 4.2817 | 2608 | 0
North Valley | 4640 | 2 | 1.9572 | 6 | 3.7802 | 1 | 3.5725e-05 | 0.066431 |  |  |  |  | 0 | 0.033628 | 1 | 2.3732e-06 | 3.5725e-05 | 0.33333 | 0.51776 | {D7294FE2-5C1D-4A22-BE67-3B019C568346} | 102911102 | WYANDOTTE 1102 | 13914 | 39.5152 | -121.5462 | WYANDOTTE 110213914 | 62 | 225 | 10400.1409 | 2833.7582 | 7566.3827 | 43.1117 | 230.59 | 3.5725e-05 | 3.5725e-05 | 0.97861 | 6 | 2389 | 2.3732e-06 | 2583 | 0 | 0 | 0.026788 | 963 | 0
Central Coast | 1695 | 9 | 24.2817 | 30 | 36.9951 | 4 | 4.4787e-05 | 0.049824 | 0.63324 | 1.3343 | 6.8035 | 0.0088668 | 0.85619 | 2.1412 | 2 | 2.3725e-06 | 3.5202e-05 | 0.3 | 0.65635 | {F70B7F2A-1768-433D-8A85-4CF42DC91D6A} | 182371112 | LAURELES 1112 | circuit_breaker | 36.4778 | -121.7273 | LAURELES 1112circuit_breaker | 83 | 213 | 12189.7088 | 3818.0634 | 8371.6454 | 334.2836 | 682.9316 | 0.00014081 | 0.00017915 | 2.698 | 7.5 | 2395 | 9.49e-06 | 2584 | 0 | 0 | 0.20771 | 372 | 0
North Coast | 5355 | 11 | 21.6414 | 23 | 27.1713 | 9 | 3.5513e-05 | 0.066432 | 0.51291 | 0.30648 | 0.33968 | 0.00046193 | 0.21632 | 0.26814 | 1 | 2.3592e-06 | 2.3527e-05 | 0.47826 | 0.79648 | {4767D54A-43F6-4C91-ADC4-A02B76D81A7F} | 43311108 | KONOCTI 1108 | 4037 | 38.9547 | -122.7114 | KONOCTI 11084037 | 38 | 177 | 11230.176 | 2770.5432 | 8459.6328 | 1312.7691 | 2877.0872 | 0.00021174 | 0.00031962 | 1.9674 | 2.5556 | 2553 | 2.1233e-05 | 2585 | 0 | 0 | 0.81572 | 2668 | 0
Central Valley | 7396 | 165 | 238.4071 | 446 | 362.6358 | 23 | 8.0327e-05 | 0.028883 | 8.201 | 9.1539 | 20.001 | 0.29869 | 0.4213 | 4.2586 | 3.1739 | 2.3539e-06 | 0.00029862 | 0.36996 | 0.65743 | {90FD8044-FB92-466A-9C47-A3D72A063397} | 163351702 | CURTIS 1702 | S2123 | 38.0176 | -120.2696 | CURTIS 1702S2123 | 52 | 203 | 12796.176 | 2995.553 | 9800.623 | 2995.553 | 9800.623 | 0.0068683 | 0.0018475 | 1.4449 | 19.3913 | 1127 | 5.4139e-05 | 2586 | 0 | 0 | 1.8613 | 1028 | 0
Sierra | 9978 | 3 | 3.6831 | 5 | 4.4694 | 1 | 3.535e-05 | 0.066432 |  |  |  |  | 0.11504 | 5.4201 | 1 | 2.3484e-06 | 3.535e-05 | 0.6 | 0.82409 | {0F59AF2F-5869-40D3-A6B5-13E6D7B47101} | 153612105 | CLARKSVILLE 2105 | 51478 | 38.6556 | -121.0151 | CLARKSVILLE 210551478 | 6 | 0 | 90.198 | 90.198 | 0 | 81.0541 | 0 | 3.535e-05 | 3.535e-05 | 1.2277 | 5 | 2392 | 2.3484e-06 | 2587 | 0 | 0 | 0.050365 | 766 | 0
Central Coast | 7069 | 65 | 198.1761 | 137 | 234.2847 | 6 | 3.4948e-05 | 0.066432 | 1.6735 | 1.5568 | 5.9039 | 0.0098805 | 0.54867 | 0.93997 | 1 | 2.3216e-06 | 3.8902e-05 | 0.47445 | 0.84588 | {8CF433ED-5D30-4AF4-B399-FAE6BF4CEC35} | 182222103 | DEL MONTE 2103 | 42226 | 36.5834 | -121.8569 | DEL MONTE 210342226 | 74 | 298 | 21669.4281 | 4032.3201 | 17637.108 | 616.5067 | 691.6034 | 0.00023341 | 0.00020969 | 3.0489 | 22.8333 | 2356 | 1.393e-05 | 2588 | 0 | 0 | 0.38308 | 153 | 0
Central Coast | 3919 | 184 | 374.6776 | 428 | 509.4524 | 50 | 3.4887e-05 | 0.066432 | 2.9048 | 16.1329 | 40.4461 | 0.57645 | 1.0962 | 7.3505 | 1.0023 | 2.3176e-06 | 5.5239e-05 | 0.42991 | 0.73545 | {E78B7822-B984-42F9-85C5-3ACE6CA5BD79} | 182381101 | DOLAN ROAD 1101 | 3012 | 36.8005 | -121.7216 | DOLAN ROAD 11013012 | 387 | 556 | 66093.496 | 33632.5258 | 32460.9702 | 5235.0908 | 5289.7599 | 0.0027619 | 0.0017443 | 2.0363 | 8.56 | 2189 | 0.00011588 | 2589 | 0 | 0 | 3.2529 | 2601 | 0
Bay Area | 4148 | 1138 | 2064.5297 | 2130 | 2593.992 | 179 | 3.4959e-05 | 0.066471 | 1.1478 | 29.3051 | 112.045 | 0.28409 | 0.37647 | 10.1419 | 1.0498 | 2.3163e-06 | 3.9624e-05 | 0.53427 | 0.79589 | {65F40270-9C1F-4F03-A2E4-A1FA52E4266C} | 24101103 | HALF MOON BAY 1103 | 8894 | 37.25 | -122.3601 | HALF MOON BAY 11038894 | 164 | 190 | 36973.666 | 18161.0155 | 18812.6505 | 18016.3153 | 18662.9325 | 0.0070926 | 0.0062576 | 1.8142 | 11.8994 | 2348 | 0.00041461 | 2590 | 0 | 0 | 11.1948 | 2207 | 0
Bay Area | 3718 | 257 | 961.0573 | 348 | 1009.7325 | 46 | 3.516e-05 | 0.064987 | 0.40024 | 0.92696 | 4.0363 | 0.0086545 | 0.52077 | 1.5915 | 1.0455 | 2.2938e-06 | 2.7004e-05 | 0.73851 | 0.95179 | {198D5285-6472-4132-B2C3-DA39131D8819} | 12541106 | OAKLAND X 1106 | CR006 | 37.7953 | -122.1576 | OAKLAND X 1106CR006 | 99 | 303 | 23862.7145 | 5810.9825 | 18051.732 | 5810.9825 | 18051.732 | 0.0012422 | 0.0016174 | 3.7395 | 7.5652 | 2505 | 0.00010551 | 2591 | 0 | 0 | 3.6108 | 2807 | 0
North Coast | 2738 | 33 | 67.7688 | 301 | 129.996 | 57 | 3.7267e-05 | 0.059785 | 0.0027129 | 0.011952 | 0.032835 | 2.675e-06 | 0.1264 | 1.3062 | 1.2982 | 2.286e-06 | 2.3122e-05 | 0.10963 | 0.52131 | {12D5CC7A-B2CA-4EEF-8AD4-C988E70110AA} | 43361102 | HIGHLANDS 1102 | circuit_breaker | 38.937 | -122.6088 | HIGHLANDS 1102circuit_breaker | 149 | 494 | 38272.4432 | 11973.99 | 26298.4532 | 11973.99 | 26298.4532 | 0.001318 | 0.0021242 | 2.0536 | 5.2807 | 2563 | 0.0001303 | 2592 | 0 | 0 | 7.4403 | 684 | 0
Central Coast | 1269 | 5 | 20.2454 | 9 | 22.9106 | 1 | 3.4075e-05 | 0.066432 | 4.2713 | 1.5793 | 3.8117 | 0.096126 | 0.0022124 | 0.38872 | 1 | 2.2637e-06 | 0.00014555 | 0.55556 | 0.88367 | {3C76847C-A8C4-4A3F-9423-53C131CDED01} | 182040405 | CARMEL 0405 | circuit_breaker | 36.5609 | -121.9197 | CARMEL 0405circuit_breaker | 107 | 759 | 24924.6515 | 4990.6238 | 19934.0277 | 58.7067 | 236.937 | 0.00014555 | 3.4075e-05 | 4.0491 | 9 | 1617 | 2.2637e-06 | 2593 | 0 | 0 | 0.036479 | 401 | 0
Central Coast | 1597 | 6 | 18.179 | 6 | 18.179 | 1 | 3.3893e-05 | 0.066432 | 7.0259 | 13.7885 | 36.6128 | 0.25724 | 0.042035 | 0.12832 | 1 | 2.2516e-06 | 0.00023813 | 1 | 1 | {81973749-CAB3-49C6-B105-0C3D389524EF} | 182631105 | SAN LUIS OBISPO 1105 | circuit_breaker | 35.2616 | -120.635 | SAN LUIS OBISPO 1105circuit_breaker | 116 | 548 | 29878.4871 | 5631.4463 | 24247.0408 | 67.4906 | 164.2514 | 0.00023813 | 3.3893e-05 | 3.0298 | 6 | 1282 | 2.2516e-06 | 2594 | 0 | 0 | 0.041937 | 195 | 0
Bay Area | 9756 | 0 | 0 | 5 | 3.3989 | 1 | 3.3702e-05 | 0.066431 |  |  |  |  | 0 | 0.004646 | 1 | 2.2389e-06 | 3.3702e-05 | 0 | 0 | {FCF2B093-ADAA-4F58-8EAB-58BC1ECF0ACE} | 42011109 | SAN RAFAEL 1109 | 2213 | 38.009 | -122.5194 | SAN RAFAEL 11092213 | 8 | 38 | 2524.7316 | 689.8513 | 1834.8802 | 666.4301 | 1371.0567 | 3.3702e-05 | 3.3702e-05 |  | 5 | 2417 | 2.2389e-06 | 2595 | 0 | 0 | 0.4141 | 2282 | 0
Bay Area | 4978 | 180 | 589.5288 | 804 | 917.1137 | 43 | 3.3695e-05 | 0.066432 | 1.0176 | 1.3154 | 4.0829 | 0.0097541 | 0.2629 | 0.98287 | 1 | 2.2384e-06 | 3.4618e-05 | 0.22388 | 0.64281 | {BFA33FCB-E1C5-4ED0-AC2E-104CE6FA2AEF} | 13681112 | EDES 1112 | CR312 | 37.7629 | -122.1407 | EDES 1112CR312 | 91 | 273 | 19922.0899 | 5884.5739 | 14037.516 | 5725.9493 | 13564.0635 | 0.0014886 | 0.0014489 | 3.2752 | 18.6977 | 2405 | 9.6253e-05 | 2596 | 0 | 0 | 3.5579 | 2771 | 0
Central Coast | 4057 | 206 | 661.2141 | 244 | 682.1921 | 12 | 3.3593e-05 | 0.066432 |  |  |  |  | 0 | 2.0081 | 0.83444 | 2.2317e-06 | 3.3593e-05 | 0.84426 | 0.96925 | {DA30E872-22F6-4600-80CD-C659254182C9} | 182852202 | VIEJO 2202 | 2606 | 36.5767 | -121.9507 | VIEJO 22022606 | 143 | 147 | 11330.9614 | 5106.4294 | 6224.532 | 1139.9059 | 2095.7364 | 0.00040312 | 0.00040312 | 3.2098 | 20.3333 | 2420 | 2.678e-05 | 2597 | 0 | 0 | 0.7083 | 1796 | 0
North Valley | 4565 | 125 | 162.5326 | 443 | 327.9876 | 72 | 3.3332e-05 | 0.066432 | 4.2796 | 12.6601 | 42.387 | 0.42495 | 0.54529 | 2.4472 | 0.82298 | 2.2143e-06 | 0.00010536 | 0.28217 | 0.49554 | {1877F2B7-68C6-4031-8C15-9D4F18F07556} | 103311101 | BURNEY 1102 | 45984 | 40.8795 | -121.6742 | BURNEY 110245984 | 182 | 496 | 26208.4965 | 7772.5624 | 18435.9341 | 7772.5624 | 18435.9341 | 0.0075862 | 0.0023999 | 1.3003 | 6.1528 | 1830 | 0.00015943 | 2598 | 0 | 0 | 4.8296 | 88 | 0
Bay Area | 6508 | 78 | 125.2677 | 290 | 255.502 | 25 | 3.3306e-05 | 0.066432 | 0.1205 | 0.079024 | 0.028928 | 7.1021e-06 | 0.36487 | 0.61541 | 1 | 2.2126e-06 | 1.877e-05 | 0.26897 | 0.49028 | {6E19C0A5-86DD-49E4-909F-112A4E9E5B6E} | 24080402 | EMERALD LAKE 0402 | 8858 | 37.4667 | -122.2733 | EMERALD LAKE 04028858 | 54 | 206 | 11168.7113 | 3073.6226 | 8095.0888 | 3073.6226 | 8095.0888 | 0.00046925 | 0.00083264 | 1.606 | 11.6 | 2637 | 5.5314e-05 | 2599 | 0 | 0 | 1.9099 | 392 | 0
Bay Area | 6087 | 11 | 23.3758 | 22 | 29.0611 | 7 | 3.3186e-05 | 0.066431 |  |  |  |  | 1.4722 | 1.504 | 1 | 2.2046e-06 | 3.3186e-05 | 0.5 | 0.80437 | {1A3DCF6A-D8D9-4366-A0A3-6456AFF85AD5} | 42011101 | SAN RAFAEL 1101 | 310 | 37.9778 | -122.5527 | SAN RAFAEL 1101310 | 94 | 698 | 36448.5475 | 5721.8801 | 30726.6673 | 395.8699 | 2734.0525 | 0.0002323 | 0.0002323 | 2.1251 | 3.1429 | 2422 | 1.5432e-05 | 2600 | 0 | 0 | 0.24598 | 2043 | 0
Bay Area | 6509 | 7 | 26.9186 | 11 | 28.7129 | 3 | 3.3069e-05 | 0.066432 | 0.25742 | 0.074131 | 0.00049751 | 3.8421e-07 | 0 | 0.10044 | 1 | 2.1969e-06 | 1.0302e-05 | 0.63636 | 0.93751 | {30A0D7F0-FF87-4B5E-B98B-6A0711429281} | 24181104 | SAN CARLOS 1104 | 75210 | 37.4841 | -122.2822 | SAN CARLOS 110475210 | 25 | 37 | 2689.3408 | 618.926 | 2070.4148 | 618.926 | 2070.4148 | 3.0905e-05 | 9.9208e-05 | 3.8455 | 3.6667 | 2782 | 6.5906e-06 | 2601 | 0 | 0 | 0.38458 | 2879 | 0
Bay Area | 5893 | 191 | 573.0355 | 618 | 824.8323 | 54 | 3.2975e-05 | 0.066432 | 0.25177 | 0.18447 | 0.92548 | 0.0029604 | 0.22341 | 0.35503 | 0.96296 | 2.1906e-06 | 2.3996e-05 | 0.30906 | 0.69473 | {ADC13D99-F0AF-402E-9F6C-0B91201427B3} | 24060404 | CAROLANDS 0404 | 9024 | 37.5445 | -122.3644 | CAROLANDS 04049024 | 124 | 268 | 17564.6639 | 6139.8959 | 11424.768 | 5539.7321 | 10964.7715 | 0.0012958 | 0.0017806 | 3.0002 | 11.4444 | 2544 | 0.00011829 | 2602 | 0 | 0 | 3.4422 | 2690 | 0
Bay Area | 5151 | 4 | 15.7305 | 21 | 22.875 | 3 | 3.2939e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0.11283 | 0.011283 | 1 | 2.1882e-06 | 1.2469e-05 | 0.19048 | 0.68767 | {659FD2EB-053C-425F-AF25-D9C58353B44F} | 13432207 | FAIRVIEW 2207 | circuit_breaker | 38.0161 | -122.1164 | FAIRVIEW 2207circuit_breaker | 130 | 142 | 12994.0229 | 8087.0352 | 4906.9877 | 267.7583 | 537.7626 | 3.7407e-05 | 9.8816e-05 | 3.9326 | 7 | 2754 | 6.5645e-06 | 2603 | 0 | 0 | 0.16638 | 2848 | 0
Bay Area | 8536 | 152 | 337.6321 | 477 | 511.6739 | 25 | 3.4424e-05 | 0.063775 | 0.43887 | 0.16411 | 0.93408 | 0.003119 | 0 | 0.042091 | 0.6 | 2.187e-06 | 2.3766e-05 | 0.31866 | 0.65986 | {834BDB9E-9A30-4D9F-8424-760E012D4EC8} | 12101103 | OAKLAND K 1103 | CR422 | 37.8412 | -122.2247 | OAKLAND K 1103CR422 | 54 | 240 | 13508.1509 | 3299.6109 | 10208.54 | 3148.3595 | 9692.7796 | 0.00059415 | 0.0008606 | 2.2213 | 19.08 | 2546 | 5.4675e-05 | 2604 | 0 | 0 | 1.9563 | 2299 | 0
Bay Area | 774 | 149 | 423.2895 | 347 | 526.9308 | 36 | 3.3924e-05 | 0.064586 | 0.86952 | 0.2073 | 0.9091 | 0.0030169 | 0.03208 | 0.010993 | 0.25 | 2.1858e-06 | 3.1424e-05 | 0.42939 | 0.80331 | {5D6DF9FD-08CF-4E49-97A3-2B3AF27CC711} | 12101104 | OAKLAND K 1104 | CR210 | 37.8299 | -122.2106 | OAKLAND K 1104CR210 | 80 | 519 | 26424.805 | 4546.547 | 21878.258 | 4546.547 | 21878.258 | 0.0011313 | 0.0012212 | 2.8409 | 9.6389 | 2450 | 7.869e-05 | 2605 | 0 | 0 | 2.8251 | 2773 | 0
Central Coast | 9104 | 27 | 79.5764 | 92 | 117.5079 | 6 | 3.2775e-05 | 0.066432 | 21.0235 | 22.5903 | 52.5838 | 1.3701 | 0.60509 | 1.5258 | 1 | 2.1773e-06 | 0.00033949 | 0.29348 | 0.6772 | {8D03B6F3-9D77-4101-86DB-95FECDC9E7D7} | 182222103 | DEL MONTE 2103 | 2204 | 36.5568 | -121.898 | DEL MONTE 21032204 | 12 | 0 | 592.6413 | 592.6413 | 0 | 592.6413 | 0 | 0.0020369 | 0.00019665 | 2.9473 | 15.3333 | 1030 | 1.3064e-05 | 2606 | 0 | 0 | 0.36825 | 1651 | 0
Bay Area | 6362 | 0 | 0 | 2 | 0.91147 | 1 | 3.2714e-05 | 0.066432 |  |  |  |  | 0 | 1.2137 | 1 | 2.1733e-06 | 3.2714e-05 | 0 | 0 | {27893E9C-0A5B-4290-96D8-63CEC0636192} | 14341106 | VALLEY VIEW 1106 | P180 | 37.9816 | -122.2684 | VALLEY VIEW 1106P180 | 100 | 329 | 19639.3023 | 3522.4569 | 16116.8455 | 133.4076 | 574.0458 | 3.2714e-05 | 3.2714e-05 |  | 2 | 2430 | 2.1733e-06 | 2607 | 0 | 0 | 0.082896 | 2783 | 0
Central Coast | 6954 | 5 | 17.1704 | 5 | 17.1704 | 1 | 3.2608e-05 | 0.066432 | 0.21628 | 0.22239 | 0.26718 | 5.7785e-05 | 2.4535 | 2.9042 | 1 | 2.1662e-06 | 7.0524e-06 | 1 | 1 | {C2A5C891-9ACA-4BCB-B672-51535FFB0933} | 182852203 | VIEJO 2203 | 2634 | 36.5669 | -121.9134 | VIEJO 22032634 | 50 | 337 | 17143.5444 | 2626.604 | 14516.9403 | 0 | 730.8417 | 7.0524e-06 | 3.2608e-05 | 3.4341 | 5 | 2821 | 2.1662e-06 | 2608 | 0 | 0 | 0 | 1847 | 0
Bay Area | 59 | 13 | 47.0604 | 15 | 47.9719 | 1 | 3.2269e-05 | 0.066432 |  |  |  |  | 0 | 0 | 0 | 2.1437e-06 | 3.2269e-05 | 0.86667 | 0.981 | {7B48B738-B738-4F2B-B0D7-4D191D860D4E} | 24012102 | BAY MEADOWS 2102 | circuit_breaker | 37.5516 | -122.293 | BAY MEADOWS 2102circuit_breaker | 250 | 1354 | 64556.3828 | 11130.4877 | 53425.895 | 5.118 | 87.7392 | 3.2269e-05 | 3.2269e-05 | 3.62 | 15 | 2437 | 2.1437e-06 | 2609 | 0 | 0 | 0.0031802 | 2797 | 0
Central Coast | 5852 | 161 | 566.9419 | 239 | 612.5294 | 25 | 3.2229e-05 | 0.066432 | 3.9961 | 2.3644 | 6.1343 | 0.053975 | 0.17823 | 0.28578 | 0.76 | 2.141e-06 | 7.5373e-05 | 0.67364 | 0.92558 | {D3AE8800-862E-498F-9908-541EA621BA7E} | 182852204 | VIEJO 2204 | 9540 | 36.5845 | -121.9023 | VIEJO 22049540 | 68 | 375 | 18501.382 | 3592.089 | 14909.2931 | 2249.934 | 9780.4911 | 0.0018843 | 0.00080573 | 3.5214 | 9.56 | 2016 | 5.3526e-05 | 2610 | 0 | 0 | 1.398 | 1319 | 0
Central Coast | 526 | 14 | 30.9972 | 59 | 45.8037 | 13 | 3.2174e-05 | 0.066432 | 7.5546 | 16.9622 | 40.8923 | 0.51433 | 14.3372 | 41.8057 | 1.0153 | 2.1374e-06 | 0.00012638 | 0.23729 | 0.67674 | {9EA2D570-9C08-4A90-9E79-02DD530C0174} | 182541101 | ATASCADERO 1101 | 2379 | 35.4651 | -120.6834 | ATASCADERO 11012379 | 17 | 21 | 2604.3064 | 1171.3689 | 1432.9375 | 1171.3689 | 1432.9375 | 0.0016429 | 0.00041826 | 2.2141 | 4.5385 | 1718 | 2.7786e-05 | 2611 | 0 | 0 | 0.72785 | 2420 | 0
Bay Area | 2893 | 16 | 58.0408 | 42 | 72.2713 | 5 | 3.2153e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.136e-06 | 2.3193e-05 | 0.38095 | 0.8031 | {37A21F97-AEE6-4520-B851-056330FD3EDF} | 24251104 | WOODSIDE 1104 | 9116 | 37.4397 | -122.2644 | WOODSIDE 11049116 | 140 | 613 | 32462.5485 | 6807.6296 | 25654.919 | 1213.0994 | 4763.5054 | 0.00011596 | 0.00016077 | 3.6275 | 8.4 | 2561 | 1.068e-05 | 2612 | 0 | 0 | 0.75378 | 2837 | 0
Central Coast | 3391 | 25 | 46.5498 | 61 | 63.9178 | 7 | 3.209e-05 | 0.066432 | 0.0028498 | 0.0014844 | 1.8415e-05 | 7.8478e-09 | 5.2359e-13 | 0.014602 | 0.28571 | 2.1318e-06 | 1.1655e-05 | 0.40984 | 0.72828 | {6679B851-BEDD-496F-943F-802ECD2AE75C} | 82021101 | LOS GATOS 1101 | 60136 | 37.2278 | -121.9676 | LOS GATOS 110160136 | 230 | 727 | 38887.4849 | 9049.3039 | 29838.181 | 461.7186 | 1148.7776 | 8.1585e-05 | 0.00022463 | 1.862 | 8.7143 | 2767 | 1.4923e-05 | 2613 | 0 | 0 | 0.2869 | 476 | 0
Central Coast | 9222 | 0 | 0 | 1 | 0.67977 | 1 | 3.2081e-05 | 0.066432 | 0.2171 | 1.0643 | 10.3514 | 0.002362 | 0 | 0.1396 | 1 | 2.1312e-06 | 6.9647e-06 | 0 | 0 | {844C973E-06B3-4BF1-90ED-935D78CB12A8} | 182222104 | DEL MONTE 2104 | 3066 | 36.5584 | -121.7506 | DEL MONTE 21043066 | 5 | 0 | 26.0345 | 26.0345 | 0 | 26.0345 | 0 | 6.9647e-06 | 3.2081e-05 |  | 1 | 2822 | 2.1312e-06 | 2614 | 0 | 0 | 0.016177 | 921 | 0
Bay Area | 7709 | 3 | 7.5922 | 5 | 8.5037 | 1 | 3.2066e-05 | 0.066432 | 0.56494 | 0.82161 | 3.0776 | 0.20378 | 1.2987 | 13.6912 | 1.0044 | 2.1302e-06 | 1.8115e-05 | 0.6 | 0.89281 | {01D4891F-C6A5-4AED-AB10-724ED9F191A9} | 13801105 | MORAGA 1105 | 18396 | 37.8312 | -122.1301 | MORAGA 110518396 | 30 | 183 | 10961.6231 | 1810.5654 | 9151.0578 | 125.7014 | 851.9358 | 1.8115e-05 | 3.2066e-05 | 2.5307 | 5 | 2646 | 2.1302e-06 | 2615 | 0 | 0 | 0.078107 | 391 | 0
Central Coast | 6806 | 151 | 393.4399 | 306 | 477.2081 | 26 | 3.1829e-05 | 0.066432 | 3.8675 | 4.6507 | 10.4057 | 0.12454 | 0.26812 | 1.4056 | 1.0003 | 2.1145e-06 | 8.1528e-05 | 0.49346 | 0.82446 | {95BA16F1-C0BE-4BE8-9C3E-AD056E7BB712} | 182222103 | DEL MONTE 2103 | 32886 | 36.5944 | -121.8659 | DEL MONTE 210332886 | 102 | 208 | 17625.6757 | 6355.8295 | 11269.8463 | 2565.9589 | 5889.2916 | 0.0021197 | 0.00082756 | 2.6056 | 11.7692 | 1971 | 5.4976e-05 | 2616 | 0 | 0 | 1.5944 | 2438 | 0
Bay Area | 6644 | 129 | 341.2053 | 489 | 556.6063 | 21 | 2.336e-05 | 0.09247 | 2.0187 | 2.9805 | 9.7091 | 0.17016 | 1.1268 | 7.9681 | 0.91372 | 2.1099e-06 | 3.9589e-05 | 0.2638 | 0.61301 | {FDA6A832-C24F-4A41-9F11-2FF86697F8AB} | 13801101 | MORAGA 1101 | 7616 | 37.8746 | -122.1864 | MORAGA 11017616 | 49 | 155 | 8380.9581 | 2295.5196 | 6085.4384 | 2295.5196 | 6085.4384 | 0.00083137 | 0.00049056 | 2.645 | 23.2857 | 2349 | 4.4308e-05 | 2617 | 0 | 0 | 1.4264 | 2826 | 0
Bay Area | 283 | 92 | 276.7559 | 478 | 477.0085 | 40 | 3.1551e-05 | 0.066432 | 0.95806 | 0.41627 | 1.9744 | 0.013438 | 0.3887 | 1.8775 | 0.825 | 2.096e-06 | 3.5947e-05 | 0.19247 | 0.58019 | {FEA3C3F3-959E-472A-9376-926585E20D05} | 12541106 | OAKLAND X 1106 | circuit_breaker | 37.8051 | -122.2314 | OAKLAND X 1106circuit_breaker | 326 | 2572 | 122146.7532 | 18897.8572 | 103248.896 | 6219.7565 | 25220.7594 | 0.0014379 | 0.0012621 | 3.0082 | 11.95 | 2387 | 8.3841e-05 | 2618 | 0 | 0 | 3.8648 | 2772 | 0
Central Coast | 995 | 178 | 414.9937 | 338 | 499.5894 | 20 | 3.4884e-05 | 0.059789 | 1.4437 | 5.0674 | 15.6289 | 0.049186 | 0.055448 | 1.1187 | 1.4 | 2.0931e-06 | 3.8643e-05 | 0.52663 | 0.83067 | {D5629837-45B4-4B33-A660-AFDD9F409AB3} | 182852201 | VIEJO 2201 | 9490 | 36.5661 | -121.9352 | VIEJO 22019490 | 106 | 77 | 6576.0945 | 3484.3168 | 3091.7777 | 2513.194 | 1612.0331 | 0.00077285 | 0.00069769 | 2.3314 | 16.9 | 2357 | 4.1862e-05 | 2619 | 0 | 0 | 1.5616 | 1717 | 0
North Valley | 5052 | 24 | 34.6876 | 88 | 65.1083 | 15 | 3.1436e-05 | 0.066432 | 2.2819 | 2.9402 | 4.742 | 0.036674 | 0.91888 | 1.7477 | 1.0015 | 2.0883e-06 | 3.7671e-05 | 0.27273 | 0.53277 | {DD5BA261-28C3-4395-8BF5-3D293075C1EE} | 103311101 | BURNEY 1102 | circuit_breaker | 40.8882 | -121.6711 | BURNEY 1102circuit_breaker | 95 | 196 | 9053.3192 | 3204.0009 | 5849.3184 | 1949.5939 | 3633.0271 | 0.00056507 | 0.00047154 | 1.4453 | 5.8667 | 2366 | 3.1325e-05 | 2620 | 0 | 0 | 1.2114 | 808 | 0
Bay Area | 289 | 54 | 105.476 | 240 | 204.1204 | 21 | 3.1434e-05 | 0.066432 | 4.6059 | 1.4762 | 4.6202 | 0.083083 | 0.10156 | 0.12111 | 0.57143 | 2.0882e-06 | 0.00011393 | 0.225 | 0.51673 | {DCA9ACB4-28D7-4107-A085-304473A5BF3B} | 12840402 | RIDGE 0402 | circuit_breaker | 37.885 | -122.2551 | RIDGE 0402circuit_breaker | 92 | 610 | 24773.3731 | 3848.2536 | 20925.1196 | 2818.3373 | 15395.9113 | 0.0023926 | 0.00066012 | 1.9533 | 11.4286 | 1780 | 4.3853e-05 | 2621 | 0 | 0 | 1.7512 | 1487 | 0
Central Coast | 7417 | 13 | 47.3811 | 45 | 66.6594 | 4 | 3.1378e-05 | 0.066432 | 7.8764 | 4.0518 | 10.165 | 0.1793 | 0.10841 | 0.30774 | 1 | 2.0845e-06 | 0.00026863 | 0.28889 | 0.71079 | {946D9301-8325-4649-B180-881E34272B41} | 182040402 | CARMEL 0402 | circuit_breaker | 36.5608 | -121.9196 | CARMEL 0402circuit_breaker | 64 | 193 | 7315.0099 | 2329.9611 | 4985.0488 | 461.4011 | 126.9579 | 0.0010745 | 0.00012551 | 3.6447 | 11.25 | 1205 | 8.3381e-06 | 2622 | 0 | 0 | 0.2867 | 2184 | 0
Central Coast | 5764 | 42 | 142.3259 | 81 | 163.1164 | 8 | 3.1378e-05 | 0.066432 |  |  |  |  | 0 | 0.052244 | 1 | 2.0845e-06 | 3.1378e-05 | 0.51852 | 0.87254 | {7C0AA1F8-3024-4D35-BAB8-1475B467A597} | 182852201 | VIEJO 2201 | 9698 | 36.5726 | -121.9437 | VIEJO 22019698 | 35 | 50 | 3493.0142 | 1448.8828 | 2044.1314 | 912.5815 | 1465.1638 | 0.00025102 | 0.00025102 | 3.3887 | 10.125 | 2451 | 1.6676e-05 | 2623 | 0 | 0 | 0.56705 | 1687 | 0
Bay Area | 5207 | 27 | 90.0903 | 65 | 108.0437 | 6 | 3.1122e-05 | 0.066432 | 0.092375 | 0.12323 | 0.084089 | 0.00048052 | 0.56637 | 1.9249 | 1 | 2.0675e-06 | 2.145e-05 | 0.41538 | 0.83383 | {939220F8-B510-43C6-B684-A1C5D4C4B3DB} | 24060404 | CAROLANDS 0404 | 84797 | 37.5504 | -122.3739 | CAROLANDS 040484797 | 52 | 41 | 4273.8622 | 2172.9793 | 2100.8829 | 159.0147 | 552.0779 | 0.0001287 | 0.00018673 | 3.3367 | 10.8333 | 2581 | 1.2405e-05 | 2624 | 0 | 0 | 0.098807 | 2278 | 0
Bay Area | 8323 | 13 | 29.304 | 32 | 39.9793 | 5 | 3.0942e-05 | 0.066432 | 0.26835 | 0.14383 | 0.061099 | 5.0541e-05 | 0 | 0 | 0 | 2.0555e-06 | 1.9648e-05 | 0.40625 | 0.73298 | {9E2BE648-1876-419E-9EA6-9561CF55CBC8} | 24181104 | SAN CARLOS 1104 | 36864 | 37.48 | -122.26 | SAN CARLOS 110436864 | 44 | 68 | 4018.6705 | 1364.5515 | 2654.119 | 812.4562 | 1833.4996 | 9.8238e-05 | 0.00015471 | 2.2542 | 6.4 | 2616 | 1.0278e-05 | 2625 | 0 | 0 | 0.50484 | 2264 | 0
Central Coast | 1411 | 982 | 3291.8671 | 1306 | 3473.9563 | 80 | 3.3116e-05 | 0.060619 | 2.1023 | 3.6416 | 12.2049 | 0.057812 | 0.019716 | 0.21513 | 1.3125 | 2.0371e-06 | 4.8569e-05 | 0.75191 | 0.94758 | {7C470D28-E772-41C4-B48A-99DC70576237} | 182852201 | VIEJO 2201 | 9114 | 36.5785 | -121.9279 | VIEJO 22019114 | 177 | 280 | 23710.3409 | 10947.6406 | 12762.7003 | 10880.685 | 12644.546 | 0.0038855 | 0.0026493 | 3.3522 | 16.325 | 2240 | 0.00016296 | 2626 | 0 | 0 | 6.7609 | 2035 | 0
Central Coast | 6135 | 70 | 226.9074 | 149 | 278.4 | 17 | 3.0657e-05 | 0.066432 | 2.8535 | 4.4026 | 17.4289 | 0.20232 | 0.1684 | 2.0701 | 1.01 | 2.0366e-06 | 8.3957e-05 | 0.4698 | 0.81504 | {E1CC4B8A-EEA0-444B-A148-93C085F63A52} | 183071101 | PERRY 1101 | W10 | 35.5663 | -121.0754 | PERRY 1101W10 | 57 | 200 | 12364.9709 | 2977.5841 | 9387.3867 | 1609.5516 | 5996.5193 | 0.0014273 | 0.00052116 | 3.2415 | 8.7647 | 1959 | 3.4622e-05 | 2627 | 0 | 0 | 1.0001 | 2200 | 0
Bay Area | 6936 | 210 | 626.0797 | 620 | 863.2987 | 69 | 3.0656e-05 | 0.066432 | 0.24201 | 0.21287 | 0.39895 | 0.0012534 | 0.41583 | 1.1106 | 0.7971 | 2.0366e-06 | 1.9404e-05 | 0.33871 | 0.72522 | {3B6CB851-40C4-4A4E-8C82-B4A7B88943F2} | 24181104 | SAN CARLOS 1104 | 9052 | 37.4781 | -122.2614 | SAN CARLOS 11049052 | 121 | 428 | 28186.0448 | 8312.0915 | 19873.9534 | 7726.2126 | 16682.7356 | 0.0013389 | 0.0021153 | 2.9813 | 8.9855 | 2621 | 0.00014052 | 2628 | 0 | 0 | 4.8008 | 2711 | 0
Central Coast | 931 | 1 | 1.2277 | 1 | 1.2277 | 1 | 3.0649e-05 | 0.066432 |  |  |  |  | 1.0531 | 1.3403 | 1 | 2.0361e-06 | 3.0649e-05 | 1 | 1 | {76970631-2436-4433-8ABE-AE41F160A6E0} | 83481109 | STELLING 1109 | 13228 | 37.3103 | -122.0504 | STELLING 110913228 | 234 | 728 | 45096.9939 | 13588.5968 | 31508.3971 | 1453.4738 | 1893.0247 | 3.0649e-05 | 3.0649e-05 | 1.2277 | 1 | 2462 | 2.0361e-06 | 2629 | 0 | 0 | 0.90315 | 1921 | 0
Bay Area | 7684 | 25 | 46.2197 | 380 | 270.0632 | 21 | 3.0636e-05 | 0.066432 | 0.18123 | 0.12057 | 0.10154 | 4.0523e-05 | 0.56764 | 0.27795 | 0.71429 | 2.0352e-06 | 1.5331e-05 | 0.065789 | 0.17114 | {A0667D06-51C5-41CE-85EE-7B2260B907EA} | 24080402 | EMERALD LAKE 0402 | circuit_breaker | 37.4617 | -122.2772 | EMERALD LAKE 0402circuit_breaker | 53 | 122 | 8022.4134 | 3052.0291 | 4970.3843 | 3052.0291 | 4970.3843 | 0.00032196 | 0.00064335 | 1.8488 | 18.0952 | 2697 | 4.2739e-05 | 2630 | 0 | 0 | 1.8964 | 1764 | 0
Bay Area | 71 | 5 | 11.2972 | 10 | 14.472 | 1 | 3.0617e-05 | 0.066432 |  |  |  |  | 0 | 0 | 0 | 2.0339e-06 | 3.0617e-05 | 0.5 | 0.78062 | {2DBE6767-7D56-4562-8F78-31E59118A4C4} | 24110404 | HILLSDALE 0404 | 85812 | 37.5365 | -122.3218 | HILLSDALE 040485812 | 159 | 780 | 39548.1564 | 9120.3733 | 30427.7832 | 0 | 31.1811 | 3.0617e-05 | 3.0617e-05 | 2.2594 | 10 | 2463 | 2.0339e-06 | 2631 | 0 | 0 | 0 | 2100 | 0
Central Valley | 8419 | 1 | 1.2277 | 4 | 2.5662 | 2 | 3.0203e-05 | 0.066432 | 0 | 0 | 0 | 0 | 2.4292 | 10.6584 | 1 | 2.0064e-06 | 1.5877e-05 | 0.25 | 0.47841 | {0F280189-7238-4409-8E14-ABF01E8D5CE1} | 254452102 | MARIPOSA 2102 | 10250 | 37.4632 | -119.9479 | MARIPOSA 210210250 | 4 | 1 | 84.368 | 66.9649 | 17.4031 | 66.9649 | 17.4031 | 3.1754e-05 | 6.0405e-05 | 1.2277 | 2 | 2685 | 4.0128e-06 | 2632 | 0 | 0 | 0.04161 | 924 | 0
Bay Area | 6763 | 106 | 186.3644 | 155 | 213.0477 | 15 | 3.0179e-05 | 0.066432 | 1.756 | 0.83373 | 1.4599 | 0.010254 | 0 | 0.011681 | 0.13333 | 2.0048e-06 | 3.6223e-05 | 0.68387 | 0.87475 | {8CEAFBDA-9CAF-47DF-A93A-B3DE193C02EB} | 12101101 | OAKLAND K 1101 | CR170 | 37.855 | -122.238 | OAKLAND K 1101CR170 | 45 | 232 | 11529.3981 | 2012.9178 | 9516.4804 | 2012.9178 | 9490.1933 | 0.00054334 | 0.00045268 | 1.7582 | 10.3333 | 2384 | 3.0072e-05 | 2633 | 0 | 0 | 1.2508 | 2059 | 0
Central Coast | 6338 | 281 | 541.2874 | 1554 | 1231.2554 | 129 | 3.0014e-05 | 0.066432 | 1.7761 | 7.4593 | 21.4656 | 0.1563 | 2.4712 | 17.0337 | 1.0315 | 1.9939e-06 | 4.046e-05 | 0.18082 | 0.43962 | {AA1A8D76-D2A1-485C-9B69-D74FAC1101F8} | 83431116 | HICKS 1116 | 60050 | 37.2297 | -121.9499 | HICKS 111660050 | 202 | 177 | 22819.0542 | 13194.2857 | 9624.7685 | 13194.2857 | 9624.7685 | 0.0052193 | 0.0038717 | 1.9263 | 12.0465 | 2333 | 0.00025721 | 2634 | 0 | 0 | 8.1985 | 723 | 0
Central Coast | 7699 | 177 | 537.8021 | 394 | 673.8203 | 27 | 3.0648e-05 | 0.063971 | 5.1588 | 10.3377 | 28.0968 | 0.29431 | 0.24175 | 1.0238 | 1.1484 | 1.9837e-06 | 0.00011857 | 0.44924 | 0.79814 | {19B86573-307E-4C6E-966B-96848CB70151} | 182291101 | HATTON 1101 | circuit_breaker | 36.5569 | -121.898 | HATTON 1101circuit_breaker | 38 | 52 | 5571.8794 | 2553.7001 | 3018.1793 | 2553.7001 | 3018.1793 | 0.0032014 | 0.00082749 | 3.0384 | 14.5926 | 1752 | 5.3559e-05 | 2635 | 0 | 0 | 1.5868 | 1441 | 0
Bay Area | 1235 | 245 | 655.7581 | 888 | 1013.0035 | 47 | 2.9761e-05 | 0.066432 | 0.64597 | 0.30398 | 1.8812 | 0.0053736 | 1.0847 | 0.71792 | 0.78723 | 1.9771e-06 | 2.5932e-05 | 0.2759 | 0.64734 | {0E3E2146-50FB-4065-BA86-A817B98C8BBE} | 13180401 | PALO SECO 0401 | circuit_breaker | 37.8193 | -122.2062 | PALO SECO 0401circuit_breaker | 105 | 474 | 28300.1837 | 7522.627 | 20777.5567 | 7450.9364 | 20758.6617 | 0.0012188 | 0.0013988 | 2.6766 | 18.8936 | 2517 | 9.2923e-05 | 2636 | 0 | 0 | 4.6298 | 2814 | 0
Bay Area | 2423 | 186 | 478.181 | 630 | 723.1767 | 52 | 3.3363e-05 | 0.060044 | 6.4095 | 1.8758 | 5.3825 | 0.14937 | 0 | 0.0047355 | 0.51923 | 1.9449e-06 | 0.00012534 | 0.29524 | 0.66122 | {C758376E-2F53-4EBD-9E43-CD37C030EEDD} | 12101103 | OAKLAND K 1103 | CR188 | 37.8331 | -122.214 | OAKLAND K 1103CR188 | 120 | 675 | 34487.2596 | 5757.5465 | 28729.7131 | 5757.5465 | 28729.7131 | 0.0065178 | 0.0017349 | 2.5709 | 12.1154 | 1721 | 0.00010113 | 2637 | 0 | 0 | 3.5776 | 2445 | 0
Central Coast | 3744 | 33 | 124.9776 | 159 | 203.8545 | 33 | 3.0956e-05 | 0.062406 | 1.999 | 17.1661 | 53.0031 | 0.11674 | 0.5941 | 19.3835 | 1.2869 | 1.9359e-06 | 3.1078e-05 | 0.20755 | 0.61307 | {72519E2E-220A-434F-A310-3B8078E34E61} | 182971101 | PURISIMA 1101 | circuit_breaker | 34.7006 | -120.4354 | PURISIMA 1101circuit_breaker | 55 | 169 | 16363.7025 | 7381.7293 | 8981.9732 | 5755.7195 | 250.1735 | 0.0010256 | 0.0010216 | 3.7872 | 4.8182 | 2457 | 6.3885e-05 | 2638 | 0 | 0 | 3.5764 | 2195 | 0
Bay Area | 5480 | 41 | 117.6325 | 106 | 150.0579 | 7 | 2.9137e-05 | 0.066432 | 3.8009 | 0.87341 | 4.8691 | 0.032811 | 0 | 0.030183 | 0.28571 | 1.9356e-06 | 6.9173e-05 | 0.38679 | 0.78391 | {3C8EEA5A-CE4E-4740-9897-693B2E67E957} | 12101104 | OAKLAND K 1104 | circuit_breaker | 37.8478 | -122.2291 | OAKLAND K 1104circuit_breaker | 52 | 178 | 10318.7727 | 2362.6398 | 7956.1329 | 2362.6398 | 7956.1329 | 0.00048421 | 0.00020396 | 2.8691 | 15.1429 | 2067 | 1.3549e-05 | 2639 | 0 | 0 | 1.4681 | 613 | 0
Bay Area | 2068 | 71 | 146.6837 | 135 | 180.7187 | 19 | 3.0921e-05 | 0.062935 | 0.90126 | 0.22277 | 0.31938 | 0.0017407 | 0.078084 | 0.13159 | 0.78947 | 1.9351e-06 | 2.8077e-05 | 0.52593 | 0.81167 | {9DF9A52F-32F8-4676-BE5E-F9A3D03712AF} | 13340402 | SPRUCE 0402 | BR304 | 37.9039 | -122.2658 | SPRUCE 0402BR304 | 124 | 838 | 40095.8245 | 5836.8583 | 34258.9662 | 2445.8736 | 14021.6203 | 0.00053346 | 0.0005875 | 2.066 | 7.1053 | 2490 | 3.6767e-05 | 2640 | 0 | 0 | 1.5198 | 1313 | 0
Central Coast | 1844 | 191 | 651.6785 | 338 | 739.8977 | 31 | 3.2898e-05 | 0.05786 | 3.7913 | 4.3266 | 13.0308 | 0.10705 | 0.19185 | 0.73205 | 1.5161 | 1.9227e-06 | 7.7522e-05 | 0.56509 | 0.88077 | {DF6AF33C-27E3-43A2-A515-B3B27F7B49FE} | 182291102 | HATTON 1102 | circuit_breaker | 36.5568 | -121.898 | HATTON 1102circuit_breaker | 127 | 110 | 14497.2028 | 7851.6881 | 6645.5147 | 3118.5334 | 3598.6962 | 0.0024032 | 0.0010198 | 3.4119 | 10.9032 | 2002 | 5.9602e-05 | 2641 | 0 | 0 | 1.9378 | 483 | 0
Central Coast | 6323 | 376 | 1346.8003 | 454 | 1395.852 | 28 | 3.099e-05 | 0.061687 | 4.1891 | 3.2405 | 7.7204 | 0.051035 | 0.14454 | 0.53146 | 1.2143 | 1.9179e-06 | 8.5017e-05 | 0.82819 | 0.96486 | {204F3E15-8D98-42F3-A6B0-F8D2FC5C7EAD} | 182852202 | VIEJO 2202 | circuit_breaker | 36.5784 | -121.9082 | VIEJO 2202circuit_breaker | 40 | 18 | 4291.4657 | 3355.2545 | 936.2113 | 3355.2545 | 936.2113 | 0.0023805 | 0.00086771 | 3.5819 | 16.2143 | 1951 | 5.37e-05 | 2642 | 0 | 0 | 2.0849 | 101 | 0
Central Coast | 542 | 3 | 11.9143 | 3 | 11.9143 | 1 | 2.8729e-05 | 0.066431 |  |  |  |  | 0 | 0.10066 | 1 | 1.9085e-06 | 2.8729e-05 | 1 | 1 | {58E90993-9BBD-4F51-9BA9-AD36025808B4} | 83531103 | MC KEE 1103 | XR028 | 37.3918 | -121.8336 | MC KEE 1103XR028 | 251 | 857 | 57415.5121 | 16781.1982 | 40634.3139 | 1085.7736 | 195.366 | 2.8729e-05 | 2.8729e-05 | 3.9714 | 3 | 2482 | 1.9085e-06 | 2643 | 0 | 0 | 0.67467 | 1793 | 0
Bay Area | 2322 | 51 | 130.857 | 197 | 210.5892 | 8 | 2.8665e-05 | 0.066432 | 0.072476 | 0.21358 | 2.0916 | 0.0003157 | 1.7345 | 0.98166 | 1 | 1.9043e-06 | 2.1042e-05 | 0.25888 | 0.62139 | {14DC5424-B005-4065-8948-2B6A676B0C25} | 12541104 | OAKLAND X 1104 | circuit_breaker | 37.8053 | -122.2313 | OAKLAND X 1104circuit_breaker | 72 | 390 | 19709.8521 | 3923.3157 | 15786.5364 | 2011.6074 | 3851.2742 | 0.00016834 | 0.00022932 | 2.5658 | 24.625 | 2589 | 1.5234e-05 | 2644 | 0 | 0 | 1.25 | 2493 | 0
Bay Area | 63 | 69 | 202.6969 | 213 | 279.0136 | 31 | 2.8604e-05 | 0.066432 | 3.5609 | 1.0257 | 3.563 | 0.075266 | 0.025692 | 0.13598 | 0.22581 | 1.9002e-06 | 8.5118e-05 | 0.32394 | 0.72648 | {44B8C422-CD6C-4697-80AE-EEAF985A6D84} | 12541105 | OAKLAND X 1105 | circuit_breaker | 37.805 | -122.2315 | OAKLAND X 1105circuit_breaker | 435 | 3989 | 182870.2829 | 23764.1022 | 159106.1807 | 3428.0095 | 24132.6032 | 0.0026387 | 0.00088673 | 2.9376 | 6.871 | 1949 | 5.8907e-05 | 2645 | 0 | 0 | 2.1301 | 2054 | 0
Bay Area | 3434 | 1 | 4.0491 | 23 | 15.0232 | 3 | 2.855e-05 | 0.066432 | 0.049162 | 0.035078 | 0.46573 | 0.00059351 | 0 | 0 | 0 | 1.8966e-06 | 1.9911e-05 | 0.043478 | 0.26952 | {D87265E8-5674-4799-A45E-7F1EC7B446CA} | 12690401 | FLORENCE 0401 | CR220 | 37.8331 | -122.2195 | FLORENCE 0401CR220 | 35 | 155 | 9433.1966 | 2216.0779 | 7217.1186 | 350.2675 | 2026.3332 | 5.9732e-05 | 8.5649e-05 | 4.0491 | 7.6667 | 2611 | 5.6899e-06 | 2646 | 0 | 0 | 0.21765 | 2759 | 0
North Valley | 1020 | 77 | 111.1289 | 158 | 152.8452 | 20 | 3.192e-05 | 0.056467 | 10.8237 | 967.93 | 25646.9655 | 394.3024 | 0.86048 | 12.5515 | 1.6 | 1.8927e-06 | 0.00024879 | 0.48734 | 0.72707 | {248F09B8-1D5D-4034-96B7-C372BB4594AA} | 103021101 | GANSNER 1101 | 52664 | 39.9392 | -120.9474 | GANSNER 110152664 | 178 | 541 | 28003.7102 | 7524.9818 | 20478.7284 | 1440.8216 | 3198.089 | 0.0049758 | 0.00063839 | 1.4432 | 7.9 | 1254 | 3.7855e-05 | 2647 | 0 | 0 | 0.89528 | 1572 | 0
Bay Area | 3120 | 20 | 43.751 | 40 | 52.9503 | 7 | 2.8483e-05 | 0.066431 | 0 | 0 | 0 | 0 | 0.010114 | 0.053003 | 0.85714 | 1.8922e-06 | 2.1051e-05 | 0.5 | 0.82627 | {01A1D9FE-BCED-4C35-831D-C0BD99AC82CE} | 43201102 | STAFFORD 1102 | 42542 | 38.1176 | -122.6086 | STAFFORD 110242542 | 129 | 406 | 24319.7226 | 5615.2121 | 18704.5105 | 623.2409 | 873.1751 | 0.00014736 | 0.00019938 | 2.1875 | 5.7143 | 2588 | 1.3245e-05 | 2648 | 0 | 0 | 0.38726 | 2812 | 0
North Coast | 7645 | 5 | 6.1386 | 13 | 9.4768 | 4 | 2.8458e-05 | 0.066432 | 5.7127 | 716.9171 | 4095.0027 | 38.8103 | 0.47124 | 15.8811 | 1 | 1.8905e-06 | 0.00010532 | 0.38462 | 0.64774 | {7E6065FF-2C07-4696-A18E-5408BD7025E6} | 42251101 | HOPLAND 1101 | circuit_breaker | 38.9728 | -123.0816 | HOPLAND 1101circuit_breaker | 107 | 173 | 17535.0189 | 9884.04 | 7650.979 | 1104.2357 | 645.4199 | 0.00042127 | 0.00011383 | 1.2277 | 3.25 | 1832 | 7.5621e-06 | 2649 | 0 | 0 | 0.68614 | 1523 | 0
Bay Area | 5759 | 261 | 575.2573 | 1087 | 1047.9886 | 61 | 2.8387e-05 | 0.066432 | 0.16207 | 0.14599 | 0.11227 | 8.438e-05 | 0.25366 | 0.88787 | 1 | 1.8858e-06 | 1.9006e-05 | 0.24011 | 0.54892 | {59262E1A-A9BD-4C08-8147-3EF20A86F7EA} | 24040403 | BERESFORD 0403 | 9154 | 37.5535 | -122.3336 | BERESFORD 04039154 | 208 | 683 | 37865.6287 | 10532.6812 | 27332.9475 | 6496.7789 | 12404.5549 | 0.0011594 | 0.0017316 | 2.2041 | 17.8197 | 2633 | 0.00011503 | 2650 | 0 | 0 | 4.0369 | 2844 | 0
Bay Area | 5120 | 232 | 795.6727 | 367 | 865.4913 | 52 | 2.8212e-05 | 0.066432 | 0.70501 | 3.3542 | 9.0929 | 0.099889 | 0.51583 | 4.7256 | 0.90402 | 1.8742e-06 | 2.545e-05 | 0.63215 | 0.91933 | {A2C189F4-1155-43D0-9466-3E701D18918E} | 13111109 | SAN LEANDRO U 1109 | CR182 | 37.7522 | -122.1267 | SAN LEANDRO U 1109CR182 | 128 | 565 | 35907.9142 | 7762.1289 | 28145.7853 | 7762.1289 | 28145.7853 | 0.0013234 | 0.001467 | 3.4296 | 7.0577 | 2529 | 9.7458e-05 | 2651 | 0 | 0 | 4.8232 | 2284 | 0
Central Coast | 9245 | 7 | 8.7249 | 51 | 34.7901 | 17 | 2.8138e-05 | 0.066432 | 0.96503 | 56.6209 | 197.8439 | 0.31327 | 0.11661 | 11.254 | 1.0203 | 1.8693e-06 | 2.7566e-05 | 0.13725 | 0.25079 | {F1939199-12BC-4979-94F2-EFC54D60817D} | 182371111 | LAURELES 1111 | 84523 | 36.4267 | -121.6767 | LAURELES 111184523 | 7 | 9 | 3683.4244 | 1964.6047 | 1718.8197 | 1964.6047 | 1718.8197 | 0.00046862 | 0.00047835 | 1.2464 | 3 | 2499 | 3.1778e-05 | 2652 | 0 | 0 | 1.2207 | 733 | 0
Bay Area | 5517 | 13 | 36.1848 | 105 | 81.6038 | 7 | 2.8112e-05 | 0.066432 | 1.753 | 0.58927 | 3.3549 | 0.019217 | 0 | 0.0012326 | 0.14286 | 1.8675e-06 | 4.3982e-05 | 0.12381 | 0.44342 | {9898F55D-4181-4FB3-A3AA-B13258B3B860} | 12690401 | FLORENCE 0401 | circuit_breaker | 37.8361 | -122.2202 | FLORENCE 0401circuit_breaker | 97 | 472 | 24508.9839 | 4654.0755 | 19854.9084 | 996.0372 | 3834.6988 | 0.00030787 | 0.00019678 | 2.7834 | 15 | 2290 | 1.3073e-05 | 2653 | 0 | 0 | 0.61891 | 1895 | 0
Bay Area | 4662 | 16 | 32.7885 | 77 | 68.6924 | 8 | 2.7916e-05 | 0.066432 | 0.82462 | 0.3093 | 2.0185 | 0.0046889 | 0.062223 | 0.21916 | 0.875 | 1.8545e-06 | 2.6918e-05 | 0.20779 | 0.47732 | {F6FBF85B-F199-40F3-8A70-868561B74EE6} | 42031125 | ALTO 1125 | circuit_breaker | 37.8983 | -122.5248 | ALTO 1125circuit_breaker | 89 | 454 | 23314.028 | 3665.4999 | 19648.5281 | 831.7602 | 3402.4742 | 0.00021534 | 0.00022333 | 2.0493 | 9.625 | 2507 | 1.4836e-05 | 2654 | 0 | 0 | 0.51683 | 2271 | 0
Central Coast | 249 | 83 | 136.6156 | 333 | 273.0778 | 35 | 2.7811e-05 | 0.066432 | 0.26023 | 0.53899 | 1.8966 | 0.0036076 | 0.44456 | 5.5409 | 1.0018 | 1.8475e-06 | 1.6196e-05 | 0.24925 | 0.50028 | {887C42B0-874F-48B4-B368-C0A3D7EE375F} | 83431116 | HICKS 1116 | circuit_breaker | 37.2339 | -121.9015 | HICKS 1116circuit_breaker | 440 | 2087 | 110300.6492 | 27431.6264 | 82869.0228 | 4776.7233 | 6318.4209 | 0.00056685 | 0.00097337 | 1.646 | 9.5143 | 2681 | 6.4663e-05 | 2655 | 0 | 0 | 2.9681 | 630 | 0
Bay Area | 613 | 393 | 780.7794 | 675 | 932.8463 | 70 | 4.01e-05 | 0.044604 | 2.8679 | 3.4427 | 11.1744 | 0.15551 | 1.9901 | 8.1293 | 2.0724 | 1.8447e-06 | 8.5876e-05 | 0.58222 | 0.83699 | {93932C89-B87A-4F1E-B65E-D8FDB2772713} | 14161101 | ROSSMOOR 1101 | L503R | 37.9011 | -122.1121 | ROSSMOOR 1101L503R | 127 | 446 | 28010.2506 | 6929.1359 | 21081.1147 | 6929.1359 | 21081.1147 | 0.0060113 | 0.002807 | 1.9867 | 9.6429 | 1939 | 0.00012913 | 2656 | 0 | 0 | 4.3056 | 2650 | 0
Central Coast | 4984 | 15 | 57.4753 | 32 | 69.0314 | 6 | 2.6286e-05 | 0.068551 | 0.49497 | 35.0246 | 228.5064 | 0.092799 | 0.38496 | 10.5423 | 1.0258 | 1.8308e-06 | 2.0308e-05 | 0.46875 | 0.8326 | {F3373B43-A9DC-45C9-B2E8-745D10B70AD6} | 183011101 | MORRO BAY 1101 | W20 | 35.3656 | -120.8403 | MORRO BAY 1101W20 | 83 | 344 | 19037.0092 | 5996.2896 | 13040.7197 | 3169.5643 | 625.2997 | 0.00012185 | 0.00015772 | 3.8317 | 5.3333 | 2603 | 1.0985e-05 | 2657 | 0 | 0 | 1.9695 | 2429 | 0
Bay Area | 5085 | 8 | 10.9791 | 40 | 30.8535 | 7 | 3.226e-05 | 0.047451 | 0.1055 | 0.055599 | 0.0010789 | 4.5529e-07 | 1.5801 | 0.66456 | 2.1429 | 1.8273e-06 | 1.2087e-05 | 0.2 | 0.35585 | {09D14343-CC3E-46D9-99DC-4193E90EB264} | 42481103 | IGNACIO 1103 | circuit_breaker | 38.0754 | -122.5398 | IGNACIO 1103circuit_breaker | 115 | 145 | 10601.782 | 4294.5405 | 6307.2415 | 849.0798 | 2246.5205 | 8.4608e-05 | 0.00022582 | 1.3724 | 5.7143 | 2763 | 1.2791e-05 | 2658 | 0 | 0 | 0.52759 | 2332 | 0
Central Coast | 695 | 143 | 455.7246 | 303 | 547.2076 | 26 | 2.5066e-05 | 0.075235 | 9.886 | 124.0847 | 576.1275 | 11.9841 | 2.8321 | 30.8693 | 1.0802 | 1.8253e-06 | 9.8998e-05 | 0.47195 | 0.83282 | {99475FCB-F6DE-46D1-A853-CCBB82A0015E} | 182222104 | DEL MONTE 2104 | 2760 | 36.5581 | -121.7506 | DEL MONTE 21042760 | 50 | 19 | 5315.2201 | 4362.4601 | 952.7601 | 4362.4601 | 952.7601 | 0.0025739 | 0.00065172 | 3.1869 | 11.6538 | 1854 | 4.7457e-05 | 2659 | 0 | 0 | 2.7107 | 1175 | 0
Central Coast | 6876 | 117 | 396.6136 | 165 | 423.8729 | 19 | 3.2127e-05 | 0.055943 | 3.8542 | 4.6226 | 9.8788 | 0.051391 | 0.083656 | 0.53863 | 1.6316 | 1.817e-06 | 8.6598e-05 | 0.70909 | 0.93569 | {11A2851C-72B1-4A62-98D6-D6E2FFA710C1} | 182852201 | VIEJO 2201 | circuit_breaker | 36.5784 | -121.9083 | VIEJO 2201circuit_breaker | 140 | 279 | 22693.4914 | 8262.6752 | 14430.8162 | 8158.9016 | 14430.8162 | 0.0016454 | 0.00061041 | 3.3899 | 8.6842 | 1936 | 3.4524e-05 | 2660 | 0 | 0 | 5.0697 | 1741 | 0
Central Coast | 3662 | 3 | 6.7662 | 31 | 18.2717 | 3 | 2.7222e-05 | 0.066432 | 1.3417 | 18.2457 | 65.4603 | 0.15839 | 0 | 0.21895 | 1 | 1.8084e-06 | 3.3135e-05 | 0.096774 | 0.37031 | {51B50550-2616-4B8D-8593-9330C414F251} | 183031101 | PALMER 1101 | M82 | 34.7369 | -120.2589 | PALMER 1101M82 | 240 | 474 | 51410.0855 | 24210.9534 | 27199.1321 | 16759.4337 | 8936.4007 | 9.9404e-05 | 8.1665e-05 | 2.2554 | 10.3333 | 2423 | 5.4252e-06 | 2661 | 0 | 0 | 10.4138 | 986 | 0
Bay Area | 645 | 77 | 242.0398 | 168 | 287.7246 | 16 | 2.7056e-05 | 0.066432 | 0.075555 | 0.039135 | 0.00068163 | 2.926e-07 | 1.4299 | 2.5021 | 1 | 1.7974e-06 | 1.9795e-05 | 0.45833 | 0.84122 | {FD5FE64E-C40E-49F6-A1B2-6062B4E7CFF6} | 12091102 | OAKLAND J 1102 | CR252 | 37.7877 | -122.2108 | OAKLAND J 1102CR252 | 224 | 1736 | 74767.1967 | 9897.4043 | 64869.7924 | 1754.2398 | 2370.1319 | 0.00031672 | 0.0004329 | 3.1434 | 10.5 | 2614 | 2.8758e-05 | 2662 | 0 | 0 | 1.09 | 2842 | 0
Bay Area | 2509 | 6 | 19.2213 | 18 | 26.6016 | 5 | 2.6828e-05 | 0.066432 | 1.4185 | 0.9549 | 4.1571 | 0.013054 | 0.65155 | 2.3343 | 1 | 1.7822e-06 | 3.3948e-05 | 0.33333 | 0.72256 | {B72D11A7-A3E3-4487-9B62-E0B9199739E9} | 14091101 | CASTRO VALLEY 1101 | MR204 | 37.6613 | -122.0557 | CASTRO VALLEY 1101MR204 | 122 | 288 | 17336.7925 | 4709.4304 | 12627.362 | 232.9604 | 2742.9841 | 0.00016974 | 0.00013414 | 3.2035 | 3.6 | 2414 | 8.9111e-06 | 2663 | 0 | 0 | 0.14475 | 2658 | 0
Bay Area | 3426 | 68 | 235.4741 | 320 | 367.9174 | 28 | 2.6756e-05 | 0.066432 | 0.1049 | 0.053861 | 0.038486 | 0.00022871 | 0.0083755 | 0.01909 | 0.10714 | 1.7774e-06 | 1.8298e-05 | 0.2125 | 0.64002 | {24F38127-D3B0-46CD-A96D-4474F1F7C2CF} | 24251104 | WOODSIDE 1104 | 9030 | 37.458 | -122.249 | WOODSIDE 11049030 | 76 | 338 | 17426.9412 | 4149.4333 | 13277.5079 | 3145.1983 | 9177.4557 | 0.00051234 | 0.00074916 | 3.4629 | 11.4286 | 2643 | 4.9768e-05 | 2664 | 0 | 0 | 1.9543 | 2805 | 0
North Valley | 2238 | 24 | 36.2932 | 865 | 460.9713 | 122 | 2.2705e-05 | 0.076855 | 5.5666 | 210.8484 | 4172.7881 | 50.6973 | 0.62709 | 10.552 | 1.0052 | 1.7533e-06 | 6.4236e-05 | 0.027746 | 0.078732 | {ED0B6774-A707-41C7-AD0B-86162B275429} | 102541101 | VOLTA 1101 | 85234 | 40.3481 | -121.6206 | VOLTA 110185234 | 143 | 466 | 26327.0541 | 12197.7117 | 14129.3424 | 12197.7117 | 14129.3424 | 0.0078368 | 0.00277 | 1.5122 | 7.0902 | 2104 | 0.0002139 | 2665 | 0 | 0 | 7.5793 | 991 | 0
Bay Area | 1112 | 128 | 286.0746 | 407 | 441.7765 | 54 | 2.6381e-05 | 0.066432 | 0.4257 | 0.26258 | 0.47709 | 0.0045021 | 0.71755 | 1.4332 | 0.72222 | 1.7526e-06 | 2.0456e-05 | 0.3145 | 0.64755 | {976CCE27-9CBA-45DD-8002-F8BFB98C14D4} | 24181103 | SAN CARLOS 1103 | 9148 | 37.4783 | -122.2474 | SAN CARLOS 11039148 | 292 | 1209 | 65871.2267 | 14673.9555 | 51197.2712 | 6379.4044 | 18535.032 | 0.0011046 | 0.0014246 | 2.235 | 7.537 | 2600 | 9.4639e-05 | 2666 | 0 | 0 | 3.964 | 2175 | 0
Bay Area | 386 | 118 | 279.2154 | 425 | 469.3789 | 40 | 2.7517e-05 | 0.06311 | 0.12629 | 0.089943 | 0.031902 | 5.0305e-06 | 0.65279 | 1.3992 | 0.925 | 1.7498e-06 | 1.5536e-05 | 0.27765 | 0.59486 | {B68C4BA8-94F5-4FA3-9062-8EFAD0B4F95D} | 24031103 | BELMONT 1103 | 8958 | 37.5064 | -122.2862 | BELMONT 11038958 | 192 | 800 | 43415.5899 | 9587.299 | 33828.2909 | 5350.191 | 18614.0034 | 0.00062145 | 0.0011007 | 2.3662 | 10.625 | 2693 | 6.9991e-05 | 2667 | 0 | 0 | 3.3245 | 2811 | 0
Bay Area | 1757 | 5 | 8.9848 | 10 | 11.2061 | 4 | 2.6328e-05 | 0.066432 | 0.010376 | 0.0012405 | 0.0015612 | 2.9042e-06 | 0 | 0.025 | 0.25 | 1.749e-06 | 1.4946e-05 | 0.5 | 0.80178 | {9CBBDE0D-F420-4BB3-A85F-B498925D2703} | 12060402 | BERKELEY F 0402 | circuit_breaker | 37.8725 | -122.278 | BERKELEY F 0402circuit_breaker | 104 | 444 | 16232.419 | 3376.7149 | 12855.704 | 226.0238 | 1666.1498 | 5.9784e-05 | 0.00010531 | 1.797 | 2.5 | 2707 | 6.9961e-06 | 2668 | 0 | 0 | 0.14044 | 2825 | 0
Bay Area | 2603 | 48 | 145.6705 | 119 | 185.1407 | 17 | 2.6252e-05 | 0.066432 | 0.36099 | 0.15885 | 2.3016 | 0.0058161 | 0.22918 | 0.70087 | 1 | 1.744e-06 | 2.0783e-05 | 0.40336 | 0.78681 | {4808F0D1-7684-45A4-AA78-2B2D6EF06890} | 12091106 | OAKLAND J 1106 | CR164 | 37.7664 | -122.1715 | OAKLAND J 1106CR164 | 217 | 1734 | 80854.5065 | 10525.9253 | 70328.5813 | 2328.9296 | 10556.1286 | 0.00035331 | 0.00044628 | 3.0348 | 7 | 2592 | 2.9647e-05 | 2669 | 0 | 0 | 1.4471 | 2818 | 0
Central Coast | 8948 | 13 | 17.5035 | 29 | 27.4837 | 4 | 2.6171e-05 | 0.066432 | 2.5316 | 25.475 | 43.4524 | 0.19581 | 0.74115 | 8.6602 | 1 | 1.7386e-06 | 6.0882e-05 | 0.44828 | 0.63687 | {DF06274D-82A7-4C1B-8F47-D036189DB7AF} | 83242105 | MORGAN HILL 2105 | XR602 | 37.1066 | -121.6568 | MORGAN HILL 2105XR602 | 23 | 24 | 3409.3424 | 1368.2778 | 2041.0645 | 356.9004 | 123.5152 | 0.00024353 | 0.00010469 | 1.3464 | 7.25 | 2128 | 6.9545e-06 | 2670 | 0 | 0 | 0.22177 | 1038 | 0
Bay Area | 6127 | 245 | 732.621 | 613 | 945.6083 | 67 | 2.9785e-05 | 0.058499 | 3.2085 | 2.0633 | 9.1775 | 0.1301 | 0.34715 | 1.189 | 1.4627 | 1.7382e-06 | 5.503e-05 | 0.39967 | 0.77476 | {A1C4F4D6-01EE-430E-BE68-0AE547BD756D} | 12541106 | OAKLAND X 1106 | CR008 | 37.8095 | -122.191 | OAKLAND X 1106CR008 | 150 | 542 | 35211.1072 | 7102.0164 | 28109.0908 | 7102.0164 | 28109.0908 | 0.003687 | 0.0019956 | 2.9903 | 9.1493 | 2191 | 0.00011646 | 2671 | 0 | 0 | 4.413 | 2261 | 0
Bay Area | 3736 | 11 | 24.7322 | 30 | 35.2107 | 3 | 2.6043e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7301e-06 | 1.8135e-05 | 0.36667 | 0.7024 | {E6E93162-4459-4248-A579-2775F57735F8} | 42031120 | ALTO 1120 | 500 | 37.88 | -122.5278 | ALTO 1120500 | 95 | 459 | 26563.3806 | 5126.8034 | 21436.5772 | 498.0083 | 2020.3081 | 5.4405e-05 | 7.813e-05 | 2.2484 | 10 | 2645 | 5.1903e-06 | 2672 | 0 | 0 | 0.30945 | 657 | 0
Central Coast | 4406 | 130 | 469.8222 | 162 | 489.3939 | 13 | 2.6035e-05 | 0.066432 | 2.6574 | 3.3373 | 6.3151 | 0.023116 | 0.10722 | 0.44428 | 1 | 1.7296e-06 | 4.2749e-05 | 0.80247 | 0.96001 | {D532A486-3F7F-4A83-AD8F-DB3333DA04B9} | 182852202 | VIEJO 2202 | 85904 | 36.5981 | -121.9245 | VIEJO 220285904 | 51 | 363 | 20214.3681 | 3179.0036 | 17035.3645 | 1316.0449 | 4391.9949 | 0.00055574 | 0.00033845 | 3.614 | 12.4615 | 2302 | 2.2484e-05 | 2673 | 0 | 0 | 0.81775 | 2694 | 0
Sierra | 10107 | 1 | 1.3586 | 1 | 1.3586 | 1 | 2.601e-05 | 0.066432 | 31.3807 | 114.8399 | 606.4609 | 22.5184 | 1.6097e-14 | 0.13606 | 1 | 1.7279e-06 | 0.00081623 | 1 | 1 | {3AE21CFF-B1F8-4F68-931E-FCCDD52142DD} | 152481104 | BRUNSWICK 1104 | 761310 | 39.2675 | -121.0555 | BRUNSWICK 1104761310 | 4 | 1 | 53.1948 | 43.1053 | 10.0895 | 43.1053 | 10.0895 | 0.00081623 | 2.601e-05 | 1.3586 | 1 | 490 | 1.7279e-06 | 2674 | 0 | 0 | 0.026784 | 132 | 0
North Coast | 197 | 0 | 0 | 1 | 0.42703 | 1 | 2.5785e-05 | 0.066431 |  |  |  |  | 0 | 0 | 0 | 1.7129e-06 | 2.5785e-05 | 0 | 0 | {3706FF29-9CD7-48BA-89F8-13A11ECD321F} | 42631109 | PETALUMA C 1109 | 270 | 38.2225 | -122.6388 | PETALUMA C 1109270 | 293 | 1107 | 59017.9245 | 12322.9722 | 46694.9522 | 2986.7863 | 6430.8011 | 2.5785e-05 | 2.5785e-05 |  | 1 | 2519 | 1.7129e-06 | 2675 | 0 | 0 | 1.8559 | 1377 | 0
Central Coast | 6784 | 45 | 70.3741 | 198 | 146.2477 | 29 | 2.3469e-05 | 0.07564 | 0.080642 | 21.6244 | 47.4387 | 0.017716 | 0.64525 | 14.9866 | 0.98955 | 1.707e-06 | 1.0124e-05 | 0.22727 | 0.4812 | {966AAD61-7205-4A6B-9491-7F1C72E1ED94} | 182731102 | RESERVATION ROAD 1102 | 3032 | 36.6338 | -121.6986 | RESERVATION ROAD 11023032 | 107 | 74 | 20240.1979 | 15612.677 | 4627.521 | 4109.0682 | 2724.3416 | 0.00029361 | 0.00068061 | 1.5639 | 6.8276 | 2789 | 4.9503e-05 | 2676 | 0 | 0 | 2.5533 | 348 | 0
Central Coast | 6768 | 199 | 488.9836 | 256 | 519.4398 | 25 | 4.1042e-05 | 0.045174 | 3.2827 | 3.5037 | 9.9467 | 0.078745 | 0.19867 | 2.2593 | 2.28 | 1.7043e-06 | 0.00010295 | 0.77734 | 0.94137 | {F6BA7330-C23E-4354-B987-13A0DB7C9D56} | 182291102 | HATTON 1102 | 9642 | 36.5085 | -121.9366 | HATTON 11029642 | 57 | 68 | 4493.8186 | 1925.8934 | 2567.9252 | 1925.8934 | 2567.9252 | 0.0025738 | 0.0010261 | 2.4572 | 10.24 | 1840 | 4.2607e-05 | 2677 | 0 | 0 | 1.1967 | 1556 | 0
North Coast | 451 | 0 | 0 | 4 | 1.8229 | 1 | 2.564e-05 | 0.066432 | 1.6127 | 0.99186 | 5.022 | 0.0090799 | 1.9646 | 0.09823 | 1 | 1.7033e-06 | 4.1351e-05 | 0 | 0 | {D91DE9C6-DAB2-43C2-806F-267EA9087948} | 43211102 | HARTLEY 1102 | 824 | 39.0723 | -122.915 | HARTLEY 1102824 | 213 | 479 | 42980.7955 | 12575.4803 | 30405.3152 | 137.5107 | 157.9055 | 4.1351e-05 | 2.564e-05 |  | 4 | 2319 | 1.7033e-06 | 2678 | 0 | 0 | 0.085445 | 2017 | 0
Bay Area | 4110 | 29 | 69.9677 | 119 | 120.8368 | 16 | 3.64e-05 | 0.045672 | 4.193 | 11.3088 | 33.8261 | 0.66917 | 0.15831 | 8.2151 | 2.2517 | 1.7013e-06 | 7.7744e-05 | 0.2437 | 0.57903 | {B787A327-E708-4D5C-865B-C65998470D53} | 14341106 | VALLEY VIEW 1106 | P176 | 37.9566 | -122.2694 | VALLEY VIEW 1106P176 | 133 | 644 | 36976.0747 | 6680.3499 | 30295.7248 | 1598.933 | 7858.7548 | 0.0012439 | 0.0005824 | 2.4127 | 7.4375 | 2001 | 2.722e-05 | 2679 | 0 | 0 | 0.99353 | 2665 | 0
Bay Area | 181 | 7 | 18.3599 | 50 | 43.7573 | 9 | 2.5509e-05 | 0.066432 | 0.77644 | 1.1902 | 4.4128 | 0.022534 | 0.073009 | 1.0271 | 1 | 1.6946e-06 | 2.3066e-05 | 0.14 | 0.41959 | {2D08B37D-CF98-45C7-A5AE-9DEB997F2ACC} | 13480401 | ESTUDILLO 0401 | circuit_breaker | 37.7272 | -122.1387 | ESTUDILLO 0401circuit_breaker | 115 | 983 | 47201.8376 | 7573.1193 | 39628.7183 | 1368.0825 | 3038.7483 | 0.00020759 | 0.00022958 | 2.6228 | 5.5556 | 2567 | 1.5252e-05 | 2680 | 0 | 0 | 0.85009 | 2196 | 0
Bay Area | 9368 | 1 | 1.6135 | 11 | 8.1279 | 2 | 2.5415e-05 | 0.066432 |  |  |  |  | 4.427 | 28.1473 | 1.0044 | 1.6884e-06 | 2.5415e-05 | 0.090909 | 0.19852 | {D8E4C9CA-7EEB-49BA-880B-C873380BC8EB} | 14091106 | CASTRO VALLEY 1106 | MR233 | 37.7049 | -122.0548 | CASTRO VALLEY 1106MR233 | 22 | 16 | 1811.7034 | 1023.3375 | 788.3659 | 164.9976 | 231.8901 | 5.083e-05 | 5.083e-05 | 1.6135 | 5.5 | 2530 | 3.3768e-06 | 2681 | 0 | 0 | 0.10252 | 753 | 0
Bay Area | 4813 | 113 | 371.2793 | 364 | 513.4789 | 49 | 2.5308e-05 | 0.066432 | 0.28134 | 0.70364 | 2.2748 | 0.005709 | 0.25135 | 1.7093 | 1 | 1.6813e-06 | 1.6544e-05 | 0.31044 | 0.72307 | {C2D0F25E-59C9-41E0-A6F7-60C91C33934C} | 13681112 | EDES 1112 | CR282 | 37.7543 | -122.1482 | EDES 1112CR282 | 89 | 478 | 30294.5359 | 6573.0208 | 23721.5151 | 6573.0208 | 23721.5151 | 0.00081064 | 0.0012401 | 3.2857 | 7.4286 | 2670 | 8.2382e-05 | 2682 | 0 | 0 | 4.0843 | 2387 | 0
Central Coast | 1079 | 9 | 34.2046 | 9 | 34.2046 | 3 | 2.5164e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0 | 0.070206 | 0.66667 | 1.6717e-06 | 1.8587e-05 | 1 | 1 | {410C255F-3E61-44D1-A47D-CA8172B6BCA6} | 182852201 | VIEJO 2201 | 2064 | 36.5823 | -121.9204 | VIEJO 22012064 | 37 | 76 | 4943.748 | 1409.3976 | 3534.3504 | 1409.3976 | 3534.3504 | 5.5762e-05 | 7.5492e-05 | 3.8005 | 3 | 2639 | 5.0151e-06 | 2683 | 0 | 0 | 0.87576 | 295 | 0
North Coast | 160 | 22 | 46.7599 | 31 | 51.0856 | 5 | 3.9491e-05 | 0.039858 | 3.2398 | 9.3406 | 27.5205 | 0.17832 | 0.0088496 | 0.2031 | 2.6168 | 1.6696e-06 | 7.9788e-05 | 0.70968 | 0.91533 | {D1AA7A01-6717-4A8D-8AC5-0F1F18BEAC1F} | 43491103 | CORONA 1103 | 4446 | 38.2842 | -122.6683 | CORONA 11034446 | 242 | 539 | 49903.899 | 19753.849 | 30150.05 | 734.2401 | 1771.5366 | 0.00039894 | 0.00019746 | 2.1254 | 6.2 | 1984 | 8.3481e-06 | 2684 | 0 | 0 | 0.45624 | 2762 | 0
Central Coast | 1767 | 0 | 0 | 1 | 0.45574 | 1 | 2.4776e-05 | 0.066432 |  |  |  |  | 0.073009 | 0.0073009 | 1 | 1.6459e-06 | 2.4776e-05 | 0 | 0 | {534A451C-57DA-44B8-B8BC-2F5C24A553D0} | 83242105 | MORGAN HILL 2105 | XR578 | 37.1273 | -121.6629 | MORGAN HILL 2105XR578 | 29 | 78 | 4202.438 | 1108.6732 | 3093.7648 | 251.9162 | 435.8843 | 2.4776e-05 | 2.4776e-05 |  | 1 | 2538 | 1.6459e-06 | 2685 | 0 | 0 | 0.15653 | 883 | 0
Bay Area | 2447 | 64 | 162.2245 | 161 | 211.3727 | 28 | 2.4631e-05 | 0.066432 | 0.1738 | 0.079103 | 0.00049246 | 2.401e-07 | 0.005452 | 0.1493 | 0.5 | 1.6363e-06 | 1.5095e-05 | 0.39752 | 0.76748 | {4B35CC98-8B7D-4556-87A5-A4000634AA4A} | 24181104 | SAN CARLOS 1104 | 8846 | 37.4895 | -122.2655 | SAN CARLOS 11048846 | 149 | 813 | 40104.2557 | 7060.9917 | 33043.264 | 3326.5951 | 12748.7827 | 0.00042267 | 0.00068966 | 2.5348 | 5.75 | 2703 | 4.5816e-05 | 2686 | 0 | 0 | 2.067 | 2822 | 0
Bay Area | 2724 | 3 | 9.6594 | 26 | 21.4639 | 4 | 2.4547e-05 | 0.066432 | 0 | 0 | 0 | 0 | 1.0791 | 0.23695 | 1 | 1.6307e-06 | 1.6273e-05 | 0.11538 | 0.45003 | {176C1DEF-377C-4002-9F9A-8DF61DB4715B} | 12501112 | EL CERRITO G 1112 | BR180 | 37.9416 | -122.3127 | EL CERRITO G 1112BR180 | 66 | 554 | 23117.5743 | 3108.6276 | 20008.9467 | 850.589 | 6823.0358 | 6.5093e-05 | 9.8188e-05 | 3.2198 | 6.5 | 2678 | 6.5228e-06 | 2687 | 0 | 0 | 0.52853 | 2744 | 0
Bay Area | 226 | 39 | 87.7853 | 158 | 153.5602 | 12 | 2.4484e-05 | 0.066432 | 1.7385 | 1.6642 | 10.9011 | 0.063043 | 0.28743 | 1.1117 | 1 | 1.6265e-06 | 3.0415e-05 | 0.24684 | 0.57167 | {EE04BD96-5787-4D66-B00B-BC1201689111} | 24060404 | CAROLANDS 0404 | 9026 | 37.5586 | -122.3566 | CAROLANDS 04049026 | 172 | 595 | 33567.2247 | 8105.233 | 25461.9917 | 1254.4036 | 2191.4703 | 0.00036498 | 0.00029381 | 2.2509 | 13.1667 | 2467 | 1.9518e-05 | 2688 | 0 | 0 | 0.77945 | 2798 | 0
Central Coast | 2301 | 10 | 15.2073 | 20 | 21.1088 | 3 | 1.7734e-05 | 0.10882 | 17.5611 | 158.6701 | 520.1456 | 9.1413 | 7.0885 | 56.608 | 1.0029 | 1.6257e-06 | 0.00022033 | 0.5 | 0.72042 | {2C56B704-0B48-474B-86AD-67CE86231708} | 83242106 | MORGAN HILL 2106 | circuit_breaker | 37.1267 | -121.659 | MORGAN HILL 2106circuit_breaker | 117 | 172 | 16081.749 | 6109.6825 | 9972.0666 | 0 | 1529.3175 | 0.000661 | 5.3202e-05 | 1.5207 | 6.6667 | 1342 | 4.877e-06 | 2689 | 0 | 0 | 0 | 2461 | 0
Bay Area | 7692 | 28 | 46.8565 | 143 | 109.6625 | 10 | 2.4283e-05 | 0.066432 | 0.13938 | 0.072779 | 0.055261 | 1.9309e-05 | 0 | 0.049425 | 0.5 | 1.6131e-06 | 9.2559e-06 | 0.1958 | 0.42728 | {64F4E128-0BF2-4FD7-B86A-5EB41BF3367E} | 24251104 | WOODSIDE 1104 | 11555 | 37.4675 | -122.2641 | WOODSIDE 110411555 | 30 | 125 | 6109.7573 | 1379.9837 | 4729.7736 | 1379.9837 | 4729.7736 | 9.2559e-05 | 0.00024283 | 1.6734 | 14.3 | 2795 | 1.6131e-05 | 2690 | 0 | 0 | 0.85748 | 2307 | 0
Bay Area | 1941 | 0 | 0 | 3 | 1.3672 | 1 | 2.4194e-05 | 0.066432 | 0.47465 | 0.22182 | 0.0016742 | 7.9846e-07 | 0 | 0.10044 | 1 | 1.6072e-06 | 1.1484e-05 | 0 | 0 | {24F66B4A-94A3-4B18-925C-2BF0060C2435} | 24141102 | RALSTON 1102 | 2028 | 37.5114 | -122.3193 | RALSTON 11022028 | 84 | 210 | 15061.7742 | 3748.0499 | 11313.7243 | 2900.1535 | 10961.6769 | 1.1484e-05 | 2.4194e-05 |  | 3 | 2769 | 1.6072e-06 | 2691 | 0 | 0 | 1.8021 | 2751 | 0
Central Coast | 4930 | 74 | 204.7233 | 575 | 517.9263 | 36 | 2.4032e-05 | 0.066432 | 0.24509 | 4.7704 | 14.5547 | 0.016967 | 0.16279 | 4.3908 | 1.0044 | 1.5965e-06 | 1.5597e-05 | 0.1287 | 0.39527 | {53A81FCC-6CE7-4EE5-B8F1-AB89BF2F3989} | 182222104 | DEL MONTE 2104 | 9096 | 36.5951 | -121.8454 | DEL MONTE 21049096 | 168 | 379 | 32418.9088 | 10640.4265 | 21778.4823 | 4576.3876 | 1251.6669 | 0.00056151 | 0.00086513 | 2.7665 | 15.9722 | 2691 | 5.7473e-05 | 2692 | 0 | 0 | 2.8436 | 337 | 0
North Valley | 4020 | 4 | 11.4126 | 5 | 11.8684 | 1 | 2.4027e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0 | 0.043805 | 1 | 1.5962e-06 | 0 | 0.8 | 0.9616 | {2AA24801-8300-4851-B080-261023387F10} | 103311102 | BURNEY 1102 | 57046 | 40.8832 | -121.664 | BURNEY 110257046 | 31 | 73 | 3452.9703 | 1135.0639 | 2317.9064 | 77.1037 | 235.4293 | 0 | 2.4027e-05 | 2.8532 | 5 | 2899 | 1.5962e-06 | 2693 | 0 | 0 | 0.04791 | 2213 | 0
Bay Area | 4178 | 80 | 202.56 | 352 | 352.0822 | 45 | 2.3979e-05 | 0.066432 | 0.39101 | 0.18367 | 0.49186 | 0.0020699 | 0.044346 | 0.03737 | 0.37778 | 1.593e-06 | 1.6457e-05 | 0.22727 | 0.57532 | {18156E3B-3444-414F-97B1-9EC6878D0720} | 24080402 | EMERALD LAKE 0402 | 8872 | 37.4638 | -122.2719 | EMERALD LAKE 04028872 | 167 | 666 | 35999.8277 | 9034.3623 | 26965.4654 | 7185.3167 | 19415.2551 | 0.00074056 | 0.001079 | 2.532 | 7.8222 | 2671 | 7.1683e-05 | 2694 | 0 | 0 | 4.4647 | 2303 | 0
Central Coast | 2515 | 8 | 21.1074 | 13 | 24.0582 | 4 | 9.9881e-06 | 0.14273 | 0 | 0 | 0 | 0 | 0.048673 | 27.1108 | 1.0044 | 1.5687e-06 | 3.1125e-06 | 0.61538 | 0.87735 | {C1DCB446-91BC-4976-8E19-E90A61136DD7} | 182222104 | DEL MONTE 2104 | 2032 | 36.5973 | -121.8479 | DEL MONTE 21042032 | 187 | 1045 | 59365.4457 | 9676.4913 | 49688.9544 | 253.941 | 215.1176 | 1.245e-05 | 3.9953e-05 | 2.6384 | 3.25 | 2863 | 6.2748e-06 | 2695 | 0 | 0 | 0.15779 | 1195 | 0
North Valley | 5708 | 136 | 178.1274 | 235 | 230.1509 | 31 | 2.9574e-05 | 0.051431 | 23.1609 | 334.0007 | 7764.9138 | 1076.275 | 0.69332 | 7.9697 | 1.9046 | 1.5672e-06 | 0.00043 | 0.57872 | 0.77396 | {59C7C56F-8F8D-453D-B2CA-2A56446D1413} | 102551101 | EAST QUINCY 1101 | 2452 | 39.935 | -120.91 | EAST QUINCY 11012452 | 236 | 740 | 43346.2252 | 13369.3596 | 29976.8656 | 2653.0626 | 2912.581 | 0.01333 | 0.00091679 | 1.3098 | 7.5806 | 890 | 4.8583e-05 | 2696 | 0 | 0 | 1.6485 | 2628 | 0
Central Coast | 5032 | 37 | 114.1435 | 70 | 133.7698 | 9 | 2.3464e-05 | 0.066432 | 7.4862 | 10.421 | 19.0893 | 0.43251 | 0.16544 | 0.84186 | 1 | 1.5588e-06 | 8.9061e-05 | 0.52857 | 0.85328 | {3A16450D-C56F-42B5-80F8-8369EAD6F0C2} | 182852202 | VIEJO 2202 | 9120 | 36.6022 | -121.9359 | VIEJO 22029120 | 234 | 785 | 48641.662 | 11893.6537 | 36748.0083 | 2530.9244 | 8236.8552 | 0.00080155 | 0.00021118 | 3.085 | 7.7778 | 1919 | 1.4029e-05 | 2697 | 0 | 0 | 1.5726 | 2584 | 0
Bay Area | 1306 | 27 | 72.8681 | 109 | 112.662 | 21 | 2.3429e-05 | 0.066432 | 0.027798 | 0.0061463 | 0.053293 | 0.00018081 | 1.0714 | 0.45354 | 0.38095 | 1.5564e-06 | 1.0312e-05 | 0.24771 | 0.64678 | {854414CD-0C09-471D-91AA-83170F69D473} | 13170401 | HOLLYWOOD 0401 | circuit_breaker | 37.8127 | -122.2187 | HOLLYWOOD 0401circuit_breaker | 150 | 1539 | 73853.3941 | 8515.2971 | 65338.097 | 4478.6501 | 31120.634 | 0.00021656 | 0.000492 | 2.6988 | 5.1905 | 2781 | 3.2684e-05 | 2698 | 0 | 0 | 2.7829 | 898 | 0
Bay Area | 7151 | 47 | 156.7815 | 86 | 176.9315 | 10 | 2.3415e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0.0066372 | 0.30555 | 1 | 1.5555e-06 | 1.2847e-05 | 0.54651 | 0.88611 | {1CFCF663-0CF6-44D7-93F9-73671725C761} | 13681112 | EDES 1112 | CR306 | 37.7522 | -122.1528 | EDES 1112CR306 | 42 | 112 | 6419.2803 | 1619.5833 | 4799.697 | 1619.5833 | 4799.697 | 0.00012847 | 0.00023415 | 3.3358 | 8.6 | 2747 | 1.5555e-05 | 2699 | 0 | 0 | 1.0064 | 717 | 0
Bay Area | 3308 | 6 | 9.883 | 11 | 12.6212 | 4 | 2.3413e-05 | 0.066431 | 3.1478 | 4.1143 | 14.802 | 0.093188 | 0.092367 | 0.023507 | 1 | 1.5554e-06 | 3.7629e-05 | 0.54545 | 0.78305 | {10EE43CC-0DC9-4A02-A6E3-072C86D8499C} | 43091104 | GREENBRAE 1104 | 751 | 37.9192 | -122.5052 | GREENBRAE 1104751 | 63 | 527 | 30727.8629 | 5014.0519 | 25713.811 | 342.6723 | 1689.1107 | 0.00015051 | 9.3654e-05 | 1.6472 | 2.75 | 2367 | 6.2216e-06 | 2700 | 0 | 0 | 0.21293 | 2495 | 0
Central Coast | 1993 | 166 | 371.8963 | 575 | 592.8869 | 44 | 2.3401e-05 | 0.066432 | 0.17703 | 0.24572 | 0.50794 | 0.00074717 | 0.23577 | 2.604 | 0.84202 | 1.5546e-06 | 1.2903e-05 | 0.2887 | 0.62726 | {128CFE15-7FAD-449A-AC53-530ECD1ABDFD} | 83431116 | HICKS 1116 | LB16 | 37.2394 | -121.9278 | HICKS 1116LB16 | 261 | 1113 | 62518.2447 | 14726.4924 | 47791.7523 | 4954.2992 | 9527.5513 | 0.00056775 | 0.0010297 | 2.2403 | 13.0682 | 2745 | 6.8402e-05 | 2701 | 0 | 0 | 3.0785 | 2519 | 0
Bay Area | 369 | 116 | 305.1356 | 342 | 434.7057 | 23 | 2.3385e-05 | 0.066432 | 0.038769 | 0.04699 | 0.00036778 | 6.7722e-08 | 0.53126 | 2.4926 | 0.8763 | 1.5535e-06 | 9.1522e-06 | 0.33918 | 0.70194 | {E9CC44B0-F274-485D-B5C7-CF59D96240F4} | 24040403 | BERESFORD 0403 | circuit_breaker | 37.5648 | -122.3193 | BERESFORD 0403circuit_breaker | 161 | 892 | 43593.5891 | 8781.4305 | 34812.1586 | 1971.1564 | 3475.5666 | 0.0002105 | 0.00053787 | 2.6305 | 14.8696 | 2796 | 3.5731e-05 | 2702 | 0 | 0 | 1.2248 | 2308 | 0
Bay Area | 4320 | 25 | 69.5264 | 66 | 88.0398 | 9 | 2.3229e-05 | 0.066432 | 1.8404 | 0.44479 | 2.1702 | 0.011982 | 0.00049164 | 0.13626 | 0.33333 | 1.5432e-06 | 3.3876e-05 | 0.37879 | 0.78972 | {42F99BA0-D146-40B7-AEEE-A7B52478E064} | 12541101 | OAKLAND X 1101 | CR224 | 37.8153 | -122.2224 | OAKLAND X 1101CR224 | 41 | 139 | 7479.799 | 1751.285 | 5728.5141 | 791.862 | 3025.2785 | 0.00030488 | 0.00020906 | 2.7811 | 7.3333 | 2415 | 1.3889e-05 | 2703 | 0 | 0 | 0.49204 | 2737 | 0
Bay Area | 543 | 24 | 48.1854 | 46 | 59.4614 | 5 | 2.3159e-05 | 0.066432 | 0.034942 | 0.074131 | 0.095841 | 1.0046e-05 | 0.13053 | 0.14181 | 1 | 1.5385e-06 | 1.2281e-05 | 0.52174 | 0.81037 | {FB7430F5-69AD-42E3-8B5B-42F0E8A7B1F0} | 42031120 | ALTO 1120 | 88190 | 37.8868 | -122.5247 | ALTO 112088190 | 117 | 442 | 23112.3981 | 5023.293 | 18089.1051 | 530.6966 | 872.407 | 6.1406e-05 | 0.0001158 | 2.0077 | 9.2 | 2758 | 7.6926e-06 | 2704 | 0 | 0 | 0.32976 | 2853 | 0
Central Coast | 6898 | 11 | 37.8287 | 11 | 37.8287 | 3 | 2.3139e-05 | 0.066432 |  |  |  |  | 0.5826 | 0.075885 | 1 | 1.5371e-06 | 2.3139e-05 | 1 | 1 | {45F66B28-3708-48B3-AEFE-0F1CE66015AD} | 182440422 | PACIFIC GROVE 0422 | 2614 | 36.6076 | -121.9243 | PACIFIC GROVE 04222614 | 55 | 164 | 10954.0181 | 3446.6772 | 7507.3409 | 283.1092 | 326.3877 | 6.9416e-05 | 6.9416e-05 | 3.439 | 3.6667 | 2562 | 4.6114e-06 | 2705 | 0 | 0 | 0.17592 | 1829 | 0
Bay Area | 40 | 88 | 193.3954 | 271 | 294.4545 | 53 | 2.3089e-05 | 0.066432 | 0.19957 | 0.078606 | 0.065994 | 0.00014138 | 0.19932 | 0.18572 | 0.86792 | 1.5338e-06 | 1.3565e-05 | 0.32472 | 0.65679 | {73C37461-BB3B-432F-BC96-82FA7CA2E859} | 24251104 | WOODSIDE 1104 | 555372 | 37.4608 | -122.259 | WOODSIDE 1104555372 | 114 | 522 | 29513.3046 | 6600.4202 | 22912.8843 | 6600.4202 | 22912.8843 | 0.00071895 | 0.0012237 | 2.1977 | 5.1132 | 2732 | 8.1294e-05 | 2706 | 0 | 0 | 4.1013 | 2867 | 0
Bay Area | 6845 | 6 | 9.3025 | 12 | 12.933 | 2 | 2.3033e-05 | 0.066432 | 0.72186 | 0.204 | 0.36128 | 0.00028626 | 0.51991 | 0.24757 | 1 | 1.5301e-06 | 1.941e-05 | 0.5 | 0.71928 | {4B13830E-5EE9-44B1-B1EB-50CAC91FBF54} | 12501112 | EL CERRITO G 1112 | 57953 | 37.9435 | -122.3119 | EL CERRITO G 111257953 | 21 | 202 | 8923.1735 | 1217.1907 | 7705.9827 | 188.8354 | 1299.7368 | 3.8819e-05 | 4.6067e-05 | 1.5504 | 6 | 2620 | 3.0603e-06 | 2707 | 0 | 0 | 0.11734 | 2823 | 0
Central Coast | 136 | 73 | 182.1581 | 432 | 369.821 | 51 | 2.2753e-05 | 0.06718 | 1.3832 | 2.3349 | 8.1325 | 0.046902 | 0.26167 | 1.7473 | 1.0033 | 1.5223e-06 | 3.5754e-05 | 0.16898 | 0.49256 | {5EA14457-409E-4700-8C2E-71D96DB5E68C} | 183011102 | MORRO BAY 1102 | W34 | 35.3109 | -120.8251 | MORRO BAY 1102W34 | 202 | 368 | 32896.7111 | 15381.6099 | 17515.1011 | 11103.8333 | 12420.7837 | 0.0018235 | 0.0011604 | 2.4953 | 8.4706 | 2388 | 7.7636e-05 | 2708 | 0 | 0 | 6.8996 | 682 | 0
Central Coast | 7806 | 52 | 121.4384 | 129 | 165.3554 | 9 | 2.2879e-05 | 0.066432 | 1.934 | 1.2546 | 4.9667 | 0.047613 | 0 | 0.11315 | 0.88889 | 1.5199e-06 | 3.1724e-05 | 0.4031 | 0.73441 | {7DB70BC4-94B0-4E36-9BF7-CCF146742A63} | 182852202 | VIEJO 2202 | 9089 | 36.6057 | -121.938 | VIEJO 22029089 | 40 | 191 | 11578.2118 | 2685.7224 | 8892.4894 | 2193.9182 | 6817.2226 | 0.00028551 | 0.00020591 | 2.3354 | 14.3333 | 2444 | 1.3679e-05 | 2709 | 0 | 0 | 1.3632 | 2228 | 0
Central Coast | 3322 | 671 | 2197.4867 | 1071 | 2427.9468 | 75 | 2.3221e-05 | 0.063775 | 3.669 | 1.8147 | 4.7502 | 0.047155 | 0.42081 | 0.2338 | 0.85333 | 1.5079e-06 | 6.5056e-05 | 0.62652 | 0.90508 | {AD318D3F-F8E0-477A-9CA4-DF6AF7B738B6} | 182852202 | VIEJO 2202 | 9104 | 36.5869 | -121.9142 | VIEJO 22029104 | 172 | 782 | 46919.0834 | 9586.0766 | 37333.0068 | 9288.626 | 34382.1791 | 0.0048792 | 0.0017416 | 3.2749 | 14.28 | 2092 | 0.00011309 | 2710 | 0 | 0 | 5.7717 | 2832 | 0
Bay Area | 7828 | 15 | 33.0905 | 42 | 46.7109 | 11 | 2.2501e-05 | 0.066432 | 0.091413 | 0.041171 | 0.021337 | 9.1081e-06 | 0.090909 | 0.14216 | 0.63636 | 1.4948e-06 | 1.3778e-05 | 0.35714 | 0.70841 | {67E8FE67-3DED-400C-8861-70D52FCAFB0E} | 12091102 | OAKLAND J 1102 | CR254 | 37.7974 | -122.1858 | OAKLAND J 1102CR254 | 53 | 397 | 19649.0283 | 2477.3187 | 17171.7095 | 1602.2826 | 10591.0011 | 0.00015156 | 0.00024751 | 2.206 | 3.8182 | 2726 | 1.6443e-05 | 2711 | 0 | 0 | 0.99561 | 2881 | 0
Bay Area | 5793 | 1 | 1.6135 | 6 | 3.8348 | 2 | 2.2303e-05 | 0.066432 | 0.6884 | 0.12668 | 0.05179 | 6.2588e-05 | 0 | 0 | 0 | 1.4816e-06 | 1.558e-05 | 0.16667 | 0.42076 | {4C49C25B-7AC8-408B-8A99-E4CB51688164} | 24251102 | WOODSIDE 1102 | 8862 | 37.4585 | -122.2437 | WOODSIDE 11028862 | 103 | 770 | 38463.3684 | 6135.6911 | 32327.6773 | 97.31 | 522.5673 | 3.1161e-05 | 4.4606e-05 | 1.6135 | 3 | 2692 | 2.9632e-06 | 2712 | 0 | 0 | 0.060466 | 2631 | 0
Central Coast | 3771 | 239 | 700.8263 | 766 | 1019.2809 | 80 | 1.9481e-05 | 0.071447 | 1.0858 | 18.0812 | 47.2662 | 0.16583 | 1.2765 | 16.0424 | 1.1181 | 1.4803e-06 | 1.7866e-05 | 0.31201 | 0.68757 | {593FA41B-396B-4601-BD50-0DE927CB7E5A} | 182291101 | HATTON 1101 | 2026 | 36.5315 | -121.8373 | HATTON 11012026 | 235 | 393 | 36545.2508 | 16427.734 | 20117.5167 | 7951.2018 | 11249.1213 | 0.0014293 | 0.0015585 | 2.9323 | 9.575 | 2653 | 0.00011843 | 2713 | 0 | 0 | 4.9406 | 2505 | 0
Central Coast | 2408 | 91 | 327.5664 | 118 | 344.5879 | 13 | 2.2175e-05 | 0.066432 | 1.16 | 3.9442 | 12.4607 | 0.035247 | 0.22668 | 0.63405 | 1 | 1.4731e-06 | 2.5726e-05 | 0.77119 | 0.9506 | {BEBF2F35-AA76-45BC-AFD8-E27852839913} | 182852202 | VIEJO 2202 | 9112 | 36.6048 | -121.9339 | VIEJO 22029112 | 119 | 440 | 25409.0833 | 5823.4278 | 19585.6555 | 1129.5145 | 2069.2012 | 0.00033444 | 0.00028827 | 3.5996 | 9.0769 | 2522 | 1.9151e-05 | 2714 | 0 | 0 | 0.70185 | 1871 | 0
Central Coast | 1081 | 92 | 253.6531 | 155 | 288.5745 | 15 | 2.4155e-05 | 0.062003 | 2.7819 | 5.7377 | 15.0086 | 0.2091 | 0.47803 | 4.0944 | 1.2667 | 1.4618e-06 | 4.6738e-05 | 0.59355 | 0.87899 | {572A903E-D7FD-4349-978F-5FBD205DDA11} | 182222103 | DEL MONTE 2103 | 86496 | 36.5937 | -121.873 | DEL MONTE 210386496 | 271 | 479 | 29625.8247 | 11778.9092 | 17846.9155 | 1909.93 | 2687.5835 | 0.00070107 | 0.00036233 | 2.7571 | 10.3333 | 2270 | 2.1926e-05 | 2715 | 0 | 0 | 1.1868 | 2117 | 0
Central Coast | 6816 | 7 | 18.1285 | 7 | 18.1285 | 1 | 2.1898e-05 | 0.066432 |  |  |  |  | 0.0022124 | 0.15907 | 1 | 1.4548e-06 | 2.1898e-05 | 1 | 1 | {B1F37713-3EC7-40D5-8605-FC72CCDF028E} | 83431115 | HICKS 1115 | 12494 | 37.2435 | -121.9378 | HICKS 111512494 | 96 | 310 | 16330.6103 | 4186.1864 | 12144.4239 | 84.655 | 101.4222 | 2.1898e-05 | 2.1898e-05 | 2.5898 | 7 | 2577 | 1.4548e-06 | 2716 | 0 | 0 | 0.052602 | 859 | 0
Bay Area | 4812 | 39 | 109.1659 | 101 | 142.7932 | 19 | 2.6287e-05 | 0.059439 | 0.23233 | 0.27117 | 0.39637 | 0.00061003 | 1.0851 | 7.5099 | 1.4231 | 1.4532e-06 | 1.6336e-05 | 0.38614 | 0.7645 | {22481AA9-CE3A-4C9E-8438-4DBF082EDD18} | 14091108 | CASTRO VALLEY 1108 | circuit_breaker | 37.6913 | -122.0615 | CASTRO VALLEY 1108circuit_breaker | 115 | 156 | 12990.0712 | 4549.646 | 8440.4252 | 2110.9437 | 4182.109 | 0.00031039 | 0.00049945 | 2.7991 | 5.3158 | 2676 | 2.7611e-05 | 2717 | 0 | 0 | 1.3117 | 2730 | 0
Bay Area | 745 | 7 | 25.653 | 9 | 26.7598 | 2 | 4.3744e-05 | 0.033216 | 2.8763 | 4.1151 | 10.5101 | 0.063715 | 1.2854 | 17.1927 | 3 | 1.4443e-06 | 0.00012648 | 0.77778 | 0.95864 | {957F3B05-D3E6-46BF-B6B1-74EF9A986684} | 13531102 | LAKEWOOD 1102 | circuit_breaker | 37.9092 | -122.0572 | LAKEWOOD 1102circuit_breaker | 300 | 895 | 52910.1038 | 15408.0523 | 37502.0515 | 153.4063 | 259.1331 | 0.00025296 | 8.7487e-05 | 3.6647 | 4.5 | 1715 | 2.8887e-06 | 2718 | 0 | 0 | 0.095322 | 1337 | 0
Bay Area | 4871 | 81 | 242.775 | 318 | 359.3217 | 41 | 2.1694e-05 | 0.066432 | 0.39214 | 0.36052 | 1.1502 | 0.0031518 | 0.12125 | 0.43515 | 0.95122 | 1.4412e-06 | 1.6035e-05 | 0.25472 | 0.67565 | {F0F7E9DB-942E-4AD9-8BB3-9A4EAA06963A} | 12091102 | OAKLAND J 1102 | CR184 | 37.7956 | -122.1834 | OAKLAND J 1102CR184 | 92 | 463 | 25097.6163 | 5568.9906 | 19528.6257 | 5568.9906 | 19528.6257 | 0.00065742 | 0.00088947 | 2.9972 | 7.7561 | 2684 | 5.9089e-05 | 2719 | 0 | 0 | 3.4604 | 2777 | 0
Bay Area | 2647 | 8 | 13.6905 | 29 | 22.9426 | 4 | 2.1689e-05 | 0.066432 | 6.8353 | 2.4988 | 11.9331 | 0.31968 | 0 | 0 | 0 | 1.4409e-06 | 0.00019318 | 0.27586 | 0.59673 | {4B545AE9-A885-48BD-BBDD-C323FFCD6AA5} | 13320401 |  | CR242 | 37.7996 | -122.2145 | CR242 | 103 | 968 | 44077.14 | 7226.0562 | 36851.0837 | 362.7025 | 2298.9488 | 0.00077271 | 8.6757e-05 | 1.7113 | 7.25 | 1438 | 5.7634e-06 | 2720 | 0 | 0 | 0.22537 | 1258 | 0
Bay Area | 4097 | 15 | 47.7069 | 147 | 117.4155 | 13 | 2.601e-05 | 0.051101 | 2.3388 | 1.1864 | 3.0009 | 0.039833 | 2.0874 | 9.7867 | 1.9232 | 1.4398e-06 | 5.0135e-05 | 0.10204 | 0.40631 | {0B7F62BF-A04D-4B9C-AA26-AFE69516CA65} | 13432207 | FAIRVIEW 2207 | P142 | 38.0485 | -122.2217 | FAIRVIEW 2207P142 | 120 | 617 | 24993.1566 | 4934.9724 | 20058.1842 | 1449.2328 | 5179.9712 | 0.00065175 | 0.00033813 | 3.1805 | 11.3077 | 2229 | 1.8718e-05 | 2721 | 0 | 0 | 0.90051 | 2118 | 0
Central Coast | 6234 | 70 | 179.9512 | 116 | 205.4841 | 8 | 2.1629e-05 | 0.066432 | 2.2318 | 1.3915 | 3.9025 | 0.034694 | 0.07052 | 0.76087 | 0.75 | 1.4369e-06 | 3.8182e-05 | 0.60345 | 0.87574 | {BA7590D4-FA7A-4E66-A4E2-9385E2F5FD08} | 182852202 | VIEJO 2202 | 9118 | 36.6037 | -121.9358 | VIEJO 22029118 | 93 | 230 | 14881.5039 | 4750.7038 | 10130.8001 | 903.5074 | 2670.7267 | 0.00030545 | 0.00017303 | 2.5707 | 14.5 | 2362 | 1.1495e-05 | 2722 | 0 | 0 | 0.56141 | 2526 | 0
Bay Area | 1645 | 3 | 6.9696 | 13 | 13.0007 | 1 | 2.1515e-05 | 0.066432 |  |  |  |  | 0 | 1.3007 | 1 | 1.4293e-06 | 2.1515e-05 | 0.23077 | 0.53609 | {75D298E6-3FF1-47B6-9B91-A2291860E391} | 14091109 | CASTRO VALLEY 1109 | circuit_breaker | 37.6913 | -122.0609 | CASTRO VALLEY 1109circuit_breaker | 50 | 134 | 10596.3229 | 3040.0219 | 7556.301 | 222.2939 | 200.4417 | 2.1515e-05 | 2.1515e-05 | 2.3232 | 13 | 2580 | 1.4293e-06 | 2723 | 0 | 0 | 0.13813 | 2820 | 0
Central Coast | 7033 | 20 | 44.2093 | 32 | 50.3299 | 4 | 2.1264e-05 | 0.066432 | 2.0368 | 1.1884 | 3.6201 | 0.011757 | 0.60122 | 0.30907 | 1 | 1.4126e-06 | 3.5518e-05 | 0.625 | 0.87839 | {5487E49D-3A5D-43A1-BCCA-6878D14EA68E} | 182852202 | VIEJO 2202 | 35388 | 36.6025 | -121.9344 | VIEJO 220235388 | 24 | 41 | 2459.5705 | 727.2974 | 1732.2731 | 676.3797 | 1299.9247 | 0.00014207 | 8.5054e-05 | 2.2105 | 8 | 2391 | 5.6503e-06 | 2724 | 0 | 0 | 0.42028 | 2567 | 0
Bay Area | 9585 | 17 | 34.1184 | 50 | 51.924 | 10 | 2.1152e-05 | 0.066431 | 1.2416 | 4.2436 | 26.0354 | 0.1142 | 1.5288 | 5.5233 | 1 | 1.4051e-06 | 2.3709e-05 | 0.34 | 0.65708 | {0FCC4668-DE07-42BB-BC4D-4288336A5D5A} | 12091102 | OAKLAND J 1102 | CR102 | 37.7964 | -122.184 | OAKLAND J 1102CR102 | 26 | 18 | 1634.8772 | 846.0426 | 788.8345 | 846.0426 | 788.8345 | 0.00023709 | 0.00021152 | 2.007 | 5 | 2548 | 1.4051e-05 | 2725 | 0 | 0 | 0.52571 | 2869 | 0
Central Coast | 822 | 61 | 119.6942 | 119 | 150.0352 | 31 | 2.0743e-05 | 0.066432 | 1.0886 | 1.8409 | 12.8795 | 0.063559 | 0.41322 | 0.80505 | 1 | 1.378e-06 | 2.075e-05 | 0.51261 | 0.79777 | {E866BEB9-EA03-48B4-BFE7-3DF4E1FFA3E2} | 183011102 | MORRO BAY 1102 | W22 | 35.3291 | -120.8245 | MORRO BAY 1102W22 | 188 | 520 | 32932.9749 | 10102.1991 | 22830.7758 | 3676.1403 | 5658.3887 | 0.00064326 | 0.00064303 | 1.9622 | 3.8387 | 2593 | 4.2718e-05 | 2726 | 0 | 0 | 2.2842 | 1986 | 0
Bay Area | 1013 | 66 | 202.7962 | 140 | 240.5359 | 8 | 2.5339e-05 | 0.049824 | 0.001532 | 0.034973 | 0.00049287 | 4.8015e-09 | 0.17662 | 0.092257 | 2 | 1.3761e-06 | 2.3296e-05 | 0.47143 | 0.8431 | {C4F18DDE-7DF7-43C4-9D20-1B47C5ED6CA4} | 42031123 | ALTO 1123 | circuit_breaker | 37.8987 | -122.525 | ALTO 1123circuit_breaker | 195 | 833 | 47418.1781 | 9495.092 | 37923.0861 | 1041.5153 | 4215.1177 | 0.00018637 | 0.00020271 | 3.0727 | 17.5 | 2560 | 1.1009e-05 | 2727 | 0 | 0 | 0.64717 | 2247 | 0
North Valley | 7297 | 0 | 0 | 3 | 1.3672 | 2 | 2.0598e-05 | 0.066432 | 0 | 0 | 0 | 0 | 9.6283 | 22.4742 | 1.0509 | 1.3684e-06 | 1.6351e-05 | 0 | 0 | {B2408DFF-DEFE-41B8-ADEE-8F62D90930D1} | 103311102 | BURNEY 1102 | 37284 | 40.8844 | -121.6665 | BURNEY 110237284 | 20 | 67 | 2831.8619 | 527.4707 | 2304.3912 | 11.2633 | 508.391 | 3.2702e-05 | 4.1196e-05 |  | 1.5 | 2674 | 2.7368e-06 | 2728 | 0 | 0 | 0.0069987 | 2376 | 0
Bay Area | 3926 | 83 | 279.4964 | 288 | 383.5774 | 35 | 2.4458e-05 | 0.05884 | 0.24169 | 0.19909 | 0.67667 | 0.0014419 | 0.33918 | 0.45996 | 1.4 | 1.3532e-06 | 1.2997e-05 | 0.28819 | 0.72866 | {63D64072-C2FD-480F-8116-E56FEE7BD425} | 13681112 | EDES 1112 | CR100 | 37.7551 | -122.1492 | EDES 1112CR100 | 86 | 456 | 27744.2888 | 5399.0675 | 22345.2213 | 5399.0675 | 22345.2213 | 0.00045491 | 0.00085602 | 3.3674 | 8.2286 | 2742 | 4.7361e-05 | 2729 | 0 | 0 | 3.3548 | 2835 | 0
Central Coast | 8192 | 132 | 430.0828 | 156 | 445.5348 | 8 | 2.8158e-05 | 0.049824 | 0.11093 | 4.6703 | 9.1322 | 0.001013 | 0.039823 | 0.71442 | 2 | 1.3359e-06 | 2.5606e-05 | 0.84615 | 0.96532 | {8E85DA31-E8CD-4D80-BE55-60AFA6937F74} | 182852202 | VIEJO 2202 | 9488 | 36.5902 | -121.9442 | VIEJO 22029488 | 54 | 23 | 2787.0272 | 2122.5518 | 664.4753 | 1141.9334 | 451.9397 | 0.00020485 | 0.00022526 | 3.2582 | 19.5 | 2525 | 1.0687e-05 | 2730 | 0 | 0 | 0.70956 | 675 | 0
Central Coast | 6710 | 2 | 8.0982 | 5 | 9.9757 | 1 | 1.9831e-05 | 0.066432 |  |  |  |  | 0 | 0.063496 | 1 | 1.3174e-06 | 1.9831e-05 | 0.4 | 0.81178 | {C8ECEDCB-3AAA-445C-9FF2-2773F53D5EAE} | 182852202 | VIEJO 2202 | 92792 | 36.5899 | -121.9458 | VIEJO 220292792 | 45 | 115 | 7539.6615 | 2455.5037 | 5084.1578 | 0 | 56.8943 | 1.9831e-05 | 1.9831e-05 | 4.0491 | 5 | 2612 | 1.3174e-06 | 2731 | 0 | 0 | 0 | 2321 | 0
Bay Area | 3642 | 29 | 60.7866 | 83 | 88.2351 | 11 | 1.9407e-05 | 0.066432 | 0.42444 | 0.55759 | 0.92791 | 0.0077493 | 1.9443 | 7.5249 | 1.0036 | 1.2892e-06 | 1.6428e-05 | 0.3494 | 0.68892 | {25DCD8D9-03C2-4BC1-93F7-DF5BB3FCC448} | 14671101 | SOBRANTE 1101 | L534R | 37.8887 | -122.133 | SOBRANTE 1101L534R | 100 | 203 | 10576.253 | 2992.4353 | 7583.8177 | 1291.9266 | 4666.681 | 0.00018071 | 0.00021348 | 2.0961 | 7.5455 | 2672 | 1.4182e-05 | 2732 | 0 | 0 | 0.80277 | 2306 | 0
Bay Area | 3626 | 12 | 28.7673 | 18 | 31.5017 | 10 | 1.9403e-05 | 0.066432 | 0.10883 | 0.10494 | 0.22461 | 0.0003563 | 0.9073 | 0.50591 | 1 | 1.289e-06 | 1.5437e-05 | 0.66667 | 0.9132 | {F23FD02C-15E0-46F5-9C74-B690AB0C4482} | 14091101 | CASTRO VALLEY 1101 | MR359 | 37.6769 | -122.0494 | CASTRO VALLEY 1101MR359 | 281 | 1386 | 71889.7595 | 14100.5025 | 57789.257 | 1462.9174 | 8353.4223 | 0.00015437 | 0.00019403 | 2.3973 | 1.8 | 2695 | 1.289e-05 | 2733 | 0 | 0 | 0.90901 | 2294 | 0
Bay Area | 5814 | 21 | 65.6152 | 167 | 151.6657 | 16 | 1.9184e-05 | 0.066432 | 1.6821 | 0.65007 | 1.9756 | 0.019203 | 0.35633 | 1.4804 | 1 | 1.2744e-06 | 3.3524e-05 | 0.12575 | 0.43263 | {FA7AC1D5-82AB-4E51-B874-C59D71756955} | 12091105 | OAKLAND J 1105 | CR256 | 37.7779 | -122.1693 | OAKLAND J 1105CR256 | 49 | 386 | 18417.7278 | 2967.1612 | 15450.5666 | 1245.6022 | 7785.0639 | 0.00053639 | 0.00030694 | 3.1245 | 10.4375 | 2421 | 2.0391e-05 | 2734 | 0 | 0 | 0.77398 | 2856 | 0
Bay Area | 410 | 136 | 381.8904 | 374 | 518.4004 | 56 | 1.9156e-05 | 0.066432 | 0.07884 | 0.40611 | 0.88172 | 1.1632e-05 | 1.0782 | 3.3384 | 1.015 | 1.2726e-06 | 8.9555e-06 | 0.36364 | 0.73667 | {C5ED9BB6-82EE-4A74-A509-3A42E5E8C396} | 24141101 | RALSTON 1101 | circuit_breaker | 37.5114 | -122.3402 | RALSTON 1101circuit_breaker | 197 | 1002 | 58267.378 | 13656.4798 | 44610.8982 | 7097.0963 | 24172.3454 | 0.00050151 | 0.0010728 | 2.808 | 6.6786 | 2797 | 7.1265e-05 | 2735 | 0 | 0 | 4.4099 | 722 | 0
Bay Area | 2000 | 113 | 345.883 | 292 | 444.4655 | 47 | 1.9143e-05 | 0.066432 | 0.24978 | 0.4378 | 1.105 | 0.002849 | 0.67233 | 5.8077 | 0.93669 | 1.2717e-06 | 1.2339e-05 | 0.38699 | 0.7782 | {21F0D258-E3F4-4472-9242-FFF30FF25E28} | 13111114 | SAN LEANDRO U 1114 | MR218 | 37.7169 | -122.1318 | SAN LEANDRO U 1114MR218 | 263 | 1622 | 94380.1655 | 18069.0511 | 76311.1143 | 8791.3954 | 30767.6748 | 0.00057996 | 0.00089973 | 3.0609 | 6.2128 | 2757 | 5.977e-05 | 2736 | 0 | 0 | 5.4627 | 2813 | 0
Central Coast | 2334 | 3 | 7.0212 | 8 | 9.6431 | 1 | 1.9108e-05 | 0.066432 |  |  |  |  | 0 | 0.034513 | 1 | 1.2694e-06 | 1.9108e-05 | 0.375 | 0.7281 | {42179AE7-9A87-4B89-B57E-456ACB950056} | 182852204 | VIEJO 2204 | 9110 | 36.6094 | -121.92 | VIEJO 22049110 | 125 | 741 | 37732.84 | 6943.3735 | 30789.4665 | 20.6903 | 415.4592 | 1.9108e-05 | 1.9108e-05 | 2.3404 | 8 | 2632 | 1.2694e-06 | 2737 | 0 | 0 | 0.012856 | 1809 | 0
Sierra | 8717 | 0 | 0 | 53 | 24.154 | 9 | 1.9078e-05 | 0.066431 | 0.54995 | 5.7136 | 28.9411 | 0.023871 | 0.12168 | 0.86318 | 1 | 1.2674e-06 | 1.5298e-05 | 0 | 0 | {C75EBAF8-0756-4F0F-AECF-0B1CCDC1C4A6} | 158031101 | ECHO SUMMIT 1101 | 741586 | 38.8252 | -120.0373 | ECHO SUMMIT 1101741586 | 19 | 33 | 1982.2893 | 1137.7952 | 844.4942 | 1137.7952 | 844.4942 | 0.00013768 | 0.00017171 |  | 5.8889 | 2698 | 1.1407e-05 | 2738 | 0 | 0 | 0.70699 | 1181 | 0
Bay Area | 2921 | 33 | 57.0576 | 78 | 80.3022 | 20 | 1.9566e-05 | 0.06311 | 2.4792 | 2.1413 | 4.1913 | 0.11017 | 1.3519 | 2.8835 | 1.0162 | 1.2578e-06 | 2.5975e-05 | 0.42308 | 0.71054 | {F6E31131-4FA7-4707-9B03-DC44D833452C} | 43201101 | STAFFORD 1101 | 1298 | 38.1199 | -122.5858 | STAFFORD 11011298 | 256 | 942 | 54315.9803 | 10849.9389 | 43466.0414 | 2037.2045 | 6390.328 | 0.0005195 | 0.00039132 | 1.729 | 3.9 | 2516 | 2.5155e-05 | 2739 | 0 | 0 | 1.2659 | 2828 | 0
Bay Area | 868 | 101 | 325.0808 | 227 | 389.8275 | 34 | 1.8852e-05 | 0.066432 | 0.21764 | 0.11578 | 0.73282 | 0.0053109 | 0.31058 | 1.5774 | 0.97059 | 1.2523e-06 | 1.2964e-05 | 0.44493 | 0.83391 | {2B6F69D9-2395-4FCE-ABEC-955C451097A3} | 13681112 | EDES 1112 | CR308 | 37.761 | -122.148 | EDES 1112CR308 | 125 | 465 | 25467.0458 | 5683.4055 | 19783.6403 | 5048.7285 | 15563.8615 | 0.00044077 | 0.00064096 | 3.2186 | 6.6765 | 2744 | 4.258e-05 | 2740 | 0 | 0 | 3.1371 | 2841 | 0
Sierra | 9061 | 1 | 3.8265 | 61 | 31.1707 | 9 | 1.8668e-05 | 0.066431 | 0.67996 | 3.7683 | 10.5807 | 0.013864 | 0.16175 | 2.347 | 1 | 1.2401e-06 | 1.7283e-05 | 0.016393 | 0.12276 | {501D001C-604C-4CB0-BC61-4A03C3824F33} | 158031101 | ECHO SUMMIT 1101 | 344250 | 38.8239 | -120.0438 | ECHO SUMMIT 1101344250 | 21 | 19 | 2254.4678 | 1668.1837 | 586.2841 | 1299.2708 | 248.7804 | 0.00015555 | 0.00016801 | 3.8265 | 6.7778 | 2661 | 1.1161e-05 | 2741 | 0 | 0 | 0.80733 | 281 | 0
Central Coast | 3597 | 1 | 1.6135 | 3 | 2.9731 | 1 | 1.863e-05 | 0.066431 | 0 | 0 | 0 | 0 | 0 | 0.029204 | 1 | 1.2376e-06 | 0 | 0.33333 | 0.54271 | {3A7DE5A9-6F9C-4704-A7B4-637F15326CD9} | 182492104 | HOLLISTER 2104 | 41808 | 36.9354 | -121.3948 | HOLLISTER 210441808 | 184 | 194 | 29610.8192 | 17500.5057 | 12110.3135 | 4.0767 | 22.487 | 0 | 1.863e-05 | 1.6135 | 3 | 2900 | 1.2376e-06 | 2742 | 0 | 0 | 0.0025331 | 1611 | 0
Bay Area | 5376 | 46 | 130.1697 | 92 | 152.566 | 27 | 2.087e-05 | 0.05413 | 0.45372 | 0.21882 | 0.43925 | 0.014083 | 0.57227 | 0.85554 | 1.5556 | 1.2368e-06 | 1.7334e-05 | 0.5 | 0.8532 | {7C12A412-D2AF-4E21-A226-597936BFB6C3} | 24181104 | SAN CARLOS 1104 | 8942 | 37.4907 | -122.2659 | SAN CARLOS 11048942 | 70 | 557 | 31453.1929 | 4451.9839 | 27001.209 | 3376.0521 | 18993.5161 | 0.00046803 | 0.0005635 | 2.8298 | 3.4074 | 2659 | 3.3394e-05 | 2743 | 0 | 0 | 2.0978 | 2901 | 0
North Valley | 8763 | 53 | 76.5612 | 98 | 97.596 | 10 | 1.8452e-05 | 0.066432 | 8.4549 | 122.5256 | 1519.4074 | 16.192 | 1.2212 | 8.6845 | 1 | 1.2258e-06 | 9.0074e-05 | 0.54082 | 0.78447 | {908347F0-FBC5-48E6-96A1-EFED3535309B} | 102812101 | BIG MEADOWS 2101 | 439 | 40.1374 | -120.9532 | BIG MEADOWS 2101439 | 19 | 21 | 2474.0764 | 1501.1745 | 972.9019 | 1041.6607 | 668.7264 | 0.00090074 | 0.00018452 | 1.4446 | 9.8 | 1908 | 1.2258e-05 | 2744 | 0 | 0 | 0.64726 | 942 | 0
Sierra | 1545 | 2 | 5.9941 | 128 | 63.4168 | 36 | 1.8419e-05 | 0.066431 | 0.80209 | 5.5641 | 14.171 | 0.020201 | 0.29142 | 4.1631 | 1.0035 | 1.2236e-06 | 1.7453e-05 | 0.015625 | 0.094518 | {52018984-7699-4174-8C0E-5E599E3F4F55} | 158031101 | ECHO SUMMIT 1101 | 2500 | 38.8236 | -120.0305 | ECHO SUMMIT 11012500 | 46 | 135 | 8046.5369 | 3502.0827 | 4544.4541 | 3502.0827 | 4544.4541 | 0.00062831 | 0.00066307 | 2.997 | 3.5556 | 2657 | 4.4048e-05 | 2745 | 0 | 0 | 2.1761 | 1281 | 0
Central Coast | 3814 | 13 | 19.0146 | 13 | 19.0146 | 1 | 1.8359e-05 | 0.066432 |  |  |  |  | 5.4867 | 17.1726 | 1.0376 | 1.2196e-06 | 1.8359e-05 | 1 | 1 | {C6CF638E-9C90-41DD-9ABD-A01972E6D396} | 183011102 | MORRO BAY 1102 | V84 | 35.3169 | -120.8248 | MORRO BAY 1102V84 | 258 | 1914 | 100285.2027 | 15814.6457 | 84470.557 | 101.4196 | 784.6383 | 1.8359e-05 | 1.8359e-05 | 1.4627 | 13 | 2641 | 1.2196e-06 | 2746 | 0 | 0 | 0.063019 | 1996 | 0
Bay Area | 199 | 10 | 29.0383 | 23 | 35.5489 | 8 | 1.8261e-05 | 0.066432 | 0.092331 | 0.036547 | 4.5595e-05 | 2.5617e-08 | 0 | 0.008656 | 0.375 | 1.2131e-06 | 8.154e-06 | 0.43478 | 0.81686 | {32DE72AC-BD44-46F9-BF98-F2D8B456CA9C} | 24120401 | LAS PULGAS 0401 | circuit_breaker | 37.4629 | -122.2278 | LAS PULGAS 0401circuit_breaker | 168 | 1382 | 64479.9046 | 9719.2183 | 54760.6863 | 583.9042 | 3184.1506 | 6.5232e-05 | 0.00014609 | 2.9038 | 2.875 | 2809 | 9.705e-06 | 2747 | 0 | 0 | 0.36282 | 2311 | 0
Central Coast | 2513 | 6 | 11.102 | 6 | 11.102 | 2 | 1.3192e-05 | 0.091864 | 0 | 17.5692 | 64.1681 | 0 | 1.4248 | 34.7254 | 1.1681 | 1.2119e-06 | 0 | 1 | 1 | {54070A16-E414-4AEE-9621-8B78CEEC4570} | 182052102 | SOLEDAD 2102 | 7562 | 36.4295 | -121.332 | SOLEDAD 21027562 | 162 | 306 | 26575.7117 | 12110.2794 | 14465.4323 | 2922.6853 | 304.4008 | 0 | 2.6384e-05 | 1.8503 | 3 | 2897 | 2.4237e-06 | 2748 | 0 | 0 | 1.8161 | 1849 | 0
Bay Area | 2617 | 15 | 33.4136 | 31 | 41.6224 | 12 | 1.8212e-05 | 0.066432 | 0.01681 | 0.045764 | 0.00050175 | 4.0988e-08 | 7.0291 | 12.6934 | 0.83481 | 1.2099e-06 | 3.8994e-06 | 0.48387 | 0.80278 | {7DC88504-8437-4262-8C77-15F7F25CD1D4} | 14091104 | CASTRO VALLEY 1104 | MR201 | 37.7014 | -122.0883 | CASTRO VALLEY 1104MR201 | 286 | 1880 | 90402.6846 | 15418.7744 | 74983.9102 | 1973.7097 | 7700.794 | 4.6793e-05 | 0.00021854 | 2.2276 | 2.5833 | 2854 | 1.4518e-05 | 2749 | 0 | 0 | 1.2264 | 405 | 0
Central Coast | 8443 | 0 | 0 | 4 | 2.7191 | 1 | 1.8208e-05 | 0.066432 | 22.7493 | 11.6609 | 30.7699 | 0.71009 | 0.21239 | 50.8825 | 1.0442 | 1.2096e-06 | 0.00041423 | 0 | 0 | {9AA16F48-39A4-4006-910E-3E37752DF955} | 182402106 | FORT ORD 2106 | 37286 | 36.6436 | -121.7895 | FORT ORD 210637286 | 33 | 3 | 5986.7736 | 5924.4605 | 62.3132 | 3227.6123 | 27.3128 | 0.00041423 | 1.8208e-05 |  | 4 | 920 | 1.2096e-06 | 2750 | 0 | 0 | 2.0055 | 2843 | 0
Bay Area | 42 | 2 | 5.0615 | 2 | 5.0615 | 2 | 1.7996e-05 | 0.066432 | 0 | 0 | 0 | 0 | 1.042 | 0.12832 | 1 | 1.1955e-06 | 0 | 1 | 1 | {FD68B15D-2380-4995-ADA8-EF407A4F9E9B} | 12091105 | OAKLAND J 1105 | 153228 | 37.775 | -122.1815 | OAKLAND J 1105153228 | 146 | 1121 | 51620.7639 | 6680.4391 | 44940.3248 | 241.8819 | 1336.9639 | 0 | 3.5991e-05 | 2.5307 | 1 | 2901 | 2.391e-06 | 2751 | 0 | 0 | 0.1503 | 2886 | 0
Sierra | 9773 | 0 | 0 | 1 | 0.45574 | 1 | 1.7815e-05 | 0.066431 | 0.3547 | 0.86404 | 2.4529 | 0.0058838 | 0.030973 | 1.9075 | 1 | 1.1835e-06 | 6.3191e-06 | 0 | 0 | {D6DB5AF9-E5B0-458F-9897-3AC3E052AB08} | 158031101 | ECHO SUMMIT 1101 | 55262 | 38.824 | -120.0291 | ECHO SUMMIT 110155262 | 17 | 3 | 324.9779 | 266.534 | 58.444 | 266.534 | 58.444 | 6.3191e-06 | 1.7815e-05 |  | 1 | 2836 | 1.1835e-06 | 2752 | 0 | 0 | 0.16562 | 2367 | 0
Bay Area | 7884 | 0 | 0 | 1 | 0.58532 | 1 | 1.7792e-05 | 0.066432 | 22.0902 | 34.9159 | 170.168 | 3.759 | 0.084071 | 0.74491 | 1 | 1.182e-06 | 0.00039303 | 0 | 0 | {117C09FD-AE60-4D22-843F-8781BD8BA585} | 42291101 | OLEMA 1101 | 37074 | 38.0687 | -122.8057 | OLEMA 110137074 | 24 | 34 | 1649.5018 | 506.0081 | 1143.4937 | 21.9456 | 0 | 0.00039303 | 1.7792e-05 |  | 1 | 955 | 1.182e-06 | 2753 | 0 | 0 | 0.013636 | 2765 | 0
Central Coast | 2481 | 3 | 6.2716 | 27 | 18.0667 | 10 | 1.6637e-05 | 0.070247 | 0.57285 | 128.968 | 622.1361 | 0.57344 | 0.26195 | 10.5618 | 1.0011 | 1.1589e-06 | 1.244e-05 | 0.11111 | 0.34713 | {5544109A-90D8-4D98-A117-3D3506C6B01F} | 182131103 | GONZALES 1103 | 3096 | 36.4982 | -121.4501 | GONZALES 11033096 | 206 | 190 | 39846.5611 | 29023.6121 | 10822.9489 | 2007.6917 | 1124.7032 | 0.0001244 | 0.00016637 | 2.0905 | 2.7 | 2755 | 1.1589e-05 | 2754 | 0 | 0 | 1.2475 | 2355 | 0
Central Coast | 1286 | 16 | 61.0585 | 16 | 61.0585 | 4 | 1.3812e-05 | 0.085506 | 0.0010331 | 88.4551 | 209.2091 | 0.00021674 | 0.36173 | 9.6782 | 1.0066 | 1.1565e-06 | 1.0791e-05 | 1 | 1 | {4C087FEB-CACD-4757-8482-26820E95E898} | 182052101 | SOLEDAD 2101 | circuit_breaker | 36.4296 | -121.3322 | SOLEDAD 2101circuit_breaker | 158 | 124 | 27792.3885 | 23674.2161 | 4118.1724 | 1217.4718 | 301.2928 | 4.3163e-05 | 5.5247e-05 | 3.8162 | 4 | 2777 | 4.6259e-06 | 2755 | 0 | 0 | 0.7565 | 1156 | 0
North Valley | 7483 | 1 | 1.3586 | 5 | 3.5871 | 2 | 1.7406e-05 | 0.066432 |  |  |  |  | 0.68363 | 15.6353 | 1.0044 | 1.1563e-06 | 1.7406e-05 | 0.2 | 0.37874 | {F015A61C-A7C7-4E4E-9F7E-089F729D8AF8} | 102551101 | EAST QUINCY 1101 | 1319 | 39.9337 | -120.9046 | EAST QUINCY 11011319 | 28 | 116 | 6468.8134 | 1710.625 | 4758.1883 | 230.1059 | 582.2453 | 3.4813e-05 | 3.4813e-05 | 1.3586 | 2.5 | 2658 | 2.3127e-06 | 2756 | 0 | 0 | 0.14298 | 2616 | 0
Bay Area | 4550 | 373 | 1395.6331 | 453 | 1441.4152 | 24 | 1.731e-05 | 0.066432 | 0.46331 | 0.20076 | 0.029299 | 2.3108e-05 | 1.3981 | 0.8391 | 0.75 | 1.1499e-06 | 1.3227e-05 | 0.8234 | 0.96824 | {5A5EFB63-6847-4F33-8DBE-F9C3D6DCF54A} | 22721101 | SNEATH LANE 1101 | 34438 | 37.6152 | -122.4385 | SNEATH LANE 110134438 | 137 | 845 | 45884.7753 | 8258.7197 | 37626.0556 | 2524.5868 | 10587.9245 | 0.00031746 | 0.00041544 | 3.7416 | 18.875 | 2739 | 2.7599e-05 | 2757 | 0 | 0 | 1.5687 | 2713 | 0
Bay Area | 474 | 224 | 499.9027 | 422 | 603.6777 | 77 | 2.2811e-05 | 0.049177 | 1.4075 | 0.91726 | 3.1826 | 0.024406 | 1.1889 | 2.179 | 1.9656 | 1.1457e-06 | 2.8171e-05 | 0.53081 | 0.8281 | {63FDD22C-1D84-438C-BDD2-97E9627809B3} | 12501105 | EL CERRITO G 1105 | circuit_breaker | 37.9162 | -122.3028 | EL CERRITO G 1105circuit_breaker | 210 | 1314 | 66304.6264 | 11881.4228 | 54423.2036 | 11881.4228 | 54423.2036 | 0.0021691 | 0.0017564 | 2.2317 | 5.4805 | 2488 | 8.8216e-05 | 2758 | 0 | 0 | 7.3828 | 2040 | 0
Bay Area | 2622 | 148 | 407.294 | 637 | 689.6989 | 49 | 1.8953e-05 | 0.059653 | 1.7608 | 1.6537 | 4.3988 | 0.032049 | 0.36312 | 1.2411 | 1.4082 | 1.1419e-06 | 2.0525e-05 | 0.23234 | 0.59054 | {9F880ADC-A7AD-4981-8671-C146C332254F} | 14341105 | VALLEY VIEW 1105 | P190 | 37.9763 | -122.2915 | VALLEY VIEW 1105P190 | 168 | 678 | 38550.0406 | 9490.8504 | 29059.1902 | 4841.3798 | 9746.1877 | 0.0010057 | 0.00092871 | 2.752 | 13 | 2598 | 5.5953e-05 | 2759 | 0 | 0 | 3.0083 | 2165 | 0
Bay Area | 3517 | 109 | 218.9683 | 249 | 290.1621 | 39 | 1.8952e-05 | 0.061322 | 1.2888 | 0.87261 | 3.1797 | 0.027691 | 0.55297 | 0.090871 | 0.74359 | 1.1395e-06 | 2.5604e-05 | 0.43775 | 0.75464 | {E8FD31A9-7950-4D14-9414-D1A0A0556AE8} | 12600401 | OAK 0401 | circuit_breaker | 37.9012 | -122.2867 | OAK 0401circuit_breaker | 150 | 1383 | 63793.9176 | 8444.2886 | 55349.629 | 5406.3145 | 35040.3995 | 0.00099854 | 0.00073914 | 2.0089 | 6.3846 | 2526 | 4.4441e-05 | 2760 | 0 | 0 | 3.3593 | 2868 | 0
Bay Area | 6115 | 270 | 739.4816 | 574 | 908.6619 | 66 | 1.7002e-05 | 0.066432 | 1.2275 | 2.4949 | 4.2146 | 0.045604 | 0.7315 | 2.7504 | 0.94151 | 1.1295e-06 | 2.4377e-05 | 0.47038 | 0.81381 | {D73C61C6-F360-40B2-9388-D54915745260} | 24012102 | BAY MEADOWS 2102 | 57886 | 37.5462 | -122.3337 | BAY MEADOWS 210257886 | 145 | 384 | 25543.7186 | 8466.0843 | 17077.6343 | 6347.2399 | 13396.3692 | 0.0016089 | 0.0011221 | 2.7388 | 8.697 | 2541 | 7.4545e-05 | 2761 | 0 | 0 | 3.944 | 2865 | 0
Bay Area | 3200 | 198 | 574.7737 | 331 | 640.6072 | 73 | 1.6933e-05 | 0.066432 | 0.52774 | 1.5345 | 5.2357 | 0.071913 | 1.0372 | 2.5326 | 0.9863 | 1.1249e-06 | 1.2397e-05 | 0.59819 | 0.89723 | {0A0CA719-3BA2-4B10-8DAF-28B4D94E2A5D} | 13111109 | SAN LEANDRO U 1109 | CR002 | 37.744 | -122.1508 | SAN LEANDRO U 1109CR002 | 194 | 1283 | 69032.9863 | 12468.7643 | 56564.222 | 10902.831 | 47424.5904 | 0.00090498 | 0.0012361 | 2.9029 | 4.5342 | 2756 | 8.2117e-05 | 2762 | 0 | 0 | 6.7747 | 747 | 0
Central Coast | 8392 | 2 | 7.6323 | 9 | 10.8225 | 1 | 1.074e-05 | 0.10458 | 0 | 78.923 | 429.7631 | 0 | 1.2279 | 28.1385 | 1.0398 | 1.1231e-06 | 0 | 0.22222 | 0.70523 | {B67EAAD0-18CE-4C8C-8264-33FF5297FE06} | 182051114 | SOLEDAD 1114 | 35306 | 36.4317 | -121.3296 | SOLEDAD 111435306 | 86 | 40 | 14931.2798 | 11463.1003 | 3468.1795 | 1328.8876 | 2046.4282 | 0 | 1.074e-05 | 3.8162 | 9 | 2895 | 1.1231e-06 | 2763 | 0 | 0 | 0.82573 | 2005 | 0
Bay Area | 3199 | 16 | 35.7174 | 23 | 39.3556 | 5 | 1.6715e-05 | 0.066432 | 1.3248 | 1.0707 | 2.2097 | 0.1307 | 0.00044248 | 0.098451 | 1 | 1.1104e-06 | 2.0485e-05 | 0.69565 | 0.90755 | {1C6F3DE6-AA4E-42DF-A55E-4A158925CCE7} | 12091106 | OAKLAND J 1106 | CR330 | 37.7648 | -122.1607 | OAKLAND J 1106CR330 | 65 | 507 | 26986.4996 | 3874.576 | 23111.9235 | 845.057 | 3745.2206 | 0.00010242 | 8.3574e-05 | 2.2323 | 4.6 | 2599 | 5.552e-06 | 2764 | 0 | 0 | 0.52509 | 2766 | 0
Central Coast | 359 | 2 | 5.0213 | 91 | 59.6577 | 10 | 1.6601e-05 | 0.066432 | 9.2181 | 26.2981 | 70.6337 | 0.61801 | 5.2192 | 18.2145 | 1.0272 | 1.1028e-06 | 0.00012482 | 0.021978 | 0.084169 | {3CCA61DC-2699-479D-8396-73463C6B90FD} | 182971101 | PURISIMA 1101 | 49394 | 34.7035 | -120.461 | PURISIMA 110149394 | 240 | 1213 | 73424.8648 | 14100.597 | 59324.2678 | 1434.279 | 941.4801 | 0.0012482 | 0.00016601 | 2.5107 | 9.1 | 1725 | 1.1028e-05 | 2765 | 0 | 0 | 0.89122 | 943 | 0
Bay Area | 5182 | 22 | 46.8616 | 80 | 79.368 | 9 | 1.5808e-05 | 0.067845 | 10.2759 | 30.0162 | 42.1635 | 1.9593 | 0.92355 | 5.8794 | 1.0015 | 1.0972e-06 | 5.4515e-05 | 0.275 | 0.59043 | {36DDF29F-B22D-4B8A-AF4A-BB933D5333CF} | 14101105 | ALHAMBRA 1105 | circuit_breaker | 37.9937 | -122.1302 | ALHAMBRA 1105circuit_breaker | 80 | 169 | 10291.6518 | 3045.0722 | 7246.5797 | 1107.679 | 1947.9854 | 0.00049064 | 0.00014227 | 2.1301 | 8.8889 | 2196 | 9.8746e-06 | 2766 | 0 | 0 | 0.68828 | 2045 | 0
Bay Area | 8049 | 9 | 14.3568 | 22 | 21.6587 | 5 | 1.6351e-05 | 0.066432 |  |  |  |  | 0.038938 | 2.1257 | 1 | 1.0862e-06 | 1.6351e-05 | 0.40909 | 0.66286 | {DE1365E8-AE71-4371-B78C-316604B54A0D} | 14161104 | ROSSMOOR 1104 | 79146 | 37.9033 | -122.0955 | ROSSMOOR 110479146 | 79 | 160 | 9989.7568 | 3498.2633 | 6491.4935 | 400.4315 | 465.663 | 8.1753e-05 | 8.1753e-05 | 1.5952 | 4.4 | 2675 | 5.431e-06 | 2767 | 0 | 0 | 0.24882 | 2840 | 0
North Valley | 9380 | 0 | 0 | 14 | 7.0608 | 9 | 7.7144e-06 | 0.19501 | 0.01019 | 54.2735 | 847.1643 | 0.031399 | 0.068584 | 43.3235 | 1.0792 | 1.0794e-06 | 3.9919e-06 | 0 | 0 | {637602BE-E394-4D87-B06C-9852D4AA6AF2} | 102361101 | HAMILTON BRANCH 1101 | 2436 | 40.2861 | -121.1155 | HAMILTON BRANCH 11012436 | 16 | 1 | 2064.2223 | 2038.321 | 25.9013 | 2038.321 | 25.9013 | 3.5927e-05 | 6.9429e-05 |  | 1.5556 | 2853 | 9.7145e-06 | 2768 | 0 | 0 | 1.2666 | 14 | 0
Central Coast | 954 | 26 | 60.5349 | 31 | 63.1143 | 4 | 1.6137e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0.038164 | 6.2355 | 1 | 1.072e-06 | 1.4309e-05 | 0.83871 | 0.95913 | {2F70F4D8-3BA3-4012-9A01-B8B771F3D276} | 182221101 | DEL MONTE 1101 | 38582 | 36.6191 | -121.8249 | DEL MONTE 110138582 | 117 | 519 | 33430.0563 | 8603.6462 | 24826.4101 | 792.5912 | 389.3044 | 5.7238e-05 | 6.4547e-05 | 2.3283 | 7.75 | 2717 | 4.288e-06 | 2769 | 0 | 0 | 0.49249 | 1862 | 0
Bay Area | 4052 | 1 | 2.5307 | 4 | 3.8979 | 3 | 1.6048e-05 | 0.066432 |  |  |  |  | 0.31416 | 0.033997 | 0.33333 | 1.0661e-06 | 1.6048e-05 | 0.25 | 0.64925 | {D5C37EEA-D463-430D-8618-04212D08A58F} | 12501110 | EL CERRITO G 1110 | circuit_breaker | 37.9161 | -122.3027 | EL CERRITO G 1110circuit_breaker | 76 | 525 | 23369.4602 | 4384.063 | 18985.3972 | 376.2535 | 3101.4916 | 4.8145e-05 | 4.8145e-05 | 2.5307 | 1.3333 | 2683 | 3.1983e-06 | 2770 | 0 | 0 | 0.23379 | 2337 | 0
Central Valley | 9984 | 0 | 0 | 3 | 1.2624 | 1 | 1.5855e-05 | 0.066431 |  |  |  |  | 0.30973 | 1.025 | 1 | 1.0532e-06 | 1.5855e-05 | 0 | 0 | {21272FCC-A834-4F21-A4CB-5DBBD597A054} | 163160401 | PINECREST 0401 | circuit_breaker | 38.1883 | -119.9938 | PINECREST 0401circuit_breaker | 4 | 0 | 20.6165 | 20.6165 | 0 | 20.6165 | 0 | 1.5855e-05 | 1.5855e-05 |  | 3 | 2686 | 1.0532e-06 | 2771 | 0 | 0 | 0.01281 | 1513 | 0
Sierra | 6441 | 1 | 0.97408 | 51 | 23.7609 | 19 | 1.5798e-05 | 0.066431 | 0.74582 | 3.0021 | 9.0941 | 0.0079402 | 0.1459 | 2.767 | 1 | 1.0495e-06 | 1.3684e-05 | 0.019608 | 0.040995 | {3CE51A5B-7612-4EAB-BF43-95EB9AC2B5AB} | 158031101 | ECHO SUMMIT 1101 | 8922 | 38.8228 | -120.0296 | ECHO SUMMIT 11018922 | 16 | 83 | 5308.6268 | 1790.6655 | 3517.9612 | 1790.6655 | 3517.9612 | 0.00025999 | 0.00030016 | 0.97408 | 2.6842 | 2728 | 1.994e-05 | 2772 | 0 | 0 | 1.1127 | 2419 | 0
Bay Area | 638 | 3 | 10.2083 | 12 | 14.534 | 2 | 1.5451e-05 | 0.066432 |  |  |  |  | 0.5 | 0.12743 | 1 | 1.0264e-06 | 1.5451e-05 | 0.25 | 0.70238 | {BE3C634B-17FC-4888-B134-237CE049DF24} | 12091105 | OAKLAND J 1105 | CR130 | 37.7794 | -122.1871 | OAKLAND J 1105CR130 | 144 | 1163 | 56272.5662 | 7851.3017 | 48421.2644 | 753.2352 | 3882.3914 | 3.0902e-05 | 3.0902e-05 | 3.4028 | 6 | 2694 | 2.0529e-06 | 2773 | 0 | 0 | 0.46804 | 748 | 0
Bay Area | 1652 | 1 | 4.0491 | 4 | 5.5864 | 1 | 1.5392e-05 | 0.066432 |  |  |  |  | 0.25885 | 0.025885 | 1 | 1.0225e-06 | 1.5392e-05 | 0.25 | 0.72481 | {218F069D-01B3-4618-A6DA-CD10F8EDDF5D} | 12091118 | OAKLAND J 1118 | CR198 | 37.7588 | -122.172 | OAKLAND J 1118CR198 | 147 | 1377 | 64068.6102 | 8427.7397 | 55640.8704 | 515.4771 | 2212.6731 | 1.5392e-05 | 1.5392e-05 | 4.0491 | 4 | 2696 | 1.0225e-06 | 2774 | 0 | 0 | 0.3203 | 2817 | 0
Bay Area | 7965 | 21 | 46.3019 | 22 | 46.9278 | 4 | 4.9457e-05 | 0.033216 | 0 | 0 | 0 | 0 | 0.97235 | 3.1833 | 3.0011 | 1.0103e-06 | 1.9224e-05 | 0.95455 | 0.98666 | {935F9503-A6EA-4581-B689-528244098488} | 22721107 | SNEATH LANE 1107 | 15341 | 37.6348 | -122.4692 | SNEATH LANE 110715341 | 48 | 168 | 8016.0621 | 2071.5108 | 5944.5513 | 518.827 | 111.522 | 7.6898e-05 | 0.00019783 | 2.2049 | 5.5 | 2629 | 4.0413e-06 | 2775 | 0 | 0 | 0.32238 | 394 | 0
Bay Area | 3699 | 3 | 9.9102 | 18 | 19.1167 | 3 | 1.5156e-05 | 0.066432 |  |  |  |  | 0.67552 | 0.21003 | 1 | 1.0068e-06 | 1.5156e-05 | 0.16667 | 0.5184 | {FFE77CFA-A34C-468C-9434-8A402AB29846} | 12501112 | EL CERRITO G 1112 | circuit_breaker | 37.9163 | -122.3029 | EL CERRITO G 1112circuit_breaker | 175 | 1176 | 57519.0637 | 10601.0269 | 46918.0368 | 510.801 | 1516.6237 | 4.5468e-05 | 4.5468e-05 | 3.3034 | 6 | 2701 | 3.0205e-06 | 2776 | 0 | 0 | 0.3174 | 398 | 0
Central Coast | 4475 | 45 | 109.5585 | 88 | 135.2264 | 10 | 3.1017e-05 | 0.026573 | 6.5526 | 7.1092 | 16.9872 | 0.20801 | 2.8673e-13 | 0.0059735 | 3.2 | 9.8727e-07 | 0.00011662 | 0.51136 | 0.81019 | {E55048C4-CAB1-4B6B-99F6-30BB24FEA325} | 182291102 | HATTON 1102 | 2070 | 36.5447 | -121.9082 | HATTON 11022070 | 50 | 206 | 13583.5716 | 3077.1708 | 10506.4008 | 797.8151 | 3584.7569 | 0.0011662 | 0.00031017 | 2.4346 | 8.8 | 1764 | 9.8727e-06 | 2777 | 0 | 0 | 0.49574 | 234 | 0
Sierra | 2274 | 5 | 9.6613 | 9 | 11.412 | 2 | 1.4811e-05 | 0.066432 |  |  |  |  | 0.64049 | 0.45896 | 1 | 9.8392e-07 | 1.4811e-05 | 0.55556 | 0.84659 | {5828CFD8-0F34-469A-AB4B-4395B45CE3D2} | 63601112 | VACAVILLE 1112 | circuit_breaker | 38.3568 | -121.9806 | VACAVILLE 1112circuit_breaker | 107 | 509 | 22924.0515 | 5210.2483 | 17713.8032 | 207.005 | 802.4661 | 2.9622e-05 | 2.9622e-05 | 1.9323 | 4.5 | 2708 | 1.9678e-06 | 2778 | 0 | 0 | 0.12863 | 1060 | 0
Bay Area | 141 | 5 | 8.2766 | 26 | 18.1873 | 11 | 1.4711e-05 | 0.066432 | 0.064148 | 0.037304 | 0.024308 | 9.2962e-06 | 0.93484 | 0.97798 | 0.81818 | 9.7725e-07 | 6.8328e-06 | 0.19231 | 0.45508 | {8CF3EAE2-3D5E-46D8-99A9-0040E44D6238} | 14091108 | CASTRO VALLEY 1108 | MR379 | 37.7032 | -122.0461 | CASTRO VALLEY 1108MR379 | 41 | 333 | 17097.9601 | 2536.0701 | 14561.89 | 1604.9824 | 7795.9576 | 7.5161e-05 | 0.00016182 | 1.6553 | 2.3636 | 2827 | 1.075e-05 | 2779 | 0 | 0 | 0.99729 | 744 | 0
Central Coast | 440 | 1 | 3.8162 | 12 | 9.2773 | 3 | 1.4703e-05 | 0.066432 |  |  |  |  | 0.0081121 | 0.18658 | 1 | 9.7678e-07 | 1.4703e-05 | 0.083333 | 0.41134 | {CED5D6B7-0919-4723-BD8E-41D37DAA2E37} | 182601105 | OCEANO 1105 | V44 | 35.1397 | -120.6393 | OCEANO 1105V44 | 42 | 148 | 6544.0681 | 1804.253 | 4739.8151 | 1004.1237 | 2116.1193 | 4.411e-05 | 4.411e-05 | 3.8162 | 4 | 2709 | 2.9303e-06 | 2780 | 0 | 0 | 0.62393 | 346 | 0
Central Coast | 6054 | 1 | 1.945 | 4 | 3.7063 | 3 | 1.4503e-05 | 0.066432 | 48.8527 | 48.4436 | 138.3035 | 6.8789 | 20.5251 | 78.5482 | 1.2714 | 9.6346e-07 | 0.00048581 | 0.25 | 0.52477 | {8D6AF672-1092-41FD-91A5-035B7D768884} | 83242111 | MORGAN HILL 2111 | circuit_breaker | 37.1269 | -121.6589 | MORGAN HILL 2111circuit_breaker | 97 | 103 | 9312.358 | 4339.1173 | 4973.2407 | 461.9266 | 978.9035 | 0.0014574 | 4.3509e-05 | 1.945 | 1.3333 | 802 | 2.8904e-06 | 2781 | 0 | 0 | 0.28703 | 547 | 0
Bay Area | 7726 | 2 | 5.4297 | 3 | 5.8854 | 3 | 1.4467e-05 | 0.066432 | 0.38497 | 0.22239 | 0.060487 | 2.3286e-05 | 0 | 0.28518 | 1 | 9.6109e-07 | 1.022e-05 | 0.66667 | 0.92257 | {B40886D4-E154-4D0B-BB2B-061EFDC2739B} | 12091105 | OAKLAND J 1105 | CR150 | 37.7759 | -122.1669 | OAKLAND J 1105CR150 | 23 | 90 | 3991.3098 | 755.1885 | 3236.1213 | 288.2243 | 892.1483 | 3.0661e-05 | 4.3402e-05 | 2.7148 | 1 | 2784 | 2.8833e-06 | 2782 | 0 | 0 | 0.17909 | 732 | 0
Bay Area | 3401 | 59 | 89.7149 | 97 | 109.8025 | 22 | 1.4273e-05 | 0.066431 | 0.30875 | 0.19008 | 0.0028158 | 1.0172e-06 | 0.32532 | 0.95299 | 1 | 9.4818e-07 | 1.3462e-05 | 0.60825 | 0.81706 | {25FEAA66-B3E3-4A2E-9CFA-07C2BE62DF67} | 42481105 |  | 318 | 38.0776 | -122.548 | 318 | 317 | 1741 | 106835.6689 | 18521.3174 | 88314.3515 | 2707.537 | 15379.4919 | 0.00029617 | 0.00031401 | 1.5206 | 4.4091 | 2736 | 2.086e-05 | 2783 | 0 | 0 | 1.6824 | 2153 | 0
Central Coast | 4756 | 12 | 41.5418 | 56 | 60.8836 | 9 | 9.9691e-06 | 0.097516 | 15.1096 | 96.9988 | 379.0326 | 10.6051 | 0.83579 | 7.3229 | 1 | 9.379e-07 | 4.189e-05 | 0.21429 | 0.68231 | {BB99A914-387F-48D8-919A-BB8BCFE90D9F} | 182631108 | SAN LUIS OBISPO 1108 | circuit_breaker | 35.2614 | -120.6348 | SAN LUIS OBISPO 1108circuit_breaker | 327 | 726 | 46100.4881 | 13627.7483 | 32472.7398 | 2912.0068 | 2165.1894 | 0.00037701 | 8.9722e-05 | 3.4618 | 6.2222 | 2311 | 8.4411e-06 | 2784 | 0 | 0 | 1.8094 | 1449 | 0
Bay Area | 4494 | 142 | 380.7965 | 281 | 458.1649 | 40 | 1.5471e-05 | 0.06145 | 2.0291 | 1.1367 | 5.722 | 0.063519 | 0.14261 | 0.23612 | 1.175 | 9.2444e-07 | 3.2891e-05 | 0.50534 | 0.83113 | {08B99221-B59C-4635-A155-E118204BFD80} | 12501105 | EL CERRITO G 1105 | BR194 | 37.9202 | -122.2873 | EL CERRITO G 1105BR194 | 155 | 792 | 40630.2955 | 8523.5207 | 32106.7748 | 5780.6278 | 22521.0256 | 0.0013156 | 0.00061882 | 2.6817 | 7.025 | 2427 | 3.6977e-05 | 2785 | 0 | 0 | 3.5919 | 2056 | 0
Bay Area | 5974 | 11 | 34.8285 | 28 | 43.9202 | 9 | 1.582e-05 | 0.059051 | 0.44755 | 0.14772 | 0.10439 | 7.0387e-05 | 0.12795 | 0.084476 | 1.4444 | 9.1582e-07 | 1.3587e-05 | 0.39286 | 0.79299 | {84501BB6-0E8B-48DF-8950-A9E642A52FF8} | 24181104 | SAN CARLOS 1104 | 79774 | 37.4931 | -122.2689 | SAN CARLOS 110479774 | 62 | 225 | 12858.1438 | 2604.2837 | 10253.8601 | 1093.2973 | 4604.0266 | 0.00012229 | 0.00014238 | 3.1662 | 3.1111 | 2731 | 8.2424e-06 | 2786 | 0 | 0 | 0.67934 | 1859 | 0
Bay Area | 1646 | 13 | 38.2016 | 22 | 42.3032 | 3 | 1.3678e-05 | 0.066432 |  |  |  |  | 1.2729 | 2.9058 | 1 | 9.0864e-07 | 1.3678e-05 | 0.59091 | 0.90304 | {59075C34-BE20-48C1-88DD-797C87DDC3D3} | 12501111 | EL CERRITO G 1111 | circuit_breaker | 37.9162 | -122.3027 | EL CERRITO G 1111circuit_breaker | 377 | 2272 | 108929.2887 | 20306.9192 | 88622.3695 | 521.1606 | 2692.9809 | 4.1033e-05 | 4.1033e-05 | 2.9386 | 7.3333 | 2730 | 2.7259e-06 | 2787 | 0 | 0 | 0.32383 | 2289 | 0
Central Coast | 4313 | 11 | 20.7576 | 16 | 23.9325 | 2 | 1.3298e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.834e-07 | 6.455e-06 | 0.6875 | 0.86734 | {7A855EEE-6A4F-4B41-AEEE-D64586BF7960} | 182090401 | MONTEREY 0401 | 2642 | 36.5933 | -121.8948 | MONTEREY 04012642 | 70 | 476 | 25848.3719 | 4201.7426 | 21646.6293 | 395.9249 | 1545.1264 | 1.291e-05 | 2.6596e-05 | 1.8871 | 8 | 2833 | 1.7668e-06 | 2788 | 0 | 0 | 0.24602 | 1239 | 0
Bay Area | 4623 | 7 | 27.1789 | 7 | 27.1789 | 2 | 1.3216e-05 | 0.066432 |  |  |  |  | 0 | 0.0049779 | 0.5 | 8.7797e-07 | 1.3216e-05 | 1 | 1 | {8E15B458-F29C-4328-B8BB-225EB178302D} | 22721107 | SNEATH LANE 1107 | 1277 | 37.6246 | -122.4557 | SNEATH LANE 11071277 | 62 | 404 | 21453.6683 | 3471.3767 | 17982.2916 | 61.1173 | 550.6473 | 2.6432e-05 | 2.6432e-05 | 3.8827 | 3.5 | 2740 | 1.7559e-06 | 2789 | 0 | 0 | 0.037977 | 2836 | 0
Bay Area | 3555 | 0 | 0 | 60 | 27.5143 | 8 | 1.3868e-05 | 0.058128 | 1.5116 | 2.4764 | 9.1642 | 0.047951 | 1.4807 | 6.0382 | 1.5006 | 8.7795e-07 | 2.0039e-05 | 0 | 0 | {FE1BD117-15DE-488E-8B59-94F428A7D4B4} | 12650401 | FAIRMOUNT 0401 | circuit_breaker | 37.9022 | -122.2967 | FAIRMOUNT 0401circuit_breaker | 150 | 1596 | 70259.9914 | 9236.8516 | 61023.1398 | 2166.002 | 11933.001 | 0.00016031 | 0.00011095 |  | 7.5 | 2606 | 7.0236e-06 | 2790 | 0 | 0 | 1.3459 | 2257 | 0
North Valley | 6801 | 53 | 68.5986 | 97 | 91.2958 | 10 | 1.3201e-05 | 0.066432 | 1.7101 | 255.8505 | 3240.1097 | 20.0102 | 0.83385 | 32.1081 | 1.002 | 8.7699e-07 | 1.9961e-05 | 0.54639 | 0.75139 | {13627031-EE44-4823-A048-AA36CB9BE013} | 103021101 | GANSNER 1101 | 99388 | 39.9405 | -120.9519 | GANSNER 110199388 | 65 | 74 | 6634.2426 | 3580.3836 | 3053.859 | 1047.5058 | 956.0837 | 0.00019961 | 0.00013201 | 1.2943 | 9.7 | 2608 | 8.7699e-06 | 2791 | 0 | 0 | 0.65089 | 596 | 0
Central Coast | 3855 | 37 | 86.598 | 87 | 108.8138 | 9 | 1.3166e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0.45501 | 0.081957 | 0.66667 | 8.7465e-07 | 8.5079e-06 | 0.42529 | 0.79584 | {2899757E-80A9-4AB1-8800-BCC024D9B2AA} | 182090402 | MONTEREY 0402 | 2644 | 36.5998 | -121.9002 | MONTEREY 04022644 | 35 | 178 | 10105.7589 | 2300.473 | 7805.2859 | 887.4818 | 4171.8374 | 7.6571e-05 | 0.0001185 | 2.3405 | 9.6667 | 2804 | 7.8719e-06 | 2792 | 0 | 0 | 0.55146 | 349 | 0
Bay Area | 1956 | 2 | 7.6323 | 5 | 9.3428 | 3 | 1.2718e-05 | 0.070671 | 0 | 0.22239 | 0.11266 | 0 | 1.649 | 18.5876 | 1 | 8.6505e-07 | 3.8825e-06 | 0.4 | 0.81692 | {BF555005-32AC-49E5-8E9E-ED1476EE192C} | 14091101 | CASTRO VALLEY 1101 | MR518 | 37.6589 | -122.0516 | CASTRO VALLEY 1101MR518 | 88 | 130 | 8175.3301 | 3163.325 | 5012.0051 | 621.9183 | 166.5334 | 1.1648e-05 | 3.8154e-05 | 3.8162 | 1.6667 | 2855 | 2.5951e-06 | 2793 | 0 | 0 | 0.38644 | 393 | 0
Bay Area | 3585 | 1 | 3.8162 | 4 | 5.3535 | 2 | 1.2737e-05 | 0.066432 |  |  |  |  | 0.21239 | 0.17622 | 1 | 8.4613e-07 | 1.2737e-05 | 0.25 | 0.71284 | {8BEFF91A-7C09-4291-9AE2-AE9219165D14} | 13681112 | EDES 1112 | circuit_breaker | 37.7388 | -122.1936 | EDES 1112circuit_breaker | 62 | 267 | 14357.8581 | 2377.7015 | 11980.1566 | 342.8746 | 1057.7955 | 2.5474e-05 | 2.5474e-05 | 3.8162 | 2 | 2750 | 1.6923e-06 | 2794 | 0 | 0 | 0.21305 | 2889 | 0
North Valley | 9495 | 1 | 1.9791 | 63 | 36.1892 | 22 | 8.4826e-06 | 0.11961 | 0 | 117.7982 | 1930.4878 | 0 | 0.7314 | 26.0458 | 1.0411 | 8.3913e-07 | 4.4993e-06 | 0.015873 | 0.054688 | {AF151625-80CF-4718-9BB9-66C05505AD54} | 102361101 | HAMILTON BRANCH 1101 | 18205 | 40.2961 | -121.1335 | HAMILTON BRANCH 110118205 | 14 | 7 | 7568.0134 | 6497.5751 | 1070.4383 | 3707.1238 | 1070.4383 | 9.8986e-05 | 0.00018662 | 1.9791 | 2.8636 | 2851 | 1.8461e-05 | 2795 | 0 | 0 | 2.3035 | 1952 | 0
Bay Area | 9208 | 70 | 253.2072 | 174 | 304.022 | 24 | 1.3343e-05 | 0.063664 | 4.4179 | 26.0512 | 48.5619 | 0.78709 | 1.669 | 20.6977 | 1.1727 | 8.3885e-07 | 1.6319e-05 | 0.4023 | 0.83286 | {F15BB3D1-0A60-48BB-96E4-777A07B496BE} | 13921104 | FRANKLIN 1104 | P136 | 38.0355 | -122.2583 | FRANKLIN 1104P136 | 78 | 63 | 11705.6696 | 9481.7884 | 2223.8812 | 6756.6357 | 1896.8607 | 0.00039166 | 0.00032023 | 3.6172 | 7.25 | 2677 | 2.0133e-05 | 2796 | 0 | 0 | 4.1984 | 2776 | 0
Bay Area | 476 | 5 | 13.5342 | 13 | 17.1801 | 1 | 1.2239e-05 | 0.066432 |  |  |  |  | 0 | 0 | 0 | 8.1308e-07 | 1.2239e-05 | 0.38462 | 0.78778 | {5D1C1AAB-9C80-45FC-B4E5-476A83A13C6E} | 22721102 | SNEATH LANE 1102 | 10255 | 37.6353 | -122.4563 | SNEATH LANE 110210255 | 80 | 644 | 31817.4541 | 4666.4719 | 27150.9822 | 0 | 243.5358 | 1.2239e-05 | 1.2239e-05 | 2.7068 | 13 | 2759 | 8.1308e-07 | 2797 | 0 | 0 | 0 | 2702 | 0
Bay Area | 3646 | 18 | 62.1252 | 100 | 105.8033 | 14 | 1.2238e-05 | 0.066432 | 3.7116 | 4.3031 | 7.5315 | 0.065895 | 1.1008 | 2.7644 | 1 | 8.1299e-07 | 3.459e-05 | 0.18 | 0.58718 | {1A179874-1BC4-4379-BC93-DB3AE752926F} | 14341105 | VALLEY VIEW 1105 | P126 | 37.9837 | -122.2966 | VALLEY VIEW 1105P126 | 60 | 293 | 16465.6417 | 3297.3508 | 13168.2909 | 1553.9705 | 4424.5498 | 0.00048425 | 0.00017133 | 3.4514 | 7.1429 | 2406 | 1.1382e-05 | 2798 | 0 | 0 | 0.96559 | 1205 | 0
Bay Area | 3167 | 1 | 4.0491 | 3 | 5.1846 | 2 | 1.2189e-05 | 0.066432 |  |  |  |  | 0.013274 | 0.26704 | 1 | 8.0976e-07 | 1.2189e-05 | 0.33333 | 0.78098 | {7F8D329C-2906-4CB9-89A6-48A9455878D0} | 14341105 | VALLEY VIEW 1105 | circuit_breaker | 37.9665 | -122.2791 | VALLEY VIEW 1105circuit_breaker | 139 | 810 | 44555.7385 | 7478.2552 | 37077.4832 | 104.2614 | 664.3344 | 2.4379e-05 | 2.4379e-05 | 4.0491 | 1.5 | 2760 | 1.6195e-06 | 2799 | 0 | 0 | 0.064785 | 2854 | 0
Bay Area | 7735 | 28 | 78.4275 | 74 | 103.24 | 13 | 1.3409e-05 | 0.061322 | 0.47746 | 0.11443 | 0.0028922 | 2.2807e-06 | 0.34845 | 0.16268 | 1.3077 | 7.892e-07 | 1.282e-05 | 0.37838 | 0.75966 | {535449DD-A4B3-4AA9-AB71-3DA62C691B7C} | 42491102 | SAUSALITO 1102 | 410 | 37.874 | -122.5127 | SAUSALITO 1102410 | 69 | 422 | 19626.5103 | 3495.0118 | 16131.4984 | 1900.8841 | 7843.9545 | 0.00016666 | 0.00017432 | 2.801 | 5.6923 | 2748 | 1.026e-05 | 2800 | 0 | 0 | 1.1812 | 2315 | 0
Central Coast | 5474 | 0 | 0 | 3 | 1.8153 | 1 | 1.171e-05 | 0.066432 | 0.042833 | 0.61678 | 2.4465 | 0.012129 | 0.31858 | 6.4555 | 1 | 7.779e-07 | 5.0157e-07 | 0 | 0 | {22E96A5A-3667-455E-A58A-C0A9770DDF94} | 182631102 | SAN LUIS OBISPO 1102 | 597518 | 35.2696 | -120.6686 | SAN LUIS OBISPO 1102597518 | 106 | 65 | 6670.2231 | 3448.5717 | 3221.6515 | 881.7949 | 110.7023 | 5.0157e-07 | 1.171e-05 |  | 3 | 2880 | 7.779e-07 | 2801 | 0 | 0 | 0.54792 | 1913 | 0
Central Coast | 7161 | 18 | 56.5456 | 34 | 63.7062 | 5 | 1.1582e-05 | 0.066432 | 0.0006208 | 0.054766 | 0.14096 | 4.4773e-05 | 0.063717 | 0.57881 | 1 | 7.6941e-07 | 4.3427e-06 | 0.52941 | 0.8876 | {FE7ADF6B-5FAD-4650-8E18-1F81A8FDEE84} | 182631107 | SAN LUIS OBISPO 1107 | circuit_breaker | 35.2613 | -120.6347 | SAN LUIS OBISPO 1107circuit_breaker | 54 | 22 | 3858.5229 | 2726.7982 | 1131.7248 | 1569.1089 | 628.2281 | 2.1714e-05 | 5.791e-05 | 3.1414 | 6.8 | 2852 | 3.8471e-06 | 2802 | 0 | 0 | 0.975 | 165 | 0
Bay Area | 25 | 166 | 427.3668 | 427 | 562.1477 | 60 | 1.1548e-05 | 0.066432 | 0.21785 | 0.11016 | 0.078047 | 0.00014044 | 0.091409 | 0.25618 | 0.63333 | 7.6714e-07 | 7.7469e-06 | 0.38876 | 0.76024 | {EA4820C6-602A-444A-A1BC-AC0CC345F5D7} | 24141101 | RALSTON 1101 | 48936 | 37.5171 | -122.3356 | RALSTON 110148936 | 185 | 582 | 42775.2235 | 9693.4724 | 33081.7511 | 7442.666 | 29537.592 | 0.00046481 | 0.00069286 | 2.5745 | 7.1167 | 2813 | 4.6028e-05 | 2803 | 0 | 0 | 4.6247 | 2900 | 0
Bay Area | 1040 | 31 | 85.2051 | 69 | 102.8664 | 23 | 1.1387e-05 | 0.066432 | 0.25789 | 0.11583 | 0.15739 | 0.0018513 | 2.0234 | 6.0799 | 0.60947 | 7.5645e-07 | 7.9039e-06 | 0.44928 | 0.82831 | {4B9E4541-F21D-43AC-ADB7-3A92CC33D20B} | 13111114 | SAN LEANDRO U 1114 | MR545 | 37.7035 | -122.1125 | SAN LEANDRO U 1114MR545 | 159 | 837 | 39491.2191 | 7220.0264 | 32271.1927 | 3494.5659 | 18097.3441 | 0.00018179 | 0.0002619 | 2.7486 | 3 | 2812 | 1.7398e-05 | 2804 | 0 | 0 | 2.1714 | 2878 | 0
Bay Area | 196 | 16 | 32.8681 | 33 | 43.2818 | 6 | 2.2662e-05 | 0.044288 | 0.82296 | 0.77947 | 6.0399 | 0.011346 | 0.10251 | 0.52743 | 2.3333 | 7.558e-07 | 2.4415e-05 | 0.48485 | 0.7594 | {9BD2CCED-08C0-4120-A490-E52866AF5C8D} | 12101103 | OAKLAND K 1103 | circuit_breaker | 37.8478 | -122.2291 | OAKLAND K 1103circuit_breaker | 172 | 1153 | 54391.0795 | 7913.1284 | 46477.9511 | 859.4149 | 378.7766 | 0.00014649 | 0.00013597 | 2.0543 | 5.5 | 2540 | 4.5348e-06 | 2805 | 0 | 0 | 0.53402 | 2052 | 0
Bay Area | 2371 | 18 | 58.2349 | 26 | 62.3289 | 4 | 1.1363e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0.0005531 | 0.1302 | 0.25 | 7.5488e-07 | 8.5073e-06 | 0.69231 | 0.93432 | {399AB5C7-22B7-4F32-8432-A7E05E9E2D06} | 13111114 | SAN LEANDRO U 1114 | MR544 | 37.7084 | -122.1271 | SAN LEANDRO U 1114MR544 | 211 | 1267 | 52658.0872 | 10049.3013 | 42608.7859 | 1064.9351 | 3725.4016 | 3.4029e-05 | 4.5453e-05 | 3.2353 | 6.5 | 2805 | 3.0195e-06 | 2806 | 0 | 0 | 0.66172 | 2897 | 0
Bay Area | 5766 | 1 | 1.246 | 1 | 1.246 | 1 | 1.093e-05 | 0.066431 |  |  |  |  | 0.96681 | 0.096903 | 1 | 7.2609e-07 | 1.093e-05 | 1 | 1 | {08FF18F2-2664-4D84-92E0-670D1D31847D} | 42991104 | LAS GALLINAS A 1104 | 1220 | 38.0098 | -122.5504 | LAS GALLINAS A 11041220 | 97 | 797 | 43225.3675 | 7696.9362 | 35528.4313 | 0 | 191.6559 | 1.093e-05 | 1.093e-05 | 1.246 | 1 | 2776 | 7.2609e-07 | 2807 | 0 | 0 | 0 | 694 | 0
North Valley | 6253 | 7 | 19.4327 | 187 | 101.1468 | 15 | 1.0885e-05 | 0.066432 | 6.2177 | 11.2628 | 28.139 | 0.32402 | 0.17817 | 1.2238 | 1 | 7.2314e-07 | 4.0751e-05 | 0.037433 | 0.19212 | {C6BC6538-2EB6-4DA5-9982-6A2D9BE60DD8} | 102361101 | HAMILTON BRANCH 1101 | 2082 | 40.2708 | -121.1269 | HAMILTON BRANCH 11012082 | 109 | 244 | 17289.5317 | 4925.5933 | 12363.9384 | 2146.9459 | 4784.4218 | 0.00061126 | 0.00016328 | 2.7761 | 12.4667 | 2332 | 1.0847e-05 | 2808 | 0 | 0 | 1.334 | 1571 | 0
Bay Area | 5600 | 0 | 0 | 1 | 0.45574 | 1 | 1.0844e-05 | 0.066431 | 0.21463 | 0.22239 | 0.0038381 | 8.2376e-07 | 2.0376 | 1.0801 | 1 | 7.2039e-07 | 2.3275e-06 | 0 | 0 | {D824A6B2-681A-48EF-8928-B97846B95D59} | 42991105 | LAS GALLINAS A 1105 | 1218 | 38.0247 | -122.5486 | LAS GALLINAS A 11051218 | 49 | 411 | 25002.9944 | 3755.6182 | 21247.3762 | 60.2784 | 1126.0745 | 2.3275e-06 | 1.0844e-05 |  | 1 | 2871 | 7.2039e-07 | 2809 | 0 | 0 | 0.037455 | 2884 | 0
Sierra | 8825 | 3 | 10.0431 | 10 | 13.9138 | 5 | 1.0832e-05 | 0.066431 | 0.14765 | 57.1554 | 278.7184 | 0.041154 | 0 | 12.1373 | 1.0358 | 7.1959e-07 | 8.664e-06 | 0.3 | 0.72181 | {F8951716-F878-4227-AE2D-235860A82922} | 158031101 | ECHO SUMMIT 1101 | 481660 | 38.8106 | -120.0319 | ECHO SUMMIT 1101481660 | 38 | 0 | 905.9644 | 905.9644 | 0 | 778.9778 | 0 | 4.332e-05 | 5.416e-05 | 3.3477 | 2 | 2802 | 3.5979e-06 | 2810 | 0 | 0 | 0.48403 | 1253 | 0
Bay Area | 7531 | 5 | 16.4698 | 86 | 55.8201 | 8 | 1.0829e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0.00082965 | 1.2637 | 0.5 | 7.194e-07 | 6.9534e-06 | 0.05814 | 0.29505 | {42064D42-EDBF-4ED5-8222-65863B241E1D} | 13111109 | SAN LEANDRO U 1109 | CR284 | 37.7436 | -122.1477 | SAN LEANDRO U 1109CR284 | 43 | 187 | 8164.7971 | 1501.5898 | 6663.2073 | 1126.0171 | 3091.4127 | 5.5628e-05 | 8.6633e-05 | 3.294 | 10.75 | 2823 | 5.7552e-06 | 2811 | 0 | 0 | 0.69967 | 2871 | 0
North Valley | 3715 | 14 | 38.6211 | 230 | 138.1803 | 14 | 1.0735e-05 | 0.066432 | 1.7626 | 1.4955 | 7.4697 | 0.042822 | 0.3848 | 2.0528 | 1 | 7.1314e-07 | 1.4116e-05 | 0.06087 | 0.2795 | {8A77F8FA-02FE-4834-A4BC-ADBE43D39923} | 102361101 | HAMILTON BRANCH 1101 | 3049 | 40.2767 | -121.1289 | HAMILTON BRANCH 11013049 | 52 | 152 | 8683.9763 | 2682.1998 | 6001.7765 | 1766.4723 | 4422.3758 | 0.00019763 | 0.00015029 | 2.7587 | 16.4286 | 2720 | 9.984e-06 | 2812 | 0 | 0 | 1.0976 | 2070 | 0
Central Coast | 4257 | 0 | 0 | 7 | 4.0094 | 1 | 1.0521e-05 | 0.066432 |  |  |  |  | 2.7058 | 16.9788 | 1 | 6.989e-07 | 1.0521e-05 | 0 | 0 | {77F4F191-CCC6-4075-AD1D-AD57A94CE7F5} | 182601103 | OCEANO 1103 | V22 | 35.1286 | -120.607 | OCEANO 1103V22 | 36 | 13 | 2775.5041 | 2481.8109 | 293.6931 | 1804.8041 | 97.4463 | 1.0521e-05 | 1.0521e-05 |  | 7 | 2778 | 6.989e-07 | 2813 | 0 | 0 | 1.1215 | 1920 | 0
Central Coast | 3165 | 19 | 42.3408 | 22 | 43.6793 | 4 | 1.0515e-05 | 0.066432 |  |  |  |  | 0.75608 | 0.15238 | 1 | 6.9853e-07 | 1.0515e-05 | 0.86364 | 0.96936 | {CAD84BE8-270C-4E67-9FBC-AF6CB4F5A5CC} | 182852204 | VIEJO 2204 | 9098 | 36.5996 | -121.9011 | VIEJO 22049098 | 189 | 1116 | 56783.072 | 9682.1971 | 47100.8749 | 444.1507 | 3060.345 | 4.206e-05 | 4.206e-05 | 2.2285 | 5.5 | 2779 | 2.7941e-06 | 2814 | 0 | 0 | 0.27598 | 2341 | 0
North Valley | 1494 | 6 | 13.513 | 326 | 159.7544 | 27 | 1.1301e-05 | 0.061511 | 8.2335 | 15.0124 | 35.3182 | 0.53671 | 0.13133 | 1.4132 | 1.2963 | 6.9392e-07 | 2.8832e-05 | 0.018405 | 0.084586 | {512E7C3F-C5ED-477A-A43F-85AACCF18F8D} | 102361101 | HAMILTON BRANCH 1101 | 87784 | 40.2567 | -121.1401 | HAMILTON BRANCH 110187784 | 44 | 104 | 11259.8874 | 2328.7215 | 8931.1659 | 2328.7215 | 8931.1659 | 0.00077846 | 0.00030513 | 2.2522 | 12.0741 | 2478 | 1.8736e-05 | 2815 | 0 | 0 | 1.447 | 128 | 0
North Valley | 6355 | 1 | 3.8265 | 156 | 74.8576 | 32 | 1.0306e-05 | 0.066432 | 2.8358 | 7.3902 | 34.7869 | 0.37493 | 0.63157 | 4.5673 | 1.0005 | 6.8466e-07 | 2.0643e-05 | 0.0064103 | 0.051118 | {FF704EC9-7B07-4166-A0E1-5C891877A473} | 102812101 | BIG MEADOWS 2101 | 2246 | 40.2108 | -121.1643 | BIG MEADOWS 21012246 | 56 | 108 | 5666.2953 | 2937.4924 | 2728.8029 | 2937.4924 | 2728.8029 | 0.00066056 | 0.0003298 | 3.8265 | 4.875 | 2595 | 2.1909e-05 | 2816 | 0 | 0 | 1.8253 | 2484 | 0
Bay Area | 342 | 1 | 1.6135 | 1 | 1.6135 | 1 | 1.0292e-05 | 0.066432 | 0 | 0 | 0 | 0 | 0 | 0.089602 | 1 | 6.8369e-07 | 0 | 1 | 1 | {CC913DB3-6A51-493D-BE11-D5EAF399B0A8} | 14101102 | ALHAMBRA 1102 | circuit_breaker | 37.9938 | -122.1301 | ALHAMBRA 1102circuit_breaker | 239 | 1142 | 51311.899 | 9246.0524 | 42065.8465 | 306.9084 | 895.7185 | 0 | 1.0292e-05 | 1.6135 | 1 | 2889 | 6.8369e-07 | 2817 | 0 | 0 | 0.1907 | 400 | 0
Bay Area | 737 | 38 | 115.5035 | 84 | 140.2448 | 18 | 1.0196e-05 | 0.066432 | 0.80167 | 0.28002 | 0.81932 | 0.0060224 | 0.35066 | 0.82608 | 0.88889 | 6.7734e-07 | 1.1674e-05 | 0.45238 | 0.82359 | {5B6AAB3F-644A-4510-BA3F-1EFCD22509A2} | 13350401 | WALDO 0401 | circuit_breaker | 37.9095 | -122.3067 | WALDO 0401circuit_breaker | 162 | 1463 | 69459.7953 | 9140.627 | 60319.1683 | 2562.0667 | 17075.9419 | 0.00021012 | 0.00018353 | 3.0396 | 4.6667 | 2766 | 1.2192e-05 | 2818 | 0 | 0 | 1.592 | 2877 | 0
Central Coast | 4836 | 1 | 3.8162 | 4 | 5.1651 | 1 | 1.0145e-05 | 0.066432 |  |  |  |  | 0.077434 | 2.8199 | 1 | 6.7393e-07 | 1.0145e-05 | 0.25 | 0.73884 | {7065F476-A653-46B8-B768-E4B58582997C} | 182052102 | SOLEDAD 2102 | 7008 | 36.4058 | -121.3537 | SOLEDAD 21027008 | 144 | 118 | 33139.1306 | 29112.5788 | 4026.5518 | 3543.9744 | 72.5893 | 1.0145e-05 | 1.0145e-05 | 3.8162 | 4 | 2787 | 6.7393e-07 | 2819 | 0 | 0 | 2.2021 | 2689 | 0
Bay Area | 5548 | 2 | 5.0588 | 14 | 10.4228 | 6 | 1.0109e-05 | 0.066432 | 0 | 0 | 0 | 0 | 1.7253e-12 | 0.069985 | 0.83333 | 6.7159e-07 | 3.0789e-06 | 0.14286 | 0.48536 | {FA2B109E-77DC-4E10-B450-A6980BE69B60} | 13111114 | SAN LEANDRO U 1114 | 9838 | 37.7025 | -122.1103 | SAN LEANDRO U 11149838 | 52 | 562 | 26810.0233 | 3949.4877 | 22860.5356 | 1189.5493 | 8262.8679 | 1.8474e-05 | 6.0657e-05 | 2.5294 | 2.3333 | 2864 | 4.0295e-06 | 2820 | 0 | 0 | 0.73915 | 385 | 0
Bay Area | 5396 | 273 | 921.4871 | 332 | 954.0046 | 14 | 1.1459e-05 | 0.056942 | 0.14858 | 0.071987 | 0.00052677 | 2.2637e-07 | 0 | 0.00090507 | 0.78571 | 6.6231e-07 | 7.55e-06 | 0.82229 | 0.96591 | {40980895-4B8E-4C74-B15F-E13FF900DC4F} | 22721102 | SNEATH LANE 1102 | circuit_breaker | 37.6222 | -122.4469 | SNEATH LANE 1102circuit_breaker | 70 | 310 | 17742.9255 | 4044.2651 | 13698.6604 | 1789.3661 | 3809.7734 | 0.0001057 | 0.00016043 | 3.3754 | 23.7143 | 2815 | 9.2723e-06 | 2821 | 0 | 0 | 1.1119 | 2845 | 0
Bay Area | 486 | 11 | 31.723 | 23 | 38.312 | 1 | 9.8626e-06 | 0.066432 | 0 | 0 | 0 | 0 | 0 | 0.13296 | 1 | 6.5519e-07 | 0 | 0.47826 | 0.82802 | {650AE2A0-8481-4167-A199-68E796B3390A} | 24031110 | BELMONT 1110 | 9090 | 37.5185 | -122.3035 | BELMONT 11109090 | 89 | 467 | 23008.6181 | 4185.121 | 18823.4971 | 0 | 150.5582 | 0 | 9.8626e-06 | 2.8839 | 23 | 2898 | 6.5519e-07 | 2822 | 0 | 0 | 0 | 742 | 0
Bay Area | 2477 | 0 | 0 | 6 | 3.9842 | 2 | 9.4335e-06 | 0.066432 | 1.6578 | 1.3037 | 1.514 | 0.0031382 | 1.9093 | 4.3023 | 1 | 6.2669e-07 | 1.2887e-05 | 0 | 0 | {F1CD3584-0342-4B1C-AC95-933DCB32DB86} | 12501113 | EL CERRITO G 1113 | circuit_breaker | 37.9162 | -122.3027 | EL CERRITO G 1113circuit_breaker | 199 | 791 | 33352.891 | 6919.0978 | 26433.7932 | 336.063 | 1296.0366 | 2.5775e-05 | 1.8867e-05 |  | 3 | 2746 | 1.2534e-06 | 2823 | 0 | 0 | 0.20882 | 2780 | 0
Bay Area | 418 | 11 | 26.9236 | 35 | 38.3237 | 15 | 9.2259e-06 | 0.066432 | 0.87093 | 0.47496 | 0.76346 | 0.0060361 | 0.21342 | 0.021342 | 0.46667 | 6.1289e-07 | 8.801e-06 | 0.31429 | 0.70253 | {C255CD66-4CFB-4E6F-AE78-6A76CA6EB0AA} | 14091104 | CASTRO VALLEY 1104 | MR236 | 37.7008 | -122.0899 | CASTRO VALLEY 1104MR236 | 259 | 1943 | 87129.8975 | 13504.2844 | 73625.613 | 1927.0653 | 9965.8966 | 0.00013201 | 0.00013839 | 2.4476 | 2.3333 | 2800 | 9.1934e-06 | 2824 | 0 | 0 | 1.1974 | 714 | 0
Bay Area | 7712 | 12 | 44.0571 | 21 | 48.1897 | 5 | 9.1723e-06 | 0.066432 | 8.7125 | 73.9203 | 151.8201 | 3.1685 | 3.7394 | 54.2053 | 1.0177 | 6.0933e-07 | 3.215e-05 | 0.57143 | 0.91424 | {DB131498-A71D-4A26-A77E-BBAB941A8DB9} | 13921101 | FRANKLIN 1101 | P138 | 38.0484 | -122.2481 | FRANKLIN 1101P138 | 40 | 51 | 3981.2584 | 2470.0232 | 1511.2353 | 2364.7362 | 1102.4839 | 0.00016075 | 4.5861e-05 | 3.6714 | 4.2 | 2439 | 3.0467e-06 | 2825 | 0 | 0 | 1.4694 | 671 | 0
North Valley | 7348 | 34 | 53.0859 | 116 | 94.6427 | 50 | 9.1394e-06 | 0.066432 | 0.19253 | 105.4446 | 676.1612 | 0.15689 | 0.044115 | 25.1444 | 1.0417 | 6.0715e-07 | 6.1246e-06 | 0.2931 | 0.56091 | {2FDD93D7-D61D-44CD-93DA-C1ACCE10D2C0} | 102812101 | BIG MEADOWS 2101 | 2510 | 40.2104 | -121.1644 | BIG MEADOWS 21012510 | 26 | 4 | 14178.3141 | 14131.8875 | 46.4267 | 6780.2402 | 33.1788 | 0.00030623 | 0.00045697 | 1.5613 | 2.32 | 2838 | 3.0357e-05 | 2826 | 0 | 0 | 4.213 | 1200 | 0
Bay Area | 6261 | 5 | 20.2454 | 5 | 20.2454 | 1 | 8.5073e-06 | 0.066432 | 0 | 0 | 0 | 0 | 0 | 0.065265 | 1 | 5.6516e-07 | 0 | 1 | 1 | {AC57E8D0-E406-43BB-B0B4-92AB46A557F5} | 22721102 | SNEATH LANE 1102 | 75844 | 37.64 | -122.4607 | SNEATH LANE 110275844 | 21 | 54 | 3774.7884 | 865.0219 | 2909.7665 | 184.0425 | 58.2418 | 0 | 8.5073e-06 | 4.0491 | 5 | 2892 | 5.6516e-07 | 2827 | 0 | 0 | 0.11436 | 1757 | 0
Central Valley | 9903 | 0 | 0 | 11 | 2.3475 | 1 | 8.4906e-06 | 0.066432 |  |  |  |  | 1.2611 | 0.48938 | 1 | 5.6405e-07 | 8.4906e-06 | 0 | 0 | {215B4A0E-B4E1-4DEB-8481-0B3FF4DD4D17} | 252691104 | INDIAN FLAT 1104 | 4440 | 37.677 | -119.7768 | INDIAN FLAT 11044440 | 6 | 0 | 376.2849 | 376.2849 | 0 | 376.2849 | 0 | 8.4906e-06 | 8.4906e-06 |  | 11 | 2806 | 5.6405e-07 | 2828 | 0 | 0 | 0.23381 | 1798 | 0
Central Coast | 2660 | 4 | 7.4993 | 21 | 16.4605 | 8 | 8.4732e-06 | 0.066432 | 0.10489 | 0.1112 | 0.14804 | 9.2912e-05 | 0.071626 | 4.8072 | 1.0094 | 5.6289e-07 | 2.8901e-06 | 0.19048 | 0.45559 | {121773FD-4C4B-4842-BF5D-136BCB9BFB8D} | 182402107 | FORT ORD 2107 | 36596 | 36.6736 | -121.7807 | FORT ORD 210736596 | 368 | 841 | 58675.0345 | 20177.9536 | 38497.0809 | 6277.7799 | 753.5961 | 2.312e-05 | 6.7785e-05 | 1.8748 | 2.625 | 2865 | 4.5031e-06 | 2829 | 0 | 0 | 3.9008 | 1338 | 0
Bay Area | 1096 | 20 | 77.247 | 22 | 78.3825 | 2 | 8.4692e-06 | 0.066432 | 0.0011931 | 0.00041086 | 3.865e-06 | 2.496e-09 | 0 | 0 | 0 | 5.6263e-07 | 3.199e-06 | 0.90909 | 0.98551 | {0670D960-5B0E-4306-B272-564D6CFEECFE} | 22721101 | SNEATH LANE 1101 | 68070 | 37.6087 | -122.4309 | SNEATH LANE 110168070 | 60 | 426 | 21755.9914 | 3445.6939 | 18310.2975 | 175.9556 | 1626.8225 | 6.3979e-06 | 1.6938e-05 | 3.8624 | 11 | 2862 | 1.1253e-06 | 2830 | 0 | 0 | 0.10933 | 2882 | 0
North Valley | 6179 | 3 | 9.7914 | 56 | 34.7689 | 10 | 8.3205e-06 | 0.066432 | 5.2544 | 11.0456 | 26.226 | 0.22268 | 1.023 | 7.1274 | 1.0115 | 5.5275e-07 | 1.8995e-05 | 0.053571 | 0.28161 | {D03C18EE-E1AA-4630-B396-89DAD0F5DDA8} | 102361101 | HAMILTON BRANCH 1101 | 53192 | 40.2726 | -121.0949 | HAMILTON BRANCH 110153192 | 59 | 127 | 8310.4211 | 3316.9892 | 4993.4319 | 1145.8186 | 414.7168 | 0.00018995 | 8.3205e-05 | 3.2638 | 5.6 | 2634 | 5.5275e-06 | 2831 | 0 | 0 | 0.71198 | 308 | 0
Central Coast | 2576 | 0 | 0 | 12 | 8.1573 | 1 | 7.6159e-06 | 0.066432 |  |  |  |  | 0.43805 | 44.4449 | 1.0177 | 5.0594e-07 | 7.6159e-06 | 0 | 0 | {6CCE4F90-013B-444F-9BDA-6C6A4EE75374} | 182222102 | DEL MONTE 2102 | 9060 | 36.608 | -121.8536 | DEL MONTE 21029060 | 335 | 1799 | 91336.4678 | 16709.22 | 74627.2478 | 1038.0388 | 29.2277 | 7.6159e-06 | 7.6159e-06 |  | 12 | 2814 | 5.0594e-07 | 2832 | 0 | 0 | 0.64501 | 1161 | 0
Sierra | 8203 | 0 | 0 | 21 | 9.5705 | 6 | 6.8291e-06 | 0.066431 | 0.28971 | 9.7197 | 23.3919 | 0.011881 | 0.094764 | 12.3978 | 1.0081 | 4.5367e-07 | 3.331e-06 | 0 | 0 | {2E3C216B-BFE5-488C-9EA5-E58CEF71CE83} | 152591101 | SUMMIT 1101 | 86658 | 39.3186 | -120.3789 | SUMMIT 110186658 | 25 | 19 | 1870.9999 | 1077.6311 | 793.3688 | 1026.4158 | 344.0684 | 1.9986e-05 | 4.0975e-05 |  | 3.5 | 2860 | 2.722e-06 | 2833 | 0 | 0 | 0.63779 | 148 | 0
Sierra | 7328 | 0 | 0 | 279 | 127.3204 | 35 | 6.7929e-06 | 0.066431 | 3.4476 | 6.1109 | 13.0478 | 0.07068 | 0.20341 | 6.8602 | 1.0003 | 4.5126e-07 | 1.6767e-05 | 0 | 0 | {E1505A10-613C-46C7-B0BB-34C322CF97E4} | 152591101 | SUMMIT 1101 | 48632 | 39.3201 | -120.3791 | SUMMIT 110148632 | 89 | 153 | 8061.6364 | 4368.1754 | 3693.461 | 4368.1754 | 3693.461 | 0.00058683 | 0.00023775 |  | 7.9714 | 2667 | 1.5794e-05 | 2834 | 0 | 0 | 2.7143 | 1285 | 0
Bay Area | 5702 | 7 | 26.7131 | 8 | 27.339 | 1 | 6.7e-06 | 0.066432 |  |  |  |  | 0 | 0.0013274 | 1 | 4.451e-07 | 6.7e-06 | 0.875 | 0.97711 | {E63B66A6-F711-492C-AE55-754D3FBB9FA4} | 22721101 | SNEATH LANE 1101 | circuit_breaker | 37.6221 | -122.4469 | SNEATH LANE 1101circuit_breaker | 38 | 92 | 5129.3903 | 1546.1502 | 3583.2401 | 448.9693 | 869.0709 | 6.7e-06 | 6.7e-06 | 3.8162 | 8 | 2829 | 4.451e-07 | 2835 | 0 | 0 | 0.27898 | 2898 | 0
Sierra | 9118 | 0 | 0 | 81 | 37.0847 | 9 | 6.6657e-06 | 0.066431 | 6.0891 | 5.8757 | 11.897 | 0.11739 | 0.71559 | 1.4533 | 1 | 4.4281e-07 | 2.9592e-05 | 0 | 0 | {9ACB9853-5199-45AF-9338-5444E567DE9F} | 152591101 | SUMMIT 1101 | 6627 | 39.3246 | -120.3841 | SUMMIT 11016627 | 15 | 47 | 1881.6877 | 903.7825 | 977.9052 | 903.7825 | 977.9052 | 0.00026633 | 5.9991e-05 |  | 9 | 2471 | 3.9853e-06 | 2836 | 0 | 0 | 0.56158 | 283 | 0
Bay Area | 1275 | 2 | 2.492 | 4 | 3.4035 | 2 | 6.4734e-06 | 0.066432 |  |  |  |  | 0.0033186 | 1.7263 | 1 | 4.3004e-07 | 6.4734e-06 | 0.5 | 0.7322 | {A91DA441-EEAC-4573-A6F0-741EAB76EF3B} | 13030402 | BANCROFT 0402 | circuit_breaker | 37.74 | -122.1553 | BANCROFT 0402circuit_breaker | 122 | 1233 | 58201.0944 | 7332.1581 | 50868.9363 | 149.8171 | 1027.8493 | 1.2947e-05 | 1.2947e-05 | 1.246 | 2 | 2832 | 8.6008e-07 | 2837 | 0 | 0 | 0.093092 | 2330 | 0
Central Valley | 5721 | 6 | 17.6388 | 883 | 418.1698 | 91 | 6.1962e-06 | 0.066431 | 0.79787 | 15.0681 | 52.4328 | 0.054624 | 0.046412 | 4.1328 | 1 | 4.1162e-07 | 5.593e-06 | 0.006795 | 0.042181 | {9EF30C64-8412-466B-8695-929E20570E0C} | 163692101 | SALT SPRINGS 2101 | 1232 | 38.4163 | -120.1331 | SALT SPRINGS 21011232 | 105 | 127 | 18295.9501 | 14525.4003 | 3770.5498 | 10582.3145 | 3063.5837 | 0.00050896 | 0.00056386 | 2.9398 | 9.7033 | 2840 | 3.7458e-05 | 2838 | 0 | 0 | 6.5755 | 612 | 0
Sierra | 5537 | 1 | 4.0491 | 7 | 6.7835 | 2 | 6.1882e-06 | 0.066431 | 0 | 0 | 0 | 0 | 0.05531 | 7.0217 | 1 | 4.1109e-07 | 2.8794e-06 | 0.14286 | 0.5969 | {BC06A3DB-78BE-4381-AABB-ACBB02D3E9CD} | 152591101 | SUMMIT 1101 | 48636 | 39.3117 | -120.3817 | SUMMIT 110148636 | 116 | 202 | 10832.0354 | 4495.7508 | 6336.2846 | 42.0553 | 23.3393 | 5.7588e-06 | 1.2376e-05 | 4.0491 | 3.5 | 2867 | 8.2218e-07 | 2839 | 0 | 0 | 0.026132 | 1119 | 0
Sierra | 6917 | 2 | 3.89 | 53 | 27.3026 | 8 | 5.8621e-06 | 0.066431 | 0.018732 | 3.7807 | 10.4588 | 0.00058774 | 0.073838 | 15.5098 | 1 | 3.8943e-07 | 3.7898e-06 | 0.037736 | 0.14248 | {B213CEE5-CB41-49F6-94A2-FED2BC2378C3} | 152591101 | SUMMIT 1101 | 742 | 39.3237 | -120.3791 | SUMMIT 1101742 | 44 | 8 | 2424.2556 | 2091.8057 | 332.4499 | 2091.8057 | 332.4499 | 3.0319e-05 | 4.6897e-05 | 1.945 | 6.625 | 2857 | 3.1154e-06 | 2840 | 0 | 0 | 1.2998 | 595 | 0
Central Valley | 7826 | 0 | 0 | 169 | 77.0194 | 13 | 5.5482e-06 | 0.066431 | 0.14868 | 20.8393 | 76.0467 | 0.022891 | 0.48026 | 3.2178 | 1 | 3.6857e-07 | 2.6154e-06 | 0 | 0 | {DE9905F1-4C65-4778-858E-371103A18BB4} | 163692101 | SALT SPRINGS 2101 | 3116 | 38.4164 | -120.134 | SALT SPRINGS 21013116 | 30 | 19 | 2271.9029 | 1616.0372 | 655.8658 | 1222.9143 | 426.8841 | 3.4e-05 | 7.2126e-05 |  | 13 | 2868 | 4.7914e-06 | 2841 | 0 | 0 | 0.75988 | 731 | 0
Sierra | 5387 | 59 | 141.4296 | 1686 | 884.443 | 185 | 5.3704e-06 | 0.066431 | 2.9812 | 12.6432 | 32.8805 | 0.10515 | 0.3307 | 11.862 | 1.0225 | 3.5676e-07 | 1.2124e-05 | 0.034994 | 0.15991 | {1755A18B-6E24-4507-ACE5-9CCC118C7159} | 152291101 | TAMARACK 1101 | circuit_breaker | 39.3138 | -120.4967 | TAMARACK 1101circuit_breaker | 271 | 580 | 47722.284 | 28848.3085 | 18873.9756 | 28053.5786 | 18441.239 | 0.002243 | 0.00099353 | 2.3971 | 9.1135 | 2762 | 6.6001e-05 | 2842 | 0 | 0 | 17.4317 | 1519 | 0
Central Valley | 7363 | 3 | 9.2342 | 913 | 424.124 | 68 | 5.3071e-06 | 0.066431 | 6.2556 | 19.1583 | 55.5024 | 0.49442 | 0.96701 | 5.4298 | 1.0011 | 3.5256e-07 | 1.9334e-05 | 0.0032859 | 0.021772 | {E91E5054-3C36-49EA-8A97-9B6297ED700A} | 163692101 | SALT SPRINGS 2101 | 4913 | 38.421 | -120.0974 | SALT SPRINGS 21014913 | 86 | 145 | 9037.0283 | 6222.6929 | 2814.3355 | 6222.6929 | 2814.3355 | 0.0013147 | 0.00036088 | 3.0781 | 13.4265 | 2625 | 2.3974e-05 | 2843 | 0 | 0 | 3.8666 | 1169 | 0
Sierra | 6918 | 0 | 0 | 38 | 17.318 | 13 | 4.9165e-06 | 0.066431 | 0.0054304 | 16.1566 | 48.0676 | 0.00040121 | 0.11249 | 18.3966 | 0.96869 | 3.2661e-07 | 2.02e-06 | 0 | 0 | {7891257C-3C80-41EA-9D49-0B129BA81A0A} | 152591101 | SUMMIT 1101 | 58642 | 39.3251 | -120.3796 | SUMMIT 110158642 | 20 | 11 | 3274.9209 | 3078.8651 | 196.0559 | 3078.8651 | 196.0559 | 2.626e-05 | 6.3914e-05 |  | 2.9231 | 2873 | 4.2459e-06 | 2844 | 0 | 0 | 1.9131 | 205 | 0
North Valley | 2421 | 1 | 1.9158 | 99 | 47.2544 | 8 | 9.2647e-06 | 0.04152 | 2.8074 | 2.1498 | 4.2793 | 0.034661 | 0.16759 | 0.41543 | 2.25 | 3.2221e-07 | 9.5811e-06 | 0.010101 | 0.040542 | {32D1F0F9-DFF9-4513-A71D-93DBB94A9BB3} | 102361101 | HAMILTON BRANCH 1101 | 37436 | 40.2562 | -121.14 | HAMILTON BRANCH 110137436 | 79 | 177 | 12868.1678 | 3303.8601 | 9564.3077 | 951.9489 | 1747.0935 | 7.6649e-05 | 7.4117e-05 | 1.9158 | 12.375 | 2793 | 2.5776e-06 | 2845 | 0 | 0 | 0.59151 | 614 | 0
Bay Area | 1305 | 0 | 0 | 1 | 0.67977 | 1 | 4.7092e-06 | 0.066432 |  |  |  |  | 0 | 0.0053097 | 1 | 3.1284e-07 | 4.7092e-06 | 0 | 0 | {2B049CE5-6DAC-4065-B555-915EF340A6E9} | 24031110 | BELMONT 1110 | 39182 | 37.5109 | -122.2994 | BELMONT 111039182 | 85 | 281 | 14128.0508 | 3455.5413 | 10672.5095 | 111.8017 | 178.3665 | 4.7092e-06 | 4.7092e-06 |  | 1 | 2849 | 3.1284e-07 | 2846 | 0 | 0 | 0.06947 | 719 | 0
Central Valley | 1985 | 14 | 37.5369 | 237 | 133.5325 | 42 | 4.2804e-06 | 0.066432 | 1.4853 | 64.9915 | 876.5214 | 4.5991 | 0.025969 | 12.1196 | 1.0164 | 2.8436e-07 | 4.9752e-06 | 0.059072 | 0.28111 | {733D4902-C475-4A3B-A2B1-E7586C4C7AE4} | 254061103 | DUNLAP 1103 | 7170 | 36.7263 | -118.9956 | DUNLAP 11037170 | 91 | 99 | 11356.4783 | 8635.1099 | 2721.3685 | 8635.1099 | 2721.3685 | 0.00020896 | 0.00017978 | 2.6812 | 5.6429 | 2846 | 1.1943e-05 | 2847 | 0 | 0 | 5.3656 | 257 | 0
North Valley | 4747 | 1 | 3.8265 | 44 | 24.7842 | 21 | 3.7843e-06 | 0.068854 | 0.16363 | 6.7316 | 26.4765 | 0.034061 | 1.1622 | 15.8479 | 1.0366 | 2.571e-07 | 2.1541e-06 | 0.022727 | 0.15439 | {C8BA9CFD-3C7E-444F-AD17-DFDE1ACC00EB} | 103181102 | CHESTER 1102 | 2564 | 40.2939 | -121.2428 | CHESTER 11022564 | 35 | 27 | 4385.5727 | 3603.0114 | 782.5613 | 3485.5234 | 674.6114 | 4.5237e-05 | 7.947e-05 | 3.8265 | 2.0952 | 2872 | 5.3991e-06 | 2848 | 0 | 0 | 2.1658 | 2534 | 0
Bay Area | 4237 | 5 | 17.4628 | 10 | 20.3058 | 2 | 2.7148e-06 | 0.066432 | 0 | 0 | 0 | 0 | 0.61947 | 0.18772 | 1 | 1.8035e-07 | 1.2377e-06 | 0.5 | 0.85999 | {1467F520-572F-46EC-93E0-707DAECC5FB0} | 24031103 | BELMONT 1103 | 8956 | 37.5067 | -122.2871 | BELMONT 11038956 | 64 | 113 | 7466.1331 | 2231.1917 | 5234.9415 | 228.0716 | 1186.804 | 2.4754e-06 | 5.4297e-06 | 3.4926 | 5 | 2876 | 3.607e-07 | 2849 | 0 | 0 | 0.14172 | 406 | 0
North Valley | 5682 | 0 | 0 | 2 | 0.91147 | 2 | 2.4204e-06 | 0.066432 |  |  |  |  | 0.090708 | 3.5671 | 1 | 1.6079e-07 | 2.4204e-06 | 0 | 0 | {655104DB-DE28-4723-9C66-99BF732C7F54} | 103181102 | CHESTER 1102 | circuit_breaker | 40.3025 | -121.227 | CHESTER 1102circuit_breaker | 119 | 174 | 12050.3428 | 5127.9433 | 6922.3995 | 460.5923 | 6.096 | 4.8408e-06 | 4.8408e-06 |  | 1 | 2869 | 3.2158e-07 | 2850 | 0 | 0 | 0.2862 | 2344 | 0
Central Valley | 9477 | 5 | 13.488 | 95 | 49.0018 | 11 | 2.1891e-06 | 0.066432 | 0.20397 | 56.7945 | 276.493 | 0.088635 | 0.093524 | 26.104 | 1.0284 | 1.4543e-07 | 8.9705e-07 | 0.052632 | 0.27526 | {DA87C478-BBD3-40FA-ACA7-D9696B584D48} | 254061102 | DUNLAP 1102 | 7290 | 36.7289 | -118.9454 | DUNLAP 11027290 | 14 | 8 | 1363.739 | 1178.1007 | 185.6383 | 1178.1007 | 185.6383 | 9.8676e-06 | 2.408e-05 | 2.6976 | 8.6364 | 2878 | 1.5997e-06 | 2851 | 0 | 0 | 0.73204 | 1863 | 0
| 9714 | [18 empty] | {3A7B6052-3325-40C5-B01B-9EE013874399} | 24181104 | SAN CARLOS 1104 | 9048 | 37.4783 | -122.2611 | SAN CARLOS 11049048 | 3 | 0 | 24.5909 | 24.5909 | 0 | 24.5909 | 0 |  |  |  |  | 2951 | 0 | 2897 | 0 | 0 | 0.01528 | 3023 | 0
| 7447 | [18 empty] | {1FEA32A9-A9DB-486B-B930-6597B0D6C986} | 182391103 | OILFIELDS 1103 | 2757 | 35.8313 | -120.9578 | OILFIELDS 11032757 | 18 | 8 | 4630.5172 | 4491.0736 | 139.4436 | 4491.0736 | 139.4436 |  |  |  |  | 2936 | 0 | 2966 | 0 | 0 | 2.7906 | 2973 | 0
| 9001 | [18 empty] | {24566083-7477-436E-B006-AF0B8D860874} | 254452101 | MARIPOSA 2101 | 90130 | 37.4926 | -119.9662 | MARIPOSA 210190130 | 10 | 0 | 144.8101 | 144.8101 | 0 | 144.8101 | 0 |  |  |  |  | 2940 | 0 | 2886 | 0 | 0 | 0.089981 | 2988 | 0
| 9068 | [18 empty] | {5A8D30A3-8AE5-4F6B-B53A-735A17ABC0FB} | 252531101 | SAN JOAQUIN #3 1101 | circuit_breaker | 37.254 | -119.5194 | SAN JOAQUIN #3 1101circuit_breaker | 42 | 15 | 9006.5115 | 8550.0082 | 456.5033 | 8550.0082 | 456.5033 |  |  |  |  | 2982 | 0 | 2871 | 0 | 0 | 5.3127 | 3112 | 0
| 9663 | [18 empty] | {5DA8991F-2CE2-4FD2-84E6-8E0B8213A71A} | 43201102 | STAFFORD 1102 | 784704 | 38.1382 | -122.6232 | STAFFORD 1102784704 | 5 | 0 | 43.8835 | 43.8835 | 0 | 43.8835 | 0 |  |  |  |  | 2983 | 0 | 2881 | 0 | 0 | 0.027268 | 3087 | 0
| 9393 | [18 empty] | {B2A3B189-1DF8-463C-BF6C-3A421128527B} | 12022215 | CLAYTON 2215 | 9765 | 37.9214 | -122.0102 | CLAYTON 22159765 | 39 | 19 | 2533.8665 | 1507.3257 | 1026.5408 | 425.4979 | 81.3198 |  |  |  |  | 3055 | 0 | 2932 | 0 | 0 | 0.26439 | 3117 | 0
| 9758 | [18 empty] | {2FC93923-0AF8-4A4D-9F96-EF0ED8AF2245} | 42711102 | CALISTOGA 1102 | 66730 | 38.5777 | -122.5257 | CALISTOGA 110266730 | 11 | 0 | 1883.757 | 1883.757 | 0 | 1883.757 | 0 |  |  |  |  | 2942 | 0 | 2916 | 0 | 0 | 1.1705 | 3058 | 0
| 7313 | [18 empty] | {369633AA-CFA4-4128-87F4-3265F391CCA6} | 63642106 | PEABODY 2106 | circuit_breaker | 38.2853 | -121.9704 | PEABODY 2106circuit_breaker | 16 | 1 | 1671.8083 | 1663.2394 | 8.5689 | 1514.2978 | 8.5689 |  |  |  |  | 2948 | 0 | 2961 | 0 | 0 | 0.94094 | 2958 | 0
| 9918 | [18 empty] | {430BD33F-FEB4-414F-BF1F-8CCB997A468A} | 162831702 |  | 188426 | 38.1684 | -120.1026 | 188426 | 1 | 0 | 4.572 | 4.572 | 0 | 4.572 | 0 |  |  |  |  | 2957 | 0 | 2898 | 0 | 0 | 0.0028409 | 2968 | 0
| 9400 | [18 empty] | {FFDB1F5B-AEE3-4CB6-9A6F-D3D25805592F} | 253642103 | POSO MOUNTAIN 2103 | circuit_breaker | 35.5592 | -118.9574 | POSO MOUNTAIN 2103circuit_breaker | 16 | 3 | 3773.9816 | 3720.379 | 53.6026 | 3720.379 | 53.6026 |  |  |  |  | 3127 | 0 | 2852 | 0 | 0 | 2.3117 | 3107 | 0
| 10004 | [18 empty] | {9E2DDAEA-6DE8-45F1-86FD-333F77EBF1FD} | 158041101 | WASHINGTON CITY GEN. 1101 | circuit_breaker | 39.3639 | -120.7922 | WASHINGTON CITY GEN. 1101circuit_breaker | 3 | 0 | 20.3534 | 20.3534 | 0 | 20.3534 | 0 |  |  |  |  | 3035 | 0 | 2913 | 0 | 0 | 0.012647 | 3110 | 0
| 9403 | [18 empty] | {56415AA1-122C-4BC6-8C7D-172F2B1EFCC0} | 163692102 | SALT SPRINGS 2102 | 3118 | 38.4164 | -120.1341 | SALT SPRINGS 21023118 | 14 | 1 | 138.0314 | 115.8501 | 22.1813 | 115.8501 | 22.1813 |  |  |  |  | 2977 | 0 | 2857 | 0 | 0 | 0.071986 | 2963 | 0
| 9683 | [18 empty] | {75A395F4-172A-4FF6-844A-F6A1B941CE83} | 182611103 | PASO ROBLES 1103 | N02 | 35.7193 | -120.8649 | PASO ROBLES 1103N02 | 10 | 0 | 70.9341 | 70.9341 | 0 | 70.9341 | 0 |  |  |  |  | 3008 | 0 | 2889 | 0 | 0 | 0.044076 | 2976 | 0
| 9410 | [18 empty] | {EEA63280-84EF-4F1E-BEC0-47F8D6EB4C01} | 43071101 | DUNBAR 1101 | 13481 | 38.4267 | -122.5553 | DUNBAR 110113481 | 27 | 30 | 3167.9428 | 1675.6333 | 1492.3095 | 0 | 42.138 |  |  |  |  | 3111 | 0 | 2859 | 0 | 0 | 0 | 3056 | 0
| 9735 | [18 empty] | {ABB7B77D-2EF2-4B3C-9B77-BF1774A4BD64} | 12061105 | BERKELEY F 1105 | BR166 | 37.8852 | -122.2551 | BERKELEY F 1105BR166 | 6 | 0 | 61.4345 | 61.4345 | 0 | 61.4345 | 0 |  |  |  |  | 3044 | 0 | 2905 | 0 | 0 | 0.038174 | 2921 | 0
| 8116 | [18 empty] | {BE0D8CE5-BE7F-4D94-B792-C4D840A2819E} | 42631108 | PETALUMA C 1108 | 636 | 38.2618 | -122.7158 | PETALUMA C 1108636 | 158 | 161 | 29950.6965 | 14844.2499 | 15106.4466 | 14844.2499 | 15106.4466 |  |  |  |  | 3070 | 0 | 2942 | 0 | 0 | 9.2238 | 2941 | 0
| 9794 | [18 empty] | {664F5053-AB62-43A2-9999-CB6966E7F628} | 43211101 | HARTLEY 1101 | 58095 | 39.0406 | -122.9367 | HARTLEY 110158095 | 7 | 5 | 569.46 | 251.9158 | 317.5442 | 251.9158 | 317.5442 |  |  |  |  | 2990 | 0 | 2928 | 0 | 0 | 0.15653 | 3094 | 0
| 8946 | [18 empty] | {F53F100A-A47D-4F77-AE95-9A2266045C73} | 103261101 | ANDERSON 1101 | 1390 | 40.441 | -122.2964 | ANDERSON 11011390 | 41 | 86 | 4303.2128 | 1742.8128 | 2560.4 | 15.3102 | 6.096 |  |  |  |  | 3120 | 0 | 2878 | 0 | 0 | 0.0095133 | 2961 | 0
| 7241 | [18 empty] | {3B54DCC0-9E34-4A0D-BB42-D31181D2C4D7} | 182631107 | SAN LUIS OBISPO 1107 | V58 | 35.247 | -120.6494 | SAN LUIS OBISPO 1107V58 | 67 | 18 | 4220.0544 | 3598.077 | 621.9775 | 1708.3239 | 24.5549 |  |  |  |  | 2952 | 0 | 2959 | 0 | 0 | 1.0615 | 3014 | 0
| 7133 | [18 empty] | {82A82E49-B7B9-4B20-91CE-19896367619D} | 153652105 | SHINGLE SPRINGS 2105 | 51738 | 38.6794 | -120.9799 | SHINGLE SPRINGS 210551738 | 52 | 71 | 4005.9683 | 1844.3225 | 2161.6458 | 26.6806 | 0 |  |  |  |  | 3017 | 0 | 2969 | 0 | 0 | 0.016579 | 2986 | 0
| 9937 | [18 empty] | {011DA57D-3361-4E85-BC2A-97718564E64F} | 182611103 | PASO ROBLES 1103 | N04 | 35.7334 | -120.8792 | PASO ROBLES 1103N04 | 10 | 0 | 858.0287 | 858.0287 | 0 | 858.0287 | 0 |  |  |  |  | 2904 | 0 | 2902 | 0 | 0 | 0.53315 | 2894 | 0
| 10128 | [18 empty] | {605FF237-9C18-43DA-A8F4-4C36FFCCA7D6} | 158011101 | SIERRA CITY GEN 1101 | 1101/2 | 39.5682 | -120.628 | SIERRA CITY GEN 11011101/2 | 1 | 0 | 8.5137 | 8.5137 | 0 | 8.5137 | 0 |  |  |  |  | 2986 | 0 | 2915 | 0 | 0 | 0.0052902 | 3125 | 0
| 9987 | [18 empty] | {FF54465D-5764-4C87-9FA1-2FCC27FF3FF8} | 182581105 | GOLDTREE 1105 | 551904 | 35.3204 | -120.692 | GOLDTREE 1105551904 | 4 | 0 | 35.7177 | 35.7177 | 0 | 35.7177 | 0 |  |  |  |  | 3126 | 0 | 2910 | 0 | 0 | 0.022194 | 2923 | 0
| 10133 | [18 empty] | {E5E88710-33BB-4103-ABE7-ACD5B4972589} | 48011146 | CALPINE 1146 | 394G | 38.8264 | -122.7998 | CALPINE 1146394G | 3 | 0 | 18.1683 | 18.1683 | 0 | 18.1683 | 0 |  |  |  |  | 3106 | 0 | 2883 | 0 | 0 | 0.011289 | 2993 | 0
| 9654 | [18 empty] | {CAAFE659-24FA-408F-BA2E-FF77F42F1864} | 103221101 | KANAKA 1101 | 1036 | 39.5633 | -121.3071 | KANAKA 11011036 | 6 | 2 | 1011.552 | 979.1369 | 32.4151 | 979.1369 | 32.4151 |  |  |  |  | 3080 | 0 | 2877 | 0 | 0 | 0.60841 | 3006 | 0
| 8404 | [18 empty] | {1190A046-44FA-405F-8A82-A8C20ADEFCFC} | 42091102 | MIRABEL 1102 | 13597 | 38.5053 | -122.9241 | MIRABEL 110213597 | 9 | 46 | 2313.865 | 625.9642 | 1687.9008 | 625.9642 | 1687.9008 |  |  |  |  | 2920 | 0 | 2941 | 0 | 0 | 0.38896 | 2974 | 0
| 9681 | [18 empty] | {4983E6BE-3B0D-43DF-9F14-94B620236C4F} | 182611103 | PASO ROBLES 1103 | 451760 | 35.7332 | -120.8795 | PASO ROBLES 1103451760 | 5 | 0 | 82.4454 | 82.4454 | 0 | 82.4454 | 0 |  |  |  |  | 2964 | 0 | 2885 | 0 | 0 | 0.051229 | 2955 | 0
| 9441 | [18 empty] | {C805E056-6565-4701-B47E-65A72A694487} | 102781101 | ELK CREEK 1101 | circuit_breaker | 39.5932 | -122.5439 | ELK CREEK 1101circuit_breaker | 11 | 0 | 130.7379 | 130.7379 | 0 | 130.7379 | 0 |  |  |  |  | 3076 | 0 | 2891 | 0 | 0 | 0.081237 | 3064 | 0
| 9704 | [18 empty] | {14BEC098-B04A-4CB2-9AA3-38D63A101CE1} | 12501105 | EL CERRITO G 1105 | BR164 | 37.8856 | -122.2541 | EL CERRITO G 1105BR164 | 7 | 0 | 91.5845 | 91.5845 | 0 | 91.5845 | 0 |  |  |  |  | 2926 | 0 | 2893 | 0 | 0 | 0.056908 | 2979 | 0
| 8335 | [18 empty] | {7A8B2A60-24C7-4493-B0A2-97491FFFA04C} | 152481104 | BRUNSWICK 1104 | 7181 | 39.2456 | -121.0444 | BRUNSWICK 11047181 | 18 | 53 | 3354.5452 | 1196.7092 | 2157.836 | 1196.7092 | 2157.836 |  |  |  |  | 3014 | 0 | 2939 | 0 | 0 | 0.7436 | 3119 | 0
| 7745 | [18 empty] | {113FEF80-B5A7-4041-A279-F58DE4B71B87} | 182082103 | LOS OSITOS 2103 | 7062 | 36.2789 | -121.303 | LOS OSITOS 21037062 | 60 | 61 | 27434.5707 | 19658.415 | 7776.1557 | 19658.415 | 7776.1557 |  |  |  |  | 2919 | 0 | 2963 | 0 | 0 | 12.2152 | 3111 | 0
| 9450 | [18 empty] | {582D525E-AEFD-49AD-B483-1141532B60A7} | 153612103 | CLARKSVILLE 2103 | circuit_breaker | 38.6558 | -121.0596 | CLARKSVILLE 2103circuit_breaker | 72 | 5 | 2400.7042 | 2324.8024 | 75.9018 | 239.3697 | 0 |  |  |  |  | 2979 | 0 | 2901 | 0 | 0 | 0.14874 | 3075 | 0
| 7381 | [18 empty] | {D4E144DE-8AEF-45D3-9080-EB1CCEA62B46} | 43061101 | COVELO 1101 | 37328 | 39.7866 | -123.2483 | COVELO 110137328 | 212 | 235 | 56836.3037 | 37925.6018 | 18910.7019 | 6550.0939 | 1617.6354 |  |  |  |  | 3087 | 0 | 2955 | 0 | 0 | 4.07 | 2969 | 0
| 10158 | [18 empty] | {594F557D-6CF0-4B0F-964C-AC76F779089D} | 189001101 | DIABLO CANYON 1101 | circuit_breaker | 35.2122 | -120.8557 | DIABLO CANYON 1101circuit_breaker | 0 | 1 | 64.2348 | 0 | 64.2348 | 0 | 64.2348 |  |  |  |  | 2981 | 0 | 2862 | 0 | 0 | 0 | 3101 | 0
| 9098 | [18 empty] | {E1A0A01B-9D60-4F0B-9CA5-E97715E5EFA6} | 255292108 | WOODWARD 2108 | 688294 | 36.9857 | -119.6388 | WOODWARD 2108688294 | 5 | 0 | 24.3604 | 24.3604 | 0 | 24.3604 | 0 |  |  |  |  | 3102 | 0 | 2869 | 0 | 0 | 0.015137 | 3001 | 0
| 8689 | [18 empty] | {DF5213A8-5BDB-44E0-A4B9-58E6CCF1A0EB} | 14671103 | SOBRANTE 1103 | N510R | 37.886 | -122.1893 | SOBRANTE 1103N510R | 29 | 25 | 2628.4483 | 1406.1178 | 1222.3305 | 404.6092 | 70.661 |  |  |  |  | 3100 | 0 | 2945 | 0 | 0 | 0.25141 | 3104 | 0
| 8771 | [18 empty] | {DDE57A1E-80D5-431E-961E-F1D86837BDD0} | 14091108 | CASTRO VALLEY 1108 | MR525 | 37.702 | -122.0378 | CASTRO VALLEY 1108MR525 | 7 | 3 | 177.5021 | 98.2491 | 79.253 | 98.2491 | 79.253 |  |  |  |  | 3098 | 0 | 2935 | 0 | 0 | 0.061049 | 2916 | 0
| 7967 | [18 empty] | {031CA341-2C0B-4194-9FCE-C18FD57B6895} | 42851121 | FORT ROSS 1121 | 204 | 38.5286 | -123.2068 | FORT ROSS 1121204 | 123 | 65 | 47901.7833 | 30176.1504 | 17725.6329 | 30176.1504 | 17725.6329 |  |  |  |  | 2907 | 0 | 2954 | 0 | 0 | 18.7506 | 2942 | 0
| 7180 | [18 empty] | {1C1CA89F-8D6E-4D8E-B038-38C87CE5A599} | 42661102 | WILLITS 1102 | 1270 | 39.4091 | -123.3481 | WILLITS 11021270 | 58 | 229 | 9749.0991 | 2454.7077 | 7294.3913 | 0 | 127.3131 |  |  |  |  | 2934 | 0 | 2968 | 0 | 0 | 0 | 3044 | 0
| 7710 | [18 empty] | {74C9689B-27E2-45AE-B69F-F01C8E2CB358} | 24251101 | WOODSIDE 1101 | circuit_breaker | 37.437 | -122.2421 | WOODSIDE 1101circuit_breaker | 103 | 74 | 10936.81 | 7096.7537 | 3840.0563 | 16.0021 | 0 |  |  |  |  | 3007 | 0 | 2970 | 0 | 0 | 0.0099432 | 3086 | 0
| 7357 | [18 empty] | {60C1A406-48B4-41B2-8A0C-9258948EB086} | 182391103 | OILFIELDS 1103 | 5175 | 35.7491 | -120.8802 | OILFIELDS 11035175 | 19 | 23 | 3937.6062 | 3554.759 | 382.8472 | 3372.5858 | 312.9119 |  |  |  |  | 2987 | 0 | 2972 | 0 | 0 | 2.0956 | 2954 | 0
| 9905 | [18 empty] | {9C37E848-C9FB-4404-B824-088800AAA1AF} | 82831109 | MILPITAS 1109 | 62157 | 37.4945 | -121.8236 | MILPITAS 110962157 | 4 | 1 | 118.8834 | 72.1015 | 46.7819 | 72.1015 | 46.7819 |  |  |  |  | 3033 | 0 | 2896 | 0 | 0 | 0.044802 | 3009 | 0
| 7326 | [18 empty] | {011DEA9E-857C-400B-8F07-19E7424464B0} | 182581107 | GOLDTREE 1107 | circuit_breaker | 35.3199 | -120.6931 | GOLDTREE 1107circuit_breaker | 59 | 29 | 6303.7814 | 5718.1268 | 585.6546 | 1525.8896 | 63.5407 |  |  |  |  | 2905 | 0 | 2962 | 0 | 0 | 0.94814 | 750 | 0
| 9928 | [18 empty] | {BD51C9D3-D0BA-422F-BCD5-DCA7AB571829} | 158011101 | SIERRA CITY GEN 1101 | circuit_breaker | 39.5685 | -120.6284 | SIERRA CITY GEN 1101circuit_breaker | 3 | 0 | 21.2814 | 21.2814 | 0 | 21.2814 | 0 |  |  |  |  | 3068 | 0 | 2900 | 0 | 0 | 0.013224 | 3042 | 0
| 9035 | [18 empty] | {970BC050-24B8-4916-A013-B639A58BC60E} | 152582109 | DEL MAR 2109 | 38684 | 38.839 | -121.2328 | DEL MAR 210938684 | 11 | 2 | 1585.5134 | 1501.1576 | 84.3558 | 0 | 19.9744 |  |  |  |  | 3028 | 0 | 2909 | 0 | 0 | 0 | 3011 | 0
| 9948 | [18 empty] | {0E163071-14D9-42E7-B9B8-B27ACF143A75} | 12541104 | OAKLAND X 1104 | CR101 | 37.8188 | -122.206 | OAKLAND X 1104CR101 | 5 | 0 | 28.3921 | 28.3921 | 0 | 28.3921 | 0 |  |  |  |  | 2918 | 0 | 2904 | 0 | 0 | 0.017642 | 3115 | 0
| 8019 | [18 empty] | {B557525E-C955-4555-A43D-602C62B6D5B3} | 14592105 | BRENTWOOD 2105 | 502672 | 37.8678 | -121.6382 | BRENTWOOD 2105502672 | 157 | 122 | 36602.0692 | 29946.4669 | 6655.6023 | 1990.2405 | 625.4042 |  |  |  |  | 3057 | 0 | 2934 | 0 | 0 | 1.2367 | 3096 | 0
| 9092 | [18 empty] | {CA99B367-8DC7-4E82-BCC3-DFC89B2C9160} | 83622105 | CAMP EVERS 2105 | 95050 | 37.0888 | -122.0876 | CAMP EVERS 210595050 | 19 | 0 | 223.2117 | 223.2117 | 0 | 223.2117 | 0 |  |  |  |  | 3079 | 0 | 2860 | 0 | 0 | 0.1387 | 2937 | 0
| 9490 | [18 empty] | {B645C72A-8233-4D5A-9F66-3DBF30EFFB75} | 188881701 |  | circuit_breaker | 34.5442 | -119.8652 | circuit_breaker | 1 | 1 | 177.962 | 168.4127 | 9.5493 | 168.4127 | 9.5493 |  |  |  |  | 3058 | 0 | 2892 | 0 | 0 | 0.10465 | 3099 | 0
| 9990 | [18 empty] | {8BA4213A-D34B-4B87-B8F6-E146FF0B7281} | 182402106 | FORT ORD 2106 | 9656 | 36.6566 | -121.7669 | FORT ORD 21069656 | 6 | 0 | 188.9883 | 188.9883 | 0 | 188.9883 | 0 |  |  |  |  | 3023 | 0 | 2912 | 0 | 0 | 0.11743 | 3067 | 0
| 8702 | [18 empty] | {18905925-DFA6-44AE-B447-3A99A2ABC9ED} | 252021101 | ANTELOPE 1101 | 1631 | 35.666 | -120.0709 | ANTELOPE 11011631 | 53 | 31 | 19994.4998 | 18929.4401 | 1065.0597 | 1210.7069 | 19.5073 |  |  |  |  | 2929 | 0 | 2937 | 0 | 0 | 0.7523 | 3108 | 0
| 7587 | [18 empty] | {6A034A59-B030-4B42-9C02-B5134DF1FD0A} | 43291105 | PUEBLO 1105 | 3022 | 38.3507 | -122.2859 | PUEBLO 11053022 | 177 | 141 | 25387.3621 | 14664.2587 | 10723.1034 | 238.6731 | 0 |  |  |  |  | 2994 | 0 | 2971 | 0 | 0 | 0.1483 | 3063 | 0
| 9337 | [18 empty] | {18F7A415-6C0E-4E68-A9B1-1EAFDA3A8A3D} | 42281105 | POTTER VALLEY P H 1105 | 990354 | 39.3618 | -123.1277 | POTTER VALLEY P H 1105990354 | 1 | 0 | 6.5127 | 6.5127 | 0 | 6.5127 | 0 |  |  |  |  | 2931 | 0 | 2863 | 0 | 0 | 0.0040468 | 2981 | 0
| 9662 | [18 empty] | {559E140E-BB75-460E-8600-94EB2CC41D94} | 258131101 | SCE TEHACHAPI 1101 | circuit_breaker | 35.1973 | -118.7006 | SCE TEHACHAPI 1101circuit_breaker | 2 | 3 | 4118.6858 | 1862.134 | 2256.5518 | 1862.134 | 2256.5518 |  |  |  |  | 2976 | 0 | 2879 | 0 | 0 | 1.1571 | 3074 | 0
| 7896 | [18 empty] | {AC82A3F6-A35E-40B3-B30F-C23643AC0649} | 152481110 | BRUNSWICK 1110 | circuit_breaker | 39.231 | -121.035 | BRUNSWICK 1110circuit_breaker | 109 | 129 | 7405.2406 | 2750.224 | 4655.0166 | 6.096 | 0 |  |  |  |  | 3046 | 0 | 2951 | 0 | 0 | 0.0037879 | 3092 | 0
| 8272 | [18 empty] | {79FEFA25-425D-4CA0-8714-2AC25C0E088A} | 102601101 | GLENN 1101 | 2012 | 39.7809 | -122.2971 | GLENN 11012012 | 88 | 54 | 49769.7182 | 48377.7244 | 1391.9937 | 480.0698 | 44.172 |  |  |  |  | 3011 | 0 | 2949 | 0 | 0 | 0.2983 | 3034 | 0
| 9502 | [18 empty] | {79DCCFC3-0111-4F08-BE2C-9A811B867436} | 103331101 | CORNING 1101 | 35974 | 39.9356 | -122.4017 | CORNING 110135974 | 19 | 4 | 1390.0483 | 1338.0934 | 51.9549 | 114.0493 | 6.096 |  |  |  |  | 3010 | 0 | 2906 | 0 | 0 | 0.070867 | 2983 | 0
| 8310 | [18 empty] | {F21A680A-E282-4C69-AC36-05BB391457FE} | 102541101 | VOLTA 1101 | circuit_breaker | 40.4593 | -121.8676 | VOLTA 1101circuit_breaker | 119 | 62 | 19127.8259 | 14809.7042 | 4318.1217 | 14809.7042 | 4318.1217 |  |  |  |  | 3115 | 0 | 2947 | 0 | 0 | 9.2023 | 2949 | 0
| 9209 | [18 empty] | {44DEC261-543D-4709-894B-61B8ADC18491} | 102911103 | WYANDOTTE 1103 | 66146 | 39.4971 | -121.4579 | WYANDOTTE 110366146 | 6 | 1 | 339.7904 | 252.3083 | 87.4822 | 252.3083 | 87.4822 |  |  |  |  | 2958 | 0 | 2894 | 0 | 0 | 0.15678 | 2905 | 0
| 8157 | [18 empty] | {2258BA59-F952-4D7E-A5B4-7204CE2B68CB} | 182601103 | OCEANO 1103 | 76678 | 35.1221 | -120.5916 | OCEANO 110376678 | 17 | 22 | 1283.4224 | 597.8557 | 685.5667 | 88.7522 | 301.4065 |  |  |  |  | 2938 | 0 | 2940 | 0 | 0 | 0.055148 | 3046 | 0
| 9519 | [18 empty] | {485D794E-EDB7-4779-A265-326DD68DD55C} | 42631109 | PETALUMA C 1109 | 664732 | 38.1908 | -122.6627 | PETALUMA C 1109664732 | 13 | 5 | 1553.9374 | 1437.8147 | 116.1227 | 1437.8147 | 116.1227 |  |  |  |  | 2962 | 0 | 2929 | 0 | 0 | 0.89342 | 3097 | 0
| 7406 | [18 empty] | {1C105F4C-AE80-4099-9437-85CB973612DF} | 42481105 |  | 908 | 38.0925 | -122.5763 | 908 | 98 | 260 | 15858.5289 | 3596.4627 | 12262.0662 | 1022.6867 | 1396.9246 |  |  |  |  | 2933 | 0 | 2958 | 0 | 0 | 0.63547 | 3071 | 0
| 7009 | [18 empty] | {4198C21C-60CC-4B51-804E-CE0EA277ED81} | 182981102 | JOLON 1102 | 7004 | 35.9367 | -121.0781 | JOLON 11027004 | 156 | 165 | 42004.6432 | 32508.6758 | 9495.9674 | 8688.0359 | 2620.8826 |  |  |  |  | 2955 | 0 | 2960 | 0 | 0 | 5.3985 | 3032 | 0
| 9721 | [18 empty] | {1EF86466-F881-472F-AD0A-3DC35663082A} | 182631107 | SAN LUIS OBISPO 1107 | V08 | 35.2449 | -120.6492 | SAN LUIS OBISPO 1107V08 | 6 | 0 | 39.9511 | 39.9511 | 0 | 39.9511 | 0 |  |  |  |  | 2935 | 0 | 2899 | 0 | 0 | 0.024824 | 2933 | 0
| 9031 | [18 empty] | {EC3D5092-5EAD-44A6-A8B2-0227C409E453} | 14232103 | SAN RAMON 2103 | MR279 | 37.7029 | -121.9121 | SAN RAMON 2103MR279 | 10 | 2 | 394.99 | 323.7748 | 71.2152 | 4.572 | 0 |  |  |  |  | 3109 | 0 | 2861 | 0 | 0 | 0.0028409 | 3116 | 0
| 7042 | [18 empty] | {AC54FADD-7787-4603-A3A1-1A1440375EA4} | 43501103 |  | circuit_breaker | 38.566 | -122.833 | circuit_breaker | 161 | 167 | 21130.7294 | 8832.9704 | 12297.759 | 0 | 1138.1889 |  |  |  |  | 3045 | 0 | 2956 | 0 | 0 | 0 | 3054 | 0
| 7391 | [18 empty] | {BD94B291-9C0B-4C28-8C7B-50F4F86D7051} | 183221111 | TRES PINOS 1111 | 4032 | 36.7834 | -121.3205 | TRES PINOS 11114032 | 208 | 207 | 44473.9275 | 30056.8781 | 14417.0494 | 0 | 23.7118 |  |  |  |  | 3069 | 0 | 2967 | 0 | 0 | 0 | 3037 | 0
| 8333 | [18 empty] | {D5C8CF3A-0CA8-4CD2-870D-AC7D1B010386} | 14232101 | SAN RAMON 2101 | circuit_breaker | 37.7453 | -121.9371 | SAN RAMON 2101circuit_breaker | 16 | 0 | 1579.2012 | 1579.2012 | 0 | 940.3742 | 0 |  |  |  |  | 3089 | 0 | 2946 | 0 | 0 | 0.58432 | 3065 | 0
| 7902 | [18 empty] | {C93D43A5-1B00-47F7-99CB-5288FDBDDC41} | 43061101 | COVELO 1101 | 96896 | 39.7587 | -123.2465 | COVELO 110196896 | 151 | 130 | 33620.768 | 24604.3242 | 9016.4438 | 5810.2676 | 1610.5407 |  |  |  |  | 3078 | 0 | 2943 | 0 | 0 | 3.6103 | 2953 | 0
| 9047 | [18 empty] | {0606B625-15C9-4BF7-B53E-DB310BE3421C} | 182082103 | LOS OSITOS 2103 | 7468 | 36.2933 | -121.2013 | LOS OSITOS 21037468 | 58 | 53 | 13369.2975 | 12232.8773 | 1136.4203 | 736.8159 | 39.971 |  |  |  |  | 2909 | 0 | 2895 | 0 | 0 | 0.45784 | 3033 | 0
| 9340 | [18 empty] | {D9F1E4D5-6C65-4B74-B28E-1D1E2528E5E8} | 42561102 | FULTON 1102 | 58990 | 38.5697 | -122.7741 | FULTON 110258990 | 11 | 2 | 922.121 | 901.0393 | 21.0818 | 0 | 10.4316 |  |  |  |  | 3093 | 0 | 2887 | 0 | 0 | 0 | 2930 | 0
| 9770 | [18 empty] | {7A676B71-51F1-4DF0-A596-B3D6F63218D3} | 163661701 | MIWUK 1701 | 79118 | 38.0384 | -120.2274 | MIWUK 170179118 | 4 | 0 | 31.1564 | 31.1564 | 0 | 31.1564 | 0 |  |  |  |  | 3013 | 0 | 2918 | 0 | 0 | 0.01936 | 3002 | 0
| 7668 | [18 empty] | {D7460C95-B7A0-4A1E-8E17-20B67F2A4B04} | 14232107 | SAN RAMON 2107 | MR441 | 37.7011 | -121.9382 | SAN RAMON 2107MR441 | 26 | 8 | 631.5486 | 350.4949 | 281.0537 | 40.2016 | 0 |  |  |  |  | 3091 | 0 | 2973 | 0 | 0 | 0.02498 | 2999 | 0
| 9776 | [18 empty] | {AFA2F3E5-5A6D-403E-A015-1BB8AB0D90BE} | 14232102 | SAN RAMON 2102 | circuit_breaker | 37.7452 | -121.9372 | SAN RAMON 2102circuit_breaker | 20 | 1 | 3418.4347 | 3412.1639 | 6.2707 | 2478.2008 | 0 |  |  |  |  | 3052 | 0 | 2926 | 0 | 0 | 1.5399 | 2946 | 0
| 9561 | [18 empty] | {7CF23476-92AA-47AB-A786-0FC0B6628675} | 158001101 | DOWNIEVILLE DIESEL 1101 | circuit_breaker | 39.5705 | -120.8209 | DOWNIEVILLE DIESEL 1101circuit_breaker | 3 | 0 | 36.9839 | 36.9839 | 0 | 36.9839 | 0 |  |  |  |  | 3015 | 0 | 2922 | 0 | 0 | 0.022981 | 2936 | 0
| 9803 | [18 empty] | {4F589EB1-04B1-4740-ACAC-1766B4EEFC97} | 14241101 | SUNOL 1101 | 48180 | 37.5707 | -121.864 | SUNOL 110148180 | 3 | 0 | 25.1925 | 25.1925 | 0 | 13.6404 | 0 |  |  |  |  | 2970 | 0 | 2858 | 0 | 0 | 0.0084757 | 2994 | 0
| 9275 | [18 empty] | {51DA223F-19E6-43F3-8CAF-437D80642823} | 43051101 | MONTICELLO 1101 | 1780 | 38.5061 | -122.1874 | MONTICELLO 11011780 | 12 | 0 | 105.9265 | 105.9265 | 0 | 105.9265 | 0 |  |  |  |  | 2971 | 0 | 2865 | 0 | 0 | 0.06582 | 3013 | 0
| 9837 | [18 empty] | {48D95B2E-35A7-46C9-8A55-36E5ABB60897} | 14091108 | CASTRO VALLEY 1108 | 7742 | 37.6984 | -122.024 | CASTRO VALLEY 11087742 | 1 | 0 | 4.5721 | 4.5721 | 0 | 4.5721 | 0 |  |  |  |  | 2963 | 0 | 2868 | 0 | 0 | 0.002841 | 2935 | 0
| 9578 | [18 empty] | {703579BF-EEA4-4200-951E-8470D02B6E41} | 253642101 | POSO MOUNTAIN 2101 | 1703 | 35.5588 | -118.9784 | POSO MOUNTAIN 21011703 | 9 | 1 | 3966.9789 | 3949.1387 | 17.8402 | 1455.5285 | 0 |  |  |  |  | 3003 | 0 | 2908 | 0 | 0 | 0.90442 | 3043 | 0
| 9849 | [18 empty] | {C6A91D98-B704-457B-84C0-0DADC269F3D4} | 152531102 | FLINT 1102 | circuit_breaker | 38.8851 | -121.0672 | FLINT 1102circuit_breaker | 4 | 1 | 158.0888 | 149.4178 | 8.671 | 149.4178 | 8.671 |  |  |  |  | 3075 | 0 | 2854 | 0 | 0 | 0.092844 | 2965 | 0
| 10125 | [18 empty] | {F4FF7575-EB60-4F06-920B-F33332AB37E0} | 153132104 | NARROWS 2104 | circuit_breaker | 39.2358 | -121.2689 | NARROWS 2104circuit_breaker | 1 | 0 | 4.572 | 4.572 | 0 | 4.572 | 0 |  |  |  |  | 3119 | 0 | 2884 | 0 | 0 | 0.0028409 | 2925 | 0
| 9864 | [18 empty] | {E15C2196-794C-43C4-A16E-3E3DEE607D39} | 48011144 | CALPINE 1144 | 962 | 38.7658 | -122.7076 | CALPINE 1144962 | 17 | 0 | 6465.1165 | 6465.1165 | 0 | 6465.1165 | 0 |  |  |  |  | 3101 | 0 | 2870 | 0 | 0 | 4.0172 | 2927 | 0
| 10038 | [18 empty] | {976E0AD8-A24B-4CE0-9666-90E1D38AD661} | 158031101 | ECHO SUMMIT 1101 | circuit_breaker | 38.8243 | -120.0287 | ECHO SUMMIT 1101circuit_breaker | 4 | 0 | 49.1761 | 49.1761 | 0 | 49.1761 | 0 |  |  |  |  | 3029 | 0 | 2914 | 0 | 0 | 0.030557 | 3103 | 0
| 9197 | [18 empty] | {53DC7FB8-8DF5-41D5-A637-520B18E24DEA} | 42821102 | CLOVERDALE 1102 | 47214 | 38.7759 | -123.0178 | CLOVERDALE 110247214 | 4 | 0 | 43.972 | 43.972 | 0 | 43.972 | 0 |  |  |  |  | 2973 | 0 | 2876 | 0 | 0 | 0.027323 | 3052 | 0
| 10071 | [18 empty] | {D46EEF9F-7543-4A99-84C1-44677B756920} | 48011144 | CALPINE 1144 | 276-G | 38.8057 | -122.8082 | CALPINE 1144276-G | 4 | 1 | 42.302 | 23.7478 | 18.5542 | 23.7478 | 18.5542 |  |  |  |  | 3086 | 0 | 2917 | 0 | 0 | 0.014756 | 2915 | 0
| 9904 | [18 empty] | {32E1896B-D7D5-45B0-A209-034283C3B19F} | 183041101 | BUELLTON 1101 | 63389 | 34.6242 | -120.2258 | BUELLTON 110163389 | 3 | 9 | 945.1414 | 391.5938 | 553.5476 | 0 | 58.2967 |  |  |  |  | 2943 | 0 | 2872 | 0 | 0 | 0 | 3055 | 0
| 10077 | [18 empty] | {F7C77AB2-FB1A-424C-8DCB-D1ED89130316} | 43361101 | HIGHLANDS 1101 | circuit_breaker | 38.937 | -122.6089 | HIGHLANDS 1101circuit_breaker | 1 | 0 | 42.5019 | 42.5019 | 0 | 42.5019 | 0 |  |  |  |  | 3122 | 0 | 2919 | 0 | 0 | 0.026409 | 2989 | 0
| 9906 | [18 empty] | {3DFFA8C0-A5C6-4A12-9D4C-C201315471FE} | 42631109 | PETALUMA C 1109 | 373772 | 38.1921 | -122.6663 | PETALUMA C 1109373772 | 4 | 0 | 28.6691 | 28.6691 | 0 | 28.6691 | 0 |  |  |  |  | 2954 | 0 | 2853 | 0 | 0 | 0.017814 | 2962 | 0
| 7938 | [18 empty] | {BF9A1CFA-5044-466A-9DCB-672D048DD99A} | 182611107 | PASO ROBLES 1107 | circuit_breaker | 35.6154 | -120.6796 | PASO ROBLES 1107circuit_breaker | 269 | 225 | 36815.055 | 22651.5162 | 14163.5388 | 447.6357 | 408.4884 |  |  |  |  | 3071 | 0 | 2938 | 0 | 0 | 0.27815 | 3026 | 0
| 9927 | [18 empty] | {47D06C81-6B61-4B8B-8054-D7C4BE7B9ED2} | 103611101 | WILDWOOD 1101 | circuit_breaker | 40.3876 | -123.0452 | WILDWOOD 1101circuit_breaker | 8 | 3 | 158.8908 | 96.3625 | 62.5283 | 96.3625 | 62.5283 |  |  |  |  | 2960 | 0 | 2874 | 0 | 0 | 0.059877 | 2928 | 0
| 7005 | [18 empty] | {CD142DCA-BFBC-491B-9C29-D02961854E56} | 152591101 | SUMMIT 1101 | circuit_breaker | 39.3195 | -120.379 | SUMMIT 1101circuit_breaker | 10 | 0 | 200.821 | 200.821 | 0 | 200.821 | 0 |  |  |  |  | 3082 | 0 | 2964 | 0 | 0 | 0.12478 | 3073 | 0
| 8915 | [18 empty] | {69E872AF-88D3-4B73-8E65-0B02DC82EDCF} | 182981102 | JOLON 1102 | 7068 | 35.9224 | -121.0378 | JOLON 11027068 | 15 | 9 | 6722.9971 | 6155.1451 | 567.852 | 5962.9889 | 567.852 |  |  |  |  | 2992 | 0 | 2921 | 0 | 0 | 3.7052 | 3084 | 0
| 9344 | [18 empty] | {0A01E260-13CE-4A2C-9E37-3DEB27359C08} | 152251101 | SPAULDING 1101 | circuit_breaker | 39.3255 | -120.643 | SPAULDING 1101circuit_breaker | 5 | 0 | 56.7484 | 56.7484 | 0 | 56.7484 | 0 |  |  |  |  | 2913 | 0 | 2903 | 0 | 0 | 0.035262 | 3007 | 0
| 8920 | [18 empty] | {DA007DA4-760F-4151-A582-C98D9C468550} | 14592105 | BRENTWOOD 2105 | 6512 | 37.8644 | -121.669 | BRENTWOOD 21056512 | 9 | 1 | 1062.6664 | 1047.7996 | 14.8668 | 1047.7996 | 14.8668 |  |  |  |  | 3094 | 0 | 2931 | 0 | 0 | 0.65107 | 3090 | 0
| 8959 | [18 empty] | {069FC1F9-26AE-4248-95D3-8B4718D722BC} | 152261106 | DIAMOND SPRINGS 1106 | 176130 | 38.676 | -120.7602 | DIAMOND SPRINGS 1106176130 | 3 | 0 | 32.0737 | 32.0737 | 0 | 32.0737 | 0 |  |  |  |  | 2910 | 0 | 2890 | 0 | 0 | 0.01993 | 3017 | 0
| 9963 | [18 empty] | {8AF78B6A-BE16-4226-B393-4AC8AD7FF084} | 183111102 | CMC 1102 | circuit_breaker | 35.3207 | -120.6935 | CMC 1102circuit_breaker | 9 | 0 | 590.8612 | 590.8612 | 0 | 590.8612 | 0 |  |  |  |  | 3022 | 0 | 2856 | 0 | 0 | 0.36714 | 3100 | 0
| 9347 | [18 empty] | {BCDF55E9-752A-4470-8F8D-971D8F755C6B} | 183111101 | CMC 1101 | circuit_breaker | 35.3208 | -120.6935 | CMC 1101circuit_breaker | 19 | 0 | 3293.5334 | 3293.5334 | 0 | 3293.5334 | 0 |  |  |  |  | 3067 | 0 | 2907 | 0 | 0 | 2.0465 | 2924 | 0
| 8351 | [18 empty] | {DBB65B1C-D816-44BD-B6A7-C95BB0A659FA} | 12501110 | EL CERRITO G 1110 | BR236 | 37.9037 | -122.2899 | EL CERRITO G 1110BR236 | 18 | 27 | 2097.9597 | 850.4173 | 1247.5424 | 784.0637 | 1247.5424 |  |  |  |  | 3097 | 0 | 2952 | 0 | 0 | 0.48719 | 2972 | 0
| 7742 | [18 empty] | {638663C7-6F74-4FCD-9DA8-4EADE901EF3B} | 163201101 | WEST POINT 1101 | L1969 | 38.4575 | -120.5238 | WEST POINT 1101L1969 | 28 | 57 | 4332.0274 | 1741.0416 | 2590.9858 | 1741.0416 | 2590.9858 |  |  |  |  | 2988 | 0 | 2957 | 0 | 0 | 1.0818 | 2992 | 0
| 9986 | [18 empty] | {AE8156AA-2834-43C3-BDEF-85E782B2D0C0} | 48011146 | CALPINE 1146 | 200-G | 38.8266 | -122.7997 | CALPINE 1146200-G | 2 | 0 | 13.7161 | 13.7161 | 0 | 13.7161 | 0 |  |  |  |  | 3050 | 0 | 2864 | 0 | 0 | 0.0085228 | 2950 | 0
| 9625 | [18 empty] | {BB375DE2-3623-4EA6-85D7-9C8360495B20} | 48011144 | CALPINE 1144 | 962 | 38.766 | -122.7077 | CALPINE 1144962 | 10 | 0 | 63.3636 | 63.3636 | 0 | 63.3636 | 0 |  |  |  |  | 3063 | 0 | 2867 | 0 | 0 | 0.039372 | 3005 | 0
| 9989 | [18 empty] | {02FE603A-B506-4A8C-BB2E-DD774BFD70EA} | 188071101 | SCE REFUGIO 1101 | circuit_breaker | 34.5249 | -120.0755 | SCE REFUGIO 1101circuit_breaker | 2 | 0 | 3.6129 | 3.6129 | 0 | 3.6129 | 0 |  |  |  |  | 2906 | 0 | 2880 | 0 | 0 | 0.0022449 | 1789 | 0
| 7912 | [18 empty] | {5475AE79-68EA-407F-8A77-46EA0AED966F} | 63172101 | MADISON 2101 | 1969 | 38.8287 | -122.1936 | MADISON 21011969 | 112 | 132 | 23291.7306 | 13351.3585 | 9940.3721 | 200.8341 | 260.1722 |  |  |  |  | 2975 | 0 | 2953 | 0 | 0 | 0.12479 | 2970 | 0
| 9995 | [18 empty] | {AB254D01-1DD0-4C3E-BC57-F17A23B31245} | 82931101 | POINT MORETTI 1101 | circuit_breaker | 37.0311 | -122.1872 | POINT MORETTI 1101circuit_breaker | 3 | 0 | 20.574 | 20.574 | 0 | 20.574 | 0 |  |  |  |  | 3043 | 0 | 2911 | 0 | 0 | 0.012784 | 3114 | 0
| 7970 | [18 empty] | {17D989D5-D004-4CEC-9F17-89364403A1F1} | 83392109 | SWIFT 2109 | XR300 | 37.3248 | -121.7847 | SWIFT 2109XR300 | 38 | 14 | 1867.4367 | 1305.5095 | 561.9272 | 121.3159 | 254.3964 |  |  |  |  | 2928 | 0 | 2933 | 0 | 0 | 0.075382 | 3082 | 0
| 7305 | [18 empty] | {A85BAC06-7F10-4768-B721-E152D18C46EA} | 183031101 | PALMER 1101 | M88 | 34.8325 | -120.3062 | PALMER 1101M88 | 91 | 34 | 26951.5029 | 24710.2481 | 2241.2548 | 3785.6453 | 249.2491 |  |  |  |  | 3041 | 0 | 2965 | 0 | 0 | 2.3523 | 3031 | 0
| 9646 | [18 empty] | {D1CBB1BF-D0FC-42E9-B7A6-D58BDF3942E8} | 103321101 | CEDAR CREEK 1101 | 1362 | 40.8068 | -121.9367 | CEDAR CREEK 11011362 | 5 | 0 | 24.9515 | 24.9515 | 0 | 24.9515 | 0 |  |  |  |  | 3085 | 0 | 2873 | 0 | 0 | 0.015504 | 3024 | 0
| 9648 | [18 empty] | {6B4BEF51-729A-495B-8FC4-CA82105C9822} | 182402106 | FORT ORD 2106 | 9658 | 36.6557 | -121.7468 | FORT ORD 21069658 | 4 | 1 | 245.0267 | 156.0125 | 89.0143 | 156.0125 | 89.0143 |  |  |  |  | 2996 | 0 | 2875 | 0 | 0 | 0.096942 | 2952 | 0
| 10074 | [18 empty] | {E653CB3B-BE58-4EE9-93A0-32BDBFAE5B66} | 158001101 | DOWNIEVILLE DIESEL 1101 | 1101/2 | 39.5705 | -120.8209 | DOWNIEVILLE DIESEL 11011101/2 | 1 | 0 | 15.6648 | 15.6648 | 0 | 15.6648 | 0 |  |  |  |  | 3108 | 0 | 2882 | 0 | 0 | 0.0097337 | 2903 | 0
| 10104 | [18 empty] | {9C6E3EC5-697A-453D-8DEA-C3F8B751E8D1} | 103451101 | KESWICK 1101 | circuit_breaker | 40.624 | -122.4618 | KESWICK 1101circuit_breaker | 4 | 0 | 26.6683 | 26.6683 | 0 | 26.6683 | 0 |  |  |  |  | 3034 | 0 | 2920 | 0 | 0 | 0.016571 | 2959 | 0
| 10095 | [18 empty] | {9A7F38E9-3BD6-4960-8772-7BAEF3923457} | 48011144 | CALPINE 1144 | 304 | 38.7727 | -122.7295 | CALPINE 1144304 | 3 | 0 | 74.6067 | 74.6067 | 0 | 74.6067 | 0 |  |  |  |  | 3032 | 0 | 2866 | 0 | 0 | 0.046358 | 2966 | 0
| 10114 | [18 empty] | {6FC75259-E499-428C-ADFE-2294A1B1EA1A} | 153132105 | NARROWS 2105 | 2214 | 39.2288 | -121.1011 | NARROWS 21052214 | 1 | 0 | 4.5721 | 4.5721 | 0 | 4.5721 | 0 |  |  |  |  | 3002 | 0 | 2923 | 0 | 0 | 0.0028409 | 3085 | 0
| 10123 | [18 empty] | {0C240C00-F56C-47A7-8A46-05398790480A} | 254421103 | OAKHURST 1103 | 10723 | 37.4745 | -119.6397 | OAKHURST 110310723 | 1 | 0 | 6.3415 | 6.3415 | 0 | 6.3415 | 0 |  |  |  |  | 2914 | 0 | 2925 | 0 | 0 | 0.0039404 | 2929 | 0
| 7908 | [18 empty] | {D140947F-0C1B-40AD-B2F0-4E3897A9B1FE} | 42491101 | SAUSALITO 1101 | 1270 | 37.8627 | -122.4994 | SAUSALITO 11011270 | 22 | 27 | 2501.3788 | 1585.1168 | 916.2621 | 817.322 | 0 |  |  |  |  | 3084 | 0 | 2944 | 0 | 0 | 0.50786 | 3072 | 0
| 10118 | [18 empty] | {4E90D6A9-1CF7-4F7C-96E6-CAB4F9D70FCF} | 158041101 | WASHINGTON CITY GEN. 1101 | 1101/2 | 39.364 | -120.7925 | WASHINGTON CITY GEN. 11011101/2 | 1 | 0 | 5.7117 | 5.7117 | 0 | 5.7117 | 0 |  |  |  |  | 2968 | 0 | 2924 | 0 | 0 | 0.0035491 | 3015 | 0
| 8129 | [18 empty] | {A38165FC-9A5A-4240-86F7-7CE409C40D9B} | 182391103 | OILFIELDS 1103 | N40 | 35.7565 | -120.8803 | OILFIELDS 1103N40 | 16 | 2 | 1242.0904 | 1192.0163 | 50.0741 | 1192.0163 | 50.0741 |  |  |  |  | 3039 | 0 | 2936 | 0 | 0 | 0.74068 | 3083 | 0
| 7848 | [18 empty] | {58E1DDBF-27C2-479B-8E69-60E9501D29C8} | 43201102 | STAFFORD 1102 | 361952 | 38.123 | -122.6267 | STAFFORD 1102361952 | 12 | 8 | 2521.9404 | 2196.587 | 325.3535 | 2196.587 | 325.3535 |  |  |  |  | 2980 | 0 | 2950 | 0 | 0 | 1.3649 | 2938 | 0
| 9594 | [18 empty] | {EF5D8957-32CC-44F0-808E-217DC0A13E35} | 102911110 | WYANDOTTE 1110 | 2590 | 39.5285 | -121.4611 | WYANDOTTE 11102590 | 22 | 6 | 993.4184 | 928.8641 | 64.5543 | 0 | 13.967 |  |  |  |  | 3112 | 0 | 2855 | 0 | 0 | 0 | 2912 | 0
| 9588 | [18 empty] | {C4A51841-0308-49DA-9C27-2509F9C64A2D} | 153081109 | PLACERVILLE 1109 | circuit_breaker | 38.731 | -120.7832 | PLACERVILLE 1109circuit_breaker | 6 | 1 | 48.2214 | 35.0819 | 13.1395 | 25.9925 | 0 |  |  |  |  | 3074 | 0 | 2888 | 0 | 0 | 0.016151 | 2908 | 0
| 10152 | [18 empty] | {096C1652-B7E1-4420-B7F5-3A29C5C5F06A} | 83622105 | CAMP EVERS 2105 | BL 2101 | 37.0926 | -122.0964 | CAMP EVERS 2105BL 2101 | 1 | 0 | 5.191 | 5.191 | 0 | 5.191 | 0 |  |  |  |  | 2911 | 0 | 2927 | 0 | 0 | 0.0032255 | 2909 | 0
| 7590 | [18 empty] | {FE2E59EB-BA50-4D05-88C6-174D3F07D4AE} | 43091101 | GREENBRAE 1101 | 82270 | 37.9369 | -122.5189 | GREENBRAE 110182270 | 47 | 89 | 5091.0228 | 1202.9792 | 3888.0436 | 4.572 | 0 |  |  |  |  | 3125 | 0 | 2974 | 0 | 0 | 0.0028409 | 3021 | 0
| 9439 | [18 empty] | {541E3522-13C9-4D47-8A88-53338B650ABF} | 14662112 | TASSAJARA 2112 | 3202 | 37.8758 | -121.9208 | TASSAJARA 21123202 | 15 | 1 | 649.7166 | 628.2778 | 21.4389 | 628.2778 | 21.4389 |  |  |  |  | 2974 | 0 | 2930 | 0 | 0 | 0.39039 | 3079 | 0
| 8654 | [18 empty] | {1BEA114F-1545-4690-B5EF-CA295187FA4B} | 252721106 | KERN OIL 1106 | 46960 | 35.4771 | -118.887 | KERN OIL 110646960 | 28 | 7 | 3294.4003 | 3100.4181 | 193.9822 | 1285.0343 | 0 |  |  |  |  | 2932 | 0 | 2948 | 0 | 0 | 0.79848 | 3028 | 0
| 5737 | [18 empty] | {A920E716-9436-4401-AAF8-C3A905DCBD43} | 24141102 | RALSTON 1102 | circuit_breaker | 37.5114 | -122.3402 | RALSTON 1102circuit_breaker | 133 | 266 | 19258.2474 | 6824.2186 | 12434.0288 | 1520.1281 | 123.7877 |  |  |  |  | 3042 | 0 | 2999 | 0 | 0 | 0.94456 | 3016 | 0
| 5746 | [18 empty] | {B05D8AC6-2B7C-4E68-B328-BD625ED75426} | 14662104 | TASSAJARA 2104 | circuit_breaker | 37.7998 | -121.9082 | TASSAJARA 2104circuit_breaker | 53 | 20 | 2596.7562 | 1951.9546 | 644.8017 | 118.3029 | 106.6047 |  |  |  |  | 3053 | 0 | 2989 | 0 | 0 | 0.07351 | 3105 | 0
| 5900 | [18 empty] | {6DD2F111-0B5B-42BB-AFF2-1BE891878CB0} | 182391103 | OILFIELDS 1103 | N64 | 35.8135 | -120.8465 | OILFIELDS 1103N64 | 133 | 74 | 23386.1198 | 20163.8274 | 3222.2924 | 16233.6548 | 3010.5027 |  |  |  |  | 3000 | 0 | 2996 | 0 | 0 | 10.0871 | 2934 | 0
| 6335 | [18 empty] | {4709726B-1243-485D-89BF-CB13962C950E} | 83192101 | GREEN VALLEY 2101 | 12824 | 36.9284 | -121.7063 | GREEN VALLEY 210112824 | 150 | 146 | 32567.5049 | 19537.6008 | 13029.9041 | 107.6616 | 71.3588 |  |  |  |  | 2959 | 0 | 2985 | 0 | 0 | 0.066898 | 2913 | 0
| 6911 | [18 empty] | {CDC6585C-22C0-4542-A949-CDEE5502EA22} | 182391103 | OILFIELDS 1103 | N42 | 35.8683 | -120.843 | OILFIELDS 1103N42 | 38 | 16 | 10747.6361 | 9813.7199 | 933.9162 | 4452.4168 | 573.2629 |  |  |  |  | 3083 | 0 | 2975 | 0 | 0 | 2.7666 | 3121 | 0
| 6363 | [18 empty] | {C84D6789-7EC5-4B63-96CB-78D964DC0C39} | 14232117 | SAN RAMON 2117 | circuit_breaker | 37.7454 | -121.9367 | SAN RAMON 2117circuit_breaker | 34 | 8 | 3014.7035 | 2698.3212 | 316.3823 | 735.1259 | 0 |  |  |  |  | 3077 | 0 | 2984 | 0 | 0 | 0.45679 | 3049 | 0
| 5861 | [18 empty] | {ADA0B946-8139-4D75-A3D4-894703D1FC57} | 192381102 | EEL RIVER 1102 | 49130 | 40.567 | -124.2044 | EEL RIVER 110249130 | 147 | 161 | 37286.3651 | 22331.5765 | 14954.7885 | 2552.3517 | 2330.8835 |  |  |  |  | 3048 | 0 | 2995 | 0 | 0 | 1.586 | 3081 | 0
| 5219 | [18 empty] | {4A8E733F-DFA6-45E2-8263-D2D979FF3043} | 43211101 | HARTLEY 1101 | 471 | 39.064 | -122.9175 | HARTLEY 1101471 | 29 | 136 | 8707.4992 | 2001.813 | 6705.6863 | 134.4299 | 283.6051 |  |  |  |  | 2966 | 0 | 3008 | 0 | 0 | 0.083531 | 2919 | 0
| 4873 | [18 empty] | {DDFFEADB-3F2B-4296-80F5-9B1536EA3D55} | 13921104 | FRANKLIN 1104 | circuit_breaker | 38.0119 | -122.264 | FRANKLIN 1104circuit_breaker | 135 | 746 | 40811.0737 | 8418.0901 | 32392.9836 | 233.9749 | 17.7499 |  |  |  |  | 3099 | 0 | 3014 | 0 | 0 | 0.14539 | 2956 | 0
| 6212 | [18 empty] | {B779C83B-3DC2-4512-9F97-360CB13A0909} | 43201102 | STAFFORD 1102 | 1048 | 38.0957 | -122.6021 | STAFFORD 11021048 | 131 | 205 | 20603.7935 | 8433.9926 | 12169.8009 | 8411.3678 | 11913.9981 |  |  |  |  | 3059 | 0 | 2982 | 0 | 0 | 5.2266 | 3113 | 0
| 5196 | [18 empty] | {E1A9F699-2041-4569-A9A7-03860994D8BC} | 14662109 | TASSAJARA 2109 | circuit_breaker | 37.7998 | -121.9077 | TASSAJARA 2109circuit_breaker | 13 | 0 | 3123.8712 | 3123.8712 | 0 | 1458.9789 | 0 |  |  |  |  | 3103 | 0 | 3010 | 0 | 0 | 0.90657 | 3012 | 0
| 5126 | [18 empty] | {6CF6A77C-B318-465C-B9DC-4D6CDBB1BB50} | 162821702 | STANISLAUS 1702 | L611 | 38.2447 | -120.3642 | STANISLAUS 1702L611 | 85 | 206 | 12448.6791 | 4813.9395 | 7634.7396 | 4813.9395 | 7634.7396 |  |  |  |  | 2998 | 0 | 3012 | 0 | 0 | 2.9912 | 2931 | 0
| 5152 | [18 empty] | {E2ABC82B-4DDD-4ED2-A54A-858526BC35DF} | 252841102 | OROSI 1102 | 7948F | 36.5441 | -119.1967 | OROSI 11027948F | 101 | 115 | 19030.7142 | 13674.0277 | 5356.6865 | 423.4544 | 55.676 |  |  |  |  | 3105 | 0 | 3004 | 0 | 0 | 0.26312 | 3118 | 0
| 6633 | [18 empty] | {97C1B34A-95F8-4CCE-8DCC-4962D06B743A} | 253911102 | LAMONT 1102 | 4222 | 35.3258 | -118.804 | LAMONT 11024222 | 110 | 91 | 28335.7841 | 26105.5713 | 2230.2128 | 805.2366 | 73.5491 |  |  |  |  | 3031 | 0 | 2981 | 0 | 0 | 0.50035 | 3124 | 0
| 6717 | [18 empty] | {783F2A5E-A6A8-4886-A311-AC927B267C5C} | 24101103 | HALF MOON BAY 1103 | 76762 | 37.4582 | -122.4293 | HALF MOON BAY 110376762 | 19 | 72 | 4025.1369 | 817.0088 | 3208.1281 | 0 | 203.7106 |  |  |  |  | 3009 | 0 | 2977 | 0 | 0 | 0 | 3122 | 0
| 4674 | [18 empty] | {EF774119-F7FE-47E7-8D97-134D999F3AC9} | 24141102 | RALSTON 1102 | 9126 | 37.5116 | -122.3183 | RALSTON 11029126 | 62 | 199 | 12378.7763 | 2944.7848 | 9433.9915 | 1709.1714 | 8246.1454 |  |  |  |  | 3113 | 0 | 3003 | 0 | 0 | 1.062 | 3030 | 0
| 5482 | [18 empty] | {6C67D310-8D73-415C-9BAA-A6CC964A8DDA} | 183011102 | MORRO BAY 1102 | V80 | 35.312 | -120.8504 | MORRO BAY 1102V80 | 55 | 199 | 10555.6494 | 3197.8948 | 7357.7546 | 18.5609 | 0 |  |  |  |  | 2997 | 0 | 2992 | 0 | 0 | 0.011533 | 2977 | 0
| 5309 | [18 empty] | {35D3CEF8-0523-4ECA-BC11-26CD68907349} | 182852204 | VIEJO 2204 | 9440 | 36.6036 | -121.9095 | VIEJO 22049440 | 155 | 164 | 11698.5629 | 5512.2097 | 6186.3533 | 10.1911 | 0 |  |  |  |  | 2946 | 0 | 2994 | 0 | 0 | 0.0063324 | 3045 | 0
| 5253 | [18 empty] | {AF6D64E0-EB57-4A91-A132-4FA867794848} | 63171105 | MADISON 1105 | 7712 | 38.6616 | -121.9708 | MADISON 11057712 | 251 | 234 | 59106.0922 | 48161.6451 | 10944.4471 | 630.6114 | 93.7954 |  |  |  |  | 3051 | 0 | 3002 | 0 | 0 | 0.39184 | 3018 | 0
| 6226 | [18 empty] | {5DD49BEE-09C2-4674-9D89-3A76B7F55110} | 43381101 | POINT ARENA 1101 | 3702 | 38.9099 | -123.6865 | POINT ARENA 11013702 | 49 | 9 | 8658.7698 | 7962.9538 | 695.8161 | 7868.7714 | 695.8161 |  |  |  |  | 2984 | 0 | 2978 | 0 | 0 | 4.8894 | 3078 | 0
| 4593 | [18 empty] | {0DB6DB9D-7804-4D10-B639-1A5CA91DDA98} | 162671103 | WESTLEY 1103 | 9010 | 37.5385 | -121.2044 | WESTLEY 11039010 | 226 | 171 | 62578.6124 | 55369.2735 | 7209.3389 | 1485.982 | 10.0171 |  |  |  |  | 2917 | 0 | 3005 | 0 | 0 | 0.92335 | 3093 | 0
| 6387 | [18 empty] | {F3C9E330-5EFE-42AE-9971-7797E81AA91A} | 83432103 | HICKS 2103 | XR248 | 37.2105 | -121.8595 | HICKS 2103XR248 | 58 | 199 | 10837.0217 | 2561.3965 | 8275.6253 | 124.695 | 69.8835 |  |  |  |  | 3117 | 0 | 2979 | 0 | 0 | 0.077482 | 2902 | 0
| 6444 | [18 empty] | {90FE2AC1-F695-42FF-8EBC-FB82E3B206C0} | 163011102 | MARTELL 1102 | 92172 | 38.3635 | -120.776 | MARTELL 110292172 | 136 | 345 | 16850.5974 | 5297.1108 | 11553.4866 | 186.9738 | 544.2233 |  |  |  |  | 3025 | 0 | 2980 | 0 | 0 | 0.11618 | 3091 | 0
| 4723 | [18 empty] | {EE561184-1754-434F-A274-A2561C8ED6F1} | 182601105 | OCEANO 1105 | V48 | 35.1385 | -120.6405 | OCEANO 1105V48 | 128 | 475 | 18556.7342 | 4102.8714 | 14453.8627 | 142.1722 | 1717.9404 |  |  |  |  | 3110 | 0 | 3007 | 0 | 0 | 0.088342 | 3038 | 0
| 4784 | [18 empty] | {FB91D5A1-93AF-44B1-AF92-030805414888} | 12660404 | BERKELEY T 0404 | circuit_breaker | 37.8645 | -122.2589 | BERKELEY T 0404circuit_breaker | 42 | 302 | 11717.182 | 1941.7529 | 9775.429 | 6.096 | 390.4782 |  |  |  |  | 3124 | 0 | 3011 | 0 | 0 | 0.0037879 | 3047 | 0
| 5400 | [18 empty] | {D5040DDA-C582-40B5-8A53-2E3901DC0B08} | 42301101 | TULUCAY 1101 | circuit_breaker | 38.2476 | -122.2681 | TULUCAY 1101circuit_breaker | 173 | 61 | 15830.2833 | 11604.5805 | 4225.7027 | 121.1978 | 0 |  |  |  |  | 3088 | 0 | 2987 | 0 | 0 | 0.075309 | 3095 | 0
| 4721 | [18 empty] | {B0A59559-066B-42EC-B669-9E26912EE6C4} | 14101102 | ALHAMBRA 1102 | 13333 | 38.0052 | -122.1313 | ALHAMBRA 110213333 | 17 | 61 | 2540.0197 | 480.3389 | 2059.6808 | 130.2273 | 995.4918 |  |  |  |  | 3054 | 0 | 3006 | 0 | 0 | 0.080919 | 3053 | 0
| 4573 | [18 empty] | {A7EF07D3-EBF2-4720-9617-7A61F7C99687} | 182852202 | VIEJO 2202 | 55787 | 36.601 | -121.9385 | VIEJO 220255787 | 3 | 24 | 1873.3596 | 58.9251 | 1814.4346 | 58.9251 | 1814.4346 |  |  |  |  | 3040 | 0 | 3000 | 0 | 0 | 0.036614 | 3077 | 0
| 6003 | [18 empty] | {13E2F68D-5FE0-429F-8E83-F4D9D6BCB638} | 42761102 | FORT BRAGG A 1102 | 33064 | 39.4128 | -123.8091 | FORT BRAGG A 110233064 | 102 | 145 | 12660.8662 | 5911.1864 | 6749.6798 | 0 | 44.7837 |  |  |  |  | 2924 | 0 | 2986 | 0 | 0 | 0 | 3109 | 0
| 5756 | [18 empty] | {7DB3B65A-9BC0-48E9-AEAF-56397C577A2D} | 42011107 | SAN RAFAEL 1107 | 434 | 37.9456 | -122.5439 | SAN RAFAEL 1107434 | 37 | 178 | 10138.9001 | 1839.9407 | 8298.9594 | 4.572 | 0 |  |  |  |  | 3016 | 0 | 2997 | 0 | 0 | 0.0028409 | 3106 | 0
| 5688 | [18 empty] | {D9A411F6-BF17-411A-B6B6-EDBF1A747192} | 12350401 | ORINDA 0401 | circuit_breaker | 37.8837 | -122.1934 | ORINDA 0401circuit_breaker | 14 | 0 | 238.0325 | 238.0325 | 0 | 160.4005 | 0 |  |  |  |  | 3092 | 0 | 2991 | 0 | 0 | 0.099668 | 3062 | 0
| 5100 | [18 empty] | {385A8486-C3EA-4FD6-BFA5-2F73ECF426BB} | 103491101 | MC ARTHUR 1101 | 37344 | 41.1203 | -121.1465 | MC ARTHUR 110137344 | 152 | 256 | 19422.5884 | 14267.9902 | 5154.5982 | 181.3406 | 6.0961 |  |  |  |  | 2950 | 0 | 3013 | 0 | 0 | 0.11268 | 3010 | 0
| 5604 | [18 empty] | {DA50CC20-DF93-4A26-9942-3A43E97DCAC4} | 252941107 | TIVY VALLEY 1107 | 37522 | 36.7856 | -119.3991 | TIVY VALLEY 110737522 | 56 | 101 | 10677.1741 | 4999.5623 | 5677.6118 | 731.9163 | 619.2504 |  |  |  |  | 3096 | 0 | 2988 | 0 | 0 | 0.45479 | 3004 | 0
| 5908 | [18 empty] | {CBC2E590-65E4-4DD8-9118-7B6CB910201C} | 82952113 | EDENVALE 2113 | circuit_breaker | 37.2443 | -121.7953 | EDENVALE 2113circuit_breaker | 50 | 334 | 15209.4564 | 2357.516 | 12851.9404 | 24.568 | 0 |  |  |  |  | 3081 | 0 | 2993 | 0 | 0 | 0.015266 | 3019 | 0
| 5528 | [18 empty] | {F1466976-3470-44F4-BFAC-1A77DCF2CCD2} | 83392107 | SWIFT 2107 | XR526 | 37.3134 | -121.7591 | SWIFT 2107XR526 | 91 | 68 | 12804.5607 | 8725.9112 | 4078.6495 | 3165.9502 | 1629.0055 |  |  |  |  | 3114 | 0 | 2998 | 0 | 0 | 1.9672 | 2944 | 0
| 5514 | [18 empty] | {5E127255-F44E-4E7F-9860-A35F96AE573A} | 42631108 | PETALUMA C 1108 | 628 | 38.2416 | -122.679 | PETALUMA C 1108628 | 208 | 314 | 46119.7279 | 18094.7665 | 28024.9614 | 14935.6028 | 22983.3503 |  |  |  |  | 2985 | 0 | 2990 | 0 | 0 | 9.2806 | 2943 | 0
| 6474 | [18 empty] | {F8B3D30D-8DD1-4628-A46B-E961D4F39DD6} | 183011101 | MORRO BAY 1101 | W04 | 35.3613 | -120.8365 | MORRO BAY 1101W04 | 68 | 513 | 24843.0563 | 3936.0015 | 20907.0547 | 0 | 56.064 |  |  |  |  | 3123 | 0 | 2976 | 0 | 0 | 0 | 2945 | 0
| 5181 | [18 empty] | {12F1A144-2063-4E28-8860-F6ADF2052849} | 182631104 | SAN LUIS OBISPO 1104 | circuit_breaker | 35.2613 | -120.6347 | SAN LUIS OBISPO 1104circuit_breaker | 105 | 42 | 14433.1824 | 11106.7457 | 3326.4367 | 889.5466 | 1045.735 |  |  |  |  | 2921 | 0 | 3001 | 0 | 0 | 0.55274 | 2990 | 0
| 6367 | [18 empty] | {859884CA-A48F-42EF-9FB7-61037D5ACB81} | 162821702 | STANISLAUS 1702 | L5381 | 38.2518 | -120.3509 | STANISLAUS 1702L5381 | 30 | 80 | 5939.6065 | 1946.774 | 3992.8324 | 1946.774 | 3992.8324 |  |  |  |  | 3018 | 0 | 2983 | 0 | 0 | 1.2097 | 2964 | 0
| 4622 | [18 empty] | {71ACD594-F55A-4D07-9FE3-9B0665AF5F6F} | 42011106 | SAN RAFAEL 1106 | 68694 | 37.9813 | -122.5223 | SAN RAFAEL 110668694 | 76 | 391 | 20324.4449 | 4050.2895 | 16274.1553 | 0 | 464.6198 |  |  |  |  | 3005 | 0 | 3009 | 0 | 0 | 0 | 3070 | 0
| 2596 | [18 empty] | {942A1F20-74CB-4B0F-A8B8-16F691C971BA} | 22721106 | SNEATH LANE 1106 | 1339 | 37.6321 | -122.4376 | SNEATH LANE 11061339 | 108 | 1025 | 51891.3443 | 8419.6559 | 43471.6884 | 0 | 69.4806 |  |  |  |  | 3026 | 0 | 3043 | 0 | 0 | 0 | 2926 | 0
| 2444 | [18 empty] | {BC94208A-FBF0-4021-BC48-64B29D924399} | 192381102 | EEL RIVER 1102 | 530 | 40.5987 | -124.2119 | EEL RIVER 1102530 | 395 | 453 | 81060.5731 | 51915.2562 | 29145.3169 | 8758.0357 | 3592.4404 |  |  |  |  | 3065 | 0 | 3045 | 0 | 0 | 5.442 | 2997 | 0
| 3390 | [18 empty] | {28C87B96-17F1-4B77-AC44-88E083C74B6C} | 182391103 | OILFIELDS 1103 | 7006 | 35.8684 | -120.8478 | OILFIELDS 11037006 | 98 | 64 | 27975.3683 | 24239.8026 | 3735.5657 | 5321.5914 | 1650.5739 |  |  |  |  | 2941 | 0 | 3028 | 0 | 0 | 3.3067 | 2948 | 0
| 2676 | [18 empty] | {87C2089E-844B-4CDB-8CA8-FEE8A9986F8E} | 182631101 | SAN LUIS OBISPO 1101 | 592368 | 35.2894 | -120.653 | SAN LUIS OBISPO 1101592368 | 179 | 785 | 38694.6404 | 7364.7529 | 31329.8875 | 0 | 71.4032 |  |  |  |  | 3019 | 0 | 3044 | 0 | 0 | 0 | 2911 | 0
| 3048 | [18 empty] | {F61A533E-D44D-4AFC-AE85-9F4FD0A8F945} | 14452104 | KIRKER 2104 | circuit_breaker | 38.0206 | -121.9058 | KIRKER 2104circuit_breaker | 303 | 1998 | 99296.6605 | 16836.6678 | 82459.9927 | 74.5132 | 0 |  |  |  |  | 3121 | 0 | 3030 | 0 | 0 | 0.0463 | 3066 | 0
| 4130 | [18 empty] | {9E74C19B-FD10-4380-8F7F-0DF0A358D1AB} | 42721104 | SONOMA 1104 | 914376 | 38.2883 | -122.4935 | SONOMA 1104914376 | 171 | 407 | 33114.2235 | 11215.1853 | 21899.0382 | 702.83 | 920.5507 |  |  |  |  | 3036 | 0 | 3024 | 0 | 0 | 0.43672 | 2998 | 0
| 3647 | [18 empty] | {8DC14E6C-EC17-4B68-AA1F-34B2D141CBFE} | 83371103 | SARATOGA 1103 | LC82 | 37.2777 | -122.0259 | SARATOGA 1103LC82 | 91 | 165 | 10573.483 | 3440.1789 | 7133.3041 | 4.8945 | 0 |  |  |  |  | 3024 | 0 | 3031 | 0 | 0 | 0.0030413 | 2920 | 0
| 3019 | [18 empty] | {A0069F30-9735-482E-85CC-36443E960AEF} | 83371103 | SARATOGA 1103 | LC40 | 37.268 | -122.0318 | SARATOGA 1103LC40 | 79 | 217 | 12245.6549 | 3059.9258 | 9185.7291 | 438.1448 | 1838.312 |  |  |  |  | 3037 | 0 | 3036 | 0 | 0 | 0.27225 | 3051 | 0
| 4309 | [18 empty] | {162FBB52-745E-4C32-9FDD-D8D884FE49AC} | 42721105 | SONOMA 1105 | 138 | 38.2726 | -122.4372 | SONOMA 1105138 | 339 | 469 | 58579.8128 | 27343.3572 | 31236.4556 | 615.5192 | 13.3928 |  |  |  |  | 2927 | 0 | 3022 | 0 | 0 | 0.38247 | 3126 | 0
| 2720 | [18 empty] | {0CEB70F5-2209-4B8B-BEA6-B7EBAFD3DEEB} | 182581108 | GOLDTREE 1108 | circuit_breaker | 35.3197 | -120.6931 | GOLDTREE 1108circuit_breaker | 115 | 344 | 20741.2203 | 7797.4445 | 12943.7759 | 3288.9555 | 1282.139 |  |  |  |  | 2916 | 0 | 3050 | 0 | 0 | 2.0437 | 2987 | 0
| 2831 | [18 empty] | {1FEB7E65-DDE1-46AE-83AD-B5F30417F926} | 13912108 | WILLOW PASS 2108 | circuit_breaker | 38.0247 | -121.9612 | WILLOW PASS 2108circuit_breaker | 168 | 89 | 18732.8786 | 14603.4136 | 4129.4649 | 235.7533 | 23.4608 |  |  |  |  | 2937 | 0 | 3048 | 0 | 0 | 0.14649 | 2975 | 0
| 3104 | [18 empty] | {B92734B7-4E4E-459E-8B98-E0A159EA0D8F} | 42271103 | COTATI 1103 | 252 | 38.2435 | -122.9424 | COTATI 1103252 | 96 | 251 | 17845.1423 | 9654.7077 | 8190.4347 | 0 | 12.0706 |  |  |  |  | 3062 | 0 | 3026 | 0 | 0 | 0 | 2917 | 0
| 2715 | [18 empty] | {D661A4C9-F1EC-4DA6-BD47-BB819E0F490C} | 14341105 | VALLEY VIEW 1105 | P124 | 37.9843 | -122.2972 | VALLEY VIEW 1105P124 | 108 | 551 | 30853.9659 | 5089.5347 | 25764.4312 | 0 | 159.6174 |  |  |  |  | 3090 | 0 | 3040 | 0 | 0 | 0 | 3036 | 0
| 3577 | [18 empty] | {BC48BC1B-FF6D-435C-9294-117A7961E04E} | 252721106 | KERN OIL 1106 | 3301 | 35.4424 | -118.9595 | KERN OIL 11063301 | 288 | 191 | 64287.2569 | 52237.9858 | 12049.2711 | 657.9886 | 461.2505 |  |  |  |  | 3064 | 0 | 3039 | 0 | 0 | 0.40886 | 3088 | 0
| 4467 | [18 empty] | {53C5BA88-884F-48FE-B87C-D7D9589897A5} | 253642101 | POSO MOUNTAIN 2101 | circuit_breaker | 35.5596 | -118.9574 | POSO MOUNTAIN 2101circuit_breaker | 45 | 4 | 7014.8715 | 6924.1001 | 90.7715 | 6924.1001 | 90.7715 |  |  |  |  | 2972 | 0 | 3018 | 0 | 0 | 4.3024 | 3003 | 0
| 2590 | [18 empty] | {4F05ED84-FE56-4A90-8DC4-86D939A68626} | 103491101 | MC ARTHUR 1101 | 53120 | 41.0559 | -121.3891 | MC ARTHUR 110153120 | 138 | 142 | 19148.4493 | 12732.032 | 6416.4173 | 0 | 20.9563 |  |  |  |  | 2969 | 0 | 3046 | 0 | 0 | 0 | 3069 | 0
| 3225 | [18 empty] | {18E8D8F7-45B7-41EF-BCF8-35FF7259EC09} | 43051101 | MONTICELLO 1101 | 1589 | 38.4069 | -122.2057 | MONTICELLO 11011589 | 95 | 205 | 15749.4751 | 6934.0024 | 8815.4726 | 6934.0024 | 8815.4726 |  |  |  |  | 2930 | 0 | 3037 | 0 | 0 | 4.3086 | 3102 | 0
| 4117 | [18 empty] | {6D5B17B5-960C-48B4-806D-BF9DA1A8A3B0} | 182331101 | GABILAN 1101 | 3722 | 36.6969 | -121.5729 | GABILAN 11013722 | 207 | 170 | 48849.5858 | 30859.7242 | 17989.8617 | 1147.7092 | 33.1264 |  |  |  |  | 2999 | 0 | 3020 | 0 | 0 | 0.71315 | 3050 | 0
| 4154 | [18 empty] | {B83D09DE-3D47-4840-BFDB-F992D85178B8} | 152481103 | BRUNSWICK 1103 | 78862 | 39.2548 | -121.0242 | BRUNSWICK 110378862 | 68 | 188 | 9183.6261 | 2157.7055 | 7025.9206 | 423.5836 | 1237.6004 |  |  |  |  | 3060 | 0 | 3021 | 0 | 0 | 0.2632 | 3123 | 0
| 3874 | [18 empty] | {E273F09C-00C1-48A4-A71E-352A62A15E75} | 182082103 | LOS OSITOS 2103 | 7082 | 36.2872 | -121.2483 | LOS OSITOS 21037082 | 182 | 190 | 45136.8617 | 33004.0765 | 12132.7852 | 1889.198 | 804.2179 |  |  |  |  | 3104 | 0 | 3015 | 0 | 0 | 1.1739 | 2939 | 0
| 3835 | [18 empty] | {42F8D929-F3A9-49A8-94C4-A1A9328D939B} | 42631109 | PETALUMA C 1109 | circuit_breaker | 38.239 | -122.637 | PETALUMA C 1109circuit_breaker | 208 | 753 | 37747.8235 | 7864.725 | 29883.0985 | 1526.3367 | 2883.912 |  |  |  |  | 2956 | 0 | 3016 | 0 | 0 | 0.94842 | 2907 | 0
| 2626 | [18 empty] | {3B5DCBB5-D826-4D6E-9F84-E8F9FA887643} | 43091103 | GREENBRAE 1103 | 7315 | 37.9337 | -122.5211 | GREENBRAE 11037315 | 74 | 466 | 24227.976 | 3607.614 | 20620.362 | 0 | 973.3956 |  |  |  |  | 2953 | 0 | 3042 | 0 | 0 | 0 | 3029 | 0
| 4373 | [18 empty] | {49931849-9CA4-43E6-B559-5E2CB6D2E2B4} | 182852201 | VIEJO 2201 | 9704 | 36.5672 | -121.9276 | VIEJO 22019704 | 88 | 489 | 19850.7669 | 4088.1892 | 15762.5778 | 786.5986 | 577.297 |  |  |  |  | 2965 | 0 | 3019 | 0 | 0 | 0.48877 | 2971 | 0
| 2673 | [18 empty] | {0490EF9F-4327-4CEC-AB8A-ADCAD043B99F} | 182981102 | JOLON 1102 | 7002 | 35.9664 | -121.1153 | JOLON 11027002 | 137 | 86 | 37851.8765 | 29669.8562 | 8182.0203 | 11843.464 | 4859.081 |  |  |  |  | 2908 | 0 | 3041 | 0 | 0 | 7.3592 | 3035 | 0
| 3245 | [18 empty] | {133545C9-FF59-4E89-AB9A-6D025A3D74E4} | 83182101 | LLAGAS 2101 | XR244 | 37.0163 | -121.5446 | LLAGAS 2101XR244 | 257 | 301 | 41416.8482 | 22757.8317 | 18659.0165 | 321.7387 | 411.7455 |  |  |  |  | 2922 | 0 | 3035 | 0 | 0 | 0.19992 | 3076 | 0
| 3532 | [18 empty] | {6F3DC4C6-B30E-4E87-89BD-977051E850B3} | 83192101 | GREEN VALLEY 2101 | 90860 | 36.9705 | -121.739 | GREEN VALLEY 210190860 | 313 | 356 | 51825.4434 | 29488.5794 | 22336.8639 | 5419.4084 | 2273.791 |  |  |  |  | 3001 | 0 | 3033 | 0 | 0 | 3.3675 | 2906 | 0
| 2578 | [18 empty] | {234C0F85-450D-4068-9BF4-08179DE2304E} | 253801101 | ARVIN 1101 | 94892 | 35.1509 | -118.8289 | ARVIN 110194892 | 92 | 45 | 19514.2472 | 15531.7609 | 3982.4863 | 345.9853 | 18.1965 |  |  |  |  | 2939 | 0 | 3049 | 0 | 0 | 0.21499 | 2910 | 0
| 3553 | [18 empty] | {C0699A77-D9F1-4326-8400-EC5E43167E10} | 24251104 | WOODSIDE 1104 | circuit_breaker | 37.437 | -122.2422 | WOODSIDE 1104circuit_breaker | 244 | 442 | 30346.3041 | 11969.1918 | 18377.1123 | 246.681 | 27.3235 |  |  |  |  | 3072 | 0 | 3029 | 0 | 0 | 0.15328 | 2947 | 0
| 3767 | [18 empty] | {7A360B24-DB74-4302-B7FF-A7991F9BEB20} | 102931103 | COTTONWOOD 1103 | circuit_breaker | 40.3969 | -122.2675 | COTTONWOOD 1103circuit_breaker | 214 | 264 | 31541.878 | 18019.9627 | 13521.9153 | 1201.9482 | 24.944 |  |  |  |  | 3012 | 0 | 3025 | 0 | 0 | 0.74686 | 2914 | 0
| 4316 | [18 empty] | {0CC5B62D-8E39-47F2-A113-AB2F434531F0} | 14232119 | SAN RAMON 2119 | circuit_breaker | 37.7453 | -121.9369 | SAN RAMON 2119circuit_breaker | 40 | 40 | 4213.6288 | 2436.9887 | 1776.6401 | 757.1628 | 26.2859 |  |  |  |  | 2915 | 0 | 3017 | 0 | 0 | 0.47048 | 2918 | 0
| 3286 | [18 empty] | {741F819D-F84A-48D0-B917-155D72B8DC6A} | 42761104 | FORT BRAGG A 1104 | 36526 | 39.4376 | -123.798 | FORT BRAGG A 110436526 | 223 | 1393 | 62262.0909 | 10589.3182 | 51672.7727 | 19.7226 | 59.2194 |  |  |  |  | 3006 | 0 | 3034 | 0 | 0 | 0.012255 | 3080 | 0
| 3602 | [18 empty] | {DA43FDAA-0AFD-4DA3-9BAB-E9F0ED9A89B4} | 42991107 | LAS GALLINAS A 1107 | 554 | 37.9977 | -122.5383 | LAS GALLINAS A 1107554 | 91 | 444 | 26520.0687 | 4418.1736 | 22101.8951 | 200.8758 | 42.546 |  |  |  |  | 3095 | 0 | 3032 | 0 | 0 | 0.12482 | 2922 | 0
| 3576 | [18 empty] | {35F57AD2-0209-4C33-8C6F-331DBFF4518F} | 42721107 | SONOMA 1107 | 294 | 38.2349 | -122.4611 | SONOMA 1107294 | 105 | 86 | 25498.5274 | 14846.705 | 10651.8224 | 321.4105 | 171.0259 |  |  |  |  | 2947 | 0 | 3038 | 0 | 0 | 0.19972 | 2904 | 0
| 3036 | [18 empty] | {707F90B6-29D2-416E-88CB-4A65D150CEBD} | 42631108 | PETALUMA C 1108 | 630 | 38.2354 | -122.6707 | PETALUMA C 1108630 | 97 | 169 | 18763.4639 | 6902.9174 | 11860.5464 | 2581.7965 | 3527.1162 |  |  |  |  | 3004 | 0 | 3027 | 0 | 0 | 1.6043 | 2996 | 0
| 4206 | [18 empty] | {AE598DAD-86E1-4B86-97A5-38FEA17FEC39} | 102911109 | WYANDOTTE 1109 | 5973 | 39.4598 | -121.5494 | WYANDOTTE 11095973 | 63 | 177 | 16863.5364 | 3972.7876 | 12890.7488 | 0 | 76.4235 |  |  |  |  | 3049 | 0 | 3023 | 0 | 0 | 0 | 3040 | 0
| 2554 | [18 empty] | {C1FA1EBC-6C51-4F6D-A326-E003BD24D8A5} | 182551101 | CAYUCOS 1101 | 4701 | 35.47 | -120.9762 | CAYUCOS 11014701 | 70 | 53 | 16347.1631 | 14292.3514 | 2054.8117 | 3147.6745 | 147.1533 |  |  |  |  | 3073 | 0 | 3047 | 0 | 0 | 1.9559 | 3060 | 0
| 1981 | [18 empty] | {87D8E969-EF8D-4B9C-90F3-5A57DD740C7C} | 42631108 | PETALUMA C 1108 | 296 | 38.2075 | -122.6755 | PETALUMA C 1108296 | 162 | 168 | 47770.8346 | 23764.0701 | 24006.7646 | 23764.0701 | 24006.7646 |  |  |  |  | 3020 | 0 | 3055 | 0 | 0 | 14.7663 | 3041 | 0
| 1629 | [18 empty] | {56915414-A928-48BE-9033-58A50A467962} | 13532224 | LAKEWOOD 2224 | W544R | 37.8983 | -122.0487 | LAKEWOOD 2224W544R | 168 | 554 | 35203.9422 | 8566.8847 | 26637.0575 | 0 | 96.4689 |  |  |  |  | 2978 | 0 | 3056 | 0 | 0 | 0 | 2980 | 0
North Coast | 1196 | 12 | 35.7944 | 12 | 35.7944 | 1 | 5.5732e-05 | 0 | [6 empty] | 5 | 0 | 5.5732e-05 | 1 | 1 | {34DFDDBB-39B7-422C-B7C0-767BF9731AB2} | 42761101 | FORT BRAGG A 1101 | circuit_breaker | 39.4351 | -123.7996 | FORT BRAGG A 1101circuit_breaker | 288 | 1129 | 59453.6309 | 13059.0747 | 46394.5562 | 290.3604 | 410.4589 | 5.5732e-05 | 5.5732e-05 | 2.9829 | 12 | 2182 | 0 | 3066 | 0 | 0 | 0.18042 | 1647 | 0
| 461 | [18 empty] | {BCAEB21F-2017-4B30-B93C-AB6BCBE099D0} | 182852203 | VIEJO 2203 | 9094 | 36.5607 | -121.915 | VIEJO 22039094 | 77 | 476 | 19005.0518 | 4020.7495 | 14984.3023 | 160.2742 | 149.0503 |  |  |  |  | 3066 | 0 | 3069 | 0 | 0 | 0.09959 | 2984 | 0
| 1213 | [18 empty] | {64E25E19-2C19-4D95-80FC-7B76CB3706C9} | 43201102 | STAFFORD 1102 | 1019 | 38.1121 | -122.5932 | STAFFORD 11021019 | 16 | 127 | 7480.595 | 1173.8689 | 6306.7261 | 191.5288 | 1773.8185 |  |  |  |  | 2989 | 0 | 3060 | 0 | 0 | 0.11901 | 2960 | 0
| 246 | [18 empty] | {B916F1BC-FDC7-4604-9F1E-064F6D66F284} | 42151108 | SANTA ROSA A 1108 | 626 | 38.4132 | -122.7114 | SANTA ROSA A 1108626 | 136 | 128 | 13999.9892 | 6415.5954 | 7584.3939 | 219.1314 | 120.8222 |  |  |  |  | 3061 | 0 | 3077 | 0 | 0 | 0.13616 | 2985 | 0
| 2087 | [18 empty] | {47FD814D-36E3-4524-B471-B70B44EFD5A6} | 182391103 | OILFIELDS 1103 | N44 | 35.7755 | -120.8965 | OILFIELDS 1103N44 | 133 | 98 | 34651.5429 | 29033.0076 | 5618.5353 | 28861.9134 | 5417.988 |  |  |  |  | 2961 | 0 | 3053 | 0 | 0 | 17.934 | 3120 | 0
| 1007 | [18 empty] | {B2FF44F5-E554-4874-9716-21C58C3BA291} | 182391103 | OILFIELDS 1103 | 83158 | 35.8991 | -120.942 | OILFIELDS 110383158 | 154 | 138 | 37569.9876 | 31398.3782 | 6171.6094 | 28457.0143 | 5421.1466 |  |  |  |  | 3056 | 0 | 3065 | 0 | 0 | 17.6824 | 3000 | 0
| 1192 | [18 empty] | {8AC1B346-79C7-4AB0-AEED-0EAD575A9A40} | 82952107 | EDENVALE 2107 | circuit_breaker | 37.2445 | -121.7957 | EDENVALE 2107circuit_breaker | 61 | 14 | 4719.8675 | 4245.231 | 474.6365 | 293.9737 | 0 |  |  |  |  | 3021 | 0 | 3068 | 0 | 0 | 0.18267 | 3098 | 0
| 203 | [18 empty] | {9452BDE0-DE70-4463-B819-B9B0CA79D823} | 22811102 | PACIFICA 1102 | 52715 | 37.6358 | -122.4885 | PACIFICA 110252715 | 155 | 899 | 40567.5571 | 6045.392 | 34522.1651 | 0 | 738.8686 |  |  |  |  | 3027 | 0 | 3071 | 0 | 0 | 0 | 3008 | 0
| 1178 | [18 empty] | {69F9D52B-D1A5-4442-84D4-BA9D76C2B3DC} | 43321102 | RINCON 1102 | 640 | 38.4797 | -122.6723 | RINCON 1102640 | 155 | 586 | 34617.9233 | 6850.8117 | 27767.1116 | 16.0031 | 0 |  |  |  |  | 2993 | 0 | 3062 | 0 | 0 | 0.0099439 | 2940 | 0
| 384 | [18 empty] | {E5F8D630-F65C-4493-B471-181129A51D2B} | 42631108 | PETALUMA C 1108 | 56774 | 38.2298 | -122.6524 | PETALUMA C 110856774 | 89 | 629 | 30488.8216 | 4425.4323 | 26063.3893 | 259.5884 | 2301.8142 |  |  |  |  | 3107 | 0 | 3075 | 0 | 0 | 0.1613 | 2995 | 0
| 1370 | [18 empty] | {149E5268-4926-4B7A-B9E2-928EA9B5F83B} | 43061101 | COVELO 1101 | 562360 | 39.7985 | -123.2481 | COVELO 1101562360 | 446 | 484 | 92045.7041 | 61312.0727 | 30733.6315 | 3783.6743 | 2575.347 |  |  |  |  | 2925 | 0 | 3061 | 0 | 0 | 2.3511 | 3068 | 0
| 657 | [18 empty] | {F3B21B24-5FCC-4918-B9AB-A8B8CD51F711} | 183101103 | CABRILLO 1103 | circuit_breaker | 34.6433 | -120.4377 | CABRILLO 1103circuit_breaker | 66 | 42 | 12549.9992 | 7201.0303 | 5348.9689 | 423.065 | 616.6007 |  |  |  |  | 3116 | 0 | 3070 | 0 | 0 | 0.26288 | 1292 | 0
| 873 | [18 empty] | {13C5D467-3A5D-46D1-9164-0C6474ACC9E0} | 42721104 | SONOMA 1104 | 414 | 38.2767 | -122.4908 | SONOMA 1104414 | 395 | 1313 | 95641.4943 | 28754.2864 | 66887.2078 | 669.1199 | 3264.5295 |  |  |  |  | 2923 | 0 | 3064 | 0 | 0 | 0.41577 | 2982 | 0
| 1372 | [18 empty] | {09A4B9E8-989B-4DA3-9154-EF01A44BB71B} | 103481101 | LOS MOLINOS 1101 | 1308 | 40.1057 | -122.1075 | LOS MOLINOS 11011308 | 151 | 150 | 28416.6941 | 19434.6302 | 8982.0639 | 205.1097 | 167.5421 |  |  |  |  | 2912 | 0 | 3063 | 0 | 0 | 0.12745 | 3039 | 0
| 1587 | [18 empty] | {33AE2657-6F42-4109-A970-89EF5E991C73} | 83252105 | PAUL SWEET 2105 | 10290 | 36.977 | -122.0377 | PAUL SWEET 210510290 | 500 | 2160 | 113528.1157 | 27546.0728 | 85982.0428 | 4.572 | 61.4992 |  |  |  |  | 2944 | 0 | 3051 | 0 | 0 | 0.0028409 | 3089 | 0
| 1298 | [18 empty] | {4BB2B9D0-8D98-43BA-87AD-9BC7CE46F8C2} | 42721105 | SONOMA 1105 | 4456 | 38.2734 | -122.4384 | SONOMA 11054456 | 185 | 318 | 29033.4529 | 11837.4512 | 17196.0017 | 2092.6975 | 1485.3571 |  |  |  |  | 2967 | 0 | 3067 | 0 | 0 | 1.3003 | 2932 | 0
| 504 | [18 empty] | {97A1F23E-492F-4228-8A5B-62D2949ABD33} | 12091116 | OAKLAND J 1116 | circuit_breaker | 37.7635 | -122.214 | OAKLAND J 1116circuit_breaker | 628 | 5772 | 258837.8753 | 29949.9344 | 228887.9408 | 0 | 172.4766 |  |  |  |  | 3030 | 0 | 3076 | 0 | 0 | 0 | 3059 | 0
| 401 | [18 empty] | {AD2D545D-446E-4C20-A74F-6B44E5722705} | 82831108 | MILPITAS 1108 | XR122 | 37.4307 | -121.8637 | MILPITAS 1108XR122 | 250 | 832 | 47617.1575 | 11983.0786 | 35634.0789 | 49.0072 | 8.6584 |  |  |  |  | 3047 | 0 | 3072 | 0 | 0 | 0.030452 | 3048 | 0
| 1657 | [18 empty] | {6B2D5F4D-4DFC-49DF-85DE-2AF9D30D36A6} | 102812101 | BIG MEADOWS 2101 | 2016 | 40.2098 | -121.1605 | BIG MEADOWS 21012016 | 146 | 423 | 30103.666 | 6821.8424 | 23281.8237 | 20.5741 | 0 |  |  |  |  | 2995 | 0 | 3057 | 0 | 0 | 0.012784 | 3022 | 0
| 647 | [18 empty] | {00AF1949-B9F3-40C7-B655-E7207FF7DB49} | 12501112 | EL CERRITO G 1112 | BR196 | 37.9216 | -122.3079 | EL CERRITO G 1112BR196 | 139 | 717 | 39086.242 | 5817.7228 | 33268.5192 | 68.9404 | 143.6722 |  |  |  |  | 2903 | 0 | 3074 | 0 | 0 | 0.042838 | 752 | 0
| 1383 | [18 empty] | {33EF8994-00DA-4C8F-AF23-8D41C5EB4753} | 182131104 | GONZALES 1104 | 22418 | 36.538 | -121.4635 | GONZALES 110422418 | 108 | 108 | 22094.2231 | 19539.8718 | 2554.3514 | 1354.2941 | 136.8892 |  |  |  |  | 2945 | 0 | 3058 | 0 | 0 | 0.84152 | 2957 | 0
| 1606 | [18 empty] | {F47DB185-D6D1-4508-B32F-E176427A55AE} | 182151101 | LOS COCHES 1101 | circuit_breaker | 36.3664 | -121.28 | LOS COCHES 1101circuit_breaker | 139 | 133 | 36165.178 | 32032.637 | 4132.5411 | 3722.9416 | 1109.6374 |  |  |  |  | 3118 | 0 | 3054 | 0 | 0 | 2.3133 | 3020 | 0
| 1457 | [18 empty] | {67620093-3D29-47F3-861E-D41DF7A61FA6} | 43201102 | STAFFORD 1102 | 1258 | 38.108 | -122.5924 | STAFFORD 11021258 | 174 | 718 | 45014.2545 | 7855.3012 | 37158.9533 | 110.3452 | 191.833 |  |  |  |  | 2991 | 0 | 3052 | 0 | 0 | 0.068565 | 3057 | 0
| 11 | [18 empty] | {382A16B7-3BCC-4C59-941A-61838BC92D6A} | 182611103 | PASO ROBLES 1103 | N50 | 35.714 | -120.8384 | PASO ROBLES 1103N50 | 44 | 3 | 3489.6284 | 3452.721 | 36.9075 | 3452.721 | 36.9075 |  |  |  |  | 2949 | 0 | 3073 | 0 | 0 | 2.1454 | 3127 | 0
| 1267 | [18 empty] | {A1A1D221-0393-4995-8057-AA9153B871D9} | 192381103 | EEL RIVER 1103 | circuit_breaker | 40.6028 | -124.21 | EEL RIVER 1103circuit_breaker | 607 | 1324 | 117233.0757 | 64348.2732 | 52884.8025 | 0 | 284.4698 |  |  |  |  | 3038 | 0 | 3059 | 0 | 0 | 0 | 3025 | 0