## Sheet1 (2)
Current State | 304 | 165 |  | 119 | 18 |  | 2 | 0 |  | Commitments
2.16.21 | Total | 233.2 | 258.4 | 214.2 | 214 | 58 | 281 |  |  | Days | Weeks
| FCST | 85.2 | 166.4 | 172.2 | 213 | 57 | 279 | 293 | Estimating: | 60 | 8.5
| ACT | 148 | 92 | 42 | 1 | 1 | 2 | 0 | PEND/ Pre-Commissioning: | 60 | 8.5 | 2020-01-01
|  | ESTS | PEND | Const - GC | Const - Cont |  | IA | QA | Field Install: | 56 | 8
2021-01-03 | ACT | 120 |  | 7 |  |  |  |  | Commissioning: | 14 | 2
| FCST | 120 |  | 7 |  |  |  |  | QA: | 14 | 2
2021-01-10 | ACT
FCST
2021-01-17 | ACT
FCST
2021-01-24 | ACT | [5 empty] | 2
| FCST | [5 empty] | 2
2021-01-31 | ACT |  |  |  | 0 | 0 | 0 | 0
| FCST |  |  |  | 0 | 0 | 0 | 0
2021-02-07 | ACT |  |  |  | 0 | 0 | 0 | 0
| FCST |  |  |  | 0 | 0 | 0 | 0
2021-02-14 | ACT
| FCST |  |  |  | 0 |  | 0
2021-02-21 | ACT | 2.5 | 1.1 | 1.8 | 1.1
| FCST | 0 | 0.7 | 0.6 | 0 | 0 | 0
2021-02-28 | ACT
| FCST | 14.6 | 1.7 | 0.7 |  |  | 0 | 0
2021-03-07 | ACT
| FCST | 21.1 | 0 | 0.8
2021-03-14 | ACT
| FCST | 0 | 0 | 2.8 | 1.5
2021-03-21 | ACT
| FCST | 0 | 0 | 0.5 | 1.5
2021-03-28 | ACT
| FCST | 5.5 | 0 | 2.8 | 2
2021-04-04 | ACT
| FCST | 20 | 20 | 20 | 2 | 1 | 12 | 16
2021-04-11 | ACT
| FCST | 20 | 20 | 20 | 33 | 8 | 20 | 20
2021-04-18 | ACT
| FCST | 4 | 20 | 20 | 9 | 2 | 19 | 20
2021-04-25 | ACT
| FCST |  | 20 | 20 | 13 | 5 | 14 | 17
2021-05-02 | ACT
| FCST |  | 20 | 20 | 3 | 5 | 18 | 16
2021-05-09 | ACT
| FCST |  | 20 | 20 | 8 | 5 | 8 | 16
2021-05-16 | ACT
| FCST |  | 20 | 20 | 11 | 5 | 13 | 16
2021-05-23 | ACT
| FCST |  | 20 | 20 | 8 | 5 | 16 | 16
2021-05-30 | ACT
| FCST |  | 4 | 4 | 1 | 5 | 16 | 16
2021-06-06 | ACT
| FCST |  |  |  | 15 | 5 | 6 | 16
2021-06-13 | ACT
| FCST |  |  |  | 15 | 5 | 20 | 16
2021-06-20 | ACT
| FCST |  |  |  | 15 | 5 | 20 | 16
2021-06-27 | ACT
| FCST |  |  |  | 15 | 1 | 20 | 16
2021-07-04 | ACT
| FCST |  |  |  | 15 | 0 | 17 | 16
2021-07-11 | ACT
| FCST |  |  |  | 15 | 0 | 15 | 15
2021-07-18 | ACT
| FCST |  |  |  | 15 | 0 | 15 | 15
2021-07-25 | ACT
| FCST |  |  |  | 15 | 0 | 15 | 15
2021-08-01 | ACT
| FCST | [5 empty] | 15 | 15
2021-08-08 | ACT
| FCST | [6 empty] | 16
2021-08-15 | ACT
| FCST | [6 empty] | 17
2021-08-22 | ACT
| FCST | [6 empty] | 18
2021-08-29 | ACT
| FCST | [6 empty] | 19
Assumptions Actual Estimating/Pend dates were used when available. If dates were not available a flat calculation of 20 units/week was used for estimating and pend out was calculated as 45 days past the estimating out date. Resource assignments were taken from the MPP workplan where available. If the resource assignment was blank, they were assigned as 25% contracting, 75% GC. Based on resource assignment, scheduled field install dates were calculated at 4 weeks after Pend Out for Contracting and 8 weeks after Pend Out for GC. The commissioning out date was set as 1 week after the scheduled field install date.

## Sheet1
Wk. of | ESTS | PEND | Construction
2021-02-21 | 0 | 0.7 | 0.55
2021-02-28 | 14.6 | 1.7 | 0.65
2021-03-07 | 21.13 | 0 | 0.83
2021-03-14 | 0 | 0 | 2.83
2021-03-21 | 0 | 0 | 0.53
2021-03-28 | 5.52 | 0 | 2.81