## Summary
Values
Job Owner Name | Order | Order Description | Project Reporting Year | Pre-Eng. Complete | Pre-Eng. Mtg Date | Base Map Status | Expected Base Map Complete | Sum of UG Feet | Sum of OH Feet
Mendez, Angelica | 35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | 2021 | Y | 2021-02-18 | N/A |  | 0 | 4752
| 35219266 | CWSP - MARIPOSA 2102CB PH 1 | 2021 | Y | 2021-02-22 | N/A | 2021-03-31 | 0 | 13713
| 35219268 | CWSP - MARIPOSA 210197142 PH 1 | 2021 | Y | 2021-02-08 | In Progress | 2021-03-12 | 0 | 8553.6
| 35226241 | CWSP - MARIPOSA 210197142 PH 2 | 2021 | Y | 2021-02-08 | In Progress | 2021-03-12 | 0 | 7920
| 35227263 | CWSP - MARIPOSA 2102CB PH 2 | 2021 | Y | 2021-02-22 | N/A |  | 0 | 1315.42
Mendez, Angelica Total | [7 empty] | 0 | 36254.02
Kringler, Jeff L | 35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | 2021 | N | 2021-04-14 | In Progress | 2021-04-12 | 8106 | 0
| 35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | 2021 | N | 2021-04-21 | In Progress | 2021-04-19 | 22892 | 0
| 35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | 2021 | N | 2021-06-01 | In Progress |  | 13200 | 0
| 35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | 2021 | N | 2021-06-01 |  |  | 264 | 0
| 35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | 2021 | Y | 2021-02-18 | N/A |  | 0 | 9153
| 35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | 2021 | Y | 2021-02-18 | N/A |  | 0 | 10475
| 35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | 2021 | Y | 2021-03-01 | N/A |  | 0 | 13164
| 35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | 2021 | Y | 2021-03-01 | N/A | 2021-04-19 | 0 | 14807
| 35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | 2021 | Y | 2021-03-01 | N/A |  | 0 | 5438.4
| 35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | 2021 | Y | 2021-03-01 | N/A |  | 0 | 10262
| 35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | 2021 | Y | 2021-02-18 | N/A |  | 0 | 8691
| 35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | 2021 |  |  | In Progress | 2021-04-12 | 1742.4 | 0
| 35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | 2021 | Y | 2021-02-18 | N/A |  | 0 | 7023
| 35232650 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | 2021 | N | 2021-06-01 | In Progress | 2021-04-15 | 9028 | 0
| 35232651 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.3 | 2021 | N | 2021-06-01 | N/A |  | 0 | 9187.2
Kringler, Jeff L Total | [7 empty] | 55232.4 | 88200.6
Nguyen, My-Linh | 35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | 2021 | Y | 2021-02-26 | In Progress | 2021-04-11 | 7075.2 | 0
| 35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | 2021 | Y | 2021-02-26 | In Progress |  | 6019 | 0
| 35219096 | CWSP - KIRKER 2104442850 PH 1.1 | 2021 | Y | 2021-02-26 | In Progress |  | 8817.6 | 0
| 35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | 2021 | Y | 2021-02-26 | N/A |  | 0 | 5544
| 35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | 2021 | Y | 2021-02-26 | In Progress |  | 6864 | 0
| 35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | 2021 | Y | 2021-02-26 | N/A |  | 0 | 6336
Nguyen, My-Linh Total | [7 empty] | 28775.8 | 11880
Pantoja-Martinez, Jaime | 35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | 2021 | Y | 2021-02-26 | N/A |  | 0 | 26400
| 35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | 2021 | N | 2021-04-09 | In Progress | 2021-04-19 | 2534.4 | 0
| 35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | 2021 | Y | 2021-02-26 | N/A |  | 0 | 12473
| 35223037 | PSPS - OAKHURST 1101 - OAKHURST | 2021 | Y | 2021-02-26 | N/A |  | 105.6 | 0
| 35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | 2021 | Y | 2021-02-26 | N/A |  | 0 | 13833.6
| 35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | 2021 | Y | 2021-02-26 | N/A |  | 0 | 12443
| 35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | 2021 | Y | 2021-02-26 | N/A |  | 0 | 11421
| 35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | 2021 | Y | 2021-02-26 | N/A |  | 0 | 6152
| 35026643 | DIAMOND SPRINGS 1105 - LR 2102 | 2021 | N | 2021-03-23 | N/A |  | 0 | 8553.6
Pantoja-Martinez, Jaime Total | [7 empty] | 2640 | 91276.2
Barron, Raul Angelo | 35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | 2021 | Y | 2021-02-22 | In Progress | 2021-04-12 | 5860 | 0
| 35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | 2021 | Y | 2021-02-11 | In Progress | 2021-03-19 | 4224 | 0
| 35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | 2021 | Y | 2021-02-11 | In Progress | 2021-03-19 | 2481.6 | 0
| 35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | 2021 | Y | 2021-02-11 | N/A |  | 0 | 5860
| 35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | 2021 | Y | 2021-02-11 | N/A |  | 0 | 3907.2
| 35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | 2021 | Y | 2021-02-11 | N/A |  | 0 | 4857.6
| 35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | 2021 | Y | 2021-02-22 | N/A |  | 0 | 15153
| 35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | 2021 | Y | 2021-02-22 | In Progress | 2021-04-12 | 9398 | 0
| 35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | 2021 | Y | 2021-02-22 | N/A |  | 0 | 9187
| 35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | 2021 | Y | 2021-02-22 | N/A |  | 0 | 11563
| 35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | 2021 | Y | 2021-02-22 | N/A |  | 0 | 3168
Barron, Raul Angelo Total | [7 empty] | 21963.6 | 53695.8
Donovan, Patrick | 35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | 2021 | N | 2021-04-30 | In Progress |  | 6177.6 | 0
| 35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | 2021 | N | 2021-03-31 |  |  | 0 | 1426
| 35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | 2021 | N | 2021-04-30 |  |  | 10771 | 0
| 35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | 2021 | N | 2021-04-30 | In Progress |  | 0 | 2270
| 35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | 2021 | N | 2021-04-30 | In Progress |  | 0 | 2904
| 35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | 2021 | N | 2021-04-30 | In Progress |  | 8131 | 0
| 35217273 | SH - UPPER LAKE 1101 CB | 2021 | N |  | In Progress | 2021-03-15 | 0 | 5702.4
| 35219272 | CWSP - MIDDLETOWN 1101481876 | 2021 | Y | 2021-02-26 |  |  | 0 | 4857.6
| 35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | 2021 | N | 2021-03-31 |  |  | 0 | 8870
| 35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | 2021 | N | 2021-03-31 | In Progress |  | 10190 | 1162
| 35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | N | 2021-04-30 | In Progress |  | 1478 | 0
| 35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | N | 2021-03-31 |  |  | 0 | 4699
| 35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | 2021 | N | 2021-04-30 | In Progress |  | 8606.4 | 0
| 35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | 2021 | N | 2021-04-30 | In Progress |  | 0 | 4699.2
| 35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | 2021 | N | 2021-03-31 | In Progress |  | 0 | 4224
| 35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | 2021 | N | 2021-04-30 |  |  | 8184 | 0
| 35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | 2021 | N | 2021-03-31 |  |  | 0 | 4013
| 35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | 2021 | N | 2021-03-31 |  |  | 0 | 6072
| 35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | 2021 | N | 2021-03-31 |  |  | 0 | 7709
| 35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | 2021 | N | 2021-04-30 |  |  | 792 | 0
| 35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | 2021 | N | 2021-04-30 |  |  | 0 | 10507
| 35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | 2021 | N | 2021-03-31 |  |  | 0 | 4171
| 35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | 2021 | N | 2021-03-31 |  |  | 0 | 3168
| 35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | 2021 | N | 2021-03-31 |  |  | 0 | 5491
| 35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | 2021 | N | 2021-03-31 | In Progress |  | 7287 | 1796
| 35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | 2021 | N | 2021-03-31 | In Progress |  | 8184 | 2534
| 35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | 2021 | N | 2021-04-30 | In Progress |  | 6970 | 0
| 35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | 2021 | N | 2021-04-30 |  |  | 0 | 3907
| 35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | 2021 | N | 2021-04-30 | In Progress |  | 1690 | 0
| 35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | 2021 | N | 2021-04-30 |  |  | 0 | 2429
| 35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | 2021 | N | 2021-04-30 |  |  | 0 | 4752
| 35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | 2021 | N | 2021-04-30 | In Progress |  | 5333 | 0
| 35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | 2021 | N | 2021-04-30 |  |  | 9504 | 0
| 35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | 2021 | N | 2021-04-30 |  |  | 8290 | 0
| 35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | 2021 | N | 2021-03-31 |  |  | 0 | 1056
| 35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | 2021 | N | 2021-03-31 |  |  | 0 | 8026
| 35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | 2021 | N | 2021-03-31 |  |  | 0 | 5755
| 35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | 2021 | N | 2021-03-31 |  |  | 0 | 4171
| 35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | 2021 | N | 2021-04-30 | In Progress |  | 3274 | 0
| 35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | 2021 | N | 2021-03-31 |  |  | 0 | 2746
| 35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | 2021 | N | 2021-03-31 |  |  | 0 | 5174
| 35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | 2021 | N | 2021-03-31 | In Progress |  | 0 | 2112
| 35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | 2021 | N | 2021-04-30 | In Progress |  | 7867 | 0
| 35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | 2021 | N | 2021-03-31 |  |  | 0 | 3326
Donovan, Patrick Total | [7 empty] | 112729 | 129729.2
Eagar, Josh | 35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | 2021 | Y | 2021-03-04 | N/A |  | 0 | 2824
| 35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | 2021 | Y | 2021-03-08 | N/A |  | 0 | 7273
| 35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | 2021 | Y | 2021-03-04 | N/A |  | 0 | 5131
| 35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | 2021 | N |  |  |  | 5491.2 | 0
| 35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | 2021 | N |  |  |  | 0 | 3761
| 35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | 2021 | N |  |  |  | 21597 | 0
| 35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | 2021 | Y | 2021-02-26 | N/A |  | 0 | 11721.6
| 35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | 2021 | Y | 2021-02-26 | N/A |  | 0 | 7075.2
| 35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | 2021 | N |  | N/A |  | 0 | 7718
| 35192284 | ECOP - SILVERADO 2104 - H05-LR726 | 2021 | N |  | In Progress | 2021-03-29 | 10929.6 | 0
| 35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | 2021 | Y | 2021-02-18 | N/A |  | 0 | 3774
| 35223024 | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | 2021 | N |  | In Progress | 2021-03-29 | 11827.2 | 0
| 35223026 | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | 2021 | N |  | In Progress | 2021-03-29 | 9504 | 0
| 35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | 2021 | Y | 2021-02-26 | N/A |  | 0 | 10190
| 35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | 2021 | Y | 2021-03-04 | N/A |  | 0 | 8026
| 35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | 2021 | N |  |  |  | 4488 | 0
| 35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | 2021 | N |  |  |  | 0 | 2006.4
| 35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | 2021 | N |  |  |  | 0 | 4646.4
| 35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | 2021 | N |  |  |  | 0 | 3484.8
| 35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | 2021 | N |  |  |  | 0 | 3062.4
| 35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | 2021 | N |  | N/A |  | 0 | 2786
| 35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | 2021 | N |  | N/A |  | 0 | 1724
| 35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | 2021 | N |  | N/A |  | 0 | 1243
| 35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | 2021 | N |  | N/A |  | 0 | 2736
| 35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | 2021 | N |  | N/A |  | 0 | 2215
| 35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | 2021 | N |  |  |  | 5488 | 0
| 35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | 2021 | N |  |  |  | 3109 | 0
| 35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | 2021 | N |  |  |  | 3809 | 0
| 35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | 2021 | N |  |  |  | 2286 | 0
| 35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | 2021 | N |  |  |  | 3067 | 0
| 35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | 2021 | N |  |  |  | 1839 | 0
| 35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | 2021 | N |  |  |  | 15183 | 0
| 35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | 2021 | N |  |  |  | 0 | 834
| 35227013 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 | 2021 | N |  |  |  | 0 | 168
| 35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | 2021 | N |  |  |  | 0 | 5106
| 35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | 2021 | N |  |  |  | 0 | 6312
| 35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | 2021 | N |  |  |  | 0 | 1144
| 35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | 2021 | N |  |  |  | 2900 | 0
| 35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | 2021 | N |  | N/A |  | 0 | 4600
| 35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | 2021 | N |  | N/A |  | 0 | 6936
| 35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | 2021 | Y | 2021-02-18 | In Progress | 2021-03-12 | 3221 | 0
| 35234756 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 |  | N |  |  |  | 14689 | 0
| 35234758 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 |  | N |  |  |  | 3073 | 0
| 35234862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 |  | N |  |  |  | 422 | 0
| 35234865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 |  | N |  |  |  | 3419 | 0
Eagar, Josh Total | [7 empty] | 126342 | 116497.8
Hernandez, Michael Donald James | 35219273 | CWSP - VOLTA 110149742 | 2021 | Y | 2021-02-26 | N/A |  | 0 | 15470
| 35219589 | CWSP - WILDWOOD 11011454 | 2021 |  |  |  |  | 0 | 13622.4
| 35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | 2021 |  |  |  |  | 0 | 12302.4
| 35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | 2021 |  |  |  |  | 0 | 8395.2
| 35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | 2021 |  |  |  |  | 1003.2 | 0
Hernandez, Michael Donald James Total | [7 empty] | 1003.2 | 49790
Lorz, Jesse | 35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | 2021 |  |  |  |  | 6124 | 420
| 35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | 2021 |  |  |  |  | 2552 | 1168
Lorz, Jesse Total | [7 empty] | 8676 | 1588
Skarda, Travis Damian | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 2021 |  |  | In Progress | 2021-05-07 | 0 | 1056
| 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 2021 |  |  | In Progress |  | 1584 | 0
| 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 2021 | Y | 2021-02-26 |  |  | 0 | 4224
| 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 2021 |  |  |  |  | 3009.6 | 0
| 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 2021 |  |  | In Progress |  | 4065.6 | 0
| 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 2021 |  |  | In Progress | 2021-05-07 | 9134.4 | 0
| 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 2021 |  |  | In Progress | 2021-05-07 | 9662.4 | 0
| 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 2021 |  |  | N/A |  | 0 | 1531.2
| 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 2021 |  |  | In Progress |  | 4329.6 | 0
| 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 2021 |  |  | In Progress |  | 23760 | 0
| 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 2021 |  |  | N/A |  | 0 | 7603.2
| 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 2021 |  |  | N/A |  | 0 | 8131.2
| 35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | 2021 |  |  | In Progress |  | 3010 | 0
Skarda, Travis Damian Total | [7 empty] | 58555.6 | 22545.6
Mccabe, Patrick James | 35219286 | CWSP - DESCHUTES 11049718 PH1.1 | [5 empty] | 0 | 18241
Mccabe, Patrick James Total | [7 empty] | 0 | 18241
Ung, Mason | 35225825 | CWSP - DESCHUTES 11049718 PH2.1 | [5 empty] | 0 | 8217
| 35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | [5 empty] | 0 | 16251
| 35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | [5 empty] | 0 | 5468
| 35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | [5 empty] | 0 | 18648
| 35232445 | CWSP - DESCHUTES 11049718 PH 2.5 | [5 empty] | 0 | 13748
| 35232960 | CWSP - DESCHUTES 11049718 PH1.2 | [5 empty] | 0 | 16057
Ung, Mason Total | [7 empty] | 0 | 78389
Grand Total | [7 empty] | 415917.6 | 698087.22

## Data
Order | Job Owner Name | Project Reporting Year | Order Description | Job Owner | Scope Status | SAP Status | Circuit Feet from Planning | UG Feet | OH Feet | Planned Circuit Feet | Planned Circuit Miles | 2020 Forecast Feet | 2020 Forecast Miles | 2021 Forecast Feet | 2021 Forecast Miles | 2022 Forecast Feet | 2022 Forecast Miles | 2023 Forecast Feet | 2023 Forecast Miles | Unallocated Forecast Miles | SAP Plan Units | SAP Plan Miles | Div | MAT | Program | Ready to Break Ground | Pre-Eng. Mtg Date | Pre-Eng. Complete | EOD Forecast | Previous EOD Forecast | Prelim Dwg Forecast | Previous Prelim Dwg Forecast | Prelim Dwg Out | PEND IN Date | --1 | Expected Joint Pole Date | Joint Pole Complete | Joint Pole Coordinator | Joint Pole Notes | LCE | Land Clear Date | Previous Land Clear Date | Base Map Status | Expected Base Map Complete | Base Map Vendor | Surveyor | Land Complete | ERTC Planned Date | Previous ERTC Date | ERTC Complete | --2 | Expected Permit Date | Permits Complete | --3 | Veg Complete | Veg Completed | Veg Start | --4 | MPP Resource | Contractor | Contract Ready Date | Contract Status | SAP Actual Units | SAP Actual Miles | 2019 Feet Installed | 2019 Miles Installed | 2020 Feet Installed | 2020 Miles Installed | 2021 Feet Installed | 2021 Miles Installed | Total Installed Miles | Remaining Planned Miles | QA Pass | QA Fix | Total QA Span Length | QA Remaining | QA Trailing Installed | IA Pass | Span Notes | Construction Notes | P6 Business Case Date | BC Complete | DS24 Status | P6 Construction Start | --5 | Auth Amt without Contingency (Expected Case) | Total EAC | --6 | Planned Num of Poles | Planning Engineer | General Comments | Scoping Status | Scoping Notes | DLT | Telecom | SCADA Specialist | SWPPP Status | FE Primary or Support | City | County | Latitude | Longitude | Schedule ID | Mainline or Tapline | Hardening Method | Rank Number | CompYR | QTR | Work Plan EOD Baseline | Construction Start Baseline | Construction Complete Baseline | Circuit Protection Zone | Risk Rank | Segmentation ID# | Project Type | Last Edited By | Last Edited Date | Blank 1
35026643 | Pantoja-Martinez, Jaime | 2021 | DIAMOND SPRINGS 1105 - LR 2102 | J1PE | Scoped | UNSE | 7400 | 0 | 8553.6 | 8553.6 | 1.62 | 0 | 0 | 8554 | 1.6201 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | SI | 08W | SH | 2022-06-10 17:00 | 2021-03-23 | N | [11 empty] | Jeanette Johnson |  |  | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.62 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-06-10 17:00 |  | INPR | 2022-06-29 11:00 |  | 100000 | 1882335.5 |  | 22 | Gurshawn Dhillon | Still need to be scoped / table topped | [7 empty] | El Dorado | El Dorado | 0 | 0 | 35026643 | MX | OH |  | 999 |  |  |  |  | DIAMOND SPRINGS 11052102 | 666 |  | WDDB | AXYX | 2021-03-11 17:02
35062374 | Kringler, Jeff L | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | J6KF | Scoped | UNSE |  | 8106 | 0 | 8106 | 1.5352 | 0 | 0 | 0 | 0 | 8106 | 1.5352 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-14 17:00 | 2021-04-14 | N | 2021-05-31 | [13 empty] | In Progress | 2021-04-12 | Mark Thomas | Eric Finley | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5352 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-29 08:00 |  | 220000 | 4904599.4 |  |  | Maxwell Muscarella | Site survey requested 3/9/2021 |  | Prioritized |  |  | SCADA |  |  | Shingle Springs | El Dorado | 0 | 0 | [10 empty] | 227 | 35062374 | PRE | AXYX | 2021-03-11 16:34
35062375 | Barron, Raul Angelo | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | R4BA | Scoped | UNSE |  | 5860 | 0 | 5860 | 1.1098 | 0 | 0 | 0 | 0 | 5860 | 1.1098 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-10-14 17:00 | 2021-02-22 | Y | 2021-05-31 | [10 empty] | Jeanette Johnson |  |  | In Progress | 2021-04-12 | Mark Thomas | Eric Finley | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1098 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-10-14 17:00 |  | INPR | 2022-01-10 08:00 | [14 empty] | Shingle Springs | El Dorado | 0 | 0 | [10 empty] | 227 | 35062375 | PRE | AXYX | 2021-03-11 16:26
35062376 | Kringler, Jeff L | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | J6KF | Scoped | UNSE |  | 22892 | 0 | 22892 | 4.3356 | 0 | 0 | 0 | 0 | 22892 | 4.3356 | 0 | 0 | 0 |  |  | SI | 08W | SH |  | 2021-04-21 | N | [14 empty] | In Progress | 2021-04-19 | Mark Thomas | Eric Finley | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3356 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 220000 | 8027019.4 |  |  | Rory McDermott | Site survey requested 2/25/2021 |  | Prioritized |  |  | SCADA |  |  | Shingle Springs | El Dorado | 0 | 0 | [10 empty] | 159 | 35062376 | PRE | J6KF | 2021-03-11 10:00
35137590 | Eagar, Josh | 2021 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | J1E1 | Scoped | ESTS | 2824 | 0 | 2824 | 2824 | 0.53485 | 0 | 0 | 2824 | 0.53485 | 0 | 0 | 0 | 0 | 1.5152e-10 |  |  | HB | 08W | SH | 2021-04-15 | 2021-03-04 | Y | 2021-04-15 | 2021-04-15 | [9 empty] | Melissa Brainard | 2021-04-05 | 2021-03-31 | N/A |  |  |  |  | 2021-04-05 | 2021-03-31 | [9 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.53485 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-03-29 17:00 |  | N/A | 2021-11-08 08:00 |  | 80000 | 50802.7 |  |  |  |  | Complete | Prioritized | [5 empty] | Middletown | Lake | 38.7927 | -122.6592 | 35137590 |  |  | 2021-056 | 2021 |  |  |  | 2020-09-01 | MIDDLETOWN 1101CB | 86 |  | ECOP | J1E1 | 2021-03-11 14:14
35137593 | Eagar, Josh | 2021 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | J1E1 | Scoped | ESTS | 7273 | 0 | 7273 | 7273 | 1.3775 | 0 | 0 | 7273 | 1.3775 | 0 | 0 | 0 | 0 | -2.1212e-10 |  |  | HB | 08W | SH | 2021-04-27 17:00 | 2021-03-08 | Y | 2021-04-15 | 2021-04-15 | [9 empty] | Melissa Brainard | 2021-04-23 |  | N/A |  |  |  |  | 2021-04-23 | [10 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3775 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-04-27 17:00 |  | N/A | 2021-10-14 08:00 |  | 80000 | 56474.5 |  |  |  |  | Complete | Prioritized | [5 empty] | Cobb | Lake | 38.7927 | -122.6592 | 35137593 |  |  | 2021-054 | 2021 |  |  |  | 2020-09-01 | MIDDLETOWN 11014646 | 328 |  | ECOP | J1E1 | 2021-03-11 14:14
35137596 | Eagar, Josh | 2021 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | J1E1 | Scoped | ESTS | 5131 | 0 | 5131 | 5131 | 0.97178 | 0 | 0 | 5131 | 0.97178 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-23 | 2021-03-04 | Y | 2021-04-15 | 2021-04-15 | [9 empty] | Melissa Brainard | 2021-04-23 |  | N/A |  |  |  |  | 2021-04-23 | [10 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97178 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-03-30 17:00 |  | N/A | 2021-10-26 08:00 |  | 80000 | 37548.6 |  |  |  |  | Complete | Prioritized | [5 empty] | Cobb | Lake | 38.7927 | -122.6592 | 35137596 |  |  | 2021-055 | 2021 |  |  |  | 2020-09-01 | MIDDLETOWN 11014646 | 328 |  | ECOP | J1E1 | 2021-03-11 14:14
35174478 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | J1E1 | Scoped | UNSE |  | 5491.2 | 0 | 5491.2 | 1.04 | 0 | 0 | 0 | 0 | 5491 | 1.04 | 0 | 0 | 3.7879e-05 |  |  | HB | 08W | SH | 2022-01-17 17:00 |  | N | 2021-06-30 | [16 empty] | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.04 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-01-17 17:00 |  | N/A | 2022-11-01 08:00 |  | 155000 | [12 empty] | Middletown | Lake | 38.7576 | -122.6358 |  |  |  | 2021-061 | 2021 |  |  |  |  | MIDDLETOWN 1101548 | 474 | 35174478 | ECOP | J1E1 | 2021-03-11 13:58
35174479 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | J1E1 | Scoped | UNSE |  | 0 | 3761 | 3761 | 0.71231 | 0 | 0 | 0 | 0 | 3761 | 0.71231 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 |  | N | 2021-04-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71231 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7576 | -122.6358 |  |  |  | 2021-063 | 2021 | [5 empty] | 474 | 35174479 | ECOP | J1E1 | 2021-03-11 13:59
35174501 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | J1E1 | Scoped | UNSE |  | 21597 | 0 | 21597 | 4.0903 | 0 | 0 | 0 | 0 | 21597 | 4.0903 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2022-01-17 17:00 |  | N | 2021-06-30 | [15 empty] | Mark Thomas & Tera Tech | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.0903 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-01-17 17:00 |  | N/A | 2022-11-01 08:00 |  | 118750 | [12 empty] | Middletown | Lake | 38.3526 | -122.5226 |  |  |  | 2021-065 | 2021 | [5 empty] | 474 | 35174501 | ECOP | J1E1 | 2021-03-11 13:59
35191318 | Eagar, Josh | 2021 | ECOP - SILVERADO 2102 - H02-LR58626 | J1E1 | Scoped | ESTS |  | 0 | 11721.6 | 11721.6 | 2.22 | 0 | 0 | 11722 | 2.2201 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | NB | 08W | SH | 2021-06-11 17:00 | 2021-02-26 | Y | 2021-03-31 | 2021-03-31 | [12 empty] | N/A | [15 empty] | Contract | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.22 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-11 17:00 |  | N/A | 2021-07-01 08:00 |  | 682400 | 45162.4 | [5 empty] | Prioritized | [5 empty] | Saint Helena | Napa | 38.5095 | -122.386 | [10 empty] | 663 |  | ECOP | EDW9 | 2021-03-12 09:13
35191319 | Donovan, Patrick | 2021 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | P3D5 | Scoped | UNSE |  | 6177.6 | 0 | 6177.6 | 1.17 | 0 | 0 | 0 | 0 | 6178 | 1.1701 | 0 | 0 | -7.5758e-05 |  |  | NB | 08W | SH | 2021-08-20 17:00 | 2021-04-30 | N | [14 empty] | In Progress |  | Tetratech | Courtney Faulkenberry | [12 empty] | Contract | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.17 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-20 17:00 |  | N/A | 2021-09-14 08:00 |  | 312500 | [12 empty] | Nicasio | Marin | 38.046 | -122.646 | [10 empty] | 215 | 35191319 | ECOP | P3D5 | 2021-03-11 10:43
35191383 | Eagar, Josh | 2021 | ECOP - SILVERADO 2102 - H01-LR58626 | J1E1 | Scoped | ESTS |  | 0 | 7075.2 | 7075.2 | 1.34 | 0 | 0 | 7075 | 1.34 | 0 | 0 | 0 | 0 | 3.7879e-05 |  |  | NB | 08W | SH | 2021-06-07 17:00 | 2021-02-26 | Y | 2021-03-31 | 2021-03-31 | [12 empty] | N/A | [15 empty] | Contract | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.34 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-07 17:00 |  | N/A | 2021-08-16 08:00 |  | 614000 | 34923.2 | [5 empty] | Prioritized | [5 empty] | Saint Helena | Napa | 38.5057 | -122.401 | [10 empty] | 663 |  | ECOP | EDW9 | 2021-03-12 09:13
35191937 | Eagar, Josh | 2021 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | J1E1 | Scoped | UNSE |  | 0 | 7718 | 7718 | 1.4617 | 0 | 0 | 0 | 0 | 7718 | 1.4617 | 0 | 0 | 0 |  |  | NB | 08W | SH |  |  | N | [14 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4617 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 237833 | [12 empty] | Napa | Napa | 38.4108 | -122.4506 | [10 empty] | 951 | 35191937 | ECOP | J1E1 | 2021-03-11 14:15
35192280 | Nguyen, My-Linh | 2021 | ECOP - CLAYTON 2212 - H01-LR2951 | M1NO | Scoped | UNSE |  | 7075.2 | 0 | 7075.2 | 1.34 | 0 | 0 | 0 | 0 | 7075 | 1.34 | 0 | 0 | 3.7879e-05 |  |  | DI | 08W | SH |  | 2021-02-26 | Y | [14 empty] | In Progress | 2021-04-11 | WHP | Joe Waller | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.34 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 550000 | 91561.9 | [5 empty] | Prioritized | [5 empty] | Clayton | Contra Costa | 37.8682 | -121.8573 | [10 empty] | 377 | 35192280 | ECOP | EDW9 | 2021-03-11 12:49
35192281 | Donovan, Patrick | 2021 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | P3D5 | Scoped | UNSE |  | 0 | 1426 | 1426 | 0.27008 | 0 | 0 | 1426 | 0.27008 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-07-23 17:00 | 2021-03-31 | N | 2021-06-30 | [29 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27008 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-23 17:00 |  | N/A | 2021-08-17 08:00 | [14 empty] | Middletown | Lake | 38.7238 | -122.6197 | [10 empty] | 468 | 35192281 | ECOP | P3D5 | 2021-03-11 10:41
35192282 | Donovan, Patrick | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | P3D5 | Scoped | UNSE |  | 10771 | 0 | 10771 | 2.04 | 0 | 0 | 0 | 0 | 10771 | 2.04 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-04-30 | N | 2021-06-30 | [29 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7238 | -122.6197 | [10 empty] | 468 | 35192282 | ECOP | P3D5 | 2021-03-11 10:43
35192284 | Eagar, Josh | 2021 | ECOP - SILVERADO 2104 - H05-LR726 | J1E1 | Scoped | UNSE |  | 10929.6 | 0 | 10929.6 | 2.07 | 0 | 0 | 10930 | 2.0701 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | NB | 08W | SH | 2021-07-28 17:00 |  | N | [14 empty] | In Progress | 2021-03-29 | Mark Thomas | Joe Waller | [12 empty] | Contract | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.07 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-28 17:00 |  | N/A | 2021-08-17 08:00 |  | 190000 | 155254 | [5 empty] | Prioritized | [5 empty] | Pope Valley | Napa | 38.6154 | -122.4315 | [10 empty] | 279 | 35192284 | ECOP | J1E1 | 2021-03-11 13:59
35192290 | Pantoja-Martinez, Jaime | 2021 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | J1PE | Scoped | ADER |  | 0 | 26400 | 26400 | 5 | 0 | 0 | 26400 | 5 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-07-01 17:00 | 2021-02-26 | Y | 2021-03-31 | 2021-03-12 | 2021-03-04 | [8 empty] | Jeanette Johnson |  |  | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-01 17:00 |  | INPR | 2021-07-26 08:00 |  | 950000 | 6927773.6 | [11 empty] | Placerville | El Dorado | 38.739 | -120.9057 |  | MX | OH | [7 empty] | 811 |  | ECOP | AXYX | 2021-03-11 16:21
35192291 | Pantoja-Martinez, Jaime | 2021 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | J1PE | Scoped | UNSE |  | 2534.4 | 0 | 2534.4 | 0.48 | 0 | 0 | 0 | 0 | 2534 | 0.47992 | 0 | 0 | 7.5758e-05 |  |  | SI | 08W | SH | 2021-11-10 17:00 | 2021-04-09 | N | 2021-04-30 | 2021-04-30 | [9 empty] | Jeanette Johnson |  |  | In Progress | 2021-04-19 | Psomas | Eric Finley | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-11-10 17:00 |  | INPR | 2022-02-04 08:00 |  | 500000 | 1628399 | [11 empty] | Placerville | El Dorado | 38.7215 | -120.8714 |  | MX | MX | [7 empty] | 811 | 35192291 | ECOP | J1PE | 2021-03-11 15:56
35192292 | Barron, Raul Angelo | 2021 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | R4BA | Scoped | UNSE |  | 4224 | 0 | 4224 | 0.8 | 0 | 0 | 0 | 0 | 4224 | 0.8 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2021-11-16 17:00 | 2021-02-11 | Y | [11 empty] | Linda Clifton |  |  | In Progress | 2021-03-19 | Mark Thomas | Eric Finley | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-11-16 17:00 |  | INPR | 2022-01-19 08:00 |  | 250000 |  |  |  | Jeff Jung |  |  | Prioritized | [5 empty] | Santa Rosa | Sonoma | 38.5527 | -122.7132 |  | ML | UG | [7 empty] | 637 | 35192292 | ECOP | R4BA | 2021-03-05 14:52
35217267 | Mendez, Angelica | 2021 | TITLE: SH - MARIPOSA 2102 LR 241564 | A0M6 | Scoped | ESTS |  | 0 | 4752 | 4752 | 0.9 | 0 | 0 | 4752 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-05-14 17:00 | 2021-02-18 | Y | 2021-03-31 | 2021-03-12 | [12 empty] | N/A |  |  | Courtney Faulkenberry | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-14 17:00 |  | N/A | 2021-06-28 08:00 | [8 empty] | Prioritized | [5 empty] | Mariposa | Mariposa | 37.4871 | -119.9619 | [10 empty] | 10 |  | CWSP | J91F | 2021-03-11 10:16
35217268 | Skarda, Travis Damian | 2021 | CWSP - BUCKS CREEK 1101 CB PH 1 | T3SQ | Scoped | UNSE |  | 0 | 1056 | 1056 | 0.2 | 0 | 0 | 0 | 0 | 1056 | 0.2 | 0 | 0 | 0 | 453 | 0.085795 | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [13 empty] | In Progress | 2021-05-07 | REY | Eric Finley |  | 2021-04-22 | [10 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 150000 | 145304.2 | [5 empty] | Prioritized | [5 empty] | Belden | Plumas | 0 | 0 | [10 empty] | 11 | 35217268 | CWSP | J91F | 2021-03-03 12:30
35217269 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | P3D5 | Scoped | UNSE |  | 0 | 2270 | 2270 | 0.42992 | 0 | 0 | 0 | 0 | 2270 | 0.42992 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-07-23 17:00 | 2021-04-30 | N | [14 empty] | In Progress |  | Mark Thomas | Joe Waller | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42992 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-23 17:00 |  | N/A | 2021-08-17 08:00 | [14 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | 8 | 35217269 | CWSP | P3D5 | 2021-03-11 10:39
35217270 | Donovan, Patrick | 2021 | CWSP - KONOCTI 1102 LR 965078 PH1 | P3D5 | Scoped | ESTS |  | 0 | 2904 | 2904 | 0.55 | 0 | 0 | 0 | 0 | 2904 | 0.55 | 0 | 0 | 0 | 2516 | 0.47652 | HB | 08W | SH | 2021-06-30 | 2021-04-30 | N | 2021-06-30 | [13 empty] | In Progress |  | Mark Thomas | Joe Waller | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 |  | 316666 | 31399.3 | [5 empty] | Prioritized | [5 empty] | Kelseyville | Lake | 38.9301 | -122.7429 | [10 empty] | 9 | 35217270 | CWSP | P3D5 | 2021-03-11 10:40
35217271 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | P3D5 | Scoped | UNSE |  | 8131 | 0 | 8131 | 1.54 | 0 | 0 | 0 | 0 | 8131 | 1.54 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [14 empty] | In Progress |  | Out to Bid | Joe Waller | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.54 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35217271 | CWSP | P3D5 | 2021-03-11 10:40
35217272 | Skarda, Travis Damian | 2021 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | T3SQ | Scoped | UNSE |  | 1584 | 0 | 1584 | 0.3 | 0 | 0 | 0 | 0 | 1584 | 0.3 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [13 empty] | In Progress |  | Tetratech | Courtney Faulkenberry | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 150000 | [12 empty] | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | 7 | 35217272 | CWSP | J91F | 2021-03-04 09:51
35217273 | Donovan, Patrick | 2021 | SH - UPPER LAKE 1101 CB | P3D5 | Scoped | UNSE |  | 0 | 5702.4 | 5702.4 | 1.08 | 0 | 0 | 0 | 0 | 5702.4 | 1.08 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-10-14 17:00 |  | N | [14 empty] | In Progress | 2021-03-15 | Mark Thomas | Joe Waller | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.08 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-10-14 17:00 |  | N/A | 2021-11-15 08:00 |  | 500000 | 30132.8 | [5 empty] | Prioritized | [5 empty] | Upper Lake | Lake | 39.353 | -122.7722 | [10 empty] | 6 |  | CWSP | AXYX | 2021-03-11 16:51
35219093 | Nguyen, My-Linh | 2021 | CWSP - TIDEWATER 210614072 PH 1.1 | M1NO | Scoped | UNSE |  | 6019 | 0 | 6019 | 1.14 | 0 | 0 | 0 | 0 | 6019 | 1.14 | 0 | 0 | 0 |  |  | DI | 08W | SH |  | 2021-02-26 | Y | [14 empty] | In Progress |  | Towill | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.14 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 350000 | [12 empty] | Concord | Contra Costa | 37.9632 | -121.9407 | [10 empty] | 18 | 35219093 | CWSP | EDW9 | 2021-03-11 12:49
35219096 | Nguyen, My-Linh | 2021 | CWSP - KIRKER 2104442850 PH 1.1 | M1NO | Scoped | UNSE |  | 8817.6 | 0 | 8817.6 | 1.67 | 0 | 0 | 0 | 0 | 8818 | 1.6701 | 0 | 0 | -7.5758e-05 |  |  | DI | 08W | SH |  | 2021-02-26 | Y | [14 empty] | In Progress |  | Towill | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.67 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 500000 | 7818.8 | [11 empty] | Pittsburg | Contra Costa | 37.9907 | -121.896 | [10 empty] | 21 | 35219096 | CWSP | EDW9 | 2021-03-11 12:49
35219097 | Pantoja-Martinez, Jaime | 2021 | CWSP - COARSEGOLD 2104CB PH 1.1 | J1PE | Scoped | ESTS |  | 0 | 12473 | 12473 | 2.3623 | 0 | 0 | 12473 | 2.3623 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-06-02 17:00 | 2021-02-26 | Y | 2021-04-30 | 2021-03-31 | [9 empty] | John Ketcherside |  |  | N/A |  | Internal | Courtney Faulkenberry | [12 empty] | Contract | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3623 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-02 17:00 |  | INPR | 2021-07-13 08:00 |  | 275000 | 2096158.8 |  |  | Tom Yang | [8 empty] | Coarsegold | Madera | 37.2276 | -119.6896 |  | ML | OH | [7 empty] | 22 | 35219097 | CWSP | J1PE | 2021-03-11 15:59
35219098 | Eagar, Josh | 2021 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | J1E1 | Scoped | UNSE |  | 0 | 3774 | 3774 | 0.71477 | 0 | 0 | 3774 | 0.71477 | 0 | 0 | 0 | 0 | 0 | 3709 | 0.70246 | HB | 08W | SH | 2021-09-13 17:00 | 2021-02-18 | Y | 2021-04-30 | 2021-04-30 | [12 empty] | N/A |  | On hold | Raul Rubio | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71477 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-09-13 17:00 |  | N/A | 2021-10-15 08:00 |  | 475000 | [6 empty] | Prioritized | [5 empty] | Middletown | Lake | 38.7514 | -122.6117 | [10 empty] | 23 | 35219098 | CWSP | AXYX | 2021-03-11 16:54
35219260 | Skarda, Travis Damian | 2021 | CWSP - WYANDOTTE 110932586 PH 1.1 | T3SQ | Scoped | ESTS |  | 0 | 4224 | 4224 | 0.8 | 0 | 0 | 4224 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2021-03-31 | 2021-02-26 | Y | 2021-03-31 | 2021-04-02 | [28 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Feather Falls | Butte | 39.4631 | -121.5149 | [10 empty] | 29 | 35219260 | CWSP | EDW9 | 2021-03-12 09:13
35219266 | Mendez, Angelica | 2021 | CWSP - MARIPOSA 2102CB PH 1 | A0M6 | Scoped | ESTS |  | 0 | 13713 | 13713 | 2.5972 | 0 | 0 | 13713 | 2.5972 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-05-17 17:00 | 2021-02-22 | Y | 2021-03-31 | 2021-03-31 | [12 empty] | N/A | 2021-03-31 | internal | Courtney Faulkenberry | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5972 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-17 17:00 |  | N/A | 2021-06-09 08:00 | [14 empty] | Mariposa | Mariposa | 37.5061 | -120.0049 | [10 empty] | 35 | 35219266 | CWSP | J91F | 2021-03-11 10:28
35219268 | Mendez, Angelica | 2021 | CWSP - MARIPOSA 210197142 PH 1 | A0M6 | Scoped | ESTS |  | 0 | 8553.6 | 8553.6 | 1.62 | 0 | 0 | 8554 | 1.6201 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | YO | 08W | SH | 2021-08-06 17:00 | 2021-02-08 | Y | 2021-03-31 | 2021-03-31 | [10 empty] | 2021-04-19 |  | In Progress | 2021-03-12 | Internal | Courtney Faulkenberry |  | 2021-04-19 | [10 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.62 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-06 17:00 |  |  | 2021-08-31 08:00 | [8 empty] | Prioritized | [5 empty] | Mariposa | Mariposa | 37.5066 | -120.0082 | [10 empty] | 36 | 35219268 | CWSP | EDW9 | 2021-03-11 10:06
35219272 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1101481876 | P3D5 | Scoped | ESTS |  | 0 | 4857.6 | 4857.6 | 0.92 | 0 | 0 | 4857.6 | 0.92 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-02-26 | Y | 2021-04-30 | 2021-04-16 | [28 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 |  | 950000 | [6 empty] | Prioritized | [5 empty] | Middletown | Lake | 38.7628 | -122.6133 | [10 empty] | 38 |  | CWSP | EDW9 | 2021-03-12 09:14
35219273 | Hernandez, Michael Donald James | 2021 | CWSP - VOLTA 110149742 | M5HF | Scoped | ADER |  | 0 | 15470 | 15470 | 2.9299 | 0 | 0 | 15470 | 2.9299 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2021-07-01 17:00 | 2021-02-26 | Y | 2021-03-31 | 2021-03-12 | [12 empty] | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9299 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-01 17:00 |  | N/A | 2021-07-26 08:00 | [8 empty] | Prioritized | [5 empty] | Manton | Tehama | 40.4305 | -121.8716 | [10 empty] | 39 |  | CWSP | EDW9 | 2021-03-12 09:14
35219280 | Donovan, Patrick | 2021 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | P3D5 | Scoped | UNSE |  | 0 | 8870 | 8870 | 1.6799 | 0 | 0 | 8870 | 1.6799 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | 2021-04-30 | 2021-04-30 | [28 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6799 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 |  | 475000 | [6 empty] | Prioritized | [5 empty] | Potter Valley | Mendocino | 39.362 | -123.1283 | [10 empty] | 43 | 35219280 | CWSP | P3D5 | 2021-03-11 10:42
35219281 | Kringler, Jeff L | 2021 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | J6KF | Scoped | UNSE |  | 13200 | 0 | 13200 | 2.5 | 0 | 0 | 0 | 0 | 13200 | 2.5 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-14 17:00 | 2021-06-01 | N | [14 empty] | In Progress |  | REY | Eric Finley | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 |  | 316666 |  |  |  | Sheena Mital | [8 empty] | Cool | El Dorado | 38.8983 | -120.9827 | [10 empty] | 45 | 35219281 | CWSP | J91F | 2021-03-11 10:09
35219286 | Mccabe, Patrick James |  | CWSP - DESCHUTES 11049718 PH1.1 | PJMW | Scoped | UNSE |  | 0 | 18241 | 18241 | 3.4547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4547 |  |  | NV | 08W | SH | [39 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4547 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [10 empty] | 48 | 35219286 | CWSP | AXYX | 2021-03-09 17:18
35219589 | Hernandez, Michael Donald James | 2021 | CWSP - WILDWOOD 11011454 | M5HF | Scoped | UNSE |  | 0 | 13622.4 | 13622.4 | 2.58 | 0 | 0 | 0 | 0 | 13622 | 2.5799 | 0 | 0 | 7.5758e-05 |  |  | NV | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.58 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Platina | Shasta | 40.3595 | -122.8928 | [10 empty] | 52 |  | CWSP | J91F | 2021-03-11 09:28
35220895 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | P3D5 | Scoped | UNSE |  | 10190 | 1162 | 11352 | 2.15 | 0 | 0 | 1162 | 0.22008 | 10190 | 1.9299 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [14 empty] | In Progress |  | Out to Bid | Joe Waller | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.15 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7569 | -122.607 | [10 empty] | 14 | 35220895 | CWSP | P3D5 | 2021-03-11 10:42
35220896 | Donovan, Patrick |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | P3D5 | Scoped | UNSE |  | 1478 | 0 | 1478 | 0.27992 | 0 | 0 | 0 | 0 | 1478 | 0.27992 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [14 empty] | In Progress |  | Out to Bid | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27992 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7569 | -122.607 | [10 empty] | 14 | 35220896 | CWSP | P3D5 | 2021-03-05 11:42
35222045 | Donovan, Patrick |  | SH - MIDDLTOWN 1103 - LR 830 PH4 | P3D5 | Scoped | UNSE |  | 0 | 4699 | 4699 | 0.88996 | 0 | 0 | 4699 | 0.88996 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88996 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Pope Valley | Napa | 38.7569 | -122.607 | [10 empty] | 14 | 35222045 | CWSP | P3D5 | 2021-03-05 11:43
35223024 | Eagar, Josh | 2021 | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | J1E1 | Scoped | UNSE |  | 11827.2 | 0 | 11827.2 | 2.24 | 0 | 0 | 11827 | 2.24 | 0 | 0 | 0 | 0 | 3.7879e-05 |  |  | NB | 08W | SH | 2021-06-08 17:00 |  | N | [14 empty] | In Progress | 2021-03-29 | Mark Thomas | Joe Waller | [12 empty] | Contract | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-08 17:00 |  | N/A | 2021-08-16 08:00 |  | 190000 | [6 empty] | Prioritized | [5 empty] | Pope Valley | Napa | 38.6152 | -122.4293 | [10 empty] | 279 | 35192284 | ECOP | J1E1 | 2021-03-11 13:59
35223026 | Eagar, Josh | 2021 | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | J1E1 | Scoped | UNSE |  | 9504 | 0 | 9504 | 1.8 | 0 | 0 | 9504 | 1.8 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2021-07-07 17:00 |  | N | [14 empty] | In Progress | 2021-03-29 | Mark Thomas | Joe Waller | [12 empty] | Contract | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-07 17:00 |  | N/A | 2021-08-17 08:00 |  | 190000 | [6 empty] | Prioritized | [5 empty] | Pope Valley | Napa | 38.6152 | -122.4293 | [10 empty] | 279 | 35192284 | ECOP | J1E1 | 2021-03-11 13:59
35223027 | Eagar, Josh | 2021 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | J1E1 | Scoped | ESTS |  | 0 | 10190 | 10190 | 1.9299 | 0 | 0 | 10190 | 1.9299 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2021-05-21 17:00 | 2021-02-26 | Y | 2021-04-30 | 2021-04-30 | [12 empty] | N/A | [15 empty] | Contract | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9299 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-21 17:00 |  | N/A | 2021-08-17 08:00 |  | 190000 | 34848.7 | [5 empty] | Prioritized | [5 empty] | Pope Valley | Napa | 38.6152 | -122.4293 | [10 empty] | 279 | 35192284 | ECOP | EDW9 | 2021-03-12 09:14
35223028 | Eagar, Josh | 2021 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | J1E1 | Scoped | ESTS |  | 0 | 8026 | 8026 | 1.5201 | 0 | 0 | 8026 | 1.5201 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2021-04-30 | 2021-03-04 | Y | 2021-04-30 | 2021-04-30 | [12 empty] | N/A | [15 empty] | Contract | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5201 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [9 empty] | Prioritized | [5 empty] | Pope Valley | Napa | 38.6152 | -122.4293 | [10 empty] | 279 | 35192284 | ECOP | J1E1 | 2021-03-11 14:16
35223030 | Skarda, Travis Damian | 2021 | PSPS - BANGOR 1101 CB - MICROGRID | T3SQ | Scoped | UNSE |  | 3009.6 | 0 | 3009.6 | 0.57 | 0 | 0 | 0 | 0 | 3010 | 0.57008 | 0 | 0 | -7.5758e-05 |  |  | NV | 08W | SH | [39 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 950000 | [12 empty] | Bangor | Butte | 39.3878 | -121.4038 | [10 empty] | 355 |  | PSPS | J91F | 2021-03-11 09:29
35223036 | Kringler, Jeff L | 2021 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | J6KF | Scoped | UNSE |  | 264 | 0 | 264 | 0.05 | 0 | 0 | 0 | 0 | 264 | 0.05 | 0 | 0 | 0 |  |  | SI | 08W | SH |  | 2021-06-01 | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 500000 | [12 empty] | Grass Valley | Nevada | 39.2376 | -121.0592 | [10 empty] | 2134 |  | PSPS | J6KF | 2021-03-11 09:59
35223037 | Pantoja-Martinez, Jaime | 2021 | PSPS - OAKHURST 1101 - OAKHURST | J1PE | Scoped | ESTS |  | 105.6 | 0 | 105.6 | 0.02 | 0 | 0 | 106 | 0.020076 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | YO | 08W | SH | 2021-03-31 | 2021-02-26 | Y | 2021-03-31 | 2021-03-31 | [9 empty] | John Ketcherside |  |  | N/A |  |  | Courtney Faulkenberry | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | INPR |  |  | 500000 | 280281.3 | [11 empty] | Oakhurst | Madera | 37.3227 | -119.6344 |  | ML | UG | [7 empty] | 847 |  | PSPS | J1PE | 2021-03-11 15:59
35223039 | Skarda, Travis Damian | 2021 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | T3SQ | Scoped | UNSE |  | 4065.6 | 0 | 4065.6 | 0.77 | 0 | 0 | 0 | 0 | 4066 | 0.77008 | 0 | 0 | -7.5758e-05 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [13 empty] | In Progress |  | PG&E | Eric Finley | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 950000 | [12 empty] | Oroville | Butte | 39.4738 | -121.5307 | [10 empty] | 218 |  | PSPS | J91F | 2021-03-11 10:10
35223615 | Donovan, Patrick | 2021 | ECOP - LAS GALLINAS A 1105 PH 2 | P3D5 | Scoped | UNSE |  | 8606.4 | 0 | 8606.4 | 1.63 | 0 | 0 | 0 | 0 | 8606 | 1.6299 | 0 | 0 | 7.5758e-05 |  |  | NB | 08W | SH | 2021-08-20 17:00 | 2021-04-30 | N | [14 empty] | In Progress |  | Tetratech | Courtney Faulkenberry | [12 empty] | Contract | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.63 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-20 17:00 |  | N/A | 2021-09-14 08:00 |  | 312500 | 1320.1 | [11 empty] | San Rafael | Marin | 38.0443 | -122.6155 | [10 empty] | 215 | 35191319 | ECOP | P3D5 | 2021-03-05 11:43
35224321 | Hernandez, Michael Donald James | 2021 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | M5HF | Scoped | ESTS |  | 0 | 12302.4 | 12302.4 | 2.33 | 0 | 0 | 0 | 0 | 12302 | 2.3299 | 0 | 0 | 7.5758e-05 |  |  | NV | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.33 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Platina | Shasta | 40.3595 | -122.8928 | [10 empty] | 52 | 35224321 | CWSP | J91F | 2021-03-11 09:28
35224712 | Skarda, Travis Damian | 2021 | CWSP - BUCKS CREEK 1101 CB PH 2 | T3SQ | Scoped | UNSE |  | 9134.4 | 0 | 9134.4 | 1.73 | 0 | 0 | 0 | 0 | 9134 | 1.7299 | 0 | 0 | 7.5758e-05 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [13 empty] | In Progress | 2021-05-07 | REY | Eric Finley | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.73 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 400000 | 390621.4 | [5 empty] | Prioritized | [5 empty] | Belden | Plumas | 0 | 0 | [10 empty] | 11 | 35217268 | CWSP | T3SQ | 2021-03-03 09:26
35224713 | Skarda, Travis Damian | 2021 | CWSP - BUCKS CREEK 1101 CB PH 3 | T3SQ | Scoped | UNSE |  | 9662.4 | 0 | 9662.4 | 1.83 | 0 | 0 | 0 | 0 | 9662 | 1.8299 | 0 | 0 | 7.5758e-05 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [13 empty] | In Progress | 2021-05-07 | REY | Eric Finley | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.83 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 400000 | 389909.1 | [5 empty] | Prioritized | [5 empty] | Belden | Plumas | 0 | 0 | [10 empty] | 11 | 35217268 | CWSP | T3SQ | 2021-03-03 09:26
35225589 | Donovan, Patrick | 2021 | CWSP - KONOCTI 1102 LR 965078 PH2 | P3D5 | Scoped | UNSE |  | 0 | 4699.2 | 4699.2 | 0.89 | 0 | 0 | 0 | 0 | 4699 | 0.88996 | 0 | 0 | 3.7879e-05 |  |  | HB | 08W | SH | 2021-06-30 | 2021-04-30 | N | 2021-06-30 | [13 empty] | In Progress |  |  | Joe Waller | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.89 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 |  | 316666 | 14484.8 | [5 empty] | Prioritized | [5 empty] | Kelseyville | Lake | 38.93 | -122.7428 | [10 empty] | 9 | 35217270 | CWSP | P3D5 | 2021-03-05 11:44
35225591 | Donovan, Patrick | 2021 | CWSP - KONOCTI 1102 LR 965078 PH3 | P3D5 | Scoped | ESTS |  | 0 | 4224 | 4224 | 0.8 | 0 | 0 | 0 | 0 | 4224 | 0.8 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | 2021-03-31 | 2021-03-12 | [12 empty] | In Progress |  |  | Joe Waller | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 |  | 316666 | 14378.3 | [5 empty] | Prioritized | [5 empty] | Kelseyville | Lake | 38.93 | -122.7428 | [10 empty] | 9 | 35217270 | CWSP | P3D5 | 2021-03-11 10:44
35225593 | Nguyen, My-Linh | 2021 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | M1NO | Scoped | ADER |  | 0 | 5544 | 5544 | 1.05 | 0 | 0 | 5544 | 1.05 | 0 | 0 | 0 | 0 | 0 |  |  | DI | 08W | SH | 2021-03-31 | 2021-02-26 | Y | 2021-03-31 | 2021-03-31 | [12 empty] | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.05 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 400000 | 44099.7 | [5 empty] | Prioritized | [5 empty] | Clayton | Contra Costa | 37.8879 | -121.8676 | [10 empty] | 377 | 35192280 | ECOP | EDW9 | 2021-03-11 12:49
35225594 | Barron, Raul Angelo | 2021 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | R4BA | Scoped | UNSE |  | 2481.6 | 0 | 2481.6 | 0.47 | 0 | 0 | 0 | 0 | 2482 | 0.47008 | 0 | 0 | -7.5758e-05 |  |  | SO | 08W | SH | 2021-11-02 17:00 | 2021-02-11 | Y | [11 empty] | Linda Clifton |  |  | In Progress | 2021-03-19 | Mark Thomas | Eric Finley | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-11-02 17:00 |  | INPR | 2022-01-05 08:00 |  | 250000 |  |  |  | Jeff Jung |  |  | Prioritized | [5 empty] | Santa Rosa | Sonoma | 38.549 | -122.72 |  | ML | UG | [7 empty] | 637 | 35192292 | ECOP | R4BA | 2021-03-05 14:52
35225595 | Barron, Raul Angelo | 2021 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | R4BA | Scoped | UNSE |  | 0 | 5860 | 5860 | 1.1098 | 0 | 0 | 5860 | 1.1098 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2021-08-20 17:00 | 2021-02-11 | Y | [11 empty] | Linda Clifton |  |  | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1098 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-20 17:00 |  | INPR | 2021-09-14 08:00 |  | 150000 |  |  |  | Jeff Jung |  |  | Prioritized | [5 empty] | Santa Rosa | Sonoma | 38.549 | -122.72 |  | TL | OH | [7 empty] | 637 | 35192292 | ECOP | R4BA | 2021-03-11 14:35
35225597 | Barron, Raul Angelo | 2021 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | R4BA | Scoped | ESTS |  | 0 | 3907.2 | 3907.2 | 0.74 | 0 | 0 | 3907 | 0.73996 | 0 | 0 | 0 | 0 | 3.7879e-05 |  |  | SO | 08W | SH | 2021-07-28 17:00 | 2021-02-11 | Y | 2021-04-30 | 2021-04-30 | [9 empty] | Linda Clifton |  |  | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.74 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-28 17:00 |  | INPR | 2021-08-20 08:00 |  | 150000 |  |  |  | Jeff Jung |  |  | Prioritized | [5 empty] | Santa Rosa | Sonoma | 38.549 | -122.72 |  | TL | OH | [7 empty] | 637 | 35192292 | ECOP | R4BA | 2021-03-11 14:34
35225598 | Barron, Raul Angelo | 2021 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | R4BA | Scoped | ESTS |  | 0 | 4857.6 | 4857.6 | 0.92 | 0 | 0 | 4858 | 0.92008 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | SO | 08W | SH | 2021-08-06 17:00 | 2021-02-11 | Y | 2021-04-30 | 2021-04-30 | [9 empty] | Linda Clifton |  |  | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-06 17:00 |  | INPR | 2021-08-31 08:00 |  | 150000 |  |  |  | Jeff Jung |  |  | Prioritized | [5 empty] | Santa Rosa | Sonoma | 38.549 | -122.72 |  | TL | OH | [7 empty] | 637 | 35192292 | ECOP | R4BA | 2021-03-11 14:34
35225825 | Ung, Mason |  | CWSP - DESCHUTES 11049718 PH2.1 | MXUA | Scoped | UNSE |  | 0 | 8217 | 8217 | 1.5562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5562 |  |  | NV | 08W | SH | [39 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5562 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [10 empty] | 48 | 35225825 | CWSP | AXYX | 2021-03-09 17:24
35226241 | Mendez, Angelica | 2021 | CWSP - MARIPOSA 210197142 PH 2 | A0M6 | Scoped | ESTS |  | 0 | 7920 | 7920 | 1.5 | 0 | 0 | 7920 | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-08-06 17:00 | 2021-02-08 | Y | 2021-03-31 | 2021-03-31 | [10 empty] | 2021-04-20 |  | In Progress | 2021-03-12 | Internal | Courtney Faulkenberry |  | 2021-04-20 | [10 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-06 17:00 |  | N/A | 2021-08-31 08:00 | [8 empty] | Prioritized | [5 empty] | Mariposa | Mariposa | 37.5066 | -120.0082 | [10 empty] | 36 | 35219268 | CWSP | EDW9 | 2021-03-11 10:06
35226621 | Donovan, Patrick | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | P3D5 | Scoped | UNSE |  | 8184 | 0 | 8184 | 1.55 | 0 | 0 | 0 | 0 | 8184 | 1.55 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-04-30 | N | 2021-06-30 | [29 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.55 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | 468 | 35192282 | ECOP | P3D5 | 2021-03-11 10:40
35226622 | Donovan, Patrick | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | P3D5 | Scoped | UNSE |  | 0 | 4013 | 4013 | 0.76004 | 0 | 0 | 4013 | 0.76004 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-03-31 | N | 2021-06-30 | [29 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.76004 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | 468 | 35192282 | ECOP | P3D5 | 2021-03-05 11:45
35226623 | Donovan, Patrick | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | P3D5 | Scoped | UNSE |  | 0 | 6072 | 6072 | 1.15 | 0 | 0 | 6072 | 1.15 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-03-31 | N | 2021-06-30 | [29 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.15 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | 468 | 35192282 | ECOP | P3D5 | 2021-03-05 11:45
35226624 | Donovan, Patrick | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | P3D5 | Scoped | UNSE |  | 0 | 7709 | 7709 | 1.46 | 0 | 0 | 7709 | 1.46 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 | 2021-03-31 | N | 2021-04-30 | [29 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.46 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | 468 | 35192282 | ECOP | P3D5 | 2021-03-05 11:45
35226627 | Skarda, Travis Damian | 2021 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | T3SQ | Scoped | UNSE |  | 0 | 1531.2 | 1531.2 | 0.29 | 0 | 0 | 1531 | 0.28996 | 0 | 0 | 0 | 0 | 3.7879e-05 |  |  | NV | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | 2021-04-02 | [12 empty] | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.29 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 150000 | [12 empty] | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | 7 | 35217272 | CWSP | T3SQ | 2021-03-11 10:12
35226628 | Skarda, Travis Damian | 2021 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | T3SQ | Scoped | UNSE |  | 4329.6 | 0 | 4329.6 | 0.82 | 0 | 0 | 0 | 0 | 4330 | 0.82008 | 0 | 0 | -7.5758e-05 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [13 empty] | In Progress |  | Tetratech | Courtney Faulkenberry | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 150000 | [12 empty] | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | 7 | 35217272 | CWSP | J91F | 2021-03-04 09:51
35226629 | Skarda, Travis Damian | 2021 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | T3SQ | Scoped | UNSE |  | 23760 | 0 | 23760 | 4.5 | 0 | 0 | 0 | 0 | 23760 | 4.5 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [13 empty] | In Progress |  | Tetratech | Courtney Faulkenberry | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 200000 | [12 empty] | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | 7 | 35217272 | CWSP | J91F | 2021-03-04 09:51
35226630 | Skarda, Travis Damian | 2021 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | T3SQ | Scoped | UNSE |  | 0 | 7603.2 | 7603.2 | 1.44 | 0 | 0 | 7608 | 1.4409 | 0 | 0 | 0 | 0 | -0.00090909 |  |  | NV | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | 2021-04-02 | [12 empty] | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.44 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 150000 | [12 empty] | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | 7 | 35217272 | CWSP | T3SQ | 2021-03-11 10:12
35226631 | Skarda, Travis Damian | 2021 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | T3SQ | Scoped | UNSE |  | 0 | 8131.2 | 8131.2 | 1.54 | 0 | 0 | 8131 | 1.54 | 0 | 0 | 0 | 0 | 3.7879e-05 |  |  | NV | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | 2021-04-02 | [12 empty] | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.54 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 150000 | [12 empty] | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | 7 | 35217272 | CWSP | T3SQ | 2021-03-11 10:12
35226632 | Donovan, Patrick | 2021 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | P3D5 | Scoped | UNSE |  | 792 | 0 | 792 | 0.15 | 0 | 0 | 0 | 0 | 792 | 0.15 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | 2021-04-30 | 2021-04-30 | [28 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 |  | 475000 | [6 empty] | Prioritized | [5 empty] | Potter Valley | Mendocino | 39.362 | -123.1283 | [10 empty] | 43 | 35219280 | CWSP | P3D5 | 2021-03-10 16:57
35226700 | Skarda, Travis Damian | 2021 | CWSP - WYANDOTTE 110932586 PH 1.2 | T3SQ | Scoped | UNSE |  | 3010 | 0 | 3010 | 0.57008 | 0 | 0 | 0 | 0 | 3010 | 0.57008 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [13 empty] | In Progress |  | PG&E | Eric Finley | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57008 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 650000 | [26 empty] | 29 | 35219260 | CWSP | J91F | 2021-03-04 09:59
35226798 | Hernandez, Michael Donald James | 2021 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | M5HF | Scoped | UNSE |  | 0 | 8395.2 | 8395.2 | 1.59 | 0 | 0 | 0 | 0 | 8395 | 1.59 | 0 | 0 | 3.7879e-05 |  |  | NV | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Platina | Shasta | 40.3595 | -122.8928 | [10 empty] | 52 | 35224321 | CWSP | J91F | 2021-03-11 09:30
35226799 | Hernandez, Michael Donald James | 2021 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | M5HF | Scoped | UNSE |  | 1003.2 | 0 | 1003.2 | 0.19 | 0 | 0 | 0 | 0 | 1003 | 0.18996 | 0 | 0 | 3.7879e-05 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Platina | Shasta | 40.3595 | -122.8928 | [10 empty] | 52 | 35224321 | CWSP | J91F | 2021-03-11 09:30
35226819 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | P3D5 | Scoped | UNSE |  | 0 | 10507 | 10507 | 1.99 | 0 | 0 | 0 | 0 | 10507 | 1.99 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-07-23 17:00 | 2021-04-30 | N | [30 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.99 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-23 17:00 |  | N/A | 2021-08-17 08:00 | [14 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | 8 | 35217269 | CWSP | P3D5 | 2021-03-05 11:46
35226845 | Pantoja-Martinez, Jaime | 2021 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | J1PE | Scoped | ESTS |  | 0 | 13833.6 | 13833.6 | 2.62 | 0 | 0 | 13834 | 2.6201 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | SI | 08W | SH | 2021-06-30 17:00 | 2021-02-26 | Y | 2021-04-30 | 2021-04-30 | [9 empty] | Jeanette Johnson |  |  | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.62 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-30 17:00 |  | INPR | 2021-07-23 08:00 |  | 450000 | 2311825 | [11 empty] | Placerville | El Dorado | 38.7201 | -120.861 |  | TL | OH | [7 empty] | 811 | 35192291 | ECOP | J1PE | 2021-03-11 15:59
35226846 | Kringler, Jeff L | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | J6KF | Scoped | ESTS |  | 0 | 9153 | 9153 | 1.7335 | 0 | 0 | 9153 | 1.7335 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-22 17:00 | 2021-02-18 | Y | 2021-04-30 | 2021-04-20 | [12 empty] | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7335 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-22 17:00 |  | N/A | 2021-07-15 08:00 |  | 70000 | 3054367.7 |  |  | Maxwell Muscarella |  |  | Prioritized |  |  | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062374 | PRE | J6KF | 2021-03-11 10:07
35226847 | Kringler, Jeff L | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | J6KF | Scoped | ESTS |  | 0 | 10475 | 10475 | 1.9839 | 0 | 0 | 10475 | 1.9839 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-22 17:00 | 2021-02-18 | Y | 2021-04-30 | 2021-04-20 | [12 empty] | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9839 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-22 17:00 |  | N/A | 2021-07-15 08:00 |  | 70000 | 3777833 |  |  | Maxwell Muscarella |  |  | Prioritized |  |  | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062374 | PRE | J6KF | 2021-03-11 10:07
35226848 | Barron, Raul Angelo | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | R4BA | Scoped | ESTS |  | 0 | 15153 | 15153 | 2.8699 | 0 | 0 | 15153 | 2.8699 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-11 17:00 | 2021-02-22 | Y | 2021-03-31 | 2021-03-26 | [9 empty] | Jeanette Johnson |  |  | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8699 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-11 17:00 |  | INPR | 2021-08-03 08:00 | [14 empty] | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062375 | PRE | J91F | 2021-03-11 10:21
35226849 | Barron, Raul Angelo | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | R4BA | Scoped | UNSE |  | 9398 | 0 | 9398 | 1.7799 | 0 | 0 | 0 | 0 | 9398 | 1.7799 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-08-27 17:00 | 2021-02-22 | Y | 2021-05-31 | [10 empty] | Jeanette Johnson |  |  | In Progress | 2021-04-12 | Mark Thomas | Eric Finley | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7799 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-27 17:00 |  | INPR | 2021-10-19 08:00 | [14 empty] | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062375 | PRE | R4BA | 2021-03-05 14:57
35226850 | Barron, Raul Angelo | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | R4BA | Scoped | ESTS |  | 0 | 9187 | 9187 | 1.74 | 0 | 0 | 9187 | 1.74 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-05-24 17:00 | 2021-02-22 | Y | 2021-04-30 | 2021-04-09 | [9 empty] | Jeanette Johnson |  |  | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-24 17:00 |  | INPR | 2021-06-22 08:00 | [14 empty] | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062375 | PRE | R4BA | 2021-03-11 14:33
35226851 | Barron, Raul Angelo | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | R4BA | Scoped | ESTS |  | 0 | 11563 | 11563 | 2.19 | 0 | 0 | 11563 | 2.19 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-05-24 17:00 | 2021-02-22 | Y | 2021-03-31 | 2021-03-12 | [9 empty] | Jeanette Johnson |  |  | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.19 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-24 17:00 |  | INPR | 2021-06-25 08:00 | [14 empty] | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062375 | PRE | J91F | 2021-03-11 10:20
35226852 | Kringler, Jeff L | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | J6KF | Scoped | ESTS |  | 0 | 13164 | 13164 | 2.4932 | 0 | 0 | 13164 | 2.4932 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-22 17:00 | 2021-03-01 | Y | 2021-04-16 | 2021-04-16 | [12 empty] | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4932 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-22 17:00 |  | N/A | 2021-07-15 08:00 |  | 70000 | 7914215.7 |  |  | Rory McDermott |  |  | Prioritized |  |  | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 159 | 35062376 | PRE | J6KF | 2021-03-11 10:07
35226853 | Kringler, Jeff L | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | J6KF | Scoped | ESTS |  | 0 | 14807 | 14807 | 2.8044 | 0 | 0 | 14807 | 2.8044 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-22 17:00 | 2021-03-01 | Y | 2021-04-30 | 2021-04-16 | [12 empty] | N/A | 2021-04-19 | Mark Thomas | Eric Finley | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8044 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-22 17:00 |  | N/A | 2021-07-15 08:00 |  | 70000 | 5739276.8 |  |  | Rory McDermott |  |  | Prioritized |  |  | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 159 | 35062376 | PRE | J6KF | 2021-03-11 10:06
35226854 | Kringler, Jeff L | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | J6KF | Scoped | ESTS |  | 0 | 5438.4 | 5438.4 | 1.03 | 0 | 0 | 5438 | 1.0299 | 0 | 0 | 0 | 0 | 7.5758e-05 |  |  | SI | 08W | SH | 2021-06-22 17:00 | 2021-03-01 | Y | 2021-04-16 | 2021-04-16 | [12 empty] | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.03 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-22 17:00 |  | N/A | 2021-07-15 08:00 |  | 70000 | 2069574.7 |  |  | Rory McDermott |  |  | Prioritized |  |  | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 159 | 35062376 | PRE | J6KF | 2021-03-11 10:06
35226856 | Kringler, Jeff L | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | J6KF | Scoped | ESTS |  | 0 | 10262 | 10262 | 1.9436 | 0 | 0 | 10262 | 1.9436 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-22 17:00 | 2021-03-01 | Y | 2021-04-16 | 2021-04-16 | [12 empty] | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9436 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-22 17:00 |  | N/A | 2021-07-15 08:00 |  | 70000 | 8797079.2 |  |  | Rory McDermott |  |  | Prioritized |  |  | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 159 | 35062376 | PRE | J6KF | 2021-03-11 10:06
35226857 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | J1E1 | Scoped | UNSE |  | 4488 | 0 | 4488 | 0.85 | 0 | 0 | 0 | 0 | 4488 | 0.85 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [16 empty] | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 155000 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174478 | ECOP | J1E1 | 2021-03-11 13:59
35226858 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | J1E1 | Scoped | UNSE |  | 0 | 2006.4 | 2006.4 | 0.38 | 0 | 0 | 0 | 0 | 2006 | 0.37992 | 0 | 0 | 7.5758e-05 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 155000 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174478 | ECOP | J1E1 | 2021-02-26 12:06
35226859 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | J1E1 | Scoped | UNSE |  | 0 | 4646.4 | 4646.4 | 0.88 | 0 | 0 | 0 | 0 | 4646 | 0.87992 | 0 | 0 | 7.5758e-05 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 155000 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174478 | ECOP | J1E1 | 2021-02-26 12:06
35226861 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | J1E1 | Scoped | UNSE |  | 0 | 3484.8 | 3484.8 | 0.66 | 0 | 0 | 0 | 0 | 3485 | 0.66004 | 0 | 0 | -3.7879e-05 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 155000 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174478 | ECOP | J1E1 | 2021-02-26 12:06
35226862 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | J1E1 | Scoped | UNSE |  | 0 | 3062.4 | 3062.4 | 0.58 | 0 | 0 | 0 | 0 | 3062 | 0.57992 | 0 | 0 | 7.5758e-05 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 155000 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174478 | ECOP | J1E1 | 2021-02-26 12:06
35226863 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | J1E1 | Scoped | UNSE |  | 0 | 2786 | 2786 | 0.52765 | 0 | 0 | 0 | 0 | 2786 | 0.52765 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 |  | N | 2021-04-30 | [13 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52765 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP | J1E1 | 2021-03-11 14:16
35226864 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | J1E1 | Scoped | UNSE |  | 0 | 1724 | 1724 | 0.32652 | 0 | 0 | 0 | 0 | 1724 | 0.32652 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 |  | N | 2021-04-30 | [13 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32652 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP | J1E1 | 2021-03-11 14:16
35226865 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | J1E1 | Scoped | UNSE |  | 0 | 1243 | 1243 | 0.23542 | 0 | 0 | 0 | 0 | 1243 | 0.23542 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 |  | N | 2021-04-30 | [13 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23542 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP | J1E1 | 2021-03-11 14:16
35226866 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | J1E1 | Scoped | UNSE |  | 0 | 2736 | 2736 | 0.51818 | 0 | 0 | 0 | 0 | 2736 | 0.51818 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 |  | N | 2021-04-30 | [13 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51818 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP | J1E1 | 2021-03-11 14:17
35226870 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | J1E1 | Scoped | UNSE |  | 0 | 2215 | 2215 | 0.41951 | 0 | 0 | 0 | 0 | 2215 | 0.41951 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 |  | N | 2021-04-30 | [13 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41951 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP | J1E1 | 2021-03-11 14:17
35226871 | Lorz, Jesse | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | JDLM | Scoped | UNSE |  | 6124 | 420 | 6544 | 1.2394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2394 |  |  | HB | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | [16 empty] | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2394 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP | AXYX | 2021-03-01 13:46
35226872 | Lorz, Jesse | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | JDLM | Scoped | UNSE |  | 2552 | 1168 | 3720 | 0.70455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70455 |  |  | HB | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | [16 empty] | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70455 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP | AXYX | 2021-03-01 13:46
35226873 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | J1E1 | Scoped | UNSE |  | 5488 | 0 | 5488 | 1.0394 | 0 | 0 | 0 | 0 | 5488 | 1.0394 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [16 empty] | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0394 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP | J1E1 | 2021-03-09 14:27
35226878 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | J1E1 | Scoped | UNSE |  | 3109 | 0 | 3109 | 0.58883 | 0 | 0 | 0 | 0 | 3109 | 0.58883 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [16 empty] | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58883 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP | J1E1 | 2021-03-09 14:27
35227001 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | J1E1 | Scoped | UNSE |  | 3809 | 0 | 3809 | 0.7214 | 0 | 0 | 0 | 0 | 3809 | 0.7214 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [16 empty] | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7214 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP | J1E1 | 2021-03-09 14:27
35227002 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | J1E1 | Scoped | UNSE |  | 2286 | 0 | 2286 | 0.43295 | 0 | 0 | 0 | 0 | 2286 | 0.43295 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [16 empty] | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43295 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP | J1E1 | 2021-03-09 14:27
35227003 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | J1E1 | Scoped | UNSE |  | 3067 | 0 | 3067 | 0.58087 | 0 | 0 | 0 | 0 | 3067 | 0.58087 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [16 empty] | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58087 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP | J1E1 | 2021-03-09 14:27
35227004 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | J1E1 | Scoped | UNSE |  | 1839 | 0 | 1839 | 0.3483 | 0 | 0 | 0 | 0 | 1839 | 0.3483 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [16 empty] | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3483 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP | J1E1 | 2021-03-09 14:28
35227007 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | J1E1 | Scoped | UNSE |  | 15183 | 0 | 15183 | 2.8756 | 0 | 0 | 0 | 0 | 15183 | 2.8756 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [16 empty] | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8756 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 118750 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174501 | ECOP | J1E1 | 2021-02-26 12:06
35227010 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | J1E1 | Scoped | UNSE |  | 0 | 834 | 834 | 0.15795 | 0 | 0 | 0 | 0 | 834 | 0.15795 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15795 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 118750 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174501 | ECOP | J1E1 | 2021-02-26 13:16
35227013 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 | J1E1 | Scoped | UNSE |  | 0 | 168 | 168 | 0.031818 | 0 | 0 | 0 | 0 | 168 | 0.031818 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.031818 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 118750 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174501 | ECOP | J1E1 | 2021-02-26 13:17
35227015 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | J1E1 | Scoped | UNSE |  | 0 | 5106 | 5106 | 0.96705 | 0 | 0 | 0 | 0 | 5106 | 0.96705 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-04-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.96705 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 118750 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174501 | ECOP | J1E1 | 2021-02-26 12:06
35227018 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | J1E1 | Scoped | UNSE |  | 0 | 6312 | 6312 | 1.1955 | 0 | 0 | 0 | 0 | 6312 | 1.1955 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1955 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 118750 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174501 | ECOP | J1E1 | 2021-03-11 14:00
35227021 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | J1E1 | Scoped | UNSE |  | 0 | 1144 | 1144 | 0.21667 | 0 | 0 | 0 | 0 | 1144 | 0.21667 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21667 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 118750 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174501 | ECOP | J1E1 | 2021-02-26 13:18
35227025 | Eagar, Josh | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | J1E1 | Scoped | UNSE |  | 2900 | 0 | 2900 | 0.54924 | 0 | 0 | 0 | 0 | 2900 | 0.54924 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [16 empty] | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.54924 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 118750 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174501 | ECOP | AXYX | 2021-03-04 09:07
35227027 | Donovan, Patrick | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | P3D5 | Scoped | UNSE |  | 0 | 4171 | 4171 | 0.78996 | 0 | 0 | 4171 | 0.78996 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | 2021-04-30 | [29 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78996 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | 468 | 35192281 | ECOP | P3D5 | 2021-03-05 11:46
35227028 | Donovan, Patrick | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | P3D5 | Scoped | UNSE |  | 0 | 3168 | 3168 | 0.6 | 0 | 0 | 3168 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-03-31 | N | 2021-06-30 | [29 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | 468 | 35192281 | ECOP | P3D5 | 2021-03-05 11:46
35227029 | Donovan, Patrick | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | P3D5 | Scoped | UNSE |  | 0 | 5491 | 5491 | 1.04 | 0 | 0 | 5491 | 1.04 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-03-31 | N | 2021-06-30 | [29 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.04 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | 468 | 35192281 | ECOP | P3D5 | 2021-03-05 11:47
35227030 | Donovan, Patrick | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | P3D5 | Scoped | UNSE |  | 7287 | 1796 | 9083 | 1.7203 | 0 | 0 | 1796 | 0.34015 | 7287 | 1.3801 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-03-31 | N | 2021-06-30 | [13 empty] | In Progress |  | Confirming scope | Joe Waller | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7203 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | 468 | 35192281 | ECOP | P3D5 | 2021-03-05 11:47
35227031 | Donovan, Patrick | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | P3D5 | Scoped | UNSE |  | 8184 | 2534 | 10718 | 2.0299 | 0 | 0 | 2534 | 0.47992 | 8184 | 1.55 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-03-31 | N | 2021-06-30 | [13 empty] | In Progress |  | Confirming scope | Joe Waller | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0299 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | 468 | 35192281 | ECOP | P3D5 | 2021-03-05 11:47
35227032 | Eagar, Josh | 2021 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | J1E1 | Scoped | UNSE |  | 0 | 4600 | 4600 | 0.87121 | 0 | 0 | 0 | 0 | 4600 | 0.87121 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2022-01-17 17:00 |  | N | [14 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87121 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-01-17 17:00 |  | N/A | 2022-02-04 08:00 |  | 237833 | [12 empty] | Napa | Napa | 38.433 | -122.4021 | [10 empty] | 951 | 35191937 | ECOP | J1E1 | 2021-03-11 14:18
35227033 | Eagar, Josh | 2021 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | J1E1 | Scoped | UNSE |  | 0 | 6936 | 6936 | 1.3136 | 0 | 0 | 0 | 0 | 6936 | 1.3136 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2022-01-17 17:00 |  | N | [14 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3136 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-01-17 17:00 |  | N/A | 2022-02-04 08:00 |  | 237833 | [12 empty] | Napa | Napa | 38.433 | -122.4021 | [10 empty] | 951 | 35191937 | ECOP | J1E1 | 2021-02-26 12:07
35227160 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | P3D5 | Scoped | UNSE |  | 6970 | 0 | 6970 | 1.3201 | 0 | 0 | 0 | 0 | 6970 | 1.3201 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-08-17 17:00 | 2021-04-30 | N | [14 empty] | In Progress |  | Confirming scope | Joe Waller | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3201 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-17 17:00 |  | N/A | 2021-09-09 08:00 | [14 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | 8 | 35217269 | CWSP | P3D5 | 2021-03-05 11:48
35227161 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | P3D5 | Scoped | UNSE |  | 0 | 3907 | 3907 | 0.73996 | 0 | 0 | 0 | 0 | 3907 | 0.73996 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-07-23 17:00 | 2021-04-30 | N | [30 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73996 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-23 17:00 |  | N/A | 2021-08-17 08:00 | [14 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | 8 | 35217269 | CWSP | P3D5 | 2021-03-05 11:48
35227162 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | P3D5 | Scoped | UNSE |  | 1690 | 0 | 1690 | 0.32008 | 0 | 0 | 0 | 0 | 1690 | 0.32008 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-07-23 17:00 | 2021-04-30 | N | [14 empty] | In Progress |  | Confirming scope | Joe Waller | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32008 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-23 17:00 |  | N/A | 2021-08-17 08:00 | [14 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | 8 | 35217269 | CWSP | P3D5 | 2021-03-05 11:49
35227163 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | P3D5 | Scoped | UNSE |  | 0 | 2429 | 2429 | 0.46004 | 0 | 0 | 0 | 0 | 2429 | 0.46004 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-07-23 17:00 | 2021-04-30 | N | [30 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46004 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-23 17:00 |  | N/A | 2021-08-17 08:00 | [14 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | 8 | 35217269 | CWSP | P3D5 | 2021-03-05 11:49
35227164 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | P3D5 | Scoped | UNSE |  | 0 | 4752 | 4752 | 0.9 | 0 | 0 | 0 | 0 | 4752 | 0.9 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-07-23 17:00 | 2021-04-30 | N | [30 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-23 17:00 |  | N/A | 2021-08-17 08:00 | [14 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | 8 | 35217269 | CWSP | P3D5 | 2021-03-05 11:49
35227165 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | P3D5 | Scoped | UNSE |  | 5333 | 0 | 5333 | 1.01 | 0 | 0 | 0 | 0 | 5333 | 1.01 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [14 empty] | In Progress |  | Out to Bid | Joe Waller | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.01 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35220896 | CWSP | P3D5 | 2021-03-05 11:50
35227167 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | P3D5 | Scoped | UNSE |  | 9504 | 0 | 9504 | 1.8 | 0 | 0 | 0 | 0 | 9504 | 1.8 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [30 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35220896 | CWSP | P3D5 | 2021-03-05 11:50
35227168 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | P3D5 | Scoped | UNSE |  | 8290 | 0 | 8290 | 1.5701 | 0 | 0 | 0 | 0 | 8290 | 1.5701 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [30 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5701 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35220896 | CWSP | P3D5 | 2021-03-05 11:50
35227260 | Pantoja-Martinez, Jaime | 2021 | CWSP - COARSEGOLD 2104CB PH 1.2 | J1PE | Scoped | ESTS |  | 0 | 12443 | 12443 | 2.3566 | 0 | 0 | 12443 | 2.3566 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-06-16 17:00 | 2021-02-26 | Y | 2021-04-16 | 2021-04-16 | [9 empty] | John Ketcherside |  |  | N/A | [15 empty] | Contract | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3566 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-16 17:00 |  | INPR | 2021-07-13 08:00 |  | 275000 | 2050512.1 |  |  | Tom Yang | [8 empty] | Coarsegold | Madera | 37.2275 | -119.6896 |  | TL | OH | [7 empty] | 22 | 35219097 | CWSP | J1PE | 2021-03-11 15:59
35227261 | Pantoja-Martinez, Jaime | 2021 | CWSP - COARSEGOLD 2104CB PH 1.3 | J1PE | Scoped | ESTS |  | 0 | 11421 | 11421 | 2.1631 | 0 | 0 | 11421 | 2.1631 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-06-18 17:00 | 2021-02-26 | Y | 2021-04-16 | 2021-04-16 | [9 empty] | John Ketcherside |  |  | N/A | [15 empty] | Contract | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1631 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-18 17:00 |  | INPR | 2021-07-13 08:00 |  | 250000 | 2053204 |  |  | Tom Yang | [8 empty] | Coarsegold | Madera | 37.2275 | -119.6896 |  | TL | OH | [7 empty] | 22 | 35219097 | CWSP | J1PE | 2021-03-11 15:59
35227262 | Pantoja-Martinez, Jaime | 2021 | CWSP - COARSEGOLD 2104CB PH 1.4 | J1PE | Scoped | ESTS |  | 0 | 6152 | 6152 | 1.1652 | 0 | 0 | 6152 | 1.1652 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-07-02 17:00 | 2021-02-26 | Y | 2021-03-31 | 2021-03-31 | [9 empty] | John Ketcherside |  |  | N/A | [15 empty] | Contract | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1652 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-02 17:00 |  | INPR | 2021-07-27 08:00 |  | 150000 | 1888154.3 |  |  | Tom Yang | [8 empty] | Coarsegold | Madera | 37.2275 | -119.6896 |  | TL | OH | [7 empty] | 22 | 35219097 | CWSP | J1PE | 2021-03-11 16:00
35227263 | Mendez, Angelica | 2021 | CWSP - MARIPOSA 2102CB PH 2 | A0M6 | Scoped | ESTS |  | 0 | 1315.42 | 1315.42 | 0.24913 | 0 | 0 | 1315 | 0.24905 | 0 | 0 | 0 | 0 | 7.9545e-05 |  |  | YO | 08W | SH | 2021-05-25 17:00 | 2021-02-22 | Y | 2021-03-31 | 2021-03-31 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24913 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-25 17:00 |  | N/A | 2021-06-22 08:00 | [14 empty] | Mariposa | Mariposa | 37.5061 | -120.0049 | [10 empty] | 35 | 35219266 | CWSP | EDW9 | 2021-03-11 10:08
35227860 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | P3D5 | Scoped | UNSE |  | 0 | 1056 | 1056 | 0.2 | 0 | 0 | 1056 | 0.2 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [30 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35217271 | CWSP | P3D5 | 2021-03-05 11:50
35227861 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | P3D5 | Scoped | UNSE |  | 0 | 8026 | 8026 | 1.5201 | 0 | 0 | 8026 | 1.5201 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [30 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5201 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35217271 | CWSP | P3D5 | 2021-03-05 11:51
35227862 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | P3D5 | Scoped | UNSE |  | 0 | 5755 | 5755 | 1.09 | 0 | 0 | 5755 | 1.09 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [30 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.09 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35217271 | CWSP | P3D5 | 2021-03-05 11:51
35227863 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | P3D5 | Scoped | UNSE |  | 0 | 4171 | 4171 | 0.78996 | 0 | 0 | 4171 | 0.78996 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [30 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78996 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35217271 | CWSP | P3D5 | 2021-03-05 11:51
35227864 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | P3D5 | Scoped | UNSE |  | 3274 | 0 | 3274 | 0.62008 | 0 | 0 | 0 | 0 | 3274 | 0.62008 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [14 empty] | In Progress |  | Out to Bid | Joe Waller | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62008 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35217271 | CWSP | P3D5 | 2021-03-05 11:51
35227866 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | P3D5 | Scoped | UNSE |  | 0 | 2746 | 2746 | 0.52008 | 0 | 0 | 2746 | 0.52008 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [30 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52008 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35217271 | CWSP | P3D5 | 2021-03-05 11:51
35227867 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | P3D5 | Scoped | UNSE |  | 0 | 5174 | 5174 | 0.97992 | 0 | 0 | 5174 | 0.97992 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [30 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97992 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35217271 | CWSP | P3D5 | 2021-03-05 11:52
35227868 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | P3D5 | Scoped | UNSE |  | 0 | 2112 | 2112 | 0.4 | 0 | 0 | 2112 | 0.4 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [14 empty] | In Progress |  | Out to Bid | Joe Waller | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35217271 | CWSP | P3D5 | 2021-03-05 11:52
35228186 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | P3D5 | Scoped | UNSE |  | 7867 | 0 | 7867 | 1.49 | 0 | 0 | 0 | 0 | 7867 | 1.49 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [14 empty] | In Progress |  | Out to Bid | Joe Waller | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35220895 | CWSP | P3D5 | 2021-03-05 11:52
35228187 | Donovan, Patrick | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | P3D5 | Scoped | UNSE |  | 0 | 3326 | 3326 | 0.62992 | 0 | 0 | 3326 | 0.62992 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [30 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62992 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35220895 | CWSP | P3D5 | 2021-03-05 11:52
35229119 | Eagar, Josh | 2021 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | J1E1 | Scoped | UNSE |  | 3221 | 0 | 3221 | 0.61004 | 0 | 0 | 3221 | 0.61004 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-10-12 17:00 | 2021-02-18 | Y | 2021-04-30 | [13 empty] | In Progress | 2021-03-12 | Mark Thomas | Joe Waller | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61004 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-10-12 17:00 |  | N/A | 2021-10-15 08:00 |  | 475000 | [6 empty] | Prioritized | [5 empty] | Middletown | Lake | 38.7514 | -122.6117 | [10 empty] | 23 | 35219098 | CWSP | J1E1 | 2021-03-11 11:36
35231543 | Nguyen, My-Linh | 2021 | CWSP - TIDEWATER 210614072 PH 1.2 | M1NO | Scoped | UNSE |  | 6864 | 0 | 6864 | 1.3 | 0 | 0 | 0 | 0 | 6864 | 1.3 | 0 | 0 | 0 |  |  | DI | 08W | SH |  | 2021-02-26 | Y | [14 empty] | In Progress |  | Towill | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 350000 | [12 empty] | Concord | Contra Costa | 37.9632 | -121.9407 | [10 empty] | 18 | 35219093 | CWSP | EDW9 | 2021-03-11 12:49
35231544 | Nguyen, My-Linh | 2021 | CWSP - TIDEWATER 210614072 PH 1.3 | M1NO | Scoped | UNSE |  | 0 | 6336 | 6336 | 1.2 | 0 | 0 | 6336 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | DI | 08W | SH |  | 2021-02-26 | Y | [14 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 181000 | [12 empty] | Concord | Contra Costa | 37.9632 | -121.9407 | [10 empty] | 18 | 35219093 | CWSP | EDW9 | 2021-03-11 12:49
35231607 | Kringler, Jeff L | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | J6KF | Scoped | ESTS |  | 0 | 8691 | 8691 | 1.646 | 0 | 0 | 8691 | 1.646 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-22 17:00 | 2021-02-18 | Y | 2021-04-30 | 2021-04-02 | [12 empty] | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.646 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-22 17:00 |  | N/A | 2021-07-15 08:00 |  | 70000 | 2836423.6 |  |  | Maxwell Muscarella | [5 empty] | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062374 | PRE | J6KF | 2021-03-11 10:06
35231608 | Kringler, Jeff L | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | J6KF | Scoped | UNSE |  | 1742.4 | 0 | 1742.4 | 0.33 | 0 | 0 | 0 | 0 | 1742 | 0.32992 | 0 | 0 | 7.5758e-05 |  |  | SI | 08W | SH | 2021-06-29 17:00 |  |  | 2021-04-30 | [13 empty] | In Progress | 2021-04-12 | Mark Thomas | Eric Finley | [12 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-29 17:00 |  | N/A | 2021-07-22 08:00 | [14 empty] | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062374 | PRE | J91F | 2021-03-04 09:43
35231609 | Kringler, Jeff L | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | J6KF | Scoped | ESTS |  | 0 | 7023 | 7023 | 1.3301 | 0 | 0 | 7023 | 1.3301 | 0 | 0 | 0 | 0 | 0 | 8783 | 1.6634 | SI | 08W | SH | 2021-07-22 17:00 | 2021-02-18 | Y | 2021-03-31 | 2021-04-02 | [12 empty] | N/A | [15 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3301 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-22 17:00 |  | N/A | 2021-08-16 08:00 |  | 70000 | 2615040.7 |  |  | Maxwell Muscarella | Site survey requested 3/9/2021 |  |  |  |  | SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062374 | PRE | J6KF | 2021-03-11 10:02
35232280 | Barron, Raul Angelo | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | R4BA | Scoped | ESTS |  | 0 | 3168 | 3168 | 0.6 | 0 | 0 | 3168 | 0.6 | 0 | 0 | 0 | 0 | 0 | 3235 | 0.61269 | SI | 08W | SH | 2021-05-24 17:00 | 2021-02-22 | Y | 2021-04-30 | 2021-04-09 | [9 empty] | Jeanette Johnson | 2021-04-13 | 2021-04-13 | N/A |  |  |  |  | 2021-04-13 | 2021-04-13 | [9 empty] | GC | GC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-24 17:00 |  | INPR | 2021-06-22 08:00 | [14 empty] | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062375 | PRE | R4BA | 2021-03-11 14:33
35232442 | Ung, Mason |  | CWSP - DESCHUTES 11049718 PH 2.2 | MXUA | Scoped | UNSE |  | 0 | 16251 | 16251 | 3.0778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0778 |  |  | NV | 08W | SH | [39 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0778 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [10 empty] | 48 | 35225825 | CWSP | AXYX | 2021-03-09 17:23
35232443 | Ung, Mason |  | CWSP - DESCHUTES 11049718 PH 2.3 | MXUA | Scoped | UNSE |  | 0 | 5468 | 5468 | 1.0356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0356 |  |  | NV | 08W | SH | [39 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0356 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [10 empty] | 48 | 35225825 | CWSP | AXYX | 2021-03-09 17:24
35232444 | Ung, Mason |  | CWSP - DESCHUTES 11049718 PH 2.4 | MXUA | Scoped | UNSE |  | 0 | 18648 | 18648 | 3.5318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5318 |  |  | NV | 08W | SH | [39 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5318 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [10 empty] | 48 | 35225825 | CWSP | AXYX | 2021-03-09 17:23
35232445 | Ung, Mason |  | CWSP - DESCHUTES 11049718 PH 2.5 | MXUA | Scoped | UNSE |  | 0 | 13748 | 13748 | 2.6038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6038 |  |  | NV | 08W | SH | [39 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6038 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [10 empty] | 48 | 35225825 | CWSP | AXYX | 2021-03-09 17:24
35232650 | Kringler, Jeff L | 2021 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | J6KF | Scoped | UNSE |  | 9028 | 0 | 9028 | 1.7098 | 0 | 0 | 0 | 0 | 9028 | 1.7098 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-14 17:00 | 2021-06-01 | N | [14 empty] | In Progress | 2021-04-15 | REY | Eric Finley | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7098 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 |  | 316667 |  |  |  | Sheena Mital | [8 empty] | Cool | El Dorado | 38.8983 | -120.9827 | [10 empty] | 45 | 35219281 | CWSP | J6KF | 2021-03-11 10:30
35232651 | Kringler, Jeff L | 2021 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.3 | J6KF | Scoped | UNSE |  | 0 | 9187.2 | 9187.2 | 1.74 | 0 | 0 | 9187 | 1.74 | 0 | 0 | 0 | 0 | 3.7879e-05 |  |  | SI | 08W | SH | 2021-06-14 17:00 | 2021-06-01 | N | [14 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 |  | 316667 |  |  |  | Sheena Mital | [8 empty] | Cool | El Dorado | 38.8983 | -120.9827 | [10 empty] | 45 | 35219281 | CWSP | J6KF | 2021-03-11 10:01
35232960 | Ung, Mason |  | CWSP - DESCHUTES 11049718 PH1.2 | MXUA | Scoped | UNSE |  | 0 | 16057 | 16057 | 3.0411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0411 |  |  | NV | 08W | SH | [39 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0411 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [10 empty] | 48 | 35219286 | CWSP | AXYX | 2021-03-09 17:18
35234756 | Eagar, Josh |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 | J1E1 | Scoped | UNSE |  | 14689 | 0 | 14689 | 2.782 | 0 | 0 | 0 | 0 | 14689 | 2.782 | 0 | 0 | 0 |  |  | HB | 08W | SH |  |  | N | [17 empty] | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.782 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Middletown | Lake | 38.7576 | -122.6358 | [10 empty] | 474 | 35174501 | ECOP | J1E1 | 2021-03-11 14:00
35234758 | Eagar, Josh |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 | J1E1 | Scoped | UNSE |  | 3073 | 0 | 3073 | 0.58201 | 0 | 0 | 0 | 0 | 3073 | 0.58201 | 0 | 0 | 0 |  |  | HB | 08W | SH |  |  | N | [17 empty] | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58201 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Middletown | Lake | 38.7576 | -122.6358 | [10 empty] | 474 | 35174501 | ECOP | J1E1 | 2021-03-05 11:41
35234862 | Eagar, Josh |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 | J1E1 | Scoped | UNSE |  | 422 | 0 | 422 | 0.079924 | 0 | 0 | 0 | 0 | 422 | 0.079924 | 0 | 0 | 0 |  |  | HB | 08W | SH |  |  | N | [17 empty] | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.079924 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Middletown | Lake | 38.7576 | -122.6358 | [10 empty] | 474 | 35174501 | ECOP | J1E1 | 2021-03-05 11:42
35234865 | Eagar, Josh |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 | J1E1 | Scoped | UNSE |  | 3419 | 0 | 3419 | 0.64754 | 0 | 0 | 0 | 0 | 3419 | 0.64754 | 0 | 0 | 0 |  |  | HB | 08W | SH |  |  | N | [17 empty] | Joe Waller | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.64754 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Middletown | Lake | 38.7576 | -122.6358 | [10 empty] | 474 | 35174501 | ECOP | J1E1 | 2021-03-05 11:42
Note on I2: Mason, Derek: This data is required by the Fed. Monitor. This is the circuit footage of primary that was moved from OH to UG. This adds into your total planned mileage.
Note on J2: Mason, Derek: This data is required by the Fed. Monitor. This is circuit footage of primary that was hardened in place and includes the relocated footage. This adds into your total planned mileage.

## Move to 2022
Order | Job Owner Name | Project Reporting Year | Order Description | Job Owner | Scope Status | SAP Status | Circuit Feet from Planning | UG Feet | OH Feet
35062374 | Kringler, Jeff L | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | J6KF | Scoped | UNSE |  | 8106 | 0
35062376 | Kringler, Jeff L | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | J6KF | Scoped | UNSE |  | 22892 | 0
35219281 | Kringler, Jeff L | 2021 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | J6KF | Scoped | UNSE |  | 13200 | 0
35223036 | Kringler, Jeff L | 2021 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | J6KF | Scoped | UNSE |  | 264 | 0
35232650 | Kringler, Jeff L | 2021 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | J6KF | Scoped | UNSE |  | 9028 | 0
35192280 | Nguyen, My-Linh | 2021 | ECOP - CLAYTON 2212 - H01-LR2951 | M1NO | Scoped | UNSE |  | 7075.2 | 0
35219093 | Nguyen, My-Linh | 2021 | CWSP - TIDEWATER 210614072 PH 1.1 | M1NO | Scoped | ESTS |  | 6019 | 0
35219096 | Nguyen, My-Linh | 2021 | CWSP - KIRKER 2104442850 PH 1.1 | M1NO | Scoped | UNSE |  | 8817.6 | 0
35231543 | Nguyen, My-Linh | 2021 | CWSP - TIDEWATER 210614072 PH 1.2 | M1NO | Scoped | ESTS |  | 6864 | 0
35192291 | Pantoja-Martinez, Jaime | 2021 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | J1PE | Scoped | UNSE |  | 2534.4 | 0
35219589 | Hernandez, Michael Donald James | 2021 | CWSP - WILDWOOD 11011454 | M5HF | Scoped | UNSE |  | 0 | 13622.4
35224321 | Hernandez, Michael Donald James | 2021 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | M5HF | Scoped | UNSE |  | 0 | 12302.4
Total | [7 empty] | 84800.2 | 25924.8
Note on I1: Mason, Derek: This data is required by the Fed. Monitor. This is the circuit footage of primary that was moved from OH to UG. This adds into your total planned mileage.
Note on J1: Mason, Derek: This data is required by the Fed. Monitor. This is circuit footage of primary that was hardened in place and includes the relocated footage. This adds into your total planned mileage.

## Sheet4
Change Request Type | Order | Notification | Order Description | Updated Sub-Category | Business Justification | Updated Work Plan Date | Updated New Construction Complete Year | Requested Budget for 2020 | Requested Budget for 2021 | Requested Budget for 2022 | Requested Budget for 2023
Defer project | 35062374 | 115323920 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | N/A