## 08W Mastersheet
[17 empty] | 1092727.2 | 6729912.78 | 7822639.98 | 1481.5606 | 498.8468 | 982.7138 | 1548432 | 799194.8 | 293.2636 | 151.3627 |  | 1090316799.45 | 150176583.15 | 940140216.3 | 565147569 | 34553871.7 | 409546519 |  | 529230341.4 | 19884871.3 | -4868720.7 | 24753592 | 17352677 | 243567772.7 | 254137812.4 | -14837673.1 | 0 | 216658280.83 | 326906147.5 | -110247866.67 | 198024124.2 | 18634156.63 | 8957958.3 | 8441496.1 | 23120612.2 | 20287115.8 | 25933895.2 | 26440319.3 | 22558375.6 | 26501078.3 | 18656927.1 | 12036984.2 | 3915002.2 | 1174359.9 | 44605035.4 | 37084837 | 36457619.8 | 27444139.9 | 31723701.5 | 40512017.2 | 46855068.3 | 38856428.3 | 42082041 | 21465297.5
Order# | Order Desc | WBS Element | Planning Order | User Status | MAT | Job Owner | Job Owner Desc | PCA LanID | PCA | Schedule PCA LanID | Schedule PCA | Project Reporting Year | Operative Year | Program | Work Center | Receiver Cost Center | UG Feet | OH Feet | Planned Circuit Feet | Planned Circuit Miles | Total Installed Miles | Remaining Planned Miles | SAP Plan Feet | SAP Actual Feet | SAP Plan Miles | SAP Actual Miles | Resource | Authorized Amt | Contingency | AJE Amt | SinceIncepsion | Open Commitment | Project Remainning Budget | Project Budget Status | Total Forecast | CurrentMonth Plan | CurrentMonth Actual | CurrentMonth Variance | 2018 Actuals | 2019 Actuals | 2020 Actuals | 2021 Actuals to date | MPP Budget Status | MPP Approved Budget (2021) | 2021 EAC PRJ Version | 2021 MPP Budget - 2021 EAC PRJ | 2021 EAC PRM Version | 2021 MPP Budget - 2021 EAC PRM | Jan2021 | Feb2021 | Mar2021 | Apr2021 | May2021 | Jun2021 | Jul2021 | Aug2021 | Sep2021 | Oct2021 | Nov2021 | Dec2021 | Jan2022 | Feb2022 | Mar2022 | Apr2022 | May2022 | Jun2022 | Jul2022 | Aug2022 | Sep2022 | Oct2022 | Nov2022 | Dec2022 | 2022 EAC | Data Date | Current Baseline ID | Baseline Type | Baseline Name | Baseline CreateDate | Finish Date - Estimating End Date "Pend-In" (DS18) | Milestone Status - Estimating End Date "Pend-In" (DS18) | Start Date - Prepare & Route Business Case/PA | Finish Date - Prepare & Route Business Case/PA | Milestone Status - PA/Business Case Approved | Finish Date - All Permits Received | Milestone Status - All Permits Received | Finish Date - PM Release to Construction | Milestone Status - PM Release to Construction | Start Date - Order Material | Finish Date - Order Material | Activity Status - Order Material | Start Date - Materials Received | Finish Date - Materials Received | Activity Status - Materials Received | Start Date - Veg Field Work | Finish Date - Veg Field Work | Activity Status - Veg Field Work | Finish Date - Construction Start | Milestone Status - Construction Start | Finish Date - Start of Civil Construction | Milestone Status - Start of Civil Construction | Finish Date - Civil Construction Complete | Milestone Status - Civil Construction Complete | Finish Date - Start of Electric Construction | Milestone Status - Start of Electric Construction | Finish Date - Electric Construction Complete | Milestone Status - Electric Construction Complete | Finish Date - Operative Date | Milestone Status -Operative Date | BL Finish Date - In-Service Date | Finish Date - In-Service Date | BL - Expected Finish Date for In Service Date | Schedule Status | Milestone Status In-Service Date | Start Date - Site Restoration | Finish Date - Site Restoration | Activity Status - Site Restoration | Finish Date - Project Close (CMPL) | Milestone Status - Project Close (CMPL)
31462406 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | 5783289 | ADER | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | E.5015235.01 | 5783907 | ADER | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 7703 | 7703 | 1.4589 | 0 | 1.4589 | [5 empty] | 500000 | 0 | 500000 | 181463.9 | 0 | 318536.1 | On/Under Budget | 2531981.2 | 323.9 | 0 | 323.9 | 0 | 32246.9 | 121772.5 | 27444.5 | Project is not in the WP or in 2020 WP | 0 | 28919.9 | -28919.9 | 28919.9 | -28919.9 | 86.6 | 16259.4 | 11098.5 | 323.9 | 323.9 | 323.9 | 335.8 | 167.9 | 0 | 0 | 0 | 0 | 467015.8 | 619831.4 | 562827.4 | 42192.8 | 23325.8 | 357345.7 | 357345.7 | 100945.1 | 0 | 0 | 0 | 0 | 2530829.7 | 2021-04-02 | 154960 | BL-B | BL-B 35072361_CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2022-01-07 | Not Started | 2022-01-11 | 2022-01-24 | Not Started | 2022-02-18 | Not Started | 2022-02-21 | Not Started | 2022-03-21 | 2022-03-21 | Not Started | 2022-03-22 | 2022-03-28 | Not Started | 2022-03-21 | 2022-04-01 | Not Started | 2022-06-06 | Not Started |  |  |  |  | 2022-06-06 | Not Started |  |  | 2022-08-15 | Not Started | 2022-09-14 | 2022-09-14 | 0 | On/ Ahead Schedule | Not Started | 2022-08-22 | 2022-09-05 | Not Started | 2022-11-04 | Not Started
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR |  | 5530168 | ADER | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | Not in the WP |  | SH | NAPA | North Bay Assets | 0 | 1876 | 1876 | 0.3553 | 0.3553 | 0 | [5 empty] | 178900 | 178900 | 0 | 606983.7 | 0 | -606983.7 | OverRun | 0 | 0 | -5172.2 | 5172.2 | 0 | 92441.4 | 507300.7 | 2069.4 | Project is not in the WP or in 2020 WP | 0 | 7241.6 | -7241.6 | 7241.6 | -7241.6 | 2069.4 | 0 | 5172.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 | E.5014746.01 | 5785240 | ADER | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 8931 | 8931 | 1.6915 | 0 | 1.6915 | [5 empty] | 250000 | 0 | 250000 | 63969.7 | 0 | 186030.3 | On/Under Budget | 3214779.4 | 431.5 | 0 | 431.5 | 0 | 5729.7 | 167571.5 | -109331.5 | Project is not in the WP or in 2020 WP | 0 | -105352.6 | 105352.6 | -105352.6 | 105352.6 | -156558.6 | 46861.3 | 365.8 | 431.5 | 431.5 | 431.5 | 447.4 | 447.4 | 447.4 | 447.4 | 447.4 | 447.4 | 231.9 | 0 | 0 | 0 | 0 | 0 | 500000 | 1355500 | 1355500 | 0 | 0 | 0 | 3211231.9 | 2021-04-02 |  |  |  |  | 2022-04-22 | Not Started | 2022-04-26 | 2022-04-26 | Not Started | 2021-04-02 | Not Started | 2022-05-10 | Not Started | 2022-04-27 | 2022-04-27 | Not Started | 2022-04-28 | 2022-04-28 | Not Started | 2021-04-05 | 2021-08-18 | Not Started | 2022-05-13 | Not Started |  |  |  |  | 2022-05-13 | Not Started | 2022-05-18 | Not Started | 2022-06-03 | Not Started | 2022-08-26 | 2022-08-26 | 0 | On/ Ahead Schedule | Not Started | 2022-08-29 | 2022-09-09 | Not Started | 2022-10-18 | Not Started
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | E.5014721.01 | 5785223 | ADER | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 1027 | 8562 | 9589 | 1.8161 | 0 | 1.8161 | [5 empty] | 300000 | 0 | 300000 | 174975.4 | 0 | 125024.6 | On/Under Budget | 3449.9 | 287.9 | 0 | 287.9 | 0 | 10638.5 | 138253.5 | 26083.4 | Project is not in the WP or in 2020 WP | 0 | 28738.1 | -28738.1 | 28738.1 | -28738.1 | 908.3 | 13511.6 | 11663.5 | 287.9 | 287.9 | 287.9 | 298.5 | 298.5 | 298.5 | 298.5 | 298.5 | 298.5 | 309.5 | 309.5 | 309.5 | 154.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1083.2 | 2021-04-02 | 145823 | BL-A: | BL-A: 35094519_CWSP - ORO FINO 1102 - LR2560 PH 1.1_08W - June 2021 | 2020-07-24 | 2022-04-07 | Not Started | 2022-04-11 | 2022-04-22 | Not Started | 2022-04-07 | Not Started | 2022-04-22 | Not Started | 2022-04-29 | 2022-04-29 | Not Started | 2022-05-02 | 2022-07-22 | Not Started | 2022-04-08 | 2022-04-21 | Not Started | 2022-08-01 | Not Started |  |  |  |  | 2022-08-01 | Not Started | 2022-10-04 | Not Started | 2022-11-14 | Not Started | 2021-06-04 | 2022-12-14 | -558 | Behind Schedule | Not Started | 2022-12-15 | 2022-12-28 | Not Started | 2023-02-03 | Not Started
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 | E.5014720.01 | 5785224 | ADER | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 8398 | 8398 | 1.5905 | 0 | 1.5905 | [5 empty] | 100000 | 0 | 100000 | 63963 | 0 | 36037 | On/Under Budget | 260.5 | 73.3 | 0 | 73.3 | 0 | 10791.4 | 37404.6 | 15767 | Project is not in the WP or in 2020 WP | 0 | 16100.9 | -16100.9 | 16100.9 | -16100.9 | -4698.1 | 17888 | 2577.1 | 73.3 | 73.3 | 73.3 | 76 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2022-04-22 | Not Started | 2022-05-13 | 2022-05-19 | Not Started | 2022-05-12 | Not Started | 2022-05-26 | Not Started | 2022-04-25 | 2022-04-25 | Not Started | 2022-04-26 | 2022-05-02 | Not Started | 2022-05-13 | 2022-05-19 | Not Started | 2022-07-01 | Not Started |  |  |  |  | 2022-07-01 | Not Started | 2022-09-08 | Not Started | 2022-09-30 | Not Started | 2022-10-07 | 2022-10-07 | 0 | On/ Ahead Schedule | Not Started | 2022-10-10 | 2022-10-21 | Not Started | 2022-11-29 | Not Started
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | E.5014742.01 | 5785227 | ADER | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 953 | 5606 | 6559 | 1.2422 | 0 | 1.2422 | [5 empty] | 1 | -624999 | 625000 | 154244.8 | 0 | 470755.2 | On/Under Budget | 2695254.2 | 174.4 | 0 | 174.4 | 0 | 15732.5 | 82619.7 | 55892.6 | Project is not in the WP or in 2020 WP | 0 | 56067 | -56067 | 56067 | -56067 | 59780.2 | -49190.5 | 45302.9 | 174.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5047.3 | 6562.3 | 19404.5 | 355664.2 | 345160.3 | 627290.3 | 523774.1 | 548356.6 | 250618.4 | 13376.2 | 0 | 0 | 2695254.2 | 2021-04-02 | 154950 | BL-B | BL-B 35095163_CWSP - PINE GROVE 1102 - LR1222 - PH 2.1_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2022-01-27 | Not Started | 2022-01-31 | 2022-02-18 | Not Started | 2022-01-07 | Not Started | 2022-02-18 | Not Started | 2022-02-21 | 2022-02-22 | Not Started | 2022-02-23 | 2022-03-08 | Not Started | 2022-01-10 | 2022-01-10 | Not Started | 2022-03-16 | Not Started |  |  |  |  | 2022-03-16 | Not Started | 2022-05-02 | Not Started | 2022-05-02 | Not Started | 2022-05-05 | 2022-05-05 | 0 | On/ Ahead Schedule | Not Started | 2022-05-10 | 2022-05-11 | Not Started | 2022-06-23 | Not Started
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | E.5014727.04 | 5786003 | ADER | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  |  | JACKSON | Stockton Assets | 0 | 9021 | 9021 | 1.7085 | 0 | 1.7085 | [5 empty] | 1 | -329999 | 330000 | 103402.3 | 0 | 226597.7 | On/Under Budget | 1681486.9 | 147.9 | 0 | 147.9 | 0 | 562.7 | 105813.7 | -2974.1 | Project is not in the WP or in 2020 WP | 0 | -2604.3 | 2604.3 | -2604.3 | 2604.3 | 55729.8 | -59293.7 | 589.8 | 147.9 | 147.9 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 8741.7 | 408484.1 | 609052.6 | 609052.6 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 1681264.6 | 2021-04-02 | 154937 | BL-B | BL-B 35112974_CWSP - WEST POINT 1101 -LR 13444- PH 1.4_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2021-12-07 | Not Started | 2021-12-08 | 2022-01-04 | Not Started | 2022-01-10 | Not Started | 2022-01-17 | Not Started | 2022-01-05 | 2022-01-05 | Not Started | 2022-01-06 | 2022-02-02 | Not Started | 2022-01-11 | 2022-01-24 | Not Started | 2022-03-09 | Not Started |  |  |  |  | 2022-03-09 | Not Started | 2022-04-26 | Not Started | 2022-04-26 | Not Started | 2022-05-26 | 2022-05-26 | 0 | On/ Ahead Schedule | Not Started | 2022-05-04 | 2022-05-17 | Not Started | 2022-07-18 | Not Started
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | E.5014727.05 | 5786004 | ADER | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  |  | JACKSON | Stockton Assets | 0 | 7634 | 7634 | 1.4458 | 0 | 1.4458 | [5 empty] | 1 | -329999 | 330000 | 82734.4 | 0 | 247265.6 | On/Under Budget | 1614689.1 | 103.1 | 0 | 103.1 | 0 | 235.3 | 97278.1 | -14779.1 | Project is not in the WP or in 2020 WP | 0 | -14624.5 | 14624.5 | -14624.5 | 14624.5 | 24563.9 | -39814.9 | 471.9 | 103.1 | 51.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 411484.1 | 575738.9 | 575738.9 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 1614637.2 | 2021-04-02 | 154938 | BL-B | BL-B 35112975_CWSP - WEST POINT 1101 -LR 13444- PH 1.5_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2021-11-25 | Not Started | 2021-11-26 | 2022-01-06 | Not Started | 2021-12-28 | Not Started | 2022-01-06 | Not Started | 2022-01-07 | 2022-01-07 | Not Started | 2022-01-10 | 2022-02-04 | Not Started | 2021-12-01 | 2021-12-14 | Not Started | 2022-03-11 | Not Started |  |  |  |  | 2022-03-11 | Not Started | 2022-05-16 | Not Started | 2022-05-16 | Not Started | 2022-06-15 | 2022-06-15 | 0 | On/ Ahead Schedule | Not Started | 2022-05-24 | 2022-06-06 | Not Started | 2022-08-05 | Not Started
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | E.5014728.03 | 5786013 | ADER | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 7001 | 7001 | 1.3259 | 0 | 1.3259 | [5 empty] | 1 | -249999 | 250000 | 93041.4 | 0 | 156958.6 | On/Under Budget | 2601312.5 | 50.5 | 0 | 50.5 | 0 | 580.3 | 37041.6 | 55419.5 | Project is not in the WP or in 2020 WP | 0 | 55470 | -55470 | 55470 | -55470 | 87684.4 | -32797.3 | 532.4 | 50.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5741.7 | 7256.8 | 325991.1 | 760028.1 | 493568.4 | 650657.6 | 320181.3 | 13392.3 | 6505.9 | 6505.9 | 5741.7 | 5741.7 | 2601312.5 | 2021-04-02 | 154943 | BL-B | BL-B 35113994_CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2021-11-10 | Not Started | 2021-11-11 | 2021-12-22 | Not Started | 2022-01-11 | Not Started | 2022-01-12 | Not Started | 2021-12-23 | 2021-12-23 | Not Started | 2021-12-24 | 2022-01-20 | Not Started | 2022-01-12 | 2022-01-12 | Not Started | 2022-02-18 | Not Started |  |  |  |  | 2022-02-18 | Not Started | 2022-04-18 | Not Started | 2022-04-18 | Not Started | 2022-05-18 | 2022-05-18 | 0 | On/ Ahead Schedule | Not Started | 2022-04-26 | 2022-05-09 | Not Started | 2022-07-08 | Not Started
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | E.5014742.08 | 5786137 | ADER | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 8212 | 8212 | 1.5553 | 0 | 1.5553 | [5 empty] | 1 | -624999 | 625000 | 73032.1 | 0 | 551967.9 | On/Under Budget | 1658945.6 | 236.8 | 0 | 236.8 | 0 | 235.3 | 51148.9 | 21647.9 | Project is not in the WP or in 2020 WP | 0 | 22481 | -22481 | 22481 | -22481 | 30740.1 | -28105.2 | 19013 | 236.8 | 236.8 | 236.8 | 122.7 | 0 | 0 | 0 | 0 | 0 | 918328.4 | 653416.7 | 77034.6 | 9569.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658349.2 | 2021-04-02 | 154956 | BL-0 | BL-0 35114053_CWSP - PINE GROVE 1102 - LR1222 - PH 2.8_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2022-02-25 | Not Started | 2022-02-28 | 2022-03-25 | Not Started | 2022-04-28 | Not Started | 2022-04-29 | Not Started | 2022-03-28 | 2022-03-28 | Not Started | 2022-03-29 | 2022-04-25 | Not Started | 2022-04-29 | 2022-05-12 | Not Started | 2022-07-11 | Not Started |  |  |  |  | 2022-07-11 | Not Started | 2022-09-06 | Not Started | 2022-09-20 | Not Started | 2022-10-20 | 2022-10-20 | 0 | On/ Ahead Schedule | Not Started | 2022-10-21 | 2022-11-03 | Not Started | 2022-12-12 | Not Started
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | E.5014723.04 | 5785937 | ADER | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 11352 | 11352 | 2.15 | 0 | 2.15 | [5 empty] | 250000 | 0 | 250000 | 170501.9 | 0 | 79498.1 | On/Under Budget | 3032490.9 | 153.7 | 0 | 153.7 | 0 | 560.9 | 32693.2 | 137247.8 | Project is not in the WP or in 2020 WP | 0 | 139132.1 | -139132.1 | 139132.1 | -139132.1 | 200954 | -64682.3 | 976.1 | 153.7 | 153.7 | 76.9 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 2870.9 | 702181.5 | 1002025.7 | 701810.6 | 609003.2 | 3332.5 | 3332.5 | 3332.5 | 2870.9 | 3030760.3 | 2021-04-02 | 145854 | BL-A: | BL-A: 35115048_CWSP - MIWUK 1701 - LR 10600 PH 1.4_08W - Oct. 2021 | 2020-07-24 | 2020-12-03 | Completed | 2022-01-04 | 2022-01-17 | Not Started | 2022-02-28 | Not Started | 2022-03-01 | Not Started | 2022-01-18 | 2022-01-18 | Not Started | 2022-01-19 | 2022-02-15 | Not Started | 2022-01-25 | 2022-03-07 | Not Started | 2022-04-07 | Not Started |  |  |  |  | 2022-04-07 | Not Started | 2022-06-10 | Not Started | 2022-07-01 | Not Started | 2021-10-06 | 2022-08-02 | -300 | Behind Schedule | Not Started | 2022-08-03 | 2022-08-16 | Not Started | 2022-09-22 | Not Started
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | E.5014540.04 | 5786032 | ADER | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | STOCKTON | Stockton Assets | 0 | 6326 | 6326 | 1.1981 | 0 | 1.1981 | [5 empty] | 1 | -124999 | 125000 | 59340.8 | 0 | 65659.2 | On/Under Budget | 1947644.5 | 131.9 | 0 | 131.9 | 0 | 1898.5 | 83602.2 | -26159.8 | Project is not in the WP or in 2020 WP | 0 | -25962 | 25962 | -25962 | 25962 | -40729.4 | 14230 | 339.6 | 131.9 | 65.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1170063.2 | 751828.9 | 25686.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1947578.7 | 2021-04-02 | 154909 | BL-B | BL-B 35116923_CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2022-02-01 | Not Started | 2022-02-07 | 2022-03-18 | Not Started | 2022-02-01 | Not Started | 2022-03-18 | Not Started | 2022-03-21 | 2022-03-21 | Not Started | 2022-03-22 | 2022-04-11 | Not Started | 2022-02-08 | 2022-03-11 | Not Started | 2022-04-19 | Not Started |  |  |  |  | 2022-04-19 | Not Started | 2022-06-15 | Not Started | 2022-06-29 | Not Started | 2022-08-30 | 2022-08-30 | 0 | On/ Ahead Schedule | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-10-20 | Not Started
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | E.5014540.06 | 5786034 | ADER | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | STOCKTON | Stockton Assets | 0 | 8968 | 8968 | 1.6985 | 0 | 1.6985 | [5 empty] | 1 | -124999 | 125000 | 71356.4 | 0 | 53643.6 | On/Under Budget | 2226262.9 | 131.6 | 0 | 131.6 | 0 | 0 | 68187.2 | 3169.1 | Project is not in the WP or in 2020 WP | 0 | 3632.1 | -3632.1 | 3632.1 | -3632.1 | -17964.2 | 20724.2 | 409.1 | 131.6 | 131.6 | 131.6 | 68.2 | 0 | 0 | 0 | 0 | 0 | 1200930.2 | 582836.3 | 442164.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2225931.4 | 2021-04-02 | 154911 | BL-B | BL-B 35116925_CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2022-02-02 | Not Started | 2022-02-07 | 2022-03-18 | Not Started | 2022-02-02 | Not Started | 2022-03-18 | Not Started | 2022-03-21 | 2022-03-21 | Not Started | 2022-03-22 | 2022-04-11 | Not Started | 2022-02-02 | 2022-03-01 | Not Started | 2022-04-19 | Not Started |  |  |  |  | 2022-04-19 | Not Started | 2022-07-04 | Not Started | 2022-07-18 | Not Started | 2022-09-16 | 2022-09-16 | 0 | On/ Ahead Schedule | Not Started | 2022-09-19 | 2022-09-30 | Not Started | 2022-11-08 | Not Started
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 | E.5014721.02 | 5786759 | ADER | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 46 | 9382 | 9428 | 1.7856 | 0 | 1.7856 | [5 empty] | 100000 | -100000 | 200000 | 104031.7 | 0 | 95968.3 | On/Under Budget | 1544.3 | 94.5 | 0 | 94.5 | 0 | 235.3 | 89499 | 14297.5 | Project is not in the WP or in 2020 WP | 0 | 15169 | -15169 | 15169 | -15169 | 546.9 | 13167 | 583.6 | 94.5 | 94.5 | 94.5 | 98 | 98 | 98 | 98 | 98 | 98 | 101.6 | 101.6 | 101.6 | 101.6 | 101.6 | 101.6 | 105.3 | 52.7 | 0 | 0 | 0 | 0 | 767.6 | 2021-04-02 | 145824 | BL-A: | BL-A: 35129304_CWSP - ORO FINO 1102 - LR2560 PH 1.2_08W - May 2021 | 2020-07-24 | 2022-04-29 | Not Started | 2022-05-03 | 2022-05-16 | Not Started | 2022-04-08 | Not Started | 2022-05-16 | Not Started | 2022-05-17 | 2022-05-17 | Not Started | 2022-05-18 | 2022-08-09 | Not Started | 2022-04-15 | 2022-04-15 | Not Started | 2022-08-10 | Not Started |  |  |  |  | 2022-08-10 | Not Started | 2022-10-13 | Not Started | 2022-10-26 | Not Started | 2021-05-14 | 2022-11-25 | -560 | Behind Schedule | Not Started | 2022-11-28 | 2022-12-02 | Not Started | 2023-01-17 | Not Started
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | E.5014724.02 | 5786775 | ADER | 08W | M5HF | Mike Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 8596 | 8596 | 1.628 | 0 | 1.628 | [5 empty] | 55556 | -194444 | 250000 | 80751.1 | 0 | 169248.9 | On/Under Budget | 60.2 | 9 | 0 | 9 | 0 | 0 | 15683 | 65068.1 | Project is not in the WP or in 2020 WP | 0 | 65137.4 | -65137.4 | 65137.4 | -65137.4 | 105787 | -41180.8 | 461.9 | 9 | 9 | 9 | 9.4 | 9.4 | 9.4 | 9.4 | 4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2022-05-05 | Not Started | 2022-05-20 | 2022-05-26 | Not Started | 2022-05-19 | Not Started | 2022-06-02 | Not Started | 2022-05-06 | 2022-05-06 | Not Started | 2022-05-09 | 2022-07-29 | Not Started | 2022-05-20 | 2022-06-02 | Not Started | 2022-08-29 | Not Started |  |  |  |  | 2022-08-29 | Not Started | 2022-10-28 | Not Started | 2022-11-25 | Not Started | 2022-12-27 | 2022-12-27 | 0 | On/ Ahead Schedule | Not Started | 2022-12-28 | 2023-01-10 | Not Started | 2023-02-16 | Not Started
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | E.5014724.08 | 5786781 | ADER | 08W | M5HF | Mike Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2022 |  | CHICO | North Valley Assets | 0 | 8397 | 8397 | 1.5903 | 0 | 1.5903 | [5 empty] | 55556 | -194444 | 250000 | 81065.9 | 0 | 168934.1 | On/Under Budget | 28.7 | 1.9 | 0 | 1.9 | 0 | 0 | 10803.6 | 70262.2 | Project is not in the WP or in 2020 WP | 0 | 70279.3 | -70279.3 | 70279.3 | -70279.3 | 116847.8 | -47049.2 | 463.6 | 1.9 | 1.9 | 1.9 | 1.9 | 1.9 | 1.9 | 1.9 | 1.9 | 1.9 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 2021-04-02 |  |  |  |  | 2022-03-31 | Not Started | 2022-04-04 | 2022-04-15 | Not Started | 2022-05-26 | Not Started | 2022-05-27 | Not Started | 2022-04-18 | 2022-04-18 | Not Started | 2022-04-19 | 2022-08-22 | Not Started | 2022-03-25 | 2022-04-07 | Not Started | 2022-09-30 | Not Started |  |  |  |  | 2022-09-30 | Not Started | 2022-12-21 | Not Started | 2023-01-19 | Not Started | 2023-02-16 | 2023-02-16 | 0 | On/ Ahead Schedule | Not Started | 2023-02-17 | 2023-03-02 | Not Started | 2023-04-10 | Not Started
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | E.5015549.02 | 5789698 | ADER | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 7561 | 7561 | 1.432 | 0 | 1.432 | [5 empty] | 250000 | 0 | 250000 | 96074.1 | 0 | 153925.9 | On/Under Budget | 2727657.6 | 21.8 | 0 | 21.8 | 0 | 0 | 93949.9 | 2124.3 | Project is not in the WP or in 2020 WP | 0 | 2268.8 | -2268.8 | 2268.8 | -2268.8 | 561.7 | 1012.6 | 550 | 21.8 | 21.8 | 21.8 | 22.6 | 22.6 | 22.6 | 11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 909178.3 | 909178.3 | 909178.3 | 0 | 0 | 0 | 0 | 2727534.9
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | E.5015549.03 | 5789699 | ADER | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 106 | 3432 | 3538 | 0.67008 | 0 | 0.67008 | [5 empty] | 250000 | 0 | 250000 | 90780.4 | 0 | 159219.6 | On/Under Budget | 1298269.6 | 17.6 | 0 | 17.6 | 0 | 0 | 88517.9 | 2262.5 | Project is not in the WP or in 2020 WP | 0 | 2397.6 | -2397.6 | 2397.6 | -2397.6 | 529.1 | 1213.7 | 519.7 | 17.6 | 17.6 | 17.6 | 18.3 | 18.3 | 18.3 | 18.3 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 432717.4 | 432717.4 | 432717.4 | 0 | 0 | 0 | 0 | 1298152.2
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 | E.5015549.08 | 5789704 | ADER | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 5910 | 5015 | 10925 | 2.0691 | 0 | 2.0691 | [5 empty] | 250000 | 0 | 250000 | 59884.9 | 0 | 190115.1 | On/Under Budget | 3786576.9 | 22.5 | 0 | 22.5 | 0 | 0 | 13978.6 | 45906.3 | Project is not in the WP or in 2020 WP | 0 | 46055.4 | -46055.4 | 46055.4 | -46055.4 | 44677.7 | 885 | 343.6 | 22.5 | 22.5 | 22.5 | 23.3 | 23.3 | 23.3 | 11.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1262150 | 1262150 | 1262150 | 0 | 0 | 0 | 0 | 3786450
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | ADER | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 |  | SH | OROVILLE | North Valley Assets | 0 | 4224 | 4224 | 0.8 | 0 | 0.8 |  |  |  |  | GC | 300000 | 0 | 300000 | 58851 | 0 | 241149 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 199.4 | 58651.6 | Budget Allocated | 1520000 | 1566946.6 | -46946.6 | 58651.6 | 1461348.4 | 11297.4 | 409.6 | 46944.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | E.5034767.01.03 | 5794998 | APPR | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 |  | SH | NAPA | North Bay Assets | 0 | 10190 | 10190 | 1.9299 | 0 | 1.9299 | 9219 | 0 | 1.746 | 0 | Contract | 190000 | 0 | 190000 | 64403.6 | 0 | 125596.4 | On/Under Budget | 10554.1 | 3518 | 131.1 | 3386.9 | 0 | 0 | 0 | 64534.7 | Request 2021 Budget | 0 | 78475.6 | -78475.6 | 78475.6 | -78475.6 | 0 | 17011.8 | 47391.8 | 3518 | 3518 | 3518 | 3518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-04-30 | Not Started |  |  | Not Started | 2021-07-23 | Not Started | 2021-07-28 | Not Started | [9 empty] | 2021-08-23 | Not Started | [8 empty] | 2021-12-17 | Not Started | 2021-12-27 | 2021-12-27 | 0 | On/ Ahead Schedule | Not Started | 2021-12-20 | 2021-12-27 | Not Started | 2022-09-06 | Not Started
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | 5530164 | APPR | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 | 2020 | SH | CLRLAKE | Humboldt Division Assets | 0 | 2824 | 2824 | 0.53485 | 0 | 0.53485 |  |  |  |  | GC | 80000 | 0 | 80000 | 44923.5 | 0 | 35076.5 | On/Under Budget | 10764.7 | 3588.2 | 0 | 3588.2 | 0 | 212.4 | 9426.3 | 35284.8 | Request 2021 Budget | 0 | 49637.6 | -49637.6 | 49637.6 | -49637.6 | 459.9 | 24346.5 | 10478.4 | 3588.2 | 3588.2 | 3588.2 | 3588.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156047 | BL-A | BL-A 35137590_CWSP-ECOP-MIDDLETOWN 1101-OCB-H02_08W - Feb. 2021 | 2021-02-17 | 2021-04-15 | Not Started | 2021-04-19 | 2021-04-30 | Not Started | 2021-08-30 | Not Started | 2021-08-31 | Not Started | 2021-05-03 | 2021-05-03 | Not Started | 2021-05-04 | 2021-05-24 | Not Started | 2021-10-11 | 2021-10-22 | Not Started | 2021-11-08 | Not Started |  |  |  |  | 2021-11-08 | Not Started | 2021-12-20 | Not Started | 2022-01-18 | Not Started | 2022-03-21 | 2022-03-21 | 0 | On/ Ahead Schedule | Not Started | 2022-03-22 | 2022-04-04 | Not Started | 2022-05-11 | Not Started
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | E.5015029.01 | 5782859 | APPR | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2022 | 2022 | SH | LAKEPORT | Humboldt Division Assets | 11422 | 1351 | 12773 | 2.4191 | 0 | 2.4191 | 14918 | 0 | 2.8254 | 0 |  | 3523187 | 3477733 | 45454 | 922871.9 | 0 | -877417.9 | OverRun | 0 | 0 | 0 | 0 | 16471 | 138809.4 | 750685.7 | 16905.8 | Request 2021 Budget | 0 | 16905.8 | -16905.8 | 16905.8 | -16905.8 | 5400.1 | 6071.7 | 5434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145842 | BL-A: | BL-A: 74022385_CWSP Konocti - 1102 - LR 532 (UG)_08W - April 2021 | 2020-07-24 | 2021-06-15 | Not Started | 2021-06-17 | 2021-06-17 | Not Started | 2022-03-01 | Not Started | 2022-03-02 | Not Started | 2021-06-18 | 2022-01-31 | Not Started | 2022-02-01 | 2022-02-01 | Not Started | 2020-07-01 | 2020-12-17 | Completed | 2022-03-21 | Not Started |  |  |  |  | 2022-03-21 | Not Started | 2022-05-30 | Not Started | 2022-06-02 | Not Started | 2021-04-13 | 2022-07-01 | -444 | Behind Schedule | Not Started | 2022-07-04 | 2022-07-15 | Not Started | 2022-07-15 | Not Started
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD |  | 5783288 | APPR | 08W | JXF8 | Joseph Fong |  |  |  |  | Not in the WP |  |  | CHICO | [26 empty] | 3902 | Project is not in the WP or in 2020 WP | 0 | 3902 | -3902 | 0 | 0
74022386 | *CANC* CWSP - LOS GATOS 1106 - LB4 |  | 5782843 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  |  | SNJOSE | [26 empty] | 9937 | Project is not in the WP or in 2020 WP | 0 | 9937 | -9937 | 0 | 0
74022387 | CWSP-MIDDLETOWN 1101-TS 1079 | E.5014744.01 | 5782842 | CLSD | 08W | HXJI | Haridayal Jaswal | SHMG | Safeer Mirza |  |  | Not in the WP |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 20962 | 20962 | 3.9701 | 3.9701 | 0 | [5 empty] | 5829000 | 0 | 5829000 | 5591711.7 | 0 | 237288.3 | On/Under Budget | 0 | 0 | 0 | 0 | 98394.5 | 5533313.8 | -39996.6 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74022389 | *CANC* CWSP - PARADISE 1106 - OCB & LR 2 | E.5015532.01 | 5782907 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  |  | CHICO | North Valley Assets | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 500000 | 0 | 500000 | 0.1 | 0 | 499999.9 | On/Under Budget | 0 | 0 | 0 | 0 | 166.6 | 20318.9 | -20485.4 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74022391 | *CANC* **DO NOT USE**CWSP - VOLTA 1102 | E.9999990.01 | 5782908 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 1 | 1 | 0 | 0 | 0 | 0 | On/Under Budget | 0 | 0 | 0 | 0 | 11103.4 | 45576 | -56679.4 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74021962 | *DO NOT USE* CWSP: DIABLO WILDFIRE HARDE | E.9999990.01 | 5782578 | CLSD | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | Not in the WP |  |  | CONCORD | Diablo Assets | [11 empty] | 5344100 | 5344100 | 0 | 0 | 0 | 0 | On/Under Budget | 0 | 0 | 0 | 0 | 166560.7 | -170924.2 | 4363.5 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74022380 | *CANC* BRUNSWICK 1103 LR2200 | E.5015531.01 | 5782906 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  |  | GRSSVLLY | Sierra Assets | [11 empty] | 1 | -499999 | 500000 | 0 | 0 | 500000 | On/Under Budget | 0 | 0 | 0 | 0 | 7021.6 | 4337.6 | -11359.2 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74022381 | *CANC* CWSP - CAMP EVERS 2106 - 50 | E.9999990.01 | 5782839 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  |  | STCRUZ | Central Coast Assets | [11 empty] | 500000 | 500000 | 0 | 0.1 | 0 | -0.1 | OverRun | 0 | 0 | 0 | 0 | 7633.8 | -6737.6 | -896.1 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74022382 | CWSP-COLUMBIA HILL 1101-LR 2212 PH1 |  | 5777898 | CLSD | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  | SH | GRSSVLLY |  | 0 | 12389 | 12389 | 2.3464 | 2.3464 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
74015668 | *CANC* RPL OH WIRE ON OTTER-1101 S |  | 5786638 | CLSD | 08W | RNLO | Russell N Loeffler |  |  |  |  | Not in the WP |  |  | MONTEREY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35121739 | *CANCEL* CENTERILLE REMOVAL - BUTTE 1105 |  | 5786123 | CLSD | 08W | AVP4 | Aaron Patane |  |  |  |  | 2020 |  |  | CHICO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35147045 | *CANC* *DO NOT USE* PSPS - CASTRO V*CANC |  | 5530167 | CLSD | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | Not in the WP |  |  | HAYWARD | Mission Assets | 2100 | 0 | 2100 | 0.39773 | 0 | 0.39773 | [5 empty] | 500000 | 0 | 500000 | 0 | 0 | 500000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35118701 | *CANC* BR-10-02-W (E) CIRCLEWOOD DR, PA |  | 5786123 | CLSD | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2020 |  |  | CHICO | North Valley Assets | [11 empty] | 1 | 1 | 0 | 0 | 0 | 0 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 208.5 | -208.5 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35115149 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.4 | E.5015567.04 | 5785727 | CLSD | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2020 |  | SH | GRSSVLLY | Sierra Assets | 0 | 6692 | 6692 | 1.2674 | 1.2674 | 0 | 6500 | 6265 | 1.2311 | 1.1866 | GC | 5030060 | 1695453.6 | 3334606.4 | 2837051.6 | 0 | 497554.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 96726.2 | 2740325.4 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | 5785728 | CLSD | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2020 |  | SH | GRSSVLLY |  | 0 | 6241 | 6241 | 1.182 | 1.182 | 0 | 6221 | 6353 | 1.1782 | 1.2032 | GC | [14 empty] | 14620.8 | Project is not in the WP or in 2020 WP | 37621 | 14620.8 | 23000.2 | 0 | 37621
35115158 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.5 | E.5015569.05 | 5785720 | CLSD | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2020 |  | SH | GRSSVLLY | Sierra Assets | 0 | 11332 | 11332 | 2.1462 | 2.1462 | 0 | 11108 | 10413 | 2.1038 | 1.9722 | GC | 1623614.28 | -2810332.02 | 4433946.3 | 3386933 | 0 | 1047013.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 2905.9 | 3384027.1 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35116393 | CWSP - MIWUK 1702 - OCB - PH 1.3 | E.5014773.03 | 5785977 | CLSD | 08W | PXSO | Peter Siu | C2LJ | Cynthia Lau | MUHQ | Matt Haley | 2020 |  | SH | SONORA | Yosemite Assets | 0 | 13572 | 13572 | 2.5705 | 2.5705 | 0 | 13485 | 13742 | 2.554 | 2.6027 | GC | 4302367 | -1 | 4302368 | 4301719 | 0 | 649 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 810426.6 | 3491292.4 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35116394 | CWSP - MIWUK 1702 - OCB - PH 1.4 | E.5014773.04 | 5785978 | CLSD | 08W | PXSO | Peter Siu | C2LJ | Cynthia Lau | MUHQ | Matt Haley | 2020 |  | SH | SONORA | Yosemite Assets | 0 | 8858 | 8858 | 1.6777 | 1.6777 | -4.8231e-15 | 8790 | 8790 | 1.6648 | 1.6648 | GC | 2102204 | 112129.2 | 1990074.8 | 1826412.3 | 0 | 163662.5 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 130824.5 | 1695587.8 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35113871 | SILVERADO 2104 RECONDUCTOR - PHASE 2 |  | 5786200 | CLSD | 08W | S2WT | Steve Whitman |  |  |  |  | Not in the WP | 2019 | SH | NAPA |  | 650 | 0 | 650 | 0.12311 | 0.12311 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [25 empty] | 2021-04-02 |  |  |  |  | 2019-08-02 | Completed | 2019-08-06 | 2019-08-06 | Completed | 2019-09-12 | Completed | 2019-08-07 | Completed | 2019-08-08 | 2019-08-09 | Completed | 2019-09-23 | 2019-09-24 | Completed | 2019-09-19 | 2019-09-19 | Completed | 2019-10-01 | Completed |  |  |  |  | 2019-10-01 | Completed | 2020-06-01 | Completed | 2019-12-14 | Completed | 2019-12-16 | 2019-12-14 | 2 | On/ Ahead Schedule | Completed | 2020-05-11 | 2020-05-22 | Completed | 2020-08-25 | Completed
35113109 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.2 | E.5014535.02 | 5786055 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 0 | 681 | 681 | 0.12898 | 0.12898 | 0 | [5 empty] | 300000 | 0 | 300000 | 294673.1 | 0 | 5326.9 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 270432.6 | 24240.5 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35113952 | *CANC* BB1101-LR10296-PH1.4 |  | 5786126 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35113953 | *CANC* BB1101-LR10296-PH1.5 | E.5014542.05 | 5786127 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  |  | STCRUZ | Central Coast Assets | [11 empty] | 1 | 1 | 0 | 0 | 0 | 0 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 400995.1 | -400995.1 | 402122.5 | -402122.5 | 0 | 0 | 0 | 402122.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35113954 | *CANC* BB1101-LR10296-PH1.6 |  | 5786129 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35113955 | *CANC* B1101-LR10296-PH1.7 |  | 5786130 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35113103 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.3 | E.5014319.03 | 5786050 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 0 | 1152 | 1152 | 0.21818 | 0.21818 | 0 | [5 empty] | 390567 | 26780 | 363787 | 319671.6 | 0 | 44115.4 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 300581.7 | 19089.9 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35113104 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.2 | E.5014319.02 | 5786049 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 0 | 1324.3 | 1324.3 | 0.25081 | 0.25081 | 0 | [5 empty] | 517390 | 100243 | 417147 | 414586.4 | 0 | 2560.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 402136.5 | 12449.9 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 |  | 5785649 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 |  | SH | PLCRVLLE |  | 0 | 7006 | 7006 | 1.3269 | 1.3269 | 0 | 7873 | 7006 | 1.4911 | 1.3269 | Contract | [14 empty] | -99.8 | Project is not in the WP or in 2020 WP | 0 | -99.8 | 99.8 | 0 | 0
35112436 | CWSP - EL DORADO 2102 - LR19562 - PH 1.6 |  | 5785650 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 |  | SH | PLCRVLLE |  | 0 | 9529 | 9529 | 1.8047 | 1.8047 | 0 | 9210 | 9867 | 1.7443 | 1.8687 | Contract | [15 empty] | Project is not in the WP or in 2020 WP | 75000 | 75000 | 0 | 0 | 75000
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | 5785651 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 |  | SH | PLCRVLLE |  | 0 | 14550 | 14550 | 2.7557 | 2.7557 | 0 | 14365 | 14550 | 2.7206 | 2.7557 | Contract | [14 empty] | 10744.3 | Project is not in the WP or in 2020 WP | 0 | 10744.3 | -10744.3 | 0 | 0
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 |  | 5785645 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 |  | SH | PLCRVLLE |  | 0 | 8117 | 8117 | 1.5373 | 1.5373 | 0 | 8118 | 8117 | 1.5375 | 1.5373 | Contract | [14 empty] | -152.3 | Project is not in the WP or in 2020 WP | 0 | -152.3 | 152.3 | 0 | 0
35112426 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.3 |  | 5785653 | CLSD | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2020 |  | SH | PLCRVLLE |  | 0 | 9077 | 9077 | 1.7191 | 1.7191 | -2.1639e-15 | 9368 | 9077 | 1.7742 | 1.7191 | Contract | [15 empty] | Project is not in the WP or in 2020 WP | 0 | -259218 | 259218 | 0 | 0
35112427 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.4 | E.5015420.04 | 5785654 | CLSD | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2020 |  | SH | PLCRVLLE | Sierra Assets | 0 | 5069 | 5069 | 0.96004 | 0.96004 | 0 | 5117 | 5069 | 0.96913 | 0.96004 | Contract | 3306693 | 969939.2 | 2336753.8 | 1848367.1 | 0 | 488386.7 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 705528.7 | 1142838.4 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112428 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.5 |  | 5785655 | CLSD | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2020 | 2020 | SH | PLCRVLLE |  | 0 | 8571 | 8571 | 1.6233 | 1.6233 | 0 | 8571 | 8571 | 1.6233 | 1.6233 | Contract | [15 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [25 empty] | 2021-04-02 | 145890 | BL-0 | BL-0 35112428_CWSP - EL DORADO 2101 - OCBZONE - PH 1.5_08W - FEB 2020 | 2020-07-26 | 2019-09-27 | Completed | 2019-11-19 | 2019-11-28 | Completed | 2019-11-11 | Completed | 2019-12-02 | Completed | 2019-12-04 | 2019-12-05 | Completed | 2019-12-16 | 2019-12-18 | Completed | 2019-11-13 | 2020-01-24 | Completed | 2019-12-18 | Completed |  |  |  |  | 2019-12-18 | Completed | 2020-01-02 | Completed | 2020-02-27 | Completed | 2020-02-27 | 2020-02-27 | 0 | On/ Ahead Schedule | Completed | 2020-02-27 | 2020-02-27 | Completed | 2021-01-30 | Completed
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | 5794986 | CLSD | 08W | JDLM | Jesse Lorz |  |  |  |  | Not in the WP |  | SH | NAPA |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | -0.1 | Project is not in the WP or in 2020 WP | 0 | -0.1 | 0.1 | 0 | 0
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | 5543349 | CLSD | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | LIVRMORE |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0 | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | 5543351 | CLSD | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | LIVRMORE |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0 | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35145523 | *CANC* PSPS - FULTON 1102 HARDENING |  | 5788784 | CLSD | 08W | DJVH | Dylan James Velazquez |  |  |  |  | Not in the WP |  |  | STROSA |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 10202969.6 | -10202969.6 | 0 | 0
35144942 | *CANC* PSPS - PAUL SWEET 2105 - CB | E.5025647.01 | 5788789 | CLSD | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | Not in the WP |  |  | STCRUZ | Central Coast Assets | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 500000 | 0 | 500000 | 0 | 0 | 500000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 2117.5 | -2117.5 |  | Project is not in the WP or in 2020 WP | 0 | 180.1 | -180.1 | 180.1 | -180.1 | 0 | 0 | 0 | 32.2 | 32.2 | 32.2 | 33.4 | 33.4 | 16.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35144940 | *CANC* PSPS - HICKS 2101 – CB | E.5025645.01 | 5788790 | CLSD | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | Not in the WP |  |  | SNJOSE | San Jose Assets | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 500000 | 0 | 500000 | 0 | 0 | 500000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 409.3 | -409.3 | 409.3 | -409.3 | 0 | 0 | 0 | 89.8 | 89.8 | 89.8 | 93.3 | 46.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35172093 | *CANC* EL DORADO PH 2102 LR19542 P*CANC |  | 5530173 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  |  | AUBURN | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35172094 | CWSP-EL DORADO PH 2102 LR19542 PH 1*CANC |  | 5530173 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  |  | AUBURN | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35172521 | *CANC* EL DORADO PH 2102 LR19542 P*CANC |  | 5530173 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  |  | AUBURN | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35172522 | *CANC* CWSP-EL DORADO PH 2102 LR195*CANC |  | 5530173 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  |  | AUBURN | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35171354 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | 5530159 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2020 |  | SH | STCRUZ | Central Coast Assets | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.00018939 | 0 | GC | 37409.67 | 37409.67 | 0 | 39600.7 | 0 | -39600.7 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 39600.7 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35175131 | *CANC* - PLACERVILLE 2106 - LR1104 - PH2 |  | 5530173 | CLSD | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 |  | 5785218 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 |  | SH | GRSSVLLY |  | 0 | 7412 | 7412 | 1.4038 | 1.4038 | 0 | 7328 | 7419 | 1.3879 | 1.4051 | Contract | [14 empty] | -99.8 | Project is not in the WP or in 2020 WP | 0 | -99.8 | 99.8 | 0 | 0
35098578 | CWSP-COLUMBIA HILL 1101-LR 2212 PH2 | E.5015491.02 | 5785301 | CLSD | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 9480 | 9480 | 1.7955 | 1.7955 | 0 | [5 empty] | 3550706 | -1.7 | 3550707.7 | 3490905 | 0 | 59802.7 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 3450575.3 | 40329.7 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35098579 | CWSP-COLUMBIA HILL 1101-LR 2212 PH3 | E.5015491.03 | 5785302 | CLSD | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 7573 | 7573 | 1.4343 | 1.4343 | 0 | [5 empty] | 2438915 | 416398.7 | 2022516.3 | 1956173 | 0 | 66343.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 2020497 | -64324 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35103324 | CWSP - ROSSMOOR 1102 - OCB | E.5014544.03 | 5785419 | CLSD | 08W | PXSO | Peter Siu | C2LJ | Cynthia Lau | MUHQ | Matt Haley | 2020 |  | SH | WALNTCRK | Diablo Assets | 0 | 4046 | 4046 | 0.76629 | 0.76629 | 4.3063e-17 | 4046 | 4046 | 0.76629 | 0.76629 | Contract | 2510809 | 0 | 2510809 | 2486089.7 | 0 | 24719.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 1818894.5 | 667195.2 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35103325 | CWSP - MORAGA 1102 & 1104 - OCB | E.5014544.04 | 5785380 | CLSD | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2020 |  | SH | WALNTCRK | Diablo Assets | 3755 | 3159 | 6914 | 1.3095 | 1.3095 | -1.7225e-16 | 6506 | 6916 | 1.2322 | 1.3098 | Contract | 6187462 | 751903.5 | 5435558.5 | 5043980.6 | 0 | 391577.9 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 1903394.3 | 3140586.3 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35103942 | *CANC* BR-09-03-W (E) CONNIE CIR PA*CANC |  | 5786123 | CLSD | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35105656 | *CANC*BR-04-02-W (E) CASTLE DR PARB |  | 5786123 | CLSD | 08W | AVP4 | Aaron Patane |  |  |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35110374 | *CANC*BR-03-06-W (E) LUNAR LN PARB |  | 5786123 | CLSD | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | 2021 |  |  | CHICO | [26 empty] | -439.7 | Request 2021 Budget | 0 | -439.7 | 439.7 | 0 | 0
35110379 | BR-03-11-W (E) WHITAKER RD PARB |  | 5786123 | CLSD | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 |  |  | CHICO | [11 empty] | GC | [14 empty] | 2446 | Project is not in the WP or in 2020 WP | 0 | 2446 | -2446 | 0 | 0
35111500 | CWSP-RECON UPPER LAKE 01 HUNTERS PT RD |  | 5533649 | CLSD | 08W | J7LE | Jared Warren Lee | ACN3 | Austin Nordman |  |  | Not in the WP |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 1850 | 1850 | 0.35038 | 0.35038 | 0 | [5 empty] | 425000 | 0 | 425000 | 418578.6 | 0 | 6421.4 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 362979.3 | 55599.3 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35089880 | OCGC PIH SILVERADO 2104 - ANGWIN UG_PH 2 |  | 5530168 | CLSD | 08W | LLM0 | Linda L Swartz |  |  |  |  | Not in the WP |  | SH | NAPA |  | 2117 | 0 | 2117 | 0.40095 | 0.40095 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35081748 | OH RECONDUCTOR - ROB ROY 2105 -S028CC119 | P.12007 | 5530159 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2020 |  | SH | STCRUZ | Central Coast Assets | 0 | 850 | 850 | 0.16098 | 0.16098 | 0 | -1617 | 1425 | -0.30625 | 0.26989 | Contract | 713114 | 80294 | 632820 | 608138.6 | 0 | 24681.4 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 597265 | 10873.6 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35072362 | CWSP-OH COND RPLC: EEL RIVER 1102 FU1913 |  | 5782526 | CLSD | 08W | S2WT | Steve Whitman |  |  |  |  | Not in the WP |  | SH | FORTUNA |  | 0 | 14292 | 14292 | 2.7068 | 2.7068 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35072363 | *CANC* RECOND 15 298 FT 6CU 4CU & | E.5014305.01 | 5782597 | CLSD | 08W | J91F | Justin M Stabe | AXYX | Aaron Yuen |  |  | Not in the WP |  |  | NAPA | North Bay Assets | [11 empty] | 1 | -49999 | 50000 | 0 | 0 | 50000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35072720 | RPL OH WIRE ON GABILN 1101 17-0077248 | E.5015593.01 | 5783290 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | SALINAS | Central Coast Assets | 0 | 11745 | 11745 | 2.2244 | 2.2244 | 0 | [5 empty] | 1869000 | 321276 | 1547724 | 1076838.7 | 0 | 470885.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 1009384.6 | 67454.1 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35065727 | *CANC* CAMP FIRE SOUTH SKYWAY EXTEN*CANC |  | 5533652 | CLSD | 08W | JXF8 | Joseph Fong |  |  |  |  | Not in the WP |  |  | CHICO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35066745 | BIG BEND 1102 - BLOOMER HILL 08W PHS 2 |  | 5530169 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  | SH | CHICO | North Valley Assets | 0 | 8900 | 8900 | 1.6856 | 1.6856 | 0 | [5 empty] | 3916190 | 1146536 | 2769654 | 3167514.9 | 0 | -397860.9 | OverRun | 0 | 0 | 0 | 0 | 0 | 3118076.8 | 49438.1 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35075591 | SILVERADO 2105 WIRE DOWN PH 1 (CANCEL) |  | 5530168 | CLSD | 08W | FXRZ | Fernando Recoder |  |  |  |  | Not in the WP |  |  | NAPA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35075594 | SILVERADO 2105 WIRE DOWN PH-2 (CANCEL) |  | 5530168 | CLSD | 08W | FXRZ | Fernando Recoder |  |  |  |  | Not in the WP |  |  | NAPA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35075647 | SILVERADO 2105 WIRE DOWN PH-3 (CANCEL) |  | 5530168 | CLSD | 08W | FXRZ | Fernando Recoder |  |  |  |  | Not in the WP |  |  | NAPA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35075650 | SILVERADO 2105 WIRE DOWN PH-4 (CANCEL) |  | 5530168 | CLSD | 08W | FXRZ | Fernando Recoder |  |  |  |  | Not in the WP |  |  | NAPA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35076062 | *CANC* RECONDUCTOR 17547 FT OF 4AC *CANC |  | 5530166 | CLSD | 08W | S3B2 | Shahryar Bayat |  |  |  |  | Not in the WP |  |  | SNLUISOB | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35076064 | *CANC* 14184 FT OF 4ACSR&3363 FT OF 6CU |  | 5530166 | CLSD | 08W | S3B2 | Shahryar Bayat |  |  |  |  | Not in the WP |  |  | SNLUISOB | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043385 | *CANC* CWSP - TASSAJARA 2112 - FUS *CANC |  | 5786801 | CLSD | 08W | D7CJ | Danielle Marie Caponpon |  |  |  |  | Not in the WP |  |  | CONCORD | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043586 | *CANC* PACIFICA 1102 WD: INS TREE W*CANC |  | 5530170 | CLSD | 08W | MXT7 | Ming-Ching Tsai |  |  |  |  | Not in the WP |  |  | COLMA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043953 | *CANC* CWSP-ORO FINO 1102 LR-2560 *CANC |  | 5530169 | CLSD | 08W | RNLO | Russell N Loeffler |  |  |  |  | Not in the WP |  |  | CHICO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043954 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC |  | 5530169 | CLSD | 08W | RNLO | Russell N Loeffler |  |  |  |  | Not in the WP |  |  | CHICO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043955 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC |  | 5530169 | CLSD | 08W | MTTA | Musie Tsegay Tesfasilassie |  |  |  |  | Not in the WP |  |  | CHICO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043956 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC |  | 5530169 | CLSD | 08W | MTTA | Musie Tsegay Tesfasilassie |  |  |  |  | Not in the WP |  |  | CHICO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043986 | *CANC*DO NOT USE*CWSP-PINE GROVE 11*CANC |  | 5530176 | CLSD | 08W | DHN4 | Dan Nguyen |  |  |  |  | Not in the WP |  |  | JACKSON | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043763 | *CANC* CWSP - MIDDLETOWN 1101-TS 1 *CANC |  | 5530164 | CLSD | 08W | SLH8 | Shawn Leslie Howard |  |  |  |  | Not in the WP |  |  | LAKEPORT | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043949 | *CANC*DO NOT USE*CWSP-ORO FINO 1102*CANC |  | 5530169 | CLSD | 08W | J91F | Justin M Stabe | AXYX | Aaron Yuen |  |  | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 500000 | 0 | 500000 | 0 | 0 | 500000 | On/Under Budget | 0 | 0 | 0 | 0 | 3582.6 | -1344 | -2238.6 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35044284 | *CANC* CWSP-KONOCTI 1102-LR 532 *CANC |  | 5530164 | CLSD | 08W | SLH8 | Shawn Leslie Howard |  |  |  |  | Not in the WP |  |  | LAKEPORT | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35045959 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC |  | 5530169 | CLSD | 08W | J91F | Justin M Stabe | AXYX | Aaron Yuen |  |  | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 500000 | 0 | 500000 | 0 | 0 | 500000 | On/Under Budget | 0 | 0 | 0 | 0 | 2413.4 | -2136.6 | -276.8 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35046383 | *CANC* CWSP - MIWUK 1701 LR11800 &*CANC |  | 5530178 | CLSD | 08W | MLMW | Michelle Myles | CBN4 | Curtis Nelson |  |  | Not in the WP |  |  | SONORA | Yosemite Assets | [11 empty] | 5000000 | 5000000 | 0 | 0 | 0 | 0 | On/Under Budget | 0 | 0 | 0 | 0 | 11991.4 | -11991.4 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35046726 | *CANC* CWSP - LOS GATOS 1106 - LB4 *CANC |  | 5530160 | CLSD | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | SNJOSE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35046759 | *CANC* CWSP - VOLTA 1102 - LR 1648 *CANC |  | 5530169 | CLSD | 08W | J91F | Justin M Stabe | AXYX | Aaron Yuen |  |  | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 500000 | 500000 | 0 | 0 | 0 | 0 | On/Under Budget | 0 | 0 | 0 | 0 | 16904.5 | -16904.5 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35046793 | *CANC* CWSP-SALT SPRINGS 2102-LR31 *CANC |  | 5530176 | CLSD | 08W | J1JD | Jesse Joyner | M4JQ | Matt James |  |  | Not in the WP |  |  | ANGLSCMP | Stockton Assets | [11 empty] | 500000 | 500000 | 0 | 0 | 0 | 0 | On/Under Budget | 0 | 0 | 0 | 0 | 8645.6 | -8645.6 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35046896 | *CANC* CWSP - FITCH MOUNTAIN 1113 *CANC |  | 5530175 | CLSD | 08W | JXF8 | Joseph Fong |  |  |  |  | Not in the WP |  |  | STROSA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047143 | *CANC*DO NOT USE* CWSP - VOLTA 1102*CANC |  | 5530169 | CLSD | 08W | MTTA | Musie Tsegay Tesfasilassie |  |  |  |  | Not in the WP |  |  | CHICO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047146 | REDBUD 1101 RELOCATE FUSE 4865 IN T*CANC |  | 5530164 | CLSD | 08W | SLH8 | Shawn Leslie Howard |  |  |  |  | Not in the WP |  |  | CLRLAKE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047402 | *CANC* CWSP-SALT SPRINGS 2102-LR31 *CANC |  | 5530176 | CLSD | 08W | J1JD | Jesse Joyner | M4JQ | Matt James |  |  | Not in the WP |  |  | ANGLSCMP | Stockton Assets | [11 empty] | 500000 | 500000 | 0 | 0 | 0 | 0 | On/Under Budget | 0 | 0 | 0 | 0 | 2577.4 | -2577.4 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35047414 | *CANC* CWSP - PARADISE 1106 - OCB *CANC |  | 5530169 | CLSD | 08W | GAE9 | Glenn Esguerra |  |  |  |  | Not in the WP |  |  | CHICO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047418 | *CANC*DO NOT USE* CWSP-EL DORADO PH*CANC |  | 5530173 | CLSD | 08W | GAE9 | Glenn Esguerra |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047419 | *CANC*CWSP-SHINGLE SPRINGS 2109-LR *CANC |  | 5530173 | CLSD | 08W | D7CJ | Danielle Marie Caponpon |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047312 | *CANC*CWSP-CAMP EVERS 2106 - 5020 P*CANC |  | 5530159 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  |  | STCRUZ | Central Coast Assets | [11 empty] | 500000 | 500000 | 0 | 0 | 0 | 0 | On/Under Budget | 0 | 0 | 0 | 0 | 13665 | -13665 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35048011 | *CANC* CWSP - EL DORADO PH 2101 LR |  | 5530173 | CLSD | 08W | GSD5 | Gurshawn Singh Dhillon |  |  |  |  | Not in the WP |  |  | AUBURN | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35048058 | *CANC* CWSP-COLUMBIA HILL 1101-LR |  | 5530173 | CLSD | 08W | SLH8 | Shawn Leslie Howard |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35049913 | *CANC* CWSP - BRUNSWICK 1103 LR220 |  | 5530173 | CLSD | 08W | JXF8 | Joseph Fong |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35046366 | *CANC* CWSP BRUNSWICK 1105 LR-1030*CANC |  | 5530173 | CLSD | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35052121 | *CANC* ZAMORA 1105 WIRE DOWN LR 36762 |  | 5530171 | CLSD | 08W | JXF8 | Joseph Fong |  |  |  |  | Not in the WP |  |  | WOODLAND | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35052128 | *CANC*DO NOT USE* CWSP-STANISLAUS17*CANC |  | 5530176 | CLSD | 08W | SZC1 | Scott Chen |  |  |  |  | Not in the WP |  |  | JACKSON | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35052129 | *CANC*DO NOT USE*CWSP-STANISLAUS170*CANC |  | 5530176 | CLSD | 08W | SZC1 | Scott Chen |  |  |  |  | Not in the WP |  |  | JACKSON | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35052718 | OCGC CWSP: ANGWIN OH TO UG DEMO - PH 2 |  | 5530168 | CLSD | 08W | LLM0 | Linda L Swartz |  |  |  |  | Not in the WP |  | SH | NAPA |  | 2265 | 0 | 2265 | 0.42898 | 0.42898 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35056666 | *CANC* EST HILL 1101 LR 50486 HARDENING |  | 5530173 | CLSD | 08W | JXF8 | Joseph Fong |  |  |  |  | Not in the WP |  |  | AUBURN | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35058080 | *CANC* X-1104 OH RECOND SKYLINE *CANC |  | 5530162 | CLSD | 08W | J91F | Justin M Stabe | AXYX | Aaron Yuen |  |  | Not in the WP |  |  | OAKPORT | East Bay Assets | [11 empty] | 50000 | 50000 | 0 | 0 | 0 | 0 | On/Under Budget | 0 | 0 | 0 | 0 | 5097.1 | -5097.1 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35060157 | CWSP- HENDRIX DEMO - LIVERMORE TRNG CNTR |  | 5530167 | CLSD | 08W | LLM0 | Linda L Swartz |  |  |  |  | Not in the WP |  |  | LIVRMORE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35060229 | 2018 OH COND RPLC: FRUITLAND 42 C/O 7449 |  | 5530164 | CLSD | 08W | S2WT | Steve Whitman |  |  |  |  | Not in the WP |  | SH | GARBRVLE |  | 0 | 6529 | 6529 | 1.2366 | 1.2366 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35060580 | *CANC*BIG BEND 1102 - BLOOMER *CANC |  | 5530169 | CLSD | 08W | AVP4 | Aaron Patane |  |  |  |  | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 1 | 1 | 0 | 0 | 0 | 0 | On/Under Budget | 0 | 0 | 0 | 0 | 259.5 | -259.5 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35060581 | *CANC* RECONDUCT PT. MORETTI FROM 5043 |  | 5530159 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35060586 | *CANC* RECONDUCTOR 5885 FT ZACA *CANC |  | 5530166 | CLSD | 08W | A2LH | Anthony Lucero | J1M9 | Jennifer Monson |  |  | Not in the WP |  |  | SNLUISOB | Los Padres Assets | [11 empty] | 1 | 1 | 0 | 0 | 0 | 0 | On/Under Budget | 0 | 0 | 0 | 0 | 2407.3 | -2407.3 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35060587 | *CANC* REPLACE~1.2MILES_MAINLINE_ *CANC |  | 5530166 | CLSD | 08W | A2LH | Anthony Lucero | J1M9 | Jennifer Monson |  |  | Not in the WP |  |  | SNLUISOB | Los Padres Assets | [11 empty] | 1 | 1 | 0 | 0 | 0 | 0 | On/Under Budget | 0 | 0 | 0 | 0 | 2212.8 | -2212.8 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35008479 | R2 2019 AUBERRY 1101 RECONDUCTOR |  | 5530163 | CLSD | 08W | B1GQ | Brian Gallo |  |  |  |  | Not in the WP | 2019 | SH | FRESNO |  | 0 | 1636.8 | 1636.8 | 0.31 | 0.31 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [25 empty] | 2020-10-30 | 128544 | WSHP | WSHP 190307 - 35008479_Auberry 1101 Reconductor_08W - B1 | 2019-03-07 | 2019-03-04 | Completed |  |  | Completed | 2019-04-28 | Completed | 2019-05-03 | Completed | [6 empty] | 2019-05-29 | 2019-05-31 | Completed | 2019-06-03 | Completed |  |  |  |  | 2019-06-03 | Completed | 2019-06-07 | Completed | 2019-06-07 | Completed | 2019-05-16 | 2019-06-07 | -22 | Behind Schedule | Completed |  |  |  | 2020-05-31 | Completed
35015705 | *CANC* R2 OH RECONDUCTR ROB ROY 21*CANC |  | 5503108 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  |  | STCRUZ | Central Coast Assets | [11 empty] | 50000 | 50000 | 0 | -0.1 | 0 | 0.1 | On/Under Budget | 0 | 0 | 0 | 0 | 6170.7 | -6650.2 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35015706 | *CANC* OH RECONDUCTOR - ROB ROY 210*CANC |  | 5530159 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  |  | STCRUZ | Central Coast Assets | [11 empty] | 155000 | 155000 | 0 | 0 | 0 | 0 | On/Under Budget | 0 | 0 | 0 | 0 | 2535.9 | -2919.4 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35018620 | *CANC* RECON CAB 1104 17K FT LASAL *CANC |  | 5530166 | CLSD | 08W | KWB6 | Kenneth W Brem |  |  |  |  | Not in the WP |  |  | SNLUISOB | Los Padres Assets | [11 empty] | 1 | 1 | 0 | 0.1 | 0 | -0.1 | OverRun | 0 | 0 | 0 | 0 | 9836.8 | -10384.1 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35018787 | HALSEY 1101 - S039NO112 HIGH SPLICE 08J |  | 5530173 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  | SH | AUBURN | Sierra Assets | 0 | 2854 | 2854 | 0.54053 | 0.54053 | 0 | [5 empty] | 873318 | 6743 | 866575 | 782303.1 | 0 | 84271.9 | On/Under Budget | 0 | 0 | 0 | 0 | 3003.3 | 801800.7 | -23757.1 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35018788 | APPLE HILL 1104 - S049NO119 HIGH SPLICE |  | 5530173 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  | SH | PLCRVLLE | Sierra Assets | 0 | 6121 | 6121 | 1.1593 | 1.1593 | 0 | [5 empty] | 1995745 | 314578 | 1681167 | 1502307 | 0 | 178860 | On/Under Budget | 0 | 0 | 0 | 0 | 30025.9 | 1560453.2 | -89428.3 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35018886 | *CANC* RPL OH WIRE ON GABILN 1101 *CANC |  | 5530159 | CLSD | 08W | AAD3 | Arthur A De La Rocha | L3WA | Laree Ward |  |  | Not in the WP |  |  | SALINAS | Central Coast Assets | [11 empty] | 1 | 1 | 0 | 0 | 0 | 0 | On/Under Budget | 0 | 0 | 0 | 0 | 559 | -1471.3 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31360766 | FROGTOWN 1701 RECOND 1153FTTO 1/0ACSR TW |  | 5530176 | CLSD | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 1153 | 1153 | 0.21837 | 0.21837 | 0 | [5 empty] | 474763 | 57925 | 416838 | 400124.9 | 0 | 16713.1 | On/Under Budget | 0 | 0 | 0 | 0 | 8463 | 429017.7 | -38997.9 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31361488 | *CANC* RECOND 15 298 FT 6CU 4CU & *CANC |  | 5530168 | CLSD | 08W | FXRZ | Fernando Recoder |  |  |  |  | Not in the WP |  |  | NAPA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31387895 | *CANC* REPL 17 500' OF 4AR & 4CU I *CANC | P.11909 | 5530168 | CLSD | 08W | S2J9 | Steven Kenneth Jackson | A8G1 | Alvin Galesic |  |  | Not in the WP |  |  | NAPA | North Bay Assets | [11 empty] | 50000 | 0 | 50000 | 0 | 0 | 50000 | On/Under Budget | 0 | 0 | 0 | 0 | 11731.7 | -11731.7 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31389448 | *CANC* SILVERADO 2104 RECONDUCTOR*CANC |  | 5530168 | CLSD | 08W | FXRZ | Fernando Recoder |  |  |  |  | Not in the WP |  |  | NAPA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31392316 | *CANC* 2018MONTERIO1112/MOLINO1102WILDFI |  | 5530175 | CLSD | 08W | EESA | Emili E Scaief |  |  |  |  | Not in the WP |  |  | STROSA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35019006 | ROB ROY 2104 CO11865 REPLACE OH LINE |  | 5530159 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | STCRUZ | Central Coast Assets | 0 | 9525 | 9525 | 1.804 | 1.804 | 0 | [5 empty] | 1485645.6 | 326113.6 | 1159532 | 1016957.3 | 0 | 142574.7 | On/Under Budget | 0 | 0 | 0 | 0 | 2188.6 | 1056388.5 | -41619.8 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35015703 | *CANC* FOOTHILL 1101 LS CO9973 REP *CANC |  | 5530166 | CLSD | 08W | A2LH | Anthony Joseph Lucero | J1M9 | Jennifer Monson |  |  | Not in the WP |  |  | SNLUISOB | Los Padres Assets | [11 empty] | 1 | -49999 | 50000 | 0 | 0 | 50000 | On/Under Budget | 0 | 0 | 0 | 0 | 9135.1 | -9135.1 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35030654 | TW ON WOODSIDE1101 N/O 7573 |  | 5530170 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | SNCARLOS |  | 0 | 5271 | 5271 | 0.9983 | 0.9983 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35031139 | SHADY GLEN 1102 RECONDUCTOR BEYOND 6343 |  | 5530173 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  | SH | AUBURN | Sierra Assets | 0 | 8016 | 8016 | 1.5182 | 1.5182 | 0 | [5 empty] | 2668456 | 157254 | 2511202 | 2416634.1 | 0 | 94567.9 | On/Under Budget | 0 | 0 | 0 | 0 | 14003.3 | 2277144.7 | 125486.1 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35031660 | *CANC* PH 1:REPL 14 000' OF 4AR IN *CANC |  | 5530160 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  |  | CUPRTINO | De Anza Assets | [11 empty] | 50000 | 0 | 50000 | 0 | 0 | 50000 | On/Under Budget | 0 | 0 | 0 | 0 | 16135.7 | -16135.7 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35026420 | *CANC*OAKLAND X-1104 OH RECOND SKYLINE |  | 5530162 | CLSD | 08W | RNLO | Russell N Loeffler |  |  |  |  | Not in the WP |  |  | OAKPORT | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35032266 | APPLE HILL 1104 RECONDUCTOR |  | 5530173 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  | SH | AUBURN | Sierra Assets | 0 | 877 | 877 | 0.1661 | 0.1661 | 0 | [5 empty] | 368711 | 17504.8 | 351206.2 | 284268.5 | 0 | 66937.7 | On/Under Budget | 0 | 0 | 0 | 0 | 12370.1 | 439474.4 | -167576 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35039002 | OCGC 2018 CALISTOGA 1101 LEVEL 2 DEMO |  | 5530168 | CLSD | 08W | LLM0 | Linda L Swartz |  |  |  |  | Not in the WP |  | SH | NAPA |  | 0 | 6019.2 | 6019.2 | 1.14 | 1.14 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35039757 | *CANC* CWSP - BURNS 2101 - OCB - P*CANC |  | 5530159 | CLSD | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35039957 | *CANC* CWSP - STANISLAUS 1702 LR18 *CANC |  | 5530176 | CLSD | 08W | SZC1 | Scott Chen |  |  |  |  | Not in the WP |  |  | ANGLSCMP | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35040016 | *CANC* CWSP-SILVERADO 2104-LR 722 *CANC |  | 5530168 | CLSD | 08W | S2WT | Steve Whitman |  |  |  |  | Not in the WP |  |  | NAPA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35040742 | OCGC - 2018 MONTE RIO 1112 OH TO UG DEMO |  | 5530175 | CLSD | 08W | LLM0 | Linda L Swartz |  |  |  |  | Not in the WP |  | SH | STROSA |  | 2798.4 | 0 | 2798.4 | 0.53 | 0.53 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35040961 | CWSP: 2018 K-1102 OH TO UG DEMO |  | 5530161 | CLSD | 08W | LLM0 | Linda L Swartz |  |  |  |  | Not in the WP |  |  | WALNTCRK | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35041202 | *TRSFR* 35052732 CWSP-BB 1101 - LR *CANC |  | 5530159 | CLSD | 08W | E2MA | Erik Madsen |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35041205 | *CANC* WSP LOS GATOS 1106 LR 60116*CANC |  | 5530160 | CLSD | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | CUPRTINO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35042612 | *CANC* CWSP-ORO FINO 1101 LR-2022 *CANC |  | 5530169 | CLSD | 08W | J91F | Justin M Stabe | AXYX | Aaron Yuen |  |  | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 500000 | 0 | 500000 | 0 | 0 | 500000 | On/Under Budget | 0 | 0 | 0 | 0 | 3759.1 | -3395.5 | -363.6 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35042631 | *CANC*DO NOT USE* CWSP-VOLTA 1102-L*CANC |  | 5530169 | CLSD | 08W | J91F | Justin M Stabe | AXYX | Aaron Yuen |  |  | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 500000 | 0 | 500000 | 0 | 0 | 500000 | On/Under Budget | 0 | 0 | 0 | 0 | 13869 | -11375.3 | -2493.7 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35042647 | *TRSFR* 35052733 CWSP-BB 1101 - LR *CANC |  | 5530159 | CLSD | 08W | E2MA | Erik Madsen |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35042648 | *TRSFR* 35052734 CWSP-CE 2105 - LR *CANC |  | 5530159 | CLSD | 08W | E2MA | Erik Madsen |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35042719 | CWSP-AMGWIN STEEL POLE & TW DEMO PH |  | 5530168 | CLSD | 08W | LLM0 | Linda L Swartz |  |  |  |  | Not in the WP |  | SH | NAPA |  | 0 | 1275 | 1275 | 0.24148 | 0.24148 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35042893 | *CANC* CWSP - BURNS 2101 - OCB - PH*CANC |  | 5530159 | CLSD | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35042923 | *CANC* CWSP-ORO FINO 1101-LR 2022 *CANC |  | 5530169 | CLSD | 08W | J91F | Justin M Stabe | AXYX | Aaron Yuen |  |  | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 500000 | 0 | 500000 | 0 | 0 | 500000 | On/Under Budget | 0 | 0 | 0 | 0 | 3979 | -3512.4 | -466.6 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35043143 | *TRSFR* 35052728 CWSP LG1107 LR6009*CANC |  | 5530160 | CLSD | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | CUPRTINO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043245 | *CANC* CWSP-ORO FINO 1101 OCB PH 1 *CANC |  | 5530169 | CLSD | 08W | J91F | Justin M Stabe | AXYX | Aaron Yuen |  |  | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 500000 | 0 | 500000 | 0 | 0 | 500000 | On/Under Budget | 0 | 0 | 0 | 0 | 4179.9 | -3674.2 | -505.7 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35043246 | *CANC* CWSP-ORO FINO 1101 OCB PH 2 *CANC |  | 5530169 | CLSD | 08W | J91F | Justin M Stabe | AXYX | Aaron Yuen |  |  | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 500000 | 0 | 500000 | 0 | 0 | 500000 | On/Under Budget | 0 | 0 | 0 | 0 | 3600.8 | -3185.6 | -415.2 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35043247 | *CANC* CWSP-ORO FINO 1101 OCB PH 3 *CANC |  | 5530169 | CLSD | 08W | J91F | Justin M Stabe | AXYX | Aaron Yuen |  |  | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 500000 | 0 | 500000 | 0 | 0 | 500000 | On/Under Budget | 0 | 0 | 0 | 0 | 2862.3 | -2518.3 | -344 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35043280 | *CANC*DO NOT USE*CWSP-PINE GROVE 11*CANC |  | 5530176 | CLSD | 08W | DHN4 | Dan Nguyen |  |  |  |  | Not in the WP |  |  | JACKSON | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 |  | 5782590 | CLSD | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2020 |  | SH | JACKSON |  | 0 | 15172 | 15172 | 2.8735 | 2.8735 | 0 | 14920 | 14872 | 2.8258 | 2.8167 | GC | [14 empty] | -22126.8 | Project is not in the WP or in 2020 WP | 0 | -22126.8 | 22126.8 | 0 | 0
35040225 | HIGGINS 1110 RECONDUCTOR |  | 5530173 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  | SH | AUBURN | Sierra Assets | 0 | 8584 | 8584 | 1.6258 | 1.6258 | 0 | [5 empty] | 2449837 | 0 | 2449837 | 2412478.7 | 0 | 37358.3 | On/Under Budget | 0 | 0 | 0 | 0 | 6004 | 2626394.5 | -219919.8 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35042417 | *TRSFR* 35052727 CWSP LG1106 LR6011*CANC |  | 5530160 | CLSD | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | CUPRTINO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043304 | *CANC* 2019 OH COND RPLC: EEL RIVE *CANC |  | 5530164 | CLSD | 08W | S2J9 | Steven Kenneth Jackson | A8G1 | Alvin Galesic |  |  | Not in the WP |  |  | FORTUNA | Humboldt Division Assets | [11 empty] | 100000 | 0 | 100000 | 0 | 0 | 100000 | On/Under Budget | 0 | 0 | 0 | 0 | 827.7 | -827.7 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31089385 | *CANC* R5WD REPL 1 SPAN WITH 4/0AL*CANC |  | 5513266 | CLSD | 08W | KGH6 | Kenneth G Huffman |  |  |  |  | Not in the WP |  |  | STMARIA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31093073 | XSHELL RD, REPL 450' 6CU OH CONDUCTOR |  | 5513259 | CLSD | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | WTSNVLLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31093074 | +SM 1109 RECON (HWY 166 / E/O SIMAS RD) |  | 5513266 | CLSD | 08W | KGH6 | Kenneth G Huffman |  |  |  |  | Not in the WP |  |  | STMARIA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31093779 | MABURY 1104 WIRE DOWN 14-0043849 |  | 5513274 | CLSD | 08W | MXEN | Mohamed Elzain |  |  |  |  | Not in the WP |  |  | CINNABAR | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31094780 | OH WIRE DOWN REPLACEMENT ME1110 |  | 5513267 | CLSD | 08W | HGL3 | Hilton Law |  |  |  |  | Not in the WP |  |  | HAYWARD | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31095523 | OCGCELIAIBLITY -K1103, REPL #4ACSR W |  | 5530162 | CLSD | 08W | MYL5 | Michael Y. Lee |  |  |  |  | Not in the WP |  |  | OAKPORT | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31097449 | XPRUNEDALE 1107 WD C/O 4485 |  | 5513259 | CLSD | 08W | MTTA | Musie Tsegay Tesfasilassie |  |  |  |  | Not in the WP |  |  | SALINAS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31097452 | XCAMPHORA 1101 WD FCO 7091 |  | 5513259 | CLSD | 08W | MTTA | Musie Tsegay Tesfasilassie |  |  |  |  | Not in the WP |  |  | SALINAS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31098259 | OCCC SALINAS 1106 WIRE DOWN FCO56459 |  | 5513259 | CLSD | 08W | MTTA | Musie Tsegay Tesfasilassie |  |  |  |  | Not in the WP |  |  | SALINAS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31098360 | OCCC XGONZALES 1104 WIRE DOWN FCO 5005 |  | 5513259 | CLSD | 08W | MTTA | Musie Tsegay Tesfasilassie |  |  |  |  | Not in the WP |  |  | SALINAS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31082394 | OCGC N SIX SPANS FRATI LN |  | 5530175 | CLSD | 08W | JBJ8 | Jeffrey Burbank Jung |  |  |  |  | Not in the WP |  |  | STROSA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31083701 | OCCC HMB-1103RECOND 400' OH PRI_INST C/O |  | 5513270 | CLSD | 08W | GMK5 | Greg Kacherginsky |  |  |  |  | Not in the WP |  |  | SNCARLOS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31085776 | SANTA MARIA 1109 (HWY166/E/O BLACK RD) |  | 5513266 | CLSD | 08W | KGH6 | Kenneth G Huffman |  |  |  |  | Not in the WP |  |  | STMARIA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31086638 | OCCC CABRILLO 1104 WIREDOWN 14-0036943 | P.08472 | 5513266 | CLSD | 08W | A2LH | Anthony Lucero | J1M9 | Jennifer Monson |  |  | Not in the WP |  |  | STMARIA | Los Padres Assets | [11 empty] | 114208 | -87382 | 201590 | 114425 | 0 | 87165 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31207126 | MVWF PANORAMIC HWY, COUNTY, ALTO 1125 | P.11106 | 5530168 | CLSD | 08W | S2J9 | Steven Kenneth Jackson | A8G1 | Alvin Galesic |  |  | Not in the WP |  |  | SNRAFAEL | North Bay Assets | [11 empty] | 2185378 | 442809 | 1742569 | 1419528.5 | 0 | 323040.5 | On/Under Budget | 0 | 0 | 0 | 0 | 1420647.1 | -56071.1 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31207128 | *CANC* MVWF ALTO 1125 MUIR WOOD DR *CANC |  | 5530168 | CLSD | 08W | S2WT | Steve Whitman |  |  |  |  | Not in the WP |  |  | SNRAFAEL | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31207160 | +SANTA MARIA 1108 WD 15-076543 | P.11028 | 5513266 | CLSD | 08W | A2LH | Anthony Lucero | J1M9 | Jennifer Monson |  |  | Not in the WP |  |  | STMARIA | Los Padres Assets | [11 empty] | 156472 | -151528 | 308000 | 210979.8 | 0 | 97020.2 | On/Under Budget | 0 | 0 | 0 | 0 | 1025 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31211274 | OCGC PINEDALE 2109 - RECONDUCTOR | P.11084 | 5513263 | CLSD | 08W | JKH3 | Jacqueline Kay Henry-Larmond | J1EP | Joni Eldred |  |  | Not in the WP |  |  | FRESNO | Fresno Assets | [11 empty] | 499000 | 44000 | 455000 | 446773.6 | 0 | 8226.4 | On/Under Budget | 0 | 0 | 0 | 0 | 3874.3 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31211275 | OCGC CANTUNA 1103 - RECONDUCTORING | P.11131 | 5513263 | CLSD | 08W | JKH3 | Jacqueline Kay Henry-Larmond | J1EP | Joni Eldred |  |  | Not in the WP |  |  | FRESNO | Fresno Assets | [11 empty] | 165000 | 5000 | 160000 | 142441 | 0 | 17559 | On/Under Budget | 0 | 0 | 0 | 0 | 87472.4 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31212864 | LP402 164 SELBY LN ATHERTON |  | 5513270 | CLSD | 08W | MXT7 | Ming-Ching Tsai |  |  |  |  | Not in the WP |  |  | SNCARLOS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31212879 | OCGC RECONDUCTOR 6 CU ON E. NICOLAUS 11 |  | 5513273 | CLSD | 08W | CTD7 | Christopher T Dux |  |  |  |  | Not in the WP |  |  | MRYSVLLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31212922 | +SISQUOC 1104 WD-15-0070918 | P.11013 | 5513266 | CLSD | 08W | KWB6 | Kenneth W Brem |  |  |  |  | Not in the WP |  |  | STMARIA | Los Padres Assets | [11 empty] | 153852 | -172848 | 326700 | 158146.3 | 0 | 168553.7 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31213040 | OCGC RECONDUCTOR 6 CU ON OLIVEHURST 1104 |  | 5513273 | CLSD | 08W | CTD7 | Christopher T Dux |  |  |  |  | Not in the WP |  |  | MRYSVLLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31215474 | RECONDUCTOR ROB ROY 2104-MCDONALD RD | P.11413 | 5530159 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | STCRUZ | Central Coast Assets | 0 | 2719 | 2719 | 0.51496 | 0.51496 | 0 | [5 empty] | 625339 | 81566 | 543773 | 541456.9 | 0 | 2316.1 | On/Under Budget | 0 | 0 | 0 | 0 | 10066.8 | 516411.7 | 13098 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31216725 | X BEN LOMOND401-RIDGE RD-FUSE6295 | P.11245 | 5519558 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  |  | STCRUZ | Central Coast Assets | [11 empty] | 81280 | -117720 | 199000 | 176041 | 0 | 22959 | On/Under Budget | 0 | 0 | 0 | 0 | -2446 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31221409 | OCGC X TERMINOUS 1102 REPL. 800FT W/#2AR |  | 5513276 | CLSD | 08W | DHN4 | Dan Nguyen |  |  |  |  | Not in the WP |  |  | STOCKTON | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31222251 | X WDN_16-09640-212 CREST RD OTTER 1101 | P.11277 | 5513259 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  |  | MONTEREY | Central Coast Assets | [11 empty] | 62976 | -102456 | 165432 | 104557 | 0 | 60875 | On/Under Budget | 0 | 0 | 0 | 0 | -6566 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31229986 | OCGC JACINTO 1101 RECOND 9677'OF 3-6CU | P.11271 | 5513269 | CLSD | 08W | AVP4 | Aaron Patane |  |  |  |  | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 549035 | 0 | 549035 | 533892.6 | 0 | 15142.4 | On/Under Budget | 0 | 0 | 0 | 0 | 13479.9 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31206912 | X WDN 15-0073161 CE2103-OLD GRAHM HL R |  | 5530159 | CLSD | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31207089 | ESA BOULEVARD ORNE AVE, LARKSPUR GB 1103 | P.11105 | 5530168 | CLSD | 08W | S2J9 | Steven Kenneth Jackson | A8G1 | Alvin Galesic |  |  | Not in the WP |  |  | SNRAFAEL | North Bay Assets | [11 empty] | 1716807 | 406951 | 1309856 | 1092736.5 | 0 | 217119.5 | On/Under Budget | 0 | 0 | 0 | 0 | 1074650.1 | -23957.5 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31234871 | -RELIAIBLITY 2017 - UWF K1104/X1105/6 | P.11404 | 5530162 | CLSD | 08W | M2HM | Matthew Joseph Herron | J1EP | Joni Eldred | J7TY | Jace Thorsen | Not in the WP |  |  | OAKPORT | East Bay Assets | [11 empty] | 2675733 | 619019 | 2056714 | 1751641.1 | 0 | 305072.9 | On/Under Budget | 0 | 0 | 0 | 0 | 1696465.6 | -17601 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31246140 | WY1105 - RECOND 3000 FT OF 4AR W 2ARTW | P.11732 | 5530169 | CLSD | 08W | AVP4 | Aaron Patane |  |  |  |  | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 352805 | 42706 | 310099 | 293661 | 0 | 16438 | On/Under Budget | 0 | 0 | 0 | 0 | 286300.5 | -1966 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31248532 | CWSP HALF MOON BAY 1101 LS CO4063 |  | 5530170 | CLSD | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2020 |  | SH | SNCARLOS |  | 0 | 3926 | 3926 | 0.74356 | 0.74356 | 0 | 4816 | 4816 | 0.91212 | 0.91212 | Contract | [15 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31255868 | R2ROB ROY 2104 HIGH SPLICE CABLE REPLACE | P.11386 | 5530159 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  |  | WTSNVLLE | Central Coast Assets | [11 empty] | 452850 | 75475 | 377375 | 176947.9 | 0 | 200427.1 | On/Under Budget | 0 | 0 | 0 | 0 | 200547.2 | -24934 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31264915 | R7 RECONDUCTOR WILSON RD- RINCON 1103 |  | 5530175 | CLSD | 08W | JBJ8 | Jeffrey Burbank Jung |  |  |  |  | Not in the WP |  |  | STROSA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31275384 | OCGC DUCTOR MAYS CANYON-MIRABEL 1101 |  | 5530175 | CLSD | 08W | JBJ8 | Jeffrey Burbank Jung |  |  |  |  | Not in the WP |  |  | STROSA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31286361 | *CANC* FRUITLAND 42 C/O 7449 *CANC |  | 5530164 | CLSD | 08W | SLH8 | Shawn Leslie Howard |  |  |  |  | Not in the WP |  |  | GARBRVLE | [26 empty] | -12258.5 | Project is not in the WP or in 2020 WP | 0 | -12258.5 | 12258.5 | 0 | 0
31286571 | *R4 EL DORADO PH 2102 HIGH SPLICE AREA | P.11874 | 5530173 | CLSD | 08W | BER5 | Brian Ritchie | JIDM | Jason Daggett |  |  | Not in the WP |  |  | PLCRVLLE | Sierra Assets | [11 empty] | 310397 | 42422 | 267975 | 174335.6 | 0 | 93639.4 | On/Under Budget | 0 | 0 | 0 | 0 | 172088.5 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31286573 | APPLE HILL 2102 HIGH SPLICE AREA |  | 5530173 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  | SH | PLCRVLLE | Sierra Assets | 0 | 3492 | 3492 | 0.66136 | 0.66136 | 0 | [5 empty] | 900307 | 326267 | 574040 | 543235.6 | 0 | 30804.4 | On/Under Budget | 0 | 0 | 0 | 0 | 11238 | 547733.4 | -17889.2 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31278200 | +OCEANO 1102 S HALCYON & PINE RDGE | P.11685 | 5530166 | CLSD | 08W | A2LH | Anthony Joseph Lucero | J1M9 | Jennifer Monson |  |  | Not in the WP |  | SH | SNLUISOB | Los Padres Assets | 0 | 2059.2 | 2059.2 | 0.39 | 0.39 | -8.6126e-17 | [5 empty] | 496629 | 20000 | 476629 | 455075 | 0 | 21554 | On/Under Budget | 0 | 0 | 0 | 0 | 31025.9 | 427685.7 | -5598.4 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31289354 | *CANC* BIG RIVER 1101 FUSE 5187 REC*CANC |  | 5530164 | CLSD | 08W | SLH8 | Shawn Leslie Howard |  |  |  |  | Not in the WP |  |  | FTBRAGG | [26 empty] | 986.2 | Project is not in the WP or in 2020 WP | 0 | 986.2 | -986.2 | 0 | 0
31290147 | OCCCR7 OLEMA 1101 REPLACE COND VISION RD |  | 5530168 | CLSD | 08W | JBCT | Joseph B Cruz | ACN3 | Austin Nordman |  |  | Not in the WP |  | SH | SNRAFAEL |  | 0 | 3174 | 3174 | 0.60114 | 0.60114 | -8.6126e-17 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31319444 | RECON 5-SPANS PORTER CRK RD-RINCON 1103 |  | 5530175 | CLSD | 08W | JBCT | Joseph B Cruz | ACN3 | Austin Nordman |  |  | Not in the WP |  | SH | STROSA |  | 0 | 1279 | 1279 | 0.24223 | 0.24223 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31326119 | WEIMAR 1101 - NATURE'S WAY RECONDUCTOR | P.11895 | 5530173 | CLSD | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  | SH | AUBURN | Sierra Assets | 0 | 2990 | 2990 | 0.56629 | 0.56629 | 0 | [5 empty] | 1325896 | 251591.5 | 1074304.5 | 997479.3 | 0 | 76825.2 | On/Under Budget | 0 | 0 | 0 | 0 | 14191.4 | 914173.6 | 66731.8 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31330635 | FORESTHILL 1102 - SPRING GARDEN RD 08W | P.11870 | 5530173 | CLSD | 08W | BER5 | Brian Ritchie | JIDM | Jason Daggett |  |  | Not in the WP |  |  | AUBURN | Sierra Assets | [11 empty] | 918095 | 82638 | 835457 | 581153.5 | 0 | 254303.5 | On/Under Budget | 0 | 0 | 0 | 0 | 577793.5 | 2265.2 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31308015 | *CANC* SLO 1107 RECOND 3836 FT 10S *CANC |  | 5530166 | CLSD | 08W | KWB6 | Kenneth W Brem |  |  |  |  | Not in the WP |  |  | SNLUISOB | Los Padres Assets | [11 empty] | 1 | 1 | 0 | 0 | 0 | 0 | On/Under Budget | 0 | 0 | 0 | 0 | 5489 | -7563.5 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31316186 | *CANC* HMB1102 CO12457 #17-00290*CANC |  | 5530170 | CLSD | 08W | GMK5 | Greg Kacherginsky |  |  |  |  | Not in the WP |  |  | CUPRTINO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31334292 | RECON 9-SPANS, AUSTIN CREEK RD |  | 5530175 | CLSD | 08W | S2WT | Steve Whitman |  |  |  |  | Not in the WP |  | SH | STROSA |  | 0 | 2493 | 2493 | 0.47216 | 0.47216 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31338871 | RELIAIBLITY RICHMOND-REPL #6 CU-UWF_PH2 | P.11717 | 5530162 | CLSD | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  |  | RICHMOND | East Bay Assets | [11 empty] | 999938 | 121000 | 878938 | 654036.7 | 0 | 224901.3 | On/Under Budget | 0 | 0 | 0 | 0 | 745161.1 | 4388 | -96695 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30978199 | OC4 HMB1102 CO5905 RECONDUCTOR 470 FT |  | 5513270 | CLSD | 08W | GMK5 | Greg Kacherginsky |  |  |  |  | Not in the WP |  |  | SNCARLOS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30978886 | OCGC RECONDUCTOR TO REMOVE SPLICES |  | 5513260 | CLSD | 08W | IRB2 | Ivan Baez |  |  |  |  | Not in the WP |  |  | CUPRTINO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30979240 | OCGC XRECON 4 SPS OF WR GLEENWOOD-CE2106 |  | 5513259 | CLSD | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30979241 | OCGC XRECON 2 SPN@GRNITE CRK/HWY17 S VLY |  | 5513259 | CLSD | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30979379 | +RECNDUCTR TO REMOVE SPLICES VASONA 110 |  | 5513260 | CLSD | 08W | IRB2 | Ivan Baez |  |  |  |  | Not in the WP |  |  | CUPRTINO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30979787 | OCGC2014 CASTLE CR RD RECONDUCTOR LW2224 | P.05925 | 5513261 | CLSD | 08W | M2HM | Matthew Joseph Herron | J1EP | Joni Eldred | J7TY | Jace Thorsen | Not in the WP |  |  | CONCORD | Diablo Assets | [11 empty] | 164688 | 0 | 164688 | 146850.9 | 0 | 17837.1 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30980061 | *CANC* RECONDUCTOR 1 SP @ THOMPSON*CANC |  | 5513259 | CLSD | 08W | T1SI | Thiha Soe |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30980068 | 285 LITTLEFIELD AVE SSF |  | 5513270 | CLSD | 08W | MXT7 | Ming-Ching Tsai |  |  |  |  | Not in the WP |  |  | COLMA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30980069 | R1 MB-1106 RECONDUCTORING |  | 5513270 | CLSD | 08W | MXT7 | Ming-Ching Tsai |  |  |  |  | Not in the WP |  |  | COLMA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30980443 | XRECOND 4433/23327 @ 105 RODGERS RD |  | 5513259 | CLSD | 08W | JLDE | Jennifer L Goncalves |  |  |  |  | Not in the WP |  |  | SALINAS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30980444 | OC4 XRECOND 310 FT 1-0C, LKHRN & CAST BL |  | 5513259 | CLSD | 08W | DEWI | Daniel Evan Waters |  |  |  |  | Not in the WP |  |  | SALINAS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30981327 | OC4 RECON 800FT 4AR - BAKERSFIELD 1110 |  | 5513265 | CLSD | 08W | JCS9 | James Chang-Soo Shin |  |  |  |  | Not in the WP |  |  | BKRSFLD | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30981330 | 2015 MCFARLAND 1104 RECONDUCTOR | P.06393 | 5513265 | CLSD | 08W | SGBA | Steve Barrow | CAGM | Claire Graves |  |  | Not in the WP |  |  | WASCO | Kern Assets | [11 empty] | 332709 | -41560 | 374269 | 238873.5 | 0 | 135395.5 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30981641 | RECOND 1608FT 2CU-SAN BERNARD 1101 | P.07966 | 5513265 | CLSD | 08W | A2LH | Anthony Lucero | J1M9 | Jennifer Monson |  |  | Not in the WP |  |  | BKRSFLD | Kern Assets | [11 empty] | 116000 | 0 | 116000 | 66664 | 0 | 49336 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30981763 | OCGC 2014 LAMONT 1106 RECONDUCTOR | P.07498 | 5513265 | CLSD | 08W | A1L6 | Alexis Ann Herrera | CAGM | Claire Graves |  |  | Not in the WP |  |  | BKRSFLD | Kern Assets | [11 empty] | 407615 | 2238 | 405377 | 239261.4 | 0 | 166115.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30982568 | OC4 LKVL1101RECOND3SPAN-BRWNSRDLKVLHW,PE |  | 5513275 | CLSD | 08W | GSD5 | Gurshawn Singh Dhillon |  |  |  |  | Not in the WP |  |  | STROSA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30982640 | OC4 OCGC INSTREEW-5600MARSHALLPTLMA,OLEM |  | 5513275 | CLSD | 08W | GSD5 | Gurshawn Singh Dhillon |  |  |  |  | Not in the WP |  |  | PETALUMA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30982694 | OCCC +Z DIVIDE 1102 WD 13-0006459 |  | 5513266 | CLSD | 08W | KGH6 | Kenneth G Huffman |  |  |  |  | Not in the WP |  |  | STMARIA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30984641 | OCLH PARL 1103 RECON 2 SPANS 800' OF 2CU |  | 5513263 | CLSD | 08W | JJV7 | Joaquin Valencia |  |  |  |  | Not in the WP |  |  | FRESNO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30984775 | OCGC 93PL OH DET WIRE ON NAPA 1104 |  | 5513268 | CLSD | 08W | C3CJ | Cristobal Cabanillas |  |  |  |  | Not in the WP |  |  | NAPA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30985803 | OCLH BARTON 1101 4 ACSR |  | 5513263 | CLSD | 08W | VXLA | Victor Lopez |  |  |  |  | Not in the WP |  |  | FRESNO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30989646 | OC4 E WEST SAC 1109 RECONDUCTOR 700 FEET |  | 5513271 | CLSD | 08W | BCF1 | Brian Cory Feis |  |  |  |  | Not in the WP |  |  | WOODLAND | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30989894 | OCGC ARCATA 1105 REMOVE EXCESS SPLICES |  | 5513264 | CLSD | 08W | S2WT | Steve Whitman |  |  |  |  | Not in the WP |  |  | EUREKA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30990258 | OCGC XKING CITY 1106 RECONDUCTORING |  | 5513259 | CLSD | 08W | PXC0 | Paul Chui |  |  |  |  | Not in the WP |  |  | KINGCITY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30991832 | OCLH SCHINDLER 1105 - REPLACE 2 SPANS 4 |  | 5513263 | CLSD | 08W | KRBK | Kevin R Banister |  |  |  |  | Not in the WP |  |  | COALINGA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30992890 | OC4 XRECNDUCTOR 2 SPOF 4AR TW-PRESCOTT R |  | 5513259 | CLSD | 08W | T1SI | Thiha Soe |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30993194 | MEN 402 REPL 630FT &3 PLS/219 ATHERTON A |  | 5513270 | CLSD | 08W | GMK5 | Greg Kacherginsky |  |  |  |  | Not in the WP |  |  | SNCARLOS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30993279 | OCLHRECOND 5 SPANS 4AR,@ 50/52 NASHUA RD |  | 5513259 | CLSD | 08W | DEWI | Daniel Evan Waters |  |  |  |  | Not in the WP |  |  | SALINAS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30993327 | OCLHR1 RECONDUCTOR 390' OHDUMBARTON 2111 |  | 5513267 | CLSD | 08W | HGL3 | Hilton Law |  |  |  |  | Not in the WP |  |  | FREMONT | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30997023 | OCGC RECONDUC TO REMOVE SPLICES LG1106 |  | 5513260 | CLSD | 08W | IRB2 | Ivan Baez |  |  |  |  | Not in the WP |  |  | CUPRTINO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30997782 | *CANC* CAMBRIA LINE RECONFIG *CANC |  | 5513266 | CLSD | 08W | MWQ1 | Matthew William Queen |  |  |  |  | Not in the WP |  |  | SNLUISOB | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30997783 | OC4+RECONDUCTOR FAIRWY 1107 AT FUCO 1219 |  | 5513266 | CLSD | 08W | T1SI | Thiha Soe |  |  |  |  | Not in the WP |  |  | STMARIA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31001492 | OC4 OCLH PLEASANTON RECONDUCTOR 2700' WI |  | 5513267 | CLSD | 08W | AHC5 | Angie H Kim |  |  |  |  | Not in the WP |  |  | LIVRMORE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31002333 | MIDWAY 1104- INSTALL FUSE |  | 5513265 | CLSD | 08W | EXVH | Eric Vazquez |  |  |  |  | Not in the WP |  |  | BKRSFLD | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31006463 | OCLHXRECOND BV1102-HARKINS RD@BURTON AVE |  | 5513259 | CLSD | 08W | JLDE | Jennifer L Goncalves |  |  |  |  | Not in the WP |  |  | SALINAS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31007718 | *CANC* WIRE DOWN SERVICE REL JOB *CANC |  | 5513271 | CLSD | 08W | SRH2 | Stephen R Henke |  |  |  |  | Not in the WP |  |  | WOODLAND | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31008212 | OC4 RECON 1/0A W/397A MERRIL ST-BV 1103- |  | 5513259 | CLSD | 08W | JLDE | Jennifer L Goncalves |  |  |  |  | Not in the WP |  |  | SALINAS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31008213 | XBUENA VISTA 1103 NUTTING 4AR |  | 5513259 | CLSD | 08W | DEWI | Daniel Evan Waters |  |  |  |  | Not in the WP |  |  | SALINAS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31009249 | RPL 800' OH CONDUCTOR GREENBRAE 1101 | P.08623 | 5513268 | CLSD | 08W | S2J9 | Steven Kenneth Jackson | A8G1 | Alvin Galesic |  |  | Not in the WP |  |  | SNRAFAEL | North Bay Assets | [11 empty] | 195180 | 0 | 195180 | 157965.1 | 0 | 37214.9 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31011324 | OCGC XREPL DETERIORTD COND SMITH RD WAT |  | 5513259 | CLSD | 08W | M2KU | Mamadou Keita |  |  |  |  | Not in the WP |  |  | WTSNVLLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31016170 | OCGC XRECONDUCTORING PRI @ IVERSON RD |  | 5513259 | CLSD | 08W | DEWI | Daniel Evan Waters |  |  |  |  | Not in the WP |  |  | SALINAS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31016636 | OC4 OCGC CORRAL 1101 RELOCAT 4ACSR (WIR | P.08226 | 5513276 | CLSD | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  |  | VICTOR | Stockton Assets | [11 empty] | 222210 | -100902 | 323112 | 163783.7 | 0 | 159328.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31017531 | OC4 OCGC KERN POWER 2103 4 SPANS RECONDU |  | 5513265 | CLSD | 08W | J5CP | Juan Castillo |  |  |  |  | Not in the WP |  |  | BKRSFLD | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31017692 | *CANC* WD SISQUOC 1102 PHASE 3A RE*CANC |  | 5513266 | CLSD | 08W | JMB4 | Jeffrey M Brewer |  |  |  |  | Not in the WP |  |  | STMARIA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31017694 | +BPO WD SANTA MARIA 1109 RECNDUCTR & FU |  | 5513266 | CLSD | 08W | T1SI | Thiha Soe |  |  |  |  | Not in the WP |  |  | STMARIA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31019802 | OC4 EP REPLACE DAMAGED CONDUCT , HICKORY |  | 5513269 | CLSD | 08W | [6 empty] | Not in the WP |  |  | WILLOWS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31021152 | OC4 OCGC R2 2014 DINUBA 1105 RECONDUCTOR | P.06833 | 5513263 | CLSD | 08W | SGBA | Steve Barrow | CAGM | Claire Graves |  |  | Not in the WP |  |  | DINUBA | Fresno Assets | [11 empty] | 1742700 | -25751 | 1768451 | 1571040.3 | 0 | 197410.7 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31028173 | OC4 +OCEANO 1103 HWY 101 REC | P.06639 | 5513266 | CLSD | 08W | KWB6 | Kenneth W Brem |  |  |  |  | Not in the WP |  |  | SNLUISOB | Los Padres Assets | [11 empty] | 215672 | -64702 | 280374 | 230317.2 | 0 | 50056.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31036265 | R1128-RECNDUCTOR 3 SPANS,NSTALL CUT |  | 5513262 | CLSD | 08W | MYL5 | Michael Y. Lee |  |  |  |  | Not in the WP |  |  | RICHMOND | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31038431 | OC4 OCCC WD CABRILLO 1104 13-0056541 | P.08519 | 5513266 | CLSD | 08W | A2LH | Anthony Lucero | J1M9 | Jennifer Monson |  |  | Not in the WP |  |  | BUELLTON | Los Padres Assets | [11 empty] | 566951 | -282289 | 849240 | 411819.9 | 0 | 437420.1 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31039795 | MABURY 1102 WIRE DOWN 13-0077162 |  | 5513274 | CLSD | 08W | MXEN | Mohamed Elzain |  |  |  |  | Not in the WP |  |  | CINNABAR | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31040925 | RECONDUCT #4ACSR_W.JACKSON_HAYWRD |  | 5513267 | CLSD | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | HAYWARD | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31043129 | EB-RELIAIBLITY K1103-RECONDUT |  | 5513262 | CLSD | 08W | MYL5 | Michael Y. Lee |  |  |  |  | Not in the WP |  |  | OAKPORT | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31043566 | OCGC XRECOND 500FT W. ZAYANTE RD CE 2105 |  | 5513259 | CLSD | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31043567 | OCGC XRECON W/675FT TW LOKHRT GL CE 2105 |  | 5513259 | CLSD | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31047513 | OCGC RECONDUCTOR 2 SPANS DIXON 1103 |  | 5513271 | CLSD | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | VACAVLLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31048179 | OC4 OCGC SONOMA1105-WIREDWN-8TH ST EAST |  | 5513275 | CLSD | 08W | JBJ8 | Jeffrey Burbank Jung |  |  |  |  | Not in the WP |  |  | STROSA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31048895 | OCGC RECONDUCT 1-SPAN -WILLITS 1103 |  | 5513264 | CLSD | 08W | DRN3 | Dale Robert Novakovich |  |  |  |  | Not in the WP |  |  | UKIAH | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31053110 | MABURY 1102 WIRE DOWN 14-0004189 |  | 5513274 | CLSD | 08W | MXEN | Mohamed Elzain |  |  |  |  | Not in the WP |  |  | CINNABAR | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31054897 | OCGC BH402 LS CO10192 REPL.2 SPANS OH LI |  | 5513270 | CLSD | 08W | GMK5 | Greg Kacherginsky |  |  |  |  | Not in the WP |  |  | SNCARLOS | [26 empty] | 476.2 | Project is not in the WP or in 2020 WP | 0 | 476.2 | -476.2 | 0 | 0
31059794 | OCGC CLARKSVILLE 2104 RECONDUCTOR,PHASE1 | P.08456 | 5513273 | CLSD | 08W | BER5 | Brian Ritchie | JIDM | Jason Daggett |  |  | Not in the WP |  |  | PLCRVLLE | Sierra Assets | [11 empty] | 549218 | -73294 | 622512 | 492416.2 | 0 | 130095.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31060016 | OCCCRECO 1 SPAN LINE SIDE FU 1829 TW2107 |  | 5513261 | CLSD | 08W | FCR1 | Felix C Regacho |  |  |  |  | Not in the WP |  |  | CONCORD | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31062729 | LERDO 1103 RECONDUCTOR 1,700FT WD |  | 5513265 | CLSD | 08W | EXVH | Eric Vazquez |  |  |  |  | Not in the WP |  |  | BKRSFLD | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31063598 | WEEDPATCH 1106 RECOND WIRE DOWN |  | 5513265 | CLSD | 08W | GHD2 | Gregory H Do |  |  |  |  | Not in the WP |  |  | BKRSFLD | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31066529 | OCGC CEDAR CRK 1101-RECOND 3528' Y2015 | P.08120 | 5513269 | CLSD | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | Not in the WP |  |  | REDDING | North Valley Assets | [11 empty] | 547671 | -79420 | 627091 | 539968.5 | 0 | 87122.5 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31067784 | OCGC XRECON 300' OF 4AR W/ 4/0A FORD ST |  | 5513259 | CLSD | 08W | M2KU | Mamadou Keita |  |  |  |  | Not in the WP |  |  | WTSNVLLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31069570 | X-SPENCE 1121 WIREDOWN 3779 |  | 5513259 | CLSD | 08W | MTTA | Musie Tsegay Tesfasilassie |  |  |  |  | Not in the WP |  |  | SALINAS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31071681 | OCGC 1105-JEFFREY PINE RECON 600' |  | 5513269 | CLSD | 08W | CTD7 | Christopher T Dux |  |  |  |  | Not in the WP |  |  | OROVILLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31073205 | *CANC* R6 BUENA VISTA 1102 WD RECO*CANC |  | 5513259 | CLSD | 08W | DEWI | Daniel Evan Waters |  |  |  |  | Not in the WP |  |  | SALINAS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31075442 | BORDEN 1103 RECONDUCTORING |  | 5513277 | CLSD | 08W | SKA1 | Scott Keith Avery |  |  |  |  | Not in the WP |  |  | MADERA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31079018 | *CANC* BIG BEND 1102 - BLOOMER HIL *CANC |  | 5530169 | CLSD | 08W | JTHL | Joseph T Hembree | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  |  | OROVILLE | North Valley Assets | [11 empty] | 50000 | 50000 | 0 | 0.1 | 0 | -0.1 | OverRun | 0 | 0 | 0 | 0 | 7037.7 | -10902.5 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31082152 | OCCC XRECNDUCTR 2900' HRD TAP GNZLS 1104 |  | 5513259 | CLSD | 08W | MTTA | Musie Tsegay Tesfasilassie |  |  |  |  | Not in the WP |  |  | SALINAS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30948153 | OC2 REPLACE #6CU WITH 4AR, VASONA 1103 |  | 5513260 | CLSD | 08W | IRB2 | Ivan Baez |  |  |  |  | Not in the WP |  |  | CUPRTINO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30949571 | OC4 GRN VALLEY 2103 WIRE DOWN NEAR 1993 |  | 5513259 | CLSD | 08W | JLDE | Jennifer L Goncalves |  |  |  |  | Not in the WP |  |  | WTSNVLLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30951870 | 2014 MALAGA 1102 RECONDUCTOR CENTRAL | P.06373 | 5513263 | CLSD | 08W | JKH3 | Jacqueline Kay Henry-Larmond | J1EP | Joni Eldred |  |  | Not in the WP |  |  | FRESNO | Fresno Assets | [11 empty] | 299128 | -3900 | 303028 | 301521.1 | 0 | 1506.9 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30951871 | OC4 2014 MALAGA 1102 RECONDUCTOR AMERICA | P.06374 | 5513263 | CLSD | 08W | JKH3 | Jacqueline Kay Henry-Larmond | J1EP | Joni Eldred |  |  | Not in the WP |  |  | FRESNO | Fresno Assets | [11 empty] | 304087 | -28105 | 332192 | 320537.9 | 0 | 11654.1 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30951993 | OC4 XSPRING VALLEY ROAD WIRE REPLACEMENT |  | 5513259 | CLSD | 08W | JLDE | Jennifer L Goncalves |  |  |  |  | Not in the WP |  |  | WTSNVLLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30965813 | OC4 +MESA 1102 WIREDOWN - C/O 8953 |  | 5513266 | CLSD | 08W | KGH6 | Kenneth G Huffman |  |  |  |  | Not in the WP |  |  | SNLUISOB | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30967034 | OC4 LINE DOWN - DAVIS 1107 RECON-REFRAME |  | 5513271 | CLSD | 08W | SRH2 | Stephen R Henke |  |  |  |  | Not in the WP |  |  | WOODLAND | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30968294 | OC2 2013, BAKERSFIELD 2104, RE-CONDUCTOR |  | 5513265 | CLSD | 08W | EXVH | Eric Vazquez |  |  |  |  | Not in the WP |  |  | BKRSFLD | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30971722 | OC4RECNDUCT 2 SP OF WIRE @ MAPLE & CEDAR |  | 5513259 | CLSD | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30971802 | OC4 RECONDUCTOR INST FUSES VACA DIXON 11 |  | 5513271 | CLSD | 08W | [6 empty] | Not in the WP |  |  | VACAVLLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30972334 | OP-1101 RECOND_SAN PABLO & O'HATCH (R) |  | 5513262 | CLSD | 08W | TJCA | Thomas James Cannon |  |  |  |  | Not in the WP |  |  | RICHMOND | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30972547 | OCGC XDEL MONTE 2104 RECOND PORTOLA WD |  | 5513259 | CLSD | 08W | DEWI | Daniel Evan Waters |  |  |  |  | Not in the WP |  |  | MONTEREY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30972642 | WIREDOWN-RECOND-KERN OIL 1116 |  | 5513265 | CLSD | 08W | EXVH | Eric Vazquez |  |  |  |  | Not in the WP |  |  | BKRSFLD | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30974004 | OC4 DIXON 1103 RECONDUCTOR |  | 5513271 | CLSD | 08W | SRH2 | Stephen R Henke |  |  |  |  | Not in the WP |  |  | VACAVLLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30974166 | +SLO 1107 WIREDOWN (BOB JONES TRAIL) | P.09170 | 5513266 | CLSD | 08W | KWB6 | Kenneth W Brem |  |  |  |  | Not in the WP |  |  | SNLUISOB | Los Padres Assets | [11 empty] | 235457 | -196493 | 431950 | 319906.2 | 0 | 112043.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30974168 | OC4 LLAGAS 2101 RECONDUCTOR 4 SPANS |  | 5513274 | CLSD | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | EDENVALE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30974722 | OC4 DEL MONTE 2102 ELM WIREDWN RECONDUCT |  | 5513259 | CLSD | 08W | DEWI | Daniel Evan Waters |  |  |  |  | Not in the WP |  |  | MONTEREY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30974723 | OCGC DEL MONTE 2105 VAN BURN WIRE RECON |  | 5513259 | CLSD | 08W | DEWI | Daniel Evan Waters |  |  |  |  | Not in the WP |  |  | MONTEREY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30974724 | OCGC DEL MNTE 2104 RECTR CORRAL TIERRA |  | 5513259 | CLSD | 08W | DEWI | Daniel Evan Waters |  |  |  |  | Not in the WP |  |  | MONTEREY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30974733 | OC2 XREPL COND, BEACH ROAD @ PALM BEACH |  | 5513259 | CLSD | 08W | JLDE | Jennifer L Goncalves |  |  |  |  | Not in the WP |  |  | WTSNVLLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30975188 | OCGC+SLO 1103 WD @ 14125 - 12-70838 |  | 5513266 | CLSD | 08W | KGH6 | Kenneth G Huffman |  |  |  |  | Not in the WP |  |  | SNLUISOB | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30975601 | NEWARK 2103 CKT - RECONDUCTOR OH |  | 5513267 | CLSD | 08W | [6 empty] | Not in the WP |  |  | FREMONT | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30975805 | OCGC XINDUSTRIAL WY ANNEALED COND,KC1102 |  | 5513259 | CLSD | 08W | PXC0 | Paul Chui |  |  |  |  | Not in the WP |  |  | KINGCITY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30976210 | OC4 WIREDOWN-RECOND-ELK HILLS 1106 |  | 5513265 | CLSD | 08W | EXVH | Eric Vazquez |  |  |  |  | Not in the WP |  |  | BKRSFLD | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30977168 | OC4 OCGC FRNCH CMP 1102 RECOND & RELOCA |  | 5513276 | CLSD | 08W | SZC1 | Scott Chen |  |  |  |  | Not in the WP |  |  | STOCKTON | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31098634 | +MESA 1102 WIREDOWN (OSO FLACO TAP) | P.08609 | 5513266 | CLSD | 08W | KWB6 | Kenneth W Brem |  |  |  |  | Not in the WP |  |  | STMARIA | Los Padres Assets | [11 empty] | 165745 | -39394 | 205139 | 131072.2 | 0 | 74066.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31100467 | OCGC ZAMORA 1105 RECONDUCTOR 3 SPANS |  | 5513273 | CLSD | 08W | SDK6 | Scott David Kostka |  |  |  |  | Not in the WP |  |  | WOODLAND | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31102548 | OC4 COTTONWOOD 1102-RECON 918' |  | 5513269 | CLSD | 08W | AXDJ | Anandi De La Fuente |  |  |  |  | Not in the WP |  |  | REDDING | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31102963 | +SISQUOC 1104 WD (ORCUTT-GAREY RD) |  | 5513266 | CLSD | 08W | KGH6 | Kenneth G Huffman |  |  |  |  | Not in the WP |  |  | STMARIA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31109716 | 2016 GUERNSEY 1104 ANNEALED RECOND | P.09854 | 5513263 | CLSD | 08W | SGBA | Steve Barrow | CAGM | Claire Graves |  |  | Not in the WP |  |  | LEMOORE | Fresno Assets | [11 empty] | 710000 | 0 | 710000 | 639358.4 | 0 | 70641.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 787 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31111367 | OCGC XR CONDCTR 4 SPANS @TROUT G&OSPREY |  | 5513259 | CLSD | 08W | M2KU | Mamadou Keita |  |  |  |  | Not in the WP |  |  | WTSNVLLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31112500 | OCGC RECON 780FT OF 4ACSR MONTE RIO 1111 |  | 5513275 | CLSD | 08W | DRN3 | Dale Robert Novakovich |  |  |  |  | Not in the WP |  |  | STROSA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31113693 | OCCC DOLAN RD 1104 WIREDOWN COOPER RD |  | 5513259 | CLSD | 08W | MTTA | Musie Tsegay Tesfasilassie |  |  |  |  | Not in the WP |  |  | SALINAS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31115088 | OCGC RECON 900FT 4CU/4/0ALTW FTROSS 1121 |  | 5513275 | CLSD | 08W | DRN3 | Dale Robert Novakovich |  |  |  |  | Not in the WP |  |  | STROSA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31115947 | EL NIDO 1103 REPLACE ANNEALTED 650FT |  | 5513277 | CLSD | 08W | DHN4 | Dan Nguyen |  |  |  |  | Not in the WP |  |  | MERCED | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31119865 | OCCC BEL 403 REPLC200FT OH LINE INST C/O |  | 5513270 | CLSD | 08W | GMK5 | Greg Kacherginsky |  |  |  |  | Not in the WP |  |  | SNCARLOS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31120755 | RECONDUCTOR ND2101 WIREDOWN |  | 5513267 | CLSD | 08W | E2MA | Erik Madsen |  |  |  |  | Not in the WP |  |  | LIVRMORE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31120911 | X-DOLN RD 1104 WIREDOWN BLNCO ARMSTRNG |  | 5513259 | CLSD | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | SALINAS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31120912 | X-DOLAN RD 1101 WIREDWN STRAWBRRY CYN |  | 5513259 | CLSD | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | SALINAS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31121472 | +OCEANO 1104 WD 14-0067445 |  | 5513266 | CLSD | 08W | S3B2 | Shahryar Bayat |  |  |  |  | Not in the WP |  |  | SNLUISOB | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31121571 | REPL OH WIRE PORT CHICAGO W/O NICHOLS |  | 5513261 | CLSD | 08W | LLM0 | Linda L Swartz |  |  |  |  | Not in the WP |  |  | ANTIOCH | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31122088 | KINGSBRG 1114 600' RECOND WIREDOWN |  | 5513263 | CLSD | 08W | DET3 | Daniel Edward Thomas |  |  |  |  | Not in the WP |  |  | FRESNO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31122833 | OCCC BASALT 1106 WIRE DWN FUSE 1157 ZONE |  | 5513268 | CLSD | 08W | C3CJ | Cristobal Cabanillas |  |  |  |  | Not in the WP |  |  | NAPA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31124815 | OCCC X-SLDD 1114 WREDWN RECND. S/O HY101 |  | 5513259 | CLSD | 08W | MTTA | Musie Tsegay Tesfasilassie |  |  |  |  | Not in the WP |  |  | KINGCITY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31124819 | OCCC KING CITY 1106 WD 14-0067419 |  | 5513259 | CLSD | 08W | S3B2 | Shahryar Bayat |  |  |  |  | Not in the WP |  |  | KINGCITY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31125443 | OCLH PASO ROBLES 1103 WD 14-0066395 |  | 5513266 | CLSD | 08W | S3B2 | Shahryar Bayat |  |  |  |  | Not in the WP |  |  | TEMPLETN | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31125646 | OCGC D 2350' EXCESS SLICES SW6041 |  | 5513264 | CLSD | 08W | SLH8 | Shawn Leslie Howard |  |  |  |  | Not in the WP |  |  | GARBRVLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31128279 | OCGC SPAULDING 1101 WIREDOWN SS OF 6607 |  | 5513273 | CLSD | 08W | JSKE | Jasjit S Khangura |  |  |  |  | Not in the WP |  |  | AUBURN | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31129830 | OCCC BIG TREES 402 _ 14-0076789 PHASE 1 | P.11076 | 5513259 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  |  | STCRUZ | Central Coast Assets | [11 empty] | 280000 | 0 | 280000 | 259437.4 | 0 | 20562.6 | On/Under Budget | 0 | 0 | 0 | 0 | -20994 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31132867 | HMB1101 REPLACE OH LINE SKYLINE BLVD | P.11476 | 5530170 | CLSD | 08W | S8BY | Samuel L. Beeghly | CBN4 | Curtis Nelson |  |  | Not in the WP |  |  | SNCARLOS | Peninsula Assets | [11 empty] | 383497 | -1080857 | 1464354 | 715788.1 | 0 | 748565.9 | On/Under Budget | 0 | 0 | 0 | 0 | 704662.5 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31133991 | OCGC WIRE DOWN-RECONDUCTOR LIVE OAK 1102 |  | 5513273 | CLSD | 08W | HSA1 | Harinderpal Singh Aulakh |  |  |  |  | Not in the WP |  |  | MRYSVLLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31134351 | +MESA 1102 (JOSHUA ST & ORCHARD RD) |  | 5513266 | CLSD | 08W | S3B2 | Shahryar Bayat |  |  |  |  | Not in the WP |  |  | SNLUISOB | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31136738 | X-KING CITY 1102 WD 15-0009162 |  | 5513259 | CLSD | 08W | MTTA | Musie Tsegay Tesfasilassie |  |  |  |  | Not in the WP |  |  | KINGCITY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31139913 | +SANTA MARIA 1110 ANNEALED RIVER X-ING |  | 5513266 | CLSD | 08W | KGH6 | Kenneth G Huffman |  |  |  |  | Not in the WP |  |  | STMARIA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31140055 | OCGC RECONDUCTOR PUEBLO 2103 AT SW 7927 | P.10252 | 5513268 | CLSD | 08W | S2J9 | Steven Kenneth Jackson | A8G1 | Alvin Galesic |  |  | Not in the WP |  |  | NAPA | North Bay Assets | [11 empty] | 81025 | -53135 | 134160 | 96664.3 | 0 | 37495.7 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31143734 | 2016 REEDLEY 1104 WIRE DOWN RECONDUCT | P.09817 | 5513263 | CLSD | 08W | JKH3 | Jacqueline Kay Henry-Larmond | J1EP | Joni Eldred |  |  | Not in the WP |  |  | DINUBA | Fresno Assets | [11 empty] | 74642 | -159358 | 234000 | 112607.5 | 0 | 121392.5 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31144558 | WDN 15-0013313 CE2105-HUBBARD GULCH | P.09907 | 5513259 | CLSD | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  |  | STCRUZ | Central Coast Assets | [11 empty] | 124617 | -133883 | 258500 | 158320 | 0 | 100180 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31144778 | OCGC TRINIDAD 1102 EXCESSIVE SPLICES |  | 5513264 | CLSD | 08W | SLH8 | Shawn Leslie Howard |  |  |  |  | Not in the WP |  |  | EUREKA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31145622 | OCGC 2016 CORCORAN 1108 RECOND WIREDOWN |  | 5513263 | CLSD | 08W | RWC7 | Rickey W Cowin |  |  |  |  | Not in the WP |  |  | LEMOORE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31150684 | MORAGA 1103 RECNDUCTOR 350' (2SPANS) |  | 5513261 | CLSD | 08W | MFN3 | Mary Frances Nunez-Westwater |  |  |  |  | Not in the WP |  |  | CONCORD | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31152787 | OCLH CLOVIS 2110 WIRE DOWN RECONDUCTOR |  | 5513263 | CLSD | 08W | DET3 | Daniel Edward Thomas |  |  |  |  | Not in the WP |  |  | FRESNO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31153724 | OCGC BANTA 1103 RECOND 968FT 6CU |  | 5513276 | CLSD | 08W | DET3 | Daniel Edward Thomas |  |  |  |  | Not in the WP |  |  | TRACY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31154886 | OCGC EP RECONDUCTOR ARBUCKLE 1102 -Y2016 |  | 5513271 | CLSD | 08W | SDK6 | Scott David Kostka |  |  |  |  | Not in the WP |  |  | MRYSVLLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31156130 | SAN ARDO 1102 WD #15-0024843 |  | 5513259 | CLSD | 08W | S3B2 | Shahryar Bayat |  |  |  |  | Not in the WP |  |  | KINGCITY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31157545 | OCGC HARDWICK 1102 WIRE DWN RECNDUCTOR |  | 5513263 | CLSD | 08W | DAV0 | Daniel Van Groningen |  |  |  |  | Not in the WP |  |  | SELMA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31157953 | RECON 1SPAN N/O FISH ROCK GUALALA1112 |  | 5513264 | CLSD | 08W | DRN3 | Dale Robert Novakovich |  |  |  |  | Not in the WP |  |  | FTBRAGG | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31163618 | SOLEDAD 2102 RECONDUCTORING JOB |  | 5513259 | CLSD | 08W | S3B2 | Shahryar Bayat |  |  |  |  | Not in the WP |  |  | KINGCITY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31163857 | X LOS OSITOS 2102 WDWN_15-0036239 |  | 5513259 | CLSD | 08W | S3B2 | Shahryar Bayat |  |  |  |  | Not in the WP |  |  | KINGCITY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31169728 | 2017 GRIZZLY PEAK REPL #6 CU-UWF | P.11397 | 5530162 | CLSD | 08W | M2HM | Matthew Joseph Herron | J1EP | Joni Eldred | J7TY | Jace Thorsen | Not in the WP |  |  | OAKPORT | East Bay Assets | [11 empty] | 1308187 | 380153 | 928034 | 718127 | 0 | 209907 | On/Under Budget | 0 | 0 | 0 | 0 | 756435.6 | -94297.8 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31169729 | OCGCABILITY 2017 D1112/K1101 UWF |  | 5530162 | CLSD | 08W | CAHW | Carolina A Huerta |  |  |  |  | Not in the WP |  |  | RICHMOND | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31170650 | X-SAN BENITO 2101 WIREDOWN 15-0039468 |  | 5513259 | CLSD | 08W | M2KU | Mamadou Keita |  |  |  |  | Not in the WP |  |  | HOLLISTR | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31173660 | OCGC SANTA ROSA A 1108 RECOND 6SPANS |  | 5513275 | CLSD | 08W | JBJ8 | Jeffrey Burbank Jung |  |  |  |  | Not in the WP |  |  | STROSA | [26 empty] | 676.7 | Project is not in the WP or in 2020 WP | 0 | 676.7 | -676.7 | 0 | 0
31175817 | +OCEANO 1108 WIREDOWN 15-0043519 | P.11011 | 5513266 | CLSD | 08W | KWB6 | Kenneth W Brem |  |  |  |  | Not in the WP |  |  | STMARIA | Los Padres Assets | [11 empty] | 156541 | -30459 | 187000 | 87077 | 0 | 99923 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31204479 | RECOND 3 SPANS GARDEN TRACT |  | 5513262 | CLSD | 08W | MYL5 | Michael Y. Lee |  |  |  |  | Not in the WP |  |  | RICHMOND | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31204706 | MVWF THROCKMORTON LANE ALTO 1124 | P.11192 | 5530168 | CLSD | 08W | S2J9 | Steven Kenneth Jackson | A8G1 | Alvin Galesic |  |  | Not in the WP |  |  | SNRAFAEL | North Bay Assets | [11 empty] | 589459 | 0 | 589459 | 528490.1 | 0 | 60968.9 | On/Under Budget | 0 | 0 | 0 | 0 | 406864.2 | 12026.9 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31205198 | MVWF 206 REED ST, COUNTY, ALTO 1125 | P.11152 | 5530168 | CLSD | 08W | S2J9 | Steven Kenneth Jackson | A8G1 | Alvin Galesic |  |  | Not in the WP |  |  | SNRAFAEL | North Bay Assets | [11 empty] | 1586740 | 338780 | 1247960 | 962856.9 | 0 | 285103.1 | On/Under Budget | 0 | 0 | 0 | 0 | 919522.3 | 1597.9 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31205343 | MVWF 388 SUMMIT AVE, CITY, ALTO 1124 | P.11151 | 5530168 | CLSD | 08W | S2J9 | Steven Kenneth Jackson | A8G1 | Alvin Galesic |  |  | Not in the WP |  |  | SNRAFAEL | North Bay Assets | [11 empty] | 1873987 | 370716 | 1503271 | 1154944.1 | 0 | 348326.9 | On/Under Budget | 0 | 0 | 0 | 0 | 1182715.1 | -74358.1 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31205418 | MVWF BROOKLINE AVE, COUNTY, ALTO 1125 | P.11156 | 5530168 | CLSD | 08W | S2J9 | Steven Kenneth Jackson | A8G1 | Alvin Galesic |  |  | Not in the WP |  |  | SNRAFAEL | North Bay Assets | [11 empty] | 1603391 | 277448 | 1325943 | 994666 | 0 | 331277 | On/Under Budget | 0 | 0 | 0 | 0 | 937200.7 | 14323.4 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31205937 | 109 HELENS LN,CITY/CNTY,ALTO | P.11155 | 5530168 | CLSD | 08W | S2J9 | Steven Kenneth Jackson | A8G1 | Alvin Galesic |  |  | Not in the WP |  |  | SNRAFAEL | North Bay Assets | [11 empty] | 1925702 | 368352 | 1557350 | 1275048.9 | 0 | 282301.1 | On/Under Budget | 0 | 0 | 0 | 0 | 1212911.2 | 2349.6 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35175132 | *CANC* - PLACERVILLE 2106 - LR1104 - PH |  | 5530173 | CNCL | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | 5530169 | CONS | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 9316 | 9316 | 1.7644 | 1.7644 | 0 | 9316 | 0 | 1.7644 | 0 | Contract | 347534 | 0 | 347534 | 126223.4 | 0 | 221310.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 641.1 | 124210.3 | 1372 | Project is not in the WP or in 2020 WP | 0 | 1372 | -1372 | 1372 | -1372 | 0 | 229.9 | 1142.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145878 | BL-0 | BL-0 35135864_CWSP - GRAYS FLAT 401 FUSE 3079 ZONE_08W - Oct. 2020 | 2020-07-25 | 2020-02-07 | Completed | 2020-05-20 | 2020-05-20 | Completed | 2020-03-26 | Completed | 2020-06-15 | Completed | 2020-02-28 | 2020-02-28 | Completed | 2020-04-16 | 2020-04-17 | Completed | 2019-10-29 | 2019-11-05 | Completed | 2020-05-26 | Completed |  |  |  |  | 2020-05-26 | Completed | 2020-08-05 | Completed | 2020-08-05 | Completed | 2020-10-14 | 2020-08-05 | 70 | On/ Ahead Schedule | Completed | 2020-08-10 | 2020-08-19 | Completed | 2021-05-10 | Not Started
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | 5784869 | CONS | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 |  |  | NAPA | North Bay Assets | 0 | 0 | 0 | 0 | 0 | 0 | 6693 | 0 | 1.2676 | 0 | GC | 1800635 | 396300.6 | 1404334.4 | 1553760 | 0 | -149425.6 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 475981 | 1077779 | Request 2021 Budget | 0 | 1077779 | -1077779 | 1077779 | -1077779 | -33984.5 | -9801.2 | 1121564.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | E.5034391.01 | 5792082 | CONS | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH - Wind | OAKHURST | Yosemite Assets | 0 | 10401.6 | 10401.6 | 1.97 | 2.1869 | -0.21693 | 11569 | 0 | 2.1911 | 0 | GC | 1877409.58 | 1877409.58 | 0 | 1539087.6 | 761327.5 | -777760.1 | OverRun | 59156.1 | 292562.3 | -18419.4 | 310981.7 | 0 | 0 | 6362.5 | 1514305.7 | Budget Allocated | 2843023 | 1884443.5 | 958579.5 | 1884443.5 | 958579.5 | 50073.4 | 1187832.4 | 294819.3 | 292562.3 | 50043.3 | 2278.2 | 2278.2 | 2278.2 | 2278.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-01-23 | Completed | 2021-02-25 | 2021-03-02 | Completed | 2021-03-02 | Completed |  |  | 2021-02-04 | 2021-02-04 | Completed | 2021-02-04 | 2021-02-05 | Completed | 2021-02-08 | 2021-03-15 | Completed | 2021-02-08 | Completed |  |  |  |  | 2021-02-08 | Completed | 2021-03-15 | Completed | 2021-03-18 | Completed | 2021-05-20 | 2021-03-18 | 63 | On/ Ahead Schedule | Completed | 2021-04-05 | 2021-04-16 | Not Started | 2021-06-29 | Not Started
35193883 | BUCOCAMPTUG 622 PEARSON RD PARADISE |  | 5791246 | CONS | 08W | DXFO | David Farris |  |  |  |  | Not in the WP |  |  | CHICO | [26 empty] | 36301.2 | Project is not in the WP or in 2020 WP | 0 | 60305.1 | -60305.1 | 0 | 0
35200008 | BUCOCAMPTUG MOORE RD PARADISE UG SHORT |  | 5791246 | CONS | 08W | J4VB | Jorge Vargas | Fire Rebuild | Fire Rebuild | Fire Rebuild | Fire Rebuild | Not in the WP |  |  | CHICO | [26 empty] | 139821.8 | Project is not in the WP or in 2020 WP | 0 | 150443.5 | -150443.5 | 0 | 0
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | E.5034572.01.12 | 5793918 | CONS | 08W | JTHL | Joseph T Hembree | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2021 | FRRB | OROVILLE | North Valley Assets | 5647 | 0 | 5647 | 1.0695 | 0 | 1.0695 | 4798 | 0 | 0.90871 | 0 | GC | 4380690 | 1219728.7 | 3160961.3 | 1133997.8 | 261121.4 | 2288084.9 | On/Under Budget | 63587 | 996540.8 | 47407.7 | 949133.1 | 0 | 0 | 0 | 1181405.6 | Budget Allocated | 3743276.52 | 3743275 | 1.52 | 2194125.7 | 1549150.82 | 93.8 | 69389.7 | 1064514.4 | 996540.8 | 37503.5 | 21510 | 4573.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157630 | BL-0 | BL-0 35225822_FRRB - Wyandotte 1103 - Bald Rock Zone 6_08W - Mar. 2021 | 2021-03-16 | 2021-02-16 | Completed | 2021-03-01 | 2021-03-05 | Completed | 2021-02-18 | Completed | 2021-03-03 | Completed | 2021-03-01 | 2021-04-05 | In Progress | 2021-04-06 | 2021-04-09 | Not Started | 2020-11-10 | 2020-12-15 | Completed | 2021-03-01 | Completed | 2021-03-01 | Completed | 2021-04-19 | Not Started | 2021-04-20 | Not Started | 2021-06-01 | Not Started | 2021-06-23 | Not Started | 2021-07-26 | 2021-07-26 | 0 | On/ Ahead Schedule | Not Started | 2021-07-27 | 2021-08-09 | Not Started | 2021-09-22 | Not Started
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | E.5034572.01.13 | 5793918 | CONS | 08W | JTHL | Joseph T Hembree | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2021 | FRRB | OROVILLE | North Valley Assets | 7340 | 0 | 7340 | 1.3902 | 0 | 1.3902 | 8431 | 0 | 1.5968 | 0 | GC | 6586891 | 1685778.4 | 4901112.6 | 173035.1 | 491237.2 | 5219314.7 | On/Under Budget | 4655228.6 | 772.2 | -27102.1 | 27874.3 | 0 | 0 | 0 | 145933 | Budget Allocated | 4901112 | 4819819 | 81293 | 4829035.7 | 72076.3 | 0 | 87486.3 | 85548.8 | 772.2 | 772.2 | 798678.2 | 798694.8 | 798694.8 | 798300.4 | 797906 | 662182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157920 | BL-0 | BL-0 35225823_FRRB - Wyandotte 1103 - LR 1976 Zone 7_08W - Mar. 2021 | 2021-03-23 | 2021-02-02 | Completed | 2021-03-01 | 2021-03-12 | Completed | 2021-02-23 | Completed | 2021-02-23 | Completed | 2021-03-29 | 2021-05-07 | In Progress | 2021-05-10 | 2021-05-10 | Not Started | 2020-11-18 | 2020-12-18 | Completed | 2021-05-12 | Not Started | 2021-05-12 | Not Started | 2021-07-13 | Not Started | 2021-06-30 | Not Started | 2021-08-05 | Not Started | 2021-08-20 | Not Started | 2021-10-22 | 2021-10-22 | 0 | On/ Ahead Schedule | Not Started | 2021-10-25 | 2021-11-09 | Not Started | 2021-12-21 | Not Started
35112220 | BR-04-06-W (E) VALLEY RIDGE PARB |  | 5786123 | CONS | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 1030719.49 | 800200.49 | 230519 | 55691.9 | 61216.1 | 236043.2 | On/Under Budget | 5046.3 | 12253.7 | -44550.6 | 56804.3 | 0 | 66867.5 | 264437.7 | -320163.8 | Project is not in the WP or in 2020 WP | 0 | -258313.2 | 258313.2 | -258313.2 | 258313.2 | -19842 | -221293.8 | -34477.4 | 12253.7 | 5046.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | E.5015489.02 | 5786131 | CONS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 | 2020 | SH | SALINAS | Central Coast Assets | 0 | 5487 | 5487 | 1.0392 | 0 | 1.0392 | 5487 | 0 | 1.0392 | 0 | GC | 2501285 | 556888.1 | 1944396.9 | 431962.8 | 53601.8 | 1566035.9 | On/Under Budget | 1433.9 | 955.9 | -223 | 1178.9 | 0 | 7067.3 | 393838.1 | 30834.3 | Request 2021 Budget | 0 | 33447 | -33447 | 33447 | -33447 | 16145.2 | 9339 | 5573.1 | 955.9 | 955.9 | 477.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157099 | BL-0 | BL-0 35114100_CWSP - Camp Evers 2106 - LR5020 - PH 2.2_08W - Mar. 2021 | 2021-03-07 | 2020-05-18 | Completed | 2020-05-20 | 2020-05-28 | Completed | 2020-06-12 | Completed | 2020-06-26 | Completed | 2020-05-29 | 2020-07-14 | Completed | 2020-06-15 | 2020-07-24 | Completed | 2020-06-01 | 2020-11-30 | Completed | 2020-07-27 | Completed |  |  |  |  | 2020-07-27 | Completed | 2021-04-19 | Not Started | 2021-04-19 | Not Started | 2021-11-17 | 2021-09-17 | 61 | On/ Ahead Schedule | Not Started | 2021-04-26 | 2021-04-30 | Not Started | 2022-02-10 | Not Started
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | E.5014742.06 | 5786000 | CONS | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | JACKSON | Stockton Assets | 0 | 7628 | 7628 | 1.4447 | 0 | 1.4447 | 7698 | 0 | 1.458 | 0 |  | 5342998 | 1393320.2 | 3949677.8 | 764746.1 | 2739.3 | 3187671 | On/Under Budget | 1741323.2 | 807294.1 | 0 | 807294.1 | 0 | 470.6 | 602117.9 | 162157.5 | Request 2021 Budget | 0 | 2640208.6 | -2640208.6 | 2640208.6 | -2640208.6 | 4523.5 | 20700.5 | 136933.5 | 807294.1 | 627293 | 768167.2 | 98087.8 | 101636 | 21673.9 | 21707.7 | 16095.7 | 16095.7 | 15681.4 | 15681.4 | 15681.4 | 15681.4 | 7840.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70566.3 | 2021-04-02 | 154954 | BL-0 | BL-0 35114051_CWSP - PINE GROVE 1102 - LR1222 - PH 2.6_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-05-19 | Completed | 2020-07-14 | 2020-07-27 | Completed | 2020-07-28 | Completed | 2020-07-29 | Completed | 2020-08-31 | 2020-08-31 | Completed | 2020-09-01 | 2020-11-30 | Completed | 2020-08-25 | 2020-10-10 | Completed | 2020-10-02 | Completed |  |  |  |  | 2020-10-02 | Completed | 2021-05-10 | Not Started | 2021-05-10 | Not Started | 2022-06-14 | 2021-06-09 | 370 | On/ Ahead Schedule | Not Started | 2021-05-18 | 2021-05-31 | Not Started | 2021-07-30 | Not Started
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | E.5014534.04 | 5786054 | CONS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 | 2020 | SH | CUPRTINO | De Anza Assets | 0 | 3807 | 3807 | 0.72102 | 0 | 0.72102 | 3807 | 0 | 0.72102 | 0 | GC | 2054719 | 474898 | 1579821 | 1217601.3 | 90411.3 | 452631 | On/Under Budget | 40201.4 | 344897.9 | -1517.8 | 346415.7 | 0 | 1516.3 | 959055.8 | 255511.4 | Request 2021 Budget | 0 | 642128.5 | -642128.5 | 642128.5 | -642128.5 | 32512.1 | 108870 | 115647.1 | 344897.9 | 40201.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156104 | BL-A | BL-A 35113108_CWSP - Los Gatos 1106 - LB44 - Phase 2.4D_08W - Feb. 2021 | 2021-02-20 | 2019-10-31 | Completed | 2020-04-02 | 2020-04-30 | Completed | 2020-02-24 | Completed | 2020-02-24 | Completed | 2020-03-25 | 2020-05-08 | Completed | 2020-04-01 | 2020-08-06 | Completed | 2020-04-21 | 2020-06-03 | Completed | 2020-08-03 | Completed |  |  |  |  | 2020-08-03 | Completed | 2021-04-14 | Not Started | 2021-04-14 | Not Started | 2021-06-30 | 2021-07-14 | -14 | Behind Schedule | Not Started | 2021-07-15 | 2021-07-28 | Not Started | 2021-08-11 | Not Started
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | E.5014742.03 | 5785997 | CONS | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | JACKSON | Stockton Assets | 0 | 7344 | 7344 | 1.3909 | 0 | 1.3909 | 7344 | 0 | 1.3909 | 0 | GC | 4178929 | 1045029.6 | 3133899.4 | 1212993.5 | 140247.1 | 2061153 | On/Under Budget | 5628.9 | 258613 | -250 | 258863 | 0 | 0 | 920063.8 | 292679.8 | Budget Allocated | 1810131 | 557171.7 | 1252959.3 | 557171.7 | 1252959.3 | 102650 | 69494.1 | 120785.7 | 258613 | 5628.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 154913 | BL-0 | BL-0 35114048_CWSP - PINE GROVE 1102 - LR1222 - PH 2.3_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-06-02 | Completed | 2020-06-26 | 2020-07-16 | Completed | 2020-06-08 | Completed | 2020-07-16 | Completed | 2020-07-28 | 2020-07-31 | Completed | 2020-07-31 | 2020-08-11 | Completed | 2020-07-21 | 2020-10-03 | Completed | 2020-08-14 | Completed |  |  |  |  | 2020-08-12 | Completed | 2021-05-25 | Not Started | 2021-05-25 | Not Started | 2021-05-07 | 2021-05-26 | -19 | Behind Schedule | Not Started | 2021-06-09 | 2021-06-22 | Not Started | 2021-07-15 | Not Started
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | E.5014742.04 | 5785998 | CONS | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | JACKSON | Stockton Assets | 0 | 8392 | 8392 | 1.5894 | 1.5189 | 0.070455 | 8392 | 0 | 1.5894 | 0 | GC | 2193681.27 | -1129156.03 | 3322837.3 | 1058009.2 | 119722 | 2384550.1 | On/Under Budget | 0 | 0 | -1043.4 | 1043.4 | 0 | 470.6 | 1036858.3 | 19637.1 | Request 2021 Budget | 0 | 20680.5 | -20680.5 | 20680.5 | -20680.5 | 4201.2 | 7561.2 | 8918.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 154914 | BL-0 | BL-0 35114049_CWSP - PINE GROVE 1102 - LR1222 - PH 2.4_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-04-24 | Completed | 2020-05-22 | 2020-06-09 | Completed | 2020-06-08 | Completed | 2020-06-29 | Completed | 2020-07-02 | 2020-07-02 | Completed | 2020-07-03 | 2020-07-24 | Completed | 2020-06-30 | 2020-07-22 | Completed | 2020-07-21 | Completed |  |  |  |  | 2020-07-21 | Completed | 2021-04-23 | Not Started | 2020-08-18 | Completed | 2021-03-01 | 2021-04-26 | -56 | Behind Schedule | Not Started | 2021-05-03 | 2021-05-07 | Not Started | 2021-06-15 | Not Started
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | E.5014745.02 | 5785991 | CONS | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2022 |  | SH | JACKSON | Stockton Assets | 477 | 7362 | 7839 | 1.4847 | 0 | 1.4847 | 7860 | 0 | 1.4886 | 0 | GC | 4232824 | 1125591.9 | 3107232.1 | 1229529 | 43154 | 1920857.1 | On/Under Budget | 1559754.6 | 79319 | -1010.7 | 80329.7 | 0 | 0 | 1145736.3 | 82782 | Request 2021 Budget | 0 | 1722866.3 | -1722866.3 | 1722866.3 | -1722866.3 | 65502 | 6710.5 | 11580.2 | 79319 | 419289.2 | 700350.5 | 440114.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 154955 | BL-0 | BL-0 35114040_CWSP - PINE GROVE 1102 - LR1222 - PH 1.2_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-04-24 | Completed | 2020-06-18 | 2020-07-06 | Completed | 2021-06-25 | Not Started | 2020-07-07 | Completed | 2020-07-20 | 2020-07-20 | Completed | 2020-07-31 | 2020-08-06 | Completed | 2020-07-13 | 2020-07-31 | Completed | 2020-07-29 | Completed |  |  |  |  | 2020-07-29 | Completed | 2021-07-16 | Not Started | 2021-07-16 | Not Started | 2021-06-03 | 2021-08-17 | -75 | Behind Schedule | Not Started | 2021-07-26 | 2021-08-06 | Not Started | 2021-10-07 | Not Started
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | E.5014745.03 | 5785992 | CONS | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 6879 | 6879 | 1.3028 | 0 | 1.3028 | [5 empty] | 2760383 | 868839 | 1891544 | 400180.9 | 0 | 1491363.1 | On/Under Budget | 1022010.1 | 263.6 | -250 | 513.6 | 0 | 633.3 | 388054.7 | 11242.9 | Project is not in the WP or in 2020 WP | 0 | 11756.5 | -11756.5 | 11756.5 | -11756.5 | 5489 | 2291.1 | 3712.8 | 263.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 492725.6 | 492944.2 | 36340.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1022010 | 2021-04-02 | 154915 | BL-0 | BL-0 35114041_CWSP - PINE GROVE 1102 - LR1222 - PH 1.3_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-06-17 | Completed | 2020-06-26 | 2020-07-16 | Completed | 2020-06-15 | Completed | 2020-07-16 | Completed | 2020-08-03 | 2020-08-03 | Completed | 2020-08-07 | 2020-08-11 | Completed | 2020-07-27 | 2020-08-25 | Completed | 2022-03-07 | Not Started |  |  |  |  | 2022-03-07 | Not Started | 2022-05-03 | Not Started | 2022-05-03 | Not Started | 2022-06-14 | 2022-06-14 | 0 | On/ Ahead Schedule | Not Started | 2022-06-15 | 2022-06-28 | Not Started | 2022-08-04 | Not Started
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | E.5014773.05 | 5785979 | CONS | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | SONORA | Yosemite Assets | 0 | 9032 | 9032 | 1.7106 | 1.2 | 0.51061 | 9032 | 0 | 1.7106 | 0 | GC | 3714853 | 1234918.8 | 2479934.2 | 1171618.2 | 73064 | 1381380 | On/Under Budget | 2110.8 | 144087 | 5866.6 | 138220.4 | 0 | 200.3 | 609523.2 | 567761.3 | Request 2021 Budget | 0 | 708092.5 | -708092.5 | 708092.5 | -708092.5 | 134721 | 157392.4 | 269781.3 | 144087 | 2110.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 151439 | BL-1 | BL-1 35116395_CWSP - MIWUK 1702 - OCB - PH 1.5_08W - Nov. 2020 | 2020-11-12 | 2020-05-22 | Completed | 2020-06-30 | 2020-07-16 | Completed | 2020-05-29 | Completed | 2020-07-06 | Completed | 2020-07-16 | 2020-07-16 | Completed | 2020-08-04 | 2020-08-18 | Completed | 2020-07-22 | 2020-09-15 | Completed | 2021-01-11 | Completed | [6 empty] | 2021-04-13 | Not Started | 2021-04-02 | Completed | 2021-01-29 | 2021-04-23 | -84 | Behind Schedule | Not Started | 2021-04-27 | 2021-05-10 | Not Started | 2021-09-16 | Not Started
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | E.5014722.02 | 5785929 | CONS | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 11216 | 11216 | 2.1242 | 0 | 2.1242 | [5 empty] | 6123271 | 1791846.5 | 4331424.5 | 576261.5 | 0 | 3755163 | On/Under Budget | 3029652.6 | 625.3 | 0 | 625.3 | 0 | 2160.8 | 553655.6 | 20445.1 | Project is not in the WP or in 2020 WP | 0 | 26210.2 | -26210.2 | 26210.2 | -26210.2 | 4224.8 | 9611.6 | 6608.7 | 625.3 | 625.3 | 625.3 | 648.2 | 648.2 | 648.2 | 648.2 | 648.2 | 648.2 | 524204.9 | 344858.5 | 25516.6 | 1214289.7 | 614506.5 | 253902 | 18893.7 | 18893.7 | 9446.9 | 0 | 0 | 0 | 3024512.5 | 2021-04-02 | 145958 | BL-B | BL-B 35116396_CWSP - MIWUK 1702 - LR 8090 - PH 1.2_08W - NOV 2021 | 2020-07-26 | 2020-05-30 | Completed | 2020-08-24 | 2020-09-14 | Completed | 2020-07-14 | Completed | 2020-07-15 | Completed | 2020-08-10 | 2020-11-06 | Completed | 2020-11-09 | 2020-11-09 | Completed |  |  |  | 2022-03-22 | Not Started |  |  |  |  | 2022-03-22 | Not Started | 2022-07-07 | Not Started | 2022-09-22 | Not Started | 2021-11-23 | 2022-09-22 | -303 | Behind Schedule | Not Started | 2022-07-29 | 2022-08-11 | Not Started | 2023-02-16 | Not Started
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | E.5015235.03 | 5786023 | CONS | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 5916 | 5916 | 1.1205 | 0 | 1.1205 | [5 empty] | 868859.26 | -1269754.74 | 2138614 | 155049 | 807420 | 2790985 | On/Under Budget | 1011032.2 | 198 | 0 | 198 | 0 | 1552 | 145946.7 | 7550.3 | Project is not in the WP or in 2020 WP | 0 | 9375.5 | -9375.5 | 9375.5 | -9375.5 | 4945.7 | 1015.9 | 1588.7 | 198 | 198 | 198 | 205.2 | 205.2 | 205.2 | 205.2 | 205.2 | 205.2 | 3092.3 | 307792.8 | 959909.9 | 23587.1 | 8008.3 | 8008.3 | -300993.9 | 0 | 0 | 0 | 0 | 0 | 1009404.8 | 2021-04-02 | 154962 | BL-0 | BL-0 35115854_CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1.3_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-05-15 | Completed | 2020-08-20 | 2020-08-21 | Completed | 2020-10-27 | Completed | 2020-08-31 | Completed | 2022-02-21 | 2022-02-21 | Not Started | 2022-02-22 | 2022-03-21 | Not Started | 2020-08-31 | 2020-10-24 | Completed | 2022-07-12 | Not Started |  |  |  |  | 2022-07-12 | Not Started | 2022-09-07 | Not Started | 2022-09-21 | Not Started | 2022-08-12 | 2022-10-21 | -70 | Behind Schedule | Not Started | 2022-10-24 | 2022-11-04 | Not Started | 2022-12-13 | Not Started
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | E.5014733.02 | 5785966 | CONS | 08W | M2HM | Matthew Joseph Herron | J1EP | Joni Eldred | J7TY | Jace Thorsen | 2021 |  | SH | SONORA | Yosemite Assets | 0 | 7319 | 7319 | 1.3862 | 0.75 | 0.63617 | 7319 | 0 | 1.3862 | 0 | Contract | 3758449 | 1211428 | 2547021 | 1317528.6 | 361803.4 | 1591295.8 | On/Under Budget | 14561.1 | 331972.8 | -43430.9 | 375403.7 | 0 | 15415.3 | 981805.6 | 276876.8 | Request 2021 Budget | 0 | 666841.7 | -666841.7 | 666841.7 | -666841.7 | 63384.6 | 23063.3 | 233859.8 | 331972.8 | 5414.2 | 3049 | 3049 | 3049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156215 | BL-2 | BL-2 35116383_CWSP - MIWUK 1701 - LR 8060 - PH 1.2_08W - DD 210219 Feb. 2021 | 2021-02-23 | 2019-12-02 | Completed | 2020-06-30 | 2020-06-30 | Completed | 2020-11-06 | Completed | 2020-06-30 | Completed | 2020-11-06 | 2020-11-06 | Completed | 2020-11-06 | 2020-11-09 | Completed | 2020-11-06 | 2020-11-12 | Completed | 2021-03-08 | Completed |  |  |  |  | 2021-03-08 | Completed | 2021-05-05 | Not Started | 2021-05-12 | Not Started | 2021-06-30 | 2021-06-30 | 0 | On/ Ahead Schedule | Not Started | 2021-07-01 | 2021-07-14 | Not Started | 2021-08-20 | Not Started
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | E.5014733.03 | 5785967 | CONS | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | SONORA | Yosemite Assets | 0 | 9700 | 9700 | 1.8371 | 0 | 1.8371 | 9700 | 0 | 1.8371 | 0 | Contract | 4624169 | 1384789.4 | 3239379.6 | 592973.6 | 912157.3 | 3558563.3 | On/Under Budget | 348361.4 | 582446.1 | 21199.1 | 561247 | 0 | 202.9 | 103744.5 | 510225.4 | Request 2021 Budget | 0 | 1419833.8 | -1419833.8 | 1419833.8 | -1419833.8 | 19034.7 | 3271.6 | 466720 | 582446.1 | 583321.4 | 0 | -117480 | -117480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 152833 | BL-1 | BL-1 35116384_CWSP - MIWUK 1701 - LR 8060 - PH 1.3_08W - Dec. 2020 | 2020-12-29 | 2020-05-08 | Completed | 2020-07-16 | 2020-07-16 | Completed | 2020-06-22 | Completed | 2020-10-30 | Completed | 2020-11-02 | 2020-11-02 | Completed | 2021-04-06 | 2021-04-13 | Not Started | 2020-09-01 | 2020-11-02 | Completed | 2021-04-14 | Not Started |  |  |  |  | 2021-04-14 | Not Started | 2021-05-27 | Not Started | 2021-06-04 | Not Started | 2021-04-22 | 2021-06-07 | -46 | Behind Schedule | Not Started | 2021-06-09 | 2021-06-10 | Not Started | 2021-06-10 | Not Started
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | E.5014776.04 | 5785983 | CONS | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 10249 | 10249 | 1.9411 | 0 | 1.9411 | [5 empty] | 4826121 | 1480335.8 | 3345785.2 | 747162.2 | 0 | 2598623 | On/Under Budget | 202479.2 | 1021.7 | -250 | 1271.7 | 0 | 441.5 | 812043 | -65572.3 | Project is not in the WP or in 2020 WP | 0 | -55891.8 | 55891.8 | -55891.8 | 55891.8 | -7344.4 | -2956.5 | -55021.4 | 1021.7 | 1021.7 | 1021.7 | 1060.9 | 1060.9 | 1060.9 | 1060.9 | 1060.9 | 1060.9 | 129415.5 | 329383.3 | 18872.9 | 1958.9 | -285560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194070.6 | 2021-04-02 | 151456 | BL-0 | BL-0 35116443_CWSP - MIWUK 1702 - LR 38218 - PH 1.4_08W - Nov. 2020 | 2020-11-12 | 2020-04-16 | Completed | 2020-07-15 | 2020-07-20 | Completed | 2020-03-03 | Completed | 2020-07-27 | Completed | 2020-08-03 | 2020-08-03 | Completed | 2020-08-11 | 2020-08-11 | Completed | 2020-08-03 | 2020-08-21 | Completed | 2020-09-01 | Completed |  |  |  |  | 2020-09-01 | Completed | 2022-03-23 | Not Started | 2022-04-07 | Not Started | 2021-04-09 | 2022-05-06 | -392 | Behind Schedule | Not Started | 2022-05-09 | 2022-05-20 | Not Started | 2022-06-28 | Not Started
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | E.5014776.05 | 5785984 | CONS | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | SONORA | Yosemite Assets | 0 | 11100 | 11100 | 2.1023 | 0 | 2.1023 | 11100 | 0 | 2.1023 | 0 | GC | 3531134 | 882956.8 | 2648177.2 | 846949.4 | 147856 | 1949083.8 | On/Under Budget | 183543.4 | 224659.8 | -6726.8 | 231386.6 | 0 | 1350.4 | 884272.9 | -45400.7 | Request 2021 Budget | 0 | 369529.3 | -369529.3 | 369529.3 | -369529.3 | 11764.5 | -93840.8 | 43402.4 | 224659.8 | 183543.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 151457 | BL-0 | BL-0 35116444_CWSP - MIWUK 1702 - LR 38218 - PH 1.5_08W - Nov. 2020 | 2020-11-12 | 2020-04-07 | Completed | 2020-04-27 | 2020-04-27 | Completed | 2020-03-31 | Completed | 2020-07-27 | Completed | 2020-07-15 | 2020-07-15 | Completed | 2020-10-30 | 2020-10-30 | Completed | 2020-03-30 | 2020-06-12 | Completed | 2020-08-04 | Completed |  |  |  |  | 2020-08-04 | Completed | 2021-06-01 | Not Started | 2021-06-16 | Not Started | 2021-04-15 | 2021-07-15 | -91 | Behind Schedule | Not Started | 2021-07-16 | 2021-07-29 | Not Started | 2021-09-06 | Not Started
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | E.5014730.03 | 5785962 | CONS | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | SONORA | Yosemite Assets | 580 | 6197 | 6777 | 1.2835 | 0.37008 | 0.91345 | 6747 | 0 | 1.2778 | 0 | Contract | 3408934 | 1074988.8 | 2333945.2 | 1643074.8 | 381713.7 | 1072584.1 | On/Under Budget | 0 | 217316.5 | -199724.7 | 417041.2 | 0 | 1320.5 | 1385193.6 | 56835.9 | Request 2021 Budget | 0 | 473877.1 | -473877.1 | 473877.1 | -473877.1 | 8463.6 | 14779.5 | 233317.5 | 217316.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145833 | BL-0: | BL-0: 35116801_CWSP - MIWUK 1702 - LR 6018 - PH 1.3_08W - Nov. 2020 | 2020-07-24 | 2020-04-15 | Completed | 2020-06-22 | 2020-07-06 | Completed | 2020-05-05 | Completed | 2020-07-06 | Completed | [6 empty] | 2020-07-20 | 2020-07-27 | Completed | 2020-08-10 | Completed | [6 empty] | 2021-05-04 | Not Started | 2021-05-11 | Not Started | 2020-11-12 | 2021-05-12 | -181 | Behind Schedule | Not Started | 2021-05-12 | 2021-05-25 | Not Started | 2021-10-12 | Not Started
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | CONS | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 10010 | 10010 | 1.8958 | 1.4576 | 0.43826 | 10013 | 0 | 1.8964 | 0 | GC | 5273989 | 1248322.6 | 4025666.4 | 1711449.1 | 150892.4 | 2465109.7 | On/Under Budget | 2046081 | 1646.9 | -31181.5 | 32828.4 | 0 | 0 | 1036914.8 | 643352.7 | Budget Allocated | 2520547.9 | 2722262.1 | -201714.2 | 2722262.1 | -201714.2 | 138183.8 | 180505 | 355845.4 | 1646.9 | 1000000 | 1046081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157117 | BL-1 | BL-1 35115151_CWSP - Brunkswick 1103 LR50070 ZONE-PH2.2_08W - Mar. 2021 | 2021-03-07 | 2020-05-29 | Completed | 2020-07-09 | 2020-07-18 | Completed | 2020-06-05 | Completed | 2020-07-21 | Completed | 2020-07-24 | 2020-07-24 | Completed | 2020-07-27 | 2020-07-28 | Completed | 2020-06-29 | 2020-07-31 | Completed | 2020-08-17 | Completed |  |  |  |  | 2020-08-17 | Completed | 2021-04-15 | Not Started | 2021-04-15 | Not Started | 2021-07-05 | 2021-07-05 | 0 | On/ Ahead Schedule | Not Started | 2021-07-06 | 2021-07-19 | Not Started | 2021-08-25 | Not Started
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | CONS | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 8460 | 8460 | 1.6023 | 0 | 1.6023 | 8271 | 0 | 1.5665 | 0 | GC | 3591121 | 911634.7 | 2679486.3 | 506291.2 | 2381.7 | 2175576.8 | On/Under Budget | 0 | 0 | -41110 | 41110 | 0 | 0 | 450434.8 | 14746.4 | Budget Allocated | 2229051.5 | 2207265.4 | 21786.1 | 55856.4 | 2173195.1 | 3022.9 | 2878.4 | 49955.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156590 | BL-1_ | BL-1_35115152_CWSP - Brunkswick 1103 LR50070 ZONE-PH2.3_08W_Mar. 2021 | 2021-03-02 | 2020-08-25 | Completed | 2020-08-27 | 2020-09-14 | Completed | 2020-08-31 | Completed | 2020-09-17 | Completed | 2021-05-03 | 2021-05-03 | Not Started | 2021-05-04 | 2021-05-04 | Not Started | 2020-07-30 | 2020-09-01 | Completed | 2021-05-31 | Not Started |  |  |  |  | 2021-05-31 | Not Started | 2021-06-30 | Not Started | 2021-07-08 | Not Started | 2021-09-17 | 2021-09-17 | 0 | On/ Ahead Schedule | Not Started | 2021-09-20 | 2021-10-01 | Not Started | 2021-11-09 | Not Started
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | CONS | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 9476 | 9476 | 1.7947 | 0 | 1.7947 | 9476 | 0 | 1.7947 | 0 | GC | 4734585 | 1528234.3 | 3206350.7 | 840364.7 | 173038.4 | 2539024.4 | On/Under Budget | 2781803 | 32376 | -13381.7 | 45757.7 | 0 | 0 | 476027.2 | 350955.8 | Budget Allocated | 3080584.2 | 3178516.5 | -97932.3 | 3178516.5 | -97932.3 | 3294.2 | 31282.6 | 329760.7 | 32376 | 1000000 | 1781803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157121 | BL-1 | BL-1 35115153_CWSP - Brunkswick 1103 LR50070 ZONE-PH2.4_08W - Mar. 2021 | 2021-03-07 | 2020-06-30 | Completed | 2020-07-24 | 2020-07-30 | Completed | 2020-06-05 | Completed | 2020-07-30 | Completed | 2020-07-23 | 2020-07-23 | Completed | 2020-08-21 | 2020-08-21 | Completed | 2020-07-13 | 2020-08-21 | Completed | 2021-03-08 | Completed |  |  |  |  | 2021-03-08 | Completed | 2021-05-14 | Not Started | 2021-05-21 | Not Started | 2021-08-11 | 2021-08-11 | 0 | On/ Ahead Schedule | Not Started | 2021-08-12 | 2021-08-25 | Not Started | 2021-10-01 | Not Started
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | CONS | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 8692 | 8692 | 1.6462 | 0 | 1.6462 | 8692 | 0 | 1.6462 | 0 | GC | 3872109 | 1075736.8 | 2796372.2 | 1322881.6 | 143959.1 | 1617449.7 | On/Under Budget | 2299034 | 0 | 5214.6 | -5214.6 | 0 | 3521.5 | 969527.1 | 355047.7 | Budget Allocated | 2584854.1 | 2648867.1 | -64013 | 2648867.1 | -64013 | 95427.3 | 63115.7 | 191290.1 | 0 | 1299034 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157122 | BL-1 | BL-1 35115154_CWSP - Brunkswick 1103 LR50070 ZONE-PH2.5_08W - Mar. 2021 | 2021-03-07 | 2020-06-30 | Completed | 2020-07-24 | 2020-07-30 | Completed | 2020-06-05 | Completed | 2020-07-30 | Completed | 2020-07-23 | 2020-07-23 | Completed | 2020-08-20 | 2020-08-20 | Completed | 2020-07-22 | 2020-10-15 | Completed | 2021-03-17 | Completed |  |  |  |  | 2021-03-17 | Completed | 2021-05-07 | Not Started | 2021-05-14 | Not Started | 2021-08-06 | 2021-08-06 | 0 | On/ Ahead Schedule | Not Started | 2021-08-09 | 2021-08-20 | Not Started | 2021-09-28 | Not Started
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | E.5015489.04 | 5786133 | CONS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 | 2020 | SH | SALINAS | Central Coast Assets | 0 | 3909 | 3909 | 0.74034 | 0.16004 | 0.5803 | 4147 | 0 | 0.78542 | 0 | GC | 1763594 | 310101.6 | 1453492.4 | 622771.1 | 149390.7 | 980112 | On/Under Budget | 3436.9 | 1365.4 | -1133.7 | 2499.1 | 0 | 2114.2 | 585256.5 | 34266.6 | Request 2021 Budget | 0 | 40202.7 | -40202.7 | 40202.7 | -40202.7 | 21980.3 | 5799.4 | 7620.6 | 1365.4 | 1365.4 | 1365.4 | 706.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157100 | BL-0 | BL-0 35114102_CWSP - Camp Evers 2106 - LR5020 - PH 2.4_08W - Mar. 2021 | 2021-03-07 | 2020-04-27 | Completed | 2020-05-07 | 2020-05-19 | Completed | 2020-03-16 | Completed | 2020-05-01 | Completed | 2020-04-28 | 2020-05-01 | Completed | 2020-05-01 | 2020-07-28 | Completed | 2020-05-19 | 2020-06-23 | Completed | 2020-08-04 | Completed |  |  |  |  | 2020-08-04 | Completed | 2021-04-22 | Not Started | 2021-04-26 | Not Started | 2021-11-17 | 2021-09-22 | 56 | On/ Ahead Schedule | Not Started | 2021-05-04 | 2021-05-17 | Not Started | 2021-11-12 | Not Started
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | E.5015489.05 | 5786203 | CONS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 | 2020 | SH | SALINAS | Central Coast Assets | 0 | 6635 | 6635 | 1.2566 | 0.44261 | 0.81402 | 5963 | 0 | 1.1294 | 0 | GC | 2335115 | 391451.6 | 1943663.4 | 793490.2 | 170640.5 | 1320813.7 | On/Under Budget | 6709.7 | 2668.7 | -1133.7 | 3802.4 | 0 | 1388.8 | 517879 | 273088.8 | Request 2021 Budget | 0 | 283601 | -283601 | 283601 | -283601 | 150007.4 | 24443.2 | 99771.9 | 2668.7 | 2668.7 | 2668.7 | 1372.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157102 | BL-0 | BL-0 35114103_CWSP - Camp Evers 2106 - LR5020 - PH 2.5_08W - Mar. 2021 | 2021-03-07 | 2020-07-03 | Completed | 2020-07-07 | 2020-07-16 | Completed | 2020-04-23 | Completed | 2020-07-16 | Completed | 2020-02-03 | 2020-07-17 | Completed | 2020-07-16 | 2020-07-31 | Completed | 2020-07-27 | 2020-10-31 | Completed | 2020-08-03 | Completed |  |  |  |  | 2020-08-03 | Completed | 2021-04-30 | Not Started | 2021-05-06 | Not Started | 2021-11-26 | 2021-09-30 | 57 | On/ Ahead Schedule | Not Started | 2021-05-12 | 2021-05-25 | Not Started | 2022-04-29 | Not Started
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | E.5014771.02 | 5785972 | CONS | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | SONORA | Yosemite Assets | 0 | 8512 | 8512 | 1.6121 | 0.84129 | 0.77083 | 8512 | 0 | 1.6121 | 0 | Contract | 4091239 | 1281646 | 2809593 | 1450373 | 544034.3 | 1903254.3 | On/Under Budget | 0 | 2603.2 | -401943.3 | 404546.5 | 0 | 3717.1 | 817284.8 | 227427.7 | Request 2021 Budget | 0 | 631974.2 | -631974.2 | 631974.2 | -631974.2 | 64714.9 | 11379.4 | 553276.7 | 2603.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 151440 | BL-0 | BL-0 35115050_CWSP - MIWUK 1701 - OCB - PH 1.2_08W - Nov 2020 | 2020-11-12 | 2020-02-13 | Completed | 2020-06-15 | 2020-06-23 | Completed | 2020-03-31 | Completed | 2020-07-02 | Completed | 2020-07-17 | 2020-07-17 | Completed | 2020-07-27 | 2020-08-07 | Completed | 2020-07-23 | 2020-08-14 | Completed | 2020-08-10 | Completed |  |  |  |  | 2020-08-10 | Completed | 2021-05-04 | Not Started | 2021-04-02 | Completed | 2021-04-30 | 2021-05-12 | -12 | Behind Schedule | Not Started | 2021-05-19 | 2021-06-01 | Not Started | 2021-10-05 | Not Started
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | E.5014771.03 | 5785973 | CONS | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP | 2020 | SH | SONORA | Yosemite Assets | 0 | 5484 | 5484 | 1.0386 | 0 | 1.0386 | [5 empty] | 2865068 | 1066735.5 | 1798332.5 | 89227.4 | 0 | 1709105.1 | On/Under Budget | 1025005.3 | 0 | 0 | 0 | 0 | 398.5 | 75437.6 | 13391.3 | Project is not in the WP or in 2020 WP | 0 | 13391.3 | -13391.3 | 13391.3 | -13391.3 | 11461.7 | 725.3 | 1204.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640210.6 | 268795.4 | 112889.2 | 3110.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1025005.3 | 2021-04-02 | 145880 | BL-0 | BL-0 35115051_CWSP - MIWUK 1701 - OCB - PH 1.3_08W - Dec 2020 | 2020-07-26 | 2020-03-03 | Completed | 2020-06-17 | 2020-06-23 | Completed | 2020-03-03 | Completed | 2020-07-06 | Completed | 2020-09-04 | 2020-09-04 | Completed | 2020-09-08 | 2020-11-20 | Completed | 2020-08-04 | 2020-09-25 | Completed | 2022-01-05 | Not Started |  |  |  |  | 2022-01-05 | Not Started | 2022-02-08 | Not Started | 2022-03-01 | Not Started | 2020-12-28 | 2022-03-31 | -458 | Behind Schedule | Not Started | 2022-04-01 | 2022-04-14 | Not Started | 2022-05-23 | Not Started
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | E.5014771.04 | 5785974 | CONS | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 8551 | 8551 | 1.6195 | 0 | 1.6195 | [5 empty] | 4217803 | 1291313.2 | 2926489.8 | 395504.1 | 34407.4 | 2565393.1 | On/Under Budget | 1391308.1 | 290.1 | -2500 | 2790.1 | 0 | 1234.8 | 381300.9 | 10468.4 | Project is not in the WP or in 2020 WP | 0 | 15642.3 | -15642.3 | 15642.3 | -15642.3 | -906.3 | 7910.8 | 5963.9 | 290.1 | 290.1 | 290.1 | 300.6 | 300.6 | 300.6 | 300.6 | 300.6 | 300.6 | 24404.1 | 919526.8 | 913166.2 | 0 | 0 | -468173 | 0 | 0 | 0 | 0 | 0 | 0 | 1388924.1 | 2021-04-02 | 151451 | BL-0 | BL-0 35115052_CWSP - MIWUK 1701 - OCB - PH 1.4_08W - Nov. 2020 | 2020-11-12 | 2020-07-31 | Completed | 2020-07-10 | 2020-07-10 | Completed | 2020-03-19 | Completed | 2020-08-04 | Completed | 2022-01-04 | 2022-01-04 | Not Started | 2022-01-05 | 2022-01-05 | Not Started | 2020-09-28 | 2020-09-28 | Completed | 2022-01-06 | Not Started |  |  |  |  | 2022-01-06 | Not Started | 2022-02-16 | Not Started | 2022-03-09 | Not Started | 2021-04-20 | 2022-04-08 | -353 | Behind Schedule | Not Started | 2022-04-11 | 2022-04-22 | Not Started | 2022-05-31 | Not Started
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | E.5014771.05 | 5785975 | CONS | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | SONORA | Yosemite Assets | 0 | 9571 | 9571 | 1.8127 | 0 | 1.8127 | 9083 | 0 | 1.7203 | 0 | GC | 2296559 | 626143.5 | 1670415.5 | 695353.6 | 268688.2 | 1243750.1 | On/Under Budget | 235516 | 2408.6 | -1083.7 | 3492.3 | 0 | 468.6 | 632591.2 | 61210.1 | Request 2021 Budget | 0 | 300218.4 | -300218.4 | 300218.4 | -300218.4 | 14398.7 | 8566.5 | 39328.6 | 2408.6 | 51743.3 | 180077.4 | 3695.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 152832 | BL-1 | BL-1 35115053_CWSP - MIWUK 1701 - OCB - PH 1.5_08W - Dec. 2020 | 2020-12-29 | 2020-04-06 | Completed | 2020-04-24 | 2020-05-21 | Completed | 2020-04-08 | Completed | 2020-01-30 | Completed | 2020-10-30 | 2020-10-30 | Completed | 2020-11-02 | 2020-11-03 | Completed | 2020-02-26 | 2020-07-22 | Completed | 2020-08-11 | Completed |  |  |  |  | 2020-08-11 | Completed | 2021-06-11 | Not Started | 2021-07-08 | Not Started | 2021-04-20 | 2021-07-09 | -80 | Behind Schedule | Not Started | 2021-07-23 | 2021-08-05 | Not Started | 2021-08-30 | Not Started
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | E.5015427.02 | 5785986 | CONS | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | SONORA | Yosemite Assets | 0 | 7523 | 7523 | 1.4248 | 0 | 1.4248 | 7529 | 0 | 1.4259 | 0 | Contract | 3789178 | 1306517 | 2482661 | 1251342.9 | 403931.3 | 1635249.4 | On/Under Budget | 0 | 211424.7 | -176627.3 | 388052 | 0 | 6442.2 | 1133674.4 | -65401.1 | Request 2021 Budget | 0 | 322650.9 | -322650.9 | 322650.9 | -322650.9 | 109608.9 | 47981.5 | -46364.2 | 211424.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 151441 | BL-0 | BL-0 35115054_CWSP - MIWUK 1701 - OCB - PH 2.2_08W - Nov. 2020 | 2020-11-12 | 2020-02-18 | Completed | 2020-06-29 | 2020-07-30 | Completed | 2020-03-31 | Completed | 2020-07-02 | Completed | 2020-08-03 | 2020-08-03 | Completed | 2020-08-24 | 2020-08-24 | Completed | 2020-08-03 | 2020-09-15 | Completed | 2020-08-24 | Completed |  |  |  |  | 2020-08-24 | Completed | 2021-04-23 | Not Started | 2021-05-14 | Not Started | 2021-04-30 | 2021-05-17 | -17 | Behind Schedule | Not Started | 2021-05-31 | 2021-06-11 | Not Started | 2021-10-08 | Not Started
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | E.5015427.03 | 5785987 | CONS | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 | 2020 | SH | SONORA | Yosemite Assets | 0 | 11269 | 11269 | 2.1343 | 0 | 2.1343 | 11269 | 0 | 2.1343 | 0 | GC | 3784068 | 882708.1 | 2901359.9 | 1225322.7 | 111911.2 | 1787948.4 | On/Under Budget | 4221.7 | 4221.7 | 2331.8 | 1889.9 | 0 | 0 | 755027.7 | 472626.8 | Request 2021 Budget | 0 | 478738.4 | -478738.4 | 478738.4 | -478738.4 | 123990.6 | 148754 | 197550.4 | 4221.7 | 4221.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 152685 | BL-1 | BL-1 35115055_CWSP - MIWUK 1701 - OCB - PH 2.3_08W - Dec. 2020 | 2020-12-21 | 2020-04-21 | Completed | 2020-05-21 | 2020-06-09 | Completed | 2020-03-17 | Completed | 2020-06-15 | Completed | 2020-07-17 | 2020-07-17 | Completed | 2020-07-17 | 2020-08-06 | Completed | 2020-05-26 | 2020-07-20 | Completed | 2020-12-31 | Completed |  |  |  |  | 2020-12-31 | Completed | 2021-04-30 | Not Started | 2021-05-07 | Not Started | 2021-04-26 | 2021-05-10 | -14 | Behind Schedule | Not Started | 2021-05-24 | 2021-06-04 | Not Started | 2021-06-29 | Not Started
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | E.5015427.04 | 5785988 | CONS | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 9236 | 9236 | 1.7492 | 0 | 1.7492 | [5 empty] | 4578906 | 1309425.5 | 3269480.5 | 518707.9 | 0 | 2750772.6 | On/Under Budget | 1717536.3 | 570.8 | -5162.1 | 5732.9 | 0 | 2309.8 | 480665.1 | 30571 | Project is not in the WP or in 2020 WP | 0 | 40996.3 | -40996.3 | 40996.3 | -40996.3 | 7618.9 | 19477.5 | 8636.7 | 570.8 | 570.8 | 570.8 | 591.8 | 591.8 | 591.8 | 591.8 | 591.8 | 591.8 | 1132693.4 | 498858.6 | 75831.2 | 5460.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1712843.6 | 2021-04-02 | 145884 | BL-0 | BL-0 35115056_CWSP - MIWUK 1701 - OCB - PH 2.4_08W - DEC 2020 | 2020-07-26 | 2020-07-07 | Completed | 2020-06-17 | 2020-06-23 | Completed | 2020-02-14 | Completed | 2020-07-08 | Completed | 2020-08-24 | 2020-08-24 | Completed | 2020-09-18 | 2020-10-13 | Completed | 2020-08-03 | 2020-09-15 | Completed | 2022-02-09 | Not Started |  |  |  |  | 2022-02-09 | Not Started | 2022-04-07 | Not Started | 2022-04-22 | Not Started | 2020-12-30 | 2022-06-07 | -524 | Behind Schedule | Not Started | 2022-06-08 | 2022-06-21 | Not Started | 2022-07-28 | Not Started
35118663 | BR-01-01-W (E) HEAVENS GATE PARB |  | 5786123 | CONS | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2021 |  | BUCOCAMP | CHICO | North Valley Assets | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Contract | 1772954.66 | 857663.66 | 915291 | 967768.7 | 2423 | -50054.7 | OverRun | 0 | 7157 | -1250 | 8407 | 0 | 4747.7 | 803302.1 | 158468.9 | Request 2021 Budget | 0 | 166875.9 | -166875.9 | 166875.9 | -166875.9 | 32313 | -1563.2 | 128969.1 | 7157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | CONS | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 11395 | 11395 | 2.1581 | 1.2688 | 0.88939 | 11395 | 0 | 2.1581 | 0 | GC | 5778810 | 1303103 | 4475707 | 2289759.7 | 347292.4 | 2533239.7 | On/Under Budget | 0 | 100891 | -18788.5 | 119679.5 | 0 | 4056.8 | 1808850.8 | 458063.6 | Budget Allocated | 2450191 | 2382080.1 | 68110.9 | 577743.1 | 1872447.9 | 122362.6 | 148848.3 | 205641.2 | 100891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 151681 | BL-1 | BL-1 35117443_CWSP - Brunkswick 1103 LR50070 ZONE-PH3.6_08W - Nov. 2020 | 2020-11-24 | 2020-06-23 | Completed | 2020-07-07 | 2020-07-08 | Completed | 2020-07-10 | Completed | 2020-07-08 | Completed | 2020-07-08 | 2020-07-08 | Completed | 2020-07-15 | 2020-07-15 | Completed | 2020-07-06 | 2020-07-10 | Completed | 2020-07-28 | Completed |  |  |  |  | 2020-07-28 | Completed | 2021-05-03 | Not Started | 2020-12-03 | Completed | 2021-04-02 | 2021-07-12 | -101 | Behind Schedule | Not Started | 2021-07-13 | 2021-07-14 | Not Started | 2021-11-17 | Not Started
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | CONS | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2021 | SH | GRSSVLLY | Sierra Assets | 0 | 8412 | 8412 | 1.5932 | 0.81932 | 0.77386 | 8412 | 0 | 1.5932 | 0 | GC | 3876275 | 1124354 | 2751921 | 1540631.6 | 124567.7 | 1335857.1 | On/Under Budget | 2297317 | 0 | 5638.5 | -5638.5 | 0 | 235.3 | 954124.7 | 591910.1 | Budget Allocated | 2721318.8 | 2883588.6 | -162269.8 | 2883588.6 | -162269.8 | 168193.5 | 151055.2 | 267022.9 | 0 | 1297317 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157123 | BL-1 | BL-1 35142826_CWSP - BRUNSWICK 1103 LR2200 Ph 2_08W - Mar. 2021 | 2021-03-07 | 2020-06-15 | Completed | 2020-08-04 | 2020-08-06 | Completed | 2020-06-01 | Completed | 2020-08-06 | Completed | 2021-01-29 | 2021-01-29 | Completed | 2021-02-01 | 2021-02-01 | Completed | 2020-09-02 | 2020-10-31 | Completed | 2021-02-01 | Completed |  |  |  |  | 2021-02-01 | Completed | 2021-04-16 | Not Started | 2021-04-22 | Not Started | 2021-06-17 | 2021-06-17 | 0 | On/ Ahead Schedule | Not Started | 2021-06-18 | 2021-06-21 | Not Started | 2021-06-23 | Not Started
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | CONS | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | GRSSVLLY | Sierra Assets | 0 | 2600 | 2600 | 0.49242 | 0 | 0.49242 | [5 empty] | 1844178 | 737162 | 1107016 | 333597.3 | 34489.5 | 807908.2 | On/Under Budget | 39822.5 | 28440.1 | 0 | 28440.1 | 0 | 235.3 | 322124.6 | 11237.5 | Project is not in the WP or in 2020 WP | 0 | 79500.1 | -79500.1 | 79500.1 | -79500.1 | 6416.1 | 2067.2 | 2754.2 | 28440.1 | 38742.1 | 159.1 | 167.5 | 167.5 | 167.5 | 167.5 | 167.5 | 83.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157124 | BL-1 | BL-1 35142828_CWSP - BRUNSWICK 1103 LR2200 Ph 4_08W - Mar. 2021 | 2021-03-07 | 2020-07-22 | Completed | 2020-08-04 | 2020-08-06 | Completed | 2020-07-07 | Completed | 2020-08-06 | Completed | 2021-12-03 | 2021-12-03 | Not Started | 2020-09-21 | 2021-12-06 | In Progress | 2020-10-01 | 2021-12-02 | In Progress | 2021-12-06 | Not Started |  |  |  |  | 2021-12-06 | Not Started | 2021-12-17 | Not Started | 2021-12-29 | Not Started | 2022-01-24 | 2022-01-24 | 0 | On/ Ahead Schedule | Not Started | 2022-01-25 | 2022-02-07 | Not Started | 2022-03-16 | Not Started
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | 5530175 | CONS | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | Not in the WP | 2022 | SH | STROSA | Sonoma Assets | 0 | 2367 | 2367 | 0.4483 | 0 | 0.4483 | [5 empty] | 1245293 | 0 | 1245293 | 369743.5 | 35000 | 910549.5 | On/Under Budget | 1094699.6 | 36799.6 | 0 | 36799.6 | 12035.3 | 383036.2 | -107919 | 82591 | Project is not in the WP or in 2020 WP | 0 | 474147.8 | -474147.8 | 1214090.3 | -1214090.3 | 5895.5 | 5344.4 | 71351.1 | 36799.6 | 183333 | 303788.9 | 303788.9 | 303788.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 128588 | WSHP | WSHP 190307 - 31361965_DUNBAR 1101 NUNS CANYON_08W - B1 | 2019-03-07 | 2019-06-19 | Completed | 2019-03-08 | 2019-06-21 | Completed | 2020-07-22 | Completed | 2020-07-24 | Completed | 2020-11-10 | 2021-04-02 | Completed | 2021-04-02 | 2021-04-09 | Not Started | 2020-09-28 | 2020-11-30 | Completed | 2021-04-12 | Not Started |  |  |  |  | 2021-04-12 | Not Started |  |  | 2021-05-28 | Not Started | 2019-07-18 | 2021-06-28 | -711 | Behind Schedule | Not Started | 2021-06-29 | 2021-07-12 | Not Started | 2021-08-18 | Not Started
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | E.5015427.01 | 5782537 | CONS | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | SONORA | Yosemite Assets | 0 | 10615 | 10615 | 2.0104 | 0 | 2.0104 | 10737 | 0 | 2.0335 | 0 | Contract | 3642331 | 691429 | 2950902 | 612571.5 | 686304.5 | 3024635 | On/Under Budget | 332523.4 | 282247.3 | -200513.6 | 482760.9 | 7046 | 16234.6 | 348014 | 40763.4 | Request 2021 Budget | 0 | 856047.7 | -856047.7 | 856047.7 | -856047.7 | 6426.2 | 5916.4 | 228934.4 | 282247.3 | 332523.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145858 | BL-A: | BL-A: 35056746_CWSP - MIWUK 1701 - OCB - PH 2.1_08W - Nov 2020 | 2020-07-24 | 2020-03-30 | Completed | 2020-07-06 | 2020-07-23 | Completed | 2020-06-29 | Completed | 2020-07-31 | Completed | 2020-07-31 | 2020-08-06 | Completed | 2020-08-07 | 2020-08-27 | Completed | 2020-08-21 | 2020-09-01 | Completed | 2020-09-14 | Completed |  |  |  |  | 2020-09-14 | Completed |  |  | 2020-09-24 | Completed | 2020-11-23 | 2021-05-21 | -179 | Behind Schedule | Not Started | 2021-06-04 | 2021-06-17 | Not Started | 2021-08-09 | Not Started
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | E.5014722.01 | 5785221 | CONS | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 | 2021 | SH | SONORA | Yosemite Assets | 0 | 6168 | 6168 | 1.1682 | 0.30189 | 0.86629 | 6168 | 0 | 1.1682 | 0 | Contract | 3544410 | 1202119 | 2342291 | 582324.9 | 678547.9 | 2438514 | On/Under Budget | 633349.7 | 404512.2 | -6232.3 | 410744.5 | 422.3 | 9464.2 | 465309.1 | 100897 | Budget Allocated | 1048628 | 1144991.1 | -96363.1 | 1144991.1 | -96363.1 | 21195.2 | 3899.3 | 82034.8 | 404512.2 | 630478.9 | 956.9 | 956.9 | 956.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145832 | BL-0: | BL-0: 35052825_CWSP - MIWUK 1702 - LR 8090 - PH 1.1_08W - Oct. 2020 | 2020-07-24 | 2020-04-29 | Completed | 2020-06-25 | 2020-07-14 | Completed | 2020-02-04 | Completed | 2020-07-14 | Completed | 2020-08-15 | 2020-08-18 | Completed | 2020-08-15 | 2020-09-09 | Completed | 2020-08-17 | 2020-10-16 | Completed | 2021-04-06 | Not Started | [8 empty] | 2021-05-13 | Not Started | 2020-10-30 | 2021-06-01 | -214 | Behind Schedule | Not Started | 2021-06-02 | 2021-06-15 | Not Started | 2021-10-18 | Not Started
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | E.5014776.01 | 5785219 | CONS | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 11546 | 11546 | 2.1867 | 0 | 2.1867 | [5 empty] | 5180025 | 1156134.2 | 4023890.8 | 643148.2 | 117051 | 3497793.6 | On/Under Budget | 1248887.4 | 1002.3 | -250 | 1252.3 | 771.6 | 11640.1 | 653821.8 | -23335.3 | Project is not in the WP or in 2020 WP | 0 | -13843.8 | 13843.8 | -13843.8 | 13843.8 | 3780.9 | -31930.8 | 5064.6 | 1002.3 | 1002.3 | 1002.3 | 1039.1 | 1039.1 | 1039.1 | 1039.1 | 1039.1 | 1039.1 | 612267.5 | 621015.8 | 7365.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1240648.4 | 2021-04-02 | 145848 | BL-0: | BL-0: 35052739_CWSP - MIWUK 1702 - LR 38218 - PH 1.1_08W - Nov 2020 | 2020-07-24 | 2020-04-13 | Completed | 2020-03-17 | 2020-03-17 | Completed | 2020-03-16 | Completed | 2020-06-26 | Completed | 2020-09-25 | 2020-10-01 | Completed | 2020-10-01 | 2020-10-01 | Completed | 2020-03-16 | 2020-04-21 | Completed | 2022-01-18 | Not Started |  |  |  |  | 2022-01-18 | Not Started |  |  | 2022-03-21 | Not Started | 2020-11-19 | 2022-04-01 | -498 | Behind Schedule | Not Started | 2022-04-05 | 2022-04-18 | Not Started | 2022-05-24 | Not Started
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | E.5014771.01 | 5784646 | CONS | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | SONORA | Yosemite Assets | 0 | 9083 | 9083 | 1.7203 | 0.50871 | 1.2116 | 10953 | 0 | 2.0744 | 0 | Contract | 4765282 | 1442306.6 | 3322975.4 | 1011653.7 | 824719.4 | 3136041.1 | On/Under Budget | -174170 | 460612 | -286246.5 | 746858.5 | 7486.6 | 9282.8 | 549366.9 | 159270.9 | Request 2021 Budget | 0 | 731959.4 | -731959.4 | 731959.4 | -731959.4 | 87989.6 | 10201 | 347326.8 | 460612 | -88198.9 | -88766 | 2794.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 152831 | BL-1 | BL-1 35052821_CWSP - MIWUK 1701 - OCB - PH 1.1_08W - Dec. 2020 | 2020-12-29 | 2019-12-20 | Completed | 2020-07-10 | 2020-07-10 | Completed | 2020-06-02 | Completed | 2020-08-04 | Completed | 2020-08-24 | 2020-08-24 | Completed | 2020-08-04 | 2020-08-04 | Completed | 2020-09-28 | 2020-09-28 | Completed | 2020-08-31 | Completed |  |  |  |  | 2020-08-31 | Completed |  |  | 2021-07-20 | Not Started | 2022-05-18 | 2021-08-31 | 260 | On/ Ahead Schedule | Not Started | 2021-09-01 | 2021-09-14 | Not Started | 2021-11-04 | Not Started
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | CONS | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 9320 | 9320 | 1.7652 | 0.82784 | 0.93731 | 9320 | 0 | 1.7652 | 0 | GC | 4711641 | 1252143 | 3459498 | 2326360.1 | 98569.1 | 1231707 | On/Under Budget | 0 | 0 | -15660.7 | 15660.7 | 2773.6 | 14800.2 | 2022743.5 | 270382.2 | Budget Allocated | 1419181 | 1560662.9 | -141481.9 | 286042.9 | 1133138.1 | 20400.3 | 30760.9 | 234881.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 151679 | BL-1 | BL-1 35061206_CWSP - Brunkswick 1103 LR50070 ZONE-PH1.1_08W - Nov. 2020 | 2020-11-24 | 2020-05-20 | Completed | 2020-05-20 | 2020-05-20 | Completed | 2020-05-22 | Completed | 2020-07-10 | Completed | 2020-05-20 | 2020-05-20 | Completed | 2020-05-26 | 2020-05-26 | Completed | 2020-06-10 | 2020-07-02 | Completed | 2020-06-15 | Completed |  |  |  |  | 2020-06-15 | Completed | 2021-05-27 | Not Started | 2020-12-03 | Completed | 2021-03-31 | 2021-06-23 | -84 | Behind Schedule | Not Started | 2021-06-24 | 2021-07-07 | Not Started | 2021-08-13 | Not Started
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | CONS | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 9445 | 9445 | 1.7888 | 0 | 1.7888 | 10109 | 0 | 1.9146 | 0 | GC | 4913095 | 1023067.2 | 3890027.8 | 1690567 | 452434 | 2651894.8 | On/Under Budget | 1733291 | 138725.2 | -17159.2 | 155884.4 | 2055 | 215821.4 | 1262448.4 | 193083 | Budget Allocated | 2161081.9 | 2082258.4 | 78823.5 | 2082258.4 | 78823.5 | 24395.5 | 110421.4 | 75425.3 | 138725.2 | 0 | 733291 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157113 | BL-1 | BL-1 35061212_CWSP - Brunkswick 1103 LR50070 ZONE-PH2.1_08W - Mar. 2021 | 2021-03-07 | 2020-09-11 | Completed | 2020-07-10 | 2020-07-19 | Completed | 2020-05-25 | Completed | 2020-07-19 | Completed | 2020-08-07 | 2020-08-07 | Completed | 2020-07-27 | 2020-08-21 | Completed | 2020-07-13 | 2020-08-19 | Completed | 2020-08-20 | Completed |  |  |  |  | 2020-08-20 | Completed |  |  | 2021-06-04 | Not Started | 2021-07-20 | 2021-07-20 | 0 | On/ Ahead Schedule | Not Started | 2021-07-21 | 2021-08-03 | Not Started | 2021-09-09 | Not Started
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | E.5015236.01 | 5783906 | CONS | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 5541 | 5541 | 1.0494 | 0 | 1.0494 | [5 empty] | 2583069 | 651010.4 | 1932058.6 | 741142.6 | 0 | 1190916 | On/Under Budget | 991697.1 | 0 | -250 | 250 | 0 | 28472 | 782376.5 | -69955.8 | Project is not in the WP or in 2020 WP | 0 | -69705.8 | 69705.8 | -69705.8 | 69705.8 | 8707.5 | -83790.9 | 5377.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2870.9 | 2870.9 | 984075.1 | 355133.6 | 3953.7 | 0 | 0 | 0 | -357207 | 0 | 0 | 0 | 991697.2 | 2021-04-02 | 130705 | WSHP | WSHP 190307 - 35072360_CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2 - DD190301 | 2019-04-15 | 2020-05-19 | Completed | 2020-07-09 | 2020-07-23 | Completed | 2020-07-07 | Completed | 2020-07-23 | Completed | 2020-08-26 | 2020-08-27 | Completed | 2020-09-11 | 2020-10-02 | Completed | 2020-07-02 | 2020-08-14 | Completed | 2022-01-11 | Not Started |  |  |  |  | 2022-01-11 | Not Started |  |  | 2022-02-25 | Not Started | 2020-10-23 | 2022-03-29 | -522 | Behind Schedule | Not Started | 2022-03-04 | 2022-03-18 | Not Started | 2022-05-03 | Not Started
35105646 | BR-03-05-W (E) DEAN RD, PARB |  | 5786123 | CONS | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 2833115.5 | 2521030.5 | 312085 | 354320.4 | 117394.9 | 75159.5 | On/Under Budget | 0 | -88682.7 | -12452.4 | -76230.3 | 0 | 1831.2 | 409873.7 | -69836.9 | Project is not in the WP or in 2020 WP | 0 | -135247.3 | 135247.3 | -146067.2 | 146067.2 | 51612.7 | -324833 | 215835.8 | -88682.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | E.5015487.01 | 5782860 | CONS | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2021 | 2021 | SH | GYSRVLLE | Sonoma Assets | 0 | 29328 | 29328 | 5.5545 | 4.6809 | 0.87367 | 28754 | 13252.8 | 5.4458 | 2.51 | GC | 9998553 | 778830 | 9219723 | 8441953.9 | 1459994.7 | 2237763.8 | On/Under Budget | 26787.1 | 485370 | -40676.3 | 526046.3 | 8050.7 | 2983380.5 | 3832391.3 | 1577455.1 | Budget Allocated | 2395900 | 2130288.6 | 265611.4 | 2130288.6 | 265611.4 | 411886.5 | 391477.5 | 814767.4 | 485370 | 8791.6 | 8791.6 | 3068 | 3068 | 3068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 152703 | BL-1 | BL-1 74022384_FITCH MOUNTAIN 1113 LR 24918_08W - Dec. 2020 | 2020-12-21 | 2019-06-06 | Completed |  |  | Completed | 2020-06-19 | Completed | 2020-06-02 | Completed | 2020-06-08 | 2020-06-10 | Completed | 2020-06-22 | 2020-06-23 | Completed | 2019-12-04 | 2021-03-19 | Completed | 2020-06-08 | Completed |  |  |  |  | 2020-06-08 | Completed | 2021-04-09 | Not Started | 2020-11-18 | Completed | 2021-03-12 | 2021-05-12 | -61 | Behind Schedule | Not Started | 2021-05-13 | 2021-05-26 | Not Started | 2021-07-02 | Not Started
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | E.5014743.02 | 5782598 | CONS | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2020 | 2020 | SH | STROSA | Sonoma Assets | 0 | 9716 | 9716 | 1.8402 | 1.8402 | 0 | 13421 | 0 | 2.5419 | 0 | GC | 4467090 | 111030 | 4356060 | 4446586.2 | 0 | -90526.2 | OverRun | 3989.1 | 67523.2 | -933.7 | 68456.9 | 0 | 664270.2 | 3482691.9 | 298690.4 | Project is not in the WP or in 2020 WP | 0 | 371136.4 | -371136.4 | 371136.4 | -371136.4 | 10315 | 277957.8 | 11351.3 | 67523.2 | 3989.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 152701 | BL-0 | BL-0 74028021_CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2_08W - Dec. 2020 | 2020-12-21 | 2020-01-30 | Completed | 2020-02-24 | 2020-02-25 | Completed | 2020-03-13 | Completed | 2020-03-16 | Completed | 2020-03-17 | 2020-03-18 | Completed | 2020-03-25 | 2020-04-20 | Completed | 2020-04-13 | 2020-04-14 | Completed | 2020-05-05 | Completed |  |  |  |  | 2020-05-05 | Completed | 2021-04-22 | Not Started | 2020-09-16 | Completed | 2021-03-02 | 2021-05-20 | -79 | Behind Schedule | Not Started | 2021-05-21 | 2021-06-03 | Not Started | 2021-07-12 | Not Started
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | 5795297 | CONS | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH - Wind | OAKHURST | Yosemite Assets | 0 | 5596.8 | 5596.8 | 1.06 | 1.09 | -0.029962 | 5598 | 0 | 1.0602 | 0 | GC | 326951.18 | 326951.18 | 0 | 869556.6 | 1398726.9 | 529170.3 | On/Under Budget | 0 | 0 | 16815.9 | -16815.9 | 0 | 0 | 0 | 886372.5 | Budget Allocated | 2183706 | 1866949.7 | 316756.3 | 869556.6 | 1314149.4 | 10026.7 | 209324.1 | 650205.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-01-24 | Completed | 2021-02-23 | 2021-03-18 | Completed | 2021-03-10 | Completed |  |  | 2021-02-04 | 2021-02-04 | Completed | 2021-02-04 | 2021-02-05 | Completed | 2021-02-08 | 2021-03-18 | Completed | 2021-02-22 | Completed |  |  |  |  | 2021-02-22 | Completed | 2021-03-18 | Completed | 2021-03-18 | Completed | 2021-04-02 | 2021-04-02 | 0 | On/ Ahead Schedule | Not Started | 2021-04-05 | 2021-04-16 | Not Started | 2021-06-29 | Not Started
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | 5795297 | CONS | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH - Wind | OAKHURST | Yosemite Assets | 0 | 4224 | 4224 | 0.8 | 0.95 | -0.15 | 4355 | 0 | 0.82481 | 0 | GC | 512371.91 | 512371.91 | 0 | 852988.5 | 1271327.5 | 418339 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 852988.6 | Budget Allocated | 2080934 | 1850268 | 230666 | 852988.6 | 1227945.4 | 6031.2 | 200461.8 | 646495.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-01-23 | Completed | 2021-03-22 | 2021-03-25 | Not Started | 2021-03-02 | Completed |  |  | 2021-02-04 | 2021-02-04 | Completed | 2021-02-04 | 2021-02-05 | Completed | 2021-02-16 | 2021-03-15 | Completed | 2021-02-02 | Completed |  |  |  |  | 2021-02-02 | Completed | 2021-03-15 | Completed | 2021-02-16 | Completed | 2021-04-05 | 2021-04-05 | 0 | On/ Ahead Schedule | Not Started | 2021-04-05 | 2021-04-16 | Not Started | 2021-06-29 | Not Started
74022620 | *DO NOT USE* RPL OH WIRE ON OTTER-1101 S |  | 5794491 | DCNL | 08W | RNLO | Russell N Loeffler |  |  |  |  | Not in the WP |  |  | MONTEREY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35107689 | OCGC CWSP - PINE GROVE 1102 - LR1222 - | E.5014745.01 | 5785659 | DCNL | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2020 |  | SH | JACKSON | Stockton Assets | 0 | 11057.2 | 11057.2 | 2.0942 | 2.0942 | 0 | 10648 | 11292 | 2.0167 | 2.1386 | GC | 5851741 | 1219955.8 | 4631785.2 | 3462511.9 | 0 | 1169273.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 10569.3 | 3451892.8 | 49.8 | Project is not in the WP or in 2020 WP | 0 | 49.8 | -49.8 | 49.8 | -49.8 | 0 | 0 | 49.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35081660 | OH RECONDUCTOR - ROB ROY 2105 -S028CC119 |  | 5519546 | DCNL | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | E.5014772.06 | 5784864 | DOCC | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2020 |  | SH | NAPA | North Bay Assets | 0 | 8793 | 8793 | 1.6653 | 1.6653 | 0 | 8793 | 8793 | 1.6653 | 1.6653 | Contract | 2979682 | 16050.9 | 2963631.1 | 2503334.4 | 0 | 460296.7 | On/Under Budget | 0 | 0 | -300 | 300 | 0 | 523283.4 | 1978598.6 | 1152.5 | Project is not in the WP or in 2020 WP | 0 | 1452.5 | -1452.5 | 1452.5 | -1452.5 | 1149.7 | 0 | 302.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-07-13 | Not Started | 2021-08-18 | 2021-08-24 | Not Started | 2021-08-17 | Not Started | 2021-09-14 | Not Started | 2021-07-14 | 2021-07-14 | Not Started | 2021-07-15 | 2021-08-04 | Not Started | 2021-08-18 | 2021-08-31 | Not Started | 2021-10-07 | Not Started | 2021-10-07 | Not Started | 2021-10-20 | Not Started | 2021-10-07 | Not Started | 2022-01-19 | Not Started | 2022-02-17 | Not Started | 2022-04-20 | 2022-04-20 | 0 | On/ Ahead Schedule | Not Started | 2022-04-21 | 2022-05-04 | Not Started | 2022-06-17 | Not Started
35085536 | CWSP - SILVERADO 2104 - LR722 PH 1G | E.5014772.07 | 5784865 | DOCC | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | Not in the WP | 2019 | SH | NAPA | North Bay Assets | 0 | 7010 | 7010 | 1.3277 | 1.3277 | 0 | [5 empty] | 1950000 | 0.4 | 1949999.6 | 1863426.2 | 0 | 86573.4 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 1738811.2 | 124615 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2019-08-13 | Completed | 2019-08-26 | 2019-08-27 | Completed | 2019-08-30 | Completed | 2019-08-23 | Completed | 2019-09-03 | 2019-09-04 | Completed | 2019-09-09 | 2019-09-10 | Completed | 2019-08-20 | 2019-08-22 | Completed | 2019-10-14 | Completed |  |  |  |  | 2019-10-14 | Completed |  |  | 2019-12-09 | Completed | 2020-05-18 | 2019-12-09 | 161 | On/ Ahead Schedule | Completed | 2019-12-12 | 2019-12-20 | Completed | 2021-05-24 | Not Started
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 | E.5014317.03 | 5784868 | DOCC | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2020 | 2019 | SH | NAPA | North Bay Assets | 0 | 10260 | 10260 | 1.9432 | 1.9432 | 0 | 34020 | 34020 | 6.4432 | 6.4432 | Contract | 2570000 | 0.2 | 2569999.8 | 2451383.3 | 0 | 118616.5 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 1271059.9 | 1099999.1 | 80324.3 | Project is not in the WP or in 2020 WP | 0 | 80324.3 | -80324.3 | 80324.3 | -80324.3 | 0 | 0 | 80324.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2019-08-09 | Completed | 2019-08-26 | 2019-12-02 | Completed | 2019-08-30 | Completed | 2019-08-22 | Completed | 2019-08-28 | 2019-08-29 | Completed | 2019-10-02 | 2019-10-07 | Completed | 2019-09-17 | 2019-09-17 | Completed | 2019-11-08 | Completed |  |  |  |  | 2019-11-08 | Completed | 2019-11-15 | Completed | 2020-05-21 | Completed | 2020-06-02 | 2020-05-21 | 12 | On/ Ahead Schedule | Completed | 2020-05-25 | 2020-05-29 | Completed | 2021-05-03 | Not Started
35085681 | SILVERADO 2105 WIRE DOWN - PH 4 | E.5014317.05 | 5784870 | DOCC | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | Not in the WP | 2019 | SH | NAPA | North Bay Assets | 0 | 2934 | 2934 | 0.55568 | 0.55568 | 0 | [5 empty] | 500000 | -0.5 | 500000.5 | 480452.5 | 0 | 19548 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 426337.6 | 54114.9 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2019-06-07 | Completed | 2019-08-15 | 2019-08-16 | Completed | 2019-08-26 | Completed | 2019-08-14 | Completed | 2019-08-19 | 2019-08-20 | Completed | 2019-08-19 | 2019-08-20 | Completed | 2019-08-22 | 2019-08-23 | Completed | 2019-09-06 | Completed |  |  |  |  | 2019-09-06 | Completed |  |  | 2019-09-24 | Completed | 2020-05-18 | 2019-09-24 | 237 | On/ Ahead Schedule | Completed | 2019-09-30 | 2019-10-04 | Completed | 2021-05-24 | Not Started
35094390 | CWSP-KONOCTI 1102-LR 532 PH 3 | E.5015029.04 | 5785160 | DOCC | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | Not in the WP | 2019 | SH | LAKEPORT | Humboldt Division Assets | 0 | 2881 | 2881 | 0.54564 | 0.54564 | 0 | [5 empty] | 900000 | -0.3 | 900000.3 | 879982.2 | 0 | 20018.1 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 837365.2 | 42617 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2019-07-26 | Completed | 2019-08-29 | 2019-08-29 | Completed | 2019-08-28 | Completed | 2019-08-28 | Completed | 2019-08-29 | 2019-08-29 | Completed | 2019-09-20 | 2019-09-20 | Completed | 2019-09-13 | 2019-09-13 | Completed | 2019-11-21 | Completed |  |  |  |  | 2019-11-21 | Completed | 2019-11-27 | Completed | 2019-12-16 | Completed | 2020-06-18 | 2018-12-16 | 550 | On/ Ahead Schedule | Completed | 2020-01-06 | 2020-01-10 | Completed | 2021-05-24 | Not Started
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 | 5785512 | DOCC | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 7065 | 7065 | 1.3381 | 1.3381 | 0 | 7492 | 7214 | 1.4189 | 1.3663 | Contract | 4228889 | 1038922 | 3189967 | 1978630.6 | 0 | 1211336.4 | On/Under Budget | 75000 | 0 | 0 | 0 | 0 | 185160.1 | 1793481.4 | -10.9 | Project is not in the WP or in 2020 WP | 75000 | 74989.1 | 10.9 | 74989.1 | 10.9 | 0 | 0 | -10.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145745 | BL-0: | BL-0: 35109540_CWSP - El Dorado 2101 - 19752 - Ph 1.2_08W - Feb. 2020 | 2020-07-23 | 2019-10-09 | Completed | 2019-09-09 | 2019-10-31 | Completed | 2019-08-29 | Completed | 2019-10-14 | Completed | 2019-10-08 | 2019-10-09 | Completed | 2019-10-01 | 2019-10-02 | Completed | 2019-10-16 | 2020-03-02 | Completed | 2019-10-16 | Completed |  |  |  |  | 2019-10-16 | Completed |  |  | 2020-02-18 | Completed | 2020-02-18 | 2020-02-18 | 0 | On/ Ahead Schedule | Completed | 2020-03-16 | 2020-04-29 | Completed | 2021-05-24 | Not Started
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | E.5014759.04 | 5785581 | DOCC | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 12307 | 12307 | 2.3309 | 2.3309 | 0 | 12968 | 13119 | 2.4561 | 2.4847 | Contract | 6122412 | 1221200.5 | 4901211.5 | 4653593.8 | 1506.9 | 249124.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 1819984.5 | 2826944.7 | 6664.6 | Project is not in the WP or in 2020 WP | 0 | 6664.6 | -6664.6 | 6664.6 | -6664.6 | 497.9 | 7323.9 | -1157.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145822 | BL-0: | BL-0: 35106331_CWSP - Volta 1102 - LR 1648 - Ph1.4_08W - May 2020 | 2020-07-24 | 2019-09-13 | Completed | 2020-02-13 | 2020-02-13 | Completed | 2019-09-04 | Completed | 2019-10-10 | Completed | 2019-10-02 | 2019-10-02 | Completed | 2019-10-22 | 2019-10-22 | Completed | 2019-11-15 | 2019-12-01 | Completed | 2019-11-22 | Completed |  |  |  |  | 2020-02-10 | Completed | 2020-05-28 | Completed | 2020-05-28 | Completed | 2020-05-28 | 2020-05-28 | 0 | On/ Ahead Schedule | Completed | 2020-06-23 | 2020-07-07 | Completed | 2021-05-24 | Not Started
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 | 5785515 | DOCC | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2019 | SH | PLCRVLLE | Sierra Assets | 0 | 8922 | 8922 | 1.6898 | 1.6898 | 0 | [5 empty] | 3608462 | 457433.2 | 3151028.8 | 2621459.5 | 0 | 529569.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 3218762.5 | -597303 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2019-09-12 | Completed | 2019-10-01 | 2019-10-01 | Completed | 2019-09-30 | Completed | 2019-10-01 | Completed | 2019-10-01 | 2019-10-01 | Completed | 2019-09-30 | 2019-10-01 | Completed | 2019-10-16 | 2019-11-08 | Completed | 2019-10-03 | Completed |  |  |  |  | 2019-10-03 | Completed |  |  | 2020-03-06 | Completed | 2020-08-12 | 2020-03-06 | 159 | On/ Ahead Schedule | Completed | 2020-03-09 | 2020-03-27 | Completed | 2021-05-24 | Not Started
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 | 5785516 | DOCC | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 12821 | 12821 | 2.4282 | 2.4282 | -3.1006e-15 | 12857 | 12784 | 2.435 | 2.4212 | Contract | 4499650 | -0.7 | 4499650.7 | 3791622.1 | 0 | 708028.6 | On/Under Budget | 75000 | 0 | -4985 | 4985 | 0 | 531278.5 | 3255312.7 | 45.9 | Project is not in the WP or in 2020 WP | 75000 | 80030.9 | -5030.9 | 80030.9 | -5030.9 | 0 | 0 | 5030.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145747 | BL-0: | BL-0: 35109545_CWSP - El Dorado 2101 - 19752 - Ph 2.2_08W - April 2020 | 2020-07-23 | 2019-11-12 | Completed | 2019-11-11 | 2019-11-18 | Completed | 2019-09-23 | Completed | 2019-11-18 | Completed | 2019-11-18 | 2019-12-04 | Completed | 2019-11-27 | 2019-11-27 | Completed | 2019-11-19 | 2019-11-19 | Completed | 2019-12-02 | Completed |  |  |  |  | 2019-12-02 | Completed |  |  | 2020-04-17 | Completed | 2020-04-17 | 2020-04-17 | 0 | On/ Ahead Schedule | Completed | 2020-04-17 | 2020-04-30 | Completed | 2021-05-24 | Not Started
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 | 5785598 | DOCC | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 8058 | 8058 | 1.5261 | 1.5261 | 0 | 7660 | 8100 | 1.4508 | 1.5341 | Contract | 3530637 | 0.6 | 3530636.4 | 3101220.7 | 0 | 429415.7 | On/Under Budget | 42017 | 0 | 0 | 0 | 0 | 275303 | 2776842 | 49075.7 | Project is not in the WP or in 2020 WP | 75000 | 91092.7 | -16092.7 | 91092.7 | -16092.7 | 16888.5 | 16093.6 | 16093.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145750 | BL-0: | BL-0: 35109547_CWSP - El Dorado 2101 - 19752 - Ph 2.4_08W - March 2020 | 2020-07-23 | 2019-10-16 | Completed | 2019-10-18 | 2019-10-18 | Completed | 2019-09-27 | Completed | 2019-10-22 | Completed | 2019-10-23 | 2019-10-24 | Completed | 2020-01-03 | 2020-01-03 | Completed | 2020-01-03 | 2020-01-03 | Completed | 2020-01-06 | Completed |  |  |  |  | 2020-01-06 | Completed |  |  | 2020-03-13 | Completed | 2020-03-13 | 2020-03-13 | 0 | On/ Ahead Schedule | Completed | 2020-03-13 | 2020-03-13 | Completed | 2021-05-24 | Not Started
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 | 5785599 | DOCC | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 15058 | 15058 | 2.8519 | 2.8519 | 0 | 15944 | 15069 | 3.0197 | 2.854 | Contract | 7082947 | 1602579 | 5480368 | 5379872.9 | 0 | 100495.1 | On/Under Budget | 106865 | 0 | 0 | 0 | 0 | 67826 | 4971508.6 | 340538.3 | Project is not in the WP or in 2020 WP | 450000 | 447403.3 | 2596.7 | 447403.3 | 2596.7 | 336335.6 | 6799.9 | -2597.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145751 | BL-0: | BL-0: 35109548_CWSP - El Dorado 2101 - 19752 - Ph 2.5_08W - May 2020 | 2020-07-23 | 2020-01-03 | Completed | 2020-01-14 | 2020-01-14 | Completed | 2019-08-17 | Completed | 2020-01-24 | Completed | 2020-01-20 | 2020-01-20 | Completed | 2020-01-27 | 2020-01-27 | Completed | 2019-12-02 | 2019-12-13 | Completed | 2020-01-27 | Completed |  |  |  |  | 2020-01-27 | Completed |  |  | 2020-05-22 | Completed | 2020-05-22 | 2020-05-22 | 0 | On/ Ahead Schedule | Completed | 2020-05-22 | 2020-08-21 | Completed | 2021-05-24 | Not Started
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 | 5785600 | DOCC | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 7062 | 7062 | 1.3375 | 1.3375 | 0 | 6933 | 7069 | 1.3131 | 1.3388 | Contract | 3123544 | -0.1 | 3123544.1 | 2635581 | 28251.7 | 516214.8 | On/Under Budget | 177549 | 0 | 0 | 0 | 0 | 2357709.6 | 380420.8 | -102549.4 | Project is not in the WP or in 2020 WP | 75000 | 74999.6 | 0.4 | 74999.6 | 0.4 | -102549.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145752 | BL-0: | BL-0: 35109549_CWSP - El Dorado 2101 - 19752 - Ph 3.2_08W - April 2020 | 2020-07-23 | 2019-09-18 | Completed | 2019-09-30 | 2019-09-30 | Completed | 2019-08-29 | Completed | 2019-09-30 | Completed | 2019-09-30 | 2019-09-30 | Completed | 2019-10-01 | 2019-10-01 | Completed | 2019-10-02 | 2020-05-01 | Completed | 2019-10-04 | Completed |  |  |  |  | 2019-10-04 | Completed |  |  | 2020-04-17 | Completed | 2020-04-17 | 2020-04-17 | 0 | On/ Ahead Schedule | Completed | 2020-04-17 | 2020-04-30 | Completed | 2021-05-24 | Not Started
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 | 5785601 | DOCC | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 10111 | 10111 | 1.915 | 1.915 | 0 | 9563 | 10305 | 1.8112 | 1.9517 | Contract | 3044150 | 2 | 3044148 | 2848313.2 | 0 | 195834.8 | On/Under Budget | 75000 | 0 | 0 | 0 | 0 | 3070771.7 | -222458.5 |  | Project is not in the WP or in 2020 WP | 75000 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145753 | BL-0: | BL-0: 35109550_CWSP - El Dorado 2101 - 19752 - Ph 3.3_08W - Jan. 2020 | 2020-07-23 | 2019-09-18 | Completed | 2019-09-30 | 2019-09-30 | Completed | 2019-08-29 | Completed | 2019-10-01 | Completed | 2019-10-01 | 2019-10-01 | Completed | 2019-10-02 | 2019-10-03 | Completed | 2019-11-19 | 2019-12-13 | Completed | 2019-10-04 | Completed |  |  |  |  | 2019-10-04 | Completed |  |  | 2020-01-31 | Completed | 2020-01-31 | 2020-01-31 | 0 | On/ Ahead Schedule | Completed | 2020-02-03 | 2020-02-07 | Completed | 2021-05-24 | Not Started
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 | 5785602 | DOCC | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 7579 | 7579 | 1.4354 | 1.4354 | 0 | 7580 | 7684 | 1.4356 | 1.4553 | Contract | 3172299 | 1.2 | 3172297.8 | 2686392 | 0 | 485905.8 | On/Under Budget | 75000 | 0 | 0 | 0 | 0 | 2714615.5 | -28223.5 |  | Project is not in the WP or in 2020 WP | 75000 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145754 | BL-0: | BL-0: 35109551_CWSP - El Dorado 2101 - 19752 - Ph 3.4_08W - April 2020 | 2020-07-23 | 2019-09-12 | Completed | 2019-09-30 | 2019-10-01 | Completed | 2019-10-01 | Completed | 2019-10-01 | Completed | 2019-10-01 | 2019-10-01 | Completed | 2019-10-01 | 2019-10-01 | Completed | 2019-10-16 | 2019-10-16 | Completed | 2019-10-02 | Completed |  |  |  |  | 2019-10-02 | Completed |  |  | 2020-04-17 | Completed | 2020-04-17 | 2020-04-17 | 0 | On/ Ahead Schedule | Completed | 2020-04-17 | 2020-04-30 | Completed | 2021-05-24 | Not Started
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | DOCC | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 11175 | 11175 | 2.1165 | 2.1165 | 0 | 11274 | 11507 | 2.1352 | 2.1794 | Contract | 5804263 | 0.9 | 5804262.1 | 4548604.4 | 0 | 1255657.7 | On/Under Budget | 74326 | 0 | 0 | 0 | 0 | 4523869.9 | -75940 | 100674.5 | Project is not in the WP or in 2020 WP | 175000 | 175000.5 | -0.5 | 175000.5 | -0.5 | 100674.5 | 0 | 0 | 0 | 0 | 0 | 0 | 74326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145755 | BL-0: | BL-0: 35109552_CWSP - El Dorado 2101 - 19752 - Ph 3.5_08W - Feb. 2020 | 2020-07-23 | 2019-09-25 | Completed | 2019-09-30 | 2019-09-30 | Completed | 2019-08-29 | Completed | 2019-09-30 | Completed | 2019-09-30 | 2019-09-30 | Completed | 2019-10-03 | 2019-10-04 | Completed | 2019-10-24 | 2019-10-24 | Completed | 2019-10-07 | Completed |  |  |  |  | 2019-10-07 | Completed |  |  | 2020-02-11 | Completed | 2020-02-11 | 2020-02-11 | 0 | On/ Ahead Schedule | Completed | 2020-02-17 | 2020-02-28 | Completed | 2021-05-24 | Not Started
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 | 5785604 | DOCC | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 14080 | 14080 | 2.6667 | 2.6667 | 0 | 14080 | 13725 | 2.6667 | 2.5994 | Contract | 4009924 | -0.5 | 4009924.5 | 3830827.7 | 0 | 179096.8 | On/Under Budget | 75000 | 0 | 0 | 0 | 0 | 2545093.1 | 1285734.6 |  | Project is not in the WP or in 2020 WP | 75000 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145756 | BL-0: | BL-0: 35109553_CWSP - El Dorado 2101 - 19752 - Ph 3.6_08W - Jan 2020 | 2020-07-23 | 2019-09-26 | Completed | 2019-09-06 | 2019-09-06 | Completed | 2019-10-11 | Completed | 2020-02-03 | Completed | 2019-09-30 | 2019-09-30 | Completed | 2019-10-14 | 2019-10-14 | Completed | 2019-11-01 | 2020-01-13 | Completed | 2019-10-21 | Completed |  |  |  |  | 2019-10-21 | Completed |  |  | 2020-01-29 | Completed | 2020-01-29 | 2020-01-29 | 0 | On/ Ahead Schedule | Completed | 2020-01-20 | 2020-01-24 | Completed | 2021-05-24 | Not Started
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | DOCC | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 6641 | 6641 | 1.2578 | 1.2578 | 0 | 6641 | 6661 | 1.2578 | 1.2616 | Contract | 2287663 | 11025 | 2276638 | 2058021.5 | 0 | 218616.5 | On/Under Budget | 74251 | 0 | 0 | 0 | 0 | 27262.3 | 2030009.8 | 749.4 | Project is not in the WP or in 2020 WP | 75000 | 75000.4 | -0.4 | 75000.4 | -0.4 | 749.4 | 0 | 0 | 0 | 0 | 74251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145757 | BL-0: | BL-0: 35109554_CWSP - El Dorado 2101 - 19752 - Ph 4.2_08W - April 2020 | 2020-07-23 | 2020-01-17 | Completed | 2020-04-22 | 2020-04-23 | Completed | 2019-08-27 | Completed | 2020-02-20 | Completed | 2020-01-29 | 2020-01-29 | Completed | 2020-02-18 | 2020-02-18 | Completed | 2020-01-21 | 2020-04-17 | Completed | 2020-02-13 | Completed |  |  |  |  | 2020-02-13 | Completed |  |  | 2020-04-03 | Completed | 2020-04-03 | 2020-04-03 | 0 | On/ Ahead Schedule | Completed | 2020-04-03 | 2020-05-12 | Completed | 2021-05-24 | Not Started
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 | 5785606 | DOCC | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 11678 | 11678 | 2.2117 | 2.2117 | 0 | 11685 | 11318 | 2.2131 | 2.1436 | Contract | 4477708 | 5757.5 | 4471950.5 | 3634489.1 | 0 | 837461.4 | On/Under Budget | 71973 | 0 | 0 | 0 | 0 | 2824429.5 | 807032.6 | 3027 | Project is not in the WP or in 2020 WP | 75000 | 75000 | 0 | 75000 | 0 | 3027 | 0 | 0 | 0 | 0 | 0 | 71973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145758 | BL-0: | BL-0: 35109555_CWSP - El Dorado 2101 - 19752 - Ph 4.3_08W - Feb. 2020 | 2020-07-23 | 2019-11-08 | Completed | 2019-08-30 | 2019-09-05 | Completed | 2019-08-23 | Completed | 2019-12-19 | Completed | 2019-12-19 | 2019-12-19 | Completed | 2019-12-10 | 2019-12-10 | Completed | 2019-11-04 | 2020-02-28 | Completed | 2019-12-09 | Completed |  |  |  |  | 2019-12-09 | Completed |  |  | 2020-02-21 | Completed | 2020-02-21 | 2020-02-21 | 0 | On/ Ahead Schedule | Completed | 2020-02-21 | 2020-08-21 | Completed | 2021-05-24 | Not Started
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 | 5785607 | DOCC | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 1618 | 1618 | 0.30644 | 0.30644 | 0 | 1618 | 1618 | 0.30644 | 0.30644 | Contract | 1197284 | 80818.4 | 1116465.6 | 898206.2 | 0 | 218259.4 | On/Under Budget | 75000 | 0 | 0 | 0 | 0 | 689326.4 | 208879.8 |  | Project is not in the WP or in 2020 WP | 75000 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145759 | BL-0: | BL-0: 35109556_CWSP - El Dorado 2101 - 19752 - Ph 4.4_08W - March 2020 | 2020-07-23 | 2019-08-26 | Completed | 2019-10-16 | 2019-10-17 | Completed | 2019-09-03 | Completed | 2019-10-18 | Completed | 2019-10-17 | 2019-10-17 | Completed | 2019-10-18 | 2019-10-18 | Completed | 2019-10-16 | 2020-01-24 | Completed | 2019-10-21 | Completed |  |  |  |  | 2019-10-21 | Completed |  |  | 2020-03-06 | Completed | 2020-03-06 | 2020-03-06 | 0 | On/ Ahead Schedule | Completed | 2020-03-06 | 2021-04-02 | In Progress | 2021-05-24 | Not Started
35105647 | BR-03-09-W (E) MERRILL RD PARB |  | 5786123 | DOCC | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2020 |  |  | CHICO | North Valley Assets | [10 empty] | Contract | 1294583.67 | -355416.33 | 1650000 | 1595820.9 | 0 | 54179.1 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 1382657.9 | 213163 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35105647 | BR-03-09-W (E) MERRILL RD PARB |  | 5786123 | DOCC | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2020 |  |  | CHICO | North Valley Assets | [10 empty] | Contract | 1294583.67 | -355416.33 | 1650000 | 1595820.9 | 0 | 54179.1 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 1382657.9 | 213163 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | E.5014544.02 | 5785418 | DOCC | 08W | A1CO | Antonio Miguel Chan | SHMG | Safeer Mirza | J7TY | Jace Thorsen | 2020 |  | SH | CONCORD | Diablo Assets | 0 | 5875 | 5875 | 1.1127 | 1.1127 | 0 | 6489 | 5368 | 1.229 | 1.0167 | Contract | 4408478 | 609832.1 | 3798645.9 | 3441611.1 | 0 | 357034.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 495114.1 | 2938936.4 | 7560.6 | Project is not in the WP or in 2020 WP | 0 | 16880.4 | -16880.4 | 7560.6 | -7560.6 | 0 | 3449 | 4111.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | E.5015491.04 | 5785303 | DOCC | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2021 | 2020 | SH | GRSSVLLY | Sierra Assets | 3761 | 2387 | 6148 | 1.1644 | 1.1644 | 0 | 5642 | 5706 | 1.0686 | 1.0807 | Contract | 2927538 | 742038.8 | 2185499.2 | 1728190.4 | 0 | 457308.8 | On/Under Budget | -20298 | 0 | 0 | 0 | 0 | 35798.4 | 1627573.9 | 64818.1 | Budget Allocated | 131088 | 64818.1 | 66269.9 | 44520.1 | 86567.9 | 8886.3 | 11598.8 | 44333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 151685 | BL-1 | BL-1 35098621_CWSP-COLUMBIA HILL 1101-LR 2212 PH4_08W - Nov. 2020 | 2020-11-24 | 2019-10-24 | Completed | 2020-05-05 | 2020-05-05 | Completed | 2020-05-25 | Completed | 2020-05-05 | Completed | 2020-05-05 | 2020-05-05 | Completed | 2020-05-01 | 2020-05-29 | Completed | 2020-05-15 | 2020-05-29 | Completed | 2020-06-01 | Completed |  |  |  |  | 2020-06-01 | Completed | 2020-09-29 | Completed | 2020-12-03 | Completed | 2021-01-29 | 2020-12-03 | 57 | On/ Ahead Schedule | Completed | 2021-03-01 | 2021-03-04 | Completed | 2021-05-14 | Not Started
35099654 | BR-04-01-W (E) SUNSET DR PARB |  | 5786123 | DOCC | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 |  |  | CHICO | North Valley Assets | [10 empty] | GC | 527505.94 | 27505.94 | 500000 | 404444.2 | 0 | 95555.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 626349 | -500878.2 | 278973.5 | Project is not in the WP or in 2020 WP | 0 | 278973.5 | -278973.5 | 278973.5 | -278973.5 | 199152.6 | 14463.3 | 65357.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 | 5782534 | DOCC | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2019 | SH | PLCRVLLE | Sierra Assets | 0 | 9006 | 9006 | 1.7057 | 1.7057 | 0 | [5 empty] | 3201494 | -0.4 | 3201494.4 | 2706369.9 | 0 | 495124.5 | On/Under Budget | 0 | 0 | 0 | 0 | 3262.5 | 2815281.3 | -112173.9 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2019-08-27 | Completed | 2019-09-17 | 2019-09-17 | Completed | 2019-08-19 | Completed | 2019-09-18 | Completed | 2019-09-18 | 2019-09-18 | Completed | 2019-09-18 | 2019-09-18 | Completed | 2019-09-20 | 2020-03-20 | Completed | 2019-09-19 | Completed |  |  |  |  | 2019-09-19 | Completed |  |  | 2019-12-03 | Completed | 2020-05-18 | 2019-12-03 | 167 | On/ Ahead Schedule | Completed | 2020-03-20 | 2020-03-27 | Completed | 2021-05-24 | Not Started
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | E.5015428.01 | 5782587 | DOCC | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 11145 | 11145 | 2.1108 | 2.1108 | 0 | 11306 | 11145 | 2.1413 | 2.1108 | Contract | 5418545 | 333247 | 5085298 | 4719488.2 | 0 | 365809.8 | On/Under Budget | 0 | 0 | 0 | 0 | 13660.6 | 3995262 | 706763.3 | 3802.3 | Project is not in the WP or in 2020 WP | 0 | 3802.3 | -3802.3 | 3802.3 | -3802.3 | 3101.9 | 1605.4 | -905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145806 | BL-0: | BL-0: 35058905_CWSP - Volta 1102 - LR 1648 - Ph 4.1_08W - Jan 2020 | 2020-07-24 | 2019-08-30 | Completed | 2019-11-27 | 2019-11-27 | Completed | 2019-08-16 | Completed | 2019-10-14 | Completed | 2019-09-11 | 2019-09-11 | Completed | 2019-09-25 | 2019-09-25 | Completed | 2019-10-22 | 2019-10-22 | Completed | 2019-11-05 | Completed |  |  |  |  | 2019-11-19 | Completed |  |  | 2020-01-16 | Completed | 2020-01-16 | 2020-01-16 | 0 | On/ Ahead Schedule | Completed | 2020-05-04 | 2020-06-01 | Completed | 2021-05-24 | Not Started
35061709 | SILVERADO 2104 RECONDUCTOR PROJECT |  | 5786199 | DOCC | 08W | S2WT | Steve Whitman |  |  |  |  | Not in the WP | 2019 | SH | NAPA |  | 0 | 8003 | 8003 | 1.5157 | 1.5157 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [25 empty] | 2021-04-02 |  |  |  |  | 2019-02-26 | Completed | 2019-04-26 | 2019-04-26 | Completed | 2019-06-03 | Completed | 2019-08-13 | Completed | 2019-08-19 | 2019-08-20 | Completed | 2019-10-21 | 2019-10-22 | Completed | 2019-10-11 | 2019-10-11 | Completed | 2019-10-23 | Completed |  |  |  |  | 2019-10-23 | Completed |  |  | 2019-12-14 | Completed | 2020-06-02 | 2019-12-14 | 171 | On/ Ahead Schedule | Completed | 2021-05-04 | 2021-05-17 | Not Started | 2021-06-23 | Not Started
35043299 | CWSP-OH COND RPLC: EEL RIVER 1102 FU1907 |  | 5533649 | DOCC | 08W | A1CO | Antonio Miguel Chan | SHMG | Safeer Mirza | J7TY | Jace Thorsen | Not in the WP | 2019 | SH | FORTUNA | Humboldt Division Assets | 0 | 6376 | 6376 | 1.2076 | 1.2076 | 0 | [5 empty] | 1224411 | 0.4 | 1224410.6 | 1211548.4 | 0 | 12862.2 | On/Under Budget | 0 | 0 | 0 | 0 | 928 | 1200028.6 | 10591.8 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 128577 | WSHP | WSHP 190307 - 35043299_EEL RIVER 1102 FU1907_08W - B1 | 2019-03-07 | 2019-06-20 | Completed | 2019-07-03 | 2019-07-04 | Completed | 2019-07-26 | Completed | 2019-07-11 | Completed | 2019-09-05 | 2019-09-06 | Completed |  |  |  | 2019-09-04 | 2019-09-04 | Completed | 2019-09-09 | Completed |  |  |  |  | 2019-09-09 | Completed |  |  | 2019-11-27 | Completed | 2019-10-07 | 2019-11-27 | -51 | Behind Schedule | Completed |  |  |  | 2021-05-25 | Not Started
35043303 | CWSP-OH COND RPLC: EEL RIVER 1102 FU1909 |  | 5530164 | DOCC | 08W | S2WT | Steve Whitman |  |  |  |  | Not in the WP | 2019 | SH | FORTUNA |  | 0 | 8140 | 8140 | 1.5417 | 1.5417 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [25 empty] | 2021-04-02 | 128576 | WSHP | WSHP 190307 - 35043303_EEL RIVER 1102 FU 1909_08W - B1 | 2019-03-07 | 2019-06-04 | Completed | 2019-06-27 | 2019-06-27 | Completed |  |  | 2019-08-02 | Completed | 2019-07-05 | 2019-07-08 | Completed |  |  |  | 2019-07-01 | 2019-07-02 | Completed | 2019-08-12 | Completed |  |  |  |  | 2019-08-12 | Completed |  |  | 2019-09-19 | Completed | 2019-12-03 | 2019-09-19 | 75 | On/ Ahead Schedule | Completed |  |  |  | 2021-05-24 | Not Started
31344015 | CNCL: 2019 CALISTOGA 1101 HIGH SPLICE CT |  | 5530168 | DOCC | 08W | FXRZ | Fernando Recoder |  |  |  |  | Not in the WP |  |  | NAPA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31289238 | FRUITLAND 1142 INS TREE WIRE LR 6064 |  | 5530164 | DOCC | 08W | S2WT | Steve Whitman |  |  |  |  | Not in the WP | 2019 | SH | GARBRVLE |  | 0 | 6271 | 6271 | 1.1877 | 1.1877 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [25 empty] | 2021-04-02 | 118758 | BL-2: | BL-2: 31157672_R7 S.ROSA A 1103 RECONDUCTOR OUTLET - Aug. 18 | 2018-08-04 | 2019-06-07 | Completed |  |  | Completed | 2019-06-10 | Completed | 2019-07-15 | Completed | [6 empty] | 2019-07-08 | 2019-07-10 | Completed | 2019-07-15 | Completed |  |  |  |  | 2019-07-15 | Completed |  |  | 2019-07-26 | Completed | 2018-12-31 | 2019-07-26 | -207 | Behind Schedule | Completed |  |  |  | 2020-02-27 | Completed
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 |  | 5530175 | DOCC | 08W | A1CO | Antonio Miguel Chan | SHMG | Safeer Mirza | J7TY | Jace Thorsen | Not in the WP | 2019 | SH | STROSA | Sonoma Assets | 0 | 2580 | 2580 | 0.48864 | 0.48864 | 0 | [5 empty] | 1092540 | 317223.4 | 775316.6 | 652020.6 | 0 | 123296 | On/Under Budget | 0 | 0 | 0 | 0 | 34250.3 | 847580.9 | -230698.4 | 406.6 | Project is not in the WP or in 2020 WP | 0 | 22073.2 | -22073.2 | 406.6 | -406.6 | 406.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 128631 | WSHP | WSHP 190307 - 31275658_DUNBAR 1102_08W - B1 | 2019-03-07 | 2019-03-13 | Completed | 2019-03-08 | 2019-03-21 | Completed | 2019-04-25 | Completed | 2019-09-26 | Completed | 2019-09-26 | 2019-09-27 | Completed | 2019-04-10 | 2019-04-15 | Completed | 2019-08-05 | 2019-08-05 | Completed | 2019-08-06 | Completed |  |  |  |  | 2019-08-06 | Completed |  |  | 2019-08-30 | Completed | 2019-07-29 | 2019-08-30 | -32 | Behind Schedule | Completed | 2019-06-28 | 2019-07-12 | Completed | 2021-05-04 | Not Started
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | P.11381 | 5530159 | DOCC | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | Not in the WP | 2022 |  | STCRUZ | Central Coast Assets | 0 | 8500 | 8500 | 1.6098 | 0 | 1.6098 | [5 empty] | 3066747 | 413254 | 2653493 | 2297092 | 0 | 356401 | On/Under Budget | 4870.3 | 4870.3 | 0 | 4870.3 | 9434.1 | 42266.6 | 2236195 | 7037.9 | Project is not in the WP or in 2020 WP | 0 | 16778.5 | -16778.5 | 16778.5 | -16778.5 | 3785.4 | 1882 | 1370.5 | 4870.3 | 4870.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158220 | BL-0 | BL-0 31272374 CWSP PT. MORETTI FROM 5043 TO 5955 - Mar. 2021 | 2021-03-31 | 2019-02-15 | Completed |  |  | Completed | 2019-04-25 | Completed | 2021-02-06 | Completed | [6 empty] | 2020-03-07 | 2020-10-03 | Completed | 2020-08-31 | Completed |  |  |  |  | 2020-09-07 | Completed | 2020-08-31 | Completed | 2020-12-18 | Completed | 2020-12-18 | 2020-12-18 | 0 | On/ Ahead Schedule | Completed |  |  |  | 2021-07-20 | Not Started
31272375 | CWSP PT. MORETTI BEYOND 5995 | P.11379 | 5530159 | DOCC | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | Not in the WP |  |  | STCRUZ | Central Coast Assets | 0 | 5150 | 5150 | 0.97538 | 0 | 0.97538 | [5 empty] | 55000 | 0 | 55000 | 82551 | 0 | -27551 | OverRun | 0 | 0 | 0 | 0 | 8996.6 | 33418.5 | 34898.2 | 1734.5 | Project is not in the WP or in 2020 WP | 0 | 1734.5 | -1734.5 | 1734.5 | -1734.5 | 1734.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 | P.11104 | 5530168 | DOCC | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2020 |  | SH | SNRAFAEL | North Bay Assets | 0 | 9487 | 9487 | 1.7968 | 1.7968 | 3.1006e-15 | 6861 | 6500 | 1.2994 | 1.2311 | Contract | 3466319 | 0 | 3466319 | 3482680.1 | 0 | -16361.1 | OverRun | 0 | 0 | 0 | 0 | 7077.1 | 53566.5 | 3328524.8 | 40382.9 | Project is not in the WP or in 2020 WP | 0 | 40382.9 | -40382.9 | 40382.9 | -40382.9 | 40382.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31209950 | R7 RECON POTTER VLY 1105 ( VAN ARSDALE) | P.11913 | 5530164 | DOCC | 08W | A1CO | Antonio Miguel Chan | SHMG | Safeer Mirza | J7TY | Jace Thorsen | Not in the WP |  | SH | UKIAH | Humboldt Division Assets | 0 | 3008 | 3008 | 0.5697 | 0.5697 | 0 | [5 empty] | 273660 | -943257.9 | 1216917.9 | 1212818 | 0 | 4099.9 | On/Under Budget | 0 | 0 | 0 | 0 | 18719.9 | 1454401.9 | -261375.4 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35023687 | R2RPL OH WIRE ON B LOMND 0401 17-0095503 | P.11844 | 5530159 | DOCC | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | STCRUZ | Central Coast Assets | 0 | 7044 | 7044 | 1.3341 | 1.3341 | 0 | [5 empty] | 4004352 | 0 | 4004352 | 3907306.6 | 0 | 97045.4 | On/Under Budget | 0 | 0 | 0 | 0 | 8068.7 | 3870173.7 | 29064.2 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31157301 | X-RECNDUCTR-POINT M1101_2598 SMITH GRDE |  | 5513259 | DOCC | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | 5790010 | DOCC | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2021 | 2020 | SH | CHICO | North Valley Assets | 10150 | 0 | 10150 | 1.9223 | 1.9223 | 0 | 20644 | 10150 | 3.9098 | 1.9223 | GC | 14251728 | 822083.8 | 13429644.2 | 12233502.2 | 0 | 1196142 | On/Under Budget | 0 | 0 | -132.7 | 132.7 | 0 | 11420292.3 | 812210.5 | 866.7 | Request 2021 Budget | 0 | 999.4 | -999.4 | 999.4 | -999.4 | 557.6 | 147.7 | 294.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2019-10-24 | Completed | 2019-11-05 | 2019-11-26 | Completed | 2019-10-14 | Completed | 2019-10-11 | Completed | 2019-11-25 | 2019-11-25 | Completed | 2019-12-06 | 2019-12-06 | Completed |  |  |  | 2019-10-14 | Completed |  |  |  |  | 2019-12-02 | Completed | 2020-06-26 | Completed | 2020-06-26 | Completed | 2020-06-12 | 2020-06-26 | -14 | Behind Schedule | Completed | 2020-06-25 | 2020-06-26 | Completed | 2021-07-29 | Not Started
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | E.5014730.02 | 5785961 | DOCC | 08W | PXSO | Peter Siu | C2LJ | Cynthia Lau | MUHQ | Matt Haley | 2021 | 2021 | SH | SONORA | Yosemite Assets | 0 | 5333 | 5333 | 1.01 | 1.01 | 0 | 7525 | 0 | 1.4252 | 0 | Contract | 2704457 | 0.1 | 2704456.9 | 1373194.9 | 230884.7 | 1562146.7 | On/Under Budget | 0 | 173720.8 | -223 | 173943.8 | 0 | 313 | 1309697.1 | 62961.7 | Request 2021 Budget | 0 | 236905.5 | -236905.5 | 236905.5 | -236905.5 | 13260.3 | 8105.9 | 41818.5 | 173720.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 152819 | BL-1 | BL-1 35116800_CWSP - MIWUK 1702 - LR 6018 - PH 1.2_08W - Dec. 2020 | 2020-12-29 | 2020-03-12 | Completed | 2020-03-31 | 2020-03-31 | Completed | 2020-04-13 | Completed | 2020-07-22 | Completed | 2020-07-16 | 2020-07-16 | Completed | 2020-07-16 | 2020-07-29 | Completed | 2020-08-03 | 2020-08-03 | Completed | 2020-08-10 | Completed |  |  |  |  | 2020-08-10 | Completed | 2021-01-08 | Completed | 2021-01-08 | Completed | 2021-04-07 | 2021-02-04 | 62 | On/ Ahead Schedule | Completed |  |  |  | 2021-10-22 | Not Started
35117983 | BR-02-07-W (E) DOLORES DR, PARB |  | 5786123 | DOCC | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2020 |  |  | CHICO | North Valley Assets | [11 empty] | 1 | -4715572 | 4715573 | 4853506 | 0 | -137933 | OverRun | 0 | 0 | 0 | 0 | 0 | 4235.7 | 4692453.4 | 156816.9 | Project is not in the WP or in 2020 WP | 0 | 156816.9 | -156816.9 | 156816.9 | -156816.9 | 108076.2 | 17288.6 | 31452.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | E.5015569.02 | 5785657 | DOCC | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2021 | 2020 | SH | GRSSVLLY | Fire Risk Mitigation Memo Account | 0 | 9416 | 9416 | 1.7833 | 1.7833 | 0 |  |  |  |  | GC | 5231108 | 1374305.6 | 3856802.4 | 3163574.3 | 22803.5 | 716031.6 | On/Under Budget | -312588 | 0 | -8960.7 | 8960.7 | 0 | 145465.8 | 2960095.5 | 49052.3 | Budget Allocated | 88800 | 58013 | 30787 | -254575 | 343375 | 38606.9 | 10193.2 | 9212.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -312588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 151680 | BL-2 | BL-2 35115155_CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 - Nov. 2020 | 2020-11-24 | 2019-11-14 | Completed | 2019-12-17 | 2020-01-15 | Completed | 2019-12-29 | Completed | 2020-03-13 | Completed | 2020-03-13 | 2020-03-13 | Completed | 2020-01-13 | 2020-01-24 | Completed | 2020-01-06 | 2020-05-26 | Completed | 2020-01-13 | Completed |  |  |  |  | 2020-01-13 | Completed | 2020-02-28 | Completed | 2020-02-06 | Completed | 2021-02-26 | 2021-02-25 | 1 | On/ Ahead Schedule | Completed | 2021-04-02 | 2021-06-24 | Not Started | 2021-09-27 | Not Started
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | E.5014730.04 | 5785963 | DOCC | 08W | PXSO | Peter Siu | C2LJ | Cynthia Lau | MUHQ | Matt Haley | 2020 | 2020 | SH | SONORA | Yosemite Assets | 0 | 11704 | 11704 | 2.2167 | 2.2167 | 0 | 11739 | 1260 | 2.2233 | 0.23864 | GC | 2559279 | -2559278.8 | 5118557.8 | 2458418.2 | 0 | 2660139.6 | On/Under Budget | 0 | 0 | -1033.7 | 1033.7 | 0 | 331.3 | 2455272.4 | 1780.9 | Project is not in the WP or in 2020 WP | 0 | 2814.6 | -2814.6 | 2814.6 | -2814.6 | 367.5 | 699.6 | 1747.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 152750 | BL-1 | BL-1 35116802_CWSP - MIWUK 1702 - LR 6018 - PH 1.4_08W - Dec. 2020 | 2020-12-22 | 2020-02-20 | Completed | 2020-02-21 | 2020-03-17 | Completed | 2020-03-31 | Completed | 2020-06-10 | Completed | 2020-05-11 | 2020-05-11 | Completed | 2020-05-11 | 2020-05-29 | Completed | 2020-06-08 | 2020-06-19 | Completed | 2020-06-16 | Completed |  |  |  |  | 2020-06-16 | Completed | 2020-09-17 | Completed | 2020-09-17 | Completed | 2020-09-17 | 2020-09-17 | 0 | On/ Ahead Schedule | Completed | 2020-09-30 | 2020-09-30 | Completed | 2021-08-31 | Not Started
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | E.5014776.03 | 5785982 | DOCC | 08W | M2HM | Matthew Joseph Herron | J1EP | Joni Eldred | J7TY | Jace Thorsen | 2021 | 2020 | SH | SONORA | Yosemite Assets | 0 | 12091 | 12091 | 2.29 | 2.29 | 0 | 12386 | 9451 | 2.3458 | 1.79 | Contract | 3849738 | 854907.6 | 2994830.4 | 1921672.8 | 92729.9 | 1165887.5 | On/Under Budget | 10092.7 | 90833.9 | -308.4 | 91142.3 | 0 | 5552.2 | 1846752.8 | 69059.4 | Request 2021 Budget | 0 | 170294.4 | -170294.4 | 170294.4 | -170294.4 | 118993.3 | 18529.7 | -68155.2 | 90833.9 | 10092.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 152683 | BL-1 | BL-1 35116442_CWSP - MIWUK 1702 - LR 38218 - PH 1.3_08W - Dec. 2020 | 2020-12-21 | 2020-02-27 | Completed | 2020-05-26 | 2020-06-05 | Completed | 2020-05-20 | Completed | 2020-06-05 | Completed | 2020-06-12 | 2020-06-12 | Completed | 2020-06-12 | 2020-07-06 | Completed | 2020-07-07 | 2020-07-31 | Completed | 2020-07-15 | Completed |  |  |  |  | 2020-07-15 | Completed | 2021-01-29 | Completed | 2020-12-15 | Completed | 2021-01-29 | 2021-01-18 | 11 | On/ Ahead Schedule | Completed | 2021-01-18 | 2021-02-09 | Completed | 2021-06-30 | Not Started
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | E.5015235.04 | 5786024 | DOCC | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2020 |  | SH | ANGLSCMP | Stockton Assets | 0 | 5727 | 5727 | 1.0847 | 1.0847 | 0 | 6672 | 0 | 1.2636 | 0 | Contract | 2958923 | 984908.3 | 1974014.7 | 1571110.2 | 66680.2 | 469584.7 | On/Under Budget | 0 | 0 | -68576.7 | 68576.7 | 0 | 398.5 | 1543526.9 | -41391.9 | Project is not in the WP or in 2020 WP | 0 | 27184.8 | -27184.8 | 27184.8 | -27184.8 | 22857.2 | 2144 | 2183.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 154990 | BL-1 | BL-1 35115855_CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1.4_08W - Jan. 2021 | 2021-01-25 | 2020-01-15 | Completed | 2020-05-05 | 2020-05-06 | Completed | 2020-01-27 | Completed | 2020-05-19 | Completed | 2020-07-03 | 2020-07-03 | Completed | 2020-07-06 | 2020-07-20 | Completed | 2020-06-05 | 2020-07-10 | Completed | 2020-07-27 | Completed |  |  |  |  | 2020-07-27 | Completed | 2020-09-25 | Completed | 2020-10-26 | Completed | 2021-04-26 | 2021-04-26 | 0 | On/ Ahead Schedule | Not Started | 2021-04-27 | 2021-05-10 | Not Started | 2021-06-16 | Not Started
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | E.5014733.07 | 5785971 | DOCC | 08W | M2HM | Matthew Joseph Herron | J1EP | Joni Eldred | J7TY | Jace Thorsen | 2020 | 2020 | SH | SONORA | Yosemite Assets | 0 | 4771 | 4771 | 0.9036 | 0.9036 | 0 | 4715 | 0 | 0.89299 | 0 | Contract | 1195542 | 0 | 1195542 | 720832.5 | 0 | 474709.5 | On/Under Budget | 0 | 0 | -250 | 250 | 0 | 29384.9 | 700382.1 | -9184.5 | Project is not in the WP or in 2020 WP | 0 | -8934.5 | 8934.5 | -8934.5 | 8934.5 | -4735.8 | -6129.1 | 1930.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145847 | BL-0: | BL-0: 35116390_CWSP - MIWUK 1701 - LR 8060 - PH 1.7_08W - Nov 2021 | 2020-07-24 | 2020-01-10 | Completed | 2020-03-17 | 2020-07-09 | Completed | 2020-08-03 | Completed | 2020-08-03 | Completed | 2020-09-08 | 2020-09-08 | Completed | 2020-09-09 | 2020-09-10 | Completed | 2020-08-19 | 2020-09-21 | Completed | 2020-10-05 | Completed |  |  |  |  | 2020-10-05 | Completed | 2020-10-12 | Completed | 2020-10-12 | Completed | 2020-11-09 | 2020-10-12 | 28 | On/ Ahead Schedule | Completed | 2020-10-12 | 2020-10-12 | Completed | 2021-07-22 | Not Started
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | E.5014773.02 | 5785976 | DOCC | 08W | PXSO | Peter Siu | C2LJ | Cynthia Lau | MUHQ | Matt Haley | 2021 | 2021 | SH | SONORA | Yosemite Assets | 0 | 10740 | 10740 | 2.0341 | 2.0902 | -0.056061 | 10932 | 0 | 2.0705 | 0 | Contract | 3920203 | -3920203.2 | 7840406.2 | 1816461.5 | 80500.8 | 6104445.5 | On/Under Budget | 0 | 2345.3 | -8197.2 | 10542.5 | 0 | 1425.3 | 1532414.3 | 274424.7 | Budget Allocated | 378038 | 284967.2 | 93070.8 | 284967.2 | 93070.8 | 210049.1 | 28961.9 | 43610.9 | 2345.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 152817 | BL-2 | BL-2 35116391_CWSP - MIWUK 1702 - OCB - PH 1.2_08W - Dec 2020 | 2020-12-29 | 2020-02-25 | Completed | 2020-02-28 | 2020-03-20 | Completed | 2020-04-20 | Completed | 2020-04-20 | Completed | 2020-06-01 | 2020-07-01 | Completed | 2020-06-15 | 2020-06-22 | Completed | 2020-03-27 | 2020-04-21 | Completed | 2020-06-22 | Completed |  |  |  |  | 2020-06-22 | Completed | 2021-01-15 | Completed | 2021-02-04 | Completed | 2021-04-01 | 2021-01-15 | 76 | On/ Ahead Schedule | Completed | 2021-01-15 | 2021-01-15 | Completed | 2021-10-07 | Not Started
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | E.5014726.05 | 5786010 | DOCC | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2020 |  | SH | JACKSON | Stockton Assets | 0 | 10822 | 10822 | 2.0496 | 2.0496 | 0 | 10788 | 0 | 2.0432 | 0 | Contract | 2715235.15 | -412833.05 | 3128068.2 | 1189939 | 136704.1 | 2074833.3 | On/Under Budget | 0 | 60000 | -21940.5 | 81940.5 | 0 | 2339.9 | 1178556.4 | -12897.8 | Project is not in the WP or in 2020 WP | 0 | 69042.7 | -69042.7 | 69042.7 | -69042.7 | 7037.3 | 1013.1 | 992.3 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | E.5015687.05 | 5785648 | DOCC | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 7924 | 7924 | 1.5008 | 1.5008 | 0 | 7924 | 7924 | 1.5008 | 1.5008 | Contract | 3756886 | 1013726 | 2743160 | 2249397.4 | 0 | 493762.6 | On/Under Budget | 63094 | 0 | -250 | 250 | 0 | 3552.1 | 2233688.1 | 11907.2 | Project is not in the WP or in 2020 WP | 75000 | 75251.2 | -251.2 | 75251.2 | -251.2 | 2812.2 | 9092.7 | 252.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145865 | BL-0 | BL-0 35112434_CWSP - El Dorado 2102 - LR 19562 - Ph 1.4_08W - Nov 2020 | 2020-07-25 | 2020-04-10 | Completed | 2020-05-05 | 2020-05-20 | Completed | 2020-03-02 | Completed | 2020-05-20 | Completed | 2021-04-02 | 2021-04-02 | Not Started | 2020-05-26 | 2020-06-12 | Completed | 2020-06-24 | 2020-08-20 | Completed | 2020-07-27 | Completed |  |  |  |  | 2020-07-27 | Completed | 2020-10-02 | Completed | 2020-10-02 | Completed | 2020-11-02 | 2020-10-02 | 31 | On/ Ahead Schedule | Completed | 2020-10-12 | 2020-10-16 | Completed | 2021-05-25 | Not Started
35112249 | BR-04-07-W (E) CRESTMOOR PARB |  | 5786123 | DOCC | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | 2020 |  |  | CHICO | North Valley Assets | [10 empty] | Contract | 1977495.99 | -3000000.01 | 4977496 | 4287754.4 | 0 | 689741.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 1450348.1 | 2837406.3 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | DOCC | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 6871 | 6871 | 1.3013 | 1.3013 | 0 | 6653 | 0 | 1.26 | 0 |  | 5238478 | 2274925.7 | 2963552.3 | 2245373.1 | 0 | 718179.2 | On/Under Budget | 43461 | 11514 | -1309.2 | 12823.2 | 0 | 58059.4 | 2110813.4 | 75191.1 | Project is not in the WP or in 2020 WP | 0 | 131475.3 | -131475.3 | 131475.3 | -131475.3 | 12643.2 | -25483.3 | 89340.4 | 11514 | 11514 | 11514 | 11514 | 8919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157115 | BL-1 | BL-1 35112425_CWSP - El Dorado 2101 - OCB Zone - Ph 1.2_08W - Mar. 2021 | 2021-03-07 | 2019-10-23 | Completed | 2020-02-10 | 2020-02-19 | Completed | 2020-01-03 | Completed | 2020-01-03 | Completed | 2020-03-02 | 2020-03-02 | Completed | 2020-03-09 | 2020-06-04 | Completed | 2020-02-28 | 2020-07-23 | Completed | 2020-05-04 | Completed |  |  |  |  | 2020-05-05 | Completed | 2020-07-13 | Completed | 2020-07-13 | Completed | 2020-07-21 | 2020-07-21 | 0 | On/ Ahead Schedule | Completed | 2020-08-21 | 2020-08-21 | Completed | 2021-05-24 | Not Started
35112089 | BR-01-05-W (E) MEYERS PARB |  | 5786123 | DOCC | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | 2020 |  |  | CHICO | North Valley Assets | [10 empty] | GC | 1477870.55 | 577870.55 | 900000 | 760015.5 | 0 | 139984.5 | On/Under Budget | 0 | 0 | 7645.4 | -7645.4 | 0 | 248805.8 | 511111.1 | 7744 | Project is not in the WP or in 2020 WP | 0 | 98.6 | -98.6 | 98.6 | -98.6 | 98.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112090 | BR-01-07-W (E) BILLE_REGIS PARB |  | 5786123 | DOCC | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2020 |  |  | CHICO | North Valley Assets | [10 empty] | GC | 1177537.75 | 927537.75 | 250000 | 154373.1 | 0 | 95626.9 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 273378.9 | -119005.8 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112128 | BR-01-04-W (E) W. WAGSTAFF PARB |  | 5786123 | DOCC | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | 2021 |  |  | CHICO | North Valley Assets | [10 empty] | GC | 991895.31 | -1499999.69 | 2491895 | 2004133.5 | 0 | 487761.5 | On/Under Budget | 0 | 0 | -1811.2 | 1811.2 | 0 | 491215.8 | 1503392.7 | 7713.8 | Request 2021 Budget | 0 | 9525 | -9525 | 9525 | -9525 | 230.6 | 11122.3 | -1827.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | E.5015687.03 | 5785646 | DOCC | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 13228 | 13228 | 2.5053 | 2.5053 | 0 | 11193 | 13572 | 2.1199 | 2.5705 | Contract | 5345911 | 1865381.3 | 3480529.7 | 3208420.5 | 0 | 272109.2 | On/Under Budget | 73976 | 0 | -1030.8 | 1030.8 | 0 | 14247 | 3191259.9 | 1882.9 | Project is not in the WP or in 2020 WP | 75000 | 76889.7 | -1889.7 | 76889.7 | -1889.7 | 5734.7 | -4711.5 | 1890.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 151661 | BL-2 | BL-2 35112432_CWSP - El Dorado 2102 - LR 19562 - Ph 1.2_08W - Nov. 2020 | 2020-11-24 | 2019-11-13 | Completed | 2020-03-06 | 2020-03-26 | Completed | 2020-03-02 | Completed | 2020-03-26 | Completed | 2020-03-06 | 2020-03-06 | Completed | 2020-04-03 | 2020-04-09 | Completed | 2020-04-13 | 2020-07-14 | Completed | 2020-05-08 | Completed |  |  |  |  | 2020-05-08 | Completed | 2020-11-18 | Completed | 2020-11-18 | Completed | 2020-11-18 | 2020-11-18 | 0 | On/ Ahead Schedule | Completed | 2020-11-20 | 2020-12-04 | Completed | 2021-05-24 | Not Started
35180088 | BUCOCAMPTUG 5507 ROCKFORD LN PARADISE |  | 5791246 | DOCC | 08W | J4VB | Jorge Vargas | Fire Rebuild | Fire Rebuild | Fire Rebuild | Fire Rebuild | Not in the WP |  |  | CHICO | [26 empty] | 19044.7 | Project is not in the WP or in 2020 WP | 0 | 19044.7 | -19044.7 | 0 | 0
35181319 | BUCOCAMPTUG STINSON LN PARADISE |  | 5791246 | DOCC | 08W | J4VB | Jorge Vargas | Fire Rebuild | Fire Rebuild | Fire Rebuild | Fire Rebuild | Not in the WP |  |  | CHICO | [26 empty] | 90750.2 | Project is not in the WP or in 2020 WP | 0 | 90750.2 | -90750.2 | 0 | 0
35145005 | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 |  | 5788785 | DOCC | 08W | GAE9 | Glenn Esguerra |  |  |  |  | Not in the WP |  |  | SNRAFAEL |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 384.5 | Project is not in the WP or in 2020 WP | 0 | 2897784.7 | -2897784.7 | 0 | 0
74022663 | CAMP FIRE RECOND LINE HONEY RN BUTTE 05 |  | 5783324 | DOCC | 08W | JXF8 | Joseph Fong |  |  |  |  | Not in the WP |  |  | CHICO | [26 empty] | -246.2 | Project is not in the WP or in 2020 WP | 0 | -246.2 | 246.2 | 0 | 0
74022721 | CWSP - CAMP FIRE PADSE 1106 BILLIE RD |  | 5783283 | DOCC | 08W | JXF8 | Joseph Fong |  |  |  |  | Not in the WP |  |  | CHICO | [26 empty] | 716.8 | Project is not in the WP or in 2020 WP | 0 | 716.8 | -716.8 | 0 | 0
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | E.5019956.01 | 5743253 | DOCC | 08W | J7LE | Jared Warren Lee | ACN3 | Austin Nordman |  |  | Not in the WP | 2019 | SH | NAPA | North Bay Assets | 0 | 13780 | 13780 | 2.6098 | 2.6098 | 0 | [5 empty] | 1714904 | 1714904 | 0 | 3307157.8 | 0 | -3307157.8 | OverRun | 0 | 0 | 0 | 0 | 0 | 3260744.3 | 44554.5 | 1859 | Project is not in the WP or in 2020 WP | 0 | 1859 | -1859 | 1859 | -1859 | 1845 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2019-06-10 | Completed | 2019-08-13 | 2019-08-14 | Completed | 2019-08-23 | Completed | 2019-08-14 | Completed | 2019-08-15 | 2019-08-15 | Completed | 2019-08-21 | 2019-08-21 | Completed | 2019-08-20 | 2019-08-20 | Completed | 2019-09-03 | Completed |  |  |  |  | 2019-09-03 | Completed |  |  | 2020-05-13 | Completed | 2020-06-02 | 2020-05-13 | 20 | On/ Ahead Schedule | Completed | 2021-04-02 | 2021-04-02 | Not Started | 2021-05-03 | Not Started
74021964 | X-1104 OH RECOND SKYLINE |  | 5513339 | DOCC | 08W | MYL5 | Michael Y. Lee |  |  |  |  | Not in the WP |  |  | OAKPORT | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | E.5015036.01 | 5782835 | DOCC | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2019 | SH | GRSSVLLY | Sierra Assets | 0 | 25191 | 25191 | 4.771 | 4.771 | 0 | [5 empty] | 12463097 | 0 | 12463097 | 12434525.6 | 0 | 28571.4 | On/Under Budget | 0 | 0 | 0 | 0 | 371758.4 | 11704542.1 | 353934.4 | 4290.7 | Project is not in the WP or in 2020 WP | 0 | 4290.7 | -4290.7 | 4290.7 | -4290.7 | 961.5 | 3329.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2019-06-12 | Completed | 2019-01-11 | 2019-02-08 | Completed | 2019-04-29 | Completed | 2019-06-12 | Completed | 2019-06-14 | 2019-06-14 | Completed | 2019-04-29 | 2019-04-29 | Completed | 2019-05-06 | 2019-05-06 | Completed | 2019-05-06 | Completed |  |  |  |  | 2019-05-06 | Completed | 2019-07-19 | Completed | 2019-07-19 | Completed | 2019-07-19 | 2019-07-19 | 0 | On/ Ahead Schedule | Completed | 2019-07-01 | 2019-07-05 | Completed | 2021-06-30 | Not Started
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | E.5015470.01 | 5782834 | DOCC | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2019 | SH | GRSSVLLY | Sierra Assets | 0 | 31023 | 31023 | 5.8756 | 5.8756 | 0 | [5 empty] | 15621955 | 0 | 15621955 | 15475726.8 | 19212.8 | 165441 | On/Under Budget | 0 | 0 | 0 | 0 | 625617.3 | 15246154.8 | -397988 | 1942.7 | Project is not in the WP or in 2020 WP | 0 | 1942.7 | -1942.7 | 1942.7 | -1942.7 | 147.4 | 1795.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2019-06-11 | Completed | 2019-01-11 | 2019-02-08 | Completed | 2019-03-15 | Completed | 2019-03-15 | Completed | 2019-03-01 | 2019-03-04 | Completed | 2019-03-05 | 2019-03-06 | Completed | 2019-01-25 | 2019-01-25 | Completed | 2019-01-25 | Completed |  |  |  |  | 2019-01-21 | Completed | 2019-06-10 | Completed | 2019-06-21 | Completed | 2019-07-24 | 2019-06-21 | 33 | On/ Ahead Schedule | Completed | 2019-06-28 | 2021-04-02 | In Progress | 2021-05-03 | Not Started
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | E.5014743.01 | 5782833 | DOCC | 08W | HXJI | Haridayal Jaswal | SHMG | Safeer Mirza |  |  | Not in the WP | 2019 | SH | STROSA | Sonoma Assets | 0 | 25170 | 25170 | 4.767 | 4.767 | 0 | [5 empty] | 6996439 | 0 | 6996439 | 20417043.3 | 735205.6 | -12685398.7 | OverRun | 6135.9 | 3068 | -2480.5 | 5548.5 | 525900.5 | 21564746 | -1430401.1 | -245682.6 | Project is not in the WP or in 2020 WP | 0 | -233998.1 | 233998.1 | -233998.1 | 233998.1 | 1093.8 | -261851.4 | 17555.5 | 3068 | 3068 | 3068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-01 |  |  |  |  | 2019-05-06 | Completed | 2019-01-11 | 2019-02-08 | Completed | 2019-02-06 | Completed | 2019-04-10 | Completed | 2019-04-01 | 2019-04-01 | Completed | 2019-04-01 | 2019-04-11 | Completed | 2019-04-11 | 2019-12-06 | Completed | 2019-04-11 | Completed |  |  |  |  | 2019-04-11 | Completed | 2019-10-07 | Completed | 2019-10-07 | Completed | 2021-01-22 | 2019-10-07 | 473 | On/ Ahead Schedule | Completed | 2019-10-08 | 2019-10-22 | Completed | 2021-06-07 | Not Started
35228449 | RIO DELL STORM REBUILD |  | 5795392 | DOCC | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 |  | SH - Wind | FORTUNA | Humboldt Division Assets | 0 | 15048 | 15048 | 2.85 | 2.8061 | 0.043939 |  |  |  |  | Contract | 6518166 | 0 | 6518166 | 2181345.4 | 127108.9 | 4463929.5 | On/Under Budget | 935030.3 | 6622.1 | -26034.5 | 32656.6 | 0 | 0 | 0 | 2155310.9 | Request 2021 Budget | 0 | 3122997.9 | -3122997.9 | 3122997.9 | -3122997.9 | 7814.2 | 871179.4 | 1302351.8 | 6622.1 | 6622.1 | 6622.1 | 6791.3 | 867240.5 | 11938.6 | 11938.6 | 11938.6 | 11938.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-02-01 | Completed | 2021-02-15 | 2021-02-19 | Completed | 2021-02-05 | Completed | 2021-02-19 | Completed | 2021-02-01 | 2021-03-02 | Completed | 2021-02-01 | 2021-02-05 | Completed | 2021-02-01 | 2021-02-05 | Completed | 2021-02-08 | Completed | 2021-03-01 | Completed | 2021-03-01 | Completed | 2021-02-08 | Completed | 2021-03-01 | Completed | 2021-03-01 | Completed | 2021-05-05 | 2021-03-01 | 65 | On/ Ahead Schedule | Completed | 2021-04-16 | 2021-04-29 | Not Started | 2021-06-07 | Not Started
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | E.5034610.01.16 | 5794205 | ESTS | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 3326 | 3326 | 0.62992 | 0 | 0.62992 |  |  |  |  | GC | 1 | 1 | 0 | 799.3 | 0 | -799.3 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799.3 | Request 2021 Budget | 0 | 799.3 | -799.3 | 799.3 | -799.3 | 0 | 0 | 799.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157824 | BL-A | BL-A 35228187_CWSP - Middletown 1103 - LR 830 PH2.3_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-21 | Not Started | 2021-06-28 | 2021-07-02 | Not Started | 2021-06-25 | Not Started | 2021-07-23 | Not Started | 2021-05-24 | 2021-05-24 | Not Started | 2021-05-25 | 2021-06-14 | Not Started | 2021-06-28 | 2021-07-09 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-30 | Not Started | 2021-08-17 | Not Started | 2021-11-29 | Not Started | 2021-12-28 | Not Started | 2022-02-24 | 2022-02-28 | -4 | Behind Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-04-27 | Not Started
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | E.5034610.01.17 | 5794205 | ESTS | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH - Remote Grid | LAKEPORT | Humboldt Division Assets | 0 | 19694.4 | 19694.4 | 3.73 | 0 | 3.73 |  |  |  |  | GC | 1 | 1 | 0 | 724.6 | 0 | -724.6 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 724.6 | Request 2021 Budget | 0 | 724.6 | -724.6 | 724.6 | -724.6 | 0 | 0 | 724.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157825 | BL-A | BL-A 35228188_CWSP - Middletown 1103 - LR 830 PH2.4_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-31 | Not Started | 2021-07-06 | 2021-07-12 | Not Started | 2021-07-05 | Not Started | 2021-08-02 | Not Started | 2021-06-01 | 2021-06-01 | Not Started | 2021-06-02 | 2021-06-22 | Not Started | 2021-07-06 | 2021-07-19 | Not Started | 2021-08-25 | Not Started | 2021-08-25 | Not Started | 2021-09-07 | Not Started | 2021-08-25 | Not Started | 2021-12-07 | Not Started | 2022-01-05 | Not Started | 2022-02-08 | 2022-03-08 | -28 | Behind Schedule | Not Started | 2022-03-09 | 2022-03-22 | Not Started | 2022-05-05 | Not Started
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | E.5034804.01.13 | 5795299 | ESTS | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2021 | 2021 | SH | PLCRVLLE | Sierra Assets | 0 | 7023 | 7023 | 1.3301 | 0 | 1.3301 | 8783 | 0 | 1.6634 | 0 | GC | 70000 | 0 | 70000 | 7319.5 | 0 | 62680.5 | On/Under Budget | 2587142.1 | 25154.9 | 0 | 25154.9 | 0 | 0 | 0 | 7319.5 | Budget Allocated | 2649841.53 | 2619616.8 | 30224.73 | 2619616.8 | 30224.73 | 0 | 2297 | 5022.5 | 25154.9 | 4969.6 | 4969.6 | 641816 | 641816 | 641816 | 641816 | 4969.6 | 4969.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-04-16 | Not Started | 2021-05-14 | 2021-05-20 | Not Started | 2021-05-13 | Not Started | 2021-06-11 | Not Started | 2021-04-19 | 2021-04-19 | Not Started | 2021-04-20 | 2021-05-10 | Not Started | 2021-05-14 | 2021-05-27 | Not Started | 2021-07-06 | Not Started | 2021-07-06 | Not Started | 2021-07-19 | Not Started | 2021-07-06 | Not Started | 2021-10-18 | Not Started | 2021-11-16 | Not Started | 2022-01-31 | 2022-01-31 | 0 | On/ Ahead Schedule | Not Started | 2022-02-01 | 2022-02-14 | Not Started | 2022-03-30 | Not Started
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | E.5034695.01.02 | 5794546 | ESTS | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | OAKHURST | Yosemite Assets | 0 | 12443 | 12443 | 2.3566 | 0 | 2.3566 |  |  |  |  | Contract | 1 | -274999 | 275000 | 30360.8 | 0 | 244639.2 | On/Under Budget | 1462813.1 | 586783.8 | 8788 | 577995.8 | 0 | 0 | 0 | 39148.7 | Request 2021 Budget | 0 | 2081737.6 | -2081737.6 | 2079957.6 | -2079957.6 | 0 | 691.8 | 29668.9 | 586783.8 | 563719.4 | 281850.2 | 291512.5 | 255439.3 | 54719.6 | 8536.1 | 4690.7 | 2345.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-24 | Not Started | 2021-06-10 | 2021-06-16 | Not Started | 2021-06-09 | Not Started | 2021-07-19 | Not Started | 2021-05-25 | 2021-05-25 | Not Started | 2021-05-26 | 2021-06-15 | Not Started | 2021-06-10 | 2021-06-23 | Not Started | 2021-08-11 | Not Started | 2021-08-11 | Not Started | 2021-08-24 | Not Started | 2021-08-11 | Not Started | 2021-11-23 | Not Started | 2021-12-22 | Not Started | 2022-02-22 | 2022-02-22 | 0 | On/ Ahead Schedule | Not Started | 2022-02-23 | 2022-03-08 | Not Started | 2022-04-21 | Not Started
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | E.5034695.01.03 | 5794546 | ESTS | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | OAKHURST | Yosemite Assets | 0 | 11421 | 11421 | 2.1631 | 0 | 2.1631 | 9130 | 0 | 1.7292 | 0 | Contract | 1 | -249999 | 250000 | 61516.1 | 0 | 188483.9 | On/Under Budget | 1982787.9 | 54715.8 | 557.2 | 54158.6 | 0 | 0 | 0 | 62073.3 | Request 2021 Budget | 0 | 2100799.8 | -2100799.8 | 2099019.8 | -2099019.8 | 0 | 13052.9 | 48463.2 | 54715.8 | 580688.4 | 503170.8 | 374451.4 | 386551.2 | 84328.7 | 47406.7 | 6190.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-28 | Not Started | 2021-06-07 | 2021-06-11 | Not Started | 2021-06-04 | Not Started | 2021-07-23 | Not Started | 2021-05-31 | 2021-05-31 | Not Started | 2021-06-01 | 2021-06-21 | Not Started | 2021-06-07 | 2021-06-18 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-30 | Not Started | 2021-08-17 | Not Started | 2021-11-29 | Not Started | 2021-12-28 | Not Started | 2022-02-28 | 2022-02-28 | 0 | On/ Ahead Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-04-27 | Not Started
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | E.5034610.01.07 | 5794205 | ESTS | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 1056 | 1056 | 0.2 | 0 | 0.2 |  |  |  |  | GC | 1 | 1 | 0 | 724.6 | 0 | -724.6 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 724.6 | Request 2021 Budget | 0 | 724.6 | -724.6 | 724.6 | -724.6 | 0 | 0 | 724.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157817 | BL-A | BL-A 35227860_CWSP - Middletown 1103 - LR 830 PH1.2_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-21 | Not Started | 2021-06-28 | 2021-07-02 | Not Started | 2021-06-25 | Not Started | 2021-07-23 | Not Started | 2021-05-24 | 2021-05-24 | Not Started | 2021-05-25 | 2021-06-14 | Not Started | 2021-06-28 | 2021-07-09 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-30 | Not Started | 2021-08-17 | Not Started | 2021-11-29 | Not Started | 2021-12-28 | Not Started | 2022-02-24 | 2022-02-28 | -4 | Behind Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-04-27 | Not Started
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | E.5034610.01.08 | 5794205 | ESTS | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 8026 | 8026 | 1.5201 | 0 | 1.5201 |  |  |  |  | GC | 1 | 1 | 0 | 724.6 | 0 | -724.6 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 724.6 | Request 2021 Budget | 0 | 724.6 | -724.6 | 724.6 | -724.6 | 0 | 0 | 724.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157818 | BL-A | BL-A 35227861_CWSP - Middletown 1103 - LR 830 PH1.3_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-24 | Not Started | 2021-06-29 | 2021-07-05 | Not Started | 2021-06-28 | Not Started | 2021-07-26 | Not Started | 2021-05-25 | 2021-05-25 | Not Started | 2021-05-26 | 2021-06-15 | Not Started | 2021-06-29 | 2021-07-12 | Not Started | 2021-08-18 | Not Started | 2021-08-18 | Not Started | 2021-08-31 | Not Started | 2021-08-18 | Not Started | 2021-11-30 | Not Started | 2021-12-29 | Not Started | 2022-02-24 | 2022-03-01 | -5 | Behind Schedule | Not Started | 2022-03-02 | 2022-03-15 | Not Started | 2022-04-28 | Not Started
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | E.5034610.01.09 | 5794205 | ESTS | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 5755 | 5755 | 1.09 | 0 | 1.09 |  |  |  |  | GC | 1 | 1 | 0 | 799.3 | 0 | -799.3 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799.3 | Request 2021 Budget | 0 | 799.3 | -799.3 | 799.3 | -799.3 | 0 | 0 | 799.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157819 | BL-A | BL-A 35227862_CWSP - Middletown 1103 - LR 830 PH1.4_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-21 | Not Started | 2021-06-28 | 2021-07-02 | Not Started | 2021-06-25 | Not Started | 2021-07-23 | Not Started | 2021-05-24 | 2021-05-24 | Not Started | 2021-05-25 | 2021-06-14 | Not Started | 2021-06-28 | 2021-07-09 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-30 | Not Started | 2021-08-17 | Not Started | 2021-11-29 | Not Started | 2021-12-28 | Not Started | 2022-02-24 | 2022-02-28 | -4 | Behind Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-04-27 | Not Started
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | E.5034610.01.10 | 5794205 | ESTS | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 4171 | 4171 | 0.78996 | 0 | 0.78996 |  |  |  |  | GC | 1 | 1 | 0 | 799.3 | 0 | -799.3 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799.3 | Request 2021 Budget | 0 | 799.3 | -799.3 | 799.3 | -799.3 | 0 | 0 | 799.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157821 | BL-A | BL-A 35227863_CWSP - Middletown 1103 - LR 830 PH1.5_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-21 | Not Started | 2021-06-28 | 2021-07-02 | Not Started | 2021-06-25 | Not Started | 2021-07-23 | Not Started | 2021-05-24 | 2021-05-24 | Not Started | 2021-05-25 | 2021-06-14 | Not Started | 2021-06-28 | 2021-07-09 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-30 | Not Started | 2021-08-17 | Not Started | 2021-11-29 | Not Started | 2021-12-28 | Not Started | 2022-02-24 | 2022-02-28 | -4 | Behind Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-04-27 | Not Started
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | E.5034610.01.12 | 5794205 | ESTS | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 2746 | 2746 | 0.52008 | 0 | 0.52008 |  |  |  |  | GC | 1 | 1 | 0 | 724.6 | 0 | -724.6 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 724.6 | Request 2021 Budget | 0 | 724.6 | -724.6 | 724.6 | -724.6 | 0 | 0 | 724.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157820 | BL-A | BL-A 35227866_CWSP - Middletown 1103 - LR 830 PH1.7_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-21 | Not Started | 2021-06-28 | 2021-07-02 | Not Started | 2021-06-25 | Not Started | 2021-07-23 | Not Started | 2021-05-24 | 2021-05-24 | Not Started | 2021-05-25 | 2021-06-14 | Not Started | 2021-06-28 | 2021-07-09 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-30 | Not Started | 2021-08-17 | Not Started | 2021-11-29 | Not Started | 2021-12-28 | Not Started | 2022-02-24 | 2022-02-28 | -4 | Behind Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-04-27 | Not Started
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | E.5034610.01.13 | 5794205 | ESTS | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 5174 | 5174 | 0.97992 | 0 | 0.97992 |  |  |  |  | GC | 1 | 1 | 0 | 775.1 | 0 | -775.1 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 775.1 | Request 2021 Budget | 0 | 775.1 | -775.1 | 775.1 | -775.1 | 0 | 8597.2 | -7822.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157822 | BL-A | BL-A 35227867_CWSP - Middletown 1103 - LR 830 PH1.8_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-21 | Not Started | 2021-06-28 | 2021-07-02 | Not Started | 2021-06-25 | Not Started | 2021-07-23 | Not Started | 2021-05-24 | 2021-05-24 | Not Started | 2021-05-25 | 2021-06-14 | Not Started | 2021-06-28 | 2021-07-09 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-30 | Not Started | 2021-08-17 | Not Started | 2021-11-29 | Not Started | 2021-12-28 | Not Started | 2022-02-24 | 2022-02-28 | -4 | Behind Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-04-27 | Not Started
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | E.5034805.01.27 | 5795300 | ESTS | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 3168 | 3168 | 0.6 | 0 | 0.6 |  |  |  |  | GC | 1 | 1 | 0 | 848.7 | 0 | -848.7 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 848.7 | Request 2021 Budget | 0 | 848.7 | -848.7 | 848.7 | -848.7 | 0 | 0 | 848.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157833 | BL-A | BL-A 35227028_ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-24 | Not Started | 2021-06-29 | 2021-07-05 | Not Started | 2021-06-28 | Not Started | 2021-07-26 | Not Started | 2021-05-25 | 2021-05-25 | Not Started | 2021-05-26 | 2021-06-15 | Not Started | 2021-06-29 | 2021-07-12 | Not Started | 2021-08-18 | Not Started | 2021-08-18 | Not Started | 2021-08-31 | Not Started | 2021-08-18 | Not Started | 2021-11-30 | Not Started | 2021-12-29 | Not Started | 2022-02-24 | 2022-03-01 | -5 | Behind Schedule | Not Started | 2022-03-02 | 2022-03-15 | Not Started | 2022-04-28 | Not Started
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | E.5034805.01.28 | 5795300 | ESTS | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 5491 | 5491 | 1.04 | 0 | 1.04 |  |  |  |  | GC | 1 | 1 | 0 | 774 | 0 | -774 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 774 | Request 2021 Budget | 0 | 774 | -774 | 774 | -774 | 0 | 0 | 774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157834 | BL-A | BL-A 35227029_ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-07 | Not Started | 2021-05-31 | 2021-06-04 | Not Started | 2021-05-28 | Not Started | 2021-07-02 | Not Started | 2021-05-10 | 2021-05-10 | Not Started | 2021-05-11 | 2021-05-31 | Not Started | 2021-05-31 | 2021-06-11 | Not Started | 2021-07-27 | Not Started | 2021-07-27 | Not Started | 2021-08-09 | Not Started | 2021-07-27 | Not Started | 2021-11-08 | Not Started | 2021-12-07 | Not Started | 2022-02-10 | 2022-02-07 | 3 | On/ Ahead Schedule | Not Started | 2022-02-08 | 2022-02-21 | Not Started | 2022-04-06 | Not Started
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | ESTS | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2022 | SH | REDDING | North Valley Assets | 0 | 1531.2 | 1531.2 | 0.29 | 0 | 0.29 |  |  |  |  | GC | 150000 | 0 | 150000 | 25647.8 | 0 | 124352.2 | On/Under Budget | 0 | 0 | -24570 | 24570 | 0 | 0 | 0 | 1077.8 | Budget Allocated | 551000 | 576647.8 | -25647.8 | 25647.8 | 525352.2 | 0 | 0 | 25647.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158023 | BL_A- | BL_A-35226627_SH - KESWICK 1101 LR 1586 PH 1.2_08W_Mar.2021 | 2021-03-26 | 2021-07-12 | Not Started | 2021-08-17 | 2021-08-23 | Not Started | 2021-08-16 | Not Started | 2021-09-13 | Not Started | 2021-07-13 | 2021-07-13 | Not Started | 2021-07-14 | 2021-08-03 | Not Started | 2021-08-17 | 2021-08-30 | Not Started | 2021-10-06 | Not Started | 2021-10-06 | Not Started | 2021-10-19 | Not Started | 2021-10-06 | Not Started | 2021-11-30 | Not Started | 2021-12-15 | Not Started | 2021-12-30 | 2022-01-26 | -27 | Behind Schedule | Not Started | 2022-01-27 | 2022-02-09 | Not Started | 2022-03-25 | Not Started
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | E.5034806.01.01 | 5795301 | ESTS | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 |  | SH | NAPA | North Bay Assets | 0 | 4600 | 4600 | 0.87121 | 0 | 0.87121 |  |  |  |  | Contract | 237833 | 0 | 237833 | 1338.7 | 0 | 236494.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1338.7 | Request 2021 Budget | 0 | 1338.7 | -1338.7 | 1338.7 | -1338.7 | 0 | 343.4 | 995.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-07-01 | Not Started | 2021-12-21 | 2021-12-27 | Not Started | 2021-12-20 | Not Started | 2022-01-17 | Not Started | 2021-07-02 | 2021-12-20 | Not Started | 2021-12-21 | 2022-01-10 | Not Started | 2021-12-21 | 2022-01-03 | Not Started | 2022-02-04 | Not Started | 2022-02-04 | Not Started | 2022-02-17 | Not Started | 2022-02-04 | Not Started | 2022-02-28 | Not Started | 2022-03-29 | Not Started | 2022-05-30 | 2022-05-30 | 0 | On/ Ahead Schedule | Not Started | 2022-05-31 | 2022-06-13 | Not Started | 2022-07-27 | Not Started
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | E.5034804.01.09 | 5795299 | ESTS | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2021 | 2021 | SH | PLCRVLLE | Sierra Assets | 0 | 5438.4 | 5438.4 | 1.03 | 0 | 1.03 |  |  |  |  | GC | 70000 | 0 | 70000 | 99989.6 | 0 | -29989.6 | OverRun | 2014888.7 | 24763.6 | 0 | 24763.6 | 0 | 0 | 0 | 99989.5 | Budget Allocated | 2086816.03 | 2142311.9 | -55495.87 | 2139641.9 | -52825.87 | 0 | 22400.2 | 77589.3 | 24763.6 | 4969.6 | 4969.6 | 498752.6 | 498752.6 | 498752.6 | 498752.6 | 4969.6 | 4969.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-04-16 | Not Started | 2021-05-19 | 2021-05-25 | Not Started | 2021-05-18 | Not Started | 2021-06-15 | Not Started | 2021-04-19 | 2021-04-19 | Not Started | 2021-04-20 | 2021-05-10 | Not Started | 2021-05-19 | 2021-06-01 | Not Started | 2021-07-08 | Not Started | 2021-07-08 | Not Started | 2021-07-21 | Not Started | 2021-07-08 | Not Started | 2021-10-20 | Not Started | 2021-11-18 | Not Started | 2022-01-19 | 2022-01-19 | 0 | On/ Ahead Schedule | Not Started | 2022-01-20 | 2022-02-02 | Not Started | 2022-03-18 | Not Started
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | E.5034804.01.10 | 5795299 | ESTS | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2021 | 2021 | SH | PLCRVLLE | Sierra Assets | 0 | 10262 | 10262 | 1.9436 | 0 | 1.9436 |  |  |  |  | GC | 70000 | 0 | 70000 | 19815.7 | 0 | 50184.3 | On/Under Budget | 8726503 | 66102 | 0 | 66102 | 0 | 0 | 0 | 19815.7 | Budget Allocated | 8862572.16 | 8815090.5 | 47481.66 | 8812420.5 | 50151.66 | 0 | 3865.2 | 15950.5 | 66102 | 4969.6 | 4969.6 | 1452760.6 | 1452760.6 | 1452760.6 | 1452760.6 | 1452760.6 | 1452760.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-04-16 | Not Started | 2021-05-18 | 2021-05-24 | Not Started | 2021-05-17 | Not Started | 2021-06-14 | Not Started | 2021-04-19 | 2021-04-19 | Not Started | 2021-04-20 | 2021-05-10 | Not Started | 2021-05-18 | 2021-05-31 | Not Started | 2021-07-07 | Not Started | 2021-07-07 | Not Started | 2021-07-20 | Not Started | 2021-07-07 | Not Started | 2021-10-19 | Not Started | 2021-11-17 | Not Started | 2022-01-18 | 2022-01-18 | 0 | On/ Ahead Schedule | Not Started | 2022-01-19 | 2022-02-01 | Not Started | 2022-03-17 | Not Started
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | E.5034825.01.17 | 5795419 | ESTS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 766 | 0 | 766 | 0.14508 | 0 | 0.14508 |  |  |  |  | GC | 2743520 | 1450230 | 1293290 | 344.2 | 0 | 1292945.8 | On/Under Budget | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 344.2 | Budget Allocated | 500000 | 525344.2 | -25344.2 | 500344.2 | -344.2 | 0 | 0 | 344.2 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158199 | BL-A | BL-A 35233310_FRRB - WYANDOTTE 1103 - W1 PH 1.14 - Mar. 2021 | 2021-03-31 | 2021-04-23 | Not Started | 2021-03-18 | 2021-03-22 | Completed | 2021-04-26 | Not Started | 2021-04-26 | Not Started | [6 empty] | 2021-04-13 | 2021-04-19 | Not Started | 2021-04-28 | Not Started | 2021-04-28 | Not Started | 2021-07-14 | Not Started | 2021-05-12 | Not Started | 2021-07-28 | Not Started | 2021-07-28 | Not Started | 2021-08-27 | 2021-08-27 | 0 | On/ Ahead Schedule | Not Started | 2021-08-27 | 2021-09-10 | Not Started | 2021-10-26 | Not Started
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | E.5034825.01.13 | 5795419 | ESTS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 1376 | 0 | 1376 | 0.26061 | 0 | 0.26061 |  |  |  |  | GC | 3246777 | 1566366 | 1680411 | 229.1 | 0 | 1680181.9 | On/Under Budget | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 229.1 | Budget Allocated | 500000 | 912350.1 | -412350.1 | 500229.1 | -229.1 | 0 | 0 | 229.1 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158203 | BL-A | BL-A 35233306_FRRB - WYANDOTTE 1103 - W1 PH 1.10 - Mar. 2021 | 2021-03-31 | 2021-04-23 | Not Started | 2021-03-18 | 2021-03-22 | Completed | 2021-04-26 | Not Started | 2021-04-26 | Not Started | [6 empty] | 2021-04-13 | 2021-04-19 | Not Started | 2021-04-28 | Not Started | 2021-04-28 | Not Started | 2021-07-14 | Not Started | 2021-05-12 | Not Started | 2021-07-28 | Not Started | 2021-07-28 | Not Started | 2021-08-27 | 2021-08-27 | 0 | On/ Ahead Schedule | Not Started | 2021-08-27 | 2021-09-10 | Not Started | 2021-10-26 | Not Started
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | E.5034825.01.14 | 5795419 | ESTS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 3153 | 0 | 3153 | 0.59716 | 0 | 0.59716 | 2254 | 0 | 0.42689 | 0 | GC | 4778094 | 1919747 | 2858347 | 229.1 | 0 | 2858117.9 | On/Under Budget | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 229.1 | Budget Allocated | 2090056.82 | 2090286.1 | -229.28 | 500229.1 | 1589827.72 | 0 | 0 | 229.1 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158202 | BL-A | BL-A 35233307_FRRB - WYANDOTTE 1103 - W1 PH 1.11 - Mar. 2021 | 2021-03-31 | 2021-04-23 | Not Started | 2021-03-18 | 2021-03-22 | Completed | 2021-04-26 | Not Started | 2021-04-26 | Not Started | [6 empty] | 2021-04-13 | 2021-04-19 | Not Started | 2021-04-28 | Not Started | 2021-04-28 | Not Started | 2021-07-14 | Not Started | 2021-05-12 | Not Started | 2021-07-28 | Not Started | 2021-07-28 | Not Started | 2021-08-27 | 2021-08-27 | 0 | On/ Ahead Schedule | Not Started | 2021-08-27 | 2021-09-10 | Not Started | 2021-10-26 | Not Started
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | E.5034825.01.15 | 5795419 | ESTS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 4896 | 0 | 4896 | 0.92727 | 0 | 0.92727 |  |  |  |  | GC | 6280110 | 2266366 | 4013744 | 229.1 | 0 | 4013514.9 | On/Under Budget | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 229.1 | Budget Allocated | 1761818.18 | 3245683.1 | -1483864.92 | 500229.1 | 1261589.08 | 0 | 0 | 229.1 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158201 | BL-A | BL-A 35233308_FRRB - WYANDOTTE 1103 - W1 PH 1.12 - Mar. 2021 | 2021-03-31 | 2021-04-23 | Not Started | 2021-03-18 | 2021-03-22 | Completed | 2021-04-26 | Not Started | 2021-04-26 | Not Started | [6 empty] | 2021-04-13 | 2021-04-19 | Not Started | 2021-04-28 | Not Started | 2021-04-28 | Not Started | 2021-07-14 | Not Started | 2021-05-12 | Not Started | 2021-07-28 | Not Started | 2021-07-28 | Not Started | 2021-08-27 | 2021-08-27 | 0 | On/ Ahead Schedule | Not Started | 2021-08-27 | 2021-09-10 | Not Started | 2021-10-26 | Not Started
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | E.5034825.01.07 | 5795419 | ESTS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 1711 | 0 | 1711 | 0.32405 | 0 | 0.32405 |  |  |  |  | GC | 3535462 | 1632986 | 1902476 | 229.1 | 0 | 1902246.9 | On/Under Budget | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 229.1 | Budget Allocated | 1134185.61 | 1134415.1 | -229.49 | 500229.1 | 633956.51 | 0 | 0 | 229.1 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158208 | BL-A | BL-A 35233300_FRRB - WYANDOTTE 1103 - W1 PH 1.4 - Mar. 2021 | 2021-03-31 | 2021-04-23 | Not Started | 2021-03-18 | 2021-03-22 | Completed | 2021-04-26 | Not Started | 2021-04-26 | Not Started | [6 empty] | 2021-04-13 | 2021-04-19 | Not Started | 2021-04-28 | Not Started | 2021-04-28 | Not Started | 2021-07-14 | Not Started | 2021-05-12 | Not Started | 2021-07-28 | Not Started | 2021-07-28 | Not Started | 2021-08-27 | 2021-08-27 | 0 | On/ Ahead Schedule | Not Started | 2021-08-27 | 2021-09-10 | Not Started | 2021-10-26 | Not Started
35233302 | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | E.5034825.01.09 | 5795419 | ESTS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 842 | 0 | 842 | 0.15947 | 0 | 0.15947 | 798 | 0 | 0.15114 | 0 | GC | 147014.36 | -1052809.64 | 1199824 | 0 | 0 | 1199824 | On/Under Budget | 500000 | 0 | 0 | 0 | 0 | 0 | 0 |  | Budget Allocated | 500000 | 431534 | 68466 | 500000 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158206 | BL-A | BL-A 35233302_FRRB - WYANDOTTE 1103 - W1 PH 1.6 - Mar. 2021 | 2021-03-31 | 2021-03-31 | Completed | 2021-03-18 | 2021-03-22 | Completed | 2021-04-26 | Not Started | 2021-04-26 | Not Started | [6 empty] | 2021-04-13 | 2021-04-19 | Not Started | 2021-04-28 | Not Started | 2021-04-28 | Not Started | 2021-07-14 | Not Started | 2021-05-12 | Not Started | 2021-07-28 | Not Started | 2021-07-28 | Not Started | 2021-08-20 | 2021-08-27 | -7 | Behind Schedule | Not Started | 2021-08-27 | 2021-09-10 | Not Started | 2021-10-26 | Not Started
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | E.5034825.01.10 | 5795419 | ESTS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 461 | 0 | 461 | 0.087311 | 0 | 0.087311 |  |  |  |  | GC | 2470520 | 1387230 | 1083290 | 229.1 | 0 | 1083060.9 | On/Under Budget | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 229.1 | Budget Allocated | 500000 | 315229.1 | 184770.9 | 500229.1 | -229.1 | 0 | 0 | 229.1 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158223 | BL-A | BL-A 35233303_FRRB - WYANDOTTE 1103 - W1 PH 1.7 - Mar. 2021 | 2021-03-31 | 2021-04-23 | Not Started | 2021-03-18 | 2021-03-22 | Completed | 2021-04-26 | Not Started | 2021-04-26 | Not Started | [6 empty] | 2021-04-13 | 2021-04-19 | Not Started | 2021-04-28 | Not Started | 2021-04-28 | Not Started | 2021-07-14 | Not Started | 2021-05-12 | Not Started | 2021-07-28 | Not Started | 2021-07-28 | Not Started | 2021-08-27 | 2021-08-27 | 0 | On/ Ahead Schedule | Not Started | 2021-08-27 | 2021-09-10 | Not Started | 2021-10-26 | Not Started
35233304 | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | E.5034825.01.11 | 5795419 | ESTS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 1606 | 0 | 1606 | 0.30417 | 0 | 0.30417 |  |  |  |  | GC | 3444978 | 1612105 | 1832873 | 0 | 0 | 1832873 | On/Under Budget | 500000 | 0 | 0 | 0 | 0 | 0 | 0 |  | Budget Allocated | 1064583.33 | 1064583 | 0.33 | 500000 | 564583.33 | 0 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158205 | BL-A | BL-A 35233304_FRRB - WYANDOTTE 1103 - W1 PH 1.8 - Mar. 2021 | 2021-03-31 | 2021-04-23 | Not Started | 2021-03-18 | 2021-03-22 | Completed | 2021-04-26 | Not Started | 2021-04-26 | Not Started | [6 empty] | 2021-04-13 | 2021-04-19 | Not Started | 2021-04-28 | Not Started | 2021-04-28 | Not Started | 2021-07-14 | Not Started | 2021-05-12 | Not Started | 2021-07-28 | Not Started | 2021-07-28 | Not Started | 2021-08-27 | 2021-08-27 | 0 | On/ Ahead Schedule | Not Started | 2021-08-27 | 2021-09-10 | Not Started | 2021-10-26 | Not Started
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | E.5034825.01.02 | 5795419 | ESTS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 1276 | 0 | 1276 | 0.24167 | 0 | 0.24167 |  |  |  |  | GC | 3159481 | 1545356 | 1614125 | 10032.7 | 0 | 1604092.3 | On/Under Budget | 496252 | 0 | 208.9 | -208.9 | 0 | 0 | 0 | 10241.6 | Budget Allocated | 845833.33 | 852118.7 | -6285.37 | 506284.7 | 339548.63 | 0 | 3749 | 6283.7 | 0 | 100000 | 100000 | 100000 | 100000 | 96252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158211 | BL-A | BL-A 35232298_FRRB - WYANDOTTE 1103 - W1 Ph 1.1 - Mar. 2021 | 2021-03-31 | 2021-04-23 | Not Started | 2021-03-18 | 2021-03-22 | Completed | 2021-04-26 | Not Started | 2021-04-26 | Not Started | [6 empty] | 2021-04-13 | 2021-04-19 | Not Started | 2021-04-28 | Not Started | 2021-04-28 | Not Started | 2021-07-14 | Not Started | 2021-05-12 | Not Started | 2021-07-28 | Not Started | 2021-07-28 | Not Started | 2021-08-27 | 2021-08-27 | 0 | On/ Ahead Schedule | Not Started | 2021-08-27 | 2021-09-10 | Not Started | 2021-10-26 | Not Started
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | E.5034713.01.03 | 5794554 | ESTS | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2021 |  | SH | REDDING | North Valley Assets | 0 | 16251 | 16251 | 3.0778 | 0 | 3.0778 | [5 empty] | 1 | 1 | 0 | 2080.4 | 0 | -2080.4 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2080.4 | Request 2021 Budget | 0 | 2080.4 | -2080.4 | 2080.4 | -2080.4 | 0 | 0 | 2080.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | E.5034713.01.04 | 5794554 | ESTS | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2021 | 2021 | SH | REDDING | North Valley Assets | 0 | 5468 | 5468 | 1.0356 | 0 | 1.0356 | [5 empty] | 1 | 1 | 0 | 2080.4 | 0 | -2080.4 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2080.4 | Request 2021 Budget | 0 | 2080.4 | -2080.4 | 2080.4 | -2080.4 | 0 | 0 | 2080.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-02-01 | 158346 | BL-A_ | BL-A_35232443_CWSP - DESCHUTES 11049718 PH2.3_08W_Apr.2021 | 2021-04-01 | 2021-05-11 | Not Started | 2021-06-16 | 2021-06-22 | Not Started | 2021-06-15 | Not Started | 2021-07-13 | Not Started | 2021-05-12 | 2021-05-12 | Not Started | 2021-05-13 | 2021-06-02 | Not Started | 2021-06-16 | 2021-06-29 | Not Started | 2021-08-05 | Not Started | 2021-08-05 | Not Started | 2021-08-18 | Not Started | 2021-08-05 | Not Started | 2021-11-17 | Not Started | 2021-12-16 | Not Started | 2022-02-16 | 2022-02-16 | 0 | On/ Ahead Schedule | Not Started | 2022-02-17 | 2022-03-02 | Not Started | 2022-04-15 | Not Started
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | E.5034713.01.05 | 5794554 | ESTS | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2021 | 2021 | SH | REDDING | North Valley Assets | 0 | 18648 | 18648 | 3.5318 | 0 | 3.5318 | [5 empty] | 1 | 1 | 0 | 688.5 | 0 | -688.5 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 688.5 | Request 2021 Budget | 0 | 688.5 | -688.5 | 688.5 | -688.5 | 0 | 0 | 688.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-02-01 | 158347 | BL-A_ | BL-A_35232444_CWSP - DESCHUTES 11049718 PH2.4_08W_Apr.2021 | 2021-04-01 | 2021-05-11 | Not Started | 2021-06-16 | 2021-06-22 | Not Started | 2021-06-15 | Not Started | 2021-07-13 | Not Started | 2021-05-12 | 2021-05-12 | Not Started | 2021-05-13 | 2021-06-02 | Not Started | 2021-06-16 | 2021-06-29 | Not Started | 2021-08-05 | Not Started | 2021-08-05 | Not Started | 2021-08-18 | Not Started | 2021-08-05 | Not Started | 2021-11-17 | Not Started | 2021-12-16 | Not Started | 2022-02-16 | 2022-02-16 | 0 | On/ Ahead Schedule | Not Started | 2022-02-17 | 2022-03-02 | Not Started | 2022-04-15 | Not Started
35232445 | CWSP - DESCHUTES 11049718 PH 2.5 |  | 5794554 | ESTS | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2021 | 2021 | SH | REDDING |  | 0 | 13748 | 13748 | 2.6038 | 0 | 2.6038 | [20 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | [25 empty] | 2021-02-01 | 158348 | BL-A_ | BL-A_35232445_CWSP - DESCHUTES 11049718 PH2.5_08W_Apr.2021 | 2021-04-01 | 2021-05-11 | Not Started | 2021-06-16 | 2021-06-22 | Not Started | 2021-06-15 | Not Started | 2021-07-13 | Not Started | 2021-05-12 | 2021-05-12 | Not Started | 2021-05-13 | 2021-06-02 | Not Started | 2021-06-16 | 2021-06-29 | Not Started | 2021-08-05 | Not Started | 2021-08-05 | Not Started | 2021-08-18 | Not Started | 2021-08-05 | Not Started | 2021-11-17 | Not Started | 2021-12-16 | Not Started | 2022-02-16 | 2022-02-16 | 0 | On/ Ahead Schedule | Not Started | 2022-02-17 | 2022-03-02 | Not Started | 2022-04-15 | Not Started
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | E.5034696.01.03 | 5794547 | ESTS | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 3221 | 0 | 3221 | 0.61004 | 0 | 0.61004 |  |  |  |  | GC | 475000 | 0 | 475000 | 22404.2 | 0 | 452595.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22404.2 | Request 2021 Budget | 0 | 22404.2 | -22404.2 | 22404.2 | -22404.2 | 0 | 2465.3 | 19938.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-04-23 | Not Started | 2021-09-16 | 2021-09-22 | Not Started | 2021-09-15 | Not Started | 2021-10-12 | Not Started | 2021-04-26 | 2021-04-26 | Not Started | 2021-04-27 | 2021-05-17 | Not Started | 2021-09-16 | 2021-09-29 | Not Started | 2021-10-15 | Not Started | 2021-10-15 | Not Started | 2021-10-28 | Not Started | 2021-10-15 | Not Started | 2021-11-19 | Not Started | 2021-12-20 | Not Started | 2022-02-18 | 2022-02-18 | 0 | On/ Ahead Schedule | Not Started | 2022-02-21 | 2022-03-04 | Not Started | 2022-04-19 | Not Started
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | E.5034692.01.03 | 5794540 | ESTS | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2021 |  | SH | CONCORD | Diablo Assets | 0 | 6336 | 6336 | 1.2 | 0 | 1.2 |  |  |  |  | GC | 181000 | 0 | 181000 | 1661 | 0 | 179339 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1661.1 | Request 2021 Budget | 0 | 1661.1 | -1661.1 | 1661.1 | -1661.1 | 0 | 462.9 | 1198.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-20 | Not Started | 2021-07-19 | 2021-07-23 | Not Started | 2021-07-16 | Not Started | 2021-08-13 | Not Started | 2021-05-21 | 2021-05-21 | Not Started | 2021-05-24 | 2021-06-11 | Not Started | 2021-06-28 | 2021-07-09 | Not Started | 2021-09-07 | Not Started |  |  |  |  | 2021-09-07 | Not Started | 2021-10-25 | Not Started | 2021-11-23 | Not Started | 2022-01-24 | 2022-01-24 | 0 | On/ Ahead Schedule | Not Started | 2022-01-25 | 2022-02-07 | Not Started | 2022-03-23 | Not Started
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | E.5034804.01.11 | 5795299 | ESTS | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2021 | 2021 | SH | PLCRVLLE | Sierra Assets | 0 | 8691 | 8691 | 1.646 | 0 | 1.646 | 7441 | 0 | 1.4093 | 0 | GC | 70000 | 0 | 70000 | 8123.3 | 0 | 61876.7 | On/Under Budget | 2812757.9 | 21594.7 | 0 | 21594.7 | 0 | 0 | 0 | 8123.3 | Budget Allocated | 2867422.68 | 2842475.6 | 24947.08 | 2842475.6 | 24947.08 | 0 | 1475.3 | 6648 | 21594.7 | 1594.7 | 1594.7 | 701594.7 | 701594.7 | 701594.7 | 701594.7 | 1594.7 | 1594.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-04-30 | Not Started | 2021-06-18 | 2021-06-24 | Not Started | 2021-06-17 | Not Started | 2021-07-15 | Not Started | 2021-05-03 | 2021-05-03 | Not Started | 2021-05-04 | 2021-05-24 | Not Started | 2021-06-18 | 2021-07-01 | Not Started | 2021-08-09 | Not Started | 2021-08-09 | Not Started | 2021-08-20 | Not Started | 2021-08-09 | Not Started | 2021-11-19 | Not Started | 2021-12-20 | Not Started | 2022-01-31 | 2022-01-31 | 0 | On/ Ahead Schedule | Not Started | 2022-02-01 | 2022-02-14 | Not Started | 2022-03-30 | Not Started
35232960 | CWSP - DESCHUTES 11049718 PH1.2 | E.5034713.01.07 | 5794554 | ESTS | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2021 |  | SH | REDDING | North Valley Assets | 0 | 15470 | 15470 | 2.9299 | 0 | 2.9299 | [5 empty] | 1 | 1 | 0 | 149.4 | 0 | -149.4 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149.4 | Request 2021 Budget | 0 | 149.4 | -149.4 | 149.4 | -149.4 | 0 | 0 | 149.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | E.5034825.01.05 | 5795419 | ESTS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 1227 | 0 | 1227 | 0.23239 | 0 | 0.23239 |  |  |  |  | GC | 3118378 | 1536736 | 1581642 | 808.9 | 0 | 1580833.1 | On/Under Budget | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 808.9 | Budget Allocated | 813352.27 | 814160.9 | -808.63 | 500808.9 | 312543.37 | 0 | 0 | 808.9 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158210 | BL-A | BL-A 35233038_FRRB - WYANDOTTE 1103 - W1 PH 1.2 - Mar. 2021 | 2021-03-31 | 2021-04-23 | Not Started | 2021-03-18 | 2021-03-22 | Completed | 2021-04-26 | Not Started | 2021-04-26 | Not Started | [6 empty] | 2021-04-13 | 2021-04-19 | Not Started | 2021-04-28 | Not Started | 2021-04-28 | Not Started | 2021-07-14 | Not Started | 2021-05-12 | Not Started | 2021-07-28 | Not Started | 2021-07-28 | Not Started | 2021-08-27 | 2021-08-27 | 0 | On/ Ahead Schedule | Not Started | 2021-08-27 | 2021-09-10 | Not Started | 2021-10-26 | Not Started
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | E.5034825.01.06 | 5795419 | ESTS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 1936 | 0 | 1936 | 0.36667 | 0 | 0.36667 |  |  |  |  | GC | 3729353 | 1677730 | 2051623 | 229.1 | 0 | 2051393.9 | On/Under Budget | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 229.1 | Budget Allocated | 1283333.33 | 1283562.1 | -228.77 | 500229.1 | 783104.23 | 0 | 0 | 229.1 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158209 | BL-A | BL-A 35233039_FRRB - WYANDOTTE 1103 - W1 PH 1.3 - Mar. 2021 | 2021-03-31 | 2021-04-23 | Not Started | 2021-03-18 | 2021-03-22 | Completed | 2021-04-26 | Not Started | 2021-04-26 | Not Started | [6 empty] | 2021-04-13 | 2021-04-19 | Not Started | 2021-04-28 | Not Started | 2021-04-28 | Not Started | 2021-07-14 | Not Started | 2021-05-12 | Not Started | 2021-07-28 | Not Started | 2021-07-28 | Not Started | 2021-08-27 | 2021-08-27 | 0 | On/ Ahead Schedule | Not Started | 2021-08-27 | 2021-09-10 | Not Started | 2021-10-26 | Not Started
35236662 | CWSP - OLETA 1101754718 PH 1.2 |  | 5794611 | ESTS | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | JACKSON |  | 0 | 8817.6 | 8817.6 | 1.67 | 0 | 1.67 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35238098 | ECOP - SILVERADO 2104 - H05 - LR726 PH 6 |  | 5794998 | ESTS | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | Not in the WP |  | SH | NAPA |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | E.5015549.04 | 5789700 | ESTS | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 6494 | 6494 | 1.2299 | 0 | 1.2299 | [5 empty] | 250000 | 0 | 250000 | 45276.6 | 0 | 204723.4 | On/Under Budget | 2046261.5 | 18.9 | 0 | 18.9 | 0 | 0 | 7182.3 | 38094.3 | Project is not in the WP or in 2020 WP | 0 | 38219.6 | -38219.6 | 38219.6 | -38219.6 | 37473 | 361.5 | 259.8 | 18.9 | 18.9 | 18.9 | 19.6 | 19.6 | 19.6 | 9.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 682051.8 | 682051.8 | 682051.8 | 0 | 0 | 0 | 2046155.4
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 | E.5015549.05 | 5789701 | ESTS | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 6312 | 6312 | 1.1955 | 0 | 1.1955 | [5 empty] | 250000 | 0 | 250000 | 45093.6 | 0 | 204906.4 | On/Under Budget | 2286532.7 | 18.9 | 0 | 18.9 | 0 | 0 | 20744.4 | 24349.2 | Project is not in the WP or in 2020 WP | 0 | 24494.1 | -24494.1 | 24494.1 | -24494.1 | 23832.2 | 258.5 | 258.5 | 18.9 | 18.9 | 18.9 | 19.6 | 19.6 | 19.6 | 19.6 | 9.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 762135.6 | 762135.6 | 762135.6 | 0 | 2286406.8
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | E.5015549.06 | 5789702 | ESTS | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 2376 | 7022 | 9398 | 1.7799 | 0 | 1.7799 | [5 empty] | 250000 | 0 | 250000 | 63888.7 | 0 | 186111.3 | On/Under Budget | 3503943.4 | 20.8 | 0 | 20.8 | 0 | 0 | 7099.3 | 56789.4 | Project is not in the WP or in 2020 WP | 0 | 56949 | -56949 | 56949 | -56949 | 52742.2 | 12991.7 | -8944.5 | 20.8 | 20.8 | 20.8 | 21.6 | 21.6 | 21.6 | 21.6 | 10.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1167934.9 | 1167934.9 | 1167934.9 | 0 | 0 | 3503804.7
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 | E.5015549.07 | 5789703 | ESTS | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 4646 | 686 | 5332 | 1.0098 | 0 | 1.0098 | [5 empty] | 250000 | 0 | 250000 | 71602.1 | 0 | 178397.9 | On/Under Budget | 1918110.8 | 23.2 | 0 | 23.2 | 0 | 0 | 8631.3 | 62970.7 | Project is not in the WP or in 2020 WP | 0 | 63148.7 | -63148.7 | 63148.7 | -63148.7 | 58733.1 | 13035.4 | -8797.8 | 23.2 | 23.2 | 23.2 | 24.1 | 24.1 | 24.1 | 24.1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 639318.7 | 639318.7 | 639318.7 | 0 | 0 | 0 | 1917956.1
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 | 5539442 | ESTS | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | AUBURN | Sierra Assets | 0 | 5000 | 5000 | 0.94697 | 0 | 0.94697 | [5 empty] | 166667 | 0 | 166667 | 22851.4 | 0 | 143815.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 214.6 | 22636.8 | Project is not in the WP or in 2020 WP | 0 | 22636.8 | -22636.8 | 22636.8 | -22636.8 | 37622.5 | -14985.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 154999 | BL-A | BL-A 35167136_CWSP - PLACERVILLE 2106 LR1104 PH 1.2_08W - Jan. 2021 | 2021-01-25 | 2022-03-28 | Not Started | 2022-03-29 | 2022-04-04 | Not Started | 2022-02-24 | Not Started | 2022-05-23 | Not Started | 2022-03-29 | 2022-03-29 | Not Started | 2022-03-30 | 2022-04-19 | Not Started | 2022-02-25 | 2022-03-10 | Not Started | 2022-05-25 | Not Started |  |  |  |  | 2022-05-25 | Not Started | 2022-09-06 | Not Started | 2022-10-05 | Not Started | 2022-12-06 | 2022-12-06 | 0 | On/ Ahead Schedule | Not Started | 2022-12-07 | 2022-12-20 | Not Started | 2023-01-26 | Not Started
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 | 5790011 | ESTS | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | AUBURN | Sierra Assets | 0 | 10745 | 10745 | 2.035 | 0 | 2.035 | [5 empty] | 166667 | 0 | 166667 | 27131.3 | 0 | 139535.7 | On/Under Budget | 14 | 2.5 | 0 | 2.5 | 0 | 0 | 608.9 | 26522.4 | Project is not in the WP or in 2020 WP | 0 | 26539 | -26539 | 26539 | -26539 | 46799 | -20431.7 | 155.1 | 2.5 | 2.5 | 2.5 | 2.6 | 2.6 | 2.6 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2022-01-20 | Not Started | 2022-04-26 | 2022-05-02 | Not Started | 2022-04-25 | Not Started | 2022-05-23 | Not Started | 2022-01-21 | 2022-01-21 | Not Started | 2022-01-24 | 2022-02-11 | Not Started | 2022-04-26 | 2022-05-09 | Not Started | 2022-06-22 | Not Started |  |  |  |  | 2022-06-22 | Not Started | 2022-10-04 | Not Started | 2022-11-02 | Not Started | 2023-01-03 | 2023-01-03 | 0 | On/ Ahead Schedule | Not Started | 2023-01-04 | 2023-01-17 | Not Started | 2023-02-23 | Not Started
35168820 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.4 |  | 5539424 | ESTS | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 23137.2 | Project is not in the WP or in 2020 WP | 0 | 23137.2 | -23137.2 | 0 | 0
35168821 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.5 |  | 5539425 | ESTS | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 9852.6 | Project is not in the WP or in 2020 WP | 0 | 9852.6 | -9852.6 | 0 | 0
35168822 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.6 |  | 5539426 | ESTS | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 6556.6 | Project is not in the WP or in 2020 WP | 0 | 6556.6 | -6556.6 | 0 | 0
35168823 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.7 |  | 5539427 | ESTS | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 4221.5 | Project is not in the WP or in 2020 WP | 0 | 4221.5 | -4221.5 | 0 | 0
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 | E.5014755.07 | 5790364 | ESTS | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 |  | CHICO | North Valley Assets | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 271429 | 0 | 271429 | 15440.2 | 0 | 255988.8 | On/Under Budget | 70300.1 | 209.6 | 0 | 209.6 | 0 | 0 | 11904.1 | 3536.1 | Project is not in the WP or in 2020 WP | 0 | 5468.1 | -5468.1 | 5468.1 | -5468.1 | 72839.3 | -69418 | 114.8 | 209.6 | 209.6 | 209.6 | 217.2 | 217.2 | 217.2 | 217.2 | 217.2 | 217.2 | 225.2 | 225.2 | 225.2 | 225.2 | 225.2 | 60408.8 | 601.8 | 601.8 | 601.8 | 601.8 | 601.8 | 601.8 | 65145.6 | 2021-04-02 | 155003 | BL-A | BL-A 35170202_CWSP - ORO FINO-1101 - LR-2022 PH 2.7_08W - Jan. 2021 | 2021-01-25 | 2022-04-21 | Not Started | 2022-04-25 | 2022-05-06 | Not Started | 2022-06-23 | Not Started | 2022-06-24 | Not Started | 2022-05-09 | 2022-05-09 | Not Started | 2022-05-10 | 2022-05-30 | Not Started | 2022-04-22 | 2022-05-05 | Not Started | 2022-08-01 | Not Started |  |  |  |  | 2022-08-01 | Not Started | 2023-01-06 | Not Started | 2023-02-06 | Not Started | 2022-12-26 | 2023-03-06 | -70 | Behind Schedule | Not Started | 2023-03-07 | 2023-03-20 | Not Started | 2023-04-26 | Not Started
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 | E.5015549.09 | 5789705 | ESTS | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 5500 | 5500 | 1.0417 | 0 | 1.0417 | [5 empty] | 250000 | 0 | 250000 | 59389.2 | 0 | 190610.8 | On/Under Budget | 1778573.1 | 23.6 | 0 | 23.6 | 0 | 0 | 7499.3 | 51890 | Project is not in the WP or in 2020 WP | 0 | 52071 | -52071 | 52071 | -52071 | 49309.5 | 12974.1 | -10393.6 | 23.6 | 23.6 | 23.6 | 24.5 | 24.5 | 24.5 | 24.5 | 12.2 | 0 | 0 | 0 | 0 | 0 | 0 | 592805.2 | 592805.2 | 592805.2 | 0 | 0 | 0 | 0 | 1778415.6
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 | E.5015550.02 | 5789706 | ESTS | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2023 | SH | GRSSVLLY | Sierra Assets | 1750 | 6415 | 8165 | 1.5464 | 0 | 1.5464 | [5 empty] | 71428 | 0 | 71428 | 34411.6 | 0 | 37016.4 | On/Under Budget | 129.3 | 16.8 | 0 | 16.8 | 0 | 0 | 4196.4 | 30215.1 | Project is not in the WP or in 2020 WP | 0 | 30361.2 | -30361.2 | 30361.2 | -30361.2 | 25.6 | 24.4 | 30165.1 | 16.8 | 16.8 | 16.8 | 17.4 | 17.4 | 17.4 | 17.4 | 17.4 | 8.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2023-01-02 | Not Started | 2023-02-14 | 2023-02-20 | Not Started | 2023-02-13 | Not Started | 2023-03-13 | Not Started | 2023-01-03 | 2023-01-03 | Not Started | 2023-01-04 | 2023-01-24 | Not Started | 2023-02-14 | 2023-02-27 | Not Started | 2023-04-05 | Not Started |  |  |  |  | 2023-04-05 | Not Started | 2023-07-18 | Not Started | 2023-08-16 | Not Started | 2023-10-17 | 2023-10-17 | 0 | On/ Ahead Schedule | Not Started | 2023-10-18 | 2023-10-31 | Not Started | 2023-12-07 | Not Started
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 | E.5015550.03 | 5789707 | ESTS | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2023 | SH | GRSSVLLY | Sierra Assets | 5400 | 2440 | 7840 | 1.4848 | 0 | 1.4848 | [5 empty] | 71428 | 0 | 71428 | 57939.3 | 0 | 13488.7 | On/Under Budget | 133.6 | 23.7 | 0 | 23.7 | 0 | 0 | 5564.5 | 52374.8 | Project is not in the WP or in 2020 WP | 0 | 52532 | -52532 | 52532 | -52532 | 25881.9 | 182.5 | 26310.4 | 23.7 | 23.7 | 23.7 | 24.6 | 24.6 | 24.6 | 12.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2023-01-02 | Not Started | 2023-02-14 | 2023-02-20 | Not Started | 2023-02-13 | Not Started | 2023-03-13 | Not Started | 2023-01-03 | 2023-01-03 | Not Started | 2023-01-04 | 2023-01-24 | Not Started | 2023-02-14 | 2023-02-27 | Not Started | 2023-04-05 | Not Started |  |  |  |  | 2023-04-05 | Not Started | 2023-07-18 | Not Started | 2023-08-16 | Not Started | 2023-10-17 | 2023-10-17 | 0 | On/ Ahead Schedule | Not Started | 2023-10-18 | 2023-10-31 | Not Started | 2023-12-07 | Not Started
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 | E.5015550.04 | 5789708 | ESTS | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2023 | SH | GRSSVLLY | Sierra Assets | 0 | 13875 | 13875 | 2.6278 | 0 | 2.6278 | [5 empty] | 60000 | 0 | 60000 | 35626.1 | 0 | 24373.9 | On/Under Budget | 13.1 | 2.8 | -34595 | 34597.8 | 0 | 0 | 913.7 | 117.4 | Project is not in the WP or in 2020 WP | 0 | 34728.1 | -34728.1 | 34728.1 | -34728.1 | 43.3 | 5.5 | 34663.6 | 2.8 | 2.8 | 2.8 | 2.9 | 2.9 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2022-01-17 | Not Started | 2022-03-01 | 2022-03-07 | Not Started | 2022-02-28 | Not Started | 2022-03-14 | Not Started | 2022-01-18 | 2022-01-18 | Not Started | 2022-01-19 | 2022-02-08 | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-03-22 | Not Started |  |  |  |  | 2022-03-22 | Not Started | 2022-07-04 | Not Started | 2022-08-02 | Not Started | 2022-10-03 | 2022-10-03 | 0 | On/ Ahead Schedule | Not Started | 2022-10-04 | 2022-10-17 | Not Started | 2022-11-23 | Not Started
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 | E.5015550.05 | 5789709 | ESTS | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2023 | SH | GRSSVLLY | Sierra Assets | 0 | 14192 | 14192 | 2.6879 | 0 | 2.6879 | [5 empty] | 94284 | 0 | 94284 | 80959.9 | 0 | 13324.1 | On/Under Budget | 19.9 | 4.3 | 0 | 4.3 | 0 | 0 | 1277.9 | 79682 | Project is not in the WP or in 2020 WP | 0 | 79706.1 | -79706.1 | 79706.1 | -79706.1 | 39607.5 | 237.4 | 39837.1 | 4.3 | 4.3 | 4.3 | 4.5 | 4.5 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2023-01-09 | Not Started | 2023-02-21 | 2023-02-27 | Not Started | 2023-02-20 | Not Started | 2023-03-06 | Not Started | 2023-01-10 | 2023-01-10 | Not Started | 2023-01-11 | 2023-01-31 | Not Started | 2023-02-21 | 2023-03-06 | Not Started | 2023-03-14 | Not Started |  |  |  |  | 2023-03-14 | Not Started | 2023-06-26 | Not Started | 2023-07-25 | Not Started | 2023-09-25 | 2023-09-25 | 0 | On/ Ahead Schedule | Not Started | 2023-09-26 | 2023-10-09 | Not Started | 2023-11-15 | Not Started
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 | E.5015550.06 | 5789710 | ESTS | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2023 | SH | GRSSVLLY | Sierra Assets | 0 | 17520 | 17520 | 3.3182 | 0 | 3.3182 | [5 empty] | 71428 | 0 | 71428 | 44387.4 | 0 | 27040.6 | On/Under Budget | 68.7 | 15 | 0 | 15 | 0 | 0 | 3298.5 | 41088.8 | Project is not in the WP or in 2020 WP | 0 | 41172.5 | -41172.5 | 41172.5 | -41172.5 | 20416.8 | 137.7 | 20534.3 | 15 | 15 | 15 | 15.5 | 15.5 | 7.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2023-01-09 | Not Started | 2023-02-21 | 2023-02-27 | Not Started | 2023-02-20 | Not Started | 2023-03-06 | Not Started | 2023-01-10 | 2023-01-10 | Not Started | 2023-01-11 | 2023-01-31 | Not Started | 2023-02-21 | 2023-03-06 | Not Started | 2023-03-14 | Not Started |  |  |  |  | 2023-03-14 | Not Started | 2023-06-26 | Not Started | 2023-07-25 | Not Started | 2023-09-25 | 2023-09-25 | 0 | On/ Ahead Schedule | Not Started | 2023-09-26 | 2023-10-09 | Not Started | 2023-11-15 | Not Started
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 | E.5015550.07 | 5789711 | ESTS | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2023 | SH | GRSSVLLY | Sierra Assets | 2960 | 0 | 2960 | 0.56061 | 0 | 0.56061 | [5 empty] | 60000 | 0 | 60000 | 22209.3 | 0 | 37790.7 | On/Under Budget | 16.2 | 3.5 | 0 | 3.5 | 0 | 0 | 972.7 | 21236.7 | Project is not in the WP or in 2020 WP | 0 | 21256.4 | -21256.4 | 21256.4 | -21256.4 | 8511.9 | 55.1 | 12669.7 | 3.5 | 3.5 | 3.5 | 3.7 | 3.7 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2022-01-06 | Not Started | 2022-02-18 | 2022-02-24 | Not Started | 2022-02-17 | Not Started | 2022-03-03 | Not Started | 2022-01-07 | 2022-01-07 | Not Started | 2022-01-10 | 2022-01-28 | Not Started | 2022-02-18 | 2022-03-03 | Not Started | 2022-03-11 | Not Started |  |  |  |  | 2022-03-11 | Not Started | 2022-06-23 | Not Started | 2022-07-22 | Not Started | 2022-09-22 | 2022-09-22 | 0 | On/ Ahead Schedule | Not Started | 2022-09-23 | 2022-10-06 | Not Started | 2022-11-14 | Not Started
35173387 | BR-09-01-W (E) SKYWAY PH3 20A PARB |  | 5786123 | ESTS | 08W | VEY1 | Virginia E Stauffer | CJPN | Corina Parker |  |  | Not in the WP |  |  | CHICO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35173959 | CWSP-MIWUK 1702-LR 38218-PH 1.6 |  | 5785985 | ESTS | 08W | J8PK | Jigneshkumar Patel |  |  |  |  | Not in the WP |  |  | SONORA |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35181199 | ECOP-WEST POINT 1101-H03-TS L373 |  | 5790907 | ESTS | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | JACKSON |  | 0 | 13306 | 13306 | 2.5201 | 0 | 2.5201 | [19 empty] | 120.1 | Project is not in the WP or in 2020 WP | 0 | 120.1 | -120.1 | 0 | 0
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | 5790005 | ESTS | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | JACKSON |  | 0 | 12038.4 | 12038.4 | 2.28 | 0 | 2.28 | [19 empty] | 10441.6 | Project is not in the WP or in 2020 WP | 0 | 1726296.8 | -1726296.8 | 0 | 0
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | 5790106 | ESTS | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | ANGLSCMP |  | 0 | 31680 | 31680 | 6 | 0 | 6 | [19 empty] | 56370.4 | Project is not in the WP or in 2020 WP | 0 | 56370.4 | -56370.4 | 0 | 0
35174468 | ECOP-STANISLAUS 1702-H01-LR37276-PH2 |  | 5790107 | ESTS | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | ANGLSCMP |  | 0 | 30202 | 30202 | 5.7201 | 0 | 5.7201 | [19 empty] | 50.4 | Project is not in the WP or in 2020 WP | 0 | 50.4 | -50.4 | 0 | 0
35174469 | ECOP-PINE GROVE 1102-H01-LR45292 |  | 5790105 | ESTS | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | JACKSON |  | 0 | 57446.4 | 57446.4 | 10.88 | 0 | 10.88 | [19 empty] | 445 | Project is not in the WP or in 2020 WP | 0 | 445 | -445 | 0 | 0
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | E.5034372.01 | 5792064 | ESTS | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 |  | SH | NAPA | North Bay Assets | 0 | 7718 | 7718 | 1.4617 | 0 | 1.4617 |  |  |  |  | Contract | 237833 | 0 | 237833 | 17913.8 | 0 | 219919.2 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 3878 | 14035.8 | Request 2021 Budget | 0 | 14035.8 | -14035.8 | 14035.8 | -14035.8 | 7740.3 | 4121.6 | 2173.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35191553 | BR-13-01-W (E) LIGHTFOOT WAY PARB |  | 5786123 | ESTS | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 1 | 1 | 0 | 8146.4 | 0 | -8146.4 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 8004.2 | 142.1 | Project is not in the WP or in 2020 WP | 0 | 142.1 | -142.1 | 142.1 | -142.1 | 48.9 | 46.6 | 46.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | E.5034352.01 | 5541303 | ESTS | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 |  | SH | NAPA | North Bay Assets | 0 | 11721.6 | 11721.6 | 2.22 | 0 | 2.22 |  |  |  |  | Contract | 682400 | 0 | 682400 | 74548.9 | 0 | 607851.1 | On/Under Budget | 10554.1 | 3518 | 2907 | 611 | 0 | 0 | 9257.6 | 68198.4 | Request 2021 Budget | 0 | 79363.4 | -79363.4 | 79363.4 | -79363.4 | 4208.5 | 15752.5 | 45330.4 | 3518 | 3518 | 3518 | 3518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-04-09 | Not Started | 2021-06-01 | 2021-06-07 | Not Started | 2021-05-31 | Not Started | 2021-06-28 | Not Started | 2021-04-12 | 2021-04-12 | Not Started | 2021-04-13 | 2021-05-03 | Not Started | 2021-06-01 | 2021-06-14 | Not Started | 2021-07-16 | Not Started | 2021-07-16 | Not Started | 2021-07-29 | Not Started | 2021-07-16 | Not Started | 2021-08-31 | Not Started | 2021-09-29 | Not Started | 2021-11-30 | 2021-11-30 | 0 | On/ Ahead Schedule | Not Started | 2021-12-01 | 2021-12-14 | Not Started | 2022-01-27 | Not Started
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | E.5034406.01 | 5792097 | ESTS | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 1426 | 1426 | 0.27008 | 0 | 0.27008 |  |  |  |  | GC | 950000 | 950000 | 0 | 21883.1 | 0 | -21883.1 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 7555.9 | 14327.3 | Request 2021 Budget | 0 | 14327.3 | -14327.3 | 14327.3 | -14327.3 | 10832.3 | 1195.8 | 2299.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157813 | BL-A | BL-A 35192281_ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-21 | Not Started | 2021-06-28 | 2021-07-02 | Not Started | 2021-06-25 | Not Started | 2021-07-23 | Not Started | 2021-05-24 | 2021-05-24 | Not Started | 2021-05-25 | 2021-06-14 | Not Started | 2021-06-28 | 2021-07-09 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-30 | Not Started | 2021-08-17 | Not Started | 2021-11-29 | Not Started | 2021-12-28 | Not Started | 2022-02-24 | 2022-02-28 | -4 | Behind Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-04-27 | Not Started
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | E.5034403.01 | 5792094 | ESTS | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2022 |  | SH | STROSA | Sonoma Assets | 4224 | 0 | 4224 | 0.8 | 0 | 0.8 |  |  |  |  | GC | 950000 | 700000 | 250000 | 45188.6 | 0 | 204811.4 | On/Under Budget | 0 | 0 | -15000 | 15000 | 0 | 0 | 15197.1 | 14991.5 | Request 2021 Budget | 0 | 29991.5 | -29991.5 | 29991.5 | -29991.5 | 14438.5 | 25366.6 | -9813.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 155774 | BL- A | BL- A 35192292_ECOP - FULTON 1107 - H02-LR604 Ph 1.1_08W - DD 210205 Feb.2021 | 2021-02-08 | 2021-07-02 | Not Started | 2021-09-13 | 2021-10-01 | Not Started | 2021-09-10 | Not Started | 2021-10-29 | Not Started | 2021-07-05 | 2021-07-05 | Not Started | 2021-07-06 | 2021-07-26 | Not Started | 2021-11-22 | 2021-12-31 | Not Started | 2022-01-03 | Not Started | 2022-01-03 | Not Started | 2022-03-18 | Not Started | 2022-01-03 | Not Started | 2022-03-18 | Not Started | 2022-03-21 | Not Started | 2022-05-03 | 2022-05-03 | 0 | On/ Ahead Schedule | Not Started | 2022-05-04 | 2022-05-17 | Not Started | 2022-06-30 | Not Started
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | E.5034713.01.02 | 5794554 | ESTS | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2021 | 2021 | SH | REDDING | North Valley Assets | 0 | 8217 | 8217 | 1.5562 | 0 | 1.5562 | [5 empty] | 1 | 1 | 0 | 17533.6 | 0 | -17533.6 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17533.6 | Request 2021 Budget | 0 | 17533.6 | -17533.6 | 17533.6 | -17533.6 | 0 | 8956.9 | 8576.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-02-01 | 158344 | BL-A_ | BL-A_35225825_CWSP - DESCHUTES 11049718 PH2.1_08W_Apr.2021 | 2021-04-01 | 2021-05-11 | Not Started | 2021-06-16 | 2021-06-22 | Not Started | 2021-06-15 | Not Started | 2021-07-13 | Not Started | 2021-05-12 | 2021-05-12 | Not Started | 2021-05-13 | 2021-06-02 | Not Started | 2021-06-16 | 2021-06-29 | Not Started | 2021-08-05 | Not Started | 2021-08-05 | Not Started | 2021-08-18 | Not Started | 2021-08-05 | Not Started | 2021-11-17 | Not Started | 2021-12-16 | Not Started | 2022-02-16 | 2022-02-16 | 0 | On/ Ahead Schedule | Not Started | 2022-02-17 | 2022-03-02 | Not Started | 2022-04-15 | Not Started
35226367 | BR-04-13-W (E) SUBSTATION/PATH PARB |  | 5786123 | ESTS | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 1 | 1 | 0 | 16610.4 | 0 | -16610.4 | OverRun | 0 | 0 | -4237.1 | 4237.1 | 0 | 0 | 0 | 12373.3 | Project is not in the WP or in 2020 WP | 0 | 16610.4 | -16610.4 | 16610.4 | -16610.4 | 2306.4 | 13.4 | 14290.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | E.5034794.01.02 | 5795152 | ESTS | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 4013 | 4013 | 0.76004 | 0 | 0.76004 |  |  |  |  | GC | 1 | 1 | 0 | 706.3 | 0 | -706.3 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706.3 | Request 2021 Budget | 0 | 706.3 | -706.3 | 706.3 | -706.3 | 0 | 0 | 706.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157829 | BL-A | BL-A 35226622_ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-21 | Not Started | 2021-06-28 | 2021-07-02 | Not Started | 2021-06-25 | Not Started | 2021-07-23 | Not Started | 2021-05-24 | 2021-05-24 | Not Started | 2021-05-25 | 2021-06-14 | Not Started | 2021-06-28 | 2021-07-09 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-30 | Not Started | 2021-08-17 | Not Started | 2021-11-29 | Not Started | 2021-12-28 | Not Started | 2022-02-24 | 2022-02-28 | -4 | Behind Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-04-27 | Not Started
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | ESTS | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2022 | SH | REDDING | North Valley Assets | 0 | 7603.2 | 7603.2 | 1.44 | 0 | 1.44 |  |  |  |  | GC | 150000 | 0 | 150000 | 24734.7 | 0 | 125265.3 | On/Under Budget | 0 | 0 | -24570 | 24570 | 0 | 0 | 0 | 164.7 | Budget Allocated | 2736000 | 2760734.7 | -24734.7 | 24734.7 | 2711265.3 | 0 | 0 | 24734.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158024 | BL-A_ | BL-A_35226630_)SH - KESWICK 1101 LR 1586 PH 1.5_08W_Mar.2021 | 2021-03-26 | 2021-05-18 | Not Started | 2021-06-16 | 2021-06-22 | Not Started | 2021-06-15 | Not Started | 2021-07-13 | Not Started | 2021-05-19 | 2021-05-19 | Not Started | 2021-05-20 | 2021-06-09 | Not Started | 2021-06-16 | 2021-06-29 | Not Started | 2021-08-05 | Not Started | 2021-08-05 | Not Started | 2021-08-18 | Not Started | 2021-08-05 | Not Started | 2021-10-20 | Not Started | 2021-11-18 | Not Started | 2021-12-30 | 2021-12-30 | 0 | On/ Ahead Schedule | Not Started | 2021-12-31 | 2022-01-13 | Not Started | 2022-02-28 | Not Started
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | ESTS | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2022 | SH | REDDING | North Valley Assets | 0 | 8131.2 | 8131.2 | 1.54 | 0 | 1.54 |  |  |  |  | GC | 150000 | 0 | 150000 | 26005.5 | 0 | 123994.5 | On/Under Budget | 0 | 0 | -24570 | 24570 | 0 | 0 | 0 | 1435.5 | Budget Allocated | 2926000 | 2951743.5 | -25743.5 | 26005.5 | 2899994.5 | 0 | 261.8 | 25743.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158025 | BL-A_ | BL-A_35226631_SH - KESWICK 1101 LR 1586 PH 1.6_08W_Mar.2021 | 2021-03-26 | 2021-06-07 | Not Started | 2021-06-29 | 2021-07-05 | Not Started | 2021-06-28 | Not Started | 2021-08-02 | Not Started | 2021-06-08 | 2021-06-08 | Not Started | 2021-06-09 | 2021-06-29 | Not Started | 2021-06-29 | 2021-07-12 | Not Started | 2021-08-25 | Not Started | 2021-08-25 | Not Started | 2021-09-07 | Not Started | 2021-08-25 | Not Started | 2021-10-19 | Not Started | 2021-11-17 | Not Started | 2021-12-30 | 2022-01-12 | -13 | Behind Schedule | Not Started | 2022-01-13 | 2022-01-26 | Not Started | 2022-03-11 | Not Started
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | E.5034803.01.01 | 5795298 | ESTS | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | PLCRVLLE | Sierra Assets | 0 | 13833.6 | 13833.6 | 2.62 | 0 | 2.62 |  |  |  |  | Contract | 1 | -449999 | 450000 | 57600.6 | 0 | 392399.4 | On/Under Budget | 2283870.1 | 17413.5 | 0 | 17413.5 | 0 | 0 | 0 | 57600.6 | Request 2021 Budget | 0 | 2360664.3 | -2360664.3 | 2358884.3 | -2358884.3 | 0 | 7535.2 | 50065.4 | 17413.5 | 123451.3 | 726049.1 | 627563.1 | 469688.2 | 232758.8 | 77461.6 | 18423.5 | 8474.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156211 | BL-A | BL-A 35226845_ECOP -DIAMOND SPRINGS 1107-H02-LR1402PH2_08W - DD 210205 Feb. 2021 | 2021-02-23 | 2021-06-11 | Not Started | 2021-06-14 | 2021-06-18 | Not Started | 2021-06-11 | Not Started | 2021-08-06 | Not Started | 2021-06-14 | 2021-06-14 | Not Started | 2021-06-15 | 2021-07-05 | Not Started | 2021-06-14 | 2021-07-02 | Not Started | 2021-08-31 | Not Started | 2021-08-31 | Not Started | 2021-09-13 | Not Started | 2021-08-31 | Not Started | 2021-11-15 | Not Started | 2021-12-07 | Not Started | 2021-12-30 | 2022-01-12 | -13 | Behind Schedule | Not Started | 2022-01-13 | 2022-01-26 | Not Started | 2022-03-11 | Not Started
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | E.5034804.01.01 | 5795299 | ESTS | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2021 | 2021 | SH | PLCRVLLE | Sierra Assets | 0 | 7851 | 7851 | 1.4869 | 0 | 1.4869 | 7851 | 0 | 1.4869 | 0 | GC | 70000 | 0 | 70000 | 9377.1 | 0 | 60622.9 | On/Under Budget | 3027181.9 | 25154.9 | 0 | 25154.9 | 0 | 0 | 0 | 9377.1 | Budget Allocated | 3089168.45 | 3061714 | 27454.45 | 3061714 | 27454.45 | 0 | 1584.2 | 7792.9 | 25154.9 | 4969.6 | 751825.9 | 751825.9 | 751825.9 | 751825.9 | 4969.6 | 4969.6 | 4969.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-04-30 | Not Started | 2021-06-18 | 2021-06-24 | Not Started | 2021-06-17 | Not Started | 2021-07-15 | Not Started | 2021-05-03 | 2021-05-03 | Not Started | 2021-05-04 | 2021-05-24 | Not Started | 2021-06-18 | 2021-07-01 | Not Started | 2021-08-09 | Not Started | 2021-08-09 | Not Started | 2021-08-20 | Not Started | 2021-08-09 | Not Started | 2021-11-19 | Not Started | 2021-12-20 | Not Started | 2022-02-18 | 2022-02-18 | 0 | On/ Ahead Schedule | Not Started | 2022-02-21 | 2022-03-04 | Not Started | 2022-04-19 | Not Started
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | E.5034804.01.02 | 5795299 | ESTS | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2021 | 2021 | SH | PLCRVLLE | Sierra Assets | 0 | 10475 | 10475 | 1.9839 | 0 | 1.9839 |  |  |  |  | GC | 70000 | 0 | 70000 | 6616.6 | 0 | 63383.4 | On/Under Budget | 3740732.4 | 35247.5 | 0 | 35247.5 | 0 | 0 | 0 | 6616.5 | Budget Allocated | 3812484.87 | 3782596.4 | 29888.47 | 3782596.4 | 29888.47 | 0 | 1257.4 | 5359.1 | 35247.5 | 4969.6 | 930213.5 | 930213.5 | 930213.5 | 930213.5 | 4969.6 | 4969.6 | 4969.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-04-30 | Not Started | 2021-06-18 | 2021-06-24 | Not Started | 2021-06-17 | Not Started | 2021-07-15 | Not Started | 2021-05-03 | 2021-05-03 | Not Started | 2021-05-04 | 2021-05-24 | Not Started | 2021-06-18 | 2021-07-01 | Not Started | 2021-08-09 | Not Started | 2021-08-09 | Not Started | 2021-08-20 | Not Started | 2021-08-09 | Not Started | 2021-11-19 | Not Started | 2021-12-20 | Not Started | 2022-02-18 | 2022-02-18 | 0 | On/ Ahead Schedule | Not Started | 2022-02-21 | 2022-03-04 | Not Started | 2022-04-19 | Not Started
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | E.5034804.01.03 | 5795299 | ESTS | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | PLCRVLLE | Sierra Assets | 0 | 15153 | 15153 | 2.8699 | 0 | 2.8699 |  |  |  |  | GC | 1 | 1 | 0 | 9529.9 | 0 | -9529.9 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9529.9 | Request 2021 Budget | 0 | 9529.9 | -9529.9 | 9529.9 | -9529.9 | 0 | 230.6 | 9299.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156276 | BL-A | BL-A 35226848_CWSP - SHINGLE SPRINGS 2109-LR 9372PH2.2_08W - DD 210219 Feb. 2021 | 2021-02-25 | 2021-05-04 | Not Started | 2021-05-24 | 2021-05-28 | Not Started | 2021-05-21 | Not Started | 2021-06-29 | Not Started | 2021-05-05 | 2021-05-05 | Not Started | 2021-05-06 | 2021-05-26 | Not Started | 2021-06-07 | 2021-07-16 | Not Started | 2021-07-22 | Not Started | 2021-07-22 | Not Started | 2021-08-04 | Not Started | 2021-07-22 | Not Started | 2021-10-27 | Not Started | 2021-11-25 | Not Started | 2021-12-27 | 2022-01-12 | -16 | Behind Schedule | Not Started | 2022-01-13 | 2022-01-26 | Not Started | 2022-03-11 | Not Started
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | E.5034804.01.05 | 5795299 | ESTS | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | PLCRVLLE | Sierra Assets | 0 | 9187 | 9187 | 1.74 | 0 | 1.74 | 7748 | 0 | 1.4674 | 0 | GC | 1 | 1 | 0 | 10614 | 0 | -10614 | OverRun | 0 | 0 | -440.7 | 440.7 | 0 | 0 | 0 | 10173.4 | Request 2021 Budget | 0 | 10614.1 | -10614.1 | 10614.1 | -10614.1 | 0 | 1947.4 | 8666.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156278 | BL-A | BL-A 35226850_CWSP - SHINGLE SPRINGS 2109-LR 9372PH2.4_08W - DD 210219 Feb. 2021 | 2021-02-25 | 2021-04-09 | Not Started | 2021-05-17 | 2021-05-21 | Not Started | 2021-05-14 | Not Started | 2021-06-11 | Not Started | 2021-04-12 | 2021-04-12 | Not Started | 2021-04-13 | 2021-05-03 | Not Started | 2021-05-11 | 2021-06-21 | Not Started | 2021-07-06 | Not Started | 2021-07-06 | Not Started | 2021-07-19 | Not Started | 2021-07-06 | Not Started | 2021-08-30 | Not Started | 2021-09-07 | Not Started | 2021-10-22 | 2021-11-05 | -14 | Behind Schedule | Not Started | 2021-11-08 | 2021-11-19 | Not Started | 2022-01-04 | Not Started
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | E.5034804.01.06 | 5795299 | ESTS | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | PLCRVLLE | Sierra Assets | 0 | 11563 | 11563 | 2.19 | 0 | 2.19 |  |  |  |  | GC | 1 | 1 | 0 | 6804.4 | 0 | -6804.4 | OverRun | 0 | 0 | 278.6 | -278.6 | 0 | 0 | 0 | 7083 | Request 2021 Budget | 0 | 6804.4 | -6804.4 | 6804.4 | -6804.4 | 0 | 1703.9 | 5100.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156279 | BL-A | BL-A 35226851_CWSP - SHINGLE SPRINGS 2109-LR 9372PH2.5_08W - DD 210219 Feb. 2021 | 2021-02-25 | 2021-05-27 | Not Started | 2021-05-28 | 2021-06-03 | Not Started | 2021-05-03 | Not Started | 2021-07-22 | Not Started | 2021-05-28 | 2021-05-28 | Not Started | 2021-05-31 | 2021-06-18 | Not Started | 2021-07-12 | 2021-08-20 | Not Started | 2021-08-23 | Not Started | 2021-08-23 | Not Started | 2021-09-03 | Not Started | 2021-08-23 | Not Started | 2021-11-12 | Not Started | 2021-11-22 | Not Started | 2021-11-24 | 2022-01-20 | -57 | Behind Schedule | Not Started | 2022-01-21 | 2022-02-03 | Not Started | 2022-03-21 | Not Started
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | E.5034804.01.07 | 5795299 | ESTS | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2021 | 2021 | SH | PLCRVLLE | Sierra Assets | 0 | 13164 | 13164 | 2.4932 | 0 | 2.4932 |  |  |  |  | GC | 70000 | 0 | 70000 | 62366.6 | 0 | 7633.4 | On/Under Budget | 7838349.6 | 66102 | 0 | 66102 | 0 | 0 | 0 | 62366.6 | Budget Allocated | 7975840.77 | 7969488.2 | 6352.57 | 7966818.2 | 9022.57 | 0 | 5287.2 | 57079.4 | 66102 | 4969.6 | 4969.6 | 1954617.8 | 1954617.8 | 1954617.8 | 1954617.8 | 4969.6 | 4969.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-04-16 | Not Started | 2021-06-18 | 2021-06-24 | Not Started | 2021-06-17 | Not Started | 2021-07-15 | Not Started | 2021-04-19 | 2021-04-19 | Not Started | 2021-04-20 | 2021-05-10 | Not Started | 2021-06-18 | 2021-07-01 | Not Started | 2021-08-09 | Not Started | 2021-08-09 | Not Started | 2021-08-20 | Not Started | 2021-08-09 | Not Started | 2021-11-19 | Not Started | 2021-12-20 | Not Started | 2022-02-18 | 2022-02-18 | 0 | On/ Ahead Schedule | Not Started | 2022-02-21 | 2022-03-04 | Not Started | 2022-04-19 | Not Started
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | 5794998 | ESTS | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 |  | SH | NAPA | North Bay Assets | 0 | 8026 | 8026 | 1.5201 | 0 | 1.5201 |  |  |  |  | Contract | 190000 | 190000 | 0 | 31726.2 | 0 | -31726.2 | OverRun | 0 | 0 | 949 | -949 | 0 | 0 | 0 | 32675.1 | Request 2021 Budget | 0 | 31726.1 | -31726.1 | 31726.1 | -31726.1 | 0 | 686.8 | 31039.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35222234 | REMG 581 - OAKHURST 1101, MIAMI MOUNTAIN |  | 5543982 | ESTS | 08W | TXY6 | Tom Yang |  |  |  |  | Not in the WP |  | SH | OAKHURST |  | 0 | 7920 | 7920 | 1.5 | 0 | 1.5 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35222236 | MARIPOSA 2101 - #531 SLAUGHTER HOUSE |  | 5543983 | ESTS | 08W | J8PK | Jigneshkumar Patel |  |  |  |  | Not in the WP |  | SH | MARIPOSA |  | 0 | 5227.2 | 5227.2 | 0.99 | 0 | 0.99 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35219591 | CWSP - OLETA 1101754718 |  | 5794611 | ESTS | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | JACKSON |  | 0 | 7128 | 7128 | 1.35 | 0 | 1.35 | [19 empty] | 11702.5 | Project is not in the WP or in 2020 WP | 0 | 11702.5 | -11702.5 | 0 | 0
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | E.5034741.01.01 | 5794898 | ESTS | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | Not in the WP |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 4699 | 4699 | 0.88996 | 0 | 0.88996 | [5 empty] | 1 | 1 | 0 | 8093.3 | 0 | -8093.3 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8093.2 | Project is not in the WP or in 2020 WP | 0 | 8093.2 | -8093.2 | 8093.2 | -8093.2 | 2858.7 | 3390.7 | 1843.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157828 | BL-A | BL-A 35222045_SH - MIDDLTOWN 1103 - LR 830 PH4_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-21 | Not Started | 2021-06-28 | 2021-07-02 | Not Started | 2021-06-25 | Not Started | 2021-07-23 | Not Started | 2021-05-24 | 2021-05-24 | Not Started | 2021-05-25 | 2021-06-14 | Not Started | 2021-06-28 | 2021-07-09 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-30 | Not Started | 2021-08-17 | Not Started | 2021-11-29 | Not Started | 2021-12-28 | Not Started | 2022-02-24 | 2022-02-28 | -4 | Behind Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-04-27 | Not Started
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | E.5034572.01.08 | 5793918 | ESTS | 08W | JTHL | Joseph T Hembree | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2021 | FRRB | OROVILLE | North Valley Assets | 4330 | 0 | 4330 | 0.82008 | 0 | 0.82008 |  |  |  |  | GC | 950000 | 0 | 950000 | 102013.6 | 0 | 847986.4 | On/Under Budget | 3429320.3 | 110.4 | -9011.4 | 9121.8 | 0 | 0 | 0 | 93002.2 | Budget Allocated | 3490209.3 | 3531388.5 | -41179.2 | 3531388.5 | -41179.2 | 375.1 | 52222.1 | 49416.4 | 110.4 | 110.4 | 500110.3 | 500112.8 | 500112.8 | 500112.8 | 500112.8 | 500112.8 | 428479.8 | 55.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.5 | 2021-04-02 | 155417 | BL-A | BL-A 35223343_FRRB - Big Bend 1102 ¿ Lake Madrone Zone 1_08W - Feb. 2021 | 2021-02-01 | 2021-04-02 | Not Started | 2021-05-07 | 2021-05-13 | Not Started | 2021-05-06 | Not Started | 2021-06-03 | Not Started | 2021-04-02 | 2021-04-02 | Not Started | 2021-04-05 | 2021-04-23 | Not Started | 2020-12-28 | 2021-04-02 | In Progress | 2021-06-28 | Not Started | 2021-06-28 | Not Started | 2021-09-06 | Not Started | 2021-09-07 | Not Started | 2021-10-22 | Not Started | 2021-11-15 | Not Started | 2022-02-11 | 2021-12-14 | 59 | On/ Ahead Schedule | Not Started | 2021-12-15 | 2021-12-28 | Not Started | 2022-02-10 | Not Started
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | E.5034792.01.01 | 5795144 | ESTS | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2022 |  | SH | STROSA | Sonoma Assets | 2481.6 | 0 | 2481.6 | 0.47 | 0 | 0.47 |  |  |  |  | GC | 1 | -249999 | 250000 | 2927.3 | 0 | 247072.7 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2927.3 | Request 2021 Budget | 0 | 2927.3 | -2927.3 | 2927.3 | -2927.3 | 691.8 | 1621.4 | 614.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 155775 | BL- A | BL- A 35225594_ ECOP - FULTON 1107 - H02-LR604 Ph 1.2_08W - DD 210205 Feb.2021 | 2021-02-08 | 2021-07-02 | Not Started | 2021-09-13 | 2021-10-01 | Not Started | 2021-09-10 | Not Started | 2021-10-29 | Not Started | 2021-07-05 | 2021-07-05 | Not Started | 2021-07-06 | 2021-07-26 | Not Started | 2021-11-22 | 2021-12-31 | Not Started | 2022-01-03 | Not Started | 2022-01-03 | Not Started | 2022-03-18 | Not Started | 2022-01-03 | Not Started | 2022-03-18 | Not Started | 2022-03-21 | Not Started | 2022-05-03 | 2022-05-03 | 0 | On/ Ahead Schedule | Not Started | 2022-05-04 | 2022-05-17 | Not Started | 2022-06-30 | Not Started
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | E.5034792.01.02 | 5795144 | ESTS | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | STROSA | Sonoma Assets | 0 | 5860 | 5860 | 1.1098 | 0 | 1.1098 |  |  |  |  | GC | 1 | -149999 | 150000 | 16654.8 | 0 | 133345.2 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16654.8 | Request 2021 Budget | 0 | 16654.8 | -16654.8 | 16654.8 | -16654.8 | 461.2 | 1271 | 14922.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 155776 | BL- A | BL- A 35225595_ECOP - FULTON 1107 - H02-LR604 Ph 1.3_08W - DD 210205 Feb.2021 | 2021-02-08 | 2021-06-04 | Not Started | 2021-08-02 | 2021-08-13 | Not Started | 2021-07-30 | Not Started | 2021-09-03 | Not Started | 2021-06-07 | 2021-06-07 | Not Started | 2021-06-08 | 2021-06-28 | Not Started | 2021-07-12 | 2021-07-23 | Not Started | 2021-09-28 | Not Started | 2021-09-28 | Not Started | 2021-09-28 | Not Started | 2021-09-28 | Not Started | 2021-11-11 | Not Started | 2021-11-12 | Not Started | 2021-12-27 | 2021-12-13 | 14 | On/ Ahead Schedule | Not Started | 2021-12-14 | 2021-12-27 | Not Started | 2022-02-09 | Not Started
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | E.5034792.01.03 | 5795144 | ESTS | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | STROSA | Sonoma Assets | 0 | 3907.2 | 3907.2 | 0.74 | 0 | 0.74 |  |  |  |  | GC | 1 | -149999 | 150000 | 46479 | 0 | 103521 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46479 | Request 2021 Budget | 0 | 46479 | -46479 | 46479 | -46479 | 461.2 | 2193.4 | 43824.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 155777 | BL- A | BL- A 35225597_ ECOP - FULTON 1107 - H02-LR604 Ph 1.4_08W - DD 210205 Feb. 2021 | 2021-02-08 | 2021-06-08 | Not Started | 2021-07-05 | 2021-07-16 | Not Started | 2021-07-02 | Not Started | 2021-08-06 | Not Started | 2021-06-09 | 2021-06-09 | Not Started | 2021-06-10 | 2021-06-30 | Not Started | 2021-06-14 | 2021-06-25 | Not Started | 2021-08-31 | Not Started | 2021-08-31 | Not Started | 2021-08-31 | Not Started | 2021-08-31 | Not Started | 2021-10-14 | Not Started | 2021-10-15 | Not Started | 2021-12-27 | 2021-11-15 | 42 | On/ Ahead Schedule | Not Started | 2021-11-16 | 2021-11-29 | Not Started | 2022-01-12 | Not Started
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | E.5034792.01.04 | 5795144 | ESTS | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | STROSA | Sonoma Assets | 0 | 4857.6 | 4857.6 | 0.92 | 0 | 0.92 |  |  |  |  | GC | 1 | -149999 | 150000 | 8706.4 | 0 | 141293.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8706.4 | Request 2021 Budget | 0 | 8706.4 | -8706.4 | 8706.4 | -8706.4 | 461.2 | 1962.8 | 6282.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 155778 | BL- A | BL- A 35225598_ECOP - FULTON 1107 - H02-LR604 Ph 1.5_08W - DD 210205 Feb. 2021 | 2021-02-08 | 2021-06-04 | Not Started | 2021-08-02 | 2021-08-13 | Not Started | 2021-07-30 | Not Started | 2021-09-03 | Not Started | 2021-06-07 | 2021-06-07 | Not Started | 2021-06-08 | 2021-06-28 | Not Started | 2021-07-12 | 2021-07-23 | Not Started | 2021-09-28 | Not Started | 2021-09-28 | Not Started | 2021-10-11 | Not Started | 2021-09-28 | Not Started | 2021-11-11 | Not Started | 2021-11-12 | Not Started | 2021-12-27 | 2021-12-13 | 14 | On/ Ahead Schedule | Not Started | 2021-12-14 | 2021-12-27 | Not Started | 2022-02-09 | Not Started
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | E.5034572.01.11 | 5793918 | ESTS | 08W | JTHL | Joseph T Hembree | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2021 | FRRB | OROVILLE | North Valley Assets | 5016 | 0 | 5016 | 0.95 | 0 | 0.95 |  |  |  |  | GC | 950000 | 0 | 950000 | 50324.3 | 0 | 899675.7 | On/Under Budget | 3432857.3 | 108.9 | 0 | 108.9 | 0 | 0 | 0 | 50324.3 | Budget Allocated | 3490167.5 | 3483290.7 | 6876.8 | 3483290.7 | 6876.8 | 1031.5 | 47934.1 | 1358.7 | 108.9 | 500108.9 | 500108.9 | 500111.4 | 500111.4 | 500111.4 | 500111.4 | 432138.4 | 55.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 155425 | BL-A | BL-A 35225821_FRRB - Big Bend 1102 ¿ Lake Madrone Zone 2_08W - Feb. 2021 | 2021-02-01 | 2021-04-02 | Not Started | 2021-05-14 | 2021-05-20 | Not Started | 2021-05-13 | Not Started | 2021-06-10 | Not Started | 2021-04-02 | 2021-04-02 | Not Started | 2021-04-05 | 2021-04-23 | Not Started | 2020-12-28 | 2021-04-02 | In Progress | 2021-07-05 | Not Started | 2021-07-05 | Not Started | 2021-09-03 | Not Started | 2021-09-06 | Not Started | 2021-11-16 | Not Started | 2021-12-08 | Not Started | 2022-02-03 | 2022-01-06 | 28 | On/ Ahead Schedule | Not Started | 2022-01-07 | 2022-01-20 | Not Started | 2022-03-07 | Not Started
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | 5790005 | ESTS | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | JACKSON | [26 empty] | 26979.6 | Project is not in the WP or in 2020 WP | 0 | 26979.6 | -26979.6 | 0 | 0
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | E.5034695.01.01 | 5794546 | ESTS | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | OAKHURST | Yosemite Assets | 0 | 12473 | 12473 | 2.3623 | 0 | 2.3623 |  |  |  |  | Contract | 1 | -274999 | 275000 | 79812.9 | 0 | 195187.1 | On/Under Budget | 1466816.9 | 593491.1 | 1453.4 | 592037.7 | 0 | 0 | 0 | 81266.3 | Request 2021 Budget | 0 | 2141900.8 | -2141900.8 | 2140120.8 | -2140120.8 | 6123.3 | 21025.8 | 52663.8 | 593491.1 | 568675.7 | 284824 | 291512.5 | 255439.3 | 50793.2 | 8536.1 | 4690.7 | 2345.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-28 | Not Started | 2021-06-14 | 2021-06-18 | Not Started | 2021-06-11 | Not Started | 2021-07-23 | Not Started | 2021-05-31 | 2021-05-31 | Not Started | 2021-06-01 | 2021-06-21 | Not Started | 2021-06-14 | 2021-06-25 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-30 | Not Started | 2021-08-17 | Not Started | 2021-11-29 | Not Started | 2021-12-28 | Not Started | 2022-02-28 | 2022-02-28 | 0 | On/ Ahead Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-04-27 | Not Started
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | E.5034696.01.01 | 5794547 | ESTS | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 3774 | 3774 | 0.71477 | 0 | 0.71477 | 3709 | 0 | 0.70246 | 0 | GC | 475000 | 0 | 475000 | 75645.1 | 0 | 399354.9 | On/Under Budget | 0 | 0 | -58783.1 | 58783.1 | 0 | 0 | 0 | 16861.9 | Request 2021 Budget | 0 | 75645 | -75645 | 75645 | -75645 | 6819.6 | 8058.8 | 60766.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-04-30 | Not Started | 2021-08-23 | 2021-08-27 | Not Started | 2021-08-20 | Not Started | 2021-09-17 | Not Started | 2021-05-03 | 2021-05-03 | Not Started | 2021-05-04 | 2021-05-24 | Not Started | 2021-09-15 | 2021-09-28 | Not Started | 2021-10-21 | Not Started | 2021-10-21 | Not Started | 2021-11-03 | Not Started | 2021-10-21 | Not Started | 2021-11-26 | Not Started | 2021-12-27 | Not Started | 2022-02-25 | 2022-02-25 | 0 | On/ Ahead Schedule | Not Started | 2022-02-28 | 2022-03-11 | Not Started | 2022-04-26 | Not Started
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | E.5034613.01.01 | 5794202 | ESTS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | SNCARLOS | Peninsula Assets | 11774 | 0 | 11774 | 2.2299 | 0 | 2.2299 |  |  |  |  | Contract | 500000 | 0 | 500000 | 23356.1 | 66682 | 543325.9 | On/Under Budget | 4540692.7 | 50587.4 | 141.2 | 50446.2 | 0 | 0 | 3168.7 | 20328.6 | Budget Allocated | 7805000 | 7802223.4 | 2776.6 | 4611467.5 | 3193532.5 | 5553.6 | 9407 | 5226.8 | 50587.4 | 3479.4 | 3479.4 | 3479.4 | 1849471.1 | 1344032.1 | 1334473.1 | 1139.1 | 1139.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-10-08 | Not Started | 2022-08-02 | 2022-08-08 | Not Started | 2022-08-01 | Not Started | 2022-08-29 | Not Started | 2021-10-11 | 2021-10-11 | Not Started | 2021-10-12 | 2021-11-01 | Not Started | 2022-08-02 | 2022-08-15 | Not Started | 2022-09-21 | Not Started | 2022-09-21 | Not Started | 2022-10-31 | Not Started | 2022-09-21 | Not Started | 2023-01-03 | Not Started | 2023-02-01 | Not Started | 2023-04-04 | 2023-04-04 | 0 | On/ Ahead Schedule | Not Started | 2023-04-05 | 2023-04-18 | Not Started | 2023-06-01 | Not Started
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | E.5034614.01.01 | 5794201 | ESTS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | SNCARLOS | Peninsula Assets | 15312 | 0 | 15312 | 2.9 | 0 | 2.9 |  |  |  |  | Contract | 500000 | 0 | 500000 | 23824.1 | 71300 | 547475.9 | On/Under Budget | 4541592.4 | 58530.3 | 210.9 | 58319.4 | 0 | 0 | 1503 | 22532 | Budget Allocated | 10150000 | 10153552.1 | -3552.1 | 4622443.8 | 5527556.2 | 7020.5 | 10246 | 5054.6 | 58530.3 | 3985.3 | 3676.3 | 3676.3 | 1849471.1 | 1344032.1 | 1334473.1 | 1139.1 | 1139.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-10-08 | Not Started | 2022-08-02 | 2022-08-08 | Not Started | 2022-08-01 | Not Started | 2022-08-29 | Not Started | 2021-10-11 | 2021-10-11 | Not Started | 2021-10-12 | 2021-11-01 | Not Started | 2022-08-02 | 2022-08-15 | Not Started | 2022-09-21 | Not Started | 2022-09-21 | Not Started | 2022-10-31 | Not Started | 2022-09-21 | Not Started | 2023-01-03 | Not Started | 2023-02-01 | Not Started | 2023-04-04 | 2023-04-04 | 0 | On/ Ahead Schedule | Not Started | 2023-04-05 | 2023-04-18 | Not Started | 2023-06-01 | Not Started
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | E.5034401.01 | 5792092 | ESTS | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | PLCRVLLE | Sierra Assets | 0 | 26400 | 26400 | 5 | 0 | 5 |  |  |  |  | Contract | 1 | -949999 | 950000 | 187121.1 | 0 | 762878.9 | On/Under Budget | 5700226.9 | 1215784.1 | 243.7 | 1215540.4 | 0 | 0 | 1955.2 | 185409.5 | Request 2021 Budget | 0 | 7107228.8 | -7107228.8 | 7101176.8 | -7101176.8 | 5326.3 | 5450.6 | 174388.9 | 1215784.1 | 2186086.3 | 1003699.6 | 815096.7 | 809009.7 | 729998.9 | 67280.5 | 54651.3 | 34403.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156209 | BL-A | BL-A 35192290_ECOP - DIAMOND SPRINGS 1107 - H01-LR1402_08W - DD 210205 Feb. 2021 | 2021-02-23 | 2021-04-16 | Not Started | 2021-05-25 | 2021-05-31 | Not Started | 2021-05-24 | Not Started | 2021-06-21 | Not Started | 2021-04-19 | 2021-04-19 | Not Started | 2021-04-20 | 2021-05-10 | Not Started | 2021-05-25 | 2021-06-14 | Not Started | 2021-07-14 | Not Started | 2021-07-14 | Not Started | 2021-07-27 | Not Started | 2021-07-14 | Not Started | 2021-09-28 | Not Started | 2021-10-20 | Not Started | 2021-12-30 | 2021-12-06 | 24 | On/ Ahead Schedule | Not Started | 2021-12-07 | 2021-12-20 | Not Started | 2022-02-02 | Not Started
35192683 | BR-05-15-W CLARK-5 PARB |  | 5786123 | ESTS | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 1 | 1 | 0 | 70263.4 | 0 | -70263.4 | OverRun | 3403.1 | 414.2 | 0 | 414.2 | 0 | 0 | 68991.4 | 1271.9 | Project is not in the WP or in 2020 WP | 0 | 5089.1 | -5089.1 | 5089.1 | -5089.1 | 467.7 | 402.1 | 402.1 | 414.2 | 414.2 | 414.2 | 429.1 | 429.1 | 429.1 | 429.1 | 429.1 | 429.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | E.5034713.01.01 | 5794554 | ESTS | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2021 | 2022 | SH | REDDING | North Valley Assets | 0 | 18241 | 18241 | 3.4547 | 0 | 3.4547 | [5 empty] | 1 | 1 | 0 | 23293.8 | 0 | -23293.8 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23293.9 | Request 2021 Budget | 0 | 23293.9 | -23293.9 | 23293.9 | -23293.9 | 8314.8 | 9351.5 | 5627.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-12-30 |  |  |  |  | 2022-04-08 | Not Started | 2022-05-16 | 2022-05-20 | Not Started | 2022-05-13 | Not Started | 2022-06-10 | Not Started | 2022-04-11 | 2022-04-11 | Not Started | 2022-04-12 | 2022-05-02 | Not Started | 2022-05-16 | 2022-05-27 | Not Started | 2022-07-05 | Not Started | 2022-07-05 | Not Started | 2022-07-18 | Not Started | 2022-07-05 | Not Started | 2022-10-17 | Not Started | 2022-11-15 | Not Started | 2022-12-30 | 2022-12-30 | 0 | On/ Ahead Schedule | Not Started | 2023-01-02 | 2023-01-13 | Not Started | 2023-02-28 | Not Started
35219272 | CWSP - MIDDLETOWN 1101481876 | E.5034696.01.02 | 5794547 | ESTS | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 4857.6 | 4857.6 | 0.92 | 0 | 0.92 |  |  |  |  | GC | 950000 | 0 | 950000 | 31148.2 | 0 | 918851.8 | On/Under Budget | 0 | 0 | -22402 | 22402 | 0 | 0 | 0 | 8746.2 | Request 2021 Budget | 0 | 31148.2 | -31148.2 | 31148.2 | -31148.2 | 5391.5 | 3418.8 | 22337.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157826 | BL-A | BL-A 35219272_CWSP - MIDDLETOWN 1101481876_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-17 | Not Started | 2021-06-01 | 2021-06-07 | Not Started | 2021-05-31 | Not Started | 2021-07-12 | Not Started | 2021-05-18 | 2021-05-18 | Not Started | 2021-05-19 | 2021-06-08 | Not Started | 2021-06-01 | 2021-06-14 | Not Started | 2021-08-04 | Not Started | 2021-08-04 | Not Started | 2021-08-17 | Not Started | 2021-08-04 | Not Started | 2021-11-16 | Not Started | 2021-12-15 | Not Started | 2022-01-18 | 2022-02-15 | -28 | Behind Schedule | Not Started | 2022-02-16 | 2022-03-01 | Not Started | 2022-04-14 | Not Started
35219273 | CWSP - VOLTA 110149742 | E.5034705.01.01 | 5794543 | ESTS | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2021 | 2021 | SH | REDBLUFF | North Valley Assets | 0 | 15470 | 15470 | 2.9299 | 0 | 2.9299 |  |  |  |  | GC | 1 | 1 | 0 | 133927 | 0 | -133927 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133927 | Request 2021 Budget | 0 | 133927 | -133927 | 133927 | -133927 | 5872.9 | 3463.4 | 124590.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156055 | BL-A | BL-A _35219273_ CWSP - VOLTA 110149742_ Feb.2021 | 2021-02-18 | 2021-06-10 | Not Started | 2021-07-16 | 2021-07-22 | Not Started | 2021-07-15 | Not Started | 2021-08-12 | Not Started | 2021-06-11 | 2021-06-11 | Not Started | 2021-06-14 | 2021-07-02 | Not Started | 2021-07-16 | 2021-07-29 | Not Started | 2021-09-06 | Not Started | 2021-09-06 | Not Started | 2021-09-17 | Not Started | 2021-09-06 | Not Started | 2021-12-17 | Not Started | 2022-01-17 | Not Started | 2022-02-01 | 2022-01-31 | 1 | On/ Ahead Schedule | Not Started | 2022-02-01 | 2022-02-14 | Not Started | 2022-03-30 | Not Started
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | E.5014727.02 | 5786001 | ESTS | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 6650 | 6650 | 1.2595 | 0 | 1.2595 | [5 empty] | 1 | -299999 | 300000 | 76919.5 | 0 | 223080.5 | On/Under Budget | 1827201 | 133.8 | 0 | 133.8 | 0 | 562.7 | 27493.6 | 48863.2 | Project is not in the WP or in 2020 WP | 0 | 49063.9 | -49063.9 | 49063.9 | -49063.9 | 68833.1 | -20410.3 | 440.4 | 133.8 | 66.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7256.8 | 231915.5 | 119503.8 | 253777.7 | 566278.9 | 495617.3 | 121032.1 | 8785.1 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 1827134 | 2021-04-02 | 154935 | BL-B | BL-B 35112972_CWSP - WEST POINT 1101 -LR 13444- PH 1.2_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2021-12-14 | Not Started | 2021-12-15 | 2022-01-11 | Not Started | 2022-01-24 | Not Started | 2022-01-25 | Not Started | 2022-01-12 | 2022-01-12 | Not Started | 2022-01-13 | 2022-01-26 | Not Started | 2022-01-25 | 2022-01-25 | Not Started | 2022-03-16 | Not Started |  |  |  |  | 2022-03-16 | Not Started | 2022-05-11 | Not Started | 2022-05-11 | Not Started | 2022-06-10 | 2022-06-10 | 0 | On/ Ahead Schedule | Not Started | 2022-05-19 | 2022-06-01 | Not Started | 2022-08-02 | Not Started
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | E.5014727.06 | 5786005 | ESTS | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  |  | JACKSON | Stockton Assets | 0 | 9652 | 9652 | 1.828 | 0 | 1.828 | [5 empty] | 1 | -299999 | 300000 | 88426.8 | 0 | 211573.2 | On/Under Budget | 1784748.2 | 102.8 | 0 | 102.8 | 0 | 705.8 | 14503.2 | 73217.8 | Project is not in the WP or in 2020 WP | 0 | 73579.5 | -73579.5 | 73579.5 | -73579.5 | 106535.2 | -33823.7 | 506.3 | 102.8 | 102.8 | 102.8 | 53.3 | 0 | 0 | 0 | 0 | 0 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 28510.3 | 398599.9 | 660664.8 | 650780.5 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 1784489.1 | 2021-04-02 | 154939 | BL-B | BL-B 35112976_CWSP - WEST POINT 1101 -LR 13444- PH 1.6_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2021-11-23 | Not Started | 2021-11-25 | 2022-01-05 | Not Started | 2021-12-27 | Not Started | 2022-01-05 | Not Started | 2022-01-06 | 2022-01-06 | Not Started | 2022-01-07 | 2022-02-03 | Not Started | 2021-12-29 | 2022-01-11 | Not Started | 2022-03-10 | Not Started |  |  |  |  | 2022-03-10 | Not Started | 2022-04-28 | Not Started | 2022-04-28 | Not Started | 2022-05-30 | 2022-05-30 | 0 | On/ Ahead Schedule | Not Started | 2022-05-06 | 2022-05-19 | Not Started | 2022-07-20 | Not Started
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | E.5014534.03 | 5786053 | ESTS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 0 | 2875 | 2875 | 0.54451 | 0 | 0.54451 | [5 empty] | 1 | -99999 | 100000 | 5932.5 | 0 | 94067.5 | On/Under Budget | 303918.4 | 11.7 | 0 | 11.7 | 0 | 327.6 | 5426.7 | 178.3 | Project is not in the WP or in 2020 WP | 0 | 231.4 | -231.4 | 231.4 | -231.4 | 110.3 | 34 | 34 | 11.7 | 11.7 | 11.7 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303877.1 | 0 | 0 | 0 | 303877.1
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | E.5014728.02 | 5786012 | ESTS | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 11177.9 | 11177.9 | 2.117 | 0 | 2.117 | [5 empty] | 1 | -249999 | 250000 | 25401.7 | 0 | 224598.3 | On/Under Budget | 3480557.9 | 326.1 | 0 | 326.1 | 0 | 580.3 | 15603.7 | 9217.7 | Project is not in the WP or in 2020 WP | 0 | 14561 | -14561 | 14561 | -14561 | 13913 | -4840.7 | 145.4 | 326.1 | 390.1 | 461.1 | 1579.3 | 2586.7 | 0 | 0 | 0 | 0 | 10645 | 10645 | 10645 | 10645 | 10645 | 13577.7 | 350265.8 | 826320.5 | 970090.3 | 672545.9 | 578870.3 | 10645 | 3475540.5 | 2021-04-02 | 154942 | BL-B | BL-B 35113993_CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2021-12-07 | Not Started | 2021-12-08 | 2022-01-04 | Not Started | 2022-05-02 | Not Started | 2022-05-03 | Not Started | 2022-01-05 | 2022-01-05 | Not Started | 2022-01-06 | 2022-02-02 | Not Started | 2022-04-19 | 2022-04-19 | Not Started | 2022-06-09 | Not Started |  |  |  |  | 2022-06-09 | Not Started | 2022-08-19 | Not Started | 2022-08-19 | Not Started | 2022-09-20 | 2022-09-20 | 0 | On/ Ahead Schedule | Not Started | 2022-08-29 | 2022-09-09 | Not Started | 2022-11-10 | Not Started
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | E.5014728.08 | 5786134 | ESTS | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  |  | JACKSON | Stockton Assets | 0 | 8940 | 8940 | 1.6932 | 0 | 1.6932 | [5 empty] | 1 | -249999 | 250000 | 107168.3 | 0 | 142831.7 | On/Under Budget | 1754191.5 | 61.8 | 0 | 61.8 | 0 | 0 | 22678.1 | 84490.2 | Project is not in the WP or in 2020 WP | 0 | 84644.7 | -84644.7 | 84644.7 | -84644.7 | 137181 | -53303.9 | 613.1 | 61.8 | 61.8 | 30.9 | 0 | 0 | 0 | 0 | 0 | 0 | 11821.8 | 11821.8 | 34590.3 | 404679.9 | 616265.6 | 606381.3 | 11821.8 | 11821.8 | 11821.8 | 11821.8 | 11821.8 | 9429.3 | 1754099 | 2021-04-02 | 154949 | BL-B | BL-B 35113999_CWSP-WEST POINT 1101-OCB&LR12256-PH1.8_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2021-12-07 | Not Started | 2021-12-08 | 2022-01-04 | Not Started | 2022-01-24 | Not Started | 2022-01-25 | Not Started | 2022-01-05 | 2022-01-05 | Not Started | 2022-01-06 | 2022-02-02 | Not Started | 2022-01-25 | 2022-02-07 | Not Started | 2022-03-09 | Not Started |  |  |  |  | 2022-03-09 | Not Started | 2022-05-05 | Not Started | 2022-05-05 | Not Started | 2022-06-06 | 2022-06-06 | 0 | On/ Ahead Schedule | Not Started | 2022-05-13 | 2022-05-26 | Not Started | 2022-07-27 | Not Started
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | E.5014722.04 | 5785931 | ESTS | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 9730 | 9730 | 1.8428 | 0 | 1.8428 | [5 empty] | 83333 | 0 | 83333 | 221696.5 | 0 | -138363.5 | OverRun | 4301324.2 | 135.4 | 0 | 135.4 | 0 | 206.2 | 39758.5 | 181731.8 | Project is not in the WP or in 2020 WP | 0 | 182980.4 | -182980.4 | 182980.4 | -182980.4 | 284859.8 | -104864.3 | 1736.3 | 135.4 | 135.4 | 135.4 | 140.4 | 140.4 | 140.4 | 140.4 | 140.4 | 140.4 | 231086.5 | 232495.1 | 562979.2 | 920784.2 | 926362.3 | 921778.3 | 504725.5 | 0 | 0 | 0 | 0 | 0 | 4300211.1 | 2021-04-02 | 151678 | BL-B1 | BL-B1 35116398_CWSP - MIWUK 1702 - LR 8090 - PH 1.4_08W - Nov.2020 | 2020-11-24 | 2022-03-02 | Not Started | 2023-02-13 | 2023-02-21 | Not Started | 2022-02-02 | Not Started | 2023-02-21 | Not Started | 2023-02-22 | 2023-02-22 | Not Started | 2023-02-23 | 2023-02-24 | Not Started | 2022-02-02 | 2022-02-03 | Not Started | 2023-03-30 | Not Started |  |  |  |  | 2023-03-30 | Not Started | 2023-06-12 | Not Started | 2023-06-15 | Not Started | 2021-07-23 | 2023-07-13 | -720 | Behind Schedule | Not Started | 2023-07-14 | 2023-07-14 | Not Started | 2023-09-07 | Not Started
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | E.5014733.06 | 5785970 | ESTS | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 9970 | 9970 | 1.8883 | 0 | 1.8883 | [5 empty] | 500000 | 0 | 500000 | 193686.6 | 0 | 306313.4 | On/Under Budget | 1688677.3 | 173.1 | 0 | 173.1 | 0 | 202.9 | 162479 | 31004.7 | Project is not in the WP or in 2020 WP | 0 | 31793.1 | -31793.1 | 31793.1 | -31793.1 | 88299 | -58401.4 | 1107.1 | 173.1 | 173.1 | 173.1 | 179.4 | 89.7 | 0 | 0 | 0 | 0 | 4784.8 | 4784.8 | 4784.8 | 4784.8 | 4784.8 | 449219.4 | 1210133.8 | 4784.8 | 0 | 0 | 0 | 0 | 1688062 | 2021-04-02 | 151455 | BL-A | BL-A 35116389_CWSP - MIWUK 1701 - LR 8060 - PH 1.6_08W - Nov. 2020 | 2020-11-12 | 2022-01-05 | Not Started | 2022-01-07 | 2022-04-05 | Not Started | 2022-01-04 | Not Started | 2022-04-05 | Not Started | 2022-04-06 | 2022-04-06 | Not Started | 2022-04-07 | 2022-05-04 | Not Started | 2022-01-05 | 2022-01-18 | Not Started | 2022-06-22 | Not Started |  |  |  |  | 2022-06-22 | Not Started | 2022-07-29 | Not Started | 2022-08-19 | Not Started | 2021-09-13 | 2022-09-20 | -372 | Behind Schedule | Not Started | 2022-09-21 | 2022-10-04 | Not Started | 2022-11-10 | Not Started
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | E.5014722.06 | 5785933 | ESTS | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2022 |  | SH | SONORA | Yosemite Assets | 0 | 9980 | 9980 | 1.8902 | 0 | 1.8902 | [5 empty] | 275000 | 0 | 275000 | 147229.5 | 0 | 127770.5 | On/Under Budget | 3568898.2 | 213.6 | 0 | 213.6 | 0 | 106.8 | 148415.9 | -1293.1 | Request 2021 Budget | 0 | -541.6 | 541.6 | -541.6 | 541.6 | 55748.4 | -57882.2 | 840.7 | 213.6 | 213.6 | 213.6 | 110.7 | 0 | 0 | 0 | 0 | 0 | 305945.4 | 305945.4 | 3110.1 | 3110.1 | 780387.4 | 906568.8 | 906568.8 | 356418 | 306.1 | 0 | 0 | 0 | 3568360.1 | 2021-04-02 | 145959 | BL-A | BL-A 35116440_CWSP - MIWUK 1702 - LR 8090 - PH 1.6_08W - MAR 2022 | 2020-07-26 | 2022-01-05 | Not Started | 2023-01-13 | 2023-02-02 | Not Started | 2022-02-15 | Not Started | 2023-02-02 | Not Started | 2023-02-03 | 2023-02-23 | Not Started | 2023-02-24 | 2023-03-02 | Not Started | 2022-02-16 | 2022-02-22 | Not Started | 2023-05-16 | Not Started |  |  |  |  | 2023-05-16 | Not Started | 2023-07-14 | Not Started | 2023-07-24 | Not Started | 2022-03-04 | 2023-08-23 | -537 | Behind Schedule | Not Started | 2023-08-24 | 2023-08-25 | Not Started | 2023-08-29 | Not Started
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | E.5014776.02 | 5785981 | ESTS | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 12015 | 12015 | 2.2756 | 0 | 2.2756 | [5 empty] | 250000 | 0 | 250000 | 164877.8 | 0 | 85122.2 | On/Under Budget | 6280306.6 | 203.9 | 0 | 203.9 | 0 | 426.4 | 47921.2 | 116530.3 | Project is not in the WP or in 2020 WP | 0 | 118410.4 | -118410.4 | 118410.4 | -118410.4 | 113950.9 | 1633.6 | 945.8 | 203.9 | 203.9 | 203.9 | 211.4 | 211.4 | 211.4 | 211.4 | 211.4 | 211.4 | 3969283.5 | 347126.9 | 1144132.3 | 812824.1 | 5263.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6278630.1 | 2021-04-02 | 151460 | BL-A1 | BL-A1 35116441_CWSP - MIWUK 1702 - LR 38218 - PH 1.2_08W - Nov. 2020 | 2020-11-12 | 2020-12-03 | Completed | 2021-12-13 | 2021-12-24 | Not Started | 2021-12-10 | Not Started | 2021-12-24 | Not Started | 2021-12-27 | 2021-12-27 | Not Started | 2021-12-28 | 2021-12-29 | Not Started | 2022-01-11 | 2022-01-12 | Not Started | 2022-01-18 | Not Started |  |  |  |  | 2022-01-18 | Not Started | 2022-03-04 | Not Started | 2022-03-18 | Not Started | 2021-02-24 | 2022-07-21 | -512 | Behind Schedule | Not Started | 2022-07-22 | 2022-08-04 | Not Started | 2022-09-12 | Not Started
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | E.5015236.02 | 5786018 | ESTS | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 9566 | 9566 | 1.8117 | 0 | 1.8117 | [5 empty] | 1 | -249999 | 250000 | 102488.3 | 0 | 147511.7 | On/Under Budget | 2811219.7 | 0 | 0 | 0 | 0 | 0 | 59248.7 | 43239.7 | Project is not in the WP or in 2020 WP | 0 | 43239.7 | -43239.7 | 43239.7 | -43239.7 | 21636 | 13113 | 8490.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 826839 | 1142562.8 | 827325 | 14493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2811219.8 | 2021-04-02 | 154966 | BL-0 | BL-0 BL-B 35115847_CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2.2_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2022-01-14 | Not Started | 2022-01-17 | 2022-02-11 | Not Started | 2022-04-07 | Not Started | 2022-04-08 | Not Started | 2022-02-14 | 2022-02-14 | Not Started | 2022-02-15 | 2022-03-14 | Not Started | 2022-04-11 | 2022-04-22 | Not Started | 2022-06-28 | Not Started |  |  |  |  | 2022-06-28 | Not Started | 2022-08-24 | Not Started | 2022-09-07 | Not Started | 2022-10-07 | 2022-10-07 | 0 | On/ Ahead Schedule | Not Started | 2022-10-10 | 2022-10-21 | Not Started | 2022-11-29 | Not Started
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | E.5014723.05 | 5785958 | ESTS | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 11880 | 11880 | 2.25 | 0 | 2.25 | [5 empty] | 250000 | 0 | 250000 | 229134.4 | 0 | 20865.6 | On/Under Budget | 3834947.5 | 163.3 | 0 | 163.3 | 0 | 1031.4 | 221098.4 | 7004.7 | Project is not in the WP or in 2020 WP | 0 | 8510.4 | -8510.4 | 8510.4 | -8510.4 | 1709.8 | 1375.7 | 3919.2 | 163.3 | 163.3 | 163.3 | 169.3 | 169.3 | 169.3 | 169.3 | 169.3 | 169.3 | 3055 | 3072.4 | 1510854.5 | 836614.2 | 584597.7 | 516071.6 | 363138.8 | 3332.5 | 3332.5 | 3332.5 | 3332.5 | 2870.9 | 3833605.1 | 2021-04-02 | 145855 | BL-A: | BL-A: 35115049_CWSP - MIWUK 1701 - LR 10600 PH 1.5_08W - Oct. 2021 | 2020-07-24 | 2022-01-10 | Not Started | 2022-01-12 | 2022-01-12 | Not Started | 2020-12-07 | Completed | 2022-01-12 | Not Started | 2022-01-12 | 2022-01-12 | Not Started | 2022-01-13 | 2022-02-09 | Not Started | 2022-01-12 | 2022-01-25 | Not Started | 2022-02-11 | Not Started |  |  |  |  | 2022-02-11 | Not Started | 2022-04-18 | Not Started | 2022-05-09 | Not Started | 2021-10-06 | 2022-06-08 | -245 | Behind Schedule | Not Started | 2022-06-09 | 2022-06-22 | Not Started | 2022-07-29 | Not Started
35117540 | BR-02-01-W (E) CLARK RD & SAN JOSE PARB |  | 5786123 | ESTS | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 | E.5014724.01 | 5786327 | ESTS | 08W | M5HF | Mike Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 8402 | 8402 | 1.5913 | 0 | 1.5913 | [5 empty] | 305556 | 0 | 305556 | 57277.4 | 0 | 248278.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 4246.6 | 10562.8 | 42468 | Project is not in the WP or in 2020 WP | 0 | 42468 | -42468 | 42468 | -42468 | 71319 | -29178.6 | 327.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2022-04-11 | Not Started | 2022-04-13 | 2022-04-26 | Not Started | 2022-04-15 | Not Started | 2022-05-13 | Not Started | 2022-04-27 | 2022-04-27 | Not Started | 2022-04-28 | 2022-07-20 | Not Started | 2022-04-12 | 2022-04-25 | Not Started | 2022-10-11 | Not Started |  |  |  |  | 2022-10-11 | Not Started | 2022-12-30 | Not Started | 2023-01-30 | Not Started | 2023-03-01 | 2023-03-01 | 0 | On/ Ahead Schedule | Not Started | 2023-03-02 | 2023-03-15 | Not Started | 2023-04-21 | Not Started
35117398 | BR-01-12-W (E) MYRTLE WAY, PARB |  | 5786123 | ESTS | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | 2021 |  |  | CHICO | North Valley Assets | [11 empty] | 1 | 1 | 0 | 9090.7 | 0 | -9090.7 | OverRun | 0 | 0 | 0 | 0 | 0 | 8516.3 | 415.7 | 158.6 | Request 2021 Budget | 0 | 158.6 | -158.6 | 158.6 | -158.6 | 54.6 | 52 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35118502 | BR-06-01-W (E) DELIA WAY, PARB |  | 5786123 | ESTS | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | 2021 |  |  | CHICO | North Valley Assets | [11 empty] | 1 | 1 | 0 | 86526.9 | 0 | -86526.9 | OverRun | 0 | 0 | 0 | 0 | 0 | 399.3 | 84617.8 | 1509.8 | Request 2021 Budget | 0 | 1509.8 | -1509.8 | 1509.8 | -1509.8 | 519.4 | 495.2 | 495.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | E.5014720.02 | 5786763 | ESTS | 08W | M5HF | Mike Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 8778 | 8778 | 1.6625 | 0 | 1.6625 | [5 empty] | 100000 | 0 | 100000 | 54914.8 | 0 | 45085.2 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 235.3 | 45714.6 | 8964.8 | Project is not in the WP or in 2020 WP | 0 | 8964.8 | -8964.8 | 8964.8 | -8964.8 | -8433.7 | 18307.1 | -908.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2022-04-15 | Not Started | 2022-04-18 | 2022-04-29 | Not Started | 2022-06-30 | Not Started | 2022-07-01 | Not Started | 2022-05-02 | 2022-05-02 | Not Started | 2022-05-03 | 2022-05-09 | Not Started | 2022-04-15 | 2022-08-18 | Not Started | 2022-08-19 | Not Started |  |  |  |  | 2022-08-19 | Not Started | 2022-09-21 | Not Started | 2022-10-19 | Not Started | 2022-12-20 | 2022-12-20 | 0 | On/ Ahead Schedule | Not Started | 2022-12-21 | 2023-01-03 | Not Started | 2023-02-09 | Not Started
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 | E.5014755.06 | 5786743 | ESTS | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 6429 | 6429 | 1.2176 | 0 | 1.2176 | [5 empty] | 271429 | 0 | 271429 | 47333.1 | 0 | 224095.9 | On/Under Budget | 2375833.5 | 381.9 | 0 | 381.9 | 0 | 0 | 10416.1 | 36917.1 | Project is not in the WP or in 2020 WP | 0 | 40438.2 | -40438.2 | 40438.2 | -40438.2 | 36373.9 | 271.6 | 271.6 | 381.9 | 381.9 | 381.9 | 395.9 | 395.9 | 395.9 | 395.9 | 395.9 | 395.9 | 410.4 | 410.4 | 410.4 | 410.4 | 50410.4 | 410.4 | 500212.8 | 909000 | 911018.9 | 0 | 0 | 0 | 2372694.1 | 2021-04-02 |  |  |  |  | 2022-09-15 | Not Started | 2022-09-19 | 2022-09-20 | Not Started | 2021-06-24 | Not Started | 2022-10-27 | Not Started | 2022-09-21 | 2022-09-21 | Not Started | 2022-09-22 | 2022-09-23 | Not Started | 2021-04-06 | 2021-06-25 | Not Started | 2022-11-08 | Not Started |  |  |  |  | 2022-11-08 | Not Started | 2022-12-02 | Not Started | 2022-12-20 | Not Started | 2023-03-14 | 2023-03-14 | 0 | On/ Ahead Schedule | Not Started | 2023-03-15 | 2023-03-28 | Not Started | 2023-05-04 | Not Started
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | E.5015030.02 | 5786744 | ESTS | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 6113 | 6113 | 1.1578 | 0 | 1.1578 | [5 empty] | 250000 | 0 | 250000 | 67369.3 | 0 | 182630.7 | On/Under Budget | 2215497.7 | 381.2 | 0 | 381.2 | 0 | 0 | 13092 | 54277.2 | Project is not in the WP or in 2020 WP | 0 | 57792 | -57792 | 57792 | -57792 | 87286.2 | -33394.4 | 385.4 | 381.2 | 381.2 | 381.2 | 395.2 | 395.2 | 395.2 | 395.2 | 395.2 | 395.2 | 409.7 | 409.7 | 2941.1 | 425.2 | 425.2 | 425.2 | 500440.5 | 852440.5 | 852440.5 | 440.5 | 440.5 | 440.5 | 2211679.1 | 2021-04-02 | 155009 | BL-A | BL-A 35129648_CWSP - ORO FINO 1101 - LR2022 PH 3.2._08W - Jan. 2021 | 2021-01-25 | 2021-12-29 | Not Started | 2021-12-31 | 2022-01-13 | Not Started | 2021-04-29 | Not Started | 2022-02-09 | Not Started | 2022-01-14 | 2022-01-14 | Not Started | 2022-01-17 | 2022-02-04 | Not Started | 2021-04-26 | 2021-07-16 | Not Started | 2022-03-21 | Not Started |  |  |  |  | 2022-03-21 | Not Started | 2022-06-07 | Not Started | 2022-07-06 | Not Started | 2022-08-05 | 2022-08-05 | 0 | On/ Ahead Schedule | Not Started | 2022-08-08 | 2022-08-19 | Not Started | 2022-09-27 | Not Started
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | 5530164 | ESTS | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 | 2020 | SH | CLRLAKE | Humboldt Division Assets | 0 | 7273 | 7273 | 1.3775 | 0 | 1.3775 | 7437 | 0 | 1.4085 | 0 | GC | 80000 | 0 | 80000 | 68952.9 | 0 | 11047.1 | On/Under Budget | 10764.7 | 3588.2 | 934.8 | 2653.4 | 0 | 212.4 | 5661.5 | 64013.8 | Request 2021 Budget | 0 | 77431.8 | -77431.8 | 77431.8 | -77431.8 | 5214.4 | 28692.8 | 29171.8 | 3588.2 | 3588.2 | 3588.2 | 3588.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156048 | BL-A | BL-A 35137593_CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07_08W - Feb. 2021 | 2021-02-17 | 2021-04-15 | Not Started | 2021-04-16 | 2021-04-29 | Not Started | 2021-08-16 | Not Started | 2021-08-17 | Not Started | 2021-04-30 | 2021-04-30 | Not Started | 2021-05-03 | 2021-05-21 | Not Started | 2021-09-14 | 2021-09-24 | Not Started | 2021-10-14 | Not Started |  |  |  |  | 2021-10-14 | Not Started | 2021-12-20 | Not Started | 2022-01-18 | Not Started | 2022-03-21 | 2022-03-21 | 0 | On/ Ahead Schedule | Not Started | 2022-03-22 | 2022-04-04 | Not Started | 2022-05-11 | Not Started
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | E.5014724.09 | 5786782 | ESTS | 08W | M5HF | Mike Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2022 |  | CHICO | North Valley Assets | 0 | 7516 | 7516 | 1.4235 | 0 | 1.4235 | [5 empty] | 55556 | -194444 | 250000 | 53092.7 | 0 | 196907.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 9177.1 | 43915.5 | Project is not in the WP or in 2020 WP | 0 | 43915.5 | -43915.5 | 43915.5 | -43915.5 | 73593.9 | -29982 | 303.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2022-03-31 | Not Started | 2022-04-04 | 2022-04-15 | Not Started | 2022-05-26 | Not Started | 2022-05-27 | Not Started | 2022-04-18 | 2022-04-18 | Not Started | 2022-04-19 | 2022-08-22 | Not Started | 2022-03-25 | 2022-04-07 | Not Started | 2022-09-30 | Not Started |  |  |  |  | 2022-09-30 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-02-15 | 2023-02-15 | 0 | On/ Ahead Schedule | Not Started | 2023-02-16 | 2023-03-01 | Not Started | 2023-04-07 | Not Started
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 | 5786480 | ESTS | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | GRSSVLLY | Sierra Assets | 12455 | 1245 | 13700 | 2.5947 | 0 | 2.5947 | [5 empty] | 500000 | 0 | 500000 | 179078.9 | 0 | 320921.1 | On/Under Budget | 3494.6 | 524.3 | 0 | 524.3 | 0 | 20886.7 | 123586.8 | 34605.4 | Project is not in the WP or in 2020 WP | 0 | 38624.1 | -38624.1 | 38624.1 | -38624.1 | 32554.4 | 1025.5 | 1025.5 | 524.3 | 524.3 | 524.3 | 543.5 | 543.5 | 543.5 | 543.5 | 271.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2022-01-28 | Not Started | 2022-02-10 | 2022-02-16 | Not Started | 2022-02-09 | Not Started | 2022-03-25 | Not Started | 2022-01-31 | 2022-01-31 | Not Started | 2022-02-01 | 2022-02-21 | Not Started | 2022-02-10 | 2022-02-23 | Not Started | 2022-04-26 | Not Started |  |  |  |  | 2022-04-26 | Not Started | 2022-08-08 | Not Started | 2022-09-06 | Not Started | 2022-11-07 | 2022-11-07 | 0 | On/ Ahead Schedule | Not Started | 2022-11-08 | 2022-11-21 | Not Started | 2022-12-28 | Not Started
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | 5530173 | ESTS | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 | 2025 | SH | AUBURN | Sierra Assets | 0 | 8553.6 | 8553.6 | 1.62 | 0 | 1.62 |  |  |  |  | Contract | 100000 | 0 | 100000 | 58947.8 | 0 | 41052.2 | On/Under Budget | 1782509 | 40878.7 | 226.3 | 40652.4 | 6886.9 | 8874.5 | 31345.8 | 12066.9 | Request 2021 Budget | 0 | 1835228.3 | -1835228.3 | 1835228.3 | -1835228.3 | 10030.5 | 2327.7 | -517.6 | 40878.7 | 50840.5 | 364247.6 | 580267 | 607467.9 | 156802.6 | 15848 | 4690.3 | 2345.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 130724 | WSHP | WSHP 190307 - 35026643_DIAMOND SPRINGS 1105_08W - B1 | 2019-04-15 | 2022-06-23 | Not Started | 2022-06-24 | 2022-07-07 | Not Started | 2022-07-01 | Not Started | 2022-07-07 | Not Started | 2022-07-22 | 2022-07-22 | Not Started |  |  |  | 2022-07-07 | 2022-07-20 | Not Started | 2022-07-26 | Not Started |  |  |  |  | 2022-07-26 | Not Started |  |  | 2022-08-24 | Not Started | 2019-08-15 | 2022-11-18 | -1191 | Behind Schedule | Not Started | 2022-11-18 | 2022-12-06 | Not Started | 2023-01-10 | Not Started
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | E.5014535.01 | 5780842 | ESTS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 3643 | 0 | 3643 | 0.68996 | 0 | 0.68996 | [5 empty] | 10000 | -50000 | 60000 | 45415.6 | 0 | 14584.4 | On/Under Budget | 3454952.6 | 0 | 0 | 0 | 19599.1 | 16376 | 8573.2 | 867.3 | Project is not in the WP or in 2020 WP | 0 | 867.3 | -867.3 | 867.3 | -867.3 | 347.5 | 259.9 | 259.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3454952.6 | 0 | 0 | 0 | 3454952.6
35040505 | CWSP - BIG BASIN 1101 - LR 10296 - PH1 |  | 5530159 | ESTS | 08W | E2MA | Erik Madsen |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | 5530166 | ESTS | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | Not in the WP | 2022 |  | SNLUISOB | Los Padres Assets | 0 | 3100 | 3100 | 0.58712 | 0 | 0.58712 | [5 empty] | 150000 | 0 | 150000 | 122686.2 | 0 | 27313.8 | On/Under Budget | 2160776.1 | 1443.9 | 0 | 1443.9 | 22865.3 | 62935.5 | 30842 | 3911 | Project is not in the WP or in 2020 WP | 0 | 16906.1 | -16906.1 | 16906.1 | -16906.1 | 2074.6 | 1379.6 | 456.8 | 1443.9 | 1443.9 | 1443.9 | 1443.9 | 1443.9 | 1443.9 | 1443.9 | 1443.9 | 1443.9 | 3088.8 | 3088.8 | 323992.9 | 124208.3 | 578406.3 | 558219.7 | 558219.7 | 0 | 0 | 0 | 0 | 0 | 2149224.5 | 2021-04-02 | 147005 | BL-A | BL-A 31291639_FH 1101 O'CONNOR WY RECOND 12 SPANS, SLO - Aug 2021 | 2020-08-11 | 2022-09-05 | Not Started |  |  | Not Started |  |  | 2022-11-15 | Not Started | 2022-11-16 | 2022-11-16 | Not Started |  |  |  | 2022-10-11 | 2022-10-31 | Not Started | 2022-11-23 | Not Started |  |  |  |  | 2022-11-23 | Not Started |  |  | 2022-12-16 | Not Started | 2021-01-25 | 2023-01-06 | -711 | Behind Schedule | Not Started | 2023-01-06 | 2023-01-23 | Not Started | 2023-06-14 | Not Started
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | E.5014728.01 | 5784647 | ESTS | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 11665.4 | 11665.4 | 2.2094 | 0 | 2.2094 | [5 empty] | 40000 | -710000 | 750000 | 57771.7 | 0 | 692228.3 | On/Under Budget | 3388117.7 | 219.5 | 0 | 219.5 | 3457 | 16449.9 | 15167.5 | 22697.4 | Project is not in the WP or in 2020 WP | 0 | 24380.1 | -24380.1 | 24380.1 | -24380.1 | 38571.8 | -16204.9 | 330.5 | 219.5 | 219.5 | 219.5 | 227.6 | 227.6 | 227.6 | 227.6 | 113.8 | 0 | 7398.6 | 7398.6 | 7398.6 | 7398.6 | 8913.7 | 14913.7 | 347752.8 | 837711.5 | 921157.9 | 616904.9 | 582020.6 | 27685.1 | 3386654.6 | 2021-04-02 | 154941 | BL-B | BL-B 35043421_CWSP - WEST POINT 1101-OCB&LR12256-PH 1.1_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2022-01-10 | Not Started | 2022-01-11 | 2022-01-31 | Not Started | 2022-05-12 | Not Started | 2022-05-13 | Not Started | 2022-06-28 | 2022-07-04 | Not Started | 2022-07-05 | 2022-08-01 | Not Started | 2022-05-13 | 2022-05-13 | Not Started | 2022-08-02 | Not Started |  |  |  |  | 2022-08-02 | Not Started |  |  | 2022-10-24 | Not Started | 2022-11-23 | 2022-11-23 | 0 | On/ Ahead Schedule | Not Started | 2022-11-24 | 2022-12-07 | Not Started | 2023-01-27 | Not Started
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | E.5014727.01 | 5785229 | ESTS | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  |  | JACKSON | Stockton Assets | 0 | 11037 | 11037 | 2.0903 | 0 | 2.0903 | [5 empty] | 500000 | 200000 | 300000 | 139465.4 | 0 | 160534.6 | On/Under Budget | 1954067 | 195.1 | 0 | 195.1 | 1645.5 | 11906.6 | 30704.6 | 95208.7 | Project is not in the WP or in 2020 WP | 0 | 95891.9 | -95891.9 | 95891.9 | -95891.9 | 131708.7 | -37298.6 | 798.6 | 195.1 | 193.8 | 193.8 | 100.5 | 0 | 0 | 0 | 0 | 0 | 5741.7 | 8741.7 | 5741.7 | 408484.1 | 876438.2 | 613980.9 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 1953578.5 | 2021-04-02 | 154934 | BL-B | BL-B 35043422_CWSP - WEST POINT 1101 -LR 13444- PH 1.1_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2021-11-29 | Not Started | 2021-12-01 | 2022-01-11 | Not Started | 2022-01-07 | Not Started | 2022-01-11 | Not Started | 2022-01-12 | 2022-01-12 | Not Started | 2022-01-13 | 2022-02-09 | Not Started | 2022-01-31 | 2022-02-11 | Not Started | 2022-03-03 | Not Started |  |  |  |  | 2022-03-03 | Not Started |  |  | 2022-04-15 | Not Started | 2022-05-17 | 2022-05-17 | 0 | On/ Ahead Schedule | Not Started | 2022-05-18 | 2022-05-31 | Not Started | 2022-07-07 | Not Started
35051472 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3 |  | 5793703 | ESTS | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  | SH | STCRUZ |  | 0 | 38438.4 | 38438.4 | 7.28 | 0 | 7.28 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | ESTS | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | PLCRVLLE | Sierra Assets | 3135 | 3779 | 6914 | 1.3095 | 0 | 1.3095 | [5 empty] | 600000 | 0 | 600000 | 320609.4 | 0 | 279390.6 | On/Under Budget | 1917.5 | 417.6 | 0 | 417.6 | 4921.4 | 31408.1 | 285613.9 | -1334.1 | Project is not in the WP or in 2020 WP | 0 | 1001 | -1001 | 1001 | -1001 | -8267.3 | 3069.1 | 3864.1 | 417.6 | 417.6 | 417.6 | 432.9 | 432.9 | 216.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158111 | BL-A1 | BL-A1_35057010_CWSP - El Dorado 2101 - 19752 - Ph 2.1_08W_Mar.2021 | 2021-03-30 | 2022-02-03 | Not Started | 2022-04-01 | 2022-04-07 | Not Started | 2022-03-31 | Not Started | 2022-04-28 | Not Started | 2022-02-04 | 2022-02-04 | Not Started | 2022-02-07 | 2022-02-25 | Not Started | 2020-07-07 | 2020-07-17 | Completed | 2022-06-20 | Not Started |  |  |  |  | 2022-06-20 | Not Started | 2022-09-30 | Not Started | 2022-10-31 | Not Started | 2022-12-30 | 2022-12-30 | 0 | On/ Ahead Schedule | Not Started | 2023-01-02 | 2023-01-13 | Not Started | 2023-02-21 | Not Started
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | 5530173 | ESTS | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | AUBURN | Sierra Assets | 3309 | 0 | 3309 | 0.6267 | 0 | 0.6267 | [5 empty] | 245000 | 0 | 245000 | 119289 | 49035 | 174746 | On/Under Budget | 5767935.9 | 253 | -43665.8 | 43918.8 | 228.6 | 12223.7 | 99460.4 | -36289.5 | Project is not in the WP or in 2020 WP | 0 | 9709.1 | -9709.1 | 9709.1 | -9709.1 | 3833.1 | 1701.7 | 1841.5 | 253 | 253 | 253 | 262.3 | 262.3 | 262.3 | 262.3 | 262.3 | 262.3 | 5395223.7 | 33032.2 | 33032.2 | 33032.2 | 33032.2 | 33032.2 | 34245.2 | 34245.2 | 34245.2 | 34245.2 | 34245.2 | 34245.2 | 5765855.9 | 2021-04-02 |  |  |  |  | 2021-05-28 | Not Started | 2021-12-03 | 2021-12-09 | Not Started | 2021-06-25 | Not Started | 2021-12-30 | Not Started | 2021-12-03 | 2021-12-03 | Not Started | 2021-12-06 | 2021-12-24 | Not Started | 2021-12-03 | 2021-12-23 | Not Started | 2022-01-24 | Not Started |  |  |  |  | 2022-01-24 | Not Started | 2022-06-03 | Not Started | 2022-07-04 | Not Started | 2022-09-02 | 2022-09-02 | 0 | On/ Ahead Schedule | Not Started | 2022-09-05 | 2022-09-16 | Not Started | 2022-10-25 | Not Started
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | ESTS | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | PLCRVLLE | Sierra Assets | 0 | 5981 | 5981 | 1.1328 | 0 | 1.1328 | [5 empty] | 166667 | 0 | 166667 | 50474.2 | 0 | 116192.8 | On/Under Budget | 1109.8 | 144.1 | 0 | 144.1 | 9079.7 | 12375.8 | 4014.4 | 25004.3 | Project is not in the WP or in 2020 WP | 0 | 26258.3 | -26258.3 | 26258.3 | -26258.3 | 34408.1 | -13457.4 | 4053.6 | 144.1 | 144.1 | 144.1 | 149.4 | 149.4 | 149.4 | 149.4 | 149.4 | 74.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 154998 | BL-A | BL-A 35056387_CWSP - Placerville 2106 - LR 1104 - Ph 1_08W - Jan. 2021 | 2021-01-25 | 2022-03-28 | Not Started | 2022-04-01 | 2022-04-07 | Not Started | 2022-03-31 | Not Started | 2022-05-23 | Not Started | 2022-03-29 | 2022-03-29 | Not Started | 2022-03-30 | 2022-04-19 | Not Started | 2022-04-01 | 2022-04-14 | Not Started | 2022-07-20 | Not Started |  |  |  |  | 2022-07-20 | Not Started | 2022-11-01 | Not Started | 2022-11-30 | Not Started | 2023-01-31 | 2023-01-31 | 0 | On/ Ahead Schedule | Not Started | 2023-02-01 | 2023-02-14 | Not Started | 2023-03-23 | Not Started
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 | E.5014755.01 | 5785243 | ESTS | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 8723 | 8723 | 1.6521 | 0 | 1.6521 | [5 empty] | 271429 | 0 | 271429 | 11103.7 | 0 | 260325.3 | On/Under Budget | 5776935 | 544.6 | 0 | 544.6 | 0 | 7347.2 | 4104.1 | -347.7 | Project is not in the WP or in 2020 WP | 0 | 2133 | -2133 | 2133 | -2133 | -474.7 | 63.5 | 63.5 | 544.6 | 544.6 | 544.6 | 564.6 | 282.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1758333 | 1758333 | 1758333 | 0 | 0 | 0 | 0 | 5774999 | 2021-04-02 |  |  |  |  | 2022-09-22 | Not Started | 2022-09-26 | 2022-10-07 | Not Started | 2022-10-21 | Not Started | 2022-10-24 | Not Started | 2022-10-10 | 2022-10-10 | Not Started | 2022-10-11 | 2022-10-31 | Not Started | 2022-09-23 | 2022-10-27 | Not Started | 2022-11-15 | Not Started |  |  |  |  | 2022-11-15 | Not Started | 2022-12-13 | Not Started | 2022-12-23 | Not Started | 2023-03-17 | 2023-03-17 | 0 | On/ Ahead Schedule | Not Started | 2023-03-20 | 2023-03-31 | Not Started | 2023-05-09 | Not Started
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | E.5015029.03 | 5785159 | ESTS | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2022 | 2022 | SH | LAKEPORT | Humboldt Division Assets | 3000 | 200 | 3200 | 0.60606 | 0 | 0.60606 | 2741 | 0 | 0.51913 | 0 |  | 85000 | 0 | 85000 | 75656 | 0 | 9344 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 36650.6 | 36553.7 | 2451.6 | Request 2021 Budget | 0 | 2451.6 | -2451.6 | 2451.6 | -2451.6 | 529.2 | 464.4 | 1458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145841 | BL-A: | BL-A: 35094389_CWSP - KONOCTI 1102-LR 532 PH 2_08W - May 2021 | 2020-07-24 | 2021-06-29 | Not Started | 2021-07-01 | 2021-07-14 | Not Started | 2021-11-15 | Not Started | 2021-11-16 | Not Started | 2021-07-15 | 2022-01-31 | Not Started | 2022-02-01 | 2022-02-14 | Not Started | 2022-01-03 | 2022-01-31 | Not Started | 2022-02-15 | Not Started |  |  |  |  | 2022-02-15 | Not Started | 2022-03-10 | Not Started | 2022-03-15 | Not Started | 2021-05-06 | 2022-05-13 | -372 | Behind Schedule | Not Started | 2022-05-16 | 2022-05-27 | Not Started | 2022-07-05 | Not Started
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | ESTS | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | PLCRVLLE | Sierra Assets | 1664 | 12975 | 14639 | 2.7725 | 0 | 2.7725 | [5 empty] | 900000 | 0 | 900000 | 599870.5 | 0 | 300129.5 | On/Under Budget | 3044.1 | 856.3 | 0 | 856.3 | 0 | 15178.2 | 543929.5 | 40762.7 | Project is not in the WP or in 2020 WP | 0 | 44663.2 | -44663.2 | 44663.2 | -44663.2 | 33624.9 | 3432.1 | 3705.7 | 856.3 | 856.3 | 856.3 | 887.7 | 443.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158113 | BL-A_ | BL-A_35109546_CWSP - El Dorado 2101 - 19752 - Ph 2.3_08W_Mar.2021 | 2021-03-30 | 2022-01-27 | Not Started | 2022-02-25 | 2022-03-03 | Not Started | 2022-02-24 | Not Started | 2022-03-24 | Not Started | 2022-01-28 | 2022-01-28 | Not Started | 2022-01-31 | 2022-02-18 | Not Started | 2020-05-21 | 2020-06-19 | Completed | 2022-06-22 | Not Started |  |  |  |  | 2022-06-22 | Not Started | 2022-10-04 | Not Started | 2022-11-02 | Not Started | 2023-01-03 | 2022-12-30 | 4 | On/ Ahead Schedule | Not Started | 2023-01-02 | 2023-01-13 | Not Started | 2023-02-21 | Not Started
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 | 5785513 | ESTS | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | PLCRVLLE | Sierra Assets | 1279 | 12807 | 14086 | 2.6678 | 0 | 2.6678 | [5 empty] | 900000 | 0 | 900000 | 617044.3 | 148634.7 | 431590.4 | On/Under Budget | 1724.3 | 684.7 | 0 | 684.7 | 0 | 21750.3 | 507594 | 87700.1 | Project is not in the WP or in 2020 WP | 0 | 90109.1 | -90109.1 | 90109.1 | -90109.1 | 80634.1 | 3533 | 3533 | 684.7 | 684.7 | 684.7 | 354.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158112 | BL-A1 | BL-A1_35109541_CWSP - El Dorado 2101 - 19752 - Ph 1.3_08W_Mar.2021 | 2021-03-30 | 2021-12-02 | Not Started | 2022-01-28 | 2022-02-03 | Not Started | 2022-01-27 | Not Started | 2022-02-24 | Not Started | 2021-12-03 | 2021-12-03 | Not Started | 2021-12-06 | 2021-12-24 | Not Started | 2020-05-04 | 2020-05-20 | Completed | 2022-07-01 | Not Started |  |  |  |  | 2022-07-01 | Not Started | 2022-10-13 | Not Started | 2022-11-11 | Not Started | 2022-12-30 | 2022-12-30 | 0 | On/ Ahead Schedule | Not Started | 2023-01-02 | 2023-01-13 | Not Started | 2023-02-21 | Not Started
35110556 | BR-04-12-W (E) SUBSTATION/PATH PARB |  | 5786123 | ESTS | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2021 |  |  | CHICO | North Valley Assets | [10 empty] | Contract | 1 | 1 | 0 | 40830.2 | 0 | -40830.2 | OverRun | 0 | 0 | -60.6 | 60.6 | 0 | 31152.6 | 8740.9 | 876 | Request 2021 Budget | 0 | 936.6 | -936.6 | 936.6 | -936.6 | 344.5 | 235.6 | 356.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | E.5015029.09 | 5785165 | ESTS | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2022 | 2022 | SH | LAKEPORT | Humboldt Division Assets | 6245 | 1055 | 7300 | 1.3826 | 0 | 1.3826 | [5 empty] | 75000 | 0 | 75000 | 58647.8 | 0 | 16352.2 | On/Under Budget | 0 | 166.3 | 0 | 166.3 | 0 | 50869.1 | 4494.7 | 3284 | Request 2021 Budget | 0 | 3450.3 | -3450.3 | 3450.3 | -3450.3 | 1376.2 | 547.1 | 1360.7 | 166.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145839 | BL-A: | BL-A: 35094395_CWSP - KONOCTI 1102-LR 532 PH 8_08W - June 2021 | 2020-07-24 | 2021-06-15 | Not Started | 2021-06-17 | 2021-06-18 | Not Started | 2021-10-15 | Not Started | 2021-10-18 | Not Started | 2021-06-21 | 2022-01-03 | Not Started | 2022-01-04 | 2022-01-05 | Not Started | 2022-01-03 | 2022-01-03 | Not Started | 2022-02-03 | Not Started |  |  |  |  | 2022-02-03 | Not Started | 2022-04-27 | Not Started | 2022-05-02 | Not Started | 2021-06-03 | 2022-06-30 | -392 | Behind Schedule | Not Started | 2022-07-01 | 2022-07-14 | Not Started | 2022-08-22 | Not Started
35085680 | SILVERADO 2105 WIRE DOWN - PH 3 | E.5014317.04 | 5784869 | ESTS | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | Not in the WP |  |  | NAPA | North Bay Assets | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2298281.08 | 2288281.08 | 10000 | 85226.8 | 0 | -75226.8 | OverRun | 0 | 0 | 0 | 0 | 0 | 85677.5 | -1924.2 | 1473.5 | Project is not in the WP or in 2020 WP | 0 | 1473.5 | -1473.5 | 1473.5 | -1473.5 | 507.1 | 483.2 | 483.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 | E.5015550.01 | 5783061 | ESTS | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2023 | SH | GRSSVLLY | Sierra Assets | 5545 | 0 | 5545 | 1.0502 | 0 | 1.0502 | [5 empty] | 71432 | 0 | 71432 | 51111.8 | 0 | 20320.2 | On/Under Budget | 327.4 | 71.3 | 0 | 71.3 | 411.1 | 7646.6 | 4750.7 | 38303.5 | Project is not in the WP or in 2020 WP | 0 | 38702.2 | -38702.2 | 38702.2 | -38702.2 | 16342.5 | 169.1 | 21791.9 | 71.3 | 71.3 | 71.3 | 73.9 | 73.9 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2022-12-13 | Not Started | 2023-01-24 | 2023-01-30 | Not Started | 2023-01-23 | Not Started | 2023-02-20 | Not Started | 2022-12-13 | 2022-12-13 | Not Started | 2022-12-14 | 2023-01-03 | Not Started | 2023-01-24 | 2023-02-06 | Not Started | 2023-03-15 | Not Started |  |  |  |  | 2023-03-15 | Not Started | 2023-06-27 | Not Started | 2023-07-26 | Not Started | 2023-09-26 | 2023-09-26 | 0 | On/ Ahead Schedule | Not Started | 2023-09-27 | 2023-10-10 | Not Started | 2023-11-16 | Not Started
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | E.5015549.01 | 5783060 | ESTS | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 2698 | 3009 | 5707 | 1.0809 | 0 | 1.0809 | [5 empty] | 250000 | 0 | 250000 | 133345.7 | 0 | 116654.3 | On/Under Budget | 2035140 | 194.5 | 0 | 194.5 | 1524.6 | 23533.8 | 10833.5 | 97453.8 | Project is not in the WP or in 2020 WP | 0 | 98743.2 | -98743.2 | 98743.2 | -98743.2 | 88153.8 | 1185.1 | 8114.9 | 194.5 | 194.5 | 194.5 | 201.7 | 201.7 | 201.7 | 100.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 678015 | 678015 | 678015 | 0 | 0 | 0 | 0 | 2034045
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | E.5014319.01 | 5782536 | ESTS | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 7868 | 0 | 7868 | 1.4902 | 0 | 1.4902 | [5 empty] | 350000 | 0 | 350000 | 218534.9 | 642.1 | 132107.2 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 43093.3 | 121749.7 | 53691.9 | Project is not in the WP or in 2020 WP | 0 | 53691.9 | -53691.9 | 53691.9 | -53691.9 | 1120.4 | 51318.2 | 1253.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 | E.5014317.01 | 5782595 | FICL | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | Not in the WP | 2019 | SH | NAPA | North Bay Assets | 0 | 3684 | 3684 | 0.69773 | 0.69773 | 0 | [5 empty] | 2410000 | -0.1 | 2410000.1 | 2113454 | 0 | 296546.1 | On/Under Budget | 103224.1 | 12675.5 | 0 | 12675.5 | 0 | 2117114.6 | -50960.7 | 47300.1 | Project is not in the WP or in 2020 WP | 0 | 163200 | -163200 | 163200 | -163200 | 0 | 0 | 47300.1 | 12675.5 | 12675.5 | 12675.5 | 12978.9 | 12978.9 | 12978.9 | 12978.9 | 12978.9 | 12978.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 128627 | WSHP | WSHP 190307 - 35072146_SILVERADO 2105 WIRE DOWN_08W - B1 | 2019-03-07 | 2019-06-12 | Completed |  |  | Completed | 2019-08-16 | Completed | 2019-06-26 | Completed | 2019-07-27 | 2019-07-27 | Completed | 2019-08-20 | 2019-08-21 | Completed | 2019-08-19 | 2019-08-20 | Completed | 2019-11-15 | Completed |  |  |  |  | 2019-11-15 | Completed |  |  | 2019-12-17 | Completed | 2020-01-07 | 2019-12-17 | 21 | On/ Ahead Schedule | Completed | 2019-12-20 | 2019-12-23 | Completed | 2021-05-24 | Not Started
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | E.5015567.01 | 5783072 | FICL | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2020 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 7099 | 7099 | 1.3445 | 1.3445 | 0 | 7662 | 7702 | 1.4511 | 1.4587 | GC | 6076529 | 1899185.2 | 4177343.8 | 2349370.2 | 0 | 1827973.6 | On/Under Budget | -212915 | 0 | -250 | 250 | 1472.8 | 11638.8 | 2320915.6 | 15092.9 | Project is not in the WP or in 2020 WP | 36100 | 15342.9 | 20757.1 | -197572.1 | 233672.1 | 14659.4 | 1440.4 | -756.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -212915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145886 | BL-0 | BL-0 35061213_CWSP - Brunkswick 1103 LR50070 ZONE-PH3.1_08W - SEPT 2020 | 2020-07-26 | 2020-02-14 | Completed | 2020-05-01 | 2020-05-01 | Completed | 2020-03-06 | Completed | 2020-05-01 | Completed | 2020-05-01 | 2020-05-01 | Completed | 2020-05-18 | 2020-05-22 | Completed | 2020-03-10 | 2020-05-29 | Completed | 2020-05-18 | Completed |  |  |  |  | 2020-05-18 | Completed | 2020-08-05 | Completed | 2020-08-14 | Completed | 2020-09-30 | 2020-08-14 | 47 | On/ Ahead Schedule | Completed | 2020-08-14 | 2020-08-20 | Completed | 2020-10-26 | Completed
35064793 | LP RECONDUCTOR, CABRILLO 1104 S006CC102 |  | 5783065 | FICL | 08W | B1GQ | Brian Gallo |  |  |  |  | Not in the WP | 2019 | SH | SNLUISOB |  | 0 | 12142 | 12142 | 2.2996 | 2.2996 | 0 | [19 empty] | 34327.2 | Project is not in the WP or in 2020 WP | 0 | 34327.2 | -34327.2 | 0 | 0 | [25 empty] | 2020-10-30 | 128543 | WSHP | WSHP 190307 - 35064793_Cabrillo 1104 Reconductoring - B1 | 2019-03-07 | 2019-02-25 | Completed |  |  | Completed | 2019-08-23 | Completed | 2019-05-29 | Completed | 2019-05-31 | 2019-06-18 | Completed |  |  |  | 2019-06-17 | 2019-07-05 | Completed | 2019-07-12 | Completed |  |  |  |  | 2019-08-05 | Completed |  |  | 2019-08-26 | Completed | 2019-10-04 | 2019-08-26 | 39 | On/ Ahead Schedule | Completed |  |  |  | 2020-10-30 | Not Started
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H | E.5014772.08 | 5784866 | FICL | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2020 | 2019 | SH | NAPA | North Bay Assets | 0 | 3752 | 3752 | 0.71061 | 0.71061 | 0 | 3442 | 3442 | 0.65189 | 0.65189 | Contract | 1350000 | -0.2 | 1350000.2 | 1281090.8 | 0 | 68909.4 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 1089162.2 | 157358.8 | 34569.8 | Project is not in the WP or in 2020 WP | 0 | 34569.8 | -34569.8 | 34569.8 | -34569.8 | 0 | 0 | 34569.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2019-07-09 | Completed | 2019-08-16 | 2019-08-29 | Completed | 2019-08-08 | Completed | 2019-08-14 | Completed | 2019-09-03 | 2019-09-04 | Completed | 2019-08-12 | 2019-08-14 | Completed | 2019-08-12 | 2019-08-16 | Completed | 2019-10-07 | Completed |  |  |  |  | 2019-10-07 | Completed |  |  | 2020-01-17 | Completed | 2020-06-02 | 2020-01-17 | 137 | On/ Ahead Schedule | Completed | 2020-01-27 | 2020-01-31 | Completed | 2021-05-24 | Not Started
35085538 | SILVERADO 2105 WIRE DOWN - PH 1 | E.5014317.02 | 5784867 | FICL | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2020 | 2019 | SH | NAPA | North Bay Assets | 0 | 10413 | 10413 | 1.9722 | 1.9722 | 0 | 9520 | 10413 | 1.803 | 1.9722 | Contract | 2950000 | -0.4 | 2950000.4 | 2775454.4 | 0 | 174546 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 1453170.1 | 1322284.3 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-12-17 |  |  |  |  | 2019-08-01 | Completed | 2019-08-20 | 2019-08-21 | Completed | 2019-08-16 | Completed | 2019-08-16 | Completed | 2019-08-22 | 2019-08-23 | Completed | 2019-10-01 | 2019-10-01 | Completed | 2019-09-20 | 2019-09-20 | Completed | 2019-10-07 | Completed |  |  |  |  | 2019-10-07 | Completed | 2019-10-25 | Completed | 2020-05-18 | Completed | 2020-06-02 | 2020-05-18 | 15 | On/ Ahead Schedule | Completed | 2020-05-25 | 2020-05-29 | Completed | 2021-01-26 | Completed
35085393 | CWSP - SILVERADO 2104 - LR722 PH 1B | E.5014772.02 | 5784860 | FICL | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | Not in the WP |  | SH | NAPA | North Bay Assets | 0 | 1871 | 1871 | 0.35436 | 0.35436 | 0 | [5 empty] | 1300000 | 0.5 | 1299999.5 | 1239931.9 | 0 | 60067.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 1516898.2 | -276966.3 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35085532 | CWSP - SILVERADO 2104 - LR722 PH 1C | E.5014772.03 | 5784861 | FICL | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | Not in the WP | 2019 | SH | NAPA | North Bay Assets | 0 | 5948 | 5948 | 1.1265 | 1.1265 | 0 | [5 empty] | 2100000 | 0.2 | 2099999.8 | 2033156.3 | 0 | 66843.5 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 1405402.1 | 627754.2 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2019-06-10 | Completed |  |  | Completed | 2019-07-15 | Completed | 2019-09-06 | Completed | 2019-08-19 | 2019-08-20 | Completed | 2019-09-09 | 2019-09-09 | Completed | 2019-07-08 | 2019-09-13 | Completed | 2019-09-13 | Completed |  |  |  |  | 2019-09-06 | Completed | 2019-10-17 | Completed | 2020-01-15 | Completed | 2020-01-15 | 2020-01-15 | 0 | On/ Ahead Schedule | Completed | 2020-01-20 | 2020-01-24 | Completed | 2021-04-02 | Not Started
35085533 | CWSP - SILVERADO 2104 - LR722 PH 1D | E.5014772.04 | 5784862 | FICL | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | Not in the WP | 2019 | SH | NAPA | North Bay Assets | 0 | 5365 | 5365 | 1.0161 | 1.0161 | 0 | [5 empty] | 2100000 | 0 | 2100000 | 2014171.4 | 0 | 85828.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 1791769.8 | 222401.6 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2019-09-10 | Completed |  |  | Completed | 2019-09-10 | Completed | 2019-09-06 | Completed | 2019-08-26 | 2019-08-27 | Completed | 2019-09-02 | 2019-09-17 | Completed | 2019-09-17 | 2019-09-17 | Completed | 2019-09-23 | Completed |  |  |  |  | 2019-09-23 | Completed |  |  | 2019-10-08 | Completed | 2020-05-19 | 2019-10-08 | 224 | On/ Ahead Schedule | Completed | 2019-10-14 | 2019-10-18 | Completed | 2021-04-02 | Not Started
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E | E.5014772.05 | 5784863 | FICL | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2020 | 2019 | SH | NAPA | North Bay Assets | 0 | 4191 | 4191 | 0.79375 | 0.79375 | 0 | 4191 | 4191 | 0.79375 | 0.79375 | Contract | 2126590 | 8100.2 | 2118489.8 | 1679560.4 | 0 | 438929.4 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 361963.8 | 1316527 | 1069.6 | Project is not in the WP or in 2020 WP | 0 | 1069.6 | -1069.6 | 1069.6 | -1069.6 | 0 | 1069.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2019-08-16 | Completed |  |  | Completed | 2019-09-02 | Completed | 2019-10-01 | Completed | 2019-10-02 | 2019-10-03 | Completed | 2019-10-03 | 2019-10-04 | Completed | 2019-09-13 | 2019-09-13 | Completed | 2019-11-20 | Completed |  |  |  |  | 2019-11-20 | Completed |  |  | 2020-05-01 | Completed | 2020-05-18 | 2020-05-01 | 17 | On/ Ahead Schedule | Completed | 2020-05-11 | 2020-05-15 | Completed | 2021-05-24 | Not Started
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | E.5015029.11 | 5785167 | FICL | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 | 2021 | SH | LAKEPORT | Humboldt Division Assets | 0 | 5621 | 5621 | 1.0646 | 1.0617 | 0.0028598 | 5621 | 0 | 1.0646 | 0 | GC | 1733017 | 294030.4 | 1438986.6 | 1305671.2 | 6838 | 140153.4 | On/Under Budget | 0 | 0 | -250 | 250 | 0 | 4708.5 | 1049980.8 | 250731.9 | Request 2021 Budget | 0 | 250981.9 | -250981.9 | 250981.9 | -250981.9 | 250292.2 | 8520.2 | -7830.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145838 | BL-0: | BL-0: 35094397_CWSP - KONOCTI 1102-LR 532 PH 10_08W - Nov 2020 | 2020-07-24 | 2019-12-26 | Completed | 2020-05-29 | 2020-05-29 | Completed | 2020-05-29 | Completed | 2020-02-21 | Completed | 2020-05-29 | 2020-05-29 | Completed | 2020-05-29 | 2020-05-29 | Completed | 2020-04-17 | 2020-04-17 | Completed | 2020-06-02 | Completed |  |  |  |  | 2020-06-02 | Completed | 2021-01-13 | Completed | 2020-11-09 | Completed | 2020-11-06 | 2021-01-15 | -70 | Behind Schedule | Completed |  |  |  | 2021-05-03 | Not Started
35094392 | OCGC CWSP-KONOCTI 1102-LR 532 PH 5 | E.5015029.06 | 5785162 | FICL | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | Not in the WP | 2019 | SH | LAKEPORT | Humboldt Division Assets | 0 | 1956 | 1956 | 0.37045 | 0.37045 | 0 | [5 empty] | 270000 | 0 | 270000 | 260347.4 | 0 | 9652.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 264079.1 | -3731.7 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2019-08-29 | Completed | 2019-08-16 | 2019-08-19 | Completed | 2019-10-22 | Completed | 2019-08-20 | Completed | 2019-10-02 | 2019-12-03 | Completed | 2019-10-24 | 2019-10-24 | Completed | 2019-09-04 | 2019-09-05 | Completed | 2019-10-28 | Completed |  |  |  |  | 2019-10-28 | Completed | 2019-11-11 | Completed | 2019-12-04 | Completed | 2020-02-10 | 2019-12-04 | 68 | On/ Ahead Schedule | Completed | 2019-12-16 | 2019-12-27 | Completed | 2021-04-02 | Not Started
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | E.5015029.07 | 5785163 | FICL | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2020 | 2020 | SH | LAKEPORT | Humboldt Division Assets | 0 | 10641 | 10641 | 2.0153 | 2.0153 | 3.4451e-16 | 10642 | 0 | 2.0155 | 0 | GC | 3335231 | 520198.9 | 2815032.1 | 1763244.6 | 0 | 1051787.5 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 3208.6 | 1794523.7 | -34487.7 | Project is not in the WP or in 2020 WP | 0 | -34487.7 | 34487.7 | -34487.7 | 34487.7 | -34487.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145836 | BL-0: | BL-0: 35094393_CWSP - KONOCTI 1102-LR 532 PH 6_08W - Oct 2020 | 2020-07-24 | 2019-12-19 | Completed | 2020-02-17 | 2020-02-18 | Completed | 2020-01-29 | Completed | 2020-02-13 | Completed | 2020-02-24 | 2020-02-25 | Completed | 2020-05-04 | 2020-06-02 | Completed | 2020-04-24 | 2020-04-24 | Completed | 2020-06-01 | Completed |  |  |  |  | 2020-06-01 | Completed | 2020-08-05 | Completed | 2020-08-20 | Completed | 2020-10-14 | 2020-08-20 | 55 | On/ Ahead Schedule | Completed |  |  |  | 2021-04-02 | Not Started
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | E.5015029.08 | 5785164 | FICL | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2020 | 2020 | SH | LAKEPORT | Humboldt Division Assets | 0 | 7765 | 7765 | 1.4706 | 1.4706 | 0 | 7765 | 0 | 1.4706 | 0 | GC | 1708101 | 37446.7 | 1670654.3 | 1480078.6 | 0 | 190575.7 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 3645.6 | 1474096.1 | 2336.8 | Project is not in the WP or in 2020 WP | 0 | 2336.8 | -2336.8 | 2336.8 | -2336.8 | 2336.8 | 252.3 | -252.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145837 | BL-0: | BL-0: 35094394_CWSP - KONOCTI 1102-LR 532 PH 7 _08W - Oct 2020 | 2020-07-24 | 2019-12-11 | Completed | 2019-11-06 | 2019-11-08 | Completed | 2020-01-13 | Completed | 2019-11-06 | Completed | 2019-11-11 | 2019-11-13 | Completed | 2020-02-10 | 2020-02-11 | Completed | 2020-02-07 | 2020-03-20 | Completed | 2020-03-09 | Completed |  |  |  |  | 2020-03-09 | Completed | 2020-11-19 | Completed | 2020-11-19 | Completed | 2020-10-07 | 2020-11-19 | -43 | Behind Schedule | Completed | 2021-04-02 | 2021-04-15 | Not Started | 2021-04-15 | Not Started
35094388 | CWSP-KONOCTI 1102-LR 532 PH 1 | E.5015029.02 | 5785158 | FICL | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | Not in the WP | 2019 | SH | LAKEPORT | Humboldt Division Assets | 0 | 2241 | 2241 | 0.42443 | 0.42443 | 0 | [5 empty] | 400000 | -0.2 | 400000.2 | 390843.6 | 0 | 9156.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 445783 | -54939.4 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2019-07-03 | Completed | 2019-07-23 | 2019-08-01 | Completed | 2019-09-16 | Completed | 2019-08-01 | Completed | 2019-08-05 | 2019-08-06 | Completed | 2018-08-13 | 2019-08-13 | Completed | 2019-09-13 | 2019-09-13 | Completed | 2019-09-16 | Completed |  |  |  |  | 2019-09-16 | Completed | 2019-09-06 | Completed | 2019-09-23 | Completed | 2020-04-01 | 2019-09-23 | 191 | On/ Ahead Schedule | Completed | 2020-03-09 | 2020-03-09 | Completed | 2021-04-02 | Not Started
35111486 | BR-04-03-W (E) EDWARDS & RIPLEY PARB |  | 5786123 | FICL | 08W | AVP4 | Aaron Patane |  |  |  |  | 2020 |  |  | CHICO | [11 empty] | GC | [14 empty] | 5091.7 | Project is not in the WP or in 2020 WP | 0 | 5091.7 | -5091.7 | 0 | 0
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | E.5015533.05 | 5785611 | FICL | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 13964 | 13964 | 2.6447 | 2.6447 | 0 | 15053 | 13964 | 2.8509 | 2.6447 | Contract | 5859212 | 599944 | 5259268 | 4003644.5 | 0 | 1255623.5 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 2158819.4 | 1843117.2 | 1707.9 | Project is not in the WP or in 2020 WP | 0 | 1707.9 | -1707.9 | 1707.9 | -1707.9 | 1304.8 | 1707.8 | -1304.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145810 | BL-0: | BL-0: 35110440_CWSP - Volta 1102 - LR 1648 - Ph2.5_08W - May 2020 | 2020-07-24 | 2019-09-13 | Completed | 2019-09-13 | 2019-09-13 | Completed | 2019-08-22 | Completed | 2019-10-10 | Completed | 2019-09-12 | 2019-09-12 | Completed | 2019-09-03 | 2019-09-03 | Completed | 2019-11-06 | 2019-11-06 | Completed | 2020-02-01 | Completed |  |  |  |  | 2020-03-13 | Completed |  |  | 2020-05-08 | Completed | 2020-05-08 | 2020-05-08 | 0 | On/ Ahead Schedule | Completed | 2020-06-04 | 2020-06-25 | Completed | 2021-03-30 | Completed
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 | E.5015428.03 | 5785617 | FICL | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 11401 | 11401 | 2.1593 | 2.1593 | 0 | 11030 | 11009 | 2.089 | 2.085 | Contract | 4988877 | 176720 | 4812157 | 4263899.6 | 0 | 548257.4 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 1730351.5 | 2533046.2 | 501.9 | Project is not in the WP or in 2020 WP | 0 | 501.9 | -501.9 | 501.9 | -501.9 | 0 | 501.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145815 | BL-0: | BL-0: 35110446_CWSP - Volta 1102 - LR 1648 - Ph4.3_08W - Feb 2020 | 2020-07-24 | 2019-08-27 | Completed | 2019-09-09 | 2019-09-13 | Completed | 2019-10-08 | Completed | 2019-10-08 | Completed | 2019-09-12 | 2019-09-12 | Completed | 2019-09-26 | 2019-09-26 | Completed | 2019-10-21 | 2020-01-05 | Completed | 2020-01-13 | Completed |  |  |  |  | 2020-01-13 | Completed |  |  | 2020-02-18 | Completed | 2020-02-18 | 2020-02-18 | 0 | On/ Ahead Schedule | Completed | 2020-05-07 | 2020-05-21 | Completed | 2021-03-26 | Completed
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | E.5015428.04 | 5785618 | FICL | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 6198 | 6198 | 1.1739 | 1.1739 | 0 | 6201 | 6190 | 1.1744 | 1.1723 | Contract | 4129566 | 0.4 | 4129565.6 | 4013101.3 | 0 | 116464.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 2016413.2 | 1994819.5 | 1868.6 | Project is not in the WP or in 2020 WP | 0 | 1868.6 | -1868.6 | 1868.6 | -1868.6 | 1465.6 | 403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145816 | BL-0: | BL-0: 35110447_CWSP - Volta 1102 - LR 1648 - Ph4.4_08W - April 2020 | 2020-07-24 | 2019-09-18 | Completed | 2019-09-24 | 2019-10-15 | Completed | 2019-09-06 | Completed | 2019-09-24 | Completed | 2019-12-27 | 2019-12-27 | Completed | 2020-01-17 | 2020-01-17 | Completed | 2019-09-06 | 2020-01-05 | Completed | 2020-01-27 | Completed |  |  |  |  | 2020-01-27 | Completed |  |  | 2020-04-10 | Completed | 2020-04-10 | 2020-04-10 | 0 | On/ Ahead Schedule | Completed | 2020-06-09 | 2020-06-24 | Completed | 2021-03-26 | Completed
35109832 | BR-03-01-W (E) GATE LN PARB |  | 5786123 | FICL | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2020 |  |  | CHICO | North Valley Assets | [10 empty] | Contract | 1762328.04 | 1662328.04 | 100000 | -164567 | 0 | 264567 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 931673.9 | -1096240.9 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | E.5015704.02 | 5785613 | FICL | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 7155 | 7155 | 1.3551 | 1.3551 | 0 | 7155 | 7126 | 1.3551 | 1.3496 | Contract | 4820085 | 175070.8 | 4645014.2 | 4396852.2 | 0 | 248162 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 5652989.3 | -1257445.1 | 1308.1 | Project is not in the WP or in 2020 WP | 0 | 1308.1 | -1308.1 | 1308.1 | -1308.1 | 905 | 1308 | -904.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145812 | BL-0: | BL-0: 35110442_CWSP - Volta 1102 - LR 1648 - Ph3.2_08W - Dec 2019 | 2020-07-24 | 2019-09-12 | Completed | 2019-09-12 | 2019-09-13 | Completed | 2019-10-01 | Completed | 2019-09-12 | Completed | 2019-11-02 | 2019-11-02 | Completed | 2019-10-22 | 2019-10-23 | Completed | 2019-10-02 | 2019-10-15 | Completed | 2019-12-02 | Completed |  |  |  |  | 2019-12-02 | Completed |  |  | 2019-12-26 | Completed | 2019-12-26 | 2019-12-26 | 0 | On/ Ahead Schedule | Completed | 2020-05-04 | 2020-07-27 | Completed | 2021-03-26 | Completed
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 | E.5015704.03 | 5785614 | FICL | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 6630 | 6630 | 1.2557 | 1.2557 | 0 | 6468 | 6433 | 1.225 | 1.2184 | Contract | 4241038 | 212599.6 | 4028438.4 | 3712360.4 | 0 | 316078 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 3633268.9 | 78890.1 | 201.4 | Project is not in the WP or in 2020 WP | 0 | 201.4 | -201.4 | 201.4 | -201.4 | 0 | 201.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145813 | BL-0: | BL-0: 35110443_CWSP - Volta 1102 - LR 1648 - Ph3.3_08W - Jan 2020 | 2020-07-24 | 2019-09-10 | Completed | 2019-09-13 | 2019-09-13 | Completed | 2019-08-30 | Completed | 2019-10-04 | Completed | 2019-09-16 | 2019-09-16 | Completed | 2019-11-29 | 2019-11-29 | Completed | 2019-11-21 | 2019-11-21 | Completed | 2019-12-03 | Completed |  |  |  |  | 2019-12-03 | Completed |  |  | 2020-01-30 | Completed | 2020-01-30 | 2020-01-30 | 0 | On/ Ahead Schedule | Completed | 2020-05-11 | 2020-07-31 | Completed | 2021-03-26 | Completed
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 | E.5015704.04 | 5785615 | FICL | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 7783 | 7783 | 1.4741 | 1.4741 | 0 | 7757 | 7728 | 1.4691 | 1.4636 | Contract | 4551984 | 182845.1 | 4369138.9 | 3593144 | 55095.4 | 831090.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 3069940.6 | 522701.5 | 501.9 | Project is not in the WP or in 2020 WP | 0 | 501.9 | -501.9 | 501.9 | -501.9 | 0 | 501.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145818 | BL-0: | BL-0: 35110444_CWSP - Volta 1102 - LR 1648 - Ph3.4_08W - Feb 2020 | 2020-07-24 | 2019-09-12 | Completed | 2019-09-13 | 2019-09-26 | Completed | 2019-08-20 | Completed | 2019-09-13 | Completed | 2019-09-20 | 2019-09-20 | Completed | 2019-10-05 | 2019-10-05 | Completed | 2019-09-24 | 2019-09-24 | Completed | 2019-10-05 | Completed |  |  |  |  | 2019-10-05 | Completed |  |  | 2020-02-06 | Completed | 2020-02-06 | 2020-02-06 | 0 | On/ Ahead Schedule | Completed | 2020-05-14 | 2020-05-28 | Completed | 2021-03-26 | Completed
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 | 5785514 | FICL | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2019 | SH | PLCRVLLE | Sierra Assets | 0 | 9673 | 9673 | 1.832 | 1.832 | 0 | [5 empty] | 3529311 | 743625.1 | 2785685.9 | 1945492.6 | 0 | 840193.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 2084656.3 | -140778.5 | 1614.8 | Project is not in the WP or in 2020 WP | 0 | 1614.8 | -1614.8 | 1614.8 | -1614.8 | 504.6 | 605.6 | 504.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2019-08-23 | Completed | 2019-10-21 | 2019-10-24 | Completed | 2019-09-27 | Completed | 2019-09-16 | Completed | 2019-08-26 | 2019-08-26 | Completed | 2019-09-11 | 2019-09-11 | Completed | 2019-09-19 | 2020-03-13 | Completed | 2019-09-16 | Completed |  |  |  |  | 2019-09-20 | Completed |  |  | 2019-11-09 | Completed | 2020-05-18 | 2019-11-09 | 191 | On/ Ahead Schedule | Completed | 2019-11-11 | 2019-11-15 | Completed | 2021-05-24 | Not Started
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | E.5014759.01 | 5785578 | FICL | 08W | M5HF | Mike Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 8626 | 8626 | 1.6337 | 1.6337 | 0 | 8626 | 8610 | 1.6337 | 1.6307 | Contract | 4120715 | 188080.5 | 3932634.5 | 3620849 | 0 | 311785.5 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 1935238.5 | 1684187.5 | 1423 | Project is not in the WP or in 2020 WP | 0 | 1423 | -1423 | 1423 | -1423 | 921 | 1406.9 | -904.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145819 | BL-0: | BL-0: 35107688_CWSP - VOLTA 1102 - LR 1648 -PH1.1_08W - April 2020 | 2020-07-24 | 2019-11-04 | Completed | 2019-11-08 | 2019-11-08 | Completed | 2019-08-27 | Completed | 2019-11-04 | Completed | 2019-11-07 | 2019-11-07 | Completed | 2019-11-21 | 2019-11-21 | Completed | 2019-11-04 | 2019-11-06 | Completed | 2020-01-07 | Completed |  |  |  |  | 2020-02-17 | Completed | 2020-04-10 | Completed | 2020-04-10 | Completed | 2020-04-10 | 2020-04-10 | 0 | On/ Ahead Schedule | Completed | 2020-04-30 | 2020-05-15 | Completed | 2021-04-02 | Not Started
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | E.5015533.02 | 5785608 | FICL | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 11610 | 11610 | 2.1989 | 2.1989 | 0 | 10965 | 11549 | 2.0767 | 2.1873 | Contract | 5442195 | 225317.5 | 5216877.5 | 4572882 | 0 | 643995.5 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 3246725.8 | 1315696.6 | 10459.5 | Project is not in the WP or in 2020 WP | 0 | 10459.5 | -10459.5 | 10459.5 | -10459.5 | 10056.3 | 3902.5 | -3499.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145807 | BL-0: | BL-0: 35109737_CWSP - Volta 1102 - LR 1648 - Ph2.2_08W - Mar 2020 | 2020-07-24 | 2019-11-08 | Completed | 2019-10-15 | 2019-11-23 | Completed | 2019-09-18 | Completed | 2019-11-08 | Completed | 2019-10-15 | 2019-10-15 | Completed | 2019-10-29 | 2019-10-29 | Completed | 2019-08-07 | 2019-11-27 | Completed | 2019-11-15 | Completed |  |  |  |  | 2019-12-16 | Completed |  |  | 2020-03-16 | Completed | 2020-03-16 | 2020-03-16 | 0 | On/ Ahead Schedule | Completed | 2020-05-04 | 2020-05-25 | Completed | 2021-03-30 | Completed
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 | E.5015533.03 | 5785609 | FICL | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 10959 | 10959 | 2.0756 | 2.0756 | 0 | 10903 | 10732 | 2.065 | 2.0326 | Contract | 4773512 | 289328.9 | 4484183.1 | 4189309.9 | 0 | 294873.2 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 2069988.1 | 2119312.7 | 9.1 | Project is not in the WP or in 2020 WP | 0 | 9.1 | -9.1 | 9.1 | -9.1 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145808 | BL-0: | BL-0: 35109738_CWSP - Volta 1102 - LR 1648 - Ph2.3_08W - May 2020 | 2020-07-24 | 2019-10-02 | Completed | 2019-12-19 | 2019-12-19 | Completed | 2019-11-06 | Completed | 2019-11-06 | Completed | 2019-10-07 | 2019-10-07 | Completed | 2019-10-21 | 2019-10-21 | Completed | 2019-11-21 | 2020-01-05 | Completed | 2020-01-06 | Completed |  |  |  |  | 2020-02-19 | Completed |  |  | 2020-05-28 | Completed | 2020-05-28 | 2020-05-28 | 0 | On/ Ahead Schedule | Completed | 2020-06-01 | 2020-10-30 | Completed | 2021-03-30 | Completed
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 | E.5015704.01 | 5785228 | FICL | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2019 | SH | CHICO | North Valley Assets | 0 | 3666 | 3666 | 0.69432 | 0.69432 | 0 | [5 empty] | 3514354 | 162325.5 | 3352028.5 | 3093747.3 | 6093.4 | 264374.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 3083316.7 | 9525.6 | 905 | Project is not in the WP or in 2020 WP | 0 | 905 | -905 | 905 | -905 | 905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145804 | BL-0: | BL-0: 35095165_CWSP - Volta 1102 - LR 1648 - Ph 3.1_08W - Nov 2019 | 2020-07-24 | 2019-07-22 | Completed | 2019-09-06 | 2019-09-11 | Completed | 2019-08-16 | Completed | 2019-09-12 | Completed | 2019-09-12 | 2019-09-12 | Completed | 2019-09-04 | 2019-09-10 | Completed | 2019-09-09 | 2019-10-01 | Completed | 2019-09-17 | Completed |  |  |  |  | 2019-09-17 | Completed | 2019-11-09 | Completed | 2019-11-25 | Completed | 2019-11-25 | 2019-11-25 | 0 | On/ Ahead Schedule | Completed | 2020-06-15 | 2020-07-06 | Completed | 2021-03-20 | Completed
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 | E.5014759.02 | 5785579 | FICL | 08W | M5HF | Mike Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 9606 | 9606 | 1.8193 | 1.8193 | 0 | 9606 | 9607 | 1.8193 | 1.8195 | Contract | 4524488 | 191615.9 | 4332872.1 | 4040877.6 | 0 | 291994.5 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 2974123.8 | 1065839.7 | 914.1 | Project is not in the WP or in 2020 WP | 0 | 914.1 | -914.1 | 914.1 | -914.1 | 914.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145820 | BL-0: | BL-0: 35106042_CWSP - VOLTA 1102 - LR 1648 - PH 1.2_08W - May 2020 | 2020-07-24 | 2019-08-27 | Completed | 2019-10-30 | 2019-12-19 | Completed | 2019-10-07 | Completed | 2019-11-01 | Completed | 2019-10-31 | 2019-10-31 | Completed | 2019-11-04 | 2019-11-04 | Completed | 2019-10-21 | 2019-11-06 | Completed | 2019-11-14 | Completed |  |  |  |  | 2019-11-14 | Completed | 2020-05-14 | Completed | 2020-05-14 | Completed | 2020-05-14 | 2020-05-14 | 0 | On/ Ahead Schedule | Completed | 2020-06-10 | 2020-06-24 | Completed | 2021-04-02 | Not Started
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | E.5014759.03 | 5785580 | FICL | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 9489 | 9489 | 1.7972 | 1.7972 | 0 | 10118 | 9489 | 1.9163 | 1.7972 | Contract | 4257794 | 515791.4 | 3742002.6 | 3560775.3 | 0 | 181227.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 1884904.9 | 1663039 | 12831.4 | Project is not in the WP or in 2020 WP | 0 | 12831.4 | -12831.4 | 12831.4 | -12831.4 | 905 | 0 | 11926.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145821 | BL-0: | BL-0: 35106265_CWSP - Volta 1102 - LR 1648 - Ph1.3_08W - Feb 2020 | 2020-07-24 | 2019-08-27 | Completed | 2019-09-19 | 2019-09-19 | Completed | 2019-08-22 | Completed | 2019-10-11 | Completed | 2019-09-12 | 2019-09-12 | Completed | 2019-09-26 | 2019-09-26 | Completed | 2019-11-04 | 2019-11-06 | Completed | 2019-10-05 | Completed |  |  |  |  | 2019-10-05 | Completed | 2020-02-17 | Completed | 2020-02-17 | Completed | 2020-02-17 | 2020-02-17 | 0 | On/ Ahead Schedule | Completed | 2020-05-12 | 2020-05-26 | Completed | 2021-03-30 | Completed
35105649 | BR-14-02-W (E) DRENDEL PARB |  | 5786123 | FICL | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2020 |  |  | CHICO | North Valley Assets | [10 empty] | GC | 1966056.89 | 1066056.89 | 900000 | 790232.6 | 0 | 109767.4 | On/Under Budget | 0 | 0 | -6790.1 | 6790.1 | 0 | 259117.9 | 514604.3 | 9720.4 | Project is not in the WP or in 2020 WP | 0 | 16510.5 | -16510.5 | 16510.5 | -16510.5 | 9880.9 | -223 | 6852.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35101875 | BR-01-10-W (E) BILLIE & LUCKY JOHN PARB |  | 5786123 | FICL | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2020 |  |  | CHICO | North Valley Assets | [10 empty] | Contract | 1612614.09 | 1112614.09 | 500000 | 312832.5 | 200 | 187367.5 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 648902.6 | -336070.1 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35101876 | BR-01-08-W (E) MADRONE_BILLE_GRAHAM PARB |  | 5786123 | FICL | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 |  |  | CHICO | North Valley Assets | [6 empty] | 3407 | 0 | 0.64527 | 0 | Contract | 910483.14 | 560483.14 | 350000 | 209590.2 | 10680 | 151089.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 928157.5 | -718567.3 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35101877 | BR-01-06-W (E) THOMASSON LN PARB |  | 5786123 | FICL | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | 2020 |  |  | CHICO | North Valley Assets | [6 empty] | 6358 | 0 | 1.2042 | 0 | Contract | 1213012.83 | 113012.83 | 1100000 | 966943.7 | 0 | 133056.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 2343712.4 | -1375858.3 | -910.4 | Project is not in the WP or in 2020 WP | 0 | -910.4 | 910.4 | -910.4 | 910.4 | -910.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 | E.5014544.01 | 5786325 | FICL | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2020 |  | SH | CONCORD | Diablo Assets | 0 | 12599 | 12599 | 2.3862 | 2.3862 | 0 | 12588 | 12151 | 2.3841 | 2.3013 | Contract | 5151555 | -1.1 | 5151556.1 | 5084914.2 | 0 | 66641.9 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 4895315.5 | 227358.4 | -37759.7 | Project is not in the WP or in 2020 WP | 0 | -37759.7 | 37759.7 | -37759.7 | 37759.7 | -37759.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 | E.5015491.05 | 5785304 | FICL | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 13101 | 13101 | 2.4813 | 2.4813 | 0 | [5 empty] | 4936253 | 781728.6 | 4154524.4 | 4043293.8 | 0 | 111230.6 | On/Under Budget | -126589 | 0 | -11500 | 11500 | 0 | 3885676.6 | 156103.3 | -9986.1 | Project is not in the WP or in 2020 WP | 0 | 1513.9 | -1513.9 | -125075.1 | 125075.1 | 1513.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -126589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | E.5014753.01 | 5782586 | FICL | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2020 | 2020 | SH | CONCORD | Diablo Assets | 0 | 31174 | 31174 | 5.9042 | 5.9042 | 0 | 31276 | 31276 | 5.9235 | 5.9235 | GC | 9709000 | 0 | 9709000 | 9409557.1 | 9394.7 | 308837.6 | On/Under Budget | 0 | 2814.4 | -5474.8 | 8289.2 | 4338.7 | 778748.6 | 8545650 | 75345 | Project is not in the WP or in 2020 WP | 368855 | 83634.2 | 285220.8 | 83634.2 | 285220.8 | 54187.1 | 12073.3 | 14559.4 | 2814.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 140140 | BL- 0 | BL- 0: 35053033_CWSP - TASSAJARA 2112 - FUSE 18053_08W - Feb 20 | 2020-02-12 | 2019-07-26 | Completed |  |  | Completed | 2019-11-21 | Completed | 2019-11-21 | Completed |  |  |  | 2019-12-09 | 2019-12-13 | Completed |  |  |  | 2019-12-03 | Completed |  |  |  |  | 2019-12-03 | Completed |  |  | 2020-06-04 | Completed | 2021-03-05 | 2020-06-04 | 274 | On/ Ahead Schedule | Completed |  |  |  | 2021-04-02 | Not Started
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | E.5014773.01 | 5785222 | FICL | 08W | PXSO | Peter Siu | C2LJ | Cynthia Lau | MUHQ | Matt Haley | 2020 | 2020 | SH | SONORA | Yosemite Assets | 0 | 10619 | 10619 | 2.0112 | 2.0112 | 0 | 10392 | 10392 | 1.9682 | 1.9682 | GC | 3585097 | -3447396.2 | 7032493.2 | 3285070.8 | 95313.6 | 3842736 | On/Under Budget | 0 | 96196.1 | 0 | 96196.1 | 6248.5 | 14703.7 | 3223881 | 40237.6 | Project is not in the WP or in 2020 WP | 0 | 136433.7 | -136433.7 | 136433.7 | -136433.7 | 0 | 40237.6 | 0 | 96196.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 155987 | BL-1 | BL-1 35052820_CWSP - MIWUK 1702 - OCB - PH 1.1_08W - Feb. 2021 | 2021-02-16 | 2020-03-19 | Completed | 2020-03-16 | 2020-04-13 | Completed | 2019-12-13 | Completed | 2020-04-10 | Completed | 2020-04-15 | 2020-04-16 | Completed | 2020-04-20 | 2020-04-21 | Completed | 2020-02-20 | 2020-03-11 | Completed | 2020-04-24 | Completed |  |  |  |  | 2020-05-01 | Completed |  |  | 2020-06-11 | Completed | 2020-06-11 | 2020-06-11 | 0 | On/ Ahead Schedule | Completed | 2020-08-05 | 2020-08-08 | Completed | 2021-03-19 | Not Started
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | FICL | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 6215 | 6215 | 1.1771 | 1.1771 | 0 | [5 empty] | 4515047 | 955704.3 | 3559342.7 | 3104134.1 | 0 | 455208.6 | On/Under Budget | 0 | 0 | -782.8 | 782.8 | 5264.2 | 34636.1 | 3029430.1 | 34021 | Project is not in the WP or in 2020 WP | 0 | 34803.8 | -34803.8 | 34803.8 | -34803.8 | -59587.4 | 80652.8 | 13738.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157111 | BL-1 | BL-1 35058273_CWSP - El Dorado 2101 - OCB Zone - Ph 1.1_08W - Mar. 2021 | 2021-03-07 | 2019-09-17 | Completed | 2020-02-17 | 2020-02-24 | Completed | 2019-12-31 | Completed | 2020-04-13 | Completed | 2020-04-13 | 2020-04-13 | Completed | 2020-03-20 | 2020-04-28 | Completed | 2020-02-14 | 2020-07-10 | Completed | 2020-03-09 | Completed |  |  |  |  | 2020-03-10 | Completed |  |  | 2020-06-26 | Completed | 2020-07-20 | 2020-07-20 | 0 | On/ Ahead Schedule | Completed | 2020-08-21 | 2020-09-03 | Completed | 2021-05-10 | Not Started
35060582 | SLO 1107 RECOD 3884 FT WITH 2CU TW |  | 5530166 | FICL | 08W | B1GQ | Brian Gallo |  |  |  |  | Not in the WP |  | SH | SNLUISOB |  | 0 | 3884 | 3884 | 0.73561 | 0.73561 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31290145 | R7 SAN RAFAEL 1107 COND REPLACEMENT |  | 5530168 | FICL | 08W | S2WT | Steve Whitman |  |  |  |  | Not in the WP | 2019 | SH | SNRAFAEL |  | 0 | 801 | 801 | 0.1517 | 0.1517 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [25 empty] | 2021-04-02 | 128629 | WSHP | WSHP 190307 - 31290145_SAN RAFAEL 1107_08W - B1 | 2019-03-07 | 2019-03-11 | Completed | 2019-03-08 | 2019-04-12 | Completed | 2019-04-09 | Completed | 2019-03-18 | Completed | 2019-03-18 | 2019-03-18 | Completed | 2019-08-06 | 2019-08-06 | Completed | 2019-08-06 | 2019-08-07 | Completed | 2019-08-07 | Completed |  |  |  |  | 2019-08-07 | Completed |  |  | 2019-08-12 | Completed | 2019-05-28 | 2019-08-12 | -76 | Behind Schedule | Completed | 2019-09-23 | 2019-10-07 | Completed | 2020-01-02 | Completed
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT |  | 5530161 | FICL | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2020 | 2020 | SH | CONCORD | Diablo Assets | 0 | 7959 | 7959 | 1.5074 | 1.5074 | 0 | 8023 | 8400 | 1.5195 | 1.5909 | Contract | 4611914 | 1613584.7 | 2998329.3 | 2743432.3 | 0 | 254897 | On/Under Budget | 0 | 0 | 0 | 0 | 12379 | 41700.6 | 2695147.8 | -7204.1 | Project is not in the WP or in 2020 WP | 0 | -7204.1 | 7204.1 | -7204.1 | 7204.1 | 0 | -7204.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 147000 | BL-0 | BL-0 31343500_2019 ORINDA 401 HIGH SPLICE COUNT - MAY 2020 | 2020-08-11 | 2019-12-16 | Completed | 2020-03-02 | 2020-03-13 | Completed | 2020-02-10 | Completed | 2020-02-17 | Completed | 2020-02-10 | 2020-02-17 | Completed | 2020-02-25 | 2020-02-25 | Completed | 2020-02-14 | 2020-02-14 | Completed | 2020-02-24 | Completed |  |  |  |  | 2020-02-24 | Completed |  |  | 2020-05-13 | Completed | 2020-05-13 | 2020-05-13 | 0 | On/ Ahead Schedule | Completed | 2020-05-13 | 2020-05-14 | Completed | 2020-10-15 | Completed
31098626 | CLARKSVILLE 2104 RECONDUCTOR -PH 3 Y2018 | P.11129 | 5530173 | FICL | 08W | BER5 | Brian Ritchie | JIDM | Jason Daggett |  |  | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 8052 | 8052 | 1.525 | 1.525 | 0 | 8052 | 8052 | 1.525 | 1.525 | GC | 1543425 | 242205 | 1301220 | 1273909.1 | 0 | 27310.9 | On/Under Budget | 0 | 0 | 0 | 0 | 401288.3 | 103291.5 | 754304.2 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 140244 | BL-2: | BL-2: 31098626_CLARKSVILLE 2104 RECOND - PH 3 - Feb 2020 | 2020-02-15 | 2018-06-20 | Completed |  |  | Completed | [10 empty] | 2018-07-10 | 2018-07-13 | Completed | 2018-07-16 | Completed | [8 empty] | 2020-06-26 | Completed | 2021-07-05 | 2020-12-01 | 216 | On/ Ahead Schedule | Completed |  |  |  | 2021-04-02 | Not Started
31269259 | ZACA 1101 FOXEN CYN RD, LOS OLIVOS |  | 5530166 | FICL | 08W | B1GQ | Brian Gallo |  |  |  |  | Not in the WP | 2019 | SH | SNLUISOB |  | 0 | 6386 | 6386 | 1.2095 | 1.2095 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [25 empty] | 2020-10-30 | 128540 | WSHP | WSHP 190307 - 35060582_SLO 1107 SQUIRE CYN WILDFIRE RESIL - B1 | 2019-03-07 | 2019-03-06 | Completed |  |  | Completed | 2019-01-08 | Completed | 2019-05-24 | Completed | 2019-07-02 | 2019-07-26 | Completed |  |  |  | 2019-07-18 | 2019-08-12 | Completed | 2019-08-13 | Completed |  |  |  |  | 2019-08-30 | Completed |  |  | 2019-09-26 | Completed | 2019-08-28 | 2019-09-26 | -29 | Behind Schedule | Completed | 2019-09-27 | 2019-10-09 | Completed | 2019-11-22 | Completed
31269259 | ZACA 1101 FOXEN CYN RD, LOS OLIVOS |  | 5530166 | FICL | 08W | B1GQ | Brian Gallo |  |  |  |  | Not in the WP | 2019 | SH | SNLUISOB |  | 0 | 6386 | 6386 | 1.2095 | 1.2095 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [25 empty] | 2020-10-30 | 128570 | WSHP | WSHP 190307 - 31278200_OCEANO 1108 S HALCYON & PINE RDGE_08J - B1 | 2019-03-07 | 2019-03-07 | Completed | 2018-07-30 | 2018-08-06 | Completed |  |  | 2018-08-07 | Completed | 2019-03-08 | 2019-06-07 | Completed |  |  |  | 2019-03-11 | 2019-03-11 | Completed | 2019-03-11 | Completed |  |  |  |  | 2019-03-11 | Completed |  |  | 2019-03-21 | Completed | 2019-03-28 | 2019-03-21 | 7 | On/ Ahead Schedule | Completed |  |  |  | 2019-10-01 | Completed
31269259 | ZACA 1101 FOXEN CYN RD, LOS OLIVOS |  | 5530166 | FICL | 08W | B1GQ | Brian Gallo |  |  |  |  | Not in the WP | 2019 | SH | SNLUISOB |  | 0 | 6386 | 6386 | 1.2095 | 1.2095 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [25 empty] | 2020-10-30 | 128538 | WSHP | WSHP 190307 - 31269259_ZACA 1101 FOXEN CYN RD, LOS OLIVOS_08W - B1 | 2019-03-07 | 2019-04-01 | Completed | 2019-04-02 | 2019-05-09 | Completed | 2019-05-30 | Completed | 2019-05-24 | Completed | 2019-05-20 | 2019-05-23 | Completed |  |  |  | 2019-05-17 | 2019-05-20 | Completed | 2019-05-23 | Completed |  |  |  |  | 2019-05-23 | Completed |  |  | 2019-06-30 | Completed | 2019-05-13 | 2019-06-30 | -48 | Behind Schedule | Completed |  |  |  | 2019-10-01 | Completed
31232280 | ZACA 1102 LONG CYN RD, SANTA YNEZ |  | 5530166 | FICL | 08W | B1GQ | Brian Gallo |  |  |  |  | Not in the WP | 2019 | SH | SNLUISOB |  | 0 | 5851 | 5851 | 1.1081 | 1.1081 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [25 empty] | 2020-10-30 | 128537 | WSHP | WSHP 190307 - 31232280_ZACA 1102 LONG CYN RD, SANTA YNEZ_08W - B2 | 2019-03-07 | 2019-04-01 | Completed | 2019-04-01 | 2019-05-09 | Completed | 2019-04-25 | Completed | 2019-05-24 | Completed | 2019-05-20 | 2019-05-23 | Completed |  |  |  | 2019-05-17 | 2019-05-22 | Completed | 2019-05-23 | Completed |  |  |  |  | 2019-05-23 | Completed |  |  | 2019-06-30 | Completed | 2019-05-15 | 2019-06-30 | -46 | Behind Schedule | Completed |  |  |  | 2019-11-02 | Completed
35031662 | CWSP - LOS GATOS 1106 - LB44 - PHASE 2.1 | E.5014534.01 | 5780841 | FICL | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2020 | 2020 | SH | CUPRTINO | De Anza Assets | 511 | 2467 | 2978 | 0.56402 | 0.56402 | 5.1676e-16 | 2978 | 2978 | 0.56402 | 0.56402 | Division | 1363100.7 | 253111.7 | 1109989 | 1026578.3 | 0 | 83410.7 | On/Under Budget | 2112.7 | 4225.3 | 0 | 4225.3 | 17817.8 | 32969.5 | 975791 |  | Project is not in the WP or in 2020 WP | 0 | 6338 | -6338 | 6338 | -6338 | 0 | 0 | 0 | 4225.3 | 2112.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-12-17 |  |  |  |  | 2019-10-07 | Completed | 2020-01-15 | 2020-02-18 | Completed | 2020-01-13 | Completed | 2020-01-13 | Completed | 2020-01-27 | 2020-01-27 | Completed | 2020-01-21 | 2020-01-21 | Completed | 2020-01-20 | 2020-03-25 | Completed | 2020-02-12 | Completed |  |  |  |  | 2020-02-12 | Completed |  |  | 2020-03-25 | Completed | 2020-03-25 | 2020-03-25 | 0 | On/ Ahead Schedule | Completed |  |  |  | 2021-02-02 | Completed
35024926 | MARTELL 1101 RECONDCUTOR 3,700FT |  | 5530176 | FICL | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 686.4 | 686.4 | 0.13 | 0.13 | 0 | [5 empty] | 824970 | 121913 | 703057 | 537779.5 | 0 | 165277.5 | On/Under Budget | 0 | 0 | 0 | 0 | 9563.7 | 528215.8 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31206678 | MVWF SEQUOIA VLY RD CTY/CNTY AL1125/1124 | P.11109 | 5530168 | FICL | 08W | J91F | Justin M Stabe | AXYX | Aaron Yuen |  |  | Not in the WP |  |  | SNRAFAEL | North Bay Assets | [11 empty] | 1689113 | 357692 | 1331421 | 920278.5 | 0 | 411142.5 | On/Under Budget | 0 | 0 | 0 | 0 | 817684.9 | 55949.4 | -6940.8 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35141419 | BR-03-07-W (E) TIMBER WALK PARB |  | 5786123 | FICL | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2020 |  |  | CHICO | North Valley Assets | [10 empty] | Contract | 261420.05 | -288579.95 | 550000 | 441599.4 | 0 | 108400.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 234659.2 | 206888.5 | 51.7 | Project is not in the WP or in 2020 WP | 0 | 51.7 | -51.7 | 51.7 | -51.7 | 51.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35119966 | CWSP - LOS GATOS 1106 - LB44 - PH 2.6F | E.5014534.06 | 5786603 | FICL | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2020 | 2020 | SH | CUPRTINO | De Anza Assets | 0 | 4325 | 4325 | 0.81913 | 0.81913 | 0 | 4325 | 4309 | 0.81913 | 0.8161 | GC | 1552000 | 416000 | 1136000 | 811677.3 | 0 | 324322.7 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 585.8 | 811091.5 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-12-17 | 141309 | BL-0: | BL-0: 35119966_CWSP Los Gatos 1106-LB44 Ph2.6F _08W - Mar 2020 | 2020-03-10 | 2019-11-22 | Completed |  |  | Completed | 2020-01-21 | Completed | 2020-01-21 | Completed | 2020-01-27 | 2020-01-27 | Completed | 2020-02-11 | 2020-02-20 | Completed | 2020-02-18 | 2020-03-27 | Completed | 2020-02-14 | Completed |  |  |  |  | 2020-02-14 | Completed | 2020-03-04 | Completed | 2020-03-10 | Completed | 2020-05-29 | 2020-03-10 | 80 | On/ Ahead Schedule | Completed |  |  |  | 2021-02-02 | Completed
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | E.5015493.02 | 5786588 | FICL | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2020 | 2020 | SH | CUPRTINO | De Anza Assets | 0 | 6777 | 6777 | 1.2835 | 1.2835 | 0 | 6777 | 0 | 1.2835 | 0 | GC | 2027153 | 0 | 2027153 | 1662230.6 | 21061.3 | 385983.7 | On/Under Budget | 0 | 0 | -1083.7 | 1083.7 | 0 | 4382 | 1663480.6 | -6715.8 | Project is not in the WP or in 2020 WP | 0 | -5632.1 | 5632.1 | -5632.1 | 5632.1 | 971.8 | 3209 | -9812.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-12-17 | 141386 | BL-0: | BL-0: 35119969_CWSP Los Gatos 1106-LB44 Ph 4.2_08W - Mar 20 | 2020-03-16 | 2019-12-02 | Completed | 2020-02-25 | 2020-03-03 | Completed | 2020-01-17 | Completed | 2020-01-22 | Completed | 2020-03-18 | 2020-04-10 | Completed | 2020-03-13 | 2020-04-10 | Completed | 2020-03-20 | 2020-06-03 | Completed | 2020-04-04 | Completed |  |  |  |  | 2020-04-04 | Completed | 2020-08-14 | Completed | 2020-08-14 | Completed | 2020-08-14 | 2020-08-14 | 0 | On/ Ahead Schedule | Completed |  |  |  | 2021-03-17 | Completed
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | E.5015493.03 | 5786587 | FICL | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2020 | 2020 | SH | CUPRTINO | De Anza Assets | 0 | 3090 | 3090 | 0.58523 | 0.58523 | 0 | 3090 | 0 | 0.58523 | 0 | GC | 1850000 | 20000.3 | 1829999.7 | 1823032.9 | 0 | 6966.8 | On/Under Budget | 0 | 0 | -983.7 | 983.7 | 0 | 1604.7 | 1818275.5 | 2169 | Project is not in the WP or in 2020 WP | 0 | 3152.7 | -3152.7 | 3152.7 | -3152.7 | 443.6 | 688.3 | 2020.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-12-17 | 141387 | BL-0: | BL-0: 35119970_CWSP Los Gatos 1106-LB44 Ph 4.3_08W - Mar 20 | 2020-03-16 | 2019-12-03 | Completed | 2020-02-14 | 2020-03-27 | Completed | 2020-01-17 | Completed | 2020-01-21 | Completed | 2019-12-03 | 2019-12-03 | Completed | 2020-02-10 | 2020-02-28 | Completed | 2020-03-20 | 2020-03-30 | Completed | 2020-02-22 | Completed |  |  |  |  | 2020-02-22 | Completed | 2020-08-09 | Completed | 2020-08-09 | Completed | 2020-07-06 | 2020-08-09 | -34 | Behind Schedule | Completed | 2020-08-10 | 2020-11-20 | Completed | 2021-01-21 | Completed
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | E.5015489.01 | 5786658 | FICL | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2020 | 2020 | SH | STCRUZ | Central Coast Assets | 0 | 5683 | 5683 | 1.0763 | 1.0763 | 0 | 5683 | 5642 | 1.0763 | 1.0686 | GC | 2570791 | 435989 | 2134802 | 1627722.3 | 49733.6 | 556813.3 | On/Under Budget | 0 | 0 | -5000 | 5000 | 0 | 29415.8 | 1582833.7 | 10472.8 | Project is not in the WP or in 2020 WP | 0 | 15472.8 | -15472.8 | 15472.8 | -15472.8 | -1819.6 | 10187.6 | 7104.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-12-17 | 128566 | WSHP | WSHP 190307 - 74022381_CWSP - CAMP EVERS 2106 - 5020 - PHASE - BL0 | 2019-03-07 | 2019-12-04 | Completed |  |  | Completed | 2020-02-18 | Completed | 2020-02-20 | Completed | [6 empty] | 2020-03-09 | 2020-05-13 | Completed | 2020-03-12 | Completed |  |  |  |  | 2020-03-12 | Completed |  |  | 2020-05-07 | Completed | 2020-05-16 | 2020-05-07 | 9 | On/ Ahead Schedule | Completed |  |  |  | 2021-02-02 | Completed
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | E.5014730.06 | 5785965 | FICL | 08W | PXSO | Peter Siu | C2LJ | Cynthia Lau | MUHQ | Matt Haley | 2020 |  | SH | SONORA | Yosemite Assets | 0 | 5368 | 5368 | 1.0167 | 1.0167 | 0 | 5387 | 5340 | 1.0203 | 1.0114 | GC | 1868187 | -1868186.6 | 3736373.6 | 2922693.8 | 0 | 813679.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 3300.2 | 2900702.4 | 18691.2 | Project is not in the WP or in 2020 WP | 0 | 18691.2 | -18691.2 | 18691.2 | -18691.2 | 0 | 15790.4 | 2900.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35117444 | CWSP - VOLTA 1102 LR 1648 PH 2.1 | E.5015533.01 | 5786479 | FICL | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 12656 | 12656 | 2.397 | 2.397 | -3.1006e-15 | 12656 | 12656 | 2.397 | 2.397 | Contract | 6272666 | 1474481.8 | 4798184.2 | 4378043 | 51818.9 | 471960.1 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 1210655.5 | 3167000 | 387.5 | Project is not in the WP or in 2020 WP | 0 | 387.5 | -387.5 | 387.5 | -387.5 | 51.2 | 1726.2 | -1389.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145805 | BL-0: | BL-0: 35117444_CWSP - Volta 1102 - LR 1648 - PH2.1_08W - Apr 2020 | 2020-07-24 | 2019-08-30 | Completed | 2019-09-06 | 2019-09-12 | Completed | 2019-09-24 | Completed | 2019-09-18 | Completed | 2019-09-12 | 2019-09-12 | Completed | 2019-09-26 | 2019-09-26 | Completed | 2019-09-24 | 2019-12-20 | Completed | 2019-12-05 | Completed |  |  |  |  | 2020-02-17 | Completed | 2020-04-29 | Completed | 2020-04-29 | Completed | 2020-04-29 | 2020-04-29 | 0 | On/ Ahead Schedule | Completed | 2020-06-01 | 2020-07-16 | Completed | 2021-03-26 | Completed
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | E.5015489.06 | 5786204 | FICL | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2020 | 2020 | SH | SALINAS | Central Coast Assets | 0 | 7775 | 7775 | 1.4725 | 1.4725 | 0 | 7619 | 7962 | 1.443 | 1.508 | GC | 3424639 | 486127 | 2938512 | 2003987.5 | 0 | 934524.5 | On/Under Budget | 0 | 0 | -196.3 | 196.3 | 0 | 2239.3 | 1944870.8 | 56681.1 | Project is not in the WP or in 2020 WP | 0 | 56877.4 | -56877.4 | 56877.4 | -56877.4 | 20063.4 | 35213.4 | 1600.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 141388 | BL-0: | BL-0: 35114104_CWSP - Camp Evers 2106 - LR5020 - PH 2.6_08W - Mar 20 | 2020-03-16 | 2019-10-29 | Completed | 2019-12-31 | 2020-01-16 | Completed | 2020-02-06 | Completed | 2020-02-06 | Completed | 2020-01-06 | 2020-02-20 | Completed | 2020-01-16 | 2020-02-20 | Completed | 2020-02-14 | 2020-06-26 | Completed | 2020-02-14 | Completed |  |  |  |  | 2020-02-14 | Completed | 2020-06-11 | Completed | 2020-06-11 | Completed | 2020-07-31 | 2020-06-11 | 50 | On/ Ahead Schedule | Completed | 2020-06-19 | 2020-06-19 | Completed | 2021-04-02 | Not Started
35114431 | CWSP - MORAGA 1101 - LR108540 - PH5 | E.5014544.05 | 5786201 | FICL | 08W | A1CO | Antonio Miguel Chan | SHMG | Safeer Mirza | J7TY | Jace Thorsen | 2020 |  | SH | CONCORD | Diablo Assets | 166 | 7421 | 7587 | 1.4369 | 1.4369 | -1.8948e-15 | 7673 | 6850 | 1.4532 | 1.2973 | Contract | 5279014 | 655669.2 | 4623344.8 | 4396853.7 | 0 | 226491.1 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 565253.8 | 3831599.9 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35115147 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.2 | E.5015567.02 | 5785725 | FICL | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2020 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 6478 | 6478 | 1.2269 | 1.2269 | 0 | 7076 | 6200 | 1.3402 | 1.1742 | GC | 5398830 | 1783865.7 | 3614964.3 | 1602705.2 | 0 | 2012259.1 | On/Under Budget | -233251 | 0 | 0 | 0 | 0 | 2731.2 | 1585145.3 | 14828.7 | Project is not in the WP or in 2020 WP | 34829 | 14828.7 | 20000.3 | -218422.3 | 253251.3 | 14828.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -233251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145891 | BL-0 | BL-0 35115147_CWSP - BRUNSWICK 1103 LR50070 ZONE-PH 3.2_08W - SEPT 2020 | 2020-07-26 | 2020-02-25 | Completed | 2020-03-18 | 2020-06-18 | Completed | 2020-03-06 | Completed | 2020-03-16 | Completed | 2020-03-24 | 2020-03-24 | Completed | 2020-05-15 | 2020-05-15 | Completed | 2020-05-29 | 2020-06-04 | Completed | 2020-05-05 | Completed |  |  |  |  | 2020-05-05 | Completed | 2020-08-12 | Completed | 2020-08-13 | Completed | 2020-09-15 | 2020-08-13 | 33 | On/ Ahead Schedule | Completed | 2020-08-13 | 2020-08-20 | Completed | 2021-04-02 | Not Started
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | E.5015567.03 | 5785726 | FICL | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2021 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 10627 | 10627 | 2.0127 | 2.0127 | 0 | 11210 | 0 | 2.1231 | 0 | GC | 5062019 | 1268837.6 | 3793181.4 | 3433102.3 | 0 | 360079.1 | On/Under Budget | -387334 | 0 | 0 | 0 | 0 | 3669.6 | 3387964.4 | 41468.3 | Budget Allocated | 59744 | 41468.3 | 18275.7 | -345865.7 | 405609.7 | 39739.6 | 3.9 | 1724.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -387334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 151684 | BL-2 | BL-2 35115148_CWSP - Brunkswick 1103 LR50070 ZONE-PH3.3_08W - Nov. 2020 | 2020-11-24 | 2020-04-24 | Completed | 2020-04-13 | 2020-04-13 | Completed | 2020-03-10 | Completed | 2020-05-04 | Completed | 2020-04-27 | 2020-04-27 | Completed | 2020-07-10 | 2020-07-13 | Completed | 2020-05-21 | 2020-07-10 | Completed | 2020-06-02 | Completed |  |  |  |  | 2020-06-02 | Completed | 2020-08-12 | Completed | 2020-07-23 | Completed | 2021-01-15 | 2020-11-20 | 56 | On/ Ahead Schedule | Completed |  |  |  | 2021-02-02 | Completed
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | E.5015569.03 | 5785718 | FICL | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2020 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 10035 | 10035 | 1.9006 | 1.9006 | 0 | 10244 | 9844 | 1.9402 | 1.8644 | GC | 1357699.57 | -3130976.63 | 4488676.2 | 3212892.6 | 0 | 1275783.6 | On/Under Budget | -174482 | 0 | -5000 | 5000 | 0 | 290688.2 | 2896900 | 20304.4 | Project is not in the WP or in 2020 WP | 37751 | 25304.4 | 12446.6 | -149177.6 | 186928.6 | 15232.4 | 2518.1 | 7553.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -174482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145895 | BL-0 | BL-0 35115156_CWSP - Brunkswick 1103 LR50070 ZONE-PH1.3_08W - JULY 2020 | 2020-07-26 | 2020-06-09 | Completed | 2020-03-06 | 2020-03-24 | Completed | 2020-03-26 | Completed | 2020-06-09 | Completed | 2020-03-18 | 2020-06-09 | Completed | 2020-03-26 | 2020-03-26 | Completed | 2020-03-02 | 2020-03-26 | Completed | 2020-04-01 | Completed |  |  |  |  | 2020-04-01 | Completed | 2020-07-14 | Completed | 2020-06-03 | Completed | 2020-07-03 | 2020-07-03 | 0 | On/ Ahead Schedule | Completed | 2020-07-15 | 2020-07-15 | Completed | 2020-09-16 | Completed
35115157 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.4 | E.5015569.04 | 5785719 | FICL | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2020 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 9456 | 9456 | 1.7909 | 1.7909 | 0 | 15728 | 10162 | 2.9788 | 1.9246 | GC | 1580553.38 | -2668498.02 | 4249051.4 | 3814674.9 | 0 | 434376.5 | On/Under Budget | -314994 | 0 | 0 | 0 | 0 | 1985 | 3797843.4 | 14846.6 | Project is not in the WP or in 2020 WP | 34847 | 14846.6 | 20000.4 | -300147.4 | 334994.4 | 14828.7 | 17.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -314994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 149009 | BL-1 | BL-1 35115157_CWSP - Brunkswick 1103 LR50070 ZONE-PH1.4_08W - Nov. 2020 | 2020-09-28 | 2019-11-14 | Completed | 2020-01-29 | 2020-01-29 | Completed | 2020-02-03 | Completed | 2020-01-29 | Completed | 2020-01-15 | 2020-01-15 | Completed | 2020-01-27 | 2020-02-14 | Completed | 2020-02-20 | 2020-03-13 | Completed | 2020-02-18 | Completed |  |  |  |  | 2020-02-18 | Completed | 2020-07-10 | Completed | 2020-06-03 | Completed | 2020-11-06 | 2020-09-30 | 37 | On/ Ahead Schedule | Completed |  |  |  | 2020-12-02 | Completed
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | E.5015489.03 | 5786132 | FICL | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2020 |  | SH | SALINAS | Central Coast Assets | 0 | 6873 | 6873 | 1.3017 | 1.3017 | 0 | 6873 | 0 | 1.3017 | 0 | GC | 2641148 | 424112.4 | 2217035.6 | 1277807.4 | 49547.6 | 988775.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 633.6 | 1276858.1 | 315.7 | Project is not in the WP or in 2020 WP | 0 | 315.7 | -315.7 | 315.7 | -315.7 | -599 | 914.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | E.5014745.04 | 5785993 | FICL | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2020 |  | SH | JACKSON | Stockton Assets | 0 | 6188 | 6188 | 1.172 | 1.172 | 0 | 7126 | 7126 | 1.3496 | 1.3496 | GC | 2867650 | 828308.7 | 2039341.3 | 1319515.8 | 0 | 719825.5 | On/Under Budget | 0 | 0 | -1030.8 | 1030.8 | 0 | 676.8 | 1292723.3 | 25084.9 | Project is not in the WP or in 2020 WP | 0 | 26115.7 | -26115.7 | 26115.7 | -26115.7 | 24841.1 | -191.5 | 1466.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | E.5014745.05 | 5785994 | FICL | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2020 |  | SH | JACKSON | Stockton Assets | 0 | 5542 | 5542 | 1.0496 | 1.0496 | 0 | 5998 | 5998 | 1.136 | 1.136 | GC | 2617141 | 669630.6 | 1947510.4 | 868502.7 | 0 | 1079007.7 | On/Under Budget | 0 | 0 | -250 | 250 | 0 | 213.7 | 836816.5 | 31222.5 | Project is not in the WP or in 2020 WP | 0 | 31472.5 | -31472.5 | 31472.5 | -31472.5 | 68.3 | 11591.8 | 19812.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | E.5014319.04 | 5786051 | FICL | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2020 |  | SH | CUPRTINO | De Anza Assets | 0 | 3782 | 3782 | 0.71629 | 0.71629 | 0 | 3582 | 3782 | 0.67841 | 0.71629 | GC | 1425671 | 22000 | 1403671 | 1401360.2 | 4307.5 | 6618.3 | On/Under Budget | 0 | 0 | -1083.7 | 1083.7 | 0 | 171437.1 | 1224566.2 | 4273.2 | Project is not in the WP or in 2020 WP | 0 | 7673.1 | -7673.1 | 5356.9 | -5356.9 | 52.2 | 734.6 | 4570.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112876 | BR-04-02-W (E) CASTLE_CLIFF DR PARB |  | 5786123 | FICL | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 |  |  | CHICO | North Valley Assets | [10 empty] | GC | 2273956.11 | 1573956.11 | 700000 | -789529.5 | 13713 | 1503242.5 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 464356.1 | -1253894 | 8.4 | Project is not in the WP or in 2020 WP | 0 | 8.4 | -8.4 | 8.4 | -8.4 | 8.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112091 | BR-01-09-W (E) FERN PARB |  | 5786123 | FICL | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | 2020 |  |  | CHICO | North Valley Assets | [10 empty] | GC | 951433.29 | 551433.29 | 400000 | 396064.2 | 0 | 3935.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 167841.7 | 203513.5 | 24709.1 | Project is not in the WP or in 2020 WP | 0 | 24709.1 | -24709.1 | 24709.1 | -24709.1 | 8256.5 | 0 | 16452.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112092 | BR-14-06 (E) BLUE DANUBE PARB |  | 5786123 | FICL | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | 2020 |  |  | CHICO | North Valley Assets | [10 empty] | Contract | 1300941.33 | 650941.33 | 650000 | 527539.2 | 0 | 122460.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 177439.3 | 345106.9 | 4993 | Project is not in the WP or in 2020 WP | 0 | 4993 | -4993 | 4993 | -4993 | 4993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35110372 | BR-03-04-W (E) SWEETBRIAR PARB |  | 5786123 | FICL | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2020 |  |  | CHICO | North Valley Assets | [10 empty] | GC | 558171.9 | -491828.1 | 1050000 | 964340.3 | 0 | 85659.7 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 521430.4 | 442909.9 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | FICL | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 7341 | 7341 | 1.3903 | 1.3903 | 0 | 7341 | 0 | 1.3903 | 0 | Contract | 5585619 | 1694081.1 | 3891537.9 | 2167282 | 0 | 1724255.9 | On/Under Budget | 129932 | 13769 | -20 | 13789 | 0 | 15536.1 | 2096578.1 | 55147.8 | Project is not in the WP or in 2020 WP | 75000 | 198868.8 | -123868.8 | 198868.8 | -123868.8 | 1287.8 | -72375.4 | 126255.4 | 13769 | 13769 | 13769 | 13768 | 13769 | 74857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145761 | BL-0: | BL-0: 35112429_CWSP - El Dorado 2101 - OCB Zone - Ph 1.6_08W - Oct.2020 | 2020-07-23 | 2019-10-15 | Completed | 2019-11-26 | 2019-11-26 | Completed | 2020-03-02 | Completed | 2019-11-27 | Completed | 2019-11-26 | 2019-11-26 | Completed | 2020-03-02 | 2020-03-02 | Completed | 2020-03-06 | 2020-03-06 | Completed | 2020-03-09 | Completed |  |  |  |  | 2020-03-09 | Completed | 2020-05-29 | Completed | 2020-07-07 | Completed | 2020-10-01 | 2020-07-18 | 75 | On/ Ahead Schedule | Completed | 2020-08-21 | 2020-08-21 | Completed | 2021-04-02 | Not Started
35181924 | BUCOCAMPTUG ROE RD/WILSON LN PARADISE |  | 5791246 | FICL | 08W | J4VB | Jorge Vargas | Fire Rebuild | Fire Rebuild | Fire Rebuild | Fire Rebuild | Not in the WP |  |  | CHICO | [26 empty] | 1787.6 | Project is not in the WP or in 2020 WP | 0 | 1787.6 | -1787.6 | 0 | 0
35179069 | BUCOCAMPTUG WILDWOOD LN PARADISE |  | 5791246 | FICL | 08W | J4VB | Jorge Vargas | Fire Rebuild | Fire Rebuild | Fire Rebuild | Fire Rebuild | Not in the WP |  |  | CHICO | [26 empty] | 48588.8 | Project is not in the WP or in 2020 WP | 0 | 48588.8 | -48588.8 | 0 | 0
35179328 | BUCOCAMPTUG SUN RIVER CT PARADISE |  | 5791246 | FICL | 08W | J4VB | Jorge Vargas | Fire Rebuild | Fire Rebuild | Fire Rebuild | Fire Rebuild | Not in the WP |  |  | CHICO | [26 empty] | 172550.9 | Project is not in the WP or in 2020 WP | 0 | 171971.7 | -171971.7 | 0 | 0
35181318 | BUCOCAMPTUG 6650 WHITTALL LN PARADISE |  | 5791246 | FICL | 08W | J4VB | Jorge Vargas | Fire Rebuild | Fire Rebuild | Fire Rebuild | Fire Rebuild | Not in the WP |  |  | CHICO | [26 empty] | 36819.6 | Project is not in the WP or in 2020 WP | 0 | 36819.6 | -36819.6 | 0 | 0
74022040 | 2019 CALISTOGA 1101 HIGH SPLICE COUNT |  | 5782596 | FICL | 08W | S2WT | Steve Whitman |  |  |  |  | Not in the WP |  | SH | NAPA |  | 0 | 6652.8 | 6652.8 | 1.26 | 1.26 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | E.5014772.01 | 5782858 | FICL | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2020 | 2020 | SH | NAPA | North Bay Assets | 0 | 5108 | 5108 | 0.96742 | 0.96742 | 0 | 5124 | 5124 | 0.97045 | 0.97045 | Contract | 2850000 | 0.4 | 2849999.6 | 2692677.1 | 7728.4 | 165050.9 | On/Under Budget | 0 | 0 | -380 | 380 | 15808.3 | 309965.1 | 2252345.5 | 114178.3 | Project is not in the WP or in 2020 WP | 0 | 114558.3 | -114558.3 | 114558.3 | -114558.3 | 1149.7 | 0 | 113408.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2019-08-08 | Completed | 2019-08-20 | 2019-08-21 | Completed | 2019-09-02 | Completed | 2019-08-19 | Completed | 2019-08-23 | 2019-08-26 | Completed | 2019-10-01 | 2019-10-02 | Completed | 2019-09-17 | 2019-09-17 | Completed | 2019-12-02 | Completed |  |  |  |  | 2019-12-02 | Completed | 2019-12-04 | Completed | 2020-05-21 | Completed | 2020-06-02 | 2020-05-21 | 12 | On/ Ahead Schedule | Completed | 2020-05-25 | 2020-05-29 | Completed | 2021-04-02 | Not Started
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | E.5014312.01 | 5537523 | FICL | 08W | A1CO | Antonio Miguel Chan | SHMG | Safeer Mirza | J7TY | Jace Thorsen | 2020 | 2019 | SH | OAKPORT | East Bay Assets | 3810 | 0 | 3810 | 0.72159 | 0.72159 | 0 | 3677 | 8409 | 0.6964 | 1.5926 | Division | 5476214 | 157404.8 | 5318809.2 | 4478214.1 | 0 | 840595.1 | On/Under Budget | 0 | 0 | 0 | 0 | 122873 | 474927.2 | 3874499.7 | 5914.2 | Project is not in the WP or in 2020 WP | 0 | 15234 | -15234 | 5914.2 | -5914.2 | -5717.4 | 6770.8 | 4860.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 152835 | BL-1 | BL-1 74022388_Oakland X 1104_08W - Dec. 2020 | 2020-12-29 | 2019-10-08 | Completed | 2019-12-16 | 2019-12-16 | Completed | 2020-01-15 | Completed | 2019-12-13 | Completed | 2019-12-19 | 2019-12-19 | Completed | 2019-12-19 | 2019-12-20 | Completed |  |  |  | 2020-02-14 | Completed | 2020-02-03 | Completed | 2020-05-15 | Completed | 2020-02-14 | Completed | 2020-07-10 | Completed | 2020-12-01 | Completed | 2020-12-01 | 2020-12-01 | 0 | On/ Ahead Schedule | Completed | 2020-10-12 | 2020-11-06 | Completed | 2021-04-16 | Not Started
74022664 | CAMP FIRE RECONDUCTOR LINE DEPOT RD |  | 5783322 | FICL | 08W | JXF8 | Joseph Fong |  |  |  |  | Not in the WP |  |  | CHICO | [26 empty] | 1532.5 | Project is not in the WP or in 2020 WP | 0 | 1532.5 | -1532.5 | 0 | 0
74022720 | CWSP-CAMP FIRE PADSE 1105 INST BIKE PATH |  | 5783286 | FICL | 08W | JXF8 | Joseph Fong |  |  |  |  | Not in the WP |  |  | CHICO | [26 empty] | 318.7 | Project is not in the WP or in 2020 WP | 0 | 318.7 | -318.7 | 0 | 0
74022615 | CWSP - CAMP FIRE PADSE 1105 PENTZ RD |  | 5783284 | FICL | 08W | JXF8 | Joseph Fong |  |  |  |  | Not in the WP |  |  | CHICO | [26 empty] | 9.8 | Project is not in the WP or in 2020 WP | 0 | 9.8 | -9.8 | 0 | 0
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | E.5014543.01 | 5782579 | MAPP | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2020 | 2020 | SH | OAKLAND | East Bay Assets | 0 | 14577.5 | 14577.5 | 2.7609 | 2.7609 | 0 | 15088 | 14748 | 2.8576 | 2.7932 | Contract | 8217834 | 0 | 8217834 | 8062435.9 | 7843.7 | 163241.8 | On/Under Budget | 0 | 0 | 0 | 0 | 310407.9 | 7141950.5 | 779241.7 | -169164.2 | Project is not in the WP or in 2020 WP | 0 | -169164.2 | 169164.2 | -169164.2 | 169164.2 | -171797.8 | -1770.7 | 4404.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 147017 | BL-0 | BL-0 74021963_Oakland K 1102_08W - JULY 2020 | 2020-08-11 | 2019-05-20 | Completed | 2019-01-11 | 2019-02-08 | Completed | 2019-04-28 | Completed | 2019-09-16 | Completed | 2019-08-12 | 2019-08-12 | Completed |  |  |  | 2019-09-03 | 2019-09-20 | Completed | 2019-08-26 | Completed |  |  |  |  | 2019-08-26 | Completed |  |  | 2020-06-02 | Completed | 2020-07-31 | 2020-06-02 | 59 | On/ Ahead Schedule | Completed |  |  |  | 2021-04-02 | Not Started
35112433 | CWSP - EL DORADO 2102 - LR19562 - PH 1.3 | E.5015687.04 | 5785647 | MAPP | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 10543 | 10543 | 1.9968 | 1.9968 | 0 | 10122 | 10205 | 1.917 | 1.9328 | Contract | 4151673 | 1283936.9 | 2867736.1 | 2700837.5 | 0 | 166898.6 | On/Under Budget | 74847 | 0 | 0 | 0 | 0 | 11601.3 | 2689083.6 | 152.6 | Project is not in the WP or in 2020 WP | 75000 | 74999.6 | 0.4 | 74999.6 | 0.4 | 0 | 152.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145863 | BL-0 | BL-0 35112433_CWSP - El Dorado 2102 - LR 19562 - Ph 1.3_08W - May 2020 | 2020-07-25 | 2019-10-11 | Completed | 2020-03-06 | 2020-03-26 | Completed | 2020-03-02 | Completed | 2020-03-06 | Completed | 2020-03-06 | 2020-03-06 | Completed | 2020-03-02 | 2020-03-02 | Completed | 2020-02-27 | 2020-04-07 | Completed | 2020-03-27 | Completed |  |  |  |  | 2020-03-27 | Completed | 2020-05-01 | Completed | 2020-05-01 | Completed | 2020-05-01 | 2020-05-01 | 0 | On/ Ahead Schedule | Completed | 2020-05-15 | 2020-05-29 | Completed | 2021-04-02 | Not Started
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | E.5014745.06 | 5785995 | MAPP | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | JACKSON | Stockton Assets | 0 | 5808 | 5808 | 1.1 | 1.1 | 0 | 6126 | 6126 | 1.1602 | 1.1602 | GC | 3012702 | 776765.3 | 2235936.7 | 1135291 | 0 | 1100645.7 | On/Under Budget | 0 | 0 | -250 | 250 | 0 | 213.7 | 1071144.6 | 63682.7 | Request 2021 Budget | 0 | 63932.7 | -63932.7 | 63932.7 | -63932.7 | 2717.4 | 4859.5 | 56355.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 154889 | BL-1 | BL-1 35114044_CWSP - PINE GROVE 1102 - LR1222 - PH 1.6_08W - DD 210108 Feb. 2021 | 2021-01-22 | 2020-04-15 | Completed | 2020-06-02 | 2020-07-16 | Completed | 2020-05-13 | Completed | 2020-07-16 | Completed | 2020-07-29 | 2020-07-29 | Completed | 2020-07-29 | 2020-08-28 | Completed | 2020-07-20 | 2020-09-03 | Completed | 2020-08-12 | Completed |  |  |  |  | 2020-08-12 | Completed | 2021-02-24 | Completed | 2020-08-26 | Completed | 2021-02-23 | 2021-02-25 | -2 | Behind Schedule | Completed | 2021-03-04 | 2021-03-05 | Completed | 2021-04-16 | Not Started
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | E.5014726.06 | 5786011 | MAPP | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2020 |  | SH | JACKSON | Stockton Assets | 0 | 11757 | 11757 | 2.2267 | 2.2267 | 0 | 11757 | 0 | 2.2267 | 0 | Contract | 4620298 | 1421971 | 3198327 | 1130929.5 | 209994.4 | 2277391.9 | On/Under Budget | 0 | 0 | -26184.4 | 26184.4 | 0 | 1292.8 | 1122470.1 | -19017.8 | Project is not in the WP or in 2020 WP | 0 | 7166.6 | -7166.6 | 7166.6 | -7166.6 | 4138.8 | 1609.5 | 1418.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 154933 | BL-0 | BL-0 35113102_CWSP - WEST POINT 1101 -LR 13444- PH 2.6_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-03-20 | Completed | 2020-05-01 | 2020-05-19 | Completed | 2020-05-13 | Completed | 2020-05-19 | Completed | 2020-07-31 | 2020-07-31 | Completed | 2020-07-31 | 2020-08-21 | Completed | 2020-07-10 | 2020-07-17 | Completed | 2020-08-24 | Completed |  |  |  |  | 2020-08-24 | Completed | 2020-10-03 | Completed | 2020-09-10 | Completed | 2020-10-03 | 2020-10-03 | 0 | On/ Ahead Schedule | Completed | 2020-10-03 | 2020-10-03 | Completed | 2021-04-16 | Not Started
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE | P.11939 | 5530168 | MAPP | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | Not in the WP |  | SH | NAPA | North Bay Assets | 0 | 6705.6 | 6705.6 | 1.27 | 1.27 | 0 | [5 empty] | 3937382 | 0 | 3937382 | 3918024.7 | 0 | 19357.3 | On/Under Budget | 0 | 0 | 0 | 0 | 689101.9 | 2636266.8 | 575750.5 | 16905.5 | Project is not in the WP or in 2020 WP | 0 | 16905.5 | -16905.5 | 16905.5 | -16905.5 | 0 | 16905.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | E.5015533.04 | 5785610 | MAPP | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 12344 | 12344 | 2.3379 | 2.3379 | 0 | 13219 | 12081 | 2.5036 | 2.2881 | Contract | 5748253 | 225417.1 | 5522835.9 | 5295742.1 | 0 | 227093.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 3494061.7 | 1800978.5 | 701.8 | Project is not in the WP or in 2020 WP | 0 | 701.8 | -701.8 | 701.8 | -701.8 | 199.9 | 701.8 | -199.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145809 | BL-0: | BL-0: 35109739_CWSP - Volta 1102 - LR 1648 - Ph2.4_08W - Jan 2020 | 2020-07-24 | 2019-09-20 | Completed | 2019-09-13 | 2019-09-13 | Completed | 2019-08-20 | Completed | 2019-09-20 | Completed | 2019-12-23 | 2019-12-23 | Completed | 2020-01-10 | 2020-01-10 | Completed | 2019-09-25 | 2019-10-15 | Completed | 2019-10-19 | Completed |  |  |  |  | 2019-10-19 | Completed |  |  | 2020-01-23 | Completed | 2020-01-23 | 2020-01-23 | 0 | On/ Ahead Schedule | Completed | 2020-05-04 | 2020-05-19 | Completed | 2021-04-02 | Not Started
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | E.5015428.02 | 5785616 | MAPP | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 8668 | 8668 | 1.6417 | 1.6417 | 0 | 10160 | 9066 | 1.9242 | 1.717 | Contract | 5440290 | 0.9 | 5440289.1 | 4616838.8 | 34797.6 | 858247.9 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 4039029.7 | 542595.4 | 35213.6 | Project is not in the WP or in 2020 WP | 0 | 35213.6 | -35213.6 | 35213.6 | -35213.6 | 31047.2 | 403 | 3763.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145814 | BL-0: | BL-0: 35110445_CWSP - Volta 1102 - LR 1648 - Ph4.2_08W - Dec 2019 | 2020-07-24 | 2019-08-27 | Completed | 2019-09-10 | 2019-09-11 | Completed | 2019-08-14 | Completed | 2019-08-27 | Completed | 2019-09-12 | 2019-09-12 | Completed | 2019-09-26 | 2019-09-26 | Completed | 2019-09-09 | 2019-11-05 | Completed | 2019-10-16 | Completed |  |  |  |  | 2019-10-16 | Completed |  |  | 2019-12-26 | Completed | 2019-12-26 | 2019-12-26 | 0 | On/ Ahead Schedule | Completed | 2020-05-12 | 2020-05-29 | Completed | 2021-05-03 | Not Started
35110369 | BR-03-03-W (E) GINNY_SUNRISE PARB |  | 5786123 | MAPP | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2020 |  |  | CHICO | North Valley Assets | [10 empty] | Contract | 1081333.96 | -758871.04 | 1840205 | 1718830.7 | 0 | 121374.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 784828.4 | 934002.3 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35110377 | BR-03-10-W (E) SHAY LN PARB |  | 5786123 | MAPP | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2020 |  |  | CHICO | North Valley Assets | [10 empty] | Contract | 2448690.3 | -651309.7 | 3100000 | 2998028.4 | 0 | 101971.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 2546046.2 | 440753.3 | 11228.9 | Project is not in the WP or in 2020 WP | 0 | 11228.9 | -11228.9 | 11228.9 | -11228.9 | 0 | 11228.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 | E.5015428.05 | 5785619 | MAPP | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 10503 | 10503 | 1.9892 | 1.9892 | 0 | 10301 | 10620 | 1.9509 | 2.0114 | Contract | 6475096 | 923719.7 | 5551376.3 | 4619755.5 | 0 | 931620.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 2017962.8 | 2598592.8 | 3199.9 | Project is not in the WP or in 2020 WP | 0 | 3199.9 | -3199.9 | 3199.9 | -3199.9 | 0 | 0 | 3199.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145817 | BL-0: | BL-0: 35110448_CWSP - Volta 1102 - LR 1648 - Ph4.5_08W - May 2020 | 2020-07-24 | 2019-09-23 | Completed | 2020-02-05 | 2020-02-06 | Completed | 2019-10-08 | Completed | 2019-10-18 | Completed | 2019-09-24 | 2019-09-24 | Completed | 2019-10-08 | 2019-10-08 | Completed | 2019-11-15 | 2020-01-05 | Completed | 2020-02-03 | Completed |  |  |  |  | 2020-04-06 | Completed |  |  | 2020-05-28 | Completed | 2020-05-28 | 2020-05-28 | 0 | On/ Ahead Schedule | Completed | 2020-06-01 | 2020-12-12 | Completed | 2021-04-02 | Not Started
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 | E.5015533.06 | 5785612 | MAPP | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 11791 | 11791 | 2.2331 | 2.2331 | 0 | 11790 | 11791 | 2.233 | 2.2331 | Contract | 4651895 | 430668 | 4221227 | 3294883.6 | 0 | 926343.4 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 418997.1 | 2875586.1 | 300.4 | Project is not in the WP or in 2020 WP | 0 | 300.4 | -300.4 | 300.4 | -300.4 | 0 | 300.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145811 | BL-0: | BL-0: 35110441_CWSP - Volta 1102 - LR 1648 - Ph2.6_08W -May 2020 | 2020-07-24 | 2019-10-03 | Completed | 2019-10-16 | 2019-10-16 | Completed | 2019-09-18 | Completed | 2019-10-17 | Completed | 2019-10-07 | 2019-10-07 | Completed | 2019-10-21 | 2019-10-21 | Completed | 2019-10-22 | 2020-01-05 | Completed | 2020-02-01 | Completed |  |  |  |  | 2020-02-17 | Completed |  |  | 2020-05-04 | Completed | 2020-05-04 | 2020-05-04 | 0 | On/ Ahead Schedule | Completed | 2020-05-11 | 2020-05-28 | Completed | 2021-04-02 | Not Started
35112076 | OCGC FULTON 1107-OH TO UG MARK W SPG |  | 5786045 | MAPP | 08W | S2WT | Steve Whitman |  |  |  |  | 2020 |  | SH | STROSA |  | 3657 | 7969 | 11626 | 2.2019 | 2.2019 | 3.4451e-16 | 11799 | 11799 | 2.2347 | 2.2347 | GC | [15 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | E.5014748.01 | 5785242 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 10300 | 10300 | 1.9508 | 0 | 1.9508 | [5 empty] | 250000 | 0 | 250000 | 55158.9 | 0 | 194841.1 | On/Under Budget | 3705313 | 625.9 | 0 | 625.9 | 0 | 14805.1 | 38082.2 | 2271.5 | Project is not in the WP or in 2020 WP | 0 | 3210.4 | -3210.4 | 3210.4 | -3210.4 | 20623.7 | 1493.3 | -19845.5 | 625.9 | 313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1602500 | 1602500 | 0 | 0 | 0 | 0 | 3705000 | 2021-04-02 | 155000 | BL-A | BL-A 35094516_CWSP - ORO FINO 1101 OCB PH 1.1_08W - Jan. 2021 | 2021-01-25 | 2020-10-29 | Completed | 2022-09-02 | 2022-09-08 | Not Started | 2021-04-30 | Not Started | 2022-09-08 | Not Started | 2022-09-09 | 2022-09-09 | Not Started | 2022-09-12 | 2022-09-16 | Not Started | 2021-04-16 | 2021-04-16 | Not Started | 2022-09-26 | Not Started |  |  |  |  | 2022-09-26 | Not Started | 2022-10-20 | Not Started | 2022-11-01 | Not Started | 2022-11-15 | 2022-11-29 | -14 | Behind Schedule | Not Started | 2022-11-30 | 2022-12-13 | Not Started | 2023-01-19 | Not Started
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | E.5014747.01 | 5785241 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 7634 | 7634 | 1.4458 | 0 | 1.4458 | [5 empty] | 333333 | 0 | 333333 | 80329.5 | 0 | 253003.5 | On/Under Budget | 2761500.5 | 497.9 | 0 | 497.9 | 0 | 7879.9 | 69449.3 | 3000.4 | Project is not in the WP or in 2020 WP | 0 | 7590.7 | -7590.7 | 7590.7 | -7590.7 | 40598.4 | -38025.7 | 427.7 | 497.9 | 497.9 | 497.9 | 516.1 | 516.1 | 516.1 | 516.1 | 516.1 | 516.1 | 535.1 | 535.1 | 535.1 | 535.1 | 267.6 | 0 | 0 | 0 | 500000 | 1127500 | 1127500 | 0 | 2757408 | 2021-04-02 | 155001 | BL-A | BL-A 35094517_CWSP - ORO FINO 1101 OCB PH 2.1_08W - Jan. 2021 | 2021-01-25 | 2020-10-29 | Completed | 2022-08-26 | 2022-08-26 | Not Started | 2021-04-29 | Not Started | 2022-08-29 | Not Started | 2022-08-29 | 2022-08-29 | Not Started | 2022-08-30 | 2022-08-30 | Not Started | 2021-04-05 | 2021-04-05 | Not Started | 2022-09-07 | Not Started |  |  |  |  | 2022-09-07 | Not Started | 2022-09-12 | Not Started | 2022-09-21 | Not Started | 2022-07-15 | 2022-09-23 | -70 | Behind Schedule | Not Started | 2022-09-26 | 2022-09-30 | Not Started | 2022-11-15 | Not Started
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | E.5015394.01 | 5785246 | PEND | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 5899 | 5899 | 1.1172 | 0 | 1.1172 | [5 empty] | 1059112.65 | -1306840.45 | 2365953.1 | 132736.8 | 561723.2 | 2794939.5 | On/Under Budget | 1321561.3 | 199.6 | 0 | 199.6 | 0 | 16758.1 | 112878.7 | 3100 | Project is not in the WP or in 2020 WP | 0 | 3599 | -3599 | 3599 | -3599 | 310.8 | 2071.5 | 717.7 | 199.6 | 199.6 | 99.8 | 0 | 0 | 0 | 0 | 0 | 0 | 80592.7 | 759623.7 | 692663.3 | 9091 | -220709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1321261.7 | 2021-04-02 | 154917 | BL-0 | BL-0 35095167_CWSP - STANISLAUS 1702 - LR1888 - PH 2.1_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-07-07 | Completed | 2020-07-30 | 2020-08-13 | Completed | 2022-02-22 | Not Started | 2022-02-23 | Not Started | 2022-02-02 | 2022-02-02 | Not Started | 2022-02-03 | 2022-02-16 | Not Started | 2020-11-05 | 2022-02-07 | In Progress | 2022-03-14 | Not Started |  |  |  |  | 2022-03-14 | Not Started | 2022-04-19 | Not Started | 2022-05-03 | Not Started | 2022-05-09 | 2022-05-09 | 0 | On/ Ahead Schedule | Not Started | 2022-05-18 | 2022-05-31 | Not Started | 2022-06-29 | Not Started
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | E.5015701.01 | 5785247 | PEND | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 6718 | 6718 | 1.2723 | 0 | 1.2723 | [5 empty] | 1296538.52 | 1046538.52 | 250000 | 128016.8 | 0 | 121983.2 | On/Under Budget | 1825283.9 | 0 | 0 | 0 | 0 | 14217.5 | 137065.6 | -23266.3 | Project is not in the WP or in 2020 WP | 0 | -23266.3 | 23266.3 | -23266.3 | 23266.3 | -24855.6 | 688.3 | 901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37371.4 | 33851.2 | 1148485.4 | 838159.9 | 0 | 0 | 0 | -232584 | 0 | 0 | 0 | 0 | 1825283.9 | 2021-04-02 | 154922 | BL-B | BL-B 35095168_CWSP - STANISLAUS 1702 - LR1888 - PH 1.1_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-08-11 | Completed | 2020-10-28 | 2022-02-07 | Not Started | 2022-02-07 | Not Started | 2022-02-08 | Not Started | 2022-02-08 | 2022-02-08 | Not Started | 2022-02-09 | 2022-02-22 | Not Started | 2020-10-23 | 2022-02-07 | In Progress | 2022-03-02 | Not Started |  |  |  |  | 2022-03-02 | Not Started | 2022-04-21 | Not Started | 2022-05-05 | Not Started | 2022-08-05 | 2022-08-05 | 0 | On/ Ahead Schedule | Not Started | 2022-08-08 | 2022-08-19 | Not Started | 2022-09-27 | Not Started
35105653 | BR-14-01-W (E) SALIDA WAY, PARB |  | 5786123 | PEND | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | 2021 |  |  | CHICO | North Valley Assets | [11 empty] | 2505596.45 | -738101.55 | 3243698 | 2166033 | 0 | 1077665 | On/Under Budget | 0 | 403878.5 | 0 | 403878.5 | 0 | 5529.9 | 1383128.3 | 777374.7 | Request 2021 Budget | 0 | 1181253.2 | -1181253.2 | 1181253.2 | -1181253.2 | 319194.1 | 235349.1 | 222831.5 | 403878.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35103617 | BR-07-09-W (E) WOODGLEN PARB |  | 5786123 | PEND | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | 2021 |  |  | CHICO | North Valley Assets | [6 empty] | 11811 | 0 | 2.2369 | 0 |  | 4528627.2 | 60605.2 | 4468022 | 34521 | 130649.2 | 4564150.2 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34521 | Request 2021 Budget | 0 | 34521 | -34521 | 34521 | -34521 | 0 | 0 | 34521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | E.5014540.01 | 5785245 | PEND | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | ANGLSCMP | Stockton Assets | 172 | 9383 | 9555 | 1.8097 | 0 | 1.8097 | 10124 | 0 | 1.9174 | 0 | Contract | 3142865.56 | 2892865.56 | 250000 | 204933.1 | 0 | 45066.9 | On/Under Budget | 3473091.9 | 6515.8 | 0 | 6515.8 | 0 | 27301.9 | 147122.6 | 30508.6 | Budget Allocated | 4178901 | 4009217.3 | 169683.7 | 4009217.3 | 169683.7 | 11008.6 | 15687.8 | 3812.2 | 6515.8 | 1016068.1 | 989534.9 | 1048402.6 | 893855.1 | 19172.5 | 5159.7 | 0 | 0 | -499101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -499101 | 2021-04-02 | 154906 | BL-B | BL-B 35094513_CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-06-29 | Completed | 2021-02-08 | 2021-03-04 | Completed | 2021-10-05 | Not Started | 2021-10-06 | Not Started | 2021-12-08 | 2021-12-08 | Not Started | 2021-12-09 | 2021-12-22 | Not Started | 2021-10-20 | 2021-11-30 | Not Started | 2021-12-30 | Not Started |  |  |  |  | 2021-12-30 | Not Started | 2022-03-08 | Not Started | 2022-03-09 | Not Started | 2021-10-07 | 2022-05-09 | -214 | Behind Schedule | Not Started | 2022-05-10 | 2022-05-23 | Not Started | 2022-06-27 | Not Started
35094514 | CWSP-ORO FINO 1101 LR-2022 PH 1.1 | E.5014760.01 | 5785244 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 6756 | 6756 | 1.2795 | 0 | 1.2795 | [5 empty] | 262500 | 0 | 262500 | 65836 | 0 | 196664 | On/Under Budget | 2432546.4 | 82 | 0 | 82 | 0 | 9725.4 | 54961.6 | 1149 | Project is not in the WP or in 2020 WP | 0 | 1777.5 | -1777.5 | 1777.5 | -1777.5 | 395.4 | 376.8 | 376.8 | 82 | 82 | 82 | 85 | 85 | 85 | 85 | 42.5 | 0 | 0 | 0 | 0 | 0 | 500000 | 966000 | 966000 | 0 | 0 | 0 | 0 | 0 | 2432000 | 2021-04-02 |  |  |  |  | 2020-08-04 | Completed | 2021-12-02 | 2021-12-02 | Not Started | 2021-04-02 | Not Started | 2021-12-09 | Not Started | 2021-12-02 | 2021-12-02 | Not Started | 2021-12-03 | 2021-12-23 | Not Started | 2021-04-23 | 2021-07-16 | Not Started | 2022-01-13 | Not Started |  |  |  |  | 2022-01-13 | Not Started | 2022-04-01 | Not Started | 2022-05-02 | Not Started | 2022-07-01 | 2022-07-01 | 0 | On/ Ahead Schedule | Not Started | 2022-07-04 | 2022-07-15 | Not Started | 2022-08-23 | Not Started
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | E.5014719.01 | 5785225 | PEND | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 132 | 3625 | 3757 | 0.71155 | 0 | 0.71155 | [5 empty] | 250000 | 0 | 250000 | 104668.1 | 0 | 145331.9 | On/Under Budget | 51.4 | 102.7 | 0 | 102.7 | 0 | 9178.3 | 93436.1 | 2053.7 | Project is not in the WP or in 2020 WP | 0 | 2207.8 | -2207.8 | 2207.8 | -2207.8 | 795.8 | 658.8 | 599.1 | 102.7 | 51.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2020-08-01 | Completed | 2022-04-22 | 2022-04-28 | Not Started | 2022-04-15 | Not Started | 2022-05-05 | Not Started | 2022-04-22 | 2022-04-22 | Not Started | 2022-04-25 | 2022-07-15 | Not Started | 2022-04-19 | 2022-04-20 | Not Started | 2022-08-15 | Not Started |  |  |  |  | 2022-08-15 | Not Started | 2022-08-24 | Not Started | 2022-09-23 | Not Started | 2022-10-18 | 2022-10-18 | 0 | On/ Ahead Schedule | Not Started | 2022-10-19 | 2022-11-01 | Not Started | 2022-12-08 | Not Started
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | E.5014718.01 | 5785226 | PEND | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 6398 | 6398 | 1.2117 | 0 | 1.2117 | [5 empty] | 1563870.91 | 1313870.91 | 250000 | 148620.1 | 0 | 101379.9 | On/Under Budget | 847.8 | 238.5 | 0 | 238.5 | 0 | 13737.6 | 134610.1 | 272.4 | Project is not in the WP or in 2020 WP | 0 | 1358.7 | -1358.7 | 1358.7 | -1358.7 | -1428.8 | 850.6 | 850.6 | 238.5 | 238.5 | 238.5 | 247.2 | 123.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2022-04-21 | Not Started | 2022-05-06 | 2022-05-12 | Not Started | 2022-05-05 | Not Started | 2022-05-19 | Not Started | 2022-04-22 | 2022-04-22 | Not Started | 2022-04-25 | 2022-07-15 | Not Started | 2022-05-06 | 2022-05-12 | Not Started | 2022-08-15 | Not Started |  |  |  |  | 2022-08-15 | Not Started | 2022-10-14 | Not Started | 2022-11-03 | Not Started | 2022-11-08 | 2022-11-08 | 0 | On/ Ahead Schedule | Not Started | 2022-11-11 | 2022-11-24 | Not Started | 2022-12-29 | Not Started
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | P.12006 | 5533644 | PEND | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2022 |  | SH | STCRUZ | Central Coast Assets | 0 | 4470 | 4470 | 0.84659 | 0 | 0.84659 | 4555 | 0 | 0.86269 | 0 |  | 5136422 | 2235896 | 2900526 | 78615.4 | 0 | 2821910.6 | On/Under Budget | 1435339.6 | 7446.2 | 0 | 7446.2 | 0 | 38211 | 36274.8 | 4129.7 | Request 2021 Budget | 0 | 1446915.8 | -1446915.8 | 1446915.8 | -1446915.8 | 1248 | 2388.8 | 492.9 | 7446.2 | 7446.2 | 7446.2 | 407929.6 | 1002922.7 | 2398.8 | 2398.8 | 2398.8 | 2398.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | PEND | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | PLCRVLLE | Sierra Assets | 1930 | 9322 | 11252 | 2.1311 | 0 | 2.1311 | [5 empty] | 725000 | 0 | 725000 | 591109.5 | 0 | 133890.5 | On/Under Budget | 1695.7 | 1130.4 | 0 | 1130.4 | 5457.6 | 78836.1 | 492869.2 | 13946.6 | Project is not in the WP or in 2020 WP | 0 | 16772.6 | -16772.6 | 16772.6 | -16772.6 | 3628 | 4866.9 | 5451.7 | 1130.4 | 1130.4 | 565.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158110 | BL-A_ | BL-A_35056733_CWSP - El Dorado 2101 - 19752 - Ph 1.1_08W_Mar.2021 | 2021-03-30 | 2020-08-31 | Completed | 2022-02-01 | 2022-02-07 | Not Started | 2022-01-31 | Not Started | 2022-03-07 | Not Started | 2022-01-11 | 2022-01-11 | Not Started | 2022-01-12 | 2022-02-01 | Not Started | 2022-01-25 | 2022-02-21 | Not Started | 2022-03-30 | Not Started |  |  |  |  | 2022-03-30 | Not Started | 2022-08-02 | Not Started | 2022-08-31 | Not Started | 2022-11-23 | 2022-11-23 | 0 | On/ Ahead Schedule | Not Started | 2022-11-24 | 2022-12-07 | Not Started | 2023-01-13 | Not Started
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | 5530176 | PEND | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | ANGLSCMP | Stockton Assets | 0 | 3115.2 | 3115.2 | 0.59 | 0 | 0.59 | 3362 | 0 | 0.63674 | 0 | Contract | 403045.55 | 103045.95 | 299999.6 | 107982.2 | 0 | 192017.4 | On/Under Budget | 341043.5 | 71683 | 0 | 71683 | 0 | 3720.4 | 0 | 104261.9 | Request 2021 Budget | 0 | 516988.4 | -516988.4 | 516988.4 | -516988.4 | 33322.3 | 63698.4 | 7241.2 | 71683 | 204737.3 | 125283.5 | 4399.4 | 2948.1 | 592.4 | 1384.9 | 1310.8 | 387.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-03-11 | Completed | 2021-04-19 | 2021-05-07 | Not Started | 2021-04-30 | Not Started | 2021-05-07 | Not Started | 2021-05-10 | 2021-05-10 | Not Started | 2021-05-11 | 2021-05-31 | Not Started | 2021-04-13 | 2021-04-26 | Not Started | 2021-06-29 | Not Started |  |  |  |  | 2021-06-29 | Not Started | 2021-08-02 | Not Started | 2021-08-09 | Not Started | 2021-09-20 | 2021-09-20 | 0 | On/ Ahead Schedule | Not Started | 2021-09-21 | 2021-09-27 | Not Started | 2021-11-10 | Not Started
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | E.0000106.01 | 5782594 | PEND | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | MONTEREY | Central Coast Assets | 0 | 24027 | 24027 | 4.5506 | 0 | 4.5506 | [5 empty] | 176000 | 0 | 176000 | 90234.3 | 0 | 85765.7 | On/Under Budget | 9200395.9 | 0 | 0 | 0 | 9826.4 | 32607.8 | 46287.6 | 1512.4 | Project is not in the WP or in 2020 WP | 0 | 1512.4 | -1512.4 | 1512.4 | -1512.4 | 507.2 | 484 | 521.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1594978.2 | 1594978.2 | 318398.7 | 2944465.5 | 2747575.3 | 0 | 0 | 0 | 9200395.9
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | E.5014733.01 | 5785238 | PEND | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2022 |  | SH | SONORA | Yosemite Assets | 0 | 8605 | 8605 | 1.6297 | 0 | 1.6297 | 8378 | 0 | 1.5867 | 0 | GC | 2768676 | 708455.8 | 2060220.2 | 109643.6 | 200 | 1950776.6 | On/Under Budget | 1847192.6 | 318.7 | 0 | 318.7 | 2635.1 | 7757.3 | 74639.8 | 24611.4 | Request 2021 Budget | 0 | 26393.5 | -26393.5 | 26393.5 | -26393.5 | 3826 | 20393 | 392.4 | 318.7 | 318.7 | 318.7 | 330.4 | 330.4 | 165.2 | 0 | 0 | 0 | 3925.2 | 971680.7 | 602556.6 | 261091.5 | 6475.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1845729.3 | 2021-04-02 | 151438 | BL-1 | BL-1 35052737_CWSP - MIWUK 1701 - LR 8060 - PH 1.1_08W - Nov. 2020 | 2020-11-12 | 2020-01-03 | Completed | 2020-05-07 | 2020-06-10 | Completed | 2021-04-30 | Not Started | 2020-05-12 | Completed | 2021-12-02 | 2021-12-03 | Not Started | 2021-12-06 | 2021-12-07 | Not Started | 2021-05-03 | 2021-05-03 | Not Started | 2022-03-02 | Not Started |  |  |  |  | 2022-03-02 | Not Started |  |  | 2022-04-27 | Not Started | 2021-10-25 | 2022-05-26 | -213 | Behind Schedule | Not Started | 2022-05-27 | 2022-06-09 | Not Started | 2022-07-18 | Not Started
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | E.5014542.01 | 5782530 | PEND | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 | 2021 | SH | STCRUZ | Central Coast Assets | 0 | 7779 | 7779 | 1.4733 | 0 | 1.4733 | 7779 | 0 | 1.4733 | 0 | Contract | 4994628 | 1603586.6 | 3391041.4 | 181087.3 | 362321.8 | 3572275.9 | On/Under Budget | 1757351.9 | 4234.2 | 0 | 4234.2 | 8061.7 | 11208.2 | 121487.2 | 40330.2 | Request 2021 Budget | 0 | 1801916.2 | -1801916.2 | 1801916.2 | -1801916.2 | 9459.6 | 4061 | 26809.6 | 4234.2 | 1746797.8 | 3518 | 3518 | 3518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 128567 | WSHP | WSHP 190307 - 35052731_CWSP - BIG BASIN 1101 - 10296 ZONE P June 23 2020 | 2019-03-07 | 2020-08-01 | Completed |  |  | Completed | 2021-07-01 | Not Started | 2020-08-18 | Completed | [6 empty] | 2021-05-03 | 2021-05-25 | Not Started | 2021-04-16 | Not Started |  |  |  |  | 2021-06-10 | Not Started |  |  | 2021-12-24 | Not Started | 2020-10-27 | 2021-12-25 | -424 | Behind Schedule | Not Started |  |  |  | 2022-08-04 | Not Started
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | PEND | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | PLCRVLLE | Sierra Assets | 10624 | 0 | 10624 | 2.0121 | 0 | 2.0121 | [5 empty] | 725000 | 0 | 725000 | 306600.2 | 22840.7 | 441240.5 | On/Under Budget | 40661.7 | 2514 | 0 | 2514 | 4114.5 | 386046.8 | -141026.1 | 57465 | Project is not in the WP or in 2020 WP | 0 | 80470.8 | -80470.8 | 80470.8 | -80470.8 | 45821.1 | 9178.2 | 2465.7 | 2514 | 2514 | 2514 | 2577.3 | 2577.3 | 2577.3 | 2577.3 | 2577.3 | 2577.3 | 2670.1 | 2670.1 | 2670.1 | 2670.1 | 2670.1 | 2670.1 | 2766.2 | 1383.1 | 0 | 0 | 0 | 0 | 20169.9 | 2021-04-02 | 158109 | BL-A_ | BL-A_35057018_CWSP - El Dorado 2101 - 19752 - Ph 4.1_08W_Mar.2021 | 2021-03-30 | 2020-07-17 | Completed | 2021-05-28 | 2021-06-03 | Not Started | 2021-05-27 | Not Started | 2021-06-24 | Not Started | 2021-04-02 | 2021-04-02 | Not Started | 2021-04-05 | 2021-04-23 | Not Started | 2021-04-23 | 2021-05-06 | Not Started | 2021-07-27 | Not Started |  |  |  |  | 2021-07-27 | Not Started | 2021-11-08 | Not Started | 2021-12-07 | Not Started | 2021-12-30 | 2022-01-13 | -14 | Behind Schedule | Not Started | 2022-01-14 | 2022-01-27 | Not Started | 2022-03-07 | Not Started
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | E.5014726.01 | 5785230 | PEND | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 5885 | 5885 | 1.1146 | 0 | 1.1146 | [5 empty] | 1561814.97 | 1311814.97 | 250000 | 68515.6 | 0 | 181484.4 | On/Under Budget | 1553854.7 | 0 | 0 | 0 | 2459 | 8746.7 | 49866.7 | 7443.2 | Project is not in the WP or in 2020 WP | 0 | 7443.2 | -7443.2 | 7443.2 | -7443.2 | 2357.7 | 4693.1 | 392.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 659940.1 | 557762 | 317890.8 | 6299.9 | 4784.8 | 3588.6 | 3588.6 | 0 | 0 | 0 | 0 | 0 | 1553854.8 | 2021-04-02 | 154928 | BL-B | BL-B 35043423_CWSP - WEST POINT 1101 -LR 13444- PH 2.1_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-10-05 | Completed | 2021-11-17 | 2021-12-28 | Not Started | 2022-02-04 | Not Started | 2022-02-07 | Not Started | 2021-12-29 | 2021-12-29 | Not Started | 2021-12-30 | 2021-12-31 | Not Started | 2021-11-19 | 2021-11-19 | Not Started | 2022-02-11 | Not Started |  |  |  |  | 2022-02-11 | Not Started |  |  | 2022-04-04 | Not Started | 2022-04-08 | 2022-04-08 | 0 | On/ Ahead Schedule | Not Started | 2022-04-07 | 2022-04-08 | Not Started | 2022-04-22 | Not Started
31429487 | OTTER-1101 S030CC121 – TRANS POLES |  | 5782594 | PEND | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | MONTEREY | Central Coast Assets | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 163000 | 0 | 163000 | 101847.1 | 0 | 61152.9 | On/Under Budget | 407562.5 | 0 | 0 | 0 | 0 | 45023.6 | 55013.7 | 1809.9 | Project is not in the WP or in 2020 WP | 0 | 1809.9 | -1809.9 | 1809.9 | -1809.9 | 745.1 | 532.4 | 532.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617.2 | 617.2 | 617.2 | 617.2 | 617.2 | 617.2 | 639.9 | 639.9 | 393469.5 | 3036.7 | 3036.7 | 3036.7 | 407562.6
31434881 | 0P 3100 SKYWAY RD PARADISE TUSCAN RIDGE |  | 5791419 | PEND | 08W | D2BB | David L Barrios |  |  |  |  | Not in the WP |  | SH | CHICO |  | 17735 | 0 | 17735 | 3.3589 | 3.3589 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | 5530164 | PEND | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | Not in the WP | 2021 | SH | FTBRAGG | Humboldt Division Assets | 0 | 2710 | 2710 | 0.51326 | 0 | 0.51326 | [5 empty] | 1115282 | -337210 | 1452492 | 361441.7 | 0 | 1091050.3 | On/Under Budget | 756949 | 2523.2 | 313.4 | 2209.8 | 3499 | 219550.1 | 131905.9 | 6026.5 | Project is not in the WP or in 2020 WP | 0 | 765185.2 | -765185.2 | 765185.2 | -765185.2 | 2121.6 | 919.7 | 2671.8 | 2523.2 | 0 | 252316.3 | 252316.3 | 252316.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 128590 | WSHP | WSHP 190307 - 31334291_FT BRAGG 1101 RECON-6 SPANS_08W - B1 | 2019-03-07 | 2019-10-18 | Completed | 2019-03-08 | 2019-03-29 | Completed | 2021-01-22 | Completed | 2021-07-30 | Not Started | 2019-03-29 | 2019-04-05 | Completed | 2019-04-08 | 2019-04-12 | Completed | 2021-08-02 | 2021-08-02 | Not Started | 2021-08-12 | Not Started |  |  |  |  | 2021-08-12 | Not Started |  |  | 2021-08-30 | Not Started | 2019-07-10 | 2021-08-31 | -783 | Behind Schedule | Not Started | 2021-09-07 | 2021-09-20 | Not Started | 2021-10-20 | Not Started
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | 5530159 | PEND | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2022 |  | SH | STCRUZ | Central Coast Assets | 0 | 5300 | 5300 | 1.0038 | 0 | 1.0038 | 5300 | 0 | 1.0038 | 0 |  | 99000 | 0 | 99000 | 59788.9 | 0 | 39211.1 | On/Under Budget | 1015363.3 | 7446.2 | 0 | 7446.2 | 3047.5 | 19106.1 | 36101.6 | 967.6 | Request 2021 Budget | 0 | 1023777.4 | -1023777.4 | 1023777.4 | -1023777.4 | 116.9 | 218.2 | 632.5 | 7446.2 | 7446.2 | 7446.2 | 447392.6 | 543483.4 | 2398.8 | 2398.8 | 2398.8 | 2398.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | 5531041 | PEND | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | Not in the WP | 2022 |  | HMOONBAY | Peninsula Assets | 838 | 3852 | 4690 | 0.88826 | 0 | 0.88826 | [5 empty] | 100000 | 0 | 100000 | 75986.4 | 0 | 24013.6 | On/Under Budget | 791507.6 | 1443.9 | 0 | 1443.9 | 16333.3 | 28294.6 | 25414.2 | 5944.3 | Project is not in the WP or in 2020 WP | 0 | 18939.4 | -18939.4 | 18939.4 | -18939.4 | 1618.1 | 3590.3 | 735.9 | 1443.9 | 1443.9 | 1443.9 | 1443.9 | 1443.9 | 1443.9 | 1443.9 | 1443.9 | 1443.9 | 4485.1 | 4485.1 | 4485.1 | 3088.8 | 3088.8 | 131450.4 | 628872.8 | 0 | 0 | 0 | 0 | 0 | 779956.1 | 2021-04-02 | 147006 | BL-A1 | BL-A1 35030568_TW ON HALF MOON BAY1101 FUCO 4141 - AUG 2020 | 2020-08-11 | 2019-12-31 | Completed |  |  | Not Started | 2021-06-04 | Not Started | 2021-06-04 | Not Started | 2021-06-07 | 2021-06-07 | Not Started |  |  |  | 2021-12-28 | 2022-02-07 | Not Started | 2022-04-19 | Not Started |  |  |  |  | 2022-04-19 | Not Started |  |  | 2022-07-14 | Not Started | 2021-08-02 | 2022-08-15 | -378 | Behind Schedule | Not Started |  |  |  | 2022-11-09 | Not Started
30977613 | WDDB OTTER 1102 PHASE 3 | P.06570 | 5530159 | PEND | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | MONTEREY | Central Coast Assets | 0 | 3637 | 3637 | 0.68883 | 0 | 0.68883 | [5 empty] | 355200 | 0 | 355200 | 312710.5 | 0 | 42489.5 | On/Under Budget | 929820 | 0 | 0 | 0 | 19392.6 | 77331.5 | 199091.9 | 5360.8 | Project is not in the WP or in 2020 WP | 0 | 5360.8 | -5360.8 | 5360.8 | -5360.8 | 5360.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 929820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 929820
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | E.5014542.02 | 5786124 | PEND | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | STCRUZ | Central Coast Assets | 0 | 18848 | 18848 | 3.5697 | 0 | 3.5697 | [5 empty] | 7087268 | 1963144.7 | 5124123.3 | 160430.5 | 362321.8 | 5326014.6 | On/Under Budget | 1632568.9 | 0 | 544 | -544 | 0 | 128.7 | 128603.3 | 32242.5 | Project is not in the WP or in 2020 WP | 0 | 31698.5 | -31698.5 | 31698.5 | -31698.5 | 1822.5 | 779.9 | 29096.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1632568.9 | 0 | 0 | 0 | 1632568.9
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | E.5014728.04 | 5786014 | PEND | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 7448.1 | 7448.1 | 1.4106 | 0 | 1.4106 | [5 empty] | 838375.56 | 588375.56 | 250000 | 42956.7 | 0 | 207043.3 | On/Under Budget | 2504962.8 | 0 | 0 | 0 | 0 | 580.3 | 35992 | 6384.4 | Project is not in the WP or in 2020 WP | 0 | 6384.4 | -6384.4 | 6384.4 | -6384.4 | 5228.5 | 934.4 | 221.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5741.7 | 5741.7 | 325717.4 | 713093.6 | 499744.3 | 601278.6 | 319946.5 | 7688.6 | 5741.7 | 8020.9 | 6505.9 | 5741.7 | 2504962.6 | 2021-04-02 | 154944 | BL-B | BL-B 35113995_CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-10-28 | Completed | 2021-12-13 | 2022-01-07 | Not Started | 2022-02-11 | Not Started | 2022-02-14 | Not Started | 2022-01-10 | 2022-01-10 | Not Started | 2022-01-11 | 2022-02-07 | Not Started | 2022-02-14 | 2022-02-14 | Not Started | 2022-03-23 | Not Started |  |  |  |  | 2022-03-23 | Not Started | 2022-05-19 | Not Started | 2022-05-19 | Not Started | 2022-06-20 | 2022-06-20 | 0 | On/ Ahead Schedule | Not Started | 2022-05-27 | 2022-06-09 | Not Started | 2022-08-10 | Not Started
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | E.5014728.05 | 5786015 | PEND | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  |  | JACKSON | Stockton Assets | 0 | 6270 | 6270 | 1.1875 | 0 | 1.1875 | [5 empty] | 841954.09 | 591954.09 | 250000 | 96252.6 | 0 | 153747.4 | On/Under Budget | 1621382.1 | 0 | 0 | 0 | 0 | 0 | 93366.1 | 2886.5 | Project is not in the WP or in 2020 WP | 0 | 2886.5 | -2886.5 | 2886.5 | -2886.5 | 1205.1 | 1184.7 | 496.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5741.7 | 5741.7 | 5741.7 | 28510.3 | 398599.9 | 579111.2 | 569226.9 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 1621381.9 | 2021-04-02 | 154945 | BL-B | BL-B 35113996_CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-09-18 | Completed | 2021-11-24 | 2021-12-21 | Not Started | 2022-01-11 | Not Started | 2022-01-12 | Not Started | 2021-12-22 | 2021-12-22 | Not Started | 2021-12-23 | 2022-01-19 | Not Started | 2022-01-12 | 2022-01-25 | Not Started | 2022-02-18 | Not Started |  |  |  |  | 2022-02-18 | Not Started | 2022-04-07 | Not Started | 2022-04-07 | Not Started | 2022-05-09 | 2022-05-09 | 0 | On/ Ahead Schedule | Not Started | 2022-04-15 | 2022-04-28 | Not Started | 2022-06-29 | Not Started
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | E.5014728.06 | 5786016 | PEND | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  |  | JACKSON | Stockton Assets | 0 | 6460 | 6460 | 1.2235 | 0 | 1.2235 | [5 empty] | 771395.95 | 521395.95 | 250000 | 74515.1 | 0 | 175484.9 | On/Under Budget | 1480987.3 | 44 | 0 | 44 | 0 | 0 | 71964.6 | 2550.6 | Project is not in the WP or in 2020 WP | 0 | 2594.6 | -2594.6 | 2594.6 | -2594.6 | 1093.8 | 1072.4 | 384.4 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5741.7 | 5741.7 | 28510.3 | 398599.9 | 508913.7 | 499029.5 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 1480987 | 2021-04-02 | 154946 | BL-B | BL-B 35113997_CWSP-WEST POINT 1101-OCB&LR12256-PH 1.6_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-09-15 | Completed | 2021-11-23 | 2021-12-20 | Not Started | 2022-01-10 | Not Started | 2022-01-11 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-18 | Not Started | 2022-01-11 | 2022-01-24 | Not Started | 2022-03-31 | Not Started |  |  |  |  | 2022-03-31 | Not Started | 2022-05-25 | Not Started | 2022-05-25 | Not Started | 2022-06-24 | 2022-06-24 | 0 | On/ Ahead Schedule | Not Started | 2022-06-02 | 2022-06-15 | Not Started | 2022-08-16 | Not Started
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | E.5014728.07 | 5786017 | PEND | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  |  | JACKSON | Stockton Assets | 120 | 5787 | 5907 | 1.1187 | 0 | 1.1187 | [5 empty] | 1129039.96 | 879039.96 | 250000 | 124894.7 | 0 | 125105.3 | On/Under Budget | 1528581.1 | 38.2 | 0 | 38.2 | 0 | 0 | 121571.7 | 3323 | Project is not in the WP or in 2020 WP | 0 | 3361.2 | -3361.2 | 3361.2 | -3361.2 | -2993.1 | 5668.3 | 647.8 | 38.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5741.7 | 5741.7 | 28510.3 | 398599.9 | 532710.7 | 522826.4 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 1528580.9 | 2021-04-02 | 154947 | BL-B | BL-B 35113998_CWSP-WEST POINT 1101-OCB&LR12256-PH 1.7_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-09-29 | Completed | 2021-11-08 | 2021-12-03 | Not Started | 2022-01-07 | Not Started | 2022-01-10 | Not Started | 2021-12-06 | 2021-12-06 | Not Started | 2021-12-07 | 2022-01-03 | Not Started | 2022-01-10 | 2022-01-21 | Not Started | 2022-02-16 | Not Started |  |  |  |  | 2022-02-16 | Not Started | 2022-04-08 | Not Started | 2022-04-08 | Not Started | 2022-05-10 | 2022-05-10 | 0 | On/ Ahead Schedule | Not Started | 2022-04-18 | 2022-04-29 | Not Started | 2022-06-30 | Not Started
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | E.5014727.03 | 5786002 | PEND | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 4248 | 4248 | 0.80455 | 0 | 0.80455 | [5 empty] | 434937.21 | 89937.21 | 345000 | 93333.6 | 0 | 251666.4 | On/Under Budget | 1461584.3 | 67 | 0 | 67 | 0 | 562.7 | 88168.5 | 4602.4 | Project is not in the WP or in 2020 WP | 0 | 4669.4 | -4669.4 | 4669.4 | -4669.4 | 1350.9 | 2770.7 | 480.8 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5741.7 | 5741.7 | 10256.8 | 107103 | 439013.7 | 387767.2 | 387767.2 | 100967.6 | 5741.7 | 5741.7 | 5741.7 | 0 | 1461584 | 2021-04-02 | 154936 | BL-B | BL-B 35112973_CWSP - WEST POINT 1101 -LR 13444- PH 1.3_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-09-15 | Completed | 2021-12-09 | 2022-01-19 | Not Started | 2021-11-23 | Not Started | 2022-01-19 | Not Started | 2022-01-20 | 2022-01-20 | Not Started | 2022-01-21 | 2022-02-17 | Not Started | 2021-12-15 | 2021-12-15 | Not Started | 2022-02-25 | Not Started |  |  |  |  | 2022-02-25 | Not Started | 2022-04-15 | Not Started | 2022-04-15 | Not Started | 2022-05-17 | 2022-05-17 | 0 | On/ Ahead Schedule | Not Started | 2022-04-25 | 2022-05-06 | Not Started | 2022-07-07 | Not Started
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | E.5014727.07 | 5786006 | PEND | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  |  | JACKSON | Stockton Assets | 0 | 6072 | 6072 | 1.15 | 0 | 1.15 | [5 empty] | 592701.09 | 247701.09 | 345000 | 75411.1 | 0 | 269588.9 | On/Under Budget | 1374530.5 | 103 | 0 | 103 | 0 | 0 | 14149.5 | 61261.6 | Project is not in the WP or in 2020 WP | 0 | 61519.1 | -61519.1 | 61519.1 | -61519.1 | 42.5 | 1414.5 | 59804.6 | 103 | 103 | 51.5 | 0 | 0 | 0 | 0 | 0 | 0 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 28510.3 | 334770.9 | 492569.9 | 472591.1 | 5741.7 | 5741.7 | 5741.7 | 5741.7 | 1374375.8 | 2021-04-02 | 154940 | BL-B | BL-B 35112977_CWSP - WEST POINT 1101 -LR 13444- PH 1.7_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-10-29 | Completed | 2021-12-07 | 2022-01-17 | Not Started | 2022-01-10 | Not Started | 2022-01-17 | Not Started | 2022-01-18 | 2022-01-18 | Not Started | 2022-01-19 | 2022-02-15 | Not Started | 2022-01-11 | 2022-01-24 | Not Started | 2022-02-23 | Not Started |  |  |  |  | 2022-02-23 | Not Started | 2022-04-19 | Not Started | 2022-04-19 | Not Started | 2022-05-19 | 2022-05-19 | 0 | On/ Ahead Schedule | Not Started | 2022-04-27 | 2022-05-10 | Not Started | 2022-07-11 | Not Started
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | E.5014726.02 | 5786007 | PEND | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 8477 | 8477 | 1.6055 | 0 | 1.6055 | [5 empty] | 1609077.23 | 1239567.23 | 369510 | 76388 | 0 | 293122 | On/Under Budget | 1868990.6 | 0 | 0 | 0 | 0 | 427.4 | 85295.7 | -9335.1 | Project is not in the WP or in 2020 WP | 0 | -9335.1 | 9335.1 | -9335.1 | 9335.1 | -10209.1 | 437 | 437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 596684 | 451415.2 | 471196.1 | 332948.5 | 4784.8 | 4784.8 | 3588.6 | 3588.6 | 0 | 0 | 0 | 0 | 1868990.6 | 2021-04-02 | 154929 | BL-B | BL-B 35112978_CWSP - WEST POINT 1101 -LR 13444- PH 2.2_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-07-27 | Completed | 2021-11-01 | 2021-11-26 | Not Started | 2021-10-14 | Not Started | 2021-11-26 | Not Started | 2021-11-29 | 2021-11-29 | Not Started | 2021-11-30 | 2021-12-13 | Not Started | 2021-11-05 | 2021-11-05 | Not Started | 2022-01-03 | Not Started |  |  |  |  | 2022-01-03 | Not Started | 2022-02-21 | Not Started | 2022-02-21 | Not Started | 2022-03-23 | 2022-03-23 | 0 | On/ Ahead Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-05-13 | Not Started
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | E.5014726.03 | 5786008 | PEND | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 5331 | 5331 | 1.0097 | 0 | 1.0097 | [5 empty] | 634232.73 | 264722.73 | 369510 | 105321.3 | 0 | 264188.7 | On/Under Budget | 1303969.6 | 0 | 0 | 0 | 0 | 213.7 | 105919.4 | -811.9 | Project is not in the WP or in 2020 WP | 0 | -811.9 | 811.9 | -811.9 | 811.9 | -1873.1 | 530.6 | 530.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 735042 | 120969 | 390492.4 | 29156.2 | 5342.9 | 3827.8 | 3827.8 | 3827.8 | 3827.8 | 3827.8 | 3827.8 | 0 | 1303969.3 | 2021-04-02 | 154930 | BL-B | BL-B 35112979_CWSP - WEST POINT 1101 -LR 13444- PH 2.3_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-08-20 | Completed | 2021-08-26 | 2021-10-06 | Not Started | 2021-08-10 | Not Started | 2021-10-06 | Not Started | 2021-10-07 | 2021-10-07 | Not Started | 2021-10-08 | 2021-11-04 | Not Started | 2021-09-01 | 2021-09-14 | Not Started | 2022-01-06 | Not Started |  |  |  |  | 2022-01-06 | Not Started | 2022-02-28 | Not Started | 2022-02-28 | Not Started | 2022-03-30 | 2022-03-30 | 0 | On/ Ahead Schedule | Not Started | 2022-03-08 | 2022-03-21 | Not Started | 2022-05-20 | Not Started
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | E.5014726.04 | 5786009 | PEND | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 10233 | 10233 | 1.9381 | 0 | 1.9381 | [5 empty] | 2254170.42 | 1884660.42 | 369510 | 122750.5 | 0 | 246759.5 | On/Under Budget | 2249604.2 | 0 | 0 | 0 | 0 | 0 | 130233.6 | -7483.1 | Project is not in the WP or in 2020 WP | 0 | -7483.1 | 7483.1 | -7483.1 | 7483.1 | 39378 | 982.8 | -47843.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 738302.5 | 500470.1 | 534791.5 | 453073.2 | 4784.8 | 4784.8 | 4784.8 | 2153.1 | 2153.1 | 2153.1 | 2153.1 | 0 | 2249604.1 | 2021-04-02 | 154931 | BL-B | BL-B 35113100_CWSP - WEST POINT 1101 -LR 13444- PH 2.4_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-10-08 | Completed | 2021-10-15 | 2021-11-25 | Not Started | 2021-09-30 | Not Started | 2021-11-25 | Not Started | 2021-11-26 | 2021-11-26 | Not Started | 2021-11-29 | 2021-12-24 | Not Started | 2021-10-22 | 2021-10-22 | Not Started | 2022-01-03 | Not Started |  |  |  |  | 2022-01-03 | Not Started | 2022-02-23 | Not Started | 2022-02-23 | Not Started | 2022-03-25 | 2022-03-25 | 0 | On/ Ahead Schedule | Not Started | 2022-03-03 | 2022-03-16 | Not Started | 2022-05-17 | Not Started
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | E.5015236.04 | 5786020 | PEND | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 9186 | 9186 | 1.7398 | 0 | 1.7398 | [5 empty] | 3838828 | 916420.8 | 2922407.2 | 810133.1 | 0 | 2112274.1 | On/Under Budget | 779598.7 | 782.7 | -250 | 1032.7 | 0 | 0 | 790085.1 | 19798 | Project is not in the WP or in 2020 WP | 0 | 22801.8 | -22801.8 | 22801.8 | -22801.8 | 10274.2 | 4633.9 | 5139.9 | 782.7 | 782.7 | 782.7 | 405.7 | 0 | 0 | 0 | 0 | 0 | 0 | 9444 | 463878.1 | 585273.3 | 28107.2 | 0 | 0 | 0 | -309075 | 0 | 0 | 0 | 777627.6 | 2021-04-02 | 154968 | BL-0 | BL-0 35115849_CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2.4_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-04-24 | Completed | 2020-06-23 | 2020-07-16 | Completed | 2020-06-12 | Completed | 2020-07-16 | Completed | 2020-08-26 | 2022-01-14 | In Progress | 2020-09-11 | 2020-10-02 | Completed | 2020-07-22 | 2020-09-04 | Completed | 2022-01-17 | Not Started |  |  |  |  | 2022-01-17 | Not Started | 2022-03-22 | Not Started | 2022-03-22 | Not Started | 2022-04-21 | 2022-04-21 | 0 | On/ Ahead Schedule | Not Started | 2022-04-22 | 2022-05-05 | Not Started | 2022-06-13 | Not Started
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | E.5015236.06 | 5786028 | PEND | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 6354 | 6354 | 1.2034 | 0 | 1.2034 | [5 empty] | 1197165.97 | 947165.97 | 250000 | 103281.1 | 0 | 146718.9 | On/Under Budget | 2489570 | 135.8 | 0 | 135.8 | 0 | 398.5 | 82715.3 | 20167.3 | Project is not in the WP or in 2020 WP | 0 | 20785.9 | -20785.9 | 20785.9 | -20785.9 | 13892.7 | 5188.8 | 1085.8 | 135.8 | 135.8 | 135.8 | 140.8 | 70.4 | 0 | 0 | 0 | 0 | 812207.3 | 815161.6 | 649069.1 | 162196 | 2870.9 | 2870.9 | 8054.9 | 11799.1 | 9743.9 | 7037.8 | 4037.8 | 4037.8 | 2489087.1 | 2021-04-02 | 154970 | BL-B | BL-B 35115851_CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.6_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-10-09 | Completed | 2022-01-10 | 2022-02-04 | Not Started | 2022-02-23 | Not Started | 2022-02-24 | Not Started | 2022-02-07 | 2022-02-07 | Not Started | 2022-02-08 | 2022-03-07 | Not Started | 2022-03-07 | 2022-03-18 | Not Started | 2022-05-24 | Not Started |  |  |  |  | 2022-05-24 | Not Started | 2022-07-20 | Not Started | 2022-08-03 | Not Started | 2022-09-02 | 2022-09-02 | 0 | On/ Ahead Schedule | Not Started | 2022-09-05 | 2022-09-16 | Not Started | 2022-10-25 | Not Started
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | E.5014742.02 | 5785996 | PEND | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 235 | 6519 | 6754 | 1.2792 | 0 | 1.2792 | [5 empty] | 1161832.82 | 536832.82 | 625000 | 311354 | 218755.7 | 532401.7 | On/Under Budget | 1729384 | 766.2 | -50000 | 50766.2 | 0 | 235.3 | 236982.3 | 24136.5 | Project is not in the WP or in 2020 WP | 0 | 75285.8 | -75285.8 | 75285.8 | -75285.8 | 1295.4 | -22134.2 | 94975.3 | 766.2 | 383.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92315.7 | 20975.6 | 20975.6 | 7256.8 | 430608.7 | 321096.4 | 563133.6 | 249293.9 | 17602.8 | 5741.7 | 0 | 0 | 1729000.8 | 2021-04-02 | 154952 | BL-B | BL-B 35114046_CWSP - PINE GROVE 1102 - LR1222 - PH 2.2_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-11-17 | Completed | 2021-09-28 | 2021-10-25 | Not Started | 2022-01-31 | Not Started | 2022-02-01 | Not Started | 2021-10-26 | 2021-10-26 | Not Started | 2021-10-27 | 2021-11-23 | Not Started | 2021-10-19 | 2021-10-19 | Not Started | 2022-03-10 | Not Started |  |  |  |  | 2022-03-10 | Not Started | 2022-04-29 | Not Started | 2022-04-29 | Not Started | 2022-05-31 | 2022-05-31 | 0 | On/ Ahead Schedule | Not Started | 2022-05-09 | 2022-05-20 | Not Started | 2022-07-21 | Not Started
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | E.5014723.03 | 5785936 | PEND | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 11880 | 11880 | 2.25 | 0 | 2.25 | [5 empty] | 250000 | 0 | 250000 | 185020 | 0 | 64980 | On/Under Budget | 3536610.3 | 197 | 0 | 197 | 0 | 761.1 | 180743.5 | 3515.3 | Project is not in the WP or in 2020 WP | 0 | 5310.8 | -5310.8 | 5310.8 | -5310.8 | 1168.2 | 1288.2 | 1058.9 | 197 | 98.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 998739 | 1145727 | 479169.4 | 884207.3 | 7943.5 | 4409.7 | 2870.9 | 2870.9 | 3332.5 | 2870.9 | 2870.9 | 3535012 | 2021-04-02 | 145853 | BL-A: | BL-A: 35115047_CWSP - MIWUK 1701 - LR 10600 PH 1.3_08W - June 2021 | 2020-07-24 | 2020-08-05 | Completed | 2020-11-20 | 2020-12-03 | Not Started | 2020-10-07 | Completed | 2021-12-22 | Not Started | 2021-12-23 | 2021-12-23 | Not Started | 2021-12-24 | 2022-01-20 | Not Started | 2021-12-23 | 2022-01-05 | Not Started | 2022-03-03 | Not Started |  |  |  |  | 2022-03-03 | Not Started | 2022-05-06 | Not Started | 2022-05-27 | Not Started | 2021-06-11 | 2022-06-28 | -382 | Behind Schedule | Not Started | 2022-06-29 | 2022-07-12 | Not Started | 2022-09-01 | Not Started
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | E.5015394.03 | 5786042 | PEND | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 2381 | 6855 | 9236 | 1.7492 | 0 | 1.7492 | [5 empty] | 1578304.87 | 1453304.87 | 125000 | 105763 | 0 | 19237 | On/Under Budget | 2930519.5 | 159.6 | -20 | 179.6 | 0 | 743.1 | 98869.6 | 6130.3 | Project is not in the WP or in 2020 WP | 0 | 6711.9 | -6711.9 | 6711.9 | -6711.9 | 1073 | 3871.8 | 1205.5 | 159.6 | 159.6 | 159.6 | 82.8 | 0 | 0 | 0 | 0 | 0 | 1296393.8 | 1622957.9 | 10765.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2930117.4 | 2021-04-02 | 154919 | BL-B | BL-B 35116512_CWSP - STANISLAUS 1702 - LR1888 - PH 2.3_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-07-23 | Completed | 2022-02-02 | 2022-03-15 | Not Started | 2022-02-07 | Not Started | 2022-03-15 | Not Started | 2022-05-31 | 2022-05-31 | Not Started | 2022-06-01 | 2022-06-28 | Not Started | 2022-02-23 | 2022-03-22 | Not Started | 2022-07-06 | Not Started |  |  |  |  | 2022-07-06 | Not Started | 2022-09-08 | Not Started | 2022-09-22 | Not Started | 2022-11-23 | 2022-11-23 | 0 | On/ Ahead Schedule | Not Started | 2022-11-24 | 2022-12-07 | Not Started | 2023-01-13 | Not Started
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 | E.5015394.04 | 5786043 | PEND | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 11249 | 11249 | 2.1305 | 0 | 2.1305 | [5 empty] | 908863.93 | 783863.93 | 125000 | 89769.6 | 0 | 35230.4 | On/Under Budget | 2803941.2 | 48.7 | 0 | 48.7 | 0 | 0 | 85630.4 | 4139.2 | Project is not in the WP or in 2020 WP | 0 | 4361 | -4361 | 4361 | -4361 | 1688.8 | 1973.2 | 477.2 | 48.7 | 48.7 | 48.7 | 50.5 | 25.2 | 0 | 0 | 0 | 0 | 1240064.5 | 1563703.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2803768.1 | 2021-04-02 | 154920 | BL-B | BL-B 35116513_CWSP - STANISLAUS 1702 - LR1888 - PH 2.4_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-10-01 | Completed | 2022-02-02 | 2022-03-15 | Not Started | 2022-02-02 | Not Started | 2020-10-12 | Completed | 2022-05-04 | 2022-05-04 | Not Started | 2022-05-05 | 2022-06-15 | Not Started | 2022-02-23 | 2022-03-29 | Not Started | 2022-08-10 | Not Started |  |  |  |  | 2022-08-10 | Not Started | 2022-10-06 | Not Started | 2022-10-20 | Not Started | 2022-12-21 | 2022-12-21 | 0 | On/ Ahead Schedule | Not Started | 2022-12-22 | 2023-01-04 | Not Started | 2023-02-10 | Not Started
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | E.5015394.05 | 5786044 | PEND | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 10852 | 10852 | 2.0553 | 0 | 2.0553 | [5 empty] | 964490.61 | 839490.61 | 125000 | 108027.5 | 0 | 16972.5 | On/Under Budget | 2810814 | 67.3 | 0 | 67.3 | 0 | 0 | 101034.8 | 6992.6 | Project is not in the WP or in 2020 WP | 0 | 7369 | -7369 | 7369 | -7369 | 3911.6 | 2075.8 | 1005.2 | 67.3 | 67.3 | 67.3 | 69.8 | 69.8 | 34.9 | 0 | 0 | 0 | 1255730 | 1029860.3 | 524914.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2810504.9 | 2021-04-02 | 154921 | BL-B | BL-B 35116514_CWSP - STANISLAUS 1702 - LR1888 - PH 2.5_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-09-22 | Completed | 2022-02-02 | 2022-03-15 | Not Started | 2022-03-22 | Not Started | 2022-03-23 | Not Started | 2022-04-13 | 2022-04-13 | Not Started | 2022-04-14 | 2022-05-11 | Not Started | 2022-02-23 | 2022-03-22 | Not Started | 2022-08-05 | Not Started |  |  |  |  | 2022-08-05 | Not Started | 2022-10-10 | Not Started | 2022-10-24 | Not Started | 2022-12-23 | 2022-12-23 | 0 | On/ Ahead Schedule | Not Started | 2022-12-26 | 2023-01-06 | Not Started | 2023-02-14 | Not Started
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | E.5014730.05 | 5785964 | PEND | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 12083 | 12083 | 2.2884 | 0 | 2.2884 | [5 empty] | 200000 | 0 | 200000 | 168751.8 | 0 | 31248.2 | On/Under Budget | 2871609.7 | 179.5 | 0 | 179.5 | 0 | 0 | 161356.2 | 7395.6 | Project is not in the WP or in 2020 WP | 0 | 9050.7 | -9050.7 | 9050.7 | -9050.7 | 955.4 | 5513 | 927.2 | 179.5 | 179.5 | 179.5 | 186.1 | 186.1 | 186.1 | 186.1 | 186.1 | 186.1 | 6671.9 | 6710.9 | 580012.6 | 1184498.3 | 971883.3 | 71002.9 | 39784.8 | 4784.8 | 4784.8 | 0 | 0 | 0 | 2870134.3 | 2021-04-02 | 145960 | BL-A | BL-A 35116803_CWSP - MIWUK 1702 - LR 6018 - PH 1.5_08W_ 2020 RESERVE - DEC 2021 | 2020-07-26 | 2020-08-24 | Completed | 2022-01-24 | 2022-01-24 | Not Started | 2020-10-23 | Completed | 2022-01-24 | Not Started | 2022-01-24 | 2022-01-24 | Not Started | 2022-01-24 | 2022-01-24 | Not Started | 2022-01-31 | 2022-03-04 | Not Started | 2022-03-07 | Not Started |  |  |  |  | 2022-03-07 | Not Started | 2022-05-16 | Not Started | 2022-06-14 | Not Started | 2021-12-16 | 2022-07-26 | -222 | Behind Schedule | Not Started | 2022-06-29 | 2022-07-12 | Not Started | 2022-12-20 | Not Started
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | E.5015701.03 | 5786037 | PEND | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 4825 | 4825 | 0.91383 | 0 | 0.91383 | [5 empty] | 1532501.31 | -706521.99 | 2239023.3 | 160597.6 | 0 | 2078425.7 | On/Under Budget | 1376188.9 | 0 | 0 | 0 | 0 | 0 | 157671.6 | 2926 | Project is not in the WP or in 2020 WP | 0 | 2926 | -2926 | 2926 | -2926 | 929.1 | 892.1 | 1104.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322521.1 | 618547.7 | 571036.4 | 7894.8 | 7894.8 | -151706 | 0 | 0 | 0 | 0 | 0 | 0 | 1376188.8 | 2021-04-02 | 154924 | BL-0 | BL-0 35116516_CWSP - STANISLAUS 1702 - LR1888 - PH 1.3_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-06-09 | Completed | 2020-07-23 | 2020-08-06 | Completed | 2020-06-16 | Completed | 2022-02-07 | Not Started | 2022-02-02 | 2022-02-02 | Not Started | 2022-02-03 | 2022-02-04 | Not Started | 2020-08-17 | 2022-02-07 | In Progress | 2022-02-22 | Not Started |  |  |  |  | 2022-02-22 | Not Started | 2022-04-04 | Not Started | 2022-04-18 | Not Started | 2022-08-12 | 2022-08-12 | 0 | On/ Ahead Schedule | Not Started | 2022-08-15 | 2022-08-26 | Not Started | 2022-10-04 | Not Started
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | E.5015701.05 | 5786039 | PEND | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 12677 | 12677 | 2.4009 | 0 | 2.4009 | [5 empty] | 2688006.56 | 2438006.56 | 250000 | 117940.9 | 0 | 132059.1 | On/Under Budget | 3000107.7 | 47.8 | 0 | 47.8 | 0 | 0 | 104294 | 13646.9 | Project is not in the WP or in 2020 WP | 0 | 13718.6 | -13718.6 | 13718.6 | -13718.6 | 1708.4 | 11094.4 | 844.1 | 47.8 | 23.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157159.4 | 719403.7 | 934420.3 | 600673.2 | 588427.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000083.7 | 2021-04-02 | 154926 | BL-B | BL-B 35116517_CWSP - STANISLAUS 1702 - LR1888 - PH 1.5_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-08-24 | Completed | 2022-02-02 | 2022-03-15 | Not Started | 2022-02-11 | Not Started | 2022-03-15 | Not Started | 2022-03-16 | 2022-03-16 | Not Started | 2022-03-17 | 2022-04-06 | Not Started | 2022-02-16 | 2022-03-30 | Not Started | 2022-04-14 | Not Started |  |  |  |  | 2022-04-14 | Not Started | 2022-06-17 | Not Started | 2022-07-01 | Not Started | 2022-10-21 | 2022-10-21 | 0 | On/ Ahead Schedule | Not Started | 2022-10-24 | 2022-11-04 | Not Started | 2022-12-13 | Not Started
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | E.5015701.06 | 5786040 | PEND | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 10922 | 10922 | 2.0686 | 0 | 2.0686 | [5 empty] | 1631980.57 | 1381980.57 | 250000 | 120671.4 | 0 | 129328.6 | On/Under Budget | 2656325.2 | 175 | 0 | 175 | 0 | 0 | 112335.5 | 8336 | Project is not in the WP or in 2020 WP | 0 | 8773.5 | -8773.5 | 8773.5 | -8773.5 | 1468.4 | 6228 | 639.6 | 175 | 175 | 87.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1001715.6 | 841878.5 | 797396.6 | 15072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2656062.7 | 2021-04-02 | 154927 | BL-B | BL-B 35116518_CWSP - STANISLAUS 1702 - LR1888 - PH 1.6_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-10-29 | Completed | 2022-02-02 | 2022-03-15 | Not Started | 2022-03-01 | Not Started | 2022-03-15 | Not Started | 2022-05-11 | 2022-05-11 | Not Started | 2022-05-12 | 2022-06-08 | Not Started | 2022-02-23 | 2022-03-22 | Not Started | 2022-06-22 | Not Started |  |  |  |  | 2022-06-22 | Not Started | 2022-08-18 | Not Started | 2022-09-01 | Not Started | 2022-11-02 | 2022-11-02 | 0 | On/ Ahead Schedule | Not Started | 2022-11-03 | 2022-11-16 | Not Started | 2022-12-23 | Not Started
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | E.5015701.04 | 5786038 | PEND | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 9268 | 9268 | 1.7553 | 0 | 1.7553 | [5 empty] | 2253896.9 | 2003896.9 | 250000 | 84405.8 | 0 | 165594.2 | On/Under Budget | 2147637.7 | 0 | 0 | 0 | 0 | 0 | 59012.9 | 25392.9 | Project is not in the WP or in 2020 WP | 0 | 25392.9 | -25392.9 | 25392.9 | -25392.9 | 22930.1 | 1979.2 | 483.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3588.6 | 247649.6 | 1454938.1 | 908878.4 | 0 | 0 | 0 | -467417 | 0 | 0 | 0 | 0 | 2147637.7 | 2021-04-02 | 154925 | BL-B | BL-B 35116519_CWSP - STANISLAUS 1702 - LR1888 - PH 1.4_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-08-27 | Completed | 2020-10-28 | 2022-02-25 | Not Started | 2022-02-01 | Not Started | 2022-02-25 | Not Started | 2022-02-28 | 2022-02-28 | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2020-10-23 | 2022-02-07 | In Progress | 2022-03-22 | Not Started |  |  |  |  | 2022-03-22 | Not Started | 2022-05-13 | Not Started | 2022-05-13 | Not Started | 2022-09-28 | 2022-09-28 | 0 | On/ Ahead Schedule | Not Started | 2022-09-29 | 2022-10-12 | Not Started | 2022-11-18 | Not Started
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | E.5014722.03 | 5785930 | PEND | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 10614 | 10614 | 2.0102 | 0 | 2.0102 | [5 empty] | 5174348 | 1534666.2 | 3639681.8 | 65180.5 | 0 | 3574501.3 | On/Under Budget | 2459730.8 | 79.3 | 0 | 79.3 | 0 | 206.2 | 57572.2 | 7402 | Project is not in the WP or in 2020 WP | 0 | 8133.1 | -8133.1 | 8133.1 | -8133.1 | 513.2 | 6540.1 | 348.7 | 79.3 | 79.3 | 79.3 | 82.2 | 82.2 | 82.2 | 82.2 | 82.2 | 82.2 | 605524.3 | 1205425.4 | 616292.9 | 24404.2 | 7431.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2459078.6 | 2021-04-02 | 145790 | BL-B: | BL-B: 35116397_CWSP - MIWUK 1702 - LR 8090 - PH 1.3_08W - Feb. 2021 | 2020-07-24 | 2020-06-15 | Completed | 2020-08-25 | 2020-09-21 | Completed | 2020-08-06 | Completed | 2022-02-02 | Not Started | 2022-02-02 | 2022-02-15 | Not Started | 2022-02-16 | 2022-02-28 | Not Started | 2020-10-12 | 2020-12-04 | Completed | 2022-03-08 | Not Started |  |  |  |  | 2022-03-08 | Not Started | 2022-05-23 | Not Started | 2022-05-31 | Not Started | 2021-02-15 | 2022-06-01 | -471 | Behind Schedule | Not Started | 2022-06-03 | 2022-06-03 | Not Started | 2022-07-04 | Not Started
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | E.5015235.06 | 5786026 | PEND | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 6445 | 6445 | 1.2206 | 0 | 1.2206 | [5 empty] | 1602218.96 | 1602218.96 | 0 | 63376.3 | 0 | -63376.3 | OverRun | 2596041.7 | 100 | 0 | 100 | 0 | 0 | 58726.8 | 4649.5 | Project is not in the WP or in 2020 WP | 0 | 5571.7 | -5571.7 | 5571.7 | -5571.7 | 3353.4 | 359.5 | 936.6 | 100 | 100 | 100 | 103.7 | 103.7 | 103.7 | 103.7 | 103.7 | 103.7 | 668648.3 | 160438.8 | 1065784.2 | 464243.5 | 466969.7 | -238795.4 | 7930.3 | 0 | 0 | 0 | 0 | 0 | 2595219.4 | 2021-04-02 | 154964 | BL-B | BL-B 35115857_CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1.6_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-07-15 | Completed | 2022-02-21 | 2022-03-18 | Not Started | 2022-04-01 | Not Started | 2022-04-04 | Not Started | 2022-03-21 | 2022-03-21 | Not Started | 2022-03-22 | 2022-04-18 | Not Started | 2022-04-18 | 2022-04-29 | Not Started | 2022-05-24 | Not Started |  |  |  |  | 2022-05-24 | Not Started | 2022-07-20 | Not Started | 2022-08-03 | Not Started | 2022-06-24 | 2022-09-02 | -70 | Behind Schedule | Not Started | 2022-09-05 | 2022-09-16 | Not Started | 2022-10-25 | Not Started
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | E.5014733.04 | 5785968 | PEND | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 8005 | 8005 | 1.5161 | 0 | 1.5161 | [5 empty] | 3489624 | 674982 | 2814642 | 79253.4 | 0 | 2735388.6 | On/Under Budget | 1530163.7 | 0 | 0 | 0 | 0 | 380.2 | 77402.9 | 1470.3 | Project is not in the WP or in 2020 WP | 0 | 1470.3 | -1470.3 | 1470.3 | -1470.3 | 1623.5 | -1094.7 | 941.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16072.2 | 8374.3 | 3110.1 | 3110.1 | 4492.4 | 3110.1 | 305945.4 | 247720.7 | 788333 | 149895.4 | 0 | 0 | 1530163.7 | 2021-04-02 | 145856 | BL-A: | BL-A: 35116385_CWSP - MIWUK 1701 - LR 8060 - PH 1.4_08W - Feb 2021 | 2020-07-24 | 2020-05-27 | Completed | 2022-03-08 | 2022-03-14 | Not Started | 2021-04-05 | Not Started | 2022-03-14 | Not Started | 2022-03-15 | 2022-03-15 | Not Started | 2022-03-16 | 2022-03-17 | Not Started | 2021-04-05 | 2021-07-16 | Not Started | 2022-07-08 | Not Started |  |  |  |  | 2022-07-08 | Not Started | 2022-08-23 | Not Started | 2022-09-20 | Not Started | 2021-02-05 | 2022-09-27 | -599 | Behind Schedule | Not Started | 2022-10-05 | 2022-10-18 | Not Started | 2022-10-18 | Not Started
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | E.5014733.05 | 5785969 | PEND | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 13109 | 13109 | 2.4828 | 0 | 2.4828 | [5 empty] | 1767022.83 | -2668338.97 | 4435361.8 | 450948 | 0 | 3984413.8 | On/Under Budget | 2197141 | 623.5 | 0 | 623.5 | 0 | 409.3 | 409455.9 | 41082.8 | Project is not in the WP or in 2020 WP | 0 | 46836.5 | -46836.5 | 46836.5 | -46836.5 | 2799.4 | 8596.8 | 29686.6 | 623.5 | 623.5 | 623.5 | 647.2 | 647.2 | 647.2 | 647.2 | 647.2 | 647.2 | 769826 | 1249859.7 | 596319.1 | 0 | 0 | 0 | -105998 | -211997 | -105999 | 0 | 0 | 0 | 2192010.8 | 2021-04-02 | 151454 | BL-0 | BL-0 35116388_CWSP - MIWUK 1701 - LR 8060 - PH 1.5_08W - Nov. 2020 | 2020-11-12 | 2020-05-06 | Completed | 2020-07-17 | 2020-07-17 | Completed | 2020-06-22 | Completed | 2020-08-04 | Completed | 2020-09-14 | 2020-09-14 | Completed | 2020-09-29 | 2020-09-29 | Completed | 2020-08-10 | 2020-11-02 | Completed | 2022-01-04 | Not Started |  |  |  |  | 2022-01-04 | Not Started | 2022-02-16 | Not Started | 2022-03-09 | Not Started | 2021-04-06 | 2022-03-23 | -351 | Behind Schedule | Not Started | 2022-03-24 | 2022-04-06 | Not Started | 2022-05-13 | Not Started
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | E.5014540.02 | 5786030 | PEND | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | STOCKTON | Stockton Assets | 0 | 8059 | 8059 | 1.5263 | 0 | 1.5263 | [5 empty] | 1152639.46 | 902639.46 | 250000 | 109114.7 | 0 | 140885.3 | On/Under Budget | 2068650 | 153.1 | 0 | 153.1 | 0 | 0 | 101809.6 | 7305.1 | Project is not in the WP or in 2020 WP | 0 | 7843.8 | -7843.8 | 7843.8 | -7843.8 | 2539.5 | 3879.3 | 886.3 | 153.1 | 153.1 | 153.1 | 79.4 | 0 | 0 | 0 | 0 | 0 | 1051517.7 | 995215.1 | 21531.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2068264.3 | 2021-04-02 | 154907 | BL-B | BL-B 35116921_CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-08-27 | Completed | 2022-02-02 | 2022-03-15 | Not Started | 2022-02-23 | Not Started | 2022-03-15 | Not Started | 2022-06-02 | 2022-06-02 | Not Started | 2022-06-03 | 2022-06-30 | Not Started | 2022-02-23 | 2022-04-05 | Not Started | 2022-07-08 | Not Started |  |  |  |  | 2022-07-08 | Not Started | 2022-09-05 | Not Started | 2022-09-19 | Not Started | 2022-11-18 | 2022-11-18 | 0 | On/ Ahead Schedule | Not Started | 2022-11-21 | 2022-12-02 | Not Started | 2023-01-10 | Not Started
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | E.5014540.03 | 5786031 | PEND | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | STOCKTON | Stockton Assets | 0 | 6121 | 6121 | 1.1593 | 0 | 1.1593 | [5 empty] | 966585.11 | 841585.11 | 125000 | 70667.8 | 0 | 54332.2 | On/Under Budget | 1502360.6 | 0 | 0 | 0 | 0 | 0 | 65744.7 | 4923.1 | Project is not in the WP or in 2020 WP | 0 | 4923.1 | -4923.1 | 4923.1 | -4923.1 | 367.1 | 4183.9 | 372.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 832851.5 | 970840.1 | 0 | 0 | 0 | -301331 | 0 | 0 | 0 | 0 | 0 | 1502360.6 | 2021-04-02 | 154908 | BL-B | BL-B 35116922_CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-06-18 | Completed | 2020-10-30 | 2022-02-08 | Not Started | 2022-02-07 | Not Started | 2022-02-08 | Not Started | 2022-02-09 | 2022-02-09 | Not Started | 2022-02-10 | 2022-02-23 | Not Started | 2022-02-08 | 2022-03-07 | Not Started | 2022-04-08 | Not Started |  |  |  |  | 2022-04-08 | Not Started | 2022-05-30 | Not Started | 2022-05-30 | Not Started | 2022-09-28 | 2022-09-28 | 0 | On/ Ahead Schedule | Not Started | 2022-09-29 | 2022-10-12 | Not Started | 2022-11-18 | Not Started
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | E.5014540.05 | 5786033 | PEND | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | STOCKTON | Stockton Assets | 0 | 9910 | 9910 | 1.8769 | 0 | 1.8769 | [5 empty] | 1835218.36 | 1585218.36 | 250000 | 94316.9 | 0 | 155683.1 | On/Under Budget | 2641317.4 | 220.4 | 0 | 220.4 | 0 | 605.7 | 92209.4 | 1501.8 | Project is not in the WP or in 2020 WP | 0 | 1832.4 | -1832.4 | 1832.4 | -1832.4 | 523.8 | 489 | 489 | 220.4 | 110.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1595919.3 | 980362.4 | 57480 | 7445.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2641207.3 | 2021-04-02 | 154910 | BL-B | BL-B 35116924_CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-12-08 | Completed | 2022-02-02 | 2022-03-15 | Not Started | 2022-02-01 | Not Started | 2022-03-15 | Not Started | 2022-03-16 | 2022-03-16 | Not Started | 2022-03-17 | 2022-03-30 | Not Started | 2022-02-23 | 2022-03-22 | Not Started | 2022-04-07 | Not Started |  |  |  |  | 2022-04-07 | Not Started | 2022-06-03 | Not Started | 2022-06-17 | Not Started | 2022-08-18 | 2022-08-18 | 0 | On/ Ahead Schedule | Not Started | 2022-08-19 | 2022-09-01 | Not Started | 2022-10-10 | Not Started
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 | E.5014540.07 | 5786035 | PEND | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | STOCKTON | Stockton Assets | 0 | 7711 | 7711 | 1.4604 | 0 | 1.4604 | [5 empty] | 1575778.82 | 1450778.82 | 125000 | 73372.8 | 0 | 51627.2 | On/Under Budget | 2086990.4 | 108.5 | 0 | 108.5 | 0 | 0 | 68584.3 | 4788.6 | Project is not in the WP or in 2020 WP | 0 | 4951.3 | -4951.3 | 4951.3 | -4951.3 | 389.6 | 4007.6 | 391.4 | 108.5 | 54.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252425.3 | 760962.2 | 651496.1 | 814360.6 | 10048 | 0 | 0 | -402356 | 0 | 0 | 0 | 0 | 2086936.2 | 2021-04-02 | 154912 | BL-B | BL-B 35116926_CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-07-16 | Completed | 2022-02-02 | 2022-03-15 | Not Started | 2022-02-08 | Not Started | 2022-03-15 | Not Started | 2022-03-23 | 2022-03-23 | Not Started | 2022-03-24 | 2022-04-06 | Not Started | 2022-03-30 | 2022-04-26 | Not Started | 2022-04-11 | Not Started |  |  |  |  | 2022-04-11 | Not Started | 2022-06-07 | Not Started | 2022-06-21 | Not Started | 2022-08-22 | 2022-08-22 | 0 | On/ Ahead Schedule | Not Started | 2022-08-23 | 2022-09-05 | Not Started | 2022-10-12 | Not Started
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | E.5014534.05 | 5786602 | PEND | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 | 2020 | SH | CUPRTINO | De Anza Assets | 0 | 4483 | 4483 | 0.84905 | 0 | 0.84905 | 4483 | 0 | 0.84905 | 0 | GC | 1924210 | 488785 | 1435425 | 792390.3 | 212251.1 | 855285.8 | On/Under Budget | 481954.8 | 5293.1 | 0 | 5293.1 | 0 | 454.5 | 745693.8 | 46242 | Request 2021 Budget | 0 | 533490 | -533490 | 533490 | -533490 | 36194.8 | 18565.8 | -8518.6 | 5293.1 | 425663.5 | 7701.1 | 29556.8 | 7943.5 | 4436 | 4436 | 2218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156105 | BL-A | BL-A 35119965_CWSP Los Gatos 1106-LB44 Ph 2.5E_08W - Feb. 2021 | 2021-02-20 | 2019-12-13 | Completed | 2020-04-13 | 2020-04-23 | Completed | 2021-05-31 | Not Started | 2021-06-01 | Not Started | 2020-03-12 | 2020-04-08 | Completed | 2020-04-08 | 2020-04-10 | Completed | 2020-06-03 | 2021-07-26 | In Progress | 2020-07-13 | Completed |  |  |  |  | 2020-06-29 | Completed | 2021-09-01 | Not Started | 2021-10-29 | Not Started | 2021-11-05 | 2021-10-29 | 7 | On/ Ahead Schedule | Not Started | 2021-11-15 | 2021-11-26 | Not Started | 2022-02-18 | Not Started
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | E.5014720.03 | 5786764 | PEND | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 8902 | 8902 | 1.686 | 0 | 1.686 | [5 empty] | 100000 | 0 | 100000 | 37855.6 | 0 | 62144.4 | On/Under Budget | 85.4 | 18.6 | 0 | 18.6 | 0 | 235.3 | 35135.9 | 2484.4 | Project is not in the WP or in 2020 WP | 0 | 2588.4 | -2588.4 | 2588.4 | -2588.4 | 2051 | 216.7 | 216.7 | 18.6 | 18.6 | 18.6 | 19.3 | 19.3 | 9.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2020-07-30 | Completed | 2022-04-08 | 2022-04-14 | Not Started | 2022-04-07 | Not Started | 2022-04-21 | Not Started | 2022-04-08 | 2022-04-08 | Not Started | 2022-04-11 | 2022-07-01 | Not Started | 2022-04-08 | 2022-04-14 | Not Started | 2022-08-01 | Not Started |  |  |  |  | 2022-08-01 | Not Started | 2022-08-26 | Not Started | 2022-10-07 | Not Started | 2022-11-08 | 2022-11-08 | 0 | On/ Ahead Schedule | Not Started | 2022-11-09 | 2022-11-22 | Not Started | 2022-12-29 | Not Started
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | E.5014720.04 | 5786765 | PEND | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 10110 | 10110 | 1.9148 | 0 | 1.9148 | [5 empty] | 100000 | 0 | 100000 | 44599.4 | 0 | 55400.6 | On/Under Budget | 95.2 | 37.8 | 0 | 37.8 | 0 | 235.3 | 43025.7 | 1338.4 | Project is not in the WP or in 2020 WP | 0 | 1471.4 | -1471.4 | 1471.4 | -1471.4 | 842.9 | 258.8 | 236.7 | 37.8 | 37.8 | 37.8 | 19.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2020-08-24 | Completed | 2022-04-08 | 2022-05-19 | Not Started | 2022-04-07 | Not Started | 2022-05-19 | Not Started | 2022-05-20 | 2022-05-20 | Not Started | 2022-05-23 | 2022-08-12 | Not Started | 2022-04-08 | 2022-04-21 | Not Started | 2022-08-15 | Not Started |  |  |  |  | 2022-08-15 | Not Started | 2022-11-18 | Not Started | 2023-01-06 | Not Started | 2023-02-03 | 2023-02-03 | 0 | On/ Ahead Schedule | Not Started | 2023-02-06 | 2023-02-17 | Not Started | 2023-03-28 | Not Started
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | E.5014720.05 | 5786766 | PEND | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 10500 | 10500 | 1.9886 | 0 | 1.9886 | [5 empty] | 1977294.19 | 1877294.19 | 100000 | 49355.8 | 0 | 50644.2 | On/Under Budget | 124.7 | 35.1 | 0 | 35.1 | 0 | 0 | 48549.8 | 805.9 | Project is not in the WP or in 2020 WP | 0 | 965.8 | -965.8 | 965.8 | -965.8 | 280.9 | 262.5 | 262.5 | 35.1 | 35.1 | 35.1 | 36.4 | 18.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2022-05-12 | Not Started | 2022-05-13 | 2022-05-19 | Not Started | 2022-04-14 | Not Started | 2022-05-26 | Not Started | 2022-05-13 | 2022-05-13 | Not Started | 2022-05-16 | 2022-06-03 | Not Started | 2022-05-06 | 2022-05-19 | Not Started | 2022-07-15 | Not Started |  |  |  |  | 2022-07-15 | Not Started | 2022-10-06 | Not Started | 2022-10-21 | Not Started | 2022-11-22 | 2022-11-22 | 0 | On/ Ahead Schedule | Not Started | 2022-11-23 | 2022-12-06 | Not Started | 2023-01-12 | Not Started
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | E.5014719.02 | 5786767 | PEND | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 10670 | 10670 | 2.0208 | 0 | 2.0208 | [5 empty] | 1281508.77 | 1031508.77 | 250000 | 197766.2 | 0 | 52233.8 | On/Under Budget | 707.2 | 198.9 | 0 | 198.9 | 0 | 235.3 | 193124.2 | 4406.7 | Project is not in the WP or in 2020 WP | 0 | 5312.7 | -5312.7 | 5312.7 | -5312.7 | 25885.8 | 1269.8 | -22748.9 | 198.9 | 198.9 | 198.9 | 206.2 | 103.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2020-11-09 | Completed | 2022-05-20 | 2022-05-26 | Not Started | 2022-05-19 | Not Started | 2022-06-16 | Not Started | 2022-04-08 | 2022-04-08 | Not Started | 2022-04-11 | 2022-04-15 | Not Started | 2022-05-20 | 2022-05-26 | Not Started | 2022-09-30 | Not Started |  |  |  |  | 2022-09-30 | Not Started | 2022-12-01 | Not Started | 2022-12-22 | Not Started | 2023-02-22 | 2023-02-22 | 0 | On/ Ahead Schedule | Not Started | 2023-02-23 | 2023-03-08 | Not Started | 2023-04-14 | Not Started
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | E.5014719.03 | 5786768 | PEND | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 10796 | 10796 | 2.0447 | 0 | 2.0447 | [5 empty] | 1701197.29 | 1451197.29 | 250000 | 140283.5 | 0 | 109716.5 | On/Under Budget | 162.8 | 108.6 | 0 | 108.6 | 0 | 235.3 | 133058 | 6990.2 | Project is not in the WP or in 2020 WP | 0 | 7261.7 | -7261.7 | 7261.7 | -7261.7 | 22113.7 | 1268.2 | -16391.7 | 108.6 | 108.6 | 54.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2020-10-08 | Completed | 2022-04-08 | 2022-04-14 | Not Started | 2022-04-07 | Not Started | 2022-06-02 | Not Started | 2022-04-08 | 2022-04-08 | Not Started | 2022-04-11 | 2022-07-01 | Not Started | 2022-04-08 | 2022-04-21 | Not Started | 2022-08-08 | Not Started |  |  |  |  | 2022-08-08 | Not Started | 2022-10-07 | Not Started | 2022-10-20 | Not Started | 2022-11-21 | 2022-11-21 | 0 | On/ Ahead Schedule | Not Started | 2022-11-22 | 2022-12-05 | Not Started | 2023-01-11 | Not Started
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | E.5014719.04 | 5786769 | PEND | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 10179 | 10179 | 1.9278 | 0 | 1.9278 | [5 empty] | 250000 | 0 | 250000 | 130347.2 | 0 | 119652.8 | On/Under Budget | 88.7 | 19.3 | 0 | 19.3 | 0 | 235.3 | 109438.9 | 20672.9 | Project is not in the WP or in 2020 WP | 0 | 20780.8 | -20780.8 | 20780.8 | -20780.8 | 18698.5 | 1251.1 | 723.3 | 19.3 | 19.3 | 19.3 | 20 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2020-09-04 | Completed | 2022-05-06 | 2022-05-12 | Not Started | 2022-05-05 | Not Started | 2022-05-19 | Not Started | 2022-04-08 | 2022-04-08 | Not Started | 2022-04-11 | 2022-07-01 | Not Started | 2022-04-08 | 2022-04-14 | Not Started | 2022-08-01 | Not Started |  |  |  |  | 2022-08-01 | Not Started | 2022-09-30 | Not Started | 2022-10-19 | Not Started | 2022-11-18 | 2022-11-18 | 0 | On/ Ahead Schedule | Not Started | 2022-11-21 | 2022-12-02 | Not Started | 2023-01-10 | Not Started
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | E.5014719.05 | 5786770 | PEND | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 10708 | 10708 | 2.028 | 0 | 2.028 | [5 empty] | 250000 | 0 | 250000 | 118857.7 | 0 | 131142.3 | On/Under Budget | 76.5 | 51 | 0 | 51 | 0 | 235.3 | 116483.8 | 2138.7 | Project is not in the WP or in 2020 WP | 0 | 2266.2 | -2266.2 | 2266.2 | -2266.2 | 778.1 | 680.3 | 680.3 | 51 | 51 | 25.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2020-08-13 | Completed | 2022-04-08 | 2022-04-14 | Not Started | 2022-04-07 | Not Started | 2022-04-21 | Not Started | 2022-04-08 | 2022-04-08 | Not Started | 2022-04-11 | 2022-07-01 | Not Started | 2022-04-08 | 2022-04-14 | Not Started | 2022-08-01 | Not Started |  |  |  |  | 2022-08-01 | Not Started | 2022-09-23 | Not Started | 2022-10-11 | Not Started | 2022-11-10 | 2022-11-10 | 0 | On/ Ahead Schedule | Not Started | 2022-11-11 | 2022-11-24 | Not Started | 2023-01-02 | Not Started
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | E.5014718.02 | 5786771 | PEND | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 9150 | 9150 | 1.733 | 0 | 1.733 | [5 empty] | 1182381.93 | 932381.93 | 250000 | 166083.9 | 0 | 83916.1 | On/Under Budget | 152.7 | 22.9 | 0 | 22.9 | 0 | 235.3 | 159248.7 | 6599.9 | Project is not in the WP or in 2020 WP | 0 | 6775.7 | -6775.7 | 6775.7 | -6775.7 | 24986.7 | 987.7 | -19374.5 | 22.9 | 22.9 | 22.9 | 23.8 | 23.8 | 23.8 | 23.8 | 11.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2022-04-21 | Not Started | 2022-04-22 | 2022-04-28 | Not Started | 2022-04-07 | Not Started | 2022-05-05 | Not Started | 2022-04-22 | 2022-04-22 | Not Started | 2022-04-25 | 2022-07-15 | Not Started | 2022-04-08 | 2022-04-21 | Not Started | 2022-08-15 | Not Started |  |  |  |  | 2022-08-15 | Not Started | 2022-10-14 | Not Started | 2022-11-07 | Not Started | 2022-12-07 | 2022-12-07 | 0 | On/ Ahead Schedule | Not Started | 2022-12-08 | 2022-12-21 | Not Started | 2023-01-27 | Not Started
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | E.5014718.03 | 5786772 | PEND | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 9792 | 9792 | 1.8545 | 0 | 1.8545 | [5 empty] | 250000 | 0 | 250000 | 148031.1 | 0 | 101968.9 | On/Under Budget | 49 | 13.2 | 0 | 13.2 | 0 | 235.3 | 126664.2 | 21131.7 | Project is not in the WP or in 2020 WP | 0 | 21193.9 | -21193.9 | 21193.9 | -21193.9 | 19436.5 | 847.6 | 847.6 | 13.2 | 14.2 | 14.2 | 13.7 | 6.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2020-09-11 | Completed | 2022-04-08 | 2022-04-14 | Not Started | 2022-04-07 | Not Started | 2022-04-21 | Not Started | 2022-04-08 | 2022-04-08 | Not Started | 2022-04-11 | 2022-07-01 | Not Started | 2022-04-08 | 2022-04-21 | Not Started | 2022-08-01 | Not Started |  |  |  |  | 2022-08-01 | Not Started | 2022-09-30 | Not Started | 2022-10-13 | Not Started | 2022-11-14 | 2022-11-14 | 0 | On/ Ahead Schedule | Not Started | 2022-11-15 | 2022-11-28 | Not Started | 2023-01-04 | Not Started
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | E.5014718.04 | 5786773 | PEND | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 6062 | 6062 | 1.1481 | 0 | 1.1481 | [5 empty] | 250000 | 0 | 250000 | 119895.2 | 0 | 130104.8 | On/Under Budget | 154.2 | 27.2 | 0 | 27.2 | 0 | 235.3 | 102239.7 | 17420.3 | Project is not in the WP or in 2020 WP | 0 | 17601.6 | -17601.6 | 17601.6 | -17601.6 | 16150.9 | 634.7 | 634.7 | 27.2 | 28.2 | 27.2 | 28.2 | 28.2 | 28.2 | 14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2020-09-11 | Completed | 2022-04-08 | 2022-04-14 | Not Started | 2022-04-07 | Not Started | 2022-04-21 | Not Started | 2022-04-08 | 2022-04-08 | Not Started | 2022-04-11 | 2022-07-01 | Not Started | 2022-04-08 | 2022-04-14 | Not Started | 2022-08-01 | Not Started |  |  |  |  | 2022-08-01 | Not Started | 2022-09-02 | Not Started | 2022-09-19 | Not Started | 2022-10-19 | 2022-10-19 | 0 | On/ Ahead Schedule | Not Started | 2022-10-20 | 2022-11-02 | Not Started | 2022-12-09 | Not Started
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | E.5014718.05 | 5786774 | PEND | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 7408 | 7408 | 1.403 | 0 | 1.403 | [5 empty] | 3374618 | 870869.7 | 2503748.3 | 184091.1 | 0 | 2319657.2 | On/Under Budget | 145.3 | 25.6 | 0 | 25.6 | 0 | 0 | 180084.2 | 4006.9 | Project is not in the WP or in 2020 WP | 0 | 4177.8 | -4177.8 | 4177.8 | -4177.8 | 1877.5 | 1075.8 | 1053.6 | 25.6 | 25.6 | 25.6 | 27.8 | 26.5 | 26.5 | 13.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2020-07-07 | Completed | 2020-09-04 | 2020-09-05 | Completed | 2022-04-07 | Not Started | 2022-04-14 | Not Started | 2022-04-08 | 2022-04-08 | Not Started | 2022-04-11 | 2022-07-01 | Not Started | 2020-11-13 | 2022-04-08 | In Progress | 2022-08-01 | Not Started |  |  |  |  | 2022-08-01 | Not Started | 2022-09-16 | Not Started | 2022-09-30 | Not Started | 2022-11-01 | 2022-11-01 | 0 | On/ Ahead Schedule | Not Started | 2022-11-02 | 2022-11-15 | Not Started | 2022-12-22 | Not Started
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | E.5014748.02 | 5786745 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 5722 | 5722 | 1.0837 | 0 | 1.0837 | [5 empty] | 4600257 | 0 | 4600257 | 24145.8 | 0 | 4576111.2 | On/Under Budget | 2116393.7 | 0 | 0 | 0 | 0 | 0 | 23526.5 | 619.3 | Project is not in the WP or in 2020 WP | 0 | 105098.8 | -105098.8 | 105098.8 | -105098.8 | 20624 | 255.6 | -20260.3 | 0 | 0 | 60286 | 19973.3 | 19647.8 | 4572.4 | 0 | 0 | 0 | 39.3 | 39.3 | 39.3 | 39.3 | 670605.3 | 670585.7 | 670566 | 0 | 0 | 0 | 0 | 0 | 2011914.2 | 2021-04-02 |  |  |  |  | 2020-07-06 | Completed | 2020-10-14 | 2020-10-14 | Completed | 2021-04-02 | Not Started | 2022-08-26 | Not Started | 2022-08-26 | 2022-08-26 | Not Started | 2022-08-29 | 2022-08-30 | Not Started | 2021-04-08 | 2021-04-08 | Not Started | 2022-09-07 | Not Started |  |  |  |  | 2022-09-07 | Not Started | 2022-09-28 | Not Started | 2022-10-11 | Not Started | 2023-01-03 | 2023-01-03 | 0 | On/ Ahead Schedule | Not Started | 2023-01-04 | 2023-01-17 | Not Started | 2023-02-23 | Not Started
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 | E.5014748.03 | 5786746 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 6970 | 6970 | 1.3201 | 0 | 1.3201 | [5 empty] | 250000 | 0 | 250000 | 33861.5 | 0 | 216138.5 | On/Under Budget | 2430468 | 33.3 | 0 | 33.3 | 0 | 0 | 32942.3 | 919.2 | Project is not in the WP or in 2020 WP | 0 | 1226.7 | -1226.7 | 1226.7 | -1226.7 | 35227.5 | 367 | -34675.3 | 33.3 | 33.3 | 33.3 | 34.6 | 34.6 | 34.6 | 34.6 | 34.6 | 34.6 | 148583.5 | 298038.4 | 2754.5 | 2754.5 | 2754.5 | 26716 | 474684.3 | 856893.1 | 470749.5 | 146265.4 | 0 | 0 | 2430193.7 | 2021-04-02 |  |  |  |  | 2020-05-06 | Completed | 2022-08-26 | 2022-08-26 | Not Started | 2021-04-02 | Not Started | 2022-08-26 | Not Started | 2022-08-26 | 2022-08-26 | Not Started | 2022-08-29 | 2022-08-30 | Not Started | 2021-04-06 | 2021-04-06 | Not Started | 2022-09-07 | Not Started |  |  |  |  | 2022-09-07 | Not Started | 2022-09-29 | Not Started | 2022-10-06 | Not Started | 2022-12-28 | 2022-12-28 | 0 | On/ Ahead Schedule | Not Started | 2022-12-29 | 2023-01-11 | Not Started | 2023-02-17 | Not Started
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | E.5014748.04 | 5786747 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 7682 | 7682 | 1.4549 | 0 | 1.4549 | [5 empty] | 250000 | 0 | 250000 | 24394.5 | 0 | 225605.5 | On/Under Budget | 2340980.9 | 33.2 | 0 | 33.2 | 0 | 0 | 23764.1 | 630.3 | Project is not in the WP or in 2020 WP | 0 | 936.3 | -936.3 | 936.3 | -936.3 | 20996.6 | 245.5 | -20611.8 | 33.2 | 33.2 | 33.2 | 34.4 | 34.4 | 34.4 | 34.4 | 34.4 | 34.4 | 236874.8 | 233257 | 2894.5 | 2894.5 | 2894.5 | 397217.9 | 420827.3 | 420827.3 | 418138 | 204882 | 0 | 0 | 2340707.8 | 2021-04-02 |  |  |  |  | 2020-08-06 | Completed | 2022-08-26 | 2022-08-26 | Not Started | 2021-04-02 | Not Started | 2022-08-29 | Not Started | 2022-08-26 | 2022-08-26 | Not Started | 2022-08-29 | 2022-08-30 | Not Started | 2021-04-06 | 2021-04-06 | Not Started | 2022-09-07 | Not Started |  |  |  |  | 2022-09-07 | Not Started | 2022-10-04 | Not Started | 2022-10-20 | Not Started | 2023-01-12 | 2023-01-12 | 0 | On/ Ahead Schedule | Not Started | 2023-01-13 | 2023-01-26 | Not Started | 2023-03-06 | Not Started
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | E.5014748.05 | 5786748 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 8342 | 8342 | 1.5799 | 0 | 1.5799 | [5 empty] | 250000 | 0 | 250000 | 23530.6 | 0 | 226469.4 | On/Under Budget | 2586840.6 | 193.6 | 0 | 193.6 | 0 | 0 | 22898.5 | 632 | Project is not in the WP or in 2020 WP | 0 | 2417 | -2417 | 2417 | -2417 | 22032.2 | 247.8 | -21648 | 193.6 | 193.6 | 193.6 | 200.7 | 200.7 | 200.7 | 200.7 | 200.7 | 200.7 | 121243.3 | 121386.6 | 239786.7 | 3133.5 | 3133.5 | 343005 | 574597.5 | 523416.9 | 466411.5 | 189135 | 0 | 0 | 2585249.5 | 2021-04-02 |  |  |  |  | 2020-08-06 | Completed | 2022-08-26 | 2022-08-26 | Not Started | 2021-04-02 | Not Started | 2022-09-02 | Not Started | 2022-08-26 | 2022-08-26 | Not Started | 2022-08-29 | 2022-09-02 | Not Started | 2021-04-09 | 2021-04-09 | Not Started | 2022-09-16 | Not Started |  |  |  |  | 2022-09-16 | Not Started | 2022-10-14 | Not Started | 2022-11-01 | Not Started | 2022-11-02 | 2022-11-02 | 0 | On/ Ahead Schedule | Not Started | 2022-11-04 | 2022-11-17 | Not Started | 2022-12-22 | Not Started
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 | E.5014748.06 | 5786749 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 5223 | 5223 | 0.9892 | 0 | 0.9892 | [5 empty] | 250000 | 0 | 250000 | 28479.6 | 0 | 221520.4 | On/Under Budget | 1767940.2 | 29 | 0 | 29 | 0 | 0 | 27777 | 702.7 | Project is not in the WP or in 2020 WP | 0 | 970.3 | -970.3 | 970.3 | -970.3 | 20873.8 | 270.7 | -20441.8 | 29 | 29 | 29 | 30.1 | 30.1 | 30.1 | 30.1 | 30.1 | 30.1 | 208298.4 | 184255.5 | 2417.9 | 2417.9 | 316552.8 | 289222.8 | 282966.4 | 262777.4 | 218792.5 | 0 | 0 | 0 | 1767701.6 | 2021-04-02 |  |  |  |  | 2020-06-24 | Completed | 2022-08-26 | 2022-09-08 | Not Started | 2020-09-28 | Completed | 2022-09-08 | Not Started | 2022-09-09 | 2022-09-09 | Not Started | 2022-09-12 | 2022-09-13 | Not Started | 2021-04-06 | 2021-04-06 | Not Started | 2022-09-21 | Not Started |  |  |  |  | 2022-09-21 | Not Started | 2022-10-14 | Not Started | 2022-11-01 | Not Started | 2023-01-24 | 2023-01-24 | 0 | On/ Ahead Schedule | Not Started | 2023-01-25 | 2023-02-07 | Not Started | 2023-03-16 | Not Started
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | E.5014748.07 | 5786750 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 7972 | 7972 | 1.5098 | 0 | 1.5098 | [5 empty] | 250000 | 0 | 250000 | 23850.8 | 0 | 226149.2 | On/Under Budget | 2910259.6 | 719.1 | 0 | 719.1 | 0 | 0 | 20719.9 | 3130.9 | Project is not in the WP or in 2020 WP | 0 | 131689.2 | -131689.2 | 131689.2 | -131689.2 | 81751.9 | 2461.4 | -81082.4 | 719.1 | 439.7 | 70778.4 | 10707.6 | 10498.6 | 10498.6 | 9269.8 | 8058.9 | 7587.6 | 302087.7 | 263829.3 | 7125.9 | 4693.6 | 4072 | 283853 | 309057.9 | 303087.8 | 284888.2 | 286057.5 | 287104.5 | 331450.2 | 2667307.6 | 2021-04-02 |  |  |  |  | 2020-08-14 | Completed | 2021-12-02 | 2021-12-02 | Not Started | 2021-04-02 | Not Started | 2022-05-20 | Not Started | 2021-12-02 | 2021-12-02 | Not Started | 2021-12-03 | 2021-12-03 | Not Started | 2021-04-05 | 2021-04-23 | Not Started | 2022-05-31 | Not Started |  |  |  |  | 2022-05-31 | Not Started | 2022-06-28 | Not Started | 2022-07-07 | Not Started | 2022-09-29 | 2022-09-29 | 0 | On/ Ahead Schedule | Not Started | 2022-09-30 | 2022-10-13 | Not Started | 2022-11-21 | Not Started
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 | E.5014747.02 | 5786751 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 7762 | 7762 | 1.4701 | 0 | 1.4701 | [5 empty] | 333333 | 0 | 333333 | 37537.8 | 0 | 295795.2 | On/Under Budget | 2705031.5 | 349.3 | 0 | 349.3 | 0 | 0 | 36874.3 | 663.5 | Project is not in the WP or in 2020 WP | 0 | 1187.4 | -1187.4 | 1187.4 | -1187.4 | 18683.5 | -18207.3 | 187.3 | 349.3 | 174.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6698.7 | 1344420.3 | 1347039.2 | 6698.7 | 0 | 0 | 0 | 2704856.9 | 2021-04-02 |  |  |  |  | 2020-09-28 | Completed | 2022-08-26 | 2022-08-26 | Not Started | 2021-04-02 | Not Started | 2022-08-29 | Not Started | 2022-08-26 | 2022-08-26 | Not Started | 2022-08-29 | 2022-08-29 | Not Started | 2021-04-05 | 2021-05-13 | Not Started | 2022-09-06 | Not Started |  |  |  |  | 2022-09-06 | Not Started | 2022-09-07 | Not Started | 2022-09-16 | Not Started | 2022-12-09 | 2022-12-09 | 0 | On/ Ahead Schedule | Not Started | 2022-12-12 | 2022-12-23 | Not Started | 2023-01-31 | Not Started
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | E.5014747.03 | 5786752 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 5626 | 5626 | 1.0655 | 0 | 1.0655 | [5 empty] | 333333 | 0 | 333333 | 85508.7 | 0 | 247824.3 | On/Under Budget | 1600939.4 | 214 | 0 | 214 | 0 | 0 | 79861.9 | 5646.8 | Project is not in the WP or in 2020 WP | 0 | 7620.2 | -7620.2 | 7620.2 | -7620.2 | 41748.7 | -36549.8 | 447.9 | 214 | 214 | 214 | 221.9 | 221.9 | 221.9 | 221.9 | 221.9 | 221.9 | 5029.3 | 3858.4 | 3880.1 | 3901.7 | 318000.8 | 317099.9 | 315760.7 | 315760.7 | 315888.1 | 0 | 0 | 0 | 1599179.7 | 2021-04-02 |  |  |  |  | 2020-06-05 | Completed | 2020-09-23 | 2020-10-09 | Completed | 2021-04-02 | Not Started | 2022-09-02 | Not Started | 2022-08-26 | 2022-08-26 | Not Started | 2022-08-29 | 2022-08-30 | Not Started | 2021-04-02 | 2021-04-02 | Not Started | 2022-09-13 | Not Started |  |  |  |  | 2022-09-13 | Not Started | 2022-10-03 | Not Started | 2022-10-14 | Not Started | 2023-01-06 | 2023-01-06 | 0 | On/ Ahead Schedule | Not Started | 2023-01-09 | 2023-01-20 | Not Started | 2023-02-28 | Not Started
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 | E.5014747.04 | 5786753 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 8284 | 8284 | 1.5689 | 0 | 1.5689 | [5 empty] | 333333 | 0 | 333333 | 47132 | 0 | 286201 | On/Under Budget | 2769226.8 | 665.1 | 0 | 665.1 | 0 | 0 | 45934 | 1198 | Project is not in the WP or in 2020 WP | 0 | 7330.3 | -7330.3 | 7330.3 | -7330.3 | 66155 | -65224.6 | 267.6 | 665.1 | 665.1 | 665.1 | 689.5 | 689.5 | 689.5 | 689.5 | 689.5 | 689.5 | 159683.6 | 204192.6 | 2920.1 | 2920.1 | 2920.1 | 440808.4 | 543293.4 | 517751 | 529839 | 314145.8 | 45285.4 | 0 | 2763759.5 | 2021-04-02 |  |  |  |  | 2020-10-28 | Completed | 2022-08-26 | 2022-08-29 | Not Started | 2021-04-02 | Not Started | 2022-09-02 | Not Started | 2022-08-30 | 2022-08-30 | Not Started | 2022-08-31 | 2022-09-01 | Not Started | 2021-04-06 | 2021-05-13 | Not Started | 2022-09-13 | Not Started |  |  |  |  | 2022-09-13 | Not Started | 2022-10-11 | Not Started | 2022-10-27 | Not Started | 2023-01-19 | 2023-01-19 | 0 | On/ Ahead Schedule | Not Started | 2023-01-20 | 2023-02-02 | Not Started | 2023-03-13 | Not Started
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | E.5014747.05 | 5786754 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 6878 | 6878 | 1.3027 | 0 | 1.3027 | [5 empty] | 333333 | 0 | 333333 | 36367.5 | 0 | 296965.5 | On/Under Budget | 2281806.1 | 50.7 | 0 | 50.7 | 0 | 0 | 35127 | 1240.5 | Project is not in the WP or in 2020 WP | 0 | 1707.6 | -1707.6 | 1707.6 | -1707.6 | 835.1 | 213.8 | 191.6 | 50.7 | 50.7 | 50.7 | 52.5 | 52.5 | 52.5 | 52.5 | 52.5 | 52.5 | 54.4 | 54.4 | 54.4 | 54.4 | 200672.1 | 207662.6 | 930767.1 | 935371.5 | 6698.7 | 0 | 0 | 0 | 2281389.6 | 2021-04-02 |  |  |  |  | 2020-08-10 | Completed | 2022-08-26 | 2022-09-08 | Not Started | 2021-04-02 | Not Started | 2022-09-08 | Not Started | 2022-09-09 | 2022-09-09 | Not Started | 2022-09-12 | 2022-09-13 | Not Started | 2021-04-06 | 2021-04-06 | Not Started | 2022-09-21 | Not Started |  |  |  |  | 2022-09-21 | Not Started | 2022-10-17 | Not Started | 2022-11-02 | Not Started | 2023-01-25 | 2023-01-25 | 0 | On/ Ahead Schedule | Not Started | 2023-01-26 | 2023-02-08 | Not Started | 2023-03-17 | Not Started
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | E.5014747.06 | 5786755 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 5997 | 5997 | 1.1358 | 0 | 1.1358 | [5 empty] | 333333 | 0 | 333333 | 35565.1 | 0 | 297767.9 | On/Under Budget | 1831439.4 | 42.5 | 0 | 42.5 | 0 | 0 | 34970.4 | 594.6 | Project is not in the WP or in 2020 WP | 0 | 788.1 | -788.1 | 788.1 | -788.1 | 195.4 | 210.7 | 188.5 | 42.5 | 42.5 | 42.5 | 44 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30178.8 | 900554.8 | 900554.8 | 0 | 0 | 0 | 0 | 1831288.4 | 2021-04-02 |  |  |  |  | 2020-07-17 | Completed | 2022-08-26 | 2022-08-26 | Not Started | 2021-04-02 | Not Started | 2022-09-02 | Not Started | 2022-08-26 | 2022-08-26 | Not Started | 2022-08-29 | 2022-08-30 | Not Started | 2021-04-06 | 2021-04-06 | Not Started | 2022-09-13 | Not Started |  |  |  |  | 2022-09-13 | Not Started | 2022-10-07 | Not Started | 2022-10-25 | Not Started | 2023-01-17 | 2023-01-17 | 0 | On/ Ahead Schedule | Not Started | 2023-01-18 | 2023-01-31 | Not Started | 2023-03-09 | Not Started
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | E.5014746.02 | 5786756 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 7303 | 7303 | 1.3831 | 0 | 1.3831 | [5 empty] | 250000 | 125000 | 125000 | 41312 | 0 | 83688 | On/Under Budget | 2090309.1 | 263.2 | 0 | 263.2 | 0 | 0 | 100151.8 | -58839.7 | Project is not in the WP or in 2020 WP | 0 | -56412.7 | 56412.7 | -56412.7 | 56412.7 | -59281.1 | 220.7 | 220.7 | 263.2 | 263.2 | 263.2 | 272.9 | 272.9 | 272.9 | 272.9 | 272.9 | 272.9 | 282.9 | 282.9 | 282.9 | 282.9 | 282.9 | 229152.8 | 1028030.5 | 829547.2 | 0 | 0 | 0 | 0 | 2088145 | 2021-04-02 |  |  |  |  | 2020-09-17 | Completed | 2022-08-26 | 2022-08-26 | Not Started | 2021-04-15 | Not Started | 2022-09-02 | Not Started | 2022-08-26 | 2022-08-26 | Not Started | 2022-08-29 | 2022-08-30 | Not Started | 2021-04-06 | 2021-04-06 | Not Started | 2022-09-13 | Not Started |  |  |  |  | 2022-09-13 | Not Started | 2022-10-10 | Not Started | 2022-10-26 | Not Started | 2023-01-18 | 2023-01-18 | 0 | On/ Ahead Schedule | Not Started | 2023-01-19 | 2023-02-01 | Not Started | 2023-03-10 | Not Started
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | E.5014746.03 | 5786757 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 8896 | 8896 | 1.6848 | 0 | 1.6848 | [5 empty] | 250000 | 0 | 250000 | 44966 | 0 | 205034 | On/Under Budget | 3231805.8 | 581.2 | 0 | 581.2 | 0 | 0 | 122971.2 | -78005.3 | Project is not in the WP or in 2020 WP | 0 | -72646.7 | 72646.7 | -72646.7 | 72646.7 | -80433.7 | 2172.4 | 256 | 581.2 | 581.2 | 581.2 | 602.5 | 602.5 | 602.5 | 602.5 | 602.5 | 602.5 | 101878.5 | 203750.3 | 82974.8 | 2969 | 15119.5 | 616494.6 | 694168.9 | 693870.1 | 625009.1 | 190793.8 | 0 | 0 | 3227028.6 | 2021-04-02 |  |  |  |  | 2020-10-05 | Completed | 2022-08-26 | 2022-08-26 | Not Started | 2021-04-02 | Not Started | 2022-09-02 | Not Started | 2022-08-26 | 2022-08-26 | Not Started | 2022-08-29 | 2022-08-30 | Not Started | 2021-04-06 | 2021-04-06 | Not Started | 2022-09-13 | Not Started |  |  |  |  | 2022-09-13 | Not Started | 2022-10-11 | Not Started | 2022-10-27 | Not Started | 2023-01-19 | 2023-01-19 | 0 | On/ Ahead Schedule | Not Started | 2023-01-20 | 2023-02-02 | Not Started | 2023-03-13 | Not Started
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | E.5014746.04 | 5786758 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 10990 | 10990 | 2.0814 | 0 | 2.0814 | [5 empty] | 125000 | -125000 | 250000 | 90131.7 | 0 | 159868.3 | On/Under Budget | 3961056.9 | 499.1 | 0 | 499.1 | 0 | 0 | 241035.8 | -150904.1 | Project is not in the WP or in 2020 WP | 0 | -146301.8 | 146301.8 | -146301.8 | 146301.8 | -153302.4 | 3843.1 | -1444.8 | 499.1 | 499.1 | 499.1 | 517.5 | 517.5 | 517.5 | 517.5 | 517.5 | 517.5 | 536.5 | 536.5 | 536.5 | 536.5 | 536.5 | 2271.3 | 500000 | 1726000 | 1726000 | 0 | 0 | 0 | 3956953.8 | 2021-04-02 |  |  |  |  | 2020-11-02 | Completed | 2022-08-26 | 2022-08-29 | Not Started | 2021-04-15 | Not Started | 2022-09-02 | Not Started | 2022-08-30 | 2022-08-30 | Not Started | 2022-08-31 | 2022-09-01 | Not Started | 2021-04-06 | 2021-06-04 | Not Started | 2022-09-13 | Not Started |  |  |  |  | 2022-09-13 | Not Started | 2022-10-13 | Not Started | 2022-10-31 | Not Started | 2023-01-23 | 2023-01-23 | 0 | On/ Ahead Schedule | Not Started | 2023-01-24 | 2023-02-06 | Not Started | 2023-03-15 | Not Started
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | E.5014760.02 | 5786672 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 8577 | 8577 | 1.6244 | 0 | 1.6244 | [5 empty] | 262500 | 0 | 262500 | 45321.7 | 0 | 217178.3 | On/Under Budget | 2581832 | 174.7 | 0 | 174.7 | 0 | 470.6 | 42489.1 | 2362 | Project is not in the WP or in 2020 WP | 0 | 3972.7 | -3972.7 | 3972.7 | -3972.7 | 1843.2 | 259.4 | 259.4 | 174.7 | 174.7 | 174.7 | 181.1 | 181.1 | 181.1 | 181.1 | 181.1 | 181.1 | 187.8 | 187.8 | 187.8 | 187.8 | 500187.8 | 1039187.8 | 1039194.7 | 194.7 | 194.7 | 194.7 | 194.7 | 194.7 | 2580295 | 2021-04-02 |  |  |  |  | 2020-08-13 | Completed | 2021-12-02 | 2021-12-22 | Not Started | 2021-04-02 | Not Started | 2021-12-22 | Not Started | 2021-12-23 | 2021-12-29 | Not Started | 2021-12-30 | 2022-01-19 | Not Started | 2021-04-23 | 2021-08-27 | Not Started | 2022-01-27 | Not Started |  |  |  |  | 2022-01-27 | Not Started | 2022-04-19 | Not Started | 2022-05-18 | Not Started | 2022-07-19 | 2022-07-19 | 0 | On/ Ahead Schedule | Not Started | 2022-07-20 | 2022-08-02 | Not Started | 2022-09-08 | Not Started
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | E.5014760.03 | 5786673 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 10289 | 10289 | 1.9487 | 0 | 1.9487 | [5 empty] | 262500 | 0 | 262500 | 110813.4 | 0 | 151686.6 | On/Under Budget | 3706306.7 | 284.6 | 0 | 284.6 | 0 | 0 | 109006 | 1807.4 | Project is not in the WP or in 2020 WP | 0 | 3398.7 | -3398.7 | 3398.7 | -3398.7 | 538.8 | 634.3 | 634.3 | 284.6 | 284.6 | 284.6 | 295 | 295 | 147.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1602500 | 1602500 | 0 | 0 | 0 | 0 | 3705000 | 2021-04-02 |  |  |  |  | 2020-09-03 | Completed | 2022-08-26 | 2022-08-26 | Not Started | 2021-04-02 | Not Started | 2022-09-01 | Not Started | 2022-08-26 | 2022-08-26 | Not Started | 2022-08-29 | 2022-08-30 | Not Started | 2021-04-06 | 2021-08-27 | Not Started | 2022-09-08 | Not Started |  |  |  |  | 2022-09-08 | Not Started | 2022-10-04 | Not Started | 2022-10-11 | Not Started | 2022-12-12 | 2022-12-12 | 0 | On/ Ahead Schedule | Not Started | 2022-12-13 | 2022-12-14 | Not Started | 2023-01-09 | Not Started
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 | E.5014760.04 | 5786674 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 10520 | 10520 | 1.9924 | 0 | 1.9924 | [5 empty] | 262500 | 0 | 262500 | 94967.9 | 0 | 167532.1 | On/Under Budget | 3785739.3 | 711 | 0 | 711 | 0 | 235.3 | 29011.9 | 65720.7 | Project is not in the WP or in 2020 WP | 0 | 71170.7 | -71170.7 | 71170.7 | -71170.7 | 64693.5 | 513.6 | 513.6 | 711 | 711 | 711 | 737.1 | 737.1 | 737.1 | 737.1 | 368.6 | 0 | 0 | 0 | 0 | 0 | 500000 | 1640500 | 1640500 | 0 | 0 | 0 | 0 | 0 | 3781000 | 2021-04-02 |  |  |  |  | 2020-10-20 | Completed | 2021-12-02 | 2021-12-15 | Not Started | 2021-04-02 | Not Started | 2021-12-15 | Not Started | 2021-12-16 | 2021-12-16 | Not Started | 2021-12-17 | 2022-01-06 | Not Started | 2021-04-23 | 2021-07-16 | Not Started | 2022-01-20 | Not Started |  |  |  |  | 2022-01-20 | Not Started | 2022-03-16 | Not Started | 2022-04-14 | Not Started | 2022-05-16 | 2022-05-16 | 0 | On/ Ahead Schedule | Not Started | 2022-05-17 | 2022-05-30 | Not Started | 2022-07-06 | Not Started
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | E.5014760.05 | 5786675 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 8750 | 8750 | 1.6572 | 0 | 1.6572 | [5 empty] | 262500 | 0 | 262500 | 83373.3 | 0 | 179126.7 | On/Under Budget | 3164448.1 | 476.4 | 0 | 476.4 | 0 | 0 | 80347.1 | 3026.2 | Project is not in the WP or in 2020 WP | 0 | 7418.8 | -7418.8 | 7418.8 | -7418.8 | 2071.8 | 477.2 | 477.2 | 476.4 | 476.4 | 476.4 | 493.9 | 493.9 | 493.9 | 493.9 | 493.9 | 493.9 | 512 | 512 | 512 | 512 | 512 | 512 | 530.8 | 500530.8 | 1327530.8 | 1327530.8 | 530.8 | 530.8 | 3160256.8 | 2021-04-02 |  |  |  |  | 2020-09-11 | Completed | 2021-12-02 | 2021-12-22 | Not Started | 2021-04-02 | Not Started | 2021-12-22 | Not Started | 2021-12-23 | 2021-12-23 | Not Started | 2021-12-24 | 2022-01-13 | Not Started | 2021-04-23 | 2021-09-16 | Not Started | 2022-01-27 | Not Started |  |  |  |  | 2022-01-27 | Not Started | 2022-04-19 | Not Started | 2022-05-18 | Not Started | 2022-07-19 | 2022-07-19 | 0 | On/ Ahead Schedule | Not Started | 2022-07-20 | 2022-08-02 | Not Started | 2022-09-08 | Not Started
35129640 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 | E.5014760.06 | 5786676 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 8536 | 8536 | 1.6167 | 0 | 1.6167 | [5 empty] | 262500 | 0 | 262500 | 15471.8 | 0 | 247028.2 | On/Under Budget | 3078566.4 | 25.8 | 0 | 25.8 | 0 | 0 | 15201.9 | 270 | Project is not in the WP or in 2020 WP | 0 | 508.2 | -508.2 | 508.2 | -508.2 | 92.8 | 88.6 | 88.6 | 25.8 | 25.8 | 25.8 | 26.8 | 26.8 | 26.8 | 26.8 | 26.8 | 26.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 27.8 | 500028.8 | 1289028.8 | 1289028.8 | 28.8 | 28.8 | 28.8 | 3078339.6 | 2021-04-02 |  |  |  |  | 2020-06-25 | Completed | 2021-12-02 | 2021-12-15 | Not Started | 2021-04-02 | Not Started | 2021-12-15 | Not Started | 2021-12-16 | 2021-12-16 | Not Started | 2021-12-17 | 2022-01-06 | Not Started | 2021-04-23 | 2021-09-16 | Not Started | 2022-01-20 | Not Started |  |  |  |  | 2022-01-20 | Not Started | 2022-04-12 | Not Started | 2022-05-11 | Not Started | 2022-06-10 | 2022-06-10 | 0 | On/ Ahead Schedule | Not Started | 2022-06-13 | 2022-06-24 | Not Started | 2022-08-02 | Not Started
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | E.5014760.07 | 5786677 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 7019 | 7019 | 1.3294 | 0 | 1.3294 | [5 empty] | 262500 | 0 | 262500 | 42363 | 0 | 220137 | On/Under Budget | 2527942.9 | 43 | 0 | 43 | 0 | 0 | 38158.2 | 4204.7 | Project is not in the WP or in 2020 WP | 0 | 4601.3 | -4601.3 | 4601.3 | -4601.3 | 43512.9 | 2851.3 | -42159.5 | 43 | 43 | 43 | 44.6 | 44.6 | 44.6 | 44.6 | 44.6 | 44.6 | 46.2 | 46.2 | 46.2 | 500046.2 | 1013546.2 | 1013546.2 | 47.9 | 47.9 | 47.9 | 47.9 | 47.9 | 47.9 | 2527564.6 | 2021-04-02 |  |  |  |  | 2020-09-08 | Completed | 2021-12-02 | 2021-12-22 | Not Started | 2021-04-15 | Not Started | 2021-12-22 | Not Started | 2021-12-23 | 2022-01-12 | Not Started | 2022-01-13 | 2022-02-02 | Not Started | 2021-04-23 | 2021-10-06 | Not Started | 2022-02-10 | Not Started |  |  |  |  | 2022-02-10 | Not Started | 2022-04-29 | Not Started | 2022-05-30 | Not Started | 2022-06-29 | 2022-06-29 | 0 | On/ Ahead Schedule | Not Started | 2022-06-30 | 2022-07-13 | Not Started | 2022-08-19 | Not Started
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | E.5014760.08 | 5786738 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 6255 | 6255 | 1.1847 | 0 | 1.1847 | [5 empty] | 262500 | 0 | 262500 | 52732.3 | 0 | 209767.7 | On/Under Budget | 2251814.7 | 330 | 0 | 330 | 0 | 0 | 14850.4 | 37881.9 | Project is not in the WP or in 2020 WP | 0 | 40924.5 | -40924.5 | 40924.5 | -40924.5 | 32223.4 | 5355.9 | 302.6 | 330 | 330 | 330 | 342.1 | 342.1 | 342.1 | 342.1 | 342.1 | 342.1 | 354.7 | 354.7 | 354.7 | 354.7 | 500354.7 | 871354.7 | 871367.7 | 2875.4 | 383.1 | 383.1 | 383.1 | 383.1 | 2248903.7 | 2021-04-02 |  |  |  |  | 2020-10-30 | Completed | 2021-12-02 | 2021-12-22 | Not Started | 2021-04-02 | Not Started | 2021-12-22 | Not Started | 2021-12-23 | 2022-01-12 | Not Started | 2022-01-13 | 2022-02-02 | Not Started | 2021-04-23 | 2021-10-28 | Not Started | 2022-02-10 | Not Started |  |  |  |  | 2022-02-10 | Not Started | 2022-04-29 | Not Started | 2022-05-30 | Not Started | 2022-06-29 | 2022-06-29 | 0 | On/ Ahead Schedule | Not Started | 2022-06-30 | 2022-07-13 | Not Started | 2022-08-19 | Not Started
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | E.5014755.02 | 5786739 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 10869 | 10869 | 2.0585 | 0 | 2.0585 | [5 empty] | 271429 | 0 | 271429 | 67570.3 | 0 | 203858.7 | On/Under Budget | 4757808.9 | 582.5 | 0 | 582.5 | 0 | 0 | 62668.8 | 4901.5 | Project is not in the WP or in 2020 WP | 0 | 10272.4 | -10272.4 | 10272.4 | -10272.4 | 386.5 | 4128.1 | 386.9 | 582.5 | 582.5 | 582.5 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 603.9 | 626.1 | 626.1 | 626.1 | 626.1 | 626.1 | 626647.6 | 1142232.4 | 1124404.2 | 1063733.4 | 792872.2 | 0 | 0 | 4753020.3 | 2021-04-02 |  |  |  |  | 2020-09-23 | Completed | 2022-08-26 | 2022-08-26 | Not Started | 2021-04-02 | Not Started | 2022-09-02 | Not Started | 2022-08-26 | 2022-08-26 | Not Started | 2022-08-29 | 2022-08-30 | Not Started | 2021-04-06 | 2021-06-04 | Not Started | 2022-09-13 | Not Started |  |  |  |  | 2022-09-13 | Not Started | 2022-10-06 | Not Started | 2022-10-17 | Not Started | 2023-01-09 | 2023-01-09 | 0 | On/ Ahead Schedule | Not Started | 2023-01-10 | 2023-01-23 | Not Started | 2023-03-01 | Not Started
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | E.5014755.03 | 5786740 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 5214 | 5214 | 0.9875 | 0 | 0.9875 | [5 empty] | 271429 | 0 | 271429 | 56327.4 | 0 | 215101.6 | On/Under Budget | 1515253 | 37 | 0 | 37 | 0 | 0 | 50990.8 | 5336.5 | Project is not in the WP or in 2020 WP | 0 | 5677.9 | -5677.9 | 5677.9 | -5677.9 | 4610.3 | 413.4 | 312.8 | 37 | 37 | 37 | 38.4 | 38.4 | 38.4 | 38.4 | 38.4 | 38.4 | 39.8 | 39.8 | 39.8 | 39.8 | 39.8 | 505196.4 | 504404.9 | 505148.7 | 0 | 0 | 0 | 0 | 1514949 | 2021-04-02 |  |  |  |  | 2020-07-31 | Completed | 2022-08-26 | 2022-08-26 | Not Started | 2021-04-02 | Not Started | 2022-09-02 | Not Started | 2022-08-26 | 2022-08-26 | Not Started | 2022-08-29 | 2022-08-30 | Not Started | 2021-04-06 | 2021-04-23 | Not Started | 2022-09-13 | Not Started |  |  |  |  | 2022-09-13 | Not Started | 2022-10-06 | Not Started | 2022-10-24 | Not Started | 2023-01-16 | 2023-01-16 | 0 | On/ Ahead Schedule | Not Started | 2023-01-17 | 2023-01-30 | Not Started | 2023-03-08 | Not Started
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | E.5014755.04 | 5786741 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 6367 | 6367 | 1.2059 | 0 | 1.2059 | [5 empty] | 271429 | 0 | 271429 | 34605.2 | 0 | 236823.8 | On/Under Budget | 1938321.5 | 283.2 | 0 | 283.2 | 0 | 0 | 26367 | 8238.2 | Project is not in the WP or in 2020 WP | 0 | 10849.4 | -10849.4 | 10849.4 | -10849.4 | 7861.2 | 188.5 | 188.5 | 283.2 | 283.2 | 283.2 | 293.6 | 293.6 | 293.6 | 293.6 | 293.6 | 293.6 | 304.4 | 304.4 | 304.4 | 304066.3 | 109356.9 | 347349 | 335434.7 | 307646.3 | 292504.5 | 238722.6 | 0 | 0 | 1935993.5 | 2021-04-02 |  |  |  |  | 2020-08-06 | Completed | 2022-08-26 | 2022-08-26 | Not Started | 2021-04-02 | Not Started | 2022-09-02 | Not Started | 2022-08-26 | 2022-08-26 | Not Started | 2022-08-29 | 2022-08-30 | Not Started | 2021-04-06 | 2021-06-25 | Not Started | 2022-09-13 | Not Started |  |  |  |  | 2022-09-13 | Not Started | 2022-10-07 | Not Started | 2022-10-25 | Not Started | 2023-01-17 | 2023-01-17 | 0 | On/ Ahead Schedule | Not Started | 2023-01-18 | 2023-01-31 | Not Started | 2023-03-09 | Not Started
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | E.5014755.05 | 5786742 | PEND | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 6644 | 6644 | 1.2583 | 0 | 1.2583 | [5 empty] | 271429 | 0 | 271429 | 42886.8 | 0 | 228542.2 | On/Under Budget | 1996611.1 | 98.5 | 0 | 98.5 | 0 | 0 | 40820.1 | 2066.7 | Project is not in the WP or in 2020 WP | 0 | 2975.4 | -2975.4 | 2975.4 | -2975.4 | 237.3 | 456.7 | 1372.7 | 98.5 | 98.5 | 98.5 | 102.2 | 102.2 | 102.2 | 102.2 | 102.2 | 102.2 | 105.9 | 105.9 | 105.9 | 105.9 | 17488.6 | 483268.5 | 491024.3 | 455225.1 | 291570.8 | 256800 | 0 | 0 | 1995800.9 | 2021-04-02 |  |  |  |  | 2020-07-14 | Completed | 2022-08-26 | 2022-08-26 | Not Started | 2021-04-02 | Not Started | 2022-09-01 | Not Started | 2022-08-26 | 2022-08-26 | Not Started | 2022-08-29 | 2022-08-30 | Not Started | 2021-04-06 | 2021-06-25 | Not Started | 2022-09-13 | Not Started |  |  |  |  | 2022-09-13 | Not Started | 2022-10-07 | Not Started | 2022-10-25 | Not Started | 2023-01-17 | 2023-01-17 | 0 | On/ Ahead Schedule | Not Started | 2023-01-18 | 2023-01-31 | Not Started | 2023-03-09 | Not Started
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | E.5014721.04 | 5786761 | PEND | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 7772 | 7772 | 1.472 | 0 | 1.472 | [5 empty] | 300000 | 0 | 300000 | 41171.4 | 0 | 258828.6 | On/Under Budget | 27.3 | 54.6 | 0 | 54.6 | 0 | 235.3 | 40220.4 | 715.7 | Project is not in the WP or in 2020 WP | 0 | 797.6 | -797.6 | 797.6 | -797.6 | 247.7 | 245.1 | 222.9 | 54.6 | 27.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145826 | BL-A: | BL-A: 35129306_CWSP - ORO FINO 1102 - LR2560 PH 1.4_08W - June 2021 | 2020-07-24 | 2020-09-04 | Completed | 2022-03-21 | 2022-04-29 | Not Started | 2022-03-18 | Not Started | 2022-04-29 | Not Started | 2022-05-23 | 2022-05-23 | Not Started | 2022-05-24 | 2022-08-15 | Not Started | 2022-04-11 | 2022-05-13 | Not Started | 2022-09-13 | Not Started |  |  |  |  | 2022-09-13 | Not Started | 2022-12-12 | Not Started | 2023-01-27 | Not Started | 2021-06-30 | 2023-02-24 | -604 | Behind Schedule | Not Started | 2023-02-27 | 2023-03-10 | Not Started | 2023-04-18 | Not Started
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | E.5014724.03 | 5786776 | PEND | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2022 |  | CHICO | North Valley Assets | 0 | 7291 | 7291 | 1.3809 | 0 | 1.3809 | [5 empty] | 305556 | 0 | 305556 | 99526.8 | 0 | 206029.2 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 97746 | 1780.7 | Project is not in the WP or in 2020 WP | 0 | 1780.7 | -1780.7 | 1780.7 | -1780.7 | 774.9 | 502.9 | 502.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2020-09-30 | Completed | 2021-12-27 | 2022-01-07 | Not Started | 2022-01-14 | Not Started | 2022-01-17 | Not Started | 2022-01-10 | 2022-01-10 | Not Started | 2022-03-22 | 2022-04-11 | Not Started | 2022-01-10 | 2022-01-21 | Not Started | 2022-07-25 | Not Started |  |  |  |  | 2022-07-25 | Not Started | 2022-10-14 | Not Started | 2022-11-14 | Not Started | 2022-12-12 | 2022-12-12 | 0 | On/ Ahead Schedule | Not Started | 2022-12-13 | 2022-12-26 | Not Started | 2023-02-01 | Not Started
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | E.5014724.04 | 5786777 | PEND | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 5493 | 5493 | 1.0403 | 0 | 1.0403 | [5 empty] | 305556 | 0 | 305556 | 85334.2 | 0 | 220221.8 | On/Under Budget | 148.3 | 22.3 | 0 | 22.3 | 0 | 0 | 82469.8 | 2864.4 | Project is not in the WP or in 2020 WP | 0 | 3035.2 | -3035.2 | 3035.2 | -3035.2 | 1942.2 | 461.1 | 461.1 | 22.3 | 22.3 | 22.3 | 23.1 | 23.1 | 23.1 | 23.1 | 11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2020-10-05 | Completed | 2022-04-29 | 2022-05-12 | Not Started | 2022-04-28 | Not Started | 2022-05-12 | Not Started | 2022-05-13 | 2022-05-13 | Not Started | 2022-05-16 | 2022-06-03 | Not Started | 2022-05-20 | 2022-06-02 | Not Started | 2022-11-18 | Not Started |  |  |  |  | 2022-11-18 | Not Started | 2022-12-16 | Not Started | 2023-01-27 | Not Started | 2023-02-28 | 2023-02-28 | 0 | On/ Ahead Schedule | Not Started | 2023-03-01 | 2023-03-14 | Not Started | 2023-04-20 | Not Started
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 | E.5014724.05 | 5786778 | PEND | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2022 |  | CHICO | North Valley Assets | 0 | 6678 | 6678 | 1.2648 | 0 | 1.2648 | [5 empty] | 1351444.1 | 1101444.1 | 250000 | 4484.5 | 0 | 245515.5 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 4428.2 | 56.4 | Project is not in the WP or in 2020 WP | 0 | 56.4 | -56.4 | 56.4 | -56.4 | -3060.6 | 3092.8 | 24.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2020-11-04 | Completed | 2022-04-15 | 2022-04-28 | Not Started | 2022-05-12 | Not Started | 2022-05-13 | Not Started | 2022-04-29 | 2022-04-29 | Not Started | 2022-05-02 | 2022-05-20 | Not Started | 2022-05-09 | 2022-05-20 | Not Started | 2022-10-14 | Not Started |  |  |  |  | 2022-10-14 | Not Started | 2023-01-02 | Not Started | 2023-01-31 | Not Started | 2023-02-28 | 2023-02-28 | 0 | On/ Ahead Schedule | Not Started | 2023-03-01 | 2023-03-14 | Not Started | 2023-04-20 | Not Started
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | E.5014724.06 | 5786779 | PEND | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2022 |  | CHICO | North Valley Assets | 0 | 10499 | 10499 | 1.9884 | 0 | 1.9884 | [5 empty] | 305556 | 0 | 305556 | 128793.2 | 0 | 176762.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 120312.1 | 8481 | Project is not in the WP or in 2020 WP | 0 | 8481 | -8481 | 8481 | -8481 | 7006.6 | 737.2 | 737.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2020-10-21 | Completed | 2022-02-25 | 2022-03-10 | Not Started | 2022-03-03 | Not Started | 2022-03-10 | Not Started | 2022-03-11 | 2022-03-11 | Not Started | 2022-03-14 | 2022-04-01 | Not Started | 2022-03-18 | 2022-03-31 | Not Started | 2022-08-26 | Not Started |  |  |  |  | 2022-08-26 | Not Started | 2022-11-17 | Not Started | 2022-12-16 | Not Started | 2023-01-13 | 2023-01-13 | 0 | On/ Ahead Schedule | Not Started | 2023-01-16 | 2023-01-27 | Not Started | 2023-03-07 | Not Started
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | E.5014724.07 | 5786780 | PEND | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2022 |  | CHICO | North Valley Assets | 0 | 9273 | 9273 | 1.7563 | 0 | 1.7563 | [5 empty] | 999695.19 | 749695.19 | 250000 | 20309.7 | 0 | 229690.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 17504.5 | 2805.3 | Project is not in the WP or in 2020 WP | 0 | 2805.3 | -2805.3 | 2805.3 | -2805.3 | 2586.9 | 109.2 | 109.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2020-10-23 | Completed | 2022-04-08 | 2022-04-21 | Not Started | 2022-04-08 | Not Started | 2022-04-21 | Not Started | 2022-04-22 | 2022-04-22 | Not Started | 2022-04-25 | 2022-08-26 | Not Started | 2022-04-29 | 2022-05-12 | Not Started | 2022-10-07 | Not Started |  |  |  |  | 2022-10-07 | Not Started | 2022-12-28 | Not Started | 2023-01-26 | Not Started | 2023-02-23 | 2023-02-23 | 0 | On/ Ahead Schedule | Not Started | 2023-02-24 | 2023-03-09 | Not Started | 2023-04-17 | Not Started
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | PEND | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | GRSSVLLY | Sierra Assets | 0 | 4793 | 4793 | 0.90777 | 0 | 0.90777 | [5 empty] | 2485715 | 683214.7 | 1802500.3 | 442989.1 | 0 | 1359511.2 | On/Under Budget | 0 | 0 | -20 | 20 | 0 | 235.3 | 434935.9 | 7797.9 | Project is not in the WP or in 2020 WP | 0 | 7817.9 | -7817.9 | 7817.9 | -7817.9 | 2595.6 | 2649.5 | 2572.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2020-08-20 | Completed | 2020-08-25 | 2020-09-25 | Completed | 2020-08-21 | Completed | 2020-09-30 | Completed | 2020-10-02 | 2020-10-02 | Completed | 2020-09-29 | 2021-12-02 | In Progress | 2020-09-02 | 2020-10-31 | Completed | 2021-12-06 | Not Started |  |  |  |  | 2021-12-06 | Not Started | 2022-03-18 | Not Started | 2022-04-18 | Not Started | 2022-06-17 | 2022-06-17 | 0 | On/ Ahead Schedule | Not Started | 2022-06-20 | 2022-07-01 | Not Started | 2022-08-09 | Not Started
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | 5530164 | PEND | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 | 2020 | SH | CLRLAKE | Humboldt Division Assets | 0 | 5131 | 5131 | 0.97178 | 0 | 0.97178 | 5341 | 0 | 1.0116 | 0 | GC | 234191.77 | 154191.77 | 80000 | 65048.7 | 0 | 14951.3 | On/Under Budget | 10764.7 | 3588.2 | 0 | 3588.2 | 0 | 0 | 3845.7 | 61203.1 | Request 2021 Budget | 0 | 75555.9 | -75555.9 | 75555.9 | -75555.9 | 459.9 | 13539.5 | 47203.7 | 3588.2 | 3588.2 | 3588.2 | 3588.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156049 | BL-A | BL-A 35137596_CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08_08W - Feb. 2021 | 2021-02-17 | 2021-03-22 | Completed | 2021-04-09 | 2021-04-22 | Not Started | 2021-09-27 | Not Started | 2021-09-28 | Not Started | 2021-04-23 | 2021-04-23 | Not Started | 2021-04-26 | 2021-10-14 | Not Started | 2021-09-27 | 2021-10-08 | Not Started | 2021-10-26 | Not Started |  |  |  |  | 2021-10-26 | Not Started | 2021-12-20 | Not Started | 2022-01-18 | Not Started | 2022-03-21 | 2022-03-21 | 0 | On/ Ahead Schedule | Not Started | 2022-03-22 | 2022-04-04 | Not Started | 2022-05-11 | Not Started
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | PEND | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2021 | SH | ANGLSCMP | Stockton Assets | 2846 | 3872 | 6718 | 1.2723 | 0 | 1.2723 | 6718 | 0 | 1.2723 | 0 | Contract | 5959167 | 1836977 | 4122190 | 247306.5 | 33975 | 3908858.5 | On/Under Budget | 3538360.3 | 578473.5 | -200 | 578673.5 | 0 | 0 | 187046.8 | 60059.7 | Budget Allocated | 4139274.6 | 4135581.6 | 3693 | 4134335.6 | 4939 | 22610.4 | 30732.5 | 6916.8 | 578473.5 | 451290.1 | 454129.2 | 452288.2 | 447736 | 447704.3 | 447121.2 | 483131.7 | 312201.7 | 42757.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42757.9 | 2021-04-02 | 158094 | BL-0_ | BL-0_35145540_PSPS - Frogtown 1702 - CB_08W_Mar.2021 | 2021-03-30 | 2020-09-02 | Completed | 2021-02-01 | 2021-02-19 | Not Started | 2021-06-29 | Not Started | 2021-06-30 | Not Started | 2021-04-02 | 2021-04-02 | Not Started | 2021-04-05 | 2021-04-23 | Not Started | 2021-02-01 | 2021-02-12 | Completed | 2022-03-30 | Not Started |  |  |  |  | 2022-03-30 | Not Started | 2022-06-28 | Not Started | 2022-07-27 | Not Started | 2022-09-13 | 2022-09-27 | -14 | Behind Schedule | Not Started | 2022-09-28 | 2022-10-11 | Not Started | 2022-11-17 | Not Started
35145006 | PSPS - STAFFORD 1101 LR 1298 | E.5025644.01 | 5788788 | PEND | 08W | DWPH | David William Phillips | D5A8 | Daniel Arrow |  |  | Not in the WP | 2021 | SH | SNRAFAEL | North Bay Assets | 1426 | 0 | 1426 | 0.27008 | 0 | 0.27008 | [5 empty] | 1039463.18 | 539463.18 | 500000 | 133469.5 | 0 | 366530.5 | On/Under Budget | 986366.1 | 344.7 | 0 | 344.7 | 0 | 1411.7 | 128240.8 | 3817 | Project is not in the WP or in 2020 WP | 0 | 6995.5 | -6995.5 | 6995.5 | -6995.5 | 1919.2 | 912.1 | 985.7 | 344.7 | 344.7 | 344.7 | 357.4 | 357.4 | 357.4 | 357.4 | 357.4 | 357.4 | 5262.2 | 5290 | 5317.8 | 69219.2 | 582558.4 | 291664 | 24220.8 | 0 | 0 | 0 | 0 | 0 | 983532.4 | 2021-03-01 | 147036 | BL-A | BL-A 35145006_CWSP - STAFFORD 1101 LR 1298_08W - JUNE 2021 | 2020-08-12 | 2022-01-04 | Not Started | 2022-01-06 | 2022-01-19 | Not Started |  |  | 2022-02-15 | Not Started | [9 empty] | 2022-05-19 | Not Started |  |  |  |  | 2022-05-19 | Not Started | 2022-07-13 | Not Started | 2022-07-13 | Not Started | 2021-06-29 | 2022-07-13 | -379 | Behind Schedule | Not Started | 2022-06-23 | 2022-07-06 | Not Started | 2022-11-25 | Not Started
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | PEND | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | AUBURN | Sierra Assets | 20830 | 0 | 20830 | 3.9451 | 0 | 3.9451 | [5 empty] | 500000 | 0 | 500000 | 157260 | 9900 | 352640 | On/Under Budget | 1194 | 260 | 0 | 260 | 0 | 0 | 150941.2 | 6318.7 | Project is not in the WP or in 2020 WP | 0 | 7772.7 | -7772.7 | 7772.7 | -7772.7 | 4134.2 | 1285.3 | 899.2 | 260 | 260 | 260 | 269.6 | 269.6 | 134.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2020-06-16 | Completed | 2022-02-18 | 2022-02-24 | Not Started | 2021-12-02 | Not Started | 2022-03-17 | Not Started | 2021-12-03 | 2021-12-03 | Not Started | 2021-12-06 | 2021-12-24 | Not Started |  |  |  | 2022-04-11 | Not Started |  |  |  |  | 2022-04-11 | Not Started | 2022-09-05 | Not Started | 2022-10-04 | Not Started | 2022-12-05 | 2022-12-05 | 0 | On/ Ahead Schedule | Not Started | 2022-12-06 | 2022-12-19 | Not Started | 2023-01-25 | Not Started
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | E.5025637.01 | 5788786 | PEND | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 | 2021 | SH | STROSA | Sonoma Assets | 3800 | 0 | 3800 | 0.7197 | 0 | 0.7197 | 12175 | 0 | 2.3059 | 0 | GC | 8431936 | 1511978 | 6919958 | 229132.3 | 382026.4 | 7072852.1 | On/Under Budget | 1059386 | 1949206.4 | 296.7 | 1948909.7 | 0 | 705.8 | 159181.9 | 69541.4 | Request 2021 Budget | 0 | 5867149.2 | -5867149.2 | 3077837 | -3077837 | 8173.6 | 8905.9 | 52165.2 | 1949206.4 | 996565.5 | 38158.1 | 21144.3 | 3518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2020-11-02 | Completed | 2021-02-12 | 2021-03-08 | Completed | 2021-02-12 | Completed | 2021-03-06 | Completed | 2021-03-09 | 2021-03-10 | Completed | 2021-03-10 | 2021-03-10 | Completed | 2021-03-01 | 2021-03-03 | Completed | 2021-04-26 | Not Started |  |  |  |  | 2021-06-07 | Not Started | 2021-07-02 | Not Started | 2021-08-02 | Not Started | 2021-10-01 | 2021-10-01 | 0 | On/ Ahead Schedule | Not Started | 2021-10-04 | 2021-10-15 | Not Started | 2021-11-23 | Not Started
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | E.5025642.01 | 5788782 | PEND | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | Not in the WP | 2021 | SH | WALNTCRK | Diablo Assets | 3073 | 1965 | 5038 | 0.95417 | 0 | 0.95417 | [5 empty] | 2226024.86 | 1726024.86 | 500000 | 100096.5 | 0 | 399903.5 | On/Under Budget | 2427949.7 | 1111.4 | 0 | 1111.4 | 0 | 4705.5 | 89894.3 | 5496.7 | Project is not in the WP or in 2020 WP | 0 | 15714.9 | -15714.9 | 15714.9 | -15714.9 | 1533.1 | 2059.6 | 1904 | 1111.4 | 1115.7 | 1119.9 | 1134.6 | 1138.8 | 1143.1 | 1147.3 | 1151.6 | 1155.8 | 899290.1 | 392319 | 394595.9 | 397282.8 | 248057.7 | 19870.6 | 20254.4 | 20288.6 | 15246.5 | 5818.7 | 5818.7 | 0 | 2418843 | 2021-04-02 | 147016 | BL-A | BL-A 35145004_CWSP - ROSSMOOR 1106 - CB - JUNE 2021 | 2020-08-11 | 2020-07-13 | Completed | 2022-05-13 | 2022-06-09 | Not Started | 2021-04-12 | Not Started | 2022-06-09 | Not Started |  |  |  | 2022-06-03 | 2022-07-14 | Not Started | 2022-04-15 | 2022-04-15 | Not Started | 2022-07-22 | Not Started |  |  |  |  | 2022-08-12 | Not Started | 2022-09-08 | Not Started | 2022-10-14 | Not Started | 2021-06-18 | 2022-11-11 | -511 | Behind Schedule | Not Started | 2022-11-14 | 2022-11-25 | Not Started | 2023-03-31 | Not Started
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | E.5025646.01 | 5788792 | PEND | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | Not in the WP | 2021 | SH | STCRUZ | Central Coast Assets | 3859 | 9792 | 13651 | 2.5854 | 0 | 2.5854 | [5 empty] | 4516366.87 | 4016366.87 | 500000 | 228198.7 | 0 | 271801.3 | On/Under Budget | 5891606.4 | 1360 | 0 | 1360 | 0 | 5881.9 | 188977.4 | 33339.4 | Project is not in the WP or in 2020 WP | 0 | 45839.3 | -45839.3 | 45839.3 | -45839.3 | 8724.9 | 21953.2 | 2661.3 | 1360 | 1364.2 | 1368.5 | 1390.6 | 1394.8 | 1399.1 | 1403.3 | 1407.6 | 1411.8 | 17498 | 31368.9 | 565552.3 | 670157.7 | 1548337.1 | 974527.2 | 980164.9 | 970703 | 34902.1 | 34902.1 | 34902.1 | 17451 | 5880466.4 | 2021-04-02 | 147009 | BL-A | BL-A 35144941_PSPS - PAUL SWEET 2105 - CB PH 1 - SEPT 2021 | 2020-08-11 | 2020-12-16 | Completed | 2022-04-15 | 2022-05-19 | Not Started | 2022-04-14 | Not Started | 2022-05-19 | Not Started | 2022-05-20 | 2022-06-09 | Not Started | 2022-06-10 | 2022-06-23 | Not Started | 2022-05-20 | 2022-06-09 | Not Started | 2022-07-25 | Not Started |  |  |  |  | 2022-07-25 | Not Started | 2022-12-16 | Not Started | 2023-01-16 | Not Started | 2021-09-27 | 2023-02-13 | -504 | Behind Schedule | Not Started | 2023-02-14 | 2023-02-27 | Not Started | 2023-04-05 | Not Started
35144943 | PSPS - ROB ROY 2105 - CB | E.5025648.01 | 5788791 | PEND | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | Not in the WP | 2021 | SH | STCRUZ | Central Coast Assets | 3326 | 0 | 3326 | 0.62992 | 0 | 0.62992 | [5 empty] | 687880.23 | 187880.23 | 500000 | 109654.6 | 0 | 390345.4 | On/Under Budget | 1633790.2 | 2244.5 | 0 | 2244.5 | 0 | 2588 | 97677.2 | 9389.4 | Project is not in the WP or in 2020 WP | 0 | 20536.9 | -20536.9 | 20536.9 | -20536.9 | 5125.8 | 2722.4 | 1541.2 | 2244.5 | 1090.6 | 1094.8 | 1109 | 1113.2 | 1117.5 | 1121.7 | 1126 | 1130.2 | 9200.3 | 9246 | 22526.2 | 1484137.4 | 33530.2 | 17525.9 | 12020.4 | 12033.2 | 9867 | 9867 | 4933.5 | 0 | 1624887.1 | 2021-04-02 | 147011 | BL-A | BL-A 35144943_PSPS - ROB ROY 2105 - CB - APRIL 2021 | 2020-08-11 | 2020-11-16 | Completed | 2022-09-30 | 2022-10-20 | Not Started | 2022-09-29 | Not Started | 2022-10-20 | Not Started | 2022-10-21 | 2022-10-27 | Not Started | 2022-10-28 | 2022-10-31 | Not Started | 2022-09-30 | 2022-10-13 | Not Started | 2022-11-03 | Not Started |  |  |  |  | 2022-11-03 | Not Started | 2022-11-28 | Not Started | 2022-12-05 | Not Started | 2021-04-29 | 2023-02-03 | -645 | Behind Schedule | Not Started | 2023-02-06 | 2023-02-17 | Not Started | 2023-03-28 | Not Started
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | 5530170 | PEND | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | Not in the WP | 2021 | SH | SNMATEO | Peninsula Assets | 1348 | 0 | 1348 | 0.2553 | 0 | 0.2553 | [5 empty] | 500000 | 0 | 500000 | 123924.8 | 0 | 376075.2 | On/Under Budget | 1379331.6 | 725.1 | 0 | 725.1 | 0 | 1643.5 | 118567.7 | 3713.5 | Project is not in the WP or in 2020 WP | 0 | 10239.4 | -10239.4 | 10239.4 | -10239.4 | 670.7 | 1414.5 | 1628.3 | 725.1 | 725.1 | 725.1 | 725.1 | 725.1 | 725.1 | 725.1 | 725.1 | 725.1 | 6075 | 6075 | 352788.9 | 996557.4 | 3129.2 | 3129.2 | 1443.9 | 1443.9 | 1443.9 | 1443.9 | 0 | 0 | 1373530.3 | 2021-04-02 | 147013 | BL-A | BL-A 35144944_PSPS - SNEATH LANE 1107 - LR 48338 - MAR 2021 | 2020-08-11 | 2020-05-29 | Completed | 2020-10-06 | 2022-04-15 | Not Started | 2022-03-03 | Not Started | 2022-04-28 | Not Started | 2022-05-17 | 2022-05-17 | Not Started | 2022-05-18 | 2022-06-07 | Not Started | 2022-02-18 | 2022-02-24 | Not Started | 2022-06-15 | Not Started |  |  |  |  | 2022-06-15 | Not Started | 2022-07-01 | Not Started | 2022-07-22 | Not Started | 2021-03-24 | 2022-08-19 | -513 | Behind Schedule | Not Started | 2022-08-22 | 2022-09-02 | Not Started | 2022-10-11 | Not Started
35145001 | PSPS - CLAYTON 2215 - CB | E.5025639.01 | 5788778 | PEND | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | Not in the WP | 2021 | SH | CONCORD | Diablo Assets | 9720 | 375 | 10095 | 1.9119 | 0 | 1.9119 | [5 empty] | 2843343.46 | 2343343.46 | 500000 | 200763.7 | 0 | 299236.3 | On/Under Budget | 7925104.1 | 5726.3 | -566.3 | 6292.6 | 0 | 5411.3 | 170533.4 | 24252.7 | Project is not in the WP or in 2020 WP | 0 | 47378.2 | -47378.2 | 47378.2 | -47378.2 | 4275.3 | 3050.3 | 17493.4 | 5726.3 | 1201.2 | 1204.3 | 1225.5 | 1228.6 | 725.4 | 725.4 | 725.4 | 9797.1 | 278231.1 | 125379.8 | 1224208.5 | 2346023.2 | 1206421 | 1210695.5 | 1212694.5 | 48408.2 | 46171.3 | 46171.3 | 46171.3 | 46171.3 | 7836747 | 2021-04-02 | 147014 | BL-A | BL-A 35145001_CWSP - CLAYTON 2215 - CB - SEPT 2021 | 2020-08-11 | 2020-10-14 | Completed | 2022-06-17 | 2022-06-30 | Not Started | 2021-04-02 | Not Started | 2022-07-14 | Not Started | 2022-07-22 | 2022-08-04 | Not Started | 2022-08-05 | 2022-08-11 | Not Started | 2022-07-15 | 2022-07-21 | Not Started |  |  | 2022-08-12 | Not Started | 2022-12-05 | Not Started | 2022-08-12 | Not Started | 2023-02-07 | Not Started | 2023-03-06 | Not Started | 2021-09-07 | 2023-04-03 | -573 | Behind Schedule | Not Started | 2023-04-04 | 2023-04-17 | Not Started | 2023-05-24 | Not Started
35145002 | PSPS - IGNACIO 1101 - CB | E.5025640.01 | 5788780 | PEND | 08W | D2PK | Donna Pontrello | A8G1 | Alvin Galesic |  |  | Not in the WP | 2021 | SH | SNRAFAEL | North Bay Assets | 6847 | 0 | 6847 | 1.2968 | 0 | 1.2968 | [5 empty] | 2311410.91 | 1811410.91 | 500000 | 122952.7 | 0 | 377047.3 | On/Under Budget | 4021.9 | 1067 | 0 | 1067 | 0 | 4235 | 115218 | 3499.7 | Project is not in the WP or in 2020 WP | 0 | 8588.6 | -8588.6 | 8588.6 | -8588.6 | 1188.6 | 929.1 | 1382 | 1067 | 1069.9 | 1072.9 | 1095.4 | 783.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 147038 | BL-A | BL-A 35145002_CWSP - IGNACIO 1101 - CB_08W - JUNE 2021 | 2020-08-12 | 2020-11-02 | Completed | 2021-04-02 | 2021-04-15 | Not Started | 2021-04-29 | Not Started | 2021-04-30 | Not Started | 2021-04-02 | 2021-04-29 | Not Started | 2021-04-30 | 2021-05-20 | Not Started | 2021-04-23 | 2021-04-23 | Not Started | [6 empty] | 2021-09-20 | Not Started | 2021-11-12 | Not Started | 2021-11-12 | Not Started | 2021-07-28 | 2022-01-13 | -169 | Behind Schedule | Not Started | 2022-01-14 | 2022-01-27 | Not Started | 2022-03-07 | Not Started
35219275 | CWSP - PUTAH CREEK 110246012 | E.5034706.01.01 | 5543347 | PEND | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | WOODLAND | Sacramento Assets | 0 | 2746 | 2746 | 0.52008 | 0 | 0.52008 |  |  |  |  | GC | 656614.03 | 656614.03 | 0 | 17400.3 | 0 | -17400.3 | OverRun | 1216606.4 | 15263.4 | 104.5 | 15158.9 | 0 | 0 | 0 | 17504.7 | Budget Allocated | 950000 | 1249269.9 | -299269.9 | 1249269.9 | -299269.9 | 2530.2 | 3445.2 | 11424.8 | 15263.4 | 980343.9 | 208118.2 | 4690.7 | 4690.7 | 4690.7 | 4690.7 | 4690.7 | 4690.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 155695 | BL-A | BL-A 35219275_CWSP - PUTAH CREEK 110246012_08W - DD 210205 Feb. 2021 | 2021-02-05 | 2021-03-05 | Completed | 2021-04-27 | 2021-05-03 | Not Started | 2021-04-26 | Not Started | 2021-05-24 | Not Started | 2021-04-30 | 2021-04-30 | Not Started | 2021-05-03 | 2021-05-21 | Not Started | 2021-05-03 | 2021-05-14 | Not Started | 2021-06-16 | Not Started | 2021-06-16 | Not Started | 2021-06-29 | Not Started | 2021-06-16 | Not Started | 2021-07-13 | Not Started | 2021-08-11 | Not Started | 2021-12-09 | 2021-09-10 | 90 | On/ Ahead Schedule | Not Started | 2021-08-26 | 2021-09-08 | Not Started | 2021-11-09 | Not Started
35219266 | CWSP - MARIPOSA 2102CB PH 1 | E.5034702.01.01 | 5794552 | PEND | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | MARIPOSA | Yosemite Assets | 0 | 13713 | 13713 | 2.5972 | 0 | 2.5972 | 15653 | 0 | 2.9646 | 0 | GC | 1304482.44 | 354482.44 | 950000 | 154538.4 | 0 | 795461.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 3082.1 | 151456.4 | Request 2021 Budget | 0 | 151456.4 | -151456.4 | 151456.4 | -151456.4 | 5965 | 68523.5 | 76967.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156028 | BL-A | BL-A 35219266_CWSP - MARIPOSA 2102CB PH 1_08W - DD 210205 Feb. 2021 | 2021-02-17 | 2021-04-01 | Completed | 2021-05-17 | 2021-05-21 | Not Started | 2021-05-14 | Not Started | 2021-06-11 | Not Started | 2021-04-15 | 2021-04-15 | Not Started | 2021-04-16 | 2021-05-06 | Not Started | 2021-05-17 | 2021-05-28 | Not Started | 2021-07-06 | Not Started | 2021-07-06 | Not Started | 2021-07-06 | Not Started | 2021-07-06 | Not Started | 2021-10-18 | Not Started | 2021-11-16 | Not Started | 2021-11-23 | 2021-12-28 | -35 | Behind Schedule | Not Started | 2021-12-29 | 2022-01-11 | Not Started | 2022-02-24 | Not Started
35219291 | CWSP - VACA DIXON 1101126774 |  | 5543350 | PEND | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2022 |  | SH | VACAVLLE | Sacramento Assets | 0 | 2112 | 2112 | 0.4 | 0 | 0.4 |  |  |  |  | GC | 165125.99 | -784874.01 | 950000 | 19154.1 | 0 | 930845.9 | On/Under Budget | 902574.5 | 8443.9 | 69.6 | 8374.3 | 0 | 0 | 0 | 19223.7 | Budget Allocated | 1265910 | 930172.5 | 335737.5 | 930172.5 | 335737.5 | 6285.1 | 5478.4 | 7390.6 | 8443.9 | 725904 | 150721.4 | 4805.4 | 4805.4 | 4805.4 | 4805.4 | 4324.8 | 2402.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156236 | BL-A | BL-A 35219291_VACA DIXON 1101 - LR 126774_08W - DD 210219 Feb. 2021 | 2021-02-24 | 2021-03-10 | Completed | 2021-04-27 | 2021-05-03 | Not Started | 2021-04-26 | Not Started | 2021-05-24 | Not Started | 2021-05-14 | 2021-05-14 | Not Started | 2021-05-31 | 2021-06-18 | Not Started | 2021-05-04 | 2021-05-17 | Not Started | 2021-06-22 | Not Started | 2021-06-22 | Not Started | 2021-06-22 | Not Started | 2021-06-22 | Not Started | 2021-07-13 | Not Started | 2021-07-15 | Not Started | 2021-08-31 | 2021-09-14 | -14 | Behind Schedule | Not Started | 2021-09-15 | 2021-09-28 | Not Started | 2021-11-11 | Not Started
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | E.5034359.01 | 5541309 | PEND | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 |  | SH | NAPA | North Bay Assets | 0 | 7075.2 | 7075.2 | 1.34 | 0 | 1.34 | 7542 | 0 | 1.4284 | 0 | Contract | 415256.78 | -198743.22 | 614000 | 57156 | 0 | 556844 | On/Under Budget | 3417.3 | 1139.1 | 0 | 1139.1 | 0 | 0 | 4189.8 | 52966.1 | Request 2021 Budget | 0 | 57522.5 | -57522.5 | 57522.5 | -57522.5 | 4944 | 17876.4 | 30145.7 | 1139.1 | 1139.1 | 1139.1 | 1139.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-03-31 | Completed | 2021-04-30 | 2021-05-06 | Not Started | 2021-04-29 | Not Started | 2021-05-27 | Not Started | 2021-04-02 | 2021-05-06 | Not Started | 2021-05-07 | 2021-05-20 | Not Started | 2021-06-07 | 2021-06-18 | Not Started | 2021-08-16 | Not Started | 2021-08-16 | Not Started | 2021-08-27 | Not Started | 2021-08-16 | Not Started | 2021-09-15 | Not Started | 2021-10-14 | Not Started | 2021-12-15 | 2021-12-15 | 0 | On/ Ahead Schedule | Not Started | 2021-12-16 | 2021-12-29 | Not Started | 2022-02-11 | Not Started
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | E.5034606.01.01 | 5794209 | PEND | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | MARIPOSA | Yosemite Assets | 0 | 4752 | 4752 | 0.9 | 0 | 0.9 |  |  |  |  | GC | 1 | -804540 | 804541 | 86528.3 | 0 | 718012.7 | On/Under Budget | 0 | 0 | 182.1 | -182.1 | 0 | 0 | 3082.1 | 83628.3 | Request 2021 Budget | 0 | 83446.2 | -83446.2 | 83446.2 | -83446.2 | 4024.1 | 47689.7 | 31732.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156027 | BL-A | BL-A 35217267_SH - MARIPOSA 2102 LR 241564_08W - DD 210205 Feb. 2021 | 2021-02-17 | 2021-03-29 | Completed | 2021-04-30 | 2021-05-06 | Not Started | 2021-04-29 | Not Started | 2021-05-27 | Not Started | 2021-04-05 | 2021-04-05 | Not Started | 2021-04-06 | 2021-04-26 | Not Started | 2021-04-30 | 2021-05-13 | Not Started | 2021-06-21 | Not Started | 2021-06-21 | Not Started | 2021-06-21 | Not Started | 2021-06-21 | Not Started | 2021-07-23 | Not Started | 2021-08-23 | Not Started | 2021-12-08 | 2021-10-04 | 65 | On/ Ahead Schedule | Not Started | 2021-10-05 | 2021-10-18 | Not Started | 2021-12-01 | Not Started
35223037 | PSPS - OAKHURST 1101 - OAKHURST | E.5034765.01.01 | 5794989 | PEND | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | OAKHURST | Yosemite Assets | 105.6 | 0 | 105.6 | 0.02 | 0 | 0.02 |  |  |  |  | GC | 124376.18 | -375623.82 | 500000 | 19792.4 | 0 | 480207.6 | On/Under Budget | 265207 | 8702.3 | 0 | 8702.3 | 0 | 0 | 0 | 19792.5 | Request 2021 Budget | 0 | 293701.7 | -293701.7 | 293701.7 | -293701.7 | 1097.8 | 4832.5 | 13862.2 | 8702.3 | 15116.6 | 20376.9 | 194641.9 | 17428.5 | 6200.9 | 5813.3 | 2814.4 | 2814.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219268 | CWSP - MARIPOSA 210197142 PH 1 | E.5034703.01.01 | 5794541 | PEND | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | MARIPOSA | Yosemite Assets | 0 | 8553.6 | 8553.6 | 1.62 | 0 | 1.62 | 10425 | 0 | 1.9744 | 0 | GC | 1289702.13 | 339702.13 | 950000 | 148687.2 | 0 | 801312.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148687.1 | Request 2021 Budget | 0 | 148687.1 | -148687.1 | 148687.1 | -148687.1 | 2024.8 | 104546.8 | 42115.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156030 | BL-A | BL-A 35219268_CWSP - MARIPOSA 210197142 PH 1_08W - DD 210205 Feb. 2021 | 2021-02-17 | 2021-03-25 | Completed | 2021-07-29 | 2021-08-04 | Not Started | 2021-07-28 | Not Started | 2021-08-25 | Not Started | 2021-04-05 | 2021-04-05 | Not Started | 2021-04-06 | 2021-04-26 | Not Started | 2021-04-30 | 2021-05-13 | Not Started | 2021-09-17 | Not Started | 2021-09-17 | Not Started | 2021-09-17 | Not Started | 2021-09-17 | Not Started | 2021-11-11 | Not Started | 2021-12-10 | Not Started | 2021-12-21 | 2022-01-21 | -31 | Behind Schedule | Not Started | 2022-01-24 | 2022-02-04 | Not Started | 2022-03-22 | Not Started
35226240 | CWSP - MARIPOSA 210197142 PH 3 | E.5034703.01.03 | 5794541 | PEND | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | MARIPOSA | Yosemite Assets | 0 | 7814.4 | 7814.4 | 1.48 | 0 | 1.48 |  |  |  |  | GC | 655862.69 | 655862.69 | 0 | 61937.8 | 0 | -61937.8 | OverRun | 0 | 0 | 330.8 | -330.8 | 0 | 0 | 0 | 62268.7 | Request 2021 Budget | 0 | 61937.9 | -61937.9 | 61937.9 | -61937.9 | 0 | 54864.6 | 7073.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156032 | BL-A | BL-A 35226240_CWSP - MARIPOSA 210197142 PH 3_08W - DD 210205 Feb.2021 | 2021-02-17 | 2021-02-27 | Completed | 2021-04-14 | 2021-04-20 | Not Started | 2021-04-13 | Not Started | 2021-05-11 | Not Started | 2021-04-05 | 2021-04-05 | Not Started | 2021-04-06 | 2021-04-26 | Not Started | 2021-04-26 | 2021-05-07 | Not Started | 2021-06-03 | Not Started | 2021-06-03 | Not Started | 2021-06-03 | Not Started | 2021-06-03 | Not Started | 2021-07-28 | Not Started | 2021-08-26 | Not Started | 2021-09-28 | 2021-09-23 | 5 | On/ Ahead Schedule | Not Started | 2021-09-24 | 2021-10-07 | Not Started | 2021-10-14 | Not Started
35226241 | CWSP - MARIPOSA 210197142 PH 2 | E.5034703.01.02 | 5794541 | PEND | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | MARIPOSA | Yosemite Assets | 0 | 7920 | 7920 | 1.5 | 0 | 1.5 | 6651 | 0 | 1.2597 | 0 | GC | 485124.83 | 485124.83 | 0 | 61616.8 | 0 | -61616.8 | OverRun | 0 | 0 | 174.1 | -174.1 | 0 | 0 | 0 | 61790.9 | Request 2021 Budget | 0 | 61616.8 | -61616.8 | 61616.8 | -61616.8 | 0 | 44761.9 | 16854.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156031 | BL-A | BL-A 35226241_CWSP - MARIPOSA 210197142 PH 2_08W - DD 210205 Feb. 2021 | 2021-02-17 | 2021-03-26 | Completed | 2021-07-30 | 2021-08-05 | Not Started | 2021-07-29 | Not Started | 2021-08-26 | Not Started | 2021-04-05 | 2021-04-05 | Not Started | 2021-04-06 | 2021-04-26 | Not Started | 2021-04-26 | 2021-05-07 | Not Started | 2021-09-20 | Not Started | 2021-09-20 | Not Started | 2021-09-20 | Not Started | 2021-09-20 | Not Started | 2021-11-12 | Not Started | 2021-12-13 | Not Started | 2021-12-22 | 2022-01-11 | -20 | Behind Schedule | Not Started | 2022-01-12 | 2022-01-25 | Not Started | 2022-03-10 | Not Started
74022723 | CWSP - CAMP FIRE PDSE 1106 PONDEROSA WAY |  | 5783287 | PEND | 08W | JXF8 | Joseph Fong |  |  |  |  | Not in the WP |  |  | CHICO | [26 empty] | 971.3 | Project is not in the WP or in 2020 WP | 0 | 971.3 | -971.3 | 0 | 0
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | E.5034791.01 | 5544143 | PEND | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2021 |  | SH | CONCORD | Diablo Assets | 0 | 5544 | 5544 | 1.05 | 0 | 1.05 |  |  |  |  | GC | 535717.12 | 135717.12 | 400000 | 109041.6 | 0 | 290958.4 | On/Under Budget | 599.5 | 8750.6 | 139.3 | 8611.3 | 0 | 0 | 0 | 109180.9 | Request 2021 Budget | 0 | 118747.7 | -118747.7 | 118391.7 | -118391.7 | 0 | 27894.8 | 81146.8 | 8750.6 | 599.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157129 | BL-A | BL-A ECOP - CLAYTON 2212 - H01-LR2951 PH2 - Mar. 2021 | 2021-03-07 | 2021-04-14 | Not Started | 2021-06-22 | 2021-06-28 | Not Started | 2021-06-21 | Not Started | 2021-07-19 | Not Started | 2021-04-15 | 2021-04-15 | Not Started | 2021-04-16 | 2021-05-06 | Not Started | 2021-06-11 | 2021-07-01 | Not Started | 2021-08-11 | Not Started |  |  |  |  | 2021-08-11 | Not Started | 2021-10-05 | Not Started | 2021-10-12 | Not Started | 2022-02-21 | 2021-12-13 | 70 | On/ Ahead Schedule | Not Started | 2021-12-14 | 2021-12-27 | Not Started | 2022-03-07 | Not Started
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | E.5034804.01.14 | 5795299 | PEND | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | PLCRVLLE | Sierra Assets | 0 | 3235 | 3235 | 0.61269 | 0 | 0.61269 | 3235 | 0 | 0.61269 | 0 | GC | 465706.54 | 465706.54 | 0 | 34669.8 | 0 | -34669.8 | OverRun | 0 | 0 | -19986.2 | 19986.2 | 0 | 0 | 0 | 14683.7 | Request 2021 Budget | 0 | 695793.9 | -695793.9 | 34669.9 | -34669.9 | 0 | 1637 | 33032.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156280 | BL-A | BL-A 35232280_CWSP - SHINGLE SPRINGS 2109-LR 9372PH2.6_08W - DD 210219 Feb. 2021 | 2021-02-25 | 2021-03-17 | Completed | 2021-04-21 | 2021-04-27 | Not Started | 2021-04-20 | Not Started | 2021-05-18 | Not Started | 2021-04-05 | 2021-04-05 | Not Started | 2021-04-06 | 2021-04-26 | Not Started | 2021-05-12 | 2021-06-08 | Not Started | 2021-06-10 | Not Started | 2021-06-10 | Not Started | 2021-06-10 | Not Started | 2021-06-10 | Not Started | 2021-07-07 | Not Started | 2021-07-15 | Not Started | 2021-09-22 | 2021-09-14 | 8 | On/ Ahead Schedule | Not Started | 2021-09-15 | 2021-09-28 | Not Started | 2021-11-11 | Not Started
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | E.5034695.01.04 | 5794546 | PEND | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | OAKHURST | Yosemite Assets | 0 | 6152 | 6152 | 1.1652 | 0 | 1.1652 | 9162 | 0 | 1.7352 | 0 | Contract | 886518.78 | 736518.78 | 150000 | 71327.2 | 0 | 78672.8 | On/Under Budget | 1826516.6 | 40878.9 | 262.2 | 40616.7 | 0 | 0 | 0 | 71589.4 | Request 2021 Budget | 0 | 1940502.7 | -1940502.7 | 1938722.7 | -1938722.7 | 0 | 13136.8 | 58190.4 | 40878.9 | 48953.9 | 518090.6 | 569033.4 | 505307.1 | 162246.7 | 15848.9 | 4690.7 | 2345.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-06-04 | Not Started | 2021-07-12 | 2021-07-16 | Not Started | 2021-07-09 | Not Started | 2021-08-06 | Not Started | 2021-06-07 | 2021-06-07 | Not Started | 2021-06-08 | 2021-06-28 | Not Started | 2021-07-12 | 2021-07-23 | Not Started | 2021-08-31 | Not Started | 2021-08-31 | Not Started | 2021-09-13 | Not Started | 2021-08-31 | Not Started | 2021-12-13 | Not Started | 2022-01-11 | Not Started | 2022-03-14 | 2022-03-14 | 0 | On/ Ahead Schedule | Not Started | 2022-03-15 | 2022-03-28 | Not Started | 2022-05-11 | Not Started
35227263 | CWSP - MARIPOSA 2102CB PH 2 | E.5034702.01.05 | 5794552 | PEND | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2021 |  | SH | MARIPOSA | Yosemite Assets | 0 | 1315.42 | 1315.42 | 0.24913 | 0 | 0.24913 |  |  |  |  | GC | 1012126.18 | 1012126.18 | 0 | 79059.7 | 0 | -79059.7 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79059.7 | Request 2021 Budget | 0 | 79059.7 | -79059.7 | 79059.7 | -79059.7 | 0 | 29628 | 49431.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156029 | BL-A | BL-A 35227263_CWSP - MARIPOSA 2102CB PH 2_08W - DD 210205 Feb. 2021 | 2021-02-17 | 2021-03-29 | Completed | 2021-05-17 | 2021-05-21 | Not Started | 2021-05-14 | Not Started | 2021-06-11 | Not Started | 2021-04-05 | 2021-04-05 | Not Started | 2021-04-06 | 2021-04-26 | Not Started | 2021-05-10 | 2021-05-21 | Not Started | 2021-07-06 | Not Started | 2021-07-06 | Not Started | 2021-07-06 | Not Started | 2021-07-06 | Not Started | 2021-10-04 | Not Started | 2021-11-02 | Not Started | 2021-12-22 | 2021-12-02 | 20 | On/ Ahead Schedule | Not Started | 2021-12-03 | 2021-12-16 | Not Started | 2022-01-31 | Not Started
31126827 | OCGC EP RECONDUCTOR WILLIAMS 1102- Y2016 | P.10692 | 5513271 | PREC | 08W | J91F | Justin M Stabe | AXYX | Aaron Yuen |  |  | Not in the WP |  |  | MRYSVLLE | Sacramento Assets | [11 empty] | 285956 | -35997 | 321953 | 274437.2 | 0 | 47515.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31082393 | RECON THREE SPANS CHERRY RIDGE RD |  | 5530175 | PREC | 08W | S2WT | Steve Whitman |  |  |  |  | Not in the WP |  | SH | STROSA |  | 0 | 1345 | 1345 | 0.25473 | 0.25473 | 0 | [19 empty] | 128.4 | Project is not in the WP or in 2020 WP | 0 | 128.4 | -128.4 | 0 | 0
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | 5530176 | PROD | 08W | SZC1 | Scott Chen |  |  |  |  | Not in the WP |  |  | ANGLSCMP |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | -56051.3 | Project is not in the WP or in 2020 WP | 0 | -56051.3 | 56051.3 | 0 | 0
35141837 | *CANC*BR-04-01-W (E) SUNSET DR PARB |  | 5786123 | PROD | 08W | AVP4 | Aaron Patane |  |  |  |  | Not in the WP |  |  | CHICO | [26 empty] | -258244.9 | Project is not in the WP or in 2020 WP | 0 | -258244.9 | 258244.9 | 0 | 0
35142198 | BR-03-08-W (E) BELLEVIEW PARB |  | 5786123 | UNSC | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2021 |  |  | CHICO | North Valley Assets | [10 empty] | Contract | 848291.05 | 0.05 | 848291 | 743391.9 | 0 | 104899.1 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 948.3 | 715640.1 | 26803.5 | Request 2021 Budget | 0 | 26803.5 | -26803.5 | 26803.5 | -26803.5 | 1276.1 | 0 | 25527.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35129944 | SILVERADO 2105 - DIST.UNDERBUILD RECON |  | 5787047 | UNSC | 08W | MDWR | Matt D White |  |  |  |  | Not in the WP |  |  | NAPA | [26 empty] | 1224.2 | Project is not in the WP or in 2020 WP | 0 | 1224.2 | -1224.2 | 0 | 0
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | E.5014721.05 | 5786762 | UNSC | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2020 | SH | CHICO | North Valley Assets | 0 | 9325 | 9325 | 1.7661 | 0 | 1.7661 | [5 empty] | 3319922 | 771603.4 | 2548318.6 | 332244.2 | 264599.9 | 2480674.3 | On/Under Budget | 402.6 | 113.3 | -168362.4 | 168475.7 | 0 | 235.3 | 325841 | -162194.4 | Project is not in the WP or in 2020 WP | 0 | 6684 | -6684 | 6684 | -6684 | 1991.9 | 2274.5 | 1901.6 | 113.3 | 113.3 | 113.3 | 117.4 | 58.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 147117 | BL-0 | BL-0 35129307_CWSP - ORO FINO 1102 - LR2560 PH 1.5_08W - JULY 2021 | 2020-08-13 | 2020-07-13 | Completed | 2020-07-28 | 2020-07-28 | Completed | 2020-08-11 | Completed | 2020-08-07 | Completed | 2020-07-27 | 2020-07-27 | Completed | 2022-04-08 | 2022-04-21 | Not Started | 2020-08-17 | 2020-11-06 | Completed | 2022-04-22 | Not Started |  |  |  |  | 2022-04-22 | Not Started | 2022-04-21 | Not Started | 2022-04-27 | Not Started | 2021-07-07 | 2022-05-27 | -324 | Behind Schedule | Not Started | 2022-05-30 | 2022-06-10 | Not Started | 2022-07-19 | Not Started
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | E.5014721.03 | 5786760 | UNSC | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2020 | SH | CHICO | North Valley Assets | 0 | 4373 | 4373 | 0.82822 | 0 | 0.82822 | [5 empty] | 1594611 | 394996.3 | 1199614.7 | 185590.6 | 0 | 1014024.1 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 235.3 | 94018 | 91337.3 | Project is not in the WP or in 2020 WP | 0 | 91337.3 | -91337.3 | 91337.3 | -91337.3 | 586.5 | 89684.1 | 1066.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 147116 | BL-0 | BL-0 35129305_CWSP - ORO FINO 1102 - LR2560 PH 1.3_08W - JULY 2021 | 2020-08-13 | 2020-07-01 | Completed | 2020-07-28 | 2020-07-28 | Completed | 2020-07-07 | Completed | 2020-08-07 | Completed | 2020-07-29 | 2020-07-29 | Completed | 2022-04-08 | 2022-04-21 | Not Started | 2020-08-10 | 2020-10-05 | Completed | 2022-05-23 | Not Started |  |  |  |  | 2022-05-23 | Not Started | 2022-05-23 | Not Started | 2022-06-03 | Not Started | 2021-07-05 | 2022-07-05 | -365 | Behind Schedule | Not Started | 2022-07-06 | 2022-07-19 | Not Started | 2022-08-25 | Not Started
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | E.5015235.07 | 5786027 | UNSC | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 6883 | 6883 | 1.3036 | 0 | 1.3036 | [5 empty] | 1190982.71 | -1022674.29 | 2213657 | 219980.7 | 0 | 1993676.3 | On/Under Budget | 963819.6 | 785.5 | 0 | 785.5 | 0 | 1326.6 | 217207.8 | 1446.3 | Project is not in the WP or in 2020 WP | 0 | 8689.2 | -8689.2 | 8689.2 | -8689.2 | -22279.8 | 6069.8 | 17656.3 | 785.5 | 785.5 | 785.5 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 814.4 | 8652.7 | 9106.5 | 372508.4 | 745761.2 | 7709.6 | 3854.8 | 0 | -190231 | 0 | 0 | 0 | 0 | 957362.2 | 2021-04-02 | 154965 | BL-0 | BL-0 35115858_CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1.7_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-07-03 | Completed | 2020-08-27 | 2020-09-14 | Completed | 2020-07-30 | Completed | 2021-12-10 | Not Started | 2021-12-13 | 2021-12-13 | Not Started | 2021-12-14 | 2022-01-03 | Not Started | 2022-02-07 | 2022-02-25 | Not Started | 2022-05-03 | Not Started |  |  |  |  | 2022-05-03 | Not Started | 2022-06-13 | Not Started | 2022-05-31 | Not Started | 2022-07-29 | 2022-07-29 | 0 | On/ Ahead Schedule | Not Started | 2022-08-01 | 2022-08-12 | Not Started | 2022-09-20 | Not Started
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | E.5015235.05 | 5786025 | UNSC | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 10943 | 10943 | 2.0725 | 0 | 2.0725 | [5 empty] | 2167732.82 | -1323323.18 | 3491056 | 317513.1 | 0 | 3173542.9 | On/Under Budget | 1756719 | 599.7 | 0 | 599.7 | 0 | 346.1 | 304656.3 | 12510.8 | Project is not in the WP or in 2020 WP | 0 | 18040.1 | -18040.1 | 18040.1 | -18040.1 | 3696.6 | 6996.5 | 1817.7 | 599.7 | 599.7 | 599.7 | 621.7 | 621.7 | 621.7 | 621.7 | 621.7 | 621.7 | 2804.2 | 2817.2 | 2830.2 | 3563.1 | 767366.5 | 764250.6 | 684532 | 3953.7 | 0 | 0 | -480328 | 0 | 1751789.5 | 2021-04-02 | 154963 | BL-0 | BL-0 35115856_CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1.5_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-07-07 | Completed | 2020-09-01 | 2020-09-29 | Completed | 2020-10-27 | Completed | 2020-09-29 | Completed | 2021-12-13 | 2021-12-13 | Not Started | 2021-12-14 | 2022-01-10 | Not Started | 2022-02-07 | 2022-02-18 | Not Started | 2022-04-26 | Not Started |  |  |  |  | 2022-04-26 | Not Started | 2022-06-22 | Not Started | 2022-07-06 | Not Started | 2022-10-06 | 2022-10-06 | 0 | On/ Ahead Schedule | Not Started | 2022-10-07 | 2022-10-20 | Not Started | 2022-11-28 | Not Started
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | E.5014722.05 | 5785932 | UNSC | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 9687 | 9687 | 1.8347 | 0 | 1.8347 | [5 empty] | 300000 | 0 | 300000 | 207205.3 | 0 | 92794.7 | On/Under Budget | 4341125.5 | 128.9 | 0 | 128.9 | 0 | 0 | 196524.8 | 10680.6 | Project is not in the WP or in 2020 WP | 0 | 11868.9 | -11868.9 | 11868.9 | -11868.9 | 2951.6 | 6616.2 | 1112.8 | 128.9 | 128.9 | 128.9 | 133.6 | 133.6 | 133.6 | 133.6 | 133.6 | 133.6 | 932240.4 | 938841.4 | 1172354.5 | 1179435.1 | 25702 | 25702 | 26316.1 | 26316.1 | 13158 | 0 | 0 | 0 | 4340065.6 | 2021-04-02 | 145792 | BL-A: | BL-A: 35116399_CWSP - MIWUK 1702 - LR 8090 - PH 1.5_08W - Jan 2021 | 2020-07-24 | 2020-08-21 | Completed | 2022-02-10 | 2022-02-23 | Not Started | 2020-09-01 | Completed | 2022-02-23 | Not Started | 2022-02-24 | 2022-02-24 | Not Started | 2022-02-25 | 2022-02-28 | Not Started | 2020-11-03 | 2020-11-19 | Completed | 2022-06-10 | Not Started |  |  |  |  | 2022-06-10 | Not Started | 2022-08-16 | Not Started | 2022-09-14 | Not Started | 2021-01-06 | 2022-10-26 | -658 | Behind Schedule | Not Started | 2022-10-27 | 2022-11-09 | Not Started | 2023-03-22 | Not Started
35116511 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 | E.5015394.02 | 5786041 | UNSC | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 6348 | 6348 | 1.2023 | 0 | 1.2023 | [5 empty] | 1026224.53 | 901224.53 | 125000 | 88811.2 | 0 | 36188.8 | On/Under Budget | 1557717.8 | 63.6 | 0 | 63.6 | 0 | 3475.9 | 80387.4 | 4947.9 | Project is not in the WP or in 2020 WP | 0 | 5011.5 | -5011.5 | 5011.5 | -5011.5 | 510.9 | 3928.5 | 508.5 | 63.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140953 | 1134451.2 | 611128.7 | 0 | 0 | 0 | 0 | -328815 | 0 | 0 | 0 | 0 | 1557717.9 | 2021-04-02 | 154918 | BL-B | BL-B 35116511_CWSP - STANISLAUS 1702 - LR1888 - PH 2.2_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-08-04 | Completed | 2022-02-02 | 2022-03-15 | Not Started | 2022-02-11 | Not Started | 2022-03-15 | Not Started | 2022-03-18 | 2022-03-18 | Not Started | 2022-03-21 | 2022-04-08 | Not Started | 2022-02-09 | 2022-03-29 | Not Started | 2022-04-12 | Not Started |  |  |  |  | 2022-04-12 | Not Started | 2022-06-08 | Not Started | 2022-06-22 | Not Started | 2022-08-23 | 2022-08-23 | 0 | On/ Ahead Schedule | Not Started | 2022-08-24 | 2022-09-06 | Not Started | 2022-10-13 | Not Started
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | E.5015701.02 | 5786036 | UNSC | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 9222 | 9222 | 1.7466 | 0 | 1.7466 | [5 empty] | 4438411 | 1235376.3 | 3203034.7 | 208305.4 | 0 | 2994729.3 | On/Under Budget | 1934594.6 | 168.6 | 0 | 168.6 | 0 | 0 | 204605.6 | 3699.9 | Project is not in the WP or in 2020 WP | 0 | 5253.9 | -5253.9 | 2196933.5 | -2196933.5 | 1193.4 | 1146.9 | 1359.6 | 168.6 | 168.6 | 6765.1 | 565331.1 | 775591.7 | 797163.9 | 17555 | 17583.1 | 12906.5 | 12217.6 | 12217.6 | 12217.6 | 12217.6 | -307340.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -258470.3 | 2021-04-02 | 154923 | BL-0 | BL-0 35116515_CWSP - STANISLAUS 1702 - LR1888 - PH 1.2_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-05-29 | Completed | 2020-07-16 | 2020-07-27 | Completed | 2020-06-15 | Completed | 2022-01-14 | Not Started | 2022-02-03 | 2022-02-09 | Not Started | 2022-02-10 | 2022-02-23 | Not Started | 2020-08-17 | 2020-10-16 | Completed | 2022-03-03 | Not Started |  |  |  |  | 2022-03-03 | Not Started | 2022-05-04 | Not Started | 2022-05-04 | Not Started | 2022-07-07 | 2022-07-11 | -4 | Behind Schedule | Not Started | 2022-07-12 | 2022-07-25 | Not Started | 2022-08-31 | Not Started
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | E.5014723.02 | 5785935 | UNSC | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 12936 | 12936 | 2.45 | 0 | 2.45 | [5 empty] | 250000 | 0 | 250000 | 207677 | 0 | 42323 | On/Under Budget | 4872422.5 | 104.4 | 0 | 104.4 | 0 | 973 | 202781.6 | 3922.4 | Project is not in the WP or in 2020 WP | 0 | 6389.4 | -6389.4 | 6389.4 | -6389.4 | 1315.9 | 1417.9 | 1188.6 | 104.4 | 104.4 | 104.4 | 108.2 | 108.2 | 108.2 | 108.2 | 108.2 | 1612.8 | 321951 | 318851.4 | 1274924.6 | 651731.1 | 688146.7 | 893231.4 | 705484.1 | 3332.5 | 3332.5 | 3332.5 | 2870.9 | 2870.9 | 4870059.6 | 2021-04-02 | 145852 | BL-A: | BL-A: 35115046_CWSP - MIWUK 1701 - LR 10600 PH 1.2_08W - Sept. 2021 | 2020-07-24 | 2020-08-13 | Completed | 2020-11-04 | 2020-12-03 | Not Started | 2020-10-07 | Completed | 2021-12-22 | Not Started | 2022-01-31 | 2022-02-04 | Not Started | 2022-02-07 | 2022-03-04 | Not Started | 2021-12-23 | 2022-01-05 | Not Started | 2022-04-08 | Not Started |  |  |  |  | 2022-04-08 | Not Started | 2022-06-23 | Not Started | 2022-07-21 | Not Started | 2021-09-08 | 2022-08-22 | -348 | Behind Schedule | Not Started | 2022-08-23 | 2022-09-05 | Not Started | 2022-10-12 | Not Started
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | E.5015427.05 | 5785989 | UNSC | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 13653 | 13653 | 2.5858 | 0 | 2.5858 | [5 empty] | 4165227 | 870173 | 3295054 | 211946.7 | 0 | 3083107.3 | On/Under Budget | 2722252.7 | 124.5 | 0 | 124.5 | 0 | 0 | 204721.6 | 7225.1 | Project is not in the WP or in 2020 WP | 0 | 7411.9 | -7411.9 | 7411.9 | -7411.9 | 4568.5 | 1542.4 | 1114.2 | 124.5 | 62.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1543739 | 859728.6 | 317222.9 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2722190.5 | 2021-04-02 | 145859 | BL-A: | BL-A: 35115057_CWSP - MIWUK 1701 - OCB - PH2.5 - Mar..2021 | 2020-07-24 | 2020-07-24 | Completed | 2020-09-14 | 2020-09-22 | Completed | 2020-08-31 | Completed | 2022-01-03 | Not Started | 2022-01-04 | 2022-01-10 | Not Started | 2022-01-11 | 2022-01-13 | Not Started | 2020-10-01 | 2020-11-03 | Completed | 2022-01-18 | Not Started |  |  |  |  | 2022-01-18 | Not Started | 2022-03-15 | Not Started | 2022-03-31 | Not Started | 2021-03-23 | 2022-05-10 | -413 | Behind Schedule | Not Started | 2022-05-11 | 2022-05-12 | Not Started | 2022-05-16 | Not Started
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | E.5015236.07 | 5786029 | UNSC | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 8454 | 8454 | 1.6011 | 0 | 1.6011 | [5 empty] | 2621905.68 | -724952.32 | 3346858 | 174841 | 0 | 3172017 | On/Under Budget | 2047549.5 | 153.8 | 0 | 153.8 | 0 | 37.8 | 169373.2 | 5429.9 | Project is not in the WP or in 2020 WP | 0 | 6848.3 | -6848.3 | 6848.3 | -6848.3 | 3516.3 | 956.8 | 956.8 | 153.8 | 153.8 | 153.8 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 730223.3 | 882002.9 | 783287.6 | 22329.7 | 18618.7 | 14593.2 | -404770.5 | 0 | 0 | 0 | 0 | 0 | 2046284.9 | 2021-04-02 | 154971 | BL-0 | BL-0 35115852_CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.7_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-05-28 | Completed | 2020-09-10 | 2020-09-22 | Completed | 2020-10-19 | Completed | 2021-12-10 | Not Started | 2021-12-13 | 2021-12-13 | Not Started | 2021-12-14 | 2022-01-10 | Not Started | 2020-08-13 | 2020-10-16 | Completed | 2022-05-03 | Not Started |  |  |  |  | 2022-05-03 | Not Started | 2022-06-29 | Not Started | 2022-07-13 | Not Started | 2022-10-13 | 2022-10-13 | 0 | On/ Ahead Schedule | Not Started | 2022-10-14 | 2022-10-27 | Not Started | 2022-12-05 | Not Started
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | E.5015235.02 | 5786022 | UNSC | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 8473 | 8473 | 1.6047 | 0 | 1.6047 | [5 empty] | 1924559.32 | -1534628.18 | 3459187.5 | 302946.2 | 0 | 3156241.3 | On/Under Budget | 1905645.3 | 0 | 0 | 0 | 0 | 1583.2 | 289417.9 | 11945.1 | Project is not in the WP or in 2020 WP | 0 | 11945.1 | -11945.1 | 11945.1 | -11945.1 | 4089.7 | 6121.3 | 1734.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2870.9 | 2870.9 | 40950.7 | 755883.1 | 760142.8 | 730940 | 0 | 0 | 0 | -388013 | 0 | 1905645.4 | 2021-04-02 | 154961 | BL-B | BL-B 35115853_CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1.2_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-07-01 | Completed | 2020-07-24 | 2020-07-30 | Completed | 2020-07-29 | Completed | 2020-07-30 | Completed | 2021-12-13 | 2021-12-13 | Not Started | 2021-12-14 | 2022-01-03 | Not Started | 2020-08-03 | 2020-09-04 | Completed | 2022-02-02 | Not Started |  |  |  |  | 2022-02-02 | Not Started | 2022-03-31 | Not Started | 2022-04-14 | Not Started | 2022-05-05 | 2022-05-05 | 0 | On/ Ahead Schedule | Not Started | 2022-05-06 | 2022-05-19 | Not Started | 2022-05-26 | Not Started
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | E.5015236.05 | 5786021 | UNSC | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 6787 | 6787 | 1.2854 | 0 | 1.2854 | [5 empty] | 1424587.78 | -1278855.22 | 2703443 | 204719.6 | 0 | 2498723.4 | On/Under Budget | 1798293.5 | 146.1 | 0 | 146.1 | 0 | 0 | 196888.4 | 7831.2 | Project is not in the WP or in 2020 WP | 0 | 9178.5 | -9178.5 | 9178.5 | -9178.5 | 5470.3 | 1094.7 | 1266.2 | 146.1 | 146.1 | 146.1 | 151.5 | 151.5 | 151.5 | 151.5 | 151.5 | 151.5 | 157 | 157 | 157 | 157 | 531948.7 | 696812.9 | 876017.1 | 6314.8 | 573.1 | 0 | -315202 | 0 | 1797092.6 | 2021-04-02 | 154969 | BL-B | BL-B 35115850_CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2.5_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-08-24 | Completed | 2020-10-01 | 2020-10-01 | Not Started | 2020-06-16 | Completed | 2021-12-07 | Not Started | 2021-12-08 | 2021-12-08 | Not Started | 2021-12-09 | 2022-01-05 | Not Started | 2020-10-23 | 2020-11-17 | Completed | 2022-04-20 | Not Started |  |  |  |  | 2022-04-20 | Not Started | 2022-06-16 | Not Started | 2022-06-30 | Not Started | 2022-08-31 | 2022-08-31 | 0 | On/ Ahead Schedule | Not Started | 2022-09-01 | 2022-09-14 | Not Started | 2022-10-21 | Not Started
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | E.5015236.03 | 5786019 | UNSC | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 8697 | 8697 | 1.6472 | 0 | 1.6472 | [5 empty] | 1308258.35 | -1364352.65 | 2672611 | 295559.8 | 1175651 | 3552702.2 | On/Under Budget | 1222473.3 | 712.9 | 0 | 712.9 | 0 | 0 | 289364.1 | 6195.8 | Project is not in the WP or in 2020 WP | 0 | 12768.5 | -12768.5 | 12768.5 | -12768.5 | 3122.2 | 1536.8 | 1536.8 | 712.9 | 712.9 | 712.9 | 739 | 739 | 739 | 739 | 739 | 739 | 3645.7 | 3663.1 | 268760.5 | 659049.8 | 630885.6 | 10219.7 | 5189.8 | 0 | -364801 | 0 | 0 | 0 | 1216613.2 | 2021-04-02 | 154967 | BL-0 | BL-0 35115848_CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2.3_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-07-08 | Completed | 2020-08-31 | 2020-08-31 | Completed | 2020-10-29 | Completed | 2020-08-31 | Completed | 2021-12-08 | 2021-12-08 | Not Started | 2021-12-09 | 2022-01-05 | Not Started | 2020-09-25 | 2020-11-13 | Completed | 2022-05-04 | Not Started |  |  |  |  | 2022-05-04 | Not Started | 2022-06-30 | Not Started | 2022-07-22 | Not Started | 2022-09-22 | 2022-09-22 | 0 | On/ Ahead Schedule | Not Started | 2022-09-23 | 2022-10-06 | Not Started | 2022-11-14 | Not Started
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | E.5014745.07 | 5786135 | UNSC | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 7602 | 7602 | 1.4398 | 0 | 1.4398 | [5 empty] | 2273638.04 | -748307.96 | 3021946 | 389476.6 | 0 | 2632469.4 | On/Under Budget | 1844556.9 | 202.3 | 0 | 202.3 | 0 | 213.7 | 383960.5 | 5302.5 | Project is not in the WP or in 2020 WP | 0 | 7167.6 | -7167.6 | 7167.6 | -7167.6 | -1016.4 | 2873.5 | 3445.4 | 202.3 | 202.3 | 202.3 | 209.7 | 209.7 | 209.7 | 209.7 | 209.7 | 209.7 | 403260.9 | 748091 | 745955.7 | -59991.5 | 5578.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1842894.2 | 2021-04-02 | 154958 | BL-0 | BL-0 35114045_CWSP - PINE GROVE 1102 - LR1222 - PH 1.7_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-06-18 | Completed | 2020-08-17 | 2020-08-17 | Completed | 2020-06-01 | Completed | 2020-08-17 | Completed | 2021-12-08 | 2021-12-08 | Not Started | 2021-12-09 | 2022-01-05 | Not Started | 2020-08-20 | 2020-10-02 | Completed | 2022-02-24 | Not Started |  |  |  |  | 2022-02-24 | Not Started | 2022-04-28 | Not Started | 2022-05-12 | Not Started | 2022-06-13 | 2022-06-13 | 0 | On/ Ahead Schedule | Not Started | 2022-06-14 | 2022-06-27 | Not Started | 2022-08-03 | Not Started
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | E.5014742.07 | 5786136 | UNSC | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 4291 | 4291 | 0.81269 | 0 | 0.81269 | [5 empty] | 1801039.27 | -221572.73 | 2022612 | 130304.3 | 0 | 1892307.7 | On/Under Budget | 1135130.8 | 163.3 | -250 | 413.3 | 0 | 235.3 | 113919.2 | 15899.8 | Project is not in the WP or in 2020 WP | 0 | 17655.5 | -17655.5 | 17655.5 | -17655.5 | 6096.5 | 8828.2 | 1225.1 | 163.3 | 163.3 | 163.3 | 169.3 | 169.3 | 169.3 | 169.3 | 169.3 | 169.3 | 1107949.3 | 12614.9 | 9770 | 3453.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1133788.1 | 2021-04-02 | 154957 | BL-0 | BL-0 35114052_CWSP - PINE GROVE 1102 - LR1222 - PH 2.7_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-06-12 | Completed | 2020-08-20 | 2020-08-31 | Completed | 2020-07-30 | Completed | 2020-08-31 | Completed | 2021-12-08 | 2021-12-08 | Not Started | 2021-12-09 | 2022-01-05 | Not Started | 2020-08-13 | 2020-09-25 | Completed | 2022-02-24 | Not Started |  |  |  |  | 2022-02-24 | Not Started | 2022-04-01 | Not Started | 2022-04-15 | Not Started | 2022-06-16 | 2022-06-16 | 0 | On/ Ahead Schedule | Not Started | 2022-06-17 | 2022-06-30 | Not Started | 2022-08-08 | Not Started
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | E.5014742.05 | 5785999 | UNSC | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 7377.2 | 7377.2 | 1.3972 | 0 | 1.3972 | [5 empty] | 4089518 | 1107840.4 | 2981677.6 | 290701 | 0 | 2690976.6 | On/Under Budget | 2129946.8 | 0 | -250 | 250 | 0 | 235.3 | 256192.1 | 34023.6 | Project is not in the WP or in 2020 WP | 0 | 34273.6 | -34273.6 | 34273.6 | -34273.6 | 11679.4 | 16671.1 | 5923.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 785305.3 | 741987.9 | 630567.9 | 5741.7 | 5741.7 | 5741.7 | -45139.6 | 0 | 0 | 0 | 0 | 0 | 2129946.6 | 2021-04-02 | 154953 | BL-0 | BL-0 35114050_CWSP - PINE GROVE 1102 - LR1222 - PH 2.5_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-06-15 | Completed | 2020-07-20 | 2020-07-27 | Completed | 2020-06-01 | Completed | 2020-07-28 | Completed | 2021-11-26 | 2021-11-26 | Not Started | 2021-11-29 | 2021-12-17 | Not Started | 2020-08-13 | 2021-12-02 | In Progress | 2022-01-03 | Not Started |  |  |  |  | 2022-01-03 | Not Started | 2022-02-24 | Not Started | 2022-02-24 | Not Started | 2022-03-28 | 2022-03-28 | 0 | On/ Ahead Schedule | Not Started | 2022-03-04 | 2022-03-17 | Not Started | 2022-05-18 | Not Started
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | E.5014542.03 | 5786125 | UNSC | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | STCRUZ | Central Coast Assets | 0 | 12799 | 12799 | 2.4241 | 0 | 2.4241 | [5 empty] | 6920313 | 1931699.3 | 4988613.7 | 144607.2 | 362321.8 | 5206328.3 | On/Under Budget | 1251745.5 | 0 | 233.8 | -233.8 | 0 | 192.2 | 128049.6 | 16599.2 | Project is not in the WP or in 2020 WP | 0 | 16365.4 | -16365.4 | 16365.4 | -16365.4 | 782.3 | 747 | 14836.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1251745.5 | 0 | 0 | 0 | 1251745.5
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | E.5034572.01.14 | 5793918 | UNSC | 08W | JTHL | Joseph T Hembree | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2021 | FRRB | OROVILLE | North Valley Assets | 12150 | 0 | 12150 | 2.3011 | 0 | 2.3011 | 15567 | 0 | 2.9483 | 0 | GC | 11016312 | 2921408 | 8094904 | 587855.9 | 4937846.9 | 12444895 | On/Under Budget | 5107927.3 | 1238795.3 | 383 | 1238412.3 | 0 | 0 | 0 | 588238.9 | Budget Allocated | 8094904 | 7960600.6 | 134303.4 | 6934578.5 | 1160325.5 | 53850.1 | 514613.7 | 19392.1 | 1238795.3 | 1265102.5 | 992806.9 | 937090.6 | 969694.5 | 889498.8 | 21891.9 | 21653.4 | 10188.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157919 | BL-0 | BL-0 35225824_FRRB - Wyandotte 1103 HWY 162_08W - Mar.2021 | 2021-03-23 | 2021-01-24 | Completed | 2021-02-26 | 2021-03-05 | Completed | 2021-01-25 | Completed | 2021-03-23 | Completed | 2021-01-22 | 2021-01-22 | Completed | 2021-02-08 | 2021-04-16 | In Progress | 2020-12-14 | 2020-12-28 | Completed | 2021-04-05 | Not Started | 2021-04-05 | Not Started | 2021-07-06 | Not Started | 2021-06-02 | Not Started | 2021-07-28 | Not Started | 2021-08-19 | Not Started | 2021-10-21 | 2021-10-21 | 0 | On/ Ahead Schedule | Not Started | 2021-10-22 | 2021-11-04 | Not Started | 2021-12-20 | Not Started
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | E.5034572.01.09 | 5793918 | UNSC | 08W | JTHL | Joseph T Hembree | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2021 | FRRB | OROVILLE | North Valley Assets | 9065 | 0 | 9065 | 1.7169 | 0 | 1.7169 | 9763 | 0 | 1.8491 | 0 | GC | 10286697 | 3196882 | 7089815 | 3358848.4 | 3558823 | 7289789.6 | On/Under Budget | 1792392.2 | 1266156.2 | -1627989.1 | 2894145.3 | 0 | 0 | 0 | 1730859.4 | Budget Allocated | 6324922 | 6423605 | -98683 | 6417396.9 | -92474.9 | 8992.2 | 1194570.6 | 2155285.7 | 1266156.2 | 803204.6 | 133136.6 | 177225.7 | 519946.6 | 109309.1 | 17525.3 | 19023.5 | 13020.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156045 | BL-0 | BL-0 35223344_FRRB - Wyandotte 1103 ¿ Bald Rock Zone 2_08W - Feb. 2021 | 2021-02-17 | 2021-01-26 | Completed | 2021-02-03 | 2021-02-05 | Completed | 2021-01-22 | Completed | 2021-02-12 | Completed | 2020-11-25 | 2020-11-25 | Completed | 2021-01-04 | 2021-01-04 | Completed | 2020-11-10 | 2020-12-16 | Completed | 2021-02-12 | Completed | 2021-02-12 | Completed | 2021-04-15 | Not Started | 2021-03-29 | Completed | 2021-04-16 | Not Started | 2021-05-03 | Not Started | 2021-07-19 | 2021-06-29 | 20 | On/ Ahead Schedule | Not Started | 2021-06-30 | 2021-07-20 | Not Started | 2021-08-26 | Not Started
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | E.5034572.01.10 | 5793918 | UNSC | 08W | JTHL | Joseph T Hembree | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2021 | FRRB | OROVILLE | North Valley Assets | 14353 | 0 | 14353 | 2.7184 | 0 | 2.7184 | 19806 | 0 | 3.7511 | 0 | GC | 10700839 | 2922154 | 7778685 | 3029433.7 | 1122448.8 | 5871700.1 | On/Under Budget | 5582541.4 | 1442184.6 | -202960.8 | 1645145.4 | 0 | 0 | 0 | 2826472.9 | Budget Allocated | 9514299.24 | 7198245.8 | 2316053.44 | 10054159.7 | -539860.46 | 1650.6 | 1009315.2 | 2018467.9 | 1442184.6 | 895698.3 | 4879584.4 | -204350.3 | 11609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156546 | BL-0 | BL-0 35223345_FRRB - Wyandotte 1103 ¿ Bald Rock Zone 3_08W - Feb. 2021 | 2021-03-01 | 2021-02-16 | Completed | 2021-02-16 | 2021-02-19 | Completed | 2021-02-17 | Completed | 2021-03-01 | Completed | 2021-02-16 | 2021-04-15 | In Progress | 2021-04-16 | 2021-05-06 | Not Started | 2020-11-23 | 2020-12-04 | Completed | 2021-02-16 | Completed | 2021-02-16 | Completed | 2021-06-21 | Not Started | 2021-05-25 | Not Started | 2021-07-09 | Not Started | 2021-07-26 | Not Started | 2021-08-02 | 2021-08-02 | 0 | On/ Ahead Schedule | Not Started | 2021-08-03 | 2021-08-23 | Not Started | 2021-09-29 | Not Started
35145003 | PSPS CWSP - MORAGA 1103 - CB | E.5025641.01 | 5788781 | UNSC | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | Not in the WP | 2021 | SH | WALNTCRK | Diablo Assets | 1268 | 420 | 1688 | 0.3197 | 0 | 0.3197 | [5 empty] | 942892 | 442892 | 500000 | 100539.8 | 0 | 399460.2 | On/Under Budget | 1068754 | 1155.7 | 0 | 1155.7 | 0 | 5176.1 | 90599.8 | 4763.9 | Project is not in the WP or in 2020 WP | 0 | 15389.2 | -15389.2 | 15389.2 | -15389.2 | 1135.1 | 1811.2 | 1817.6 | 1155.7 | 1160 | 1164.2 | 1180.3 | 1184.5 | 1188.8 | 1193 | 1197.3 | 1201.5 | 310412.3 | 231278.1 | 232819.6 | 234222.8 | 12174 | 12208.2 | 9056.2 | 5704.3 | 5704.3 | 5704.3 | 0 | 0 | 1059284.1 | 2021-04-02 | 147015 | BL-A | BL-A 35145003_CWSP - MORAGA 1103 - CB - MAY 2021 | 2020-08-11 | 2020-06-03 | Completed |  |  | Not Started | 2020-11-16 | Completed | 2022-04-07 | Not Started |  |  |  | 2022-05-06 | 2022-05-12 | Not Started | 2022-04-01 | 2022-04-01 | Not Started | 2022-05-13 | Not Started |  |  |  |  | 2022-05-27 | Not Started | 2022-06-28 | Not Started | 2022-07-22 | Not Started | 2021-05-11 | 2022-08-19 | -465 | Behind Schedule | Not Started | 2022-08-22 | 2022-09-02 | Not Started | 2023-01-06 | Not Started
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | E.5025638.01 | 5788787 | UNSC | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 | 2021 | SH | STROSA | Sonoma Assets | 7819 | 1056 | 8875 | 1.6809 | 0 | 1.6809 | 7760 | 0 | 1.4697 | 0 | GC | 7914493 | 2012705.6 | 5901787.4 | 171281.4 | 2229106 | 7959612 | On/Under Budget | 1751219.6 | 1130460.6 | -2042.5 | 1132503.1 | 0 | 470.6 | 144612.4 | 24155.9 | Request 2021 Budget | 0 | 5018819.4 | -5018819.4 | 2907878.6 | -2907878.6 | 8171.8 | 8841.4 | 9185.2 | 1130460.6 | 1137133 | 587754.5 | 19296.1 | 3518 | 3518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2020-10-25 | Completed | 2021-02-12 | 2021-03-02 | Completed | 2021-02-18 | Completed | 2021-03-03 | Completed | 2021-02-19 | 2021-03-19 | Completed | 2021-02-19 | 2021-03-24 | Completed | 2021-02-22 | 2021-03-01 | Completed | 2021-04-26 | Not Started |  |  |  |  | 2021-05-13 | Not Started | 2021-07-02 | Not Started | 2021-08-02 | Not Started | 2021-10-01 | 2021-10-01 | 0 | On/ Ahead Schedule | Not Started | 2021-10-04 | 2021-10-15 | Not Started | 2021-11-23 | Not Started
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | 5539479 | UNSC | 08W | SGBA | Steve Barrow | CAGM | Claire Graves |  |  | Not in the WP |  | FRRB | OAKHURST | Yosemite Assets | 0 | 2500 | 2500 | 0.47348 | 0 | 0.47348 | [5 empty] | 1676000 | 103000 | 1573000 | 797989.8 | 886242 | 1661252.2 | On/Under Budget | 0 | 564097.8 | -365447 | 929544.8 | 0 | 0 | 183806.2 | 248736.7 | Project is not in the WP or in 2020 WP | 0 | 1207674.2 | -1207674.2 | 1178281.5 | -1178281.5 | 76343.5 | 63893 | 473947.2 | 564097.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35174085 | PSPS - FIA320 - LR @ 101269978 |  | 5530176 | UNSC | 08W | DHN4 | Dan Nguyen |  |  |  |  | 2020 |  | SH | ANGLSCMP |  | 0 | 528 | 528 | 0.1 | 0 | 0.1 |  |  |  |  | GC | [14 empty] | 3800.2 | Project is not in the WP or in 2020 WP | 0 | 3800.2 | -3800.2 | 0 | 0
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | E.5014730.01 | 5791727 | UNSC | 08W | A0M6 | Angelica Mendez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP | 2021 | SH | SONORA | Yosemite Assets | 0 | 8100 | 8100 | 1.5341 | 0 | 1.5341 | [5 empty] | 6133206 | 1783746 | 4349460 | 109537.3 | 694817.6 | 4934740.3 | On/Under Budget | 2522849.2 | 158.5 | 0 | 158.5 | 205.5 | 6602.9 | 86609.2 | 16119.8 | Project is not in the WP or in 2020 WP | 0 | 17581.1 | -17581.1 | 17581.1 | -17581.1 | 10706.7 | 4819.5 | 593.6 | 158.5 | 158.5 | 158.5 | 164.3 | 164.3 | 164.3 | 164.3 | 164.3 | 164.3 | 999444.1 | 854928.4 | 640143.5 | 14111.8 | 6459.5 | 6459.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2521546.8 | 2021-04-02 | 145830 | BL-B: | BL-B: 35052823_CWSP - MIWUK 1702 - LR 6018 - PH 1.1_08W -May 2021 | 2020-07-24 | 2020-07-03 | Completed |  |  | Completed | 2020-07-30 | Completed | 2020-10-23 | Completed | 2022-02-02 | 2022-02-04 | Not Started | 2022-02-07 | 2022-02-25 | Not Started | 2020-09-04 | 2020-09-30 | Completed | 2022-02-25 | Not Started | [8 empty] | 2022-04-07 | Not Started | 2021-05-07 | 2022-04-25 | -353 | Behind Schedule | Not Started | 2022-04-26 | 2022-05-09 | Not Started | 2022-08-02 | Not Started
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | 5531041 | UNSC | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | Not in the WP | 2021 | SH | SNCARLOS | Peninsula Assets | 0 | 5597 | 5597 | 1.06 | 0 | 1.06 | [5 empty] | 190000 | 0 | 190000 | 110998.5 | 0 | 79001.5 | On/Under Budget | 1371398.3 | 721.9 | 0 | 721.9 | 5447.9 | 42969.5 | 56522.8 | 6058.4 | Project is not in the WP or in 2020 WP | 0 | 12555.6 | -12555.6 | 12555.6 | -12555.6 | 3625.8 | 1609.1 | 823.5 | 721.9 | 721.9 | 722 | 721.9 | 721.9 | 721.9 | 721.9 | 721.9 | 721.9 | 614285.8 | 366659.6 | 365598.9 | 3280.7 | 3280.7 | 3129.2 | 3129.2 | 3129.2 | 3129.2 | 0 | 0 | 0 | 1365622.5 | 2021-04-02 | 147007 | BL-A | BL-A 35053429__CWSP - HALF MOON BAY 1102 - FUCO 12457 REPL OH - FEB 2021 | 2020-08-11 | 2019-06-13 | Completed |  |  | Not Started | 2020-10-16 | Completed | 2022-04-28 | Not Started | 2022-05-13 | 2022-05-13 | Not Started | 2022-06-03 | 2022-06-09 | Not Started | 2022-05-02 | 2022-05-20 | Not Started | 2022-06-10 | Not Started |  |  |  |  | 2022-06-13 | Not Started | 2022-07-19 | Not Started | 2022-07-19 | Not Started | 2021-02-15 | 2022-08-08 | -539 | Behind Schedule | Not Started | 2022-09-27 | 2022-10-10 | Not Started | 2023-01-30 | Not Started
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | E.5014723.01 | 5783905 | UNSC | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 10641 | 10641 | 2.0153 | 0 | 2.0153 | [5 empty] | 250000 | 0 | 250000 | 173503.1 | 0 | 76496.9 | On/Under Budget | 2890491.4 | 239.8 | -250 | 489.8 | 205.5 | 23989.3 | 146272.5 | 2785.8 | Project is not in the WP or in 2020 WP | 0 | 6751.4 | -6751.4 | 6751.4 | -6751.4 | 957.4 | 660.4 | 1418 | 239.8 | 239.8 | 239.8 | 248.6 | 248.6 | 248.6 | 248.6 | 248.6 | 1753.2 | 1378915.5 | 578469.1 | 614438.9 | 279462.3 | 15060.7 | 3444 | 2870.9 | 2870.9 | 2870.9 | 2870.9 | 2870.9 | 2870.9 | 2887015.9 | 2021-04-02 | 145851 | BL-A: | BL-A: 35052735_CWSP - MIWUK 1701 - LR 10600 PH 1.1_08W - April 2021 | 2020-07-24 | 2020-07-14 | Completed | 2020-10-30 | 2020-12-03 | Not Started | 2020-09-04 | Completed | 2022-01-03 | Not Started | 2020-11-17 | 2020-11-17 | Completed | 2022-01-04 | 2022-01-10 | Not Started | 2022-01-04 | 2022-01-13 | Not Started | 2022-02-22 | Not Started |  |  |  |  | 2022-02-22 | Not Started |  |  | 2022-05-26 | Not Started | 2021-04-02 | 2022-08-11 | -496 | Behind Schedule | Not Started | 2022-08-12 | 2022-08-25 | Not Started | 2022-10-17 | Not Started
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | E.5015029.10 | 5785166 | UNSC | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2022 | 2022 | SH | LAKEPORT | Humboldt Division Assets | 0 | 4961 | 4961 | 0.93958 | 0 | 0.93958 | 4351 | 0 | 0.82405 | 0 |  | 687082.4 | 641628.4 | 45454 | 33641.8 | 0 | 11812.2 | On/Under Budget | 397492.4 | 2294.7 | 0 | 2294.7 | 0 | 736.1 | 30188.3 | 2717.4 | Request 2021 Budget | 0 | 402504.6 | -402504.6 | 402504.6 | -402504.6 | 1288.1 | 1459.3 | -30 | 2294.7 | 2294.7 | 2294.7 | 3706.7 | 225872.1 | 163324.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145845 | BL-A: | BL-A: 35094396_CWSP - KONOCTI 1102-LR 532 PH 9_08W - July 2021 | 2020-07-24 | 2020-03-21 | Completed | 2021-04-09 | 2021-04-09 | Not Started | 2020-12-04 | Completed | 2021-04-09 | Not Started | 2021-04-12 | 2021-04-12 | Not Started | 2021-04-13 | 2021-04-13 | Not Started | 2021-04-05 | 2021-04-14 | Not Started | 2022-05-09 | Not Started |  |  |  |  | 2022-05-09 | Not Started | 2022-06-01 | Not Started | 2022-06-06 | Not Started | 2021-07-02 | 2022-08-04 | -398 | Behind Schedule | Not Started | 2022-08-05 | 2022-08-18 | Not Started | 2022-09-26 | Not Started
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | E.5015029.05 | 5785161 | UNSC | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2022 | 2022 | SH | LAKEPORT | Humboldt Division Assets | 0 | 3625 | 3625 | 0.68655 | 0 | 0.68655 | [5 empty] | 470100.69 | 424646.69 | 45454 | 30214.7 | 0 | 15239.3 | On/Under Budget | 0 | 86.4 | 0 | 86.4 | 0 | 2170.7 | 25450.1 | 2593.9 | Request 2021 Budget | 0 | 2680.3 | -2680.3 | 2680.3 | -2680.3 | 1234.4 | 1195.7 | 163.8 | 86.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 145843 | BL-A: | BL-A: 35094391_CWSP - KONOCTI 1102-LR 532 PH 4_08W - June 2021 | 2020-07-24 | 2020-01-10 | Completed | 2021-04-05 | 2021-04-05 | Not Started | 2020-01-16 | Completed | 2021-04-05 | Not Started | 2021-04-06 | 2021-04-06 | Not Started | 2021-04-07 | 2021-04-08 | Not Started | 2020-07-13 | 2020-07-13 | Completed | 2022-05-17 | Not Started |  |  |  |  | 2022-05-17 | Not Started | 2022-05-25 | Not Started | 2022-05-30 | Not Started | 2021-06-17 | 2022-07-28 | -406 | Behind Schedule | Not Started | 2022-07-29 | 2022-08-11 | Not Started | 2022-09-19 | Not Started
35095246 | BUCOCAMP - ERIKA DRIVE, PARADISE |  | 5786123 | UNSC | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 89554.6 | -410445.4 | 500000 | 145545.9 | 0 | 354454.1 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 121763.3 | 23737.2 | 45.4 | Project is not in the WP or in 2020 WP | 0 | 45.4 | -45.4 | 45.4 | -45.4 | 0 | 45.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35095164 | CWSP-ORO FINO 1101 LR-2022 PH 3.1 | E.5015030.01 | 5785239 | UNSC | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 610 | 9619 | 10229 | 1.9373 | 0 | 1.9373 | [5 empty] | 250000 | 0 | 250000 | 189635.4 | 0 | 60364.6 | On/Under Budget | 3686622.9 | 110.7 | 0 | 110.7 | 0 | 5537.1 | 180788.7 | 3309.5 | Project is not in the WP or in 2020 WP | 0 | 4043.1 | -4043.1 | 4043.1 | -4043.1 | 1138.9 | 1085.3 | 1085.3 | 110.7 | 110.7 | 110.7 | 114.7 | 114.7 | 114.7 | 57.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1593000 | 1593000 | 0 | 0 | 3686000 | 2021-04-02 |  |  |  |  | 2020-08-12 | Completed | 2021-12-02 | 2021-12-22 | Not Started | 2021-04-02 | Not Started | 2021-12-22 | Not Started | 2021-12-23 | 2021-12-23 | Not Started | 2021-12-24 | 2022-01-13 | Not Started | 2021-04-23 | 2021-08-06 | Not Started | 2022-01-31 | Not Started |  |  |  |  | 2022-01-31 | Not Started | 2022-04-22 | Not Started | 2022-05-23 | Not Started | 2022-06-22 | 2022-06-22 | 0 | On/ Ahead Schedule | Not Started | 2022-06-23 | 2022-07-06 | Not Started | 2022-08-12 | Not Started
30977614 | WDDB OTTER 1102 PHASE 4 | P.06571 | 5530159 | UNSC | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | MONTEREY | Central Coast Assets | 0 | 3681 | 3681 | 0.69716 | 0 | 0.69716 | [5 empty] | 326400 | 0 | 326400 | 279877.3 | 0 | 46522.7 | On/Under Budget | 857037.1 | 0 | 0 | 0 | 26157.1 | 60844.3 | 180102.1 | 1128.2 | Project is not in the WP or in 2020 WP | 0 | 1128.2 | -1128.2 | 1128.2 | -1128.2 | 1128.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 857037.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 857037.1
30977615 | WDDB OTTER 1102 PHASE 5 | P.06572 | 5530159 | UNSC | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | MONTEREY | Central Coast Assets | 0 | 2664 | 2664 | 0.50455 | 0 | 0.50455 | [5 empty] | 245198 | 5198 | 240000 | 226469.9 | 2096 | 15626.1 | On/Under Budget | 813848.2 | 0 | 0 | 0 | 19685.7 | 50312 | 145733.4 | 1034.7 | Project is not in the WP or in 2020 WP | 0 | 1034.7 | -1034.7 | 1034.7 | -1034.7 | 1034.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 813848.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 813848.2
31478906 | RAISE T-LINE H-FRAME DONNELS-MI WUK 18/2 |  | 5785972 | UNSC | 08W | MQH5 | Matthew Heminover |  |  |  |  | Not in the WP |  |  | SONORA | [26 empty] | 9593.1 | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | 5530164 | UNSC | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2022 | 2021 | SH | WLLWCRK | Humboldt Division Assets | 0 | 6698 | 6698 | 1.2686 | 0 | 1.2686 | 6722 | 0 | 1.2731 | 0 |  | 776346.19 | -99999.81 | 876346 | 153587.7 | 0 | 722758.3 | On/Under Budget | 626206.7 | 0 | 0 | 0 | 1784.2 | 20519.3 | 128982.3 | 2301.9 | Request 2021 Budget | 0 | 628508.6 | -628508.6 | 628508.6 | -628508.6 | 1049.9 | 1252 | 0 | 0 | 0 | 0 | 302779.6 | 323427.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 128578 | WSHP | WSHP 190307 - 35043296_WILLOW CRK 03 LR 3090_08W - B1 | 2019-03-07 | 2020-05-22 | Completed | 2020-11-12 | 2021-04-02 | Not Started | 2019-07-16 | Completed | 2021-04-23 | Not Started | 2022-01-19 | 2022-01-19 | Not Started |  |  |  | 2022-01-19 | 2022-02-15 | Not Started | 2022-02-16 | Not Started |  |  |  |  | 2022-02-16 | Not Started |  |  | 2022-04-04 | Not Started | 2019-11-13 | 2022-04-04 | -873 | Behind Schedule | Not Started |  |  |  | 2022-05-24 | Not Started
35040506 | RR2105 RESILIENCE - 5090 ZONE STEEL & TW |  | 5530159 | UNSE | 08W | EESA | Emili E Scaief |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35042421 | CWSP - MIWUK 1701 - LR 8050 |  | 5530178 | UNSE | 08W | SKA1 | Scott Keith Avery |  |  |  |  | Not in the WP |  |  | SONORA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35042603 | DIAMOND SPRINGS 1103 RECOND 18-0029738 |  | 5530173 | UNSE | 08W | GSD5 | Gurshawn Singh Dhillon |  |  |  |  | Not in the WP |  |  | AUBURN | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043311 | CWSP - MIWUK 1701- LR8060 |  | 5530178 | UNSE | 08W | DET3 | Daniel Edward Thomas |  |  |  |  | Not in the WP |  |  | SONORA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043381 | CWSP-MIWUK 1702-LR 6018-PHASE 1 |  | 5530178 | UNSE | 08W | SKA1 | Scott Keith Avery |  |  |  |  | Not in the WP |  |  | SONORA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043384 | CWSP-CURTIS 1705 - TS843 & 10590 |  | 5530178 | UNSE | 08W | JU2K | Joshua Chung |  |  |  |  | Not in the WP |  |  | SONORA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35042365 | CWSP - CAMP EVERS 2106 - LR 60124 - PH 5 |  | 5530160 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | SNJOSE |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35042366 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 4 |  | 5530160 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | SNJOSE |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35042367 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 3 |  | 5530160 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | SNJOSE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35042368 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 2 |  | 5530160 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | SNJOSE |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35042369 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 1 |  | 5530160 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | SNJOSE |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35040017 | CWSP - OAK K 1102 OCB LVL 1 HARDENING |  | 5530162 | UNSE | 08W | RNLO | Russell N Loeffler |  |  |  |  | Not in the WP |  |  | OAKLAND | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35040018 | CWSP - MORAGA 1101 (VARIOUS) - OCB |  | 5530161 | UNSE | 08W | RNLO | Russell N Loeffler |  |  |  |  | Not in the WP |  |  | CONCORD | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35040118 | CWSP: MIWUK 1701_OCB WILDFIRE HARDENING |  | 5530178 | UNSE | 08W | SKA1 | Scott Keith Avery |  |  |  |  | Not in the WP |  |  | SONORA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35039982 | CWSP: MIWUK 1702_OCB WILDFIRE HARDENING |  | 5530178 | UNSE | 08W | SKA1 | Scott Keith Avery |  |  |  |  | Not in the WP |  |  | SONORA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35039748 | CWSP-MIWUK 1702-LR 38218 |  | 5530178 | UNSE | 08W | SKA1 | Scott Keith Avery |  |  |  |  | Not in the WP |  |  | SONORA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35013233 | R2RPL OH WIRE ON GONZALS-1101 17-0063084 |  | 5530159 | UNSE | 08W | MUGM | Michael Andrew Garcia |  |  |  |  | Not in the WP |  |  | SALINAS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35019004 | PURISIMA 1101 LS SW8139 REPL OH LINE |  | 5530159 | UNSE | 08W | A2LH | Anthony Lucero | J1M9 | Jennifer Monson |  |  | Not in the WP |  |  | SALINAS | Central Coast Assets | [11 empty] | 1 | -49999 | 50000 | 8820.9 | 0 | 41179.1 | On/Under Budget | 0 | 0 | 0 | 0 | 2339.3 | 6481.6 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31361489 | OLEMA 1101 HIGH SPLICE COUNT 3 |  | 5530168 | UNSE | 08W | FXRZ | Fernando Recoder |  |  |  |  | Not in the WP |  |  | SNRAFAEL | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35029270 | MORGAN HILL 2111 RECOND 13-SPANS W TW |  | 5530174 | UNSE | 08W | MUR6 | Mario Alberto Rodriguez Gonzalez |  |  |  |  | Not in the WP |  |  | SNJOSE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35024428 | SUMMIT 1101 RECONDUCTOR W TREE WIRE |  | 5530173 | UNSE | 08W | GSD5 | Gurshawn Singh Dhillon |  |  |  |  | Not in the WP |  |  | AUBURN | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35024647 | RR 2104 RECOND 1051 ZONE W TW |  | 5530159 | UNSE | 08W | E2MA | Erik Madsen |  |  |  |  | Not in the WP |  |  | WTSNVLLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31246787 | RECONDUCTOR 4 SPANS - 100 DEODARA WAY |  | 5530161 | UNSE | 08W | GAE9 | Glenn Esguerra |  |  |  |  | Not in the WP |  |  | CONCORD | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31089263 | MOVE FUSE 1179/RECON WITH TREE WIRE |  | 5530161 | UNSE | 08W | ARBS | Amanda Robin Barley |  |  |  |  | Not in the WP |  | SH | CONCORD |  | 0 | 400 | 400 | 0.075758 | 0 | 0.075758 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31319329 | SAN LUIS OBISP1103 - RECOND WITH 2CU TW |  | 5530166 | UNSE | 08W | S3B2 | Shahryar Bayat |  |  |  |  | Not in the WP |  |  | SNLUISOB | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31334290 | RECON 24 SPANS -ALBION RIDGE RD |  | 5533649 | UNSE | 08W | DRN3 | Dale Robert Novakovich |  |  |  |  | Not in the WP |  |  | FTBRAGG | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31344016 | 2019 OLEMA 1101 HIGH SPLICE CNT_1 |  | 5530168 | UNSE | 08W | FXRZ | Fernando Recoder |  |  |  |  | Not in the WP |  |  | SNRAFAEL | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31344017 | 2019 OLEMA 1101 HIGH SPLICE CNT_2 |  | 5530168 | UNSE | 08W | FXRZ | Fernando Recoder |  |  |  |  | Not in the WP |  |  | SNRAFAEL | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | 5530168 | UNSE | 08W | FXRZ | Fernando Recoder |  |  |  |  | Not in the WP |  | SH | NAPA |  | 7180.8 | 316.8 | 7497.6 | 1.42 | 0 | 1.42 | [19 empty] | 4586.3 | Project is not in the WP or in 2020 WP | 0 | 4586.3 | -4586.3 | 0 | 0
31361969 | RECON 9,400 FT - POINT ARENA 1101 |  | 5530175 | UNSE | 08W | DRN3 | Dale Robert Novakovich |  |  |  |  | Not in the WP |  |  | STROSA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31364228 | RECOND 4490FT OF 4ACSR WITH 2CU TW |  | 5530166 | UNSE | 08W | S3B2 | Shahryar Bayat |  |  |  |  | Not in the WP |  |  | SNLUISOB | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31374249 | 14184 FT OF 4ACSR&3363 FT OF 6CUW 2CU TW |  | 5530166 | UNSE | 08W | S3B2 | Shahryar Bayat |  |  |  |  | Not in the WP |  |  | SNLUISOB | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31297273 | RECOND HWY1 (BY SW 92493)- GUALALA 1111 |  | 5530175 | UNSE | 08W | DRN3 | Dale Robert Novakovich |  |  |  |  | Not in the WP |  |  | PTARENA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31289812 | RECOND TAP W TW - LCO 5265 GUALALA 1112 |  | 5530175 | UNSE | 08W | DRN3 | Dale Robert Novakovich |  |  |  |  | Not in the WP |  |  | PTARENA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 |  | 5530159 | UNSE | 08W | SMQ3 | Stephen Michael Queen |  |  |  |  | Not in the WP |  |  | STCRUZ | [26 empty] | 1370.5 | Project is not in the WP or in 2020 WP | 0 | 1370.5 | -1370.5 | 0 | 0
31288039 | HOOPA 1101 RCOND WITH TREE WIRE |  | 5530164 | UNSE | 08W | SLH8 | Shawn Leslie Howard |  |  |  |  | Not in the WP |  |  | WLLWCRK | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35099603 | MORRO BAY 1102 RECON 4728 FT W TW |  | 5530166 | UNSE | 08W | S3B2 | Shahryar Bayat |  |  |  |  | Not in the WP |  |  | SNLUISOB | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35103619 | BR-10-03-W (E) FILBERT PARB |  | 5786123 | UNSE | 08W | AVP4 | Aaron Patane |  |  |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35104252 | BR-05-03-W (E) CLARK PH II PARB |  | 5786123 | UNSE | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35105650 | BR-08-06-W (E) FICKETT LN PARB |  | 5786123 | UNSE | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | 2021 |  |  | CHICO | North Valley Assets | [11 empty] | 1 | -6790956 | 6790957 | 2313391.8 | 0 | 4477565.2 | On/Under Budget | 956.7 | 1913.4 | 0 | 1913.4 | 0 | 8755 | 722620.4 | 1582016.4 | Request 2021 Budget | 0 | 1584886.5 | -1584886.5 | 1584886.5 | -1584886.5 | 411156.7 | 68424 | 1102435.7 | 1913.4 | 956.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35093737 | FAIRVIEW 2207-CROCKETT BLVD-WIRE DOWN |  | 5530162 | UNSE | 08W | MYL5 | Michael Y. Lee |  |  |  |  | Not in the WP |  |  | RICHMOND | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35081862 | MARTELL 1101 RECOND. 4ACSR W/ 1/0AR TW | E.5020288.01 | 5784648 | UNSE | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  |  | JACKSON | Stockton Assets | [11 empty] | 50000 | 0 | 50000 | 2914.4 | 0 | 47085.6 | On/Under Budget | 1262610.9 | 0 | 0 | 0 | 0 | 2766.5 | 97 | 50.9 | Project is not in the WP or in 2020 WP | 0 | 50.9 | -50.9 | 50.9 | -50.9 | 17.5 | 16.7 | 16.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3827.8 | 3827.8 | 3827.8 | 3827.8 | 3827.8 | 3827.8 | 3827.8 | 3827.8 | 6827.8 | 598870.6 | 622462 | 3827.8 | 1262610.6
35075365 | RPL OH.COND.CAMP EVERS 2106 19-0015630 |  | 5530159 | UNSE | 08W | SMQ3 | Stephen Michael Queen |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35067619 | CWSP – MONTE RIO 1112 – LR 120 |  | 5782761 | UNSE | 08W | SLH8 | Shawn Leslie Howard |  |  |  |  | Not in the WP |  |  | STROSA |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 4 | Project is not in the WP or in 2020 WP | 0 | 4 | -4 | 0 | 0
35071495 | RPL OH.CON.RESERVATION RD.1102 18-011072 |  | 5530159 | UNSE | 08W | MUGM | Michael Andrew Garcia |  |  |  |  | Not in the WP |  |  | SALINAS | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35065842 | CWSP-EL DORADO 2101 - LR 26000 - PH3 |  | 5782591 | UNSE | 08W | GSD5 | Gurshawn Singh Dhillon |  |  |  |  | Not in the WP |  |  | AUBURN | [26 empty] | 29.9 | Project is not in the WP or in 2020 WP | 0 | 29.9 | -29.9 | 0 | 0
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | 5783289 | UNSE | 08W | B1GQ | Brian Gallo |  |  |  |  | Not in the WP | 2021 |  | SNLUISOB |  | 0 | 10900 | 10900 | 2.0644 | 0 | 2.0644 | [19 empty] | 1993.6 | Project is not in the WP or in 2020 WP | 0 | 1993.6 | -1993.6 | 0 | 0 | [25 empty] | 2021-04-02 | 130697 | WSHP | WSHP 190307 - 35066622_FOOTHILL 1101 LS CO9973 REPL OH LINE - B1 | 2019-04-15 | 2022-06-21 | Not Started |  |  | Not Started |  |  | 2022-09-06 | Not Started | 2022-09-07 | 2022-09-27 | Not Started |  |  |  | 2022-09-07 | 2022-09-20 | Not Started | 2022-10-20 | Not Started |  |  |  |  | 2022-10-20 | Not Started |  |  | 2022-12-15 | Not Started | 2019-10-07 | 2022-12-29 | -1179 | Behind Schedule | Not Started |  |  |  | 2023-07-06 | Not Started
35076129 | DIAMOND SPRINGS 1105 RECOND WD18-0105867 |  | 5784105 | UNSE | 08W | GSD5 | Gurshawn Singh Dhillon |  |  |  |  | Not in the WP |  |  | AUBURN | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35076130 | TAMARACK 1101 WD 19-0011942 |  | 5530173 | UNSE | 08W | GSD5 | Gurshawn Singh Dhillon |  |  |  |  | Not in the WP |  |  | AUBURN | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35077348 | RECONDUCTOR 17547 FT OF 4ACSR W 2CU TW |  | 5784376 | UNSE | 08W | S3B2 | Shahryar Bayat |  |  |  |  | Not in the WP |  |  | SNLUISOB | [26 empty] | 15.6 | Project is not in the WP or in 2020 WP | 0 | 15.6 | -15.6 | 0 | 0
35060995 | CWSP-BRUNSWICK 1106 LR-2104 ZONE |  | 5783059 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [26 empty] | 32.4 | Project is not in the WP or in 2020 WP | 0 | 32.4 | -32.4 | 0 | 0
35061041 | CWSP – MONTE RIO 1112 – TS 15401 |  | 5782762 | UNSE | 08W | SLH8 | Shawn Leslie Howard |  |  |  |  | Not in the WP |  |  | STROSA | [26 empty] | 180.7 | Project is not in the WP or in 2020 WP | 0 | 180.7 | -180.7 | 0 | 0
35073059 | SONOMA1104 WIREDOWN |  | 5530175 | UNSE | 08W | JBJ8 | Jeffrey Burbank Jung |  |  |  |  | Not in the WP |  |  | STROSA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35073637 | LOS GATOS 1107 RECOND FUSE 468855 ZONE |  | 5530160 | UNSE | 08W | GMK5 | Greg Kacherginsky |  |  |  |  | Not in the WP |  |  | CUPRTINO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35074009 | ALTO 1124 WIRE DOWN ILIS 18-0109573 |  | 5530168 | UNSE | 08W | FXRZ | Fernando Recoder |  |  |  |  | Not in the WP |  |  | SNRAFAEL | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35074388 | RECOND GV2101 FUSE 12347 ZONE |  | 5784143 | UNSE | 08W | E2MA | Erik Madsen |  |  |  |  | Not in the WP |  |  | WTSNVLLE | [26 empty] | 19.3 | Project is not in the WP or in 2020 WP | 0 | 19.3 | -19.3 | 0 | 0
35052736 | CWSP - MIWUK 1701 LR11800 |  | 5784645 | UNSE | 08W | DET3 | Daniel Edward Thomas |  |  |  |  | Not in the WP |  |  | SONORA | [26 empty] | 403.7 | Project is not in the WP or in 2020 WP | 0 | 1606.6 | -1606.6 | 0 | 0
35052738 | CWSP-CURTIS1705-TS843-PHASE1 |  | 5530178 | UNSE | 08W | JU2K | Joshua Chung |  |  |  |  | Not in the WP |  |  | SONORA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35052822 | CWSP - MIWUK 1701 - LR 8050 |  | 5793711 | UNSE | 08W | TXY6 | Tom Yang |  |  |  |  | Not in the WP |  |  | SONORA |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 10.6 | Project is not in the WP or in 2020 WP | 0 | 10.6 | -10.6 | 0 | 0
35052732 | CWSP - BIG BASIN 1101 5028 ZONE |  | 5530159 | UNSE | 08W | E2MA | Erik Madsen |  |  |  |  | Not in the WP |  |  | STCRUZ | [26 empty] | 253.4 | Project is not in the WP or in 2020 WP | 0 | 253.4 | -253.4 | 0 | 0
35052733 | CWSP - BIG BASIN 1101 - 10296 ZONE PH2 |  | 5530159 | UNSE | 08W | E2MA | Erik Madsen |  |  |  |  | Not in the WP |  |  | STCRUZ | [26 empty] | 104.3 | Project is not in the WP or in 2020 WP | 0 | 104.3 | -104.3 | 0 | 0
35052734 | CWSP - CAMP EVERS 2105 - LR 5232-33542 |  | 5530159 | UNSE | 08W | E2MA | Erik Madsen |  |  |  |  | Not in the WP |  |  | STCRUZ | [26 empty] | 232.4 | Project is not in the WP or in 2020 WP | 0 | 232.4 | -232.4 | 0 | 0
35052726 | CWSP - LOS GATOS 1106 LR 60116 PH1 |  | 5530160 | UNSE | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | CUPRTINO | [26 empty] | 514.7 | Project is not in the WP or in 2020 WP | 0 | 514.7 | -514.7 | 0 | 0
35052727 | CWSP LOS GATOS 1106 LR 1106 PHASE 2 |  | 5530160 | UNSE | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | CUPRTINO | [26 empty] | 332.7 | Project is not in the WP or in 2020 WP | 0 | 332.7 | -332.7 | 0 | 0
35052728 | CWSP - LOS GATOS 1107 LR 60092 PH1 |  | 5530160 | UNSE | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | CUPRTINO | [26 empty] | 398.8 | Project is not in the WP or in 2020 WP | 0 | 398.8 | -398.8 | 0 | 0
35052729 | CWSP - BURNS 2101 - PH 1 |  | 5530159 | UNSE | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | STCRUZ | [26 empty] | 247.6 | Project is not in the WP or in 2020 WP | 0 | 247.6 | -247.6 | 0 | 0
35052730 | CWSP - BURNS 2101- PH 2 |  | 5530159 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | STCRUZ | [26 empty] | 113.4 | Project is not in the WP or in 2020 WP | 0 | 113.4 | -113.4 | 0 | 0
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | 5795126 | UNSE | 08W | SLH8 | Shawn Leslie Howard |  |  |  |  | Not in the WP |  | SH | GRSSVLLY |  | 0 | 4804.8 | 4804.8 | 0.91 | 0 | 0.91 | [19 empty] | 18695 | Project is not in the WP or in 2020 WP | 0 | 18695 | -18695 | 0 | 0
35056433 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 | E.5015425.01 | 5782581 | UNSE | 08W | J91F | Justin M Stabe | AXYX | Aaron Yuen |  |  | Not in the WP |  |  | PLCRVLLE | Sierra Assets | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 1 | 1 | 0 | 21280.5 | 0 | -21280.5 | OverRun | 0 | 0 | 0 | 0 | 5694.8 | 9046.4 | 6167.9 | 371.4 | Project is not in the WP or in 2020 WP | 0 | 371.4 | -371.4 | 371.4 | -371.4 | 127.8 | 121.8 | 121.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35056434 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 |  | 5782582 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | PLCRVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 303.5 | Project is not in the WP or in 2020 WP | 0 | 303.5 | -303.5 | 0 | 0
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | 5782583 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | PLCRVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 2091.4 | Project is not in the WP or in 2020 WP | 0 | 2091.4 | -2091.4 | 0 | 0
35056438 | REMG 650 - PLACERVILLE 2106, RINGTAIL |  | 5782584 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | PLCRVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 227.5 | Project is not in the WP or in 2020 WP | 0 | 227.5 | -227.5 | 0 | 0
35056439 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 |  | 5782585 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | PLCRVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 211.3 | Project is not in the WP or in 2020 WP | 0 | 211.3 | -211.3 | 0 | 0
35052824 | CWSP - MIWUK 1702 - LR6018 - PH 2 |  | 5786460 | UNSE | 08W | SKA1 | Scott Keith Avery |  |  |  |  | Not in the WP |  |  | SONORA |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 4 | Project is not in the WP or in 2020 WP | 0 | 4 | -4 | 0 | 0
35056732 | CWSP FOREST HILL 1101 LR 50486 HARDENING |  | 5782592 | UNSE | 08W | JXF8 | Joseph Fong |  |  |  |  | Not in the WP |  |  | AUBURN | [26 empty] | 52.4 | Project is not in the WP or in 2020 WP | 0 | 52.4 | -52.4 | 0 | 0
35057802 | CWSP-CAMPEVERS2105 - LR 12590 - 4KV PH5 |  | 5782531 | UNSE | 08W | E2MA | Erik Madsen |  |  |  |  | Not in the WP |  |  | STCRUZ | [26 empty] | 102.5 | Project is not in the WP or in 2020 WP | 0 | 102.5 | -102.5 | 0 | 0
35057921 | PUEBLO 2103 RECOND W TW PAST FUSE 2013 |  | 5530168 | UNSE | 08W | FXRZ | Fernando Recoder |  |  |  |  | Not in the WP |  |  | NAPA | [26 empty] | 23.5 | Project is not in the WP or in 2020 WP | 0 | 23.5 | -23.5 | 0 | 0
35060990 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH3.01 |  | 5783062 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 4562 | 4562 | 0.86402 | 0 | 0.86402 | [19 empty] | 355.6 | Project is not in the WP or in 2020 WP | 0 | 355.6 | -355.6 | 0 | 0
35060991 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH2.01 |  | 5783063 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 2465 | 2465 | 0.46686 | 0 | 0.46686 | [19 empty] | 290.9 | Project is not in the WP or in 2020 WP | 0 | 290.9 | -290.9 | 0 | 0
35060992 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH1.01 |  | 5783064 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 2534 | 2534 | 0.47992 | 0 | 0.47992 | [19 empty] | 637.3 | Project is not in the WP or in 2020 WP | 0 | 637.3 | -637.3 | 0 | 0
35061810 | CWSP - EL DORADO PH 2101 ZONE 19612 |  | 5783177 | UNSE | 08W | GSD5 | Gurshawn Singh Dhillon |  |  |  |  | Not in the WP |  |  | AUBURN | [26 empty] | 80.5 | Project is not in the WP or in 2020 WP | 0 | 80.5 | -80.5 | 0 | 0
35061811 | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 | E.5015574.01 | 5783198 | UNSE | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  |  | AUBURN | Sierra Assets | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100000 | 0 | 100000 | 7250.5 | 0 | 92749.5 | On/Under Budget | 0 | 0 | 0 | 0 | 3336.1 | 3311.4 | 476.4 | 126.6 | Project is not in the WP or in 2020 WP | 0 | 126.6 | -126.6 | 126.6 | -126.6 | 43.6 | 41.5 | 41.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35061812 | CWSP - EL DORADO PH 2102 ZONE 6645 |  | 5783199 | UNSE | 08W | GSD5 | Gurshawn Singh Dhillon |  |  |  |  | Not in the WP |  |  | AUBURN | [26 empty] | 114.3 | Project is not in the WP or in 2020 WP | 0 | 114.3 | -114.3 | 0 | 0
35062173 | Cancl FIRE PADSE 1105 INST NOVA BILLE RD |  | 5530169 | UNSE | 08W | JXF8 | Joseph Fong |  |  |  |  | Not in the WP |  |  | CHICO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | E.5015572.01 | 5783067 | UNSE | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2022 |  | SH | PLCRVLLE | Sierra Assets | 8106 | 0 | 8106 | 1.5352 | 0 | 1.5352 |  |  |  |  | GC | 220000 | 0 | 220000 | 110722.5 | 0 | 109277.5 | On/Under Budget | 4791806.4 | 60000 | -55000 | 115000 | 23416.9 | 1241.9 | 3363.4 | 27700.3 | Budget Allocated | 153434.85 | 211145.1 | -57710.25 | 211145.1 | -57710.25 | 12840.2 | 12149.9 | 57710.2 | 60000 | 44222.4 | 24222.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1180840.4 | 1180840.4 | 1180840.4 | 1180840.4 | 0 | 0 | 0 | 0 | 0 | 4723361.6 | 2021-04-02 |  |  |  |  | 2021-06-30 | Not Started | 2021-08-05 | 2021-08-11 | Not Started | 2021-08-04 | Not Started | 2021-09-01 | Not Started | 2021-07-01 | 2021-07-01 | Not Started | 2021-07-02 | 2021-07-22 | Not Started | 2021-08-05 | 2021-08-18 | Not Started | 2021-09-24 | Not Started | 2021-09-24 | Not Started | 2021-10-07 | Not Started | 2021-09-24 | Not Started | 2022-01-06 | Not Started | 2022-02-04 | Not Started | 2022-04-07 | 2022-04-07 | 0 | On/ Ahead Schedule | Not Started | 2022-04-08 | 2022-04-21 | Not Started | 2022-06-06 | Not Started
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | E.5015571.01 | 5783068 | UNSE | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2022 |  | SH | PLCRVLLE | Sierra Assets | 5860 | 0 | 5860 | 1.1098 | 0 | 1.1098 |  |  |  |  | GC | 1 | 1 | 0 | 155814.5 | 0 | -155814.5 | OverRun | 0 | 0 | -119930.4 | 119930.4 | 2301.1 | 1702.9 | 1203.9 | 30676.1 | Request 2021 Budget | 0 | 150606.5 | -150606.5 | 150606.5 | -150606.5 | 15839.5 | 11458 | 123309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156275 | BL-A | BL-A 35062375_CWSP - Shingle Springs 2109 - LR 9372_08W - DD 210219 Feb. 2021 | 2021-02-25 | 2021-07-02 | Not Started | 2021-09-13 | 2021-09-17 | Not Started | 2021-09-10 | Not Started | 2021-10-08 | Not Started | 2021-07-05 | 2021-07-05 | Not Started | 2021-07-06 | 2021-07-26 | Not Started | 2021-09-13 | 2021-11-12 | Not Started | 2022-01-04 | Not Started | 2022-01-04 | Not Started | 2022-01-17 | Not Started | 2022-01-04 | Not Started | 2022-03-14 | Not Started | 2022-04-12 | Not Started | 2022-06-13 | 2022-06-13 | 0 | On/ Ahead Schedule | Not Started | 2022-06-14 | 2022-06-27 | Not Started | 2022-08-10 | Not Started
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | E.5015570.01 | 5783069 | UNSE | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2022 | 2022 | SH | PLCRVLLE | Sierra Assets | 22892 | 0 | 22892 | 4.3356 | 0 | 4.3356 |  |  |  |  | GC | 220000 | 0 | 220000 | 26352.8 | 0 | 193647.2 | On/Under Budget | 7842197.4 | 161132.5 | 0 | 161132.5 | 1438.6 | 76.4 | 397.4 | 24440.5 | Budget Allocated | 364360.62 | 372786.7 | -8426.08 | 367446.7 | -3086.08 | 14536.2 | 6818.3 | 3086 | 161132.5 | 161688.4 | 20185.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1532064.7 | 1532064.7 | 1532064.7 | 1532064.7 | 1532064.7 | 0 | 0 | 0 | 7660323.5 | 2021-04-02 |  |  |  |  | 2021-05-21 | Not Started | 2021-05-28 | 2021-06-03 | Not Started | 2021-05-27 | Not Started | 2021-07-16 | Not Started | 2021-05-24 | 2021-05-24 | Not Started | 2021-05-25 | 2021-06-14 | Not Started | 2021-05-28 | 2021-06-10 | Not Started | 2021-08-10 | Not Started | 2021-08-10 | Not Started | 2021-08-23 | Not Started | 2021-08-10 | Not Started | 2021-11-22 | Not Started | 2021-12-21 | Not Started | 2022-02-21 | 2022-02-21 | 0 | On/ Ahead Schedule | Not Started | 2022-02-22 | 2022-03-07 | Not Started | 2022-04-20 | Not Started
35058794 | CWSP - APPLE HILL 2102 - 7502 - PHASE 1 |  | 5782527 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | PLCRVLLE | [26 empty] | 118.4 | Project is not in the WP or in 2020 WP | 0 | 118.4 | -118.4 | 0 | 0
35058795 | CWSP - APPLE HILL 2102 - 7502 - PHASE 2 |  | 5782528 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | PLCRVLLE | [26 empty] | 59.8 | Project is not in the WP or in 2020 WP | 0 | 59.8 | -59.8 | 0 | 0
35058797 | CWSP - APPLE HILL 2102 - 7502 - PHASE 3 |  | 5782529 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | PLCRVLLE | [26 empty] | 81.7 | Project is not in the WP or in 2020 WP | 0 | 81.7 | -81.7 | 0 | 0
35058060 | SWIFT 2110 - CONDUCTOR REPL |  | 5530174 | UNSE | 08W | MXEN | Mohamed Elzain |  |  |  |  | Not in the WP |  |  | SNJOSE | [26 empty] | 141.3 | Project is not in the WP or in 2020 WP | 0 | 141.3 | -141.3 | 0 | 0
35059696 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH |  | 5782841 | UNSE | 08W | GSD5 | Gurshawn Singh Dhillon |  |  |  |  | Not in the WP |  |  | AUBURN | [26 empty] | 13.4 | Project is not in the WP or in 2020 WP | 0 | 13.4 | -13.4 | 0 | 0
35060027 | CWSP-PARADISE 1104-TS 1571 |  | 5530169 | UNSE | 08W | SLH8 | Shawn Leslie Howard |  |  |  |  | Not in the WP |  |  | CHICO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35058272 | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 |  | 5782589 | UNSE | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | PLCRVLLE | [26 empty] | 110.4 | Project is not in the WP or in 2020 WP | 0 | 110.4 | -110.4 | 0 | 0
35060383 | WDDB - FRUITLAND 1142CB C/O 1679 |  | 5530164 | UNSE | 08W | SLH8 | Shawn Leslie Howard |  |  |  |  | Not in the WP |  |  | GARBRVLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35060387 | WDDB BIG RIVER 1101 FUSE 5187 RECONDUCTO |  | 5513264 | UNSE | 08W | SLH8 | Shawn Leslie Howard |  |  |  |  | Not in the WP |  |  | FTBRAGG | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35060228 | 2019 OH COND RPLC: EEL RIVER 1102 FU1903 |  | 5530164 | UNSE | 08W | SLH8 | Shawn Leslie Howard |  |  |  |  | Not in the WP |  |  | FORTUNA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35051484 | CWSP - MONTE RIO 1113 - 8299 |  | 5530175 | UNSE | 08W | JBJ8 | Jeffrey Burbank Jung |  |  |  |  | Not in the WP |  |  | STROSA | [26 empty] | 172 | Project is not in the WP or in 2020 WP | 0 | 172 | -172 | 0 | 0
35051485 | CWSP - MONTE RIO 1111 - 1701 |  | 5530175 | UNSE | 08W | JBJ8 | Jeffrey Burbank Jung |  |  |  |  | Not in the WP |  |  | STROSA | [26 empty] | 195.2 | Project is not in the WP or in 2020 WP | 0 | 195.2 | -195.2 | 0 | 0
35052327 | CWSP-PARADISE 1101 OCB ZONE |  | 5530169 | UNSE | 08W | MTTA | Musie Tsegay Tesfasilassie |  |  |  |  | Not in the WP |  |  | CHICO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35052328 | CALISTOGA 1101 WIRE DOWN 18-0052856 |  | 5530168 | UNSE | 08W | FXRZ | Fernando Recoder |  |  |  |  | Not in the WP |  |  | NAPA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35050942 | CWSP: GARBERVILLE 1101 HENDRIX PILOT |  | 5530164 | UNSE | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2023 |  |  | GARBRVLE | Humboldt Division Assets | 0 | 9000 | 9000 | 1.7045 | 0 | 1.7045 | [5 empty] | 95000 | 0 | 95000 | 13257.7 | 0 | 81742.3 | On/Under Budget | 0 | 0 | 0 | 0 | 2135.4 | 5409.6 | 5712.7 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35050945 | CWSP - BRUNSWICK 1106 - 2143 |  | 5530173 | UNSE | 08W | MYL5 | Michael Y. Lee |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35050947 | CWSP - BRUNSWICK 1106 - 2794 - PH 1 |  | 5530173 | UNSE | 08W | MYL5 | Michael Y. Lee |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35050949 | CWSP - BRUNSWICK 1106 - 2794 - PH 2 |  | 5530173 | UNSE | 08W | MYL5 | Michael Y. Lee |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35050950 | CWSP - BRUNSWICK 1106 - 2794 - PH 3 |  | 5530173 | UNSE | 08W | MYL5 | Michael Y. Lee |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | 5530175 | UNSE | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2023 | 2022 |  | STROSA | Sonoma Assets | 0 | 7400 | 7400 | 1.4015 | 0 | 1.4015 | [5 empty] | 95000 | 0 | 95000 | 24945.7 | 0 | 70054.3 | On/Under Budget | 0 | 0 | 0 | 0 | 8053.2 | 6619.1 | 9127 | 1146.4 | Project is not in the WP or in 2020 WP | 0 | 1146.4 | -1146.4 | 1146.4 | -1146.4 | 1034.7 | 0 | 111.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-03-05 | 128600 | WSHP | WSHP 190307 - 35050951_MONTE RIO 1113 HENDRIX CABLE_08W - B1 | 2019-03-07 | 2021-07-30 | Not Started |  |  | Not Started | 2019-07-16 | Completed | 2021-09-03 | Not Started | 2021-09-13 | 2021-09-13 | Not Started |  |  |  | 2022-01-14 | 2022-01-31 | Not Started | 2022-02-01 | Not Started |  |  |  |  | 2022-02-01 | Not Started |  |  | 2022-03-16 | Not Started | 2019-10-04 | 2022-03-16 | -894 | Behind Schedule | Not Started |  |  |  | 2022-05-06 | Not Started
35051252 | CWSP - PLACERVILLE 2106 - LR 1104 |  | 5530173 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35051268 | CWSP - WILLITS 1104 - LR 34008 - PH 2 |  | 5530164 | UNSE | 08W | GXFF | Grigoriy Frenkel |  |  |  |  | Not in the WP |  |  | UKIAH |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 212.5 | Project is not in the WP or in 2020 WP | 0 | 212.5 | -212.5 | 0 | 0
35051356 | CWSP - EL DORADO PH 2101 LR 26000 PH 2 |  | 5530173 | UNSE | 08W | GSD5 | Gurshawn Singh Dhillon |  |  |  |  | Not in the WP |  |  | AUBURN | [26 empty] | 66.8 | Project is not in the WP or in 2020 WP | 0 | 66.8 | -66.8 | 0 | 0
35048613 | CWSP - PARADISE 1106 - LR 2084 |  | 5530169 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | CHICO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35048678 | ECOP-BRUNSWICK 1105-H01-LR32536 ZONE PH3 |  | 5530173 | UNSE | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 36960 | 36960 | 7 | 0 | 7 | [5 empty] | 500000 | 0 | 500000 | 15606.5 | 0 | 484393.5 | On/Under Budget | 13385321.5 | 0 | 0 | 0 | 6012.1 | 0 | 9594.4 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3346330.4 | 3346330.4 | 3346330.4 | 3346330.4 | 13385321.6
35049537 | CWSP - BIG BASIN 1102 - 9741 |  | 5530159 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | STCRUZ |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35049538 | CWSP - BIG BASIN 1102 - 12758 |  | 5530159 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047314 | CWSP - CAMPEVERS2105 - LR10294 - 4KV PH1 |  | 5530159 | UNSE | 08W | E2MA | Erik Madsen |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047315 | CWSP: CAMPEVERS 2105 - LR11010 - 4KV PH2 |  | 5530159 | UNSE | 08W | E2MA | Erik Madsen |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047316 | CWSP - CAMPEVERS2105 - LR 5206 - 4KV PH3 |  | 5530159 | UNSE | 08W | E2MA | Erik Madsen |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047317 | CWSP - CAMPEVERS2105 - LR 5300 - 4KV PH7 |  | 5530159 | UNSE | 08W | E2MA | Erik Madsen |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047318 | CWSP - CAMPEVERS2105 - BT402CB - 4KV PH6 |  | 5530159 | UNSE | 08W | E2MA | Erik Madsen |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047420 | CWSP - BRUNSWICK 1106 - LR 51486 |  | 5530173 | UNSE | 08W | GAE9 | Glenn Esguerra |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047422 | CWSP - PLACERVILLE 2106 - LR 1104 |  | 5530173 | UNSE | 08W | GAE9 | Glenn Esguerra |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047429 | CWSP - WILLITS 1104 - LR 34008 PH 1 |  | 5530164 | UNSE | 08W | GAE9 | Glenn Esguerra |  |  |  |  | Not in the WP |  |  | UKIAH |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 222.6 | Project is not in the WP or in 2020 WP | 0 | 222.6 | -222.6 | 0 | 0
35047557 | *CANCEL*CWSP-BRUNSWICK 1105 LR-32536 |  | 5530173 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047601 | ECOP-BRUNSWICK 1105-H01-LR32536 ZONE PH2 |  | 5530173 | UNSE | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 46358.4 | 46358.4 | 8.78 | 0 | 8.78 | [5 empty] | 500000 | 0 | 500000 | 19712.7 | 0 | 480287.3 | On/Under Budget | 16756888.2 | 0 | 0 | 0 | 4101.4 | 0 | 15611.3 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4189222.1 | 4189222.1 | 4189222.1 | 4189222.1 | 16756888.4
35048009 | CWSP - APPLE HILL 2102 LR97982 HARDENING |  | 5530173 | UNSE | 08W | JXF8 | Joseph Fong |  |  |  |  | Not in the WP |  |  | PLCRVLLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043604 | CWSP - MIWUK 1702 - LR6018 - PHASE 2 |  | 5530178 | UNSE | 08W | SKA1 | Scott Keith Avery |  |  |  |  | Not in the WP |  |  | SONORA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043993 | CWSP - CAMPEVERS2105 - LR 74170 - 4KVPH4 |  | 5530159 | UNSE | 08W | E2MA | Erik Madsen |  |  |  |  | Not in the WP |  |  | STCRUZ | [26 empty] | 161.9 | Project is not in the WP or in 2020 WP | 0 | 161.9 | -161.9 | 0 | 0
35043994 | CWSP - CAMP EVERS 2105 - LR 11384 ZONE |  | 5530159 | UNSE | 08W | E2MA | Erik Madsen |  |  |  |  | Not in the WP |  |  | STCRUZ | [26 empty] | 145.7 | Project is not in the WP or in 2020 WP | 0 | 145.7 | -145.7 | 0 | 0
35044115 | CWSP - ROB ROY 2105 - LR 5166 |  | 5530159 | UNSE | 08W | E2MA | Erik Madsen |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35044117 | CWSP: LOS GATOS 1107 - LR60092 PH 2 |  | 5530160 | UNSE | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | CUPRTINO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047311 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 1 |  | 5530159 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | STCRUZ | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35046211 | CWSP - GARBERVILLE 1102 HENDRIX PILOT |  | 5530164 | UNSE | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2023 |  |  | GARBRVLE | Humboldt Division Assets | 0 | 4000 | 4000 | 0.75758 | 0 | 0.75758 | [5 empty] | 95000 | 0 | 95000 | 23788.8 | 0 | 71211.2 | On/Under Budget | 0 | 0 | 0 | 0 | 3303 | 16284.3 | 4201.5 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35046276 | CWSP LOS GATOS 1107-LR60092 PH 3 |  | 5530160 | UNSE | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | CUPRTINO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35046278 | CWSP LOS GATOS 1107-LR60092 PH 4 |  | 5530160 | UNSE | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | CUPRTINO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35046279 | CWSP - LOS GATOS 1107-LR60092 PH 5 |  | 5530160 | UNSE | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | CUPRTINO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35046280 | CWSP - LOS GATOS 1107 - LR60092 PH 6 |  | 5530160 | UNSE | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | CUPRTINO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043950 | CWSP - MIWUK 1701 - LR 10600 |  | 5530178 | UNSE | 08W | TXY6 | Tom Yang |  |  |  |  | Not in the WP |  |  | SONORA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043952 | CWSP - MIWUK 1702 - LR 8090 |  | 5530178 | UNSE | 08W | SKA1 | Scott Keith Avery |  |  |  |  | Not in the WP |  |  | SONORA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043830 | CWSP - MIRABEL 02 /MONTE RIO 13 - LR 652 |  | 5530175 | UNSE | 08W | JXF8 | Joseph Fong |  |  |  |  | Not in the WP |  |  | STROSA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35174174 | ECOP-STANISLAUS 1702-H03-LR1850 |  | 5539421 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | ANGLSCMP |  | 0 | 3168 | 3168 | 0.6 | 0 | 0.6 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 | 5790002 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | PLCRVLLE | Sierra Assets | 0 | 47520 | 47520 | 9 | 0 | 9 | [5 empty] | 950000 | 0 | 950000 | 19761.2 | 0 | 930238.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 19398.2 | 362.9 | Project is not in the WP or in 2020 WP | 0 | 362.9 | -362.9 | 362.9 | -362.9 | 118.5 | 3295.2 | -3050.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2022-03-14 | Not Started | 2022-04-19 | 2022-04-25 | Not Started | 2022-04-18 | Not Started | 2022-05-16 | Not Started | 2022-03-15 | 2022-03-15 | Not Started | 2022-03-16 | 2022-04-05 | Not Started | 2022-04-19 | 2022-05-02 | Not Started | 2022-06-08 | Not Started |  |  |  |  | 2022-06-08 | Not Started | 2022-09-20 | Not Started | 2022-10-19 | Not Started | 2022-12-20 | 2022-12-20 | 0 | On/ Ahead Schedule | Not Started | 2022-12-21 | 2023-01-03 | Not Started | 2023-02-09 | Not Started
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 | 5790004 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | PLCRVLLE | Sierra Assets | 0 | 38808 | 38808 | 7.35 | 0 | 7.35 | [5 empty] | 950000 | 0 | 950000 | 12501.4 | 0 | 937498.6 | On/Under Budget | 11.2 | 2.4 | 0 | 2.4 | 0 | 0 | 12283.2 | 218.3 | Project is not in the WP or in 2020 WP | 0 | 231.8 | -231.8 | 231.8 | -231.8 | 75.1 | 71.6 | 71.6 | 2.4 | 2.4 | 2.4 | 2.5 | 2.5 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2022-03-08 | Not Started | 2022-04-13 | 2022-04-19 | Not Started | 2022-04-12 | Not Started | 2022-05-10 | Not Started | 2022-03-09 | 2022-03-09 | Not Started | 2022-03-10 | 2022-03-30 | Not Started | 2022-04-13 | 2022-04-26 | Not Started | 2022-06-02 | Not Started |  |  |  |  | 2022-06-02 | Not Started | 2022-09-14 | Not Started | 2022-10-13 | Not Started | 2022-12-14 | 2022-12-14 | 0 | On/ Ahead Schedule | Not Started | 2022-12-15 | 2022-12-28 | Not Started | 2023-02-03 | Not Started
35173754 | ECOP-BRUNSWICK 1106-H08-LR51486 | E.5030956.01 | 5790001 | UNSE | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 33264 | 33264 | 6.3 | 0 | 6.3 | [5 empty] | 884000 | 0 | 884000 | 24909.4 | 0 | 859090.6 | On/Under Budget | 12075054 | 0 | 0 | 0 | 0 | 0 | 24476 | 433.5 | Project is not in the WP or in 2020 WP | 0 | 433.5 | -433.5 | 433.5 | -433.5 | 148.3 | 142.6 | 142.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3018763.5 | 3018763.5 | 3018763.5 | 3018763.5 | 12075054
35171705 | BR-03-12-W (E) PENTZ RD SRTS PARB |  | 5786123 | UNSE | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 1 | -3894675 | 3894676 | 3875057.5 | 0 | 19618.5 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 3795358.1 | 79699.4 | Project is not in the WP or in 2020 WP | 0 | 79699.4 | -79699.4 | 79699.4 | -79699.4 | 18763.4 | 36769.8 | 24166.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35173253 | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 | E.5015574.03 | 5790582 | UNSE | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  |  | AUBURN | Sierra Assets | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100000 | 0 | 100000 | 512.3 | 0 | 99487.7 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 503.4 | 8.9 | Project is not in the WP or in 2020 WP | 0 | 8.9 | -8.9 | 8.9 | -8.9 | 3.1 | 2.9 | 2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35173255 | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 | E.5015574.02 | 5790581 | UNSE | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  |  | AUBURN | Sierra Assets | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100000 | 0 | 100000 | 1543.5 | 0 | 98456.5 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 1516.5 | 26.9 | Project is not in the WP or in 2020 WP | 0 | 26.9 | -26.9 | 26.9 | -26.9 | 9.3 | 8.8 | 8.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35173320 | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 | E.5015574.05 | 5790538 | UNSE | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  |  | AUBURN | Sierra Assets | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100000 | 0 | 100000 | 512.3 | 0 | 99487.7 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 503.4 | 8.9 | Project is not in the WP or in 2020 WP | 0 | 8.9 | -8.9 | 8.9 | -8.9 | 3.1 | 2.9 | 2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35173321 | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 | E.5015574.04 | 5790539 | UNSE | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  |  | AUBURN | Sierra Assets | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100000 | 0 | 100000 | 512.3 | 0 | 99487.7 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 503.4 | 8.9 | Project is not in the WP or in 2020 WP | 0 | 8.9 | -8.9 | 8.9 | -8.9 | 3.1 | 2.9 | 2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35175549 | BR-05-07-W (E) HIGH SCHOOL MAXWELL PARB |  | 5786123 | UNSE | 08W | VEY1 | Virginia E Stauffer | CJPN | Corina Parker |  |  | Not in the WP |  |  | CHICO | North Valley Assets | [11 empty] | 1 | 1 | 0 | 251.5 | 0 | -251.5 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 247.1 | 4.3 | Project is not in the WP or in 2020 WP | 0 | 4.3 | -4.3 | 4.3 | -4.3 | 1.5 | 1.4 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35175843 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.2 |  | 5790545 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175844 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.3 |  | 5790546 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175845 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.4 |  | 5790547 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175846 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.5 |  | 5790548 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175847 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 |  | 5790549 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 63.4 | Project is not in the WP or in 2020 WP | 0 | 63.4 | -63.4 | 0 | 0
35175848 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.3 |  | 5790550 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175849 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.4 |  | 5790551 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175850 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.5 |  | 5790552 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175852 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.2 |  | 5790553 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | 5790554 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  | SH | AUBURN |  | 0 | 5280 | 5280 | 1 | 0 | 1 | [19 empty] | 18831.7 | Project is not in the WP or in 2020 WP | 0 | 18831.7 | -18831.7 | 0 | 0
35175854 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.4 |  | 5790555 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175855 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.5 |  | 5790556 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175856 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 |  | 5790557 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 2.8 | Project is not in the WP or in 2020 WP | 0 | 2.8 | -2.8 | 0 | 0
35175857 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.3 |  | 5790578 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175858 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.4 |  | 5790579 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175859 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.5 |  | 5790580 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35176209 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.3 |  | 5790542 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35176210 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.4 |  | 5790543 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35176211 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.5 |  | 5790544 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35176497 | ECOP-STANISLAUS 1702-H03-LR1850 |  | 5539421 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | ANGLSCMP |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35176549 | ECOP-MONTE RIO 1113-H07-LR180 |  | 5539421 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | STROSA |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35177107 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.6 |  | 5540299 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35177108 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.7 |  | 5540300 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35177109 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.6 |  | 5540306 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35177110 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.7 |  | 5540307 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35177111 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.8 |  | 5791027 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35167137 | CANCEL DUPLICATE ORDER |  | 5530173 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35181576 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH1 |  | 5791419 | UNSE | 08W | AVP4 | Aaron Patane |  |  |  |  | Not in the WP |  |  | CHICO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 | 5790003 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP | 2022 | SH | PLCRVLLE | Sierra Assets | 0 | 47520 | 47520 | 9 | 0 | 9 | [5 empty] | 950000 | 0 | 950000 | 8444.7 | 0 | 941555.3 | On/Under Budget | 3.8 | 0.8 | 0 | 0.8 | 0 | 0 | 8275.4 | 169.4 | Project is not in the WP or in 2020 WP | 0 | 173.8 | -173.8 | 173.8 | -173.8 | 50.6 | 3891.4 | -3772.6 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2022-03-14 | Not Started | 2022-04-19 | 2022-04-25 | Not Started | 2022-04-18 | Not Started | 2022-05-16 | Not Started | 2022-03-15 | 2022-03-15 | Not Started | 2022-03-16 | 2022-04-05 | Not Started | 2022-04-19 | 2022-05-02 | Not Started | 2022-06-08 | Not Started |  |  |  |  | 2022-06-08 | Not Started | 2022-09-20 | Not Started | 2022-10-19 | Not Started | 2022-12-20 | 2022-12-20 | 0 | On/ Ahead Schedule | Not Started | 2022-12-21 | 2023-01-03 | Not Started | 2023-02-09 | Not Started
35174470 | ECOP-MOLINO 1102-H01-LR318 |  | 5790008 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | STROSA |  | 0 | 13728 | 13728 | 2.6 | 0 | 2.6 | [19 empty] | 148.2 | Project is not in the WP or in 2020 WP | 0 | 148.2 | -148.2 | 0 | 0
35174471 | ECOP-MONTE RIO 1113-H07-LR180 |  | 5539421 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | STROSA |  | 0 | 5280 | 5280 | 1 | 0 | 1 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 |  | 5790006 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | NAPA |  | 0 | 9979.2 | 9979.2 | 1.89 | 0 | 1.89 | [19 empty] | 452.1 | Project is not in the WP or in 2020 WP | 0 | 452.1 | -452.1 | 0 | 0
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 |  | 5790007 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | NAPA |  | 0 | 9610 | 9610 | 1.8201 | 0 | 1.8201 | [19 empty] | 1897.6 | Project is not in the WP or in 2020 WP | 0 | 1897.6 | -1897.6 | 0 | 0
35174474 | ECOP-CALISTOGA 1101-H01-LR736 PH1 |  | 5790104 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | NAPA |  | 0 | 23232 | 23232 | 4.4 | 0 | 4.4 | [19 empty] | 313.5 | Project is not in the WP or in 2020 WP | 0 | 313.5 | -313.5 | 0 | 0
35174475 | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 |  | 5790108 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | NAPA |  | 0 | 15628.8 | 15628.8 | 2.96 | 0 | 2.96 | [19 empty] | 84.4 | Project is not in the WP or in 2020 WP | 0 | 84.4 | -84.4 | 0 | 0
35174476 | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 |  | 5790109 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | STROSA |  | 0 | 46358.4 | 46358.4 | 8.78 | 0 | 8.78 | [19 empty] | 90 | Project is not in the WP or in 2020 WP | 0 | 90 | -90 | 0 | 0
35174477 | ECOP-CALISTOGA 1101-H01-LR736-PH3 |  | 5790110 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | NAPA |  | 0 | 50318.4 | 50318.4 | 9.53 | 0 | 9.53 | [19 empty] | 100.6 | Project is not in the WP or in 2020 WP | 0 | 100.6 | -100.6 | 0 | 0
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | E.5033917.01 | 5790111 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | CLRLAKE | Humboldt Division Assets | 5491.2 | 0 | 5491.2 | 1.04 | 0 | 1.04 |  |  |  |  | GC | 155000 | 0 | 155000 | 13691.3 | 0 | 141308.7 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13691.3 | Request 2021 Budget | 0 | 13691.3 | -13691.3 | 13691.3 | -13691.3 | 0 | 9372.6 | 4318.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-12-20 | Not Started | 2021-12-21 | 2021-12-27 | Not Started |  |  | 2022-03-14 | Not Started | 2022-07-05 | 2022-07-05 | Not Started | [6 empty] | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-28 | Not Started | 2022-11-01 | Not Started |  |  | 2022-12-20 | Not Started | 2022-12-20 | 2022-12-20 | 0 | On/ Ahead Schedule | Not Started |  |  |  | 2023-09-12 | Not Started
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | E.5033918.01 | 5790119 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | CLRLAKE | Humboldt Division Assets | 0 | 3761 | 3761 | 0.71231 | 0 | 0.71231 | [5 empty] | 67857 | 0 | 67857 | 24457.4 | 0 | 43399.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 13053 | 11404.4 | Request 2021 Budget | 0 | 11404.4 | -11404.4 | 11404.4 | -11404.4 | 696.5 | 8559.7 | 2148.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2022-01-03 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2022-01-04 | 2022-01-04 | Not Started | 2022-01-05 | 2022-01-25 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | 5790112 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | 2022 |  | SH | CLRLAKE |  | 21597 | 0 | 21597 | 4.0903 | 0 | 4.0903 |  |  |  |  | GC | [14 empty] | 16102.4 | Request 2021 Budget | 0 | 16102.4 | -16102.4 | 0 | 0 | [25 empty] | 2021-03-19 |  |  |  |  | 2021-12-20 | Not Started | 2021-12-21 | 2021-12-27 | Not Started |  |  | 2022-01-17 | Not Started | 2022-07-05 | 2022-09-30 | Not Started | [6 empty] | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-28 | Not Started | 2022-11-01 | Not Started |  |  | 2022-12-20 | Not Started | 2022-12-20 | 2022-12-20 | 0 | On/ Ahead Schedule | Not Started |  |  |  | 2023-09-12 | Not Started
35174993 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.2 |  | 5790541 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 |  | 5792071 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | NAPA | [26 empty] | 186.4 | Project is not in the WP or in 2020 WP | 0 | 186.4 | -186.4 | 0 | 0
35192025 | ECOP - FORESTHILL 1101 - H02-LR1802 PH1 |  | 5792058 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | AUBURN | [26 empty] | 51.2 | Project is not in the WP or in 2020 WP | 0 | 51.2 | -51.2 | 0 | 0
35192028 | ECOP - FORESTHILL 1101 - H02-LR1802 PH2 |  | 5792059 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | AUBURN | [26 empty] | 27.7 | Project is not in the WP or in 2020 WP | 0 | 27.7 | -27.7 | 0 | 0
35192029 | ECOP - FORESTHILL 1101 - H02-LR1802 PH3 |  | 5792060 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | AUBURN | [26 empty] | 35.4 | Project is not in the WP or in 2020 WP | 0 | 35.4 | -35.4 | 0 | 0
35192031 | ECOP - COLUMBIA HILL 1101 - H01-LR35424 |  | 5792070 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [26 empty] | 68 | Project is not in the WP or in 2020 WP | 0 | 68 | -68 | 0 | 0
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 |  | 5792076 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | PLCRVLLE | [26 empty] | 39 | Project is not in the WP or in 2020 WP | 0 | 39 | -39 | 0 | 0
35192035 | ECOP - MIRABEL 1101 - H01-LR298 |  | 5792065 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | STROSA | [26 empty] | 27.5 | Project is not in the WP or in 2020 WP | 0 | 27.5 | -27.5 | 0 | 0
35192036 | ECOP - RINCON 1103 - H01-LR474 |  | 5792069 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | STROSA | [26 empty] | 74.1 | Project is not in the WP or in 2020 WP | 0 | 74.1 | -74.1 | 0 | 0
35192037 | ECOP - SILVERADO 2105 - H01-LR1421 |  | 5792078 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | NAPA | [26 empty] | 130.8 | Project is not in the WP or in 2020 WP | 0 | 130.8 | -130.8 | 0 | 0
35192039 | ECOP - MONTE RIO 1113 - H04-LR320 |  | 5792080 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | STROSA | [26 empty] | 41.7 | Project is not in the WP or in 2020 WP | 0 | 41.7 | -41.7 | 0 | 0
35192040 | ECOP - MONTE RIO 1113 - H08-LR477 |  | 5792084 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | STROSA | [26 empty] | 38.8 | Project is not in the WP or in 2020 WP | 0 | 38.8 | -38.8 | 0 | 0
35192041 | ECOP - WEST POINT 1101 - H01-LR4706 |  | 5792061 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | JACKSON | [26 empty] | 129.6 | Project is not in the WP or in 2020 WP | 0 | 129.6 | -129.6 | 0 | 0
35192043 | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 |  | 5792066 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | JACKSON |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 76.2 | Project is not in the WP or in 2020 WP | 0 | 76.2 | -76.2 | 0 | 0
35192044 | ECOP - PINE GROVE 1102 - H03-LR13438 PH2 |  | 5792067 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | JACKSON | [26 empty] | 82.6 | Project is not in the WP or in 2020 WP | 0 | 82.6 | -82.6 | 0 | 0
35192045 | ECOP - STANISLAUS 1702 - H02-LR75348 |  | 5792068 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | ANGLSCMP | [26 empty] | 61.6 | Project is not in the WP or in 2020 WP | 0 | 61.6 | -61.6 | 0 | 0
35192046 | ECOP - PINE GROVE 1102 - H04-LR3172 PH1 |  | 5792072 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | JACKSON | [26 empty] | 90.3 | Project is not in the WP or in 2020 WP | 0 | 90.3 | -90.3 | 0 | 0
35192047 | ECOP - PINE GROVE 1102 - H04-LR3172 PH2 |  | 5792073 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | JACKSON | [26 empty] | 100.9 | Project is not in the WP or in 2020 WP | 0 | 100.9 | -100.9 | 0 | 0
35192048 | ECOP - PINE GROVE 1102 - H04-LR3172 PH3 |  | 5792074 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | JACKSON | [26 empty] | 94.3 | Project is not in the WP or in 2020 WP | 0 | 94.3 | -94.3 | 0 | 0
35192049 | ECOP - PINE GROVE 1102 - H04-LR3172 PH4 |  | 5792075 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | JACKSON | [26 empty] | 86.9 | Project is not in the WP or in 2020 WP | 0 | 86.9 | -86.9 | 0 | 0
35192050 | ECOP - WEST POINT 1102 - H01-TS1303 |  | 5792077 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | JACKSON | [26 empty] | 32 | Project is not in the WP or in 2020 WP | 0 | 32 | -32 | 0 | 0
35192051 | ECOP - SALT SPRINGS 2102 - H01-LR4796 |  | 5792079 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | ANGLSCMP | [26 empty] | 41.7 | Project is not in the WP or in 2020 WP | 0 | 41.7 | -41.7 | 0 | 0
35192052 | ECOP - WEST POINT 1102 - H05-LR34416 |  | 5792081 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | JACKSON | [26 empty] | 36.6 | Project is not in the WP or in 2020 WP | 0 | 36.6 | -36.6 | 0 | 0
35181939 | WD RECONDUCTORING ON WYANDOTTE 1103 |  | 5791278 | UNSE | 08W | MTTA | Musie Tsegay Tesfasilassie |  |  |  |  | Not in the WP |  |  | OROVILLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35185714 | WDDB - OTTER 1102 - LR 2002 |  | 5791660 | UNSE | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | MONTEREY | [26 empty] | 32 | Project is not in the WP or in 2020 WP | 0 | 32 | -32 | 0 | 0
35191130 | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 |  | 5792200 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | NAPA |  | 0 | 42768 | 42768 | 8.1 | 0 | 8.1 | [19 empty] | 122.3 | Project is not in the WP or in 2020 WP | 0 | 122.3 | -122.3 | 0 | 0
35191311 | ECOP - MONTE RIO 1113 - H06-LR8299 |  | 5541300 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | STROSA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35191313 | ECOP - MONTE RIO 1113 - H06-LR8299 |  | 5541301 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | STROSA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35191316 | ECOP - OAKHURST 1103 - H01-LR10190 |  | 5541302 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | OAKHURST | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35191317 | ECOP - BRUNSWICK 1106 - H03 - LR4639 |  | 5541304 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | E.5034355.01 | 5541305 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | SNRAFAEL | North Bay Assets | 6177.6 | 0 | 6177.6 | 1.17 | 0 | 1.17 |  |  |  |  | Contract | 312500 | 0 | 312500 | 18667 | 0 | 293833 | On/Under Budget | 0 | 0 | 389.6 | -389.6 | 0 | 0 | 7395.4 | 11661.2 | Request 2021 Budget | 0 | 11271.6 | -11271.6 | 11271.6 | -11271.6 | 9867.7 | -328.6 | 1732.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156498 | BL-A | BL-A 35191319_ECOP - LAS GALLINAS A 1105 - H01-LR99904_08W - DD 210219 Feb. 2021 | 2021-03-01 | 2021-06-24 | Not Started | 2021-09-10 | 2021-09-16 | Not Started | 2021-09-09 | Not Started | 2021-10-07 | Not Started | 2021-06-25 | 2021-06-25 | Not Started | 2021-06-28 | 2021-07-16 | Not Started | 2021-09-10 | 2021-09-23 | Not Started | 2021-11-01 | Not Started | 2021-11-01 | Not Started | 2021-11-12 | Not Started | 2021-11-01 | Not Started | 2022-02-11 | Not Started | 2022-03-14 | Not Started | 2022-03-28 | 2022-05-13 | -46 | Behind Schedule | Not Started | 2022-05-16 | 2022-05-27 | Not Started | 2022-07-12 | Not Started
35191380 | ECOP - MIWUK 1702 - H02-LR9270 |  | 5541306 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | SONORA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35191381 | ECOP - MIWUK 1702 - H03-LR9270 |  | 5541307 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | SONORA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35191382 | ECOP - MORAGA 1105 - H01-CB |  | 5541308 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | WALNTCRK | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35191930 | ECOP - WOODACRE 1101 - H01-LR404 PH1 |  | 5792062 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | SNRAFAEL | [26 empty] | 81.4 | Project is not in the WP or in 2020 WP | 0 | 81.4 | -81.4 | 0 | 0
35191934 | ECOP - WOODACRE 1101 - H01-LR404 PH2 |  | 5792063 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | SNRAFAEL | [26 empty] | 58.6 | Project is not in the WP or in 2020 WP | 0 | 58.6 | -58.6 | 0 | 0
35192054 | ECOP-OAKHURST 1103-LR 5470 |  | 5792083 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | OAKHURST | [26 empty] | 104.3 | Project is not in the WP or in 2020 WP | 0 | 104.3 | -104.3 | 0 | 0
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | E.5034400.01 | 5792091 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | CONCORD | Diablo Assets | 7075.2 | 0 | 7075.2 | 1.34 | 0 | 1.34 |  |  |  |  | GC | 550000 | 0 | 550000 | 43392.8 | 0 | 506607.2 | On/Under Budget | 20977 | 32279.8 | 97.2 | 32182.6 | 0 | 0 | 8804.8 | 34685.3 | Request 2021 Budget | 0 | 89980.9 | -89980.9 | 87844.9 | -87844.9 | 7595 | 21330 | 5663.1 | 32279.8 | 20977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157128 | BL-A | BL-A ECOP - CLAYTON 2212 - H01-LR2951 - Mar. 2021 | 2021-03-07 | 2021-09-27 | Not Started | 2022-04-26 | 2022-05-02 | Not Started | 2022-04-25 | Not Started | 2022-05-23 | Not Started | 2021-09-28 | 2021-09-28 | Not Started | 2021-09-29 | 2021-10-19 | Not Started | 2022-05-24 | 2022-06-13 | Not Started | 2022-06-22 | Not Started | 2022-06-22 | Not Started | 2022-09-16 | Not Started | 2022-06-22 | Not Started | 2022-09-16 | Not Started | 2022-09-23 | Not Started | 2023-01-20 | 2023-01-20 | 0 | On/ Ahead Schedule | Not Started | 2023-01-23 | 2023-02-03 | Not Started | 2023-04-14 | Not Started
35192293 | ECOP - MOLINO 1102 - H03-LR396 PH1 |  | 5792100 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | STROSA | [26 empty] | 27.8 | Project is not in the WP or in 2020 WP | 0 | 27.8 | -27.8 | 0 | 0
35192294 | ECOP - MOLINO 1102 - H03-LR396 PH2 |  | 5792101 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | STROSA | [26 empty] | 27.5 | Project is not in the WP or in 2020 WP | 0 | 27.5 | -27.5 | 0 | 0
35192295 | ECOP - RINCON 1103 - H02-LR198 |  | 5792104 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | STROSA | [26 empty] | 27.7 | Project is not in the WP or in 2020 WP | 0 | 27.7 | -27.7 | 0 | 0
35192296 | ECOP - PINE GROVE 1102 - H06-LR83098 |  | 5792102 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | JACKSON | [26 empty] | 30.5 | Project is not in the WP or in 2020 WP | 0 | 30.5 | -30.5 | 0 | 0
35192297 | ECOP - PINE GROVE 1102 - H07-CB |  | 5792103 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | JACKSON | [26 empty] | 30.4 | Project is not in the WP or in 2020 WP | 0 | 30.4 | -30.4 | 0 | 0
35192298 | ECOP - SALT SPRINGS 2102 - H02-LR37300 |  | 5792105 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | ANGLSCMP | [26 empty] | 27.7 | Project is not in the WP or in 2020 WP | 0 | 27.7 | -27.7 | 0 | 0
35192299 | ECOP - SALT SPRINGS 2102 - H04-LR97924 |  | 5792106 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | ANGLSCMP | [26 empty] | 27.5 | Project is not in the WP or in 2020 WP | 0 | 27.5 | -27.5 | 0 | 0
35192300 | ECOP - WEST POINT 1101 - H04-TSL3355 |  | 5792108 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | JACKSON | [26 empty] | 34.7 | Project is not in the WP or in 2020 WP | 0 | 34.7 | -34.7 | 0 | 0
35192301 | ECOP - WEST POINT 1102 - H06-LR36676 |  | 5792109 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | JACKSON | [26 empty] | 27.5 | Project is not in the WP or in 2020 WP | 0 | 27.5 | -27.5 | 0 | 0
35192302 | ECOP - WEST POINT 1102 - H07-LR93116 |  | 5792110 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | JACKSON | [26 empty] | 27.5 | Project is not in the WP or in 2020 WP | 0 | 27.5 | -27.5 | 0 | 0
35192303 | ECOP - MARIPOSA 2101 - H01-LR10170 PH1 |  | 5792095 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | MARIPOSA | [26 empty] | 27.5 | Project is not in the WP or in 2020 WP | 0 | 27.5 | -27.5 | 0 | 0
35192304 | ECOP - MARIPOSA 2101 - H01-LR10170 PH2 |  | 5792096 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | MARIPOSA | [26 empty] | 27.5 | Project is not in the WP or in 2020 WP | 0 | 27.5 | -27.5 | 0 | 0
35192305 | ECOP - MIWUK 1702 - H01-LR8130 |  | 5792099 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | SONORA | [26 empty] | 27.5 | Project is not in the WP or in 2020 WP | 0 | 27.5 | -27.5 | 0 | 0
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | E.5034407.01 | 5792098 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 10771 | 0 | 10771 | 2.04 | 0 | 2.04 |  |  |  |  | GC | 950000 | 950000 | 0 | 22247.1 | 0 | -22247.1 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 8393.2 | 13853.9 | Request 2021 Budget | 0 | 13853.9 | -13853.9 | 13853.9 | -13853.9 | 8265.2 | 4650.4 | 938.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157814 | BL-A | BL-A 35192282_ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-24 | Not Started | 2021-06-29 | 2021-07-05 | Not Started | 2021-06-28 | Not Started | 2021-07-26 | Not Started | 2021-05-25 | 2021-05-25 | Not Started | 2021-05-26 | 2021-06-15 | Not Started | 2021-06-29 | 2021-07-12 | Not Started | 2021-08-18 | Not Started | 2021-08-18 | Not Started | 2021-08-31 | Not Started | 2021-08-18 | Not Started | 2021-11-30 | Not Started | 2021-12-29 | Not Started | 2022-03-28 | 2022-03-01 | 27 | On/ Ahead Schedule | Not Started | 2022-03-02 | 2022-03-15 | Not Started | 2022-04-28 | Not Started
35192283 | ECOP - CALISTOGA 1101 - H04-LR1087 |  | 5792090 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | NAPA | [26 empty] | 27.5 | Project is not in the WP or in 2020 WP | 0 | 27.5 | -27.5 | 0 | 0
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | E.5034416.01 | 5792107 | UNSE | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 |  | SH | NAPA | North Bay Assets | 10929.6 | 0 | 10929.6 | 2.07 | 0 | 2.07 |  |  |  |  | Contract | 190000 | 0 | 190000 | 50755 | 0 | 139245 | On/Under Budget | 10554.1 | 127518 | 0 | 127518 | 0 | 0 | 9858.5 | 40896.5 | Request 2021 Budget | 0 | 178968.5 | -178968.5 | 178968.5 | -178968.5 | 3968.9 | 3216.5 | 33711.1 | 127518 | 3518 | 3518 | 3518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-07 | Not Started | 2021-07-08 | 2021-07-14 | Not Started | 2021-07-07 | Not Started | 2021-08-04 | Not Started | 2021-05-07 | 2021-05-07 | Not Started | 2021-05-10 | 2021-05-28 | Not Started | 2021-07-01 | 2021-07-14 | Not Started | 2021-08-24 | Not Started | 2021-08-24 | Not Started | 2021-09-06 | Not Started | 2021-08-24 | Not Started | 2021-12-27 | Not Started | 2022-01-25 | Not Started | 2022-03-28 | 2022-03-28 | 0 | On/ Ahead Schedule | Not Started | 2022-03-29 | 2022-04-11 | Not Started | 2022-05-25 | Not Started
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 |  | 5792085 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [26 empty] | 32 | Project is not in the WP or in 2020 WP | 0 | 32 | -32 | 0 | 0
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 |  | 5792086 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [26 empty] | 38.9 | Project is not in the WP or in 2020 WP | 0 | 38.9 | -38.9 | 0 | 0
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB |  | 5792087 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [26 empty] | 32 | Project is not in the WP or in 2020 WP | 0 | 32 | -32 | 0 | 0
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 |  | 5792088 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [26 empty] | 32 | Project is not in the WP or in 2020 WP | 0 | 32 | -32 | 0 | 0
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 |  | 5792089 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [26 empty] | 4.5 | Project is not in the WP or in 2020 WP | 0 | 4.5 | -4.5 | 0 | 0
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | E.5034785.01 | 5795129 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | SNRAFAEL | North Bay Assets | 8606.4 | 0 | 8606.4 | 1.63 | 0 | 1.63 |  |  |  |  | Contract | 312500 | 0 | 312500 | 2885.1 | 0 | 309614.9 | On/Under Budget | 284.8 | 32.9 | 129.6 | -96.7 | 0 | 0 | 0 | 3014.7 | Request 2021 Budget | 0 | 3185.4 | -3185.4 | 3185.4 | -3185.4 | 0 | 698 | 2187.1 | 32.9 | 32.9 | 32.9 | 33.6 | 33.6 | 33.6 | 33.6 | 33.6 | 33.6 | 17.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.4 | 2021-04-02 | 156499 | BL-A | BL-A 35223615_ECOP - LAS GALLINAS A 1105 Ph 2_08W - DD 210219 Feb. 2021 | 2021-03-01 | 2021-06-24 | Not Started | 2021-10-22 | 2021-10-28 | Not Started | 2021-10-21 | Not Started | 2021-11-18 | Not Started | 2021-06-25 | 2021-06-25 | Not Started | 2021-06-28 | 2021-07-16 | Not Started | 2021-09-10 | 2021-09-23 | Not Started | 2021-12-13 | Not Started | 2021-12-13 | Not Started | 2021-12-24 | Not Started | 2021-12-13 | Not Started | 2022-03-25 | Not Started | 2022-04-25 | Not Started | 2022-03-28 | 2022-06-24 | -88 | Behind Schedule | Not Started | 2022-06-27 | 2022-07-08 | Not Started | 2022-08-23 | Not Started
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE |  | 5795062 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | NAPA |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 117.7 | Project is not in the WP or in 2020 WP | 0 | 117.7 | -117.7 | 0 | 0
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | E.5034784.01.01 | 5795128 | UNSE | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2022 |  | SH | REDBLUFF | North Valley Assets | 0 | 12302.4 | 12302.4 | 2.33 | 0 | 2.33 |  |  |  |  | GC | 1 | 1 | 0 | 32992.2 | 0 | -32992.2 | OverRun | 0 | 0 | -25292.3 | 25292.3 | 0 | 0 | 0 | 7699.8 | Request 2021 Budget | 0 | 32992.1 | -32992.1 | 32992.1 | -32992.1 | 1790.5 | 3189.5 | 28012.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | E.5034778.01.01 | 5795018 | UNSE | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  | SH | PLCRVLLE | Sierra Assets | 739 | 0 | 739 | 0.13996 | 0 | 0.13996 | [5 empty] | 320000 | 320000 | 0 | 6546.6 | 0 | -6546.6 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6546.7 | Project is not in the WP or in 2020 WP | 0 | 6546.7 | -6546.7 | 6546.7 | -6546.7 | 93.8 | 3943.5 | 2509.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | E.5034707.01.02 | 5794545 | UNSE | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | VACAVLLE | Sacramento Assets | 0 | 16579.2 | 16579.2 | 3.14 | 0 | 3.14 | [5 empty] | 1 | 1 | 0 | 15197.1 | 0 | -15197.1 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15197.2 | Project is not in the WP or in 2020 WP | 0 | 15197.2 | -15197.2 | 15197.2 | -15197.2 | 1383.5 | 13304.9 | 508.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2022 | 2022 | SH | CHICO | North Valley Assets | 9134.4 | 0 | 9134.4 | 1.73 | 0 | 1.73 |  |  |  |  | GC | 400000 | 0 | 400000 | 5580.4 | 0 | 394419.6 | On/Under Budget | 387291 | 0 | 0 | 0 | 0 | 0 | 0 | 5580.4 | Budget Allocated | 400000 | 492871.4 | -92871.4 | 392871.4 | 7128.6 | 0 | 2617.6 | 2962.8 | 0 | 200000 | 187291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-05 | 157967 | BL-A1 | BL-A1_35224712_SH - BUCKS CREEK 1101 CB PH 2_08W_Mar.2021 | 2021-03-23 | 2021-05-28 | Not Started | 2022-01-11 | 2022-01-17 | Not Started | 2022-01-10 | Not Started | 2022-02-07 | Not Started | 2021-05-31 | 2021-05-31 | Not Started | 2021-06-01 | 2021-06-21 | Not Started | 2021-07-12 | 2021-07-23 | Not Started | 2022-03-02 | Not Started | 2022-03-02 | Not Started | 2022-03-15 | Not Started | 2022-03-02 | Not Started | 2022-06-14 | Not Started | 2022-07-13 | Not Started | 2022-12-30 | 2022-09-13 | 108 | On/ Ahead Schedule | Not Started | 2022-09-14 | 2022-09-27 | Not Started | 2022-11-10 | Not Started
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2022 | 2022 | SH | CHICO | North Valley Assets | 9662.4 | 0 | 9662.4 | 1.83 | 0 | 1.83 |  |  |  |  | GC | 400000 | 0 | 400000 | 2212.6 | 0 | 397787.4 | On/Under Budget | 387815 | 0 | 0 | 0 | 0 | 0 | 0 | 2212.6 | Budget Allocated | 400000 | 490027.6 | -90027.6 | 390027.6 | 9972.4 | 0 | 2094.1 | 118.5 | 0 | 200000 | 187815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-05 | 157968 | BL-A1 | BL-A1_35224713_SH - BUCKS CREEK 1101 CB PH 3_08W_Mar.2021 | 2021-03-23 | 2021-05-28 | Not Started | 2022-01-11 | 2022-01-17 | Not Started | 2022-01-10 | Not Started | 2022-02-07 | Not Started | 2021-05-31 | 2021-05-31 | Not Started | 2021-06-01 | 2021-06-21 | Not Started | 2021-07-19 | 2021-07-30 | Not Started | 2022-03-02 | Not Started | 2022-03-02 | Not Started | 2022-03-15 | Not Started | 2022-03-02 | Not Started | 2022-06-14 | Not Started | 2022-07-13 | Not Started | 2022-12-16 | 2022-09-13 | 94 | On/ Ahead Schedule | Not Started | 2022-09-14 | 2022-09-27 | Not Started | 2022-11-10 | Not Started
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | E.5034609.01.02 | 5794206 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 4699.2 | 4699.2 | 0.89 | 0 | 0.89 |  |  |  |  | GC | 316666 | 0 | 316666 | 26883.8 | 0 | 289782.2 | On/Under Budget | 10554.1 | 3518 | -24570 | 28088 | 0 | 0 | 0 | 2313.8 | Request 2021 Budget | 0 | 40955.8 | -40955.8 | 40955.8 | -40955.8 | 0 | 31739.7 | -4855.9 | 3518 | 3518 | 3518 | 3518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157800 | BL-A | BL-A 35225589_CWSP - KONOCTI 1102 LR 965078 PH2_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-24 | Not Started | 2021-08-31 | 2021-09-06 | Not Started | 2021-08-30 | Not Started | 2021-09-27 | Not Started | 2021-05-25 | 2021-05-25 | Not Started | 2021-05-26 | 2021-06-15 | Not Started | 2021-08-31 | 2021-09-13 | Not Started | 2021-10-20 | Not Started | 2021-10-20 | Not Started | 2021-11-02 | Not Started | 2021-10-20 | Not Started | 2022-02-01 | Not Started | 2022-03-02 | Not Started | 2022-06-03 | 2022-05-03 | 31 | On/ Ahead Schedule | Not Started | 2022-05-04 | 2022-05-17 | Not Started | 2022-06-30 | Not Started
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | E.5034609.01.03 | 5794206 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 4224 | 4224 | 0.8 | 0 | 0.8 |  |  |  |  | GC | 316666 | 0 | 316666 | 26393.4 | 0 | 290272.6 | On/Under Budget | 10554.1 | 3518 | -24570 | 28088 | 0 | 0 | 0 | 1823.3 | Request 2021 Budget | 0 | 40465.3 | -40465.3 | 40465.3 | -40465.3 | 0 | 28530 | -2136.7 | 3518 | 3518 | 3518 | 3518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157815 | BL-A | BL-A 35225591_CWSP - KONOCTI 1102 LR 965078 PH3_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-10 | Not Started | 2021-05-25 | 2021-05-31 | Not Started | 2021-05-24 | Not Started | 2021-07-05 | Not Started | 2021-05-11 | 2021-05-11 | Not Started | 2021-05-12 | 2021-06-01 | Not Started | 2021-05-25 | 2021-06-07 | Not Started | 2021-07-28 | Not Started | 2021-07-28 | Not Started | 2021-08-10 | Not Started | 2021-07-28 | Not Started | 2021-11-09 | Not Started | 2021-12-08 | Not Started | 2022-02-03 | 2022-02-08 | -5 | Behind Schedule | Not Started | 2022-02-09 | 2022-02-22 | Not Started | 2022-04-07 | Not Started
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | 5794988 | UNSE | 08W | JDLM | Jesse Lorz |  |  |  |  | Not in the WP |  | SH | JACKSON |  | 2428.8 | 0 | 2428.8 | 0.46 | 0 | 0.46 | [19 empty] | 9004.5 | Project is not in the WP or in 2020 WP | 0 | 9004.5 | -9004.5 | 0 | 0
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2022 |  | SH | OROVILLE | North Valley Assets | 4065.6 | 0 | 4065.6 | 0.77 | 0 | 0.77 | [5 empty] | 950000 | 0 | 950000 | 25393.1 | 0 | 924606.9 | On/Under Budget | 0 | 0 | 393.8 | -393.8 | 0 | 0 | 0 | 25786.8 | Request 2021 Budget | 0 | 514982 | -514982 | 25393 | -25393 | 330.9 | 10083.3 | 14978.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158071 | BL-A_ | BL-A_35223039_PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE_08W_Mar.2021 | 2021-03-29 | 2021-06-14 | Not Started | 2021-07-13 | 2021-07-19 | Not Started | 2021-07-12 | Not Started | 2021-08-09 | Not Started | 2021-06-15 | 2021-06-15 | Not Started | 2021-06-16 | 2021-07-06 | Not Started | 2021-07-13 | 2021-07-26 | Not Started | 2021-09-01 | Not Started | 2021-09-01 | Not Started | 2021-09-14 | Not Started | 2021-09-01 | Not Started | 2021-10-26 | Not Started | 2021-11-24 | Not Started | 2022-01-19 | 2022-01-13 | 6 | On/ Ahead Schedule | Not Started | 2022-01-14 | 2022-01-27 | Not Started | 2022-03-14 | Not Started
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | 5794984 | UNSE | 08W | JDLM | Jesse Lorz |  |  |  |  | Not in the WP |  | SH | GRSSVLLY |  | 9187.2 | 0 | 9187.2 | 1.74 | 0 | 1.74 | [19 empty] | 5107.4 | Project is not in the WP or in 2020 WP | 0 | 5107.4 | -5107.4 | 0 | 0
35219269 | CWSP - VACA DIXON 110540092 |  | 5794542 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | VACAVLLE |  | 0 | 122337.6 | 122337.6 | 23.17 | 0 | 23.17 | [19 empty] | 25369.2 | Project is not in the WP or in 2020 WP | 0 | 25369.2 | -25369.2 | 0 | 0
35222233 | NULL PM |  | 5794900 | UNSE | 08W | JSZ2 | Jan Salim Zafar |  |  |  |  | Not in the WP |  |  | DINUBA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | E.5034610.01.02 | 5794205 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 10190 | 0 | 10190 | 1.9299 | 0 | 1.9299 |  |  |  |  | GC | 1 | 1 | 0 | 16985.4 | 0 | -16985.4 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16985.4 | Request 2021 Budget | 0 | 16985.4 | -16985.4 | 16985.4 | -16985.4 | 8383.6 | 5521.5 | 3080.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157816 | BL-A | BL-A 35220895_CWSP - MIDDLETOWN 1103 - LR 830 PH2.1_08W - DD 210305 Mar. 2021 | 2021-03-19 | 2021-05-21 | Not Started | 2021-06-28 | 2021-07-02 | Not Started | 2021-06-25 | Not Started | 2021-07-23 | Not Started | 2021-05-24 | 2021-05-24 | Not Started | 2021-05-25 | 2021-06-14 | Not Started | 2021-06-28 | 2021-07-09 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-30 | Not Started | 2021-08-17 | Not Started | 2021-11-29 | Not Started | 2021-12-28 | Not Started | 2022-02-24 | 2022-02-28 | -4 | Behind Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-04-27 | Not Started
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | E.5034610.01.03 | 5794205 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 1478 | 0 | 1478 | 0.27992 | 0 | 0.27992 | [5 empty] | 1 | 1 | 0 | 8339.9 | 0 | -8339.9 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8339.9 | Request 2021 Budget | 0 | 8339.9 | -8339.9 | 8339.9 | -8339.9 | 3718.1 | 3545.7 | 1076.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157802 | BL-A | BL-A 35220896_CWSP - MIDDLETOWN 1103 - LR 830 PH3.1_08W - DD 210305 Mar. 2021 | 2021-03-19 | 2021-07-29 | Not Started | 2021-11-26 | 2021-12-02 | Not Started | 2021-11-25 | Not Started | 2021-12-23 | Not Started | 2021-07-30 | 2021-07-30 | Not Started | 2021-08-02 | 2021-08-20 | Not Started | 2021-11-26 | 2021-12-09 | Not Started | 2022-01-17 | Not Started | 2022-01-17 | Not Started | 2022-01-28 | Not Started | 2022-01-17 | Not Started | 2022-04-29 | Not Started | 2022-05-30 | Not Started | 2022-07-29 | 2022-07-29 | 0 | On/ Ahead Schedule | Not Started | 2022-08-01 | 2022-08-12 | Not Started | 2022-09-27 | Not Started
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | 5794202 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | SNCARLOS |  | 0 | 5016 | 5016 | 0.95 | 0 | 0.95 | [19 empty] | 8096.4 | Project is not in the WP or in 2020 WP | 0 | 8096.4 | -8096.4 | 0 | 0
35223024 | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | E.5034767.01.01 | 5794998 | UNSE | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 |  | SH | NAPA | North Bay Assets | 11827.2 | 0 | 11827.2 | 2.24 | 0 | 2.24 |  |  |  |  | Contract | 190000 | 0 | 190000 | 0 | 0 | 190000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-06-30 | Not Started |  |  | Not Started | 2021-07-16 | Not Started | 2021-08-12 | Not Started | [9 empty] | 2021-09-14 | Not Started | [8 empty] | 2022-01-10 | Not Started | 2022-01-18 | 2022-01-18 | 0 | On/ Ahead Schedule | Not Started | 2022-01-11 | 2022-01-18 | Not Started | 2022-09-21 | Not Started
35223026 | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | E.5034767.01.02 | 5794998 | UNSE | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 |  | SH | NAPA | North Bay Assets | 9504 | 0 | 9504 | 1.8 | 0 | 1.8 |  |  |  |  | Contract | 190000 | 0 | 190000 | 0 | 0 | 190000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-07-14 | Not Started |  |  | Not Started | 2021-07-23 | Not Started | 2021-08-12 | Not Started | [9 empty] | 2021-08-31 | Not Started | [8 empty] | 2021-12-27 | Not Started | 2022-01-03 | 2022-01-03 | 0 | On/ Ahead Schedule | Not Started | 2021-12-28 | 2022-01-03 | Not Started | 2022-09-07 | Not Started
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | 5794900 | UNSE | 08W | JSZ2 | Jan Salim Zafar |  |  |  |  | Not in the WP |  | SH | DINUBA |  | 0 | 13728 | 13728 | 2.6 | 0 | 2.6 | [19 empty] | 27810.5 | Project is not in the WP or in 2020 WP | 0 | 27810.5 | -27810.5 | 0 | 0
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2022 | 2021 | SH | OROVILLE | North Valley Assets | 3009.6 | 0 | 3009.6 | 0.57 | 0 | 0.57 | [5 empty] | 950000 | 0 | 950000 | 34141.7 | 0 | 915858.3 | On/Under Budget | 0 | 0 | 387.1 | -387.1 | 0 | 0 | 0 | 34528.8 | Request 2021 Budget | 0 | 521271.7 | -521271.7 | 34141.7 | -34141.7 | 237.1 | 12632.9 | 21271.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157966 | BL-A_ | BL-A_35223030_PSPS - BANGOR 1101 CB - MICROGRID_08W_Mar.2021 | 2021-03-23 | 2021-07-12 | Not Started | 2021-08-02 | 2021-08-06 | Not Started | 2021-07-30 | Not Started | 2021-08-27 | Not Started | 2021-07-13 | 2021-07-13 | Not Started | 2021-07-14 | 2021-08-03 | Not Started | 2021-07-20 | 2021-08-02 | Not Started | 2021-09-21 | Not Started | 2021-09-21 | Not Started | 2021-10-04 | Not Started | 2021-09-21 | Not Started | 2022-01-03 | Not Started | 2022-02-01 | Not Started | 2022-12-30 | 2022-04-04 | 270 | On/ Ahead Schedule | Not Started | 2022-04-05 | 2022-04-18 | Not Started | 2022-06-01 | Not Started
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | E.5034758.01.01 | 5794982 | UNSE | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2021 |  | SH | AUBURN | Sierra Assets | 2323.2 | 0 | 2323.2 | 0.44 | 0 | 0.44 | [5 empty] | 500000 | 0 | 500000 | 9981 | 0 | 490019 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9981.1 | Request 2021 Budget | 0 | 9981.1 | -9981.1 | 9981.1 | -9981.1 | 371 | 8951 | 659.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-07-12 | Not Started | 2021-08-17 | 2021-08-23 | Not Started | 2021-08-16 | Not Started | 2021-09-13 | Not Started | 2021-07-13 | 2021-07-13 | Not Started | 2021-07-14 | 2021-08-03 | Not Started | 2021-08-17 | 2021-08-30 | Not Started | 2021-10-06 | Not Started | 2021-10-06 | Not Started | 2021-10-19 | Not Started | 2021-10-06 | Not Started | 2022-01-18 | Not Started | 2022-02-16 | Not Started | 2022-04-19 | 2022-04-19 | 0 | On/ Ahead Schedule | Not Started | 2022-04-20 | 2022-05-03 | Not Started | 2022-06-16 | Not Started
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | E.5034759.01.01 | 5794983 | UNSE | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2022 |  | SH | GRSSVLLY | Sierra Assets | 264 | 0 | 264 | 0.05 | 0 | 0.05 | [5 empty] | 500000 | 0 | 500000 | 6215 | 0 | 493785 | On/Under Budget | 0 | 0 | 268.9 | -268.9 | 0 | 0 | 0 | 6483.9 | Budget Allocated | 110970 | 90017.5 | 20952.5 | 6215 | 104755 | 274.8 | 4562.6 | 1377.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-08-10 | Not Started | 2021-09-15 | 2021-09-21 | Not Started | 2021-09-14 | Not Started | 2021-10-12 | Not Started | 2021-08-11 | 2021-08-11 | Not Started | 2021-08-12 | 2021-09-01 | Not Started | 2021-09-15 | 2021-09-28 | Not Started | 2021-11-04 | Not Started | 2021-11-04 | Not Started | 2021-11-17 | Not Started | 2021-11-04 | Not Started | 2022-02-16 | Not Started | 2022-03-17 | Not Started | 2022-05-18 | 2022-05-18 | 0 | On/ Ahead Schedule | Not Started | 2022-05-19 | 2022-06-01 | Not Started | 2022-07-15 | Not Started
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | E.5034762.01.01 | 5794986 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | NAPA | North Bay Assets | 950.4 | 0 | 950.4 | 0.18 | 0 | 0.18 | [5 empty] | 1 | 1 | 0 | 7635.4 | 0 | -7635.4 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7635.3 | Request 2021 Budget | 0 | 7635.3 | -7635.3 | 7635.3 | -7635.3 | 664.5 | 6325.3 | 645.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | 5794985 | UNSE | 08W | JDLM | Jesse Lorz |  |  |  |  | Not in the WP |  | SH | STROSA |  | 798 | 0 | 798 | 0.15114 | 0 | 0.15114 | [19 empty] | 4582.1 | Project is not in the WP or in 2020 WP | 0 | 4582.1 | -4582.1 | 0 | 0
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 |  | SH | REDDING | North Valley Assets | 0 | 13424 | 13424 | 2.5424 | 0 | 2.5424 | [5 empty] | 100000 | 0 | 100000 | 12735.7 | 0 | 87264.3 | On/Under Budget | 0 | 0 | 104.5 | -104.5 | 0 | 0 | 0 | 12840.2 | Budget Allocated | 4825999.3 | 4836738.7 | -10739.4 | 12735.7 | 4813263.6 | 0 | 1996.3 | 10739.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-07-12 | Not Started | 2021-08-17 | 2021-08-23 | Not Started | 2021-08-16 | Not Started | 2021-09-13 | Not Started | 2021-07-13 | 2021-07-13 | Not Started | 2021-07-14 | 2021-08-03 | Not Started | 2021-08-17 | 2021-08-30 | Not Started | 2021-10-06 | Not Started | 2021-10-06 | Not Started | 2021-10-19 | Not Started | 2021-10-06 | Not Started | 2022-01-18 | Not Started | 2022-02-16 | Not Started | 2022-04-19 | 2022-04-19 | 0 | On/ Ahead Schedule | Not Started | 2022-04-20 | 2022-05-03 | Not Started | 2022-06-16 | Not Started
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | 5794555 | UNSE | 08W | A3CG | Adoni Andreas Christie |  |  |  |  | 2021 |  | SH | REDDING |  | 4465 | 0 | 4465 | 0.84564 | 0 | 0.84564 | [19 empty] | 1891.2 | Request 2021 Budget | 0 | 1786.7 | -1786.7 | 0 | 0
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | E.5034714.01.05 | 5794555 | UNSE | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP |  | SH | REDDING | North Valley Assets | 13366 | 0 | 13366 | 2.5314 | 0 | 2.5314 | [5 empty] | 1 | 1 | 0 | 1554.1 | 0 | -1554.1 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1554.1 | Project is not in the WP or in 2020 WP | 0 | 1554.1 | -1554.1 | 1554.1 | -1554.1 | 0 | 1139.7 | 414.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | E.5034714.01.06 | 5794555 | UNSE | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP |  | SH | REDDING | North Valley Assets | 0 | 11563 | 11563 | 2.19 | 0 | 2.19 | [5 empty] | 1 | 1 | 0 | 1123.3 | 0 | -1123.3 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1123.3 | Project is not in the WP or in 2020 WP | 0 | 1123.3 | -1123.3 | 1123.3 | -1123.3 | 0 | 711.4 | 411.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | E.5034794.01.01 | 5795152 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 8184 | 0 | 8184 | 1.55 | 0 | 1.55 |  |  |  |  | GC | 1 | 1 | 0 | 935.4 | 0 | -935.4 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935.4 | Request 2021 Budget | 0 | 935.4 | -935.4 | 935.4 | -935.4 | 0 | 0 | 935.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157811 | BL-A | BL-A 35226621_ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-06-28 | Not Started | 2021-10-26 | 2021-11-01 | Not Started | 2021-10-25 | Not Started | 2021-11-22 | Not Started | 2021-06-29 | 2021-06-29 | Not Started | 2021-06-30 | 2021-07-20 | Not Started | 2021-10-26 | 2021-11-08 | Not Started | 2021-12-15 | Not Started | 2021-12-15 | Not Started | 2021-12-28 | Not Started | 2021-12-15 | Not Started | 2022-03-29 | Not Started | 2022-04-27 | Not Started | 2022-07-29 | 2022-06-28 | 31 | On/ Ahead Schedule | Not Started | 2022-06-29 | 2022-07-12 | Not Started | 2022-08-25 | Not Started
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | E.5034794.01.03 | 5795152 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 6072 | 6072 | 1.15 | 0 | 1.15 |  |  |  |  | GC | 1 | 1 | 0 | 687.3 | 0 | -687.3 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687.3 | Request 2021 Budget | 0 | 687.3 | -687.3 | 687.3 | -687.3 | 0 | 0 | 687.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157830 | BL-A | BL-A 35226623_ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-21 | Not Started | 2021-06-28 | 2021-07-02 | Not Started | 2021-06-25 | Not Started | 2021-07-23 | Not Started | 2021-05-24 | 2021-05-24 | Not Started | 2021-05-25 | 2021-06-14 | Not Started | 2021-06-28 | 2021-07-09 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-30 | Not Started | 2021-08-17 | Not Started | 2021-11-29 | Not Started | 2021-12-28 | Not Started | 2022-02-24 | 2022-02-28 | -4 | Behind Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-04-27 | Not Started
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | E.5034794.01.04 | 5795152 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 7709 | 7709 | 1.46 | 0 | 1.46 |  |  |  |  | GC | 1 | 1 | 0 | 687.3 | 0 | -687.3 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687.3 | Request 2021 Budget | 0 | 687.3 | -687.3 | 687.3 | -687.3 | 0 | 0 | 687.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157831 | BL-A | BL-A 35226624_ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-21 | Not Started | 2021-06-28 | 2021-07-02 | Not Started | 2021-06-25 | Not Started | 2021-07-23 | Not Started | 2021-05-24 | 2021-05-24 | Not Started | 2021-05-25 | 2021-06-14 | Not Started | 2021-06-28 | 2021-07-09 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-30 | Not Started | 2021-08-17 | Not Started | 2021-11-29 | Not Started | 2021-12-28 | Not Started | 2022-02-24 | 2022-02-28 | -4 | Behind Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-04-27 | Not Started
35226625 | FRRB - ELK CREEK 1101 LR 2106 |  | 5795150 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  | FRRB | WILLOWS |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 2924 | Project is not in the WP or in 2020 WP | 0 | 2924 | -2924 | 0 | 0
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | 5795151 | UNSE | 08W | JDLM | Jesse Lorz |  |  |  |  | Not in the WP |  | FRRB | GYSRVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 13287.6 | Project is not in the WP or in 2020 WP | 0 | 12769.2 | -12769.2 | 0 | 0
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | E.5034804.01.08 | 5795299 | UNSE | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2021 | 2021 | SH | PLCRVLLE | Sierra Assets | 0 | 14807 | 14807 | 2.8044 | 0 | 2.8044 |  |  |  |  | GC | 70000 | 0 | 70000 | 67039.8 | 0 | 2960.2 | On/Under Budget | 5658336.4 | 66102 | 0 | 66102 | 0 | 0 | 0 | 67039.8 | Budget Allocated | 5802223.75 | 5794148.2 | 8075.55 | 5791478.2 | 10745.55 | 0 | 11683.3 | 55356.5 | 66102 | 4969.6 | 4969.6 | 1409614.5 | 1409614.5 | 1409614.5 | 1409614.5 | 4969.6 | 4969.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-04-30 | Not Started | 2021-05-14 | 2021-05-20 | Not Started | 2021-05-13 | Not Started | 2021-06-10 | Not Started | 2021-05-03 | 2021-05-03 | Not Started | 2021-05-04 | 2021-05-24 | Not Started | 2021-05-14 | 2021-05-27 | Not Started | 2021-07-05 | Not Started | 2021-07-05 | Not Started | 2021-07-16 | Not Started | 2021-07-05 | Not Started | 2021-10-15 | Not Started | 2021-11-15 | Not Started | 2022-01-14 | 2022-01-14 | 0 | On/ Ahead Schedule | Not Started | 2022-01-17 | 2022-01-28 | Not Started | 2022-03-15 | Not Started
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | E.5034804.01.04 | 5795299 | UNSE | 08W | R4BA | Raul Angelo Barron | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2022 |  | SH | PLCRVLLE | Sierra Assets | 9398 | 0 | 9398 | 1.7799 | 0 | 1.7799 |  |  |  |  | GC | 1 | 1 | 0 | 4165.5 | 0 | -4165.5 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4165.5 | Request 2021 Budget | 0 | 4165.5 | -4165.5 | 4165.5 | -4165.5 | 0 | 2225 | 1940.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156277 | BL-A | BL-A 35226849_CWSP - SHINGLE SPRINGS 2109-LR 9372PH2.3_08W - DD 210219 Feb. 2021 | 2021-02-25 | 2021-07-05 | Not Started | 2021-09-21 | 2021-09-27 | Not Started | 2021-09-20 | Not Started | 2021-10-18 | Not Started | 2021-07-06 | 2021-07-06 | Not Started | 2021-07-07 | 2021-07-27 | Not Started | 2021-09-21 | 2021-10-04 | Not Started | 2021-12-08 | Not Started | 2021-12-08 | Not Started | 2021-12-21 | Not Started | 2021-12-08 | Not Started | 2022-03-22 | Not Started | 2022-03-30 | Not Started | 2022-06-24 | 2022-05-30 | 25 | On/ Ahead Schedule | Not Started | 2022-05-31 | 2022-06-13 | Not Started | 2022-07-27 | Not Started
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | E.5034709.01.02 | 5794548 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | UKIAH | Humboldt Division Assets | 792 | 0 | 792 | 0.15 | 0 | 0.15 |  |  |  |  | GC | 475000 | 0 | 475000 | 1863.1 | 0 | 473136.9 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1863.1 | Request 2021 Budget | 0 | 1863.1 | -1863.1 | 1863.1 | -1863.1 | 0 | 922.4 | 940.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157809 | BL-A | BL-A 35226632_CWSP - POTTER VALLEY PH 110564118 PH 1.2_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-29 | Not Started | 2021-11-26 | 2021-12-02 | Not Started | 2021-11-25 | Not Started | 2021-12-23 | Not Started | 2021-07-30 | 2021-07-30 | Not Started | 2021-08-02 | 2021-08-20 | Not Started | 2021-11-26 | 2021-12-09 | Not Started | 2022-01-17 | Not Started | 2022-01-17 | Not Started | 2022-01-28 | Not Started | 2022-01-17 | Not Started | 2022-04-29 | Not Started | 2022-05-30 | Not Started | 2022-07-29 | 2022-07-29 | 0 | On/ Ahead Schedule | Not Started | 2022-08-01 | 2022-08-12 | Not Started | 2022-09-27 | Not Started
35226659 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.2 |  | 5795126 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  | SH | GRSSVLLY |  | 4382.4 | 5544 | 9926.4 | 1.88 | 0 | 1.88 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 | 5543352 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2022 | 2022 | SH | OROVILLE | North Valley Assets | 3010 | 0 | 3010 | 0.57008 | 0 | 0.57008 | [5 empty] | 650000 | 0 | 650000 | 0 | 0 | 650000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Request 2021 Budget | 0 | 500000 | -500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-12-29 | 158090 | BL-A_ | BL-A_35226700_CWSP - WYANDOTTE 110932586 PH 2_08W_Mar.2021 | 2021-03-30 | 2022-03-24 | Not Started | 2022-04-22 | 2022-04-28 | Not Started | 2022-04-21 | Not Started | 2022-05-19 | Not Started | 2022-03-25 | 2022-03-25 | Not Started | 2022-03-28 | 2022-04-15 | Not Started | 2022-04-22 | 2022-05-05 | Not Started | 2022-06-13 | Not Started | 2022-06-13 | Not Started | 2022-06-24 | Not Started | 2022-06-13 | Not Started | 2022-09-23 | Not Started | 2022-10-24 | Not Started | 2022-12-30 | 2022-12-30 | 0 | On/ Ahead Schedule | Not Started | 2023-01-02 | 2023-01-13 | Not Started | 2023-02-28 | Not Started
35226720 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.3 |  | 5795126 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  | SH | GRSSVLLY |  | 0 | 2745.6 | 2745.6 | 0.52 | 0 | 0.52 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35226723 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.4 |  | 5795126 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  | SH | GRSSVLLY |  | 4065.6 | 1425.6 | 5491.2 | 1.04 | 0 | 1.04 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | E.5034784.01.02 | 5795128 | UNSE | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2021 | 2021 | SH | REDBLUFF | North Valley Assets | 0 | 8395.2 | 8395.2 | 1.59 | 0 | 1.59 | [5 empty] | 1 | 1 | 0 | 24539.7 | 0 | -24539.7 | OverRun | 0 | 0 | -24250 | 24250 | 0 | 0 | 0 | 289.7 | Request 2021 Budget | 0 | 24539.7 | -24539.7 | 24539.7 | -24539.7 | 0 | 217.8 | 24321.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-02-01 | 158352 | BL-A_ | BL-A_35226798_CWSP - WILDWOOD 1101 LR 1454TEHAMACO PH2_08W_Apr.2021 | 2021-04-01 | 2021-05-11 | Not Started | 2021-06-16 | 2021-06-22 | Not Started | 2021-06-15 | Not Started | 2021-07-13 | Not Started | 2021-05-12 | 2021-05-12 | Not Started | 2021-05-13 | 2021-06-02 | Not Started | 2021-06-16 | 2021-06-29 | Not Started | 2021-08-05 | Not Started | 2021-08-05 | Not Started | 2021-08-18 | Not Started | 2021-08-05 | Not Started | 2021-11-17 | Not Started | 2021-12-16 | Not Started | 2022-02-16 | 2022-02-16 | 0 | On/ Ahead Schedule | Not Started | 2022-02-17 | 2022-03-02 | Not Started | 2022-04-15 | Not Started
35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | E.5034784.01.03 | 5795128 | UNSE | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2021 | 2021 | SH | REDBLUFF | North Valley Assets | 0 | 1003 | 1003 | 0.18996 | 0 | 0.18996 | [5 empty] | 1 | 1 | 0 | 24320.6 | 0 | -24320.6 | OverRun | 0 | 0 | -24250 | 24250 | 0 | 0 | 0 | 70.6 | Request 2021 Budget | 0 | 24320.6 | -24320.6 | 24320.6 | -24320.6 | 0 | 0 | 24320.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-02-01 | 158353 | BL-A_ | BL-A_35226799_CWSP - WILDWOOD 1101 LR 1454TEHAMACO PH3_08W_Apr.2021 | 2021-04-01 | 2021-05-11 | Not Started | 2021-06-16 | 2021-06-22 | Not Started | 2021-06-15 | Not Started | 2021-07-13 | Not Started | 2021-05-12 | 2021-05-12 | Not Started | 2021-05-13 | 2021-06-02 | Not Started | 2021-06-16 | 2021-06-29 | Not Started | 2021-08-05 | Not Started | 2021-08-05 | Not Started | 2021-08-18 | Not Started | 2021-08-05 | Not Started | 2021-11-17 | Not Started | 2021-12-16 | Not Started | 2022-02-16 | 2022-02-16 | 0 | On/ Ahead Schedule | Not Started | 2022-02-17 | 2022-03-02 | Not Started | 2022-04-15 | Not Started
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | E.5034608.01.02 | 5794207 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 10507 | 10507 | 1.99 | 0 | 1.99 |  |  |  |  | GC | 1 | 1 | 0 | 687.3 | 0 | -687.3 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687.3 | Request 2021 Budget | 0 | 687.3 | -687.3 | 687.3 | -687.3 | 0 | 0 | 687.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157793 | BL-A | BL-A 35226819_CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-08 | Not Started | 2021-11-05 | 2021-11-11 | Not Started | 2021-11-04 | Not Started | 2021-12-02 | Not Started | 2021-07-09 | 2021-07-09 | Not Started | 2021-07-12 | 2021-07-30 | Not Started | 2021-11-05 | 2021-11-18 | Not Started | 2021-12-27 | Not Started | 2021-12-27 | Not Started | 2022-01-07 | Not Started | 2021-12-27 | Not Started | 2022-04-08 | Not Started | 2022-05-09 | Not Started | 2022-07-08 | 2022-07-08 | 0 | On/ Ahead Schedule | Not Started | 2022-07-11 | 2022-07-22 | Not Started | 2022-09-06 | Not Started
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 |  | SH | CHICO | North Valley Assets | 0 | 1056 | 1056 | 0.2 | 0 | 0.2 | 453 | 0 | 0.085795 | 0 | GC | 150000 | 0 | 150000 | 20951.2 | 0 | 129048.8 | On/Under Budget | 131623 | 0 | 278.6 | -278.6 | 0 | 0 | 604.7 | 20625 | Budget Allocated | 380000 | 381969.4 | -1969.4 | 151969.4 | 228030.6 | 15933.6 | 2441.8 | 1971 | 0 | 0 | 0 | 0 | 0 | 131623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | E.5034608.01.01 | 5794207 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 2270 | 2270 | 0.42992 | 0 | 0.42992 |  |  |  |  | GC | 1 | 1 | 0 | 16647.4 | 0 | -16647.4 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 2545.5 | 14101.9 | Request 2021 Budget | 0 | 14101.9 | -14101.9 | 14101.9 | -14101.9 | 10793.2 | 2529.8 | 778.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157792 | BL-A | BL-A 35217269_CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-08 | Not Started | 2021-11-05 | 2021-11-11 | Not Started | 2021-11-04 | Not Started | 2021-12-02 | Not Started | 2021-07-09 | 2021-07-09 | Not Started | 2021-07-12 | 2021-07-30 | Not Started | 2021-11-05 | 2021-11-18 | Not Started | 2021-12-27 | Not Started | 2021-12-27 | Not Started | 2022-01-07 | Not Started | 2021-12-27 | Not Started | 2022-04-08 | Not Started | 2022-05-09 | Not Started | 2022-07-08 | 2022-07-08 | 0 | On/ Ahead Schedule | Not Started | 2022-07-11 | 2022-07-22 | Not Started | 2022-09-06 | Not Started
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | E.5034609.01.01 | 5794206 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 2904 | 2904 | 0.55 | 0 | 0.55 | 2516 | 0 | 0.47652 | 0 | GC | 316666 | 0 | 316666 | 44155.9 | 0 | 272510.1 | On/Under Budget | 10736.1 | 3578.7 | -24570 | 28148.7 | 0 | 0 | 4345.2 | 15240.8 | Request 2021 Budget | 0 | 54125.6 | -54125.6 | 54125.6 | -54125.6 | 11436.1 | 20604.5 | 7770.2 | 3578.7 | 3578.7 | 3578.7 | 3578.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157799 | BL-A | BL-A 35217270_CWSP - KONOCTI 1102 LR 965078 PH1_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-24 | Not Started | 2021-09-28 | 2021-10-04 | Not Started | 2021-09-27 | Not Started | 2021-10-25 | Not Started | 2021-05-25 | 2021-05-25 | Not Started | 2021-05-26 | 2021-06-15 | Not Started | 2021-09-28 | 2021-10-11 | Not Started | 2021-11-17 | Not Started | 2021-11-17 | Not Started | 2021-11-30 | Not Started | 2021-11-17 | Not Started | 2022-03-01 | Not Started | 2022-03-30 | Not Started | 2022-07-01 | 2022-05-31 | 31 | On/ Ahead Schedule | Not Started | 2022-06-01 | 2022-06-14 | Not Started | 2022-07-28 | Not Started
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | E.5034610.01.01 | 5794205 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 8131 | 0 | 8131 | 1.54 | 0 | 1.54 |  |  |  |  | GC | 1 | 1 | 0 | 49076.3 | 0 | -49076.3 | OverRun | 0 | 0 | 196.6 | -196.6 | 0 | 0 | 18452.7 | 30820.1 | Request 2021 Budget | 0 | 30623.5 | -30623.5 | 30623.5 | -30623.5 | 31985.8 | -2610.8 | 1248.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157801 | BL-A | BL-A 35217271_CWSP - MIDDLETOWN 1103 LR 830 PH 1.1_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-06-07 | Not Started | 2021-10-05 | 2021-10-11 | Not Started | 2021-10-04 | Not Started | 2021-11-01 | Not Started | 2021-06-08 | 2021-06-08 | Not Started | 2021-06-09 | 2021-06-29 | Not Started | 2021-10-05 | 2021-10-18 | Not Started | 2021-11-24 | Not Started | 2021-11-24 | Not Started | 2021-12-07 | Not Started | 2021-11-24 | Not Started | 2022-03-08 | Not Started | 2022-04-06 | Not Started | 2022-07-08 | 2022-06-07 | 31 | On/ Ahead Schedule | Not Started | 2022-06-08 | 2022-06-21 | Not Started | 2022-08-04 | Not Started
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2022 | 2022 | SH | REDDING | North Valley Assets | 1584 | 0 | 1584 | 0.3 | 0 | 0.3 |  |  |  |  | GC | 150000 | 0 | 150000 | 50170.5 | 0 | 99829.5 | On/Under Budget | 0 | 0 | -24570 | 24570 | 0 | 0 | 2467.6 | 23132.9 | Request 2021 Budget | 0 | 514955.9 | -514955.9 | 47702.9 | -47702.9 | 14932.4 | 7721.9 | 25048.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157965 | BL-A_ | BL-A_35217272_SH - KESWICK 1101 LR 1586 PH 1.1_08W_Mar.2021 | 2021-03-23 | 2021-06-28 | Not Started | 2022-04-29 | 2022-05-05 | Not Started | 2022-04-28 | Not Started | 2022-05-26 | Not Started | 2021-06-29 | 2021-06-29 | Not Started | 2021-06-30 | 2021-07-20 | Not Started | 2021-08-03 | 2021-08-16 | Not Started | 2022-06-20 | Not Started | 2022-06-20 | Not Started | 2022-07-01 | Not Started | 2022-06-20 | Not Started | 2022-09-30 | Not Started | 2022-10-31 | Not Started | 2022-12-30 | 2022-12-30 | 0 | On/ Ahead Schedule | Not Started | 2023-01-02 | 2023-01-13 | Not Started | 2023-02-28 | Not Started
35217273 | SH - UPPER LAKE 1101 CB | E.5034612.01.01 | 5794203 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH - Remote Grid | LAKEPORT | Humboldt Division Assets | 0 | 5702.4 | 5702.4 | 1.08 | 0 | 1.08 |  |  |  |  | GC | 500000 | 0 | 500000 | 15520.6 | 0 | 484479.4 | On/Under Budget | 11551.3 | 3610.5 | 0 | 3610.5 | 0 | 0 | 2331.9 | 13188.7 | Request 2021 Budget | 0 | 28350.6 | -28350.6 | 28350.6 | -28350.6 | 7022.9 | 5512.6 | 653.2 | 3610.5 | 3631.6 | 3652.7 | 3676.3 | 168.8 | 168.8 | 168.8 | 84.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 156046 | BL-A | BL-A 35217273 _SH - UPPER LAKE 1101 CB_08W - Feb. 2021 | 2021-02-17 | 2021-05-11 | Not Started | 2021-10-27 | 2021-11-02 | Not Started | 2021-10-26 | Not Started | 2021-11-23 | Not Started | 2021-05-12 | 2021-05-12 | Not Started | 2021-05-13 | 2021-06-02 | Not Started | 2021-10-01 | 2021-10-15 | Not Started | 2021-12-16 | Not Started | 2021-12-16 | Not Started | 2021-12-29 | Not Started | 2021-12-16 | Not Started | 2022-02-02 | Not Started | 2022-03-03 | Not Started | 2022-04-01 | 2022-05-04 | -33 | Behind Schedule | Not Started | 2022-05-05 | 2022-05-18 | Not Started | 2022-07-01 | Not Started
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | E.5034402.01 | 5792093 | UNSE | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | 2022 |  | SH | PLCRVLLE | Sierra Assets | 2534.4 | 0 | 2534.4 | 0.48 | 0 | 0.48 |  |  |  |  | Contract | 1 | -499999 | 500000 | 39020.6 | 0 | 460979.4 | On/Under Budget | 1543575.2 | 71601.4 | -22000 | 93601.4 | 0 | 0 | 1755.2 | 15265.4 | Request 2021 Budget | 0 | 290630.9 | -290630.9 | 287783 | -287783 | 5236 | 12170.3 | 19859.1 | 71601.4 | 32989.8 | 29031 | 6572.5 | 7883 | 6387.8 | 17691.9 | 75521.4 | 2838.8 | 14841.2 | 385066.9 | 564445.7 | 170754.5 | 221277.5 | 5274.2 | 2998.9 | 0 | 0 | 0 | 0 | 0 | 1364658.9 | 2021-04-02 | 156210 | BL-A | BL-A 35192291_ECOP - DIAMOND SPRINGS 1107 - H02-LR1402_08W - DD 210205 Feb. 2021 | 2021-02-23 | 2021-09-15 | Not Started | 2021-10-28 | 2021-11-03 | Not Started | 2021-10-27 | Not Started | 2021-11-24 | Not Started | 2021-09-16 | 2021-09-16 | Not Started | 2021-09-17 | 2021-10-07 | Not Started | 2021-10-28 | 2021-11-10 | Not Started | 2022-02-18 | Not Started | 2022-03-04 | Not Started | 2022-03-31 | Not Started | 2022-02-18 | Not Started | 2022-04-21 | Not Started | 2022-05-20 | Not Started | 2022-07-07 | 2022-06-27 | 10 | On/ Ahead Schedule | Not Started | 2022-06-28 | 2022-07-11 | Not Started | 2022-08-24 | Not Started
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | 5794539 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | BKRSFLD |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 4623.7 | Project is not in the WP or in 2020 WP | 0 | 4623.7 | -4623.7 | 0 | 0
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | E.5034692.01.01 | 5794540 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | CONCORD | Diablo Assets | 6019 | 0 | 6019 | 1.14 | 0 | 1.14 | [5 empty] | 350000 | 0 | 350000 | 19405.4 | 0 | 330594.6 | On/Under Budget | 0 | 0 | 541.6 | -541.6 | 0 | 0 | 0 | 19947 | Request 2021 Budget | 0 | 19405.4 | -19405.4 | 19405.4 | -19405.4 | 4101.9 | 3385 | 11918.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-10-19 | Not Started | 2022-03-23 | 2022-03-29 | Not Started | 2022-03-22 | Not Started | 2022-04-19 | Not Started | 2021-10-20 | 2021-10-20 | Not Started | 2021-10-21 | 2021-11-10 | Not Started | 2022-03-23 | 2022-04-05 | Not Started | 2022-05-12 | Not Started | 2022-05-12 | Not Started | 2022-07-21 | Not Started | 2022-05-12 | Not Started | 2022-07-25 | Not Started | 2022-08-23 | Not Started | 2022-10-24 | 2022-10-24 | 0 | On/ Ahead Schedule | Not Started | 2022-10-25 | 2022-11-07 | Not Started | 2022-12-21 | Not Started
35219094 | CNCL CWSP - VACA DIXON 1101126774 |  | 5543350 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | VACAVLLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | E.5034694.01.01 | 5794544 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | ANTIOCH | Diablo Assets | 8817.6 | 0 | 8817.6 | 1.67 | 0 | 1.67 | [5 empty] | 500000 | 0 | 500000 | 9432.5 | 0 | 490567.5 | On/Under Budget | 249.2 | 14.9 | 97.2 | -82.3 | 0 | 0 | 0 | 9529.6 | Request 2021 Budget | 0 | 9568.9 | -9568.9 | 9568.9 | -9568.9 | 1726.1 | 5403.7 | 2302.6 | 14.9 | 14.9 | 14.9 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 15.3 | 14.9 | 14.9 | 14.9 | 14.9 | 14.9 | 14.9 | 15.4 | 15.4 | 7.7 | 0 | 0 | 0 | 127.9 | 2021-04-02 | 157130 | BL-A | BL-A CWSP - KIRKER 2104442850 PH 1 - Mar. 2021 | 2021-03-07 | 2021-12-15 | Not Started | 2022-03-10 | 2022-03-16 | Not Started | 2022-03-09 | Not Started | 2022-04-06 | Not Started | 2021-12-16 | 2021-12-16 | Not Started | 2021-12-17 | 2022-01-06 | Not Started | 2022-03-10 | 2022-03-23 | Not Started | 2022-04-29 | Not Started | 2022-04-29 | Not Started | 2022-08-11 | Not Started | 2022-04-29 | Not Started | 2022-08-11 | Not Started | 2022-09-09 | Not Started | 2023-01-20 | 2023-01-13 | 7 | On/ Ahead Schedule | Not Started | 2023-01-16 | 2023-01-27 | Not Started | 2023-04-07 | Not Started
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | 5794549 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | Not in the WP |  | SH | LAKEPORT |  | 0 | 11208 | 11208 | 2.1227 | 0 | 2.1227 | [19 empty] | 26487.5 | Project is not in the WP or in 2020 WP | 0 | 26452.7 | -26452.7 | 0 | 0
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | 5543321 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | PLCRVLLE |  | 739.2 | 0 | 739.2 | 0.14 | 0 | 0.14 | [19 empty] | 8210.3 | Project is not in the WP or in 2020 WP | 0 | 8210.3 | -8210.3 | 0 | 0
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | E.5034715.01.02 | 5543321 | UNSE | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2021 |  | SH | PLCRVLLE | Sierra Assets | 1267.2 | 0 | 1267.2 | 0.24 | 0 | 0.24 | [5 empty] | 500000 | 0 | 500000 | 5724.4 | 0 | 494275.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5724.5 | Request 2021 Budget | 0 | 5724.5 | -5724.5 | 5724.5 | -5724.5 | 456.6 | 3448.3 | 1819.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | 5794552 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | MARIPOSA |  | 0 | 11378.4 | 11378.4 | 2.155 | 0 | 2.155 | [19 empty] | 7953.8 | Project is not in the WP or in 2020 WP | 0 | 7953.8 | -7953.8 | 0 | 0
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | 5794552 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | MARIPOSA |  | 0 | 11378.4 | 11378.4 | 2.155 | 0 | 2.155 | [19 empty] | 6908.6 | Project is not in the WP or in 2020 WP | 0 | 6908.6 | -6908.6 | 0 | 0
35219589 | CWSP - WILDWOOD 11011454 | E.5034719.01.01 | 5794561 | UNSE | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2022 | 2021 | SH | REDBLUFF | North Valley Assets | 0 | 13622.4 | 13622.4 | 2.58 | 0 | 2.58 |  |  |  |  | GC | 1 | 1 | 0 | 37314.9 | 0 | -37314.9 | OverRun | 0 | 0 | -24505.2 | 24505.2 | 0 | 0 | 0 | 12809.8 | Request 2021 Budget | 0 | 37315 | -37315 | 37315 | -37315 | 7243.7 | 3571.9 | 26499.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-02-01 | 158350 | BL-A_ | BL-A_35219589_CWSP - WILDWOOD 11011454_08W_Apr.2021 | 2021-04-01 | 2021-05-11 | Not Started | 2021-06-16 | 2021-06-22 | Not Started | 2021-06-15 | Not Started | 2021-07-13 | Not Started | 2021-05-12 | 2021-05-12 | Not Started | 2021-05-13 | 2021-06-02 | Not Started | 2021-06-16 | 2021-06-29 | Not Started | 2021-08-05 | Not Started | 2021-08-05 | Not Started | 2021-08-18 | Not Started | 2021-08-05 | Not Started | 2021-11-17 | Not Started | 2021-12-16 | Not Started | 2022-02-16 | 2022-02-16 | 0 | On/ Ahead Schedule | Not Started | 2022-02-17 | 2022-03-02 | Not Started | 2022-04-15 | Not Started
35219590 | CWSP - VACA DIXON 1105965390 |  | 5794542 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | VACAVLLE |  | 0 | 3273.6 | 3273.6 | 0.62 | 0 | 0.62 | [19 empty] | 10657.5 | Project is not in the WP or in 2020 WP | 0 | 10657.5 | -10657.5 | 0 | 0
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | 5794555 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | REDDING |  | 0 | 12652 | 12652 | 2.3962 | 0 | 2.3962 | [19 empty] | 11421.5 | Project is not in the WP or in 2020 WP | 0 | 11421.5 | -11421.5 | 0 | 0
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | 5794555 | UNSE | 08W | A3CG | Adoni Andreas Christie |  |  |  |  | Not in the WP |  | SH | REDDING |  | 22991 | 0 | 22991 | 4.3544 | 0 | 4.3544 | [19 empty] | 13890.9 | Project is not in the WP or in 2020 WP | 0 | 13890.9 | -13890.9 | 0 | 0
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | 5794552 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | MARIPOSA |  | 0 | 22545.6 | 22545.6 | 4.27 | 0 | 4.27 | [19 empty] | 21593.8 | Project is not in the WP or in 2020 WP | 0 | 21453.2 | -21453.2 | 0 | 0
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | 5794550 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | BKRSFLD |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 2988.4 | Project is not in the WP or in 2020 WP | 0 | 2988.4 | -2988.4 | 0 | 0
35219265 | CWSP - CRESTA 1101546650 |  | 5543353 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | CHICO |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 4535.7 | Project is not in the WP or in 2020 WP | 0 | 4535.7 | -4535.7 | 0 | 0
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | E.5034707.01.01 | 5794545 | UNSE | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | VACAVLLE | Sacramento Assets | 14203.2 | 0 | 14203.2 | 2.69 | 0 | 2.69 | [5 empty] | 1 | 1 | 0 | 33244.9 | 0 | -33244.9 | OverRun | 0 | 0 | 97.2 | -97.2 | 0 | 0 | 799.7 | 32542.5 | Request 2021 Budget | 0 | 32445.3 | -32445.3 | 32445.3 | -32445.3 | 5965.5 | 23990.5 | 2489.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219279 | CWSP - VACAVILLE 11088762 |  | 5543348 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | VACAVLLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | E.5034709.01.01 | 5794548 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | UKIAH | Humboldt Division Assets | 0 | 8870 | 8870 | 1.6799 | 0 | 1.6799 |  |  |  |  | GC | 475000 | 0 | 475000 | 5362.8 | 0 | 469637.2 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5362.7 | Request 2021 Budget | 0 | 5362.7 | -5362.7 | 5362.7 | -5362.7 | 2219 | 2182.9 | 960.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157827 | BL-A | BL-A 35219280_CWSP - POTTER VALLEY PH 110564118 PH 1.1_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-31 | Not Started | 2021-07-06 | 2021-07-12 | Not Started | 2021-07-05 | Not Started | 2021-08-02 | Not Started | 2021-06-01 | 2021-06-01 | Not Started | 2021-06-02 | 2021-06-22 | Not Started | 2021-07-06 | 2021-07-19 | Not Started | 2021-08-25 | Not Started | 2021-08-25 | Not Started | 2021-09-07 | Not Started | 2021-08-25 | Not Started | 2021-12-07 | Not Started | 2022-01-05 | Not Started | 2022-02-24 | 2022-03-08 | -12 | Behind Schedule | Not Started | 2022-03-09 | 2022-03-22 | Not Started | 2022-05-05 | Not Started
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | E.5034710.01.01 | 5794551 | UNSE | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2022 | 2021 | SH | AUBURN | Sierra Assets | 13200 | 0 | 13200 | 2.5 | 0 | 2.5 |  |  |  |  | GC | 316666 | 0 | 316666 | 20740.1 | 0 | 295925.9 | On/Under Budget | 0 | 0 | 174.1 | -174.1 | 0 | 0 | 0 | 20914.2 | Budget Allocated | 251101 | 208345.1 | 42755.9 | 20740.1 | 230360.9 | 6787.7 | 12048.2 | 1904.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-07-14 | Not Started | 2021-08-19 | 2021-08-25 | Not Started | 2021-08-18 | Not Started | 2021-09-15 | Not Started | 2021-07-15 | 2021-07-15 | Not Started | 2021-07-16 | 2021-08-05 | Not Started | 2021-08-19 | 2021-09-01 | Not Started | 2021-10-08 | Not Started | 2021-10-08 | Not Started | 2021-10-21 | Not Started | 2021-10-08 | Not Started | 2022-01-20 | Not Started | 2022-02-18 | Not Started | 2022-04-21 | 2022-04-21 | 0 | On/ Ahead Schedule | Not Started | 2022-04-22 | 2022-05-05 | Not Started | 2022-06-20 | Not Started
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 |  | 5792513 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | AUBURN | [26 empty] | 57.4 | Project is not in the WP or in 2020 WP | 0 | 57.4 | -57.4 | 0 | 0
35206134 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.2 |  | 5793703 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | STCRUZ |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35206135 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.3 |  | 5793703 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | STCRUZ |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35206136 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.4 |  | 5793703 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | STCRUZ |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35206138 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.5 |  | 5793703 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | STCRUZ |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35212401 | FRRB - MONTICELLO 1101 CB |  | 5793892 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | NAPA |  | 0 | 369.6 | 369.6 | 0.07 | 0.07 | 0 | [19 empty] | -60921531.3 | Project is not in the WP or in 2020 WP | 0 | -29042039.3 | 29042039.3 | 0 | 0
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | 5793892 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | NAPA |  | 0 | 20644.8 | 20644.8 | 3.91 | 3.91 | 0 | [19 empty] | 77902.8 | Project is not in the WP or in 2020 WP | 0 | 77902.8 | -77902.8 | 0 | 0
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | 5793892 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | NAPA |  | 0 | 24288 | 24288 | 4.6 | 4.6 | 0 | [19 empty] | 91650.5 | Project is not in the WP or in 2020 WP | 0 | 91650.5 | -91650.5 | 0 | 0
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | 5793892 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | NAPA |  | 0 | 33369.6 | 33369.6 | 6.32 | 6.32 | 0 | [19 empty] | 125919.9 | Project is not in the WP or in 2020 WP | 0 | 125919.9 | -125919.9 | 0 | 0
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | 5793892 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | NAPA |  | 0 | 69062.4 | 69062.4 | 13.08 | 13.08 | 0 | [19 empty] | 260606.3 | Project is not in the WP or in 2020 WP | 0 | 260606.3 | -260606.3 | 0 | 0
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | 5793892 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | NAPA |  | 0 | 8184 | 8184 | 1.55 | 1.55 | 0 | [19 empty] | 30882.2 | Project is not in the WP or in 2020 WP | 0 | 30882.2 | -30882.2 | 0 | 0
35212407 | FRRB - SILVERADO 2102 LR 636 |  | 5793892 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | NAPA |  | 0 | 3537.6 | 3537.6 | 0.67 | 0.67 | 0 | [19 empty] | 66781.2 | Project is not in the WP or in 2020 WP | 0 | 66781.2 | -66781.2 | 0 | 0
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | 5793892 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | NAPA |  | 0 | 9873.6 | 9873.6 | 1.87 | 1.87 | 0 | [19 empty] | 186362.8 | Project is not in the WP or in 2020 WP | 0 | 186362.8 | -186362.8 | 0 | 0
35212409 | FRRB - SILVERADO 2104 LR 645 |  | 5793892 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | NAPA |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 407268 | Project is not in the WP or in 2020 WP | 0 | 407268 | -407268 | 0 | 0
35212410 | FRRB - SILVERADO 2104 LR 708 |  | 5793892 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | NAPA |  | 0 | 3907.2 | 3907.2 | 0.74 | 0.74 | 0 | [19 empty] | 73746.1 | Project is not in the WP or in 2020 WP | 0 | 73746.1 | -73746.1 | 0 | 0
35212411 | FRRB - SILVERADO 2104 LR 722 |  | 5793892 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | NAPA |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 343915.2 | Project is not in the WP or in 2020 WP | 0 | 343915.2 | -343915.2 | 0 | 0
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | 5793892 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | NAPA |  | 0 | 26136 | 26136 | 4.95 | 4.95 | 0 | [19 empty] | 493331.2 | Project is not in the WP or in 2020 WP | 0 | 493331.2 | -493331.2 | 0 | 0
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | 5793892 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | NAPA |  | 0 | 10697.28 | 10697.28 | 2.026 | 2.026 | 0 | [19 empty] | 201910.8 | Project is not in the WP or in 2020 WP | 0 | 201910.8 | -201910.8 | 0 | 0
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | 5793892 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | NAPA |  | 0 | 2513.28 | 2513.28 | 0.476 | 0.476 | 0 | [19 empty] | 47436.5 | Project is not in the WP or in 2020 WP | 0 | 47436.5 | -47436.5 | 0 | 0
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | 5793892 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | NAPA |  | 0 | 12672 | 12672 | 2.4 | 2.4 | 0 | [19 empty] | 239197.1 | Project is not in the WP or in 2020 WP | 0 | 239197.1 | -239197.1 | 0 | 0
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | 5793892 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | NAPA |  | 0 | 7920 | 7920 | 1.5 | 1.5 | 0 | [19 empty] | 149489.7 | Project is not in the WP or in 2020 WP | 0 | 149489.7 | -149489.7 | 0 | 0
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | 5793892 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | NAPA |  | 0 | 20856 | 20856 | 3.95 | 3.95 | 0 | [19 empty] | 393671.5 | Project is not in the WP or in 2020 WP | 0 | 393671.5 | -393671.5 | 0 | 0
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | 5793893 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | GYSRVLLE |  | 0 | 72336 | 72336 | 13.7 | 13.7 | 0 | [19 empty] | 117919.3 | Project is not in the WP or in 2020 WP | 0 | 117919.3 | -117919.3 | 0 | 0
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | 5793893 | UNSE | 08W | M5PO | Marc Henry Tabunot Perez |  |  |  |  | Not in the WP |  | FRRB | STROSA |  | 0 | 12355.2 | 12355.2 | 2.34 | 2.34 | 0 | [19 empty] | 25241 | Project is not in the WP or in 2020 WP | 0 | 25241 | -25241 | 0 | 0
35212460 | FRRB - RINCON 1101 LR 14605 |  | 5793893 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | STROSA |  | 0 | 69854.4 | 69854.4 | 13.23 | 13.23 | 0 | [19 empty] | 140001.2 | Project is not in the WP or in 2020 WP | 0 | 140001.2 | -140001.2 | 0 | 0
35212461 | FRRB - RINCON 1101 LR 663641 |  | 5793893 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | STROSA |  | 0 | 3115.2 | 3115.2 | 0.59 | 0.59 | 0 | [19 empty] | 6611.1 | Project is not in the WP or in 2020 WP | 0 | 6611.1 | -6611.1 | 0 | 0
35212462 | FRRB - RINCON 1103 LR 198 |  | 5793893 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | STROSA |  | 0 | 13728 | 13728 | 2.6 | 2.6 | 0 | [19 empty] | 27228.5 | Project is not in the WP or in 2020 WP | 0 | 27228.5 | -27228.5 | 0 | 0
35212463 | FRRB - RINCON 1103 LR 474 |  | 5793893 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | STROSA |  | 0 | 87595.2 | 87595.2 | 16.59 | 16.59 | 0 | [19 empty] | 176191 | Project is not in the WP or in 2020 WP | 0 | 176191 | -176191 | 0 | 0
35212464 | FRRB - CALISTOGA 1101 LR 886282 |  | 5793893 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | STROSA |  | 0 | 5016 | 5016 | 0.95 | 0.95 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | 5793894 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | VACAVLLE |  | 0 | 33475.2 | 33475.2 | 6.34 | 6.34 | 0 | [19 empty] | 106666.3 | Project is not in the WP or in 2020 WP | 0 | 106666.3 | -106666.3 | 0 | 0
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | 5793894 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | VACAVLLE |  | 0 | 47203.2 | 47203.2 | 8.94 | 8.94 | 0 | [19 empty] | 150409.5 | Project is not in the WP or in 2020 WP | 0 | 150409.5 | -150409.5 | 0 | 0
35212467 | FRRB - LAURELES 1111 LR 2020 |  | 5793895 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | MONTEREY |  | 0 | 6441.6 | 6441.6 | 1.22 | 1.22 | 0 | [19 empty] | 40652.5 | Project is not in the WP or in 2020 WP | 0 | 40652.5 | -40652.5 | 0 | 0
35212468 | FRRB - POINT MORETTI 1101 LR36516 |  | 5793896 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | STCRUZ |  | 0 | 5016 | 5016 | 0.95 | 0.95 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35212469 | FRRB - POINT MORETTI 1101 LR12122 |  | 5793896 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | STCRUZ |  | 0 | 24393.6 | 24393.6 | 4.62 | 4.62 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35212470 | FRRB - POINT MORETTI 1101 LR83716 |  | 5793896 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | STCRUZ |  | 0 | 4065.6 | 4065.6 | 0.77 | 0.77 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35212471 | FRRB - POINT MORETTI 1101 LR5076 |  | 5793896 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | STCRUZ |  | 0 | 8976 | 8976 | 1.7 | 1.7 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | 5793896 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | STCRUZ |  | 0 | 13411.2 | 13411.2 | 2.54 | 2.54 | 0 | [19 empty] | 147257 | Project is not in the WP or in 2020 WP | 0 | 147257 | -147257 | 0 | 0
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | 5793896 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | STCRUZ |  | 0 | 11668.8 | 11668.8 | 2.21 | 2.21 | 0 | [19 empty] | 128125.3 | Project is not in the WP or in 2020 WP | 0 | 128125.3 | -128125.3 | 0 | 0
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | 5793896 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | STCRUZ |  | 0 | 2745.6 | 2745.6 | 0.52 | 0.52 | 0 | [19 empty] | 30147.1 | Project is not in the WP or in 2020 WP | 0 | 30147.1 | -30147.1 | 0 | 0
35212475 | FRRB - BIG BASIN 1101 CB |  | 5793896 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | STCRUZ |  | 0 | 16315.2 | 16315.2 | 3.09 | 3.09 | 0 | [19 empty] | 179143.5 | Project is not in the WP or in 2020 WP | 0 | 179143.5 | -179143.5 | 0 | 0
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | 5793896 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | STCRUZ |  | 0 | 7233.6 | 7233.6 | 1.37 | 1.37 | 0 | [19 empty] | 79426.1 | Project is not in the WP or in 2020 WP | 0 | 79426.1 | -79426.1 | 0 | 0
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | 5793896 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | STCRUZ |  | 0 | 3115.2 | 3115.2 | 0.59 | 0.59 | 0 | [19 empty] | 34205.4 | Project is not in the WP or in 2020 WP | 0 | 34205.4 | -34205.4 | 0 | 0
35212478 | FRRB - SWIFT 2110 XR332 |  | 5793897 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | CINNABAR |  | 0 | 44616 | 44616 | 8.45 | 8.45 | 0 | [19 empty] | 45547.7 | Project is not in the WP or in 2020 WP | 0 | 45547.7 | -45547.7 | 0 | 0
35212479 | FRRB - BIG BEND 1102 CB |  | 5793918 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | CHICO |  | 0 | 21331.2 | 21331.2 | 4.04 | 4.04 | 0 | [19 empty] | 434596.1 | Project is not in the WP or in 2020 WP | 0 | 434596.1 | -434596.1 | 0 | 0
35212480 | FRRB - BIG BEND 1102 LR1972 |  | 5793918 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 21436.8 | 21436.8 | 4.06 | 4.06 | 0 | [19 empty] | 436670.5 | Project is not in the WP or in 2020 WP | 0 | 436670.5 | -436670.5 | 0 | 0
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | 5793918 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 52377.6 | 52377.6 | 9.92 | 9.92 | 0 | [19 empty] | 945218.6 | Project is not in the WP or in 2020 WP | 0 | 945218.6 | -945218.6 | 0 | 0
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | 5793918 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 42081.6 | 42081.6 | 7.97 | 7.97 | 0 | [19 empty] | 857782.5 | Project is not in the WP or in 2020 WP | 0 | 857782.5 | -857782.5 | 0 | 0
35212486 | FRRB - KANAKA 1101 CB |  | 5793918 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 16262.4 | 16262.4 | 3.08 | 3.08 | 0 | [19 empty] | 394662.1 | Project is not in the WP or in 2020 WP | 0 | 394662.1 | -394662.1 | 0 | 0
35212487 | FRRB - KANAKA 1101 LR1034 |  | 5793918 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 14150.4 | 14150.4 | 2.68 | 2.68 | 0 | [19 empty] | 298778.3 | Project is not in the WP or in 2020 WP | 0 | 298778.3 | -298778.3 | 0 | 0
35212488 | FRRB - KANAKA 1101 LR1406 |  | 5793918 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 47044.8 | 47044.8 | 8.91 | 8.91 | 0 | [19 empty] | 985361.7 | Project is not in the WP or in 2020 WP | 0 | 985361.7 | -985361.7 | 0 | 0
35212489 | FRRB - GIRVAN 1101 LR1330 |  | 5793919 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | REDDING |  | 0 | 16104 | 16104 | 3.05 | 3.05 | 0 | [19 empty] | 175615.1 | Project is not in the WP or in 2020 WP | 0 | 175615.1 | -175615.1 | 0 | 0
35212490 | FRRB - GIRVAN 1101 LR323094 |  | 5793919 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | REDDING |  | 0 | 28934.4 | 28934.4 | 5.48 | 5.48 | 0 | [19 empty] | 315525.2 | Project is not in the WP or in 2020 WP | 0 | 315525.2 | -315525.2 | 0 | 0
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | 5793920 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | OAKHURST |  | 0 | 5068.8 | 5068.8 | 0.96 | 0.96 | 0 | [19 empty] | 27764.1 | Project is not in the WP or in 2020 WP | 0 | 27764.1 | -27764.1 | 0 | 0
35212492 | FRRB - AUBERRY 1101 R2845 |  | 5793921 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | FRESNO |  | 0 | 10084.8 | 10084.8 | 1.91 | 1.91 | 0 | [19 empty] | 9005.6 | Project is not in the WP or in 2020 WP | 0 | 9005.6 | -9005.6 | 0 | 0
35212493 | FRRB - AUBERRY 1101 R324 |  | 5793921 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | FRESNO |  | 0 | 34003.2 | 34003.2 | 6.44 | 6.44 | 0 | [19 empty] | 29703.9 | Project is not in the WP or in 2020 WP | 0 | 29703.9 | -29703.9 | 0 | 0
35212494 | FRRB - AUBERRY 1101 LR37536 |  | 5793921 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | FRESNO |  | 0 | 13833.6 | 13833.6 | 2.62 | 2.62 | 0 | [19 empty] | 11692.6 | Project is not in the WP or in 2020 WP | 0 | 11692.6 | -11692.6 | 0 | 0
35212495 | FRRB - AUBERRY 1101 LR233716 |  | 5793921 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | FRESNO |  | 0 | 45672 | 45672 | 8.65 | 8.65 | 0 | [19 empty] | 39598.4 | Project is not in the WP or in 2020 WP | 0 | 39598.4 | -39598.4 | 0 | 0
35212496 | FRRB - HB TRINITY COUNTY |  | 5793922 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | FRRB | FORTUNA |  | 0 | 11932.8 | 11932.8 | 2.26 | 2.26 | 0 | [19 empty] | 57184.2 | Project is not in the WP or in 2020 WP | 0 | 57184.2 | -57184.2 | 0 | 0
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | E.5014535.03 | 5786056 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 0 | 7920 | 7920 | 1.5 | 0 | 1.5 | [5 empty] | 10000 | 0 | 10000 | 5282.6 | 0 | 4717.4 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 327.6 | 4788.1 | 166.8 | Project is not in the WP or in 2020 WP | 0 | 166.8 | -166.8 | 166.8 | -166.8 | 106.4 | 30.2 | 30.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | E.5014535.04 | 5786057 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 0 | 4065.6 | 4065.6 | 0.77 | 0 | 0.77 | [5 empty] | 10000 | 0 | 10000 | 4989.1 | 0 | 5010.9 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 292.8 | 4497.2 | 199.2 | Project is not in the WP or in 2020 WP | 0 | 199.2 | -199.2 | 199.2 | -199.2 | 142 | 28.6 | 28.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35113945 | CWSP - BRUNSWICK 1102 - LR 1010 |  | 5786218 | UNSE | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | GRSSVLLY | [26 empty] | 48.9 | Project is not in the WP or in 2020 WP | 0 | 48.9 | -48.9 | 0 | 0
35113946 | CWSP - WYANDOTTE 1103 – LR 1974 |  | 5786219 | UNSE | 08W | MTTA | Musie Tsegay Tesfasilassie |  |  |  |  | Not in the WP |  |  | OROVILLE | [26 empty] | 14.9 | Project is not in the WP or in 2020 WP | 0 | 14.9 | -14.9 | 0 | 0
35113947 | CWSP - LOS GATOS 1107 – LR 60114 |  | 5786220 | UNSE | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | STCRUZ | [26 empty] | 33.5 | Project is not in the WP or in 2020 WP | 0 | 33.5 | -33.5 | 0 | 0
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | E.5014534.02 | 5786052 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 0 | 4588 | 4588 | 0.86894 | 0 | 0.86894 | [5 empty] | 1 | -99999 | 100000 | 5640.1 | 0 | 94359.9 | On/Under Budget | 303925 | 10.5 | 0 | 10.5 | 0 | 362.4 | 5067.2 | 210.5 | Project is not in the WP or in 2020 WP | 0 | 269 | -269 | 269 | -269 | 145.9 | 32.3 | 32.3 | 10.5 | 10.5 | 10.5 | 10.8 | 10.8 | 5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303877.1 | 0 | 0 | 0 | 303877.1
35112968 | WOODSIDE 1101 RECOND FUSE 1097 ZONE |  | 5786098 | UNSE | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | SNMATEO | [26 empty] | 29.6 | Project is not in the WP or in 2020 WP | 0 | 29.6 | -29.6 | 0 | 0
35112340 | *CANC*CWSP - MIWUK 1701 - LR 10600 |  | 5530178 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35112126 | BR-01-03-W (E) PARAGALIA PARB |  | 5786123 | UNSE | 08W | AVP4 | Aaron Patane |  |  |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35112157 | *CANC*CWSP - MIWUK 1701 - LR 10600 |  | 5530178 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35112158 | *CANC*CWSP - MIWUK 1701 - LR 10600 |  | 5530178 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35112159 | *CANC*CWSP - MIWUK 1701 - LR 10600 |  | 5530178 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35115080 | BR-02-10-W (E) HARVEY RD PARB |  | 5786123 | UNSE | 08W | VEY1 | Virginia E Stauffer | CJPN | Corina Parker |  |  | 2021 |  |  | CHICO | North Valley Assets | [11 empty] | 1 | 1 | 0 | 2355 | 0 | -2355 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2355 | Request 2021 Budget | 0 | 2355 | -2355 | 2355 | -2355 | 0 | 2341.4 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35115084 | BR-01-11-W (E) MONTNA DR PARB |  | 5786123 | UNSE | 08W | AVP4 | Aaron Patane |  |  |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | E.5015493.01 | 5786589 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | SNJOSE | De Anza Assets | 8554 | 0 | 8554 | 1.6201 | 0 | 1.6201 | [5 empty] | 500000 | 400000 | 100000 | 78408.4 | 0 | 21591.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 35907.9 | 90032.3 | -47531.9 | Project is not in the WP or in 2020 WP | 0 | -47531.9 | 47531.9 | -47531.9 | 47531.9 | 952.7 | -48930.8 | 446.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | E.5014535.05 | 5786605 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 0 | 4593.6 | 4593.6 | 0.87 | 0 | 0.87 | [5 empty] | 10000 | 0 | 10000 | 4870 | 0 | 5130 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 153.8 | 4519.2 | 197.1 | Project is not in the WP or in 2020 WP | 0 | 197.1 | -197.1 | 197.1 | -197.1 | 141.3 | 27.9 | 27.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | E.5014535.06 | 5786604 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 0 | 2164.8 | 2164.8 | 0.41 | 0 | 0.41 | [5 empty] | 10000 | 0 | 10000 | 5712.7 | 0 | 4287.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 250.8 | 5250.2 | 211.7 | Project is not in the WP or in 2020 WP | 0 | 211.7 | -211.7 | 211.7 | -211.7 | 146.3 | 32.7 | 32.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35134806 | BR-03-14-W (E) PENTZ RD, PARB |  | 5786123 | UNSE | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35135005 | MVWF ALTO 1125 MUIR WOOD DR,MUIR BEACH |  | 5530168 | UNSE | 08W | S2J9 | Steven Kenneth Jackson | A8G1 | Alvin Galesic |  |  | Not in the WP | 2022 |  | SNRAFAEL | North Bay Assets | [11 empty] | 50000 | 0 | 50000 | 8238.3 | 0 | 41761.7 | On/Under Budget | 1055415.6 | 0 | 0 | 0 | 0 | 7358.6 | 879.7 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1055415.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1055415.6 | 2021-04-02 | 147261 | BL-A | BL-A 35135005_MVWF ALTO 1125 MUIR WOOD DR,MUIR BEACH_08W - AUG 2021 | 2020-08-19 | 2022-06-08 | Not Started |  |  | Not Started | 2022-07-14 | Not Started | 2022-07-14 | Not Started | [9 empty] | 2022-08-26 | Not Started | [8 empty] | 2022-12-21 | Not Started | 2021-08-04 | 2022-12-21 | -504 | Behind Schedule | Not Started |  |  |  | 2023-08-10 | Not Started
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | 5530164 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | Not in the WP |  | SH | CLRLAKE | Humboldt Division Assets | 0 | 6828 | 6828 | 1.2932 | 0 | 1.2932 | [5 empty] | 80000 | 0 | 80000 | 6965.2 | 0 | 73034.8 | On/Under Budget | 10764.7 | 3588.2 | 0 | 3588.2 | 0 | 0 | 3861.1 | 3104.1 | Project is not in the WP or in 2020 WP | 0 | 17456.9 | -17456.9 | 17456.9 | -17456.9 | 459.9 | 2644.2 | 0 | 3588.2 | 3588.2 | 3588.2 | 3588.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157812 | BL-A | BL-A 35137599_CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11_08W - DD 210305 Mar. 2021 | 2021-03-19 | 2021-05-31 | Not Started | 2021-07-06 | 2021-07-12 | Not Started | 2021-07-05 | Not Started | 2021-08-02 | Not Started | 2021-06-01 | 2021-06-01 | Not Started | 2021-06-02 | 2021-06-22 | Not Started | 2021-07-06 | 2021-07-19 | Not Started | 2021-08-25 | Not Started | 2021-08-25 | Not Started | 2021-09-07 | Not Started | 2021-08-25 | Not Started | 2021-12-07 | Not Started | 2022-01-05 | Not Started | 2022-02-24 | 2022-03-08 | -12 | Behind Schedule | Not Started | 2022-03-09 | 2022-03-22 | Not Started | 2022-05-05 | Not Started
35144588 | PSPS MITIGATION - ROSSMOOR 1106 |  | 5530161 | UNSE | 08W | D7CJ | Danielle Marie Caponpon |  |  |  |  | Not in the WP |  |  | WALNTCRK | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35144589 | PSPS MITIGATION - MORAGA 1103 |  | 5530161 | UNSE | 08W | MUSF | Maria Sonia Silva |  |  |  |  | Not in the WP |  |  | WALNTCRK | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35144591 | PSPS MITIGATION - STAFFORD 1101 - PH1 |  | 5530168 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | SNRAFAEL | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35144592 | PSPS MITIGATION - STAFFORD 1101 - PH2 |  | 5530168 | UNSE | 08W | J1NV | Jonathan Nicolas |  |  |  |  | Not in the WP |  |  | SNRAFAEL | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35148272 | CREATED IN ERROR |  | 5785220 | UNSE | 08W | J1PE | Jaime Pantoja-Martinez | B4HS | Brandon Hayashi | J7TY | Jace Thorsen | Not in the WP |  |  | SONORA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155680 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.02 |  | 5789366 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 6990 | 6990 | 1.3239 | 0 | 1.3239 | [19 empty] | 22 | Project is not in the WP or in 2020 WP | 0 | 22 | -22 | 0 | 0
35155681 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.03 |  | 5789378 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 1335 | 1335 | 0.25284 | 0 | 0.25284 | [19 empty] | 13.4 | Project is not in the WP or in 2020 WP | 0 | 13.4 | -13.4 | 0 | 0
35155682 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.04 |  | 5789379 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 1930 | 1930 | 0.36553 | 0 | 0.36553 | [19 empty] | 8.9 | Project is not in the WP or in 2020 WP | 0 | 8.9 | -8.9 | 0 | 0
35155683 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.05 |  | 5789380 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 6550 | 6550 | 1.2405 | 0 | 1.2405 | [19 empty] | 39.6 | Project is not in the WP or in 2020 WP | 0 | 39.6 | -39.6 | 0 | 0
35155684 | CWSP-BRUNSWICK 1105 LR2140 - PH 1.06 |  | 5789381 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 3288 | 3288 | 0.62273 | 0 | 0.62273 | [19 empty] | 8.9 | Project is not in the WP or in 2020 WP | 0 | 8.9 | -8.9 | 0 | 0
35155685 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.07 |  | 5789382 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 3780 | 3780 | 0.71591 | 0 | 0.71591 | [19 empty] | 8.9 | Project is not in the WP or in 2020 WP | 0 | 8.9 | -8.9 | 0 | 0
35155686 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.08 |  | 5789383 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 3240 | 3240 | 0.61364 | 0 | 0.61364 | [19 empty] | 4.5 | Project is not in the WP or in 2020 WP | 0 | 4.5 | -4.5 | 0 | 0
35155687 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.09 |  | 5789384 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 8886 | 8886 | 1.683 | 0 | 1.683 | [19 empty] | 4.5 | Project is not in the WP or in 2020 WP | 0 | 4.5 | -4.5 | 0 | 0
35155688 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.10 |  | 5789385 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 2961 | 2961 | 0.5608 | 0 | 0.5608 | [19 empty] | 4.5 | Project is not in the WP or in 2020 WP | 0 | 4.5 | -4.5 | 0 | 0
35155689 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.11 |  | 5789386 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 4900 | 4900 | 0.92803 | 0 | 0.92803 | [19 empty] | 4.5 | Project is not in the WP or in 2020 WP | 0 | 4.5 | -4.5 | 0 | 0
35155690 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.12 |  | 5789387 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 5082 | 5082 | 0.9625 | 0 | 0.9625 | [19 empty] | 4.5 | Project is not in the WP or in 2020 WP | 0 | 4.5 | -4.5 | 0 | 0
35155691 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.13 |  | 5789388 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 3010 | 3010 | 0.57008 | 0 | 0.57008 | [19 empty] | 4.5 | Project is not in the WP or in 2020 WP | 0 | 4.5 | -4.5 | 0 | 0
35155692 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.14 |  | 5789389 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 5268 | 5268 | 0.99773 | 0 | 0.99773 | [19 empty] | 4.5 | Project is not in the WP or in 2020 WP | 0 | 4.5 | -4.5 | 0 | 0
35155693 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.15 |  | 5789390 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 6100 | 6100 | 1.1553 | 0 | 1.1553 | [19 empty] | 5.5 | Project is not in the WP or in 2020 WP | 0 | 5.5 | -5.5 | 0 | 0
35155694 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.16 |  | 5789391 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 5900 | 5900 | 1.1174 | 0 | 1.1174 | [19 empty] | 4.5 | Project is not in the WP or in 2020 WP | 0 | 4.5 | -4.5 | 0 | 0
35155695 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.02 |  | 5789392 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 5465 | 5465 | 1.035 | 0 | 1.035 | [19 empty] | 8.3 | Project is not in the WP or in 2020 WP | 0 | 8.3 | -8.3 | 0 | 0
35155696 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.03 |  | 5789393 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 2440 | 2440 | 0.46212 | 0 | 0.46212 | [19 empty] | 13.1 | Project is not in the WP or in 2020 WP | 0 | 13.1 | -13.1 | 0 | 0
35155697 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.04 |  | 5789394 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 2080 | 2080 | 0.39394 | 0 | 0.39394 | [19 empty] | 4.5 | Project is not in the WP or in 2020 WP | 0 | 4.5 | -4.5 | 0 | 0
35155698 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.05 |  | 5789395 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 6332 | 6332 | 1.1992 | 0 | 1.1992 | [19 empty] | 4.5 | Project is not in the WP or in 2020 WP | 0 | 4.5 | -4.5 | 0 | 0
35155699 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.06 |  | 5789396 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 2415 | 2415 | 0.45739 | 0 | 0.45739 | [19 empty] | 4.5 | Project is not in the WP or in 2020 WP | 0 | 4.5 | -4.5 | 0 | 0
35155740 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.07 |  | 5789397 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 3636 | 3636 | 0.68864 | 0 | 0.68864 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155741 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.08 |  | 5789398 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 890 | 890 | 0.16856 | 0 | 0.16856 | [19 empty] | 4.5 | Project is not in the WP or in 2020 WP | 0 | 4.5 | -4.5 | 0 | 0
35155742 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.09 |  | 5789399 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 6100 | 6100 | 1.1553 | 0 | 1.1553 | [19 empty] | 13.1 | Project is not in the WP or in 2020 WP | 0 | 13.1 | -13.1 | 0 | 0
35155743 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.10 |  | 5789400 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 3692 | 3692 | 0.69924 | 0 | 0.69924 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155744 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.11 |  | 5789401 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 2671 | 2671 | 0.50587 | 0 | 0.50587 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155746 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.12 |  | 5789402 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 5910 | 5910 | 1.1193 | 0 | 1.1193 | [19 empty] | 8.9 | Project is not in the WP or in 2020 WP | 0 | 8.9 | -8.9 | 0 | 0
35155747 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.13 |  | 5789403 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 4025 | 4025 | 0.76231 | 0 | 0.76231 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155748 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.14 |  | 5789404 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 2740 | 2740 | 0.51894 | 0 | 0.51894 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155749 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.15 |  | 5789405 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 2662 | 2662 | 0.50417 | 0 | 0.50417 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155750 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.16 |  | 5789406 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 8872 | 8872 | 1.6803 | 0 | 1.6803 | [19 empty] | 8.9 | Project is not in the WP or in 2020 WP | 0 | 8.9 | -8.9 | 0 | 0
35155751 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.17 |  | 5789407 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 2627 | 2627 | 0.49754 | 0 | 0.49754 | [19 empty] | 13.1 | Project is not in the WP or in 2020 WP | 0 | 13.1 | -13.1 | 0 | 0
35155752 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.02 |  | 5789408 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 2727 | 2727 | 0.51648 | 0 | 0.51648 | [19 empty] | 3.9 | Project is not in the WP or in 2020 WP | 0 | 3.9 | -3.9 | 0 | 0
35155753 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.03 |  | 5789409 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 5611 | 5611 | 1.0627 | 0 | 1.0627 | [19 empty] | 14 | Project is not in the WP or in 2020 WP | 0 | 14 | -14 | 0 | 0
35155754 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.04 |  | 5789410 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 6626 | 6626 | 1.2549 | 0 | 1.2549 | [19 empty] | 9.5 | Project is not in the WP or in 2020 WP | 0 | 9.5 | -9.5 | 0 | 0
35155755 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.05 |  | 5789411 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 1431 | 1431 | 0.27102 | 0 | 0.27102 | [19 empty] | 3.9 | Project is not in the WP or in 2020 WP | 0 | 3.9 | -3.9 | 0 | 0
35155756 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.06 |  | 5789412 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 9214 | 9214 | 1.7451 | 0 | 1.7451 | [19 empty] | 32.7 | Project is not in the WP or in 2020 WP | 0 | 32.7 | -32.7 | 0 | 0
35155757 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.07 |  | 5789413 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 2913 | 2913 | 0.5517 | 0 | 0.5517 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155758 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.08 |  | 5789414 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 3510 | 3510 | 0.66477 | 0 | 0.66477 | [19 empty] | 9.5 | Project is not in the WP or in 2020 WP | 0 | 9.5 | -9.5 | 0 | 0
35155759 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.09 |  | 5789415 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 3500 | 3500 | 0.66288 | 0 | 0.66288 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155840 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.10 |  | 5789416 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 2596 | 2596 | 0.49167 | 0 | 0.49167 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155841 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.11 |  | 5789417 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 4491 | 4491 | 0.85057 | 0 | 0.85057 | [19 empty] | 14 | Project is not in the WP or in 2020 WP | 0 | 14 | -14 | 0 | 0
35155842 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.12 |  | 5789418 | UNSE | 08W | EXNN | Emilio Nunez |  |  |  |  | Not in the WP |  |  | GRSSVLLY |  | 0 | 808 | 808 | 0.15303 | 0 | 0.15303 | [19 empty] | 8.6 | Project is not in the WP or in 2020 WP | 0 | 8.6 | -8.6 | 0 | 0
35118702 | BR-11-03-W (E) GREGS WAY, PARB |  | 5786123 | UNSE | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | 2020 |  |  | CHICO | North Valley Assets | [10 empty] | Division | 1 | -4471274 | 4471275 | 3314403.6 | 0 | 1156871.4 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 399.3 | 1998776.9 | 1315227.4 | Project is not in the WP or in 2020 WP | 0 | 1315227.4 | -1315227.4 | 1315227.4 | -1315227.4 | 316957.8 | 42613.4 | 955656.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35118702 | BR-11-03-W (E) GREGS WAY, PARB |  | 5786123 | UNSE | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | 2020 |  |  | CHICO | North Valley Assets | [10 empty] | Division | 1 | -4471274 | 4471275 | 3314403.6 | 0 | 1156871.4 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 399.3 | 1998776.9 | 1315227.4 | Project is not in the WP or in 2020 WP | 0 | 1315227.4 | -1315227.4 | 1315227.4 | -1315227.4 | 316957.8 | 42613.4 | 955656.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35118671 | BR-MG-1A-W DRAKE CT PARB |  | 5786123 | UNSE | 08W | AVP4 | Aaron Patane |  |  |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35118673 | BR-MG-4A-W WICHITA DR PARB |  | 5786123 | UNSE | 08W | AVP4 | Aaron Patane |  |  |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35118674 | BR-MG-05-W PUEBLO DR PARB |  | 5786123 | UNSE | 08W | AVP4 | Aaron Patane |  |  |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35118675 | BR-MG-05-W SHAW CIR PARB |  | 5786123 | UNSE | 08W | AVP4 | Aaron Patane |  |  |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35118700 | BR-10-01-W (E) STARLIGHT CT PARB |  | 5786123 | UNSE | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35118504 | BR-06-02-W (E) COPELAND RD PARB |  | 5786123 | UNSE | 08W | VEY1 | Virginia E Stauffer | CJPN | Corina Parker |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35118511 | BR-06-03-W (E) DEL MAR AVE PARB |  | 5786123 | UNSE | 08W | VEY1 | Virginia E Stauffer | CJPN | Corina Parker |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35118513 | BR-06-04-W (E) HEAVENLY PARB |  | 5786123 | UNSE | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35118515 | BR-07-02-W (E) YOUNG AVE PARB |  | 5786123 | UNSE | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35118516 | BR-07-04-W_03 (E) PECK LN PARB |  | 5786123 | UNSE | 08W | VEY1 | Virginia E Stauffer | CJPN | Corina Parker |  |  | 2021 |  |  | CHICO | North Valley Assets | [11 empty] | 1 | -3213348 | 3213349 | 467.8 | 0 | 3212881.2 | On/Under Budget | 2561381.4 | 644639.2 | 0 | 644639.2 | 0 | 0 | 459.7 | 8.1 | Request 2021 Budget | 0 | 3099988.9 | -3099988.9 | 3206028.7 | -3206028.7 | 2.7 | 2.7 | 2.7 | 644639.2 | 648572.3 | 652505.5 | 656547 | 531416.6 | 15436.6 | 18967.8 | 18967.8 | 18967.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35118517 | BR-07-05-W (E) FLICKER LN, PARB |  | 5786123 | UNSE | 08W | M0S4 | Michael J Shaeffer | CJPN | Corina Parker |  |  | 2021 |  |  | CHICO | North Valley Assets | [11 empty] | 1 | -7388299 | 7388300 | 4307361.8 | 0 | 3080938.2 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 23.9 | 3647580.9 | 659757 | Request 2021 Budget | 0 | 659757 | -659757 | 659757 | -659757 | 106054.3 | 343498.1 | 210204.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35118518 | BR-07-06-W (E) NIELSEN DR PARB |  | 5786123 | UNSE | 08W | VEY1 | Virginia E Stauffer | CJPN | Corina Parker |  |  | 2021 |  |  | CHICO | North Valley Assets | [11 empty] | 1 | 1 | 0 | 1037.7 | 0 | -1037.7 | OverRun | 50.3 | 6.1 | 0 | 6.1 | 0 | 0 | 1019.6 | 18 | Request 2021 Budget | 0 | 74.1 | -74.1 | 74.1 | -74.1 | 6.2 | 5.9 | 5.9 | 6.1 | 6.1 | 6.1 | 6.3 | 6.3 | 6.3 | 6.3 | 6.3 | 6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35118519 | BR-07-08-W (E) FOLAND RD PARB |  | 5786123 | UNSE | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | 2021 |  |  | CHICO | North Valley Assets | [10 empty] | Contract | 1 | 1 | 0 | 225.5 | 0 | -225.5 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 72.2 | 153.4 | Request 2021 Budget | 0 | 153.4 | -153.4 | 153.4 | -153.4 | 150.8 | 1.3 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35118662 | BR-11-07-W (E) APPLE LN PARB |  | 5786123 | UNSE | 08W | AVP4 | Aaron Patane |  |  |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35117455 | BR-02-04-W (E) HERMAN PARB |  | 5786123 | UNSE | 08W | AVP4 | Aaron Patane |  |  |  |  | 2021 |  |  | CHICO | [26 empty] | 131.6 | Request 2021 Budget | 0 | 131.6 | -131.6 | 0 | 0
35117986 | BR-02-08-W (E) DIAMOND LN PARB |  | 5786123 | UNSE | 08W | VEY1 | Virginia E Stauffer | CJPN | Corina Parker |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35118422 | BR-02-13-W (E) LANCASTER DR PARB |  | 5786123 | UNSE | 08W | AVP4 | Aaron Patane |  |  |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35118425 | BR-04-04-W (E) VALLEY VIEW PARB |  | 5786123 | UNSE | 08W | VEY1 | Virginia E Stauffer | CJPN | Corina Parker |  |  | 2021 |  |  | CHICO | North Valley Assets | [11 empty] | 1 | 1 | 0 | 211.3 | 0 | -211.3 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 207.6 | 3.7 | Request 2021 Budget | 0 | 3.7 | -3.7 | 3.7 | -3.7 | 1.3 | 1.2 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35118433 | BR-04-10/11-W (E) CRESTVIEW PARB |  | 5786123 | UNSE | 08W | AVP4 | Aaron Patane |  |  |  |  | 2021 |  |  | CHICO | [27 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35118438 | BR-11-01-W (E) FOSTER RD, PARB |  | 5786123 | UNSE | 08W | M8D1 | Matthew D'Luzansky | L7SA | Lisa Spath |  |  | 2021 |  |  | CHICO | North Valley Assets | [11 empty] | 1 | 1 | 0 | 3068.1 | 0 | -3068.1 | OverRun | 0 | 0 | 0 | 0 | 0 | 2908.1 | 106.4 | 53.6 | Request 2021 Budget | 0 | 53.6 | -53.6 | 53.6 | -53.6 | 18.4 | 17.6 | 17.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35227651 | CWSP - VACAVILLE 11046542 PH 1.2 |  | 5794545 | UNSE | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | VACAVLLE |  | 0 | 18216 | 18216 | 3.45 | 0 | 3.45 | [20 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35227652 | CWSP - VACAVILLE 11046542 PH 1.3 |  | 5794545 | UNSE | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | VACAVLLE |  | 2904 | 2904 | 5808 | 1.1 | 0 | 1.1 | [20 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35227653 | CWSP - VACAVILLE 11046542 PH 1.4 |  | 5794545 | UNSE | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | VACAVLLE |  | 0 | 14414.4 | 14414.4 | 2.73 | 0 | 2.73 | [20 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35227654 | CWSP - VACAVILLE 11046542 PH 1.5 |  | 5794545 | UNSE | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | 2021 |  | SH | VACAVLLE |  | 0 | 2798.4 | 2798.4 | 0.53 | 0 | 0.53 | [20 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | E.5034694.01.02 | 5794544 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2021 |  | SH - Remote Grid | ANTIOCH | Diablo Assets | 0 | 19905.6 | 19905.6 | 3.77 | 0 | 3.77 | [5 empty] | 450000 | 0 | 450000 | 828.3 | 0 | 449171.7 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 828.3 | Request 2021 Budget | 0 | 828.3 | -828.3 | 828.3 | -828.3 | 0 | 116.4 | 711.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157131 | BL-A | BL-A CWSP - KIRKER 2104442850 PH 2 - Mar. 2021 | 2021-03-07 | 2021-09-16 | Not Started | 2021-12-10 | 2021-12-16 | Not Started | 2021-12-09 | Not Started | 2022-01-06 | Not Started | 2021-09-17 | 2021-09-17 | Not Started | 2021-09-20 | 2021-10-08 | Not Started | 2021-12-10 | 2021-12-30 | Not Started | 2022-01-31 | Not Started |  |  |  |  | 2022-01-31 | Not Started | 2022-10-31 | Not Started | 2022-11-07 | Not Started | 2023-01-06 | 2023-01-06 | 0 | On/ Ahead Schedule | Not Started | 2023-02-21 | 2023-03-06 | Not Started | 2023-03-31 | Not Started
35227656 | CWSP - VACAVILLE 11046542 - PH 2.3 |  | 5794545 | UNSE | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | VACAVLLE |  | 5280 | 1742.4 | 7022.4 | 1.33 | 0 | 1.33 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35227657 | CWSP - VACAVILLE 11046542 - PH 2.4 |  | 5794545 | UNSE | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | VACAVLLE |  | 0 | 2428.8 | 2428.8 | 0.46 | 0 | 0.46 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35227658 | CWSP - VACAVILLE 11046542 - PH 2.5 |  | 5794545 | UNSE | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | VACAVLLE |  | 1372.8 | 1478.4 | 2851.2 | 0.54 | 0 | 0.54 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35227659 | CWSP - VACAVILLE 11046542 - PH 2.6 |  | 5794545 | UNSE | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | VACAVLLE |  | 0 | 1267.2 | 1267.2 | 0.24 | 0 | 0.24 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | E.5034610.01.14 | 5794205 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 2112 | 2112 | 0.4 | 0 | 0.4 |  |  |  |  | GC | 1 | 1 | 0 | 898 | 0 | -898 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 898 | Request 2021 Budget | 0 | 898 | -898 | 898 | -898 | 0 | 0 | 898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157823 | BL-A | BL-A 35227868_CWSP - Middletown 1103 - LR 830 PH1.9_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-21 | Not Started | 2021-06-28 | 2021-07-02 | Not Started | 2021-06-25 | Not Started | 2021-07-23 | Not Started | 2021-05-24 | 2021-05-24 | Not Started | 2021-05-25 | 2021-06-14 | Not Started | 2021-06-28 | 2021-07-09 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-30 | Not Started | 2021-08-17 | Not Started | 2021-11-29 | Not Started | 2021-12-28 | Not Started | 2022-02-24 | 2022-02-28 | -4 | Behind Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-04-27 | Not Started
35227870 | CWSP - VACAVILLE 11046542 - PH 2.2 |  | 5794545 | UNSE | 08W | FXA7 | Fernando Armas | T1DA | Tracy Daughtery | J7TY | Jace Thorsen | Not in the WP |  | SH | VACAVLLE |  | 316.8 | 7180.8 | 7497.6 | 1.42 | 0 | 1.42 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35228082 | BR-14-04-W (E) ARROWHEAD DR PARB |  | 5786123 | UNSE | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP |  |  | CHICO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35228083 | BR-14-05-W (E) HILLPARK LN DR PARB |  | 5786123 | UNSE | 08W | S4K5 | Scot Krenek | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP |  |  | CHICO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | E.5034610.01.15 | 5794205 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 7867 | 0 | 7867 | 1.49 | 0 | 1.49 |  |  |  |  | GC | 1 | 1 | 0 | 898 | 0 | -898 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 898 | Request 2021 Budget | 0 | 898 | -898 | 898 | -898 | 0 | 0 | 898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157807 | BL-A | BL-A 35228186_CWSP - Middletown 1103 - LR 830 PH2.2_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-06-07 | Not Started | 2021-10-05 | 2021-10-11 | Not Started | 2021-10-04 | Not Started | 2021-11-01 | Not Started | 2021-06-08 | 2021-06-08 | Not Started | 2021-06-09 | 2021-06-29 | Not Started | 2021-10-05 | 2021-10-18 | Not Started | 2021-11-24 | Not Started | 2021-11-24 | Not Started | 2021-12-07 | Not Started | 2021-11-24 | Not Started | 2022-03-08 | Not Started | 2022-04-06 | Not Started | 2022-07-08 | 2022-06-07 | 31 | On/ Ahead Schedule | Not Started | 2022-06-08 | 2022-06-21 | Not Started | 2022-08-04 | Not Started
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | E.5034610.01.11 | 5794205 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 3274 | 0 | 3274 | 0.62008 | 0 | 0.62008 |  |  |  |  | GC | 1 | 1 | 0 | 1591.5 | 0 | -1591.5 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1591.5 | Request 2021 Budget | 0 | 1591.5 | -1591.5 | 1591.5 | -1591.5 | 0 | 0 | 1591.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157806 | BL-A | BL-A 35227864_CWSP - Middletown 1103 - LR 830 PH1.6_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-06-07 | Not Started | 2021-10-05 | 2021-10-11 | Not Started | 2021-10-04 | Not Started | 2021-11-01 | Not Started | 2021-06-08 | 2021-06-08 | Not Started | 2021-06-09 | 2021-06-29 | Not Started | 2021-10-05 | 2021-10-18 | Not Started | 2021-11-24 | Not Started | 2021-11-24 | Not Started | 2021-12-07 | Not Started | 2021-11-24 | Not Started | 2022-03-08 | Not Started | 2022-04-06 | Not Started | 2022-07-08 | 2022-06-07 | 31 | On/ Ahead Schedule | Not Started | 2022-06-08 | 2022-06-21 | Not Started | 2022-08-04 | Not Started
35231620 | CWSP - HIGHLANDS 1102628 PH 1.2 |  | 5794549 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | Not in the WP |  | SH | LAKEPORT |  | 13740 | 0 | 13740 | 2.6023 | 0 | 2.6023 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35231621 | CWSP - HIGHLANDS 1102628 PH 1.3 |  | 5794549 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | Not in the WP |  | SH | LAKEPORT |  | 13276 | 0 | 13276 | 2.5144 | 0 | 2.5144 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35231622 | CWSP - HIGHLANDS 1102628 PH 1.4 |  | 5794549 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | Not in the WP |  | SH | LAKEPORT |  | 24550 | 0 | 24550 | 4.6496 | 0 | 4.6496 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35231623 | CWSP - HIGHLANDS 1102628 PH 1.5 |  | 5794549 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | Not in the WP |  | SH - Remote Grid | LAKEPORT |  | 0 | 7120 | 7120 | 1.3485 | 0 | 1.3485 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35231624 | CWSP - HIGHLANDS 1102628 PH 1.6 |  | 5794549 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | Not in the WP |  | SH | LAKEPORT |  | 0 | 6228 | 6228 | 1.1795 | 0 | 1.1795 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35231625 | CWSP - HIGHLANDS 1102628 PH 1.7 |  | 5794549 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | Not in the WP |  | SH - Remote Grid | LAKEPORT |  | 0 | 4152 | 4152 | 0.78636 | 0 | 0.78636 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35231626 | CWSP - HIGHLANDS 1102628 PH 1.8 |  | 5794549 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | Not in the WP |  | SH | LAKEPORT |  | 0 | 4124 | 4124 | 0.78106 | 0 | 0.78106 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35231627 | CWSP - HIGHLANDS 1102628 PH 1.9 |  | 5794549 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | Not in the WP |  | SH | LAKEPORT |  | 0 | 1862 | 1862 | 0.35265 | 0 | 0.35265 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35231628 | CWSP - HIGHLANDS 1102628 PH 1.10 |  | 5794549 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | Not in the WP |  | SH - Remote Grid | LAKEPORT |  | 0 | 1078 | 1078 | 0.20417 | 0 | 0.20417 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35231629 | CWSP - HIGHLANDS 1102628 PH 1.11 |  | 5794549 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | Not in the WP |  | SH - Remote Grid | LAKEPORT |  | 0 | 6382 | 6382 | 1.2087 | 0 | 1.2087 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35231630 | CWSP - HIGHLANDS 1102628 PH 1.12 |  | 5794549 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | Not in the WP |  | SH | LAKEPORT |  | 0 | 1574 | 1574 | 0.29811 | 0 | 0.29811 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35231631 | CWSP - HIGHLANDS 1102628 PH 1.13 |  | 5794549 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | Not in the WP |  | SH | LAKEPORT |  | 0 | 2000 | 2000 | 0.37879 | 0 | 0.37879 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35227204 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.5 |  | 5795126 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  | SH | GRSSVLLY |  | 0 | 6864 | 6864 | 1.3 | 0 | 1.3 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35228774 | PSPS - DUNBAR 1101 - OAKMONT PH 2 |  | 5794985 | UNSE | 08W | JDLM | Jesse Lorz |  |  |  |  | Not in the WP |  | SH | STROSA |  | 5143 | 0 | 5143 | 0.97405 | 0 | 0.97405 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35228775 | PSPS - DUNBAR 1101 - OAKMONT PH 3 |  | 5794985 | UNSE | 08W | JDLM | Jesse Lorz |  |  |  |  | Not in the WP |  | SH | STROSA |  | 4679 | 0 | 4679 | 0.88617 | 0 | 0.88617 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35229043 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 1 |  | 5795419 | UNSE | 08W | JTHL | Joseph T Hembree | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  | FRRB | OROVILLE |  | 2183 | 0 | 2183 | 0.41345 | 0.41345 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | 5795612 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  | SH | REDBLUFF |  | 0 | 16051 | 16051 | 3.04 | 0 | 3.04 | [19 empty] | 18626.4 | Project is not in the WP or in 2020 WP | 0 | 18626.4 | -18626.4 | 0 | 0
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | E.5034805.01.01 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 4488 | 0 | 4488 | 0.85 | 0 | 0.85 |  |  |  |  | GC | 155000 | 0 | 155000 | 1964.7 | 0 | 153035.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1964.7 | Request 2021 Budget | 0 | 1964.7 | -1964.7 | 1964.7 | -1964.7 | 0 | 1042.3 | 922.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2022-09-09 | Not Started | 2022-09-12 | 2022-09-30 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-16 | Not Started | 2022-11-16 | Not Started | 2022-11-29 | Not Started | 2022-11-16 | Not Started | 2023-01-04 | Not Started | 2023-02-02 | Not Started | 2023-04-05 | 2023-04-05 | 0 | On/ Ahead Schedule | Not Started | 2023-04-06 | 2023-04-19 | Not Started | 2023-06-02 | Not Started
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | E.5034805.01.02 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 2006.4 | 2006.4 | 0.38 | 0 | 0.38 |  |  |  |  | GC | 155000 | 0 | 155000 | 1261.7 | 0 | 153738.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1261.7 | Request 2021 Budget | 0 | 1261.7 | -1261.7 | 1261.7 | -1261.7 | 0 | 343.4 | 918.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2022-09-09 | Not Started | 2022-09-12 | 2022-09-30 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | E.5034805.01.03 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 4646.4 | 4646.4 | 0.88 | 0 | 0.88 |  |  |  |  | GC | 155000 | 0 | 155000 | 2442.1 | 0 | 152557.9 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2442.1 | Request 2021 Budget | 0 | 2442.1 | -2442.1 | 2442.1 | -2442.1 | 0 | 343.4 | 2098.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | E.5034805.01.04 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 3484.8 | 3484.8 | 0.66 | 0 | 0.66 |  |  |  |  | GC | 155000 | 0 | 155000 | 2521.7 | 0 | 152478.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2521.7 | Request 2021 Budget | 0 | 2521.7 | -2521.7 | 2521.7 | -2521.7 | 0 | 343.4 | 2178.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2022-09-09 | Not Started | 2022-09-12 | 2022-09-30 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | E.5034805.01.05 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 3062.4 | 3062.4 | 0.58 | 0 | 0.58 |  |  |  |  | GC | 155000 | 0 | 155000 | 2175.7 | 0 | 152824.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2175.7 | Request 2021 Budget | 0 | 2175.7 | -2175.7 | 2175.7 | -2175.7 | 0 | 343.4 | 1832.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2022-09-09 | Not Started | 2022-09-12 | 2022-09-30 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | E.5034805.01.06 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 2786 | 2786 | 0.52765 | 0 | 0.52765 | [5 empty] | 67857 | 0 | 67857 | 2400.5 | 0 | 65456.5 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400.5 | Request 2021 Budget | 0 | 2400.5 | -2400.5 | 2400.5 | -2400.5 | 0 | 0 | 2400.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | E.5034805.01.07 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 1724 | 1724 | 0.32652 | 0 | 0.32652 | [5 empty] | 67857 | 0 | 67857 | 2400.5 | 0 | 65456.5 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400.5 | Request 2021 Budget | 0 | 2400.5 | -2400.5 | 2400.5 | -2400.5 | 0 | 0 | 2400.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | E.5034805.01.08 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 1243 | 1243 | 0.23542 | 0 | 0.23542 | [5 empty] | 67857 | 0 | 67857 | 2400.5 | 0 | 65456.5 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400.5 | Request 2021 Budget | 0 | 2400.5 | -2400.5 | 2400.5 | -2400.5 | 0 | 0 | 2400.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | E.5034805.01.09 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 2736 | 2736 | 0.51818 | 0 | 0.51818 | [5 empty] | 67857 | 0 | 67857 | 1028.4 | 0 | 66828.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1028.4 | Request 2021 Budget | 0 | 1028.4 | -1028.4 | 1028.4 | -1028.4 | 0 | 0 | 1028.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | E.5034805.01.10 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 2215 | 2215 | 0.41951 | 0 | 0.41951 | [5 empty] | 67857 | 0 | 67857 | 1718.2 | 0 | 66138.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1718.2 | Request 2021 Budget | 0 | 1718.2 | -1718.2 | 1718.2 | -1718.2 | 0 | 0 | 1718.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | E.5034805.01.11 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 420 | 420 | 0.079545 | 0 | 0.079545 | [5 empty] | 67857 | 0 | 67857 | 1834.1 | 0 | 66022.9 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1834.1 | Request 2021 Budget | 0 | 1834.1 | -1834.1 | 1834.1 | -1834.1 | 0 | 0 | 1834.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | E.5034805.01.12 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 1168 | 1168 | 0.22121 | 0 | 0.22121 | [5 empty] | 67857 | 0 | 67857 | 2180.8 | 0 | 65676.2 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2180.8 | Request 2021 Budget | 0 | 2180.8 | -2180.8 | 2180.8 | -2180.8 | 0 | 0 | 2180.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | E.5034805.01.13 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 5488 | 0 | 5488 | 1.0394 | 0 | 1.0394 | [5 empty] | 67857 | 0 | 67857 | 2630.2 | 0 | 65226.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2630.2 | Request 2021 Budget | 0 | 2630.2 | -2630.2 | 2630.2 | -2630.2 | 0 | 0 | 2630.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | E.5034805.01.14 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 3109 | 0 | 3109 | 0.58883 | 0 | 0.58883 | [5 empty] | 67857 | 0 | 67857 | 1344.9 | 0 | 66512.1 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344.9 | Request 2021 Budget | 0 | 1344.9 | -1344.9 | 1344.9 | -1344.9 | 0 | 0 | 1344.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35226900 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | E.5034784.01.04 | 5795128 | UNSE | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | 2021 | 2021 | SH | REDBLUFF | North Valley Assets | 0 | 3643.2 | 3643.2 | 0.69 | 0 | 0.69 | [5 empty] | 1 | 1 | 0 | 25323.5 | 0 | -25323.5 | OverRun | 0 | 0 | -25250 | 25250 | 0 | 0 | 0 | 73.5 | Request 2021 Budget | 0 | 25323.5 | -25323.5 | 25323.5 | -25323.5 | 0 | 0 | 25323.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-02-01 | 158354 | BL-A_ | BL-A_35226900_CWSP - WILDWOOD 1101 LR 1454TEHAMACO PH4_08W_Apr.2021 | 2021-04-01 | 2021-05-11 | Not Started | 2021-06-16 | 2021-06-22 | Not Started | 2021-06-15 | Not Started | 2021-07-13 | Not Started | 2021-05-12 | 2021-05-12 | Not Started | 2021-05-13 | 2021-06-02 | Not Started | 2021-06-16 | 2021-06-29 | Not Started | 2021-08-05 | Not Started | 2021-08-05 | Not Started | 2021-08-18 | Not Started | 2021-08-05 | Not Started | 2021-11-17 | Not Started | 2021-12-16 | Not Started | 2022-02-16 | 2022-02-16 | 0 | On/ Ahead Schedule | Not Started | 2022-02-17 | 2022-03-02 | Not Started | 2022-04-15 | Not Started
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | E.5034805.01.15 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 3809 | 0 | 3809 | 0.7214 | 0 | 0.7214 | [5 empty] | 67857 | 0 | 67857 | 2034.6 | 0 | 65822.4 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2034.6 | Request 2021 Budget | 0 | 2034.6 | -2034.6 | 2034.6 | -2034.6 | 0 | 0 | 2034.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | E.5034805.01.16 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 2286 | 0 | 2286 | 0.43295 | 0 | 0.43295 | [5 empty] | 67857 | 0 | 67857 | 1687.9 | 0 | 66169.1 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1687.9 | Request 2021 Budget | 0 | 1687.9 | -1687.9 | 1687.9 | -1687.9 | 0 | 0 | 1687.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | E.5034805.01.17 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 3067 | 0 | 3067 | 0.58087 | 0 | 0.58087 | [5 empty] | 67857 | 0 | 67857 | 2065.7 | 0 | 65791.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2065.7 | Request 2021 Budget | 0 | 2065.7 | -2065.7 | 2065.7 | -2065.7 | 0 | 0 | 2065.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | E.5034805.01.18 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 1839 | 0 | 1839 | 0.3483 | 0 | 0.3483 | [5 empty] | 67857 | 0 | 67857 | 1718.9 | 0 | 66138.1 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1718.9 | Request 2021 Budget | 0 | 1718.9 | -1718.9 | 1718.9 | -1718.9 | 0 | 0 | 1718.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | 5795300 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | 2022 |  | SH | LAKEPORT |  | 15183 | 0 | 15183 | 2.8756 | 0 | 2.8756 |  |  |  |  | GC | [14 empty] | 1669.9 | Request 2021 Budget | 0 | 1669.9 | -1669.9 | 0 | 0 | [25 empty] | 2021-03-19 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | 5795300 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | 2022 |  | SH | LAKEPORT |  | 0 | 834 | 834 | 0.15795 | 0 | 0.15795 |  |  |  |  | GC | [14 empty] | 2746.2 | Request 2021 Budget | 0 | 2746.2 | -2746.2 | 0 | 0 | [25 empty] | 2021-03-19 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2022-09-09 | Not Started | 2022-09-12 | 2022-09-30 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35227013 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 |  | 5795300 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | 2022 |  | SH | LAKEPORT |  | 0 | 168 | 168 | 0.031818 | 0 | 0.031818 |  |  |  |  | GC | [15 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | [25 empty] | 2021-03-19 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2022-09-09 | Not Started | 2022-09-12 | 2022-09-30 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 |  | 5795300 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | 2022 |  | SH | LAKEPORT |  | 0 | 5106 | 5106 | 0.96705 | 0 | 0.96705 |  |  |  |  | GC | [14 empty] | 911.4 | Request 2021 Budget | 0 | 911.4 | -911.4 | 0 | 0 | [25 empty] | 2021-03-19 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | 5795300 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | 2022 |  | SH | LAKEPORT |  | 0 | 6312 | 6312 | 1.1955 | 0 | 1.1955 |  |  |  |  | GC | [14 empty] | 1832.3 | Request 2021 Budget | 0 | 1832.3 | -1832.3 | 0 | 0 | [25 empty] | 2021-03-19 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2022-09-09 | Not Started | 2022-09-12 | 2022-09-30 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | 5795300 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | 2022 |  | SH | LAKEPORT |  | 0 | 1144 | 1144 | 0.21667 | 0 | 0.21667 |  |  |  |  | GC | [14 empty] | 1166.2 | Request 2021 Budget | 0 | 1166.2 | -1166.2 | 0 | 0 | [25 empty] | 2021-03-19 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2022-09-09 | Not Started | 2022-09-12 | 2022-09-30 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | 5795300 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | 2022 |  | SH | LAKEPORT |  | 2900 | 0 | 2900 | 0.54924 | 0 | 0.54924 |  |  |  |  | GC | [14 empty] | 808.6 | Request 2021 Budget | 0 | 808.6 | -808.6 | 0 | 0 | [25 empty] | 2021-04-02 |  |  |  |  | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2022-09-09 | Not Started | 2022-09-12 | 2022-09-30 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | E.5034805.01.26 | 5795300 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 4171 | 4171 | 0.78996 | 0 | 0.78996 |  |  |  |  | GC | 1 | 1 | 0 | 848.7 | 0 | -848.7 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 848.7 | Request 2021 Budget | 0 | 848.7 | -848.7 | 848.7 | -848.7 | 0 | 0 | 848.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157832 | BL-A | BL-A 35227027_ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-21 | Not Started | 2021-06-28 | 2021-07-02 | Not Started | 2021-06-25 | Not Started | 2021-07-23 | Not Started | 2021-05-24 | 2021-05-24 | Not Started | 2021-05-25 | 2021-06-14 | Not Started | 2021-06-28 | 2021-07-09 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-30 | Not Started | 2021-08-17 | Not Started | 2021-11-29 | Not Started | 2021-12-28 | Not Started | 2022-02-24 | 2022-02-28 | -4 | Behind Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-04-27 | Not Started
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | E.5034806.01.02 | 5795301 | UNSE | 08W | J1E1 | Josh Eagar | D5A8 | Daniel Arrow | MUHQ | Matt Haley | 2021 |  | SH - Remote Grid | NAPA | North Bay Assets | 0 | 6936 | 6936 | 1.3136 | 0 | 1.3136 |  |  |  |  | Contract | 237833 | 0 | 237833 | 993.3 | 0 | 236839.7 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 993.3 | Request 2021 Budget | 0 | 993.3 | -993.3 | 993.3 | -993.3 | 0 | 0 | 993.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-07-01 | Not Started | 2021-12-21 | 2021-12-27 | Not Started | 2021-12-20 | Not Started | 2022-01-17 | Not Started | 2021-07-02 | 2021-12-20 | Not Started | 2021-12-21 | 2022-01-10 | Not Started | 2021-12-21 | 2022-01-03 | Not Started | 2022-02-04 | Not Started | 2022-02-04 | Not Started | 2022-02-17 | Not Started | 2022-02-04 | Not Started | 2022-03-21 | Not Started | 2022-04-19 | Not Started | 2022-06-20 | 2022-06-20 | 0 | On/ Ahead Schedule | Not Started | 2022-06-21 | 2022-07-04 | Not Started | 2022-08-17 | Not Started
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2022 | 2022 | SH | REDDING | North Valley Assets | 4329.6 | 0 | 4329.6 | 0.82 | 0 | 0.82 |  |  |  |  | GC | 150000 | 0 | 150000 | 25468.3 | 0 | 124531.7 | On/Under Budget | 0 | 0 | -24570 | 24570 | 0 | 0 | 0 | 898.3 | Request 2021 Budget | 0 | 515114.3 | -515114.3 | 25468.3 | -25468.3 | 0 | 261.8 | 25206.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-12-29 | 158088 | BL-A_ | BL-A_35226628_SH - KESWICK 1101 LR 1586 PH 1.3_08W_Mar.2021 | 2021-03-30 | 2022-04-07 | Not Started | 2022-05-13 | 2022-05-19 | Not Started | 2022-05-12 | Not Started | 2022-06-09 | Not Started | 2022-04-08 | 2022-04-08 | Not Started | 2022-04-11 | 2022-04-29 | Not Started | 2022-05-13 | 2022-05-26 | Not Started | 2022-07-04 | Not Started | 2022-07-04 | Not Started | 2022-07-15 | Not Started | 2022-07-04 | Not Started | 2022-10-14 | Not Started | 2022-11-14 | Not Started | 2023-01-13 | 2023-01-13 | 0 | On/ Ahead Schedule | Not Started | 2023-01-16 | 2023-01-27 | Not Started | 2023-03-14 | Not Started
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2022 | 2022 | SH | REDDING | North Valley Assets | 23760 | 0 | 23760 | 4.5 | 0 | 4.5 |  |  |  |  | GC | 200000 | 0 | 200000 | 25425 | 0 | 174575 | On/Under Budget | 0 | 0 | -24570 | 24570 | 0 | 0 | 0 | 855 | Request 2021 Budget | 0 | 515071 | -515071 | 25425 | -25425 | 0 | 261.8 | 25163.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-12-29 | 158089 | BL-A_ | BL-A_35226629_SH - KESWICK 1101 LR 1586 PH 1.4_08W_Mar.2021 | 2021-03-30 | 2022-04-07 | Not Started | 2022-05-13 | 2022-05-19 | Not Started | 2022-05-12 | Not Started | 2022-06-09 | Not Started | 2022-04-08 | 2022-04-08 | Not Started | 2022-04-11 | 2022-04-29 | Not Started | 2022-05-13 | 2022-05-26 | Not Started | 2022-07-04 | Not Started | 2022-07-04 | Not Started | 2022-07-15 | Not Started | 2022-07-04 | Not Started | 2022-10-14 | Not Started | 2022-11-14 | Not Started | 2023-01-13 | 2023-01-13 | 0 | On/ Ahead Schedule | Not Started | 2023-01-16 | 2023-01-27 | Not Started | 2023-03-14 | Not Started
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | E.5034805.01.29 | 5795300 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 7287 | 0 | 7287 | 1.3801 | 0 | 1.3801 |  |  |  |  | GC | 1 | 1 | 0 | 1820.8 | 0 | -1820.8 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1820.8 | Request 2021 Budget | 0 | 1820.8 | -1820.8 | 1820.8 | -1820.8 | 0 | 0 | 1820.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157835 | BL-A | BL-A 35227030_ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-21 | Not Started | 2021-06-28 | 2021-07-02 | Not Started | 2021-06-25 | Not Started | 2021-07-23 | Not Started | 2021-05-24 | 2021-05-24 | Not Started | 2021-05-25 | 2021-06-14 | Not Started | 2021-06-28 | 2021-07-09 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-30 | Not Started | 2021-08-17 | Not Started | 2021-11-29 | Not Started | 2021-12-28 | Not Started | 2022-02-24 | 2022-02-28 | -4 | Behind Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-04-27 | Not Started
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | E.5034805.01.30 | 5795300 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 8184 | 0 | 8184 | 1.55 | 0 | 1.55 |  |  |  |  | GC | 1 | 1 | 0 | 2198.6 | 0 | -2198.6 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2198.6 | Request 2021 Budget | 0 | 2198.6 | -2198.6 | 2198.6 | -2198.6 | 0 | 0 | 2198.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157836 | BL-A | BL-A 35227031_ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-21 | Not Started | 2021-06-28 | 2021-07-02 | Not Started | 2021-06-25 | Not Started | 2021-07-23 | Not Started | 2021-05-24 | 2021-05-24 | Not Started | 2021-05-25 | 2021-06-14 | Not Started | 2021-06-28 | 2021-07-09 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-30 | Not Started | 2021-08-17 | Not Started | 2021-11-29 | Not Started | 2021-12-28 | Not Started | 2022-02-24 | 2022-02-28 | -4 | Behind Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-04-27 | Not Started
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | E.5034608.01.03 | 5794207 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 6970 | 0 | 6970 | 1.3201 | 0 | 1.3201 |  |  |  |  | GC | 1 | 1 | 0 | 768.4 | 0 | -768.4 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 768.4 | Request 2021 Budget | 0 | 768.4 | -768.4 | 768.4 | -768.4 | 0 | 0 | 768.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157794 | BL-A | BL-A 35227160_CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-29 | Not Started | 2021-11-26 | 2021-12-02 | Not Started | 2021-11-25 | Not Started | 2021-12-23 | Not Started | 2021-07-30 | 2021-07-30 | Not Started | 2021-08-02 | 2021-08-20 | Not Started | 2021-11-26 | 2021-12-09 | Not Started | 2022-01-17 | Not Started | 2022-01-17 | Not Started | 2022-01-28 | Not Started | 2022-01-17 | Not Started | 2022-04-29 | Not Started | 2022-05-30 | Not Started | 2022-07-29 | 2022-07-29 | 0 | On/ Ahead Schedule | Not Started | 2022-08-01 | 2022-08-12 | Not Started | 2022-09-27 | Not Started
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | E.5034608.01.04 | 5794207 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 3907 | 3907 | 0.73996 | 0 | 0.73996 |  |  |  |  | GC | 1 | 1 | 0 | 687.3 | 0 | -687.3 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687.3 | Request 2021 Budget | 0 | 687.3 | -687.3 | 687.3 | -687.3 | 0 | 0 | 687.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157795 | BL-A | BL-A 35227161_CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-08 | Not Started | 2021-11-05 | 2021-11-11 | Not Started | 2021-11-04 | Not Started | 2021-12-02 | Not Started | 2021-07-09 | 2021-07-09 | Not Started | 2021-07-12 | 2021-07-30 | Not Started | 2021-11-05 | 2021-11-18 | Not Started | 2021-12-27 | Not Started | 2021-12-27 | Not Started | 2022-01-07 | Not Started | 2021-12-27 | Not Started | 2022-04-08 | Not Started | 2022-05-09 | Not Started | 2022-07-08 | 2022-07-08 | 0 | On/ Ahead Schedule | Not Started | 2022-07-11 | 2022-07-22 | Not Started | 2022-09-06 | Not Started
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | E.5034608.01.05 | 5794207 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 1690 | 0 | 1690 | 0.32008 | 0 | 0.32008 |  |  |  |  | GC | 1 | 1 | 0 | 768.4 | 0 | -768.4 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 768.4 | Request 2021 Budget | 0 | 768.4 | -768.4 | 768.4 | -768.4 | 0 | 0 | 768.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157796 | BL-A | BL-A 35227162_CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-08 | Not Started | 2021-11-05 | 2021-11-11 | Not Started | 2021-11-04 | Not Started | 2021-12-02 | Not Started | 2021-07-09 | 2021-07-09 | Not Started | 2021-07-12 | 2021-07-30 | Not Started | 2021-11-05 | 2021-11-18 | Not Started | 2021-12-27 | Not Started | 2021-12-27 | Not Started | 2022-01-07 | Not Started | 2021-12-27 | Not Started | 2022-04-08 | Not Started | 2022-05-09 | Not Started | 2022-07-08 | 2022-07-08 | 0 | On/ Ahead Schedule | Not Started | 2022-07-11 | 2022-07-22 | Not Started | 2022-09-06 | Not Started
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | E.5034608.01.06 | 5794207 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 2429 | 2429 | 0.46004 | 0 | 0.46004 |  |  |  |  | GC | 1 | 1 | 0 | 687.3 | 0 | -687.3 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687.3 | Request 2021 Budget | 0 | 687.3 | -687.3 | 687.3 | -687.3 | 0 | 0 | 687.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157797 | BL-A | BL-A 35227163_CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-08 | Not Started | 2021-11-05 | 2021-11-11 | Not Started | 2021-11-04 | Not Started | 2021-12-02 | Not Started | 2021-07-09 | 2021-07-09 | Not Started | 2021-07-12 | 2021-07-30 | Not Started | 2021-11-05 | 2021-11-18 | Not Started | 2021-12-27 | Not Started | 2021-12-27 | Not Started | 2022-01-07 | Not Started | 2021-12-27 | Not Started | 2022-04-08 | Not Started | 2022-05-09 | Not Started | 2022-07-08 | 2022-07-08 | 0 | On/ Ahead Schedule | Not Started | 2022-07-11 | 2022-07-22 | Not Started | 2022-09-06 | Not Started
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | E.5034608.01.07 | 5794207 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 4752 | 4752 | 0.9 | 0 | 0.9 |  |  |  |  | GC | 1 | 1 | 0 | 687.3 | 0 | -687.3 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687.3 | Request 2021 Budget | 0 | 687.3 | -687.3 | 687.3 | -687.3 | 0 | 0 | 687.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157798 | BL-A | BL-A 35227164_CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-08 | Not Started | 2021-11-05 | 2021-11-11 | Not Started | 2021-11-04 | Not Started | 2021-12-02 | Not Started | 2021-07-09 | 2021-07-09 | Not Started | 2021-07-12 | 2021-07-30 | Not Started | 2021-11-05 | 2021-11-18 | Not Started | 2021-12-27 | Not Started | 2021-12-27 | Not Started | 2022-01-07 | Not Started | 2021-12-27 | Not Started | 2022-04-08 | Not Started | 2022-05-09 | Not Started | 2022-07-08 | 2022-07-08 | 0 | On/ Ahead Schedule | Not Started | 2022-07-11 | 2022-07-22 | Not Started | 2022-09-06 | Not Started
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | E.5034610.01.04 | 5794205 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 5333 | 0 | 5333 | 1.01 | 0 | 1.01 |  |  |  |  | GC | 1 | 1 | 0 | 1380.8 | 0 | -1380.8 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380.8 | Request 2021 Budget | 0 | 1380.8 | -1380.8 | 1380.8 | -1380.8 | 0 | 0 | 1380.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157803 | BL-A | BL-A 35227165_CWSP - MIDDLETOWN 1103 - LR 830 PH3.2_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-29 | Not Started | 2021-11-26 | 2021-12-02 | Not Started | 2021-11-25 | Not Started | 2021-12-23 | Not Started | 2021-07-30 | 2021-07-30 | Not Started | 2021-08-02 | 2021-08-20 | Not Started | 2021-11-26 | 2021-12-09 | Not Started | 2022-01-17 | Not Started | 2022-01-17 | Not Started | 2022-01-28 | Not Started | 2022-01-17 | Not Started | 2022-04-29 | Not Started | 2022-05-30 | Not Started | 2022-07-29 | 2022-07-29 | 0 | On/ Ahead Schedule | Not Started | 2022-08-01 | 2022-08-12 | Not Started | 2022-09-27 | Not Started
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | E.5034610.01.05 | 5794205 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 9504 | 0 | 9504 | 1.8 | 0 | 1.8 |  |  |  |  | GC | 1 | 1 | 0 | 860.7 | 0 | -860.7 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860.7 | Request 2021 Budget | 0 | 860.7 | -860.7 | 860.7 | -860.7 | 0 | 0 | 860.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157804 | BL-A | BL-A 35227167_CWSP - Middletown 1103 - LR 830 PH3.3_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-29 | Not Started | 2021-11-26 | 2021-12-02 | Not Started | 2021-11-25 | Not Started | 2021-12-23 | Not Started | 2021-07-30 | 2021-07-30 | Not Started | 2021-08-02 | 2021-08-20 | Not Started | 2021-11-26 | 2021-12-09 | Not Started | 2022-01-17 | Not Started | 2022-01-17 | Not Started | 2022-01-28 | Not Started | 2022-01-17 | Not Started | 2022-04-29 | Not Started | 2022-05-30 | Not Started | 2022-07-29 | 2022-07-29 | 0 | On/ Ahead Schedule | Not Started | 2022-08-01 | 2022-08-12 | Not Started | 2022-09-27 | Not Started
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | E.5034610.01.06 | 5794205 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 8290 | 0 | 8290 | 1.5701 | 0 | 1.5701 |  |  |  |  | GC | 1 | 1 | 0 | 860.7 | 0 | -860.7 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860.7 | Request 2021 Budget | 0 | 860.7 | -860.7 | 860.7 | -860.7 | 0 | 0 | 860.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 157805 | BL-A | BL-A 35227168_CWSP - Middletown 1103 - LR 830 PH3.4_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-29 | Not Started | 2021-11-26 | 2021-12-02 | Not Started | 2021-11-25 | Not Started | 2021-12-23 | Not Started | 2021-07-30 | 2021-07-30 | Not Started | 2021-08-02 | 2021-08-20 | Not Started | 2021-11-26 | 2021-12-09 | Not Started | 2022-01-17 | Not Started | 2022-01-17 | Not Started | 2022-01-28 | Not Started | 2022-01-17 | Not Started | 2022-04-29 | Not Started | 2022-05-30 | Not Started | 2022-07-29 | 2022-07-29 | 0 | On/ Ahead Schedule | Not Started | 2022-08-01 | 2022-08-12 | Not Started | 2022-09-27 | Not Started
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | E.5034825.01.18 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 6600 | 0 | 6600 | 1.25 | 0 | 1.25 |  |  |  |  | GC | 118750 | 0 | 118750 | 684.6 | 0 | 118065.4 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 684.6 | Budget Allocated | 4375000 | 4375684.6 | -684.6 | 684.6 | 4374315.4 | 0 | 0 | 684.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-20 | Not Started | 2021-06-04 | 2021-06-10 | Not Started | 2021-06-03 | Not Started | 2021-07-15 | Not Started | [6 empty] | 2021-05-14 | 2021-05-20 | Not Started | 2021-07-19 | Not Started | 2021-07-19 | Not Started | 2021-10-04 | Not Started | 2021-07-19 | Not Started | 2021-10-18 | Not Started | 2021-10-18 | Not Started | 2021-11-17 | 2021-11-17 | 0 | On/ Ahead Schedule | Not Started | 2021-11-17 | 2021-12-01 | Not Started | 2022-01-14 | Not Started
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | E.5034825.01.19 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 5808 | 0 | 5808 | 1.1 | 0 | 1.1 |  |  |  |  | GC | 118750 | 0 | 118750 | 229.1 | 0 | 118520.9 | On/Under Budget | 0 | 0 | 615.6 | -615.6 | 0 | 0 | 0 | 844.7 | Budget Allocated | 3850000 | 3850229.1 | -229.1 | 229.1 | 3849770.9 | 0 | 0 | 229.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-20 | Not Started | 2021-06-04 | 2021-06-10 | Not Started | 2021-06-03 | Not Started | 2021-07-15 | Not Started | [6 empty] | 2021-05-14 | 2021-05-20 | Not Started | 2021-07-19 | Not Started | 2021-07-19 | Not Started | 2021-10-04 | Not Started | 2021-07-19 | Not Started | 2021-10-18 | Not Started | 2021-10-18 | Not Started | 2021-11-17 | 2021-11-17 | 0 | On/ Ahead Schedule | Not Started | 2021-11-17 | 2021-12-01 | Not Started | 2022-01-14 | Not Started
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | E.5034825.01.20 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 8448 | 0 | 8448 | 1.6 | 0 | 1.6 |  |  |  |  | GC | 118750 | 0 | 118750 | 3880.8 | 0 | 114869.2 | On/Under Budget | 0 | 0 | 304.9 | -304.9 | 0 | 0 | 0 | 4185.6 | Budget Allocated | 5600000 | 5603880.7 | -3880.7 | 3880.7 | 5596119.3 | 0 | 0 | 3880.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-20 | Not Started | 2021-06-04 | 2021-06-10 | Not Started | 2021-06-03 | Not Started | 2021-07-15 | Not Started | [6 empty] | 2021-05-14 | 2021-05-20 | Not Started | 2021-07-19 | Not Started | 2021-07-19 | Not Started | 2021-10-04 | Not Started | 2021-07-19 | Not Started | 2021-10-18 | Not Started | 2021-10-18 | Not Started | 2021-11-17 | 2021-11-17 | 0 | On/ Ahead Schedule | Not Started | 2021-11-17 | 2021-12-01 | Not Started | 2022-01-14 | Not Started
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | E.5034825.01.21 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 5068 | 0 | 5068 | 0.95985 | 0 | 0.95985 |  |  |  |  | GC | 118750 | 0 | 118750 | 573.3 | 0 | 118176.7 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573.3 | Budget Allocated | 3360000 | 3360573.3 | -573.3 | 573.3 | 3359426.7 | 0 | 0 | 573.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-20 | Not Started | 2021-06-04 | 2021-06-10 | Not Started | 2021-06-03 | Not Started | 2021-07-15 | Not Started | [6 empty] | 2021-05-14 | 2021-05-20 | Not Started | 2021-07-19 | Not Started | 2021-07-19 | Not Started | 2021-10-04 | Not Started | 2021-07-19 | Not Started | 2021-10-18 | Not Started | 2021-10-18 | Not Started | 2021-11-17 | 2021-11-17 | 0 | On/ Ahead Schedule | Not Started | 2021-11-17 | 2021-12-01 | Not Started | 2022-01-14 | Not Started
35233947 | CWSP - OREGON TRAIL 110335002 PH1.2 |  | 5794555 | UNSE | 08W | A3CG | Adoni Andreas Christie |  |  |  |  | Not in the WP |  | SH | REDDING |  | 0 | 9734 | 9734 | 1.8436 | 0 | 1.8436 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35233948 | CWSP - OREGON TRAIL 110335002 PH1.3 |  | 5794555 | UNSE | 08W | A3CG | Adoni Andreas Christie |  |  |  |  | Not in the WP |  | SH | REDDING |  | 13660 | 0 | 13660 | 2.5871 | 0 | 2.5871 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35233949 | CWSP - OREGON TRAIL 110335002 PH1.4 |  | 5794555 | UNSE | 08W | A3CG | Adoni Andreas Christie |  |  |  |  | Not in the WP |  | SH | REDDING |  | 0 | 10438 | 10438 | 1.9769 | 0 | 1.9769 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35233950 | CWSP - OREGON TRAIL 110335002 PH1.5 |  | 5794555 | UNSE | 08W | A3CG | Adoni Andreas Christie |  |  |  |  | Not in the WP |  | SH | REDDING |  | 14542 | 0 | 14542 | 2.7542 | 0 | 2.7542 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35233951 | CWSP - OREGON TRAIL 110335002 PH1.6 |  | 5794555 | UNSE | 08W | A3CG | Adoni Andreas Christie |  |  |  |  | Not in the WP |  | SH | REDDING |  | 0 | 8262 | 8262 | 1.5648 | 0 | 1.5648 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | E.5034714.01.08 | 5794555 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 |  | SH | REDDING | North Valley Assets | 0 | 11413 | 11413 | 2.1616 | 0 | 2.1616 | [5 empty] | 100000 | 0 | 100000 | 0 | 0 | 100000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Budget Allocated | 4104000 | 4104000 | 0 | 0 | 4104000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-06-22 | Not Started | 2021-07-14 | 2021-07-20 | Not Started | 2021-07-13 | Not Started | 2021-08-17 | Not Started | 2021-06-23 | 2021-06-23 | Not Started | 2021-06-24 | 2021-07-14 | Not Started | 2021-06-30 | 2021-07-13 | Not Started | 2021-09-09 | Not Started | 2021-09-09 | Not Started | 2021-09-22 | Not Started | 2021-09-09 | Not Started | 2021-11-03 | Not Started | 2021-12-02 | Not Started | 2022-01-13 | 2022-01-13 | 0 | On/ Ahead Schedule | Not Started | 2022-01-14 | 2022-01-27 | Not Started | 2022-03-14 | Not Started
35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | E.5034714.01.09 | 5794555 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2022 |  | SH | REDDING | North Valley Assets | 4437 | 0 | 4437 | 0.84034 | 0 | 0.84034 | [5 empty] | 150000 | 0 | 150000 | 0 | 0 | 150000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Request 2021 Budget | 0 | 500000 | -500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-06-28 | Not Started | 2021-07-20 | 2021-07-26 | Not Started | 2021-07-19 | Not Started | 2021-08-16 | Not Started | 2021-06-29 | 2021-06-29 | Not Started | 2021-06-30 | 2021-07-20 | Not Started | 2021-07-20 | 2021-08-02 | Not Started | 2021-09-08 | Not Started | 2021-09-08 | Not Started | 2021-09-21 | Not Started | 2021-09-08 | Not Started | 2021-11-02 | Not Started | 2021-12-01 | Not Started | 2022-01-13 | 2022-01-13 | 0 | On/ Ahead Schedule | Not Started | 2022-01-14 | 2022-01-27 | Not Started | 2022-03-14 | Not Started
35233954 | CWSP - OREGON TRAIL 110335002 PH3.2 |  | 5794555 | UNSE | 08W | A3CG | Adoni Andreas Christie |  |  |  |  | 2021 |  | SH | REDDING |  | 0 | 1120 | 1120 | 0.21212 | 0 | 0.21212 | [20 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | E.5034714.01.10 | 5794555 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2022 |  | SH | REDDING | North Valley Assets | 2900 | 0 | 2900 | 0.54924 | 0 | 0.54924 | [5 empty] | 150000 | 0 | 150000 | 0 | 0 | 150000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Request 2021 Budget | 0 | 500000 | -500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-17 | Not Started | 2021-06-15 | 2021-06-21 | Not Started | 2021-06-14 | Not Started | 2021-06-28 | Not Started | 2021-05-18 | 2021-05-18 | Not Started | 2021-05-19 | 2021-06-08 | Not Started | 2021-06-15 | 2021-06-28 | Not Started | 2021-08-03 | Not Started | 2021-08-03 | Not Started | 2021-08-16 | Not Started | 2021-08-03 | Not Started | 2021-10-18 | Not Started | 2021-11-16 | Not Started | 2022-01-13 | 2022-01-13 | 0 | On/ Ahead Schedule | Not Started | 2022-01-14 | 2022-01-27 | Not Started | 2022-03-14 | Not Started
35233956 | CWSP - OREGON TRAIL 110335002 PH3.3 |  | 5794555 | UNSE | 08W | A3CG | Adoni Andreas Christie |  |  |  |  | 2021 |  | SH | REDDING |  | 0 | 1344 | 1344 | 0.25455 | 0 | 0.25455 | [20 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | E.5034714.01.11 | 5794555 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2022 |  | SH | REDDING | North Valley Assets | 539 | 0 | 539 | 0.10208 | 0 | 0.10208 | [5 empty] | 125000 | 0 | 125000 | 0 | 0 | 125000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Request 2021 Budget | 0 | 125000 | -125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-06-16 | Not Started | 2021-06-24 | 2021-06-30 | Not Started | 2021-06-23 | Not Started | 2021-07-28 | Not Started | 2021-06-17 | 2021-06-17 | Not Started | 2021-06-18 | 2021-07-08 | Not Started | 2021-06-24 | 2021-07-07 | Not Started | 2021-08-06 | Not Started | 2021-08-06 | Not Started | 2021-08-19 | Not Started | 2021-08-06 | Not Started | 2021-10-07 | Not Started | 2021-11-05 | Not Started | 2022-01-13 | 2022-01-13 | 0 | On/ Ahead Schedule | Not Started | 2022-01-14 | 2022-01-27 | Not Started | 2022-03-14 | Not Started
35233958 | CWSP - OREGON TRAIL 110335002 PH3.4 |  | 5794555 | UNSE | 08W | A3CG | Adoni Andreas Christie |  |  |  |  | 2021 |  | SH | REDDING |  | 0 | 1099 | 1099 | 0.20814 | 0 | 0.20814 | [20 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | E.5034714.01.12 | 5794555 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 |  | SH | REDDING | North Valley Assets | 0 | 1827 | 1827 | 0.34602 | 0 | 0.34602 | [5 empty] | 75000 | 0 | 75000 | 0 | 0 | 75000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Budget Allocated | 665000 | 665000 | 0 | 0 | 665000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-06-09 | Not Started | 2021-07-08 | 2021-07-14 | Not Started | 2021-07-07 | Not Started | 2021-08-04 | Not Started | 2021-06-10 | 2021-06-10 | Not Started | 2021-06-11 | 2021-07-01 | Not Started | 2021-07-08 | 2021-07-21 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-09-09 | Not Started | 2021-08-27 | Not Started | 2021-10-25 | Not Started | 2021-11-23 | Not Started | 2022-01-13 | 2022-01-13 | 0 | On/ Ahead Schedule | Not Started | 2022-01-14 | 2022-01-27 | Not Started | 2022-03-14 | Not Started
35233995 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.2 |  | 5795018 | UNSE | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  | SH | PLCRVLLE |  | 2640 | 0 | 2640 | 0.5 | 0 | 0.5 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35233996 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.3 |  | 5795018 | UNSE | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | Not in the WP |  | SH | PLCRVLLE |  | 3748.8 | 0 | 3748.8 | 0.71 | 0 | 0.71 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234284 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.2 |  | 5794988 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | JACKSON |  | 2376 | 0 | 2376 | 0.45 | 0 | 0.45 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234380 | CWSP - OREGON TRAIL 110335002 PH3.5 |  | 5794555 | UNSE | 08W | A3CG | Adoni Andreas Christie |  |  |  |  | 2021 |  | SH | REDDING |  | 0 | 11837 | 11837 | 2.2419 | 0 | 2.2419 | [20 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | E.5034714.01.13 | 5794555 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 |  | SH | REDDING | North Valley Assets | 0 | 8167 | 8167 | 1.5468 | 0 | 1.5468 | [5 empty] | 100000 | 0 | 100000 | 0 | 0 | 100000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Budget Allocated | 2945000 | 2945000 | 0 | 0 | 2945000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-06-03 | Not Started | 2021-07-09 | 2021-07-15 | Not Started | 2021-07-08 | Not Started | 2021-08-05 | Not Started | 2021-06-04 | 2021-06-04 | Not Started | 2021-06-07 | 2021-06-25 | Not Started | 2021-07-09 | 2021-07-22 | Not Started | 2021-08-16 | Not Started | 2021-08-16 | Not Started | 2021-08-27 | Not Started | 2021-08-16 | Not Started | 2021-10-15 | Not Started | 2021-11-15 | Not Started | 2022-01-13 | 2022-01-13 | 0 | On/ Ahead Schedule | Not Started | 2022-01-14 | 2022-01-27 | Not Started | 2022-03-14 | Not Started
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | E.5034714.01.14 | 5794555 | UNSE | 08W | T3SQ | Travis Damian Skarda | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 |  | SH | REDDING | North Valley Assets | 0 | 8382 | 8382 | 1.5875 | 0 | 1.5875 | [5 empty] | 100000 | 0 | 100000 | 0 | 0 | 100000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Budget Allocated | 3021000 | 3021000 | 0 | 0 | 3021000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-06-09 | Not Started | 2021-07-08 | 2021-07-14 | Not Started | 2021-07-07 | Not Started | 2021-08-04 | Not Started | 2021-06-10 | 2021-06-10 | Not Started | 2021-06-11 | 2021-07-01 | Not Started | 2021-07-08 | 2021-07-21 | Not Started | 2021-08-13 | Not Started | 2021-08-13 | Not Started | 2021-08-26 | Not Started | 2021-08-13 | Not Started | 2021-10-14 | Not Started | 2021-11-12 | Not Started | 2022-01-13 | 2022-01-13 | 0 | On/ Ahead Schedule | Not Started | 2022-01-14 | 2022-01-27 | Not Started | 2022-03-14 | Not Started
35234383 | CWSP - OREGON TRAIL 110335002 PH3.6 |  | 5794555 | UNSE | 08W | A3CG | Adoni Andreas Christie |  |  |  |  | 2021 |  | SH | REDDING |  | 6328 | 0 | 6328 | 1.1985 | 0 | 1.1985 | [20 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35234384 | CWSP - OREGON TRAIL 110335002 PH3.7 |  | 5794555 | UNSE | 08W | A3CG | Adoni Andreas Christie |  |  |  |  | 2021 |  | SH | REDDING |  | 0 | 307 | 307 | 0.058144 | 0 | 0.058144 | [20 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35234385 | CWSP - OREGON TRAIL 110335002 PH3.8 |  | 5794555 | UNSE | 08W | A3CG | Adoni Andreas Christie |  |  |  |  | 2021 |  | SH | REDDING |  | 0 | 3561 | 3561 | 0.67443 | 0 | 0.67443 | [20 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35234386 | CWSP - OREGON TRAIL 110335002 PH3.9 |  | 5794555 | UNSE | 08W | A3CG | Adoni Andreas Christie |  |  |  |  | 2021 |  | SH | REDDING |  | 0 | 4529 | 4529 | 0.85777 | 0 | 0.85777 | [20 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35234387 | CWSP - OREGON TRAIL 110335002 PH4.2 |  | 5794555 | UNSE | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP |  | SH | REDDING |  | 0 | 4963 | 4963 | 0.93996 | 0 | 0.93996 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234388 | CWSP - OREGON TRAIL 110335002 PH4.3 |  | 5794555 | UNSE | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP |  | SH | REDDING |  | 0 | 10772 | 10772 | 2.0402 | 0 | 2.0402 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234389 | CWSP - OREGON TRAIL 110335002 PH4.4 |  | 5794555 | UNSE | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP |  | SH | REDDING |  | 0 | 4752 | 4752 | 0.9 | 0 | 0.9 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234390 | CWSP - OREGON TRAIL 110335002 PH4.5 |  | 5794555 | UNSE | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP |  | SH | REDDING |  | 0 | 2746 | 2746 | 0.52008 | 0 | 0.52008 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234391 | CWSP - OREGON TRAIL 110335002 PH4.6 |  | 5794555 | UNSE | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP |  | SH | REDDING |  | 0 | 6653 | 6653 | 1.26 | 0 | 1.26 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234392 | CWSP - OREGON TRAIL 110335002 PH4.7 |  | 5794555 | UNSE | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP |  | SH | REDDING |  | 0 | 8765 | 8765 | 1.66 | 0 | 1.66 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234393 | CWSP - OREGON TRAIL 110335002 PH5.2 |  | 5794555 | UNSE | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP |  | SH | REDDING |  | 0 | 12778 | 12778 | 2.4201 | 0 | 2.4201 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234394 | CWSP - OREGON TRAIL 110335002 PH5.3 |  | 5794555 | UNSE | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP |  | SH | REDDING |  | 0 | 9451 | 9451 | 1.79 | 0 | 1.79 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234395 | CWSP - OREGON TRAIL 110335002 PH5.4 |  | 5794555 | UNSE | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP |  | SH | REDDING |  | 0 | 14309 | 14309 | 2.71 | 0 | 2.71 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234396 | CWSP - OREGON TRAIL 110335002 PH5.5 |  | 5794555 | UNSE | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP |  | SH | REDDING |  | 0 | 8923 | 8923 | 1.69 | 0 | 1.69 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234397 | CWSP - OREGON TRAIL 110335002 PH5.6 |  | 5794555 | UNSE | 08W | M5HF | Michael Donald James Hernandez | RTSL | Ryan Shankel | T8B5 | Tyler Babin | Not in the WP |  | SH | REDDING |  | 0 | 3802 | 3802 | 0.72008 | 0 | 0.72008 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234398 | CWSP - OREGON TRAIL 110335002 PHASE 6.2 |  | 5794555 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  | SH | REDDING |  | 0 | 15061 | 15061 | 2.8525 | 0 | 2.8525 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234399 | CWSP - OREGON TRAIL 110335002 PHASE 6.3 |  | 5794555 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  | SH | REDDING |  | 2535 | 0 | 2535 | 0.48011 | 0 | 0.48011 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234400 | CWSP - OREGON TRAIL 110335002 PHASE 6.4 |  | 5794555 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  | SH | REDDING |  | 0 | 7339 | 7339 | 1.39 | 0 | 1.39 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234401 | CWSP - OREGON TRAIL 110335002 PHASE 6.5 |  | 5794555 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  | SH | REDDING |  | 0 | 9768 | 9768 | 1.85 | 0 | 1.85 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234526 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.3 |  | 5794988 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | JACKSON |  | 0 | 2112 | 2112 | 0.4 | 0 | 0.4 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234527 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.2 |  | 5794984 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  | SH | GRSSVLLY |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234528 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.3 |  | 0000000 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  | SH | GRSSVLLY |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234529 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.4 |  | 5794984 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  | SH | GRSSVLLY |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234756 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 |  | 5795300 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | 2022 |  | SH | LAKEPORT |  | 14689 | 0 | 14689 | 2.782 | 0 | 2.782 | [20 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35234758 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 |  | 5795300 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | 2022 |  | SH | LAKEPORT |  | 3073 | 0 | 3073 | 0.58201 | 0 | 0.58201 | [20 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35234862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 |  | 5795300 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | 2022 |  | SH | LAKEPORT |  | 422 | 0 | 422 | 0.079924 | 0 | 0.079924 | [20 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35234865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 |  | 5795300 | UNSE | 08W | SFMT | Steven Moraga |  |  |  |  | 2022 |  | SH | LAKEPORT |  | 3419 | 0 | 3419 | 0.64754 | 0 | 0.64754 | [20 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | E.5034825.01.22 | 5795419 | UNSE | 08W | JTHL | Joseph T Hembree | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2021 | FRRB | OROVILLE | North Valley Assets | 604 | 0 | 604 | 0.11439 | 0 | 0.11439 | [5 empty] | 950000 | 0 | 950000 | 893.1 | 0 | 949106.9 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 893.1 | Request 2021 Budget | 0 | 4620893.1 | -4620893.1 | 893.1 | -893.1 | 0 | 0 | 893.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-07-05 | Not Started | 2021-08-10 | 2021-08-16 | Not Started | 2021-08-09 | Not Started | 2021-09-06 | Not Started | 2021-07-06 | 2021-07-06 | Not Started | 2021-07-07 | 2021-07-27 | Not Started | 2021-08-10 | 2021-08-23 | Not Started | 2021-09-29 | Not Started | 2021-09-29 | Not Started | 2021-10-12 | Not Started | 2021-10-13 | Not Started | 2021-11-16 | Not Started | 2021-12-08 | Not Started | 2022-02-08 | 2022-02-08 | 0 | On/ Ahead Schedule | Not Started | 2022-02-09 | 2022-02-22 | Not Started | 2022-04-07 | Not Started
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | E.5034825.01.23 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 5280 | 0 | 5280 | 1 | 0 | 1 | [5 empty] | 105560 | 0 | 105560 | 3270.6 | 0 | 102289.4 | On/Under Budget | 0 | 0 | 199.2 | -199.2 | 0 | 0 | 0 | 3469.7 | Request 2021 Budget | 0 | 3503270.5 | -3503270.5 | 3270.5 | -3270.5 | 0 | 0 | 3270.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-12 | Not Started | 2021-05-27 | 2021-06-02 | Not Started | 2021-05-26 | Not Started | 2021-07-07 | Not Started | [6 empty] | 2021-05-14 | 2021-05-20 | Not Started | 2021-07-09 | Not Started | 2021-07-09 | Not Started | 2021-09-24 | Not Started | 2021-07-09 | Not Started | 2021-10-08 | Not Started | 2021-10-08 | Not Started | 2021-11-09 | 2021-11-09 | 0 | On/ Ahead Schedule | Not Started | 2021-11-09 | 2021-11-23 | Not Started | 2022-01-06 | Not Started
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 | E.5034825.01.24 | 5795419 | UNSE | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  | FRRB | OROVILLE | North Valley Assets | 0 | 2730 | 2730 | 0.51705 | 0 | 0.51705 | [5 empty] | 95000 | 0 | 95000 | 2295.5 | 0 | 92704.5 | On/Under Budget | 0 | 0 | 69.6 | -69.6 | 0 | 0 | 0 | 2365.1 | Project is not in the WP or in 2020 WP | 0 | 2295.5 | -2295.5 | 2295.5 | -2295.5 | 0 | 0 | 2295.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-21 | Not Started | 2021-06-07 | 2021-06-11 | Not Started | 2021-06-04 | Not Started | 2021-07-16 | Not Started | [6 empty] | 2021-05-20 | 2021-05-26 | Not Started | 2021-07-20 | Not Started | 2021-07-20 | Not Started | 2021-10-05 | Not Started | 2021-07-20 | Not Started | 2021-10-19 | Not Started | 2021-10-19 | Not Started | 2021-11-18 | 2021-11-18 | 0 | On/ Ahead Schedule | Not Started | 2021-11-18 | 2021-12-02 | Not Started | 2022-01-17 | Not Started
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 3555 | 3555 | 0.6733 | 0 | 0.6733 | [19 empty] | 235.6 | Project is not in the WP or in 2020 WP | 0 | 235.6 | -235.6 | 0 | 0
35235671 | FRRB - WYANDOTTE 1103 - W4 PH4.2 | E.5034825.01.26 | 5795419 | UNSE | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  | FRRB | OROVILLE | North Valley Assets | 0 | 4445 | 4445 | 0.84186 | 0 | 0.84186 | [5 empty] | 95000 | 0 | 95000 | 0 | 0 | 95000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-21 | Not Started | 2021-06-07 | 2021-06-11 | Not Started | 2021-06-04 | Not Started | 2021-07-16 | Not Started | [6 empty] | 2021-05-20 | 2021-05-26 | Not Started | 2021-07-20 | Not Started | 2021-07-20 | Not Started | 2021-10-05 | Not Started | 2021-07-20 | Not Started | 2021-10-19 | Not Started | 2021-10-19 | Not Started | 2021-11-18 | 2021-11-18 | 0 | On/ Ahead Schedule | Not Started | 2021-11-18 | 2021-12-02 | Not Started | 2022-01-17 | Not Started
35235672 | FRRB - WYANDOTTE 1103 - W7 PH7 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 2353 | 2353 | 0.44564 | 0 | 0.44564 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35235673 | FRRB - WYANDOTTE 1103 - W8 PH8 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 1445 | 1445 | 0.27367 | 0 | 0.27367 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35235674 | FRRB - BIG BEND 1102 - B1 PH1 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 1246 | 1246 | 0.23598 | 0 | 0.23598 | [19 empty] | 235.6 | Project is not in the WP or in 2020 WP | 0 | 235.6 | -235.6 | 0 | 0
35235675 | FRRB - BIG BEND 1102 - B2 PH2 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 988 | 988 | 0.18712 | 0 | 0.18712 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | E.5034825.01.31 | 5795419 | UNSE | 08W | JTHL | Joseph T Hembree | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | 2021 | 2021 | FRRB | OROVILLE | North Valley Assets | 3089 | 0 | 3089 | 0.58504 | 0 | 0.58504 | [5 empty] | 950000 | 0 | 950000 | 235.6 | 0 | 949764.4 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235.6 | Request 2021 Budget | 0 | 8400235.6 | -8400235.6 | 235.6 | -235.6 | 0 | 0 | 235.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-07-05 | Not Started | 2021-08-10 | 2021-08-16 | Not Started | 2021-08-09 | Not Started | 2021-09-06 | Not Started | 2021-07-06 | 2021-07-06 | Not Started | 2021-07-07 | 2021-07-27 | Not Started | 2021-08-10 | 2021-08-23 | Not Started | 2021-09-29 | Not Started | 2021-09-29 | Not Started | 2021-10-12 | Not Started | 2021-10-13 | Not Started | 2021-11-16 | Not Started | 2021-12-08 | Not Started | 2022-02-08 | 2022-02-08 | 0 | On/ Ahead Schedule | Not Started | 2022-02-09 | 2022-02-22 | Not Started | 2022-04-07 | Not Started
35235677 | FRRB - BIG BEND 1102 - B4 PH4 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 101 | 0 | 101 | 0.019129 | 0 | 0.019129 | [19 empty] | 235.6 | Project is not in the WP or in 2020 WP | 0 | 235.6 | -235.6 | 0 | 0
35235678 | FRRB - BIG BEND 1102 - B5 PH5 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 18651 | 0 | 18651 | 3.5324 | 0 | 3.5324 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35235679 | FRRB - BIG BEND 1102 - B6 PH6 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 3557 | 0 | 3557 | 0.67367 | 0 | 0.67367 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35235700 | FRRB - KANAKA 1101 - K1 PH1 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 2317 | 2317 | 0.43883 | 0 | 0.43883 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35235701 | FRRB - KANAKA 1101 - K2 PH2 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 1137 | 1137 | 0.21534 | 0 | 0.21534 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35235702 | FRRB - KANAKA 1101 - K3 PH3 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 3537 | 3537 | 0.66989 | 0 | 0.66989 | [19 empty] | 235.6 | Project is not in the WP or in 2020 WP | 0 | 235.6 | -235.6 | 0 | 0
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 123 | 123 | 0.023295 | 0 | 0.023295 | [19 empty] | 235.6 | Project is not in the WP or in 2020 WP | 0 | 235.6 | -235.6 | 0 | 0
35235704 | FRRB - KANAKA 1101 - K5 PH5 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 1893 | 1893 | 0.35852 | 0 | 0.35852 | [19 empty] | 471.2 | Project is not in the WP or in 2020 WP | 0 | 471.2 | -471.2 | 0 | 0
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | E.5034825.01.40 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 6970 | 0 | 6970 | 1.3201 | 0 | 1.3201 |  |  |  |  | GC | 118750 | 0 | 118750 | 229 | 0 | 118521 | On/Under Budget | 0 | 0 | 889.2 | -889.2 | 0 | 0 | 0 | 1118.3 | Budget Allocated | 4620000 | 4620229.1 | -229.1 | 229.1 | 4619770.9 | 0 | 0 | 229.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-20 | Not Started | 2021-06-04 | 2021-06-10 | Not Started | 2021-06-03 | Not Started | 2021-07-15 | Not Started | [6 empty] | 2021-05-14 | 2021-05-20 | Not Started | 2021-07-19 | Not Started | 2021-07-19 | Not Started | 2021-10-04 | Not Started | 2021-07-19 | Not Started | 2021-10-18 | Not Started | 2021-10-18 | Not Started | 2021-11-17 | 2021-11-17 | 0 | On/ Ahead Schedule | Not Started | 2021-11-17 | 2021-12-01 | Not Started | 2022-01-14 | Not Started
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | E.5034825.01.41 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 6125 | 0 | 6125 | 1.16 | 0 | 1.16 |  |  |  |  | GC | 118750 | 0 | 118750 | 229.1 | 0 | 118520.9 | On/Under Budget | 0 | 0 | 273.6 | -273.6 | 0 | 0 | 0 | 502.7 | Budget Allocated | 4060000 | 4060229.1 | -229.1 | 229.1 | 4059770.9 | 0 | 0 | 229.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-20 | Not Started | 2021-06-04 | 2021-06-10 | Not Started | 2021-06-03 | Not Started | 2021-07-15 | Not Started | [6 empty] | 2021-05-14 | 2021-05-20 | Not Started | 2021-07-19 | Not Started | 2021-07-19 | Not Started | 2021-10-04 | Not Started | 2021-07-19 | Not Started | 2021-10-18 | Not Started | 2021-10-18 | Not Started | 2021-11-17 | 2021-11-17 | 0 | On/ Ahead Schedule | Not Started | 2021-11-17 | 2021-12-01 | Not Started | 2022-01-14 | Not Started
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | E.5034825.01.42 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 5016 | 0 | 5016 | 0.95 | 0 | 0.95 |  |  |  |  | GC | 118750 | 0 | 118750 | 827.9 | 0 | 117922.1 | On/Under Budget | 0 | 0 | 61 | -61 | 0 | 0 | 0 | 888.9 | Budget Allocated | 3325000 | 3325827.9 | -827.9 | 827.9 | 3324172.1 | 0 | 0 | 827.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-20 | Not Started | 2021-06-04 | 2021-06-10 | Not Started | 2021-06-03 | Not Started | 2021-07-15 | Not Started | [6 empty] | 2021-05-14 | 2021-05-20 | Not Started | 2021-07-19 | Not Started | 2021-07-19 | Not Started | 2021-10-04 | Not Started | 2021-07-19 | Not Started | 2021-10-18 | Not Started | 2021-10-18 | Not Started | 2021-11-17 | 2021-11-17 | 0 | On/ Ahead Schedule | Not Started | 2021-11-17 | 2021-12-01 | Not Started | 2022-01-14 | Not Started
35236437 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.7 |  | 5795300 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT |  | 0 | 1796 | 1796 | 0.34015 | 0 | 0.34015 | [20 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35236438 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.8 |  | 5795300 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT |  | 0 | 2534 | 2534 | 0.47992 | 0 | 0.47992 | [20 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | E.5034805.01.37 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 5914 | 0 | 5914 | 1.1201 | 0 | 1.1201 | [5 empty] | 67857 | 67857 | 0 | 229.1 | 0 | -229.1 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229.1 | Request 2021 Budget | 0 | 229.1 | -229.1 | 229.1 | -229.1 | 0 | 0 | 229.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | E.5034805.01.38 | 5795300 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 2534 | 0 | 2534 | 0.47992 | 0 | 0.47992 | [5 empty] | 67857 | 67857 | 0 | 229.1 | 0 | -229.1 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229.1 | Request 2021 Budget | 0 | 229.1 | -229.1 | 229.1 | -229.1 | 0 | 0 | 229.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | E.5034610.01.18 | 5794205 | UNSE | 08W | P3D5 | Patrick Donovan | A9R3 | Aamani Ravikanti | J7TY | Jace Thorsen | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 1162 | 1162 | 0.22008 | 0 | 0.22008 | [5 empty] | 1 | 1 | 0 | 37.3 | 0 | -37.3 | OverRun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.3 | Request 2021 Budget | 0 | 37.3 | -37.3 | 37.3 | -37.3 | 0 | 0 | 37.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | E.5034825.01.08 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 1920 | 0 | 1920 | 0.36364 | 0 | 0.36364 |  |  |  |  | GC | 3715565 | 1674548 | 2041017 | 229.1 | 0 | 2040787.9 | On/Under Budget | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 229.1 | Budget Allocated | 1272727.27 | 1272956.1 | -228.83 | 500229.1 | 772498.17 | 0 | 0 | 229.1 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158207 | BL-A | BL-A 35233301_FRRB - WYANDOTTE 1103 - W1 PH 1.5 - Mar. 2021 | 2021-03-31 | 2021-04-23 | Not Started | 2021-03-18 | 2021-03-22 | Completed | 2021-04-26 | Not Started | 2021-04-26 | Not Started | [6 empty] | 2021-04-13 | 2021-04-19 | Not Started | 2021-04-28 | Not Started | 2021-04-28 | Not Started | 2021-07-14 | Not Started | 2021-05-12 | Not Started | 2021-07-28 | Not Started | 2021-07-28 | Not Started | 2021-08-27 | 2021-08-27 | 0 | On/ Ahead Schedule | Not Started | 2021-08-27 | 2021-09-10 | Not Started | 2021-10-26 | Not Started
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | E.5034825.01.12 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 1529 | 0 | 1529 | 0.28958 | 0 | 0.28958 |  |  |  |  | GC | 3378623 | 1596792 | 1781831 | 573.3 | 0 | 1781257.7 | On/Under Budget | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 573.3 | Budget Allocated | 1013541.67 | 1014114.3 | -572.63 | 500573.3 | 512968.37 | 0 | 0 | 573.3 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158204 | BL-A | BL-A 35233305_FRRB - WYANDOTTE 1103 - W1 PH 1.9 - Mar. 2021 | 2021-03-31 | 2021-04-23 | Not Started | 2021-03-18 | 2021-03-22 | Completed | 2021-04-26 | Not Started | 2021-04-26 | Not Started | [6 empty] | 2021-04-13 | 2021-04-19 | Not Started | 2021-04-28 | Not Started | 2021-04-28 | Not Started | 2021-07-14 | Not Started | 2021-05-12 | Not Started | 2021-07-28 | Not Started | 2021-07-28 | Not Started | 2021-08-27 | 2021-08-27 | 0 | On/ Ahead Schedule | Not Started | 2021-08-27 | 2021-09-10 | Not Started | 2021-10-26 | Not Started
35233309 | FRRB - WYANDOTTE 1103 - W1 PH1.13 | E.5034825.01.16 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 1935 | 0 | 1935 | 0.36648 | 0 | 0.36648 |  |  |  |  | GC | 3728491 | 1677531 | 2050960 | 0 | 0 | 2050960 | On/Under Budget | 500000 | 0 | 0 | 0 | 0 | 0 | 0 |  | Budget Allocated | 1282670.45 | 1282670 | 0.45 | 500000 | 782670.45 | 0 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 | 158200 | BL- A | BL- A 35233309_FRRB - WYANDOTTE 1103 - W1 PH 1.13 - Mar. 2021 | 2021-03-31 | 2021-04-23 | Not Started | 2021-03-18 | 2021-03-22 | Completed | 2021-04-26 | Not Started | 2021-04-26 | Not Started | [6 empty] | 2021-04-13 | 2021-04-19 | Not Started | 2021-04-28 | Not Started | 2021-04-28 | Not Started | 2021-07-14 | Not Started | 2021-05-12 | Not Started | 2021-07-28 | Not Started | 2021-07-28 | Not Started | 2021-08-27 | 2021-08-27 | 0 | On/ Ahead Schedule | Not Started | 2021-08-27 | 2021-09-10 | Not Started | 2021-10-26 | Not Started
35233166 | FRRB - BIG BEND 11021972 - B4 |  | 5795419 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | E.5034804.01.12 | 5795299 | UNSE | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2021 | 2021 | SH | PLCRVLLE | Sierra Assets | 1742.4 | 0 | 1742.4 | 0.33 | 0 | 0.33 |  |  |  |  | GC | 1 | 1 | 0 | 131.3 | 0 | -131.3 | OverRun | 0 | 0 | 65.5 | -65.5 | 0 | 0 | 0 | 196.7 | Request 2021 Budget | 0 | 131.2 | -131.2 | 131.2 | -131.2 | 0 | 1861.4 | -1730.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-04-30 | Not Started | 2021-06-18 | 2021-06-24 | Not Started | 2021-06-17 | Not Started | 2021-07-15 | Not Started | 2021-05-03 | 2021-05-03 | Not Started | 2021-05-04 | 2021-05-24 | Not Started | 2021-06-18 | 2021-07-01 | Not Started | 2021-08-09 | Not Started | 2021-08-09 | Not Started | 2021-08-20 | Not Started | 2021-08-09 | Not Started | 2021-11-19 | Not Started | 2021-12-20 | Not Started | 2022-01-31 | 2022-01-31 | 0 | On/ Ahead Schedule | Not Started | 2022-02-01 | 2022-02-14 | Not Started | 2022-03-30 | Not Started
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | E.5034692.01.02 | 5794540 | UNSE | 08W | M1NO | My-Linh Nguyen | DxS7 | Dorene Soe | MUHQ | Matt Haley | 2022 |  | SH | CONCORD | Diablo Assets | 6864 | 0 | 6864 | 1.3 | 0 | 1.3 | [5 empty] | 350000 | 0 | 350000 | 3497.8 | 0 | 346502.2 | On/Under Budget | 0 | 0 | 97.2 | -97.2 | 0 | 0 | 0 | 3595 | Request 2021 Budget | 0 | 3497.8 | -3497.8 | 3497.8 | -3497.8 | 0 | 462.9 | 3034.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-10-19 | Not Started | 2022-03-23 | 2022-03-29 | Not Started | 2022-03-22 | Not Started | 2022-04-19 | Not Started | 2021-10-20 | 2021-10-20 | Not Started | 2021-10-21 | 2021-11-10 | Not Started | 2022-03-23 | 2022-04-05 | Not Started | 2022-05-12 | Not Started | 2022-05-12 | Not Started | 2022-08-03 | Not Started | 2022-05-12 | Not Started | 2022-08-03 | Not Started | 2022-09-01 | Not Started | 2022-11-02 | 2022-11-02 | 0 | On/ Ahead Schedule | Not Started | 2022-11-03 | 2022-11-16 | Not Started | 2022-12-30 | Not Started
35232650 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | E.5034710.01.02 | 5794551 | UNSE | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2022 | 2021 | SH | AUBURN | Sierra Assets | 9028 | 0 | 9028 | 1.7098 | 0 | 1.7098 | [5 empty] | 316667 | 0 | 316667 | 0 | 0 | 316667 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Budget Allocated | 212265 | 167605 | 44660 | 0 | 212265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-07-05 | Not Started | 2021-08-10 | 2021-08-16 | Not Started | 2021-08-09 | Not Started | 2021-09-06 | Not Started | 2021-07-06 | 2021-07-06 | Not Started | 2021-07-07 | 2021-07-27 | Not Started | 2021-08-10 | 2021-08-23 | Not Started | 2021-09-29 | Not Started | 2021-09-29 | Not Started | 2021-10-12 | Not Started | 2021-09-29 | Not Started | 2022-01-11 | Not Started | 2022-02-09 | Not Started | 2022-04-12 | 2022-04-12 | 0 | On/ Ahead Schedule | Not Started | 2022-04-13 | 2022-04-26 | Not Started | 2022-06-09 | Not Started
35232651 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.3 | E.5034710.01.03 | 5794551 | UNSE | 08W | J6KF | Jeff L Kringler | M4JQ | Matt James | T8B5 | Tyler Babin | 2021 | 2021 | SH | AUBURN | Sierra Assets | 0 | 9187.2 | 9187.2 | 1.74 | 0 | 1.74 | [5 empty] | 316667 | 0 | 316667 | 0 | 0 | 316667 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Budget Allocated | 3458896 | 3464236.2 | -5340.2 | 0 | 3458896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-07-14 | Not Started | 2021-08-19 | 2021-08-25 | Not Started | 2021-08-18 | Not Started | 2021-09-15 | Not Started | 2021-07-15 | 2021-07-15 | Not Started | 2021-07-16 | 2021-08-05 | Not Started | 2021-08-19 | 2021-09-01 | Not Started | 2021-10-08 | Not Started | 2021-10-08 | Not Started | 2021-10-21 | Not Started | 2021-10-08 | Not Started | 2022-01-20 | Not Started | 2022-02-18 | Not Started | 2022-04-21 | 2022-04-21 | 0 | On/ Ahead Schedule | Not Started | 2022-04-22 | 2022-05-05 | Not Started | 2022-06-20 | Not Started
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | E.5034825.01.03 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 6336 | 0 | 6336 | 1.2 | 0 | 1.2 | [5 empty] | 118750 | 0 | 118750 | 10251.4 | 0 | 108498.6 | On/Under Budget | 0 | 0 | 1017.2 | -1017.2 | 0 | 0 | 0 | 11268.7 | Budget Allocated | 4200000 | 1757360.5 | 2442639.5 | 10251.5 | 4189748.5 | 0 | 2879.4 | 7372.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-10 | Not Started | 2021-05-11 | 2021-05-13 | Not Started | 2021-05-11 | Not Started | 2021-05-20 | Not Started | [6 empty] | 2021-04-20 | 2021-04-26 | Not Started | 2021-05-24 | Not Started | 2021-05-24 | Not Started | 2021-08-09 | Not Started | 2021-05-24 | Not Started | 2021-08-23 | Not Started | 2021-08-23 | Not Started | 2021-09-22 | 2021-09-22 | 0 | On/ Ahead Schedule | Not Started | 2021-09-22 | 2021-10-06 | Not Started | 2021-11-19 | Not Started
74024660 | 2019 CALISTOGA 1101 SUB ORDER |  | 5530168 | UNSE | 08W | S2WT | Steve Whitman |  |  |  |  | Not in the WP |  |  | NAPA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
74024661 | CWSP-BRUNSWICK 1105 LR32536 PH1 SUBORDER |  | 5530173 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
74022302 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH |  | 5786461 | UNSE | 08W | GSD5 | Gurshawn Singh Dhillon |  |  |  |  | Not in the WP |  |  | AUBURN | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
74022383 | CWSP-EL DORADO PH 2102 LR19542 PH 1.0 |  | 5782840 | UNSE | 08W | RYSJ | Ravneeta Singh |  |  |  |  | Not in the WP |  |  | AUBURN |  | 0 | 59136 | 59136 | 11.2 | 0 | 11.2 | [19 empty] | 594.1 | Project is not in the WP or in 2020 WP | 0 | 3646.6 | -3646.6 | 0 | 0
74022614 | CWSP - CAMP FIRE PADSE 1105 QUAIL RD |  | 5783285 | UNSE | 08W | JXF8 | Joseph Fong |  |  |  |  | Not in the WP |  |  | CHICO | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 |  | 5794541 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | MARIPOSA |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 1630.9 | Project is not in the WP or in 2020 WP | 0 | 1630.9 | -1630.9 | 0 | 0
35239094 | FRRB - DUNBAR 1101416 |  | 5545079 | UNSE | 08W | JDLM | Jesse Lorz |  |  |  |  | Not in the WP |  |  | STROSA | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35239095 | FRRB - WYANDOTTE 1103 - W4 PH 4.3 | E.5034825.01.66 | 5795419 | UNSE | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  |  | OROVILLE | North Valley Assets | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 95000 | 0 | 95000 | 0 | 0 | 95000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-21 | Not Started | 2021-06-07 | 2021-06-11 | Not Started | 2021-06-04 | Not Started | 2021-07-16 | Not Started | [6 empty] | 2021-05-20 | 2021-05-26 | Not Started | 2021-07-20 | Not Started | 2021-07-20 | Not Started | 2021-10-05 | Not Started | 2021-07-20 | Not Started | 2021-10-19 | Not Started | 2021-10-19 | Not Started | 2021-11-18 | 2021-11-18 | 0 | On/ Ahead Schedule | Not Started | 2021-11-18 | 2021-12-02 | Not Started | 2022-01-17 | Not Started
35239096 | FRRB - WYANDOTTE 1103 - W4 PH 4.4 | E.5034825.01.67 | 5795419 | UNSE | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  |  | OROVILLE | North Valley Assets | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 95000 | 0 | 95000 | 0 | 0 | 95000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-21 | Not Started | 2021-06-07 | 2021-06-11 | Not Started | 2021-06-04 | Not Started | 2021-07-16 | Not Started | [6 empty] | 2021-05-20 | 2021-05-26 | Not Started | 2021-07-20 | Not Started | 2021-07-20 | Not Started | 2021-10-05 | Not Started | 2021-07-20 | Not Started | 2021-10-19 | Not Started | 2021-10-19 | Not Started | 2021-11-18 | 2021-11-18 | 0 | On/ Ahead Schedule | Not Started | 2021-11-18 | 2021-12-02 | Not Started | 2022-01-17 | Not Started
35239097 | FRRB - WYANDOTTE 1103 - W4 PH 4.5 | E.5034825.01.68 | 5795419 | UNSE | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  |  | OROVILLE | North Valley Assets | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 95000 | 0 | 95000 | 0 | 0 | 95000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-21 | Not Started | 2021-06-07 | 2021-06-11 | Not Started | 2021-06-04 | Not Started | 2021-07-16 | Not Started | [6 empty] | 2021-05-20 | 2021-05-26 | Not Started | 2021-07-20 | Not Started | 2021-07-20 | Not Started | 2021-10-05 | Not Started | 2021-07-20 | Not Started | 2021-10-19 | Not Started | 2021-10-19 | Not Started | 2021-11-18 | 2021-11-18 | 0 | On/ Ahead Schedule | Not Started | 2021-11-18 | 2021-12-02 | Not Started | 2022-01-17 | Not Started
35239098 | FRRB - WYANDOTTE 1103 - W4 PH 4.6 | E.5034825.01.69 | 5795419 | UNSE | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  |  | OROVILLE | North Valley Assets | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 95000 | 0 | 95000 | 0 | 0 | 95000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-21 | Not Started | 2021-06-07 | 2021-06-11 | Not Started | 2021-06-04 | Not Started | 2021-07-16 | Not Started | [6 empty] | 2021-05-20 | 2021-05-26 | Not Started | 2021-07-20 | Not Started | 2021-07-20 | Not Started | 2021-10-05 | Not Started | 2021-07-20 | Not Started | 2021-10-19 | Not Started | 2021-10-19 | Not Started | 2021-11-18 | 2021-11-18 | 0 | On/ Ahead Schedule | Not Started | 2021-11-18 | 2021-12-02 | Not Started | 2022-01-17 | Not Started
35239099 | FRRB - WYANDOTTE 1103 - W4 PH 4.7 | E.5034825.01.70 | 5795419 | UNSE | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  |  | OROVILLE | North Valley Assets | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 95000 | 0 | 95000 | 0 | 0 | 95000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-21 | Not Started | 2021-06-07 | 2021-06-11 | Not Started | 2021-06-04 | Not Started | 2021-07-16 | Not Started | [6 empty] | 2021-05-20 | 2021-05-26 | Not Started | 2021-07-20 | Not Started | 2021-07-20 | Not Started | 2021-10-05 | Not Started | 2021-07-20 | Not Started | 2021-10-19 | Not Started | 2021-10-19 | Not Started | 2021-11-18 | 2021-11-18 | 0 | On/ Ahead Schedule | Not Started | 2021-11-18 | 2021-12-02 | Not Started | 2022-01-17 | Not Started
35239522 | FRRB - WYANDOTTE 1103 - W2 PH2.9 |  | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | FRRB | OROVILLE |  | 1320 | 0 | 1320 | 0.25 | 0 | 0.25 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 875000 | -875000 | 0 | 0 | [25 empty] | 2021-04-02 |  |  |  |  | 2021-05-06 | Not Started | 2021-05-07 | 2021-05-11 | Not Started | 2021-05-07 | Not Started | 2021-05-18 | Not Started | [6 empty] | 2021-04-16 | 2021-04-22 | Not Started | 2021-05-20 | Not Started | 2021-05-20 | Not Started | 2021-08-05 | Not Started | 2021-05-20 | Not Started | 2021-08-19 | Not Started | 2021-08-19 | Not Started | 2021-09-20 | 2021-09-20 | 0 | On/ Ahead Schedule | Not Started | 2021-09-20 | 2021-10-04 | Not Started | 2021-11-17 | Not Started
35239523 | FRRB - WYANDOTTE 1103 - W2 PH2.10 |  | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | Not in the WP |  | FRRB | OROVILLE |  | 1320 | 0 | 1320 | 0.25 | 0 | 0.25 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 875000 | -875000 | 0 | 0 | [25 empty] | 2021-04-02 |  |  |  |  | 2021-05-06 | Not Started | 2021-05-07 | 2021-05-11 | Not Started | 2021-05-07 | Not Started | 2021-05-18 | Not Started | [6 empty] | 2021-04-16 | 2021-04-22 | Not Started | 2021-05-20 | Not Started | 2021-05-20 | Not Started | 2021-08-05 | Not Started | 2021-05-20 | Not Started | 2021-08-19 | Not Started | 2021-08-19 | Not Started | 2021-09-20 | 2021-09-20 | 0 | On/ Ahead Schedule | Not Started | 2021-09-20 | 2021-10-04 | Not Started | 2021-11-17 | Not Started
35239937 | FRRB - WYANDOTTE 1103 - W2 PH2.11 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240160 | CWSP - COARSEGOLD 21045310 PH 1 |  | 5796380 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | OAKHURST |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240162 | CWSP - COARSEGOLD 21045310 PH 2 |  | 5796380 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | OAKHURST |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240163 | CWSP - COARSEGOLD 21045310 PH 3 |  | 5796380 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | OAKHURST |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240164 | CWSP - COARSEGOLD 2104570682 PH 1 |  | 5796380 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | OAKHURST |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240165 | CWSP - COARSEGOLD 21046210 PH 1 |  | 5796380 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | OAKHURST |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240166 | CWSP - VOLTA 1101CB PH 1 |  | 5796381 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240167 | CWSP - VOLTA 1101CB PH 2 |  | 5796382 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240168 | CWSP - VOLTA 110153118 PH 1 |  | 5796382 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240169 | CWSP - VOLTA 11011568 PH 1 |  | 5796381 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240170 | CWSP - VOLTA 11011568 PH 2 |  | 5796381 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240171 | CWSP - VOLTA 11011568 PH 3 |  | 5796382 | UNSE | 08W | MXUA | Mason Ung |  |  |  |  | Not in the WP |  |  | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240173 | CWSP - PUTAH CREEK 11028352 PH 1 |  | 5796383 | UNSE | 08W | KPH6 | Keith P Herrmann |  |  |  |  | Not in the WP |  |  | WOODLAND |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240174 | CWSP - PUTAH CREEK 11028352 PH 2 |  | 5796384 | UNSE | 08W | KPH6 | Keith P Herrmann |  |  |  |  | Not in the WP |  |  | WOODLAND |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240175 | CWSP - PUTAH CREEK 110267858 PH 1 |  | 5796384 | UNSE | 08W | KPH6 | Keith P Herrmann |  |  |  |  | Not in the WP |  |  | WOODLAND |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240176 | CWSP - PUTAH CREEK 110264044 PH 1 |  | 5796384 | UNSE | 08W | KPH6 | Keith P Herrmann |  |  |  |  | Not in the WP |  |  | WOODLAND |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240177 | CWSP - PUTAH CREEK 110264044 PH 2 |  | 5796383 | UNSE | 08W | KPH6 | Keith P Herrmann |  |  |  |  | Not in the WP |  |  | WOODLAND |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240178 | CWSP - PUTAH CREEK 1102710384 PH 1 |  | 5796383 | UNSE | 08W | KPH6 | Keith P Herrmann |  |  |  |  | Not in the WP |  |  | WOODLAND |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240179 | CWSP - SANTA YNEZ 1104CB |  | 5796385 | UNSE | 08W | JDLM | Jesse Lorz |  |  |  |  | Not in the WP |  |  | STMARIA |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240220 | CWSP - SANTA YNEZ 1104Y04 PH 1 |  | 5796385 | UNSE | 08W | JDLM | Jesse Lorz |  |  |  |  | Not in the WP |  |  | STMARIA |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240221 | CWSP - SANTA YNEZ 1104Y04 PH 2 |  | 5796385 | UNSE | 08W | JDLM | Jesse Lorz |  |  |  |  | Not in the WP |  |  | STMARIA |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240222 | CWSP - SANTA YNEZ 1104Y66 PH 1 |  | 5796385 | UNSE | 08W | JDLM | Jesse Lorz |  |  |  |  | Not in the WP |  |  | STMARIA |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240223 | CWSP - SANTA YNEZ 1104Y66 PH 2 |  | 5796385 | UNSE | 08W | JDLM | Jesse Lorz |  |  |  |  | Not in the WP |  |  | STMARIA |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240224 | CWSP - SANTA YNEZ 110477098 PH 1 |  | 5796385 | UNSE | 08W | JDLM | Jesse Lorz |  |  |  |  | Not in the WP |  |  | STMARIA |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240467 | FRRB - KANAKA 1101 - K4 PH4.2 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240468 | FRRB - KANAKA 1101 - K4 PH4.3 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240469 | FRRB - KANAKA 1101 - K4 PH4.4 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240470 | FRRB - KANAKA 1101 - K4 PH4.5 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240471 | FRRB - KANAKA 1101 - K4 PH4.6 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240472 | FRRB - KANAKA 1101 - K4 PH4.7 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240473 | FRRB - KANAKA 1101 - K4 PH4.8 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240474 | FRRB - KANAKA 1101 - K4 PH4.9 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240475 | FRRB - KANAKA 1101 - K4 PH4.10 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240476 | FRRB - KANAKA 1101 - K4 PH4.11 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240477 | FRRB - KANAKA 1101 - K4 PH4.12 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240478 | FRRB - KANAKA 1101 - K4 PH4.13 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240479 | FRRB - KANAKA 1101 - K4 PH4.14 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240540 | FRRB - KANAKA 1101 - K4 PH4.15 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240541 | FRRB - KANAKA 1101 - K4 PH4.16 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240542 | FRRB - KANAKA 1101 - K4 PH4.17 |  | 5793918 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240543 | FRRB - KANAKA 1101 - K4 PH4.18 |  | 5793918 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240545 | FRRB - WYANDOTTE 1103 - W2 PH2.12 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35240546 | FRRB - WYANDOTTE 1103 - W2 PH2.13 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  |  | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
74011865 | PH.3 - RECON. ECHO SUMMIT 1101 11,600' | E.0000088.01 | 5775246 | UNSE | 08W | BER5 | Brian Ritchie | JIDM | Jason Daggett |  |  | Not in the WP |  |  | PLCRVLLE | Sierra Assets | [11 empty] | 1 | -199999 | 200000 | 106900.9 | 0 | 93099.1 | On/Under Budget | 557694.7 | 26385 | 0 | 26385 | 17840.5 | 25084.5 | 3830.8 | 1865.8 | Project is not in the WP or in 2020 WP | 0 | 28250.8 | -28250.8 | 28250.8 | -28250.8 | 642.2 | 611.8 | 611.8 | 26385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 557694.7 | 0 | 0 | 0 | 0 | 0 | 0 | 557694.7
74014860 | R2 REPL OH COND/ ALTERNTE BACKTIE CE2104 |  | 5777380 | UNSE | 08W | OXL3 | Olaide Lamidi |  |  |  |  | Not in the WP |  |  | STCRUZ | [26 empty] | 244.8 | Project is not in the WP or in 2020 WP | 0 | 244.8 | -244.8 | 0 | 0
35236982 | NCF - RG - K1101 - REMOVAL 33 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 10163 | 10163 | 1.9248 | 0 | 1.9248 | [19 empty] | 471.2 | Project is not in the WP or in 2020 WP | 0 | 471.2 | -471.2 | 0 | 0
35236983 | NCF - RG - BB1102 - FH-73T (PARTIAL) |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | CHICO |  | 0 | 1600 | 1600 | 0.30303 | 0 | 0.30303 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35236984 | NCF - RG - W1103- REMOVAL 95, 96 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 9799 | 9799 | 1.8559 | 0 | 1.8559 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35236985 | NCF - RG - K1101- REMOVAL 28, 105,150 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 8401 | 8401 | 1.5911 | 0 | 1.5911 | [19 empty] | 394.4 | Project is not in the WP or in 2020 WP | 0 | 394.4 | -394.4 | 0 | 0
35236986 | NCF - RG - K1101 - REMOVAL 5 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 8315 | 8315 | 1.5748 | 0 | 1.5748 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35236988 | FRRB - KANAKA 1101 - K4 PH4.19 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 1293 | 1293 | 0.24489 | 0 | 0.24489 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35236989 | NCF - RG - K1101 - REMOVAL 1 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 2493 | 2493 | 0.47216 | 0 | 0.47216 | [19 empty] | 394.4 | Project is not in the WP or in 2020 WP | 0 | 394.4 | -394.4 | 0 | 0
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 | E.5034825.01.51 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 4118 | 0 | 4118 | 0.77992 | 0 | 0.77992 | [5 empty] | 105555 | 0 | 105555 | 382.2 | 0 | 105172.8 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 382.2 | Request 2021 Budget | 0 | 2730382.2 | -2730382.2 | 382.2 | -382.2 | 0 | 0 | 382.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-12 | Not Started | 2021-05-27 | 2021-06-02 | Not Started | 2021-05-26 | Not Started | 2021-07-07 | Not Started | [6 empty] | 2021-05-14 | 2021-05-20 | Not Started | 2021-07-09 | Not Started | 2021-07-09 | Not Started | 2021-09-24 | Not Started | 2021-07-09 | Not Started | 2021-10-08 | Not Started | 2021-10-08 | Not Started | 2021-11-09 | 2021-11-09 | 0 | On/ Ahead Schedule | Not Started | 2021-11-09 | 2021-11-23 | Not Started | 2022-01-06 | Not Started
35236991 | FRRB - WYANDOTTE 1103 - W4 PH4.8 | E.5034825.01.52 | 5795419 | UNSE | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  | FRRB | OROVILLE | North Valley Assets | 0 | 8805 | 8805 | 1.6676 | 0 | 1.6676 | [5 empty] | 95000 | 0 | 95000 | 0 | 0 | 95000 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-21 | Not Started | 2021-06-07 | 2021-06-11 | Not Started | 2021-06-04 | Not Started | 2021-07-16 | Not Started | [6 empty] | 2021-05-20 | 2021-05-26 | Not Started | 2021-07-20 | Not Started | 2021-07-20 | Not Started | 2021-10-05 | Not Started | 2021-07-20 | Not Started | 2021-10-19 | Not Started | 2021-10-19 | Not Started | 2021-11-18 | 2021-11-18 | 0 | On/ Ahead Schedule | Not Started | 2021-11-18 | 2021-12-02 | Not Started | 2022-01-17 | Not Started
35236992 | NCF - RG - K1101 - REMOVAL 24 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 3100 | 3100 | 0.58712 | 0 | 0.58712 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35236993 | FRRB - WYANDOTTE 1103 - W4 PH4.9 | E.5034825.01.54 | 5795419 | UNSE | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  | FRRB | OROVILLE | North Valley Assets | 0 | 2100 | 2100 | 0.39773 | 0 | 0.39773 | [5 empty] | 95000 | 0 | 95000 | 394.4 | 0 | 94605.6 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394.4 | Project is not in the WP or in 2020 WP | 0 | 394.4 | -394.4 | 394.4 | -394.4 | 0 | 0 | 394.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-21 | Not Started | 2021-06-07 | 2021-06-11 | Not Started | 2021-06-04 | Not Started | 2021-07-16 | Not Started | [6 empty] | 2021-05-20 | 2021-05-26 | Not Started | 2021-07-20 | Not Started | 2021-07-20 | Not Started | 2021-10-05 | Not Started | 2021-07-20 | Not Started | 2021-10-19 | Not Started | 2021-10-19 | Not Started | 2021-11-18 | 2021-11-18 | 0 | On/ Ahead Schedule | Not Started | 2021-11-18 | 2021-12-02 | Not Started | 2022-01-17 | Not Started
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 | E.5034825.01.55 | 5795419 | UNSE | 08W | CRGN | Christopher R Gras | ZXAC | Zaid Al-Saffar | T8B5 | Tyler Babin | Not in the WP |  | FRRB | OROVILLE | North Valley Assets | 0 | 21024 | 21024 | 3.9818 | 0 | 3.9818 | [5 empty] | 95000 | -855000 | 950000 | 530.7 | 0 | 949469.3 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530.7 | Project is not in the WP or in 2020 WP | 0 | 530.7 | -530.7 | 530.7 | -530.7 | 0 | 0 | 530.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-21 | Not Started | 2021-06-07 | 2021-06-11 | Not Started | 2021-06-04 | Not Started | 2021-07-16 | Not Started | [6 empty] | 2021-05-20 | 2021-05-26 | Not Started | 2021-07-20 | Not Started | 2021-07-20 | Not Started | 2021-10-05 | Not Started | 2021-07-20 | Not Started | 2021-10-19 | Not Started | 2021-10-19 | Not Started | 2021-11-18 | 2021-11-18 | 0 | On/ Ahead Schedule | Not Started | 2021-11-18 | 2021-12-02 | Not Started | 2022-01-17 | Not Started
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 8745 | 8745 | 1.6562 | 0 | 1.6562 | [19 empty] | 530.7 | Project is not in the WP or in 2020 WP | 0 | 530.7 | -530.7 | 0 | 0
35236999 | NCF - RG - K1101 - REMOVAL 3 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 5300 | 5300 | 1.0038 | 0 | 1.0038 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35237020 | NCF - RG - K1101 - REMOVAL 50 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 2100 | 2100 | 0.39773 | 0 | 0.39773 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35237021 | FRRB - KANAKA 1101 - K6 PH6 |  | 5795419 | UNSE | 08W | RVS7 | Richard Salcedo |  |  |  |  | Not in the WP |  | FRRB | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 |  | 5794542 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | VACAVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 235.6 | Project is not in the WP or in 2020 WP | 0 | 235.6 | -235.6 | 0 | 0
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 |  | 5794542 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | VACAVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 706.7 | Project is not in the WP or in 2020 WP | 0 | 706.7 | -706.7 | 0 | 0
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 |  | 5794542 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | VACAVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 706.7 | Project is not in the WP or in 2020 WP | 0 | 706.7 | -706.7 | 0 | 0
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 |  | 5794542 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | VACAVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 942.3 | Project is not in the WP or in 2020 WP | 0 | 942.3 | -942.3 | 0 | 0
35237364 | CWSP - VACA DIXON 110540092 PH 1.6 |  | 5794542 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | VACAVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35237365 | CWSP - VACA DIXON 110540092 PH 1.7 |  | 5794542 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | VACAVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35237366 | CWSP - VACA DIXON 110540092 PH 1.8 |  | 5794542 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | VACAVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 |  | 5794542 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | VACAVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 471.2 | Project is not in the WP or in 2020 WP | 0 | 471.2 | -471.2 | 0 | 0
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 |  | 5794542 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | VACAVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 235.6 | Project is not in the WP or in 2020 WP | 0 | 235.6 | -235.6 | 0 | 0
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 |  | 5794542 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | VACAVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 471.2 | Project is not in the WP or in 2020 WP | 0 | 471.2 | -471.2 | 0 | 0
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 |  | 5794542 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  | SH | VACAVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 1177.9 | Project is not in the WP or in 2020 WP | 0 | 1177.9 | -1177.9 | 0 | 0
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 | E.5034825.01.59 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 7234 | 0 | 7234 | 1.3701 | 0 | 1.3701 | [5 empty] | 105555 | 0 | 105555 | 1020 | 0 | 104535 | On/Under Budget | 0 | 0 | 129.6 | -129.6 | 0 | 0 | 0 | 1149.6 | Request 2021 Budget | 0 | 4796020 | -4796020 | 1020 | -1020 | 0 | 0 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-12 | Not Started | 2021-05-27 | 2021-06-02 | Not Started | 2021-05-26 | Not Started | 2021-07-07 | Not Started | [6 empty] | 2021-05-14 | 2021-05-20 | Not Started | 2021-07-09 | Not Started | 2021-07-09 | Not Started | 2021-09-24 | Not Started | 2021-07-09 | Not Started | 2021-10-08 | Not Started | 2021-10-08 | Not Started | 2021-11-09 | 2021-11-09 | 0 | On/ Ahead Schedule | Not Started | 2021-11-09 | 2021-11-23 | Not Started | 2022-01-06 | Not Started
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 | E.5034825.01.60 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 4277 | 0 | 4277 | 0.81004 | 0 | 0.81004 | [5 empty] | 105555 | 0 | 105555 | 1275 | 0 | 104280 | On/Under Budget | 0 | 0 | 162 | -162 | 0 | 0 | 0 | 1437 | Request 2021 Budget | 0 | 2836275 | -2836275 | 1275 | -1275 | 0 | 0 | 1275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-12 | Not Started | 2021-05-27 | 2021-06-02 | Not Started | 2021-05-26 | Not Started | 2021-07-07 | Not Started | [6 empty] | 2021-05-14 | 2021-05-20 | Not Started | 2021-07-09 | Not Started | 2021-07-09 | Not Started | 2021-09-24 | Not Started | 2021-07-09 | Not Started | 2021-10-08 | Not Started | 2021-10-08 | Not Started | 2021-11-09 | 2021-11-09 | 0 | On/ Ahead Schedule | Not Started | 2021-11-09 | 2021-11-23 | Not Started | 2022-01-06 | Not Started
35237891 | FRRB - WYANDOTTE 1103 - W3 PH3.4 | E.5034825.01.61 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 2429 | 0 | 2429 | 0.46004 | 0 | 0.46004 | [5 empty] | 105555 | 0 | 105555 | 0 | 0 | 105555 | On/Under Budget | 0 | 0 | 129.6 | -129.6 | 0 | 0 | 0 | 129.6 | Request 2021 Budget | 0 | 1610000 | -1610000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-12 | Not Started | 2021-05-27 | 2021-06-02 | Not Started | 2021-05-26 | Not Started | 2021-07-07 | Not Started | [6 empty] | 2021-05-14 | 2021-05-20 | Not Started | 2021-07-09 | Not Started | 2021-07-09 | Not Started | 2021-09-24 | Not Started | 2021-07-09 | Not Started | 2021-10-08 | Not Started | 2021-10-08 | Not Started | 2021-11-09 | 2021-11-09 | 0 | On/ Ahead Schedule | Not Started | 2021-11-09 | 2021-11-23 | Not Started | 2022-01-06 | Not Started
35237893 | FRRB - WYANDOTTE 1103 - W3 PH3.5 | E.5034825.01.62 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 1531 | 0 | 1531 | 0.28996 | 0 | 0.28996 | [5 empty] | 105555 | 0 | 105555 | 0 | 0 | 105555 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Request 2021 Budget | 0 | 1015000 | -1015000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-12 | Not Started | 2021-05-27 | 2021-06-02 | Not Started | 2021-05-26 | Not Started | 2021-07-07 | Not Started | [6 empty] | 2021-05-14 | 2021-05-20 | Not Started | 2021-07-09 | Not Started | 2021-07-09 | Not Started | 2021-09-24 | Not Started | 2021-07-09 | Not Started | 2021-10-08 | Not Started | 2021-10-08 | Not Started | 2021-11-09 | 2021-11-09 | 0 | On/ Ahead Schedule | Not Started | 2021-11-09 | 2021-11-23 | Not Started | 2022-01-06 | Not Started
35237894 | FRRB - WYANDOTTE 1103 - W3 PH3.6 | E.5034825.01.63 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 4541 | 0 | 4541 | 0.86004 | 0 | 0.86004 | [5 empty] | 105555 | 0 | 105555 | 0 | 0 | 105555 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Request 2021 Budget | 0 | 3010000 | -3010000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-12 | Not Started | 2021-05-27 | 2021-06-02 | Not Started | 2021-05-26 | Not Started | 2021-07-07 | Not Started | [6 empty] | 2021-05-14 | 2021-05-20 | Not Started | 2021-07-09 | Not Started | 2021-07-09 | Not Started | 2021-09-24 | Not Started | 2021-07-09 | Not Started | 2021-10-08 | Not Started | 2021-10-08 | Not Started | 2021-11-09 | 2021-11-09 | 0 | On/ Ahead Schedule | Not Started | 2021-11-09 | 2021-11-23 | Not Started | 2022-01-06 | Not Started
35237895 | FRRB - WYANDOTTE 1103 - W3 PH3.7 | E.5034825.01.64 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 4171 | 0 | 4171 | 0.78996 | 0 | 0.78996 | [5 empty] | 105555 | 0 | 105555 | 0 | 0 | 105555 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Request 2021 Budget | 0 | 2765000 | -2765000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-12 | Not Started | 2021-05-27 | 2021-06-02 | Not Started | 2021-05-26 | Not Started | 2021-07-07 | Not Started | [6 empty] | 2021-05-14 | 2021-05-20 | Not Started | 2021-07-09 | Not Started | 2021-07-09 | Not Started | 2021-09-24 | Not Started | 2021-07-09 | Not Started | 2021-10-08 | Not Started | 2021-10-08 | Not Started | 2021-11-09 | 2021-11-09 | 0 | On/ Ahead Schedule | Not Started | 2021-11-09 | 2021-11-23 | Not Started | 2022-01-06 | Not Started
35237896 | FRRB - WYANDOTTE 1103 - W3 PH3.8 | E.5034825.01.65 | 5795419 | UNSE | 08W | SLKD | Sharon Kennedy | VBA1 | Violeta Alcantara | MUHQ | Matt Haley | 2021 |  | FRRB | OROVILLE | North Valley Assets | 5861 | 0 | 5861 | 1.11 | 0 | 1.11 | [5 empty] | 105555 | 0 | 105555 | 0 | 0 | 105555 | On/Under Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Request 2021 Budget | 0 | 3885000 | -3885000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-04-02 |  |  |  |  | 2021-05-12 | Not Started | 2021-05-27 | 2021-06-02 | Not Started | 2021-05-26 | Not Started | 2021-07-07 | Not Started | [6 empty] | 2021-05-14 | 2021-05-20 | Not Started | 2021-07-09 | Not Started | 2021-07-09 | Not Started | 2021-09-24 | Not Started | 2021-07-09 | Not Started | 2021-10-08 | Not Started | 2021-10-08 | Not Started | 2021-11-09 | 2021-11-09 | 0 | On/ Ahead Schedule | Not Started | 2021-11-09 | 2021-11-23 | Not Started | 2022-01-06 | Not Started
35238087 | REMG - OAKHURST 110110090 |  | 0000000 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | OAKHURST | [27 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35238088 | REMG 531 - MARIPOSA 2101, SLAUGHTER HOUS |  | 5544972 | UNSE | 08W | PJMW | Patrick James McCabe |  |  |  |  | Not in the WP |  |  | MARIPOSA | [26 empty] | 7767.7 | Project is not in the WP or in 2020 WP | 0 | 7767.7 | -7767.7 | 0 | 0
Note on B821: Al-Saffar, Zaid: move it to 2022 and request budget for 2021 and $500k and the rest is 2022
Note on B1233: Al-Saffar, Zaid: move it to 2022 and request budget for 2021 and $500k and the rest is 2022
Note on B1234: Al-Saffar, Zaid: move it to 2022 and request budget for 2021 and $500k and the rest is 2022
Note on B1341: Al-Saffar, Zaid: move it to 2022 and request budget for 2021 and $500k and the rest is 2022

## Raghu Sheet
Order | Description | WBS Element | User Status | MAT | Job Owner | Job Owner Desc | Authorized Amt | Contingency | AJE Amt
35113109 |  | E.5014535.02 | CLSD | 08W | SLKD | Sharon Kennedy | 300000 | 0 | 300000
35113104 | CWSP - Los Gatos 1106 - LB44 - Phase 1.2 | E.5014319.02 | CLSD | 08W | SLKD | Sharon Kennedy | 517390 | 100243 | 417147
35080227 | Calistoga 1101 - Legal Hold |  | ADER | 08W | J1E1 | Josh Eagar | 178900 | 178900 | 0
35113103 | CWSP - Los Gatos 1106 - LB44 - Phase 1.3 | E.5014319.03 | CLSD | 08W | SLKD | Sharon Kennedy | 390567 | 26780 | 363787
74022387 | MIDDLETOWN 1101-TS 1079 | E.5014744.01 | CLSD | 08W | HXJI | Haridayal Jaswal | 5829000 | 0 | 5829000
74022382 | Columbia Hill 1101 |  | CLSD | 08W | J6KF | Jeff L Kringler
35098578 | CWSP-COLUMBIA HILL 1101-LR 2212 Ph 2 | E.5015491.02 | CLSD | 08W | J6KF | Jeff L Kringler | 3550706 | -1.7 | 3550707.7
35098579 | CWSP-COLUMBIA HILL 1101-LR 2212 Ph 3 | E.5015491.03 | CLSD | 08W | J6KF | Jeff L Kringler | 2438915 | 416398.7 | 2022516.3
35112426 | CWSP - El Dorado 2101 - OCB Zone - Ph 1.3 |  | CLSD | 08W | J6KF | Jeff L Kringler
35112427 | CWSP - El Dorado 2101 - OCB Zone - Ph 1.4 | E.5015420.04 | CLSD | 08W | J6KF | Jeff L Kringler | 3306693 | 969939.2 | 2336753.8
35103324 | CWSP - Rossmoor 1102 OCB | E.5014544.03 | CLSD | 08W | PXSO | Peter Siu | 2510809 | 0 | 2510809
35111500 | RECONDUCTOR UPPER LAKE 01 HUNTERS PT RD |  | CLSD | 08W | J7LE | Jared Warren Lee | 425000 | 0 | 425000
35081748 | Rob Roy 2105-SO28CC1119 | P.12007 | CLSD | 08W | SLKD | Sharon Kennedy | 713114 | 80294 | 632820
35072362 | Eel River 1102 |  | CLSD | 08W | S2WT | Steve Whitman
35072720 | Gabilan 1101 17-0077248 | E.5015593.01 | CLSD | 08W | SLKD | Sharon Kennedy | 1869000 | 321276 | 1547724
35066745 | Big Bend 1102 - Bloomer Hill |  | CLSD | 08W | CRGN | Christopher R Gras | 3916190 | 1146536 | 2769654
35060229 | Fruitland 1142 |  | CLSD | 08W | S2WT | Steve Whitman
35008479 | Auberry 1101 Reconductor |  | CLSD | 08W | B1GQ | Brian Gallo
35018787 | Halsey 1101 |  | CLSD | 08W | CRGN | Christopher R Gras | 873318 | 6743 | 866575
35018788 | Apple Hill 1104 |  | CLSD | 08W | CRGN | Christopher R Gras | 1995745 | 314578 | 1681167
31360766 | FROGTOWN 1701 RECOND 1080FT TO 2AR |  | CLSD | 08W | J1PE | Jaime Pantoja-Martinez | 474763 | 57925 | 416838
35019006 | Rob Roy 2104 CO11865 |  | CLSD | 08W | SLKD | Sharon Kennedy | 1485645.6 | 326113.6 | 1159532
35030654 | TW ON WOODSIDE1101 N/O 7573 |  | CLSD | 08W | SLKD | Sharon Kennedy
35031139 | Shady Glen 1102 |  | CLSD | 08W | CRGN | Christopher R Gras | 2668456 | 157254 | 2511202
35032266 | Apple Hill 1104 - 2 |  | CLSD | 08W | CRGN | Christopher R Gras | 368711 | 17504.8 | 351206.2
35039002 | DEMO - 2018 CALISTOGA 1101 WILDFIRE DEMO Comp |  | CLSD | 08W | LLM0 | Linda L Swartz
35042719 | CWSP DEMO: ANGWIN (Silverado) Steel |  | CLSD | 08W | LLM0 | Linda L Swartz
35043291 | CWSP- PINE GROVE 1102 LR9145 WFH LEVEL 1 |  | CLSD | 08W | J1PE | Jaime Pantoja-Martinez
35040225 | Higgins 1110 |  | CLSD | 08W | CRGN | Christopher R Gras | 2449837 | 0 | 2449837
31215474 | Reconductor Rob Roy 2104 McDonald | P.11413 | CLSD | 08W | SLKD | Sharon Kennedy | 625339 | 81566 | 543773
31286573 | Apple Hill 2102 |  | CLSD | 08W | CRGN | Christopher R Gras | 900307 | 326267 | 574040
31278200 | OCEANO 1102 S HALCYON & PINE RDGE | P.11685 | CLSD | 08W | A2LH | Anthony Joseph Lucero | 496629 | 20000 | 476629
31290147 | Olema 1101 |  | CLSD | 08W | JBCT | Joseph B Cruz
31319444 | Rincon 1103 |  | CLSD | 08W | JBCT | Joseph B Cruz
31326119 | Weimar 1101 | P.11895 | CLSD | 08W | CRGN | Christopher R Gras | 1325896 | 251591.5 | 1074304.5
31334292 | Austin Creek Rd |  | CLSD | 08W | S2WT | Steve Whitman
35085536 | CWSP Silverado 2104 1G | E.5014772.07 | DOCC | 08W | J1E1 | Josh Eagar | 1950000 | 0.4 | 1949999.6
35085681 | SILVERADO 2105 WIRE DOWN PH 4 | E.5014317.05 | DOCC | 08W | J1E1 | Josh Eagar | 500000 | -0.5 | 500000.5
35094390 | CWSP Konocti-1102-LR 532 PH 3 | E.5015029.04 | DOCC | 08W | J1E1 | Josh Eagar | 900000 | -0.3 | 900000.3
35109543 | CWSP - El Dorado 2101 - 19752 - PHASE 1.5 | E.5015417.05 | DOCC | 08W | T3SQ | Travis Damian Skarda | 3608462 | 457433.2 | 3151028.8
35057017 | CWSP - EL DORADO 2101 - 19752 - PHASE 3.1 | E.5015415.01 | DOCC | 08W | T3SQ | Travis Damian Skarda | 3201494 | -0.4 | 3201494.4
35061709 | Silverado 2104 |  | DOCC | 08W | S2WT | Steve Whitman
35043299 | Eel River 1102 - 3 |  | DOCC | 08W | A1CO | Antonio Miguel Chan | 1224411 | 0.4 | 1224410.6
35043303 | Eel River 1102 - 2 |  | DOCC | 08W | S2WT | Steve Whitman
31289238 | Fruitland 1142-2 |  | DOCC | 08W | S2WT | Steve Whitman
31275658 | Dunbar 1102 |  | DOCC | 08W | A1CO | Antonio Miguel Chan | 1092540 | 317223.4 | 775316.6
31209950 | Potter Valley 1105 | P.11913 | DOCC | 08W | A1CO | Antonio Miguel Chan | 273660 | -943257.9 | 1216917.9
35023687 | Ben Lomond 0401 | P.11844 | DOCC | 08W | SLKD | Sharon Kennedy | 4004352 | 0 | 4004352
74024171 | Calistoga 1101 - Petrified Forest Rd. | E.5019956.01 | DOCC | 08W | J7LE | Jared Warren Lee | 1714904 | 1714904 | 0
74021903 | BRUNSWICK 1105 LR-1030 ZONE | E.5015036.01 | DOCC | 08W | CRGN | Christopher R Gras | 12463097 | 0 | 12463097
74021960 | BRUNSWICK 1105 (LR 32536) | E.5015470.01 | DOCC | 08W | CRGN | Christopher R Gras | 15621955 | 0 | 15621955
74021961 | MIRABEL 1102 /MONTE RIO 13 - LR 652 | E.5014743.01 | DOCC | 08W | HXJI | Haridayal Jaswal | 6996439 | 0 | 6996439
35072146 | Silverado 2105 WIRE DOWN OH | E.5014317.01 | FICL | 08W | J1E1 | Josh Eagar | 2410000 | -0.1 | 2410000.1
35064793 | LP CABRILLO 1104 S006CC102 |  | FICL | 08W | B1GQ | Brian Gallo
35085393 | CWSP Silverado 2104 1B | E.5014772.02 | FICL | 08W | J1E1 | Josh Eagar | 1300000 | 0.5 | 1299999.5
35085532 | CWSP Silverado 2104 1C:Harden OH In Place | E.5014772.03 | FICL | 08W | J1E1 | Josh Eagar | 2100000 | 0.2 | 2099999.8
35085533 | CWSP Silverado 2104 1D | E.5014772.04 | FICL | 08W | J1E1 | Josh Eagar | 2100000 | 0 | 2100000
35094392 | CWSP Konocti-1102-LR 532 PH 5 | E.5015029.06 | FICL | 08W | J1E1 | Josh Eagar | 270000 | 0 | 270000
35094388 | CWSP Konocti-1102-LR 532 PH 1 | E.5015029.02 | FICL | 08W | J1E1 | Josh Eagar | 400000 | -0.2 | 400000.2
35109542 | CWSP - El Dorado 2101 - 19752 - PHASE 1.4 | E.5015417.04 | FICL | 08W | T3SQ | Travis Damian Skarda | 3529311 | 743625.1 | 2785685.9
35095165 | Volta 1102 LR 1648 Ph 3.1 | E.5015704.01 | FICL | 08W | M5HF | Michael Donald James Hernandez | 3514354 | 162325.5 | 3352028.5
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 Ph 5 | E.5015491.05 | FICL | 08W | J6KF | Jeff L Kringler | 4936253 | 781728.6 | 4154524.4
35060582 | SLO 1107 Recon 3,836 ft of 4ar to 2cu in corrosion zone |  | FICL | 08W | B1GQ | Brian Gallo
31290145 | San Rafael 1107 |  | FICL | 08W | S2WT | Steve Whitman
31269259 | ZACA 1101 FOXEN CYN RD, LOS OLIVOS |  | FICL | 08W | B1GQ | Brian Gallo
31232280 | ZACA 1102 LONG CYN RD, SANTA YNEZ |  | FICL | 08W | B1GQ | Brian Gallo
35024926 | MARTELL 1101 RECONDCUTOR 3,700FT |  | FICL | 08W | J1PE | Jaime Pantoja-Martinez | 824970 | 121913 | 703057
74022040 | CALISTOGA 1101 |  | FICL | 08W | S2WT | Steve Whitman
31389447 | PUEBLO 1105 RECONDUCTOR PROJECT | P.11939 | MAPP | 08W | J1E1 | Josh Eagar | 3937382 | 0 | 3937382
35112076 | CWSP - FULTON 1107 - MARK WEST SPR RD. |  | MAPP | 08W | S2WT | Steve Whitman
31082393 | Cherry Ridge Road |  | PREC | 08W | S2WT | Steve Whitman

## Sheet1 (hidden)
Order | Description
35113109
35113104 | CWSP - Los Gatos 1106 - LB44 - Phase 1.2
35030654 | TW ON WOODSIDE1101 N/O 7573
35113103 | CWSP - Los Gatos 1106 - LB44 - Phase 1.3
35103324 | CWSP - Rossmoor 1102 OCB
74021961 | MIRABEL 1102 /MONTE RIO 13 - LR 652
35042719 | CWSP DEMO: ANGWIN (Silverado) Steel
35085393 | CWSP Silverado 2104 1B
35072146 | Silverado 2105 WIRE DOWN OH
35061709 | Silverado 2104
31334292 | Austin Creek Rd
31389447 | PUEBLO 1105 RECONDUCTOR PROJECT
31319444 | Rincon 1103
31209950 | Potter Valley 1105
31290145 | San Rafael 1107
31082393 | Cherry Ridge Road
74022040 | CALISTOGA 1101
31289238 | Fruitland 1142-2
31275658 | Dunbar 1102
35085533 | CWSP Silverado 2104 1D
35060229 | Fruitland 1142
35094390 | CWSP Konocti-1102-LR 532 PH 3
74022387 | MIDDLETOWN 1101-TS 1079
35085536 | CWSP Silverado 2104 1G
31290147 | Olema 1101
74024171 | Calistoga 1101 - Petrified Forest Rd.
35085532 | CWSP Silverado 2104 1C:Harden OH In Place
35094388 | CWSP Konocti-1102-LR 532 PH 1
35111500 | RECONDUCTOR UPPER LAKE 01 HUNTERS PT RD
35039002 | DEMO - 2018 CALISTOGA 1101 WILDFIRE DEMO Comp
35043299 | Eel River 1102 - 3
35043303 | Eel River 1102 - 2
35085681 | SILVERADO 2105 WIRE DOWN PH 4
35094392 | CWSP Konocti-1102-LR 532 PH 5
35072362 | Eel River 1102
35080227 | Calistoga 1101 - Legal Hold
35112076 | CWSP - FULTON 1107 - MARK WEST SPR RD.
35095165 | Volta 1102 LR 1648 Ph 3.1
35032266 | Apple Hill 1104 - 2
74021960 | BRUNSWICK 1105 (LR 32536)
74021903 | BRUNSWICK 1105 LR-1030 ZONE
74022382 | Columbia Hill 1101
35098578 | CWSP-COLUMBIA HILL 1101-LR 2212 Ph 2
35109543 | CWSP - El Dorado 2101 - 19752 - PHASE 1.5
35066745 | Big Bend 1102 - Bloomer Hill
35057017 | CWSP - EL DORADO 2101 - 19752 - PHASE 3.1
31326119 | Weimar 1101
35040225 | Higgins 1110
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 Ph 5
35031139 | Shady Glen 1102
35018787 | Halsey 1101
35098579 | CWSP-COLUMBIA HILL 1101-LR 2212 Ph 3
35018788 | Apple Hill 1104
35109542 | CWSP - El Dorado 2101 - 19752 - PHASE 1.4
31286573 | Apple Hill 2102
35112427 | CWSP - El Dorado 2101 - OCB Zone - Ph 1.4
35112426 | CWSP - El Dorado 2101 - OCB Zone - Ph 1.3
35081748 | Rob Roy 2105-SO28CC1119
35023687 | Ben Lomond 0401
31278200 | OCEANO 1102 S HALCYON & PINE RDGE
35060582 | SLO 1107 Recon 3,836 ft of 4ar to 2cu in corrosion zone
35064793 | LP CABRILLO 1104 S006CC102
31215474 | Reconductor Rob Roy 2104 McDonald
35008479 | Auberry 1101 Reconductor
35019006 | Rob Roy 2104 CO11865
31232280 | ZACA 1102 LONG CYN RD, SANTA YNEZ
31269259 | ZACA 1101 FOXEN CYN RD, LOS OLIVOS
35072720 | Gabilan 1101 17-0077248
35024926 | MARTELL 1101 RECONDCUTOR 3,700FT
31360766 | FROGTOWN 1701 RECOND 1080FT TO 2AR
35043291 | CWSP- PINE GROVE 1102 LR9145 WFH LEVEL 1

## DOT_Changes
Change ID | Change Request Type | Order | Notification | Order Description | Change Request Status | MAT | Sub-Category | Updated Sub-Category | Civil Resource | Electric Resource | New Civil Resource | New Electric Resource | Business Justification | Work Plan Date | Updated Work Plan Date | Est Const Hours | Authorized Amount | Initial Funding Year | New Construction Complete Year | Updated New Construction Complete Year | MPP Approved Budget (2020) | MPP Approved Budget (2021) | Requested Budget for 2020 | Requested Budget for 2021 | Requested Budget for 2022 | Requested Budget for 2023 | Req End Date | User Status | CN24 Out Date | CSTRT Finish Date (P6) | Job Owner | Job Owner Name | Strike Force Population | Exclusions | Updated Strike Force Population | Updated Exclusions | Past Due Reason | Estimating Review | Estimating Comments | Construction Review | Construction Comments | Program Manager | Program Manager Review | Program Manager Comments | Warning Message | Portfolio Manager Review | Portfolio Manager Comments | Last Changed By | Last Changed On | Last Changed Name | Created By | Created On | Creator Name
66001 | Resource change | 35233314 | 120541635 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 5600000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 18:20 | Pereyda, Jessica Ann Hiroko
66000 | Resource change | 35226624 | 120445228 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-08-17 |  | 111.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 18:19 | Pereyda, Jessica Ann Hiroko
65999 | Resource change | 35235705 | 120594567 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 4620000 |  |  |  |  | 2022-03-03 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 18:18 | Pereyda, Jessica Ann Hiroko
65998 | Resource change | 35233311 | 120541633 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 4375000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 18:17 | Pereyda, Jessica Ann Hiroko
65997 | Resource change | 35232718 | 120538803 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Approved | 08W |  |  |  |  | N/A | Contract | 4.2 Resource Update to Contract | 2021-05-24 |  | 0 | 118750 | 2021 |  |  |  | 4200000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-05-24 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 18:12 | Pereyda, Jessica Ann Hiroko
65996 | Resource change | 35235706 | 120594568 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 4060000 |  |  |  |  | 2022-03-03 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 18:06 | Pereyda, Jessica Ann Hiroko
65995 | Resource change | 35226623 | 120445227 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-08-17 |  | 111.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 18:05 | Pereyda, Jessica Ann Hiroko
65994 | Resource change | 35233312 | 120541634 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 3850000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 18:04 | Pereyda, Jessica Ann Hiroko
65993 | Resource change | 35227029 | 120449800 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-07-27 |  | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-07-27 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 18:01 | Pereyda, Jessica Ann Hiroko
65992 | Resource change | 35233315 | 120541636 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 3360000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 18:00 | Pereyda, Jessica Ann Hiroko
65991 | Resource change | 35235707 | 120594569 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 3325000 |  |  |  |  | 2022-03-03 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:56 | Pereyda, Jessica Ann Hiroko
65990 | Resource change | 35233308 | 120541539 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-04-28 |  | 30.1 | 6280110 | 2021 |  |  |  | 1761818.18 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:55 | Pereyda, Jessica Ann Hiroko
65989 | Resource change | 35219272 | 120142171 | CWSP - MIDDLETOWN 1101481876 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-07-21 |  | 130.1 | 950000 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-07-21 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:53 | Pereyda, Jessica Ann Hiroko
65988 | Resource change | 35227027 | 120449717 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-08-17 |  | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:53 | Pereyda, Jessica Ann Hiroko
65987 | Resource change | 35226622 | 120445225 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-08-17 |  | 111.1 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:52 | Pereyda, Jessica Ann Hiroko
65986 | Resource change | 35219098 | 120141805 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-10-21 |  | 130.1 | 475000 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-10-21 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:50 | Pereyda, Jessica Ann Hiroko
65985 | Resource change | 35229119 | 120496477 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-10-15 |  | 110.1 | 475000 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-10-15 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:49 | Pereyda, Jessica Ann Hiroko
65984 | Resource change | 35233307 | 120541538 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-04-28 |  | 30.1 | 4778094 | 2021 |  |  |  | 2090056.82 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:48 | Pereyda, Jessica Ann Hiroko
65983 | Resource change | 35227028 | 120449719 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-08-18 |  | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-08-18 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:46 | Pereyda, Jessica Ann Hiroko
65982 | Resource change | 35233309 | 120541630 | FRRB - WYANDOTTE 1103 - W1 PH1.13 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-04-28 |  | 30.1 | 3728491 | 2021 |  |  |  | 1282670.45 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:46 | Pereyda, Jessica Ann Hiroko
65981 | Resource change | 35233039 | 120542500 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-04-28 |  | 30.1 | 3729353 | 2021 |  |  |  | 1283333.33 |  |  |  |  | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:28 | Pereyda, Jessica Ann Hiroko
65980 | Resource change | 35233301 | 120542503 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-04-28 |  | 30.1 | 3715565 | 2021 |  |  |  | 1272727.27 |  |  |  |  | 2022-01-01 | UNSE |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:27 | Pereyda, Jessica Ann Hiroko
65979 | Resource change | 35233300 | 120542502 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-04-28 |  | 30.1 | 3535462 | 2021 |  |  |  | 1134185.61 |  |  |  |  | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:25 | Pereyda, Jessica Ann Hiroko
65978 | Resource change | 35233304 | 120542506 | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-04-28 |  | 30.1 | 3444978 | 2021 |  |  |  | 1064583.33 |  |  |  |  | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:22 | Pereyda, Jessica Ann Hiroko
65977 | Resource change | 35233305 | 120542507 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-04-28 |  | 30.1 | 3378623 | 2021 |  |  |  | 1013541.67 |  |  |  |  | 2022-01-01 | UNSE |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:21 | Pereyda, Jessica Ann Hiroko
65976 | Resource change | 35192281 | 119556250 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-08-17 |  | 110.1 | 950000 | 2021 | [8 empty] | 2023-12-31 | ESTS |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:20 | Pereyda, Jessica Ann Hiroko
65975 | Resource change | 35233306 | 120541535 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-04-28 |  | 30.1 | 3246777 | 2021 |  |  |  | 500000 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:18 | Pereyda, Jessica Ann Hiroko
65974 | Resource change | 35232298 | 120532441 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-04-28 |  | 30.1 | 3159481 | 2021 |  |  |  | 845833.33 |  |  |  |  | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:15 | Pereyda, Jessica Ann Hiroko
65973 | Resource change | 35233038 | 120542278 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-04-28 |  | 30.1 | 3118378 | 2021 |  |  |  | 813352.27 |  |  |  |  | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:14 | Pereyda, Jessica Ann Hiroko
65972 | Resource change | 35233302 | 120542504 | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-04-21 |  | 0.6 | 147014.36 | 2021 |  |  |  | 500000 |  |  |  |  | 2022-01-01 | ESTS |  | 2021-04-21 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:12 | Pereyda, Jessica Ann Hiroko
65971 | Resource change | 35233310 | 120541632 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-04-28 |  | 30.1 | 2743520 | 2021 |  |  |  | 500000 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 17:11 | Pereyda, Jessica Ann Hiroko
65970 | Resource change | 35233303 | 120542505 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Approved | 08W |  |  |  | GC | N/A | Contract | 4.2 Resource Update to Contract | 2021-04-28 |  | 30.1 | 2470520 | 2021 |  |  |  | 500000 |  |  |  |  | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-04-04 15:08 | Saraf, Shubham | JUPX | 2021-04-02 16:28 | Pereyda, Jessica Ann Hiroko
65928 | Add project | 35234398 |  | CWSP - OREGON TRAIL 110335002 PHASE 6.2 | Program Manager Review | 08W | [6 empty] | Projects was approved on 4/1/2021 by WFGC to bring into the workplan. Current submitted workplan dates are placeholder dates and will be superceded once project schedule is completed. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | MXUA | Ung, Mason | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-04-02 13:04 | Yuen, Aaron Ho
65929 | Add project | 35234399 |  | CWSP - OREGON TRAIL 110335002 PHASE 6.3 | Program Manager Review | 08W | [6 empty] | Projects was approved on 4/1/2021 by WFGC to bring into the workplan. Current submitted workplan dates are placeholder dates and will be superceded once project schedule is completed. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | MXUA | Ung, Mason | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-04-02 13:04 | Yuen, Aaron Ho
65930 | Add project | 35234400 |  | CWSP - OREGON TRAIL 110335002 PHASE 6.4 | Program Manager Review | 08W | [6 empty] | Projects was approved on 4/1/2021 by WFGC to bring into the workplan. Current submitted workplan dates are placeholder dates and will be superceded once project schedule is completed. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | MXUA | Ung, Mason | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-04-02 13:04 | Yuen, Aaron Ho
65931 | Add project | 35234401 |  | CWSP - OREGON TRAIL 110335002 PHASE 6.5 | Program Manager Review | 08W | [6 empty] | Projects was approved on 4/1/2021 by WFGC to bring into the workplan. Current submitted workplan dates are placeholder dates and will be superceded once project schedule is completed. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | MXUA | Ung, Mason | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-04-02 13:04 | Yuen, Aaron Ho
65932 | Add project | 35219591 |  | CWSP - OLETA 1101754718 | Program Manager Review | 08W | [6 empty] | Projects was approved on 4/1/2021 by WFGC to bring into the workplan. Current submitted workplan dates are placeholder dates and will be superceded once project schedule is completed. | 2021-12-31 |  |  |  | 2021 | [9 empty] | ESTS |  |  | PJMW | Mccabe, Patrick James | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-04-02 13:04 | Yuen, Aaron Ho
65933 | Add project | 35236662 |  | CWSP - OLETA 1101754718 PH 1.2 | Program Manager Review | 08W | [6 empty] | Projects was approved on 4/1/2021 by WFGC to bring into the workplan. Current submitted workplan dates are placeholder dates and will be superceded once project schedule is completed. | 2021-12-31 |  |  |  | 2021 | [9 empty] | ESTS |  |  | PJMW | Mccabe, Patrick James | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-04-02 13:04 | Yuen, Aaron Ho
65934 | Add project | 35219542 |  | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Program Manager Review | 08W | [6 empty] | Projects was approved on 4/1/2021 by WFGC to bring into the workplan. Current submitted workplan dates are placeholder dates and will be superceded once project schedule is completed. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | PJMW | Mccabe, Patrick James | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-04-02 13:04 | Yuen, Aaron Ho
65927 | Add project | 35219287 |  | CWSP - OREGON TRAIL 110335002 PHASE 6 | Program Manager Review | 08W | [6 empty] | Projects was approved on 4/1/2021 by WFGC to bring into the workplan. Current submitted workplan dates are placeholder dates and will be superceded once project schedule is completed. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | PJMW | Mccabe, Patrick James | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-04-02 13:04 | Yuen, Aaron Ho
65926 | Add project | 35238098 |  | ECOP - SILVERADO 2104 - H05 - LR726 PH 6 | Program Manager Review | 08W | [6 empty] | PM created as PH6 to avoid idle facilities on ML UG work | 2021-11-20 |  |  |  | 2021 | [5 empty] | 190000 |  |  |  | ESTS |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | [8 empty] | J1E1 | 2021-04-02 12:04 | Eagar, Josh
65909 | Defer project | 35231608 | 120504095 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Construction Review | 08W |  |  |  | GC |  |  | Updated Construction Completion year to match forecast. | 2021-08-09 | 2022-08-01 | 110.1 | 1 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-08-09 | J6KF | Kringler, Jeff L | [5 empty] | Approved |  |  |  | Merih Tekeste | [5 empty] | M2HA | 2021-04-02 09:25 | Camacho, Margaux L. | M4JQ | 2021-04-01 13:46 | James, Matthew
65905 | Update work plan date | 35227655 | 120462115 | CWSP - KIRKER 2104442850 PH 1.2 | Denied | 08W | [6 empty] | OH removal for proposed remote grid project planned for 2022. | 2022-01-31 | 2022-06-01 | 80 | 450000 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2022-01-31 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Cannot update work plan date to 2022 , should be a defer project request type | SFSS | 2021-04-04 15:12 | Saraf, Shubham | M1NO | 2021-04-01 13:08 | Nguyen, My-Linh
65903 | Add project | 35144944 | 118261958 | PSPS - SNEATH LANE 1107 - LR 48338 | Program Manager Review | 08W | [6 empty] | Add project back into MPP workplan. Approved by WFGC on 3/24/21 | 2022-03-01 |  |  |  | 2022 | [9 empty] | PEND |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | [8 empty] | M1NO | 2021-04-01 12:33 | Nguyen, My-Linh
65901 | Defer project | 35094513 | 114567769 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Construction Review | 08W |  |  |  | Contract |  |  | CalTrans DSDD approval not expected until EOY 2021 or 2022 | 2021-12-30 | 2022-06-01 | 1781.5 | 3142865.56 | 2021 | 2022 | 2022 | 48176.5 | 4178901 |  | 500000 | 3678901 |  | 2021-12-20 | PEND |  | 2021-12-30 | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste | [8 empty] | T1DA | 2021-04-01 11:57 | Daugherty, Tracy
65669 | Add project | 35222234 |  | REMG 581 - OAKHURST 1101, MIAMI MOUNTAIN | Program Manager Review | 08W | [6 empty] | Adding 2021 Remote Grid Projects as requested | 2021-12-31 |  |  |  | 2021 |  |  |  |  | 0 | 1000000 |  |  |  | ESTS |  |  | TXY6 | Yang, Tom |  |  | Critical Work | [6 empty] | Merih Tekeste | [8 empty] | A1L6 | 2021-04-01 09:18 | Herrera, Alexis Ann
65668 | Add project | 35229051 |  | REMG 299/300 - CORNING 1102, TURRI ELLIS | Program Manager Review | 08W | [6 empty] | Adding 2021 Remote Grid Projects as requested | 2021-12-31 |  |  |  | 2021 |  |  |  |  | 0 | 1000000 |  |  |  | UNSE |  |  | MXUA | Ung, Mason |  |  | Critical Work | [6 empty] | Merih Tekeste | [8 empty] | A1L6 | 2021-04-01 09:18 | Herrera, Alexis Ann
65667 | Add project | 35056438 |  | REMG 650 - PLACERVILLE 2106, RINGTAIL | Program Manager Review | 08W | [6 empty] | Adding 2021 Remote Grid Projects as requested | 2021-12-31 |  |  |  | 2021 |  |  |  |  | 0 | 775000 |  |  |  | UNSE |  |  | J1NV | Nicolas, Jonathan |  |  | Critical Work | [6 empty] | Merih Tekeste | [8 empty] | A1L6 | 2021-04-01 09:16 | Herrera, Alexis Ann
65665 | Add project | 35222235 |  | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Program Manager Review | 08W | [6 empty] | Adding 2021 Remote Grid Projects as requested | 2021-12-31 |  |  |  | 2021 |  |  |  |  | 0 | 625000 |  |  |  | UNSE |  |  | JSZ2 | Zafar, Jan Salim |  |  | Critical Work | [6 empty] | Merih Tekeste | [8 empty] | A1L6 | 2021-04-01 09:02 | Herrera, Alexis Ann
65666 | Add project | 35238088 |  | REMG 531 - MARIPOSA 2101, SLAUGHTER HOUS | Program Manager Review | 08W | [6 empty] | Adding 2021 Remote Grid Projects as requested | 2021-12-31 |  |  |  | 2021 |  |  |  |  | 0 | 800000 |  |  |  | UNSE |  |  | PJMW | Mccabe, Patrick James |  |  | Critical Work | [6 empty] | Merih Tekeste | [8 empty] | A1L6 | 2021-04-01 08:57 | Herrera, Alexis Ann
65647 | Update work plan date | 35236660 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Denied | 08W | [6 empty] | Underground segements of Middletown LR548 that is now forecasted for execution in 2022. Requesting to defer from current year to 2022 execution. Workplan date not yet avaliable and provided WP date is placeholder to be superceded by P6 data |  | 2022-12-31 |  |  |  |  | 2022 | [7 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Job is not on workplan. To add job to work plan please submit and add job request. | BCMK | 2021-04-01 13:02 | Mueller, Bret Charles | AXYX | 2021-03-31 17:00 | Yuen, Aaron Ho
65646 | Update work plan date | 35236439 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Denied | 08W | [6 empty] | Underground segements of Middletown LR548 that is now forecasted for execution in 2022. Requesting to defer from current year to 2022 execution. Workplan date not yet avaliable and provided WP date is placeholder to be superceded by P6 data |  | 2022-12-31 |  |  |  |  | 2022 | [7 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Job is not on workplan. To add job to work plan please submit and add job request. | BCMK | 2021-04-01 13:02 | Mueller, Bret Charles | AXYX | 2021-03-31 17:00 | Yuen, Aaron Ho
65645 | Resource change | 35225824 | 120424703 | FRRB - WYANDOTTE 1103 - HWY 162 | Approved | 08W |  |  |  | GC | Contract | Contract | 3.31 Resource Update to Contract per Joe Hambree | 2021-04-05 |  | 1434.6 | 11016312 | 2021 |  |  |  | 8094904 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-04-05 | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-04-01 13:55 | Mueller, Bret Charles | JUPX | 2021-03-31 16:54 | Pereyda, Jessica Ann Hiroko
65644 | Resource change | 35223344 | 120255980 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Approved | 08W |  |  |  | GC | Contract | Contract | 3.31 Resource Update to Contract per Joe Hambree | 2021-02-12 |  | 1781.8 | 10286697 | 2021 |  |  |  | 6324922 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-02-12 | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-04-01 13:55 | Mueller, Bret Charles | JUPX | 2021-03-31 16:53 | Pereyda, Jessica Ann Hiroko
65618 | Pull-in Project from Future Year | 35226870 | 120449231 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Program Manager Review | 08W | [6 empty] | OH; base map n/a; 2021 possible execution | 2022-11-01 | 2021-11-20 | 0 | 67857 | 2021 | 2022 | 2021 |  |  |  | 67857 |  |  | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Pull in project approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:26 | Reyes, Christina R | J1E1 | 2021-03-31 16:48 | Eagar, Josh
65619 | Pull-in Project from Future Year | 35226866 | 120449230 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Program Manager Review | 08W | [6 empty] | OH; base map n/a; 2021 possible execution | 2022-11-20 | 2021-11-20 | 0 | 67857 | 2021 | 2022 | 2021 |  |  |  | 67857 |  |  | 2021-12-31 | UNSE |  |  | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Pull in project approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:25 | Reyes, Christina R | J1E1 | 2021-03-31 16:47 | Eagar, Josh
65616 | Pull-in Project from Future Year | 35226865 | 120449208 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Program Manager Review | 08W | [6 empty] | OH; base map n/a; 2021 possible execution | 2022-11-01 | 2021-11-20 | 0 | 67857 | 2021 | 2022 | 2021 |  |  |  | 67857 |  |  | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Pull in project approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:25 | Reyes, Christina R | J1E1 | 2021-03-31 16:46 | Eagar, Josh
65615 | Pull-in Project from Future Year | 35226864 | 120449207 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Program Manager Review | 08W | [6 empty] | OH; base map n/a; 2021 possible execution | 2022-11-01 | 2021-11-20 | 0 | 67857 | 2021 | 2022 | 2021 |  |  |  | 67857 |  |  | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Pull in project approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:26 | Reyes, Christina R | J1E1 | 2021-03-31 16:45 | Eagar, Josh
65617 | Pull-in Project from Future Year | 35226863 | 120449205 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Program Manager Review | 08W | [6 empty] | OH; base map n/a; 2021 possible execution | 2022-11-01 | 2021-11-20 | 0 | 67857 | 2021 | 2022 | 2021 |  |  |  | 67857 |  |  | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Pull in project approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:25 | Reyes, Christina R | J1E1 | 2021-03-31 16:43 | Eagar, Josh
65568 | Add project | 35161152 | 118677953 | OCT2019 BRICEBURG FIRE REBUILD | Program Manager Review | 08W | [6 empty] | Fire Hardening 08W Remote Grid project | 2021-04-05 |  |  |  | 2021 | [5 empty] | 1200000 |  |  |  | UNSC |  |  | SGBA | Barrow, Steve | [9 empty] | Merih Tekeste | [8 empty] | SGBA | 2021-03-31 16:19 | Barrow, Steve
65567 | Add project | 31361965 |  | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Program Manager Review | 08W | [6 empty] | Construction & Program Mgmt requested to add to 2021 work plan | 2021-05-15 |  |  |  | 2021 | [5 empty] | 1245293 |  |  |  | CONS |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | [8 empty] | J1E1 | 2021-03-31 15:26 | Eagar, Josh
65566 | Add project | 31334291 |  | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Program Manager Review | 08W | [6 empty] | Construction & Program Mgmt requested to add to 2021 work plan | 2021-11-20 |  |  |  | 2021 | [5 empty] | 1115282 |  |  |  | PEND |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | [8 empty] | J1E1 | 2021-03-31 15:26 | Eagar, Josh
65546 | Budget change | 35233959 | 120564052 | CWSP - OREGON TRAIL 110335002 PH2.6 | Approved | 08W | [6 empty] | Requesting 2021 Budget for this job using avarage cost $1.9M per mile | 2021-08-27 |  | 0 | 75000 | 2021 |  |  |  | 665000 | 0 | 665000 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-08-27 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-04-01 12:38 | Mueller, Bret Charles | ZXAC | 2021-03-31 11:46 | Al-Saffar, Zaid Dhafer Hashim
65545 | Budget change | 35233952 | 120563958 | CWSP - OREGON TRAIL 110335002 PH2.2 | Approved | 08W | [6 empty] | Requesting 2021 Budget for this job using avarage cost $1.9M per mile | 2021-09-09 |  | 0 | 100000 | 2021 |  |  |  | 4104000 | 0 | 4104000 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-09-09 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-04-01 12:38 | Mueller, Bret Charles | ZXAC | 2021-03-31 11:45 | Al-Saffar, Zaid Dhafer Hashim
65544 | Budget change | 35234382 | 120564057 | CWSP - OREGON TRAIL 110335002 PH2.8 | Approved | 08W | [6 empty] | Requesting 2021 Budget for this job using avarage cost $1.9M per mile | 2021-08-13 |  | 0 | 100000 | 2021 |  |  |  | 3021000 | 0 | 3021000 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-08-13 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-04-01 12:38 | Mueller, Bret Charles | ZXAC | 2021-03-31 11:45 | Al-Saffar, Zaid Dhafer Hashim
65543 | Budget change | 35234381 | 120564055 | CWSP - OREGON TRAIL 110335002 PH2.7 | Approved | 08W | [6 empty] | Requesting 2021 Budget for this job using avarage cost $1.9M per mile | 2021-08-16 |  | 0 | 100000 | 2021 |  |  |  | 2945000 | 0 | 2945000 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-08-16 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-04-01 12:38 | Mueller, Bret Charles | ZXAC | 2021-03-31 11:45 | Al-Saffar, Zaid Dhafer Hashim
65542 | Budget change | 35225826 | 120426402 | CWSP - OREGON TRAIL 110335002 PH2.1 | Approved | 08W | [6 empty] | Requesting 2021 Budget for this job using avarage cost $1.9M per mile | 2021-10-06 |  | 0 | 100000 | 2021 |  |  |  | 4825999.3 | 0 | 4825999.3 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-10-06 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-04-01 12:38 | Mueller, Bret Charles | ZXAC | 2021-03-31 11:44 | Al-Saffar, Zaid Dhafer Hashim
64319 | Defer project | 35217268 | 120047659 | CWSP - BUCKS CREEK 1101 CB PH 1 | Program Manager Review | 08W |  | 2022 |  | GC |  |  | the scope of this job is a span across a river. It will be exceuted with 2 UG projects ph2 and ph3 that planned to be in 2022 WP | 2021-09-22 | 2022-06-30 | 690.1 | 150000 | 2021 |  | 2022 |  | 380000 | 0 | 0 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-09-22 | T3SQ | Skarda, Travis Damian | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:24 | Reyes, Christina R | ZXAC | 2021-03-31 09:37 | Al-Saffar, Zaid Dhafer Hashim
64318 | Update work plan date | 35226900 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | Denied | 08W |  | N/A |  |  |  |  | Due to DSDD requirements on other project phases and GC completing all 5 phases. Then keeping this smaller 0.69 mile project is the same construction year would be best. |  | 2022-06-01 |  |  |  |  | 2022 | [7 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Job is on 2021 work plan, if you want to move to 2022 you need to submit a deferral request. | BCMK | 2021-04-01 13:00 | Mueller, Bret Charles | M5HF | 2021-03-31 08:23 | Hernandez, Michael Donald James
64317 | Update work plan date | 35226799 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | Denied | 08W |  | N/A |  |  |  |  | Due to DSDD requirements on other project phases and GC completing all 5 phases. Then keeping this smaller 0.19 mile project is the same construction year would be best. |  | 2022-06-01 |  |  |  |  | 2022 | [7 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Job is on 2021 work plan, if you want to move to 2022 you need to submit a deferral request. | BCMK | 2021-04-01 13:00 | Mueller, Bret Charles | M5HF | 2021-03-31 08:23 | Hernandez, Michael Donald James
64316 | Update work plan date | 35226798 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Denied | 08W |  | N/A |  |  |  |  | DSDD Required - Due to dependencies deferring project to 2022. |  | 2022-06-01 |  |  |  |  | 2022 | [7 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Job is on 2021 work plan, if you want to move to 2022 you need to submit a deferral request. | BCMK | 2021-04-01 13:01 | Mueller, Bret Charles | M5HF | 2021-03-31 08:23 | Hernandez, Michael Donald James
64168 | Add project | 35057018 |  | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Program Manager Review | 08W | [6 empty] | Adding this job to 2021 WP as part of SH Program | 2021-07-13 |  |  |  | 2021 | [9 empty] | PEND |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | [8 empty] | ZXAC | 2021-03-30 12:48 | Al-Saffar, Zaid Dhafer Hashim
64167 | Add project | 35109546 |  | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Program Manager Review | 08W | [6 empty] | Adding this job to 2022 WP as part of SH Program | 2022-06-22 |  |  |  | 2022 | [9 empty] | ESTS |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | [8 empty] | ZXAC | 2021-03-30 12:47 | Al-Saffar, Zaid Dhafer Hashim
64166 | Add project | 35109541 |  | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Program Manager Review | 08W | [6 empty] | Adding this job to 2022 WP as part of SH Program | 2022-07-01 |  |  |  | 2022 | [9 empty] | ESTS |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | [8 empty] | ZXAC | 2021-03-30 12:47 | Al-Saffar, Zaid Dhafer Hashim
64165 | Add project | 35056733 |  | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Program Manager Review | 08W | [6 empty] | Adding this job to 2022 WP as part of SH Program | 2022-03-30 |  |  |  | 2022 | [9 empty] | PEND |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | [8 empty] | ZXAC | 2021-03-30 12:47 | Al-Saffar, Zaid Dhafer Hashim
64164 | Add project | 35057010 |  | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Program Manager Review | 08W | [6 empty] | Adding this job to 2022 WP as part of SH Program | 2022-06-20 |  |  |  | 2022 | [9 empty] | ESTS |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | [8 empty] | ZXAC | 2021-03-30 12:46 | Al-Saffar, Zaid Dhafer Hashim
64129 | Defer project | 35145540 | 118259180 | PSPS - FROGTOWN 1702 - CB | Program Manager Review | 08W |  | 2022 |  | Contract |  |  | Push this project to 2022 due to DSDD issue | 2022-03-30 | 2022-03-16 | 4233.1 | 5959167 | 2021 |  | 2022 | 49246 | 4139274.6 | 0 | 500000 | 3639275 | 0 | 2020-09-30 | PEND |  | 2022-03-30 | T3SQ | Skarda, Travis Damian | [7 empty] | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:23 | Reyes, Christina R | ZXAC | 2021-03-30 11:47 | Al-Saffar, Zaid Dhafer Hashim
64071 | Budget change | 35227201 | 120457012 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Approved | 08W |  |  |  | GC |  |  | 08W Fire Hardening Project | 2021-02-02 |  | 791.2 | 512371.91 | 2021 |  |  |  | 2080934 |  | 2080934 |  |  | 2021-12-31 | CONS |  | 2021-02-02 | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-04-01 12:38 | Mueller, Bret Charles | B4HS | 2021-03-30 08:14 | Hayashi, Brandon
64050 | Add project | 35233996 |  | PSPS - PLACERVILLE 2106 MICROGRID PH 1.3 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:21 | Yuen, Aaron Ho
64051 | Add project | 35219289 |  | CWSP - OREGON TRAIL 110335002 PH1.1 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | A3CG | Christie, Adoni Andreas | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64052 | Add project | 35233947 |  | CWSP - OREGON TRAIL 110335002 PH1.2 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | A3CG | Christie, Adoni Andreas | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64053 | Add project | 35233948 |  | CWSP - OREGON TRAIL 110335002 PH1.3 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | A3CG | Christie, Adoni Andreas | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64054 | Add project | 35233949 |  | CWSP - OREGON TRAIL 110335002 PH1.4 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | A3CG | Christie, Adoni Andreas | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64055 | Add project | 35233950 |  | CWSP - OREGON TRAIL 110335002 PH1.5 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | A3CG | Christie, Adoni Andreas | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64056 | Add project | 35233951 |  | CWSP - OREGON TRAIL 110335002 PH1.6 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | A3CG | Christie, Adoni Andreas | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64057 | Add project | 35225828 |  | CWSP - OREGON TRAIL 110335002 PH4.1 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64058 | Add project | 35234387 |  | CWSP - OREGON TRAIL 110335002 PH4.2 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64059 | Add project | 35234388 |  | CWSP - OREGON TRAIL 110335002 PH4.3 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64060 | Add project | 35234389 |  | CWSP - OREGON TRAIL 110335002 PH4.4 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64061 | Add project | 35234390 |  | CWSP - OREGON TRAIL 110335002 PH4.5 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64062 | Add project | 35234391 |  | CWSP - OREGON TRAIL 110335002 PH4.6 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64063 | Add project | 35234392 |  | CWSP - OREGON TRAIL 110335002 PH4.7 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64064 | Add project | 35225829 |  | CWSP - OREGON TRAIL 110335002 PH5.1 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64065 | Add project | 35234393 |  | CWSP - OREGON TRAIL 110335002 PH5.2 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64066 | Add project | 35234394 |  | CWSP - OREGON TRAIL 110335002 PH5.3 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64067 | Add project | 35234395 |  | CWSP - OREGON TRAIL 110335002 PH5.4 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64068 | Add project | 35234396 |  | CWSP - OREGON TRAIL 110335002 PH5.5 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64069 | Add project | 35234397 |  | CWSP - OREGON TRAIL 110335002 PH5.6 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64030 | Add project | 35227870 |  | CWSP - VACAVILLE 11046542 - PH 2.2 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64031 | Add project | 35227656 |  | CWSP - VACAVILLE 11046542 - PH 2.3 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64032 | Add project | 35227657 |  | CWSP - VACAVILLE 11046542 - PH 2.4 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64033 | Add project | 35227658 |  | CWSP - VACAVILLE 11046542 - PH 2.5 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64034 | Add project | 35227659 |  | CWSP - VACAVILLE 11046542 - PH 2.6 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64035 | Add project | 35219099 |  | CWSP - HIGHLANDS 1102628 PH 1.1 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64036 | Add project | 35231620 |  | CWSP - HIGHLANDS 1102628 PH 1.2 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64037 | Add project | 35231621 |  | CWSP - HIGHLANDS 1102628 PH 1.3 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64038 | Add project | 35231622 |  | CWSP - HIGHLANDS 1102628 PH 1.4 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64039 | Add project | 35231623 |  | CWSP - HIGHLANDS 1102628 PH 1.5 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64040 | Add project | 35231624 |  | CWSP - HIGHLANDS 1102628 PH 1.6 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64041 | Add project | 35231625 |  | CWSP - HIGHLANDS 1102628 PH 1.7 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64042 | Add project | 35231626 |  | CWSP - HIGHLANDS 1102628 PH 1.8 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64043 | Add project | 35231627 |  | CWSP - HIGHLANDS 1102628 PH 1.9 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64044 | Add project | 35231628 |  | CWSP - HIGHLANDS 1102628 PH 1.10 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64045 | Add project | 35231629 |  | CWSP - HIGHLANDS 1102628 PH 1.11 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64046 | Add project | 35231630 |  | CWSP - HIGHLANDS 1102628 PH 1.12 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64047 | Add project | 35231631 |  | CWSP - HIGHLANDS 1102628 PH 1.13 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64048 | Add project | 35224377 |  | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64049 | Add project | 35233995 |  | PSPS - PLACERVILLE 2106 MICROGRID PH 1.2 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
64029 | Add project | 35224378 |  | CWSP - VACAVILLE 11046542 - PH 2.1 | Program Manager Review | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste | [8 empty] | AXYX | 2021-03-29 21:12 | Yuen, Aaron Ho
62697 | Defer project | 35227162 | 120456655 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileage forecasted for 2021;updating the project report year from 2021 to 2022 | 2021-12-27 | 2022-12-27 | 110.1 | 1 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-12-27 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:26 | Reyes, Christina R | A9R3 | 2021-03-29 10:48 | Ravikanti, Aamani
62696 | Defer project | 35227030 | 120449801 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileage forecasted for 2021;updating the project report year from 2021 to 2022 | 2021-08-17 | 2022-08-13 | 110.1 | 1 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-08-17 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:25 | Reyes, Christina R | A9R3 | 2021-03-29 10:48 | Ravikanti, Aamani
62698 | Defer project | 35227161 | 120456654 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileage forecasted for 2021;updating the project report year from 2021 to 2022 | 2021-12-27 | 2022-12-27 | 110.1 | 1 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-12-27 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:24 | Reyes, Christina R | A9R3 | 2021-03-29 10:48 | Ravikanti, Aamani
62693 | Defer project | 35227168 | 120456742 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2022-01-17 | 2022-01-17 | 110.1 | 1 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-17 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:25 | Reyes, Christina R | A9R3 | 2021-03-29 10:37 | Ravikanti, Aamani
62692 | Defer project | 35228186 | 120475322 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2021-11-24 | 2022-12-27 | 110.1 | 1 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-11-24 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:26 | Reyes, Christina R | A9R3 | 2021-03-29 10:37 | Ravikanti, Aamani
62689 | Defer project | 35217269 | 120048011 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2021-12-27 | 2022-12-27 | 110.1 | 1 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-12-27 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:24 | Reyes, Christina R | A9R3 | 2021-03-29 10:37 | Ravikanti, Aamani
62691 | Defer project | 35191319 | 119518398 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Program Manager Review | 08W |  |  |  | Contract |  |  | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2021-11-01 | 2022-09-28 | 80 | 312500 | 2021 |  | 2022 | [6 empty] | 2023-12-31 | UNSE |  | 2021-11-01 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:24 | Reyes, Christina R | A9R3 | 2021-03-29 10:37 | Ravikanti, Aamani
62687 | Defer project | 35226632 | 120445424 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2022-01-17 | 2022-01-17 | 130.1 | 475000 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-17 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:24 | Reyes, Christina R | A9R3 | 2021-03-29 10:37 | Ravikanti, Aamani
62688 | Defer project | 35223615 | 120401360 | ECOP - LAS GALLINAS A 1105 PH 2 | Program Manager Review | 08W |  |  |  | Contract |  |  | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2021-12-13 | 2022-11-09 | 83 | 312500 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-12-13 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:26 | Reyes, Christina R | A9R3 | 2021-03-29 10:37 | Ravikanti, Aamani
62694 | Defer project | 35225589 | 120423768 | CWSP - KONOCTI 1102 LR 965078 PH2 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2021-10-20 | 2022-11-22 | 131.1 | 316666 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-10-20 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:27 | Reyes, Christina R | A9R3 | 2021-03-29 10:37 | Ravikanti, Aamani
62695 | Defer project | 35220895 | 120221891 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2021-08-17 | 2022-08-13 | 111.1 | 1 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-08-17 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:24 | Reyes, Christina R | A9R3 | 2021-03-29 10:37 | Ravikanti, Aamani
62690 | Defer project | 35217270 | 120048013 | CWSP - KONOCTI 1102 LR 965078 PH1 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2021-11-17 | 2022-12-20 | 130.1 | 316666 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-11-17 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:15 | Reyes, Christina R | A9R3 | 2021-03-29 10:37 | Ravikanti, Aamani
62686 | Defer project | 35217273 | 120048019 | SH - UPPER LAKE 1101 CB | Program Manager Review | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2021-12-16 | 2022-11-22 | 80 | 500000 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-12-16 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:27 | Reyes, Christina R | A9R3 | 2021-03-29 10:37 | Ravikanti, Aamani
62685 | Defer project | 35227165 | 120456740 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2022-01-17 | 2022-01-17 | 110.1 | 1 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-17 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:25 | Reyes, Christina R | A9R3 | 2021-03-29 10:36 | Ravikanti, Aamani
62682 | Defer project | 35227163 | 120456657 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileaage forecasted for 2022;updating the project report year from 2021 to 2022 | 2021-12-27 | 2022-12-27 | 110.1 | 1 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-12-27 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:25 | Reyes, Christina R | A9R3 | 2021-03-29 10:14 | Ravikanti, Aamani
62677 | Defer project | 35227164 | 120456658 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileaage forecasted for 2022;updating the project report year from 2021 to 2022 | 2021-12-27 | 2022-12-27 | 110.1 | 1 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-12-27 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:27 | Reyes, Christina R | A9R3 | 2021-03-29 10:14 | Ravikanti, Aamani
62681 | Defer project | 35227031 | 120449802 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileaage forecasted for 2022;updating the project report year from 2021 to 2022 | 2021-08-17 | 2022-08-13 | 110.1 | 1 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-08-17 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:24 | Reyes, Christina R | A9R3 | 2021-03-29 10:14 | Ravikanti, Aamani
62680 | Defer project | 35226819 | 120456652 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileaage forecasted for 2022;updating the project report year from 2021 to 2022 | 2021-12-27 | 2022-12-27 | 110.1 | 1 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-12-27 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:24 | Reyes, Christina R | A9R3 | 2021-03-29 10:14 | Ravikanti, Aamani
62678 | Defer project | 35227160 | 120456653 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileaage forecasted for 2022;updating the project report year from 2021 to 2022 | 2022-01-17 | 2022-01-17 | 110.1 | 1 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-17 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:25 | Reyes, Christina R | A9R3 | 2021-03-29 10:14 | Ravikanti, Aamani
62684 | Defer project | 35227167 | 120456741 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileaage forecasted for 2022;updating the project report year from 2021 to 2022 | 2022-01-17 | 2022-01-17 | 110.1 | 1 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-17 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:27 | Reyes, Christina R | A9R3 | 2021-03-29 10:14 | Ravikanti, Aamani
62679 | Defer project | 35217271 | 120048017 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileaage forecasted for 2022;updating the project report year from 2021 to 2022 | 2021-11-24 | 2022-12-27 | 110.1 | 1 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-11-24 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:25 | Reyes, Christina R | A9R3 | 2021-03-29 10:14 | Ravikanti, Aamani
62683 | Defer project | 35192282 | 119556300 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileaage forecasted for 2022;updating the project report year from 2021 to 2022 | 2021-08-18 | 2022-09-14 | 110.1 | 950000 | 2021 |  | 2022 | [6 empty] | 2023-12-31 | UNSE |  | 2021-08-18 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:22 | Reyes, Christina R | A9R3 | 2021-03-29 10:14 | Ravikanti, Aamani
62676 | Defer project | 35225591 | 120423769 | CWSP - KONOCTI 1102 LR 965078 PH3 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileaage forecasted for 2022;updating the project report year from 2021 to 2022 | 2021-07-28 | 2022-07-23 | 131.1 | 316666 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-07-28 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:25 | Reyes, Christina R | A9R3 | 2021-03-29 10:12 | Ravikanti, Aamani
62675 | Defer project | 35226621 | 120445224 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Program Manager Review | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022;updating the project report year from 2021 to 2022 | 2021-12-15 | 2022-01-17 | 111.1 | 1 | 2021 |  | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-12-15 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | [5 empty] | CRV4 | 2021-04-01 11:27 | Reyes, Christina R | A9R3 | 2021-03-29 09:50 | Ravikanti, Aamani
61317 | Add project | 35239522 |  | FRRB - WYANDOTTE 1103 - W2 PH2.9 | Approved | 08W | [6 empty] | addin this project to 2021 WP as part of NCFR program | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-04-01 11:26 | Mueller, Bret Charles | ZXAC | 2021-03-26 09:30 | Al-Saffar, Zaid Dhafer Hashim
61318 | Add project | 35239523 |  | FRRB - WYANDOTTE 1103 - W2 PH2.10 | Approved | 08W | [6 empty] | addin this project to 2021 WP as part of NCFR program | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-04-01 11:26 | Mueller, Bret Charles | ZXAC | 2021-03-26 09:30 | Al-Saffar, Zaid Dhafer Hashim
61308 | Resource change | 35026643 | 114258488 | DIAMOND SPRINGS 1105 - LR 2102 | Approved | 08W |  |  |  | Contract | N/A | Contract | 3.26 Resource Update to Contract p/Joe Cntrct Q2 work | 2022-07-26 |  | 35.1 | 100000 | 2021 |  |  | 10430.5 | [5 empty] | 2020-12-31 | ESTS |  | 2022-07-26 | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-26 10:59 | Mueller, Bret Charles | JUPX | 2021-03-26 08:52 | Pereyda, Jessica Ann Hiroko
61309 | Resource change | 35226845 | 120448987 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Approved | 08W |  |  |  | Contract | N/A | Contract | 3.26 Resource Update to Contract p/Joe Cntrct Q2 work | 2021-08-18 |  | 80 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-08-18 | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-26 10:59 | Mueller, Bret Charles | JUPX | 2021-03-26 08:51 | Pereyda, Jessica Ann Hiroko
61310 | Resource change | 35192290 | 119556075 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Approved | 08W |  |  |  | Contract | N/A | Contract | 3.26 Resource Update to Contract p/Joe Cntrct Q2 work | 2021-06-29 |  | 80 | 1 | 2021 | [8 empty] | 2023-12-31 | ESTS |  | 2021-06-29 | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-26 10:59 | Mueller, Bret Charles | JUPX | 2021-03-26 08:51 | Pereyda, Jessica Ann Hiroko
61311 | Resource change | 35192291 | 119556091 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Approved | 08W |  |  |  | Contract | N/A | Contract | 3.26 Resource Update to Contract p/Joe Cntrct Q2 work | 2022-03-02 |  | 80 | 1 | 2021 | 2022 | [7 empty] | 2023-12-31 | UNSE |  | 2022-03-02 | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-26 10:59 | Mueller, Bret Charles | JUPX | 2021-03-26 08:51 | Pereyda, Jessica Ann Hiroko
61287 | Update work plan date | 35226900 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | Denied | 08W | [6 empty] | GC to complete 6.5 miles in 3 other phases om this circuit, but they require DSDD. It makes a good business decision to complete the 0.69 miles when the 6.5 miles is completed. |  | 2022-12-31 | [12 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Needs to be Deferral request | BCMK | 2021-03-26 12:50 | Mueller, Bret Charles | M5HF | 2021-03-25 14:19 | Hernandez, Michael Donald James
61286 | Update work plan date | 35226799 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | Denied | 08W | [6 empty] | GC to complete 6.5 miles in 3 other phases om this circuit, but they require DSDD. It makes a good business decision to complete the 0.19 miles when the 6.5 miles is completed. |  | 2022-12-31 | [12 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Needs to be Deferral request | BCMK | 2021-03-26 12:50 | Mueller, Bret Charles | M5HF | 2021-03-25 14:19 | Hernandez, Michael Donald James
60788 | Update work plan date | 35226798 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Denied | 08W | [6 empty] | Push to 2022 due to dependencies clearing. |  | 2022-12-31 | [12 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Needs to be Deferral request | BCMK | 2021-03-26 12:50 | Mueller, Bret Charles | M5HF | 2021-03-25 10:41 | Hernandez, Michael Donald James
60779 | Add project | 35235676 |  | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-08-31 |  |  |  | 2021 | 2021 |  |  |  |  | 8400000 |  |  |  | UNSE |  |  | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | ZXAC | 2021-03-25 08:47 | Al-Saffar, Zaid Dhafer Hashim
60778 | Add project | 35235139 |  | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-08-31 |  |  |  | 2021 | 2021 |  |  |  |  | 4620000 |  |  |  | UNSE |  |  | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | ZXAC | 2021-03-25 08:47 | Al-Saffar, Zaid Dhafer Hashim
60605 | Resource change | 35232298 | 120532441 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Approved | 08W |  |  |  | GC | N/A | GC | 3.24 Resource Update to GC per Joe email | 2021-04-28 |  | 30.1 | 3159481 | 2021 |  |  |  | 845833.33 |  |  |  |  | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-26 10:57 | Mueller, Bret Charles | JUPX | 2021-03-24 18:52 | Pereyda, Jessica Ann Hiroko
60501 | Update work plan date | 35226798 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Denied | 08W |  | N/A |  |  |  |  | Due to the current status of this SH project and all the dependencies needed to be completed will need to be in 2022. |  | 2022-09-30 |  |  |  |  | 2022 | [7 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Needs to be Deferral request | BCMK | 2021-03-26 12:50 | Mueller, Bret Charles | M5HF | 2021-03-24 15:34 | Hernandez, Michael Donald James
60500 | Budget change | 35115157 | 117492085 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.4 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Adjusting budget to allign with 2021 EAC | 2020-02-18 |  | 2628.1 | 1580553.38 | 2020 |  |  | 3443012.7 | 34847 |  | 34847 |  |  | 2020-12-31 | FICL | 2020-09-30 | 2020-02-18 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-26 12:22 | Mueller, Bret Charles | M4JQ | 2021-03-24 15:32 | James, Matthew
60499 | Budget change | 35115156 | 117491998 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Adjusting budget to allign with 2021 EAC | 2020-04-01 |  | 1825.3 | 1357699.57 | 2020 |  |  | 5490339.7 | 37751 |  | 37751 |  |  | 2020-12-31 | FICL | 2020-07-03 | 2020-04-01 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-26 12:22 | Mueller, Bret Charles | M4JQ | 2021-03-24 15:32 | James, Matthew
60498 | Budget change | 35115155 | 117491298 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Adjusting budget to allign with 2021 EAC | 2020-01-13 |  | 2123.7 | 5231108 | 2020 | 2021 |  | 2946774.1 | 88800 |  | 88800 |  |  | 2020-12-31 | DOCC | 2021-02-25 | 2020-01-13 | J6KF | Kringler, Jeff L | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-26 12:22 | Mueller, Bret Charles | M4JQ | 2021-03-24 15:32 | James, Matthew
60497 | Budget change | 35115150 | 117496277 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Adjusting budget to allign with 2021 EAC | 2020-07-08 |  | 2266.9 | 4212019 | 2020 |  |  | 2197037.6 | 37621 |  | 37621 |  |  | 2020-12-31 | PREC |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-26 12:22 | Mueller, Bret Charles | M4JQ | 2021-03-24 15:32 | James, Matthew
60496 | Budget change | 35115148 | 117496270 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Adjusting budget to allign with 2021 EAC | 2020-06-02 |  | 3236.8 | 5062019 | 2020 | 2021 |  | 4762461.3 | 59744 |  | 59744 |  |  | 2020-12-31 | FICL | 2020-11-20 | 2020-06-02 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-26 12:22 | Mueller, Bret Charles | M4JQ | 2021-03-24 15:31 | James, Matthew
60495 | Budget change | 35115147 | 117496196 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.2 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Adjusting budget to allign with 2021 EAC | 2020-05-05 |  | 1223.8 | 5398830 | 2020 |  |  | 2808776.3 | 34829 |  | 34829 |  |  | 2020-12-31 | FICL | 2020-08-13 | 2020-05-05 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-26 12:22 | Mueller, Bret Charles | M4JQ | 2021-03-24 15:31 | James, Matthew
60494 | Budget change | 35098621 | 117177530 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Adjusting budget to allign with 2021 EAC | 2020-06-01 |  | 2558.5 | 2927538 | 2020 | 2021 |  | 1520689.3 | 131088 |  | 131088 |  |  | 2020-11-30 | DOCC | 2020-12-03 | 2020-06-01 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-26 12:22 | Mueller, Bret Charles | M4JQ | 2021-03-24 15:31 | James, Matthew
60493 | Budget change | 35061213 | 115106582 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Adjusting budget to allign with 2021 EAC | 2020-05-18 |  | 3375.3 | 6076529 | 2020 |  |  | 3590381.7 | 36100 |  | 36100 |  |  | 2020-12-31 | FICL | 2020-08-14 | 2020-05-18 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-26 12:22 | Mueller, Bret Charles | M4JQ | 2021-03-24 15:30 | James, Matthew
60490 | Add project | 35116440 |  | CWSP-MIWUK 1702-LR8090-PH 1.6 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-07-31 |  |  |  | 2022 | 2022 | [5 empty] | 3568368 |  |  | ESTS |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:39 | Mueller, Bret Charles | T1DA | 2021-03-24 14:26 | Daugherty, Tracy
60489 | Add project | 35116385 |  | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Approved | 08W | [6 empty] | Adding project back into work plan as 2021 per WFGC Committee approval | 2022-08-31 |  |  |  | 2021 | 2022 | [5 empty] | 1530167 |  |  | PEND |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste | Approved | Revised to 2021 dates per latest information after change request was initially submitted |  | Approved | 2022 per email from Fernando Armas | BCMK | 2021-03-30 17:17 | Mueller, Bret Charles | T1DA | 2021-03-24 14:22 | Daugherty, Tracy
60473 | Update work plan date | 35192291 | 119556091 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Denied | 08W |  |  |  | Contract |  |  | 08W Fire Hardening Project | 2022-03-02 | 2022-03-02 | 80 | 1 | 2021 | 2022 | 2022 |  |  |  | 300000 | 1364659 |  | 2023-12-31 | UNSE |  | 2022-03-02 | J1PE | Pantoja-Martinez, Jaime | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Job is on 2021 work plan, if you want to move to 2022 you need to submit a deferral request. | BCMK | 2021-04-01 13:00 | Mueller, Bret Charles | B4HS | 2021-03-24 11:58 | Hayashi, Brandon
60398 | Add project | 35233955 |  | CWSP - OREGON TRAIL 110335002 PH2.4 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2022 workplan. | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:40 | Mueller, Bret Charles | ZXAC | 2021-03-23 10:47 | Al-Saffar, Zaid Dhafer Hashim
60399 | Add project | 35233957 |  | CWSP - OREGON TRAIL 110335002 PH2.5 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2022 workplan. | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:40 | Mueller, Bret Charles | ZXAC | 2021-03-23 10:47 | Al-Saffar, Zaid Dhafer Hashim
60397 | Add project | 35233953 |  | CWSP - OREGON TRAIL 110335002 PH2.3 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2022 workplan. | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:40 | Mueller, Bret Charles | ZXAC | 2021-03-23 10:47 | Al-Saffar, Zaid Dhafer Hashim
60400 | Add project | 35233959 |  | CWSP - OREGON TRAIL 110335002 PH2.6 | Denied | 08W | [6 empty] | Adding this project as part of SH program | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Denied | Duplicate of Change ID 60027 |  | Denied |  | BCMK | 2021-03-26 10:34 | Mueller, Bret Charles | ZXAC | 2021-03-23 10:47 | Al-Saffar, Zaid Dhafer Hashim
60401 | Add project | 35234381 |  | CWSP - OREGON TRAIL 110335002 PH2.7 | Denied | 08W | [6 empty] | Adding this project as part of SH program | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Denied | Duplicate of Change ID 60028 |  | Denied |  | BCMK | 2021-03-26 10:34 | Mueller, Bret Charles | ZXAC | 2021-03-23 10:47 | Al-Saffar, Zaid Dhafer Hashim
60402 | Add project | 35234382 |  | CWSP - OREGON TRAIL 110335002 PH2.8 | Denied | 08W | [6 empty] | Adding this project as part of SH program | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Denied | Duplicate of Change ID 60029 |  | Denied |  | BCMK | 2021-03-26 10:34 | Mueller, Bret Charles | ZXAC | 2021-03-23 10:47 | Al-Saffar, Zaid Dhafer Hashim
60396 | Add project | 35233952 |  | CWSP - OREGON TRAIL 110335002 PH2.2 | Denied | 08W | [6 empty] | Adding this project as part of SH program | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Denied | Duplicate of Change ID 60023 |  | Denied |  | BCMK | 2021-03-26 10:34 | Mueller, Bret Charles | ZXAC | 2021-03-23 10:47 | Al-Saffar, Zaid Dhafer Hashim
60395 | Add project | 35225826 |  | CWSP - OREGON TRAIL 110335002 PH2.1 | Denied | 08W | [6 empty] | Adding this project as part of SH program | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Denied | Duplicate of Change ID 61305 |  | Denied |  | BCMK | 2021-03-26 10:34 | Mueller, Bret Charles | ZXAC | 2021-03-23 10:47 | Al-Saffar, Zaid Dhafer Hashim
61306 | Add project | 35225826 |  | CWSP - OREGON TRAIL 110335002 PH2.1 | Denied | 08W | [6 empty] | Adding this project as part of SH program | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Denied | Duplicate of Change ID 61305 |  | Denied |  | BCMK | 2021-03-26 10:34 | Mueller, Bret Charles | ZXAC | 2021-03-23 10:47 | Al-Saffar, Zaid Dhafer Hashim
60363 | Budget change | 35225823 | 120424672 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Approved | 08W |  |  |  | GC |  |  | Requesting Addational $35,581 for 2021 to align with expected case number in the approved BC | 2021-05-12 |  | 4018.3 | 6586891 | 2021 |  |  |  | 4901112 | 0 | 4901112 | 0 | 0 | 2021-12-31 | CONS |  | 2021-05-12 | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-26 12:21 | Mueller, Bret Charles | ZXAC | 2021-03-22 12:12 | Al-Saffar, Zaid Dhafer Hashim
60015 | Add project | 35223062 |  | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:46 | Yuen, Aaron Ho
60016 | Add project | 35223032 |  | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:46 | Yuen, Aaron Ho
60017 | Add project | 35219276 |  | CWSP - VACAVILLE 11046542 PH 1.1 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:46 | Yuen, Aaron Ho
60019 | Add project | 35227652 |  | CWSP - VACAVILLE 11046542 PH 1.3 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60020 | Add project | 35227653 |  | CWSP - VACAVILLE 11046542 PH 1.4 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60021 | Add project | 35227654 |  | CWSP - VACAVILLE 11046542 PH 1.5 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
61305 | Add project | 35225826 |  | CWSP - OREGON TRAIL 110335002 PH2.1 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60023 | Add project | 35233952 |  | CWSP - OREGON TRAIL 110335002 PH2.2 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60027 | Add project | 35233959 |  | CWSP - OREGON TRAIL 110335002 PH2.6 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60028 | Add project | 35234381 |  | CWSP - OREGON TRAIL 110335002 PH2.7 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60029 | Add project | 35234382 |  | CWSP - OREGON TRAIL 110335002 PH2.8 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60026 | Add project | 35233957 |  | CWSP - OREGON TRAIL 110335002 PH2.5 | Denied | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-12-31 |  |  |  |  | 2021 | [8 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Denied | Duplicate of Change ID 60399 |  | Denied |  | BCMK | 2021-03-26 10:34 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60024 | Add project | 35233953 |  | CWSP - OREGON TRAIL 110335002 PH2.3 | Denied | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-12-31 |  |  |  |  | 2021 | [8 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Denied | Duplicate of Change ID 60397 |  | Denied |  | BCMK | 2021-03-26 10:33 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60025 | Add project | 35233955 |  | CWSP - OREGON TRAIL 110335002 PH2.4 | Denied | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-12-31 |  |  |  |  | 2021 | [8 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Denied | Duplicate of Change ID 60398 |  | Denied |  | BCMK | 2021-03-26 10:34 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60022 | Add project | 35225826 |  | CWSP - OREGON TRAIL 110335002 PH2.1 | Denied | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-12-31 |  |  |  |  | 2021 | [8 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Denied | Duplicate of Change ID 61305 |  | Denied |  | BCMK | 2021-03-26 10:34 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60039 | Add project | 35236437 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.7 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60040 | Add project | 35236438 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.8 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60043 | Add project | 35236661 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60041 | Add project | 35236439 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60042 | Add project | 35236660 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60030 | Add project | 35225827 |  | CWSP - OREGON TRAIL 110335002 PH3.1 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | A3CG | Christie, Adoni Andreas | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60031 | Add project | 35233954 |  | CWSP - OREGON TRAIL 110335002 PH3.2 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | A3CG | Christie, Adoni Andreas | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60032 | Add project | 35233956 |  | CWSP - OREGON TRAIL 110335002 PH3.3 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | A3CG | Christie, Adoni Andreas | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60033 | Add project | 35233958 |  | CWSP - OREGON TRAIL 110335002 PH3.4 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | A3CG | Christie, Adoni Andreas | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60034 | Add project | 35234380 |  | CWSP - OREGON TRAIL 110335002 PH3.5 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | A3CG | Christie, Adoni Andreas | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60035 | Add project | 35234383 |  | CWSP - OREGON TRAIL 110335002 PH3.6 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | A3CG | Christie, Adoni Andreas | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60036 | Add project | 35234384 |  | CWSP - OREGON TRAIL 110335002 PH3.7 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | A3CG | Christie, Adoni Andreas | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60037 | Add project | 35234385 |  | CWSP - OREGON TRAIL 110335002 PH3.8 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | A3CG | Christie, Adoni Andreas | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60038 | Add project | 35234386 |  | CWSP - OREGON TRAIL 110335002 PH3.9 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | A3CG | Christie, Adoni Andreas | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60044 | Add project | 35219543 |  | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60018 | Add project | 35227651 |  | CWSP - VACAVILLE 11046542 PH 1.2 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:36 | Mueller, Bret Charles | AXYX | 2021-03-19 14:44 | Yuen, Aaron Ho
60014 | Add project | 74022385 | 114691436 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-03-21 |  | 9 | 3523187 | 2022 | 2022 |  | 3643552.6 | 3379.1 |  |  | 3523187 |  | 2020-11-30 | APPR |  | 2022-03-21 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:40 | Mueller, Bret Charles | D5A8 | 2021-03-19 13:52 | Arrow, Daniel
60013 | Add project | 35094396 | 117130859 | CWSP-KONOCTI 1102-LR 532 PH 9 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-05-09 |  | 2754.1 | 687082.4 | 2022 | 2022 |  | 11365.3 | 407602.1 |  |  | 687082.4 |  | 2020-11-30 | UNSC |  | 2022-05-09 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:40 | Mueller, Bret Charles | D5A8 | 2021-03-19 13:52 | Arrow, Daniel
60012 | Add project | 35094395 | 117130858 | CWSP-KONOCTI 1102-LR 532 PH 8 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-02-03 |  | 131 | 75000 | 2022 | 2022 |  | 3948.6 | 1163.8 |  |  | 75000 |  | 2020-11-30 | ESTS |  | 2022-02-03 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:40 | Mueller, Bret Charles | D5A8 | 2021-03-19 13:52 | Arrow, Daniel
60011 | Add project | 35094391 | 117130854 | CWSP-KONOCTI 1102-LR 532 PH 4 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-05-17 |  | 1696.6 | 470100.69 | 2022 | 2022 |  | 6426.8 | 604.8 |  |  | 470100.69 |  | 2020-11-30 | UNSC |  | 2022-05-17 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:40 | Mueller, Bret Charles | D5A8 | 2021-03-19 13:52 | Arrow, Daniel
60010 | Add project | 35094389 | 117130852 | CWSP-KONOCTI 1102-LR 532 PH 2 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-02-15 |  | 816 | 85000 | 2022 | 2022 |  | 997290.6 | 835.5 |  |  | 85000 |  | 2020-11-30 | ESTS |  | 2022-02-15 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:40 | Mueller, Bret Charles | D5A8 | 2021-03-19 13:52 | Arrow, Daniel
60009 | Add project | 35050951 | 114848376 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-02-01 |  | 2001.1 | 95000 | 2023 | 2023 |  | 1542801.8 |  |  |  |  | 95000 | 2019-12-31 | UNSE |  | 2022-02-01 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:40 | Mueller, Bret Charles | D5A8 | 2021-03-19 13:52 | Arrow, Daniel
60008 | Add project | 35050942 | 114848297 | CWSP: GARBERVILLE 1101 HENDRIX PILOT | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2023-12-31 |  | 3 | 95000 | 2023 | 2023 |  | 3133811.9 |  |  |  |  | 95000 | 2019-10-25 | UNSE |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:40 | Mueller, Bret Charles | D5A8 | 2021-03-19 13:52 | Arrow, Daniel
60007 | Add project | 35046211 | 114730956 | CWSP - GARBERVILLE 1102 HENDRIX PILOT | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2023-12-31 |  | 3 | 95000 | 2023 | 2023 |  | 1475029.2 |  |  |  |  | 95000 | 2019-10-25 | UNSE |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:40 | Mueller, Bret Charles | D5A8 | 2021-03-19 13:52 | Arrow, Daniel
60006 | Add project | 35043296 | 112191208 | WDDB - WILLOW CRK 1103 LR 3090 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-02-16 |  | 3255.1 | 776346.19 | 2022 | 2022 |  | 269830.7 |  |  |  | 776346 |  | 2018-10-10 | UNSC |  | 2022-02-16 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:40 | Mueller, Bret Charles | D5A8 | 2021-03-19 13:51 | Arrow, Daniel
60005 | Add project | 35234865 | 120581001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-11-01 |  | 0 |  | 2022 | 2022 | [5 empty] | 300000 |  | 2021-12-31 | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:39 | Mueller, Bret Charles | D5A8 | 2021-03-19 13:51 | Arrow, Daniel
60004 | Add project | 35234862 | 120580959 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-11-01 |  | 0 |  | 2022 | 2022 | [5 empty] | 300000 |  | 2021-12-31 | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:39 | Mueller, Bret Charles | D5A8 | 2021-03-19 13:51 | Arrow, Daniel
60003 | Add project | 35234758 | 120580957 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-11-01 |  | 0 |  | 2022 | 2022 | [5 empty] | 300000 |  | 2021-12-31 | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:39 | Mueller, Bret Charles | D5A8 | 2021-03-19 13:51 | Arrow, Daniel
60002 | Add project | 35234756 | 120580906 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-11-01 |  | 0 |  | 2022 | 2022 | [5 empty] | 300000 |  | 2021-12-31 | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:39 | Mueller, Bret Charles | D5A8 | 2021-03-19 13:51 | Arrow, Daniel
59951 | Budget change | 35219281 | 120142240 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Approved | 08W |  |  |  | GC |  |  | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 & 2022 workplan. | 2021-10-08 |  | 110.1 | 316666 | 2021 | 2022 |  |  | 251101 |  | 251101 | 7569490 |  | 2021-12-31 | UNSE |  | 2021-10-08 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | M4JQ | 2021-03-19 10:57 | James, Matthew
59959 | Budget change | 35223036 | 120242599 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 & 2022 workplan. | 2021-11-04 |  | 0 | 500000 | 2021 | 2022 |  |  | 110970 |  | 110970 | 201853 |  | 2021-12-31 | UNSE |  | 2021-11-04 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | M4JQ | 2021-03-19 10:56 | James, Matthew
59954 | Budget change | 35232651 | 120529255 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.3 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 workplan. | 2021-10-08 |  | 80 | 316667 | 2021 |  |  |  | 3458896 |  | 3458896 |  |  | 2021-12-31 | UNSE |  | 2021-10-08 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | M4JQ | 2021-03-19 10:53 | James, Matthew
59955 | Budget change | 35232650 | 120529254 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 & 2022 workplan. | 2021-09-29 |  | 80 | 316667 | 2021 | 2022 |  |  | 212265 |  | 212265 | 5177531 |  | 2021-12-31 | UNSE |  | 2021-09-29 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | M4JQ | 2021-03-19 10:52 | James, Matthew
59948 | Budget change | 35225824 | 120424703 | FRRB - WYANDOTTE 1103 - HWY 162 | Approved | 08W |  |  |  | GC |  |  | requesting additional $40,927 for 2021 MPP budget to allign with BC approval (Expected Case number) | 2021-04-05 |  | 1434.6 | 11016312 | 2021 |  |  |  | 8094904 | 0 | 8094904 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-04-05 | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | ZXAC | 2021-03-19 08:57 | Al-Saffar, Zaid Dhafer Hashim
59944 | Update work plan date | 35062375 | 115323921 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Approved | 08W |  |  |  | GC |  |  | Defer to 2022, 08W CWSP 100% UG project dependencies will not be completed until 2022. | 2022-01-04 | 2022-11-24 | 131.1 | 1 | 2021 | 2022 | 2022 | 58.9 |  |  | 200 |  |  | 2020-12-31 | UNSE |  | 2022-01-04 | R4BA | Barron, Raul Angelo | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | R4BA | 2021-03-19 07:54 | Barron, Raul Angelo
59945 | Update work plan date | 35192292 | 119556108 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Approved | 08W |  |  |  | GC |  |  | Defer to 2022, 08W ECOP 100% UG project dependencies will not be completed until 2022. | 2022-01-03 | 2022-11-24 | 50.1 | 950000 | 2021 | 2022 | 2022 |  |  |  | 200 |  |  | 2023-12-31 | ESTS |  | 2022-01-03 | R4BA | Barron, Raul Angelo | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | R4BA | 2021-03-19 07:54 | Barron, Raul Angelo
59946 | Update work plan date | 35226849 | 120449142 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Approved | 08W |  |  |  | GC |  |  | Defer to 2022, 08W CWSP 100% UG project dependencies will not be completed until 2022. | 2021-12-08 | 2022-11-24 | 130.1 | 1 | 2021 | 2022 | 2022 |  |  |  | 200 |  |  | 2021-12-31 | UNSE |  | 2021-12-08 | R4BA | Barron, Raul Angelo | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | R4BA | 2021-03-19 07:54 | Barron, Raul Angelo
59947 | Update work plan date | 35225594 | 120424183 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Approved | 08W |  |  |  | GC |  |  | Defer to 2022, 08W CWSP 100% UG project dependencies will not be completed until 2022. | 2022-01-03 | 2022-11-24 | 50.1 | 1 | 2021 | 2022 | 2022 |  |  |  | 200 |  |  | 2021-12-31 | ESTS |  | 2022-01-03 | R4BA | Barron, Raul Angelo | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | R4BA | 2021-03-19 07:54 | Barron, Raul Angelo
59939 | Update work plan date | 35227025 | 120449714 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Approved | 08W |  |  |  | GC |  |  | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 80 | 118750 | 2021 | 2022 | 2022 |  |  |  | 500000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | SFMT | Moraga, Steven | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:45 | Eagar, Josh
59935 | Update work plan date | 35227021 | 120449712 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Approved | 08W |  |  |  | GC |  |  | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 0 | 118750 | 2021 | 2022 | 2022 |  |  |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | SFMT | Moraga, Steven | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:44 | Eagar, Josh
59940 | Update work plan date | 35227018 | 120449711 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Approved | 08W |  |  |  | GC |  |  | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 80 | 118750 | 2021 | 2022 | 2022 |  |  |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | SFMT | Moraga, Steven | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:43 | Eagar, Josh
59923 | Update work plan date | 35227015 | 120449710 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Approved | 08W |  |  |  | GC |  |  | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 80 | 118750 | 2021 | 2022 | 2022 |  |  |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | SFMT | Moraga, Steven | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:42 | Eagar, Josh
59920 | Update work plan date | 35227013 | 120449539 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 | Approved | 08W |  |  |  | GC |  |  | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 80 |  | 2021 | 2022 | 2022 |  |  |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | SFMT | Moraga, Steven | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:41 | Eagar, Josh
59919 | Update work plan date | 35227010 | 120449536 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Approved | 08W |  |  |  | GC |  |  | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 80 | 118750 | 2021 | 2022 | 2022 |  |  |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | SFMT | Moraga, Steven | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:40 | Eagar, Josh
59932 | Update work plan date | 35227007 | 120449533 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Approved | 08W |  |  |  | GC |  |  | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 80 | 118750 | 2021 | 2022 | 2022 |  |  |  | 500000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | SFMT | Moraga, Steven | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:39 | Eagar, Josh
59930 | Update work plan date | 35227004 | 120449457 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2022-11-01 | 2022-11-20 | 0 | 67857 | 2021 | 2022 | 2022 |  |  |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:38 | Eagar, Josh
59928 | Update work plan date | 35227003 | 120449456 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2022-11-01 | 2022-11-20 | 0 | 67857 | 2021 | 2022 | 2022 |  |  |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:37 | Eagar, Josh
59931 | Update work plan date | 35227002 | 120449455 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2022-11-01 | 2022-11-20 | 0 | 67857 | 2021 | 2022 | 2022 |  |  |  | 200000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:36 | Eagar, Josh
59929 | Update work plan date | 35227001 | 120449454 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2022-11-01 | 2022-11-20 | 0 | 67857 | 2021 | 2022 | 2022 |  |  |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | J1E1 | Eagar, Josh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:35 | Eagar, Josh
59936 | Update work plan date | 35226878 | 120449453 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 0 | 67857 | 2021 | 2022 | 2022 |  |  |  | 500000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:34 | Eagar, Josh
59924 | Update work plan date | 35226873 | 120449450 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2022-11-01 | 2022-11-20 | 0 | 67857 | 2021 | 2022 | 2022 |  |  |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:33 | Eagar, Josh
59934 | Update work plan date | 35226870 | 120449231 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2022-11-01 | 2022-11-20 | 0 | 67857 | 2021 | 2022 | 2022 |  |  |  | 200000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:31 | Eagar, Josh
59926 | Update work plan date | 35226866 | 120449230 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2022-11-20 | 2022-11-20 | 0 | 67857 | 2021 | 2022 | 2022 |  |  |  | 200000 | 100000 |  | 2021-12-31 | UNSE |  |  | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:30 | Eagar, Josh
59925 | Update work plan date | 35226865 | 120449208 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2022-11-01 | 2022-11-20 | 0 | 67857 | 2021 | 2022 | 2022 |  |  |  | 200000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:30 | Eagar, Josh
59941 | Update work plan date | 35226864 | 120449207 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2022-11-01 | 2022-11-20 | 0 | 67857 | 2021 | 2022 | 2022 |  |  |  | 100000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:29 | Eagar, Josh
59942 | Update work plan date | 35226863 | 120449205 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2022-11-01 | 2022-11-20 | 0 | 67857 | 2021 | 2022 | 2022 |  |  |  | 100000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:28 | Eagar, Josh
59927 | Update work plan date | 35226862 | 120449204 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Approved | 08W |  |  |  | GC |  |  | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 80 | 155000 | 2021 | 2022 | 2022 |  |  |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:27 | Eagar, Josh
59922 | Update work plan date | 35226861 | 120449203 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Approved | 08W |  |  |  | GC |  |  | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 80 | 155000 | 2021 | 2022 | 2022 |  |  |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:26 | Eagar, Josh
59918 | Update work plan date | 35226859 | 120449202 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Approved | 08W |  |  |  | GC |  |  | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 80 | 155000 | 2021 | 2022 | 2022 |  |  |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:25 | Eagar, Josh
59933 | Update work plan date | 35226858 | 120449201 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Approved | 08W |  |  |  | GC |  |  | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 80 | 155000 | 2021 | 2022 | 2022 |  |  |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:24 | Eagar, Josh
59938 | Update work plan date | 35226857 | 120449200 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Approved | 08W |  |  |  | GC |  |  | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-16 | 2022-11-20 | 80 | 155000 | 2021 | 2022 | 2022 |  |  |  | 500000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-16 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:22 | Eagar, Josh
59915 | Update work plan date | 35174501 | 118913026 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Approved | 08W |  |  |  | GC |  |  | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 3 | 118750 | 2021 | 2022 | 2022 |  |  |  | 500000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | SFMT | Moraga, Steven | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:21 | Eagar, Josh
59917 | Update work plan date | 35174479 | 118913025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 3 | 67857 | 2021 | 2022 | 2022 |  |  |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:20 | Eagar, Josh
59916 | Update work plan date | 35174478 | 118913024 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Approved | 08W |  |  |  | GC |  |  | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 123 | 155000 | 2021 | 2022 | 2022 |  |  | 0 | 500000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | J1E1 | 2021-03-18 21:18 | Eagar, Josh
59913 | Add project | 35220896 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 10:40 | Mueller, Bret Charles | A9R3 | 2021-03-18 17:37 | Ravikanti, Aamani
59912 | Update work plan date | 35191319 | 119518398 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Denied | 08W |  |  |  | Contract |  |  | Mileage forecasted for FY 2022; updating project report year from FY2021 to FY2022 | 2021-11-01 | 2022-09-14 | 80 | 312500 | 2021 | [8 empty] | 2023-12-31 | UNSE |  | 2021-11-01 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. | BCMK | 2021-03-25 14:18 | Mueller, Bret Charles | A9R3 | 2021-03-18 17:02 | Ravikanti, Aamani
59902 | Update work plan date | 35227160 | 120456653 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2022-01-17 | 2022-09-09 | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2022-01-17 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. | BCMK | 2021-03-25 14:18 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:45 | Ravikanti, Aamani
59903 | Update work plan date | 35226819 | 120456652 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-12-27 | 2022-08-17 | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-12-27 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. | BCMK | 2021-03-25 14:18 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:45 | Ravikanti, Aamani
59904 | Update work plan date | 35227161 | 120456654 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-12-27 | 2022-08-17 | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-12-27 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. | BCMK | 2021-03-25 14:18 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:45 | Ravikanti, Aamani
59909 | Update work plan date | 35227162 | 120456655 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-12-27 | 2022-08-17 | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-12-27 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. | BCMK | 2021-03-25 14:18 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:45 | Ravikanti, Aamani
59906 | Update work plan date | 35227164 | 120456658 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-12-27 | 2022-08-17 | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-12-27 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. | BCMK | 2021-03-25 14:18 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:44 | Ravikanti, Aamani
59911 | Update work plan date | 35227163 | 120456657 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-12-27 | 2022-08-17 | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-12-27 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. | BCMK | 2021-03-25 14:18 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:44 | Ravikanti, Aamani
59910 | Update work plan date | 35227165 | 120456740 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2022-01-17 |  | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2022-01-17 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Looks like should be Deferral request. Also needs Update Work Plan Date and Updated Construction Complete Date | BCMK | 2021-03-25 14:22 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:43 | Ravikanti, Aamani
59908 | Update work plan date | 35227168 | 120456742 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2022-01-17 |  | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2022-01-17 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Looks like should be Deferral request. Also needs Update Work Plan Date and Updated Construction Complete Date | BCMK | 2021-03-25 14:22 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:42 | Ravikanti, Aamani
59907 | Update work plan date | 35227030 | 120449801 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-08-17 |  | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-08-17 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Looks like should be Deferral request. Also needs Update Work Plan Date and Updated Construction Complete Date | BCMK | 2021-03-25 14:22 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:42 | Ravikanti, Aamani
59905 | Update work plan date | 35227167 | 120456741 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2022-01-17 |  | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2022-01-17 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Looks like should be Deferral request. Also needs Update Work Plan Date and Updated Construction Complete Date | BCMK | 2021-03-25 14:22 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:42 | Ravikanti, Aamani
59900 | Update work plan date | 35227031 | 120449802 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-08-17 |  | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-08-17 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Looks like should be Deferral request. Also needs Update Work Plan Date and Updated Construction Complete Date | BCMK | 2021-03-25 14:22 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:42 | Ravikanti, Aamani
59899 | Update work plan date | 35226632 | 120445424 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2022-01-17 |  | 130.1 | 475000 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2022-01-17 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Looks like should be Deferral request. Also needs Update Work Plan Date and Updated Construction Complete Date | BCMK | 2021-03-25 14:22 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:42 | Ravikanti, Aamani
59901 | Update work plan date | 35226621 | 120445224 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-12-15 |  | 111.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-12-15 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Looks like should be Deferral request. Also needs Update Work Plan Date and Updated Construction Complete Date | BCMK | 2021-03-25 14:22 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:42 | Ravikanti, Aamani
59898 | Update work plan date | 35217271 | 120048017 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-11-24 |  | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-11-24 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Looks like should be Deferral request. Also needs Update Work Plan Date and Updated Construction Complete Date | BCMK | 2021-03-25 14:22 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:42 | Ravikanti, Aamani
59897 | Update work plan date | 35217273 | 120048019 | SH - UPPER LAKE 1101 CB | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-12-16 | 2022-11-15 | 80 | 500000 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-12-16 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. | BCMK | 2021-03-25 14:18 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:42 | Ravikanti, Aamani
59896 | Update work plan date | 35225591 | 120423769 | CWSP - KONOCTI 1102 LR 965078 PH3 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-07-28 | 2022-07-27 | 131.1 | 316666 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-07-28 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. | BCMK | 2021-03-25 14:18 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:41 | Ravikanti, Aamani
59895 | Update work plan date | 35217270 | 120048013 | CWSP - KONOCTI 1102 LR 965078 PH1 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-11-17 | 2022-08-10 | 130.1 | 316666 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-11-17 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. | BCMK | 2021-03-25 14:18 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:41 | Ravikanti, Aamani
59894 | Update work plan date | 35225589 | 120423768 | CWSP - KONOCTI 1102 LR 965078 PH2 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-10-20 | 2022-07-27 | 131.1 | 316666 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-10-20 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. | BCMK | 2021-03-25 14:18 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:41 | Ravikanti, Aamani
59893 | Update work plan date | 35217269 | 120048011 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-12-27 | 2022-08-17 | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-12-27 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. | BCMK | 2021-03-25 14:18 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:41 | Ravikanti, Aamani
59892 | Update work plan date | 35228186 | 120475322 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-11-24 | 2022-07-07 | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-11-24 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. | BCMK | 2021-03-25 14:18 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:31 | Ravikanti, Aamani
59891 | Update work plan date | 35223615 | 120401360 | ECOP - LAS GALLINAS A 1105 PH 2 | Denied | 08W |  |  |  | Contract |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-12-13 | 2022-09-14 | 83 | 312500 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-12-13 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. | BCMK | 2021-03-25 14:18 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:30 | Ravikanti, Aamani
59890 | Update work plan date | 35220895 | 120221891 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-08-17 | 2022-07-07 | 111.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-08-17 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. | BCMK | 2021-03-25 14:18 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:29 | Ravikanti, Aamani
59889 | Update work plan date | 35192282 | 119556300 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Denied | 08W |  |  |  | GC |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-08-18 | 2022-07-07 | 110.1 | 950000 | 2021 | [8 empty] | 2023-12-31 | UNSE |  | 2021-08-18 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. | BCMK | 2021-03-25 14:18 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:28 | Ravikanti, Aamani
59888 | Update work plan date | 35191319 | 119518398 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Denied | 08W |  |  |  | Contract |  |  | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-11-01 | 2022-09-14 | 80 | 312500 | 2021 | [8 empty] | 2023-12-31 | UNSE |  | 2021-11-01 | P3D5 | Donovan, Patrick | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. | BCMK | 2021-03-25 14:18 | Mueller, Bret Charles | A9R3 | 2021-03-18 16:27 | Ravikanti, Aamani
59836 | Resource change | 35233307 | 120541538 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-04-28 |  | 30.1 | 4778094 | 2021 |  |  |  | 2090056.82 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59837 | Resource change | 35233308 | 120541539 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-04-28 |  | 30.1 | 6280110 | 2021 |  |  |  | 1761818.18 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59835 | Resource change | 35233306 | 120541535 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-04-28 |  | 30.1 | 3246777 | 2021 |  |  |  | 500000 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59838 | Resource change | 35233309 | 120541630 | FRRB - WYANDOTTE 1103 - W1 PH1.13 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-04-28 |  | 30.1 | 3728491 | 2021 |  |  |  | 1282670.45 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59850 | Resource change | 35233314 | 120541635 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 5600000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59851 | Resource change | 35233315 | 120541636 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 3360000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59848 | Resource change | 35233311 | 120541633 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 4375000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59849 | Resource change | 35233312 | 120541634 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 3850000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59839 | Resource change | 35233310 | 120541632 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-04-28 |  | 30.1 | 2743520 | 2021 |  |  |  | 500000 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59845 | Resource change | 35233303 | 120542505 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-04-28 |  | 30.1 | 2470520 | 2021 |  |  |  | 500000 |  |  |  |  | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59846 | Resource change | 35233304 | 120542506 | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-04-28 |  | 30.1 | 3444978 | 2021 |  |  |  | 1064583.33 |  |  |  |  | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59841 | Resource change | 35233039 | 120542500 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-04-28 |  | 30.1 | 3729353 | 2021 |  |  |  | 1283333.33 |  |  |  |  | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59843 | Resource change | 35233301 | 120542503 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-04-28 |  | 30.1 | 3715565 | 2021 |  |  |  | 1272727.27 |  |  |  |  | 2022-01-01 | UNSE |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59844 | Resource change | 35233302 | 120542504 | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-04-21 |  | 0.6 | 147014.36 | 2021 |  |  |  | 500000 |  |  |  |  | 2022-01-01 | ESTS |  | 2021-04-21 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59842 | Resource change | 35233300 | 120542502 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-04-28 |  | 30.1 | 3535462 | 2021 |  |  |  | 1134185.61 |  |  |  |  | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59840 | Resource change | 35233038 | 120542278 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-04-28 |  | 30.1 | 3118378 | 2021 |  |  |  | 813352.27 |  |  |  |  | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59847 | Resource change | 35233305 | 120542507 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-04-28 |  | 30.1 | 3378623 | 2021 |  |  |  | 1013541.67 |  |  |  |  | 2022-01-01 | UNSE |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59852 | Resource change | 35235705 | 120594567 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 4620000 |  |  |  |  | 2022-03-03 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59853 | Resource change | 35235706 | 120594568 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 4060000 |  |  |  |  | 2022-03-03 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59854 | Resource change | 35235707 | 120594569 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Approved | 08W |  |  |  | GC | N/A | GC | 3.18 Resource Update to GC | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 3325000 |  |  |  |  | 2022-03-03 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59856 | Resource change | 35026643 | 114258488 | DIAMOND SPRINGS 1105 - LR 2102 | Denied | 08W |  |  |  | Contract | N/A | GC | 3.18 Resource Update to GC | 2022-07-26 |  | 35.1 | 100000 | 2021 |  |  | 10430.5 | [5 empty] | 2020-12-31 | ESTS |  | 2022-07-26 | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Denied | Requested resource matches the current resource on the work plan | SFSS | 2021-03-19 20:02 | Saraf, Shubham | JUPX | 2021-03-18 11:18 | Pereyda, Jessica Ann Hiroko
59798 | Resource change | 35227032 | 120449806 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Denied | 08W |  |  |  | Contract | N/A | Contract | 3.18 Resource Update to Contract | 2022-02-04 |  | 80 | 237833 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2022-02-04 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Denied | Requested resource matches the current resource on the work plan | SFSS | 2021-03-19 20:02 | Saraf, Shubham | JUPX | 2021-03-18 10:50 | Pereyda, Jessica Ann Hiroko
59799 | Resource change | 35227033 | 120449807 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Denied | 08W |  |  |  | Contract | N/A | Contract | 3.18 Resource Update to Contract | 2022-02-04 |  | 80 | 237833 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2022-02-04 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Denied | Requested resource matches the current resource on the work plan | SFSS | 2021-03-19 20:02 | Saraf, Shubham | JUPX | 2021-03-18 10:50 | Pereyda, Jessica Ann Hiroko
59797 | Resource change | 35191937 | 119553837 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Denied | 08W |  |  |  | Contract | N/A | Contract | 3.18 Resource Update to Contract |  |  | 0 | 237833 | 2021 | [8 empty] | 2022-12-31 | ESTS |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Denied | Requested resource matches the current resource on the work plan | SFSS | 2021-03-19 20:02 | Saraf, Shubham | JUPX | 2021-03-18 10:50 | Pereyda, Jessica Ann Hiroko
59582 | Resource change | 35094513 | 114567769 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Approved | 08W |  |  |  | Contract | GC Gas | Contract | Resource Change - GC Gas confirmed has the civil portion | 2021-12-30 |  | 1781.5 | 3142865.56 | 2021 |  |  | 48176.5 | 4178901 |  |  |  |  | 2021-12-20 | PEND |  | 2021-12-30 | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-17 15:57 | Mueller, Bret Charles | M117 | 2021-03-17 15:21 | Munkhbaatar, Munkhjin
59576 | Update work plan date | 35223030 | 120242544 | PSPS - BANGOR 1101 CB - MICROGRID | Approved | 08W |  | 2022 |  |  |  |  | Per project Manager, This will be a 2022 project due to the underground scope | 2021-09-21 | 2022-12-31 | 80 | 950000 | 2021 | 2022 | 2022 |  |  | 0 | 500000 | 1495000 | 0 | 2021-12-31 | UNSE |  | 2021-09-21 | T3SQ | Skarda, Travis Damian | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | ZXAC | 2021-03-17 10:21 | Al-Saffar, Zaid Dhafer Hashim
59569 | Add project | 35237890 |  | FRRB - WYANDOTTE 1103 - W3 PH3.3 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-12-31 |  |  |  |  | 2021 |  |  |  | 0 | 2835000 | 0 | 0 |  | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | ZXAC | 2021-03-17 09:45 | Al-Saffar, Zaid Dhafer Hashim
59568 | Add project | 35237889 |  | FRRB - WYANDOTTE 1103 - W3 PH3.2 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-12-31 |  |  |  |  | 2021 |  |  |  | 0 | 4795000 | 0 | 0 |  | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | ZXAC | 2021-03-17 09:45 | Al-Saffar, Zaid Dhafer Hashim
59567 | Add project | 35235320 |  | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-12-31 |  |  |  |  | 2021 |  |  |  | 0 | 3500000 | 0 | 0 |  | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | ZXAC | 2021-03-17 09:45 | Al-Saffar, Zaid Dhafer Hashim
59575 | Add project | 35236990 |  | FRRB - WYANDOTTE 1103 - W3 PH3.9 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-12-31 |  |  |  |  | 2021 |  |  |  | 0 | 2730000 | 0 | 0 |  | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | ZXAC | 2021-03-17 09:45 | Al-Saffar, Zaid Dhafer Hashim
59574 | Add project | 35237896 |  | FRRB - WYANDOTTE 1103 - W3 PH3.8 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-12-31 |  |  |  |  | 2021 |  |  |  | 0 | 3885000 | 0 | 0 |  | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | ZXAC | 2021-03-17 09:45 | Al-Saffar, Zaid Dhafer Hashim
59573 | Add project | 35237895 |  | FRRB - WYANDOTTE 1103 - W3 PH3.7 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-12-31 |  |  |  |  | 2021 |  |  |  | 0 | 2765000 | 0 | 0 |  | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | ZXAC | 2021-03-17 09:45 | Al-Saffar, Zaid Dhafer Hashim
59572 | Add project | 35237894 |  | FRRB - WYANDOTTE 1103 - W3 PH3.6 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-12-31 |  |  |  |  | 2021 |  |  |  | 0 | 3010000 | 0 | 0 |  | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | ZXAC | 2021-03-17 09:45 | Al-Saffar, Zaid Dhafer Hashim
59571 | Add project | 35237893 |  | FRRB - WYANDOTTE 1103 - W3 PH3.5 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-12-31 |  |  |  |  | 2021 |  |  |  | 0 | 1015000 | 0 | 0 |  | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | ZXAC | 2021-03-17 09:45 | Al-Saffar, Zaid Dhafer Hashim
59570 | Add project | 35237891 |  | FRRB - WYANDOTTE 1103 - W3 PH3.4 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-12-31 |  |  |  |  | 2021 |  |  |  | 0 | 1610000 | 0 | 0 |  | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | ZXAC | 2021-03-17 09:45 | Al-Saffar, Zaid Dhafer Hashim
59465 | Resource change | 35219266 | 120141949 | CWSP - MARIPOSA 2102CB PH 1 | Approved | 08W |  |  |  | GC |  | GC | Resource Change - Assigned to GC | 2021-06-22 |  | 4713.7 | 1304482.44 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-06-22 | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-17 15:57 | Mueller, Bret Charles | M117 | 2021-03-16 19:22 | Munkhbaatar, Munkhjin
59466 | Resource change | 35227263 | 120457435 | CWSP - MARIPOSA 2102CB PH 2 | Approved | 08W |  |  |  | GC |  | GC | Resource Change - Assigned to GC | 2021-06-22 |  | 2088.9 | 1012126.18 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-06-22 | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-17 15:57 | Mueller, Bret Charles | M117 | 2021-03-16 19:22 | Munkhbaatar, Munkhjin
53119 | Remove project | 35116515 |  | CWSP - STANISLAUS 1702 - LR1888 - PH 1.2 | Approved | 08W | [6 empty] | Order was originally reviewed by WFGC and approved based on information that 15 poles had been previously installed. Information related to previous construction however was incorrect and thus WFGC has retracted approval inlieu of more higher priority work. Requesting order be removed from MPP Workplan until further notice. | [14 empty] | UNSC |  |  | R4BA | Barron, Raul Angelo | [7 empty] | Approved |  | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-03-19 19:56 | Saraf, Shubham | AXYX | 2021-03-15 10:35 | Yuen, Aaron Ho
53066 | Resource change | 35026643 | 114258488 | DIAMOND SPRINGS 1105 - LR 2102 | Approved | 08W |  |  |  | Contract |  | GC | 3.12 Resource Update to GC | 2022-07-26 |  | 35.1 | 100000 | 2021 |  |  | 10430.5 | [5 empty] | 2020-12-31 | ESTS |  | 2022-07-26 | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:51 | Saraf, Shubham | JUPX | 2021-03-12 13:54 | Pereyda, Jessica Ann Hiroko
53038 | Update work plan date | 35224321 | 120401277 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Approved | 08W |  | N/A |  | GC |  |  | Due to the current status of this SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2022-09-30 | 2022-09-30 | 30.1 | 1 | 2021 | 2022 | 2022 |  |  |  | 5000 |  |  | 2021-12-31 | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | EDW9 | 2021-03-12 12:15 | Walker, Eric Delaney
53039 | Update work plan date | 35219589 | 120165231 | CWSP - WILDWOOD 11011454 | Approved | 08W |  | N/A |  | GC |  |  | Due to the current status of this SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2021-08-05 | 2022-09-30 | 2000.1 | 1 | 2021 | 2022 | 2022 |  |  |  | 10816 |  |  | 2021-12-31 | UNSE |  | 2021-08-05 | M5HF | Hernandez, Michael Donald James | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | EDW9 | 2021-03-12 12:09 | Walker, Eric Delaney
53037 | Update work plan date | 35192291 | 119556091 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Approved | 08W |  | N/A |  | Contract |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2022-03-02 | 2022-06-30 | 80 | 1 | 2021 | 2022 | 2022 |  |  |  | 267945.29 | 1364658.88 |  | 2023-12-31 | UNSE |  | 2022-03-02 | J1PE | Pantoja-Martinez, Jaime | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | EDW9 | 2021-03-12 12:06 | Walker, Eric Delaney
53045 | Update work plan date | 35231543 | 120504099 | CWSP - TIDEWATER 210614072 PH 1.2 | Approved | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2022-05-12 | 2022-09-30 | 80 | 350000 | 2021 | 2022 | 2022 |  |  |  | 5000 |  |  | 2021-12-31 | UNSE |  | 2022-05-12 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | EDW9 | 2021-03-12 12:04 | Walker, Eric Delaney
53047 | Update work plan date | 35219096 | 120141671 | CWSP - KIRKER 2104442850 PH 1.1 | Approved | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2022-04-29 | 2022-09-30 | 0 | 500000 | 2021 | 2022 | 2022 |  |  |  | 8302 |  |  | 2021-12-31 | UNSE |  | 2022-04-29 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | EDW9 | 2021-03-12 12:02 | Walker, Eric Delaney
53046 | Update work plan date | 35219093 | 120141622 | CWSP - TIDEWATER 210614072 PH 1.1 | Approved | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2022-05-12 | 2022-09-30 | 80 | 350000 | 2021 | 2022 | 2022 |  |  |  | 8255 |  |  | 2021-12-31 | UNSE |  | 2022-05-12 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | EDW9 | 2021-03-12 12:01 | Walker, Eric Delaney
53048 | Update work plan date | 35192280 | 119556070 | ECOP - CLAYTON 2212 - H01-LR2951 | Denied | 08W |  | N/A |  | GC |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2022-06-22 | 2022-09-30 | 180 | 550000 | 2021 | 2022 | 2022 |  |  |  | 193996.68 |  |  | 2023-12-31 | UNSE |  | 2022-06-22 | M1NO | Nguyen, My-Linh | [5 empty] | Denied | Per Nguyen, My-Linh |  |  | Merih Tekeste |  |  |  | Denied | Denied by Estimating | BCMK | 2021-03-25 14:19 | Mueller, Bret Charles | EDW9 | 2021-03-12 11:59 | Walker, Eric Delaney
53041 | Update work plan date | 35232650 | 120529254 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | Approved | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2021-09-29 | 2022-07-07 | 80 | 316667 | 2021 | 2022 | 2022 |  | 212265 |  | 162264.96 | 5177530.95 |  | 2021-12-31 | UNSE |  | 2021-09-29 | J6KF | Kringler, Jeff L | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | EDW9 | 2021-03-12 11:56 | Walker, Eric Delaney
53040 | Update work plan date | 35223036 | 120242599 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Approved | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2021-11-04 | 2022-09-30 | 0 | 500000 | 2021 | 2022 | 2022 |  | 110970 |  | 85970 |  |  | 2021-12-31 | UNSE |  | 2021-11-04 | J6KF | Kringler, Jeff L | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | EDW9 | 2021-03-12 11:54 | Walker, Eric Delaney
53044 | Update work plan date | 35219281 | 120142240 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Approved | 08W |  | N/A |  | GC |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2021-10-08 | 2022-07-07 | 110.1 | 316666 | 2021 | 2022 | 2022 |  | 251101 |  | 201100.86 | 7569489.75 |  | 2021-12-31 | UNSE |  | 2021-10-08 | J6KF | Kringler, Jeff L | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | EDW9 | 2021-03-12 11:52 | Walker, Eric Delaney
53042 | Update work plan date | 35062376 | 115323922 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Approved | 08W |  | N/A |  | GC |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2021-08-10 | 2022-09-30 | 131.1 | 220000 | 2021 | 2022 | 2022 | 22.4 | 364360.62 |  | 364360.62 | 7660323.65 |  | 2020-12-31 | UNSE |  | 2021-08-10 | J6KF | Kringler, Jeff L | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | EDW9 | 2021-03-12 11:46 | Walker, Eric Delaney
53043 | Update work plan date | 35062374 | 115323920 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Approved | 08W |  | N/A |  | GC |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2021-09-24 | 2022-07-29 | 31.1 | 220000 | 2021 | 2022 | 2022 | 365.3 | 153434.85 |  | 153434.85 | 4723361.6 |  | 2020-12-31 | UNSE |  | 2021-09-24 | J6KF | Kringler, Jeff L | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | EDW9 | 2021-03-12 11:43 | Walker, Eric Delaney
53002 | Update work plan date | 35226857 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Denied | 08W | [6 empty] | Underground work in CT ROW causing a shift to 2022 fulfillment. | 2021-12-01 | 2022-12-01 | [12 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Needs to be defer request. And needs Construction Complete Date. | BCMK | 2021-03-25 14:09 | Mueller, Bret Charles | J1E1 | 2021-03-12 08:26 | Eagar, Josh
53003 | Update work plan date | 35227007 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Denied | 08W | [6 empty] | Underground work in CT ROW causing a shift to 2022 fulfillment. | 2021-12-01 | 2022-12-01 | [12 empty] | UNSE |  |  | SFMT | Moraga, Steven | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Needs to be defer request. And needs Construction Complete Date. | BCMK | 2021-03-25 14:09 | Mueller, Bret Charles | J1E1 | 2021-03-12 08:26 | Eagar, Josh
53001 | Update work plan date | 35174478 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Denied | 08W | [6 empty] | Underground work in CT ROW causing a shift to 2022 fulfillment. | 2021-12-01 | 2022-12-01 | [12 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Needs to be defer request. And needs Construction Complete Date. | BCMK | 2021-03-25 14:09 | Mueller, Bret Charles | J1E1 | 2021-03-12 08:26 | Eagar, Josh
52997 | Update work plan date | 35226864 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Denied | 08W | [6 empty] | later EOD's causing feasibility to construct in 2021 less likely due to high volume of work in same area for 2021 | 2021-12-01 | 2022-12-01 | [12 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Needs to be defer request. And needs Construction Complete Date. | BCMK | 2021-03-25 14:09 | Mueller, Bret Charles | J1E1 | 2021-03-12 08:26 | Eagar, Josh
52998 | Update work plan date | 35226865 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Denied | 08W | [6 empty] | later EOD's causing feasibility to construct in 2021 less likely due to high volume of work in same area for 2021 | 2021-12-01 | 2022-12-01 | [12 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Needs to be defer request. And needs Construction Complete Date. | BCMK | 2021-03-25 14:09 | Mueller, Bret Charles | J1E1 | 2021-03-12 08:26 | Eagar, Josh
52999 | Update work plan date | 35226866 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Denied | 08W | [6 empty] | later EOD's causing feasibility to construct in 2021 less likely due to high volume of work in same area for 2021 | 2021-12-01 | 2022-12-01 | [12 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Needs to be defer request. And needs Construction Complete Date. | BCMK | 2021-03-25 14:09 | Mueller, Bret Charles | J1E1 | 2021-03-12 08:26 | Eagar, Josh
53000 | Update work plan date | 35226870 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Denied | 08W | [6 empty] | later EOD's causing feasibility to construct in 2021 less likely due to high volume of work in same area for 2021 | 2021-12-01 | 2022-12-01 | [12 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Needs to be defer request. And needs Construction Complete Date. | BCMK | 2021-03-25 14:09 | Mueller, Bret Charles | J1E1 | 2021-03-12 08:26 | Eagar, Josh
52996 | Update work plan date | 35226863 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Denied | 08W | [6 empty] | later EOD's causing feasibility to construct in 2021 less likely due to high volume of work in same area for 2021 | 2021-12-01 | 2022-12-01 | [12 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Needs to be defer request. And needs Construction Complete Date. | BCMK | 2021-03-25 14:08 | Mueller, Bret Charles | J1E1 | 2021-03-12 08:26 | Eagar, Josh
52988 | Budget change | 35095166 | 114742467 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Denied | 08W | 220 Mile Plan |  |  | Contract |  |  | Return $75k to the program since the project is closed now. Nothing spent in 2021 | 2020-08-06 |  | 4104 | 3293522 | 2020 |  |  | 1538336.7 |  | 0 | 0 | 0 | 0 | 2019-12-31 | CLSD |  |  | CRGN | Gras, Christopher R | [9 empty] | Merih Tekeste |  |  |  | Denied | Duplicate of change ID 52984 | SFSS | 2021-03-16 18:00 | Saraf, Shubham | ZXAC | 2021-03-11 13:32 | Al-Saffar, Zaid Dhafer Hashim
52984 | Budget change | 35095166 | 114742467 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Return $75k to the program since the project is closed now. Nothing spent in 2021 | 2020-08-06 |  | 4104 | 3293522 | 2020 |  |  | 1538336.7 |  | 0 | 0 | 0 | 0 | 2019-12-31 | CLSD |  |  | CRGN | Gras, Christopher R | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:51 | Saraf, Shubham | ZXAC | 2021-03-11 13:32 | Al-Saffar, Zaid Dhafer Hashim
52987 | Budget change | 35112437 | 117472564 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Denied | 08W | 220 Mile Plan |  |  | Contract |  |  | Return $75k to the program since the project is closed now. Nothing spent in 2021 | 2020-07-08 |  | 2578.5 | 5431839 | 2020 |  |  | 5750872.5 |  | 0 | 0 | 0 | 0 | 2020-12-31 | CLSD |  |  | CRGN | Gras, Christopher R | [9 empty] | Merih Tekeste |  |  |  | Denied | Duplicate of change ID 52983 | SFSS | 2021-03-16 18:00 | Saraf, Shubham | ZXAC | 2021-03-11 13:32 | Al-Saffar, Zaid Dhafer Hashim
52983 | Budget change | 35112437 | 117472564 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Return $75k to the program since the project is closed now. Nothing spent in 2021 | 2020-07-08 |  | 2578.5 | 5431839 | 2020 |  |  | 5750872.5 |  | 0 | 0 | 0 | 0 | 2020-12-31 | CLSD |  |  | CRGN | Gras, Christopher R | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:51 | Saraf, Shubham | ZXAC | 2021-03-11 13:32 | Al-Saffar, Zaid Dhafer Hashim
52982 | Budget change | 35112431 | 117472384 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Return $75k to the program since the project is closed now. Nothing spent in 2021 | 2020-05-27 |  | 2000.4 | 4166416 | 2020 |  |  | 2992595.4 |  | 0 | 0 | 0 | 0 | 2020-12-31 | CLSD |  |  | CRGN | Gras, Christopher R | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:51 | Saraf, Shubham | ZXAC | 2021-03-11 13:32 | Al-Saffar, Zaid Dhafer Hashim
52986 | Budget change | 35112431 | 117472384 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | Denied | 08W | 220 Mile Plan |  |  | Contract |  |  | Return $75k to the program since the project is closed now. Nothing spent in 2021 | 2020-05-27 |  | 2000.4 | 4166416 | 2020 |  |  | 2992595.4 |  | 0 | 0 | 0 | 0 | 2020-12-31 | CLSD |  |  | CRGN | Gras, Christopher R | [9 empty] | Merih Tekeste |  |  |  | Denied | Duplicate of change ID 52982 | SFSS | 2021-03-16 18:00 | Saraf, Shubham | ZXAC | 2021-03-11 13:32 | Al-Saffar, Zaid Dhafer Hashim
52981 | Budget change | 35112435 | 117472561 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Return $75k to the program since the project is closed now. Nothing spent in 2021 | 2020-05-31 |  | 5177.2 | 4061849 | 2020 |  |  | 2068858.2 |  | 0 | 0 | 0 | 0 | 2020-12-31 | CLSD |  |  | CRGN | Gras, Christopher R | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:51 | Saraf, Shubham | ZXAC | 2021-03-11 13:32 | Al-Saffar, Zaid Dhafer Hashim
52985 | Budget change | 35112435 | 117472561 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Denied | 08W | 220 Mile Plan |  |  | Contract |  |  | Return $75k to the program since the project is closed now. Nothing spent in 2021 | 2020-05-31 |  | 5177.2 | 4061849 | 2020 |  |  | 2068858.2 |  | 0 | 0 | 0 | 0 | 2020-12-31 | CLSD |  |  | CRGN | Gras, Christopher R | [9 empty] | Merih Tekeste |  |  |  | Denied | Duplicate of change ID 52981 | SFSS | 2021-03-16 18:00 | Saraf, Shubham | ZXAC | 2021-03-11 13:32 | Al-Saffar, Zaid Dhafer Hashim
52961 | Resource change | 35191937 | 119553837 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Approved | 08W |  |  |  | Contract |  | Contract | 3.11 Resource Update to Contract |  |  | 0 | 237833 | 2021 | [8 empty] | 2022-12-31 | ESTS |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | JUPX | 2021-03-11 11:31 | Pereyda, Jessica Ann Hiroko
52963 | Resource change | 35227033 | 120449807 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Approved | 08W |  |  |  | Contract |  | Contract | 3.11 Resource Update to Contract | 2022-02-04 |  | 80 | 237833 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2022-02-04 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | JUPX | 2021-03-11 11:31 | Pereyda, Jessica Ann Hiroko
52962 | Resource change | 35227032 | 120449806 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Approved | 08W |  |  |  | Contract |  | Contract | 3.11 Resource Update to Contract | 2022-02-04 |  | 80 | 237833 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2022-02-04 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | JUPX | 2021-03-11 11:31 | Pereyda, Jessica Ann Hiroko
52930 | Resource change | 35227007 | 120449533 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2022-11-01 |  | 80 | 118750 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-11-01 | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52931 | Resource change | 35227010 | 120449536 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2022-11-01 |  | 80 | 118750 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-11-01 | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52932 | Resource change | 35227013 | 120449539 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2022-11-01 |  | 80 |  | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-11-01 | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52933 | Resource change | 35227015 | 120449710 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2022-11-01 |  | 80 | 118750 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-11-01 | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52934 | Resource change | 35227018 | 120449711 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2022-11-01 |  | 80 | 118750 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-11-01 | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52935 | Resource change | 35227021 | 120449712 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2022-11-01 |  | 0 | 118750 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-11-01 | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52936 | Resource change | 35227025 | 120449714 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2022-11-01 |  | 80 | 118750 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-11-01 | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:51 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52921 | Resource change | 35174501 | 118913026 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2022-11-01 |  | 3 | 118750 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-11-01 | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:51 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52920 | Resource change | 35174478 | 118913024 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2022-11-01 |  | 123 | 155000 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52939 | Resource change | 35219589 | 120165231 | CWSP - WILDWOOD 11011454 | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2021-08-05 |  | 2000.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2021-08-05 | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52946 | Resource change | 35219281 | 120142240 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2021-10-08 |  | 110.1 | 316666 | 2021 | 2022 |  |  | 251101 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-10-08 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52923 | Resource change | 35223343 | 120255838 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2021-06-28 |  | 80 | 950000 | 2021 |  |  |  | 3490209.3 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-06-28 | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52940 | Resource change | 35224321 | 120401277 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2022-09-30 |  | 30.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52924 | Resource change | 35225821 | 120424578 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2021-07-05 |  | 80 | 950000 | 2021 |  |  |  | 3490167.5 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-07-05 | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:51 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52928 | Resource change | 35226861 | 120449203 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2022-11-01 |  | 80 | 155000 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52929 | Resource change | 35226862 | 120449204 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2022-11-01 |  | 80 | 155000 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52926 | Resource change | 35226858 | 120449201 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2022-11-01 |  | 80 | 155000 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52927 | Resource change | 35226859 | 120449202 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2022-11-01 |  | 80 | 155000 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-11-01 | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52925 | Resource change | 35226857 | 120449200 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2022-11-16 |  | 80 | 155000 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-11-16 | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52938 | Resource change | 35115152 | 117495855 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Approved | 08W |  |  |  | GC |  | GC | 3.11 Resource Update to GC | 2021-05-31 |  | 4541.7 | 3591121 | 2021 |  |  | 3558481.2 | 2229051.5 |  |  |  |  | 2020-12-31 | CONS |  | 2021-05-31 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:51 | Saraf, Shubham | JUPX | 2021-03-11 11:25 | Pereyda, Jessica Ann Hiroko
52903 | Resource change | 35231544 | 120504131 | CWSP - TIDEWATER 210614072 PH 1.3 | Approved | 08W |  |  |  | GC |  | GC | Resource Change - Assigned to GC | 2021-09-07 |  | 100 | 181000 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-09-07 | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-16 17:52 | Saraf, Shubham | M117 | 2021-03-11 09:40 | Munkhbaatar, Munkhjin
52900 | Update work plan date | 35226700 | 14272795 | CWSP - WYANDOTTE 110932586 PH 1.2 | Approved | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | 2022-06-13 | 2022-12-31 | 31.1 | 650000 | 2021 | 2022 | 2022 |  |  | 0 | 500000 | 1495265 | 0 |  | UNSE |  | 2022-06-13 | T3SQ | Skarda, Travis Damian | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | ZXAC | 2021-03-11 09:15 | Al-Saffar, Zaid Dhafer Hashim
52883 | Update work plan date | 35192280 | 119556070 | ECOP - CLAYTON 2212 - H01-LR2951 | Denied | 08W |  |  |  | GC |  |  | Defer project to 2022. Project still in estimating and requires new land rights. | 2022-06-22 | 2022-05-01 | 180 | 550000 | 2021 | 2022 | 2022 |  |  |  | 852800 | 2984800 | 426400 | 2023-12-31 | UNSE |  | 2022-06-22 | M1NO | Nguyen, My-Linh | [5 empty] | Denied | Per Nguyen, My-Linh |  |  | Merih Tekeste |  |  |  | Denied | Denied by Estimating | BCMK | 2021-03-25 14:19 | Mueller, Bret Charles | M1NO | 2021-03-11 08:17 | Nguyen, My-Linh
52784 | Resource change | 31334291 | 112994395 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Approved | 08W | [5 empty] | GC | 3.10- Resource Update to GC - added back to WP | [14 empty] | PEND |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-11 00:04 | Saraf, Shubham | JUPX | 2021-03-10 21:35 | Pereyda, Jessica Ann Hiroko
52783 | Resource change | 31361965 | 113751296 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Approved | 08W | [5 empty] | GC | 3.10- Resource Update to GC - added back to WP | [14 empty] | CONS |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-11 00:04 | Saraf, Shubham | JUPX | 2021-03-10 21:34 | Pereyda, Jessica Ann Hiroko
52594 | Budget change | 35192053 | 119554059 | STRM-OAKHURST 1103-LR 5120 PH1 | Approved | 08W |  |  |  | GC |  |  | 08W Fire Hardening Project | 2021-02-08 |  | 3504.6 | 1877409.58 | 2021 |  |  |  | 2843023 |  | 2843023 |  |  | 2022-12-31 | CONS |  | 2021-02-08 | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | B4HS | 2021-03-10 15:43 | Hayashi, Brandon
52593 | Budget change | 35227096 | 120457011 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Approved | 08W |  |  |  | GC |  |  | 08W Fire Hardening Project | 2021-02-22 |  | 1203 | 326951.18 | 2021 |  |  |  | 2183706 |  | 2183706 |  |  | 2021-12-31 | CONS |  | 2021-02-22 | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | B4HS | 2021-03-10 15:25 | Hayashi, Brandon
52592 | Update work plan date | 35226628 | 120445377 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Approved | 08W |  | 2022 |  | GC |  |  | Per PM, this job is not going to be constructed in 2021 | 2022-07-04 | 2022-12-31 | 111.1 | 150000 | 2021 | 2022 | 2022 |  |  | 0 | 500000 | 2370000 | 0 | 2021-12-31 | UNSE |  | 2022-07-04 | T3SQ | Skarda, Travis Damian | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | ZXAC | 2021-03-10 15:03 | Al-Saffar, Zaid Dhafer Hashim
52591 | Update work plan date | 35217272 | 120048018 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Approved | 08W |  | 2022 |  | GC |  |  | Per PM, this job is not going to be constructed in 2021 | 2022-06-20 | 2022-12-31 | 110.1 | 150000 | 2021 | 2022 | 2022 |  |  | 0 | 500000 | 550000 | 0 | 2021-12-31 | UNSE |  | 2022-06-20 | T3SQ | Skarda, Travis Damian | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | ZXAC | 2021-03-10 14:56 | Al-Saffar, Zaid Dhafer Hashim
52589 | Update work plan date | 35226629 | 120445378 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Denied | 08W |  | 2022 |  | GC |  |  | Per PM, this job is not going to be constructed in 2021 | 2022-07-04 | 2022-12-31 | 111.1 | 200000 | 2021 | 2022 | 2022 |  |  | 0 | 500000 | 5555000 | 0 | 2021-12-31 | UNSE |  | 2022-07-04 | T3SQ | Skarda, Travis Damian | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Denied | Duplicate of Change ID 52588 |  | Denied |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | ZXAC | 2021-03-10 14:31 | Al-Saffar, Zaid Dhafer Hashim
52588 | Update work plan date | 35226629 | 120445378 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Approved | 08W |  | 2022 |  | GC |  |  | Per PM, this job is not going to be constructed in 2021 | 2022-07-04 | 2022-12-31 | 111.1 | 200000 | 2021 | 2022 | 2022 |  |  | 0 | 500000 | 5555000 | 0 | 2021-12-31 | UNSE |  | 2022-07-04 | T3SQ | Skarda, Travis Damian | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | ZXAC | 2021-03-10 14:31 | Al-Saffar, Zaid Dhafer Hashim
61303 | Update work plan date | 35226629 | 120445378 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Denied | 08W |  | 2022 |  | GC |  |  | Per PM, this job is not going to be constructed in 2021 | 2022-07-04 | 2022-12-31 | 111.1 | 200000 | 2021 | 2022 | 2022 |  |  | 0 | 500000 | 5555000 | 0 | 2021-12-31 | UNSE |  | 2022-07-04 | T3SQ | Skarda, Travis Damian | [5 empty] | Approved |  |  |  | Merih Tekeste | Denied | Duplicate of Change ID 52588 |  | Denied | Duplicate of Change ID 52588 | BCMK | 2021-04-01 12:58 | Mueller, Bret Charles | ZXAC | 2021-03-10 14:31 | Al-Saffar, Zaid Dhafer Hashim
61304 | Update work plan date | 35226629 | 120445378 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Denied | 08W |  | 2022 |  | GC |  |  | Per PM, this job is not going to be constructed in 2021 | 2022-07-04 | 2022-12-31 | 111.1 | 200000 | 2021 | 2022 | 2022 |  |  | 0 | 500000 | 5555000 | 0 | 2021-12-31 | UNSE |  | 2022-07-04 | T3SQ | Skarda, Travis Damian | [5 empty] | Approved |  |  |  | Merih Tekeste | Denied | Duplicate of Change ID 52588 |  | Denied | Duplicate of Change ID 52588 | BCMK | 2021-04-01 12:58 | Mueller, Bret Charles | ZXAC | 2021-03-10 14:31 | Al-Saffar, Zaid Dhafer Hashim
52586 | Update work plan date | 35224713 | 120427329 | CWSP - BUCKS CREEK 1101 CB PH 3 | Approved | 08W |  | 2022 |  | GC |  |  | Per PM, this job is not going to be constructed in 2021 | 2022-03-02 | 2022-12-31 | 132 | 400000 | 2021 | 2022 | 2022 |  | 400000 | 0 | 500000 | 5905000 | 0 | 2021-12-31 | UNSE |  | 2022-03-02 | T3SQ | Skarda, Travis Damian | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | ZXAC | 2021-03-10 14:18 | Al-Saffar, Zaid Dhafer Hashim
52584 | Update work plan date | 35224712 | 120427328 | CWSP - BUCKS CREEK 1101 CB PH 2 | Approved | 08W |  | 2022 |  | GC |  |  | Per PM, this job is not going to be constructed in 2021 | 2022-03-02 | 2022-12-31 | 132 | 400000 | 2021 | 2022 | 2022 |  | 400000 | 0 | 500000 | 15250000 | 0 | 2021-12-31 | UNSE |  | 2022-03-02 | T3SQ | Skarda, Travis Damian | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-26 11:16 | Mueller, Bret Charles | ZXAC | 2021-03-10 14:05 | Al-Saffar, Zaid Dhafer Hashim
52582 | Budget change | 35115152 | 117495855 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Approved | 08W |  |  |  | GC |  |  | this project pulled back to 2021 WP. Requesting $2,229,051.5 in 2021 to allign with BC figures | 2021-05-31 |  | 4541.7 | 3591121 | 2021 |  |  | 3558481.2 | 2229051.5 | 0 | 2229051.5 | 0 | 0 | 2020-12-31 | CONS |  | 2021-05-31 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-10 13:43 | Al-Saffar, Zaid Dhafer Hashim
52583 | Budget change | 35115152 | 117495855 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Denied | 08W |  |  |  | GC |  |  | this project pulled back to 2021 WP. Requesting $2,229,051.5 in 2021 to allign with BC figures | 2021-05-31 |  | 4541.7 | 3591121 | 2021 |  |  | 3558481.2 | 2229051.5 | 0 | 2229051.5 | 0 | 0 | 2020-12-31 | CONS |  | 2021-05-31 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Denied | Duplicate of change ID 52582 | SFSS | 2021-03-11 00:03 | Saraf, Shubham | ZXAC | 2021-03-10 13:43 | Al-Saffar, Zaid Dhafer Hashim
52578 | Budget change | 35217275 | 120048103 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Approved | 08W |  |  |  | Contract |  |  | Requesting 2021MPP $10,150,000. using Avarage cost for UG per mile $3.5M. The project mile is 2.90 | 2022-09-21 |  | 80 | 500000 | 2021 |  |  |  | 10150000 | 0 | 10150000 | 0 | 0 | 2021-12-31 | UNSE |  | 2022-09-21 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-10 11:30 | Al-Saffar, Zaid Dhafer Hashim
52577 | Budget change | 35217274 | 120048101 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Approved | 08W |  |  |  | Contract |  |  | Requesting 2021MPP $7,805,000. using Avarage cost for UG per mile $3.5M. The project mile is 2.23 | 2022-09-21 |  | 80 | 500000 | 2021 |  |  |  | 7805000 | 0 | 7805000 | 0 | 0 | 2021-12-31 | UNSE |  | 2022-09-21 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-10 11:28 | Al-Saffar, Zaid Dhafer Hashim
52576 | Budget change | 35235707 | 120594569 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Approved | 08W |  |  |  | GC |  |  | Requesting 2021 Budget $3,325,000. project is 0.95 mile. Using avarege cost $3.5M for UG | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 3325000 | 0 | 3325000 | 0 | 0 | 2022-03-03 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-10 10:07 | Al-Saffar, Zaid Dhafer Hashim
52572 | Budget change | 35235706 | 120594568 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Approved | 08W |  |  |  | GC |  |  | Requesting 2021 Budget $4,060,000. project is 1.16 mile. Using avarege cost $3.5M for UG | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 4060000 | 0 | 4060000 | 0 | 0 | 2022-03-03 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-10 10:05 | Al-Saffar, Zaid Dhafer Hashim
52571 | Budget change | 35235705 | 120594567 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Approved | 08W |  |  |  | GC |  |  | Requesting 2021 Budget $4,620,000. project is 1.32 mile. Using avarege cost $3.5M for UG | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 4620000 | 0 | 4620000 | 0 | 0 | 2022-03-03 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-10 10:02 | Al-Saffar, Zaid Dhafer Hashim
52569 | Budget change | 35233315 | 120541636 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Approved | 08W |  |  |  | GC |  |  | Requesting 2021 Budget $3,360,000. project is 0.96 mile. Using avarege cost $3.5M for UG | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 3360000 | 0 | 3360000 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-10 09:59 | Al-Saffar, Zaid Dhafer Hashim
52575 | Budget change | 35233314 | 120541635 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Approved | 08W |  |  |  | GC |  |  | Requesting 2021 Budget $5,600,000. project is 1.6 mile. Using avarege cost $3.5M for UG | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 5600000 | 0 | 5600000 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-10 09:57 | Al-Saffar, Zaid Dhafer Hashim
52574 | Budget change | 35233312 | 120541634 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Approved | 08W |  |  |  | GC |  |  | Requesting 2021 Budget $3,850,000. project is 1.1 mile. Using avarege cost $3.5M for UG | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 3850000 | 0 | 3850000 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-10 09:55 | Al-Saffar, Zaid Dhafer Hashim
52573 | Budget change | 35233311 | 120541633 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Approved | 08W |  |  |  | GC |  |  | Requesting 2021 Budget $4,375,000. project is 1.25 mile. Using avarege cost $3.5M for UG | 2021-07-19 |  | 30.1 | 118750 | 2021 |  |  |  | 4375000 | 0 | 4375000 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-07-19 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-10 09:52 | Al-Saffar, Zaid Dhafer Hashim
52570 | Budget change | 35232718 | 120538803 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Approved | 08W | [6 empty] | Requesting 2021 Budget $4,200,000. project is 1.2 mile. Using avarege cost $3.5M for UG | 2021-05-24 |  | 0 | 118750 | 2021 |  |  |  | 4200000 | 0 | 4200000 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-05-24 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-10 09:50 | Al-Saffar, Zaid Dhafer Hashim
52447 | Add project | 35219286 |  | CWSP - DESCHUTES 11049718 PH1.1 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | 2021-12-31 |  |  |  | 2021 | [9 empty] | ESTS |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 New construction Complete year | SFSS | 2021-03-16 17:57 | Saraf, Shubham | AXYX | 2021-03-10 08:47 | Yuen, Aaron Ho
52443 | Add project | 35232442 |  | CWSP - DESCHUTES 11049718 PH 2.2 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | 2021-12-31 |  |  |  | 2021 | [9 empty] | ESTS |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 New construction Complete year | SFSS | 2021-03-16 17:57 | Saraf, Shubham | AXYX | 2021-03-10 08:47 | Yuen, Aaron Ho
52444 | Add project | 35232443 |  | CWSP - DESCHUTES 11049718 PH 2.3 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | 2021-12-31 |  |  |  | 2021 | [9 empty] | ESTS |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 New construction Complete year | SFSS | 2021-03-16 17:57 | Saraf, Shubham | AXYX | 2021-03-10 08:47 | Yuen, Aaron Ho
52445 | Add project | 35232444 |  | CWSP - DESCHUTES 11049718 PH 2.4 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | 2021-12-31 |  |  |  | 2021 | [9 empty] | ESTS |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 New construction Complete year | SFSS | 2021-03-16 17:57 | Saraf, Shubham | AXYX | 2021-03-10 08:47 | Yuen, Aaron Ho
52446 | Add project | 35232445 |  | CWSP - DESCHUTES 11049718 PH 2.5 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | 2021-12-31 |  |  |  | 2021 | [9 empty] | ESTS |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 New construction Complete year | SFSS | 2021-03-16 17:57 | Saraf, Shubham | AXYX | 2021-03-10 08:47 | Yuen, Aaron Ho
52448 | Add project | 35232960 |  | CWSP - DESCHUTES 11049718 PH1.2 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | 2021-12-31 |  |  |  | 2021 | [9 empty] | ESTS |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 New construction Complete year | SFSS | 2021-03-16 17:57 | Saraf, Shubham | AXYX | 2021-03-10 08:47 | Yuen, Aaron Ho
52442 | Add project | 35225825 |  | CWSP - DESCHUTES 11049718 PH2.1 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | 2021-12-31 |  |  |  | 2021 | [9 empty] | ESTS |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 New construction Complete year | SFSS | 2021-03-16 17:57 | Saraf, Shubham | AXYX | 2021-03-10 08:46 | Yuen, Aaron Ho
52438 | Budget change | 35061206 | 115106231 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | inherited this project from Jeff Kringeler.requesting 2021 budget$1,419,181 to allign with approved BC | 2020-06-15 |  | 4091.3 | 4711641 | 2020 | 2021 |  | 3596290.1 | 1419181 | 0 | 1419181 | 0 | 0 | 2020-12-31 | CONS |  | 2020-06-15 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-09 21:22 | Al-Saffar, Zaid Dhafer Hashim
52437 | Budget change | 35117443 | 117634567 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | this job inhertted from Jeff Kringler. Requesting $2,450,191 to allign with the approved BC | 2020-07-28 |  | 5134.2 | 5778810 | 2020 | 2021 |  | 4175407.8 | 2450191 | 0 | 2450191 | 0 | 0 | 2020-12-31 | CONS |  | 2020-07-28 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-09 21:12 | Al-Saffar, Zaid Dhafer Hashim
52436 | Budget change | 35226631 | 120445423 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Approved | 08W |  |  |  | GC |  |  | requesting $2,926,000 for 2021. project miles 1.54 | 2021-08-25 |  | 1581.1 | 150000 | 2021 |  |  |  | 2926000 | 0 | 2926000 | 0 | 0 | 2021-12-31 | ESTS |  | 2021-08-25 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-09 20:43 | Al-Saffar, Zaid Dhafer Hashim
52435 | Budget change | 35226630 | 120445421 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Approved | 08W |  |  |  | GC |  |  | requesting $2,736,000 for 2021. project miles is 1.44 | 2021-08-05 |  | 1581.1 | 150000 | 2021 |  |  |  | 2736000 | 0 | 2736000 | 0 | 0 | 2021-12-31 | ESTS |  | 2021-08-05 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-09 20:43 | Al-Saffar, Zaid Dhafer Hashim
52434 | Budget change | 35217268 | 120047659 | CWSP - BUCKS CREEK 1101 CB PH 1 | Approved | 08W |  |  |  | GC |  |  | requesting $551,000 for 2021. project miles 0.3 | 2021-09-22 |  | 690.1 | 150000 | 2021 |  |  |  | 380000 | 0 | 380000 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-09-22 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-09 20:42 | Al-Saffar, Zaid Dhafer Hashim
52433 | Budget change | 35226627 | 120445375 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Approved | 08W |  |  |  | GC |  |  | requesting $551,000 for 2021. project miles 0.3 | 2021-10-06 |  | 111.1 | 150000 | 2021 |  |  |  | 551000 | 0 | 551000 | 0 | 0 | 2021-12-31 | ESTS |  | 2021-10-06 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-09 20:42 | Al-Saffar, Zaid Dhafer Hashim
52432 | Budget change | 35219260 | 120141880 | CWSP - WYANDOTTE 110932586 PH 1.1 | Approved | 08W |  |  |  | GC |  |  | requesting $1.52M for 2021. using avarage cost per mile for 08W $1.9M. The project miles is 0.8 |  |  | 31.1 | 300000 | 2021 |  |  |  | 1520000 | 0 | 1520000 | 0 | 0 | 2021-12-31 | ADER |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-09 20:31 | Al-Saffar, Zaid Dhafer Hashim
52431 | Update work plan date | 35223039 | 120242691 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Approved | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | 2021-09-01 | 2022-12-31 | 0 | 950000 | 2021 | 2022 | 2022 |  |  | 0 | 500000 | 5905000 | 0 | 2021-12-31 | UNSE |  | 2021-09-01 | T3SQ | Skarda, Travis Damian | [5 empty] | Approved |  | Approved | Defer project approved | Merih Tekeste | Approved |  |  | Approved | Approve so long as all info is provided | BCMK | 2021-03-26 11:20 | Mueller, Bret Charles | ZXAC | 2021-03-09 15:59 | Al-Saffar, Zaid Dhafer Hashim
52425 | Budget change | 35233309 | 120541630 | FRRB - WYANDOTTE 1103 - W1 PH1.13 | Approved | 08W |  |  |  | GC |  |  | Per Paul Stnden, requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-04-28 |  | 30.1 | 3728491 | 2021 |  |  |  | 1282670.45 | 0 | 1282670.45 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-09 14:51 | Al-Saffar, Zaid Dhafer Hashim
52424 | Budget change | 35233304 | 120542506 | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | Approved | 08W |  |  |  | GC |  |  | Per Paul Stnden, requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-04-28 |  | 30.1 | 3444978 | 2021 |  |  |  | 1064583.33 | 0 | 1064583.33 | 0 | 0 | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-09 14:51 | Al-Saffar, Zaid Dhafer Hashim
52423 | Budget change | 35233305 | 120542507 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Approved | 08W |  |  |  | GC |  |  | Per Paul Stnden, requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-04-28 |  | 30.1 | 3378623 | 2021 |  |  |  | 1013541.67 | 0 | 1013541.67 | 0 | 0 | 2022-01-01 | UNSE |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-09 14:51 | Al-Saffar, Zaid Dhafer Hashim
52422 | Budget change | 35232298 | 120532441 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Approved | 08W |  |  |  | GC |  |  | Per Paul Stnden, requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-04-28 |  | 30.1 | 3159481 | 2021 |  |  |  | 845833.33 | 0 | 845833.33 | 0 | 0 | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-09 14:51 | Al-Saffar, Zaid Dhafer Hashim
52421 | Budget change | 35233301 | 120542503 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Approved | 08W |  |  |  | GC |  |  | Per Paul Stnden, requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-04-28 |  | 30.1 | 3715565 | 2021 |  |  |  | 1272727.27 | 0 | 1272727.27 | 0 | 0 | 2022-01-01 | UNSE |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-09 14:51 | Al-Saffar, Zaid Dhafer Hashim
52420 | Budget change | 35233038 | 120542278 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Approved | 08W |  |  |  | GC |  |  | Per Paul Stnden, requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-04-28 |  | 30.1 | 3118378 | 2021 |  |  |  | 813352.27 | 0 | 813352.27 | 0 | 0 | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-09 14:51 | Al-Saffar, Zaid Dhafer Hashim
52419 | Budget change | 35233308 | 120541539 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Approved | 08W |  |  |  | GC |  |  | Per Paul Stnden, requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-04-28 |  | 30.1 | 6280110 | 2021 |  |  |  | 1761818.18 | 0 | 1761818.18 | 0 | 0 | 2021-12-31 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-09 14:50 | Al-Saffar, Zaid Dhafer Hashim
52418 | Budget change | 35233307 | 120541538 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Approved | 08W |  |  |  | GC |  |  | Per Paul Stnden, requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-04-28 |  | 30.1 | 4778094 | 2021 |  |  |  | 2090056.82 | 0 | 2090056.82 | 0 | 0 | 2021-12-31 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-09 14:50 | Al-Saffar, Zaid Dhafer Hashim
52417 | Budget change | 35233039 | 120542500 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Approved | 08W |  |  |  | GC |  |  | Per Paul Stnden, requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-04-28 |  | 30.1 | 3729353 | 2021 |  |  |  | 1283333.33 | 0 | 1283333.33 | 0 | 0 | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-09 14:50 | Al-Saffar, Zaid Dhafer Hashim
52416 | Budget change | 35233300 | 120542502 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Approved | 08W |  |  |  | GC |  |  | Per Paul Stnden, requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-04-28 |  | 30.1 | 3535462 | 2021 |  |  |  | 1134185.61 | 0 | 1134185.61 | 0 | 0 | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-10 23:49 | Saraf, Shubham | ZXAC | 2021-03-09 14:50 | Al-Saffar, Zaid Dhafer Hashim
52134 | Pull-in Project from Future Year | 31334291 |  | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Denied | 08W | [6 empty] | Program requested project to move to 2021 workplan | 2021-06-30 |  |  |  |  | 2021 | [8 empty] | PEND |  |  | J1E1 | Eagar, Josh | [7 empty] | Approved |  | Merih Tekeste |  |  |  | Denied | Project not on MPP work plan | BCMK | 2021-03-18 09:55 | Mueller, Bret Charles | D5A8 | 2021-03-08 14:59 | Arrow, Daniel
52133 | Pull-in Project from Future Year | 31361965 |  | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Denied | 08W | [6 empty] | Program requested project to move to 2021 workplan | 2021-03-31 |  |  |  |  | 2021 | [8 empty] | CONS |  |  | J1E1 | Eagar, Josh | [7 empty] | Approved |  | Merih Tekeste |  |  |  | Denied | Project not on MPP work plan | BCMK | 2021-03-18 09:55 | Mueller, Bret Charles | D5A8 | 2021-03-08 14:59 | Arrow, Daniel
51957 | Resource change | 35231609 | 120504096 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Approved | 08W |  |  |  | GC |  | GC | 3.4 Resource Update to GC | 2021-07-06 |  | 110.1 | 70000 | 2021 |  |  |  | 2649841.53 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-07-06 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 11:14 | Mueller, Bret Charles | JUPX | 2021-03-04 10:47 | Pereyda, Jessica Ann Hiroko
51955 | Resource change | 35231607 | 120504093 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Approved | 08W |  |  |  | GC |  | GC | 3.4 Resource Update to GC | 2021-08-09 |  | 110.1 | 70000 | 2021 |  |  |  | 2867422.68 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-08-09 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 11:14 | Mueller, Bret Charles | JUPX | 2021-03-04 10:47 | Pereyda, Jessica Ann Hiroko
51956 | Resource change | 35231608 | 120504095 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Approved | 08W |  |  |  | GC |  | GC | 3.4 Resource Update to GC | 2021-08-09 |  | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-08-09 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 11:14 | Mueller, Bret Charles | JUPX | 2021-03-04 10:47 | Pereyda, Jessica Ann Hiroko
51950 | Resource change | 35226627 | 120445375 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Approved | 08W |  |  |  | GC |  | GC | 3.4 Resource Update to GC | 2021-10-06 |  | 111.1 | 150000 | 2021 |  |  |  | 551000 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-10-06 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 11:14 | Mueller, Bret Charles | JUPX | 2021-03-04 10:47 | Pereyda, Jessica Ann Hiroko
51951 | Resource change | 35226628 | 120445377 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Approved | 08W |  |  |  | GC |  | GC | 3.4 Resource Update to GC | 2022-07-04 |  | 111.1 | 150000 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-07-04 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 11:14 | Mueller, Bret Charles | JUPX | 2021-03-04 10:47 | Pereyda, Jessica Ann Hiroko
51952 | Resource change | 35226629 | 120445378 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Approved | 08W |  |  |  | GC |  | GC | 3.4 Resource Update to GC | 2022-07-04 |  | 111.1 | 200000 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-07-04 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 11:14 | Mueller, Bret Charles | JUPX | 2021-03-04 10:47 | Pereyda, Jessica Ann Hiroko
51953 | Resource change | 35226630 | 120445421 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Approved | 08W |  |  |  | GC |  | GC | 3.4 Resource Update to GC | 2021-08-05 |  | 1581.1 | 150000 | 2021 |  |  |  | 2736000 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-08-05 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 11:14 | Mueller, Bret Charles | JUPX | 2021-03-04 10:47 | Pereyda, Jessica Ann Hiroko
51947 | Resource change | 35225823 | 120424672 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Approved | 08W |  |  |  | GC |  | GC | 3.4 Resource Update to GC | 2021-05-12 |  | 4018.3 | 6586891 | 2021 |  |  |  | 4901112 |  |  |  |  | 2021-12-31 | CONS |  | 2021-05-12 | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 11:14 | Mueller, Bret Charles | JUPX | 2021-03-04 10:47 | Pereyda, Jessica Ann Hiroko
51954 | Resource change | 35226631 | 120445423 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Approved | 08W |  |  |  | GC |  | GC | 3.4 Resource Update to GC | 2021-08-25 |  | 1581.1 | 150000 | 2021 |  |  |  | 2926000 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-08-25 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 11:14 | Mueller, Bret Charles | JUPX | 2021-03-04 10:47 | Pereyda, Jessica Ann Hiroko
51948 | Resource change | 35226845 | 120448987 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Approved | 08W |  |  |  | Contract |  | GC | 3.4 Resource Update to GC | 2021-08-18 |  | 80 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-08-18 | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 11:14 | Mueller, Bret Charles | JUPX | 2021-03-04 10:47 | Pereyda, Jessica Ann Hiroko
51946 | Resource change | 35225822 | 120424579 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Approved | 08W |  |  |  | GC |  | GC | 3.4 Resource Update to GC | 2021-03-01 |  | 2924.8 | 4380690 | 2021 |  |  |  | 3743276.52 |  |  |  |  | 2021-12-31 | CONS |  | 2021-03-01 | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 11:14 | Mueller, Bret Charles | JUPX | 2021-03-04 10:47 | Pereyda, Jessica Ann Hiroko
51873 | Budget change | 35233307 | 120541538 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Approved | 08W |  |  |  | GC |  |  | requeting $500k to algin with AA budget for 2021 | 2021-04-28 |  | 30.1 | 4778094 | 2021 |  |  |  | 2090056.82 | 0 | 500000 | 0 | 0 | 2021-12-31 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | ZXAC | 2021-03-04 10:24 | Al-Saffar, Zaid Dhafer Hashim
51872 | Budget change | 35233305 | 120542507 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Approved | 08W |  |  |  | GC |  |  | requeting $500k to algin with AA budget for 2021 | 2021-04-28 |  | 30.1 | 3378623 | 2021 |  |  |  | 1013541.67 | 0 | 500000 | 0 | 0 | 2022-01-01 | UNSE |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | ZXAC | 2021-03-04 10:24 | Al-Saffar, Zaid Dhafer Hashim
51868 | Budget change | 35233303 | 120542505 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Approved | 08W |  |  |  | GC |  |  | requeting $500k to algin with AA budget for 2021 | 2021-04-28 |  | 30.1 | 2470520 | 2021 |  |  |  | 500000 | 0 | 500000 | 0 | 0 | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | ZXAC | 2021-03-04 10:24 | Al-Saffar, Zaid Dhafer Hashim
51866 | Budget change | 35233300 | 120542502 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Approved | 08W |  |  |  | GC |  |  | requeting $500k to algin with AA budget for 2021 | 2021-04-28 |  | 30.1 | 3535462 | 2021 |  |  |  | 1134185.61 | 0 | 500000 | 0 | 0 | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | ZXAC | 2021-03-04 10:24 | Al-Saffar, Zaid Dhafer Hashim
51871 | Budget change | 35233039 | 120542500 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Approved | 08W |  |  |  | GC |  |  | requeting $500k to algin with AA budget for 2021 | 2021-04-28 |  | 30.1 | 3729353 | 2021 |  |  |  | 1283333.33 | 0 | 500000 | 0 | 0 | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | ZXAC | 2021-03-04 10:24 | Al-Saffar, Zaid Dhafer Hashim
51869 | Budget change | 35233306 | 120541535 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Approved | 08W |  |  |  | GC |  |  | requeting $500k to algin with AA budget for 2021 | 2021-04-28 |  | 30.1 | 3246777 | 2021 |  |  |  | 500000 | 0 | 500000 | 0 | 0 | 2021-12-31 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | ZXAC | 2021-03-04 10:24 | Al-Saffar, Zaid Dhafer Hashim
51867 | Budget change | 35232298 | 120532441 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Approved | 08W |  |  |  | GC |  |  | requeting $500k to algin with AA budget for 2021 | 2021-04-28 |  | 30.1 | 3159481 | 2021 |  |  |  | 845833.33 | 0 | 500000 | 0 | 0 | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | ZXAC | 2021-03-04 10:24 | Al-Saffar, Zaid Dhafer Hashim
51870 | Budget change | 35233308 | 120541539 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Approved | 08W |  |  |  | GC |  |  | requeting $500k to algin with AA budget for 2021 | 2021-04-28 |  | 30.1 | 6280110 | 2021 |  |  |  | 1761818.18 | 0 | 500000 | 0 | 0 | 2021-12-31 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | ZXAC | 2021-03-04 10:24 | Al-Saffar, Zaid Dhafer Hashim
51860 | Budget change | 35233309 | 120541630 | FRRB - WYANDOTTE 1103 - W1 PH1.13 | Approved | 08W |  |  |  | GC |  |  | requeting $500k to algin with AA budget for 2021 | 2021-04-28 |  | 30.1 | 3728491 | 2021 |  |  |  | 1282670.45 | 0 | 500000 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | ZXAC | 2021-03-04 10:24 | Al-Saffar, Zaid Dhafer Hashim
51861 | Budget change | 35233310 | 120541632 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Approved | 08W |  |  |  | GC |  |  | requeting $500k to algin with AA budget for 2021 | 2021-04-28 |  | 30.1 | 2743520 | 2021 |  |  |  | 500000 | 0 | 500000 | 0 | 0 | 2021-12-31 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | ZXAC | 2021-03-04 10:24 | Al-Saffar, Zaid Dhafer Hashim
51862 | Budget change | 35233038 | 120542278 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Approved | 08W |  |  |  | GC |  |  | requeting $500k to algin with AA budget for 2021 | 2021-04-28 |  | 30.1 | 3118378 | 2021 |  |  |  | 813352.27 | 0 | 500000 | 0 | 0 | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | ZXAC | 2021-03-04 10:24 | Al-Saffar, Zaid Dhafer Hashim
51864 | Budget change | 35233301 | 120542503 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Approved | 08W |  |  |  | GC |  |  | requeting $500k to algin with AA budget for 2021 | 2021-04-28 |  | 30.1 | 3715565 | 2021 |  |  |  | 1272727.27 | 0 | 500000 | 0 | 0 | 2022-01-01 | UNSE |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | ZXAC | 2021-03-04 10:24 | Al-Saffar, Zaid Dhafer Hashim
51863 | Budget change | 35233302 | 120542504 | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | Approved | 08W |  |  |  | GC |  |  | requeting $500k to algin with AA budget for 2021 | 2021-04-21 |  | 0.6 | 147014.36 | 2021 |  |  |  | 500000 | 0 | 500000 | 0 | 0 | 2022-01-01 | ESTS |  | 2021-04-21 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | ZXAC | 2021-03-04 10:24 | Al-Saffar, Zaid Dhafer Hashim
51865 | Budget change | 35233304 | 120542506 | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | Approved | 08W |  |  |  | GC |  |  | requeting $500k to algin with AA budget for 2021 | 2021-04-28 |  | 30.1 | 3444978 | 2021 |  |  |  | 1064583.33 | 0 | 500000 | 0 | 0 | 2022-01-01 | ESTS |  | 2021-04-28 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | ZXAC | 2021-03-04 10:24 | Al-Saffar, Zaid Dhafer Hashim
51802 | Add project | 35233311 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Approved | 08W | [6 empty] | requesting to add this project to the WP as part of NCFR program | 2021-12-31 | [5 empty] | 2021 | [7 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ZXAC | 2021-03-04 09:14 | Al-Saffar, Zaid Dhafer Hashim
51807 | Add project | 35235706 |  | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Approved | 08W | [6 empty] | requesting to add this project to the WP as part of NCFR program | 2021-12-31 | [5 empty] | 2021 | [7 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ZXAC | 2021-03-04 09:14 | Al-Saffar, Zaid Dhafer Hashim
51806 | Add project | 35235705 |  | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Approved | 08W | [6 empty] | requesting to add this project to the WP as part of NCFR program | 2021-12-31 | [5 empty] | 2021 | [7 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ZXAC | 2021-03-04 09:14 | Al-Saffar, Zaid Dhafer Hashim
51801 | Add project | 35232718 |  | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Approved | 08W | [6 empty] | requesting to add this project to the WP as part of NCFR program | 2021-12-31 | [5 empty] | 2021 | [7 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ZXAC | 2021-03-04 09:14 | Al-Saffar, Zaid Dhafer Hashim
51803 | Add project | 35233312 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Approved | 08W | [6 empty] | requesting to add this project to the WP as part of NCFR program | 2021-12-31 | [5 empty] | 2021 | [7 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ZXAC | 2021-03-04 09:14 | Al-Saffar, Zaid Dhafer Hashim
51805 | Add project | 35233315 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Approved | 08W | [6 empty] | requesting to add this project to the WP as part of NCFR program | 2021-12-31 | [5 empty] | 2021 | [7 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ZXAC | 2021-03-04 09:14 | Al-Saffar, Zaid Dhafer Hashim
51808 | Add project | 35235707 |  | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Approved | 08W | [6 empty] | requesting to add this project to the WP as part of NCFR program | 2021-12-31 | [5 empty] | 2021 | [7 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ZXAC | 2021-03-04 09:14 | Al-Saffar, Zaid Dhafer Hashim
51804 | Add project | 35233314 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Approved | 08W | [6 empty] | requesting to add this project to the WP as part of NCFR program | 2021-12-31 | [5 empty] | 2021 | [7 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ZXAC | 2021-03-04 09:14 | Al-Saffar, Zaid Dhafer Hashim
51754 | Budget change | 35062376 | 115323922 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Approved | 08W |  |  |  | GC |  |  | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 & 2022 workplan. | 2021-08-10 |  | 131.1 | 220000 | 2021 | 2022 |  | 22.4 | 364360.62 |  | 364360.62 | 7660323.65 |  | 2020-12-31 | UNSE |  | 2021-08-10 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | M4JQ | 2021-03-04 08:17 | James, Matthew
51750 | Resource change | 35227260 | 120457078 | CWSP - COARSEGOLD 2104CB PH 1.2 | Approved | 08W |  |  |  | Contract |  | Contract | Resource Change - Assigned to Contract | 2021-07-28 |  | 80 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-07-28 | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 10:38 | Mueller, Bret Charles | M117 | 2021-03-04 08:17 | Munkhbaatar, Munkhjin
51751 | Resource change | 35227261 | 120457111 | CWSP - COARSEGOLD 2104CB PH 1.3 | Approved | 08W |  |  |  | Contract |  | Contract | Resource Change - Assigned to Contract | 2021-08-03 |  | 80 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-08-03 | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 10:38 | Mueller, Bret Charles | M117 | 2021-03-04 08:17 | Munkhbaatar, Munkhjin
51752 | Resource change | 35227262 | 120457115 | CWSP - COARSEGOLD 2104CB PH 1.4 | Approved | 08W |  |  |  | Contract |  | Contract | Resource Change - Assigned to Contract | 2021-08-17 |  | 1487.4 | 886518.78 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-08-17 | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 10:38 | Mueller, Bret Charles | M117 | 2021-03-04 08:17 | Munkhbaatar, Munkhjin
51753 | Resource change | 35223037 | 120242694 | PSPS - OAKHURST 1101 - OAKHURST | Approved | 08W |  |  |  | GC |  | GC | Resource Change - Assigned to GC |  |  | 419.4 | 124376.18 | 2021 | [8 empty] | 2021-12-31 | PEND |  |  | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 10:38 | Mueller, Bret Charles | M117 | 2021-03-04 08:17 | Munkhbaatar, Munkhjin
51749 | Resource change | 35219097 | 120141762 | CWSP - COARSEGOLD 2104CB PH 1.1 | Approved | 08W |  |  |  | Contract |  | Contract | Resource Change - Assigned to Contract | 2021-08-03 |  | 80 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-08-03 | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 10:38 | Mueller, Bret Charles | M117 | 2021-03-04 08:17 | Munkhbaatar, Munkhjin
51727 | Add project | 35085847 | 113255606 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Approved | 08W | [6 empty] | Keep relations with regulators | 2022-09-30 |  | 1380.2 | 5136422 | 2022 |  | 2022 | 6463.1 | 1353842.8 |  |  |  |  | 2019-09-30 | PEND |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2022 completion year | SFSS | 2021-03-08 15:19 | Saraf, Shubham | SLKD | 2021-03-04 07:32 | Kennedy, Sharon
51726 | Add project | 35015704 | 113255603 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Approved | 08W | [6 empty] | Keep relations with regulators | 2022-09-30 |  | 1186.4 | 99000 | 2022 |  | 2022 | 5945.7 | 1196.1 |  |  |  |  | 2019-09-30 | PEND |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2022 completion year | SFSS | 2021-03-08 15:19 | Saraf, Shubham | SLKD | 2021-03-04 07:32 | Kennedy, Sharon
51724 | Resource change | 35217271 | 120048017 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Approved | 08W |  |  |  | GC |  | GC | 3.3 Resource Update to GC | 2021-11-24 |  | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-11-24 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 10:38 | Mueller, Bret Charles | JUPX | 2021-03-03 20:35 | Pereyda, Jessica Ann Hiroko
51723 | Resource change | 35217269 | 120048011 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Approved | 08W |  |  |  | GC |  | GC | 3.3 Resource Update to GC | 2021-12-27 |  | 110.1 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-12-27 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 10:38 | Mueller, Bret Charles | JUPX | 2021-03-03 20:34 | Pereyda, Jessica Ann Hiroko
51722 | Resource change | 35192282 | 119556300 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Approved | 08W |  |  |  | GC |  | GC | 3.3 Resource Update to GC | 2021-08-18 |  | 110.1 | 950000 | 2021 | [8 empty] | 2023-12-31 | UNSE |  | 2021-08-18 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 10:38 | Mueller, Bret Charles | JUPX | 2021-03-03 20:34 | Pereyda, Jessica Ann Hiroko
51721 | Resource change | 35192281 | 119556250 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Approved | 08W |  |  |  | GC |  | GC | 3.3 Resource Update to GC | 2021-08-17 |  | 110.1 | 950000 | 2021 | [8 empty] | 2023-12-31 | ESTS |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 10:38 | Mueller, Bret Charles | JUPX | 2021-03-03 20:34 | Pereyda, Jessica Ann Hiroko
51755 | Budget change | 35062374 | 115323920 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Approved | 08W |  |  |  | GC |  |  | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 & 2022 workplan. | 2021-09-24 |  | 31.1 | 220000 | 2021 | 2022 |  | 365.3 | 153434.85 |  | 153434.85 | 4723361.6 |  | 2020-12-31 | UNSE |  | 2021-09-24 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | M4JQ | 2021-03-03 16:21 | James, Matthew
51672 | Budget change | 35226847 | 120449140 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Approved | 08W |  |  |  | GC |  |  | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 workplan | 2021-08-09 |  | 130.1 | 70000 | 2021 |  |  |  | 3812484.87 |  | 3812484.87 |  |  | 2021-12-31 | ESTS |  | 2021-08-09 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | M4JQ | 2021-03-03 15:27 | James, Matthew
51673 | Budget change | 35226854 | 120449147 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Approved | 08W |  |  |  | GC |  |  | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 workplan | 2021-07-08 |  | 130.1 | 70000 | 2021 |  |  |  | 2086816.03 |  | 2086816.03 |  |  | 2021-12-31 | ESTS |  | 2021-07-08 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | M4JQ | 2021-03-03 15:27 | James, Matthew
51674 | Budget change | 35226856 | 120449149 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Approved | 08W |  |  |  | GC |  |  | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 workplan | 2021-07-07 |  | 130.1 | 70000 | 2021 |  |  |  | 8862572.16 |  | 8862572.16 |  |  | 2021-12-31 | ESTS |  | 2021-07-07 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | M4JQ | 2021-03-03 15:27 | James, Matthew
51675 | Budget change | 35226852 | 120449145 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Approved | 08W |  |  |  | GC |  |  | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 workplan | 2021-08-09 |  | 130.1 | 70000 | 2021 |  |  |  | 7975840.77 |  | 7975840.77 |  |  | 2021-12-31 | ESTS |  | 2021-08-09 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | M4JQ | 2021-03-03 15:27 | James, Matthew
51671 | Budget change | 35226853 | 120449146 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Approved | 08W |  |  |  | GC |  |  | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 workplan | 2021-07-05 |  | 130.1 | 70000 | 2021 |  |  |  | 5802223.75 |  | 5802223.75 |  |  | 2021-12-31 | UNSE |  | 2021-07-05 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | M4JQ | 2021-03-03 15:27 | James, Matthew
51670 | Budget change | 35231607 | 120504093 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Approved | 08W |  |  |  | GC |  |  | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 workplan | 2021-08-09 |  | 110.1 | 70000 | 2021 |  |  |  | 2867422.68 |  | 2867422.68 |  |  | 2021-12-31 | ESTS |  | 2021-08-09 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | M4JQ | 2021-03-03 15:27 | James, Matthew
51669 | Budget change | 35231609 | 120504096 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Approved | 08W |  |  |  | GC |  |  | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 workplan | 2021-07-06 |  | 110.1 | 70000 | 2021 |  |  |  | 2649841.53 |  | 2649841.53 |  |  | 2021-12-31 | ESTS |  | 2021-07-06 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-03-04 15:14 | Mueller, Bret Charles | M4JQ | 2021-03-03 15:27 | James, Matthew
51562 | Budget change | 35226846 | 120448989 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Approved | 08W |  |  |  | GC |  |  | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 workplan | 2021-08-09 |  | 130.1 | 70000 | 2021 |  |  |  | 3089168.45 |  | 3089168.45 |  |  | 2021-12-31 | ESTS |  | 2021-08-09 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-03 17:48 | Saraf, Shubham | M4JQ | 2021-03-03 09:17 | James, Matthew
51541 | Budget change | 35223343 | 120255838 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Approved | 08W |  |  |  | GC |  |  | Requesting 2021 Budget to cover the budget for UG construction for 2021 for North Complex Fire Rebuild | 2021-06-28 |  | 80 | 950000 | 2021 |  |  |  | 3490209.3 | 0 | 3490209.3 | 0 | 0 | 2021-12-31 | ESTS |  | 2021-06-28 | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-03 17:48 | Saraf, Shubham | ZXAC | 2021-03-02 14:44 | Al-Saffar, Zaid Dhafer Hashim
51540 | Budget change | 35225821 | 120424578 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Approved | 08W |  |  |  | GC |  |  | Requesting 2021 Budget to cover the budget for UG construction for 2021 for North Complex Fire Rebuild | 2021-07-05 |  | 80 | 950000 | 2021 |  |  |  | 3490167.5 | 0 | 3490167.5 | 0 | 0 | 2021-12-31 | ESTS |  | 2021-07-05 | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-03 17:48 | Saraf, Shubham | ZXAC | 2021-03-02 14:44 | Al-Saffar, Zaid Dhafer Hashim
51514 | Budget change | 35094513 | 114567769 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Approved | 08W |  |  |  | Contract |  |  | Project pulled into the 2021 workplan, approved by Wildfire Governanace Ciommittee | 2021-12-30 |  | 1781.5 | 3142865.56 | 2021 |  |  | 48176.5 | 4178901 |  | 4178901 |  |  | 2021-12-20 | PEND |  | 2021-12-30 | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-03 17:48 | Saraf, Shubham | T1DA | 2021-03-02 11:50 | Daugherty, Tracy
51396 | Update work plan date | 35174479 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Approved | 08W | [6 empty] | Request change in project work plan date as project was recently approved by the WFGC to pull into 2021. | 2022-12-31 | 2021-12-31 |  |  | 2021 | 2021 | [8 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-08 15:25 | Saraf, Shubham | AXYX | 2021-03-01 20:01 | Yuen, Aaron Ho
51374 | Add project | 35114051 |  | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Approved | 08W | [6 empty] | Per Bradk Koelling, this project was approved to continue executing on 2/25/21. | 2021-06-30 | [5 empty] | 2021 |  |  |  | 2575321 |  |  |  | CONS |  |  | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | J1PE | 2021-03-01 10:02 | Pantoja-Martinez, Jaime
51211 | Update work plan date | 35192280 | 119556070 | ECOP - CLAYTON 2212 - H01-LR2951 | Approved | 08W |  |  |  | GC |  |  | 2021 not realistic with 1.64 miles of UG with new lands rights. Defer project to 2022 | 2022-06-22 | 2022-05-01 | 180 | 550000 | 2021 | 2022 | 2022 |  |  |  | 852800 | 2984800 | 426400 | 2023-12-31 | UNSE |  | 2022-06-22 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Defer approved, GC notified | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-03-19 19:59 | Saraf, Shubham | M1NO | 2021-02-25 14:53 | Nguyen, My-Linh
51072 | Resource change | 35192290 | 119556075 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Approved | 08W |  |  |  | Contract |  | GC | 2.25 Update Resource to GC | 2021-06-29 |  | 80 | 1 | 2021 | [8 empty] | 2023-12-31 | ESTS |  | 2021-06-29 | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51073 | Resource change | 35192291 | 119556091 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Approved | 08W |  |  |  | Contract |  | GC | 2.25 Update Resource to GC | 2022-03-02 |  | 80 | 1 | 2021 | 2022 | [7 empty] | 2023-12-31 | UNSE |  | 2022-03-02 | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51129 | Resource change | 35225824 | 120424703 | FRRB - WYANDOTTE 1103 - HWY 162 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-04-05 |  | 1434.6 | 11016312 | 2021 |  |  |  | 8094904 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-04-05 | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51077 | Resource change | 35226622 | 120445225 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-08-17 |  | 111.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | ESTS |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51076 | Resource change | 35226621 | 120445224 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-12-15 |  | 111.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2021-12-15 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51078 | Resource change | 35226623 | 120445227 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-08-17 |  | 111.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51079 | Resource change | 35226624 | 120445228 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-08-17 |  | 111.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51126 | Resource change | 35223344 | 120255980 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-02-12 |  | 1781.8 | 10286697 | 2021 |  |  |  | 6324922 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-02-12 | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51127 | Resource change | 35223345 | 120255982 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-02-16 |  | 2963.2 | 10700839 | 2021 |  |  |  | 9514299.24 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-02-16 | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51113 | Resource change | 35219260 | 120141880 | CWSP - WYANDOTTE 110932586 PH 1.1 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC |  |  | 31.1 | 300000 | 2021 | 2021 |  |  | 1520000 |  |  |  |  | 2021-12-31 | ADER |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51071 | Resource change | 35219273 | 120142173 | CWSP - VOLTA 110149742 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-09-06 |  | 1750.1 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-09-06 | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51075 | Resource change | 35220895 | 120221891 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-08-17 |  | 111.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51116 | Resource change | 35232280 | 120527401 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-06-10 |  | 741 | 465706.54 | 2021 | 2021 | [7 empty] | 2021-12-31 | PEND |  | 2021-06-10 | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51105 | Resource change | 35229119 | 120496477 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-10-15 |  | 110.1 | 475000 | 2021 | 2021 | [7 empty] | 2021-12-31 | ESTS |  | 2021-10-15 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51103 | Resource change | 35228187 | 120475324 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-08-17 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | ESTS |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51104 | Resource change | 35228188 | 120475326 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-08-25 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | ESTS |  | 2021-08-25 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51102 | Resource change | 35228186 | 120475322 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-11-24 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2021-11-24 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51094 | Resource change | 35227860 | 120462186 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-08-17 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | ESTS |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51095 | Resource change | 35227861 | 120462188 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-08-18 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | ESTS |  | 2021-08-18 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51096 | Resource change | 35227862 | 120462232 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-08-17 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | ESTS |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51097 | Resource change | 35227863 | 120462233 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-08-17 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | ESTS |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51098 | Resource change | 35227864 | 120462234 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-11-24 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2021-11-24 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51099 | Resource change | 35227866 | 120462238 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-08-17 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | ESTS |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51100 | Resource change | 35227867 | 120462241 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-08-17 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | ESTS |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51101 | Resource change | 35227868 | 120462242 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-08-17 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51080 | Resource change | 35227027 | 120449717 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-08-17 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51081 | Resource change | 35227028 | 120449719 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-08-18 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | ESTS |  | 2021-08-18 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51082 | Resource change | 35227029 | 120449800 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-07-27 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | ESTS |  | 2021-07-27 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51083 | Resource change | 35227030 | 120449801 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-08-17 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51084 | Resource change | 35227031 | 120449802 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-08-17 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2021-08-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51085 | Resource change | 35226819 | 120456652 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-12-27 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2021-12-27 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51087 | Resource change | 35227161 | 120456654 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-12-27 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2021-12-27 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51086 | Resource change | 35227160 | 120456653 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2022-01-17 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2022-01-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51093 | Resource change | 35227168 | 120456742 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2022-01-17 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2022-01-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51091 | Resource change | 35227165 | 120456740 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2022-01-17 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2022-01-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51092 | Resource change | 35227167 | 120456741 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2022-01-17 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2022-01-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51089 | Resource change | 35227163 | 120456657 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-12-27 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2021-12-27 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51088 | Resource change | 35227162 | 120456655 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-12-27 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2021-12-27 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51090 | Resource change | 35227164 | 120456658 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-12-27 |  | 110.1 | 1 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2021-12-27 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51074 | Resource change | 35062374 | 115323920 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2021-09-24 |  | 31.1 | 220000 | 2021 | 2022 |  | 365.3 | 153434.85 |  |  |  |  | 2020-12-31 | UNSE |  | 2021-09-24 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51058 | Resource change | 35217272 | 120048018 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Approved | 08W |  |  |  | GC |  | GC | 2.25 Update Resource to GC | 2022-06-20 |  | 110.1 | 150000 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-06-20 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:22 | Pereyda, Jessica Ann Hiroko
51046 | Resource change | 35223615 | 120401360 | ECOP - LAS GALLINAS A 1105 PH 2 | Approved | 08W |  |  |  | Contract |  | Contract | 2.25 Resource Update to Contract | 2021-12-13 |  | 83 | 312500 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-12-13 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:11 | Pereyda, Jessica Ann Hiroko
51045 | Resource change | 35191319 | 119518398 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Approved | 08W |  |  |  | Contract |  | Contract | 2.25 Resource Update to Contract | 2021-11-01 |  | 80 | 312500 | 2021 | [8 empty] | 2023-12-31 | UNSE |  | 2021-11-01 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 11:22 | Mueller, Bret Charles | JUPX | 2021-02-25 10:11 | Pereyda, Jessica Ann Hiroko
50828 | Budget change | 35219275 | 120142210 | CWSP - PUTAH CREEK 110246012 | Approved | 08W |  |  |  | GC |  |  | Respectfully request MPP Budget Approved 2021 for $950k. This project is currently on the WP 2021. | 2021-06-30 |  | 832.6 | 656614.03 | 2021 |  |  |  | 950000 | 0 | 950000 | 0 | 0 | 2021-12-31 | PEND |  | 2021-06-30 | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 16:22 | Mueller, Bret Charles | L3WA | 2021-02-24 15:34 | Ward, Laree
50827 | Budget change | 35219291 | 120141627 | CWSP - VACA DIXON 1101126774 | Approved | 08W |  |  |  | GC |  |  | Respectfully request MPP Budget Approved 2021 for $1.2M. This project is currently on the WP 2021. Business case to be routed next month. | 2021-06-22 |  | 421.2 | 165125.99 | 2021 | 2022 |  |  | 1265910 | 0 | 1265910 | 0 | 0 | 2021-12-31 | PEND |  | 2021-06-22 | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 16:22 | Mueller, Bret Charles | L3WA | 2021-02-24 15:34 | Ward, Laree
50654 | Add project | 35233306 |  | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Approved | 08W | [6 empty] | adding this project to 2021 as part of NCFR | 2021-12-31 | [13 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | ZXAC | 2021-02-23 14:12 | Al-Saffar, Zaid Dhafer Hashim
50650 | Add project | 35233306 |  | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Approved | 08W | [6 empty] | adding this project as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | ZXAC | 2021-02-23 14:06 | Al-Saffar, Zaid Dhafer Hashim
50651 | Add project | 35233307 |  | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Approved | 08W | [6 empty] | adding this project as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | ZXAC | 2021-02-23 14:06 | Al-Saffar, Zaid Dhafer Hashim
50652 | Add project | 35233308 |  | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Approved | 08W | [6 empty] | adding this project as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | ZXAC | 2021-02-23 14:06 | Al-Saffar, Zaid Dhafer Hashim
50653 | Add project | 35233309 |  | FRRB - WYANDOTTE 1103 - W1 PH1.13 | Approved | 08W | [6 empty] | adding this project as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | ZXAC | 2021-02-23 14:06 | Al-Saffar, Zaid Dhafer Hashim
50634 | Add project | 35232298 |  | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | ZXAC | 2021-02-23 13:48 | Al-Saffar, Zaid Dhafer Hashim
50637 | Add project | 35233300 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | ZXAC | 2021-02-23 13:48 | Al-Saffar, Zaid Dhafer Hashim
50639 | Add project | 35233302 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | ZXAC | 2021-02-23 13:48 | Al-Saffar, Zaid Dhafer Hashim
50641 | Add project | 35233304 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | ZXAC | 2021-02-23 13:48 | Al-Saffar, Zaid Dhafer Hashim
50642 | Add project | 35233305 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | ZXAC | 2021-02-23 13:48 | Al-Saffar, Zaid Dhafer Hashim
50646 | Add project | 35233309 |  | FRRB - WYANDOTTE 1103 - W1 PH1.13 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | ZXAC | 2021-02-23 13:48 | Al-Saffar, Zaid Dhafer Hashim
50647 | Add project | 35233310 |  | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | ZXAC | 2021-02-23 13:48 | Al-Saffar, Zaid Dhafer Hashim
50635 | Add project | 35233038 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | ZXAC | 2021-02-23 13:48 | Al-Saffar, Zaid Dhafer Hashim
50636 | Add project | 35233039 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | ZXAC | 2021-02-23 13:48 | Al-Saffar, Zaid Dhafer Hashim
50644 | Add project | 35233307 |  | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | ZXAC | 2021-02-23 13:48 | Al-Saffar, Zaid Dhafer Hashim
50638 | Add project | 35233301 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | ZXAC | 2021-02-23 13:48 | Al-Saffar, Zaid Dhafer Hashim
50640 | Add project | 35233303 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | ZXAC | 2021-02-23 13:48 | Al-Saffar, Zaid Dhafer Hashim
50643 | Add project | 35233306 |  | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | ZXAC | 2021-02-23 13:48 | Al-Saffar, Zaid Dhafer Hashim
50645 | Add project | 35233308 |  | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | ZXAC | 2021-02-23 13:48 | Al-Saffar, Zaid Dhafer Hashim
50625 | Budget change | 35217268 | 120047659 | CWSP - BUCKS CREEK 1101 CB PH 1 | Approved | 08W |  |  |  | GC |  |  | Requesting $150k for 2021 to cover Estimating and dependency work | 2021-09-22 |  | 690.1 | 150000 | 2021 |  |  |  | 380000 | 0 | 150000 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-09-22 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 16:22 | Mueller, Bret Charles | ZXAC | 2021-02-23 11:16 | Al-Saffar, Zaid Dhafer Hashim
50624 | Budget change | 35224713 | 120427329 | CWSP - BUCKS CREEK 1101 CB PH 3 | Approved | 08W |  |  |  | GC |  |  | Requesting $400k for 2021 to cover Estimating and dependency work | 2022-03-02 |  | 132 | 400000 | 2021 | 2022 |  |  | 400000 | 0 | 400000 | 0 | 0 | 2021-12-31 | UNSE |  | 2022-03-02 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 16:22 | Mueller, Bret Charles | ZXAC | 2021-02-23 11:15 | Al-Saffar, Zaid Dhafer Hashim
50623 | Budget change | 35224712 | 120427328 | CWSP - BUCKS CREEK 1101 CB PH 2 | Approved | 08W |  |  |  | GC |  |  | Requesting $400k for 2021 to cover Estimating and dependency work | 2022-03-02 |  | 132 | 400000 | 2021 | 2022 |  |  | 400000 | 0 | 400000 | 0 | 0 | 2021-12-31 | UNSE |  | 2022-03-02 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | BCMK | 2021-02-25 16:22 | Mueller, Bret Charles | ZXAC | 2021-02-23 11:15 | Al-Saffar, Zaid Dhafer Hashim
50586 | Budget change | 35116443 |  | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Approved | 08W | [6 empty] | Respectfully request $22k to be moved into the MPP Approved Budget 2021, due to a late invoice coming in. | [9 empty] | 0 | 22000 | 194071 |  |  | CONS |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-22 14:11 | Saraf, Shubham | L3WA | 2021-02-22 09:09 | Ward, Laree
50566 | Add project | 35226862 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50563 | Add project | 35226858 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50569 | Add project | 35227010 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50567 | Add project | 35174501 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50578 | Add project | 35223039 |  | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50573 | Add project | 35227021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50583 | Add project | 35231544 |  | CWSP - TIDEWATER 210614072 PH 1.3 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | ESTS |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50579 | Add project | 35219096 |  | CWSP - KIRKER 2104442850 PH 1.1 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50582 | Add project | 35231543 |  | CWSP - TIDEWATER 210614072 PH 1.2 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50580 | Add project | 35227655 |  | CWSP - KIRKER 2104442850 PH 1.2 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50564 | Add project | 35226859 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50570 | Add project | 35227013 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50574 | Add project | 35227025 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50575 | Add project | 35191937 |  | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | ESTS |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50562 | Add project | 35226857 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50571 | Add project | 35227015 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50577 | Add project | 35227033 |  | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50581 | Add project | 35219093 |  | CWSP - TIDEWATER 210614072 PH 1.1 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50565 | Add project | 35226861 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50568 | Add project | 35227007 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50572 | Add project | 35227018 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | SFMT | Moraga, Steven | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50576 | Add project | 35227032 |  | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | ESTS |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50561 | Add project | 35174478 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | AXYX | 2021-02-20 15:21 | Yuen, Aaron Ho
50501 | Resource change | 35226241 | 120431331 | CWSP - MARIPOSA 210197142 PH 2 | Approved | 08W |  |  |  | GC |  | GC | Resource Change - Assigned to GC | 2021-09-20 |  | 1742.6 | 485124.83 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-09-20 | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-22 14:11 | Saraf, Shubham | M117 | 2021-02-19 14:02 | Munkhbaatar, Munkhjin
50502 | Resource change | 35226240 | 120431332 | CWSP - MARIPOSA 210197142 PH 3 | Approved | 08W |  |  |  | GC |  | GC | Resource Change - Assigned to GC | 2021-06-08 |  | 1336.8 | 655862.69 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-06-08 | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-22 14:11 | Saraf, Shubham | M117 | 2021-02-19 14:02 | Munkhbaatar, Munkhjin
50500 | Resource change | 35219268 | 120142035 | CWSP - MARIPOSA 210197142 PH 1 | Approved | 08W |  |  |  | GC |  | GC | Resource Change - Assigned to GC | 2021-09-14 |  | 3531.3 | 1289702.13 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-09-14 | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-22 14:11 | Saraf, Shubham | M117 | 2021-02-19 14:02 | Munkhbaatar, Munkhjin
50498 | Resource change | 35217267 | 120047657 | TITLE: SH - MARIPOSA 2102 LR 241564 | Approved | 08W |  |  |  | GC |  | GC | Resource Change - Assigned to GC | 2021-06-22 |  | 80 | 1 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-06-22 | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-22 14:11 | Saraf, Shubham | M117 | 2021-02-19 14:02 | Munkhbaatar, Munkhjin
50376 | Budget change | 35103065 | 114592041 | CWSP - MORAGA 1101 - LR 108540 PH 1 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Negative 2021 budget not correct. Updating to $1 for 2020 project (couldn't use $0) | 2019-12-18 |  | 2738.3 | 5151555 | 2020 |  |  | 241010.3 | -37865.9 |  | 0 | 1 |  | 2020-12-31 | FICL | 2019-12-18 |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-22 14:11 | Saraf, Shubham | M1NO | 2021-02-19 10:34 | Nguyen, My-Linh
50374 | Budget change | 74022384 | 114753320 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Updating 2021 Budget to complete project and close out. | 2020-06-08 |  | 8146.2 | 9998553 | 2020 | 2021 |  | 6860373.1 | 2395900 |  | 2395900 | 1 |  | 2020-12-31 | CONS |  | 2020-06-08 | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-22 14:11 | Saraf, Shubham | M1NO | 2021-02-19 10:34 | Nguyen, My-Linh
50377 | Budget change | 35053033 | 114688204 | CWSP - TASSAJARA 2112 - FUSE 18053 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Updating 2021 Budget for project close out. | 2019-12-03 |  | 11746.9 | 9709000 | 2020 |  |  | 5741528.5 | 368855 |  | 368855 | 1 |  | 2019-12-31 | FICL | 2021-01-13 | 2019-12-03 | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-22 14:11 | Saraf, Shubham | M1NO | 2021-02-19 10:22 | Nguyen, My-Linh
50375 | Update work plan date | 35192280 | 119556070 | ECOP - CLAYTON 2212 - H01-LR2951 | Denied | 08W |  |  |  | GC |  |  | 2021 not realistic with 1.64 miles of UG with new lands rights | 2022-06-22 | 2021-05-01 | 180 | 550000 | 2021 | 2022 | [7 empty] | 2023-12-31 | UNSE |  | 2022-06-22 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Denied | Hi My-Linh and Merih, There is update date request in queue for the 08W job below. I'm not clear on the ask: note says "2021 not realistic with 1.64 miles of UG with new lands rights" and updated work plan date is earlier in 2021 than previous date. Please reply back with: 1. Correct Updated Work Plan Date 2. Construction Complete Year Order Notification Order Description 35192280 119556070 ECOP - CLAYTON 2212 - H01-LR2951 Going forward, please ensure that the notes align with the request and the minimum info above is provided. Thanks, Bret | BCMK | 2021-03-08 16:53 | Mueller, Bret Charles | M1NO | 2021-02-19 10:20 | Nguyen, My-Linh
50371 | Add project | 35219291 |  | CWSP - VACA DIXON 1101126774 | Approved | 08W | [6 empty] | Add to MPP | 2022-02-23 | [13 empty] | PEND |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | L3WA | 2021-02-18 16:55 | Ward, Laree
50370 | Add project | 35219275 |  | CWSP - PUTAH CREEK 110246012 | Approved | 08W | [6 empty] | Add project to MPP | 2021-12-09 | [13 empty] | PEND |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-02-25 16:47 | Mueller, Bret Charles | L3WA | 2021-02-18 16:49 | Ward, Laree
50315 | Resource change | 35062375 | 115323921 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2022-01-04 |  | 131.1 | 1 | 2021 | 2022 |  | 58.9 | [5 empty] | 2020-12-31 | UNSE |  | 2022-01-04 | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50316 | Resource change | 35062376 | 115323922 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-08-10 |  | 131.1 | 220000 | 2021 | 2022 |  | 22.4 | 364360.62 |  |  |  |  | 2020-12-31 | UNSE |  | 2021-08-10 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50280 | Resource change | 35217268 | 120047659 | CWSP - BUCKS CREEK 1101 CB PH 1 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-09-22 |  | 690.1 | 150000 | 2021 |  |  |  | 380000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-09-22 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50329 | Resource change | 35192292 | 119556108 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2022-01-03 |  | 50.1 | 950000 | 2021 | 2022 | [7 empty] | 2023-12-31 | ESTS |  | 2022-01-03 | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50276 | Resource change | 35219272 | 120142171 | CWSP - MIDDLETOWN 1101481876 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-07-21 |  | 130.1 | 950000 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-07-21 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50289 | Resource change | 35219275 | 120142210 | CWSP - PUTAH CREEK 110246012 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-06-30 |  | 832.6 | 656614.03 | 2021 |  |  |  | 950000 |  |  |  |  | 2021-12-31 | PEND |  | 2021-06-30 | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50275 | Resource change | 35219098 | 120141805 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-10-21 |  | 130.1 | 475000 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-10-21 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50277 | Resource change | 35219280 | 120142216 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-08-25 |  | 130.1 | 475000 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-08-25 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50288 | Resource change | 35219291 | 120141627 | CWSP - VACA DIXON 1101126774 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-06-22 |  | 421.2 | 165125.99 | 2021 | 2022 |  |  | 1265910 |  |  |  |  | 2021-12-31 | PEND |  | 2021-06-22 | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50279 | Resource change | 35217273 | 120048019 | SH - UPPER LAKE 1101 CB | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-12-16 |  | 80 | 500000 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-12-16 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50271 | Resource change | 35217270 | 120048013 | CWSP - KONOCTI 1102 LR 965078 PH1 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-11-17 |  | 130.1 | 316666 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-11-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50272 | Resource change | 35225589 | 120423768 | CWSP - KONOCTI 1102 LR 965078 PH2 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-10-20 |  | 131.1 | 316666 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-10-20 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50273 | Resource change | 35225591 | 120423769 | CWSP - KONOCTI 1102 LR 965078 PH3 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-07-28 |  | 131.1 | 316666 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-07-28 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50330 | Resource change | 35225594 | 120424183 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2022-01-03 |  | 50.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2022-01-03 | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50331 | Resource change | 35225595 | 120424186 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-09-28 |  | 50.1 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-09-28 | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50332 | Resource change | 35225597 | 120424187 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-08-31 |  | 40 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-08-31 | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50333 | Resource change | 35225598 | 120424188 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-09-28 |  | 50.1 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-09-28 | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50282 | Resource change | 35224713 | 120427329 | CWSP - BUCKS CREEK 1101 CB PH 3 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2022-03-02 |  | 132 | 400000 | 2021 | 2022 |  |  | 400000 |  |  |  |  | 2021-12-31 | UNSE |  | 2022-03-02 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50281 | Resource change | 35224712 | 120427328 | CWSP - BUCKS CREEK 1101 CB PH 2 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2022-03-02 |  | 132 | 400000 | 2021 | 2022 |  |  | 400000 |  |  |  |  | 2021-12-31 | UNSE |  | 2022-03-02 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50278 | Resource change | 35226632 | 120445424 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2022-01-17 |  | 130.1 | 475000 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2022-01-17 | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50319 | Resource change | 35226847 | 120449140 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-08-09 |  | 130.1 | 70000 | 2021 |  |  |  | 3812484.87 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-08-09 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50320 | Resource change | 35226848 | 120449141 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-07-22 |  | 130.1 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-07-22 | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50321 | Resource change | 35226849 | 120449142 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-12-08 |  | 130.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2021-12-08 | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50322 | Resource change | 35226850 | 120449143 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-07-06 |  | 130.1 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-07-06 | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50323 | Resource change | 35226851 | 120449144 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-08-23 |  | 130.1 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-08-23 | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50324 | Resource change | 35226852 | 120449145 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-08-09 |  | 130.1 | 70000 | 2021 |  |  |  | 7975840.77 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-08-09 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50318 | Resource change | 35226846 | 120448989 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-08-09 |  | 130.1 | 70000 | 2021 |  |  |  | 3089168.45 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-08-09 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50327 | Resource change | 35226856 | 120449149 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-07-07 |  | 130.1 | 70000 | 2021 |  |  |  | 8862572.16 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-07-07 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50325 | Resource change | 35226853 | 120449146 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-07-05 |  | 130.1 | 70000 | 2021 |  |  |  | 5802223.75 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-07-05 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50326 | Resource change | 35226854 | 120449147 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Approved | 08W |  |  |  | GC |  | GC | 2.18 Resource Update to GC | 2021-07-08 |  | 130.1 | 70000 | 2021 |  |  |  | 2086816.03 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-07-08 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:18 | Pereyda, Jessica Ann Hiroko
50167 | Resource change | 35228449 | 120481753 | RIO DELL STORM REBUILD | Denied | 08W |  |  |  | Contract |  | Contract | 2.18 Resource Update to Contract | 2021-02-08 |  | 2388.1 | 6518166 | 2021 | [8 empty] | 2021-06-30 | DOCC | 2021-03-01 | 2021-02-08 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Denied | Duplicate of Change ID 50144 | SFSS | 2021-02-19 00:07 | Saraf, Shubham | JUPX | 2021-02-18 10:07 | Pereyda, Jessica Ann Hiroko
50154 | Resource change | 35223028 | 120245193 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Denied | 08W |  |  |  | Contract |  | Contract | 2.18 Resource Update to Contract | 2021-12-31 |  | 3 | 190000 | 2021 | [8 empty] | 2021-12-31 | ESTS |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Denied | Duplicate of Change ID 50131 | SFSS | 2021-02-19 00:07 | Saraf, Shubham | JUPX | 2021-02-18 10:07 | Pereyda, Jessica Ann Hiroko
50152 | Resource change | 35223026 | 120245190 | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | Denied | 08W |  |  |  | Contract |  | Contract | 2.18 Resource Update to Contract | 2021-08-31 |  | 640 |  | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-08-31 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Denied | Duplicate of Change ID 50129 | SFSS | 2021-02-19 00:07 | Saraf, Shubham | JUPX | 2021-02-18 10:07 | Pereyda, Jessica Ann Hiroko
50153 | Resource change | 35223027 | 120245192 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Denied | 08W |  |  |  | Contract |  | Contract | 2.18 Resource Update to Contract | 2021-08-23 |  | 640 | 190000 | 2021 | [8 empty] | 2021-12-31 | APPR |  | 2021-08-23 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Denied | Duplicate of Change ID 50130 | SFSS | 2021-02-19 00:07 | Saraf, Shubham | JUPX | 2021-02-18 10:07 | Pereyda, Jessica Ann Hiroko
50151 | Resource change | 35223024 | 120245076 | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | Denied | 08W |  |  |  | Contract |  | Contract | 2.18 Resource Update to Contract | 2021-09-14 |  | 640 |  | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-09-14 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Denied | Duplicate of Change ID 50128 | SFSS | 2021-02-19 00:07 | Saraf, Shubham | JUPX | 2021-02-18 10:07 | Pereyda, Jessica Ann Hiroko
50150 | Resource change | 35192284 | 119556691 | ECOP - SILVERADO 2104 - H05-LR726 | Denied | 08W |  |  |  | Contract |  | Contract | 2.18 Resource Update to Contract | 2021-08-24 |  | 80 | 190000 | 2021 | [8 empty] | 2023-12-31 | UNSE |  | 2021-08-24 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Denied | Duplicate of Change ID 50127 | SFSS | 2021-02-19 00:08 | Saraf, Shubham | JUPX | 2021-02-18 10:07 | Pereyda, Jessica Ann Hiroko
50156 | Resource change | 35191383 | 119518528 | ECOP - SILVERADO 2102 - H01-LR58626 | Denied | 08W |  |  |  | Contract |  | Contract | 2.18 Resource Update to Contract | 2021-08-16 |  | 869.7 | 415256.78 | 2021 | [8 empty] | 2023-12-31 | PEND |  | 2021-08-16 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Denied | Duplicate of Change ID 50133 | SFSS | 2021-02-19 00:08 | Saraf, Shubham | JUPX | 2021-02-18 10:07 | Pereyda, Jessica Ann Hiroko
50155 | Resource change | 35191318 | 119518390 | ECOP - SILVERADO 2102 - H02-LR58626 | Denied | 08W |  |  |  | Contract |  | Contract | 2.18 Resource Update to Contract | 2021-07-16 |  | 80 | 682400 | 2021 | [8 empty] | 2022-12-31 | ESTS |  | 2021-07-16 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Denied | Duplicate of Change ID 50132 | SFSS | 2021-02-19 00:08 | Saraf, Shubham | JUPX | 2021-02-18 10:07 | Pereyda, Jessica Ann Hiroko
50132 | Resource change | 35191318 | 119518390 | ECOP - SILVERADO 2102 - H02-LR58626 | Approved | 08W |  |  |  | Contract |  | Contract | 2.18 Resource Updates | 2021-07-16 |  | 80 | 682400 | 2021 | [8 empty] | 2022-12-31 | ESTS |  | 2021-07-16 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:00 | Pereyda, Jessica Ann Hiroko
50133 | Resource change | 35191383 | 119518528 | ECOP - SILVERADO 2102 - H01-LR58626 | Approved | 08W |  |  |  | Contract |  | Contract | 2.18 Resource Updates | 2021-08-16 |  | 869.7 | 415256.78 | 2021 | [8 empty] | 2023-12-31 | PEND |  | 2021-08-16 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:00 | Pereyda, Jessica Ann Hiroko
50127 | Resource change | 35192284 | 119556691 | ECOP - SILVERADO 2104 - H05-LR726 | Approved | 08W |  |  |  | Contract |  | Contract | 2.18 Resource Updates | 2021-08-24 |  | 80 | 190000 | 2021 | [8 empty] | 2023-12-31 | UNSE |  | 2021-08-24 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:00 | Pereyda, Jessica Ann Hiroko
50129 | Resource change | 35223026 | 120245190 | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | Approved | 08W |  |  |  | Contract |  | Contract | 2.18 Resource Updates | 2021-08-31 |  | 640 |  | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-08-31 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:00 | Pereyda, Jessica Ann Hiroko
50128 | Resource change | 35223024 | 120245076 | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | Approved | 08W |  |  |  | Contract |  | Contract | 2.18 Resource Updates | 2021-09-14 |  | 640 |  | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-09-14 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:00 | Pereyda, Jessica Ann Hiroko
50131 | Resource change | 35223028 | 120245193 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Approved | 08W |  |  |  | Contract |  | Contract | 2.18 Resource Updates | 2021-12-31 |  | 3 | 190000 | 2021 | [8 empty] | 2021-12-31 | ESTS |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:00 | Pereyda, Jessica Ann Hiroko
50130 | Resource change | 35223027 | 120245192 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Approved | 08W |  |  |  | Contract |  | Contract | 2.18 Resource Updates | 2021-08-23 |  | 640 | 190000 | 2021 | [8 empty] | 2021-12-31 | APPR |  | 2021-08-23 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:00 | Pereyda, Jessica Ann Hiroko
50144 | Resource change | 35228449 | 120481753 | RIO DELL STORM REBUILD | Approved | 08W |  |  |  | Contract |  | Contract | 2.18 Resource Updates | 2021-02-08 |  | 2388.1 | 6518166 | 2021 | [8 empty] | 2021-06-30 | DOCC | 2021-03-01 | 2021-02-08 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | JUPX | 2021-02-18 10:00 | Pereyda, Jessica Ann Hiroko
49792 | Resource change | 35227201 | 120457012 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Approved | 08W |  |  |  | GC |  | GC | Resource Change - Assigned to GC | 2021-02-02 |  | 791.2 | 512371.91 | 2021 |  |  |  | 2080934 |  |  |  |  | 2021-12-31 | CONS |  | 2021-02-02 | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | M117 | 2021-02-17 21:11 | Munkhbaatar, Munkhjin
49791 | Resource change | 35227096 | 120457011 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Approved | 08W |  |  |  | GC |  | GC | Resource Change - Assigned to GC | 2021-02-22 |  | 1203 | 326951.18 | 2021 |  |  |  | 2183706 |  |  |  |  | 2021-12-31 | CONS |  | 2021-02-22 | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | M117 | 2021-02-17 21:11 | Munkhbaatar, Munkhjin
49790 | Resource change | 35192053 | 119554059 | STRM-OAKHURST 1103-LR 5120 PH1 | Approved | 08W |  |  |  | GC |  | GC | Resource Change - Assigned to GC | 2021-02-08 |  | 3504.6 | 1877409.58 | 2021 |  |  |  | 2843023 |  |  |  |  | 2022-12-31 | CONS |  | 2021-02-08 | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-19 00:05 | Saraf, Shubham | M117 | 2021-02-17 21:11 | Munkhbaatar, Munkhjin
49702 | Add project | 35232280 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Approved | 08W | [6 empty] | Approved Scope from WFGC and part of segment for original project order 35062375. | [6 empty] | 2021 | [7 empty] | PEND |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-17 10:09 | Yuen, Aaron Ho
49434 | Add project | 35227201 |  | STRM - OAKHURST 1103 - LR 5120 PH 3 | Approved | 08W | [6 empty] | 08W Fire Hardening Project | 2021-02-22 | [5 empty] | 2021 | [7 empty] | CONS |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | B4HS | 2021-02-16 12:41 | Hayashi, Brandon
49433 | Add project | 35227096 |  | STRM - OAKHURST 1103 - LR 5120 PH 2 | Approved | 08W | [6 empty] | 08W Fire Hardening Project | 2021-02-22 | [5 empty] | 2021 | [7 empty] | CONS |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | B4HS | 2021-02-16 12:41 | Hayashi, Brandon
49432 | Add project | 35192053 |  | STRM-OAKHURST 1103-LR 5120 PH1 | Approved | 08W | [6 empty] | 08W Fire Hardening Project | 2021-02-22 | [5 empty] | 2021 | [7 empty] | CONS |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | B4HS | 2021-02-16 12:41 | Hayashi, Brandon
49421 | Add project | 35227867 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49409 | Add project | 35227261 |  | CWSP - COARSEGOLD 2104CB PH 1.3 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49380 | Add project | 35227027 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49427 | Add project | 35026643 |  | DIAMOND SPRINGS 1105 - LR 2102 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49396 | Add project | 35217269 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49390 | Add project | 35217272 |  | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49386 | Add project | 35226621 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49407 | Add project | 35219097 |  | CWSP - COARSEGOLD 2104CB PH 1.1 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49389 | Add project | 35226624 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49395 | Add project | 35226631 |  | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49412 | Add project | 35226700 |  | CWSP - WYANDOTTE 110932586 PH 1.2 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49398 | Add project | 35227160 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49402 | Add project | 35227164 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49419 | Add project | 35227864 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49423 | Add project | 35220895 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49384 | Add project | 35227031 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49415 | Add project | 35227860 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49387 | Add project | 35226622 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49393 | Add project | 35226629 |  | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49394 | Add project | 35226630 |  | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49425 | Add project | 35228187 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49400 | Add project | 35227162 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49406 | Add project | 35223037 |  | PSPS - OAKHURST 1101 - OAKHURST | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | PEND |  |  | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49381 | Add project | 35227028 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49405 | Add project | 35227168 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49392 | Add project | 35226628 |  | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49401 | Add project | 35227163 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49403 | Add project | 35227165 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49404 | Add project | 35227167 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49408 | Add project | 35227260 |  | CWSP - COARSEGOLD 2104CB PH 1.2 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49410 | Add project | 35227262 |  | CWSP - COARSEGOLD 2104CB PH 1.4 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | PEND |  |  | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49411 | Add project | 35219260 |  | CWSP - WYANDOTTE 110932586 PH 1.1 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ADER |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49397 | Add project | 35226819 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49383 | Add project | 35227030 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49399 | Add project | 35227161 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49417 | Add project | 35227862 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49418 | Add project | 35227863 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49424 | Add project | 35228186 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49426 | Add project | 35228188 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49385 | Add project | 35192282 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49416 | Add project | 35227861 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49422 | Add project | 35227868 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49388 | Add project | 35226623 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49391 | Add project | 35226627 |  | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49382 | Add project | 35227029 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49420 | Add project | 35227866 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49414 | Add project | 35217271 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49379 | Add project | 35192281 |  | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-16 10:10 | Yuen, Aaron Ho
49364 | Budget change | 35116391 | 117605551 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Insufficient funds to complete project. Additional funds needed to complete project in 2021, per work plan | 2020-06-22 |  | 2329 | 3920203 | 2020 | 2021 |  | 4125714.8 | 378038 |  | 378038 | 0 | 0 | 2019-12-27 | DOCC | 2021-02-04 | 2020-06-22 | PXSO | Siu, Peter | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-16 21:51 | Saraf, Shubham | PXSO | 2021-02-16 00:21 | Siu, Peter
49363 | Budget change | 35116391 | 117605551 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Denied | 08W | 220 Mile Plan |  |  | Contract |  |  | Insufficient funds to complete project. Additional funds needed to complete project in 2021, per work plan | 2020-06-22 |  | 2329 | 3920203 | 2020 | 2021 |  | 4125714.8 | 378038 |  | 367484 | 0 | 0 | 2019-12-27 | DOCC | 2021-02-04 | 2020-06-22 | PXSO | Siu, Peter | [9 empty] | Merih Tekeste |  |  |  | Denied | corrected budget on change ID 49364 | SFSS | 2021-02-16 21:55 | Saraf, Shubham | PXSO | 2021-02-16 00:13 | Siu, Peter
49107 | Resource change | 35217275 | 120048103 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Approved | 08W |  |  |  | Contract |  | Contract | Resource Change - Contract | 2022-09-21 |  | 80 | 500000 | 2021 |  |  |  | 10150000 |  |  |  |  | 2021-12-31 | UNSE |  | 2022-09-21 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-16 21:51 | Saraf, Shubham | M117 | 2021-02-12 16:12 | Munkhbaatar, Munkhjin
49106 | Resource change | 35217274 | 120048101 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Approved | 08W |  |  |  | Contract |  | Contract | Resource Change - Contract | 2022-09-21 |  | 80 | 500000 | 2021 |  |  |  | 7805000 |  |  |  |  | 2021-12-31 | UNSE |  | 2022-09-21 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-16 21:51 | Saraf, Shubham | M117 | 2021-02-12 16:12 | Munkhbaatar, Munkhjin
49101 | Resource change | 35075103 | 116475141 | FROGTOWN 1701 TIER 2 RECOND - FUSE L2969 | Approved | 08W |  |  |  | Contract |  | Contract | Resource Change - Assigned to Contract | 2021-06-02 |  | 686.3 | 403045.55 | 2021 |  |  |  | 490994.6 |  |  |  |  | 2020-12-30 | PEND |  | 2021-06-02 | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-16 21:51 | Saraf, Shubham | M117 | 2021-02-12 12:02 | Munkhbaatar, Munkhjin
49096 | Resource change | 35225593 | 120424181 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Approved | 08W |  |  |  | GC |  | GC | Resource Change - Assigned to GC | 2021-08-11 |  | 1076.2 | 535717.12 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-08-11 | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-16 21:51 | Saraf, Shubham | M117 | 2021-02-12 11:52 | Munkhbaatar, Munkhjin
49071 | Add project | 35231608 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Approved | 08W | [6 empty] | Additonal suborders created for WFGC approved segements under CWSP - SHINGLE SPRINGS 2109-LR 9372. Requesting to add to 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-11 13:20 | Yuen, Aaron Ho
49072 | Add project | 35231609 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Approved | 08W | [6 empty] | Additonal suborders created for WFGC approved segements under CWSP - SHINGLE SPRINGS 2109-LR 9372. Requesting to add to 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-11 13:20 | Yuen, Aaron Ho
49070 | Add project | 35231607 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Approved | 08W | [6 empty] | Additonal suborders created for WFGC approved segements under CWSP - SHINGLE SPRINGS 2109-LR 9372. Requesting to add to 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-11 13:20 | Yuen, Aaron Ho
48887 | Add project | 35229119 |  | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Approved | 08W | [6 empty] | Project is a segement of order 35219098 which was previously approved by the WFGC and requesting to add to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-19 00:11 | Saraf, Shubham | AXYX | 2021-02-11 10:02 | Yuen, Aaron Ho
48877 | Resource change | 35228449 | 120481753 | RIO DELL STORM REBUILD | Approved | 08W |  |  |  | Contract |  | GC | 2.10 Resource Update to GC p/Cathy Fernandez | 2021-02-08 |  | 2388.1 | 6518166 | 2021 | [8 empty] | 2021-06-30 | DOCC | 2021-03-01 | 2021-02-08 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-11 16:10 | Saraf, Shubham | JUPX | 2021-02-10 22:55 | Pereyda, Jessica Ann Hiroko
47375 | Budget change | 35225824 | 120424703 | FRRB - WYANDOTTE 1103 - HWY 162 | Approved | 08W |  |  |  | GC |  |  | Requesting 2021 Budget for UG main line under North Complex Fire Rebuild | 2021-04-05 |  | 1434.6 | 11016312 | 2021 |  |  |  | 8094904 | 0 | 8053977.27 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-04-05 | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-09 11:28 | Saraf, Shubham | ZXAC | 2021-02-08 13:28 | Al-Saffar, Zaid Dhafer Hashim
47374 | Budget change | 35225823 | 120424672 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Approved | 08W |  |  |  | GC |  |  | Requesting 2021 Budget for UG main line under North Complex Fire Rebuild | 2021-05-12 |  | 4018.3 | 6586891 | 2021 |  |  |  | 4901112 | 0 | 4865530.3 | 0 | 0 | 2021-12-31 | CONS |  | 2021-05-12 | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-09 11:28 | Saraf, Shubham | ZXAC | 2021-02-08 13:28 | Al-Saffar, Zaid Dhafer Hashim
47373 | Budget change | 35225822 | 120424579 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Approved | 08W |  |  |  | GC |  |  | Requesting 2021 Budget for UG main line under North Complex Fire Rebuild | 2021-03-01 |  | 2924.8 | 4380690 | 2021 |  |  |  | 3743276.52 | 0 | 3743276.52 | 0 | 0 | 2021-12-31 | CONS |  | 2021-03-01 | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-09 11:28 | Saraf, Shubham | ZXAC | 2021-02-08 13:27 | Al-Saffar, Zaid Dhafer Hashim
47372 | Budget change | 35223345 | 120255982 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Approved | 08W |  |  |  | GC |  |  | Requesting 2021 Budget for UG main line under North Complex Fire Rebuild | 2021-02-16 |  | 2963.2 | 10700839 | 2021 |  |  |  | 9514299.24 | 0 | 9514299.24 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-02-16 | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-09 11:28 | Saraf, Shubham | ZXAC | 2021-02-08 13:27 | Al-Saffar, Zaid Dhafer Hashim
47371 | Budget change | 35223344 | 120255980 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Approved | 08W |  |  |  | GC |  |  | request Budget for 2021 to match with 2021 EAC in BC | 2021-02-12 |  | 1781.8 | 10286697 | 2021 |  |  |  | 6324922 | 0 | 6324922 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-02-12 | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-09 11:28 | Saraf, Shubham | ZXAC | 2021-02-08 13:20 | Al-Saffar, Zaid Dhafer Hashim
47369 | Add project | 35142828 |  | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Denied | 08W | [6 empty] | Project is deffered but still accuring charges that budget is needed to cover | [14 empty] | CONS |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Denied | cannot be added to the plan without approvals from wildfire committee | SFSS | 2021-02-11 20:26 | Saraf, Shubham | T3SQ | 2021-02-08 12:52 | Skarda, Travis Damian
47368 | Add project | 35115152 |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Denied | 08W | [6 empty] | Project is deffered but still accuring charges that budget is needed to cover | [14 empty] | CONS |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Denied | cannot be added to the plan without approvals from wildfire committee | SFSS | 2021-02-11 20:26 | Saraf, Shubham | T3SQ | 2021-02-08 12:52 | Skarda, Travis Damian
47367 | Add project | 35112425 |  | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Approved | 08W | [6 empty] | Close out costs | 2020-05-04 | [9 empty] | 75000 |  |  |  | DOCC | 2020-07-21 |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-17 20:41 | Saraf, Shubham | T3SQ | 2021-02-08 12:48 | Skarda, Travis Damian
45744 | Add project | 35228449 |  | RIO DELL STORM REBUILD | Approved | 08W | [6 empty] | 08W Rebuild projects related to recent windstorm event that meets system hardening criteria for 2021 credit currently under construction. Requesting to be added to 2021 workplan. | [14 empty] | DOCC | 2021-03-01 |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-11 16:10 | Saraf, Shubham | AXYX | 2021-02-05 11:08 | Yuen, Aaron Ho
45743 | Add project | 35227096 |  | STRM - OAKHURST 1103 - LR 5120 PH 2 | Approved | 08W | [6 empty] | 08W Rebuild projects related to recent windstorm event that meets system hardening criteria for 2021 credit currently under construction. Requesting to be added to 2021 workplan. | [14 empty] | CONS |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-11 16:10 | Saraf, Shubham | AXYX | 2021-02-05 11:08 | Yuen, Aaron Ho
45742 | Add project | 35227201 |  | STRM - OAKHURST 1103 - LR 5120 PH 3 | Approved | 08W | [6 empty] | 08W Rebuild projects related to recent windstorm event that meets system hardening criteria for 2021 credit currently under construction. Requesting to be added to 2021 workplan. | [14 empty] | CONS |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-11 16:10 | Saraf, Shubham | AXYX | 2021-02-05 11:08 | Yuen, Aaron Ho
45741 | Add project | 35192053 |  | STRM-OAKHURST 1103-LR 5120 PH1 | Approved | 08W | [6 empty] | 08W Rebuild projects related to recent windstorm event that meets system hardening criteria for 2021 credit currently under construction. Requesting to be added to 2021 workplan. | [14 empty] | CONS |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-11 16:10 | Saraf, Shubham | AXYX | 2021-02-05 11:08 | Yuen, Aaron Ho
44818 | Resource change | 35094513 | 114567769 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Approved | 08W |  |  |  | Contract |  | Contract | Resource Change - Assigned to Contract | 2021-12-30 |  | 1781.5 | 3142865.56 | 2021 |  |  | 48176.5 | 4178901 |  |  |  |  | 2021-12-20 | PEND |  | 2021-12-30 | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-02-06 15:26 | Saraf, Shubham | M117 | 2021-02-04 08:04 | Munkhbaatar, Munkhjin
44669 | Add project | 35224712 |  | CWSP - BUCKS CREEK 1101 CB PH 2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44670 | Add project | 35224713 |  | CWSP - BUCKS CREEK 1101 CB PH 3 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44679 | Add project | 35226849 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | UNSE |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44673 | Add project | 35226845 |  | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS |  |  | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44674 | Add project | 35062374 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | UNSE |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44675 | Add project | 35226846 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44676 | Add project | 35226847 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44677 | Add project | 35062375 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | UNSE |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44678 | Add project | 35226848 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44682 | Add project | 35062376 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | UNSE |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44683 | Add project | 35226852 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44688 | Add project | 35219098 |  | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44667 | Add project | 35225593 |  | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | PEND |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44668 | Add project | 35217268 |  | CWSP - BUCKS CREEK 1101 CB PH 1 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44671 | Add project | 35192290 |  | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS |  |  | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44672 | Add project | 35192291 |  | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | UNSE |  |  | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44680 | Add project | 35226850 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44684 | Add project | 35226853 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | UNSE |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44685 | Add project | 35226854 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44686 | Add project | 35226856 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44687 | Add project | 35075103 |  | FROGTOWN 1701 TIER 2 RECOND - FUSE L2969 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | PEND |  |  | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44681 | Add project | 35226851 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44689 | Add project | 35219272 |  | CWSP - MIDDLETOWN 1101481876 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44690 | Add project | 35219280 |  | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44691 | Add project | 35226632 |  | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44692 | Add project | 35219273 |  | CWSP - VOLTA 110149742 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44693 | Add project | 35219291 |  | CWSP - VACA DIXON 1101126774 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | PEND |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44694 | Add project | 35219266 |  | CWSP - MARIPOSA 2102CB PH 1 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | PEND |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44695 | Add project | 35227263 |  | CWSP - MARIPOSA 2102CB PH 2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | PEND |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
44666 | Add project | 35192280 |  | ECOP - CLAYTON 2212 - H01-LR2951 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-06 15:25 | Saraf, Shubham | AXYX | 2021-02-03 21:27 | Yuen, Aaron Ho
35671 | Add project | 35225821 |  | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Approved | 08W | [6 empty] | UG Mainline North Complex Fire Rebuild | 2021-05-19 | [8 empty] | 0 | 3500000 | 0 | 0 |  | ESTS |  |  | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-02 16:58 | Saraf, Shubham | ZXAC | 2021-02-01 13:40 | Al-Saffar, Zaid Dhafer Hashim
35670 | Add project | 35223343 |  | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Approved | 08W | [6 empty] | UG Mainline North Complex Fire Rebuild | 2021-05-19 | [8 empty] | 0 | 3500000 | 0 | 0 |  | ESTS |  |  | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-02 16:58 | Saraf, Shubham | ZXAC | 2021-02-01 13:40 | Al-Saffar, Zaid Dhafer Hashim
35663 | Add project | 35223345 |  | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Approved | 08W | [6 empty] | UG Mainline part of North Complex Fire Rebuild | 2021-05-03 | [8 empty] | 0 | 9514299.24 | 0 | 0 |  | UNSC |  |  | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-02 16:58 | Saraf, Shubham | ZXAC | 2021-02-01 13:30 | Al-Saffar, Zaid Dhafer Hashim
35664 | Add project | 35225823 |  | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Approved | 08W | [6 empty] | UG Mainline part of North Complex Fire Rebuild | 2021-07-01 | [8 empty] | 0 | 4865530.3 | 0 | 0 |  | CONS |  |  | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-02 16:58 | Saraf, Shubham | ZXAC | 2021-02-01 13:30 | Al-Saffar, Zaid Dhafer Hashim
35665 | Add project | 35225822 |  | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Approved | 08W | [6 empty] | UG Mainline part of North Complex Fire Rebuild | 2021-07-01 | [8 empty] | 0 | 3743276.52 | 0 | 0 |  | CONS |  |  | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-02 16:58 | Saraf, Shubham | ZXAC | 2021-02-01 13:30 | Al-Saffar, Zaid Dhafer Hashim
35666 | Add project | 35225824 |  | FRRB - WYANDOTTE 1103 - HWY 162 | Approved | 08W | [6 empty] | UG Mainline part of North Complex Fire Rebuild | 2021-04-29 | [8 empty] | 0 | 8053977.27 | 0 | 0 |  | UNSC |  |  | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-02 16:58 | Saraf, Shubham | ZXAC | 2021-02-01 13:30 | Al-Saffar, Zaid Dhafer Hashim
35662 | Add project | 35223344 |  | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Approved | 08W | [6 empty] | UG main line under North Complex Fire Rebuild | 2021-03-10 | [8 empty] | 0 | 6000000 | 0 | 0 |  | UNSC |  |  | JTHL | Hembree, Joseph T | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-02 16:58 | Saraf, Shubham | ZXAC | 2021-02-01 13:23 | Al-Saffar, Zaid Dhafer Hashim
32219 | Add project | 35223615 |  | ECOP - LAS GALLINAS A 1105 PH 2 | Approved | 08W | [6 empty] | Add project recently approved by WFGC to bring into 2021 workplan | [14 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-02 16:58 | Saraf, Shubham | AXYX | 2021-01-28 21:18 | Yuen, Aaron Ho
32221 | Add project | 35225589 |  | CWSP - KONOCTI 1102 LR 965078 PH2 | Approved | 08W | [6 empty] | Add project recently approved by WFGC to bring into 2021 workplan | [14 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-02 16:58 | Saraf, Shubham | AXYX | 2021-01-28 21:18 | Yuen, Aaron Ho
32222 | Add project | 35225591 |  | CWSP - KONOCTI 1102 LR 965078 PH3 | Approved | 08W | [6 empty] | Add project recently approved by WFGC to bring into 2021 workplan | [14 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-02 16:58 | Saraf, Shubham | AXYX | 2021-01-28 21:18 | Yuen, Aaron Ho
32220 | Update work plan date | 35217270 |  | CWSP - KONOCTI 1102 LR 965078 PH1 | Withdrawn | 08W | [6 empty] | Add project recently approved by WFGC to bring into 2021 workplan |  | 2021-06-01 |  |  |  |  | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Withdrawn | submitted as add project, changed to update work plan date to move back to 2021 | SFSS | 2021-02-02 16:55 | Saraf, Shubham | AXYX | 2021-01-28 21:18 | Yuen, Aaron Ho
32218 | Update work plan date | 35191319 |  | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Withdrawn | 08W | [6 empty] | Add project recently approved by WFGC to bring into 2021 workplan |  | 2021-06-01 |  |  |  |  | 2021 | [7 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Withdrawn | submitted as add project, changed to update work plan date to move back to 2021 | SFSS | 2021-02-02 16:55 | Saraf, Shubham | AXYX | 2021-01-28 21:18 | Yuen, Aaron Ho
32216 | Add project | 35223027 |  | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Approved | 08W | [6 empty] | Add projects recently approved by the WFGC to the 2021 Workplan | [14 empty] | APPR |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-02 16:58 | Saraf, Shubham | AXYX | 2021-01-28 20:58 | Yuen, Aaron Ho
32217 | Add project | 35223028 |  | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Approved | 08W | [6 empty] | Add projects recently approved by the WFGC to the 2021 Workplan | [14 empty] | ESTS |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-02 16:58 | Saraf, Shubham | AXYX | 2021-01-28 20:58 | Yuen, Aaron Ho
32214 | Add project | 35223024 |  | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | Approved | 08W | [6 empty] | Add projects recently approved by the WFGC to the 2021 Workplan | [14 empty] | UNSE |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-02 16:58 | Saraf, Shubham | AXYX | 2021-01-28 20:58 | Yuen, Aaron Ho
32215 | Add project | 35223026 |  | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | Approved | 08W | [6 empty] | Add projects recently approved by the WFGC to the 2021 Workplan | [14 empty] | UNSE |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-02-02 16:58 | Saraf, Shubham | AXYX | 2021-01-28 20:58 | Yuen, Aaron Ho
32213 | Update work plan date | 35192284 |  | ECOP - SILVERADO 2104 - H05-LR726 | Withdrawn | 08W | [6 empty] | Add projects recently approved by the WFGC to the 2021 Workplan |  | 2021-06-01 |  |  |  |  | 2021 | [7 empty] | UNSE |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Withdrawn | submitted as add project, changed to update work plan date to move back to 2021 | SFSS | 2021-02-02 16:55 | Saraf, Shubham | AXYX | 2021-01-28 20:58 | Yuen, Aaron Ho
31281 | Add project | 35226241 |  | CWSP - MARIPOSA 210197142 PH 2 | Approved | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | PEND |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-01-28 18:17 | Saraf, Shubham | AXYX | 2021-01-25 14:26 | Yuen, Aaron Ho
31282 | Add project | 35226240 |  | CWSP - MARIPOSA 210197142 PH 3 | Approved | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | PEND |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-01-28 18:17 | Saraf, Shubham | AXYX | 2021-01-25 14:26 | Yuen, Aaron Ho
31283 | Add project | 35192292 |  | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Withdrawn | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | ESTS |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste | Approved |  |  | Withdrawn | job already on work plan, manually changed work plan year to 2021 | SFSS | 2021-01-28 18:22 | Saraf, Shubham | AXYX | 2021-01-25 14:26 | Yuen, Aaron Ho
31284 | Add project | 35225594 |  | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Approved | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | ESTS |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-01-28 18:17 | Saraf, Shubham | AXYX | 2021-01-25 14:26 | Yuen, Aaron Ho
31285 | Add project | 35225595 |  | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Approved | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | ESTS |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-01-28 18:17 | Saraf, Shubham | AXYX | 2021-01-25 14:26 | Yuen, Aaron Ho
31286 | Add project | 35225597 |  | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Approved | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | ESTS |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-01-28 18:17 | Saraf, Shubham | AXYX | 2021-01-25 14:26 | Yuen, Aaron Ho
31287 | Add project | 35225598 |  | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Approved | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | ESTS |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-01-28 18:17 | Saraf, Shubham | AXYX | 2021-01-25 14:26 | Yuen, Aaron Ho
31288 | Add project | 35191318 |  | ECOP - SILVERADO 2102 - H02-LR58626 | Withdrawn | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | ESTS |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Withdrawn | job already on work plan, manually changed work plan year to 2021 | SFSS | 2021-01-28 18:22 | Saraf, Shubham | AXYX | 2021-01-25 14:26 | Yuen, Aaron Ho
31289 | Add project | 35191383 |  | ECOP - SILVERADO 2102 - H01-LR58626 | Withdrawn | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | PEND |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Withdrawn | job already on work plan, manually changed work plan year to 2021 | SFSS | 2021-01-28 18:22 | Saraf, Shubham | AXYX | 2021-01-25 14:26 | Yuen, Aaron Ho
31280 | Add project | 35219268 |  | CWSP - MARIPOSA 210197142 PH 1 | Approved | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | PEND |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-01-28 18:17 | Saraf, Shubham | AXYX | 2021-01-25 14:26 | Yuen, Aaron Ho
31279 | Add project | 35219275 |  | CWSP - PUTAH CREEK 110246012 | Approved | 08W | [6 empty] | Requesting project to be added to the 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | PEND |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-01-28 18:17 | Saraf, Shubham | AXYX | 2021-01-25 14:16 | Yuen, Aaron Ho
31278 | Add project | 35217267 |  | TITLE: SH - MARIPOSA 2102 LR 241564 | Withdrawn | 08W | [6 empty] | Requesting project to be added to the 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | PEND |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste | Approved |  |  | Withdrawn | job already on work plan, manually changed work plan year to 2021 | SFSS | 2021-01-28 18:21 | Saraf, Shubham | AXYX | 2021-01-25 14:16 | Yuen, Aaron Ho
31277 | Add project | 35217273 |  | SH - UPPER LAKE 1101 CB | Withdrawn | 08W | [6 empty] | Project to be added to 2021 workplan based on Risk model updates and approved by WFM committee | [14 empty] | UNSE |  |  | P3D5 | Donovan, Patrick | [9 empty] | Merih Tekeste | Approved |  |  | Withdrawn | job already on work plan, manually changed work plan year to 2021 | SFSS | 2021-01-28 18:22 | Saraf, Shubham | AXYX | 2021-01-25 14:04 | Yuen, Aaron Ho
30522 | Budget change | 35109552 | 117348827 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | requesting addational $100k to cover Sierra Springs Owners Association (SSOA) Road Repairs | 2019-10-07 |  | 2699 | 5804263 | 2020 |  |  | 1092828.8 | 175000 | 0 | 175000 | 0 | 0 | 2020-12-30 | DOCC | 2020-02-11 | 2019-10-07 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-20 23:35 | Saraf, Shubham | ZXAC | 2021-01-20 14:05 | Al-Saffar, Zaid Dhafer Hashim
29293 | Update work plan date | 35114044 | 117502841 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Approved by Wildfire Governance Committee for 2021 | 2020-08-12 | 2021-12-31 | 2524.7 | 3012702 | 2020 | 2021 | 2021 | 2235937 | 20105.2 |  |  |  |  | 2019-12-06 | MAPP | 2021-02-25 | 2020-08-12 | A0M6 | Mendez, Angelica | [7 empty] | Approved | Defer approved | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-01-20 09:45 | Saraf, Shubham | J91F | 2021-01-14 09:12 | Stabe, Justin M
29301 | Update work plan date | 35113108 | 117492255 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Approved by Wildfire Governance Committee for 2021 | 2020-08-03 | 2021-12-31 | 1934 | 2054719 | 2020 | 2021 | 2021 | 1139777.4 | 183849 |  |  |  |  | 2020-12-31 | CONS |  | 2020-08-03 | SLKD | Kennedy, Sharon | Critical Work | [6 empty] | Approved | Defer approved | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-01-20 09:45 | Saraf, Shubham | J91F | 2021-01-14 09:12 | Stabe, Justin M
29300 | Update work plan date | 35114103 | 117560686 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Approved by Wildfire Governance Committee for 2021 | 2020-08-03 | 2021-12-31 | 1753 | 2335115 | 2020 | 2021 | 2021 | 2491580.1 | 506601.3 |  |  |  |  | 2020-12-31 | CONS |  | 2020-08-03 | SLKD | Kennedy, Sharon | Critical Work | [6 empty] | Approved | Defer approved | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-01-20 09:45 | Saraf, Shubham | J91F | 2021-01-14 09:12 | Stabe, Justin M
29299 | Update work plan date | 35114102 | 117545619 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Approved by Wildfire Governance Committee for 2021 | 2020-08-04 | 2021-12-31 | 2103 | 1763594 | 2020 | 2021 | 2021 | 1166533.7 | 428517.6 |  |  |  |  | 2020-12-31 | CONS |  | 2020-08-04 | SLKD | Kennedy, Sharon | Critical Work | [6 empty] | Approved | Defer approved | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-01-20 09:45 | Saraf, Shubham | J91F | 2021-01-14 09:12 | Stabe, Justin M
29298 | Update work plan date | 35114049 | 117499469 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Approved by Wildfire Governance Committee for 2021 | 2020-07-21 | 2021-12-31 | 1963.9 | 2193681.27 | 2020 | 2021 | 2021 | 3322836 | 1168197.9 |  |  |  |  | 2021-12-31 | CONS |  | 2020-07-21 | R4BA | Barron, Raul Angelo | Critical Work | [6 empty] | Approved | Defer approved | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-01-20 09:45 | Saraf, Shubham | J91F | 2021-01-14 09:12 | Stabe, Justin M
29297 | Update work plan date | 35116801 | 117605266 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Approved by Wildfire Governance Committee for 2021 | 2020-08-10 | 2021-12-31 | 3432 | 3408934 | 2020 | 2021 | 2021 | 3741713.1 | 441774.7 |  |  |  |  | 2020-12-31 | CONS |  | 2020-08-10 | A0M6 | Mendez, Angelica | Critical Work | [6 empty] | Approved | Defer approved | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-01-20 09:45 | Saraf, Shubham | J91F | 2021-01-14 09:12 | Stabe, Justin M
29294 | Update work plan date | 35157845 | 118548863 | SILVERADO 2105 WIRE DOWN - PH 3 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Approved by Wildfire Governance Committee for 2021 | 2020-05-07 | 2021-12-31 | 875.3 | 1800635 | 2020 | 2021 | 2021 | 1717.8 | [5 empty] | 2020-12-31 | CONS |  |  | J1E1 | Eagar, Josh | [7 empty] | Approved | Defer approved | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-01-20 09:45 | Saraf, Shubham | J91F | 2021-01-14 09:11 | Stabe, Justin M
29295 | Update work plan date | 35114040 | 117500499 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Delayed by Caltrans DSDD Permit | 2020-07-29 | 2022-12-31 | 4154.9 | 4232824 | 2020 | 2022 | 2022 | 3110000 | 1676839.1 |  |  |  |  | 2019-12-06 | CONS |  | 2020-07-29 | J1PE | Pantoja-Martinez, Jaime | Critical Work | [6 empty] | Approved | Defer approved | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-01-20 09:45 | Saraf, Shubham | J91F | 2021-01-14 09:06 | Stabe, Justin M
29296 | Update work plan date | 35052737 | 114675474 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Approved | 08W | 2021 Rsrv |  |  | GC |  |  | Delayed by Caltrans DSDD permit | 2022-03-02 | 2022-12-31 | 2163 | 2768676 | 2021 | 2022 | 2022 | 4086056.3 | 2738.2 |  |  |  |  | 2021-07-12 | PEND |  | 2022-03-02 | A0M6 | Mendez, Angelica | [7 empty] | Approved | Defer approved | Merih Tekeste | Approved |  |  | Approved |  | SFSS | 2021-01-20 09:45 | Saraf, Shubham | J91F | 2021-01-14 09:05 | Stabe, Justin M
27633 | Budget change | 35145540 | 118259180 | PSPS - FROGTOWN 1702 - CB | Approved | 08W |  |  |  | Contract |  |  | Carry over from 2020 | 2022-03-30 |  | 4233.1 | 5959167 | 2021 |  |  | 49246 | 4139274.6 |  | 4139274.6 | 0 | 0 | 2020-09-30 | PEND |  | 2022-03-30 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-13 10:56 | Saraf, Shubham | T3SQ | 2021-01-12 12:31 | Skarda, Travis Damian
27632 | Budget change | 35142826 | 118218639 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Approved | 08W | 2020 Rsrv |  |  | GC |  |  | Carry over from 2020 | 2021-02-01 |  | 1689.6 | 3876275 | 2021 |  |  | 2721318.8 | 2721318.8 |  | 2721318.8 | 0 | 0 | 2020-12-31 | CONS |  | 2021-02-01 | T3SQ | Skarda, Travis Damian | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-13 10:56 | Saraf, Shubham | T3SQ | 2021-01-12 12:30 | Skarda, Travis Damian
27631 | Budget change | 35115154 | 117496036 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Carry over from 2020 | 2021-03-17 |  | 3107.7 | 3872109 | 2020 | 2021 |  | 3557902.7 | 2584854.1 |  | 2584854.1 | 0 | 0 | 2020-12-31 | CONS |  | 2021-03-17 | T3SQ | Skarda, Travis Damian | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-13 10:56 | Saraf, Shubham | T3SQ | 2021-01-12 12:30 | Skarda, Travis Damian
27630 | Budget change | 35115153 | 117495859 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Carry over from 2020 | 2021-03-08 |  | 2375.4 | 4734585 | 2020 | 2021 |  | 3556611.4 | 3080584.2 |  | 3080584.2 | 0 | 0 | 2020-12-31 | CONS |  | 2021-03-08 | T3SQ | Skarda, Travis Damian | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-13 10:56 | Saraf, Shubham | T3SQ | 2021-01-12 12:29 | Skarda, Travis Damian
27629 | Budget change | 35115151 | 117493857 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Carry over from 2020 | 2020-08-17 |  | 1832.1 | 5273989 | 2020 | 2021 |  | 3557462.7 | 2520547.9 |  | 2520547.9 | 0 | 0 | 2020-12-31 | CONS |  | 2020-08-17 | T3SQ | Skarda, Travis Damian | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-13 10:56 | Saraf, Shubham | T3SQ | 2021-01-12 12:29 | Skarda, Travis Damian
27628 | Budget change | 35112429 | 117467966 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Carryover/closeout costs | 2020-03-09 |  | 4175 | 5585619 | 2020 |  |  | 2122911.2 | 75000 |  | 75000 | 0 | 0 | 2020-12-31 | FICL | 2020-07-18 | 2020-03-09 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-13 10:56 | Saraf, Shubham | T3SQ | 2021-01-12 12:28 | Skarda, Travis Damian
27627 | Budget change | 35109556 | 117348368 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Carryover/closeout costs | 2019-10-21 |  | 525.7 | 1197284 | 2020 |  |  | 539895.8 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-03-06 | 2019-10-21 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-13 10:56 | Saraf, Shubham | T3SQ | 2021-01-12 12:28 | Skarda, Travis Damian
27626 | Budget change | 35109555 | 117348367 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Carryover/closeout costs | 2019-12-09 |  | 3331.1 | 4477708 | 2020 |  |  | 1377445.6 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-02-21 | 2019-12-09 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-13 10:56 | Saraf, Shubham | T3SQ | 2021-01-12 12:28 | Skarda, Travis Damian
27625 | Budget change | 35109554 | 117348366 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Carryover/closeout costs | 2020-02-13 |  | 1515 | 2287663 | 2020 |  |  | 2052799.3 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-04-03 | 2020-02-13 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-13 10:56 | Saraf, Shubham | T3SQ | 2021-01-12 12:27 | Skarda, Travis Damian
27624 | Budget change | 35109553 | 117348828 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Carryover/closeout costs | 2019-10-21 |  | 2781.7 | 4009924 | 2020 |  |  | 2010425.3 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-01-29 | 2019-10-21 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-13 10:56 | Saraf, Shubham | T3SQ | 2021-01-12 12:27 | Skarda, Travis Damian
27623 | Budget change | 35109552 | 117348827 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Carryover/closeout costs | 2019-10-07 |  | 2699 | 5804263 | 2020 |  |  | 1092828.8 | 175000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-02-11 | 2019-10-07 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-13 10:56 | Saraf, Shubham | T3SQ | 2021-01-12 12:27 | Skarda, Travis Damian
27619 | Budget change | 35109548 | 117349073 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Carryover/closeout costs | 2020-01-27 |  | 4055.7 | 7082947 | 2020 |  |  | 5761350.2 | 450000 |  | 450000 | 0 | 0 | 2020-12-30 | DOCC | 2020-05-22 | 2020-01-27 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-13 10:56 | Saraf, Shubham | T3SQ | 2021-01-12 12:26 | Skarda, Travis Damian
27620 | Budget change | 35109549 | 117348822 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Carryover/closeout costs | 2019-10-04 |  | 1629 | 3123544 | 2020 |  |  | 1170998.5 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-04-17 | 2019-10-04 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-13 10:56 | Saraf, Shubham | T3SQ | 2021-01-12 12:26 | Skarda, Travis Damian
27622 | Budget change | 35109551 | 117348824 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Carryover/closeout costs | 2019-10-02 |  | 439.4 | 3172299 | 2020 |  |  | 372852.5 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-04-17 | 2019-10-02 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-13 10:56 | Saraf, Shubham | T3SQ | 2021-01-12 12:26 | Skarda, Travis Damian
27621 | Budget change | 35109550 | 117348823 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Carryover/closeout costs | 2019-10-04 |  | 1821.7 | 3044150 | 2020 |  |  | 627012.7 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-01-31 | 2019-10-04 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-13 10:56 | Saraf, Shubham | T3SQ | 2021-01-12 12:26 | Skarda, Travis Damian
27618 | Budget change | 35109547 | 117349072 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Carryover/closeout costs | 2020-01-06 |  | 2120.4 | 3530637 | 2020 |  |  | 2778156 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-03-13 | 2020-01-06 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-13 10:56 | Saraf, Shubham | T3SQ | 2021-01-12 12:24 | Skarda, Travis Damian
27617 | Budget change | 35109545 | 117349070 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Carryover/closeout costs | 2019-12-02 |  | 2430 | 4499650 | 2020 |  |  | 4126337.8 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-04-17 | 2019-12-02 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-13 10:56 | Saraf, Shubham | T3SQ | 2021-01-12 12:01 | Skarda, Travis Damian
27616 | Budget change | 35109540 | 117348505 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Carryover/closeout costs | 2019-10-16 |  | 1065 | 4228889 | 2020 |  |  | 1838510.1 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-02-18 | 2019-10-16 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-13 10:56 | Saraf, Shubham | T3SQ | 2021-01-12 12:00 | Skarda, Travis Damian
27615 | Budget change | 35061212 | 115106486 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Carry over from 2020 | 2020-08-20 |  | 1612.8 | 4913095 | 2020 | 2021 |  | 3641406.7 | 2161081.9 |  | 2161081.9 | 0 | 0 | 2020-12-31 | CONS |  | 2020-08-20 | T3SQ | Skarda, Travis Damian | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-13 10:56 | Saraf, Shubham | T3SQ | 2021-01-12 12:00 | Skarda, Travis Damian
27380 | Budget change | 35095166 | 114742467 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | requesting $75,000 for closing out fee and any unexpected charges that might hit the project | 2020-08-06 |  | 4104 | 3293522 | 2020 |  |  | 1538336.7 |  |  | 75000 | 0 | 0 | 2019-12-31 | MAPP |  |  | CRGN | Gras, Christopher R | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-11 22:39 | Saraf, Shubham | ZXAC | 2021-01-11 11:05 | Al-Saffar, Zaid Dhafer Hashim
27374 | Budget change | 35112432 | 117472387 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | requesting $75,000 for closing out fee and any unexpected charges that might hit the project | 2020-05-08 |  | 2667.8 | 5345911 | 2020 |  |  | 4912207.3 | 75000 |  | 75000 | 0 | 0 | 2020-12-31 | DOCC | 2020-11-18 | 2020-05-08 | CRGN | Gras, Christopher R | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-11 22:39 | Saraf, Shubham | ZXAC | 2021-01-11 11:05 | Al-Saffar, Zaid Dhafer Hashim
27375 | Budget change | 35112433 | 117472388 | CWSP - EL DORADO 2102 - LR19562 - PH 1.3 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | requesting $75,000 for closing out fee and any unexpected charges that might hit the project | 2020-03-27 |  | 2274 | 4151673 | 2020 |  |  | 4707102.8 | 75000 |  | 75000 | 0 | 0 | 2020-12-31 | MAPP | 2020-06-11 | 2020-03-27 | CRGN | Gras, Christopher R | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-11 22:39 | Saraf, Shubham | ZXAC | 2021-01-11 11:05 | Al-Saffar, Zaid Dhafer Hashim
27376 | Budget change | 35112434 | 117472389 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | requesting $75,000 for closing out fee and any unexpected charges that might hit the project | 2020-07-27 |  | 3098.1 | 3756886 | 2020 |  |  | 2403957.8 | 75000 |  | 75000 | 0 | 0 | 2020-12-31 | DOCC | 2020-10-02 | 2020-07-27 | CRGN | Gras, Christopher R | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-11 22:39 | Saraf, Shubham | ZXAC | 2021-01-11 11:05 | Al-Saffar, Zaid Dhafer Hashim
27378 | Budget change | 35112436 | 117472563 | CWSP - EL DORADO 2102 - LR19562 - PH 1.6 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | requesting $75,000 for closing out fee and any unexpected charges that might hit the project | 2020-06-07 |  | 2454.5 | 3899347 | 2020 |  |  | 2566326.4 | 75000 |  | 75000 | 0 | 0 | 2020-12-31 | MAPP |  |  | CRGN | Gras, Christopher R | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-11 22:39 | Saraf, Shubham | ZXAC | 2021-01-11 11:05 | Al-Saffar, Zaid Dhafer Hashim
27379 | Budget change | 35112437 | 117472564 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | requesting $75,000 for closing out fee and any unexpected charges that might hit the project | 2020-07-08 |  | 2578.5 | 5431839 | 2020 |  |  | 5750872.5 |  |  | 75000 | 0 | 0 | 2020-12-31 | FICL |  |  | CRGN | Gras, Christopher R | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-11 22:39 | Saraf, Shubham | ZXAC | 2021-01-11 11:05 | Al-Saffar, Zaid Dhafer Hashim
27377 | Budget change | 35112435 | 117472561 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | requesting $75,000 for closing out fee and any unexpected charges that might hit the project | 2020-05-31 |  | 5177.2 | 4061849 | 2020 |  |  | 2068858.2 |  |  | 75000 | 0 | 0 | 2020-12-31 | MAPP |  |  | CRGN | Gras, Christopher R | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-11 22:39 | Saraf, Shubham | ZXAC | 2021-01-11 11:05 | Al-Saffar, Zaid Dhafer Hashim
27373 | Budget change | 35112431 | 117472384 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | requesting $75,000 for closing out fee and any unexpected charges that might hit the project | 2020-05-27 |  | 2000.4 | 4166416 | 2020 |  |  | 2992595.4 |  |  | 75000 | 0 | 0 | 2020-12-31 | FICL |  |  | CRGN | Gras, Christopher R | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-11 22:39 | Saraf, Shubham | ZXAC | 2021-01-11 11:05 | Al-Saffar, Zaid Dhafer Hashim
27341 | RCR - Add and Assign Resource | 35161152 | 118677878 | OCT2019 BRICEBURG FIRE REBUILD | Denied | 08W |  |  |  |  | N/A | GC | GC has reviewed and orderd mtls. | [13 empty] | 2021-02-26 | UNSC |  |  | SGBA | Barrow, Steve | [7 empty] | Approved | WK3 2021 | Merih Tekeste |  |  |  | Denied | Order and Notification don't match | SFSS | 2021-01-11 16:25 | Saraf, Shubham | SZC3 | 2021-01-08 15:04 | Calvert, Susan
25906 | Resource change | 35145525 | 118266592 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Approved | 08W |  |  | Contract | GC | CONTRACT | GC | Civil work to be completed by Contract. | 2021-04-26 |  | 4043.7 | 7914493 | 2021 |  |  | 18422.4 | 18928.2 |  |  |  |  | 2020-12-01 | UNSC |  | 2021-04-26 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-11 22:39 | Saraf, Shubham | JUPX | 2021-01-07 11:53 | Pereyda, Jessica Ann Hiroko
25905 | Resource change | 35145524 | 118266591 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Approved | 08W |  |  | Contract | GC | CONTRACT | GC | Civil work to be completed by Contract. | 2021-04-26 |  | 3740.9 | 8431936 | 2021 |  |  | 18613.1 | 19836.3 |  |  |  |  | 2020-12-01 | PEND |  | 2021-04-26 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-01-11 22:39 | Saraf, Shubham | JUPX | 2021-01-07 11:53 | Pereyda, Jessica Ann Hiroko
25869 | Add project | 35145525 | 118266592 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Denied | 08W |  |  | Contract | GC | Contract |  | Civil work to be completed by Contract. | 2021-04-26 |  | 4043.7 | 7914493 | 2021 |  |  | 18422.4 | 18928.2 |  |  |  |  | 2020-12-01 | UNSC |  | 2021-04-26 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Denied | job is already on the work plan | SFSS | 2021-01-20 09:57 | Saraf, Shubham | JUPX | 2021-01-06 16:24 | Pereyda, Jessica Ann Hiroko
25868 | Add project | 35145524 | 118266591 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Denied | 08W |  |  | Contract | GC | Contract |  | Civil work to be completed by Contract. | 2021-04-26 |  | 3740.9 | 8431936 | 2021 |  |  | 18613.1 | 19836.3 |  |  |  |  | 2020-12-01 | PEND |  | 2021-04-26 | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Denied | job is already on the work plan | SFSS | 2021-01-20 09:57 | Saraf, Shubham | JUPX | 2021-01-06 16:24 | Pereyda, Jessica Ann Hiroko
21389 | Resource change | 35192280 | 119556070 | ECOP - CLAYTON 2212 - H01-LR2951 | Approved | 08W |  |  |  | GC |  | GC | 12.18 Resource Updates | 2022-06-22 |  | 180 | 550000 | 2021 | 2022 | [7 empty] | 2023-12-31 | UNSE |  | 2022-06-22 | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2020-12-21 20:35 | Saraf, Shubham | ATSC | 2020-12-21 15:08 | Spreen, Andrew
20603 | Resource change | 35116384 | 117604604 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Approved | 08W | 220 Mile Plan |  |  | Contract |  | GC | 12.18 Resource Updates | 2021-04-12 |  | 2558 | 4624169 | 2020 | 2021 |  | 3239382 | 1875779.4 |  |  |  |  | 2020-12-25 | CONS |  | 2021-04-12 | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2020-12-21 14:39 | Saraf, Shubham | ATSC | 2020-12-21 12:11 | Spreen, Andrew
20604 | Resource change | 35052825 | 114701195 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Approved | 08W | 220 Mile Plan |  |  | Contract |  | GC | 12.18 Resource Updates | 2021-04-20 |  | 2073 | 3544410 | 2021 | 2021 |  | 288570 | 1048628 |  |  |  |  | 2020-12-31 | CONS |  | 2021-04-20 | A0M6 | Mendez, Angelica | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2020-12-21 14:39 | Saraf, Shubham | ATSC | 2020-12-21 12:11 | Spreen, Andrew
20304 | Update work plan date | 35115053 |  | CWSP - MIWUK 1701_OCB - PH 1.5 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Project has been pushed into 2021. | 2020-08-11 | 2021-04-20 | 1878 | 2296559 | 2020 | 2021 | 2021 | 5520083.3 | 204609 | 823352 | 8996 |  |  |  | CONS |  | 2020-08-11 | FXA7 | Armas, Fernando | Critical Work |  |  |  |  | Approved |  | Approved | Defer approved | Merih Tekeste | Approved | Temporaily until this can be owned by program managers themselves in DOT |  | Approved |  | JZSG | 2020-12-29 11:30 | Sadler, Justin R | L3WA | 2020-12-15 13:17 | Ward, Laree
20303 | Update work plan date | 35116384 | 117604604 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Project has been pushed into 2021. | 2021-04-12 | 2021-04-22 | 2558 | 4624169 | 2020 | 2021 | 2021 | 3239382 | 1875779.4 | 64331 | 2026268 |  |  | 2020-12-25 | CONS |  | 2021-04-12 | FXA7 | Armas, Fernando | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | Approved | Temporaily until this can be owned by program managers themselves in DOT |  | Approved |  | JZSG | 2020-12-29 11:31 | Sadler, Justin R | L3WA | 2020-12-15 13:14 | Ward, Laree
20302 | Update work plan date | 35116444 | 117605182 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Project has been pushed into 2021. | 2020-08-04 | 2021-04-15 | 1664 | 3531134 | 2020 | 2021 | 2021 | 3634380.5 | 603963.1 | 920437 | 559463 |  |  | 2020-12-31 | CONS |  | 2020-08-04 | FXA7 | Armas, Fernando | [5 empty] | Approved |  | Approved | Defer approved | Merih Tekeste | Approved | Temporaily until this can be owned by program managers themselves in DOT |  | Approved |  | JZSG | 2020-12-29 11:31 | Sadler, Justin R | L3WA | 2020-12-15 13:10 | Ward, Laree
20301 | Update work plan date | 35052821 | 114593976 | CWSP - MIWUK 1701 - OCB - PH 1.1 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Project has been pushed into 2021. | 2020-08-31 | 2021-01-05 | 1732 | 4765282 | 2020 | 2021 | 2021 | 3323925 | 1325532.5 | 798819 | 1382243 |  |  | 2020-12-31 | CONS |  | 2020-08-31 | FXA7 | Armas, Fernando | Critical Work |  |  |  |  | Approved |  | Approved | Defer approved | Merih Tekeste | Approved | Temporaily until this can be owned by program managers themselves in DOT |  | Approved |  | JZSG | 2020-12-29 11:30 | Sadler, Justin R | L3WA | 2020-12-15 13:03 | Ward, Laree
19647 | RCR - Add and Assign Resource | 31334291 | 112994395 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Approved | 08W |  |  |  |  | N/A | GC | [14 empty] | 2020-12-31 | PEND |  |  | J1E1 | Eagar, Josh | [7 empty] | Approved |  | Merih Tekeste |  |  |  | Approved |  | SFSS | 2020-12-15 11:45 | Saraf, Shubham | SZC3 | 2020-12-14 17:03 | Calvert, Susan
19648 | RCR - Add and Assign Resource | 31361965 | 113751296 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Approved | 08W |  |  |  |  | N/A | GC | [14 empty] | 2020-12-31 | CONS |  |  | J1E1 | Eagar, Josh | [7 empty] | Approved |  | Merih Tekeste |  |  |  | Approved |  | SFSS | 2020-12-15 11:45 | Saraf, Shubham | SZC3 | 2020-12-14 17:03 | Calvert, Susan
19709 | RCR - Change or Assign Resource | 35031662 | 114474310 | CWSP - LOS GATOS 1106 - LB44 - PHASE 2.1 | Approved | 08W | 220 Mile Plan |  | Contract | Division | Contract | Division |  | 2020-02-12 |  | 1767.5 | 1363100.7 | 2020 |  |  | 1012978.8 | 19394.1 |  |  |  |  | 2020-08-31 | FICL | 2020-03-25 | 2020-02-12 | SLKD | Kennedy, Sharon | [7 empty] | Approved |  | Merih Tekeste |  |  |  | Approved |  | SFSS | 2020-12-15 11:38 | Saraf, Shubham | SZC3 | 2020-12-14 17:03 | Calvert, Susan
19775 | RCR - Change or Assign Resource | 35145004 | 118263746 | PSPS CWSP - ROSSMOOR 1106 - CB | Approved | 08W |  |  |  |  | Contract | GC |  | 2022-04-12 |  |  |  | 2021 | [8 empty] | 2020-12-31 | PEND |  |  | M1NO | Nguyen, My-Linh | [7 empty] | Approved |  | Merih Tekeste |  |  |  | Approved |  | SFSS | 2020-12-15 11:45 | Saraf, Shubham | SZC3 | 2020-12-14 17:03 | Calvert, Susan
19776 | RCR - Change or Assign Resource | 35144941 | 118261469 | PSPS - PAUL SWEET 2105 - CB PH 1 | Approved | 08W |  |  |  |  | Contract | GC |  | 2022-03-16 |  |  |  | 2021 | [8 empty] | 2020-12-31 | PEND |  |  | M1NO | Nguyen, My-Linh | [7 empty] | Approved |  | Merih Tekeste |  |  |  | Approved |  | SFSS | 2020-12-15 11:45 | Saraf, Shubham | SZC3 | 2020-12-14 17:03 | Calvert, Susan
20090 | RCR - Change or Assign Resource | 35145522 | 118265394 | PSPS - CLARKSVILLE 2104 - CB UG | Approved | 08W |  |  |  |  | Contract | GC |  | 2022-04-11 |  |  |  | 2021 | [8 empty] | 2020-12-31 | PEND |  |  | T3SQ | Skarda, Travis Damian | [7 empty] | Approved |  | Merih Tekeste |  |  |  | Approved |  | SFSS | 2020-12-15 11:45 | Saraf, Shubham | SZC3 | 2020-12-14 16:55 | Calvert, Susan
20086 | RCR - Change or Assign Resource | 74022388 | 114266765 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Approved | 08W | 220 Mile Plan |  | Contract | Division | Contract | Division |  | 2020-02-14 |  | 6713 | 5476214 | 2020 |  |  | 5268810 | [5 empty] | 2020-03-01 | FICL | 2020-11-05 | 2020-02-14 | A1CO | Chan, Antonio Miguel | Critical Work | [6 empty] | Approved |  | Merih Tekeste |  |  |  | Approved |  | SFSS | 2020-12-15 11:38 | Saraf, Shubham | SZC3 | 2020-12-14 16:55 | Calvert, Susan
20087 | RCR - Change or Assign Resource | 74022388 | 114266765 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Approved | 08W | 220 Mile Plan |  | Contract | Division | Contract | Division |  | 2020-02-14 |  | 6713 | 5476214 | 2020 |  |  | 5268810 | [5 empty] | 2020-03-01 | FICL | 2020-11-05 | 2020-02-14 | A1CO | Chan, Antonio Miguel | Critical Work | [6 empty] | Approved |  | Merih Tekeste |  |  |  | Approved |  | SFSS | 2020-12-15 11:38 | Saraf, Shubham | SZC3 | 2020-12-14 16:55 | Calvert, Susan
19249 | Update work plan date | 35116442 | 117605169 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Project deferred into 2021. | 2020-07-15 | 2021-01-18 | 2736 | 3849738 | 2020 | 2021 | 2021 | 2989278 | 203909.1 | 1894612 | 201890 | 0 |  | 2020-12-31 | DOCC | 2021-02-04 | 2020-07-15 | M2HM | Herron, Matthew Joseph | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-12-14 13:37 | Sadler, Justin R | L3WA | 2020-12-11 15:34 | Ward, Laree
19183 | Update work plan date | 35056746 |  | CWSP - MIWUK 1701 OCB PHASE 2.1 | Approved | 08W | [6 empty] | Add Project to MPP | 2021-02-15 | [13 empty] | CONS |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved | Changed to deferral, project on 2020 work plan | JZSG | 2020-12-11 15:22 | Sadler, Justin R | L3WA | 2020-12-10 14:30 | Ward, Laree
19182 | Add project | 35115057 |  | CWSP - MIWUK 1701 - OCB - PH2.5 | Denied | 08W | [6 empty] | Add Project to MPP | 2022-03-31 | [13 empty] | UNSC |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Denied | Project removed from work plan due to new risk model | JZSG | 2020-12-11 15:23 | Sadler, Justin R | L3WA | 2020-12-10 14:29 | Ward, Laree
19181 | Add project | 35115051 |  | CWSP - MIWUK 1701_OCB - PH 1.3 | Denied | 08W | [6 empty] | Add Project to MPP | 2022-03-01 | [13 empty] | CONS |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Denied | Project removed from work plan due to new risk model | JZSG | 2020-12-11 15:23 | Sadler, Justin R | L3WA | 2020-12-10 13:02 | Ward, Laree
19180 | Add project | 35052739 |  | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Denied | 08W | [6 empty] | Add Project to MPP | 2022-03-09 | [13 empty] | CONS |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Denied | Project removed from work plan due to new risk model | JZSG | 2020-12-11 15:21 | Sadler, Justin R | L3WA | 2020-12-10 12:26 | Ward, Laree
18937 | Update work plan date | 35116383 | 117604600 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Project has been pushed out into 2021; delay due to fire rebuild | 2021-03-08 | 2021-01-26 | 1953 | 3758449 | 2020 | 2021 | 2021 | 2531607.33 | 722523.9 | 1077436 | 1035343 |  |  | 2021-06-30 | CONS |  | 2021-03-08 | M2HM | Herron, Matthew Joseph | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Approved | See EDRS 2020-83277 | JZSG | 2020-12-11 14:51 | Sadler, Justin R | L3WA | 2020-12-09 14:33 | Ward, Laree
18936 | Update work plan date | 35115055 | 117490481 | CWSP - MIWUK 1701 - OCB - PH 2.3 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Project has been pushed out into 2021; delay due to fire rebuild | 2020-12-31 | 2021-03-15 | 1664 | 3784068 | 2020 | 2021 | 2021 | 5311510 | 655429.1 | 986382 | 1023108 |  |  | 2020-12-04 | CONS |  | 2020-12-31 | A0M6 | Mendez, Angelica | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Approved | See EDRS 2020-83277 | JZSG | 2020-12-11 14:51 | Sadler, Justin R | L3WA | 2020-12-09 14:30 | Ward, Laree
18935 | Update work plan date | 35056746 | 114996821 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Project has been pushed out into 2021; delay due to fire rebuild | 2020-09-14 | 2021-02-15 | 1536 | 3642331 | 2020 | 2021 | 2021 | 5901804 | 975015.3 | 544498 | 1257187 |  |  | 2020-12-01 | CONS |  | 2020-09-14 | A0M6 | Mendez, Angelica | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Approved | See EDRS 2020-83277 | JZSG | 2020-12-11 14:51 | Sadler, Justin R | L3WA | 2020-12-09 14:26 | Ward, Laree
18736 | Budget change | 35145002 |  | PSPS - IGNACIO 1101 - CB | Approved | 08W | [6 empty] | More accurate estimate and forecast available | [9 empty] | 120000 | 2556721.57 |  |  |  | PEND |  |  | D2PK | Pontrello, Donna | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2020-12-08 12:53 | Saraf, Shubham | A8G1 | 2020-12-07 16:57 | Galesic, Alvin
17723 | Resource change | 35113950 | 117560045 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Approved | 08W | [5 empty] | CONTRACT | 2021 PRIORITY ASSIGNMENT CONTRACT | 2021-02-24 |  |  |  | 2020 | [9 empty] | PEND |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2020-11-22 20:36 | Saraf, Shubham | DWFB | 2020-11-20 12:32 | Fisher, Douglas Wayne
17722 | Resource change | 35113951 | 117560047 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Approved | 08W | [5 empty] | CONTRACT | 2021 PRIORITY ASSIGNMENT CONTRACT | 2021-09-23 |  |  |  | 2020 | [9 empty] | UNSC |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2020-11-22 20:36 | Saraf, Shubham | DWFB | 2020-11-20 12:31 | Fisher, Douglas Wayne
17721 | Resource change | 35052731 | 114607365 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Approved | 08W | 220 Mile Plan |  |  | Contract |  | CONTRACT | 2021 PRIORITY ASSIGNMENT CONTRACT | 2021-04-16 |  | 3503.2 | 4994628 | 2020 | 2021 |  | 2414517.1 | 1805936 |  |  |  |  | 2020-09-30 | PEND |  | 2021-04-16 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2020-11-22 20:36 | Saraf, Shubham | DWFB | 2020-11-20 12:31 | Fisher, Douglas Wayne
17133 | RCR - Change or Assign Resource | 35145004 | 118263746 | PSPS CWSP - ROSSMOOR 1106 - CB | Approved | 08W |  |  |  |  | Contract | GC | VPI was awarded civil contract on Rossmoor 1109/PM# 74008802. Rossmoor 1109 is installing spare ducts for Rossmoor 1106. There is a small portion of civil work on Rossmoor 1106 project that is outside scope of Rossmoor 1109 (~150k/300 hours). Requestig | 2021-02-04 |  |  |  | 2021 | [8 empty] | 2021-03-31 | PEND |  |  | M1NO | Nguyen, My-Linh | [7 empty] | Approved | Civil only reqeust | Merih Tekeste |  |  |  | Approved |  | SFSS | 2020-11-19 19:42 | Saraf, Shubham | M1NO | 2020-11-17 12:28 | Nguyen, My-Linh
15700 | Update work plan date | 35112427 | 117467963 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.4 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Reprioritization of workplan for 08W | 2020-11-14 | 2020-11-14 | 2279.8 | 3306693 | 2020 |  | 2020 | 1425167.6 | -231631 |  |  |  |  | 2020-12-31 | MAPP |  |  | J6KF | Kringler, Jeff L | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Approved | BISD Extension approved in EDRS 2020-76744 | D4L6 | 2020-11-23 10:09 | Le, Dung | HAMG | 2020-11-13 10:41 | Marshall, Holly Ann
15699 | Update work plan date | 35115155 | 117491298 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Reprioritization of workplan for 08W | 2020-01-13 | 2020-11-14 | 2123.7 | 5231108 | 2020 | 2021 | 2021 | 2946774.1 | 88800 |  |  |  |  | 2020-12-31 | DOCC | 2021-02-25 | 2020-01-13 | J6KF | Kringler, Jeff L | Critical Work |  |  |  |  | Approved |  |  |  | Merih Tekeste |  |  |  | Approved | BISD Extension approved in EDRS 2020-76744 | D4L6 | 2020-11-23 10:11 | Le, Dung | HAMG | 2020-11-13 10:41 | Marshall, Holly Ann
15698 | Update work plan date | 35117443 | 117634567 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Reprioritization of workplan for 08W | 2020-07-28 | 2020-11-14 | 5134.2 | 5778810 | 2020 | 2021 | 2021 | 4175407.8 | 2450191 |  |  |  |  | 2020-12-31 | CONS |  | 2020-07-28 | T3SQ | Skarda, Travis Damian | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Approved | BISD Extension approved in EDRS 2020-76744 | D4L6 | 2020-11-23 10:09 | Le, Dung | HAMG | 2020-11-13 10:41 | Marshall, Holly Ann
15697 | Update work plan date | 35115148 | 117496270 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Reprioritization of workplan for 08W | 2020-06-02 | 2020-11-14 | 3236.8 | 5062019 | 2020 | 2021 | 2021 | 4762461.3 | 59744 |  |  |  |  | 2020-12-31 | FICL | 2020-11-20 | 2020-06-02 | J6KF | Kringler, Jeff L | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Approved | BISD Extension approved in EDRS 2020-76744 | D4L6 | 2020-11-23 10:10 | Le, Dung | HAMG | 2020-11-13 10:41 | Marshall, Holly Ann
15696 | Update work plan date | 35098621 | 117177530 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Reprioritization of workplan for 08W | 2020-06-01 | 2020-11-14 | 2558.5 | 2927538 | 2020 | 2021 | 2021 | 1520689.3 | 131088 |  |  |  |  | 2020-11-30 | DOCC | 2020-12-03 | 2020-06-01 | J6KF | Kringler, Jeff L | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Approved | BISD Extension approved in EDRS 2020-76744 | D4L6 | 2020-11-23 10:11 | Le, Dung | HAMG | 2020-11-13 10:40 | Marshall, Holly Ann
15695 | Update work plan date | 35061206 | 115106231 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Reprioritization of workplan for 08W | 2020-06-15 | 2020-11-14 | 4091.3 | 4711641 | 2020 | 2021 | 2021 | 3596290.1 | 1419181 |  |  |  |  | 2020-12-31 | CONS |  | 2020-06-15 | T3SQ | Skarda, Travis Damian | [5 empty] | Approved |  |  |  | Merih Tekeste |  |  |  | Approved | BISD Extension approved in EDRS 2020-76744 | D4L6 | 2020-11-23 10:11 | Le, Dung | HAMG | 2020-11-13 10:40 | Marshall, Holly Ann
15688 | Budget change | 35053429 | 114921419 | CWSP HALF MOON BAY 1102 FUCO 12457 | Approved | 08W | [6 empty] | Requet update to 2021 Optimized Budget before routing business case. | 2021-01-20 |  |  |  | 2021 |  |  |  |  | 138035 | 1672108 |  |  |  | UNSC |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-20 14:19 | Sadler, Justin R | M1NO | 2020-11-13 09:05 | Nguyen, My-Linh
15692 | Update work plan date | 74022384 | 114753320 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Sonoma GC crews pulled off project in mid-August to assist with fire restoration. Has not been able to return to jobsite and not likely until next year. | 2020-06-08 | 2021-05-31 | 8146.2 | 9998553 | 2020 | 2021 | 2021 | 6860373.1 | 2395900 | 3838756.17 | 3032683 |  |  | 2020-12-31 | CONS |  | 2020-06-08 | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Deferrals approved, start dates subject to 2021 work plan priorities TBD | Merih Tekeste |  |  |  | Approved | Confirmed this job is approved to work | JZSG | 2020-12-07 10:29 | Sadler, Justin R | M1NO | 2020-11-13 08:58 | Nguyen, My-Linh
15480 | Budget change | 35060994 | 115101557 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Approved | 08W | [6 empty] | Additional estimating costs. | 2021-05-31 |  |  |  | 2021 |  |  |  |  | 150000 | 2034045 |  |  |  | ESTS |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-12 19:47 | Sadler, Justin R | HAMG | 2020-11-12 11:38 | Marshall, Holly Ann
15479 | Budget change | 35160098 | 118532430 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 | Approved | 08W | [6 empty] | Additional estimating costs. | 2021-06-01 |  |  |  | 2021 |  |  |  |  | 150000 | 1778415.6 |  |  |  | ESTS |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-12 19:47 | Sadler, Justin R | HAMG | 2020-11-12 11:38 | Marshall, Holly Ann
15474 | Budget change | 35160095 | 118532315 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Approved | 08W | [6 empty] | Additional estimating costs. | 2021-06-29 |  |  |  | 2021 |  |  |  |  | 150000 | 3503804.7 |  |  |  | ESTS |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-12 19:47 | Sadler, Justin R | HAMG | 2020-11-12 11:38 | Marshall, Holly Ann
15473 | Budget change | 35160096 | 118532317 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 | Approved | 08W | [6 empty] | Additional estimating costs. | 2021-06-28 |  |  |  | 2021 |  |  |  |  | 150000 | 1917956.1 |  |  |  | ESTS |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-12 19:47 | Sadler, Justin R | HAMG | 2020-11-12 11:38 | Marshall, Holly Ann
15476 | Budget change | 35160097 | 118532318 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 | Approved | 08W | [6 empty] | Additional estimating costs. | 2021-06-15 |  |  |  | 2021 |  |  |  |  | 150000 | 3786450 |  |  |  | ADER |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-12 19:47 | Sadler, Justin R | HAMG | 2020-11-12 11:38 | Marshall, Holly Ann
15477 | Budget change | 35158717 | 118531819 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | Approved | 08W | [6 empty] | Additional estimating costs. | 2021-05-31 |  |  |  | 2021 |  |  |  |  | 150000 | 2727534.9 |  |  |  | ADER |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-12 19:47 | Sadler, Justin R | HAMG | 2020-11-12 11:38 | Marshall, Holly Ann
15475 | Budget change | 35160091 | 118532310 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | Approved | 08W | [6 empty] | Additional estimating costs. | 2021-06-28 |  |  |  | 2021 |  |  |  |  | 150000 | 1298152.2 |  |  |  | ADER |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-12 19:47 | Sadler, Justin R | HAMG | 2020-11-12 11:38 | Marshall, Holly Ann
15472 | Budget change | 35160093 | 118532312 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Approved | 08W | [6 empty] | Additional estimating costs. | 2021-06-02 |  |  |  | 2021 |  |  |  |  | 150000 | 2046155.4 |  |  |  | ESTS |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-12 19:47 | Sadler, Justin R | HAMG | 2020-11-12 11:38 | Marshall, Holly Ann
15424 | Budget change | 35112428 | 117467964 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.5 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Cover unexpected construction costs | 2019-12-18 |  | 1611.4 | 3809898 | 2020 |  |  | 2279000 | -340669 | 2279000 | 0 |  |  | 2020-12-31 | DOCC |  | 2019-12-18 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-12 19:47 | Sadler, Justin R | HAMG | 2020-11-12 11:20 | Marshall, Holly Ann
15423 | Budget change | 35098621 | 117177530 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Cover unexpected construction costs | 2020-06-01 |  | 2558.5 | 2927538 | 2020 | 2021 |  | 1520689.3 | 131088 | 1900000 | 0 |  |  | 2020-11-30 | DOCC | 2020-12-03 | 2020-06-01 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-12 19:47 | Sadler, Justin R | HAMG | 2020-11-12 11:20 | Marshall, Holly Ann
15425 | Budget change | 35115155 | 117491298 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Cover unexpected construction costs | 2020-01-13 |  | 2123.7 | 5231108 | 2020 | 2021 |  | 2946774.1 | 88800 | 3150000 | 0 |  |  | 2020-12-31 | DOCC | 2021-02-25 | 2020-01-13 | J6KF | Kringler, Jeff L | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-12 19:47 | Sadler, Justin R | HAMG | 2020-11-12 11:19 | Marshall, Holly Ann
15426 | Budget change | 35115157 | 117492085 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.4 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Cover unexpected construction costs | 2020-02-18 |  | 2628.1 | 1580553.38 | 2020 |  |  | 3443012.7 | 34847 | 3900000 | 0 |  |  | 2020-12-31 | FICL | 2020-09-30 | 2020-02-18 | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-12 19:47 | Sadler, Justin R | HAMG | 2020-11-12 11:14 | Marshall, Holly Ann
15427 | Budget change | 35160094 | 118532313 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 | Approved | 08W | [6 empty] | Cover estimating costs and overheads. | 2021-06-28 |  |  |  | 2021 |  |  |  |  | 150000 | 2286407 |  |  |  | ESTS |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-12 19:47 | Sadler, Justin R | HAMG | 2020-11-12 11:09 | Marshall, Holly Ann
15422 | Budget change | 35145006 | 118263874 | PSPS - STAFFORD 1101 LR 1298 | Approved | 08W | [6 empty] | Additional budget for estimating/OH dollars. | 2021-05-17 |  |  |  | 2021 |  |  |  |  | 150000 | 2723214 |  |  |  | PEND |  |  | DWPH | Phillips, David William | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-12 19:47 | Sadler, Justin R | HAMG | 2020-11-12 09:56 | Marshall, Holly Ann
13574 | Budget change | 35145540 | 118259180 | PSPS - FROGTOWN 1702 - CB | Approved | 08W |  |  |  | Contract |  |  | Coverage of current year spend in addition to forecasted remaining spend which includes Veg-scope | 2022-03-30 | 2021-04-01 | 4233.1 | 5959167 | 2021 |  |  | 49246 | 4139274.6 | 300000 | 3888521 |  |  | 2020-09-30 | PEND |  | 2022-03-30 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-12 19:47 | Sadler, Justin R | T3SQ | 2020-11-09 10:47 | Skarda, Travis Damian
13573 | Budget change | 35145522 | 118265394 | PSPS - CLARKSVILLE 2104 - CB UG | Approved | 08W | [6 empty] | Coverage of current and future expected charges in 2020 | 2021-03-19 | 2021-03-19 |  |  | 2021 |  |  |  |  | 210000 | 17803529 |  |  |  | PEND |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-12 19:47 | Sadler, Justin R | T3SQ | 2020-11-09 10:42 | Skarda, Travis Damian
12266 | Budget change | 35095168 | 114832575 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.1 | Approved | 08W | [6 empty] | 2021 CWSP Wildfire Hardening Project BC EDRS routing | 2021-06-25 | 2021-04-23 |  |  | 2021 |  |  |  |  | 352872 | 2673326 |  |  |  | PEND |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-06 17:06 | Sadler, Justin R | R4BA | 2020-11-04 14:18 | Barron, Raul Angelo
12268 | Budget change | 35116922 | 117605456 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | Approved | 08W | [6 empty] | 2021 CWSP Wildfire Hardening Project BC EDRS routing | 2021-07-22 | 2021-06-24 |  |  | 2021 |  |  |  |  | 356755 | 2149979 |  |  |  | PEND |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-06 17:06 | Sadler, Justin R | R4BA | 2020-11-04 14:13 | Barron, Raul Angelo
12267 | Budget change | 35116519 | 117608026 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.4 | Approved | 08W | [6 empty] | 2021 CWSP Wildfire Hardening Project BC EDRS routing | 2021-08-10 | 2021-06-15 |  |  | 2021 |  |  |  |  | 487522 | 3021306 |  |  |  | PEND |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-06 17:06 | Sadler, Justin R | R4BA | 2020-11-04 14:11 | Barron, Raul Angelo
12260 | Update work plan date | 35094397 | 117165917 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Approved | 08W | [6 empty] | Crew resources deferred to 2021 |  | 2021-04-04 |  |  | 2022 |  |  |  |  | 900000 | 833017 |  |  |  | FICL | 2021-01-14 |  | J1E1 | Eagar, Josh | [5 empty] | Approved |  | Approved | Deferrals approved, start dates subject to 2021 work plan priorities TBD | Merih Tekeste |  |  |  | Approved | Confirmed this job is approved to work | JZSG | 2020-12-07 10:24 | Sadler, Justin R | J1E1 | 2020-11-03 09:38 | Eagar, Josh
12220 | Update work plan date | 35116443 | 117605181 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Approved | 08W | [6 empty] | Deferred due to wild fire impact | 2021-01-12 | 2021-06-25 |  |  | 2020 | [9 empty] | CONS |  |  | FXA7 | Armas, Fernando | [5 empty] | Approved |  | Approved | Impacted by resource pulled for fire response | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-12 19:29 | Sadler, Justin R | FXA7 | 2020-10-30 12:59 | Armas, Fernando
12218 | Budget change | 35129652 | 117873102 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Approved | 08W | [6 empty] | Requesting budget of $103,113 for 2020. Requesting $1,860,548 for 2021. Per phase gate review. | 2021-12-16 | 2021-12-16 |  |  | 2021 |  |  |  |  | 103113 | 1860547.5 |  |  |  | PEND |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | M5HF | 2020-10-30 12:12 | Hernandez, Michael Donald James
12217 | Budget change | 35129600 | 117873031 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Approved | 08W | [6 empty] | Requesting budget of $113,375 for 2020. Requesting $2,001,194 for 2021. Per phase gate review. | 2021-11-12 | 2021-11-12 |  |  | 2021 |  |  |  |  | 113375 | 2001193.57 |  |  |  | PEND |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | M5HF | 2020-10-30 12:08 | Hernandez, Michael Donald James
12216 | Budget change | 35129439 | 117873030 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Approved | 08W | [6 empty] | Requesting budget of $180,355 for 2020. Requesting $3,307,746 for 2021. Per phase gate review. | 2021-09-13 | 2021-09-13 |  |  | 2021 |  |  |  |  | 180355 | 3307745.54 |  |  |  | PEND |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | M5HF | 2020-10-30 12:03 | Hernandez, Michael Donald James
12215 | Budget change | 35129438 | 117873019 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Approved | 08W | [6 empty] | Requesting budget of $164,470 for 2020. Requesting $2,917,462 for 2021. Per phase gate review. | 2021-12-24 | 2021-12-24 |  |  | 2021 |  |  |  |  | 164470 | 2917462.33 |  |  |  | PEND |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | M5HF | 2020-10-30 11:59 | Hernandez, Michael Donald James
12214 | Budget change | 35129437 | 117873018 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | Approved | 08W | [6 empty] | Requesting budget of $226,132 for 2020. Requesting $3,865,175 for 2021. Per phase gate review. | 2021-07-23 | 2021-07-23 |  |  | 2021 |  |  |  |  | 226132 | 3865175.43 |  |  |  | PEND |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | M5HF | 2020-10-30 11:55 | Hernandez, Michael Donald James
12213 | Budget change | 35129436 | 117873017 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Approved | 08W | [6 empty] | Requesting budget of $193,892 for 2020. Requesting $3,361,536 for 2021. Per phase gate review. | 2021-10-18 | 2021-10-18 |  |  | 2021 |  |  |  |  | 193892 | 3361535.78 |  |  |  | PEND |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | M5HF | 2020-10-30 11:50 | Hernandez, Michael Donald James
12212 | Budget change | 35129435 | 117873016 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Approved | 08W | [6 empty] | Requesting budget of $225,846 for 2020. Requesting $3,655,621 for 2021. Per phase gate review. | 2021-07-27 | 2021-07-27 |  |  | 2021 |  |  |  |  | 225846 | 3655621.16 |  |  |  | PEND |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | M5HF | 2020-10-30 11:45 | Hernandez, Michael Donald James
12211 | Budget change | 35129311 | 117873013 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | Approved | 08W | [6 empty] | Requesting budget of $1,028,872 for 2020. Requesting $3,528,928 for 2021. Per phase gate review. | 2021-09-20 | 2021-09-20 |  |  | 2021 |  |  |  |  | 1028872 | 3528928 |  |  |  | PEND |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | M5HF | 2020-10-30 11:41 | Hernandez, Michael Donald James
12210 | Budget change | 35129310 | 117873012 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Approved | 08W | [6 empty] | Requesting budget of $861,191 for 2020. Requesting $2,822,841 for 2021. Per phase gate review. | 2021-08-13 | 2021-08-13 |  |  | 2021 |  |  |  |  | 861191.35 | 2822841.45 |  |  |  | PEND |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | M5HF | 2020-10-30 11:35 | Hernandez, Michael Donald James
12209 | Budget change | 35129309 | 117873011 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | Approved | 08W | [6 empty] | Requesting budget of $235,647 for 2020. Requesting $2866907 for 2021. Per phase gate review. | 2021-10-20 | 2021-10-20 |  |  | 2021 |  |  |  |  | 235647 | 2866906.81 |  |  |  | PEND |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | M5HF | 2020-10-30 11:23 | Hernandez, Michael Donald James
12208 | Budget change | 35129306 | 117872787 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Approved | 08W | [6 empty] | Requesting budget of $605,702 for 2020. Requesting $1,293,508 for 2021. Per phase gate review. | 2021-06-30 | 2021-06-30 |  |  | 2021 |  |  |  |  | 605702 | 1293508 |  |  |  | PEND |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | M5HF | 2020-10-30 11:09 | Hernandez, Michael Donald James
12207 | Budget change | 35095161 | 114708383 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Approved | 08W | [6 empty] | Requesting budget of $117,609 for 2020. Requesting $1,995,462 for 2021. Per phase gate review. | 2021-06-11 | 2021-06-11 |  |  | 2021 |  |  |  |  | 117609 | 1995461.65 |  |  |  | PEND |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | M5HF | 2020-10-30 10:47 | Hernandez, Michael Donald James
12206 | Budget change | 35095161 | 114708383 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Approved | 08W | [6 empty] | Requesting budget of $117,609 for 2020. Requesting $1,995,462 for 2021. As per phase gate review meeting. | 2021-06-11 | 2021-06-11 |  |  | 2021 |  |  |  |  | 117609 | 1995461.65 |  |  |  | PEND |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | M5HF | 2020-10-30 10:43 | Hernandez, Michael Donald James
11642 | Budget change | 35058273 | 114987127 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Approved | 08W | [6 empty] | Need to cover Veg PO increase | 2020-06-26 | 2020-12-31 |  |  | 2020 |  |  |  |  | 2678180 | 0 |  |  |  | FICL | 2020-07-20 |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | T3SQ | 2020-10-29 08:02 | Skarda, Travis Damian
11640 | Budget change | 35115049 | 117497752 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Approved | 08W | [6 empty] | True-up of 2020 RES per instruction from M2Hm and JZSg | 2021-10-06 |  |  |  | 2021 |  |  |  |  | 33000 | 4700000 |  |  |  | ESTS |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | CBN4 | 2020-10-28 12:06 | Nelson, Curtis Barlow
11639 | Budget change | 35115048 | 117497751 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Approved | 08W | [6 empty] | True-up of 2020 RES per instruction from M2Hm and JZSg | 2021-10-06 |  |  |  | 2021 |  |  |  |  | 18500 | 3550000 |  |  |  | ADER |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | CBN4 | 2020-10-28 12:06 | Nelson, Curtis Barlow
11638 | Budget change | 35115047 | 117496281 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | Approved | 08W | [6 empty] | True-up of 2020 RES per instruction from M2Hm and JZSg | 2021-06-11 |  |  |  | 2021 |  |  |  |  | 163000 | 4100000 |  |  |  | PEND |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | CBN4 | 2020-10-28 12:06 | Nelson, Curtis Barlow
11637 | Budget change | 35115046 | 117496177 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Approved | 08W | [6 empty] | True-up of 2020 RES per instruction from M2Hm and JZSg | 2021-09-08 |  |  |  | 2021 |  |  |  |  | 22500 | 4900000 |  |  |  | UNSC |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | CBN4 | 2020-10-28 12:06 | Nelson, Curtis Barlow
11636 | Budget change | 35115057 | 117489824 | CWSP - MIWUK 1701 - OCB - PH2.5 | Approved | 08W | [6 empty] | True-up of 2020 RES per instruction from M2Hm and JZSg | 2021-03-23 |  |  |  | 2021 |  |  |  |  | 127500 | 2750000 |  |  |  | UNSC |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | CBN4 | 2020-10-28 12:06 | Nelson, Curtis Barlow
11635 | Budget change | 35052735 | 114706118 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Approved | 08W | [6 empty] | True-up of 2020 RES per instruction from M2Hm and JZSg | 2021-04-02 |  |  |  | 2021 |  |  |  |  | 140000 | 2600000 |  |  |  | UNSC |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | CBN4 | 2020-10-28 12:06 | Nelson, Curtis Barlow
11633 | Budget change | 35058273 | 114987127 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Withdrawn | 08W | [6 empty] | CO associated with Veg PO needs additional budget to cover | 2020-06-26 | 2020-12-31 |  |  | 2020 |  |  |  |  | 2686180 | 0 |  |  |  | FICL | 2020-07-20 |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Withdrawn | Withdrawn by PM Request | JZSG | 2020-11-03 11:35 | Sadler, Justin R | T3SQ | 2020-10-28 11:24 | Skarda, Travis Damian
11576 | Budget change | 35052825 | 114701195 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Due to contract resources working on fire rebuild project schedule has slipped to 2021 | 2021-04-20 | 2021-06-30 | 2073 | 3544410 | 2021 | 2021 |  | 288570 | 1048628 | 288570 | 1048628 |  |  | 2020-12-31 | CONS |  | 2021-04-20 | A0M6 | Mendez, Angelica | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-01 17:41 | Sadler, Justin R | MXLD | 2020-10-27 07:31
11574 | Update work plan date | 35052825 | 114701195 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Due to fire rebuild resources have been moved off this project resulting in construction being defered until 2021 | 2021-04-20 | 2021-05-31 | 2073 | 3544410 | 2021 | 2021 |  | 288570 | 1048628 |  |  |  |  | 2020-12-31 | CONS |  | 2021-04-20 | A0M6 | Mendez, Angelica | Critical Work |  |  |  |  | Approved |  | Approved | Resource impacted due to fire | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-12 19:29 | Sadler, Justin R | MXLD | 2020-10-27 07:10
11387 | Budget change | 35095167 | 114832579 | CWSP - STANISLAUS 1702 - LR1888 - PH 2.1 | Approved | 08W | [6 empty] | CWSP 2020 Activated Reserve pushed into 2021. | 2021-04-16 | 2021-05-31 |  |  | 2021 |  |  |  |  | 282834 | 2083119 |  |  |  | PEND |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-23 16:53 | Sadler, Justin R | R4BA | 2020-10-22 13:26 | Barron, Raul Angelo
11385 | Budget change | 35116516 | 117608020 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.3 | Approved | 08W | [6 empty] | CWSP 2020 Activated Reserve pushed into 2021. | 2021-06-04 | 2021-06-04 |  |  | 2021 |  |  |  |  | 387975 | 1851047 |  |  |  | PEND |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-23 16:53 | Sadler, Justin R | R4BA | 2020-10-22 13:26 | Barron, Raul Angelo
11384 | Budget change | 35116515 | 117607998 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.2 | Approved | 08W | [6 empty] | CWSP 2020 Activated Reserve pushed into 2021. | 2021-07-07 | 2021-07-07 |  |  | 2021 |  |  |  |  | 517463 | 2685572 |  |  |  | UNSC |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-23 16:53 | Sadler, Justin R | R4BA | 2020-10-22 13:26 | Barron, Raul Angelo
11388 | Budget change | 35114041 | 117500692 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Approved | 08W | [6 empty] | GC pulled for fire restoration, construction continue Q1 2021. | 2021-01-22 | 2021-03-31 |  |  | 2020 |  |  |  |  | 554619 | 1156148 |  |  |  | CONS |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-23 16:53 | Sadler, Justin R | R4BA | 2020-10-22 13:24 | Barron, Raul Angelo
11386 | Budget change | 35114048 | 117499466 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | GC pulled for fire restoration, construction continue Q1 2021. | 2020-08-14 | 2021-02-28 | 1828 | 4178929 | 2020 | 2021 |  | 1323768 | 1810131 | 1323768 | 1810131 |  |  | 2021-12-31 | CONS |  | 2020-08-14 | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-23 16:53 | Sadler, Justin R | R4BA | 2020-10-22 13:20 | Barron, Raul Angelo
11383 | Update work plan date | 35114040 | 117500499 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Project involves Caltrans DSDD. Land is in the process of preparing basemap to revise drawings. | 2020-07-29 | 2021-04-30 | 4154.9 | 4232824 | 2020 | 2022 |  | 3110000 | 1676839.1 | 1150000 | 1750000 |  |  | 2019-12-06 | CONS |  | 2020-07-29 | J1PE | Pantoja-Martinez, Jaime | Critical Work |  |  |  |  | Approved |  | Approved | LAND in process | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-11-12 19:29 | Sadler, Justin R | J1PE | 2020-10-22 12:42 | Pantoja-Martinez, Jaime
11291 | Budget change | 31098626 | 108895192 | CLARKSVILLE 2104 RECONDUCTOR -PH 3 Y2018 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | DO Calendar closed due to fires & PSPS | 2018-07-16 | 2020-12-31 | 2526.2 | 1543425 | 2020 |  |  | 775000 |  | 775000 | 0 |  |  | 2017-12-29 | FICL | 2020-11-10 | 2018-07-16 | BER5 | Ritchie, Brian | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-23 16:53 | Sadler, Justin R | BER5 | 2020-10-22 11:55 | Ritchie, Brian
11255 | Budget change | 35113103 | 117492227 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.3 | Approved | 08W | [6 empty] | Contingency Release $50,000 due to over-run of Contracts and associated overheads |  | 2020-10-30 | [7 empty] | 48205 | 0 | [6 empty] | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-23 16:53 | Sadler, Justin R | VBA1 | 2020-10-21 23:30 | Alcantara, Violeta
11252 | Budget change | 35103324 | 117251430 | CWSP - ROSSMOOR 1102 - OCB | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Unexpected estimating charges | 2020-10-30 | 2020-10-30 | 1360.6 | 2510809 | 2020 |  |  | 654743 |  | 654743 |  |  |  | 2020-12-31 | FICL |  |  | PXSO | Siu, Peter | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-23 16:53 | Sadler, Justin R | PXSO | 2020-10-21 20:22 | Siu, Peter
11253 | Budget change | 35116802 | 117605267 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Increase in overhead costs, vegetation costs, and unexpected estimating charges. | 2020-06-16 | 2020-10-30 | 2139.5 | 2559279 | 2020 |  |  | 2446652 | 53034.5 | 2446652 |  |  |  | 2020-12-31 | DOCC | 2020-12-15 | 2020-06-16 | PXSO | Siu, Peter | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-23 16:53 | Sadler, Justin R | PXSO | 2020-10-21 20:21 | Siu, Peter
11205 | RCR - Change or Assign Resource | 35144941 | 118261469 | PSPS - PAUL SWEET 2105 - CB PH 1 | Approved | 08W |  |  |  |  | Contract | GC | PSPS Mitigation project, commitment to finish by 8/31/21 (before fire season). There could be summer load restrictions that would require this project be completed by 6/30/21. Requesting that civil work be completed by contractor to meet deadline. | 2021-04-12 |  |  |  | 2021 | [8 empty] | 2021-04-30 | PEND |  |  | M1NO | Nguyen, My-Linh | [7 empty] | Approved | Per 11/19/2020 discussion with GC, GC will be the electric assigned resource for 2021,must complete before 8/2021 | Merih Tekeste |  |  |  | Approved |  | SFSS | 2020-11-19 19:42 | Saraf, Shubham | M1NO | 2020-10-19 11:07 | Nguyen, My-Linh
11196 | Resource change | 35145001 | 118259181 | PSPS - CLAYTON 2215 - CB | Approved | 08W |  |  |  |  | Contract | GC | Timing - +/- 10,000' of trenching = +/- 8000 MH Civil | 2021-09-07 |  |  |  | 2021 | [9 empty] | PEND |  |  | M1NO | Nguyen, My-Linh | [7 empty] | Approved | Civil request, Electric to follow, GC noted as the electric resource | Merih Tekeste |  |  |  | Approved |  | CRV4 | 2020-10-23 07:41 | Reyes, Christina R | J91F | 2020-10-19 10:14 | Stabe, Justin M
10919 | RCR - Change or Assign Resource | 35118663 | 117670940 | BR-01-01-W (E) HEAVENS GATE PARB | Approved | 08W |  |  |  | Contract | N/A | Contract | Additional resource update to Contract | 2020-04-23 |  | 3321.9 | 1772954.66 | 2021 |  |  |  | 41246.6 |  |  |  |  | 2020-12-26 | CONS |  | 2020-04-23 | M0S4 | Shaeffer, Michael J | [7 empty] | Approved |  | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-23 16:53 | Sadler, Justin R | ATSC | 2020-10-16 09:27 | Spreen, Andrew
10917 | RCR - Change or Assign Resource | 35105646 | 117306439 | BR-03-05-W (E) DEAN RD, PARB | Approved | 08W |  |  |  |  | N/A | Contract | Additional resource update to Contract | [14 empty] | CONS |  |  | M0S4 | Shaeffer, Michael J | [7 empty] | Approved |  | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-23 16:53 | Sadler, Justin R | ATSC | 2020-10-16 09:27 | Spreen, Andrew
10918 | RCR - Change or Assign Resource | 35110556 | 117402466 | BR-04-12-W (E) SUBSTATION/PATH PARB | Approved | 08W |  |  |  | Contract | N/A | Contract | Additional resource update to Contract |  |  | 3588 | 1 | 2020 | 2021 | [7 empty] | 2019-12-27 | ESTS |  |  | M0S4 | Shaeffer, Michael J | [7 empty] | Approved |  | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-23 16:53 | Sadler, Justin R | ATSC | 2020-10-16 09:27 | Spreen, Andrew
10921 | RCR - Change or Assign Resource | 35112220 | 117463683 | BR-04-06-W (E) VALLEY RIDGE PARB | Approved | 08W |  |  |  |  | N/A | Contract | Additional resource update to Contract | [14 empty] | CONS |  |  | M0S4 | Shaeffer, Michael J | [7 empty] | Approved |  | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-23 16:53 | Sadler, Justin R | ATSC | 2020-10-16 09:27 | Spreen, Andrew
10525 | Budget change | 35112076 | 117440386 | OCGC FULTON 1107-OH TO UG MARK W SPG | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Addition dollars to cover estimating correction and closeout | 2020-03-23 |  | 3025.9 | 5750000 | 2020 |  |  | 950000 |  | 950000 |  |  |  | 2019-11-30 | MAPP | 2020-04-06 |  | S2WT | Whitman, Steve | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-16 13:46 | Sadler, Justin R | HAMG | 2020-10-15 10:37 | Marshall, Holly Ann
10524 | Update work plan date | 35115849 | 117602058 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Approved | 08W | [6 empty] | Moving 08W project to 2021 due to budget and crew constraints | 2021-02-09 | 2021-03-01 |  |  | 2020 | [5 empty] | 2922407 |  |  |  | PEND |  |  | A0M6 | Mendez, Angelica | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | A0M6 | 2020-10-15 09:13 | Mendez, Angelica
10520 | Update work plan date | 35052825 | 114701195 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Fire rebuild has taken away resources | 2021-04-20 | 2021-06-30 | 2073 | 3544410 | 2021 | 2021 |  | 288570 | 1048628 | 300000 | 1250000 |  |  | 2020-12-31 | CONS |  | 2021-04-20 | A0M6 | Mendez, Angelica | Critical Work |  |  |  |  | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | MXLD | 2020-10-15 06:04
10446 | Budget change | 35145006 | 118263874 | PSPS - STAFFORD 1101 LR 1298 | Approved | 08W | [6 empty] | Additional funds needed to cover estimating, dependency costs in 2020 | 2021-06-29 | 2021-06-29 |  |  | 2021 |  |  |  |  | 120000 |  |  |  |  | PEND |  |  | DWPH | Phillips, David William | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-16 13:46 | Sadler, Justin R | HAMG | 2020-10-14 13:34 | Marshall, Holly Ann
10434 | Add project | 35206138 |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.5 | Approved | 08W | [6 empty] | Add to 2022 work plan | 2022-12-31 | [13 empty] | UNSE |  |  | PJMW | Mccabe, Patrick James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-16 13:46 | Sadler, Justin R | E2P9 | 2020-10-14 08:45 | Perryman, Eric Chase
10433 | Add project | 35206136 |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.4 | Approved | 08W | [6 empty] | Add to 2022 work plan | 2022-12-31 | [13 empty] | UNSE |  |  | PJMW | Mccabe, Patrick James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-16 13:46 | Sadler, Justin R | E2P9 | 2020-10-14 08:45 | Perryman, Eric Chase
10432 | Add project | 35206135 |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.3 | Approved | 08W | [6 empty] | Add to 2022 work plan | 2022-12-31 | [13 empty] | UNSE |  |  | PJMW | Mccabe, Patrick James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-16 13:46 | Sadler, Justin R | E2P9 | 2020-10-14 08:45 | Perryman, Eric Chase
10431 | Add project | 35206134 |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.2 | Approved | 08W | [6 empty] | Add to 2022 work plan | 2022-12-31 | [13 empty] | UNSE |  |  | PJMW | Mccabe, Patrick James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-16 13:46 | Sadler, Justin R | E2P9 | 2020-10-14 08:44 | Perryman, Eric Chase
10430 | Update work plan date | 35051472 |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3 | Approved | 08W | [6 empty] | Add to 2022 work plan | 2022-12-31 | 2022-12-31 | [7 empty] | 0 | 0 |  |  |  | ESTS |  |  | MXUA | Ung, Mason | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 13:46 | Sadler, Justin R | E2P9 | 2020-10-14 08:32 | Perryman, Eric Chase
10422 | Update work plan date | 35174474 |  | ECOP-CALISTOGA 1101-H01-LR736 PH1 | Approved | 08W | [6 empty] | 2032 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 20000 | 480000 |  |  |  | UNSE |  |  | PJMW | Mccabe, Patrick James | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | J91F | 2020-10-13 15:54 | Stabe, Justin M
10424 | Update work plan date | 35174466 |  | ECOP-EL DORADO 2101-H02-LR6852-PH3 | Approved | 08W | [6 empty] | 2034 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 15000 | 485000 |  |  |  | UNSE |  |  | T3SQ | Skarda, Travis Damian | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | J91F | 2020-10-13 15:54 | Stabe, Justin M
10425 | Update work plan date | 35174478 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Approved | 08W | [6 empty] | 2035 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 10000 | 490000 |  |  |  | UNSE |  |  | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | J91F | 2020-10-13 15:54 | Stabe, Justin M
10426 | Update work plan date | 35174479 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Approved | 08W | [6 empty] | 2036 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 15000 | 485000 |  |  |  | UNSE |  |  | M1NO | Nguyen, My-Linh | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | J91F | 2020-10-13 15:54 | Stabe, Justin M
10427 | Update work plan date | 35174501 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Approved | 08W | [6 empty] | 2037 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 10000 | 490000 |  |  |  | UNSE |  |  | SFMT | Moraga, Steven | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | J91F | 2020-10-13 15:54 | Stabe, Justin M
10423 | Update work plan date | 35173756 |  | ECOP-EL DORADO 2101-H02-LR6852-PH2 | Approved | 08W | [6 empty] | 2033 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 10000 | 490000 |  |  |  | UNSE |  |  | T3SQ | Skarda, Travis Damian | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | J91F | 2020-10-13 15:54 | Stabe, Justin M
10420 | Update work plan date | 35095164 |  | CWSP-ORO FINO 1101 LR-2022 PH 3.1 | Approved | 08W | [6 empty] | 2030 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 200000 | 300000 |  |  |  | UNSC |  |  | S4K5 | Krenek, Scot | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | J91F | 2020-10-13 15:54 | Stabe, Justin M
10421 | Update work plan date | 35173754 |  | ECOP-BRUNSWICK 1106-H08-LR51486 | Approved | 08W | [6 empty] | 2031 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 10000 | 490000 |  |  |  | UNSE |  |  | J6KF | Kringler, Jeff L | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | J91F | 2020-10-13 15:54 | Stabe, Justin M
10411 | Update work plan date | 35129618 |  | CWSP - ORO FINO 1101 - LR2022 PH 1.4 | Approved | 08W | [6 empty] | 2021 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 30000 | 470000 |  |  |  | PEND |  |  | S4K5 | Krenek, Scot | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | J91F | 2020-10-13 15:54 | Stabe, Justin M
10412 | Update work plan date | 35129642 |  | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Approved | 08W | [6 empty] | 2022 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 30000 | 470000 |  |  |  | PEND |  |  | S4K5 | Krenek, Scot | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | J91F | 2020-10-13 15:54 | Stabe, Justin M
10413 | Update work plan date | 35129648 |  | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Approved | 08W | [6 empty] | 2023 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 10000 | 490000 |  |  |  | ESTS |  |  | S4K5 | Krenek, Scot | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | J91F | 2020-10-13 15:54 | Stabe, Justin M
10414 | Update work plan date | 35129616 |  | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | Approved | 08W | [6 empty] | 2024 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 45000 | 455000 |  |  |  | PEND |  |  | S4K5 | Krenek, Scot | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | J91F | 2020-10-13 15:54 | Stabe, Justin M
10415 | Update work plan date | 35129617 |  | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | Approved | 08W | [6 empty] | 2025 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 30000 | 470000 |  |  |  | PEND |  |  | S4K5 | Krenek, Scot | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | J91F | 2020-10-13 15:54 | Stabe, Justin M
10416 | Update work plan date | 35129619 |  | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | Approved | 08W | [6 empty] | 2026 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 30000 | 470000 |  |  |  | PEND |  |  | S4K5 | Krenek, Scot | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | J91F | 2020-10-13 15:54 | Stabe, Justin M
10417 | Update work plan date | 35129640 |  | CWSP - ORO FINO 1101 - LR2022 PH 1.6 | Approved | 08W | [6 empty] | 2027 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 30000 | 470000 |  |  |  | PEND |  |  | S4K5 | Krenek, Scot | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | J91F | 2020-10-13 15:54 | Stabe, Justin M
10418 | Update work plan date | 35129641 |  | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Approved | 08W | [6 empty] | 2028 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 45000 | 455000 |  |  |  | PEND |  |  | S4K5 | Krenek, Scot | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | J91F | 2020-10-13 15:54 | Stabe, Justin M
10419 | Update work plan date | 35094514 |  | CWSP-ORO FINO 1101 LR-2022 PH 1.1 | Approved | 08W | [6 empty] | 2029 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 75000 | 425000 |  |  |  | PEND |  |  | S4K5 | Krenek, Scot | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | J91F | 2020-10-13 15:54 | Stabe, Justin M
10410 | Update work plan date | 35046371 |  | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Approved | 08W | [6 empty] | defining as 2022 at assett managments request |  | 2022-12-31 | [7 empty] | 30000 | 470000 |  |  |  | PROD |  |  | SZC1 | Chen, Scott | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-10-16 14:30 | Sadler, Justin R | J91F | 2020-10-13 15:54 | Stabe, Justin M
10098 | Budget change | 35052739 | 114567186 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Approved | 08W | [6 empty] | Legacy approved Budget | 2020-11-19 |  |  |  | 2020 |  |  |  |  | 5180025 |  |  |  |  | CONS |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2020-10-11 23:50 | Saraf, Shubham | SFSS | 2020-10-11 23:45 | Saraf, Shubham
10057 | RCR - Change or Assign Resource | 35112220 | 117463683 | BR-04-06-W (E) VALLEY RIDGE PARB | Approved | 08W |  |  |  |  | N/A | Contract | Resource change from GC to Contract due to GC emergency response deployment | [14 empty] | CONS |  |  | M0S4 | Shaeffer, Michael J | [7 empty] | Approved |  | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-09 16:31 | Sadler, Justin R | ATSC | 2020-10-09 09:53 | Spreen, Andrew
10053 | RCR - Change or Assign Resource | 35105646 | 117306439 | BR-03-05-W (E) DEAN RD, PARB | Approved | 08W |  |  |  |  | N/A | Contract | Resource change from GC to Contract due to GC emergency response deployment | [14 empty] | CONS |  |  | M0S4 | Shaeffer, Michael J | [7 empty] | Approved |  | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-09 16:31 | Sadler, Justin R | ATSC | 2020-10-09 09:53 | Spreen, Andrew
10048 | RCR - Change or Assign Resource | 35095246 | 117164122 | BUCOCAMP - ERIKA DRIVE, PARADISE | Approved | 08W |  |  |  |  | N/A | Contract | Resource change from GC to Contract due to GC emergency response deployment | [14 empty] | UNSC |  |  | S4K5 | Krenek, Scot | [7 empty] | Approved |  | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-09 16:31 | Sadler, Justin R | ATSC | 2020-10-09 09:53 | Spreen, Andrew
10081 | RCR - Change or Assign Resource | 35141837 | 118195513 | *CANC*BR-04-01-W (E) SUNSET DR PARB | Approved | 08W |  |  |  |  | N/A | Contract | Resource change from GC to Contract due to GC emergency response deployment | [14 empty] | PROD |  |  | AVP4 | Patane, Aaron | [7 empty] | Approved |  | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-09 16:31 | Sadler, Justin R | ATSC | 2020-10-09 09:53 | Spreen, Andrew
10058 | RCR - Change or Assign Resource | 35118663 | 117670940 | BR-01-01-W (E) HEAVENS GATE PARB | Approved | 08W |  |  |  | Contract | N/A | Contract | Resource change from GC to Contract due to GC emergency response deployment | 2020-04-23 |  | 3321.9 | 1772954.66 | 2021 |  |  |  | 41246.6 |  |  |  |  | 2020-12-26 | CONS |  | 2020-04-23 | M0S4 | Shaeffer, Michael J | [7 empty] | Approved |  | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-09 16:31 | Sadler, Justin R | ATSC | 2020-10-09 09:53 | Spreen, Andrew
9206 | Add project | 35161152 |  | OCT2019 BRICEBURG FIRE REBUILD | Approved | 08W | [6 empty] | Wild Fire Rebuild | 2021-04-01 | [8 empty] | 375186 | 1138733 |  |  |  | UNSC |  |  | SGBA | Barrow, Steve | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-10-09 16:31 | Sadler, Justin R | SGBA | 2020-10-02 11:54 | Barrow, Steve
8637 | Budget change | 35112435 | 117472561 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | requesting addational $805,821 due to realse contingency | 2020-05-31 | 2020-12-31 | 5177.2 | 4061849 | 2020 |  |  | 2068858.2 |  | 2874679 |  |  |  | 2020-12-31 | DOCC |  |  | CRGN | Gras, Christopher R | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-09-25 15:28 | Sadler, Justin R | ZXAC | 2020-09-23 11:49 | Al-Saffar, Zaid Dhafer Hashim
8631 | Update work plan date | 35115154 |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 725000 | 399656.8 |  |  |  | CONS |  |  | T3SQ | Skarda, Travis Damian | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-09-29 09:44 | Sadler, Justin R | J91F | 2020-09-22 15:36 | Stabe, Justin M
8629 | Update work plan date | 35115152 |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 370000 | 1188363.6 |  |  |  | CONS |  |  | T3SQ | Skarda, Travis Damian | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-09-29 09:44 | Sadler, Justin R | J91F | 2020-09-22 15:34 | Stabe, Justin M
8627 | Update work plan date | 35114041 |  | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 325000 | 1090171.7 |  |  |  | CONS |  |  | R4BA | Barron, Raul Angelo | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-09-29 09:44 | Sadler, Justin R | J91F | 2020-09-22 15:32 | Stabe, Justin M
8626 | Update work plan date | 35115853 |  | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 200000 | 1189127.5 |  |  |  | UNSC |  |  | A0M6 | Mendez, Angelica | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-09-29 09:44 | Sadler, Justin R | J91F | 2020-09-22 15:31 | Stabe, Justin M
8625 | Update work plan date | 35115153 |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Approved | 08W | [6 empty] | Defer due to fire rebuild work | 2020-06-29 | 2021-12-31 | [7 empty] | 410000 | 1491841.1 |  |  |  | CONS |  |  | T3SQ | Skarda, Travis Damian | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-09-29 09:44 | Sadler, Justin R | J91F | 2020-09-22 15:30 | Stabe, Justin M
8621 | Update work plan date | 35052739 |  | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 620000 | 1101941.4 |  |  |  | CONS |  |  | FXA7 | Armas, Fernando | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-09-29 09:44 | Sadler, Justin R | J91F | 2020-09-22 15:27 | Stabe, Justin M
8630 | Update work plan date | 35116388 |  | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 200000 | 2483533.4 |  |  |  | PEND |  |  | FXA7 | Armas, Fernando | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-09-29 09:44 | Sadler, Justin R | J91F | 2020-09-22 15:01 | Stabe, Justin M
8628 | Update work plan date | 35115052 |  | CWSP - MIWUK 1701_OCB - PH 1.4 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 200000 | 1664060 |  |  |  | CONS |  |  | FXA7 | Armas, Fernando | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-09-29 09:44 | Sadler, Justin R | J91F | 2020-09-22 15:01 | Stabe, Justin M
8624 | Update work plan date | 35113951 |  | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 200000 | 1582293.6 |  |  |  | UNSC |  |  | SLKD | Kennedy, Sharon | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-09-29 09:44 | Sadler, Justin R | J91F | 2020-09-22 15:01 | Stabe, Justin M
8623 | Update work plan date | 35115051 |  | CWSP - MIWUK 1701_OCB - PH 1.3 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 180000 | 1042881.3 |  |  |  | CONS |  |  | FXA7 | Armas, Fernando | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-09-29 09:44 | Sadler, Justin R | J91F | 2020-09-22 15:01 | Stabe, Justin M
8622 | Update work plan date | 35113950 |  | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 180000 | 2226592 |  |  |  | PEND |  |  | SLKD | Kennedy, Sharon | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-09-29 09:44 | Sadler, Justin R | J91F | 2020-09-22 15:01 | Stabe, Justin M
8620 | Update work plan date | 35052731 |  | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 220000 | 2129616.4 |  |  |  | PEND |  |  | SLKD | Kennedy, Sharon | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-09-29 09:44 | Sadler, Justin R | J91F | 2020-09-22 14:50 | Stabe, Justin M
8619 | Update work plan date | 31361965 |  | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 250000 | 986551.1 |  |  |  | CONS |  |  | J1E1 | Eagar, Josh | [5 empty] | Approved |  | Approved | Project defered as identified in business justification | Merih Tekeste |  |  |  | Approved | Does not require WRFR approval | JZSG | 2020-09-29 09:44 | Sadler, Justin R | J91F | 2020-09-22 14:50 | Stabe, Justin M
8579 | Resource change | 35129601 | 117873032 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Approved | 08W | [5 empty] | GC | Work assignment to GC | 2021-11-09 |  |  |  | 2021 | [9 empty] | PEND |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-09-18 14:57 | Sadler, Justin R | ATSC | 2020-09-18 10:53 | Spreen, Andrew
8580 | Resource change | 35129609 | 117873070 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Approved | 08W | [5 empty] | GC | Work Assignment to GC | 2021-11-05 |  |  |  | 2021 | [9 empty] | PEND |  |  | S4K5 | Krenek, Scot | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-09-18 14:57 | Sadler, Justin R | ATSC | 2020-09-18 10:53 | Spreen, Andrew
8516 | Budget change | 35095166 | 114742467 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | requesting $850,379 addational budget to be allocated in 2020 due to release contingency. | 2020-08-06 | 2020-12-31 | 4104 | 3293522 | 2020 |  |  | 1538336.7 |  | 2388716 |  |  |  | 2019-12-31 | DOCC |  |  | CRGN | Gras, Christopher R | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-09-18 14:57 | Sadler, Justin R | ZXAC | 2020-09-17 09:36 | Al-Saffar, Zaid Dhafer Hashim
8513 | Add project | 35112972 | 117491267 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Approved | 08W | [6 empty] | Connection of 3rd phase for segment 3 on PM# 35112973 is not possible without first constructing segment 2 on PM# 35112972 | 2021-07-31 | [9 empty] | 1614773 |  |  |  | ESTS |  |  | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Approved | 2021 project, confirmed with J. Stabe | JZSG | 2020-09-18 15:30 | Sadler, Justin R | J1PE | 2020-09-16 11:28 | Pantoja-Martinez, Jaime
8429 | Budget change | 35115852 | 117602171 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Approved | 08W | [6 empty] | 08W Fire Hardening Project Optimized Budget Request | 2021-07-16 | 2021-07-16 |  |  | 2021 |  |  |  |  | 0 | 3346858.76 |  |  |  | UNSC |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-09-18 14:57 | Sadler, Justin R | A0M6 | 2020-09-15 13:51 | Mendez, Angelica
8285 | Budget change | 35115057 | 117489824 | CWSP - MIWUK 1701 - OCB - PH2.5 | Approved | 08W | [7 empty] | 2021-03-23 |  |  |  | 2021 |  |  |  |  | 30000 | 2996000 |  |  |  | UNSC |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-09-11 15:12 | Sadler, Justin R | M2HM | 2020-09-08 13:40 | Herron, Matthew Joseph
8265 | Budget change | 35129601 | 117873032 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Approved | 08W | [6 empty] | requesting additional budget $546,369 for veg work after phase gate review meeting | 2021-10-29 |  |  |  | 2021 |  |  |  |  | 546863 |  |  |  |  | PEND |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-09-11 15:12 | Sadler, Justin R | M5HF | 2020-09-04 13:58 | Hernandez, Michael Donald James
7894 | Resource change | 35144944 |  | PSPS - SNEATH LANE 1107 - LR 48338 | Approved | 08W | [5 empty] | Contract | To Contract per request from Cathy | [14 empty] | PEND |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-09-04 14:21 | Sadler, Justin R | ATSC | 2020-09-03 17:09 | Spreen, Andrew
7770 | Budget change | 35115856 | 117601688 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Approved | 08W | [6 empty] | 08W Fire Hardening Project Optimized budget request | 2021-03-15 | 2020-12-18 | [7 empty] | 3491056 |  |  |  |  | UNSC |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-09-03 11:05 | Sadler, Justin R | A0M6 | 2020-09-01 08:38 | Mendez, Angelica
7752 | Budget change | 35116396 | 117604756 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Approved | 08W | [6 empty] | Need adjustment for vegetation management contract in 2020 | 2021-11-23 | 2020-09-01 | [7 empty] | 875000 | 3457000 |  |  |  | CONS |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-09-03 11:05 | Sadler, Justin R | PRE2 | 2020-08-31 09:26 | Espinola, Paul R
7541 | Budget change | 35115152 | 117495855 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Approved | 08W |  |  |  | GC |  |  | Change Request will be submitted to reduce 2020 MPP budget by $943,013.01 to be $2,611,485.99. Also, CR will be submitted to increse 2021 MPP budget by $67,999,.82 | 2021-05-31 | 2020-12-31 | 4541.7 | 3591121 | 2021 |  |  | 3558481.2 | 2229051.5 | 2611485.99 | 67999.82 |  |  | 2020-12-31 | CONS |  | 2021-05-31 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-08-28 18:59 | Sadler, Justin R | T3SQ | 2020-08-26 13:27 | Skarda, Travis Damian
7539 | Budget change | 35142827 | 118218951 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Approved | 08W | [6 empty] | Returning $206,728.59 to align with 2020 forecast per Gateway Review Meeting held 8/24/2020, and shifting $43,741 to 2021 budget. | 2021-03-30 | 2020-12-31 | [7 empty] | 1758524.99 | 43741.12 |  |  |  | PEND |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-08-28 18:59 | Sadler, Justin R | T3SQ | 2020-08-25 09:37 | Skarda, Travis Damian
7537 | Budget change | 35115858 | 117601885 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Approved | 08W | [6 empty] | 08W Fire Hardening Project Optimized Budget Request | 2021-02-11 | 2021-11-20 | [7 empty] | 2216657 |  |  |  |  | UNSC |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-08-28 18:59 | Sadler, Justin R | A0M6 | 2020-08-24 15:56 | Mendez, Angelica
7536 | Budget change | 35115848 | 117602057 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Approved | 08W | [6 empty] | 08W Fire Hardening Project Optimized Budget Request | 2021-06-22 | 2020-11-20 | [7 empty] | 2672610 |  |  |  |  | UNSC |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-08-28 18:59 | Sadler, Justin R | A0M6 | 2020-08-24 15:54 | Mendez, Angelica
7534 | Budget change | 35115854 | 117601685 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Approved | 08W | [6 empty] | 08W Fire Hardening Project Optimized Budget Ree\quest | 2021-03-04 | [8 empty] | 2138614 | 0 |  |  |  | CONS |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-08-28 18:59 | Sadler, Justin R | A0M6 | 2020-08-24 15:51 | Mendez, Angelica
7531 | Budget change | 35114045 | 117502843 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Approved | 08W | [6 empty] | 08W Fire Hardening Project Optimized Budget Request | 2021-03-10 | [8 empty] | 0 | 3021946 |  |  |  | UNSC |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-08-28 18:59 | Sadler, Justin R | A0M6 | 2020-08-24 15:49 | Mendez, Angelica
7529 | Budget change | 35114052 | 117502368 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Approved | 08W | [6 empty] | 08W Fire Hardening Project optimized budget Request | 2021-03-19 | 2021-03-19 | [7 empty] | 0 | 2022612 |  |  |  | UNSC |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-08-28 18:59 | Sadler, Justin R | A0M6 | 2020-08-24 15:47 | Mendez, Angelica
7054 | Budget change | 35116385 | 117604609 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Approved | 08W | [6 empty] | Bids received and reduced project cost | 2021-02-05 | 2021-02-05 | [7 empty] | 0 | 2815000 |  |  |  | PEND |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-08-24 08:22 | Sadler, Justin R | M2HM | 2020-08-18 11:50 | Herron, Matthew Joseph
6998 | Resource change | 35052735 | 114706118 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Approved | 08W | [5 empty] | GC | 8/12 - Assign to GC | 2021-04-02 | [13 empty] | UNSC |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-08-14 17:25 | Sadler, Justin R | ATSC | 2020-08-14 12:01 | Spreen, Andrew
5928 | Resource change | 35103065 |  | CWSP - MORAGA 1101 - LR 108540 PH 1 | Approved | 08W | [5 empty] | Contract | Carry over projects from 2019 to go to contract | [14 empty] | FICL | 2019-12-18 |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-08-14 17:25 | Sadler, Justin R | ATSC | 2020-08-13 19:14 | Spreen, Andrew
5929 | Resource change | 35110442 |  | CWSP-VOLTA 1102-LR 1648-PH3.2 | Approved | 08W | [5 empty] | Contract | Carry over projects from 2019 to go to contract | [14 empty] | FICL | 2020-05-28 |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-08-14 17:25 | Sadler, Justin R | ATSC | 2020-08-13 19:14 | Spreen, Andrew
5930 | Resource change | 35110445 |  | CWSP-VOLTA 1102-LR 1648-PH4.2 | Approved | 08W | [5 empty] | Contract | Carry over projects from 2019 to go to contract | [14 empty] | MAPP | 2020-07-01 |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-08-14 17:25 | Sadler, Justin R | ATSC | 2020-08-13 19:14 | Spreen, Andrew
5931 | Resource change | 35112426 |  |  | Approved | 08W | [5 empty] | Contract | Carry over projects from 2019 to go to contract | [28 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-08-14 17:25 | Sadler, Justin R | ATSC | 2020-08-13 19:14 | Spreen, Andrew
5838 | Budget change | 35053033 | 114688204 | CWSP - TASSAJARA 2112 - FUSE 18053 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Request additional $608,000 required for reauthorization. Environmental remediation and monitoring through fall/winter in reseeding areas needed. This is the only work that is remaining. | 2019-12-03 | 2020-11-01 | 11746.9 | 9709000 | 2020 |  |  | 5741528.5 | 368855 | 8728000 | 0 |  |  | 2019-12-31 | FICL | 2021-01-13 | 2019-12-03 | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-08-14 17:25 | Sadler, Justin R | LLM0 | 2020-08-10 08:28 | Swartz, Linda L
5837 | Update work plan date | 30977615 | 106691315 | WDDB OTTER 1102 PHASE 5 | Approved | 08W | [6 empty] | Due to numerous site constraints impacting all 3 Otter projects e.g. The Forest Service stated new LZ/Staging Yard location has cultural concerns, Right of Entry process with State Parks and request to perform a valuation to assist with determining a Rent value for staging of the Generators and potential cost for noise output of the Generators, location of temporary pole/line runs, trailer staging areas, vehicle staging areas, equipment staging areas etc. If reopening to tours occurs prior to or at any time mid-stage during PG&E occupying the site then PG&E to compensate for lost tour revenue. | 2019-12-15 | 2020-10-29 | [7 empty] | 146307 | 974597 |  |  |  | UNSC |  |  | SLKD | Kennedy, Sharon | [5 empty] | Approved |  | Approved |  | Merih Tekeste |  |  |  | Approved | Confirmed with Justin Stabe 08.24.20 | JZSG | 2020-08-24 09:55 | Sadler, Justin R | VBA1 | 2020-08-07 17:11 | Alcantara, Violeta
5836 | Update work plan date | 30977614 | 106691314 | WDDB OTTER 1102 PHASE 4 | Approved | 08W | [6 empty] | Due to numerous site constraints impacting all 3 Otter projects e.g. The Forest Service stated new LZ/Staging Yard location has cultural concerns, Right of Entry process with State Parks and request to perform a valuation to assist with determining a Rent value for staging of the Generators and potential cost for noise output of the Generators, location of temporary pole/line runs, trailer staging areas, vehicle staging areas, equipment staging areas etc. If reopening to tours occurs prior to or at any time mid-stage during PG&E occupying the site then PG&E to compensate for lost tour revenue. | 2019-12-15 | 2020-10-29 | [7 empty] | 182209 | 1035817 |  |  |  | UNSC |  |  | SLKD | Kennedy, Sharon | [5 empty] | Approved |  | Approved |  | Merih Tekeste |  |  |  | Approved | Confirmed with Justin Stabe 08.24.20 | JZSG | 2020-08-24 09:55 | Sadler, Justin R | VBA1 | 2020-08-07 17:08 | Alcantara, Violeta
5835 | Update work plan date | 30977613 | 106691313 | WDDB OTTER 1102 PHASE 3 | Approved | 08W | [6 empty] | Due to numerous site constraints impacting all 3 Otter projects e.g. The Forest Service stated new LZ/Staging Yard location has cultural concerns, Right of Entry process with State Parks and request to perform a valuation to assist with determining a Rent value for staging of the Generators and potential cost for noise output of the Generators, location of temporary pole/line runs, trailer staging areas, vehicle staging areas, equipment staging areas etc. If reopening to tours occurs prior to or at any time mid-stage during PG&E occupying the site then PG&E to compensate for lost tour revenue. | 2019-12-15 | 2020-10-29 | [7 empty] | 177310 | 1905941 |  |  |  | PEND |  |  | SLKD | Kennedy, Sharon | [5 empty] | Approved |  | Approved |  | Merih Tekeste |  |  |  | Approved | Confirmed with Justin Stabe 08.24.20 | JZSG | 2020-08-24 09:55 | Sadler, Justin R | VBA1 | 2020-08-07 16:59 | Alcantara, Violeta
5547 | Budget change | 35052820 | 114580704 | CWSP - MIWUK 1702 - OCB - PH 1.1 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Contengency release | 2020-04-24 |  | 4109.5 | 3585097 | 2020 |  |  | 3516246 | 91962 | 3516246 |  |  |  | 2020-12-31 | FICL | 2020-08-04 | 2020-04-24 | PXSO | Siu, Peter | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-08-07 16:37 | Sadler, Justin R | JMVH | 2020-08-05 08:23 | Vogt, John
5539 | Update work plan date | 31334291 | 117065226 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Approved | 08W | [6 empty] | Job requires coastal commission permit (6 month lead time) causing a job ready date of 2021. | 2020-03-31 | 2021-02-05 | [7 empty] | 150000 | 741459 |  |  |  | PEND |  |  | J1E1 | Eagar, Josh | [5 empty] | Approved |  | Approved |  | Merih Tekeste |  |  |  | Approved | Already implemented | JZSG | 2020-09-03 09:49 | Sadler, Justin R | J1E1 | 2020-08-03 13:46 | Eagar, Josh
5529 | Budget change | 35095167 | 114832579 | CWSP - STANISLAUS 1702 - LR1888 - PH 2.1 | Approved | 08W | [6 empty] | 08W CWSP 2020 Activated Reserve Wildfire Hardening. | 2020-12-29 | [8 empty] | 2365953 |  |  |  |  | PEND |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-08-01 16:32 | Sadler, Justin R | R4BA | 2020-07-30 15:19 | Barron, Raul Angelo
5311 | Resource change | 35112128 | 117462629 | BR-01-04-W (E) W. WAGSTAFF PARB | Approved | 08W | 2019 |  |  | GC |  | GC | Resourced to GC due to need for additional GC work in this Division | 2019-11-18 |  | 4479.5 | 991895.31 | 2020 | 2021 | [7 empty] | 2019-12-27 | DOCC |  | 2019-11-18 | M8D1 | D'Luzansky, Matthew | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-08-01 16:32 | Sadler, Justin R | ATSC | 2020-07-30 11:45 | Spreen, Andrew
4937 | Resource change | 35120949 | 117755982 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Denied | 08W |  |  |  | GC |  | Contract | Work identified as not having had resource updated to date | 2019-10-14 |  | 7588.6 | 14251728 | 2020 | 2021 |  | 947568.2 | [5 empty] | 2020-02-28 | DOCC |  | 2019-10-14 | S4K5 | Krenek, Scot | [9 empty] | Merih Tekeste |  |  |  | Denied | Job removed from work plan | JZSG | 2020-08-01 16:31 | Sadler, Justin R | ATSC | 2020-07-30 11:45 | Spreen, Andrew
4816 | Budget change | 35116516 | 117608020 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.3 | Approved | 08W | [6 empty] | Wildfire Hardening, project moved from 2020 Reserve to 2020 Activated Reserve plan. | 2020-11-25 | [8 empty] | 2239022 | 0 |  |  |  | PEND |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-08-01 16:32 | Sadler, Justin R | R4BA | 2020-07-29 15:11 | Barron, Raul Angelo
4805 | Update work plan date | 35116385 | 117604609 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Approved | 08W | [6 empty] | Caltrans permitting delay. | 2020-09-04 | 2021-01-02 | [7 empty] | 0 | 2750000 |  |  |  | PEND |  |  | FXA7 | Armas, Fernando | [5 empty] | Approved |  | Approved |  | Merih Tekeste |  |  |  | Approved | Deferred 7/29/20; Brad and Justin signed-off | C4CQ | 2020-08-16 23:01 | Fernandez, Catherine Melody Cassidy | M2HM | 2020-07-27 12:52 | Herron, Matthew Joseph
4261 | Budget change | 35115853 | 117601683 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Approved | 08W | [6 empty] | 08W Fire Hardening Project Budget Adjustment | 2020-09-06 | 2020-09-25 | [7 empty] | 3459188 |  |  |  |  | UNSC |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-07-23 22:32 | Sadler, Justin R | A0M6 | 2020-07-22 13:59 | Mendez, Angelica
4259 | Budget change | 35114050 | 117499593 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Approved | 08W | [6 empty] | 2020 Activated Reserve | 2020-11-02 | [8 empty] | 2981678 |  |  |  |  | UNSC |  |  | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-07-23 22:32 | Sadler, Justin R | J1PE | 2020-07-22 11:12 | Pantoja-Martinez, Jaime
4260 | Budget change | 35114051 | 117502234 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Approved | 08W | [6 empty] | 2020 Activated Reserve | 2020-10-02 |  | 4387.5 | 5342998 | 2021 |  |  | 3949678 |  | 3949678 |  |  |  | 2019-12-31 | CONS |  | 2020-10-02 | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-07-23 22:32 | Sadler, Justin R | J1PE | 2020-07-22 10:53 | Pantoja-Martinez, Jaime
4256 | Budget change | 35056746 | 114996821 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | 2020 Work plan | 2020-09-14 | 2020-09-15 | 1536 | 3642331 | 2020 | 2021 |  | 5901804 | 975015.3 | 2950902 | 0 |  |  | 2020-12-01 | CONS |  | 2020-09-14 | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-07-23 22:32 | Sadler, Justin R | M2HM | 2020-07-21 11:06 | Herron, Matthew Joseph
4255 | Budget change | 35056746 | 114996821 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | 2020 work plan | 2020-09-14 | 2020-09-15 | 1536 | 3642331 | 2020 | 2021 |  | 5901804 | 975015.3 | 2950902 | 0 |  |  | 2020-12-01 | CONS |  | 2020-09-14 | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-07-23 22:32 | Sadler, Justin R | M2HM | 2020-07-21 11:03 | Herron, Matthew Joseph
4253 | Budget change | 74022388 | 114266765 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Approved | 08W | 220 Mile Plan |  | Contract | Division |  |  |  | 2020-02-14 |  | 6713 | 5476214 | 2020 |  |  | 5268810 |  | 5268810 |  |  |  | 2020-03-01 | FICL | 2020-11-05 | 2020-02-14 | A1CO | Chan, Antonio Miguel | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-07-23 22:32 | Sadler, Justin R | KXYR | 2020-07-20 13:58
4205 | Budget change | 35116388 | 117604672 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Approved | 08W | [6 empty] | Wildfire Hardening | 2020-07-30 | 2020-09-01 | [7 empty] | 4458163 | 0 |  |  |  | PEND |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-07-18 19:35 | Sadler, Justin R | FXA7 | 2020-07-17 11:02 | Armas, Fernando
3923 | Budget change | 35116515 | 117607998 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.2 | Approved | 08W | [6 empty] | Wildfire Hardening, project moved from 2020 Reserve to 2020 Activated Reserve plan. | 2020-12-07 | [8 empty] | 3203035 | 0 |  |  |  | UNSC |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-07-18 19:35 | Sadler, Justin R | R4BA | 2020-07-16 14:31 | Barron, Raul Angelo
3921 | Budget change | 35116384 | 117604604 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Wildfire Hardening | 2021-04-12 | 2020-09-09 | 2558 | 4624169 | 2020 | 2021 |  | 3239382 | 1875779.4 | 3239382 | 0 |  |  | 2020-12-25 | CONS |  | 2021-04-12 | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-07-18 19:35 | Sadler, Justin R | FXA7 | 2020-07-16 13:06 | Armas, Fernando
3869 | Resource change | 35142827 | 118218951 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Approved | 08W | [5 empty] | GC | GC Work Assignments due to GC needing work in that division | 2020-11-04 | [13 empty] | PEND |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-07-18 19:35 | Sadler, Justin R | ATSC | 2020-07-16 12:57 | Spreen, Andrew
3870 | Resource change | 35142828 | 118218953 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Approved | 08W | [5 empty] | GC | GC Work Assignments due to GC needing work in that division | 2020-10-28 | [13 empty] | CONS |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-07-18 19:35 | Sadler, Justin R | ATSC | 2020-07-16 12:57 | Spreen, Andrew
3896 | Resource change | 35142826 | 118218639 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Approved | 08W | 2020 Rsrv |  |  | GC |  | GC | GC Work Assignments due to GC needing work in that division | 2021-02-01 |  | 1689.6 | 3876275 | 2021 |  |  | 2721318.8 | 2721318.8 |  |  |  |  | 2020-12-31 | CONS |  | 2021-02-01 | T3SQ | Skarda, Travis Damian | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-07-18 19:35 | Sadler, Justin R | ATSC | 2020-07-16 12:57 | Spreen, Andrew
3868 | Resource change | 35129767 | 114810960 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Approved | 08W | [5 empty] | GC | GC Work Assignments due to GC needing work in that division | 2020-10-31 | [13 empty] | ESTS |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-07-18 19:35 | Sadler, Justin R | ATSC | 2020-07-16 12:57 | Spreen, Andrew
3652 | Budget change | 35116443 | 117605181 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Approved | 08W | [6 empty] | Wildfire Hardening | 2020-06-28 | 2020-08-18 | [7 empty] | 3345785 | 0 |  |  |  | CONS |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-07-18 19:35 | Sadler, Justin R | FXA7 | 2020-07-14 13:25 | Armas, Fernando
3651 | Budget change | 35115052 | 117496040 | CWSP - MIWUK 1701_OCB - PH 1.4 | Approved | 08W | [6 empty] | Wildfire Hardening | 2020-06-22 | 2020-08-26 | [7 empty] | 2920492 | 0 |  |  |  | CONS |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-07-18 19:35 | Sadler, Justin R | FXA7 | 2020-07-14 13:19 | Armas, Fernando
3650 | Budget change | 35052821 | 114593976 | CWSP - MIWUK 1701 - OCB - PH 1.1 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Critical Fire Hardening work; $301/ft | 2020-08-31 | 2020-08-31 | 1732 | 4765282 | 2020 | 2021 |  | 3323925 | 1325532.5 | 3323925 | 0 |  |  | 2020-12-31 | CONS |  | 2020-08-31 | FXA7 | Armas, Fernando | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-07-18 19:35 | Sadler, Justin R | FXA7 | 2020-07-14 11:15 | Armas, Fernando
2941 | Budget change | 35115151 | 117493857 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Increse MPP budget by $472,747.85 to align with 2020 budget year per gate review meeting | 2020-08-17 | 2020-08-25 | 1832.1 | 5273989 | 2020 | 2021 |  | 3557462.7 | 2520547.9 | 4025666.85 |  |  |  | 2020-12-31 | CONS |  | 2020-08-17 | T3SQ | Skarda, Travis Damian | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Approved | Project on 220 mile plan | JZSG | 2020-07-10 18:18 | Sadler, Justin R | ZXAC | 2020-07-09 11:02 | Al-Saffar, Zaid Dhafer Hashim
2939 | Update work plan date | 35052737 | 114675474 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Approved | 08W | 2021 Rsrv |  |  | GC |  |  | Due to Caltrans permitting delay, project will not be started in 2020 | 2022-03-02 | 2021-01-01 | 2163 | 2768676 | 2021 | 2022 |  | 4086056.3 | 2738.2 | 0 | 1876271 |  |  | 2021-07-12 | PEND |  | 2022-03-02 | A0M6 | Mendez, Angelica | [5 empty] | Approved |  | Approved | GC has now been informed of project deferral. | Merih Tekeste |  |  |  | Approved | Deferred 7/29/20; Brad and Justin signed-off | C4CQ | 2020-08-16 22:59 | Fernandez, Catherine Melody Cassidy | M2HM | 2020-07-09 07:57 | Herron, Matthew Joseph
2937 | Update work plan date | 35052737 |  | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Denied | 08W | [6 empty] | Due to Caltrans permitting delays. Project will not be completed in 2020 and should be removed from the 2020 work plan |  | 2021-01-01 | [7 empty] | 0 | 3500000 |  |  |  | PEND |  |  | A0M6 | Mendez, Angelica | [5 empty] | Approved |  | Approved |  | Merih Tekeste |  |  |  | Denied | Duplicate of Change ID 3061 | C4CQ | 2020-08-28 12:30 | Fernandez, Catherine Melody Cassidy | M2HM | 2020-07-09 07:51 | Herron, Matthew Joseph
2932 | Budget change | 35072360 | 114754229 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Approved | 08W | [6 empty] | 08W fire hardening project adjust budget | 2020-09-12 | 2020-08-27 | [7 empty] | 1932059 | 0 |  |  |  | CONS |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved | Project part of 220 Mile Plan | JZSG | 2020-07-09 10:41 | Sadler, Justin R | A0M6 | 2020-07-07 14:54 | Mendez, Angelica
1926 | Budget change | 35114048 | 117499466 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | System Hardening work. Amount requested based on final Job Estimate and Constructability Review. | 2020-08-14 | 2020-12-15 | 1828 | 4178929 | 2020 | 2021 |  | 1323768 | 1810131 | 3133899 |  |  |  | 2021-12-31 | CONS |  | 2020-08-14 | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-07-06 12:58 | Sadler, Justin R | R4BA | 2020-06-29 14:55 | Barron, Raul Angelo
1916 | Budget change | 35114044 | 117502841 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | 08W Fire Hardening Project adjust CBP to match | 2020-08-12 | 2020-08-01 | 2524.7 | 3012702 | 2020 | 2021 |  | 2235937 | 20105.2 | 2235937 |  |  |  | 2019-12-06 | MAPP | 2021-02-25 | 2020-08-12 | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-06-27 18:19 | Sadler, Justin R | A0M6 | 2020-06-26 13:35 | Mendez, Angelica
1634 | Resource change | 35145522 | 117639249 | PSPS - CLARKSVILLE 2104 - CB UG | Denied | 08W |  |  |  |  | Contract |  | RCR update process - Project Added and Resource Updated | [14 empty] | PEND |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste |  |  |  | Denied | Resubmit. Notification and Order do not match. | JZSG | 2020-06-27 18:16 | Sadler, Justin R | ATSC | 2020-06-26 11:00 | Spreen, Andrew
1354 | Update work plan date | 74022385 | 114691436 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Approved | 08W | [6 empty] | Project still in design phase; CT impasse hindering final design; pushing out to 2021. No estimate available yet due to this. | 2022-03-21 | 2021-06-01 | 9 | 3523187 | 2022 |  |  | 3643552.6 | 3379.1 | 750000 |  |  |  | 2020-11-30 | APPR |  | 2022-03-21 | J1E1 | Eagar, Josh | [5 empty] | Approved |  | Approved | GC reviewed and confirmed no issues | Merih Tekeste |  |  |  | Approved | Reviewed by Justin Stabe | JZSG | 2020-07-28 09:52 | Sadler, Justin R | J1E1 | 2020-06-25 11:57 | Eagar, Josh
1352 | Budget change | 35115849 | 117602058 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Denied | 08W | [6 empty] | 08W Fire Hardening Project adjust CBP to match Final Estimate | 2020-11-21 | 2020-12-14 | [7 empty] | 2922407 |  |  |  |  | PEND |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Denied | Duplicate | JZSG | 2020-06-27 18:16 | Sadler, Justin R | A0M6 | 2020-06-24 10:00 | Mendez, Angelica
1351 | Budget change | 35115849 | 117602058 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Denied | 08W | [6 empty] | 08W Fire Hardening Project adjust CBP budget to match final estimate | 2020-11-21 | 2020-12-14 | [7 empty] | 2466182 |  |  |  |  | PEND |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Denied | Duplicate | JZSG | 2020-06-27 18:16 | Sadler, Justin R | A0M6 | 2020-06-24 08:25 | Mendez, Angelica
1350 | Budget change | 35115849 | 117602058 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Approved | 08W | [6 empty] | 08W Fire Hardening Project adjust CBP to final estimate | 2020-11-21 | 2020-12-14 | [7 empty] | 2922407 |  |  |  |  | PEND |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-06-27 18:19 | Sadler, Justin R | A0M6 | 2020-06-24 08:09 | Mendez, Angelica
1348 | Budget change | 35116394 | 117605556 | CWSP - MIWUK 1702 - OCB - PH 1.4 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Contingency release due to unexpected overhead cost increases. | 2020-06-07 | 2020-06-23 | 4778 | 2102204 | 2020 |  |  | 1990076 |  | 1990076 |  |  |  | 2019-12-27 | CONS |  |  | PXSO | Siu, Peter | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-06-27 18:19 | Sadler, Justin R | KXYR | 2020-06-23 16:55
1342 | Budget change | 35116383 | 117604600 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Updated constructability review after phase gate call to include risks discussed and veg est at $300k/mile | 2021-03-08 | 2020-08-17 | 1953 | 3758449 | 2020 | 2021 |  | 2531607.33 | 722523.9 | 2531607.33 |  |  |  | 2021-06-30 | CONS |  | 2021-03-08 | M2HM | Herron, Matthew Joseph | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-06-27 18:19 | Sadler, Justin R | KXYR | 2020-06-23 10:04
365 | Budget change | 35115051 | 117495949 | CWSP - MIWUK 1701_OCB - PH 1.3 | Denied | 08W | [6 empty] | Requesting budget to cover project work in 2020 | 2020-07-28 | 2020-07-28 | [7 empty] | 1623456.19 |  |  |  |  | CONS |  |  | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Denied | MPP Approved Budget sufficient | JZSG | 2020-07-09 10:46 | Sadler, Justin R | ZXAC | 2020-06-15 21:06 | Al-Saffar, Zaid Dhafer Hashim
362 | Budget change | 35103324 | 117251430 | CWSP - ROSSMOOR 1102 - OCB | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Increase in overhead costs. | 2020-10-30 | 2020-06-30 | 1360.6 | 2510809 | 2020 |  |  | 654743 |  | 654743 |  |  |  | 2020-12-31 | DOCC |  |  | PXSO | Siu, Peter | [9 empty] | Merih Tekeste |  |  |  | Approved |  | JZSG | 2020-06-19 18:22 | Sadler, Justin R | PXSO | 2020-06-15 15:27 | Siu, Peter
358 | Budget change | 35115050 | 117495948 | CWSP - MIWUK 1701_OCB - PH 1.2 | Denied | 08W | 220 Mile Plan |  |  | Contract |  |  | Requesting Budget for 2020 year | 2020-08-10 | 2020-08-04 | 2728 | 4091239 | 2020 | 2021 |  | 5030586.4 | 744758.2 | 2507646.03 |  |  |  | 2021-04-30 | CONS |  | 2020-08-10 | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Denied | MPP Approved Budget sufficient | JZSG | 2020-07-09 10:46 | Sadler, Justin R | ZXAC | 2020-06-15 12:00 | Al-Saffar, Zaid Dhafer Hashim
357 | Budget change | 35115050 | 119073950 | CWSP - MIWUK 1701_OCB - PH 1.2 | Denied | 08W | [6 empty] | Requesting Budget for 2020 |  | 2020-08-04 | [7 empty] | 2507646.03 |  |  |  |  | CONS |  |  | A0M6 | Mendez, Angelica | [9 empty] | Merih Tekeste |  |  |  | Denied | MPP Approved Budget sufficient | JZSG | 2020-07-09 10:46 | Sadler, Justin R | ZXAC | 2020-06-15 11:23 | Al-Saffar, Zaid Dhafer Hashim
326 | Budget change | 35114040 | 117500499 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | System Hardening work. Amount requested based on final Job Estimate and Constructability Review. | 2020-07-29 | 2020-10-19 | 4154.9 | 4232824 | 2020 | 2022 |  | 3110000 | 1676839.1 | 3110000 |  |  |  | 2019-12-06 | CONS |  | 2020-07-29 | J1PE | Pantoja-Martinez, Jaime | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Approved | Budget is sufficient. On 220 Mile Plan. | JZSG | 2020-06-12 11:55 | Sadler, Justin R | J1PE | 2020-06-12 09:49 | Pantoja-Martinez, Jaime
10154 | Budget change | 35114042 | 117500694 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Legacy Buget approved | 2020-10-02 |  | 2597.2 | 2867650 | 2020 |  |  | 2084370 |  | 2084370 |  |  |  | 2020-10-23 | FICL | 2020-08-25 |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved | Legacy budget approvals | SFSS | 2020-10-12 00:17 | Saraf, Shubham | ----
10103 | Budget change | 35114042 | 117500694 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Withdrawn | 08W | 220 Mile Plan |  |  | GC |  |  | Legacy approved Budget | 2020-10-02 |  | 2597.2 | 2867650 | 2020 |  |  | 2084370 |  | 2084370 |  |  |  | 2020-10-23 | FICL | 2020-08-25 |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Withdrawn | duplicate budget change request | SFSS | 2020-10-12 00:11 | Saraf, Shubham | ----
10146 | Budget change | 35115153 | 117495859 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Withdrawn | 08W | 220 Mile Plan |  |  | GC |  |  | Legacy approved Budget | 2021-03-08 |  | 2375.4 | 4734585 | 2020 | 2021 |  | 3556611.4 | 3080584.2 | 3595900 |  |  |  | 2020-12-31 | CONS |  | 2021-03-08 | T3SQ | Skarda, Travis Damian | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Withdrawn | duplicate budget change request | SFSS | 2020-10-12 00:11 | Saraf, Shubham | ----
10197 | Budget change | 35115153 | 117495859 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Legacy Buget approved | 2021-03-08 |  | 2375.4 | 4734585 | 2020 | 2021 |  | 3556611.4 | 3080584.2 | 3595900 |  |  |  | 2020-12-31 | CONS |  | 2021-03-08 | T3SQ | Skarda, Travis Damian | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Approved | Legacy budget approvals | SFSS | 2020-10-12 00:17 | Saraf, Shubham | ----
10182 | Budget change | 35114049 | 117499469 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Legacy Buget approved | 2020-07-21 |  | 1963.9 | 2193681.27 | 2020 | 2021 |  | 3322836 | 1168197.9 | 3322836 |  |  |  | 2021-12-31 | CONS |  | 2020-07-21 | R4BA | Barron, Raul Angelo | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Approved | Legacy budget approvals | SFSS | 2020-10-12 00:17 | Saraf, Shubham | ----
10131 | Budget change | 35114049 | 117499469 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Withdrawn | 08W | 220 Mile Plan |  |  | GC |  |  | Legacy approved Budget | 2020-07-21 |  | 1963.9 | 2193681.27 | 2020 | 2021 |  | 3322836 | 1168197.9 | 3322836 |  |  |  | 2021-12-31 | CONS |  | 2020-07-21 | R4BA | Barron, Raul Angelo | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Withdrawn | duplicate budget change request | SFSS | 2020-10-12 00:11 | Saraf, Shubham | ----
51506 | Add project | 35115152 | 117495855 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Approved | 08W |  |  |  | GC |  |  | WGC (Wildfire Governance Committee) agreed to pull this project back into the 2021 work plan. | 2021-05-31 |  | 4541.7 | 3591121 | 2021 |  | 2021 | 3558481.2 | 2229051.5 |  |  |  |  | 2020-12-31 | CONS |  | 2021-05-31 | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
10125 | Budget change | 35112434 | 117472389 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Withdrawn | 08W | 220 Mile Plan |  |  | Contract |  |  | Legacy approved Budget | 2020-07-27 |  | 3098.1 | 3756886 | 2020 |  |  | 2403957.8 | 75000 | 3110193 |  |  |  | 2020-12-31 | DOCC | 2020-10-02 | 2020-07-27 | CRGN | Gras, Christopher R | [9 empty] | Merih Tekeste |  |  |  | Withdrawn | duplicate budget change request | SFSS | 2020-10-12 00:11 | Saraf, Shubham | ----
10176 | Budget change | 35112434 | 117472389 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Legacy Buget approved | 2020-07-27 |  | 3098.1 | 3756886 | 2020 |  |  | 2403957.8 | 75000 | 3110193 |  |  |  | 2020-12-31 | DOCC | 2020-10-02 | 2020-07-27 | CRGN | Gras, Christopher R | [9 empty] | Merih Tekeste |  |  |  | Approved | Legacy budget approvals | SFSS | 2020-10-12 00:17 | Saraf, Shubham | ----
10147 | Budget change | 35095168 | 114832575 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.1 | Withdrawn | 08W | [6 empty] | Legacy approved Budget | 2021-05-19 |  |  |  | 2021 |  |  |  |  | 1474118 |  |  |  |  | PEND |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Withdrawn | duplicate budget change request | SFSS | 2020-10-12 00:11 | Saraf, Shubham | ----
10198 | Budget change | 35095168 | 114832575 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.1 | Approved | 08W | [6 empty] | Legacy Buget approved | 2021-05-19 |  |  |  | 2021 |  |  |  |  | 1474118 |  |  |  |  | PEND |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved | Legacy budget approvals | SFSS | 2020-10-12 00:17 | Saraf, Shubham | ----
51392 | Resource change | 35052825 | 114701195 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Approved | 08W | 220 Mile Plan |  |  | Contract |  | Contract | Resource Change - Reassigned to Contract from GC | 2021-04-20 |  | 2073 | 3544410 | 2021 | 2021 |  | 288570 | 1048628 |  |  |  |  | 2020-12-31 | CONS |  | 2021-04-20 | A0M6 | Mendez, Angelica | Critical Work | [8 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-03 17:48 | Saraf, Shubham | ----
10167 | Budget change | 35043423 | 114678726 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Approved | 08W | [6 empty] | Legacy Buget approved | 2021-04-09 |  |  |  | 2021 |  |  |  |  | 1638834 |  |  |  |  | PEND |  |  | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Approved | Legacy budget approvals | SFSS | 2020-10-12 00:17 | Saraf, Shubham | ----
10116 | Budget change | 35043423 | 114678726 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Withdrawn | 08W | [6 empty] | Legacy approved Budget | 2021-04-09 |  |  |  | 2021 |  |  |  |  | 1638834 |  |  |  |  | PEND |  |  | J1PE | Pantoja-Martinez, Jaime | [9 empty] | Merih Tekeste |  |  |  | Withdrawn | duplicate budget change request | SFSS | 2020-10-12 00:11 | Saraf, Shubham | ----
51548 | Add project | 35116515 |  | CWSP - STANISLAUS 1702 - LR1888 - PH 1.2 | Denied | 08W | [6 empty] | Pulling project back into 2021, per Asset Manager | 2021-09-01 | [8 empty] | 517463 | 2685572 |  |  |  | UNSC |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste | Denied |  |  | Denied | Duplicate | BCMK | 2021-03-04 10:51 | Mueller, Bret Charles | ----
51549 | Add project | 35116515 |  | CWSP - STANISLAUS 1702 - LR1888 - PH 1.2 | Approved | 08W | [6 empty] | Pulling project back in 2021 per Asset Manager | 2021-09-01 | [8 empty] | 517463 | 2685572 |  |  |  | UNSC |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste | Approved |  |  | Approved |  | BCMK | 2021-03-04 10:50 | Mueller, Bret Charles | ----
51539 | Add project | 35116515 |  | CWSP - STANISLAUS 1702 - LR1888 - PH 1.2 | Denied | 08W | [6 empty] | Project pulled back into 2021 work plan. Approved by Wildfire Governance Committee | 2021-09-01 | [9 empty] | 2685572 |  |  |  | UNSC |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste | Denied |  |  | Denied | Duplicate | BCMK | 2021-03-04 10:51 | Mueller, Bret Charles | ----
51434 | Add project | 35219281 |  | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51398 | Add project | 35226864 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51409 | Add project | 35227004 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51420 | Add project | 35233301 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51422 | Add project | 35233303 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51425 | Add project | 35233306 |  | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51427 | Add project | 35233308 |  | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51413 | Add project | 35226798 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51401 | Add project | 35226870 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51407 | Add project | 35227002 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51438 | Add project | 35219589 |  | CWSP - WILDWOOD 11011454 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51436 | Add project | 35232651 |  | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.3 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51415 | Add project | 35226900 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51406 | Add project | 35227001 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | J1E1 | Eagar, Josh | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51408 | Add project | 35227003 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51416 | Add project | 35232298 |  | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51417 | Add project | 35233038 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51419 | Add project | 35233300 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51421 | Add project | 35233302 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51423 | Add project | 35233304 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51424 | Add project | 35233305 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51428 | Add project | 35233309 |  | FRRB - WYANDOTTE 1103 - W1 PH1.13 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51430 | Add project | 35233311 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Denied | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [14 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Denied | Duplicate of change ID 51802 | SFSS | 2021-03-08 15:23 | Saraf, Shubham | ----
51432 | Add project | 35233314 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Denied | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [14 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Denied | Duplicate of change ID 51804 | SFSS | 2021-03-08 15:23 | Saraf, Shubham | ----
51410 | Add project | 35223036 |  | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51404 | Add project | 35226873 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51414 | Add project | 35226799 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51429 | Add project | 35233310 |  | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51431 | Add project | 35233312 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Denied | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [14 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Denied | Duplicate of change ID 51803 | SFSS | 2021-03-08 15:23 | Saraf, Shubham | ----
51397 | Add project | 35226863 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51399 | Add project | 35226865 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51400 | Add project | 35226866 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51402 | Add project | 35226871 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51435 | Add project | 35232650 |  | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | J6KF | Kringler, Jeff L | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51411 | Add project | 35223030 |  | PSPS - BANGOR 1101 CB - MICROGRID | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | T3SQ | Skarda, Travis Damian | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51433 | Add project | 35233315 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Denied | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [14 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Denied | Duplicate of change ID 51805 | SFSS | 2021-03-08 15:23 | Saraf, Shubham | ----
51437 | Add project | 35232718 |  | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Denied | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [14 empty] | UNSE |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Denied | Duplicate of change ID 51801 | SFSS | 2021-03-08 15:23 | Saraf, Shubham | ----
51418 | Add project | 35233039 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51426 | Add project | 35233307 |  | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS |  |  | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51403 | Add project | 35226872 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51405 | Add project | 35226878 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | M1NO | Nguyen, My-Linh | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51412 | Add project | 35224321 |  | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSE |  |  | M5HF | Hernandez, Michael Donald James | [9 empty] | Merih Tekeste | Approved |  |  | Approved | Approved with 2021 completion year | SFSS | 2021-03-08 15:18 | Saraf, Shubham | ----
51393 | Resource change | 35116384 | 117604604 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Approved | 08W | 220 Mile Plan |  |  | Contract |  | Contract | Resource Change - Reassigned to Contract from GC | 2021-04-12 |  | 2558 | 4624169 | 2020 | 2021 |  | 3239382 | 1875779.4 |  |  |  |  | 2020-12-25 | CONS |  | 2021-04-12 | FXA7 | Armas, Fernando | [9 empty] | Merih Tekeste |  |  |  | Approved |  | SFSS | 2021-03-03 17:48 | Saraf, Shubham | ----
10121 | Budget change | 35114431 | 117572146 | CWSP - MORAGA 1101 - LR108540 - PH5 | Withdrawn | 08W | 220 Mile Plan |  |  | Contract |  |  | Legacy approved Budget | 2020-03-31 |  | 4180.7 | 5279014 | 2020 |  |  | 3868379 |  | 3868379 |  |  |  | 2020-12-30 | FICL | 2020-03-23 |  | A1CO | Chan, Antonio Miguel | [9 empty] | Merih Tekeste |  |  |  | Withdrawn | duplicate budget change request | SFSS | 2020-10-12 00:11 | Saraf, Shubham | ----
10172 | Budget change | 35114431 | 117572146 | CWSP - MORAGA 1101 - LR108540 - PH5 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Legacy Buget approved | 2020-03-31 |  | 4180.7 | 5279014 | 2020 |  |  | 3868379 |  | 3868379 |  |  |  | 2020-12-30 | FICL | 2020-03-23 |  | A1CO | Chan, Antonio Miguel | [9 empty] | Merih Tekeste |  |  |  | Approved | Legacy budget approvals | SFSS | 2020-10-12 00:17 | Saraf, Shubham | ----
10180 | Budget change | 35116442 | 117605169 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Legacy Buget approved | 2020-07-15 |  | 2736 | 3849738 | 2020 | 2021 |  | 2989278 | 203909.1 | 2989278 |  |  |  | 2020-12-31 | DOCC | 2021-02-04 | 2020-07-15 | M2HM | Herron, Matthew Joseph | [9 empty] | Merih Tekeste |  |  |  | Approved | Legacy budget approvals | SFSS | 2020-10-12 00:17 | Saraf, Shubham | ----
10129 | Budget change | 35116442 | 117605169 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Withdrawn | 08W | 220 Mile Plan |  |  | Contract |  |  | Legacy approved Budget | 2020-07-15 |  | 2736 | 3849738 | 2020 | 2021 |  | 2989278 | 203909.1 | 2989278 |  |  |  | 2020-12-31 | DOCC | 2021-02-04 | 2020-07-15 | M2HM | Herron, Matthew Joseph | [9 empty] | Merih Tekeste |  |  |  | Withdrawn | duplicate budget change request | SFSS | 2020-10-12 00:11 | Saraf, Shubham | ----
10117 | Budget change | 35116390 | 117604678 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Withdrawn | 08W | 220 Mile Plan |  |  | Contract |  |  | Legacy approved Budget | 2020-10-05 |  | 1222.2 | 1195542 | 2020 |  |  | 935005 | 41387.5 | 935005 |  |  |  | 2020-12-25 | DOCC | 2021-01-29 | 2020-10-05 | M2HM | Herron, Matthew Joseph | [9 empty] | Merih Tekeste |  |  |  | Withdrawn | duplicate budget change request | SFSS | 2020-10-12 00:11 | Saraf, Shubham | ----
10168 | Budget change | 35116390 | 117604678 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Approved | 08W | 220 Mile Plan |  |  | Contract |  |  | Legacy Buget approved | 2020-10-05 |  | 1222.2 | 1195542 | 2020 |  |  | 935005 | 41387.5 | 935005 |  |  |  | 2020-12-25 | DOCC | 2021-01-29 | 2020-10-05 | M2HM | Herron, Matthew Joseph | [9 empty] | Merih Tekeste |  |  |  | Approved | Legacy budget approvals | SFSS | 2020-10-12 00:17 | Saraf, Shubham | ----
10199 | Budget change | 35116519 | 117608026 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.4 | Approved | 08W | [6 empty] | Legacy Buget approved | 2021-08-10 |  |  |  | 2021 |  |  |  |  | 1992384 |  |  |  |  | PEND |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Approved | Legacy budget approvals | SFSS | 2020-10-12 00:17 | Saraf, Shubham | ----
10148 | Budget change | 35116519 | 117608026 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.4 | Withdrawn | 08W | [6 empty] | Legacy approved Budget | 2021-08-10 |  |  |  | 2021 |  |  |  |  | 1992384 |  |  |  |  | PEND |  |  | R4BA | Barron, Raul Angelo | [9 empty] | Merih Tekeste |  |  |  | Withdrawn | duplicate budget change request | SFSS | 2020-10-12 00:11 | Saraf, Shubham | ----
10118 | Budget change | 35119966 | 117721841 | CWSP - LOS GATOS 1106 - LB44 - PH 2.6F | Withdrawn | 08W | 220 Mile Plan |  |  | GC |  |  | Legacy approved Budget | 2020-02-14 |  | 1106 | 1552000 | 2020 |  |  | 1136736 |  | 1136736 |  |  |  | 2020-12-31 | FICL | 2020-03-10 | 2020-02-14 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Withdrawn | duplicate budget change request | SFSS | 2020-10-12 00:11 | Saraf, Shubham | ----
10169 | Budget change | 35119966 | 117721841 | CWSP - LOS GATOS 1106 - LB44 - PH 2.6F | Approved | 08W | 220 Mile Plan |  |  | GC |  |  | Legacy Buget approved | 2020-02-14 |  | 1106 | 1552000 | 2020 |  |  | 1136736 |  | 1136736 |  |  |  | 2020-12-31 | FICL | 2020-03-10 | 2020-02-14 | SLKD | Kennedy, Sharon | [9 empty] | Merih Tekeste |  |  |  | Approved | Legacy budget approvals | SFSS | 2020-10-12 00:17 | Saraf, Shubham | ----