## Workbook Description
System Hardening Update
Information Updated as of 3 March, 2021
Contents
1 | Workbook Description - Overview of workbook contents and key definitions
2 | Summary Reporting - Summary Statistics for on-going System Hardening efforts
3 | Approved CPZ List - Current list of Circuit Protection Zones (CPZ's) approved by the Wildfire Risk Governance Committee for work over the three year period*
3 | O8W Project List - List of projects in Scoping, Estimating, Dependency Clearing, Construction*
*Total approved CPZ miles (1,201) reflects the miles which the hardening team has been approved to scope by the Wildfire Governance Committee (WGC). Planned miles (830) reflects the number of miles that the system hardening team has estimated based on existing projects in the pipeline.
Glossary - In order of presentation
Summary Reporting
| CPZ's Approved | Number of CPZ's approved by the WGC based on risk characteristics and other considerations.
| CPZ Miles Approved | Number of miles the hardening team has been approved to scope within the approved CPZs.
| CPZs with Active Jobs | Number of CPZs where the hardening team is actively pursuing a projects (some CPZs have many projects)
| Active Job Miles | Number of miles being pursued with active projects.
| Mitigation Approved | Number of miles which have had a specific mitigation approved by the WGC.
| Mitigation Not Approved | Number of miles which have yet to be approved for a specific mitigation by the WGC
| Scoping | Initial phase of project lifecycle which ends once a mitigation is approved by the WGC.
| Estimating | Second phase of project lifecycle; Refining project scope and estimates with detailed estimates and project planning.
| Dependencies | Third phase of project lifecycle; Clearing all dependencies required to execute the project (e.g., Easements, Permitting, etc.)
| Construction | Fourth phase of project lifecycle; field team execute the project as scoped.
| Close-out | Final phase of the project lifecycle; Closing and documenting the project.
| Overhead | Miles mitigated with Overhead Hardening.
| Underground | Miles mitigated with Underground Hardening.
| Removal | Miles mitigated with line Removal.
| Remote Grid | Miles mitigated with a Remote Grid Solution.
Approved CPZ List
| PZ_idx | Unique ID for each Circuit Protection Zone.
| circuit_protection_zone_id | Unique name for each Circuit Protection Zone.
| feeder_id | Unique ID for each circuit.
| feeder_name | Unique name for each circuit.
| Miles | Total miles in each .
| pixel_count | Number of 100mx100m pixels in each CPZ. As the risk model has the risk score at this 100mx100m pixel level
| mean_mavf_core_risk | Average - Multi Attribute Value Framework (MAVF) risk score per pixel; used to rank the CPZs from riskiest to least risky. The MAVF developed via regulatory proceedings
| Total Risk Value | Total risk associated with each CPZ, per the 2021 approved conductor risk model.
| mean_mavf_core_risk_rank | Rank of CPZs based on the average risk score (mean_mavf_core_risk).
| Number of Projects | Number of active projects / jobs within the CPZ.
| Residual Miles | Number of miles being hardened within each CPZ, as of the latest revision.
| Scoping | Number of miles in the scoping phase.
| Estimating | Number of miles in the estimating phase.
| Dependencies | Number of miles in the decency clearing phase.
| Construction | Number of miles in the construction phase.
| Close-out | Number of miles in the close-out phase.
| Work Bucket | Justification for approval of work in the CPZ by WGC.
| Date Approved | Date work was approved for scoping by the WGC.
08W Project List
| Order | SAP order number for the system hardening job / project.
| Exec. Status | Detailed view of current status.
| Planned Miles (SAP EST) | Number of miles anticipated to be hardened within the CPZ, based on current assumptions on the mitigation.
| Residual Miles (SAP EST) | Number of miles remaining to be hardened within the CPZ, based on current assumptions on the mitigaiton.
| Circuit Name | Unique name for each circuit.
| Circuit Protection Zone | Unique name for each Circuit Protection Zone.
| Pixel(s) | Number of 100mx100m pixels in each CPZ.
| Total HFTD Zone Miles | Number of miles within High Fire Threat Districts (HFTD)
| Mean MAVF Core Risk Rank | Rank of CPZs based on the average risk score (mean_mavf_core_risk).
| Total MAVF Core Risk Value | Total risk associated with each CPZ, per the 2021 approved conductor risk model.
| Mean MAVF Core Risk Value | Average MAVF risk score per pixel; used to rank the CPZs from riskiest to least risky.
| Mean Risk Rank | The rank of the circuit protection zone from 1-N based on the 2021 Wildfire Risk Model
| HFTD Tier | Description of HFTD tiers in the CPZ (e.g., Tier 2, Tier 3).
| OH - Feet | Number of feet estimated to be overhead hardened, given current scoping assumptions.
| UG - Feet | Number of feet estimated to be underground hardened, given current scoping assumptions.
| Remove - Feet | Number of feet estimated to be removed, given current scoping assumptions.
| Remote Grid - Feet | Number of feet estimated to be replace with a remote grid solution, given current scoping assumptions.
| Planned Mitigation | Mitigation planned (e.g., Overhead Harden, Underground Harden, Line Removal / Remote Grid).
| Status | Current status of project (e.g., Scoping, Estimating, Dependencies, Construction, Close-out).
| Work Bucket | Justification for approval of work in the CPZ by Wildfire Risk Governance Committee (WGC).

## Summary Reporting
System Hardening Summary Reporting
Information Updated as of 3 March, 2021
Approved CPZs
|  | CPZ's Approved (#) | CPZ Miles Approved | CPZs with Active Jobs (#) | Active Job Miles
| Total | 114 | 1201.0946 | 85 | 600.7915
08W Opportunity Hopper by Phase (Miles)
|  | Total | Scoping | Estimating | Dependencies | Construction | Close-out
| Total | 830.2725 | 609.1841 | 123.7654 | 20.9347 | 76.3883 | 0
08W Opportunity Hopper (Miles)
|  | Total | Mitigation Approved | Mitigation Not Approved
| Total | 830.2725 | 520.9024 | 309.3701
08W Opportunity Hopper - Approved Scope by Mitigation Type (Miles)
|  | Total | Overhead | Underground | Removal | Remote Grid
| Total | 520.6056 | 287.9898 | 204.9805 | 9.2324 | 18.403
8762
15000
Supplemental Information:
The top 20% riskiest CPZ's represent 73% of total system Risk and 8,762 miles.
The 08W Project list (orange dots) represents all CPZ's where there is an on-going system hardening project. All on-going projects have been approved by the WGC for risk characteristics or other factors on a case-by-case basis.
Top 20% Riskiest CPZs
08W projects outside of the Top 20% CPZs have been approved directly by the Wildfire Governance Comitteee (WGC). Rational includes: Fire Rebuild, In-construction work, CalTrans Permitting Pilots

## 08W Project List
#N/A | Detailed view of current status. | Number of miles anticipated to be hardened within the CPZ, based on current assumptions on the mitigation. |  |  | Unique name for each circuit. | Unique name for each Circuit Protection Zone. | Number of 100mx100m pixels in each CPZ. | Number of miles within High Fire Threat Districts (HFTD) | The rank of the circuit protection zone from 1-N based on the 2021 Wildfire Risk Model | Total risk associated with each CPZ, per the 2021 approved conductor risk model. | Average MAVF risk score per pixel; used to rank the CPZs from riskiest to least risky. | Description of HFTD tiers in the CPZ (e.g., Tier 2, Tier 3). | Number of feet estimated to be overhead hardened, given current scoping assumptions. | Number of feet estimated to be underground hardened, given current scoping assumptions. | Number of feet estimated to be removed, given current scoping assumptions. | Number of feet estimated to be replace with a remote grid solution, given current scoping assumptions. | Mitigation planned (e.g., Overhead Harden, Underground Harden, Line Removal / Remote Grid). | Current status of project (e.g., Scoping, Estimating, Dependencies, Construction, Close-out). | Justification for approval of work in the CPZ by Wildfire Risk Governance Committee (WGC).
Order (SH Project) | Exec. Status | Planned Miles (SAP EST) | Residual Miles (SAP EST) |  | Circuit Name | Circuit Protection Zone | Pixel(s) | Total HFTD Zone Miles | Mean Risk Rank | Total MAVF Core Risk Value | Mean MAVF Core Risk Value | HFTD Tier | OH - Feet | UG - Feet | Remove - Feet | Remote Grid - Feet | Planned Mitigation | Status | Work Bucket
74022384 | 20 | 5.4458 | 2.0458 | 3.4 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 111324918 | 49 | 5.4965 | 481 | 7.7177 | 0.1575 | Tier 3 | 28754 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35119965 | 18 | 0.84905 | 0.84905 | 0 | LOS GATOS 1106 | LOS GATOS 1106LB44 | 213 | 19.3536 | 1864 | 2.6623 | 0.012499 | Tier 3 | 4483 | 0 | 0 | 0 | Overhead | Dependencies | In-Construction
35094397 | 20 | 1.0646 | 0.0045833 | 1.06 | KONOCTI 1102 | KONOCTI 1102532 | 124 | 9.7315 | 1999 | 1.1234 | 0.0090595 | Tier 3 | 5621 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35061206 | 20 | 1.7652 | 0.93515 | 0.83 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | Tier 3 | 9320 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35061212 | 20 | 1.7888 | 1.7888 | 0 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | Tier 3 | 9445 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35115151 | 20 | 1.8964 | 0.5664 | 1.33 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | Tier 3 | 10013 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35115152 | 20 | 1.57 | 1.57 | 0 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | Tier 3 | 8271 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35117443 | 20 | 2.1581 | 0.88814 | 1.27 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | Tier 3 | 11395 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35116383 | 20 | 1.3862 | 1.3862 | 0 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | Tier 3 | 7319 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35116384 | 20 | 1.8371 | 1.6671 | 0.17 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | Tier 3 | 9700 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35116385 | 18 | 1.4 | 1.4 | 0 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | Tier 3 | 7392 | 0 | 0 | 0 | Overhead | Dependencies | In-Construction
35114048 | 20 | 1.3909 | 1.3909 | 0 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | Tier 3 | 7344 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35114051 | 20 | 1.44 | 1.44 | 0 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | Tier 3 | 7698 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35052821 | 20 | 2.0744 | 1.8344 | 0.24 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | Tier 3 | 10953 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35115050 | 20 | 1.6121 | 1.3121 | 0.3 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | Tier 3 | 8512 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35115053 | 20 | 1.7203 | 1.7203 | 0 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | Tier 3 | 9083 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35056746 | 20 | 2.0335 | 2.0335 | 0 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | Tier 3 | 10737 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35115054 | 20 | 1.4259 | 1.3959 | 0.03 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | Tier 3 | 7529 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35115055 | 20 | 2.1343 | 2.1343 | 0 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | Tier 2 | 11269 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35116391 | 20 | 2.0902 | 0.060152 | 2.03 | MIWUK 1702 | MIWUK 1702CB | 110 | 9.055 | 2369 | 0.30977 | 0.0028161 | Tier 3 | 11036 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35116395 | 20 | 1.7106 | 1.0206 | 0.69 | MIWUK 1702 | MIWUK 1702CB | 110 | 9.055 | 2369 | 0.30977 | 0.0028161 | Tier 3 | 9032 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35116800 | 20 | 1.4252 | 0.41519 | 1.01 | MIWUK 1702 | MIWUK 1702823548 | 231 | 19.7318 | 2411 | 0.57976 | 0.0025098 | Tier 3 | 7525 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35114100 | 20 | 1.0392 | 1.0392 | 0 | CAMP EVERS 2106 | CAMP EVERS 21065020 | 185 | 15.0734 | 2464 | 0.3934 | 0.0021265 | Tier 3 | 5487 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35052825 | 20 | 1.1682 | 0.86818 | 0.3 | MIWUK 1702 | MIWUK 1702S2247 | 21 | 1.4879 | 2737 | 0.010338 | 0.00049228 | Tier 3 | 6168 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35116442 | 20 | 2.29 | 0 | 2.29 | MIWUK 1702 | MIWUK 170238218 | 132 | 10.9416 | 2678 | 0.098599 | 0.00074696 | Tier 3 | 12386 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35116444 | 20 | 2.1023 | 2.1023 | 0 | MIWUK 1702 | MIWUK 170238218 | 132 | 10.9416 | 2678 | 0.098599 | 0.00074696 | Tier 3 | 11100 | 0 | 0 | 0 | Overhead | Construction | In-Construction
31361965 | 20 | 0.45 | 0.45 | 0 | DUNBAR 1101 | DUNBAR 110147964 | 68 | 6.5107 | 1794 | 0.99704 | 0.014662 | Tier 3 | 0 | 2367 | 0 | 0 | Underground | Construction | In-Construction
31334291 | 18 | 0.51 | 0.51 | 0 | FORT BRAGG A 1101 | FORT BRAGG A 11013113 | 68 | 10.0269 | 2140 | 0.42396 | 0.0062347 | Tier 3 | 2710 | 0 | 0 | 0 | Overhead | Dependencies | In-Construction
35085847 | 18 | 0.86 | 0.86 | 0 | ROB ROY 2105 | ROB ROY 210512474 | 105 | 3.4104 | 3283 | 0.00048831 | 4.6505e-06 | Tier 3 | 4555 | 0 | 0 | 0 | Overhead | Dependencies | In-Construction
35015704 | 18 | 1 | 1 | 0 | ROB ROY 2105 | ROB ROY 210512474 | 105 | 3.4104 | 3283 | 0.00048831 | 4.6505e-06 | Tier 3 | 5300 | 0 | 0 | 0 | Overhead | Dependencies | In-Construction
35052731 | 19 | 1.4733 | 1.4733 | 0 | BIG BASIN 1101 | BIG BASIN 110110296 | 181 | 14.4211 | 2456 | 0.3928 | 0.0021702 | Tier 3 | 7779 | 0 | 0 | 0 | Overhead | Construction | DSDD
35113950 | 19 | 3.57 | 3.57 | 0 | BIG BASIN 1101 | BIG BASIN 110110296 | 181 | 14.4211 | 2456 | 0.3928 | 0.0021702 | Tier 3 | 18849.6 | 0 | 0 | 0 | Overhead | Construction | DSDD
35113951 | 19 | 2.58 | 2.58 | 0 | BIG BASIN 1101 | BIG BASIN 110110296 | 181 | 14.4211 | 2456 | 0.3928 | 0.0021702 | Tier 3 | 13622.4 | 0 | 0 | 0 | Overhead | Construction | DSDD
35145540 | 18 | 1.2739 | 1.2739 | 0 | FROGTOWN 1702 | FROGTOWN 1702CB | 47 | 1.4614 | 1316 | 1.844 | 0.039234 | Tier 3 | 0 | 2272 | 4454 | 0 | Remote Grid / Removal | Dependencies | PSPS
35094513 | 18 | 1.9112 | 1.9112 | 0 | STANISLAUS 1702 | STANISLAUS 17021804 | 118 | 8.3797 | 2712 | 0.069602 | 0.00058985 | Tier 3 | 10091 | 0 | 0 | 0 | Overhead | Dependencies | DSDD
35145525 | 18 | 1.78 | 1.78 | 0 | RINCON 1104 | RINCON 1104CB | 34 | 0.56024 | 3302 | 0.00014935 | 4.3928e-06 | Tier 2 | 0 | 9398.4 | 0 | 0 | Underground | Dependencies | PSPS
35145524 | 18 | 1.5 | 1.5 | 0 | RINCON 1103 | RINCON 1103CB | 41 | 2.4433 | 1755 | 0.67489 | 0.016461 | Tier 3 | 0 | 7920 | 0 | 0 | Underground | Dependencies | PSPS
35137590 | 14 | 0.53485 | 0.53485 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101CB | 146 | 4.731 | 86 | 52.8144 | 0.36174 | Tier 3 | 2824 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35137593 | 14 | 1.3775 | 1.3775 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 11014646 | 165 | 18.5633 | 328 | 32.9712 | 0.19983 | Tier 3 | 7273 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35137596 | 14 | 0.97178 | 0.97178 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 11014646 | 165 | 18.5633 | 328 | 32.9712 | 0.19983 | Tier 3 | 5131 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35192284 | 13 | 1.086 | 1.086 | 0 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | Tier 3 | 0 | 5734 | 0 | 0 | Underground | Scoping | ECOP
35223024 | 13 | 1.2659 | 1.2659 | 0 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | Tier 3 | 0 | 6684 | 0 | 0 | Underground | Scoping | ECOP
35223026 | 13 | 1.0348 | 1.0348 | 0 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | Tier 3 | 5464 | 0 | 0 | 0 | Overhead | Scoping | ECOP
35223027 | 14 | 1.5674 | 1.5674 | 0 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | Tier 3 | 8276 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35223028 | 14 | 1.208 | 1.208 | 0 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | Tier 3 | 6378 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35238098 | 14 | 0 | 0 | 0 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | Tier 3 | 0 | 0 | 0 | 0 | TBD | Estimating | ECOP
35225593 | 14 | 1.1756 | 1.1756 | 0 | CLAYTON 2212 | CLAYTON 221296224 | 174 | 19.3992 | 377 | 32.6329 | 0.18755 | Tier 3 | 6207 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35192281 | 13 | 0.30663 | 0.30663 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 1619 | 0 | 0 | 0 | Overhead | Scoping | ECOP
35227027 | 13 | 0.97576 | 0.97576 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 5152 | 0 | 0 | 0 | Overhead | Scoping | ECOP
35227028 | 13 | 0.61723 | 0.61723 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 3259 | 0 | 0 | 0 | Overhead | Scoping | ECOP
35227029 | 13 | 1.0886 | 1.0886 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 5748 | 0 | 0 | 0 | Overhead | Scoping | ECOP
35236437 | 13 | 0.34 | 0.34 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 0 | 1795.2 | 0 | 0 | Underground | Scoping | ECOP
35236438 | 13 | 0.48 | 0.48 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 0 | 2534.4 | 0 | 0 | Underground | Scoping | ECOP
35226622 | 13 | 0.87841 | 0.87841 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 4638 | 0 | 0 | 0 | Overhead | Scoping | ECOP
35226623 | 13 | 1.2953 | 1.2953 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 6839 | 0 | 0 | 0 | Overhead | Scoping | ECOP
35226624 | 13 | 0.70795 | 0.70795 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 3738 | 0 | 0 | 0 | Overhead | Scoping | ECOP
35225595 | 13 | 0.87803 | 0.87803 | 0 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | Tier 3 | 4636 | 0 | 0 | 0 | Overhead | Scoping | ECOP
35225597 | 14 | 0.77576 | 0.77576 | 0 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | Tier 3 | 4096 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35225598 | 14 | 0.88144 | 0.88144 | 0 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | Tier 3 | 4654 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35174479 | 14 | 0.72159 | 0.72159 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 3810 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35226863 | 14 | 0.52765 | 0.52765 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 2786 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35226864 | 14 | 0.32652 | 0.32652 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 1724 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35226865 | 14 | 0.23542 | 0.23542 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 1243 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35226866 | 14 | 0.51818 | 0.51818 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 2736 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35226870 | 14 | 0.41951 | 0.41951 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 2215 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35226871 | 13 | 1.9117 | 1.9117 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 420 | 6124 | 3550 | 0 | Hybrid | Scoping | ECOP
35226872 | 13 | 1.4881 | 1.4881 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 1168 | 2552 | 4137 | 0 | Hybrid | Scoping | ECOP
35226873 | 13 | 1.0394 | 1.0394 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 0 | 0 | 5488 | Remote Grid / Removal | Scoping | ECOP
35226878 | 13 | 0.58883 | 0.58883 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 3109 | 0 | 0 | Underground | Scoping | ECOP
35227001 | 13 | 0.7214 | 0.7214 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 3809 | 0 | 0 | Underground | Scoping | ECOP
35227002 | 13 | 0.43295 | 0.43295 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 2286 | 0 | 0 | Underground | Scoping | ECOP
35227003 | 13 | 0.58087 | 0.58087 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 3067 | 0 | 0 | Underground | Scoping | ECOP
35227004 | 13 | 0.3483 | 0.3483 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 1839 | 0 | 0 | Underground | Scoping | ECOP
35236439 | 13 | 1.12 | 1.12 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 5913.6 | 0 | 0 | Underground | Scoping | ECOP
35236660 | 13 | 0.48 | 0.48 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 2534.4 | 0 | 0 | Underground | Scoping | ECOP
35191383 | 14 | 1.3286 | 1.3286 | 0 | SILVERADO 2102 | SILVERADO 210258626 | 125 | 15.2217 | 663 | 14.6249 | 0.117 | Tier 3 | 7015 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35191318 | 14 | 2.2159 | 2.2159 | 0 | SILVERADO 2102 | SILVERADO 210258626 | 125 | 15.2217 | 663 | 14.6249 | 0.117 | Tier 3 | 11700 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35192290 | 15 | 5.0004 | 5.0004 | 0 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | 541 | 44.1915 | 811 | 49.924 | 0.092281 | Tier 3 | 26402 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35226845 | 14 | 2.3674 | 2.3674 | 0 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | 541 | 44.1915 | 811 | 49.924 | 0.092281 | Tier 3 | 12500 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35231544 | 14 | 1.2 | 1.2 | 0 | TIDEWATER 2106 | TIDEWATER 210614072 | 30 | 3.6652 | 18 | 19.5994 | 0.65331 | Tier 2 | 6336 | 0 | 0 | 0 | Overhead | Estimating | Top 50 Miles
35226627 | 13 | 0.31231 | 0.31231 | 0 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | Tier 3 | 1649 | 0 | 0 | 0 | Overhead | Scoping | Top 50 Miles
35226630 | 13 | 1.4061 | 1.4061 | 0 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | Tier 3 | 7424 | 0 | 0 | 0 | Overhead | Scoping | Top 50 Miles
35226631 | 13 | 1.5326 | 1.5326 | 0 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | Tier 3 | 8092 | 0 | 0 | 0 | Overhead | Scoping | Top 50 Miles
35217267 | 14 | 0.71 | 0.71 | 0 | MARIPOSA 2102 | MARIPOSA 2102241564 | 14 | 0.71281 | 10 | 10.8148 | 0.77248 | Tier 2 & 3 | 3748.8 | 0 | 0 | 0 | Overhead | Estimating | Top 50 Miles
35227860 | 13 | 0.19583 | 0.19583 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 1034 | 0 | 0 | 0 | Overhead | Scoping | Top 50 Miles
35227861 | 13 | 1.5339 | 1.5339 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 8099 | 0 | 0 | 0 | Overhead | Scoping | Top 50 Miles
35227862 | 13 | 0.93466 | 0.93466 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 4935 | 0 | 0 | 0 | Overhead | Scoping | Top 50 Miles
35227863 | 13 | 0.79129 | 0.79129 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 4178 | 0 | 0 | 0 | Overhead | Scoping | Top 50 Miles
35227866 | 13 | 0.52386 | 0.52386 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 2766 | 0 | 0 | 0 | Overhead | Scoping | Top 50 Miles
35227867 | 13 | 0.99527 | 0.99527 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 5255 | 0 | 0 | 0 | Overhead | Scoping | Top 50 Miles
35227868 | 13 | 0.51686 | 0.51686 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 2729 | 0 | 0 | 0 | Overhead | Scoping | Top 50 Miles
35228187 | 13 | 0.62879 | 0.62879 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 3320 | 0 | 0 | 0 | Overhead | Scoping | Top 50 Miles
35228188 | 13 | 3.73 | 3.73 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 0 | 0 | 19694.4 | 0 | Remote Grid / Removal | Scoping | Top 50 Miles
35236661 | 13 | 0.22 | 0.22 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 1161.6 | 0 | 0 | 0 | Overhead | Scoping | Top 50 Miles
35222045 | 13 | 0.88864 | 0.88864 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 4692 | 0 | 0 | 0 | Overhead | Scoping | Top 50 Miles
35226846 | 14 | 1.5714 | 1.5714 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 8297 | 0 | 0 | 0 | Overhead | Estimating | Top 20% MAVF CPZ
35226847 | 14 | 1.9839 | 1.9839 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 10475 | 0 | 0 | 0 | Overhead | Estimating | Top 20% MAVF CPZ
35231607 | 14 | 1.646 | 1.646 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 8691 | 0 | 0 | 0 | Overhead | Estimating | Top 20% MAVF CPZ
35231609 | 14 | 1.3301 | 1.3301 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 7023 | 0 | 0 | 0 | Overhead | Estimating | Top 20% MAVF CPZ
35226848 | 14 | 2.4445 | 2.4445 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 12907 | 0 | 0 | 0 | Overhead | Estimating | Top 20% MAVF CPZ
35226850 | 14 | 1.5451 | 1.5451 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 8158 | 0 | 0 | 0 | Overhead | Estimating | Top 20% MAVF CPZ
35226851 | 14 | 1.8784 | 1.8784 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 9918 | 0 | 0 | 0 | Overhead | Estimating | Top 20% MAVF CPZ
35232280 | 18 | 0.6 | 0.6 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 3168 | 0 | 0 | 0 | Overhead | Dependencies | Top 20% MAVF CPZ
35226852 | 14 | 2.4932 | 2.4932 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | Tier 3 | 13164 | 0 | 0 | 0 | Overhead | Estimating | Top 20% MAVF CPZ
35226853 | 14 | 2.8044 | 2.8044 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | Tier 3 | 14807 | 0 | 0 | 0 | Overhead | Estimating | Top 20% MAVF CPZ
35226854 | 14 | 1.0299 | 1.0299 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | Tier 3 | 5438 | 0 | 0 | 0 | Overhead | Estimating | Top 20% MAVF CPZ
35226856 | 14 | 1.9436 | 1.9436 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | Tier 3 | 10262 | 0 | 0 | 0 | Overhead | Estimating | Top 20% MAVF CPZ
35026643 | 13 | 1.6339 | 1.6339 | 0 | DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 11052102 | 417 | 37.4816 | 666 | 48.4576 | 0.11621 | Tier 2 | 5727 | 0 | 2900 | 0 | Remote Grid / Removal | Scoping | Top 20% MAVF CPZ
35075103 | 18 | 0.59 | 0.59 | 0 | FROGTOWN 1701 | FROGTOWN 17011623 | 152 | 15.2605 | 721 | 16.3546 | 0.1076 | Tier 3 | 3115.2 | 0 | 0 | 0 | Overhead | Dependencies | Top 20% MAVF CPZ
77799999 | 0 | 31.8 | 31.8 | 0 | VARIOUS | VARIOUS | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 167904 | 0 | Remote Grid / Removal | Scoping | Line Removal
35226625 | 2 | 7.9 | 7.9 | 0 | ELK CREEK 1101 | ELK CREEK 11012106 | 67 | 13.2402 | 340 | 13.1388 | 0.1961 |  | 0 | 0 | 0 | 41712 | Remote Grid / Removal | Scoping | FRRB
35217274 | 13 | 2.52 | 2.52 | 0 | HALF MOON BAY 1103 | HALF MOON BAY 110369412 | 150 | 15.5679 | 2055 | 1.1767 | 0.0078448 |  | 0 | 13305.6 | 0 | 0 | Underground | Scoping | FRRB
35217275 | 13 | 2.9 | 2.9 | 0 | HALF MOON BAY 1103 | HALF MOON BAY 110369412 | 150 | 15.5679 | 2055 | 1.1767 | 0.0078448 |  | 0 | 15312 | 0 | 0 | Underground | Scoping | FRRB
35226626 | 2 | 4.03 | 4.03 | 0 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 11136751 | 139 | 22.6749 | 945 | 10.2759 | 0.073927 |  | 0 | 0 | 0 | 21278.4 | Remote Grid / Removal | Scoping | FRRB
35199565 | 14 | 2.56 | 2.56 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 13516.8 | 0 | 0 | 0 | Overhead | Estimating | FRRB
35200051 | 14 | 4.8 | 4.8 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 25344 | 0 | 0 | Underground | Estimating | FRRB
35199565 | 14 | 6.72 | 6.72 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 |  | 35481.6 | 0 | 0 | 0 | Overhead | Estimating | FRRB
35200051 | 14 | 7.25 | 7.25 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 |  | 0 | 38280 | 0 | 0 | Underground | Estimating | FRRB
35220936 | 5 | 0.95 | 0.95 | 0 | HALF MOON BAY 1103 | HALF MOON BAY 11036012 | 79 | 6.6683 | 2186 | 0.42722 | 0.0054078 |  | 0 | 5016 | 0 | 0 | Underground | Scoping | FRRB
35223343 | 14 | 0.85019 | 0.85019 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | Tier 3 | 0 | 4489 | 0 | 0 | Underground | Estimating | FRRB
35225821 | 14 | 0.63371 | 0.63371 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 3346 | 0 | 0 | Underground | Estimating | FRRB
35235139 | 7 | 1.3186 |  |  | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 6962 | 0 | 0 | Underground | Scoping | FRRB
35235676 | 7 | 2.3958 | 2.3958 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 12650 | 0 | 0 | Underground | Scoping | FRRB
35229043 | 7 | 0.41345 | 0.41345 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | Tier 3 | 0 | 2183 | 0 | 0 | Underground | Scoping | FRRB
35223344 | 19 | 4.1617 | 4.1617 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | Tier 3 | 0 | 21974 | 0 | 0 | Underground | Construction | FRRB
35223345 | 19 | 4.454 | 4.454 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | Tier 3 | 0 | 23517 | 0 | 0 | Underground | Construction | FRRB
35225822 | 20 | 1.8693 | 1.8693 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | Tier 3 | 0 | 9870 | 0 | 0 | Underground | Construction | FRRB
35225823 | 20 | 1.7159 | 1.7159 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 9060 | 0 | 0 | Underground | Construction | FRRB
35225824 | 19 | 2.9364 | 2.9364 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 |  | 0 | 15504 | 0 | 0 | Underground | Construction | FRRB
35222234 | 10 | 1.39 | 1.39 | 0 | OAKHURST 1101 | OAKHURST 110110090 | 435 | 44.0886 | 421 | 75.8506 | 0.17437 |  | 0 | 0 | 0 | 7339.2 | Remote Grid / Removal | Scoping | Remote Grid
35232298 | 14 | 0.24 | 0.24 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1267.2 | 0 | 0 | Underground | Estimating | FRRB
35233038 | 16 | 0.23 | 0.23 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1214.4 | 0 | 0 | Underground | Estimating | FRRB
35233039 | 13 | 0.37 | 0.37 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1953.6 | 0 | 0 | Underground | Scoping | FRRB
35233300 | 13 | 0.32 | 0.32 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1689.6 | 0 | 0 | Underground | Scoping | FRRB
35233301 | 13 | 0.36 | 0.36 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1900.8 | 0 | 0 | Underground | Scoping | FRRB
35233302 | 16 | 0.12 | 0.12 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 633.6 | 0 | 0 | Underground | Estimating | FRRB
35233303 | 14 | 0.09 | 0.09 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 475.2 | 0 | 0 | Underground | Estimating | FRRB
35233304 | 14 | 0.3 | 0.3 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1584 | 0 | 0 | Underground | Estimating | FRRB
35233305 | 13 | 0.29 | 0.29 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1531.2 | 0 | 0 | Underground | Scoping | FRRB
35233306 | 14 | 0.26 | 0.26 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1372.8 | 0 | 0 | Underground | Estimating | FRRB
35233307 | 16 | 0.6 | 0.6 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 3168 | 0 | 0 | Underground | Estimating | FRRB
35233308 | 16 | 0.93 | 0.93 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 4910.4 | 0 | 0 | Underground | Estimating | FRRB
35233309 | 13 | 0.37 | 0.37 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1953.6 | 0 | 0 | Underground | Scoping | FRRB
35233310 | 14 | 0.15 | 0.15 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 792 | 0 | 0 | Underground | Estimating | FRRB
35232718 | 13 | 0.5 | 0.5 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 2640 | 0 | 0 | Underground | Scoping | FRRB
35233311 | 13 | 0.58996 | 0.58996 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 3115 | 0 | 0 | Underground | Scoping | FRRB
35233312 | 13 | 1.1 | 1.1 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 5808 | 0 | 0 | Underground | Scoping | FRRB
35233314 | 13 | 1.6 | 1.6 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 8448 | 0 | 0 | Underground | Scoping | FRRB
35233315 | 13 | 0.96 | 0.96 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 5068.8 | 0 | 0 | Underground | Scoping | FRRB
35235705 | 13 | 1.32 | 1.32 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 6969.6 | 0 | 0 | Underground | Scoping | FRRB
35235706 | 13 | 1.16 | 1.16 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 6125 | 0 | 0 | Underground | Scoping | FRRB
35235707 | 13 | 0.95 | 0.95 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 5016 | 0 | 0 | Underground | Scoping | FRRB
35239522 | 13 | 0.25 | 0.25 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1320 | 0 | 0 | Underground | Scoping | FRRB
35239523 | 13 | 0.25 | 0.25 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1320 | 0 | 0 | Underground | Scoping | FRRB
35239937 | 13 | 0.58712 | 0.58712 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 3100 | 0 | 0 | Underground | Scoping | FRRB
35235320 | 13 | 1.0015 | 1.0015 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 5288 | 0 | 0 | Underground | Scoping | FRRB
35237889 | 13 | 1.3674 | 1.3674 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 7220 | 0 | 0 | Underground | Scoping | FRRB
35237890 | 13 | 0.80795 | 0.80795 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 4266 | 0 | 0 | Underground | Scoping | FRRB
35237891 | 13 | 0.45833 | 0.45833 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 2420 | 0 | 0 | Underground | Scoping | FRRB
35237893 | 13 | 0.28958 | 0.28958 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 1529 | 0 | 0 | Underground | Scoping | FRRB
35237894 | 13 | 0.85985 | 0.85985 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 4540 | 0 | 0 | Underground | Scoping | FRRB
35237895 | 13 | 0.78939 | 0.78939 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 4168 | 0 | 0 | Underground | Scoping | FRRB
35237896 | 13 | 1.1121 | 1.1121 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 5872 | 0 | 0 | Underground | Scoping | FRRB
35236990 | 13 | 0.77652 | 0.77652 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 4100 | 0 | 0 | Underground | Scoping | FRRB
35235669 | 13 | 0.41098 | 0.41098 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 2170 | 0 | 0 | Underground | Scoping | FRRB
35235671 | 13 | 0.49242 | 0.49242 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 2600 | 0 | 0 | Underground | Scoping | FRRB
35239095 | 13 | 1.1326 | 1.1326 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 5980 | 0 | 0 | Underground | Scoping | FRRB
35239096 | 13 | 0.88125 | 0.88125 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 4653 | 0 | 0 | Underground | Scoping | FRRB
35239097 | 13 | 1.0127 | 1.0127 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 5347 | 0 | 0 | Underground | Scoping | FRRB
35239098 | 13 | 1.3792 | 1.3792 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 7282 | 0 | 0 | Underground | Scoping | FRRB
35239099 | 13 | 0.65758 | 0.65758 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 3472 | 0 | 0 | Underground | Scoping | FRRB
35236991 | 13 | 1.5188 | 1.5188 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 8019 | 0 | 0 | Underground | Scoping | FRRB
35236993 | 13 | 0.39773 | 0.39773 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 0 | 0 | 2100 | Remote Grid / Removal | Scoping | FRRB
35236995 | 3 | 1.972 | 1.972 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 0 | 0 | 10412 | Remote Grid / Removal | Scoping | FRRB
35235670 | 3 | 3.91 | 3.91 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 20645 | 0 | 0 | Underground | Scoping | FRRB
35235672 | 3 | 1.64 | 1.64 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 8659 | 0 | 0 | Underground | Scoping | FRRB
35235673 | 2 | 2.14 | 2.14 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 11299 | 0 | 0 | Underground | Scoping | FRRB
35235674 | 13 | 4.3 | 4.3 | 0 | BIG BEND 1102 | BIG BEND 1102CB | 139 | 17.0366 | 865 | 11.7994 | 0.084888 |  | 0 | 22704 | 0 | 0 | Underground | Scoping | FRRB
35235675 | 2 | 1 | 1 | 0 | BIG BEND 1102 | BIG BEND 1102CB | 139 | 17.0366 | 865 | 11.7994 | 0.084888 |  | 0 | 5280 | 0 | 0 | Underground | Scoping | FRRB
35235677 | 13 | 6.7297 | 6.7297 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 35533 | 0 | 0 | Underground | Scoping | FRRB
35233166 | 14 | 0 |  | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 0 | 0 | 0 | TBD | Estimating | FRRB
35235678 | 3 | 4.4 | 4.4 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 23232 | 0 | 0 | Underground | Scoping | FRRB
35235679 | 6 | 6.5 | 6.5 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 34320 | 0 | 0 | Underground | Scoping | FRRB
35235700 | 3 | 5.44 | 5.44 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 28723 | 0 | 0 | Underground | Scoping | FRRB
35235701 | 6 | 3.49 | 3.49 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 18427 | 0 | 0 | Underground | Scoping | FRRB
35235702 | 13 | 2.14 | 2.14 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 11299 | 0 | 0 | Underground | Scoping | FRRB
35235703 | 13 | 8.44 | 8.44 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 44563 | 0 | 0 | Underground | Scoping | FRRB
35235704 | 13 | 6.1 | 6.1 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 32208 | 0 | 0 | Underground | Scoping | FRRB
35237021 | 13 | 0 | 0 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 0 | 0 | 0 | TBD | Scoping | FRRB
35236983 | 3 | 0.30303 | 0.30303 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 0 | 0 | 1600 | Remote Grid / Removal | Scoping | FRRB
35236997 | 6 | 1.6562 | 1.6562 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 0 | 0 | 8745 | Remote Grid / Removal | Scoping | FRRB
35236982 | 2 | 1.9248 | 1.9248 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 0 | 0 | 10163 | Remote Grid / Removal | Scoping | FRRB
35236985 | 3 | 1.5911 | 1.5911 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 0 | 0 | 8401 | Remote Grid / Removal | Scoping | FRRB
35236986 | 13 | 1.5748 | 1.5748 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 0 | 0 | 8315 | Remote Grid / Removal | Scoping | FRRB
35236988 | 13 | 0.24489 | 0.24489 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 0 | 0 | 1293 | Remote Grid / Removal | Scoping | FRRB
35236989 | 6 | 0.47216 | 0.47216 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 0 | 0 | 2493 | Remote Grid / Removal | Scoping | FRRB
35236992 | 3 | 0.58712 | 0.58712 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 0 | 0 | 3100 | Remote Grid / Removal | Scoping | FRRB
35236999 | 13 | 1.0038 | 1.0038 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 0 | 0 | 5300 | Remote Grid / Removal | Scoping | FRRB
35237020 | 13 | 0.39773 | 0.39773 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 0 | 0 | 2100 | Remote Grid / Removal | Scoping | FRRB
35236984 | 3 | 1.8559 | 1.8559 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 |  | 0 | 0 | 0 | 9799 | Remote Grid / Removal | Scoping | FRRB
35222236 | 11 | 0.84 | 0.84 | 0 | MARIPOSA 2101 | MARIPOSA 210135244 | 146 | 17.4635 | 428 | 25.237 | 0.17286 |  | 0 | 0 | 0 | 4435.2 | Remote Grid / Removal | Scoping | Remote Grid
35175853 | 13 | 0.7 | 0.7 | 0 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 |  | 0 | 0 | 0 | 3696 | Remote Grid / Removal | Scoping | Remote Grid
35222235 | 10 | 2.48 | 2.48 | 0 | DUNLAP 1102 | DUNLAP 1102778286 | 5 | 2.6029 | 2738 | 0.0024545 | 0.0004909 |  | 0 | 0 | 0 | 13094.4 | Remote Grid / Removal | Scoping | Remote Grid
35229051 | 10 | 3.04 | 3.04 | 0 | CORNING 1102 | CORNING 110253184 | 123 | 31.8239 | 413 | 21.5791 | 0.17544 |  | 0 | 0 | 0 | 16051 | Remote Grid / Removal | Scoping | Remote Grid
35219543 | 13 | 0.24015 | 0.24015 | 0 | PLACERVILLE 1112 | PLACERVILLE 1112CB | 117 | 8.513 | 2123 | 0.76223 | 0.0065148 | Tier 2 | 0 | 1268 | 0 | 0 | Underground | Scoping | PSPS
35223036 | 13 | 0.055871 | 0.055871 | 0 | BRUNSWICK 1110 | BRUNSWICK 1110CB | 26 | 0.0034177 | 2134 | 0.16685 | 0.0064174 |  | 0 | 295 | 0 | 0 | Underground | Scoping | PSPS
35223030 | 13 | 0.85 | 0.85 | 0 | BANGOR 1101 | BANGOR 1101CB | 171 | 18.7561 | 355 | 33.1366 | 0.19378 |  | 0 | 4488 | 0 | 0 | Underground | Scoping | PSPS
35223062 | 13 | 0.18 | 0.18 | 0 | CALISTOGA 1102 | CALISTOGA 1102184814 | 20 | 0.42402 | 3098 | 0.00017414 | 8.707e-06 | Tier 2 | 0 | 950.4 | 0 | 0 | Underground | Scoping | PSPS
35223038 | 10 | 0.46 | 0.46 | 0 | MARTELL 1101 | MARTELL 1101CB | 171 | 5.879 | 999 | 11.5263 | 0.067405 | Tier 2 | 0 | 2428.8 | 0 | 0 | Underground | Scoping | PSPS
35234284 | 10 | 0.45 | 0.45 | 0 | MARTELL 1101 | MARTELL 1101CB | 171 | 5.879 | 999 | 11.5263 | 0.067405 | Tier 2 | 0 | 2376 | 0 | 0 | Underground | Scoping | PSPS
35234526 | 10 | 0.4 | 0.4 | 0 | MARTELL 1101 | MARTELL 1101CB | 171 | 5.879 | 999 | 11.5263 | 0.067405 | Tier 2 | 2112 | 0 | 0 | 0 | Overhead | Scoping | PSPS
35223060 | 9 | 1.74 | 1.74 | 0 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 |  | 0 | 9187.2 | 0 | 0 | Underground | Scoping | PSPS
35234527 | 9 | 0 | 0 | 0 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 |  | 0 | 0 | 0 | 0 | TBD | Scoping | PSPS
35234528 | 9 |  |  | 0 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 |  | 0 | 0 | 0 | 0 | TBD | Scoping | PSPS
35234529 | 9 |  |  | 0 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 |  | 0 | 0 | 0 | 0 | TBD | Scoping | PSPS
35223063 | 10 | 0.15114 | 0.15114 | 0 | DUNBAR 1101 | DUNBAR 1101CB | 191 | 3.1203 | 2048 | 1.5267 | 0.007993 | Tier 2 | 0 | 798 | 0 | 0 | Underground | Scoping | PSPS
35228774 | 10 | 0.97405 | 0.97405 | 0 | DUNBAR 1101 | DUNBAR 1101CB | 191 | 3.1203 | 2048 | 1.5267 | 0.007993 | Tier 2 | 0 | 5143 | 0 | 0 | Underground | Scoping | PSPS
35228775 | 10 | 0.88617 | 0.88617 | 0 | DUNBAR 1101 | DUNBAR 1101CB | 191 | 3.1203 | 2048 | 1.5267 | 0.007993 | Tier 2 | 0 | 4679 | 0 | 0 | Underground | Scoping | PSPS
35223032 | 13 | 0.43087 | 0.43087 | 0 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 2101CB | 262 | 24.9941 | 68 | 101.3032 | 0.38665 | Tier 2 | 0 | 2275 | 0 | 0 | Underground | Scoping | PSPS
35223037 | 18 | 0.052083 | 0.052083 | 0 | OAKHURST 1101 | OAKHURST 1101CB | 47 | 2.3149 | 847 | 4.0694 | 0.086583 | Tier 3 | 0 | 275 | 0 | 0 | Underground | Dependencies | PSPS
35224377 | 13 | 0.13996 | 0.13996 | 0 | PLACERVILLE 2106 | PLACERVILLE 21067522 | 745 | 67.3656 | 1363 | 26.4689 | 0.035529 | Tier 3 | 0 | 739 | 0 | 0 | Underground | Scoping | PSPS
35233995 | 13 | 0.5 | 0.5 | 0 | PLACERVILLE 2106 | PLACERVILLE 21067522 | 745 | 67.3656 | 1363 | 26.4689 | 0.035529 | Tier 3 | 0 | 2640 | 0 | 0 | Underground | Scoping | PSPS
35233996 | 13 | 0.71 | 0.71 | 0 | PLACERVILLE 2106 | PLACERVILLE 21067522 | 745 | 67.3656 | 1363 | 26.4689 | 0.035529 | Tier 3 | 0 | 3748.8 | 0 | 0 | Underground | Scoping | PSPS
35223039 | 13 | 0.60739 | 0.60739 | 0 | WYANDOTTE 1109 | WYANDOTTE 1109702710 | 49 | 2.6641 | 218 | 12.174 | 0.24845 | Tier 2 | 705 | 2502 | 0 | 0 | Hybrid | Scoping | PSPS
35219542 | 11 | 0.14 | 0.14 | 0 | PLACERVILLE 1112 | PLACERVILLE 1112CB | 117 | 8.513 | 2123 | 0.76223 | 0.0065148 | Tier 2 | 0 | 739.2 | 0 | 0 | Underground | Scoping | PSPS
35144944 | 18 | 0.26 | 0.26 | 0 | SNEATH LANE 1107 | SNEATH LANE 1107CB | 45 | 1.0038 | 2336 | 0.14045 | 0.003121 |  | 1372.8 | 0 | 0 | 0 | Overhead | Dependencies | PSPS
35219291 | 18 | 0.39811 | 0.39811 | 0 | VACA DIXON 1101 | VACA DIXON 1101126774 | 11 | 0.78766 | 20 | 6.8232 | 0.62029 | Tier 2 | 2102 | 0 | 0 | 0 | Overhead | Dependencies | Top 250 Miles
35219097 | 14 | 2.36 | 2.36 | 0 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | Tier 2 | 12460.8 | 0 | 0 | 0 | Overhead | Estimating | Top 250 Miles
35227260 | 14 | 2.36 | 2.36 | 0 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | Tier 2 | 12460.8 | 0 | 0 | 0 | Overhead | Estimating | Top 250 Miles
35227261 | 14 | 2.16 | 2.16 | 0 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | Tier 2 | 11404.8 | 0 | 0 | 0 | Overhead | Estimating | Top 250 Miles
35227262 | 14 | 1.4015 | 1.4015 | 0 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | Tier 2 | 7400 | 0 | 0 | 0 | Overhead | Estimating | Top 250 Miles
35219098 | 14 | 0.72 | 0.72 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101118494 | 12 | 1.0659 | 23 | 6.971 | 0.58092 | Tier 2 & 3 | 3801.6 | 0 | 0 | 0 | Overhead | Estimating | Top 250 Miles
35229119 | 13 | 0.61 | 0.61 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101118494 | 12 | 1.0659 | 23 | 6.971 | 0.58092 | Tier 2 & 3 | 0 | 3220.8 | 0 | 0 | Underground | Scoping | Top 250 Miles
35219099 | 13 | 2.7269 | 2.7269 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 14398 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35231620 | 13 | 2.6782 | 2.6782 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 0 | 14141 | 0 | 0 | Underground | Scoping | Top 250 Miles
35231621 | 13 | 1.3655 | 1.3655 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 0 | 7210 | 0 | 0 | Underground | Scoping | Top 250 Miles
35231622 | 13 | 2.8339 | 2.8339 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 0 | 0 | 0 | 14963 | Remote Grid / Removal | Scoping | Top 250 Miles
35231623 | 13 | 1.3784 | 1.3784 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 1078 | 0 | 0 | 6200 | Remote Grid / Removal | Scoping | Top 250 Miles
35231624 | 13 | 0.77576 | 0.77576 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 4096 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35231625 | 13 | 0.7392 | 0.7392 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 0 | 0 | 0 | 3903 | Remote Grid / Removal | Scoping | Top 250 Miles
35231626 | 13 | 0.68314 | 0.68314 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 3607 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35231627 | 13 | 0.39867 | 0.39867 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 2105 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35231628 | 13 | 7.2661 | 7.2661 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 7861 | 0 | 0 | 30504 | Remote Grid / Removal | Scoping | Top 250 Miles
35231629 | 13 | 1.3808 | 1.3808 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 902 | 0 | 0 | 6388.8 | Remote Grid / Removal | Scoping | Top 250 Miles
35231630 | 13 | 0.36345 | 0.36345 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 1919 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35231631 | 13 | 0.46686 | 0.46686 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 2465 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35219260 | 15 | 0.84432 | 0.84432 | 0 | WYANDOTTE 1109 | WYANDOTTE 110932586 | 15 | 1.3417 | 29 | 7.9481 | 0.52987 | Tier 2 | 4458 | 0 | 0 | 0 | Overhead | Estimating | Top 250 Miles
35219266 | 15 | 2.6 | 2.6 | 0 | MARIPOSA 2102 | MARIPOSA 2102CB | 31 | 5.2539 | 35 | 14.6212 | 0.47165 | Tier 2 | 13728 | 0 | 0 | 0 | Overhead | Estimating | Top 250 Miles
35227263 | 14 | 0.25 | 0.25 | 0 | MARIPOSA 2102 | MARIPOSA 2102CB | 31 | 5.2539 | 35 | 14.6212 | 0.47165 | Tier 2 | 1320 | 0 | 0 | 0 | Overhead | Estimating | Top 250 Miles
35219268 | 14 | 1.6212 | 1.6212 | 0 | MARIPOSA 2101 | MARIPOSA 210197142 | 40 | 4.6029 | 36 | 18.8487 | 0.47122 | Tier 2 | 8560 | 0 | 0 | 0 | Overhead | Estimating | Top 250 Miles
35226241 | 15 | 1.4799 | 1.4799 | 0 | MARIPOSA 2101 | MARIPOSA 210197142 | 40 | 4.6029 | 36 | 18.8487 | 0.47122 | Tier 2 | 7814 | 0 | 0 | 0 | Overhead | Estimating | Top 250 Miles
35226240 | 18 | 1.4625 | 1.4625 | 0 | MARIPOSA 2101 | MARIPOSA 210197142 | 40 | 4.6029 | 36 | 18.8487 | 0.47122 | Tier 2 | 7722 | 0 | 0 | 0 | Overhead | Dependencies | Top 250 Miles
35238567 | 14 | 0 | 0 | 0 | MARIPOSA 2101 | MARIPOSA 210197142 | 40 | 4.6029 | 36 | 18.8487 | 0.47122 | Tier 2 | 0 | 0 | 0 | 0 | TBD | Estimating | Top 250 Miles
35219269 | 10 | 2.14 | 2.14 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 11299.2 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35237258 | 10 | 2.15 | 2.15 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 11352 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35237259 | 10 | 3.2 | 3.2 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 16896 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35237360 | 10 | 3.01 | 3.01 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 15892.8 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35237361 | 10 | 2.87 | 2.87 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 15153.6 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35237364 | 10 | 3.03 | 3.03 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 15998.4 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35237365 | 10 | 2.81 | 2.81 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 14836.8 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35237366 | 10 | 2.19 | 2.19 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 11563.2 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35237368 | 10 | 2.93 | 2.93 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 15470.4 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35237369 | 10 | 2.38 | 2.38 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 12566.4 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35237370 | 10 | 3.53 | 3.53 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 18638.4 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35237371 | 10 | 0.34 | 0.34 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 1795.2 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35219272 | 14 | 0.85436 | 0.85436 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101481876 | 14 | 0.8534 | 38 | 6.5476 | 0.46769 | Tier 2 & 3 | 4511 | 0 | 0 | 0 | Overhead | Estimating | Top 250 Miles
35219273 | 14 | 3.461 | 3.461 | 0 | VOLTA 1101 | VOLTA 110149742 | 28 | 3.4766 | 39 | 13.0013 | 0.46433 | Tier 2 | 18274 | 0 | 0 | 0 | Overhead | Estimating | Top 250 Miles
35219275 | 18 | 0.52 | 0.52 | 0 | PUTAH CREEK 1102 | PUTAH CREEK 110246012 | 38 | 0.63713 | 41 | 17.3115 | 0.45557 | Tier 2 | 2745.6 | 0 | 0 | 0 | Overhead | Dependencies | Top 250 Miles
35219276 | 13 | 2.16 | 2.16 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 0 | 11404.8 | 0 | 0 | Underground | Scoping | Top 250 Miles
35227651 | 13 | 2.31 | 2.31 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 12196.8 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35227652 | 13 | 0.41 | 0.41 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 0 | 2164.8 | 0 | 0 | Underground | Scoping | Top 250 Miles
35227653 | 13 | 2 | 2 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 10560 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35227654 | 13 | 0.72 | 0.72 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 3801.6 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35224378 | 13 | 3.14 | 3.14 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 16579.2 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35227870 | 13 | 1.42 | 1.42 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 316.8 | 7180.8 | 0 | 0 | Hybrid | Scoping | Top 250 Miles
35227656 | 13 | 1.33 | 1.33 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 1742.4 | 5280 | 0 | 0 | Hybrid | Scoping | Top 250 Miles
35227657 | 13 | 0.46 | 0.46 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 2428.8 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35227658 | 13 | 0.54 | 0.54 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 1478.4 | 1372.8 | 0 | 0 | Hybrid | Scoping | Top 250 Miles
35227659 | 13 | 0.24 | 0.24 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 1267.2 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35219280 | 13 | 0.15152 | 0.15152 | 0 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110564118 | 101 | 1.6451 | 43 | 44.7046 | 0.44262 | Tier 2 | 0 | 800 | 0 | 0 | Underground | Scoping | Top 250 Miles
35226632 | 13 | 1.6828 | 1.6828 | 0 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110564118 | 101 | 1.6451 | 43 | 44.7046 | 0.44262 |  | 8885 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35232651 | 13 | 1.74 | 1.74 | 0 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | 58 | 5.7104 | 45 | 25.2473 | 0.4353 |  | 9187 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35219286 | 13 | 3.4547 | 3.4547 | 0 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | Tier 2 | 18241 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35232960 | 13 | 3.0411 | 3.0411 | 0 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | Tier 2 | 16057 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35225825 | 13 | 1.5562 | 1.5562 | 0 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | Tier 2 | 8217 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35232442 | 13 | 3.0778 | 3.0778 | 0 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | Tier 2 | 16251 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35232443 | 13 | 1.0356 | 1.0356 | 0 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | Tier 2 | 5468 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35232444 | 13 | 3.5318 | 3.5318 | 0 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | Tier 2 | 18648 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35232445 | 13 | 2.6038 | 2.6038 | 0 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | Tier 2 | 13748 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35219289 | 13 | 4.3544 | 4.3544 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 22991 | 0 | 0 | Underground | Scoping | Top 250 Miles
35233947 | 13 | 1.8436 | 1.8436 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 9734 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35233948 | 13 | 2.5871 | 2.5871 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 13660 | 0 | 0 | Underground | Scoping | Top 250 Miles
35233949 | 13 | 1.9769 | 1.9769 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 10438 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35233950 | 13 | 2.7542 | 2.7542 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 14542 | 0 | 0 | Underground | Scoping | Top 250 Miles
35233951 | 13 | 1.5648 | 1.5648 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 8262 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35225826 | 13 | 2.5424 | 2.5424 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 13424 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35233952 | 13 | 2.1616 | 2.1616 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 11413 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35233953 | 13 | 0.84034 | 0.84034 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 4437 | 0 | 0 | Underground | Scoping | Top 250 Miles
35233955 | 13 | 0.54924 | 0.54924 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 2900 | 0 | 0 | Underground | Scoping | Top 250 Miles
35233957 | 13 | 0.10208 | 0.10208 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 539 | 0 | 0 | Underground | Scoping | Top 250 Miles
35233959 | 13 | 0.34602 | 0.34602 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 1827 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35234381 | 13 | 1.5468 | 1.5468 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 8167 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35234382 | 13 | 1.5875 | 1.5875 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 8382 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35225827 | 13 | 0.84564 | 0.84564 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 4465 | 0 | 0 | Underground | Scoping | Top 250 Miles
35233954 | 13 | 0.21212 | 0.21212 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 1120 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35233956 | 13 | 0.25455 | 0.25455 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 1344 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35233958 | 13 | 0.20814 | 0.20814 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 1099 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35234380 | 13 | 2.2419 | 2.2419 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 11837 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35234383 | 13 | 1.1985 | 1.1985 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 6328 | 0 | 0 | Underground | Scoping | Top 250 Miles
35234384 | 13 | 0.058144 | 0.058144 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 307 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35234385 | 13 | 0.67443 | 0.67443 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 3561 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35234386 | 13 | 0.85777 | 0.85777 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 4529 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35225828 | 13 | 2.5314 | 2.5314 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 13366 | 0 | 0 | Underground | Scoping | Top 250 Miles
35234387 | 13 | 0.93996 | 0.93996 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 4963 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35234388 | 13 | 2.0402 | 2.0402 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 10772 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35234389 | 13 | 0.9 | 0.9 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 4752 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35234390 | 13 | 0.52008 | 0.52008 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 2746 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35234391 | 13 | 1.26 | 1.26 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 6653 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35234392 | 13 | 1.66 | 1.66 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 8765 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35225829 | 13 | 2.19 | 2.19 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 11563.2 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35234393 | 13 | 2.42 | 2.42 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 12777.6 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35234394 | 13 | 2.3858 | 2.3858 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 9451.2 | 0 | 3146 | 0 | Remote Grid / Removal | Scoping | Top 250 Miles
35234395 | 13 | 2.71 | 2.71 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 14308.8 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35234396 | 13 | 1.69 | 1.69 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 8923.2 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35234397 | 13 | 0.72 | 0.72 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 3801.6 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35219287 | 11 | 2.3962 | 2.3962 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 12652 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35234398 | 11 | 2.8525 | 2.8525 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 15061 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35234399 | 11 | 0.48011 | 0.48011 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 2535 | 0 | 0 | Underground | Scoping | Top 250 Miles
35234400 | 11 | 1.39 | 1.39 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 7339 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35234401 | 11 | 1.85 | 1.85 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 9768 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35219267 | 9 | 4.27 | 4.27 | 0 | MARIPOSA 2102 | MARIPOSA 2102440236 | 38 | 4.2727 | 50 | 15.979 | 0.4205 | Tier 2 & 3 | 22545.6 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35219587 | 9 | 2.16 | 2.16 | 0 | MARIPOSA 2102 | MARIPOSA 2102440236 | 38 | 4.2727 | 50 | 15.979 | 0.4205 |  | 11404.8 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35219588 | 9 | 2.16 | 2.16 | 0 | MARIPOSA 2102 | MARIPOSA 2102440236 | 38 | 4.2727 | 50 | 15.979 | 0.4205 |  | 11404.8 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35219589 | 13 | 2.81 | 2.81 | 0 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | Tier 2 | 14836.8 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35224321 | 14 | 2.46 | 2.46 | 0 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | Tier 2 | 12988.8 | 0 | 0 | 0 | Overhead | Estimating | Top 250 Miles
35226798 | 13 | 1.72 | 1.72 | 0 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | Tier 2 | 9081.6 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35226799 | 13 | 0.19 | 0.19 | 0 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | Tier 2 | 1003.2 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35226900 | 13 | 0.69 | 0.69 | 0 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | Tier 2 | 3643.2 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35219590 | 10 | 0.75 | 0.75 | 0 | VACA DIXON 1105 | VACA DIXON 1105965390 | 21 | 0.75147 | 53 | 8.6971 | 0.41415 | Tier 2 | 3960 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35219591 | 11 | 1.34 | 1.34 | 0 | OLETA 1101 | OLETA 1101754718 | 29 | 2.8841 | 54 | 11.8066 | 0.40712 |  | 7075.2 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35236662 | 11 | 1.67 | 1.67 | 0 | OLETA 1101 | OLETA 1101754718 | 29 | 2.8841 | 54 | 11.8066 | 0.40712 |  | 8817.6 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35192053 | 20 | 2.19 | 0 | 2.19 | OAKHURST 1103 | OAKHURST 11035120 | 19 | 6.1606 | 1975 | 0.18333 | 0.0096488 | Tier 3 | 10401.6 | 0 | 0 | 0 | Overhead | Construction | Storm Rebuild
35227096 | 20 | 1.09 | 0 | 1.09 | OAKHURST 1103 | OAKHURST 11035120 | 19 | 6.1606 | 1975 | 0.18333 | 0.0096488 | Tier 3 | 5598 | 0 | 0 | 0 | Overhead | Construction | Storm Rebuild
35227201 | 20 | 0.95 | 0 | 0.95 | OAKHURST 1103 | OAKHURST 11035120 | 19 | 6.1606 | 1975 | 0.18333 | 0.0096488 | Tier 3 | 4355 | 0 | 0 | 0 | Overhead | Construction | Storm Rebuild
35228449 | 19 | 2.8937 | 0.08375 | 2.81 | RIO DELL 1102 | Rio Dell 11024230 | 59 | 22.9009 | 585 | 7.9721 | 0.13512 | Tier 2 | 15279 | 0 | 0 | 0 | Overhead | Construction | Storm Rebuild
35056733 | 18 | 2.13 | 2.13 | 0 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | Tier 3 | 11246.4 | 0 | 0 | 0 | Overhead | Dependencies | PSS Approved
35109541 | 14 | 2.67 | 2.67 | 0 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | Tier 3 | 14097.6 | 0 | 0 | 0 | Overhead | Estimating | PSS Approved
35057010 | 14 | 10.8799 | 10.8799 | 0 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | Tier 3 | 57446 | 0 | 0 | 0 | Overhead | Estimating | PSS Approved
35109546 | 15 | 2.77 | 2.77 | 0 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | Tier 3 | 14625 | 0 | 0 | 0 | Overhead | Estimating | PSS Approved
35057018 | 18 | 2.2511 | 2.2511 | 0 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | Tier 3 | 507 | 11379 | 0 | 0 | Hybrid | Dependencies | PSS Approved
31272374 |  | 0 | 0 | 0 | POINT MORETTI 1101 | POINT MORETTI 11015076 | 67 | 7.4948 | 1393 | 2.2618 | 0.033758 |  | 0 | 0 | 0 | 0 | TBD | Scoping | DSDD
35114040 | 20 | 1.4847 | 1.4847 | 0 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | Tier 3 | 7839 | 0 | 0 | 0 | Overhead | Construction | In-Construction
35052737 | 18 | 1.5867 | 1.5867 | 0 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | Tier 3 | 8378 | 0 | 0 | 0 | Overhead | Dependencies | DSDD
35192280 | 14 | 1.643 | 1.643 | 0 | CLAYTON 2212 | CLAYTON 221296224 | 174 | 19.3992 | 377 | 32.6329 | 0.18755 | Tier 3 | 0 | 8675 | 0 | 0 | Underground | Estimating | ECOP
35225589 | 14 | 1.0983 | 1.0983 | 0 | KONOCTI 1102 | KONOCTI 1102965078 | 59 | 6.2704 | 9 | 51.7008 | 0.87629 | Tier 3 | 5799 | 0 | 0 | 0 | Overhead | Estimating | Top 50 Miles
35225591 | 14 | 1.4723 | 1.4723 | 0 | KONOCTI 1102 | KONOCTI 1102965078 | 59 | 6.2704 | 9 | 51.7008 | 0.87629 | Tier 3 | 4527 | 0 | 3247 | 0 | Remote Grid / Removal | Estimating | Top 50 Miles
35217268 | 14 | 0.25795 | 0.25795 | 0 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | 13 | 4.8008 | 11 | 9.5539 | 0.73491 | Tier 2 & 3 | 1158 | 204 | 0 | 0 | Hybrid | Estimating | Top 50 Miles
35224712 | 14 | 3.2869 | 3.2869 | 0 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | 13 | 4.8008 | 11 | 9.5539 | 0.73491 | Tier 2 & 3 | 1222 | 16133 | 0 | 0 | Hybrid | Estimating | Top 50 Miles
35224713 | 14 | 1.8655 | 1.8655 | 0 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | 13 | 4.8008 | 11 | 9.5539 | 0.73491 | Tier 2 & 3 | 160 | 9690 | 0 | 0 | Hybrid | Estimating | Top 50 Miles
35062375 | 14 | 1.0902 | 1.0902 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 0 | 5756 | 0 | 0 | Underground | Estimating | Top 20% MAVF CPZ
35191319 | 13 | 1.1705 | 1.1705 | 0 | LAS GALLINAS A 1105 | LAS GALLINAS A 110599904 | 54 | 5.5621 | 215 | 13.5032 | 0.25006 | Tier 3 | 0 | 6180 | 0 | 0 | Underground | Scoping | ECOP
35223615 | 13 | 1.6258 | 1.6258 | 0 | LAS GALLINAS A 1105 | LAS GALLINAS A 110599904 | 54 | 5.5621 | 215 | 13.5032 | 0.25006 | Tier 3 | 0 | 8584 | 0 | 0 | Underground | Scoping | ECOP
35227030 | 13 | 1.7072 | 1.7072 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 2233 | 6781 | 0 | 0 | Hybrid | Scoping | ECOP
35227031 | 13 | 2.03 | 2.03 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 2534.4 | 8184 | 0 | 0 | Hybrid | Scoping | ECOP
35192282 | 13 | 2.2621 | 2.2621 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 0 | 11944 | 0 | 0 | Underground | Scoping | ECOP
35226621 | 13 | 2.6562 | 2.6562 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 2941 | 11084 | 0 | 0 | Hybrid | Scoping | ECOP
35192292 | 13 | 0.95114 | 0.95114 | 0 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | Tier 3 | 830 | 4192 | 0 | 0 | Hybrid | Scoping | ECOP
35225594 | 13 | 0.5286 | 0.5286 | 0 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | Tier 3 | 261 | 2530 | 0 | 0 | Hybrid | Scoping | ECOP
35174478 | 13 | 1.79 | 1.79 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 9451.2 | 0 | 0 | Underground | Scoping | ECOP
35226857 | 13 | 1.94 | 1.94 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 10243.2 | 0 | 0 | Underground | Scoping | ECOP
35226858 | 14 | 0.74295 | 0.74295 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 1900.8 | 0 | 2022 | 0 | Remote Grid / Removal | Estimating | ECOP
35226859 | 14 | 0.88 | 0.88 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 4646.4 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35226861 | 14 | 0.75 | 0.75 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 3960 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35226862 | 14 | 0.58 | 0.58 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 3062.4 | 0 | 0 | 0 | Overhead | Estimating | ECOP
35174501 | 13 | 1.683 | 1.683 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 8886 | 0 | 0 | Underground | Scoping | ECOP
35227007 | 13 | 1.1288 | 1.1288 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 5960 | 0 | 0 | Underground | Scoping | ECOP
35227010 | 13 | 0.15985 | 0.15985 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 844 | 0 | 0 | 0 | Overhead | Scoping | ECOP
35227013 | 13 | 0.026894 | 0.026894 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 142 | 0 | 0 | 0 | Overhead | Scoping | ECOP
35227015 | 13 | 0.95758 | 0.95758 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 5056 | 0 | 0 | 0 | Overhead | Scoping | ECOP
35227018 | 13 | 1.2 | 1.2 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 6336 | 0 | 0 | 0 | Overhead | Scoping | ECOP
35227021 | 13 | 0.21989 | 0.21989 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 1161 | 0 | 0 | 0 | Overhead | Scoping | ECOP
35227025 | 13 | 0.7536 | 0.7536 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 2259 | 1720 | 0 | 0 | Hybrid | Scoping | ECOP
35234756 | 13 | 2.782 | 2.782 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 14689 | 0 | 0 | Underground | Scoping | ECOP
35234758 | 13 | 0.58201 | 0.58201 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 3073 | 0 | 0 | Underground | Scoping | ECOP
35234862 | 13 | 0.079924 | 0.079924 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 422 | 0 | 0 | Underground | Scoping | ECOP
35234865 | 13 | 0.64754 | 0.64754 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 3419 | 0 | 0 | Underground | Scoping | ECOP
35192291 | 13 | 1.0972 | 1.0972 | 0 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | 541 | 44.1915 | 811 | 49.924 | 0.092281 | Tier 3 | 521 | 5272 | 0 | 0 | Hybrid | Scoping | ECOP
35191937 | 13 | 1.4528 | 1.4528 | 0 | PUEBLO 2102 | PUEBLO 2102792 | 180 | 19.3407 | 951 | 13.2101 | 0.073389 | Tier 3 | 7671 | 0 | 0 | 0 | Overhead | Scoping | ECOP
35227032 | 13 | 0.575 | 0.575 | 0 | PUEBLO 2102 | PUEBLO 2102792 | 180 | 19.3407 | 951 | 13.2101 | 0.073389 | Tier 3 | 3036 | 0 | 0 | 0 | Overhead | Scoping | ECOP
35227033 | 13 | 1.31 | 1.31 | 0 | PUEBLO 2102 | PUEBLO 2102792 | 180 | 19.3407 | 951 | 13.2101 | 0.073389 | Tier 3 | 0 | 0 | 0 | 6917 | Remote Grid / Removal | Scoping | ECOP
35219093 | 13 | 1.14 | 1.14 | 0 | TIDEWATER 2106 | TIDEWATER 210614072 | 30 | 3.6652 | 18 | 19.5994 | 0.65331 | Tier 2 | 0 | 6019.2 | 0 | 0 | Underground | Scoping | Top 50 Miles
35231543 | 13 | 1.3 | 1.3 | 0 | TIDEWATER 2106 | TIDEWATER 210614072 | 30 | 3.6652 | 18 | 19.5994 | 0.65331 | Tier 2 | 0 | 6864 | 0 | 0 | Underground | Scoping | Top 50 Miles
35217273 | 13 | 1.1055 | 1.1055 | 0 | UPPER LAKE 1101 | UPPER LAKE 1101CB | 3 | 1.1133 | 6 | 3.7676 | 1.2559 | Tier 2 | 240 | 0 | 5596.8 | 0 | Remote Grid / Removal | Scoping | Top 50 Miles
35217272 | 13 | 0.34053 | 0.34053 | 0 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | Tier 3 | 94 | 1704 | 0 | 0 | Hybrid | Scoping | Top 50 Miles
35226628 | 13 | 0.81913 | 0.81913 | 0 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | Tier 3 | 0 | 4325 | 0 | 0 | Underground | Scoping | Top 50 Miles
35226629 | 13 | 4.6972 | 4.6972 | 0 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | Tier 3 | 0 | 24801 | 0 | 0 | Underground | Scoping | Top 50 Miles
35217269 | 13 | 0.52083 | 0.52083 | 0 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | Tier 2 | 630 | 2120 | 0 | 0 | Hybrid | Scoping | Top 50 Miles
35226819 | 13 | 1.321 | 1.321 | 0 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | Tier 2 | 6975 | 0 | 0 | 0 | Overhead | Scoping | Top 50 Miles
35227160 | 13 | 2.843 | 2.843 | 0 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | Tier 2 | 176 | 14835 | 0 | 0 | Hybrid | Scoping | Top 50 Miles
35227161 | 13 | 0.73068 | 0.73068 | 0 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | Tier 2 | 3858 | 0 | 0 | 0 | Overhead | Scoping | Top 50 Miles
35227162 | 13 | 0.4178 | 0.4178 | 0 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | Tier 2 | 0 | 2206 | 0 | 0 | Underground | Scoping | Top 50 Miles
35227163 | 13 | 0.41117 | 0.41117 | 0 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | Tier 2 | 2171 | 0 | 0 | 0 | Overhead | Scoping | Top 50 Miles
35227164 | 13 | 0.5589 | 0.5589 | 0 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | Tier 2 | 2951 | 0 | 0 | 0 | Overhead | Scoping | Top 50 Miles
35217270 | 14 | 0.57614 | 0.57614 | 0 | KONOCTI 1102 | KONOCTI 1102965078 | 59 | 6.2704 | 9 | 51.7008 | 0.87629 | Tier 3 | 3042 | 0 | 0 | 0 | Overhead | Estimating | Top 50 Miles
35217271 | 13 | 2.8496 | 2.8496 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 0 | 15046 | 0 | 0 | Underground | Scoping | Top 50 Miles
35227864 | 13 | 1.8392 | 1.8392 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 0 | 9711 | 0 | 0 | Underground | Scoping | Top 50 Miles
35220895 | 13 | 2.1489 | 2.1489 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 1137 | 10209 | 0 | 0 | Hybrid | Scoping | Top 50 Miles
35228186 | 13 | 1.4847 | 1.4847 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 0 | 7839 | 0 | 0 | Underground | Scoping | Top 50 Miles
35220896 | 13 | 0.2803 | 0.2803 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 0 | 1480 | 0 | 0 | Underground | Scoping | Top 50 Miles
35227165 | 13 | 1.0112 | 1.0112 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 0 | 5339 | 0 | 0 | Underground | Scoping | Top 50 Miles
35227167 | 13 | 1.7975 | 1.7975 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 0 | 9491 | 0 | 0 | Underground | Scoping | Top 50 Miles
35227168 | 13 | 1.5741 | 1.5741 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 0 | 8311 | 0 | 0 | Underground | Scoping | Top 50 Miles
35062374 | 13 | 1.5352 | 1.5352 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 0 | 8106 | 0 | 0 | Underground | Scoping | Top 20% MAVF CPZ
35231608 | 14 | 0.16212 | 0.16212 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 856 | 0 | 0 | 0 | Overhead | Estimating | Top 20% MAVF CPZ
35226849 | 13 | 1.7833 | 1.7833 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 0 | 9416 | 0 | 0 | Underground | Scoping | Top 20% MAVF CPZ
35062376 | 13 | 4.3231 | 4.3231 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | Tier 3 | 0 | 22826 | 0 | 0 | Underground | Scoping | Top 20% MAVF CPZ
35219096 | 13 | 1.67 | 1.67 | 0 | KIRKER 2104 | KIRKER 2104442850 | 30 | 5.7542 | 21 | 18.4361 | 0.61454 | Tier 2 | 0 | 8817.6 | 0 | 0 | Underground | Scoping | Top 250 Miles
35227655 | 13 | 3.77 | 3.77 | 0 | KIRKER 2104 | KIRKER 2104442850 | 30 | 5.7542 | 21 | 18.4361 | 0.61454 | Tier 2 | 19905.6 | 0 | 0 | 0 | Overhead | Scoping | Top 250 Miles
35226700 | 13 | 0.45758 | 0.45758 | 0 | WYANDOTTE 1109 | WYANDOTTE 110932586 | 15 | 1.3417 | 29 | 7.9481 | 0.52987 | Tier 2 | 0 | 2416 | 0 | 0 | Underground | Scoping | Top 250 Miles
35219281 | 13 | 2.5 | 2.5 | 0 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | 58 | 5.7104 | 45 | 25.2473 | 0.4353 |  | 0 | 13200 | 0 | 0 | Underground | Scoping | Top 250 Miles
35232650 | 13 | 1.71 | 1.71 | 0 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | 58 | 5.7104 | 45 | 25.2473 | 0.4353 |  | 0 | 9029 | 0 | 0 | Underground | Scoping | Top 250 Miles
35240160 | 2 | 28.09 | 28.09 | 0 | COARSEGOLD 2104 | COARSEGOLD 21045310 | 299 | 28.0892 | 61 | 117.8076 | 0.39401 |  | 148315.2 | 0 | 0 | 0 | Overhead | Scoping | CWSP 2022-2023
35240162 | 2 | 0 | 0 | 0 | COARSEGOLD 2104 | COARSEGOLD 21045310 | 299 | 28.0892 | 61 | 117.8076 | 0.39401 |  | 0 | 0 | 0 | 0 | TBD | Scoping | CWSP 2022-2023
35240163 | 2 | 0 | 0 | 0 | COARSEGOLD 2104 | COARSEGOLD 21045310 | 299 | 28.0892 | 61 | 117.8076 | 0.39401 |  | 0 | 0 | 0 | 0 | TBD | Scoping | CWSP 2022-2023
35240164 | 2 | 2.03 | 2.03 | 0 | COARSEGOLD 2104 | COARSEGOLD 2104570682 | 26 | 2.0288 | 78 | 9.6995 | 0.37306 |  | 10718.4 | 0 | 0 | 0 | Overhead | Scoping | CWSP 2022-2023
35240165 | 2 | 10.68 | 10.68 | 0 | COARSEGOLD 2104 | COARSEGOLD 21046210 | 49 | 10.6757 | 132 | 14.9278 | 0.30465 |  | 56390.4 | 0 | 0 | 0 | Overhead | Scoping | CWSP 2022-2023
35240166 | 2 | 9.21 | 9.21 | 0 | VOLTA 1101 | VOLTA 1101CB | 80 | 9.2089 | 76 | 30.036 | 0.37545 |  | 48628.8 | 0 | 0 | 0 | Overhead | Scoping | CWSP 2022-2023
35240167 | 2 | 0 | 0 | 0 | VOLTA 1101 | VOLTA 1101CB | 80 | 9.2089 | 76 | 30.036 | 0.37545 |  | 0 | 0 | 0 | 0 | TBD | Scoping | CWSP 2022-2023
35240168 | 2 | 9.62 | 9.62 | 0 | VOLTA 1101 | VOLTA 110153118 | 47 | 9.6273 | 157 | 13.1375 | 0.27952 |  | 50793.6 | 0 | 0 | 0 | Overhead | Scoping | CWSP 2022-2023
35240169 | 2 | 23.11 | 23.11 | 0 | VOLTA 1101 | VOLTA 11011568 | 136 | 23.1053 | 85 | 49.2203 | 0.36191 |  | 122020.8 | 0 | 0 | 0 | Overhead | Scoping | CWSP 2022-2023
35240170 | 2 | 0 | 0 | 0 | VOLTA 1101 | VOLTA 11011568 | 136 | 23.1053 | 85 | 49.2203 | 0.36191 |  | 0 | 0 | 0 | 0 | TBD | Scoping | CWSP 2022-2023
35240171 | 2 | 0 | 0 | 0 | VOLTA 1101 | VOLTA 11011568 | 136 | 23.1053 | 85 | 49.2203 | 0.36191 |  | 0 | 0 | 0 | 0 | TBD | Scoping | CWSP 2022-2023
35240173 | 2 | 6.4 | 6.4 | 0 | PUTAH CREEK 1102 | PUTAH CREEK 11028352 | 133 | 6.4005 | 171 | 36.3202 | 0.27308 |  | 33792 | 0 | 0 | 0 | Overhead | Scoping | CWSP 2022-2023
35240174 | 2 | 0 | 0 | 0 | PUTAH CREEK 1102 | PUTAH CREEK 11028352 | 133 | 6.4005 | 171 | 36.3202 | 0.27308 |  | 0 | 0 | 0 | 0 | TBD | Scoping | CWSP 2022-2023
35240175 | 2 | 11.42 | 11.42 | 0 | PUTAH CREEK 1102 | PUTAH CREEK 110267858 | 107 | 11.4216 | 92 | 38.201 | 0.35702 |  | 60297.6 | 0 | 0 | 0 | Overhead | Scoping | CWSP 2022-2023
35240176 | 2 | 6 | 6 | 0 | PUTAH CREEK 1102 | PUTAH CREEK 110264044 | 46 | 5.9969 | 529 | 6.8236 | 0.14834 |  | 31680 | 0 | 0 | 0 | Overhead | Scoping | CWSP 2022-2023
35240177 | 2 | 0 | 0 | 0 | PUTAH CREEK 1102 | PUTAH CREEK 110264044 | 46 | 5.9969 | 529 | 6.8236 | 0.14834 |  | 0 | 0 | 0 | 0 | TBD | Scoping | CWSP 2022-2023
35240178 | 2 | 5.34 | 5.34 | 0 | PUTAH CREEK 1102 | PUTAH CREEK 1102710384 | 84 | 5.3351 | 418 | 14.6739 | 0.17469 |  | 28195.2 | 0 | 0 | 0 | Overhead | Scoping | CWSP 2022-2023
35240179 | 2 | 0.38 | 0.38 | 0 | SANTA YNEZ 1104 | SANTA YNEZ 1104CB | 105 | 0.035126 | 137 | 31.6947 | 0.30185 |  | 2006.4 | 0 | 0 | 0 | Overhead | Scoping | CWSP 2022-2023
35240220 | 2 | 15.65 | 15.65 | 0 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y04 | 238 | 15.6586 | 108 | 77.261 | 0.32463 |  | 82632 | 0 | 0 | 0 | Overhead | Scoping | CWSP 2022-2023
35240221 | 2 | 0 | 0 | 0 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y04 | 238 | 15.6586 | 108 | 77.261 | 0.32463 |  | 0 | 0 | 0 | 0 | TBD | Scoping | CWSP 2022-2023
35240222 | 2 | 16.94 | 16.94 | 0 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y66 | 138 | 16.9474 | 153 | 39.0253 | 0.28279 |  | 89443.2 | 0 | 0 | 0 | Overhead | Scoping | CWSP 2022-2023
35240223 | 2 | 0 | 0 | 0 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y66 | 138 | 16.9474 | 153 | 39.0253 | 0.28279 |  | 0 | 0 | 0 | 0 | TBD | Scoping | CWSP 2022-2023
35240224 | 2 | 11.96 | 11.96 | 0 | SANTA YNEZ 1104 | SANTA YNEZ 110477098 | 112 | 11.9643 | 308 | 23.5673 | 0.21042 |  | 63148.8 | 0 | 0 | 0 | Overhead | Scoping | CWSP 2022-2023
Totals |  | 830.2725 | [5 empty] | 9077.6335 |  | 25681.378 |  |  | 2622250.8 | 1287579 | 216651.2 | 255791

## HFTD CPZ
PZ_idx | circuit_protection_zone_id | feeder_id | feeder_name | Miles | pixel_count | mean_mavf_core_risk | Total Risk Value | mean_mavf_core_risk_rank | Cumulative Miles | Decreasing Risk | Project List | CPZs Approved
10544 | OREGON TRAIL 1103CUS391 | 103521103 | OREGON TRAIL 1103 | 0.022596 | 1 | 3.1639 | 3.1639 | 1 | 0.022596 | 24761.6364 | #N/A | 24761.6364
11024 | CALPINE 1144276-G | 48011144 | CALPINE 1144 | 0.014759 | 1 | 1.8786 | 1.8786 | 2 | 0.037356 | 24759.7577 | #N/A | 24759.7577
9665 | MARIPOSA 210190130 | 254452101 | MARIPOSA 2101 | 0.09394 | 1 | 1.6924 | 1.6924 | 3 | 0.1313 | 24758.0654 | #N/A | 24758.0654
9783 | SHEPHERD 2111688294 | 252062111 | SHEPHERD 2111 | 0.01514 | 1 | 1.4425 | 1.4425 | 4 | 0.14644 | 24756.6229 | #N/A | 24756.6229
10354 | MIDDLETOWN 1103CB | 43141103 | MIDDLETOWN 1103 | 0.052975 | 4 | 1.3006 | 5.2026 | 5 | 0.19941 | 24751.4203 | #N/A | 24751.4203
10600 | UPPER LAKE 1101CB | 42871101 | UPPER LAKE 1101 | 1.1133 | 3 | 1.2559 | 3.7676 | 6 | 1.3127 | 24747.6528 | 24747.6528 | #N/A
8894 | KESWICK 11011586 | 103451101 | KESWICK 1101 | 7.4478 | 39 | 1.2524 | 48.8434 | 7 | 8.7605 | 24698.8094 | 24698.8094 | #N/A
6776 | MIDDLETOWN 1102302610 | 43141102 | MIDDLETOWN 1102 | 4.7058 | 53 | 0.91632 | 48.565 | 8 | 13.4663 | 24650.2444 | 24650.2444 | #N/A
2373 | KONOCTI 1102965078 | 43311102 | KONOCTI 1102 | 6.2704 | 59 | 0.87629 | 51.7008 | 9 | 19.7367 | 24598.5436 | 24598.5436 | #N/A
5527 | MARIPOSA 2102241564 | 254452102 | MARIPOSA 2102 | 0.71281 | 14 | 0.77248 | 10.8148 | 10 | 20.4495 | 24587.7288 | 24587.7288 | #N/A
7968 | BUCKS CREEK 1101CB | 102211101 | BUCKS CREEK 1101 | 4.8008 | 13 | 0.73491 | 9.5539 | 11 | 25.2503 | 24578.1749 | 24578.1749 | #N/A
10918 | DEL MAR 2109378446 | 152582109 | DEL MAR 2109 | 0.098166 | 3 | 0.73151 | 2.1945 | 12 | 25.3484 | 24575.9804 | #N/A | 24575.9804
6966 | MIDDLETOWN 1102CB | 43141102 | MIDDLETOWN 1102 | 0.46739 | 12 | 0.72481 | 8.6977 | 13 | 25.8158 | 24567.2827 | #N/A | 24567.2827
3511 | MIDDLETOWN 1103830 | 43141103 | MIDDLETOWN 1103 | 27.7328 | 212 | 0.71618 | 151.8291 | 14 | 53.5487 | 24415.4536 | 24415.4536 | #N/A
9537 | POSO MOUNTAIN 2104CB | 253642104 | POSO MOUNTAIN 2104 | 5.3534 | 38 | 0.70423 | 26.7607 | 15 | 58.9021 | 24388.6929 | #N/A | 24388.6929
10827 | INDIAN FLAT 11044440 | 252691104 | INDIAN FLAT 1104 | 0.23386 | 4 | 0.68656 | 2.7463 | 16 | 59.136 | 24385.9466 | #N/A | 24385.9466
10242 | ELK CREEK 1101CB | 102781101 | ELK CREEK 1101 | 0.084235 | 1 | 0.67079 | 0.67079 | 17 | 59.2202 | 24385.2758 | #N/A | 24385.2758
5791 | TIDEWATER 210614072 | 14652106 | TIDEWATER 2106 | 3.6652 | 30 | 0.65331 | 19.5994 | 18 | 62.8854 | 24365.6765 | 24365.6765 | #N/A
10735 | HARTLEY 1101980662 | 43211101 | HARTLEY 1101 | 0.22763 | 3 | 0.64187 | 1.9256 | 19 | 63.113 | 24363.7509 | #N/A | 24363.7509
10532 | VACA DIXON 1101126774 | 63591101 | VACA DIXON 1101 | 0.78766 | 11 | 0.62029 | 6.8232 | 20 | 63.9007 | 24356.9277 | 24356.9277 | #N/A
10277 | KIRKER 2104442850 | 14452104 | KIRKER 2104 | 5.7542 | 30 | 0.61454 | 18.4361 | 21 | 69.6549 | 24338.4916 | 24338.4916 | #N/A
8742 | COARSEGOLD 2104CB | 254432104 | COARSEGOLD 2104 | 2.4277 | 27 | 0.59573 | 16.0848 | 22 | 72.0826 | 24322.4068 | 24322.4068 | #N/A
8905 | MIDDLETOWN 1101118494 | 43141101 | MIDDLETOWN 1101 | 1.0659 | 12 | 0.58092 | 6.971 | 23 | 73.1484 | 24315.4357 | 24315.4357 | #N/A
10515 | STAFFORD 1102784704 | 43201102 | STAFFORD 1102 | 0.027274 | 1 | 0.564 | 0.564 | 24 | 73.1757 | 24314.8717 | #N/A | 24314.8717
10181 | PEABODY 2108113684 | 63642108 | PEABODY 2108 | 0.36709 | 4 | 0.55276 | 2.211 | 25 | 73.5428 | 24312.6607 | #N/A | 24312.6607
7688 | PEABODY 2106250154 | 63642106 | PEABODY 2106 | 0.28499 | 4 | 0.55243 | 2.2097 | 26 | 73.8278 | 24310.451 | #N/A | 24310.451
7743 | HIGHLANDS 1102628 | 43361102 | HIGHLANDS 1102 | 14.2224 | 51 | 0.5487 | 27.9838 | 27 | 88.0502 | 24282.4672 | 24282.4672 | #N/A
6480 | TASSAJARA 21123202 | 14662112 | TASSAJARA 2112 | 0.39174 | 9 | 0.53731 | 4.8358 | 28 | 88.442 | 24277.6315 | #N/A | 24277.6315
10043 | WYANDOTTE 110932586 | 102911109 | WYANDOTTE 1109 | 1.3417 | 15 | 0.52987 | 7.9481 | 29 | 89.7837 | 24269.6834 | 24269.6834 | #N/A
10052 | POSO MOUNTAIN 2103CB | 253642103 | POSO MOUNTAIN 2103 | 2.3287 | 10 | 0.51619 | 5.1619 | 30 | 92.1124 | 24264.5215 | #N/A | 24264.5215
10924 | CALPINE 1146200-G | 48011146 | CALPINE 1146 | 0.0085246 | 1 | 0.50979 | 0.50979 | 31 | 92.121 | 24264.0117 | #N/A | 24264.0117
11090 | CALPINE 1146394G | 48011146 | CALPINE 1146 | 0.011292 | 1 | 0.50979 | 0.50979 | 32 | 92.1323 | 24263.5019 | #N/A | 24263.5019
4828 | CRESTA 1101546650 | 102251101 | CRESTA 1101 | 0.89694 | 6 | 0.50291 | 3.0174 | 33 | 93.0292 | 24260.4844 | #N/A | 24260.4844
9923 | CLOVERDALE 110247214 | 42821102 | CLOVERDALE 1102 | 0.027329 | 1 | 0.48427 | 0.48427 | 34 | 93.0565 | 24260.0002 | #N/A | 24260.0002
8034 | MARIPOSA 2102CB | 254452102 | MARIPOSA 2102 | 5.2539 | 31 | 0.47165 | 14.6212 | 35 | 98.3104 | 24245.379 | 24245.379 | #N/A
7873 | MARIPOSA 210197142 | 254452101 | MARIPOSA 2101 | 4.6029 | 40 | 0.47122 | 18.8487 | 36 | 102.9133 | 24226.5303 | 24226.5303 | #N/A
4526 | VACA DIXON 110540092 | 63591105 | VACA DIXON 1105 | 23.1653 | 464 | 0.46772 | 217.022 | 37 | 126.0786 | 24009.5083 | 24009.5083 | #N/A
2215 | MIDDLETOWN 1101481876 | 43141101 | MIDDLETOWN 1101 | 0.8534 | 14 | 0.46769 | 6.5476 | 38 | 126.932 | 24002.9607 | 24002.9607 | #N/A
9655 | VOLTA 110149742 | 102541101 | VOLTA 1101 | 3.4766 | 28 | 0.46433 | 13.0013 | 39 | 130.4086 | 23989.9594 | 23989.9594 | #N/A
10699 | SUNOL 110148180 | 14241101 | SUNOL 1101 | 0.013145 | 2 | 0.46103 | 0.92206 | 40 | 130.4218 | 23989.0374 | #N/A | 23989.0374
7414 | PUTAH CREEK 110246012 | 63681102 | PUTAH CREEK 1102 | 0.63713 | 38 | 0.45557 | 17.3115 | 41 | 131.0589 | 23971.7259 | 23971.7259 | #N/A
4076 | VACAVILLE 11046542 | 63601104 | VACAVILLE 1104 | 14.6602 | 140 | 0.44642 | 62.4985 | 42 | 145.719 | 23909.2273 | 23909.2273 | #N/A
7056 | POTTER VALLEY P H 110564118 | 42281105 | POTTER VALLEY P H 1105 | 1.6451 | 101 | 0.44262 | 44.7046 | 43 | 147.3641 | 23864.5228 | 23864.5228 | #N/A
10934 | POINT MORETTI 1101CB | 82931101 | POINT MORETTI 1101 | 0.012787 | 1 | 0.44218 | 0.44218 | 44 | 147.3769 | 23864.0806 | #N/A | 23864.0806
5032 | MOUNTAIN QUARRIES 21016953 | 152282101 | MOUNTAIN QUARRIES 2101 | 5.7104 | 58 | 0.4353 | 25.2473 | 45 | 153.0873 | 23838.8333 | 23838.8333 | #N/A
9729 | BRENTWOOD 210596324 | 14592105 | BRENTWOOD 2105 | 0.48214 | 6 | 0.4317 | 2.5902 | 46 | 153.5694 | 23836.2431 | #N/A | 23836.2431
6662 | NORTH DUBLIN 2101CB | 14052101 | NORTH DUBLIN 2101 | 1.7629 | 23 | 0.42859 | 9.8576 | 47 | 155.3324 | 23826.3855 | #N/A | 23826.3855
1690 | DESCHUTES 11049718 | 103351104 | DESCHUTES 1104 | 18.6049 | 357 | 0.42526 | 151.8163 | 48 | 173.9373 | 23674.5692 | 23674.5692 | #N/A
193 | OREGON TRAIL 110335002 | 103521103 | OREGON TRAIL 1103 | 57.1429 | 641 | 0.42185 | 270.4028 | 49 | 231.0802 | 23404.1664 | 23404.1664 | #N/A
7274 | MARIPOSA 2102440236 | 254452102 | MARIPOSA 2102 | 4.2727 | 38 | 0.4205 | 15.979 | 50 | 235.3529 | 23388.1874 | 23388.1874 | #N/A
10024 | CLEAR LAKE 1101881362 | 42141101 | CLEAR LAKE 1101 | 0.29834 | 10 | 0.41959 | 4.1959 | 51 | 235.6513 | 23383.9915 | #N/A | 23383.9915
7141 | WILDWOOD 11011454 | 103611101 | WILDWOOD 1101 | 7.8323 | 31 | 0.41883 | 12.9837 | 52 | 243.4835 | 23371.0078 | 23371.0078 | #N/A
7033 | VACA DIXON 1105965390 | 63591105 | VACA DIXON 1105 | 0.75147 | 21 | 0.41415 | 8.6971 | 53 | 244.235 | 23362.3107 | 23362.3107 | #N/A
9936 | OLETA 1101754718 | 163541101 | OLETA 1101 | 2.8841 | 29 | 0.40712 | 11.8066 | 54 | 247.1191 | 23350.5042 | 23350.5042 | #N/A
10113 | CALISTOGA 1101CB | 42711101 | CALISTOGA 1101 | 0.13777 | 9 | 0.40561 | 3.6505 | 55 | 247.2569 | 23346.8537 | #N/A | 23346.8537
9252 | STANISLAUS 1701CB | 162821701 | STANISLAUS 1701 | 6.8569 | 54 | 0.40353 | 21.7909 | 56 | 254.1138 | 23325.0628 | #N/A | #N/A
9014 | MARIPOSA 2101CB | 254452101 | MARIPOSA 2101 | 2.5043 | 34 | 0.39837 | 13.5444 | 57 | 256.6181 | 23311.5183 | #N/A | #N/A
4909 | HARTLEY 1101698 | 43211101 | HARTLEY 1101 | 6.8807 | 97 | 0.39723 | 38.5312 | 58 | 263.4988 | 23272.9871 | #N/A | #N/A
9239 | BANGOR 1101979830 | 103191101 | BANGOR 1101 | 0.42309 | 7 | 0.3972 | 2.7804 | 59 | 263.9219 | 23270.2067 | #N/A | #N/A
4242 | POTTER VALLEY P H 110495878 | 42281104 | POTTER VALLEY P H 1104 | 6.126 | 191 | 0.3965 | 75.7306 | 60 | 270.0479 | 23194.4761 | #N/A | #N/A
2058 | COARSEGOLD 21045310 | 254432104 | COARSEGOLD 2104 | 28.0892 | 299 | 0.39401 | 117.8076 | 61 | 298.1371 | 23076.6685 | 23076.6685 | #N/A
8298 | STAFFORD 1102361952 | 43201102 | STAFFORD 1102 | 1.3652 | 9 | 0.39288 | 3.536 | 62 | 299.5023 | 23073.1326 | #N/A | #N/A
1488 | AUBERRY 1101CB | 254151101 | AUBERRY 1101 | 18.1661 | 204 | 0.39206 | 79.9801 | 63 | 317.6684 | 22993.1524 | #N/A | #N/A
3596 | VACAVILLE 11088762 | 63601108 | VACAVILLE 1108 | 13.8344 | 147 | 0.39138 | 57.5327 | 64 | 331.5028 | 22935.6197 | #N/A | #N/A
6014 | OREGON TRAIL 11041634 | 103521104 | OREGON TRAIL 1104 | 18.0925 | 192 | 0.39094 | 75.0607 | 65 | 349.5953 | 22860.5591 | #N/A | #N/A
6392 | COARSEGOLD 210410335 | 254432104 | COARSEGOLD 2104 | 5.8229 | 69 | 0.39082 | 26.9663 | 66 | 355.4182 | 22833.5927 | #N/A | #N/A
7352 | JAMESON 1102865502 | 63801102 | JAMESON 1102 | 0.40084 | 27 | 0.38957 | 10.5185 | 67 | 355.819 | 22823.0743 | #N/A | #N/A
3943 | MOUNTAIN QUARRIES 2101CB | 152282101 | MOUNTAIN QUARRIES 2101 | 24.9941 | 262 | 0.38665 | 101.3032 | 68 | 380.8131 | 22721.7711 | 22721.7711 | #N/A
2633 | PASO ROBLES 1103N54 | 182611103 | PASO ROBLES 1103 | 20.0132 | 221 | 0.38568 | 85.2354 | 69 | 400.8263 | 22636.5357 | #N/A | #N/A
6808 | PHILO 110137222 | 42601101 | PHILO 1101 | 25.4153 | 152 | 0.3839 | 58.3523 | 70 | 426.2416 | 22578.1834 | #N/A | #N/A
8006 | RISING RIVER 11011532 | 103551101 | RISING RIVER 1101 | 3.8118 | 27 | 0.38077 | 10.2807 | 71 | 430.0534 | 22567.9027 | #N/A | #N/A
10120 | DEL MAR 210975802 | 152582109 | DEL MAR 2109 | 0.35808 | 6 | 0.37901 | 2.2741 | 72 | 430.4114 | 22565.6287 | #N/A | #N/A
8754 | NOTRE DAME 11042408 | 102041104 | NOTRE DAME 1104 | 11.5235 | 76 | 0.37815 | 28.7393 | 73 | 441.9349 | 22536.8893 | #N/A | #N/A
5603 | HIGHLANDS 1102623120 | 43361102 | HIGHLANDS 1102 | 6.5476 | 67 | 0.3774 | 25.2855 | 74 | 448.4825 | 22511.6038 | #N/A | #N/A
2079 | POTTER VALLEY P H 11051904 | 42281105 | POTTER VALLEY P H 1105 | 31.8476 | 332 | 0.37685 | 125.1141 | 75 | 480.3302 | 22386.4897 | #N/A | #N/A
8836 | VOLTA 1101CB | 102541101 | VOLTA 1101 | 9.2089 | 80 | 0.37545 | 30.036 | 76 | 489.5391 | 22356.4537 | 22356.4537 | #N/A
10966 | HICKS 2101984788 | 83432101 | HICKS 2101 | 0.0031475 | 1 | 0.37348 | 0.37348 | 77 | 489.5422 | 22356.0802 | #N/A | #N/A
6191 | COARSEGOLD 2104570682 | 254432104 | COARSEGOLD 2104 | 2.0288 | 26 | 0.37306 | 9.6995 | 78 | 491.571 | 22346.3807 | 22346.3807 | #N/A
8841 | NORTH DUBLIN 210311101 | 14052103 | NORTH DUBLIN 2103 | 3.6863 | 37 | 0.36793 | 13.6135 | 79 | 495.2573 | 22332.7673 | #N/A | #N/A
7776 | NORTH DUBLIN 21039473 | 14052103 | NORTH DUBLIN 2103 | 2.4179 | 27 | 0.36547 | 9.8678 | 80 | 497.6753 | 22322.8995 | #N/A | #N/A
9266 | WILLOW PASS 2107445650 | 13912107 | WILLOW PASS 2107 | 0.66278 | 5 | 0.36477 | 1.8239 | 81 | 498.3381 | 22321.0756 | #N/A | #N/A
2272 | MIDDLETOWN 1102414 | 43141102 | MIDDLETOWN 1102 | 5.9319 | 114 | 0.36434 | 41.5353 | 82 | 504.27 | 22279.5404 | #N/A | #N/A
3625 | CAYETANO 2109884904 | 14422109 | CAYETANO 2109 | 11.6368 | 77 | 0.36326 | 27.9711 | 83 | 515.9068 | 22251.5693 | #N/A | #N/A
10903 | PEABODY 2106592742 | 63642106 | PEABODY 2106 | 0.3398 | 5 | 0.36227 | 1.8113 | 84 | 516.2466 | 22249.7579 | #N/A | #N/A
5260 | VOLTA 11011568 | 102541101 | VOLTA 1101 | 23.1053 | 136 | 0.36191 | 49.2203 | 85 | 539.352 | 22200.5377 | 22200.5377 | #N/A
4693 | MIDDLETOWN 1101CB | 43141101 | MIDDLETOWN 1101 | 4.731 | 146 | 0.36174 | 52.8144 | 86 | 544.083 | 22147.7233 | 22147.7233 | #N/A
10547 | PASO ROBLES 1103N02 | 182611103 | PASO ROBLES 1103 | 0.044086 | 1 | 0.36094 | 0.36094 | 87 | 544.127 | 22147.3624 | #N/A | #N/A
2088 | COARSEGOLD 21035020 | 254432103 | COARSEGOLD 2103 | 16.1994 | 159 | 0.36009 | 57.2543 | 88 | 560.3265 | 22090.108 | #N/A | #N/A
7913 | JESSUP 11023105 | 103441102 | JESSUP 1102 | 6.0031 | 65 | 0.35978 | 23.3856 | 89 | 566.3296 | 22066.7225 | #N/A | #N/A
10257 | CAYETANO 2111389190 | 14422111 | CAYETANO 2111 | 2.2019 | 18 | 0.35946 | 6.4703 | 90 | 568.5315 | 22060.2522 | #N/A | #N/A
10351 | VACAVILLE 1109799940 | 63601109 | VACAVILLE 1109 | 0.59339 | 9 | 0.35844 | 3.2259 | 91 | 569.1249 | 22057.0263 | #N/A | #N/A
745 | PUTAH CREEK 110267858 | 63681102 | PUTAH CREEK 1102 | 11.4216 | 107 | 0.35702 | 38.201 | 92 | 580.5464 | 22018.8252 | 22018.8252 | #N/A
10611 | PEABODY 2113945670 | 63642113 | PEABODY 2113 | 0.20785 | 3 | 0.35536 | 1.0661 | 93 | 580.7543 | 22017.7592 | #N/A | #N/A
835 | ZACA 1102Y54 | 182681102 | ZACA 1102 | 34.0882 | 296 | 0.35181 | 104.1359 | 94 | 614.8425 | 21913.6233 | #N/A | #N/A
9806 | OLETA 1101CB | 163541101 | OLETA 1101 | 0.084664 | 2 | 0.35138 | 0.70277 | 95 | 614.9272 | 21912.9205 | #N/A | #N/A
7864 | SISQUOC 1103867486 | 182811103 | SISQUOC 1103 | 2.1165 | 20 | 0.35061 | 7.0121 | 96 | 617.0437 | 21905.9084 | #N/A | #N/A
10173 | CALPINE 1146400 | 48011146 | CALPINE 1146 | 3.1431 | 8 | 0.34896 | 2.7917 | 97 | 620.1868 | 21903.1167 | #N/A | #N/A
615 | KERCKHOFF 1101CB | 252561101 | KERCKHOFF 1101 | 17.0284 | 154 | 0.348 | 53.5915 | 98 | 637.2152 | 21849.5252 | #N/A | #N/A
1695 | DESCHUTES 110449024 | 103351104 | DESCHUTES 1104 | 16.5991 | 209 | 0.34786 | 72.7038 | 99 | 653.8143 | 21776.8214 | #N/A | #N/A
3728 | DESCHUTES 11041370 | 103351104 | DESCHUTES 1104 | 13.5869 | 272 | 0.34561 | 94.0068 | 100 | 667.4013 | 21682.8146 | #N/A | #N/A
10316 | CORNING 110135974 | 103331101 | CORNING 1101 | 0.2479 | 11 | 0.34404 | 3.7844 | 101 | 667.6492 | 21679.0302 | #N/A | #N/A
10256 | VACAVILLE 1104874798 | 63601104 | VACAVILLE 1104 | 0.41158 | 3 | 0.33623 | 1.0087 | 102 | 668.0608 | 21678.0215 | #N/A | #N/A
6277 | WILLITS 1103964 | 42661103 | WILLITS 1103 | 3.1073 | 41 | 0.33456 | 13.717 | 103 | 671.1681 | 21664.3045 | #N/A | #N/A
6777 | BELL 11085703 | 152701108 | BELL 1108 | 5.2984 | 96 | 0.33328 | 31.9947 | 104 | 676.4664 | 21632.3099 | #N/A | #N/A
10040 | PANORAMA 11021632 | 103461102 | PANORAMA 1102 | 8.5467 | 19 | 0.33244 | 6.3164 | 105 | 685.0131 | 21625.9934 | #N/A | #N/A
9960 | WILLITS 1103CB | 42661103 | WILLITS 1103 | 2.9857 | 44 | 0.32751 | 14.4105 | 106 | 687.9988 | 21611.583 | #N/A | #N/A
6501 | SAN MIGUEL 1104895760 | 182661104 | SAN MIGUEL 1104 | 9.1711 | 96 | 0.32643 | 31.3373 | 107 | 697.17 | 21580.2456 | #N/A | #N/A
4461 | SANTA YNEZ 1104Y04 | 182721104 | SANTA YNEZ 1104 | 15.6586 | 238 | 0.32463 | 77.261 | 108 | 712.8286 | 21502.9846 | 21502.9846 | #N/A
10609 | PEABODY 2106CB | 63642106 | PEABODY 2106 | 0.32679 | 9 | 0.32442 | 2.9197 | 109 | 713.1553 | 21500.0649 | #N/A | #N/A
3147 | HOPLAND 1101768 | 42251101 | HOPLAND 1101 | 16.9261 | 115 | 0.32431 | 37.2953 | 110 | 730.0814 | 21462.7695 | #N/A | #N/A
6991 | COVELO 1101478952 | 43061101 | COVELO 1101 | 0.71079 | 39 | 0.32368 | 12.6234 | 111 | 730.7922 | 21450.1461 | #N/A | #N/A
9010 | STAFFORD 11021202 | 43201102 | STAFFORD 1102 | 7.9017 | 41 | 0.32328 | 13.2544 | 112 | 738.694 | 21436.8917 | #N/A | #N/A
5081 | RED BLUFF 11041566 | 103541104 | RED BLUFF 1104 | 12.0889 | 94 | 0.3225 | 30.3149 | 113 | 750.7829 | 21406.5768 | #N/A | #N/A
9508 | ANDERSON 1101426745 | 103261101 | ANDERSON 1101 | 0.20439 | 3 | 0.32224 | 0.96673 | 114 | 750.9873 | 21405.6101 | #N/A | #N/A
10637 | SYCAMORE CREEK 1111153260 | 102971111 | SYCAMORE CREEK 1111 | 0.2638 | 2 | 0.32186 | 0.64373 | 115 | 751.2511 | 21404.9664 | #N/A | #N/A
3800 | DESCHUTES 11049726 | 103351104 | DESCHUTES 1104 | 15.6976 | 197 | 0.32131 | 63.2977 | 116 | 766.9487 | 21341.6686 | #N/A | #N/A
4142 | GIRVAN 1101323094 | 103401101 | GIRVAN 1101 | 36.1569 | 208 | 0.32037 | 66.6373 | 117 | 803.1056 | 21275.0313 | #N/A | #N/A
4869 | BELL 11082202 | 152701108 | BELL 1108 | 32.5292 | 363 | 0.32016 | 116.2183 | 118 | 835.6348 | 21158.813 | #N/A | #N/A
9492 | OLETA 1101296804 | 163541101 | OLETA 1101 | 3.2862 | 12 | 0.31954 | 3.8345 | 119 | 838.921 | 21154.9785 | #N/A | #N/A
10541 | CLARKSVILLE 2105CB | 153612105 | CLARKSVILLE 2105 | 0.80419 | 9 | 0.31824 | 2.8642 | 120 | 839.7252 | 21152.1143 | #N/A | #N/A
5372 | TEMPLETON 2113A20 | 183052113 | TEMPLETON 2113 | 7.4575 | 92 | 0.3179 | 29.2466 | 121 | 847.1827 | 21122.8677 | #N/A | #N/A
8293 | VACAVILLE 110838316 | 63601108 | VACAVILLE 1108 | 15.9209 | 232 | 0.31672 | 73.4796 | 122 | 863.1036 | 21049.3881 | #N/A | #N/A
907 | COTTONWOOD 1102544790 | 102931102 | COTTONWOOD 1102 | 16.3719 | 185 | 0.31273 | 57.8548 | 123 | 879.4755 | 20991.5333 | #N/A | #N/A
6176 | COARSEGOLD 21045525 | 254432104 | COARSEGOLD 2104 | 13.1465 | 175 | 0.31171 | 54.5497 | 124 | 892.622 | 20936.9836 | #N/A | #N/A
3989 | MIDDLETOWN 1102878 | 43141102 | MIDDLETOWN 1102 | 3.3752 | 49 | 0.31109 | 15.2435 | 125 | 895.9972 | 20921.7401 | #N/A | #N/A
2201 | RACETRACK 1704CB | 163761704 | RACETRACK 1704 | 22.8928 | 193 | 0.31093 | 60.0095 | 126 | 918.89 | 20861.7305 | #N/A | #N/A
4707 | HIGHLANDS 1103828 | 43361103 | HIGHLANDS 1103 | 8.5948 | 112 | 0.31086 | 34.8164 | 127 | 927.4847 | 20826.9141 | #N/A | #N/A
8759 | KERCKHOFF 1101R308 | 252561101 | KERCKHOFF 1101 | 3.8641 | 22 | 0.30901 | 6.7983 | 128 | 931.3489 | 20820.1158 | #N/A | #N/A
7918 | FORESTHILL 1102CB | 152181102 | FORESTHILL 1102 | 1.6448 | 13 | 0.30873 | 4.0135 | 129 | 932.9936 | 20816.1023 | #N/A | #N/A
9076 | SYCAMORE CREEK 1111976428 | 102971111 | SYCAMORE CREEK 1111 | 8.7518 | 82 | 0.30752 | 25.2165 | 130 | 941.7454 | 20790.8858 | #N/A | #N/A
6711 | PUTAH CREEK 110396792 | 63681103 | PUTAH CREEK 1103 | 3.9739 | 30 | 0.30689 | 9.2067 | 131 | 945.7193 | 20781.6791 | #N/A | #N/A
9779 | COARSEGOLD 21046210 | 254432104 | COARSEGOLD 2104 | 10.6757 | 49 | 0.30465 | 14.9278 | 132 | 956.3951 | 20766.7513 | 20766.7513 | #N/A
7407 | TEMPLETON 2113A12 | 183052113 | TEMPLETON 2113 | 40.3073 | 180 | 0.30414 | 54.7453 | 133 | 996.7024 | 20712.006 | #N/A | #N/A
6929 | CLARKSVILLE 2104CB | 153612104 | CLARKSVILLE 2104 | 8.8028 | 107 | 0.30391 | 32.5187 | 134 | 1005.5052 | 20679.4873 | #N/A | #N/A
8076 | NORTH DUBLIN 2103CB | 14052103 | NORTH DUBLIN 2103 | 13.884 | 147 | 0.30349 | 44.6134 | 135 | 1019.3892 | 20634.8739 | #N/A | #N/A
9798 | BALCH NO 1 1101CB | 252501101 | BALCH NO 1 1101 | 10.5522 | 33 | 0.30244 | 9.9805 | 136 | 1029.9414 | 20624.8934 | #N/A | #N/A
8821 | SANTA YNEZ 1104CB | 182721104 | SANTA YNEZ 1104 | 0.035126 | 105 | 0.30185 | 31.6947 | 137 | 1029.9765 | 20593.1987 | 20593.1987 | #N/A
12 | PASO ROBLES 1103N50 | 182611103 | PASO ROBLES 1103 | 2.2288 | 24 | 0.30039 | 7.2094 | 138 | 1032.2054 | 20585.9893 | #N/A | #N/A
461 | KONOCTI 1102354890 | 43311102 | KONOCTI 1102 | 9.3328 | 131 | 0.29712 | 38.9233 | 139 | 1041.5382 | 20547.0661 | #N/A | #N/A
4081 | OREGON TRAIL 11021382 | 103521102 | OREGON TRAIL 1102 | 5.4675 | 67 | 0.29503 | 19.7671 | 140 | 1047.0057 | 20527.299 | #N/A | #N/A
207 | AUBERRY 1102CB | 254151102 | AUBERRY 1102 | 34.7177 | 368 | 0.29173 | 107.3565 | 141 | 1081.7235 | 20419.9425 | #N/A | #N/A
929 | CORRAL 1101CB | 162991101 | CORRAL 1101 | 26.2967 | 280 | 0.29054 | 81.3506 | 142 | 1108.0201 | 20338.5918 | #N/A | #N/A
3287 | ANDERSON 11031600 | 103261103 | ANDERSON 1103 | 4.4944 | 106 | 0.2889 | 30.6232 | 143 | 1112.5145 | 20307.9686 | #N/A | #N/A
1107 | COARSEGOLD 210410030 | 254432104 | COARSEGOLD 2104 | 33.9336 | 227 | 0.28655 | 65.0478 | 144 | 1146.4481 | 20242.9208 | #N/A | #N/A
9519 | ARBUCKLE 1104669720 | 62081104 | ARBUCKLE 1104 | 2.245 | 22 | 0.28655 | 6.3042 | 145 | 1148.6932 | 20236.6166 | #N/A | #N/A
3809 | WISE 11022230 | 152271102 | WISE 1102 | 23.7482 | 278 | 0.28438 | 79.0585 | 146 | 1172.4414 | 20157.5581 | #N/A | #N/A
2464 | SHEPHERD 2111327814 | 252062111 | SHEPHERD 2111 | 11.5731 | 119 | 0.28428 | 33.8288 | 147 | 1184.0144 | 20123.7293 | #N/A | #N/A
3815 | PANORAMA 1102280170 | 103461102 | PANORAMA 1102 | 13.0164 | 102 | 0.28426 | 28.9943 | 148 | 1197.0308 | 20094.735 | #N/A | #N/A
10166 | TEMPLETON 21132949 | 183052113 | TEMPLETON 2113 | 0.47643 | 6 | 0.28416 | 1.7049 | 149 | 1197.5072 | 20093.03 | #N/A | #N/A
6611 | DESCHUTES 1101CB | 103351101 | DESCHUTES 1101 | 4.9829 | 118 | 0.28403 | 33.5157 | 150 | 1202.4902 | 20059.5143 | #N/A | #N/A
195 | COARSEGOLD 21045300 | 254432104 | COARSEGOLD 2104 | 55.8005 | 507 | 0.28372 | 143.8456 | 151 | 1258.2906 | 19915.6687 | #N/A | #N/A
5871 | FLINT 1101750 | 152531101 | FLINT 1101 | 4.5636 | 93 | 0.28318 | 26.3354 | 152 | 1262.8543 | 19889.3333 | #N/A | #N/A
952 | SANTA YNEZ 1104Y66 | 182721104 | SANTA YNEZ 1104 | 16.9474 | 138 | 0.28279 | 39.0253 | 153 | 1279.8017 | 19850.3081 | 19850.3081 | #N/A
1401 | SAN JOAQUIN #2 110310320 | 252521103 | SAN JOAQUIN #2 1103 | 11.785 | 133 | 0.28179 | 37.4782 | 154 | 1291.5867 | 19812.8299 | #N/A | #N/A
10123 | FULTON 110258990 | 42561102 | FULTON 1102 | 0.26599 | 6 | 0.28025 | 1.6815 | 155 | 1291.8527 | 19811.1484 | #N/A | #N/A
3591 | SANTA YNEZ 1101277014 | 182721101 | SANTA YNEZ 1101 | 5.5008 | 149 | 0.28002 | 41.7232 | 156 | 1297.3535 | 19769.4252 | #N/A | #N/A
2737 | VOLTA 110153118 | 102541101 | VOLTA 1101 | 9.6273 | 47 | 0.27952 | 13.1375 | 157 | 1306.9808 | 19756.2877 | 19756.2877 | #N/A
9393 | PUTAH CREEK 1103654021 | 63681103 | PUTAH CREEK 1103 | 0.2046 | 12 | 0.27878 | 3.3454 | 158 | 1307.1854 | 19752.9423 | #N/A | #N/A
5717 | SHINGLE SPRINGS 210935598 | 153652109 | SHINGLE SPRINGS 2109 | 10.847 | 122 | 0.27855 | 33.9836 | 159 | 1318.0323 | 19718.9587 | 19718.9587 | #N/A
1630 | OREGON TRAIL 11041574 | 103521104 | OREGON TRAIL 1104 | 16.9108 | 221 | 0.27852 | 61.5533 | 160 | 1334.9432 | 19657.4053 | #N/A | #N/A
2168 | HOPLAND 11014626 | 42251101 | HOPLAND 1101 | 27.0525 | 238 | 0.27841 | 66.2609 | 161 | 1361.9956 | 19591.1444 | #N/A | #N/A
10275 | SAN MIGUEL 1105873457 | 182661105 | SAN MIGUEL 1105 | 1.5169 | 18 | 0.27723 | 4.9901 | 162 | 1363.5125 | 19586.1543 | #N/A | #N/A
5141 | AUBERRY 1101R2578 | 254151101 | AUBERRY 1101 | 46.3393 | 506 | 0.27714 | 140.2335 | 163 | 1409.8519 | 19445.9209 | #N/A | #N/A
710 | COARSEGOLD 2103CB | 254432103 | COARSEGOLD 2103 | 38.4248 | 420 | 0.27679 | 116.2539 | 164 | 1448.2766 | 19329.667 | #N/A | #N/A
9397 | BEAR VALLEY 21059570 | 252192105 | BEAR VALLEY 2105 | 8.0496 | 59 | 0.27669 | 16.3249 | 165 | 1456.3262 | 19313.3421 | #N/A | #N/A
4772 | COARSEGOLD 2102CB | 254432102 | COARSEGOLD 2102 | 14.0441 | 79 | 0.2766 | 21.851 | 166 | 1470.3703 | 19291.4911 | #N/A | #N/A
11028 | NARROWS PH 1151CB | 153131151 | NARROWS PH 1151 | 0.17836 | 2 | 0.27613 | 0.55227 | 167 | 1470.5487 | 19290.9388 | #N/A | #N/A
5439 | KONOCTI 110264664 | 43311102 | KONOCTI 1102 | 27.7628 | 263 | 0.27567 | 72.501 | 168 | 1498.3115 | 19218.4378 | #N/A | #N/A
307 | MOUNTAIN QUARRIES 21011350 | 152282101 | MOUNTAIN QUARRIES 2101 | 21.7526 | 212 | 0.27537 | 58.3793 | 169 | 1520.0641 | 19160.0586 | #N/A | #N/A
8396 | NORTH DUBLIN 2101MR765 | 14052101 | NORTH DUBLIN 2101 | 2.0702 | 15 | 0.2736 | 4.104 | 170 | 1522.1343 | 19155.9545 | #N/A | #N/A
6379 | PUTAH CREEK 11028352 | 63681102 | PUTAH CREEK 1102 | 6.4005 | 133 | 0.27308 | 36.3202 | 171 | 1528.5348 | 19119.6343 | 19119.6343 | #N/A
7979 | KONOCTI 1102716 | 43311102 | KONOCTI 1102 | 15.342 | 109 | 0.27295 | 29.7514 | 172 | 1543.8768 | 19089.8829 | #N/A | #N/A
1249 | PENRYN 11032198 | 152561103 | PENRYN 1103 | 20.2312 | 248 | 0.27291 | 67.6807 | 173 | 1564.108 | 19022.2022 | #N/A | #N/A
10021 | OLETA 1101400470 | 163541101 | OLETA 1101 | 0.20759 | 3 | 0.27287 | 0.81862 | 174 | 1564.3156 | 19021.3836 | #N/A | #N/A
3674 | AUBERRY 1102R309 | 254151102 | AUBERRY 1102 | 8.5928 | 92 | 0.27286 | 25.1032 | 175 | 1572.9084 | 18996.2804 | #N/A | #N/A
1420 | MIDDLETOWN 1102998 | 43141102 | MIDDLETOWN 1102 | 14.8545 | 205 | 0.27124 | 55.6044 | 176 | 1587.7629 | 18940.676 | #N/A | #N/A
6398 | CAYETANO 2109MR572 | 14422109 | CAYETANO 2109 | 8.2926 | 80 | 0.27121 | 21.6967 | 177 | 1596.0555 | 18918.9793 | #N/A | #N/A
6361 | APPLE HILL 21026552 | 153662102 | APPLE HILL 2102 | 12.4854 | 139 | 0.2712 | 37.6964 | 178 | 1608.5409 | 18881.2829 | #N/A | #N/A
5677 | BANGOR 110180670 | 103191101 | BANGOR 1101 | 14.4199 | 158 | 0.27059 | 42.753 | 179 | 1622.9608 | 18838.5299 | #N/A | #N/A
7666 | JAMESON 1103118944 | 63801103 | JAMESON 1103 | 2.3449 | 41 | 0.27039 | 11.0862 | 180 | 1625.3058 | 18827.4438 | #N/A | #N/A
5313 | HIGHLANDS 1103482 | 43361103 | HIGHLANDS 1103 | 24.5081 | 188 | 0.26975 | 50.7128 | 181 | 1649.8138 | 18776.7309 | #N/A | #N/A
5299 | HIGGINS 1109CB | 152691109 | HIGGINS 1109 | 22.6477 | 254 | 0.26784 | 68.0313 | 182 | 1672.4615 | 18708.6996 | #N/A | #N/A
7848 | OAKHURST 1101636114 | 254421101 | OAKHURST 1101 | 20.4936 | 153 | 0.26702 | 40.8546 | 183 | 1692.9551 | 18667.8449 | #N/A | #N/A
10324 | SANTA YNEZ 1104564710 | 182721104 | SANTA YNEZ 1104 | 0.17013 | 7 | 0.26624 | 1.8637 | 184 | 1693.1252 | 18665.9812 | #N/A | #N/A
10018 | LINCOLN 1104275986 | 153701104 | LINCOLN 1104 | 0.58085 | 5 | 0.26526 | 1.3263 | 185 | 1693.7061 | 18664.6549 | #N/A | #N/A
5709 | HIGGINS 110950072 | 152691109 | HIGGINS 1109 | 42.3943 | 424 | 0.26524 | 112.4633 | 186 | 1736.1003 | 18552.1917 | #N/A | #N/A
3710 | MARIPOSA 210110070 | 254452101 | MARIPOSA 2101 | 26.137 | 249 | 0.2644 | 65.835 | 187 | 1762.2373 | 18486.3566 | #N/A | #N/A
3891 | MARIPOSA 210210880 | 254452102 | MARIPOSA 2102 | 39.6903 | 362 | 0.2637 | 95.458 | 188 | 1801.9276 | 18390.8986 | #N/A | #N/A
1822 | BELL 110750172 | 152701107 | BELL 1107 | 17.4906 | 210 | 0.2635 | 55.3341 | 189 | 1819.4182 | 18335.5645 | #N/A | #N/A
7084 | VACAVILLE 111113652 | 63601111 | VACAVILLE 1111 | 4.2976 | 58 | 0.26339 | 15.2768 | 190 | 1823.7158 | 18320.2877 | #N/A | #N/A
3429 | CLOVERDALE 1101399855 | 42821101 | CLOVERDALE 1101 | 2.7408 | 19 | 0.26331 | 5.0028 | 191 | 1826.4566 | 18315.2848 | #N/A | #N/A
9762 | HARTLEY 11014710 | 43211101 | HARTLEY 1101 | 1.5003 | 18 | 0.26308 | 4.7355 | 192 | 1827.9569 | 18310.5493 | #N/A | #N/A
2103 | DOBBINS 11011808 | 153741101 | DOBBINS 1101 | 15.5397 | 171 | 0.26282 | 44.9426 | 193 | 1843.4966 | 18265.6067 | #N/A | #N/A
3817 | DESCHUTES 11011380 | 103351101 | DESCHUTES 1101 | 17.8201 | 204 | 0.26207 | 53.462 | 194 | 1861.3167 | 18212.1447 | #N/A | #N/A
1392 | SAND CREEK 110345190 | 254601103 | SAND CREEK 1103 | 37.5908 | 416 | 0.26095 | 108.5552 | 195 | 1898.9075 | 18103.5895 | #N/A | #N/A
4741 | BRENTWOOD 2105B504R | 14592105 | BRENTWOOD 2105 | 8.7475 | 97 | 0.26071 | 25.289 | 196 | 1907.655 | 18078.3005 | #N/A | #N/A
7636 | VACA DIXON 110118292 | 63591101 | VACA DIXON 1101 | 0.045391 | 73 | 0.26015 | 18.9907 | 197 | 1907.7004 | 18059.3098 | #N/A | #N/A
4859 | OREGON TRAIL 1102CB | 103521102 | OREGON TRAIL 1102 | 9.3555 | 98 | 0.25991 | 25.4708 | 198 | 1917.0559 | 18033.839 | #N/A | #N/A
1063 | MARIPOSA 210110990 | 254452101 | MARIPOSA 2101 | 40.0451 | 390 | 0.25971 | 101.2865 | 199 | 1957.101 | 17932.5525 | #N/A | #N/A
9382 | CORNING 110185162 | 103331101 | CORNING 1101 | 5.7598 | 28 | 0.2589 | 7.2492 | 200 | 1962.8608 | 17925.3033 | #N/A | #N/A
1035 | CORRAL 110136652 | 162991101 | CORRAL 1101 | 36.1423 | 357 | 0.25884 | 92.4048 | 201 | 1999.003 | 17832.8985 | #N/A | #N/A
4603 | UPPER LAKE 1101660 | 42871101 | UPPER LAKE 1101 | 6.1619 | 91 | 0.25883 | 23.5531 | 202 | 2005.165 | 17809.3454 | #N/A | #N/A
521 | WILLITS 1103696 | 42661103 | WILLITS 1103 | 6.5038 | 87 | 0.25793 | 22.4395 | 203 | 2011.6688 | 17786.9059 | #N/A | #N/A
134 | SAN JOAQUIN #2 1103CB | 252521103 | SAN JOAQUIN #2 1103 | 67.9182 | 589 | 0.25597 | 150.7655 | 204 | 2079.587 | 17636.1404 | #N/A | #N/A
3686 | UKIAH 1111534 | 42771111 | UKIAH 1111 | 18.9138 | 142 | 0.25577 | 36.3189 | 205 | 2098.5008 | 17599.8215 | #N/A | #N/A
8712 | ELK CREEK 110193504 | 102781101 | ELK CREEK 1101 | 2.1512 | 15 | 0.25426 | 3.8139 | 206 | 2100.652 | 17596.0075 | #N/A | #N/A
10786 | PEABODY 2113873304 | 63642113 | PEABODY 2113 | 0.816 | 5 | 0.25419 | 1.2709 | 207 | 2101.468 | 17594.7366 | #N/A | #N/A
9423 | CLAY 110359714 | 163341103 | CLAY 1103 | 4.6637 | 34 | 0.25391 | 8.6328 | 208 | 2106.1317 | 17586.1038 | #N/A | #N/A
9267 | POTTER VALLEY P H 1105990354 | 42281105 | POTTER VALLEY P H 1105 | 0.1059 | 2 | 0.25341 | 0.50682 | 209 | 2106.2376 | 17585.597 | #N/A | #N/A
4480 | LUCERNE 1106526 | 43351106 | LUCERNE 1106 | 10.1036 | 100 | 0.25318 | 25.318 | 210 | 2116.3412 | 17560.279 | #N/A | #N/A
3034 | HOPLAND 1101558 | 42251101 | HOPLAND 1101 | 2.9946 | 72 | 0.25266 | 18.1915 | 211 | 2119.3358 | 17542.0874 | #N/A | #N/A
4451 | HIGHLANDS 1103568 | 43361103 | HIGHLANDS 1103 | 8.0426 | 118 | 0.25222 | 29.7625 | 212 | 2127.3784 | 17512.3249 | #N/A | #N/A
5062 | AUBERRY 1102R902 | 254151102 | AUBERRY 1102 | 15.0784 | 156 | 0.25137 | 39.2136 | 213 | 2142.4568 | 17473.1113 | #N/A | #N/A
5371 | SUNOL 1101MR169 | 14241101 | SUNOL 1101 | 3.0929 | 96 | 0.25044 | 24.0426 | 214 | 2145.5497 | 17449.0687 | #N/A | #N/A
8139 | LAS GALLINAS A 110599904 | 42991105 | LAS GALLINAS A 1105 | 5.5621 | 54 | 0.25006 | 13.5032 | 215 | 2151.1119 | 17435.5655 | 17435.5655 | #N/A
4462 | WILLITS 110337504 | 42661103 | WILLITS 1103 | 1.1752 | 41 | 0.24974 | 10.2392 | 216 | 2152.2871 | 17425.3263 | #N/A | #N/A
4593 | POSO MOUNTAIN 2101CB | 253642101 | POSO MOUNTAIN 2101 | 4.3034 | 22 | 0.24862 | 5.4697 | 217 | 2156.5905 | 17419.8566 | #N/A | #N/A
6909 | WYANDOTTE 1109702710 | 102911109 | WYANDOTTE 1109 | 2.6641 | 49 | 0.24845 | 12.174 | 218 | 2159.2546 | 17407.6826 | 17407.6826 | #N/A
9944 | WYANDOTTE 110366146 | 102911103 | WYANDOTTE 1103 | 0.15681 | 4 | 0.24793 | 0.99171 | 219 | 2159.4114 | 17406.6909 | #N/A | #N/A
10031 | SOLEDAD 2102346006 | 182052102 | SOLEDAD 2102 | 2.2688 | 5 | 0.24765 | 1.2382 | 220 | 2161.6802 | 17405.4527 | #N/A | #N/A
905 | CORNING 110290036 | 103331102 | CORNING 1102 | 13.4004 | 87 | 0.24724 | 21.5103 | 221 | 2175.0805 | 17383.9424 | #N/A | #N/A
5847 | OAKHURST 11035732 | 254421103 | OAKHURST 1103 | 3.3843 | 37 | 0.24719 | 9.1461 | 222 | 2178.4648 | 17374.7963 | #N/A | #N/A
5505 | MARIPOSA 210237282 | 254452102 | MARIPOSA 2102 | 53.7171 | 498 | 0.24522 | 122.1205 | 223 | 2232.1819 | 17252.6758 | #N/A | #N/A
4841 | OAKHURST 110363334 | 254421103 | OAKHURST 1103 | 17.2902 | 154 | 0.24446 | 37.6467 | 224 | 2249.4721 | 17215.0291 | #N/A | #N/A
8342 | BANGOR 110131502 | 103191101 | BANGOR 1101 | 11.8734 | 102 | 0.24429 | 24.9173 | 225 | 2261.3455 | 17190.1118 | #N/A | #N/A
9205 | POINT MORETTI 110135874 | 82931101 | POINT MORETTI 1101 | 0.20478 | 4 | 0.24298 | 0.97191 | 226 | 2261.5503 | 17189.1399 | #N/A | #N/A
2854 | SHINGLE SPRINGS 21099372 | 153652109 | SHINGLE SPRINGS 2109 | 17.8687 | 190 | 0.24281 | 46.1342 | 227 | 2279.419 | 17143.0056 | 17143.0056 | #N/A
10573 | GEYSERVILLE 1102756 | 42891102 | GEYSERVILLE 1102 | 0.58944 | 7 | 0.24238 | 1.6966 | 228 | 2280.0084 | 17141.309 | #N/A | #N/A
6313 | SAN MIGUEL 1104N60 | 182661104 | SAN MIGUEL 1104 | 8.2764 | 66 | 0.24236 | 15.9958 | 229 | 2288.2848 | 17125.3131 | #N/A | #N/A
2085 | LINCOLN 1104685276 | 153701104 | LINCOLN 1104 | 6.4838 | 216 | 0.24208 | 52.2897 | 230 | 2294.7686 | 17073.0234 | #N/A | #N/A
7825 | HORSESHOE 1101416226 | 152571101 | HORSESHOE 1101 | 0.11601 | 5 | 0.24182 | 1.2091 | 231 | 2294.8846 | 17071.8143 | #N/A | #N/A
9295 | BROWNS VALLEY 110117011 | 152921101 | BROWNS VALLEY 1101 | 1.8678 | 22 | 0.24153 | 5.3136 | 232 | 2296.7524 | 17066.5007 | #N/A | #N/A
1428 | ZACA 1102Y02 | 182681102 | ZACA 1102 | 10.449 | 158 | 0.24142 | 38.1442 | 233 | 2307.2014 | 17028.3565 | #N/A | #N/A
6825 | OLETA 1102186326 | 163541102 | OLETA 1102 | 11.8638 | 123 | 0.24114 | 29.6596 | 234 | 2319.0652 | 16998.6969 | #N/A | #N/A
7670 | STANISLAUS 1702CB | 162821702 | STANISLAUS 1702 | 8.1208 | 67 | 0.24096 | 16.1444 | 235 | 2327.186 | 16982.5525 | #N/A | #N/A
9773 | MADISON 2101117644 | 63172101 | MADISON 2101 | 0.67144 | 12 | 0.23987 | 2.8784 | 236 | 2327.8574 | 16979.6741 | #N/A | #N/A
10170 | PUTAH CREEK 1105617260 | 63681105 | PUTAH CREEK 1105 | 1.1665 | 15 | 0.2396 | 3.5941 | 237 | 2329.0239 | 16976.08 | #N/A | #N/A
10828 | BUELLTON 110163389 | 183041101 | BUELLTON 1101 | 0 | 2 | 0.23935 | 0.47871 | 238 | 2329.0239 | 16975.6013 | #N/A | #N/A
8291 | CLEAR LAKE 1102904 | 42141102 | CLEAR LAKE 1102 | 3.3845 | 30 | 0.23862 | 7.1587 | 239 | 2332.4084 | 16968.4425 | #N/A | #N/A
6235 | SHINGLE SPRINGS 210519522 | 153652105 | SHINGLE SPRINGS 2105 | 9.6738 | 113 | 0.23827 | 26.9251 | 240 | 2342.0822 | 16941.5175 | #N/A | #N/A
9843 | SUNOL 1101MR387 | 14241101 | SUNOL 1101 | 5.013 | 24 | 0.23776 | 5.7062 | 241 | 2347.0952 | 16935.8113 | #N/A | #N/A
109 | WISE 11022054 | 152271102 | WISE 1102 | 13.0143 | 147 | 0.23735 | 34.8898 | 242 | 2360.1095 | 16900.9214 | #N/A | #N/A
9387 | ANTELOPE 1101318686 | 252021101 | ANTELOPE 1101 | 1.4578 | 7 | 0.23683 | 1.6578 | 243 | 2361.5673 | 16899.2636 | #N/A | #N/A
2465 | JESSUP 11021314 | 103441102 | JESSUP 1102 | 6.0148 | 161 | 0.23664 | 38.0983 | 244 | 2367.5821 | 16861.1654 | #N/A | #N/A
4610 | KERCKHOFF 1101R353 | 252561101 | KERCKHOFF 1101 | 13.7915 | 53 | 0.23576 | 12.4952 | 245 | 2381.3736 | 16848.6702 | #N/A | #N/A
7566 | CORRAL 110112608 | 162991101 | CORRAL 1101 | 16.8621 | 187 | 0.23545 | 44.029 | 246 | 2398.2357 | 16804.6412 | #N/A | #N/A
5704 | SHEPHERD 2111707358 | 252062111 | SHEPHERD 2111 | 18.9795 | 219 | 0.23489 | 51.4409 | 247 | 2417.2152 | 16753.2003 | #N/A | #N/A
10861 | PEORIA 170492888 | 163781704 | PEORIA 1704 | 0.24898 | 4 | 0.23471 | 0.93885 | 248 | 2417.4642 | 16752.2615 | #N/A | #N/A
5055 | FROGTOWN 17028482 | 163451702 | FROGTOWN 1702 | 14.5376 | 117 | 0.23437 | 27.4214 | 249 | 2432.0018 | 16724.84 | #N/A | #N/A
10192 | MADISON 2101725408 | 63172101 | MADISON 2101 | 0.95102 | 9 | 0.23427 | 2.1085 | 250 | 2432.9528 | 16722.7316 | #N/A | #N/A
852 | PASO ROBLES 1104R56 | 182611104 | PASO ROBLES 1104 | 11.5141 | 117 | 0.2342 | 27.401 | 251 | 2444.4669 | 16695.3306 | #N/A | #N/A
9420 | FRENCH GULCH 11011892 | 103381101 | FRENCH GULCH 1101 | 3.2034 | 12 | 0.23339 | 2.8006 | 252 | 2447.6703 | 16692.53 | #N/A | #N/A
2713 | ELK CREEK 110137334 | 102781101 | ELK CREEK 1101 | 9.5668 | 70 | 0.23311 | 16.3175 | 253 | 2457.2371 | 16676.2125 | #N/A | #N/A
8722 | POSO MOUNTAIN 21033988 | 253642103 | POSO MOUNTAIN 2103 | 16.9159 | 68 | 0.23303 | 15.8463 | 254 | 2474.1531 | 16660.3662 | #N/A | #N/A
6130 | OREGON TRAIL 1104CB | 103521104 | OREGON TRAIL 1104 | 10.5844 | 164 | 0.23182 | 38.0188 | 255 | 2484.7374 | 16622.3474 | #N/A | #N/A
6781 | PALMER 1101M84 | 183031101 | PALMER 1101 | 23.4425 | 145 | 0.23169 | 33.5958 | 256 | 2508.1799 | 16588.7517 | #N/A | #N/A
7251 | PASO ROBLES 1103N58 | 182611103 | PASO ROBLES 1103 | 4.5492 | 91 | 0.23099 | 21.0205 | 257 | 2512.7291 | 16567.7312 | #N/A | #N/A
9345 | CHOLAME 21025597 | 182562102 | CHOLAME 2102 | 5.1149 | 22 | 0.23009 | 5.062 | 258 | 2517.844 | 16562.6692 | #N/A | #N/A
6582 | UPPER LAKE 1101412 | 42871101 | UPPER LAKE 1101 | 10.317 | 152 | 0.23008 | 34.9724 | 259 | 2528.161 | 16527.6968 | #N/A | #N/A
7180 | PASO ROBLES 11032731 | 182611103 | PASO ROBLES 1103 | 1.6349 | 13 | 0.2296 | 2.9847 | 260 | 2529.7959 | 16524.712 | #N/A | #N/A
6731 | DEL MAR 2109CB | 152582109 | DEL MAR 2109 | 1.4773 | 72 | 0.22956 | 16.5281 | 261 | 2531.2732 | 16508.1839 | #N/A | #N/A
4193 | ANDERSON 1103226050 | 103261103 | ANDERSON 1103 | 4.876 | 160 | 0.22913 | 36.6601 | 262 | 2536.1492 | 16471.5238 | #N/A | #N/A
2449 | COARSEGOLD 210410400 | 254432104 | COARSEGOLD 2104 | 42.6149 | 539 | 0.22826 | 123.0305 | 263 | 2578.7641 | 16348.4933 | #N/A | #N/A
6456 | HIGGINS 110950078 | 152691109 | HIGGINS 1109 | 48.4307 | 427 | 0.22791 | 97.3194 | 264 | 2627.1948 | 16251.1739 | #N/A | #N/A
6171 | WYANDOTTE 110737472 | 102911107 | WYANDOTTE 1107 | 9.2827 | 157 | 0.22739 | 35.7007 | 265 | 2636.4775 | 16215.4732 | #N/A | #N/A
1604 | COARSEGOLD 210310820 | 254432103 | COARSEGOLD 2103 | 28.8331 | 327 | 0.2269 | 74.1966 | 266 | 2665.3106 | 16141.2766 | #N/A | #N/A
3581 | JESSUP 110296554 | 103441102 | JESSUP 1102 | 8.0717 | 172 | 0.22645 | 38.9486 | 267 | 2673.3823 | 16102.328 | #N/A | #N/A
10176 | CLARK ROAD 1102CB | 103091102 | CLARK ROAD 1102 | 0.89192 | 20 | 0.22632 | 4.5263 | 268 | 2674.2742 | 16097.8016 | #N/A | #N/A
1714 | BUELLTON 1102Y50 | 183041102 | BUELLTON 1102 | 10.6284 | 147 | 0.22624 | 33.2573 | 269 | 2684.9026 | 16064.5443 | #N/A | #N/A
2661 | CLAY 11031230 | 163341103 | CLAY 1103 | 16.8239 | 136 | 0.22608 | 30.7471 | 270 | 2701.7264 | 16033.7972 | #N/A | #N/A
511 | COTTONWOOD 11029026 | 102931102 | COTTONWOOD 1102 | 12.5262 | 282 | 0.22599 | 63.7295 | 271 | 2714.2527 | 15970.0677 | #N/A | #N/A
5682 | CLOVERDALE 1102672 | 42821102 | CLOVERDALE 1102 | 21.8079 | 140 | 0.22571 | 31.5995 | 272 | 2736.0605 | 15938.4682 | #N/A | #N/A
920 | RED BLUFF 11041630 | 103541104 | RED BLUFF 1104 | 2.499 | 152 | 0.22562 | 34.2944 | 273 | 2738.5596 | 15904.1738 | #N/A | #N/A
6155 | AUBERRY 1101R2839 | 254151101 | AUBERRY 1101 | 12.8085 | 121 | 0.22501 | 27.2266 | 274 | 2751.3681 | 15876.9472 | #N/A | #N/A
252 | CLARK ROAD 11022582 | 103091102 | CLARK ROAD 1102 | 19.895 | 186 | 0.22449 | 41.7559 | 275 | 2771.2631 | 15835.1913 | #N/A | #N/A
5168 | CORNING 11021622 | 103331102 | CORNING 1102 | 33.9975 | 126 | 0.22413 | 28.2406 | 276 | 2805.2606 | 15806.9507 | #N/A | #N/A
2620 | AUBERRY 1101R2579 | 254151101 | AUBERRY 1101 | 34.9054 | 286 | 0.22394 | 64.0469 | 277 | 2840.166 | 15742.9037 | #N/A | #N/A
7109 | AUBERRY 1102R1013 | 254151102 | AUBERRY 1102 | 12.4639 | 132 | 0.22385 | 29.5483 | 278 | 2852.6299 | 15713.3555 | #N/A | #N/A
1039 | SILVERADO 2104726 | 43432104 | SILVERADO 2104 | 30.3762 | 263 | 0.22347 | 58.7725 | 279 | 2883.0061 | 15654.583 | 15654.583 | #N/A
8364 | PEORIA 1705CB | 163781705 | PEORIA 1705 | 7.0494 | 33 | 0.22294 | 7.3571 | 280 | 2890.0555 | 15647.226 | #N/A | #N/A
42 | CEDAR CREEK 11011664 | 103321101 | CEDAR CREEK 1101 | 29.572 | 244 | 0.22209 | 54.1896 | 281 | 2919.6274 | 15593.0364 | #N/A | #N/A
8613 | ZACA 1101Y72 | 182681101 | ZACA 1101 | 6.3801 | 36 | 0.2213 | 7.967 | 282 | 2926.0076 | 15585.0694 | #N/A | #N/A
5656 | PANORAMA 1102508502 | 103461102 | PANORAMA 1102 | 11.7575 | 115 | 0.22043 | 25.3491 | 283 | 2937.7651 | 15559.7203 | #N/A | #N/A
2018 | SMARTVILLE 1101CB | 153791101 | SMARTVILLE 1101 | 16.1753 | 152 | 0.21931 | 33.3354 | 284 | 2953.9404 | 15526.3848 | #N/A | #N/A
8459 | CAYETANO 21099504 | 14422109 | CAYETANO 2109 | 14.471 | 97 | 0.21922 | 21.2645 | 285 | 2968.4114 | 15505.1203 | #N/A | #N/A
3475 | SO. CAL. EDISON #3 1101CB | 258861101 | SO. CAL. EDISON #3 1101 | 8.5384 | 32 | 0.21869 | 6.998 | 286 | 2976.9499 | 15498.1224 | #N/A | #N/A
5637 | NARROWS 2101CB | 153132101 | NARROWS 2101 | 15.5673 | 65 | 0.21823 | 14.185 | 287 | 2992.5172 | 15483.9374 | #N/A | #N/A
8049 | BROWNS VALLEY 110136622 | 152921101 | BROWNS VALLEY 1101 | 5.1447 | 42 | 0.21771 | 9.1438 | 288 | 2997.6619 | 15474.7936 | #N/A | #N/A
5251 | WYANDOTTE 110313018 | 102911103 | WYANDOTTE 1103 | 0.67768 | 20 | 0.21662 | 4.3325 | 289 | 2998.3396 | 15470.4611 | #N/A | #N/A
7438 | OREGON TRAIL 1103CB | 103521103 | OREGON TRAIL 1103 | 2.7062 | 38 | 0.21644 | 8.2246 | 290 | 3001.0458 | 15462.2365 | #N/A | #N/A
9233 | PASO ROBLES 1103N52 | 182611103 | PASO ROBLES 1103 | 6.5701 | 32 | 0.21643 | 6.9258 | 291 | 3007.616 | 15455.3107 | #N/A | #N/A
5544 | TYLER 11051536 | 103571105 | TYLER 1105 | 17.7774 | 79 | 0.21608 | 17.0703 | 292 | 3025.3933 | 15438.2404 | #N/A | #N/A
8708 | PUTAH CREEK 1105665952 | 63681105 | PUTAH CREEK 1105 | 0.15126 | 13 | 0.21591 | 2.8069 | 293 | 3025.5446 | 15435.4336 | #N/A | #N/A
9580 | SUMMIT 110147786 | 152591101 | SUMMIT 1101 | 1.8121 | 13 | 0.21513 | 2.7967 | 294 | 3027.3567 | 15432.6368 | #N/A | #N/A
10253 | CLOVERDALE 1102736078 | 42821102 | CLOVERDALE 1102 | 0.23224 | 3 | 0.2146 | 0.64381 | 295 | 3027.589 | 15431.993 | #N/A | #N/A
10589 | DEL MAR 2109306972 | 152582109 | DEL MAR 2109 | 0.051859 | 2 | 0.21455 | 0.4291 | 296 | 3027.6408 | 15431.5639 | #N/A | #N/A
9314 | CALPINE 1146CB | 48011146 | CALPINE 1146 | 3.0749 | 21 | 0.21399 | 4.4937 | 297 | 3030.7157 | 15427.0702 | #N/A | #N/A
5389 | BEAR VALLEY 210511210 | 252192105 | BEAR VALLEY 2105 | 17.0869 | 139 | 0.21387 | 29.7273 | 298 | 3047.8026 | 15397.3429 | #N/A | #N/A
9003 | HARTLEY 1102385838 | 43211102 | HARTLEY 1102 | 1.2468 | 11 | 0.21349 | 2.3484 | 299 | 3049.0494 | 15394.9945 | #N/A | #N/A
4243 | CLAYTON 22122944 | 12022212 | CLAYTON 2212 | 15.0792 | 148 | 0.21331 | 31.5694 | 300 | 3064.1286 | 15363.4251 | #N/A | #N/A
3022 | DESCHUTES 11041582 | 103351104 | DESCHUTES 1104 | 6.3798 | 173 | 0.21327 | 36.8955 | 301 | 3070.5085 | 15326.5296 | #N/A | #N/A
5186 | DUNLAP 11027360 | 254061102 | DUNLAP 1102 | 8.9138 | 83 | 0.21272 | 17.6557 | 302 | 3079.4222 | 15308.8739 | #N/A | #N/A
7188 | UPPER LAKE 1101472084 | 42871101 | UPPER LAKE 1101 | 4.6331 | 66 | 0.21229 | 14.0108 | 303 | 3084.0554 | 15294.863 | #N/A | #N/A
1958 | CURTIS 170411290 | 163351704 | CURTIS 1704 | 7.8695 | 75 | 0.21224 | 15.9178 | 304 | 3091.9249 | 15278.9452 | #N/A | #N/A
10301 | SCE VEGAS 1701CB | 188881701 | SCE VEGAS 1701 | 0.10467 | 1 | 0.2122 | 0.2122 | 305 | 3092.0295 | 15278.733 | #N/A | #N/A
4384 | AUBERRY 110237466 | 254151102 | AUBERRY 1102 | 31.3612 | 345 | 0.21127 | 72.8874 | 306 | 3123.3908 | 15205.8456 | #N/A | #N/A
2676 | BUELLTON 1102CB | 183041102 | BUELLTON 1102 | 7.0863 | 148 | 0.21085 | 31.2055 | 307 | 3130.4771 | 15174.6401 | #N/A | #N/A
5276 | SANTA YNEZ 110477098 | 182721104 | SANTA YNEZ 1104 | 11.9643 | 112 | 0.21042 | 23.5673 | 308 | 3142.4414 | 15151.0728 | 15151.0728 | #N/A
7565 | SILVERADO 2104806 | 43432104 | SILVERADO 2104 | 21.0265 | 229 | 0.21008 | 48.1076 | 309 | 3163.4679 | 15102.9653 | #N/A | #N/A
1159 | LONE TREE 210521210 | 13232105 | LONE TREE 2105 | 12.8566 | 111 | 0.20896 | 23.1943 | 310 | 3176.3245 | 15079.7709 | #N/A | #N/A
1515 | WYANDOTTE 110979932 | 102911109 | WYANDOTTE 1109 | 22.0664 | 345 | 0.20828 | 71.8562 | 311 | 3198.3909 | 15007.9148 | #N/A | #N/A
4727 | REDBUD 1101454 | 43191101 | REDBUD 1101 | 5.5371 | 54 | 0.20738 | 11.1984 | 312 | 3203.928 | 14996.7164 | #N/A | #N/A
2411 | MARIPOSA 210190180 | 254452101 | MARIPOSA 2101 | 4.9571 | 49 | 0.20688 | 10.1373 | 313 | 3208.8851 | 14986.5791 | #N/A | #N/A
6630 | MIDDLETOWN 1101644756 | 43141101 | MIDDLETOWN 1101 | 17.325 | 163 | 0.20636 | 33.6372 | 314 | 3226.2101 | 14952.9419 | #N/A | #N/A
8301 | ELK CREEK 11012002 | 102781101 | ELK CREEK 1101 | 21.7811 | 109 | 0.20473 | 22.3155 | 315 | 3247.9912 | 14930.6264 | #N/A | #N/A
1537 | BELL 11072400 | 152701107 | BELL 1107 | 25.7395 | 320 | 0.20423 | 65.3543 | 316 | 3273.7307 | 14865.2721 | #N/A | #N/A
2016 | PETALUMA C 1108296 | 42631108 | PETALUMA C 1108 | 14.7695 | 123 | 0.20401 | 25.0928 | 317 | 3288.5001 | 14840.1792 | #N/A | #N/A
1327 | DESCHUTES 1104CB | 103351104 | DESCHUTES 1104 | 13.5086 | 273 | 0.20316 | 55.4629 | 318 | 3302.0088 | 14784.7163 | #N/A | #N/A
10175 | JESSUP 1102936897 | 103441102 | JESSUP 1102 | 0.41364 | 12 | 0.20267 | 2.432 | 319 | 3302.4224 | 14782.2843 | #N/A | #N/A
2512 | CLAY 110334338 | 163341103 | CLAY 1103 | 9.7742 | 66 | 0.2022 | 13.3455 | 320 | 3312.1966 | 14768.9388 | #N/A | #N/A
3530 | AUBERRY 1102R2850 | 254151102 | AUBERRY 1102 | 26.3694 | 222 | 0.20166 | 44.7693 | 321 | 3338.566 | 14724.1695 | #N/A | #N/A
4238 | NORTH BRANCH 1101CB | 163231101 | NORTH BRANCH 1101 | 15.7926 | 114 | 0.20132 | 22.9503 | 322 | 3354.3586 | 14701.2192 | #N/A | #N/A
11083 | NARROWS 2104CB | 153132104 | NARROWS 2104 | 0.0028415 | 1 | 0.20132 | 0.20132 | 323 | 3354.3615 | 14701.0179 | #N/A | #N/A
389 | VASCO 1102MR176 | 13751102 | VASCO 1102 | 38.828 | 256 | 0.20121 | 51.5086 | 324 | 3393.1894 | 14649.5093 | #N/A | #N/A
7455 | SAN MIGUEL 1104514987 | 182661104 | SAN MIGUEL 1104 | 8.3156 | 63 | 0.20048 | 12.6303 | 325 | 3401.505 | 14636.879 | #N/A | #N/A
7507 | NORTH BRANCH 110111158 | 163231101 | NORTH BRANCH 1101 | 12.7408 | 229 | 0.20008 | 45.8175 | 326 | 3414.2458 | 14591.0614 | #N/A | #N/A
3193 | AUBERRY 1101R314 | 254151101 | AUBERRY 1101 | 42.4149 | 390 | 0.20004 | 78.017 | 327 | 3456.6606 | 14513.0444 | #N/A | #N/A
1293 | MIDDLETOWN 11014646 | 43141101 | MIDDLETOWN 1101 | 18.5633 | 165 | 0.19983 | 32.9712 | 328 | 3475.2239 | 14480.0732 | 14480.0732 | #N/A
9642 | LUCERNE 11034200 | 43351103 | LUCERNE 1103 | 4.0371 | 37 | 0.19927 | 7.3729 | 329 | 3479.261 | 14472.7003 | #N/A | #N/A
7729 | AUBERRY 110149122 | 254151101 | AUBERRY 1101 | 3.9629 | 40 | 0.19907 | 7.9627 | 330 | 3483.224 | 14464.7376 | #N/A | #N/A
464 | WOODACRE 110196844 | 43021101 | WOODACRE 1101 | 5.9393 | 63 | 0.19881 | 12.5249 | 331 | 3489.1633 | 14452.2127 | #N/A | #N/A
4726 | SHINGLE SPRINGS 210985766 | 153652109 | SHINGLE SPRINGS 2109 | 18.4877 | 166 | 0.19865 | 32.9759 | 332 | 3507.651 | 14419.2368 | #N/A | #N/A
9424 | VINEYARD 2110391250 | 14502110 | VINEYARD 2110 | 0.92065 | 3 | 0.19841 | 0.59524 | 333 | 3508.5716 | 14418.6416 | #N/A | #N/A
308 | CALPINE 1144CB | 48011144 | CALPINE 1144 | 26.271 | 131 | 0.19817 | 25.9607 | 334 | 3534.8426 | 14392.6809 | #N/A | #N/A
7335 | UPPER LAKE 11011276 | 42871101 | UPPER LAKE 1101 | 12.9316 | 116 | 0.19794 | 22.9608 | 335 | 3547.7742 | 14369.7201 | #N/A | #N/A
3179 | CHOLAME 2102796386 | 182562102 | CHOLAME 2102 | 35.6693 | 159 | 0.19792 | 31.4686 | 336 | 3583.4435 | 14338.2515 | #N/A | #N/A
9031 | SAND CREEK 1103CB | 254601103 | SAND CREEK 1103 | 13.0411 | 77 | 0.19768 | 15.2216 | 337 | 3596.4847 | 14323.0299 | #N/A | #N/A
6545 | TULUCAY 1101628 | 42301101 | TULUCAY 1101 | 4.1726 | 98 | 0.19686 | 19.2923 | 338 | 3600.6572 | 14303.7376 | #N/A | 14303.7376
4963 | BEAR VALLEY 210190550 | 252192101 | BEAR VALLEY 2101 | 8.0244 | 47 | 0.19624 | 9.2235 | 339 | 3608.6816 | 14294.5141 | #N/A | #N/A
8575 | ELK CREEK 11012106 | 102781101 | ELK CREEK 1101 | 13.2402 | 67 | 0.1961 | 13.1388 | 340 | 3621.9218 | 14281.3753 | 14281.3753 | #N/A
3500 | DUNLAP 11037040 | 254061103 | DUNLAP 1103 | 24.7794 | 230 | 0.19605 | 45.0921 | 341 | 3646.7012 | 14236.2832 | #N/A | #N/A
2568 | LAYTONVILLE 1102500 | 42681102 | LAYTONVILLE 1102 | 21.3647 | 214 | 0.19576 | 41.8921 | 342 | 3668.0659 | 14194.3911 | #N/A | #N/A
2190 | DIAMOND SPRINGS 110519910 | 152261105 | DIAMOND SPRINGS 1105 | 20.699 | 226 | 0.19568 | 44.2238 | 343 | 3688.7649 | 14150.1673 | #N/A | #N/A
9927 | FITCH MOUNTAIN 1111555644 | 42751111 | FITCH MOUNTAIN 1111 | 0.16699 | 19 | 0.19539 | 3.7125 | 344 | 3688.9319 | 14146.4548 | #N/A | #N/A
41 | REDBUD 1101708166 | 43191101 | REDBUD 1101 | 11.5048 | 162 | 0.19539 | 31.6535 | 345 | 3700.4367 | 14114.8013 | #N/A | #N/A
8428 | CALPELLA 11013419 | 43411101 | CALPELLA 1101 | 7.9853 | 38 | 0.19531 | 7.4218 | 346 | 3708.4219 | 14107.3795 | #N/A | #N/A
4645 | OLETA 110241396 | 163541102 | OLETA 1102 | 6.7546 | 75 | 0.19503 | 14.6272 | 347 | 3715.1765 | 14092.7523 | #N/A | #N/A
1354 | CORRAL 1102CB | 162991102 | CORRAL 1102 | 16.8855 | 236 | 0.19501 | 46.0213 | 348 | 3732.0621 | 14046.731 | #N/A | #N/A
6647 | TIVY VALLEY 1107584840 | 252941107 | TIVY VALLEY 1107 | 45.0784 | 449 | 0.19446 | 87.311 | 349 | 3777.1404 | 13959.42 | #N/A | #N/A
4112 | JESSUP 110141356 | 103441101 | JESSUP 1101 | 32.4662 | 318 | 0.19445 | 61.8351 | 350 | 3809.6067 | 13897.5849 | #N/A | #N/A
1219 | APPLE HILL 21021532 | 153662102 | APPLE HILL 2102 | 38.9629 | 465 | 0.19412 | 90.2637 | 351 | 3848.5696 | 13807.3212 | #N/A | #N/A
4008 | OLETA 11011208 | 163541101 | OLETA 1101 | 33.0009 | 334 | 0.19404 | 64.811 | 352 | 3881.5705 | 13742.5102 | #N/A | #N/A
9763 | WISHON 1101CB | 251511101 | WISHON 1101 | 7.6405 | 36 | 0.19398 | 6.9834 | 353 | 3889.211 | 13735.5268 | #N/A | #N/A
4721 | COPPERMINE 1104613086 | 252411104 | COPPERMINE 1104 | 5.1231 | 63 | 0.19391 | 12.2166 | 354 | 3894.3341 | 13723.3102 | #N/A | #N/A
8166 | BANGOR 1101CB | 103191101 | BANGOR 1101 | 18.7561 | 171 | 0.19378 | 33.1366 | 355 | 3913.0902 | 13690.1736 | 13690.1736 | #N/A
10364 | MADISON 2101745850 | 63172101 | MADISON 2101 | 0.47947 | 7 | 0.19369 | 1.3558 | 356 | 3913.5697 | 13688.8178 | #N/A | #N/A
10620 | OLETA 1102793776 | 163541102 | OLETA 1102 | 1.2163 | 6 | 0.19328 | 1.1597 | 357 | 3914.7859 | 13687.6581 | #N/A | #N/A
1881 | PENRYN 1103604 | 152561103 | PENRYN 1103 | 26.4244 | 240 | 0.19315 | 46.357 | 358 | 3941.2103 | 13641.301 | #N/A | #N/A
10174 | LAS GALLINAS A 1105532 | 42991105 | LAS GALLINAS A 1105 | 4.4122 | 34 | 0.19264 | 6.5497 | 359 | 3945.6225 | 13634.7514 | #N/A | #N/A
9563 | ELK CREEK 11012032 | 102781101 | ELK CREEK 1101 | 8.7618 | 52 | 0.19237 | 10.0031 | 360 | 3954.3843 | 13624.7483 | #N/A | #N/A
7617 | WYANDOTTE 110213044 | 102911102 | WYANDOTTE 1102 | 4.7699 | 51 | 0.19229 | 9.8065 | 361 | 3959.1542 | 13614.9417 | #N/A | #N/A
3855 | SAND CREEK 11037140 | 254601103 | SAND CREEK 1103 | 26.29 | 296 | 0.19202 | 56.8394 | 362 | 3985.4442 | 13558.1024 | #N/A | #N/A
5056 | BANGOR 110182350 | 103191101 | BANGOR 1101 | 19.6266 | 230 | 0.19196 | 44.1515 | 363 | 4005.0708 | 13513.9509 | #N/A | #N/A
523 | DUNLAP 11037220 | 254061103 | DUNLAP 1103 | 24.8305 | 188 | 0.19171 | 36.0414 | 364 | 4029.9013 | 13477.9095 | #N/A | #N/A
8426 | FORT ROSS 1121CB | 42851121 | FORT ROSS 1121 | 0.016118 | 1 | 0.19152 | 0.19152 | 365 | 4029.9174 | 13477.7179 | #N/A | #N/A
8629 | FOOTHILL 1101645910 | 182951101 | FOOTHILL 1101 | 0.48143 | 14 | 0.19134 | 2.6788 | 366 | 4030.3989 | 13475.0391 | #N/A | #N/A
7469 | PALMER 110198478 | 183031101 | PALMER 1101 | 6.0154 | 34 | 0.19124 | 6.5022 | 367 | 4036.4142 | 13468.5369 | #N/A | #N/A
5366 | WYANDOTTE 11095607 | 102911109 | WYANDOTTE 1109 | 4.5158 | 71 | 0.19115 | 13.5714 | 368 | 4040.93 | 13454.9654 | #N/A | #N/A
9473 | HARTLEY 1102524 | 43211102 | HARTLEY 1102 | 0.24826 | 31 | 0.19015 | 5.8946 | 369 | 4041.1783 | 13449.0708 | #N/A | #N/A
6494 | WISE 1102697216 | 152271102 | WISE 1102 | 13.2842 | 145 | 0.18992 | 27.5378 | 370 | 4054.4625 | 13421.533 | #N/A | #N/A
4257 | REDBUD 1102CB | 43191102 | REDBUD 1102 | 17.4931 | 170 | 0.18973 | 32.2538 | 371 | 4071.9556 | 13389.2792 | #N/A | #N/A
9558 | BRENTWOOD 21056512 | 14592105 | BRENTWOOD 2105 | 0.65121 | 5 | 0.18909 | 0.94545 | 372 | 4072.6068 | 13388.3338 | #N/A | #N/A
10458 | DEL MAR 2109805882 | 152582109 | DEL MAR 2109 | 0.29665 | 6 | 0.18904 | 1.1343 | 373 | 4072.9035 | 13387.1995 | #N/A | #N/A
2068 | OLETA 11021228 | 163541102 | OLETA 1102 | 10.8452 | 368 | 0.18877 | 69.4681 | 374 | 4083.7487 | 13317.7315 | #N/A | #N/A
2280 | DESCHUTES 11011580 | 103351101 | DESCHUTES 1101 | 47.4617 | 383 | 0.18779 | 71.9249 | 375 | 4131.2104 | 13245.8065 | #N/A | #N/A
6271 | COTTONWOOD 110131500 | 102931101 | COTTONWOOD 1101 | 4.6622 | 111 | 0.18759 | 20.823 | 376 | 4135.8726 | 13224.9836 | #N/A | #N/A
449 | CLAYTON 221296224 | 12022212 | CLAYTON 2212 | 19.3992 | 174 | 0.18755 | 32.6329 | 377 | 4155.2718 | 13192.3507 | 13192.3507 | #N/A
9225 | BUCKS CREEK 1102CB | 102211102 | BUCKS CREEK 1102 | 29.5832 | 121 | 0.1873 | 22.6633 | 378 | 4184.8549 | 13169.6874 | #N/A | #N/A
4556 | MARIPOSA 210237288 | 254452102 | MARIPOSA 2102 | 85.2905 | 678 | 0.18718 | 126.9051 | 379 | 4270.1454 | 13042.7824 | #N/A | #N/A
9851 | PANORAMA 1101885215 | 103461101 | PANORAMA 1101 | 2.0047 | 23 | 0.18705 | 4.3021 | 380 | 4272.1501 | 13038.4803 | #N/A | #N/A
1129 | PETALUMA C 1109128 | 42631109 | PETALUMA C 1109 | 34.9319 | 269 | 0.18687 | 50.2671 | 381 | 4307.082 | 12988.2132 | #N/A | #N/A
5974 | DOBBINS 110169722 | 153741101 | DOBBINS 1101 | 6.6336 | 68 | 0.18675 | 12.6993 | 382 | 4313.7155 | 12975.5139 | #N/A | #N/A
6088 | TYLER 110585132 | 103571105 | TYLER 1105 | 31.133 | 217 | 0.18633 | 40.4342 | 383 | 4344.8486 | 12935.0798 | #N/A | #N/A
6487 | STILLWATER 110248952 | 103561102 | STILLWATER 1102 | 10.597 | 123 | 0.18561 | 22.8305 | 384 | 4355.4456 | 12912.2492 | #N/A | #N/A
7029 | PENRYN 1106212772 | 152561106 | PENRYN 1106 | 1.0001 | 11 | 0.18554 | 2.041 | 385 | 4356.4457 | 12910.2083 | #N/A | #N/A
7958 | GEYSERVILLE 110179788 | 42891101 | GEYSERVILLE 1101 | 39.5659 | 157 | 0.18551 | 29.1256 | 386 | 4396.0116 | 12881.0826 | #N/A | #N/A
2772 | WYANDOTTE 110913052 | 102911109 | WYANDOTTE 1109 | 19.5651 | 213 | 0.18514 | 39.4358 | 387 | 4415.5767 | 12841.6469 | #N/A | #N/A
9699 | LOGAN CREEK 2102795010 | 103142102 | LOGAN CREEK 2102 | 3.7072 | 12 | 0.18505 | 2.2206 | 388 | 4419.2839 | 12839.4263 | #N/A | #N/A
2290 | JESSUP 11021550 | 103441102 | JESSUP 1102 | 19.2725 | 237 | 0.18396 | 43.5983 | 389 | 4438.5564 | 12795.828 | #N/A | #N/A
881 | RED BLUFF 11011556 | 103541101 | RED BLUFF 1101 | 38.4898 | 411 | 0.18357 | 75.4478 | 390 | 4477.0462 | 12720.3803 | #N/A | #N/A
11061 | SAN LUIS OBISPO 1103365572 | 182631103 | SAN LUIS OBISPO 1103 | 0.38027 | 2 | 0.18299 | 0.36597 | 391 | 4477.4265 | 12720.0143 | #N/A | #N/A
6935 | CEDAR CREEK 1101CB | 103321101 | CEDAR CREEK 1101 | 15.4219 | 127 | 0.18254 | 23.1832 | 392 | 4492.8484 | 12696.8311 | #N/A | #N/A
3564 | JAMESON 1105466348 | 63801105 | JAMESON 1105 | 16.1835 | 294 | 0.18223 | 53.5743 | 393 | 4509.0319 | 12643.2568 | #N/A | #N/A
2550 | COTTONWOOD 110335470 | 102931103 | COTTONWOOD 1103 | 20.5787 | 174 | 0.18214 | 31.6926 | 394 | 4529.6106 | 12611.5642 | #N/A | #N/A
2265 | BELL 1108CB | 152701108 | BELL 1108 | 0 | 83 | 0.18213 | 15.1167 | 395 | 4529.6106 | 12596.4475 | #N/A | #N/A
6694 | POTTER VALLEY P H 110537476 | 42281105 | POTTER VALLEY P H 1105 | 2.63 | 82 | 0.18107 | 14.8479 | 396 | 4532.2406 | 12581.5996 | #N/A | #N/A
2442 | CORRAL 110112612 | 162991101 | CORRAL 1101 | 19.3235 | 195 | 0.18095 | 35.2855 | 397 | 4551.564 | 12546.3141 | #N/A | #N/A
2325 | COTTONWOOD 11011510 | 102931101 | COTTONWOOD 1101 | 0.38123 | 35 | 0.18088 | 6.3309 | 398 | 4551.9453 | 12539.9832 | #N/A | #N/A
6987 | TEMPLETON 2113641367 | 183052113 | TEMPLETON 2113 | 39.7012 | 278 | 0.18079 | 50.2607 | 399 | 4591.6465 | 12489.7225 | #N/A | #N/A
1077 | CLAYTON 2212Y504R | 12022212 | CLAYTON 2212 | 11.708 | 112 | 0.18021 | 20.1836 | 400 | 4603.3546 | 12469.5389 | #N/A | #N/A
6538 | DUNLAP 11027060 | 254061102 | DUNLAP 1102 | 17.8746 | 162 | 0.18019 | 29.1914 | 401 | 4621.2291 | 12440.3474 | #N/A | #N/A
8223 | POSO MOUNTAIN 210448268 | 253642104 | POSO MOUNTAIN 2104 | 5.0668 | 30 | 0.17977 | 5.3932 | 402 | 4626.296 | 12434.9542 | #N/A | #N/A
7847 | OILFIELDS 11032757 | 182391103 | OILFIELDS 1103 | 2.6245 | 16 | 0.1791 | 2.8656 | 403 | 4628.9205 | 12432.0886 | #N/A | #N/A
1905 | TIVY VALLEY 1107R1817 | 252941107 | TIVY VALLEY 1107 | 19.2848 | 145 | 0.17888 | 25.9373 | 404 | 4648.2053 | 12406.1513 | #N/A | #N/A
3840 | SAND CREEK 11037070 | 254601103 | SAND CREEK 1103 | 17.5579 | 103 | 0.17873 | 18.4097 | 405 | 4665.7632 | 12387.7417 | #N/A | #N/A
1011 | CALISTOGA 1101890 | 42711101 | CALISTOGA 1101 | 24.3702 | 203 | 0.17857 | 36.2505 | 406 | 4690.1334 | 12351.4912 | #N/A | #N/A
1851 | KONOCTI 1102CB | 43311102 | KONOCTI 1102 | 3.9318 | 97 | 0.1779 | 17.2565 | 407 | 4694.0653 | 12334.2347 | #N/A | #N/A
7708 | COLUMBIA HILL 110190730 | 152471101 | COLUMBIA HILL 1101 | 8.33 | 77 | 0.17712 | 13.6383 | 408 | 4702.3952 | 12320.5964 | #N/A | #N/A
10514 | SCE TEHACHAPI 1101CB | 258131101 | SCE TEHACHAPI 1101 | 1.1573 | 2 | 0.17665 | 0.3533 | 409 | 4703.5526 | 12320.2431 | #N/A | #N/A
5375 | TASSAJARA 2109CB | 14662109 | TASSAJARA 2109 | 1.9336 | 12 | 0.17607 | 2.1128 | 410 | 4705.4862 | 12318.1303 | #N/A | #N/A
8181 | APPLE HILL 210289934 | 153662102 | APPLE HILL 2102 | 5.5425 | 56 | 0.17581 | 9.8455 | 411 | 4711.0287 | 12308.2848 | #N/A | #N/A
3827 | HIGGINS 1109594 | 152691109 | HIGGINS 1109 | 14.3437 | 155 | 0.17563 | 27.2219 | 412 | 4725.3724 | 12281.0628 | #N/A | #N/A
329 | CORNING 110253184 | 103331102 | CORNING 1102 | 31.8239 | 123 | 0.17544 | 21.5791 | 413 | 4757.1963 | 12259.4838 | 12259.4838 | #N/A
6969 | PETALUMA C 1108208 | 42631108 | PETALUMA C 1108 | 12.4785 | 95 | 0.1754 | 16.663 | 414 | 4769.6748 | 12242.8208 | #N/A | #N/A
8229 | GARBERVILLE 11012026 | 192221101 | GARBERVILLE 1101 | 6.352 | 26 | 0.17512 | 4.5532 | 415 | 4776.0269 | 12238.2677 | #N/A | #N/A
8173 | ZACA 1101CB | 182681101 | ZACA 1101 | 7.4782 | 60 | 0.17499 | 10.4995 | 416 | 4783.5051 | 12227.7682 | #N/A | #N/A
5131 | PHILO 11013700 | 42601101 | PHILO 1101 | 18.1206 | 116 | 0.17472 | 20.2673 | 417 | 4801.6257 | 12207.5009 | #N/A | #N/A
908 | PUTAH CREEK 1102710384 | 63681102 | PUTAH CREEK 1102 | 5.3351 | 84 | 0.17469 | 14.6739 | 418 | 4806.9608 | 12192.827 | 12192.827 | #N/A
9983 | JAMESON 1105913400 | 63801105 | JAMESON 1105 | 0.10712 | 14 | 0.17457 | 2.444 | 419 | 4807.0679 | 12190.383 | #N/A | #N/A
6899 | FORT SEWARD 11211690 | 192321121 | FORT SEWARD 1121 | 10.8003 | 77 | 0.17449 | 13.4358 | 420 | 4817.8683 | 12176.9472 | #N/A | #N/A
2810 | OAKHURST 110110090 | 254421101 | OAKHURST 1101 | 44.0886 | 435 | 0.17437 | 75.8506 | 421 | 4861.9569 | 12101.0967 | 12101.0967 | #N/A
8488 | BROWNS VALLEY 1101CB | 152921101 | BROWNS VALLEY 1101 | 2.2619 | 17 | 0.1743 | 2.9631 | 422 | 4864.2187 | 12098.1336 | #N/A | #N/A
1886 | REDBUD 1101323962 | 43191101 | REDBUD 1101 | 20.5821 | 282 | 0.17389 | 49.0357 | 423 | 4884.8008 | 12049.0979 | #N/A | #N/A
7655 | SHINGLE SPRINGS 210851476 | 153652108 | SHINGLE SPRINGS 2108 | 4.9262 | 74 | 0.1736 | 12.8462 | 424 | 4889.727 | 12036.2517 | #N/A | #N/A
6143 | OILFIELDS 1103N64 | 182391103 | OILFIELDS 1103 | 11.0139 | 101 | 0.17314 | 17.4874 | 425 | 4900.7409 | 12018.7643 | #N/A | #N/A
3312 | OLETA 11011217 | 163541101 | OLETA 1101 | 14.1973 | 116 | 0.17295 | 20.0623 | 426 | 4914.9382 | 11998.7021 | #N/A | #N/A
10420 | SANTA YNEZ 1101673618 | 182721101 | SANTA YNEZ 1101 | 0.10651 | 4 | 0.17294 | 0.69175 | 427 | 4915.0447 | 11998.0103 | #N/A | #N/A
50 | MARIPOSA 210135244 | 254452101 | MARIPOSA 2101 | 17.4635 | 146 | 0.17286 | 25.237 | 428 | 4932.5082 | 11972.7733 | 11972.7733 | #N/A
6824 | MARIPOSA 21021960 | 254452102 | MARIPOSA 2102 | 24.6717 | 223 | 0.17242 | 38.4488 | 429 | 4957.1798 | 11934.3245 | #N/A | #N/A
7293 | WISE 11022234 | 152271102 | WISE 1102 | 15.1336 | 179 | 0.17198 | 30.784 | 430 | 4972.3135 | 11903.5405 | #N/A | #N/A
6103 | CALPELLA 1102421412 | 43411102 | CALPELLA 1102 | 1.0045 | 38 | 0.17127 | 6.5083 | 431 | 4973.318 | 11897.0323 | #N/A | #N/A
8262 | DESCHUTES 11019722 | 103351101 | DESCHUTES 1101 | 3.1941 | 55 | 0.17084 | 9.3959 | 432 | 4976.5121 | 11887.6363 | #N/A | #N/A
3350 | OAKHURST 110310570 | 254421103 | OAKHURST 1103 | 9.5965 | 92 | 0.17053 | 15.6885 | 433 | 4986.1086 | 11871.9478 | #N/A | #N/A
7252 | OILFIELDS 1103N42 | 182391103 | OILFIELDS 1103 | 3.7274 | 30 | 0.17017 | 5.105 | 434 | 4989.836 | 11866.8428 | #N/A | #N/A
2738 | SAN BENITO 2101221165 | 182742101 | SAN BENITO 2101 | 4.3859 | 39 | 0.17016 | 6.6364 | 435 | 4994.2219 | 11860.2064 | #N/A | #N/A
10162 | MADISON 210113372 | 63172101 | MADISON 2101 | 3.8236 | 5 | 0.17014 | 0.85069 | 436 | 4998.0455 | 11859.3557 | #N/A | #N/A
4788 | COTTONWOOD 11039072 | 102931103 | COTTONWOOD 1103 | 28.8029 | 279 | 0.1698 | 47.3736 | 437 | 5026.8484 | 11811.9821 | #N/A | #N/A
10660 | CLAYTON 2212334476 | 12022212 | CLAYTON 2212 | 0.0559 | 2 | 0.16961 | 0.33922 | 438 | 5026.9043 | 11811.6428 | #N/A | #N/A
5708 | HARTLEY 1101658 | 43211101 | HARTLEY 1101 | 2.8348 | 136 | 0.16943 | 23.042 | 439 | 5029.7391 | 11788.6009 | #N/A | #N/A
52 | HIGHLANDS 1103520 | 43361103 | HIGHLANDS 1103 | 46.6894 | 437 | 0.16915 | 73.9165 | 440 | 5076.4285 | 11714.6843 | #N/A | #N/A
5485 | ZACA 1102CB | 182681102 | ZACA 1102 | 15.6783 | 190 | 0.16908 | 32.1248 | 441 | 5092.1067 | 11682.5595 | #N/A | #N/A
2709 | CHOLAME 2102X10 | 182562102 | CHOLAME 2102 | 21.4267 | 156 | 0.16893 | 26.3532 | 442 | 5113.5335 | 11656.2063 | #N/A | #N/A
2509 | HIGGINS 111051794 | 152691110 | HIGGINS 1110 | 3.9179 | 32 | 0.16883 | 5.4026 | 443 | 5117.4513 | 11650.8036 | #N/A | #N/A
3144 | MORGAN HILL 2105XR564 | 83242105 | MORGAN HILL 2105 | 5.6724 | 81 | 0.16792 | 13.6018 | 444 | 5123.1237 | 11637.2018 | #N/A | #N/A
8832 | PEORIA 17046090 | 163781704 | PEORIA 1704 | 0.54664 | 10 | 0.16726 | 1.6726 | 445 | 5123.6703 | 11635.5292 | #N/A | #N/A
6712 | CORNING 110182846 | 103331101 | CORNING 1101 | 4.7401 | 61 | 0.16626 | 10.1421 | 446 | 5128.4104 | 11625.3871 | #N/A | #N/A
3069 | NARROWS 21052228 | 153132105 | NARROWS 2105 | 20.9616 | 199 | 0.16595 | 33.0243 | 447 | 5149.372 | 11592.3628 | #N/A | #N/A
10116 | SANTA YNEZ 1104117616 | 182721104 | SANTA YNEZ 1104 | 0.18542 | 5 | 0.16564 | 0.82819 | 448 | 5149.5574 | 11591.5346 | #N/A | #N/A
10070 | SILVERADO 2102772792 | 43432102 | SILVERADO 2102 | 2.3506 | 19 | 0.16509 | 3.1366 | 449 | 5151.908 | 11588.398 | #N/A | #N/A
6113 | MIDDLETOWN 1101439572 | 43141101 | MIDDLETOWN 1101 | 1.229 | 18 | 0.16479 | 2.9663 | 450 | 5153.1369 | 11585.4317 | #N/A | #N/A
1940 | NORTH BRANCH 1101TS1115 | 163231101 | NORTH BRANCH 1101 | 17.6137 | 147 | 0.16462 | 24.1996 | 451 | 5170.7507 | 11561.2321 | #N/A | #N/A
7043 | ANDERSON 1101514412 | 103261101 | ANDERSON 1101 | 1.0314 | 5 | 0.16405 | 0.82024 | 452 | 5171.7821 | 11560.4118 | #N/A | #N/A
7318 | PUEBLO 2102226562 | 43292102 | PUEBLO 2102 | 0.8527 | 7 | 0.16403 | 1.1482 | 453 | 5172.6348 | 11559.2636 | #N/A | #N/A
9693 | WILDWOOD 110198896 | 103611101 | WILDWOOD 1101 | 5.0283 | 25 | 0.16402 | 4.1004 | 454 | 5177.6631 | 11555.1632 | #N/A | #N/A
8907 | SHINGLE SPRINGS 1103CB | 153651103 | SHINGLE SPRINGS 1103 | 6.6178 | 143 | 0.16378 | 23.42 | 455 | 5184.2809 | 11531.7432 | #N/A | #N/A
3737 | KESWICK 110148480 | 103451101 | KESWICK 1101 | 10.5208 | 125 | 0.16355 | 20.4433 | 456 | 5194.8017 | 11511.2999 | #N/A | #N/A
9178 | CORNING 1102915324 | 103331102 | CORNING 1102 | 2.228 | 27 | 0.16319 | 4.406 | 457 | 5197.0297 | 11506.8939 | #N/A | #N/A
9985 | BOLINAS 1101530 | 42261101 | BOLINAS 1101 | 10.9659 | 23 | 0.16273 | 3.7427 | 458 | 5207.9956 | 11503.1512 | #N/A | #N/A
10086 | NAPA 1102561208 | 42021102 | NAPA 1102 | 0.8375 | 15 | 0.1626 | 2.439 | 459 | 5208.8331 | 11500.7122 | #N/A | #N/A
7995 | HOPLAND 110194006 | 42251101 | HOPLAND 1101 | 13.8855 | 112 | 0.1626 | 18.2107 | 460 | 5222.7186 | 11482.5015 | #N/A | #N/A
5192 | HIGHLANDS 1103CB | 43361103 | HIGHLANDS 1103 | 10.5955 | 144 | 0.16238 | 23.3827 | 461 | 5233.3141 | 11459.1188 | #N/A | #N/A
10927 | SCE REFUGIO 1701CB | 188071701 | SCE REFUGIO 1701 | 0.0022454 | 1 | 0.16185 | 0.16185 | 462 | 5233.3164 | 11458.957 | #N/A | #N/A
1961 | NARROWS 210534069 | 153132105 | NARROWS 2105 | 15.7438 | 156 | 0.16138 | 25.1758 | 463 | 5249.0602 | 11433.7812 | #N/A | #N/A
11018 | CLAY 110398680 | 163341103 | CLAY 1103 | 0.02896 | 1 | 0.16135 | 0.16135 | 464 | 5249.0892 | 11433.6198 | #N/A | #N/A
5283 | ANDERSON 11011752 | 103261101 | ANDERSON 1101 | 8.4222 | 96 | 0.16096 | 15.4521 | 465 | 5257.5114 | 11418.1677 | #N/A | #N/A
4672 | LOW GAP 110137498 | 192411101 | LOW GAP 1101 | 16.282 | 129 | 0.16073 | 20.7336 | 466 | 5273.7934 | 11397.4341 | #N/A | #N/A
1841 | NARROWS 21057203 | 153132105 | NARROWS 2105 | 18.5859 | 197 | 0.16043 | 31.6051 | 467 | 5292.3793 | 11365.8291 | #N/A | #N/A
652 | MIDDLETOWN 110148212 | 43141101 | MIDDLETOWN 1101 | 10.6994 | 110 | 0.1603 | 17.6327 | 468 | 5303.0787 | 11348.1963 | 11348.1963 | #N/A
1128 | SAN MIGUEL 1106605393 | 182661106 | SAN MIGUEL 1106 | 20.7432 | 119 | 0.15998 | 19.0373 | 469 | 5323.8219 | 11329.1591 | #N/A | #N/A
3473 | COTTONWOOD 11011610 | 102931101 | COTTONWOOD 1101 | 38.4226 | 295 | 0.15996 | 47.1875 | 470 | 5362.2445 | 11281.9716 | #N/A | #N/A
1571 | SAN MIGUEL 1106428314 | 182661106 | SAN MIGUEL 1106 | 14.7129 | 73 | 0.15993 | 11.675 | 471 | 5376.9574 | 11270.2966 | #N/A | #N/A
6359 | FROGTOWN 1702592404 | 163451702 | FROGTOWN 1702 | 1.6422 | 20 | 0.15963 | 3.1926 | 472 | 5378.5996 | 11267.104 | #N/A | #N/A
7337 | WYANDOTTE 110738438 | 102911107 | WYANDOTTE 1107 | 16.8604 | 181 | 0.15947 | 28.8637 | 473 | 5395.46 | 11238.2402 | #N/A | #N/A
932 | MIDDLETOWN 1101548 | 43141101 | MIDDLETOWN 1101 | 27.4082 | 298 | 0.15935 | 47.4878 | 474 | 5422.8682 | 11190.7525 | 11190.7525 | #N/A
9379 | SUNOL 11018721 | 14241101 | SUNOL 1101 | 2.7351 | 29 | 0.1593 | 4.6198 | 475 | 5425.6033 | 11186.1327 | #N/A | #N/A
1763 | RED BLUFF 110451238 | 103541104 | RED BLUFF 1104 | 39.2404 | 335 | 0.15926 | 53.3509 | 476 | 5464.8437 | 11132.7818 | #N/A | #N/A
1814 | CLOVERDALE 110184088 | 42821101 | CLOVERDALE 1101 | 16.1366 | 127 | 0.15858 | 20.1391 | 477 | 5480.9803 | 11112.6427 | #N/A | #N/A
4306 | RAWSON 1103428534 | 103531103 | RAWSON 1103 | 4.5381 | 18 | 0.15819 | 2.8474 | 478 | 5485.5183 | 11109.7952 | #N/A | #N/A
8922 | CLOVERDALE 1101964556 | 42821101 | CLOVERDALE 1101 | 5.0445 | 31 | 0.15803 | 4.8988 | 479 | 5490.5628 | 11104.8964 | #N/A | #N/A
7447 | BELL 1109CB | 152701109 | BELL 1109 | 0.30133 | 53 | 0.15794 | 8.3708 | 480 | 5490.8641 | 11096.5256 | #N/A | #N/A
5391 | FITCH MOUNTAIN 111324918 | 42751113 | FITCH MOUNTAIN 1113 | 5.4965 | 49 | 0.1575 | 7.7177 | 481 | 5496.3606 | 11088.8079 | 11088.8079 | #N/A
6800 | GEYSERVILLE 1101705777 | 42891101 | GEYSERVILLE 1101 | 6.1467 | 46 | 0.15746 | 7.2434 | 482 | 5502.5073 | 11081.5646 | #N/A | #N/A
29 | CALPELLA 1101542 | 43411101 | CALPELLA 1101 | 33.5352 | 311 | 0.15746 | 48.9707 | 483 | 5536.0426 | 11032.5939 | #N/A | #N/A
9538 | PIT NO 1 1101CB | 103721101 | PIT NO 1 1101 | 6.5478 | 40 | 0.15705 | 6.2822 | 484 | 5542.5904 | 11026.3117 | #N/A | #N/A
7813 | CLOVERDALE 1102383183 | 42821102 | CLOVERDALE 1102 | 14.6467 | 53 | 0.15687 | 8.3141 | 485 | 5557.2371 | 11017.9977 | #N/A | #N/A
8188 | LAKEVILLE 1102152632 | 43371102 | LAKEVILLE 1102 | 1.9263 | 13 | 0.15681 | 2.0385 | 486 | 5559.1634 | 11015.9592 | #N/A | #N/A
5065 | WOODACRE 11011456 | 43021101 | WOODACRE 1101 | 3.8256 | 46 | 0.15596 | 7.1739 | 487 | 5562.989 | 11008.7852 | #N/A | #N/A
5726 | POINT MORETTI 11015104 | 82931101 | POINT MORETTI 1101 | 1.8014 | 11 | 0.15579 | 1.7137 | 488 | 5564.7904 | 11007.0715 | #N/A | #N/A
3142 | MOLINO 110279306 | 42571102 | MOLINO 1102 | 3.7837 | 73 | 0.15551 | 11.352 | 489 | 5568.5741 | 10995.7194 | #N/A | #N/A
10072 | BALCH NO 1 1101R372 | 252501101 | BALCH NO 1 1101 | 4.1665 | 14 | 0.15539 | 2.1754 | 490 | 5572.7406 | 10993.544 | #N/A | #N/A
1776 | TIVY VALLEY 1107869946 | 252941107 | TIVY VALLEY 1107 | 29.7395 | 197 | 0.15534 | 30.6024 | 491 | 5602.4801 | 10962.9417 | #N/A | #N/A
9099 | BELL 1110946229 | 152701110 | BELL 1110 | 0.21901 | 27 | 0.15489 | 4.1819 | 492 | 5602.6991 | 10958.7597 | #N/A | #N/A
11045 | CLARK ROAD 1101CB | 103091101 | CLARK ROAD 1101 | 0.017868 | 2 | 0.15464 | 0.30929 | 493 | 5602.717 | 10958.4504 | #N/A | #N/A
1243 | SHINGLE SPRINGS 110419502 | 153651104 | SHINGLE SPRINGS 1104 | 44.9701 | 672 | 0.15447 | 103.8019 | 494 | 5647.6872 | 10854.6485 | #N/A | #N/A
3579 | WILLITS 1102CB | 42661102 | WILLITS 1102 | 5.3142 | 114 | 0.15412 | 17.5695 | 495 | 5653.0014 | 10837.0791 | #N/A | #N/A
6413 | UKIAH 1114408 | 42771114 | UKIAH 1114 | 37.319 | 280 | 0.15401 | 43.1236 | 496 | 5690.3204 | 10793.9554 | #N/A | #N/A
4125 | SAND CREEK 11037420 | 254601103 | SAND CREEK 1103 | 23.1951 | 263 | 0.15397 | 40.4954 | 497 | 5713.5154 | 10753.4601 | #N/A | #N/A
6897 | SALMON CREEK 110188998 | 43161101 | SALMON CREEK 1101 | 7.9521 | 116 | 0.15352 | 17.8079 | 498 | 5721.4675 | 10735.6522 | #N/A | #N/A
4452 | SILVERADO 2102942170 | 43432102 | SILVERADO 2102 | 3.1315 | 99 | 0.15348 | 15.1945 | 499 | 5724.5991 | 10720.4577 | #N/A | #N/A
59 | VACAVILLE 1111CB | 63601111 | VACAVILLE 1111 | 7.3197 | 154 | 0.15336 | 23.6178 | 500 | 5731.9188 | 10696.8399 | #N/A | #N/A
5605 | SANTA YNEZ 1101Y52 | 182721101 | SANTA YNEZ 1101 | 19.5955 | 141 | 0.15332 | 21.6184 | 501 | 5751.5143 | 10675.2215 | #N/A | #N/A
4437 | STILLWATER 1102CB | 103561102 | STILLWATER 1102 | 25.0474 | 275 | 0.15318 | 42.1242 | 502 | 5776.5617 | 10633.0973 | #N/A | #N/A
3264 | BEAR VALLEY 21059480 | 252192105 | BEAR VALLEY 2105 | 12.4123 | 80 | 0.15314 | 12.251 | 503 | 5788.974 | 10620.8463 | #N/A | #N/A
1519 | FROGTOWN 17021573 | 163451702 | FROGTOWN 1702 | 18.0653 | 156 | 0.15282 | 23.8402 | 504 | 5807.0393 | 10597.0062 | #N/A | #N/A
1732 | NARROWS 21022220 | 153132102 | NARROWS 2102 | 27.4869 | 266 | 0.15235 | 40.5244 | 505 | 5834.5262 | 10556.4817 | #N/A | #N/A
2529 | FULTON 1102287172 | 42561102 | FULTON 1102 | 20.4403 | 258 | 0.15216 | 39.2578 | 506 | 5854.9666 | 10517.2239 | #N/A | #N/A
9038 | OTTER 11022012 | 182941102 | OTTER 1102 | 9.2069 | 64 | 0.15189 | 9.7211 | 507 | 5864.1734 | 10507.5028 | #N/A | #N/A
6205 | OILFIELDS 1103N48 | 182391103 | OILFIELDS 1103 | 47.6716 | 292 | 0.15188 | 44.3489 | 508 | 5911.8451 | 10463.1538 | #N/A | #N/A
6912 | BANGOR 1101301886 | 103191101 | BANGOR 1101 | 2.635 | 90 | 0.15165 | 13.6484 | 509 | 5914.48 | 10449.5055 | #N/A | #N/A
10865 | PASO ROBLES 1103N04 | 182611103 | PASO ROBLES 1103 | 0.53424 | 4 | 0.1516 | 0.60641 | 510 | 5915.0143 | 10448.899 | #N/A | #N/A
10126 | WINDSOR 1103701650 | 43501103 | WINDSOR 1103 | 0.74025 | 12 | 0.15159 | 1.8191 | 511 | 5915.7545 | 10447.0799 | #N/A | #N/A
2118 | LUCERNE 11031280 | 43351103 | LUCERNE 1103 | 8.0384 | 238 | 0.1512 | 35.9845 | 512 | 5923.7929 | 10411.0954 | #N/A | #N/A
7467 | CORRAL 110214026 | 162991102 | CORRAL 1102 | 10.1358 | 101 | 0.15084 | 15.2344 | 513 | 5933.9287 | 10395.861 | #N/A | #N/A
2447 | SAN LUIS OBISPO 110342344 | 182631103 | SAN LUIS OBISPO 1103 | 9.438 | 123 | 0.15077 | 18.5441 | 514 | 5943.3667 | 10377.3169 | #N/A | #N/A
9162 | PUTAH CREEK 1105748272 | 63681105 | PUTAH CREEK 1105 | 0.74961 | 26 | 0.15028 | 3.9074 | 515 | 5944.1163 | 10373.4095 | #N/A | #N/A
6146 | PETALUMA C 1108618 | 42631108 | PETALUMA C 1108 | 8.6329 | 119 | 0.15 | 17.8498 | 516 | 5952.7492 | 10355.5597 | #N/A | #N/A
7759 | BUELLTON 1101Y26 | 183041101 | BUELLTON 1101 | 15.1717 | 133 | 0.14946 | 19.8785 | 517 | 5967.9208 | 10335.6812 | #N/A | #N/A
8614 | WILLOW CREEK 110237374 | 192171102 | WILLOW CREEK 1102 | 2.2478 | 9 | 0.14938 | 1.3444 | 518 | 5970.1686 | 10334.3367 | #N/A | #N/A
1351 | FULTON 11024522 | 42561102 | FULTON 1102 | 8.8123 | 128 | 0.14919 | 19.0963 | 519 | 5978.9809 | 10315.2405 | #N/A | #N/A
5116 | APPLE HILL 210251792 | 153662102 | APPLE HILL 2102 | 9.3569 | 99 | 0.14914 | 14.7646 | 520 | 5988.3378 | 10300.4759 | #N/A | #N/A
2803 | ZACA 1102Y48 | 182681102 | ZACA 1102 | 4.3905 | 157 | 0.14907 | 23.4041 | 521 | 5992.7283 | 10277.0719 | #N/A | #N/A
453 | GARBERVILLE 11011604 | 192221101 | GARBERVILLE 1101 | 4.1852 | 166 | 0.14905 | 24.7419 | 522 | 5996.9134 | 10252.33 | #N/A | #N/A
10386 | CALISTOGA 1101537148 | 42711101 | CALISTOGA 1101 | 0.5737 | 14 | 0.14902 | 2.0863 | 523 | 5997.4871 | 10250.2436 | #N/A | #N/A
1087 | GRASS VALLEY 11032180 | 152031103 | GRASS VALLEY 1103 | 44.1964 | 444 | 0.1487 | 66.0238 | 524 | 6041.6836 | 10184.2198 | #N/A | #N/A
6232 | POSO MOUNTAIN 21012181 | 253642101 | POSO MOUNTAIN 2101 | 16.8531 | 120 | 0.14869 | 17.8426 | 525 | 6058.5367 | 10166.3773 | #N/A | #N/A
1083 | CLARK ROAD 11022044 | 103091102 | CLARK ROAD 1102 | 8.5077 | 67 | 0.14865 | 9.9595 | 526 | 6067.0444 | 10156.4177 | #N/A | #N/A
1119 | MERCED FALLS 110287352 | 252811102 | MERCED FALLS 1102 | 26.6195 | 215 | 0.14862 | 31.9523 | 527 | 6093.6639 | 10124.4654 | #N/A | #N/A
3359 | WISE 1102307494 | 152271102 | WISE 1102 | 31.0496 | 279 | 0.14841 | 41.4062 | 528 | 6124.7134 | 10083.0592 | #N/A | #N/A
8461 | PUTAH CREEK 110264044 | 63681102 | PUTAH CREEK 1102 | 5.9969 | 46 | 0.14834 | 6.8236 | 529 | 6130.7103 | 10076.2356 | 10076.2356 | #N/A
7436 | MENLO 110212249 | 24131102 | MENLO 1102 | 2.4049 | 25 | 0.14826 | 3.7065 | 530 | 6133.1153 | 10072.5291 | #N/A | #N/A
170 | NORTH BRANCH 110111206 | 163231101 | NORTH BRANCH 1101 | 17.8882 | 146 | 0.14787 | 21.5893 | 531 | 6151.0035 | 10050.9398 | #N/A | #N/A
2440 | VOLTA 110180454 | 102541101 | VOLTA 1101 | 31.8338 | 254 | 0.14786 | 37.5574 | 532 | 6182.8373 | 10013.3824 | #N/A | #N/A
6322 | SALMON CREEK 1101196 | 43161101 | SALMON CREEK 1101 | 5.6122 | 36 | 0.14755 | 5.3118 | 533 | 6188.4495 | 10008.0706 | #N/A | #N/A
6558 | MOLINO 110266006 | 42571102 | MOLINO 1102 | 9.0433 | 98 | 0.14747 | 14.4519 | 534 | 6197.4928 | 9993.6188 | #N/A | #N/A
6860 | GARBERVILLE 1101CB | 192221101 | GARBERVILLE 1101 | 7.023 | 87 | 0.14742 | 12.8257 | 535 | 6204.5158 | 9980.793 | #N/A | #N/A
2892 | WYANDOTTE 11071026 | 102911107 | WYANDOTTE 1107 | 22.4808 | 273 | 0.14732 | 40.2177 | 536 | 6226.9966 | 9940.5753 | #N/A | #N/A
1817 | COARSEGOLD 210410110 | 254432104 | COARSEGOLD 2104 | 49.621 | 518 | 0.1471 | 76.1986 | 537 | 6276.6176 | 9864.3767 | #N/A | #N/A
5315 | GIRVAN 11011636 | 103401101 | GIRVAN 1101 | 18.0679 | 200 | 0.14693 | 29.387 | 538 | 6294.6854 | 9834.9897 | #N/A | #N/A
7739 | OILFIELDS 1103N40 | 182391103 | OILFIELDS 1103 | 2.8763 | 23 | 0.14681 | 3.3766 | 539 | 6297.5618 | 9831.6131 | #N/A | #N/A
1598 | COTTONWOOD 11031348 | 102931103 | COTTONWOOD 1103 | 29.1887 | 357 | 0.14666 | 52.3583 | 540 | 6326.7505 | 9779.2548 | #N/A | #N/A
2008 | OAKHURST 11015490 | 254421101 | OAKHURST 1101 | 25.0102 | 276 | 0.14657 | 40.4521 | 541 | 6351.7607 | 9738.8027 | #N/A | #N/A
6294 | OLETA 1101239062 | 163541101 | OLETA 1101 | 12.193 | 113 | 0.14634 | 16.5367 | 542 | 6363.9537 | 9722.266 | #N/A | #N/A
6920 | LAYTONVILLE 110268436 | 42681102 | LAYTONVILLE 1102 | 9.1143 | 45 | 0.14627 | 6.582 | 543 | 6373.068 | 9715.684 | #N/A | #N/A
1698 | GARBERVILLE 11022010 | 192221102 | GARBERVILLE 1102 | 6.6674 | 39 | 0.14585 | 5.6882 | 544 | 6379.7355 | 9709.9958 | #N/A | #N/A
2911 | SHINGLE SPRINGS 210819762 | 153652108 | SHINGLE SPRINGS 2108 | 4.3995 | 72 | 0.14549 | 10.4755 | 545 | 6384.135 | 9699.5204 | #N/A | #N/A
2598 | ELK CREEK 11012008 | 102781101 | ELK CREEK 1101 | 5.734 | 154 | 0.14517 | 22.3567 | 546 | 6389.8689 | 9677.1637 | #N/A | #N/A
2127 | OILFIELDS 1103N44 | 182391103 | OILFIELDS 1103 | 18.1527 | 109 | 0.14496 | 15.8008 | 547 | 6408.0217 | 9661.3629 | #N/A | #N/A
381 | MOUNTAIN QUARRIES 21011102 | 152282101 | MOUNTAIN QUARRIES 2101 | 43.4367 | 431 | 0.14479 | 62.4048 | 548 | 6451.4583 | 9598.9582 | #N/A | #N/A
3913 | CORNING 110164090 | 103331101 | CORNING 1101 | 13.6692 | 170 | 0.1444 | 24.5486 | 549 | 6465.1275 | 9574.4096 | #N/A | #N/A
2481 | BROWNS VALLEY 11011268 | 152921101 | BROWNS VALLEY 1101 | 10.9003 | 106 | 0.14435 | 15.3013 | 550 | 6476.0278 | 9559.1083 | #N/A | #N/A
948 | MARIPOSA 21029590 | 254452102 | MARIPOSA 2102 | 36.2878 | 387 | 0.144 | 55.7277 | 551 | 6512.3156 | 9503.3806 | #N/A | #N/A
4109 | TEMPLETON 2113A60 | 183052113 | TEMPLETON 2113 | 7.2773 | 88 | 0.14391 | 12.6644 | 552 | 6519.5929 | 9490.7162 | #N/A | #N/A
9361 | CLOVERDALE 1102429006 | 42821102 | CLOVERDALE 1102 | 1.9972 | 23 | 0.1436 | 3.3029 | 553 | 6521.59 | 9487.4133 | #N/A | #N/A
429 | COTTONWOOD 11021578 | 102931102 | COTTONWOOD 1102 | 30.142 | 269 | 0.14355 | 38.6147 | 554 | 6551.732 | 9448.7986 | #N/A | #N/A
3755 | INDIAN FLAT 1104CB | 252691104 | INDIAN FLAT 1104 | 12.7765 | 85 | 0.14347 | 12.1951 | 555 | 6564.5085 | 9436.6035 | #N/A | #N/A
5039 | OREGON TRAIL 11031448 | 103521103 | OREGON TRAIL 1103 | 30.7551 | 232 | 0.14347 | 33.2848 | 556 | 6595.2636 | 9403.3187 | #N/A | #N/A
5385 | MONTICELLO 110137384 | 43051101 | MONTICELLO 1101 | 9.3736 | 71 | 0.14324 | 10.17 | 557 | 6604.6372 | 9393.1487 | #N/A | #N/A
9323 | POSO MOUNTAIN 21013990 | 253642101 | POSO MOUNTAIN 2101 | 4.3279 | 25 | 0.14297 | 3.5744 | 558 | 6608.9651 | 9389.5744 | #N/A | #N/A
8609 | PETALUMA C 1108636 | 42631108 | PETALUMA C 1108 | 9.4338 | 108 | 0.14279 | 15.4213 | 559 | 6618.3989 | 9374.1531 | #N/A | #N/A
9301 | VOLTA 110165764 | 102541101 | VOLTA 1101 | 10.3601 | 34 | 0.1423 | 4.8382 | 560 | 6628.759 | 9369.3149 | #N/A | #N/A
10478 | STONE CORRAL 1110189488 | 252921110 | STONE CORRAL 1110 | 0.8249 | 8 | 0.14211 | 1.1369 | 561 | 6629.5839 | 9368.178 | #N/A | #N/A
1096 | CABRILLO 1103Y12 | 183101103 | CABRILLO 1103 | 26.5393 | 274 | 0.14205 | 38.9225 | 562 | 6656.1232 | 9329.2556 | #N/A | #N/A
9878 | CEDAR CREEK 1101451856 | 103321101 | CEDAR CREEK 1101 | 0.065349 | 2 | 0.14172 | 0.28345 | 563 | 6656.1886 | 9328.9721 | #N/A | #N/A
9745 | TASSAJARA 21126392 | 14662112 | TASSAJARA 2112 | 5.4935 | 37 | 0.14162 | 5.2399 | 564 | 6661.682 | 9323.7322 | #N/A | #N/A
4697 | CALISTOGA 1101242919 | 42711101 | CALISTOGA 1101 | 1.3123 | 15 | 0.14151 | 2.1226 | 565 | 6662.9943 | 9321.6095 | #N/A | #N/A
5376 | FORT SEWARD 1121CB | 192321121 | FORT SEWARD 1121 | 9.2029 | 54 | 0.14139 | 7.6353 | 566 | 6672.1973 | 9313.9743 | #N/A | #N/A
4876 | SISQUOC 1102M54 | 182811102 | SISQUOC 1102 | 19.8162 | 166 | 0.14114 | 23.4289 | 567 | 6692.0135 | 9290.5454 | #N/A | #N/A
4881 | LINCOLN 11042070 | 153701104 | LINCOLN 1104 | 17.9936 | 303 | 0.14111 | 42.7554 | 568 | 6710.007 | 9247.7901 | #N/A | #N/A
8866 | SAN RAMON 2101CB | 14232101 | SAN RAMON 2101 | 0.79388 | 11 | 0.14108 | 1.5519 | 569 | 6710.8009 | 9246.2382 | #N/A | #N/A
10487 | HIGGINS 1107746082 | 152691107 | HIGGINS 1107 | 0.81177 | 6 | 0.14016 | 0.84097 | 570 | 6711.6127 | 9245.3972 | #N/A | #N/A
3139 | WILLITS 11044650 | 42661104 | WILLITS 1104 | 3.8474 | 80 | 0.14007 | 11.2058 | 571 | 6715.4601 | 9234.1914 | #N/A | #N/A
474 | COTTONWOOD 11031616 | 102931103 | COTTONWOOD 1103 | 46.9461 | 454 | 0.13915 | 63.1735 | 572 | 6762.4062 | 9171.0179 | #N/A | #N/A
4424 | POSO MOUNTAIN 21014456 | 253642101 | POSO MOUNTAIN 2101 | 23.5315 | 102 | 0.13881 | 14.1582 | 573 | 6785.9377 | 9156.8597 | #N/A | #N/A
7546 | LAYTONVILLE 11022502 | 42681102 | LAYTONVILLE 1102 | 17.8061 | 80 | 0.13859 | 11.0874 | 574 | 6803.7438 | 9145.7723 | #N/A | #N/A
7849 | BEAR VALLEY 21014160 | 252192101 | BEAR VALLEY 2101 | 22.8241 | 192 | 0.13839 | 26.57 | 575 | 6826.5679 | 9119.2023 | #N/A | #N/A
10064 | WILLOW PASS 1101152874 | 13911101 | WILLOW PASS 1101 | 0.61051 | 10 | 0.13803 | 1.3803 | 576 | 6827.1784 | 9117.822 | #N/A | #N/A
2621 | LINCOLN 1101186060 | 153701101 | LINCOLN 1101 | 10.9028 | 161 | 0.13732 | 22.1085 | 577 | 6838.0812 | 9095.7135 | #N/A | #N/A
5254 | SHINGLE SPRINGS 21092679 | 153652109 | SHINGLE SPRINGS 2109 | 7.1071 | 70 | 0.13732 | 9.6123 | 578 | 6845.1883 | 9086.1012 | #N/A | #N/A
3959 | SILVERADO 210234959 | 43432102 | SILVERADO 2102 | 25.7758 | 205 | 0.13657 | 27.9958 | 579 | 6870.9641 | 9058.1054 | #N/A | #N/A
4389 | VOLTA 11011516 | 102541101 | VOLTA 1101 | 25.3925 | 123 | 0.13616 | 16.7471 | 580 | 6896.3566 | 9041.3583 | #N/A | #N/A
9812 | CURTIS 170411300 | 163351704 | CURTIS 1704 | 3.6748 | 41 | 0.1361 | 5.5803 | 581 | 6900.0314 | 9035.778 | #N/A | #N/A
4676 | NARROWS 210551582 | 153132105 | NARROWS 2105 | 9.5278 | 105 | 0.13574 | 14.2523 | 582 | 6909.5592 | 9021.5257 | #N/A | #N/A
430 | TEJON 1102732836 | 252931102 | TEJON 1102 | 11.6772 | 154 | 0.1353 | 20.8364 | 583 | 6921.2364 | 9000.6893 | #N/A | #N/A
4932 | MONTICELLO 1101720 | 43051101 | MONTICELLO 1101 | 6.7891 | 70 | 0.1353 | 9.4707 | 584 | 6928.0255 | 8991.2186 | #N/A | #N/A
6310 | RIO DELL 11024230 | 192251102 | RIO DELL 1102 | 22.9009 | 59 | 0.13512 | 7.9721 | 585 | 6950.9265 | 8983.2465 | 8983.2465 | #N/A
517 | CLARKSVILLE 210413352 | 153612104 | CLARKSVILLE 2104 | 34.7401 | 409 | 0.13486 | 55.1568 | 586 | 6985.6666 | 8928.0897 | #N/A | #N/A
7402 | MARIPOSA 2102594143 | 254452102 | MARIPOSA 2102 | 0.50625 | 60 | 0.13461 | 8.0769 | 587 | 6986.1728 | 8920.0128 | #N/A | #N/A
19 | CLEAR LAKE 1101406 | 42141101 | CLEAR LAKE 1101 | 12.4205 | 312 | 0.1343 | 41.9011 | 588 | 6998.5934 | 8878.1117 | #N/A | #N/A
4720 | DUNLAP 11027849F | 254061102 | DUNLAP 1102 | 8.6698 | 61 | 0.13395 | 8.1711 | 589 | 7007.2631 | 8869.9406 | #N/A | #N/A
6125 | JESSUP 1103348657 | 103441103 | JESSUP 1103 | 2.0223 | 29 | 0.13388 | 3.8825 | 590 | 7009.2854 | 8866.0581 | #N/A | #N/A
9100 | BANGOR 1101870548 | 103191101 | BANGOR 1101 | 5.0876 | 56 | 0.13326 | 7.4625 | 591 | 7014.373 | 8858.5956 | #N/A | #N/A
7774 | RED BLUFF 110176020 | 103541101 | RED BLUFF 1101 | 9.3423 | 137 | 0.13318 | 18.2456 | 592 | 7023.7153 | 8840.35 | #N/A | #N/A
5975 | HARTLEY 11011306 | 43211101 | HARTLEY 1101 | 9.4843 | 117 | 0.13303 | 15.5648 | 593 | 7033.1996 | 8824.7852 | #N/A | #N/A
3100 | GARBERVILLE 11022540 | 192221102 | GARBERVILLE 1102 | 16.2351 | 135 | 0.13296 | 17.9496 | 594 | 7049.4348 | 8806.8356 | #N/A | #N/A
9542 | OLETA 1102CB | 163541102 | OLETA 1102 | 0.3708 | 11 | 0.13274 | 1.4601 | 595 | 7049.8056 | 8805.3755 | #N/A | #N/A
6900 | SALT SPRINGS 210110416 | 163692101 | SALT SPRINGS 2101 | 0.68999 | 7 | 0.1325 | 0.92748 | 596 | 7050.4956 | 8804.448 | #N/A | #N/A
1019 | HOPLAND 1101770 | 42251101 | HOPLAND 1101 | 8.6005 | 110 | 0.13217 | 14.5382 | 597 | 7059.096 | 8789.9098 | #N/A | #N/A
9774 | WILDWOOD 1101384582 | 103611101 | WILDWOOD 1101 | 4.5397 | 8 | 0.13184 | 1.0547 | 598 | 7063.6357 | 8788.8551 | #N/A | #N/A
6290 | WYANDOTTE 110796390 | 102911107 | WYANDOTTE 1107 | 8.5479 | 124 | 0.13125 | 16.2749 | 599 | 7072.1836 | 8772.5802 | #N/A | #N/A
8217 | VINEYARD 2110CB | 14502110 | VINEYARD 2110 | 5.5901 | 86 | 0.1308 | 11.2491 | 600 | 7077.7737 | 8761.3311 | #N/A | #N/A
7155 | PEORIA 1701CB | 163781701 | PEORIA 1701 | 8.7743 | 70 | 0.13063 | 9.1442 | 601 | 7086.548 | 8752.1869 | #N/A | #N/A
1707 | HIGGINS 11039753 | 152691103 | HIGGINS 1103 | 2.0548 | 23 | 0.13059 | 3.0036 | 602 | 7088.6028 | 8749.1833 | #N/A | #N/A
10679 | COVELO 1101627416 | 43061101 | COVELO 1101 | 0.6038 | 14 | 0.13024 | 1.8234 | 603 | 7089.2066 | 8747.3599 | #N/A | #N/A
2248 | CORRAL 110313474 | 162991103 | CORRAL 1103 | 2.9373 | 99 | 0.13001 | 12.8713 | 604 | 7092.1439 | 8734.4886 | #N/A | #N/A
6056 | MARIPOSA 2101309438 | 254452101 | MARIPOSA 2101 | 3.6909 | 93 | 0.12966 | 12.0584 | 605 | 7095.8347 | 8722.4301 | #N/A | #N/A
5806 | COLUMBIA HILL 11012212 | 152471101 | COLUMBIA HILL 1101 | 9.1336 | 76 | 0.12922 | 9.8207 | 606 | 7104.9684 | 8712.6094 | #N/A | 8712.6094
5628 | PUEBLO 11041304 | 43291104 | PUEBLO 1104 | 19.2267 | 175 | 0.12902 | 22.578 | 607 | 7124.195 | 8690.0314 | #N/A | #N/A
5578 | VASCO 1102886522 | 13751102 | VASCO 1102 | 6.7797 | 154 | 0.12899 | 19.8644 | 608 | 7130.9747 | 8670.167 | #N/A | #N/A
2390 | WYANDOTTE 11091520 | 102911109 | WYANDOTTE 1109 | 4.1643 | 230 | 0.1287 | 29.6011 | 609 | 7135.139 | 8640.5659 | #N/A | #N/A
2104 | LINCOLN 11045391 | 153701104 | LINCOLN 1104 | 0.95101 | 7 | 0.12868 | 0.90075 | 610 | 7136.09 | 8639.6651 | #N/A | #N/A
826 | TASSAJARA 210419042 | 14662104 | TASSAJARA 2104 | 6.2584 | 89 | 0.12861 | 11.4466 | 611 | 7142.3484 | 8628.2185 | #N/A | #N/A
7172 | FITCH MOUNTAIN 1113356 | 42751113 | FITCH MOUNTAIN 1113 | 10.7179 | 136 | 0.12847 | 17.4723 | 612 | 7153.0663 | 8610.7463 | #N/A | #N/A
761 | BANGOR 11017446 | 103191101 | BANGOR 1101 | 43.5002 | 427 | 0.12828 | 54.7764 | 613 | 7196.5665 | 8555.9699 | #N/A | #N/A
9800 | CALISTOGA 110135588 | 42711101 | CALISTOGA 1101 | 3.0795 | 18 | 0.12786 | 2.3016 | 614 | 7199.646 | 8553.6683 | #N/A | #N/A
9664 | PASO ROBLES 110359763 | 182611103 | PASO ROBLES 1103 | 2.8168 | 30 | 0.12716 | 3.8149 | 615 | 7202.4628 | 8549.8533 | #N/A | #N/A
5583 | RED BLUFF 11031702 | 103541103 | RED BLUFF 1103 | 16.7546 | 177 | 0.12716 | 22.5069 | 616 | 7219.2174 | 8527.3465 | #N/A | #N/A
4955 | WILLITS 1104188268 | 42661104 | WILLITS 1104 | 4.2682 | 66 | 0.1264 | 8.3425 | 617 | 7223.4856 | 8519.004 | #N/A | #N/A
9342 | SAND CREEK 11037823F | 254601103 | SAND CREEK 1103 | 4.6783 | 49 | 0.12636 | 6.1917 | 618 | 7228.1639 | 8512.8123 | #N/A | #N/A
7895 | PEORIA 1704877670 | 163781704 | PEORIA 1704 | 6.585 | 28 | 0.12626 | 3.5352 | 619 | 7234.7489 | 8509.2772 | #N/A | #N/A
1593 | MENLO 1102W80 | 24131102 | MENLO 1102 | 18.9504 | 129 | 0.12598 | 16.2519 | 620 | 7253.6993 | 8493.0253 | #N/A | #N/A
9134 | SAN LUIS OBISPO 1104350030 | 182631104 | SAN LUIS OBISPO 1104 | 5.7957 | 107 | 0.12598 | 13.4795 | 621 | 7259.495 | 8479.5457 | #N/A | #N/A
10634 | EDENVALE 2107288980 | 82952107 | EDENVALE 2107 | 0.33085 | 6 | 0.12531 | 0.75188 | 622 | 7259.8259 | 8478.7939 | #N/A | #N/A
8835 | SOLEDAD 2102955138 | 182052102 | SOLEDAD 2102 | 2.6274 | 16 | 0.12515 | 2.0024 | 623 | 7262.4533 | 8476.7915 | #N/A | #N/A
6170 | GIRVAN 11011330 | 103401101 | GIRVAN 1101 | 31.0696 | 264 | 0.12503 | 33.0087 | 624 | 7293.5228 | 8443.7828 | #N/A | #N/A
9760 | RINCON 11035152 | 43321103 | RINCON 1103 | 1.6688 | 17 | 0.1239 | 2.1064 | 625 | 7295.1916 | 8441.6764 | #N/A | #N/A
6631 | HIGHLANDS 11031282 | 43361103 | HIGHLANDS 1103 | 14.2542 | 164 | 0.12376 | 20.2971 | 626 | 7309.4457 | 8421.3793 | #N/A | #N/A
7124 | SANTA YNEZ 1102CB | 182721102 | SANTA YNEZ 1102 | 1.4593 | 124 | 0.12375 | 15.3456 | 627 | 7310.9051 | 8406.0337 | #N/A | #N/A
547 | STILLWATER 11021644 | 103561102 | STILLWATER 1102 | 22.8387 | 244 | 0.12375 | 30.1941 | 628 | 7333.7438 | 8375.8396 | #N/A | #N/A
6046 | WOODWARD 210878448 | 255292108 | WOODWARD 2108 | 19.5076 | 188 | 0.12365 | 23.2453 | 629 | 7353.2514 | 8352.5943 | #N/A | #N/A
7443 | GARBERVILLE 11011770 | 192221101 | GARBERVILLE 1101 | 8.6077 | 66 | 0.12342 | 8.1457 | 630 | 7361.8591 | 8344.4486 | #N/A | #N/A
2056 | BUELLTON 1101Y06 | 183041101 | BUELLTON 1101 | 30.3639 | 304 | 0.12317 | 37.4433 | 631 | 7392.2231 | 8307.0054 | #N/A | #N/A
1863 | DIAMOND SPRINGS 110610587 | 152261106 | DIAMOND SPRINGS 1106 | 21.9618 | 212 | 0.12297 | 26.0703 | 632 | 7414.1849 | 8280.9351 | #N/A | #N/A
5060 | CLOVERDALE 1102156 | 42821102 | CLOVERDALE 1102 | 6.1652 | 110 | 0.12268 | 13.4944 | 633 | 7420.3501 | 8267.4407 | #N/A | #N/A
8874 | BRIDGEVILLE 110169866 | 192461101 | BRIDGEVILLE 1101 | 6.5701 | 46 | 0.12256 | 5.6379 | 634 | 7426.9202 | 8261.8028 | #N/A | #N/A
7200 | DIAMOND SPRINGS 1104705100 | 152261104 | DIAMOND SPRINGS 1104 | 7.3867 | 78 | 0.12223 | 9.5341 | 635 | 7434.3068 | 8252.2687 | #N/A | #N/A
5273 | SAND CREEK 11037110 | 254601103 | SAND CREEK 1103 | 18.6347 | 132 | 0.12197 | 16.0996 | 636 | 7452.9416 | 8236.1691 | #N/A | #N/A
3234 | FULTON 1107604 | 42561107 | FULTON 1107 | 17.4386 | 169 | 0.12169 | 20.5661 | 637 | 7470.3801 | 8215.603 | 8215.603 | #N/A
8992 | TIDEWATER 2106781445 | 14652106 | TIDEWATER 2106 | 0.25204 | 6 | 0.12145 | 0.72871 | 638 | 7470.6322 | 8214.8743 | #N/A | #N/A
9503 | SAN LUIS OBISPO 1103153199 | 182631103 | SAN LUIS OBISPO 1103 | 2.9525 | 53 | 0.1214 | 6.4339 | 639 | 7473.5847 | 8208.4404 | #N/A | #N/A
8489 | LAYTONVILLE 1102572 | 42681102 | LAYTONVILLE 1102 | 21.398 | 155 | 0.12097 | 18.7503 | 640 | 7494.9826 | 8189.6901 | #N/A | #N/A
1408 | ATASCADERO 1103A16 | 182541103 | ATASCADERO 1103 | 19.7861 | 122 | 0.12088 | 14.7476 | 641 | 7514.7688 | 8174.9425 | #N/A | #N/A
68 | TEJON 11022455 | 252931102 | TEJON 1102 | 6.3179 | 84 | 0.12034 | 10.1082 | 642 | 7521.0867 | 8164.8343 | #N/A | #N/A
6764 | MAXWELL 11053008 | 62881105 | MAXWELL 1105 | 8.4754 | 55 | 0.1202 | 6.6112 | 643 | 7529.5621 | 8158.2231 | #N/A | #N/A
3997 | APPLE HILL 2102CB | 153662102 | APPLE HILL 2102 | 41.2823 | 448 | 0.12006 | 53.7868 | 644 | 7570.8445 | 8104.4363 | #N/A | #N/A
4706 | WYANDOTTE 11031504 | 102911103 | WYANDOTTE 1103 | 11.0226 | 186 | 0.12006 | 22.3307 | 645 | 7581.8671 | 8082.1056 | #N/A | #N/A
8185 | CLARKSVILLE 2109CB | 153612109 | CLARKSVILLE 2109 | 0.99037 | 15 | 0.11989 | 1.7983 | 646 | 7582.8575 | 8080.3073 | #N/A | #N/A
5862 | HOLLISTER 2102855412 | 182492102 | HOLLISTER 2102 | 28.4042 | 108 | 0.11956 | 12.9123 | 647 | 7611.2617 | 8067.395 | #N/A | #N/A
2833 | MARTELL 11033152 | 163011103 | MARTELL 1103 | 16.733 | 134 | 0.11956 | 16.0208 | 648 | 7627.9946 | 8051.3742 | #N/A | #N/A
3141 | DIAMOND SPRINGS 11057722 | 152261105 | DIAMOND SPRINGS 1105 | 60.1507 | 572 | 0.11928 | 68.2291 | 649 | 7688.1454 | 7983.1451 | #N/A | #N/A
501 | DOBBINS 11011264 | 153741101 | DOBBINS 1101 | 34.9826 | 307 | 0.11917 | 36.585 | 650 | 7723.1279 | 7946.5601 | #N/A | #N/A
855 | HIGGINS 1103CB | 152691103 | HIGGINS 1103 | 28.0762 | 315 | 0.11916 | 37.536 | 651 | 7751.2042 | 7909.0241 | #N/A | #N/A
491 | TIVY VALLEY 1107822606 | 252941107 | TIVY VALLEY 1107 | 13.4878 | 144 | 0.11894 | 17.1275 | 652 | 7764.692 | 7891.8966 | #N/A | #N/A
8121 | CAYETANO 2109MR186 | 14422109 | CAYETANO 2109 | 0.50894 | 27 | 0.11874 | 3.2061 | 653 | 7765.201 | 7888.6905 | #N/A | #N/A
2634 | APPLE HILL 21028372 | 153662102 | APPLE HILL 2102 | 58.7208 | 629 | 0.11858 | 74.5861 | 654 | 7823.9218 | 7814.1044 | #N/A | #N/A
1440 | MARIPOSA 21019400 | 254452101 | MARIPOSA 2101 | 63.1061 | 667 | 0.11849 | 79.0304 | 655 | 7887.0279 | 7735.074 | #N/A | #N/A
8059 | OILFIELDS 1103N62 | 182391103 | OILFIELDS 1103 | 5.5613 | 39 | 0.11842 | 4.6183 | 656 | 7892.5893 | 7730.4558 | #N/A | #N/A
1860 | SHINGLE SPRINGS 2105CB | 153652105 | SHINGLE SPRINGS 2105 | 19.0248 | 245 | 0.11812 | 28.9401 | 657 | 7911.614 | 7701.5157 | #N/A | #N/A
1237 | NARROWS 2102CB | 153132102 | NARROWS 2102 | 22.5529 | 243 | 0.11807 | 28.6917 | 658 | 7934.1669 | 7672.824 | #N/A | #N/A
9931 | CORTINA 1101528460 | 63121101 | CORTINA 1101 | 1.8916 | 12 | 0.11792 | 1.415 | 659 | 7936.0585 | 7671.409 | #N/A | #N/A
6877 | COARSEGOLD 21036110 | 254432103 | COARSEGOLD 2103 | 11.0096 | 179 | 0.11737 | 21.0097 | 660 | 7947.0681 | 7650.3993 | #N/A | #N/A
3126 | HORSESHOE 110150140 | 152571101 | HORSESHOE 1101 | 3.9511 | 82 | 0.11734 | 9.6215 | 661 | 7951.0192 | 7640.7778 | #N/A | #N/A
9916 | SAN LUIS OBISPO 1104777686 | 182631104 | SAN LUIS OBISPO 1104 | 1.6826 | 17 | 0.11731 | 1.9944 | 662 | 7952.7018 | 7638.7835 | #N/A | #N/A
8080 | SILVERADO 210258626 | 43432102 | SILVERADO 2102 | 15.2217 | 125 | 0.117 | 14.6249 | 663 | 7967.9235 | 7624.1586 | 7624.1586 | #N/A
4277 | SAN JOAQUIN #2 1103157026 | 252521103 | SAN JOAQUIN #2 1103 | 3.2319 | 44 | 0.11682 | 5.1403 | 664 | 7971.1554 | 7619.0183 | #N/A | #N/A
6827 | PEORIA 170411232 | 163781704 | PEORIA 1704 | 12.7443 | 222 | 0.11656 | 25.8772 | 665 | 7983.8997 | 7593.1411 | #N/A | #N/A
772 | DIAMOND SPRINGS 11052102 | 152261105 | DIAMOND SPRINGS 1105 | 37.4816 | 417 | 0.11621 | 48.4576 | 666 | 8021.3813 | 7544.6834 | 7544.6834 | #N/A
1946 | WILLITS 1104CB | 42661104 | WILLITS 1104 | 3.8906 | 90 | 0.11609 | 10.4477 | 667 | 8025.2719 | 7534.2357 | #N/A | #N/A
2370 | GEYSERVILLE 1102484 | 42891102 | GEYSERVILLE 1102 | 33.3678 | 379 | 0.11607 | 43.9888 | 668 | 8058.6397 | 7490.2469 | #N/A | #N/A
7186 | HIGGINS 1104CB | 152691104 | HIGGINS 1104 | 11.2182 | 124 | 0.11592 | 14.3743 | 669 | 8069.8579 | 7475.8727 | #N/A | #N/A
9814 | PENRYN 1105119949 | 152561105 | PENRYN 1105 | 1.3809 | 25 | 0.11529 | 2.8822 | 670 | 8071.2388 | 7472.9905 | #N/A | #N/A
7423 | CLAY 1103CB | 163341103 | CLAY 1103 | 6.0162 | 110 | 0.11521 | 12.6729 | 671 | 8077.255 | 7460.3176 | #N/A | #N/A
7292 | TIDEWATER 2106745811 | 14652106 | TIDEWATER 2106 | 0.39857 | 8 | 0.11506 | 0.92047 | 672 | 8077.6536 | 7459.3971 | #N/A | #N/A
8864 | WOODACRE 110191900 | 43021101 | WOODACRE 1101 | 9.0238 | 91 | 0.11491 | 10.4566 | 673 | 8086.6774 | 7448.9405 | #N/A | #N/A
9782 | SAND CREEK 110397354 | 254601103 | SAND CREEK 1103 | 8.8056 | 59 | 0.11488 | 6.7778 | 674 | 8095.483 | 7442.1627 | #N/A | #N/A
7321 | CLARKSVILLE 210619642 | 153612106 | CLARKSVILLE 2106 | 0.77467 | 17 | 0.11477 | 1.9511 | 675 | 8096.2577 | 7440.2116 | #N/A | #N/A
1291 | MERCED FALLS 11029470 | 252811102 | MERCED FALLS 1102 | 22.84 | 277 | 0.11474 | 31.7833 | 676 | 8119.0977 | 7408.4283 | #N/A | #N/A
10278 | PUEBLO 2102943820 | 43292102 | PUEBLO 2102 | 1.8891 | 13 | 0.11464 | 1.4903 | 677 | 8120.9868 | 7406.938 | #N/A | #N/A
2358 | WHITMORE 11011594 | 103601101 | WHITMORE 1101 | 24.2649 | 160 | 0.11449 | 18.3178 | 678 | 8145.2517 | 7388.6202 | #N/A | #N/A
892 | MARIPOSA 210110240 | 254452101 | MARIPOSA 2101 | 21.5594 | 189 | 0.11431 | 21.6045 | 679 | 8166.8111 | 7367.0158 | #N/A | #N/A
4813 | CLOVERDALE 1102674 | 42821102 | CLOVERDALE 1102 | 16.9652 | 122 | 0.11401 | 13.9092 | 680 | 8183.7763 | 7353.1066 | #N/A | #N/A
4778 | SHINGLE SPRINGS 210961892 | 153652109 | SHINGLE SPRINGS 2109 | 30.116 | 318 | 0.11372 | 36.1635 | 681 | 8213.8923 | 7316.9431 | #N/A | #N/A
9093 | BANGOR 110155206 | 103191101 | BANGOR 1101 | 0 | 28 | 0.11351 | 3.1783 | 682 | 8213.8923 | 7313.7647 | #N/A | #N/A
395 | CALISTOGA 1101734 | 42711101 | CALISTOGA 1101 | 13.7047 | 162 | 0.11348 | 18.3842 | 683 | 8227.597 | 7295.3805 | #N/A | #N/A
7143 | COTATI 1103CB | 42271103 | COTATI 1103 | 12.0712 | 106 | 0.11341 | 12.0218 | 684 | 8239.6682 | 7283.3587 | #N/A | #N/A
2744 | WHITMORE 110145262 | 103601101 | WHITMORE 1101 | 28.7967 | 221 | 0.11334 | 25.0485 | 685 | 8268.4649 | 7258.3102 | #N/A | #N/A
4167 | COTTONWOOD 11031344 | 102931103 | COTTONWOOD 1103 | 10.1214 | 152 | 0.11327 | 17.2178 | 686 | 8278.5863 | 7241.0924 | #N/A | #N/A
9035 | CLEAR LAKE 1101699062 | 42141101 | CLEAR LAKE 1101 | 0.84503 | 20 | 0.11322 | 2.2645 | 687 | 8279.4314 | 7238.8279 | #N/A | #N/A
2015 | SHINGLE SPRINGS 210912392 | 153652109 | SHINGLE SPRINGS 2109 | 14.6504 | 178 | 0.11309 | 20.1293 | 688 | 8294.0818 | 7218.6986 | #N/A | #N/A
2546 | PLACERVILLE 1110421358 | 153081110 | PLACERVILLE 1110 | 14.8357 | 169 | 0.11286 | 19.0733 | 689 | 8308.9175 | 7199.6253 | #N/A | #N/A
6240 | SILVERADO 2104722 | 43432104 | SILVERADO 2104 | 7.8964 | 99 | 0.11274 | 11.1613 | 690 | 8316.8139 | 7188.464 | #N/A | #N/A
6314 | TEJON 11023751 | 252931102 | TEJON 1102 | 9.8215 | 65 | 0.11269 | 7.325 | 691 | 8326.6355 | 7181.139 | #N/A | #N/A
8377 | CAYETANO 2111CB | 14422111 | CAYETANO 2111 | 3.3871 | 81 | 0.11258 | 9.1187 | 692 | 8330.0225 | 7172.0203 | #N/A | #N/A
84 | LINCOLN 110451756 | 153701104 | LINCOLN 1104 | 10.8395 | 264 | 0.11252 | 29.7041 | 693 | 8340.8621 | 7142.3162 | #N/A | #N/A
4410 | MC ARTHUR 1101501106 | 103491101 | MC ARTHUR 1101 | 9.9962 | 86 | 0.11248 | 9.6734 | 694 | 8350.8583 | 7132.6427 | #N/A | #N/A
1376 | CLARKSVILLE 210419772 | 153612104 | CLARKSVILLE 2104 | 17.9244 | 185 | 0.11233 | 20.7806 | 695 | 8368.7827 | 7111.8621 | #N/A | #N/A
138 | CLARKSVILLE 2103593454 | 153612103 | CLARKSVILLE 2103 | 32.0092 | 324 | 0.11221 | 36.3549 | 696 | 8400.7919 | 7075.5073 | #N/A | #N/A
6028 | RISING RIVER 11011530 | 103551101 | RISING RIVER 1101 | 11.2915 | 167 | 0.11218 | 18.7349 | 697 | 8412.0834 | 7056.7724 | #N/A | #N/A
6687 | CLARK ROAD 110281296 | 103091102 | CLARK ROAD 1102 | 10.9205 | 124 | 0.11218 | 13.9107 | 698 | 8423.0039 | 7042.8618 | #N/A | #N/A
2672 | APPLE HILL 210277546 | 153662102 | APPLE HILL 2102 | 43.0994 | 403 | 0.11214 | 45.1922 | 699 | 8466.1033 | 6997.6696 | #N/A | #N/A
4377 | MARIPOSA 2101752630 | 254452101 | MARIPOSA 2101 | 18.9925 | 154 | 0.11205 | 17.2553 | 700 | 8485.0958 | 6980.4143 | #N/A | #N/A
5474 | COTATI 1105213984 | 42271105 | COTATI 1105 | 6.9378 | 47 | 0.11198 | 5.263 | 701 | 8492.0335 | 6975.1513 | #N/A | #N/A
6448 | MERCED FALLS 110238748 | 252811102 | MERCED FALLS 1102 | 15.354 | 178 | 0.11192 | 19.9215 | 702 | 8507.3876 | 6955.2298 | #N/A | #N/A
1645 | COTATI 110599720 | 42271105 | COTATI 1105 | 9.1863 | 134 | 0.11177 | 14.9768 | 703 | 8516.5739 | 6940.2531 | #N/A | #N/A
439 | HIGGINS 1110CB | 152691110 | HIGGINS 1110 | 8.7129 | 134 | 0.11172 | 14.9707 | 704 | 8525.2868 | 6925.2824 | #N/A | #N/A
6646 | UPPER LAKE 110175370 | 42871101 | UPPER LAKE 1101 | 11.0775 | 133 | 0.11161 | 14.8441 | 705 | 8536.3643 | 6910.4383 | #N/A | #N/A
3320 | LAYTONVILLE 110237586 | 42681102 | LAYTONVILLE 1102 | 13.9571 | 72 | 0.11137 | 8.0187 | 706 | 8550.3215 | 6902.4196 | #N/A | #N/A
8527 | HIGGINS 11097831 | 152691109 | HIGGINS 1109 | 8.8881 | 86 | 0.1113 | 9.5719 | 707 | 8559.2096 | 6892.8477 | #N/A | #N/A
8404 | TEMPLETON 2110317796 | 183052110 | TEMPLETON 2110 | 5.0644 | 65 | 0.11087 | 7.2063 | 708 | 8564.2739 | 6885.6414 | #N/A | #N/A
9399 | CALAVERAS CEMENT 1101585 | 162211101 | CALAVERAS CEMENT 1101 | 14.1272 | 95 | 0.11082 | 10.5283 | 709 | 8578.4011 | 6875.1132 | #N/A | #N/A
9168 | CAL WATER 1102690954 | 255451102 | CAL WATER 1102 | 3.9839 | 12 | 0.11057 | 1.3268 | 710 | 8582.385 | 6873.7863 | #N/A | #N/A
1850 | OAKHURST 1103CB | 254421103 | OAKHURST 1103 | 32.1872 | 417 | 0.11044 | 46.0525 | 711 | 8614.5722 | 6827.7338 | #N/A | #N/A
4124 | CALPELLA 1102CB | 43411102 | CALPELLA 1102 | 0.16351 | 61 | 0.1104 | 6.7341 | 712 | 8614.7357 | 6820.9997 | #N/A | #N/A
10720 | OCEANO 1103839302 | 182601103 | OCEANO 1103 | 1.1227 | 8 | 0.11001 | 0.88007 | 713 | 8615.8584 | 6820.1196 | #N/A | #N/A
2355 | OLETA 11021204 | 163541102 | OLETA 1102 | 25.7145 | 233 | 0.10989 | 25.6033 | 714 | 8641.5729 | 6794.5163 | #N/A | #N/A
635 | BRUNSWICK 11062790 | 152481106 | BRUNSWICK 1106 | 9.9616 | 115 | 0.10954 | 12.5971 | 715 | 8651.5345 | 6781.9193 | #N/A | #N/A
6919 | COTTONWOOD 110168190 | 102931101 | COTTONWOOD 1101 | 23.9832 | 238 | 0.10937 | 26.0311 | 716 | 8675.5177 | 6755.8881 | #N/A | #N/A
10335 | PETALUMA C 1109664732 | 42631109 | PETALUMA C 1109 | 0.89361 | 6 | 0.10842 | 0.65051 | 717 | 8676.4113 | 6755.2376 | #N/A | #N/A
4157 | CALPELLA 1101600 | 43411101 | CALPELLA 1101 | 19.186 | 164 | 0.10818 | 17.7408 | 718 | 8695.5973 | 6737.4968 | #N/A | #N/A
3546 | LUCERNE 1103CB | 43351103 | LUCERNE 1103 | 2.2493 | 59 | 0.10789 | 6.3658 | 719 | 8697.8466 | 6731.131 | #N/A | #N/A
6463 | SONOMA 1105229588 | 42721105 | SONOMA 1105 | 9.6526 | 149 | 0.10786 | 16.0708 | 720 | 8707.4992 | 6715.0603 | #N/A | #N/A
2133 | FROGTOWN 17011623 | 163451701 | FROGTOWN 1701 | 15.2605 | 152 | 0.1076 | 16.3546 | 721 | 8722.7597 | 6698.7057 | 6698.7057 | #N/A
10925 | GOLDTREE 1105551904 | 182581105 | GOLDTREE 1105 | 0.022199 | 1 | 0.10733 | 0.10733 | 722 | 8722.7819 | 6698.5984 | #N/A | #N/A
9605 | NOTRE DAME 1104937710 | 102041104 | NOTRE DAME 1104 | 0.85279 | 8 | 0.10733 | 0.85862 | 723 | 8723.6347 | 6697.7397 | #N/A | #N/A
3953 | JAMESON 11059472 | 63801105 | JAMESON 1105 | 3.0669 | 90 | 0.10731 | 9.6577 | 724 | 8726.7016 | 6688.0821 | #N/A | #N/A
6952 | OLETA 110151740 | 163541101 | OLETA 1101 | 15.5571 | 129 | 0.107 | 13.8028 | 725 | 8742.2587 | 6674.2793 | #N/A | #N/A
4360 | CORRAL 110236666 | 162991102 | CORRAL 1102 | 16.9644 | 207 | 0.10683 | 22.1131 | 726 | 8759.2231 | 6652.1662 | #N/A | #N/A
10467 | BIG BEND 11011704 | 103751101 | BIG BEND 1101 | 2.9988 | 9 | 0.1065 | 0.95854 | 727 | 8762.2219 | 6651.2077 | #N/A | #N/A
2963 | KONOCTI 110275382 | 43311102 | KONOCTI 1102 | 23.2045 | 198 | 0.10636 | 21.0588 | 728 | 8785.4264 | 6630.1489 | #N/A | #N/A
7719 | GEYSERVILLE 1102220154 | 42891102 | GEYSERVILLE 1102 | 0.26588 | 30 | 0.10579 | 3.1738 | 729 | 8785.6923 | 6626.9751 | #N/A | #N/A
4276 | NARROWS 2105CB | 153132105 | NARROWS 2105 | 36.093 | 382 | 0.10567 | 40.3677 | 730 | 8821.7853 | 6586.6073 | #N/A | #N/A
4123 | MARIPOSA 21014410 | 254452101 | MARIPOSA 2101 | 22.8107 | 232 | 0.10548 | 24.471 | 731 | 8844.596 | 6562.1363 | #N/A | #N/A
5996 | MONTICELLO 1101630 | 43051101 | MONTICELLO 1101 | 18.7154 | 93 | 0.10515 | 9.7794 | 732 | 8863.3114 | 6552.3569 | #N/A | #N/A
7010 | WILLITS 1103966 | 42661103 | WILLITS 1103 | 0.96697 | 34 | 0.10505 | 3.5716 | 733 | 8864.2783 | 6548.7854 | #N/A | #N/A
6094 | PARADISE 110443008 | 102831104 | PARADISE 1104 | 12.8637 | 145 | 0.10501 | 15.2269 | 734 | 8877.1421 | 6533.5584 | #N/A | #N/A
6540 | MORGAN HILL 2105XR070 | 83242105 | MORGAN HILL 2105 | 6.5379 | 90 | 0.10473 | 9.4261 | 735 | 8883.68 | 6524.1324 | #N/A | #N/A
1104 | BRUNSWICK 11042112 | 152481104 | BRUNSWICK 1104 | 19.3921 | 222 | 0.1046 | 23.2211 | 736 | 8903.0721 | 6500.9113 | #N/A | #N/A
3331 | NARROWS 21052216 | 153132105 | NARROWS 2105 | 56.6762 | 663 | 0.10438 | 69.2068 | 737 | 8959.7484 | 6431.7045 | #N/A | #N/A
10962 | POINT ARENA 1101CB | 43381101 | POINT ARENA 1101 | 0.040346 | 2 | 0.10413 | 0.20825 | 738 | 8959.7887 | 6431.4963 | #N/A | #N/A
7695 | JAMESON 110265516 | 63801102 | JAMESON 1102 | 7.7033 | 137 | 0.104 | 14.2484 | 739 | 8967.492 | 6417.2479 | #N/A | #N/A
4131 | CURTIS 170565908 | 163351705 | CURTIS 1705 | 13.9093 | 205 | 0.10393 | 21.3052 | 740 | 8981.4013 | 6395.9427 | #N/A | #N/A
386 | CORRAL 110112606 | 162991101 | CORRAL 1101 | 22.4639 | 216 | 0.10392 | 22.4476 | 741 | 9003.8652 | 6373.4951 | #N/A | #N/A
1298 | DESCHUTES 11011652 | 103351101 | DESCHUTES 1101 | 21.066 | 170 | 0.10352 | 17.5982 | 742 | 9024.9312 | 6355.8969 | #N/A | #N/A
10344 | CLARKSVILLE 210319572 | 153612103 | CLARKSVILLE 2103 | 0.37003 | 12 | 0.10348 | 1.2418 | 743 | 9025.3013 | 6354.6551 | #N/A | #N/A
2338 | CLAY 110113442 | 163341101 | CLAY 1101 | 25.3259 | 272 | 0.10338 | 28.1191 | 744 | 9050.6272 | 6326.536 | #N/A | #N/A
1080 | PLACER 1103284874 | 152461103 | PLACER 1103 | 2.1447 | 56 | 0.10322 | 5.7804 | 745 | 9052.7719 | 6320.7556 | #N/A | #N/A
2572 | VACA DIXON 11059792 | 63591105 | VACA DIXON 1105 | 0.78022 | 329 | 0.10322 | 33.9591 | 746 | 9053.5521 | 6286.7965 | #N/A | #N/A
10829 | MILPITAS 110962157 | 82831109 | MILPITAS 1109 | 0.044811 | 3 | 0.10257 | 0.30771 | 747 | 9053.5969 | 6286.4888 | #N/A | #N/A
9526 | DOBBINS 110191464 | 153741101 | DOBBINS 1101 | 7.0318 | 81 | 0.10229 | 8.2855 | 748 | 9060.6286 | 6278.2032 | #N/A | #N/A
4686 | ELK CREEK 11012212 | 102781101 | ELK CREEK 1101 | 15.6044 | 136 | 0.10222 | 13.9025 | 749 | 9076.2331 | 6264.3007 | #N/A | #N/A
2703 | COTATI 110536536 | 42271105 | COTATI 1105 | 17.2163 | 206 | 0.10219 | 21.0515 | 750 | 9093.4494 | 6243.2492 | #N/A | #N/A
261 | CLARK ROAD 11022584 | 103091102 | CLARK ROAD 1102 | 9.0835 | 83 | 0.1019 | 8.4581 | 751 | 9102.5329 | 6234.7911 | #N/A | #N/A
6202 | COARSEGOLD 210490356 | 254432104 | COARSEGOLD 2104 | 4.8161 | 148 | 0.10189 | 15.079 | 752 | 9107.3489 | 6219.7121 | #N/A | #N/A
10164 | CALPELLA 1101345230 | 43411101 | CALPELLA 1101 | 1.186 | 22 | 0.10181 | 2.2398 | 753 | 9108.5349 | 6217.4723 | #N/A | #N/A
10372 | CLOVERDALE 11024646 | 42821102 | CLOVERDALE 1102 | 0.15065 | 8 | 0.10163 | 0.81301 | 754 | 9108.6855 | 6216.6593 | #N/A | #N/A
10615 | STAFFORD 1102CB | 43201102 | STAFFORD 1102 | 0.59497 | 10 | 0.10116 | 1.0116 | 755 | 9109.2805 | 6215.6478 | #N/A | #N/A
10097 | GARBERVILLE 110256048 | 192221102 | GARBERVILLE 1102 | 4.9779 | 27 | 0.10102 | 2.7275 | 756 | 9114.2584 | 6212.9202 | #N/A | #N/A
2214 | MONTICELLO 11014360 | 43051101 | MONTICELLO 1101 | 7.564 | 76 | 0.10101 | 7.6765 | 757 | 9121.8224 | 6205.2438 | #N/A | #N/A
2869 | NARROWS 21011202 | 153132101 | NARROWS 2101 | 45.7737 | 459 | 0.10087 | 46.3007 | 758 | 9167.5961 | 6158.9431 | #N/A | #N/A
2918 | JESSUP 110338864 | 103441103 | JESSUP 1103 | 1.8068 | 94 | 0.10076 | 9.4715 | 759 | 9169.4029 | 6149.4716 | #N/A | #N/A
8434 | FORT ROSS 1121204 | 42851121 | FORT ROSS 1121 | 19.6108 | 107 | 0.10067 | 10.7713 | 760 | 9189.0138 | 6138.7003 | #N/A | #N/A
9462 | BEAR VALLEY 210110019 | 252192101 | BEAR VALLEY 2101 | 1.981 | 11 | 0.10052 | 1.1057 | 761 | 9190.9948 | 6137.5945 | #N/A | #N/A
3132 | MORGAN HILL 210542348 | 83242105 | MORGAN HILL 2105 | 1.343 | 53 | 0.10037 | 5.3194 | 762 | 9192.3378 | 6132.2751 | #N/A | #N/A
10415 | SAN LUIS OBISPO 1103934355 | 182631103 | SAN LUIS OBISPO 1103 | 0.56909 | 12 | 0.10029 | 1.2035 | 763 | 9192.9068 | 6131.0716 | #N/A | #N/A
800 | NARROWS 210248484 | 153132102 | NARROWS 2102 | 41.6749 | 450 | 0.09998 | 44.991 | 764 | 9234.5817 | 6086.0806 | #N/A | #N/A
3794 | HIGGINS 11077559 | 152691107 | HIGGINS 1107 | 4.4708 | 52 | 0.099807 | 5.1899 | 765 | 9239.0525 | 6080.8907 | #N/A | #N/A
4136 | MONTICELLO 1101718 | 43051101 | MONTICELLO 1101 | 27.0127 | 247 | 0.099744 | 24.6369 | 766 | 9266.0652 | 6056.2538 | #N/A | #N/A
2696 | OLETA 110163500 | 163541101 | OLETA 1101 | 0.20333 | 46 | 0.099652 | 4.584 | 767 | 9266.2685 | 6051.6698 | #N/A | #N/A
3595 | CEDAR CREEK 11011608 | 103321101 | CEDAR CREEK 1101 | 33.4541 | 252 | 0.099644 | 25.1102 | 768 | 9299.7226 | 6026.5596 | #N/A | #N/A
80 | WHEATLAND 1105248490 | 152811105 | WHEATLAND 1105 | 11.0172 | 228 | 0.099611 | 22.7114 | 769 | 9310.7397 | 6003.8482 | #N/A | #N/A
24 | FITCH MOUNTAIN 1113443164 | 42751113 | FITCH MOUNTAIN 1113 | 2.7965 | 111 | 0.099321 | 11.0246 | 770 | 9313.5363 | 5992.8236 | #N/A | #N/A
6194 | CLARK ROAD 110292622 | 103091102 | CLARK ROAD 1102 | 31.2685 | 257 | 0.098498 | 25.314 | 771 | 9344.8048 | 5967.5096 | #N/A | #N/A
643 | PENRYN 1105154362 | 152561105 | PENRYN 1105 | 2.163 | 90 | 0.098415 | 8.8574 | 772 | 9346.9678 | 5958.6522 | #N/A | #N/A
10663 | SAN RAMON 2102CB | 14232102 | SAN RAMON 2102 | 1.763 | 16 | 0.098349 | 1.5736 | 773 | 9348.7308 | 5957.0787 | #N/A | #N/A
7571 | BROWNS VALLEY 110193870 | 152921101 | BROWNS VALLEY 1101 | 18.5376 | 342 | 0.098287 | 33.6143 | 774 | 9367.2684 | 5923.4643 | #N/A | #N/A
9322 | MONTICELLO 1101CB | 43051101 | MONTICELLO 1101 | 0.53443 | 5 | 0.098274 | 0.49137 | 775 | 9367.8028 | 5922.973 | #N/A | #N/A
5943 | TEMPLETON 2113A10 | 183052113 | TEMPLETON 2113 | 31.0415 | 264 | 0.098002 | 25.8725 | 776 | 9398.8442 | 5897.1005 | #N/A | #N/A
5478 | PENRYN 11072706 | 152561107 | PENRYN 1107 | 5.783 | 190 | 0.09785 | 18.5915 | 777 | 9404.6273 | 5878.509 | #N/A | #N/A
3757 | WILLITS 1104934 | 42661104 | WILLITS 1104 | 30.8641 | 279 | 0.097599 | 27.2301 | 778 | 9435.4914 | 5851.2789 | #N/A | #N/A
7329 | CORRAL 110213498 | 162991102 | CORRAL 1102 | 0.98568 | 13 | 0.097071 | 1.2619 | 779 | 9436.4771 | 5850.017 | #N/A | #N/A
6184 | PEORIA 170190090 | 163781701 | PEORIA 1701 | 30.0386 | 168 | 0.09692 | 16.2826 | 780 | 9466.5157 | 5833.7343 | #N/A | #N/A
1027 | OILFIELDS 110383158 | 182391103 | OILFIELDS 1103 | 17.6694 | 132 | 0.09689 | 12.7894 | 781 | 9484.185 | 5820.9449 | #N/A | #N/A
3208 | WILLITS 11032500 | 42661103 | WILLITS 1103 | 29.917 | 143 | 0.096773 | 13.8385 | 782 | 9514.102 | 5807.1065 | #N/A | #N/A
9576 | LLAGAS 2104603392 | 83182104 | LLAGAS 2104 | 2.9124 | 17 | 0.096621 | 1.6426 | 783 | 9517.0144 | 5805.4639 | #N/A | #N/A
211 | APPLE HILL 110313312 | 153661103 | APPLE HILL 1103 | 13.1484 | 190 | 0.096554 | 18.3453 | 784 | 9530.1627 | 5787.1186 | #N/A | #N/A
1106 | BANGOR 11011958 | 103191101 | BANGOR 1101 | 33.8504 | 353 | 0.096142 | 33.9382 | 785 | 9564.0132 | 5753.1804 | #N/A | #N/A
5073 | LAYTONVILLE 1102CB | 42681102 | LAYTONVILLE 1102 | 11.9747 | 95 | 0.095782 | 9.0993 | 786 | 9575.9879 | 5744.0811 | #N/A | #N/A
7859 | MOUNTAIN QUARRIES 210135466 | 152282101 | MOUNTAIN QUARRIES 2101 | 7.3565 | 82 | 0.095562 | 7.8361 | 787 | 9583.3444 | 5736.245 | #N/A | #N/A
871 | PEORIA 17019811 | 163781701 | PEORIA 1701 | 3.5901 | 92 | 0.095333 | 8.7707 | 788 | 9586.9345 | 5727.4744 | #N/A | #N/A
669 | CABRILLO 1103CB | 183101103 | CABRILLO 1103 | 0.54422 | 45 | 0.095165 | 4.2824 | 789 | 9587.4788 | 5723.1919 | #N/A | #N/A
3438 | CALISTOGA 1102CB | 42711102 | CALISTOGA 1102 | 0.32187 | 37 | 0.095153 | 3.5207 | 790 | 9587.8006 | 5719.6713 | #N/A | #N/A
8923 | SUNOL 1101CB | 14241101 | SUNOL 1101 | 3.2822 | 53 | 0.095135 | 5.0422 | 791 | 9591.0828 | 5714.6291 | #N/A | #N/A
5883 | SILVERADO 2104632 | 43432104 | SILVERADO 2104 | 18.3299 | 193 | 0.094959 | 18.327 | 792 | 9609.4127 | 5696.3021 | #N/A | #N/A
5762 | CHALLENGE 11021064 | 103201102 | CHALLENGE 1102 | 19.6711 | 179 | 0.094905 | 16.9879 | 793 | 9629.0837 | 5679.3141 | #N/A | #N/A
847 | CURTIS 17026008 | 163351702 | CURTIS 1702 | 23.3091 | 236 | 0.094797 | 22.3721 | 794 | 9652.3928 | 5656.942 | #N/A | #N/A
7905 | CAYETANO 2109CB | 14422109 | CAYETANO 2109 | 1.4107 | 51 | 0.094773 | 4.8334 | 795 | 9653.8035 | 5652.1086 | #N/A | #N/A
6145 | OAKHURST 110210100 | 254421102 | OAKHURST 1102 | 10.3936 | 142 | 0.094733 | 13.4521 | 796 | 9664.1971 | 5638.6565 | #N/A | #N/A
6083 | MILPITAS 1109XR524 | 82831109 | MILPITAS 1109 | 10.891 | 59 | 0.09443 | 5.5714 | 797 | 9675.0882 | 5633.0852 | #N/A | #N/A
370 | UKIAH 1114CB | 42771114 | UKIAH 1114 | 0.66327 | 93 | 0.094346 | 8.7742 | 798 | 9675.7514 | 5624.311 | #N/A | #N/A
7085 | MESA 1103854149 | 182821103 | MESA 1103 | 0.97169 | 12 | 0.094333 | 1.132 | 799 | 9676.7231 | 5623.179 | #N/A | #N/A
8026 | PEORIA 1704CB | 163781704 | PEORIA 1704 | 8.3718 | 64 | 0.094159 | 6.0262 | 800 | 9685.0949 | 5617.1528 | #N/A | #N/A
4910 | PUEBLO 2103373667 | 43292103 | PUEBLO 2103 | 3.275 | 45 | 0.09414 | 4.2363 | 801 | 9688.3699 | 5612.9165 | #N/A | #N/A
3504 | MOLINO 1102396 | 42571102 | MOLINO 1102 | 16.102 | 182 | 0.093951 | 17.099 | 802 | 9704.4719 | 5595.8175 | #N/A | #N/A
8266 | LAS POSITAS 2108MR182 | 14402108 | LAS POSITAS 2108 | 6.6928 | 56 | 0.093921 | 5.2596 | 803 | 9711.1648 | 5590.5579 | #N/A | #N/A
6506 | CALAVERAS CEMENT 11014786 | 162211101 | CALAVERAS CEMENT 1101 | 18.0074 | 173 | 0.09378 | 16.224 | 804 | 9729.1722 | 5574.3339 | #N/A | #N/A
1161 | WYANDOTTE 110777578 | 102911107 | WYANDOTTE 1107 | 21.3971 | 389 | 0.09328 | 36.2858 | 805 | 9750.5693 | 5538.0481 | #N/A | #N/A
5393 | GARBERVILLE 11024744 | 192221102 | GARBERVILLE 1102 | 17.3636 | 161 | 0.093231 | 15.0101 | 806 | 9767.9329 | 5523.038 | #N/A | #N/A
5755 | PENRYN 11072704 | 152561107 | PENRYN 1107 | 1.4297 | 76 | 0.093023 | 7.0698 | 807 | 9769.3626 | 5515.9682 | #N/A | #N/A
8038 | WILLITS 1103826 | 42661103 | WILLITS 1103 | 7.7413 | 89 | 0.092902 | 8.2683 | 808 | 9777.1039 | 5507.6999 | #N/A | #N/A
5718 | PETALUMA C 1108233646 | 42631108 | PETALUMA C 1108 | 9.3863 | 127 | 0.092653 | 11.7669 | 809 | 9786.4902 | 5495.933 | #N/A | #N/A
7314 | CLARKSVILLE 210575884 | 153612105 | CLARKSVILLE 2105 | 10.6684 | 94 | 0.09258 | 8.7025 | 810 | 9797.1586 | 5487.2305 | #N/A | #N/A
837 | DIAMOND SPRINGS 11071402 | 152261107 | DIAMOND SPRINGS 1107 | 44.1915 | 541 | 0.092281 | 49.924 | 811 | 9841.3501 | 5437.3065 | 5437.3065 | #N/A
1640 | JESSUP 1101CB | 103441101 | JESSUP 1101 | 1.5303 | 66 | 0.092174 | 6.0835 | 812 | 9842.8804 | 5431.223 | #N/A | #N/A
2558 | PENRYN 1103660 | 152561103 | PENRYN 1103 | 10.1639 | 233 | 0.092166 | 21.4747 | 813 | 9853.0443 | 5409.7483 | #N/A | #N/A
9244 | KERN OIL 110646960 | 252721106 | KERN OIL 1106 | 0.91054 | 14 | 0.092145 | 1.29 | 814 | 9853.9548 | 5408.4583 | #N/A | #N/A
4181 | MONTICELLO 1101666 | 43051101 | MONTICELLO 1101 | 12.0959 | 90 | 0.092048 | 8.2843 | 815 | 9866.0507 | 5400.174 | #N/A | #N/A
8910 | BRIDGEVILLE 110255612 | 192461102 | BRIDGEVILLE 1102 | 22.2384 | 93 | 0.090894 | 8.4532 | 816 | 9888.2891 | 5391.7208 | #N/A | #N/A
3415 | PARADISE 1104409622 | 102831104 | PARADISE 1104 | 12.7625 | 156 | 0.090831 | 14.1696 | 817 | 9901.0516 | 5377.5512 | #N/A | #N/A
4056 | CALAVERAS CEMENT 110113424 | 162211101 | CALAVERAS CEMENT 1101 | 1.4942 | 43 | 0.090714 | 3.9007 | 818 | 9902.5458 | 5373.6504 | #N/A | #N/A
345 | COTTONWOOD 1101384360 | 102931101 | COTTONWOOD 1101 | 4.9052 | 70 | 0.090426 | 6.3298 | 819 | 9907.451 | 5367.3206 | #N/A | #N/A
287 | WHITMORE 11011598 | 103601101 | WHITMORE 1101 | 33.5165 | 251 | 0.09042 | 22.6955 | 820 | 9940.9674 | 5344.6251 | #N/A | #N/A
8279 | LOW GAP 110186816 | 192411101 | LOW GAP 1101 | 4.4149 | 51 | 0.090319 | 4.6062 | 821 | 9945.3823 | 5340.0189 | #N/A | #N/A
7426 | SANTA MARIA 1108M18 | 182671108 | SANTA MARIA 1108 | 15.2655 | 81 | 0.090027 | 7.2922 | 822 | 9960.6477 | 5332.7267 | #N/A | #N/A
7586 | KONOCTI 1102948 | 43311102 | KONOCTI 1102 | 6.3142 | 73 | 0.089784 | 6.5542 | 823 | 9966.962 | 5326.1725 | #N/A | #N/A
8787 | GIRVAN 1102212096 | 103401102 | GIRVAN 1102 | 2.5631 | 42 | 0.089733 | 3.7688 | 824 | 9969.5251 | 5322.4037 | #N/A | #N/A
10586 | LOS MOLINOS 1101297862 | 103481101 | LOS MOLINOS 1101 | 0.31276 | 4 | 0.089567 | 0.35827 | 825 | 9969.8378 | 5322.0455 | #N/A | #N/A
6573 | SISQUOC 1103858898 | 182811103 | SISQUOC 1103 | 19.6096 | 152 | 0.089508 | 13.6052 | 826 | 9989.4474 | 5308.4403 | #N/A | #N/A
10830 | PETALUMA C 1109373772 | 42631109 | PETALUMA C 1109 | 0.017818 | 2 | 0.089417 | 0.17883 | 827 | 9989.4652 | 5308.2615 | #N/A | #N/A
817 | CLOVERDALE 1102570 | 42821102 | CLOVERDALE 1102 | 17.7483 | 199 | 0.089292 | 17.7691 | 828 | 10007.2135 | 5290.4923 | #N/A | #N/A
5781 | SAN JOAQUIN #3 11035100 | 252531103 | SAN JOAQUIN #3 1103 | 21.334 | 204 | 0.089218 | 18.2004 | 829 | 10028.5475 | 5272.2919 | #N/A | #N/A
6729 | SAN LUIS OBISPO 110788962 | 182631107 | SAN LUIS OBISPO 1107 | 2.4841 | 45 | 0.089174 | 4.0128 | 830 | 10031.0316 | 5268.2791 | #N/A | #N/A
5238 | DIAMOND SPRINGS 110656026 | 152261106 | DIAMOND SPRINGS 1106 | 15.1269 | 158 | 0.089061 | 14.0716 | 831 | 10046.1585 | 5254.2074 | #N/A | #N/A
4137 | UKIAH 1114528 | 42771114 | UKIAH 1114 | 3.7591 | 110 | 0.08906 | 9.7966 | 832 | 10049.9177 | 5244.4108 | #N/A | #N/A
2145 | CALISTOGA 1101736 | 42711101 | CALISTOGA 1101 | 34.6626 | 350 | 0.088841 | 31.0945 | 833 | 10084.5802 | 5213.3163 | #N/A | #N/A
8817 | WYANDOTTE 1105CB | 102911105 | WYANDOTTE 1105 | 11.4973 | 14 | 0.088539 | 1.2395 | 834 | 10096.0776 | 5212.0768 | #N/A | #N/A
3899 | PEORIA 170510580 | 163781705 | PEORIA 1705 | 7.7172 | 129 | 0.088489 | 11.415 | 835 | 10103.7948 | 5200.6617 | #N/A | #N/A
5666 | WOODSIDE 110147872 | 24251101 | WOODSIDE 1101 | 4.17 | 52 | 0.088422 | 4.5979 | 836 | 10107.9648 | 5196.0638 | #N/A | #N/A
7241 | ATASCADERO 1103A14 | 182541103 | ATASCADERO 1103 | 25.119 | 152 | 0.088418 | 13.4395 | 837 | 10133.0838 | 5182.6243 | #N/A | #N/A
878 | FROGTOWN 170275252 | 163451702 | FROGTOWN 1702 | 57.9081 | 401 | 0.088153 | 35.3494 | 838 | 10190.9919 | 5147.2749 | #N/A | #N/A
4836 | GRASS VALLEY 11031700 | 152031103 | GRASS VALLEY 1103 | 21.7093 | 255 | 0.087918 | 22.4191 | 839 | 10212.7011 | 5124.8558 | #N/A | #N/A
7987 | BELL 1108339792 | 152701108 | BELL 1108 | 2.6235 | 43 | 0.087729 | 3.7723 | 840 | 10215.3246 | 5121.0835 | #N/A | #N/A
8725 | LLAGAS 2101984552 | 83182101 | LLAGAS 2101 | 4.5399 | 53 | 0.087511 | 4.6381 | 841 | 10219.8645 | 5116.4454 | #N/A | #N/A
4715 | GIRVAN 110280726 | 103401102 | GIRVAN 1102 | 7.8692 | 217 | 0.087369 | 18.9591 | 842 | 10227.7337 | 5097.4863 | #N/A | #N/A
5678 | SAN LUIS OBISPO 1102348318 | 182631102 | SAN LUIS OBISPO 1102 | 0.37106 | 6 | 0.087346 | 0.52408 | 843 | 10228.1048 | 5096.9622 | #N/A | #N/A
8497 | BEAR VALLEY 210576694 | 252192105 | BEAR VALLEY 2105 | 4.5478 | 37 | 0.087295 | 3.2299 | 844 | 10232.6525 | 5093.7323 | #N/A | #N/A
4933 | RACETRACK 17039190 | 163761703 | RACETRACK 1703 | 8.9738 | 104 | 0.087115 | 9.06 | 845 | 10241.6264 | 5084.6723 | #N/A | #N/A
10437 | RIO DELL 110275970 | 192251102 | RIO DELL 1102 | 7.072 | 33 | 0.08694 | 2.869 | 846 | 10248.6984 | 5081.8033 | #N/A | #N/A
3279 | OAKHURST 1101CB | 254421101 | OAKHURST 1101 | 2.3149 | 47 | 0.086583 | 4.0694 | 847 | 10251.0133 | 5077.7339 | 5077.7339 | #N/A
6810 | KESWICK 11011590 | 103451101 | KESWICK 1101 | 6.4567 | 63 | 0.086534 | 5.4516 | 848 | 10257.47 | 5072.2823 | #N/A | #N/A
2304 | SAN JOAQUIN #3 1103CB | 252531103 | SAN JOAQUIN #3 1103 | 28.3844 | 294 | 0.086354 | 25.3881 | 849 | 10285.8544 | 5046.8942 | #N/A | #N/A
7373 | TIVY VALLEY 11077380 | 252941107 | TIVY VALLEY 1107 | 12.9556 | 240 | 0.086218 | 20.6923 | 850 | 10298.81 | 5026.2019 | #N/A | #N/A
1492 | STILLWATER 110148950 | 103561101 | STILLWATER 1101 | 12.4809 | 145 | 0.085979 | 12.467 | 851 | 10311.2909 | 5013.735 | #N/A | #N/A
3172 | RED BLUFF 1105161818 | 103541105 | RED BLUFF 1105 | 0.13198 | 59 | 0.08588 | 5.0669 | 852 | 10311.4229 | 5008.668 | #N/A | #N/A
5834 | SANTA YNEZ 1102320270 | 182721102 | SANTA YNEZ 1102 | 8.4827 | 137 | 0.08574 | 11.7464 | 853 | 10319.9055 | 4996.9216 | #N/A | #N/A
742 | MORGAN HILL 2105XR176 | 83242105 | MORGAN HILL 2105 | 22.5311 | 309 | 0.085689 | 26.478 | 854 | 10342.4366 | 4970.4437 | #N/A | #N/A
8450 | MARTELL 1102CB | 163011102 | MARTELL 1102 | 5.6818 | 69 | 0.08567 | 5.9113 | 855 | 10348.1185 | 4964.5324 | #N/A | #N/A
3883 | COTATI 1102167726 | 42271102 | COTATI 1102 | 3.8001 | 50 | 0.08544 | 4.272 | 856 | 10351.9186 | 4960.2605 | #N/A | #N/A
10186 | CLAYTON 22159765 | 12022215 | CLAYTON 2215 | 0.26445 | 16 | 0.085394 | 1.3663 | 857 | 10352.183 | 4958.8941 | #N/A | #N/A
5425 | CORNING 110187304 | 103331101 | CORNING 1101 | 2.8806 | 100 | 0.085339 | 8.5339 | 858 | 10355.0636 | 4950.3602 | #N/A | #N/A
4113 | PHILO 1101CB | 42601101 | PHILO 1101 | 31.8871 | 469 | 0.085283 | 39.9976 | 859 | 10386.9507 | 4910.3627 | #N/A | #N/A
10106 | GEYSERVILLE 1102537096 | 42891102 | GEYSERVILLE 1102 | 0.48227 | 6 | 0.085228 | 0.51137 | 860 | 10387.433 | 4909.8513 | #N/A | #N/A
9409 | CLAY 1102CB | 163341102 | CLAY 1102 | 0.92759 | 19 | 0.085217 | 1.6191 | 861 | 10388.3606 | 4908.2322 | #N/A | #N/A
6247 | ELK CREEK 11012004 | 102781101 | ELK CREEK 1101 | 25 | 174 | 0.085175 | 14.8204 | 862 | 10413.3606 | 4893.4117 | #N/A | #N/A
2719 | SAN LUIS OBISPO 1104V10 | 182631104 | SAN LUIS OBISPO 1104 | 2.1783 | 54 | 0.085103 | 4.5956 | 863 | 10415.5389 | 4888.8162 | #N/A | #N/A
541 | TEMPLETON 2113R82 | 183052113 | TEMPLETON 2113 | 38.4024 | 563 | 0.084913 | 47.806 | 864 | 10453.9413 | 4841.0101 | #N/A | #N/A
7060 | BIG BEND 1102CB | 103751102 | BIG BEND 1102 | 17.0366 | 139 | 0.084888 | 11.7994 | 865 | 10470.9778 | 4829.2107 | 4829.2107 | #N/A
7634 | IONE 1101L3141 | 163881101 | IONE 1101 | 13.8321 | 97 | 0.084539 | 8.2002 | 866 | 10484.8099 | 4821.0105 | #N/A | #N/A
1449 | FORT SEWARD 1122CB | 192321122 | FORT SEWARD 1122 | 17.6589 | 111 | 0.084457 | 9.3748 | 867 | 10502.4688 | 4811.6357 | #N/A | #N/A
3137 | MOLINO 1102104 | 42571102 | MOLINO 1102 | 21.7475 | 235 | 0.084332 | 19.818 | 868 | 10524.2162 | 4791.8177 | #N/A | #N/A
4967 | NARROWS 21052748 | 153132105 | NARROWS 2105 | 12.9469 | 245 | 0.084145 | 20.6156 | 869 | 10537.1631 | 4771.2021 | #N/A | #N/A
9631 | EDENVALE 2107739448 | 82952107 | EDENVALE 2107 | 1.7776 | 12 | 0.084104 | 1.0093 | 870 | 10538.9407 | 4770.1929 | #N/A | #N/A
5449 | PENRYN 110351658 | 152561103 | PENRYN 1103 | 8.1666 | 108 | 0.084002 | 9.0722 | 871 | 10547.1073 | 4761.1207 | #N/A | #N/A
9940 | MILPITAS 110598568 | 82831105 | MILPITAS 1105 | 0.1045 | 7 | 0.083995 | 0.58797 | 872 | 10547.2118 | 4760.5327 | #N/A | #N/A
4281 | PUEBLO 1105637242 | 43291105 | PUEBLO 1105 | 16.8339 | 193 | 0.083893 | 16.1913 | 873 | 10564.0457 | 4744.3414 | #N/A | #N/A
9696 | LAS GALLINAS A 1104507389 | 42991104 | LAS GALLINAS A 1104 | 0.13197 | 4 | 0.083842 | 0.33537 | 874 | 10564.1776 | 4744.0061 | #N/A | #N/A
3446 | ELK CREEK 11012228 | 102781101 | ELK CREEK 1101 | 3.3625 | 80 | 0.082955 | 6.6364 | 875 | 10567.5401 | 4737.3697 | #N/A | #N/A
2644 | WILLITS 110391948 | 42661103 | WILLITS 1103 | 7.4224 | 69 | 0.082927 | 5.7219 | 876 | 10574.9625 | 4731.6477 | #N/A | #N/A
2263 | SWIFT 2110XR366 | 83392110 | SWIFT 2110 | 8.4324 | 129 | 0.082848 | 10.6874 | 877 | 10583.3949 | 4720.9604 | #N/A | #N/A
9623 | SANTA YNEZ 1104685160 | 182721104 | SANTA YNEZ 1104 | 0.58655 | 17 | 0.082766 | 1.407 | 878 | 10583.9815 | 4719.5534 | #N/A | #N/A
7942 | FULTON 11024994 | 42561102 | FULTON 1102 | 1.3585 | 45 | 0.082765 | 3.7244 | 879 | 10585.34 | 4715.8289 | #N/A | #N/A
4041 | FROGTOWN 1702737236 | 163451702 | FROGTOWN 1702 | 8.7642 | 88 | 0.082425 | 7.2534 | 880 | 10594.1042 | 4708.5755 | #N/A | #N/A
4759 | COTATI 110379140 | 42271103 | COTATI 1103 | 9.7839 | 154 | 0.082367 | 12.6845 | 881 | 10603.8881 | 4695.891 | #N/A | #N/A
1164 | BEAR VALLEY 2105454432 | 252192105 | BEAR VALLEY 2105 | 14.4352 | 112 | 0.08233 | 9.221 | 882 | 10618.3233 | 4686.67 | #N/A | #N/A
4634 | SHINGLE SPRINGS 211051790 | 153652110 | SHINGLE SPRINGS 2110 | 7.909 | 106 | 0.082229 | 8.7163 | 883 | 10626.2323 | 4677.9538 | #N/A | #N/A
4491 | CALPELLA 1102144510 | 43411102 | CALPELLA 1102 | 3.1138 | 41 | 0.08218 | 3.3694 | 884 | 10629.3461 | 4674.5844 | #N/A | #N/A
3945 | DOBBINS 11015202 | 153741101 | DOBBINS 1101 | 16.3256 | 162 | 0.082155 | 13.3091 | 885 | 10645.6717 | 4661.2753 | #N/A | #N/A
5174 | CALAVERAS CEMENT 110111236 | 162211101 | CALAVERAS CEMENT 1101 | 19.7501 | 143 | 0.081838 | 11.7029 | 886 | 10665.4218 | 4649.5724 | #N/A | #N/A
4695 | SILVERADO 21043485 | 43432104 | SILVERADO 2104 | 1.7427 | 23 | 0.081749 | 1.8802 | 887 | 10667.1645 | 4647.6922 | #N/A | #N/A
5312 | PETALUMA C 1108632 | 42631108 | PETALUMA C 1108 | 14.7283 | 81 | 0.081559 | 6.6063 | 888 | 10681.8928 | 4641.0858 | #N/A | #N/A
8333 | BEAR VALLEY 21054609 | 252192105 | BEAR VALLEY 2105 | 4.5506 | 41 | 0.081381 | 3.3366 | 889 | 10686.4434 | 4637.7492 | #N/A | #N/A
7354 | JOLON 11027004 | 182981102 | JOLON 1102 | 7.9213 | 128 | 0.081062 | 10.3759 | 890 | 10694.3647 | 4627.3733 | #N/A | #N/A
4785 | MORGAN HILL 2111XR398 | 83242111 | MORGAN HILL 2111 | 37.7039 | 341 | 0.080766 | 27.5412 | 891 | 10732.0686 | 4599.8321 | #N/A | #N/A
9589 | CLAY 11031821 | 163341103 | CLAY 1103 | 3.5846 | 33 | 0.080483 | 2.6559 | 892 | 10735.6531 | 4597.1762 | #N/A | #N/A
1075 | LINCOLN 110195756 | 153701101 | LINCOLN 1101 | 7.4272 | 200 | 0.080379 | 16.0759 | 893 | 10743.0804 | 4581.1003 | #N/A | #N/A
3754 | PALMER 1101M82 | 183031101 | PALMER 1101 | 10.8435 | 149 | 0.080327 | 11.9687 | 894 | 10753.9239 | 4569.1316 | #N/A | #N/A
5126 | CRESCENT MILLS 21012056 | 103132101 | CRESCENT MILLS 2101 | 5.0155 | 70 | 0.080308 | 5.6215 | 895 | 10758.9394 | 4563.51 | #N/A | #N/A
7701 | SILVERADO 2102808 | 43432102 | SILVERADO 2102 | 2.5368 | 39 | 0.0803 | 3.1317 | 896 | 10761.4762 | 4560.3783 | #N/A | #N/A
1034 | HOOPA 11013290 | 192401101 | HOOPA 1101 | 13.5618 | 135 | 0.080281 | 10.8379 | 897 | 10775.038 | 4549.5404 | #N/A | #N/A
7166 | GANSNER 1101372132 | 103021101 | GANSNER 1101 | 0.41841 | 13 | 0.08025 | 1.0433 | 898 | 10775.4564 | 4548.4971 | #N/A | #N/A
9769 | UKIAH 1111807988 | 42771111 | UKIAH 1111 | 4.168 | 15 | 0.080023 | 1.2003 | 899 | 10779.6244 | 4547.2968 | #N/A | #N/A
6682 | OILFIELDS 1103643162 | 182391103 | OILFIELDS 1103 | 3.4384 | 41 | 0.079941 | 3.2776 | 900 | 10783.0628 | 4544.0192 | #N/A | #N/A
10896 | CMC 1102CB | 183111102 | CMC 1102 | 0.36161 | 5 | 0.079905 | 0.39953 | 901 | 10783.4244 | 4543.6197 | #N/A | #N/A
2989 | KONOCTI 11024300 | 43311102 | KONOCTI 1102 | 26.9634 | 268 | 0.079811 | 21.3893 | 902 | 10810.3878 | 4522.2304 | #N/A | #N/A
10408 | POSO MOUNTAIN 21011703 | 253642101 | POSO MOUNTAIN 2101 | 0.90462 | 7 | 0.079525 | 0.55668 | 903 | 10811.2924 | 4521.6737 | #N/A | #N/A
6364 | PLACERVILLE 2106935216 | 153082106 | PLACERVILLE 2106 | 21.0371 | 204 | 0.079474 | 16.2127 | 904 | 10832.3295 | 4505.461 | #N/A | #N/A
4098 | WYANDOTTE 11071510 | 102911107 | WYANDOTTE 1107 | 25.4992 | 243 | 0.079411 | 19.297 | 905 | 10857.8287 | 4486.164 | #N/A | #N/A
7076 | CLARKSVILLE 210419632 | 153612104 | CLARKSVILLE 2104 | 5.5922 | 110 | 0.07935 | 8.7285 | 906 | 10863.4209 | 4477.4355 | #N/A | #N/A
1230 | TEMPLETON 2113A08 | 183052113 | TEMPLETON 2113 | 10.4677 | 257 | 0.079335 | 20.3891 | 907 | 10873.8886 | 4457.0464 | #N/A | #N/A
5155 | FOOTHILL 1101CB | 182951101 | FOOTHILL 1101 | 13.3962 | 149 | 0.079316 | 11.8181 | 908 | 10887.2848 | 4445.2283 | #N/A | #N/A
2049 | FRUITLAND 1141CB | 192311141 | FRUITLAND 1141 | 3.1918 | 17 | 0.079299 | 1.3481 | 909 | 10890.4766 | 4443.8802 | #N/A | #N/A
4771 | OCEANO 1104Q12 | 182601104 | OCEANO 1104 | 11.3133 | 142 | 0.079257 | 11.2544 | 910 | 10901.7898 | 4432.6258 | #N/A | #N/A
10844 | SPRING GAP 1702188426 | 162831702 | SPRING GAP 1702 | 0.0028415 | 1 | 0.078773 | 0.078773 | 911 | 10901.7927 | 4432.547 | #N/A | #N/A
1175 | HIGGINS 11044281 | 152691104 | HIGGINS 1104 | 13.3249 | 138 | 0.078646 | 10.8532 | 912 | 10915.1176 | 4421.6938 | #N/A | #N/A
9778 | HIGGINS 11097863 | 152691109 | HIGGINS 1109 | 4.2244 | 42 | 0.078616 | 3.3019 | 913 | 10919.342 | 4418.3919 | #N/A | #N/A
6230 | MONTICELLO 110193384 | 43051101 | MONTICELLO 1101 | 16.1387 | 101 | 0.078583 | 7.9369 | 914 | 10935.4808 | 4410.455 | #N/A | #N/A
9152 | MIDDLETOWN 11011314 | 43141101 | MIDDLETOWN 1101 | 0.92556 | 13 | 0.078235 | 1.0171 | 915 | 10936.4063 | 4409.438 | #N/A | #N/A
10292 | BIG MEADOWS 21012248 | 102812101 | BIG MEADOWS 2101 | 9.1535 | 28 | 0.077859 | 2.18 | 916 | 10945.5598 | 4407.2579 | #N/A | #N/A
3275 | OCEANO 1104Q10 | 182601104 | OCEANO 1104 | 23.6364 | 289 | 0.077836 | 22.4946 | 917 | 10969.1963 | 4384.7634 | #N/A | #N/A
5179 | HARTLEY 1102CB | 43211102 | HARTLEY 1102 | 3.428 | 135 | 0.077778 | 10.5 | 918 | 10972.6243 | 4374.2633 | #N/A | #N/A
8256 | MORGAN HILL 2105XR268 | 83242105 | MORGAN HILL 2105 | 7.9569 | 61 | 0.077596 | 4.7333 | 919 | 10980.5811 | 4369.53 | #N/A | #N/A
1037 | MIDDLETOWN 11021312 | 43141102 | MIDDLETOWN 1102 | 9.834 | 120 | 0.077577 | 9.3092 | 920 | 10990.4151 | 4360.2207 | #N/A | #N/A
3607 | OCEANO 1104V38 | 182601104 | OCEANO 1104 | 12.0606 | 212 | 0.077544 | 16.4392 | 921 | 11002.4757 | 4343.7815 | #N/A | #N/A
9877 | CLOVERDALE 1102307342 | 42821102 | CLOVERDALE 1102 | 0.22003 | 6 | 0.077416 | 0.46449 | 922 | 11002.6958 | 4343.317 | #N/A | #N/A
3974 | FITCH MOUNTAIN 111324550 | 42751113 | FITCH MOUNTAIN 1113 | 11.0612 | 203 | 0.077338 | 15.6996 | 923 | 11013.757 | 4327.6174 | #N/A | #N/A
962 | MIDDLETOWN 1102514 | 43141102 | MIDDLETOWN 1102 | 3.3507 | 71 | 0.077302 | 5.4884 | 924 | 11017.1076 | 4322.129 | #N/A | #N/A
10365 | CURTIS 170349746 | 163351703 | CURTIS 1703 | 0.37408 | 3 | 0.077172 | 0.23152 | 925 | 11017.4817 | 4321.8974 | #N/A | #N/A
3098 | PETALUMA C 1108630 | 42631108 | PETALUMA C 1108 | 1.6495 | 55 | 0.077168 | 4.2442 | 926 | 11019.1312 | 4317.6532 | #N/A | #N/A
6234 | SAN JUSTO 1101201311 | 183181101 | SAN JUSTO 1101 | 7.8594 | 108 | 0.077053 | 8.3218 | 927 | 11026.9906 | 4309.3315 | #N/A | #N/A
6221 | GARBERVILLE 110135706 | 192221101 | GARBERVILLE 1101 | 10.1113 | 97 | 0.076898 | 7.4591 | 928 | 11037.1019 | 4301.8723 | #N/A | #N/A
2802 | PENRYN 11072410 | 152561107 | PENRYN 1107 | 3.2618 | 96 | 0.076748 | 7.3678 | 929 | 11040.3637 | 4294.5045 | #N/A | #N/A
8295 | COTATI 110387402 | 42271103 | COTATI 1103 | 11.3572 | 42 | 0.07664 | 3.2189 | 930 | 11051.721 | 4291.2856 | #N/A | #N/A
10268 | TEJON 11023760 | 252931102 | TEJON 1102 | 6.4735 | 6 | 0.076506 | 0.45904 | 931 | 11058.1945 | 4290.8266 | #N/A | #N/A
10279 | VOLTA 1102CB | 102541102 | VOLTA 1102 | 3.2988 | 25 | 0.076253 | 1.9063 | 932 | 11061.4933 | 4288.9202 | #N/A | #N/A
9092 | FORT ROSS 11214614 | 42851121 | FORT ROSS 1121 | 12.5587 | 95 | 0.075773 | 7.1985 | 933 | 11074.052 | 4281.7218 | #N/A | #N/A
3923 | AUBERRY 110137536 | 254151101 | AUBERRY 1101 | 5.3994 | 60 | 0.075515 | 4.5309 | 934 | 11079.4514 | 4277.1909 | #N/A | #N/A
5756 | CABRILLO 11031437 | 183101103 | CABRILLO 1103 | 2.8448 | 39 | 0.075332 | 2.9379 | 935 | 11082.2963 | 4274.2529 | #N/A | #N/A
6109 | FITCH MOUNTAIN 1113583202 | 42751113 | FITCH MOUNTAIN 1113 | 4.8942 | 106 | 0.075101 | 7.9607 | 936 | 11087.1905 | 4266.2923 | #N/A | #N/A
4163 | WILLITS 1103538 | 42661103 | WILLITS 1103 | 6.3249 | 48 | 0.074937 | 3.597 | 937 | 11093.5154 | 4262.6953 | #N/A | #N/A
9780 | SONOMA 1107854266 | 42721107 | SONOMA 1107 | 0.19976 | 6 | 0.074827 | 0.44896 | 938 | 11093.7152 | 4262.2463 | #N/A | #N/A
260 | BRUNSWICK 11067099 | 152481106 | BRUNSWICK 1106 | 7.7312 | 83 | 0.074794 | 6.2079 | 939 | 11101.4464 | 4256.0384 | #N/A | #N/A
3084 | GEYSERVILLE 1102274 | 42891102 | GEYSERVILLE 1102 | 6.4625 | 173 | 0.074787 | 12.9382 | 940 | 11107.9089 | 4243.1002 | #N/A | #N/A
6342 | MADISON 21011606 | 63172101 | MADISON 2101 | 0.15808 | 280 | 0.074511 | 20.863 | 941 | 11108.067 | 4222.2372 | #N/A | #N/A
10492 | DRUM 1101CB | 152321101 | DRUM 1101 | 2.1651 | 16 | 0.074456 | 1.1913 | 942 | 11110.232 | 4221.0459 | #N/A | #N/A
874 | RISING RIVER 1101CB | 103551101 | RISING RIVER 1101 | 9.9169 | 121 | 0.074106 | 8.9669 | 943 | 11120.1489 | 4212.0791 | #N/A | #N/A
8386 | PEORIA 1705999 | 163781705 | PEORIA 1705 | 2.3089 | 22 | 0.074075 | 1.6297 | 944 | 11122.4578 | 4210.4494 | #N/A | #N/A
7502 | FITCH MOUNTAIN 11136751 | 42751113 | FITCH MOUNTAIN 1113 | 22.6749 | 139 | 0.073927 | 10.2759 | 945 | 11145.1327 | 4200.1735 | 4200.1735 | #N/A
5338 | SAN JOAQUIN #3 1102CB | 252531102 | SAN JOAQUIN #3 1102 | 9.6963 | 97 | 0.073848 | 7.1632 | 946 | 11154.8291 | 4193.0103 | #N/A | #N/A
7052 | CALISTOGA 1101134232 | 42711101 | CALISTOGA 1101 | 1.6277 | 89 | 0.0737 | 6.5593 | 947 | 11156.4567 | 4186.451 | #N/A | #N/A
10249 | SILVERADO 2102CB | 43432102 | SILVERADO 2102 | 0.59218 | 22 | 0.073682 | 1.621 | 948 | 11157.0489 | 4184.8299 | #N/A | #N/A
6791 | CABRILLO 1104Y24 | 183101104 | CABRILLO 1104 | 19.1707 | 91 | 0.073569 | 6.6947 | 949 | 11176.2196 | 4178.1352 | #N/A | #N/A
3606 | HORSESHOE 1101CB | 152571101 | HORSESHOE 1101 | 0.35258 | 55 | 0.073561 | 4.0458 | 950 | 11176.5721 | 4174.0894 | #N/A | #N/A
2673 | PUEBLO 2102792 | 43292102 | PUEBLO 2102 | 19.3407 | 180 | 0.073389 | 13.2101 | 951 | 11195.9128 | 4160.8793 | 4160.8793 | #N/A
4637 | SAN LUIS OBISPO 1104V40 | 182631104 | SAN LUIS OBISPO 1104 | 14.7 | 194 | 0.073389 | 14.2374 | 952 | 11210.6128 | 4146.6419 | #N/A | #N/A
2241 | CURTIS 170247488 | 163351702 | CURTIS 1702 | 19.011 | 207 | 0.07338 | 15.1897 | 953 | 11229.6238 | 4131.4522 | #N/A | #N/A
9651 | PURISIMA 1101Y44 | 182971101 | PURISIMA 1101 | 10.4077 | 45 | 0.073295 | 3.2983 | 954 | 11240.0315 | 4128.1539 | #N/A | #N/A
1008 | TEMPLETON 2113A70 | 183052113 | TEMPLETON 2113 | 24.7135 | 659 | 0.073157 | 48.2106 | 955 | 11264.745 | 4079.9434 | #N/A | #N/A
3782 | AUBERRY 1101R322 | 254151101 | AUBERRY 1101 | 7.6672 | 44 | 0.073065 | 3.2149 | 956 | 11272.4122 | 4076.7285 | #N/A | #N/A
700 | MERCED FALLS 11029460 | 252811102 | MERCED FALLS 1102 | 11.1412 | 91 | 0.073014 | 6.6443 | 957 | 11283.5534 | 4070.0842 | #N/A | #N/A
1286 | CURTIS 170384944 | 163351703 | CURTIS 1703 | 58.219 | 439 | 0.072725 | 31.9262 | 958 | 11341.7723 | 4038.158 | #N/A | #N/A
8476 | ALTO 1124810594 | 42031124 | ALTO 1124 | 0.55899 | 6 | 0.072684 | 0.4361 | 959 | 11342.3313 | 4037.7219 | #N/A | #N/A
1350 | PENRYN 1107CB | 152561107 | PENRYN 1107 | 5.429 | 200 | 0.072647 | 14.5295 | 960 | 11347.7603 | 4023.1925 | #N/A | #N/A
10196 | SANTA YNEZ 1101980192 | 182721101 | SANTA YNEZ 1101 | 3.8401 | 19 | 0.072592 | 1.3793 | 961 | 11351.6004 | 4021.8132 | #N/A | #N/A
4126 | VACAVILLE 1104CB | 63601104 | VACAVILLE 1104 | 0.43299 | 36 | 0.07222 | 2.5999 | 962 | 11352.0333 | 4019.2133 | #N/A | #N/A
6142 | JOLON 1103CB | 182981103 | JOLON 1103 | 13.1598 | 91 | 0.072102 | 6.5613 | 963 | 11365.1932 | 4012.652 | #N/A | #N/A
4505 | LOW GAP 11014086 | 192411101 | LOW GAP 1101 | 11.4942 | 66 | 0.072098 | 4.7585 | 964 | 11376.6874 | 4007.8935 | #N/A | #N/A
5220 | COTATI 1103132 | 42271103 | COTATI 1103 | 25.2965 | 184 | 0.071994 | 13.2468 | 965 | 11401.9839 | 3994.6467 | #N/A | #N/A
2886 | VOLTA 11011596 | 102541101 | VOLTA 1101 | 21.8176 | 132 | 0.071922 | 9.4937 | 966 | 11423.8015 | 3985.1529 | #N/A | #N/A
7748 | PEORIA 170413490 | 163781704 | PEORIA 1704 | 4.2731 | 49 | 0.071878 | 3.522 | 967 | 11428.0746 | 3981.6309 | #N/A | #N/A
1885 | OREGON TRAIL 110249144 | 103521102 | OREGON TRAIL 1102 | 18.3805 | 169 | 0.071512 | 12.0855 | 968 | 11446.4551 | 3969.5454 | #N/A | #N/A
3676 | COTTONWOOD 1101CB | 102931101 | COTTONWOOD 1101 | 0.11437 | 188 | 0.0715 | 13.442 | 969 | 11446.5694 | 3956.1035 | #N/A | #N/A
7714 | FROGTOWN 17027134 | 163451702 | FROGTOWN 1702 | 20.2101 | 172 | 0.071297 | 12.2631 | 970 | 11466.7796 | 3943.8404 | #N/A | #N/A
4319 | MESA 11016111 | 182821101 | MESA 1101 | 24.2535 | 202 | 0.071153 | 14.3729 | 971 | 11491.0331 | 3929.4675 | #N/A | #N/A
5571 | CLEAR LAKE 1101740076 | 42141101 | CLEAR LAKE 1101 | 0.39302 | 106 | 0.071071 | 7.5335 | 972 | 11491.4261 | 3921.934 | #N/A | #N/A
9268 | OLETA 1102799924 | 163541102 | OLETA 1102 | 0.38634 | 4 | 0.070818 | 0.28327 | 973 | 11491.8125 | 3921.6507 | #N/A | #N/A
1141 | BELL 1109724884 | 152701109 | BELL 1109 | 14.0392 | 167 | 0.070791 | 11.822 | 974 | 11505.8517 | 3909.8287 | #N/A | #N/A
9406 | EDENVALE 2107469810 | 82952107 | EDENVALE 2107 | 2.153 | 14 | 0.070672 | 0.98941 | 975 | 11508.0047 | 3908.8393 | #N/A | #N/A
2788 | WYANDOTTE 1110980944 | 102911110 | WYANDOTTE 1110 | 10.4309 | 198 | 0.070566 | 13.9721 | 976 | 11518.4355 | 3894.8671 | #N/A | #N/A
3339 | JESSUP 110276068 | 103441102 | JESSUP 1102 | 17.1802 | 232 | 0.070348 | 16.3207 | 977 | 11535.6157 | 3878.5465 | #N/A | #N/A
6626 | CLAY 1101CB | 163341101 | CLAY 1101 | 0.56812 | 33 | 0.070136 | 2.3145 | 978 | 11536.1838 | 3876.232 | #N/A | #N/A
9158 | COVELO 1101306476 | 43061101 | COVELO 1101 | 1.9306 | 49 | 0.069853 | 3.4228 | 979 | 11538.1145 | 3872.8092 | #N/A | #N/A
5752 | MONTICELLO 110165454 | 43051101 | MONTICELLO 1101 | 1.3526 | 23 | 0.069594 | 1.6007 | 980 | 11539.4671 | 3871.2085 | #N/A | #N/A
2727 | OREGON TRAIL 11031500 | 103521103 | OREGON TRAIL 1103 | 26.0289 | 261 | 0.069495 | 18.1383 | 981 | 11565.4959 | 3853.0702 | #N/A | #N/A
10741 | HALF MOON BAY 11038920 | 24101103 | HALF MOON BAY 1103 | 0.098275 | 2 | 0.069477 | 0.13895 | 982 | 11565.5942 | 3852.9313 | #N/A | #N/A
2684 | BEAR VALLEY 210110000 | 252192101 | BEAR VALLEY 2101 | 29.2711 | 230 | 0.069198 | 15.9156 | 983 | 11594.8653 | 3837.0157 | #N/A | #N/A
1190 | OCEANO 1104V36 | 182601104 | OCEANO 1104 | 11.205 | 150 | 0.069118 | 10.3677 | 984 | 11606.0703 | 3826.648 | #N/A | #N/A
9260 | DIAMOND SPRINGS 110777086 | 152261107 | DIAMOND SPRINGS 1107 | 2.717 | 47 | 0.068998 | 3.2429 | 985 | 11608.7873 | 3823.4051 | #N/A | #N/A
87 | CORNING 110185152 | 103331101 | CORNING 1101 | 23.2021 | 279 | 0.068983 | 19.2463 | 986 | 11631.9894 | 3804.1589 | #N/A | #N/A
2893 | UKIAH 1114544 | 42771114 | UKIAH 1114 | 0.48867 | 98 | 0.068781 | 6.7406 | 987 | 11632.478 | 3797.4183 | #N/A | #N/A
69 | BROWNS VALLEY 110197188 | 152921101 | BROWNS VALLEY 1101 | 6.7867 | 71 | 0.068613 | 4.8715 | 988 | 11639.2647 | 3792.5468 | #N/A | #N/A
1342 | AUBERRY 1101R2838 | 254151101 | AUBERRY 1101 | 20.4455 | 210 | 0.068544 | 14.3942 | 989 | 11659.7102 | 3778.1526 | #N/A | #N/A
9647 | GARCIA 0401CB | 43040401 | GARCIA 0401 | 0.029031 | 1 | 0.068469 | 0.068469 | 990 | 11659.7392 | 3778.0841 | #N/A | #N/A
2407 | FROGTOWN 1702835115 | 163451702 | FROGTOWN 1702 | 18.143 | 191 | 0.068398 | 13.0639 | 991 | 11677.8822 | 3765.0202 | #N/A | #N/A
3939 | ZACA 1101Y70 | 182681101 | ZACA 1101 | 6.7366 | 61 | 0.068291 | 4.1658 | 992 | 11684.6188 | 3760.8544 | #N/A | #N/A
3966 | SAN BENITO 2101295566 | 182742101 | SAN BENITO 2101 | 0.46708 | 18 | 0.068263 | 1.2287 | 993 | 11685.0859 | 3759.6257 | #N/A | #N/A
1800 | BANGOR 11011804 | 103191101 | BANGOR 1101 | 42.8988 | 394 | 0.068197 | 26.8697 | 994 | 11727.9846 | 3732.756 | #N/A | #N/A
1078 | BIG MEADOWS 21012260 | 102812101 | BIG MEADOWS 2101 | 15.795 | 185 | 0.067786 | 12.5404 | 995 | 11743.7797 | 3720.2156 | #N/A | #N/A
8083 | ANDERSON 1101583708 | 103261101 | ANDERSON 1101 | 0.62857 | 11 | 0.067762 | 0.74538 | 996 | 11744.4082 | 3719.4702 | #N/A | #N/A
6638 | SAN RAMON 2117CB | 14232117 | SAN RAMON 2117 | 0.68297 | 23 | 0.067722 | 1.5576 | 997 | 11745.0912 | 3717.9126 | #N/A | #N/A
7538 | CABRILLO 1103Y46 | 183101103 | CABRILLO 1103 | 31.4816 | 277 | 0.067522 | 18.7037 | 998 | 11776.5728 | 3699.2089 | #N/A | #N/A
4175 | MARTELL 1101CB | 163011101 | MARTELL 1101 | 5.879 | 171 | 0.067405 | 11.5263 | 999 | 11782.4518 | 3687.6826 | 3687.6826 | #N/A
9619 | PETALUMA C 1108456397 | 42631108 | PETALUMA C 1108 | 1.3916 | 19 | 0.067328 | 1.2792 | 1000 | 11783.8434 | 3686.4034 | #N/A | #N/A
3701 | FRENCH GULCH 1101CB | 103381101 | FRENCH GULCH 1101 | 2.298 | 32 | 0.067293 | 2.1534 | 1001 | 11786.1414 | 3684.25 | #N/A | #N/A
4093 | RED BLUFF 1105146070 | 103541105 | RED BLUFF 1105 | 12.7281 | 167 | 0.067012 | 11.191 | 1002 | 11798.8695 | 3673.059 | #N/A | #N/A
1562 | LAYTONVILLE 110264908 | 42681102 | LAYTONVILLE 1102 | 3.877 | 84 | 0.066995 | 5.6276 | 1003 | 11802.7465 | 3667.4314 | #N/A | #N/A
7452 | SAN RAMON 210853732 | 14232108 | SAN RAMON 2108 | 7.7954 | 77 | 0.066862 | 5.1484 | 1004 | 11810.5419 | 3662.283 | #N/A | #N/A
509 | CALISTOGA 110143924 | 42711101 | CALISTOGA 1101 | 7.7836 | 107 | 0.066852 | 7.1532 | 1005 | 11818.3255 | 3655.1298 | #N/A | #N/A
2808 | PASO ROBLES 1104P02 | 182611104 | PASO ROBLES 1104 | 0.32009 | 93 | 0.06682 | 6.2143 | 1006 | 11818.6456 | 3648.9155 | #N/A | #N/A
6977 | CLOVERDALE 1102172096 | 42821102 | CLOVERDALE 1102 | 0.26446 | 12 | 0.06657 | 0.79884 | 1007 | 11818.9101 | 3648.1167 | #N/A | #N/A
6400 | PHILO 1102CB | 42601102 | PHILO 1102 | 7.699 | 131 | 0.06648 | 8.7089 | 1008 | 11826.6091 | 3639.4078 | #N/A | #N/A
1390 | CURTIS 170539256 | 163351705 | CURTIS 1705 | 26.4643 | 287 | 0.066296 | 19.0271 | 1009 | 11853.0734 | 3620.3808 | #N/A | #N/A
9080 | SUMMIT 110249484 | 152591102 | SUMMIT 1102 | 2.646 | 27 | 0.06627 | 1.7893 | 1010 | 11855.7194 | 3618.5915 | #N/A | #N/A
493 | BRUNSWICK 11102664 | 152481110 | BRUNSWICK 1110 | 8.0242 | 132 | 0.066185 | 8.7364 | 1011 | 11863.7436 | 3609.8551 | #N/A | #N/A
6828 | SILVERADO 210298998 | 43432102 | SILVERADO 2102 | 0.073401 | 136 | 0.066014 | 8.9779 | 1012 | 11863.817 | 3600.8772 | #N/A | #N/A
828 | ATASCADERO 1103A18 | 182541103 | ATASCADERO 1103 | 8.8187 | 188 | 0.065994 | 12.4068 | 1013 | 11872.6357 | 3588.4703 | #N/A | #N/A
7881 | CALISTOGA 1102141073 | 42711102 | CALISTOGA 1102 | 1.2408 | 27 | 0.065722 | 1.7745 | 1014 | 11873.8765 | 3586.6958 | #N/A | #N/A
5591 | CURTIS 17029220 | 163351702 | CURTIS 1702 | 11.0031 | 123 | 0.065661 | 8.0763 | 1015 | 11884.8796 | 3578.6196 | #N/A | #N/A
1187 | PENRYN 11051342 | 152561105 | PENRYN 1105 | 20.7279 | 440 | 0.065366 | 28.7609 | 1016 | 11905.6075 | 3549.8587 | #N/A | #N/A
8143 | CLAYTON 2215W531R | 12022215 | CLAYTON 2215 | 6.4908 | 100 | 0.065356 | 6.5356 | 1017 | 11912.0983 | 3543.3231 | #N/A | #N/A
2291 | SHINGLE SPRINGS 210913322 | 153652109 | SHINGLE SPRINGS 2109 | 41.4032 | 490 | 0.065331 | 32.0124 | 1018 | 11953.5015 | 3511.3107 | #N/A | #N/A
2286 | BEAR VALLEY 210521160 | 252192105 | BEAR VALLEY 2105 | 23.7846 | 194 | 0.065187 | 12.6462 | 1019 | 11977.2861 | 3498.6645 | #N/A | #N/A
9841 | MESA 1103126697 | 182821103 | MESA 1103 | 1.0204 | 10 | 0.065062 | 0.65062 | 1020 | 11978.3065 | 3498.0139 | #N/A | #N/A
9670 | FRENCH GULCH 1102CB | 103381102 | FRENCH GULCH 1102 | 1.6961 | 12 | 0.06474 | 0.77689 | 1021 | 11980.0026 | 3497.237 | #N/A | #N/A
2589 | FORT ROSS 1121124 | 42851121 | FORT ROSS 1121 | 18.4975 | 99 | 0.064597 | 6.3951 | 1022 | 11998.5001 | 3490.8419 | #N/A | #N/A
2518 | OCEANO 1104Q08 | 182601104 | OCEANO 1104 | 12.4187 | 148 | 0.064559 | 9.5547 | 1023 | 12010.9188 | 3481.2872 | #N/A | #N/A
10030 | MC ARTHUR 1102542920 | 103491102 | MC ARTHUR 1102 | 1.2647 | 10 | 0.064427 | 0.64427 | 1024 | 12012.1834 | 3480.6429 | #N/A | #N/A
4185 | PASO ROBLES 1104R12 | 182611104 | PASO ROBLES 1104 | 32.8131 | 278 | 0.064341 | 17.8868 | 1025 | 12044.9965 | 3462.7561 | #N/A | #N/A
7956 | JESSUP 11011993 | 103441101 | JESSUP 1101 | 2.7783 | 39 | 0.064212 | 2.5043 | 1026 | 12047.7749 | 3460.2518 | #N/A | #N/A
10640 | CALISTOGA 110266730 | 42711102 | CALISTOGA 1102 | 1.0586 | 6 | 0.064035 | 0.38421 | 1027 | 12048.8335 | 3459.8676 | #N/A | #N/A
9262 | LAKEVILLE 110287432 | 43371102 | LAKEVILLE 1102 | 9.7629 | 81 | 0.063901 | 5.176 | 1028 | 12058.5964 | 3454.6916 | #N/A | #N/A
6678 | MIDDLETOWN 11011325 | 43141101 | MIDDLETOWN 1101 | 8.5951 | 80 | 0.063613 | 5.0891 | 1029 | 12067.1915 | 3449.6025 | #N/A | #N/A
5737 | UKIAH 11151216 | 42771115 | UKIAH 1115 | 13.4422 | 182 | 0.063522 | 11.561 | 1030 | 12080.6337 | 3438.0415 | #N/A | #N/A
1518 | DIAMOND SPRINGS 110518935 | 152261105 | DIAMOND SPRINGS 1105 | 6.696 | 76 | 0.063224 | 4.805 | 1031 | 12087.3297 | 3433.2365 | #N/A | #N/A
8962 | TEMPLETON 2110N30 | 183052110 | TEMPLETON 2110 | 20.3656 | 120 | 0.063152 | 7.5782 | 1032 | 12107.6954 | 3425.6583 | #N/A | #N/A
5800 | CLARK ROAD 11022070 | 103091102 | CLARK ROAD 1102 | 9.1899 | 72 | 0.063106 | 4.5436 | 1033 | 12116.8853 | 3421.1147 | #N/A | #N/A
1728 | TEMPLETON 2112116402 | 183052112 | TEMPLETON 2112 | 2.3685 | 64 | 0.062979 | 4.0307 | 1034 | 12119.2538 | 3417.084 | #N/A | #N/A
727 | APPLE HILL 2102186912 | 153662102 | APPLE HILL 2102 | 58.5914 | 606 | 0.06292 | 38.1293 | 1035 | 12177.8452 | 3378.9548 | #N/A | #N/A
7181 | BEAR VALLEY 21054170 | 252192105 | BEAR VALLEY 2105 | 9.5212 | 45 | 0.062779 | 2.8251 | 1036 | 12187.3664 | 3376.1297 | #N/A | #N/A
8856 | GARBERVILLE 11028189 | 192221102 | GARBERVILLE 1102 | 1.0475 | 11 | 0.062553 | 0.68809 | 1037 | 12188.4139 | 3375.4416 | #N/A | #N/A
1917 | PANORAMA 1101CB | 103461101 | PANORAMA 1101 | 1.1366 | 175 | 0.062374 | 10.9155 | 1038 | 12189.5506 | 3364.5261 | #N/A | #N/A
9789 | TASSAJARA 2106203380 | 14662106 | TASSAJARA 2106 | 0.50317 | 26 | 0.062335 | 1.6207 | 1039 | 12190.0537 | 3362.9054 | #N/A | #N/A
8449 | VACAVILLE 111112342 | 63601111 | VACAVILLE 1111 | 0.21883 | 16 | 0.062293 | 0.99668 | 1040 | 12190.2726 | 3361.9087 | #N/A | #N/A
3572 | OLETA 110113478 | 163541101 | OLETA 1101 | 12.3348 | 169 | 0.062159 | 10.5049 | 1041 | 12202.6073 | 3351.4038 | #N/A | #N/A
1028 | LOW GAP 11012094 | 192411101 | LOW GAP 1101 | 15.6921 | 139 | 0.062103 | 8.6323 | 1042 | 12218.2995 | 3342.7715 | #N/A | #N/A
3105 | NOTRE DAME 11042028 | 102041104 | NOTRE DAME 1104 | 10.8376 | 86 | 0.062015 | 5.3333 | 1043 | 12229.1371 | 3337.4382 | #N/A | #N/A
2667 | FROGTOWN 170212282 | 163451702 | FROGTOWN 1702 | 36.3469 | 261 | 0.061928 | 16.1631 | 1044 | 12265.4839 | 3321.2751 | #N/A | #N/A
7606 | NOTRE DAME 11042537 | 102041104 | NOTRE DAME 1104 | 4.9907 | 37 | 0.061762 | 2.2852 | 1045 | 12270.4747 | 3318.9899 | #N/A | #N/A
2093 | ATASCADERO 1103A46 | 182541103 | ATASCADERO 1103 | 0.39348 | 94 | 0.06175 | 5.8045 | 1046 | 12270.8682 | 3313.1854 | #N/A | #N/A
7485 | SHINGLE SPRINGS 210551738 | 153652105 | SHINGLE SPRINGS 2105 | 0.016582 | 19 | 0.061564 | 1.1697 | 1047 | 12270.8847 | 3312.0157 | #N/A | #N/A
284 | PERRY 1101V78 | 183071101 | PERRY 1101 | 29.5036 | 164 | 0.061453 | 10.0783 | 1048 | 12300.3884 | 3301.9374 | #N/A | #N/A
10468 | CALPINE 1144962 | 48011144 | CALPINE 1144 | 0.039381 | 1 | 0.061428 | 0.061428 | 1049 | 12300.4278 | 3301.876 | #N/A | #N/A
8597 | ORO FINO 1102127563 | 103031102 | ORO FINO 1102 | 6.9024 | 63 | 0.061336 | 3.8642 | 1050 | 12307.3301 | 3298.0118 | #N/A | #N/A
6425 | MADISON 2101351038 | 63172101 | MADISON 2101 | 1.6542 | 130 | 0.061316 | 7.971 | 1051 | 12308.9844 | 3290.0408 | #N/A | #N/A
5524 | JESSUP 11011496 | 103441101 | JESSUP 1101 | 14.6221 | 201 | 0.06121 | 12.3032 | 1052 | 12323.6065 | 3277.7376 | #N/A | #N/A
10127 | SPAULDING 1101CB | 152251101 | SPAULDING 1101 | 0.035269 | 1 | 0.061207 | 0.061207 | 1053 | 12323.6417 | 3277.6764 | #N/A | #N/A
4318 | HIGGINS 11102408 | 152691110 | HIGGINS 1110 | 11.569 | 124 | 0.060864 | 7.5471 | 1054 | 12335.2108 | 3270.1292 | #N/A | #N/A
7906 | PIT NO 7 1101CB | 103501101 | PIT NO 7 1101 | 2.7084 | 3 | 0.060819 | 0.18246 | 1055 | 12337.9192 | 3269.9468 | #N/A | #N/A
7035 | SYCAMORE CREEK 1111CB | 102971111 | SYCAMORE CREEK 1111 | 0.48337 | 85 | 0.060715 | 5.1608 | 1056 | 12338.4026 | 3264.786 | #N/A | #N/A
4688 | UPPER LAKE 1101452 | 42871101 | UPPER LAKE 1101 | 5.0523 | 207 | 0.060708 | 12.5666 | 1057 | 12343.4548 | 3252.2194 | #N/A | #N/A
7853 | CLOVERDALE 1102670 | 42821102 | CLOVERDALE 1102 | 0.36491 | 43 | 0.06056 | 2.6041 | 1058 | 12343.8197 | 3249.6153 | #N/A | #N/A
9980 | BRIDGEVILLE 1101CB | 192461101 | BRIDGEVILLE 1101 | 8.5166 | 51 | 0.060495 | 3.0852 | 1059 | 12352.3363 | 3246.53 | #N/A | #N/A
3075 | REDBUD 11022013 | 43191102 | REDBUD 1102 | 0.14852 | 51 | 0.06048 | 3.0845 | 1060 | 12352.4848 | 3243.4455 | #N/A | #N/A
377 | FROGTOWN 1702L5407 | 163451702 | FROGTOWN 1702 | 18.279 | 153 | 0.060463 | 9.2508 | 1061 | 12370.7638 | 3234.1948 | #N/A | #N/A
599 | CURTIS 170356972 | 163351703 | CURTIS 1703 | 8.5712 | 57 | 0.060186 | 3.4306 | 1062 | 12379.335 | 3230.7642 | #N/A | #N/A
9546 | COTATI 1102CB | 42271102 | COTATI 1102 | 1.805 | 19 | 0.05984 | 1.137 | 1063 | 12381.1401 | 3229.6272 | #N/A | #N/A
9754 | CALPELLA 1102708161 | 43411102 | CALPELLA 1102 | 1.0037 | 12 | 0.059606 | 0.71527 | 1064 | 12382.1438 | 3228.9119 | #N/A | #N/A
7941 | FRUITLAND 11426064 | 192311142 | FRUITLAND 1142 | 6.6979 | 66 | 0.059515 | 3.928 | 1065 | 12388.8417 | 3224.9839 | #N/A | #N/A
1172 | CORRAL 110336680 | 162991103 | CORRAL 1103 | 9.357 | 265 | 0.059472 | 15.7601 | 1066 | 12398.1987 | 3209.2239 | #N/A | #N/A
7127 | SONOMA 1107844168 | 42721107 | SONOMA 1107 | 4.5426 | 100 | 0.059437 | 5.9437 | 1067 | 12402.7413 | 3203.2802 | #N/A | #N/A
2372 | GRASS VALLEY 11032110 | 152031103 | GRASS VALLEY 1103 | 19.7627 | 224 | 0.059423 | 13.3106 | 1068 | 12422.504 | 3189.9695 | #N/A | #N/A
2173 | PUEBLO 1105696 | 43291105 | PUEBLO 1105 | 3.7526 | 79 | 0.059025 | 4.663 | 1069 | 12426.2566 | 3185.3066 | #N/A | #N/A
2604 | JESSUP 11031540 | 103441103 | JESSUP 1103 | 0.15935 | 157 | 0.058865 | 9.2418 | 1070 | 12426.4159 | 3176.0648 | #N/A | #N/A
8024 | PENRYN 11072708 | 152561107 | PENRYN 1107 | 9.3816 | 124 | 0.058775 | 7.2881 | 1071 | 12435.7975 | 3168.7766 | #N/A | #N/A
660 | GABILAN 1101460414 | 182331101 | GABILAN 1101 | 5.3792 | 38 | 0.058719 | 2.2313 | 1072 | 12441.1768 | 3166.5453 | #N/A | #N/A
2838 | MENDOCINO 110148750 | 42951101 | MENDOCINO 1101 | 17.9237 | 165 | 0.058621 | 9.6724 | 1073 | 12459.1005 | 3156.8729 | #N/A | #N/A
5642 | ALHAMBRA 110582622 | 14101105 | ALHAMBRA 1105 | 25.9188 | 254 | 0.058508 | 14.8609 | 1074 | 12485.0193 | 3142.012 | #N/A | #N/A
5965 | JOLON 1102CB | 182981102 | JOLON 1102 | 23.5798 | 181 | 0.058399 | 10.5701 | 1075 | 12508.5991 | 3131.4419 | #N/A | #N/A
5646 | SANTA YNEZ 1104512912 | 182721104 | SANTA YNEZ 1104 | 0.89193 | 23 | 0.058383 | 1.3428 | 1076 | 12509.491 | 3130.099 | #N/A | #N/A
1584 | COLUMBIA HILL 1101CB | 152471101 | COLUMBIA HILL 1101 | 39.3563 | 375 | 0.058367 | 21.8875 | 1077 | 12548.8473 | 3108.2116 | #N/A | #N/A
8255 | CRESCENT MILLS 21012562 | 103132101 | CRESCENT MILLS 2101 | 19.3429 | 222 | 0.057915 | 12.8572 | 1078 | 12568.1902 | 3095.3543 | #N/A | #N/A
2533 | MOLINO 1101338 | 42571101 | MOLINO 1101 | 7.7669 | 176 | 0.05791 | 10.1921 | 1079 | 12575.9571 | 3085.1622 | #N/A | #N/A
9899 | LLAGAS 21014523 | 83182101 | LLAGAS 2101 | 0.91427 | 28 | 0.057806 | 1.6186 | 1080 | 12576.8714 | 3083.5436 | #N/A | #N/A
10017 | PASO ROBLES 1107289947 | 182611107 | PASO ROBLES 1107 | 0.27821 | 21 | 0.057658 | 1.2108 | 1081 | 12577.1496 | 3082.3328 | #N/A | #N/A
451 | CALISTOGA 11011087 | 42711101 | CALISTOGA 1101 | 1.9622 | 22 | 0.05764 | 1.2681 | 1082 | 12579.1117 | 3081.0648 | #N/A | #N/A
90 | TYLER 1105816852 | 103571105 | TYLER 1105 | 12.7692 | 423 | 0.057549 | 24.3431 | 1083 | 12591.881 | 3056.7217 | #N/A | #N/A
67 | WOODACRE 1102CB | 43021102 | WOODACRE 1102 | 12.4834 | 141 | 0.057543 | 8.1136 | 1084 | 12604.3644 | 3048.6081 | #N/A | #N/A
3103 | JOLON 11027070 | 182981102 | JOLON 1102 | 6.4059 | 132 | 0.057494 | 7.5892 | 1085 | 12610.7703 | 3041.0189 | #N/A | #N/A
6894 | DESCHUTES 11011654 | 103351101 | DESCHUTES 1101 | 17.5396 | 168 | 0.057486 | 9.6576 | 1086 | 12628.3099 | 3031.3613 | #N/A | #N/A
1819 | ALTO 11243745 | 42031124 | ALTO 1124 | 4.5042 | 52 | 0.057415 | 2.9856 | 1087 | 12632.8141 | 3028.3757 | #N/A | #N/A
1989 | ELECTRA 1101CB | 162161101 | ELECTRA 1101 | 31.6879 | 293 | 0.05741 | 16.8213 | 1088 | 12664.502 | 3011.5544 | #N/A | #N/A
994 | BUTTE 1105751990 | 103081105 | BUTTE 1105 | 24.51 | 243 | 0.057382 | 13.9439 | 1089 | 12689.012 | 2997.6106 | #N/A | #N/A
7429 | MOUNTAIN QUARRIES 210151584 | 152282101 | MOUNTAIN QUARRIES 2101 | 21.7785 | 224 | 0.057318 | 12.8393 | 1090 | 12710.7905 | 2984.7712 | #N/A | #N/A
7628 | WISE 11011404 | 152271101 | WISE 1101 | 1.4934 | 47 | 0.057199 | 2.6884 | 1091 | 12712.2839 | 2982.0829 | #N/A | #N/A
7386 | SAN RAMON 2108CB | 14232108 | SAN RAMON 2108 | 8.709 | 102 | 0.057183 | 5.8326 | 1092 | 12720.9928 | 2976.2502 | #N/A | #N/A
9327 | CALISTOGA 110189150 | 42711101 | CALISTOGA 1101 | 9.5291 | 88 | 0.057148 | 5.029 | 1093 | 12730.5219 | 2971.2212 | #N/A | #N/A
4436 | SAN RAMON 2119CB | 14232119 | SAN RAMON 2119 | 0.73831 | 21 | 0.057097 | 1.199 | 1094 | 12731.2602 | 2970.0222 | #N/A | #N/A
4471 | ELECTRA 11024756 | 162161102 | ELECTRA 1102 | 9.4092 | 95 | 0.057032 | 5.4181 | 1095 | 12740.6694 | 2964.6041 | #N/A | #N/A
10516 | GARBERVILLE 11022124 | 192221102 | GARBERVILLE 1102 | 3.1238 | 6 | 0.057006 | 0.34203 | 1096 | 12743.7932 | 2964.2621 | #N/A | #N/A
10428 | ANNAPOLIS 1101CB | 42861101 | ANNAPOLIS 1101 | 0.658 | 7 | 0.057005 | 0.39904 | 1097 | 12744.4512 | 2963.863 | #N/A | #N/A
5436 | TEMPLETON 2110901690 | 183052110 | TEMPLETON 2110 | 37.3078 | 306 | 0.056927 | 17.4196 | 1098 | 12781.759 | 2946.4434 | #N/A | #N/A
1208 | HOPLAND 1101CB | 42251101 | HOPLAND 1101 | 14.6549 | 190 | 0.056867 | 10.8047 | 1099 | 12796.4139 | 2935.6387 | #N/A | #N/A
582 | SWIFT 2110853720 | 83392110 | SWIFT 2110 | 31.2472 | 140 | 0.056625 | 7.9275 | 1100 | 12827.6612 | 2927.7112 | #N/A | #N/A
6471 | SALMON CREEK 110137368 | 43161101 | SALMON CREEK 1101 | 6.0824 | 48 | 0.056596 | 2.7166 | 1101 | 12833.7436 | 2924.9946 | #N/A | #N/A
7036 | WOODACRE 1101CB | 43021101 | WOODACRE 1101 | 2.7686 | 35 | 0.056508 | 1.9778 | 1102 | 12836.5121 | 2923.0168 | #N/A | #N/A
9354 | FRUITLAND 114137410 | 192311141 | FRUITLAND 1141 | 5.2288 | 42 | 0.056472 | 2.3718 | 1103 | 12841.7409 | 2920.645 | #N/A | #N/A
8408 | GOLDTREE 1105CB | 182581105 | GOLDTREE 1105 | 7.4012 | 76 | 0.056447 | 4.29 | 1104 | 12849.1421 | 2916.355 | #N/A | #N/A
1036 | FRUITLAND 1142CB | 192311142 | FRUITLAND 1142 | 10.504 | 116 | 0.056321 | 6.5332 | 1105 | 12859.6461 | 2909.8218 | #N/A | #N/A
5437 | FITCH MOUNTAIN 1113775992 | 42751113 | FITCH MOUNTAIN 1113 | 2.1016 | 34 | 0.056251 | 1.9125 | 1106 | 12861.7477 | 2907.9093 | #N/A | #N/A
8868 | SALMON CREEK 1101461703 | 43161101 | SALMON CREEK 1101 | 0.87921 | 8 | 0.05614 | 0.44912 | 1107 | 12862.627 | 2907.4602 | #N/A | #N/A
1882 | SHINGLE SPRINGS 211051800 | 153652110 | SHINGLE SPRINGS 2110 | 9.1961 | 128 | 0.05603 | 7.1719 | 1108 | 12871.8231 | 2900.2883 | #N/A | #N/A
3611 | SANTA MARIA 1108M80 | 182671108 | SANTA MARIA 1108 | 58.257 | 397 | 0.055911 | 22.1966 | 1109 | 12930.0801 | 2878.0917 | #N/A | #N/A
6376 | MONTE RIO 11131991 | 42811113 | MONTE RIO 1113 | 7.1257 | 51 | 0.055786 | 2.8451 | 1110 | 12937.2058 | 2875.2466 | #N/A | #N/A
1111 | PEORIA 17056697 | 163781705 | PEORIA 1705 | 4.1376 | 46 | 0.055767 | 2.5653 | 1111 | 12941.3434 | 2872.6813 | #N/A | #N/A
3012 | RACETRACK 170311270 | 163761703 | RACETRACK 1703 | 12.6241 | 123 | 0.055685 | 6.8493 | 1112 | 12953.9675 | 2865.832 | #N/A | #N/A
722 | MONTE RIO 11125040 | 42811112 | MONTE RIO 1112 | 4.0445 | 46 | 0.055628 | 2.5589 | 1113 | 12958.0119 | 2863.2731 | #N/A | #N/A
9716 | WINDSOR 1103171410 | 43501103 | WINDSOR 1103 | 1.3785 | 40 | 0.055603 | 2.2241 | 1114 | 12959.3904 | 2861.049 | #N/A | #N/A
15 | MENDOCINO 1101450 | 42951101 | MENDOCINO 1101 | 5.7869 | 208 | 0.055438 | 11.531 | 1115 | 12965.1774 | 2849.518 | #N/A | #N/A
6036 | PLACER 1103CB | 152461103 | PLACER 1103 | 6.9691 | 99 | 0.05535 | 5.4797 | 1116 | 12972.1464 | 2844.0383 | #N/A | #N/A
6178 | GEYSERVILLE 110135492 | 42891101 | GEYSERVILLE 1101 | 9.9907 | 219 | 0.055239 | 12.0973 | 1117 | 12982.1371 | 2831.941 | #N/A | #N/A
6625 | WYANDOTTE 1107829470 | 102911107 | WYANDOTTE 1107 | 10.3139 | 93 | 0.055226 | 5.136 | 1118 | 12992.451 | 2826.805 | #N/A | #N/A
7721 | CURTIS 17058110 | 163351705 | CURTIS 1705 | 8.1481 | 99 | 0.055185 | 5.4634 | 1119 | 13000.5991 | 2821.3417 | #N/A | #N/A
8806 | CLAYTON 2212859443 | 12022212 | CLAYTON 2212 | 0.29539 | 5 | 0.055167 | 0.27584 | 1120 | 13000.8945 | 2821.0658 | #N/A | #N/A
8792 | DUNLAP 1103CB | 254061103 | DUNLAP 1103 | 5.6118 | 38 | 0.055113 | 2.0943 | 1121 | 13006.5063 | 2818.9715 | #N/A | #N/A
4534 | MERCED FALLS 110285002 | 252811102 | MERCED FALLS 1102 | 35.4838 | 394 | 0.055026 | 21.6802 | 1122 | 13041.9901 | 2797.2913 | #N/A | #N/A
2247 | FROGTOWN 170113412 | 163451701 | FROGTOWN 1701 | 38.8065 | 333 | 0.055018 | 18.321 | 1123 | 13080.7966 | 2778.9703 | #N/A | #N/A
3205 | COTATI 110361736 | 42271103 | COTATI 1103 | 12.1558 | 129 | 0.054986 | 7.0932 | 1124 | 13092.9524 | 2771.8771 | #N/A | #N/A
9516 | WILDWOOD 11011576 | 103611101 | WILDWOOD 1101 | 8.0638 | 51 | 0.054922 | 2.801 | 1125 | 13101.0162 | 2769.0761 | #N/A | #N/A
4729 | FITCH MOUNTAIN 1113352 | 42751113 | FITCH MOUNTAIN 1113 | 5.6471 | 123 | 0.054876 | 6.7498 | 1126 | 13106.6633 | 2762.3263 | #N/A | #N/A
6906 | IONE 1101CB | 163881101 | IONE 1101 | 1.8464 | 85 | 0.054859 | 4.663 | 1127 | 13108.5097 | 2757.6633 | #N/A | #N/A
1910 | FROGTOWN 17016807 | 163451701 | FROGTOWN 1701 | 4.9065 | 49 | 0.054517 | 2.6713 | 1128 | 13113.4162 | 2754.992 | #N/A | #N/A
1099 | HIGHLANDS 110275140 | 43361102 | HIGHLANDS 1102 | 8.6818 | 238 | 0.054483 | 12.967 | 1129 | 13122.098 | 2742.025 | #N/A | #N/A
9073 | CORRAL 1103831781 | 162991103 | CORRAL 1103 | 0.73719 | 19 | 0.054336 | 1.0324 | 1130 | 13122.8352 | 2740.9926 | #N/A | #N/A
1018 | APPLE HILL 21029722 | 153662102 | APPLE HILL 2102 | 38.8052 | 359 | 0.054308 | 19.4965 | 1131 | 13161.6404 | 2721.4961 | #N/A | #N/A
882 | MORGAN HILL 2105XR152 | 83242105 | MORGAN HILL 2105 | 8.7296 | 156 | 0.054285 | 8.4685 | 1132 | 13170.3699 | 2713.0276 | #N/A | #N/A
7464 | CLARKSVILLE 2106CB | 153612106 | CLARKSVILLE 2106 | 0.1396 | 9 | 0.054215 | 0.48794 | 1133 | 13170.5095 | 2712.5396 | #N/A | #N/A
8313 | RED BLUFF 1104135854 | 103541104 | RED BLUFF 1104 | 1.4451 | 34 | 0.053974 | 1.8351 | 1134 | 13171.9546 | 2710.7045 | #N/A | #N/A
8191 | KESWICK 11011588 | 103451101 | KESWICK 1101 | 8.6957 | 33 | 0.053968 | 1.7809 | 1135 | 13180.6504 | 2708.9236 | #N/A | #N/A
5209 | OLETA 11022642 | 163541102 | OLETA 1102 | 4.6599 | 27 | 0.053841 | 1.4537 | 1136 | 13185.3103 | 2707.4699 | #N/A | #N/A
2961 | SYCAMORE CREEK 11112014 | 102971111 | SYCAMORE CREEK 1111 | 22.3643 | 181 | 0.053762 | 9.731 | 1137 | 13207.6746 | 2697.7389 | #N/A | #N/A
5221 | EL DORADO PH 210163464 | 152762101 | EL DORADO PH 2101 | 13.6239 | 70 | 0.05356 | 3.7492 | 1138 | 13221.2985 | 2693.9897 | #N/A | #N/A
1685 | WILLOW CREEK 110347966 | 192171103 | WILLOW CREEK 1103 | 16.9492 | 167 | 0.053445 | 8.9254 | 1139 | 13238.2477 | 2685.0643 | #N/A | #N/A
1361 | RED BLUFF 11051564 | 103541105 | RED BLUFF 1105 | 1.1756 | 133 | 0.053412 | 7.1038 | 1140 | 13239.4234 | 2677.9605 | #N/A | #N/A
566 | MORGAN HILL 2110814616 | 83242110 | MORGAN HILL 2110 | 0.097826 | 28 | 0.053409 | 1.4955 | 1141 | 13239.5212 | 2676.4651 | #N/A | #N/A
9804 | FROGTOWN 1702694042 | 163451702 | FROGTOWN 1702 | 0.60413 | 8 | 0.053395 | 0.42716 | 1142 | 13240.1253 | 2676.0379 | #N/A | #N/A
548 | SHINGLE SPRINGS 21107742 | 153652110 | SHINGLE SPRINGS 2110 | 45.7027 | 475 | 0.053392 | 25.3612 | 1143 | 13285.828 | 2650.6767 | #N/A | #N/A
4014 | CURTIS 1704CB | 163351704 | CURTIS 1704 | 13.8938 | 170 | 0.053282 | 9.058 | 1144 | 13299.7218 | 2641.6187 | #N/A | #N/A
5744 | WOODSIDE 11018974 | 24251101 | WOODSIDE 1101 | 13.2248 | 149 | 0.05299 | 7.8956 | 1145 | 13312.9466 | 2633.7232 | #N/A | #N/A
4200 | MOLINO 1101322 | 42571101 | MOLINO 1101 | 14.2081 | 167 | 0.052976 | 8.847 | 1146 | 13327.1547 | 2624.8762 | #N/A | #N/A
7680 | PALMER 1101M88 | 183031101 | PALMER 1101 | 3.0885 | 85 | 0.052933 | 4.4993 | 1147 | 13330.2431 | 2620.3768 | #N/A | #N/A
2401 | WOODSIDE 11018884 | 24251101 | WOODSIDE 1101 | 7.4789 | 74 | 0.052785 | 3.9061 | 1148 | 13337.7221 | 2616.4708 | #N/A | #N/A
5333 | GARBERVILLE 11022500 | 192221102 | GARBERVILLE 1102 | 16.0206 | 106 | 0.052654 | 5.5813 | 1149 | 13353.7427 | 2610.8895 | #N/A | #N/A
3787 | BEAR VALLEY 21014500 | 252192101 | BEAR VALLEY 2101 | 24.1783 | 516 | 0.052537 | 27.1089 | 1150 | 13377.921 | 2583.7806 | #N/A | #N/A
8553 | RED BLUFF 11041302 | 103541104 | RED BLUFF 1104 | 13.9155 | 113 | 0.052453 | 5.9272 | 1151 | 13391.8365 | 2577.8535 | #N/A | #N/A
10783 | BEAR VALLEY 2105CB | 252192105 | BEAR VALLEY 2105 | 3.838 | 9 | 0.052345 | 0.4711 | 1152 | 13395.6745 | 2577.3824 | #N/A | #N/A
10429 | BUTTE 1105244246 | 103081105 | BUTTE 1105 | 1.2034 | 11 | 0.052269 | 0.57496 | 1153 | 13396.8779 | 2576.8074 | #N/A | #N/A
1753 | BRUNSWICK 110651484 | 152481106 | BRUNSWICK 1106 | 15.3771 | 195 | 0.052211 | 10.1812 | 1154 | 13412.255 | 2566.6262 | #N/A | #N/A
7841 | STONE CORRAL 1110975698 | 252921110 | STONE CORRAL 1110 | 0.89608 | 44 | 0.052194 | 2.2966 | 1155 | 13413.1511 | 2564.3296 | #N/A | #N/A
10305 | MIDDLETOWN 1101612 | 43141101 | MIDDLETOWN 1101 | 3.9544 | 25 | 0.05213 | 1.3033 | 1156 | 13417.1055 | 2563.0264 | #N/A | #N/A
9510 | PUEBLO 2103776244 | 43292103 | PUEBLO 2103 | 0.17065 | 5 | 0.052117 | 0.26059 | 1157 | 13417.2762 | 2562.7658 | #N/A | #N/A
2874 | FORT ROSS 11214947 | 42851121 | FORT ROSS 1121 | 10.3498 | 56 | 0.052018 | 2.913 | 1158 | 13427.626 | 2559.8528 | #N/A | #N/A
5370 | FROGTOWN 17027108 | 163451702 | FROGTOWN 1702 | 9.6202 | 99 | 0.05186 | 5.1341 | 1159 | 13437.2462 | 2554.7187 | #N/A | #N/A
7742 | WEST POINT 110272036 | 163201102 | WEST POINT 1102 | 12.9673 | 105 | 0.051819 | 5.441 | 1160 | 13450.2135 | 2549.2777 | #N/A | #N/A
8013 | WILLITS 110337506 | 42661103 | WILLITS 1103 | 11.5613 | 77 | 0.051705 | 3.9812 | 1161 | 13461.7748 | 2545.2964 | #N/A | #N/A
8123 | OTTER 1102CB | 182941102 | OTTER 1102 | 6.7693 | 40 | 0.051564 | 2.0626 | 1162 | 13468.5441 | 2543.2338 | #N/A | #N/A
7649 | HARTLEY 1101CB | 43211101 | HARTLEY 1101 | 1.4678 | 33 | 0.051416 | 1.6967 | 1163 | 13470.0119 | 2541.5371 | #N/A | #N/A
4094 | HOPLAND 1101960 | 42251101 | HOPLAND 1101 | 3.8765 | 33 | 0.051413 | 1.6966 | 1164 | 13473.8884 | 2539.8405 | #N/A | #N/A
7517 | PENRYN 110790970 | 152561107 | PENRYN 1107 | 1.4404 | 45 | 0.051234 | 2.3055 | 1165 | 13475.3289 | 2537.535 | #N/A | #N/A
371 | CURTIS 1701CB | 163351701 | CURTIS 1701 | 8.0631 | 159 | 0.051116 | 8.1275 | 1166 | 13483.392 | 2529.4074 | #N/A | #N/A
8728 | CORRAL 1103569005 | 162991103 | CORRAL 1103 | 0.71634 | 38 | 0.051027 | 1.939 | 1167 | 13484.1083 | 2527.4684 | #N/A | #N/A
3664 | PLACERVILLE 2106CB | 153082106 | PLACERVILLE 2106 | 6.554 | 31 | 0.050873 | 1.5771 | 1168 | 13490.6623 | 2525.8914 | #N/A | #N/A
10993 | MESA 1103737698 | 182821103 | MESA 1103 | 0.2019 | 3 | 0.050749 | 0.15225 | 1169 | 13490.8642 | 2525.7391 | #N/A | #N/A
7973 | PENRYN 110550548 | 152561105 | PENRYN 1105 | 0.095853 | 58 | 0.050695 | 2.9403 | 1170 | 13490.96 | 2522.7988 | #N/A | #N/A
9859 | CUYAMA 1103684566 | 253141103 | CUYAMA 1103 | 3.0185 | 4 | 0.050626 | 0.20251 | 1171 | 13493.9785 | 2522.5963 | #N/A | #N/A
7777 | GANSNER 11012424 | 103021101 | GANSNER 1101 | 18.7613 | 141 | 0.050559 | 7.1288 | 1172 | 13512.7398 | 2515.4675 | #N/A | #N/A
10622 | TEJON 1103286542 | 252931103 | TEJON 1103 | 2.1764 | 25 | 0.050527 | 1.2632 | 1173 | 13514.9162 | 2514.2043 | #N/A | #N/A
2224 | COTATI 1103148 | 42271103 | COTATI 1103 | 15.4446 | 107 | 0.050374 | 5.39 | 1174 | 13530.3608 | 2508.8143 | #N/A | #N/A
2728 | MESA 1103M72 | 182821103 | MESA 1103 | 8.4225 | 180 | 0.050224 | 9.0403 | 1175 | 13538.7833 | 2499.774 | #N/A | #N/A
4743 | WYANDOTTE 11031508 | 102911103 | WYANDOTTE 1103 | 27.2173 | 249 | 0.050062 | 12.4656 | 1176 | 13566.0006 | 2487.3085 | 2487.3085 | #N/A
1729 | LUCERNE 1106664 | 43351106 | LUCERNE 1106 | 9.6353 | 140 | 0.050043 | 7.006 | 1177 | 13575.6359 | 2480.3024 | #N/A | #N/A
1094 | HIGGINS 110332120 | 152691103 | HIGGINS 1103 | 40.6428 | 485 | 0.049959 | 24.23 | 1178 | 13616.2787 | 2456.0724 | #N/A | #N/A
1827 | BELL 11082226 | 152701108 | BELL 1108 | 24.0911 | 329 | 0.049738 | 16.3638 | 1179 | 13640.3699 | 2439.7086 | #N/A | #N/A
971 | KANAKA 110183288 | 103221101 | KANAKA 1101 | 17.3628 | 140 | 0.049736 | 6.9631 | 1180 | 13657.7327 | 2432.7455 | #N/A | #N/A
6396 | MC ARTHUR 11011490 | 103491101 | MC ARTHUR 1101 | 10.5575 | 122 | 0.0497 | 6.0634 | 1181 | 13668.2901 | 2426.6822 | #N/A | #N/A
1501 | PIERCY 2110XR258 | 83912110 | PIERCY 2110 | 21.9439 | 117 | 0.049692 | 5.814 | 1182 | 13690.234 | 2420.8682 | #N/A | #N/A
4371 | BELLEVUE 2103552 | 43182103 | BELLEVUE 2103 | 9.4678 | 172 | 0.049565 | 8.5251 | 1183 | 13699.7017 | 2412.343 | #N/A | #N/A
774 | MORGAN HILL 2110654924 | 83242110 | MORGAN HILL 2110 | 2.749 | 61 | 0.049343 | 3.0099 | 1184 | 13702.4507 | 2409.3331 | #N/A | #N/A
4796 | SISQUOC 1102M52 | 182811102 | SISQUOC 1102 | 33.8908 | 131 | 0.04915 | 6.4386 | 1185 | 13736.3415 | 2402.8945 | #N/A | #N/A
899 | RACETRACK 170455798 | 163761704 | RACETRACK 1704 | 23.5467 | 246 | 0.049086 | 12.0752 | 1186 | 13759.8882 | 2390.8193 | #N/A | #N/A
8632 | STELLING 11102243 | 83481110 | STELLING 1110 | 1.8963 | 16 | 0.049051 | 0.78482 | 1187 | 13761.7845 | 2390.0345 | #N/A | #N/A
4409 | HIGGINS 11071070 | 152691107 | HIGGINS 1107 | 7.9153 | 100 | 0.048737 | 4.8737 | 1188 | 13769.6998 | 2385.1608 | #N/A | #N/A
2076 | SAN JUSTO 110136902 | 183181101 | SAN JUSTO 1101 | 12.4242 | 147 | 0.048735 | 7.1641 | 1189 | 13782.124 | 2377.9967 | #N/A | #N/A
6423 | TASSAJARA 2113MR276 | 14662113 | TASSAJARA 2113 | 3.8533 | 42 | 0.048684 | 2.0447 | 1190 | 13785.9773 | 2375.952 | #N/A | #N/A
7009 | PENRYN 110551676 | 152561105 | PENRYN 1105 | 8.0239 | 145 | 0.048603 | 7.0475 | 1191 | 13794.0012 | 2368.9045 | #N/A | #N/A
9522 | STONE CORRAL 1110894956 | 252921110 | STONE CORRAL 1110 | 0.77267 | 16 | 0.048471 | 0.77554 | 1192 | 13794.7739 | 2368.129 | #N/A | #N/A
4908 | DIVIDE 1103567884 | 182571103 | DIVIDE 1103 | 2.5019 | 27 | 0.048164 | 1.3004 | 1193 | 13797.2758 | 2366.8286 | #N/A | #N/A
537 | FORT SEWARD 11211602 | 192321121 | FORT SEWARD 1121 | 18.2149 | 109 | 0.048111 | 5.244 | 1194 | 13815.4906 | 2361.5845 | #N/A | #N/A
522 | MONTE RIO 1111292 | 42811111 | MONTE RIO 1111 | 15.5718 | 165 | 0.048057 | 7.9294 | 1195 | 13831.0625 | 2353.6552 | #N/A | #N/A
6679 | LAYTONVILLE 11011760 | 42681101 | LAYTONVILLE 1101 | 9.7018 | 73 | 0.048043 | 3.5072 | 1196 | 13840.7643 | 2350.148 | #N/A | #N/A
7262 | LOW GAP 11014160 | 192411101 | LOW GAP 1101 | 21.7466 | 194 | 0.047994 | 9.3109 | 1197 | 13862.5109 | 2340.8371 | #N/A | #N/A
2115 | GARBERVILLE 1102CB | 192221102 | GARBERVILLE 1102 | 11.9953 | 191 | 0.047992 | 9.1665 | 1198 | 13874.5063 | 2331.6707 | #N/A | #N/A
859 | SALT SPRINGS 21011216 | 163692101 | SALT SPRINGS 2101 | 5.4829 | 32 | 0.04796 | 1.5347 | 1199 | 13879.9891 | 2330.136 | #N/A | #N/A
4717 | CAMBRIA 1101V76 | 182771101 | CAMBRIA 1101 | 18.9625 | 59 | 0.047925 | 2.8276 | 1200 | 13898.9516 | 2327.3084 | #N/A | #N/A
3890 | KANAKA 110165606 | 103221101 | KANAKA 1101 | 12.7444 | 145 | 0.047918 | 6.9481 | 1201 | 13911.696 | 2320.3603 | #N/A | #N/A
11044 | SAN LUIS OBISPO 1104753254 | 182631104 | SAN LUIS OBISPO 1104 | 0.34876 | 2 | 0.047657 | 0.095314 | 1202 | 13912.0447 | 2320.2649 | #N/A | #N/A
868 | PEORIA 170459596 | 163781704 | PEORIA 1704 | 20.8818 | 294 | 0.047553 | 13.9806 | 1203 | 13932.9265 | 2306.2844 | #N/A | #N/A
5643 | CLEAR LAKE 1102991285 | 42141102 | CLEAR LAKE 1102 | 0.32685 | 24 | 0.047469 | 1.1393 | 1204 | 13933.2534 | 2305.1451 | #N/A | #N/A
2996 | BURNEY 11012402 | 103311101 | BURNEY 1101 | 1.4989 | 18 | 0.047353 | 0.85235 | 1205 | 13934.7523 | 2304.2928 | #N/A | #N/A
982 | WEST POINT 11024788 | 163201102 | WEST POINT 1102 | 69.5307 | 673 | 0.047319 | 31.8454 | 1206 | 14004.283 | 2272.4474 | #N/A | #N/A
6337 | MIWUK 170219772 | 163661702 | MIWUK 1702 | 3.8525 | 41 | 0.047283 | 1.9386 | 1207 | 14008.1354 | 2270.5088 | #N/A | #N/A
1317 | MOLINO 1102178 | 42571102 | MOLINO 1102 | 12.1979 | 182 | 0.047227 | 8.5954 | 1208 | 14020.3334 | 2261.9135 | #N/A | #N/A
2756 | AUBERRY 1101R2845 | 254151101 | AUBERRY 1101 | 17.8248 | 172 | 0.047182 | 8.1154 | 1209 | 14038.1581 | 2253.7981 | #N/A | #N/A
1878 | JESSUP 110168362 | 103441101 | JESSUP 1101 | 5.1662 | 96 | 0.047076 | 4.5193 | 1210 | 14043.3243 | 2249.2788 | #N/A | #N/A
1899 | SAN BENITO 2104785888 | 182742104 | SAN BENITO 2104 | 4.8047 | 49 | 0.047021 | 2.304 | 1211 | 14048.129 | 2246.9748 | #N/A | #N/A
1312 | MOUNTAIN QUARRIES 210192474 | 152282101 | MOUNTAIN QUARRIES 2101 | 15.1059 | 173 | 0.046937 | 8.12 | 1212 | 14063.2349 | 2238.8547 | #N/A | #N/A
9280 | FREMONT 1104MR339 | 14351104 | FREMONT 1104 | 1.1941 | 73 | 0.046887 | 3.4227 | 1213 | 14064.4289 | 2235.432 | #N/A | #N/A
10367 | PEORIA 170488630 | 163781704 | PEORIA 1704 | 0.77849 | 6 | 0.046842 | 0.28105 | 1214 | 14065.2074 | 2235.151 | #N/A | #N/A
3920 | LLAGAS 2107XR178 | 83182107 | LLAGAS 2107 | 5.9005 | 138 | 0.04683 | 6.4625 | 1215 | 14071.108 | 2228.6884 | #N/A | #N/A
9293 | DUNLAP 110239190 | 254061102 | DUNLAP 1102 | 1.7882 | 17 | 0.046743 | 0.79463 | 1216 | 14072.8962 | 2227.8938 | #N/A | #N/A
9995 | GEYSERVILLE 1102180193 | 42891102 | GEYSERVILLE 1102 | 2.161 | 23 | 0.046684 | 1.0737 | 1217 | 14075.0572 | 2226.82 | #N/A | #N/A
2795 | BELL 1108467470 | 152701108 | BELL 1108 | 1.857 | 40 | 0.046424 | 1.857 | 1218 | 14076.9142 | 2224.9631 | #N/A | #N/A
6866 | EDENVALE 1102XR064 | 82951102 | EDENVALE 1102 | 0.73065 | 35 | 0.046387 | 1.6236 | 1219 | 14077.6449 | 2223.3395 | #N/A | #N/A
2884 | MC ARTHUR 110137388 | 103491101 | MC ARTHUR 1101 | 8.1109 | 56 | 0.046193 | 2.5868 | 1220 | 14085.7557 | 2220.7527 | #N/A | #N/A
8090 | PENRYN 1105817491 | 152561105 | PENRYN 1105 | 1.4167 | 24 | 0.046183 | 1.1084 | 1221 | 14087.1724 | 2219.6443 | #N/A | #N/A
196 | MILPITAS 1109XR082 | 82831109 | MILPITAS 1109 | 19.6858 | 186 | 0.046133 | 8.5807 | 1222 | 14106.8583 | 2211.0636 | #N/A | #N/A
9874 | JARVIS 1108767280 | 13501108 | JARVIS 1108 | 0.5074 | 11 | 0.046117 | 0.50728 | 1223 | 14107.3657 | 2210.5563 | #N/A | #N/A
3653 | PUEBLO 2103678 | 43292103 | PUEBLO 2103 | 35.3374 | 325 | 0.046077 | 14.9751 | 1224 | 14142.7031 | 2195.5812 | #N/A | #N/A
4529 | MC ARTHUR 110138998 | 103491101 | MC ARTHUR 1101 | 0.11777 | 61 | 0.046064 | 2.8099 | 1225 | 14142.8208 | 2192.7713 | #N/A | #N/A
9562 | MOLINO 1101600112 | 42571101 | MOLINO 1101 | 0.798 | 18 | 0.045774 | 0.82393 | 1226 | 14143.6188 | 2191.9473 | #N/A | #N/A
8471 | MONTICELLO 1101654 | 43051101 | MONTICELLO 1101 | 8.2164 | 71 | 0.045547 | 3.2338 | 1227 | 14151.8352 | 2188.7135 | #N/A | #N/A
9084 | SWIFT 2110XR254 | 83392110 | SWIFT 2110 | 25.1775 | 134 | 0.045544 | 6.1028 | 1228 | 14177.0127 | 2182.6107 | #N/A | #N/A
5247 | MOLINO 1102658 | 42571102 | MOLINO 1102 | 10.8829 | 107 | 0.045341 | 4.8515 | 1229 | 14187.8955 | 2177.7592 | #N/A | #N/A
1624 | CLAY 11037124 | 163341103 | CLAY 1103 | 11.0615 | 286 | 0.045279 | 12.9498 | 1230 | 14198.9571 | 2164.8094 | #N/A | #N/A
6683 | UKIAH 11143606 | 42771114 | UKIAH 1114 | 10.702 | 129 | 0.045178 | 5.828 | 1231 | 14209.6591 | 2158.9814 | #N/A | #N/A
6114 | GANSNER 110137550 | 103021101 | GANSNER 1101 | 0.36702 | 33 | 0.045042 | 1.4864 | 1232 | 14210.0261 | 2157.495 | #N/A | #N/A
10276 | LAKEVILLE 1102367100 | 43371102 | LAKEVILLE 1102 | 0.55985 | 6 | 0.04493 | 0.26958 | 1233 | 14210.5859 | 2157.2254 | #N/A | #N/A
3592 | CURTIS 17039330 | 163351703 | CURTIS 1703 | 41.3401 | 345 | 0.044648 | 15.4037 | 1234 | 14251.9261 | 2141.8217 | #N/A | #N/A
1338 | SILVERADO 210437632 | 43432104 | SILVERADO 2104 | 26.5819 | 304 | 0.044601 | 13.5588 | 1235 | 14278.508 | 2128.2629 | #N/A | #N/A
9592 | BELL 1107912460 | 152701107 | BELL 1107 | 0.1406 | 6 | 0.044495 | 0.26697 | 1236 | 14278.6486 | 2127.996 | #N/A | #N/A
9543 | GARBERVILLE 110237054 | 192221102 | GARBERVILLE 1102 | 8.9461 | 76 | 0.044439 | 3.3774 | 1237 | 14287.5946 | 2124.6186 | #N/A | #N/A
528 | PLACERVILLE 210692012 | 153082106 | PLACERVILLE 2106 | 18.5175 | 219 | 0.044304 | 9.7026 | 1238 | 14306.1121 | 2114.916 | #N/A | #N/A
2289 | PASO ROBLES 1103351084 | 182611103 | PASO ROBLES 1103 | 2.3702 | 91 | 0.044255 | 4.0272 | 1239 | 14308.4824 | 2110.8888 | #N/A | #N/A
4151 | SHINGLE SPRINGS 2109CB | 153652109 | SHINGLE SPRINGS 2109 | 27.3462 | 341 | 0.044085 | 15.0331 | 1240 | 14335.8286 | 2095.8557 | #N/A | #N/A
8694 | MC ARTHUR 11011544 | 103491101 | MC ARTHUR 1101 | 16.9615 | 135 | 0.044056 | 5.9476 | 1241 | 14352.7901 | 2089.9081 | #N/A | #N/A
5303 | STONE CORRAL 11087100 | 252921108 | STONE CORRAL 1108 | 2.3355 | 130 | 0.04396 | 5.7148 | 1242 | 14355.1256 | 2084.1933 | #N/A | #N/A
5138 | SUMMIT 11022302 | 152591102 | SUMMIT 1102 | 1.3381 | 19 | 0.043905 | 0.8342 | 1243 | 14356.4637 | 2083.3591 | #N/A | #N/A
3403 | PENRYN 11051378 | 152561105 | PENRYN 1105 | 0.89964 | 25 | 0.043839 | 1.096 | 1244 | 14357.3633 | 2082.2631 | #N/A | #N/A
5562 | GARBERVILLE 110139524 | 192221101 | GARBERVILLE 1101 | 5.1162 | 138 | 0.04372 | 6.0334 | 1245 | 14362.4795 | 2076.2298 | #N/A | #N/A
3303 | BIG BEND 1101180398 | 103751101 | BIG BEND 1101 | 5.56 | 48 | 0.04366 | 2.0957 | 1246 | 14368.0395 | 2074.1341 | #N/A | #N/A
5481 | VACAVILLE 110847860 | 63601108 | VACAVILLE 1108 | 0.28963 | 54 | 0.043573 | 2.353 | 1247 | 14368.3291 | 2071.7811 | #N/A | #N/A
8994 | SAN LUIS OBISPO 1104982992 | 182631104 | SAN LUIS OBISPO 1104 | 8.9436 | 52 | 0.043526 | 2.2633 | 1248 | 14377.2727 | 2069.5178 | #N/A | #N/A
6482 | UKIAH 1113691436 | 42771113 | UKIAH 1113 | 1.0446 | 28 | 0.043449 | 1.2166 | 1249 | 14378.3173 | 2068.3012 | #N/A | #N/A
7283 | COVELO 1101112804 | 43061101 | COVELO 1101 | 10.2626 | 67 | 0.043443 | 2.9107 | 1250 | 14388.5799 | 2065.3906 | #N/A | #N/A
2688 | STILLWATER 11021466 | 103561102 | STILLWATER 1102 | 20.5343 | 211 | 0.043245 | 9.1248 | 1251 | 14409.1142 | 2056.2658 | #N/A | #N/A
6122 | EEL RIVER 11024814 | 192381102 | EEL RIVER 1102 | 26.9939 | 117 | 0.043216 | 5.0562 | 1252 | 14436.1081 | 2051.2096 | #N/A | #N/A
8658 | MENLO 11037902 | 24131103 | MENLO 1103 | 11.6992 | 143 | 0.043162 | 6.1722 | 1253 | 14447.8072 | 2045.0373 | #N/A | #N/A
5986 | SILVERADO 210478268 | 43432104 | SILVERADO 2104 | 9.7249 | 114 | 0.043133 | 4.9171 | 1254 | 14457.5321 | 2040.1202 | #N/A | #N/A
3705 | ALTO 11221212 | 42031122 | ALTO 1122 | 1.8503 | 25 | 0.043056 | 1.0764 | 1255 | 14459.3824 | 2039.0438 | #N/A | #N/A
565 | CALPELLA 1101CB | 43411101 | CALPELLA 1101 | 11.7762 | 226 | 0.043018 | 9.722 | 1256 | 14471.1587 | 2029.3218 | #N/A | #N/A
1815 | OTTER 110298036 | 182941102 | OTTER 1102 | 9.2007 | 64 | 0.042868 | 2.7435 | 1257 | 14480.3594 | 2026.5782 | #N/A | #N/A
5821 | HIGHLANDS 11034630 | 43361103 | HIGHLANDS 1103 | 1.0747 | 42 | 0.042814 | 1.7982 | 1258 | 14481.4341 | 2024.78 | #N/A | #N/A
1927 | HIGGINS 1110166282 | 152691110 | HIGGINS 1110 | 23.9909 | 256 | 0.042498 | 10.8796 | 1259 | 14505.425 | 2013.9005 | #N/A | #N/A
6705 | GIRVAN 11021028 | 103401102 | GIRVAN 1102 | 17.6533 | 208 | 0.042483 | 8.8364 | 1260 | 14523.0782 | 2005.0641 | #N/A | #N/A
3470 | OILFIELDS 1103370932 | 182391103 | OILFIELDS 1103 | 0.38529 | 6 | 0.042464 | 0.25478 | 1261 | 14523.4635 | 2004.8093 | #N/A | #N/A
9825 | GIRVAN 1101CB | 103401101 | GIRVAN 1101 | 1.5361 | 31 | 0.042406 | 1.3146 | 1262 | 14524.9996 | 2003.4947 | #N/A | #N/A
4531 | CRESCENT MILLS 21013113 | 103132101 | CRESCENT MILLS 2101 | 1.1931 | 9 | 0.042389 | 0.3815 | 1263 | 14526.1927 | 2003.1132 | #N/A | #N/A
4502 | WILLITS 1103968 | 42661103 | WILLITS 1103 | 26.7055 | 283 | 0.042383 | 11.9944 | 1264 | 14552.8982 | 1991.1188 | #N/A | #N/A
293 | MENDOCINO 110131322 | 42951101 | MENDOCINO 1101 | 5.8546 | 310 | 0.04237 | 13.1348 | 1265 | 14558.7527 | 1977.984 | #N/A | #N/A
332 | MESA 1101CB | 182821101 | MESA 1101 | 13.8593 | 230 | 0.042367 | 9.7444 | 1266 | 14572.6121 | 1968.2396 | #N/A | #N/A
6761 | HORSESHOE 11011682 | 152571101 | HORSESHOE 1101 | 0.20299 | 112 | 0.042324 | 4.7402 | 1267 | 14572.8151 | 1963.4994 | #N/A | #N/A
4789 | APPLE HILL 110412842 | 153661104 | APPLE HILL 1104 | 15.8199 | 209 | 0.042311 | 8.8429 | 1268 | 14588.6349 | 1954.6565 | #N/A | #N/A
5435 | SUNOL 1101MR299 | 14241101 | SUNOL 1101 | 4.9442 | 58 | 0.042276 | 2.452 | 1269 | 14593.5791 | 1952.2045 | #N/A | #N/A
5875 | MESA 11016113 | 182821101 | MESA 1101 | 1.7404 | 100 | 0.042268 | 4.2268 | 1270 | 14595.3195 | 1947.9777 | #N/A | #N/A
6536 | PINE GROVE 11026080 | 163751102 | PINE GROVE 1102 | 34.374 | 322 | 0.042249 | 13.6042 | 1271 | 14629.6935 | 1934.3734 | #N/A | #N/A
10453 | RIO DELL 11027124 | 192251102 | RIO DELL 1102 | 0.67208 | 5 | 0.042229 | 0.21114 | 1272 | 14630.3656 | 1934.1623 | #N/A | #N/A
9767 | SAN BERNARD 1101641042 | 253191101 | SAN BERNARD 1101 | 1.4299 | 22 | 0.042194 | 0.92827 | 1273 | 14631.7956 | 1933.234 | #N/A | #N/A
7173 | OTTER 110237132 | 182941102 | OTTER 1102 | 5.8068 | 50 | 0.042173 | 2.1086 | 1274 | 14637.6024 | 1931.1254 | #N/A | #N/A
7839 | FROGTOWN 1702204480 | 163451702 | FROGTOWN 1702 | 0.50198 | 28 | 0.04209 | 1.1785 | 1275 | 14638.1044 | 1929.9469 | #N/A | #N/A
1556 | HOPLAND 110180620 | 42251101 | HOPLAND 1101 | 1.2417 | 51 | 0.04205 | 2.1446 | 1276 | 14639.3461 | 1927.8023 | #N/A | #N/A
796 | MESA 1101M86 | 182821101 | MESA 1101 | 12.7414 | 217 | 0.041844 | 9.0801 | 1277 | 14652.0875 | 1918.7222 | #N/A | #N/A
4020 | CABRILLO 1103Y10 | 183101103 | CABRILLO 1103 | 4.8408 | 122 | 0.041779 | 5.0971 | 1278 | 14656.9283 | 1913.6251 | #N/A | #N/A
4294 | FITCH MOUNTAIN 11134566 | 42751113 | FITCH MOUNTAIN 1113 | 12.5097 | 180 | 0.041761 | 7.5169 | 1279 | 14669.438 | 1906.1082 | #N/A | #N/A
3368 | PEORIA 17051834 | 163781705 | PEORIA 1705 | 23.5691 | 217 | 0.041581 | 9.0231 | 1280 | 14693.0071 | 1897.0852 | #N/A | #N/A
4811 | CALAVERAS CEMENT 1101502 | 162211101 | CALAVERAS CEMENT 1101 | 37.6576 | 331 | 0.041554 | 13.7543 | 1281 | 14730.6646 | 1883.3309 | #N/A | #N/A
8493 | COTATI 1102282 | 42271102 | COTATI 1102 | 2.7813 | 62 | 0.041526 | 2.5746 | 1282 | 14733.4459 | 1880.7562 | #N/A | #N/A
3229 | WISE 1102CB | 152271102 | WISE 1102 | 14.0667 | 177 | 0.041442 | 7.3353 | 1283 | 14747.5126 | 1873.4209 | #N/A | #N/A
2423 | APPLE HILL 110413512 | 153661104 | APPLE HILL 1104 | 28.4598 | 345 | 0.041392 | 14.2801 | 1284 | 14775.9724 | 1859.1408 | #N/A | #N/A
3013 | BIG MEADOWS 21012586 | 102812101 | BIG MEADOWS 2101 | 6.2589 | 91 | 0.041237 | 3.7526 | 1285 | 14782.2313 | 1855.3882 | #N/A | #N/A
6401 | COPPERMINE 1104556430 | 252411104 | COPPERMINE 1104 | 4.8433 | 122 | 0.041063 | 5.0096 | 1286 | 14787.0746 | 1850.3785 | #N/A | #N/A
9989 | ORO FINO 11022236 | 103031102 | ORO FINO 1102 | 2.5609 | 11 | 0.040994 | 0.45093 | 1287 | 14789.6355 | 1849.9276 | #N/A | #N/A
3633 | BIG BEND 11021972 | 103751102 | BIG BEND 1102 | 21.2964 | 177 | 0.040961 | 7.25 | 1288 | 14810.932 | 1842.6776 | 1842.6776 | #N/A
7419 | MARTELL 110299214 | 163011102 | MARTELL 1102 | 1.8356 | 21 | 0.040838 | 0.85759 | 1289 | 14812.7676 | 1841.82 | #N/A | #N/A
5589 | BUELLTON 1101Y36 | 183041101 | BUELLTON 1101 | 37.7365 | 283 | 0.0408 | 11.5464 | 1290 | 14850.5041 | 1830.2737 | #N/A | #N/A
2824 | GEYSERVILLE 1101166 | 42891101 | GEYSERVILLE 1101 | 6.1958 | 110 | 0.040759 | 4.4835 | 1291 | 14856.6999 | 1825.7901 | #N/A | #N/A
612 | DIAMOND SPRINGS 11062100 | 152261106 | DIAMOND SPRINGS 1106 | 39.0796 | 403 | 0.040696 | 16.4004 | 1292 | 14895.7795 | 1809.3897 | #N/A | #N/A
4758 | LAYTONVILLE 1101402 | 42681101 | LAYTONVILLE 1101 | 23.359 | 151 | 0.040695 | 6.145 | 1293 | 14919.1385 | 1803.2447 | #N/A | #N/A
7625 | ATASCADERO 1103440856 | 182541103 | ATASCADERO 1103 | 34.8114 | 349 | 0.040647 | 14.1857 | 1294 | 14953.9499 | 1789.059 | #N/A | #N/A
3291 | FRUITLAND 11426054 | 192311142 | FRUITLAND 1142 | 7.1968 | 58 | 0.040642 | 2.3572 | 1295 | 14961.1467 | 1786.7018 | #N/A | #N/A
2753 | CALPELLA 11011204 | 43411101 | CALPELLA 1101 | 9.4816 | 124 | 0.040535 | 5.0263 | 1296 | 14970.6283 | 1781.6755 | #N/A | #N/A
6226 | FULTON 1107214 | 42561107 | FULTON 1107 | 11.7268 | 142 | 0.040503 | 5.7514 | 1297 | 14982.3551 | 1775.924 | #N/A | #N/A
6297 | PEORIA 170176030 | 163781701 | PEORIA 1701 | 5.1103 | 55 | 0.040366 | 2.2201 | 1298 | 14987.4654 | 1773.7039 | #N/A | #N/A
4946 | WYANDOTTE 11031976 | 102911103 | WYANDOTTE 1103 | 23.7815 | 217 | 0.040282 | 8.7412 | 1299 | 15011.2469 | 1764.9627 | 1764.9627 | #N/A
3803 | CALAVERAS CEMENT 1101CB | 162211101 | CALAVERAS CEMENT 1101 | 10.4702 | 203 | 0.040232 | 8.1671 | 1300 | 15021.717 | 1756.7956 | #N/A | #N/A
601 | FORESTHILL 11022106 | 152181102 | FORESTHILL 1102 | 27.8816 | 264 | 0.040196 | 10.6117 | 1301 | 15049.5987 | 1746.1839 | #N/A | #N/A
3937 | AUBERRY 1101176050 | 254151101 | AUBERRY 1101 | 21.128 | 168 | 0.040157 | 6.7464 | 1302 | 15070.7267 | 1739.4374 | #N/A | #N/A
3563 | SHINGLE SPRINGS 21092053 | 153652109 | SHINGLE SPRINGS 2109 | 5.7415 | 74 | 0.040131 | 2.9697 | 1303 | 15076.4681 | 1736.4677 | #N/A | #N/A
639 | LAYTONVILLE 1101CB | 42681101 | LAYTONVILLE 1101 | 5.954 | 90 | 0.040116 | 3.6104 | 1304 | 15082.4222 | 1732.8573 | #N/A | #N/A
8583 | UKIAH 1111168892 | 42771111 | UKIAH 1111 | 0.16428 | 8 | 0.040099 | 0.32079 | 1305 | 15082.5864 | 1732.5365 | #N/A | #N/A
6071 | SHINGLE SPRINGS 210981390 | 153652109 | SHINGLE SPRINGS 2109 | 18.6189 | 208 | 0.039915 | 8.3022 | 1306 | 15101.2053 | 1724.2343 | #N/A | #N/A
5271 | WILLITS 1104504 | 42661104 | WILLITS 1104 | 22.5315 | 205 | 0.039748 | 8.1484 | 1307 | 15123.7368 | 1716.0859 | #N/A | #N/A
8156 | PIKE CITY 1102CB | 152201102 | PIKE CITY 1102 | 9.5189 | 44 | 0.03956 | 1.7406 | 1308 | 15133.2557 | 1714.3452 | #N/A | #N/A
1834 | CASTRO VALLEY 1110MR748 | 14091110 | CASTRO VALLEY 1110 | 6.2313 | 86 | 0.039516 | 3.3984 | 1309 | 15139.487 | 1710.9468 | #N/A | #N/A
4232 | GABILAN 1101989608 | 182331101 | GABILAN 1101 | 0.75178 | 6 | 0.039513 | 0.23708 | 1310 | 15140.2388 | 1710.7098 | #N/A | #N/A
2029 | OCEANO 1102V56 | 182601102 | OCEANO 1102 | 9.3367 | 115 | 0.039442 | 4.5359 | 1311 | 15149.5755 | 1706.1739 | #N/A | #N/A
6282 | MOLINO 1101891 | 42571101 | MOLINO 1101 | 3.1513 | 41 | 0.03939 | 1.615 | 1312 | 15152.7268 | 1704.5589 | #N/A | #N/A
7224 | MIRABEL 1101116 | 42091101 | MIRABEL 1101 | 10.3331 | 112 | 0.039363 | 4.4087 | 1313 | 15163.0599 | 1700.1502 | #N/A | #N/A
3752 | MONTE RIO 1113539938 | 42811113 | MONTE RIO 1113 | 2.7721 | 26 | 0.039354 | 1.0232 | 1314 | 15165.8319 | 1699.127 | #N/A | #N/A
8901 | BRIDGEVILLE 110237486 | 192461102 | BRIDGEVILLE 1102 | 6.9374 | 85 | 0.039237 | 3.3351 | 1315 | 15172.7693 | 1695.7919 | #N/A | #N/A
3640 | FROGTOWN 1702CB | 163451702 | FROGTOWN 1702 | 1.4614 | 47 | 0.039234 | 1.844 | 1316 | 15174.2307 | 1693.9479 | 1693.9479 | #N/A
4627 | SAN LUIS OBISPO 1107V02 | 182631107 | SAN LUIS OBISPO 1107 | 18.189 | 202 | 0.039184 | 7.9151 | 1317 | 15192.4197 | 1686.0327 | #N/A | #N/A
2477 | CEDAR CREEK 11011656 | 103321101 | CEDAR CREEK 1101 | 32.2308 | 208 | 0.039176 | 8.1485 | 1318 | 15224.6505 | 1677.8842 | #N/A | #N/A
6350 | NAPA 11121302 | 42021112 | NAPA 1112 | 20.0955 | 317 | 0.039053 | 12.3798 | 1319 | 15244.7461 | 1665.5044 | #N/A | #N/A
798 | HIGGINS 1107CB | 152691107 | HIGGINS 1107 | 5.7283 | 243 | 0.03873 | 9.4114 | 1320 | 15250.4743 | 1656.093 | #N/A | #N/A
10498 | CLAYTON 2212158138 | 12022212 | CLAYTON 2212 | 0.5155 | 10 | 0.038704 | 0.38704 | 1321 | 15250.9898 | 1655.706 | #N/A | #N/A
9150 | SPANISH CREEK 4401CB | 103104401 | SPANISH CREEK 4401 | 7.7363 | 22 | 0.038702 | 0.85144 | 1322 | 15258.7262 | 1654.8545 | #N/A | #N/A
561 | ALTO 11221260 | 42031122 | ALTO 1122 | 2.9876 | 36 | 0.038665 | 1.3919 | 1323 | 15261.7138 | 1653.4626 | #N/A | #N/A
2054 | PUEBLO 1104580658 | 43291104 | PUEBLO 1104 | 9.3918 | 107 | 0.038518 | 4.1214 | 1324 | 15271.1056 | 1649.3412 | #N/A | #N/A
3362 | REDBUD 110191960 | 43191101 | REDBUD 1101 | 6.5181 | 90 | 0.038488 | 3.4639 | 1325 | 15277.6237 | 1645.8773 | #N/A | #N/A
3879 | WILLITS 11032506 | 42661103 | WILLITS 1103 | 12.608 | 89 | 0.038425 | 3.4198 | 1326 | 15290.2317 | 1642.4575 | #N/A | #N/A
2472 | SANTA ROSA A 1104220 | 42151104 | SANTA ROSA A 1104 | 9.5948 | 105 | 0.038284 | 4.0198 | 1327 | 15299.8265 | 1638.4376 | #N/A | #N/A
2655 | TEMPLETON 2110R90 | 183052110 | TEMPLETON 2110 | 30.1931 | 259 | 0.038279 | 9.9144 | 1328 | 15330.0196 | 1628.5233 | #N/A | #N/A
4442 | OCEANO 1104Q06 | 182601104 | OCEANO 1104 | 12.4701 | 154 | 0.038111 | 5.8691 | 1329 | 15342.4896 | 1622.6542 | #N/A | #N/A
3161 | MARTELL 110368192 | 163011103 | MARTELL 1103 | 2.7363 | 72 | 0.037972 | 2.734 | 1330 | 15345.2259 | 1619.9202 | #N/A | #N/A
7038 | MIRABEL 1102334 | 42091102 | MIRABEL 1102 | 5.9568 | 84 | 0.037896 | 3.1833 | 1331 | 15351.1827 | 1616.7369 | #N/A | #N/A
6568 | GEYSERVILLE 110137454 | 42891101 | GEYSERVILLE 1101 | 6.5152 | 114 | 0.037721 | 4.3002 | 1332 | 15357.6979 | 1612.4367 | #N/A | #N/A
9085 | SAN LUIS OBISPO 1107V62 | 182631107 | SAN LUIS OBISPO 1107 | 6.904 | 50 | 0.037409 | 1.8704 | 1333 | 15364.6019 | 1610.5663 | #N/A | #N/A
3181 | SONOMA 110478372 | 42721104 | SONOMA 1104 | 16.6264 | 198 | 0.037304 | 7.3862 | 1334 | 15381.2283 | 1603.1801 | #N/A | #N/A
296 | TASSAJARA 2112D514R | 14662112 | TASSAJARA 2112 | 3.1274 | 73 | 0.037278 | 2.7213 | 1335 | 15384.3557 | 1600.4588 | #N/A | #N/A
5732 | SWIFT 2107XR526 | 83392107 | SWIFT 2107 | 2.0918 | 64 | 0.037122 | 2.3758 | 1336 | 15386.4474 | 1598.083 | #N/A | #N/A
4671 | PURISIMA 1101Y42 | 182971101 | PURISIMA 1101 | 3.4981 | 127 | 0.037118 | 4.714 | 1337 | 15389.9456 | 1593.369 | #N/A | #N/A
7642 | PENRYN 1105168616 | 152561105 | PENRYN 1105 | 3.1566 | 102 | 0.03705 | 3.7791 | 1338 | 15393.1022 | 1589.5899 | #N/A | #N/A
2287 | OCEANO 1104104102 | 182601104 | OCEANO 1104 | 3.3123 | 32 | 0.03704 | 1.1853 | 1339 | 15396.4145 | 1588.4046 | #N/A | #N/A
9499 | OILFIELDS 1103N46 | 182391103 | OILFIELDS 1103 | 5.8177 | 29 | 0.036988 | 1.0726 | 1340 | 15402.2322 | 1587.332 | #N/A | #N/A
5619 | NARROWS 21052426 | 153132105 | NARROWS 2105 | 8.566 | 226 | 0.036874 | 8.3335 | 1341 | 15410.7982 | 1578.9985 | #N/A | #N/A
3889 | RINCON 1103474 | 43321103 | RINCON 1103 | 18.3351 | 174 | 0.036813 | 6.4055 | 1342 | 15429.1333 | 1572.593 | #N/A | #N/A
6070 | CRESCENT MILLS 21012230 | 103132101 | CRESCENT MILLS 2101 | 6.8196 | 112 | 0.036587 | 4.0978 | 1343 | 15435.9529 | 1568.4952 | #N/A | #N/A
7395 | HALF MOON BAY 11018902 | 24101101 | HALF MOON BAY 1101 | 14.1623 | 145 | 0.036496 | 5.2919 | 1344 | 15450.1152 | 1563.2033 | #N/A | #N/A
8155 | PIT NO 5 11011606 | 101321101 | PIT NO 5 1101 | 5.527 | 40 | 0.036482 | 1.4593 | 1345 | 15455.6422 | 1561.744 | #N/A | #N/A
6340 | ELECTRA 11011238 | 162161101 | ELECTRA 1101 | 3.6201 | 81 | 0.036431 | 2.9509 | 1346 | 15459.2622 | 1558.7932 | #N/A | #N/A
988 | FROGTOWN 1701CB | 163451701 | FROGTOWN 1701 | 10.062 | 76 | 0.036334 | 2.7614 | 1347 | 15469.3242 | 1556.0317 | #N/A | #N/A
6703 | POTTER VALLEY P H 110576498 | 42281105 | POTTER VALLEY P H 1105 | 14.8806 | 119 | 0.036331 | 4.3234 | 1348 | 15484.2049 | 1551.7084 | #N/A | #N/A
10138 | LLAGAS 2107870396 | 83182107 | LLAGAS 2107 | 0.82442 | 40 | 0.036327 | 1.4531 | 1349 | 15485.0293 | 1550.2553 | #N/A | #N/A
7528 | LAYTONVILLE 110189606 | 42681101 | LAYTONVILLE 1101 | 11.6322 | 100 | 0.036226 | 3.6226 | 1350 | 15496.6615 | 1546.6327 | #N/A | #N/A
1489 | CURTIS 1702CB | 163351702 | CURTIS 1702 | 22.0674 | 293 | 0.036175 | 10.5993 | 1351 | 15518.7289 | 1536.0334 | #N/A | #N/A
3159 | SALMON CREEK 1101194 | 43161101 | SALMON CREEK 1101 | 6.7792 | 62 | 0.03614 | 2.2407 | 1352 | 15525.5081 | 1533.7927 | #N/A | #N/A
5649 | MORGAN HILL 2111XR186 | 83242111 | MORGAN HILL 2111 | 2.8908 | 191 | 0.036035 | 6.8827 | 1353 | 15528.3989 | 1526.91 | #N/A | #N/A
972 | BRUNSWICK 11062392 | 152481106 | BRUNSWICK 1106 | 6.098 | 111 | 0.036 | 3.996 | 1354 | 15534.4969 | 1522.914 | #N/A | #N/A
4961 | TEMPLETON 2110R94 | 183052110 | TEMPLETON 2110 | 13.9097 | 179 | 0.035946 | 6.4343 | 1355 | 15548.4066 | 1516.4797 | #N/A | #N/A
2592 | CAYUCOS 11014701 | 182551101 | CAYUCOS 1101 | 2.1061 | 65 | 0.035932 | 2.3356 | 1356 | 15550.5127 | 1514.1441 | #N/A | #N/A
160 | MOUNTAIN QUARRIES 21011346 | 152282101 | MOUNTAIN QUARRIES 2101 | 30.8214 | 410 | 0.035841 | 14.6948 | 1357 | 15581.3341 | 1499.4493 | #N/A | #N/A
3187 | SAN MIGUEL 1104R58 | 182661104 | SAN MIGUEL 1104 | 0.54102 | 130 | 0.035811 | 4.6554 | 1358 | 15581.8751 | 1494.7939 | #N/A | #N/A
8179 | LOS OSITOS 21037062 | 182082103 | LOS OSITOS 2103 | 12.2213 | 53 | 0.035805 | 1.8977 | 1359 | 15594.0965 | 1492.8962 | #N/A | #N/A
7911 | OAKLAND K 110217430 | 12101102 | OAKLAND K 1102 | 1.4697 | 15 | 0.035767 | 0.5365 | 1360 | 15595.5662 | 1492.3597 | #N/A | #N/A
88 | SILVERADO 2105658898 | 43432105 | SILVERADO 2105 | 17.1737 | 151 | 0.035763 | 5.4002 | 1361 | 15612.7399 | 1486.9595 | #N/A | 1486.9595
2757 | BURNEY 11011358 | 103311101 | BURNEY 1101 | 8.4314 | 51 | 0.035574 | 1.8143 | 1362 | 15621.1713 | 1485.1452 | #N/A | #N/A
2335 | PLACERVILLE 21067522 | 153082106 | PLACERVILLE 2106 | 67.3656 | 745 | 0.035529 | 26.4689 | 1363 | 15688.537 | 1458.6763 | 1458.6763 | #N/A
10054 | GARBERVILLE 110197300 | 192221101 | GARBERVILLE 1101 | 3.2078 | 32 | 0.035439 | 1.1341 | 1364 | 15691.7448 | 1457.5422 | #N/A | #N/A
2680 | SAN RAMON 2107MR284 | 14232107 | SAN RAMON 2107 | 14.6886 | 134 | 0.035373 | 4.7399 | 1365 | 15706.4333 | 1452.8023 | #N/A | #N/A
6323 | FORT ROSS 112170288 | 42851121 | FORT ROSS 1121 | 11.7339 | 94 | 0.035369 | 3.3247 | 1366 | 15718.1672 | 1449.4776 | #N/A | #N/A
4070 | CLAYTON 2213CB | 12022213 | CLAYTON 2213 | 3.8725 | 51 | 0.03535 | 1.8029 | 1367 | 15722.0398 | 1447.6747 | #N/A | #N/A
5947 | GARCIA 0401666 | 43040401 | GARCIA 0401 | 2.4068 | 12 | 0.035311 | 0.42373 | 1368 | 15724.4466 | 1447.251 | #N/A | #N/A
8699 | UKIAH 1113548420 | 42771113 | UKIAH 1113 | 5.2018 | 54 | 0.035261 | 1.9041 | 1369 | 15729.6484 | 1445.3469 | #N/A | #N/A
7081 | NOVATO 110455398 | 42211104 | NOVATO 1104 | 3.6541 | 82 | 0.035221 | 2.8881 | 1370 | 15733.3025 | 1442.4588 | #N/A | #N/A
2938 | PETALUMA C 110948000 | 42631109 | PETALUMA C 1109 | 9.4991 | 115 | 0.035167 | 4.0442 | 1371 | 15742.8016 | 1438.4145 | #N/A | #N/A
9847 | PENRYN 1105CB | 152561105 | PENRYN 1105 | 0.60814 | 7 | 0.035133 | 0.24593 | 1372 | 15743.4097 | 1438.1686 | #N/A | #N/A
1921 | WYANDOTTE 110641650 | 102911106 | WYANDOTTE 1106 | 1.1575 | 152 | 0.035126 | 5.3392 | 1373 | 15744.5672 | 1432.8294 | #N/A | #N/A
7481 | OTTER 11012052 | 182941101 | OTTER 1101 | 4.8364 | 53 | 0.034981 | 1.854 | 1374 | 15749.4036 | 1430.9754 | #N/A | #N/A
3295 | REDBUD 1102510 | 43191102 | REDBUD 1102 | 4.2062 | 101 | 0.03495 | 3.5299 | 1375 | 15753.6097 | 1427.4454 | #N/A | #N/A
4887 | WOODSIDE 11018972 | 24251101 | WOODSIDE 1101 | 6.2151 | 60 | 0.034933 | 2.096 | 1376 | 15759.8249 | 1425.3494 | #N/A | #N/A
9433 | JAMESON 11028842 | 63801102 | JAMESON 1102 | 0.14985 | 42 | 0.03478 | 1.4608 | 1377 | 15759.9747 | 1423.8887 | #N/A | #N/A
5225 | SHADY GLEN 110248894 | 152431102 | SHADY GLEN 1102 | 8.8833 | 119 | 0.034658 | 4.1244 | 1378 | 15768.858 | 1419.7643 | #N/A | #N/A
4594 | WEIMAR 11012058 | 152491101 | WEIMAR 1101 | 21.327 | 256 | 0.034582 | 8.853 | 1379 | 15790.185 | 1410.9113 | #N/A | #N/A
10315 | CLAYTON 2212523764 | 12022212 | CLAYTON 2212 | 0.11036 | 5 | 0.034478 | 0.17239 | 1380 | 15790.2954 | 1410.7389 | #N/A | #N/A
4872 | SUNOL 1101MR196 | 14241101 | SUNOL 1101 | 3.9361 | 96 | 0.034417 | 3.304 | 1381 | 15794.2315 | 1407.4349 | #N/A | #N/A
1388 | MIWUK 170193062 | 163661701 | MIWUK 1701 | 8.2823 | 84 | 0.034301 | 2.8813 | 1382 | 15802.5138 | 1404.5537 | #N/A | #N/A
10333 | SAN ARDO 1101650772 | 182191101 | SAN ARDO 1101 | 0.78395 | 10 | 0.03426 | 0.3426 | 1383 | 15803.2977 | 1404.2111 | #N/A | #N/A
132 | APPLE HILL 1103CB | 153661103 | APPLE HILL 1103 | 19.3465 | 268 | 0.034245 | 9.1777 | 1384 | 15822.6442 | 1395.0334 | #N/A | #N/A
7451 | LOW GAP 1101CB | 192411101 | LOW GAP 1101 | 2.1692 | 23 | 0.034029 | 0.78267 | 1385 | 15824.8135 | 1394.2507 | #N/A | #N/A
10038 | JESSUP 110194468 | 103441101 | JESSUP 1101 | 1.7135 | 21 | 0.033993 | 0.71385 | 1386 | 15826.527 | 1393.5368 | #N/A | #N/A
3608 | PIT NO 1 11011552 | 103721101 | PIT NO 1 1101 | 14.8177 | 221 | 0.033912 | 7.4946 | 1387 | 15841.3446 | 1386.0422 | #N/A | #N/A
5359 | SAN LUIS OBISPO 1104CB | 182631104 | SAN LUIS OBISPO 1104 | 0.077221 | 65 | 0.033863 | 2.2011 | 1388 | 15841.4218 | 1383.8412 | #N/A | #N/A
9613 | REEDLEY 1112477952 | 252341112 | REEDLEY 1112 | 0.17579 | 14 | 0.033843 | 0.47381 | 1389 | 15841.5976 | 1383.3674 | #N/A | #N/A
6901 | JESSUP 11019752 | 103441101 | JESSUP 1101 | 3.8145 | 41 | 0.033837 | 1.3873 | 1390 | 15845.4121 | 1381.98 | #N/A | #N/A
8898 | RACETRACK 17036014 | 163761703 | RACETRACK 1703 | 6.9405 | 73 | 0.033829 | 2.4695 | 1391 | 15852.3526 | 1379.5105 | #N/A | #N/A
7674 | LLAGAS 21011451 | 83182101 | LLAGAS 2101 | 6.1922 | 61 | 0.03381 | 2.0624 | 1392 | 15858.5448 | 1377.4481 | #N/A | #N/A
5880 | POINT MORETTI 11015076 | 82931101 | POINT MORETTI 1101 | 7.4948 | 67 | 0.033758 | 2.2618 | 1393 | 15866.0396 | 1375.1863 | 1375.1863 | #N/A
8948 | CLARKSVILLE 2109102734 | 153612109 | CLARKSVILLE 2109 | 0.593 | 7 | 0.033754 | 0.23628 | 1394 | 15866.6326 | 1374.9501 | #N/A | #N/A
10958 | CURTIS 170511790 | 163351705 | CURTIS 1705 | 0.014232 | 1 | 0.033732 | 0.033732 | 1395 | 15866.6468 | 1374.9163 | #N/A | #N/A
10247 | MILPITAS 1108342498 | 82831108 | MILPITAS 1108 | 0.030458 | 9 | 0.033722 | 0.3035 | 1396 | 15866.6773 | 1374.6128 | #N/A | #N/A
5434 | MADISON 1105495270 | 63171105 | MADISON 1105 | 0.53656 | 50 | 0.033688 | 1.6844 | 1397 | 15867.2139 | 1372.9284 | #N/A | #N/A
5420 | PETALUMA C 1108600 | 42631108 | PETALUMA C 1108 | 3.7082 | 107 | 0.033514 | 3.586 | 1398 | 15870.9221 | 1369.3425 | #N/A | #N/A
5203 | HALSEY 11012414 | 152241101 | HALSEY 1101 | 14.7877 | 168 | 0.033489 | 5.6261 | 1399 | 15885.7098 | 1363.7163 | #N/A | #N/A
322 | PIKE CITY 11011730 | 152201101 | PIKE CITY 1101 | 8.4807 | 73 | 0.033438 | 2.441 | 1400 | 15894.1905 | 1361.2753 | #N/A | #N/A
5994 | RED BLUFF 11011334 | 103541101 | RED BLUFF 1101 | 1.7937 | 155 | 0.033359 | 5.1706 | 1401 | 15895.9842 | 1356.1047 | #N/A | #N/A
3212 | HALF MOON BAY 1103H82 | 24101103 | HALF MOON BAY 1103 | 32.6223 | 262 | 0.033242 | 8.7095 | 1402 | 15928.6066 | 1347.3952 | #N/A | #N/A
1462 | GIRVAN 11029012 | 103401102 | GIRVAN 1102 | 15.6409 | 176 | 0.033219 | 5.8466 | 1403 | 15944.2475 | 1341.5486 | #N/A | #N/A
10706 | GONZALES 1104807000 | 182131104 | GONZALES 1104 | 0.8417 | 7 | 0.033203 | 0.23242 | 1404 | 15945.0892 | 1341.3162 | #N/A | #N/A
5652 | CORRAL 110214028 | 162991102 | CORRAL 1102 | 3.812 | 103 | 0.033074 | 3.4066 | 1405 | 15948.9012 | 1337.9096 | #N/A | #N/A
7408 | KANAKA 11011044 | 103221101 | KANAKA 1101 | 6.1466 | 17 | 0.033036 | 0.56161 | 1406 | 15955.0478 | 1337.348 | #N/A | #N/A
2114 | WYANDOTTE 11091040 | 102911109 | WYANDOTTE 1109 | 1.046 | 62 | 0.032999 | 2.0459 | 1407 | 15956.0938 | 1335.3021 | #N/A | #N/A
9307 | LINCOLN 11012310 | 153701101 | LINCOLN 1101 | 0.81088 | 34 | 0.032911 | 1.119 | 1408 | 15956.9046 | 1334.1831 | #N/A | #N/A
4870 | BEAR VALLEY 2101CB | 252192101 | BEAR VALLEY 2101 | 18.7781 | 154 | 0.03289 | 5.065 | 1409 | 15975.6828 | 1329.118 | #N/A | #N/A
3833 | APPLE HILL 110412832 | 153661104 | APPLE HILL 1104 | 14.4402 | 166 | 0.032787 | 5.4427 | 1410 | 15990.123 | 1323.6754 | #N/A | #N/A
10090 | TIVY VALLEY 1107599142 | 252941107 | TIVY VALLEY 1107 | 0.35631 | 19 | 0.03274 | 0.62205 | 1411 | 15990.4793 | 1323.0533 | #N/A | #N/A
2297 | STANISLAUS 17011812 | 162821701 | STANISLAUS 1701 | 19.2124 | 234 | 0.032657 | 7.6418 | 1412 | 16009.6917 | 1315.4116 | #N/A | #N/A
8485 | HOLLISTER 2102113634 | 182492102 | HOLLISTER 2102 | 1.8279 | 76 | 0.032654 | 2.4817 | 1413 | 16011.5196 | 1312.9299 | #N/A | #N/A
7193 | ELECTRA 1102CB | 162161102 | ELECTRA 1102 | 2.654 | 7 | 0.032515 | 0.22761 | 1414 | 16014.1736 | 1312.7023 | #N/A | #N/A
5731 | PLACERVILLE 21062224 | 153082106 | PLACERVILLE 2106 | 10.51 | 123 | 0.032512 | 3.999 | 1415 | 16024.6836 | 1308.7033 | #N/A | #N/A
4312 | MENDOCINO 110137462 | 42951101 | MENDOCINO 1101 | 2.3591 | 63 | 0.032457 | 2.0448 | 1416 | 16027.0427 | 1306.6585 | #N/A | #N/A
8959 | OLETA 1101894006 | 163541101 | OLETA 1101 | 0.39028 | 8 | 0.03239 | 0.25912 | 1417 | 16027.433 | 1306.3994 | #N/A | #N/A
4513 | SAN LUIS OBISPO 1104V14 | 182631104 | SAN LUIS OBISPO 1104 | 8.1438 | 69 | 0.03238 | 2.2342 | 1418 | 16035.5768 | 1304.1652 | #N/A | #N/A
4357 | APPLE HILL 11038412 | 153661103 | APPLE HILL 1103 | 19.5828 | 201 | 0.032352 | 6.5027 | 1419 | 16055.1596 | 1297.6625 | #N/A | #N/A
2717 | JOLON 11027002 | 182981102 | JOLON 1102 | 8.3578 | 117 | 0.032323 | 3.7818 | 1420 | 16063.5174 | 1293.8807 | #N/A | #N/A
5768 | BIG BASIN 110210254 | 82841102 | BIG BASIN 1102 | 2.1441 | 11 | 0.03232 | 0.35552 | 1421 | 16065.6615 | 1293.5252 | #N/A | #N/A
5734 | APPLE HILL 1104CB | 153661104 | APPLE HILL 1104 | 4.0885 | 51 | 0.032289 | 1.6467 | 1422 | 16069.75 | 1291.8784 | #N/A | #N/A
7601 | JARVIS 1111907698 | 13501111 | JARVIS 1111 | 1.5329 | 14 | 0.03225 | 0.4515 | 1423 | 16071.2829 | 1291.4269 | #N/A | #N/A
7801 | HALF MOON BAY 11012500 | 24101101 | HALF MOON BAY 1101 | 6.5201 | 74 | 0.032243 | 2.3859 | 1424 | 16077.8029 | 1289.041 | #N/A | #N/A
4135 | BRUNSWICK 11041020 | 152481104 | BRUNSWICK 1104 | 28.7752 | 311 | 0.032187 | 10.0103 | 1425 | 16106.5782 | 1279.0307 | #N/A | #N/A
7772 | FRUITLAND 11422006 | 192311142 | FRUITLAND 1142 | 8.327 | 75 | 0.03216 | 2.412 | 1426 | 16114.9051 | 1276.6187 | #N/A | #N/A
10311 | MADISON 2101760730 | 63172101 | MADISON 2101 | 0.59926 | 17 | 0.032096 | 0.54562 | 1427 | 16115.5044 | 1276.0731 | #N/A | #N/A
1525 | CHALLENGE 11025462 | 103201102 | CHALLENGE 1102 | 23.2735 | 248 | 0.032082 | 7.9564 | 1428 | 16138.7779 | 1268.1167 | #N/A | #N/A
7510 | FRUITLAND 114263170 | 192311142 | FRUITLAND 1142 | 12.4496 | 86 | 0.031951 | 2.7478 | 1429 | 16151.2275 | 1265.3689 | #N/A | #N/A
8635 | MOLINO 11026917 | 42571102 | MOLINO 1102 | 6.9789 | 58 | 0.031941 | 1.8526 | 1430 | 16158.2064 | 1263.5163 | #N/A | #N/A
5301 | REEDLEY 1104887932 | 252341104 | REEDLEY 1104 | 1.698 | 34 | 0.031896 | 1.0845 | 1431 | 16159.9044 | 1262.4319 | #N/A | #N/A
8600 | CALPELLA 1101619542 | 43411101 | CALPELLA 1101 | 1.4967 | 21 | 0.031874 | 0.66935 | 1432 | 16161.4011 | 1261.7625 | #N/A | #N/A
145 | MOUNTAIN QUARRIES 21011130 | 152282101 | MOUNTAIN QUARRIES 2101 | 20.0341 | 231 | 0.031834 | 7.3538 | 1433 | 16181.4353 | 1254.4088 | #N/A | #N/A
8867 | FORESTHILL 110137238 | 152181101 | FORESTHILL 1101 | 11.4259 | 79 | 0.031693 | 2.5038 | 1434 | 16192.8612 | 1251.905 | #N/A | #N/A
10121 | COARSEGOLD 210210610 | 254432102 | COARSEGOLD 2102 | 1.3653 | 22 | 0.031595 | 0.6951 | 1435 | 16194.2265 | 1251.2099 | #N/A | #N/A
8481 | PERRY 110185870 | 183071101 | PERRY 1101 | 11.4413 | 109 | 0.031502 | 3.4337 | 1436 | 16205.6678 | 1247.7762 | #N/A | #N/A
3885 | BELLEVUE 2103478 | 43182103 | BELLEVUE 2103 | 8.3261 | 213 | 0.031296 | 6.6661 | 1437 | 16213.9939 | 1241.1101 | #N/A | #N/A
1942 | UKIAH 1113CB | 42771113 | UKIAH 1113 | 0.046885 | 69 | 0.031266 | 2.1574 | 1438 | 16214.0408 | 1238.9527 | #N/A | #N/A
10742 | GEYSERVILLE 1101463260 | 42891101 | GEYSERVILLE 1101 | 0.54302 | 6 | 0.031168 | 0.18701 | 1439 | 16214.5838 | 1238.7657 | #N/A | #N/A
8417 | CURTIS 1703CB | 163351703 | CURTIS 1703 | 9.0466 | 119 | 0.031137 | 3.7053 | 1440 | 16223.6304 | 1235.0604 | #N/A | #N/A
1279 | ORO FINO 11022556 | 103031102 | ORO FINO 1102 | 6.6622 | 41 | 0.031032 | 1.2723 | 1441 | 16230.2926 | 1233.7881 | #N/A | #N/A
1200 | OCEANO 1106CB | 182601106 | OCEANO 1106 | 1.1261 | 57 | 0.03103 | 1.7687 | 1442 | 16231.4187 | 1232.0194 | #N/A | #N/A
766 | SISQUOC 1103M98 | 182811103 | SISQUOC 1103 | 7.8401 | 56 | 0.030988 | 1.7353 | 1443 | 16239.2588 | 1230.284 | #N/A | #N/A
8592 | STELLING 11109265 | 83481110 | STELLING 1110 | 5.5411 | 45 | 0.03098 | 1.3941 | 1444 | 16244.7999 | 1228.8899 | #N/A | #N/A
5933 | MIRABEL 1102524356 | 42091102 | MIRABEL 1102 | 1.2978 | 29 | 0.030872 | 0.89528 | 1445 | 16246.0977 | 1227.9947 | #N/A | #N/A
802 | ALLEGHANY 1101806 | 152101101 | ALLEGHANY 1101 | 11.2762 | 65 | 0.030867 | 2.0063 | 1446 | 16257.3739 | 1225.9883 | #N/A | #N/A
1506 | GARBERVILLE 11011750 | 192221101 | GARBERVILLE 1101 | 8.4428 | 62 | 0.030822 | 1.911 | 1447 | 16265.8167 | 1224.0773 | #N/A | #N/A
4004 | COARSEGOLD 21025380 | 254432102 | COARSEGOLD 2102 | 14.2766 | 143 | 0.030806 | 4.4053 | 1448 | 16280.0933 | 1219.672 | #N/A | #N/A
1308 | RINCON 1101578 | 43321101 | RINCON 1101 | 17.1022 | 170 | 0.030756 | 5.2285 | 1449 | 16297.1955 | 1214.4436 | #N/A | #N/A
10309 | BOLINAS 1101806 | 42261101 | BOLINAS 1101 | 3.0444 | 17 | 0.030667 | 0.52134 | 1450 | 16300.2399 | 1213.9222 | #N/A | #N/A
6983 | BASALT 1106657038 | 42461106 | BASALT 1106 | 2.5995 | 72 | 0.030657 | 2.2073 | 1451 | 16302.8394 | 1211.715 | #N/A | #N/A
3194 | DIAMOND SPRINGS 1103467046 | 152261103 | DIAMOND SPRINGS 1103 | 15.3228 | 266 | 0.030581 | 8.1346 | 1452 | 16318.1622 | 1203.5803 | #N/A | #N/A
4703 | WISE 1101CB | 152271101 | WISE 1101 | 4.7624 | 112 | 0.030561 | 3.4229 | 1453 | 16322.9246 | 1200.1575 | #N/A | #N/A
6843 | DUNBAR 11033127 | 43071103 | DUNBAR 1103 | 9.3565 | 78 | 0.030422 | 2.3729 | 1454 | 16332.2811 | 1197.7845 | #N/A | #N/A
3373 | VOLTA 11021646 | 102541102 | VOLTA 1102 | 23.9497 | 215 | 0.030417 | 6.5396 | 1455 | 16356.2307 | 1191.2449 | #N/A | #N/A
9167 | WILDWOOD 1101CB | 103611101 | WILDWOOD 1101 | 0.12484 | 2 | 0.030413 | 0.060827 | 1456 | 16356.3556 | 1191.1841 | #N/A | #N/A
1377 | FROGTOWN 170211212 | 163451702 | FROGTOWN 1702 | 22.3393 | 155 | 0.030264 | 4.691 | 1457 | 16378.6949 | 1186.4931 | #N/A | #N/A
2196 | ATASCADERO 1101A02 | 182541101 | ATASCADERO 1101 | 25.4858 | 253 | 0.030233 | 7.649 | 1458 | 16404.1807 | 1178.844 | #N/A | #N/A
6596 | STELLING 111060090 | 83481110 | STELLING 1110 | 6.554 | 62 | 0.030171 | 1.8706 | 1459 | 16410.7347 | 1176.9735 | #N/A | #N/A
6029 | PANORAMA 1101713592 | 103461101 | PANORAMA 1101 | 10.3886 | 152 | 0.030005 | 4.5608 | 1460 | 16421.1233 | 1172.4126 | #N/A | #N/A
3261 | CRESCENT MILLS 2101CB | 103132101 | CRESCENT MILLS 2101 | 2.8253 | 60 | 0.029932 | 1.7959 | 1461 | 16423.9486 | 1170.6167 | #N/A | #N/A
4399 | PLACERVILLE 210619552 | 153082106 | PLACERVILLE 2106 | 21.3424 | 238 | 0.029928 | 7.123 | 1462 | 16445.291 | 1163.4937 | #N/A | #N/A
10240 | LLAGAS 2105534019 | 83182105 | LLAGAS 2105 | 0.71346 | 5 | 0.029893 | 0.14947 | 1463 | 16446.0045 | 1163.3442 | #N/A | #N/A
5361 | HOOPA 11013174 | 192401101 | HOOPA 1101 | 18.4899 | 162 | 0.029875 | 4.8397 | 1464 | 16464.4943 | 1158.5046 | #N/A | #N/A
5027 | PEORIA 17048040 | 163781704 | PEORIA 1704 | 7.325 | 145 | 0.02987 | 4.3312 | 1465 | 16471.8194 | 1154.1733 | #N/A | #N/A
9000 | CASTRO VALLEY 11088971 | 14091108 | CASTRO VALLEY 1108 | 7.9032 | 72 | 0.029749 | 2.1419 | 1466 | 16479.7226 | 1152.0314 | #N/A | #N/A
3972 | CORRAL 1103936674 | 162991103 | CORRAL 1103 | 0.66102 | 56 | 0.029729 | 1.6648 | 1467 | 16480.3836 | 1150.3666 | #N/A | #N/A
5038 | MOLINO 110241392 | 42571102 | MOLINO 1102 | 4.3895 | 171 | 0.029696 | 5.078 | 1468 | 16484.7731 | 1145.2886 | #N/A | #N/A
8758 | PUTAH CREEK 11033783 | 63681103 | PUTAH CREEK 1103 | 0.088571 | 96 | 0.029685 | 2.8498 | 1469 | 16484.8617 | 1142.4388 | #N/A | #N/A
10009 | OREGON TRAIL 110346860 | 103521103 | OREGON TRAIL 1103 | 0.71448 | 15 | 0.029648 | 0.44471 | 1470 | 16485.5761 | 1141.9941 | #N/A | #N/A
944 | CURTIS 17036064 | 163351703 | CURTIS 1703 | 18.9875 | 199 | 0.029564 | 5.8832 | 1471 | 16504.5637 | 1136.1109 | #N/A | #N/A
5754 | SANTA YNEZ 1102Y18 | 182721102 | SANTA YNEZ 1102 | 4.8831 | 60 | 0.029555 | 1.7733 | 1472 | 16509.4468 | 1134.3376 | #N/A | #N/A
1748 | CLAY 110113450 | 163341101 | CLAY 1101 | 0.93803 | 42 | 0.029532 | 1.2403 | 1473 | 16510.3848 | 1133.0972 | #N/A | #N/A
2073 | WILLOW CREEK 11032936 | 192171103 | WILLOW CREEK 1103 | 33.1751 | 249 | 0.029513 | 7.3486 | 1474 | 16543.5599 | 1125.7486 | #N/A | #N/A
3589 | MIRABEL 1101688780 | 42091101 | MIRABEL 1101 | 0.57358 | 14 | 0.029456 | 0.41239 | 1475 | 16544.1334 | 1125.3362 | #N/A | #N/A
4182 | GARBERVILLE 11021510 | 192221102 | GARBERVILLE 1102 | 13.1584 | 107 | 0.029417 | 3.1476 | 1476 | 16557.2918 | 1122.1886 | #N/A | #N/A
3154 | CALISTOGA 1102634 | 42711102 | CALISTOGA 1102 | 11.216 | 178 | 0.029373 | 5.2284 | 1477 | 16568.5078 | 1116.9603 | #N/A | 1116.9603
133 | GEYSERVILLE 1102522 | 42891102 | GEYSERVILLE 1102 | 8.0023 | 109 | 0.029361 | 3.2003 | 1478 | 16576.5102 | 1113.76 | #N/A | #N/A
10360 | OLEMA 110175686 | 42291101 | OLEMA 1101 | 4.6305 | 31 | 0.029281 | 0.90772 | 1479 | 16581.1406 | 1112.8523 | #N/A | #N/A
9801 | KANAKA 1101CB | 103221101 | KANAKA 1101 | 4.7271 | 37 | 0.029281 | 1.0834 | 1480 | 16585.8678 | 1111.7689 | 1111.7689 | #N/A
4062 | WHITMORE 1101CB | 103601101 | WHITMORE 1101 | 5.9029 | 69 | 0.029248 | 2.0181 | 1481 | 16591.7707 | 1109.7508 | #N/A | #N/A
1547 | WILLITS 110391810 | 42661103 | WILLITS 1103 | 29.4465 | 296 | 0.029203 | 8.6442 | 1482 | 16621.2172 | 1101.1066 | #N/A | #N/A
8861 | GEYSERVILLE 1102331444 | 42891102 | GEYSERVILLE 1102 | 2.225 | 44 | 0.029048 | 1.2781 | 1483 | 16623.4421 | 1099.8285 | #N/A | #N/A
3080 | PIKE CITY 1101CB | 152201101 | PIKE CITY 1101 | 19.6536 | 162 | 0.029034 | 4.7034 | 1484 | 16643.0957 | 1095.125 | #N/A | #N/A
9245 | FRUITLAND 1142899734 | 192311142 | FRUITLAND 1142 | 3.4006 | 36 | 0.028754 | 1.0351 | 1485 | 16646.4963 | 1094.0899 | #N/A | #N/A
2842 | SAN LUIS OBISPO 1101CB | 182631101 | SAN LUIS OBISPO 1101 | 3.5923 | 75 | 0.028742 | 2.1556 | 1486 | 16650.0886 | 1091.9342 | #N/A | #N/A
8606 | PUEBLO 1105684564 | 43291105 | PUEBLO 1105 | 0.27557 | 28 | 0.02858 | 0.80024 | 1487 | 16650.3641 | 1091.134 | #N/A | #N/A
3749 | VINEYARD 2107978364 | 14502107 | VINEYARD 2107 | 0.96809 | 36 | 0.028543 | 1.0276 | 1488 | 16651.3322 | 1090.1064 | #N/A | #N/A
1264 | TEMPLETON 2113CB | 183052113 | TEMPLETON 2113 | 0.899 | 288 | 0.028499 | 8.2077 | 1489 | 16652.2312 | 1081.8987 | #N/A | #N/A
6493 | POINT ARENA 11013702 | 43381101 | POINT ARENA 1101 | 4.8876 | 35 | 0.028477 | 0.99668 | 1490 | 16657.1188 | 1080.902 | #N/A | #N/A
2973 | TEMPLETON 2111R86 | 183052111 | TEMPLETON 2111 | 10.9225 | 160 | 0.028407 | 4.5451 | 1491 | 16668.0413 | 1076.3569 | #N/A | #N/A
2170 | MC KEE 1111711900 | 83531111 | MC KEE 1111 | 8.9846 | 116 | 0.028347 | 3.2883 | 1492 | 16677.0259 | 1073.0686 | #N/A | #N/A
7676 | JARVIS 1108289662 | 13501108 | JARVIS 1108 | 0.33148 | 11 | 0.028227 | 0.31049 | 1493 | 16677.3574 | 1072.7581 | #N/A | #N/A
5235 | BELLEVUE 2103648 | 43182103 | BELLEVUE 2103 | 3.802 | 187 | 0.028161 | 5.2662 | 1494 | 16681.1594 | 1067.492 | #N/A | #N/A
10298 | PIT NO 5 11011618 | 101321101 | PIT NO 5 1101 | 6.0573 | 15 | 0.028087 | 0.42131 | 1495 | 16687.2167 | 1067.0706 | #N/A | #N/A
5972 | TASSAJARA 2104CB | 14662104 | TASSAJARA 2104 | 0.098921 | 22 | 0.028017 | 0.61638 | 1496 | 16687.3156 | 1066.4543 | #N/A | #N/A
2469 | ELECTRA 11026014 | 162161102 | ELECTRA 1102 | 4.9988 | 50 | 0.027926 | 1.3963 | 1497 | 16692.3144 | 1065.058 | #N/A | #N/A
1225 | SUNOL 1101MR298 | 14241101 | SUNOL 1101 | 5.1238 | 39 | 0.027925 | 1.0891 | 1498 | 16697.4382 | 1063.9689 | #N/A | #N/A
739 | COTATI 1105CB | 42271105 | COTATI 1105 | 2.6781 | 35 | 0.027854 | 0.97488 | 1499 | 16700.1163 | 1062.994 | #N/A | #N/A
1612 | CABRILLO 1104Y22 | 183101104 | CABRILLO 1104 | 10.3926 | 178 | 0.027743 | 4.9383 | 1500 | 16710.5089 | 1058.0558 | #N/A | #N/A
2769 | ANNAPOLIS 110176842 | 42861101 | ANNAPOLIS 1101 | 5.6909 | 33 | 0.027724 | 0.91488 | 1501 | 16716.1998 | 1057.1409 | #N/A | #N/A
2631 | TEMPLETON 2111A66 | 183052111 | TEMPLETON 2111 | 33.7563 | 429 | 0.027639 | 11.8573 | 1502 | 16749.9561 | 1045.2836 | #N/A | #N/A
2379 | SAN LUIS OBISPO 1103CB | 182631103 | SAN LUIS OBISPO 1103 | 0 | 68 | 0.027594 | 1.8764 | 1503 | 16749.9561 | 1043.4072 | #N/A | #N/A
4288 | SAN LUIS OBISPO 1103V82 | 182631103 | SAN LUIS OBISPO 1103 | 8.7819 | 174 | 0.027572 | 4.7975 | 1504 | 16758.738 | 1038.6096 | #N/A | #N/A
3496 | APPLE HILL 21027502 | 153662102 | APPLE HILL 2102 | 22.9542 | 267 | 0.027532 | 7.351 | 1505 | 16781.6922 | 1031.2586 | #N/A | #N/A
3795 | SAN LUIS OBISPO 1101V12 | 182631101 | SAN LUIS OBISPO 1101 | 21.0492 | 127 | 0.027414 | 3.4815 | 1506 | 16802.7414 | 1027.7771 | #N/A | #N/A
5816 | PAUL SWEET 210710986 | 83252107 | PAUL SWEET 2107 | 9.3155 | 180 | 0.027411 | 4.9339 | 1507 | 16812.0569 | 1022.8431 | #N/A | #N/A
9709 | LAYTONVILLE 1102682 | 42681102 | LAYTONVILLE 1102 | 14.8195 | 97 | 0.027282 | 2.6464 | 1508 | 16826.8764 | 1020.1968 | #N/A | #N/A
1461 | LOS OSITOS 21033010 | 182082103 | LOS OSITOS 2103 | 31.1134 | 229 | 0.027281 | 6.2474 | 1509 | 16857.9898 | 1013.9493 | #N/A | #N/A
6161 | HIGHLANDS 1102556 | 43361102 | HIGHLANDS 1102 | 0.1777 | 90 | 0.027227 | 2.4505 | 1510 | 16858.1674 | 1011.4989 | #N/A | #N/A
8442 | MARTELL 11016074 | 163011101 | MARTELL 1101 | 3.6816 | 34 | 0.027132 | 0.92248 | 1511 | 16861.849 | 1010.5764 | #N/A | #N/A
7912 | HALF MOON BAY 1101818874 | 24101101 | HALF MOON BAY 1101 | 5.6859 | 42 | 0.02708 | 1.1374 | 1512 | 16867.5349 | 1009.439 | #N/A | #N/A
5790 | HIGGINS 1110869408 | 152691110 | HIGGINS 1110 | 0.44171 | 6 | 0.027041 | 0.16225 | 1513 | 16867.9766 | 1009.2768 | #N/A | #N/A
9590 | OILFIELDS 11037006 | 182391103 | OILFIELDS 1103 | 0 | 42 | 0.027015 | 1.1346 | 1514 | 16867.9766 | 1008.1421 | #N/A | #N/A
9570 | SWIFT 2102889948 | 83392102 | SWIFT 2102 | 0.43933 | 8 | 0.026886 | 0.21509 | 1515 | 16868.4159 | 1007.927 | #N/A | #N/A
9335 | SAN MIGUEL 1106N34 | 182661106 | SAN MIGUEL 1106 | 3.7549 | 62 | 0.02675 | 1.6585 | 1516 | 16872.1708 | 1006.2685 | #N/A | #N/A
8060 | MONTE RIO 1112120 | 42811112 | MONTE RIO 1112 | 6.4178 | 67 | 0.026687 | 1.788 | 1517 | 16878.5886 | 1004.4805 | #N/A | #N/A
2780 | HIGHLANDS 1102CB | 43361102 | HIGHLANDS 1102 | 7.4098 | 78 | 0.026652 | 2.0789 | 1518 | 16885.9984 | 1002.4017 | #N/A | #N/A
5253 | HOOPA 110182542 | 192401101 | HOOPA 1101 | 12.1274 | 150 | 0.026646 | 3.9969 | 1519 | 16898.1259 | 998.4048 | #N/A | #N/A
9493 | BRUNSWICK 1103904574 | 152481103 | BRUNSWICK 1103 | 1.5654 | 25 | 0.026628 | 0.6657 | 1520 | 16899.6913 | 997.7391 | #N/A | #N/A
2834 | WILLOW PASS 1101CB | 13911101 | WILLOW PASS 1101 | 1.1805 | 75 | 0.026552 | 1.9914 | 1521 | 16900.8718 | 995.7477 | #N/A | #N/A
4322 | WYANDOTTE 11095973 | 102911109 | WYANDOTTE 1109 | 0.085914 | 35 | 0.026544 | 0.92904 | 1522 | 16900.9577 | 994.8186 | #N/A | #N/A
9896 | PUEBLO 2102773926 | 43292102 | PUEBLO 2102 | 0.43924 | 25 | 0.026524 | 0.66311 | 1523 | 16901.3969 | 994.1555 | #N/A | #N/A
7392 | WINDSOR 1103CB | 43501103 | WINDSOR 1103 | 0 | 64 | 0.026458 | 1.6933 | 1524 | 16901.3969 | 992.4623 | #N/A | #N/A
7312 | PEABODY 2113CB | 63642113 | PEABODY 2113 | 0.36506 | 40 | 0.026426 | 1.057 | 1525 | 16901.762 | 991.4052 | #N/A | #N/A
5020 | BONNIE NOOK 1101CB | 152301101 | BONNIE NOOK 1101 | 14.4507 | 153 | 0.026396 | 4.0386 | 1526 | 16916.2126 | 987.3666 | #N/A | #N/A
2080 | NEWBURG 11313446 | 192151131 | NEWBURG 1131 | 0.29522 | 87 | 0.026372 | 2.2944 | 1527 | 16916.5079 | 985.0722 | #N/A | #N/A
5621 | FORT ROSS 112137326 | 42851121 | FORT ROSS 1121 | 5.1046 | 31 | 0.026358 | 0.8171 | 1528 | 16921.6124 | 984.2551 | #N/A | #N/A
7707 | SUMMIT 110148632 | 152591101 | SUMMIT 1101 | 2.7294 | 38 | 0.026323 | 1.0003 | 1529 | 16924.3418 | 983.2548 | #N/A | #N/A
4086 | WEST POINT 110236676 | 163201102 | WEST POINT 1102 | 16.9707 | 173 | 0.026145 | 4.5232 | 1530 | 16941.3126 | 978.7317 | #N/A | #N/A
3634 | CHALLENGE 11021902 | 103201102 | CHALLENGE 1102 | 4.8728 | 44 | 0.026064 | 1.1468 | 1531 | 16946.1854 | 977.5849 | #N/A | #N/A
5849 | HOPLAND 11011100 | 42251101 | HOPLAND 1101 | 3.7166 | 68 | 0.026059 | 1.772 | 1532 | 16949.9019 | 975.8128 | #N/A | #N/A
9887 | NOVATO 1104676060 | 42211104 | NOVATO 1104 | 0.44921 | 9 | 0.026046 | 0.23441 | 1533 | 16950.3511 | 975.5784 | #N/A | #N/A
6186 | CALAVERAS CEMENT 110111188 | 162211101 | CALAVERAS CEMENT 1101 | 29.9581 | 294 | 0.02599 | 7.641 | 1534 | 16980.3092 | 967.9374 | #N/A | #N/A
6575 | CLARK ROAD 110247006 | 103091102 | CLARK ROAD 1102 | 4.4715 | 51 | 0.025936 | 1.3227 | 1535 | 16984.7807 | 966.6146 | #N/A | #N/A
5041 | MARTELL 1103CB | 163011103 | MARTELL 1103 | 1.7681 | 76 | 0.025924 | 1.9702 | 1536 | 16986.5488 | 964.6444 | #N/A | #N/A
7535 | PARADISE 11042034 | 102831104 | PARADISE 1104 | 10.9756 | 99 | 0.025842 | 2.5583 | 1537 | 16997.5244 | 962.0861 | #N/A | #N/A
3586 | PENRYN 1107346 | 152561107 | PENRYN 1107 | 14.0643 | 309 | 0.025706 | 7.9433 | 1538 | 17011.5887 | 954.1428 | #N/A | #N/A
8624 | JESSUP 11012839 | 103441101 | JESSUP 1101 | 1.4657 | 20 | 0.02569 | 0.5138 | 1539 | 17013.0544 | 953.629 | #N/A | #N/A
2763 | GOLDTREE 1108CB | 182581108 | GOLDTREE 1108 | 2.2661 | 50 | 0.025673 | 1.2836 | 1540 | 17015.3205 | 952.3454 | #N/A | #N/A
9750 | COVELO 1101430286 | 43061101 | COVELO 1101 | 3.6933 | 13 | 0.025652 | 0.33348 | 1541 | 17019.0138 | 952.0119 | #N/A | #N/A
8494 | BRENTWOOD 2105502672 | 14592105 | BRENTWOOD 2105 | 1.4203 | 127 | 0.025636 | 3.2558 | 1542 | 17020.4341 | 948.7561 | #N/A | #N/A
5780 | GREEN VALLEY 210111054 | 83192101 | GREEN VALLEY 2101 | 24.3425 | 272 | 0.025605 | 6.9646 | 1543 | 17044.7766 | 941.7916 | #N/A | #N/A
5526 | LLAGAS 2107XR188 | 83182107 | LLAGAS 2107 | 0.37797 | 43 | 0.025596 | 1.1006 | 1544 | 17045.1546 | 940.6909 | #N/A | #N/A
3427 | COTATI 1105616 | 42271105 | COTATI 1105 | 2.6399 | 198 | 0.025585 | 5.0659 | 1545 | 17047.7944 | 935.625 | #N/A | #N/A
9956 | CLARKSVILLE 2109781566 | 153612109 | CLARKSVILLE 2109 | 0.69205 | 11 | 0.025518 | 0.28069 | 1546 | 17048.4865 | 935.3443 | #N/A | #N/A
1199 | BEAR VALLEY 21059560 | 252192105 | BEAR VALLEY 2105 | 22.0236 | 226 | 0.025353 | 5.7297 | 1547 | 17070.5101 | 929.6146 | #N/A | #N/A
4849 | ELECTRA 11017104 | 162161101 | ELECTRA 1101 | 12.0762 | 148 | 0.025302 | 3.7447 | 1548 | 17082.5863 | 925.87 | #N/A | #N/A
4914 | JESSUP 11019002 | 103441101 | JESSUP 1101 | 0.97482 | 74 | 0.025292 | 1.8716 | 1549 | 17083.5611 | 923.9984 | #N/A | #N/A
6329 | SILVERADO 2102636 | 43432102 | SILVERADO 2102 | 5.465 | 81 | 0.025287 | 2.0483 | 1550 | 17089.0262 | 921.9501 | #N/A | #N/A
7235 | BRIDGEVILLE 110137484 | 192461101 | BRIDGEVILLE 1101 | 7.8861 | 74 | 0.025267 | 1.8698 | 1551 | 17096.9122 | 920.0803 | #N/A | #N/A
4335 | UKIAH 1114844294 | 42771114 | UKIAH 1114 | 2.4113 | 55 | 0.025242 | 1.3883 | 1552 | 17099.3235 | 918.692 | #N/A | #N/A
5817 | TIVY VALLEY 110737522 | 252941107 | TIVY VALLEY 1107 | 0.5181 | 43 | 0.025221 | 1.0845 | 1553 | 17099.8416 | 917.6075 | #N/A | #N/A
402 | REDBUD 1102922 | 43191102 | REDBUD 1102 | 7.8244 | 84 | 0.025187 | 2.1157 | 1554 | 17107.666 | 915.4918 | #N/A | #N/A
4837 | SAN LUIS OBISPO 1104V46 | 182631104 | SAN LUIS OBISPO 1104 | 19.9362 | 206 | 0.025184 | 5.1879 | 1555 | 17127.6022 | 910.3039 | #N/A | #N/A
6418 | DUNLAP 1102CB | 254061102 | DUNLAP 1102 | 6.7372 | 79 | 0.025156 | 1.9873 | 1556 | 17134.3394 | 908.3166 | #N/A | #N/A
8607 | ANNAPOLIS 1101608 | 42861101 | ANNAPOLIS 1101 | 17.8111 | 74 | 0.025135 | 1.86 | 1557 | 17152.1505 | 906.4566 | #N/A | #N/A
8805 | FRUITLAND 114293234 | 192311142 | FRUITLAND 1142 | 11.4803 | 96 | 0.025062 | 2.4059 | 1558 | 17163.6308 | 904.0507 | #N/A | #N/A
3300 | FULTON 1102CB | 42561102 | FULTON 1102 | 0.20314 | 48 | 0.025061 | 1.2029 | 1559 | 17163.8339 | 902.8477 | #N/A | #N/A
4515 | GIRVAN 11019732 | 103401101 | GIRVAN 1101 | 20.9813 | 267 | 0.025046 | 6.6872 | 1560 | 17184.8152 | 896.1605 | #N/A | #N/A
602 | STAFFORD 1102524 | 43201102 | STAFFORD 1102 | 6.1352 | 162 | 0.02502 | 4.0533 | 1561 | 17190.9504 | 892.1072 | #N/A | #N/A
6121 | OTTER 110263868 | 182941102 | OTTER 1102 | 15.8771 | 171 | 0.024964 | 4.2689 | 1562 | 17206.8275 | 887.8383 | #N/A | #N/A
4102 | SPAULDING 1101578852 | 152251101 | SPAULDING 1101 | 20.6406 | 173 | 0.024946 | 4.3156 | 1563 | 17227.4681 | 883.5227 | #N/A | #N/A
9390 | COAST RD 04015134 | 88820401 | COAST RD 0401 | 0.63308 | 23 | 0.024922 | 0.57321 | 1564 | 17228.1011 | 882.9495 | #N/A | #N/A
9959 | BRIDGEVILLE 1102384530 | 192461102 | BRIDGEVILLE 1102 | 3.8189 | 12 | 0.024779 | 0.29735 | 1565 | 17231.9201 | 882.6522 | #N/A | #N/A
2322 | KANAKA 11011034 | 103221101 | KANAKA 1101 | 11.1511 | 80 | 0.024689 | 1.9751 | 1566 | 17243.0711 | 880.6771 | #N/A | #N/A
5230 | BANGOR 11011806 | 103191101 | BANGOR 1101 | 4.0291 | 17 | 0.024567 | 0.41764 | 1567 | 17247.1003 | 880.2594 | #N/A | #N/A
4084 | JOLON 11027040 | 182981102 | JOLON 1102 | 20.8303 | 119 | 0.02433 | 2.8953 | 1568 | 17267.9305 | 877.3642 | #N/A | #N/A
7751 | MIWUK 17018050 | 163661701 | MIWUK 1701 | 12.1121 | 137 | 0.024311 | 3.3307 | 1569 | 17280.0426 | 874.0335 | #N/A | #N/A
10676 | KERN OIL 1106397902 | 252721106 | KERN OIL 1106 | 0.44595 | 9 | 0.024302 | 0.21872 | 1570 | 17280.4885 | 873.8148 | #N/A | #N/A
5615 | ELECTRA 110161816 | 162161101 | ELECTRA 1101 | 23.5096 | 228 | 0.0243 | 5.5405 | 1571 | 17303.9981 | 868.2743 | #N/A | #N/A
801 | OCEANO 1102CB | 182601102 | OCEANO 1102 | 15.8171 | 183 | 0.024236 | 4.4352 | 1572 | 17319.8153 | 863.8391 | #N/A | #N/A
8403 | MOLINO 1101472660 | 42571101 | MOLINO 1101 | 1.4504 | 18 | 0.024226 | 0.43606 | 1573 | 17321.2657 | 863.403 | #N/A | #N/A
4244 | BRUNSWICK 1104CB | 152481104 | BRUNSWICK 1104 | 0.38641 | 28 | 0.024194 | 0.67743 | 1574 | 17321.6521 | 862.7256 | #N/A | #N/A
10152 | SPENCE 1102321000 | 182201102 | SPENCE 1102 | 1.4483 | 13 | 0.024187 | 0.31443 | 1575 | 17323.1004 | 862.4112 | #N/A | #N/A
3391 | COTATI 1105734248 | 42271105 | COTATI 1105 | 0.48145 | 9 | 0.024166 | 0.2175 | 1576 | 17323.5819 | 862.1937 | #N/A | #N/A
9545 | WYANDOTTE 110942650 | 102911109 | WYANDOTTE 1109 | 0.90716 | 37 | 0.024082 | 0.89104 | 1577 | 17324.489 | 861.3026 | #N/A | #N/A
4392 | CLARK ROAD 110290548 | 103091102 | CLARK ROAD 1102 | 17.9431 | 168 | 0.024003 | 4.0325 | 1578 | 17342.4321 | 857.2701 | #N/A | #N/A
9548 | FROGTOWN 1702224708 | 163451702 | FROGTOWN 1702 | 0.64211 | 9 | 0.02399 | 0.21591 | 1579 | 17343.0743 | 857.0542 | #N/A | #N/A
2473 | COLUMBIA HILL 110135424 | 152471101 | COLUMBIA HILL 1101 | 13.8646 | 147 | 0.023757 | 3.4923 | 1580 | 17356.9388 | 853.5619 | #N/A | #N/A
3207 | SHADY GLEN 110151696 | 152431101 | SHADY GLEN 1101 | 17.4501 | 238 | 0.023753 | 5.6532 | 1581 | 17374.3889 | 847.9088 | #N/A | #N/A
7684 | PETALUMA C 1109738866 | 42631109 | PETALUMA C 1109 | 2.0387 | 28 | 0.023732 | 0.66451 | 1582 | 17376.4276 | 847.2443 | #N/A | #N/A
10885 | MORGAN HILL 2111940112 | 83242111 | MORGAN HILL 2111 | 0.2828 | 2 | 0.023701 | 0.047401 | 1583 | 17376.7104 | 847.1969 | #N/A | #N/A
10683 | SAN BERNARD 1101438074 | 253191101 | SAN BERNARD 1101 | 0.32085 | 6 | 0.023646 | 0.14187 | 1584 | 17377.0313 | 847.055 | #N/A | #N/A
274 | GEYSERVILLE 1102350 | 42891102 | GEYSERVILLE 1102 | 5.199 | 194 | 0.023632 | 4.5846 | 1585 | 17382.2303 | 842.4704 | #N/A | #N/A
6780 | FOOTHILL 1102CB | 182951102 | FOOTHILL 1102 | 7.8927 | 97 | 0.023627 | 2.2918 | 1586 | 17390.123 | 840.1786 | #N/A | #N/A
5469 | FROGTOWN 1701L3361 | 163451701 | FROGTOWN 1701 | 1.8743 | 21 | 0.023616 | 0.49595 | 1587 | 17391.9973 | 839.6827 | #N/A | #N/A
279 | GEYSERVILLE 1101122 | 42891101 | GEYSERVILLE 1101 | 1.3131 | 54 | 0.023602 | 1.2745 | 1588 | 17393.3103 | 838.4082 | #N/A | #N/A
1737 | FORT BRAGG A 110195294 | 42761101 | FORT BRAGG A 1101 | 27.0321 | 186 | 0.023449 | 4.3615 | 1589 | 17420.3425 | 834.0467 | #N/A | #N/A
1091 | COLUMBIA HILL 1101764 | 152471101 | COLUMBIA HILL 1101 | 14.6945 | 146 | 0.023389 | 3.4148 | 1590 | 17435.037 | 830.6318 | #N/A | #N/A
9377 | COVELO 1101516510 | 43061101 | COVELO 1101 | 3.7746 | 73 | 0.02337 | 1.706 | 1591 | 17438.8116 | 828.9258 | #N/A | #N/A
2700 | PINE GROVE 11023172 | 163751102 | PINE GROVE 1102 | 37.6855 | 448 | 0.023346 | 10.4588 | 1592 | 17476.4971 | 818.4669 | #N/A | #N/A
10187 | LLAGAS 2105154256 | 83182105 | LLAGAS 2105 | 0.26763 | 2 | 0.023318 | 0.046636 | 1593 | 17476.7647 | 818.4203 | #N/A | #N/A
8561 | FROGTOWN 1702307998 | 163451702 | FROGTOWN 1702 | 0.5565 | 6 | 0.023314 | 0.13989 | 1594 | 17477.3212 | 818.2804 | #N/A | #N/A
4078 | PENNGROVE 1101170 | 43471101 | PENNGROVE 1101 | 17.9647 | 223 | 0.023285 | 5.1925 | 1595 | 17495.286 | 813.0879 | #N/A | #N/A
7270 | LAKEVILLE 1102347280 | 43371102 | LAKEVILLE 1102 | 7.9316 | 99 | 0.023256 | 2.3024 | 1596 | 17503.2176 | 810.7855 | #N/A | #N/A
2895 | ALHAMBRA 11058302 | 14101105 | ALHAMBRA 1105 | 8.1754 | 83 | 0.023206 | 1.9261 | 1597 | 17511.393 | 808.8594 | #N/A | #N/A
9502 | WILLOW CREEK 11033090 | 192171103 | WILLOW CREEK 1103 | 10.8102 | 58 | 0.023177 | 1.3443 | 1598 | 17522.2032 | 807.5152 | #N/A | #N/A
6394 | ORO FINO 11022040 | 103031102 | ORO FINO 1102 | 9.1516 | 21 | 0.023168 | 0.48652 | 1599 | 17531.3548 | 807.0286 | #N/A | #N/A
2990 | HICKS 2101XR548 | 83432101 | HICKS 2101 | 1.6831 | 95 | 0.023159 | 2.2001 | 1600 | 17533.0379 | 804.8285 | #N/A | #N/A
633 | RACETRACK 170310870 | 163761703 | RACETRACK 1703 | 1.909 | 28 | 0.023077 | 0.64616 | 1601 | 17534.9469 | 804.1824 | #N/A | #N/A
4692 | PINE GROVE 11023168 | 163751102 | PINE GROVE 1102 | 29.9741 | 285 | 0.023045 | 6.5678 | 1602 | 17564.921 | 797.6146 | #N/A | #N/A
10488 | HALF MOON BAY 1103531594 | 24101103 | HALF MOON BAY 1103 | 2.4852 | 25 | 0.022917 | 0.57293 | 1603 | 17567.4062 | 797.0416 | #N/A | #N/A
1419 | CURTIS 17048140 | 163351704 | CURTIS 1704 | 26.3871 | 260 | 0.022915 | 5.958 | 1604 | 17593.7934 | 791.0836 | #N/A | #N/A
5050 | ATASCADERO 1101A22 | 182541101 | ATASCADERO 1101 | 0 | 167 | 0.022889 | 3.8224 | 1605 | 17593.7934 | 787.2613 | #N/A | #N/A
10722 | TASSAJARA 2103557000 | 14662103 | TASSAJARA 2103 | 0.20822 | 3 | 0.022855 | 0.068564 | 1606 | 17594.0016 | 787.1927 | #N/A | #N/A
4033 | GANSNER 11012006 | 103021101 | GANSNER 1101 | 17.1356 | 151 | 0.022834 | 3.4479 | 1607 | 17611.1372 | 783.7448 | #N/A | #N/A
5518 | BIG BEND 1101641808 | 103751101 | BIG BEND 1101 | 25.7525 | 234 | 0.022822 | 5.3404 | 1608 | 17636.8897 | 778.4044 | #N/A | #N/A
8814 | CLAY 11037142 | 163341103 | CLAY 1103 | 3.9003 | 100 | 0.022773 | 2.2773 | 1609 | 17640.7899 | 776.1271 | #N/A | #N/A
9514 | HALF MOON BAY 110258448 | 24101102 | HALF MOON BAY 1102 | 4.4382 | 22 | 0.022766 | 0.50086 | 1610 | 17645.2282 | 775.6262 | #N/A | #N/A
4404 | EEL RIVER 1102630456 | 192381102 | EEL RIVER 1102 | 5.3553 | 37 | 0.022761 | 0.84216 | 1611 | 17650.5834 | 774.784 | #N/A | #N/A
9626 | SAUSALITO 110284278 | 42491102 | SAUSALITO 1102 | 1.5476 | 18 | 0.022717 | 0.4089 | 1612 | 17652.1311 | 774.3751 | #N/A | #N/A
5345 | ELK 11011300 | 42981101 | ELK 1101 | 3.5496 | 64 | 0.02261 | 1.447 | 1613 | 17655.6806 | 772.9281 | #N/A | #N/A
3272 | KESWICK 11019712 | 103451101 | KESWICK 1101 | 18.589 | 214 | 0.022607 | 4.838 | 1614 | 17674.2697 | 768.0901 | #N/A | #N/A
7529 | EEL RIVER 11021902 | 192381102 | EEL RIVER 1102 | 6.5648 | 43 | 0.022585 | 0.97115 | 1615 | 17680.8344 | 767.119 | #N/A | #N/A
9292 | PUEBLO 2102895310 | 43292102 | PUEBLO 2102 | 0.36853 | 31 | 0.022565 | 0.69951 | 1616 | 17681.203 | 766.4195 | #N/A | #N/A
3684 | VASCO 1102MR178 | 13751102 | VASCO 1102 | 1.6033 | 117 | 0.022562 | 2.6398 | 1617 | 17682.8062 | 763.7797 | #N/A | #N/A
6059 | RINCON 1103198 | 43321103 | RINCON 1103 | 6.4238 | 62 | 0.02256 | 1.3987 | 1618 | 17689.23 | 762.381 | #N/A | #N/A
8232 | FOOTHILL 1101251688 | 182951101 | FOOTHILL 1101 | 6.9818 | 68 | 0.022486 | 1.5291 | 1619 | 17696.2118 | 760.8519 | #N/A | #N/A
9659 | CAMBRIA 1101858200 | 182771101 | CAMBRIA 1101 | 5.718 | 31 | 0.022446 | 0.69582 | 1620 | 17701.9297 | 760.1561 | #N/A | #N/A
5819 | COTTONWOOD 110359128 | 102931103 | COTTONWOOD 1103 | 0.74702 | 65 | 0.022397 | 1.4558 | 1621 | 17702.6768 | 758.7002 | #N/A | #N/A
9234 | WILDWOOD 110185112 | 103611101 | WILDWOOD 1101 | 6.7944 | 54 | 0.022386 | 1.2088 | 1622 | 17709.4712 | 757.4914 | #N/A | #N/A
2051 | LAYTONVILLE 1101518 | 42681101 | LAYTONVILLE 1101 | 3.0081 | 165 | 0.02237 | 3.6911 | 1623 | 17712.4793 | 753.8003 | #N/A | #N/A
4400 | CALISTOGA 1102769230 | 42711102 | CALISTOGA 1102 | 11.021 | 160 | 0.022338 | 3.574 | 1624 | 17723.5003 | 750.2263 | #N/A | #N/A
1232 | VOLTA 110237350 | 102541102 | VOLTA 1102 | 24.2821 | 255 | 0.02227 | 5.6788 | 1625 | 17747.7824 | 744.5475 | #N/A | #N/A
1076 | MC ARTHUR 1101648698 | 103491101 | MC ARTHUR 1101 | 10.6495 | 173 | 0.022255 | 3.85 | 1626 | 17758.4319 | 740.6975 | #N/A | #N/A
6771 | HALSEY 1102CB | 152241102 | HALSEY 1102 | 7.8822 | 86 | 0.022172 | 1.9068 | 1627 | 17766.3141 | 738.7907 | #N/A | #N/A
1966 | GARBERVILLE 11011514 | 192221101 | GARBERVILLE 1101 | 14.7717 | 123 | 0.022168 | 2.7266 | 1628 | 17781.0858 | 736.0641 | #N/A | #N/A
7554 | SAN LUIS OBISPO 1105512313 | 182631105 | SAN LUIS OBISPO 1105 | 0.48845 | 10 | 0.022063 | 0.22063 | 1629 | 17781.5743 | 735.8434 | #N/A | #N/A
6120 | PUEBLO 2103895784 | 43292103 | PUEBLO 2103 | 7.793 | 110 | 0.022046 | 2.4251 | 1630 | 17789.3673 | 733.4184 | #N/A | #N/A
63 | CORRAL 110175204 | 162991101 | CORRAL 1101 | 0.85548 | 130 | 0.021935 | 2.8515 | 1631 | 17790.2227 | 730.5669 | #N/A | #N/A
9574 | MONROE 2103848530 | 43302103 | MONROE 2103 | 0.44461 | 17 | 0.021849 | 0.37143 | 1632 | 17790.6673 | 730.1954 | #N/A | #N/A
7210 | WEST POINT 110234416 | 163201102 | WEST POINT 1102 | 10.4546 | 113 | 0.021823 | 2.466 | 1633 | 17801.122 | 727.7294 | #N/A | #N/A
2105 | WEST POINT 1102CB | 163201102 | WEST POINT 1102 | 17.7877 | 195 | 0.02173 | 4.2374 | 1634 | 17818.9097 | 723.492 | #N/A | #N/A
6954 | WYANDOTTE 1110144140 | 102911110 | WYANDOTTE 1110 | 0.25917 | 20 | 0.021719 | 0.43439 | 1635 | 17819.1689 | 723.0576 | #N/A | #N/A
9884 | ELK 1101311906 | 42981101 | ELK 1101 | 0.69139 | 12 | 0.021675 | 0.2601 | 1636 | 17819.8603 | 722.7975 | #N/A | #N/A
1046 | GARBERVILLE 11028652 | 192221102 | GARBERVILLE 1102 | 13.1503 | 114 | 0.021633 | 2.4661 | 1637 | 17833.0106 | 720.3314 | #N/A | #N/A
3164 | BRUNSWICK 11062416 | 152481106 | BRUNSWICK 1106 | 28.9391 | 360 | 0.021547 | 7.7569 | 1638 | 17861.9497 | 712.5745 | #N/A | #N/A
3168 | LUCERNE 1103630 | 43351103 | LUCERNE 1103 | 12.4377 | 154 | 0.021529 | 3.3154 | 1639 | 17874.3874 | 709.259 | #N/A | #N/A
9831 | HALF MOON BAY 1101771258 | 24101101 | HALF MOON BAY 1101 | 0.19165 | 4 | 0.021484 | 0.085935 | 1640 | 17874.5791 | 709.1731 | #N/A | #N/A
8239 | FRUITLAND 11413902 | 192311141 | FRUITLAND 1141 | 5.111 | 9 | 0.021389 | 0.1925 | 1641 | 17879.6901 | 708.9806 | #N/A | #N/A
4880 | CURTIS 1705CB | 163351705 | CURTIS 1705 | 13.3382 | 163 | 0.021383 | 3.4854 | 1642 | 17893.0284 | 705.4952 | #N/A | #N/A
1762 | VINEYARD 2108609690 | 14502108 | VINEYARD 2108 | 4.8318 | 72 | 0.021383 | 1.5396 | 1643 | 17897.8601 | 703.9556 | #N/A | #N/A
7400 | CLARKSVILLE 21096502 | 153612109 | CLARKSVILLE 2109 | 0.93268 | 52 | 0.021251 | 1.1051 | 1644 | 17898.7928 | 702.8506 | #N/A | #N/A
10207 | MONTE RIO 111159046 | 42811111 | MONTE RIO 1111 | 3.506 | 15 | 0.021246 | 0.31869 | 1645 | 17902.2988 | 702.5319 | #N/A | #N/A
4878 | PLACERVILLE 21069712 | 153082106 | PLACERVILLE 2106 | 24.7147 | 226 | 0.021241 | 4.8004 | 1646 | 17927.0135 | 697.7315 | #N/A | #N/A
2046 | LINCOLN 11042072 | 153701104 | LINCOLN 1104 | 0.31166 | 193 | 0.021197 | 4.091 | 1647 | 17927.3252 | 693.6404 | #N/A | #N/A
7243 | SILVERADO 2104708 | 43432104 | SILVERADO 2104 | 3.7544 | 61 | 0.02118 | 1.292 | 1648 | 17931.0796 | 692.3484 | #N/A | #N/A
593 | BRUNSWICK 11021010 | 152481102 | BRUNSWICK 1102 | 44.3718 | 479 | 0.021168 | 10.1396 | 1649 | 17975.4514 | 682.2089 | #N/A | #N/A
5896 | CHALLENGE 11015460 | 103201101 | CHALLENGE 1101 | 11.7964 | 91 | 0.021116 | 1.9215 | 1650 | 17987.2478 | 680.2873 | #N/A | #N/A
9400 | BELL 110880680 | 152701108 | BELL 1108 | 0.64051 | 24 | 0.021095 | 0.50627 | 1651 | 17987.8883 | 679.7811 | #N/A | #N/A
6134 | CALAVERAS CEMENT 110180930 | 162211101 | CALAVERAS CEMENT 1101 | 18.3521 | 180 | 0.021019 | 3.7835 | 1652 | 18006.2404 | 675.9976 | #N/A | #N/A
5626 | WYANDOTTE 1103CB | 102911103 | WYANDOTTE 1103 | 0.24488 | 100 | 0.021017 | 2.1017 | 1653 | 18006.4852 | 673.8959 | #N/A | #N/A
5183 | ALTO 1125902 | 42031125 | ALTO 1125 | 12.0907 | 83 | 0.020905 | 1.7351 | 1654 | 18018.5759 | 672.1607 | #N/A | #N/A
7644 | LLAGAS 2101783467 | 83182101 | LLAGAS 2101 | 10.2229 | 61 | 0.020785 | 1.2679 | 1655 | 18028.7988 | 670.8929 | #N/A | #N/A
7011 | MOUNTAIN QUARRIES 21011180 | 152282101 | MOUNTAIN QUARRIES 2101 | 12.9566 | 141 | 0.020771 | 2.9287 | 1656 | 18041.7554 | 667.9642 | #N/A | #N/A
11063 | APPLE HILL 1104814656 | 153661104 | APPLE HILL 1104 | 0.01748 | 1 | 0.020643 | 0.020643 | 1657 | 18041.7729 | 667.9435 | #N/A | #N/A
9926 | BUCKS CREEK 1103CB | 102211103 | BUCKS CREEK 1103 | 2.3045 | 31 | 0.020623 | 0.63931 | 1658 | 18044.0774 | 667.3042 | #N/A | #N/A
3649 | FROGTOWN 1702812366 | 163451702 | FROGTOWN 1702 | 2.7477 | 28 | 0.020596 | 0.57668 | 1659 | 18046.8251 | 666.7275 | #N/A | #N/A
9417 | DUNBAR 1102694641 | 43071102 | DUNBAR 1102 | 4.0571 | 49 | 0.020553 | 1.0071 | 1660 | 18050.8822 | 665.7204 | #N/A | #N/A
8194 | STANISLAUS 17017144 | 162821701 | STANISLAUS 1701 | 4.6557 | 52 | 0.020479 | 1.0649 | 1661 | 18055.5379 | 664.6556 | #N/A | #N/A
10788 | FITCH MOUNTAIN 1111752596 | 42751111 | FITCH MOUNTAIN 1111 | 0.24558 | 6 | 0.020465 | 0.12279 | 1662 | 18055.7835 | 664.5328 | #N/A | #N/A
3463 | WOODACRE 1102851 | 43021102 | WOODACRE 1102 | 1.2611 | 14 | 0.020416 | 0.28582 | 1663 | 18057.0446 | 664.247 | #N/A | #N/A
331 | WEST POINT 11024790 | 163201102 | WEST POINT 1102 | 32.7726 | 305 | 0.020377 | 6.2151 | 1664 | 18089.8171 | 658.0318 | #N/A | #N/A
8939 | STELLING 111060080 | 83481110 | STELLING 1110 | 9.5829 | 64 | 0.020345 | 1.3021 | 1665 | 18099.4001 | 656.7297 | #N/A | #N/A
5387 | PLACERVILLE 210611132 | 153082106 | PLACERVILLE 2106 | 43.2776 | 420 | 0.020262 | 8.5102 | 1666 | 18142.6777 | 648.2195 | #N/A | #N/A
3326 | ORO FINO 110265932 | 103031102 | ORO FINO 1102 | 4.5225 | 48 | 0.020219 | 0.97052 | 1667 | 18147.2002 | 647.249 | #N/A | #N/A
7230 | PINE GROVE 110283098 | 163751102 | PINE GROVE 1102 | 7.9173 | 104 | 0.020137 | 2.0942 | 1668 | 18155.1175 | 645.1548 | #N/A | #N/A
2235 | MOLINO 1102318 | 42571102 | MOLINO 1102 | 19.3375 | 228 | 0.020097 | 4.5821 | 1669 | 18174.455 | 640.5727 | #N/A | #N/A
9552 | JOLON 11027068 | 182981102 | JOLON 1102 | 3.8155 | 12 | 0.019995 | 0.23993 | 1670 | 18178.2705 | 640.3327 | #N/A | #N/A
7621 | UKIAH 1115CB | 42771115 | UKIAH 1115 | 4.3108 | 73 | 0.019906 | 1.4531 | 1671 | 18182.5813 | 638.8796 | #N/A | #N/A
5118 | SAN LUIS OBISPO 1107V60 | 182631107 | SAN LUIS OBISPO 1107 | 16.042 | 142 | 0.0199 | 2.8258 | 1672 | 18198.6233 | 636.0538 | #N/A | #N/A
1916 | MOLINO 1104368158 | 42571104 | MOLINO 1104 | 2.7874 | 105 | 0.019862 | 2.0855 | 1673 | 18201.4107 | 633.9684 | #N/A | #N/A
8812 | ANTLER 11011376 | 103271101 | ANTLER 1101 | 8.998 | 70 | 0.019836 | 1.3885 | 1674 | 18210.4087 | 632.5799 | #N/A | #N/A
3393 | SILVERADO 2102714 | 43432102 | SILVERADO 2102 | 3.4609 | 121 | 0.019829 | 2.3993 | 1675 | 18213.8697 | 630.1806 | #N/A | #N/A
8102 | FORESTHILL 110175340 | 152181101 | FORESTHILL 1101 | 4.7831 | 62 | 0.01968 | 1.2202 | 1676 | 18218.6528 | 628.9604 | #N/A | #N/A
7713 | DUNBAR 11014817 | 43071101 | DUNBAR 1101 | 3.1568 | 42 | 0.019666 | 0.82599 | 1677 | 18221.8096 | 628.1344 | #N/A | #N/A
6368 | EAST QUINCY 1101951424 | 102551101 | EAST QUINCY 1101 | 0.69872 | 49 | 0.019501 | 0.95554 | 1678 | 18222.5083 | 627.1789 | #N/A | #N/A
6762 | HOOPA 11013304 | 192401101 | HOOPA 1101 | 17.341 | 88 | 0.019486 | 1.7148 | 1679 | 18239.8493 | 625.4641 | #N/A | #N/A
4845 | SAN JOAQUIN #3 110210342 | 252531102 | SAN JOAQUIN #3 1102 | 1.8216 | 23 | 0.019463 | 0.44766 | 1680 | 18241.6709 | 625.0165 | #N/A | #N/A
3381 | LUCERNE 110638436 | 43351106 | LUCERNE 1106 | 4.5081 | 62 | 0.019424 | 1.2043 | 1681 | 18246.179 | 623.8122 | #N/A | #N/A
8990 | HALF MOON BAY 1103540991 | 24101103 | HALF MOON BAY 1103 | 1.5814 | 16 | 0.019417 | 0.31068 | 1682 | 18247.7604 | 623.5015 | #N/A | #N/A
1522 | RIO DELL 11021504 | 192251102 | RIO DELL 1102 | 10.8482 | 64 | 0.019342 | 1.2379 | 1683 | 18258.6086 | 622.2636 | #N/A | #N/A
6286 | DUNBAR 1101416 | 43071101 | DUNBAR 1101 | 2.6414 | 28 | 0.019316 | 0.54085 | 1684 | 18261.25 | 621.7228 | #N/A | #N/A
2445 | MC ARTHUR 11011546 | 103491101 | MC ARTHUR 1101 | 13.7936 | 102 | 0.019258 | 1.9643 | 1685 | 18275.0436 | 619.7585 | #N/A | #N/A
2748 | HALF MOON BAY 11036018 | 24101103 | HALF MOON BAY 1103 | 15.6741 | 160 | 0.019223 | 3.0757 | 1686 | 18290.7177 | 616.6828 | #N/A | #N/A
4766 | CLOVERDALE 1101807953 | 42821101 | CLOVERDALE 1101 | 0.46353 | 11 | 0.019176 | 0.21093 | 1687 | 18291.1812 | 616.4718 | #N/A | #N/A
3508 | CLEAR LAKE 1102223792 | 42141102 | CLEAR LAKE 1102 | 0.78455 | 10 | 0.019106 | 0.19106 | 1688 | 18291.9658 | 616.2808 | #N/A | #N/A
3278 | KONOCTI 1108CB | 43311108 | KONOCTI 1108 | 6.3576 | 98 | 0.019021 | 1.864 | 1689 | 18298.3233 | 614.4167 | #N/A | #N/A
218 | MADISON 21017702 | 63172101 | MADISON 2101 | 0 | 168 | 0.018893 | 3.174 | 1690 | 18298.3233 | 611.2427 | #N/A | #N/A
5100 | RIO DELL 110270960 | 192251102 | RIO DELL 1102 | 5.7786 | 103 | 0.018609 | 1.9167 | 1691 | 18304.102 | 609.3261 | #N/A | #N/A
1226 | FORT ROSS 11212987 | 42851121 | FORT ROSS 1121 | 1.9714 | 18 | 0.018603 | 0.33485 | 1692 | 18306.0733 | 608.9912 | #N/A | #N/A
4217 | CHALLENGE 1102CB | 103201102 | CHALLENGE 1102 | 15.3169 | 123 | 0.0185 | 2.2755 | 1693 | 18321.3902 | 606.7157 | #N/A | #N/A
4592 | PHILO 1102928 | 42601102 | PHILO 1102 | 13.9642 | 125 | 0.018489 | 2.3111 | 1694 | 18335.3544 | 604.4046 | #N/A | #N/A
4143 | MENDOCINO 1101CB | 42951101 | MENDOCINO 1101 | 2.6352 | 54 | 0.018327 | 0.98966 | 1695 | 18337.9897 | 603.4149 | #N/A | #N/A
5556 | WEST POINT 11021305 | 163201102 | WEST POINT 1102 | 11.3122 | 105 | 0.01831 | 1.9226 | 1696 | 18349.3019 | 601.4923 | #N/A | #N/A
7818 | SONOMA 1105575872 | 42721105 | SONOMA 1105 | 1.1851 | 12 | 0.018279 | 0.21935 | 1697 | 18350.487 | 601.273 | #N/A | #N/A
1713 | HALF MOON BAY 1103H80 | 24101103 | HALF MOON BAY 1103 | 19.8193 | 164 | 0.018248 | 2.9927 | 1698 | 18370.3063 | 598.2803 | #N/A | #N/A
3304 | DIAMOND SPRINGS 11039432 | 152261103 | DIAMOND SPRINGS 1103 | 17.4645 | 251 | 0.018233 | 4.5765 | 1699 | 18387.7708 | 593.7038 | #N/A | #N/A
1922 | ALLEGHANY 1102CB | 152101102 | ALLEGHANY 1102 | 18.012 | 104 | 0.018204 | 1.8932 | 1700 | 18405.7828 | 591.8106 | #N/A | #N/A
4888 | DUNBAR 110179086 | 43071101 | DUNBAR 1101 | 6.8083 | 82 | 0.018179 | 1.4907 | 1701 | 18412.5911 | 590.3199 | #N/A | #N/A
1290 | FROGTOWN 170232556 | 163451702 | FROGTOWN 1702 | 0.1169 | 19 | 0.018147 | 0.34478 | 1702 | 18412.708 | 589.9751 | #N/A | #N/A
4459 | CLARK ROAD 11022094 | 103091102 | CLARK ROAD 1102 | 3.4289 | 11 | 0.018088 | 0.19897 | 1703 | 18416.1369 | 589.7761 | #N/A | #N/A
8596 | SAN JOAQUIN #3 1101CB | 252531101 | SAN JOAQUIN #3 1101 | 11.8429 | 80 | 0.018079 | 1.4463 | 1704 | 18427.9798 | 588.3298 | #N/A | #N/A
7985 | MERCED FALLS 1102482838 | 252811102 | MERCED FALLS 1102 | 8.8777 | 52 | 0.018057 | 0.93898 | 1705 | 18436.8575 | 587.3908 | #N/A | #N/A
5651 | MOUNTAIN QUARRIES 21012422 | 152282101 | MOUNTAIN QUARRIES 2101 | 8.671 | 81 | 0.018043 | 1.4615 | 1706 | 18445.5285 | 585.9293 | #N/A | #N/A
9070 | SILVERADO 2102437194 | 43432102 | SILVERADO 2102 | 1.0584 | 17 | 0.018026 | 0.30645 | 1707 | 18446.5869 | 585.6229 | #N/A | #N/A
2577 | HARTLEY 110186876 | 43211101 | HARTLEY 1101 | 2.4524 | 110 | 0.018007 | 1.9808 | 1708 | 18449.0393 | 583.6421 | #N/A | #N/A
5850 | GEYSERVILLE 1101711966 | 42891101 | GEYSERVILLE 1101 | 3.9317 | 122 | 0.017908 | 2.1848 | 1709 | 18452.971 | 581.4573 | #N/A | #N/A
8508 | PIKE CITY 11011720 | 152201101 | PIKE CITY 1101 | 5.8975 | 34 | 0.017864 | 0.60738 | 1710 | 18458.8685 | 580.8499 | #N/A | #N/A
4021 | GRASS VALLEY 11012766 | 152031101 | GRASS VALLEY 1101 | 3.2943 | 31 | 0.017834 | 0.55287 | 1711 | 18462.1628 | 580.297 | #N/A | #N/A
5421 | DUNBAR 1102261774 | 43071102 | DUNBAR 1102 | 13.5246 | 142 | 0.01783 | 2.5319 | 1712 | 18475.6874 | 577.7652 | #N/A | #N/A
1746 | TEMPLETON 2111CB | 183052111 | TEMPLETON 2111 | 2.2544 | 118 | 0.017802 | 2.1007 | 1713 | 18477.9418 | 575.6645 | #N/A | #N/A
2820 | ALTO 1124432 | 42031124 | ALTO 1124 | 7.8461 | 72 | 0.017729 | 1.2765 | 1714 | 18485.7878 | 574.388 | #N/A | #N/A
5452 | PUEBLO 2102850102 | 43292102 | PUEBLO 2102 | 0.17865 | 23 | 0.01772 | 0.40756 | 1715 | 18485.9665 | 573.9804 | #N/A | #N/A
3283 | CURTIS 170390320 | 163351703 | CURTIS 1703 | 27.8742 | 282 | 0.017701 | 4.9917 | 1716 | 18513.8407 | 568.9887 | #N/A | #N/A
3501 | CRESCENT MILLS 21012232 | 103132101 | CRESCENT MILLS 2101 | 15.8568 | 128 | 0.017667 | 2.2614 | 1717 | 18529.6976 | 566.7274 | #N/A | #N/A
10143 | GRASS VALLEY 1101750804 | 152031101 | GRASS VALLEY 1101 | 0.24243 | 5 | 0.017655 | 0.088275 | 1718 | 18529.94 | 566.6391 | #N/A | #N/A
3289 | MONTICELLO 11011589 | 43051101 | MONTICELLO 1101 | 4.2717 | 52 | 0.01765 | 0.91781 | 1719 | 18534.2117 | 565.7213 | #N/A | #N/A
1138 | ELECTRA 110136816 | 162161101 | ELECTRA 1101 | 4.9869 | 60 | 0.017625 | 1.0575 | 1720 | 18539.1986 | 564.6638 | #N/A | #N/A
9331 | WILLOW CREEK 1102CB | 192171102 | WILLOW CREEK 1102 | 7.3272 | 71 | 0.017606 | 1.25 | 1721 | 18546.5257 | 563.4138 | #N/A | #N/A
6284 | ANTLER 11011378 | 103271101 | ANTLER 1101 | 24.5436 | 201 | 0.017574 | 3.5323 | 1722 | 18571.0694 | 559.8814 | #N/A | #N/A
8843 | HOLLISTER 2104117328 | 182492104 | HOLLISTER 2104 | 6.1496 | 44 | 0.017549 | 0.77216 | 1723 | 18577.2189 | 559.1093 | #N/A | #N/A
106 | WYANDOTTE 11101954 | 102911110 | WYANDOTTE 1110 | 2.625 | 132 | 0.017468 | 2.3057 | 1724 | 18579.8439 | 556.8035 | #N/A | #N/A
7269 | CURTIS 17046060 | 163351704 | CURTIS 1704 | 4.0652 | 50 | 0.01746 | 0.873 | 1725 | 18583.9091 | 555.9305 | #N/A | #N/A
4024 | MOLINO 11015042 | 42571101 | MOLINO 1101 | 6.0518 | 90 | 0.01743 | 1.5687 | 1726 | 18589.9609 | 554.3619 | #N/A | #N/A
8422 | FROGTOWN 1702739858 | 163451702 | FROGTOWN 1702 | 4.8793 | 46 | 0.017426 | 0.80161 | 1727 | 18594.8402 | 553.5602 | #N/A | #N/A
3353 | KANAKA 11011406 | 103221101 | KANAKA 1101 | 27.2731 | 204 | 0.017352 | 3.5397 | 1728 | 18622.1132 | 550.0205 | #N/A | #N/A
10623 | MORGAN HILL 2111477914 | 83242111 | MORGAN HILL 2111 | 0.19132 | 3 | 0.017329 | 0.051987 | 1729 | 18622.3045 | 549.9685 | #N/A | #N/A
1703 | SAN LUIS OBISPO 1105796050 | 182631105 | SAN LUIS OBISPO 1105 | 0.2385 | 45 | 0.017291 | 0.7781 | 1730 | 18622.543 | 549.1904 | #N/A | #N/A
2587 | MENLO 11031721 | 24131103 | MENLO 1103 | 6.7914 | 52 | 0.01726 | 0.89751 | 1731 | 18629.3344 | 548.2929 | #N/A | #N/A
5617 | MIRABEL 1101298 | 42091101 | MIRABEL 1101 | 12.5878 | 123 | 0.017238 | 2.1202 | 1732 | 18641.9222 | 546.1727 | #N/A | #N/A
183 | CLEAR LAKE 110192870 | 42141101 | CLEAR LAKE 1101 | 0.11557 | 187 | 0.017207 | 3.2176 | 1733 | 18642.0378 | 542.9551 | #N/A | #N/A
5761 | SAN LUIS OBISPO 1102597518 | 182631102 | SAN LUIS OBISPO 1102 | 0.0405 | 30 | 0.017175 | 0.51524 | 1734 | 18642.0783 | 542.4398 | #N/A | #N/A
694 | PIT NO 1 11013312 | 103721101 | PIT NO 1 1101 | 8.045 | 82 | 0.017169 | 1.4079 | 1735 | 18650.1233 | 541.0319 | #N/A | #N/A
6571 | MC ARTHUR 11011488 | 103491101 | MC ARTHUR 1101 | 2.4678 | 217 | 0.01714 | 3.7195 | 1736 | 18652.5911 | 537.3125 | #N/A | #N/A
7993 | STILLWATER 1101CB | 103561101 | STILLWATER 1101 | 4.198 | 47 | 0.017137 | 0.80543 | 1737 | 18656.789 | 536.5071 | #N/A | #N/A
3453 | LOS GATOS 110760114 | 82021107 | LOS GATOS 1107 | 24.3201 | 220 | 0.016971 | 3.7337 | 1738 | 18681.1091 | 532.7734 | #N/A | #N/A
3503 | CLAYTON 2215184604 | 12022215 | CLAYTON 2215 | 2.0891 | 106 | 0.016935 | 1.7951 | 1739 | 18683.1982 | 530.9783 | #N/A | #N/A
5231 | BURNEY 1101CB | 103311101 | BURNEY 1101 | 1.2417 | 29 | 0.016895 | 0.48997 | 1740 | 18684.4399 | 530.4883 | #N/A | #N/A
5033 | ALTO 11243121 | 42031124 | ALTO 1124 | 2.7976 | 36 | 0.016885 | 0.60788 | 1741 | 18687.2375 | 529.8804 | #N/A | #N/A
4749 | FRUITLAND 11418860 | 192311141 | FRUITLAND 1141 | 1.9962 | 34 | 0.016867 | 0.57347 | 1742 | 18689.2337 | 529.307 | #N/A | #N/A
8284 | FRENCH GULCH 11011464 | 103381101 | FRENCH GULCH 1101 | 0.85238 | 10 | 0.01686 | 0.1686 | 1743 | 18690.0861 | 529.1384 | #N/A | #N/A
10232 | TIGER CREEK 0201CB | 161380201 | TIGER CREEK 0201 | 3.7431 | 20 | 0.016801 | 0.33603 | 1744 | 18693.8292 | 528.8024 | #N/A | #N/A
5809 | TEMPLETON 2110N32 | 183052110 | TEMPLETON 2110 | 29.5034 | 251 | 0.016765 | 4.208 | 1745 | 18723.3326 | 524.5943 | #N/A | #N/A
7289 | PLACERVILLE 111019582 | 153081110 | PLACERVILLE 1110 | 7.2707 | 80 | 0.016762 | 1.341 | 1746 | 18730.6033 | 523.2534 | #N/A | #N/A
9046 | OTTER 11022166 | 182941102 | OTTER 1102 | 4.0764 | 41 | 0.016743 | 0.68648 | 1747 | 18734.6798 | 522.5669 | #N/A | #N/A
3955 | GRAYS FLAT 0401CB | 102530401 | GRAYS FLAT 0401 | 10.7279 | 77 | 0.016728 | 1.2881 | 1748 | 18745.4076 | 521.2788 | #N/A | #N/A
4383 | FRUITLAND 114195324 | 192311141 | FRUITLAND 1141 | 6.4826 | 40 | 0.016671 | 0.66685 | 1749 | 18751.8902 | 520.612 | #N/A | #N/A
9718 | GARBERVILLE 1101323694 | 192221101 | GARBERVILLE 1101 | 6.4004 | 17 | 0.016661 | 0.28324 | 1750 | 18758.2906 | 520.3287 | #N/A | #N/A
7551 | GARBERVILLE 1101438596 | 192221101 | GARBERVILLE 1101 | 11.0232 | 69 | 0.016624 | 1.1471 | 1751 | 18769.3137 | 519.1817 | #N/A | #N/A
9937 | OTTER 11022002 | 182941102 | OTTER 1102 | 2.8257 | 27 | 0.01654 | 0.44657 | 1752 | 18772.1395 | 518.7351 | #N/A | #N/A
5432 | ALLEGHANY 1101804 | 152101101 | ALLEGHANY 1101 | 21.8915 | 163 | 0.016525 | 2.6936 | 1753 | 18794.031 | 516.0415 | #N/A | #N/A
6356 | NORTH BRANCH 110113496 | 163231101 | NORTH BRANCH 1101 | 1.9962 | 58 | 0.016506 | 0.95734 | 1754 | 18796.0272 | 515.0842 | #N/A | #N/A
249 | RINCON 1103CB | 43321103 | RINCON 1103 | 2.4433 | 41 | 0.016461 | 0.67489 | 1755 | 18798.4705 | 514.4093 | 514.4093 | #N/A
1025 | MARIPOSA 2101439030 | 254452101 | MARIPOSA 2101 | 19.621 | 200 | 0.016434 | 3.2868 | 1756 | 18818.0914 | 511.1225 | #N/A | #N/A
8791 | GLENN 11012012 | 102601101 | GLENN 1101 | 2.3047 | 73 | 0.016401 | 1.1972 | 1757 | 18820.3962 | 509.9252 | #N/A | #N/A
10780 | CALPINE 1144962 | 48011144 | CALPINE 1144 | 4.0181 | 13 | 0.01639 | 0.21307 | 1758 | 18824.4143 | 509.7121 | #N/A | #N/A
715 | ALTO 1124430 | 42031124 | ALTO 1124 | 7.0575 | 92 | 0.016311 | 1.5006 | 1759 | 18831.4718 | 508.2116 | #N/A | #N/A
9633 | MONTE RIO 11131067 | 42811113 | MONTE RIO 1113 | 0.81192 | 11 | 0.016 | 0.176 | 1760 | 18832.2837 | 508.0356 | #N/A | #N/A
1412 | PLACERVILLE 1109CB | 153081109 | PLACERVILLE 1109 | 10.8452 | 133 | 0.015996 | 2.1275 | 1761 | 18843.1289 | 505.9081 | #N/A | #N/A
8245 | BEAR VALLEY 210513430 | 252192105 | BEAR VALLEY 2105 | 13.1178 | 129 | 0.015945 | 2.057 | 1762 | 18856.2467 | 503.8511 | #N/A | #N/A
8966 | MORAGA 1101772781 | 13801101 | MORAGA 1101 | 1.4399 | 12 | 0.015766 | 0.1892 | 1763 | 18857.6866 | 503.6619 | #N/A | #N/A
3619 | PINE GROVE 11013166 | 163751101 | PINE GROVE 1101 | 12.2922 | 147 | 0.015763 | 2.3172 | 1764 | 18869.9788 | 501.3447 | #N/A | #N/A
4486 | WEST POINT 1101CB | 163201101 | WEST POINT 1101 | 4.7938 | 20 | 0.015736 | 0.31472 | 1765 | 18874.7727 | 501.03 | #N/A | #N/A
3894 | BONNIE NOOK 110186696 | 152301101 | BONNIE NOOK 1101 | 9.641 | 86 | 0.015606 | 1.3421 | 1766 | 18884.4137 | 499.6879 | #N/A | #N/A
1913 | OLEMA 1101416 | 42291101 | OLEMA 1101 | 16.1787 | 79 | 0.015542 | 1.2278 | 1767 | 18900.5923 | 498.4601 | #N/A | #N/A
2787 | PINE GROVE 11013170 | 163751101 | PINE GROVE 1101 | 39.8073 | 445 | 0.015534 | 6.9125 | 1768 | 18940.3996 | 491.5476 | #N/A | #N/A
8370 | SWIFT 2110XR332 | 83392110 | SWIFT 2110 | 18.4582 | 83 | 0.015532 | 1.2892 | 1769 | 18958.8578 | 490.2584 | #N/A | #N/A
6569 | CURTIS 17058170 | 163351705 | CURTIS 1705 | 7.6995 | 109 | 0.015509 | 1.6904 | 1770 | 18966.5573 | 488.568 | #N/A | #N/A
9835 | SPRING GAP 1702CB | 162831702 | SPRING GAP 1702 | 7.4405 | 18 | 0.015422 | 0.27759 | 1771 | 18973.9978 | 488.2904 | #N/A | #N/A
1693 | BUCKS CREEK 1103338520 | 102211103 | BUCKS CREEK 1103 | 7.8641 | 87 | 0.015412 | 1.3409 | 1772 | 18981.8619 | 486.9496 | #N/A | #N/A
4370 | OREGON TRAIL 11021584 | 103521102 | OREGON TRAIL 1102 | 13.0507 | 136 | 0.015387 | 2.0926 | 1773 | 18994.9126 | 484.857 | #N/A | #N/A
6223 | MOLINO 1101152 | 42571101 | MOLINO 1101 | 1.6586 | 125 | 0.015258 | 1.9072 | 1774 | 18996.5712 | 482.9497 | #N/A | #N/A
991 | PEORIA 170413494 | 163781704 | PEORIA 1704 | 2.7686 | 93 | 0.015212 | 1.4148 | 1775 | 18999.3399 | 481.535 | #N/A | #N/A
10392 | VINEYARD 2108383748 | 14502108 | VINEYARD 2108 | 0.36191 | 4 | 0.015207 | 0.060827 | 1776 | 18999.7018 | 481.4741 | #N/A | #N/A
5782 | GARBERVILLE 11026084 | 192221102 | GARBERVILLE 1102 | 15.311 | 120 | 0.015158 | 1.8189 | 1777 | 19015.0127 | 479.6552 | #N/A | #N/A
8670 | COTATI 1102462 | 42271102 | COTATI 1102 | 2.8283 | 40 | 0.015132 | 0.6053 | 1778 | 19017.841 | 479.0499 | #N/A | #N/A
5839 | SOLEDAD 21027048 | 182052102 | SOLEDAD 2102 | 11.5993 | 173 | 0.015069 | 2.607 | 1779 | 19029.4403 | 476.4429 | #N/A | #N/A
5090 | BRIDGEVILLE 1102CB | 192461102 | BRIDGEVILLE 1102 | 2.9355 | 52 | 0.015061 | 0.78316 | 1780 | 19032.3758 | 475.6597 | #N/A | #N/A
10131 | CMC 1101CB | 183111101 | CMC 1101 | 2.0423 | 16 | 0.014989 | 0.23983 | 1781 | 19034.4181 | 475.4199 | #N/A | #N/A
4953 | FRENCH GULCH 11021462 | 103381102 | FRENCH GULCH 1102 | 10.0162 | 51 | 0.01495 | 0.76245 | 1782 | 19044.4343 | 474.6575 | #N/A | #N/A
8365 | GRASS VALLEY 110358498 | 152031103 | GRASS VALLEY 1103 | 1.1937 | 34 | 0.01494 | 0.50797 | 1783 | 19045.628 | 474.1495 | #N/A | #N/A
4523 | TIDEWATER 210665866 | 14652106 | TIDEWATER 2106 | 3.419 | 65 | 0.014918 | 0.9697 | 1784 | 19049.047 | 473.1798 | #N/A | #N/A
7430 | FOOTHILL 1101549904 | 182951101 | FOOTHILL 1101 | 0.15565 | 54 | 0.014902 | 0.80473 | 1785 | 19049.2026 | 472.3751 | #N/A | #N/A
10743 | ANDERSON 1101909424 | 103261101 | ANDERSON 1101 | 0.3992 | 8 | 0.014888 | 0.1191 | 1786 | 19049.6018 | 472.256 | #N/A | #N/A
6685 | OCEANO 1102749231 | 182601102 | OCEANO 1102 | 5.5563 | 141 | 0.014847 | 2.0934 | 1787 | 19055.1582 | 470.1626 | #N/A | #N/A
2541 | BRUNSWICK 110651486 | 152481106 | BRUNSWICK 1106 | 56.6847 | 656 | 0.014797 | 9.7068 | 1788 | 19111.8429 | 460.4558 | #N/A | #N/A
7750 | BRUNSWICK 110765574 | 152481107 | BRUNSWICK 1107 | 0.58392 | 23 | 0.014793 | 0.34024 | 1789 | 19112.4268 | 460.1156 | #N/A | #N/A
5279 | MC ARTHUR 110137344 | 103491101 | MC ARTHUR 1101 | 0.1127 | 75 | 0.014768 | 1.1076 | 1790 | 19112.5395 | 459.008 | #N/A | #N/A
7132 | ANTLER 11011612 | 103271101 | ANTLER 1101 | 9.1773 | 86 | 0.014748 | 1.2683 | 1791 | 19121.7168 | 457.7396 | #N/A | #N/A
3386 | NEWBURG 1132665674 | 192151132 | NEWBURG 1132 | 0.43431 | 20 | 0.014722 | 0.29443 | 1792 | 19122.1511 | 457.4452 | #N/A | #N/A
7872 | PIT NO 1 110170952 | 103721101 | PIT NO 1 1101 | 1.6934 | 29 | 0.014692 | 0.42606 | 1793 | 19123.8445 | 457.0192 | #N/A | #N/A
5114 | DUNBAR 110147964 | 43071101 | DUNBAR 1101 | 6.5107 | 68 | 0.014662 | 0.99704 | 1794 | 19130.3552 | 456.0221 | 456.0221 | #N/A
7691 | POINT ARENA 110198224 | 43381101 | POINT ARENA 1101 | 2.3915 | 23 | 0.014654 | 0.33704 | 1795 | 19132.7467 | 455.6851 | #N/A | #N/A
2530 | BRUNSWICK 111061602 | 152481110 | BRUNSWICK 1110 | 9.8175 | 137 | 0.014648 | 2.0068 | 1796 | 19142.5641 | 453.6783 | #N/A | #N/A
7167 | FRENCH GULCH 11012905 | 103381101 | FRENCH GULCH 1101 | 9.692 | 83 | 0.014648 | 1.2158 | 1797 | 19152.2561 | 452.4625 | #N/A | #N/A
4457 | HIGGINS 11041006 | 152691104 | HIGGINS 1104 | 10.8946 | 266 | 0.014639 | 3.8939 | 1798 | 19163.1507 | 448.5686 | #N/A | #N/A
7710 | CARLOTTA 11214045 | 192291121 | CARLOTTA 1121 | 0.35805 | 18 | 0.014618 | 0.26312 | 1799 | 19163.5088 | 448.3055 | #N/A | #N/A
9405 | SILVERADO 2105861266 | 43432105 | SILVERADO 2105 | 1.5562 | 31 | 0.014616 | 0.45311 | 1800 | 19165.065 | 447.8524 | #N/A | #N/A
463 | WEIMAR 11012084 | 152491101 | WEIMAR 1101 | 18.4732 | 219 | 0.014579 | 3.1928 | 1801 | 19183.5382 | 444.6596 | #N/A | #N/A
3551 | WILLOW CREEK 11014904 | 192171101 | WILLOW CREEK 1101 | 18.2331 | 121 | 0.014552 | 1.7608 | 1802 | 19201.7713 | 442.8987 | #N/A | #N/A
6996 | KONOCTI 1102714370 | 43311102 | KONOCTI 1102 | 2.1274 | 28 | 0.014533 | 0.40694 | 1803 | 19203.8987 | 442.4918 | #N/A | #N/A
1102 | MC KEE 1107XR010 | 83531107 | MC KEE 1107 | 2.7862 | 160 | 0.014407 | 2.3052 | 1804 | 19206.6849 | 440.1866 | #N/A | #N/A
2551 | SOLEDAD 2102823854 | 182052102 | SOLEDAD 2102 | 2.0556 | 33 | 0.01437 | 0.47422 | 1805 | 19208.7405 | 439.7124 | #N/A | #N/A
2101 | SAN BENITO 210488772 | 182742104 | SAN BENITO 2104 | 24.323 | 474 | 0.014358 | 6.8057 | 1806 | 19233.0635 | 432.9067 | #N/A | #N/A
7410 | RIO DELL 11028852 | 192251102 | RIO DELL 1102 | 4.6451 | 46 | 0.014354 | 0.66027 | 1807 | 19237.7086 | 432.2464 | #N/A | #N/A
5404 | PIT NO 3 21011386 | 103732101 | PIT NO 3 2101 | 6.8695 | 47 | 0.014294 | 0.67181 | 1808 | 19244.5781 | 431.5746 | #N/A | #N/A
4186 | MARIPOSA 210110170 | 254452101 | MARIPOSA 2101 | 16.3165 | 149 | 0.014293 | 2.1297 | 1809 | 19260.8946 | 429.4449 | #N/A | #N/A
7884 | SONOMA 11045661 | 42721104 | SONOMA 1104 | 2.8951 | 66 | 0.014289 | 0.94309 | 1810 | 19263.7898 | 428.5018 | #N/A | #N/A
967 | DUNBAR 1102903030 | 43071102 | DUNBAR 1102 | 1.4552 | 17 | 0.014278 | 0.24273 | 1811 | 19265.245 | 428.2591 | #N/A | #N/A
3516 | NARROWS 21022718 | 153132102 | NARROWS 2102 | 0.30804 | 114 | 0.014276 | 1.6275 | 1812 | 19265.553 | 426.6316 | #N/A | #N/A
5103 | SAN LUIS OBISPO 1107V18 | 182631107 | SAN LUIS OBISPO 1107 | 2.6999 | 41 | 0.014215 | 0.5828 | 1813 | 19268.2529 | 426.0488 | #N/A | #N/A
177 | KING CITY 11037038 | 182031103 | KING CITY 1103 | 18.3291 | 186 | 0.014161 | 2.6339 | 1814 | 19286.5819 | 423.4149 | #N/A | #N/A
4472 | WEST POINT 110277204 | 163201102 | WEST POINT 1102 | 7.4073 | 68 | 0.014094 | 0.95841 | 1815 | 19293.9893 | 422.4565 | #N/A | #N/A
8017 | PIT NO 3 2101CB | 103732101 | PIT NO 3 2101 | 4.532 | 7 | 0.01407 | 0.098493 | 1816 | 19298.5213 | 422.358 | #N/A | #N/A
4764 | ALLEGHANY 1101CB | 152101101 | ALLEGHANY 1101 | 4.3721 | 40 | 0.014057 | 0.5623 | 1817 | 19302.8934 | 421.7957 | #N/A | #N/A
2091 | STELLING 111060094 | 83481110 | STELLING 1110 | 9.8619 | 95 | 0.014041 | 1.3339 | 1818 | 19312.7553 | 420.4618 | #N/A | #N/A
2701 | PEORIA 170567898 | 163781705 | PEORIA 1705 | 4.2992 | 70 | 0.014037 | 0.98259 | 1819 | 19317.0545 | 419.4792 | #N/A | #N/A
8037 | CAYUCOS 1102613456 | 182551102 | CAYUCOS 1102 | 13.4475 | 145 | 0.014028 | 2.0341 | 1820 | 19330.5021 | 417.4452 | #N/A | #N/A
4958 | WILLOW CREEK 11035012 | 192171103 | WILLOW CREEK 1103 | 11.1274 | 131 | 0.014012 | 1.8356 | 1821 | 19341.6295 | 415.6095 | #N/A | #N/A
1586 | MARTELL 110111244 | 163011101 | MARTELL 1101 | 20.6924 | 202 | 0.01399 | 2.826 | 1822 | 19362.3219 | 412.7835 | #N/A | #N/A
8222 | DUNBAR 1102528 | 43071102 | DUNBAR 1102 | 3.4314 | 50 | 0.013987 | 0.69934 | 1823 | 19365.7534 | 412.0842 | #N/A | #N/A
6649 | SAN LUIS OBISPO 1108337126 | 182631108 | SAN LUIS OBISPO 1108 | 0.70138 | 28 | 0.013964 | 0.39101 | 1824 | 19366.4547 | 411.6932 | #N/A | #N/A
716 | LAKEVILLE 1102280 | 43371102 | LAKEVILLE 1102 | 0.68764 | 52 | 0.013918 | 0.72376 | 1825 | 19367.1424 | 410.9694 | #N/A | #N/A
1162 | DUNBAR 1101302 | 43071101 | DUNBAR 1101 | 8.7659 | 123 | 0.013839 | 1.7022 | 1826 | 19375.9083 | 409.2672 | #N/A | #N/A
5443 | DUNBAR 1103534 | 43071103 | DUNBAR 1103 | 15.8602 | 162 | 0.01369 | 2.2178 | 1827 | 19391.7685 | 407.0495 | #N/A | #N/A
3834 | STILLWATER 11011320 | 103561101 | STILLWATER 1101 | 19.8125 | 179 | 0.013687 | 2.4499 | 1828 | 19411.5809 | 404.5996 | #N/A | #N/A
3066 | SHADY GLEN 1102CB | 152431102 | SHADY GLEN 1102 | 21.1633 | 240 | 0.01359 | 3.2616 | 1829 | 19432.7443 | 401.338 | #N/A | #N/A
8639 | GREEN VALLEY 2101135762 | 83192101 | GREEN VALLEY 2101 | 0.7393 | 28 | 0.013539 | 0.3791 | 1830 | 19433.4836 | 400.9589 | #N/A | #N/A
1363 | BURNEY 11011322 | 103311101 | BURNEY 1101 | 16.0665 | 81 | 0.01351 | 1.0943 | 1831 | 19449.5501 | 399.8645 | #N/A | #N/A
5427 | PENRYN 1103CB | 152561103 | PENRYN 1103 | 2.4031 | 37 | 0.013499 | 0.49946 | 1832 | 19451.9533 | 399.3651 | #N/A | #N/A
8202 | DUNBAR 1102861496 | 43071102 | DUNBAR 1102 | 4.4679 | 51 | 0.013491 | 0.68805 | 1833 | 19456.4211 | 398.677 | #N/A | #N/A
3776 | ALTO 1125510 | 42031125 | ALTO 1125 | 7.3721 | 77 | 0.013466 | 1.0369 | 1834 | 19463.7932 | 397.6402 | #N/A | #N/A
2524 | PHILO 1102920 | 42601102 | PHILO 1102 | 17.7725 | 258 | 0.013411 | 3.4601 | 1835 | 19481.5657 | 394.1801 | #N/A | #N/A
8287 | LUCERNE 11034624 | 43351103 | LUCERNE 1103 | 0.031493 | 42 | 0.013292 | 0.55825 | 1836 | 19481.5972 | 393.6218 | #N/A | #N/A
3582 | SAN RAFAEL 1108516 | 42011108 | SAN RAFAEL 1108 | 10.9401 | 135 | 0.013281 | 1.7929 | 1837 | 19492.5373 | 391.8289 | #N/A | #N/A
6863 | GREEN VALLEY 2101942143 | 83192101 | GREEN VALLEY 2101 | 5.0581 | 74 | 0.013216 | 0.97798 | 1838 | 19497.5954 | 390.8509 | #N/A | #N/A
7880 | POINT ARENA 110183354 | 43381101 | POINT ARENA 1101 | 5.1341 | 36 | 0.013182 | 0.47457 | 1839 | 19502.7295 | 390.3763 | #N/A | #N/A
2799 | TASSAJARA 211238868 | 14662112 | TASSAJARA 2112 | 1.9386 | 61 | 0.01315 | 0.80215 | 1840 | 19504.6681 | 389.5742 | #N/A | #N/A
10912 | TOCALOMA 0241CB | 43150241 | TOCALOMA 0241 | 0.016479 | 1 | 0.013124 | 0.013124 | 1841 | 19504.6845 | 389.5611 | #N/A | #N/A
6124 | ANDERSON 1101CB | 103261101 | ANDERSON 1101 | 1.1835 | 85 | 0.013117 | 1.115 | 1842 | 19505.868 | 388.4461 | #N/A | #N/A
6165 | BRUNSWICK 1105CB | 152481105 | BRUNSWICK 1105 | 1.1628 | 21 | 0.013096 | 0.27501 | 1843 | 19507.0308 | 388.1711 | #N/A | #N/A
9119 | SONOMA 1106296492 | 42721106 | SONOMA 1106 | 0.78968 | 29 | 0.013092 | 0.37968 | 1844 | 19507.8205 | 387.7914 | #N/A | #N/A
3902 | SOLEDAD 2102858388 | 182052102 | SOLEDAD 2102 | 4.7963 | 72 | 0.013047 | 0.93942 | 1845 | 19512.6168 | 386.852 | #N/A | #N/A
6187 | JESSUP 11013383 | 103441101 | JESSUP 1101 | 1.4095 | 24 | 0.012944 | 0.31066 | 1846 | 19514.0263 | 386.5413 | #N/A | #N/A
4407 | APPLE HILL 210297982 | 153662102 | APPLE HILL 2102 | 9.6617 | 104 | 0.012892 | 1.3407 | 1847 | 19523.688 | 385.2006 | #N/A | #N/A
7041 | JAMESON 1105371694 | 63801105 | JAMESON 1105 | 0.2273 | 40 | 0.012819 | 0.51277 | 1848 | 19523.9153 | 384.6878 | #N/A | #N/A
3447 | WYANDOTTE 11031974 | 102911103 | WYANDOTTE 1103 | 22.4168 | 259 | 0.012814 | 3.3188 | 1849 | 19546.3321 | 381.369 | 381.369 | #N/A
7950 | SONOMA 11033052 | 42721103 | SONOMA 1103 | 12.5899 | 163 | 0.012795 | 2.0855 | 1850 | 19558.922 | 379.2835 | #N/A | #N/A
5166 | LOS GATOS 1106LB48 | 82021106 | LOS GATOS 1106 | 14.71 | 142 | 0.012757 | 1.8115 | 1851 | 19573.632 | 377.4719 | #N/A | #N/A
3055 | LAS POSITAS 2108MR190 | 14402108 | LAS POSITAS 2108 | 0.83091 | 130 | 0.012744 | 1.6567 | 1852 | 19574.4629 | 375.8152 | #N/A | #N/A
8820 | HICKS 2101CB | 83432101 | HICKS 2101 | 5.3825 | 20 | 0.012742 | 0.25483 | 1853 | 19579.8454 | 375.5604 | #N/A | #N/A
987 | OAKHURST 110310140 | 254421103 | OAKHURST 1103 | 16.6091 | 188 | 0.012696 | 2.3869 | 1854 | 19596.4545 | 373.1735 | #N/A | #N/A
1124 | COARSEGOLD 210210040 | 254432102 | COARSEGOLD 2102 | 17.6377 | 213 | 0.01266 | 2.6967 | 1855 | 19614.0922 | 370.4768 | #N/A | #N/A
6998 | PUEBLO 1104640 | 43291104 | PUEBLO 1104 | 1.0173 | 43 | 0.012658 | 0.54429 | 1856 | 19615.1095 | 369.9326 | #N/A | #N/A
2113 | HALSEY 11025739 | 152241102 | HALSEY 1102 | 6.6699 | 74 | 0.012582 | 0.93104 | 1857 | 19621.7794 | 369.0015 | #N/A | #N/A
9463 | ATASCADERO 1103A06 | 182541103 | ATASCADERO 1103 | 0.27446 | 27 | 0.012566 | 0.33927 | 1858 | 19622.0538 | 368.6622 | #N/A | #N/A
673 | FLINT 110140666 | 152531101 | FLINT 1101 | 0.35747 | 18 | 0.012564 | 0.22615 | 1859 | 19622.4113 | 368.4361 | #N/A | #N/A
6086 | SONOMA 1102113082 | 42721102 | SONOMA 1102 | 6.1264 | 75 | 0.012535 | 0.94012 | 1860 | 19628.5377 | 367.496 | #N/A | #N/A
4138 | ORO FINO 11022096 | 103031102 | ORO FINO 1102 | 14.1535 | 129 | 0.012531 | 1.6166 | 1861 | 19642.6912 | 365.8794 | #N/A | #N/A
8669 | HORSESHOE 1101663244 | 152571101 | HORSESHOE 1101 | 0.28862 | 6 | 0.012526 | 0.075153 | 1862 | 19642.9798 | 365.8043 | #N/A | #N/A
1101 | HOOPA 110137202 | 192401101 | HOOPA 1101 | 24.9008 | 190 | 0.012512 | 2.3773 | 1863 | 19667.8806 | 363.427 | #N/A | #N/A
1135 | LOS GATOS 1106LB44 | 82021106 | LOS GATOS 1106 | 19.3536 | 213 | 0.012499 | 2.6623 | 1864 | 19687.2342 | 360.7647 | 360.7647 | #N/A
5450 | FORESTHILL 11011802 | 152181101 | FORESTHILL 1101 | 22.2318 | 259 | 0.012496 | 3.2365 | 1865 | 19709.466 | 357.5283 | #N/A | #N/A
5898 | WISE 1102465074 | 152271102 | WISE 1102 | 4.7621 | 57 | 0.012495 | 0.7122 | 1866 | 19714.2281 | 356.8161 | #N/A | #N/A
7150 | FRUITLAND 1141200856 | 192311141 | FRUITLAND 1141 | 2.5758 | 31 | 0.012452 | 0.38602 | 1867 | 19716.8039 | 356.43 | #N/A | #N/A
6814 | SAN ARDO 11017632 | 182191101 | SAN ARDO 1101 | 2.2163 | 35 | 0.012428 | 0.43499 | 1868 | 19719.0202 | 355.995 | #N/A | #N/A
4514 | SOLEDAD 2101526864 | 182052101 | SOLEDAD 2101 | 3.1129 | 18 | 0.012408 | 0.22335 | 1869 | 19722.1331 | 355.7717 | #N/A | #N/A
10395 | CLARKSVILLE 2109649874 | 153612109 | CLARKSVILLE 2109 | 0.37816 | 5 | 0.012324 | 0.061618 | 1870 | 19722.5113 | 355.7101 | #N/A | #N/A
368 | POINT MORETTI 11015078 | 82931101 | POINT MORETTI 1101 | 14.8373 | 154 | 0.012313 | 1.8962 | 1871 | 19737.3486 | 353.8139 | #N/A | #N/A
4025 | CARLOTTA 1121CB | 192291121 | CARLOTTA 1121 | 2.6253 | 255 | 0.012302 | 3.1369 | 1872 | 19739.9739 | 350.677 | #N/A | #N/A
9319 | GONZALES 11013094 | 182131101 | GONZALES 1101 | 4.0888 | 63 | 0.012298 | 0.77477 | 1873 | 19744.0627 | 349.9022 | #N/A | #N/A
5655 | CHALLENGE 1101CB | 103201101 | CHALLENGE 1101 | 16.5645 | 128 | 0.012215 | 1.5636 | 1874 | 19760.6272 | 348.3386 | #N/A | #N/A
9730 | MC KEE 1108976553 | 83531108 | MC KEE 1108 | 1.0843 | 20 | 0.012197 | 0.24394 | 1875 | 19761.7115 | 348.0947 | #N/A | #N/A
8214 | BRUNSWICK 1106CB | 152481106 | BRUNSWICK 1106 | 8.7425 | 88 | 0.012162 | 1.0703 | 1876 | 19770.454 | 347.0244 | #N/A | #N/A
3779 | NOTRE DAME 1103317782 | 102041103 | NOTRE DAME 1103 | 0.54331 | 53 | 0.012141 | 0.64349 | 1877 | 19770.9973 | 346.3809 | #N/A | #N/A
1366 | HALF MOON BAY 11036014 | 24101103 | HALF MOON BAY 1103 | 6.192 | 106 | 0.012138 | 1.2867 | 1878 | 19777.1894 | 345.0943 | #N/A | #N/A
7316 | HOLLISTER 2102676164 | 182492102 | HOLLISTER 2102 | 0.30298 | 26 | 0.012062 | 0.3136 | 1879 | 19777.4923 | 344.7807 | #N/A | #N/A
2140 | BRUNSWICK 1102CB | 152481102 | BRUNSWICK 1102 | 6.2764 | 73 | 0.01204 | 0.87889 | 1880 | 19783.7688 | 343.9018 | #N/A | #N/A
9978 | FROGTOWN 1702411508 | 163451702 | FROGTOWN 1702 | 0.45171 | 6 | 0.012026 | 0.072157 | 1881 | 19784.2205 | 343.8296 | #N/A | #N/A
5364 | FULTON 1104466 | 42561104 | FULTON 1104 | 0.38717 | 21 | 0.01202 | 0.25243 | 1882 | 19784.6077 | 343.5772 | #N/A | #N/A
916 | WYANDOTTE 1105329930 | 102911105 | WYANDOTTE 1105 | 6.5421 | 137 | 0.012012 | 1.6456 | 1883 | 19791.1497 | 341.9315 | #N/A | #N/A
4781 | SONOMA 1105539450 | 42721105 | SONOMA 1105 | 1.4938 | 28 | 0.011978 | 0.33537 | 1884 | 19792.6436 | 341.5962 | #N/A | #N/A
5493 | SHADY GLEN 11012768 | 152431101 | SHADY GLEN 1101 | 7.6253 | 88 | 0.011963 | 1.0528 | 1885 | 19800.2688 | 340.5434 | #N/A | #N/A
8268 | LLAGAS 2101587857 | 83182101 | LLAGAS 2101 | 0.10681 | 28 | 0.011944 | 0.33442 | 1886 | 19800.3756 | 340.209 | #N/A | #N/A
1441 | MIWUK 170111800 | 163661701 | MIWUK 1701 | 9.5248 | 116 | 0.011866 | 1.3764 | 1887 | 19809.9005 | 338.8326 | #N/A | #N/A
2749 | ELK 1101900 | 42981101 | ELK 1101 | 8.7791 | 185 | 0.011859 | 2.1939 | 1888 | 19818.6795 | 336.6387 | #N/A | #N/A
1288 | CALAVERAS CEMENT 11012646 | 162211101 | CALAVERAS CEMENT 1101 | 17.6594 | 149 | 0.01184 | 1.7642 | 1889 | 19836.339 | 334.8745 | #N/A | #N/A
8429 | FOOTHILL 1101386844 | 182951101 | FOOTHILL 1101 | 0.3826 | 19 | 0.01183 | 0.22478 | 1890 | 19836.7216 | 334.6497 | #N/A | #N/A
6057 | LLAGAS 2101XR264 | 83182101 | LLAGAS 2101 | 0 | 258 | 0.011726 | 3.0254 | 1891 | 19836.7216 | 331.6243 | #N/A | #N/A
5358 | UKIAH 1113968652 | 42771113 | UKIAH 1113 | 0.99825 | 25 | 0.011684 | 0.2921 | 1892 | 19837.7198 | 331.3322 | #N/A | #N/A
9622 | SAN RAFAEL 110863598 | 42011108 | SAN RAFAEL 1108 | 1.9122 | 24 | 0.011681 | 0.28035 | 1893 | 19839.632 | 331.0519 | #N/A | #N/A
6523 | ALTO 1124870444 | 42031124 | ALTO 1124 | 2.95 | 35 | 0.011666 | 0.40831 | 1894 | 19842.582 | 330.6436 | #N/A | #N/A
4747 | SANTA ROSA A 1104716 | 42151104 | SANTA ROSA A 1104 | 8.8999 | 109 | 0.01165 | 1.2698 | 1895 | 19851.4819 | 329.3738 | #N/A | #N/A
9188 | HALF MOON BAY 1102350336 | 24101102 | HALF MOON BAY 1102 | 1.2038 | 13 | 0.011629 | 0.15117 | 1896 | 19852.6857 | 329.2226 | #N/A | #N/A
10068 | SAN LUIS OBISPO 1108809986 | 182631108 | SAN LUIS OBISPO 1108 | 1.0323 | 18 | 0.011626 | 0.20927 | 1897 | 19853.7181 | 329.0133 | #N/A | #N/A
3493 | MARTELL 110198374 | 163011101 | MARTELL 1101 | 0.8271 | 46 | 0.011616 | 0.53436 | 1898 | 19854.5452 | 328.479 | #N/A | #N/A
3767 | HOLLISTER 210491424 | 182492104 | HOLLISTER 2104 | 0.18842 | 95 | 0.01155 | 1.0973 | 1899 | 19854.7336 | 327.3817 | #N/A | #N/A
7603 | CLOVERDALE 1102262 | 42821102 | CLOVERDALE 1102 | 1.2848 | 61 | 0.011548 | 0.70445 | 1900 | 19856.0183 | 326.6772 | #N/A | #N/A
712 | SILVERADO 2105247660 | 43432105 | SILVERADO 2105 | 2.3981 | 35 | 0.011541 | 0.40392 | 1901 | 19858.4164 | 326.2733 | #N/A | #N/A
4631 | BRUNSWICK 11052210 | 152481105 | BRUNSWICK 1105 | 22.9574 | 280 | 0.01151 | 3.2229 | 1902 | 19881.3738 | 323.0504 | #N/A | #N/A
1236 | OAKHURST 11035480 | 254421103 | OAKHURST 1103 | 16.9994 | 180 | 0.011505 | 2.0709 | 1903 | 19898.3733 | 320.9796 | #N/A | #N/A
2425 | PIT NO 3 21011360 | 103732101 | PIT NO 3 2101 | 22.4404 | 92 | 0.011504 | 1.0584 | 1904 | 19920.8137 | 319.9212 | #N/A | #N/A
9598 | MILPITAS 1109XR044 | 82831109 | MILPITAS 1109 | 0.42126 | 18 | 0.011436 | 0.20585 | 1905 | 19921.2349 | 319.7153 | #N/A | #N/A
3999 | CALAVERAS CEMENT 11011419 | 162211101 | CALAVERAS CEMENT 1101 | 15.0161 | 130 | 0.011428 | 1.4856 | 1906 | 19936.2511 | 318.2297 | #N/A | #N/A
3421 | HIGGINS 1104324510 | 152691104 | HIGGINS 1104 | 12.4758 | 154 | 0.011404 | 1.7562 | 1907 | 19948.7269 | 316.4735 | #N/A | #N/A
6037 | COARSEGOLD 210210050 | 254432102 | COARSEGOLD 2102 | 7.0172 | 81 | 0.01137 | 0.92095 | 1908 | 19955.7441 | 315.5525 | #N/A | #N/A
942 | WEST POINT 110293116 | 163201102 | WEST POINT 1102 | 42.3267 | 453 | 0.011348 | 5.1406 | 1909 | 19998.0708 | 310.4119 | #N/A | #N/A
1810 | CABRILLO 1104CB | 183101104 | CABRILLO 1104 | 4.128 | 121 | 0.011318 | 1.3695 | 1910 | 20002.1988 | 309.0424 | #N/A | #N/A
1626 | MOLINO 110251788 | 42571102 | MOLINO 1102 | 5.0892 | 153 | 0.011264 | 1.7234 | 1911 | 20007.288 | 307.319 | #N/A | #N/A
6259 | RISING RIVER 11019032 | 103551101 | RISING RIVER 1101 | 22.8885 | 175 | 0.011207 | 1.9611 | 1912 | 20030.1765 | 305.3578 | #N/A | #N/A
1825 | FORT BRAGG A 11014622 | 42761101 | FORT BRAGG A 1101 | 13.456 | 109 | 0.011136 | 1.2138 | 1913 | 20043.6325 | 304.144 | #N/A | #N/A
5920 | CASTRO VALLEY 1110MR243 | 14091110 | CASTRO VALLEY 1110 | 5.5499 | 72 | 0.011084 | 0.79807 | 1914 | 20049.1824 | 303.346 | #N/A | #N/A
3864 | PLACER 1103429574 | 152461103 | PLACER 1103 | 4.9745 | 114 | 0.011083 | 1.2634 | 1915 | 20054.1569 | 302.0826 | #N/A | #N/A
4013 | LAURELES 1111CB | 182371111 | LAURELES 1111 | 7.1569 | 82 | 0.011075 | 0.90815 | 1916 | 20061.3139 | 301.1744 | #N/A | #N/A
9810 | MENLO 11028896 | 24131102 | MENLO 1102 | 0.95586 | 14 | 0.011065 | 0.15491 | 1917 | 20062.2698 | 301.0195 | #N/A | #N/A
8395 | CARLOTTA 112142896 | 192291121 | CARLOTTA 1121 | 2.2912 | 71 | 0.011029 | 0.78303 | 1918 | 20064.561 | 300.2365 | #N/A | #N/A
5390 | SOLEDAD 2102304826 | 182052102 | SOLEDAD 2102 | 5.2196 | 61 | 0.010995 | 0.6707 | 1919 | 20069.7806 | 299.5658 | #N/A | #N/A
4943 | PINE GROVE 1102CB | 163751102 | PINE GROVE 1102 | 10.8527 | 136 | 0.010952 | 1.4895 | 1920 | 20080.6332 | 298.0762 | #N/A | #N/A
2277 | ORO FINO 11022560 | 103031102 | ORO FINO 1102 | 16.7269 | 179 | 0.010913 | 1.9534 | 1921 | 20097.3601 | 296.1228 | #N/A | #N/A
8219 | CAMPHORA 1101613562 | 182071101 | CAMPHORA 1101 | 3.695 | 29 | 0.010904 | 0.31622 | 1922 | 20101.0552 | 295.8066 | #N/A | #N/A
8001 | MOLINO 1102189602 | 42571102 | MOLINO 1102 | 0.62848 | 9 | 0.010902 | 0.098117 | 1923 | 20101.6837 | 295.7085 | #N/A | #N/A
8797 | CAMP EVERS 210533542 | 83622105 | CAMP EVERS 2105 | 2.6827 | 39 | 0.010901 | 0.42515 | 1924 | 20104.3664 | 295.2833 | #N/A | #N/A
6026 | ROSSMOOR 110837848 | 14161108 | ROSSMOOR 1108 | 5.9544 | 60 | 0.010901 | 0.65406 | 1925 | 20110.3208 | 294.6293 | #N/A | #N/A
9862 | MONTE RIO 11113891 | 42811111 | MONTE RIO 1111 | 3.4699 | 23 | 0.010887 | 0.2504 | 1926 | 20113.7907 | 294.3789 | #N/A | #N/A
9761 | HALF MOON BAY 1103341542 | 24101103 | HALF MOON BAY 1103 | 6.0713 | 47 | 0.010885 | 0.5116 | 1927 | 20119.862 | 293.8673 | #N/A | #N/A
6971 | WILLOW CREEK 11037514 | 192171103 | WILLOW CREEK 1103 | 9.0713 | 118 | 0.010882 | 1.2841 | 1928 | 20128.9333 | 292.5832 | #N/A | #N/A
8324 | MONTE RIO 1112999 | 42811112 | MONTE RIO 1112 | 0.8778 | 7 | 0.010787 | 0.075506 | 1929 | 20129.8111 | 292.5077 | #N/A | #N/A
3097 | ATASCADERO 1103492068 | 182541103 | ATASCADERO 1103 | 7.4298 | 75 | 0.010772 | 0.80789 | 1930 | 20137.2409 | 291.6998 | #N/A | #N/A
1425 | CLAY 110184572 | 163341101 | CLAY 1101 | 0.52505 | 27 | 0.010769 | 0.29075 | 1931 | 20137.766 | 291.409 | #N/A | #N/A
8269 | COTATI 1105893 | 42271105 | COTATI 1105 | 0.19405 | 91 | 0.010724 | 0.9759 | 1932 | 20137.96 | 290.4331 | #N/A | #N/A
1839 | VOLTA 11021650 | 102541102 | VOLTA 1102 | 21.7104 | 154 | 0.010701 | 1.6479 | 1933 | 20159.6704 | 288.7852 | #N/A | #N/A
5835 | APPLE HILL 110497086 | 153661104 | APPLE HILL 1104 | 25.6961 | 301 | 0.010689 | 3.2174 | 1934 | 20185.3665 | 285.5678 | #N/A | #N/A
7014 | ALTO 1122591122 | 42031122 | ALTO 1122 | 0.46531 | 7 | 0.010649 | 0.074542 | 1935 | 20185.8319 | 285.4933 | #N/A | #N/A
1545 | MARTELL 110191216 | 163011101 | MARTELL 1101 | 40.579 | 380 | 0.010587 | 4.0231 | 1936 | 20226.4109 | 281.4701 | #N/A | #N/A
812 | DUNBAR 1102246 | 43071102 | DUNBAR 1102 | 13.3609 | 148 | 0.010561 | 1.563 | 1937 | 20239.7718 | 279.9071 | #N/A | #N/A
6481 | DEL MONTE 21043088 | 182222104 | DEL MONTE 2104 | 15.4183 | 175 | 0.010503 | 1.8381 | 1938 | 20255.1901 | 278.069 | #N/A | #N/A
336 | CAMBRIA 1102CB | 182771102 | CAMBRIA 1102 | 16.0058 | 153 | 0.010468 | 1.6015 | 1939 | 20271.1959 | 276.4675 | #N/A | #N/A
3334 | VOLTA 110297816 | 102541102 | VOLTA 1102 | 5.2562 | 50 | 0.010402 | 0.52009 | 1940 | 20276.4521 | 275.9474 | #N/A | #N/A
1241 | CALAVERAS CEMENT 110147968 | 162211101 | CALAVERAS CEMENT 1101 | 40.4602 | 306 | 0.010385 | 3.1777 | 1941 | 20316.9123 | 272.7697 | #N/A | #N/A
8572 | LOS GATOS 110760024 | 82021107 | LOS GATOS 1107 | 3.9764 | 27 | 0.010381 | 0.28029 | 1942 | 20320.8887 | 272.4894 | #N/A | #N/A
8425 | PINE GROVE 110194936 | 163751101 | PINE GROVE 1101 | 9.1674 | 82 | 0.010365 | 0.84992 | 1943 | 20330.0561 | 271.6395 | #N/A | #N/A
10220 | ALLEGHANY 1101808 | 152101101 | ALLEGHANY 1101 | 6.1786 | 23 | 0.010361 | 0.23829 | 1944 | 20336.2347 | 271.4012 | #N/A | #N/A
7876 | PUEBLO 2103706399 | 43292103 | PUEBLO 2103 | 0.33435 | 16 | 0.010338 | 0.1654 | 1945 | 20336.5691 | 271.2358 | #N/A | #N/A
1021 | EL DORADO PH 210119752 | 152762101 | EL DORADO PH 2101 | 36.5225 | 436 | 0.0103 | 4.4909 | 1946 | 20373.0916 | 266.7448 | 266.7448 | #N/A
5417 | SILVERADO 2105131568 | 43432105 | SILVERADO 2105 | 4.1385 | 57 | 0.010281 | 0.58604 | 1947 | 20377.2301 | 266.1588 | #N/A | #N/A
3018 | LUCERNE 110638632 | 43351106 | LUCERNE 1106 | 4.6833 | 58 | 0.010245 | 0.59423 | 1948 | 20381.9133 | 265.5646 | #N/A | #N/A
9909 | OLEMA 1101337220 | 42291101 | OLEMA 1101 | 4.9471 | 28 | 0.010237 | 0.28665 | 1949 | 20386.8604 | 265.2779 | #N/A | #N/A
7162 | BIG BEND 1101CB | 103751101 | BIG BEND 1101 | 23.2301 | 171 | 0.010207 | 1.7454 | 1950 | 20410.0905 | 263.5325 | #N/A | #N/A
9067 | PEORIA 170570198 | 163781705 | PEORIA 1705 | 2.255 | 36 | 0.010197 | 0.36709 | 1951 | 20412.3455 | 263.1654 | #N/A | #N/A
6816 | REDBUD 1101400 | 43191101 | REDBUD 1101 | 0.87662 | 14 | 0.010195 | 0.14273 | 1952 | 20413.2221 | 263.0227 | #N/A | #N/A
5252 | POINT ARENA 110137426 | 43381101 | POINT ARENA 1101 | 0.78956 | 65 | 0.010169 | 0.66101 | 1953 | 20414.0117 | 262.3617 | #N/A | #N/A
7444 | HOLLISTER 21064004 | 182492106 | HOLLISTER 2106 | 8.7531 | 180 | 0.010124 | 1.8224 | 1954 | 20422.7648 | 260.5393 | #N/A | #N/A
2021 | WOODACRE 11021280 | 43021102 | WOODACRE 1102 | 8.5847 | 111 | 0.010109 | 1.1221 | 1955 | 20431.3496 | 259.4173 | #N/A | #N/A
9350 | WEST POINT 1101L3355 | 163201101 | WEST POINT 1101 | 2.2487 | 27 | 0.010104 | 0.2728 | 1956 | 20433.5983 | 259.1445 | #N/A | #N/A
4549 | ALHAMBRA 110595016 | 14101105 | ALHAMBRA 1105 | 0.76011 | 69 | 0.010066 | 0.69458 | 1957 | 20434.3584 | 258.4499 | #N/A | #N/A
5052 | BIG MEADOWS 21012474 | 102812101 | BIG MEADOWS 2101 | 8.3349 | 83 | 0.010035 | 0.83287 | 1958 | 20442.6933 | 257.617 | #N/A | #N/A
616 | SONOMA 1104414 | 42721104 | SONOMA 1104 | 1.3137 | 260 | 0.009991 | 2.5977 | 1959 | 20444.007 | 255.0193 | #N/A | #N/A
8621 | FELTON 0401CB | 83140401 | FELTON 0401 | 2.5249 | 34 | 0.0099584 | 0.33859 | 1960 | 20446.5319 | 254.6808 | #N/A | #N/A
10564 | WISE 110163199 | 152271101 | WISE 1101 | 0.61492 | 8 | 0.0099235 | 0.079388 | 1961 | 20447.1469 | 254.6014 | #N/A | #N/A
6010 | MORGAN HILL 2111XR292 | 83242111 | MORGAN HILL 2111 | 11.1721 | 130 | 0.0098996 | 1.287 | 1962 | 20458.319 | 253.3144 | #N/A | #N/A
222 | DUNBAR 1102CB | 43071102 | DUNBAR 1102 | 7.9142 | 113 | 0.0098816 | 1.1166 | 1963 | 20466.2331 | 252.1978 | #N/A | #N/A
8045 | PERRY 1101W26 | 183071101 | PERRY 1101 | 2.7287 | 18 | 0.0098794 | 0.17783 | 1964 | 20468.9618 | 252.02 | #N/A | #N/A
7530 | BUCKS CREEK 11031131 | 102211103 | BUCKS CREEK 1103 | 2.7496 | 33 | 0.0098607 | 0.3254 | 1965 | 20471.7114 | 251.6946 | #N/A | #N/A
7965 | RINCON 1103568 | 43321103 | RINCON 1103 | 12.6078 | 129 | 0.0098399 | 1.2694 | 1966 | 20484.3192 | 250.4252 | #N/A | #N/A
7623 | PANOCHE 11034008 | 253671103 | PANOCHE 1103 | 35.3757 | 138 | 0.0097859 | 1.3505 | 1967 | 20519.6949 | 249.0748 | #N/A | #N/A
1557 | WILLOW CREEK 11015002 | 192171101 | WILLOW CREEK 1101 | 13.6356 | 161 | 0.0097721 | 1.5733 | 1968 | 20533.3305 | 247.5015 | #N/A | #N/A
2260 | EL DORADO PH 210152456 | 152762101 | EL DORADO PH 2101 | 10.2017 | 96 | 0.0097493 | 0.93593 | 1969 | 20543.5323 | 246.5655 | #N/A | #N/A
4474 | SPENCE 1104965598 | 182201104 | SPENCE 1104 | 9.2081 | 139 | 0.0097442 | 1.3544 | 1970 | 20552.7404 | 245.2111 | #N/A | #N/A
9612 | DIAMOND SPRINGS 1107203504 | 152261107 | DIAMOND SPRINGS 1107 | 0.14077 | 4 | 0.0097327 | 0.038931 | 1971 | 20552.8811 | 245.1721 | #N/A | #N/A
7259 | SUMMIT 1101742 | 152591101 | SUMMIT 1101 | 1.2955 | 21 | 0.009698 | 0.20366 | 1972 | 20554.1766 | 244.9685 | #N/A | #N/A
3486 | GRASS VALLEY 11012208 | 152031101 | GRASS VALLEY 1101 | 11.791 | 159 | 0.0096885 | 1.5405 | 1973 | 20565.9676 | 243.428 | #N/A | #N/A
6926 | EL DORADO PH 210113532 | 152762101 | EL DORADO PH 2101 | 5.3305 | 46 | 0.0096754 | 0.44507 | 1974 | 20571.2981 | 242.9829 | #N/A | #N/A
4034 | OAKHURST 11035120 | 254421103 | OAKHURST 1103 | 6.1606 | 19 | 0.0096488 | 0.18333 | 1975 | 20577.4587 | 242.7996 | 242.7996 | #N/A
3547 | RINCON 1101539980 | 43321101 | RINCON 1101 | 0.295 | 4 | 0.0096291 | 0.038517 | 1976 | 20577.7537 | 242.7611 | #N/A | #N/A
2441 | SILVERADO 2103617828 | 43432103 | SILVERADO 2103 | 1.4315 | 28 | 0.0096279 | 0.26958 | 1977 | 20579.1852 | 242.4915 | #N/A | #N/A
5129 | NEWBURG 1131380686 | 192151131 | NEWBURG 1131 | 1.8735 | 34 | 0.0095954 | 0.32624 | 1978 | 20581.0587 | 242.1653 | #N/A | #N/A
2275 | BUTTE 11051243 | 103081105 | BUTTE 1105 | 5.1707 | 50 | 0.0095359 | 0.47679 | 1979 | 20586.2295 | 241.6885 | #N/A | #N/A
4445 | PINE GROVE 1102467560 | 163751102 | PINE GROVE 1102 | 2.038 | 27 | 0.009532 | 0.25736 | 1980 | 20588.2675 | 241.4311 | #N/A | #N/A
6213 | JESSUP 1103728460 | 103441103 | JESSUP 1103 | 0.72903 | 17 | 0.0095302 | 0.16201 | 1981 | 20588.9965 | 241.2691 | #N/A | #N/A
3085 | SHINGLE SPRINGS 210819622 | 153652108 | SHINGLE SPRINGS 2108 | 5.6185 | 165 | 0.0095283 | 1.5722 | 1982 | 20594.615 | 239.6969 | #N/A | #N/A
9214 | SAN RAFAEL 11081250 | 42011108 | SAN RAFAEL 1108 | 3.5686 | 26 | 0.0094996 | 0.24699 | 1983 | 20598.1837 | 239.4499 | #N/A | #N/A
10597 | MONTE RIO 11135024 | 42811113 | MONTE RIO 1113 | 0.32729 | 4 | 0.0094858 | 0.037943 | 1984 | 20598.5109 | 239.412 | #N/A | #N/A
2882 | WILLOW PASS 2108CB | 13912108 | WILLOW PASS 2108 | 0.19769 | 91 | 0.0094639 | 0.86121 | 1985 | 20598.7086 | 238.5508 | #N/A | #N/A
5172 | LOS OSITOS 2103220608 | 182082103 | LOS OSITOS 2103 | 1.0434 | 10 | 0.009449 | 0.09449 | 1986 | 20599.752 | 238.4563 | #N/A | #N/A
1655 | BRUNSWICK 110750010 | 152481107 | BRUNSWICK 1107 | 6.1163 | 117 | 0.0094406 | 1.1046 | 1987 | 20605.8683 | 237.3518 | #N/A | #N/A
3494 | WILLITS 110434008 | 42661104 | WILLITS 1104 | 22.9249 | 259 | 0.0094239 | 2.4408 | 1988 | 20628.7932 | 234.911 | #N/A | #N/A
7626 | RESERVATION ROAD 11023030 | 182731102 | RESERVATION ROAD 1102 | 10.026 | 186 | 0.0094083 | 1.7499 | 1989 | 20638.8193 | 233.161 | #N/A | #N/A
10686 | HARTLEY 110158095 | 43211101 | HARTLEY 1101 | 0.15657 | 2 | 0.0094017 | 0.018803 | 1990 | 20638.9758 | 233.1422 | #N/A | #N/A
7656 | PHILO 11022600 | 42601102 | PHILO 1102 | 20.0154 | 114 | 0.0093006 | 1.0603 | 1991 | 20658.9912 | 232.0819 | #N/A | #N/A
7863 | SANTA ROSA A 1104642 | 42151104 | SANTA ROSA A 1104 | 9.3201 | 127 | 0.0092364 | 1.173 | 1992 | 20668.3112 | 230.9089 | #N/A | #N/A
581 | POINT ARENA 1101474 | 43381101 | POINT ARENA 1101 | 9.0096 | 77 | 0.0092125 | 0.70936 | 1993 | 20677.3209 | 230.1996 | #N/A | #N/A
9791 | LOS OSITOS 2103695270 | 182082103 | LOS OSITOS 2103 | 0.69372 | 12 | 0.009199 | 0.11039 | 1994 | 20678.0146 | 230.0892 | #N/A | #N/A
9383 | CASTRO VALLEY 1110MR525 | 14091110 | CASTRO VALLEY 1110 | 0.011114 | 2 | 0.0091967 | 0.018393 | 1995 | 20678.0257 | 230.0708 | #N/A | #N/A
5023 | MC ARTHUR 11021324 | 103491102 | MC ARTHUR 1102 | 1.0184 | 169 | 0.0091756 | 1.5507 | 1996 | 20679.0441 | 228.5201 | #N/A | #N/A
7662 | CASTRO VALLEY 1110610800 | 14091110 | CASTRO VALLEY 1110 | 2.4009 | 33 | 0.0091096 | 0.30062 | 1997 | 20681.445 | 228.2195 | #N/A | #N/A
6717 | NEWBURG 1132910230 | 192151132 | NEWBURG 1132 | 0.96986 | 27 | 0.0090947 | 0.24556 | 1998 | 20682.4148 | 227.9739 | #N/A | #N/A
10 | KONOCTI 1102532 | 43311102 | KONOCTI 1102 | 9.7315 | 124 | 0.0090595 | 1.1234 | 1999 | 20692.1463 | 226.8505 | 226.8505 | #N/A
5170 | EL DORADO PH 2102542272 | 152762102 | EL DORADO PH 2102 | 7.8219 | 80 | 0.0090446 | 0.72357 | 2000 | 20699.9682 | 226.127 | #N/A | #N/A
8963 | MIRABEL 1101253331 | 42091101 | MIRABEL 1101 | 0.06691 | 5 | 0.0090171 | 0.045085 | 2001 | 20700.0351 | 226.0819 | #N/A | #N/A
10053 | ROB ROY 21046577 | 83692104 | ROB ROY 2104 | 3.4689 | 33 | 0.0089943 | 0.29681 | 2002 | 20703.504 | 225.7851 | #N/A | #N/A
8505 | NEWBURG 113190242 | 192151131 | NEWBURG 1131 | 4.1346 | 51 | 0.0089934 | 0.45866 | 2003 | 20707.6386 | 225.3264 | #N/A | #N/A
283 | SAN RAFAEL 1104802 | 42011104 | SAN RAFAEL 1104 | 8.5661 | 162 | 0.0089568 | 1.451 | 2004 | 20716.2047 | 223.8754 | #N/A | #N/A
9446 | ECHO SUMMIT 1101481660 | 158031101 | ECHO SUMMIT 1101 | 1.0879 | 21 | 0.0089565 | 0.18809 | 2005 | 20717.2925 | 223.6873 | #N/A | #N/A
1636 | LOS COCHES 1101625902 | 182151101 | LOS COCHES 1101 | 2.6193 | 26 | 0.0089147 | 0.23178 | 2006 | 20719.9118 | 223.4555 | #N/A | #N/A
8007 | SAN JUSTO 11014002 | 183181101 | SAN JUSTO 1101 | 18.3678 | 140 | 0.0088999 | 1.246 | 2007 | 20738.2796 | 222.2095 | #N/A | #N/A
4827 | ATASCADERO 1103A88 | 182541103 | ATASCADERO 1103 | 0.93649 | 41 | 0.008869 | 0.36363 | 2008 | 20739.2161 | 221.8459 | #N/A | #N/A
6300 | DRUM 11011602 | 152321101 | DRUM 1101 | 16.2013 | 121 | 0.0088619 | 1.0723 | 2009 | 20755.4174 | 220.7736 | #N/A | #N/A
7254 | ALLEGHANY 1101VR816 | 152101101 | ALLEGHANY 1101 | 4.1491 | 49 | 0.0088541 | 0.43385 | 2010 | 20759.5665 | 220.3398 | 220.3398 | #N/A
2986 | PINE GROVE 110235576 | 163751102 | PINE GROVE 1102 | 7.8788 | 77 | 0.0088445 | 0.68102 | 2011 | 20767.4453 | 219.6588 | #N/A | #N/A
8230 | SAN LUIS OBISPO 1102357407 | 182631102 | SAN LUIS OBISPO 1102 | 0.23782 | 5 | 0.0088377 | 0.044188 | 2012 | 20767.6831 | 219.6146 | #N/A | #N/A
1189 | PEORIA 170575274 | 163781705 | PEORIA 1705 | 0.38764 | 43 | 0.0088331 | 0.37982 | 2013 | 20768.0708 | 219.2347 | #N/A | #N/A
299 | MONTE RIO 111164758 | 42811111 | MONTE RIO 1111 | 10.4662 | 97 | 0.0087918 | 0.8528 | 2014 | 20778.537 | 218.3819 | #N/A | #N/A
8131 | HARTLEY 1101534548 | 43211101 | HARTLEY 1101 | 0.40005 | 7 | 0.008746 | 0.061222 | 2015 | 20778.937 | 218.3207 | #N/A | #N/A
3395 | BOLINAS 1101504 | 42261101 | BOLINAS 1101 | 6.6893 | 53 | 0.0087025 | 0.46123 | 2016 | 20785.6264 | 217.8595 | #N/A | #N/A
6220 | LAKEVILLE 1102530 | 43371102 | LAKEVILLE 1102 | 0.071467 | 55 | 0.0087005 | 0.47853 | 2017 | 20785.6978 | 217.381 | #N/A | #N/A
8104 | MONTE RIO 111137520 | 42811111 | MONTE RIO 1111 | 2.1367 | 20 | 0.0086846 | 0.17369 | 2018 | 20787.8345 | 217.2073 | #N/A | #N/A
5024 | MONTE RIO 1113180 | 42811113 | MONTE RIO 1113 | 1.9628 | 28 | 0.0086779 | 0.24298 | 2019 | 20789.7973 | 216.9643 | #N/A | #N/A
2418 | CLEAR LAKE 11011302 | 42141101 | CLEAR LAKE 1101 | 7.5749 | 189 | 0.0086777 | 1.6401 | 2020 | 20797.3722 | 215.3242 | #N/A | #N/A
6344 | WEST POINT 11021303 | 163201102 | WEST POINT 1102 | 15.6665 | 146 | 0.0086648 | 1.2651 | 2021 | 20813.0387 | 214.0591 | #N/A | #N/A
147 | SHADY GLEN 11022232 | 152431102 | SHADY GLEN 1102 | 10.4684 | 88 | 0.0086414 | 0.76044 | 2022 | 20823.5072 | 213.2987 | #N/A | #N/A
8652 | LOYOLA 1102725939 | 82161102 | LOYOLA 1102 | 0.093558 | 14 | 0.0086108 | 0.12055 | 2023 | 20823.6007 | 213.1782 | #N/A | #N/A
10013 | GREEN VALLEY 21016601 | 83192101 | GREEN VALLEY 2101 | 1.904 | 19 | 0.0085862 | 0.16314 | 2024 | 20825.5048 | 213.015 | #N/A | #N/A
3970 | PUEBLO 1105348368 | 43291105 | PUEBLO 1105 | 2.7804 | 107 | 0.0085797 | 0.91803 | 2025 | 20828.2852 | 212.097 | #N/A | #N/A
5419 | MIRABEL 11014859 | 42091101 | MIRABEL 1101 | 1.8699 | 22 | 0.0085572 | 0.18826 | 2026 | 20830.155 | 211.9087 | #N/A | #N/A
3836 | PURISIMA 1101CB | 182971101 | PURISIMA 1101 | 3.6778 | 32 | 0.0085315 | 0.27301 | 2027 | 20833.8328 | 211.6357 | #N/A | #N/A
589 | EL DORADO PH 21016852 | 152762101 | EL DORADO PH 2101 | 25.2481 | 309 | 0.0085289 | 2.6354 | 2028 | 20859.081 | 209.0003 | #N/A | #N/A
7704 | GOLDTREE 1107CB | 182581107 | GOLDTREE 1107 | 0.9199 | 28 | 0.0085282 | 0.23879 | 2029 | 20860.0009 | 208.7615 | #N/A | #N/A
10273 | POINT ARENA 11014923 | 43381101 | POINT ARENA 1101 | 2.866 | 12 | 0.008518 | 0.10222 | 2030 | 20862.8668 | 208.6593 | #N/A | #N/A
327 | CURTIS 170463502 | 163351704 | CURTIS 1704 | 10.4643 | 107 | 0.0084952 | 0.90898 | 2031 | 20873.3311 | 207.7503 | #N/A | #N/A
7937 | CLARK ROAD 11022068 | 103091102 | CLARK ROAD 1102 | 10.8871 | 90 | 0.0084897 | 0.76407 | 2032 | 20884.2182 | 206.9862 | #N/A | #N/A
4769 | WYANDOTTE 1107CB | 102911107 | WYANDOTTE 1107 | 1.2619 | 199 | 0.0084763 | 1.6868 | 2033 | 20885.4801 | 205.2995 | #N/A | #N/A
7564 | COLUMBIA HILL 11018233 | 152471101 | COLUMBIA HILL 1101 | 4.9588 | 51 | 0.008467 | 0.43182 | 2034 | 20890.4389 | 204.8676 | #N/A | #N/A
2536 | HALSEY 1101CB | 152241101 | HALSEY 1101 | 17.1811 | 231 | 0.0084422 | 1.9501 | 2035 | 20907.62 | 202.9175 | #N/A | #N/A
2174 | DIAMOND SPRINGS 1104CB | 152261104 | DIAMOND SPRINGS 1104 | 5.6226 | 127 | 0.008393 | 1.0659 | 2036 | 20913.2426 | 201.8516 | #N/A | #N/A
4975 | EL DORADO PH 210119612 | 152762101 | EL DORADO PH 2101 | 9.1294 | 102 | 0.0083743 | 0.85418 | 2037 | 20922.372 | 200.9974 | #N/A | #N/A
7088 | SAUSALITO 11021500 | 42491102 | SAUSALITO 1102 | 1.1618 | 8 | 0.0083473 | 0.066779 | 2038 | 20923.5338 | 200.9306 | #N/A | #N/A
4510 | CAMP EVERS 210511010 | 83622105 | CAMP EVERS 2105 | 2.176 | 26 | 0.0083235 | 0.21641 | 2039 | 20925.7098 | 200.7142 | #N/A | #N/A
7509 | WESTLEY 1103237522 | 162671103 | WESTLEY 1103 | 0.92354 | 39 | 0.0082937 | 0.32346 | 2040 | 20926.6334 | 200.3908 | #N/A | #N/A
2971 | CASTRO VALLEY 1111MR334 | 14091111 | CASTRO VALLEY 1111 | 5.666 | 80 | 0.0082358 | 0.65886 | 2041 | 20932.2994 | 199.7319 | #N/A | #N/A
143 | RACETRACK 1703CB | 163761703 | RACETRACK 1703 | 15.7571 | 216 | 0.008163 | 1.7632 | 2042 | 20948.0565 | 197.9687 | #N/A | #N/A
1117 | MORGAN HILL 2104152774 | 83242104 | MORGAN HILL 2104 | 6.4135 | 84 | 0.0081314 | 0.68304 | 2043 | 20954.4699 | 197.2857 | #N/A | #N/A
3526 | SILVERADO 2103920793 | 43432103 | SILVERADO 2103 | 6.5094 | 51 | 0.008033 | 0.40968 | 2044 | 20960.9794 | 196.876 | #N/A | #N/A
7263 | FORESTHILL 11011820 | 152181101 | FORESTHILL 1101 | 5.735 | 51 | 0.0080276 | 0.40941 | 2045 | 20966.7144 | 196.4666 | #N/A | #N/A
4807 | PLACER 1103238990 | 152461103 | PLACER 1103 | 0.040446 | 84 | 0.0080184 | 0.67354 | 2046 | 20966.7548 | 195.793 | #N/A | #N/A
7786 | UPPER LAKE 11016663 | 42871101 | UPPER LAKE 1101 | 2.3539 | 17 | 0.0079953 | 0.13592 | 2047 | 20969.1088 | 195.6571 | #N/A | #N/A
797 | DUNBAR 1101CB | 43071101 | DUNBAR 1101 | 3.1203 | 191 | 0.007993 | 1.5267 | 2048 | 20972.2291 | 194.1304 | 194.1304 | #N/A
1103 | HOOPA 1101CB | 192401101 | HOOPA 1101 | 23.229 | 440 | 0.0079104 | 3.4806 | 2049 | 20995.4581 | 190.6499 | #N/A | #N/A
8668 | BIG BASIN 110211062 | 82841102 | BIG BASIN 1102 | 13.3177 | 88 | 0.007899 | 0.69511 | 2050 | 21008.7758 | 189.9548 | #N/A | #N/A
7844 | ELK 11011260 | 42981101 | ELK 1101 | 15.6786 | 120 | 0.0078966 | 0.94759 | 2051 | 21024.4544 | 189.0072 | #N/A | #N/A
2387 | HALSEY 110239104 | 152241102 | HALSEY 1102 | 30.6812 | 346 | 0.007888 | 2.7292 | 2052 | 21055.1356 | 186.2779 | #N/A | #N/A
1085 | MORAGA 1101CB | 13801101 | MORAGA 1101 | 8.4595 | 92 | 0.0078811 | 0.72506 | 2053 | 21063.5951 | 185.5529 | #N/A | #N/A
6726 | MARTELL 110292172 | 163011102 | MARTELL 1102 | 0.11858 | 45 | 0.0078638 | 0.35387 | 2054 | 21063.7137 | 185.199 | #N/A | #N/A
1984 | HALF MOON BAY 110369412 | 24101103 | HALF MOON BAY 1103 | 15.5679 | 150 | 0.0078448 | 1.1767 | 2055 | 21079.2816 | 184.0223 | 184.0223 | #N/A
2299 | VINEYARD 2107CB | 14502107 | VINEYARD 2107 | 1.9079 | 111 | 0.0077955 | 0.8653 | 2056 | 21081.1895 | 183.157 | #N/A | #N/A
9627 | POINT ARENA 11011296 | 43381101 | POINT ARENA 1101 | 3.4995 | 37 | 0.007772 | 0.28757 | 2057 | 21084.6891 | 182.8694 | #N/A | #N/A
2765 | FORESTHILL 1101CB | 152181101 | FORESTHILL 1101 | 9.1111 | 110 | 0.0077431 | 0.85174 | 2058 | 21093.8002 | 182.0177 | #N/A | #N/A
4087 | BURNEY 11011340 | 103311101 | BURNEY 1101 | 18.0215 | 144 | 0.0077101 | 1.1103 | 2059 | 21111.8216 | 180.9074 | #N/A | #N/A
8844 | MIDDLETOWN 1101614 | 43141101 | MIDDLETOWN 1101 | 1.3814 | 18 | 0.0076984 | 0.13857 | 2060 | 21113.2031 | 180.7688 | #N/A | #N/A
3083 | MONTE RIO 1113320 | 42811113 | MONTE RIO 1113 | 2.7766 | 29 | 0.0076924 | 0.22308 | 2061 | 21115.9796 | 180.5458 | #N/A | #N/A
7740 | POINT MORETTI 110136514 | 82931101 | POINT MORETTI 1101 | 6.8677 | 64 | 0.0076624 | 0.4904 | 2062 | 21122.8473 | 180.0554 | #N/A | #N/A
898 | COTATI 11055156 | 42271105 | COTATI 1105 | 4.8381 | 114 | 0.0076261 | 0.86938 | 2063 | 21127.6854 | 179.186 | #N/A | #N/A
3027 | PHILO 11021308 | 42601102 | PHILO 1102 | 32.0022 | 245 | 0.0076242 | 1.8679 | 2064 | 21159.6876 | 177.3181 | #N/A | #N/A
10504 | KANAKA 11011036 | 103221101 | KANAKA 1101 | 0.61495 | 4 | 0.0076073 | 0.030429 | 2065 | 21160.3026 | 177.2876 | #N/A | #N/A
2446 | FOOTHILL 1102V06 | 182951102 | FOOTHILL 1102 | 2.2392 | 66 | 0.007606 | 0.50199 | 2066 | 21162.5417 | 176.7856 | #N/A | #N/A
4588 | COARSEGOLD 21025722 | 254432102 | COARSEGOLD 2102 | 1.978 | 23 | 0.0076053 | 0.17492 | 2067 | 21164.5197 | 176.6107 | #N/A | #N/A
8714 | OTTER 1101CB | 182941101 | OTTER 1101 | 6.4437 | 54 | 0.0075954 | 0.41015 | 2068 | 21170.9634 | 176.2006 | #N/A | #N/A
9866 | DUNBAR 1101343 | 43071101 | DUNBAR 1101 | 4.4381 | 39 | 0.0075606 | 0.29486 | 2069 | 21175.4015 | 175.9057 | #N/A | #N/A
723 | BIG BASIN 110296986 | 82841102 | BIG BASIN 1102 | 5.9027 | 63 | 0.0075562 | 0.47604 | 2070 | 21181.3043 | 175.4297 | #N/A | #N/A
5272 | NEWBURG 1133CB | 192151133 | NEWBURG 1133 | 3.163 | 92 | 0.0075338 | 0.69311 | 2071 | 21184.4672 | 174.7365 | #N/A | #N/A
6817 | HALF MOON BAY 1103695411 | 24101103 | HALF MOON BAY 1103 | 8.2989 | 99 | 0.0075292 | 0.74539 | 2072 | 21192.7662 | 173.9911 | #N/A | #N/A
9735 | EEL RIVER 1103216324 | 192381103 | EEL RIVER 1103 | 2.2883 | 23 | 0.0075204 | 0.17297 | 2073 | 21195.0545 | 173.8182 | #N/A | #N/A
803 | DIAMOND SPRINGS 1107CB | 152261107 | DIAMOND SPRINGS 1107 | 0 | 51 | 0.0074949 | 0.38224 | 2074 | 21195.0545 | 173.4359 | #N/A | #N/A
2229 | EL DORADO PH 210136764 | 152762101 | EL DORADO PH 2101 | 3.129 | 46 | 0.0074941 | 0.34473 | 2075 | 21198.1835 | 173.0912 | #N/A | #N/A
5945 | SANTA ROSA A 1111758024 | 42151111 | SANTA ROSA A 1111 | 4.7171 | 72 | 0.007484 | 0.53884 | 2076 | 21202.9007 | 172.5524 | #N/A | #N/A
726 | DIAMOND SPRINGS 1106930190 | 152261106 | DIAMOND SPRINGS 1106 | 17.1408 | 207 | 0.0074761 | 1.5476 | 2077 | 21220.0415 | 171.0048 | #N/A | #N/A
353 | CURTIS 170210940 | 163351702 | CURTIS 1702 | 8.5923 | 138 | 0.0073788 | 1.0183 | 2078 | 21228.6337 | 169.9865 | #N/A | #N/A
1231 | RED BLUFF 1103CB | 103541103 | RED BLUFF 1103 | 0.10234 | 261 | 0.0073172 | 1.9098 | 2079 | 21228.7361 | 168.0767 | #N/A | #N/A
10001 | PANOCHE 11034036 | 253671103 | PANOCHE 1103 | 9.9443 | 57 | 0.0073003 | 0.41612 | 2080 | 21238.6804 | 167.6606 | #N/A | #N/A
9426 | GREEN VALLEY 2101380922 | 83192101 | GREEN VALLEY 2101 | 0.98732 | 30 | 0.0072901 | 0.2187 | 2081 | 21239.6677 | 167.4419 | #N/A | #N/A
1700 | LUCERNE 110676850 | 43351106 | LUCERNE 1106 | 2.1492 | 51 | 0.0072691 | 0.37072 | 2082 | 21241.8169 | 167.0712 | #N/A | #N/A
2002 | HOLLISTER 21054018 | 182492105 | HOLLISTER 2105 | 44.4195 | 280 | 0.0072679 | 2.035 | 2083 | 21286.2364 | 165.0362 | #N/A | #N/A
2867 | MONTE RIO 1113346 | 42811113 | MONTE RIO 1113 | 10.0437 | 101 | 0.0072159 | 0.72881 | 2084 | 21296.2802 | 164.3074 | #N/A | #N/A
7311 | LOS OSITOS 2102258878 | 182082102 | LOS OSITOS 2102 | 3.3295 | 26 | 0.0072141 | 0.18757 | 2085 | 21299.6097 | 164.1198 | #N/A | #N/A
1213 | WOODACRE 1102137662 | 43021102 | WOODACRE 1102 | 8.585 | 104 | 0.0071841 | 0.74714 | 2086 | 21308.1947 | 163.3727 | #N/A | #N/A
2384 | BONNIE NOOK 1102CB | 152301102 | BONNIE NOOK 1102 | 34.0109 | 337 | 0.0071702 | 2.4164 | 2087 | 21342.2056 | 160.9563 | #N/A | #N/A
324 | PLACERVILLE 1110953474 | 153081110 | PLACERVILLE 1110 | 10.6374 | 133 | 0.0071239 | 0.94748 | 2088 | 21352.843 | 160.0088 | #N/A | #N/A
9849 | FOOTHILL 1101722270 | 182951101 | FOOTHILL 1101 | 0.17623 | 5 | 0.0070957 | 0.035479 | 2089 | 21353.0192 | 159.9733 | #N/A | #N/A
3510 | MONTE RIO 1111140 | 42811111 | MONTE RIO 1111 | 8.4064 | 96 | 0.0070376 | 0.67561 | 2090 | 21361.4256 | 159.2977 | #N/A | #N/A
1551 | CARLOTTA 11214914 | 192291121 | CARLOTTA 1121 | 10.6261 | 138 | 0.0070374 | 0.97117 | 2091 | 21372.0518 | 158.3266 | #N/A | #N/A
4560 | COARSEGOLD 210210330 | 254432102 | COARSEGOLD 2102 | 9.6646 | 90 | 0.0069896 | 0.62906 | 2092 | 21381.7164 | 157.6975 | #N/A | #N/A
6442 | PIT NO 1 11019702 | 103721101 | PIT NO 1 1101 | 0.64383 | 91 | 0.006985 | 0.63564 | 2093 | 21382.3602 | 157.0619 | #N/A | #N/A
8877 | WILLOW CREEK 11013050 | 192171101 | WILLOW CREEK 1101 | 2.6251 | 18 | 0.0069828 | 0.12569 | 2094 | 21384.9852 | 156.9362 | #N/A | #N/A
9559 | SONOMA 1103581588 | 42721103 | SONOMA 1103 | 0.19454 | 14 | 0.0069585 | 0.097419 | 2095 | 21385.1798 | 156.8388 | #N/A | #N/A
2326 | BRUNSWICK 11052140 | 152481105 | BRUNSWICK 1105 | 34.5738 | 373 | 0.0069513 | 2.5928 | 2096 | 21419.7536 | 154.2459 | #N/A | #N/A
7797 | SAUSALITO 1101331806 | 42491101 | SAUSALITO 1101 | 0.49662 | 5 | 0.0069274 | 0.034637 | 2097 | 21420.2502 | 154.2113 | #N/A | #N/A
1778 | WEIMAR 11026175 | 152491102 | WEIMAR 1102 | 2.7461 | 30 | 0.0069045 | 0.20713 | 2098 | 21422.9963 | 154.0042 | #N/A | #N/A
2962 | CURTIS 1704803 | 163351704 | CURTIS 1704 | 9.7146 | 93 | 0.0068944 | 0.64118 | 2099 | 21432.7109 | 153.363 | #N/A | #N/A
5429 | MIRABEL 1101228 | 42091101 | MIRABEL 1101 | 2.115 | 123 | 0.0068367 | 0.84091 | 2100 | 21434.8259 | 152.5221 | #N/A | #N/A
8011 | HORSESHOE 1101603250 | 152571101 | HORSESHOE 1101 | 0.57636 | 21 | 0.0068337 | 0.14351 | 2101 | 21435.4023 | 152.3786 | #N/A | #N/A
7095 | PUEBLO 2102618 | 43292102 | PUEBLO 2102 | 0.46132 | 118 | 0.0068234 | 0.80516 | 2102 | 21435.8636 | 151.5734 | #N/A | #N/A
8240 | WOODSIDE 11018601 | 24251101 | WOODSIDE 1101 | 0.59766 | 9 | 0.0067792 | 0.061013 | 2103 | 21436.4613 | 151.5124 | #N/A | #N/A
3848 | REEDLEY 11127240 | 252341112 | REEDLEY 1112 | 0.96577 | 234 | 0.0067642 | 1.5828 | 2104 | 21437.427 | 149.9296 | #N/A | #N/A
4429 | SONOMA 1105138 | 42721105 | SONOMA 1105 | 0.064666 | 197 | 0.0067556 | 1.3309 | 2105 | 21437.4917 | 148.5987 | #N/A | #N/A
1588 | CORRAL 110359770 | 162991103 | CORRAL 1103 | 4.8165 | 97 | 0.0067467 | 0.65443 | 2106 | 21442.3082 | 147.9443 | #N/A | #N/A
6984 | GABILAN 1101566352 | 182331101 | GABILAN 1101 | 0.42309 | 9 | 0.0067421 | 0.060679 | 2107 | 21442.7313 | 147.8836 | #N/A | #N/A
8546 | SPENCE 1102990464 | 182201102 | SPENCE 1102 | 2.092 | 53 | 0.0067321 | 0.3568 | 2108 | 21444.8233 | 147.5268 | #N/A | #N/A
9813 | BOLINAS 110137034 | 42261101 | BOLINAS 1101 | 4.5289 | 16 | 0.006701 | 0.10722 | 2109 | 21449.3522 | 147.4196 | #N/A | #N/A
8495 | PENRYN 110550550 | 152561105 | PENRYN 1105 | 0 | 127 | 0.0066813 | 0.84852 | 2110 | 21449.3522 | 146.5711 | #N/A | #N/A
533 | HIGHLANDS 110439458 | 43361104 | HIGHLANDS 1104 | 1.1825 | 72 | 0.0066627 | 0.47971 | 2111 | 21450.5347 | 146.0913 | #N/A | #N/A
6908 | MENLO 11038512 | 24131103 | MENLO 1103 | 24.7387 | 228 | 0.0066372 | 1.5133 | 2112 | 21475.2734 | 144.5781 | #N/A | #N/A
1455 | LAS GALLINAS A 1105904 | 42991105 | LAS GALLINAS A 1105 | 1.5346 | 78 | 0.0066274 | 0.51694 | 2113 | 21476.808 | 144.0611 | #N/A | #N/A
2184 | GEYSERVILLE 110289714 | 42891102 | GEYSERVILLE 1102 | 0.11077 | 71 | 0.0066271 | 0.47052 | 2114 | 21476.9188 | 143.5906 | #N/A | #N/A
2865 | MOLINO 1102344 | 42571102 | MOLINO 1102 | 1.5085 | 77 | 0.0066172 | 0.50953 | 2115 | 21478.4273 | 143.0811 | #N/A | #N/A
2057 | SHINGLE SPRINGS 210911092 | 153652109 | SHINGLE SPRINGS 2109 | 22.4365 | 239 | 0.0066099 | 1.5798 | 2116 | 21500.8638 | 141.5013 | #N/A | #N/A
10095 | SILVERADO 2104645 | 43432104 | SILVERADO 2104 | 1.0111 | 13 | 0.0065604 | 0.085285 | 2117 | 21501.8749 | 141.416 | #N/A | #N/A
6812 | CLOVERDALE 1101474708 | 42821101 | CLOVERDALE 1101 | 0.2623 | 13 | 0.0065356 | 0.084962 | 2118 | 21502.1372 | 141.3311 | #N/A | #N/A
891 | TEMPLETON 2108A64 | 183052108 | TEMPLETON 2108 | 2.0152 | 150 | 0.0065293 | 0.9794 | 2119 | 21504.1525 | 140.3517 | #N/A | #N/A
851 | HIGGINS 1110861610 | 152691110 | HIGGINS 1110 | 1.0502 | 99 | 0.0065286 | 0.64633 | 2120 | 21505.2027 | 139.7053 | #N/A | #N/A
10050 | MIRABEL 110286326 | 42091102 | MIRABEL 1102 | 0.70422 | 5 | 0.0065228 | 0.032614 | 2121 | 21505.9069 | 139.6727 | #N/A | #N/A
1904 | SONOMA 1105404 | 42721105 | SONOMA 1105 | 2.3529 | 63 | 0.0065164 | 0.41053 | 2122 | 21508.2598 | 139.2622 | #N/A | #N/A
4884 | PLACERVILLE 1112CB | 153081112 | PLACERVILLE 1112 | 8.513 | 117 | 0.0065148 | 0.76223 | 2123 | 21516.7728 | 138.5 | 138.5 | #N/A
3571 | OAKHURST 110377384 | 254421103 | OAKHURST 1103 | 4.7207 | 61 | 0.0065145 | 0.39738 | 2124 | 21521.4935 | 138.1026 | #N/A | #N/A
2586 | VOLTA 11021504 | 102541102 | VOLTA 1102 | 8.2955 | 95 | 0.0065125 | 0.61869 | 2125 | 21529.789 | 137.4839 | #N/A | #N/A
5574 | PARADISE 1104920400 | 102831104 | PARADISE 1104 | 4.6854 | 66 | 0.0064968 | 0.42879 | 2126 | 21534.4744 | 137.0551 | #N/A | #N/A
3679 | SUNOL 1101MR297 | 14241101 | SUNOL 1101 | 5.9239 | 66 | 0.0064881 | 0.42822 | 2127 | 21540.3983 | 136.6269 | #N/A | #N/A
3379 | GEYSERVILLE 1101354 | 42891101 | GEYSERVILLE 1101 | 0.62784 | 79 | 0.0064828 | 0.51214 | 2128 | 21541.0262 | 136.1147 | #N/A | #N/A
5354 | FORT ROSS 1121560 | 42851121 | FORT ROSS 1121 | 5.0625 | 31 | 0.0064599 | 0.20026 | 2129 | 21546.0887 | 135.9145 | #N/A | #N/A
1701 | CALAVERAS CEMENT 110136880 | 162211101 | CALAVERAS CEMENT 1101 | 6.1526 | 92 | 0.0064477 | 0.59319 | 2130 | 21552.2412 | 135.3213 | #N/A | #N/A
3076 | PLACERVILLE 21061104 | 153082106 | PLACERVILLE 2106 | 49.4989 | 462 | 0.0064469 | 2.9785 | 2131 | 21601.7401 | 132.3428 | 132.3428 | #N/A
6813 | CASTRO VALLEY 111010315 | 14091110 | CASTRO VALLEY 1110 | 5.489 | 53 | 0.006431 | 0.34084 | 2132 | 21607.2291 | 132.002 | #N/A | #N/A
7135 | MOLINO 1102982462 | 42571102 | MOLINO 1102 | 1.4422 | 18 | 0.006427 | 0.11569 | 2133 | 21608.6713 | 131.8863 | #N/A | #N/A
8349 | BRUNSWICK 1110CB | 152481110 | BRUNSWICK 1110 | 0.0034177 | 26 | 0.0064174 | 0.16685 | 2134 | 21608.6748 | 131.7194 | 131.7194 | #N/A
3244 | PLACERVILLE 111219712 | 153081112 | PLACERVILLE 1112 | 12.9125 | 151 | 0.0064118 | 0.96818 | 2135 | 21621.5873 | 130.7513 | #N/A | #N/A
3409 | PINE GROVE 110213438 | 163751102 | PINE GROVE 1102 | 16.5438 | 172 | 0.0063999 | 1.1008 | 2136 | 21638.1311 | 129.6505 | #N/A | #N/A
9640 | OLEMA 110149756 | 42291101 | OLEMA 1101 | 1.0738 | 40 | 0.0063622 | 0.25449 | 2137 | 21639.2049 | 129.396 | #N/A | #N/A
5813 | PERRY 1101CB | 183071101 | PERRY 1101 | 2.539 | 27 | 0.0062536 | 0.16885 | 2138 | 21641.7438 | 129.2271 | #N/A | #N/A
5598 | FROGTOWN 170236870 | 163451702 | FROGTOWN 1702 | 0.33642 | 29 | 0.0062483 | 0.1812 | 2139 | 21642.0803 | 129.0459 | #N/A | #N/A
7823 | FORT BRAGG A 11013113 | 42761101 | FORT BRAGG A 1101 | 10.0269 | 68 | 0.0062347 | 0.42396 | 2140 | 21652.1072 | 128.622 | 128.622 | #N/A
3839 | PARADISE 11052214 | 102831105 | PARADISE 1105 | 15.0808 | 233 | 0.0062243 | 1.4503 | 2141 | 21667.188 | 127.1717 | #N/A | #N/A
955 | STANISLAUS 170179826 | 162821701 | STANISLAUS 1701 | 10.3076 | 95 | 0.0062159 | 0.59051 | 2142 | 21677.4956 | 126.5812 | #N/A | #N/A
165 | CHALLENGE 110198174 | 103201101 | CHALLENGE 1101 | 12.2322 | 66 | 0.0062048 | 0.40952 | 2143 | 21689.7278 | 126.1717 | #N/A | #N/A
2120 | BRUNSWICK 110350070 | 152481103 | BRUNSWICK 1103 | 17.7473 | 201 | 0.0062036 | 1.2469 | 2144 | 21707.475 | 124.9248 | 124.9248 | #N/A
4607 | SARATOGA 1107413816 | 83371107 | SARATOGA 1107 | 11.1426 | 104 | 0.0061927 | 0.64404 | 2145 | 21718.6176 | 124.2807 | #N/A | #N/A
1564 | SAN LUIS OBISPO 1101483444 | 182631101 | SAN LUIS OBISPO 1101 | 2.0579 | 67 | 0.0061552 | 0.4124 | 2146 | 21720.6754 | 123.8683 | #N/A | #N/A
4427 | PLACERVILLE 11118582 | 153081111 | PLACERVILLE 1111 | 9.4809 | 163 | 0.0061345 | 0.99993 | 2147 | 21730.1563 | 122.8684 | #N/A | #N/A
9649 | LOS GATOS 1107LA60 | 82021107 | LOS GATOS 1107 | 8.6744 | 61 | 0.0061263 | 0.3737 | 2148 | 21738.8308 | 122.4947 | #N/A | #N/A
3992 | VOLTA 11021502 | 102541102 | VOLTA 1102 | 7.2593 | 80 | 0.0061144 | 0.48915 | 2149 | 21746.0901 | 122.0056 | #N/A | #N/A
4576 | VALLEY VIEW 1106CB | 14341106 | VALLEY VIEW 1106 | 3.7553 | 50 | 0.0060781 | 0.30391 | 2150 | 21749.8454 | 121.7016 | #N/A | #N/A
10363 | SAN LEANDRO U 1114653758 | 13111114 | SAN LEANDRO U 1114 | 0.36194 | 5 | 0.0060671 | 0.030336 | 2151 | 21750.2074 | 121.6713 | #N/A | #N/A
7007 | ORO FINO 110238698 | 103031102 | ORO FINO 1102 | 15.6488 | 103 | 0.0060349 | 0.62159 | 2152 | 21765.8562 | 121.0497 | #N/A | #N/A
3531 | HALF MOON BAY 11039112 | 24101103 | HALF MOON BAY 1103 | 0.86172 | 68 | 0.0060009 | 0.40806 | 2153 | 21766.7179 | 120.6417 | #N/A | #N/A
9344 | HALF MOON BAY 1101821698 | 24101101 | HALF MOON BAY 1101 | 0.84831 | 9 | 0.0060008 | 0.054007 | 2154 | 21767.5662 | 120.5876 | #N/A | #N/A
10526 | SANTA ROSA A 1108409621 | 42151108 | SANTA ROSA A 1108 | 0.13619 | 4 | 0.0059943 | 0.023977 | 2155 | 21767.7024 | 120.5637 | #N/A | #N/A
3796 | CAMP EVERS 210612518 | 83622106 | CAMP EVERS 2106 | 15.6477 | 145 | 0.0059295 | 0.85978 | 2156 | 21783.3501 | 119.7039 | #N/A | #N/A
2601 | BRUNSWICK 11062104 | 152481106 | BRUNSWICK 1106 | 9.8261 | 123 | 0.0059169 | 0.72777 | 2157 | 21793.1763 | 118.9761 | #N/A | #N/A
2204 | OAKHURST 11035470 | 254421103 | OAKHURST 1103 | 9.3162 | 104 | 0.0059093 | 0.61457 | 2158 | 21802.4925 | 118.3616 | #N/A | #N/A
2618 | ARVIN 110194892 | 253801101 | ARVIN 1101 | 0.21503 | 66 | 0.0059064 | 0.38983 | 2159 | 21802.7075 | 117.9717 | #N/A | #N/A
6041 | CAMP EVERS 210694770 | 83622106 | CAMP EVERS 2106 | 2.3658 | 55 | 0.0059058 | 0.32482 | 2160 | 21805.0733 | 117.6469 | #N/A | #N/A
1981 | COTATI 1105328 | 42271105 | COTATI 1105 | 1.5009 | 173 | 0.0058817 | 1.0175 | 2161 | 21806.5742 | 116.6294 | #N/A | #N/A
519 | POINT ARENA 110147952 | 43381101 | POINT ARENA 1101 | 10.3901 | 88 | 0.0058506 | 0.51485 | 2162 | 21816.9643 | 116.1145 | #N/A | #N/A
2535 | COTATI 1102825 | 42271102 | COTATI 1102 | 0.46579 | 26 | 0.0058122 | 0.15112 | 2163 | 21817.4301 | 115.9634 | #N/A | #N/A
698 | RESERVATION ROAD 11013026 | 182731101 | RESERVATION ROAD 1101 | 21.8777 | 238 | 0.0057671 | 1.3726 | 2164 | 21839.3078 | 114.5908 | #N/A | #N/A
4296 | MORGAN HILL 2105XR494 | 83242105 | MORGAN HILL 2105 | 0.45836 | 98 | 0.0057504 | 0.56354 | 2165 | 21839.7662 | 114.0273 | #N/A | #N/A
875 | FULTON 110777670 | 42561107 | FULTON 1107 | 6.7586 | 98 | 0.0057454 | 0.56305 | 2166 | 21846.5248 | 113.4642 | #N/A | #N/A
2839 | CAMP EVERS 210510294 | 83622105 | CAMP EVERS 2105 | 8.3915 | 95 | 0.0057046 | 0.54194 | 2167 | 21854.9163 | 112.9223 | #N/A | #N/A
4923 | GEYSERVILLE 1101480 | 42891101 | GEYSERVILLE 1101 | 1.5553 | 161 | 0.0057021 | 0.91803 | 2168 | 21856.4716 | 112.0043 | #N/A | #N/A
5117 | WOODSIDE 11018912 | 24251101 | WOODSIDE 1101 | 3.8961 | 52 | 0.0056974 | 0.29627 | 2169 | 21860.3677 | 111.708 | #N/A | #N/A
6008 | GEYSERVILLE 1101482 | 42891101 | GEYSERVILLE 1101 | 0.36983 | 38 | 0.0056711 | 0.2155 | 2170 | 21860.7375 | 111.4925 | #N/A | #N/A
3612 | BIG BASIN 110212992 | 82841102 | BIG BASIN 1102 | 14.242 | 160 | 0.0056575 | 0.90521 | 2171 | 21874.9796 | 110.5873 | #N/A | #N/A
151 | SUMMIT 1102CB | 152591102 | SUMMIT 1102 | 1.0531 | 22 | 0.0056462 | 0.12422 | 2172 | 21876.0327 | 110.4631 | #N/A | #N/A
585 | LUCERNE 110647198 | 43351106 | LUCERNE 1106 | 3.0699 | 70 | 0.0056207 | 0.39345 | 2173 | 21879.1026 | 110.0696 | #N/A | #N/A
7910 | SILVERADO 2105167360 | 43432105 | SILVERADO 2105 | 9.5796 | 70 | 0.0056116 | 0.39281 | 2174 | 21888.6822 | 109.6768 | #N/A | #N/A
1304 | CURTIS 17028000 | 163351702 | CURTIS 1702 | 14.3291 | 174 | 0.0056032 | 0.97497 | 2175 | 21903.0112 | 108.7018 | #N/A | #N/A
417 | RALSTON 1101CB | 24141101 | RALSTON 1101 | 0.37713 | 37 | 0.0055946 | 0.207 | 2176 | 21903.3884 | 108.4948 | #N/A | #N/A
1975 | RALSTON 11022028 | 24141102 | RALSTON 1102 | 2.0968 | 38 | 0.0055851 | 0.21223 | 2177 | 21905.4852 | 108.2826 | #N/A | #N/A
6769 | ATASCADERO 1101A50 | 182541101 | ATASCADERO 1101 | 19.3404 | 269 | 0.0055802 | 1.5011 | 2178 | 21924.8256 | 106.7815 | #N/A | #N/A
2377 | GUALALA 11121294 | 42841112 | GUALALA 1112 | 19.8593 | 234 | 0.0055387 | 1.2961 | 2179 | 21944.6849 | 105.4855 | #N/A | #N/A
5858 | FAIRVIEW 2207P150 | 13432207 | FAIRVIEW 2207 | 2.2703 | 18 | 0.0055206 | 0.09937 | 2180 | 21946.9552 | 105.3861 | #N/A | #N/A
2861 | PIT NO 5 11011660 | 101321101 | PIT NO 5 1101 | 4.8823 | 43 | 0.0055185 | 0.23729 | 2181 | 21951.8375 | 105.1488 | #N/A | #N/A
4568 | RINCON 1101CB | 43321101 | RINCON 1101 | 1.6038 | 68 | 0.0054995 | 0.37397 | 2182 | 21953.4413 | 104.7748 | #N/A | #N/A
8511 | SAN ARDO 1101610148 | 182191101 | SAN ARDO 1101 | 1.9606 | 58 | 0.0054812 | 0.31791 | 2183 | 21955.4019 | 104.4569 | #N/A | #N/A
4730 | HARTLEY 110194178 | 43211101 | HARTLEY 1101 | 2.1488 | 57 | 0.0054615 | 0.3113 | 2184 | 21957.5507 | 104.1456 | #N/A | #N/A
1445 | BIG BASIN 1102CB | 82841102 | BIG BASIN 1102 | 6.1923 | 59 | 0.0054141 | 0.31943 | 2185 | 21963.743 | 103.8262 | #N/A | #N/A
6388 | HALF MOON BAY 11036012 | 24101103 | HALF MOON BAY 1103 | 6.6683 | 79 | 0.0054078 | 0.42722 | 2186 | 21970.4113 | 103.399 | 103.399 | #N/A
629 | LAURELES 11112020 | 182371111 | LAURELES 1111 | 34.3538 | 281 | 0.005376 | 1.5107 | 2187 | 22004.7651 | 101.8883 | #N/A | #N/A
3079 | OCEANO 1102V50 | 182601102 | OCEANO 1102 | 7.1582 | 107 | 0.005367 | 0.57427 | 2188 | 22011.9233 | 101.3141 | #N/A | #N/A
342 | WOODACRE 1101404 | 43021101 | WOODACRE 1101 | 12.4146 | 152 | 0.0053668 | 0.81576 | 2189 | 22024.3378 | 100.4983 | #N/A | #N/A
4506 | TIDEWATER 210657926 | 14652106 | TIDEWATER 2106 | 0.12479 | 97 | 0.0053561 | 0.51954 | 2190 | 22024.4626 | 99.9788 | #N/A | #N/A
6794 | CAMP EVERS 21055188 | 83622105 | CAMP EVERS 2105 | 2.0389 | 19 | 0.0053482 | 0.10162 | 2191 | 22026.5016 | 99.8771 | #N/A | #N/A
4962 | MONTE RIO 1113652 | 42811113 | MONTE RIO 1113 | 1.6208 | 25 | 0.0053427 | 0.13357 | 2192 | 22028.1224 | 99.7436 | #N/A | #N/A
5950 | COTATI 1102260 | 42271102 | COTATI 1102 | 2.6831 | 68 | 0.0053405 | 0.36316 | 2193 | 22030.8055 | 99.3804 | #N/A | #N/A
2816 | HICKS 2101574315 | 83432101 | HICKS 2101 | 7.399 | 78 | 0.005318 | 0.4148 | 2194 | 22038.2045 | 98.9656 | #N/A | #N/A
4882 | NARROWS 210276952 | 153132102 | NARROWS 2102 | 2.2675 | 161 | 0.0052383 | 0.84337 | 2195 | 22040.472 | 98.1222 | #N/A | #N/A
8374 | SAN JOAQUIN #3 1103501771 | 252531103 | SAN JOAQUIN #3 1103 | 4.9047 | 54 | 0.0052248 | 0.28214 | 2196 | 22045.3767 | 97.8401 | #N/A | #N/A
4446 | OTTER 1101440 | 182941101 | OTTER 1101 | 8.3237 | 107 | 0.0051543 | 0.5515 | 2197 | 22053.7004 | 97.2886 | #N/A | #N/A
1813 | PUEBLO 210375612 | 43292103 | PUEBLO 2103 | 0 | 114 | 0.0051135 | 0.58294 | 2198 | 22053.7004 | 96.7057 | #N/A | #N/A
3962 | POINT MORETTI 110112122 | 82931101 | POINT MORETTI 1101 | 6.5695 | 63 | 0.0051004 | 0.32133 | 2199 | 22060.2699 | 96.3843 | #N/A | #N/A
6972 | BRUNSWICK 1102940 | 152481102 | BRUNSWICK 1102 | 1.1878 | 46 | 0.005067 | 0.23308 | 2200 | 22061.4577 | 96.1513 | #N/A | #N/A
2994 | SHADY GLEN 110132726 | 152431101 | SHADY GLEN 1101 | 12.17 | 146 | 0.00506 | 0.73876 | 2201 | 22073.6277 | 95.4125 | #N/A | #N/A
5931 | EAST QUINCY 11012452 | 102551101 | EAST QUINCY 1101 | 0.14202 | 87 | 0.0050248 | 0.43716 | 2202 | 22073.7697 | 94.9753 | #N/A | #N/A
1799 | MORGAN HILL 2105XR578 | 83242105 | MORGAN HILL 2105 | 0.16225 | 12 | 0.0050174 | 0.060209 | 2203 | 22073.932 | 94.9151 | #N/A | #N/A
5416 | ANNAPOLIS 1101528344 | 42861101 | ANNAPOLIS 1101 | 26.9559 | 171 | 0.0049999 | 0.85498 | 2204 | 22100.8879 | 94.0601 | #N/A | #N/A
7537 | LOS OSITOS 2102148504 | 182082102 | LOS OSITOS 2102 | 0.17139 | 14 | 0.0049963 | 0.069948 | 2205 | 22101.0593 | 93.9902 | #N/A | #N/A
235 | KONOCTI 11022293 | 43311102 | KONOCTI 1102 | 1.753 | 21 | 0.0049653 | 0.10427 | 2206 | 22102.8123 | 93.8859 | #N/A | #N/A
3072 | ANTLER 1101CB | 103271101 | ANTLER 1101 | 1.6 | 18 | 0.0049349 | 0.088829 | 2207 | 22104.4123 | 93.7971 | #N/A | #N/A
8410 | CAMP EVERS 210611533 | 83622106 | CAMP EVERS 2106 | 2.6412 | 28 | 0.0048855 | 0.13679 | 2208 | 22107.0535 | 93.6603 | #N/A | #N/A
3050 | AUBERRY 1101R324 | 254151101 | AUBERRY 1101 | 10.7137 | 119 | 0.0048731 | 0.5799 | 2209 | 22117.7672 | 93.0804 | #N/A | #N/A
9906 | POINT MORETTI 110183716 | 82931101 | POINT MORETTI 1101 | 2.503 | 22 | 0.0048588 | 0.10689 | 2210 | 22120.2703 | 92.9735 | #N/A | #N/A
5631 | PARADISE 1105878870 | 102831105 | PARADISE 1105 | 2.5217 | 29 | 0.0048412 | 0.1404 | 2211 | 22122.792 | 92.8331 | #N/A | #N/A
1901 | MOUNTAIN QUARRIES 21011184 | 152282101 | MOUNTAIN QUARRIES 2101 | 11.6971 | 136 | 0.0048403 | 0.65828 | 2212 | 22134.4891 | 92.1748 | #N/A | #N/A
4871 | BRUNSWICK 11052130 | 152481105 | BRUNSWICK 1105 | 14.4069 | 163 | 0.0048209 | 0.78581 | 2213 | 22148.896 | 91.389 | #N/A | #N/A
10520 | CASTRO VALLEY 1110MR273 | 14091110 | CASTRO VALLEY 1110 | 0.72381 | 13 | 0.0047919 | 0.062294 | 2214 | 22149.6198 | 91.3267 | #N/A | #N/A
9367 | REDBUD 110244119 | 43191102 | REDBUD 1102 | 0.31866 | 35 | 0.0047623 | 0.16668 | 2215 | 22149.9385 | 91.1601 | #N/A | #N/A
1147 | STAFFORD 11011082 | 43201101 | STAFFORD 1101 | 1.5607 | 36 | 0.0047619 | 0.17143 | 2216 | 22151.4992 | 90.9886 | #N/A | #N/A
2516 | MIWUK 17028130 | 163661702 | MIWUK 1702 | 9.9199 | 123 | 0.0047602 | 0.5855 | 2217 | 22161.4191 | 90.4031 | #N/A | #N/A
2340 | JESSUP 1102CB | 103441102 | JESSUP 1102 | 0.099243 | 47 | 0.0047601 | 0.22372 | 2218 | 22161.5184 | 90.1794 | #N/A | #N/A
10932 | CALPELLA 1102127462 | 43411102 | CALPELLA 1102 | 0.11763 | 2 | 0.0047158 | 0.0094316 | 2219 | 22161.636 | 90.17 | #N/A | #N/A
9177 | MORAGA 1105829530 | 13801105 | MORAGA 1105 | 1.6704 | 32 | 0.0047024 | 0.15048 | 2220 | 22163.3064 | 90.0195 | #N/A | #N/A
1591 | SAN JOAQUIN #3 1101673480 | 252531101 | SAN JOAQUIN #3 1101 | 12.7333 | 88 | 0.0046984 | 0.41346 | 2221 | 22176.0397 | 89.606 | #N/A | #N/A
7450 | WILLOW CREEK 1103CB | 192171103 | WILLOW CREEK 1103 | 3.92 | 54 | 0.0046671 | 0.25202 | 2222 | 22179.9596 | 89.354 | #N/A | #N/A
3048 | LAURELES 1111432 | 182371111 | LAURELES 1111 | 49.3307 | 320 | 0.0046501 | 1.488 | 2223 | 22229.2903 | 87.866 | #N/A | #N/A
9657 | PIT NO 5 1101CB | 101321101 | PIT NO 5 1101 | 0.72234 | 10 | 0.0046279 | 0.046279 | 2224 | 22230.0127 | 87.8197 | #N/A | #N/A
2107 | MIRABEL 110238514 | 42091102 | MIRABEL 1102 | 10.7254 | 102 | 0.0046099 | 0.47021 | 2225 | 22240.7381 | 87.3495 | #N/A | #N/A
4382 | WOODSIDE 11011922 | 24251101 | WOODSIDE 1101 | 4.594 | 70 | 0.004588 | 0.32116 | 2226 | 22245.3321 | 87.0283 | #N/A | #N/A
4539 | LOS GATOS 110760118 | 82021107 | LOS GATOS 1107 | 27.9074 | 323 | 0.0045775 | 1.4785 | 2227 | 22273.2395 | 85.5498 | #N/A | #N/A
8332 | VINEYARD 2108MR172 | 14502108 | VINEYARD 2108 | 0.5325 | 26 | 0.0045679 | 0.11876 | 2228 | 22273.772 | 85.431 | #N/A | #N/A
4690 | CORRAL 1103681991 | 162991103 | CORRAL 1103 | 1.3748 | 50 | 0.0045171 | 0.22586 | 2229 | 22275.1468 | 85.2052 | #N/A | #N/A
10188 | BOLINAS 11011232 | 42261101 | BOLINAS 1101 | 2.2606 | 22 | 0.0045024 | 0.099054 | 2230 | 22277.4074 | 85.1061 | #N/A | #N/A
4590 | REDBUD 11021212 | 43191102 | REDBUD 1102 | 0 | 62 | 0.0044984 | 0.2789 | 2231 | 22277.4074 | 84.8272 | #N/A | #N/A
6700 | TIVY VALLEY 1107CB | 252941107 | TIVY VALLEY 1107 | 0.18027 | 155 | 0.0044835 | 0.69495 | 2232 | 22277.5876 | 84.1323 | #N/A | #N/A
7824 | CAYUCOS 1102317156 | 182551102 | CAYUCOS 1102 | 2.3719 | 67 | 0.0044039 | 0.29506 | 2233 | 22279.9595 | 83.8372 | #N/A | #N/A
9117 | WEST POINT 11021535 | 163201102 | WEST POINT 1102 | 3.0662 | 30 | 0.0043786 | 0.13136 | 2234 | 22283.0257 | 83.7058 | #N/A | #N/A
1000 | MORGAN HILL 2111CB | 83242111 | MORGAN HILL 2111 | 0.2194 | 38 | 0.0043636 | 0.16582 | 2235 | 22283.2451 | 83.54 | #N/A | #N/A
9339 | LAKEWOOD 2109432198 FM | 13532109 | LAKEWOOD 2109 | 0.56371 | 31 | 0.004363 | 0.13525 | 2236 | 22283.8088 | 83.4048 | #N/A | #N/A
420 | ARCATA 11225384 | 192021122 | ARCATA 1122 | 15.5688 | 202 | 0.0043604 | 0.88081 | 2237 | 22299.3777 | 82.524 | #N/A | #N/A
268 | MIRABEL 1102332 | 42091102 | MIRABEL 1102 | 5.7022 | 67 | 0.0043573 | 0.29194 | 2238 | 22305.0799 | 82.232 | #N/A | #N/A
6281 | MONTE RIO 11131989 | 42811113 | MONTE RIO 1113 | 0.74282 | 9 | 0.0043487 | 0.039138 | 2239 | 22305.8227 | 82.1929 | #N/A | #N/A
11081 | OAKHURST 110310723 | 254421103 | OAKHURST 1103 | 0.0039412 | 1 | 0.0043094 | 0.0043094 | 2240 | 22305.8266 | 82.1886 | #N/A | #N/A
8151 | SILVERADO 2105309298 | 43432105 | SILVERADO 2105 | 1.0992 | 23 | 0.0043094 | 0.099116 | 2241 | 22306.9259 | 82.0895 | #N/A | #N/A
4858 | GUALALA 111223444 | 42841112 | GUALALA 1112 | 14.5312 | 135 | 0.0042666 | 0.57599 | 2242 | 22321.457 | 81.5135 | #N/A | #N/A
2658 | CAMP EVERS 210660124 | 83622106 | CAMP EVERS 2106 | 22.4613 | 267 | 0.0042657 | 1.1389 | 2243 | 22343.9183 | 80.3745 | #N/A | #N/A
7144 | BELLEVUE 1102392 | 43181102 | BELLEVUE 1102 | 0.25165 | 68 | 0.0042431 | 0.28853 | 2244 | 22344.17 | 80.086 | #N/A | #N/A
5164 | MORAGA 1104N532R | 13801104 | MORAGA 1104 | 3.6935 | 65 | 0.004228 | 0.27482 | 2245 | 22347.8635 | 79.8112 | #N/A | #N/A
9096 | BIG BASIN 11022253 | 82841102 | BIG BASIN 1102 | 1.4514 | 12 | 0.0041981 | 0.050377 | 2246 | 22349.3149 | 79.7608 | #N/A | #N/A
4580 | WEST POINT 11021341 | 163201102 | WEST POINT 1102 | 9.8988 | 87 | 0.0041901 | 0.36454 | 2247 | 22359.2137 | 79.3962 | #N/A | #N/A
2630 | MC ARTHUR 110153120 | 103491101 | MC ARTHUR 1101 | 0.10763 | 92 | 0.004183 | 0.38483 | 2248 | 22359.3213 | 79.0114 | #N/A | #N/A
9114 | LAS GALLINAS A 1105CB | 42991105 | LAS GALLINAS A 1105 | 0.44146 | 26 | 0.0041416 | 0.10768 | 2249 | 22359.7628 | 78.9037 | #N/A | #N/A
2500 | EL DORADO PH 2101CB | 152762101 | EL DORADO PH 2101 | 7.4577 | 74 | 0.0041406 | 0.3064 | 2250 | 22367.2205 | 78.5973 | #N/A | #N/A
2083 | ALTO 11201214 | 42031120 | ALTO 1120 | 3.4493 | 45 | 0.004132 | 0.18594 | 2251 | 22370.6698 | 78.4114 | #N/A | #N/A
1240 | EL DORADO PH 210126000 | 152762101 | EL DORADO PH 2101 | 34.3764 | 339 | 0.0041222 | 1.3974 | 2252 | 22405.0461 | 77.014 | #N/A | #N/A
2830 | MENLO 11029110 | 24131102 | MENLO 1102 | 0.92693 | 138 | 0.0040502 | 0.55893 | 2253 | 22405.9731 | 76.455 | #N/A | #N/A
8665 | BRUNSWICK 111094368 | 152481110 | BRUNSWICK 1110 | 0.37065 | 9 | 0.0040353 | 0.036317 | 2254 | 22406.3437 | 76.4187 | #N/A | #N/A
2181 | MERCED FALLS 110222774 | 252811102 | MERCED FALLS 1102 | 1.0094 | 27 | 0.0040151 | 0.10841 | 2255 | 22407.3531 | 76.3103 | #N/A | #N/A
2725 | BIG BASIN 110212124 | 82841102 | BIG BASIN 1102 | 4.4856 | 59 | 0.0040119 | 0.2367 | 2256 | 22411.8387 | 76.0736 | #N/A | #N/A
1448 | PARADISE 1103CB | 102831103 | PARADISE 1103 | 1.3783 | 61 | 0.0039747 | 0.24245 | 2257 | 22413.2169 | 75.8311 | #N/A | #N/A
3467 | WEIMAR 11012740 | 152491101 | WEIMAR 1101 | 19.2287 | 235 | 0.003969 | 0.93271 | 2258 | 22432.4457 | 74.8984 | #N/A | #N/A
497 | AUBURN 1101173014 | 152161101 | AUBURN 1101 | 3.2881 | 43 | 0.0039357 | 0.16924 | 2259 | 22435.7338 | 74.7292 | #N/A | #N/A
7194 | WEST POINT 1101L373 | 163201101 | WEST POINT 1101 | 7.3956 | 93 | 0.0039044 | 0.36311 | 2260 | 22443.1294 | 74.3661 | #N/A | #N/A
6474 | STAFFORD 11021048 | 43201102 | STAFFORD 1102 | 5.2734 | 72 | 0.0039018 | 0.28093 | 2261 | 22448.4027 | 74.0851 | #N/A | #N/A
4378 | RESERVATION ROAD 110222136 | 182731102 | RESERVATION ROAD 1102 | 1.7669 | 59 | 0.0038829 | 0.22909 | 2262 | 22450.1697 | 73.856 | #N/A | #N/A
7747 | ANITA 1106552724 | 102841106 | ANITA 1106 | 1.4691 | 77 | 0.0038689 | 0.29791 | 2263 | 22451.6388 | 73.5581 | #N/A | #N/A
6189 | PLACER 1101106534 | 152461101 | PLACER 1101 | 1.2115 | 38 | 0.0038425 | 0.14601 | 2264 | 22452.8503 | 73.4121 | #N/A | #N/A
8134 | MORAGA 110518396 | 13801105 | MORAGA 1105 | 0.18228 | 16 | 0.0038298 | 0.061277 | 2265 | 22453.0325 | 73.3509 | #N/A | #N/A
2828 | PANORAMA 11019092 | 103461101 | PANORAMA 1101 | 0.15856 | 113 | 0.0038237 | 0.43208 | 2266 | 22453.1911 | 72.9188 | #N/A | #N/A
1451 | MIWUK 1701953336 | 163661701 | MIWUK 1701 | 11.8581 | 132 | 0.0038168 | 0.50381 | 2267 | 22465.0492 | 72.415 | 72.415 | #N/A
8189 | CAMP EVERS 210660120 | 83622106 | CAMP EVERS 2106 | 4.3466 | 42 | 0.0038109 | 0.16006 | 2268 | 22469.3957 | 72.2549 | #N/A | #N/A
3086 | PANOCHE 11034016 | 253671103 | PANOCHE 1103 | 2.3473 | 59 | 0.0038045 | 0.22447 | 2269 | 22471.7431 | 72.0304 | #N/A | #N/A
3744 | FORESTHILL 110150486 | 152181101 | FORESTHILL 1101 | 11.6759 | 163 | 0.0037623 | 0.61325 | 2270 | 22483.419 | 71.4172 | #N/A | #N/A
1371 | PINE GROVE 11021222 | 163751102 | PINE GROVE 1102 | 17.2598 | 218 | 0.0037571 | 0.81905 | 2271 | 22500.6788 | 70.5981 | 70.5981 | #N/A
2904 | MONTE RIO 111153477 | 42811111 | MONTE RIO 1111 | 2.0483 | 21 | 0.0037529 | 0.078812 | 2272 | 22502.7271 | 70.5193 | #N/A | #N/A
4467 | RINCON 1102CB | 43321102 | RINCON 1102 | 2.9661 | 49 | 0.0037209 | 0.18233 | 2273 | 22505.6933 | 70.337 | #N/A | #N/A
4949 | BRENTWOOD 210598606 | 14592105 | BRENTWOOD 2105 | 0.086065 | 88 | 0.0037138 | 0.32681 | 2274 | 22505.7793 | 70.0102 | #N/A | #N/A
8946 | MIRABEL 110213597 | 42091102 | MIRABEL 1102 | 0.46726 | 6 | 0.0037122 | 0.022273 | 2275 | 22506.2466 | 69.9879 | #N/A | #N/A
3893 | FAIRVIEW 2207P304 | 13432207 | FAIRVIEW 2207 | 5.2458 | 47 | 0.0037077 | 0.17426 | 2276 | 22511.4924 | 69.8137 | #N/A | #N/A
7178 | BURNEY 11019042 | 103311101 | BURNEY 1101 | 3.1577 | 31 | 0.0036996 | 0.11469 | 2277 | 22514.6501 | 69.699 | #N/A | #N/A
8790 | MONTICELLO 110152910 | 43051101 | MONTICELLO 1101 | 2.182 | 41 | 0.0036877 | 0.1512 | 2278 | 22516.8321 | 69.5478 | #N/A | #N/A
8586 | WEST POINT 1102L3733 | 163201102 | WEST POINT 1102 | 1.7527 | 22 | 0.0036798 | 0.080956 | 2279 | 22518.5848 | 69.4668 | #N/A | #N/A
2143 | VOLTA 11029742 | 102541102 | VOLTA 1102 | 9.1272 | 120 | 0.0036718 | 0.44061 | 2280 | 22527.712 | 69.0262 | #N/A | #N/A
8195 | SAUSALITO 11021268 | 42491102 | SAUSALITO 1102 | 4.9334 | 46 | 0.0036642 | 0.16855 | 2281 | 22532.6454 | 68.8577 | #N/A | #N/A
200 | PETALUMA C 1109270 | 42631109 | PETALUMA C 1109 | 2.1115 | 101 | 0.0036568 | 0.36934 | 2282 | 22534.7569 | 68.4883 | #N/A | #N/A
9326 | COARSEGOLD 2102383092 | 254432102 | COARSEGOLD 2102 | 0.3811 | 5 | 0.0036345 | 0.018173 | 2283 | 22535.138 | 68.4701 | #N/A | #N/A
10306 | SOLEDAD 1114413916 | 182051114 | SOLEDAD 1114 | 1.4145 | 24 | 0.0036248 | 0.086994 | 2284 | 22536.5525 | 68.3832 | #N/A | #N/A
6836 | LLAGAS 2106338878 | 83182106 | LLAGAS 2106 | 2.051 | 23 | 0.0036203 | 0.083266 | 2285 | 22538.6034 | 68.2999 | #N/A | #N/A
685 | MONTE RIO 1113524 | 42811113 | MONTE RIO 1113 | 6.2639 | 76 | 0.0036171 | 0.2749 | 2286 | 22544.8674 | 68.025 | #N/A | #N/A
3555 | DUNBAR 1103CB | 43071103 | DUNBAR 1103 | 2.6944 | 149 | 0.0036086 | 0.53768 | 2287 | 22547.5617 | 67.4873 | #N/A | #N/A
6157 | IGNACIO 11041290 | 42481104 | IGNACIO 1104 | 4.0937 | 126 | 0.0035797 | 0.45104 | 2288 | 22551.6554 | 67.0363 | #N/A | #N/A
1177 | ORO FINO 1101CB | 103031101 | ORO FINO 1101 | 22.3304 | 271 | 0.0035789 | 0.96987 | 2289 | 22573.9859 | 66.0664 | #N/A | #N/A
3178 | PENNGROVE 1101461338 | 43471101 | PENNGROVE 1101 | 1.7854 | 24 | 0.0035591 | 0.085418 | 2290 | 22575.7713 | 65.981 | #N/A | #N/A
3360 | GRASS VALLEY 1101CB | 152031101 | GRASS VALLEY 1101 | 0.87991 | 32 | 0.0035509 | 0.11363 | 2291 | 22576.6512 | 65.8673 | #N/A | #N/A
10815 | HICKS 2101949522 | 83432101 | HICKS 2101 | 0.44016 | 2 | 0.0035464 | 0.0070929 | 2292 | 22577.0914 | 65.8603 | #N/A | #N/A
6548 | WEST POINT 110113444 | 163201101 | WEST POINT 1101 | 17.021 | 221 | 0.0035258 | 0.77919 | 2293 | 22594.1124 | 65.0811 | #N/A | #N/A
2950 | HICKS 2101XR162 | 83432101 | HICKS 2101 | 0.61478 | 122 | 0.0035232 | 0.42983 | 2294 | 22594.7272 | 64.6512 | #N/A | #N/A
9560 | VINEYARD 2107246084 | 14502107 | VINEYARD 2107 | 0.23943 | 7 | 0.0035033 | 0.024523 | 2295 | 22594.9666 | 64.6267 | #N/A | #N/A
3073 | CAMP EVERS 210510728 | 83622105 | CAMP EVERS 2105 | 10.4737 | 134 | 0.0034865 | 0.46719 | 2296 | 22605.4403 | 64.1595 | #N/A | #N/A
7203 | BRUNSWICK 110663124 | 152481106 | BRUNSWICK 1106 | 5.893 | 65 | 0.0034764 | 0.22596 | 2297 | 22611.3333 | 63.9336 | #N/A | #N/A
7594 | SHINGLE SPRINGS 2108CB | 153652108 | SHINGLE SPRINGS 2108 | 1.4768 | 18 | 0.0034725 | 0.062504 | 2298 | 22612.81 | 63.871 | #N/A | #N/A
180 | HIGGINS 11041374 | 152691104 | HIGGINS 1104 | 7.7503 | 117 | 0.0034694 | 0.40592 | 2299 | 22620.5603 | 63.4651 | #N/A | #N/A
8764 | TRES PINOS 1111203126 | 183221111 | TRES PINOS 1111 | 0.066788 | 58 | 0.0034419 | 0.19963 | 2300 | 22620.6271 | 63.2655 | #N/A | #N/A
6133 | SALT SPRINGS 210237300 | 163692102 | SALT SPRINGS 2102 | 6.9662 | 41 | 0.0034152 | 0.14002 | 2301 | 22627.5932 | 63.1255 | #N/A | #N/A
8353 | VOLTA 110254932 | 102541102 | VOLTA 1102 | 4.377 | 46 | 0.0034144 | 0.15706 | 2302 | 22631.9703 | 62.9684 | #N/A | #N/A
1504 | HUMBOLDT BAY 1102741980 | 192341102 | HUMBOLDT BAY 1102 | 5.7434 | 81 | 0.0034064 | 0.27592 | 2303 | 22637.7137 | 62.6925 | #N/A | #N/A
341 | COTATI 1102464 | 42271102 | COTATI 1102 | 2.1402 | 103 | 0.0034005 | 0.35026 | 2304 | 22639.8539 | 62.3422 | #N/A | #N/A
1877 | FORT BRAGG A 110231304 | 42761102 | FORT BRAGG A 1102 | 21.6783 | 119 | 0.0033857 | 0.40289 | 2305 | 22661.5322 | 61.9394 | #N/A | #N/A
9731 | FITCH MOUNTAIN 1111792628 | 42751111 | FITCH MOUNTAIN 1111 | 0.22723 | 13 | 0.0033779 | 0.043913 | 2306 | 22661.7594 | 61.8954 | #N/A | #N/A
10338 | FRANKLIN 1104P146 | 13921104 | FRANKLIN 1104 | 3.6318 | 36 | 0.0033674 | 0.12123 | 2307 | 22665.3912 | 61.7742 | #N/A | #N/A
11025 | CALPINE 1144304 | 48011144 | CALPINE 1144 | 0.046368 | 2 | 0.0033555 | 0.006711 | 2308 | 22665.4376 | 61.7675 | #N/A | #N/A
7073 | RINCON 1101663641 | 43321101 | RINCON 1101 | 0.72937 | 13 | 0.0033545 | 0.043609 | 2309 | 22666.1669 | 61.7239 | #N/A | #N/A
37 | CURTIS 17019230 | 163351701 | CURTIS 1701 | 2.5262 | 41 | 0.0033425 | 0.13704 | 2310 | 22668.6931 | 61.5868 | #N/A | #N/A
7129 | GANSNER 1101336664 | 103021101 | GANSNER 1101 | 0.72016 | 16 | 0.0033324 | 0.053319 | 2311 | 22669.4133 | 61.5335 | #N/A | #N/A
6003 | CALPELLA 1102477890 | 43411102 | CALPELLA 1102 | 1.0733 | 35 | 0.0033264 | 0.11642 | 2312 | 22670.4866 | 61.4171 | #N/A | #N/A
6936 | LAMONT 11024222 | 253911102 | LAMONT 1102 | 2.6385 | 87 | 0.0033258 | 0.28934 | 2313 | 22673.1251 | 61.1278 | #N/A | #N/A
1031 | VOLTA 110253130 | 102541102 | VOLTA 1102 | 13.8057 | 168 | 0.0033207 | 0.55788 | 2314 | 22686.9308 | 60.5699 | #N/A | #N/A
729 | RADUM 1105806392 | 13151105 | RADUM 1105 | 3.3853 | 79 | 0.0033155 | 0.26192 | 2315 | 22690.3161 | 60.308 | #N/A | #N/A
6737 | POINT ARENA 1101476 | 43381101 | POINT ARENA 1101 | 2.9988 | 97 | 0.0032902 | 0.31915 | 2316 | 22693.3149 | 59.9888 | #N/A | #N/A
9971 | LOS OSITOS 2103258688 | 182082103 | LOS OSITOS 2103 | 1.0735 | 17 | 0.0032882 | 0.0559 | 2317 | 22694.3884 | 59.9329 | #N/A | #N/A
2467 | HARRIS 1109183860 | 192431109 | HARRIS 1109 | 4.9361 | 92 | 0.0032843 | 0.30215 | 2318 | 22699.3245 | 59.6308 | #N/A | #N/A
3741 | PINE GROVE 110152088 | 163751101 | PINE GROVE 1101 | 2.4775 | 28 | 0.0032783 | 0.091793 | 2319 | 22701.802 | 59.539 | #N/A | #N/A
8487 | PIT NO 3 21011482 | 103732101 | PIT NO 3 2101 | 12.0356 | 43 | 0.0032735 | 0.14076 | 2320 | 22713.8376 | 59.3982 | #N/A | #N/A
9213 | GREEN VALLEY 210197574 | 83192101 | GREEN VALLEY 2101 | 3.5697 | 60 | 0.0032547 | 0.19528 | 2321 | 22717.4072 | 59.2029 | #N/A | #N/A
6945 | CHOLAME 2102X06 | 182562102 | CHOLAME 2102 | 0.40519 | 40 | 0.0032533 | 0.13013 | 2322 | 22717.8124 | 59.0728 | #N/A | #N/A
1559 | PAUL SWEET 21065178 | 83252106 | PAUL SWEET 2106 | 7.1789 | 84 | 0.0032408 | 0.27223 | 2323 | 22724.9914 | 58.8006 | #N/A | #N/A
8048 | DEL MONTE 21042762 | 182222104 | DEL MONTE 2104 | 9.3599 | 138 | 0.0032245 | 0.44498 | 2324 | 22734.3513 | 58.3556 | #N/A | #N/A
394 | WOODSIDE 11049032 | 24251104 | WOODSIDE 1104 | 2.1459 | 72 | 0.0032245 | 0.23216 | 2325 | 22736.4972 | 58.1234 | #N/A | #N/A
3140 | BAYWOOD 1101CB | 182801101 | BAYWOOD 1101 | 4.6156 | 214 | 0.003207 | 0.6863 | 2326 | 22741.1128 | 57.4371 | #N/A | #N/A
197 | BRUNSWICK 1105733408 | 152481105 | BRUNSWICK 1105 | 3.447 | 45 | 0.0032065 | 0.14429 | 2327 | 22744.5598 | 57.2928 | #N/A | #N/A
1600 | RINCON 1104786782 | 43321104 | RINCON 1104 | 2.2059 | 46 | 0.0032053 | 0.14745 | 2328 | 22746.7657 | 57.1454 | #N/A | #N/A
7931 | PIT NO 5 11011658 | 101321101 | PIT NO 5 1101 | 4.5409 | 25 | 0.0031839 | 0.079597 | 2329 | 22751.3066 | 57.0658 | #N/A | #N/A
4023 | DUNLAP 11037080 | 254061103 | DUNLAP 1103 | 10.5819 | 67 | 0.0031698 | 0.21238 | 2330 | 22761.8885 | 56.8534 | #N/A | #N/A
7290 | ARCATA 1121716954 | 192021121 | ARCATA 1121 | 6.9085 | 97 | 0.0031691 | 0.30741 | 2331 | 22768.7969 | 56.546 | #N/A | #N/A
8705 | CARLOTTA 112144150 | 192291121 | CARLOTTA 1121 | 3.5717 | 13 | 0.0031685 | 0.04119 | 2332 | 22772.3686 | 56.5048 | #N/A | #N/A
5063 | WOODSIDE 11043583 | 24251104 | WOODSIDE 1104 | 2.8372 | 38 | 0.0031615 | 0.12014 | 2333 | 22775.2057 | 56.3847 | #N/A | #N/A
8125 | PINE GROVE 1101CB | 163751101 | PINE GROVE 1101 | 4.3027 | 57 | 0.0031502 | 0.17956 | 2334 | 22779.5084 | 56.2051 | #N/A | #N/A
6730 | CAMP EVERS 210637210 | 83622106 | CAMP EVERS 2106 | 6.0576 | 65 | 0.0031442 | 0.20437 | 2335 | 22785.566 | 56.0007 | #N/A | #N/A
82 | SNEATH LANE 1107CB | 22721107 | SNEATH LANE 1107 | 1.0038 | 45 | 0.003121 | 0.14045 | 2336 | 22786.5698 | 55.8603 | 55.8603 | #N/A
1487 | STAFFORD 11021258 | 43201102 | STAFFORD 1102 | 0.31195 | 65 | 0.0031184 | 0.2027 | 2337 | 22786.8817 | 55.6576 | #N/A | #N/A
201 | RESERVATION ROAD 1101CB | 182731101 | RESERVATION ROAD 1101 | 5.1043 | 106 | 0.0031059 | 0.32923 | 2338 | 22791.9861 | 55.3284 | #N/A | #N/A
9832 | WILLOW CREEK 1101CB | 192171101 | WILLOW CREEK 1101 | 0.28641 | 6 | 0.0031037 | 0.018622 | 2339 | 22792.2725 | 55.3097 | #N/A | #N/A
22 | PARADISE 1104457900 | 102831104 | PARADISE 1104 | 12.0452 | 208 | 0.0030985 | 0.64448 | 2340 | 22804.3177 | 54.6653 | #N/A | #N/A
7703 | SILVERADO 21051306 | 43432105 | SILVERADO 2105 | 0.24462 | 55 | 0.0030939 | 0.17016 | 2341 | 22804.5623 | 54.4951 | #N/A | #N/A
8415 | BIG MEADOWS 21012476 | 102812101 | BIG MEADOWS 2101 | 8.1111 | 75 | 0.0030704 | 0.23028 | 2342 | 22812.6734 | 54.2648 | #N/A | #N/A
2480 | REDBUD 1101CB | 43191101 | REDBUD 1101 | 3.3608 | 91 | 0.0030523 | 0.27776 | 2343 | 22816.0342 | 53.987 | #N/A | #N/A
10178 | MAPLE CREEK 1101555034 | 192101101 | MAPLE CREEK 1101 | 1.4947 | 8 | 0.0030461 | 0.024368 | 2344 | 22817.5289 | 53.9627 | #N/A | #N/A
1443 | MENLO 11028952 | 24131102 | MENLO 1102 | 6.6746 | 82 | 0.0030386 | 0.24916 | 2345 | 22824.2034 | 53.7135 | #N/A | #N/A
5316 | PAUL SWEET 210610424 | 83252106 | PAUL SWEET 2106 | 5.688 | 87 | 0.0030267 | 0.26332 | 2346 | 22829.8914 | 53.4502 | #N/A | #N/A
2267 | ELK 11011298 | 42981101 | ELK 1101 | 12.4112 | 119 | 0.0030233 | 0.35978 | 2347 | 22842.3026 | 53.0904 | #N/A | #N/A
6724 | CURTIS 17039210 | 163351703 | CURTIS 1703 | 22.4939 | 124 | 0.0030209 | 0.37459 | 2348 | 22864.7965 | 52.7158 | #N/A | #N/A
3063 | ELECTRA 1101L1697 | 162161101 | ELECTRA 1101 | 5.7698 | 70 | 0.0030208 | 0.21145 | 2349 | 22870.5662 | 52.5044 | #N/A | #N/A
8682 | CLARKSVILLE 210951744 | 153612109 | CLARKSVILLE 2109 | 1.3051 | 25 | 0.0030149 | 0.075372 | 2350 | 22871.8713 | 52.429 | #N/A | #N/A
6410 | SILVERADO 2105616 | 43432105 | SILVERADO 2105 | 0.4965 | 103 | 0.0030112 | 0.31016 | 2351 | 22872.3678 | 52.1188 | #N/A | #N/A
2231 | HICKS 2103LB50 | 83432103 | HICKS 2103 | 11.268 | 65 | 0.0029902 | 0.19436 | 2352 | 22883.6359 | 51.9245 | #N/A | #N/A
1742 | MIWUK 1701CB | 163661701 | MIWUK 1701 | 16.2494 | 187 | 0.0029901 | 0.55914 | 2353 | 22899.8853 | 51.3653 | 51.3653 | #N/A
4916 | SARATOGA 1107167792 | 83371107 | SARATOGA 1107 | 4.6865 | 48 | 0.0029842 | 0.14324 | 2354 | 22904.5718 | 51.2221 | #N/A | #N/A
55 | CURTIS 170234426 | 163351702 | CURTIS 1702 | 4.718 | 81 | 0.0029697 | 0.24054 | 2355 | 22909.2898 | 50.9816 | #N/A | #N/A
4236 | LOS GATOS 1106LA64 | 82021106 | LOS GATOS 1106 | 12.6946 | 152 | 0.0029684 | 0.4512 | 2356 | 22921.9844 | 50.5304 | #N/A | #N/A
6476 | PAUL SWEET 21068091 | 83252106 | PAUL SWEET 2106 | 6.0152 | 69 | 0.0029648 | 0.20457 | 2357 | 22927.9996 | 50.3258 | #N/A | #N/A
7197 | BIG BASIN 110212758 | 82841102 | BIG BASIN 1102 | 5.982 | 70 | 0.002947 | 0.20629 | 2358 | 22933.9816 | 50.1195 | #N/A | #N/A
2069 | BIG BASIN 11025066 | 82841102 | BIG BASIN 1102 | 13.7481 | 121 | 0.0029066 | 0.35169 | 2359 | 22947.7297 | 49.7678 | #N/A | #N/A
8715 | OLEMA 1101602 | 42291101 | OLEMA 1101 | 16.1792 | 115 | 0.0028981 | 0.33328 | 2360 | 22963.9089 | 49.4345 | #N/A | #N/A
5548 | ANTLER 11011384 | 103271101 | ANTLER 1101 | 9.1423 | 106 | 0.0028857 | 0.30589 | 2361 | 22973.0512 | 49.1286 | #N/A | #N/A
2497 | ROB ROY 210410714 | 83692104 | ROB ROY 2104 | 14.1675 | 212 | 0.002884 | 0.61141 | 2362 | 22987.2187 | 48.5172 | #N/A | #N/A
2343 | OCEANO 1104CB | 182601104 | OCEANO 1104 | 4.5697 | 146 | 0.0028615 | 0.41777 | 2363 | 22991.7883 | 48.0995 | #N/A | #N/A
7790 | SANTA ROSA A 1111147198 | 42151111 | SANTA ROSA A 1111 | 1.3511 | 24 | 0.0028527 | 0.068464 | 2364 | 22993.1395 | 48.031 | #N/A | #N/A
5803 | BEN LOMOND 04015206 | 83040401 | BEN LOMOND 0401 | 7.16 | 78 | 0.0028387 | 0.22141 | 2365 | 23000.2994 | 47.8096 | #N/A | #N/A
6276 | MONTE RIO 1113202 | 42811113 | MONTE RIO 1113 | 5.2711 | 55 | 0.0028293 | 0.15561 | 2366 | 23005.5705 | 47.654 | #N/A | #N/A
6911 | DEL MONTE 21042624 | 182222104 | DEL MONTE 2104 | 18.5151 | 148 | 0.0028273 | 0.41844 | 2367 | 23024.0856 | 47.2355 | #N/A | #N/A
3771 | CURTIS 170510590 | 163351705 | CURTIS 1705 | 16.3818 | 199 | 0.0028226 | 0.56169 | 2368 | 23040.4674 | 46.6738 | #N/A | #N/A
2714 | MIWUK 1702CB | 163661702 | MIWUK 1702 | 9.055 | 110 | 0.0028161 | 0.30977 | 2369 | 23049.5224 | 46.3641 | 46.3641 | #N/A
3825 | SARATOGA 1105LC14 | 83371105 | SARATOGA 1105 | 9.869 | 137 | 0.0028157 | 0.38575 | 2370 | 23059.3914 | 45.9783 | #N/A | #N/A
5150 | HAMILTON BRANCH 11012046 | 102361101 | HAMILTON BRANCH 1101 | 9.1511 | 57 | 0.0028141 | 0.1604 | 2371 | 23068.5425 | 45.8179 | #N/A | #N/A
6397 | BRUNSWICK 110584480 | 152481105 | BRUNSWICK 1105 | 4.7332 | 50 | 0.0028064 | 0.14032 | 2372 | 23073.2758 | 45.6776 | #N/A | #N/A
7609 | SAN LUIS OBISPO 1107V58 | 182631107 | SAN LUIS OBISPO 1107 | 1.1426 | 25 | 0.0027879 | 0.069698 | 2373 | 23074.4184 | 45.6079 | #N/A | #N/A
10167 | HAMILTON BRANCH 11012436 | 102361101 | HAMILTON BRANCH 1101 | 5.3051 | 19 | 0.0027598 | 0.052436 | 2374 | 23079.7235 | 45.5555 | #N/A | #N/A
289 | BIG BASIN 110169550 | 82841101 | BIG BASIN 1101 | 17.5407 | 188 | 0.0027545 | 0.51784 | 2375 | 23097.2642 | 45.0376 | #N/A | #N/A
3662 | SONOMA 1107294 | 42721107 | SONOMA 1107 | 0 | 66 | 0.002743 | 0.18104 | 2376 | 23097.2642 | 44.8566 | #N/A | #N/A
6355 | BIG RIVER 11017273 | 43081101 | BIG RIVER 1101 | 6.618 | 38 | 0.0027408 | 0.10415 | 2377 | 23103.8822 | 44.7524 | #N/A | #N/A
7672 | POINT ARENA 11012637 | 43381101 | POINT ARENA 1101 | 4.0402 | 28 | 0.0027385 | 0.076678 | 2378 | 23107.9223 | 44.6758 | #N/A | #N/A
1790 | CAMP EVERS 210510912 | 83622105 | CAMP EVERS 2105 | 4.8632 | 54 | 0.0027343 | 0.14765 | 2379 | 23112.7856 | 44.5281 | #N/A | #N/A
10750 | BOGARD 1101CB | 103301101 | BOGARD 1101 | 0.51616 | 7 | 0.0027213 | 0.019049 | 2380 | 23113.3017 | 44.5091 | #N/A | #N/A
6610 | GREEN VALLEY 210112824 | 83192101 | GREEN VALLEY 2101 | 0.87637 | 97 | 0.0027199 | 0.26383 | 2381 | 23114.1781 | 44.2452 | #N/A | #N/A
6375 | HOLLISTER 21054048 | 182492105 | HOLLISTER 2105 | 18.1541 | 157 | 0.0027194 | 0.42694 | 2382 | 23132.3322 | 43.8183 | #N/A | #N/A
317 | PARADISE 11042206 | 102831104 | PARADISE 1104 | 4.1388 | 227 | 0.0027 | 0.61291 | 2383 | 23136.4709 | 43.2054 | #N/A | #N/A
6305 | WILLOW CREEK 110191926 | 192171101 | WILLOW CREEK 1101 | 6.438 | 48 | 0.0026935 | 0.12929 | 2384 | 23142.9089 | 43.0761 | #N/A | #N/A
5185 | SILVERADO 21023010 | 43432102 | SILVERADO 2102 | 0.35395 | 106 | 0.0026922 | 0.28537 | 2385 | 23143.2629 | 42.7907 | #N/A | #N/A
122 | STANISLAUS 17021888 | 162821702 | STANISLAUS 1702 | 18.9186 | 231 | 0.0026855 | 0.62036 | 2386 | 23162.1815 | 42.1704 | #N/A | #N/A
7468 | ROB ROY 210410298 | 83692104 | ROB ROY 2104 | 10.9608 | 138 | 0.0026825 | 0.37018 | 2387 | 23173.1423 | 41.8002 | #N/A | #N/A
3981 | CAMP EVERS 210510214 | 83622105 | CAMP EVERS 2105 | 13.9276 | 149 | 0.0026769 | 0.39885 | 2388 | 23187.0699 | 41.4013 | #N/A | #N/A
4982 | WEST POINT 110136674 | 163201101 | WEST POINT 1101 | 9.4121 | 125 | 0.0026639 | 0.33299 | 2389 | 23196.4821 | 41.0683 | #N/A | #N/A
7345 | WILLOW CREEK 110129362 | 192171101 | WILLOW CREEK 1101 | 7.6889 | 74 | 0.0026559 | 0.19654 | 2390 | 23204.171 | 40.8718 | #N/A | #N/A
8996 | FORT ORD 210637286 | 182402106 | FORT ORD 2106 | 2.5798 | 25 | 0.0026543 | 0.066357 | 2391 | 23206.7508 | 40.8054 | #N/A | #N/A
8063 | COARSEGOLD 210210207 | 254432102 | COARSEGOLD 2102 | 3.5622 | 38 | 0.0026426 | 0.10042 | 2392 | 23210.313 | 40.705 | #N/A | #N/A
4536 | TASSAJARA 2108437582 | 14662108 | TASSAJARA 2108 | 0.72879 | 31 | 0.0026389 | 0.081807 | 2393 | 23211.0418 | 40.6232 | #N/A | #N/A
1013 | CASTRO VALLEY 1108MR337 | 14091108 | CASTRO VALLEY 1108 | 9.0923 | 193 | 0.0026206 | 0.50578 | 2394 | 23220.1341 | 40.1174 | #N/A | #N/A
1167 | BIG BASIN 110195690 | 82841101 | BIG BASIN 1101 | 3.8701 | 58 | 0.0026164 | 0.15175 | 2395 | 23224.0042 | 39.9657 | #N/A | #N/A
7588 | IGNACIO 1104450582 | 42481104 | IGNACIO 1104 | 2.9881 | 50 | 0.0026097 | 0.13049 | 2396 | 23226.9923 | 39.8352 | #N/A | #N/A
976 | BRUNSWICK 1103CB | 152481103 | BRUNSWICK 1103 | 1.6787 | 82 | 0.0026094 | 0.21397 | 2397 | 23228.671 | 39.6212 | #N/A | #N/A
3119 | BIG BASIN 1101CB | 82841101 | BIG BASIN 1101 | 4.6531 | 45 | 0.0025849 | 0.11632 | 2398 | 23233.3241 | 39.5049 | #N/A | #N/A
8530 | MORRO BAY 1102CB | 183011102 | MORRO BAY 1102 | 4.5245 | 36 | 0.0025799 | 0.092875 | 2399 | 23237.8485 | 39.412 | #N/A | #N/A
1372 | TASSAJARA 2112CB | 14662112 | TASSAJARA 2112 | 0.17367 | 22 | 0.0025794 | 0.056746 | 2400 | 23238.0222 | 39.3553 | #N/A | #N/A
1496 | BRUNSWICK 1103173934 | 152481103 | BRUNSWICK 1103 | 10.9458 | 125 | 0.0025705 | 0.32131 | 2401 | 23248.968 | 39.034 | #N/A | #N/A
1818 | MORRO BAY 1101V66 | 183011101 | MORRO BAY 1101 | 3.6296 | 151 | 0.0025703 | 0.38811 | 2402 | 23252.5976 | 38.6459 | #N/A | #N/A
3089 | CAMBRIA 1101CB | 182771101 | CAMBRIA 1101 | 0.25849 | 45 | 0.0025606 | 0.11523 | 2403 | 23252.8561 | 38.5306 | #N/A | #N/A
3722 | BRUNSWICK 11032784 | 152481103 | BRUNSWICK 1103 | 14.6627 | 202 | 0.0025529 | 0.51568 | 2404 | 23267.5187 | 38.0149 | #N/A | #N/A
3654 | PENNGROVE 1101247511 | 43471101 | PENNGROVE 1101 | 1.2047 | 26 | 0.0025357 | 0.065929 | 2405 | 23268.7235 | 37.949 | #N/A | #N/A
2397 | MILPITAS 1109XR374 | 82831109 | MILPITAS 1109 | 0.47477 | 29 | 0.002531 | 0.073398 | 2406 | 23269.1982 | 37.8756 | #N/A | #N/A
1430 | ANTLER 11011520 | 103271101 | ANTLER 1101 | 8.972 | 69 | 0.002519 | 0.17381 | 2407 | 23278.1702 | 37.7018 | #N/A | #N/A
9020 | EAST QUINCY 1101424048 | 102551101 | EAST QUINCY 1101 | 0.66413 | 12 | 0.002517 | 0.030204 | 2408 | 23278.8344 | 37.6716 | #N/A | #N/A
5728 | HALF MOON BAY 1101CB | 24101101 | HALF MOON BAY 1101 | 1.5982 | 80 | 0.0025158 | 0.20127 | 2409 | 23280.4326 | 37.4703 | #N/A | #N/A
2399 | MONTE RIO 1113477 | 42811113 | MONTE RIO 1113 | 1.8313 | 25 | 0.002515 | 0.062875 | 2410 | 23282.2639 | 37.4075 | #N/A | #N/A
5291 | MIWUK 1702823548 | 163661702 | MIWUK 1702 | 19.7318 | 231 | 0.0025098 | 0.57976 | 2411 | 23301.9958 | 36.8277 | 36.8277 | #N/A
2843 | PLACERVILLE 111219742 | 153081112 | PLACERVILLE 1112 | 6.5567 | 92 | 0.0025093 | 0.23086 | 2412 | 23308.5525 | 36.5968 | #N/A | #N/A
7112 | BELLEVUE 2103646 | 43182103 | BELLEVUE 2103 | 8.4179 | 154 | 0.0025033 | 0.3855 | 2413 | 23316.9703 | 36.2113 | #N/A | #N/A
637 | DUNBAR 1101160 | 43071101 | DUNBAR 1101 | 2.7777 | 77 | 0.0024952 | 0.19213 | 2414 | 23319.748 | 36.0192 | #N/A | #N/A
551 | MC KEE 1103XR028 | 83531103 | MC KEE 1103 | 0.76232 | 134 | 0.0024946 | 0.33428 | 2415 | 23320.5103 | 35.6849 | #N/A | #N/A
4532 | RESERVATION ROAD 1102CB | 182731102 | RESERVATION ROAD 1102 | 7.8257 | 180 | 0.0024688 | 0.44438 | 2416 | 23328.336 | 35.2405 | #N/A | #N/A
2736 | ROSSMOOR 110845268 | 14161108 | ROSSMOOR 1108 | 2.735 | 112 | 0.0024458 | 0.27393 | 2417 | 23331.071 | 34.9666 | #N/A | #N/A
4245 | SONOMA 1104914376 | 42721104 | SONOMA 1104 | 0.53577 | 93 | 0.0024267 | 0.22569 | 2418 | 23331.6068 | 34.7409 | #N/A | #N/A
9993 | STELLING 1109478699 | 83481109 | STELLING 1109 | 0.8256 | 14 | 0.0024262 | 0.033967 | 2419 | 23332.4324 | 34.707 | #N/A | #N/A
1421 | ORO FINO 11012022 | 103031101 | ORO FINO 1101 | 16.0901 | 207 | 0.0024209 | 0.50113 | 2420 | 23348.5225 | 34.2058 | #N/A | #N/A
4226 | RIO DELL 1102772210 | 192251102 | RIO DELL 1102 | 0.82646 | 32 | 0.0023979 | 0.076733 | 2421 | 23349.3489 | 34.1291 | #N/A | #N/A
3489 | WEIMAR 1101CB | 152491101 | WEIMAR 1101 | 9.2589 | 116 | 0.0023893 | 0.27716 | 2422 | 23358.6078 | 33.8519 | #N/A | #N/A
9667 | NORTH TOWER 2101CB | 42042101 | NORTH TOWER 2101 | 1.3545 | 22 | 0.0023847 | 0.052462 | 2423 | 23359.9623 | 33.7995 | #N/A | #N/A
8228 | GONZALES 1104415382 | 182131104 | GONZALES 1104 | 0.060313 | 8 | 0.0023723 | 0.018978 | 2424 | 23360.0226 | 33.7805 | #N/A | #N/A
4259 | DIAMOND SPRINGS 110676088 | 152261106 | DIAMOND SPRINGS 1106 | 11.0106 | 124 | 0.0023715 | 0.29407 | 2425 | 23371.0332 | 33.4864 | #N/A | #N/A
9364 | MIWUK 170236888 | 163661702 | MIWUK 1702 | 0.60778 | 7 | 0.0023702 | 0.016592 | 2426 | 23371.641 | 33.4698 | #N/A | #N/A
5480 | PUEBLO 2102647842 | 43292102 | PUEBLO 2102 | 0.11668 | 6 | 0.0023697 | 0.014218 | 2427 | 23371.7576 | 33.4556 | #N/A | #N/A
1607 | MONTE RIO 11133970 | 42811113 | MONTE RIO 1113 | 7.3031 | 87 | 0.0023638 | 0.20565 | 2428 | 23379.0608 | 33.25 | #N/A | #N/A
4343 | BOLINAS 11011236 | 42261101 | BOLINAS 1101 | 3.6104 | 34 | 0.0023633 | 0.080354 | 2429 | 23382.6712 | 33.1696 | #N/A | #N/A
4341 | PLACERVILLE 210623190 | 153082106 | PLACERVILLE 2106 | 3.6786 | 45 | 0.0023536 | 0.10591 | 2430 | 23386.3497 | 33.0637 | #N/A | #N/A
6831 | INDIAN FLAT 110410270 | 252691104 | INDIAN FLAT 1104 | 3.8035 | 39 | 0.002349 | 0.091612 | 2431 | 23390.1533 | 32.9721 | #N/A | #N/A
10358 | KONOCTI 11024421 | 43311102 | KONOCTI 1102 | 0.3638 | 5 | 0.0023217 | 0.011609 | 2432 | 23390.5171 | 32.9605 | #N/A | #N/A
822 | PERRY 1101V74 | 183071101 | PERRY 1101 | 4.2891 | 61 | 0.0023119 | 0.14103 | 2433 | 23394.8061 | 32.8195 | #N/A | #N/A
1876 | HATTON 1102CB | 182291102 | HATTON 1102 | 1.9684 | 66 | 0.0022934 | 0.15136 | 2434 | 23396.7745 | 32.6681 | #N/A | #N/A
5363 | BIG BASIN 110110720 | 82841101 | BIG BASIN 1101 | 4.71 | 44 | 0.002283 | 0.10045 | 2435 | 23401.4845 | 32.5676 | #N/A | #N/A
3635 | PERRY 1101V88 | 183071101 | PERRY 1101 | 1.0768 | 48 | 0.002278 | 0.10934 | 2436 | 23402.5613 | 32.4583 | #N/A | #N/A
4348 | SANTA ROSA A 110432180 | 42151104 | SANTA ROSA A 1104 | 2.4675 | 36 | 0.0022763 | 0.081948 | 2437 | 23405.0288 | 32.3763 | #N/A | #N/A
9525 | BIG BASIN 11028403 | 82841102 | BIG BASIN 1102 | 4.8898 | 42 | 0.0022738 | 0.095499 | 2438 | 23409.9186 | 32.2808 | #N/A | #N/A
7227 | SAN RAFAEL 11071415 | 42011107 | SAN RAFAEL 1107 | 0.79554 | 14 | 0.0022706 | 0.031789 | 2439 | 23410.7141 | 32.2491 | #N/A | #N/A
649 | ORO FINO 11022090 | 103031102 | ORO FINO 1102 | 14.7459 | 183 | 0.0022675 | 0.41496 | 2440 | 23425.4601 | 31.8341 | #N/A | #N/A
2752 | FULTON 1107CB | 42561107 | FULTON 1107 | 0.54401 | 166 | 0.0022645 | 0.37591 | 2441 | 23426.0041 | 31.4582 | #N/A | #N/A
8081 | CAMP EVERS 210612840 | 83622106 | CAMP EVERS 2106 | 3.9298 | 50 | 0.002258 | 0.1129 | 2442 | 23429.9339 | 31.3453 | #N/A | #N/A
365 | PURISIMA 110149394 | 182971101 | PURISIMA 1101 | 1.1416 | 111 | 0.0022509 | 0.24985 | 2443 | 23431.0755 | 31.0954 | #N/A | #N/A
707 | DEL MONTE 21042760 | 182222104 | DEL MONTE 2104 | 2.7091 | 28 | 0.0022393 | 0.062701 | 2444 | 23433.7846 | 31.0327 | #N/A | #N/A
7540 | LUCERNE 11062327 | 43351106 | LUCERNE 1106 | 1.1901 | 20 | 0.0022381 | 0.044762 | 2445 | 23434.9747 | 30.988 | #N/A | #N/A
9432 | GUALALA 1111445166 | 42841111 | GUALALA 1111 | 7.5601 | 71 | 0.0022354 | 0.15871 | 2446 | 23442.5349 | 30.8293 | #N/A | #N/A
2414 | PINE GROVE 110245292 | 163751102 | PINE GROVE 1102 | 10.7835 | 132 | 0.002235 | 0.29501 | 2447 | 23453.3183 | 30.5342 | #N/A | #N/A
7039 | IGNACIO 1101CB | 42481101 | IGNACIO 1101 | 1.6722 | 19 | 0.0022279 | 0.042331 | 2448 | 23454.9905 | 30.4919 | #N/A | #N/A
6713 | LAURELES 1112438 | 182371112 | LAURELES 1112 | 5.1127 | 48 | 0.0022241 | 0.10675 | 2449 | 23460.1033 | 30.3852 | #N/A | #N/A
1808 | HARTLEY 1101738 | 43211101 | HARTLEY 1101 | 2.6156 | 106 | 0.0022159 | 0.23488 | 2450 | 23462.7189 | 30.1503 | #N/A | #N/A
9055 | ORO FINO 1102CB | 103031102 | ORO FINO 1102 | 2.0983 | 27 | 0.0021922 | 0.059189 | 2451 | 23464.8172 | 30.0911 | #N/A | #N/A
500 | ALTO 112278672 | 42031122 | ALTO 1122 | 3.778 | 123 | 0.0021883 | 0.26916 | 2452 | 23468.5952 | 29.8219 | #N/A | #N/A
9919 | MONTE RIO 1113678 | 42811113 | MONTE RIO 1113 | 1.867 | 17 | 0.002188 | 0.037196 | 2453 | 23470.4622 | 29.7847 | #N/A | #N/A
8710 | SUMMIT 110186658 | 152591101 | SUMMIT 1101 | 0.63954 | 7 | 0.0021861 | 0.015303 | 2454 | 23471.1017 | 29.7694 | #N/A | #N/A
3183 | PINE GROVE 11011021 | 163751101 | PINE GROVE 1101 | 4.1659 | 56 | 0.0021716 | 0.12161 | 2455 | 23475.2676 | 29.6478 | #N/A | #N/A
3039 | BIG BASIN 110110296 | 82841101 | BIG BASIN 1101 | 14.4211 | 181 | 0.0021702 | 0.3928 | 2456 | 23489.6887 | 29.255 | 29.255 | #N/A
10621 | EEL RIVER 1103987714 | 192381103 | EEL RIVER 1103 | 0.75759 | 6 | 0.0021699 | 0.01302 | 2457 | 23490.4463 | 29.242 | #N/A | #N/A
2552 | HALSEY 11022514 | 152241102 | HALSEY 1102 | 10.9686 | 212 | 0.0021687 | 0.45975 | 2458 | 23501.4149 | 28.7823 | #N/A | #N/A
1900 | PLACERVILLE 1111508410 | 153081111 | PLACERVILLE 1111 | 4.6805 | 73 | 0.002162 | 0.15783 | 2459 | 23506.0954 | 28.6244 | #N/A | #N/A
7805 | POINT MORETTI 11015074 | 82931101 | POINT MORETTI 1101 | 1.3653 | 34 | 0.0021548 | 0.073264 | 2460 | 23507.4607 | 28.5512 | #N/A | #N/A
9738 | ECHO SUMMIT 1101344250 | 158031101 | ECHO SUMMIT 1101 | 0.8075 | 10 | 0.0021484 | 0.021484 | 2461 | 23508.2682 | 28.5297 | #N/A | #N/A
3248 | HARRIS 1109355914 | 192431109 | HARRIS 1109 | 8.0813 | 104 | 0.0021471 | 0.2233 | 2462 | 23516.3495 | 28.3064 | #N/A | #N/A
5158 | MORRO BAY 1101W20 | 183011101 | MORRO BAY 1101 | 2.2074 | 48 | 0.0021357 | 0.10251 | 2463 | 23518.5569 | 28.2039 | #N/A | #N/A
5206 | CAMP EVERS 21065020 | 83622106 | CAMP EVERS 2106 | 15.0734 | 185 | 0.0021265 | 0.3934 | 2464 | 23533.6303 | 27.8105 | 27.8105 | #N/A
8641 | PETALUMA C 1109857148 | 42631109 | PETALUMA C 1109 | 0.93456 | 31 | 0.0021126 | 0.065491 | 2465 | 23534.5649 | 27.745 | #N/A | #N/A
4750 | PENNGROVE 1101554 | 43471101 | PENNGROVE 1101 | 0 | 130 | 0.0021107 | 0.2744 | 2466 | 23534.5649 | 27.4706 | #N/A | #N/A
5805 | PARADISE 110439216 | 102831104 | PARADISE 1104 | 1.6313 | 41 | 0.0021 | 0.086098 | 2467 | 23536.1962 | 27.3845 | #N/A | #N/A
3222 | WEST POINT 11014706 | 163201101 | WEST POINT 1101 | 11.4541 | 138 | 0.0020959 | 0.28923 | 2468 | 23547.6503 | 27.0953 | #N/A | #N/A
2065 | EL DORADO PH 21026645 | 152762102 | EL DORADO PH 2102 | 4.2184 | 52 | 0.0020868 | 0.10851 | 2469 | 23551.8687 | 26.9867 | #N/A | #N/A
6903 | VINEYARD 2107MR332 | 14502107 | VINEYARD 2107 | 0.32359 | 31 | 0.0020705 | 0.064186 | 2470 | 23552.1923 | 26.9226 | #N/A | #N/A
3802 | MORRO BAY 1102868170 | 183011102 | MORRO BAY 1102 | 9.071 | 59 | 0.0020479 | 0.12083 | 2471 | 23561.2632 | 26.8017 | #N/A | #N/A
3290 | TAR FLAT 04023144 | 163240402 | TAR FLAT 0402 | 4.8657 | 58 | 0.0020462 | 0.11868 | 2472 | 23566.1289 | 26.683 | #N/A | #N/A
9541 | RINCON 1101839669 | 43321101 | RINCON 1101 | 0.6148 | 12 | 0.0020383 | 0.02446 | 2473 | 23566.7437 | 26.6586 | #N/A | #N/A
671 | CAMP EVERS 21045096 | 83622104 | CAMP EVERS 2104 | 20.3112 | 232 | 0.0020379 | 0.4728 | 2474 | 23587.0549 | 26.1858 | #N/A | #N/A
6416 | PLACER 1102CB | 152461102 | PLACER 1102 | 2.0893 | 23 | 0.0020369 | 0.046849 | 2475 | 23589.1443 | 26.1389 | #N/A | #N/A
9674 | GUALALA 1112CB | 42841112 | GUALALA 1112 | 1.5966 | 22 | 0.0020177 | 0.044389 | 2476 | 23590.7409 | 26.0946 | #N/A | #N/A
1510 | MONTE RIO 1113CB | 42811113 | MONTE RIO 1113 | 4.5284 | 49 | 0.0020136 | 0.098667 | 2477 | 23595.2693 | 25.9959 | #N/A | #N/A
1572 | ECHO SUMMIT 11012500 | 158031101 | ECHO SUMMIT 1101 | 2.1886 | 26 | 0.0019811 | 0.05151 | 2478 | 23597.4579 | 25.9444 | #N/A | #N/A
808 | PEORIA 1701169700 | 163781701 | PEORIA 1701 | 8.3415 | 63 | 0.001973 | 0.1243 | 2479 | 23605.7994 | 25.8201 | #N/A | #N/A
1792 | MORAGA 1102CB | 13801102 | MORAGA 1102 | 5.3075 | 130 | 0.0019722 | 0.25639 | 2480 | 23611.1069 | 25.5637 | #N/A | #N/A
6608 | FORT ROSS 1121134 | 42851121 | FORT ROSS 1121 | 8.2489 | 99 | 0.0019671 | 0.19475 | 2481 | 23619.3559 | 25.3689 | #N/A | #N/A
5795 | HIGGINS 1103995672 | 152691103 | HIGGINS 1103 | 3.6847 | 79 | 0.0019604 | 0.15487 | 2482 | 23623.0405 | 25.2141 | #N/A | #N/A
7320 | FAIRVIEW 220799096 | 13432207 | FAIRVIEW 2207 | 9.8793 | 56 | 0.0019603 | 0.10978 | 2483 | 23632.9199 | 25.1043 | #N/A | #N/A
1460 | PARADISE 1105121988 | 102831105 | PARADISE 1105 | 6.9728 | 92 | 0.0019488 | 0.17929 | 2484 | 23639.8926 | 24.925 | #N/A | #N/A
223 | ROB ROY 210410960 | 83692104 | ROB ROY 2104 | 18.7275 | 320 | 0.0019454 | 0.62252 | 2485 | 23658.6201 | 24.3025 | #N/A | #N/A
9882 | VOLTA 1102453266 | 102541102 | VOLTA 1102 | 0.31706 | 5 | 0.0019312 | 0.0096562 | 2486 | 23658.9372 | 24.2928 | #N/A | #N/A
2825 | COTATI 1104CB | 42271104 | COTATI 1104 | 4.5242 | 93 | 0.0019107 | 0.17769 | 2487 | 23663.4613 | 24.1151 | #N/A | #N/A
9868 | VOLTA 110293418 | 102541102 | VOLTA 1102 | 2.5767 | 23 | 0.0019038 | 0.043787 | 2488 | 23666.0381 | 24.0713 | #N/A | #N/A
7915 | LOS GATOS 1106697500 | 82021106 | LOS GATOS 1106 | 6.735 | 74 | 0.0019029 | 0.14082 | 2489 | 23672.7731 | 23.9305 | #N/A | #N/A
9296 | DUNBAR 1103835658 | 43071103 | DUNBAR 1103 | 0.0311 | 11 | 0.0018987 | 0.020885 | 2490 | 23672.8042 | 23.9096 | #N/A | #N/A
6742 | ALTO 11251158 | 42031125 | ALTO 1125 | 2.2302 | 65 | 0.0018981 | 0.12337 | 2491 | 23675.0344 | 23.7863 | #N/A | #N/A
4000 | RINCON 1101576 | 43321101 | RINCON 1101 | 0.98357 | 116 | 0.0018636 | 0.21618 | 2492 | 23676.0179 | 23.5701 | #N/A | #N/A
4995 | SOLEDAD 21027008 | 182052102 | SOLEDAD 2102 | 5.0272 | 122 | 0.0018473 | 0.22537 | 2493 | 23681.0451 | 23.3447 | #N/A | #N/A
6887 | HATTON 1102648928 | 182291102 | HATTON 1102 | 3.9523 | 44 | 0.0018437 | 0.081123 | 2494 | 23684.9974 | 23.2636 | #N/A | #N/A
9513 | GREEN VALLEY 2101535998 | 83192101 | GREEN VALLEY 2101 | 4.4378 | 43 | 0.0018414 | 0.079178 | 2495 | 23689.4352 | 23.1844 | #N/A | #N/A
2632 | APPLE HILL 110412947 | 153661104 | APPLE HILL 1104 | 3.5483 | 49 | 0.0018388 | 0.0901 | 2496 | 23692.9835 | 23.0943 | #N/A | #N/A
7783 | MIRABEL 110257840 | 42091102 | MIRABEL 1102 | 2.6345 | 29 | 0.0018331 | 0.053161 | 2497 | 23695.6181 | 23.0411 | #N/A | #N/A
26 | TASSAJARA 2103CB | 14662103 | TASSAJARA 2103 | 0.48966 | 259 | 0.0018283 | 0.47354 | 2498 | 23696.1077 | 22.5676 | #N/A | #N/A
8978 | BIG RIVER 1101954 | 43081101 | BIG RIVER 1101 | 7.6897 | 78 | 0.0018244 | 0.1423 | 2499 | 23703.7974 | 22.4253 | #N/A | #N/A
85 | HALSEY 11011704 | 152241101 | HALSEY 1101 | 13.1957 | 160 | 0.001823 | 0.29168 | 2500 | 23716.9931 | 22.1336 | #N/A | #N/A
2388 | CAMP EVERS 21059031 | 83622105 | CAMP EVERS 2105 | 1.0823 | 17 | 0.0018195 | 0.030932 | 2501 | 23718.0754 | 22.1027 | #N/A | #N/A
2038 | MORAGA 1104CB | 13801104 | MORAGA 1104 | 9.7831 | 214 | 0.0018118 | 0.38772 | 2502 | 23727.8585 | 21.715 | #N/A | #N/A
6140 | OCEANO 1106V28 | 182601106 | OCEANO 1106 | 1.2171 | 99 | 0.0018053 | 0.17873 | 2503 | 23729.0756 | 21.5362 | #N/A | #N/A
9346 | LAURELES 11116421 | 182371111 | LAURELES 1111 | 1.7261 | 20 | 0.0018044 | 0.036089 | 2504 | 23730.8017 | 21.5002 | #N/A | #N/A
680 | CAMP EVERS 210612760 | 83622106 | CAMP EVERS 2106 | 26.3906 | 299 | 0.0017903 | 0.53531 | 2505 | 23757.1923 | 20.9648 | #N/A | #N/A
1725 | BOLINAS 1101CB | 42261101 | BOLINAS 1101 | 2.1394 | 26 | 0.0017811 | 0.04631 | 2506 | 23759.3317 | 20.9185 | #N/A | #N/A
1486 | BEN LOMOND 1101BL 1101 | 83041101 | BEN LOMOND 1101 | 8.4328 | 101 | 0.0017681 | 0.17858 | 2507 | 23767.7645 | 20.74 | #N/A | #N/A
8439 | OAKHURST 110310190 | 254421103 | OAKHURST 1103 | 8.4469 | 61 | 0.0017583 | 0.10725 | 2508 | 23776.2114 | 20.6327 | #N/A | #N/A
10411 | BURNEY 1102272636 | 103311102 | BURNEY 1102 | 0.2681 | 5 | 0.0017542 | 0.0087708 | 2509 | 23776.4795 | 20.6239 | #N/A | #N/A
9794 | SONOMA 1106510055 | 42721106 | SONOMA 1106 | 0.50815 | 11 | 0.0017489 | 0.019238 | 2510 | 23776.9877 | 20.6047 | #N/A | #N/A
1870 | TEMPLETON 2110307832 | 183052110 | TEMPLETON 2110 | 1.6247 | 133 | 0.0017438 | 0.23192 | 2511 | 23778.6123 | 20.3728 | #N/A | #N/A
4149 | EL DORADO PH 210219542 | 152762102 | EL DORADO PH 2102 | 9.5212 | 111 | 0.0017374 | 0.19285 | 2512 | 23788.1335 | 20.1799 | #N/A | #N/A
5394 | BRUNSWICK 11052100 | 152481105 | BRUNSWICK 1105 | 3.9724 | 47 | 0.0017366 | 0.081621 | 2513 | 23792.106 | 20.0983 | #N/A | #N/A
7138 | MONTE RIO 11138299 | 42811113 | MONTE RIO 1113 | 1.2021 | 13 | 0.0017192 | 0.02235 | 2514 | 23793.3081 | 20.076 | #N/A | #N/A
2315 | MORAGA 1101108540 | 13801101 | MORAGA 1101 | 4.8175 | 44 | 0.001717 | 0.075547 | 2515 | 23798.1256 | 20.0004 | #N/A | #N/A
110 | RACETRACK 17038120 | 163761703 | RACETRACK 1703 | 8.932 | 108 | 0.0017068 | 0.18434 | 2516 | 23807.0576 | 19.8161 | #N/A | #N/A
1996 | MORAGA 1103E510R | 13801103 | MORAGA 1103 | 0.50207 | 84 | 0.0017029 | 0.14305 | 2517 | 23807.5597 | 19.673 | #N/A | #N/A
2784 | FRENCH GULCH 11022902 | 103381102 | FRENCH GULCH 1102 | 6.9875 | 8 | 0.0016954 | 0.013563 | 2518 | 23814.5472 | 19.6595 | #N/A | #N/A
4648 | HALF MOON BAY 1102863822 | 24101102 | HALF MOON BAY 1102 | 0.10488 | 8 | 0.0016933 | 0.013546 | 2519 | 23814.6521 | 19.6459 | #N/A | #N/A
4537 | LAKEWOOD 2107396264 | 13532107 | LAKEWOOD 2107 | 4.7882 | 95 | 0.0016927 | 0.16081 | 2520 | 23819.4403 | 19.4851 | #N/A | #N/A
6727 | BRUNSWICK 11032200 | 152481103 | BRUNSWICK 1103 | 5.5723 | 64 | 0.0016888 | 0.10808 | 2521 | 23825.0126 | 19.377 | #N/A | #N/A
5446 | PENRYN 11052406 | 152561105 | PENRYN 1105 | 0.076795 | 50 | 0.0016854 | 0.084272 | 2522 | 23825.0894 | 19.2928 | #N/A | #N/A
9065 | OTTER 11017611 | 182941101 | OTTER 1101 | 4.3928 | 42 | 0.0016834 | 0.070701 | 2523 | 23829.4822 | 19.2221 | #N/A | #N/A
4321 | BRUNSWICK 110633050 | 152481106 | BRUNSWICK 1106 | 1.1145 | 56 | 0.0016799 | 0.094072 | 2524 | 23830.5967 | 19.128 | #N/A | #N/A
7573 | ROSSMOOR 110639424 | 14161106 | ROSSMOOR 1106 | 0.92086 | 36 | 0.0016754 | 0.060313 | 2525 | 23831.5175 | 19.0677 | #N/A | #N/A
1005 | ROB ROY 21045082 | 83692104 | ROB ROY 2104 | 19.896 | 215 | 0.0016672 | 0.35844 | 2526 | 23851.4135 | 18.7092 | #N/A | #N/A
5885 | LAURELES 11122768 | 182371112 | LAURELES 1112 | 6.2832 | 92 | 0.0016647 | 0.15315 | 2527 | 23857.6968 | 18.5561 | #N/A | #N/A
2281 | VOLTA 110185234 | 102541101 | VOLTA 1101 | 7.9123 | 92 | 0.0016524 | 0.15202 | 2528 | 23865.609 | 18.404 | #N/A | #N/A
3545 | PACIFICA 1104230272 | 22811104 | PACIFICA 1104 | 0.85605 | 18 | 0.0016485 | 0.029673 | 2529 | 23866.4651 | 18.3744 | #N/A | #N/A
6564 | NEWBURG 1131557468 | 192151131 | NEWBURG 1131 | 0.88482 | 28 | 0.0016475 | 0.046129 | 2530 | 23867.3499 | 18.3282 | #N/A | #N/A
2123 | IGNACIO 11011300 | 42481101 | IGNACIO 1101 | 3.1977 | 84 | 0.0016445 | 0.13814 | 2531 | 23870.5476 | 18.1901 | #N/A | #N/A
7516 | SAN LUIS OBISPO 1107CB | 182631107 | SAN LUIS OBISPO 1107 | 0.77757 | 19 | 0.0016436 | 0.031229 | 2532 | 23871.3252 | 18.1589 | #N/A | #N/A
1994 | SILVERADO 2103218894 | 43432103 | SILVERADO 2103 | 0.33574 | 14 | 0.00163 | 0.022819 | 2533 | 23871.6609 | 18.1361 | #N/A | #N/A
10204 | DUNBAR 110113481 | 43071101 | DUNBAR 1101 | 0 | 14 | 0.0016289 | 0.022805 | 2534 | 23871.6609 | 18.1133 | #N/A | #N/A
3837 | AUBERRY 1101D4982 | 254151101 | AUBERRY 1101 | 2.6805 | 21 | 0.0016248 | 0.034121 | 2535 | 23874.3414 | 18.0791 | #N/A | #N/A
586 | WEIMAR 11022038 | 152491102 | WEIMAR 1102 | 13.3691 | 155 | 0.0016155 | 0.2504 | 2536 | 23887.7105 | 17.8287 | #N/A | #N/A
5218 | SYCAMORE CREEK 11112268 | 102971111 | SYCAMORE CREEK 1111 | 21.8256 | 217 | 0.0016039 | 0.34805 | 2537 | 23909.5361 | 17.4807 | #N/A | #N/A
1040 | GANSNER 110152664 | 103021101 | GANSNER 1101 | 0.17676 | 44 | 0.0016028 | 0.070524 | 2538 | 23909.7128 | 17.4102 | #N/A | #N/A
3804 | POINT MORETTI 110110726 | 82931101 | POINT MORETTI 1101 | 10.5262 | 124 | 0.0016007 | 0.19849 | 2539 | 23920.2391 | 17.2117 | #N/A | #N/A
1389 | STANISLAUS 17011331 | 162821701 | STANISLAUS 1701 | 4.3908 | 63 | 0.0015977 | 0.10065 | 2540 | 23924.6299 | 17.111 | #N/A | #N/A
8302 | VALLEY VIEW 1106P166 | 14341106 | VALLEY VIEW 1106 | 4.3931 | 27 | 0.0015975 | 0.043133 | 2541 | 23929.023 | 17.0679 | #N/A | #N/A
7677 | POINT MORETTI 110136516 | 82931101 | POINT MORETTI 1101 | 4.1639 | 53 | 0.0015908 | 0.08431 | 2542 | 23933.1869 | 16.9836 | #N/A | #N/A
9231 | ROB ROY 21045304 | 83692104 | ROB ROY 2104 | 3.5819 | 60 | 0.0015784 | 0.094707 | 2543 | 23936.7688 | 16.8889 | #N/A | #N/A
10838 | LAS GALLINAS A 1106685852 | 42991106 | LAS GALLINAS A 1106 | 0.065216 | 3 | 0.0015648 | 0.0046945 | 2544 | 23936.834 | 16.8842 | #N/A | #N/A
1125 | LAS GALLINAS A 1106CB | 42991106 | LAS GALLINAS A 1106 | 0.095554 | 111 | 0.0015644 | 0.17365 | 2545 | 23936.9295 | 16.7105 | #N/A | #N/A
6613 | HICKS 111660050 | 83431116 | HICKS 1116 | 8.1518 | 98 | 0.0015546 | 0.15235 | 2546 | 23945.0813 | 16.5582 | #N/A | #N/A
10410 | PUEBLO 2102391312 | 43292102 | PUEBLO 2102 | 0.14272 | 13 | 0.0015528 | 0.020186 | 2547 | 23945.2241 | 16.538 | #N/A | #N/A
3988 | SAN RAFAEL 1108322 | 42011108 | SAN RAFAEL 1108 | 7.1787 | 88 | 0.0015474 | 0.13618 | 2548 | 23952.4028 | 16.4018 | #N/A | #N/A
3811 | OAKLAND X 1106950688 | 12541106 | OAKLAND X 1106 | 3.6566 | 50 | 0.0015407 | 0.077034 | 2549 | 23956.0594 | 16.3248 | #N/A | #N/A
1254 | CURTIS 17039240 | 163351703 | CURTIS 1703 | 10.9736 | 151 | 0.0015394 | 0.23246 | 2550 | 23967.033 | 16.0923 | #N/A | #N/A
9703 | VOLTA 110280982 | 102541102 | VOLTA 1102 | 0.5199 | 8 | 0.0015382 | 0.012305 | 2551 | 23967.5529 | 16.08 | #N/A | #N/A
8204 | BEN LOMOND 04015144 | 83040401 | BEN LOMOND 0401 | 3.9583 | 36 | 0.0015295 | 0.055061 | 2552 | 23971.5112 | 16.025 | #N/A | #N/A
4922 | BIG RIVER 11013019 | 43081101 | BIG RIVER 1101 | 0.26534 | 11 | 0.0015165 | 0.016682 | 2553 | 23971.7766 | 16.0083 | #N/A | #N/A
4844 | SANTA ROSA A 1104173590 | 42151104 | SANTA ROSA A 1104 | 4.2891 | 46 | 0.0015131 | 0.069603 | 2554 | 23976.0657 | 15.9387 | #N/A | #N/A
7483 | FLINT 1101CB | 152531101 | FLINT 1101 | 0.64467 | 36 | 0.0015072 | 0.054259 | 2555 | 23976.7104 | 15.8844 | #N/A | #N/A
6669 | DUNBAR 1101234 | 43071101 | DUNBAR 1101 | 3.4708 | 81 | 0.0015051 | 0.12191 | 2556 | 23980.1812 | 15.7625 | #N/A | #N/A
7886 | OAKHURST 1102CB | 254421102 | OAKHURST 1102 | 2.6438 | 61 | 0.0014997 | 0.091479 | 2557 | 23982.825 | 15.671 | #N/A | #N/A
1710 | ELK 110191336 | 42981101 | ELK 1101 | 7.9184 | 78 | 0.0014969 | 0.11676 | 2558 | 23990.7434 | 15.5543 | #N/A | #N/A
583 | MONTE RIO 1111969182 | 42811111 | MONTE RIO 1111 | 5.3314 | 64 | 0.0014937 | 0.095599 | 2559 | 23996.0748 | 15.4587 | #N/A | #N/A
3182 | KONOCTI 1108950 | 43311108 | KONOCTI 1108 | 6.2017 | 85 | 0.0014937 | 0.12697 | 2560 | 24002.2765 | 15.3317 | #N/A | #N/A
5332 | CLAYTON 2212CB | 12022212 | CLAYTON 2212 | 1.1805 | 140 | 0.0014894 | 0.20851 | 2561 | 24003.4571 | 15.1232 | #N/A | #N/A
4270 | LAS GALLINAS A 1104304 | 42991104 | LAS GALLINAS A 1104 | 0.13738 | 27 | 0.0014798 | 0.039953 | 2562 | 24003.5945 | 15.0832 | #N/A | #N/A
886 | SALT SPRINGS 21024796 | 163692102 | SALT SPRINGS 2102 | 7.1917 | 114 | 0.0014707 | 0.16766 | 2563 | 24010.7862 | 14.9156 | #N/A | #N/A
1846 | BIG RIVER 11013002 | 43081101 | BIG RIVER 1101 | 7.2444 | 76 | 0.001464 | 0.11126 | 2564 | 24018.0306 | 14.8043 | #N/A | #N/A
6005 | MIRABEL 1101201156 | 42091101 | MIRABEL 1101 | 1.4513 | 26 | 0.0014632 | 0.038044 | 2565 | 24019.4819 | 14.7663 | #N/A | #N/A
9286 | SOLEDAD 2101315500 | 182052101 | SOLEDAD 2101 | 1.1082 | 22 | 0.0014578 | 0.032073 | 2566 | 24020.59 | 14.7342 | #N/A | #N/A
2001 | SAN RAFAEL 110839156 | 42011108 | SAN RAFAEL 1108 | 3.4686 | 62 | 0.0014467 | 0.089693 | 2567 | 24024.0586 | 14.6445 | #N/A | #N/A
2593 | HIGGINS 1104533648 | 152691104 | HIGGINS 1104 | 6.7544 | 93 | 0.0014323 | 0.13321 | 2568 | 24030.813 | 14.5113 | #N/A | #N/A
2853 | EL DORADO PH 2101668674 | 152762101 | EL DORADO PH 2101 | 9.5082 | 112 | 0.0014289 | 0.16003 | 2569 | 24040.3212 | 14.3513 | #N/A | #N/A
701 | CAMP EVERS 210512590 | 83622105 | CAMP EVERS 2105 | 5.1174 | 69 | 0.0014267 | 0.09844 | 2570 | 24045.4386 | 14.2528 | #N/A | #N/A
9206 | SISQUOC 110245261 | 182811102 | SISQUOC 1102 | 0.10255 | 10 | 0.001423 | 0.01423 | 2571 | 24045.5411 | 14.2386 | #N/A | #N/A
6505 | MONTE RIO 11131313 | 42811113 | MONTE RIO 1113 | 1.2408 | 19 | 0.0014057 | 0.026709 | 2572 | 24046.7819 | 14.2119 | #N/A | #N/A
4406 | COTATI 110475972 | 42271104 | COTATI 1104 | 3.3475 | 61 | 0.0013938 | 0.085021 | 2573 | 24050.1294 | 14.1269 | #N/A | #N/A
7967 | MENLO 11038982 | 24131103 | MENLO 1103 | 4.6205 | 50 | 0.0013928 | 0.06964 | 2574 | 24054.7499 | 14.0572 | #N/A | #N/A
9897 | ORO FINO 110239154 | 103031102 | ORO FINO 1102 | 0.88247 | 11 | 0.0013923 | 0.015315 | 2575 | 24055.6324 | 14.0419 | #N/A | #N/A
5536 | GUALALA 1111CB | 42841111 | GUALALA 1111 | 3.8705 | 47 | 0.0013913 | 0.065391 | 2576 | 24059.5029 | 13.9765 | #N/A | #N/A
3869 | PINE GROVE 11021765 | 163751102 | PINE GROVE 1102 | 1.4523 | 20 | 0.0013887 | 0.027774 | 2577 | 24060.9553 | 13.9487 | #N/A | #N/A
2705 | FORT ORD 210736596 | 182402107 | FORT ORD 2107 | 4.0848 | 145 | 0.0013847 | 0.20079 | 2578 | 24065.04 | 13.7479 | #N/A | #N/A
5302 | BIG BASIN 11015000 | 82841101 | BIG BASIN 1101 | 1.9571 | 23 | 0.0013814 | 0.031772 | 2579 | 24066.9972 | 13.7162 | #N/A | #N/A
10692 | ROSSMOOR 1109CB | 14161109 | ROSSMOOR 1109 | 0.0047054 | 6 | 0.001321 | 0.0079259 | 2580 | 24067.0019 | 13.7082 | #N/A | #N/A
5396 | FORT BRAGG A 11041316 | 42761104 | FORT BRAGG A 1104 | 13.7359 | 166 | 0.0013124 | 0.21786 | 2581 | 24080.7378 | 13.4904 | #N/A | #N/A
6380 | GUALALA 111135562 | 42841111 | GUALALA 1111 | 14.2412 | 147 | 0.0013006 | 0.19119 | 2582 | 24094.979 | 13.2992 | #N/A | #N/A
5878 | OLEMA 11011318 | 42291101 | OLEMA 1101 | 8.5105 | 113 | 0.0012974 | 0.14661 | 2583 | 24103.4895 | 13.1526 | #N/A | #N/A
7013 | SALT SPRINGS 2102L491 | 163692102 | SALT SPRINGS 2102 | 2.2154 | 31 | 0.0012903 | 0.039999 | 2584 | 24105.7048 | 13.1126 | #N/A | #N/A
3314 | LLAGAS 2101XR244 | 83182101 | LLAGAS 2101 | 0 | 157 | 0.0012825 | 0.20135 | 2585 | 24105.7048 | 12.9112 | #N/A | #N/A
595 | GARBERVILLE 1103CB | 192221103 | GARBERVILLE 1103 | 0.60372 | 31 | 0.0012726 | 0.039451 | 2586 | 24106.3086 | 12.8718 | #N/A | #N/A
842 | ELK 11011272 | 42981101 | ELK 1101 | 22.0935 | 236 | 0.0012681 | 0.29926 | 2587 | 24128.4021 | 12.5725 | #N/A | #N/A
3308 | SNEATH LANE 1106CB | 22721106 | SNEATH LANE 1106 | 3.0362 | 66 | 0.0012656 | 0.083532 | 2588 | 24131.4383 | 12.489 | #N/A | #N/A
4674 | WEST POINT 110112256 | 163201101 | WEST POINT 1101 | 6.4793 | 86 | 0.0012622 | 0.10855 | 2589 | 24137.9176 | 12.3804 | #N/A | #N/A
141 | MORRO BAY 1102W34 | 183011102 | MORRO BAY 1102 | 7.5967 | 112 | 0.0012584 | 0.14094 | 2590 | 24145.5142 | 12.2395 | #N/A | #N/A
8023 | HOLLISTER 2105903238 | 182492105 | HOLLISTER 2105 | 4.0092 | 30 | 0.001258 | 0.037741 | 2591 | 24149.5235 | 12.2018 | #N/A | #N/A
53 | DUNBAR 1102448 | 43071102 | DUNBAR 1102 | 2.4441 | 116 | 0.001256 | 0.1457 | 2592 | 24151.9676 | 12.0561 | #N/A | #N/A
5111 | ALHAMBRA 110581514 | 14101105 | ALHAMBRA 1105 | 2.9716 | 65 | 0.0012525 | 0.08141 | 2593 | 24154.9392 | 11.9746 | #N/A | #N/A
347 | BRUNSWICK 11052204 | 152481105 | BRUNSWICK 1105 | 7.2254 | 84 | 0.0012429 | 0.1044 | 2594 | 24162.1646 | 11.8702 | #N/A | #N/A
2860 | CAMP EVERS 210311046 | 83622103 | CAMP EVERS 2103 | 16.0762 | 194 | 0.0012326 | 0.23912 | 2595 | 24178.2407 | 11.6311 | #N/A | #N/A
5152 | WOODSIDE 11018522 | 24251101 | WOODSIDE 1101 | 1.9088 | 123 | 0.0012059 | 0.14833 | 2596 | 24180.1495 | 11.4828 | #N/A | #N/A
10217 | PAUL SWEET 2102959032 | 83252102 | PAUL SWEET 2102 | 0.79772 | 11 | 0.0012034 | 0.013238 | 2597 | 24180.9472 | 11.4696 | #N/A | #N/A
6918 | DUNBAR 1103872066 | 43071103 | DUNBAR 1103 | 0.53256 | 13 | 0.0011906 | 0.015478 | 2598 | 24181.4798 | 11.4541 | #N/A | #N/A
5057 | WEIMAR 11012764 | 152491101 | WEIMAR 1101 | 6.1351 | 68 | 0.0011906 | 0.080958 | 2599 | 24187.6149 | 11.3731 | #N/A | #N/A
8401 | IGNACIO 11051943 | 42481105 | IGNACIO 1105 | 1.2181 | 17 | 0.0011872 | 0.020183 | 2600 | 24188.833 | 11.3529 | #N/A | #N/A
2098 | VOLTA 1102641544 | 102541102 | VOLTA 1102 | 4.9448 | 58 | 0.0011816 | 0.068531 | 2601 | 24193.7779 | 11.2844 | #N/A | #N/A
5971 | SANTA ROSA A 110464565 | 42151104 | SANTA ROSA A 1104 | 0.79819 | 13 | 0.001175 | 0.015275 | 2602 | 24194.576 | 11.2691 | #N/A | #N/A
1887 | NAPA 1112CB | 42021112 | NAPA 1112 | 0.58483 | 226 | 0.0011724 | 0.26497 | 2603 | 24195.1609 | 11.0042 | #N/A | #N/A
5833 | DEL MONTE 21049500 | 182222104 | DEL MONTE 2104 | 5.698 | 71 | 0.0011663 | 0.082807 | 2604 | 24200.8589 | 10.9214 | #N/A | #N/A
3301 | RALSTON 1101836528 | 24141101 | RALSTON 1101 | 2.9084 | 39 | 0.0011552 | 0.045051 | 2605 | 24203.7673 | 10.8763 | #N/A | #N/A
1278 | LOS GATOS 1107CB | 82021107 | LOS GATOS 1107 | 15.2993 | 192 | 0.0011504 | 0.22088 | 2606 | 24219.0666 | 10.6554 | #N/A | #N/A
1215 | SAN RAMON 2106CB | 14232106 | SAN RAMON 2106 | 0.46931 | 25 | 0.001149 | 0.028724 | 2607 | 24219.5359 | 10.6267 | #N/A | #N/A
10840 | CLOVERDALE 1101704542 | 42821101 | CLOVERDALE 1101 | 0.215 | 3 | 0.0011475 | 0.0034424 | 2608 | 24219.7509 | 10.6233 | #N/A | #N/A
9582 | LOS OSITOS 2102624200 | 182082102 | LOS OSITOS 2102 | 1.5487 | 6 | 0.0011432 | 0.0068593 | 2609 | 24221.2996 | 10.6164 | #N/A | #N/A
6642 | STANISLAUS 1702L5381 | 162821702 | STANISLAUS 1702 | 1.2153 | 15 | 0.0011429 | 0.017144 | 2610 | 24222.515 | 10.5993 | #N/A | #N/A
10129 | VALLEY VIEW 1103218424 | 14341103 | VALLEY VIEW 1103 | 0.53854 | 4 | 0.0011372 | 0.0045488 | 2611 | 24223.0535 | 10.5947 | #N/A | #N/A
2575 | BIG RIVER 110155402 | 43081101 | BIG RIVER 1101 | 2.4826 | 104 | 0.0011234 | 0.11683 | 2612 | 24225.5361 | 10.4779 | #N/A | #N/A
2609 | MIRABEL 1102503000 | 42091102 | MIRABEL 1102 | 4.5824 | 54 | 0.0011185 | 0.060401 | 2613 | 24230.1185 | 10.4175 | #N/A | #N/A
8405 | MONTE RIO 1111240 | 42811111 | MONTE RIO 1111 | 3.0785 | 42 | 0.0011134 | 0.046762 | 2614 | 24233.1971 | 10.3707 | #N/A | #N/A
1947 | ROB ROY 210410930 | 83692104 | ROB ROY 2104 | 0.98524 | 149 | 0.0011126 | 0.16578 | 2615 | 24234.1823 | 10.2049 | #N/A | #N/A
6789 | MIRABEL 11021139 | 42091102 | MIRABEL 1102 | 2.0454 | 25 | 0.0011071 | 0.027677 | 2616 | 24236.2277 | 10.1773 | #N/A | #N/A
10452 | PIT NO 3 21011480 | 103732101 | PIT NO 3 2101 | 2.1529 | 20 | 0.0011038 | 0.022077 | 2617 | 24238.3806 | 10.1552 | #N/A | #N/A
3881 | CORRAL 110275622 | 162991102 | CORRAL 1102 | 1.2162 | 78 | 0.0010989 | 0.085711 | 2618 | 24239.5968 | 10.0695 | #N/A | #N/A
656 | MORAGA 1105CB | 13801105 | MORAGA 1105 | 5.7453 | 121 | 0.001078 | 0.13044 | 2619 | 24245.3422 | 9.939 | #N/A | #N/A
7044 | SALT SPRINGS 210297924 | 163692102 | SALT SPRINGS 2102 | 5.1507 | 49 | 0.0010653 | 0.052198 | 2620 | 24250.4928 | 9.8868 | #N/A | #N/A
1866 | HIGGINS 1104842642 | 152691104 | HIGGINS 1104 | 5.8135 | 80 | 0.0010503 | 0.084021 | 2621 | 24256.3063 | 9.8028 | #N/A | #N/A
1316 | SHADY GLEN 1101CB | 152431101 | SHADY GLEN 1101 | 3.5282 | 72 | 0.0010502 | 0.075616 | 2622 | 24259.8345 | 9.7272 | #N/A | #N/A
8148 | MIWUK 1702S1547 | 163661702 | MIWUK 1702 | 2.7718 | 39 | 0.0010487 | 0.040901 | 2623 | 24262.6064 | 9.6863 | #N/A | #N/A
4763 | SNEATH LANE 11071277 | 22721107 | SNEATH LANE 1107 | 0 | 30 | 0.001018 | 0.030539 | 2624 | 24262.6064 | 9.6558 | #N/A | #N/A
10287 | DUNLAP 11027290 | 254061102 | DUNLAP 1102 | 0.66837 | 8 | 0.0010126 | 0.0081011 | 2625 | 24263.2747 | 9.6477 | #N/A | #N/A
9998 | RESEARCH 2102644462 | 14692102 | RESEARCH 2102 | 0.35278 | 24 | 0.0010124 | 0.024298 | 2626 | 24263.6275 | 9.6234 | #N/A | #N/A
1937 | SARATOGA 1107LC12 | 83371107 | SARATOGA 1107 | 7.4858 | 86 | 0.0010097 | 0.086838 | 2627 | 24271.1133 | 9.5365 | #N/A | #N/A
3 | HIGGINS 1104498932 | 152691104 | HIGGINS 1104 | 3.7441 | 57 | 0.0010076 | 0.057431 | 2628 | 24274.8574 | 9.4791 | #N/A | #N/A
7928 | HALSEY 11015731 | 152241101 | HALSEY 1101 | 3.1259 | 41 | 0.0010067 | 0.041274 | 2629 | 24277.9833 | 9.4378 | #N/A | #N/A
5582 | TAMARACK 1101CB | 152291101 | TAMARACK 1101 | 17.479 | 148 | 0.0010065 | 0.14896 | 2630 | 24295.4623 | 9.2889 | #N/A | #N/A
5935 | MORAGA 1103CB | 13801103 | MORAGA 1103 | 1.3309 | 82 | 0.0010058 | 0.082476 | 2631 | 24296.7932 | 9.2064 | #N/A | #N/A
6299 | PEORIA 170587222 | 163781705 | PEORIA 1705 | 5.1212 | 57 | 0.0010031 | 0.057176 | 2632 | 24301.9144 | 9.1492 | #N/A | #N/A
2943 | PAUL SWEET 2105CB | 83252105 | PAUL SWEET 2105 | 7.4461 | 86 | 0.0010024 | 0.086208 | 2633 | 24309.3606 | 9.063 | #N/A | #N/A
9018 | GREEN VALLEY 2101509068 | 83192101 | GREEN VALLEY 2101 | 1.0289 | 22 | 0.0010019 | 0.022042 | 2634 | 24310.3894 | 9.041 | #N/A | #N/A
8604 | MORGAN HILL 2105975388 | 83242105 | MORGAN HILL 2105 | 0.48181 | 18 | 0.0010016 | 0.018029 | 2635 | 24310.8713 | 9.0229 | #N/A | #N/A
5120 | PAUL SWEET 21045394 | 83252104 | PAUL SWEET 2104 | 14.5061 | 180 | 0.00099214 | 0.17859 | 2636 | 24325.3774 | 8.8443 | #N/A | #N/A
6690 | GUALALA 1111887180 | 42841111 | GUALALA 1111 | 5.3384 | 61 | 0.00098628 | 0.060163 | 2637 | 24330.7158 | 8.7842 | #N/A | #N/A
3875 | FORT BRAGG A 11014698 | 42761101 | FORT BRAGG A 1101 | 8.0068 | 101 | 0.00097756 | 0.098734 | 2638 | 24338.7226 | 8.6854 | #N/A | #N/A
8479 | SALT SPRINGS 2102L7283 | 163692102 | SALT SPRINGS 2102 | 0.65475 | 12 | 0.00097446 | 0.011693 | 2639 | 24339.3774 | 8.6738 | #N/A | #N/A
1105 | PLACER 110451732 | 152461104 | PLACER 1104 | 0.67967 | 110 | 0.00097323 | 0.10706 | 2640 | 24340.0571 | 8.5667 | #N/A | #N/A
6916 | BEN LOMOND 110196738 | 83041101 | BEN LOMOND 1101 | 6.7078 | 84 | 0.00097276 | 0.081712 | 2641 | 24346.7649 | 8.485 | #N/A | #N/A
5851 | SAN RAFAEL 1109692576 | 42011109 | SAN RAFAEL 1109 | 2.4083 | 51 | 0.0009691 | 0.049424 | 2642 | 24349.1732 | 8.4356 | #N/A | #N/A
1894 | HALF MOON BAY 11028848 | 24101102 | HALF MOON BAY 1102 | 3.8535 | 117 | 0.00096385 | 0.11277 | 2643 | 24353.0266 | 8.3228 | #N/A | #N/A
3844 | OLEMA 110150396 | 42291101 | OLEMA 1101 | 12.9443 | 162 | 0.00096084 | 0.15566 | 2644 | 24365.971 | 8.1671 | #N/A | #N/A
8685 | SANTA ROSA A 1111114 | 42151111 | SANTA ROSA A 1111 | 0.010871 | 40 | 0.00096055 | 0.038422 | 2645 | 24365.9818 | 8.1287 | #N/A | #N/A
3877 | LOS GATOS 110660116 | 82021106 | LOS GATOS 1106 | 12.2027 | 151 | 0.00095505 | 0.14421 | 2646 | 24378.1846 | 7.9845 | #N/A | #N/A
46 | MONTE RIO 11111703 | 42811111 | MONTE RIO 1111 | 1.376 | 16 | 0.00095446 | 0.015271 | 2647 | 24379.5606 | 7.9692 | #N/A | #N/A
2992 | EMERALD LAKE 0401CB | 24080401 | EMERALD LAKE 0401 | 9.3444 | 130 | 0.00094726 | 0.12314 | 2648 | 24388.905 | 7.8461 | #N/A | #N/A
5798 | DIAMOND SPRINGS 1107217974 | 152261107 | DIAMOND SPRINGS 1107 | 4.0976 | 44 | 0.00093976 | 0.04135 | 2649 | 24393.0026 | 7.8047 | #N/A | #N/A
5351 | TEMPLETON 2113A32 | 183052113 | TEMPLETON 2113 | 1.6367 | 76 | 0.00093807 | 0.071294 | 2650 | 24394.6393 | 7.7334 | #N/A | #N/A
5142 | STANISLAUS 17021850 | 162821702 | STANISLAUS 1702 | 13.4625 | 182 | 0.00093342 | 0.16988 | 2651 | 24408.1018 | 7.5636 | #N/A | #N/A
7375 | ARCATA 11224218 | 192021122 | ARCATA 1122 | 4.7795 | 27 | 0.00093079 | 0.025131 | 2652 | 24412.8813 | 7.5384 | #N/A | #N/A
2956 | BIG BASIN 110276752 | 82841102 | BIG BASIN 1102 | 2.7224 | 36 | 0.00091318 | 0.032874 | 2653 | 24415.6037 | 7.5056 | #N/A | #N/A
3629 | BRUNSWICK 11051030 | 152481105 | BRUNSWICK 1105 | 15.89 | 217 | 0.00090994 | 0.19746 | 2654 | 24431.4937 | 7.3081 | #N/A | #N/A
9250 | MIWUK 17021808 | 163661702 | MIWUK 1702 | 1.8333 | 27 | 0.00090929 | 0.024551 | 2655 | 24433.327 | 7.2835 | #N/A | #N/A
8540 | DEL MONTE 210436720 | 182222104 | DEL MONTE 2104 | 5.9526 | 87 | 0.00089535 | 0.077895 | 2656 | 24439.2796 | 7.2056 | #N/A | #N/A
950 | JARVIS 1108MR366 | 13501108 | JARVIS 1108 | 0 | 134 | 0.00088159 | 0.11813 | 2657 | 24439.2796 | 7.0875 | #N/A | #N/A
1888 | ROB ROY 2104CB | 83692104 | ROB ROY 2104 | 14.3153 | 170 | 0.0008744 | 0.14865 | 2658 | 24453.595 | 6.9389 | #N/A | #N/A
311 | SALT SPRINGS 21023142 | 163692102 | SALT SPRINGS 2102 | 17.9625 | 256 | 0.00086175 | 0.22061 | 2659 | 24471.5575 | 6.7183 | #N/A | #N/A
978 | BRYANT 0402CB | 13090402 | BRYANT 0402 | 2.3419 | 111 | 0.00085884 | 0.095332 | 2660 | 24473.8994 | 6.6229 | #N/A | #N/A
7054 | STANISLAUS 1702L3151 | 162821702 | STANISLAUS 1702 | 0.99155 | 13 | 0.00085242 | 0.011082 | 2661 | 24474.8909 | 6.6118 | #N/A | #N/A
3980 | BIG BASIN 110112838 | 82841101 | BIG BASIN 1101 | 2.3664 | 32 | 0.00085046 | 0.027215 | 2662 | 24477.2573 | 6.5846 | #N/A | #N/A
8804 | SILVERADO 2103403102 | 43432103 | SILVERADO 2103 | 0.4901 | 18 | 0.00084561 | 0.015221 | 2663 | 24477.7474 | 6.5694 | #N/A | #N/A
6283 | HATTON 11022010 | 182291102 | HATTON 1102 | 3.9836 | 43 | 0.00084365 | 0.036277 | 2664 | 24481.731 | 6.5331 | #N/A | #N/A
164 | CORONA 11034446 | 43491103 | CORONA 1103 | 0 | 124 | 0.00084052 | 0.10422 | 2665 | 24481.731 | 6.4289 | #N/A | #N/A
5512 | MORAGA 1101669542 | 13801101 | MORAGA 1101 | 3.5232 | 49 | 0.0008334 | 0.040836 | 2666 | 24485.2542 | 6.3881 | #N/A | #N/A
5671 | CURTIS 170190120 | 163351701 | CURTIS 1701 | 3.1334 | 64 | 0.00082387 | 0.052727 | 2667 | 24488.3875 | 6.3353 | #N/A | #N/A
5328 | OROSI 11027948F | 252841102 | OROSI 1102 | 1.064 | 74 | 0.00082174 | 0.060809 | 2668 | 24489.4516 | 6.2745 | #N/A | #N/A
3271 | STAFFORD 1101CB | 43201101 | STAFFORD 1101 | 1.3605 | 180 | 0.0008192 | 0.14746 | 2669 | 24490.812 | 6.1271 | #N/A | #N/A
3349 | STANISLAUS 17026028 | 162821702 | STANISLAUS 1702 | 8.3097 | 115 | 0.0008147 | 0.09369 | 2670 | 24499.1217 | 6.0334 | #N/A | #N/A
4063 | REDBUD 1102432 | 43191102 | REDBUD 1102 | 1.1202 | 130 | 0.00080536 | 0.1047 | 2671 | 24500.2419 | 5.9287 | #N/A | #N/A
4207 | SPRING GAP 170210720 | 162831702 | SPRING GAP 1702 | 4.7701 | 25 | 0.00079114 | 0.019779 | 2672 | 24505.012 | 5.9089 | #N/A | #N/A
6208 | BIG MEADOWS 2101CB | 102812101 | BIG MEADOWS 2101 | 2.106 | 21 | 0.00079069 | 0.016605 | 2673 | 24507.118 | 5.8923 | #N/A | #N/A
682 | ROSSMOOR 110676468 | 14161106 | ROSSMOOR 1106 | 0.79619 | 35 | 0.00078905 | 0.027617 | 2674 | 24507.9142 | 5.8647 | #N/A | #N/A
5936 | OAKLAND K 1102CB | 12101102 | OAKLAND K 1102 | 2.9934 | 40 | 0.0007688 | 0.030752 | 2675 | 24510.9076 | 5.8339 | #N/A | #N/A
5479 | ROSSMOOR 1108CB | 14161108 | ROSSMOOR 1108 | 4.1821 | 92 | 0.00076238 | 0.070139 | 2676 | 24515.0896 | 5.7638 | #N/A | #N/A
3739 | WEIMAR 1102CB | 152491102 | WEIMAR 1102 | 12.1849 | 151 | 0.00075189 | 0.11354 | 2677 | 24527.2746 | 5.6503 | #N/A | #N/A
4477 | MIWUK 170238218 | 163661702 | MIWUK 1702 | 10.9416 | 132 | 0.00074696 | 0.098599 | 2678 | 24538.2162 | 5.5517 | 5.5517 | #N/A
262 | ROB ROY 21055090 | 83692105 | ROB ROY 2105 | 21.267 | 245 | 0.00074249 | 0.18191 | 2679 | 24559.4832 | 5.3698 | #N/A | #N/A
459 | HARTLEY 1102824 | 43211102 | HARTLEY 1102 | 0.085463 | 103 | 0.00072721 | 0.074902 | 2680 | 24559.5687 | 5.2949 | #N/A | #N/A
3196 | SPRING GAP 17029280 | 162831702 | SPRING GAP 1702 | 6.3783 | 80 | 0.00072124 | 0.057699 | 2681 | 24565.9469 | 5.2372 | #N/A | #N/A
1359 | CAMP EVERS 210311056 | 83622103 | CAMP EVERS 2103 | 4.1747 | 48 | 0.00071991 | 0.034556 | 2682 | 24570.1216 | 5.2026 | #N/A | #N/A
2485 | EEL RIVER 1102530 | 192381102 | EEL RIVER 1102 | 0.073044 | 255 | 0.00070447 | 0.17964 | 2683 | 24570.1947 | 5.023 | #N/A | #N/A
6651 | PINECREST 04011818 | 163160401 | PINECREST 0401 | 3.0718 | 26 | 0.00069935 | 0.018183 | 2684 | 24573.2664 | 5.0048 | #N/A | #N/A
413 | BRUNSWICK 11062796 | 152481106 | BRUNSWICK 1106 | 19.8767 | 253 | 0.00069507 | 0.17585 | 2685 | 24593.1431 | 4.8289 | #N/A | #N/A
4105 | CAMP EVERS 210410442 | 83622104 | CAMP EVERS 2104 | 5.6589 | 133 | 0.00069444 | 0.092361 | 2686 | 24598.802 | 4.7366 | #N/A | #N/A
2116 | LUCERNE 1106CB | 43351106 | LUCERNE 1106 | 1.8914 | 48 | 0.00069407 | 0.033315 | 2687 | 24600.6935 | 4.7032 | #N/A | #N/A
10094 | HARRIS 1109237791 | 192431109 | HARRIS 1109 | 1.4173 | 23 | 0.00069283 | 0.015935 | 2688 | 24602.1108 | 4.6873 | #N/A | #N/A
9596 | BRUNSWICK 1104285704 | 152481104 | BRUNSWICK 1104 | 1.0477 | 17 | 0.00068515 | 0.011648 | 2689 | 24603.1585 | 4.6757 | #N/A | #N/A
591 | MIWUK 170110600 | 163661701 | MIWUK 1701 | 13.2797 | 161 | 0.000683 | 0.10996 | 2690 | 24616.4382 | 4.5657 | #N/A | #N/A
7040 | PAUL SWEET 2106428102 | 83252106 | PAUL SWEET 2106 | 12.2622 | 158 | 0.00068264 | 0.10786 | 2691 | 24628.7005 | 4.4578 | #N/A | #N/A
9535 | HOLLISTER 2105480430 | 182492105 | HOLLISTER 2105 | 0.90126 | 39 | 0.00068138 | 0.026574 | 2692 | 24629.6017 | 4.4313 | #N/A | #N/A
751 | GUALALA 1112662 | 42841112 | GUALALA 1112 | 6.2273 | 104 | 0.00067921 | 0.070638 | 2693 | 24635.8291 | 4.3606 | #N/A | #N/A
9192 | PURISIMA 110154728 | 182971101 | PURISIMA 1101 | 1.0366 | 37 | 0.00066262 | 0.024517 | 2694 | 24636.8657 | 4.3361 | #N/A | #N/A
6603 | MIRABEL 11027347 | 42091102 | MIRABEL 1102 | 0.81751 | 10 | 0.00065864 | 0.0065864 | 2695 | 24637.6832 | 4.3295 | #N/A | #N/A
6890 | CHALLENGE 110113026 | 103201101 | CHALLENGE 1101 | 8.0255 | 70 | 0.00065269 | 0.045688 | 2696 | 24645.7086 | 4.2838 | #N/A | #N/A
4651 | PACIFICA 1102320094 | 22811102 | PACIFICA 1102 | 0.2735 | 11 | 0.00064788 | 0.0071266 | 2697 | 24645.9821 | 4.2767 | #N/A | #N/A
7773 | MONTE RIO 111215401 | 42811112 | MONTE RIO 1112 | 0.86276 | 11 | 0.00064146 | 0.0070561 | 2698 | 24646.8449 | 4.2697 | #N/A | #N/A
8375 | MONTE RIO 1111256 | 42811111 | MONTE RIO 1111 | 1.5013 | 17 | 0.00063627 | 0.010817 | 2699 | 24648.3462 | 4.2588 | #N/A | #N/A
6923 | OLEMA 1101758594 | 42291101 | OLEMA 1101 | 1.2079 | 21 | 0.00062774 | 0.013182 | 2700 | 24649.5541 | 4.2457 | #N/A | #N/A
10215 | IGNACIO 11011779 | 42481101 | IGNACIO 1101 | 0.33618 | 5 | 0.00062625 | 0.0031313 | 2701 | 24649.8903 | 4.2425 | #N/A | #N/A
4571 | TEMPLETON 2113A30 | 183052113 | TEMPLETON 2113 | 0.24929 | 25 | 0.00062089 | 0.015522 | 2702 | 24650.1396 | 4.227 | #N/A | #N/A
5501 | FORT BRAGG A 11013100 | 42761101 | FORT BRAGG A 1101 | 12.2041 | 198 | 0.00061511 | 0.12179 | 2703 | 24662.3436 | 4.1052 | #N/A | #N/A
7330 | HAMILTON BRANCH 110190334 | 102361101 | HAMILTON BRANCH 1101 | 3.3524 | 44 | 0.00061497 | 0.027059 | 2704 | 24665.696 | 4.0782 | #N/A | #N/A
3053 | HIGGINS 11032194 | 152691103 | HIGGINS 1103 | 1.3317 | 36 | 0.00060703 | 0.021853 | 2705 | 24667.0277 | 4.0563 | #N/A | #N/A
9597 | MORGAN HILL 2105XR602 | 83242105 | MORGAN HILL 2105 | 0.24324 | 13 | 0.00060529 | 0.0078688 | 2706 | 24667.2709 | 4.0484 | #N/A | #N/A
5378 | DIAMOND SPRINGS 1105CB | 152261105 | DIAMOND SPRINGS 1105 | 2.0698 | 47 | 0.00059825 | 0.028118 | 2707 | 24669.3407 | 4.0203 | #N/A | #N/A
1437 | HORSESHOE 110450142 | 152571104 | HORSESHOE 1104 | 2.2351 | 55 | 0.00059558 | 0.032757 | 2708 | 24671.5758 | 3.9876 | #N/A | #N/A
4026 | MIRABEL 1101CB | 42091101 | MIRABEL 1101 | 0.49245 | 70 | 0.00059471 | 0.04163 | 2709 | 24672.0682 | 3.9459 | #N/A | #N/A
7798 | LOS GATOS 110712041 | 82021107 | LOS GATOS 1107 | 6.3044 | 65 | 0.00059297 | 0.038543 | 2710 | 24678.3727 | 3.9074 | #N/A | #N/A
1553 | MEADOW LANE 2106C558R | 14302106 | MEADOW LANE 2106 | 1.2073 | 180 | 0.00059158 | 0.10648 | 2711 | 24679.5799 | 3.8009 | #N/A | #N/A
380 | STANISLAUS 17021804 | 162821702 | STANISLAUS 1702 | 8.3797 | 118 | 0.00058985 | 0.069602 | 2712 | 24687.9596 | 3.7313 | 3.7313 | #N/A
10645 | DIAMOND SPRINGS 1103635040 | 152261103 | DIAMOND SPRINGS 1103 | 0.20148 | 2 | 0.0005888 | 0.0011776 | 2713 | 24688.1611 | 3.7301 | #N/A | #N/A
7077 | CORONA 1103776806 | 43491103 | CORONA 1103 | 0.25631 | 15 | 0.00058477 | 0.0087716 | 2714 | 24688.4174 | 3.7213 | #N/A | #N/A
4432 | BRUNSWICK 11053611 | 152481105 | BRUNSWICK 1105 | 1.6143 | 23 | 0.00057745 | 0.013281 | 2715 | 24690.0317 | 3.7081 | #N/A | #N/A
5741 | HICKS 2101XR250 | 83432101 | HICKS 2101 | 0 | 80 | 0.00057262 | 0.04581 | 2716 | 24690.0317 | 3.6623 | #N/A | #N/A
8362 | CASTRO VALLEY 1111CB | 14091111 | CASTRO VALLEY 1111 | 0.22209 | 16 | 0.00057058 | 0.0091293 | 2717 | 24690.2538 | 3.6531 | #N/A | #N/A
4792 | HALF MOON BAY 1102CB | 24101102 | HALF MOON BAY 1102 | 0.16592 | 50 | 0.0005603 | 0.028015 | 2718 | 24690.4197 | 3.6251 | #N/A | #N/A
2151 | MIWUK 170153038 | 163661701 | MIWUK 1701 | 6.6683 | 62 | 0.00055181 | 0.034212 | 2719 | 24697.088 | 3.5909 | #N/A | #N/A
5668 | ALLEGHANY 1101978 | 152101101 | ALLEGHANY 1101 | 13.9579 | 130 | 0.00055148 | 0.071692 | 2720 | 24711.0459 | 3.5192 | #N/A | #N/A
6116 | IGNACIO 1105908 | 42481105 | IGNACIO 1105 | 0.70005 | 42 | 0.00055062 | 0.023126 | 2721 | 24711.7459 | 3.4961 | #N/A | #N/A
2452 | OAKHURST 1103719490 | 254421103 | OAKHURST 1103 | 3.0184 | 44 | 0.00054847 | 0.024132 | 2722 | 24714.7643 | 3.4719 | #N/A | #N/A
1532 | HAMILTON BRANCH 1101CB | 102361101 | HAMILTON BRANCH 1101 | 2.3343 | 56 | 0.00054657 | 0.030608 | 2723 | 24717.0986 | 3.4413 | #N/A | #N/A
8732 | EL CERRITO G 1112418480 | 12501112 | EL CERRITO G 1112 | 0.75636 | 13 | 0.0005464 | 0.0071032 | 2724 | 24717.855 | 3.4342 | #N/A | #N/A
4263 | HALF MOON BAY 11038894 | 24101103 | HALF MOON BAY 1103 | 11.2506 | 110 | 0.00053494 | 0.058844 | 2725 | 24729.1056 | 3.3754 | #N/A | #N/A
4900 | CHESTER 11022564 | 103181102 | CHESTER 1102 | 2.2364 | 21 | 0.00053291 | 0.011191 | 2726 | 24731.3421 | 3.3642 | #N/A | #N/A
1003 | SANTA ROSA A 1111CB | 42151111 | SANTA ROSA A 1111 | 0.30506 | 88 | 0.00052634 | 0.046318 | 2727 | 24731.6472 | 3.3179 | #N/A | #N/A
8503 | SAN RAFAEL 11071276 | 42011107 | SAN RAFAEL 1107 | 3.7367 | 56 | 0.00052522 | 0.029412 | 2728 | 24735.3839 | 3.2885 | #N/A | #N/A
6580 | MIWUK 170247143 | 163661702 | MIWUK 1702 | 4.8991 | 67 | 0.00052216 | 0.034985 | 2729 | 24740.283 | 3.2535 | #N/A | #N/A
4101 | LAURELES 1112562376 | 182371112 | LAURELES 1112 | 7.9218 | 82 | 0.00052151 | 0.042763 | 2730 | 24748.2047 | 3.2107 | #N/A | #N/A
5934 | FITCH MOUNTAIN 1113154 | 42751113 | FITCH MOUNTAIN 1113 | 0.012787 | 108 | 0.00051973 | 0.056131 | 2731 | 24748.2175 | 3.1546 | #N/A | #N/A
5473 | EL DORADO PH 2102CB | 152762102 | EL DORADO PH 2102 | 5.5428 | 46 | 0.00051722 | 0.023792 | 2732 | 24753.7603 | 3.1308 | #N/A | #N/A
4174 | CAMP EVERS 210610718 | 83622106 | CAMP EVERS 2106 | 8.4677 | 98 | 0.0005122 | 0.050195 | 2733 | 24762.228 | 3.0806 | #N/A | #N/A
4155 | BRUNSWICK 110532536 | 152481105 | BRUNSWICK 1105 | 10.8995 | 144 | 0.00050182 | 0.072262 | 2734 | 24773.1275 | 3.0083 | #N/A | #N/A
4857 | SEACLIFF 040112946 | 83500401 | SEACLIFF 0401 | 2.4314 | 41 | 0.00050028 | 0.020511 | 2735 | 24775.5589 | 2.9878 | #N/A | #N/A
3888 | PUEBLO 1105716 | 43291105 | PUEBLO 1105 | 0.10016 | 124 | 0.00049954 | 0.061943 | 2736 | 24775.6591 | 2.9259 | #N/A | #N/A
6409 | MIWUK 1702S2247 | 163661702 | MIWUK 1702 | 1.4879 | 21 | 0.00049228 | 0.010338 | 2737 | 24777.1469 | 2.9156 | 2.9156 | #N/A
9855 | DUNLAP 1102778286 | 254061102 | DUNLAP 1102 | 2.6029 | 5 | 0.0004909 | 0.0024545 | 2738 | 24779.7498 | 2.9131 | 2.9131 | #N/A
9129 | ROSSMOOR 1102457174 | 14161102 | ROSSMOOR 1102 | 0.57523 | 14 | 0.00048348 | 0.0067687 | 2739 | 24780.325 | 2.9063 | #N/A | #N/A
8205 | ATASCADERO 1102825520 | 182541102 | ATASCADERO 1102 | 1.1789 | 21 | 0.00047064 | 0.0098834 | 2740 | 24781.504 | 2.8964 | #N/A | #N/A
2233 | IGNACIO 11011264 | 42481101 | IGNACIO 1101 | 1.9136 | 50 | 0.00046357 | 0.023178 | 2741 | 24783.4175 | 2.8733 | #N/A | #N/A
4702 | BURNEY 110145984 | 103311101 | BURNEY 1101 | 4.8309 | 68 | 0.00046238 | 0.031442 | 2742 | 24788.2484 | 2.8418 | #N/A | #N/A
911 | PEORIA 170590374 | 163781705 | PEORIA 1705 | 4.0885 | 48 | 0.0004592 | 0.022042 | 2743 | 24792.337 | 2.8198 | #N/A | #N/A
4097 | SILVERADO 2103CB | 43432103 | SILVERADO 2103 | 0 | 197 | 0.00045724 | 0.090077 | 2744 | 24792.337 | 2.7297 | #N/A | #N/A
5992 | MIWUK 17029270 | 163661702 | MIWUK 1702 | 5.8239 | 68 | 0.00045602 | 0.03101 | 2745 | 24798.1609 | 2.6987 | #N/A | #N/A
9472 | LLAGAS 2105XR234 | 83182105 | LLAGAS 2105 | 0.0025635 | 26 | 0.00045563 | 0.011846 | 2746 | 24798.1635 | 2.6869 | #N/A | #N/A
6378 | WOODACRE 11011238 | 43021101 | WOODACRE 1101 | 3.6817 | 30 | 0.0004533 | 0.013599 | 2747 | 24801.8452 | 2.6733 | #N/A | #N/A
1227 | MORAGA 110381146 | 13801103 | MORAGA 1103 | 0.7625 | 79 | 0.00045161 | 0.035677 | 2748 | 24802.6076 | 2.6376 | #N/A | #N/A
2519 | CAMPHORA 110122412 | 182071101 | CAMPHORA 1101 | 2.2876 | 130 | 0.0004496 | 0.058447 | 2749 | 24804.8952 | 2.5791 | #N/A | #N/A
2793 | CAMP EVERS 21065302 | 83622106 | CAMP EVERS 2106 | 5.9332 | 57 | 0.00044854 | 0.025567 | 2750 | 24810.8284 | 2.5536 | #N/A | #N/A
5402 | PACIFICA 1101CB | 22811101 | PACIFICA 1101 | 0.13437 | 38 | 0.00044808 | 0.017027 | 2751 | 24810.9628 | 2.5365 | #N/A | #N/A
6879 | SEACLIFF 0401CB | 83500401 | SEACLIFF 0401 | 5.7464 | 73 | 0.00044728 | 0.032652 | 2752 | 24816.7092 | 2.5039 | #N/A | #N/A
5244 | DUNBAR 1103440 | 43071103 | DUNBAR 1103 | 2.057 | 158 | 0.00044177 | 0.0698 | 2753 | 24818.7662 | 2.4341 | #N/A | #N/A
4679 | ROB ROY 210412596 | 83692104 | ROB ROY 2104 | 8.033 | 140 | 0.00043371 | 0.060719 | 2754 | 24826.7992 | 2.3734 | #N/A | #N/A
4037 | EL DORADO PH 21019759 | 152762101 | EL DORADO PH 2101 | 2.5547 | 32 | 0.00043106 | 0.013794 | 2755 | 24829.354 | 2.3596 | #N/A | #N/A
909 | TULE POWER HOUSE 1101CB | 258591101 | TULE POWER HOUSE 1101 | 4.0838 | 11 | 0.00042329 | 0.0046561 | 2756 | 24833.4378 | 2.3549 | #N/A | #N/A
7552 | WEST POINT 1101L2219 | 163201101 | WEST POINT 1101 | 3.3854 | 41 | 0.00042266 | 0.017329 | 2757 | 24836.8232 | 2.3376 | #N/A | #N/A
3464 | SERRAMONTE 110412705 | 22861104 | SERRAMONTE 1104 | 0 | 74 | 0.00042265 | 0.031276 | 2758 | 24836.8232 | 2.3063 | #N/A | #N/A
7216 | BIG RIVER 110169032 | 43081101 | BIG RIVER 1101 | 8.487 | 101 | 0.00041877 | 0.042296 | 2759 | 24845.3102 | 2.264 | #N/A | #N/A
2590 | WOODSIDE 1104520832 | 24251104 | WOODSIDE 1104 | 6.0406 | 90 | 0.00040636 | 0.036573 | 2760 | 24851.3507 | 2.2274 | #N/A | #N/A
8755 | HALF MOON BAY 1101903182 | 24101101 | HALF MOON BAY 1101 | 0.65426 | 15 | 0.00040533 | 0.0060799 | 2761 | 24852.005 | 2.2214 | #N/A | #N/A
4732 | BIG RIVER 11011286 | 43081101 | BIG RIVER 1101 | 4.775 | 92 | 0.00040112 | 0.036903 | 2762 | 24856.78 | 2.1845 | #N/A | #N/A
3369 | ORO FINO 110276008 | 103031102 | ORO FINO 1102 | 15.9545 | 170 | 0.000401 | 0.068169 | 2763 | 24872.7345 | 2.1163 | #N/A | #N/A
9255 | LAS GALLINAS A 1106228906 | 42991106 | LAS GALLINAS A 1106 | 0.61442 | 21 | 0.00039716 | 0.0083403 | 2764 | 24873.3489 | 2.1079 | #N/A | #N/A
2888 | FOOTHILL 110299432 | 182951102 | FOOTHILL 1102 | 1.4661 | 115 | 0.00039549 | 0.045481 | 2765 | 24874.8151 | 2.0625 | #N/A | #N/A
7168 | STANISLAUS 17024905 | 162821702 | STANISLAUS 1702 | 2.3021 | 35 | 0.00038885 | 0.01361 | 2766 | 24877.1172 | 2.0489 | #N/A | #N/A
4177 | LOS GATOS 110760092 | 82021107 | LOS GATOS 1107 | 9.7136 | 108 | 0.00038814 | 0.041919 | 2767 | 24886.8308 | 2.0069 | #N/A | #N/A
9726 | SALT SPRINGS 21028442 | 163692102 | SALT SPRINGS 2102 | 12.0752 | 50 | 0.00038233 | 0.019117 | 2768 | 24898.9059 | 1.9878 | #N/A | #N/A
1168 | SAN RAFAEL 11081210 | 42011108 | SAN RAFAEL 1108 | 3.2645 | 73 | 0.00038163 | 0.027859 | 2769 | 24902.1705 | 1.96 | #N/A | #N/A
9856 | PUEBLO 1105419634 | 43291105 | PUEBLO 1105 | 0.10261 | 14 | 0.00037832 | 0.0052965 | 2770 | 24902.2731 | 1.9547 | #N/A | #N/A
1493 | SAN RAMON 2107CB | 14232107 | SAN RAMON 2107 | 0.30216 | 107 | 0.00037788 | 0.040433 | 2771 | 24902.5752 | 1.9142 | #N/A | #N/A
531 | SAN RAFAEL 1109418 | 42011109 | SAN RAFAEL 1109 | 5.135 | 130 | 0.00037742 | 0.049065 | 2772 | 24907.7102 | 1.8652 | #N/A | #N/A
10509 | PAUL SWEET 2102337544 | 83252102 | PAUL SWEET 2102 | 0.35989 | 13 | 0.00037689 | 0.0048996 | 2773 | 24908.0701 | 1.8603 | #N/A | #N/A
910 | DUNLAP 11027050 | 254061102 | DUNLAP 1102 | 9.4119 | 67 | 0.0003702 | 0.024804 | 2774 | 24917.482 | 1.8355 | #N/A | #N/A
3656 | HALF MOON BAY 11038089 | 24101103 | HALF MOON BAY 1103 | 2.8145 | 29 | 0.00036614 | 0.010618 | 2775 | 24920.2965 | 1.8248 | #N/A | #N/A
6207 | CAMP EVERS 210584166 | 83622105 | CAMP EVERS 2105 | 8.2232 | 97 | 0.00036427 | 0.035334 | 2776 | 24928.5197 | 1.7895 | #N/A | #N/A
6326 | OLEMA 11011252 | 42291101 | OLEMA 1101 | 4.1073 | 50 | 0.00036141 | 0.018071 | 2777 | 24932.627 | 1.7714 | #N/A | #N/A
872 | FAIRVIEW 2207M501R | 13432207 | FAIRVIEW 2207 | 2.4962 | 60 | 0.00035751 | 0.021451 | 2778 | 24935.1232 | 1.75 | #N/A | #N/A
6151 | EDENVALE 2113CB | 82952113 | EDENVALE 2113 | 0.015269 | 24 | 0.00035038 | 0.0084091 | 2779 | 24935.1385 | 1.7416 | #N/A | #N/A
6316 | BIG RIVER 11011052 | 43081101 | BIG RIVER 1101 | 3.3289 | 49 | 0.00034866 | 0.017084 | 2780 | 24938.4674 | 1.7245 | #N/A | #N/A
4831 | ROB ROY 2105CB | 83692105 | ROB ROY 2105 | 0.73407 | 17 | 0.00034683 | 0.0058961 | 2781 | 24939.2014 | 1.7186 | #N/A | #N/A
5876 | OAKLAND X 1106CR020 | 12541106 | OAKLAND X 1106 | 2.4443 | 15 | 0.00034485 | 0.0051727 | 2782 | 24941.6458 | 1.7134 | #N/A | #N/A
8254 | DOLAN ROAD 1101857972 | 182381101 | DOLAN ROAD 1101 | 1.0395 | 18 | 0.00034064 | 0.0061316 | 2783 | 24942.6852 | 1.7073 | #N/A | #N/A
7697 | PARADISE 1103143744 | 102831103 | PARADISE 1103 | 1.0604 | 13 | 0.00033981 | 0.0044176 | 2784 | 24943.7456 | 1.7029 | #N/A | #N/A
4615 | PEORIA 170184318 | 163781701 | PEORIA 1701 | 10.2462 | 142 | 0.00033804 | 0.048002 | 2785 | 24953.9917 | 1.6549 | #N/A | #N/A
8175 | WEST POINT 1101L1969 | 163201101 | WEST POINT 1101 | 1.0992 | 16 | 0.00032448 | 0.0051917 | 2786 | 24955.0909 | 1.6497 | #N/A | #N/A
2671 | LOS GATOS 1101LB40 | 82021101 | LOS GATOS 1101 | 8.5234 | 131 | 0.00032354 | 0.042384 | 2787 | 24963.6143 | 1.6073 | #N/A | #N/A
1669 | SPRING GAP 17029690 | 162831702 | SPRING GAP 1702 | 17.3503 | 185 | 0.00031402 | 0.058094 | 2788 | 24980.9646 | 1.5492 | #N/A | #N/A
1740 | GUALALA 1111402866 | 42841111 | GUALALA 1111 | 1.5913 | 20 | 0.0003137 | 0.0062739 | 2789 | 24982.5559 | 1.5429 | #N/A | #N/A
6457 | ATASCADERO 1103CB | 182541103 | ATASCADERO 1103 | 0.18914 | 18 | 0.00031227 | 0.0056208 | 2790 | 24982.745 | 1.5373 | #N/A | #N/A
4913 | SAN LUIS OBISPO 1108CB | 182631108 | SAN LUIS OBISPO 1108 | 0.0063814 | 69 | 0.00031202 | 0.02153 | 2791 | 24982.7514 | 1.5158 | #N/A | #N/A
3199 | EL CERRITO G 1105BR160 | 12501105 | EL CERRITO G 1105 | 8.3249 | 132 | 0.00031068 | 0.04101 | 2792 | 24991.0763 | 1.4748 | #N/A | #N/A
7182 | EEL RIVER 1102720639 | 192381102 | EEL RIVER 1102 | 1.6537 | 25 | 0.0003062 | 0.0076549 | 2793 | 24992.73 | 1.4671 | #N/A | #N/A
6389 | PERRY 1101W10 | 183071101 | PERRY 1101 | 1.4636 | 29 | 0.00030601 | 0.0088744 | 2794 | 24994.1936 | 1.4582 | #N/A | #N/A
5102 | DEL MONTE 21049096 | 182222104 | DEL MONTE 2104 | 3.2966 | 78 | 0.00030601 | 0.023869 | 2795 | 24997.4902 | 1.4344 | #N/A | #N/A
483 | EL CERRITO G 1105CB | 12501105 | EL CERRITO G 1105 | 7.4474 | 97 | 0.00030421 | 0.029509 | 2796 | 25004.9376 | 1.4049 | #N/A | #N/A
8801 | WOODSIDE 1104420146 | 24251104 | WOODSIDE 1104 | 2.728 | 43 | 0.00030412 | 0.013077 | 2797 | 25007.6656 | 1.3918 | #N/A | #N/A
2740 | SUNOL 1101MR650 | 14241101 | SUNOL 1101 | 1.2969 | 30 | 0.00029523 | 0.0088568 | 2798 | 25008.9624 | 1.3829 | #N/A | #N/A
1558 | RINCON 1103472 | 43321103 | RINCON 1103 | 3.0645 | 71 | 0.00029462 | 0.020918 | 2799 | 25012.027 | 1.362 | #N/A | #N/A
1849 | FORT BRAGG A 11044690 | 42761104 | FORT BRAGG A 1104 | 11.6289 | 161 | 0.00029439 | 0.047396 | 2800 | 25023.6558 | 1.3146 | #N/A | #N/A
1214 | ROB ROY 21055166 | 83692105 | ROB ROY 2105 | 5.4945 | 81 | 0.00028991 | 0.023482 | 2801 | 25029.1503 | 1.2911 | #N/A | #N/A
6981 | HALF MOON BAY 110148868 | 24101101 | HALF MOON BAY 1101 | 0 | 21 | 0.00028316 | 0.0059463 | 2802 | 25029.1503 | 1.2852 | #N/A | #N/A
5899 | VOLTA 11011640 | 102541101 | VOLTA 1101 | 10.4439 | 59 | 0.00028287 | 0.016689 | 2803 | 25039.5941 | 1.2685 | #N/A | #N/A
7108 | RESERVATION ROAD 11023032 | 182731102 | RESERVATION ROAD 1102 | 3.6042 | 84 | 0.00028141 | 0.023638 | 2804 | 25043.1984 | 1.2449 | #N/A | #N/A
5988 | SPRING GAP 1702693441 | 162831702 | SPRING GAP 1702 | 4.2634 | 59 | 0.00027928 | 0.016478 | 2805 | 25047.4618 | 1.2284 | #N/A | #N/A
5979 | BIG RIVER 11012183 | 43081101 | BIG RIVER 1101 | 2.6394 | 33 | 0.00027436 | 0.009054 | 2806 | 25050.1012 | 1.2193 | #N/A | #N/A
760 | BIG RIVER 1101952 | 43081101 | BIG RIVER 1101 | 10.1564 | 130 | 0.00027431 | 0.03566 | 2807 | 25060.2576 | 1.1837 | #N/A | #N/A
1378 | PARADISE 1105CB | 102831105 | PARADISE 1105 | 6.1048 | 86 | 0.00026897 | 0.023131 | 2808 | 25066.3624 | 1.1605 | #N/A | #N/A
4711 | RESEARCH 2102446423 | 14692102 | RESEARCH 2102 | 0.70566 | 23 | 0.00026534 | 0.0061027 | 2809 | 25067.0681 | 1.1544 | #N/A | #N/A
534 | STANISLAUS 170237278 | 162821702 | STANISLAUS 1702 | 6.7927 | 99 | 0.00026318 | 0.026055 | 2810 | 25073.8608 | 1.1284 | #N/A | #N/A
956 | PAUL SWEET 2106CB | 83252106 | PAUL SWEET 2106 | 5.2845 | 115 | 0.00025895 | 0.029779 | 2811 | 25079.1453 | 1.0986 | #N/A | #N/A
832 | ROSSMOOR 110168920 | 14161101 | ROSSMOOR 1101 | 6.4273 | 91 | 0.0002577 | 0.02345 | 2812 | 25085.5726 | 1.0751 | #N/A | #N/A
5459 | PARADISE 1106CB | 102831106 | PARADISE 1106 | 4.6443 | 53 | 0.0002457 | 0.013022 | 2813 | 25090.2169 | 1.0621 | #N/A | #N/A
8168 | SAUSALITO 1102410 | 42491102 | SAUSALITO 1102 | 1.5556 | 28 | 0.00024476 | 0.0068532 | 2814 | 25091.7724 | 1.0553 | #N/A | #N/A
2941 | DIAMOND SPRINGS 1103CB | 152261103 | DIAMOND SPRINGS 1103 | 0.55038 | 109 | 0.00024231 | 0.026412 | 2815 | 25092.3228 | 1.0289 | #N/A | #N/A
5531 | MAPLE CREEK 1101CB | 192101101 | MAPLE CREEK 1101 | 8.8674 | 60 | 0.00023784 | 0.01427 | 2816 | 25101.1902 | 1.0146 | #N/A | #N/A
6907 | BRUNSWICK 111063100 | 152481110 | BRUNSWICK 1110 | 4.0969 | 55 | 0.00023675 | 0.013021 | 2817 | 25105.2871 | 1.0016 | #N/A | #N/A
2877 | MONTE RIO 11111701 | 42811111 | MONTE RIO 1111 | 1.3978 | 18 | 0.00023556 | 0.0042401 | 2818 | 25106.6849 | 0.99733 | #N/A | #N/A
6347 | PACIFICA 11015001 | 22811101 | PACIFICA 1101 | 0 | 25 | 0.00023403 | 0.0058507 | 2819 | 25106.6849 | 0.99148 | #N/A | #N/A
1625 | SAN LUIS OBISPO 1105CB | 182631105 | SAN LUIS OBISPO 1105 | 0.041946 | 43 | 0.000232 | 0.0099759 | 2820 | 25106.7268 | 0.9815 | #N/A | #N/A
5409 | SAN RAFAEL 1108CB | 42011108 | SAN RAFAEL 1108 | 5.8855 | 102 | 0.00023023 | 0.023483 | 2821 | 25112.6123 | 0.95802 | #N/A | #N/A
8271 | ROSSMOOR 1107857172 | 14161107 | ROSSMOOR 1107 | 0.094493 | 15 | 0.00022992 | 0.0034488 | 2822 | 25112.7068 | 0.95457 | #N/A | #N/A
10147 | WINDSOR 11035060 | 43501103 | WINDSOR 1103 | 0.18121 | 12 | 0.00022663 | 0.0027196 | 2823 | 25112.888 | 0.95185 | #N/A | #N/A
8566 | CORONA 1103114284 | 43491103 | CORONA 1103 | 0.28075 | 11 | 0.00022547 | 0.0024802 | 2824 | 25113.1688 | 0.94937 | #N/A | #N/A
849 | STANISLAUS 170237276 | 162821702 | STANISLAUS 1702 | 11.651 | 168 | 0.00022047 | 0.037039 | 2825 | 25124.8198 | 0.91233 | #N/A | #N/A
3868 | HATTON 11012026 | 182291101 | HATTON 1101 | 5.2447 | 126 | 0.00021753 | 0.027409 | 2826 | 25130.0646 | 0.88492 | #N/A | #N/A
427 | SAUSALITO 1101688590 | 42491101 | SAUSALITO 1101 | 1.0513 | 32 | 0.00021706 | 0.0069459 | 2827 | 25131.1158 | 0.87798 | #N/A | #N/A
4476 | CALISTOGA 1102705 | 42711102 | CALISTOGA 1102 | 0.38677 | 20 | 0.00021298 | 0.0042596 | 2828 | 25131.5026 | 0.87372 | #N/A | #N/A
1205 | MIWUK 17028090 | 163661702 | MIWUK 1702 | 4.0407 | 53 | 0.00021162 | 0.011216 | 2829 | 25135.5433 | 0.8625 | #N/A | #N/A
61 | CAMBRIA 1102W50 | 182771102 | CAMBRIA 1102 | 0.62023 | 40 | 0.00021093 | 0.0084371 | 2830 | 25136.1636 | 0.85406 | #N/A | #N/A
189 | BIG RIVER 110179628 | 43081101 | BIG RIVER 1101 | 14.8005 | 156 | 0.00021051 | 0.032839 | 2831 | 25150.964 | 0.82123 | #N/A | #N/A
3166 | ALTO 11251226 | 42031125 | ALTO 1125 | 7.6339 | 96 | 0.00020916 | 0.02008 | 2832 | 25158.598 | 0.80115 | #N/A | #N/A
6809 | OAKLAND D 1112CR192 | 12041112 | OAKLAND D 1112 | 2.463 | 54 | 0.00020828 | 0.011247 | 2833 | 25161.061 | 0.7899 | #N/A | #N/A
4374 | OCEANO 1103V22 | 182601103 | OCEANO 1103 | 0.031381 | 14 | 0.00020377 | 0.0028528 | 2834 | 25161.0924 | 0.78705 | #N/A | #N/A
9957 | DEL MONTE 21043066 | 182222104 | DEL MONTE 2104 | 0.016181 | 2 | 0.00020359 | 0.00040718 | 2835 | 25161.1086 | 0.78664 | #N/A | #N/A
4818 | ROSSMOOR 11018132 | 14161101 | ROSSMOOR 1101 | 2.6402 | 47 | 0.00020337 | 0.0095582 | 2836 | 25163.7487 | 0.77708 | #N/A | #N/A
2856 | SAN RAFAEL 11071166 | 42011107 | SAN RAFAEL 1107 | 12.5314 | 213 | 0.00020294 | 0.043227 | 2837 | 25176.2802 | 0.73385 | #N/A | #N/A
445 | MONTE RIO 1112CB | 42811112 | MONTE RIO 1112 | 3.5299 | 43 | 0.00020121 | 0.0086519 | 2838 | 25179.8101 | 0.7252 | #N/A | #N/A
10280 | SAUSALITO 1102964592 | 42491102 | SAUSALITO 1102 | 0.58542 | 15 | 0.00019824 | 0.0029736 | 2839 | 25180.3955 | 0.72223 | #N/A | #N/A
1145 | OLEMA 11011200 | 42291101 | OLEMA 1101 | 2.8955 | 34 | 0.00019566 | 0.0066525 | 2840 | 25183.291 | 0.71558 | #N/A | #N/A
6437 | HAMILTON BRANCH 110153192 | 102361101 | HAMILTON BRANCH 1101 | 0.55299 | 30 | 0.0001937 | 0.0058109 | 2841 | 25183.844 | 0.70976 | #N/A | #N/A
7381 | PACIFICA 1102660408 | 22811102 | PACIFICA 1102 | 0.35468 | 26 | 0.00019086 | 0.0049624 | 2842 | 25184.1987 | 0.7048 | #N/A | #N/A
5360 | ALHAMBRA 1105CB | 14101105 | ALHAMBRA 1105 | 0.82879 | 33 | 0.00018865 | 0.0062254 | 2843 | 25185.0275 | 0.69858 | #N/A | #N/A
1909 | MORAGA 1104750618 | 13801104 | MORAGA 1104 | 0.95612 | 13 | 0.0001837 | 0.002388 | 2844 | 25185.9836 | 0.69619 | #N/A | #N/A
7663 | SOBRANTE 1103CB | 14671103 | SOBRANTE 1103 | 4.1925 | 55 | 0.00018024 | 0.0099135 | 2845 | 25190.1761 | 0.68627 | #N/A | #N/A
4846 | ORINDA 0402402/2 LR | 12350402 | ORINDA 0402 | 6.554 | 91 | 0.00017917 | 0.016305 | 2846 | 25196.7301 | 0.66997 | #N/A | #N/A
6268 | CURTIS 1702S2123 | 163351702 | CURTIS 1702 | 1.8577 | 25 | 0.00017177 | 0.0042941 | 2847 | 25198.5878 | 0.66568 | #N/A | #N/A
1067 | DIAMOND SPRINGS 1106290705 | 152261106 | DIAMOND SPRINGS 1106 | 3.2275 | 38 | 0.00016712 | 0.0063506 | 2848 | 25201.8153 | 0.65933 | #N/A | #N/A
3874 | PARADISE 1105829194 | 102831105 | PARADISE 1105 | 11.2644 | 142 | 0.00016422 | 0.023319 | 2849 | 25213.0797 | 0.63601 | #N/A | #N/A
1686 | CAMP EVERS 210312990 | 83622103 | CAMP EVERS 2103 | 13.2243 | 161 | 0.00016127 | 0.025964 | 2850 | 25226.304 | 0.61004 | #N/A | #N/A
6595 | HIGGINS 110432747 | 152691104 | HIGGINS 1104 | 0.65102 | 26 | 0.00016086 | 0.0041824 | 2851 | 25226.955 | 0.60586 | #N/A | #N/A
2910 | HALSEY 110176178 | 152241101 | HALSEY 1101 | 20.219 | 248 | 0.00015934 | 0.039517 | 2852 | 25247.174 | 0.56634 | #N/A | #N/A
2602 | PRUNEDALE 11103716 | 182961110 | PRUNEDALE 1110 | 0.42929 | 157 | 0.00015488 | 0.024316 | 2853 | 25247.6033 | 0.54203 | #N/A | #N/A
6371 | BAY MEADOWS 210257886 | 24012102 | BAY MEADOWS 2102 | 4.0705 | 81 | 0.00015101 | 0.012232 | 2854 | 25251.6738 | 0.52979 | #N/A | #N/A
3718 | TEMPLETON 2108A40 | 183052108 | TEMPLETON 2108 | 3.7814 | 174 | 0.00015079 | 0.026237 | 2855 | 25255.4552 | 0.50356 | #N/A | #N/A
8208 | BRUNSWICK 11038918 | 152481103 | BRUNSWICK 1103 | 1.5109 | 30 | 0.0001494 | 0.0044819 | 2856 | 25256.9661 | 0.49908 | #N/A | #N/A
833 | BRUNSWICK 110456468 | 152481104 | BRUNSWICK 1104 | 5.538 | 85 | 0.0001483 | 0.012606 | 2857 | 25262.5041 | 0.48647 | #N/A | #N/A
8651 | MORGAN HILL 2111419718 | 83242111 | MORGAN HILL 2111 | 2.2684 | 25 | 0.0001469 | 0.0036725 | 2858 | 25264.7725 | 0.4828 | #N/A | #N/A
4060 | KONOCTI 11081278 | 43311108 | KONOCTI 1108 | 5.6556 | 96 | 0.00014529 | 0.013948 | 2859 | 25270.4281 | 0.46885 | #N/A | #N/A
5993 | LAS GALLINAS A 11041220 | 42991104 | LAS GALLINAS A 1104 | 0 | 57 | 0.00013353 | 0.0076113 | 2860 | 25270.4281 | 0.46124 | #N/A | #N/A
1481 | SOBRANTE 1101CB | 14671101 | SOBRANTE 1101 | 14.2302 | 209 | 0.00012965 | 0.027098 | 2861 | 25284.6583 | 0.43414 | #N/A | #N/A
6330 | CURTIS 170268380 | 163351702 | CURTIS 1702 | 6.6575 | 88 | 0.00012865 | 0.011322 | 2862 | 25291.3158 | 0.42282 | #N/A | #N/A
2410 | SAN LEANDRO U 1114MR544 | 13111114 | SAN LEANDRO U 1114 | 0.017391 | 62 | 0.00012274 | 0.0076101 | 2863 | 25291.3332 | 0.41521 | #N/A | #N/A
5853 | ROB ROY 210410954 | 83692104 | ROB ROY 2104 | 7.103 | 90 | 0.00012262 | 0.011036 | 2864 | 25298.4363 | 0.40417 | #N/A | #N/A
4344 | NOVATO 11041282 | 42211104 | NOVATO 1104 | 0 | 56 | 0.00012029 | 0.0067363 | 2865 | 25298.4363 | 0.39744 | #N/A | #N/A
8432 | SNEATH LANE 110715341 | 22721107 | SNEATH LANE 1107 | 0.24318 | 18 | 0.00011859 | 0.0021346 | 2866 | 25298.6794 | 0.3953 | #N/A | #N/A
6986 | RESERVATION ROAD 1102303870 | 182731102 | RESERVATION ROAD 1102 | 0.63919 | 7 | 0.0001185 | 0.00082948 | 2867 | 25299.3186 | 0.39447 | #N/A | #N/A
4626 | COTATI 1104426 | 42271104 | COTATI 1104 | 2.0009 | 52 | 0.00011662 | 0.0060642 | 2868 | 25301.3196 | 0.38841 | #N/A | #N/A
8778 | PAUL SWEET 2107774760 | 83252107 | PAUL SWEET 2107 | 3.3243 | 37 | 0.00011197 | 0.0041429 | 2869 | 25304.6439 | 0.38427 | #N/A | #N/A
4484 | FROGTOWN 170274648 | 163451702 | FROGTOWN 1702 | 0.16296 | 63 | 0.00011106 | 0.0069966 | 2870 | 25304.8069 | 0.37727 | #N/A | #N/A
6192 | PEORIA 170169124 | 163781701 | PEORIA 1701 | 2.7019 | 33 | 0.00010917 | 0.0036026 | 2871 | 25307.5087 | 0.37367 | #N/A | #N/A
8000 | DIAMOND SPRINGS 1107116815 | 152261107 | DIAMOND SPRINGS 1107 | 1.5788 | 33 | 0.00010723 | 0.0035385 | 2872 | 25309.0875 | 0.37013 | #N/A | #N/A
8610 | HOOPA 110193038 | 192401101 | HOOPA 1101 | 1.3098 | 39 | 0.00010645 | 0.0041517 | 2873 | 25310.3973 | 0.36598 | #N/A | #N/A
995 | HALF MOON BAY 11022032 | 24101102 | HALF MOON BAY 1102 | 0.56279 | 103 | 0.0001063 | 0.010949 | 2874 | 25310.9601 | 0.35503 | #N/A | #N/A
7250 | ORINDA 04013442 | 12350401 | ORINDA 0401 | 3.4803 | 68 | 0.00010618 | 0.0072205 | 2875 | 25314.4404 | 0.34781 | #N/A | #N/A
367 | ARCATA 112233060 | 192021122 | ARCATA 1122 | 0.53218 | 64 | 9.9531e-05 | 0.00637 | 2876 | 25314.9726 | 0.34144 | #N/A | #N/A
2545 | FAIRVIEW 2207P148 | 13432207 | FAIRVIEW 2207 | 0.84643 | 54 | 9.8792e-05 | 0.0053348 | 2877 | 25315.819 | 0.3361 | #N/A | #N/A
5688 | STANISLAUS 170275348 | 162821702 | STANISLAUS 1702 | 5.3029 | 77 | 9.5481e-05 | 0.0073521 | 2878 | 25321.122 | 0.32875 | #N/A | #N/A
5946 | SALT SPRINGS 21011232 | 163692101 | SALT SPRINGS 2101 | 7.7196 | 64 | 9.0864e-05 | 0.0058153 | 2879 | 25328.8415 | 0.32293 | #N/A | #N/A
4735 | ELK 11018779 | 42981101 | ELK 1101 | 4.2669 | 41 | 8.9792e-05 | 0.0036815 | 2880 | 25333.1084 | 0.31925 | #N/A | #N/A
744 | GABILAN 11013034 | 182331101 | GABILAN 1101 | 0.04993 | 193 | 8.716e-05 | 0.016822 | 2881 | 25333.1583 | 0.30243 | #N/A | #N/A
8975 | SPRING GAP 170286032 | 162831702 | SPRING GAP 1702 | 1.0042 | 23 | 8.538e-05 | 0.0019637 | 2882 | 25334.1625 | 0.30047 | #N/A | #N/A
6252 | CHESTER 1101922138 | 103181101 | CHESTER 1101 | 1.5691 | 24 | 8.4169e-05 | 0.00202 | 2883 | 25335.7316 | 0.29845 | #N/A | #N/A
320 | GREEN VALLEY 210112106 | 83192101 | GREEN VALLEY 2101 | 0.34608 | 139 | 8.0919e-05 | 0.011248 | 2884 | 25336.0776 | 0.2872 | #N/A | #N/A
390 | PETALUMA C 110856774 | 42631108 | PETALUMA C 1108 | 0.23933 | 39 | 7.8722e-05 | 0.0030702 | 2885 | 25336.317 | 0.28413 | #N/A | #N/A
3580 | SOBRANTE 1102CB | 14671102 | SOBRANTE 1102 | 10.4408 | 132 | 7.4597e-05 | 0.0098468 | 2886 | 25346.7578 | 0.27428 | #N/A | #N/A
5433 | HATTON 110137088 | 182291101 | HATTON 1101 | 7.1066 | 135 | 7.338e-05 | 0.0099063 | 2887 | 25353.8644 | 0.26438 | #N/A | #N/A
2226 | FORT BRAGG A 11021226 | 42761102 | FORT BRAGG A 1102 | 1.6891 | 102 | 7.0366e-05 | 0.0071773 | 2888 | 25355.5535 | 0.2572 | #N/A | #N/A
7611 | DIAMOND SPRINGS 1106279670 | 152261106 | DIAMOND SPRINGS 1106 | 3.8807 | 54 | 7.0093e-05 | 0.003785 | 2889 | 25359.4342 | 0.25341 | #N/A | #N/A
9967 | CRESTA 1101103126 | 102251101 | CRESTA 1101 | 0.30269 | 5 | 6.9083e-05 | 0.00034541 | 2890 | 25359.7369 | 0.25307 | #N/A | #N/A
6701 | BRUNSWICK 11064639 | 152481106 | BRUNSWICK 1106 | 3.2493 | 44 | 6.7888e-05 | 0.0029871 | 2891 | 25362.9862 | 0.25008 | #N/A | #N/A
8130 | LAURELES 111110141 | 182371111 | LAURELES 1111 | 2.9178 | 21 | 6.784e-05 | 0.0014246 | 2892 | 25365.9041 | 0.24866 | #N/A | #N/A
17 | SAN RAFAEL 1106910 | 42011106 | SAN RAFAEL 1106 | 1.6921 | 89 | 6.6955e-05 | 0.005959 | 2893 | 25367.5962 | 0.2427 | #N/A | #N/A
428 | SOBRANTE 1102690098 | 14671102 | SOBRANTE 1102 | 7.3859 | 108 | 6.6684e-05 | 0.0072019 | 2894 | 25374.9821 | 0.2355 | #N/A | #N/A
6532 | PARADISE 110536656 | 102831105 | PARADISE 1105 | 0.13723 | 14 | 6.4706e-05 | 0.00090588 | 2895 | 25375.1194 | 0.23459 | #N/A | #N/A
1066 | JARVIS 1101MR210 | 13501101 | JARVIS 1101 | 0.81682 | 103 | 6.2939e-05 | 0.0064828 | 2896 | 25375.9362 | 0.22811 | #N/A | #N/A
5877 | OAKLAND K 1102CR014 | 12101102 | OAKLAND K 1102 | 10.5071 | 137 | 6.2366e-05 | 0.0085442 | 2897 | 25386.4432 | 0.21956 | #N/A | #N/A
7339 | BIG BASIN 110165444 | 82841101 | BIG BASIN 1101 | 0.47064 | 9 | 6.0572e-05 | 0.00054514 | 2898 | 25386.9139 | 0.21902 | #N/A | #N/A
1476 | BOLINAS 1101528 | 42261101 | BOLINAS 1101 | 1.7811 | 46 | 5.4065e-05 | 0.002487 | 2899 | 25388.695 | 0.21653 | #N/A | #N/A
9601 | CAMP EVERS 2104189010 | 83622104 | CAMP EVERS 2104 | 0.036695 | 4 | 5.2348e-05 | 0.00020939 | 2900 | 25388.7317 | 0.21632 | #N/A | #N/A
4401 | SILVERADO 2103507513 | 43432103 | SILVERADO 2103 | 2.9853 | 65 | 4.9269e-05 | 0.0032025 | 2901 | 25391.717 | 0.21312 | #N/A | #N/A
625 | ROSSMOOR 1101L503R | 14161101 | ROSSMOOR 1101 | 4.2951 | 62 | 4.8731e-05 | 0.0030213 | 2902 | 25396.0121 | 0.2101 | #N/A | #N/A
7021 | DOLAN ROAD 1101590402 | 182381101 | DOLAN ROAD 1101 | 2.4338 | 78 | 4.8446e-05 | 0.0037788 | 2903 | 25398.4459 | 0.20632 | #N/A | #N/A
7515 | PARADISE 1103468200 | 102831103 | PARADISE 1103 | 0.33044 | 4 | 4.8111e-05 | 0.00019244 | 2904 | 25398.7764 | 0.20613 | #N/A | #N/A
8899 | NAPA 11025039 | 42021102 | NAPA 1102 | 0 | 28 | 4.5334e-05 | 0.0012694 | 2905 | 25398.7764 | 0.20486 | #N/A | #N/A
10522 | PARADISE 11042486 | 102831104 | PARADISE 1104 | 0.091002 | 2 | 4.4268e-05 | 8.8537e-05 | 2906 | 25398.8674 | 0.20477 | #N/A | #N/A
11006 | PARADISE 1105828400 | 102831105 | PARADISE 1105 | 0.031143 | 2 | 4.4154e-05 | 8.8308e-05 | 2907 | 25398.8985 | 0.20468 | #N/A | #N/A
10495 | CEDAR CREEK 11011362 | 103321101 | CEDAR CREEK 1101 | 0.015507 | 1 | 4.3827e-05 | 4.3827e-05 | 2908 | 25398.914 | 0.20464 | #N/A | #N/A
4622 | EL CERRITO G 1105BR194 | 12501105 | EL CERRITO G 1105 | 3.8214 | 74 | 4.3185e-05 | 0.0031957 | 2909 | 25402.7355 | 0.20144 | #N/A | #N/A
7319 | PARADISE 11061212 | 102831106 | PARADISE 1106 | 2.0091 | 33 | 4.2503e-05 | 0.0014026 | 2910 | 25404.7445 | 0.20004 | #N/A | #N/A
10489 | CAMP EVERS 210510996 | 83622105 | CAMP EVERS 2105 | 0.76209 | 8 | 4.2365e-05 | 0.00033892 | 2911 | 25405.5066 | 0.1997 | #N/A | #N/A
7716 | PARADISE 110599226 | 102831105 | PARADISE 1105 | 1.1447 | 42 | 4.1187e-05 | 0.0017299 | 2912 | 25406.6514 | 0.19797 | #N/A | #N/A
6446 | FORT BRAGG A 1102956 | 42761102 | FORT BRAGG A 1102 | 11.3603 | 145 | 4.0908e-05 | 0.0059316 | 2913 | 25418.0117 | 0.19204 | #N/A | #N/A
2257 | BIG TREES 04025300 | 83050402 | BIG TREES 0402 | 9.7951 | 115 | 3.9714e-05 | 0.0045672 | 2914 | 25427.8068 | 0.18747 | #N/A | #N/A
9775 | CAMP EVERS 210595050 | 83622105 | CAMP EVERS 2105 | 0.13873 | 5 | 3.9532e-05 | 0.00019766 | 2915 | 25427.9455 | 0.18727 | #N/A | #N/A
2020 | DUNLAP 11037170 | 254061103 | DUNLAP 1103 | 5.4237 | 54 | 3.9493e-05 | 0.0021326 | 2916 | 25433.3692 | 0.18514 | #N/A | #N/A
9147 | BEN LOMOND 04015400 | 83040401 | BEN LOMOND 0401 | 0.45458 | 4 | 3.9445e-05 | 0.00015778 | 2917 | 25433.8238 | 0.18498 | #N/A | #N/A
2924 | ROB ROY 210538430 | 83692105 | ROB ROY 2105 | 3.7665 | 90 | 3.7768e-05 | 0.0033991 | 2918 | 25437.5903 | 0.18158 | #N/A | #N/A
2345 | MORGAN HILL 2106CB | 83242106 | MORGAN HILL 2106 | 0.62349 | 47 | 3.5184e-05 | 0.0016536 | 2919 | 25438.2138 | 0.17993 | #N/A | #N/A
4552 | SHINGLE SPRINGS 2108449638 | 153652108 | SHINGLE SPRINGS 2108 | 0.026093 | 1 | 3.5151e-05 | 3.5151e-05 | 2920 | 25438.2399 | 0.17989 | #N/A | #N/A
2359 | PACIFICA 1101777484 | 22811101 | PACIFICA 1101 | 0.90431 | 50 | 3.5066e-05 | 0.0017533 | 2921 | 25439.1442 | 0.17814 | #N/A | #N/A
6715 | PARADISE 11032534 | 102831103 | PARADISE 1103 | 3.1733 | 49 | 3.3375e-05 | 0.0016354 | 2922 | 25442.3175 | 0.17651 | #N/A | #N/A
416 | PACIFICA 1102CB | 22811102 | PACIFICA 1102 | 0.34812 | 51 | 3.2507e-05 | 0.0016578 | 2923 | 25442.6657 | 0.17485 | #N/A | #N/A
4774 | PARADISE 11042488 | 102831104 | PARADISE 1104 | 3.5364 | 47 | 3.2259e-05 | 0.0015162 | 2924 | 25446.2021 | 0.17333 | #N/A | #N/A
10872 | WILLOW CREEK 1103181562 | 192171103 | WILLOW CREEK 1103 | 0.0028415 | 1 | 3.208e-05 | 3.208e-05 | 2925 | 25446.2049 | 0.1733 | #N/A | #N/A
5198 | PARADISE 1104283794 | 102831104 | PARADISE 1104 | 2.3684 | 37 | 3.2004e-05 | 0.0011841 | 2926 | 25448.5733 | 0.17212 | #N/A | #N/A
2421 | FORT BRAGG A 110235592 | 42761102 | FORT BRAGG A 1102 | 13.1322 | 149 | 3.1961e-05 | 0.0047622 | 2927 | 25461.7055 | 0.16735 | #N/A | #N/A
6748 | BRUNSWICK 11103907 | 152481110 | BRUNSWICK 1110 | 0.89367 | 16 | 3.1747e-05 | 0.00050795 | 2928 | 25462.5991 | 0.16685 | #N/A | #N/A
1323 | PEORIA 17013186 | 163781701 | PEORIA 1701 | 9.8236 | 143 | 3.1551e-05 | 0.0045118 | 2929 | 25472.4227 | 0.16233 | #N/A | #N/A
6182 | BERESFORD 0403435168 | 24040403 | BERESFORD 0403 | 1.2855 | 26 | 3.1131e-05 | 0.00080941 | 2930 | 25473.7082 | 0.16152 | #N/A | #N/A
8329 | BRUNSWICK 1104244027 | 152481104 | BRUNSWICK 1104 | 0.30625 | 6 | 3.093e-05 | 0.00018558 | 2931 | 25474.0145 | 0.16134 | #N/A | #N/A
10464 | CAMP EVERS 210595394 | 83622105 | CAMP EVERS 2105 | 0.49123 | 8 | 3.0854e-05 | 0.00024683 | 2932 | 25474.5057 | 0.16109 | #N/A | #N/A
4342 | PARADISE 110636042 | 102831106 | PARADISE 1106 | 8.1942 | 119 | 3.0817e-05 | 0.0036673 | 2933 | 25482.7 | 0.15742 | #N/A | #N/A
9818 | ANDERSON 1101561686 | 103261101 | ANDERSON 1101 | 0.091487 | 1 | 2.9674e-05 | 2.9674e-05 | 2934 | 25482.7914 | 0.1574 | #N/A | #N/A
2309 | BEN LOMOND 040116010 | 83040401 | BEN LOMOND 0401 | 1.696 | 25 | 2.9564e-05 | 0.00073909 | 2935 | 25484.4875 | 0.15666 | #N/A | #N/A
2259 | LAKEWOOD 210738404 | 13532107 | LAKEWOOD 2107 | 3.5616 | 47 | 2.9507e-05 | 0.0013868 | 2936 | 25488.0491 | 0.15527 | #N/A | #N/A
6756 | FAIRMOUNT 0401395180 | 12650401 | FAIRMOUNT 0401 | 1.407 | 20 | 2.9412e-05 | 0.00058824 | 2937 | 25489.4561 | 0.15468 | #N/A | #N/A
9891 | RIO DELL 1102214052 | 192251102 | RIO DELL 1102 | 0.58493 | 7 | 2.933e-05 | 0.00020531 | 2938 | 25490.041 | 0.15448 | #N/A | #N/A
9611 | DIAMOND SPRINGS 1106176130 | 152261106 | DIAMOND SPRINGS 1106 | 0.019934 | 1 | 2.9315e-05 | 2.9315e-05 | 2939 | 25490.0609 | 0.15445 | #N/A | #N/A
9648 | CAMP EVERS 2103CB | 83622103 | CAMP EVERS 2103 | 0.11832 | 6 | 2.9049e-05 | 0.00017429 | 2940 | 25490.1793 | 0.15427 | #N/A | #N/A
7669 | PARADISE 1104CB | 102831104 | PARADISE 1104 | 1.3747 | 46 | 2.9018e-05 | 0.0013348 | 2941 | 25491.5539 | 0.15294 | #N/A | #N/A
8116 | BRUNSWICK 1107969778 | 152481107 | BRUNSWICK 1107 | 0.66562 | 9 | 2.8554e-05 | 0.00025699 | 2942 | 25492.2196 | 0.15268 | #N/A | #N/A
1751 | PARADISE 1104954322 | 102831104 | PARADISE 1104 | 4.3027 | 63 | 2.8353e-05 | 0.0017862 | 2943 | 25496.5223 | 0.15089 | #N/A | #N/A
6559 | BIG BASIN 11015479 | 82841101 | BIG BASIN 1101 | 0.17979 | 3 | 2.7773e-05 | 8.3319e-05 | 2944 | 25496.7021 | 0.15081 | #N/A | #N/A
11110 | CAMP EVERS 2105BL 2101 | 83622105 | CAMP EVERS 2105 | 0.0032262 | 1 | 2.7401e-05 | 2.7401e-05 | 2945 | 25496.7053 | 0.15078 | #N/A | #N/A
7068 | BURNS 2101CB | 183582101 | BURNS 2101 | 1.7044 | 19 | 2.7081e-05 | 0.00051453 | 2946 | 25498.4097 | 0.15027 | #N/A | #N/A
10401 | POINT MORETTI 110110722 | 82931101 | POINT MORETTI 1101 | 0.58294 | 9 | 2.6688e-05 | 0.00024019 | 2947 | 25498.9926 | 0.15003 | #N/A | #N/A
2162 | SOBRANTE 1102L510R | 14671102 | SOBRANTE 1102 | 9.6575 | 136 | 2.6158e-05 | 0.0035575 | 2948 | 25508.6501 | 0.14647 | #N/A | #N/A
8264 | MIRABEL 1101781318 | 42091101 | MIRABEL 1101 | 0.10698 | 3 | 2.5377e-05 | 7.6132e-05 | 2949 | 25508.7571 | 0.14639 | #N/A | #N/A
2959 | PARADISE 110453544 | 102831104 | PARADISE 1104 | 0.64333 | 19 | 2.5314e-05 | 0.00048097 | 2950 | 25509.4004 | 0.14591 | #N/A | #N/A
2047 | VALLEY VIEW 1103CB | 14341103 | VALLEY VIEW 1103 | 0.16939 | 83 | 2.5206e-05 | 0.0020921 | 2951 | 25509.5698 | 0.14382 | #N/A | #N/A
3341 | CAMP EVERS 21055146 | 83622105 | CAMP EVERS 2105 | 5.9259 | 63 | 2.4561e-05 | 0.0015473 | 2952 | 25515.4957 | 0.14227 | #N/A | #N/A
4945 | CASTRO VALLEY 1102837904 | 14091102 | CASTRO VALLEY 1102 | 1.0374 | 25 | 2.4435e-05 | 0.00061089 | 2953 | 25516.5331 | 0.14166 | #N/A | #N/A
5852 | PARADISE 1104961990 | 102831104 | PARADISE 1104 | 6.8193 | 91 | 2.3677e-05 | 0.0021547 | 2954 | 25523.3524 | 0.13951 | #N/A | #N/A
8958 | PARADISE 1103772517 | 102831103 | PARADISE 1103 | 1.7261 | 24 | 2.3519e-05 | 0.00056446 | 2955 | 25525.0785 | 0.13894 | #N/A | #N/A
5973 | BEN LOMOND 0401CB | 83040401 | BEN LOMOND 0401 | 7.7747 | 106 | 2.3026e-05 | 0.0024408 | 2956 | 25532.8532 | 0.1365 | #N/A | #N/A
10776 | GRASS VALLEY 1101528232 | 152031101 | GRASS VALLEY 1101 | 0.093008 | 2 | 2.2245e-05 | 4.449e-05 | 2957 | 25532.9462 | 0.13646 | #N/A | #N/A
10760 | FLINT 1102CB | 152531102 | FLINT 1102 | 0.092864 | 2 | 2.218e-05 | 4.436e-05 | 2958 | 25533.0391 | 0.13641 | #N/A | #N/A
3909 | MORRO BAY 1102V84 | 183011102 | MORRO BAY 1102 | 0.22982 | 126 | 2.1832e-05 | 0.0027508 | 2959 | 25533.2689 | 0.13366 | #N/A | #N/A
7549 | PLACERVILLE 1111CB | 153081111 | PLACERVILLE 1111 | 1.3954 | 16 | 2.1827e-05 | 0.00034924 | 2960 | 25534.6644 | 0.13331 | #N/A | #N/A
6107 | POINT MORETTI 110139126 | 82931101 | POINT MORETTI 1101 | 2.259 | 31 | 2.101e-05 | 0.00065131 | 2961 | 25536.9234 | 0.13266 | #N/A | #N/A
9485 | CAMP EVERS 2106834583 | 83622106 | CAMP EVERS 2106 | 0.60972 | 7 | 1.9977e-05 | 0.00013984 | 2962 | 25537.5331 | 0.13252 | #N/A | #N/A
6136 | BIG TREES 0402737512 | 83050402 | BIG TREES 0402 | 6.7852 | 89 | 1.9465e-05 | 0.0017324 | 2963 | 25544.3183 | 0.13079 | #N/A | #N/A
940 | CAMP EVERS 210511384 | 83622105 | CAMP EVERS 2105 | 5.2222 | 59 | 1.9223e-05 | 0.0011342 | 2964 | 25549.5405 | 0.12966 | #N/A | #N/A
8260 | DIAMOND SPRINGS 1106762780 | 152261106 | DIAMOND SPRINGS 1106 | 0.24908 | 11 | 1.9222e-05 | 0.00021145 | 2965 | 25549.7896 | 0.12945 | #N/A | #N/A
9711 | BRUNSWICK 1103262343 | 152481103 | BRUNSWICK 1103 | 0.76623 | 11 | 1.9193e-05 | 0.00021112 | 2966 | 25550.5558 | 0.12923 | #N/A | #N/A
6422 | BIG BASIN 11029741 | 82841102 | BIG BASIN 1102 | 0.64417 | 10 | 1.8794e-05 | 0.00018794 | 2967 | 25551.2 | 0.12905 | #N/A | #N/A
471 | BIG BASIN 11015028 | 82841101 | BIG BASIN 1101 | 5.0266 | 59 | 1.8516e-05 | 0.0010925 | 2968 | 25556.2265 | 0.12795 | #N/A | #N/A
5836 | BRUNSWICK 1103851116 | 152481103 | BRUNSWICK 1103 | 0.1964 | 4 | 1.8459e-05 | 7.3835e-05 | 2969 | 25556.4229 | 0.12788 | #N/A | #N/A
10320 | DIAMOND SPRINGS 1106926235 | 152261106 | DIAMOND SPRINGS 1106 | 0.18979 | 4 | 1.8372e-05 | 7.3487e-05 | 2970 | 25556.6127 | 0.12781 | #N/A | #N/A
10026 | SARATOGA 1103981056 | 83371103 | SARATOGA 1103 | 0.082049 | 2 | 1.8259e-05 | 3.6518e-05 | 2971 | 25556.6948 | 0.12777 | #N/A | #N/A
7034 | DIAMOND SPRINGS 110699658 | 152261106 | DIAMOND SPRINGS 1106 | 0 | 39 | 1.8228e-05 | 0.0007109 | 2972 | 25556.6948 | 0.12706 | #N/A | #N/A
4269 | BRUNSWICK 110378862 | 152481103 | BRUNSWICK 1103 | 0.076823 | 17 | 1.8213e-05 | 0.00030962 | 2973 | 25556.7716 | 0.12675 | #N/A | #N/A
3650 | ROB ROY 210512584 | 83692105 | ROB ROY 2105 | 3.5122 | 297 | 1.8188e-05 | 0.0054019 | 2974 | 25560.2838 | 0.12135 | #N/A | #N/A
2640 | PERRY 1101V72 | 183071101 | PERRY 1101 | 5.9727 | 101 | 1.8115e-05 | 0.0018297 | 2975 | 25566.2565 | 0.11952 | #N/A | #N/A
7574 | CAMP EVERS 210611006 | 83622106 | CAMP EVERS 2106 | 2.0392 | 24 | 1.8001e-05 | 0.00043202 | 2976 | 25568.2957 | 0.11909 | #N/A | #N/A
10111 | ALLEGHANY 11011101/2 | 152101101 | ALLEGHANY 1101 | 0.020437 | 1 | 1.7836e-05 | 1.7836e-05 | 2977 | 25568.3161 | 0.11907 | #N/A | #N/A
7350 | SUMMIT 1101CB | 152591101 | SUMMIT 1101 | 0.1374 | 2 | 1.7744e-05 | 3.5488e-05 | 2978 | 25568.4535 | 0.11903 | #N/A | #N/A
10523 | CAMP EVERS 2104710556 | 83622104 | CAMP EVERS 2104 | 0.040934 | 2 | 1.7662e-05 | 3.5324e-05 | 2979 | 25568.4944 | 0.119 | #N/A | #N/A
5707 | FLINT 1101958726 | 152531101 | FLINT 1101 | 0.9978 | 13 | 1.7619e-05 | 0.00022904 | 2980 | 25569.4922 | 0.11877 | #N/A | #N/A
8628 | POINT MORETTI 11015401 | 82931101 | POINT MORETTI 1101 | 2.5155 | 34 | 1.7505e-05 | 0.00059516 | 2981 | 25572.0078 | 0.11817 | #N/A | #N/A
10455 | POTTER VALLEY P H 1104CB | 42281104 | POTTER VALLEY P H 1104 | 0.098474 | 2 | 1.7411e-05 | 3.4822e-05 | 2982 | 25572.1063 | 0.11814 | #N/A | #N/A
1795 | BOLINAS 11011064 | 42261101 | BOLINAS 1101 | 0.62485 | 51 | 1.7391e-05 | 0.00088693 | 2983 | 25572.7311 | 0.11725 | #N/A | #N/A
11067 | BRUNSWICK 1104761310 | 152481104 | BRUNSWICK 1104 | 0.02679 | 1 | 1.7283e-05 | 1.7283e-05 | 2984 | 25572.7579 | 0.11723 | #N/A | #N/A
130 | CAMP EVERS 21055232 | 83622105 | CAMP EVERS 2105 | 4.5152 | 50 | 1.7257e-05 | 0.00086284 | 2985 | 25577.2731 | 0.11637 | #N/A | #N/A
9051 | BRUNSWICK 1103956424 | 152481103 | BRUNSWICK 1103 | 1.0328 | 21 | 1.7224e-05 | 0.00036171 | 2986 | 25578.3059 | 0.11601 | #N/A | #N/A
7122 | CAMP EVERS 210510786 | 83622105 | CAMP EVERS 2105 | 4.5943 | 58 | 1.7083e-05 | 0.0009908 | 2987 | 25582.9002 | 0.11502 | #N/A | #N/A
7997 | CAMP EVERS 210411048 | 83622104 | CAMP EVERS 2104 | 0.91592 | 19 | 1.6894e-05 | 0.00032099 | 2988 | 25583.8161 | 0.1147 | #N/A | #N/A
10098 | RALSTON 1101100040 | 24141101 | RALSTON 1101 | 0.82301 | 7 | 1.6779e-05 | 0.00011745 | 2989 | 25584.6392 | 0.11458 | #N/A | #N/A
4770 | CAMP EVERS 210574170 | 83622105 | CAMP EVERS 2105 | 3.5755 | 43 | 1.6759e-05 | 0.00072063 | 2990 | 25588.2146 | 0.11386 | #N/A | #N/A
10059 | POTTER VALLEY P H 1105CB | 42281105 | POTTER VALLEY P H 1105 | 0.055533 | 2 | 1.6548e-05 | 3.3096e-05 | 2991 | 25588.2702 | 0.11383 | #N/A | #N/A
1470 | PLACERVILLE 210619732 | 153082106 | PLACERVILLE 2106 | 9.2596 | 125 | 1.6359e-05 | 0.0020448 | 2992 | 25597.5297 | 0.11178 | #N/A | #N/A
5865 | CAMP EVERS 210611044 | 83622106 | CAMP EVERS 2106 | 7.6394 | 144 | 1.6316e-05 | 0.0023496 | 2993 | 25605.1691 | 0.10943 | #N/A | #N/A
4584 | BRUNSWICK 1107357568 | 152481107 | BRUNSWICK 1107 | 1.1981 | 35 | 1.6214e-05 | 0.0005675 | 2994 | 25606.3672 | 0.10886 | #N/A | #N/A
4170 | SAN RAFAEL 11042651 | 42011104 | SAN RAFAEL 1104 | 0.76975 | 10 | 1.6143e-05 | 0.00016143 | 2995 | 25607.1369 | 0.1087 | #N/A | #N/A
4250 | SAN RAFAEL 1106837 | 42011106 | SAN RAFAEL 1106 | 0.67349 | 22 | 1.6143e-05 | 0.00035514 | 2996 | 25607.8104 | 0.10835 | #N/A | #N/A
8770 | MIRABEL 11027401 | 42091102 | MIRABEL 1102 | 1.0628 | 12 | 1.5859e-05 | 0.00019031 | 2997 | 25608.8732 | 0.10816 | #N/A | #N/A
5879 | BIG BASIN 11019773 | 82841101 | BIG BASIN 1101 | 0.4505 | 6 | 1.5808e-05 | 9.4849e-05 | 2998 | 25609.3237 | 0.10806 | #N/A | #N/A
4254 | BRUNSWICK 111095576 | 152481110 | BRUNSWICK 1110 | 0 | 30 | 1.5765e-05 | 0.00047296 | 2999 | 25609.3237 | 0.10759 | #N/A | #N/A
5644 | BRUNSWICK 1103234378 | 152481103 | BRUNSWICK 1103 | 0.6406 | 13 | 1.5727e-05 | 0.00020445 | 3000 | 25609.9643 | 0.10739 | #N/A | #N/A
644 | CAMP EVERS 210511004 | 83622105 | CAMP EVERS 2105 | 4.3389 | 60 | 1.5545e-05 | 0.00093268 | 3001 | 25614.3032 | 0.10645 | #N/A | #N/A
10461 | GIRVAN 1102296428 | 103401102 | GIRVAN 1102 | 1.7207 | 14 | 1.5492e-05 | 0.00021689 | 3002 | 25616.0239 | 0.10624 | #N/A | #N/A
8135 | WOODSIDE 1101CB | 24251101 | WOODSIDE 1101 | 0 | 59 | 1.545e-05 | 0.00091153 | 3003 | 25616.0239 | 0.10532 | #N/A | #N/A
555 | BRUNSWICK 110750008 | 152481107 | BRUNSWICK 1107 | 1.1366 | 64 | 1.5377e-05 | 0.0009841 | 3004 | 25617.1606 | 0.10434 | #N/A | #N/A
4851 | DIAMOND SPRINGS 1106910235 | 152261106 | DIAMOND SPRINGS 1106 | 0.52893 | 16 | 1.5283e-05 | 0.00024453 | 3005 | 25617.6895 | 0.1041 | #N/A | #N/A
436 | SARATOGA 1107LC26 | 83371107 | SARATOGA 1107 | 5.6293 | 74 | 1.5103e-05 | 0.0011176 | 3006 | 25623.3188 | 0.10298 | #N/A | #N/A
3317 | PLACERVILLE 1110CB | 153081110 | PLACERVILLE 1110 | 0.86396 | 28 | 1.5035e-05 | 0.00042097 | 3007 | 25624.1827 | 0.10256 | #N/A | #N/A
4169 | GRASS VALLEY 1102CB | 152031102 | GRASS VALLEY 1102 | 0.081891 | 81 | 1.4894e-05 | 0.0012064 | 3008 | 25624.2646 | 0.10135 | #N/A | #N/A
1767 | MONTE RIO 111264682 | 42811112 | MONTE RIO 1112 | 1.762 | 22 | 1.4883e-05 | 0.00032742 | 3009 | 25626.0267 | 0.10102 | #N/A | #N/A
7374 | MIRABEL 1102841 | 42091102 | MIRABEL 1102 | 0.81233 | 12 | 1.4849e-05 | 0.00017819 | 3010 | 25626.839 | 0.10085 | #N/A | #N/A
9494 | SAN RAFAEL 1101546438 | 42011101 | SAN RAFAEL 1101 | 0.95798 | 14 | 1.4698e-05 | 0.00020577 | 3011 | 25627.797 | 0.10064 | #N/A | #N/A
7746 | SALT SPRINGS 21014913 | 163692101 | SALT SPRINGS 2101 | 3.7696 | 54 | 1.4645e-05 | 0.00079082 | 3012 | 25631.5666 | 0.099849 | #N/A | #N/A
7346 | OAKLAND K 1101CR346 | 12101101 | OAKLAND K 1101 | 0.20568 | 3 | 1.4607e-05 | 4.3821e-05 | 3013 | 25631.7723 | 0.099805 | #N/A | #N/A
112 | EL DORADO PH 210219562 | 152762102 | EL DORADO PH 2102 | 7.2492 | 98 | 1.4503e-05 | 0.0014213 | 3014 | 25639.0214 | 0.098384 | #N/A | #N/A
3957 | LOS GATOS 1106LA42 | 82021106 | LOS GATOS 1106 | 2.7716 | 35 | 1.445e-05 | 0.00050575 | 3015 | 25641.793 | 0.097878 | #N/A | #N/A
10681 | GEYSERVILLE 1101975350 | 42891101 | GEYSERVILLE 1101 | 0.045436 | 3 | 1.4284e-05 | 4.2852e-05 | 3016 | 25641.8384 | 0.097835 | #N/A | #N/A
10208 | SHINGLE SPRINGS 2110CB | 153652110 | SHINGLE SPRINGS 2110 | 0.83703 | 15 | 1.4099e-05 | 0.00021149 | 3017 | 25642.6755 | 0.097624 | #N/A | #N/A
10739 | FORT BRAGG A 1104920850 | 42761104 | FORT BRAGG A 1104 | 0.20025 | 3 | 1.406e-05 | 4.2181e-05 | 3018 | 25642.8757 | 0.097581 | #N/A | #N/A
9733 | AUBURN 11028611 | 152161102 | AUBURN 1102 | 1.7986 | 22 | 1.3867e-05 | 0.00030508 | 3019 | 25644.6743 | 0.097276 | #N/A | #N/A
6925 | MIRABEL 11022043 | 42091102 | MIRABEL 1102 | 0.56074 | 8 | 1.3842e-05 | 0.00011074 | 3020 | 25645.235 | 0.097166 | #N/A | #N/A
6206 | SAN RAFAEL 11081247 | 42011108 | SAN RAFAEL 1108 | 0.27562 | 3 | 1.3714e-05 | 4.1142e-05 | 3021 | 25645.5107 | 0.097124 | #N/A | #N/A
9515 | HARRIS 1109661309 | 192431109 | HARRIS 1109 | 0.28204 | 16 | 1.3667e-05 | 0.00021867 | 3022 | 25645.7927 | 0.096906 | #N/A | #N/A
10016 | CAMP EVERS 2104600529 | 83622104 | CAMP EVERS 2104 | 0.26277 | 4 | 1.3356e-05 | 5.3422e-05 | 3023 | 25646.0555 | 0.096852 | #N/A | #N/A
10551 | PUEBLO 1104968601 | 43291104 | PUEBLO 1104 | 0.0076071 | 1 | 1.3316e-05 | 1.3316e-05 | 3024 | 25646.0631 | 0.096839 | #N/A | #N/A
8097 | SARATOGA 11075696 | 83371107 | SARATOGA 1107 | 5.0666 | 90 | 1.3265e-05 | 0.0011939 | 3025 | 25651.1297 | 0.095645 | #N/A | #N/A
9710 | GEYSERVILLE 1101216442 | 42891101 | GEYSERVILLE 1101 | 0.2035 | 4 | 1.2906e-05 | 5.1625e-05 | 3026 | 25651.3332 | 0.095593 | #N/A | #N/A
8869 | BRUNSWICK 11047181 | 152481104 | BRUNSWICK 1104 | 0.77324 | 11 | 1.2843e-05 | 0.00014128 | 3027 | 25652.1065 | 0.095452 | #N/A | #N/A
8464 | CAMP EVERS 21067603 | 83622106 | CAMP EVERS 2106 | 0.94918 | 11 | 1.278e-05 | 0.00014058 | 3028 | 25653.0556 | 0.095312 | #N/A | #N/A
1616 | SARATOGA 1106LC24 | 83371106 | SARATOGA 1106 | 8.2403 | 154 | 1.2747e-05 | 0.001963 | 3029 | 25661.2959 | 0.093349 | #N/A | #N/A
10877 | MORAGA 110183424 | 13801101 | MORAGA 1101 | 1.6162 | 7 | 1.2546e-05 | 8.7822e-05 | 3030 | 25662.9121 | 0.093261 | #N/A | #N/A
7661 | CAMP EVERS 210616000 | 83622106 | CAMP EVERS 2106 | 2.0843 | 51 | 1.2496e-05 | 0.0006373 | 3031 | 25664.9964 | 0.092623 | #N/A | #N/A
11062 | KESWICK 1101CB | 103451101 | KESWICK 1101 | 0.016574 | 1 | 1.2413e-05 | 1.2413e-05 | 3032 | 25665.0129 | 0.092611 | #N/A | #N/A
10730 | STAFFORD 1101344092 | 43201101 | STAFFORD 1101 | 0.071671 | 2 | 1.2368e-05 | 2.4736e-05 | 3033 | 25665.0846 | 0.092586 | #N/A | #N/A
2899 | PLACER 1101208930 | 152461101 | PLACER 1101 | 0.1163 | 10 | 1.2302e-05 | 0.00012302 | 3034 | 25665.2009 | 0.092463 | #N/A | #N/A
3721 | SHINGLE SPRINGS 210511172 | 153652105 | SHINGLE SPRINGS 2105 | 2.0001 | 38 | 1.2003e-05 | 0.00045612 | 3035 | 25667.2011 | 0.092007 | #N/A | #N/A
8829 | MONTE RIO 1111CB | 42811111 | MONTE RIO 1111 | 0.25414 | 4 | 1.1845e-05 | 4.7378e-05 | 3036 | 25667.4552 | 0.09196 | #N/A | #N/A
3789 | LOS GATOS 1106LA46 | 82021106 | LOS GATOS 1106 | 1.4989 | 20 | 1.1694e-05 | 0.00023387 | 3037 | 25668.9541 | 0.091726 | #N/A | #N/A
8577 | SARATOGA 1115463510 | 83371115 | SARATOGA 1115 | 2.9197 | 41 | 1.1648e-05 | 0.00047756 | 3038 | 25671.8739 | 0.091248 | #N/A | #N/A
8231 | HALF MOON BAY 11038898 | 24101103 | HALF MOON BAY 1103 | 0.64313 | 9 | 1.1558e-05 | 0.00010403 | 3039 | 25672.517 | 0.091144 | #N/A | #N/A
3716 | CASTRO VALLEY 1102MR359 | 14091102 | CASTRO VALLEY 1102 | 0 | 90 | 1.1476e-05 | 0.0010328 | 3040 | 25672.517 | 0.090112 | #N/A | #N/A
9742 | MONROE 210392868 | 43302103 | MONROE 2103 | 0.1265 | 14 | 1.1443e-05 | 0.0001602 | 3041 | 25672.6435 | 0.089951 | #N/A | #N/A
830 | OAKLAND X 1104391688 | 12541104 | OAKLAND X 1104 | 1.2876 | 16 | 1.1434e-05 | 0.00018295 | 3042 | 25673.9311 | 0.089768 | #N/A | #N/A
3807 | CAMP EVERS 210355638 | 83622103 | CAMP EVERS 2103 | 1.8332 | 42 | 1.1416e-05 | 0.00047946 | 3043 | 25675.7643 | 0.089289 | #N/A | #N/A
2161 | LAKEWOOD 2227W503R | 13532227 | LAKEWOOD 2227 | 0.075745 | 89 | 1.1363e-05 | 0.0010113 | 3044 | 25675.84 | 0.088278 | #N/A | #N/A
10225 | CLOVERDALE 1101409224 | 42821101 | CLOVERDALE 1101 | 0.086215 | 4 | 1.131e-05 | 4.524e-05 | 3045 | 25675.9262 | 0.088232 | #N/A | #N/A
9704 | DEL MAR 210938684 | 152582109 | DEL MAR 2109 | 0.023864 | 1 | 1.1274e-05 | 1.1274e-05 | 3046 | 25675.9501 | 0.088221 | #N/A | #N/A
6951 | MONTE RIO 1111506 | 42811111 | MONTE RIO 1111 | 1.2565 | 18 | 1.1203e-05 | 0.00020165 | 3047 | 25677.2066 | 0.088019 | #N/A | #N/A
7579 | WOODSIDE 11012299 | 24251101 | WOODSIDE 1101 | 1.8197 | 25 | 1.1198e-05 | 0.00027996 | 3048 | 25679.0263 | 0.08774 | #N/A | #N/A
4426 | SHINGLE SPRINGS 11038752 | 153651103 | SHINGLE SPRINGS 1103 | 1.8569 | 32 | 1.0889e-05 | 0.00034845 | 3049 | 25680.8832 | 0.087391 | #N/A | #N/A
3276 | CAMP EVERS 210310946 | 83622103 | CAMP EVERS 2103 | 5.6546 | 112 | 1.0851e-05 | 0.0012153 | 3050 | 25686.5379 | 0.086176 | #N/A | #N/A
4220 | OAKLAND X 1104CR214 | 12541104 | OAKLAND X 1104 | 2.882 | 35 | 1.0841e-05 | 0.00037942 | 3051 | 25689.4199 | 0.085796 | #N/A | #N/A
3032 | OAKLAND X 1104CR288 | 12541104 | OAKLAND X 1104 | 2.7237 | 46 | 1.0814e-05 | 0.00049744 | 3052 | 25692.1436 | 0.085299 | #N/A | #N/A
3352 | OAKLAND X 1104CR022 | 12541104 | OAKLAND X 1104 | 4.0194 | 48 | 1.073e-05 | 0.00051505 | 3053 | 25696.163 | 0.084784 | #N/A | #N/A
9828 | ALLEGHANY 11021101/2 | 152101102 | ALLEGHANY 1102 | 0.019385 | 1 | 1.0723e-05 | 1.0723e-05 | 3054 | 25696.1824 | 0.084773 | #N/A | #N/A
9784 | CAMP EVERS 2104496570 | 83622104 | CAMP EVERS 2104 | 0.24196 | 8 | 1.0717e-05 | 8.5734e-05 | 3055 | 25696.4243 | 0.084687 | #N/A | #N/A
6309 | MONTE RIO 1113250 | 42811113 | MONTE RIO 1113 | 1.2339 | 14 | 1.0662e-05 | 0.00014927 | 3056 | 25697.6582 | 0.084538 | #N/A | #N/A
10893 | FROGTOWN 1702390720 | 163451702 | FROGTOWN 1702 | 0.12582 | 2 | 1.055e-05 | 2.11e-05 | 3057 | 25697.784 | 0.084517 | #N/A | #N/A
4614 | SAN RAFAEL 11081262 | 42011108 | SAN RAFAEL 1108 | 3.9225 | 57 | 1.0529e-05 | 0.00060016 | 3058 | 25701.7065 | 0.083917 | #N/A | #N/A
9095 | LLAGAS 2107250129 | 83182107 | LLAGAS 2107 | 0.24964 | 5 | 1.046e-05 | 5.23e-05 | 3059 | 25701.9561 | 0.083865 | #N/A | #N/A
8911 | CAMP EVERS 2106CB | 83622106 | CAMP EVERS 2106 | 0.68456 | 37 | 1.0397e-05 | 0.00038468 | 3060 | 25702.6407 | 0.08348 | #N/A | #N/A
10545 | PASO ROBLES 1103451760 | 182611103 | PASO ROBLES 1103 | 0.061067 | 2 | 1.0297e-05 | 2.0594e-05 | 3061 | 25702.7018 | 0.083459 | #N/A | #N/A
1830 | SANTA ROSA A 1104210 | 42151104 | SANTA ROSA A 1104 | 6.512 | 107 | 1.0255e-05 | 0.0010973 | 3062 | 25709.2138 | 0.082362 | #N/A | #N/A
10656 | MIWUK 170179118 | 163661701 | MIWUK 1701 | 0.019364 | 2 | 1.0238e-05 | 2.0475e-05 | 3063 | 25709.2332 | 0.082342 | #N/A | #N/A
7888 | MONTE RIO 1112212 | 42811112 | MONTE RIO 1112 | 2.2487 | 27 | 1.0234e-05 | 0.00027631 | 3064 | 25711.4819 | 0.082065 | #N/A | #N/A
5285 | CAMP EVERS 21061625 | 83622106 | CAMP EVERS 2106 | 0.87071 | 10 | 1.0231e-05 | 0.00010231 | 3065 | 25712.3526 | 0.081963 | #N/A | #N/A
7246 | HUMBOLDT BAY 1102104220 | 192341102 | HUMBOLDT BAY 1102 | 0.91788 | 45 | 1.0177e-05 | 0.00045796 | 3066 | 25713.2705 | 0.081505 | #N/A | #N/A
3485 | SAN RAFAEL 1107CB | 42011107 | SAN RAFAEL 1107 | 4.8541 | 107 | 9.9897e-06 | 0.0010689 | 3067 | 25718.1246 | 0.080436 | #N/A | #N/A
1447 | OAKLAND K 1104CR204 | 12101104 | OAKLAND K 1104 | 4.1265 | 49 | 9.9677e-06 | 0.00048842 | 3068 | 25722.2511 | 0.079948 | #N/A | #N/A
10822 | GRASS VALLEY 1103CB | 152031103 | GRASS VALLEY 1103 | 0.11882 | 2 | 9.9558e-06 | 1.9912e-05 | 3069 | 25722.3699 | 0.079928 | #N/A | #N/A
3457 | OAKLAND K 1101CR178 | 12101101 | OAKLAND K 1101 | 0.32933 | 7 | 9.8623e-06 | 6.9036e-05 | 3070 | 25722.6992 | 0.079859 | #N/A | #N/A
3129 | SYCAMORE CREEK 1109CB | 102971109 | SYCAMORE CREEK 1109 | 0.16852 | 108 | 9.8448e-06 | 0.0010632 | 3071 | 25722.8678 | 0.078795 | #N/A | #N/A
2013 | SHINGLE SPRINGS 210851474 | 153652108 | SHINGLE SPRINGS 2108 | 0.36925 | 68 | 9.839e-06 | 0.00066905 | 3072 | 25723.237 | 0.078126 | #N/A | #N/A
4677 | MIDDLETOWN 1101932140 | 43141101 | MIDDLETOWN 1101 | 0.53555 | 15 | 9.669e-06 | 0.00014503 | 3073 | 25723.7726 | 0.077981 | #N/A | #N/A
3638 | WOODSIDE 1104CB | 24251104 | WOODSIDE 1104 | 0.10424 | 114 | 9.6632e-06 | 0.0011016 | 3074 | 25723.8768 | 0.07688 | #N/A | #N/A
8277 | MONTE RIO 1113532 | 42811113 | MONTE RIO 1113 | 0.52475 | 8 | 9.6241e-06 | 7.6993e-05 | 3075 | 25724.4016 | 0.076803 | #N/A | #N/A
854 | SHINGLE SPRINGS 1104CB | 153651104 | SHINGLE SPRINGS 1104 | 0.70184 | 32 | 9.5675e-06 | 0.00030616 | 3076 | 25725.1034 | 0.076497 | #N/A | #N/A
6660 | HALSEY 11026129 | 152241102 | HALSEY 1102 | 3.2042 | 39 | 9.5328e-06 | 0.00037178 | 3077 | 25728.3076 | 0.076125 | #N/A | #N/A
10561 | BIG RIVER 1101CB | 43081101 | BIG RIVER 1101 | 0.02199 | 1 | 9.4951e-06 | 9.4951e-06 | 3078 | 25728.3295 | 0.076115 | #N/A | #N/A
4323 | GIRVAN 1102CB | 103401102 | GIRVAN 1102 | 1.0934 | 102 | 9.4726e-06 | 0.0009662 | 3079 | 25729.423 | 0.075149 | #N/A | #N/A
5228 | MONTE RIO 11135026 | 42811113 | MONTE RIO 1113 | 1.844 | 23 | 9.4686e-06 | 0.00021778 | 3080 | 25731.267 | 0.074931 | #N/A | #N/A
7379 | CALPELLA 1102379946 | 43411102 | CALPELLA 1102 | 0.75316 | 15 | 9.4131e-06 | 0.0001412 | 3081 | 25732.0202 | 0.07479 | #N/A | #N/A
8927 | ELK 1101CB | 42981101 | ELK 1101 | 0.02481 | 1 | 9.4072e-06 | 9.4072e-06 | 3082 | 25732.045 | 0.074781 | #N/A | #N/A
6426 | ALTO 1125296476 | 42031125 | ALTO 1125 | 0.65944 | 11 | 9.3993e-06 | 0.00010339 | 3083 | 25732.7044 | 0.074677 | #N/A | #N/A
7763 | BRUNSWICK 1105297538 | 152481105 | BRUNSWICK 1105 | 1.0588 | 15 | 9.367e-06 | 0.0001405 | 3084 | 25733.7632 | 0.074537 | #N/A | #N/A
6048 | SILVERADO 2105337226 | 43432105 | SILVERADO 2105 | 0.28495 | 13 | 9.3615e-06 | 0.0001217 | 3085 | 25734.0481 | 0.074415 | #N/A | #N/A
785 | MIRABEL 1102CB | 42091102 | MIRABEL 1102 | 0.22303 | 85 | 9.286e-06 | 0.00078931 | 3086 | 25734.2711 | 0.073626 | #N/A | #N/A
10915 | CLARKSVILLE 210551478 | 153612105 | CLARKSVILLE 2105 | 0.050375 | 3 | 9.2483e-06 | 2.7745e-05 | 3087 | 25734.3215 | 0.073598 | #N/A | #N/A
3642 | AUBURN 1102CB | 152161102 | AUBURN 1102 | 1.3908 | 99 | 9.2292e-06 | 0.00091369 | 3088 | 25735.7123 | 0.072684 | #N/A | #N/A
10606 | BERKELEY F 1105BR166 | 12061105 | BERKELEY F 1105 | 0.038182 | 2 | 9.2229e-06 | 1.8446e-05 | 3089 | 25735.7505 | 0.072666 | #N/A | #N/A
2771 | RIO DELL 1102CB | 192251102 | RIO DELL 1102 | 0 | 86 | 9.2139e-06 | 0.0007924 | 3090 | 25735.7505 | 0.071874 | #N/A | #N/A
10346 | EEL RIVER 1103241646 | 192381103 | EEL RIVER 1103 | 0.3626 | 13 | 9.1396e-06 | 0.00011881 | 3091 | 25736.1131 | 0.071755 | #N/A | #N/A
964 | SAN RAFAEL 110991742 | 42011109 | SAN RAFAEL 1109 | 2.3895 | 67 | 9.0186e-06 | 0.00060425 | 3092 | 25738.5026 | 0.07115 | #N/A | #N/A
5348 | EEL RIVER 11033820 | 192381103 | EEL RIVER 1103 | 0 | 115 | 8.9864e-06 | 0.0010334 | 3093 | 25738.5026 | 0.070117 | #N/A | #N/A
3020 | SARATOGA 1104209146 | 83371104 | SARATOGA 1104 | 3.0679 | 85 | 8.9692e-06 | 0.00076238 | 3094 | 25741.5705 | 0.069355 | #N/A | #N/A
10029 | MONTICELLO 11011780 | 43051101 | MONTICELLO 1101 | 0.071678 | 1 | 8.9608e-06 | 8.9608e-06 | 3095 | 25741.6422 | 0.069346 | #N/A | #N/A
10582 | OAKLAND X 1101328808 | 12541101 | OAKLAND X 1101 | 0.11589 | 1 | 8.9528e-06 | 8.9528e-06 | 3096 | 25741.7581 | 0.069337 | #N/A | #N/A
8839 | BIG BASIN 11026219 | 82841102 | BIG BASIN 1102 | 0.92519 | 11 | 8.7836e-06 | 9.662e-05 | 3097 | 25742.6832 | 0.06924 | #N/A | #N/A
2096 | CALISTOGA 1102184814 | 42711102 | CALISTOGA 1102 | 0.42402 | 20 | 8.707e-06 | 0.00017414 | 3098 | 25743.1073 | 0.069066 | 0.069066 | #N/A
10342 | FROGTOWN 1702832694 | 163451702 | FROGTOWN 1702 | 0.28686 | 5 | 8.7057e-06 | 4.3529e-05 | 3099 | 25743.3941 | 0.069022 | #N/A | #N/A
2914 | EUREKA E 110435934 | 192331104 | EUREKA E 1104 | 0.048733 | 46 | 8.6658e-06 | 0.00039863 | 3100 | 25743.4429 | 0.068624 | #N/A | #N/A
4896 | IGNACIO 1105490728 | 42481105 | IGNACIO 1105 | 0.649 | 11 | 8.6628e-06 | 9.5291e-05 | 3101 | 25744.0919 | 0.068529 | #N/A | #N/A
9315 | LAKEWOOD 2224798018 | 13532224 | LAKEWOOD 2224 | 0.90013 | 13 | 8.6422e-06 | 0.00011235 | 3102 | 25744.992 | 0.068416 | #N/A | #N/A
9391 | WATERSHED 0402CB | 24240402 | WATERSHED 0402 | 0.21316 | 11 | 8.6414e-06 | 9.5055e-05 | 3103 | 25745.2052 | 0.068321 | #N/A | #N/A
9903 | PACIFICA 1102894156 | 22811102 | PACIFICA 1102 | 0.38867 | 4 | 8.6111e-06 | 3.4445e-05 | 3104 | 25745.5938 | 0.068287 | #N/A | #N/A
7834 | GREENBRAE 1103718674 | 43091103 | GREENBRAE 1103 | 0.80908 | 16 | 8.6092e-06 | 0.00013775 | 3105 | 25746.4029 | 0.068149 | #N/A | #N/A
10810 | PLACERVILLE 1111610322 | 153081111 | PLACERVILLE 1111 | 0.13716 | 3 | 8.5935e-06 | 2.578e-05 | 3106 | 25746.5401 | 0.068123 | #N/A | #N/A
10497 | FORT ORD 21069658 | 182402106 | FORT ORD 2106 | 0.096962 | 3 | 8.4949e-06 | 2.5485e-05 | 3107 | 25746.637 | 0.068098 | #N/A | #N/A
5369 | OAKLAND K 1104CR206 | 12101104 | OAKLAND K 1104 | 1.7882 | 22 | 8.4479e-06 | 0.00018585 | 3108 | 25748.4252 | 0.067912 | #N/A | #N/A
6668 | PAUL SWEET 21075291 | 83252107 | PAUL SWEET 2107 | 0.031348 | 14 | 8.4226e-06 | 0.00011792 | 3109 | 25748.4565 | 0.067794 | #N/A | #N/A
4822 | CAMP EVERS 21035404 | 83622103 | CAMP EVERS 2103 | 2.7208 | 63 | 8.4149e-06 | 0.00053014 | 3110 | 25751.1774 | 0.067264 | #N/A | #N/A
10986 | RINCON 1101205854 | 43321101 | RINCON 1101 | 0.31393 | 5 | 8.3652e-06 | 4.1826e-05 | 3111 | 25751.4913 | 0.067222 | #N/A | #N/A
1364 | CAMP EVERS 21035402 | 83622103 | CAMP EVERS 2103 | 2.8564 | 87 | 8.3234e-06 | 0.00072413 | 3112 | 25754.3477 | 0.066498 | #N/A | #N/A
9661 | SARATOGA 1105431214 | 83371105 | SARATOGA 1105 | 0.31096 | 9 | 8.308e-06 | 7.4772e-05 | 3113 | 25754.6587 | 0.066423 | #N/A | #N/A
6999 | JESSUP 1102158468 | 103441102 | JESSUP 1102 | 0.69613 | 11 | 8.3063e-06 | 9.1369e-05 | 3114 | 25755.3548 | 0.066332 | #N/A | #N/A
7019 | FORT BRAGG A 1102816 | 42761102 | FORT BRAGG A 1102 | 2.4498 | 29 | 8.2407e-06 | 0.00023898 | 3115 | 25757.8046 | 0.066093 | #N/A | #N/A
9287 | SOBRANTE 1103N510R | 14671103 | SOBRANTE 1103 | 0.24969 | 15 | 8.2224e-06 | 0.00012334 | 3116 | 25758.0543 | 0.065969 | #N/A | #N/A
10537 | FROGTOWN 1702798032 | 163451702 | FROGTOWN 1702 | 0.15196 | 2 | 8.1969e-06 | 1.6394e-05 | 3117 | 25758.2062 | 0.065953 | #N/A | #N/A
7405 | HARRIS 11082062 | 192431108 | HARRIS 1108 | 1.5887 | 83 | 8.1613e-06 | 0.00067739 | 3118 | 25759.795 | 0.065276 | #N/A | #N/A
3886 | SAN RAFAEL 11081457 | 42011108 | SAN RAFAEL 1108 | 0.76406 | 9 | 8.1539e-06 | 7.3385e-05 | 3119 | 25760.559 | 0.065202 | #N/A | #N/A
9639 | IGNACIO 1105967039 | 42481105 | IGNACIO 1105 | 0.18205 | 3 | 8.139e-06 | 2.4417e-05 | 3120 | 25760.7411 | 0.065178 | #N/A | #N/A
10422 | OAKLAND J 1102CR102 | 12091102 | OAKLAND J 1102 | 0.1966 | 6 | 8.0835e-06 | 4.8501e-05 | 3121 | 25760.9377 | 0.065129 | #N/A | #N/A
10726 | CALISTOGA 1102960240 | 42711102 | CALISTOGA 1102 | 0.50732 | 5 | 8.0789e-06 | 4.0394e-05 | 3122 | 25761.445 | 0.065089 | #N/A | #N/A
9181 | MIWUK 1702531976 | 163661702 | MIWUK 1702 | 1.3067 | 17 | 8.0236e-06 | 0.0001364 | 3123 | 25762.7517 | 0.064952 | #N/A | #N/A
10385 | ALLEGHANY 11011101/2 | 152101101 | ALLEGHANY 1101 | 0.022986 | 1 | 8.0126e-06 | 8.0126e-06 | 3124 | 25762.7747 | 0.064944 | #N/A | #N/A
9316 | FORT BRAGG A 1103284356 | 42761103 | FORT BRAGG A 1103 | 0.13557 | 4 | 7.9902e-06 | 3.1961e-05 | 3125 | 25762.9103 | 0.064913 | #N/A | #N/A
10880 | OAKLAND X 1104CR101 | 12541104 | OAKLAND X 1104 | 0.017646 | 1 | 7.9011e-06 | 7.9011e-06 | 3126 | 25762.9279 | 0.064905 | #N/A | #N/A
4441 | OAKLAND X 1101CR224 | 12541101 | OAKLAND X 1101 | 0.40793 | 17 | 7.8938e-06 | 0.0001342 | 3127 | 25763.3358 | 0.06477 | #N/A | #N/A
10513 | OILFIELDS 1103441010 | 182391103 | OILFIELDS 1103 | 0.36823 | 4 | 7.8772e-06 | 3.1509e-05 | 3128 | 25763.7041 | 0.064739 | #N/A | #N/A
1793 | SAN RAFAEL 1109535284 | 42011109 | SAN RAFAEL 1109 | 0.0067505 | 9 | 7.8608e-06 | 7.0747e-05 | 3129 | 25763.7108 | 0.064668 | #N/A | #N/A
8925 | FRUITLAND 11418746 | 192311141 | FRUITLAND 1141 | 0.4013 | 8 | 7.8216e-06 | 6.2573e-05 | 3130 | 25764.1121 | 0.064606 | #N/A | #N/A
8734 | LOS GATOS 110160052 | 82021101 | LOS GATOS 1101 | 1.9696 | 28 | 7.8045e-06 | 0.00021853 | 3131 | 25766.0817 | 0.064387 | #N/A | #N/A
6798 | SAN CARLOS 110475210 | 24181104 | SAN CARLOS 1104 | 0.38467 | 6 | 7.7312e-06 | 4.6387e-05 | 3132 | 25766.4663 | 0.064341 | #N/A | #N/A
6381 | OAKLAND X 1106CR008 | 12541106 | OAKLAND X 1106 | 4.4615 | 65 | 7.7074e-06 | 0.00050098 | 3133 | 25770.9279 | 0.06384 | #N/A | #N/A
10638 | SAN RAFAEL 11092213 | 42011109 | SAN RAFAEL 1109 | 0.42875 | 6 | 7.6893e-06 | 4.6136e-05 | 3134 | 25771.3566 | 0.063794 | #N/A | #N/A
9009 | ALTO 1124553571 | 42031124 | ALTO 1124 | 0.1087 | 4 | 7.6617e-06 | 3.0647e-05 | 3135 | 25771.4653 | 0.063763 | #N/A | #N/A
1292 | EEL RIVER 1103CB | 192381103 | EEL RIVER 1103 | 0 | 374 | 7.6507e-06 | 0.0028614 | 3136 | 25771.4653 | 0.060902 | #N/A | #N/A
2486 | LOYOLA 110260082 | 82161102 | LOYOLA 1102 | 0 | 57 | 7.6477e-06 | 0.00043592 | 3137 | 25771.4653 | 0.060466 | #N/A | #N/A
9942 | BRUNSWICK 1104327226 | 152481104 | BRUNSWICK 1104 | 0.049461 | 2 | 7.6459e-06 | 1.5292e-05 | 3138 | 25771.5148 | 0.06045 | #N/A | #N/A
10778 | PIT NO 5 110190846 | 101321101 | PIT NO 5 1101 | 0.092731 | 2 | 7.6083e-06 | 1.5217e-05 | 3139 | 25771.6075 | 0.060435 | #N/A | #N/A
9691 | STELLING 1109787007 | 83481109 | STELLING 1109 | 0.19092 | 5 | 7.5915e-06 | 3.7958e-05 | 3140 | 25771.7984 | 0.060397 | #N/A | #N/A
1439 | TAR FLAT 0402CB | 163240402 | TAR FLAT 0402 | 0.7963 | 18 | 7.5882e-06 | 0.00013659 | 3141 | 25772.5947 | 0.060261 | #N/A | #N/A
4239 | TAR FLAT 0401CB | 163240401 | TAR FLAT 0401 | 3.4952 | 45 | 7.5759e-06 | 0.00034092 | 3142 | 25776.0899 | 0.05992 | #N/A | #N/A
6173 | OAKLAND X 1104645092 | 12541104 | OAKLAND X 1104 | 1.3857 | 16 | 7.5529e-06 | 0.00012085 | 3143 | 25777.4756 | 0.059799 | #N/A | #N/A
9734 | HIGHLANDS 110484640 | 43361104 | HIGHLANDS 1104 | 0.41053 | 14 | 7.5307e-06 | 0.00010543 | 3144 | 25777.8862 | 0.059693 | #N/A | #N/A
10502 | TRIDAM POWERHOUSE 2101CB | 168152101 | TRIDAM POWERHOUSE 2101 | 0.050339 | 3 | 7.4775e-06 | 2.2433e-05 | 3145 | 25777.9365 | 0.059671 | #N/A | #N/A
3266 | UKIAH 1113658899 | 42771113 | UKIAH 1113 | 0.58507 | 8 | 7.4661e-06 | 5.9729e-05 | 3146 | 25778.5216 | 0.059611 | #N/A | #N/A
10496 | FROGTOWN 1702814784 | 163451702 | FROGTOWN 1702 | 0.17406 | 3 | 7.4475e-06 | 2.2342e-05 | 3147 | 25778.6956 | 0.059589 | #N/A | #N/A
9921 | OAKLAND X 1106CR266 | 12541106 | OAKLAND X 1106 | 1.1819 | 8 | 7.421e-06 | 5.9368e-05 | 3148 | 25779.8775 | 0.05953 | #N/A | #N/A
7361 | SARATOGA 11076867 | 83371107 | SARATOGA 1107 | 0.61277 | 11 | 7.4136e-06 | 8.155e-05 | 3149 | 25780.4903 | 0.059448 | #N/A | #N/A
7276 | SAN CARLOS 11049052 | 24181104 | SAN CARLOS 1104 | 4.7995 | 65 | 7.4082e-06 | 0.00048153 | 3150 | 25785.2897 | 0.058966 | #N/A | #N/A
9123 | UKIAH 1114296894 | 42771114 | UKIAH 1114 | 0.17288 | 6 | 7.398e-06 | 4.4388e-05 | 3151 | 25785.4626 | 0.058922 | #N/A | #N/A
10484 | SANTA ROSA A 1111407286 | 42151111 | SANTA ROSA A 1111 | 0.06092 | 1 | 7.3466e-06 | 7.3466e-06 | 3152 | 25785.5235 | 0.058915 | #N/A | #N/A
6588 | HARRIS 1108705523 | 192431108 | HARRIS 1108 | 0.20008 | 11 | 7.293e-06 | 8.0224e-05 | 3153 | 25785.7236 | 0.058834 | #N/A | #N/A
3678 | RESEARCH 2102183888 | 14692102 | RESEARCH 2102 | 1.1802 | 43 | 7.2344e-06 | 0.00031108 | 3154 | 25786.9038 | 0.058523 | #N/A | #N/A
9265 | ROSSMOOR 1104892332 | 14161104 | ROSSMOOR 1104 | 0.25496 | 4 | 7.2035e-06 | 2.8814e-05 | 3155 | 25787.1588 | 0.058495 | #N/A | #N/A
5151 | EDES 1112CR312 | 13681112 | EDES 1112 | 3.6881 | 42 | 7.189e-06 | 0.00030194 | 3156 | 25790.8469 | 0.058193 | #N/A | #N/A
6055 | SILVERADO 2105191725 | 43432105 | SILVERADO 2105 | 0.34689 | 8 | 7.1671e-06 | 5.7337e-05 | 3157 | 25791.1938 | 0.058135 | #N/A | #N/A
8973 | DIAMOND SPRINGS 1103394169 | 152261103 | DIAMOND SPRINGS 1103 | 0.39906 | 7 | 7.1481e-06 | 5.0037e-05 | 3158 | 25791.5928 | 0.058085 | #N/A | #N/A
9966 | MONROE 2107380760 | 43302107 | MONROE 2107 | 0.65446 | 12 | 7.1451e-06 | 8.5741e-05 | 3159 | 25792.2473 | 0.058 | #N/A | #N/A
2463 | OAKLAND K 1103CR188 | 12101103 | OAKLAND K 1103 | 3.58 | 47 | 7.1432e-06 | 0.00033573 | 3160 | 25795.8273 | 0.057664 | #N/A | #N/A
7755 | HICKS 1116983580 | 83431116 | HICKS 1116 | 2.4602 | 33 | 7.1402e-06 | 0.00023563 | 3161 | 25798.2875 | 0.057428 | #N/A | #N/A
2292 | OAKLAND K 1104CR326 | 12101104 | OAKLAND K 1104 | 1.3045 | 17 | 7.0989e-06 | 0.00012068 | 3162 | 25799.592 | 0.057307 | #N/A | #N/A
10476 | SAN RAFAEL 1106618957 | 42011106 | SAN RAFAEL 1106 | 0.18715 | 4 | 7.0643e-06 | 2.8257e-05 | 3163 | 25799.7791 | 0.057279 | #N/A | #N/A
3538 | CORTINA 1101302192 | 63121101 | CORTINA 1101 | 0 | 79 | 7.0599e-06 | 0.00055773 | 3164 | 25799.7791 | 0.056721 | #N/A | #N/A
3533 | OAKLAND K 1104432850 | 12101104 | OAKLAND K 1104 | 1.2358 | 26 | 6.9884e-06 | 0.0001817 | 3165 | 25801.0149 | 0.05654 | #N/A | #N/A
9797 | DEL MONTE 21032204 | 182222103 | DEL MONTE 2103 | 0.36833 | 8 | 6.9782e-06 | 5.5825e-05 | 3166 | 25801.3832 | 0.056484 | #N/A | #N/A
10205 | BERKELEY F 1103813976 | 12061103 | BERKELEY F 1103 | 0.19409 | 4 | 6.9422e-06 | 2.7769e-05 | 3167 | 25801.5773 | 0.056456 | #N/A | #N/A
398 | ROSSMOOR 1104CB | 14161104 | ROSSMOOR 1104 | 0 | 150 | 6.9228e-06 | 0.0010384 | 3168 | 25801.5773 | 0.055418 | #N/A | #N/A
465 | MOLINO 1102111666 | 42571102 | MOLINO 1102 | 0.11349 | 13 | 6.9214e-06 | 8.9978e-05 | 3169 | 25801.6908 | 0.055328 | #N/A | #N/A
9817 | SUMMIT 11016627 | 152591101 | SUMMIT 1101 | 0.56581 | 8 | 6.9114e-06 | 5.5291e-05 | 3170 | 25802.2566 | 0.055273 | #N/A | #N/A
6657 | SAN RAFAEL 110168970 | 42011101 | SAN RAFAEL 1101 | 0.047002 | 44 | 6.892e-06 | 0.00030325 | 3171 | 25802.3036 | 0.054969 | #N/A | #N/A
8713 | GANSNER 1101489276 | 103021101 | GANSNER 1101 | 0.44978 | 9 | 6.8546e-06 | 6.1691e-05 | 3172 | 25802.7534 | 0.054908 | #N/A | #N/A
6405 | ROB ROY 210571630 | 83692105 | ROB ROY 2105 | 1.3562 | 26 | 6.8241e-06 | 0.00017743 | 3173 | 25804.1096 | 0.05473 | #N/A | #N/A
1284 | SARATOGA 1106LC22 | 83371106 | SARATOGA 1106 | 7.4822 | 114 | 6.8223e-06 | 0.00077774 | 3174 | 25811.5918 | 0.053952 | #N/A | #N/A
4762 | SAN RAFAEL 110668694 | 42011106 | SAN RAFAEL 1106 | 0 | 32 | 6.7736e-06 | 0.00021675 | 3175 | 25811.5918 | 0.053736 | #N/A | #N/A
9002 | PAUL SWEET 2102168368 | 83252102 | PAUL SWEET 2102 | 0.36697 | 8 | 6.7491e-06 | 5.3993e-05 | 3176 | 25811.9588 | 0.053682 | #N/A | #N/A
8371 | RINCON 1102782389 | 43321102 | RINCON 1102 | 0.36418 | 8 | 6.7151e-06 | 5.3721e-05 | 3177 | 25812.3229 | 0.053628 | #N/A | #N/A
7829 | UKIAH 111472990 | 42771114 | UKIAH 1114 | 0.73068 | 38 | 6.7147e-06 | 0.00025516 | 3178 | 25813.0536 | 0.053373 | #N/A | #N/A
4895 | SARATOGA 1103LC16 | 83371103 | SARATOGA 1103 | 4.2817 | 72 | 6.7061e-06 | 0.00048284 | 3179 | 25817.3353 | 0.05289 | #N/A | #N/A
2902 | WAYNE 0401954811 | 13810401 | WAYNE 0401 | 0.17582 | 9 | 6.7055e-06 | 6.0349e-05 | 3180 | 25817.5111 | 0.05283 | #N/A | #N/A
6002 | SAN RAFAEL 1105818262 | 42011105 | SAN RAFAEL 1105 | 0.18205 | 11 | 6.6573e-06 | 7.3231e-05 | 3181 | 25817.6932 | 0.052756 | #N/A | #N/A
9719 | PIT NO 5 11011614 | 101321101 | PIT NO 5 1101 | 1.8648 | 5 | 6.6513e-06 | 3.3257e-05 | 3182 | 25819.558 | 0.052723 | #N/A | #N/A
5122 | RIDGE 0401CB | 12840401 | RIDGE 0401 | 2.654 | 36 | 6.6432e-06 | 0.00023916 | 3183 | 25822.212 | 0.052484 | #N/A | #N/A
1193 | FORT BRAGG A 1102418 | 42761102 | FORT BRAGG A 1102 | 14.0083 | 178 | 6.6205e-06 | 0.0011785 | 3184 | 25836.2202 | 0.051305 | #N/A | #N/A
8138 | FRANKLIN 1101P138 | 13921101 | FRANKLIN 1101 | 1.404 | 15 | 6.5684e-06 | 9.8527e-05 | 3185 | 25837.6242 | 0.051207 | #N/A | #N/A
11032 | HIGHLANDS 1101CB | 43361101 | HIGHLANDS 1101 | 0.026415 | 1 | 6.536e-06 | 6.536e-06 | 3186 | 25837.6506 | 0.0512 | #N/A | #N/A
3671 | CAMP EVERS 2104CB | 83622104 | CAMP EVERS 2104 | 0.39105 | 71 | 6.5265e-06 | 0.00046338 | 3187 | 25838.0417 | 0.050737 | #N/A | #N/A
8113 | WOODSIDE 110411555 | 24251104 | WOODSIDE 1104 | 0.85767 | 11 | 6.5136e-06 | 7.165e-05 | 3188 | 25838.8994 | 0.050665 | #N/A | #N/A
8611 | CAROLANDS 04018888 | 24060401 | CAROLANDS 0401 | 0 | 25 | 6.5082e-06 | 0.0001627 | 3189 | 25838.8994 | 0.050503 | #N/A | #N/A
10705 | CLOVERDALE 1102801904 | 42821102 | CLOVERDALE 1102 | 0.013914 | 1 | 6.5066e-06 | 6.5066e-06 | 3190 | 25838.9133 | 0.050496 | #N/A | #N/A
7620 | CASTRO VALLEY 1110MR341 | 14091110 | CASTRO VALLEY 1110 | 0.25931 | 11 | 6.5027e-06 | 7.1529e-05 | 3191 | 25839.1726 | 0.050425 | #N/A | #N/A
6399 | ROB ROY 21049973 | 83692104 | ROB ROY 2104 | 0.57273 | 7 | 6.4944e-06 | 4.5461e-05 | 3192 | 25839.7453 | 0.050379 | #N/A | #N/A
4710 | VIEJO 220255787 | 182852202 | VIEJO 2202 | 0.036622 | 1 | 6.491e-06 | 6.491e-06 | 3193 | 25839.7819 | 0.050373 | #N/A | #N/A
3931 | LAS AROMAS 04013342 | 13600401 | LAS AROMAS 0401 | 2.2944 | 30 | 6.402e-06 | 0.00019206 | 3194 | 25842.0764 | 0.050181 | #N/A | #N/A
738 | SAN RAFAEL 1104CB | 42011104 | SAN RAFAEL 1104 | 3.4557 | 140 | 6.3852e-06 | 0.00089393 | 3195 | 25845.5321 | 0.049287 | #N/A | #N/A
9201 | HICKS 1116583284 | 83431116 | HICKS 1116 | 0.14703 | 4 | 6.3368e-06 | 2.5347e-05 | 3196 | 25845.6791 | 0.049261 | #N/A | #N/A
7050 | EAST QUINCY 1101678650 | 102551101 | EAST QUINCY 1101 | 1.1243 | 14 | 6.2788e-06 | 8.7903e-05 | 3197 | 25846.8034 | 0.049173 | #N/A | #N/A
9107 | OAKLAND K 1103CR422 | 12101103 | OAKLAND K 1103 | 2.0126 | 24 | 6.2703e-06 | 0.00015049 | 3198 | 25848.816 | 0.049023 | #N/A | #N/A
2296 | LAURELES 11112028 | 182371111 | LAURELES 1111 | 8.7309 | 107 | 6.2585e-06 | 0.00066966 | 3199 | 25857.5469 | 0.048353 | #N/A | #N/A
4668 | KONOCTI 11084041 | 43311108 | KONOCTI 1108 | 1.3514 | 54 | 6.2484e-06 | 0.00033741 | 3200 | 25858.8984 | 0.048016 | #N/A | #N/A
4517 | SILVERADO 2105CB | 43432105 | SILVERADO 2105 | 0.62873 | 66 | 6.2313e-06 | 0.00041127 | 3201 | 25859.5271 | 0.047605 | #N/A | #N/A
1407 | SAN RAFAEL 11061230 | 42011106 | SAN RAFAEL 1106 | 1.0861 | 57 | 6.2233e-06 | 0.00035473 | 3202 | 25860.6132 | 0.04725 | #N/A | #N/A
7332 | LOS GATOS 1101184035 | 82021101 | LOS GATOS 1101 | 0.56304 | 9 | 6.0721e-06 | 5.4649e-05 | 3203 | 25861.1763 | 0.047195 | #N/A | #N/A
10579 | SAN CARLOS 11049048 | 24181104 | SAN CARLOS 1104 | 0.015283 | 1 | 6.06e-06 | 6.06e-06 | 3204 | 25861.1916 | 0.047189 | #N/A | #N/A
2032 | LUCERNE 11031663 | 43351103 | LUCERNE 1103 | 1.2105 | 17 | 6.0525e-06 | 0.00010289 | 3205 | 25862.402 | 0.047086 | #N/A | #N/A
9700 | SAN RAMON 2103MR279 | 14232103 | SAN RAMON 2103 | 0.0028415 | 5 | 6.0521e-06 | 3.0261e-05 | 3206 | 25862.4049 | 0.047056 | #N/A | #N/A
5325 | SAN RAFAEL 1105534 | 42011105 | SAN RAFAEL 1105 | 0.97555 | 22 | 6.0384e-06 | 0.00013284 | 3207 | 25863.3804 | 0.046923 | #N/A | #N/A
8122 | HATTON 1101CB | 182291101 | HATTON 1101 | 1.5858 | 22 | 6.0227e-06 | 0.0001325 | 3208 | 25864.9662 | 0.046791 | #N/A | #N/A
6886 | ALTO 1124526955 | 42031124 | ALTO 1124 | 0.44373 | 6 | 6.0133e-06 | 3.608e-05 | 3209 | 25865.41 | 0.046755 | #N/A | #N/A
5909 | CAMP EVERS 210392582 | 83622103 | CAMP EVERS 2103 | 0.15274 | 41 | 5.9997e-06 | 0.00024599 | 3210 | 25865.5627 | 0.046509 | #N/A | #N/A
6632 | SAN RAFAEL 1106588020 | 42011106 | SAN RAFAEL 1106 | 0.23943 | 19 | 5.9904e-06 | 0.00011382 | 3211 | 25865.8021 | 0.046395 | #N/A | #N/A
763 | LOS GATOS 1108LB86 | 82021108 | LOS GATOS 1108 | 4.5188 | 69 | 5.9458e-06 | 0.00041026 | 3212 | 25870.321 | 0.045985 | #N/A | #N/A
10570 | EL CERRITO G 1105BR164 | 12501105 | EL CERRITO G 1105 | 0.05692 | 2 | 5.9372e-06 | 1.1874e-05 | 3213 | 25870.3779 | 0.045973 | #N/A | #N/A
9932 | ALTO 1125291744 | 42031125 | ALTO 1125 | 0.12168 | 3 | 5.9276e-06 | 1.7783e-05 | 3214 | 25870.4996 | 0.045955 | #N/A | #N/A
8178 | DOLAN ROAD 1101156268 | 182381101 | DOLAN ROAD 1101 | 0.032781 | 31 | 5.914e-06 | 0.00018333 | 3215 | 25870.5323 | 0.045772 | #N/A | #N/A
6600 | VIEJO 2202CB | 182852202 | VIEJO 2202 | 2.1443 | 23 | 5.9077e-06 | 0.00013588 | 3216 | 25872.6767 | 0.045636 | #N/A | #N/A
4067 | LAS AROMAS 0401LA401R | 13600401 | LAS AROMAS 0401 | 3.0804 | 55 | 5.9068e-06 | 0.00032487 | 3217 | 25875.7571 | 0.045311 | #N/A | #N/A
807 | RESEARCH 210263274 | 14692102 | RESEARCH 2102 | 0.046218 | 119 | 5.8646e-06 | 0.00069789 | 3218 | 25875.8033 | 0.044613 | #N/A | #N/A
10104 | LAKEWOOD 1102964292 | 13531102 | LAKEWOOD 1102 | 0.079652 | 2 | 5.8569e-06 | 1.1714e-05 | 3219 | 25875.8829 | 0.044601 | #N/A | #N/A
8987 | ROSSMOOR 110181770 | 14161101 | ROSSMOOR 1101 | 0.068628 | 21 | 5.8019e-06 | 0.00012184 | 3220 | 25875.9516 | 0.044479 | #N/A | #N/A
9943 | FRANKLIN 1104P136 | 13921104 | FRANKLIN 1104 | 4.9295 | 43 | 5.7997e-06 | 0.00024939 | 3221 | 25880.881 | 0.04423 | #N/A | #N/A
9679 | DOBBINS 1101CB | 153741101 | DOBBINS 1101 | 0.67066 | 8 | 5.7961e-06 | 4.6369e-05 | 3222 | 25881.5517 | 0.044184 | #N/A | #N/A
734 | SILVERADO 21051308 | 43432105 | SILVERADO 2105 | 0.15225 | 60 | 5.7874e-06 | 0.00034724 | 3223 | 25881.7039 | 0.043836 | #N/A | #N/A
5907 | ORINDA 0401401/2 LR | 12350401 | ORINDA 0401 | 0.098352 | 4 | 5.7731e-06 | 2.3093e-05 | 3224 | 25881.8023 | 0.043813 | #N/A | #N/A
648 | KONOCTI 11084039 | 43311108 | KONOCTI 1108 | 1.8946 | 32 | 5.7609e-06 | 0.00018435 | 3225 | 25883.6969 | 0.043629 | #N/A | #N/A
5547 | KONOCTI 11084037 | 43311108 | KONOCTI 1108 | 1.1437 | 22 | 5.7543e-06 | 0.0001266 | 3226 | 25884.8406 | 0.043502 | #N/A | #N/A
3274 | RACETRACK 170310850 | 163761703 | RACETRACK 1703 | 0.61832 | 28 | 5.704e-06 | 0.00015971 | 3227 | 25885.4589 | 0.043343 | #N/A | #N/A
5740 | SUMMIT 110148636 | 152591101 | SUMMIT 1101 | 0.053712 | 38 | 5.6861e-06 | 0.00021607 | 3228 | 25885.5127 | 0.043127 | #N/A | #N/A
8762 | VASONA 1102944560 | 83771102 | VASONA 1102 | 0.17566 | 9 | 5.6635e-06 | 5.0971e-05 | 3229 | 25885.6883 | 0.043076 | #N/A | #N/A
5538 | BERKELEY F 1103162952 | 12061103 | BERKELEY F 1103 | 1.7693 | 25 | 5.6583e-06 | 0.00014146 | 3230 | 25887.4576 | 0.042934 | #N/A | #N/A
319 | DUNBAR 1103725292 | 43071103 | DUNBAR 1103 | 0.21105 | 13 | 5.658e-06 | 7.3554e-05 | 3231 | 25887.6686 | 0.042861 | #N/A | #N/A
5356 | SOBRANTE 110142914 | 14671101 | SOBRANTE 1101 | 0.4137 | 51 | 5.6577e-06 | 0.00028854 | 3232 | 25888.0823 | 0.042572 | #N/A | #N/A
4656 | OAKLAND K 1104CR208 | 12101104 | OAKLAND K 1104 | 2.421 | 29 | 5.6453e-06 | 0.00016371 | 3233 | 25890.5034 | 0.042408 | #N/A | #N/A
1498 | SAN RAFAEL 1101189400 | 42011101 | SAN RAFAEL 1101 | 2.7637 | 45 | 5.6305e-06 | 0.00025337 | 3234 | 25893.267 | 0.042155 | #N/A | #N/A
9302 | NEWBURG 1131987158 | 192151131 | NEWBURG 1131 | 0.24716 | 2 | 5.6215e-06 | 1.1243e-05 | 3235 | 25893.5142 | 0.042144 | #N/A | #N/A
1260 | PALO SECO 0401CB | 13180401 | PALO SECO 0401 | 4.745 | 55 | 5.6154e-06 | 0.00030885 | 3236 | 25898.2592 | 0.041835 | #N/A | #N/A
7087 | OAKLAND K 1101CR170 | 12101101 | OAKLAND K 1101 | 1.251 | 17 | 5.5684e-06 | 9.4663e-05 | 3237 | 25899.5102 | 0.04174 | #N/A | #N/A
9325 | TASSAJARA 2108189700 | 14662108 | TASSAJARA 2108 | 0.19063 | 22 | 5.5512e-06 | 0.00012213 | 3238 | 25899.7009 | 0.041618 | #N/A | #N/A
8529 | ROSSMOOR 110479146 | 14161104 | ROSSMOOR 1104 | 0.05321 | 28 | 5.451e-06 | 0.00015263 | 3239 | 25899.7541 | 0.041465 | #N/A | #N/A
5159 | PAUL SWEET 2109634576 | 83252109 | PAUL SWEET 2109 | 1.8241 | 29 | 5.4462e-06 | 0.00015794 | 3240 | 25901.5782 | 0.041308 | #N/A | #N/A
176 | TASSAJARA 2108D520R | 14662108 | TASSAJARA 2108 | 0 | 50 | 5.4455e-06 | 0.00027228 | 3241 | 25901.5782 | 0.041035 | #N/A | #N/A
2934 | LAKEWOOD 210769586 | 13532107 | LAKEWOOD 2107 | 0.42817 | 80 | 5.4423e-06 | 0.00043538 | 3242 | 25902.0064 | 0.0406 | #N/A | #N/A
2160 | HIGHLANDS 1104CB | 43361104 | HIGHLANDS 1104 | 4.7619 | 102 | 5.4342e-06 | 0.00055429 | 3243 | 25906.7683 | 0.040046 | #N/A | #N/A
7487 | GANSNER 1101174072 | 103021101 | GANSNER 1101 | 0.10734 | 3 | 5.3939e-06 | 1.6182e-05 | 3244 | 25906.8756 | 0.040029 | #N/A | #N/A
10550 | SANTA ROSA A 1104834094 | 42151104 | SANTA ROSA A 1104 | 0.096633 | 3 | 5.3913e-06 | 1.6174e-05 | 3245 | 25906.9723 | 0.040013 | #N/A | #N/A
6137 | CAROLANDS 04049024 | 24060404 | CAROLANDS 0404 | 3.5095 | 62 | 5.3873e-06 | 0.00033401 | 3246 | 25910.4818 | 0.039679 | #N/A | #N/A
8307 | SAN RAFAEL 11042235 | 42011104 | SAN RAFAEL 1104 | 0.18438 | 10 | 5.3477e-06 | 5.3477e-05 | 3247 | 25910.6662 | 0.039626 | #N/A | #N/A
4970 | CASTRO VALLEY 1110264914 | 14091110 | CASTRO VALLEY 1110 | 0.868 | 14 | 5.3219e-06 | 7.4507e-05 | 3248 | 25911.5342 | 0.039551 | #N/A | #N/A
6336 | SAN RAFAEL 1101310 | 42011101 | SAN RAFAEL 1101 | 0.19876 | 48 | 5.3143e-06 | 0.00025509 | 3249 | 25911.7329 | 0.039296 | #N/A | #N/A
5625 | LAURELES 11116617 | 182371111 | LAURELES 1111 | 1.8171 | 13 | 5.304e-06 | 6.8952e-05 | 3250 | 25913.55 | 0.039227 | #N/A | #N/A
4819 | GANSNER 1101590690 | 103021101 | GANSNER 1101 | 0.063412 | 4 | 5.2923e-06 | 2.1169e-05 | 3251 | 25913.6134 | 0.039206 | #N/A | #N/A
3357 | TASSAJARA 210812712 | 14662108 | TASSAJARA 2108 | 0.76312 | 46 | 5.2813e-06 | 0.00024294 | 3252 | 25914.3765 | 0.038963 | #N/A | #N/A
4164 | ELK 11014628 | 42981101 | ELK 1101 | 2.4709 | 54 | 5.2551e-06 | 0.00028378 | 3253 | 25916.8475 | 0.038679 | #N/A | #N/A
5329 | ROSSMOOR 1106L522R | 14161106 | ROSSMOOR 1106 | 1.8843 | 56 | 5.255e-06 | 0.00029428 | 3254 | 25918.7318 | 0.038385 | #N/A | #N/A
10811 | STAFFORD 1101803535 | 43201101 | STAFFORD 1101 | 0.16314 | 3 | 5.2193e-06 | 1.5658e-05 | 3255 | 25918.8949 | 0.038369 | #N/A | #N/A
7133 | DEL MONTE 21032000 | 182222103 | DEL MONTE 2103 | 9.0089 | 101 | 5.2097e-06 | 0.00052618 | 3256 | 25927.9038 | 0.037843 | #N/A | #N/A
5982 | SAN RAFAEL 1107434 | 42011107 | SAN RAFAEL 1107 | 0.030591 | 16 | 5.2024e-06 | 8.3238e-05 | 3257 | 25927.9344 | 0.03776 | #N/A | #N/A
7562 | IGNACIO 1105784032 | 42481105 | IGNACIO 1105 | 0.53682 | 11 | 5.1906e-06 | 5.7096e-05 | 3258 | 25928.4712 | 0.037703 | #N/A | #N/A
4422 | ROSSMOOR 1106CB | 14161106 | ROSSMOOR 1106 | 1.8254 | 60 | 5.1594e-06 | 0.00030957 | 3259 | 25930.2967 | 0.037393 | #N/A | #N/A
788 | OAKLAND K 1104CR210 | 12101104 | OAKLAND K 1104 | 2.8257 | 35 | 5.1591e-06 | 0.00018057 | 3260 | 25933.1224 | 0.037213 | #N/A | #N/A
5398 | HARTLEY 1101471 | 43211101 | HARTLEY 1101 | 0 | 16 | 5.1543e-06 | 8.2468e-05 | 3261 | 25933.1224 | 0.03713 | #N/A | #N/A
3021 | SAN RAFAEL 1101494 | 42011101 | SAN RAFAEL 1101 | 5.6152 | 114 | 5.1065e-06 | 0.00058215 | 3262 | 25938.7376 | 0.036548 | #N/A | #N/A
2946 | WOODSIDE 11049116 | 24251104 | WOODSIDE 1104 | 0.83032 | 53 | 5.0499e-06 | 0.00026765 | 3263 | 25939.5679 | 0.03628 | #N/A | #N/A
8964 | MARIPOSA 2102527766 | 254452102 | MARIPOSA 2102 | 0.041619 | 1 | 5.0408e-06 | 5.0408e-06 | 3264 | 25939.6096 | 0.036275 | #N/A | #N/A
8147 | LAS GALLINAS A 1105648439 | 42991105 | LAS GALLINAS A 1105 | 0.0067816 | 3 | 5.033e-06 | 1.5099e-05 | 3265 | 25939.6163 | 0.03626 | #N/A | #N/A
6797 | EMERALD LAKE 04028858 | 24080402 | EMERALD LAKE 0402 | 1.9103 | 27 | 4.9935e-06 | 0.00013482 | 3266 | 25941.5266 | 0.036125 | #N/A | #N/A
8050 | BIG RIVER 11015065 | 43081101 | BIG RIVER 1101 | 2.2023 | 27 | 4.9756e-06 | 0.00013434 | 3267 | 25943.729 | 0.035991 | #N/A | #N/A
6040 | RACETRACK 17032553 | 163761703 | RACETRACK 1703 | 0.96229 | 32 | 4.9535e-06 | 0.00015851 | 3268 | 25944.6912 | 0.035833 | #N/A | #N/A
4959 | VALLEY VIEW 1105305072 | 14341105 | VALLEY VIEW 1105 | 3.1349 | 45 | 4.9532e-06 | 0.0002229 | 3269 | 25947.8261 | 0.03561 | #N/A | #N/A
1675 | CASTRO VALLEY 1111227862 | 14091111 | CASTRO VALLEY 1111 | 0.19847 | 26 | 4.952e-06 | 0.00012875 | 3270 | 25948.0246 | 0.035481 | #N/A | #N/A
9676 | PACIFICA 1103885952 | 22811103 | PACIFICA 1103 | 0.17616 | 4 | 4.9074e-06 | 1.963e-05 | 3271 | 25948.2008 | 0.035461 | #N/A | #N/A
8421 | EL CERRITO G 1112779030 | 12501112 | EL CERRITO G 1112 | 0.51428 | 11 | 4.881e-06 | 5.3691e-05 | 3272 | 25948.715 | 0.035408 | #N/A | #N/A
2317 | VACAVILLE 1112CB | 63601112 | VACAVILLE 1112 | 0.23531 | 52 | 4.847e-06 | 0.00025204 | 3273 | 25948.9504 | 0.035156 | #N/A | #N/A
2187 | NEWBURG 1131CB | 192151131 | NEWBURG 1131 | 0.15993 | 91 | 4.8414e-06 | 0.00044057 | 3274 | 25949.1103 | 0.034715 | #N/A | #N/A
8107 | EMERALD LAKE 0402CB | 24080402 | EMERALD LAKE 0402 | 1.8968 | 23 | 4.8042e-06 | 0.0001105 | 3275 | 25951.0071 | 0.034605 | #N/A | #N/A
1133 | SAN CARLOS 1103586832 | 24181103 | SAN CARLOS 1103 | 3.8195 | 53 | 4.7995e-06 | 0.00025437 | 3276 | 25954.8267 | 0.03435 | #N/A | #N/A
9839 | SAN RAFAEL 11073323 | 42011107 | SAN RAFAEL 1107 | 0.13345 | 2 | 4.7655e-06 | 9.5309e-06 | 3277 | 25954.9601 | 0.034341 | #N/A | #N/A
3598 | PAUL SWEET 210210290 | 83252102 | PAUL SWEET 2102 | 0.0028415 | 75 | 4.7388e-06 | 0.00035541 | 3278 | 25954.963 | 0.033985 | #N/A | #N/A
4237 | PAUL SWEET 2109687295 | 83252109 | PAUL SWEET 2109 | 0.92949 | 14 | 4.7113e-06 | 6.5958e-05 | 3279 | 25955.8925 | 0.033919 | #N/A | #N/A
4104 | GREENBRAE 1103CB | 43091103 | GREENBRAE 1103 | 0 | 61 | 4.6915e-06 | 0.00028618 | 3280 | 25955.8925 | 0.033633 | #N/A | #N/A
9040 | SAN RAFAEL 1101CB | 42011101 | SAN RAFAEL 1101 | 0 | 17 | 4.6868e-06 | 7.9676e-05 | 3281 | 25955.8925 | 0.033553 | #N/A | #N/A
9787 | ATASCADERO 1103395936 | 182541103 | ATASCADERO 1103 | 0.42621 | 6 | 4.6656e-06 | 2.7994e-05 | 3282 | 25956.3187 | 0.033525 | #N/A | #N/A
3209 | ROB ROY 210512474 | 83692105 | ROB ROY 2105 | 3.4104 | 105 | 4.6505e-06 | 0.00048831 | 3283 | 25959.729 | 0.033037 | 0.033037 | #N/A
10084 | SAN RAFAEL 1106307651 | 42011106 | SAN RAFAEL 1106 | 0.10506 | 4 | 4.6267e-06 | 1.8507e-05 | 3284 | 25959.8341 | 0.033019 | #N/A | #N/A
8574 | BIG RIVER 1101262924 | 43081101 | BIG RIVER 1101 | 1.8846 | 30 | 4.6224e-06 | 0.00013867 | 3285 | 25961.7187 | 0.03288 | #N/A | #N/A
9375 | BIG MEADOWS 2101439 | 102812101 | BIG MEADOWS 2101 | 0.66455 | 12 | 4.6178e-06 | 5.5413e-05 | 3286 | 25962.3832 | 0.032825 | #N/A | #N/A
10457 | ALTO 1124319320 | 42031124 | ALTO 1124 | 0.1309 | 3 | 4.6148e-06 | 1.3844e-05 | 3287 | 25962.5141 | 0.032811 | #N/A | #N/A
9137 | BERKELEY F 1103620294 | 12061103 | BERKELEY F 1103 | 0.15517 | 4 | 4.6109e-06 | 1.8443e-05 | 3288 | 25962.6693 | 0.032792 | #N/A | #N/A
10199 | SALT SPRINGS 21023116 | 163692102 | SALT SPRINGS 2102 | 0.054163 | 2 | 4.5851e-06 | 9.1703e-06 | 3289 | 25962.7235 | 0.032783 | #N/A | #N/A
7887 | EAST QUINCY 1101782320 | 102551101 | EAST QUINCY 1101 | 0.2115 | 5 | 4.5524e-06 | 2.2762e-05 | 3290 | 25962.935 | 0.03276 | #N/A | #N/A
5305 | SAN RAFAEL 1105CB | 42011105 | SAN RAFAEL 1105 | 0 | 124 | 4.5504e-06 | 0.00056425 | 3291 | 25962.935 | 0.032196 | #N/A | #N/A
8451 | GUALALA 11124431 | 42841112 | GUALALA 1112 | 1.4093 | 16 | 4.548e-06 | 7.2768e-05 | 3292 | 25964.3443 | 0.032123 | #N/A | #N/A
2628 | EAST QUINCY 1101186938 | 102551101 | EAST QUINCY 1101 | 1.6607 | 41 | 4.5458e-06 | 0.00018638 | 3293 | 25966.005 | 0.031937 | #N/A | #N/A
8531 | VALLEY VIEW 1106602871 | 14341106 | VALLEY VIEW 1106 | 0.82315 | 14 | 4.5365e-06 | 6.3511e-05 | 3294 | 25966.8282 | 0.031873 | #N/A | #N/A
6262 | HIGHLANDS 110448262 | 43361104 | HIGHLANDS 1104 | 6.1995 | 74 | 4.5315e-06 | 0.00033533 | 3295 | 25973.0277 | 0.031538 | #N/A | #N/A
3513 | FLORENCE 0401CR220 | 12690401 | FLORENCE 0401 | 0.20224 | 19 | 4.51e-06 | 8.5689e-05 | 3296 | 25973.2299 | 0.031452 | #N/A | #N/A
5570 | SAN CARLOS 11048942 | 24181104 | SAN CARLOS 1104 | 2.118 | 35 | 4.5084e-06 | 0.00015779 | 3297 | 25975.3479 | 0.031295 | #N/A | #N/A
5867 | ARLINGTON 0401404226 | 13700401 | ARLINGTON 0401 | 0.87233 | 15 | 4.4777e-06 | 6.7165e-05 | 3298 | 25976.2203 | 0.031227 | #N/A | #N/A
1380 | HARRIS 11084674 | 192431108 | HARRIS 1108 | 0.045245 | 85 | 4.4584e-06 | 0.00037897 | 3299 | 25976.2655 | 0.030848 | #N/A | #N/A
7856 | FORT BRAGG A 1102CB | 42761102 | FORT BRAGG A 1102 | 2.234 | 73 | 4.4533e-06 | 0.00032509 | 3300 | 25978.4995 | 0.030523 | #N/A | #N/A
7134 | DEL MONTE 2103617344 | 182222103 | DEL MONTE 2103 | 1.8348 | 34 | 4.4076e-06 | 0.00014986 | 3301 | 25980.3342 | 0.030373 | #N/A | #N/A
3773 | RINCON 1104CB | 43321104 | RINCON 1104 | 0.56024 | 34 | 4.3928e-06 | 0.00014935 | 3302 | 25980.8945 | 0.030224 | 0.030224 | #N/A
7255 | VIEJO 2203CB | 182852203 | VIEJO 2203 | 2.9383 | 42 | 4.392e-06 | 0.00018447 | 3303 | 25983.8328 | 0.03004 | #N/A | #N/A
1976 | LAURELES 111268454 | 182371112 | LAURELES 1112 | 8.4458 | 142 | 4.3912e-06 | 0.00062355 | 3304 | 25992.2786 | 0.029416 | #N/A | #N/A
1047 | DOLAN ROAD 110122158 | 182381101 | DOLAN ROAD 1101 | 0.11487 | 119 | 4.3836e-06 | 0.00052165 | 3305 | 25992.3934 | 0.028894 | #N/A | #N/A
4984 | PAUL SWEET 210212850 | 83252102 | PAUL SWEET 2102 | 0.66094 | 52 | 4.3733e-06 | 0.00022741 | 3306 | 25993.0544 | 0.028667 | #N/A | #N/A
10216 | GUALALA 1111498 | 42841111 | GUALALA 1111 | 2.8569 | 18 | 4.3648e-06 | 7.8567e-05 | 3307 | 25995.9113 | 0.028588 | #N/A | #N/A
5466 | WEST POINT 11025357 | 163201102 | WEST POINT 1102 | 3.3572 | 37 | 4.3621e-06 | 0.0001614 | 3308 | 25999.2685 | 0.028427 | #N/A | #N/A
5373 | VIEJO 22019490 | 182852201 | VIEJO 2201 | 1.2455 | 21 | 4.3539e-06 | 9.1432e-05 | 3309 | 26000.514 | 0.028336 | #N/A | #N/A
3074 | GANSNER 1101480328 | 103021101 | GANSNER 1101 | 0.29358 | 7 | 4.3254e-06 | 3.0278e-05 | 3310 | 26000.8076 | 0.028305 | #N/A | #N/A
2211 | DEL MONTE 21032654 | 182222103 | DEL MONTE 2103 | 1.8419 | 23 | 4.3113e-06 | 9.916e-05 | 3311 | 26002.6495 | 0.028206 | #N/A | #N/A
8914 | CLAYTON 2217CB | 12022217 | CLAYTON 2217 | 0.23231 | 8 | 4.2861e-06 | 3.4288e-05 | 3312 | 26002.8818 | 0.028172 | #N/A | #N/A
9870 | PUEBLO 2103253312 | 43292103 | PUEBLO 2103 | 0.42436 | 2 | 4.2859e-06 | 8.5718e-06 | 3313 | 26003.3061 | 0.028163 | #N/A | #N/A
10448 | DOLAN ROAD 1101173702 | 182381101 | DOLAN ROAD 1101 | 0.053872 | 3 | 4.2778e-06 | 1.2834e-05 | 3314 | 26003.36 | 0.028151 | #N/A | #N/A
7265 | ALTO 112265474 | 42031122 | ALTO 1122 | 2.3852 | 47 | 4.2638e-06 | 0.0002004 | 3315 | 26005.7452 | 0.02795 | #N/A | #N/A
6511 | PACIFICA 1103218962 | 22811103 | PACIFICA 1103 | 0.053658 | 2 | 4.2591e-06 | 8.5182e-06 | 3316 | 26005.7988 | 0.027942 | #N/A | #N/A
10670 | VACAVILLE 1111772224 | 63601111 | VACAVILLE 1111 | 0.057152 | 2 | 4.2158e-06 | 8.4316e-06 | 3317 | 26005.856 | 0.027933 | #N/A | #N/A
5386 | CAROLANDS 040484797 | 24060404 | CAROLANDS 0404 | 0.041454 | 21 | 4.2155e-06 | 8.8525e-05 | 3318 | 26005.8974 | 0.027845 | #N/A | #N/A
1724 | LAURELES 1112CB | 182371112 | LAURELES 1112 | 0.30651 | 38 | 4.2137e-06 | 0.00016012 | 3319 | 26006.204 | 0.027685 | #N/A | #N/A
1512 | ATASCADERO 1102CB | 182541102 | ATASCADERO 1102 | 0 | 67 | 4.207e-06 | 0.00028187 | 3320 | 26006.204 | 0.027403 | #N/A | #N/A
557 | GREENBRAE 11021254 | 43091102 | GREENBRAE 1102 | 5.991 | 130 | 4.1869e-06 | 0.0005443 | 3321 | 26012.195 | 0.026858 | #N/A | #N/A
9628 | SAN CARLOS 110436864 | 24181104 | SAN CARLOS 1104 | 0.55297 | 10 | 4.1763e-06 | 4.1763e-05 | 3322 | 26012.748 | 0.026817 | #N/A | #N/A
7091 | HATTON 11029642 | 182291102 | HATTON 1102 | 1.197 | 18 | 4.1709e-06 | 7.5077e-05 | 3323 | 26013.9449 | 0.026742 | #N/A | #N/A
757 | LAKEWOOD 1102CB | 13531102 | LAKEWOOD 1102 | 0.014663 | 121 | 4.1691e-06 | 0.00050446 | 3324 | 26013.9596 | 0.026237 | #N/A | #N/A
10987 | ECHO SUMMIT 1101CB | 158031101 | ECHO SUMMIT 1101 | 0.030563 | 1 | 4.1622e-06 | 4.1622e-06 | 3325 | 26013.9901 | 0.026233 | #N/A | #N/A
9358 | PACIFICA 1102267868 | 22811102 | PACIFICA 1102 | 0.84745 | 13 | 4.157e-06 | 5.4041e-05 | 3326 | 26014.8376 | 0.026179 | #N/A | #N/A
5985 | BERESFORD 04039154 | 24040403 | BERESFORD 0403 | 4.2117 | 95 | 4.1518e-06 | 0.00039442 | 3327 | 26019.0493 | 0.025784 | #N/A | #N/A
7732 | BIG MEADOWS 21012510 | 102812101 | BIG MEADOWS 2101 | 7.9419 | 22 | 4.1333e-06 | 9.0933e-05 | 3328 | 26026.9912 | 0.025694 | #N/A | #N/A
3692 | LAS GALLINAS A 1107554 | 42991107 | LAS GALLINAS A 1107 | 0.032931 | 35 | 4.1303e-06 | 0.00014456 | 3329 | 26027.0241 | 0.025549 | #N/A | #N/A
7653 | WOOD 0401265211 | 13380401 | WOOD 0401 | 0.14802 | 4 | 4.1276e-06 | 1.651e-05 | 3330 | 26027.1722 | 0.025532 | #N/A | #N/A
7212 | VIEJO 2201CB | 182852201 | VIEJO 2201 | 5.0859 | 67 | 4.1068e-06 | 0.00027516 | 3331 | 26032.2581 | 0.025257 | #N/A | #N/A
4015 | DOLAN ROAD 11013012 | 182381101 | DOLAN ROAD 1101 | 0.18766 | 160 | 4.0749e-06 | 0.00065198 | 3332 | 26032.4458 | 0.024605 | #N/A | #N/A
6661 | HICKS 2103XR248 | 83432103 | HICKS 2103 | 0 | 22 | 4.0743e-06 | 8.9634e-05 | 3333 | 26032.4458 | 0.024516 | #N/A | #N/A
9871 | SARATOGA 1103709451 | 83371103 | SARATOGA 1103 | 0.18799 | 5 | 4.0301e-06 | 2.0151e-05 | 3334 | 26032.6337 | 0.024496 | #N/A | #N/A
3396 | SARATOGA 1107CB | 83371107 | SARATOGA 1107 | 0.17019 | 135 | 4.0299e-06 | 0.00054404 | 3335 | 26032.8039 | 0.023951 | #N/A | #N/A
697 | SANTA ROSA A 1107CB | 42151107 | SANTA ROSA A 1107 | 3.0326 | 92 | 3.9708e-06 | 0.00036531 | 3336 | 26035.8365 | 0.023586 | #N/A | #N/A
7511 | BERKELEY F 1105189500 | 12061105 | BERKELEY F 1105 | 0.76177 | 17 | 3.9708e-06 | 6.7503e-05 | 3337 | 26036.5983 | 0.023519 | #N/A | #N/A
5683 | OAKLAND K 1104CB | 12101104 | OAKLAND K 1104 | 1.4708 | 17 | 3.9555e-06 | 6.7244e-05 | 3338 | 26038.0691 | 0.023451 | #N/A | #N/A
4165 | VIEJO 22022606 | 182852202 | VIEJO 2202 | 0.79514 | 52 | 3.9158e-06 | 0.00020362 | 3339 | 26038.8642 | 0.023248 | #N/A | #N/A
5028 | PUEBLO 21031970 | 43292103 | PUEBLO 2103 | 0 | 60 | 3.9099e-06 | 0.00023459 | 3340 | 26038.8642 | 0.023013 | #N/A | #N/A
4499 | MORGAN HILL 2109145998 | 83242109 | MORGAN HILL 2109 | 2.5034 | 28 | 3.8997e-06 | 0.00010919 | 3341 | 26041.3676 | 0.022904 | #N/A | #N/A
1014 | VIEJO 22019114 | 182852201 | VIEJO 2201 | 6.8226 | 92 | 3.8947e-06 | 0.00035832 | 3342 | 26048.1902 | 0.022546 | #N/A | #N/A
230 | CAROLANDS 04049026 | 24060404 | CAROLANDS 0404 | 0.73595 | 71 | 3.8932e-06 | 0.00027642 | 3343 | 26048.9262 | 0.022269 | #N/A | #N/A
10928 | FORT ORD 21069656 | 182402106 | FORT ORD 2106 | 0.11746 | 2 | 3.8714e-06 | 7.7429e-06 | 3344 | 26049.0436 | 0.022262 | #N/A | #N/A
5034 | OAKLAND J 1102CR184 | 12091102 | OAKLAND J 1102 | 3.4612 | 43 | 3.8445e-06 | 0.00016531 | 3345 | 26052.5048 | 0.022096 | #N/A | #N/A
4211 | FAIRVIEW 2207P142 | 13432207 | FAIRVIEW 2207 | 1.2204 | 41 | 3.8432e-06 | 0.00015757 | 3346 | 26053.7252 | 0.021939 | #N/A | #N/A
10430 | BELL 1107643778 | 152701107 | BELL 1107 | 0.168 | 4 | 3.7919e-06 | 1.5168e-05 | 3347 | 26053.8932 | 0.021923 | #N/A | #N/A
9697 | DOLAN ROAD 1101882610 | 182381101 | DOLAN ROAD 1101 | 0.1419 | 8 | 3.7868e-06 | 3.0295e-05 | 3348 | 26054.0351 | 0.021893 | #N/A | #N/A
238 | LOS GATOS 1102526868 | 82021102 | LOS GATOS 1102 | 1.1066 | 20 | 3.7614e-06 | 7.5227e-05 | 3349 | 26055.1417 | 0.021818 | #N/A | #N/A
7260 | SUMMIT 110158642 | 152591101 | SUMMIT 1101 | 1.7974 | 13 | 3.7548e-06 | 4.8812e-05 | 3350 | 26056.9391 | 0.021769 | #N/A | #N/A
535 | ATASCADERO 11012379 | 182541101 | ATASCADERO 1101 | 0.72801 | 11 | 3.7546e-06 | 4.1301e-05 | 3351 | 26057.6671 | 0.021728 | #N/A | #N/A
4492 | DEL MONTE 2103468158 | 182222103 | DEL MONTE 2103 | 0.51374 | 12 | 3.7407e-06 | 4.4889e-05 | 3352 | 26058.1808 | 0.021683 | #N/A | #N/A
8753 | HALF MOON BAY 1102650808 | 24101102 | HALF MOON BAY 1102 | 0.52415 | 8 | 3.6894e-06 | 2.9515e-05 | 3353 | 26058.705 | 0.021653 | #N/A | #N/A
43 | WOODSIDE 1104555372 | 24251104 | WOODSIDE 1104 | 4.1545 | 54 | 3.6721e-06 | 0.0001983 | 3354 | 26062.8594 | 0.021455 | #N/A | #N/A
10659 | ECHO SUMMIT 110155262 | 158031101 | ECHO SUMMIT 1101 | 0.16565 | 4 | 3.653e-06 | 1.4612e-05 | 3355 | 26063.0251 | 0.021441 | #N/A | #N/A
7441 | SAN LUIS OBISPO 110596874 | 182631105 | SAN LUIS OBISPO 1105 | 0.83624 | 16 | 3.6408e-06 | 5.8253e-05 | 3356 | 26063.8613 | 0.021382 | #N/A | #N/A
9136 | VIEJO 2204CB | 182852204 | VIEJO 2204 | 2.3167 | 24 | 3.64e-06 | 8.736e-05 | 3357 | 26066.178 | 0.021295 | #N/A | #N/A
4971 | EDES 1112CR282 | 13681112 | EDES 1112 | 4.0852 | 45 | 3.6364e-06 | 0.00016364 | 3358 | 26070.2632 | 0.021131 | #N/A | #N/A
7343 | ATASCADERO 1101CB | 182541101 | ATASCADERO 1101 | 0.03803 | 24 | 3.6135e-06 | 8.6724e-05 | 3359 | 26070.3012 | 0.021045 | #N/A | #N/A
8700 | VIEJO 22029488 | 182852202 | VIEJO 2202 | 0.90765 | 18 | 3.6034e-06 | 6.486e-05 | 3360 | 26071.2088 | 0.02098 | #N/A | #N/A
3541 | SEACLIFF 0402558727 | 83500402 | SEACLIFF 0402 | 0.13496 | 22 | 3.5926e-06 | 7.9037e-05 | 3361 | 26071.3438 | 0.020901 | #N/A | #N/A
7420 | DEL MONTE 210342226 | 182222103 | DEL MONTE 2103 | 0.58433 | 32 | 3.588e-06 | 0.00011482 | 3362 | 26071.9281 | 0.020786 | #N/A | #N/A
7115 | LAS GALLINAS A 1104309087 | 42991104 | LAS GALLINAS A 1104 | 0.188 | 6 | 3.575e-06 | 2.145e-05 | 3363 | 26072.1161 | 0.020764 | #N/A | #N/A
5040 | TEMPLETON 2112238418 | 183052112 | TEMPLETON 2112 | 0.20587 | 6 | 3.5615e-06 | 2.1369e-05 | 3364 | 26072.322 | 0.020743 | #N/A | #N/A
77 | ALTO 1124428 | 42031124 | ALTO 1124 | 0 | 21 | 3.5167e-06 | 7.3852e-05 | 3365 | 26072.322 | 0.020669 | #N/A | #N/A
288 | MORGAN HILL 2110XR326 | 83242110 | MORGAN HILL 2110 | 0 | 163 | 3.509e-06 | 0.00057196 | 3366 | 26072.322 | 0.020097 | #N/A | #N/A
1912 | SANTA ROSA A 110439786 | 42151104 | SANTA ROSA A 1104 | 0.28262 | 44 | 3.496e-06 | 0.00015383 | 3367 | 26072.6046 | 0.019943 | #N/A | #N/A
6503 | VIEJO 22029118 | 182852202 | VIEJO 2202 | 0.78669 | 41 | 3.4915e-06 | 0.00014315 | 3368 | 26073.3913 | 0.0198 | #N/A | #N/A
4440 | SANTA ROSA A 1104991788 | 42151104 | SANTA ROSA A 1104 | 0.75952 | 43 | 3.4631e-06 | 0.00014892 | 3369 | 26074.1508 | 0.019651 | #N/A | #N/A
8382 | MORGAN HILL 2109XR246 | 83242109 | MORGAN HILL 2109 | 0.044495 | 61 | 3.4559e-06 | 0.00021081 | 3370 | 26074.1953 | 0.019441 | #N/A | #N/A
8657 | OCEANO 110376678 | 182601103 | OCEANO 1103 | 0.05516 | 8 | 3.4511e-06 | 2.7609e-05 | 3371 | 26074.2505 | 0.019413 | #N/A | #N/A
9324 | ECHO SUMMIT 1101741586 | 158031101 | ECHO SUMMIT 1101 | 0.70714 | 9 | 3.4334e-06 | 3.09e-05 | 3372 | 26074.9576 | 0.019382 | #N/A | #N/A
392 | BELMONT 11038958 | 24031103 | BELMONT 1103 | 3.3803 | 73 | 3.4119e-06 | 0.00024907 | 3373 | 26078.3379 | 0.019133 | #N/A | #N/A
9058 | LOS GATOS 1101502026 | 82021101 | LOS GATOS 1101 | 0.11221 | 17 | 3.4024e-06 | 5.784e-05 | 3374 | 26078.4502 | 0.019075 | #N/A | #N/A
2028 | HICKS 1116LB16 | 83431116 | HICKS 1116 | 2.734 | 97 | 3.3964e-06 | 0.00032945 | 3375 | 26081.1842 | 0.018746 | #N/A | #N/A
10450 | OAKLAND J 1102951816 | 12091102 | OAKLAND J 1102 | 0.3351 | 6 | 3.3923e-06 | 2.0354e-05 | 3376 | 26081.5193 | 0.018725 | #N/A | #N/A
3081 | SARATOGA 1103LC40 | 83371103 | SARATOGA 1103 | 0.016639 | 28 | 3.3827e-06 | 9.4717e-05 | 3377 | 26081.5359 | 0.018631 | #N/A | #N/A
5298 | SAN LEANDRO U 1109CR182 | 13111109 | SAN LEANDRO U 1109 | 4.8284 | 56 | 3.38e-06 | 0.00018928 | 3378 | 26086.3643 | 0.018441 | #N/A | #N/A
9781 | SAN LUIS OBISPO 1108903036 | 182631108 | SAN LUIS OBISPO 1108 | 0.19058 | 5 | 3.3474e-06 | 1.6737e-05 | 3379 | 26086.5549 | 0.018425 | #N/A | #N/A
1847 | ALTO 1122CB | 42031122 | ALTO 1122 | 2.2447 | 46 | 3.3325e-06 | 0.0001533 | 3380 | 26088.7995 | 0.018271 | #N/A | #N/A
559 | PACIFICA 110266732 | 22811102 | PACIFICA 1102 | 0.20817 | 23 | 3.3135e-06 | 7.6211e-05 | 3381 | 26089.0077 | 0.018195 | #N/A | #N/A
7812 | LUCERNE 11062355 | 43351106 | LUCERNE 1106 | 0.40047 | 13 | 3.2963e-06 | 4.2852e-05 | 3382 | 26089.4082 | 0.018152 | #N/A | #N/A
9811 | PACIFICA 1103119798 | 22811103 | PACIFICA 1103 | 0.080612 | 2 | 3.2867e-06 | 6.5735e-06 | 3383 | 26089.4888 | 0.018146 | #N/A | #N/A
10195 | ALTO 112081716 | 42031120 | ALTO 1120 | 0.2528 | 5 | 3.2689e-06 | 1.6345e-05 | 3384 | 26089.7416 | 0.018129 | #N/A | #N/A
6620 | LOS GATOS 1101950286 | 82021101 | LOS GATOS 1101 | 1.0633 | 17 | 3.2625e-06 | 5.5462e-05 | 3385 | 26090.8049 | 0.018074 | #N/A | #N/A
5964 | RALSTON 1102CB | 24141102 | RALSTON 1102 | 0.94477 | 66 | 3.2502e-06 | 0.00021451 | 3386 | 26091.7496 | 0.017859 | #N/A | #N/A
8215 | GREENBRAE 1104107508 | 43091104 | GREENBRAE 1104 | 0 | 2 | 3.214e-06 | 6.4279e-06 | 3387 | 26091.7496 | 0.017853 | #N/A | #N/A
1635 | OAKLAND K 1101CR172 | 12101101 | OAKLAND K 1101 | 0.56244 | 30 | 3.209e-06 | 9.6271e-05 | 3388 | 26092.3121 | 0.017757 | #N/A | #N/A
3774 | PAUL SWEET 210411074 | 83252104 | PAUL SWEET 2104 | 2.9324 | 41 | 3.1905e-06 | 0.00013081 | 3389 | 26095.2445 | 0.017626 | #N/A | #N/A
8087 | SAN RAMON 2107MR441 | 14232107 | SAN RAMON 2107 | 0.024985 | 8 | 3.1892e-06 | 2.5513e-05 | 3390 | 26095.2695 | 0.0176 | #N/A | #N/A
7720 | SAN RAFAEL 1106764698 | 42011106 | SAN RAFAEL 1106 | 0.082913 | 5 | 3.1867e-06 | 1.5933e-05 | 3391 | 26095.3524 | 0.017584 | #N/A | #N/A
3736 | VALLEY VIEW 1105P126 | 14341105 | VALLEY VIEW 1105 | 1.0446 | 25 | 3.1848e-06 | 7.9621e-05 | 3392 | 26096.3971 | 0.017505 | #N/A | #N/A
2670 | GREENBRAE 11037315 | 43091103 | GREENBRAE 1103 | 0 | 32 | 3.1589e-06 | 0.00010108 | 3393 | 26096.3971 | 0.017404 | #N/A | #N/A
6253 | FORT BRAGG A 110233064 | 42761102 | FORT BRAGG A 1102 | 0 | 49 | 3.15e-06 | 0.00015435 | 3394 | 26096.3971 | 0.017249 | #N/A | #N/A
4022 | EDES 1112CR100 | 13681112 | EDES 1112 | 3.3555 | 40 | 3.1366e-06 | 0.00012546 | 3395 | 26099.7526 | 0.017124 | #N/A | #N/A
1730 | LOS GATOS 1101CB | 82021101 | LOS GATOS 1101 | 0.029616 | 34 | 3.1364e-06 | 0.00010664 | 3396 | 26099.7822 | 0.017017 | #N/A | #N/A
5067 | EL CERRITO G 1112BR178 | 12501112 | EL CERRITO G 1112 | 0.029957 | 93 | 3.1309e-06 | 0.00029117 | 3397 | 26099.8122 | 0.016726 | #N/A | #N/A
3732 | SOBRANTE 1101L534R | 14671101 | SOBRANTE 1101 | 0.80294 | 34 | 3.1282e-06 | 0.00010636 | 3398 | 26100.6151 | 0.01662 | #N/A | #N/A
4550 | VALLEY VIEW 1106P176 | 14341106 | VALLEY VIEW 1106 | 0.2203 | 44 | 3.1268e-06 | 0.00013758 | 3399 | 26100.8354 | 0.016482 | #N/A | #N/A
7024 | VIEJO 220292792 | 182852202 | VIEJO 2202 | 0 | 21 | 3.1236e-06 | 6.5595e-05 | 3400 | 26100.8354 | 0.016416 | #N/A | #N/A
8774 | TULUCAY 1101504524 | 42301101 | TULUCAY 1101 | 0.37918 | 15 | 3.1216e-06 | 4.6823e-05 | 3401 | 26101.2146 | 0.01637 | #N/A | #N/A
9561 | ATASCADERO 1101747522 | 182541101 | ATASCADERO 1101 | 0.25664 | 16 | 3.1133e-06 | 4.9813e-05 | 3402 | 26101.4712 | 0.01632 | #N/A | #N/A
1757 | OAKLAND X 1106121588 | 12541106 | OAKLAND X 1106 | 0.84288 | 27 | 3.0983e-06 | 8.3654e-05 | 3403 | 26102.3141 | 0.016236 | #N/A | #N/A
641 | ALTO 11251256 | 42031125 | ALTO 1125 | 7.46 | 88 | 3.098e-06 | 0.00027263 | 3404 | 26109.7741 | 0.015964 | #N/A | #N/A
7693 | SARATOGA 1103595689 | 83371103 | SARATOGA 1103 | 0.027822 | 4 | 3.0826e-06 | 1.233e-05 | 3405 | 26109.802 | 0.015951 | #N/A | #N/A
1201 | RINCON 1102640 | 43321102 | RINCON 1102 | 0 | 56 | 3.0722e-06 | 0.00017204 | 3406 | 26109.802 | 0.015779 | #N/A | #N/A
8249 | VIEJO 22029089 | 182852202 | VIEJO 2202 | 1.4419 | 20 | 3.0684e-06 | 6.1368e-05 | 3407 | 26111.2438 | 0.015718 | #N/A | #N/A
4500 | PACIFICA 1102968736 | 22811102 | PACIFICA 1102 | 0.70371 | 9 | 3.0372e-06 | 2.7334e-05 | 3408 | 26111.9475 | 0.01569 | #N/A | #N/A
5121 | BURNEY 110237284 | 103311102 | BURNEY 1102 | 0.18836 | 15 | 3.0199e-06 | 4.5299e-05 | 3409 | 26112.1359 | 0.015645 | #N/A | #N/A
3124 | SAN RAFAEL 110648752 | 42011106 | SAN RAFAEL 1106 | 0.014424 | 28 | 2.9974e-06 | 8.3928e-05 | 3410 | 26112.1503 | 0.015561 | #N/A | #N/A
292 | RIDGE 0402CB | 12840402 | RIDGE 0402 | 1.8211 | 31 | 2.9927e-06 | 9.2772e-05 | 3411 | 26113.9715 | 0.015468 | #N/A | #N/A
5812 | LAS GALLINAS A 11051218 | 42991105 | LAS GALLINAS A 1105 | 0.066343 | 28 | 2.9904e-06 | 8.3731e-05 | 3412 | 26114.0378 | 0.015385 | #N/A | #N/A
5928 | IGNACIO 110584764 | 42481105 | IGNACIO 1105 | 0.21126 | 33 | 2.9818e-06 | 9.8398e-05 | 3413 | 26114.2491 | 0.015286 | #N/A | #N/A
231 | PAUL SWEET 210912828 | 83252109 | PAUL SWEET 2109 | 1.1399 | 66 | 2.9651e-06 | 0.0001957 | 3414 | 26115.389 | 0.015091 | #N/A | #N/A
5926 | CASTRO VALLEY 1110CB | 14091110 | CASTRO VALLEY 1110 | 0.32525 | 23 | 2.9632e-06 | 6.8153e-05 | 3415 | 26115.7142 | 0.015023 | #N/A | #N/A
8452 | HARRIS 1108395498 | 192431108 | HARRIS 1108 | 0.1063 | 8 | 2.9622e-06 | 2.3698e-05 | 3416 | 26115.8205 | 0.014999 | #N/A | #N/A
8569 | IGNACIO 1105683542 | 42481105 | IGNACIO 1105 | 0.13854 | 2 | 2.9468e-06 | 5.8935e-06 | 3417 | 26115.9591 | 0.014993 | #N/A | #N/A
6289 | STAFFORD 1101405812 | 43201101 | STAFFORD 1101 | 0.1835 | 7 | 2.9445e-06 | 2.0611e-05 | 3418 | 26116.1426 | 0.014972 | #N/A | #N/A
8541 | ROSSMOOR 1106L541R | 14161106 | ROSSMOOR 1106 | 0 | 11 | 2.9324e-06 | 3.2256e-05 | 3419 | 26116.1426 | 0.01494 | #N/A | #N/A
3241 | OAKLAND K 1101CB | 12101101 | OAKLAND K 1101 | 0.33465 | 40 | 2.9186e-06 | 0.00011674 | 3420 | 26116.4772 | 0.014823 | #N/A | #N/A
6045 | OAKLAND J 1105CR256 | 12091105 | OAKLAND J 1105 | 1.2215 | 27 | 2.9181e-06 | 7.879e-05 | 3421 | 26117.6987 | 0.014745 | #N/A | #N/A
8780 | SAN LUIS OBISPO 1108144690 | 182631108 | SAN LUIS OBISPO 1108 | 0.26037 | 10 | 2.905e-06 | 2.905e-05 | 3422 | 26117.9591 | 0.014715 | #N/A | #N/A
10157 | CASTRO VALLEY 1108MR233 | 14091108 | CASTRO VALLEY 1108 | 0.23054 | 7 | 2.9035e-06 | 2.0325e-05 | 3423 | 26118.1897 | 0.014695 | #N/A | #N/A
3481 | IGNACIO 1105318 | 42481105 | IGNACIO 1105 | 1.7945 | 150 | 2.9031e-06 | 0.00043547 | 3424 | 26119.9841 | 0.01426 | #N/A | #N/A
1523 | HAMILTON BRANCH 110187784 | 102361101 | HAMILTON BRANCH 1101 | 1.4473 | 23 | 2.8956e-06 | 6.6598e-05 | 3425 | 26121.4314 | 0.014193 | #N/A | #N/A
10922 | PINECREST 0401CB | 163160401 | PINECREST 0401 | 0.013801 | 1 | 2.8911e-06 | 2.8911e-06 | 3426 | 26121.4452 | 0.01419 | #N/A | #N/A
1324 | SONOMA 11054456 | 42721105 | SONOMA 1105 | 0 | 62 | 2.8714e-06 | 0.00017803 | 3427 | 26121.4452 | 0.014012 | #N/A | #N/A
8419 | SAN CARLOS 1103785521 | 24181103 | SAN CARLOS 1103 | 0.067757 | 3 | 2.8654e-06 | 8.5962e-06 | 3428 | 26121.513 | 0.014004 | #N/A | #N/A
6629 | BIG MEADOWS 21012246 | 102812101 | BIG MEADOWS 2101 | 1.8257 | 23 | 2.8555e-06 | 6.5676e-05 | 3429 | 26123.3387 | 0.013938 | #N/A | #N/A
692 | ECHO SUMMIT 11018922 | 158031101 | ECHO SUMMIT 1101 | 1.206 | 11 | 2.852e-06 | 3.1372e-05 | 3430 | 26124.5446 | 0.013907 | #N/A | #N/A
5593 | SNEATH LANE 1102CB | 22721102 | SNEATH LANE 1102 | 1.3642 | 37 | 2.8459e-06 | 0.0001053 | 3431 | 26125.9088 | 0.013801 | #N/A | #N/A
7382 | VIEJO 220235388 | 182852202 | VIEJO 2202 | 0.32133 | 8 | 2.8344e-06 | 2.2676e-05 | 3432 | 26126.2301 | 0.013779 | #N/A | #N/A
5265 | IGNACIO 1103CB | 42481103 | IGNACIO 1103 | 0.21773 | 34 | 2.8181e-06 | 9.5817e-05 | 3433 | 26126.4479 | 0.013683 | #N/A | #N/A
9102 | HICKS 1116733078 | 83431116 | HICKS 1116 | 0.34299 | 7 | 2.777e-06 | 1.9439e-05 | 3434 | 26126.7909 | 0.013663 | #N/A | #N/A
199 | OAKLAND K 1103CB | 12101103 | OAKLAND K 1103 | 0.47804 | 66 | 2.758e-06 | 0.00018203 | 3435 | 26127.2689 | 0.013481 | #N/A | #N/A
2072 | RALSTON 1101420730 | 24141101 | RALSTON 1101 | 0.80338 | 21 | 2.7513e-06 | 5.7777e-05 | 3436 | 26128.0723 | 0.013423 | #N/A | #N/A
8913 | WOOD 0401880795 | 13380401 | WOOD 0401 | 0.10191 | 6 | 2.7412e-06 | 1.6447e-05 | 3437 | 26128.1742 | 0.013407 | #N/A | #N/A
7811 | VIEJO 2203947314 | 182852203 | VIEJO 2203 | 0.28676 | 22 | 2.7164e-06 | 5.9761e-05 | 3438 | 26128.461 | 0.013347 | #N/A | #N/A
8336 | OLEMA 110137074 | 42291101 | OLEMA 1101 | 0.013639 | 6 | 2.7134e-06 | 1.628e-05 | 3439 | 26128.4746 | 0.013331 | #N/A | #N/A
6224 | SAN CARLOS 110479774 | 24181104 | SAN CARLOS 1104 | 0.89241 | 24 | 2.698e-06 | 6.4753e-05 | 3440 | 26129.367 | 0.013266 | #N/A | #N/A
2094 | ROB ROY 210512586 | 83692105 | ROB ROY 2105 | 1.8902 | 85 | 2.697e-06 | 0.00022925 | 3441 | 26131.2572 | 0.013037 | #N/A | #N/A
8276 | OAKLAND J 1102CR254 | 12091102 | OAKLAND J 1102 | 1.0485 | 20 | 2.6941e-06 | 5.3882e-05 | 3442 | 26132.3057 | 0.012983 | #N/A | #N/A
5380 | CASTROVILLE 210436922 | 182352104 | CASTROVILLE 2104 | 0 | 37 | 2.6705e-06 | 9.8808e-05 | 3443 | 26132.3057 | 0.012884 | #N/A | #N/A
6593 | FOOTHILL 1101798137 | 182951101 | FOOTHILL 1101 | 0.042272 | 5 | 2.6637e-06 | 1.3319e-05 | 3444 | 26132.348 | 0.012871 | #N/A | #N/A
1687 | BIG MEADOWS 21012016 | 102812101 | BIG MEADOWS 2101 | 0.09383 | 65 | 2.6614e-06 | 0.00017299 | 3445 | 26132.4418 | 0.012698 | #N/A | #N/A
10145 | GREENBRAE 1104317890 | 43091104 | GREENBRAE 1104 | 0.078205 | 2 | 2.6567e-06 | 5.3133e-06 | 3446 | 26132.52 | 0.012693 | #N/A | #N/A
3009 | GREENBRAE 1102CB | 43091102 | GREENBRAE 1102 | 0 | 28 | 2.6553e-06 | 7.4348e-05 | 3447 | 26132.52 | 0.012618 | #N/A | #N/A
9193 | LOS GATOS 1106CB | 82021106 | LOS GATOS 1106 | 0.10208 | 11 | 2.651e-06 | 2.9161e-05 | 3448 | 26132.6221 | 0.012589 | #N/A | #N/A
6430 | FORT BRAGG A 110465894 | 42761104 | FORT BRAGG A 1104 | 0 | 12 | 2.6468e-06 | 3.1761e-05 | 3449 | 26132.6221 | 0.012557 | #N/A | #N/A
6292 | RIO DEL MAR 0401931192 | 83260401 | RIO DEL MAR 0401 | 2.2472 | 87 | 2.6467e-06 | 0.00023026 | 3450 | 26134.8692 | 0.012327 | #N/A | #N/A
8372 | LAURELES 11122142 | 182371112 | LAURELES 1112 | 0.094397 | 26 | 2.6301e-06 | 6.8383e-05 | 3451 | 26134.9636 | 0.012259 | #N/A | #N/A
4353 | FLORENCE 0401CB | 12690401 | FLORENCE 0401 | 0.64714 | 39 | 2.6231e-06 | 0.0001023 | 3452 | 26135.6108 | 0.012156 | #N/A | #N/A
1560 | SANTA ROSA A 1104CB | 42151104 | SANTA ROSA A 1104 | 0.22934 | 76 | 2.617e-06 | 0.00019889 | 3453 | 26135.8401 | 0.011958 | #N/A | #N/A
9790 | PAUL SWEET 2109680537 | 83252109 | PAUL SWEET 2109 | 0.22544 | 9 | 2.5979e-06 | 2.3381e-05 | 3454 | 26136.0656 | 0.011934 | #N/A | #N/A
9764 | PACIFICA 1102512070 | 22811102 | PACIFICA 1102 | 0.17379 | 5 | 2.586e-06 | 1.293e-05 | 3455 | 26136.2393 | 0.011921 | #N/A | #N/A
2324 | ALTO 1124CB | 42031124 | ALTO 1124 | 1.6988 | 81 | 2.5838e-06 | 0.00020929 | 3456 | 26137.9381 | 0.011712 | #N/A | #N/A
2547 | CASTRO VALLEY 1102MR204 | 14091102 | CASTRO VALLEY 1102 | 0.20294 | 46 | 2.5759e-06 | 0.00011849 | 3457 | 26138.1411 | 0.011593 | #N/A | #N/A
885 | EDES 1112CR308 | 13681112 | EDES 1112 | 3.2124 | 53 | 2.5524e-06 | 0.00013527 | 3458 | 26141.3535 | 0.011458 | #N/A | #N/A
7145 | HICKS 111512494 | 83431115 | HICKS 1115 | 0.1368 | 35 | 2.5505e-06 | 8.9268e-05 | 3459 | 26141.4903 | 0.011369 | #N/A | #N/A
970 | CAYUCOS 1102CB | 182551102 | CAYUCOS 1102 | 0 | 41 | 2.5468e-06 | 0.00010442 | 3460 | 26141.4903 | 0.011265 | #N/A | #N/A
7960 | LOS GATOS 1101206248 | 82021101 | LOS GATOS 1101 | 0.051587 | 10 | 2.5435e-06 | 2.5435e-05 | 3461 | 26141.5419 | 0.011239 | #N/A | #N/A
2461 | HAMILTON BRANCH 110137436 | 102361101 | HAMILTON BRANCH 1101 | 0.75082 | 33 | 2.5374e-06 | 8.3735e-05 | 3462 | 26142.2927 | 0.011155 | #N/A | #N/A
5208 | VIEJO 22029120 | 182852202 | VIEJO 2202 | 1.7763 | 112 | 2.5361e-06 | 0.00028404 | 3463 | 26144.069 | 0.010871 | #N/A | #N/A
10027 | PACIFICA 1103398620 | 22811103 | PACIFICA 1103 | 0.47115 | 7 | 2.531e-06 | 1.7717e-05 | 3464 | 26144.5401 | 0.010854 | #N/A | #N/A
4053 | OAKLAND X 1105184672 | 12541105 | OAKLAND X 1105 | 1.657 | 46 | 2.5255e-06 | 0.00011617 | 3465 | 26146.1971 | 0.010737 | #N/A | #N/A
5327 | FAIRVIEW 2207CB | 13432207 | FAIRVIEW 2207 | 0.24062 | 57 | 2.5112e-06 | 0.00014314 | 3466 | 26146.4377 | 0.010594 | #N/A | #N/A
1098 | VIEJO 22012064 | 182852201 | VIEJO 2201 | 0.87595 | 15 | 2.486e-06 | 3.729e-05 | 3467 | 26147.3136 | 0.010557 | #N/A | #N/A
3180 | STAFFORD 110242542 | 43201102 | STAFFORD 1102 | 0.53595 | 52 | 2.465e-06 | 0.00012818 | 3468 | 26147.8496 | 0.010429 | #N/A | #N/A
4684 | SNEATH LANE 110134438 | 22721101 | SNEATH LANE 1101 | 2.3055 | 67 | 2.4545e-06 | 0.00016445 | 3469 | 26150.1551 | 0.010264 | #N/A | #N/A
5609 | BURNEY 110297318 | 103311102 | BURNEY 1102 | 0.18333 | 18 | 2.4455e-06 | 4.4019e-05 | 3470 | 26150.3385 | 0.01022 | #N/A | #N/A
3808 | HAMILTON BRANCH 11013049 | 102361101 | HAMILTON BRANCH 1101 | 1.0261 | 23 | 2.4445e-06 | 5.6224e-05 | 3471 | 26151.3646 | 0.010164 | #N/A | #N/A
10978 | ALTO 1124965060 | 42031124 | ALTO 1124 | 0.061936 | 1 | 2.4396e-06 | 2.4396e-06 | 3472 | 26151.4265 | 0.010162 | #N/A | #N/A
10767 | SAUSALITO 1102758798 | 42491102 | SAUSALITO 1102 | 0.033105 | 2 | 2.4159e-06 | 4.8318e-06 | 3473 | 26151.4596 | 0.010157 | #N/A | #N/A
2223 | PAUL SWEET 2109CB | 83252109 | PAUL SWEET 2109 | 0.012889 | 171 | 2.3948e-06 | 0.00040951 | 3474 | 26151.4725 | 0.0097474 | #N/A | #N/A
4848 | VALLEY VIEW 1103P160 | 14341103 | VALLEY VIEW 1103 | 0 | 96 | 2.3734e-06 | 0.00022785 | 3475 | 26151.4725 | 0.0095195 | #N/A | #N/A
1157 | MORAGA 1105116034 | 13801105 | MORAGA 1105 | 0.33531 | 41 | 2.3641e-06 | 9.6928e-05 | 3476 | 26151.8078 | 0.0094226 | #N/A | #N/A
6537 | SNEATH LANE 110275844 | 22721102 | SNEATH LANE 1102 | 0.16947 | 10 | 2.3271e-06 | 2.3271e-05 | 3477 | 26151.9773 | 0.0093993 | #N/A | #N/A
1692 | SAN CARLOS 11048846 | 24181104 | SAN CARLOS 1104 | 2.2303 | 61 | 2.3218e-06 | 0.00014163 | 3478 | 26154.2076 | 0.0092577 | #N/A | #N/A
5922 | SNEATH LANE 1101CB | 22721101 | SNEATH LANE 1101 | 0.46322 | 19 | 2.3127e-06 | 4.3942e-05 | 3479 | 26154.6708 | 0.0092137 | #N/A | #N/A
3263 | SAN LEANDRO U 1109936988 | 13111109 | SAN LEANDRO U 1109 | 6.7688 | 86 | 2.3051e-06 | 0.00019824 | 3480 | 26161.4397 | 0.0090155 | #N/A | #N/A
7536 | WILLITS 11021270 | 42661102 | WILLITS 1102 | 0 | 21 | 2.3027e-06 | 4.8357e-05 | 3481 | 26161.4397 | 0.0089671 | #N/A | #N/A
2607 | WALDO 0402258792 | 13350402 | WALDO 0402 | 2.9795 | 36 | 2.3019e-06 | 8.287e-05 | 3482 | 26164.4191 | 0.0088843 | #N/A | #N/A
2976 | STAFFORD 1101902998 | 43201101 | STAFFORD 1101 | 1.0766 | 81 | 2.2981e-06 | 0.00018615 | 3483 | 26165.4958 | 0.0086981 | #N/A | #N/A
28 | RALSTON 110148936 | 24141101 | RALSTON 1101 | 4.6223 | 86 | 2.2943e-06 | 0.00019731 | 3484 | 26170.118 | 0.0085008 | #N/A | #N/A
6723 | VALLEY VIEW 1106P128 | 14341106 | VALLEY VIEW 1106 | 0.11865 | 31 | 2.2678e-06 | 7.0301e-05 | 3485 | 26170.2367 | 0.0084305 | #N/A | #N/A
6528 | LAS GALLINAS A 1106206332 | 42991106 | LAS GALLINAS A 1106 | 0.30383 | 7 | 2.2569e-06 | 1.5798e-05 | 3486 | 26170.5405 | 0.0084147 | #N/A | #N/A
2106 | SPRUCE 0402BR304 | 13340402 | SPRUCE 0402 | 1.4871 | 53 | 2.2492e-06 | 0.00011921 | 3487 | 26172.0276 | 0.0082955 | #N/A | #N/A
3661 | LAS GALLINAS A 1106685656 | 42991106 | LAS GALLINAS A 1106 | 1.1954 | 43 | 2.2325e-06 | 9.5996e-05 | 3488 | 26173.223 | 0.0081995 | #N/A | #N/A
3471 | LOS GATOS 110160136 | 82021101 | LOS GATOS 1101 | 0 | 57 | 2.2252e-06 | 0.00012684 | 3489 | 26173.223 | 0.0080727 | #N/A | #N/A
4292 | EMERALD LAKE 04028872 | 24080402 | EMERALD LAKE 0402 | 4.5022 | 77 | 2.2015e-06 | 0.00016952 | 3490 | 26177.7252 | 0.0079032 | #N/A | #N/A
1116 | SNEATH LANE 110168070 | 22721101 | SNEATH LANE 1101 | 0.23226 | 30 | 2.1953e-06 | 6.5858e-05 | 3491 | 26177.9575 | 0.0078373 | #N/A | #N/A
9555 | IGNACIO 1103504941 | 42481103 | IGNACIO 1103 | 0.41221 | 6 | 2.194e-06 | 1.3164e-05 | 3492 | 26178.3697 | 0.0078241 | #N/A | #N/A
4494 | VIEJO 22019704 | 182852201 | VIEJO 2201 | 0.48887 | 29 | 2.1872e-06 | 6.3429e-05 | 3493 | 26178.8586 | 0.0077607 | #N/A | #N/A
3505 | WOODSIDE 11049030 | 24251104 | WOODSIDE 1104 | 2.0338 | 37 | 2.1865e-06 | 8.0902e-05 | 3494 | 26180.8924 | 0.0076798 | #N/A | #N/A
4601 | HATTON 11022070 | 182291102 | HATTON 1102 | 0.52422 | 26 | 2.1767e-06 | 5.6595e-05 | 3495 | 26181.4166 | 0.0076232 | #N/A | #N/A
10245 | GREENBRAE 1104972264 | 43091104 | GREENBRAE 1104 | 0 | 4 | 2.1732e-06 | 8.6927e-06 | 3496 | 26181.4166 | 0.0076145 | #N/A | #N/A
6525 | HAMILTON BRANCH 11012082 | 102361101 | HAMILTON BRANCH 1101 | 1.5197 | 46 | 2.1552e-06 | 9.9139e-05 | 3497 | 26182.9363 | 0.0075154 | #N/A | #N/A
7268 | HICKS 1116203897 | 83431116 | HICKS 1116 | 0.22866 | 9 | 2.1509e-06 | 1.9358e-05 | 3498 | 26183.165 | 0.007496 | #N/A | #N/A
5472 | CHESTER 1101656108 | 103181101 | CHESTER 1101 | 0.52126 | 10 | 2.1478e-06 | 2.1478e-05 | 3499 | 26183.6862 | 0.0074745 | #N/A | #N/A
659 | EL CERRITO G 1112BR196 | 12501112 | EL CERRITO G 1112 | 0 | 51 | 2.127e-06 | 0.00010848 | 3500 | 26183.6862 | 0.0073661 | #N/A | #N/A
286 | OAKLAND X 1106CB | 12541106 | OAKLAND X 1106 | 3.2846 | 136 | 2.1195e-06 | 0.00028825 | 3501 | 26186.9709 | 0.0070778 | #N/A | #N/A
3401 | VIEJO 22029104 | 182852202 | VIEJO 2202 | 5.6859 | 79 | 2.113e-06 | 0.00016692 | 3502 | 26192.6567 | 0.0069109 | #N/A | #N/A
617 | OAK 0401CB | 12600401 | OAK 0401 | 3.4715 | 68 | 2.0871e-06 | 0.00014192 | 3503 | 26196.1282 | 0.006769 | #N/A | #N/A
5991 | VIEJO 22019698 | 182852201 | VIEJO 2201 | 0.57779 | 10 | 2.0607e-06 | 2.0607e-05 | 3504 | 26196.706 | 0.0067484 | #N/A | #N/A
2044 | SPRUCE 0401BR316 | 13340401 | SPRUCE 0401 | 4.1073 | 56 | 2.0588e-06 | 0.00011529 | 3505 | 26200.8133 | 0.0066331 | #N/A | #N/A
7179 | EL CERRITO G 111257953 | 12501112 | EL CERRITO G 1112 | 0.21956 | 11 | 2.0515e-06 | 2.2566e-05 | 3506 | 26201.0329 | 0.0066105 | #N/A | #N/A
5036 | FRANKLIN 1104CB | 13921104 | FRANKLIN 1104 | 0.28979 | 63 | 2.0367e-06 | 0.00012831 | 3507 | 26201.3227 | 0.0064822 | #N/A | #N/A
6325 | LOS GATOS 1108CB | 82021108 | LOS GATOS 1108 | 0 | 15 | 2.0334e-06 | 3.0501e-05 | 3508 | 26201.3227 | 0.0064517 | #N/A | #N/A
6874 | LOS GATOS 1102CB | 82021102 | LOS GATOS 1102 | 0 | 70 | 2.0154e-06 | 0.00014108 | 3509 | 26201.3227 | 0.0063106 | #N/A | #N/A
1424 | PACIFICA 1103CB | 22811103 | PACIFICA 1103 | 0.068073 | 62 | 2.0046e-06 | 0.00012428 | 3510 | 26201.3907 | 0.0061863 | #N/A | #N/A
10000 | ALTO 1125781759 | 42031125 | ALTO 1125 | 0.13082 | 4 | 2.0026e-06 | 8.0105e-06 | 3511 | 26201.5216 | 0.0061783 | #N/A | #N/A
254 | HICKS 1116CB | 83431116 | HICKS 1116 | 0.20893 | 165 | 1.9553e-06 | 0.00032262 | 3512 | 26201.7305 | 0.0058557 | #N/A | #N/A
1238 | STAFFORD 11021019 | 43201102 | STAFFORD 1102 | 0.26853 | 10 | 1.946e-06 | 1.946e-05 | 3513 | 26201.999 | 0.0058362 | #N/A | #N/A
10590 | CHESTER 1102546744 | 103181102 | CHESTER 1102 | 0.26654 | 7 | 1.934e-06 | 1.3538e-05 | 3514 | 26202.2656 | 0.0058227 | #N/A | #N/A
6891 | ALTO 1124994213 | 42031124 | ALTO 1124 | 0.12354 | 8 | 1.9051e-06 | 1.5241e-05 | 3515 | 26202.3891 | 0.0058075 | #N/A | #N/A
9434 | BERKELEY F 1105849701 | 12061105 | BERKELEY F 1105 | 0.13286 | 2 | 1.8894e-06 | 3.7788e-06 | 3516 | 26202.522 | 0.0058037 | #N/A | #N/A
6092 | VIEJO 22049540 | 182852204 | VIEJO 2204 | 1.4417 | 32 | 1.8885e-06 | 6.0431e-05 | 3517 | 26203.9637 | 0.0057433 | #N/A | #N/A
9394 | ALTO 1124884949 | 42031124 | ALTO 1124 | 0.19437 | 5 | 1.8768e-06 | 9.3841e-06 | 3518 | 26204.1581 | 0.0057339 | #N/A | #N/A
8014 | WALDO 0401965216 | 13350401 | WALDO 0401 | 1.6425 | 21 | 1.868e-06 | 3.9227e-05 | 3519 | 26205.8005 | 0.0056946 | #N/A | #N/A
4883 | LAS PULGAS 0401104588 | 24120401 | LAS PULGAS 0401 | 0.36135 | 11 | 1.8653e-06 | 2.0518e-05 | 3520 | 26206.1619 | 0.0056741 | #N/A | #N/A
8033 | MORAGA 110531512 | 13801105 | MORAGA 1105 | 0 | 29 | 1.8558e-06 | 5.3819e-05 | 3521 | 26206.1619 | 0.0056203 | #N/A | #N/A
4423 | SAN RAFAEL 1105344 | 42011105 | SAN RAFAEL 1105 | 0.81713 | 97 | 1.8552e-06 | 0.00017996 | 3522 | 26206.979 | 0.0054403 | #N/A | #N/A
3011 | PERRY 1101W52 | 183071101 | PERRY 1101 | 3.1282 | 51 | 1.8539e-06 | 9.4548e-05 | 3523 | 26210.1072 | 0.0053458 | #N/A | #N/A
2767 | EL CERRITO G 1112BR180 | 12501112 | EL CERRITO G 1112 | 0.41956 | 25 | 1.8513e-06 | 4.6282e-05 | 3524 | 26210.5268 | 0.0052995 | #N/A | #N/A
7505 | EDES 1112CR306 | 13681112 | EDES 1112 | 1.0066 | 16 | 1.8377e-06 | 2.9404e-05 | 3525 | 26211.5334 | 0.0052701 | #N/A | #N/A
349 | ALHAMBRA 1102CB | 14101102 | ALHAMBRA 1102 | 0.26794 | 75 | 1.7835e-06 | 0.00013376 | 3526 | 26211.8013 | 0.0051363 | #N/A | #N/A
5900 | CHESTER 1102CB | 103181102 | CHESTER 1102 | 0.025045 | 38 | 1.7766e-06 | 6.751e-05 | 3527 | 26211.8264 | 0.0050688 | #N/A | #N/A
6024 | WOODSIDE 11028862 | 24251102 | WOODSIDE 1102 | 0 | 38 | 1.7665e-06 | 6.7125e-05 | 3528 | 26211.8264 | 0.0050017 | #N/A | #N/A
4122 | BURNEY 110257046 | 103311102 | BURNEY 1102 | 0.030397 | 12 | 1.7587e-06 | 2.1104e-05 | 3529 | 26211.8568 | 0.0049806 | #N/A | #N/A
2110 | CASTRO VALLEY 1108MR205 | 14091108 | CASTRO VALLEY 1108 | 0 | 73 | 1.7478e-06 | 0.00012759 | 3530 | 26211.8568 | 0.004853 | #N/A | #N/A
2448 | VIEJO 22029112 | 182852202 | VIEJO 2202 | 0.84488 | 43 | 1.7421e-06 | 7.4909e-05 | 3531 | 26212.7016 | 0.0047781 | #N/A | #N/A
8885 | EL CERRITO G 1110BR236 | 12501110 | EL CERRITO G 1110 | 0.50957 | 7 | 1.7373e-06 | 1.2161e-05 | 3532 | 26213.2112 | 0.004766 | #N/A | #N/A
7598 | ALTO 1123820379 | 42031123 | ALTO 1123 | 0.15245 | 2 | 1.7362e-06 | 3.4724e-06 | 3533 | 26213.3637 | 0.0047625 | #N/A | #N/A
1294 | VIEJO 2203573610 | 182852203 | VIEJO 2203 | 0 | 41 | 1.7259e-06 | 7.0764e-05 | 3534 | 26213.3637 | 0.0046917 | #N/A | #N/A
2844 | SAN CARLOS 11039148 | 24181103 | SAN CARLOS 1103 | 0 | 51 | 1.7214e-06 | 8.7791e-05 | 3535 | 26213.3637 | 0.0046039 | #N/A | #N/A
469 | VIEJO 22039094 | 182852203 | VIEJO 2203 | 0.099611 | 32 | 1.7132e-06 | 5.4823e-05 | 3536 | 26213.4633 | 0.0045491 | #N/A | #N/A
7298 | VIEJO 22032634 | 182852203 | VIEJO 2203 | 0 | 23 | 1.6721e-06 | 3.8458e-05 | 3537 | 26213.4633 | 0.0045106 | #N/A | #N/A
8157 | OAKLAND J 1105CR150 | 12091105 | OAKLAND J 1105 | 0.21662 | 6 | 1.667e-06 | 1.0002e-05 | 3538 | 26213.6799 | 0.0045006 | #N/A | #N/A
7733 | FORT BRAGG A 1103CB | 42761103 | FORT BRAGG A 1103 | 0.094139 | 40 | 1.6633e-06 | 6.6534e-05 | 3539 | 26213.774 | 0.0044341 | #N/A | #N/A
9029 | MORGAN HILL 2105375239 | 83242105 | MORGAN HILL 2105 | 0.090219 | 4 | 1.6455e-06 | 6.5821e-06 | 3540 | 26213.8642 | 0.0044275 | #N/A | #N/A
9198 | MORGAN HILL 2105345099 | 83242105 | MORGAN HILL 2105 | 0.1823 | 5 | 1.6312e-06 | 8.156e-06 | 3541 | 26214.0465 | 0.0044194 | #N/A | #N/A
8274 | SALT SPRINGS 21013116 | 163692101 | SALT SPRINGS 2101 | 0.77748 | 10 | 1.6267e-06 | 1.6267e-05 | 3542 | 26214.824 | 0.0044031 | #N/A | #N/A
1788 | BERKELEY F 0402502466 | 12060402 | BERKELEY F 0402 | 0.14047 | 10 | 1.6151e-06 | 1.6151e-05 | 3543 | 26214.9645 | 0.004387 | #N/A | #N/A
2459 | BERKELEY F 1105CB | 12061105 | BERKELEY F 1105 | 1.0374 | 103 | 1.6033e-06 | 0.00016514 | 3544 | 26216.0019 | 0.0042218 | #N/A | #N/A
179 | EL CERRITO G 1108BR346 | 12501108 | EL CERRITO G 1108 | 0 | 102 | 1.5894e-06 | 0.00016212 | 3545 | 26216.0019 | 0.0040597 | #N/A | #N/A
1332 | HOLLYWOOD 0401CB | 13170401 | HOLLYWOOD 0401 | 2.862 | 70 | 1.5619e-06 | 0.00010933 | 3546 | 26218.8639 | 0.0039504 | #N/A | #N/A
6502 | ESTUDILLO 0401850884 | 13480401 | ESTUDILLO 0401 | 0.85032 | 19 | 1.5552e-06 | 2.9549e-05 | 3547 | 26219.7142 | 0.0039208 | #N/A | #N/A
1386 | PACIFICA 1103915474 | 22811103 | PACIFICA 1103 | 0.43345 | 98 | 1.5073e-06 | 0.00014771 | 3548 | 26220.1476 | 0.0037731 | #N/A | #N/A
1210 | COTATI 110283200 | 42271102 | COTATI 1102 | 0 | 48 | 1.471e-06 | 7.0606e-05 | 3549 | 26220.1476 | 0.0037025 | #N/A | #N/A
7453 | SNEATH LANE 110748338 | 22721107 | SNEATH LANE 1107 | 0.11259 | 17 | 1.4569e-06 | 2.4768e-05 | 3550 | 26220.2602 | 0.0036777 | #N/A | #N/A
4821 | RALSTON 11029126 | 24141102 | RALSTON 1102 | 1.0077 | 25 | 1.4329e-06 | 3.5823e-05 | 3551 | 26221.2679 | 0.0036419 | #N/A | #N/A
7237 | PACIFIC GROVE 04222614 | 182440422 | PACIFIC GROVE 0422 | 0.64463 | 28 | 1.4317e-06 | 4.0087e-05 | 3552 | 26221.9126 | 0.0036018 | #N/A | #N/A
1100 | DEL MONTE 210386496 | 182222103 | DEL MONTE 2103 | 0.99474 | 94 | 1.4269e-06 | 0.00013413 | 3553 | 26222.9073 | 0.0034677 | #N/A | #N/A
8851 | SAN CARLOS 1103888954 | 24181103 | SAN CARLOS 1103 | 0 | 6 | 1.4152e-06 | 8.4914e-06 | 3554 | 26222.9073 | 0.0034592 | #N/A | #N/A
2645 | OAKLAND J 1106CR164 | 12091106 | OAKLAND J 1106 | 1.495 | 85 | 1.4079e-06 | 0.00011967 | 3555 | 26224.4023 | 0.0033395 | #N/A | #N/A
7417 | EL CERRITO G 1112209865 | 12501112 | EL CERRITO G 1112 | 0.2629 | 11 | 1.4074e-06 | 1.5482e-05 | 3556 | 26224.6652 | 0.003324 | #N/A | #N/A
45 | OAKLAND J 1105153228 | 12091105 | OAKLAND J 1105 | 0.28806 | 54 | 1.4041e-06 | 7.5821e-05 | 3557 | 26224.9532 | 0.0032482 | #N/A | #N/A
8437 | SWIFT 2109XR300 | 83392109 | SWIFT 2109 | 0.32738 | 14 | 1.3951e-06 | 1.9531e-05 | 3558 | 26225.2806 | 0.0032287 | #N/A | #N/A
10517 | EL CERRITO G 1110173396 | 12501110 | EL CERRITO G 1110 | 0.16516 | 3 | 1.3889e-06 | 4.1666e-06 | 3559 | 26225.4458 | 0.0032245 | #N/A | #N/A
9170 | SAN CARLOS 1103313472 | 24181103 | SAN CARLOS 1103 | 0.026825 | 9 | 1.3509e-06 | 1.2158e-05 | 3560 | 26225.4726 | 0.0032124 | #N/A | #N/A
9880 | IGNACIO 1103151462 | 42481103 | IGNACIO 1103 | 0.15399 | 3 | 1.3417e-06 | 4.025e-06 | 3561 | 26225.6266 | 0.0032083 | #N/A | #N/A
8103 | WOODSIDE 1102472928 | 24251102 | WOODSIDE 1102 | 0.077579 | 14 | 1.3331e-06 | 1.8663e-05 | 3562 | 26225.7042 | 0.0031897 | #N/A | #N/A
657 | OAKLAND J 1102CR252 | 12091102 | OAKLAND J 1102 | 1.0971 | 92 | 1.3184e-06 | 0.0001213 | 3563 | 26226.8013 | 0.0030684 | #N/A | #N/A
146 | CASTRO VALLEY 1110MR379 | 14091110 | CASTRO VALLEY 1110 | 1.0874 | 22 | 1.3088e-06 | 2.8794e-05 | 3564 | 26227.8887 | 0.0030396 | #N/A | #N/A
9441 | MORRO BAY 11013487 | 183011101 | MORRO BAY 1101 | 0 | 20 | 1.2622e-06 | 2.5244e-05 | 3565 | 26227.8887 | 0.0030143 | #N/A | #N/A
5751 | FORT BRAGG A 1104CB | 42761104 | FORT BRAGG A 1104 | 0.0738 | 41 | 1.2596e-06 | 5.1642e-05 | 3566 | 26227.9625 | 0.0029627 | #N/A | #N/A
8075 | ALTO 1124246034 | 42031124 | ALTO 1124 | 0.12572 | 4 | 1.2578e-06 | 5.0314e-06 | 3567 | 26228.0882 | 0.0029577 | #N/A | #N/A
447 | OCEANO 1105V44 | 182601105 | OCEANO 1105 | 0.78295 | 17 | 1.2575e-06 | 2.1378e-05 | 3568 | 26228.8711 | 0.0029363 | #N/A | #N/A
3262 | OAKLAND J 1106CR330 | 12091106 | OAKLAND J 1106 | 0.7182 | 31 | 1.2463e-06 | 3.8635e-05 | 3569 | 26229.5893 | 0.0028977 | #N/A | #N/A
650 | OAKLAND J 1116CR328 | 12091116 | OAKLAND J 1116 | 0.59424 | 68 | 1.2458e-06 | 8.4712e-05 | 3570 | 26230.1836 | 0.0028129 | #N/A | #N/A
4530 | VIEJO 220285904 | 182852202 | VIEJO 2202 | 1.0472 | 24 | 1.2443e-06 | 2.9864e-05 | 3571 | 26231.2308 | 0.0027831 | #N/A | #N/A
4873 | ALHAMBRA 110213333 | 14101102 | ALHAMBRA 1102 | 0.043994 | 4 | 1.2398e-06 | 4.9594e-06 | 3572 | 26231.2748 | 0.0027781 | #N/A | #N/A
5686 | MORRO BAY 1102V80 | 183011102 | MORRO BAY 1102 | 0.13844 | 28 | 1.2121e-06 | 3.3939e-05 | 3573 | 26231.4132 | 0.0027442 | #N/A | #N/A
495 | BELMONT 11109090 | 24031110 | BELMONT 1110 | 0 | 38 | 1.2039e-06 | 4.5748e-05 | 3574 | 26231.4132 | 0.0026984 | #N/A | #N/A
1032 | ALTO 1123CB | 42031123 | ALTO 1123 | 0.5554 | 84 | 1.1648e-06 | 9.7839e-05 | 3575 | 26231.9686 | 0.0026006 | #N/A | #N/A
4356 | BELMONT 11038956 | 24031103 | BELMONT 1103 | 0.29497 | 18 | 1.1529e-06 | 2.0752e-05 | 3576 | 26232.2636 | 0.0025798 | #N/A | #N/A
3862 | GREENBRAE 1104751 | 43091104 | GREENBRAE 1104 | 0.16446 | 31 | 1.1521e-06 | 3.5714e-05 | 3577 | 26232.4281 | 0.0025441 | #N/A | #N/A
3522 | CHESTER 1101CB | 103181101 | CHESTER 1101 | 0.080148 | 69 | 1.1453e-06 | 7.9023e-05 | 3578 | 26232.5082 | 0.0024651 | #N/A | #N/A
1797 | BERKELEY F 1103BR110 | 12061103 | BERKELEY F 1103 | 0 | 45 | 1.1415e-06 | 5.1365e-05 | 3579 | 26232.5082 | 0.0024137 | #N/A | #N/A
3950 | MONTEREY 04022644 | 182090402 | MONTEREY 0402 | 1.1362 | 23 | 1.1355e-06 | 2.6115e-05 | 3580 | 26233.6444 | 0.0023876 | #N/A | #N/A
3110 | KIRKER 2104CB | 14452104 | KIRKER 2104 | 0.04631 | 140 | 1.1257e-06 | 0.0001576 | 3581 | 26233.6907 | 0.00223 | #N/A | #N/A
973 | DEL MONTE 110138582 | 182221101 | DEL MONTE 1101 | 0.53069 | 53 | 1.1245e-06 | 5.9598e-05 | 3582 | 26234.2214 | 0.0021704 | #N/A | #N/A
72 | PACIFICA 11026783 | 22811102 | PACIFICA 1102 | 0 | 50 | 1.1229e-06 | 5.6147e-05 | 3583 | 26234.2214 | 0.0021143 | #N/A | #N/A
6129 | PERRY 1101W12 | 183071101 | PERRY 1101 | 3.7577 | 70 | 1.0833e-06 | 7.5829e-05 | 3584 | 26237.9791 | 0.0020385 | #N/A | #N/A
3828 | ALTO 1120500 | 42031120 | ALTO 1120 | 0.2649 | 39 | 1.0777e-06 | 4.203e-05 | 3585 | 26238.244 | 0.0019964 | #N/A | #N/A
2036 | SAN LEANDRO U 1114MR218 | 13111114 | SAN LEANDRO U 1114 | 6.4554 | 134 | 1.0693e-06 | 0.00014329 | 3586 | 26244.6994 | 0.0018531 | #N/A | #N/A
66 | OAKLAND X 1105CB | 12541105 | OAKLAND X 1105 | 1.0411 | 153 | 1.0578e-06 | 0.00016184 | 3587 | 26245.7405 | 0.0016913 | #N/A | #N/A
3740 | BERKELEY F 0402CB | 12060402 | BERKELEY F 0402 | 0.029225 | 21 | 1.0552e-06 | 2.2159e-05 | 3588 | 26245.7698 | 0.0016691 | #N/A | #N/A
2665 | VALLEY VIEW 1105P190 | 14341105 | VALLEY VIEW 1105 | 0 | 28 | 1.0539e-06 | 2.951e-05 | 3589 | 26245.7698 | 0.0016396 | #N/A | #N/A
62 | BAY MEADOWS 2102CB | 24012102 | BAY MEADOWS 2102 | 0.099037 | 95 | 1.0373e-06 | 9.8546e-05 | 3590 | 26245.8688 | 0.0015411 | #N/A | #N/A
3225 | VALLEY VIEW 1105CB | 14341105 | VALLEY VIEW 1105 | 0 | 59 | 1.0169e-06 | 5.9995e-05 | 3591 | 26245.8688 | 0.0014811 | #N/A | #N/A
1682 | OAKLAND J 1118CR198 | 12091118 | OAKLAND J 1118 | 0.32037 | 70 | 1.006e-06 | 7.0418e-05 | 3592 | 26246.1892 | 0.0014107 | #N/A | #N/A
6551 | EL CERRITO G 1111760530 | 12501111 | EL CERRITO G 1111 | 0.21291 | 13 | 9.624e-07 | 1.2511e-05 | 3593 | 26246.4021 | 0.0013982 | #N/A | #N/A
838 | MORRO BAY 1102W22 | 183011102 | MORRO BAY 1102 | 2.5943 | 85 | 9.5877e-07 | 8.1495e-05 | 3594 | 26248.9964 | 0.0013167 | #N/A | #N/A
2660 | CASTRO VALLEY 1105MR201 | 14091105 | CASTRO VALLEY 1105 | 1.252 | 112 | 9.5698e-07 | 0.00010718 | 3595 | 26250.2483 | 0.0012095 | #N/A | #N/A
6961 | SAUSALITO 11021224 | 42491102 | SAUSALITO 1102 | 0.010738 | 29 | 9.3531e-07 | 2.7124e-05 | 3596 | 26250.2591 | 0.0011824 | #N/A | #N/A
2515 | EL CERRITO G 1113CB | 12501113 | EL CERRITO G 1113 | 0.098306 | 63 | 9.1814e-07 | 5.7843e-05 | 3597 | 26250.3574 | 0.0011245 | #N/A | #N/A
3037 | EL CERRITO G 1108CB | 12501108 | EL CERRITO G 1108 | 0.0026991 | 99 | 9.0819e-07 | 8.9911e-05 | 3598 | 26250.3601 | 0.0010346 | #N/A | #N/A
2758 | VALLEY VIEW 1105P124 | 14341105 | VALLEY VIEW 1105 | 0 | 43 | 9.0411e-07 | 3.8877e-05 | 3599 | 26250.3601 | 0.00099572 | #N/A | #N/A
3672 | EDES 1112CB | 13681112 | EDES 1112 | 0.043792 | 16 | 8.9903e-07 | 1.4384e-05 | 3600 | 26250.4039 | 0.00098134 | #N/A | #N/A
2376 | VIEJO 22049110 | 182852204 | VIEJO 2204 | 0.29392 | 58 | 8.7872e-07 | 5.0966e-05 | 3601 | 26250.6978 | 0.00093037 | #N/A | #N/A
552 | ALTO 112088190 | 42031120 | ALTO 1120 | 0.10133 | 34 | 8.5763e-07 | 2.9159e-05 | 3602 | 26250.7991 | 0.00090121 | #N/A | #N/A
5498 | VIEJO 22049440 | 182852204 | VIEJO 2204 | 0.076905 | 55 | 8.5438e-07 | 4.6991e-05 | 3603 | 26250.876 | 0.00085422 | #N/A | #N/A
10858 | SOLEDAD 2101125484 | 182052101 | SOLEDAD 2101 | 0.74739 | 4 | 8.4928e-07 | 3.3971e-06 | 3604 | 26251.6234 | 0.00085082 | #N/A | #N/A
10655 | OCEANO 1104793774 | 182601104 | OCEANO 1104 | 0.069539 | 3 | 8.3998e-07 | 2.52e-06 | 3605 | 26251.6929 | 0.0008483 | #N/A | #N/A
4160 | EL CERRITO G 1110CB | 12501110 | EL CERRITO G 1110 | 0.26297 | 35 | 8.2339e-07 | 2.8819e-05 | 3606 | 26251.9559 | 0.00081949 | #N/A | #N/A
5087 | EDES 1112714759 | 13681112 | EDES 1112 | 0.22493 | 11 | 8.1071e-07 | 8.9178e-06 | 3607 | 26252.1808 | 0.00081057 | #N/A | #N/A
2691 | BOSTON 0401CR242 | 13320401 | BOSTON 0401 | 0.31043 | 59 | 8.0537e-07 | 4.7517e-05 | 3608 | 26252.4913 | 0.00076305 | #N/A | #N/A
425 | CASTRO VALLEY 1105MR236 | 14091105 | CASTRO VALLEY 1105 | 1.3753 | 112 | 8.0193e-07 | 8.9816e-05 | 3609 | 26253.8666 | 0.00067323 | #N/A | #N/A
5569 | MORRO BAY 1101CB | 183011101 | MORRO BAY 1101 | 0 | 28 | 8.0102e-07 | 2.2429e-05 | 3610 | 26253.8666 | 0.00065081 | #N/A | #N/A
513 | OAKLAND J 1116CB | 12091116 | OAKLAND J 1116 | 0 | 253 | 7.8965e-07 | 0.00019978 | 3611 | 26253.8666 | 0.00045102 | #N/A | #N/A
4433 | MONTEREY 04012642 | 182090401 | MONTEREY 0401 | 0 | 28 | 7.8793e-07 | 2.2062e-05 | 3612 | 26253.8666 | 0.00042896 | #N/A | #N/A
1060 | SAN LEANDRO U 1114MR545 | 13111114 | SAN LEANDRO U 1114 | 2.1728 | 66 | 7.6919e-07 | 5.0766e-05 | 3613 | 26256.0394 | 0.0003782 | #N/A | #N/A
8159 | SAN LUIS OBISPO 1103191498 | 182631103 | SAN LUIS OBISPO 1103 | 0.118 | 2 | 7.2794e-07 | 1.4559e-06 | 3614 | 26256.1574 | 0.00037674 | #N/A | #N/A
749 | WALDO 0401CB | 13350401 | WALDO 0401 | 0 | 56 | 6.8547e-07 | 3.8386e-05 | 3615 | 26256.1574 | 0.00033835 | #N/A | #N/A
8960 | OCEANO 1104337754 | 182601104 | OCEANO 1104 | 0.060732 | 3 | 6.1054e-07 | 1.8316e-06 | 3616 | 26256.2181 | 0.00033652 | #N/A | #N/A
11035 | SOLEDAD 2101404754 | 182052101 | SOLEDAD 2101 | 0.86267 | 2 | 5.7048e-07 | 1.141e-06 | 3617 | 26257.0808 | 0.00033538 | #N/A | #N/A
2616 | DEL MONTE 21029060 | 182222102 | DEL MONTE 2102 | 0.94774 | 98 | 5.5361e-07 | 5.4254e-05 | 3618 | 26258.0285 | 0.00028113 | #N/A | #N/A
3316 | SAN LEANDRO U 1114501762 | 13111114 | SAN LEANDRO U 1114 | 0.4817 | 23 | 5.5098e-07 | 1.2672e-05 | 3619 | 26258.5102 | 0.00026845 | #N/A | #N/A
9297 | PACIFICA 1102934870 | 22811102 | PACIFICA 1102 | 0.091704 | 7 | 5.496e-07 | 3.8472e-06 | 3620 | 26258.602 | 0.00026461 | #N/A | #N/A
7940 | SAN LEANDRO U 1109CR284 | 13111109 | SAN LEANDRO U 1109 | 0.76807 | 14 | 5.1364e-07 | 7.191e-06 | 3621 | 26259.37 | 0.00025742 | #N/A | #N/A
3930 | SAN LEANDRO U 1109CR002 | 13111109 | SAN LEANDRO U 1109 | 0.16771 | 16 | 5.1358e-07 | 8.2173e-06 | 3622 | 26259.5377 | 0.0002492 | #N/A | #N/A
5801 | BELMONT 1110330790 | 24031110 | BELMONT 1110 | 0.12403 | 8 | 5.0999e-07 | 4.0799e-06 | 3623 | 26259.6618 | 0.00024512 | #N/A | #N/A
915 | WALDO 0402CB | 13350402 | WALDO 0402 | 0 | 27 | 5.064e-07 | 1.3673e-05 | 3624 | 26259.6618 | 0.00023145 | #N/A | #N/A
472 | BANCROFT 0401CB | 13030401 | BANCROFT 0401 | 0.043075 | 103 | 4.9968e-07 | 5.1467e-05 | 3625 | 26259.7048 | 0.00017998 | #N/A | #N/A
4940 | BERKELEY T 0404CB | 12660404 | BERKELEY T 0404 | 0 | 20 | 4.9106e-07 | 9.8213e-06 | 3626 | 26259.7048 | 0.00017016 | #N/A | #N/A
206 | PACIFICA 110252715 | 22811102 | PACIFICA 1102 | 0 | 60 | 4.8039e-07 | 2.8824e-05 | 3627 | 26259.7048 | 0.00014133 | #N/A | #N/A
4875 | OCEANO 1105V48 | 182601105 | OCEANO 1105 | 0.12351 | 39 | 4.6154e-07 | 1.8e-05 | 3628 | 26259.8283 | 0.00012333 | #N/A | #N/A
3910 | SAN LEANDRO U 1114458451 | 13111114 | SAN LEANDRO U 1114 | 1.2228 | 29 | 4.5289e-07 | 1.3134e-05 | 3629 | 26261.0511 | 0.0001102 | #N/A | #N/A
1300 | BANCROFT 0402CB | 13030402 | BANCROFT 0402 | 0.37117 | 58 | 4.3467e-07 | 2.5211e-05 | 3630 | 26261.4223 | 8.4989e-05 | #N/A | #N/A
1186 | VIEJO 220436948 | 182852204 | VIEJO 2204 | 0.50319 | 109 | 3.9816e-07 | 4.34e-05 | 3631 | 26261.9255 | 4.1589e-05 | #N/A | #N/A
8981 | CASTRO VALLEY 1105132304 | 14091105 | CASTRO VALLEY 1105 | 0.07375 | 13 | 3.785e-07 | 4.9205e-06 | 3632 | 26261.9992 | 3.6669e-05 | #N/A | #N/A
3358 | FORT BRAGG A 110436526 | 42761104 | FORT BRAGG A 1104 | 0.044913 | 84 | 3.6398e-07 | 3.0574e-05 | 3633 | 26262.0442 | 6.0945e-06 | #N/A | #N/A
6760 | MORRO BAY 1101W04 | 183011101 | MORRO BAY 1101 | 0.27175 | 26 | 2.344e-07 | 6.0945e-06 | 3634 | 26262.3159 | 2.6486e-11 | #N/A | #N/A
11118 | DIABLO CANYON 1101CB | 189001101 | DIABLO CANYON 1101 | 0 |  |  | 0 | 3635 | 26262.3159 | 2.6486e-11 | #N/A | #N/A

## Approved CPZ List
Unique ID for each Circuit Protection Zone. | Unique name for each Circuit Protection Zone. | Unique ID for each circuit. | Unique name for each circuit. | Total miles in each . | Number of 100mx100m pixels in each CPZ. As the risk model has the risk score at this 100mx100m pixel level | Average - Multi Attribute Value Framework (MAVF) risk score per pixel; used to rank the CPZs from riskiest to least risky. The MAVF developed via regulatory proceedings | Total risk associated with each CPZ, per the 2021 approved conductor risk model. | Rank of CPZs based on the average risk score (mean_mavf_core_risk). | Number of active projects / jobs within the CPZ. | Number of miles being hardened within each CPZ, as of the latest revision. | Number of miles in the scoping phase. | Number of miles in the estimating phase. | Number of miles in the decency clearing phase. | Number of miles in the construction phase. | Number of miles in the close-out phase. | Justification for approval of work in the CPZ by WGC. | Date work was approved for scoping by the WGC.
PZ_idx | circuit_protection_zone_id | feeder_id | feeder_name | Miles | pixel_count | mean_mavf_core_risk | Total Risk Value | mean_mavf_core_risk_rank | Number of Projects | Residual Miles | Scoping | Estimating | Dependencies | Construction | Close-out | Work Bucket | Date Approved
10544 | OREGON TRAIL 1103CUS391 | 103521103 | OREGON TRAIL 1103 | 0.022596 | 1 | 3.1639 | 3.1639 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
11024 | CALPINE 1144276-G | 48011144 | CALPINE 1144 | 0.014759 | 1 | 1.8786 | 1.8786 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
9665 | MARIPOSA 210190130 | 254452101 | MARIPOSA 2101 | 0.09394 | 1 | 1.6924 | 1.6924 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
9783 | SHEPHERD 2111688294 | 252062111 | SHEPHERD 2111 | 0.01514 | 1 | 1.4425 | 1.4425 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10354 | MIDDLETOWN 1103CB | 43141103 | MIDDLETOWN 1103 | 0.052975 | 4 | 1.3006 | 5.2026 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10600 | UPPER LAKE 1101CB | 42871101 | UPPER LAKE 1101 | 1.1133 | 3 | 1.2559 | 3.7676 | 6 | 1 | 1.1055 | 1.1055 | 0 | 0 | 0 | 0 | Top 50 Miles | 2020-11-13
8894 | KESWICK 11011586 | 103451101 | KESWICK 1101 | 7.4478 | 39 | 1.2524 | 48.8434 | 7 | 6 | 9.1078 | 9.1078 | 0 | 0 | 0 | 0 | Top 50 Miles | 2020-11-13
6776 | MIDDLETOWN 1102302610 | 43141102 | MIDDLETOWN 1102 | 4.7058 | 53 | 0.91632 | 48.565 | 8 | 7 | 6.8034 | 6.8034 | 0 | 0 | 0 | 0 | Top 50 Miles | 2020-11-13
2373 | KONOCTI 1102965078 | 43311102 | KONOCTI 1102 | 6.2704 | 59 | 0.87629 | 51.7008 | 9 | 3 | 3.1468 | 0 | 3.1468 | 0 | 0 | 0 | Top 50 Miles | 2020-11-13
5527 | MARIPOSA 2102241564 | 254452102 | MARIPOSA 2102 | 0.71281 | 14 | 0.77248 | 10.8148 | 10 | 1 | 0.71 | 0 | 0.71 | 0 | 0 | 0 | Top 50 Miles | 2020-11-13
7968 | BUCKS CREEK 1101CB | 102211101 | BUCKS CREEK 1101 | 4.8008 | 13 | 0.73491 | 9.5539 | 11 | 3 | 5.4104 | 0 | 5.4104 | 0 | 0 | 0 | Top 50 Miles | 2020-11-13
10918 | DEL MAR 2109378446 | 152582109 | DEL MAR 2109 | 0.098166 | 3 | 0.73151 | 2.1945 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
6966 | MIDDLETOWN 1102CB | 43141102 | MIDDLETOWN 1102 | 0.46739 | 12 | 0.72481 | 8.6977 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
3511 | MIDDLETOWN 1103830 | 43141103 | MIDDLETOWN 1103 | 27.7328 | 212 | 0.71618 | 151.8291 | 14 | 19 | 23.9445 | 23.9445 | 0 | 0 | 0 | 0 | Top 50 Miles | 2020-11-13
9537 | POSO MOUNTAIN 2104CB | 253642104 | POSO MOUNTAIN 2104 | 5.3534 | 38 | 0.70423 | 26.7607 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10827 | INDIAN FLAT 11044440 | 252691104 | INDIAN FLAT 1104 | 0.23386 | 4 | 0.68656 | 2.7463 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10242 | ELK CREEK 1101CB | 102781101 | ELK CREEK 1101 | 0.084235 | 1 | 0.67079 | 0.67079 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
5791 | TIDEWATER 210614072 | 14652106 | TIDEWATER 2106 | 3.6652 | 30 | 0.65331 | 19.5994 | 18 | 3 | 3.64 | 2.44 | 1.2 | 0 | 0 | 0 | Top 50 Miles | 2020-11-13
10735 | HARTLEY 1101980662 | 43211101 | HARTLEY 1101 | 0.22763 | 3 | 0.64187 | 1.9256 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10532 | VACA DIXON 1101126774 | 63591101 | VACA DIXON 1101 | 0.78766 | 11 | 0.62029 | 6.8232 | 20 | 1 | 0.39811 | 0 | 0 | 0.39811 | 0 | 0 | Top 250 Miles | 2020-11-13
10277 | KIRKER 2104442850 | 14452104 | KIRKER 2104 | 5.7542 | 30 | 0.61454 | 18.4361 | 21 | 2 | 5.44 | 5.44 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
8742 | COARSEGOLD 2104CB | 254432104 | COARSEGOLD 2104 | 2.4277 | 27 | 0.59573 | 16.0848 | 22 | 4 | 8.2815 | 0 | 8.2815 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
8905 | MIDDLETOWN 1101118494 | 43141101 | MIDDLETOWN 1101 | 1.0659 | 12 | 0.58092 | 6.971 | 23 | 2 | 1.33 | 0.61 | 0.72 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10515 | STAFFORD 1102784704 | 43201102 | STAFFORD 1102 | 0.027274 | 1 | 0.564 | 0.564 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10181 | PEABODY 2108113684 | 63642108 | PEABODY 2108 | 0.36709 | 4 | 0.55276 | 2.211 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
7688 | PEABODY 2106250154 | 63642106 | PEABODY 2106 | 0.28499 | 4 | 0.55243 | 2.2097 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
7743 | HIGHLANDS 1102628 | 43361102 | HIGHLANDS 1102 | 14.2224 | 51 | 0.5487 | 27.9838 | 27 | 13 | 23.057 | 23.057 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
6480 | TASSAJARA 21123202 | 14662112 | TASSAJARA 2112 | 0.39174 | 9 | 0.53731 | 4.8358 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10043 | WYANDOTTE 110932586 | 102911109 | WYANDOTTE 1109 | 1.3417 | 15 | 0.52987 | 7.9481 | 29 | 2 | 1.3019 | 0.45758 | 0.84432 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10052 | POSO MOUNTAIN 2103CB | 253642103 | POSO MOUNTAIN 2103 | 2.3287 | 10 | 0.51619 | 5.1619 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10924 | CALPINE 1146200-G | 48011146 | CALPINE 1146 | 0.0085246 | 1 | 0.50979 | 0.50979 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
11090 | CALPINE 1146394G | 48011146 | CALPINE 1146 | 0.011292 | 1 | 0.50979 | 0.50979 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
4828 | CRESTA 1101546650 | 102251101 | CRESTA 1101 | 0.89694 | 6 | 0.50291 | 3.0174 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
9923 | CLOVERDALE 110247214 | 42821102 | CLOVERDALE 1102 | 0.027329 | 1 | 0.48427 | 0.48427 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
8034 | MARIPOSA 2102CB | 254452102 | MARIPOSA 2102 | 5.2539 | 31 | 0.47165 | 14.6212 | 35 | 2 | 2.85 | 0 | 2.85 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
7873 | MARIPOSA 210197142 | 254452101 | MARIPOSA 2101 | 4.6029 | 40 | 0.47122 | 18.8487 | 36 | 4 | 4.5636 | 0 | 3.1011 | 1.4625 | 0 | 0 | Top 250 Miles | 2020-11-13
4526 | VACA DIXON 110540092 | 63591105 | VACA DIXON 1105 | 23.1653 | 464 | 0.46772 | 217.022 | 37 | 12 | 30.58 | 30.58 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
2215 | MIDDLETOWN 1101481876 | 43141101 | MIDDLETOWN 1101 | 0.8534 | 14 | 0.46769 | 6.5476 | 38 | 1 | 0.85436 | 0 | 0.85436 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
9655 | VOLTA 110149742 | 102541101 | VOLTA 1101 | 3.4766 | 28 | 0.46433 | 13.0013 | 39 | 1 | 3.461 | 0 | 3.461 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10699 | SUNOL 110148180 | 14241101 | SUNOL 1101 | 0.013145 | 2 | 0.46103 | 0.92206 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
7414 | PUTAH CREEK 110246012 | 63681102 | PUTAH CREEK 1102 | 0.63713 | 38 | 0.45557 | 17.3115 | 41 | 1 | 0.52 | 0 | 0 | 0.52 | 0 | 0 | Top 250 Miles | 2020-11-13
4076 | VACAVILLE 11046542 | 63601104 | VACAVILLE 1104 | 14.6602 | 140 | 0.44642 | 62.4985 | 42 | 11 | 14.73 | 14.73 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
7056 | POTTER VALLEY P H 110564118 | 42281105 | POTTER VALLEY P H 1105 | 1.6451 | 101 | 0.44262 | 44.7046 | 43 | 2 | 1.8343 | 1.8343 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10934 | POINT MORETTI 1101CB | 82931101 | POINT MORETTI 1101 | 0.012787 | 1 | 0.44218 | 0.44218 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
5032 | MOUNTAIN QUARRIES 21016953 | 152282101 | MOUNTAIN QUARRIES 2101 | 5.7104 | 58 | 0.4353 | 25.2473 | 45 | 3 | 5.95 | 5.95 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
9729 | BRENTWOOD 210596324 | 14592105 | BRENTWOOD 2105 | 0.48214 | 6 | 0.4317 | 2.5902 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
6662 | NORTH DUBLIN 2101CB | 14052101 | NORTH DUBLIN 2101 | 1.7629 | 23 | 0.42859 | 9.8576 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
1690 | DESCHUTES 11049718 | 103351104 | DESCHUTES 1104 | 18.6049 | 357 | 0.42526 | 151.8163 | 48 | 7 | 18.3011 | 18.3011 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
193 | OREGON TRAIL 110335002 | 103521103 | OREGON TRAIL 1103 | 57.1429 | 641 | 0.42185 | 270.4028 | 49 | 41 | 62.2442 | 62.2442 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
7274 | MARIPOSA 2102440236 | 254452102 | MARIPOSA 2102 | 4.2727 | 38 | 0.4205 | 15.979 | 50 | 3 | 8.59 | 8.59 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10024 | CLEAR LAKE 1101881362 | 42141101 | CLEAR LAKE 1101 | 0.29834 | 10 | 0.41959 | 4.1959 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
7141 | WILDWOOD 11011454 | 103611101 | WILDWOOD 1101 | 7.8323 | 31 | 0.41883 | 12.9837 | 52 | 5 | 7.87 | 5.41 | 2.46 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
7033 | VACA DIXON 1105965390 | 63591105 | VACA DIXON 1105 | 0.75147 | 21 | 0.41415 | 8.6971 | 53 | 1 | 0.75 | 0.75 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
9936 | OLETA 1101754718 | 163541101 | OLETA 1101 | 2.8841 | 29 | 0.40712 | 11.8066 | 54 | 2 | 3.01 | 3.01 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10113 | CALISTOGA 1101CB | 42711101 | CALISTOGA 1101 | 0.13777 | 9 | 0.40561 | 3.6505 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
3943 | MOUNTAIN QUARRIES 2101CB | 152282101 | MOUNTAIN QUARRIES 2101 | 24.9941 | 262 | 0.38665 | 101.3032 | 68 | 1 | 0.43087 | 0.43087 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
4693 | MIDDLETOWN 1101CB | 43141101 | MIDDLETOWN 1101 | 4.731 | 146 | 0.36174 | 52.8144 | 86 | 1 | 0.53485 | 0 | 0.53485 | 0 | 0 | 0 | ECOP - Top 20% | 2020-11-13
5717 | SHINGLE SPRINGS 210935598 | 153652109 | SHINGLE SPRINGS 2109 | 10.847 | 122 | 0.27855 | 33.9836 | 159 | 5 | 12.5941 | 4.3231 | 8.271 | 0 | 0 | 0 | Top 20% MAVF CPZ | 2020-11-13
8139 | LAS GALLINAS A 110599904 | 42991105 | LAS GALLINAS A 1105 | 5.5621 | 54 | 0.25006 | 13.5032 | 215 | 2 | 2.7962 | 2.7962 | 0 | 0 | 0 | 0 | ECOP - Top 20% | 2020-11-13
6909 | WYANDOTTE 1109702710 | 102911109 | WYANDOTTE 1109 | 2.6641 | 49 | 0.24845 | 12.174 | 218 | 1 | 0.60739 | 0.60739 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
2854 | SHINGLE SPRINGS 21099372 | 153652109 | SHINGLE SPRINGS 2109 | 17.8687 | 190 | 0.24281 | 46.1342 | 227 | 12 | 17.5703 | 3.3186 | 13.6517 | 0.6 | 0 | 0 | Top 20% MAVF CPZ | 2020-11-13
1039 | SILVERADO 2104726 | 43432104 | SILVERADO 2104 | 30.3762 | 263 | 0.22347 | 58.7725 | 279 | 6 | 6.1621 | 3.3867 | 2.7754 | 0 | 0 | 0 | ECOP - Top 20% | 2020-11-13
1293 | MIDDLETOWN 11014646 | 43141101 | MIDDLETOWN 1101 | 18.5633 | 165 | 0.19983 | 32.9712 | 328 | 2 | 2.3492 | 0 | 2.3492 | 0 | 0 | 0 | ECOP - Top 20% | 2020-11-13
6545 | TULUCAY 1101628 | 42301101 | TULUCAY 1101 | 4.1726 | 98 | 0.19686 | 19.2923 | 338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 20% MAVF CPZ | 2020-11-13
8575 | ELK CREEK 11012106 | 102781101 | ELK CREEK 1101 | 13.2402 | 67 | 0.1961 | 13.1388 | 340 | 1 | 7.9 | 7.9 | 0 | 0 | 0 | 0 | FRRB - REMG - 2021 | 2020-11-13
8166 | BANGOR 1101CB | 103191101 | BANGOR 1101 | 18.7561 | 171 | 0.19378 | 33.1366 | 355 | 1 | 0.85 | 0.85 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
449 | CLAYTON 221296224 | 12022212 | CLAYTON 2212 | 19.3992 | 174 | 0.18755 | 32.6329 | 377 | 2 | 2.8186 | 0 | 2.8186 | 0 | 0 | 0 | ECOP - Top 20% | 2020-11-13
2810 | OAKHURST 110110090 | 254421101 | OAKHURST 1101 | 44.0886 | 435 | 0.17437 | 75.8506 | 421 | 1 | 1.39 | 1.39 | 0 | 0 | 0 | 0 | Remote Grid Pilot | 2020-12-18
50 | MARIPOSA 210135244 | 254452101 | MARIPOSA 2101 | 17.4635 | 146 | 0.17286 | 25.237 | 428 | 1 | 0.84 | 0.84 | 0 | 0 | 0 | 0 | Remote Grid Pilot | 2020-12-18
652 | MIDDLETOWN 110148212 | 43141101 | MIDDLETOWN 1101 | 10.6994 | 110 | 0.1603 | 17.6327 | 468 | 13 | 15.3455 | 15.3455 | 0 | 0 | 0 | 0 | ECOP - Top 20% | 2020-11-13
932 | MIDDLETOWN 1101548 | 43141101 | MIDDLETOWN 1101 | 27.4082 | 298 | 0.15935 | 47.4878 | 474 | 34 | 28.3644 | 22.6626 | 5.7018 | 0 | 0 | 0 | ECOP - Top 20% | 2020-11-13
5391 | FITCH MOUNTAIN 111324918 | 42751113 | FITCH MOUNTAIN 1113 | 5.4965 | 49 | 0.1575 | 7.7177 | 481 | 1 | 5.4458 | 0 | 0 | 0 | 5.4458 | 0 | In-Construction | 2020-12-01
5806 | COLUMBIA HILL 11012212 | 152471101 | COLUMBIA HILL 1101 | 9.1336 | 76 | 0.12922 | 9.8207 | 606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 20% MAVF CPZ | 2020-11-13
3234 | FULTON 1107604 | 42561107 | FULTON 1107 | 17.4386 | 169 | 0.12169 | 20.5661 | 637 | 5 | 4.015 | 2.3578 | 1.6572 | 0 | 0 | 0 | ECOP - Top 20% | 2020-11-13
8080 | SILVERADO 210258626 | 43432102 | SILVERADO 2102 | 15.2217 | 125 | 0.117 | 14.6249 | 663 | 2 | 3.5445 | 0 | 3.5445 | 0 | 0 | 0 | ECOP - Top 20% | 2020-11-13
772 | DIAMOND SPRINGS 11052102 | 152261105 | DIAMOND SPRINGS 1105 | 37.4816 | 417 | 0.11621 | 48.4576 | 666 | 1 | 1.6339 | 1.6339 | 0 | 0 | 0 | 0 | Top 20% MAVF CPZ | 2020-11-13
2133 | FROGTOWN 17011623 | 163451701 | FROGTOWN 1701 | 15.2605 | 152 | 0.1076 | 16.3546 | 721 | 1 | 0.59 | 0 | 0 | 0.59 | 0 | 0 | Top 20% MAVF CPZ | 2020-11-13
837 | DIAMOND SPRINGS 11071402 | 152261107 | DIAMOND SPRINGS 1107 | 44.1915 | 541 | 0.092281 | 49.924 | 811 | 3 | 8.465 | 1.0972 | 7.3678 | 0 | 0 | 0 | ECOP | 2020-12-11
3279 | OAKHURST 1101CB | 254421101 | OAKHURST 1101 | 2.3149 | 47 | 0.086583 | 4.0694 | 847 | 1 | 0.052083 | 0 | 0 | 0.052083 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
7502 | FITCH MOUNTAIN 11136751 | 42751113 | FITCH MOUNTAIN 1113 | 22.6749 | 139 | 0.073927 | 10.2759 | 945 | 1 | 4.03 | 4.03 | 0 | 0 | 0 | 0 | FRRB - REMG - 2021 | 2020-11-13
2673 | PUEBLO 2102792 | 43292102 | PUEBLO 2102 | 19.3407 | 180 | 0.073389 | 13.2101 | 951 | 3 | 3.3379 | 3.3379 | 0 | 0 | 0 | 0 | ECOP | 2020-12-11
4175 | MARTELL 1101CB | 163011101 | MARTELL 1101 | 5.879 | 171 | 0.067405 | 11.5263 | 999 | 3 | 1.31 | 1.31 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
4743 | WYANDOTTE 11031508 | 102911103 | WYANDOTTE 1103 | 27.2173 | 249 | 0.050062 | 12.4656 | 1176 | 4 | 18.7622 | 1.8559 | 13.97 | 0 | 2.9364 | 0 | FRRB - OH - 2021 | 2020-11-13
3633 | BIG BEND 11021972 | 103751102 | BIG BEND 1102 | 21.2964 | 177 | 0.040961 | 7.25 | 1288 | 12 | 32.1473 | 23.3034 | 8.8439 | 0 | 0 | 0 | FRRB - OH - 2021 | 2020-11-13
4946 | WYANDOTTE 11031976 | 102911103 | WYANDOTTE 1103 | 23.7815 | 217 | 0.040282 | 8.7412 | 1299 | 24 | 31.1777 | 25.0078 | 0 | 0 | 6.1699 | 0 | FRRB - UG - 2021 | 2020-11-13
3640 | FROGTOWN 1702CB | 163451702 | FROGTOWN 1702 | 1.4614 | 47 | 0.039234 | 1.844 | 1316 | 1 | 1.2739 | 0 | 0 | 1.2739 | 0 | 0 | PSPS - Scoped | 2020-12-18
88 | SILVERADO 2105658898 | 43432105 | SILVERADO 2105 | 17.1737 | 151 | 0.035763 | 5.4002 | 1361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In-Construction | 2020-12-01
2335 | PLACERVILLE 21067522 | 153082106 | PLACERVILLE 2106 | 67.3656 | 745 | 0.035529 | 26.4689 | 1363 | 3 | 1.35 | 1.35 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
3154 | CALISTOGA 1102634 | 42711102 | CALISTOGA 1102 | 11.216 | 178 | 0.029373 | 5.2284 | 1477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
249 | RINCON 1103CB | 43321103 | RINCON 1103 | 2.4433 | 41 | 0.016461 | 0.67489 | 1755 | 1 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | PSPS - Scoped | 2020-12-18
3447 | WYANDOTTE 11031974 | 102911103 | WYANDOTTE 1103 | 22.4168 | 259 | 0.012814 | 3.3188 | 1849 | 28 | 20.3416 | 11.3906 | 2.92 | 0 | 6.0311 | 0 | FRRB - UG - 2021 | 2020-11-13
1135 | LOS GATOS 1106LB44 | 82021106 | LOS GATOS 1106 | 19.3536 | 213 | 0.012499 | 2.6623 | 1864 | 1 | 0.84905 | 0 | 0 | 0.84905 | 0 | 0 | In-Construction | 2020-12-01
10 | KONOCTI 1102532 | 43311102 | KONOCTI 1102 | 9.7315 | 124 | 0.0090595 | 1.1234 | 1999 | 1 | 1.0646 | 0 | 0 | 0 | 1.0646 | 0 | In-Construction | 2020-12-01
7254 | ALLEGHANY 1101VR816 | 152101101 | ALLEGHANY 1101 | 4.1491 | 49 | 0.0088541 | 0.43385 | 2010 | 4 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
797 | DUNBAR 1101CB | 43071101 | DUNBAR 1101 | 3.1203 | 191 | 0.007993 | 1.5267 | 2048 | 3 | 2.0114 | 2.0114 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
1984 | HALF MOON BAY 110369412 | 24101103 | HALF MOON BAY 1103 | 15.5679 | 150 | 0.0078448 | 1.1767 | 2055 | 2 | 5.42 | 5.42 | 0 | 0 | 0 | 0 | FRRB - UG - 2021 | 2020-11-13
4884 | PLACERVILLE 1112CB | 153081112 | PLACERVILLE 1112 | 8.513 | 117 | 0.0065148 | 0.76223 | 2123 | 2 | 0.38015 | 0.38015 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
3076 | PLACERVILLE 21061104 | 153082106 | PLACERVILLE 2106 | 49.4989 | 462 | 0.0064469 | 2.9785 | 2131 | 1 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | Remote Grid Pilot | 2020-12-18
8349 | BRUNSWICK 1110CB | 152481110 | BRUNSWICK 1110 | 0.0034177 | 26 | 0.0064174 | 0.16685 | 2134 | 1 | 0.055871 | 0.055871 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
2120 | BRUNSWICK 110350070 | 152481103 | BRUNSWICK 1103 | 17.7473 | 201 | 0.0062036 | 1.2469 | 2144 | 5 | 9.1785 | 0 | 0 | 0 | 9.1785 | 0 | In-Construction | 2020-12-01
6388 | HALF MOON BAY 11036012 | 24101103 | HALF MOON BAY 1103 | 6.6683 | 79 | 0.0054078 | 0.42722 | 2186 | 1 | 0.95 | 0.95 | 0 | 0 | 0 | 0 | FRRB - OH - 2021 | 2020-11-13
1451 | MIWUK 1701953336 | 163661701 | MIWUK 1701 | 11.8581 | 132 | 0.0038168 | 0.50381 | 2267 | 4 | 6.21 | 0 | 0 | 2.9867 | 3.2233 | 0 | In-Construction | 2020-12-01
1371 | PINE GROVE 11021222 | 163751102 | PINE GROVE 1102 | 17.2598 | 218 | 0.0037571 | 0.81905 | 2271 | 3 | 4.3156 | 0 | 0 | 0 | 4.3156 | 0 | In-Construction | 2020-12-01
1742 | MIWUK 1701CB | 163661701 | MIWUK 1701 | 16.2494 | 187 | 0.0029901 | 0.55914 | 2353 | 6 | 11.0006 | 0 | 0 | 0 | 11.0006 | 0 | In-Construction | 2020-12-01
2714 | MIWUK 1702CB | 163661702 | MIWUK 1702 | 9.055 | 110 | 0.0028161 | 0.30977 | 2369 | 2 | 3.8008 | 0 | 0 | 0 | 3.8008 | 0 | In-Construction | 2020-12-01
5291 | MIWUK 1702823548 | 163661702 | MIWUK 1702 | 19.7318 | 231 | 0.0025098 | 0.57976 | 2411 | 1 | 1.4252 | 0 | 0 | 0 | 1.4252 | 0 | In-Construction | 2020-12-01
3039 | BIG BASIN 110110296 | 82841101 | BIG BASIN 1101 | 14.4211 | 181 | 0.0021702 | 0.3928 | 2456 | 3 | 7.6233 | 0 | 0 | 0 | 7.6233 | 0 | DSDD | 2020-12-18
5206 | CAMP EVERS 21065020 | 83622106 | CAMP EVERS 2106 | 15.0734 | 185 | 0.0021265 | 0.3934 | 2464 | 1 | 1.0392 | 0 | 0 | 0 | 1.0392 | 0 | In-Construction | 2020-12-01
4477 | MIWUK 170238218 | 163661702 | MIWUK 1702 | 10.9416 | 132 | 0.00074696 | 0.098599 | 2678 | 2 | 4.3923 | 0 | 0 | 0 | 4.3923 | 0 | In-Construction | 2020-12-01
380 | STANISLAUS 17021804 | 162821702 | STANISLAUS 1702 | 8.3797 | 118 | 0.00058985 | 0.069602 | 2712 | 1 | 1.9112 | 0 | 0 | 1.9112 | 0 | 0 | DSDD | 2020-12-18
6409 | MIWUK 1702S2247 | 163661702 | MIWUK 1702 | 1.4879 | 21 | 0.00049228 | 0.010338 | 2737 | 1 | 1.1682 | 0 | 0 | 0 | 1.1682 | 0 | In-Construction | 2020-12-01
9855 | DUNLAP 1102778286 | 254061102 | DUNLAP 1102 | 2.6029 | 5 | 0.0004909 | 0.0024545 | 2738 | 1 | 2.48 | 2.48 | 0 | 0 | 0 | 0 | Remote Grid Pilot | 2020-12-18
2096 | CALISTOGA 1102184814 | 42711102 | CALISTOGA 1102 | 0.42402 | 20 | 8.707e-06 | 0.00017414 | 3098 | 1 | 0.18 | 0.18 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
3773 | RINCON 1104CB | 43321104 | RINCON 1104 | 0.56024 | 34 | 4.3928e-06 | 0.00014935 | 3302 | 1 | 1.78 | 0 | 0 | 1.78 | 0 | 0 | PSPS - Scoped | 2020-12-18
n/a | VARIOUS | n/a | VARIOUS | 31.8 | 34 |  |  |  |  | 31.8 | 31.8 | 0 | 0 | 0 | 0 | Line Removal | 2020-12-11
|  |  | Totals: | 1201.0946 |  |  | 2328.1944 |  | 388 | 600.7915 | 410.6079 | 107.4455 | 13.9235 | 68.8146 | 0

## Mapping
Phase | Exec Status
Scoping | 0
Scoping | 1
Scoping | 2
Scoping | 3
Scoping | 4
Scoping | 5
Scoping | 6
Scoping | 7
Scoping | 8
Scoping | 9
Scoping | 10
Scoping | 11
Scoping | 12
Scoping | 13
Estimating | 14
Estimating | 15
Estimating | 16
Estimating | 17
Dependencies | 18
Construction | 19
Construction | 20
Scoping
Estimating
Dependencies
Construction