## Summary
System Hardening 2021 Financial Review
amounts in 1,000s
| Mar |  |  |  | YTD |  |  |  | EOY
| Act | Forecast (PRJ) | Var | % of Var | Act | Budget | Var | % of Var | Run Rate | Forecast (Act+ PRJ) | Budget | Var | % of Var
System Hardening | 18491.1826 | 19983.4005 | 1492.2179 | 7.467% | 15450.5839 | 107826.0352 | 92375.4513 | 85.67% | 61802.3358 | 554043.2958 | 640246.4953 | 86203.1996 | 13.46%
update North Complex review as well. have ready for monthly meeting

## Forecast
System Hardening 2021
$ amount in thousands
|  | Actuals |  |  | Forecast
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
| 08W hardened miles | 3.6 | 6.1 | 14.3 | 15 | 20 | 25 | 25 | 30 | 30 | 17 | 12 | 6
2AF idle facilities |  | Actuals Jan: 1.5; Actuals Feb: 0; Actuals Mar: 0
| Total Miles | 5.1 | 6.1 | 14.3 | 15 | 20 | 25 | 25 | 30 | 30 | 17 | 12 | 6
Total Charges |  | -55177.2964 | 52136.6978 | 18491.1826 | 33309.5204 | 68372.0725 | 48288.7917 | 79784.6031 | 78975.855 | 77507.6145 | 58944.9378 | 49375.6234 | 37861.4416
Cumulative Miles |  | 5.1 | 11.2 | 25.5 | 40.5 | 60.5 | 85.5 | 110.5 | 140.5 | 170.5 | 187.5 | 199.5 | 205.5
Cumulative Costs |  | -55177.2964 | -3040.5987 | 15450.5839 | 48760.1044 | 117132.1769 | 165420.9686 | 245205.5718 | 324181.4268 | 401689.0413 | 460633.9792 | 510009.6025 | 547871.0441
Cumulative Unit Cost
data pulled on 4/05
Version | Overall Result | 001/2021 | 002/2021 | 003/2021 | 004/2021 | 005/2021 | 006/2021 | 007/2021 | 008/2021 | 009/2021 | 010/2021 | 011/2021 | 012/2021
Act | 15450.5839 | Actuals Jan: -55177.2964; Actuals Feb: 52136.6978; Actuals Mar: 18491.1826
DET | 640246.4953 | 38955.8793 | 32804.3138 | 36065.8422 | 33309.5204 | 68372.0725 | 48288.7917 | 79784.6031 | 78975.855 | 77507.6145 | 58944.9378 | 49375.6234 | 37861.4416
PRJ |  | 5865.2357 | 13501.8008 | 19983.4005 | 26095.4924 | 34460.4448 | 34502.317 | 85539.3035 | 89463.4532 | 83456.6229 | 77060.3795 | 58598.9477 | 49415.7509
PRM |  | 6512.8753 | 7525.0554 | 22594.6181 | 21745.0599 | 27403.7394 | 28657.3597 | 64225.1738 | 66781.6194 | 59564.7393 | 53022.5193 | 43543.6248 | 40454.8241
RET | 640246.5103 | -54924.5581 | 52216.5349 | 18391.4524 | 35000 | 105245.6349 | 79250.0753 | 92606.1512 | 88021.5687 | 82371.5502 | 59826.7931 | 48187.3008 | 34054.007
PRJ Act plus forecast | 554043.2958 | -55177.2964 | 52136.6978 | 18491.1826 | 26095.4924 | 34460.4448 | 34502.317 | 85539.3035 | 89463.4532 | 83456.6229 | 77060.3795 | 58598.9477 | 49415.7509
PRM Act plus forecast | 420849.2436 | -55177.2964 | 52136.6978 | 18491.1826 | 21745.0599 | 27403.7394 | 28657.3597 | 64225.1738 | 66781.6194 | 59564.7393 | 53022.5193 | 43543.6248 | 40454.8241
Jan Notes
January - reversal of accruals, additional costs have not been JEd over yet
should have re accrued in Jan
new accruals will need to be recalculated to account for any costs that have actually hit
at some point we have to assume all costs have hit and they may be different from the accrued amount
readiness may exceed execution
1100 miles to get ready for 2022 and 2023
PRJ will only include cost for current projects
Feb Notes
original DET based on 358 miles, 20 miles in Jan & Feb
Original DET forecasted $30M to hit in Jan and Feb, for 40 miles to be completed in March
delta of Contracts accrual credit, when actuals hit in 2020 |  | Forecast Jun: 10
delta of Material accrual credit, when actuals hit in 2020 |  | Forecast Jun: 2
$3.2M of Pure Hardening in CEMA should have been JE over, and was missed (Glass Fire) |  | Forecast Jun: 3.2
$200k of comingled costs still sitting in CEMA |  | Forecast Jun: 0.2
[6 empty] | total | 15.4
$1.8M of contract credits on other orders not associated with accrual |  | Forecast Jun: 1.8; Forecast Jul: leave out
$200k of material credits on other orders not associated with accrual |  | Forecast Jun: 0.2; Forecast Jul: leave out
March Notes

## Order Costs
| Fiscal year | Overall Result | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2021 | 2021 | 2021 | 2021 | 2021
| Period/Year |  | Result | 001/2019 | 002/2019 | 003/2019 | 004/2019 | 005/2019 | 006/2019 | 007/2019 | 008/2019 | 009/2019 | 010/2019 | 011/2019 | 012/2019 | Result | 001/2020 | 002/2020 | 003/2020 | 004/2020 | 005/2020 | 006/2020 | 007/2020 | 008/2020 | 009/2020 | 010/2020 | 011/2020 | 012/2020 | Result | 001/2021 | 002/2021 | 003/2021 | 004/2021
Program | CE Mjr Resource Grp | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $
System Hardening | Result | 719978.1406 | 281059.7753 | 1582.4611 | 7313.7969 | -1140.3883 | 4255.5908 | 14398.5306 | 10930.3735 | 29523.3696 | 17803.1175 | 41111.531 | 20606.5898 | 25377.1694 | 109297.6334 | 460142.0956 | 20416.445 | 42332.8513 | 40351.3224 | 20294.4875 | 31684.484 | 20149.5278 | 20659.1091 | 25563.684 | 20012.027 | 10193.1686 | 37818.3138 | 170666.6751 | -21223.7303 | -55177.2964 | 52136.6978 | 18491.1826 | -36674.3142
System Hardening | Contract | 390182.8567 | 163941.05 | 481.8788 | 5528.7973 | -2832.0529 | 2361.9 | 10380.1222 | 8020.3883 | 22839.3579 | 10963.0344 | 28777.2828 | 10788.855 | 14693.002 | 51938.4841 | 254772.2734 | 12570.3417 | 26443.5351 | 24524.8751 | 6436.4236 | 15350.7304 | 7545.5351 | 8815.7608 | 14823.3691 | 17935.6653 | 6842.8607 | 20240.7545 | 93242.4221 | -28530.4667 | -41082.5986 | 33900.6717 | 9729.3245 | -31077.8644
System Hardening | Labor External | 3039.7285 | 1615.2383 | 117.1437 | 76.8664 | 176.2427 | 123.4429 | 175.0799 | 114.5026 | 100.059 | 225.2097 | 111.7257 | 83.1401 | 138.9171 | 172.9085 | 1167.6795 | 135.427 | 157.1252 | 59.121 | 75.1725 | 139.5837 | 117.3487 | 11.0702 | 155.6365 | 71.9692 | 91.5633 | 78.724 | 74.9382 | 256.8106 | 75.2401 | 87.7535 | 101.8769 | -8.0598
System Hardening | Labor Internal | 123182.044 | 41134.04 | 316.3163 | 547.6106 | 44.1139 | 378.2441 | 907.643 | 847.1416 | 2019.8356 | 2161.2455 | 4282.937 | 2515.9722 | 4266.1679 | 22846.8123 | 75002.8969 | 2710.1258 | 5304.988 | 5467.118 | 4495.4007 | 5859.0395 | 4243.613 | 4379.7544 | 2630.4612 | 2088.2888 | 927.8995 | 1159.5743 | 35736.6338 | 7045.1071 | 852.561 | 2327.8274 | 3770.7704 | 93.9484
System Hardening | Materials | 74675.585 | 25565.5583 | 313.0765 | 523.6219 | 1425.7668 | 943.303 | 1900.9236 | 1017.1376 | 2422.3923 | 2300.8393 | 3773.0927 | 5209.551 | 2587.2554 | 3148.5982 | 60488.3771 | 2021.7741 | 2937.8658 | 2893.4369 | 2951.2288 | 2990.8529 | 2695.3891 | 2675.6371 | 4622.7359 | 2751.8669 | 941.1017 | 13334.6336 | 19671.8544 | -11378.3504 | -15702.0022 | 10683.6907 | -883.1535 | -5476.8854
System Hardening | Other | 128897.9264 | 48803.8886 | 354.0458 | 636.9007 | 45.5411 | 448.7007 | 1034.762 | 931.2034 | 2141.7248 | 2152.7886 | 4166.4929 | 2009.0715 | 3691.8269 | 31190.8303 | 68710.8687 | 2978.7765 | 7489.3372 | 7406.7714 | 6336.2619 | 7344.2774 | 5547.642 | 4776.8866 | 3331.4813 | -2835.7632 | 1389.7435 | 3004.6274 | 21940.8266 | 11383.1691 | 679.5033 | 5136.7545 | 5772.3643 | -205.453
Order Costs

## data for pivot
Order | Order Desc | CE Mjr Resource Grp | Cost Element | Vendor | Fiscal year/period | $
1014895 | Contract Estimating 08W Planning | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 001/2021 | -407447.88
1014895 | Contract Estimating 08W Planning | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE ENGINEERING INC | 001/2021 | -65509
1014895 | Contract Estimating 08W Planning | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | 83622
1014895 | Contract Estimating 08W Planning | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | 39687.75
1014895 | Contract Estimating 08W Planning | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 003/2021 | 95831.15
1014895 | Contract Estimating 08W Planning | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 137460.27
1014895 | Contract Estimating 08W Planning | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -137460.27
1014895 | Contract Estimating 08W Planning | Other | Cash Discount earned | PIKE ENGINEERING INC | 002/2021 | -1660
1014895 | Contract Estimating 08W Planning | Other | Cash Discount earned | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -4460.89
1014895 | Contract Estimating 08W Planning | Other | Cash Discount earned | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | -1767.79
1014895 | Contract Estimating 08W Planning | Other | Cash Discount earned | SPECIALIST STAFFING SOLUTIONS INC | 003/2021 | -4451.88
7093505 | 08W - WILDFIRE RESILIENCY PMO | Labor External | Consulting Services - Other | PROCUREABILITY INC | 001/2021 | 64250
7093505 | 08W - WILDFIRE RESILIENCY PMO | Labor External | Consulting Services - Other | PROCUREABILITY INC | 002/2021 | 59850
7093505 | 08W - WILDFIRE RESILIENCY PMO | Labor External | Consulting Services - Other | PROCUREABILITY INC | 003/2021 | 62525
7093505 | 08W - WILDFIRE RESILIENCY PMO | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 7045.32
7093505 | 08W - WILDFIRE RESILIENCY PMO | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 6065.95
7093505 | 08W - WILDFIRE RESILIENCY PMO | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 6162.32
7093505 | 08W - WILDFIRE RESILIENCY PMO | Other | AFUDC-Equity | Not assigned | 001/2021 | 16104.72
7093505 | 08W - WILDFIRE RESILIENCY PMO | Other | AFUDC-Equity | Not assigned | 002/2021 | 16368.44
7093505 | 08W - WILDFIRE RESILIENCY PMO | Other | AFUDC-Equity | Not assigned | 003/2021 | 16628.48
7094406 | 08W - CWSP Materials | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2
7094406 | 08W - CWSP Materials | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.69
7094406 | 08W - CWSP Materials | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.69
7094406 | 08W - CWSP Materials | Other | AFUDC-Equity | Not assigned | 001/2021 | 4.56
7094406 | 08W - CWSP Materials | Other | AFUDC-Equity | Not assigned | 002/2021 | 4.56
7094406 | 08W - CWSP Materials | Other | AFUDC-Equity | Not assigned | 003/2021 | 4.56
30977613 | WDDB OTTER 1102 PHASE 3 | Contract | Contracts | DAVEY TREE SURGERY CO | 001/2021 | 5218.95
30977613 | WDDB OTTER 1102 PHASE 3 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 34.82
30977613 | WDDB OTTER 1102 PHASE 3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 5.31
30977613 | WDDB OTTER 1102 PHASE 3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 12.3
30977613 | WDDB OTTER 1102 PHASE 3 | Labor Internal | Mapping | Not assigned | 001/2021 | 15.66
30977613 | WDDB OTTER 1102 PHASE 3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 10.16
30977613 | WDDB OTTER 1102 PHASE 3 | Other | Benefits OH | Not assigned | 001/2021 | 18.24
30977613 | WDDB OTTER 1102 PHASE 3 | Other | Building Service Overhead | Not assigned | 001/2021 | 3.13
30977613 | WDDB OTTER 1102 PHASE 3 | Other | Capitalized A&G | Not assigned | 001/2021 | 18.59
30977613 | WDDB OTTER 1102 PHASE 3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 3.55
30977613 | WDDB OTTER 1102 PHASE 3 | Other | IT Device OH | Not assigned | 001/2021 | 1.78
30977613 | WDDB OTTER 1102 PHASE 3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 4.8
30977613 | WDDB OTTER 1102 PHASE 3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 7.37
30977613 | WDDB OTTER 1102 PHASE 3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 6.16
30977614 | WDDB OTTER 1102 PHASE 4 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 335.03
30977614 | WDDB OTTER 1102 PHASE 4 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 34.82
30977614 | WDDB OTTER 1102 PHASE 4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 113.58
30977614 | WDDB OTTER 1102 PHASE 4 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 12.3
30977614 | WDDB OTTER 1102 PHASE 4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 74.49
30977614 | WDDB OTTER 1102 PHASE 4 | Other | Benefits OH | Not assigned | 001/2021 | 146.73
30977614 | WDDB OTTER 1102 PHASE 4 | Other | Building Service Overhead | Not assigned | 001/2021 | 25.19
30977614 | WDDB OTTER 1102 PHASE 4 | Other | Capitalized A&G | Not assigned | 001/2021 | 136.18
30977614 | WDDB OTTER 1102 PHASE 4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 75.88
30977614 | WDDB OTTER 1102 PHASE 4 | Other | IT Device OH | Not assigned | 001/2021 | 14.29
30977614 | WDDB OTTER 1102 PHASE 4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 102.79
30977614 | WDDB OTTER 1102 PHASE 4 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 7.37
30977614 | WDDB OTTER 1102 PHASE 4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 49.57
30977615 | WDDB OTTER 1102 PHASE 5 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 335.03
30977615 | WDDB OTTER 1102 PHASE 5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 113.58
30977615 | WDDB OTTER 1102 PHASE 5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 67.48
30977615 | WDDB OTTER 1102 PHASE 5 | Other | Benefits OH | Not assigned | 001/2021 | 134.8
30977615 | WDDB OTTER 1102 PHASE 5 | Other | Building Service Overhead | Not assigned | 001/2021 | 23.14
30977615 | WDDB OTTER 1102 PHASE 5 | Other | Capitalized A&G | Not assigned | 001/2021 | 123.36
30977615 | WDDB OTTER 1102 PHASE 5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 75.88
30977615 | WDDB OTTER 1102 PHASE 5 | Other | IT Device OH | Not assigned | 001/2021 | 13.12
30977615 | WDDB OTTER 1102 PHASE 5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 102.79
30977615 | WDDB OTTER 1102 PHASE 5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 45.54
31082393 | RECON THREE SPANS CHERRY RIDGE RD | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 36.09
31082393 | RECON THREE SPANS CHERRY RIDGE RD | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.11
31082393 | RECON THREE SPANS CHERRY RIDGE RD | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 13.06
31082393 | RECON THREE SPANS CHERRY RIDGE RD | Labor Internal | Mapping | Not assigned | 003/2021 | 0.32
31082393 | RECON THREE SPANS CHERRY RIDGE RD | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 7.33
31082393 | RECON THREE SPANS CHERRY RIDGE RD | Other | Benefits OH | Not assigned | 003/2021 | 16.28
31082393 | RECON THREE SPANS CHERRY RIDGE RD | Other | Building Service Overhead | Not assigned | 003/2021 | 2.94
31082393 | RECON THREE SPANS CHERRY RIDGE RD | Other | Capitalized A&G | Not assigned | 003/2021 | 13.41
31082393 | RECON THREE SPANS CHERRY RIDGE RD | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.07
31082393 | RECON THREE SPANS CHERRY RIDGE RD | Other | Fleet OH - Gas | Not assigned | 003/2021 | 11.18
31082393 | RECON THREE SPANS CHERRY RIDGE RD | Other | IT Device OH | Not assigned | 003/2021 | 1.67
31082393 | RECON THREE SPANS CHERRY RIDGE RD | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.1
31082393 | RECON THREE SPANS CHERRY RIDGE RD | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 20.02
31082393 | RECON THREE SPANS CHERRY RIDGE RD | Other | Payroll Taxes OH | Not assigned | 003/2021 | 5.8
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 | Contract | Contracts | ARBORWORKS INC | 001/2021 | 40012.18
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 40.69
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 | Labor Internal | Mapping | Not assigned | 001/2021 | 120.04
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 24.18
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 | Other | Benefits OH | Not assigned | 001/2021 | 48.31
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 | Other | Building Service Overhead | Not assigned | 001/2021 | 8.29
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 | Other | Capitalized A&G | Not assigned | 001/2021 | 44.2
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 27.19
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 | Other | IT Device OH | Not assigned | 001/2021 | 4.71
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 36.83
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 16.32
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 1956.23
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 25.74
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Labor Internal | Construction | Not assigned | 001/2021 | 521.15
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Labor Internal | Construction | Not assigned | 002/2021 | 595.6
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 446.7
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 69.64
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 180.25
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 203.75
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 151.43
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 24.6
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Labor Internal | Mapping | Not assigned | 001/2021 | 10.56
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Labor Internal | Mapping | Not assigned | 002/2021 | 5.44
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 121.12
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 121.05
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 89.97
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | Benefits OH | Not assigned | 001/2021 | 237.81
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | Benefits OH | Not assigned | 002/2021 | 241.82
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | Benefits OH | Not assigned | 003/2021 | 170.67
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | Building Service Overhead | Not assigned | 001/2021 | 40.81
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | Building Service Overhead | Not assigned | 002/2021 | 41.5
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | Building Service Overhead | Not assigned | 003/2021 | 30.85
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | Capitalized A&G | Not assigned | 001/2021 | 221.42
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | Capitalized A&G | Not assigned | 002/2021 | 221.3
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | Capitalized A&G | Not assigned | 003/2021 | 164.47
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 120.43
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 136.13
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 101.18
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | IT Device OH | Not assigned | 001/2021 | 23.17
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | IT Device OH | Not assigned | 002/2021 | 23.55
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | IT Device OH | Not assigned | 003/2021 | 17.5
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 163.13
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 184.4
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 137.05
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 14.74
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 80.34
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 81.71
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 60.72
31272375 | CWSP PT. MORETTI BEYOND 5995 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 1015.28
31272375 | CWSP PT. MORETTI BEYOND 5995 | Labor Internal | Construction | Not assigned | 001/2021 | -215.71
31272375 | CWSP PT. MORETTI BEYOND 5995 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 443.49
31272375 | CWSP PT. MORETTI BEYOND 5995 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 78.95
31272375 | CWSP PT. MORETTI BEYOND 5995 | Labor Internal | Mapping | Not assigned | 001/2021 | 5.1
31272375 | CWSP PT. MORETTI BEYOND 5995 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 46.9
31272375 | CWSP PT. MORETTI BEYOND 5995 | Other | Benefits OH | Not assigned | 001/2021 | 93.7
31272375 | CWSP PT. MORETTI BEYOND 5995 | Other | Building Service Overhead | Not assigned | 001/2021 | 16.09
31272375 | CWSP PT. MORETTI BEYOND 5995 | Other | Capitalized A&G | Not assigned | 001/2021 | 85.75
31272375 | CWSP PT. MORETTI BEYOND 5995 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 52.75
31272375 | CWSP PT. MORETTI BEYOND 5995 | Other | IT Device OH | Not assigned | 001/2021 | 9.14
31272375 | CWSP PT. MORETTI BEYOND 5995 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 71.44
31272375 | CWSP PT. MORETTI BEYOND 5995 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 31.66
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 | Labor Internal | Construction | Not assigned | 001/2021 | 130.48
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 44.63
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.17
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 26.52
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 | Other | Benefits OH | Not assigned | 001/2021 | 52.97
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 | Other | Building Service Overhead | Not assigned | 001/2021 | 9.09
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 | Other | Capitalized A&G | Not assigned | 001/2021 | 48.47
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 29.82
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 | Other | IT Device OH | Not assigned | 001/2021 | 5.16
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 40.39
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 17.88
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 446.7
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 151.43
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 89.97
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 | Other | Benefits OH | Not assigned | 003/2021 | 170.67
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 | Other | Building Service Overhead | Not assigned | 003/2021 | 30.85
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 | Other | Capitalized A&G | Not assigned | 003/2021 | 164.47
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 101.18
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 | Other | IT Device OH | Not assigned | 003/2021 | 17.5
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 137.05
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 60.72
31286361 | *CANC* FRUITLAND 42 C/O 7449 *CANC | Other | Canceled Capital Order | Not assigned | 003/2021 | -12258.47
31289354 | *CANC* BIG RIVER 1101 FUSE 5187 REC*CANC | Other | Canceled Capital Order | Not assigned | 003/2021 | 986.2
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Labor Internal | Construction | Not assigned | 001/2021 | 186.13
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 483.93
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 446.7
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 148.9
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 227.72
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 151.43
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 50.48
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Labor Internal | Mapping | Not assigned | 001/2021 | 1.68
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 135.29
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 89.97
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 29.99
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | Benefits OH | Not assigned | 001/2021 | 270.28
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | Benefits OH | Not assigned | 002/2021 | 179.73
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | Benefits OH | Not assigned | 003/2021 | 56.89
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | Building Service Overhead | Not assigned | 001/2021 | 46.39
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | Building Service Overhead | Not assigned | 002/2021 | 30.85
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | Building Service Overhead | Not assigned | 003/2021 | 10.28
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | Capitalized A&G | Not assigned | 001/2021 | 247.34
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | Capitalized A&G | Not assigned | 002/2021 | 164.47
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | Capitalized A&G | Not assigned | 003/2021 | 54.82
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | Fleet OH - Elec | Not assigned | 001/2021 | 152.15
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | Fleet OH - Elec | Not assigned | 002/2021 | 101.18
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | Fleet OH - Elec | Not assigned | 003/2021 | 33.73
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | IT Device OH | Not assigned | 001/2021 | 26.32
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | IT Device OH | Not assigned | 002/2021 | 17.5
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | IT Device OH | Not assigned | 003/2021 | 5.83
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 206.09
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 137.05
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 45.68
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | Payroll Taxes OH | Not assigned | 001/2021 | 91.31
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | Payroll Taxes OH | Not assigned | 002/2021 | 60.72
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS | Other | Payroll Taxes OH | Not assigned | 003/2021 | 20.24
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 1722
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Labor Internal | Account Services | Not assigned | 001/2021 | 65.63
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Labor Internal | Administration | Not assigned | 003/2021 | 208.92
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 297.8
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Labor Internal | Environmental Services | Not assigned | 001/2021 | 87.05
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Labor Internal | Environmental Services | Not assigned | 003/2021 | 678.99
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Labor Internal | Environmental Services | Not assigned | 004/2021 | 313.38
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 16.99
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1.75
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 100.95
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.24
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 30.75
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 313.7
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Labor Internal | Mapping | Not assigned | 001/2021 | 5.17
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 31.79
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 59.98
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 200.43
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Labor Internal | Project Management Services | Not assigned | 003/2021 | 74.45
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Benefits OH | Not assigned | 001/2021 | 50.49
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Benefits OH | Not assigned | 002/2021 | 119.83
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Benefits OH | Not assigned | 003/2021 | 326.23
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Building Service Overhead | Not assigned | 001/2021 | 8.65
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Building Service Overhead | Not assigned | 002/2021 | 20.57
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Building Service Overhead | Not assigned | 003/2021 | 58.96
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Capitalized A&G | Not assigned | 001/2021 | 58.12
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Capitalized A&G | Not assigned | 002/2021 | 109.65
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Capitalized A&G | Not assigned | 003/2021 | 366.43
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1.17
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Fleet OH - Elec | Not assigned | 002/2021 | 67.45
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.86
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | IT Device OH | Not assigned | 001/2021 | 4.92
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | IT Device OH | Not assigned | 002/2021 | 11.67
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | IT Device OH | Not assigned | 003/2021 | 33.46
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1.59
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 91.37
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 22.84
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 18.42
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 187.88
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Payroll Taxes OH | Not assigned | 001/2021 | 17.07
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Payroll Taxes OH | Not assigned | 002/2021 | 40.48
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Other | Payroll Taxes OH | Not assigned | 003/2021 | 116.07
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT | Materials | Material Burden | Not assigned | 002/2021 | -826.24
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 002/2021 | -5659.16
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT | Other | Benefits OH | Not assigned | 002/2021 | -160.31
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT | Other | Building Service Overhead | Not assigned | 002/2021 | -27.51
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT | Other | IT Device OH | Not assigned | 002/2021 | -15.62
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT | Other | Minor Material OH | Not assigned | 002/2021 | -461.12
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT | Other | Payroll Taxes OH | Not assigned | 002/2021 | -54.16
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 3270.6
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Labor Internal | Administration | Not assigned | 001/2021 | 69.64
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 325.38
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 34.82
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 110.3
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 3.33
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 36.91
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Labor Internal | Mapping | Not assigned | 002/2021 | 9.81
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 86.57
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1.98
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | Benefits OH | Not assigned | 001/2021 | 166.71
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | Benefits OH | Not assigned | 002/2021 | 3.95
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | Building Service Overhead | Not assigned | 001/2021 | 28.6
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | Building Service Overhead | Not assigned | 002/2021 | 0.68
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | Capitalized A&G | Not assigned | 001/2021 | 158.27
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | Capitalized A&G | Not assigned | 002/2021 | 3.61
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | Fleet OH - Elec | Not assigned | 001/2021 | 73.7
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | Fleet OH - Elec | Not assigned | 002/2021 | 2.22
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | IT Device OH | Not assigned | 001/2021 | 16.23
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | IT Device OH | Not assigned | 002/2021 | 0.39
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 99.83
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 3.01
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 22.1
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | Payroll Taxes OH | Not assigned | 001/2021 | 56.33
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | Payroll Taxes OH | Not assigned | 002/2021 | 1.34
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Contract | Contracts | WILHELM LLC | 003/2021 | -28494.09
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Account Services | Not assigned | 001/2021 | 49.23
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Account Services | Not assigned | 002/2021 | 16.41
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Account Services | Not assigned | 003/2021 | 211.34
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 226.8
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 388.8
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 324
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Administration | Not assigned | 003/2021 | 139.28
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Construction | Not assigned | 003/2021 | 19824.89
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Construction Doubletime Services | Not assigned | 003/2021 | 299.35
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 2186.28
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 335.03
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 139.28
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 12.75
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 4.25
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 54.72
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 504.77
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 189.29
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 7605.8
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 129.34
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 148.81
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 163.68
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 23.26
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 32.4
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Management Services | Not assigned | 001/2021 | 102.88
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Management Services | Not assigned | 002/2021 | 102.88
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Management Services | Not assigned | 003/2021 | 514.4
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Mapping | Not assigned | 003/2021 | 115.31
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 383.53
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 200.59
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 4667.42
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Project Management Services | Not assigned | 001/2021 | 1489
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Project Management Services | Not assigned | 002/2021 | 223.35
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 74.45
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Materials | Material Burden | Not assigned | 003/2021 | 3269.17
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 003/2021 | 22188.04
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 203.56
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Benefits OH | Not assigned | 001/2021 | 762.7
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Benefits OH | Not assigned | 002/2021 | 397.85
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Benefits OH | Not assigned | 003/2021 | 9525.4
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Building Service Overhead | Not assigned | 001/2021 | 130.9
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Building Service Overhead | Not assigned | 002/2021 | 68.28
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Building Service Overhead | Not assigned | 003/2021 | 1721.63
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Capitalized A&G | Not assigned | 001/2021 | 739.05
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Capitalized A&G | Not assigned | 002/2021 | 404.6
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Capitalized A&G | Not assigned | 003/2021 | 8722.4
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Cash Discount earned | STELLA-JONES CORPORATION | 003/2021 | -407.46
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 337.26
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 126.47
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 5081.75
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 19.91
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | IT Device OH | Not assigned | 001/2021 | 74.29
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | IT Device OH | Not assigned | 002/2021 | 38.75
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | IT Device OH | Not assigned | 003/2021 | 977.15
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Minor Material OH | Not assigned | 003/2021 | 1824.48
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 456.83
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 171.31
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 6883.36
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 99.23
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 110.9
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 206.88
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 35.67
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Other Land Fees | SONOMA COUNTY AGRICULTURAL | 002/2021 | 2250
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 257.68
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 134.41
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 3389.1
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE | Contract | Electric Construction Contract | ARB INC | 002/2021 | 16750.31
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 17.03
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE | Labor Internal | Mapping | Not assigned | 002/2021 | 50.25
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 10.12
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE | Other | Benefits OH | Not assigned | 002/2021 | 20.22
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE | Other | Building Service Overhead | Not assigned | 002/2021 | 3.47
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE | Other | Capitalized A&G | Not assigned | 002/2021 | 18.5
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE | Other | Fleet OH - Elec | Not assigned | 002/2021 | 11.38
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE | Other | IT Device OH | Not assigned | 002/2021 | 1.97
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 15.42
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE | Other | Payroll Taxes OH | Not assigned | 002/2021 | 6.83
31429487 | OTTER-1101 S030CC121 – TRANS POLES | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 69.64
31429487 | OTTER-1101 S030CC121 – TRANS POLES | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 24.6
31429487 | OTTER-1101 S030CC121 – TRANS POLES | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 14.03
31429487 | OTTER-1101 S030CC121 – TRANS POLES | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 170.05
31429487 | OTTER-1101 S030CC121 – TRANS POLES | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 143.94
31429487 | OTTER-1101 S030CC121 – TRANS POLES | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 143.94
31429487 | OTTER-1101 S030CC121 – TRANS POLES | Other | AFUDC-Equity | Not assigned | 001/2021 | 388.06
31429487 | OTTER-1101 S030CC121 – TRANS POLES | Other | AFUDC-Equity | Not assigned | 002/2021 | 388.42
31429487 | OTTER-1101 S030CC121 – TRANS POLES | Other | AFUDC-Equity | Not assigned | 003/2021 | 388.42
31429487 | OTTER-1101 S030CC121 – TRANS POLES | Other | Benefits OH | Not assigned | 001/2021 | 23.86
31429487 | OTTER-1101 S030CC121 – TRANS POLES | Other | Building Service Overhead | Not assigned | 001/2021 | 4.1
31429487 | OTTER-1101 S030CC121 – TRANS POLES | Other | Capitalized A&G | Not assigned | 001/2021 | 25.64
31429487 | OTTER-1101 S030CC121 – TRANS POLES | Other | IT Device OH | Not assigned | 001/2021 | 2.33
31429487 | OTTER-1101 S030CC121 – TRANS POLES | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 14.74
31429487 | OTTER-1101 S030CC121 – TRANS POLES | Other | Payroll Taxes OH | Not assigned | 001/2021 | 8.07
31478906 | RAISE T-LINE H-FRAME DONNELS-MI WUK 18/2 | Materials | Fabricated Structures | Not assigned | 004/2021 | 9593.12
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 115.83
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 47.5
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 002/2021 | 168.75
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 003/2021 | 369.04
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Labor Internal | Analyst Services | Not assigned | 003/2021 | 27.85
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 69.64
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.12
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.22
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.38
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 34.44
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.35
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.65
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Labor Internal | Mapping | Not assigned | 003/2021 | 1.11
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.07
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.13
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 19.85
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | Benefits OH | Not assigned | 001/2021 | 0.14
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | Benefits OH | Not assigned | 002/2021 | 0.26
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | Benefits OH | Not assigned | 003/2021 | 32.14
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.02
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.04
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.82
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.13
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.24
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | Capitalized A&G | Not assigned | 003/2021 | 36.31
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.08
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.15
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.25
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | IT Device OH | Not assigned | 001/2021 | 0.02
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | IT Device OH | Not assigned | 002/2021 | 0.02
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | IT Device OH | Not assigned | 003/2021 | 3.29
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.11
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.2
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.34
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 20.63
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.04
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.08
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 11.44
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 517.64
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -517.64
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 1793.43
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Labor Internal | Administrative Services - OT | Not assigned | 001/2021 | 229.83
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Labor Internal | Design Overtime Services | Not assigned | 001/2021 | 87.28
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Labor Internal | Design Services | Not assigned | 001/2021 | 236.84
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Labor Internal | Design Services Double Time | Not assigned | 001/2021 | 118.4
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 118.42
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 2144.76
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 69.64
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 226.33
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 917.23
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1.82
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 220.27
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 324
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Labor Internal | Mapping | Not assigned | 002/2021 | 5.38
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 670.49
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1.08
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Other | Benefits OH | Not assigned | 001/2021 | 1302.33
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Other | Benefits OH | Not assigned | 002/2021 | 2.16
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Other | Building Service Overhead | Not assigned | 001/2021 | 223.51
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.37
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Other | Capitalized A&G | Not assigned | 001/2021 | 1225.8
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Other | Capitalized A&G | Not assigned | 002/2021 | 1.98
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 612.84
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1.22
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Other | IT Device OH | Not assigned | 001/2021 | 126.85
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Other | IT Device OH | Not assigned | 002/2021 | 0.21
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 830.11
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1.65
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 131.93
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 439.97
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.74
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Contract | Construction Inspection | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 1904.34
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 001/2021 | 1.8
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Account Services | Not assigned | 001/2021 | 49.23
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Account Services | Not assigned | 002/2021 | 65.64
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Account Services | Not assigned | 003/2021 | 82.05
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 307.8
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Construction | Not assigned | 001/2021 | 335.03
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Construction | Not assigned | 002/2021 | 74.45
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 148.9
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 148.9
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 148.9
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 34.82
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 12.75
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 16.99
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 21.24
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 165.07
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 77.89
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 50.48
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 108.75
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 12.3
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Mapping | Not assigned | 001/2021 | 3.03
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Mapping | Not assigned | 002/2021 | 6.38
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 107.98
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 121.47
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 53.53
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Benefits OH | Not assigned | 001/2021 | 209.88
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Benefits OH | Not assigned | 002/2021 | 216.51
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Benefits OH | Not assigned | 003/2021 | 90.29
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Building Service Overhead | Not assigned | 001/2021 | 36.01
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Building Service Overhead | Not assigned | 002/2021 | 37.16
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Building Service Overhead | Not assigned | 003/2021 | 16.32
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Capitalized A&G | Not assigned | 001/2021 | 197.42
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Capitalized A&G | Not assigned | 002/2021 | 222.08
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Capitalized A&G | Not assigned | 003/2021 | 97.85
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 110.29
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 52.03
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 33.73
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | IT Device OH | Not assigned | 001/2021 | 20.45
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | IT Device OH | Not assigned | 002/2021 | 21.09
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | IT Device OH | Not assigned | 003/2021 | 9.26
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 149.4
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 70.48
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 45.68
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 65.13
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 7.37
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 70.9
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 73.16
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 32.13
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | Labor Internal | Account Services | Not assigned | 001/2021 | 32.82
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 8.5
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 6.61
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 83.03
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 70.28
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 70.28
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 189.49
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 189.65
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 189.65
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | Other | Benefits OH | Not assigned | 001/2021 | 9.31
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 1.59
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 12.08
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | Other | IT Device OH | Not assigned | 001/2021 | 0.91
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 3.14
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 | Contract | Contracts | THE ORIGINAL MOWBRAY'S TREE SERVICE | 001/2021 | 265492.24
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 | Contract | Contracts | Not assigned | 001/2021 | -287415.88
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -22.29
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | -65.77
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | -13.25
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | -26.46
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | -4.54
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | -24.22
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | -14.9
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | -2.59
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -20.18
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | -8.95
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 001/2021 | 15
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 002/2021 | 30
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 335.03
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 335.03
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 69.64
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 113.6
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 113.61
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 24.6
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.05
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.09
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 67.49
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 81.53
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Other | Benefits OH | Not assigned | 001/2021 | 134.82
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Other | Benefits OH | Not assigned | 002/2021 | 158.7
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Other | Building Service Overhead | Not assigned | 001/2021 | 23.14
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Other | Building Service Overhead | Not assigned | 002/2021 | 27.24
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Other | Capitalized A&G | Not assigned | 001/2021 | 123.38
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Other | Capitalized A&G | Not assigned | 002/2021 | 149.03
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 75.89
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 75.9
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Other | IT Device OH | Not assigned | 001/2021 | 13.12
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Other | IT Device OH | Not assigned | 002/2021 | 15.45
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 102.81
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 102.82
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 14.74
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 45.54
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 53.63
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 37556.33
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -17273.54
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 75.72
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 75.72
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 44.98
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 44.98
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 95.29
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 102.42
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 89.36
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 230.34
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 276.37
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 241.13
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | Benefits OH | Not assigned | 001/2021 | 89.88
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | Benefits OH | Not assigned | 002/2021 | 89.88
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 15.42
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.42
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 82.24
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 82.24
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 50.59
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 50.59
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | IT Device OH | Not assigned | 001/2021 | 8.76
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | IT Device OH | Not assigned | 002/2021 | 8.76
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 68.52
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 68.52
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 30.36
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.36
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 136340.54
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -45561.14
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -5973
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | 5973
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 446.7
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 75.72
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 151.43
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 44.98
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 89.97
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 184.71
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 246.03
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 215.94
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 466.59
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 663.89
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 582.7
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 89.88
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 179.73
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 15.42
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 30.85
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 82.24
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 164.47
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 50.59
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 101.18
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 8.76
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 17.5
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 68.52
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 137.05
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 30.36
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 60.72
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 1500
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Labor Internal | Construction | Not assigned | 002/2021 | 681.4
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 75.72
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 308.79
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 6.13
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 44.98
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 183.44
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Materials | Material Burden | Not assigned | 001/2021 | 150.52
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 001/2021 | 1021.47
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 001/2021 | 9.48
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 110.73
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 102.71
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 106.11
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 263.77
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 277.15
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 286.32
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | Benefits OH | Not assigned | 001/2021 | 119.09
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | Benefits OH | Not assigned | 002/2021 | 366.5
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 20.43
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 62.89
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 82.24
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 335.39
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | Cash Discount earned | STELLA-JONES CORPORATION | 001/2021 | -18.97
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 50.59
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 206.32
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | IT Device OH | Not assigned | 001/2021 | 11.6
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | IT Device OH | Not assigned | 002/2021 | 35.71
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | Minor Material OH | Not assigned | 001/2021 | 84
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 68.52
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 279.45
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 40.23
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 123.82
35043993 | CWSP - CAMPEVERS2105 - LR 74170 - 4KVPH4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 17
35043993 | CWSP - CAMPEVERS2105 - LR 74170 - 4KVPH4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 14.36
35043993 | CWSP - CAMPEVERS2105 - LR 74170 - 4KVPH4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 14.36
35043993 | CWSP - CAMPEVERS2105 - LR 74170 - 4KVPH4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 38.74
35043993 | CWSP - CAMPEVERS2105 - LR 74170 - 4KVPH4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 38.74
35043993 | CWSP - CAMPEVERS2105 - LR 74170 - 4KVPH4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 38.74
35043994 | CWSP - CAMP EVERS 2105 - LR 11384 ZONE | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 15.28
35043994 | CWSP - CAMP EVERS 2105 - LR 11384 ZONE | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 12.91
35043994 | CWSP - CAMP EVERS 2105 - LR 11384 ZONE | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 12.91
35043994 | CWSP - CAMP EVERS 2105 - LR 11384 ZONE | Other | AFUDC-Equity | Not assigned | 001/2021 | 34.84
35043994 | CWSP - CAMP EVERS 2105 - LR 11384 ZONE | Other | AFUDC-Equity | Not assigned | 002/2021 | 34.84
35043994 | CWSP - CAMP EVERS 2105 - LR 11384 ZONE | Other | AFUDC-Equity | Not assigned | 003/2021 | 34.84
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Contract | Contracts | Not assigned | 003/2021 | -4918.23
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 97.43
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Labor Internal | Electric Activity Charge - Non-Type A | Not assigned | 003/2021 | -328.2
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | -15836.4
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | -324.95
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.1
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | -5373.54
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | -114.8
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.29
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Labor Internal | Mapping | Not assigned | 003/2021 | -14.75
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.06
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | -3257.87
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Other | Benefits OH | Not assigned | 001/2021 | 0.12
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Other | Benefits OH | Not assigned | 003/2021 | -6254.53
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.02
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Other | Building Service Overhead | Not assigned | 003/2021 | -1130.45
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.11
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Other | Capitalized A&G | Not assigned | 003/2021 | -6076.88
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Other | Cost Adjustments | Not assigned | 003/2021 | -955
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.07
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Other | Fleet OH - Elec | Not assigned | 003/2021 | -3664.62
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Other | IT Device OH | Not assigned | 001/2021 | 0.02
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Other | IT Device OH | Not assigned | 003/2021 | -641.61
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.09
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | -4963.83
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | -68.76
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.04
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 | Other | Payroll Taxes OH | Not assigned | 003/2021 | -2225.33
35047429 | CWSP - WILLITS 1104 - LR 34008 PH 1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 23.37
35047429 | CWSP - WILLITS 1104 - LR 34008 PH 1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 19.74
35047429 | CWSP - WILLITS 1104 - LR 34008 PH 1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 19.74
35047429 | CWSP - WILLITS 1104 - LR 34008 PH 1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 53.27
35047429 | CWSP - WILLITS 1104 - LR 34008 PH 1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 53.27
35047429 | CWSP - WILLITS 1104 - LR 34008 PH 1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 53.27
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Labor Internal | Account Services | Not assigned | 003/2021 | 49.23
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 335.03
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 12.75
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 113.58
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 67.48
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 9.91
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Other | Benefits OH | Not assigned | 001/2021 | 134.8
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Other | Benefits OH | Not assigned | 003/2021 | 13.25
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Other | Building Service Overhead | Not assigned | 001/2021 | 23.14
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Other | Building Service Overhead | Not assigned | 003/2021 | 2.39
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Other | Capitalized A&G | Not assigned | 001/2021 | 123.36
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Other | Capitalized A&G | Not assigned | 003/2021 | 18.13
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Other | Fleet OH - Elec | Not assigned | 001/2021 | 75.88
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Other | IT Device OH | Not assigned | 001/2021 | 13.12
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Other | IT Device OH | Not assigned | 003/2021 | 1.36
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 102.79
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Other | Payroll Taxes OH | Not assigned | 001/2021 | 45.54
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Other | Payroll Taxes OH | Not assigned | 003/2021 | 4.71
35051268 | CWSP - WILLITS 1104 - LR 34008 - PH 2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 22.3
35051268 | CWSP - WILLITS 1104 - LR 34008 - PH 2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 18.84
35051268 | CWSP - WILLITS 1104 - LR 34008 - PH 2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 18.84
35051268 | CWSP - WILLITS 1104 - LR 34008 - PH 2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 50.84
35051268 | CWSP - WILLITS 1104 - LR 34008 - PH 2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 50.84
35051268 | CWSP - WILLITS 1104 - LR 34008 - PH 2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 50.84
35051356 | CWSP - EL DORADO PH 2101 LR 26000 PH 2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 7.01
35051356 | CWSP - EL DORADO PH 2101 LR 26000 PH 2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 5.92
35051356 | CWSP - EL DORADO PH 2101 LR 26000 PH 2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 5.92
35051356 | CWSP - EL DORADO PH 2101 LR 26000 PH 2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 15.96
35051356 | CWSP - EL DORADO PH 2101 LR 26000 PH 2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 15.96
35051356 | CWSP - EL DORADO PH 2101 LR 26000 PH 2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 15.96
35051484 | CWSP - MONTE RIO 1113 - 8299 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 18.04
35051484 | CWSP - MONTE RIO 1113 - 8299 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 15.24
35051484 | CWSP - MONTE RIO 1113 - 8299 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 15.24
35051484 | CWSP - MONTE RIO 1113 - 8299 | Other | AFUDC-Equity | Not assigned | 001/2021 | 41.13
35051484 | CWSP - MONTE RIO 1113 - 8299 | Other | AFUDC-Equity | Not assigned | 002/2021 | 41.13
35051484 | CWSP - MONTE RIO 1113 - 8299 | Other | AFUDC-Equity | Not assigned | 003/2021 | 41.13
35051485 | CWSP - MONTE RIO 1111 - 1701 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 20.49
35051485 | CWSP - MONTE RIO 1111 - 1701 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 17.31
35051485 | CWSP - MONTE RIO 1111 - 1701 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 17.31
35051485 | CWSP - MONTE RIO 1111 - 1701 | Other | AFUDC-Equity | Not assigned | 001/2021 | 46.7
35051485 | CWSP - MONTE RIO 1111 - 1701 | Other | AFUDC-Equity | Not assigned | 002/2021 | 46.7
35051485 | CWSP - MONTE RIO 1111 - 1701 | Other | AFUDC-Equity | Not assigned | 003/2021 | 46.7
35052726 | CWSP - LOS GATOS 1106 LR 60116 PH1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 53.98
35052726 | CWSP - LOS GATOS 1106 LR 60116 PH1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 45.63
35052726 | CWSP - LOS GATOS 1106 LR 60116 PH1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 45.63
35052726 | CWSP - LOS GATOS 1106 LR 60116 PH1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 123.14
35052726 | CWSP - LOS GATOS 1106 LR 60116 PH1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 123.14
35052726 | CWSP - LOS GATOS 1106 LR 60116 PH1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 123.14
35052727 | CWSP LOS GATOS 1106 LR 1106 PHASE 2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 34.87
35052727 | CWSP LOS GATOS 1106 LR 1106 PHASE 2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 29.51
35052727 | CWSP LOS GATOS 1106 LR 1106 PHASE 2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 29.51
35052727 | CWSP LOS GATOS 1106 LR 1106 PHASE 2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 79.64
35052727 | CWSP LOS GATOS 1106 LR 1106 PHASE 2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 79.64
35052727 | CWSP LOS GATOS 1106 LR 1106 PHASE 2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 79.64
35052728 | CWSP - LOS GATOS 1107 LR 60092 PH1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 41.78
35052728 | CWSP - LOS GATOS 1107 LR 60092 PH1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 35.36
35052728 | CWSP - LOS GATOS 1107 LR 60092 PH1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 35.36
35052728 | CWSP - LOS GATOS 1107 LR 60092 PH1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 95.41
35052728 | CWSP - LOS GATOS 1107 LR 60092 PH1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 95.41
35052728 | CWSP - LOS GATOS 1107 LR 60092 PH1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 95.41
35052729 | CWSP - BURNS 2101 - PH 1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 25.95
35052729 | CWSP - BURNS 2101 - PH 1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 21.96
35052729 | CWSP - BURNS 2101 - PH 1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 21.96
35052729 | CWSP - BURNS 2101 - PH 1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 59.24
35052729 | CWSP - BURNS 2101 - PH 1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 59.24
35052729 | CWSP - BURNS 2101 - PH 1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 59.24
35052730 | CWSP - BURNS 2101- PH 2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 11.89
35052730 | CWSP - BURNS 2101- PH 2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 10.06
35052730 | CWSP - BURNS 2101- PH 2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 10.06
35052730 | CWSP - BURNS 2101- PH 2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 27.14
35052730 | CWSP - BURNS 2101- PH 2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 27.14
35052730 | CWSP - BURNS 2101- PH 2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 27.14
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 6679.6
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 348.98
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | -348.98
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 23.75
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 002/2021 | 964.65
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 003/2021 | 50.02
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Account Services | Not assigned | 002/2021 | 32.82
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Analyst Services | Not assigned | 002/2021 | 55.69
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 592.11
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 872.8
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1079.54
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 781.74
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 409.49
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 174.1
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 34.82
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 8.5
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 862.92
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 265.66
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 145.66
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 61.51
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 19.68
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 12.3
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.05
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 1.92
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 20.19
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 547.72
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 175.65
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 93.55
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 237.05
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 210.05
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 225.7
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 544.43
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 566.81
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 609.04
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 1083.85
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 343.67
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 175.5
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 186.03
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 58.99
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 31.73
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 1001.36
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 321.14
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 171.03
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 576.56
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 177.5
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 97.32
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 105.58
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 33.46
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 17.99
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 780.95
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 240.43
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 131.83
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 36.84
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 11.78
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 7.37
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 366.18
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 116.1
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 62.45
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Other | Permits/FeesLand Surveying Services | TOWILL INC | 003/2021 | 17834
35052732 | CWSP - BIG BASIN 1101 5028 ZONE | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 26.55
35052732 | CWSP - BIG BASIN 1101 5028 ZONE | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 22.47
35052732 | CWSP - BIG BASIN 1101 5028 ZONE | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 22.47
35052732 | CWSP - BIG BASIN 1101 5028 ZONE | Other | AFUDC-Equity | Not assigned | 001/2021 | 60.64
35052732 | CWSP - BIG BASIN 1101 5028 ZONE | Other | AFUDC-Equity | Not assigned | 002/2021 | 60.64
35052732 | CWSP - BIG BASIN 1101 5028 ZONE | Other | AFUDC-Equity | Not assigned | 003/2021 | 60.64
35052733 | CWSP - BIG BASIN 1101 - 10296 ZONE PH2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 10.93
35052733 | CWSP - BIG BASIN 1101 - 10296 ZONE PH2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 9.25
35052733 | CWSP - BIG BASIN 1101 - 10296 ZONE PH2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 9.25
35052733 | CWSP - BIG BASIN 1101 - 10296 ZONE PH2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 24.97
35052733 | CWSP - BIG BASIN 1101 - 10296 ZONE PH2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 24.97
35052733 | CWSP - BIG BASIN 1101 - 10296 ZONE PH2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 24.97
35052734 | CWSP - CAMP EVERS 2105 - LR 5232-33542 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 24.36
35052734 | CWSP - CAMP EVERS 2105 - LR 5232-33542 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 20.61
35052734 | CWSP - CAMP EVERS 2105 - LR 5232-33542 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 20.61
35052734 | CWSP - CAMP EVERS 2105 - LR 5232-33542 | Other | AFUDC-Equity | Not assigned | 001/2021 | 55.63
35052734 | CWSP - CAMP EVERS 2105 - LR 5232-33542 | Other | AFUDC-Equity | Not assigned | 002/2021 | 55.63
35052734 | CWSP - CAMP EVERS 2105 - LR 5232-33542 | Other | AFUDC-Equity | Not assigned | 003/2021 | 55.63
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | -250
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 500
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | -0.25
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.51
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | -0.75
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 1.5
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | -0.15
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 0.3
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 291.03
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 246.78
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 246.96
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 666.41
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 665.92
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 666.41
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | -0.3
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 0.57
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | -0.05
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.1
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | -0.28
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 0.55
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | -0.17
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.34
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | -0.03
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 0.06
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | -0.23
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.46
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | -0.1
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.2
35052736 | CWSP - MIWUK 1701 LR11800 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 42.37
35052736 | CWSP - MIWUK 1701 LR11800 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 35.79
35052736 | CWSP - MIWUK 1701 LR11800 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 35.79
35052736 | CWSP - MIWUK 1701 LR11800 | Other | AFUDC-Equity | Not assigned | 001/2021 | 96.57
35052736 | CWSP - MIWUK 1701 LR11800 | Other | AFUDC-Equity | Not assigned | 002/2021 | 96.57
35052736 | CWSP - MIWUK 1701 LR11800 | Other | AFUDC-Equity | Not assigned | 003/2021 | 96.57
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 978.88
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 348.98
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | -348.98
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 23.75
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 95
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 23.75
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 003/2021 | 291.8
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Account Services | Not assigned | 002/2021 | 598.8
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Account Services | Not assigned | 003/2021 | 119.76
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 388.8
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 64.8
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 64.8
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Analyst Services | Not assigned | 001/2021 | 55.69
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 118.42
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 1347.04
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 785.52
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 595.6
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 139.28
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 243.74
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 155.03
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 31.01
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 41.51
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 924.59
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.32
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 206.25
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 131.9
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 22.89
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 64.8
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 4.05
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | -0.76
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.95
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 142.23
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 745.09
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 37.36
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 160.22
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 154.73
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 170.15
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 368.39
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 417.52
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 459.14
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 249.32
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 1394.98
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 53.66
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 42.77
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 239.41
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 9.71
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 260.05
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 1362.17
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 68.31
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 27.74
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 617.75
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.22
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 24.29
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 135.89
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 5.5
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 37.57
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 836.77
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.29
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 123.52
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 79
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 13.71
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 84.25
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 471.29
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 19.09
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 002/2021 | 9281.34
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 003/2021 | -1000
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | -250
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 500
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 372.25
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 24.99
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 126.7
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | -0.75
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 1.5
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.84
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 75.27
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Materials | Material Burden | Not assigned | 002/2021 | -4062.03
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 002/2021 | -27822.13
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1150.69
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 948.84
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 924.16
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2630.18
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2560.35
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2493.77
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | -758.48
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 142.78
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | -130.18
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 25.81
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 27.13
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 137.61
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 16.69
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 84.65
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | -73.88
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 14.65
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | Minor Material OH | Not assigned | 002/2021 | -2266.96
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 22.61
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 114.67
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | -256.25
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 50.8
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | Labor Internal | Apprentice OT | Not assigned | 002/2021 | -0.77
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | Labor Internal | Construction | Not assigned | 002/2021 | 10886.7
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | Labor Internal | Construction Doubletime Services | Not assigned | 002/2021 | 601.65
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 1424.7
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 4416.66
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 116.21
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 2623.93
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 5242.02
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 899.68
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 4797.09
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 2950.95
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 510.62
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 3997.14
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 1771.04
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Construction Inspection | CANUS CORPORATION | 001/2021 | 8935.12
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Construction Inspection | CANUS CORPORATION | 002/2021 | 629.37
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Construction Inspection | CANUS CORPORATION | 003/2021 | 18693.31
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Construction Inspection | CANUS CORPORATION | 004/2021 | 4904.79
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 911.03
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Contracts | CANUS CORPORATION | 004/2021 | 1097.55
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 001/2021 | -5414.76
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 003/2021 | 287.14
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 001/2021 | 70146.56
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 003/2021 | 256840.77
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 004/2021 | -291914.05
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Environmental Contract | AHTNA GOVERNMENT SERVICES CORP | 001/2021 | 1535.92
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 333.51
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 799.25
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -250
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 1065
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 1055
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -750
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Contract | Helicopter Contract | Not assigned | 003/2021 | 33339.18
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Account Services | Not assigned | 003/2021 | 59.88
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Analyst Services | Not assigned | 001/2021 | 55.69
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Construction | Not assigned | 003/2021 | 2364.38
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 337.52
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Design Overtime Services | Not assigned | 001/2021 | 1.06
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Design Services Double Time | Not assigned | 001/2021 | 1.02
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 740.14
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 1.06
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 218.2
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 2680.2
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 670.05
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 4090.62
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 139.28
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 15.5
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 986.29
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 229.25
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 3093.25
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 19.68
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 49.21
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 9.31
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 004/2021 | 648.54
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 003/2021 | 216.32
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 004/2021 | 162.24
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Maintain & Operate Services | Not assigned | 003/2021 | 322.82
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Maintain & Operate Services | Not assigned | 004/2021 | 38.07
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 226.03
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 6.21
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 860.32
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 597.16
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 136.2
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1882.99
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Materials | Material Burden | Not assigned | 002/2021 | 283.12
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Materials | Material Burden | Not assigned | 003/2021 | 254.57
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 002/2021 | 1921.44
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 003/2021 | 1727.67
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 17.75
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 15.96
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1060.21
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 975.67
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1227.49
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2449.55
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2632.76
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3312.28
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 1189.69
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 327.03
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 3605.98
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 204.2
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 56.13
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 651.75
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 1091.73
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 249
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 3442.48
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Cash Discount earned | STELLA-JONES CORPORATION | 002/2021 | -35.53
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Cash Discount earned | STELLA-JONES CORPORATION | 003/2021 | -31.94
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 658.98
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 153.18
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 2066.73
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 7.97
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 115.89
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 31.86
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 369.91
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Minor Material OH | Not assigned | 002/2021 | 158.01
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Minor Material OH | Not assigned | 003/2021 | 142.07
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 892.6
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 207.48
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 2799.43
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 11.78
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 29.47
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 14.27
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 401.94
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 110.49
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 1282.99
35052822 | CWSP - MIWUK 1701 - LR 8050 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1.11
35052822 | CWSP - MIWUK 1701 - LR 8050 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.94
35052822 | CWSP - MIWUK 1701 - LR 8050 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.94
35052822 | CWSP - MIWUK 1701 - LR 8050 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2.53
35052822 | CWSP - MIWUK 1701 - LR 8050 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2.53
35052822 | CWSP - MIWUK 1701 - LR 8050 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.53
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Contract | Contracts | ARBORWORKS INC | 001/2021 | 10053.25
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Contract | Contracts | ARBORWORKS INC | 002/2021 | 553.5
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1191.2
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 10.22
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 404.38
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 30.16
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 1.66
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 6.07
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 240.24
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 164.6
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 157.34
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 160.49
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 395.69
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 424.57
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 433.07
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 12.13
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 479.95
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 2.08
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 82.38
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 11.1
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 439.21
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 6.83
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 270.19
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 1.18
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 46.75
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 9.25
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 365.97
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 4.1
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 162.14
35052824 | CWSP - MIWUK 1702 - LR6018 - PH 2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.41
35052824 | CWSP - MIWUK 1702 - LR6018 - PH 2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.35
35052824 | CWSP - MIWUK 1702 - LR6018 - PH 2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.35
35052824 | CWSP - MIWUK 1702 - LR6018 - PH 2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 0.95
35052824 | CWSP - MIWUK 1702 - LR6018 - PH 2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 0.95
35052824 | CWSP - MIWUK 1702 - LR6018 - PH 2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.95
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Contract | Construction Inspection | CANUS CORPORATION | 003/2021 | 1670.86
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Contract | Contracts | ARBORWORKS INC | 003/2021 | 49504.22
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 001/2021 | 14662.12
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 003/2021 | 4614.44
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 004/2021 | -4614.44
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 003/2021 | 934.18
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 004/2021 | -934.18
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 379.27
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 381.27
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 363.15
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 799.25
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | 250
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 565
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 505
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 32.29
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Account Services | Not assigned | 003/2021 | 678.86
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Administration | Not assigned | 003/2021 | 442.55
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Analyst Services | Not assigned | 003/2021 | 55.69
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Construction | Not assigned | 003/2021 | 2700.56
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 1603.22
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 967.85
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 818.97
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 278.56
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 175.76
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 343.65
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 26.22
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1910.88
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 118.1
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 9.31
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 003/2021 | 144.12
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 003/2021 | 108.16
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Maintain & Operate Services | Not assigned | 003/2021 | 76.13
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Management Services | Not assigned | 003/2021 | 42.3
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 45.88
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 2.88
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 211.4
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 204.16
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 15.57
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1344.48
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 840.05
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 730.06
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 788.9
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1930.92
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1970
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2128.77
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 407.87
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 31.12
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 2545.87
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 70
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.34
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 460.15
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 373.26
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 28.47
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 2636.5
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 229.61
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 17.51
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1276.75
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 7.97
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 39.73
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 3.03
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 261.16
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 311.02
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 23.72
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1729.39
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 70.72
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 14.27
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 137.81
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.51
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 905.8
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 784.06
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 1048.43
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 1006.68
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | 1500
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 4065
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 12350
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -5000
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Contract | Traffic Control Contracts | ROAD SAFETY INC | 002/2021 | 4032
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 86.1
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 164.56
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -82.16
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Labor Internal | Construction | Not assigned | 001/2021 | 12878.46
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 1472.38
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 483.93
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 930.63
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 297.8
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 5246.14
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 320.77
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 114.7
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 001/2021 | 288.24
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 001/2021 | 216.32
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Labor Internal | Mapping | Not assigned | 001/2021 | 136.01
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Labor Internal | Mapping | Not assigned | 002/2021 | 15.6
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Labor Internal | Mapping | Not assigned | 003/2021 | 40.56
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 3116.73
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 190.57
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 68.15
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Materials | Material Burden | Not assigned | 001/2021 | 471.2
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Materials | Transformers, Regulators & Capacitors | Not assigned | 001/2021 | 3227.42
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Benefits OH | Not assigned | 001/2021 | 6317.95
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Benefits OH | Not assigned | 002/2021 | 380.73
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Benefits OH | Not assigned | 003/2021 | 129.27
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Building Service Overhead | Not assigned | 001/2021 | 1084.31
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Building Service Overhead | Not assigned | 002/2021 | 65.35
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Building Service Overhead | Not assigned | 003/2021 | 23.37
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Capitalized A&G | Not assigned | 001/2021 | 5698.02
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Capitalized A&G | Not assigned | 002/2021 | 348.4
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Capitalized A&G | Not assigned | 003/2021 | 124.58
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Cash Discount earned | ROAD SAFETY INC | 002/2021 | -80.64
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 3505.16
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 214.32
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 76.64
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | IT Device OH | Not assigned | 001/2021 | 615.43
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | IT Device OH | Not assigned | 002/2021 | 37.08
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | IT Device OH | Not assigned | 003/2021 | 13.26
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Minor Material OH | Not assigned | 001/2021 | 262.97
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 4747.84
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 290.31
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 103.81
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 2134.54
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 128.63
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 45.99
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 1032.03
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Account Services | Not assigned | 001/2021 | 65.64
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Account Services | Not assigned | 002/2021 | 49.23
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Account Services | Not assigned | 003/2021 | 98.46
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Construction | Not assigned | 001/2021 | -67.61
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Construction | Not assigned | 002/2021 | 74.45
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 110.87
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 744.51
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 409.48
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.45
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 139.28
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 16.99
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 12.75
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 25.49
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 268.24
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 164.28
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.24
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 49.21
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Mapping | Not assigned | 001/2021 | 3.49
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.67
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 172.57
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 107.5
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 62.87
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | Benefits OH | Not assigned | 001/2021 | 336.98
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | Benefits OH | Not assigned | 002/2021 | 208.92
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | Benefits OH | Not assigned | 003/2021 | 100.26
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | Building Service Overhead | Not assigned | 001/2021 | 57.85
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | Building Service Overhead | Not assigned | 002/2021 | 35.86
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | Building Service Overhead | Not assigned | 003/2021 | 18.12
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | Capitalized A&G | Not assigned | 001/2021 | 315.52
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | Capitalized A&G | Not assigned | 002/2021 | 196.56
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | Capitalized A&G | Not assigned | 003/2021 | 114.94
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 179.22
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 109.76
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.86
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | IT Device OH | Not assigned | 001/2021 | 32.83
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | IT Device OH | Not assigned | 002/2021 | 20.34
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | IT Device OH | Not assigned | 003/2021 | 10.29
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 242.76
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 148.68
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 22.84
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 29.47
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 113.86
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 70.59
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 35.67
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 219.22
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -219.22
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 1793.43
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 356.25
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Labor Internal | Administrative Services - OT | Not assigned | 001/2021 | 97.81
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Labor Internal | Design Overtime Services | Not assigned | 001/2021 | 523.68
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Labor Internal | Design Services | Not assigned | 001/2021 | 414.47
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Labor Internal | Design Services Double Time | Not assigned | 001/2021 | 355.2
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 148.03
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 612.48
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 229.68
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 001/2021 | 2792.92
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1643.42
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 79.68
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 68.9
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 97.2
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.07
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 5.38
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 1015.63
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 47.34
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 19.72
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 33.27
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 35.25
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 50.26
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 89.76
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 95.12
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 2017.37
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 94.57
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 346.24
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 16.23
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 1856.78
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 86.55
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1098.03
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 53.24
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 196.52
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 9.21
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1487.33
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 72.12
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 41.26
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 681.59
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 31.96
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 34153.17
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -13764.62
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 1219.57
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 417.15
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 10.98
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 247.83
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 74.13
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 83.07
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 75.2
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 180.82
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 224.15
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 202.92
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Other | Benefits OH | Not assigned | 003/2021 | 470.15
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 84.98
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 453.09
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 278.72
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Other | IT Device OH | Not assigned | 003/2021 | 48.23
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 377.53
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 167.27
35056433 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 38.96
35056433 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 32.93
35056433 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 32.93
35056433 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 88.86
35056433 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 88.86
35056433 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 88.86
35056434 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 31.84
35056434 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 26.91
35056434 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 26.91
35056434 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 72.61
35056434 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 72.61
35056434 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 72.61
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Labor Internal | Management Services | Not assigned | 001/2021 | 117.74
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Labor Internal | Management Services | Not assigned | 002/2021 | 176.61
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Labor Internal | Management Services | Not assigned | 003/2021 | 765.31
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 32.61
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 27.99
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 29.23
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 74.48
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 75.53
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 78.87
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | Benefits OH | Not assigned | 001/2021 | 22.84
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | Benefits OH | Not assigned | 002/2021 | 34.27
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | Benefits OH | Not assigned | 003/2021 | 141
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | Building Service Overhead | Not assigned | 001/2021 | 3.92
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.88
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | Building Service Overhead | Not assigned | 003/2021 | 25.48
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | Capitalized A&G | Not assigned | 001/2021 | 43.35
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | Capitalized A&G | Not assigned | 002/2021 | 65.03
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | Capitalized A&G | Not assigned | 003/2021 | 281.79
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | IT Device OH | Not assigned | 001/2021 | 2.23
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | IT Device OH | Not assigned | 002/2021 | 3.34
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | IT Device OH | Not assigned | 003/2021 | 14.46
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 7.72
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 11.57
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 50.17
35056438 | REMG 650 - PLACERVILLE 2106, RINGTAIL | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 23.88
35056438 | REMG 650 - PLACERVILLE 2106, RINGTAIL | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 20.18
35056438 | REMG 650 - PLACERVILLE 2106, RINGTAIL | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 20.18
35056438 | REMG 650 - PLACERVILLE 2106, RINGTAIL | Other | AFUDC-Equity | Not assigned | 001/2021 | 54.46
35056438 | REMG 650 - PLACERVILLE 2106, RINGTAIL | Other | AFUDC-Equity | Not assigned | 002/2021 | 54.46
35056438 | REMG 650 - PLACERVILLE 2106, RINGTAIL | Other | AFUDC-Equity | Not assigned | 003/2021 | 54.46
35056439 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 22.16
35056439 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 18.73
35056439 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 18.73
35056439 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 50.54
35056439 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 50.54
35056439 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 50.54
35056732 | CWSP FOREST HILL 1101 LR 50486 HARDENING | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 5.49
35056732 | CWSP FOREST HILL 1101 LR 50486 HARDENING | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4.64
35056732 | CWSP FOREST HILL 1101 LR 50486 HARDENING | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 4.64
35056732 | CWSP FOREST HILL 1101 LR 50486 HARDENING | Other | AFUDC-Equity | Not assigned | 001/2021 | 12.53
35056732 | CWSP FOREST HILL 1101 LR 50486 HARDENING | Other | AFUDC-Equity | Not assigned | 002/2021 | 12.53
35056732 | CWSP FOREST HILL 1101 LR 50486 HARDENING | Other | AFUDC-Equity | Not assigned | 003/2021 | 12.53
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 1500
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Labor Internal | Construction | Not assigned | 003/2021 | 670.05
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 3.18
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Labor Internal | Environmental Services | Not assigned | 001/2021 | 17.41
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1.08
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 229.19
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 11.87
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 001/2021 | 16.2
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 6.03
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 7.41
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 136.16
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1074.81
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 910.37
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 913.19
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2453.15
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2456.55
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2464.15
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 12.81
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 258.31
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 2.19
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 46.69
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 13.54
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 248.93
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.72
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 153.14
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 1.24
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 26.49
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.98
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 207.42
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 7.11
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 4.31
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 91.91
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Contract | Construction Inspection | CANUS CORPORATION | 002/2021 | 250.78
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Contract | Construction Inspection | CANUS CORPORATION | 003/2021 | 3775.11
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Contract | Contracts | ARBORWORKS INC | 003/2021 | 4965.38
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 003/2021 | 200000.4
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 004/2021 | -200000.4
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 333.51
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 799.25
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -150
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 665
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 4895
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -750
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Account Services | Not assigned | 003/2021 | 32.03
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Analyst Services | Not assigned | 003/2021 | 55.69
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 675.04
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 932.57
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Electric Estimating | Not assigned | 004/2021 | 442.46
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 392.76
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 004/2021 | 227.98
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1265.65
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 781.73
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1042.32
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.29
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 429.31
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 266.32
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1251.72
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 19.68
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.73
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 3.87
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 649.64
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 255.05
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 158.22
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 761.3
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 686.17
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 594.26
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 775.21
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1586.83
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1603.55
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2091.85
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | Benefits OH | Not assigned | 001/2021 | 509.52
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | Benefits OH | Not assigned | 002/2021 | 316.12
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | Benefits OH | Not assigned | 003/2021 | 1437.41
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 87.45
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 54.25
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 259.82
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 466.28
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 289.26
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 1391.83
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 286.84
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 177.94
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 836.33
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | IT Device OH | Not assigned | 001/2021 | 49.63
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | IT Device OH | Not assigned | 002/2021 | 30.78
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | IT Device OH | Not assigned | 003/2021 | 147.44
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 388.52
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 241.02
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1132.8
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 11.78
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 172.15
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 106.78
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 511.43
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 001/2021 | -9887.01
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -250
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Labor Internal | Construction | Not assigned | 003/2021 | 670.05
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -0.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 229.19
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Labor Internal | Mapping | Not assigned | 001/2021 | -0.75
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 6.03
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | -0.15
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 136.16
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 554.76
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 481.35
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 483.94
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1317.26
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1298.87
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1305.86
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | Benefits OH | Not assigned | 001/2021 | -0.3
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | Benefits OH | Not assigned | 003/2021 | 258.31
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | Building Service Overhead | Not assigned | 001/2021 | -0.05
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 46.69
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | Capitalized A&G | Not assigned | 001/2021 | -0.28
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 248.93
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | -0.17
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 153.14
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | IT Device OH | Not assigned | 001/2021 | -0.03
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | IT Device OH | Not assigned | 003/2021 | 26.49
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -0.23
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 207.42
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | -0.1
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 91.91
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Other | Permits/Fees | EL DORADO COUNTY | 002/2021 | 1288.92
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 44019.23
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 003/2021 | -1362.54
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 7448
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Labor Internal | Analyst Services | Not assigned | 001/2021 | 55.69
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Labor Internal | Construction | Not assigned | 003/2021 | 670.05
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 229.19
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 19.68
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 6.03
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 11.22
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 136.16
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 499.66
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 467.82
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 474.24
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1152.68
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1262.37
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1279.71
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Other | Benefits OH | Not assigned | 001/2021 | 19.08
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Other | Benefits OH | Not assigned | 003/2021 | 258.31
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 3.27
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 46.69
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 20.51
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 248.93
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 153.14
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Other | IT Device OH | Not assigned | 001/2021 | 1.85
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Other | IT Device OH | Not assigned | 003/2021 | 26.49
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 207.42
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 11.78
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 6.45
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 91.91
35057802 | CWSP-CAMPEVERS2105 - LR 12590 - 4KV PH5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 10.76
35057802 | CWSP-CAMPEVERS2105 - LR 12590 - 4KV PH5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 9.09
35057802 | CWSP-CAMPEVERS2105 - LR 12590 - 4KV PH5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 9.09
35057802 | CWSP-CAMPEVERS2105 - LR 12590 - 4KV PH5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 24.52
35057802 | CWSP-CAMPEVERS2105 - LR 12590 - 4KV PH5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 24.52
35057802 | CWSP-CAMPEVERS2105 - LR 12590 - 4KV PH5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 24.52
35057921 | PUEBLO 2103 RECOND W TW PAST FUSE 2013 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.46
35057921 | PUEBLO 2103 RECOND W TW PAST FUSE 2013 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.08
35057921 | PUEBLO 2103 RECOND W TW PAST FUSE 2013 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.08
35057921 | PUEBLO 2103 RECOND W TW PAST FUSE 2013 | Other | AFUDC-Equity | Not assigned | 001/2021 | 5.61
35057921 | PUEBLO 2103 RECOND W TW PAST FUSE 2013 | Other | AFUDC-Equity | Not assigned | 002/2021 | 5.61
35057921 | PUEBLO 2103 RECOND W TW PAST FUSE 2013 | Other | AFUDC-Equity | Not assigned | 003/2021 | 5.61
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | VETERAN POWER INC | 004/2021 | -43735.44
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 2367.84
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 340.4
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Labor Internal | Account Services | Not assigned | 003/2021 | 196.89
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Labor Internal | Administration | Not assigned | 002/2021 | 139.28
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 1.06
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 278.56
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 243.74
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 139.28
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 69.64
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 50.97
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 2.77
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.35
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 98.42
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 135.32
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 49.21
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Labor Internal | Mapping | Not assigned | 001/2021 | 7.1
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Labor Internal | Mapping | Not assigned | 003/2021 | 1.02
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 57.74
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 77.14
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 67.91
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 209.82
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 182.02
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 183.74
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | AFUDC-Equity | Not assigned | 001/2021 | 482.3
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | AFUDC-Equity | Not assigned | 002/2021 | 491.16
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | AFUDC-Equity | Not assigned | 003/2021 | 495.82
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | Benefits OH | Not assigned | 001/2021 | 98.75
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | Benefits OH | Not assigned | 002/2021 | 131.28
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | Benefits OH | Not assigned | 003/2021 | 98.68
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | Building Service Overhead | Not assigned | 001/2021 | 16.96
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | Building Service Overhead | Not assigned | 002/2021 | 22.53
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | Building Service Overhead | Not assigned | 003/2021 | 17.83
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | Capitalized A&G | Not assigned | 001/2021 | 105.57
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | Capitalized A&G | Not assigned | 002/2021 | 141.03
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | Capitalized A&G | Not assigned | 003/2021 | 124.16
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1.85
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.23
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | IT Device OH | Not assigned | 001/2021 | 9.6
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | IT Device OH | Not assigned | 002/2021 | 12.78
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | IT Device OH | Not assigned | 003/2021 | 10.12
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 2.51
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.31
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 58.94
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 81.05
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 29.47
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | Payroll Taxes OH | Not assigned | 001/2021 | 33.36
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | Payroll Taxes OH | Not assigned | 002/2021 | 44.34
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | Other | Payroll Taxes OH | Not assigned | 003/2021 | 35.11
35058060 | SWIFT 2110 - CONDUCTOR REPL | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 14.69
35058060 | SWIFT 2110 - CONDUCTOR REPL | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 12.54
35058060 | SWIFT 2110 - CONDUCTOR REPL | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 12.54
35058060 | SWIFT 2110 - CONDUCTOR REPL | Other | AFUDC-Equity | Not assigned | 001/2021 | 33.84
35058060 | SWIFT 2110 - CONDUCTOR REPL | Other | AFUDC-Equity | Not assigned | 002/2021 | 33.84
35058060 | SWIFT 2110 - CONDUCTOR REPL | Other | AFUDC-Equity | Not assigned | 003/2021 | 33.84
35058272 | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 11.6
35058272 | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 9.8
35058272 | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 9.8
35058272 | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 26.43
35058272 | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 26.43
35058272 | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 26.43
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Contract | Contracts | Not assigned | 002/2021 | 63000
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Contract | Electric Construction Contract | WILSON UTILITY CONSTRUCTION COMPANY | 001/2021 | -76837.9
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | -367.28
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 383.94
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 465
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 1067.5
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -750
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 32.84
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -32.84
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 372.25
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -77.74
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 89.45
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 127.7
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Labor Internal | Mapping | Not assigned | 001/2021 | -229.33
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Labor Internal | Mapping | Not assigned | 002/2021 | 189.42
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Labor Internal | Mapping | Not assigned | 003/2021 | 4.45
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | -46.18
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 53.13
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 75.87
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 5357.73
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4514.66
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 4560.01
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 12208.98
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 12182.43
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 12304.79
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | Benefits OH | Not assigned | 001/2021 | -92.28
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | Benefits OH | Not assigned | 002/2021 | 106.17
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | Benefits OH | Not assigned | 003/2021 | 143.91
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | Building Service Overhead | Not assigned | 001/2021 | -15.84
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | Building Service Overhead | Not assigned | 002/2021 | 18.21
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | Building Service Overhead | Not assigned | 003/2021 | 26.02
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | Capitalized A&G | Not assigned | 001/2021 | -84.44
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | Capitalized A&G | Not assigned | 002/2021 | 97.15
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | Capitalized A&G | Not assigned | 003/2021 | 138.7
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | Cash Discount earned | WILSON UTILITY CONSTRUCTION COMPANY | 003/2021 | -5766.49
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | -51.94
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 59.77
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 85.32
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | IT Device OH | Not assigned | 001/2021 | -9
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | IT Device OH | Not assigned | 002/2021 | 10.35
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | IT Device OH | Not assigned | 003/2021 | 14.76
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -70.36
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 80.96
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 115.58
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | -31.18
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 35.86
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 51.21
35058794 | CWSP - APPLE HILL 2102 - 7502 - PHASE 1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 12.43
35058794 | CWSP - APPLE HILL 2102 - 7502 - PHASE 1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 10.5
35058794 | CWSP - APPLE HILL 2102 - 7502 - PHASE 1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 10.5
35058794 | CWSP - APPLE HILL 2102 - 7502 - PHASE 1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 28.32
35058794 | CWSP - APPLE HILL 2102 - 7502 - PHASE 1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 28.32
35058794 | CWSP - APPLE HILL 2102 - 7502 - PHASE 1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 28.32
35058795 | CWSP - APPLE HILL 2102 - 7502 - PHASE 2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 6.27
35058795 | CWSP - APPLE HILL 2102 - 7502 - PHASE 2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 5.3
35058795 | CWSP - APPLE HILL 2102 - 7502 - PHASE 2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 5.3
35058795 | CWSP - APPLE HILL 2102 - 7502 - PHASE 2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 14.29
35058795 | CWSP - APPLE HILL 2102 - 7502 - PHASE 2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 14.29
35058795 | CWSP - APPLE HILL 2102 - 7502 - PHASE 2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 14.29
35058797 | CWSP - APPLE HILL 2102 - 7502 - PHASE 3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 8.58
35058797 | CWSP - APPLE HILL 2102 - 7502 - PHASE 3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 7.25
35058797 | CWSP - APPLE HILL 2102 - 7502 - PHASE 3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 7.25
35058797 | CWSP - APPLE HILL 2102 - 7502 - PHASE 3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 19.56
35058797 | CWSP - APPLE HILL 2102 - 7502 - PHASE 3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 19.56
35058797 | CWSP - APPLE HILL 2102 - 7502 - PHASE 3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 19.56
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Contract | Construction Inspection | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 1280.08
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Contract | Construction Inspection | ENERGY EXPERTS INTERNATIONAL | 003/2021 | -0.05
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 002/2021 | 694.01
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 001/2021 | 1793.32
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 896.66
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 003/2021 | -896.66
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 3.13
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1.62
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | -0.91
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 9.22
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 4.77
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Labor Internal | Mapping | Not assigned | 003/2021 | -2.69
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 1.86
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.96
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | -0.54
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | Benefits OH | Not assigned | 001/2021 | 3.71
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | Benefits OH | Not assigned | 002/2021 | 1.92
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | Benefits OH | Not assigned | 003/2021 | -1.03
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.64
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.33
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | Building Service Overhead | Not assigned | 003/2021 | -0.19
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 3.39
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 1.76
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | Capitalized A&G | Not assigned | 003/2021 | -0.99
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 2.09
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1.08
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | -0.61
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | IT Device OH | Not assigned | 001/2021 | 0.36
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | IT Device OH | Not assigned | 002/2021 | 0.19
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | IT Device OH | Not assigned | 003/2021 | -0.1
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 2.83
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1.46
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | -0.83
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 1.25
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.65
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | -0.37
35059696 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1.4
35059696 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.18
35059696 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.18
35059696 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH | Other | AFUDC-Equity | Not assigned | 001/2021 | 3.18
35059696 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH | Other | AFUDC-Equity | Not assigned | 002/2021 | 3.18
35059696 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.18
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | Labor Internal | Analyst Services | Not assigned | 003/2021 | 13.92
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 4.92
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 2.8
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 154.11
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 130.86
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 130.89
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | Other | AFUDC-Equity | Not assigned | 001/2021 | 353.12
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | Other | AFUDC-Equity | Not assigned | 002/2021 | 353.12
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | Other | AFUDC-Equity | Not assigned | 003/2021 | 353.19
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | Other | Benefits OH | Not assigned | 003/2021 | 4.54
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.82
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | Other | Capitalized A&G | Not assigned | 003/2021 | 5.13
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | Other | IT Device OH | Not assigned | 003/2021 | 0.47
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 2.95
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 1.61
35060990 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH3.01 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 37.3
35060990 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH3.01 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 31.53
35060990 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH3.01 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 31.53
35060990 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH3.01 | Other | AFUDC-Equity | Not assigned | 001/2021 | 85.09
35060990 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH3.01 | Other | AFUDC-Equity | Not assigned | 002/2021 | 85.09
35060990 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH3.01 | Other | AFUDC-Equity | Not assigned | 003/2021 | 85.09
35060991 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH2.01 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 30.52
35060991 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH2.01 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 25.8
35060991 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH2.01 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 25.8
35060991 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH2.01 | Other | AFUDC-Equity | Not assigned | 001/2021 | 69.61
35060991 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH2.01 | Other | AFUDC-Equity | Not assigned | 002/2021 | 69.61
35060991 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH2.01 | Other | AFUDC-Equity | Not assigned | 003/2021 | 69.61
35060992 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH1.01 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 66.85
35060992 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH1.01 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 56.51
35060992 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH1.01 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 56.51
35060992 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH1.01 | Other | AFUDC-Equity | Not assigned | 001/2021 | 152.49
35060992 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH1.01 | Other | AFUDC-Equity | Not assigned | 002/2021 | 152.49
35060992 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH1.01 | Other | AFUDC-Equity | Not assigned | 003/2021 | 152.49
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 16216.98
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 003/2021 | 21560
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 36.63
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 45.71
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 62.69
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 88.9
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 123.36
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 169.17
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 001/2021 | 87206.4
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Labor Internal | Construction | Not assigned | 002/2021 | 148.9
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 153.12
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 51.91
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 50.93
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 1.34
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 30.84
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 30.26
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Labor Internal | Technical Services | Not assigned | 003/2021 | 4413.22
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 135.61
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 194.99
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 201.16
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 338.86
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 526.16
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 542.81
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 61.6
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 60.44
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 813.09
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 10.57
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 10.37
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 146.96
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 56.38
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 55.31
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 1624.95
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 34.68
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 34.03
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 6
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 5.88
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 83.41
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 46.98
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 46.09
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 20.82
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 20.42
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 289.29
35060995 | CWSP-BRUNSWICK 1106 LR-2104 ZONE | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3.41
35060995 | CWSP-BRUNSWICK 1106 LR-2104 ZONE | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.88
35060995 | CWSP-BRUNSWICK 1106 LR-2104 ZONE | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.88
35060995 | CWSP-BRUNSWICK 1106 LR-2104 ZONE | Other | AFUDC-Equity | Not assigned | 001/2021 | 7.77
35060995 | CWSP-BRUNSWICK 1106 LR-2104 ZONE | Other | AFUDC-Equity | Not assigned | 002/2021 | 7.77
35060995 | CWSP-BRUNSWICK 1106 LR-2104 ZONE | Other | AFUDC-Equity | Not assigned | 003/2021 | 7.77
35061041 | CWSP – MONTE RIO 1112 – TS 15401 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 64.8
35061041 | CWSP – MONTE RIO 1112 – TS 15401 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 22.89
35061041 | CWSP – MONTE RIO 1112 – TS 15401 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 13.05
35061041 | CWSP – MONTE RIO 1112 – TS 15401 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.77
35061041 | CWSP – MONTE RIO 1112 – TS 15401 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.65
35061041 | CWSP – MONTE RIO 1112 – TS 15401 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.78
35061041 | CWSP – MONTE RIO 1112 – TS 15401 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.75
35061041 | CWSP – MONTE RIO 1112 – TS 15401 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.75
35061041 | CWSP – MONTE RIO 1112 – TS 15401 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.12
35061041 | CWSP – MONTE RIO 1112 – TS 15401 | Other | Benefits OH | Not assigned | 003/2021 | 21.09
35061041 | CWSP – MONTE RIO 1112 – TS 15401 | Other | Building Service Overhead | Not assigned | 003/2021 | 3.82
35061041 | CWSP – MONTE RIO 1112 – TS 15401 | Other | Capitalized A&G | Not assigned | 003/2021 | 23.86
35061041 | CWSP – MONTE RIO 1112 – TS 15401 | Other | IT Device OH | Not assigned | 003/2021 | 2.16
35061041 | CWSP – MONTE RIO 1112 – TS 15401 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 13.71
35061041 | CWSP – MONTE RIO 1112 – TS 15401 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 7.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Contract | Construction Inspection | CANUS CORPORATION | 003/2021 | 457.11
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 3371.62
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Contract | Contracts | DISCOVERY HYDROVAC LLC | 003/2021 | 1430
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 002/2021 | 2452.72
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 003/2021 | 2328.92
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 004/2021 | -1160.74
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Contract | Electric Construction Contract | SILLER CONSTRUCTION CO | 003/2021 | 10480.7
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Contract | Electric Construction Contract | SILLER CONSTRUCTION CO | 004/2021 | -2500
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE ENGINEERING INC | 001/2021 | 14828.66
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 22.04
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | -250
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 250
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Contract | Traffic Control Contracts | ROAD SAFETY INC | 001/2021 | 940
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Contract | Traffic Control Contracts | ROAD SAFETY INC | 002/2021 | 1316
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Contract | Traffic Control Contracts | ROAD SAFETY INC | 003/2021 | 29749
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Contract | Traffic Control Contracts | ROAD SAFETY INC | 004/2021 | -12000
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 23.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Account Services | Not assigned | 001/2021 | 131.26
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Account Services | Not assigned | 002/2021 | 65.63
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Account Services | Not assigned | 003/2021 | 196.89
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 194.4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Administration | Not assigned | 002/2021 | 139.28
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Administration | Not assigned | 003/2021 | 69.64
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 195.62
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Construction | Not assigned | 001/2021 | 1042.3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Construction | Not assigned | 002/2021 | 3553.4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Construction | Not assigned | 003/2021 | 36780.6
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Construction Doubletime Services | Not assigned | 003/2021 | 9232.04
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 133.86
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 9776.22
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 854.78
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 174.1
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 226.33
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 33.98
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 16.99
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 50.97
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 394.21
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1900.84
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 19561.93
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 61.51
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 49.21
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 242.36
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 002/2021 | 262.92
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 003/2021 | 216.18
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 001/2021 | 54.08
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 002/2021 | 508.04
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 003/2021 | 108.16
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Maintain & Operate Services | Not assigned | 001/2021 | 57.1
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Maintain & Operate Services | Not assigned | 002/2021 | 753.94
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Maintain & Operate Services | Not assigned | 003/2021 | 179.7
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Management Services | Not assigned | 003/2021 | 356.2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 9.38
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 39.86
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 557.13
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 295.7
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1170.57
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 11799.57
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Labor Internal | SCADA Services | Not assigned | 002/2021 | 280.72
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 003/2021 | 1155.15
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Materials | Electl & Electronic Equipment Component | Not assigned | 002/2021 | 7367.43
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Materials | Material Burden | Not assigned | 002/2021 | 1075.64
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Materials | Material Burden | Not assigned | 003/2021 | 168.65
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 291.72
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Benefits OH | Not assigned | 001/2021 | 564.74
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Benefits OH | Not assigned | 002/2021 | 2531.07
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Benefits OH | Not assigned | 003/2021 | 22454.53
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 96.94
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 434.41
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 4058.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 540.59
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 2140.02
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 21703.14
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Cash Discount earned | ROAD SAFETY INC | 001/2021 | -18.8
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Cash Discount earned | ROAD SAFETY INC | 003/2021 | -94
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 263.38
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1270.02
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 13150.82
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | IT Device OH | Not assigned | 001/2021 | 55.02
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | IT Device OH | Not assigned | 002/2021 | 246.56
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | IT Device OH | Not assigned | 003/2021 | 2303.46
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Minor Material OH | Not assigned | 002/2021 | 600.3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Minor Material OH | Not assigned | 003/2021 | 94.12
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 356.77
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1720.29
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 17813.12
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 36.84
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 29.47
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 145.15
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Other Land Fees | RICHARD SCHLUTER | 003/2021 | 5250
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 190.8
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 855.17
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 7989.26
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Contract | Contracts | MOUNTAIN F ENTERPRISES INC | 004/2021 | -18974.16
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 002/2021 | 1200
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 003/2021 | 1811.04
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 004/2021 | -480
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Contract | Electric Construction Contract | SILLER CONSTRUCTION CO | 003/2021 | 3276.81
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 115.83
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 1129.43
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 1707
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 348.98
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 191.6
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 758.16
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | -250
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 1500
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -1000
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Account Services | Not assigned | 001/2021 | 244.93
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Account Services | Not assigned | 002/2021 | 196.89
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Account Services | Not assigned | 003/2021 | 262.52
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Administration | Not assigned | 003/2021 | 69.64
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Analyst Svcs Overtime | Not assigned | 001/2021 | 79.49
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Construction | Not assigned | 001/2021 | 3407
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Construction | Not assigned | 002/2021 | 29981.6
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Construction | Not assigned | 003/2021 | 10571.22
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Construction | Not assigned | 004/2021 | 2725.6
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 223.1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 1383.22
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 535.44
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Construction Overtime Services | Not assigned | 004/2021 | 892.32
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 1.06
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 306.24
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 415.82
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 139.28
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 69.64
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Hours - Straight Time | Not assigned | 003/2021 | 496.56
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 63.41
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 50.97
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 67.97
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1242.51
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 10834.49
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 4154.03
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 28.08
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 108.15
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 126.71
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Indirect Labor - IT | Not assigned | 003/2021 | 185.22
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 97.2
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 003/2021 | 236.93
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Maintain & Operate Services | Not assigned | 003/2021 | 717.48
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Management Services | Not assigned | 001/2021 | 42.3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 34.06
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 289.09
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 127.12
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 803.51
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 6476.43
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 2752.99
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Materials | Communication & Signaling Equipment | Not assigned | 003/2021 | 1250.13
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Materials | Electrical Specialties | Not assigned | 003/2021 | 5140.06
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Materials | Material Burden | Not assigned | 001/2021 | 291.14
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Materials | Material Burden | Not assigned | 002/2021 | 2.71
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Materials | Material Burden | Not assigned | 003/2021 | 1013.97
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 001/2021 | 1994.13
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 18.55
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 1719.28
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2774.82
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2435.47
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2567.25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6323.89
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6571.9
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6927.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Benefits OH | Not assigned | 001/2021 | 1636.06
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Benefits OH | Not assigned | 002/2021 | 12915.53
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Benefits OH | Not assigned | 003/2021 | 5354.09
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 280.81
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 2216.66
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 967.69
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 1484.55
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 11840.22
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 5032.99
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Cash Discount earned | STELLA-JONES CORPORATION | 002/2021 | -37.12
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 830.17
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 7238.97
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 2775.48
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 108.46
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | IT Device OH | Not assigned | 001/2021 | 159.37
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | IT Device OH | Not assigned | 002/2021 | 1258.11
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | IT Device OH | Not assigned | 003/2021 | 549.23
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Minor Material OH | Not assigned | 001/2021 | 162.48
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Minor Material OH | Not assigned | 002/2021 | 1.51
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Minor Material OH | Not assigned | 003/2021 | 648.69
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1124.49
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 9805.37
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 3759.47
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 16.82
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 64.78
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 194.3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Operation Mgmt & Support - IT | Not assigned | 003/2021 | 79.7
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Other Land Fees | RICHARD SCHLUTER | 003/2021 | 5250
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 552.76
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 4363.56
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 1904.97
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Other | Permits/Fees | COUNTY OF NEVADA | 001/2021 | 129.72
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE ENGINEERING INC | 001/2021 | 14828.66
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 32.29
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 154.91
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -200
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 1240
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | -750
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 32.29
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -0.17
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1.45
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | -0.76
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Labor Internal | Mapping | Not assigned | 001/2021 | -0.5
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Labor Internal | Mapping | Not assigned | 002/2021 | 4.28
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Labor Internal | Mapping | Not assigned | 003/2021 | -2.25
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | -0.1
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.86
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | -0.45
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | Benefits OH | Not assigned | 001/2021 | -0.2
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | Benefits OH | Not assigned | 002/2021 | 1.72
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | Benefits OH | Not assigned | 003/2021 | -0.85
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | Building Service Overhead | Not assigned | 001/2021 | -0.04
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.29
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | Building Service Overhead | Not assigned | 003/2021 | -0.15
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | Capitalized A&G | Not assigned | 001/2021 | -0.18
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | Capitalized A&G | Not assigned | 002/2021 | 1.58
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | Capitalized A&G | Not assigned | 003/2021 | -0.83
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | -0.11
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.97
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | -0.51
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | IT Device OH | Not assigned | 001/2021 | -0.02
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | IT Device OH | Not assigned | 002/2021 | 0.17
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | IT Device OH | Not assigned | 003/2021 | -0.09
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -0.15
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1.31
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | -0.69
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | -0.06
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.59
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | -0.3
35061810 | CWSP - EL DORADO PH 2101 ZONE 19612 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 8.44
35061810 | CWSP - EL DORADO PH 2101 ZONE 19612 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 7.13
35061810 | CWSP - EL DORADO PH 2101 ZONE 19612 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 7.13
35061810 | CWSP - EL DORADO PH 2101 ZONE 19612 | Other | AFUDC-Equity | Not assigned | 001/2021 | 19.23
35061810 | CWSP - EL DORADO PH 2101 ZONE 19612 | Other | AFUDC-Equity | Not assigned | 002/2021 | 19.23
35061810 | CWSP - EL DORADO PH 2101 ZONE 19612 | Other | AFUDC-Equity | Not assigned | 003/2021 | 19.23
35061811 | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 13.28
35061811 | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 11.22
35061811 | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 11.22
35061811 | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 30.28
35061811 | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 30.28
35061811 | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 30.28
35061812 | CWSP - EL DORADO PH 2102 ZONE 6645 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 11.99
35061812 | CWSP - EL DORADO PH 2102 ZONE 6645 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 10.13
35061812 | CWSP - EL DORADO PH 2102 ZONE 6645 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 10.13
35061812 | CWSP - EL DORADO PH 2102 ZONE 6645 | Other | AFUDC-Equity | Not assigned | 001/2021 | 27.33
35061812 | CWSP - EL DORADO PH 2102 ZONE 6645 | Other | AFUDC-Equity | Not assigned | 002/2021 | 27.33
35061812 | CWSP - EL DORADO PH 2102 ZONE 6645 | Other | AFUDC-Equity | Not assigned | 003/2021 | 27.33
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 219.22
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -219.22
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 1299.72
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 4264.54
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 210.12
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 712.5
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 23.75
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Construction | Not assigned | 002/2021 | 595.6
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Design Overtime Services | Not assigned | 001/2021 | 436.4
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Design Services | Not assigned | 001/2021 | 29.61
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Design Services Double Time | Not assigned | 001/2021 | 59.2
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 2285.4
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1265.76
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 174.1
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Hours - Overtime | Not assigned | 003/2021 | 224.33
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Hours - Straight Time | Not assigned | 003/2021 | 124.14
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 954.85
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 637.18
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.21
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 233.21
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 206.04
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Indirect Labor - IT | Not assigned | 003/2021 | 129.98
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 97.2
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 001/2021 | 388.8
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 583.2
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Management Services | Not assigned | 001/2021 | 88.31
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 6.04
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 18.22
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.63
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 700.22
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 496
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 70.31
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 62.19
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 73.38
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 127.81
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 145.94
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 198.02
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 344.89
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Benefits OH | Not assigned | 001/2021 | 1376.64
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Benefits OH | Not assigned | 002/2021 | 956.12
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Benefits OH | Not assigned | 003/2021 | 111.63
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 236.28
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 164.09
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 20.17
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 1312.66
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 906.8
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 128.54
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 637.96
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 425.71
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.14
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | IT Device OH | Not assigned | 001/2021 | 134.09
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | IT Device OH | Not assigned | 002/2021 | 93.13
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | IT Device OH | Not assigned | 003/2021 | 11.45
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 864.15
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 576.66
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.19
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 139.68
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 123.41
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Operation Mgmt & Support - IT | Not assigned | 003/2021 | 55.93
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 465.07
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 323.02
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 39.71
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 003/2021 | 56329.28
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 004/2021 | -55000
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 219.22
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -219.22
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 6156.09
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 210.12
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 118.75
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 118.75
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 47.5
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Account Services | Not assigned | 002/2021 | 131.26
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 129.6
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 32.4
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 64.8
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Design Overtime Services | Not assigned | 002/2021 | 523.68
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Design Services | Not assigned | 001/2021 | 976.97
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Design Services Double Time | Not assigned | 001/2021 | 414.4
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 2109.6
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 889.33
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 291.61
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 001/2021 | 603.78
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 174.1
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 174.1
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 69.64
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Hours - Straight Time | Not assigned | 003/2021 | 124.14
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 33.98
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1391.63
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 485.39
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 99.12
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 370.58
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 11.45
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 84.4
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Indirect Labor - IT | Not assigned | 003/2021 | 46.3
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 550.8
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 001/2021 | 194.4
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Management Services | Not assigned | 001/2021 | 88.31
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.36
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 18.82
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.77
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 1038.01
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 321.34
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 132.01
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 21.97
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 41.93
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 147.51
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 55.63
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 113.14
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 398.03
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Benefits OH | Not assigned | 001/2021 | 2028.28
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Benefits OH | Not assigned | 002/2021 | 624.37
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Benefits OH | Not assigned | 003/2021 | 229.12
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 348.09
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 107.16
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 41.42
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 1930.22
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 587.46
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 241.33
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 929.81
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 324.3
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 66.22
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | IT Device OH | Not assigned | 001/2021 | 197.6
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | IT Device OH | Not assigned | 002/2021 | 60.83
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | IT Device OH | Not assigned | 003/2021 | 23.51
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1259.44
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 439.28
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 89.7
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 221.95
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 6.86
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 50.55
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Operation Mgmt & Support - IT | Not assigned | 003/2021 | 19.92
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 685.25
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 210.97
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 81.51
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 003/2021 | 120864.52
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 004/2021 | -120000
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 219.22
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -219.22
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 1992.01
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 105.06
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 118.75
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 166.25
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Account Services | Not assigned | 003/2021 | 131.26
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 129.6
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Construction | Not assigned | 002/2021 | 595.6
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Design Overtime Services | Not assigned | 001/2021 | 349.12
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Design Services | Not assigned | 001/2021 | 207.24
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 2250.24
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 580.66
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 140.64
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 001/2021 | 1106.93
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 208.92
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 278.56
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Hours - Straight Time | Not assigned | 002/2021 | 248.28
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Hours - Straight Time | Not assigned | 003/2021 | 372.42
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 33.98
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1326.81
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 402.76
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 47.79
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 211.18
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 178.54
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Indirect Labor - IT | Not assigned | 002/2021 | 92.61
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Indirect Labor - IT | Not assigned | 003/2021 | 138.91
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 97.2
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 001/2021 | 162
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 226.8
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Management Services | Not assigned | 001/2021 | 88.31
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.36
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 11.83
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.32
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 908.63
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 289.28
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 231.61
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 14.92
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 31.1
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 38.7
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 38.9
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 83.92
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 104.42
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Benefits OH | Not assigned | 001/2021 | 1796.74
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Benefits OH | Not assigned | 002/2021 | 561.59
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Benefits OH | Not assigned | 003/2021 | 372.67
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 308.36
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 96.38
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 67.36
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 1693.69
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 528.88
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 423.44
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 886.5
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 269.11
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 31.92
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | IT Device OH | Not assigned | 001/2021 | 175.04
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | IT Device OH | Not assigned | 002/2021 | 54.68
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | IT Device OH | Not assigned | 003/2021 | 38.23
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Land Acquisition Services | BENDER ROSENTHAL INC | 001/2021 | 522.5
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1200.78
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 364.51
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 43.25
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 126.47
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 106.94
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Operation Mgmt & Support - IT | Not assigned | 002/2021 | 39.85
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Operation Mgmt & Support - IT | Not assigned | 003/2021 | 59.77
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 607.02
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 189.74
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 132.59
35064793 | LP RECONDUCTOR, CABRILLO 1104 S006CC102 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 4310.25
35064793 | LP RECONDUCTOR, CABRILLO 1104 S006CC102 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 3640.17
35064793 | LP RECONDUCTOR, CABRILLO 1104 S006CC102 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1820.09
35064793 | LP RECONDUCTOR, CABRILLO 1104 S006CC102 | Other | AFUDC-Equity | Not assigned | 001/2021 | 9822.69
35064793 | LP RECONDUCTOR, CABRILLO 1104 S006CC102 | Other | AFUDC-Equity | Not assigned | 002/2021 | 9822.69
35064793 | LP RECONDUCTOR, CABRILLO 1104 S006CC102 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4911.34
35065842 | CWSP-EL DORADO 2101 - LR 26000 - PH3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3.15
35065842 | CWSP-EL DORADO 2101 - LR 26000 - PH3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.66
35065842 | CWSP-EL DORADO 2101 - LR 26000 - PH3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.66
35065842 | CWSP-EL DORADO 2101 - LR 26000 - PH3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 7.17
35065842 | CWSP-EL DORADO 2101 - LR 26000 - PH3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 7.17
35065842 | CWSP-EL DORADO 2101 - LR 26000 - PH3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 7.17
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 335.03
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 113.58
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 67.48
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 99.87
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 85.3
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 85.3
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | Other | AFUDC-Equity | Not assigned | 001/2021 | 227.97
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | Other | AFUDC-Equity | Not assigned | 002/2021 | 230.17
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | Other | AFUDC-Equity | Not assigned | 003/2021 | 230.17
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | Other | Benefits OH | Not assigned | 001/2021 | 134.8
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | Other | Building Service Overhead | Not assigned | 001/2021 | 23.14
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | Other | Capitalized A&G | Not assigned | 001/2021 | 123.36
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | Other | Fleet OH - Elec | Not assigned | 001/2021 | 75.88
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | Other | IT Device OH | Not assigned | 001/2021 | 13.12
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 102.79
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | Other | Payroll Taxes OH | Not assigned | 001/2021 | 45.54
35067619 | CWSP – MONTE RIO 1112 – LR 120 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.43
35067619 | CWSP – MONTE RIO 1112 – LR 120 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.36
35067619 | CWSP – MONTE RIO 1112 – LR 120 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.36
35067619 | CWSP – MONTE RIO 1112 – LR 120 | Other | AFUDC-Equity | Not assigned | 001/2021 | 0.97
35067619 | CWSP – MONTE RIO 1112 – LR 120 | Other | AFUDC-Equity | Not assigned | 002/2021 | 0.97
35067619 | CWSP – MONTE RIO 1112 – LR 120 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.97
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 499.6
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 003/2021 | 46369.1
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 47.67
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 | Labor Internal | Mapping | Not assigned | 003/2021 | 140.61
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 28.32
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 | Other | Benefits OH | Not assigned | 003/2021 | 53.73
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 | Other | Building Service Overhead | Not assigned | 003/2021 | 9.71
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 | Other | Capitalized A&G | Not assigned | 003/2021 | 51.77
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 31.85
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 | Other | IT Device OH | Not assigned | 003/2021 | 5.51
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 43.14
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 19.12
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Labor Internal | Account Services | Not assigned | 001/2021 | 49.23
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 12.75
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 75.72
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 9.91
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 44.98
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 307.14
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 299.35
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 338.89
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 700.82
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 807.76
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 914.46
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 13.95
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 89.88
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 2.39
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.42
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 18.13
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 82.24
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 50.59
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 1.36
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 8.76
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 68.52
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 4.71
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.36
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 002/2021 | 49521.26
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Contract | Contracts | MARIOS TREE SERVICE INC | 002/2021 | 11536.89
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Contract | Contracts | Not assigned | 002/2021 | -11536.89
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Contract | Environmental Contract | FAR WESTERN ANTHROPOLOGICAL | 002/2021 | 159
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -250
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 500
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Labor Internal | Construction | Not assigned | 001/2021 | 65.24
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 110.87
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1340.1
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 476.36
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 25.4
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 114.15
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Labor Internal | Mapping | Not assigned | 001/2021 | -0.16
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.48
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 2.5
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 283.01
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 15.09
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 67.81
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Materials | Material Burden | Not assigned | 002/2021 | -10129.68
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Materials | Material Burden | Not assigned | 003/2021 | -7.44
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 003/2021 | -50.97
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | -69381.34
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1432.26
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1119.7
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1057.02
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3185.42
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3021.41
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2852.28
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Benefits OH | Not assigned | 001/2021 | 565.37
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Benefits OH | Not assigned | 002/2021 | -1935.27
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Benefits OH | Not assigned | 003/2021 | 127.27
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 97.04
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Building Service Overhead | Not assigned | 002/2021 | -332.15
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 22.99
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 517.38
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 27.58
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 123.98
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 318.27
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 16.97
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 76.27
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | IT Device OH | Not assigned | 001/2021 | 55.08
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | IT Device OH | Not assigned | 002/2021 | -188.52
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | IT Device OH | Not assigned | 003/2021 | 13.06
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Minor Material OH | Not assigned | 002/2021 | -5653.23
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Minor Material OH | Not assigned | 003/2021 | -4.15
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 431.11
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 22.99
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 103.31
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 191.02
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | -653.83
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 45.28
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 002/2021 | 12607.55
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 003/2021 | 10087.65
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -2715
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | 2715
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 430.52
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 34.82
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.44
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 12.3
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.29
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 7.27
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 278.16
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 253.32
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 273.33
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 652.79
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 683.55
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 737.55
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 12.47
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 2.14
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 13.29
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.29
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 1.21
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.4
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 7.37
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 4.21
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 001/2021 | 1342.61
35074388 | RECOND GV2101 FUSE 12347 ZONE | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.04
35074388 | RECOND GV2101 FUSE 12347 ZONE | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.72
35074388 | RECOND GV2101 FUSE 12347 ZONE | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.72
35074388 | RECOND GV2101 FUSE 12347 ZONE | Other | AFUDC-Equity | Not assigned | 001/2021 | 4.63
35074388 | RECOND GV2101 FUSE 12347 ZONE | Other | AFUDC-Equity | Not assigned | 002/2021 | 4.63
35074388 | RECOND GV2101 FUSE 12347 ZONE | Other | AFUDC-Equity | Not assigned | 003/2021 | 4.63
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Contract | Contracts | Not assigned | 003/2021 | 2622.78
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 219.22
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -219.22
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 2580.85
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 1249.2
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 308.75
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 142.5
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 285
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Administration | Not assigned | 002/2021 | 139.28
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Administration | Not assigned | 003/2021 | 278.56
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Administrative Services - OT | Not assigned | 001/2021 | 185.82
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Analyst Services | Not assigned | 003/2021 | 55.69
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Analyst Svcs Overtime | Not assigned | 003/2021 | 158.98
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Construction | Not assigned | 002/2021 | 521.92
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Design Drafting Services | Not assigned | 001/2021 | 5299.35
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Design Drafting Services | Not assigned | 002/2021 | 7904.62
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 001/2021 | 2443.84
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 002/2021 | 4974.96
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Design Services | Not assigned | 001/2021 | 384.87
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Drafting Doubletime | Not assigned | 001/2021 | 2249.6
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Drafting Doubletime | Not assigned | 002/2021 | 4558.4
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1335.98
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 483.93
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 139.28
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 278.56
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 174.1
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 3518.35
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 6545.69
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 168.28
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 126.31
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 147.62
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 235.77
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 001/2021 | 32.4
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.93
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Mapping | Not assigned | 002/2021 | 12.87
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Mapping | Not assigned | 003/2021 | 12.47
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 2162.25
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 3972.93
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 234.36
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Benefits OH | Not assigned | 001/2021 | 4298.35
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Benefits OH | Not assigned | 002/2021 | 7912.06
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Benefits OH | Not assigned | 003/2021 | 406.81
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Building Service Overhead | Not assigned | 001/2021 | 737.71
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Building Service Overhead | Not assigned | 002/2021 | 1357.94
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Building Service Overhead | Not assigned | 003/2021 | 73.55
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Capitalized A&G | Not assigned | 001/2021 | 3953.02
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Capitalized A&G | Not assigned | 002/2021 | 7263.35
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Capitalized A&G | Not assigned | 003/2021 | 428.49
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 2350.75
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 4373.43
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 112.43
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | IT Device OH | Not assigned | 001/2021 | 418.71
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | IT Device OH | Not assigned | 002/2021 | 770.71
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | IT Device OH | Not assigned | 003/2021 | 41.72
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 3184.16
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 5923.9
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 152.3
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 75.64
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 88.41
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 141.2
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 1452.22
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 2673.16
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 144.76
35077348 | RECONDUCTOR 17547 FT OF 4ACSR W 2CU TW | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1.65
35077348 | RECONDUCTOR 17547 FT OF 4ACSR W 2CU TW | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.39
35077348 | RECONDUCTOR 17547 FT OF 4ACSR W 2CU TW | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.39
35077348 | RECONDUCTOR 17547 FT OF 4ACSR W 2CU TW | Other | AFUDC-Equity | Not assigned | 001/2021 | 3.75
35077348 | RECONDUCTOR 17547 FT OF 4ACSR W 2CU TW | Other | AFUDC-Equity | Not assigned | 002/2021 | 3.75
35077348 | RECONDUCTOR 17547 FT OF 4ACSR W 2CU TW | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.75
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 003/2021 | 5172.18
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 004/2021 | -5172.18
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 227.15
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 134.95
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR | Labor Internal | Project Management Services | Not assigned | 001/2021 | 670.05
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR | Other | Benefits OH | Not assigned | 001/2021 | 269.61
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR | Other | Building Service Overhead | Not assigned | 001/2021 | 46.27
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR | Other | Capitalized A&G | Not assigned | 001/2021 | 246.71
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR | Other | Fleet OH - Elec | Not assigned | 001/2021 | 151.77
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR | Other | IT Device OH | Not assigned | 001/2021 | 26.26
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 205.57
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR | Other | Payroll Taxes OH | Not assigned | 001/2021 | 91.09
35081862 | MARTELL 1101 RECOND. 4ACSR W/ 1/0AR TW | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 5.34
35081862 | MARTELL 1101 RECOND. 4ACSR W/ 1/0AR TW | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4.51
35081862 | MARTELL 1101 RECOND. 4ACSR W/ 1/0AR TW | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 4.51
35081862 | MARTELL 1101 RECOND. 4ACSR W/ 1/0AR TW | Other | AFUDC-Equity | Not assigned | 001/2021 | 12.17
35081862 | MARTELL 1101 RECOND. 4ACSR W/ 1/0AR TW | Other | AFUDC-Equity | Not assigned | 002/2021 | 12.17
35081862 | MARTELL 1101 RECOND. 4ACSR W/ 1/0AR TW | Other | AFUDC-Equity | Not assigned | 003/2021 | 12.17
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E | Labor Internal | Hours - Straight Time | Not assigned | 002/2021 | 341.39
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 18.33
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E | Labor Internal | Indirect Labor - IT | Not assigned | 002/2021 | 127.34
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 002/2021 | 54.08
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 79.65
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E | Other | Benefits OH | Not assigned | 002/2021 | 136.67
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E | Other | Building Service Overhead | Not assigned | 002/2021 | 23.46
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E | Other | Capitalized A&G | Not assigned | 002/2021 | 145.61
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E | Other | Fleet OH - Elec | Not assigned | 002/2021 | 12.25
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E | Other | IT Device OH | Not assigned | 002/2021 | 13.31
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 16.59
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E | Other | Operation Mgmt & Support - IT | Not assigned | 002/2021 | 54.79
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E | Other | Payroll Taxes OH | Not assigned | 002/2021 | 46.18
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 003/2021 | 300
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 004/2021 | -300
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 126.19
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.31
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Labor Internal | Mapping | Not assigned | 003/2021 | 0.9
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 74.97
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 0.18
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Labor Internal | Project Management Services | Not assigned | 001/2021 | 372.25
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Other | Benefits OH | Not assigned | 001/2021 | 149.77
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Other | Benefits OH | Not assigned | 003/2021 | 0.35
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Other | Building Service Overhead | Not assigned | 001/2021 | 25.71
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Other | Building Service Overhead | Not assigned | 003/2021 | 0.06
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Other | Capitalized A&G | Not assigned | 001/2021 | 137.06
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Other | Capitalized A&G | Not assigned | 003/2021 | 0.33
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Other | Fleet OH - Elec | Not assigned | 001/2021 | 84.31
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.2
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Other | IT Device OH | Not assigned | 001/2021 | 14.59
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Other | IT Device OH | Not assigned | 003/2021 | 0.04
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 114.21
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.28
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Other | Payroll Taxes OH | Not assigned | 001/2021 | 50.6
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.13
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H | Contract | Contracts | CANUS CORPORATION | 003/2021 | 379.63
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 003/2021 | 33874.91
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 34.84
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H | Labor Internal | Mapping | Not assigned | 003/2021 | 102.76
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 20.7
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H | Other | Benefits OH | Not assigned | 003/2021 | 39.26
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H | Other | Building Service Overhead | Not assigned | 003/2021 | 7.09
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H | Other | Capitalized A&G | Not assigned | 003/2021 | 37.84
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H | Other | Fleet OH - Elec | Not assigned | 003/2021 | 23.28
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H | Other | IT Device OH | Not assigned | 003/2021 | 4.03
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 31.53
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H | Other | Payroll Taxes OH | Not assigned | 003/2021 | 13.96
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 003/2021 | 79591.68
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 80.95
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 | Labor Internal | Mapping | Not assigned | 003/2021 | 238.78
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 48.09
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 | Other | Benefits OH | Not assigned | 003/2021 | 91.23
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 | Other | Building Service Overhead | Not assigned | 003/2021 | 16.49
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 | Other | Capitalized A&G | Not assigned | 003/2021 | 87.92
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 54.08
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 | Other | IT Device OH | Not assigned | 003/2021 | 9.36
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 73.26
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 32.46
35085680 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 154.55
35085680 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 130.65
35085680 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 130.65
35085680 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 352.54
35085680 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 352.54
35085680 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 352.54
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 2250
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 47.5
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 23.75
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 002/2021 | 90
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 003/2021 | 114.02
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 97.81
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 139.28
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 34.82
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.14
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.14
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 49.21
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 46.86
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.41
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.41
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 28.05
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.08
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 26.79
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | Benefits OH | Not assigned | 001/2021 | 47.73
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | Benefits OH | Not assigned | 002/2021 | 0.17
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | Benefits OH | Not assigned | 003/2021 | 43.32
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | Building Service Overhead | Not assigned | 001/2021 | 8.19
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.02
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | Building Service Overhead | Not assigned | 003/2021 | 7.83
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | Capitalized A&G | Not assigned | 001/2021 | 51.28
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.15
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | Capitalized A&G | Not assigned | 003/2021 | 48.98
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | Encroachment Permit Fees | COUNTY OF SANTA CRUZ | 001/2021 | 874
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.09
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.09
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | IT Device OH | Not assigned | 001/2021 | 4.65
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | IT Device OH | Not assigned | 002/2021 | 0.02
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | IT Device OH | Not assigned | 003/2021 | 4.45
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.13
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.13
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 29.47
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 28.07
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 16.13
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.06
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 15.41
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Labor Internal | Account Services | Not assigned | 001/2021 | 32.82
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Labor Internal | Account Services | Not assigned | 002/2021 | 16.41
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 2.12
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 335.03
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 8.5
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 4.25
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.72
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 113.58
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 7.04
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 3.3
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 67.48
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 136.45
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 115.45
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 116.29
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 311.29
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 311.54
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 313.81
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | Benefits OH | Not assigned | 001/2021 | 10.16
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | Benefits OH | Not assigned | 002/2021 | 4.65
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | Benefits OH | Not assigned | 003/2021 | 128
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | Building Service Overhead | Not assigned | 001/2021 | 1.74
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.8
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | Building Service Overhead | Not assigned | 003/2021 | 23.14
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | Capitalized A&G | Not assigned | 001/2021 | 12.86
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | Capitalized A&G | Not assigned | 002/2021 | 6.04
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | Capitalized A&G | Not assigned | 003/2021 | 123.36
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.48
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 75.88
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | IT Device OH | Not assigned | 001/2021 | 0.99
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | IT Device OH | Not assigned | 002/2021 | 0.45
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | IT Device OH | Not assigned | 003/2021 | 13.12
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.65
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 102.79
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 3.43
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 1.56
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 45.54
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Labor Internal | Account Services | Not assigned | 001/2021 | 16.41
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 335.03
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 335.03
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 4.25
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 113.58
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 113.58
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 70.78
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 67.48
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 49.05
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 43.52
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 44.29
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 113.2
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 117.43
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 119.51
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | Benefits OH | Not assigned | 001/2021 | 139.45
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | Benefits OH | Not assigned | 002/2021 | 134.8
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | Building Service Overhead | Not assigned | 001/2021 | 23.94
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | Building Service Overhead | Not assigned | 002/2021 | 23.14
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | Capitalized A&G | Not assigned | 001/2021 | 129.4
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | Capitalized A&G | Not assigned | 002/2021 | 123.36
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 75.88
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 75.88
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | IT Device OH | Not assigned | 001/2021 | 13.57
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | IT Device OH | Not assigned | 002/2021 | 13.12
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 102.79
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 102.79
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 47.1
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 45.54
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | Labor Internal | Electric Estimating Doubletime | Not assigned | 001/2021 | 9.18
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 7.42
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 5.63
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 3.34
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | Materials | Conductors, Cable & Wire Connectors | Not assigned | 001/2021 | -5262.41
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | Materials | Material Burden | Not assigned | 001/2021 | -3961.26
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 001/2021 | -21869.52
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | Other | Benefits OH | Not assigned | 001/2021 | -761.92
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | Other | Building Service Overhead | Not assigned | 001/2021 | -130.77
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | Other | Capitalized A&G | Not assigned | 001/2021 | 6.11
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | Other | Fleet OH - Elec | Not assigned | 001/2021 | 3.76
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | Other | IT Device OH | Not assigned | 001/2021 | -74.22
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | Other | Minor Material OH | Not assigned | 001/2021 | -2210.73
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 5.09
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | Other | Payroll Taxes OH | Not assigned | 001/2021 | -257.41
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 250
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | -250
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Labor Internal | Account Services | Not assigned | 001/2021 | 16.41
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 4.25
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 252.39
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.25
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | -0.25
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.75
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Labor Internal | Mapping | Not assigned | 003/2021 | -0.75
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 153.24
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.15
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | -0.15
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Labor Internal | Project Management Services | Not assigned | 001/2021 | 744.5
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | Benefits OH | Not assigned | 001/2021 | 304.22
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | Benefits OH | Not assigned | 002/2021 | 0.3
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | Benefits OH | Not assigned | 003/2021 | -0.28
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | Building Service Overhead | Not assigned | 001/2021 | 52.22
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.05
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | Building Service Overhead | Not assigned | 003/2021 | -0.05
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | Capitalized A&G | Not assigned | 001/2021 | 280.16
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.28
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | Capitalized A&G | Not assigned | 003/2021 | -0.28
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 168.63
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.17
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | Fleet OH - Elec | Not assigned | 003/2021 | -0.17
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | IT Device OH | Not assigned | 001/2021 | 29.63
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | IT Device OH | Not assigned | 002/2021 | 0.03
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | IT Device OH | Not assigned | 003/2021 | -0.03
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 228.41
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.23
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | -0.23
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 102.77
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.1
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | Other | Payroll Taxes OH | Not assigned | 003/2021 | -0.1
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 335.03
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 70.58
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 335.03
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 113.58
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 23.93
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 113.58
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 67.48
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.21
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 67.48
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 103.98
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 89
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 89.98
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | AFUDC-Equity | Not assigned | 001/2021 | 237.5
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | AFUDC-Equity | Not assigned | 002/2021 | 240.16
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | AFUDC-Equity | Not assigned | 003/2021 | 242.8
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | Benefits OH | Not assigned | 001/2021 | 134.8
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | Benefits OH | Not assigned | 002/2021 | 28.39
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | Benefits OH | Not assigned | 003/2021 | 128
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | Building Service Overhead | Not assigned | 001/2021 | 23.14
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | Building Service Overhead | Not assigned | 002/2021 | 4.87
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | Building Service Overhead | Not assigned | 003/2021 | 23.14
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | Capitalized A&G | Not assigned | 001/2021 | 123.36
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | Capitalized A&G | Not assigned | 002/2021 | 25.99
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | Capitalized A&G | Not assigned | 003/2021 | 123.36
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 75.88
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 15.99
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 75.88
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | IT Device OH | Not assigned | 001/2021 | 13.12
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | IT Device OH | Not assigned | 002/2021 | 2.76
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | IT Device OH | Not assigned | 003/2021 | 13.12
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 102.79
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 21.65
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 102.79
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 45.54
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 9.61
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 45.54
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | TRC SOLUTIONS INC | 002/2021 | 210
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | TRC SOLUTIONS INC | 003/2021 | -210
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Labor Internal | Account Services | Not assigned | 001/2021 | 32.82
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Labor Internal | Account Services | Not assigned | 002/2021 | 16.41
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 335.03
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 335.03
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 8.5
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 4.25
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 113.58
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 113.58
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 74.09
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 70.78
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 53.97
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 47.89
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 48.67
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | AFUDC-Equity | Not assigned | 001/2021 | 124.49
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | AFUDC-Equity | Not assigned | 002/2021 | 129.22
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | AFUDC-Equity | Not assigned | 003/2021 | 131.33
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | Benefits OH | Not assigned | 001/2021 | 144.11
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | Benefits OH | Not assigned | 002/2021 | 139.45
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | Building Service Overhead | Not assigned | 001/2021 | 24.73
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | Building Service Overhead | Not assigned | 002/2021 | 23.94
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | Capitalized A&G | Not assigned | 001/2021 | 135.44
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | Capitalized A&G | Not assigned | 002/2021 | 129.4
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 75.88
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 75.88
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | IT Device OH | Not assigned | 001/2021 | 14.03
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | IT Device OH | Not assigned | 002/2021 | 13.57
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 102.79
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 102.79
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 48.68
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 47.1
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 002/2021 | 1540
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -250
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 500
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 500
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Contract | Gas Construction Contract | LUCCHETTI ENTERPRISES INC | 001/2021 | 28202.45
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Contract | Traffic Control Contracts | LUCCHETTI ENTERPRISES INC | 001/2021 | 2467.35
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Contract | Traffic Control Contracts | LUCCHETTI ENTERPRISES INC | 002/2021 | 3743.5
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Administration | Not assigned | 001/2021 | 139.28
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Construction | Not assigned | 001/2021 | 50628.02
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Construction Doubletime Services | Not assigned | 001/2021 | 1197.3
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 15080.23
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1600.68
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 335.03
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.46
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Field Services | Not assigned | 001/2021 | 75.75
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 24130.9
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 342.8
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.75
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 49.21
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 001/2021 | 576.48
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 001/2021 | 108.16
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Maintain & Operate Services | Not assigned | 001/2021 | 38.07
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Mapping | Not assigned | 001/2021 | 686.69
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Mapping | Not assigned | 002/2021 | 6.12
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Mapping | Not assigned | 003/2021 | 1.5
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 14364.22
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 203.65
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 15.3
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Project Management Services | Not assigned | 001/2021 | 1191.2
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Labor Internal | Project Management Services | Not assigned | 002/2021 | 670.05
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 003/2021 | -5344.77
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Materials | Material Burden | Not assigned | 003/2021 | -983.25
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | -1389.85
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Benefits OH | Not assigned | 001/2021 | 28688.11
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Benefits OH | Not assigned | 002/2021 | 406.88
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Benefits OH | Not assigned | 003/2021 | -152.14
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Building Service Overhead | Not assigned | 001/2021 | 4923.64
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Building Service Overhead | Not assigned | 002/2021 | 69.83
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Building Service Overhead | Not assigned | 003/2021 | -27.5
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Capitalized A&G | Not assigned | 001/2021 | 26260.7
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Capitalized A&G | Not assigned | 002/2021 | 372.32
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Capitalized A&G | Not assigned | 003/2021 | 27.97
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Cash Discount earned | LUCCHETTI ENTERPRISES INC | 001/2021 | -344.24
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Cash Discount earned | LUCCHETTI ENTERPRISES INC | 002/2021 | -386.37
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 16122.85
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 229.04
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 17.21
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | IT Device OH | Not assigned | 001/2021 | 2794.48
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | IT Device OH | Not assigned | 002/2021 | 39.64
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | IT Device OH | Not assigned | 003/2021 | -15.6
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Minor Material OH | Not assigned | 003/2021 | -548.74
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 21838.82
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 310.24
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 23.3
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 29.47
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 9692.34
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 137.46
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Other | Payroll Taxes OH | Not assigned | 003/2021 | -54.14
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Contract | Construction Management Contracts | TRC SOLUTIONS INC | 002/2021 | 236
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 347.49
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 348.98
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | -348.98
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 241.36
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 23.75
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 23.75
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 71.25
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 003/2021 | 306.8
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 453.6
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 64.8
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Analyst Services | Not assigned | 002/2021 | 111.38
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Analyst Services | Not assigned | 003/2021 | 222.76
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Analyst Svcs Overtime | Not assigned | 002/2021 | 158.98
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 192.44
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 296.05
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1861.25
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 3089.68
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 483.93
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 626.76
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 34.82
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 696.93
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1147.42
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 164.68
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 381.69
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 142.16
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 78.7
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Manage L&EM | Not assigned | 002/2021 | 32.4
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 2.16
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | -0.98
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 1.86
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 631.64
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 762.72
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 142.69
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 314.14
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 286.65
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 299.59
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 723.92
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 773.49
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 808.42
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 1197.42
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 1499.76
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 258.11
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 205.51
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 257.42
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 46.64
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 1154.76
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 1394.43
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 260.88
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 465.65
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 766.65
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 110.03
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 116.65
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 146.09
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 26.49
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 630.73
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1038.44
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 149.04
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 228.6
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 85.15
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 47.14
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 404.55
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 506.67
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 91.83
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 002/2021 | 3182.81
35094514 | CWSP-ORO FINO 1101 LR-2022 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 120.51
35094514 | CWSP-ORO FINO 1101 LR-2022 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 101.88
35094514 | CWSP-ORO FINO 1101 LR-2022 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 101.88
35094514 | CWSP-ORO FINO 1101 LR-2022 PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 274.92
35094514 | CWSP-ORO FINO 1101 LR-2022 PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 274.92
35094514 | CWSP-ORO FINO 1101 LR-2022 PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 274.92
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -543
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 20.83
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 17.18
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 17.18
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 47.51
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 46.36
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 46.36
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 001/2021 | 20200
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | -20200
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -1086
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | 1086
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 1137.78
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1.16
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 3.41
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.69
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 107.21
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 110.13
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 95.86
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 254.18
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 297.19
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 258.68
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 1.38
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.23
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 1.26
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.77
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 0.13
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1.05
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.46
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 001/2021 | 38557.9
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 002/2021 | -38557.9
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 1479.11
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1.51
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 4.44
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.89
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 162.36
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 143.89
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 115.64
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 385.32
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 388.27
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 312.03
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | Other | Benefits OH | Not assigned | 001/2021 | 1.79
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.31
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 1.63
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1.01
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | Other | IT Device OH | Not assigned | 001/2021 | 0.17
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1.36
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.61
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLAIR CHURCH & FLYNN CONSULTING | 001/2021 | -143200.57
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLAIR CHURCH & FLYNN CONSULTING | 002/2021 | 35952.33
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -13937
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | 10679
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 176.4
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 62.18
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 98.9
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 402.61
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 167.79
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 266.88
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 002/2021 | 12607.55
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 003/2021 | 10349.45
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 003/2021 | 339.02
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.35
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | Labor Internal | Mapping | Not assigned | 003/2021 | 1.02
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 0.21
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 275.55
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 244.43
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 262.78
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 632.79
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 659.58
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 709.09
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | Other | Benefits OH | Not assigned | 003/2021 | 0.39
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.07
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | Other | Capitalized A&G | Not assigned | 003/2021 | 0.38
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.23
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | Other | IT Device OH | Not assigned | 003/2021 | 0.04
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.31
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.14
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 002/2021 | 12607.55
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 003/2021 | 2216.45
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -4977.5
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | 4977.5
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 85.17
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 81.92
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 97.51
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 194.26
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 221.05
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 263.13
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 166.63
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 59.36
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.17
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.06
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.5
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.18
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.1
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.04
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 191.21
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 161.93
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 161.98
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 436.47
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 436.95
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 437.08
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 0.2
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 0.07
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.04
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.02
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.18
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.07
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.11
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.04
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 0.02
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.15
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.06
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.06
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.02
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE ENGINEERING INC | 001/2021 | -2800
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 153.12
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 51.91
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 30.84
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 272.79
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 229.98
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 229.98
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 625.53
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 620.59
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 620.59
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | Other | Benefits OH | Not assigned | 001/2021 | 61.6
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 10.57
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 56.38
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 34.68
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | Other | IT Device OH | Not assigned | 001/2021 | 6
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 46.98
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 20.82
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 001/2021 | 52376.73
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 002/2021 | -52376.73
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | 44547.54
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 129.6
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 446.7
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 151.43
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 75.72
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 45.79
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 116.07
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 44.98
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 226.8
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 208.5
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 204.24
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 543.39
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 562.62
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 551.12
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | Benefits OH | Not assigned | 001/2021 | 224.16
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | Benefits OH | Not assigned | 002/2021 | 89.88
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 38.47
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.42
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 212.19
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 82.24
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 101.18
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 50.59
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | IT Device OH | Not assigned | 001/2021 | 21.83
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | IT Device OH | Not assigned | 002/2021 | 8.76
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 137.05
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 68.52
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 27.42
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 75.72
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.36
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 001/2021 | 4905.7
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 002/2021 | 1725.3
35095164 | CWSP-ORO FINO 1101 LR-2022 PH 3.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 346.99
35095164 | CWSP-ORO FINO 1101 LR-2022 PH 3.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 293.46
35095164 | CWSP-ORO FINO 1101 LR-2022 PH 3.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 293.46
35095164 | CWSP-ORO FINO 1101 LR-2022 PH 3.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 791.88
35095164 | CWSP-ORO FINO 1101 LR-2022 PH 3.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 791.88
35095164 | CWSP-ORO FINO 1101 LR-2022 PH 3.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 791.88
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 001/2021 | 896.66
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.91
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 2.69
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.54
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 | Other | Benefits OH | Not assigned | 001/2021 | 1.08
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.19
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.99
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.61
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 | Other | IT Device OH | Not assigned | 001/2021 | 0.1
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.83
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.37
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | -250
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | -0.25
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Labor Internal | Mapping | Not assigned | 002/2021 | -0.75
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | -0.15
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Other | Benefits OH | Not assigned | 002/2021 | -0.3
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Other | Building Service Overhead | Not assigned | 002/2021 | -0.05
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Other | Capitalized A&G | Not assigned | 002/2021 | -0.28
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Other | Fleet OH - Elec | Not assigned | 002/2021 | -0.17
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Other | IT Device OH | Not assigned | 002/2021 | -0.03
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | -0.23
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Other | Payroll Taxes OH | Not assigned | 002/2021 | -0.1
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Other | Permits/Fees | EL DORADO COUNTY | 002/2021 | 152.56
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -1357.5
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | 1357.5
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 297.8
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 100.95
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 59.98
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 229.42
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 193.06
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 194.07
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 519.11
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 520.95
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 523.67
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | Other | Benefits OH | Not assigned | 001/2021 | 119.83
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 20.57
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 109.65
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 67.45
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | Other | IT Device OH | Not assigned | 001/2021 | 11.67
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 91.37
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 40.48
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Contract | Contracts | Not assigned | 001/2021 | -26111.86
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Labor Internal | Analyst Svcs Overtime | Not assigned | 003/2021 | 79.49
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 49.16
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 28.08
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | -78.34
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 29.2
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 16.01
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 255
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 186.1
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 186.26
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 553.41
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 502.18
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 502.6
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 58.36
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 25.88
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 10.01
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 4.68
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 53.4
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 29.27
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 32.85
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 5.69
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 2.65
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 44.49
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 16.82
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 19.71
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 9.21
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Contract | Contracts | CANUS CORPORATION | 001/2021 | 5883.58
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 002/2021 | 1128
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 003/2021 | 305480.37
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 50.23
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 43.05
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 91.94
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -2000
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Contract | Gas Construction Contract | QUANTA ENERGY SERVICES LLC | 003/2021 | 16139.48
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Contract | Gas Construction Contract | Not assigned | 003/2021 | -275375.9
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Labor Internal | Construction | Not assigned | 001/2021 | 1489
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Labor Internal | Construction | Not assigned | 002/2021 | 3201.35
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Labor Internal | Construction | Not assigned | 003/2021 | 660.84
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 595.6
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 34.82
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 513.35
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1096.32
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 474.99
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 45.79
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 29.47
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 129.6
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 48.6
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Labor Internal | Mapping | Not assigned | 001/2021 | 25.33
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Labor Internal | Mapping | Not assigned | 002/2021 | 32.59
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Labor Internal | Mapping | Not assigned | 003/2021 | 144.68
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 304.98
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 677.42
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 298.99
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 232.57
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Benefits OH | Not assigned | 001/2021 | 609.27
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Benefits OH | Not assigned | 002/2021 | 1345.59
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Benefits OH | Not assigned | 003/2021 | 562.45
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Building Service Overhead | Not assigned | 001/2021 | 104.56
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Building Service Overhead | Not assigned | 002/2021 | 230.94
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Building Service Overhead | Not assigned | 003/2021 | 101.67
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Capitalized A&G | Not assigned | 001/2021 | 557.57
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Capitalized A&G | Not assigned | 002/2021 | 1238.46
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Capitalized A&G | Not assigned | 003/2021 | 546.61
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Cash Discount earned | QUANTA ENERGY SERVICES LLC | 003/2021 | -6432.4
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 343
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 732.5
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 317.35
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | IT Device OH | Not assigned | 001/2021 | 59.36
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | IT Device OH | Not assigned | 002/2021 | 131.08
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | IT Device OH | Not assigned | 003/2021 | 57.71
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 464.6
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 992.17
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 429.86
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 27.43
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 17.65
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 205.84
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 454.61
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 200.12
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 | Contract | Contracts | QUANTA ENERGY SERVICES LLC | 001/2021 | 1500
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 | Contract | Contracts | QUANTA ENERGY SERVICES LLC | 004/2021 | -11500
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1.53
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 | Labor Internal | Mapping | Not assigned | 001/2021 | 4.5
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.91
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 | Other | Benefits OH | Not assigned | 001/2021 | 1.81
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.31
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 | Other | Capitalized A&G | Not assigned | 001/2021 | 1.66
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1.02
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 | Other | IT Device OH | Not assigned | 001/2021 | 0.18
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1.38
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.61
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 | Materials | Electl & Electronic Equipment Component | Not assigned | 001/2021 | -29662
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 | Materials | Material Burden | Not assigned | 001/2021 | -4330.65
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 | Other | Benefits OH | Not assigned | 001/2021 | -840.26
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 | Other | Building Service Overhead | Not assigned | 001/2021 | -144.21
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 | Other | IT Device OH | Not assigned | 001/2021 | -81.85
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 | Other | Minor Material OH | Not assigned | 001/2021 | -2416.88
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | -283.88
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1116.75
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1340.1
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 378.58
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 454.29
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 224.91
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 269.9
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Other | Benefits OH | Not assigned | 002/2021 | 449.32
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Other | Benefits OH | Not assigned | 003/2021 | 512
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Other | Building Service Overhead | Not assigned | 002/2021 | 77.12
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Other | Building Service Overhead | Not assigned | 003/2021 | 92.55
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Other | Capitalized A&G | Not assigned | 002/2021 | 411.19
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Other | Capitalized A&G | Not assigned | 003/2021 | 493.42
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 252.94
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 303.53
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Other | IT Device OH | Not assigned | 002/2021 | 43.78
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Other | IT Device OH | Not assigned | 003/2021 | 52.53
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 342.62
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 411.14
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 151.81
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 182.17
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 001/2021 | 896.66
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 001/2021 | 9
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.92
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 2.72
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.55
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 | Other | Benefits OH | Not assigned | 001/2021 | 1.1
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.19
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 1
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.62
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 | Other | IT Device OH | Not assigned | 001/2021 | 0.1
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.84
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.37
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Contract | Contracts | QUANTA ENERGY SERVICES LLC | 003/2021 | 11817.61
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 001/2021 | 896.66
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.91
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 12.02
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 2.69
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 35.45
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.54
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 7.14
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Other | Benefits OH | Not assigned | 001/2021 | 1.08
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Other | Benefits OH | Not assigned | 003/2021 | 13.55
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.19
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 2.45
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.99
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 13.05
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.61
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 8.03
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Other | IT Device OH | Not assigned | 001/2021 | 0.1
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Other | IT Device OH | Not assigned | 003/2021 | 1.39
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.83
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 10.88
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.37
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 4.82
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 001/2021 | 1793.32
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 896.66
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 003/2021 | -896.66
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -1300
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 6360
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | -250
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.5
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 7.38
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | -1.16
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.48
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 21.77
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Labor Internal | Mapping | Not assigned | 003/2021 | -3.44
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.29
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 4.38
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | -0.69
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | Benefits OH | Not assigned | 001/2021 | 0.59
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | Benefits OH | Not assigned | 002/2021 | 8.76
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | Benefits OH | Not assigned | 003/2021 | -1.31
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.1
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 1.51
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | -0.24
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.54
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 8.02
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | -1.27
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.34
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 4.93
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | -0.78
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | IT Device OH | Not assigned | 001/2021 | 0.06
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | IT Device OH | Not assigned | 002/2021 | 0.85
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | IT Device OH | Not assigned | 003/2021 | -0.13
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.45
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 6.68
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | -1.06
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.21
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 2.97
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | -0.47
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 001/2021 | 896.66
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 1393.99
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 003/2021 | -896.66
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 001/2021 | 9
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.92
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1.42
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | -0.91
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 2.72
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 4.18
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | -2.69
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.55
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.84
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | -0.54
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | Benefits OH | Not assigned | 001/2021 | 1.1
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | Benefits OH | Not assigned | 002/2021 | 1.68
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | Benefits OH | Not assigned | 003/2021 | -1.03
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.19
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.29
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | -0.19
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 1
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 1.54
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | -0.99
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | Cellular Phone Use | VERIZON WIRELESS | 001/2021 | 6.96
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.62
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.95
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | -0.61
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | IT Device OH | Not assigned | 001/2021 | 0.1
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | IT Device OH | Not assigned | 002/2021 | 0.16
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | IT Device OH | Not assigned | 003/2021 | -0.1
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.84
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1.28
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | -0.83
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.37
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.57
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | -0.37
35107689 | OCGC CWSP - PINE GROVE 1102 - LR1222 - | Other | Reimbursed Mileage Expense | JARED M BROWN | 003/2021 | 49.84
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Materials | Material Burden | Not assigned | 003/2021 | 2.19
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 15.01
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 0.4
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.07
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Other | Cash Discount earned | MCFARLAND CASCADE HOLDINGS INC | 003/2021 | -30.04
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 0.04
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Other | Minor Material OH | Not assigned | 003/2021 | 1.23
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.15
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 77174.08
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1046.26
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 955.27
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 955.27
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2413.71
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2577.7
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2577.7
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Contract | Environmental Contract | AHTNA GOVERNMENT SERVICES CORP | 001/2021 | 500
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Contract | Environmental Contract | AHTNA GOVERNMENT SERVICES CORP | 002/2021 | 600
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Contract | Environmental Contract | AHTNA GOVERNMENT SERVICES CORP | 003/2021 | 500
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.51
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.61
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.51
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.5
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 1.8
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Labor Internal | Mapping | Not assigned | 003/2021 | 1.5
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.3
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.36
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 0.3
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | Benefits OH | Not assigned | 001/2021 | 0.61
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | Benefits OH | Not assigned | 002/2021 | 0.73
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | Benefits OH | Not assigned | 003/2021 | 0.57
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.1
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.12
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.1
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.55
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.66
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 0.55
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.34
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.41
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.34
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | IT Device OH | Not assigned | 001/2021 | 0.06
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | IT Device OH | Not assigned | 002/2021 | 0.07
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | IT Device OH | Not assigned | 003/2021 | 0.06
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.46
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.55
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.46
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.2
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.24
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.2
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 003/2021 | 4985
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 004/2021 | -4985
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 5.07
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 14.96
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 3.01
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Other | Benefits OH | Not assigned | 003/2021 | 5.71
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 1.03
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 5.51
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 3.39
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Other | IT Device OH | Not assigned | 003/2021 | 0.58
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 4.59
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 2.03
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 001/2021 | 6131.84
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 002/2021 | 23992
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 003/2021 | 0.14
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 23992.14
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -23992.14
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 88.82
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 30.11
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 17.89
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1060.74
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 928.04
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 928.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2440.22
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2504.23
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2504.81
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Other | Benefits OH | Not assigned | 003/2021 | 33.92
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 6.14
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 32.7
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 20.12
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Other | IT Device OH | Not assigned | 003/2021 | 3.49
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 27.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 12.07
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 5146.43
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4351.48
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 4351.48
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 11742.1
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 11742.1
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 11742.1
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 1048.67
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 001/2021 | 350617.54
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Contract | Electric Construction Contract | Not assigned | 001/2021 | -10632.08
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 345.77
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1.07
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Labor Internal | Mapping | Not assigned | 001/2021 | 1019.95
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Labor Internal | Mapping | Not assigned | 003/2021 | 3.15
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 205.42
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 0.63
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Materials | Fabricated Structures | Not assigned | 003/2021 | -3369.64
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Materials | Material Burden | Not assigned | 003/2021 | -33.7
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Other | Benefits OH | Not assigned | 001/2021 | 410.38
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Other | Benefits OH | Not assigned | 003/2021 | -5.01
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 70.44
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Other | Building Service Overhead | Not assigned | 003/2021 | -0.91
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 375.54
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 1.16
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Other | Cash Discount earned | QUANTA ENERGY SERVICES LLC | 001/2021 | -6799.89
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Other | Cash Discount earned | QUANTA ENERGY SERVICES LLC | 002/2021 | 6799.89
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 231.01
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.71
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Other | IT Device OH | Not assigned | 001/2021 | 39.98
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Other | IT Device OH | Not assigned | 003/2021 | -0.52
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Other | Minor Material OH | Not assigned | 003/2021 | -241.98
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 312.92
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.97
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 138.65
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | -1.78
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Contract | Construction Inspection | CANUS CORPORATION | 001/2021 | 1499.62
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 001/2021 | -0.17
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Contract | Electric Construction Contract | Not assigned | 001/2021 | -103107.41
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -103.33
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Labor Internal | Mapping | Not assigned | 001/2021 | -304.82
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | -61.39
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Other | Benefits OH | Not assigned | 001/2021 | -122.65
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Other | Building Service Overhead | Not assigned | 001/2021 | -21.05
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Other | Capitalized A&G | Not assigned | 001/2021 | -112.23
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | -69.04
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Other | IT Device OH | Not assigned | 001/2021 | -11.95
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -93.52
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | -41.44
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | Labor Internal | Account Services | Not assigned | 001/2021 | 295.34
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 76.46
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 59.48
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | Other | Benefits OH | Not assigned | 001/2021 | 83.68
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | Other | Billing Credit - CIAC Non Taxable | Not assigned | 001/2021 | 100000
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 14.36
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 108.74
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | Other | IT Device OH | Not assigned | 001/2021 | 8.15
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 28.27
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | Labor Internal | Account Services | Not assigned | 001/2021 | 328.15
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 84.96
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 66.09
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | Other | Benefits OH | Not assigned | 001/2021 | 92.97
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 15.96
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 120.82
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | Other | IT Device OH | Not assigned | 001/2021 | 9.05
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 31.41
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Contract | Construction Inspection | CANUS CORPORATION | 001/2021 | 2999.24
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 3.05
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 9
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 1.81
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Other | Benefits OH | Not assigned | 001/2021 | 3.62
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.62
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 3.31
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 2.04
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Other | IT Device OH | Not assigned | 001/2021 | 0.35
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 2.76
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 1.22
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Contract | Construction Inspection | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 3467.36
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Contract | Construction Inspection | ENERGY EXPERTS INTERNATIONAL | 002/2021 | 3467.36
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Contract | Construction Inspection | ENERGY EXPERTS INTERNATIONAL | 003/2021 | -3467.36
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Contract | Contracts | MOUNTAIN G ENTERPRISES INC | 001/2021 | 6410.42
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 399.33
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 10.04
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 3.93
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | -3.53
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 11.45
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 001/2021 | 32.4
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 29.63
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 11.6
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Labor Internal | Mapping | Not assigned | 003/2021 | -10.4
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 12.5
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 2.34
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | -2.09
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | Benefits OH | Not assigned | 001/2021 | 23.02
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | Benefits OH | Not assigned | 002/2021 | 4.67
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | Benefits OH | Not assigned | 003/2021 | -3.98
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 3.96
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.8
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | Building Service Overhead | Not assigned | 003/2021 | -0.72
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 22.84
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 4.27
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | Capitalized A&G | Not assigned | 003/2021 | -3.83
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 6.71
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 2.63
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | -2.36
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | IT Device OH | Not assigned | 001/2021 | 2.24
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | IT Device OH | Not assigned | 002/2021 | 0.46
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | IT Device OH | Not assigned | 003/2021 | -0.41
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 9.09
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 3.56
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | -3.19
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 6.86
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 7.79
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 1.58
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | -1.42
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 001/2021 | 9
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.01
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.03
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.01
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 | Other | Benefits OH | Not assigned | 001/2021 | 0.02
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.01
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.01
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.01
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Contract | Construction Inspection | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 198.08
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Contract | Construction Inspection | ENERGY EXPERTS INTERNATIONAL | 002/2021 | 198.08
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Contract | Construction Inspection | ENERGY EXPERTS INTERNATIONAL | 003/2021 | -198.08
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 497.33
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.2
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.71
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | -0.2
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.59
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 2.09
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Labor Internal | Mapping | Not assigned | 003/2021 | -0.59
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.12
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.42
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | -0.12
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | Benefits OH | Not assigned | 001/2021 | 0.24
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | Benefits OH | Not assigned | 002/2021 | 0.84
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | Benefits OH | Not assigned | 003/2021 | -0.22
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.04
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.14
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | Building Service Overhead | Not assigned | 003/2021 | -0.04
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.22
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.77
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | Capitalized A&G | Not assigned | 003/2021 | -0.22
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.13
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.47
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | -0.13
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | IT Device OH | Not assigned | 001/2021 | 0.02
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | IT Device OH | Not assigned | 002/2021 | 0.08
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | IT Device OH | Not assigned | 003/2021 | -0.02
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.18
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.64
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | -0.18
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.08
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.28
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | -0.08
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Contract | Construction Inspection | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 396.16
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Contract | Construction Inspection | ENERGY EXPERTS INTERNATIONAL | 002/2021 | 396.16
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Contract | Construction Inspection | ENERGY EXPERTS INTERNATIONAL | 003/2021 | -396.16
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 001/2021 | 896.66
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 1295.99
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 003/2021 | -896.66
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1.32
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1.72
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | -1.32
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Labor Internal | Mapping | Not assigned | 001/2021 | 3.88
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Labor Internal | Mapping | Not assigned | 002/2021 | 5.08
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Labor Internal | Mapping | Not assigned | 003/2021 | -3.88
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.78
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1.02
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | -0.78
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | Benefits OH | Not assigned | 001/2021 | 1.57
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | Benefits OH | Not assigned | 002/2021 | 2.04
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | Benefits OH | Not assigned | 003/2021 | -1.48
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.27
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.35
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | Building Service Overhead | Not assigned | 003/2021 | -0.27
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 1.43
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 1.87
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | Capitalized A&G | Not assigned | 003/2021 | -1.43
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.88
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1.15
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | -0.88
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | IT Device OH | Not assigned | 001/2021 | 0.15
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | IT Device OH | Not assigned | 002/2021 | 0.2
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | IT Device OH | Not assigned | 003/2021 | -0.15
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1.19
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1.56
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | -1.19
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.53
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.69
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | -0.53
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 297.67
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.3
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.89
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.18
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 | Other | Benefits OH | Not assigned | 002/2021 | 0.36
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.06
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.33
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.2
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 | Other | IT Device OH | Not assigned | 002/2021 | 0.04
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.27
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.13
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 001/2021 | 896.66
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 1295.99
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 003/2021 | -896.66
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.91
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1.32
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | -0.91
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 2.69
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 3.89
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Labor Internal | Mapping | Not assigned | 003/2021 | -2.69
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.54
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.78
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | -0.54
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | Benefits OH | Not assigned | 001/2021 | 1.08
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | Benefits OH | Not assigned | 002/2021 | 1.57
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | Benefits OH | Not assigned | 003/2021 | -1.03
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.19
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.27
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | Building Service Overhead | Not assigned | 003/2021 | -0.19
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.99
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 1.43
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | Capitalized A&G | Not assigned | 003/2021 | -0.99
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.61
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.88
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | -0.61
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | IT Device OH | Not assigned | 001/2021 | 0.1
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | IT Device OH | Not assigned | 002/2021 | 0.15
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | IT Device OH | Not assigned | 003/2021 | -0.1
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.83
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1.19
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | -0.83
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.37
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.53
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | -0.37
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 199.57
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.2
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.6
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.12
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 | Other | Benefits OH | Not assigned | 002/2021 | 0.24
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.04
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.22
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.14
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 | Other | IT Device OH | Not assigned | 002/2021 | 0.02
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.18
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.08
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 497.33
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.51
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 1.49
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.3
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 | Other | Benefits OH | Not assigned | 002/2021 | 0.6
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.1
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.55
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.34
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 | Other | IT Device OH | Not assigned | 002/2021 | 0.06
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.46
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.2
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Contract | Construction Inspection | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 594.24
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Contract | Construction Inspection | ENERGY EXPERTS INTERNATIONAL | 003/2021 | 2072.4
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 399.33
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 001/2021 | 30066.81
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Labor Internal | Construction | Not assigned | 001/2021 | 32.62
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 42.34
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.41
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 2.11
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 92.27
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 1.2
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 6.22
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 25.16
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.24
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1.25
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 003/2021 | 26.15
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Materials | Electrical Specialties | Not assigned | 003/2021 | 1106.54
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Materials | Material Burden | Not assigned | 003/2021 | 191.97
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Materials | Materials Not Otherwise Classified | Not assigned | 003/2021 | 42.24
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Materials | Transformers, Regulators & Capacitors | Not assigned | 003/2021 | 139.92
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Benefits OH | Not assigned | 001/2021 | 50.26
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Benefits OH | Not assigned | 002/2021 | 0.48
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Benefits OH | Not assigned | 003/2021 | 37.74
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 8.63
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.08
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 6.82
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 45.98
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.44
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 2.29
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Cellular Phone Use | VERIZON WIRELESS | 001/2021 | 0.42
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 28.29
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.27
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1.41
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | IT Device OH | Not assigned | 001/2021 | 4.89
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | IT Device OH | Not assigned | 002/2021 | 0.04
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | IT Device OH | Not assigned | 003/2021 | 3.88
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Minor Material OH | Not assigned | 003/2021 | 107.14
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 38.32
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.37
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1.91
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 16.98
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.16
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 13.43
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 497.33
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.51
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 1.49
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.3
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 | Other | Benefits OH | Not assigned | 002/2021 | 0.6
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.1
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.55
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.34
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 | Other | IT Device OH | Not assigned | 002/2021 | 0.06
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.46
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.2
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Contract | Construction Inspection | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 1452.08
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 399.33
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1.48
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.41
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 4.36
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 1.2
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.88
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.24
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Other | Benefits OH | Not assigned | 001/2021 | 1.75
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Other | Benefits OH | Not assigned | 002/2021 | 0.48
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.31
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.08
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 1.61
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.44
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.99
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.27
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Other | IT Device OH | Not assigned | 001/2021 | 0.17
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Other | IT Device OH | Not assigned | 002/2021 | 0.04
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1.34
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.37
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.59
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.16
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 | Contract | Construction Inspection | ENERGY EXPERTS INTERNATIONAL | 003/2021 | 198.08
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 003/2021 | 3000
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.2
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.59
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 0.12
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 | Other | Benefits OH | Not assigned | 003/2021 | 0.22
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.04
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 0.22
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.13
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 | Other | IT Device OH | Not assigned | 003/2021 | 0.02
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.18
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.08
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Contract | Electric Construction Contract | WILSON UTILITY CONSTRUCTION COMPANY | 001/2021 | -37756.61
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Contract | Electric Construction Contract | WILSON UTILITY CONSTRUCTION COMPANY | 003/2021 | 75513.22
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Contract | Electric Construction Contract | Not assigned | 001/2021 | 37756.61
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Contract | Electric Construction Contract | Not assigned | 002/2021 | -37756.61
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 143.11
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -200
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 112.5
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Labor Internal | Administration | Not assigned | 003/2021 | 16.46
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 520.43
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -0.2
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | -12.9
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 253.22
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 5.82
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Labor Internal | Mapping | Not assigned | 001/2021 | -0.6
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Labor Internal | Mapping | Not assigned | 002/2021 | -112.5
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 226.54
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | -0.12
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | -7.67
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 153.75
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3913.12
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 3281.21
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3311.31
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 8931.88
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 8854.06
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 8935.28
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Benefits OH | Not assigned | 001/2021 | -0.24
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | -15.32
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 290.73
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Building Service Overhead | Not assigned | 001/2021 | -0.04
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | -2.63
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 52.55
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Capitalized A&G | Not assigned | 001/2021 | -0.22
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | -14.01
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 281.09
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Cash Discount earned | WILSON UTILITY CONSTRUCTION COMPANY | 003/2021 | -755.13
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Cash Discount earned | WILSON UTILITY CONSTRUCTION COMPANY | 004/2021 | -1309.15
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | -0.14
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | -8.62
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 169.18
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | IT Device OH | Not assigned | 001/2021 | -0.02
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | IT Device OH | Not assigned | 002/2021 | -1.49
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 29.81
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -0.18
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | -11.68
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 229.17
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 3.48
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | -0.08
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | -5.18
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 103.45
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Contract | Electric Construction Contract | WILSON UTILITY CONSTRUCTION COMPANY | 001/2021 | -71985.28
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Contract | Electric Construction Contract | WILSON UTILITY CONSTRUCTION COMPANY | 003/2021 | 127373.94
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Contract | Electric Construction Contract | Not assigned | 001/2021 | 71985.28
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Contract | Electric Construction Contract | Not assigned | 002/2021 | -71985.28
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 22.04
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | -250
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Labor External | Contractor Consultant | Not assigned | 003/2021 | 60.24
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 291.6
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 64.8
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | -47.95
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 205.01
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 114.47
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 22.89
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 32.4
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Labor Internal | Mapping | Not assigned | 002/2021 | -215.89
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Labor Internal | Mapping | Not assigned | 003/2021 | 381.37
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 65.25
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | -28.49
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 134.84
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Benefits OH | Not assigned | 001/2021 | 111.03
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Benefits OH | Not assigned | 002/2021 | -56.91
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Benefits OH | Not assigned | 003/2021 | 252.68
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Building Service Overhead | Not assigned | 001/2021 | 19.07
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Building Service Overhead | Not assigned | 002/2021 | -9.77
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Building Service Overhead | Not assigned | 003/2021 | 47.58
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Capitalized A&G | Not assigned | 001/2021 | 119.3
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Capitalized A&G | Not assigned | 002/2021 | -52.08
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Capitalized A&G | Not assigned | 003/2021 | 247.8
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Cash Discount earned | WILSON UTILITY CONSTRUCTION COMPANY | 003/2021 | -3037.22
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Fleet OH - Elec | Not assigned | 002/2021 | -32.04
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 136.97
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | IT Device OH | Not assigned | 001/2021 | 10.82
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | IT Device OH | Not assigned | 002/2021 | -5.54
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | IT Device OH | Not assigned | 003/2021 | 27
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Land Acquisition Services | INTERWEST CONSULTING GROUP INC | 001/2021 | 417.82
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Land Acquisition Services | INTERWEST CONSULTING GROUP INC | 002/2021 | 24.68
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Land Acquisition Services | INTERWEST CONSULTING GROUP INC | 003/2021 | 75
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Land Acquisition Services | INTERWEST CONSULTING GROUP INC | 004/2021 | -20
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | -43.4
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 185.52
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 68.56
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 13.71
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 37.52
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | -19.23
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 89.9
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | -250
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | -0.25
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | -0.75
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | -0.15
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | -0.3
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | -0.05
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | -0.28
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | Other | Cellular Phone Use | VERIZON WIRELESS | 001/2021 | 46.57
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | Other | Cellular Phone Use | VERIZON WIRELESS | 002/2021 | 53.45
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | -0.17
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | -0.03
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | -0.23
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | -0.1
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Contract | Contracts | CANUS CORPORATION | 001/2021 | 2591.59
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 002/2021 | 7399.96
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 001/2021 | 89476.5
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Contract | Electric Construction Contract | Not assigned | 001/2021 | -89476.5
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | -367.28
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 381.91
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 1455
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 540
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -1000
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Contract | Gas Construction Contract | QUANTA ENERGY SERVICES LLC | 002/2021 | -12000
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 30.81
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -30.81
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor Internal | Administration | Not assigned | 001/2021 | 974.96
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor Internal | Administration | Not assigned | 002/2021 | 139.28
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor Internal | Administration | Not assigned | 003/2021 | 278.56
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 34.82
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 69.64
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 3.03
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | -3.52
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.97
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 356.76
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 49.21
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 123.02
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 8.95
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor Internal | Mapping | Not assigned | 002/2021 | -10.41
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 2.86
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 205.18
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 25.95
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 70.71
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Benefits OH | Not assigned | 001/2021 | 349.67
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 43.54
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 114.4
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 60.02
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 7.46
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 20.68
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 375.1
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 47.44
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 129.26
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Cash Discount earned | QUANTA ENERGY SERVICES LLC | 002/2021 | -1789.53
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 2.03
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | -2.35
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.65
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | IT Device OH | Not assigned | 001/2021 | 34.06
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | IT Device OH | Not assigned | 002/2021 | 4.24
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 11.73
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 2.75
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | -3.19
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.88
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 213.67
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 29.47
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 73.68
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 118.14
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 14.72
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 40.7
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Permits/Fees | EL DORADO COUNTY | 002/2021 | 152.56
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Postage | PITNEY BOWES BANK | 001/2021 | 11.9
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Other | Reimbursed Mileage Expense | DARYL S SATTELBERG | 002/2021 | 52.86
35112433 | CWSP - EL DORADO 2102 - LR19562 - PH 1.3 | Other | Permits/Fees | EL DORADO COUNTY | 002/2021 | 152.56
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Contract | Contracts | CANUS CORPORATION | 001/2021 | 2665.79
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 002/2021 | 8358.12
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -250
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 500
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 250
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Labor Internal | Administration | Not assigned | 001/2021 | 139.28
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 2.46
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 9.01
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.25
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 49.21
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 7.25
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 26.57
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.75
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 29.51
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 5.35
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 0.15
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Benefits OH | Not assigned | 001/2021 | 50.65
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Benefits OH | Not assigned | 002/2021 | 10.69
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Benefits OH | Not assigned | 003/2021 | 0.28
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 8.7
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 1.83
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.05
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 53.95
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 9.78
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 0.28
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1.64
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 6.02
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.17
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | IT Device OH | Not assigned | 001/2021 | 4.93
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | IT Device OH | Not assigned | 002/2021 | 1.04
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | IT Device OH | Not assigned | 003/2021 | 0.03
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 2.22
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 8.15
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.23
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 29.47
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 17.11
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 3.61
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.1
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Other | Permits/Fees | EL DORADO COUNTY | 002/2021 | 152.56
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | -250
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | -0.25
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Labor Internal | Mapping | Not assigned | 002/2021 | -0.75
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | -0.15
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Other | Benefits OH | Not assigned | 002/2021 | -0.3
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Other | Building Service Overhead | Not assigned | 002/2021 | -0.05
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Other | Capitalized A&G | Not assigned | 002/2021 | -0.28
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | -0.17
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Other | IT Device OH | Not assigned | 002/2021 | -0.03
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | -0.23
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | -0.1
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Other | Permits/Fees | EL DORADO COUNTY | 002/2021 | 152.56
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | -250
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | -0.25
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Labor Internal | Mapping | Not assigned | 002/2021 | -0.75
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | -0.15
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Materials | Material Burden | Not assigned | 001/2021 | 1261.2
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 001/2021 | 8638.35
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Other | Benefits OH | Not assigned | 001/2021 | 244.71
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Other | Benefits OH | Not assigned | 002/2021 | -0.3
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Other | Building Service Overhead | Not assigned | 001/2021 | 42
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Other | Building Service Overhead | Not assigned | 002/2021 | -0.05
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Other | Capitalized A&G | Not assigned | 002/2021 | -0.28
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Other | Fleet OH - Elec | Not assigned | 002/2021 | -0.17
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Other | IT Device OH | Not assigned | 001/2021 | 23.84
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Other | IT Device OH | Not assigned | 002/2021 | -0.03
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Other | Minor Material OH | Not assigned | 001/2021 | 703.86
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | -0.23
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 82.67
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Other | Payroll Taxes OH | Not assigned | 002/2021 | -0.1
35112968 | WOODSIDE 1101 RECOND FUSE 1097 ZONE | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3.13
35112968 | WOODSIDE 1101 RECOND FUSE 1097 ZONE | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.64
35112968 | WOODSIDE 1101 RECOND FUSE 1097 ZONE | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.64
35112968 | WOODSIDE 1101 RECOND FUSE 1097 ZONE | Other | AFUDC-Equity | Not assigned | 001/2021 | 7.11
35112968 | WOODSIDE 1101 RECOND FUSE 1097 ZONE | Other | AFUDC-Equity | Not assigned | 002/2021 | 7.11
35112968 | WOODSIDE 1101 RECOND FUSE 1097 ZONE | Other | AFUDC-Equity | Not assigned | 003/2021 | 7.11
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 67765.97
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -21831.38
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 2.12
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 297.8
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 76.44
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 100.95
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 45.41
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 59.98
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 106.06
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 135.55
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 119.08
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 264.72
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 365.77
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 321.33
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | Benefits OH | Not assigned | 001/2021 | 90.73
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 119.83
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 15.57
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 20.57
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 83.02
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 109.65
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 51.07
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 67.45
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | IT Device OH | Not assigned | 001/2021 | 8.84
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | IT Device OH | Not assigned | 002/2021 | 11.67
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 69.17
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 91.37
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 30.65
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 40.48
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 167.38
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 105.06
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 1500
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 1.06
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 76.25
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 75.83
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.5
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.32
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 45.29
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 45.04
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 148.51
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 128.38
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 130
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 340.4
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 346.43
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 350.8
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | Benefits OH | Not assigned | 001/2021 | 90.51
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | Benefits OH | Not assigned | 002/2021 | 90.01
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 15.54
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.44
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 82.81
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 82.36
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 50.94
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 50.66
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | IT Device OH | Not assigned | 001/2021 | 8.82
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | IT Device OH | Not assigned | 002/2021 | 8.78
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 69
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 68.62
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 30.56
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.4
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 54241.37
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -60748.18
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 75.72
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 75.72
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 44.98
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 44.98
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 229.75
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 206.76
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 159.47
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 568.83
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 557.93
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 430.31
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | Benefits OH | Not assigned | 001/2021 | 89.88
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | Benefits OH | Not assigned | 002/2021 | 89.88
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 15.42
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.42
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 82.24
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 82.24
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 50.59
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 50.59
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | IT Device OH | Not assigned | 001/2021 | 8.76
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | IT Device OH | Not assigned | 002/2021 | 8.76
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 68.52
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 68.52
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 30.36
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.36
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 23220.09
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -41094.35
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 003/2021 | -0.01
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 75.72
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 75.72
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 44.98
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 44.98
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 188.8
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 159.42
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 127.6
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 465.24
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 430.19
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 344.33
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | Benefits OH | Not assigned | 001/2021 | 89.88
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | Benefits OH | Not assigned | 002/2021 | 89.88
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 15.42
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.42
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 82.24
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 82.24
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 50.59
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 50.59
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | IT Device OH | Not assigned | 001/2021 | 8.76
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | IT Device OH | Not assigned | 002/2021 | 8.76
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 68.52
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 68.52
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 30.36
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.36
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 109063.93
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -35120.04
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -3620
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 75.72
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 75.72
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 44.98
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 44.98
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 111.28
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 164
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 136.89
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 290.17
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 442.54
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 369.38
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | Benefits OH | Not assigned | 001/2021 | 89.88
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | Benefits OH | Not assigned | 002/2021 | 89.88
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | Building Service Overhead | Not assigned | 001/2021 | 15.42
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.42
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | Capitalized A&G | Not assigned | 001/2021 | 82.24
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | Capitalized A&G | Not assigned | 002/2021 | 82.24
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 50.59
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 50.59
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | IT Device OH | Not assigned | 001/2021 | 8.76
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | IT Device OH | Not assigned | 002/2021 | 8.76
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 68.52
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 68.52
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 30.36
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.36
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 003/2021 | 59570.26
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -724
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | 647.98
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 75.72
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 75.72
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 44.98
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 44.98
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 23.17
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 20.74
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 63.35
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | AFUDC-Equity | Not assigned | 001/2021 | 53.5
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | AFUDC-Equity | Not assigned | 002/2021 | 55.97
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 170.95
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | Benefits OH | Not assigned | 001/2021 | 89.88
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | Benefits OH | Not assigned | 002/2021 | 89.88
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | Building Service Overhead | Not assigned | 001/2021 | 15.42
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.42
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | Capitalized A&G | Not assigned | 001/2021 | 82.24
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | Capitalized A&G | Not assigned | 002/2021 | 82.24
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 50.59
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 50.59
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | IT Device OH | Not assigned | 001/2021 | 8.76
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | IT Device OH | Not assigned | 002/2021 | 8.76
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 68.52
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 68.52
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 30.36
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.36
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | Contract | Contracts | Not assigned | 001/2021 | -11283.95
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 64.24
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | Labor Internal | Mapping | Not assigned | 001/2021 | -33.85
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 38.16
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 148
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 118.16
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 118.16
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 341.59
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 318.85
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 318.85
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | Other | Benefits OH | Not assigned | 001/2021 | 76.26
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 13.08
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 69.78
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 42.92
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | Other | IT Device OH | Not assigned | 001/2021 | 7.43
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 58.13
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 25.75
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | Contract | Contracts | Not assigned | 001/2021 | -3092.2
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 72.57
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | Labor Internal | Mapping | Not assigned | 001/2021 | -9.28
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 43.11
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 166.26
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 143.48
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 143.48
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 391.69
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 387.16
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 387.16
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | Other | Benefits OH | Not assigned | 001/2021 | 86.14
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 14.78
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 78.82
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 48.49
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | Other | IT Device OH | Not assigned | 001/2021 | 8.39
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 65.67
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 29.1
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Contract | Contracts | Not assigned | 001/2021 | -11798.15
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 49698.39
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 003/2021 | -48684.88
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 63.72
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Labor Internal | Mapping | Not assigned | 001/2021 | -35.39
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 37.85
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 262.03
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 265.73
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 227.39
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 635.26
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 717.04
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 613.58
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Other | Benefits OH | Not assigned | 001/2021 | 75.63
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 12.97
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 69.21
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 42.57
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Other | IT Device OH | Not assigned | 001/2021 | 7.37
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 57.66
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 25.55
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Contract | Contracts | CANUS CORPORATION | 002/2021 | 436.91
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Contract | Contracts | MARIOS TREE SERVICE INC | 001/2021 | 169.5
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Contract | Contracts | MARIOS TREE SERVICE INC | 002/2021 | 1149.2
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Contract | Contracts | Not assigned | 002/2021 | -1149.2
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Contract | Electric Construction Contract | ARB INC | 004/2021 | -21690.48
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 2725
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -100
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | -800
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 500
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 97.2
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 3.18
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1340.1
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 446.7
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.45
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 34.82
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 455.44
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 151.06
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.75
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 12.3
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 34.34
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.21
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Labor Internal | Mapping | Not assigned | 002/2021 | -1.09
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Labor Internal | Mapping | Not assigned | 003/2021 | 1.5
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 277.59
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 89.74
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 34.87
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Benefits OH | Not assigned | 001/2021 | 552.47
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Benefits OH | Not assigned | 002/2021 | 179.29
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Benefits OH | Not assigned | 003/2021 | 60.64
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 94.84
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 30.77
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 10.96
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 507.49
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 164.07
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 63.75
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 304.3
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 100.93
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 17.2
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | IT Device OH | Not assigned | 001/2021 | 53.81
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | IT Device OH | Not assigned | 002/2021 | 17.46
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | IT Device OH | Not assigned | 003/2021 | 6.23
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 412.19
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 136.72
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 23.3
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 7.37
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 20.57
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 186.65
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 60.57
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 21.58
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Contract | Contracts | MARIOS TREE SERVICE INC | 001/2021 | 847.5
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Contract | Contracts | Not assigned | 001/2021 | -847.5
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Contract | Electric Construction Contract | ARB INC | 004/2021 | -25934.4
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 500
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1340.1
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 521.15
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 297.8
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 454.29
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 176.67
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 101.46
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Labor Internal | Mapping | Not assigned | 003/2021 | 1.5
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 269.9
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 104.96
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 60.28
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | Benefits OH | Not assigned | 001/2021 | 539.18
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | Benefits OH | Not assigned | 002/2021 | 209.68
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | Benefits OH | Not assigned | 003/2021 | 114.34
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | Building Service Overhead | Not assigned | 001/2021 | 92.55
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | Building Service Overhead | Not assigned | 002/2021 | 35.98
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | Building Service Overhead | Not assigned | 003/2021 | 20.67
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | Capitalized A&G | Not assigned | 001/2021 | 493.42
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | Capitalized A&G | Not assigned | 002/2021 | 191.89
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | Capitalized A&G | Not assigned | 003/2021 | 110.2
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 303.53
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 118.04
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 67.79
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | IT Device OH | Not assigned | 001/2021 | 52.53
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | IT Device OH | Not assigned | 002/2021 | 20.42
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | IT Device OH | Not assigned | 003/2021 | 11.73
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 411.14
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 159.89
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 91.83
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 182.17
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 70.84
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 40.68
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Contract | Contracts | SCENIC LANDSCAPE SERVICES INC | 003/2021 | 2475.03
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 101.74
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 920.12
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -492.59
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -350
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 540
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 1100
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -550
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 86.1
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.04
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.74
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 4.66
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.13
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 2.18
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Labor Internal | Mapping | Not assigned | 003/2021 | 13.74
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.03
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.44
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 2.77
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | Benefits OH | Not assigned | 001/2021 | 0.05
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | Benefits OH | Not assigned | 002/2021 | 0.87
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | Benefits OH | Not assigned | 003/2021 | 5.25
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.15
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.96
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.05
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.8
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 5.06
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | Cash Discount earned | SCENIC LANDSCAPE SERVICES INC | 003/2021 | -49.5
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.03
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.49
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 3.11
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | IT Device OH | Not assigned | 002/2021 | 0.08
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | IT Device OH | Not assigned | 003/2021 | 0.54
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.04
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.67
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 4.22
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.02
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.3
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 1.86
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Other | Postage | PITNEY BOWES BANK | 001/2021 | 9.8
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | Labor Internal | Account Services | Not assigned | 001/2021 | 49.23
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 12.75
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 9.91
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 10.16
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 8.73
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 8.73
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | Other | AFUDC-Equity | Not assigned | 001/2021 | 23.31
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | Other | AFUDC-Equity | Not assigned | 002/2021 | 23.55
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | Other | AFUDC-Equity | Not assigned | 003/2021 | 23.55
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | Other | Benefits OH | Not assigned | 001/2021 | 13.95
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | Other | Building Service Overhead | Not assigned | 001/2021 | 2.39
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | Other | Capitalized A&G | Not assigned | 001/2021 | 18.13
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | Other | IT Device OH | Not assigned | 001/2021 | 1.36
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | Other | Payroll Taxes OH | Not assigned | 001/2021 | 4.71
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | Labor Internal | Account Services | Not assigned | 001/2021 | 32.82
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 8.5
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 6.61
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 10.73
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 9.18
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 9.18
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | Other | AFUDC-Equity | Not assigned | 001/2021 | 24.61
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | Other | AFUDC-Equity | Not assigned | 002/2021 | 24.77
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | Other | AFUDC-Equity | Not assigned | 003/2021 | 24.77
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | Other | Benefits OH | Not assigned | 001/2021 | 9.31
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | Other | Building Service Overhead | Not assigned | 001/2021 | 1.59
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | Other | Capitalized A&G | Not assigned | 001/2021 | 12.08
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | Other | IT Device OH | Not assigned | 001/2021 | 0.91
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | Other | Payroll Taxes OH | Not assigned | 001/2021 | 3.14
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Contract | Contracts | THE ORIGINAL MOWBRAY'S TREE SERVICE | 002/2021 | 10000
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Contract | Contracts | THE ORIGINAL MOWBRAY'S TREE SERVICE | 003/2021 | 13776.1
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Contract | Contracts | THE ORIGINAL MOWBRAY'S TREE SERVICE | 004/2021 | -1887.86
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 22.05
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 300
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -300
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | 650
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | -650
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Contract | Traffic Control Contracts | BAY AREA TRAFFIC SOLUTIONS INC | 003/2021 | 2288
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Account Services | Not assigned | 001/2021 | 82.05
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Account Services | Not assigned | 002/2021 | 131.28
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Account Services | Not assigned | 003/2021 | 98.46
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 712.8
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 437.4
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Administration | Not assigned | 002/2021 | 139.28
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Apprentice | Not assigned | 001/2021 | 2180.48
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Apprentice | Not assigned | 002/2021 | 4224.68
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Apprentice | Not assigned | 003/2021 | 8585.64
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Apprentice DT | Not assigned | 002/2021 | 778.26
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Apprentice DT | Not assigned | 003/2021 | 478.94
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Apprentice OT | Not assigned | 002/2021 | 847.74
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Apprentice OT | Not assigned | 003/2021 | 5577.07
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Construction | Not assigned | 001/2021 | 4701.66
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Construction | Not assigned | 002/2021 | 9607.74
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Construction | Not assigned | 003/2021 | 12878.46
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Construction Doubletime Services | Not assigned | 002/2021 | 1556.52
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Construction Doubletime Services | Not assigned | 003/2021 | 1257.21
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 1784.72
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 9436.38
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 707.28
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1005.08
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 967.87
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Engineering/Mapping | Not assigned | 004/2021 | 670.05
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 69.64
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 21.24
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 33.99
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 25.49
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 2594.48
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 6853.98
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 13413.46
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 276.44
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 203.74
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 002/2021 | 216.18
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Mapping | Not assigned | 001/2021 | 63.89
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Mapping | Not assigned | 002/2021 | 197.32
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Mapping | Not assigned | 003/2021 | 386.15
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 1715.48
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 4214.53
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 7988.78
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Materials | Material Burden | Not assigned | 002/2021 | 2483.87
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Materials | Material Burden | Not assigned | 003/2021 | -3330.46
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 17012.83
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | -22811.35
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1798.07
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1635.73
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1802.51
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | AFUDC-Equity | Not assigned | 001/2021 | 4138.9
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | AFUDC-Equity | Not assigned | 002/2021 | 4413.87
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | AFUDC-Equity | Not assigned | 003/2021 | 4863.91
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Benefits OH | Not assigned | 001/2021 | 3370.71
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Benefits OH | Not assigned | 002/2021 | 8851.61
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Benefits OH | Not assigned | 003/2021 | 14530.08
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Building Service Overhead | Not assigned | 001/2021 | 578.5
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Building Service Overhead | Not assigned | 002/2021 | 1519.19
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Building Service Overhead | Not assigned | 003/2021 | 2626.21
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Capitalized A&G | Not assigned | 001/2021 | 3136.26
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Capitalized A&G | Not assigned | 002/2021 | 7705.02
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Capitalized A&G | Not assigned | 003/2021 | 14605.08
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1733.47
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Fleet OH - Elec | Not assigned | 002/2021 | 4579.42
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Fleet OH - Elec | Not assigned | 003/2021 | 8962.09
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | IT Device OH | Not assigned | 001/2021 | 328.35
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | IT Device OH | Not assigned | 002/2021 | 862.25
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | IT Device OH | Not assigned | 003/2021 | 1490.56
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Minor Material OH | Not assigned | 002/2021 | 1386.21
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Minor Material OH | Not assigned | 003/2021 | -1858.68
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 2348.03
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 6202.96
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 12139.37
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 165.56
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 122.03
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Other Land Fees | JERRY LEX HERRING | 002/2021 | 7500
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Payroll Taxes OH | Not assigned | 001/2021 | 1138.79
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Payroll Taxes OH | Not assigned | 002/2021 | 2990.54
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Other | Payroll Taxes OH | Not assigned | 003/2021 | 5169.77
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | Labor Internal | Account Services | Not assigned | 001/2021 | 32.82
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 8.5
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 6.61
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 9.55
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 8.18
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 8.18
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 21.9
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 22.06
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 22.06
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | Other | Benefits OH | Not assigned | 001/2021 | 9.31
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 1.59
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 12.08
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | Other | IT Device OH | Not assigned | 001/2021 | 0.91
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 3.14
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | Labor Internal | Account Services | Not assigned | 001/2021 | 49.23
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 12.75
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 9.91
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 8.96
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 7.72
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 7.72
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 20.6
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 20.84
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 20.84
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | Other | Benefits OH | Not assigned | 001/2021 | 13.95
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 2.39
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 18.13
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | Other | IT Device OH | Not assigned | 001/2021 | 1.36
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 4.71
35113945 | CWSP - BRUNSWICK 1102 - LR 1010 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 5.14
35113945 | CWSP - BRUNSWICK 1102 - LR 1010 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4.34
35113945 | CWSP - BRUNSWICK 1102 - LR 1010 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 4.34
35113945 | CWSP - BRUNSWICK 1102 - LR 1010 | Other | AFUDC-Equity | Not assigned | 001/2021 | 11.71
35113945 | CWSP - BRUNSWICK 1102 - LR 1010 | Other | AFUDC-Equity | Not assigned | 002/2021 | 11.71
35113945 | CWSP - BRUNSWICK 1102 - LR 1010 | Other | AFUDC-Equity | Not assigned | 003/2021 | 11.71
35113946 | CWSP - WYANDOTTE 1103 – LR 1974 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1.56
35113946 | CWSP - WYANDOTTE 1103 – LR 1974 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.32
35113946 | CWSP - WYANDOTTE 1103 – LR 1974 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.32
35113946 | CWSP - WYANDOTTE 1103 – LR 1974 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3.56
35113946 | CWSP - WYANDOTTE 1103 – LR 1974 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3.56
35113946 | CWSP - WYANDOTTE 1103 – LR 1974 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.56
35113947 | CWSP - LOS GATOS 1107 – LR 60114 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3.52
35113947 | CWSP - LOS GATOS 1107 – LR 60114 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.97
35113947 | CWSP - LOS GATOS 1107 – LR 60114 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.97
35113947 | CWSP - LOS GATOS 1107 – LR 60114 | Other | AFUDC-Equity | Not assigned | 001/2021 | 8.01
35113947 | CWSP - LOS GATOS 1107 – LR 60114 | Other | AFUDC-Equity | Not assigned | 002/2021 | 8.01
35113947 | CWSP - LOS GATOS 1107 – LR 60114 | Other | AFUDC-Equity | Not assigned | 003/2021 | 8.01
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Contract | Contracts | TOWILL INC | 003/2021 | 28000
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 23.75
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Labor Internal | Acquisition - Misc | Not assigned | 004/2021 | 324
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Labor Internal | Administrative Services - OT | Not assigned | 004/2021 | 220.03
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 335.03
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 113.58
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.02
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 28.48
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.07
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 84
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 67.48
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.01
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 16.92
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 238.44
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 204.4
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 226.67
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 549.31
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 551.56
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 611.66
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | Benefits OH | Not assigned | 001/2021 | 134.8
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 0.02
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 32.09
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 23.14
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.8
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 123.36
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.03
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 30.93
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 75.88
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.02
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 19.03
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | IT Device OH | Not assigned | 001/2021 | 13.12
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 3.29
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 102.79
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.02
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 25.77
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 45.54
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 11.42
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Contract | Contracts | TOWILL INC | 003/2021 | 13870
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 003/2021 | 50.02
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Labor Internal | Acquisition - Misc | Not assigned | 004/2021 | 145.8
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Labor Internal | Administrative Services - OT | Not assigned | 004/2021 | 88.01
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 14.16
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 41.76
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 8.41
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 237.3
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 201.98
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 213.04
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 545.03
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 545.03
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 574.88
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Other | Benefits OH | Not assigned | 003/2021 | 15.96
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 2.89
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 15.38
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 9.45
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Other | IT Device OH | Not assigned | 003/2021 | 1.63
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 12.82
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 5.67
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 13544.24
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -5690.45
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 74.45
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 25.24
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 75.72
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 14.99
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 44.98
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 40.79
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 43.25
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 39.31
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 98.05
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 116.7
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 106.07
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | Benefits OH | Not assigned | 001/2021 | 29.96
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 89.88
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 5.14
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.42
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 27.41
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 82.24
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 16.86
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 50.59
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | IT Device OH | Not assigned | 001/2021 | 2.92
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | IT Device OH | Not assigned | 002/2021 | 8.76
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 22.84
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 68.52
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 10.12
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.36
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 92665.76
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -34840.87
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -6154
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | 724
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 75.72
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 75.72
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 44.98
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 44.98
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 137.67
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 170.27
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 143.95
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 345.2
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 459.47
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 388.43
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | Benefits OH | Not assigned | 001/2021 | 89.88
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | Benefits OH | Not assigned | 002/2021 | 89.88
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 15.42
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.42
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 82.24
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 82.24
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 50.59
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 50.59
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | IT Device OH | Not assigned | 001/2021 | 8.76
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | IT Device OH | Not assigned | 002/2021 | 8.76
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 68.52
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 68.52
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 30.36
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.36
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 4286.07
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 24.75
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 80.08
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 75.74
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 12.86
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.07
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 47.57
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 44.99
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 63.62
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 59.38
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 59.88
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 149.3
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 160.22
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 161.58
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | Benefits OH | Not assigned | 001/2021 | 95.06
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | Benefits OH | Not assigned | 002/2021 | 89.9
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 16.31
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.42
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 86.98
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 82.27
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 53.5
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 50.61
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | IT Device OH | Not assigned | 001/2021 | 9.26
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | IT Device OH | Not assigned | 002/2021 | 8.76
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 72.47
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 68.54
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 32.11
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.36
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 75.72
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 75.72
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 44.98
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 44.98
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 156.89
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 133.81
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 134.3
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 358.43
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 361.07
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 362.39
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | Benefits OH | Not assigned | 001/2021 | 89.88
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | Benefits OH | Not assigned | 002/2021 | 89.88
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 15.42
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.42
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 82.24
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 82.24
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 50.59
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 50.59
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | IT Device OH | Not assigned | 001/2021 | 8.76
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | IT Device OH | Not assigned | 002/2021 | 8.76
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 68.52
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 68.52
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 30.36
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.36
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 2.12
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.36
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 76.44
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 75.72
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 45.41
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 44.98
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 120.95
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 103.44
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 103.92
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 276.47
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 279.11
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 280.43
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | Benefits OH | Not assigned | 001/2021 | 90.73
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | Benefits OH | Not assigned | 002/2021 | 89.88
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | Building Service Overhead | Not assigned | 001/2021 | 15.57
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.42
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | Capitalized A&G | Not assigned | 001/2021 | 83.02
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | Capitalized A&G | Not assigned | 002/2021 | 82.24
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 51.07
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 50.59
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | IT Device OH | Not assigned | 001/2021 | 8.84
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | IT Device OH | Not assigned | 002/2021 | 8.76
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 69.17
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 68.53
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 30.65
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.37
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -4344
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | 4344
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 75.72
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 75.72
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 44.98
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 44.98
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 200.81
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 171.57
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 175.15
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | AFUDC-Equity | Not assigned | 001/2021 | 460.31
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | AFUDC-Equity | Not assigned | 002/2021 | 462.95
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 472.62
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | Benefits OH | Not assigned | 001/2021 | 89.88
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | Benefits OH | Not assigned | 002/2021 | 89.88
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | Building Service Overhead | Not assigned | 001/2021 | 15.42
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.42
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | Capitalized A&G | Not assigned | 001/2021 | 82.24
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | Capitalized A&G | Not assigned | 002/2021 | 82.24
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 50.59
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 50.59
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | IT Device OH | Not assigned | 001/2021 | 8.76
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | IT Device OH | Not assigned | 002/2021 | 8.76
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 68.52
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 68.52
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 30.36
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.36
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 140843.33
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -58961.46
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -4887
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | 4887
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 75.72
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 44.98
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 148.09
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 208.35
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 165.77
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Other | AFUDC-Equity | Not assigned | 001/2021 | 386.75
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Other | AFUDC-Equity | Not assigned | 002/2021 | 562.22
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Other | AFUDC-Equity | Not assigned | 003/2021 | 447.31
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Other | Benefits OH | Not assigned | 001/2021 | 89.88
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Other | Building Service Overhead | Not assigned | 001/2021 | 15.42
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Other | Capitalized A&G | Not assigned | 001/2021 | 82.24
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 50.59
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Other | IT Device OH | Not assigned | 001/2021 | 8.76
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 68.52
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 30.36
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Contract | Contracts | MARIOS TREE SERVICE INC | 002/2021 | 1695
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Contract | Contracts | Not assigned | 002/2021 | -1695
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 001/2021 | 29338.24
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 248.73
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 79.69
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 659.03
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -252.37
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Contract | Environmental Contract | ERM-WEST INC | 001/2021 | 110.92
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Contract | Environmental Contract | ERM-WEST INC | 002/2021 | -80
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -800
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 555
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 1260
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -750
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 47.5
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 001/2021 | 45
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 002/2021 | 769.65
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 003/2021 | 368.6
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 842.4
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 110.87
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 947.38
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 59.21
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Electric Estimating | Not assigned | 004/2021 | 32.78
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Electric Estimating Doubletime | Not assigned | 001/2021 | 414.4
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 632.78
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 87.28
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 670.05
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 967.85
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 446.7
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 313.38
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 104.46
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1038.43
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 329.55
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 241.43
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 408.33
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 36.91
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Maintain & Operate Services | Not assigned | 001/2021 | 398.6
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Mapping | Not assigned | 001/2021 | -0.01
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 4.25
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 8.11
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 849.7
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 216.82
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 143.42
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 001/2021 | 7800
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Materials | Material Burden | Not assigned | 001/2021 | 1138.8
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2176.1
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1896.17
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1899.52
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 4993.34
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 5116.65
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 5125.69
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Benefits OH | Not assigned | 001/2021 | 1849.55
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 426.94
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 272.09
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 317.44
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 73.29
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 49.18
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 1553.44
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 396.38
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 262.23
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 693.82
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 220.18
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 161.31
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | IT Device OH | Not assigned | 001/2021 | 180.17
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | IT Device OH | Not assigned | 002/2021 | 41.59
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 27.91
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Minor Material OH | Not assigned | 001/2021 | 635.55
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 939.79
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 298.24
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 218.49
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 244.57
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 22.1
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Other Expenses | MIGUEL ALEMAN JR. | 001/2021 | 65.99
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 624.88
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 144.24
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 96.82
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 001/2021 | 6438.16
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 002/2021 | -5000
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 500
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1079.53
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 372.25
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 365.96
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 25.24
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 126.7
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 1.5
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 217.42
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.99
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 75.27
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 657.92
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 557.31
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 558.64
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1497.03
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1503.85
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1507.44
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | Benefits OH | Not assigned | 001/2021 | 434.36
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | Benefits OH | Not assigned | 002/2021 | 29.96
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | Benefits OH | Not assigned | 003/2021 | 142.78
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 74.55
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.14
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 25.81
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 397.48
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 27.41
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 137.61
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 244.51
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 16.86
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 84.65
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | IT Device OH | Not assigned | 001/2021 | 42.31
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | IT Device OH | Not assigned | 002/2021 | 2.92
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | IT Device OH | Not assigned | 003/2021 | 14.65
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 331.2
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 22.84
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 114.67
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 146.73
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.12
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 50.8
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Contract | Contracts | MARIOS TREE SERVICE INC | 002/2021 | 508.5
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Contract | Contracts | Not assigned | 002/2021 | -508.5
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | -301.13
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 381.91
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | 300
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 115
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 1040
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -1000
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Contract | Security Services | G4S SECURE SOLUTIONS USA INC | 001/2021 | 24238.84
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Contract | Security Services | G4S SECURE SOLUTIONS USA INC | 002/2021 | -5000
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Contract | Traffic Control Contracts | ROAD SAFETY INC | 002/2021 | 5054
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 30.81
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -30.81
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.71
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | -0.14
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1.48
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 2.08
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Labor Internal | Mapping | Not assigned | 002/2021 | -0.42
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Labor Internal | Mapping | Not assigned | 003/2021 | 4.36
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.42
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | -0.08
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 0.88
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Benefits OH | Not assigned | 001/2021 | 0.83
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Benefits OH | Not assigned | 002/2021 | -0.18
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Benefits OH | Not assigned | 003/2021 | 1.66
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.14
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | -0.03
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.31
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.77
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | -0.16
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 1.61
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Cash Discount earned | G4S SECURE SOLUTIONS USA INC | 001/2021 | -96.19
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Cash Discount earned | ROAD SAFETY INC | 002/2021 | -101.08
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.47
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | -0.09
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.99
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | IT Device OH | Not assigned | 001/2021 | 0.08
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | IT Device OH | Not assigned | 002/2021 | -0.02
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | IT Device OH | Not assigned | 003/2021 | 0.17
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.64
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | -0.13
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1.34
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.28
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | -0.05
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.59
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Contract | Contracts | MARIOS TREE SERVICE INC | 001/2021 | 33856.24
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Contract | Contracts | MARIOS TREE SERVICE INC | 002/2021 | 4252.94
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Contract | Contracts | Not assigned | 001/2021 | -33686.74
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | 19404.52
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -250
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 500
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 97.2
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Labor Internal | Analyst Services | Not assigned | 001/2021 | 55.69
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Labor Internal | Analyst Services | Not assigned | 003/2021 | 55.69
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Labor Internal | Construction | Not assigned | 002/2021 | 2180.48
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -0.08
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 750.67
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 19.68
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 54.02
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Labor Internal | Mapping | Not assigned | 001/2021 | -0.24
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Labor Internal | Mapping | Not assigned | 002/2021 | 33.88
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 11.18
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 445.97
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 30.8
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | Benefits OH | Not assigned | 001/2021 | 18.99
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | Benefits OH | Not assigned | 002/2021 | 890.95
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | Benefits OH | Not assigned | 003/2021 | 49.75
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 3.25
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 152.91
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 8.99
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 20.42
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 815.32
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 56.3
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | -0.05
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 501.55
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | IT Device OH | Not assigned | 001/2021 | 1.84
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | IT Device OH | Not assigned | 002/2021 | 86.78
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | IT Device OH | Not assigned | 003/2021 | 5.1
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -0.08
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 679.36
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 11.78
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 32.35
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 6.41
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 301
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 17.71
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Contract | Construction Inspection | CANUS CORPORATION | 002/2021 | 1081.6
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Contract | Construction Inspection | CANUS CORPORATION | 003/2021 | 2651.33
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Contract | Contracts | MARIOS TREE SERVICE INC | 001/2021 | 1879.6
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Contract | Contracts | MARIOS TREE SERVICE INC | 003/2021 | 678
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Contract | Contracts | Not assigned | 001/2021 | -1474.5
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 4722.61
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | -250
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 500
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Contract | Traffic Control Contracts | CITY RISE INC | 002/2021 | 272
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Contract | Traffic Control Contracts | CITY RISE INC | 003/2021 | 406
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Construction | Not assigned | 003/2021 | 10493.56
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Construction Doubletime Services | Not assigned | 003/2021 | 957.86
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 3501.68
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 148.9
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 335.04
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 557.12
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 835.68
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 89.6
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 156.42
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 5237
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 196.83
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 306.7
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 32.4
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 002/2021 | 216.18
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 002/2021 | 54.08
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Maintain & Operate Services | Not assigned | 001/2021 | 114.2
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Maintain & Operate Services | Not assigned | 002/2021 | 114.2
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.22
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Mapping | Not assigned | 002/2021 | 2.49
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Mapping | Not assigned | 003/2021 | 160.23
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 165.44
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 267.76
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 3111.31
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Benefits OH | Not assigned | 001/2021 | 297.27
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Benefits OH | Not assigned | 002/2021 | 483.14
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Benefits OH | Not assigned | 003/2021 | 5902.21
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Building Service Overhead | Not assigned | 001/2021 | 51.01
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Building Service Overhead | Not assigned | 002/2021 | 82.92
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Building Service Overhead | Not assigned | 003/2021 | 1066.76
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Capitalized A&G | Not assigned | 001/2021 | 302.45
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Capitalized A&G | Not assigned | 002/2021 | 489.51
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Capitalized A&G | Not assigned | 003/2021 | 5688.09
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 59.88
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 104.5
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 3499.07
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | IT Device OH | Not assigned | 001/2021 | 28.96
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | IT Device OH | Not assigned | 002/2021 | 47.07
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | IT Device OH | Not assigned | 003/2021 | 605.47
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 81.09
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 141.55
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 4739.57
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 117.89
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 183.68
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 100.41
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 163.22
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 2099.98
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Contract | Contracts | MARIOS TREE SERVICE INC | 001/2021 | 4008.35
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Contract | Contracts | MARIOS TREE SERVICE INC | 002/2021 | 819.19
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Contract | Contracts | MARIOS TREE SERVICE INC | 003/2021 | 1380.09
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Contract | Contracts | Not assigned | 001/2021 | -8959.93
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 595.6
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 196.88
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.83
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1.4
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Labor Internal | Mapping | Not assigned | 001/2021 | -14.85
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Labor Internal | Mapping | Not assigned | 002/2021 | 2.46
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Labor Internal | Mapping | Not assigned | 003/2021 | 4.14
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 116.96
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.5
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 0.83
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 643.75
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 553.39
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 555
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1497.84
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1493.28
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1497.62
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | Benefits OH | Not assigned | 001/2021 | 233.66
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | Benefits OH | Not assigned | 002/2021 | 0.99
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | Benefits OH | Not assigned | 003/2021 | 1.58
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | Building Service Overhead | Not assigned | 001/2021 | 40.09
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.17
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.29
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | Capitalized A&G | Not assigned | 001/2021 | 213.83
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.91
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | Capitalized A&G | Not assigned | 003/2021 | 1.52
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 131.53
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.56
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.94
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | IT Device OH | Not assigned | 001/2021 | 22.75
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | IT Device OH | Not assigned | 002/2021 | 0.1
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | IT Device OH | Not assigned | 003/2021 | 0.16
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 178.17
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.75
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1.27
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 78.94
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.33
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.57
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Contract | Contracts | MARIOS TREE SERVICE INC | 003/2021 | 1606.4
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 001/2021 | 28016.79
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 002/2021 | -28016.79
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | 28016.76
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -1629
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | -181
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Contract | Security Services | G4S SECURE SOLUTIONS USA INC | 001/2021 | -27805.78
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Contract | Security Services | G4S SECURE SOLUTIONS USA INC | 002/2021 | 4142.46
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Contract | Security Services | G4S SECURE SOLUTIONS USA INC | 003/2021 | 64316.98
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Contract | Security Services | G4S SECURE SOLUTIONS USA INC | 004/2021 | -50000
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 446.7
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 151.43
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 75.72
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1.63
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 4.82
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 89.97
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 44.98
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 0.97
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 388.81
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 332.93
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 384.72
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 944.98
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 898.38
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1038.13
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | Benefits OH | Not assigned | 001/2021 | 179.73
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | Benefits OH | Not assigned | 002/2021 | 89.88
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | Benefits OH | Not assigned | 003/2021 | 1.84
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 30.85
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.42
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.33
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 164.47
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 82.24
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 1.77
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | Cash Discount earned | G4S SECURE SOLUTIONS USA INC | 003/2021 | -402.51
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 101.18
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 50.59
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1.09
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | IT Device OH | Not assigned | 001/2021 | 17.5
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | IT Device OH | Not assigned | 002/2021 | 8.76
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | IT Device OH | Not assigned | 003/2021 | 0.19
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 137.05
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 68.52
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1.48
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 60.72
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.36
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.65
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Contract | Contracts | MARIOS TREE SERVICE INC | 001/2021 | 19634.57
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Contract | Contracts | MARIOS TREE SERVICE INC | 002/2021 | 4752
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Contract | Contracts | Not assigned | 001/2021 | -5001.4
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Contract | Contracts | Not assigned | 002/2021 | -24386.57
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Contract | Electric Construction Contract | PARMETER GENERAL ENGINEERS | 003/2021 | 11240.9
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | 1956
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | -1956
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -250
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 750
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Construction | Not assigned | 001/2021 | 20375.16
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Construction | Not assigned | 002/2021 | 23508.3
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Construction | Not assigned | 003/2021 | 27084.4
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Construction Doubletime Services | Not assigned | 003/2021 | 239.47
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 1647.29
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 1293.95
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 3837
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Engineering Services - OT | Not assigned | 003/2021 | 776.09
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 3201.35
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 2307.95
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1153.99
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 8436.52
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 9258.97
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 11343.42
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Indirect Labor - Gas | Not assigned | 001/2021 | 250.69
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 003/2021 | 54.08
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Maintain & Operate Services | Not assigned | 001/2021 | 114.2
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Maintain & Operate Services | Not assigned | 002/2021 | 38.07
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 241.35
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 164.32
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 316.42
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 5151.68
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 5500.76
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 6739.13
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Materials | Electrical Specialties | Not assigned | 002/2021 | 612.62
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Materials | Material Burden | Not assigned | 001/2021 | 151.75
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Materials | Material Burden | Not assigned | 002/2021 | 89.44
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 001/2021 | 1039.39
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1688.78
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1583.95
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1718.34
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3946.99
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 4274.16
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4636.79
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Benefits OH | Not assigned | 001/2021 | 10368.92
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Benefits OH | Not assigned | 002/2021 | 11006.59
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Benefits OH | Not assigned | 003/2021 | 12784.26
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 1779.59
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 1889.01
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 2310.66
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 9418.33
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 10056.5
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 12320.51
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Cash Discount earned | PARMETER GENERAL ENGINEERS | 003/2021 | -224.82
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 5636.79
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 6186.3
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 7579.02
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Fleet OH - Gas | Not assigned | 001/2021 | 214.59
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | IT Device OH | Not assigned | 001/2021 | 1010.04
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | IT Device OH | Not assigned | 002/2021 | 1072.16
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | IT Device OH | Not assigned | 003/2021 | 1311.45
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Meals Expense | AARON HACKER | 002/2021 | 63.55
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Minor Material OH | Not assigned | 001/2021 | 84.69
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Minor Material OH | Not assigned | 002/2021 | 49.92
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 7635.16
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 8379.49
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 10265.98
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Operation Mgmt & Support - Gas | Not assigned | 001/2021 | 384.42
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Other Expenses | DATOLIBAN R COULIBALY | 001/2021 | 30
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Other Expenses | DATOLIBAN R COULIBALY | 002/2021 | 30
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 3503.15
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 3718.62
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 4548.58
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Contract | Construction Inspection | CANUS CORPORATION | 003/2021 | 586.6
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Contract | Contracts | MARIOS TREE SERVICE INC | 001/2021 | 508.5
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Contract | Contracts | MARIOS TREE SERVICE INC | 002/2021 | 1525.5
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Contract | Contracts | Not assigned | 001/2021 | -6847.9
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Contract | Contracts | Not assigned | 002/2021 | -2034
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 869.2
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 79.69
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 659.03
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -252.37
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -100
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 815
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 1260
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -750
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Labor Internal | Construction | Not assigned | 003/2021 | 893.4
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 3052.45
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 2307.95
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1153.99
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1029.52
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 782.83
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 699.43
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Labor Internal | Mapping | Not assigned | 001/2021 | -15.53
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 1.29
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Labor Internal | Mapping | Not assigned | 003/2021 | 15.8
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 611.63
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 465.08
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 415.52
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | Benefits OH | Not assigned | 001/2021 | 1221.9
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | Benefits OH | Not assigned | 002/2021 | 929.12
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | Benefits OH | Not assigned | 003/2021 | 788.26
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 209.71
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 159.45
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 142.47
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 1118.19
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 850.27
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 759.67
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 687.87
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 523.04
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 467.31
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | IT Device OH | Not assigned | 001/2021 | 119.03
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | IT Device OH | Not assigned | 002/2021 | 90.5
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | IT Device OH | Not assigned | 003/2021 | 80.86
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 931.73
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 708.48
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 632.99
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 412.83
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 313.93
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 280.45
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Contract | Contracts | MARIOS TREE SERVICE INC | 001/2021 | 8939.29
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Contract | Contracts | MARIOS TREE SERVICE INC | 003/2021 | 3838.85
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Contract | Contracts | Not assigned | 002/2021 | 14607
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | -250
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 500
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 001/2021 | 1.06
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 372.25
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 135.64
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 90.32
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 4.42
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Labor Internal | Mapping | Not assigned | 001/2021 | 26.82
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Labor Internal | Mapping | Not assigned | 002/2021 | 43.07
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Labor Internal | Mapping | Not assigned | 003/2021 | 13.02
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 80.58
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 53.65
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 2.62
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 466.54
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 403.21
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 417.57
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1037.78
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1088.02
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1126.77
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | Benefits OH | Not assigned | 001/2021 | 160.99
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | Benefits OH | Not assigned | 002/2021 | 107.21
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | Benefits OH | Not assigned | 003/2021 | 4.98
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 27.64
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 18.39
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.89
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 147.33
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 98.1
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 4.79
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 90.62
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 60.35
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 2.95
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | IT Device OH | Not assigned | 001/2021 | 15.68
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | IT Device OH | Not assigned | 002/2021 | 10.44
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | IT Device OH | Not assigned | 003/2021 | 0.51
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 122.77
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 81.73
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 3.99
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 54.38
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 36.21
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 1.77
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Contract | Contracts | MARIOS TREE SERVICE INC | 002/2021 | 13072.31
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 463.32
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 346.71
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Contract | Traffic Control Contracts | ROAD SAFETY INC | 003/2021 | 2162
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 47.5
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 001/2021 | 60
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 002/2021 | 15
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 003/2021 | 149.04
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor Internal | Construction | Not assigned | 003/2021 | 34659.5
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 5398.66
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 1.06
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 148.9
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 670.05
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 670.05
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 51.37
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 240.87
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 13833.35
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 102.34
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.57
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor Internal | Mapping | Not assigned | 002/2021 | 40.45
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor Internal | Mapping | Not assigned | 003/2021 | 360.97
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 30.52
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 143.1
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 8275.36
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Materials | Electrical Specialties | Not assigned | 003/2021 | 2371.01
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Materials | Material Burden | Not assigned | 003/2021 | 530.81
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 1264.69
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1098.22
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 915.69
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1019.79
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2434
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2470.91
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2751.8
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Benefits OH | Not assigned | 001/2021 | 60.97
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Benefits OH | Not assigned | 002/2021 | 285.89
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Benefits OH | Not assigned | 003/2021 | 15814.75
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Building Service Overhead | Not assigned | 001/2021 | 10.47
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Building Service Overhead | Not assigned | 002/2021 | 49.06
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Building Service Overhead | Not assigned | 003/2021 | 2858.4
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Building-utilities | ACES WASTE SERVICES INC | 002/2021 | 1638.02
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Capitalized A&G | Not assigned | 001/2021 | 55.79
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Capitalized A&G | Not assigned | 002/2021 | 261.6
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Capitalized A&G | Not assigned | 003/2021 | 15129.03
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 34.33
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 160.93
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 9242.63
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 87.61
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | IT Device OH | Not assigned | 001/2021 | 5.93
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | IT Device OH | Not assigned | 002/2021 | 27.85
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | IT Device OH | Not assigned | 003/2021 | 1622.33
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Minor Material OH | Not assigned | 003/2021 | 296.24
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 46.49
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 217.98
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 12519.38
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 156.93
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Other Expenses | DATOLIBAN R COULIBALY | 003/2021 | 30
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 20.6
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 96.58
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 5626.85
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Contract | Contracts | MARIOS TREE SERVICE INC | 001/2021 | 6170.64
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Contract | Contracts | MARIOS TREE SERVICE INC | 002/2021 | 8057.4
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Contract | Contracts | Not assigned | 001/2021 | -4672.99
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -250
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 500
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1340.1
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 455.55
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 8.19
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.51
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Labor Internal | Mapping | Not assigned | 001/2021 | 3.74
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Labor Internal | Mapping | Not assigned | 002/2021 | 24.17
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Labor Internal | Mapping | Not assigned | 003/2021 | 1.5
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 270.66
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 4.87
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 0.3
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 218.3
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 188.24
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 194.81
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | AFUDC-Equity | Not assigned | 001/2021 | 480.17
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | AFUDC-Equity | Not assigned | 002/2021 | 507.94
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 525.67
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | Benefits OH | Not assigned | 001/2021 | 540.68
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | Benefits OH | Not assigned | 002/2021 | 9.73
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | Benefits OH | Not assigned | 003/2021 | 0.57
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | Building Service Overhead | Not assigned | 001/2021 | 92.81
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | Building Service Overhead | Not assigned | 002/2021 | 1.66
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.1
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | Capitalized A&G | Not assigned | 001/2021 | 494.8
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | Capitalized A&G | Not assigned | 002/2021 | 8.9
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | Capitalized A&G | Not assigned | 003/2021 | 0.55
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 304.37
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 5.47
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.34
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | IT Device OH | Not assigned | 001/2021 | 52.68
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | IT Device OH | Not assigned | 002/2021 | 0.95
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | IT Device OH | Not assigned | 003/2021 | 0.06
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 412.29
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 7.42
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.46
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 182.68
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 3.29
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.2
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 001/2021 | 28498.26
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 002/2021 | -28498.26
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | 18648.63
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 595.6
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 201.91
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 119.95
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 119.59
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 106.27
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 98.51
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | Other | AFUDC-Equity | Not assigned | 001/2021 | 282.85
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | Other | AFUDC-Equity | Not assigned | 002/2021 | 286.76
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | Other | AFUDC-Equity | Not assigned | 003/2021 | 265.83
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | Other | Benefits OH | Not assigned | 001/2021 | 239.64
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | Other | Building Service Overhead | Not assigned | 001/2021 | 41.12
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | Other | Capitalized A&G | Not assigned | 001/2021 | 219.3
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 134.9
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | Other | IT Device OH | Not assigned | 001/2021 | 23.34
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 182.73
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 80.96
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Contract | Contracts | DAVEY TREE SURGERY CO | 001/2021 | 1028.9
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 168.38
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 226.67
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 46.33
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 312.14
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -196.3
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | 250
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | -250
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Labor Internal | Administration | Not assigned | 001/2021 | 829.73
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Labor Internal | Administration | Not assigned | 002/2021 | 1770.08
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Labor Internal | Construction | Not assigned | 001/2021 | 1771.64
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 437.63
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 55.44
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1228.43
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1377.33
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 893.41
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Labor Internal | Engineering/Mapping | Not assigned | 004/2021 | 223.35
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1161.59
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 466.7
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 322.15
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Labor Internal | Indirect Labor - Gas | Not assigned | 001/2021 | 13.05
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 24.9
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Labor Internal | Mapping | Not assigned | 002/2021 | -0.61
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 1.44
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 697.38
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 277.27
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 191.39
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 718.05
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 626.49
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 634.16
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1648.52
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1690.52
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1711.22
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Benefits OH | Not assigned | 001/2021 | 1556.65
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Benefits OH | Not assigned | 002/2021 | 897.38
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Benefits OH | Not assigned | 003/2021 | 363.05
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 267.19
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 154.02
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 65.61
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 1580.44
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 1158.65
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 349.9
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 776.12
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 311.83
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 215.23
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Fleet OH - Gas | Not assigned | 001/2021 | 11.17
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | IT Device OH | Not assigned | 001/2021 | 151.61
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | IT Device OH | Not assigned | 002/2021 | 87.42
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | IT Device OH | Not assigned | 003/2021 | 37.24
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1051.25
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 422.37
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 291.55
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Operation Mgmt & Support - Gas | Not assigned | 001/2021 | 20.02
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 525.92
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 303.2
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 129.18
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 21.53
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 209.78
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -615
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 675
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 21.53
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -0.6
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.92
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Labor Internal | Mapping | Not assigned | 001/2021 | -1.78
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 2.72
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | -0.36
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.55
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Other | Benefits OH | Not assigned | 001/2021 | -0.72
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Other | Benefits OH | Not assigned | 002/2021 | 1.1
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Other | Building Service Overhead | Not assigned | 001/2021 | -0.12
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.19
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Other | Capitalized A&G | Not assigned | 001/2021 | -0.66
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 1
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | -0.4
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.62
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Other | IT Device OH | Not assigned | 001/2021 | -0.07
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Other | IT Device OH | Not assigned | 002/2021 | 0.11
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -0.55
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.83
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | -0.24
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.37
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 170.59
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 820.12
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | 35
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 240
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 1860
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -700
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Contract | Environmental Contract | SURF TO SNOW ENVIRONMENTAL RESOURCE | 001/2021 | 6830.84
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Contract | Traffic Control Contracts | CITY RISE INC | 001/2021 | 1392
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Labor Internal | Construction | Not assigned | 001/2021 | 1646.3
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 281.85
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 55.44
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 967.86
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 670.05
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 446.71
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 341.36
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 227.61
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 173.21
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Labor Internal | Indirect Labor - Gas | Not assigned | 001/2021 | 697.61
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 39.12
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 1.36
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Labor Internal | Mapping | Not assigned | 003/2021 | 8.79
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 591.14
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 135.22
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 102.9
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1023.8
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 884.74
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 889.72
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2345.9
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2387.39
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2400.84
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Benefits OH | Not assigned | 001/2021 | 1313.39
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Benefits OH | Not assigned | 002/2021 | 270.16
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Benefits OH | Not assigned | 003/2021 | 195.23
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 225.42
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 46.37
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 35.3
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 1080.71
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 247.21
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 188.12
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Cellular Phone Use | VERIZON WIRELESS | 001/2021 | 0.42
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 228.08
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 152.08
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 115.73
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Fleet OH - Gas | Not assigned | 001/2021 | 597.15
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | IT Device OH | Not assigned | 001/2021 | 127.93
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | IT Device OH | Not assigned | 002/2021 | 26.32
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | IT Device OH | Not assigned | 003/2021 | 20.03
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 308.94
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 205.99
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 156.75
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Operation Mgmt & Support - Gas | Not assigned | 001/2021 | 1069.74
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 443.74
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 91.27
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 69.46
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 868.96
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Contract | Contracts | DAVEY TREE SURGERY CO | 002/2021 | 13634.76
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Contract | Contracts | SCENIC LANDSCAPE SERVICES INC | 002/2021 | 800
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 195.35
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 820.12
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | 35
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 735
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 1560
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -700
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Contract | Traffic Control Contracts | CAL-SAFETY INC | 003/2021 | 5340
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Contract | Traffic Control Contracts | STATEWIDE TRAFFIC SAFETY AND SIGNS | 003/2021 | 1957.5
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Account Services | Not assigned | 001/2021 | 131.26
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Account Services | Not assigned | 002/2021 | 164.09
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Account Services | Not assigned | 003/2021 | 65.64
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Construction | Not assigned | 001/2021 | 37142.68
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Construction | Not assigned | 002/2021 | 136.95
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Construction | Not assigned | 003/2021 | 7495.4
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Construction Doubletime Services | Not assigned | 001/2021 | 7902.18
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 125.27
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 18035.43
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1191.2
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1191.2
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1842.65
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 33.98
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 42.49
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 16.99
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 15434.36
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 466.76
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 9360.9
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Indirect Labor - Gas | Not assigned | 001/2021 | 516.04
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Indirect Labor - Gas | Not assigned | 002/2021 | 49.55
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 001/2021 | 72.06
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 002/2021 | 81.12
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Maintain & Operate Services | Not assigned | 001/2021 | 114.21
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Maintain & Operate Services | Not assigned | 002/2021 | 57.1
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Mapping | Not assigned | 001/2021 | 407.82
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Mapping | Not assigned | 002/2021 | 47.45
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Mapping | Not assigned | 003/2021 | 239.78
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 9483.25
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 337.94
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 5574.54
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1081.54
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1064.59
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1155.26
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2518
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2872.7
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3117.36
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Benefits OH | Not assigned | 001/2021 | 19027.72
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Benefits OH | Not assigned | 002/2021 | 664.99
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Benefits OH | Not assigned | 003/2021 | 10567.57
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 3265.66
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 114.13
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 1910.02
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 17337.31
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 617.78
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 10191.37
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Cash Discount earned | SCENIC LANDSCAPE SERVICES INC | 002/2021 | -16
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 10312.34
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 311.87
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 6254.4
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Fleet OH - Gas | Not assigned | 001/2021 | 441.73
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Fleet OH - Gas | Not assigned | 002/2021 | 42.41
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | IT Device OH | Not assigned | 001/2021 | 1853.48
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | IT Device OH | Not assigned | 002/2021 | 64.79
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | IT Device OH | Not assigned | 003/2021 | 1084.05
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 13968.33
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 422.43
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 8471.74
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Operation Mgmt & Support - Gas | Not assigned | 001/2021 | 791.32
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 75.98
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 6428.58
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 224.68
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 3759.89
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Contract | Contracts | DAVEY TREE SURGERY CO | 001/2021 | 8580
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Contract | Contracts | DAVEY TREE SURGERY CO | 002/2021 | 26586
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 226.67
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 134.52
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 704.32
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -196.3
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | 250
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | -250
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | -250
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 288
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Labor Internal | Account Services | Not assigned | 001/2021 | 32.82
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Labor Internal | Construction | Not assigned | 001/2021 | 272.56
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Labor Internal | Construction | Not assigned | 002/2021 | 2044.2
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Labor Internal | Construction Doubletime Services | Not assigned | 001/2021 | 359.2
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 1740.02
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1005.08
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 595.61
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 372.25
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 8.5
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1199.92
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 928.05
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 126.65
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Labor Internal | Maintain & Operate Services | Not assigned | 001/2021 | 114.2
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Labor Internal | Mapping | Not assigned | 001/2021 | 48.52
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Labor Internal | Mapping | Not assigned | 002/2021 | 97.81
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Labor Internal | Mapping | Not assigned | 003/2021 | 1.36
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 719.48
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 551.36
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 75.24
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | Benefits OH | Not assigned | 001/2021 | 1433.45
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | Benefits OH | Not assigned | 002/2021 | 1101.46
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | Benefits OH | Not assigned | 003/2021 | 142.74
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | Building Service Overhead | Not assigned | 001/2021 | 246.01
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | Building Service Overhead | Not assigned | 002/2021 | 189.03
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | Building Service Overhead | Not assigned | 003/2021 | 25.81
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | Capitalized A&G | Not assigned | 001/2021 | 1315.35
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | Capitalized A&G | Not assigned | 002/2021 | 1007.98
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | Capitalized A&G | Not assigned | 003/2021 | 137.56
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 801.71
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 620.08
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 84.62
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | IT Device OH | Not assigned | 001/2021 | 139.64
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | IT Device OH | Not assigned | 002/2021 | 107.29
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | IT Device OH | Not assigned | 003/2021 | 14.65
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1085.95
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 839.9
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 114.63
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 484.3
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 372.14
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 50.78
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 4.24
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1.44
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 25.24
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.85
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.99
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 377.8
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 321.21
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 321.39
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 866.11
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 866.75
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 867.24
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | Benefits OH | Not assigned | 001/2021 | 1.7
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 29.96
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.29
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.14
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 1.56
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 27.41
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.96
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 16.86
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | IT Device OH | Not assigned | 001/2021 | 0.16
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | IT Device OH | Not assigned | 002/2021 | 2.92
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1.3
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 22.84
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.56
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.12
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Other | Reimbursed Mileage Expense | MATTHEW J HERRON | 001/2021 | 58.94
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 25.24
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.99
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 337.76
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 286.14
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 286.32
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 771.52
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 772.13
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 772.62
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | Other | Benefits OH | Not assigned | 002/2021 | 29.96
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.14
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 27.41
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 16.86
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | Other | IT Device OH | Not assigned | 002/2021 | 2.92
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 22.84
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.12
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | Other | Reimbursed Mileage Expense | MATTHEW J HERRON | 001/2021 | 58.94
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 198858.24
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -66080.16
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 1281.3
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 5.3
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 3.1
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 25.24
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 3.84
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 1.84
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.99
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 219.58
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 315.78
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 263.93
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 566.69
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 852.11
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 712.18
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | Benefits OH | Not assigned | 001/2021 | 3.68
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | Benefits OH | Not assigned | 002/2021 | 29.96
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.64
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.14
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 3.36
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 27.41
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 2.07
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 16.86
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | IT Device OH | Not assigned | 001/2021 | 0.35
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | IT Device OH | Not assigned | 002/2021 | 2.92
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 2.81
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 22.84
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 1.25
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.12
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 495.61
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Labor Internal | Construction | Not assigned | 003/2021 | 893.4
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 3.18
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1.59
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 25.24
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 305.59
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.49
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Labor Internal | Mapping | Not assigned | 003/2021 | 8.04
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.94
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.99
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 181.55
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 365.18
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 309.79
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 311.87
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 834.55
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 835.93
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 841.55
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | Benefits OH | Not assigned | 001/2021 | 1.88
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | Benefits OH | Not assigned | 002/2021 | 29.96
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | Benefits OH | Not assigned | 003/2021 | 344.41
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.32
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.14
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 62.26
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 1.72
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 27.41
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 331.91
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1.06
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 16.86
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 204.18
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | IT Device OH | Not assigned | 001/2021 | 0.18
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | IT Device OH | Not assigned | 002/2021 | 2.92
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | IT Device OH | Not assigned | 003/2021 | 35.33
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1.44
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 22.84
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 276.57
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.63
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.12
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 122.55
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Construction Inspection | CANUS CORPORATION | 001/2021 | 12781.81
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Construction Inspection | CANUS CORPORATION | 002/2021 | 1670.06
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Construction Inspection | CANUS CORPORATION | 003/2021 | 58563.44
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Construction Inspection | CANUS CORPORATION | 004/2021 | 7690.42
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Contracts | ARBORWORKS INC | 001/2021 | 8727.88
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Contracts | ARBORWORKS INC | 002/2021 | 2249.88
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Contracts | ARBORWORKS INC | 003/2021 | 26082.5
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Contracts | BESS TESTLAB INC | 001/2021 | 1810.27
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Contracts | CANUS CORPORATION | 002/2021 | 1351.78
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 1498.08
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Contracts | CANUS CORPORATION | 004/2021 | 3370.28
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 001/2021 | -9454.03
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 003/2021 | -452.81
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 001/2021 | 25123.88
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 003/2021 | 411412.4
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 004/2021 | -411412.4
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Electric Construction Contract | Not assigned | 001/2021 | 9646.44
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Electric Construction Contract | Not assigned | 002/2021 | -9646.44
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 251.13
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 197.52
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 348.98
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 1444.2
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | -135.78
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -450
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 4410
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 1980
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -2750
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 47.5
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 002/2021 | 105
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 003/2021 | 50.02
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Administration | Not assigned | 003/2021 | 442.54
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Construction | Not assigned | 003/2021 | 32.62
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 84.38
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 2422.02
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 431.22
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1324.63
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 003/2021 | 206.1
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Field Services | Not assigned | 003/2021 | 303
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Field Services | Not assigned | 004/2021 | 75.75
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Field Services Doubletime | Not assigned | 003/2021 | 3381.59
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Field Services Doubletime | Not assigned | 004/2021 | 162.58
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Field Services Overtime | Not assigned | 003/2021 | 292.54
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Field Services Overtime | Not assigned | 004/2021 | 633.82
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1217.05
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 347.74
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 5088.84
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 002/2021 | 72.06
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 003/2021 | 3761.43
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 004/2021 | 288.24
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 001/2021 | 108.16
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 002/2021 | 174.38
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 003/2021 | 1089.33
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 004/2021 | 162.24
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Maintain & Operate Services | Not assigned | 001/2021 | 913.58
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Maintain & Operate Services | Not assigned | 002/2021 | 342.63
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Maintain & Operate Services | Not assigned | 003/2021 | 2424.13
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Maintain & Operate Services | Not assigned | 004/2021 | 228.39
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 146.35
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 5.49
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 1533.84
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 723.04
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 206.6
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 3023.29
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Switching Operation Svcs. - Overtime | Not assigned | 003/2021 | 392.36
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Labor Internal | Switching Operator Service | Not assigned | 003/2021 | 185.37
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Materials | Material Burden | Not assigned | 002/2021 | 183.23
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Materials | Material Burden | Not assigned | 003/2021 | 145.81
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 002/2021 | 1243.44
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 11.54
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 998.67
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1457.53
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1293.58
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1679.9
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3359.49
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3490.61
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4533.07
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Benefits OH | Not assigned | 001/2021 | 1444.48
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 448.27
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 5843.6
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 247.9
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 76.93
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 1056.19
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 1321.87
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 377.7
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 5690.13
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 813.16
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 232.34
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 3400.07
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | IT Device OH | Not assigned | 001/2021 | 140.71
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | IT Device OH | Not assigned | 002/2021 | 43.67
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 599.49
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Land Acquisition Services | BENDER ROSENTHAL INC | 001/2021 | 23.75
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Minor Material OH | Not assigned | 002/2021 | 102.26
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Minor Material OH | Not assigned | 003/2021 | 81.38
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1101.45
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 314.71
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 4605.47
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 488.02
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 151.48
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 2079.11
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Contract | Contracts | BESS TESTLAB INC | 003/2021 | 737.33
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Contract | Contracts | WINDY TREE INC | 001/2021 | 10914
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 11.1
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 25.24
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.75
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 32.74
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 2.21
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 6.59
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.99
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 0.45
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 002/2021 | 29.68
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Materials | Material Burden | Not assigned | 002/2021 | 4.33
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 134.42
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 123.72
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 124.44
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 312.22
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 333.85
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 335.79
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | Benefits OH | Not assigned | 001/2021 | 13.17
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | Benefits OH | Not assigned | 002/2021 | 30.8
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | Benefits OH | Not assigned | 003/2021 | 0.85
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 2.26
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.28
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.15
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 12.05
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 27.41
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 0.81
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 7.42
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 16.86
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.5
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | IT Device OH | Not assigned | 001/2021 | 1.28
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | IT Device OH | Not assigned | 002/2021 | 3
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | IT Device OH | Not assigned | 003/2021 | 0.08
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | Minor Material OH | Not assigned | 002/2021 | 2.42
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 10.04
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 22.84
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.68
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 4.45
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.4
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.3
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -3200
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 4160
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 2545
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -2500
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 372.25
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -3.25
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 29.47
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 128.78
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Labor Internal | Mapping | Not assigned | 001/2021 | -9.6
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 12.48
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Labor Internal | Mapping | Not assigned | 003/2021 | 7.64
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | -1.93
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 17.5
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 76.51
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 002/2021 | 104.14
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Materials | Electl & Electronic Equipment Component | Not assigned | 002/2021 | 4.24
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Materials | Electrical Specialties | Not assigned | 002/2021 | 809.39
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Materials | Material Burden | Not assigned | 002/2021 | 144.09
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 69.14
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 704.38
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 601.88
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 609.28
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1618.91
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1624.13
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1644.1
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | Benefits OH | Not assigned | 001/2021 | -3.86
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | Benefits OH | Not assigned | 002/2021 | 62.94
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | Benefits OH | Not assigned | 003/2021 | 145.13
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | Building Service Overhead | Not assigned | 001/2021 | -0.66
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 10.81
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 26.23
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | -3.53
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 32.01
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 139.87
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | -2.17
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 19.69
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 86.04
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | IT Device OH | Not assigned | 001/2021 | -0.37
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | IT Device OH | Not assigned | 002/2021 | 6.13
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | IT Device OH | Not assigned | 003/2021 | 14.88
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | Minor Material OH | Not assigned | 002/2021 | 80.41
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -2.95
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 26.67
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 116.55
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | -1.3
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 21.26
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 51.64
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Contract | Contracts | ARBORWORKS INC | 001/2021 | 184.5
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 123.79
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 799.25
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | 35
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 765
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 715
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -650
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 166.25
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Account Services | Not assigned | 002/2021 | 479.04
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Account Services | Not assigned | 003/2021 | 359.28
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Construction | Not assigned | 002/2021 | 25.72
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Construction | Not assigned | 003/2021 | 893.4
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 577.36
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 2531.3
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 670.05
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 4467.01
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 226.33
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 124.02
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 93.02
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 860.5
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 228.18
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1821.7
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 79.96
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 183.15
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Indirect Labor - Gas | Not assigned | 001/2021 | 208.89
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Indirect Labor - Gas | Not assigned | 002/2021 | 9.31
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Manage L&EM | Not assigned | 003/2021 | 518.4
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Mapping | Not assigned | 001/2021 | 7.03
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Mapping | Not assigned | 002/2021 | 3.03
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Mapping | Not assigned | 003/2021 | 13.33
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 627.5
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 282.81
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1259.05
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1183.65
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1017.39
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1049.09
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2712.82
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2745.35
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2830.88
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Benefits OH | Not assigned | 001/2021 | 1293.26
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Benefits OH | Not assigned | 002/2021 | 496.23
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Benefits OH | Not assigned | 003/2021 | 2318.44
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 221.97
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 85.16
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 419.04
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 1147.19
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 517.01
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 2301.77
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 574.93
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 152.45
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1217.15
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Fleet OH - Gas | Not assigned | 001/2021 | 178.81
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Fleet OH - Gas | Not assigned | 002/2021 | 7.97
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | IT Device OH | Not assigned | 001/2021 | 125.97
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | IT Device OH | Not assigned | 002/2021 | 48.34
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | IT Device OH | Not assigned | 003/2021 | 237.83
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 778.76
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 206.5
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1648.66
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 47.89
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 109.69
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Operation Mgmt & Support - Gas | Not assigned | 001/2021 | 320.32
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 14.27
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Other Land Fees | JOEL PLUIM | 003/2021 | 15000
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 436.93
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 167.64
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 824.89
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Contract | Construction Inspection | CANUS CORPORATION | 002/2021 | 200.78
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Contract | Construction Inspection | CANUS CORPORATION | 003/2021 | 6083.06
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Contract | Contracts | ARBORWORKS INC | 003/2021 | -241441.2
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 001/2021 | 89507.45
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 003/2021 | 175550
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 004/2021 | -175550
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | 9110
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | -1462.75
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 330.81
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 799.25
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -1350
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 765
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 715
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -650
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 47.5
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 003/2021 | 50.02
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Analyst Services | Not assigned | 001/2021 | 55.69
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Construction | Not assigned | 003/2021 | 51.43
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 210.95
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 675.04
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | -479.79
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1637.9
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 632.84
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 313.38
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Hours - Straight Time | Not assigned | 001/2021 | 496.56
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 317.6
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 787.56
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | -8.56
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 130.4
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 18.61
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Indirect Labor - IT | Not assigned | 001/2021 | 185.22
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Maintain & Operate Services | Not assigned | 001/2021 | 458.39
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 267.55
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 10.24
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Mapping | Not assigned | 003/2021 | -178.34
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 363.03
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 467.88
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 5.27
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Materials | Communication & Signaling Equipment | Not assigned | 002/2021 | 601.17
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 002/2021 | 1344.65
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 003/2021 | 579.66
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 004/2021 | 6.38
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Materials | Construction Supplies | Not assigned | 002/2021 | 275.1
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Materials | Construction Supplies | Not assigned | 003/2021 | 20.6
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Materials | Electrical Specialties | Not assigned | 002/2021 | 9609.23
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Materials | Fabricated Structures | Not assigned | 002/2021 | 1765.56
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Materials | Material Burden | Not assigned | 002/2021 | 3628.45
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Materials | Material Burden | Not assigned | 003/2021 | 586.03
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Materials | Materials Not Otherwise Classified | Not assigned | 002/2021 | 8.12
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 002/2021 | 11543.26
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 003/2021 | 789.81
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 1907.37
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 2623.82
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 002/2021 | 37.02
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2046.57
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1849.03
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1840.24
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 4705.44
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 4989.45
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4965.73
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Benefits OH | Not assigned | 001/2021 | 670.61
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Benefits OH | Not assigned | 002/2021 | 1638.77
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Benefits OH | Not assigned | 003/2021 | 121.31
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 115.09
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 281.24
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 21.92
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 663.69
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 855.39
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 9.62
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Cash Discount earned | STELLA-JONES CORPORATION | 003/2021 | -229.09
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Cellular Phone Use | VERIZON WIRELESS | 002/2021 | 8.28
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Cellular Phone Use | VERIZON WIRELESS | 003/2021 | 12.66
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 212.21
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 526.21
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | -5.72
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 15.93
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | IT Device OH | Not assigned | 001/2021 | 65.3
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | IT Device OH | Not assigned | 002/2021 | 159.62
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | IT Device OH | Not assigned | 003/2021 | 12.46
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Minor Material OH | Not assigned | 002/2021 | 2184.18
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Minor Material OH | Not assigned | 003/2021 | 327.06
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 287.43
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 712.75
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | -7.75
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 78.09
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 28.53
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Operation Mgmt & Support - IT | Not assigned | 001/2021 | 79.7
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 226.56
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 553.65
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 43.14
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Contract | Construction Inspection | CANUS CORPORATION | 002/2021 | 136.49
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 333.4
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Contract | Contracts | CANUS CORPORATION | 004/2021 | 275.9
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Contract | Electric Construction Contract | OLSEN EXCAVATION & GRADING | 002/2021 | 8000
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 105.06
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 226.67
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 209.78
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 210.22
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -196.3
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -365
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | -250
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 500
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Contract | Gas Construction Contract | ALLISON SIERRA INC | 001/2021 | 5212.85
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Contract | Traffic Control Contracts | ROAD SAFETY INC | 001/2021 | 17448
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Contract | Traffic Control Contracts | ROAD SAFETY INC | 002/2021 | -3248
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Contract | Traffic Control Contracts | ROAD SAFETY INC | 003/2021 | 28676
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 71.25
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 32.4
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Administration | Not assigned | 003/2021 | 442.54
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 264.03
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Construction | Not assigned | 001/2021 | 27963.12
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Construction | Not assigned | 002/2021 | 34070
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Construction | Not assigned | 003/2021 | 34615.12
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Construction | Not assigned | 004/2021 | 2248.62
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 1829.42
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 4907.9
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 10975.57
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Construction Overtime Services | Not assigned | 004/2021 | 356.96
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1340.1
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 818.95
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1079.54
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 121.87
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 208.92
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 10641.3
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 13618.3
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 15961.54
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 182.13
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 268.41
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Indirect Labor - Gas | Not assigned | 001/2021 | 9.31
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Manage L&EM | Not assigned | 002/2021 | 129.6
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Manage L&EM | Not assigned | 003/2021 | 518.4
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 283.35
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 375.09
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 413.98
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 6327.19
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 8194.46
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 9635.77
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Materials | Material Burden | Not assigned | 002/2021 | 1556.2
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 10658.91
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1382.56
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1375.79
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1619.21
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3197.06
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3712.44
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4369.29
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Benefits OH | Not assigned | 001/2021 | 12642.02
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Benefits OH | Not assigned | 002/2021 | 16641.83
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Benefits OH | Not assigned | 003/2021 | 18317.71
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 2169.73
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 2856.18
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 3310.79
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 11567.36
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 14981.1
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 17779.07
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Cash Discount earned | ALLISON SIERRA INC | 002/2021 | -104.26
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Cash Discount earned | OLSEN EXCAVATION & GRADING | 003/2021 | -167.12
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Cash Discount earned | ROAD SAFETY INC | 001/2021 | -149.68
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Cash Discount earned | ROAD SAFETY INC | 002/2021 | -99.64
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Cash Discount earned | ROAD SAFETY INC | 003/2021 | -393.88
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Cash Discount earned | ROAD SAFETY INC | 004/2021 | -103.4
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 7109.89
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 9098.95
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 10664.57
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Fleet OH - Gas | Not assigned | 001/2021 | 7.97
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | IT Device OH | Not assigned | 001/2021 | 1231.47
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | IT Device OH | Not assigned | 002/2021 | 1621.06
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | IT Device OH | Not assigned | 003/2021 | 1879.07
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Minor Material OH | Not assigned | 002/2021 | 868.5
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 9630.53
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 12324.74
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 14445.43
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 109.07
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 160.76
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Operation Mgmt & Support - Gas | Not assigned | 001/2021 | 14.27
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Other Land Fees | JOEL PLUIM | 003/2021 | 15000
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 4271.15
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 5622.49
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 6517.37
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Contract | Contracts | ARBORWORKS INC | 001/2021 | 738
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Contract | Contracts | ARBORWORKS INC | 002/2021 | 6896.65
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Contract | Contracts | ARBORWORKS INC | 003/2021 | 553.5
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 348.98
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | -122.61
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 1166.04
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -112.14
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | 3535
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 5560
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 2780
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -5050
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1489
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 372.25
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 4.7
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 517.31
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 130.76
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 13.86
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 37
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Labor Internal | Mapping | Not assigned | 003/2021 | 13.5
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 2.8
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 307.33
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 77.68
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 891.5
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 781.1
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 798.64
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2062.56
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2107.72
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2155.05
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | Benefits OH | Not assigned | 001/2021 | 5.58
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | Benefits OH | Not assigned | 002/2021 | 613.99
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | Benefits OH | Not assigned | 003/2021 | 147.35
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.96
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 105.36
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 26.64
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 5.1
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 561.88
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 142.03
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | Cash Discount earned | STELLA-JONES CORPORATION | 002/2021 | -458.27
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 3.14
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 345.64
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 87.37
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | IT Device OH | Not assigned | 001/2021 | 0.54
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | IT Device OH | Not assigned | 002/2021 | 59.8
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | IT Device OH | Not assigned | 003/2021 | 15.11
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 4.25
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 468.18
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 118.35
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 1.89
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 207.43
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 52.43
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Contract | Contracts | ARBORWORKS INC | 001/2021 | 1104.95
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 2156.13
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 197.52
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 3.31
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 25.44
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Labor Internal | Mapping | Not assigned | 001/2021 | 9.78
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.59
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 1.97
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 15.11
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 343.17
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 300.97
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 301.28
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 804.63
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 812.13
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 812.97
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | Benefits OH | Not assigned | 001/2021 | 3.94
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | Benefits OH | Not assigned | 002/2021 | 30.2
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.68
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.18
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 3.6
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 27.63
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 2.22
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 16.99
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | IT Device OH | Not assigned | 001/2021 | 0.38
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | IT Device OH | Not assigned | 002/2021 | 2.94
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 3
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 23.02
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 1.32
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.2
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | Other | Reimbursed Mileage Expense | MATTHEW J HERRON | 001/2021 | 129.38
35115147 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE ENGINEERING INC | 001/2021 | 14828.66
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Contract | Electric Construction Contract | SILLER CONSTRUCTION CO | 001/2021 | 20242.23
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Contract | Electric Construction Contract | SILLER CONSTRUCTION CO | 003/2021 | 1709.11
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE ENGINEERING INC | 001/2021 | 14828.66
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Labor Internal | Account Services | Not assigned | 001/2021 | 32.03
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Labor Internal | Construction | Not assigned | 001/2021 | 1414.55
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 8.29
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 504.44
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1.74
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 73.46
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 5.13
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 306.13
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1.03
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Other | Benefits OH | Not assigned | 001/2021 | 607.77
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Other | Benefits OH | Not assigned | 003/2021 | 1.96
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 104.3
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.35
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 559.68
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 1.89
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 337.04
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1.16
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Other | IT Device OH | Not assigned | 001/2021 | 59.2
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Other | IT Device OH | Not assigned | 003/2021 | 0.2
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 456.52
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1.57
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 205.32
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.69
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Other | Postage | PITNEY BOWES BANK | 002/2021 | 3.85
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE ENGINEERING INC | 001/2021 | 14828.66
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 44.09
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -250
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -0.25
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.04
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Labor Internal | Mapping | Not assigned | 001/2021 | -0.75
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.13
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | -0.15
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.03
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Other | Benefits OH | Not assigned | 001/2021 | -0.3
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Other | Benefits OH | Not assigned | 002/2021 | 0.05
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Other | Building Service Overhead | Not assigned | 001/2021 | -0.05
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Other | Capitalized A&G | Not assigned | 001/2021 | -0.28
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.05
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | -0.17
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.03
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Other | IT Device OH | Not assigned | 001/2021 | -0.03
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -0.23
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.04
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | -0.1
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.02
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Contract | Construction Inspection | CANUS CORPORATION | 003/2021 | 1491.97
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 1378.72
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Contract | Contracts | MOUNTAIN F ENTERPRISES INC | 004/2021 | -1150
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 003/2021 | 2281.48
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 004/2021 | -2281.48
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Contract | Electric Construction Contract | SILLER CONSTRUCTION CO | 002/2021 | 51053.41
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Contract | Electric Construction Contract | SILLER CONSTRUCTION CO | 003/2021 | 68056.38
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Contract | Electric Construction Contract | SILLER CONSTRUCTION CO | 004/2021 | -20000
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 68.85
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 250
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Contract | Paving Contracts | A-1 ADVANTAGE ASPHALT INC | 003/2021 | 5316
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Contract | Traffic Control Contracts | ROAD SAFETY INC | 003/2021 | 10883.75
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Contract | Traffic Control Contracts | ROAD SAFETY INC | 004/2021 | -7500
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Administration | Not assigned | 001/2021 | 139.28
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Analyst Services | Not assigned | 001/2021 | 55.69
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Construction | Not assigned | 001/2021 | 33933.72
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Construction | Not assigned | 002/2021 | 32025.8
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Construction | Not assigned | 003/2021 | 54341.65
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Construction Doubletime Services | Not assigned | 003/2021 | 3831.43
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 4283.27
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 4327.84
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 10708.11
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 11390.86
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 69.64
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 13072.16
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 12486.79
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 27502.48
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 68.89
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 24.6
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 343.95
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 480.55
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 856.25
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 7805.44
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 7418.4
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 16353.27
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 001/2021 | 208.42
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 002/2021 | 3983.41
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Materials | Construction Supplies | Not assigned | 001/2021 | 2691.08
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Materials | Electrical Specialties | Not assigned | 001/2021 | 465.02
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Materials | Electrical Specialties | Not assigned | 002/2021 | 1590.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Materials | Material Burden | Not assigned | 001/2021 | 1389.42
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Materials | Material Burden | Not assigned | 002/2021 | 989.26
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Materials | Material Burden | Not assigned | 003/2021 | 391.7
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 001/2021 | 1816.76
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 001/2021 | 4335.32
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 1201.82
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 2682.91
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1946.05
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1901.13
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2287.61
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 4506.74
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 5130.03
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6172.92
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Benefits OH | Not assigned | 001/2021 | 15851.41
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Benefits OH | Not assigned | 002/2021 | 15012.21
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Benefits OH | Not assigned | 003/2021 | 31090.64
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 2720.53
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 2576.51
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 5619.38
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 14269.93
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 13562.35
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 29897.08
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Cash Discount earned | ROAD SAFETY INC | 003/2021 | -33.84
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Cash Discount earned | STELLA-JONES CORPORATION | 002/2021 | -33.83
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 8734.05
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 8342.95
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 18375.56
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | IT Device OH | Not assigned | 001/2021 | 1544.07
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | IT Device OH | Not assigned | 002/2021 | 1462.33
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | IT Device OH | Not assigned | 003/2021 | 3189.38
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Minor Material OH | Not assigned | 001/2021 | 775.42
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Minor Material OH | Not assigned | 002/2021 | 552.09
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Minor Material OH | Not assigned | 003/2021 | 218.6
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 11830.49
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 11300.73
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 24890.17
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 41.25
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 14.74
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Other Land Fees | RICHARD SCHLUTER | 003/2021 | 5250
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 5355.45
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 5071.91
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 11061.95
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLAIR CHURCH & FLYNN CONSULTING | 003/2021 | 40860
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLAIR CHURCH & FLYNN CONSULTING | 004/2021 | -40860
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -250
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 250
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 250
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Labor Internal | Administration | Not assigned | 001/2021 | 139.28
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Labor Internal | Administration | Not assigned | 003/2021 | 69.64
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Labor Internal | Analyst Services | Not assigned | 001/2021 | 55.69
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 2.12
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 148.9
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 69.64
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.47
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.25
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 50.73
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 68.89
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 49.2
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Labor Internal | Mapping | Not assigned | 001/2021 | -0.75
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.75
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.75
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 39.55
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.15
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 58.2
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 830.15
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 710.07
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 747.43
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1914.94
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1916.06
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2016.88
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Benefits OH | Not assigned | 001/2021 | 67.36
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Benefits OH | Not assigned | 002/2021 | 0.3
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Benefits OH | Not assigned | 003/2021 | 102.49
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 11.56
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.05
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 18.53
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 72.29
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.28
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 106.38
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.31
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.17
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 33.9
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | IT Device OH | Not assigned | 001/2021 | 6.55
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | IT Device OH | Not assigned | 002/2021 | 0.03
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | IT Device OH | Not assigned | 003/2021 | 10.52
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.42
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.23
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 45.91
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 41.25
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 29.48
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Other Land Fees | RICHARD SCHLUTER | 003/2021 | 5250
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 22.77
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 36.49
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Contract | Electric Construction Contract | ROAD SAFETY INC | 003/2021 | 2162
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 348.98
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 97.99
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 758.16
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 2500
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 5190
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -4500
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 118.75
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 23.75
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 20.6
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 64.8
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Administration | Not assigned | 003/2021 | 208.92
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Analyst Services | Not assigned | 001/2021 | 55.69
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Construction | Not assigned | 003/2021 | 16017.98
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Construction | Not assigned | 004/2021 | 3407
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 5487.75
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Construction Overtime Services | Not assigned | 004/2021 | 223.1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.46
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 69.64
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.36
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 2.76
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 7389.6
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 19.68
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 121.3
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.05
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 8.15
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Mapping | Not assigned | 003/2021 | 218.02
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 11.43
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1.64
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 4459.32
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 002/2021 | 589.24
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 003/2021 | 57613.38
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 004/2021 | -12119.17
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Materials | Construction Supplies | Not assigned | 002/2021 | 102.14
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Materials | Construction Supplies | Not assigned | 003/2021 | 1215.01
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Materials | Electl & Electronic Equipment Component | Not assigned | 002/2021 | 1.9
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Materials | Electrical Specialties | STELLA-JONES CORPORATION | 003/2021 | 5944.75
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Materials | Electrical Specialties | Not assigned | 002/2021 | 13850.32
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Materials | Electrical Specialties | Not assigned | 003/2021 | 13230.68
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Materials | Fabricated Structures | Not assigned | 002/2021 | 753.15
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Materials | Fabricated Structures | Not assigned | 003/2021 | 19343.38
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Materials | Gas & Water Specialties | Not assigned | 002/2021 | 372.53
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Materials | Material Burden | Not assigned | 002/2021 | 2871.93
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Materials | Material Burden | Not assigned | 003/2021 | 26053.55
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 003/2021 | 68488.25
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 4703.01
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 30632.03
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 846.38
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 743.14
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1010.05
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1946.02
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2005.3
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2725.53
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Benefits OH | Not assigned | 001/2021 | 19.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Benefits OH | Not assigned | 002/2021 | 560.49
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Benefits OH | Not assigned | 003/2021 | 13240.06
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 3.34
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 96.19
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 2393.05
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 20.9
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 3.01
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 8152.52
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Cash Discount earned | STELLA-JONES CORPORATION | 003/2021 | -1385.74
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.24
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1.85
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 4937.29
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | IT Device OH | Not assigned | 001/2021 | 1.89
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | IT Device OH | Not assigned | 002/2021 | 54.59
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | IT Device OH | Not assigned | 003/2021 | 1358.22
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Minor Material OH | Not assigned | 002/2021 | 1652.66
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Minor Material OH | Not assigned | 003/2021 | 15821.25
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.32
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 2.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 6687.69
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 11.78
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 72.66
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Other Land Fees | RICHARD SCHLUTER | 003/2021 | 5250
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 6.6
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 189.35
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 4710.78
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Contract | Contracts | DISCOVERY HYDROVAC LLC | 003/2021 | 1430
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Contract | Contracts | MOUNTAIN F ENTERPRISES INC | 001/2021 | 9200
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Contract | Contracts | MOUNTAIN F ENTERPRISES INC | 003/2021 | -8334.16
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 002/2021 | 1388.18
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 003/2021 | 1620.74
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 004/2021 | -660.74
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 79.69
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 799.24
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -185
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 1200
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 645
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -615
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Contract | Traffic Control Contracts | ROAD SAFETY INC | 003/2021 | 4999
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Contract | Traffic Control Contracts | ROAD SAFETY INC | 004/2021 | -1850
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Administration | Not assigned | 003/2021 | 69.64
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Analyst Services | Not assigned | 001/2021 | 55.69
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Construction | Not assigned | 001/2021 | 17035
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Construction | Not assigned | 002/2021 | 2725.6
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Construction | Not assigned | 003/2021 | 42224.1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Construction | Not assigned | 004/2021 | 6814
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Construction Doubletime Services | Not assigned | 003/2021 | 2574.22
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Construction Doubletime Services | Not assigned | 004/2021 | 239.48
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 3452.99
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 12269.67
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Construction Overtime Services | Not assigned | 004/2021 | 1650.9
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 8636.2
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 11316.4
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 372.26
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 69.64
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 8764.09
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 5952.41
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 19642.55
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 19.68
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 24.6
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Mapping | Not assigned | 001/2021 | 181.54
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Mapping | Not assigned | 002/2021 | 63.73
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Mapping | Not assigned | 003/2021 | 502.35
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 5217.96
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 3536.33
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 11683.67
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1822.45
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1669.83
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1848.39
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 4203.79
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 4505.9
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4987.72
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Benefits OH | Not assigned | 001/2021 | 10420.94
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Benefits OH | Not assigned | 002/2021 | 7064.79
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Benefits OH | Not assigned | 003/2021 | 22160.13
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 1788.53
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 1212.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 4005.26
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 9539.49
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 6465.11
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 21360.11
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 5855.65
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 3977.05
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 13123.98
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | IT Device OH | Not assigned | 001/2021 | 1015.1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | IT Device OH | Not assigned | 002/2021 | 688.19
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | IT Device OH | Not assigned | 003/2021 | 2273.28
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 7931.63
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 5387.03
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 17776.79
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 11.78
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 14.74
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Other Land Fees | RICHARD SCHLUTER | 003/2021 | 5250
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 3520.78
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 2386.87
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 7884.5
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Contract | Contracts | MOUNTAIN F ENTERPRISES INC | 001/2021 | 21850
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Contract | Contracts | MOUNTAIN F ENTERPRISES INC | 002/2021 | 7912
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Contract | Contracts | MOUNTAIN F ENTERPRISES INC | 004/2021 | -7912
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE ENGINEERING INC | 001/2021 | 14828.66
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 173.29
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 799.24
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -185
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | -115
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 1595
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -615
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Account Services | Not assigned | 001/2021 | 262.52
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Account Services | Not assigned | 002/2021 | 65.63
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Account Services | Not assigned | 003/2021 | 131.26
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Construction | Not assigned | 002/2021 | 297.8
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Construction | Not assigned | 003/2021 | 1703.5
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 372.25
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 67.97
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 16.99
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 33.98
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 123.12
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 222.82
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 711.4
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 001/2021 | 87.64
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 002/2021 | 144.12
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Maintain & Operate Services | Not assigned | 001/2021 | 209.37
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Maintain & Operate Services | Not assigned | 002/2021 | 114.2
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 66.17
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 26.72
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 22.76
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 126.02
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 145.6
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 449.08
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | Benefits OH | Not assigned | 001/2021 | 220.5
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 283.03
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 837.04
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 37.83
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 48.59
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 151.3
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 230.38
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 266.17
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 821
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 82.26
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 148.88
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 475.3
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | IT Device OH | Not assigned | 001/2021 | 21.46
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | IT Device OH | Not assigned | 002/2021 | 27.58
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 85.87
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 111.42
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 201.66
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 643.82
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 74.5
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 95.64
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 297.83
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE ENGINEERING INC | 001/2021 | 14828.66
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | 400
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 2495
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 7485
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -5000
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.41
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 2.54
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 7.61
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.2
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 7.49
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 22.46
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.24
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1.51
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 4.52
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | Benefits OH | Not assigned | 001/2021 | 0.48
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | Benefits OH | Not assigned | 002/2021 | 3.01
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | Benefits OH | Not assigned | 003/2021 | 8.58
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.08
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.52
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 1.55
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.44
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 2.76
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 8.27
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.27
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1.7
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 5.09
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | IT Device OH | Not assigned | 001/2021 | 0.04
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | IT Device OH | Not assigned | 002/2021 | 0.29
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | IT Device OH | Not assigned | 003/2021 | 0.88
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.37
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 2.3
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 6.89
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.16
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 1.02
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 3.05
35115157 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE ENGINEERING INC | 001/2021 | 14828.66
35115157 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.4 | Other | Postage | PITNEY BOWES BANK | 002/2021 | 17.85
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 001/2021 | 21186.45
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 002/2021 | 12607.55
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 003/2021 | 7925.45
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 8.48
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 2.87
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 1.71
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 126.5
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 136.66
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 152.82
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 296.88
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 368.75
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 412.38
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | Other | Benefits OH | Not assigned | 001/2021 | 3.4
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.58
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 3.12
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1.92
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | Other | IT Device OH | Not assigned | 001/2021 | 0.34
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 2.6
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 1.16
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Contract | Contracts | MARIOS TREE SERVICE INC | 003/2021 | 18573.17
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Contract | Contracts | Not assigned | 001/2021 | -759.84
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Contract | Contracts | Not assigned | 003/2021 | -18573.17
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 744.5
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 251.62
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Labor Internal | Mapping | Not assigned | 001/2021 | -2.28
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 149.48
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 471.44
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 415.52
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 415.52
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1118.28
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1121.23
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1121.23
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Other | Benefits OH | Not assigned | 001/2021 | 298.65
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 51.26
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 273.28
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 168.11
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Other | IT Device OH | Not assigned | 001/2021 | 29.09
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 227.71
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 100.9
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Contract | Contracts | MARIOS TREE SERVICE INC | 003/2021 | 1318.7
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Contract | Contracts | Not assigned | 003/2021 | -1318.7
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 168.38
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 500
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Labor Internal | Construction | Not assigned | 001/2021 | 65.24
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1637.9
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 577.74
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.51
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.1
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Labor Internal | Mapping | Not assigned | 003/2021 | 1.5
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 343.23
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 0.3
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1472.98
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1252.94
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1253.34
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3369.4
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3380.95
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3382.02
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | Benefits OH | Not assigned | 001/2021 | 685.71
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | Benefits OH | Not assigned | 003/2021 | 0.56
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 117.67
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.1
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 627.5
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 0.55
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 386.01
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.34
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | IT Device OH | Not assigned | 001/2021 | 66.8
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | IT Device OH | Not assigned | 003/2021 | 0.05
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 522.87
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.46
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 231.66
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.21
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Contract | Contracts | MARIOS TREE SERVICE INC | 003/2021 | 169.5
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Contract | Contracts | Not assigned | 001/2021 | -481.1
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1563.45
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 529.52
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.17
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Labor Internal | Mapping | Not assigned | 001/2021 | -1.44
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.51
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 314.59
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 0.1
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 337.25
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 295.98
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 296.11
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 790.07
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 798.68
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 799.02
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | Benefits OH | Not assigned | 001/2021 | 628.47
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | Benefits OH | Not assigned | 003/2021 | 0.2
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 107.85
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.04
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 575.13
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 0.19
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 353.79
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.12
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | IT Device OH | Not assigned | 001/2021 | 61.22
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | IT Device OH | Not assigned | 003/2021 | 0.02
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 479.23
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.16
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 212.32
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.06
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 001/2021 | 10828.63
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -452.5
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | -90.5
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 2943.86
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 4704
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Labor Internal | Analyst Services | Not assigned | 003/2021 | 167.07
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 2.99
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 59.03
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Labor Internal | Mapping | Not assigned | 001/2021 | 8.83
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 1.78
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 33.65
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 163.79
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 155.56
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 159.58
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 381.6
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 419.76
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 430.62
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | Benefits OH | Not assigned | 001/2021 | 3.56
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | Benefits OH | Not assigned | 003/2021 | 54.37
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.61
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | Building Service Overhead | Not assigned | 003/2021 | 9.83
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | Capitalized A&G | Not assigned | 001/2021 | 3.25
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | Capitalized A&G | Not assigned | 003/2021 | 61.52
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 2
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | IT Device OH | Not assigned | 001/2021 | 0.35
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | IT Device OH | Not assigned | 003/2021 | 5.58
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 2.71
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 35.35
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 1.2
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 19.34
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | Other | Reimbursed Mileage Expense | JARED M BROWN | 003/2021 | 49.84
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Contract | Contracts | MARIOS TREE SERVICE INC | 003/2021 | 1203.59
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Contract | Contracts | Not assigned | 003/2021 | -1203.59
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 818.95
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 277.62
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 164.94
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 294.06
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 258.72
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 258.72
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Other | AFUDC-Equity | Not assigned | 001/2021 | 692.99
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Other | AFUDC-Equity | Not assigned | 002/2021 | 698.12
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 698.12
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Other | Benefits OH | Not assigned | 001/2021 | 329.5
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Other | Building Service Overhead | Not assigned | 001/2021 | 56.56
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Other | Capitalized A&G | Not assigned | 001/2021 | 301.54
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 185.49
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Other | IT Device OH | Not assigned | 001/2021 | 32.1
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 251.25
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 111.32
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Contract | Contracts | MARIOS TREE SERVICE INC | 003/2021 | 1025.38
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Contract | Contracts | Not assigned | 003/2021 | -1025.38
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 002/2021 | 4400
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 744.5
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 252.39
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 149.94
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 548.69
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 465.41
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 468.88
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1241.64
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1255.88
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1265.23
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Other | Benefits OH | Not assigned | 001/2021 | 299.57
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 51.42
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 274.12
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 168.63
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Other | IT Device OH | Not assigned | 001/2021 | 29.18
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 228.41
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 101.21
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 110.87
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1340.1
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 148.9
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 454.29
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 25.24
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 88.4
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 1
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 269.9
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.99
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 52.52
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 241.73
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 212.51
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 213.23
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 565.2
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 573.44
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 575.38
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | Benefits OH | Not assigned | 001/2021 | 539.18
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | Benefits OH | Not assigned | 002/2021 | 29.96
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | Benefits OH | Not assigned | 003/2021 | 99.64
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 92.55
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.14
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 18
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 493.42
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 27.41
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 96.02
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 303.53
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 16.86
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 59.07
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | IT Device OH | Not assigned | 001/2021 | 52.53
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | IT Device OH | Not assigned | 002/2021 | 2.92
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | IT Device OH | Not assigned | 003/2021 | 10.22
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 411.14
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 22.84
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 80.01
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 182.17
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.12
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 35.44
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Contract | Construction Inspection | CANUS CORPORATION | 001/2021 | 1432.11
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Contract | Contracts | MARIOS TREE SERVICE INC | 003/2021 | 12916.4
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Contract | Contracts | Not assigned | 001/2021 | 14734.43
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Contract | Contracts | Not assigned | 003/2021 | -12916.4
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 002/2021 | 1646.55
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 004/2021 | -1646.55
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Contract | Electric Construction Contract | WILSON UTILITY CONSTRUCTION COMPANY | 004/2021 | -66680.17
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 250
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 500
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Construction | Not assigned | 001/2021 | 356.92
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Construction | Not assigned | 003/2021 | 25.72
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 110.87
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1489
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 684.26
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 27.16
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 175.99
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Indirect Labor - Gas | Not assigned | 001/2021 | 46.52
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 9.31
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 003/2021 | 144.12
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 001/2021 | 135.2
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Maintain & Operate Services | Not assigned | 001/2021 | 114.2
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Maintain & Operate Services | Not assigned | 003/2021 | 38.07
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 51.71
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 5.69
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Mapping | Not assigned | 003/2021 | 2.73
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 432.41
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 16.13
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 109.73
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Benefits OH | Not assigned | 001/2021 | 872.7
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Benefits OH | Not assigned | 002/2021 | 32.25
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Benefits OH | Not assigned | 003/2021 | 209.88
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 149.76
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.53
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 37.93
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 790.54
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 29.51
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 200.61
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 457.18
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 18.15
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 117.59
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Fleet OH - Gas | Not assigned | 001/2021 | 39.83
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 7.97
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | IT Device OH | Not assigned | 001/2021 | 85
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | IT Device OH | Not assigned | 002/2021 | 3.14
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | IT Device OH | Not assigned | 003/2021 | 21.53
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 619.26
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 24.59
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 159.28
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Operation Mgmt & Support - Gas | Not assigned | 001/2021 | 71.34
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 14.27
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 294.84
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.89
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 74.65
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Contract | Contracts | MARIOS TREE SERVICE INC | 001/2021 | 26487.17
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Contract | Contracts | MARIOS TREE SERVICE INC | 003/2021 | 3117.1
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Contract | Contracts | Not assigned | 001/2021 | -26755.55
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Contract | Contracts | Not assigned | 003/2021 | -3117.1
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -181
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 5194
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 744.5
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 252.12
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Labor Internal | Mapping | Not assigned | 001/2021 | -0.81
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 149.77
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 548.87
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 487.38
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 491.47
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1300.19
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1315.15
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1326.19
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Other | Benefits OH | Not assigned | 001/2021 | 299.25
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 51.37
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 273.82
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 168.45
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Other | IT Device OH | Not assigned | 001/2021 | 29.14
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 228.16
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 101.11
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Labor Internal | Analyst Svcs Overtime | Not assigned | 003/2021 | 79.49
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 118.42
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 967.85
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 328.1
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 40.14
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 28.08
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 194.92
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 39.86
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 108.35
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 97.2
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 97.66
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 255.94
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 262.29
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 263.52
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | Benefits OH | Not assigned | 001/2021 | 389.41
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | Benefits OH | Not assigned | 003/2021 | 71.12
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | Building Service Overhead | Not assigned | 001/2021 | 66.84
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | Building Service Overhead | Not assigned | 003/2021 | 12.85
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | Capitalized A&G | Not assigned | 001/2021 | 356.36
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | Capitalized A&G | Not assigned | 003/2021 | 72.87
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 219.22
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 26.82
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | IT Device OH | Not assigned | 001/2021 | 37.93
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | IT Device OH | Not assigned | 003/2021 | 7.3
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 296.94
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 36.33
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 16.82
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 131.57
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 25.31
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Contract | Contracts | MARIOS TREE SERVICE INC | 003/2021 | 16375.38
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Contract | Contracts | Not assigned | 001/2021 | -25883.19
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 4998
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Labor Internal | Analyst Services | Not assigned | 001/2021 | 55.69
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 818.95
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 251.3
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 16.66
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 19.68
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Labor Internal | Mapping | Not assigned | 001/2021 | -77.65
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Labor Internal | Mapping | Not assigned | 003/2021 | 49.13
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 160.52
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 9.89
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 345.86
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 289.81
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 305.58
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | AFUDC-Equity | Not assigned | 001/2021 | 818.5
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | AFUDC-Equity | Not assigned | 002/2021 | 782.02
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 824.59
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | Benefits OH | Not assigned | 001/2021 | 317.34
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | Benefits OH | Not assigned | 003/2021 | 18.77
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | Building Service Overhead | Not assigned | 001/2021 | 54.46
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | Building Service Overhead | Not assigned | 003/2021 | 3.4
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | Capitalized A&G | Not assigned | 001/2021 | 293.46
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | Capitalized A&G | Not assigned | 003/2021 | 18.09
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 167.9
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 11.13
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | IT Device OH | Not assigned | 001/2021 | 30.9
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | IT Device OH | Not assigned | 003/2021 | 1.93
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 227.43
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 15.07
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 11.78
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 107.22
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 6.68
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Contract | Construction Inspection | CANUS CORPORATION | 002/2021 | 3393.83
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Contract | Construction Inspection | CANUS CORPORATION | 003/2021 | 8545.48
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Contract | Construction Inspection | CANUS CORPORATION | 004/2021 | 3541.11
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Contract | Contracts | ARBORWORKS INC | 003/2021 | 2029.5
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Contract | Contracts | CANUS CORPORATION | 002/2021 | 2915.57
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 555.95
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Contract | Contracts | CANUS CORPORATION | 004/2021 | 2082.76
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Contract | Contracts | WINDY TREE INC | 003/2021 | -19646.16
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Contract | Contracts | WINDY TREE INC | 004/2021 | -48744.08
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 2324.44
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Contract | Electric Construction Contract | WILSON UTILITY CONSTRUCTION COMPANY | 003/2021 | 193978.67
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Contract | Electric Construction Contract | Not assigned | 003/2021 | 11760
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -250
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 250
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 1000
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -500
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Contract | Gas Construction Contract | WILSON UTILITY CONSTRUCTION COMPANY | 003/2021 | 5461.78
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 95
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 002/2021 | 108.75
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Account Services | Not assigned | 001/2021 | 598.8
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Account Services | Not assigned | 002/2021 | 1017.96
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Account Services | Not assigned | 003/2021 | 978.26
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Construction | Not assigned | 001/2021 | 624.78
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Construction | Not assigned | 002/2021 | 97.86
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Construction | Not assigned | 003/2021 | 1095.28
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 84.38
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1340.1
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 2233.5
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1340.11
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 278.56
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Hours - Straight Time | Not assigned | 002/2021 | 155.18
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 155.03
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 263.55
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 253.27
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 934.35
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 870.83
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1708.46
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 98.42
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 434.98
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Indirect Labor - Gas | Not assigned | 001/2021 | 37.21
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 18.61
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Indirect Labor - IT | Not assigned | 002/2021 | 57.88
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 1231.2
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Land Rights - Misc | Not assigned | 004/2021 | 97.2
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 001/2021 | 216.18
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 003/2021 | 720.6
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 001/2021 | 162.24
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 002/2021 | 216.32
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 003/2021 | 324.48
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 004/2021 | 54.08
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Maintain & Operate Services | Not assigned | 001/2021 | 418.75
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Maintain & Operate Services | Not assigned | 003/2021 | 989.75
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Maintain & Operate Services | Not assigned | 004/2021 | 38.07
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Management Services | Not assigned | 003/2021 | 42.3
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 12.6
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 21.17
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 620.92
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 752.51
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 753.64
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1470.34
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Materials | Communication & Signaling Equipment | Not assigned | 001/2021 | 1835.25
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 001/2021 | 30178.26
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Materials | Electl & Electronic Equipment Component | Not assigned | 001/2021 | 1025.82
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Materials | Electrical Specialties | Not assigned | 001/2021 | 2203.51
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Materials | Electrical Specialties | Not assigned | 003/2021 | 2104.23
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Materials | Material Burden | Not assigned | 001/2021 | 4910.16
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Materials | Material Burden | Not assigned | 003/2021 | 307.22
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 001/2021 | 22.1
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Materials | Transformers, Regulators & Capacitors | Not assigned | 001/2021 | 75.88
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1709.64
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1522.61
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1697.67
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3963.64
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 4108.63
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4581.02
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Benefits OH | Not assigned | 001/2021 | 2375.22
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 1374.26
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 2676.72
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 407.65
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 235.87
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 483.81
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 1375.73
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 1377.8
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 2703.65
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Cellular Phone Use | VERIZON WIRELESS | 003/2021 | 0.57
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 624.27
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 581.86
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1141.5
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Fleet OH - Gas | Not assigned | 001/2021 | 31.86
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 15.93
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | IT Device OH | Not assigned | 001/2021 | 231.37
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | IT Device OH | Not assigned | 002/2021 | 133.87
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 274.59
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Minor Material OH | Not assigned | 001/2021 | 2861.85
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Minor Material OH | Not assigned | 003/2021 | 171.45
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 845.59
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 788.13
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1546.17
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 58.94
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 260.52
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Operation Mgmt & Support - Gas | Not assigned | 001/2021 | 57.07
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 28.54
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Operation Mgmt & Support - IT | Not assigned | 002/2021 | 24.9
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 802.47
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 464.28
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 952.4
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Contract | Contracts | ARBORWORKS INC | 001/2021 | 10060.42
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Contract | Contracts | ARBORWORKS INC | 003/2021 | 18358.18
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Labor Internal | Construction | Not assigned | 003/2021 | 65.24
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 2680.2
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 818.95
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 3722.51
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 918.82
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 277.62
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1302.92
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 30.18
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 55.66
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 545.87
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 164.94
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 774.06
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Materials | Chemicals,Cleaners,Compounds & Lab Suppl | Not assigned | 003/2021 | 525.98
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 003/2021 | 7600.62
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 004/2021 | 21199.09
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Materials | Construction Supplies | Not assigned | 003/2021 | 1325.94
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Materials | Electl & Electronic Equipment Component | Not assigned | 003/2021 | 12.59
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Materials | Electrical Specialties | Not assigned | 003/2021 | 34106.63
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Materials | Fabricated Structures | Not assigned | 003/2021 | 14425
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Materials | Material Burden | Not assigned | 003/2021 | 48239.96
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Materials | Materials Not Otherwise Classified | Not assigned | 003/2021 | 497.54
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 285339.91
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 003/2021 | 197.24
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 178.15
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 172.24
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 497.42
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 425.25
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 464.78
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1342.25
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Benefits OH | Not assigned | 001/2021 | 1090.53
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Benefits OH | Not assigned | 002/2021 | 329.5
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Benefits OH | Not assigned | 003/2021 | 10356.15
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 187.16
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 56.56
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 1871.79
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 997.96
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 301.54
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 1415.15
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 613.91
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 185.49
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 870.53
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | IT Device OH | Not assigned | 001/2021 | 106.22
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | IT Device OH | Not assigned | 002/2021 | 32.1
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | IT Device OH | Not assigned | 003/2021 | 1062.39
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Minor Material OH | Not assigned | 003/2021 | 27890.5
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 831.55
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 251.25
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1179.17
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 368.44
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 111.32
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 3684.69
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Other | Reimbursed Mileage Expense | FERNANDO ARMAS | 002/2021 | 105.28
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Contract | Traffic Control Contracts | Not assigned | 001/2021 | -2439.93
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 25.24
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 68.68
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 194.4
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.99
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 39.15
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 134.33
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 115.08
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 114.34
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 311.21
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 310.53
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 308.54
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | Benefits OH | Not assigned | 002/2021 | 29.96
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | Benefits OH | Not assigned | 003/2021 | 63.26
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.14
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 11.43
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 27.41
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 71.58
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 16.86
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | IT Device OH | Not assigned | 002/2021 | 2.92
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | IT Device OH | Not assigned | 003/2021 | 6.49
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 22.84
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 41.14
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.12
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 22.5
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 001/2021 | 3500
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 002/2021 | -1750.24
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Other | Reimbursed Mileage Expense | MATTHEW J HERRON | 001/2021 | 117.88
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Contract | Contracts | ARBORWORKS INC | 001/2021 | 292.13
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Contract | Contracts | ARBORWORKS INC | 002/2021 | 6132.75
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Contract | Contracts | ARBORWORKS INC | 003/2021 | 26934.26
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.3
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 6.24
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 27.39
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.88
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Labor Internal | Mapping | Not assigned | 002/2021 | 18.4
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Labor Internal | Mapping | Not assigned | 003/2021 | 80.8
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.18
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 3.71
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 16.27
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 761.98
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 650.88
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 677.16
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1742.55
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1756.33
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1827.25
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | Benefits OH | Not assigned | 001/2021 | 0.36
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | Benefits OH | Not assigned | 002/2021 | 7.41
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | Benefits OH | Not assigned | 003/2021 | 30.87
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.06
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 1.27
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.58
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.32
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 6.77
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 29.75
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.2
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 4.17
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 18.3
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | IT Device OH | Not assigned | 001/2021 | 0.04
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | IT Device OH | Not assigned | 002/2021 | 0.72
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | IT Device OH | Not assigned | 003/2021 | 3.17
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.27
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 5.65
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 24.79
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.12
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 2.5
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.98
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 88841.42
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -59862.08
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -2005.48
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 229
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 178.08
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.23
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.18
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.69
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.53
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.14
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.11
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 355.5
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 346.35
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 299.35
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 876.42
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 934.61
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 807.78
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | Benefits OH | Not assigned | 001/2021 | 0.28
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | Benefits OH | Not assigned | 002/2021 | 0.22
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.04
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.04
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.25
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.2
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.16
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.12
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | IT Device OH | Not assigned | 001/2021 | 0.02
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | IT Device OH | Not assigned | 002/2021 | 0.02
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.21
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.16
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.09
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.07
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 001/2021 | -6839.06
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -9306.73
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -250
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 500
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 500
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 003/2021 | 281.11
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 744.5
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 893.4
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 372.25
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 245.18
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 293.92
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 126.98
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Labor Internal | Mapping | Not assigned | 001/2021 | -21.27
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Labor Internal | Mapping | Not assigned | 002/2021 | -26.42
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Labor Internal | Mapping | Not assigned | 003/2021 | 2.34
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 145.66
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 174.61
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 75.44
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | Benefits OH | Not assigned | 001/2021 | 291.01
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | Benefits OH | Not assigned | 002/2021 | 348.85
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | Benefits OH | Not assigned | 003/2021 | 143.1
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | Building Service Overhead | Not assigned | 001/2021 | 49.96
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | Building Service Overhead | Not assigned | 002/2021 | 59.87
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | Building Service Overhead | Not assigned | 003/2021 | 25.87
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | Capitalized A&G | Not assigned | 001/2021 | 266.28
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | Capitalized A&G | Not assigned | 002/2021 | 319.22
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | Capitalized A&G | Not assigned | 003/2021 | 137.92
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 163.81
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 196.38
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 84.84
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | IT Device OH | Not assigned | 001/2021 | 28.34
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | IT Device OH | Not assigned | 002/2021 | 33.98
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | IT Device OH | Not assigned | 003/2021 | 14.68
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 221.88
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 265.98
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 114.93
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 98.32
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 117.85
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 50.93
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Other | Reimbursed Mileage Expense | MATTHEW J HERRON | 001/2021 | 119.6
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Construction Inspection | CANUS CORPORATION | 001/2021 | 10079.12
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Construction Inspection | CANUS CORPORATION | 002/2021 | 1540.23
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Contracts | ARBORWORKS INC | 001/2021 | 70458.28
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Contracts | ARBORWORKS INC | 002/2021 | 1525
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Contracts | ARBORWORKS INC | 003/2021 | 20399.62
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Contracts | CANUS CORPORATION | 001/2021 | 2943.99
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Contracts | CANUS CORPORATION | 002/2021 | 394.76
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 209.83
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Contracts | CANUS CORPORATION | 004/2021 | 275.9
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Contracts | Not assigned | 003/2021 | 10500
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Electric Construction Contract | ALVAH CONTRACTORS INC | 001/2021 | 27571.6
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Electric Construction Contract | ALVAH CONTRACTORS INC | 003/2021 | 53050
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 70334.66
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 003/2021 | -68566.5
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Environmental Contract | AHTNA GOVERNMENT SERVICES CORP | 001/2021 | 9150.3
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Environmental Contract | AHTNA GOVERNMENT SERVICES CORP | 002/2021 | 2519.3
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Environmental Contract | AHTNA GOVERNMENT SERVICES CORP | 003/2021 | 2766.6
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 79.69
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 799.25
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | 1450
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 9520
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 8455
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -8300
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Contract | Helicopter Contract | Not assigned | 001/2021 | 2232
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor Internal | Construction | Not assigned | 001/2021 | 893.4
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor Internal | Construction | Not assigned | 002/2021 | 967.85
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor Internal | Construction | Not assigned | 003/2021 | 967.85
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor Internal | Construction | Not assigned | 004/2021 | 260.58
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.38
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.37
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 781.78
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 348.2
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 505.43
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 422.66
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 693.98
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 123.02
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 374.17
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 55.57
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 297.5
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 370.41
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 251.1
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 412.3
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Materials | Material Burden | Not assigned | 001/2021 | 69.51
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 001/2021 | 476.11
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2804.44
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2565.76
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2604.87
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6486.87
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6923.47
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 7029.01
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Benefits OH | Not assigned | 001/2021 | 732.71
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 501.66
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 782.15
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 125.76
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 86.11
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 141.37
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 677.18
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 459.08
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 753.75
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 337.69
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 282.39
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 463.67
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | IT Device OH | Not assigned | 001/2021 | 71.36
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | IT Device OH | Not assigned | 002/2021 | 48.87
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 80.24
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Minor Material OH | Not assigned | 001/2021 | 38.79
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 457.43
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 382.52
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 628.06
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 73.68
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 247.55
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 169.48
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 278.26
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Contract | Contracts | ARBORWORKS INC | 001/2021 | 8347.62
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Contract | Contracts | ARBORWORKS INC | 002/2021 | 25585.11
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Contract | Contracts | ARBORWORKS INC | 003/2021 | 13618.17
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Contract | Contracts | BESS TESTLAB INC | 003/2021 | 363.14
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 3500.47
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Contract | Contracts | CANUS CORPORATION | 004/2021 | 1893.32
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 119706.75
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 003/2021 | -118946.31
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 78.27
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Contract | Environmental Contract | AHTNA GOVERNMENT SERVICES CORP | 001/2021 | 2418.91
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 370.51
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 145.31
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 799.25
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -1800
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 30
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 850
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -600
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Contract | Traffic Control Contracts | ROAD SAFETY INC | 003/2021 | 32806
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 213.75
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 21.53
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Account Services | Not assigned | 002/2021 | 179.64
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Account Services | Not assigned | 003/2021 | 239.52
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Administration | Not assigned | 001/2021 | 885.04
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Administration | Not assigned | 002/2021 | 1438.19
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Administration | Not assigned | 003/2021 | 497.86
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Apprentice | Not assigned | 002/2021 | 2813.8
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Apprentice OT | Not assigned | 002/2021 | 1373.82
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Construction | Not assigned | 002/2021 | 25826
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Construction | Not assigned | 003/2021 | 64211.07
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Construction | Not assigned | 004/2021 | 4088.4
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Construction Doubletime Services | Not assigned | 003/2021 | 957.88
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Construction Doubletime Services | Not assigned | 004/2021 | 239.46
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 8263.14
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 34406.53
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Construction Overtime Services | Not assigned | 004/2021 | 803.12
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1414.55
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 446.71
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 52.23
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 313.38
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 46.51
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 62.01
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 9.5
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 13598.35
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 34501.43
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 18.45
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 293.87
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Maintain & Operate Services | Not assigned | 003/2021 | 797.2
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Manage L&EM | Not assigned | 003/2021 | 518.4
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Mapping | Not assigned | 001/2021 | 28.01
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Mapping | Not assigned | 002/2021 | 421.84
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Mapping | Not assigned | 003/2021 | 954.69
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 5.64
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 8125.49
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 20713.07
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1234.97
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1286.24
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1612.41
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2868.89
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3470.8
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4350.95
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Benefits OH | Not assigned | 001/2021 | 183
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Benefits OH | Not assigned | 002/2021 | 16487.42
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Benefits OH | Not assigned | 003/2021 | 39310.53
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 31.41
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 2829.68
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 7105.07
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 336.18
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 15384.58
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 38050.97
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Cash Discount earned | ROAD SAFETY INC | 003/2021 | -398.56
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Cash Discount earned | ROAD SAFETY INC | 004/2021 | -124.08
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 6.34
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 9085.64
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 23051.82
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | IT Device OH | Not assigned | 001/2021 | 17.83
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | IT Device OH | Not assigned | 002/2021 | 1606.04
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | IT Device OH | Not assigned | 003/2021 | 4032.61
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 8.59
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 12306.71
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 31224.29
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 11.05
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 176
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Other Land Fees | JOEL PLUIM | 003/2021 | 15000
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 61.83
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 5570.31
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 13986.57
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Contract | Contracts | ARBORWORKS INC | 001/2021 | 358.76
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Contract | Contracts | ARBORWORKS INC | 002/2021 | 369
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Contract | Contracts | ARBORWORKS INC | 003/2021 | 2157.64
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1935.7
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 372.25
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 174.1
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.37
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 656.58
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 128.38
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 61.51
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.08
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 1.11
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 6.47
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 35.28
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 390.07
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 76.27
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1031.2
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 881.72
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 889.33
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2363.98
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2379.24
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2399.79
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | Benefits OH | Not assigned | 001/2021 | 60.1
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 779.27
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 144.68
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 10.33
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 133.75
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 26.16
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 64.5
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 713.13
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 139.44
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.24
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 438.69
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 85.78
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | IT Device OH | Not assigned | 001/2021 | 5.86
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | IT Device OH | Not assigned | 002/2021 | 75.9
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 14.84
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.33
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 594.21
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 116.19
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 36.84
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 20.32
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 263.27
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 51.47
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Contract | Contracts | ARBORWORKS INC | 001/2021 | 184.5
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 2010.15
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.19
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 681.44
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.55
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.11
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 404.84
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 97.57
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 89.74
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 94.29
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 229.48
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 242.15
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 254.45
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | Benefits OH | Not assigned | 001/2021 | 0.22
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | Benefits OH | Not assigned | 002/2021 | 808.79
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.04
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 138.81
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.2
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 740.14
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.12
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 455.3
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | IT Device OH | Not assigned | 001/2021 | 0.02
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | IT Device OH | Not assigned | 002/2021 | 78.79
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.17
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 616.71
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.07
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 273.26
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 280416.07
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -107498.82
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 3659.31
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Contract | Environmental Contract | FAR WESTERN ANTHROPOLOGICAL | 002/2021 | 137.66
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | -103.36
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 297.8
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -31.32
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 101.09
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 10.98
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.41
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | -18.61
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 60.06
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 296.89
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 426.09
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 342.64
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 772.9
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1149.77
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 924.58
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | Benefits OH | Not assigned | 001/2021 | -37.18
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | Benefits OH | Not assigned | 002/2021 | 120
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | Building Service Overhead | Not assigned | 001/2021 | -6.38
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 20.59
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | -34.02
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 109.8
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | -20.92
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 67.54
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | IT Device OH | Not assigned | 001/2021 | -3.62
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | IT Device OH | Not assigned | 002/2021 | 11.69
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -28.34
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 91.5
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | -12.58
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 40.54
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | Other | Permits/Fees | CHRISTINE V AGUILAR | 003/2021 | 469.08
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Contract | Contracts | ARBORWORKS INC | 001/2021 | 1804
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 1.06
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1786.8
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 2.19
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 605.73
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Labor Internal | Mapping | Not assigned | 001/2021 | 5.41
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 1.3
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 359.86
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 341.29
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 296.81
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 300.88
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 786.31
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 800.93
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 811.91
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | Benefits OH | Not assigned | 001/2021 | 2.61
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | Benefits OH | Not assigned | 002/2021 | 718.93
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.45
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 123.38
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 2.38
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 657.9
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1.47
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 404.71
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | IT Device OH | Not assigned | 001/2021 | 0.25
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | IT Device OH | Not assigned | 002/2021 | 70.03
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1.99
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 548.19
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.88
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 242.89
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 51112.95
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -59124.35
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 1623.6
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 1.06
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 2.01
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 25.24
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Labor Internal | Mapping | Not assigned | 001/2021 | 4.87
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 1.19
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.99
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 305.34
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 273.69
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 227.31
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 747.45
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 738.53
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 613.38
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | Benefits OH | Not assigned | 001/2021 | 2.39
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | Benefits OH | Not assigned | 002/2021 | 29.96
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.41
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.14
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | Capitalized A&G | Not assigned | 001/2021 | 2.18
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | Capitalized A&G | Not assigned | 002/2021 | 27.41
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1.34
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 16.86
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | IT Device OH | Not assigned | 001/2021 | 0.23
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | IT Device OH | Not assigned | 002/2021 | 2.92
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1.82
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 22.84
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.8
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.12
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | Permits/Fees | CHRISTINE V AGUILAR | 002/2021 | 469.08
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | Permits/Fees | Not assigned | 001/2021 | 469.08
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | Permits/Fees | Not assigned | 002/2021 | -469.08
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 001/2021 | 1471.63
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 113325.74
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 75.72
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 44.98
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 178.84
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 255.18
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 255.72
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 446.29
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 688.58
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 690.04
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | Other | Benefits OH | Not assigned | 002/2021 | 89.88
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.42
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 82.24
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 50.59
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | Other | IT Device OH | Not assigned | 002/2021 | 8.76
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 68.52
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.36
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Construction Inspection | CANUS CORPORATION | 001/2021 | 4050.71
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Construction Inspection | CANUS CORPORATION | 002/2021 | 6390.09
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Contracts | ARBORWORKS INC | 001/2021 | 1522.13
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Contracts | ARBORWORKS INC | 003/2021 | 184.5
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Contracts | BESS TESTLAB INC | 003/2021 | 217.05
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Contracts | CANUS CORPORATION | 001/2021 | 2561.19
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Contracts | CANUS CORPORATION | 002/2021 | 2794.38
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 405.3
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Contracts | CANUS CORPORATION | 004/2021 | 137.94
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Electric Construction Contract | ALVAH CONTRACTORS INC | 001/2021 | 16608.96
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Electric Construction Contract | ALVAH CONTRACTORS INC | 003/2021 | 19399.87
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 001/2021 | -1303.52
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 77211.71
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 003/2021 | -76531.71
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 185.09
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 154.06
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 379.08
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -196.3
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -900
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 500
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 250
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Construction | Not assigned | 002/2021 | 25.72
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1340.1
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 2754.65
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1637.91
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Field Services | Not assigned | 001/2021 | 75.75
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Hours - Straight Time | Not assigned | 001/2021 | 434.49
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 986.31
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 943.91
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 817.23
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Indirect Labor - Gas | Not assigned | 002/2021 | 9.31
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Indirect Labor - IT | Not assigned | 001/2021 | 162.07
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 001/2021 | 703.04
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Maintain & Operate Services | Not assigned | 001/2021 | 721.75
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Maintain & Operate Services | Not assigned | 003/2021 | 710.3
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 68.86
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 29.74
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 62.51
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 673.48
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 565.94
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 485.53
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 001/2021 | 677.7
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 003/2021 | -1307.74
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Materials | Material Burden | Not assigned | 001/2021 | 350.25
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Materials | Material Burden | Not assigned | 003/2021 | -2280.37
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 001/2021 | 1721.28
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | -14311.23
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1967.64
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3900.47
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Benefits OH | Not assigned | 001/2021 | 1384.87
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Benefits OH | Not assigned | 002/2021 | 1132.43
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Benefits OH | Not assigned | 003/2021 | 500.91
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 237.67
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 194.38
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 90.55
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 1231.25
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 1034.68
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 887.62
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Cellular Phone Use | VERIZON WIRELESS | 001/2021 | 0.42
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Cellular Phone Use | VERIZON WIRELESS | 002/2021 | 0.39
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Cellular Phone Use | VERIZON WIRELESS | 003/2021 | 4.86
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 659
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 630.66
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 546.03
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Fleet OH - Gas | Not assigned | 002/2021 | 7.97
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | IT Device OH | Not assigned | 001/2021 | 134.87
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | IT Device OH | Not assigned | 002/2021 | 110.31
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | IT Device OH | Not assigned | 003/2021 | 51.4
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Minor Material OH | Not assigned | 001/2021 | 195.47
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Minor Material OH | Not assigned | 003/2021 | -1272.64
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 892.63
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 854.24
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 739.6
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 14.27
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Operation Mgmt & Support - IT | Not assigned | 001/2021 | 69.74
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 467.89
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 382.59
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 178.23
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Contract | Construction Inspection | CANUS CORPORATION | 001/2021 | 1661.28
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Contract | Contracts | ARBORWORKS INC | 001/2021 | 553.5
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Contract | Contracts | ARBORWORKS INC | 003/2021 | -57286.05
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Contract | Contracts | CANUS CORPORATION | 001/2021 | 959.48
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Contract | Contracts | CANUS CORPORATION | 002/2021 | 389.84
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Contract | Electric Construction Contract | ALVAH CONTRACTORS INC | 001/2021 | 7796.99
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Contract | Electric Construction Contract | Not assigned | 001/2021 | -23305.15
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Contract | Electric Construction Contract | Not assigned | 002/2021 | -7796.99
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 187.53
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | -96.63
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | -250
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 500
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 372.25
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -12.36
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 17.36
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 68.44
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Labor Internal | Mapping | Not assigned | 001/2021 | -36.44
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Labor Internal | Mapping | Not assigned | 002/2021 | -23.26
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Labor Internal | Mapping | Not assigned | 003/2021 | -170.36
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | -7.35
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 10.31
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 40.66
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 003/2021 | -2422.85
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Materials | Material Burden | Not assigned | 003/2021 | -378.75
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 003/2021 | -171.3
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1487.55
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1254.37
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1201.56
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3427.01
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3384.82
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3242.31
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | Benefits OH | Not assigned | 001/2021 | -14.66
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | Benefits OH | Not assigned | 002/2021 | 20.6
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | Benefits OH | Not assigned | 003/2021 | 7.34
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | Building Service Overhead | Not assigned | 001/2021 | -2.51
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 3.54
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 1.34
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | -13.41
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 18.84
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 74.33
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | -8.25
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 11.6
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 45.72
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | IT Device OH | Not assigned | 001/2021 | -1.44
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | IT Device OH | Not assigned | 002/2021 | 2
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | IT Device OH | Not assigned | 003/2021 | 0.75
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | Minor Material OH | Not assigned | 003/2021 | -211.37
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -11.18
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 15.7
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 61.94
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | -4.96
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 6.97
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 2.61
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Contract | Contracts | ARBORWORKS INC | 002/2021 | -107941.6
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 226.67
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 159.28
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 659.53
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -476.75
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -2150
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 7295
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 7315
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -6250
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 71.25
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Labor Internal | Analyst Svcs Overtime | Not assigned | 003/2021 | 79.49
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Labor Internal | Construction | Not assigned | 003/2021 | 744.5
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 2680.2
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 818.95
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 3796.96
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 52.23
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 906.63
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 175.43
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1550
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 18.45
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 211.23
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Labor Internal | Manage L&EM | Not assigned | 003/2021 | 518.4
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Labor Internal | Mapping | Not assigned | 001/2021 | -5.77
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Labor Internal | Mapping | Not assigned | 002/2021 | -301.46
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Labor Internal | Mapping | Not assigned | 003/2021 | 30.84
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 538.63
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 114.75
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1041.28
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1650.62
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1327.07
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1279.76
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3777.36
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3580.99
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3453.32
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Benefits OH | Not assigned | 001/2021 | 1076.06
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Benefits OH | Not assigned | 002/2021 | 226.12
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Benefits OH | Not assigned | 003/2021 | 1941.47
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 184.68
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 38.81
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 350.89
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 984.73
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 209.77
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 1903.67
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 605.76
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 117.21
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1035.63
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | IT Device OH | Not assigned | 001/2021 | 104.81
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | IT Device OH | Not assigned | 002/2021 | 22.02
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | IT Device OH | Not assigned | 003/2021 | 199.15
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 820.52
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 158.76
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1402.79
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 11.05
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 126.51
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Other Land Fees | JOEL PLUIM | 003/2021 | 15000
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 363.55
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 76.39
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 690.75
35116511 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 3430
35116511 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 154.46
35116511 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 134.79
35116511 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 137.49
35116511 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 356.42
35116511 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 363.71
35116511 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 371
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Contract | Construction Management Contracts | TRC SOLUTIONS INC | 002/2021 | 236
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 2842
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 194.4
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 34.82
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 35.19
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 68.68
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 32.4
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 001/2021 | 32.4
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 20.06
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 39.15
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 184.96
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 160.2
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 163.26
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 424.34
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 432.29
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 440.54
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | Benefits OH | Not assigned | 001/2021 | 34.15
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | Benefits OH | Not assigned | 003/2021 | 63.26
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 5.87
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 11.43
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 36.68
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 71.58
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | IT Device OH | Not assigned | 001/2021 | 3.32
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | IT Device OH | Not assigned | 003/2021 | 6.49
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | Land Acquisition Services | INTERWEST CONSULTING GROUP INC | 001/2021 | 196.18
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | Land Acquisition Services | INTERWEST CONSULTING GROUP INC | 002/2021 | 201.32
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | Land Acquisition Services | INTERWEST CONSULTING GROUP INC | 003/2021 | 20
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | Land Acquisition Services | INTERWEST CONSULTING GROUP INC | 004/2021 | -20
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 21.08
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 41.14
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | Other Land Fees | CORPORATION SERVICE COMPANY | 003/2021 | 63.1
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 11.53
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 22.5
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE ENGINEERING INC | 001/2021 | 1206.77
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 1500
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 142.13
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 127.94
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 129.04
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 339.91
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 345.24
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 348.19
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 3298.56
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 1500
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Labor Internal | Analyst Svcs Overtime | Not assigned | 003/2021 | 158.98
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 3.36
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 56.17
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Labor Internal | Mapping | Not assigned | 001/2021 | 9.9
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 1.99
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 32.02
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 171.99
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 155.69
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 157.12
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 410.48
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 420.13
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 423.97
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Other | Benefits OH | Not assigned | 001/2021 | 3.99
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Other | Benefits OH | Not assigned | 003/2021 | 51.74
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.68
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 9.35
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 3.65
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 58.54
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 2.24
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Other | IT Device OH | Not assigned | 001/2021 | 0.39
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Other | IT Device OH | Not assigned | 003/2021 | 5.31
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 3.04
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 33.64
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 1.35
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 18.41
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | Labor Internal | Analyst Svcs Overtime | Not assigned | 003/2021 | 79.49
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 28.08
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 16.01
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 356.62
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 310.1
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 310.26
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 836.78
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 836.78
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 837.21
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 25.88
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 4.68
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 29.27
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 2.65
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 16.82
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 9.21
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | Labor Internal | Analyst Svcs Overtime | Not assigned | 003/2021 | 79.49
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 28.08
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 16.01
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 278.14
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 241.22
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 241.38
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 650.91
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 650.91
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 651.35
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | Other | Benefits OH | Not assigned | 003/2021 | 25.88
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 4.68
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 29.27
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | Other | IT Device OH | Not assigned | 003/2021 | 2.65
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 16.82
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 9.21
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 189.63
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 199.62
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 10290
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Labor Internal | Analyst Svcs Overtime | Not assigned | 003/2021 | 79.49
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 297.8
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 101.14
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.2
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 28.08
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.57
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.6
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 60.09
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.12
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 16.01
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 180.43
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 163.02
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 170.9
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 416.84
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 439.89
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 461.15
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | Benefits OH | Not assigned | 001/2021 | 120.06
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | Benefits OH | Not assigned | 002/2021 | 0.24
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | Benefits OH | Not assigned | 003/2021 | 25.88
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 20.61
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.04
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 4.68
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 109.86
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.22
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 29.27
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 67.58
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.14
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | IT Device OH | Not assigned | 001/2021 | 11.69
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | IT Device OH | Not assigned | 002/2021 | 0.02
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | IT Device OH | Not assigned | 003/2021 | 2.65
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 91.54
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.18
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 16.82
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 40.56
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.08
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 9.21
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 5390
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Labor Internal | Analyst Services | Not assigned | 001/2021 | 55.69
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Labor Internal | Analyst Svcs Overtime | Not assigned | 002/2021 | 79.49
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 75.72
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 19.68
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 28.08
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 56.2
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 16.01
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 186.03
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 168.86
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 172.94
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 443
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 455.65
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 466.65
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | Benefits OH | Not assigned | 001/2021 | 108.96
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | Benefits OH | Not assigned | 002/2021 | 27.25
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | Building Service Overhead | Not assigned | 001/2021 | 18.69
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | Building Service Overhead | Not assigned | 002/2021 | 4.68
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | Capitalized A&G | Not assigned | 001/2021 | 102.75
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | Capitalized A&G | Not assigned | 002/2021 | 29.27
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 50.59
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | IT Device OH | Not assigned | 001/2021 | 10.61
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | IT Device OH | Not assigned | 002/2021 | 2.65
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 68.52
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 11.78
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 16.82
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 36.81
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 9.21
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE ENGINEERING INC | 001/2021 | 21586
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 1500
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 297.8
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 100.95
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 59.98
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 125.69
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 129.57
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 130.75
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 298.63
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 349.64
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 352.83
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | Other | Benefits OH | Not assigned | 001/2021 | 119.83
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 20.57
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 109.65
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 67.45
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | Other | IT Device OH | Not assigned | 001/2021 | 11.67
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 91.37
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 40.48
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Contract | Construction Inspection | CANUS CORPORATION | 001/2021 | 2832.2
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Contract | Contracts | ARBORWORKS INC | 001/2021 | 4535.63
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Contract | Contracts | ARBORWORKS INC | 002/2021 | 2398.5
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Contract | Contracts | CANUS CORPORATION | 001/2021 | 2833.2
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Contract | Contracts | CANUS CORPORATION | 002/2021 | 1567.02
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 530
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Contract | Electric Construction Contract | ALVAH CONTRACTORS INC | 001/2021 | 3832.8
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Contract | Electric Construction Contract | ALVAH CONTRACTORS INC | 003/2021 | 34396.12
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 001/2021 | -7676.32
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 002/2021 | 198.14
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 185.09
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 82.5
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 433.95
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -196.3
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -650
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 250
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 500
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Labor Internal | Construction | Not assigned | 001/2021 | 893.4
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Labor Internal | Construction | Not assigned | 002/2021 | 993.57
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Labor Internal | Construction | Not assigned | 003/2021 | 1153.98
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Labor Internal | Construction | Not assigned | 004/2021 | 223.35
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 111.69
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 148.92
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 670.09
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 349.45
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 386.2
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 658.35
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Labor Internal | Indirect Labor - Gas | Not assigned | 002/2021 | 9.31
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 25.72
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 22.43
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 117.97
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 207.62
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 234.62
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 391.12
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1390.66
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2793.42
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Benefits OH | Not assigned | 001/2021 | 414.77
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 470.49
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 741.96
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 71.19
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 80.76
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 134.1
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 379.53
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 428.92
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 715.06
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 233.47
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 258.03
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 439.86
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Fleet OH - Gas | Not assigned | 002/2021 | 7.97
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | IT Device OH | Not assigned | 001/2021 | 40.41
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | IT Device OH | Not assigned | 002/2021 | 45.84
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 76.11
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 316.25
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 349.51
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 595.81
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 14.27
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 140.14
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 158.95
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 263.98
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Contract | Construction Inspection | CANUS CORPORATION | 003/2021 | 985.09
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Contract | Contracts | ARBORWORKS INC | 001/2021 | 738
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Contract | Contracts | BESS TESTLAB INC | 003/2021 | 144.7
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 001/2021 | -974.54
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 002/2021 | 94.29
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 003/2021 | -282.84
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 003/2021 | 195191
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 004/2021 | -195191
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 308.29
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 799.25
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -500
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 2275
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 5580
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -4100
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Construction | Not assigned | 003/2021 | 990.51
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 1265.7
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 370.06
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 261.84
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1340.1
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 670.06
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 208.92
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 104.46
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -0.35
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 457.05
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1644.07
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 73.81
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 36.91
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 27.91
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 003/2021 | 360.3
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Maintain & Operate Services | Not assigned | 003/2021 | 380.67
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Mapping | Not assigned | 001/2021 | -1.03
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 8.16
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 627.8
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 41.88
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 271.55
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1013.32
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 003/2021 | 160.11
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Materials | Construction Supplies | Not assigned | 003/2021 | 47.87
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Materials | Electl & Electronic Equipment Component | Not assigned | 003/2021 | 3683.71
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Materials | Electrical Specialties | Not assigned | 003/2021 | 528.83
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Materials | Material Burden | Not assigned | 003/2021 | 786.7
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 003/2021 | 789.81
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 178.02
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2504.84
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2134.66
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2311.86
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 5745.5
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 5760.2
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6238.35
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Benefits OH | Not assigned | 001/2021 | 71.17
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Benefits OH | Not assigned | 002/2021 | 542.47
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Benefits OH | Not assigned | 003/2021 | 2066.34
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 12.22
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 93.11
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 373.49
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 76.53
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 496.42
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 1852.57
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Cash Discount earned | STELLA-JONES CORPORATION | 003/2021 | -14.67
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | -0.23
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 305.37
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1098.49
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 23.89
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | IT Device OH | Not assigned | 001/2021 | 6.92
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | IT Device OH | Not assigned | 002/2021 | 52.86
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | IT Device OH | Not assigned | 003/2021 | 211.98
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Minor Material OH | Not assigned | 003/2021 | 439.05
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -0.32
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 413.65
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1487.92
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 44.21
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 22.1
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 42.8
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 24.06
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 183.28
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 735.22
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 220.1
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 799.25
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 430
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 850
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -600
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.4
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.71
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1.76
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.18
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 2.08
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Labor Internal | Mapping | Not assigned | 003/2021 | 5.19
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.24
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.42
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1.05
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | Benefits OH | Not assigned | 001/2021 | 0.47
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | Benefits OH | Not assigned | 002/2021 | 0.83
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | Benefits OH | Not assigned | 003/2021 | 1.99
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.08
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.14
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.36
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.43
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.77
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 1.91
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | Cash Discount earned | ROAD SAFETY INC | 001/2021 | -28.2
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.27
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.47
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1.18
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | IT Device OH | Not assigned | 001/2021 | 0.04
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | IT Device OH | Not assigned | 002/2021 | 0.08
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | IT Device OH | Not assigned | 003/2021 | 0.21
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.36
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.64
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1.59
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.16
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.28
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.71
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 001/2021 | 1.06
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 2.12
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1489
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1.08
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 504.77
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.64
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 299.88
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 287.82
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 247.23
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 250.7
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 657.74
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 667.13
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 676.5
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | Benefits OH | Not assigned | 001/2021 | 1.28
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | Benefits OH | Not assigned | 002/2021 | 599.1
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.22
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 102.81
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 1.17
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 548.25
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.72
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 337.26
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | IT Device OH | Not assigned | 001/2021 | 0.12
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | IT Device OH | Not assigned | 002/2021 | 58.35
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.98
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 456.83
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.43
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 202.4
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Contract | Contracts | ARBORWORKS INC | 002/2021 | 2029.5
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Contract | Contracts | ARBORWORKS INC | 003/2021 | 2501
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Contract | Contracts | BESS TESTLAB INC | 003/2021 | 373.33
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Contract | Contracts | WINDY TREE INC | 002/2021 | 6808
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Contract | Contracts | Not assigned | 002/2021 | 6808
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 15.91
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 2.92
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Labor Internal | Mapping | Not assigned | 002/2021 | 46.93
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Labor Internal | Mapping | Not assigned | 003/2021 | 8.62
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 9.45
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1.74
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Other | Benefits OH | Not assigned | 002/2021 | 18.89
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Other | Benefits OH | Not assigned | 003/2021 | 3.29
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Other | Building Service Overhead | Not assigned | 002/2021 | 3.24
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.6
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Other | Capitalized A&G | Not assigned | 002/2021 | 17.28
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Other | Capitalized A&G | Not assigned | 003/2021 | 3.17
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 10.63
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1.95
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Other | IT Device OH | Not assigned | 002/2021 | 1.84
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Other | IT Device OH | Not assigned | 003/2021 | 0.33
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 14.39
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 2.64
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 6.38
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 1.17
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 791.32
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 3300
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Labor Internal | Analyst Services | Not assigned | 003/2021 | 111.38
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 372.25
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 126.99
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 39.35
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 2.37
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 75.45
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 22.43
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 179.05
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 156.63
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 159.3
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 412.14
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 422.66
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 429.86
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Other | Benefits OH | Not assigned | 001/2021 | 150.73
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 36.25
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 25.87
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 6.55
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 137.93
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 41.01
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 84.85
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Other | IT Device OH | Not assigned | 001/2021 | 14.68
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 3.73
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 114.94
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 23.57
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 50.93
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 12.9
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 3822
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 110.57
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 97.84
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 100.61
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 256.58
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 264.03
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 271.48
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | Contract | Contracts | Not assigned | 001/2021 | -35317.22
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLAIR CHURCH & FLYNN CONSULTING | 001/2021 | -5494.5
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLAIR CHURCH & FLYNN CONSULTING | 002/2021 | 13931.04
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -35.92
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | Labor Internal | Mapping | Not assigned | 001/2021 | -105.95
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | -21.34
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 133.57
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 80.84
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 91.81
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 275.96
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 218.14
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 247.74
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | Other | Benefits OH | Not assigned | 001/2021 | -42.64
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | Other | Building Service Overhead | Not assigned | 001/2021 | -7.32
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | -39.01
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | -24
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | Other | IT Device OH | Not assigned | 001/2021 | -4.15
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -32.51
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | -14.4
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 3.18
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1.08
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.64
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 157.19
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 132.23
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 132.23
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 356.78
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 356.8
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 356.8
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | Other | Benefits OH | Not assigned | 001/2021 | 1.28
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.22
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 1.17
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.72
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | Other | IT Device OH | Not assigned | 001/2021 | 0.12
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.98
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.43
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Contract | Construction Inspection | PRO ENERGY SERVICES GROUP LLC | 001/2021 | 3465.6
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLAIR CHURCH & FLYNN CONSULTING | 001/2021 | -20374.41
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLAIR CHURCH & FLYNN CONSULTING | 002/2021 | 20374.41
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -1448
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 3.53
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Labor Internal | Mapping | Not assigned | 001/2021 | 10.4
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 2.09
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 109.66
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 94.58
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 110.62
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 250.86
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 255.21
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 298.51
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Other | Benefits OH | Not assigned | 001/2021 | 4.19
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.72
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Other | Capitalized A&G | Not assigned | 001/2021 | 3.83
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 2.36
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Other | IT Device OH | Not assigned | 001/2021 | 0.41
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 3.19
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 1.42
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 3626
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 118.32
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 103.17
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 105.83
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 | Other | AFUDC-Equity | Not assigned | 001/2021 | 271.24
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 | Other | AFUDC-Equity | Not assigned | 002/2021 | 278.4
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 285.56
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 71022.48
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -29592.4
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 82.63
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 111.88
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 88.58
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 213.86
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 301.9
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 239.02
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 1347.56
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 002/2021 | 1705
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 003/2021 | 1622.87
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Contract | Electric Construction Contract | SILLER CONSTRUCTION CO | 002/2021 | 10374.72
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Contract | Electric Construction Contract | SILLER CONSTRUCTION CO | 003/2021 | 38009.52
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Contract | Electric Construction Contract | SILLER CONSTRUCTION CO | 004/2021 | -25000
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE ENGINEERING INC | 001/2021 | 14828.72
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 101.73
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 799.24
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | 115
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 335
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 1375
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -615
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Account Services | Not assigned | 001/2021 | 196.89
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Account Services | Not assigned | 002/2021 | 65.63
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Account Services | Not assigned | 003/2021 | 196.89
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Administration | Not assigned | 002/2021 | 557.12
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Administration | Not assigned | 003/2021 | 766.04
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Construction | Not assigned | 001/2021 | 28372.75
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Construction | Not assigned | 002/2021 | 32896.5
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Construction | Not assigned | 003/2021 | 42934.24
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Construction | Not assigned | 004/2021 | 6814
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 1561.7
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 6514.02
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 2186.37
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Construction Overtime Services | Not assigned | 004/2021 | 446.2
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 118.42
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 118.42
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 236.84
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 523.27
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 69.64
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 50.97
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 16.99
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 50.97
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 10279.77
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 13558.56
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 15717.75
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 196.83
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 295.24
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 18.62
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Mapping | Not assigned | 001/2021 | 270.93
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Mapping | Not assigned | 002/2021 | 392.37
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Mapping | Not assigned | 003/2021 | 535.79
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 6146.86
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 8180.57
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 9556.23
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 001/2021 | 151.25
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Materials | Construction Supplies | Not assigned | 001/2021 | 443.83
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Materials | Material Burden | Not assigned | 001/2021 | 202.99
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 001/2021 | 795.29
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3385.65
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 3006.34
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3256.06
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 7768.55
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 8112.35
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 8786.19
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Benefits OH | Not assigned | 001/2021 | 12295.98
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Benefits OH | Not assigned | 002/2021 | 16301.86
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Benefits OH | Not assigned | 003/2021 | 18062.12
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Building Service Overhead | Not assigned | 001/2021 | 2110.31
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Building Service Overhead | Not assigned | 002/2021 | 2797.83
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Building Service Overhead | Not assigned | 003/2021 | 3264.6
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Capitalized A&G | Not assigned | 001/2021 | 11237.72
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Capitalized A&G | Not assigned | 002/2021 | 14955.73
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Capitalized A&G | Not assigned | 003/2021 | 17470.75
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 6868.34
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 9059.04
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 10501.69
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 15.94
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | IT Device OH | Not assigned | 001/2021 | 1197.76
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | IT Device OH | Not assigned | 002/2021 | 1587.97
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | IT Device OH | Not assigned | 003/2021 | 1852.87
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Minor Material OH | Not assigned | 001/2021 | 113.29
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 9303.34
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 12270.7
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 14224.81
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 117.89
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 176.84
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 28.54
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Other Land Fees | RICHARD SCHLUTER | 003/2021 | 5250
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 4154.23
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 5507.62
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 6426.47
35117444 | CWSP - VOLTA 1102 LR 1648 PH 2.1 | Other | Land Acquisition Services | INTERWEST CONSULTING GROUP INC | 001/2021 | 51.18
35117444 | CWSP - VOLTA 1102 LR 1648 PH 2.1 | Other | Land Acquisition Services | INTERWEST CONSULTING GROUP INC | 002/2021 | 1726.2
35117444 | CWSP - VOLTA 1102 LR 1648 PH 2.1 | Other | Land Acquisition Services | INTERWEST CONSULTING GROUP INC | 003/2021 | -1389.88
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 497.13
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 49.51
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -2300
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 7295
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 7040
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -5000
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Contract | Environmental Contract | SURF TO SNOW ENVIRONMENTAL RESOURCE | 002/2021 | 2749.58
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -1.83
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 10.26
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 7.16
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Labor Internal | Mapping | Not assigned | 001/2021 | -5.41
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Labor Internal | Mapping | Not assigned | 002/2021 | 30.28
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Labor Internal | Mapping | Not assigned | 003/2021 | 21.12
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | -1.09
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 6.1
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 4.25
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | Benefits OH | Not assigned | 001/2021 | -2.18
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | Benefits OH | Not assigned | 002/2021 | 12.17
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | Benefits OH | Not assigned | 003/2021 | 8.07
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | Building Service Overhead | Not assigned | 001/2021 | -0.37
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | Building Service Overhead | Not assigned | 002/2021 | 2.09
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | Building Service Overhead | Not assigned | 003/2021 | 1.45
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | Capitalized A&G | Not assigned | 001/2021 | -1.99
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | Capitalized A&G | Not assigned | 002/2021 | 11.15
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | Capitalized A&G | Not assigned | 003/2021 | 7.78
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | -1.23
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 6.86
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 4.78
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | IT Device OH | Not assigned | 001/2021 | -0.21
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | IT Device OH | Not assigned | 002/2021 | 1.18
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | IT Device OH | Not assigned | 003/2021 | 0.83
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -1.66
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 9.29
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 6.48
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | -0.74
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 4.12
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 2.87
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Contract | Contracts | THE ORIGINAL MOWBRAY'S TREE SERVICE | 003/2021 | -0.8
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 22.05
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 002/2021 | 800.7
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Account Services | Not assigned | 001/2021 | 65.64
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Account Services | Not assigned | 002/2021 | 65.64
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Account Services | Not assigned | 003/2021 | 82.05
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 372.6
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Administration | Not assigned | 002/2021 | 139.28
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Design Drafting Services | Not assigned | 001/2021 | 355.26
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Design Drafting Services - Overtime | Not assigned | 001/2021 | 567.32
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 636.52
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1153.98
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1526.23
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1191.21
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 69.64
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 16.99
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 16.99
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 21.24
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 919.73
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 518.23
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 403.82
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 320.52
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 49.21
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 24.6
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 001/2021 | 534.6
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Mapping | Not assigned | 002/2021 | 2.47
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 742.34
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 349.15
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 270.46
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Materials | Material Burden | Not assigned | 002/2021 | 1520.27
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Materials | Material Burden | Not assigned | 003/2021 | -2488.73
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 10412.8
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | -17046.13
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1292.68
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1131.39
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1132.59
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | AFUDC-Equity | Not assigned | 001/2021 | 2963.08
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | AFUDC-Equity | Not assigned | 002/2021 | 3052.97
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | AFUDC-Equity | Not assigned | 003/2021 | 3056.18
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Benefits OH | Not assigned | 001/2021 | 1421.1
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Benefits OH | Not assigned | 002/2021 | 976.38
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Benefits OH | Not assigned | 003/2021 | 41.31
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Building Service Overhead | Not assigned | 001/2021 | 243.92
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Building Service Overhead | Not assigned | 002/2021 | 167.56
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Building Service Overhead | Not assigned | 003/2021 | 7.48
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Capitalized A&G | Not assigned | 001/2021 | 1357.16
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Capitalized A&G | Not assigned | 002/2021 | 638.32
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Capitalized A&G | Not assigned | 003/2021 | 494.45
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Fleet OH - Elec | Not assigned | 001/2021 | 614.52
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Fleet OH - Elec | Not assigned | 002/2021 | 346.25
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Fleet OH - Elec | Not assigned | 003/2021 | 269.81
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | IT Device OH | Not assigned | 001/2021 | 138.42
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | IT Device OH | Not assigned | 002/2021 | 95.11
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | IT Device OH | Not assigned | 003/2021 | 4.24
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Minor Material OH | Not assigned | 002/2021 | 848.44
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Minor Material OH | Not assigned | 003/2021 | -1388.93
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 832.37
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 469.01
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 365.46
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 191.97
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 29.47
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 14.74
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Other Land Fees | ROBERT BRUCE CRISWELL | 001/2021 | 4500
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Payroll Taxes OH | Not assigned | 001/2021 | 480.11
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Payroll Taxes OH | Not assigned | 002/2021 | 329.86
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Payroll Taxes OH | Not assigned | 003/2021 | 14.7
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Permits/FeesLand Surveying Services | BLAIR CHURCH & FLYNN CONSULTING | 001/2021 | 16474
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Permits/FeesLand Surveying Services | BLAIR CHURCH & FLYNN CONSULTING | 002/2021 | -4942
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Other | Permits/FeesLand Surveying Services | BLAIR CHURCH & FLYNN CONSULTING | 003/2021 | 4942
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | Labor Internal | Account Services | Not assigned | 001/2021 | 49.23
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 12.75
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 9.91
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 8.75
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 7.54
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 7.54
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 20.1
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 20.34
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 20.34
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | Other | Benefits OH | Not assigned | 001/2021 | 13.95
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 2.39
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 18.13
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | Other | IT Device OH | Not assigned | 001/2021 | 1.36
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 4.71
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | Labor Internal | Account Services | Not assigned | 001/2021 | 49.23
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 12.75
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 9.91
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 10.29
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 8.84
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 8.84
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 23.62
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 23.86
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 23.86
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | Other | Benefits OH | Not assigned | 001/2021 | 13.95
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | Other | Building Service Overhead | Not assigned | 001/2021 | 2.39
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | Other | Capitalized A&G | Not assigned | 001/2021 | 18.13
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | Other | IT Device OH | Not assigned | 001/2021 | 1.36
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 4.71
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 145.84
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 920.12
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -492.59
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | 35
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 540
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 1240
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -550
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor Internal | Administrative Services - OT | Not assigned | 001/2021 | 88.01
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 744.5
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.43
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 253.13
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 2.28
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 71.16
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 22.89
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 17.17
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 64.8
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 64.8
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 48.6
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 001/2021 | 48.6
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.28
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 2.19
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 6.73
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 40.82
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 163.43
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 11.15
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Materials | Material Burden | Not assigned | 003/2021 | -1401.43
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | -9598.81
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Benefits OH | Not assigned | 001/2021 | 69.54
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Benefits OH | Not assigned | 002/2021 | 322.65
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Benefits OH | Not assigned | 003/2021 | -239.82
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 11.94
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 55.39
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Building Service Overhead | Not assigned | 003/2021 | -43.35
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 74.63
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 298.79
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 20.37
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.29
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 169.13
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1.52
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | IT Device OH | Not assigned | 001/2021 | 6.78
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | IT Device OH | Not assigned | 002/2021 | 31.42
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | IT Device OH | Not assigned | 003/2021 | -24.6
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Minor Material OH | Not assigned | 003/2021 | -782.12
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.39
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 229.08
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 2.06
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 42.62
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 13.71
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 10.28
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 23.51
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 109.01
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | -85.32
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 145.84
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 820.12
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | 35
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 450
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 1100
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -550
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 86.1
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.43
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.69
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 2.04
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.28
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 2.05
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 6.01
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.26
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.41
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1.21
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | Benefits OH | Not assigned | 001/2021 | 0.52
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | Benefits OH | Not assigned | 002/2021 | 0.82
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | Benefits OH | Not assigned | 003/2021 | 2.29
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.09
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.14
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.41
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.47
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.75
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 2.21
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.29
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.46
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1.36
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | IT Device OH | Not assigned | 001/2021 | 0.05
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | IT Device OH | Not assigned | 002/2021 | 0.08
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | IT Device OH | Not assigned | 003/2021 | 0.23
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.39
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.63
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1.84
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.18
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.28
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.81
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | Other | Postage | PITNEY BOWES BANK | 001/2021 | 12.6
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Labor Internal | Account Services | Not assigned | 001/2021 | 82.05
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 21.24
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 16.52
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 229.74
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 159.65
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 120.65
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 535.64
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 430.81
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 325.58
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Other | Benefits OH | Not assigned | 001/2021 | 23.24
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Other | Building Service Overhead | Not assigned | 001/2021 | 3.99
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Other | Capitalized A&G | Not assigned | 001/2021 | 30.21
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Other | IT Device OH | Not assigned | 001/2021 | 2.26
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 7.85
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 002/2021 | -49521.26
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 90.41
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 117.87
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 243.39
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -112.14
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 21.53
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 41.14
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -20.54
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.09
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.14
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.29
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.27
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.42
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.85
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.05
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.08
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 0.17
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Benefits OH | Not assigned | 001/2021 | 0.11
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Benefits OH | Not assigned | 002/2021 | 0.17
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Benefits OH | Not assigned | 003/2021 | 0.33
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.02
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.02
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.06
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.1
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.15
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Capitalized A&G | Not assigned | 003/2021 | 0.31
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Cellular Phone Use | VERIZON WIRELESS | 002/2021 | 6.96
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Cellular Phone Use | VERIZON WIRELESS | 003/2021 | 6.96
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Cellular Phone Use | Not assigned | 001/2021 | -11.32
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.06
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.1
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.19
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | IT Device OH | Not assigned | 001/2021 | 0.02
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | IT Device OH | Not assigned | 002/2021 | 0.02
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | IT Device OH | Not assigned | 003/2021 | 0.04
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.08
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.13
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.26
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.04
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.06
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.12
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Other | Permits/Fees - Environmental | STATE WATER RESOURCES | 001/2021 | 477.67
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 002/2021 | 12607.55
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 003/2021 | -12.55
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 165.49
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 151.26
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 161.18
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 381.37
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 408.16
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 434.93
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | Contract | Contracts | THE ORIGINAL MOWBRAY'S TREE SERVICE | 002/2021 | 88060.28
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 89.56
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 264.18
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 53.21
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 185.96
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 218.44
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 288.43
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 400.58
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 589.44
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 778.3
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | Other | Benefits OH | Not assigned | 002/2021 | 106.29
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 18.25
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 97.27
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 59.84
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | Other | IT Device OH | Not assigned | 002/2021 | 10.35
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 81.05
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 35.91
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 22.05
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 4.24
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1.44
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.02
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.07
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.85
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.01
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 72.19
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 60.25
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 60.26
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 162.5
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 162.57
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 162.62
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Other | Benefits OH | Not assigned | 001/2021 | 1.7
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Other | Benefits OH | Not assigned | 002/2021 | 0.02
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.29
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 1.56
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.03
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.96
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.02
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Other | IT Device OH | Not assigned | 001/2021 | 0.16
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1.3
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.02
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.56
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | Contract | Contracts | MOUNTAIN F ENTERPRISES INC | 004/2021 | -168362.45
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | Labor Internal | Administration | Not assigned | 002/2021 | 139.28
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 49.21
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 28.05
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 606.07
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 513.86
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 514.16
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1385.82
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1386.62
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1387.41
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | Other | Benefits OH | Not assigned | 002/2021 | 47.73
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 8.19
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 51.28
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | Other | IT Device OH | Not assigned | 002/2021 | 4.65
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 29.47
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 16.13
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 002/2021 | 12607.55
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 003/2021 | -1227.15
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -8688
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | 5430
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 77.52
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 72.89
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 86.13
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 176.82
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 196.69
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 232.41
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | Contract | Construction Inspection | PRO ENERGY SERVICES GROUP LLC | 001/2021 | 1813.39
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1.84
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 5.44
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 1.1
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 66.59
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 58.59
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 58.59
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 154.22
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 158.11
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 158.11
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | Other | Benefits OH | Not assigned | 001/2021 | 2.19
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.37
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 2
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1.23
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | Other | IT Device OH | Not assigned | 001/2021 | 0.21
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1.67
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.74
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Contract | Contracts | CANUS CORPORATION | 001/2021 | 589.06
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 22.05
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 1.06
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.96
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.02
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.77
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.07
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.57
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.01
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 73.65
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 63.97
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 63.99
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 171.41
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 172.63
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 172.67
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Other | Benefits OH | Not assigned | 001/2021 | 1.15
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Other | Benefits OH | Not assigned | 002/2021 | 0.02
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.2
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 1.04
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.03
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.64
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.02
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Other | IT Device OH | Not assigned | 001/2021 | 0.11
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.87
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.02
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.38
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 2.12
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.72
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.43
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 82.8
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 70.99
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 70.99
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 191.54
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 191.55
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 191.55
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | Other | Benefits OH | Not assigned | 001/2021 | 0.85
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.15
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.78
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.48
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | Other | IT Device OH | Not assigned | 001/2021 | 0.08
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.65
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.29
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | Contract | Contracts | CANUS CORPORATION | 001/2021 | 681.1
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 23949
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 003/2021 | -23949
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.69
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 2.04
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.41
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 375.29
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 343.34
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 324.48
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 874.13
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 926.48
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 875.59
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | Other | Benefits OH | Not assigned | 001/2021 | 0.82
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.14
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.75
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.46
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | Other | IT Device OH | Not assigned | 001/2021 | 0.08
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.63
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.28
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Contract | Contracts | CANUS CORPORATION | 001/2021 | 1558.98
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Contract | Contracts | CANUS CORPORATION | 002/2021 | 402.47
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 17207
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 003/2021 | -17207
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 90.2
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Labor Internal | Administration | Not assigned | 001/2021 | 139.28
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Labor Internal | Construction | Not assigned | 001/2021 | 652.4
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 224.83
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.41
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 49.21
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 10.82
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 1.21
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 161.61
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.24
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 250.36
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 233.08
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 220.43
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 584.9
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 628.94
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 594.82
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | Benefits OH | Not assigned | 001/2021 | 314.58
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | Benefits OH | Not assigned | 002/2021 | 0.48
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 53.99
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.08
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 295.47
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.45
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 150.22
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.27
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | IT Device OH | Not assigned | 001/2021 | 30.65
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | IT Device OH | Not assigned | 002/2021 | 0.04
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 203.48
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.37
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 29.47
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 106.28
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.17
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Contract | Contracts | CANUS CORPORATION | 001/2021 | 1558.98
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Contract | Contracts | CANUS CORPORATION | 002/2021 | 524.41
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE ENGINEERING INC | 001/2021 | 14222
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 168.38
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Labor Internal | Construction | Not assigned | 001/2021 | 652.4
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 224.91
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.53
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 11.06
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 1.57
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 133.61
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.32
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 211.56
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 195.18
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 195.58
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 488.55
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 526.67
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 527.76
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | Benefits OH | Not assigned | 001/2021 | 266.94
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | Benefits OH | Not assigned | 002/2021 | 0.63
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 45.82
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.11
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 244.28
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.58
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 150.28
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.36
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | IT Device OH | Not assigned | 001/2021 | 26
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | IT Device OH | Not assigned | 002/2021 | 0.06
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 203.56
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.48
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 90.17
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.22
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | Labor Internal | Electric Estimating Doubletime | Not assigned | 001/2021 | 59.2
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | -38.34
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 7.07
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 4.2
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 217.49
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 183.93
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 183.93
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 496.19
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 496.33
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 496.33
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | Other | Benefits OH | Not assigned | 001/2021 | 8.4
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 1.44
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 7.68
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 4.72
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | Other | IT Device OH | Not assigned | 001/2021 | 0.81
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 6.4
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 2.83
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Contract | Contracts | CANUS CORPORATION | 001/2021 | 1834.18
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE CORPORATION | 001/2021 | 20358
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE CORPORATION | 002/2021 | -20358
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE ENGINEERING INC | 001/2021 | -20358
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE ENGINEERING INC | 002/2021 | 20358
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 20358
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 003/2021 | -20358
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 90.2
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 001/2021 | 315
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 003/2021 | 50.02
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 2.27
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.05
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 6.72
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.15
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 1.36
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 0.03
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 287.52
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 267.05
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 252.29
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 673.48
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 720.61
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 680.77
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | Benefits OH | Not assigned | 001/2021 | 2.69
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | Benefits OH | Not assigned | 003/2021 | 0.06
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.46
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.01
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 2.48
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 0.06
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1.53
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.03
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | IT Device OH | Not assigned | 001/2021 | 0.25
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 2.06
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.05
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.92
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.02
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 001/2021 | 1407.61
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE ENGINEERING INC | 001/2021 | 19885
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -1448
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 168.38
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.17
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.51
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.1
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 250.64
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 229.17
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 229.17
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 578.86
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 618.4
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 618.4
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Other | Benefits OH | Not assigned | 001/2021 | 0.2
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.04
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.19
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.12
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Other | IT Device OH | Not assigned | 001/2021 | 0.02
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.16
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.06
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Contract | Construction Inspection | PRO ENERGY SERVICES GROUP LLC | 001/2021 | 1904.34
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | PIKE ENGINEERING INC | 001/2021 | 13439
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 168.38
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 2.11
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 6.22
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 1.25
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 187.35
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 171.6
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 171.6
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 432.6
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 463.05
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 463.05
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Other | Benefits OH | Not assigned | 001/2021 | 2.49
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.43
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 2.29
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1.41
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Other | IT Device OH | Not assigned | 001/2021 | 0.25
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1.91
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.84
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Contract | Contracts | CANUS CORPORATION | 001/2021 | 771.38
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 22.05
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.78
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.02
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Labor Internal | Mapping | Not assigned | 001/2021 | 2.31
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.07
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.47
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.01
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 331.94
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 284.88
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 284.89
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 767.01
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 768.71
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 768.76
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Other | Benefits OH | Not assigned | 001/2021 | 0.94
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Other | Benefits OH | Not assigned | 002/2021 | 0.02
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.16
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.85
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.03
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.52
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.02
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Other | IT Device OH | Not assigned | 001/2021 | 0.09
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.71
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.02
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.31
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 001/2021 | 20439.55
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | -20439.55
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 22.05
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.02
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.07
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.01
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 53.71
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 63.11
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 48.47
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 130.7
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 170.29
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 130.78
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 0.02
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.03
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.02
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.02
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 001/2021 | 34947.89
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | -34947.89
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 80.72
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 99.24
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 73.71
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 198.89
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 267.79
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 198.89
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 001/2021 | 20800
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | -20800
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 1.06
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.36
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.21
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 55.98
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 66.39
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 50.9
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 137.35
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 179.14
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 137.35
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | Other | Benefits OH | Not assigned | 001/2021 | 0.43
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.08
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.39
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.24
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | Other | IT Device OH | Not assigned | 001/2021 | 0.04
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.33
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.14
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 001/2021 | 21835.36
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | -21835.36
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 1.06
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.36
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.21
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 56.9
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 67.01
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 50.66
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 136.7
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 180.81
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 136.71
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | Other | Benefits OH | Not assigned | 001/2021 | 0.43
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.08
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.39
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.24
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | Other | IT Device OH | Not assigned | 001/2021 | 0.04
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.33
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.14
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 001/2021 | 20654.76
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | -20654.76
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 63.6
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 73.19
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 57.59
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 155.39
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 197.49
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 155.39
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 001/2021 | 1904.34
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 1904.34
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 003/2021 | -1904.34
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 001/2021 | 79241.81
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | -79241.81
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 3.18
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Labor Internal | Field Services Overtime | Not assigned | 001/2021 | 80.86
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Labor Internal | Field Services Overtime | Not assigned | 003/2021 | -80.86
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 30.68
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1.94
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | -29.6
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Labor Internal | Mapping | Not assigned | 001/2021 | 6.44
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Labor Internal | Mapping | Not assigned | 002/2021 | 5.71
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Labor Internal | Mapping | Not assigned | 003/2021 | -6.44
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 18.23
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1.15
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | -17.59
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 91.66
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 145.86
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 89.66
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | AFUDC-Equity | Not assigned | 001/2021 | 234.59
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | AFUDC-Equity | Not assigned | 002/2021 | 393.58
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 241.95
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | Benefits OH | Not assigned | 001/2021 | 36.39
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | Benefits OH | Not assigned | 002/2021 | 2.29
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | Benefits OH | Not assigned | 003/2021 | -33.35
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | Building Service Overhead | Not assigned | 001/2021 | 6.25
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.39
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | Building Service Overhead | Not assigned | 003/2021 | -6.03
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | Capitalized A&G | Not assigned | 001/2021 | 33.31
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | Capitalized A&G | Not assigned | 002/2021 | 2.1
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | Capitalized A&G | Not assigned | 003/2021 | -32.14
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 20.49
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1.29
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | Fleet OH - Elec | Not assigned | 003/2021 | -19.77
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | IT Device OH | Not assigned | 001/2021 | 3.55
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | IT Device OH | Not assigned | 002/2021 | 0.23
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | IT Device OH | Not assigned | 003/2021 | -3.43
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 27.76
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1.75
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | -26.78
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 12.31
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.78
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | Other | Payroll Taxes OH | Not assigned | 003/2021 | -11.88
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 001/2021 | 18441.37
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 002/2021 | -18441.37
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 71.32
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 63.29
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 50.64
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 170.78
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 170.78
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 136.65
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Contract | Contracts | CANUS CORPORATION | 001/2021 | 589.06
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Contract | Contracts | MOUNTAIN F ENTERPRISES INC | 001/2021 | 3450
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 001/2021 | 37118.77
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 002/2021 | -37118.77
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 22.05
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 4.11
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.02
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 12.12
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.07
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 2.44
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.01
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 162.54
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 147.83
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 121.1
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 390.93
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 398.91
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 326.77
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Other | Benefits OH | Not assigned | 001/2021 | 4.89
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Other | Benefits OH | Not assigned | 002/2021 | 0.02
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.83
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 4.46
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.03
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 2.74
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.02
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Other | IT Device OH | Not assigned | 001/2021 | 0.48
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 3.72
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.02
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 1.64
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 001/2021 | 65683.51
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 002/2021 | -65683.51
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 136.71
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 124.07
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 72.35
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 334.8
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 334.8
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 195.22
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Contract | Contracts | CANUS CORPORATION | 001/2021 | 539.06
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 22.05
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 34.82
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.55
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.02
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 12.3
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.62
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.07
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 7.34
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.01
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 59.05
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 51.8
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 51.81
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 138.48
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 139.77
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 139.81
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Other | Benefits OH | Not assigned | 001/2021 | 12.59
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Other | Benefits OH | Not assigned | 002/2021 | 0.02
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 2.16
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 13.42
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.03
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.37
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.02
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Other | IT Device OH | Not assigned | 001/2021 | 1.22
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.5
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.02
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 7.37
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 4.25
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 22.05
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.02
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.07
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.01
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 57.98
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 50.96
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 50.97
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 137.46
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 137.51
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 137.55
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | Other | Benefits OH | Not assigned | 002/2021 | 0.02
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.03
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.02
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.02
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLAIR CHURCH & FLYNN CONSULTING | 001/2021 | -59853.3
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 168.38
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.17
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.51
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.1
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 122.63
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 59.66
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 59.66
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 279.59
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 160.99
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 160.99
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | Other | Benefits OH | Not assigned | 001/2021 | 0.2
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.04
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.19
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.12
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | Other | IT Device OH | Not assigned | 001/2021 | 0.02
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.16
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.06
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Contract | Construction Inspection | PRO ENERGY SERVICES GROUP LLC | 001/2021 | 1909.89
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Contract | Construction Inspection | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 1904.34
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLAIR CHURCH & FLYNN CONSULTING | 001/2021 | -83038.8
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 168.38
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 1.06
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 2.47
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1.94
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 6.24
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 5.71
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 1.46
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1.15
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 153.69
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 67.72
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 69.23
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 350.63
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 182.73
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 186.81
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | Benefits OH | Not assigned | 001/2021 | 2.93
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | Benefits OH | Not assigned | 002/2021 | 2.29
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.51
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.39
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 2.69
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 2.1
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1.66
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1.29
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | IT Device OH | Not assigned | 001/2021 | 0.29
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | IT Device OH | Not assigned | 002/2021 | 0.23
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 2.25
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1.75
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.98
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.78
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 001/2021 | 1904.34
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 1904.34
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 003/2021 | -1904.34
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLAIR CHURCH & FLYNN CONSULTING | 001/2021 | -159520.8
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -1629
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | 1448
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 4229.78
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Labor Internal | Administration | Not assigned | 001/2021 | 278.56
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 6.24
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1.94
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | -1.94
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 98.42
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 18.4
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 5.71
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Labor Internal | Mapping | Not assigned | 003/2021 | -5.71
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 59.81
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1.15
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | -1.15
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 269.29
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 127.94
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 128.98
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 639.17
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 345.23
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 348.05
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | Benefits OH | Not assigned | 001/2021 | 102.85
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | Benefits OH | Not assigned | 002/2021 | 2.29
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | Benefits OH | Not assigned | 003/2021 | -2.18
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 17.65
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.39
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | Building Service Overhead | Not assigned | 003/2021 | -0.39
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 109.34
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 2.1
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | Capitalized A&G | Not assigned | 003/2021 | -2.1
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 4.16
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1.29
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | -1.29
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | IT Device OH | Not assigned | 001/2021 | 10.02
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | IT Device OH | Not assigned | 002/2021 | 0.23
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | IT Device OH | Not assigned | 003/2021 | -0.23
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 5.64
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1.75
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | -1.75
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 58.94
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 34.76
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.78
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | -0.78
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | Contract | Construction Inspection | PRO ENERGY SERVICES GROUP LLC | 001/2021 | 1561.26
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1.59
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | Labor Internal | Mapping | Not assigned | 001/2021 | 4.68
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.94
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 81.5
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 70.14
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 70.14
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 185.93
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 189.28
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 189.28
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | Other | Benefits OH | Not assigned | 001/2021 | 1.89
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.33
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 1.72
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1.06
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | Other | IT Device OH | Not assigned | 001/2021 | 0.19
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1.44
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.63
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | Labor Internal | Electric Estimating Doubletime | Not assigned | 001/2021 | 1.02
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | -38.34
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -12.65
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | -7.52
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 191.08
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 171.5
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 171.5
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 463.03
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 462.79
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 462.79
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | Other | Benefits OH | Not assigned | 001/2021 | -15.02
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | Other | Building Service Overhead | Not assigned | 001/2021 | -2.57
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | Other | Capitalized A&G | Not assigned | 001/2021 | -13.74
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | -8.45
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | Other | IT Device OH | Not assigned | 001/2021 | -1.47
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -11.45
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | -5.08
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 64348.8
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 98.7
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 138.88
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 138.88
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 245.97
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 374.76
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 374.76
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | Contract | Construction Inspection | PRO ENERGY SERVICES GROUP LLC | 001/2021 | 1561.26
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1.59
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | Labor Internal | Mapping | Not assigned | 001/2021 | 4.68
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.94
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 151.21
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 129.03
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 129.03
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 344.82
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 348.17
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 348.17
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | Other | Benefits OH | Not assigned | 001/2021 | 1.89
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.33
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 1.72
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1.06
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | Other | IT Device OH | Not assigned | 001/2021 | 0.19
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1.44
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.63
35129640 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 28.21
35129640 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 23.94
35129640 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 23.94
35129640 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 64.61
35129640 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 64.61
35129640 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 64.61
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Contract | Construction Inspection | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 2349.03
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Contract | Contracts | CANUS CORPORATION | 001/2021 | 539.06
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 42609.73
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 003/2021 | -42523.1
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.55
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 2.39
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.62
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Labor Internal | Mapping | Not assigned | 002/2021 | 7.05
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.33
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1.42
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 105.27
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 129.93
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 98.31
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | AFUDC-Equity | Not assigned | 001/2021 | 253.87
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | AFUDC-Equity | Not assigned | 002/2021 | 350.61
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 265.29
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | Benefits OH | Not assigned | 001/2021 | 0.65
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | Benefits OH | Not assigned | 002/2021 | 2.84
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.11
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.48
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.6
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | Capitalized A&G | Not assigned | 002/2021 | 2.6
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.37
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1.6
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | IT Device OH | Not assigned | 001/2021 | 0.06
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | IT Device OH | Not assigned | 002/2021 | 0.27
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.5
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 2.16
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.22
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.96
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 35011.19
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -3439
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | 5068
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 463.32
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.47
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.39
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.28
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 52.35
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 77.84
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 81.83
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Other | AFUDC-Equity | Not assigned | 001/2021 | 131.2
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Other | AFUDC-Equity | Not assigned | 002/2021 | 210.05
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Other | AFUDC-Equity | Not assigned | 003/2021 | 220.82
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Other | Benefits OH | Not assigned | 001/2021 | 0.56
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.1
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.51
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.31
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Other | IT Device OH | Not assigned | 001/2021 | 0.06
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.43
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.19
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Contract | Construction Inspection | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 3717.64
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 1.06
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.36
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 3.78
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 11.15
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.21
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 2.25
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 116.85
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 101.66
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 104.62
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 266.35
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 274.33
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 282.3
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | Benefits OH | Not assigned | 001/2021 | 0.43
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | Benefits OH | Not assigned | 002/2021 | 4.49
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.08
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.77
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.39
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 4.11
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.24
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 2.53
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | IT Device OH | Not assigned | 001/2021 | 0.04
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | IT Device OH | Not assigned | 002/2021 | 0.44
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.33
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 3.42
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.14
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 1.52
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 4259
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Contract | Environmental Contract | FAR WESTERN ANTHROPOLOGICAL | 002/2021 | 99.95
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 4.33
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.1
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 12.78
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.3
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 2.57
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.06
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 92.87
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 84.51
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 84.58
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 218.97
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 228.03
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 228.24
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | Benefits OH | Not assigned | 001/2021 | 5.15
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | Benefits OH | Not assigned | 002/2021 | 0.13
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.89
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.02
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 4.71
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.11
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 2.89
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.07
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | IT Device OH | Not assigned | 001/2021 | 0.5
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | IT Device OH | Not assigned | 002/2021 | 0.02
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 3.92
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.09
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 1.74
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.04
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | Contract | Contracts | CANUS CORPORATION | 001/2021 | 539.06
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 7077.54
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 7.75
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 22.85
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 4.61
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 51.99
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 50.97
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 50.97
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 122.03
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 137.55
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 137.55
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | Other | Benefits OH | Not assigned | 001/2021 | 9.18
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 1.58
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 8.42
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 5.18
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | Other | IT Device OH | Not assigned | 001/2021 | 0.89
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 7.01
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 3.1
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 372.25
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 25.24
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 126.19
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.99
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 74.97
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 72.24
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 61.33
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 62.35
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 165.02
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 165.48
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 168.25
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | Benefits OH | Not assigned | 002/2021 | 29.96
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | Benefits OH | Not assigned | 003/2021 | 142.21
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.14
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 25.71
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 27.41
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 137.06
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 16.86
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 84.31
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | IT Device OH | Not assigned | 002/2021 | 2.92
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | IT Device OH | Not assigned | 003/2021 | 14.59
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 22.84
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 114.21
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.12
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 50.6
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 36204.87
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 47.79
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 73.43
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 73.43
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 121.2
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 198.14
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 198.14
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Contract | Construction Inspection | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 3465.6
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 90391.9
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -40815.18
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 003/2021 | -0.01
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -3439
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | 3439
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 3.53
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 10.4
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 2.09
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 92.9
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 130.89
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 104.21
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 240.42
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 353.2
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 281.21
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Other | Benefits OH | Not assigned | 002/2021 | 4.19
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.72
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 3.83
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 2.36
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Other | IT Device OH | Not assigned | 002/2021 | 0.41
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 3.19
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 1.42
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 105746.23
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -41764.37
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -362
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 112.16
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 157.79
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 124.9
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 290.59
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 425.79
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 337.04
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 246
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.25
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.74
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.15
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 160.12
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 135.99
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 135.99
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 366.49
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 366.95
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 366.95
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | Other | Benefits OH | Not assigned | 001/2021 | 0.3
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.05
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 0.27
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.17
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | Other | IT Device OH | Not assigned | 001/2021 | 0.03
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.23
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.1
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Contract | Contracts | CANUS CORPORATION | 001/2021 | 589.06
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 861
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1.47
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Labor Internal | Mapping | Not assigned | 001/2021 | 4.35
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.88
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 145.21
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 124.67
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 124.67
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 333.49
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 336.42
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 336.42
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Other | Benefits OH | Not assigned | 001/2021 | 1.76
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.3
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 1.6
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.98
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Other | IT Device OH | Not assigned | 001/2021 | 0.17
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1.33
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.59
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -3077
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | 3077
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 4.91
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4.26
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 6.53
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 11.5
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 11.5
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 17.62
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 5936.38
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Labor Internal | Administration | Not assigned | 001/2021 | 139.28
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | -36.22
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -6.24
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 49.21
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Labor Internal | Mapping | Not assigned | 001/2021 | 17.81
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 24.35
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 228.5
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 199.34
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 199.34
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 524.62
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 537.9
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 537.9
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Other | Benefits OH | Not assigned | 001/2021 | 40.33
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Other | Building Service Overhead | Not assigned | 001/2021 | 6.92
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Other | Capitalized A&G | Not assigned | 001/2021 | 44.5
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Other | Fleet OH - Elec | Not assigned | 001/2021 | -4.17
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Other | IT Device OH | Not assigned | 001/2021 | 3.94
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -5.65
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 29.47
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 13.62
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 2086.92
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Labor Internal | Administration | Not assigned | 001/2021 | 139.28
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 2.12
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 49.21
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Labor Internal | Mapping | Not assigned | 001/2021 | 6.26
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 29.31
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 31.89
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 29.52
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 29.52
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Other | AFUDC-Equity | Not assigned | 001/2021 | 74.72
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Other | AFUDC-Equity | Not assigned | 002/2021 | 79.66
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 79.66
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Other | Benefits OH | Not assigned | 001/2021 | 50.25
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Other | Building Service Overhead | Not assigned | 001/2021 | 8.62
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Other | Capitalized A&G | Not assigned | 001/2021 | 53.58
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1.42
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Other | IT Device OH | Not assigned | 001/2021 | 4.9
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1.92
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 29.47
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 16.98
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 123684.11
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -51814.62
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -7240
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | 4163
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 110.36
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 162.89
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 125.36
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | Other | AFUDC-Equity | Not assigned | 001/2021 | 293.36
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | Other | AFUDC-Equity | Not assigned | 002/2021 | 439.54
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | Other | AFUDC-Equity | Not assigned | 003/2021 | 338.28
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 73541.45
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -30374.09
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | -70.32
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -23.84
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | -14.16
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 74.85
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 106.02
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 82.1
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | Other | AFUDC-Equity | Not assigned | 001/2021 | 194.82
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | Other | AFUDC-Equity | Not assigned | 002/2021 | 286.09
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | Other | AFUDC-Equity | Not assigned | 003/2021 | 221.54
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | Other | Benefits OH | Not assigned | 001/2021 | -28.31
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | Other | Building Service Overhead | Not assigned | 001/2021 | -4.86
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | Other | Capitalized A&G | Not assigned | 001/2021 | -25.89
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | Other | Fleet OH - Elec | Not assigned | 001/2021 | -15.93
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | Other | IT Device OH | Not assigned | 001/2021 | -2.76
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -21.57
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | Other | Payroll Taxes OH | Not assigned | 001/2021 | -9.56
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 31581.44
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 291.83
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 277.29
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 277.29
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 681.12
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 748.23
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 748.23
35129944 | SILVERADO 2105 - DIST.UNDERBUILD RECON | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 128.28
35129944 | SILVERADO 2105 - DIST.UNDERBUILD RECON | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 108.56
35129944 | SILVERADO 2105 - DIST.UNDERBUILD RECON | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 108.56
35129944 | SILVERADO 2105 - DIST.UNDERBUILD RECON | Other | AFUDC-Equity | Not assigned | 001/2021 | 292.93
35129944 | SILVERADO 2105 - DIST.UNDERBUILD RECON | Other | AFUDC-Equity | Not assigned | 002/2021 | 292.93
35129944 | SILVERADO 2105 - DIST.UNDERBUILD RECON | Other | AFUDC-Equity | Not assigned | 003/2021 | 292.93
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 372.25
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 25.24
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 126.19
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.99
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 74.97
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Other | Benefits OH | Not assigned | 002/2021 | 29.96
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Other | Benefits OH | Not assigned | 003/2021 | 142.21
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Other | Building Service Overhead | Not assigned | 002/2021 | 5.14
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Other | Building Service Overhead | Not assigned | 003/2021 | 25.71
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Other | Capitalized A&G | Not assigned | 002/2021 | 27.41
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Other | Capitalized A&G | Not assigned | 003/2021 | 137.06
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Other | Fleet OH - Elec | Not assigned | 002/2021 | 16.86
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Other | Fleet OH - Elec | Not assigned | 003/2021 | 84.31
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Other | IT Device OH | Not assigned | 002/2021 | 2.92
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Other | IT Device OH | Not assigned | 003/2021 | 14.59
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 22.84
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 114.21
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.12
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | Other | Payroll Taxes OH | Not assigned | 003/2021 | 50.6
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 119.74
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -119.74
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 1300.68
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 190
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Administration | Not assigned | 002/2021 | 417.84
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Administration | Not assigned | 003/2021 | 348.2
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 4736.8
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 1065.78
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 1701.96
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 218.2
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 372.26
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 411.59
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 208.92
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Environmental Services | Not assigned | 003/2021 | 17.41
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 50.48
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 2536.08
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 828.7
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 147.62
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 202.98
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Mapping | Not assigned | 003/2021 | 4.47
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 29.99
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1590.84
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 614.65
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Project Management Services | Not assigned | 001/2021 | 148.9
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Project Management Services | Not assigned | 002/2021 | 670.05
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 744.5
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Benefits OH | Not assigned | 001/2021 | 59.91
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Benefits OH | Not assigned | 002/2021 | 3153.21
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Benefits OH | Not assigned | 003/2021 | 1129.76
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Building Service Overhead | Not assigned | 001/2021 | 10.28
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Building Service Overhead | Not assigned | 002/2021 | 541.17
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Building Service Overhead | Not assigned | 003/2021 | 204.21
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Capitalized A&G | Not assigned | 001/2021 | 54.82
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Capitalized A&G | Not assigned | 002/2021 | 2908.38
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Capitalized A&G | Not assigned | 003/2021 | 1123.71
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 33.73
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1694.46
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 553.68
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | IT Device OH | Not assigned | 001/2021 | 5.83
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | IT Device OH | Not assigned | 002/2021 | 307.15
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | IT Device OH | Not assigned | 003/2021 | 115.9
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 45.68
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 2295.19
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 749.99
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 88.41
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 121.57
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 20.24
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 1065.32
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 401.94
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 119.74
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -119.74
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 95
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 1539.47
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 7460.49
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 7164.43
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Electric Estimating | Not assigned | 004/2021 | 524.4
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Electric Estimating Doubletime | Not assigned | 002/2021 | 59.2
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 610.96
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 916.44
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Electric Estimating Overtime | Not assigned | 004/2021 | 410.37
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 525.38
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 372.26
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 572.36
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 3136.3
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 3017.14
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 240.39
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 550.8
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 129.6
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.29
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 340.04
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1863.28
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1936.13
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Project Management Services | Not assigned | 001/2021 | 148.9
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Project Management Services | Not assigned | 002/2021 | 595.6
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 446.7
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | Benefits OH | Not assigned | 001/2021 | 679.32
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | Benefits OH | Not assigned | 002/2021 | 3722.4
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | Benefits OH | Not assigned | 003/2021 | 3630.62
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | Building Service Overhead | Not assigned | 001/2021 | 116.58
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | Building Service Overhead | Not assigned | 002/2021 | 638.87
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | Building Service Overhead | Not assigned | 003/2021 | 656.22
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | Capitalized A&G | Not assigned | 001/2021 | 621.65
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | Capitalized A&G | Not assigned | 002/2021 | 3406.45
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | Capitalized A&G | Not assigned | 003/2021 | 3539.63
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 382.42
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 2095.49
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 2015.88
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | IT Device OH | Not assigned | 001/2021 | 66.17
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | IT Device OH | Not assigned | 002/2021 | 362.58
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | IT Device OH | Not assigned | 003/2021 | 372.44
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 517.99
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 2838.41
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 2730.57
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 143.97
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 229.51
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 1257.62
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 1291.74
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 119.74
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -119.74
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 23.75
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Administration | Not assigned | 003/2021 | 278.56
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 97.82
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 2590.44
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 11072.27
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 414.58
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 3513.02
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 372.26
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.46
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 208.92
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 50.48
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1473.01
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 5045.4
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 206.79
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.07
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 29.99
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 875.11
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 3121.95
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Project Management Services | Not assigned | 001/2021 | 148.9
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Project Management Services | Not assigned | 002/2021 | 967.85
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 223.35
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | Benefits OH | Not assigned | 001/2021 | 59.91
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | Benefits OH | Not assigned | 002/2021 | 1748.29
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | Benefits OH | Not assigned | 003/2021 | 5885.54
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | Building Service Overhead | Not assigned | 001/2021 | 10.28
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | Building Service Overhead | Not assigned | 002/2021 | 300.07
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | Building Service Overhead | Not assigned | 003/2021 | 1063.76
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | Capitalized A&G | Not assigned | 001/2021 | 54.82
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | Capitalized A&G | Not assigned | 002/2021 | 1599.88
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | Capitalized A&G | Not assigned | 003/2021 | 5707.57
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 33.73
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 984.17
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 3371.03
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | IT Device OH | Not assigned | 001/2021 | 5.83
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | IT Device OH | Not assigned | 002/2021 | 170.32
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | IT Device OH | Not assigned | 003/2021 | 603.76
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 45.68
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1333.09
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 4566.16
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 123.85
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 20.24
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 590.68
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 2094.06
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 335.03
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 50.48
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 290.25
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 29.99
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 172.43
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Labor Internal | Project Management Services | Not assigned | 001/2021 | 148.9
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Labor Internal | Project Management Services | Not assigned | 002/2021 | 521.15
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Other | Benefits OH | Not assigned | 001/2021 | 59.91
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Other | Benefits OH | Not assigned | 002/2021 | 344.49
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Other | Building Service Overhead | Not assigned | 001/2021 | 10.28
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Other | Building Service Overhead | Not assigned | 002/2021 | 59.13
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Other | Capitalized A&G | Not assigned | 001/2021 | 54.82
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Other | Capitalized A&G | Not assigned | 002/2021 | 315.25
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 33.73
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 193.92
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Other | IT Device OH | Not assigned | 001/2021 | 5.83
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Other | IT Device OH | Not assigned | 002/2021 | 33.55
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 45.68
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 262.68
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 20.24
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 116.37
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Contract | Construction Inspection | CANUS CORPORATION | 003/2021 | 1026.32
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Contract | Contracts | CANUS CORPORATION | 004/2021 | 1095.27
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Contract | Contracts | NOR CAL PIPELINE SERVICES | 003/2021 | 2725
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Contract | Electric Construction Contract | SILLER CONSTRUCTION CO | 003/2021 | 28677.67
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Contract | Electric Construction Contract | SILLER CONSTRUCTION CO | 004/2021 | 2189.65
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Contract | Traffic Control Contracts | ROAD SAFETY INC | 001/2021 | 5452
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Contract | Traffic Control Contracts | ROAD SAFETY INC | 002/2021 | 1931
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Contract | Traffic Control Contracts | ROAD SAFETY INC | 003/2021 | 8256
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Contract | Traffic Control Contracts | ROAD SAFETY INC | 004/2021 | -372
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 95
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Administration | Not assigned | 003/2021 | 69.64
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Analyst Services | Not assigned | 001/2021 | 55.69
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Construction | Not assigned | 001/2021 | 43200.76
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Construction | Not assigned | 002/2021 | 27937.4
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Construction | Not assigned | 003/2021 | 40781.79
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Construction | Not assigned | 004/2021 | 2725.6
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Construction Doubletime Services | Not assigned | 002/2021 | 8411.1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Construction Doubletime Services | Not assigned | 003/2021 | 3023.24
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 6112.34
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 8744.79
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 23512.42
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Design Services Double Time | Not assigned | 001/2021 | 5.1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 769.74
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 414.47
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 153.12
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 525.38
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 17182.27
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 15449.45
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 23377.61
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 19.68
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 24.6
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Mapping | Not assigned | 001/2021 | 444.11
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Mapping | Not assigned | 002/2021 | 405.84
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Mapping | Not assigned | 003/2021 | 703.15
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 10219.22
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 9178.52
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 13902.66
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Materials | Material Burden | Not assigned | 002/2021 | 251.59
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Materials | Material Burden | Not assigned | 003/2021 | 200.58
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 1723.19
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 1373.86
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1799.8
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1777.36
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2077.79
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 4177.72
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 4796.05
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 5606.75
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Benefits OH | Not assigned | 001/2021 | 20412.31
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Benefits OH | Not assigned | 002/2021 | 18385.39
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Benefits OH | Not assigned | 003/2021 | 26406.58
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Building Service Overhead | Not assigned | 001/2021 | 3503.29
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Building Service Overhead | Not assigned | 002/2021 | 3155.42
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Building Service Overhead | Not assigned | 003/2021 | 4772.79
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Capitalized A&G | Not assigned | 001/2021 | 18682.79
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Capitalized A&G | Not assigned | 002/2021 | 16780.19
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Capitalized A&G | Not assigned | 003/2021 | 25416.89
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Cash Discount earned | ROAD SAFETY INC | 001/2021 | -18.36
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Cash Discount earned | ROAD SAFETY INC | 002/2021 | -109.04
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Cash Discount earned | ROAD SAFETY INC | 003/2021 | -109.82
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Cash Discount earned | STELLA-JONES CORPORATION | 002/2021 | -284.78
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 11480.2
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 10322.41
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 15619.55
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | IT Device OH | Not assigned | 001/2021 | 1988.35
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | IT Device OH | Not assigned | 002/2021 | 1790.91
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | IT Device OH | Not assigned | 003/2021 | 2708.87
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Minor Material OH | Not assigned | 002/2021 | 140.41
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Minor Material OH | Not assigned | 003/2021 | 111.94
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 15550.21
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 13981.97
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 21157.08
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 11.78
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 14.74
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Other Land Fees | RICHARD SCHLUTER | 003/2021 | 5250
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 6896.36
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 6211.55
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 9395.38
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 64.8
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 22.89
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 13.05
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 789.82
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 669.35
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 669.55
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1805.81
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1806.17
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1806.73
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Other | Benefits OH | Not assigned | 002/2021 | 22.21
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Other | Building Service Overhead | Not assigned | 002/2021 | 3.82
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Other | Capitalized A&G | Not assigned | 002/2021 | 23.86
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Other | IT Device OH | Not assigned | 002/2021 | 2.16
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Other | Land Acquisition Services | INTERWEST CONSULTING GROUP INC | 003/2021 | 60
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Other | Land Acquisition Services | INTERWEST CONSULTING GROUP INC | 004/2021 | -20
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 13.71
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Other | Other Land Fees | CORPORATION SERVICE COMPANY | 003/2021 | 36.5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 7.5
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Contract | Contracts | MOUNTAIN G ENTERPRISES INC | 001/2021 | 4462.92
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 297.8
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 4.54
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 25.24
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 100.95
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Labor Internal | Mapping | Not assigned | 001/2021 | 13.39
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 2.7
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.99
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 59.98
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 580.99
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 496.77
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 497.64
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1330.79
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1340.49
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1342.83
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | Benefits OH | Not assigned | 001/2021 | 5.39
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | Benefits OH | Not assigned | 002/2021 | 29.96
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | Benefits OH | Not assigned | 003/2021 | 113.77
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.93
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.14
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | Building Service Overhead | Not assigned | 003/2021 | 20.57
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | Capitalized A&G | Not assigned | 001/2021 | 4.93
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | Capitalized A&G | Not assigned | 002/2021 | 27.41
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | Capitalized A&G | Not assigned | 003/2021 | 109.65
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 3.03
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 16.86
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 67.45
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | IT Device OH | Not assigned | 001/2021 | 0.52
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | IT Device OH | Not assigned | 002/2021 | 2.92
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | IT Device OH | Not assigned | 003/2021 | 11.67
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 4.11
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 22.84
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 91.37
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 1.82
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.12
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 40.48
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 5208.85
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 51.48
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Contract | Environmental Contract | FAR WESTERN ANTHROPOLOGICAL | 002/2021 | 312.77
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 18380
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Account Services | Not assigned | 002/2021 | 49.22
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Construction | Not assigned | 002/2021 | 409.48
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 207.24
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 372.25
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 409.48
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 174.1
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Field Services | Not assigned | 003/2021 | 28.55
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 12.74
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 201.74
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 165.67
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 138.9
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 61.51
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 45.79
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 10.33
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 129.6
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Mapping | Not assigned | 001/2021 | 15.63
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Mapping | Not assigned | 002/2021 | 4.78
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.26
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 154.93
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 134.44
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 88.27
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 366.43
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 335.05
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 352.43
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 844.12
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 904.11
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 951.01
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Benefits OH | Not assigned | 001/2021 | 299.12
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Benefits OH | Not assigned | 002/2021 | 254.99
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Benefits OH | Not assigned | 003/2021 | 169.32
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Building Service Overhead | Not assigned | 001/2021 | 51.35
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Building Service Overhead | Not assigned | 002/2021 | 43.76
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Building Service Overhead | Not assigned | 003/2021 | 30.6
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Capitalized A&G | Not assigned | 001/2021 | 283.22
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Capitalized A&G | Not assigned | 002/2021 | 245.78
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Capitalized A&G | Not assigned | 003/2021 | 161.38
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 134.79
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 110.69
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 92.81
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 8.84
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | IT Device OH | Not assigned | 001/2021 | 29.16
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | IT Device OH | Not assigned | 002/2021 | 24.83
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | IT Device OH | Not assigned | 003/2021 | 17.37
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 182.59
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 149.94
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 125.71
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 36.84
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 27.42
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 15.84
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 101.06
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 86.16
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 60.24
35144943 | PSPS - ROB ROY 2105 - CB | Contract | Construction Inspection | CANUS CORPORATION | 003/2021 | 683
35144943 | PSPS - ROB ROY 2105 - CB | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 2893.66
35144943 | PSPS - ROB ROY 2105 - CB | Contract | Environmental Contract | FAR WESTERN ANTHROPOLOGICAL | 002/2021 | 150.17
35144943 | PSPS - ROB ROY 2105 - CB | Labor Internal | Design Overtime Services | Not assigned | 001/2021 | 4.24
35144943 | PSPS - ROB ROY 2105 - CB | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 446.7
35144943 | PSPS - ROB ROY 2105 - CB | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 632.83
35144943 | PSPS - ROB ROY 2105 - CB | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.45
35144943 | PSPS - ROB ROY 2105 - CB | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 69.64
35144943 | PSPS - ROB ROY 2105 - CB | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 155.81
35144943 | PSPS - ROB ROY 2105 - CB | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 214.68
35144943 | PSPS - ROB ROY 2105 - CB | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.93
35144943 | PSPS - ROB ROY 2105 - CB | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 24.6
35144943 | PSPS - ROB ROY 2105 - CB | Labor Internal | Mapping | Not assigned | 001/2021 | 8.68
35144943 | PSPS - ROB ROY 2105 - CB | Labor Internal | Mapping | Not assigned | 002/2021 | 0.45
35144943 | PSPS - ROB ROY 2105 - CB | Labor Internal | Mapping | Not assigned | 003/2021 | 2.05
35144943 | PSPS - ROB ROY 2105 - CB | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 106.59
35144943 | PSPS - ROB ROY 2105 - CB | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 127.54
35144943 | PSPS - ROB ROY 2105 - CB | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 15.4
35144943 | PSPS - ROB ROY 2105 - CB | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 189.99
35144943 | PSPS - ROB ROY 2105 - CB | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 166.66
35144943 | PSPS - ROB ROY 2105 - CB | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 168.58
35144943 | PSPS - ROB ROY 2105 - CB | Other | AFUDC-Equity | Not assigned | 001/2021 | 435.69
35144943 | PSPS - ROB ROY 2105 - CB | Other | AFUDC-Equity | Not assigned | 002/2021 | 449.73
35144943 | PSPS - ROB ROY 2105 - CB | Other | AFUDC-Equity | Not assigned | 003/2021 | 454.91
35144943 | PSPS - ROB ROY 2105 - CB | Other | Benefits OH | Not assigned | 001/2021 | 208.8
35144943 | PSPS - ROB ROY 2105 - CB | Other | Benefits OH | Not assigned | 002/2021 | 254.79
35144943 | PSPS - ROB ROY 2105 - CB | Other | Benefits OH | Not assigned | 003/2021 | 29.22
35144943 | PSPS - ROB ROY 2105 - CB | Other | Building Service Overhead | Not assigned | 001/2021 | 35.83
35144943 | PSPS - ROB ROY 2105 - CB | Other | Building Service Overhead | Not assigned | 002/2021 | 43.73
35144943 | PSPS - ROB ROY 2105 - CB | Other | Building Service Overhead | Not assigned | 003/2021 | 5.28
35144943 | PSPS - ROB ROY 2105 - CB | Other | Capitalized A&G | Not assigned | 001/2021 | 194.88
35144943 | PSPS - ROB ROY 2105 - CB | Other | Capitalized A&G | Not assigned | 002/2021 | 233.18
35144943 | PSPS - ROB ROY 2105 - CB | Other | Capitalized A&G | Not assigned | 003/2021 | 28.16
35144943 | PSPS - ROB ROY 2105 - CB | Other | Fleet OH - Elec | Not assigned | 001/2021 | 104.11
35144943 | PSPS - ROB ROY 2105 - CB | Other | Fleet OH - Elec | Not assigned | 002/2021 | 143.44
35144943 | PSPS - ROB ROY 2105 - CB | Other | Fleet OH - Elec | Not assigned | 003/2021 | 17.32
35144943 | PSPS - ROB ROY 2105 - CB | Other | IT Device OH | Not assigned | 001/2021 | 20.33
35144943 | PSPS - ROB ROY 2105 - CB | Other | IT Device OH | Not assigned | 002/2021 | 24.82
35144943 | PSPS - ROB ROY 2105 - CB | Other | IT Device OH | Not assigned | 003/2021 | 3
35144943 | PSPS - ROB ROY 2105 - CB | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 141.02
35144943 | PSPS - ROB ROY 2105 - CB | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 194.29
35144943 | PSPS - ROB ROY 2105 - CB | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 23.47
35144943 | PSPS - ROB ROY 2105 - CB | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 14.74
35144943 | PSPS - ROB ROY 2105 - CB | Other | Payroll Taxes OH | Not assigned | 001/2021 | 70.54
35144943 | PSPS - ROB ROY 2105 - CB | Other | Payroll Taxes OH | Not assigned | 002/2021 | 86.1
35144943 | PSPS - ROB ROY 2105 - CB | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.4
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Account Services | Not assigned | 001/2021 | 65.64
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Account Services | Not assigned | 002/2021 | 65.64
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Account Services | Not assigned | 003/2021 | 82.05
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Construction | Not assigned | 001/2021 | -128.38
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 221.74
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 74.45
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 409.48
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 409.48
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 69.64
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 16.99
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 16.99
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 21.24
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 57.17
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 138.81
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 138.81
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 24.6
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.84
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 47.18
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 95.69
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 113.02
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | Benefits OH | Not assigned | 001/2021 | 86.44
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | Benefits OH | Not assigned | 002/2021 | 183.34
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | Benefits OH | Not assigned | 003/2021 | 201.18
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | Building Service Overhead | Not assigned | 001/2021 | 14.84
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | Building Service Overhead | Not assigned | 002/2021 | 31.48
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | Building Service Overhead | Not assigned | 003/2021 | 36.37
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | Capitalized A&G | Not assigned | 001/2021 | 86.27
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | Capitalized A&G | Not assigned | 002/2021 | 174.94
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | Capitalized A&G | Not assigned | 003/2021 | 206.62
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 38.2
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 92.75
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 92.75
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | IT Device OH | Not assigned | 001/2021 | 8.41
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | IT Device OH | Not assigned | 002/2021 | 17.85
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | IT Device OH | Not assigned | 003/2021 | 20.63
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 51.74
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 125.63
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 125.63
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 14.74
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 29.21
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 61.95
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 71.59
35145001 | PSPS - CLAYTON 2215 - CB | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 2675.33
35145001 | PSPS - CLAYTON 2215 - CB | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 356.16
35145001 | PSPS - CLAYTON 2215 - CB | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 59.36
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Account Services | Not assigned | 003/2021 | 29.94
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Analyst Services | Not assigned | 002/2021 | 111.38
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Analyst Services | Not assigned | 003/2021 | 111.38
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Construction | Not assigned | 001/2021 | -135.22
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 221.74
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1191.2
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 002/2021 | 322.26
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 174.1
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 7.75
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 32.32
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 109.61
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 403.87
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 11.45
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 73.69
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 249.67
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 001/2021 | 32.4
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 97.2
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Manage L&EM | Not assigned | 003/2021 | 421.2
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Management Services | Not assigned | 001/2021 | 9.85
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Mapping | Not assigned | 001/2021 | 8.81
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Mapping | Not assigned | 002/2021 | 1.07
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Mapping | Not assigned | 003/2021 | 0.18
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 25.73
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 107.13
35145001 | PSPS - CLAYTON 2215 - CB | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 388.3
35145001 | PSPS - CLAYTON 2215 - CB | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 325.52
35145001 | PSPS - CLAYTON 2215 - CB | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 283.72
35145001 | PSPS - CLAYTON 2215 - CB | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 236.28
35145001 | PSPS - CLAYTON 2215 - CB | Other | AFUDC-Equity | Not assigned | 001/2021 | 754.55
35145001 | PSPS - CLAYTON 2215 - CB | Other | AFUDC-Equity | Not assigned | 002/2021 | 765.6
35145001 | PSPS - CLAYTON 2215 - CB | Other | AFUDC-Equity | Not assigned | 003/2021 | 637.58
35145001 | PSPS - CLAYTON 2215 - CB | Other | Benefits OH | Not assigned | 001/2021 | 52.38
35145001 | PSPS - CLAYTON 2215 - CB | Other | Benefits OH | Not assigned | 002/2021 | 201.56
35145001 | PSPS - CLAYTON 2215 - CB | Other | Benefits OH | Not assigned | 003/2021 | 693.19
35145001 | PSPS - CLAYTON 2215 - CB | Other | Building Service Overhead | Not assigned | 001/2021 | 8.99
35145001 | PSPS - CLAYTON 2215 - CB | Other | Building Service Overhead | Not assigned | 002/2021 | 34.6
35145001 | PSPS - CLAYTON 2215 - CB | Other | Building Service Overhead | Not assigned | 003/2021 | 125.3
35145001 | PSPS - CLAYTON 2215 - CB | Other | Capitalized A&G | Not assigned | 001/2021 | 50.66
35145001 | PSPS - CLAYTON 2215 - CB | Other | Capitalized A&G | Not assigned | 002/2021 | 195.85
35145001 | PSPS - CLAYTON 2215 - CB | Other | Capitalized A&G | Not assigned | 003/2021 | 709.89
35145001 | PSPS - CLAYTON 2215 - CB | Other | Cash Discount earned | TOWILL INC | 002/2021 | -249.53
35145001 | PSPS - CLAYTON 2215 - CB | Other | Fleet OH - Elec | Not assigned | 001/2021 | 23.83
35145001 | PSPS - CLAYTON 2215 - CB | Other | Fleet OH - Elec | Not assigned | 002/2021 | 73.23
35145001 | PSPS - CLAYTON 2215 - CB | Other | Fleet OH - Elec | Not assigned | 003/2021 | 269.85
35145001 | PSPS - CLAYTON 2215 - CB | Other | IT Device OH | Not assigned | 001/2021 | 5.11
35145001 | PSPS - CLAYTON 2215 - CB | Other | IT Device OH | Not assigned | 002/2021 | 19.65
35145001 | PSPS - CLAYTON 2215 - CB | Other | IT Device OH | Not assigned | 003/2021 | 71.1
35145001 | PSPS - CLAYTON 2215 - CB | Other | Land Acquisition Services | ASSOCIATED RIGHT OF WAY SVCS INC | 001/2021 | 115
35145001 | PSPS - CLAYTON 2215 - CB | Other | Land Acquisition Services | ASSOCIATED RIGHT OF WAY SVCS INC | 002/2021 | 335.63
35145001 | PSPS - CLAYTON 2215 - CB | Other | Land Acquisition Services | ASSOCIATED RIGHT OF WAY SVCS INC | 003/2021 | 451.55
35145001 | PSPS - CLAYTON 2215 - CB | Other | Land Acquisition Services | ASSOCIATED RIGHT OF WAY SVCS INC | 004/2021 | -566.3
35145001 | PSPS - CLAYTON 2215 - CB | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 32.26
35145001 | PSPS - CLAYTON 2215 - CB | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 99.2
35145001 | PSPS - CLAYTON 2215 - CB | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 365.53
35145001 | PSPS - CLAYTON 2215 - CB | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 6.86
35145001 | PSPS - CLAYTON 2215 - CB | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 44.14
35145001 | PSPS - CLAYTON 2215 - CB | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 149.53
35145001 | PSPS - CLAYTON 2215 - CB | Other | Other Land Fees | CITY OF WALNUT CREEK | 003/2021 | 10500
35145001 | PSPS - CLAYTON 2215 - CB | Other | Payroll Taxes OH | Not assigned | 001/2021 | 17.7
35145001 | PSPS - CLAYTON 2215 - CB | Other | Payroll Taxes OH | Not assigned | 002/2021 | 68.13
35145001 | PSPS - CLAYTON 2215 - CB | Other | Payroll Taxes OH | Not assigned | 003/2021 | 246.66
35145002 | PSPS - IGNACIO 1101 - CB | Labor External | Consulting Services - Other | MOTIVE POWER INC | 001/2021 | 454.12
35145002 | PSPS - IGNACIO 1101 - CB | Labor External | Consulting Services - Other | MOTIVE POWER INC | 003/2021 | 454.12
35145002 | PSPS - IGNACIO 1101 - CB | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 1.06
35145002 | PSPS - IGNACIO 1101 - CB | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35145002 | PSPS - IGNACIO 1101 - CB | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.45
35145002 | PSPS - IGNACIO 1101 - CB | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.36
35145002 | PSPS - IGNACIO 1101 - CB | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 25.24
35145002 | PSPS - IGNACIO 1101 - CB | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.24
35145002 | PSPS - IGNACIO 1101 - CB | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 0.21
35145002 | PSPS - IGNACIO 1101 - CB | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.99
35145002 | PSPS - IGNACIO 1101 - CB | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 14.99
35145002 | PSPS - IGNACIO 1101 - CB | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 222.57
35145002 | PSPS - IGNACIO 1101 - CB | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 189.04
35145002 | PSPS - IGNACIO 1101 - CB | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 189.12
35145002 | PSPS - IGNACIO 1101 - CB | Other | AFUDC-Equity | Not assigned | 001/2021 | 508.65
35145002 | PSPS - IGNACIO 1101 - CB | Other | AFUDC-Equity | Not assigned | 002/2021 | 510.11
35145002 | PSPS - IGNACIO 1101 - CB | Other | AFUDC-Equity | Not assigned | 003/2021 | 510.32
35145002 | PSPS - IGNACIO 1101 - CB | Other | Benefits OH | Not assigned | 001/2021 | 0.43
35145002 | PSPS - IGNACIO 1101 - CB | Other | Benefits OH | Not assigned | 002/2021 | 29.96
35145002 | PSPS - IGNACIO 1101 - CB | Other | Benefits OH | Not assigned | 003/2021 | 28.44
35145002 | PSPS - IGNACIO 1101 - CB | Other | Building Service Overhead | Not assigned | 001/2021 | 0.08
35145002 | PSPS - IGNACIO 1101 - CB | Other | Building Service Overhead | Not assigned | 002/2021 | 5.14
35145002 | PSPS - IGNACIO 1101 - CB | Other | Building Service Overhead | Not assigned | 003/2021 | 5.14
35145002 | PSPS - IGNACIO 1101 - CB | Other | Capitalized A&G | Not assigned | 001/2021 | 0.39
35145002 | PSPS - IGNACIO 1101 - CB | Other | Capitalized A&G | Not assigned | 002/2021 | 27.41
35145002 | PSPS - IGNACIO 1101 - CB | Other | Capitalized A&G | Not assigned | 003/2021 | 27.41
35145002 | PSPS - IGNACIO 1101 - CB | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.24
35145002 | PSPS - IGNACIO 1101 - CB | Other | Fleet OH - Elec | Not assigned | 002/2021 | 16.86
35145002 | PSPS - IGNACIO 1101 - CB | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.86
35145002 | PSPS - IGNACIO 1101 - CB | Other | IT Device OH | Not assigned | 001/2021 | 0.04
35145002 | PSPS - IGNACIO 1101 - CB | Other | IT Device OH | Not assigned | 002/2021 | 2.92
35145002 | PSPS - IGNACIO 1101 - CB | Other | IT Device OH | Not assigned | 003/2021 | 2.92
35145002 | PSPS - IGNACIO 1101 - CB | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.33
35145002 | PSPS - IGNACIO 1101 - CB | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 22.84
35145002 | PSPS - IGNACIO 1101 - CB | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 22.84
35145002 | PSPS - IGNACIO 1101 - CB | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.14
35145002 | PSPS - IGNACIO 1101 - CB | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.12
35145002 | PSPS - IGNACIO 1101 - CB | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.12
35145003 | PSPS CWSP - MORAGA 1103 - CB | Labor Internal | Construction | Not assigned | 001/2021 | -169.03
35145003 | PSPS CWSP - MORAGA 1103 - CB | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 277.18
35145003 | PSPS CWSP - MORAGA 1103 - CB | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 74.45
35145003 | PSPS CWSP - MORAGA 1103 - CB | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 409.48
35145003 | PSPS CWSP - MORAGA 1103 - CB | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 409.48
35145003 | PSPS CWSP - MORAGA 1103 - CB | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 62.23
35145003 | PSPS CWSP - MORAGA 1103 - CB | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 138.81
35145003 | PSPS CWSP - MORAGA 1103 - CB | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 138.81
35145003 | PSPS CWSP - MORAGA 1103 - CB | Labor Internal | Mapping | Not assigned | 001/2021 | 0.97
35145003 | PSPS CWSP - MORAGA 1103 - CB | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 36.97
35145003 | PSPS CWSP - MORAGA 1103 - CB | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 82.47
35145003 | PSPS CWSP - MORAGA 1103 - CB | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 82.47
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 173.2
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 147.78
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 151.75
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | AFUDC-Equity | Not assigned | 001/2021 | 395
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | AFUDC-Equity | Not assigned | 002/2021 | 398.76
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | AFUDC-Equity | Not assigned | 003/2021 | 409.5
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | Benefits OH | Not assigned | 001/2021 | 73.87
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | Benefits OH | Not assigned | 002/2021 | 164.75
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | Benefits OH | Not assigned | 003/2021 | 156.45
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | Building Service Overhead | Not assigned | 001/2021 | 12.67
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | Building Service Overhead | Not assigned | 002/2021 | 28.28
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | Building Service Overhead | Not assigned | 003/2021 | 28.28
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | Capitalized A&G | Not assigned | 001/2021 | 67.59
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | Capitalized A&G | Not assigned | 002/2021 | 150.77
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | Capitalized A&G | Not assigned | 003/2021 | 150.77
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | Fleet OH - Elec | Not assigned | 001/2021 | 41.58
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | Fleet OH - Elec | Not assigned | 002/2021 | 92.75
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | Fleet OH - Elec | Not assigned | 003/2021 | 92.75
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | IT Device OH | Not assigned | 001/2021 | 7.19
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | IT Device OH | Not assigned | 002/2021 | 16.04
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | IT Device OH | Not assigned | 003/2021 | 16.04
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 56.32
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 125.63
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 125.63
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | Payroll Taxes OH | Not assigned | 001/2021 | 24.95
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | Payroll Taxes OH | Not assigned | 002/2021 | 55.67
35145003 | PSPS CWSP - MORAGA 1103 - CB | Other | Payroll Taxes OH | Not assigned | 003/2021 | 55.67
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Labor Internal | Construction | Not assigned | 001/2021 | -229.8
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Labor Internal | Construction | Not assigned | 002/2021 | 148.9
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 388.05
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 148.9
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 335.03
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 409.48
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 104.61
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 164.51
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 138.81
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 11.45
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 32.4
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Labor Internal | Mapping | Not assigned | 001/2021 | 1.42
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Labor Internal | Mapping | Not assigned | 002/2021 | 1.34
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 62.15
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 97.74
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 89
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 175.97
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 151.68
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 151.74
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | AFUDC-Equity | Not assigned | 001/2021 | 404.07
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | AFUDC-Equity | Not assigned | 002/2021 | 409.28
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | AFUDC-Equity | Not assigned | 003/2021 | 409.45
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | Benefits OH | Not assigned | 001/2021 | 124.16
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | Benefits OH | Not assigned | 002/2021 | 195.24
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | Benefits OH | Not assigned | 003/2021 | 167
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | Building Service Overhead | Not assigned | 001/2021 | 21.32
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | Building Service Overhead | Not assigned | 002/2021 | 33.51
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | Building Service Overhead | Not assigned | 003/2021 | 30.19
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | Capitalized A&G | Not assigned | 001/2021 | 113.61
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | Capitalized A&G | Not assigned | 002/2021 | 178.67
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | Capitalized A&G | Not assigned | 003/2021 | 162.7
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | Fleet OH - Elec | Not assigned | 001/2021 | 69.89
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | Fleet OH - Elec | Not assigned | 002/2021 | 109.91
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | Fleet OH - Elec | Not assigned | 003/2021 | 92.75
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | IT Device OH | Not assigned | 001/2021 | 12.09
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | IT Device OH | Not assigned | 002/2021 | 19
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | IT Device OH | Not assigned | 003/2021 | 17.12
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 94.68
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 148.88
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 125.63
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 6.86
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | Payroll Taxes OH | Not assigned | 001/2021 | 41.94
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | Payroll Taxes OH | Not assigned | 002/2021 | 65.96
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Other | Payroll Taxes OH | Not assigned | 003/2021 | 59.43
35145005 | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 40.31
35145005 | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 34.09
35145005 | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 34.09
35145005 | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 92
35145005 | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 92
35145005 | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 92
35145006 | PSPS - STAFFORD 1101 LR 1298 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 886.11
35145006 | PSPS - STAFFORD 1101 LR 1298 | Labor Internal | Account Services | Not assigned | 002/2021 | 65.64
35145006 | PSPS - STAFFORD 1101 LR 1298 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 74.45
35145006 | PSPS - STAFFORD 1101 LR 1298 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.45
35145006 | PSPS - STAFFORD 1101 LR 1298 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 16.99
35145006 | PSPS - STAFFORD 1101 LR 1298 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 26.14
35145006 | PSPS - STAFFORD 1101 LR 1298 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.24
35145006 | PSPS - STAFFORD 1101 LR 1298 | Labor Internal | Mapping | Not assigned | 001/2021 | 2.66
35145006 | PSPS - STAFFORD 1101 LR 1298 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 15.53
35145006 | PSPS - STAFFORD 1101 LR 1298 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 13.22
35145006 | PSPS - STAFFORD 1101 LR 1298 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 14.99
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 241.53
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 206.09
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 204.77
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | AFUDC-Equity | Not assigned | 001/2021 | 553.41
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | AFUDC-Equity | Not assigned | 002/2021 | 556.12
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | AFUDC-Equity | Not assigned | 003/2021 | 552.54
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | Benefits OH | Not assigned | 001/2021 | 31.03
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | Benefits OH | Not assigned | 002/2021 | 18.59
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | Benefits OH | Not assigned | 003/2021 | 28.44
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | Building Service Overhead | Not assigned | 001/2021 | 5.33
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | Building Service Overhead | Not assigned | 002/2021 | 3.2
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.14
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | Capitalized A&G | Not assigned | 001/2021 | 28.39
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | Capitalized A&G | Not assigned | 002/2021 | 24.17
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | Capitalized A&G | Not assigned | 003/2021 | 27.41
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 17.46
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.86
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | IT Device OH | Not assigned | 001/2021 | 3.02
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | IT Device OH | Not assigned | 002/2021 | 1.81
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | IT Device OH | Not assigned | 003/2021 | 2.92
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 23.66
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 22.84
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 10.49
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 6.28
35145006 | PSPS - STAFFORD 1101 LR 1298 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.12
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | INSIGHT GLOBAL LLC | 001/2021 | 1380.03
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 259.2
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Labor Internal | Administration | Not assigned | 001/2021 | 417.84
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Labor Internal | Administration | Not assigned | 002/2021 | 139.28
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 2.12
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.72
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 239.2
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 49.21
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 136.78
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 28.05
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 282.04
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 242.84
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 243.14
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | AFUDC-Equity | Not assigned | 001/2021 | 647.65
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | AFUDC-Equity | Not assigned | 002/2021 | 655.28
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | AFUDC-Equity | Not assigned | 003/2021 | 656.1
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | Benefits OH | Not assigned | 001/2021 | 232.86
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | Benefits OH | Not assigned | 002/2021 | 47.73
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | Building Service Overhead | Not assigned | 001/2021 | 39.97
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | Building Service Overhead | Not assigned | 002/2021 | 8.19
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | Capitalized A&G | Not assigned | 001/2021 | 250.07
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | Capitalized A&G | Not assigned | 002/2021 | 51.28
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | Fleet OH - Elec | Not assigned | 001/2021 | 0.48
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | IT Device OH | Not assigned | 001/2021 | 22.69
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | IT Device OH | Not assigned | 002/2021 | 4.65
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 0.65
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 143.26
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 29.47
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | Payroll Taxes OH | Not assigned | 001/2021 | 78.69
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | Payroll Taxes OH | Not assigned | 002/2021 | 16.13
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Other | Reimbursed Mileage Expense | DARYL S SATTELBERG | 002/2021 | 13.22
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Contract | Construction Management Contracts | TRC SOLUTIONS INC | 003/2021 | 13861.31
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Contract | Construction Management Contracts | TRC SOLUTIONS INC | 004/2021 | -13861.31
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 246
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 220.64
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 4277.18
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 500
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Account Services | Not assigned | 001/2021 | 16.41
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Account Services | Not assigned | 002/2021 | 310.57
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Account Services | Not assigned | 003/2021 | 213.32
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Administration | Not assigned | 002/2021 | 348.2
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Administration | Not assigned | 003/2021 | 69.64
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Analyst Services | Not assigned | 001/2021 | 250.62
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Analyst Services | Not assigned | 002/2021 | 362.02
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Analyst Services | Not assigned | 003/2021 | 306.32
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Construction | Not assigned | 003/2021 | 574.1
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 1.06
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 372.26
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 372.26
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 001/2021 | 150.95
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 69.64
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 104.46
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 4.25
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 80.41
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 55.23
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 682.74
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 529.14
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 284.23
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 88.55
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 275.53
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 169.73
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 207.7
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Management Services | Not assigned | 002/2021 | 42.3
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Mapping | Not assigned | 001/2021 | 0.74
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Mapping | Not assigned | 002/2021 | 0.66
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Mapping | Not assigned | 003/2021 | 19.49
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 459.4
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 533.98
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 424.21
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Project Management Overtime | Not assigned | 002/2021 | 443.48
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Project Management Services | Not assigned | 001/2021 | 1861.25
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Project Management Services | Not assigned | 002/2021 | 744.5
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Labor Internal | Project Management Services | Not assigned | 003/2021 | 446.7
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Materials | Chemicals,Cleaners,Compounds & Lab Suppl | Not assigned | 003/2021 | 75.14
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Materials | Conductors, Cable & Wire Connectors | Not assigned | 003/2021 | 2292.23
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Materials | Construction Supplies | Not assigned | 003/2021 | 101.04
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Materials | Electl & Electronic Equipment Component | Not assigned | 003/2021 | 3.47
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Materials | Electrical Specialties | Not assigned | 003/2021 | 2142.72
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Materials | Fabricated Structures | Not assigned | 003/2021 | 525.05
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Materials | Material Burden | Not assigned | 003/2021 | 1271.63
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 4059.12
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 003/2021 | 1.51
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 302.29
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 267.71
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 311.98
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | AFUDC-Equity | Not assigned | 001/2021 | 694.77
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | AFUDC-Equity | Not assigned | 002/2021 | 722.4
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | AFUDC-Equity | Not assigned | 003/2021 | 841.85
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Benefits OH | Not assigned | 001/2021 | 900.89
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Benefits OH | Not assigned | 002/2021 | 991.51
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Benefits OH | Not assigned | 003/2021 | 1025.15
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Building Service Overhead | Not assigned | 001/2021 | 154.62
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Building Service Overhead | Not assigned | 002/2021 | 170.14
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Building Service Overhead | Not assigned | 003/2021 | 185.3
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Capitalized A&G | Not assigned | 001/2021 | 839.87
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Capitalized A&G | Not assigned | 002/2021 | 991.79
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Capitalized A&G | Not assigned | 003/2021 | 775.54
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Encroachment Permit Fees | CITY OF HEALDSBURG | 003/2021 | 14408
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Encroachment Permit Fees | COUNTY OF SONOMA | 004/2021 | 14408
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Fleet OH - Elec | Not assigned | 001/2021 | 456.17
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Fleet OH - Elec | Not assigned | 002/2021 | 353.54
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Fleet OH - Elec | Not assigned | 003/2021 | 189.9
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Fleet OH - Gas | Not assigned | 003/2021 | 177.8
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | IT Device OH | Not assigned | 001/2021 | 87.73
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | IT Device OH | Not assigned | 002/2021 | 96.57
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | IT Device OH | Not assigned | 003/2021 | 105.18
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Minor Material OH | Not assigned | 003/2021 | 744.54
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 617.9
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 478.88
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 257.24
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 53.03
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 165.02
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 101.66
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 318.52
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Payroll Taxes OH | Not assigned | 001/2021 | 304.35
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Payroll Taxes OH | Not assigned | 002/2021 | 334.98
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Other | Payroll Taxes OH | Not assigned | 003/2021 | 364.73
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Contract | Construction Management Contracts | TRC SOLUTIONS INC | 003/2021 | 1540.15
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Contract | Construction Management Contracts | TRC SOLUTIONS INC | 004/2021 | -1540.15
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 307.5
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 644.04
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 252.37
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -252.37
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Contract | Environmental Contract | FAR WESTERN ANTHROPOLOGICAL | 002/2021 | 252.36
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 250
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -250
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Contract | Traffic Control Contracts | CITY RISE INC | 001/2021 | 1950
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Account Services | Not assigned | 001/2021 | 16.41
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Account Services | Not assigned | 002/2021 | 311.75
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Account Services | Not assigned | 003/2021 | 311.77
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 777.6
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Administration | Not assigned | 002/2021 | 348.2
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Analyst Services | Not assigned | 001/2021 | 139.23
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Analyst Services | Not assigned | 002/2021 | 83.54
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Analyst Services | Not assigned | 003/2021 | 194.93
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Electric Estimating | Not assigned | 001/2021 | -179.94
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 29.61
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 2.12
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 707.29
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 372.26
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 001/2021 | 176.1
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 69.64
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 34.82
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 4.25
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 80.71
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 80.72
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 504.5
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 617.52
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 238.36
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 49.19
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 177.13
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 355.9
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Mapping | Not assigned | 001/2021 | 0.92
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Mapping | Not assigned | 002/2021 | 0.76
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Mapping | Not assigned | 003/2021 | 3.44
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 331.06
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 530.62
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 407.28
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Project Management Overtime | Not assigned | 002/2021 | 443.48
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Project Management Services | Not assigned | 001/2021 | 1489
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Project Management Services | Not assigned | 002/2021 | 670.05
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Labor Internal | Project Management Services | Not assigned | 003/2021 | 297.8
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 274.78
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 244.7
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 255.86
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | AFUDC-Equity | Not assigned | 001/2021 | 632.04
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | AFUDC-Equity | Not assigned | 002/2021 | 660.3
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | AFUDC-Equity | Not assigned | 003/2021 | 690.42
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Benefits OH | Not assigned | 001/2021 | 651.13
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Benefits OH | Not assigned | 002/2021 | 993.06
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Benefits OH | Not assigned | 003/2021 | 680.29
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Building Service Overhead | Not assigned | 001/2021 | 111.74
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Building Service Overhead | Not assigned | 002/2021 | 170.44
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Building Service Overhead | Not assigned | 003/2021 | 122.95
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Capitalized A&G | Not assigned | 001/2021 | 605.26
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Capitalized A&G | Not assigned | 002/2021 | 970.11
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Capitalized A&G | Not assigned | 003/2021 | 744.58
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Fleet OH - Elec | Not assigned | 001/2021 | 337.08
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Fleet OH - Elec | Not assigned | 002/2021 | 412.59
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Fleet OH - Elec | Not assigned | 003/2021 | 159.26
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | IT Device OH | Not assigned | 001/2021 | 63.41
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | IT Device OH | Not assigned | 002/2021 | 96.73
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | IT Device OH | Not assigned | 003/2021 | 69.8
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 456.59
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 558.86
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 215.71
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 29.46
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 106.09
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 213.16
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Payroll Taxes OH | Not assigned | 001/2021 | 219.98
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Payroll Taxes OH | Not assigned | 002/2021 | 335.51
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Payroll Taxes OH | Not assigned | 003/2021 | 242.07
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Other | Permits/FeesLand Surveying Services | R.E.Y. ENGINEERS INC | 001/2021 | -0.03
35145540 | PSPS - FROGTOWN 1702 - CB | Contract | Contracts | BLAIR CHURCH & FLYNN CONSULTING | 001/2021 | 5000
35145540 | PSPS - FROGTOWN 1702 - CB | Contract | Contracts | BLAIR CHURCH & FLYNN CONSULTING | 002/2021 | -2500
35145540 | PSPS - FROGTOWN 1702 - CB | Contract | Contracts | BLAIR CHURCH & FLYNN CONSULTING | 003/2021 | -2500
35145540 | PSPS - FROGTOWN 1702 - CB | Contract | Contracts | MARIOS TREE SERVICE INC | 001/2021 | 472.8
35145540 | PSPS - FROGTOWN 1702 - CB | Contract | Contracts | MARIOS TREE SERVICE INC | 002/2021 | 14668.88
35145540 | PSPS - FROGTOWN 1702 - CB | Contract | Contracts | MARIOS TREE SERVICE INC | 003/2021 | 4395.95
35145540 | PSPS - FROGTOWN 1702 - CB | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SOHA ENGINEERS | 004/2021 | -200
35145540 | PSPS - FROGTOWN 1702 - CB | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 3535.45
35145540 | PSPS - FROGTOWN 1702 - CB | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 933.43
35145540 | PSPS - FROGTOWN 1702 - CB | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 348.98
35145540 | PSPS - FROGTOWN 1702 - CB | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | -348.98
35145540 | PSPS - FROGTOWN 1702 - CB | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 10340
35145540 | PSPS - FROGTOWN 1702 - CB | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 71.25
35145540 | PSPS - FROGTOWN 1702 - CB | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 001/2021 | 595.69
35145540 | PSPS - FROGTOWN 1702 - CB | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 002/2021 | 30
35145540 | PSPS - FROGTOWN 1702 - CB | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 003/2021 | 690.17
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 453.6
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Administration | Not assigned | 001/2021 | 663.78
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Administration | Not assigned | 002/2021 | 1659.46
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 374.05
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Construction | Not assigned | 002/2021 | 670.05
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Construction | Not assigned | 003/2021 | 326.2
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 167.57
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 37.23
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 104.46
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 10.19
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 254.81
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 126.83
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 197.17
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 246.62
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Indirect Labor - Gas | Not assigned | 002/2021 | 47.16
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 324
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Mapping | Not assigned | 001/2021 | 30.07
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Mapping | Not assigned | 002/2021 | 44.38
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Mapping | Not assigned | 003/2021 | 10.69
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 118.46
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 177.63
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 215.95
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Technical Services | Not assigned | 001/2021 | 4534.13
35145540 | PSPS - FROGTOWN 1702 - CB | Labor Internal | Technical Services | Not assigned | 002/2021 | 483.64
35145540 | PSPS - FROGTOWN 1702 - CB | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 341.07
35145540 | PSPS - FROGTOWN 1702 - CB | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 331.05
35145540 | PSPS - FROGTOWN 1702 - CB | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 357.05
35145540 | PSPS - FROGTOWN 1702 - CB | Other | AFUDC-Equity | Not assigned | 001/2021 | 791.41
35145540 | PSPS - FROGTOWN 1702 - CB | Other | AFUDC-Equity | Not assigned | 002/2021 | 893.31
35145540 | PSPS - FROGTOWN 1702 - CB | Other | AFUDC-Equity | Not assigned | 003/2021 | 963.46
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Benefits OH | Not assigned | 001/2021 | 1211.89
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Benefits OH | Not assigned | 002/2021 | 779.63
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Benefits OH | Not assigned | 003/2021 | 370.1
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Building Service Overhead | Not assigned | 001/2021 | 208.01
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Building Service Overhead | Not assigned | 002/2021 | 133.81
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Building Service Overhead | Not assigned | 003/2021 | 66.9
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Capitalized A&G | Not assigned | 001/2021 | 2130.42
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Capitalized A&G | Not assigned | 002/2021 | 1113.84
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Capitalized A&G | Not assigned | 003/2021 | 394.77
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Cash Discount earned | BLAIR CHURCH & FLYNN CONSULTING | 001/2021 | -23.06
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Fleet OH - Elec | Not assigned | 001/2021 | 6.81
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Fleet OH - Elec | Not assigned | 002/2021 | 170.26
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Fleet OH - Elec | Not assigned | 003/2021 | 84.74
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Fleet OH - Gas | Not assigned | 002/2021 | 40.37
35145540 | PSPS - FROGTOWN 1702 - CB | Other | IT Device OH | Not assigned | 001/2021 | 118.05
35145540 | PSPS - FROGTOWN 1702 - CB | Other | IT Device OH | Not assigned | 002/2021 | 75.94
35145540 | PSPS - FROGTOWN 1702 - CB | Other | IT Device OH | Not assigned | 003/2021 | 37.96
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 9.23
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 230.6
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 114.78
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 118.08
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 147.71
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 72.31
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Payroll Taxes OH | Not assigned | 001/2021 | 409.43
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Payroll Taxes OH | Not assigned | 002/2021 | 263.39
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Payroll Taxes OH | Not assigned | 003/2021 | 131.65
35145540 | PSPS - FROGTOWN 1702 - CB | Other | Permits/FeesLand Surveying Services | BLAIR CHURCH & FLYNN CONSULTING | 001/2021 | 1153
35155680 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.02 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.31
35155680 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.02 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.95
35155680 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.02 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.95
35155680 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.02 | Other | AFUDC-Equity | Not assigned | 001/2021 | 5.27
35155680 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.02 | Other | AFUDC-Equity | Not assigned | 002/2021 | 5.27
35155680 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.02 | Other | AFUDC-Equity | Not assigned | 003/2021 | 5.27
35155681 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.03 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1.41
35155681 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.03 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.19
35155681 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.03 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.19
35155681 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.03 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3.2
35155681 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.03 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3.2
35155681 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.03 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.2
35155682 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.04 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.93
35155682 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.04 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.79
35155682 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.04 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.79
35155682 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.04 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2.14
35155682 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.04 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2.14
35155682 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.04 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.14
35155683 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.05 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 4.15
35155683 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.05 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 3.51
35155683 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.05 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3.51
35155683 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.05 | Other | AFUDC-Equity | Not assigned | 001/2021 | 9.48
35155683 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.05 | Other | AFUDC-Equity | Not assigned | 002/2021 | 9.48
35155683 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.05 | Other | AFUDC-Equity | Not assigned | 003/2021 | 9.48
35155684 | CWSP-BRUNSWICK 1105 LR2140 - PH 1.06 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.93
35155684 | CWSP-BRUNSWICK 1105 LR2140 - PH 1.06 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.79
35155684 | CWSP-BRUNSWICK 1105 LR2140 - PH 1.06 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.79
35155684 | CWSP-BRUNSWICK 1105 LR2140 - PH 1.06 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2.14
35155684 | CWSP-BRUNSWICK 1105 LR2140 - PH 1.06 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2.14
35155684 | CWSP-BRUNSWICK 1105 LR2140 - PH 1.06 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.14
35155685 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.07 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.93
35155685 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.07 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.79
35155685 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.07 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.79
35155685 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.07 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2.14
35155685 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.07 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2.14
35155685 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.07 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.14
35155686 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.08 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.47
35155686 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.08 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.4
35155686 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.08 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.4
35155686 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.08 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.07
35155686 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.08 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.07
35155686 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.08 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.07
35155687 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.09 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.47
35155687 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.09 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.4
35155687 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.09 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.4
35155687 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.09 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.07
35155687 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.09 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.07
35155687 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.09 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.07
35155688 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.10 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.47
35155688 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.10 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.4
35155688 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.10 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.4
35155688 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.10 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.07
35155688 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.10 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.07
35155688 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.10 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.07
35155689 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.11 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.47
35155689 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.11 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.4
35155689 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.11 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.4
35155689 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.11 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.07
35155689 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.11 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.07
35155689 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.11 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.07
35155690 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.12 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.47
35155690 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.12 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.4
35155690 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.12 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.4
35155690 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.12 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.07
35155690 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.12 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.07
35155690 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.12 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.07
35155691 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.13 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.47
35155691 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.13 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.4
35155691 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.13 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.4
35155691 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.13 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.07
35155691 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.13 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.07
35155691 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.13 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.07
35155692 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.14 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.47
35155692 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.14 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.4
35155692 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.14 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.4
35155692 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.14 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.07
35155692 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.14 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.07
35155692 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.14 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.07
35155693 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.15 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.59
35155693 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.15 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.5
35155693 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.15 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.5
35155693 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.15 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.34
35155693 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.15 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.34
35155693 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.15 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.34
35155694 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.16 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.47
35155694 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.16 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.4
35155694 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.16 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.4
35155694 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.16 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.07
35155694 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.16 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.07
35155694 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.16 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.07
35155695 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.02 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.87
35155695 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.02 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.74
35155695 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.02 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.74
35155695 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.02 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.99
35155695 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.02 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.99
35155695 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.02 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.99
35155696 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.03 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1.38
35155696 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.03 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.17
35155696 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.03 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.17
35155696 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.03 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3.15
35155696 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.03 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3.15
35155696 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.03 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.15
35155697 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.04 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.47
35155697 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.04 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.4
35155697 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.04 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.4
35155697 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.04 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.08
35155697 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.04 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.08
35155697 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.04 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.08
35155698 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.05 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.47
35155698 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.05 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.4
35155698 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.05 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.4
35155698 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.05 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.08
35155698 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.05 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.08
35155698 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.05 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.08
35155699 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.06 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.47
35155699 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.06 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.4
35155699 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.06 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.4
35155699 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.06 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.08
35155699 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.06 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.08
35155699 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.06 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.08
35155741 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.08 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.47
35155741 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.08 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.4
35155741 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.08 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.4
35155741 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.08 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.08
35155741 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.08 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.08
35155741 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.08 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.08
35155742 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.09 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1.38
35155742 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.09 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.17
35155742 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.09 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.17
35155742 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.09 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3.15
35155742 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.09 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3.15
35155742 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.09 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.15
35155746 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.12 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.94
35155746 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.12 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.8
35155746 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.12 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.8
35155746 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.12 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2.15
35155746 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.12 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2.15
35155746 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.12 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.15
35155750 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.16 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.94
35155750 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.16 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.8
35155750 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.16 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.8
35155750 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.16 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2.15
35155750 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.16 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2.15
35155750 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.16 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.15
35155751 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.17 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1.38
35155751 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.17 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.17
35155751 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.17 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.17
35155751 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.17 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3.15
35155751 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.17 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3.15
35155751 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.17 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.15
35155752 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.02 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.4
35155752 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.02 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.34
35155752 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.02 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.34
35155752 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.02 | Other | AFUDC-Equity | Not assigned | 001/2021 | 0.93
35155752 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.02 | Other | AFUDC-Equity | Not assigned | 002/2021 | 0.93
35155752 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.02 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.93
35155753 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.03 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1.47
35155753 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.03 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.24
35155753 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.03 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.24
35155753 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.03 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3.34
35155753 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.03 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3.34
35155753 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.03 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.34
35155754 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.04 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.99
35155754 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.04 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.84
35155754 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.04 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.84
35155754 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.04 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2.27
35155754 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.04 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2.27
35155754 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.04 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.27
35155755 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.05 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.4
35155755 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.05 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.34
35155755 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.05 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.34
35155755 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.05 | Other | AFUDC-Equity | Not assigned | 001/2021 | 0.93
35155755 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.05 | Other | AFUDC-Equity | Not assigned | 002/2021 | 0.93
35155755 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.05 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.93
35155756 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.06 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3.44
35155756 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.06 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.91
35155756 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.06 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.91
35155756 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.06 | Other | AFUDC-Equity | Not assigned | 001/2021 | 7.84
35155756 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.06 | Other | AFUDC-Equity | Not assigned | 002/2021 | 7.84
35155756 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.06 | Other | AFUDC-Equity | Not assigned | 003/2021 | 7.84
35155758 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.08 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.99
35155758 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.08 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.84
35155758 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.08 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.84
35155758 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.08 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2.27
35155758 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.08 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2.27
35155758 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.08 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.27
35155841 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.11 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1.47
35155841 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.11 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.24
35155841 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.11 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.24
35155841 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.11 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3.34
35155841 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.11 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3.34
35155841 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.11 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.34
35155842 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.12 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.91
35155842 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.12 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.77
35155842 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.12 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.77
35155842 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.12 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2.07
35155842 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.12 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2.07
35155842 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.12 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.07
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 001/2021 | -27852.77
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -14712.33
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Contract | Electric Construction Contract | Not assigned | 003/2021 | 1111335.51
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Contract | Traffic Control Contracts | Not assigned | 001/2021 | -2759.9
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Labor Internal | Construction | Not assigned | 002/2021 | 545.12
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 728.83
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 550.08
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1130.23
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Labor Internal | Mapping | Not assigned | 001/2021 | -83.56
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Labor Internal | Mapping | Not assigned | 002/2021 | -39.23
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Labor Internal | Mapping | Not assigned | 003/2021 | 3334.01
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 433
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 326.8
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 671.47
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Labor Internal | Project Management Services | Not assigned | 001/2021 | 2233.5
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Labor Internal | Project Management Services | Not assigned | 002/2021 | 1116.75
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Materials | Electl & Electronic Equipment Component | Not assigned | 001/2021 | -3740.35
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Materials | Electrical Specialties | Not assigned | 001/2021 | -2797.23
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Materials | Material Burden | Not assigned | 001/2021 | -1148.25
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Materials | Material Burden | Not assigned | 002/2021 | 20.1
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 001/2021 | -0.02
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 001/2021 | -1327.12
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 137.68
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Benefits OH | Not assigned | 001/2021 | 642.24
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Benefits OH | Not assigned | 002/2021 | 656.77
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Benefits OH | Not assigned | 003/2021 | 1273.79
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Building Service Overhead | Not assigned | 001/2021 | 110.23
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Building Service Overhead | Not assigned | 002/2021 | 112.72
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Building Service Overhead | Not assigned | 003/2021 | 230.22
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Capitalized A&G | Not assigned | 001/2021 | 791.6
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Capitalized A&G | Not assigned | 002/2021 | 597.46
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Capitalized A&G | Not assigned | 003/2021 | 1227.58
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Cash Discount earned | STELLA-JONES CORPORATION | 002/2021 | -275.57
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 486.96
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 367.52
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 755.15
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | IT Device OH | Not assigned | 001/2021 | 62.55
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | IT Device OH | Not assigned | 002/2021 | 63.99
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | IT Device OH | Not assigned | 003/2021 | 130.67
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Minor Material OH | Not assigned | 001/2021 | -640.82
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Minor Material OH | Not assigned | 002/2021 | 11.22
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 659.6
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 497.82
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1022.87
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 216.98
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 221.9
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 453.21
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | Labor Internal | Construction | Not assigned | 002/2021 | 148.9
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 50.93
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 1.34
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 30.26
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 162.38
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 148.34
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 148.7
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 399.29
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 400.27
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 401.26
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 60.44
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 10.37
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 55.31
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 34.03
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | Other | IT Device OH | Not assigned | 002/2021 | 5.88
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 46.09
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 20.42
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | Labor Internal | Construction | Not assigned | 002/2021 | 223.35
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 76.4
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 2.01
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 45.38
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 152.9
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 139.96
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 140.51
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 376.2
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 377.68
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 379.16
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | Other | Benefits OH | Not assigned | 002/2021 | 90.69
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.57
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 82.98
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 51.05
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | Other | IT Device OH | Not assigned | 002/2021 | 8.84
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 69.14
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.64
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 001/2021 | 37320.8
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | -362
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Labor Internal | Construction | Not assigned | 002/2021 | 148.9
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 50.93
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 1.34
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 30.26
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 42.39
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 70.17
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 70.25
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 109.83
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 189.35
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 189.57
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Other | Benefits OH | Not assigned | 002/2021 | 60.44
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 10.37
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 55.31
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 34.03
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Other | IT Device OH | Not assigned | 002/2021 | 5.88
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 46.09
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 20.42
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 001/2021 | 37756.8
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -14118
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 54.96
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 69.9
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 69.9
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 138.4
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 188.63
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 188.63
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 001/2021 | 52309.6
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 002/2021 | 12607.55
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 003/2021 | -9338.2
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 76.56
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 25.95
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 15.42
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 54.3
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 103.87
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 106.44
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 141.83
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 280.28
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 287.23
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Other | Benefits OH | Not assigned | 001/2021 | 30.81
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Other | Building Service Overhead | Not assigned | 001/2021 | 5.29
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Other | Capitalized A&G | Not assigned | 001/2021 | 28.19
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 17.34
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Other | IT Device OH | Not assigned | 001/2021 | 3
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 23.49
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 10.41
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 001/2021 | 59234.4
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 002/2021 | 12607.55
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 003/2021 | -9235.4
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -724
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 61.72
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 115.68
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 118.33
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 | Other | AFUDC-Equity | Not assigned | 001/2021 | 161.02
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 | Other | AFUDC-Equity | Not assigned | 002/2021 | 312.14
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 319.31
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 001/2021 | 48084
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | -3620
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | 543
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 59.84
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 92.47
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 92.9
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 | Other | AFUDC-Equity | Not assigned | 001/2021 | 153.9
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 | Other | AFUDC-Equity | Not assigned | 002/2021 | 249.53
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 | Other | AFUDC-Equity | Not assigned | 003/2021 | 250.69
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 001/2021 | 49120.8
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 002/2021 | 12607.55
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 003/2021 | -10765.52
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 52.41
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 99.11
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 100.56
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 | Other | AFUDC-Equity | Not assigned | 001/2021 | 136.25
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 | Other | AFUDC-Equity | Not assigned | 002/2021 | 267.43
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 | Other | AFUDC-Equity | Not assigned | 003/2021 | 271.34
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 003/2021 | 30053.16
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 7.77
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 6.61
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 30.28
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 17.83
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 17.83
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 81.7
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 25772.79
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 003/2021 | 26052
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 30.66
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 49.36
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 69.87
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 78.42
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 133.18
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 188.54
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 37.62
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 003/2021 | 34557.38
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 004/2021 | -34595
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1.73
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.5
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 28.71
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3.96
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 4.04
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 77.48
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 39484.64
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 003/2021 | 39484.64
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 33.48
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 64.2
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 95.3
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 89.34
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 173.24
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 257.15
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 20337.44
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 003/2021 | 20337.44
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 22.16
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 37.23
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 53.24
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 57.24
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 100.45
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 143.67
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 8481.2
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 003/2021 | 12578
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 8.49
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 14.89
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 24.8
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 | Other | AFUDC-Equity | Not assigned | 001/2021 | 22.16
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 | Other | AFUDC-Equity | Not assigned | 002/2021 | 40.18
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 66.91
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Contract | Electric Construction Contract | BOXPOWER INC | 003/2021 | 365447
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Contract | Electric Construction Contract | BOXPOWER INC | 004/2021 | -365447
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 181.34
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 19716.17
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Contract | Gas Construction Contract | ALLISON SIERRA INC | 001/2021 | 8204.77
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Account Services | Not assigned | 002/2021 | 65.63
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Administrative Services - OT | Not assigned | 001/2021 | 97.81
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Civil Construction | Not assigned | 001/2021 | 5381.68
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Civil Construction | Not assigned | 002/2021 | 11436.05
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Civil Construction | Not assigned | 003/2021 | 11436.06
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Civil Construction DT | Not assigned | 002/2021 | 805.32
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Civil Construction DT | Not assigned | 003/2021 | 1879.08
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Civil Construction OT | Not assigned | 001/2021 | 1006.9
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Civil Construction OT | Not assigned | 002/2021 | 2416.59
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Civil Construction OT | Not assigned | 003/2021 | 5638.71
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Construction | Not assigned | 001/2021 | 10137
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Construction | Not assigned | 002/2021 | 545.12
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 754.46
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 2010.15
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1712.35
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 2307.95
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 16.99
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 6342.37
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 6038.97
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 7657.3
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 34.56
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Management Services | Not assigned | 001/2021 | 5357.17
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Management Services | Not assigned | 002/2021 | 4120.91
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Management Services | Not assigned | 003/2021 | 9801.86
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Mapping | Not assigned | 001/2021 | 173.34
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Mapping | Not assigned | 002/2021 | 144.16
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Mapping | Not assigned | 003/2021 | 1326.07
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 3787.7
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 3600.97
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 4549.2
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Materials | Material Burden | Not assigned | 001/2021 | 5.22
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 001/2021 | 35.76
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 381.58
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 438.35
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 840.96
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | AFUDC-Equity | Not assigned | 001/2021 | 903
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | AFUDC-Equity | Not assigned | 002/2021 | 1182.86
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | AFUDC-Equity | Not assigned | 003/2021 | 2269.25
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Benefits OH | Not assigned | 001/2021 | 8601.59
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Benefits OH | Not assigned | 002/2021 | 7985.66
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Benefits OH | Not assigned | 003/2021 | 10435.78
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Building Service Overhead | Not assigned | 001/2021 | 1476.25
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Building Service Overhead | Not assigned | 002/2021 | 1370.54
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Building Service Overhead | Not assigned | 003/2021 | 1886.19
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Capitalized A&G | Not assigned | 001/2021 | 8897.2
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Capitalized A&G | Not assigned | 002/2021 | 8100.62
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Capitalized A&G | Not assigned | 003/2021 | 11925.9
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Cash Discount earned | ALLISON SIERRA INC | 001/2021 | -164.1
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Cash Discount earned | STELLA-JONES CORPORATION | 001/2021 | -71.57
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Fleet OH - Elec | Not assigned | 001/2021 | 4237.6
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Fleet OH - Elec | Not assigned | 002/2021 | 4034.88
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Fleet OH - Elec | Not assigned | 003/2021 | 5116.16
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | IT Device OH | Not assigned | 001/2021 | 837.87
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | IT Device OH | Not assigned | 002/2021 | 777.87
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | IT Device OH | Not assigned | 003/2021 | 1070.53
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Minor Material OH | Not assigned | 001/2021 | 2.91
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 5739.94
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 5465.34
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 6929.96
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 20.7
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Payroll Taxes OH | Not assigned | 001/2021 | 2906.07
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Payroll Taxes OH | Not assigned | 002/2021 | 2697.98
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Other | Payroll Taxes OH | Not assigned | 003/2021 | 3713.03
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 37622.48
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -14985.68
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 46659.4
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -20646.93
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 37.88
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 58.19
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 41.93
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 101.74
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 157.02
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 113.14
35168820 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 40010.02
35168820 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -16872.76
35168821 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 17178.86
35168821 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -7326.33
35168822 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 11607.34
35168822 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -5050.72
35168822 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 003/2021 | -0.01
35168823 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.7 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 001/2021 | 6885.63
35168823 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.7 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | ENERGY EXPERTS INTERNATIONAL | 002/2021 | -2664.12
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 001/2021 | 72555.3
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 002/2021 | -69786.92
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 79.23
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 78.13
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 23.26
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 | Other | AFUDC-Equity | Not assigned | 001/2021 | 204.77
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 | Other | AFUDC-Equity | Not assigned | 002/2021 | 210.83
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 62.76
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 | Other | Land Acquisition Services | INTERWEST CONSULTING GROUP INC | 002/2021 | 80
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 | Other | Land Acquisition Services | INTERWEST CONSULTING GROUP INC | 003/2021 | 28.75
35173253 | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.93
35173253 | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.79
35173253 | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.79
35173253 | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2.14
35173253 | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2.14
35173253 | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.14
35173255 | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.82
35173255 | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.39
35173255 | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.39
35173255 | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6.45
35173255 | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6.45
35173255 | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6.45
35173320 | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.93
35173320 | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.79
35173320 | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.79
35173320 | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2.14
35173320 | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2.14
35173320 | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.14
35173321 | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.93
35173321 | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.79
35173321 | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.79
35173321 | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2.14
35173321 | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2.14
35173321 | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.14
35173754 | ECOP-BRUNSWICK 1106-H08-LR51486 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 44.26
35173754 | ECOP-BRUNSWICK 1106-H08-LR51486 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 38.55
35173754 | ECOP-BRUNSWICK 1106-H08-LR51486 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 38.55
35173754 | ECOP-BRUNSWICK 1106-H08-LR51486 | Other | AFUDC-Equity | Not assigned | 001/2021 | 104.02
35173754 | ECOP-BRUNSWICK 1106-H08-LR51486 | Other | AFUDC-Equity | Not assigned | 002/2021 | 104.02
35173754 | ECOP-BRUNSWICK 1106-H08-LR51486 | Other | AFUDC-Equity | Not assigned | 003/2021 | 104.02
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 352.04
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 16.96
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 5.75
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 120.19
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 628.04
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 434.98
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 129.6
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 972
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 001/2021 | 340.2
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 1296
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 259.2
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 71.94
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 358.02
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 247.96
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 100.59
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 92.83
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 99.46
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | AFUDC-Equity | Not assigned | 001/2021 | 238.29
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | AFUDC-Equity | Not assigned | 002/2021 | 250.49
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | AFUDC-Equity | Not assigned | 003/2021 | 268.39
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | Benefits OH | Not assigned | 001/2021 | 123.41
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | Benefits OH | Not assigned | 002/2021 | 609.21
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | Benefits OH | Not assigned | 003/2021 | 400.65
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | Building Service Overhead | Not assigned | 001/2021 | 21.18
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | Building Service Overhead | Not assigned | 002/2021 | 104.57
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | Building Service Overhead | Not assigned | 003/2021 | 72.42
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | Capitalized A&G | Not assigned | 001/2021 | 131.5
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | Capitalized A&G | Not assigned | 002/2021 | 654.53
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | Capitalized A&G | Not assigned | 003/2021 | 453.33
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 3.84
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | IT Device OH | Not assigned | 001/2021 | 12.02
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | IT Device OH | Not assigned | 002/2021 | 59.35
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | IT Device OH | Not assigned | 003/2021 | 41.1
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | Lodging | JEFFREY G RUDNICK | 003/2021 | 280.24
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | Meals Expense | JEFFREY G RUDNICK | 003/2021 | 87.37
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 5.2
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 71.99
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 376.15
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 260.52
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 41.69
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 205.82
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 142.55
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 3832
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -3832
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 15.42
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 16.05
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 16.05
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 35.17
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 43.31
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 43.31
35174085 | PSPS - FIA320 - LR @ 101269978 | Materials | Material Burden | Not assigned | 001/2021 | 442.26
35174085 | PSPS - FIA320 - LR @ 101269978 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 001/2021 | 2996.57
35174085 | PSPS - FIA320 - LR @ 101269978 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 001/2021 | 32.59
35174085 | PSPS - FIA320 - LR @ 101269978 | Other | Benefits OH | Not assigned | 001/2021 | 85.81
35174085 | PSPS - FIA320 - LR @ 101269978 | Other | Building Service Overhead | Not assigned | 001/2021 | 14.73
35174085 | PSPS - FIA320 - LR @ 101269978 | Other | Cash Discount earned | STELLA-JONES CORPORATION | 001/2021 | -55.92
35174085 | PSPS - FIA320 - LR @ 101269978 | Other | IT Device OH | Not assigned | 001/2021 | 8.36
35174085 | PSPS - FIA320 - LR @ 101269978 | Other | Minor Material OH | Not assigned | 001/2021 | 246.81
35174085 | PSPS - FIA320 - LR @ 101269978 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 28.99
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 3173
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -3173
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 36.1
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 33.05
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 33.05
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 82.44
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 89.19
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 89.19
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 22.89
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 19.35
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 19.35
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 52.2
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 52.2
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 52.2
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Contract | Contracts | Not assigned | 003/2021 | 4918.23
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Labor Internal | Electric Activity Charge - Non-Type A | Not assigned | 003/2021 | 328.2
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 15836.4
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 324.95
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 5373.54
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 114.8
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Labor Internal | Mapping | Not assigned | 003/2021 | 14.75
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 3257.87
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 6
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 5.07
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 49.29
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 13.67
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 13.67
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 132.99
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Other | Benefits OH | Not assigned | 003/2021 | 6254.53
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Other | Building Service Overhead | Not assigned | 003/2021 | 1130.45
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Other | Capitalized A&G | Not assigned | 003/2021 | 6076.88
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Other | Cost Adjustments | Not assigned | 003/2021 | 955
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 3664.62
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Other | IT Device OH | Not assigned | 003/2021 | 641.61
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 4963.83
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 68.76
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 2225.33
35174468 | ECOP-STANISLAUS 1702-H01-LR37276-PH2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 5.29
35174468 | ECOP-STANISLAUS 1702-H01-LR37276-PH2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4.47
35174468 | ECOP-STANISLAUS 1702-H01-LR37276-PH2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 4.47
35174468 | ECOP-STANISLAUS 1702-H01-LR37276-PH2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 12.06
35174468 | ECOP-STANISLAUS 1702-H01-LR37276-PH2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 12.06
35174468 | ECOP-STANISLAUS 1702-H01-LR37276-PH2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 12.06
35174469 | ECOP-PINE GROVE 1102-H01-LR45292 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 46.78
35174469 | ECOP-PINE GROVE 1102-H01-LR45292 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 39.44
35174469 | ECOP-PINE GROVE 1102-H01-LR45292 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 39.44
35174469 | ECOP-PINE GROVE 1102-H01-LR45292 | Other | AFUDC-Equity | Not assigned | 001/2021 | 106.43
35174469 | ECOP-PINE GROVE 1102-H01-LR45292 | Other | AFUDC-Equity | Not assigned | 002/2021 | 106.43
35174469 | ECOP-PINE GROVE 1102-H01-LR45292 | Other | AFUDC-Equity | Not assigned | 003/2021 | 106.43
35174470 | ECOP-MOLINO 1102-H01-LR318 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 15.55
35174470 | ECOP-MOLINO 1102-H01-LR318 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 13.15
35174470 | ECOP-MOLINO 1102-H01-LR318 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 13.15
35174470 | ECOP-MOLINO 1102-H01-LR318 | Other | AFUDC-Equity | Not assigned | 001/2021 | 35.48
35174470 | ECOP-MOLINO 1102-H01-LR318 | Other | AFUDC-Equity | Not assigned | 002/2021 | 35.48
35174470 | ECOP-MOLINO 1102-H01-LR318 | Other | AFUDC-Equity | Not assigned | 003/2021 | 35.48
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | Contract | Environmental Contract | FAR WESTERN ANTHROPOLOGICAL | 002/2021 | 190.84
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.19
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.57
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.11
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 27.04
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 23.01
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 23.17
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | Other | AFUDC-Equity | Not assigned | 001/2021 | 61.69
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | Other | AFUDC-Equity | Not assigned | 002/2021 | 62.1
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | Other | AFUDC-Equity | Not assigned | 003/2021 | 62.51
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | Other | Benefits OH | Not assigned | 002/2021 | 0.23
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.04
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | Other | Capitalized A&G | Not assigned | 002/2021 | 0.21
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.13
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | Other | IT Device OH | Not assigned | 002/2021 | 0.02
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.17
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.08
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | Contract | Environmental Contract | FAR WESTERN ANTHROPOLOGICAL | 002/2021 | 1641.83
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1.67
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | Labor Internal | Mapping | Not assigned | 002/2021 | 4.93
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.99
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 23.7
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 21.35
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 22.65
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | Other | AFUDC-Equity | Not assigned | 001/2021 | 54.08
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | Other | AFUDC-Equity | Not assigned | 002/2021 | 57.6
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | Other | AFUDC-Equity | Not assigned | 003/2021 | 61.12
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | Other | Benefits OH | Not assigned | 002/2021 | 1.99
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.34
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | Other | Capitalized A&G | Not assigned | 002/2021 | 1.82
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1.12
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | Other | IT Device OH | Not assigned | 002/2021 | 0.19
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1.51
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.67
35174474 | ECOP-CALISTOGA 1101-H01-LR736 PH1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 32.88
35174474 | ECOP-CALISTOGA 1101-H01-LR736 PH1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 27.8
35174474 | ECOP-CALISTOGA 1101-H01-LR736 PH1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 27.8
35174474 | ECOP-CALISTOGA 1101-H01-LR736 PH1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 75.02
35174474 | ECOP-CALISTOGA 1101-H01-LR736 PH1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 75.02
35174474 | ECOP-CALISTOGA 1101-H01-LR736 PH1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 75.02
35174475 | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 8.85
35174475 | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 7.48
35174475 | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 7.48
35174475 | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 | Other | AFUDC-Equity | Not assigned | 001/2021 | 20.17
35174475 | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 | Other | AFUDC-Equity | Not assigned | 002/2021 | 20.17
35174475 | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 | Other | AFUDC-Equity | Not assigned | 003/2021 | 20.17
35174476 | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 9.45
35174476 | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 7.99
35174476 | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 7.99
35174476 | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 | Other | AFUDC-Equity | Not assigned | 001/2021 | 21.55
35174476 | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 | Other | AFUDC-Equity | Not assigned | 002/2021 | 21.55
35174476 | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 | Other | AFUDC-Equity | Not assigned | 003/2021 | 21.55
35174477 | ECOP-CALISTOGA 1101-H01-LR736-PH3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 10.55
35174477 | ECOP-CALISTOGA 1101-H01-LR736-PH3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 8.92
35174477 | ECOP-CALISTOGA 1101-H01-LR736-PH3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 8.92
35174477 | ECOP-CALISTOGA 1101-H01-LR736-PH3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 24.06
35174477 | ECOP-CALISTOGA 1101-H01-LR736-PH3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 24.06
35174477 | ECOP-CALISTOGA 1101-H01-LR736-PH3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 24.06
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 8194.28
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | 676.06
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 486
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 88.01
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 48.91
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 34.82
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 100.41
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 227.15
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 31.09
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 201.28
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 77.38
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 249.69
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Labor Internal | Project Management Overtime | Not assigned | 002/2021 | 221.74
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 670.05
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 7.36
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 18.07
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 19.86
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 48.75
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | Benefits OH | Not assigned | 002/2021 | 149.34
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | Benefits OH | Not assigned | 003/2021 | 441.4
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 25.63
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 79.78
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 141.47
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 456.49
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 67.09
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 151.77
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | IT Device OH | Not assigned | 002/2021 | 14.55
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | IT Device OH | Not assigned | 003/2021 | 45.28
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 90.87
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 205.57
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 18.62
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 120.56
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 50.44
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 157.05
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 001/2021 | -233.08
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 8572
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -1158.72
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 116.54
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -116.54
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 48.91
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 236.84
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 409.48
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 69.64
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 80.29
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 277.35
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 87.67
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 129.6
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 47.7
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 214.76
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 110.87
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 297.8
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 24.75
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 28.19
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 36.43
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 56.78
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 76.06
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 98.3
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | Benefits OH | Not assigned | 001/2021 | 95.29
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | Benefits OH | Not assigned | 003/2021 | 393.34
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 16.36
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 71.09
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 87.2
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 392.61
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 53.64
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 185.31
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | IT Device OH | Not assigned | 001/2021 | 9.28
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | IT Device OH | Not assigned | 003/2021 | 40.34
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 72.66
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 251.01
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 52.51
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 32.2
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 139.95
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 2313.74
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -59.87
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 88.01
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 473.68
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Electric Estimating Doubletime | Not assigned | 001/2021 | 266.4
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 2051.08
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 288.3
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 001/2021 | 103.05
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 34.82
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1078.87
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 100.41
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 189.02
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 31.09
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 103.88
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 259.2
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 640.96
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 77.38
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 171.51
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Project Management Overtime | Not assigned | 002/2021 | 221.74
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 110.87
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 446.7
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 27.96
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 35.3
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 39.95
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 67.01
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 95.26
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 107.8
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Benefits OH | Not assigned | 001/2021 | 1280.51
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Benefits OH | Not assigned | 002/2021 | 149.34
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Benefits OH | Not assigned | 003/2021 | 308.7
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 219.77
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 25.63
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 55.8
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 1171.81
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 141.47
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 313.56
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 720.84
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 67.09
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 126.29
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | IT Device OH | Not assigned | 001/2021 | 124.74
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | IT Device OH | Not assigned | 002/2021 | 14.55
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | IT Device OH | Not assigned | 003/2021 | 31.67
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 976.4
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 90.87
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 171.06
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 18.62
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 62.21
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 432.63
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 50.44
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 109.85
35175847 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 6.64
35175847 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 5.62
35175847 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 5.62
35175847 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 15.16
35175847 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 15.16
35175847 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 15.16
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Labor Internal | Account Services | Not assigned | 003/2021 | 179.64
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 1004.4
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 46.51
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 183.15
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 354.85
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 518.4
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Labor Internal | Management Services | Not assigned | 002/2021 | 2914.09
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Labor Internal | Management Services | Not assigned | 003/2021 | 5563.25
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 104.41
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 238.47
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4.95
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 19.71
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 13.36
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 53.18
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Other | Benefits OH | Not assigned | 002/2021 | 743.08
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Other | Benefits OH | Not assigned | 003/2021 | 1400.15
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 127.54
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 253.06
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 1263.84
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 2484.35
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Other | IT Device OH | Not assigned | 002/2021 | 72.37
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Other | IT Device OH | Not assigned | 003/2021 | 143.63
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 109.69
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 212.53
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 251.03
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 498.16
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | Other | Reimbursed Mileage Expense | TREVOR R LATURNER | 003/2021 | 73.92
35175856 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 001/2021 | 489
35175856 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 002/2021 | -489
35175856 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.39
35175856 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.39
35175856 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.04
35175856 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.04
35181199 | ECOP-WEST POINT 1101-H03-TS L373 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 12.59
35181199 | ECOP-WEST POINT 1101-H03-TS L373 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 10.64
35181199 | ECOP-WEST POINT 1101-H03-TS L373 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 10.64
35181199 | ECOP-WEST POINT 1101-H03-TS L373 | Other | AFUDC-Equity | Not assigned | 001/2021 | 28.71
35181199 | ECOP-WEST POINT 1101-H03-TS L373 | Other | AFUDC-Equity | Not assigned | 002/2021 | 28.71
35181199 | ECOP-WEST POINT 1101-H03-TS L373 | Other | AFUDC-Equity | Not assigned | 003/2021 | 28.71
35185714 | WDDB - OTTER 1102 - LR 2002 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3.36
35185714 | WDDB - OTTER 1102 - LR 2002 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.84
35185714 | WDDB - OTTER 1102 - LR 2002 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.84
35185714 | WDDB - OTTER 1102 - LR 2002 | Other | AFUDC-Equity | Not assigned | 001/2021 | 7.67
35185714 | WDDB - OTTER 1102 - LR 2002 | Other | AFUDC-Equity | Not assigned | 002/2021 | 7.67
35185714 | WDDB - OTTER 1102 - LR 2002 | Other | AFUDC-Equity | Not assigned | 003/2021 | 7.67
35191130 | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 12.6
35191130 | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 10.87
35191130 | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 10.87
35191130 | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 29.34
35191130 | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 29.34
35191130 | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 29.34
35191317 | ECOP - BRUNSWICK 1106 - H03 - LR4639 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 001/2021 | -254.22
35191317 | ECOP - BRUNSWICK 1106 - H03 - LR4639 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 254.22
35191317 | ECOP - BRUNSWICK 1106 - H03 - LR4639 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 254.22
35191317 | ECOP - BRUNSWICK 1106 - H03 - LR4639 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -254.22
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 001/2021 | -2097.72
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 2217.46
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | 119.74
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 2330.8
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -2330.8
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 3753.65
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 003/2021 | 1483.76
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 3315.76
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 10628.2
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Electric Estimating | Not assigned | 004/2021 | 2359.8
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 741.88
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 2400.2
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Electric Estimating Overtime | Not assigned | 004/2021 | 547.16
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 335.03
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.46
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 69.64
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 3.82
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1741.5
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 4995.34
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 24.6
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Mapping | Not assigned | 001/2021 | 11.26
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 16.3
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1034.63
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 2967.73
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Project Management Services | Not assigned | 002/2021 | 744.5
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 148.9
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | Benefits OH | Not assigned | 001/2021 | 28.4
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | Benefits OH | Not assigned | 002/2021 | 2066.95
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | Benefits OH | Not assigned | 003/2021 | 5629.82
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | Building Service Overhead | Not assigned | 001/2021 | 4.87
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | Building Service Overhead | Not assigned | 002/2021 | 354.74
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | Building Service Overhead | Not assigned | 003/2021 | 1017.54
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | Capitalized A&G | Not assigned | 001/2021 | 29.79
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | Capitalized A&G | Not assigned | 002/2021 | 1891.5
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | Capitalized A&G | Not assigned | 003/2021 | 5425.62
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 2.55
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1163.57
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 3337.59
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | IT Device OH | Not assigned | 001/2021 | 2.77
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | IT Device OH | Not assigned | 002/2021 | 201.34
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | IT Device OH | Not assigned | 003/2021 | 577.53
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 3.45
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1576.08
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 4520.86
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 14.74
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 9.6
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 698.32
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 2003.08
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Contract | Contracts | BENDER ROSENTHAL INC | 004/2021 | 260
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 001/2021 | -1548.96
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 1668.7
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -119.74
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 5614.98
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -5614.98
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 4391.69
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 907.2
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 340.2
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Labor Internal | Acquisition - Misc | Not assigned | 004/2021 | 129.6
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 440.07
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 382.8
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 69.64
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 134.24
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 24.6
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 475.99
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 154.53
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 97.2
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Labor Internal | Mapping | Not assigned | 001/2021 | 13.18
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 93.78
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 271.34
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 133.07
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | Benefits OH | Not assigned | 001/2021 | 183.2
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | Benefits OH | Not assigned | 002/2021 | 461.73
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | Benefits OH | Not assigned | 003/2021 | 227.67
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | Building Service Overhead | Not assigned | 001/2021 | 31.45
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | Building Service Overhead | Not assigned | 002/2021 | 79.24
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | Building Service Overhead | Not assigned | 003/2021 | 41.15
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | Capitalized A&G | Not assigned | 001/2021 | 171.44
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | Capitalized A&G | Not assigned | 002/2021 | 496.06
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | Capitalized A&G | Not assigned | 003/2021 | 243.29
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 89.69
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | IT Device OH | Not assigned | 001/2021 | 17.85
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | IT Device OH | Not assigned | 002/2021 | 44.97
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | IT Device OH | Not assigned | 003/2021 | 23.37
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 121.48
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 14.74
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 285.08
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 92.55
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 61.9
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 155.99
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 81.01
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 001/2021 | -1186.54
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 1306.28
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | 377.4
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 1186.54
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -1186.54
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 4898.62
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Design Drafting Services | Not assigned | 002/2021 | 2072.35
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Design Drafting Services | Not assigned | 003/2021 | 6276.26
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 002/2021 | 741.88
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 003/2021 | 1178.28
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Drafting Doubletime | Not assigned | 003/2021 | 473.6
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 1687.49
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 1036.18
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 130.92
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 372.26
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.46
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 591.94
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 4.98
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1949.04
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 3114.63
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 209.13
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Mapping | Not assigned | 001/2021 | 14.7
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 2.96
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1157.94
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1969.62
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Project Management Services | Not assigned | 002/2021 | 744.5
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 148.9
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | Benefits OH | Not assigned | 001/2021 | 5.92
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | Benefits OH | Not assigned | 002/2021 | 2313.26
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | Benefits OH | Not assigned | 003/2021 | 3702.85
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | Building Service Overhead | Not assigned | 001/2021 | 1.02
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | Building Service Overhead | Not assigned | 002/2021 | 397.02
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | Building Service Overhead | Not assigned | 003/2021 | 669.27
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | Capitalized A&G | Not assigned | 001/2021 | 5.41
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | Capitalized A&G | Not assigned | 002/2021 | 2116.93
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | Capitalized A&G | Not assigned | 003/2021 | 3600.85
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 3.33
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1302.24
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 2081
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | IT Device OH | Not assigned | 001/2021 | 0.58
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | IT Device OH | Not assigned | 002/2021 | 225.34
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | IT Device OH | Not assigned | 003/2021 | 379.86
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 4.51
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1763.92
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 2818.78
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 125.26
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 2
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 781.56
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 1317.48
35191930 | ECOP - WOODACRE 1101 - H01-LR404 PH1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 8.54
35191930 | ECOP - WOODACRE 1101 - H01-LR404 PH1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 7.22
35191930 | ECOP - WOODACRE 1101 - H01-LR404 PH1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 7.22
35191930 | ECOP - WOODACRE 1101 - H01-LR404 PH1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 19.48
35191930 | ECOP - WOODACRE 1101 - H01-LR404 PH1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 19.48
35191930 | ECOP - WOODACRE 1101 - H01-LR404 PH1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 19.48
35191934 | ECOP - WOODACRE 1101 - H01-LR404 PH2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 6.14
35191934 | ECOP - WOODACRE 1101 - H01-LR404 PH2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 5.19
35191934 | ECOP - WOODACRE 1101 - H01-LR404 PH2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 5.19
35191934 | ECOP - WOODACRE 1101 - H01-LR404 PH2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 14.01
35191934 | ECOP - WOODACRE 1101 - H01-LR404 PH2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 14.01
35191934 | ECOP - WOODACRE 1101 - H01-LR404 PH2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 14.01
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 1582.12
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | 119.74
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 1140.68
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -1140.68
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 2388.28
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 2302.45
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 95
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 95
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 71.25
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Account Services | Not assigned | 001/2021 | 65.64
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 64.8
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 226.8
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Administration | Not assigned | 003/2021 | 69.64
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 473.68
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 87.28
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 57.42
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 139.28
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 208.92
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 16.99
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 212.17
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 65.26
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 126.26
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 255.25
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 80.13
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 98.42
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 388.8
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Manage L&EM | Not assigned | 001/2021 | 129.6
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 7.45
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 7.19
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.21
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 284.77
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 84.45
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 131.11
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Project Management Overtime | Not assigned | 002/2021 | 110.87
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 372.25
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 13.19
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 21.41
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 26.23
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 32.83
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 57.77
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 70.78
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 518
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 155.18
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 232.93
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 88.9
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 26.63
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 42.13
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 520.62
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 154.39
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 239.7
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 141.76
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 43.6
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 84.36
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 50.46
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 15.12
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 23.9
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Land Acquisition Services | BENDER ROSENTHAL INC | 001/2021 | 47.5
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 192.01
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 59.07
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 114.27
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 152.88
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 47.99
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 58.94
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 175.03
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 52.44
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 82.89
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 001/2021 | -1165.4
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 1165.4
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 2235.4
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -2235.4
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 19.58
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 16.83
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 15.99
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 | Other | AFUDC-Equity | Not assigned | 001/2021 | 45.43
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 | Other | AFUDC-Equity | Not assigned | 002/2021 | 45.43
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 | Other | AFUDC-Equity | Not assigned | 003/2021 | 43.15
35192025 | ECOP - FORESTHILL 1101 - H02-LR1802 PH1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 5.38
35192025 | ECOP - FORESTHILL 1101 - H02-LR1802 PH1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4.55
35192025 | ECOP - FORESTHILL 1101 - H02-LR1802 PH1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 4.55
35192025 | ECOP - FORESTHILL 1101 - H02-LR1802 PH1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 12.27
35192025 | ECOP - FORESTHILL 1101 - H02-LR1802 PH1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 12.27
35192025 | ECOP - FORESTHILL 1101 - H02-LR1802 PH1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 12.27
35192028 | ECOP - FORESTHILL 1101 - H02-LR1802 PH2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.91
35192028 | ECOP - FORESTHILL 1101 - H02-LR1802 PH2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.46
35192028 | ECOP - FORESTHILL 1101 - H02-LR1802 PH2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.46
35192028 | ECOP - FORESTHILL 1101 - H02-LR1802 PH2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6.63
35192028 | ECOP - FORESTHILL 1101 - H02-LR1802 PH2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6.63
35192028 | ECOP - FORESTHILL 1101 - H02-LR1802 PH2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6.63
35192029 | ECOP - FORESTHILL 1101 - H02-LR1802 PH3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3.71
35192029 | ECOP - FORESTHILL 1101 - H02-LR1802 PH3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 3.14
35192029 | ECOP - FORESTHILL 1101 - H02-LR1802 PH3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3.14
35192029 | ECOP - FORESTHILL 1101 - H02-LR1802 PH3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 8.47
35192029 | ECOP - FORESTHILL 1101 - H02-LR1802 PH3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 8.47
35192029 | ECOP - FORESTHILL 1101 - H02-LR1802 PH3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 8.47
35192031 | ECOP - COLUMBIA HILL 1101 - H01-LR35424 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 7.14
35192031 | ECOP - COLUMBIA HILL 1101 - H01-LR35424 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 6.04
35192031 | ECOP - COLUMBIA HILL 1101 - H01-LR35424 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 6.04
35192031 | ECOP - COLUMBIA HILL 1101 - H01-LR35424 | Other | AFUDC-Equity | Not assigned | 001/2021 | 16.3
35192031 | ECOP - COLUMBIA HILL 1101 - H01-LR35424 | Other | AFUDC-Equity | Not assigned | 002/2021 | 16.3
35192031 | ECOP - COLUMBIA HILL 1101 - H01-LR35424 | Other | AFUDC-Equity | Not assigned | 003/2021 | 16.3
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 001/2021 | -49.16
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 49.16
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 49.16
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -49.16
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 4.08
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 3.46
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3.46
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 | Other | AFUDC-Equity | Not assigned | 001/2021 | 9.33
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 | Other | AFUDC-Equity | Not assigned | 002/2021 | 9.33
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 | Other | AFUDC-Equity | Not assigned | 003/2021 | 9.33
35192035 | ECOP - MIRABEL 1101 - H01-LR298 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.89
35192035 | ECOP - MIRABEL 1101 - H01-LR298 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.44
35192035 | ECOP - MIRABEL 1101 - H01-LR298 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.44
35192035 | ECOP - MIRABEL 1101 - H01-LR298 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6.59
35192035 | ECOP - MIRABEL 1101 - H01-LR298 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6.59
35192035 | ECOP - MIRABEL 1101 - H01-LR298 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6.59
35192036 | ECOP - RINCON 1103 - H01-LR474 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 7.76
35192036 | ECOP - RINCON 1103 - H01-LR474 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 6.56
35192036 | ECOP - RINCON 1103 - H01-LR474 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 6.56
35192036 | ECOP - RINCON 1103 - H01-LR474 | Other | AFUDC-Equity | Not assigned | 001/2021 | 17.71
35192036 | ECOP - RINCON 1103 - H01-LR474 | Other | AFUDC-Equity | Not assigned | 002/2021 | 17.71
35192036 | ECOP - RINCON 1103 - H01-LR474 | Other | AFUDC-Equity | Not assigned | 003/2021 | 17.71
35192037 | ECOP - SILVERADO 2105 - H01-LR1421 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 13.71
35192037 | ECOP - SILVERADO 2105 - H01-LR1421 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 11.59
35192037 | ECOP - SILVERADO 2105 - H01-LR1421 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 11.59
35192037 | ECOP - SILVERADO 2105 - H01-LR1421 | Other | AFUDC-Equity | Not assigned | 001/2021 | 31.28
35192037 | ECOP - SILVERADO 2105 - H01-LR1421 | Other | AFUDC-Equity | Not assigned | 002/2021 | 31.28
35192037 | ECOP - SILVERADO 2105 - H01-LR1421 | Other | AFUDC-Equity | Not assigned | 003/2021 | 31.28
35192039 | ECOP - MONTE RIO 1113 - H04-LR320 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 4.37
35192039 | ECOP - MONTE RIO 1113 - H04-LR320 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 3.7
35192039 | ECOP - MONTE RIO 1113 - H04-LR320 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3.7
35192039 | ECOP - MONTE RIO 1113 - H04-LR320 | Other | AFUDC-Equity | Not assigned | 001/2021 | 9.97
35192039 | ECOP - MONTE RIO 1113 - H04-LR320 | Other | AFUDC-Equity | Not assigned | 002/2021 | 9.97
35192039 | ECOP - MONTE RIO 1113 - H04-LR320 | Other | AFUDC-Equity | Not assigned | 003/2021 | 9.97
35192040 | ECOP - MONTE RIO 1113 - H08-LR477 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 4.07
35192040 | ECOP - MONTE RIO 1113 - H08-LR477 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 3.44
35192040 | ECOP - MONTE RIO 1113 - H08-LR477 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3.44
35192040 | ECOP - MONTE RIO 1113 - H08-LR477 | Other | AFUDC-Equity | Not assigned | 001/2021 | 9.28
35192040 | ECOP - MONTE RIO 1113 - H08-LR477 | Other | AFUDC-Equity | Not assigned | 002/2021 | 9.28
35192040 | ECOP - MONTE RIO 1113 - H08-LR477 | Other | AFUDC-Equity | Not assigned | 003/2021 | 9.28
35192041 | ECOP - WEST POINT 1101 - H01-LR4706 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 13.58
35192041 | ECOP - WEST POINT 1101 - H01-LR4706 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 11.48
35192041 | ECOP - WEST POINT 1101 - H01-LR4706 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 11.48
35192041 | ECOP - WEST POINT 1101 - H01-LR4706 | Other | AFUDC-Equity | Not assigned | 001/2021 | 30.99
35192041 | ECOP - WEST POINT 1101 - H01-LR4706 | Other | AFUDC-Equity | Not assigned | 002/2021 | 30.99
35192041 | ECOP - WEST POINT 1101 - H01-LR4706 | Other | AFUDC-Equity | Not assigned | 003/2021 | 30.99
35192043 | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 7.98
35192043 | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 6.75
35192043 | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 6.75
35192043 | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 18.21
35192043 | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 18.21
35192043 | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 18.21
35192044 | ECOP - PINE GROVE 1102 - H03-LR13438 PH2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 8.67
35192044 | ECOP - PINE GROVE 1102 - H03-LR13438 PH2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 7.33
35192044 | ECOP - PINE GROVE 1102 - H03-LR13438 PH2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 7.33
35192044 | ECOP - PINE GROVE 1102 - H03-LR13438 PH2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 19.78
35192044 | ECOP - PINE GROVE 1102 - H03-LR13438 PH2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 19.78
35192044 | ECOP - PINE GROVE 1102 - H03-LR13438 PH2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 19.78
35192045 | ECOP - STANISLAUS 1702 - H02-LR75348 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 6.46
35192045 | ECOP - STANISLAUS 1702 - H02-LR75348 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 5.46
35192045 | ECOP - STANISLAUS 1702 - H02-LR75348 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 5.46
35192045 | ECOP - STANISLAUS 1702 - H02-LR75348 | Other | AFUDC-Equity | Not assigned | 001/2021 | 14.73
35192045 | ECOP - STANISLAUS 1702 - H02-LR75348 | Other | AFUDC-Equity | Not assigned | 002/2021 | 14.73
35192045 | ECOP - STANISLAUS 1702 - H02-LR75348 | Other | AFUDC-Equity | Not assigned | 003/2021 | 14.73
35192046 | ECOP - PINE GROVE 1102 - H04-LR3172 PH1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 9.47
35192046 | ECOP - PINE GROVE 1102 - H04-LR3172 PH1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 8.01
35192046 | ECOP - PINE GROVE 1102 - H04-LR3172 PH1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 8.01
35192046 | ECOP - PINE GROVE 1102 - H04-LR3172 PH1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 21.62
35192046 | ECOP - PINE GROVE 1102 - H04-LR3172 PH1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 21.62
35192046 | ECOP - PINE GROVE 1102 - H04-LR3172 PH1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 21.62
35192047 | ECOP - PINE GROVE 1102 - H04-LR3172 PH2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 10.59
35192047 | ECOP - PINE GROVE 1102 - H04-LR3172 PH2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 8.95
35192047 | ECOP - PINE GROVE 1102 - H04-LR3172 PH2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 8.95
35192047 | ECOP - PINE GROVE 1102 - H04-LR3172 PH2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 24.15
35192047 | ECOP - PINE GROVE 1102 - H04-LR3172 PH2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 24.15
35192047 | ECOP - PINE GROVE 1102 - H04-LR3172 PH2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 24.15
35192048 | ECOP - PINE GROVE 1102 - H04-LR3172 PH3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 9.89
35192048 | ECOP - PINE GROVE 1102 - H04-LR3172 PH3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 8.36
35192048 | ECOP - PINE GROVE 1102 - H04-LR3172 PH3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 8.36
35192048 | ECOP - PINE GROVE 1102 - H04-LR3172 PH3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 22.57
35192048 | ECOP - PINE GROVE 1102 - H04-LR3172 PH3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 22.57
35192048 | ECOP - PINE GROVE 1102 - H04-LR3172 PH3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 22.57
35192049 | ECOP - PINE GROVE 1102 - H04-LR3172 PH4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 9.11
35192049 | ECOP - PINE GROVE 1102 - H04-LR3172 PH4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 7.7
35192049 | ECOP - PINE GROVE 1102 - H04-LR3172 PH4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 7.7
35192049 | ECOP - PINE GROVE 1102 - H04-LR3172 PH4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 20.77
35192049 | ECOP - PINE GROVE 1102 - H04-LR3172 PH4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 20.77
35192049 | ECOP - PINE GROVE 1102 - H04-LR3172 PH4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 20.77
35192050 | ECOP - WEST POINT 1102 - H01-TS1303 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3.36
35192050 | ECOP - WEST POINT 1102 - H01-TS1303 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.84
35192050 | ECOP - WEST POINT 1102 - H01-TS1303 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.84
35192050 | ECOP - WEST POINT 1102 - H01-TS1303 | Other | AFUDC-Equity | Not assigned | 001/2021 | 7.65
35192050 | ECOP - WEST POINT 1102 - H01-TS1303 | Other | AFUDC-Equity | Not assigned | 002/2021 | 7.65
35192050 | ECOP - WEST POINT 1102 - H01-TS1303 | Other | AFUDC-Equity | Not assigned | 003/2021 | 7.65
35192051 | ECOP - SALT SPRINGS 2102 - H01-LR4796 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 4.36
35192051 | ECOP - SALT SPRINGS 2102 - H01-LR4796 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 3.69
35192051 | ECOP - SALT SPRINGS 2102 - H01-LR4796 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3.69
35192051 | ECOP - SALT SPRINGS 2102 - H01-LR4796 | Other | AFUDC-Equity | Not assigned | 001/2021 | 9.96
35192051 | ECOP - SALT SPRINGS 2102 - H01-LR4796 | Other | AFUDC-Equity | Not assigned | 002/2021 | 9.96
35192051 | ECOP - SALT SPRINGS 2102 - H01-LR4796 | Other | AFUDC-Equity | Not assigned | 003/2021 | 9.96
35192052 | ECOP - WEST POINT 1102 - H05-LR34416 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3.84
35192052 | ECOP - WEST POINT 1102 - H05-LR34416 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 3.25
35192052 | ECOP - WEST POINT 1102 - H05-LR34416 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3.25
35192052 | ECOP - WEST POINT 1102 - H05-LR34416 | Other | AFUDC-Equity | Not assigned | 001/2021 | 8.78
35192052 | ECOP - WEST POINT 1102 - H05-LR34416 | Other | AFUDC-Equity | Not assigned | 002/2021 | 8.78
35192052 | ECOP - WEST POINT 1102 - H05-LR34416 | Other | AFUDC-Equity | Not assigned | 003/2021 | 8.78
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Contract | Construction Inspection | CANUS CORPORATION | 002/2021 | 44430.02
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Contract | Construction Inspection | CANUS CORPORATION | 003/2021 | -41775.97
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Contract | Contracts | ARBORWORKS INC | 003/2021 | 70195.18
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Contract | Contracts | ARBORWORKS INC | 004/2021 | 19832.38
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 33496.17
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 11714.64
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 80936.8
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Contract | Environmental Contract | CH2M HILL ENGINEERS INC | 002/2021 | 12300
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Contract | Environmental Contract | CH2M HILL ENGINEERS INC | 003/2021 | -11900
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Contract | Environmental Contract | CH2M HILL ENGINEERS INC | 004/2021 | -400
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Contract | Environmental Contract | FAR WESTERN ANTHROPOLOGICAL | 002/2021 | 161.95
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor External | Consulting Services - Environmental Perm | KLEINFELDER INC | 003/2021 | 10083.82
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Administration | Not assigned | 001/2021 | 139.28
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Administrative Services - OT | Not assigned | 001/2021 | 489.06
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 3682.53
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 1075.91
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Construction | Not assigned | 002/2021 | 102219.4
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Construction | Not assigned | 003/2021 | 23140.36
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Construction Doubletime Services | Not assigned | 002/2021 | 121402.9
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Construction Doubletime Services | Not assigned | 003/2021 | 14429.02
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Design Drafting Services | Not assigned | 001/2021 | 473.68
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 001/2021 | 43.64
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Design Overtime Services | Not assigned | 001/2021 | 698.24
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Design Services | Not assigned | 001/2021 | 592.1
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Design Services Double Time | Not assigned | 001/2021 | 1864.8
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Drafting Doubletime | Not assigned | 001/2021 | 1243.2
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 1850.31
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Electric Estimating Doubletime | Not assigned | 001/2021 | 1953.6
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 2705.68
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 281.28
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1427
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 707.28
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 4491.78
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 2733.37
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 2507.04
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Environmental Services | Not assigned | 003/2021 | 591.94
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Hours - Overtime | Not assigned | 003/2021 | 89.73
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Hours - Straight Time | Not assigned | 002/2021 | 134.64
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Hours - Straight Time | Not assigned | 003/2021 | 165.68
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 3968.51
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 77392.79
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 13656.36
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 1808.94
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 2289.63
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 1520.78
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Indirect Labor - IT | Not assigned | 002/2021 | 50.22
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Indirect Labor - IT | Not assigned | 003/2021 | 95.27
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 002/2021 | 216.18
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 003/2021 | 288.24
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 002/2021 | 106.73
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 003/2021 | 52.65
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Maintain & Operate Services | Not assigned | 002/2021 | 706.71
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Maintain & Operate Services | Not assigned | 003/2021 | 835.27
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Manage L&EM | Not assigned | 002/2021 | 64.8
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Manage L&EM | Not assigned | 003/2021 | 129.6
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Mapping | Not assigned | 002/2021 | 2218.42
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Mapping | Not assigned | 003/2021 | 761.23
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Operating Services | Not assigned | 003/2021 | 70.17
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 3388.89
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 47311.41
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 9031.59
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Materials | Communication & Signaling Equipment | Not assigned | 003/2021 | 614.88
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 002/2021 | 2827.4
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 004/2021 | -37851.8
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Materials | Construction Supplies | Not assigned | 002/2021 | 1534.78
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Materials | Electl & Electronic Equipment Component | Not assigned | 002/2021 | 3708.14
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Materials | Electrical Specialties | Not assigned | 002/2021 | 6554.88
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Materials | Electrical Specialties | Not assigned | 003/2021 | 7760.77
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Materials | Fabricated Structures | Not assigned | 002/2021 | 20957.37
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Materials | Material Burden | Not assigned | 002/2021 | 42650.1
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Materials | Material Burden | Not assigned | 003/2021 | 2016.03
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Materials | Materials Not Otherwise Classified | Not assigned | 002/2021 | 20322.28
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 002/2021 | 201337.13
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 003/2021 | 4032.87
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 53326.92
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 1972.64
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 002/2021 | 153.78
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Materials | Transformers, Regulators & Capacitors | Not assigned | 002/2021 | 1066.53
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 47.31
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 932.68
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 991.85
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 122.72
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2516.76
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2676.42
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Benefits OH | Not assigned | 001/2021 | 6464.85
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Benefits OH | Not assigned | 002/2021 | 102397.19
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Benefits OH | Not assigned | 003/2021 | 17244.79
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Building Service Overhead | Not assigned | 001/2021 | 1109.54
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Building Service Overhead | Not assigned | 002/2021 | 17574.1
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Building Service Overhead | Not assigned | 003/2021 | 3116.86
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Capitalized A&G | Not assigned | 001/2021 | 6195.57
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Capitalized A&G | Not assigned | 002/2021 | 86494.84
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Capitalized A&G | Not assigned | 003/2021 | 16511.61
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Cash Discount earned | STELLA-JONES CORPORATION | 003/2021 | -3809.47
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 2651.53
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 51709.35
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 9124.37
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | IT Device OH | Not assigned | 001/2021 | 629.74
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | IT Device OH | Not assigned | 002/2021 | 9974.5
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | IT Device OH | Not assigned | 003/2021 | 1769.04
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Minor Material OH | Not assigned | 002/2021 | 25200.63
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Minor Material OH | Not assigned | 003/2021 | 1165.85
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 3591.57
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 70041.64
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 12359.21
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 1083.42
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 1371.32
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 910.83
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Operation Mgmt & Support - IT | Not assigned | 002/2021 | 21.61
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Operation Mgmt & Support - IT | Not assigned | 003/2021 | 40.99
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 2184.16
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 34595.16
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 6135.6
35192054 | ECOP-OAKHURST 1103-LR 5470 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 10.93
35192054 | ECOP-OAKHURST 1103-LR 5470 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 9.24
35192054 | ECOP-OAKHURST 1103-LR 5470 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 9.24
35192054 | ECOP-OAKHURST 1103-LR 5470 | Other | AFUDC-Equity | Not assigned | 001/2021 | 24.93
35192054 | ECOP-OAKHURST 1103-LR 5470 | Other | AFUDC-Equity | Not assigned | 002/2021 | 24.93
35192054 | ECOP-OAKHURST 1103-LR 5470 | Other | AFUDC-Equity | Not assigned | 003/2021 | 24.93
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 001/2021 | -720.38
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 840.12
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | 59.87
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 2468.48
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -2468.48
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 5051.33
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 95
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 47.5
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Construction | Not assigned | 002/2021 | 744.51
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Design Overtime Services | Not assigned | 001/2021 | 218.2
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 1302.62
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Electric Estimating Doubletime | Not assigned | 002/2021 | 1184
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 2923.88
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 260.58
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1156.1
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 278.56
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 243.74
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 79.11
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 2177.26
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 391.96
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 224.34
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 234.92
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 97.2
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 259.2
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 421.2
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 004/2021 | 97.2
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Mapping | Not assigned | 001/2021 | 15.15
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Mapping | Not assigned | 002/2021 | 6.98
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.14
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 47
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1421.4
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 366.79
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 21.45
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 42.39
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 63.33
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | AFUDC-Equity | Not assigned | 001/2021 | 53.4
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | AFUDC-Equity | Not assigned | 002/2021 | 114.37
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | AFUDC-Equity | Not assigned | 003/2021 | 170.9
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Benefits OH | Not assigned | 001/2021 | 93.88
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Benefits OH | Not assigned | 002/2021 | 2801.77
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Benefits OH | Not assigned | 003/2021 | 658.13
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Building Service Overhead | Not assigned | 001/2021 | 16.12
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Building Service Overhead | Not assigned | 002/2021 | 480.86
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Building Service Overhead | Not assigned | 003/2021 | 118.96
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Capitalized A&G | Not assigned | 001/2021 | 85.92
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Capitalized A&G | Not assigned | 002/2021 | 2598.58
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Capitalized A&G | Not assigned | 003/2021 | 670.56
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 52.85
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1454.71
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 261.89
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | IT Device OH | Not assigned | 001/2021 | 9.15
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | IT Device OH | Not assigned | 002/2021 | 272.92
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | IT Device OH | Not assigned | 003/2021 | 67.51
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 71.59
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1970.44
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 354.73
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 134.35
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 140.71
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 31.71
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 946.58
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 234.16
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Other | Permits/FeesLand Surveying Services | WHPACIFIC INC | 002/2021 | 1165.84
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 001/2021 | -1944.05
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 2800.05
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -119.74
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 1944.05
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -1944.05
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 4000.16
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Labor Internal | Design Services | Not assigned | 001/2021 | 296.05
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 1421.04
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 473.68
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 458.22
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 741.5
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 25.24
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 236.3
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 11.45
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 32.4
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Labor Internal | Mapping | Not assigned | 001/2021 | 12
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 440.53
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.99
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 153.52
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 21.75
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 29.7
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 32.27
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 54.97
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 80.13
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 87.07
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | Benefits OH | Not assigned | 001/2021 | 880.08
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | Benefits OH | Not assigned | 002/2021 | 29.96
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | Benefits OH | Not assigned | 003/2021 | 285.7
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | Building Service Overhead | Not assigned | 001/2021 | 151.05
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.14
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | Building Service Overhead | Not assigned | 003/2021 | 51.62
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | Capitalized A&G | Not assigned | 001/2021 | 805.37
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | Capitalized A&G | Not assigned | 002/2021 | 27.41
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | Capitalized A&G | Not assigned | 003/2021 | 280.66
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 495.43
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 16.86
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 157.88
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | IT Device OH | Not assigned | 001/2021 | 85.72
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | IT Device OH | Not assigned | 002/2021 | 2.92
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | IT Device OH | Not assigned | 003/2021 | 29.32
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 671.07
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 22.84
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 213.85
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 6.86
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 297.34
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.12
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 101.64
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 001/2021 | -2177.13
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 6487.77
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -119.74
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 2177.13
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -2177.13
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 4406.08
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 1124.99
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 87.28
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 415.44
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 25.24
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 22.89
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 64.8
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 13.22
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 246.81
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.99
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 64.64
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 21.23
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 29.7
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 33.91
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 53.08
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 80.13
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 91.51
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | Benefits OH | Not assigned | 001/2021 | 493.07
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | Benefits OH | Not assigned | 002/2021 | 29.96
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | Benefits OH | Not assigned | 003/2021 | 115.26
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 84.62
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.14
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 20.83
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 451.23
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 27.41
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 118.18
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 277.57
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 16.86
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | IT Device OH | Not assigned | 001/2021 | 48.03
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | IT Device OH | Not assigned | 002/2021 | 2.92
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | IT Device OH | Not assigned | 003/2021 | 11.83
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 375.98
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 22.84
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 13.71
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 166.57
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.12
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 41
35192283 | ECOP - CALISTOGA 1101 - H04-LR1087 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.89
35192283 | ECOP - CALISTOGA 1101 - H04-LR1087 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.44
35192283 | ECOP - CALISTOGA 1101 - H04-LR1087 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.44
35192283 | ECOP - CALISTOGA 1101 - H04-LR1087 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6.58
35192283 | ECOP - CALISTOGA 1101 - H04-LR1087 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6.58
35192283 | ECOP - CALISTOGA 1101 - H04-LR1087 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6.58
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 001/2021 | -1048.86
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 1168.6
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | 239.48
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 1048.86
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -1048.86
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 3449.21
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 23.75
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 88.01
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 59.21
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 769.73
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 130.92
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 74.45
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 335.03
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 69.64
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 383.02
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 28.75
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 285.08
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 305.34
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 24.6
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 53.99
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 181.11
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 64.8
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 129.6
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Mapping | Not assigned | 001/2021 | 10.35
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.07
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 31.1
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 200.14
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 284.64
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Labor Internal | Project Management Services | Not assigned | 002/2021 | 446.7
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 20.65
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 24.13
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 52.99
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | AFUDC-Equity | Not assigned | 001/2021 | 50.18
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | AFUDC-Equity | Not assigned | 002/2021 | 65.11
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | AFUDC-Equity | Not assigned | 003/2021 | 142.98
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Benefits OH | Not assigned | 001/2021 | 57.99
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Benefits OH | Not assigned | 002/2021 | 390.71
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Benefits OH | Not assigned | 003/2021 | 510.94
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Building Service Overhead | Not assigned | 001/2021 | 9.95
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Building Service Overhead | Not assigned | 002/2021 | 67.08
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Building Service Overhead | Not assigned | 003/2021 | 92.34
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Capitalized A&G | Not assigned | 001/2021 | 56.86
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Capitalized A&G | Not assigned | 002/2021 | 365.89
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Capitalized A&G | Not assigned | 003/2021 | 520.4
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 19.2
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 190.47
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 204.02
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | IT Device OH | Not assigned | 001/2021 | 5.66
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | IT Device OH | Not assigned | 002/2021 | 38.04
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | IT Device OH | Not assigned | 003/2021 | 52.42
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 26.02
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 258
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 276.34
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 14.74
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 32.33
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 108.47
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 19.59
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 132
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 181.77
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 003/2021 | 29120.8
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 001/2021 | -254.22
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 254.22
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 254.22
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -254.22
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3.32
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.84
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.84
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 7.67
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 7.67
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 7.67
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 001/2021 | -641.46
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 641.46
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 641.46
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -641.46
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3.99
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 3.45
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3.45
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 9.32
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 9.32
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 9.32
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 001/2021 | -254.22
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 254.22
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 254.22
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -254.22
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3.32
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.84
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.84
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB | Other | AFUDC-Equity | Not assigned | 001/2021 | 7.67
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB | Other | AFUDC-Equity | Not assigned | 002/2021 | 7.67
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB | Other | AFUDC-Equity | Not assigned | 003/2021 | 7.67
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 001/2021 | -254.22
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 254.22
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 254.22
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -254.22
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3.32
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.84
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.84
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 | Other | AFUDC-Equity | Not assigned | 001/2021 | 7.67
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 | Other | AFUDC-Equity | Not assigned | 002/2021 | 7.67
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 | Other | AFUDC-Equity | Not assigned | 003/2021 | 7.67
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 001/2021 | -254.22
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 254.22
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 254.22
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -254.22
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.44
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.4
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.4
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.08
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.08
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.08
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 1556.62
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -119.74
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 003/2021 | 165235.2
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 2851.59
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 2704.31
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 71.25
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 71.25
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 23.75
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Administration | Not assigned | 004/2021 | 139.28
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Construction | Not assigned | 003/2021 | 670.05
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Design Overtime Services | Not assigned | 001/2021 | 87.28
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Design Services | Not assigned | 001/2021 | 296.05
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Engineering Services - OT | Not assigned | 003/2021 | 443.48
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 335.03
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1340.11
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 003/2021 | 214.84
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 139.28
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 174.1
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 104.46
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 132.92
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 116.4
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 906.67
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 106.43
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 61.51
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 32.4
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 001/2021 | 129.6
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Mapping | Not assigned | 001/2021 | 8.76
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Mapping | Not assigned | 002/2021 | 8.33
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Mapping | Not assigned | 003/2021 | 6.1
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 139.65
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 69.16
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 573.71
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 7.75
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 15.67
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 156.62
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | AFUDC-Equity | Not assigned | 001/2021 | 19.57
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | AFUDC-Equity | Not assigned | 002/2021 | 42.29
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | AFUDC-Equity | Not assigned | 003/2021 | 422.62
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Benefits OH | Not assigned | 001/2021 | 260.99
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Benefits OH | Not assigned | 002/2021 | 138.16
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Benefits OH | Not assigned | 003/2021 | 1078.48
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Building Service Overhead | Not assigned | 001/2021 | 44.8
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Building Service Overhead | Not assigned | 002/2021 | 23.72
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Building Service Overhead | Not assigned | 003/2021 | 194.93
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Capitalized A&G | Not assigned | 001/2021 | 255.3
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Capitalized A&G | Not assigned | 002/2021 | 126.43
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Capitalized A&G | Not assigned | 003/2021 | 1048.88
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 88.81
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 77.77
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 605.8
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | IT Device OH | Not assigned | 001/2021 | 25.42
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | IT Device OH | Not assigned | 002/2021 | 13.45
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | IT Device OH | Not assigned | 003/2021 | 110.64
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Land Acquisition Services | BENDER ROSENTHAL INC | 001/2021 | 356.25
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 120.29
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 105.35
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 820.56
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 63.76
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 36.84
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 88.2
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 46.68
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 383.74
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 6346.22
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -3592.2
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 2874.65
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 2620.25
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 47.5
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 95
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 47.5
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Administrative Services - OT | Not assigned | 001/2021 | 44.01
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Design Overtime Services | Not assigned | 001/2021 | 349.12
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Design Services | Not assigned | 001/2021 | 207.24
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 148.03
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 218.2
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 297.8
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 372.25
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 69.64
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 34.82
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 191.58
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 227.86
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 126.24
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 40.15
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 125.92
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 12.3
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 356.4
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Mapping | Not assigned | 001/2021 | 8.76
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Mapping | Not assigned | 002/2021 | 8.15
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.14
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 136.71
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 207.16
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 82.01
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 7.35
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 20.49
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 45.53
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | AFUDC-Equity | Not assigned | 001/2021 | 18.53
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | AFUDC-Equity | Not assigned | 002/2021 | 55.3
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | AFUDC-Equity | Not assigned | 003/2021 | 122.85
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Benefits OH | Not assigned | 001/2021 | 266.34
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Benefits OH | Not assigned | 002/2021 | 392.6
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Benefits OH | Not assigned | 003/2021 | 153.59
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Building Service Overhead | Not assigned | 001/2021 | 45.71
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Building Service Overhead | Not assigned | 002/2021 | 67.38
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Building Service Overhead | Not assigned | 003/2021 | 27.76
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Capitalized A&G | Not assigned | 001/2021 | 249.91
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Capitalized A&G | Not assigned | 002/2021 | 378.73
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Capitalized A&G | Not assigned | 003/2021 | 149.93
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 128
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 152.25
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 84.34
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | IT Device OH | Not assigned | 001/2021 | 25.94
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | IT Device OH | Not assigned | 002/2021 | 38.25
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | IT Device OH | Not assigned | 003/2021 | 15.75
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Land Acquisition Services | BENDER ROSENTHAL INC | 001/2021 | 237.5
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 173.37
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 206.23
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 114.25
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 24.05
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 75.41
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 7.37
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 89.98
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 132.65
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 54.65
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Permits/FeesLand Surveying Services | PSOMAS | 003/2021 | 22000
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Other | Permits/FeesLand Surveying Services | PSOMAS | 004/2021 | -22000
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 001/2021 | -10393.2
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 10986.6
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -119.74
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 19094.24
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -19094.24
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 4869.9
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 1573.86
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 403.75
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 166.25
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Account Services | Not assigned | 002/2021 | 164.09
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Account Services | Not assigned | 003/2021 | 213.31
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 64.8
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 174.56
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 305.48
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 148.9
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 42.48
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 55.23
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 80.67
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 135.31
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 155.81
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 160.26
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 183.15
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 453.6
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 453.6
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 14.61
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 1.21
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 5.22
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 47.92
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 204.79
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 239.93
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 37.63
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 66.25
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 78.08
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 94.99
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 178.77
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 210.69
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Benefits OH | Not assigned | 001/2021 | 95.75
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Benefits OH | Not assigned | 002/2021 | 362.55
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Benefits OH | Not assigned | 003/2021 | 401.69
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 16.43
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 62.22
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 72.59
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 87.62
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 374.4
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 438.63
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 53.9
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 90.4
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 104.1
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | IT Device OH | Not assigned | 001/2021 | 9.34
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | IT Device OH | Not assigned | 002/2021 | 35.31
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | IT Device OH | Not assigned | 003/2021 | 41.2
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 73
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 122.45
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 141
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 95.98
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 109.69
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 32.35
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 122.5
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 142.92
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 002/2021 | 30000
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 003/2021 | -15000
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 004/2021 | -15000
35192293 | ECOP - MOLINO 1102 - H03-LR396 PH1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.92
35192293 | ECOP - MOLINO 1102 - H03-LR396 PH1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.47
35192293 | ECOP - MOLINO 1102 - H03-LR396 PH1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.47
35192293 | ECOP - MOLINO 1102 - H03-LR396 PH1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6.66
35192293 | ECOP - MOLINO 1102 - H03-LR396 PH1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6.66
35192293 | ECOP - MOLINO 1102 - H03-LR396 PH1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6.66
35192294 | ECOP - MOLINO 1102 - H03-LR396 PH2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.89
35192294 | ECOP - MOLINO 1102 - H03-LR396 PH2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.44
35192294 | ECOP - MOLINO 1102 - H03-LR396 PH2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.44
35192294 | ECOP - MOLINO 1102 - H03-LR396 PH2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6.58
35192294 | ECOP - MOLINO 1102 - H03-LR396 PH2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6.58
35192294 | ECOP - MOLINO 1102 - H03-LR396 PH2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6.58
35192295 | ECOP - RINCON 1103 - H02-LR198 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.9
35192295 | ECOP - RINCON 1103 - H02-LR198 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.45
35192295 | ECOP - RINCON 1103 - H02-LR198 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.45
35192295 | ECOP - RINCON 1103 - H02-LR198 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6.61
35192295 | ECOP - RINCON 1103 - H02-LR198 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6.61
35192295 | ECOP - RINCON 1103 - H02-LR198 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6.61
35192296 | ECOP - PINE GROVE 1102 - H06-LR83098 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3.19
35192296 | ECOP - PINE GROVE 1102 - H06-LR83098 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.7
35192296 | ECOP - PINE GROVE 1102 - H06-LR83098 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.7
35192296 | ECOP - PINE GROVE 1102 - H06-LR83098 | Other | AFUDC-Equity | Not assigned | 001/2021 | 7.27
35192296 | ECOP - PINE GROVE 1102 - H06-LR83098 | Other | AFUDC-Equity | Not assigned | 002/2021 | 7.27
35192296 | ECOP - PINE GROVE 1102 - H06-LR83098 | Other | AFUDC-Equity | Not assigned | 003/2021 | 7.27
35192297 | ECOP - PINE GROVE 1102 - H07-CB | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3.18
35192297 | ECOP - PINE GROVE 1102 - H07-CB | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.69
35192297 | ECOP - PINE GROVE 1102 - H07-CB | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.69
35192297 | ECOP - PINE GROVE 1102 - H07-CB | Other | AFUDC-Equity | Not assigned | 001/2021 | 7.27
35192297 | ECOP - PINE GROVE 1102 - H07-CB | Other | AFUDC-Equity | Not assigned | 002/2021 | 7.27
35192297 | ECOP - PINE GROVE 1102 - H07-CB | Other | AFUDC-Equity | Not assigned | 003/2021 | 7.27
35192298 | ECOP - SALT SPRINGS 2102 - H02-LR37300 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.9
35192298 | ECOP - SALT SPRINGS 2102 - H02-LR37300 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.45
35192298 | ECOP - SALT SPRINGS 2102 - H02-LR37300 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.45
35192298 | ECOP - SALT SPRINGS 2102 - H02-LR37300 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6.6
35192298 | ECOP - SALT SPRINGS 2102 - H02-LR37300 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6.6
35192298 | ECOP - SALT SPRINGS 2102 - H02-LR37300 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6.6
35192299 | ECOP - SALT SPRINGS 2102 - H04-LR97924 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.89
35192299 | ECOP - SALT SPRINGS 2102 - H04-LR97924 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.44
35192299 | ECOP - SALT SPRINGS 2102 - H04-LR97924 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.44
35192299 | ECOP - SALT SPRINGS 2102 - H04-LR97924 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6.58
35192299 | ECOP - SALT SPRINGS 2102 - H04-LR97924 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6.58
35192299 | ECOP - SALT SPRINGS 2102 - H04-LR97924 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6.58
35192300 | ECOP - WEST POINT 1101 - H04-TSL3355 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3.64
35192300 | ECOP - WEST POINT 1101 - H04-TSL3355 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 3.08
35192300 | ECOP - WEST POINT 1101 - H04-TSL3355 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3.08
35192300 | ECOP - WEST POINT 1101 - H04-TSL3355 | Other | AFUDC-Equity | Not assigned | 001/2021 | 8.3
35192300 | ECOP - WEST POINT 1101 - H04-TSL3355 | Other | AFUDC-Equity | Not assigned | 002/2021 | 8.3
35192300 | ECOP - WEST POINT 1101 - H04-TSL3355 | Other | AFUDC-Equity | Not assigned | 003/2021 | 8.3
35192301 | ECOP - WEST POINT 1102 - H06-LR36676 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.89
35192301 | ECOP - WEST POINT 1102 - H06-LR36676 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.44
35192301 | ECOP - WEST POINT 1102 - H06-LR36676 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.44
35192301 | ECOP - WEST POINT 1102 - H06-LR36676 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6.58
35192301 | ECOP - WEST POINT 1102 - H06-LR36676 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6.58
35192301 | ECOP - WEST POINT 1102 - H06-LR36676 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6.58
35192302 | ECOP - WEST POINT 1102 - H07-LR93116 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.89
35192302 | ECOP - WEST POINT 1102 - H07-LR93116 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.44
35192302 | ECOP - WEST POINT 1102 - H07-LR93116 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.44
35192302 | ECOP - WEST POINT 1102 - H07-LR93116 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6.58
35192302 | ECOP - WEST POINT 1102 - H07-LR93116 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6.58
35192302 | ECOP - WEST POINT 1102 - H07-LR93116 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6.58
35192303 | ECOP - MARIPOSA 2101 - H01-LR10170 PH1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.89
35192303 | ECOP - MARIPOSA 2101 - H01-LR10170 PH1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.44
35192303 | ECOP - MARIPOSA 2101 - H01-LR10170 PH1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.44
35192303 | ECOP - MARIPOSA 2101 - H01-LR10170 PH1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6.58
35192303 | ECOP - MARIPOSA 2101 - H01-LR10170 PH1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6.58
35192303 | ECOP - MARIPOSA 2101 - H01-LR10170 PH1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6.58
35192304 | ECOP - MARIPOSA 2101 - H01-LR10170 PH2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.89
35192304 | ECOP - MARIPOSA 2101 - H01-LR10170 PH2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.44
35192304 | ECOP - MARIPOSA 2101 - H01-LR10170 PH2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.44
35192304 | ECOP - MARIPOSA 2101 - H01-LR10170 PH2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6.58
35192304 | ECOP - MARIPOSA 2101 - H01-LR10170 PH2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6.58
35192304 | ECOP - MARIPOSA 2101 - H01-LR10170 PH2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6.58
35192305 | ECOP - MIWUK 1702 - H01-LR8130 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.89
35192305 | ECOP - MIWUK 1702 - H01-LR8130 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.44
35192305 | ECOP - MIWUK 1702 - H01-LR8130 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.44
35192305 | ECOP - MIWUK 1702 - H01-LR8130 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6.58
35192305 | ECOP - MIWUK 1702 - H01-LR8130 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6.58
35192305 | ECOP - MIWUK 1702 - H01-LR8130 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6.58
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 129.6
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Labor Internal | Administrative Services - OT | Not assigned | 001/2021 | 88.01
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 1276.15
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 1416.17
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 1435.3
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 618.13
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 2041.2
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 1944
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 1004.4
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 001/2021 | 1879.2
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 842.4
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 615.6
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 807.29
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 818.2
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 352.37
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 11.37
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 27.98
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 40.52
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 29.46
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 75.51
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 109.34
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | Benefits OH | Not assigned | 001/2021 | 1373.7
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | Benefits OH | Not assigned | 002/2021 | 1392.27
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | Benefits OH | Not assigned | 003/2021 | 569.36
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | Building Service Overhead | Not assigned | 001/2021 | 235.76
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | Building Service Overhead | Not assigned | 002/2021 | 238.95
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | Building Service Overhead | Not assigned | 003/2021 | 102.9
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | Capitalized A&G | Not assigned | 001/2021 | 1475.9
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | Capitalized A&G | Not assigned | 002/2021 | 1495.83
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | Capitalized A&G | Not assigned | 003/2021 | 644.21
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | IT Device OH | Not assigned | 001/2021 | 133.81
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | IT Device OH | Not assigned | 002/2021 | 135.62
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | IT Device OH | Not assigned | 003/2021 | 58.42
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | Lodging | JEFFREY G RUDNICK | 003/2021 | 280.24
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | Meals Expense | JEFFREY G RUDNICK | 003/2021 | 65.37
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 848.18
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 859.64
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 370.21
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 464.11
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 470.38
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 202.58
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 4125.1
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -4125.1
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 6.75
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 6.21
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.96
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 | Other | AFUDC-Equity | Not assigned | 001/2021 | 16.75
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 | Other | AFUDC-Equity | Not assigned | 002/2021 | 16.75
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 | Other | AFUDC-Equity | Not assigned | 003/2021 | 7.99
35212401 | FRRB - MONTICELLO 1101 CB | Contract | Contracts | Not assigned | 001/2021 | -45250000
35212401 | FRRB - MONTICELLO 1101 CB | Contract | Contracts | Not assigned | 002/2021 | 29674441.66
35212401 | FRRB - MONTICELLO 1101 CB | Contract | Contracts | Not assigned | 003/2021 | -3252662.66
35212401 | FRRB - MONTICELLO 1101 CB | Contract | Contracts | Not assigned | 004/2021 | -26421779
35212401 | FRRB - MONTICELLO 1101 CB | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -46019.25
35212401 | FRRB - MONTICELLO 1101 CB | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 30178.91
35212401 | FRRB - MONTICELLO 1101 CB | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | -3307.96
35212401 | FRRB - MONTICELLO 1101 CB | Labor Internal | Mapping | Not assigned | 001/2021 | -135750
35212401 | FRRB - MONTICELLO 1101 CB | Labor Internal | Mapping | Not assigned | 002/2021 | 89023.32
35212401 | FRRB - MONTICELLO 1101 CB | Labor Internal | Mapping | Not assigned | 003/2021 | -9757.99
35212401 | FRRB - MONTICELLO 1101 CB | Labor Internal | Paid Time Off | Not assigned | 001/2021 | -27340.05
35212401 | FRRB - MONTICELLO 1101 CB | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 17929.3
35212401 | FRRB - MONTICELLO 1101 CB | Labor Internal | Paid Time Off | Not assigned | 003/2021 | -1965.26
35212401 | FRRB - MONTICELLO 1101 CB | Materials | Material Burden | Not assigned | 001/2021 | -2010850.55
35212401 | FRRB - MONTICELLO 1101 CB | Materials | Material Burden | Not assigned | 002/2021 | 1084000.94
35212401 | FRRB - MONTICELLO 1101 CB | Materials | Material Burden | Not assigned | 003/2021 | -287174.85
35212401 | FRRB - MONTICELLO 1101 CB | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 001/2021 | -13772949
35212401 | FRRB - MONTICELLO 1101 CB | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 7424664
35212401 | FRRB - MONTICELLO 1101 CB | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | -1966951
35212401 | FRRB - MONTICELLO 1101 CB | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 004/2021 | -5457713
35212401 | FRRB - MONTICELLO 1101 CB | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 65648.53
35212401 | FRRB - MONTICELLO 1101 CB | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 32568.13
35212401 | FRRB - MONTICELLO 1101 CB | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 59041.72
35212401 | FRRB - MONTICELLO 1101 CB | Other | AFUDC-Equity | Not assigned | 001/2021 | 138459.89
35212401 | FRRB - MONTICELLO 1101 CB | Other | AFUDC-Equity | Not assigned | 002/2021 | 87882.26
35212401 | FRRB - MONTICELLO 1101 CB | Other | AFUDC-Equity | Not assigned | 003/2021 | 159318.94
35212401 | FRRB - MONTICELLO 1101 CB | Other | Benefits OH | Not assigned | 001/2021 | -444775.8
35212401 | FRRB - MONTICELLO 1101 CB | Other | Benefits OH | Not assigned | 002/2021 | 246142.64
35212401 | FRRB - MONTICELLO 1101 CB | Other | Benefits OH | Not assigned | 003/2021 | -56637.28
35212401 | FRRB - MONTICELLO 1101 CB | Other | Building Service Overhead | Not assigned | 001/2021 | -76335.43
35212401 | FRRB - MONTICELLO 1101 CB | Other | Building Service Overhead | Not assigned | 002/2021 | 42244.67
35212401 | FRRB - MONTICELLO 1101 CB | Other | Building Service Overhead | Not assigned | 003/2021 | -10236.75
35212401 | FRRB - MONTICELLO 1101 CB | Other | Capitalized A&G | Not assigned | 001/2021 | -49983.15
35212401 | FRRB - MONTICELLO 1101 CB | Other | Capitalized A&G | Not assigned | 002/2021 | 32778.39
35212401 | FRRB - MONTICELLO 1101 CB | Other | Capitalized A&G | Not assigned | 003/2021 | -3592.89
35212401 | FRRB - MONTICELLO 1101 CB | Other | Fleet OH - Elec | Not assigned | 001/2021 | -30747.38
35212401 | FRRB - MONTICELLO 1101 CB | Other | Fleet OH - Elec | Not assigned | 002/2021 | 20163.78
35212401 | FRRB - MONTICELLO 1101 CB | Other | Fleet OH - Elec | Not assigned | 003/2021 | -2210.18
35212401 | FRRB - MONTICELLO 1101 CB | Other | IT Device OH | Not assigned | 001/2021 | -43325.53
35212401 | FRRB - MONTICELLO 1101 CB | Other | IT Device OH | Not assigned | 002/2021 | 23976.7
35212401 | FRRB - MONTICELLO 1101 CB | Other | IT Device OH | Not assigned | 003/2021 | -5810.05
35212401 | FRRB - MONTICELLO 1101 CB | Other | Minor Material OH | Not assigned | 001/2021 | -1122228.14
35212401 | FRRB - MONTICELLO 1101 CB | Other | Minor Material OH | Not assigned | 002/2021 | 604966.08
35212401 | FRRB - MONTICELLO 1101 CB | Other | Minor Material OH | Not assigned | 003/2021 | -160268.35
35212401 | FRRB - MONTICELLO 1101 CB | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -41648.1
35212401 | FRRB - MONTICELLO 1101 CB | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 27312.35
35212401 | FRRB - MONTICELLO 1101 CB | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | -2993.75
35212401 | FRRB - MONTICELLO 1101 CB | Other | Payroll Taxes OH | Not assigned | 001/2021 | -150268.62
35212401 | FRRB - MONTICELLO 1101 CB | Other | Payroll Taxes OH | Not assigned | 002/2021 | 83159.9
35212401 | FRRB - MONTICELLO 1101 CB | Other | Payroll Taxes OH | Not assigned | 003/2021 | -20151.36
35212402 | FRRB - MONTICELLO 1101 LR 666 | Contract | Contracts | Not assigned | 003/2021 | 31742.85
35212402 | FRRB - MONTICELLO 1101 LR 666 | Labor Internal | Electric Activity Charge - Non-Type A | Not assigned | 003/2021 | -63.76
35212402 | FRRB - MONTICELLO 1101 LR 666 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 1118.3
35212402 | FRRB - MONTICELLO 1101 LR 666 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 1.12
35212402 | FRRB - MONTICELLO 1101 LR 666 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 003/2021 | 118.87
35212402 | FRRB - MONTICELLO 1101 LR 666 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 411.38
35212402 | FRRB - MONTICELLO 1101 LR 666 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 0.4
35212402 | FRRB - MONTICELLO 1101 LR 666 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 43.01
35212402 | FRRB - MONTICELLO 1101 LR 666 | Labor Internal | Mapping | Not assigned | 003/2021 | 95.23
35212402 | FRRB - MONTICELLO 1101 LR 666 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 268.57
35212402 | FRRB - MONTICELLO 1101 LR 666 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 003/2021 | -2207.72
35212402 | FRRB - MONTICELLO 1101 LR 666 | Materials | Construction Supplies | Not assigned | 003/2021 | 1.32
35212402 | FRRB - MONTICELLO 1101 LR 666 | Materials | Fabricated Structures | Not assigned | 003/2021 | 58.37
35212402 | FRRB - MONTICELLO 1101 LR 666 | Materials | Material Burden | Not assigned | 003/2021 | -487.31
35212402 | FRRB - MONTICELLO 1101 LR 666 | Materials | Materials Not Otherwise Classified | Not assigned | 003/2021 | -117.06
35212402 | FRRB - MONTICELLO 1101 LR 666 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | -1018.24
35212402 | FRRB - MONTICELLO 1101 LR 666 | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 003/2021 | 0.12
35212402 | FRRB - MONTICELLO 1101 LR 666 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 4605.88
35212402 | FRRB - MONTICELLO 1101 LR 666 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4216.54
35212402 | FRRB - MONTICELLO 1101 LR 666 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 4240.67
35212402 | FRRB - MONTICELLO 1101 LR 666 | Other | AFUDC-Equity | Not assigned | 001/2021 | 11377.96
35212402 | FRRB - MONTICELLO 1101 LR 666 | Other | AFUDC-Equity | Not assigned | 002/2021 | 11377.96
35212402 | FRRB - MONTICELLO 1101 LR 666 | Other | AFUDC-Equity | Not assigned | 003/2021 | 11443.07
35212402 | FRRB - MONTICELLO 1101 LR 666 | Other | Benefits OH | Not assigned | 003/2021 | 409.37
35212402 | FRRB - MONTICELLO 1101 LR 666 | Other | Building Service Overhead | Not assigned | 003/2021 | 73.98
35212402 | FRRB - MONTICELLO 1101 LR 666 | Other | Capitalized A&G | Not assigned | 003/2021 | 467.52
35212402 | FRRB - MONTICELLO 1101 LR 666 | Other | Cost Adjustments | Not assigned | 003/2021 | -911.25
35212402 | FRRB - MONTICELLO 1101 LR 666 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 260.42
35212402 | FRRB - MONTICELLO 1101 LR 666 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 36.81
35212402 | FRRB - MONTICELLO 1101 LR 666 | Other | IT Device OH | Not assigned | 003/2021 | 42
35212402 | FRRB - MONTICELLO 1101 LR 666 | Other | Minor Material OH | Not assigned | 003/2021 | -268.09
35212402 | FRRB - MONTICELLO 1101 LR 666 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 352.75
35212402 | FRRB - MONTICELLO 1101 LR 666 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 0.24
35212402 | FRRB - MONTICELLO 1101 LR 666 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 65.95
35212402 | FRRB - MONTICELLO 1101 LR 666 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 145.65
35212403 | FRRB - MONTICELLO 1101 LR 654 | Contract | Contracts | Not assigned | 003/2021 | 37344.53
35212403 | FRRB - MONTICELLO 1101 LR 654 | Labor Internal | Electric Activity Charge - Non-Type A | Not assigned | 003/2021 | -75.01
35212403 | FRRB - MONTICELLO 1101 LR 654 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 1315.65
35212403 | FRRB - MONTICELLO 1101 LR 654 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 1.31
35212403 | FRRB - MONTICELLO 1101 LR 654 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 003/2021 | 139.85
35212403 | FRRB - MONTICELLO 1101 LR 654 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 483.99
35212403 | FRRB - MONTICELLO 1101 LR 654 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 0.46
35212403 | FRRB - MONTICELLO 1101 LR 654 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 50.6
35212403 | FRRB - MONTICELLO 1101 LR 654 | Labor Internal | Mapping | Not assigned | 003/2021 | 112.03
35212403 | FRRB - MONTICELLO 1101 LR 654 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 315.96
35212403 | FRRB - MONTICELLO 1101 LR 654 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 003/2021 | -2597.32
35212403 | FRRB - MONTICELLO 1101 LR 654 | Materials | Construction Supplies | Not assigned | 003/2021 | 1.55
35212403 | FRRB - MONTICELLO 1101 LR 654 | Materials | Fabricated Structures | Not assigned | 003/2021 | 68.67
35212403 | FRRB - MONTICELLO 1101 LR 654 | Materials | Material Burden | Not assigned | 003/2021 | -573.3
35212403 | FRRB - MONTICELLO 1101 LR 654 | Materials | Materials Not Otherwise Classified | Not assigned | 003/2021 | -137.72
35212403 | FRRB - MONTICELLO 1101 LR 654 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | -1197.93
35212403 | FRRB - MONTICELLO 1101 LR 654 | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 003/2021 | 0.14
35212403 | FRRB - MONTICELLO 1101 LR 654 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 5418.68
35212403 | FRRB - MONTICELLO 1101 LR 654 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4960.63
35212403 | FRRB - MONTICELLO 1101 LR 654 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 4989.02
35212403 | FRRB - MONTICELLO 1101 LR 654 | Other | AFUDC-Equity | Not assigned | 001/2021 | 13385.84
35212403 | FRRB - MONTICELLO 1101 LR 654 | Other | AFUDC-Equity | Not assigned | 002/2021 | 13385.84
35212403 | FRRB - MONTICELLO 1101 LR 654 | Other | AFUDC-Equity | Not assigned | 003/2021 | 13462.44
35212403 | FRRB - MONTICELLO 1101 LR 654 | Other | Benefits OH | Not assigned | 003/2021 | 481.62
35212403 | FRRB - MONTICELLO 1101 LR 654 | Other | Building Service Overhead | Not assigned | 003/2021 | 87.04
35212403 | FRRB - MONTICELLO 1101 LR 654 | Other | Capitalized A&G | Not assigned | 003/2021 | 550.03
35212403 | FRRB - MONTICELLO 1101 LR 654 | Other | Cost Adjustments | Not assigned | 003/2021 | -1072.06
35212403 | FRRB - MONTICELLO 1101 LR 654 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 306.37
35212403 | FRRB - MONTICELLO 1101 LR 654 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 43.31
35212403 | FRRB - MONTICELLO 1101 LR 654 | Other | IT Device OH | Not assigned | 003/2021 | 49.41
35212403 | FRRB - MONTICELLO 1101 LR 654 | Other | Minor Material OH | Not assigned | 003/2021 | -315.39
35212403 | FRRB - MONTICELLO 1101 LR 654 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 415
35212403 | FRRB - MONTICELLO 1101 LR 654 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 0.28
35212403 | FRRB - MONTICELLO 1101 LR 654 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 77.59
35212403 | FRRB - MONTICELLO 1101 LR 654 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 171.36
35212404 | FRRB - MONTICELLO 1101 LR 630 | Contract | Contracts | Not assigned | 003/2021 | 51308.13
35212404 | FRRB - MONTICELLO 1101 LR 630 | Labor Internal | Electric Activity Charge - Non-Type A | Not assigned | 003/2021 | -103.06
35212404 | FRRB - MONTICELLO 1101 LR 630 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 1807.59
35212404 | FRRB - MONTICELLO 1101 LR 630 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 1.8
35212404 | FRRB - MONTICELLO 1101 LR 630 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 003/2021 | 192.14
35212404 | FRRB - MONTICELLO 1101 LR 630 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 664.95
35212404 | FRRB - MONTICELLO 1101 LR 630 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 0.64
35212404 | FRRB - MONTICELLO 1101 LR 630 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 69.52
35212404 | FRRB - MONTICELLO 1101 LR 630 | Labor Internal | Mapping | Not assigned | 003/2021 | 153.92
35212404 | FRRB - MONTICELLO 1101 LR 630 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 434.11
35212404 | FRRB - MONTICELLO 1101 LR 630 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 003/2021 | -3568.49
35212404 | FRRB - MONTICELLO 1101 LR 630 | Materials | Construction Supplies | Not assigned | 003/2021 | 2.13
35212404 | FRRB - MONTICELLO 1101 LR 630 | Materials | Fabricated Structures | Not assigned | 003/2021 | 94.35
35212404 | FRRB - MONTICELLO 1101 LR 630 | Materials | Material Burden | Not assigned | 003/2021 | -787.66
35212404 | FRRB - MONTICELLO 1101 LR 630 | Materials | Materials Not Otherwise Classified | Not assigned | 003/2021 | -189.22
35212404 | FRRB - MONTICELLO 1101 LR 630 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | -1645.85
35212404 | FRRB - MONTICELLO 1101 LR 630 | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 003/2021 | 0.19
35212404 | FRRB - MONTICELLO 1101 LR 630 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 7444.8
35212404 | FRRB - MONTICELLO 1101 LR 630 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 6815.48
35212404 | FRRB - MONTICELLO 1101 LR 630 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 6854.48
35212404 | FRRB - MONTICELLO 1101 LR 630 | Other | AFUDC-Equity | Not assigned | 001/2021 | 18390.98
35212404 | FRRB - MONTICELLO 1101 LR 630 | Other | AFUDC-Equity | Not assigned | 002/2021 | 18390.98
35212404 | FRRB - MONTICELLO 1101 LR 630 | Other | AFUDC-Equity | Not assigned | 003/2021 | 18496.22
35212404 | FRRB - MONTICELLO 1101 LR 630 | Other | Benefits OH | Not assigned | 003/2021 | 661.71
35212404 | FRRB - MONTICELLO 1101 LR 630 | Other | Building Service Overhead | Not assigned | 003/2021 | 119.61
35212404 | FRRB - MONTICELLO 1101 LR 630 | Other | Capitalized A&G | Not assigned | 003/2021 | 755.69
35212404 | FRRB - MONTICELLO 1101 LR 630 | Other | Cost Adjustments | Not assigned | 003/2021 | -1472.92
35212404 | FRRB - MONTICELLO 1101 LR 630 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 420.94
35212404 | FRRB - MONTICELLO 1101 LR 630 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 59.51
35212404 | FRRB - MONTICELLO 1101 LR 630 | Other | IT Device OH | Not assigned | 003/2021 | 67.89
35212404 | FRRB - MONTICELLO 1101 LR 630 | Other | Minor Material OH | Not assigned | 003/2021 | -433.32
35212404 | FRRB - MONTICELLO 1101 LR 630 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 570.17
35212404 | FRRB - MONTICELLO 1101 LR 630 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 0.38
35212404 | FRRB - MONTICELLO 1101 LR 630 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 106.6
35212404 | FRRB - MONTICELLO 1101 LR 630 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 235.43
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Contract | Contracts | Not assigned | 003/2021 | 106188.35
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Labor Internal | Electric Activity Charge - Non-Type A | Not assigned | 003/2021 | -213.29
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 3741.02
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 3.73
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 003/2021 | 397.66
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1376.21
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 1.32
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 143.87
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Labor Internal | Mapping | Not assigned | 003/2021 | 318.57
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 898.44
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 003/2021 | -7385.41
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Materials | Construction Supplies | Not assigned | 003/2021 | 4.4
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Materials | Fabricated Structures | Not assigned | 003/2021 | 195.26
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Materials | Material Burden | Not assigned | 003/2021 | -1630.16
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Materials | Materials Not Otherwise Classified | Not assigned | 003/2021 | -391.61
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | -3406.29
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 003/2021 | 0.39
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 15407.91
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 14105.45
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 14186.17
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Other | AFUDC-Equity | Not assigned | 001/2021 | 38062.34
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Other | AFUDC-Equity | Not assigned | 002/2021 | 38062.34
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Other | AFUDC-Equity | Not assigned | 003/2021 | 38280.15
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Other | Benefits OH | Not assigned | 003/2021 | 1369.49
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Other | Building Service Overhead | Not assigned | 003/2021 | 247.53
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Other | Capitalized A&G | Not assigned | 003/2021 | 1564
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Other | Cost Adjustments | Not assigned | 003/2021 | -3048.39
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 871.19
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 123.16
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Other | IT Device OH | Not assigned | 003/2021 | 140.48
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Other | Minor Material OH | Not assigned | 003/2021 | -896.81
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1180.05
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 0.79
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 220.62
35212405 | FRRB - MONTICELLO 1101 LR 93384 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 487.26
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Contract | Contracts | Not assigned | 003/2021 | 12583.48
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Labor Internal | Electric Activity Charge - Non-Type A | Not assigned | 003/2021 | -25.28
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 443.32
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 0.44
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 003/2021 | 47.12
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 163.09
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 0.16
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 17.05
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Labor Internal | Mapping | Not assigned | 003/2021 | 37.75
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 106.46
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 003/2021 | -875.18
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Materials | Construction Supplies | Not assigned | 003/2021 | 0.52
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Materials | Fabricated Structures | Not assigned | 003/2021 | 23.14
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Materials | Material Burden | Not assigned | 003/2021 | -193.18
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Materials | Materials Not Otherwise Classified | Not assigned | 003/2021 | -46.41
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | -403.65
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 003/2021 | 0.05
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1825.86
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1671.52
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1681.08
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Other | AFUDC-Equity | Not assigned | 001/2021 | 4510.44
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Other | AFUDC-Equity | Not assigned | 002/2021 | 4510.44
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4536.26
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Other | Benefits OH | Not assigned | 003/2021 | 162.27
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Other | Building Service Overhead | Not assigned | 003/2021 | 29.33
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Other | Capitalized A&G | Not assigned | 003/2021 | 185.33
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Other | Cost Adjustments | Not assigned | 003/2021 | -361.24
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 103.24
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 14.59
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Other | IT Device OH | Not assigned | 003/2021 | 16.64
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Other | Minor Material OH | Not assigned | 003/2021 | -106.28
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 139.83
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 0.09
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 26.14
35212406 | FRRB - MONTICELLO 1101 LR 37384 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 57.72
35212407 | FRRB - SILVERADO 2102 LR 636 | Contract | Contracts | Not assigned | 003/2021 | 57190.91
35212407 | FRRB - SILVERADO 2102 LR 636 | Labor External | Contractor Activity Charges | Not assigned | 003/2021 | 2.95
35212407 | FRRB - SILVERADO 2102 LR 636 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 15.36
35212407 | FRRB - SILVERADO 2102 LR 636 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 69.35
35212407 | FRRB - SILVERADO 2102 LR 636 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 63.37
35212407 | FRRB - SILVERADO 2102 LR 636 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 24.5
35212407 | FRRB - SILVERADO 2102 LR 636 | Labor Internal | Mapping | Not assigned | 003/2021 | 171.57
35212407 | FRRB - SILVERADO 2102 LR 636 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 51.61
35212407 | FRRB - SILVERADO 2102 LR 636 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 599.85
35212407 | FRRB - SILVERADO 2102 LR 636 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 549.14
35212407 | FRRB - SILVERADO 2102 LR 636 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 596.75
35212407 | FRRB - SILVERADO 2102 LR 636 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1481.81
35212407 | FRRB - SILVERADO 2102 LR 636 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1481.81
35212407 | FRRB - SILVERADO 2102 LR 636 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1610.29
35212407 | FRRB - SILVERADO 2102 LR 636 | Other | Benefits OH | Not assigned | 003/2021 | 94
35212407 | FRRB - SILVERADO 2102 LR 636 | Other | Building Service Overhead | Not assigned | 003/2021 | 17.09
35212407 | FRRB - SILVERADO 2102 LR 636 | Other | Capitalized A&G | Not assigned | 003/2021 | 94.42
35212407 | FRRB - SILVERADO 2102 LR 636 | Other | Cost Adjustments | Not assigned | 003/2021 | 2508.93
35212407 | FRRB - SILVERADO 2102 LR 636 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 42.34
35212407 | FRRB - SILVERADO 2102 LR 636 | Other | IT Device OH | Not assigned | 003/2021 | 9.7
35212407 | FRRB - SILVERADO 2102 LR 636 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 57.35
35212407 | FRRB - SILVERADO 2102 LR 636 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 14.67
35212407 | FRRB - SILVERADO 2102 LR 636 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 33.45
35212408 | FRRB - SILVERADO 2102 LR 34959 | Contract | Contracts | Not assigned | 003/2021 | 159622.4
35212408 | FRRB - SILVERADO 2102 LR 34959 | Labor External | Contractor Activity Charges | Not assigned | 003/2021 | 8.22
35212408 | FRRB - SILVERADO 2102 LR 34959 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 42.87
35212408 | FRRB - SILVERADO 2102 LR 34959 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 193.55
35212408 | FRRB - SILVERADO 2102 LR 34959 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 176.87
35212408 | FRRB - SILVERADO 2102 LR 34959 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 68.38
35212408 | FRRB - SILVERADO 2102 LR 34959 | Labor Internal | Mapping | Not assigned | 003/2021 | 478.87
35212408 | FRRB - SILVERADO 2102 LR 34959 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 144.05
35212408 | FRRB - SILVERADO 2102 LR 34959 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1671.59
35212408 | FRRB - SILVERADO 2102 LR 34959 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1530.29
35212408 | FRRB - SILVERADO 2102 LR 34959 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1663.19
35212408 | FRRB - SILVERADO 2102 LR 34959 | Other | AFUDC-Equity | Not assigned | 001/2021 | 4129.37
35212408 | FRRB - SILVERADO 2102 LR 34959 | Other | AFUDC-Equity | Not assigned | 002/2021 | 4129.37
35212408 | FRRB - SILVERADO 2102 LR 34959 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4487.96
35212408 | FRRB - SILVERADO 2102 LR 34959 | Other | Benefits OH | Not assigned | 003/2021 | 262.39
35212408 | FRRB - SILVERADO 2102 LR 34959 | Other | Building Service Overhead | Not assigned | 003/2021 | 47.69
35212408 | FRRB - SILVERADO 2102 LR 34959 | Other | Capitalized A&G | Not assigned | 003/2021 | 263.55
35212408 | FRRB - SILVERADO 2102 LR 34959 | Other | Cost Adjustments | Not assigned | 003/2021 | 7002.53
35212408 | FRRB - SILVERADO 2102 LR 34959 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 118.17
35212408 | FRRB - SILVERADO 2102 LR 34959 | Other | IT Device OH | Not assigned | 003/2021 | 27.06
35212408 | FRRB - SILVERADO 2102 LR 34959 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 160.07
35212408 | FRRB - SILVERADO 2102 LR 34959 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 40.96
35212408 | FRRB - SILVERADO 2102 LR 34959 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 93.36
35212409 | FRRB - SILVERADO 2104 LR 645 | Contract | Contracts | Not assigned | 003/2021 | 384118.07
35212409 | FRRB - SILVERADO 2104 LR 645 | Labor External | Contractor Activity Charges | Not assigned | 003/2021 | 19.78
35212409 | FRRB - SILVERADO 2104 LR 645 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 103.16
35212409 | FRRB - SILVERADO 2104 LR 645 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 465.77
35212409 | FRRB - SILVERADO 2104 LR 645 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 425.62
35212409 | FRRB - SILVERADO 2104 LR 645 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 164.56
35212409 | FRRB - SILVERADO 2104 LR 645 | Labor Internal | Mapping | Not assigned | 003/2021 | 1152.35
35212409 | FRRB - SILVERADO 2104 LR 645 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 346.66
35212409 | FRRB - SILVERADO 2104 LR 645 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 319.79
35212409 | FRRB - SILVERADO 2104 LR 645 | Other | AFUDC-Equity | Not assigned | 003/2021 | 862.93
35212409 | FRRB - SILVERADO 2104 LR 645 | Other | Benefits OH | Not assigned | 003/2021 | 631.44
35212409 | FRRB - SILVERADO 2104 LR 645 | Other | Building Service Overhead | Not assigned | 003/2021 | 114.75
35212409 | FRRB - SILVERADO 2104 LR 645 | Other | Capitalized A&G | Not assigned | 003/2021 | 634.2
35212409 | FRRB - SILVERADO 2104 LR 645 | Other | Cost Adjustments | Not assigned | 003/2021 | 16851.01
35212409 | FRRB - SILVERADO 2104 LR 645 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 284.38
35212409 | FRRB - SILVERADO 2104 LR 645 | Other | IT Device OH | Not assigned | 003/2021 | 65.14
35212409 | FRRB - SILVERADO 2104 LR 645 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 385.19
35212409 | FRRB - SILVERADO 2104 LR 645 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 98.56
35212409 | FRRB - SILVERADO 2104 LR 645 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 224.65
35212410 | FRRB - SILVERADO 2104 LR 708 | Contract | Contracts | Not assigned | 003/2021 | 63166.08
35212410 | FRRB - SILVERADO 2104 LR 708 | Labor External | Contractor Activity Charges | Not assigned | 003/2021 | 3.25
35212410 | FRRB - SILVERADO 2104 LR 708 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 16.96
35212410 | FRRB - SILVERADO 2104 LR 708 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 76.59
35212410 | FRRB - SILVERADO 2104 LR 708 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 69.99
35212410 | FRRB - SILVERADO 2104 LR 708 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 27.06
35212410 | FRRB - SILVERADO 2104 LR 708 | Labor Internal | Mapping | Not assigned | 003/2021 | 189.5
35212410 | FRRB - SILVERADO 2104 LR 708 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 57.01
35212410 | FRRB - SILVERADO 2104 LR 708 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 661.32
35212410 | FRRB - SILVERADO 2104 LR 708 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 605.42
35212410 | FRRB - SILVERADO 2104 LR 708 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 658.01
35212410 | FRRB - SILVERADO 2104 LR 708 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1633.69
35212410 | FRRB - SILVERADO 2104 LR 708 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1633.69
35212410 | FRRB - SILVERADO 2104 LR 708 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1775.59
35212410 | FRRB - SILVERADO 2104 LR 708 | Other | Benefits OH | Not assigned | 003/2021 | 103.82
35212410 | FRRB - SILVERADO 2104 LR 708 | Other | Building Service Overhead | Not assigned | 003/2021 | 18.86
35212410 | FRRB - SILVERADO 2104 LR 708 | Other | Capitalized A&G | Not assigned | 003/2021 | 104.29
35212410 | FRRB - SILVERADO 2104 LR 708 | Other | Cost Adjustments | Not assigned | 003/2021 | 2771.05
35212410 | FRRB - SILVERADO 2104 LR 708 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 46.76
35212410 | FRRB - SILVERADO 2104 LR 708 | Other | IT Device OH | Not assigned | 003/2021 | 10.71
35212410 | FRRB - SILVERADO 2104 LR 708 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 63.34
35212410 | FRRB - SILVERADO 2104 LR 708 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 16.21
35212410 | FRRB - SILVERADO 2104 LR 708 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 36.95
35212411 | FRRB - SILVERADO 2104 LR 722 | Contract | Contracts | Not assigned | 003/2021 | 324366.37
35212411 | FRRB - SILVERADO 2104 LR 722 | Labor External | Contractor Activity Charges | Not assigned | 003/2021 | 16.71
35212411 | FRRB - SILVERADO 2104 LR 722 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 87.11
35212411 | FRRB - SILVERADO 2104 LR 722 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 393.32
35212411 | FRRB - SILVERADO 2104 LR 722 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 359.41
35212411 | FRRB - SILVERADO 2104 LR 722 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 138.96
35212411 | FRRB - SILVERADO 2104 LR 722 | Labor Internal | Mapping | Not assigned | 003/2021 | 973.1
35212411 | FRRB - SILVERADO 2104 LR 722 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 292.74
35212411 | FRRB - SILVERADO 2104 LR 722 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 270.05
35212411 | FRRB - SILVERADO 2104 LR 722 | Other | AFUDC-Equity | Not assigned | 003/2021 | 728.7
35212411 | FRRB - SILVERADO 2104 LR 722 | Other | Benefits OH | Not assigned | 003/2021 | 533.2
35212411 | FRRB - SILVERADO 2104 LR 722 | Other | Building Service Overhead | Not assigned | 003/2021 | 96.89
35212411 | FRRB - SILVERADO 2104 LR 722 | Other | Capitalized A&G | Not assigned | 003/2021 | 535.55
35212411 | FRRB - SILVERADO 2104 LR 722 | Other | Cost Adjustments | Not assigned | 003/2021 | 14229.74
35212411 | FRRB - SILVERADO 2104 LR 722 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 240.14
35212411 | FRRB - SILVERADO 2104 LR 722 | Other | IT Device OH | Not assigned | 003/2021 | 55
35212411 | FRRB - SILVERADO 2104 LR 722 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 325.28
35212411 | FRRB - SILVERADO 2104 LR 722 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 83.23
35212411 | FRRB - SILVERADO 2104 LR 722 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 189.72
35212412 | FRRB - SILVERADO 2104 LR 37632 | Contract | Contracts | Not assigned | 003/2021 | 422529.88
35212412 | FRRB - SILVERADO 2104 LR 37632 | Labor External | Contractor Activity Charges | Not assigned | 003/2021 | 21.76
35212412 | FRRB - SILVERADO 2104 LR 37632 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 113.47
35212412 | FRRB - SILVERADO 2104 LR 37632 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 512.35
35212412 | FRRB - SILVERADO 2104 LR 37632 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 468.18
35212412 | FRRB - SILVERADO 2104 LR 37632 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 181.01
35212412 | FRRB - SILVERADO 2104 LR 37632 | Labor Internal | Mapping | Not assigned | 003/2021 | 1267.59
35212412 | FRRB - SILVERADO 2104 LR 37632 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 381.33
35212412 | FRRB - SILVERADO 2104 LR 37632 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 4426.58
35212412 | FRRB - SILVERADO 2104 LR 37632 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4052.39
35212412 | FRRB - SILVERADO 2104 LR 37632 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 4404.16
35212412 | FRRB - SILVERADO 2104 LR 37632 | Other | AFUDC-Equity | Not assigned | 001/2021 | 10935.02
35212412 | FRRB - SILVERADO 2104 LR 37632 | Other | AFUDC-Equity | Not assigned | 002/2021 | 10935.02
35212412 | FRRB - SILVERADO 2104 LR 37632 | Other | AFUDC-Equity | Not assigned | 003/2021 | 11884.24
35212412 | FRRB - SILVERADO 2104 LR 37632 | Other | Benefits OH | Not assigned | 003/2021 | 694.58
35212412 | FRRB - SILVERADO 2104 LR 37632 | Other | Building Service Overhead | Not assigned | 003/2021 | 126.23
35212412 | FRRB - SILVERADO 2104 LR 37632 | Other | Capitalized A&G | Not assigned | 003/2021 | 697.63
35212412 | FRRB - SILVERADO 2104 LR 37632 | Other | Cost Adjustments | Not assigned | 003/2021 | 18536.11
35212412 | FRRB - SILVERADO 2104 LR 37632 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 312.81
35212412 | FRRB - SILVERADO 2104 LR 37632 | Other | IT Device OH | Not assigned | 003/2021 | 71.65
35212412 | FRRB - SILVERADO 2104 LR 37632 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 423.71
35212412 | FRRB - SILVERADO 2104 LR 37632 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 108.41
35212412 | FRRB - SILVERADO 2104 LR 37632 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 247.13
35212413 | FRRB - SILVERADO 2105 LR 658898 | Contract | Contracts | Not assigned | 003/2021 | 172938.49
35212413 | FRRB - SILVERADO 2105 LR 658898 | Labor External | Contractor Activity Charges | Not assigned | 003/2021 | 8.91
35212413 | FRRB - SILVERADO 2105 LR 658898 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 46.44
35212413 | FRRB - SILVERADO 2105 LR 658898 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 209.7
35212413 | FRRB - SILVERADO 2105 LR 658898 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 191.62
35212413 | FRRB - SILVERADO 2105 LR 658898 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 74.09
35212413 | FRRB - SILVERADO 2105 LR 658898 | Labor Internal | Mapping | Not assigned | 003/2021 | 518.82
35212413 | FRRB - SILVERADO 2105 LR 658898 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 156.08
35212413 | FRRB - SILVERADO 2105 LR 658898 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1811.17
35212413 | FRRB - SILVERADO 2105 LR 658898 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1658.07
35212413 | FRRB - SILVERADO 2105 LR 658898 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1802.05
35212413 | FRRB - SILVERADO 2105 LR 658898 | Other | AFUDC-Equity | Not assigned | 001/2021 | 4474.16
35212413 | FRRB - SILVERADO 2105 LR 658898 | Other | AFUDC-Equity | Not assigned | 002/2021 | 4474.16
35212413 | FRRB - SILVERADO 2105 LR 658898 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4862.67
35212413 | FRRB - SILVERADO 2105 LR 658898 | Other | Benefits OH | Not assigned | 003/2021 | 284.28
35212413 | FRRB - SILVERADO 2105 LR 658898 | Other | Building Service Overhead | Not assigned | 003/2021 | 51.67
35212413 | FRRB - SILVERADO 2105 LR 658898 | Other | Capitalized A&G | Not assigned | 003/2021 | 285.53
35212413 | FRRB - SILVERADO 2105 LR 658898 | Other | Cost Adjustments | Not assigned | 003/2021 | 7586.7
35212413 | FRRB - SILVERADO 2105 LR 658898 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 128.03
35212413 | FRRB - SILVERADO 2105 LR 658898 | Other | IT Device OH | Not assigned | 003/2021 | 29.33
35212413 | FRRB - SILVERADO 2105 LR 658898 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 173.42
35212413 | FRRB - SILVERADO 2105 LR 658898 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 44.37
35212413 | FRRB - SILVERADO 2105 LR 658898 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 101.14
35212414 | FRRB - SILVERADO 2105 LR 131568 | Contract | Contracts | Not assigned | 003/2021 | 40631.16
35212414 | FRRB - SILVERADO 2105 LR 131568 | Labor External | Contractor Activity Charges | Not assigned | 003/2021 | 2.09
35212414 | FRRB - SILVERADO 2105 LR 131568 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 10.91
35212414 | FRRB - SILVERADO 2105 LR 131568 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 49.27
35212414 | FRRB - SILVERADO 2105 LR 131568 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 45.02
35212414 | FRRB - SILVERADO 2105 LR 131568 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 17.41
35212414 | FRRB - SILVERADO 2105 LR 131568 | Labor Internal | Mapping | Not assigned | 003/2021 | 121.89
35212414 | FRRB - SILVERADO 2105 LR 131568 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 36.67
35212414 | FRRB - SILVERADO 2105 LR 131568 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 425.38
35212414 | FRRB - SILVERADO 2105 LR 131568 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 389.42
35212414 | FRRB - SILVERADO 2105 LR 131568 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 423.25
35212414 | FRRB - SILVERADO 2105 LR 131568 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1050.81
35212414 | FRRB - SILVERADO 2105 LR 131568 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1050.81
35212414 | FRRB - SILVERADO 2105 LR 131568 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1142.09
35212414 | FRRB - SILVERADO 2105 LR 131568 | Other | Benefits OH | Not assigned | 003/2021 | 66.79
35212414 | FRRB - SILVERADO 2105 LR 131568 | Other | Building Service Overhead | Not assigned | 003/2021 | 12.14
35212414 | FRRB - SILVERADO 2105 LR 131568 | Other | Capitalized A&G | Not assigned | 003/2021 | 67.08
35212414 | FRRB - SILVERADO 2105 LR 131568 | Other | Cost Adjustments | Not assigned | 003/2021 | 1782.46
35212414 | FRRB - SILVERADO 2105 LR 131568 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 30.08
35212414 | FRRB - SILVERADO 2105 LR 131568 | Other | IT Device OH | Not assigned | 003/2021 | 6.89
35212414 | FRRB - SILVERADO 2105 LR 131568 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 40.75
35212414 | FRRB - SILVERADO 2105 LR 131568 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 10.43
35212414 | FRRB - SILVERADO 2105 LR 131568 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 23.76
35212415 | FRRB - SILVERADO 2105 LR 167360 | Contract | Contracts | Not assigned | 003/2021 | 204862.97
35212415 | FRRB - SILVERADO 2105 LR 167360 | Labor External | Contractor Activity Charges | Not assigned | 003/2021 | 10.55
35212415 | FRRB - SILVERADO 2105 LR 167360 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 55.02
35212415 | FRRB - SILVERADO 2105 LR 167360 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 248.41
35212415 | FRRB - SILVERADO 2105 LR 167360 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 227
35212415 | FRRB - SILVERADO 2105 LR 167360 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 87.76
35212415 | FRRB - SILVERADO 2105 LR 167360 | Labor Internal | Mapping | Not assigned | 003/2021 | 614.59
35212415 | FRRB - SILVERADO 2105 LR 167360 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 184.89
35212415 | FRRB - SILVERADO 2105 LR 167360 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2146.82
35212415 | FRRB - SILVERADO 2105 LR 167360 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1965.35
35212415 | FRRB - SILVERADO 2105 LR 167360 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2135.9
35212415 | FRRB - SILVERADO 2105 LR 167360 | Other | AFUDC-Equity | Not assigned | 001/2021 | 5303.32
35212415 | FRRB - SILVERADO 2105 LR 167360 | Other | AFUDC-Equity | Not assigned | 002/2021 | 5303.32
35212415 | FRRB - SILVERADO 2105 LR 167360 | Other | AFUDC-Equity | Not assigned | 003/2021 | 5763.55
35212415 | FRRB - SILVERADO 2105 LR 167360 | Other | Benefits OH | Not assigned | 003/2021 | 336.76
35212415 | FRRB - SILVERADO 2105 LR 167360 | Other | Building Service Overhead | Not assigned | 003/2021 | 61.21
35212415 | FRRB - SILVERADO 2105 LR 167360 | Other | Capitalized A&G | Not assigned | 003/2021 | 338.24
35212415 | FRRB - SILVERADO 2105 LR 167360 | Other | Cost Adjustments | Not assigned | 003/2021 | 8987.2
35212415 | FRRB - SILVERADO 2105 LR 167360 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 151.66
35212415 | FRRB - SILVERADO 2105 LR 167360 | Other | IT Device OH | Not assigned | 003/2021 | 34.74
35212415 | FRRB - SILVERADO 2105 LR 167360 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 205.44
35212415 | FRRB - SILVERADO 2105 LR 167360 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 52.56
35212415 | FRRB - SILVERADO 2105 LR 167360 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 119.83
35212416 | FRRB - CALISTOGA 1102 LR 634 | Contract | Contracts | Not assigned | 003/2021 | 128039.36
35212416 | FRRB - CALISTOGA 1102 LR 634 | Labor External | Contractor Activity Charges | Not assigned | 003/2021 | 6.59
35212416 | FRRB - CALISTOGA 1102 LR 634 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 34.39
35212416 | FRRB - CALISTOGA 1102 LR 634 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 155.26
35212416 | FRRB - CALISTOGA 1102 LR 634 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 141.88
35212416 | FRRB - CALISTOGA 1102 LR 634 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 54.85
35212416 | FRRB - CALISTOGA 1102 LR 634 | Labor Internal | Mapping | Not assigned | 003/2021 | 384.12
35212416 | FRRB - CALISTOGA 1102 LR 634 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 115.56
35212416 | FRRB - CALISTOGA 1102 LR 634 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1340.93
35212416 | FRRB - CALISTOGA 1102 LR 634 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1227.58
35212416 | FRRB - CALISTOGA 1102 LR 634 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1334.18
35212416 | FRRB - CALISTOGA 1102 LR 634 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3312.52
35212416 | FRRB - CALISTOGA 1102 LR 634 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3312.52
35212416 | FRRB - CALISTOGA 1102 LR 634 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3600.17
35212416 | FRRB - CALISTOGA 1102 LR 634 | Other | Benefits OH | Not assigned | 003/2021 | 210.48
35212416 | FRRB - CALISTOGA 1102 LR 634 | Other | Building Service Overhead | Not assigned | 003/2021 | 38.25
35212416 | FRRB - CALISTOGA 1102 LR 634 | Other | Capitalized A&G | Not assigned | 003/2021 | 211.4
35212416 | FRRB - CALISTOGA 1102 LR 634 | Other | Cost Adjustments | Not assigned | 003/2021 | 5617
35212416 | FRRB - CALISTOGA 1102 LR 634 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 94.79
35212416 | FRRB - CALISTOGA 1102 LR 634 | Other | IT Device OH | Not assigned | 003/2021 | 21.71
35212416 | FRRB - CALISTOGA 1102 LR 634 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 128.4
35212416 | FRRB - CALISTOGA 1102 LR 634 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 32.85
35212416 | FRRB - CALISTOGA 1102 LR 634 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 74.89
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Contract | Contracts | Not assigned | 003/2021 | 337170.31
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Labor External | Contractor Activity Charges | Not assigned | 003/2021 | 17.37
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 90.55
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 408.84
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 373.6
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 144.44
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Labor Internal | Mapping | Not assigned | 003/2021 | 1011.51
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 304.3
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3532.62
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 3234
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3514.71
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Other | AFUDC-Equity | Not assigned | 001/2021 | 8726.67
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Other | AFUDC-Equity | Not assigned | 002/2021 | 8726.67
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Other | AFUDC-Equity | Not assigned | 003/2021 | 9484.13
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Other | Benefits OH | Not assigned | 003/2021 | 554.25
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Other | Building Service Overhead | Not assigned | 003/2021 | 100.73
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Other | Capitalized A&G | Not assigned | 003/2021 | 556.69
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Other | Cost Adjustments | Not assigned | 003/2021 | 14791.44
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 249.62
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Other | IT Device OH | Not assigned | 003/2021 | 57.17
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 338.11
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 86.51
35212417 | FRRB - CALISTOGA 1102 LR 769230 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 197.21
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Contract | Contracts | Not assigned | 003/2021 | 13768.5
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 807.74
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 1314.57
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 003/2021 | 605.28
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 287.82
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 464.44
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 218.99
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Mapping | Not assigned | 003/2021 | 41.31
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 557.66
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Materials | Material Burden | Not assigned | 003/2021 | 341.26
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 2337.41
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 8913.87
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 8160.37
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 8181.27
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | AFUDC-Equity | Not assigned | 001/2021 | 22020.03
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | AFUDC-Equity | Not assigned | 002/2021 | 22020.03
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | AFUDC-Equity | Not assigned | 003/2021 | 22076.45
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Benefits OH | Not assigned | 003/2021 | 1085.77
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Building Service Overhead | Not assigned | 003/2021 | 196.25
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Capitalized A&G | Not assigned | 003/2021 | 1019.51
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Cost Adjustments | Not assigned | 003/2021 | 1558.37
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 192.31
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 187.46
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | IT Device OH | Not assigned | 003/2021 | 111.38
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Minor Material OH | Not assigned | 003/2021 | 190.45
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 260.48
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 278.16
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 335.81
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 386.32
35212419 | FRRB - DUNBAR 1101 - LR 416 | Contract | Contracts | Not assigned | 002/2021 | 3575.41
35212419 | FRRB - DUNBAR 1101 - LR 416 | Contract | Contracts | Not assigned | 003/2021 | 8554.61
35212419 | FRRB - DUNBAR 1101 - LR 416 | Labor External | Contractor Activity Charges | Not assigned | 002/2021 | 27.45
35212419 | FRRB - DUNBAR 1101 - LR 416 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 174.23
35212419 | FRRB - DUNBAR 1101 - LR 416 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 635.67
35212419 | FRRB - DUNBAR 1101 - LR 416 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 344.79
35212419 | FRRB - DUNBAR 1101 - LR 416 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 261.49
35212419 | FRRB - DUNBAR 1101 - LR 416 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 003/2021 | 104.09
35212419 | FRRB - DUNBAR 1101 - LR 416 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 62.7
35212419 | FRRB - DUNBAR 1101 - LR 416 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 224.19
35212419 | FRRB - DUNBAR 1101 - LR 416 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 121.81
35212419 | FRRB - DUNBAR 1101 - LR 416 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 92.38
35212419 | FRRB - DUNBAR 1101 - LR 416 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 37.66
35212419 | FRRB - DUNBAR 1101 - LR 416 | Labor Internal | Indirect Labor - Nuclear Gen | Not assigned | 002/2021 | 0.5
35212419 | FRRB - DUNBAR 1101 - LR 416 | Labor Internal | Indirect Labor - Nuclear Gen | Not assigned | 003/2021 | 0.67
35212419 | FRRB - DUNBAR 1101 - LR 416 | Labor Internal | Mapping | Not assigned | 002/2021 | 10.73
35212419 | FRRB - DUNBAR 1101 - LR 416 | Labor Internal | Mapping | Not assigned | 003/2021 | 25.66
35212419 | FRRB - DUNBAR 1101 - LR 416 | Labor Internal | Nuclear Activity Charge - Type A | Not assigned | 002/2021 | 16.55
35212419 | FRRB - DUNBAR 1101 - LR 416 | Labor Internal | Nuclear Activity Charge - Type A | Not assigned | 003/2021 | 22.07
35212419 | FRRB - DUNBAR 1101 - LR 416 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 110.02
35212419 | FRRB - DUNBAR 1101 - LR 416 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 211.27
35212419 | FRRB - DUNBAR 1101 - LR 416 | Materials | Material Burden | Not assigned | 003/2021 | 15.68
35212419 | FRRB - DUNBAR 1101 - LR 416 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 107.41
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 785.83
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 723.55
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 737.03
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1941.25
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1952.44
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1988.81
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Benefits OH | Not assigned | 002/2021 | 198.56
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Benefits OH | Not assigned | 003/2021 | 394.44
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Building Service Overhead | Not assigned | 002/2021 | 34.95
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Building Service Overhead | Not assigned | 003/2021 | 71.29
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Capitalized A&G | Not assigned | 002/2021 | 201.74
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Capitalized A&G | Not assigned | 003/2021 | 386.24
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Cost Adjustments | Not assigned | 002/2021 | 120.57
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 41.89
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 149.79
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 32.24
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | IT Device OH | Not assigned | 002/2021 | 19.83
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | IT Device OH | Not assigned | 003/2021 | 40.46
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Minor Material OH | Not assigned | 003/2021 | 8.75
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 56.74
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 202.89
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 72.96
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 55.33
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 57.75
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Operation Mgmt & Support - Nuclear Gen | Not assigned | 002/2021 | 9.1
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Operation Mgmt & Support - Nuclear Gen | Not assigned | 003/2021 | 12.13
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 67.09
35212419 | FRRB - DUNBAR 1101 - LR 416 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 140.34
35212460 | FRRB - RINCON 1101 LR 14605 | Contract | Contracts | Not assigned | 002/2021 | 20214.81
35212460 | FRRB - RINCON 1101 LR 14605 | Contract | Contracts | Not assigned | 003/2021 | 48366.47
35212460 | FRRB - RINCON 1101 LR 14605 | Labor External | Contractor Activity Charges | Not assigned | 002/2021 | 155.19
35212460 | FRRB - RINCON 1101 LR 14605 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 985.05
35212460 | FRRB - RINCON 1101 LR 14605 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 3593.96
35212460 | FRRB - RINCON 1101 LR 14605 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 1949.42
35212460 | FRRB - RINCON 1101 LR 14605 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 1478.44
35212460 | FRRB - RINCON 1101 LR 14605 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 003/2021 | 588.5
35212460 | FRRB - RINCON 1101 LR 14605 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 354.49
35212460 | FRRB - RINCON 1101 LR 14605 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1267.54
35212460 | FRRB - RINCON 1101 LR 14605 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 688.73
35212460 | FRRB - RINCON 1101 LR 14605 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 522.33
35212460 | FRRB - RINCON 1101 LR 14605 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 212.92
35212460 | FRRB - RINCON 1101 LR 14605 | Labor Internal | Indirect Labor - Nuclear Gen | Not assigned | 002/2021 | 2.84
35212460 | FRRB - RINCON 1101 LR 14605 | Labor Internal | Indirect Labor - Nuclear Gen | Not assigned | 003/2021 | 3.78
35212460 | FRRB - RINCON 1101 LR 14605 | Labor Internal | Mapping | Not assigned | 002/2021 | 60.64
35212460 | FRRB - RINCON 1101 LR 14605 | Labor Internal | Mapping | Not assigned | 003/2021 | 145.1
35212460 | FRRB - RINCON 1101 LR 14605 | Labor Internal | Nuclear Activity Charge - Type A | Not assigned | 002/2021 | 93.57
35212460 | FRRB - RINCON 1101 LR 14605 | Labor Internal | Nuclear Activity Charge - Type A | Not assigned | 003/2021 | 124.76
35212460 | FRRB - RINCON 1101 LR 14605 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 622.06
35212460 | FRRB - RINCON 1101 LR 14605 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1194.45
35212460 | FRRB - RINCON 1101 LR 14605 | Materials | Material Burden | Not assigned | 003/2021 | 88.66
35212460 | FRRB - RINCON 1101 LR 14605 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 607.26
35212460 | FRRB - RINCON 1101 LR 14605 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 4178.59
35212460 | FRRB - RINCON 1101 LR 14605 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 3848.82
35212460 | FRRB - RINCON 1101 LR 14605 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3925.01
35212460 | FRRB - RINCON 1101 LR 14605 | Other | AFUDC-Equity | Not assigned | 001/2021 | 10322.41
35212460 | FRRB - RINCON 1101 LR 14605 | Other | AFUDC-Equity | Not assigned | 002/2021 | 10385.7
35212460 | FRRB - RINCON 1101 LR 14605 | Other | AFUDC-Equity | Not assigned | 003/2021 | 10591.29
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Benefits OH | Not assigned | 002/2021 | 1122.66
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Benefits OH | Not assigned | 003/2021 | 2230.16
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Building Service Overhead | Not assigned | 002/2021 | 197.59
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Building Service Overhead | Not assigned | 003/2021 | 403.07
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Capitalized A&G | Not assigned | 002/2021 | 1140.57
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Capitalized A&G | Not assigned | 003/2021 | 2183.71
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Cost Adjustments | Not assigned | 002/2021 | 681.67
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 236.84
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 846.9
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 182.26
35212460 | FRRB - RINCON 1101 LR 14605 | Other | IT Device OH | Not assigned | 002/2021 | 112.15
35212460 | FRRB - RINCON 1101 LR 14605 | Other | IT Device OH | Not assigned | 003/2021 | 228.78
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Minor Material OH | Not assigned | 003/2021 | 49.48
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 320.81
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1147.15
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 412.5
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 312.84
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 326.5
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Operation Mgmt & Support - Nuclear Gen | Not assigned | 002/2021 | 51.44
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Operation Mgmt & Support - Nuclear Gen | Not assigned | 003/2021 | 68.59
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 379.3
35212460 | FRRB - RINCON 1101 LR 14605 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 793.5
35212461 | FRRB - RINCON 1101 LR 663641 | Contract | Contracts | Not assigned | 002/2021 | 901.49
35212461 | FRRB - RINCON 1101 LR 663641 | Contract | Contracts | Not assigned | 003/2021 | 2156.93
35212461 | FRRB - RINCON 1101 LR 663641 | Labor External | Contractor Activity Charges | Not assigned | 002/2021 | 6.92
35212461 | FRRB - RINCON 1101 LR 663641 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 43.93
35212461 | FRRB - RINCON 1101 LR 663641 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 160.27
35212461 | FRRB - RINCON 1101 LR 663641 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 86.94
35212461 | FRRB - RINCON 1101 LR 663641 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 65.93
35212461 | FRRB - RINCON 1101 LR 663641 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 003/2021 | 26.24
35212461 | FRRB - RINCON 1101 LR 663641 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 15.81
35212461 | FRRB - RINCON 1101 LR 663641 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 56.52
35212461 | FRRB - RINCON 1101 LR 663641 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 30.72
35212461 | FRRB - RINCON 1101 LR 663641 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 23.29
35212461 | FRRB - RINCON 1101 LR 663641 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 9.49
35212461 | FRRB - RINCON 1101 LR 663641 | Labor Internal | Indirect Labor - Nuclear Gen | Not assigned | 002/2021 | 0.13
35212461 | FRRB - RINCON 1101 LR 663641 | Labor Internal | Indirect Labor - Nuclear Gen | Not assigned | 003/2021 | 0.17
35212461 | FRRB - RINCON 1101 LR 663641 | Labor Internal | Mapping | Not assigned | 002/2021 | 2.7
35212461 | FRRB - RINCON 1101 LR 663641 | Labor Internal | Mapping | Not assigned | 003/2021 | 6.47
35212461 | FRRB - RINCON 1101 LR 663641 | Labor Internal | Nuclear Activity Charge - Type A | Not assigned | 002/2021 | 4.17
35212461 | FRRB - RINCON 1101 LR 663641 | Labor Internal | Nuclear Activity Charge - Type A | Not assigned | 003/2021 | 5.56
35212461 | FRRB - RINCON 1101 LR 663641 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 27.74
35212461 | FRRB - RINCON 1101 LR 663641 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 53.26
35212461 | FRRB - RINCON 1101 LR 663641 | Materials | Material Burden | Not assigned | 003/2021 | 3.95
35212461 | FRRB - RINCON 1101 LR 663641 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 27.08
35212461 | FRRB - RINCON 1101 LR 663641 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 222.25
35212461 | FRRB - RINCON 1101 LR 663641 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 204.51
35212461 | FRRB - RINCON 1101 LR 663641 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 207.91
35212461 | FRRB - RINCON 1101 LR 663641 | Other | AFUDC-Equity | Not assigned | 001/2021 | 549.03
35212461 | FRRB - RINCON 1101 LR 663641 | Other | AFUDC-Equity | Not assigned | 002/2021 | 551.85
35212461 | FRRB - RINCON 1101 LR 663641 | Other | AFUDC-Equity | Not assigned | 003/2021 | 561.02
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Benefits OH | Not assigned | 002/2021 | 50.07
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Benefits OH | Not assigned | 003/2021 | 99.45
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Building Service Overhead | Not assigned | 002/2021 | 8.82
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Building Service Overhead | Not assigned | 003/2021 | 17.98
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Capitalized A&G | Not assigned | 002/2021 | 50.86
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Capitalized A&G | Not assigned | 003/2021 | 97.38
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Cost Adjustments | Not assigned | 002/2021 | 30.4
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 10.56
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 37.77
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 8.13
35212461 | FRRB - RINCON 1101 LR 663641 | Other | IT Device OH | Not assigned | 002/2021 | 5
35212461 | FRRB - RINCON 1101 LR 663641 | Other | IT Device OH | Not assigned | 003/2021 | 10.2
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Minor Material OH | Not assigned | 003/2021 | 2.21
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 14.31
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 51.15
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 18.4
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 13.95
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 14.56
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Operation Mgmt & Support - Nuclear Gen | Not assigned | 002/2021 | 2.29
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Operation Mgmt & Support - Nuclear Gen | Not assigned | 003/2021 | 3.06
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 16.91
35212461 | FRRB - RINCON 1101 LR 663641 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 35.38
35212462 | FRRB - RINCON 1103 LR 198 | Contract | Contracts | Not assigned | 002/2021 | 3972.68
35212462 | FRRB - RINCON 1103 LR 198 | Contract | Contracts | Not assigned | 003/2021 | 9505.13
35212462 | FRRB - RINCON 1103 LR 198 | Labor External | Contractor Activity Charges | Not assigned | 002/2021 | 30.5
35212462 | FRRB - RINCON 1103 LR 198 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 193.58
35212462 | FRRB - RINCON 1103 LR 198 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 706.3
35212462 | FRRB - RINCON 1103 LR 198 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 383.11
35212462 | FRRB - RINCON 1103 LR 198 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 290.55
35212462 | FRRB - RINCON 1103 LR 198 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 003/2021 | 115.65
35212462 | FRRB - RINCON 1103 LR 198 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 69.66
35212462 | FRRB - RINCON 1103 LR 198 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 249.11
35212462 | FRRB - RINCON 1103 LR 198 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 135.35
35212462 | FRRB - RINCON 1103 LR 198 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 102.65
35212462 | FRRB - RINCON 1103 LR 198 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 41.84
35212462 | FRRB - RINCON 1103 LR 198 | Labor Internal | Indirect Labor - Nuclear Gen | Not assigned | 002/2021 | 0.56
35212462 | FRRB - RINCON 1103 LR 198 | Labor Internal | Indirect Labor - Nuclear Gen | Not assigned | 003/2021 | 0.74
35212462 | FRRB - RINCON 1103 LR 198 | Labor Internal | Mapping | Not assigned | 002/2021 | 11.92
35212462 | FRRB - RINCON 1103 LR 198 | Labor Internal | Mapping | Not assigned | 003/2021 | 28.52
35212462 | FRRB - RINCON 1103 LR 198 | Labor Internal | Nuclear Activity Charge - Type A | Not assigned | 002/2021 | 18.39
35212462 | FRRB - RINCON 1103 LR 198 | Labor Internal | Nuclear Activity Charge - Type A | Not assigned | 003/2021 | 24.52
35212462 | FRRB - RINCON 1103 LR 198 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 122.25
35212462 | FRRB - RINCON 1103 LR 198 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 234.74
35212462 | FRRB - RINCON 1103 LR 198 | Materials | Material Burden | Not assigned | 003/2021 | 17.42
35212462 | FRRB - RINCON 1103 LR 198 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 119.34
35212462 | FRRB - RINCON 1103 LR 198 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 793.35
35212462 | FRRB - RINCON 1103 LR 198 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 730.9
35212462 | FRRB - RINCON 1103 LR 198 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 745.87
35212462 | FRRB - RINCON 1103 LR 198 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1959.82
35212462 | FRRB - RINCON 1103 LR 198 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1972.26
35212462 | FRRB - RINCON 1103 LR 198 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2012.66
35212462 | FRRB - RINCON 1103 LR 198 | Other | Benefits OH | Not assigned | 002/2021 | 220.63
35212462 | FRRB - RINCON 1103 LR 198 | Other | Benefits OH | Not assigned | 003/2021 | 438.27
35212462 | FRRB - RINCON 1103 LR 198 | Other | Building Service Overhead | Not assigned | 002/2021 | 38.83
35212462 | FRRB - RINCON 1103 LR 198 | Other | Building Service Overhead | Not assigned | 003/2021 | 79.22
35212462 | FRRB - RINCON 1103 LR 198 | Other | Capitalized A&G | Not assigned | 002/2021 | 224.15
35212462 | FRRB - RINCON 1103 LR 198 | Other | Capitalized A&G | Not assigned | 003/2021 | 429.15
35212462 | FRRB - RINCON 1103 LR 198 | Other | Cost Adjustments | Not assigned | 002/2021 | 133.96
35212462 | FRRB - RINCON 1103 LR 198 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 46.55
35212462 | FRRB - RINCON 1103 LR 198 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 166.44
35212462 | FRRB - RINCON 1103 LR 198 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 35.82
35212462 | FRRB - RINCON 1103 LR 198 | Other | IT Device OH | Not assigned | 002/2021 | 22.04
35212462 | FRRB - RINCON 1103 LR 198 | Other | IT Device OH | Not assigned | 003/2021 | 44.96
35212462 | FRRB - RINCON 1103 LR 198 | Other | Minor Material OH | Not assigned | 003/2021 | 9.73
35212462 | FRRB - RINCON 1103 LR 198 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 63.05
35212462 | FRRB - RINCON 1103 LR 198 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 225.44
35212462 | FRRB - RINCON 1103 LR 198 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 81.07
35212462 | FRRB - RINCON 1103 LR 198 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 61.48
35212462 | FRRB - RINCON 1103 LR 198 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 64.16
35212462 | FRRB - RINCON 1103 LR 198 | Other | Operation Mgmt & Support - Nuclear Gen | Not assigned | 002/2021 | 10.11
35212462 | FRRB - RINCON 1103 LR 198 | Other | Operation Mgmt & Support - Nuclear Gen | Not assigned | 003/2021 | 13.48
35212462 | FRRB - RINCON 1103 LR 198 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 74.53
35212462 | FRRB - RINCON 1103 LR 198 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 155.96
35212463 | FRRB - RINCON 1103 LR 474 | Contract | Contracts | Not assigned | 002/2021 | 25348.74
35212463 | FRRB - RINCON 1103 LR 474 | Contract | Contracts | Not assigned | 003/2021 | 60650.01
35212463 | FRRB - RINCON 1103 LR 474 | Labor External | Contractor Activity Charges | Not assigned | 002/2021 | 194.6
35212463 | FRRB - RINCON 1103 LR 474 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 1235.22
35212463 | FRRB - RINCON 1103 LR 474 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 4506.71
35212463 | FRRB - RINCON 1103 LR 474 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 2444.51
35212463 | FRRB - RINCON 1103 LR 474 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 1853.91
35212463 | FRRB - RINCON 1103 LR 474 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 003/2021 | 737.96
35212463 | FRRB - RINCON 1103 LR 474 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 444.52
35212463 | FRRB - RINCON 1103 LR 474 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1589.45
35212463 | FRRB - RINCON 1103 LR 474 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 863.65
35212463 | FRRB - RINCON 1103 LR 474 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 654.99
35212463 | FRRB - RINCON 1103 LR 474 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 266.99
35212463 | FRRB - RINCON 1103 LR 474 | Labor Internal | Indirect Labor - Nuclear Gen | Not assigned | 002/2021 | 3.56
35212463 | FRRB - RINCON 1103 LR 474 | Labor Internal | Indirect Labor - Nuclear Gen | Not assigned | 003/2021 | 4.74
35212463 | FRRB - RINCON 1103 LR 474 | Labor Internal | Mapping | Not assigned | 002/2021 | 76.05
35212463 | FRRB - RINCON 1103 LR 474 | Labor Internal | Mapping | Not assigned | 003/2021 | 181.95
35212463 | FRRB - RINCON 1103 LR 474 | Labor Internal | Nuclear Activity Charge - Type A | Not assigned | 002/2021 | 117.34
35212463 | FRRB - RINCON 1103 LR 474 | Labor Internal | Nuclear Activity Charge - Type A | Not assigned | 003/2021 | 156.45
35212463 | FRRB - RINCON 1103 LR 474 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 780.05
35212463 | FRRB - RINCON 1103 LR 474 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1497.8
35212463 | FRRB - RINCON 1103 LR 474 | Materials | Material Burden | Not assigned | 003/2021 | 111.18
35212463 | FRRB - RINCON 1103 LR 474 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 761.48
35212463 | FRRB - RINCON 1103 LR 474 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 5301.7
35212463 | FRRB - RINCON 1103 LR 474 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4882.95
35212463 | FRRB - RINCON 1103 LR 474 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 4978.49
35212463 | FRRB - RINCON 1103 LR 474 | Other | AFUDC-Equity | Not assigned | 001/2021 | 13096.85
35212463 | FRRB - RINCON 1103 LR 474 | Other | AFUDC-Equity | Not assigned | 002/2021 | 13176.21
35212463 | FRRB - RINCON 1103 LR 474 | Other | AFUDC-Equity | Not assigned | 003/2021 | 13434.02
35212463 | FRRB - RINCON 1103 LR 474 | Other | Benefits OH | Not assigned | 002/2021 | 1407.78
35212463 | FRRB - RINCON 1103 LR 474 | Other | Benefits OH | Not assigned | 003/2021 | 2796.56
35212463 | FRRB - RINCON 1103 LR 474 | Other | Building Service Overhead | Not assigned | 002/2021 | 247.77
35212463 | FRRB - RINCON 1103 LR 474 | Other | Building Service Overhead | Not assigned | 003/2021 | 505.45
35212463 | FRRB - RINCON 1103 LR 474 | Other | Capitalized A&G | Not assigned | 002/2021 | 1430.24
35212463 | FRRB - RINCON 1103 LR 474 | Other | Capitalized A&G | Not assigned | 003/2021 | 2738.29
35212463 | FRRB - RINCON 1103 LR 474 | Other | Cost Adjustments | Not assigned | 002/2021 | 854.8
35212463 | FRRB - RINCON 1103 LR 474 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 297.01
35212463 | FRRB - RINCON 1103 LR 474 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1061.98
35212463 | FRRB - RINCON 1103 LR 474 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 228.55
35212463 | FRRB - RINCON 1103 LR 474 | Other | IT Device OH | Not assigned | 002/2021 | 140.63
35212463 | FRRB - RINCON 1103 LR 474 | Other | IT Device OH | Not assigned | 003/2021 | 286.88
35212463 | FRRB - RINCON 1103 LR 474 | Other | Minor Material OH | Not assigned | 003/2021 | 62.04
35212463 | FRRB - RINCON 1103 LR 474 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 402.3
35212463 | FRRB - RINCON 1103 LR 474 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1438.48
35212463 | FRRB - RINCON 1103 LR 474 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 517.26
35212463 | FRRB - RINCON 1103 LR 474 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 392.29
35212463 | FRRB - RINCON 1103 LR 474 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 409.42
35212463 | FRRB - RINCON 1103 LR 474 | Other | Operation Mgmt & Support - Nuclear Gen | Not assigned | 002/2021 | 64.51
35212463 | FRRB - RINCON 1103 LR 474 | Other | Operation Mgmt & Support - Nuclear Gen | Not assigned | 003/2021 | 86.02
35212463 | FRRB - RINCON 1103 LR 474 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 475.63
35212463 | FRRB - RINCON 1103 LR 474 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 995.01
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Contract | Contracts | Not assigned | 003/2021 | 15324.78
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 6179.16
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 28.9
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 2110.32
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 10.21
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Labor Internal | Indirect Labor - IT | Not assigned | 003/2021 | 47.51
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Labor Internal | IT Activity Charge - Type A | Not assigned | 003/2021 | 127.37
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Labor Internal | Mapping | Not assigned | 003/2021 | 45.97
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1285.22
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Materials | Construction Supplies | Not assigned | 003/2021 | -24.5
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Materials | Material Burden | Not assigned | 003/2021 | -13.66
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | -65.88
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Materials | Tools, First Aid & Safety Supplies | Not assigned | 003/2021 | -45.58
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 7001.36
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 6409.52
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 6436.97
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Other | AFUDC-Equity | Not assigned | 001/2021 | 17295.54
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Other | AFUDC-Equity | Not assigned | 002/2021 | 17295.54
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Other | AFUDC-Equity | Not assigned | 003/2021 | 17369.61
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Other | Benefits OH | Not assigned | 003/2021 | 2425.98
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Other | Building Service Overhead | Not assigned | 003/2021 | 438.48
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Other | Capitalized A&G | Not assigned | 003/2021 | 2349.64
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Other | Cost Adjustments | Not assigned | 003/2021 | 185.98
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1409.99
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Other | IT Device OH | Not assigned | 003/2021 | 248.86
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Other | Minor Material OH | Not assigned | 003/2021 | -10.64
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1909.87
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 6.12
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Other | Operation Mgmt & Support - IT | Not assigned | 003/2021 | 20.44
35212465 | FRRB - VACAVILLE 1108 LR 38316 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 863.15
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Contract | Contracts | Not assigned | 003/2021 | 21609.39
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 8713.2
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 40.74
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 2975.75
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 14.39
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Labor Internal | Indirect Labor - IT | Not assigned | 003/2021 | 66.99
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Labor Internal | IT Activity Charge - Type A | Not assigned | 003/2021 | 179.61
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Labor Internal | Mapping | Not assigned | 003/2021 | 64.83
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1812.28
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Materials | Construction Supplies | Not assigned | 003/2021 | -34.54
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Materials | Material Burden | Not assigned | 003/2021 | -19.24
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | -92.89
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Materials | Tools, First Aid & Safety Supplies | Not assigned | 003/2021 | -64.28
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 9872.59
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 9038.04
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 9076.74
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Other | AFUDC-Equity | Not assigned | 001/2021 | 24388.35
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Other | AFUDC-Equity | Not assigned | 002/2021 | 24388.35
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Other | AFUDC-Equity | Not assigned | 003/2021 | 24492.8
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Other | Benefits OH | Not assigned | 003/2021 | 3420.85
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Other | Building Service Overhead | Not assigned | 003/2021 | 618.29
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Other | Capitalized A&G | Not assigned | 003/2021 | 3313.2
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Other | Cost Adjustments | Not assigned | 003/2021 | 262.25
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1988.22
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Other | IT Device OH | Not assigned | 003/2021 | 350.93
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Other | Minor Material OH | Not assigned | 003/2021 | -15
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 2693.1
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 8.62
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Other | Operation Mgmt & Support - IT | Not assigned | 003/2021 | 28.83
35212466 | FRRB - VACAVILLE 1108 LR 8762 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 1217.12
35212467 | FRRB - LAURELES 1111 LR 2020 | Contract | Contracts | Not assigned | 003/2021 | -9978.15
35212467 | FRRB - LAURELES 1111 LR 2020 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | -10.15
35212467 | FRRB - LAURELES 1111 LR 2020 | Labor Internal | Mapping | Not assigned | 003/2021 | -29.93
35212467 | FRRB - LAURELES 1111 LR 2020 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | -6.03
35212467 | FRRB - LAURELES 1111 LR 2020 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 4943.5
35212467 | FRRB - LAURELES 1111 LR 2020 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4525.62
35212467 | FRRB - LAURELES 1111 LR 2020 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 4517.79
35212467 | FRRB - LAURELES 1111 LR 2020 | Other | AFUDC-Equity | Not assigned | 001/2021 | 12212
35212467 | FRRB - LAURELES 1111 LR 2020 | Other | AFUDC-Equity | Not assigned | 002/2021 | 12212
35212467 | FRRB - LAURELES 1111 LR 2020 | Other | AFUDC-Equity | Not assigned | 003/2021 | 12190.85
35212467 | FRRB - LAURELES 1111 LR 2020 | Other | Benefits OH | Not assigned | 003/2021 | -11.44
35212467 | FRRB - LAURELES 1111 LR 2020 | Other | Building Service Overhead | Not assigned | 003/2021 | -2.07
35212467 | FRRB - LAURELES 1111 LR 2020 | Other | Capitalized A&G | Not assigned | 003/2021 | -11.02
35212467 | FRRB - LAURELES 1111 LR 2020 | Other | Cost Adjustments | Not assigned | 003/2021 | 120.78
35212467 | FRRB - LAURELES 1111 LR 2020 | Other | Fleet OH - Elec | Not assigned | 003/2021 | -6.78
35212467 | FRRB - LAURELES 1111 LR 2020 | Other | IT Device OH | Not assigned | 003/2021 | -1.18
35212467 | FRRB - LAURELES 1111 LR 2020 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | -9.18
35212467 | FRRB - LAURELES 1111 LR 2020 | Other | Payroll Taxes OH | Not assigned | 003/2021 | -4.06
35212472 | FRRB - BIG BASIN 1102 LR5066 | Contract | Contracts | Not assigned | 003/2021 | 97230.86
35212472 | FRRB - BIG BASIN 1102 LR5066 | Labor External | Contractor Activity Charges | Not assigned | 003/2021 | 0.16
35212472 | FRRB - BIG BASIN 1102 LR5066 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 263.14
35212472 | FRRB - BIG BASIN 1102 LR5066 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 16.08
35212472 | FRRB - BIG BASIN 1102 LR5066 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 188.08
35212472 | FRRB - BIG BASIN 1102 LR5066 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 5.68
35212472 | FRRB - BIG BASIN 1102 LR5066 | Labor Internal | Indirect Labor - IT | Not assigned | 003/2021 | 69.81
35212472 | FRRB - BIG BASIN 1102 LR5066 | Labor Internal | IT Activity Charge - Type A | Not assigned | 003/2021 | 187.15
35212472 | FRRB - BIG BASIN 1102 LR5066 | Labor Internal | Mapping | Not assigned | 003/2021 | 291.69
35212472 | FRRB - BIG BASIN 1102 LR5066 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 152.68
35212472 | FRRB - BIG BASIN 1102 LR5066 | Materials | Electrical Specialties | Not assigned | 003/2021 | 32.36
35212472 | FRRB - BIG BASIN 1102 LR5066 | Materials | Fabricated Structures | Not assigned | 003/2021 | 64.81
35212472 | FRRB - BIG BASIN 1102 LR5066 | Materials | Material Burden | Not assigned | 003/2021 | 60.71
35212472 | FRRB - BIG BASIN 1102 LR5066 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 379.01
35212472 | FRRB - BIG BASIN 1102 LR5066 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 5188.77
35212472 | FRRB - BIG BASIN 1102 LR5066 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4750.15
35212472 | FRRB - BIG BASIN 1102 LR5066 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 4824.05
35212472 | FRRB - BIG BASIN 1102 LR5066 | Other | AFUDC-Equity | Not assigned | 001/2021 | 12817.87
35212472 | FRRB - BIG BASIN 1102 LR5066 | Other | AFUDC-Equity | Not assigned | 002/2021 | 12817.87
35212472 | FRRB - BIG BASIN 1102 LR5066 | Other | AFUDC-Equity | Not assigned | 003/2021 | 13017.28
35212472 | FRRB - BIG BASIN 1102 LR5066 | Other | Benefits OH | Not assigned | 003/2021 | 288.21
35212472 | FRRB - BIG BASIN 1102 LR5066 | Other | Building Service Overhead | Not assigned | 003/2021 | 52.09
35212472 | FRRB - BIG BASIN 1102 LR5066 | Other | Capitalized A&G | Not assigned | 003/2021 | 279.12
35212472 | FRRB - BIG BASIN 1102 LR5066 | Other | Cost Adjustments | Not assigned | 003/2021 | -6220.16
35212472 | FRRB - BIG BASIN 1102 LR5066 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 125.67
35212472 | FRRB - BIG BASIN 1102 LR5066 | Other | IT Device OH | Not assigned | 003/2021 | 29.58
35212472 | FRRB - BIG BASIN 1102 LR5066 | Other | Minor Material OH | Not assigned | 003/2021 | 38.18
35212472 | FRRB - BIG BASIN 1102 LR5066 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 170.22
35212472 | FRRB - BIG BASIN 1102 LR5066 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 3.4
35212472 | FRRB - BIG BASIN 1102 LR5066 | Other | Operation Mgmt & Support - IT | Not assigned | 003/2021 | 30.04
35212472 | FRRB - BIG BASIN 1102 LR5066 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 102.53
35212473 | FRRB - BIG BASIN 1102 LR10254 | Contract | Contracts | Not assigned | 003/2021 | 84598.51
35212473 | FRRB - BIG BASIN 1102 LR10254 | Labor External | Contractor Activity Charges | Not assigned | 003/2021 | 0.14
35212473 | FRRB - BIG BASIN 1102 LR10254 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 228.95
35212473 | FRRB - BIG BASIN 1102 LR10254 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 13.99
35212473 | FRRB - BIG BASIN 1102 LR10254 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 163.65
35212473 | FRRB - BIG BASIN 1102 LR10254 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 4.94
35212473 | FRRB - BIG BASIN 1102 LR10254 | Labor Internal | Indirect Labor - IT | Not assigned | 003/2021 | 60.74
35212473 | FRRB - BIG BASIN 1102 LR10254 | Labor Internal | IT Activity Charge - Type A | Not assigned | 003/2021 | 162.83
35212473 | FRRB - BIG BASIN 1102 LR10254 | Labor Internal | Mapping | Not assigned | 003/2021 | 253.8
35212473 | FRRB - BIG BASIN 1102 LR10254 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 132.84
35212473 | FRRB - BIG BASIN 1102 LR10254 | Materials | Electrical Specialties | Not assigned | 003/2021 | 28.16
35212473 | FRRB - BIG BASIN 1102 LR10254 | Materials | Fabricated Structures | Not assigned | 003/2021 | 56.39
35212473 | FRRB - BIG BASIN 1102 LR10254 | Materials | Material Burden | Not assigned | 003/2021 | 52.82
35212473 | FRRB - BIG BASIN 1102 LR10254 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 329.77
35212473 | FRRB - BIG BASIN 1102 LR10254 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 4514.63
35212473 | FRRB - BIG BASIN 1102 LR10254 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4133
35212473 | FRRB - BIG BASIN 1102 LR10254 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 4197.3
35212473 | FRRB - BIG BASIN 1102 LR10254 | Other | AFUDC-Equity | Not assigned | 001/2021 | 11152.55
35212473 | FRRB - BIG BASIN 1102 LR10254 | Other | AFUDC-Equity | Not assigned | 002/2021 | 11152.55
35212473 | FRRB - BIG BASIN 1102 LR10254 | Other | AFUDC-Equity | Not assigned | 003/2021 | 11326.06
35212473 | FRRB - BIG BASIN 1102 LR10254 | Other | Benefits OH | Not assigned | 003/2021 | 250.77
35212473 | FRRB - BIG BASIN 1102 LR10254 | Other | Building Service Overhead | Not assigned | 003/2021 | 45.33
35212473 | FRRB - BIG BASIN 1102 LR10254 | Other | Capitalized A&G | Not assigned | 003/2021 | 242.85
35212473 | FRRB - BIG BASIN 1102 LR10254 | Other | Cost Adjustments | Not assigned | 003/2021 | -5412.03
35212473 | FRRB - BIG BASIN 1102 LR10254 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 109.35
35212473 | FRRB - BIG BASIN 1102 LR10254 | Other | IT Device OH | Not assigned | 003/2021 | 25.73
35212473 | FRRB - BIG BASIN 1102 LR10254 | Other | Minor Material OH | Not assigned | 003/2021 | 33.22
35212473 | FRRB - BIG BASIN 1102 LR10254 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 148.11
35212473 | FRRB - BIG BASIN 1102 LR10254 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 2.96
35212473 | FRRB - BIG BASIN 1102 LR10254 | Other | Operation Mgmt & Support - IT | Not assigned | 003/2021 | 26.13
35212473 | FRRB - BIG BASIN 1102 LR10254 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 89.23
35212474 | FRRB - BIG BASIN 1102 LR12758 | Contract | Contracts | Not assigned | 003/2021 | 19905.53
35212474 | FRRB - BIG BASIN 1102 LR12758 | Labor External | Contractor Activity Charges | Not assigned | 003/2021 | 0.03
35212474 | FRRB - BIG BASIN 1102 LR12758 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 53.87
35212474 | FRRB - BIG BASIN 1102 LR12758 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 3.29
35212474 | FRRB - BIG BASIN 1102 LR12758 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 38.51
35212474 | FRRB - BIG BASIN 1102 LR12758 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 1.16
35212474 | FRRB - BIG BASIN 1102 LR12758 | Labor Internal | Indirect Labor - IT | Not assigned | 003/2021 | 14.29
35212474 | FRRB - BIG BASIN 1102 LR12758 | Labor Internal | IT Activity Charge - Type A | Not assigned | 003/2021 | 38.31
35212474 | FRRB - BIG BASIN 1102 LR12758 | Labor Internal | Mapping | Not assigned | 003/2021 | 59.72
35212474 | FRRB - BIG BASIN 1102 LR12758 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 31.26
35212474 | FRRB - BIG BASIN 1102 LR12758 | Materials | Electrical Specialties | Not assigned | 003/2021 | 6.63
35212474 | FRRB - BIG BASIN 1102 LR12758 | Materials | Fabricated Structures | Not assigned | 003/2021 | 13.27
35212474 | FRRB - BIG BASIN 1102 LR12758 | Materials | Material Burden | Not assigned | 003/2021 | 12.43
35212474 | FRRB - BIG BASIN 1102 LR12758 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 77.59
35212474 | FRRB - BIG BASIN 1102 LR12758 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1062.27
35212474 | FRRB - BIG BASIN 1102 LR12758 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 972.47
35212474 | FRRB - BIG BASIN 1102 LR12758 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 987.6
35212474 | FRRB - BIG BASIN 1102 LR12758 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2624.13
35212474 | FRRB - BIG BASIN 1102 LR12758 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2624.13
35212474 | FRRB - BIG BASIN 1102 LR12758 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2664.95
35212474 | FRRB - BIG BASIN 1102 LR12758 | Other | Benefits OH | Not assigned | 003/2021 | 59.01
35212474 | FRRB - BIG BASIN 1102 LR12758 | Other | Building Service Overhead | Not assigned | 003/2021 | 10.66
35212474 | FRRB - BIG BASIN 1102 LR12758 | Other | Capitalized A&G | Not assigned | 003/2021 | 57.14
35212474 | FRRB - BIG BASIN 1102 LR12758 | Other | Cost Adjustments | Not assigned | 003/2021 | -1273.42
35212474 | FRRB - BIG BASIN 1102 LR12758 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 25.73
35212474 | FRRB - BIG BASIN 1102 LR12758 | Other | IT Device OH | Not assigned | 003/2021 | 6.04
35212474 | FRRB - BIG BASIN 1102 LR12758 | Other | Minor Material OH | Not assigned | 003/2021 | 7.81
35212474 | FRRB - BIG BASIN 1102 LR12758 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 34.85
35212474 | FRRB - BIG BASIN 1102 LR12758 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 0.7
35212474 | FRRB - BIG BASIN 1102 LR12758 | Other | Operation Mgmt & Support - IT | Not assigned | 003/2021 | 6.15
35212474 | FRRB - BIG BASIN 1102 LR12758 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 21
35212475 | FRRB - BIG BASIN 1101 CB | Contract | Contracts | Not assigned | 003/2021 | 118284.79
35212475 | FRRB - BIG BASIN 1101 CB | Labor External | Contractor Activity Charges | Not assigned | 003/2021 | 0.19
35212475 | FRRB - BIG BASIN 1101 CB | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 320.12
35212475 | FRRB - BIG BASIN 1101 CB | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 19.56
35212475 | FRRB - BIG BASIN 1101 CB | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 228.81
35212475 | FRRB - BIG BASIN 1101 CB | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 6.91
35212475 | FRRB - BIG BASIN 1101 CB | Labor Internal | Indirect Labor - IT | Not assigned | 003/2021 | 84.92
35212475 | FRRB - BIG BASIN 1101 CB | Labor Internal | IT Activity Charge - Type A | Not assigned | 003/2021 | 227.67
35212475 | FRRB - BIG BASIN 1101 CB | Labor Internal | Mapping | Not assigned | 003/2021 | 354.85
35212475 | FRRB - BIG BASIN 1101 CB | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 185.73
35212475 | FRRB - BIG BASIN 1101 CB | Materials | Electrical Specialties | Not assigned | 003/2021 | 39.37
35212475 | FRRB - BIG BASIN 1101 CB | Materials | Fabricated Structures | Not assigned | 003/2021 | 78.84
35212475 | FRRB - BIG BASIN 1101 CB | Materials | Material Burden | Not assigned | 003/2021 | 73.86
35212475 | FRRB - BIG BASIN 1101 CB | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 461.08
35212475 | FRRB - BIG BASIN 1101 CB | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 6312.32
35212475 | FRRB - BIG BASIN 1101 CB | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 5778.73
35212475 | FRRB - BIG BASIN 1101 CB | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 5868.63
35212475 | FRRB - BIG BASIN 1101 CB | Other | AFUDC-Equity | Not assigned | 001/2021 | 15593.39
35212475 | FRRB - BIG BASIN 1101 CB | Other | AFUDC-Equity | Not assigned | 002/2021 | 15593.39
35212475 | FRRB - BIG BASIN 1101 CB | Other | AFUDC-Equity | Not assigned | 003/2021 | 15835.98
35212475 | FRRB - BIG BASIN 1101 CB | Other | Benefits OH | Not assigned | 003/2021 | 350.62
35212475 | FRRB - BIG BASIN 1101 CB | Other | Building Service Overhead | Not assigned | 003/2021 | 63.39
35212475 | FRRB - BIG BASIN 1101 CB | Other | Capitalized A&G | Not assigned | 003/2021 | 339.56
35212475 | FRRB - BIG BASIN 1101 CB | Other | Cost Adjustments | Not assigned | 003/2021 | -7567.04
35212475 | FRRB - BIG BASIN 1101 CB | Other | Fleet OH - Elec | Not assigned | 003/2021 | 152.88
35212475 | FRRB - BIG BASIN 1101 CB | Other | IT Device OH | Not assigned | 003/2021 | 35.99
35212475 | FRRB - BIG BASIN 1101 CB | Other | Minor Material OH | Not assigned | 003/2021 | 46.44
35212475 | FRRB - BIG BASIN 1101 CB | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 207.08
35212475 | FRRB - BIG BASIN 1101 CB | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 4.14
35212475 | FRRB - BIG BASIN 1101 CB | Other | Operation Mgmt & Support - IT | Not assigned | 003/2021 | 36.54
35212475 | FRRB - BIG BASIN 1101 CB | Other | Payroll Taxes OH | Not assigned | 003/2021 | 124.76
35212476 | FRRB - BIG BASIN 1101 LR5000 | Contract | Contracts | Not assigned | 003/2021 | 52443.42
35212476 | FRRB - BIG BASIN 1101 LR5000 | Labor External | Contractor Activity Charges | Not assigned | 003/2021 | 0.09
35212476 | FRRB - BIG BASIN 1101 LR5000 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 141.93
35212476 | FRRB - BIG BASIN 1101 LR5000 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 8.67
35212476 | FRRB - BIG BASIN 1101 LR5000 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 101.44
35212476 | FRRB - BIG BASIN 1101 LR5000 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 3.06
35212476 | FRRB - BIG BASIN 1101 LR5000 | Labor Internal | Indirect Labor - IT | Not assigned | 003/2021 | 37.65
35212476 | FRRB - BIG BASIN 1101 LR5000 | Labor Internal | IT Activity Charge - Type A | Not assigned | 003/2021 | 100.94
35212476 | FRRB - BIG BASIN 1101 LR5000 | Labor Internal | Mapping | Not assigned | 003/2021 | 157.33
35212476 | FRRB - BIG BASIN 1101 LR5000 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 82.35
35212476 | FRRB - BIG BASIN 1101 LR5000 | Materials | Electrical Specialties | Not assigned | 003/2021 | 17.46
35212476 | FRRB - BIG BASIN 1101 LR5000 | Materials | Fabricated Structures | Not assigned | 003/2021 | 34.96
35212476 | FRRB - BIG BASIN 1101 LR5000 | Materials | Material Burden | Not assigned | 003/2021 | 32.75
35212476 | FRRB - BIG BASIN 1101 LR5000 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 204.43
35212476 | FRRB - BIG BASIN 1101 LR5000 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2798.67
35212476 | FRRB - BIG BASIN 1101 LR5000 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2562.09
35212476 | FRRB - BIG BASIN 1101 LR5000 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2601.95
35212476 | FRRB - BIG BASIN 1101 LR5000 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6913.57
35212476 | FRRB - BIG BASIN 1101 LR5000 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6913.57
35212476 | FRRB - BIG BASIN 1101 LR5000 | Other | AFUDC-Equity | Not assigned | 003/2021 | 7021.13
35212476 | FRRB - BIG BASIN 1101 LR5000 | Other | Benefits OH | Not assigned | 003/2021 | 155.44
35212476 | FRRB - BIG BASIN 1101 LR5000 | Other | Building Service Overhead | Not assigned | 003/2021 | 28.1
35212476 | FRRB - BIG BASIN 1101 LR5000 | Other | Capitalized A&G | Not assigned | 003/2021 | 150.55
35212476 | FRRB - BIG BASIN 1101 LR5000 | Other | Cost Adjustments | Not assigned | 003/2021 | -3354.97
35212476 | FRRB - BIG BASIN 1101 LR5000 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 67.79
35212476 | FRRB - BIG BASIN 1101 LR5000 | Other | IT Device OH | Not assigned | 003/2021 | 15.95
35212476 | FRRB - BIG BASIN 1101 LR5000 | Other | Minor Material OH | Not assigned | 003/2021 | 20.59
35212476 | FRRB - BIG BASIN 1101 LR5000 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 91.81
35212476 | FRRB - BIG BASIN 1101 LR5000 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 1.83
35212476 | FRRB - BIG BASIN 1101 LR5000 | Other | Operation Mgmt & Support - IT | Not assigned | 003/2021 | 16.2
35212476 | FRRB - BIG BASIN 1101 LR5000 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 55.32
35212477 | FRRB - BIG BASIN 1101 LR10720 | Contract | Contracts | Not assigned | 003/2021 | 22585.12
35212477 | FRRB - BIG BASIN 1101 LR10720 | Labor External | Contractor Activity Charges | Not assigned | 003/2021 | 0.04
35212477 | FRRB - BIG BASIN 1101 LR10720 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 61.12
35212477 | FRRB - BIG BASIN 1101 LR10720 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 3.74
35212477 | FRRB - BIG BASIN 1101 LR10720 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 43.69
35212477 | FRRB - BIG BASIN 1101 LR10720 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 1.32
35212477 | FRRB - BIG BASIN 1101 LR10720 | Labor Internal | Indirect Labor - IT | Not assigned | 003/2021 | 16.21
35212477 | FRRB - BIG BASIN 1101 LR10720 | Labor Internal | IT Activity Charge - Type A | Not assigned | 003/2021 | 43.47
35212477 | FRRB - BIG BASIN 1101 LR10720 | Labor Internal | Mapping | Not assigned | 003/2021 | 67.76
35212477 | FRRB - BIG BASIN 1101 LR10720 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 35.47
35212477 | FRRB - BIG BASIN 1101 LR10720 | Materials | Electrical Specialties | Not assigned | 003/2021 | 7.52
35212477 | FRRB - BIG BASIN 1101 LR10720 | Materials | Fabricated Structures | Not assigned | 003/2021 | 15.05
35212477 | FRRB - BIG BASIN 1101 LR10720 | Materials | Material Burden | Not assigned | 003/2021 | 14.1
35212477 | FRRB - BIG BASIN 1101 LR10720 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 88.04
35212477 | FRRB - BIG BASIN 1101 LR10720 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1205.26
35212477 | FRRB - BIG BASIN 1101 LR10720 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1103.38
35212477 | FRRB - BIG BASIN 1101 LR10720 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1120.55
35212477 | FRRB - BIG BASIN 1101 LR10720 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2977.38
35212477 | FRRB - BIG BASIN 1101 LR10720 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2977.38
35212477 | FRRB - BIG BASIN 1101 LR10720 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3023.7
35212477 | FRRB - BIG BASIN 1101 LR10720 | Other | Benefits OH | Not assigned | 003/2021 | 66.94
35212477 | FRRB - BIG BASIN 1101 LR10720 | Other | Building Service Overhead | Not assigned | 003/2021 | 12.1
35212477 | FRRB - BIG BASIN 1101 LR10720 | Other | Capitalized A&G | Not assigned | 003/2021 | 64.84
35212477 | FRRB - BIG BASIN 1101 LR10720 | Other | Cost Adjustments | Not assigned | 003/2021 | -1444.84
35212477 | FRRB - BIG BASIN 1101 LR10720 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 29.19
35212477 | FRRB - BIG BASIN 1101 LR10720 | Other | IT Device OH | Not assigned | 003/2021 | 6.88
35212477 | FRRB - BIG BASIN 1101 LR10720 | Other | Minor Material OH | Not assigned | 003/2021 | 8.86
35212477 | FRRB - BIG BASIN 1101 LR10720 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 39.54
35212477 | FRRB - BIG BASIN 1101 LR10720 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 0.79
35212477 | FRRB - BIG BASIN 1101 LR10720 | Other | Operation Mgmt & Support - IT | Not assigned | 003/2021 | 6.98
35212477 | FRRB - BIG BASIN 1101 LR10720 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 23.82
35212478 | FRRB - SWIFT 2110 XR332 | Contract | Contracts | Not assigned | 003/2021 | -47405.9
35212478 | FRRB - SWIFT 2110 XR332 | Labor Internal | Electric Activity Charge - Non-Type A | Not assigned | 003/2021 | 3.94
35212478 | FRRB - SWIFT 2110 XR332 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 60.94
35212478 | FRRB - SWIFT 2110 XR332 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | -48.21
35212478 | FRRB - SWIFT 2110 XR332 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 21.53
35212478 | FRRB - SWIFT 2110 XR332 | Labor Internal | Mapping | Not assigned | 003/2021 | -142.22
35212478 | FRRB - SWIFT 2110 XR332 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | -16.37
35212478 | FRRB - SWIFT 2110 XR332 | Materials | Material Burden | Not assigned | 003/2021 | -50.68
35212478 | FRRB - SWIFT 2110 XR332 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | -363.94
35212478 | FRRB - SWIFT 2110 XR332 | Materials | Purchasing Card | Not assigned | 003/2021 | 246
35212478 | FRRB - SWIFT 2110 XR332 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 9841.46
35212478 | FRRB - SWIFT 2110 XR332 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 9009.54
35212478 | FRRB - SWIFT 2110 XR332 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 8966.16
35212478 | FRRB - SWIFT 2110 XR332 | Other | AFUDC-Equity | Not assigned | 001/2021 | 24311.47
35212478 | FRRB - SWIFT 2110 XR332 | Other | AFUDC-Equity | Not assigned | 002/2021 | 24311.47
35212478 | FRRB - SWIFT 2110 XR332 | Other | AFUDC-Equity | Not assigned | 003/2021 | 24194.41
35212478 | FRRB - SWIFT 2110 XR332 | Other | Benefits OH | Not assigned | 003/2021 | -42.72
35212478 | FRRB - SWIFT 2110 XR332 | Other | Building Service Overhead | Not assigned | 003/2021 | -7.72
35212478 | FRRB - SWIFT 2110 XR332 | Other | Capitalized A&G | Not assigned | 003/2021 | -28.48
35212478 | FRRB - SWIFT 2110 XR332 | Other | Cost Adjustments | Not assigned | 003/2021 | -7220.52
35212478 | FRRB - SWIFT 2110 XR332 | Other | Fleet OH - Elec | Not assigned | 003/2021 | -31.32
35212478 | FRRB - SWIFT 2110 XR332 | Other | IT Device OH | Not assigned | 003/2021 | -4.38
35212478 | FRRB - SWIFT 2110 XR332 | Other | Minor Material OH | Not assigned | 003/2021 | -11.99
35212478 | FRRB - SWIFT 2110 XR332 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | -42.42
35212478 | FRRB - SWIFT 2110 XR332 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 12.89
35212478 | FRRB - SWIFT 2110 XR332 | Other | Payroll Taxes OH | Not assigned | 003/2021 | -15.21
35212479 | FRRB - BIG BEND 1102 CB | Contract | Contracts | Not assigned | 002/2021 | 280936.73
35212479 | FRRB - BIG BEND 1102 CB | Contract | Contracts | Not assigned | 003/2021 | 10818.36
35212479 | FRRB - BIG BEND 1102 CB | Labor External | Contractor Activity Charges | Not assigned | 002/2021 | 67.49
35212479 | FRRB - BIG BEND 1102 CB | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 3780.88
35212479 | FRRB - BIG BEND 1102 CB | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 609.89
35212479 | FRRB - BIG BEND 1102 CB | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 157.71
35212479 | FRRB - BIG BEND 1102 CB | Labor Internal | GAS Activity Charge - Type A | Not assigned | 002/2021 | 16.91
35212479 | FRRB - BIG BEND 1102 CB | Labor Internal | GAS Activity Charge - Type A | Not assigned | 003/2021 | 5.11
35212479 | FRRB - BIG BEND 1102 CB | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1567.43
35212479 | FRRB - BIG BEND 1102 CB | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 11
35212479 | FRRB - BIG BEND 1102 CB | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 215.47
35212479 | FRRB - BIG BEND 1102 CB | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 55.72
35212479 | FRRB - BIG BEND 1102 CB | Labor Internal | Indirect Labor - Gas | Not assigned | 002/2021 | 6.12
35212479 | FRRB - BIG BEND 1102 CB | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 1.85
35212479 | FRRB - BIG BEND 1102 CB | Labor Internal | Mapping | Not assigned | 002/2021 | 842.81
35212479 | FRRB - BIG BEND 1102 CB | Labor Internal | Mapping | Not assigned | 003/2021 | 32.46
35212479 | FRRB - BIG BEND 1102 CB | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1057.45
35212479 | FRRB - BIG BEND 1102 CB | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 39.33
35212479 | FRRB - BIG BEND 1102 CB | Materials | Chemicals,Cleaners,Compounds & Lab Suppl | Not assigned | 002/2021 | 159.75
35212479 | FRRB - BIG BEND 1102 CB | Materials | Conductors, Cable & Wire Connectors | Not assigned | 002/2021 | -158.56
35212479 | FRRB - BIG BEND 1102 CB | Materials | Construction Supplies | Not assigned | 002/2021 | -36.09
35212479 | FRRB - BIG BEND 1102 CB | Materials | Fabricated Structures | Not assigned | 002/2021 | -460.97
35212479 | FRRB - BIG BEND 1102 CB | Materials | Material Burden | Not assigned | 002/2021 | 2496.51
35212479 | FRRB - BIG BEND 1102 CB | Materials | Materials Not Otherwise Classified | Not assigned | 002/2021 | -650.95
35212479 | FRRB - BIG BEND 1102 CB | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 17816.71
35212479 | FRRB - BIG BEND 1102 CB | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 002/2021 | 1.02
35212479 | FRRB - BIG BEND 1102 CB | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 8720.8
35212479 | FRRB - BIG BEND 1102 CB | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 8244.28
35212479 | FRRB - BIG BEND 1102 CB | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 8513.89
35212479 | FRRB - BIG BEND 1102 CB | Other | AFUDC-Equity | Not assigned | 001/2021 | 21543.11
35212479 | FRRB - BIG BEND 1102 CB | Other | AFUDC-Equity | Not assigned | 002/2021 | 22246.47
35212479 | FRRB - BIG BEND 1102 CB | Other | AFUDC-Equity | Not assigned | 003/2021 | 22973.98
35212479 | FRRB - BIG BEND 1102 CB | Other | Benefits OH | Not assigned | 002/2021 | 2562.36
35212479 | FRRB - BIG BEND 1102 CB | Other | Benefits OH | Not assigned | 003/2021 | 66.01
35212479 | FRRB - BIG BEND 1102 CB | Other | Building Service Overhead | Not assigned | 002/2021 | 441.91
35212479 | FRRB - BIG BEND 1102 CB | Other | Building Service Overhead | Not assigned | 003/2021 | 11.93
35212479 | FRRB - BIG BEND 1102 CB | Other | Capitalized A&G | Not assigned | 002/2021 | 1934.67
35212479 | FRRB - BIG BEND 1102 CB | Other | Capitalized A&G | Not assigned | 003/2021 | 71.9
35212479 | FRRB - BIG BEND 1102 CB | Other | Cost Adjustments | Not assigned | 002/2021 | 12700.49
35212479 | FRRB - BIG BEND 1102 CB | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1047.27
35212479 | FRRB - BIG BEND 1102 CB | Other | Fleet OH - Elec | Not assigned | 003/2021 | 7.35
35212479 | FRRB - BIG BEND 1102 CB | Other | Fleet OH - Gas | Not assigned | 002/2021 | 5.24
35212479 | FRRB - BIG BEND 1102 CB | Other | Fleet OH - Gas | Not assigned | 003/2021 | 1.58
35212479 | FRRB - BIG BEND 1102 CB | Other | IT Device OH | Not assigned | 002/2021 | 250.81
35212479 | FRRB - BIG BEND 1102 CB | Other | IT Device OH | Not assigned | 003/2021 | 6.77
35212479 | FRRB - BIG BEND 1102 CB | Other | Minor Material OH | Not assigned | 002/2021 | 1362.8
35212479 | FRRB - BIG BEND 1102 CB | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1418.54
35212479 | FRRB - BIG BEND 1102 CB | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 9.96
35212479 | FRRB - BIG BEND 1102 CB | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 129.05
35212479 | FRRB - BIG BEND 1102 CB | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 33.37
35212479 | FRRB - BIG BEND 1102 CB | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 9.38
35212479 | FRRB - BIG BEND 1102 CB | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 2.84
35212479 | FRRB - BIG BEND 1102 CB | Other | Payroll Taxes OH | Not assigned | 002/2021 | 865.69
35212479 | FRRB - BIG BEND 1102 CB | Other | Payroll Taxes OH | Not assigned | 003/2021 | 23.49
35212480 | FRRB - BIG BEND 1102 LR1972 | Contract | Contracts | Not assigned | 002/2021 | 282327.5
35212480 | FRRB - BIG BEND 1102 LR1972 | Contract | Contracts | Not assigned | 003/2021 | 10871.91
35212480 | FRRB - BIG BEND 1102 LR1972 | Labor External | Contractor Activity Charges | Not assigned | 002/2021 | 67.82
35212480 | FRRB - BIG BEND 1102 LR1972 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 3799.6
35212480 | FRRB - BIG BEND 1102 LR1972 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 612.9
35212480 | FRRB - BIG BEND 1102 LR1972 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 158.49
35212480 | FRRB - BIG BEND 1102 LR1972 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 002/2021 | 16.99
35212480 | FRRB - BIG BEND 1102 LR1972 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 003/2021 | 5.13
35212480 | FRRB - BIG BEND 1102 LR1972 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1575.19
35212480 | FRRB - BIG BEND 1102 LR1972 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 11.06
35212480 | FRRB - BIG BEND 1102 LR1972 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 216.54
35212480 | FRRB - BIG BEND 1102 LR1972 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 55.99
35212480 | FRRB - BIG BEND 1102 LR1972 | Labor Internal | Indirect Labor - Gas | Not assigned | 002/2021 | 6.15
35212480 | FRRB - BIG BEND 1102 LR1972 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 1.86
35212480 | FRRB - BIG BEND 1102 LR1972 | Labor Internal | Mapping | Not assigned | 002/2021 | 846.98
35212480 | FRRB - BIG BEND 1102 LR1972 | Labor Internal | Mapping | Not assigned | 003/2021 | 32.62
35212480 | FRRB - BIG BEND 1102 LR1972 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1062.68
35212480 | FRRB - BIG BEND 1102 LR1972 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 39.52
35212480 | FRRB - BIG BEND 1102 LR1972 | Materials | Chemicals,Cleaners,Compounds & Lab Suppl | Not assigned | 002/2021 | 160.54
35212480 | FRRB - BIG BEND 1102 LR1972 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 002/2021 | -159.35
35212480 | FRRB - BIG BEND 1102 LR1972 | Materials | Construction Supplies | Not assigned | 002/2021 | -36.27
35212480 | FRRB - BIG BEND 1102 LR1972 | Materials | Fabricated Structures | Not assigned | 002/2021 | -463.25
35212480 | FRRB - BIG BEND 1102 LR1972 | Materials | Material Burden | Not assigned | 002/2021 | 2508.86
35212480 | FRRB - BIG BEND 1102 LR1972 | Materials | Materials Not Otherwise Classified | Not assigned | 002/2021 | -654.18
35212480 | FRRB - BIG BEND 1102 LR1972 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 17904.91
35212480 | FRRB - BIG BEND 1102 LR1972 | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 002/2021 | 1.03
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 8756.46
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 8278.21
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 8549.15
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | AFUDC-Equity | Not assigned | 001/2021 | 21631.19
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | AFUDC-Equity | Not assigned | 002/2021 | 22338.04
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | AFUDC-Equity | Not assigned | 003/2021 | 23069.14
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Benefits OH | Not assigned | 002/2021 | 2575.04
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Benefits OH | Not assigned | 003/2021 | 66.34
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Building Service Overhead | Not assigned | 002/2021 | 444.09
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Building Service Overhead | Not assigned | 003/2021 | 11.99
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Capitalized A&G | Not assigned | 002/2021 | 1944.25
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Capitalized A&G | Not assigned | 003/2021 | 72.25
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Cost Adjustments | Not assigned | 002/2021 | 12763.35
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1052.45
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 7.39
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Fleet OH - Gas | Not assigned | 002/2021 | 5.26
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 1.59
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | IT Device OH | Not assigned | 002/2021 | 252.05
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | IT Device OH | Not assigned | 003/2021 | 6.81
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Minor Material OH | Not assigned | 002/2021 | 1369.55
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1425.57
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 10.01
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 129.69
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 33.54
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 9.43
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 2.85
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 869.99
35212480 | FRRB - BIG BEND 1102 LR1972 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 23.6
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Contract | Contracts | Not assigned | 001/2021 | -120307.46
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Contract | Contracts | Not assigned | 002/2021 | 689824.84
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Contract | Contracts | Not assigned | 003/2021 | 26563.89
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Labor External | Contractor Activity Charges | Not assigned | 002/2021 | 165.72
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 9283.75
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 1497.54
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 387.24
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 002/2021 | 41.52
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 003/2021 | 12.55
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -122.35
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 3848.74
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 27.01
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 529.08
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 136.81
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Labor Internal | Indirect Labor - Gas | Not assigned | 002/2021 | 15.02
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 4.54
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Labor Internal | Mapping | Not assigned | 001/2021 | -360.92
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Labor Internal | Mapping | Not assigned | 002/2021 | 2069.47
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Labor Internal | Mapping | Not assigned | 003/2021 | 79.69
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | -72.69
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 2596.5
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 96.57
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Materials | Chemicals,Cleaners,Compounds & Lab Suppl | Not assigned | 002/2021 | 392.26
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 002/2021 | -389.34
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Materials | Construction Supplies | Not assigned | 002/2021 | -88.61
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Materials | Fabricated Structures | Not assigned | 002/2021 | -1131.88
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Materials | Material Burden | Not assigned | 002/2021 | 6130.04
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Materials | Materials Not Otherwise Classified | Not assigned | 002/2021 | -1598.38
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 43747.97
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 002/2021 | 2.51
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 21443.02
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 20166.73
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 20828.73
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | AFUDC-Equity | Not assigned | 001/2021 | 52949.11
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | AFUDC-Equity | Not assigned | 002/2021 | 54418.17
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | AFUDC-Equity | Not assigned | 003/2021 | 56204.51
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Benefits OH | Not assigned | 001/2021 | -145.21
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Benefits OH | Not assigned | 002/2021 | 6291.74
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Benefits OH | Not assigned | 003/2021 | 162.07
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Building Service Overhead | Not assigned | 001/2021 | -24.92
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Building Service Overhead | Not assigned | 002/2021 | 1085.07
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Building Service Overhead | Not assigned | 003/2021 | 29.29
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Capitalized A&G | Not assigned | 001/2021 | -132.89
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Capitalized A&G | Not assigned | 002/2021 | 4750.49
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Capitalized A&G | Not assigned | 003/2021 | 176.54
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Cost Adjustments | Not assigned | 002/2021 | 31185.35
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Fleet OH - Elec | Not assigned | 001/2021 | -81.75
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 2571.5
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 18.05
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Fleet OH - Gas | Not assigned | 002/2021 | 12.86
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 3.89
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | IT Device OH | Not assigned | 001/2021 | -14.14
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | IT Device OH | Not assigned | 002/2021 | 615.85
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | IT Device OH | Not assigned | 003/2021 | 16.63
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Minor Material OH | Not assigned | 002/2021 | 3346.3
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -110.73
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 3483.16
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 24.45
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 316.88
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 81.94
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 23.04
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 6.96
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Payroll Taxes OH | Not assigned | 001/2021 | -49.06
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 2125.67
35212481 | FRRB - WYANDOTTE 1103 LR1508 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 57.66
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Contract | Contracts | Not assigned | 002/2021 | 554224.19
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Contract | Contracts | Not assigned | 003/2021 | 21342.16
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Labor External | Contractor Activity Charges | Not assigned | 002/2021 | 133.13
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 7458.81
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 1203.17
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 311.12
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 002/2021 | 33.36
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 003/2021 | 10.08
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 3092.19
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 21.71
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 425.08
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 109.92
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Labor Internal | Indirect Labor - Gas | Not assigned | 002/2021 | 12.07
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 3.65
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Labor Internal | Mapping | Not assigned | 002/2021 | 1662.67
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Labor Internal | Mapping | Not assigned | 003/2021 | 64.03
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 2086.1
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 77.59
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Materials | Chemicals,Cleaners,Compounds & Lab Suppl | Not assigned | 002/2021 | 315.15
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 002/2021 | -312.81
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Materials | Construction Supplies | Not assigned | 002/2021 | -71.19
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Materials | Fabricated Structures | Not assigned | 002/2021 | -909.38
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Materials | Material Burden | Not assigned | 002/2021 | 4925.04
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Materials | Materials Not Otherwise Classified | Not assigned | 002/2021 | -1284.19
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 35148.32
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 002/2021 | 2.02
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 17245.5
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 16301.93
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 16833.8
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | AFUDC-Equity | Not assigned | 001/2021 | 42601.75
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | AFUDC-Equity | Not assigned | 002/2021 | 43989.34
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | AFUDC-Equity | Not assigned | 003/2021 | 45424.53
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Benefits OH | Not assigned | 002/2021 | 5054.95
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Benefits OH | Not assigned | 003/2021 | 130.21
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Building Service Overhead | Not assigned | 002/2021 | 871.78
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Building Service Overhead | Not assigned | 003/2021 | 23.54
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Capitalized A&G | Not assigned | 002/2021 | 3816.67
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Capitalized A&G | Not assigned | 003/2021 | 141.85
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Cost Adjustments | Not assigned | 002/2021 | 25055.16
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 2066.01
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 14.5
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Fleet OH - Gas | Not assigned | 002/2021 | 10.33
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 3.12
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | IT Device OH | Not assigned | 002/2021 | 494.79
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | IT Device OH | Not assigned | 003/2021 | 13.36
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Minor Material OH | Not assigned | 002/2021 | 2688.5
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 2798.47
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 19.64
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 254.59
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 65.83
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 18.51
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 5.59
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 1707.82
35212483 | FRRB - WYANDOTTE 1103 LR1974 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 46.33
35212486 | FRRB - KANAKA 1101 CB | Contract | Contracts | Not assigned | 002/2021 | 214179.49
35212486 | FRRB - KANAKA 1101 CB | Contract | Contracts | Not assigned | 003/2021 | 8247.66
35212486 | FRRB - KANAKA 1101 CB | Labor External | Contractor Activity Charges | Not assigned | 002/2021 | 51.45
35212486 | FRRB - KANAKA 1101 CB | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 2882.45
35212486 | FRRB - KANAKA 1101 CB | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 464.96
35212486 | FRRB - KANAKA 1101 CB | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 120.23
35212486 | FRRB - KANAKA 1101 CB | Labor Internal | GAS Activity Charge - Type A | Not assigned | 002/2021 | 12.89
35212486 | FRRB - KANAKA 1101 CB | Labor Internal | GAS Activity Charge - Type A | Not assigned | 003/2021 | 3.9
35212486 | FRRB - KANAKA 1101 CB | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1194.97
35212486 | FRRB - KANAKA 1101 CB | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 8.39
35212486 | FRRB - KANAKA 1101 CB | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 164.27
35212486 | FRRB - KANAKA 1101 CB | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 42.48
35212486 | FRRB - KANAKA 1101 CB | Labor Internal | Indirect Labor - Gas | Not assigned | 002/2021 | 4.66
35212486 | FRRB - KANAKA 1101 CB | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 1.41
35212486 | FRRB - KANAKA 1101 CB | Labor Internal | Mapping | Not assigned | 002/2021 | 642.54
35212486 | FRRB - KANAKA 1101 CB | Labor Internal | Mapping | Not assigned | 003/2021 | 24.74
35212486 | FRRB - KANAKA 1101 CB | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 806.17
35212486 | FRRB - KANAKA 1101 CB | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 29.98
35212486 | FRRB - KANAKA 1101 CB | Materials | Chemicals,Cleaners,Compounds & Lab Suppl | Not assigned | 002/2021 | 121.79
35212486 | FRRB - KANAKA 1101 CB | Materials | Conductors, Cable & Wire Connectors | Not assigned | 002/2021 | -120.89
35212486 | FRRB - KANAKA 1101 CB | Materials | Construction Supplies | Not assigned | 002/2021 | -27.51
35212486 | FRRB - KANAKA 1101 CB | Materials | Fabricated Structures | Not assigned | 002/2021 | -351.43
35212486 | FRRB - KANAKA 1101 CB | Materials | Material Burden | Not assigned | 002/2021 | 1903.27
35212486 | FRRB - KANAKA 1101 CB | Materials | Materials Not Otherwise Classified | Not assigned | 002/2021 | -496.27
35212486 | FRRB - KANAKA 1101 CB | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 13583.04
35212486 | FRRB - KANAKA 1101 CB | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 002/2021 | 0.78
35212486 | FRRB - KANAKA 1101 CB | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 12832.61
35212486 | FRRB - KANAKA 1101 CB | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 11946.57
35212486 | FRRB - KANAKA 1101 CB | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 12152.11
35212486 | FRRB - KANAKA 1101 CB | Other | AFUDC-Equity | Not assigned | 001/2021 | 31700.54
35212486 | FRRB - KANAKA 1101 CB | Other | AFUDC-Equity | Not assigned | 002/2021 | 32236.77
35212486 | FRRB - KANAKA 1101 CB | Other | AFUDC-Equity | Not assigned | 003/2021 | 32791.4
35212486 | FRRB - KANAKA 1101 CB | Other | Benefits OH | Not assigned | 002/2021 | 1953.46
35212486 | FRRB - KANAKA 1101 CB | Other | Benefits OH | Not assigned | 003/2021 | 50.31
35212486 | FRRB - KANAKA 1101 CB | Other | Building Service Overhead | Not assigned | 002/2021 | 336.9
35212486 | FRRB - KANAKA 1101 CB | Other | Building Service Overhead | Not assigned | 003/2021 | 9.08
35212486 | FRRB - KANAKA 1101 CB | Other | Capitalized A&G | Not assigned | 002/2021 | 1474.94
35212486 | FRRB - KANAKA 1101 CB | Other | Capitalized A&G | Not assigned | 003/2021 | 54.81
35212486 | FRRB - KANAKA 1101 CB | Other | Cost Adjustments | Not assigned | 002/2021 | 9682.55
35212486 | FRRB - KANAKA 1101 CB | Other | Fleet OH - Elec | Not assigned | 002/2021 | 798.41
35212486 | FRRB - KANAKA 1101 CB | Other | Fleet OH - Elec | Not assigned | 003/2021 | 5.6
35212486 | FRRB - KANAKA 1101 CB | Other | Fleet OH - Gas | Not assigned | 002/2021 | 3.99
35212486 | FRRB - KANAKA 1101 CB | Other | Fleet OH - Gas | Not assigned | 003/2021 | 1.21
35212486 | FRRB - KANAKA 1101 CB | Other | IT Device OH | Not assigned | 002/2021 | 191.2
35212486 | FRRB - KANAKA 1101 CB | Other | IT Device OH | Not assigned | 003/2021 | 5.16
35212486 | FRRB - KANAKA 1101 CB | Other | Minor Material OH | Not assigned | 002/2021 | 1038.97
35212486 | FRRB - KANAKA 1101 CB | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1081.47
35212486 | FRRB - KANAKA 1101 CB | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 7.59
35212486 | FRRB - KANAKA 1101 CB | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 98.39
35212486 | FRRB - KANAKA 1101 CB | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 25.44
35212486 | FRRB - KANAKA 1101 CB | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 7.15
35212486 | FRRB - KANAKA 1101 CB | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 2.16
35212486 | FRRB - KANAKA 1101 CB | Other | Payroll Taxes OH | Not assigned | 002/2021 | 659.99
35212486 | FRRB - KANAKA 1101 CB | Other | Payroll Taxes OH | Not assigned | 003/2021 | 17.89
35212487 | FRRB - KANAKA 1101 LR1034 | Contract | Contracts | Not assigned | 002/2021 | 186363.97
35212487 | FRRB - KANAKA 1101 LR1034 | Contract | Contracts | Not assigned | 003/2021 | 7176.53
35212487 | FRRB - KANAKA 1101 LR1034 | Labor External | Contractor Activity Charges | Not assigned | 002/2021 | 44.77
35212487 | FRRB - KANAKA 1101 LR1034 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 2508.11
35212487 | FRRB - KANAKA 1101 LR1034 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 404.58
35212487 | FRRB - KANAKA 1101 LR1034 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 104.62
35212487 | FRRB - KANAKA 1101 LR1034 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 002/2021 | 11.22
35212487 | FRRB - KANAKA 1101 LR1034 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 003/2021 | 3.39
35212487 | FRRB - KANAKA 1101 LR1034 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1039.78
35212487 | FRRB - KANAKA 1101 LR1034 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 7.3
35212487 | FRRB - KANAKA 1101 LR1034 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 142.94
35212487 | FRRB - KANAKA 1101 LR1034 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 36.96
35212487 | FRRB - KANAKA 1101 LR1034 | Labor Internal | Indirect Labor - Gas | Not assigned | 002/2021 | 4.06
35212487 | FRRB - KANAKA 1101 LR1034 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 1.23
35212487 | FRRB - KANAKA 1101 LR1034 | Labor Internal | Mapping | Not assigned | 002/2021 | 559.09
35212487 | FRRB - KANAKA 1101 LR1034 | Labor Internal | Mapping | Not assigned | 003/2021 | 21.53
35212487 | FRRB - KANAKA 1101 LR1034 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 701.48
35212487 | FRRB - KANAKA 1101 LR1034 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 26.09
35212487 | FRRB - KANAKA 1101 LR1034 | Materials | Chemicals,Cleaners,Compounds & Lab Suppl | Not assigned | 002/2021 | 105.97
35212487 | FRRB - KANAKA 1101 LR1034 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 002/2021 | -105.19
35212487 | FRRB - KANAKA 1101 LR1034 | Materials | Construction Supplies | Not assigned | 002/2021 | -23.94
35212487 | FRRB - KANAKA 1101 LR1034 | Materials | Fabricated Structures | Not assigned | 002/2021 | -305.79
35212487 | FRRB - KANAKA 1101 LR1034 | Materials | Material Burden | Not assigned | 002/2021 | 1656.1
35212487 | FRRB - KANAKA 1101 LR1034 | Materials | Materials Not Otherwise Classified | Not assigned | 002/2021 | -431.82
35212487 | FRRB - KANAKA 1101 LR1034 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 11819.01
35212487 | FRRB - KANAKA 1101 LR1034 | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 002/2021 | 0.68
35212487 | FRRB - KANAKA 1101 LR1034 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 6808.53
35212487 | FRRB - KANAKA 1101 LR1034 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 6405.9
35212487 | FRRB - KANAKA 1101 LR1034 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 6584.74
35212487 | FRRB - KANAKA 1101 LR1034 | Other | AFUDC-Equity | Not assigned | 001/2021 | 16819.17
35212487 | FRRB - KANAKA 1101 LR1034 | Other | AFUDC-Equity | Not assigned | 002/2021 | 17285.76
35212487 | FRRB - KANAKA 1101 LR1034 | Other | AFUDC-Equity | Not assigned | 003/2021 | 17768.36
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Benefits OH | Not assigned | 002/2021 | 1699.79
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Benefits OH | Not assigned | 003/2021 | 43.8
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Building Service Overhead | Not assigned | 002/2021 | 293.15
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Building Service Overhead | Not assigned | 003/2021 | 7.93
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Capitalized A&G | Not assigned | 002/2021 | 1283.4
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Capitalized A&G | Not assigned | 003/2021 | 47.7
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Cost Adjustments | Not assigned | 002/2021 | 8425.07
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 694.72
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 4.88
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Fleet OH - Gas | Not assigned | 002/2021 | 3.47
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 1.05
35212487 | FRRB - KANAKA 1101 LR1034 | Other | IT Device OH | Not assigned | 002/2021 | 166.39
35212487 | FRRB - KANAKA 1101 LR1034 | Other | IT Device OH | Not assigned | 003/2021 | 4.49
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Minor Material OH | Not assigned | 002/2021 | 904.04
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 941.02
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 6.61
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 85.61
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 22.14
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 6.22
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 1.88
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 574.28
35212487 | FRRB - KANAKA 1101 LR1034 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 15.58
35212488 | FRRB - KANAKA 1101 LR1406 | Contract | Contracts | Not assigned | 002/2021 | 619590.65
35212488 | FRRB - KANAKA 1101 LR1406 | Contract | Contracts | Not assigned | 003/2021 | 23859.3
35212488 | FRRB - KANAKA 1101 LR1406 | Labor External | Contractor Activity Charges | Not assigned | 002/2021 | 148.84
35212488 | FRRB - KANAKA 1101 LR1406 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 8338.52
35212488 | FRRB - KANAKA 1101 LR1406 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 1345.07
35212488 | FRRB - KANAKA 1101 LR1406 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 347.81
35212488 | FRRB - KANAKA 1101 LR1406 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 002/2021 | 37.29
35212488 | FRRB - KANAKA 1101 LR1406 | Labor Internal | GAS Activity Charge - Type A | Not assigned | 003/2021 | 11.27
35212488 | FRRB - KANAKA 1101 LR1406 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 3456.88
35212488 | FRRB - KANAKA 1101 LR1406 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 24.27
35212488 | FRRB - KANAKA 1101 LR1406 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 475.21
35212488 | FRRB - KANAKA 1101 LR1406 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 122.88
35212488 | FRRB - KANAKA 1101 LR1406 | Labor Internal | Indirect Labor - Gas | Not assigned | 002/2021 | 13.49
35212488 | FRRB - KANAKA 1101 LR1406 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 4.08
35212488 | FRRB - KANAKA 1101 LR1406 | Labor Internal | Mapping | Not assigned | 002/2021 | 1858.77
35212488 | FRRB - KANAKA 1101 LR1406 | Labor Internal | Mapping | Not assigned | 003/2021 | 71.58
35212488 | FRRB - KANAKA 1101 LR1406 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 2332.15
35212488 | FRRB - KANAKA 1101 LR1406 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 86.74
35212488 | FRRB - KANAKA 1101 LR1406 | Materials | Chemicals,Cleaners,Compounds & Lab Suppl | Not assigned | 002/2021 | 352.32
35212488 | FRRB - KANAKA 1101 LR1406 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 002/2021 | -349.7
35212488 | FRRB - KANAKA 1101 LR1406 | Materials | Construction Supplies | Not assigned | 002/2021 | -79.59
35212488 | FRRB - KANAKA 1101 LR1406 | Materials | Fabricated Structures | Not assigned | 002/2021 | -1016.64
35212488 | FRRB - KANAKA 1101 LR1406 | Materials | Material Burden | Not assigned | 002/2021 | 5505.91
35212488 | FRRB - KANAKA 1101 LR1406 | Materials | Materials Not Otherwise Classified | Not assigned | 002/2021 | -1435.65
35212488 | FRRB - KANAKA 1101 LR1406 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 39293.79
35212488 | FRRB - KANAKA 1101 LR1406 | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 002/2021 | 2.26
35212488 | FRRB - KANAKA 1101 LR1406 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 21858.19
35212488 | FRRB - KANAKA 1101 LR1406 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 20585.32
35212488 | FRRB - KANAKA 1101 LR1406 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 21179.92
35212488 | FRRB - KANAKA 1101 LR1406 | Other | AFUDC-Equity | Not assigned | 001/2021 | 53996.45
35212488 | FRRB - KANAKA 1101 LR1406 | Other | AFUDC-Equity | Not assigned | 002/2021 | 55547.69
35212488 | FRRB - KANAKA 1101 LR1406 | Other | AFUDC-Equity | Not assigned | 003/2021 | 57152.15
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Benefits OH | Not assigned | 002/2021 | 5651.14
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Benefits OH | Not assigned | 003/2021 | 145.56
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Building Service Overhead | Not assigned | 002/2021 | 974.61
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Building Service Overhead | Not assigned | 003/2021 | 26.32
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Capitalized A&G | Not assigned | 002/2021 | 4266.82
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Capitalized A&G | Not assigned | 003/2021 | 158.57
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Cost Adjustments | Not assigned | 002/2021 | 28010.23
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 2309.68
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.21
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Fleet OH - Gas | Not assigned | 002/2021 | 11.55
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 3.49
35212488 | FRRB - KANAKA 1101 LR1406 | Other | IT Device OH | Not assigned | 002/2021 | 553.14
35212488 | FRRB - KANAKA 1101 LR1406 | Other | IT Device OH | Not assigned | 003/2021 | 14.94
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Minor Material OH | Not assigned | 002/2021 | 3005.59
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 3128.53
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 21.96
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 284.62
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 73.6
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 20.69
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 6.25
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 1909.25
35212488 | FRRB - KANAKA 1101 LR1406 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 51.8
35212489 | FRRB - GIRVAN 1101 LR1330 | Contract | Contracts | Not assigned | 002/2021 | 43504.45
35212489 | FRRB - GIRVAN 1101 LR1330 | Contract | Contracts | Not assigned | 003/2021 | 127106.35
35212489 | FRRB - GIRVAN 1101 LR1330 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 153.64
35212489 | FRRB - GIRVAN 1101 LR1330 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 96.32
35212489 | FRRB - GIRVAN 1101 LR1330 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 129.27
35212489 | FRRB - GIRVAN 1101 LR1330 | Labor Internal | Mapping | Not assigned | 002/2021 | 130.51
35212489 | FRRB - GIRVAN 1101 LR1330 | Labor Internal | Mapping | Not assigned | 003/2021 | 381.32
35212489 | FRRB - GIRVAN 1101 LR1330 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 57.22
35212489 | FRRB - GIRVAN 1101 LR1330 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 76.8
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 32.14
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 64.46
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 201.9
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | AFUDC-Equity | Not assigned | 001/2021 | 79.39
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | AFUDC-Equity | Not assigned | 002/2021 | 173.95
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | AFUDC-Equity | Not assigned | 003/2021 | 544.8
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | Benefits OH | Not assigned | 002/2021 | 114.33
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | Benefits OH | Not assigned | 003/2021 | 145.69
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | Building Service Overhead | Not assigned | 002/2021 | 19.62
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | Building Service Overhead | Not assigned | 003/2021 | 26.33
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | Capitalized A&G | Not assigned | 002/2021 | 104.62
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | Capitalized A&G | Not assigned | 003/2021 | 140.4
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | Cost Adjustments | Not assigned | 002/2021 | 113.13
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | Cost Adjustments | Not assigned | 003/2021 | 1747
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 64.36
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 86.37
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | IT Device OH | Not assigned | 002/2021 | 11.14
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | IT Device OH | Not assigned | 003/2021 | 14.95
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 87.18
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 116.99
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 38.63
35212489 | FRRB - GIRVAN 1101 LR1330 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 51.84
35212490 | FRRB - GIRVAN 1101 LR323094 | Contract | Contracts | Not assigned | 002/2021 | 78165.38
35212490 | FRRB - GIRVAN 1101 LR323094 | Contract | Contracts | Not assigned | 003/2021 | 228374.7
35212490 | FRRB - GIRVAN 1101 LR323094 | Labor Internal | Customer Care Activity Charge - Non-Type | Not assigned | 002/2021 | 0.01
35212490 | FRRB - GIRVAN 1101 LR323094 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 276.04
35212490 | FRRB - GIRVAN 1101 LR323094 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 173.08
35212490 | FRRB - GIRVAN 1101 LR323094 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 232.26
35212490 | FRRB - GIRVAN 1101 LR323094 | Labor Internal | Mapping | Not assigned | 002/2021 | 234.5
35212490 | FRRB - GIRVAN 1101 LR323094 | Labor Internal | Mapping | Not assigned | 003/2021 | 685.12
35212490 | FRRB - GIRVAN 1101 LR323094 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 102.82
35212490 | FRRB - GIRVAN 1101 LR323094 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 137.98
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 57.14
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 115.26
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 362.19
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | AFUDC-Equity | Not assigned | 001/2021 | 141.14
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | AFUDC-Equity | Not assigned | 002/2021 | 311.03
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | AFUDC-Equity | Not assigned | 003/2021 | 977.34
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | Benefits OH | Not assigned | 002/2021 | 205.42
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | Benefits OH | Not assigned | 003/2021 | 261.76
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | Building Service Overhead | Not assigned | 002/2021 | 35.26
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | Building Service Overhead | Not assigned | 003/2021 | 47.31
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | Capitalized A&G | Not assigned | 002/2021 | 187.98
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | Capitalized A&G | Not assigned | 003/2021 | 252.26
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | Cost Adjustments | Not assigned | 002/2021 | 203.27
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | Cost Adjustments | Not assigned | 003/2021 | 3138.88
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 115.63
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 155.18
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | IT Device OH | Not assigned | 002/2021 | 20.01
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | IT Device OH | Not assigned | 003/2021 | 26.85
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 156.63
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 210.19
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 69.41
35212490 | FRRB - GIRVAN 1101 LR323094 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 93.13
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 003/2021 | 2.04
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 69.64
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.69
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 24.6
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 14.44
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2668.69
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2443.1
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2443.44
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6592.49
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6592.49
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6593.41
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Other | Benefits OH | Not assigned | 003/2021 | 23.44
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Other | Building Service Overhead | Not assigned | 003/2021 | 4.24
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Other | Capitalized A&G | Not assigned | 003/2021 | 26.39
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Other | Cost Adjustments | Not assigned | 003/2021 | 238.44
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.46
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Other | IT Device OH | Not assigned | 003/2021 | 2.4
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.63
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 14.74
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 8.35
35212492 | FRRB - AUBERRY 1101 R2845 | Contract | Contracts | Not assigned | 002/2021 | -2446.78
35212492 | FRRB - AUBERRY 1101 R2845 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 97.23
35212492 | FRRB - AUBERRY 1101 R2845 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | -2.49
35212492 | FRRB - AUBERRY 1101 R2845 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 34.35
35212492 | FRRB - AUBERRY 1101 R2845 | Labor Internal | Mapping | Not assigned | 002/2021 | -7.34
35212492 | FRRB - AUBERRY 1101 R2845 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 18.1
35212492 | FRRB - AUBERRY 1101 R2845 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 962.79
35212492 | FRRB - AUBERRY 1101 R2845 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 880.66
35212492 | FRRB - AUBERRY 1101 R2845 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 880
35212492 | FRRB - AUBERRY 1101 R2845 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2378.37
35212492 | FRRB - AUBERRY 1101 R2845 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2376.39
35212492 | FRRB - AUBERRY 1101 R2845 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2374.59
35212492 | FRRB - AUBERRY 1101 R2845 | Other | Benefits OH | Not assigned | 002/2021 | 30.37
35212492 | FRRB - AUBERRY 1101 R2845 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.22
35212492 | FRRB - AUBERRY 1101 R2845 | Other | Capitalized A&G | Not assigned | 002/2021 | 33.1
35212492 | FRRB - AUBERRY 1101 R2845 | Other | Cost Adjustments | Not assigned | 002/2021 | 1277.24
35212492 | FRRB - AUBERRY 1101 R2845 | Other | Cost Adjustments | Not assigned | 003/2021 | 83.93
35212492 | FRRB - AUBERRY 1101 R2845 | Other | Fleet OH - Elec | Not assigned | 002/2021 | -1.66
35212492 | FRRB - AUBERRY 1101 R2845 | Other | IT Device OH | Not assigned | 002/2021 | 2.96
35212492 | FRRB - AUBERRY 1101 R2845 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | -2.25
35212492 | FRRB - AUBERRY 1101 R2845 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 20.57
35212492 | FRRB - AUBERRY 1101 R2845 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.26
35212493 | FRRB - AUBERRY 1101 R324 | Contract | Contracts | Not assigned | 002/2021 | -8249.89
35212493 | FRRB - AUBERRY 1101 R324 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 327.83
35212493 | FRRB - AUBERRY 1101 R324 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | -8.39
35212493 | FRRB - AUBERRY 1101 R324 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 115.82
35212493 | FRRB - AUBERRY 1101 R324 | Labor Internal | Mapping | Not assigned | 002/2021 | -24.75
35212493 | FRRB - AUBERRY 1101 R324 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 61.04
35212493 | FRRB - AUBERRY 1101 R324 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3181.75
35212493 | FRRB - AUBERRY 1101 R324 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2910.31
35212493 | FRRB - AUBERRY 1101 R324 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2908.06
35212493 | FRRB - AUBERRY 1101 R324 | Other | AFUDC-Equity | Not assigned | 001/2021 | 7859.9
35212493 | FRRB - AUBERRY 1101 R324 | Other | AFUDC-Equity | Not assigned | 002/2021 | 7853.23
35212493 | FRRB - AUBERRY 1101 R324 | Other | AFUDC-Equity | Not assigned | 003/2021 | 7847.16
35212493 | FRRB - AUBERRY 1101 R324 | Other | Benefits OH | Not assigned | 002/2021 | 102.4
35212493 | FRRB - AUBERRY 1101 R324 | Other | Building Service Overhead | Not assigned | 002/2021 | 17.59
35212493 | FRRB - AUBERRY 1101 R324 | Other | Capitalized A&G | Not assigned | 002/2021 | 111.6
35212493 | FRRB - AUBERRY 1101 R324 | Other | Cost Adjustments | Not assigned | 002/2021 | 4306.5
35212493 | FRRB - AUBERRY 1101 R324 | Other | Cost Adjustments | Not assigned | 003/2021 | 283
35212493 | FRRB - AUBERRY 1101 R324 | Other | Fleet OH - Elec | Not assigned | 002/2021 | -5.61
35212493 | FRRB - AUBERRY 1101 R324 | Other | IT Device OH | Not assigned | 002/2021 | 9.98
35212493 | FRRB - AUBERRY 1101 R324 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | -7.59
35212493 | FRRB - AUBERRY 1101 R324 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 69.37
35212493 | FRRB - AUBERRY 1101 R324 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 34.59
35212494 | FRRB - AUBERRY 1101 LR37536 | Contract | Contracts | Not assigned | 002/2021 | -3356.32
35212494 | FRRB - AUBERRY 1101 LR37536 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 133.37
35212494 | FRRB - AUBERRY 1101 LR37536 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | -3.41
35212494 | FRRB - AUBERRY 1101 LR37536 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 47.12
35212494 | FRRB - AUBERRY 1101 LR37536 | Labor Internal | Mapping | Not assigned | 002/2021 | -10.07
35212494 | FRRB - AUBERRY 1101 LR37536 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 24.83
35212494 | FRRB - AUBERRY 1101 LR37536 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1256.18
35212494 | FRRB - AUBERRY 1101 LR37536 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1148.99
35212494 | FRRB - AUBERRY 1101 LR37536 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1148.07
35212494 | FRRB - AUBERRY 1101 LR37536 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3103.15
35212494 | FRRB - AUBERRY 1101 LR37536 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3100.44
35212494 | FRRB - AUBERRY 1101 LR37536 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3097.97
35212494 | FRRB - AUBERRY 1101 LR37536 | Other | Benefits OH | Not assigned | 002/2021 | 41.64
35212494 | FRRB - AUBERRY 1101 LR37536 | Other | Building Service Overhead | Not assigned | 002/2021 | 7.14
35212494 | FRRB - AUBERRY 1101 LR37536 | Other | Capitalized A&G | Not assigned | 002/2021 | 45.4
35212494 | FRRB - AUBERRY 1101 LR37536 | Other | Cost Adjustments | Not assigned | 002/2021 | 1752.02
35212494 | FRRB - AUBERRY 1101 LR37536 | Other | Cost Adjustments | Not assigned | 003/2021 | 115.13
35212494 | FRRB - AUBERRY 1101 LR37536 | Other | Fleet OH - Elec | Not assigned | 002/2021 | -2.28
35212494 | FRRB - AUBERRY 1101 LR37536 | Other | IT Device OH | Not assigned | 002/2021 | 4.06
35212494 | FRRB - AUBERRY 1101 LR37536 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | -3.09
35212494 | FRRB - AUBERRY 1101 LR37536 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 28.22
35212494 | FRRB - AUBERRY 1101 LR37536 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 14.07
35212495 | FRRB - AUBERRY 1101 LR233716 | Contract | Contracts | Not assigned | 002/2021 | -11080.98
35212495 | FRRB - AUBERRY 1101 LR233716 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 440.33
35212495 | FRRB - AUBERRY 1101 LR233716 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | -11.27
35212495 | FRRB - AUBERRY 1101 LR233716 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 155.57
35212495 | FRRB - AUBERRY 1101 LR233716 | Labor Internal | Mapping | Not assigned | 002/2021 | -33.24
35212495 | FRRB - AUBERRY 1101 LR233716 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 81.99
35212495 | FRRB - AUBERRY 1101 LR233716 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 4244.43
35212495 | FRRB - AUBERRY 1101 LR233716 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 3882.32
35212495 | FRRB - AUBERRY 1101 LR233716 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3879.3
35212495 | FRRB - AUBERRY 1101 LR233716 | Other | AFUDC-Equity | Not assigned | 001/2021 | 10485.07
35212495 | FRRB - AUBERRY 1101 LR233716 | Other | AFUDC-Equity | Not assigned | 002/2021 | 10476.11
35212495 | FRRB - AUBERRY 1101 LR233716 | Other | AFUDC-Equity | Not assigned | 003/2021 | 10467.96
35212495 | FRRB - AUBERRY 1101 LR233716 | Other | Benefits OH | Not assigned | 002/2021 | 137.53
35212495 | FRRB - AUBERRY 1101 LR233716 | Other | Building Service Overhead | Not assigned | 002/2021 | 23.59
35212495 | FRRB - AUBERRY 1101 LR233716 | Other | Capitalized A&G | Not assigned | 002/2021 | 149.89
35212495 | FRRB - AUBERRY 1101 LR233716 | Other | Cost Adjustments | Not assigned | 002/2021 | 5784.35
35212495 | FRRB - AUBERRY 1101 LR233716 | Other | Cost Adjustments | Not assigned | 003/2021 | 380.12
35212495 | FRRB - AUBERRY 1101 LR233716 | Other | Fleet OH - Elec | Not assigned | 002/2021 | -7.53
35212495 | FRRB - AUBERRY 1101 LR233716 | Other | IT Device OH | Not assigned | 002/2021 | 13.4
35212495 | FRRB - AUBERRY 1101 LR233716 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | -10.2
35212495 | FRRB - AUBERRY 1101 LR233716 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 93.17
35212495 | FRRB - AUBERRY 1101 LR233716 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 46.46
35212496 | FRRB - HB TRINITY COUNTY | Contract | Contracts | Not assigned | 003/2021 | 30352.32
35212496 | FRRB - HB TRINITY COUNTY | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 003/2021 | 817.1
35212496 | FRRB - HB TRINITY COUNTY | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 30.87
35212496 | FRRB - HB TRINITY COUNTY | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 288.68
35212496 | FRRB - HB TRINITY COUNTY | Labor Internal | Mapping | Not assigned | 003/2021 | 91.06
35212496 | FRRB - HB TRINITY COUNTY | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 182.9
35212496 | FRRB - HB TRINITY COUNTY | Materials | Material Burden | Not assigned | 003/2021 | 1.82
35212496 | FRRB - HB TRINITY COUNTY | Materials | Purchasing Card | Not assigned | 003/2021 | 182.48
35212496 | FRRB - HB TRINITY COUNTY | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 4313.99
35212496 | FRRB - HB TRINITY COUNTY | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 3949.32
35212496 | FRRB - HB TRINITY COUNTY | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3959.53
35212496 | FRRB - HB TRINITY COUNTY | Other | AFUDC-Equity | Not assigned | 001/2021 | 10656.89
35212496 | FRRB - HB TRINITY COUNTY | Other | AFUDC-Equity | Not assigned | 002/2021 | 10656.89
35212496 | FRRB - HB TRINITY COUNTY | Other | AFUDC-Equity | Not assigned | 003/2021 | 10684.44
35212496 | FRRB - HB TRINITY COUNTY | Other | Benefits OH | Not assigned | 003/2021 | 301.02
35212496 | FRRB - HB TRINITY COUNTY | Other | Building Service Overhead | Not assigned | 003/2021 | 54.41
35212496 | FRRB - HB TRINITY COUNTY | Other | Capitalized A&G | Not assigned | 003/2021 | 334.39
35212496 | FRRB - HB TRINITY COUNTY | Other | Cost Adjustments | Not assigned | 003/2021 | -20046.44
35212496 | FRRB - HB TRINITY COUNTY | Other | Fleet OH - Elec | Not assigned | 003/2021 | 20.63
35212496 | FRRB - HB TRINITY COUNTY | Other | IT Device OH | Not assigned | 003/2021 | 30.88
35212496 | FRRB - HB TRINITY COUNTY | Other | Minor Material OH | Not assigned | 003/2021 | 13.1
35212496 | FRRB - HB TRINITY COUNTY | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 27.94
35212496 | FRRB - HB TRINITY COUNTY | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 172.9
35212496 | FRRB - HB TRINITY COUNTY | Other | Payroll Taxes OH | Not assigned | 003/2021 | 107.11
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 119.74
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -119.74
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 254.22
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -254.22
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 1578.52
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 3502.8
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 551.6
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 285
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Administration | Not assigned | 003/2021 | 104.46
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Administrative Services - OT | Not assigned | 001/2021 | 97.81
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 308.04
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Design Services | Not assigned | 001/2021 | 236.84
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 10406.28
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 5195.76
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Electric Estimating Doubletime | Not assigned | 002/2021 | 118.4
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 3098.44
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 2443.84
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 74.45
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 628.7
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1335.98
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 139.28
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 34.82
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 107.43
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 4834.93
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 3043.28
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 118.11
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 12.3
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 443.36
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 97.2
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 842.4
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Mapping | Not assigned | 001/2021 | 5.6
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Mapping | Not assigned | 002/2021 | 10.51
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Mapping | Not assigned | 003/2021 | 1.65
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 131.15
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 2879.45
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 2060.75
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 8.45
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 48.56
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 110.64
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | AFUDC-Equity | Not assigned | 001/2021 | 21.59
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | AFUDC-Equity | Not assigned | 002/2021 | 131.03
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | AFUDC-Equity | Not assigned | 003/2021 | 298.55
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Benefits OH | Not assigned | 001/2021 | 242.08
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Benefits OH | Not assigned | 002/2021 | 5750.4
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Benefits OH | Not assigned | 003/2021 | 3838.18
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Building Service Overhead | Not assigned | 001/2021 | 41.54
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Building Service Overhead | Not assigned | 002/2021 | 986.92
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Building Service Overhead | Not assigned | 003/2021 | 693.75
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Capitalized A&G | Not assigned | 001/2021 | 239.77
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Capitalized A&G | Not assigned | 002/2021 | 5264.21
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Capitalized A&G | Not assigned | 003/2021 | 3767.47
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 71.76
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 3230.42
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 2033.34
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | IT Device OH | Not assigned | 001/2021 | 23.59
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | IT Device OH | Not assigned | 002/2021 | 560.14
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | IT Device OH | Not assigned | 003/2021 | 393.74
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Lodging | EDWARD T SMITH IV | 004/2021 | -287.57
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Meals Expense | EDWARD T SMITH IV | 004/2021 | 66.43
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 97.21
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 4375.67
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 2754.21
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 70.73
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 7.37
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 265.53
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 81.81
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 1942.79
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 1365.63
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | Other | Reimbursed Mileage Expense | EDWARD T SMITH IV | 004/2021 | 403.2
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 5298.97
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | 871.56
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 8967.12
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -8967.12
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 5499.18
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 2276.71
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 105.06
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 95
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 23.75
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Administration | Not assigned | 003/2021 | 243.74
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Administration | Not assigned | 004/2021 | 278.56
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Construction | Not assigned | 002/2021 | 670.05
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 177.63
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 94.65
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.46
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 139.28
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 65.91
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 263.62
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.35
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 95
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 171.7
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 86.11
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 129.6
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 486
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Mapping | Not assigned | 001/2021 | 16.79
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Mapping | Not assigned | 002/2021 | 12.93
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.32
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 93.3
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 254.49
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 64.15
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 13.55
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 27.81
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 31.01
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 36.32
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 75.05
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 83.67
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Benefits OH | Not assigned | 001/2021 | 170.38
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Benefits OH | Not assigned | 002/2021 | 479.42
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Benefits OH | Not assigned | 003/2021 | 107.9
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Building Service Overhead | Not assigned | 001/2021 | 29.24
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Building Service Overhead | Not assigned | 002/2021 | 82.28
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Building Service Overhead | Not assigned | 003/2021 | 19.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Capitalized A&G | Not assigned | 001/2021 | 170.59
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Capitalized A&G | Not assigned | 002/2021 | 465.27
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Capitalized A&G | Not assigned | 003/2021 | 117.29
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 44.04
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 176.14
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.94
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | IT Device OH | Not assigned | 001/2021 | 16.6
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | IT Device OH | Not assigned | 002/2021 | 46.71
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | IT Device OH | Not assigned | 003/2021 | 11.08
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 59.65
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 238.58
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 22.94
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 56.89
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 102.84
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 51.58
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 57.57
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 161.98
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 38.38
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 2275.06
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 5694.47
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -5694.47
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 861
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 4882.13
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 641.25
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 23.75
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 858.55
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 177.63
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 43.64
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 76.56
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 208.92
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 318.52
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 105.24
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 85.26
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 32.4
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 4.5
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 14.72
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 237.85
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 62.51
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 44.98
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 12.84
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 22.86
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 25.33
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 33.66
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 61.69
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 68.34
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 460.76
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 124.91
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 85.33
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 79.09
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 21.44
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 15.42
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 434.82
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 114.3
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 82.24
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 212.81
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 70.31
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 44.9
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 12.17
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 8.76
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 288.27
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 95.25
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 51.07
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 155.67
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 42.2
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 30.36
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | 239.48
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 002/2021 | 19557.45
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | 5012.55
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 004/2021 | -24570
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 4992.9
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -4992.9
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 5090.77
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 3289.57
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 23.75
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Account Services | Not assigned | 002/2021 | 229.71
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Account Services | Not assigned | 003/2021 | 82.05
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Administrative Services - OT | Not assigned | 001/2021 | 44.01
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 44.01
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 87.28
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 130.92
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 76.56
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 69.64
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 59.47
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 21.24
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 60.72
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 148.7
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 97.38
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 91.58
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 187.25
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 162
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 259.2
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 486
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Mapping | Not assigned | 001/2021 | 15.27
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Mapping | Not assigned | 002/2021 | 9.94
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 91.59
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 186.81
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 168.24
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Labor Internal | Project Management Services | Not assigned | 002/2021 | 297.8
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 16.43
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 40.87
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 62.91
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 42.64
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 110.28
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 169.76
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Benefits OH | Not assigned | 001/2021 | 166.54
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Benefits OH | Not assigned | 002/2021 | 330.43
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Benefits OH | Not assigned | 003/2021 | 279.88
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Building Service Overhead | Not assigned | 001/2021 | 28.58
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Building Service Overhead | Not assigned | 002/2021 | 56.73
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Building Service Overhead | Not assigned | 003/2021 | 50.58
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Capitalized A&G | Not assigned | 001/2021 | 167.44
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Capitalized A&G | Not assigned | 002/2021 | 341.53
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Capitalized A&G | Not assigned | 003/2021 | 307.6
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 40.57
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 99.35
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | IT Device OH | Not assigned | 001/2021 | 16.21
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | IT Device OH | Not assigned | 002/2021 | 32.19
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | IT Device OH | Not assigned | 003/2021 | 28.72
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 54.95
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 134.59
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 58.33
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 54.85
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 112.15
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 56.25
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 111.65
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 99.58
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 15018.96
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 23039.1
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -23039.1
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 2316.07
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 3953.96
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 783.75
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 47.5
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Account Services | Not assigned | 003/2021 | 49.23
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 473.68
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 59.21
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 004/2021 | 196.65
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Electric Estimating Doubletime | Not assigned | 001/2021 | 148
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 894.62
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 218.2
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 76.56
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 226.33
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 12.75
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 543.14
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 123.35
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 91.41
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 22.89
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 32.4
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 64.8
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 9.3
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 12
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 374.78
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 73.28
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 67.94
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 58.01
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 76.84
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 75.32
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 145.96
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 207.35
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 203.25
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 733.3
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 146.4
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 119.67
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 125.86
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 25.12
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 21.63
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 685.18
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 133.97
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 124.23
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 362.88
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 82.41
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 71.43
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 14.26
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 12.28
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 491.54
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 111.63
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 54.75
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 13.71
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 247.77
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 49.45
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 42.57
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 5410.25
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | 24570
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 004/2021 | -24570
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 7187.82
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -7187.82
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 5370.02
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 2173.75
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 47.5
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 23.75
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 194.4
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 97.81
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 414.47
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 591.23
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 002/2021 | 1557.6
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 69.64
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 146.02
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 730.68
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 70.39
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 68.68
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 34.56
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 129.6
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 16.25
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 6.59
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 126.87
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 473.25
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 19.7
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 15.96
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 33.3
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 58.84
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 42.1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 89.85
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 158.76
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 241.6
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 933.87
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 31.83
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 41.46
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 160.28
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.76
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 231.95
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 865.21
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 36.01
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 97.56
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 488.2
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 23.52
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 90.97
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 3.27
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Land Acquisition Services | BENDER ROSENTHAL INC | 001/2021 | 403.75
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 132.14
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 661.28
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 42.16
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 41.14
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 20.7
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 81.62
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 315.49
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 11.32
35217273 | SH - UPPER LAKE 1101 CB | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 119.74
35217273 | SH - UPPER LAKE 1101 CB | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -119.74
35217273 | SH - UPPER LAKE 1101 CB | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 1068.16
35217273 | SH - UPPER LAKE 1101 CB | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -1068.16
35217273 | SH - UPPER LAKE 1101 CB | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 3602.96
35217273 | SH - UPPER LAKE 1101 CB | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 3281.68
35217273 | SH - UPPER LAKE 1101 CB | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 47.5
35217273 | SH - UPPER LAKE 1101 CB | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 236.84
35217273 | SH - UPPER LAKE 1101 CB | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 87.28
35217273 | SH - UPPER LAKE 1101 CB | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 151.01
35217273 | SH - UPPER LAKE 1101 CB | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 297.8
35217273 | SH - UPPER LAKE 1101 CB | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35217273 | SH - UPPER LAKE 1101 CB | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 104.46
35217273 | SH - UPPER LAKE 1101 CB | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 185.39
35217273 | SH - UPPER LAKE 1101 CB | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 336.07
35217273 | SH - UPPER LAKE 1101 CB | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35217273 | SH - UPPER LAKE 1101 CB | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 82.69
35217273 | SH - UPPER LAKE 1101 CB | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 129.6
35217273 | SH - UPPER LAKE 1101 CB | Labor Internal | Mapping | Not assigned | 001/2021 | 10.81
35217273 | SH - UPPER LAKE 1101 CB | Labor Internal | Mapping | Not assigned | 002/2021 | 9.99
35217273 | SH - UPPER LAKE 1101 CB | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 157.28
35217273 | SH - UPPER LAKE 1101 CB | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 199.65
35217273 | SH - UPPER LAKE 1101 CB | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 44.98
35217273 | SH - UPPER LAKE 1101 CB | Labor Internal | Project Management Services | Not assigned | 001/2021 | 297.8
35217273 | SH - UPPER LAKE 1101 CB | Labor Internal | Project Management Services | Not assigned | 002/2021 | 446.7
35217273 | SH - UPPER LAKE 1101 CB | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 9.52
35217273 | SH - UPPER LAKE 1101 CB | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 18.97
35217273 | SH - UPPER LAKE 1101 CB | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 23.7
35217273 | SH - UPPER LAKE 1101 CB | Other | AFUDC-Equity | Not assigned | 001/2021 | 24.76
35217273 | SH - UPPER LAKE 1101 CB | Other | AFUDC-Equity | Not assigned | 002/2021 | 51.18
35217273 | SH - UPPER LAKE 1101 CB | Other | AFUDC-Equity | Not assigned | 003/2021 | 63.94
35217273 | SH - UPPER LAKE 1101 CB | Other | Benefits OH | Not assigned | 001/2021 | 300.28
35217273 | SH - UPPER LAKE 1101 CB | Other | Benefits OH | Not assigned | 002/2021 | 398.88
35217273 | SH - UPPER LAKE 1101 CB | Other | Benefits OH | Not assigned | 003/2021 | 85.33
35217273 | SH - UPPER LAKE 1101 CB | Other | Building Service Overhead | Not assigned | 001/2021 | 51.53
35217273 | SH - UPPER LAKE 1101 CB | Other | Building Service Overhead | Not assigned | 002/2021 | 68.47
35217273 | SH - UPPER LAKE 1101 CB | Other | Building Service Overhead | Not assigned | 003/2021 | 15.42
35217273 | SH - UPPER LAKE 1101 CB | Other | Capitalized A&G | Not assigned | 001/2021 | 287.55
35217273 | SH - UPPER LAKE 1101 CB | Other | Capitalized A&G | Not assigned | 002/2021 | 365
35217273 | SH - UPPER LAKE 1101 CB | Other | Capitalized A&G | Not assigned | 003/2021 | 82.24
35217273 | SH - UPPER LAKE 1101 CB | Other | Fleet OH - Elec | Not assigned | 001/2021 | 123.87
35217273 | SH - UPPER LAKE 1101 CB | Other | Fleet OH - Elec | Not assigned | 002/2021 | 224.53
35217273 | SH - UPPER LAKE 1101 CB | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35217273 | SH - UPPER LAKE 1101 CB | Other | IT Device OH | Not assigned | 001/2021 | 29.24
35217273 | SH - UPPER LAKE 1101 CB | Other | IT Device OH | Not assigned | 002/2021 | 38.85
35217273 | SH - UPPER LAKE 1101 CB | Other | IT Device OH | Not assigned | 003/2021 | 8.76
35217273 | SH - UPPER LAKE 1101 CB | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 167.8
35217273 | SH - UPPER LAKE 1101 CB | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 304.13
35217273 | SH - UPPER LAKE 1101 CB | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35217273 | SH - UPPER LAKE 1101 CB | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 49.53
35217273 | SH - UPPER LAKE 1101 CB | Other | Payroll Taxes OH | Not assigned | 001/2021 | 101.42
35217273 | SH - UPPER LAKE 1101 CB | Other | Payroll Taxes OH | Not assigned | 002/2021 | 134.77
35217273 | SH - UPPER LAKE 1101 CB | Other | Payroll Taxes OH | Not assigned | 003/2021 | 30.36
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Contract | Contracts | BENDER ROSENTHAL INC | 003/2021 | 240
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 4214.88
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 220.64
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 71.25
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 23.75
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Account Services | Not assigned | 002/2021 | 229.73
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 194.4
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Administrative Services - Double Time | Not assigned | 002/2021 | 182.09
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Administrative Services - Double Time | Not assigned | 003/2021 | 60.7
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 572.09
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 286.04
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Administrative Services - OT | Not assigned | 004/2021 | 44.01
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 409.48
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 632.83
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 483.93
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 34.82
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 591.94
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 59.48
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 143.09
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 214.82
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 164.31
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 862.54
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 434.66
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 421.2
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 97.2
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 1231.2
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 004/2021 | 97.2
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Mapping | Not assigned | 001/2021 | 12.64
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Mapping | Not assigned | 002/2021 | 0.87
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Mapping | Not assigned | 003/2021 | 0.79
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 85.02
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 665.59
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 352.01
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 9.8
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 21.03
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 32.21
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | AFUDC-Equity | Not assigned | 001/2021 | 25.19
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | AFUDC-Equity | Not assigned | 002/2021 | 56.75
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | AFUDC-Equity | Not assigned | 003/2021 | 86.91
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Benefits OH | Not assigned | 001/2021 | 169.83
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Benefits OH | Not assigned | 002/2021 | 1156.71
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Benefits OH | Not assigned | 003/2021 | 594.37
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Building Service Overhead | Not assigned | 001/2021 | 29.15
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Building Service Overhead | Not assigned | 002/2021 | 198.53
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Building Service Overhead | Not assigned | 003/2021 | 107.42
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Capitalized A&G | Not assigned | 001/2021 | 155.42
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Capitalized A&G | Not assigned | 002/2021 | 1216.84
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Capitalized A&G | Not assigned | 003/2021 | 643.56
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Fleet OH - Elec | Not assigned | 001/2021 | 95.61
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Fleet OH - Elec | Not assigned | 002/2021 | 143.54
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Fleet OH - Elec | Not assigned | 003/2021 | 109.79
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | IT Device OH | Not assigned | 001/2021 | 16.54
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | IT Device OH | Not assigned | 002/2021 | 112.65
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | IT Device OH | Not assigned | 003/2021 | 60.96
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 129.51
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 194.41
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 148.71
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 516.6
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 260.33
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Payroll Taxes OH | Not assigned | 001/2021 | 57.4
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Payroll Taxes OH | Not assigned | 002/2021 | 390.82
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Other | Payroll Taxes OH | Not assigned | 003/2021 | 211.45
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Contract | Contracts | BENDER ROSENTHAL INC | 003/2021 | 340
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 3449.21
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 661.91
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 23.75
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 23.75
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Account Services | Not assigned | 001/2021 | 65.64
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Account Services | Not assigned | 002/2021 | 623.52
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 194.4
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Administrative Services - Double Time | Not assigned | 002/2021 | 121.4
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Administrative Services - Double Time | Not assigned | 003/2021 | 60.7
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 616.1
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 334.95
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Administrative Services - OT | Not assigned | 004/2021 | 44.01
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1087.97
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 483.93
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 260.58
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 278.56
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 696.4
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 69.64
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 16.99
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 161.43
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 372.34
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 164.74
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 88.71
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 862.63
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 488.85
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 356.4
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 1069.2
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 97.2
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 004/2021 | 97.2
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Mapping | Not assigned | 001/2021 | 10.35
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Mapping | Not assigned | 002/2021 | 2.06
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Mapping | Not assigned | 003/2021 | 1.09
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 234.42
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 715.2
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 337.97
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 8.09
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 21.38
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 33.02
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | AFUDC-Equity | Not assigned | 001/2021 | 21.24
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | AFUDC-Equity | Not assigned | 002/2021 | 57.7
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | AFUDC-Equity | Not assigned | 003/2021 | 89.11
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Benefits OH | Not assigned | 001/2021 | 460.49
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Benefits OH | Not assigned | 002/2021 | 1209
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Benefits OH | Not assigned | 003/2021 | 559.06
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Building Service Overhead | Not assigned | 001/2021 | 79.05
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Building Service Overhead | Not assigned | 002/2021 | 207.49
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Building Service Overhead | Not assigned | 003/2021 | 101.05
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Capitalized A&G | Not assigned | 001/2021 | 428.57
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Capitalized A&G | Not assigned | 002/2021 | 1307.54
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Capitalized A&G | Not assigned | 003/2021 | 617.89
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Fleet OH - Elec | Not assigned | 001/2021 | 248.76
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Fleet OH - Elec | Not assigned | 002/2021 | 110.08
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Fleet OH - Elec | Not assigned | 003/2021 | 59.27
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | IT Device OH | Not assigned | 001/2021 | 44.86
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | IT Device OH | Not assigned | 002/2021 | 117.77
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | IT Device OH | Not assigned | 003/2021 | 57.35
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 336.96
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 149.1
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 80.28
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 516.66
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 292.78
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Payroll Taxes OH | Not assigned | 001/2021 | 155.57
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Payroll Taxes OH | Not assigned | 002/2021 | 408.42
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Other | Payroll Taxes OH | Not assigned | 003/2021 | 198.92
35219092 | CWSP - POSO MOUNTAIN 2104CB | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 492.24
35219092 | CWSP - POSO MOUNTAIN 2104CB | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 984.48
35219092 | CWSP - POSO MOUNTAIN 2104CB | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 166.87
35219092 | CWSP - POSO MOUNTAIN 2104CB | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 333.74
35219092 | CWSP - POSO MOUNTAIN 2104CB | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 99.13
35219092 | CWSP - POSO MOUNTAIN 2104CB | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 198.27
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.59
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 6.06
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 8.46
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | AFUDC-Equity | Not assigned | 001/2021 | 6.67
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | AFUDC-Equity | Not assigned | 002/2021 | 16.36
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | AFUDC-Equity | Not assigned | 003/2021 | 22.82
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | Benefits OH | Not assigned | 001/2021 | 198.05
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | Benefits OH | Not assigned | 002/2021 | 396.12
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | Building Service Overhead | Not assigned | 001/2021 | 33.99
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | Building Service Overhead | Not assigned | 002/2021 | 67.99
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | Capitalized A&G | Not assigned | 001/2021 | 181.24
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | Capitalized A&G | Not assigned | 002/2021 | 362.49
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | Fleet OH - Elec | Not assigned | 001/2021 | 111.49
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | Fleet OH - Elec | Not assigned | 002/2021 | 222.98
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | IT Device OH | Not assigned | 001/2021 | 19.31
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | IT Device OH | Not assigned | 002/2021 | 38.58
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 151.02
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 302.04
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | Payroll Taxes OH | Not assigned | 001/2021 | 66.9
35219092 | CWSP - POSO MOUNTAIN 2104CB | Other | Payroll Taxes OH | Not assigned | 002/2021 | 133.82
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 119.74
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | 9460.56
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 2320.81
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Contract | Traffic Control Contracts | CITY RISE INC | 004/2021 | 250
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 332.5
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 23.75
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor External | Contractor Consultant | Not assigned | 003/2021 | 90.36
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 32.4
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Acquisition - Misc | Not assigned | 004/2021 | 194.4
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Administrative Services - OT | Not assigned | 001/2021 | 229.83
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Construction | Not assigned | 002/2021 | 37.23
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 110.87
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Design Overtime Services | Not assigned | 001/2021 | 523.68
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 153.12
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 297.8
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 69.64
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 229.78
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 78.27
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 100.95
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 151.59
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 22.89
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 80.12
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 64.8
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 64.8
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 001/2021 | 129.6
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 129.6
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 004/2021 | 97.2
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Management Services | Not assigned | 001/2021 | 215.18
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Management Services | Not assigned | 003/2021 | 322.77
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 1
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 8.36
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 222.93
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 59.56
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 105.66
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3.22
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 9.08
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 21.04
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 8.69
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 24.5
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 56.79
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 483.76
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 115.13
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 279.58
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 83.01
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 19.75
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 53.4
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 486.78
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 108.88
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 313.93
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 202.26
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 52.3
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 140.56
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 47.12
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 11.21
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 30.3
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 273.97
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 70.85
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 190.4
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 90.8
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 13.71
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 47.99
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 163.46
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 38.88
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 99.47
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 219.22
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -219.22
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 3785.15
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 23.75
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 641.25
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 23.75
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 129.6
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Construction | Not assigned | 002/2021 | 37.23
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 110.87
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 297.8
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 0.02
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 80.39
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 100.97
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 103.88
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 68.68
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 129.6
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 64.8
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 129.6
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 004/2021 | 97.2
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Manage L&EM | Not assigned | 001/2021 | 34.82
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Management Services | Not assigned | 001/2021 | 450.66
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Management Services | Not assigned | 003/2021 | 430.36
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.07
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 14.61
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.07
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 59.22
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 47.76
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 99.14
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1.36
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 6.95
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 12.96
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3.66
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 18.74
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 34.96
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 210.48
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 95.43
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 298.64
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 36.13
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 16.36
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 53.99
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 274.22
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 87.32
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 339.72
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 48.76
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 53.72
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 164.95
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 20.51
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 9.3
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 30.63
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 66.04
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 72.76
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 223.42
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 62.22
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 41.13
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 71.12
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 32.23
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 106.24
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 1950.01
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 546.34
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 712.5
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 522.5
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 194.4
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 259.2
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 176.02
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Design Drafting Services | Not assigned | 001/2021 | 192.43
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Design Drafting Services | Not assigned | 002/2021 | 518.09
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Design Drafting Services | Not assigned | 003/2021 | 532.9
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 002/2021 | 283.66
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 003/2021 | 632.78
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Design Overtime Services | Not assigned | 003/2021 | 414.58
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Design Services | Not assigned | 003/2021 | 1243.43
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 118.42
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 2072.38
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 8023.1
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 004/2021 | 1278.25
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Electric Estimating Doubletime | Not assigned | 002/2021 | 710.4
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Electric Estimating Doubletime | Not assigned | 003/2021 | 1657.6
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 785.52
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 2574.76
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 004/2021 | 45.6
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1547.04
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1158.16
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 446.7
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 104.46
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 629.83
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1876.78
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 5264.35
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 48.36
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 153.76
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 480.77
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 32.4
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 64.8
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 1101.6
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 004/2021 | 129.6
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 7.99
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 3.21
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 401.75
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1202.64
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 3401.63
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 4.81
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 26.1
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 83.63
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 12.97
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 70.42
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 225.68
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 794.43
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 2376.65
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 6375.85
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 136.34
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 407.89
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 1152.39
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 734.46
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 2198.67
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 6218.84
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 420.81
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1253.95
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 3517.34
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 77.39
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 231.5
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 654.06
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Meals Expense | AUSTIN MARTIN | 003/2021 | 9.76
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 570
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1698.5
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 4764.31
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 28.96
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 92.09
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 287.95
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 268.42
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 802.96
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 2268.51
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLAIR CHURCH & FLYNN CONSULTING | 003/2021 | 45521
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLAIR CHURCH & FLYNN CONSULTING | 004/2021 | -45521
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 003/2021 | 13262.07
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 004/2021 | -13262.07
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 2057.14
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 712.32
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 237.5
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 71.25
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 118.75
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Account Services | Not assigned | 002/2021 | 82.05
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Account Services | Not assigned | 003/2021 | 65.64
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 32.4
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 220.03
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 59.21
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 207.24
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Electric Estimating Doubletime | Not assigned | 001/2021 | 207.2
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Electric Estimating Doubletime | Not assigned | 002/2021 | 118.4
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 130.92
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1607.76
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 562.6
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | -306.24
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 104.46
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 34.82
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 21.24
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 16.99
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 679.96
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 471.98
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | -32.73
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 48.35
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 181.61
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 137.36
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 32.4
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 226.8
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 388.8
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.71
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 6.38
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 2.49
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 431.53
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 400.46
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 72.08
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Project Management Overtime | Not assigned | 002/2021 | 332.61
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Labor Internal | Project Management Services | Not assigned | 002/2021 | 372.25
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 5.35
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 17.01
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 70.95
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 14.45
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 45.89
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 191.45
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 853.95
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 759.58
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 107.3
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 146.58
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 130.36
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 19.4
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 788.93
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 732.1
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 131.8
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 454.32
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 315.34
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | -21.86
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 83.16
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 73.98
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 11.01
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 615.38
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 427.14
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | -29.61
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 28.97
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 108.78
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 82.27
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 288.5
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 256.64
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 38.17
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 219.22
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -219.22
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 6209.59
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 190
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 1686.25
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 95
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 55.44
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 1894.72
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 392.76
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 349.12
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 376.82
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 2526.48
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 76.56
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 34.82
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 261.08
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1625.17
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 45.01
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 57.23
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 162
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.57
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 23.69
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.79
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 187.73
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 965.51
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 26.75
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.37
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 22.78
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 41.05
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6.38
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 61.47
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 110.78
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 365.38
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 1928.86
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 50.75
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 62.7
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 331.03
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 9.19
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 343.22
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 1765.15
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 48.89
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 174.44
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1085.85
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 30.08
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 35.59
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 187.9
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 5.21
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 236.28
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1470.8
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 40.74
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 34.28
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 123.47
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 651.68
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 18.06
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 198.95
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | 59.87
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 003/2021 | 45439.68
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 4461.69
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -4461.69
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 3368.91
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 23.75
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 71.25
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 194.4
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 97.2
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 129.6
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Administrative Services - OT | Not assigned | 001/2021 | 352.05
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1148.4
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 304.13
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 76.56
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 001/2021 | 322.26
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 104.46
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 498.57
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 106.6
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.95
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 298.65
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 34.34
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 160.26
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 194.4
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 324
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.07
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 10.32
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 466.45
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 82.9
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 106.77
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 881.42
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 159.85
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 176.87
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 151.27
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 27.43
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 31.97
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 852.77
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 151.57
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 195.2
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 333.12
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 71.22
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 17.34
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 85.86
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 15.57
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 18.15
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 451.22
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 96.48
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 23.49
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 178.87
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 20.57
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 95.98
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 297.77
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 53.98
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 62.92
35219264 | CWSP - POSO MOUNTAIN 2103CB | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 281.28
35219264 | CWSP - POSO MOUNTAIN 2103CB | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 668.04
35219264 | CWSP - POSO MOUNTAIN 2103CB | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 95.35
35219264 | CWSP - POSO MOUNTAIN 2103CB | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 226.47
35219264 | CWSP - POSO MOUNTAIN 2103CB | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 56.65
35219264 | CWSP - POSO MOUNTAIN 2103CB | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 134.54
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3.21
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 5.3
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 6.93
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | AFUDC-Equity | Not assigned | 001/2021 | 8.08
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | AFUDC-Equity | Not assigned | 002/2021 | 14.31
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | AFUDC-Equity | Not assigned | 003/2021 | 18.7
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | Benefits OH | Not assigned | 001/2021 | 113.17
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | Benefits OH | Not assigned | 002/2021 | 268.78
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | Building Service Overhead | Not assigned | 001/2021 | 19.42
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | Building Service Overhead | Not assigned | 002/2021 | 46.13
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | Capitalized A&G | Not assigned | 001/2021 | 103.57
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | Capitalized A&G | Not assigned | 002/2021 | 245.97
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | Fleet OH - Elec | Not assigned | 001/2021 | 63.71
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | Fleet OH - Elec | Not assigned | 002/2021 | 151.31
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | IT Device OH | Not assigned | 001/2021 | 11.02
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | IT Device OH | Not assigned | 002/2021 | 26.18
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 86.3
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 204.95
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | Payroll Taxes OH | Not assigned | 001/2021 | 38.24
35219264 | CWSP - POSO MOUNTAIN 2103CB | Other | Payroll Taxes OH | Not assigned | 002/2021 | 90.81
35219265 | CWSP - CRESTA 1101546650 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 2771.28
35219265 | CWSP - CRESTA 1101546650 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -2771.28
35219265 | CWSP - CRESTA 1101546650 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 3431.54
35219265 | CWSP - CRESTA 1101546650 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 23.75
35219265 | CWSP - CRESTA 1101546650 | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 64.8
35219265 | CWSP - CRESTA 1101546650 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 29.61
35219265 | CWSP - CRESTA 1101546650 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 10.04
35219265 | CWSP - CRESTA 1101546650 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 3.52
35219265 | CWSP - CRESTA 1101546650 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 125.92
35219265 | CWSP - CRESTA 1101546650 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 291.6
35219265 | CWSP - CRESTA 1101546650 | Labor Internal | Mapping | Not assigned | 002/2021 | 10.37
35219265 | CWSP - CRESTA 1101546650 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 77.74
35219265 | CWSP - CRESTA 1101546650 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 2.09
35219265 | CWSP - CRESTA 1101546650 | Other | Benefits OH | Not assigned | 001/2021 | 134.06
35219265 | CWSP - CRESTA 1101546650 | Other | Benefits OH | Not assigned | 002/2021 | 4.17
35219265 | CWSP - CRESTA 1101546650 | Other | Building Service Overhead | Not assigned | 001/2021 | 23
35219265 | CWSP - CRESTA 1101546650 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.72
35219265 | CWSP - CRESTA 1101546650 | Other | Capitalized A&G | Not assigned | 001/2021 | 142.13
35219265 | CWSP - CRESTA 1101546650 | Other | Capitalized A&G | Not assigned | 002/2021 | 3.82
35219265 | CWSP - CRESTA 1101546650 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 6.71
35219265 | CWSP - CRESTA 1101546650 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 2.35
35219265 | CWSP - CRESTA 1101546650 | Other | IT Device OH | Not assigned | 001/2021 | 13.07
35219265 | CWSP - CRESTA 1101546650 | Other | IT Device OH | Not assigned | 002/2021 | 0.41
35219265 | CWSP - CRESTA 1101546650 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 9.08
35219265 | CWSP - CRESTA 1101546650 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 3.18
35219265 | CWSP - CRESTA 1101546650 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 75.41
35219265 | CWSP - CRESTA 1101546650 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 45.3
35219265 | CWSP - CRESTA 1101546650 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 1.41
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 219.22
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -219.22
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 3417.73
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 887.8
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 451.25
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 95
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 64.8
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 421.2
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 32.4
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 484.06
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 748.11
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 332.61
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Design Drafting Services | Not assigned | 002/2021 | 3463.8
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Design Drafting Services | Not assigned | 003/2021 | 1953.94
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 002/2021 | 3229.36
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 003/2021 | 2138.36
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Drafting Doubletime | Not assigned | 002/2021 | 1450.4
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Drafting Doubletime | Not assigned | 003/2021 | 1924
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 207.24
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 4026.29
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 8467.15
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Electric Estimating Doubletime | Not assigned | 002/2021 | 947.2
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Electric Estimating Doubletime | Not assigned | 003/2021 | 2190.4
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 5455
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 4822.22
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1476.72
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 847.92
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 442.58
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 174.1
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 570.86
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 6587.31
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 7551.97
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 95.85
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 548.77
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 951.12
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 32.4
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 64.8
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 583.2
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 1911.6
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Mapping | Not assigned | 002/2021 | 11.61
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Mapping | Not assigned | 003/2021 | 5.94
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 393.8
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 4226.35
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 5028.81
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 9.97
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 67.96
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 181.8
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 25.7
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 183.38
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 490.58
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Benefits OH | Not assigned | 001/2021 | 770.53
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Benefits OH | Not assigned | 002/2021 | 8350.61
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Benefits OH | Not assigned | 003/2021 | 9387.29
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Building Service Overhead | Not assigned | 001/2021 | 132.24
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Building Service Overhead | Not assigned | 002/2021 | 1433.19
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Building Service Overhead | Not assigned | 003/2021 | 1696.68
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Capitalized A&G | Not assigned | 001/2021 | 719.93
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Capitalized A&G | Not assigned | 002/2021 | 7726.61
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Capitalized A&G | Not assigned | 003/2021 | 9193.69
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 381.42
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 4401.25
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 5045.79
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | IT Device OH | Not assigned | 001/2021 | 75.07
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | IT Device OH | Not assigned | 002/2021 | 813.44
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | IT Device OH | Not assigned | 003/2021 | 963
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 516.64
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 5961.6
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 6834.64
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 57.41
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 328.67
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 569.65
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 260.32
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 2821.28
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 3339.98
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 219.22
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -219.22
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 6918.36
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 665
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 95
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Labor Internal | Design Services | Not assigned | 002/2021 | 414.47
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1898.64
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1968.96
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Labor Internal | Engineering/Mapping | Not assigned | 004/2021 | 140.64
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 139.28
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 643.64
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 141.19
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 674.61
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 49.2
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Labor Internal | Mapping | Not assigned | 002/2021 | 2
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Labor Internal | Mapping | Not assigned | 003/2021 | 21.04
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 382.39
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 111.93
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 400.79
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 4.62
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 11.24
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 23.4
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 12.46
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 30.33
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 63.15
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | Benefits OH | Not assigned | 001/2021 | 763.91
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | Benefits OH | Not assigned | 002/2021 | 215.29
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | Benefits OH | Not assigned | 003/2021 | 760.29
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | Building Service Overhead | Not assigned | 001/2021 | 131.11
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | Building Service Overhead | Not assigned | 002/2021 | 36.96
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | Building Service Overhead | Not assigned | 003/2021 | 137.42
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | Capitalized A&G | Not assigned | 001/2021 | 699.08
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | Capitalized A&G | Not assigned | 002/2021 | 204.63
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | Capitalized A&G | Not assigned | 003/2021 | 732.72
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 430.04
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 94.33
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 450.74
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | IT Device OH | Not assigned | 001/2021 | 74.41
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | IT Device OH | Not assigned | 002/2021 | 20.97
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | IT Device OH | Not assigned | 003/2021 | 78
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 582.5
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 127.77
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 610.54
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 29.48
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 258.09
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 72.75
35219267 | CWSP - MARIPOSA 2102440236 PH1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 270.51
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 2066.79
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 3552.96
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 1258.66
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 23.75
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 1567.5
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 546.25
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 003/2021 | 30
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 129.6
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 826.2
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 421.2
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Administration | Not assigned | 003/2021 | 557.12
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 2200.29
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 1540.23
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 221.74
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Design Services | Not assigned | 001/2021 | 236.84
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Design Services | Not assigned | 002/2021 | 1361.83
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Design Services | Not assigned | 003/2021 | 651.31
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 11249.91
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 2575.64
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Electric Estimating Doubletime | Not assigned | 002/2021 | 4144
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Electric Estimating Doubletime | Not assigned | 003/2021 | 503.2
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 8487.98
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 2618.4
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 847.92
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 744.51
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 243.74
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 34.82
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 80.31
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 8926.13
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 2408.51
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 166.24
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 2340.72
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 2080.28
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 97.2
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 3564
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 3369.6
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.07
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Mapping | Not assigned | 002/2021 | 17.37
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Mapping | Not assigned | 003/2021 | 11.7
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 142.48
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 6637.34
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 2616.77
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1.59
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 85.26
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 190.99
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 4.29
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 230.07
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 515.38
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Benefits OH | Not assigned | 001/2021 | 256.56
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Benefits OH | Not assigned | 002/2021 | 12864.77
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Benefits OH | Not assigned | 003/2021 | 4630.56
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Building Service Overhead | Not assigned | 001/2021 | 44.05
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Building Service Overhead | Not assigned | 002/2021 | 2207.94
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Building Service Overhead | Not assigned | 003/2021 | 836.94
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Capitalized A&G | Not assigned | 001/2021 | 260.48
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Capitalized A&G | Not assigned | 002/2021 | 12134.42
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Capitalized A&G | Not assigned | 003/2021 | 4784
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 53.66
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 5963.92
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1609.22
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | IT Device OH | Not assigned | 001/2021 | 25.01
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | IT Device OH | Not assigned | 002/2021 | 1253.16
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | IT Device OH | Not assigned | 003/2021 | 475.03
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 72.68
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 8078.27
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 2179.74
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 99.57
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 1401.92
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 1245.94
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 86.71
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 4346.37
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 1647.54
35219269 | CWSP - VACA DIXON 110540092 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 119.74
35219269 | CWSP - VACA DIXON 110540092 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | 3674.36
35219269 | CWSP - VACA DIXON 110540092 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 5589.37
35219269 | CWSP - VACA DIXON 110540092 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 2707.5
35219269 | CWSP - VACA DIXON 110540092 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 831.25
35219269 | CWSP - VACA DIXON 110540092 | Labor Internal | Administration | Not assigned | 002/2021 | 69.64
35219269 | CWSP - VACA DIXON 110540092 | Labor Internal | Design Drafting Services | Not assigned | 002/2021 | 177.63
35219269 | CWSP - VACA DIXON 110540092 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 995.28
35219269 | CWSP - VACA DIXON 110540092 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 306.24
35219269 | CWSP - VACA DIXON 110540092 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1148.4
35219269 | CWSP - VACA DIXON 110540092 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 003/2021 | 1074.2
35219269 | CWSP - VACA DIXON 110540092 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 69.64
35219269 | CWSP - VACA DIXON 110540092 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 174.1
35219269 | CWSP - VACA DIXON 110540092 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 337.4
35219269 | CWSP - VACA DIXON 110540092 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 166.79
35219269 | CWSP - VACA DIXON 110540092 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 759.99
35219269 | CWSP - VACA DIXON 110540092 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 49.2
35219269 | CWSP - VACA DIXON 110540092 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 61.51
35219269 | CWSP - VACA DIXON 110540092 | Labor Internal | Mapping | Not assigned | 002/2021 | 8.12
35219269 | CWSP - VACA DIXON 110540092 | Labor Internal | Mapping | Not assigned | 003/2021 | 19.26
35219269 | CWSP - VACA DIXON 110540092 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 200.45
35219269 | CWSP - VACA DIXON 110540092 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 127.15
35219269 | CWSP - VACA DIXON 110540092 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 486.57
35219269 | CWSP - VACA DIXON 110540092 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.42
35219269 | CWSP - VACA DIXON 110540092 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 8.56
35219269 | CWSP - VACA DIXON 110540092 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 26.01
35219269 | CWSP - VACA DIXON 110540092 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6.53
35219269 | CWSP - VACA DIXON 110540092 | Other | AFUDC-Equity | Not assigned | 002/2021 | 23.1
35219269 | CWSP - VACA DIXON 110540092 | Other | AFUDC-Equity | Not assigned | 003/2021 | 70.18
35219269 | CWSP - VACA DIXON 110540092 | Other | Benefits OH | Not assigned | 001/2021 | 400.46
35219269 | CWSP - VACA DIXON 110540092 | Other | Benefits OH | Not assigned | 002/2021 | 245.67
35219269 | CWSP - VACA DIXON 110540092 | Other | Benefits OH | Not assigned | 003/2021 | 913.19
35219269 | CWSP - VACA DIXON 110540092 | Other | Building Service Overhead | Not assigned | 001/2021 | 68.73
35219269 | CWSP - VACA DIXON 110540092 | Other | Building Service Overhead | Not assigned | 002/2021 | 42.18
35219269 | CWSP - VACA DIXON 110540092 | Other | Building Service Overhead | Not assigned | 003/2021 | 165.05
35219269 | CWSP - VACA DIXON 110540092 | Other | Capitalized A&G | Not assigned | 001/2021 | 366.46
35219269 | CWSP - VACA DIXON 110540092 | Other | Capitalized A&G | Not assigned | 002/2021 | 232.43
35219269 | CWSP - VACA DIXON 110540092 | Other | Capitalized A&G | Not assigned | 003/2021 | 889.55
35219269 | CWSP - VACA DIXON 110540092 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 225.43
35219269 | CWSP - VACA DIXON 110540092 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 111.43
35219269 | CWSP - VACA DIXON 110540092 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 507.78
35219269 | CWSP - VACA DIXON 110540092 | Other | IT Device OH | Not assigned | 001/2021 | 39.01
35219269 | CWSP - VACA DIXON 110540092 | Other | IT Device OH | Not assigned | 002/2021 | 23.94
35219269 | CWSP - VACA DIXON 110540092 | Other | IT Device OH | Not assigned | 003/2021 | 93.68
35219269 | CWSP - VACA DIXON 110540092 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 305.35
35219269 | CWSP - VACA DIXON 110540092 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 150.94
35219269 | CWSP - VACA DIXON 110540092 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 687.8
35219269 | CWSP - VACA DIXON 110540092 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 29.48
35219269 | CWSP - VACA DIXON 110540092 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 36.84
35219269 | CWSP - VACA DIXON 110540092 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 135.3
35219269 | CWSP - VACA DIXON 110540092 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 83.03
35219269 | CWSP - VACA DIXON 110540092 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 324.91
35219272 | CWSP - MIDDLETOWN 1101481876 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLAIR CHURCH & FLYNN CONSULTING | 003/2021 | 22402
35219272 | CWSP - MIDDLETOWN 1101481876 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLAIR CHURCH & FLYNN CONSULTING | 004/2021 | -22402
35219272 | CWSP - MIDDLETOWN 1101481876 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 1820.75
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 712.5
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 47.5
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 87.28
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1301.52
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | -82.89
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 104.46
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 471.54
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 165.68
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | -28.1
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 48.35
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 32.4
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor Internal | Mapping | Not assigned | 001/2021 | 2.14
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor Internal | Mapping | Not assigned | 002/2021 | 5.6
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 307.7
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 98.43
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | -10.09
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor Internal | Project Management Overtime | Not assigned | 002/2021 | 110.87
35219272 | CWSP - MIDDLETOWN 1101481876 | Labor Internal | Project Management Services | Not assigned | 002/2021 | 297.8
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 4.23
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 11.13
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 31.29
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | AFUDC-Equity | Not assigned | 001/2021 | 11.42
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | AFUDC-Equity | Not assigned | 002/2021 | 30.02
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | AFUDC-Equity | Not assigned | 003/2021 | 84.42
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | Benefits OH | Not assigned | 001/2021 | 606.55
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | Benefits OH | Not assigned | 002/2021 | 196.63
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | Benefits OH | Not assigned | 003/2021 | -22.83
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | Building Service Overhead | Not assigned | 001/2021 | 104.12
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | Building Service Overhead | Not assigned | 002/2021 | 33.75
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | Building Service Overhead | Not assigned | 003/2021 | -4.14
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | Capitalized A&G | Not assigned | 001/2021 | 562.54
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | Capitalized A&G | Not assigned | 002/2021 | 179.94
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | Capitalized A&G | Not assigned | 003/2021 | -18.44
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 315.04
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 110.7
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | Fleet OH - Elec | Not assigned | 003/2021 | -18.77
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | IT Device OH | Not assigned | 001/2021 | 59.07
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | IT Device OH | Not assigned | 002/2021 | 19.15
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | IT Device OH | Not assigned | 003/2021 | -2.34
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 426.75
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 149.94
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | -25.43
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 28.97
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 204.92
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 66.45
35219272 | CWSP - MIDDLETOWN 1101481876 | Other | Payroll Taxes OH | Not assigned | 003/2021 | -8.13
35219273 | CWSP - VOLTA 110149742 | Contract | Contracts | Not assigned | 003/2021 | 2950.63
35219273 | CWSP - VOLTA 110149742 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 239.48
35219273 | CWSP - VOLTA 110149742 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | 239.48
35219273 | CWSP - VOLTA 110149742 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | CAL ENGINEERING SOLUTIONS INC | 003/2021 | 118074.32
35219273 | CWSP - VOLTA 110149742 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 3750.42
35219273 | CWSP - VOLTA 110149742 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -3750.42
35219273 | CWSP - VOLTA 110149742 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 3928.33
35219273 | CWSP - VOLTA 110149742 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 261.25
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Account Services | Not assigned | 002/2021 | 65.63
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 64.8
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 129.6
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Construction | Not assigned | 002/2021 | 652.4
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Construction | Not assigned | 003/2021 | 670.05
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 29.61
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 111.68
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 151.02
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 69.64
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 16.99
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 10.04
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 265.27
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 283.38
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 264.99
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 22.89
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 45.79
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 615.6
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 64.8
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Mapping | Not assigned | 002/2021 | 18.44
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Mapping | Not assigned | 003/2021 | 14.88
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 157.02
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 183.86
35219273 | CWSP - VOLTA 110149742 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 194.45
35219273 | CWSP - VOLTA 110149742 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 4.61
35219273 | CWSP - VOLTA 110149742 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 11.92
35219273 | CWSP - VOLTA 110149742 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 112.4
35219273 | CWSP - VOLTA 110149742 | Other | AFUDC-Equity | Not assigned | 001/2021 | 12.44
35219273 | CWSP - VOLTA 110149742 | Other | AFUDC-Equity | Not assigned | 002/2021 | 32.15
35219273 | CWSP - VOLTA 110149742 | Other | AFUDC-Equity | Not assigned | 003/2021 | 303.29
35219273 | CWSP - VOLTA 110149742 | Other | Benefits OH | Not assigned | 001/2021 | 268.96
35219273 | CWSP - VOLTA 110149742 | Other | Benefits OH | Not assigned | 002/2021 | 355.65
35219273 | CWSP - VOLTA 110149742 | Other | Benefits OH | Not assigned | 003/2021 | 361.56
35219273 | CWSP - VOLTA 110149742 | Other | Building Service Overhead | Not assigned | 001/2021 | 46.16
35219273 | CWSP - VOLTA 110149742 | Other | Building Service Overhead | Not assigned | 002/2021 | 61.06
35219273 | CWSP - VOLTA 110149742 | Other | Building Service Overhead | Not assigned | 003/2021 | 65.34
35219273 | CWSP - VOLTA 110149742 | Other | Capitalized A&G | Not assigned | 001/2021 | 287.06
35219273 | CWSP - VOLTA 110149742 | Other | Capitalized A&G | Not assigned | 002/2021 | 336.14
35219273 | CWSP - VOLTA 110149742 | Other | Capitalized A&G | Not assigned | 003/2021 | 355.52
35219273 | CWSP - VOLTA 110149742 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 6.71
35219273 | CWSP - VOLTA 110149742 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 177.25
35219273 | CWSP - VOLTA 110149742 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 189.34
35219273 | CWSP - VOLTA 110149742 | Other | IT Device OH | Not assigned | 001/2021 | 26.2
35219273 | CWSP - VOLTA 110149742 | Other | IT Device OH | Not assigned | 002/2021 | 34.64
35219273 | CWSP - VOLTA 110149742 | Other | IT Device OH | Not assigned | 003/2021 | 37.09
35219273 | CWSP - VOLTA 110149742 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 9.08
35219273 | CWSP - VOLTA 110149742 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 240.08
35219273 | CWSP - VOLTA 110149742 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 256.48
35219273 | CWSP - VOLTA 110149742 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 158.71
35219273 | CWSP - VOLTA 110149742 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 13.71
35219273 | CWSP - VOLTA 110149742 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 27.42
35219273 | CWSP - VOLTA 110149742 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 90.88
35219273 | CWSP - VOLTA 110149742 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 120.15
35219273 | CWSP - VOLTA 110149742 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 128.64
35219275 | CWSP - PUTAH CREEK 110246012 | Contract | Contracts | Not assigned | 003/2021 | 655.7
35219275 | CWSP - PUTAH CREEK 110246012 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 1041.27
35219275 | CWSP - PUTAH CREEK 110246012 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | 261.22
35219275 | CWSP - PUTAH CREEK 110246012 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 2103.34
35219275 | CWSP - PUTAH CREEK 110246012 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 142.5
35219275 | CWSP - PUTAH CREEK 110246012 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 47.5
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Account Services | Not assigned | 003/2021 | 65.63
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Administration | Not assigned | 003/2021 | 139.28
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Analyst Services | Not assigned | 003/2021 | 167.07
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Construction | Not assigned | 003/2021 | 1042.3
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 744.5
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 75.51
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1414.56
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 104.46
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 16.99
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 252.54
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 27.79
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 964.3
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 11.45
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 108.24
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 32.4
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.43
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Mapping | Not assigned | 002/2021 | 6.45
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Mapping | Not assigned | 003/2021 | 11.35
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 156.56
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 16.51
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 647.81
35219275 | CWSP - PUTAH CREEK 110246012 | Labor Internal | Vegetation Management - Misc | Not assigned | 003/2021 | 376.32
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Benefits OH | Not assigned | 001/2021 | 310.85
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Benefits OH | Not assigned | 002/2021 | 32.99
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Benefits OH | Not assigned | 003/2021 | 1204.13
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Building Service Overhead | Not assigned | 001/2021 | 53.36
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.65
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Building Service Overhead | Not assigned | 003/2021 | 217.63
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Capitalized A&G | Not assigned | 001/2021 | 286.21
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Capitalized A&G | Not assigned | 002/2021 | 30.17
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Capitalized A&G | Not assigned | 003/2021 | 1184.33
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 168.73
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 18.56
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 644.29
35219275 | CWSP - PUTAH CREEK 110246012 | Other | IT Device OH | Not assigned | 001/2021 | 30.28
35219275 | CWSP - PUTAH CREEK 110246012 | Other | IT Device OH | Not assigned | 002/2021 | 3.2
35219275 | CWSP - PUTAH CREEK 110246012 | Other | IT Device OH | Not assigned | 003/2021 | 123.54
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 228.54
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 25.14
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 872.7
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 6.86
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 64.82
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 105.03
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 11.13
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 428.43
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Permits/Fees | SOLANO COUNTY | 003/2021 | 747
35219275 | CWSP - PUTAH CREEK 110246012 | Other | Reimbursed Mileage Expense | FERNANDO ARMAS | 003/2021 | 67.2
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 219.22
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -219.22
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 4332.29
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 807.5
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 95
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 97.2
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 55.44
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1684.32
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 4823.28
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 535.92
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 002/2021 | 1074.2
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 243.74
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 34.82
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 570.98
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 2004.48
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 200.74
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 97.56
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 34.34
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 80.98
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 32.4
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 194.4
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 004/2021 | 97.2
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 15.42
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.79
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 394.84
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1210.44
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 165.42
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 6.06
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 29.43
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 50.05
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 16.03
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 79.41
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 135.05
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 772.32
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 2412.37
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 300.85
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 132.56
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 414.03
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 54.39
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 721.84
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 2212.92
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 302.43
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 381.5
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1339.27
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 134.13
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 75.23
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 234.99
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 30.87
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 516.75
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1814.08
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 181.67
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 58.44
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 20.57
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 48.51
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 260.93
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 815.03
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 107.02
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 1090.05
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 166.25
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 142.5
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 236.84
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 306.24
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 104.46
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 184.28
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 102.2
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 48.35
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 22.89
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 32.4
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 64.8
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.5
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 3.7
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 137.05
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 60.73
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 64.64
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Labor Internal | Project Management Services | Not assigned | 002/2021 | 297.8
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1.74
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 5.19
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 7.63
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 4.7
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 14
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 20.58
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 265.59
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 121.31
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 115.26
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 45.6
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 20.82
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 20.83
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 250.53
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 111.01
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 118.18
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 123.11
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 68.29
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 25.87
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 11.82
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 11.83
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 166.76
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 92.51
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 28.97
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 13.71
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 89.75
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 40.98
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 41
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 6106.74
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | 239.48
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 5760.74
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -5760.74
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 7025.4
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 23.75
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 356.25
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Design Overtime Services | Not assigned | 002/2021 | 349.12
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Design Services | Not assigned | 002/2021 | 473.68
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Design Services Double Time | Not assigned | 002/2021 | 473.6
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 88.82
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Engineering Services - OT | Not assigned | 003/2021 | 110.87
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 69.64
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 174.1
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 30.13
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 446.99
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 37.58
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 93.28
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 22.89
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 160.26
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 64.8
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 001/2021 | 129.6
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 64.8
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 453.6
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.07
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 22.14
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 71.08
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 278.6
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 113.69
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 5.33
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 20.09
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 30.93
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 14.38
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 54.21
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 83.46
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Benefits OH | Not assigned | 001/2021 | 126.24
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Benefits OH | Not assigned | 002/2021 | 552.73
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Benefits OH | Not assigned | 003/2021 | 189.98
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 21.67
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 94.87
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 34.34
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 129.95
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 509.34
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 207.84
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 20.14
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 298.64
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 25.11
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | IT Device OH | Not assigned | 001/2021 | 12.31
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | IT Device OH | Not assigned | 002/2021 | 53.84
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | IT Device OH | Not assigned | 003/2021 | 19.48
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 27.27
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 404.53
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 34.01
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 55.88
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 13.71
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 95.98
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 42.64
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 186.75
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 67.59
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 1703.4
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -1703.4
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 2031.89
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 47.5
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 76.56
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 139.28
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 25.95
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 2.12
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 140.78
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 259.2
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Management Services | Not assigned | 001/2021 | 215.18
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Mapping | Not assigned | 002/2021 | 6.24
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 95.68
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1.26
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Benefits OH | Not assigned | 001/2021 | 231.38
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Benefits OH | Not assigned | 002/2021 | 2.52
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Building Service Overhead | Not assigned | 001/2021 | 39.72
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Building Service Overhead | Not assigned | 002/2021 | 0.43
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Canceled Capital Order | Not assigned | 003/2021 | -3917.2
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Capitalized A&G | Not assigned | 001/2021 | 254.14
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Capitalized A&G | Not assigned | 002/2021 | 2.3
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Fleet OH - Elec | Not assigned | 001/2021 | 66.08
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1.41
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | IT Device OH | Not assigned | 001/2021 | 22.55
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | IT Device OH | Not assigned | 002/2021 | 0.25
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 89.51
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1.91
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 84.32
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Payroll Taxes OH | Not assigned | 001/2021 | 78.19
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.85
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 1816.07
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -1816.07
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 1915.26
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 71.25
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Administrative Services - OT | Not assigned | 001/2021 | 264.04
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 153.12
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 612.48
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 174.1
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 51.91
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 209.65
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 178.55
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 32.4
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Manage L&EM | Not assigned | 001/2021 | 34.82
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Management Services | Not assigned | 001/2021 | 215.18
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Mapping | Not assigned | 002/2021 | 5.96
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 132.62
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 124.55
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Benefits OH | Not assigned | 001/2021 | 298.81
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Benefits OH | Not assigned | 002/2021 | 248.83
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Building Service Overhead | Not assigned | 001/2021 | 51.29
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Building Service Overhead | Not assigned | 002/2021 | 42.71
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Canceled Capital Order | Not assigned | 003/2021 | -6238.48
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Capitalized A&G | Not assigned | 001/2021 | 321.68
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Capitalized A&G | Not assigned | 002/2021 | 227.71
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Fleet OH - Elec | Not assigned | 001/2021 | 83.42
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Fleet OH - Elec | Not assigned | 002/2021 | 140.08
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | IT Device OH | Not assigned | 001/2021 | 29.12
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | IT Device OH | Not assigned | 002/2021 | 24.24
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 113
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 189.74
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 106.93
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Payroll Taxes OH | Not assigned | 001/2021 | 100.96
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC | Other | Payroll Taxes OH | Not assigned | 002/2021 | 84.07
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 10016.88
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -3113.24
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 7246.62
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -7246.62
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 1634.79
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 5783.23
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Account Services | Not assigned | 003/2021 | 65.63
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Construction | Not assigned | 003/2021 | 670.05
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Design Drafting Services | Not assigned | 002/2021 | 592.1
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 002/2021 | 349.12
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Drafting Doubletime | Not assigned | 002/2021 | 148
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 153.12
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 34.82
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 16.99
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 370.91
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 286.98
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 137.36
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 196.3
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 12.3
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 259.2
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 421.2
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 64.8
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Manage L&EM | Not assigned | 001/2021 | 129.6
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Management Services | Not assigned | 002/2021 | 69.64
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 4.9
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 23.38
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 78.3
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 332.27
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 190.72
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 6.53
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 20.36
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 32.01
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 17.62
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 54.95
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 86.37
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | Benefits OH | Not assigned | 001/2021 | 133.24
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | Benefits OH | Not assigned | 002/2021 | 630.62
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | Benefits OH | Not assigned | 003/2021 | 352.43
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 22.87
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 108.24
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 63.71
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 143.16
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 607.44
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 348.68
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 247.82
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 191.75
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | IT Device OH | Not assigned | 001/2021 | 12.98
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | IT Device OH | Not assigned | 002/2021 | 61.44
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | IT Device OH | Not assigned | 003/2021 | 36.14
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 335.67
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 259.72
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 82.27
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 117.58
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 7.37
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 45.02
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 213.07
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 125.4
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 5145.12
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -3951.42
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 2215.24
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -2215.24
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 4862.18
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 71.25
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 382.8
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 76.56
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 003/2021 | 50.32
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 129.84
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 47.96
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 470.18
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 1296
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Labor Internal | Management Services | Not assigned | 002/2021 | 34.82
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.21
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Labor Internal | Mapping | Not assigned | 003/2021 | 14.59
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 345.16
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 28.49
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1.74
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 9.6
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 16.77
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 4.71
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 25.9
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 45.24
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | Benefits OH | Not assigned | 002/2021 | 610.19
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | Benefits OH | Not assigned | 003/2021 | 54.04
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | Building Service Overhead | Not assigned | 002/2021 | 104.73
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | Building Service Overhead | Not assigned | 003/2021 | 9.78
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | Capitalized A&G | Not assigned | 002/2021 | 631.04
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | Capitalized A&G | Not assigned | 003/2021 | 52.09
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 86.75
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 32.04
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | IT Device OH | Not assigned | 002/2021 | 59.42
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | IT Device OH | Not assigned | 003/2021 | 5.54
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 117.5
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 43.41
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 281.6
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 206.15
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 19.22
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 3568.96
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -994.75
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 001/2021 | 12895.14
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | Not assigned | 002/2021 | -12895.14
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 5251.13
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 1520
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 55.44
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 612.48
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 002/2021 | 537.1
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 183.63
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 231.93
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 80.98
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 194.4
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Labor Internal | Management Services | Not assigned | 002/2021 | 34.82
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 4.56
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 16.25
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 155.25
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 137.79
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 10.15
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 15.96
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 16.62
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 27.4
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 43.08
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 44.86
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | Benefits OH | Not assigned | 002/2021 | 296.49
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | Benefits OH | Not assigned | 003/2021 | 261.42
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 50.89
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 47.26
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 283.84
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 251.91
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 122.68
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 154.97
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | IT Device OH | Not assigned | 002/2021 | 28.88
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | IT Device OH | Not assigned | 003/2021 | 26.82
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 166.18
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 209.9
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 48.51
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 100.17
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 93
35219291 | CWSP - VACA DIXON 1101126774 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 219.22
35219291 | CWSP - VACA DIXON 1101126774 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -219.22
35219291 | CWSP - VACA DIXON 1101126774 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 1662.11
35219291 | CWSP - VACA DIXON 1101126774 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 52.53
35219291 | CWSP - VACA DIXON 1101126774 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 332.5
35219291 | CWSP - VACA DIXON 1101126774 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 47.5
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Account Services | Not assigned | 003/2021 | 65.63
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Analyst Services | Not assigned | 003/2021 | 27.85
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Construction | Not assigned | 003/2021 | 446.7
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1799.16
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 782.78
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 882.85
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 003/2021 | 859.36
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 174.1
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 243.74
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 208.92
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 69.64
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 16.99
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 609.92
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 267.4
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 743.5
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 95.85
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 109
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 83.65
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 97.2
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 64.8
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Mapping | Not assigned | 002/2021 | 5.98
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Mapping | Not assigned | 003/2021 | 4.32
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 416.99
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 220.99
35219291 | CWSP - VACA DIXON 1101126774 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 502.62
35219291 | CWSP - VACA DIXON 1101126774 | Other | Benefits OH | Not assigned | 001/2021 | 816.87
35219291 | CWSP - VACA DIXON 1101126774 | Other | Benefits OH | Not assigned | 002/2021 | 423.11
35219291 | CWSP - VACA DIXON 1101126774 | Other | Benefits OH | Not assigned | 003/2021 | 932.66
35219291 | CWSP - VACA DIXON 1101126774 | Other | Building Service Overhead | Not assigned | 001/2021 | 140.2
35219291 | CWSP - VACA DIXON 1101126774 | Other | Building Service Overhead | Not assigned | 002/2021 | 72.63
35219291 | CWSP - VACA DIXON 1101126774 | Other | Building Service Overhead | Not assigned | 003/2021 | 168.56
35219291 | CWSP - VACA DIXON 1101126774 | Other | Capitalized A&G | Not assigned | 001/2021 | 762.34
35219291 | CWSP - VACA DIXON 1101126774 | Other | Capitalized A&G | Not assigned | 002/2021 | 404.02
35219291 | CWSP - VACA DIXON 1101126774 | Other | Capitalized A&G | Not assigned | 003/2021 | 918.89
35219291 | CWSP - VACA DIXON 1101126774 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 407.51
35219291 | CWSP - VACA DIXON 1101126774 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 178.65
35219291 | CWSP - VACA DIXON 1101126774 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 496.77
35219291 | CWSP - VACA DIXON 1101126774 | Other | IT Device OH | Not assigned | 001/2021 | 79.57
35219291 | CWSP - VACA DIXON 1101126774 | Other | IT Device OH | Not assigned | 002/2021 | 41.22
35219291 | CWSP - VACA DIXON 1101126774 | Other | IT Device OH | Not assigned | 003/2021 | 95.69
35219291 | CWSP - VACA DIXON 1101126774 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 551.98
35219291 | CWSP - VACA DIXON 1101126774 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 241.98
35219291 | CWSP - VACA DIXON 1101126774 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 672.88
35219291 | CWSP - VACA DIXON 1101126774 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 57.41
35219291 | CWSP - VACA DIXON 1101126774 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 65.29
35219291 | CWSP - VACA DIXON 1101126774 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 50.1
35219291 | CWSP - VACA DIXON 1101126774 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 275.98
35219291 | CWSP - VACA DIXON 1101126774 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 142.96
35219291 | CWSP - VACA DIXON 1101126774 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 331.83
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 1798.19
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 47.5
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Labor Internal | Design Overtime Services | Not assigned | 002/2021 | 610.96
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Labor Internal | Design Services | Not assigned | 002/2021 | 473.68
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Labor Internal | Design Services Double Time | Not assigned | 002/2021 | 592
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 003/2021 | 322.26
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 34.82
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 570.26
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 109.25
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 12.3
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 11.45
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 32.4
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Labor Internal | Mapping | Not assigned | 002/2021 | 5.54
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 7.01
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 345.33
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 64.9
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | Benefits OH | Not assigned | 001/2021 | 11.94
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | Benefits OH | Not assigned | 002/2021 | 687.93
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | Benefits OH | Not assigned | 003/2021 | 123.12
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | Building Service Overhead | Not assigned | 001/2021 | 2.05
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | Building Service Overhead | Not assigned | 002/2021 | 118.07
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | Building Service Overhead | Not assigned | 003/2021 | 22.25
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | Capitalized A&G | Not assigned | 001/2021 | 12.82
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | Capitalized A&G | Not assigned | 002/2021 | 631.31
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | Capitalized A&G | Not assigned | 003/2021 | 118.66
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 381.01
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 72.99
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | IT Device OH | Not assigned | 001/2021 | 1.16
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | IT Device OH | Not assigned | 002/2021 | 67
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | IT Device OH | Not assigned | 003/2021 | 12.63
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 516.09
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 98.87
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 7.37
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 6.86
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 4.03
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 232.43
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 43.82
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 2410.43
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 118.75
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 55.44
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Labor Internal | Design Overtime Services | Not assigned | 002/2021 | 261.84
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 87.28
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 003/2021 | 537.1
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 69.64
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 29.59
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 91.33
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 201.04
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 24.6
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 11.45
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 32.4
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Labor Internal | Mapping | Not assigned | 002/2021 | 7.59
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Labor Internal | Mapping | Not assigned | 003/2021 | 0.5
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 31.61
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 60.79
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 119.44
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Benefits OH | Not assigned | 001/2021 | 58.98
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Benefits OH | Not assigned | 002/2021 | 119.5
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Benefits OH | Not assigned | 003/2021 | 226.59
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Building Service Overhead | Not assigned | 001/2021 | 10.13
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Building Service Overhead | Not assigned | 002/2021 | 20.51
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Building Service Overhead | Not assigned | 003/2021 | 40.98
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Capitalized A&G | Not assigned | 001/2021 | 57.78
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Capitalized A&G | Not assigned | 002/2021 | 111.13
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Capitalized A&G | Not assigned | 003/2021 | 218.35
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Fleet OH - Elec | Not assigned | 001/2021 | 19.77
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Fleet OH - Elec | Not assigned | 002/2021 | 61.03
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Fleet OH - Elec | Not assigned | 003/2021 | 134.32
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | IT Device OH | Not assigned | 001/2021 | 5.75
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | IT Device OH | Not assigned | 002/2021 | 11.63
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | IT Device OH | Not assigned | 003/2021 | 23.25
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 26.78
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 82.66
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 181.94
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 14.74
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 6.86
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Payroll Taxes OH | Not assigned | 001/2021 | 19.93
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Payroll Taxes OH | Not assigned | 002/2021 | 40.37
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Other | Payroll Taxes OH | Not assigned | 003/2021 | 80.63
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 4803.52
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 71.25
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 597.72
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 208.92
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.07
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 207.51
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 153.94
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 226.8
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.21
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Labor Internal | Mapping | Not assigned | 003/2021 | 14.41
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 87.8
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 123.28
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.98
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 7.22
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2.64
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 19.48
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Other | Benefits OH | Not assigned | 002/2021 | 149.4
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Other | Benefits OH | Not assigned | 003/2021 | 233.86
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Other | Building Service Overhead | Not assigned | 002/2021 | 25.65
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Other | Building Service Overhead | Not assigned | 003/2021 | 42.27
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Other | Capitalized A&G | Not assigned | 002/2021 | 160.51
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Other | Capitalized A&G | Not assigned | 003/2021 | 225.39
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.05
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 138.64
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Other | IT Device OH | Not assigned | 002/2021 | 14.56
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Other | IT Device OH | Not assigned | 003/2021 | 23.99
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.06
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 187.8
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 92.2
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 50.48
35219587 | CWSP - MARIPOSA 2102440236 PH2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 83.2
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 4864.46
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 118.75
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 421.92
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 208.92
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.12
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 147.98
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 73.81
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.36
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Labor Internal | Mapping | Not assigned | 003/2021 | 14.59
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 42.15
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 87.91
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.54
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 5.96
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.45
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 16.08
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Other | Benefits OH | Not assigned | 002/2021 | 71.74
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Other | Benefits OH | Not assigned | 003/2021 | 166.78
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Other | Building Service Overhead | Not assigned | 002/2021 | 12.31
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Other | Building Service Overhead | Not assigned | 003/2021 | 30.14
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Other | Capitalized A&G | Not assigned | 002/2021 | 77.05
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Other | Capitalized A&G | Not assigned | 003/2021 | 160.72
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.08
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 98.86
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Other | IT Device OH | Not assigned | 002/2021 | 7
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Other | IT Device OH | Not assigned | 003/2021 | 17.11
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.11
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 133.93
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 44.21
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 24.23
35219588 | CWSP - MARIPOSA 2102440236 PH3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 59.33
35219589 | CWSP - WILDWOOD 11011454 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 219.22
35219589 | CWSP - WILDWOOD 11011454 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -219.22
35219589 | CWSP - WILDWOOD 11011454 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | 24570
35219589 | CWSP - WILDWOOD 11011454 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 004/2021 | -24570
35219589 | CWSP - WILDWOOD 11011454 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 2655.74
35219589 | CWSP - WILDWOOD 11011454 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 23.75
35219589 | CWSP - WILDWOOD 11011454 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 380
35219589 | CWSP - WILDWOOD 11011454 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 95
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Account Services | Not assigned | 003/2021 | 191.14
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 64.8
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Administrative Services - OT | Not assigned | 001/2021 | 44.01
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Engineering Services - OT | Not assigned | 003/2021 | 110.87
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 2179.92
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 76.56
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 250.25
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 139.28
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 49.49
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 739.02
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 29.04
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 122.52
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 61.34
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 49.21
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 64.8
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 004/2021 | 64.8
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Mapping | Not assigned | 001/2021 | 0.07
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Mapping | Not assigned | 002/2021 | 9.11
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.29
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 474.02
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 17.25
35219589 | CWSP - WILDWOOD 11011454 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 139.34
35219589 | CWSP - WILDWOOD 11011454 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 5.69
35219589 | CWSP - WILDWOOD 11011454 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 14.15
35219589 | CWSP - WILDWOOD 11011454 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 37.68
35219589 | CWSP - WILDWOOD 11011454 | Other | AFUDC-Equity | Not assigned | 001/2021 | 15.35
35219589 | CWSP - WILDWOOD 11011454 | Other | AFUDC-Equity | Not assigned | 002/2021 | 38.18
35219589 | CWSP - WILDWOOD 11011454 | Other | AFUDC-Equity | Not assigned | 003/2021 | 101.67
35219589 | CWSP - WILDWOOD 11011454 | Other | Benefits OH | Not assigned | 001/2021 | 936.58
35219589 | CWSP - WILDWOOD 11011454 | Other | Benefits OH | Not assigned | 002/2021 | 34.47
35219589 | CWSP - WILDWOOD 11011454 | Other | Benefits OH | Not assigned | 003/2021 | 234.85
35219589 | CWSP - WILDWOOD 11011454 | Other | Building Service Overhead | Not assigned | 001/2021 | 160.75
35219589 | CWSP - WILDWOOD 11011454 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.92
35219589 | CWSP - WILDWOOD 11011454 | Other | Building Service Overhead | Not assigned | 003/2021 | 42.43
35219589 | CWSP - WILDWOOD 11011454 | Other | Capitalized A&G | Not assigned | 001/2021 | 866.6
35219589 | CWSP - WILDWOOD 11011454 | Other | Capitalized A&G | Not assigned | 002/2021 | 31.54
35219589 | CWSP - WILDWOOD 11011454 | Other | Capitalized A&G | Not assigned | 003/2021 | 254.73
35219589 | CWSP - WILDWOOD 11011454 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 493.77
35219589 | CWSP - WILDWOOD 11011454 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 19.4
35219589 | CWSP - WILDWOOD 11011454 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 81.86
35219589 | CWSP - WILDWOOD 11011454 | Other | IT Device OH | Not assigned | 001/2021 | 91.21
35219589 | CWSP - WILDWOOD 11011454 | Other | IT Device OH | Not assigned | 002/2021 | 3.35
35219589 | CWSP - WILDWOOD 11011454 | Other | IT Device OH | Not assigned | 003/2021 | 24.08
35219589 | CWSP - WILDWOOD 11011454 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 668.82
35219589 | CWSP - WILDWOOD 11011454 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 26.28
35219589 | CWSP - WILDWOOD 11011454 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 110.89
35219589 | CWSP - WILDWOOD 11011454 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 36.74
35219589 | CWSP - WILDWOOD 11011454 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 29.47
35219589 | CWSP - WILDWOOD 11011454 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 316.44
35219589 | CWSP - WILDWOOD 11011454 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 11.65
35219589 | CWSP - WILDWOOD 11011454 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 83.55
35219590 | CWSP - VACA DIXON 1105965390 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 6288.04
35219590 | CWSP - VACA DIXON 1105965390 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 166.25
35219590 | CWSP - VACA DIXON 1105965390 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 166.25
35219590 | CWSP - VACA DIXON 1105965390 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1110.12
35219590 | CWSP - VACA DIXON 1105965390 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 69.64
35219590 | CWSP - VACA DIXON 1105965390 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.17
35219590 | CWSP - VACA DIXON 1105965390 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 382.89
35219590 | CWSP - VACA DIXON 1105965390 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 70.39
35219590 | CWSP - VACA DIXON 1105965390 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 129.6
35219590 | CWSP - VACA DIXON 1105965390 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.5
35219590 | CWSP - VACA DIXON 1105965390 | Labor Internal | Mapping | Not assigned | 003/2021 | 19.36
35219590 | CWSP - VACA DIXON 1105965390 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 40.23
35219590 | CWSP - VACA DIXON 1105965390 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 227.48
35219590 | CWSP - VACA DIXON 1105965390 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.55
35219590 | CWSP - VACA DIXON 1105965390 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 8.92
35219590 | CWSP - VACA DIXON 1105965390 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.49
35219590 | CWSP - VACA DIXON 1105965390 | Other | AFUDC-Equity | Not assigned | 003/2021 | 24.07
35219590 | CWSP - VACA DIXON 1105965390 | Other | Benefits OH | Not assigned | 002/2021 | 68.49
35219590 | CWSP - VACA DIXON 1105965390 | Other | Benefits OH | Not assigned | 003/2021 | 431.53
35219590 | CWSP - VACA DIXON 1105965390 | Other | Building Service Overhead | Not assigned | 002/2021 | 11.76
35219590 | CWSP - VACA DIXON 1105965390 | Other | Building Service Overhead | Not assigned | 003/2021 | 77.99
35219590 | CWSP - VACA DIXON 1105965390 | Other | Capitalized A&G | Not assigned | 002/2021 | 73.54
35219590 | CWSP - VACA DIXON 1105965390 | Other | Capitalized A&G | Not assigned | 003/2021 | 415.88
35219590 | CWSP - VACA DIXON 1105965390 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.11
35219590 | CWSP - VACA DIXON 1105965390 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 255.83
35219590 | CWSP - VACA DIXON 1105965390 | Other | IT Device OH | Not assigned | 002/2021 | 6.68
35219590 | CWSP - VACA DIXON 1105965390 | Other | IT Device OH | Not assigned | 003/2021 | 44.27
35219590 | CWSP - VACA DIXON 1105965390 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.15
35219590 | CWSP - VACA DIXON 1105965390 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 346.52
35219590 | CWSP - VACA DIXON 1105965390 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 42.16
35219590 | CWSP - VACA DIXON 1105965390 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 23.13
35219590 | CWSP - VACA DIXON 1105965390 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 153.54
35219591 | CWSP - OLETA 1101754718 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 5687.01
35219591 | CWSP - OLETA 1101754718 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 23.75
35219591 | CWSP - OLETA 1101754718 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 973.75
35219591 | CWSP - OLETA 1101754718 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 36.09
35219591 | CWSP - OLETA 1101754718 | Labor Internal | Design Drafting Services | Not assigned | 002/2021 | 1036.19
35219591 | CWSP - OLETA 1101754718 | Labor Internal | Design Drafting Services | Not assigned | 003/2021 | 355.27
35219591 | CWSP - OLETA 1101754718 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 003/2021 | 87.28
35219591 | CWSP - OLETA 1101754718 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 70.32
35219591 | CWSP - OLETA 1101754718 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 351.4
35219591 | CWSP - OLETA 1101754718 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 180.63
35219591 | CWSP - OLETA 1101754718 | Labor Internal | Indirect Labor - Gas | Not assigned | 002/2021 | 13.06
35219591 | CWSP - OLETA 1101754718 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.39
35219591 | CWSP - OLETA 1101754718 | Labor Internal | Mapping | Not assigned | 003/2021 | 19.98
35219591 | CWSP - OLETA 1101754718 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 216.03
35219591 | CWSP - OLETA 1101754718 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 107.31
35219591 | CWSP - OLETA 1101754718 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.64
35219591 | CWSP - OLETA 1101754718 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 11.81
35219591 | CWSP - OLETA 1101754718 | Other | AFUDC-Equity | Not assigned | 002/2021 | 7.13
35219591 | CWSP - OLETA 1101754718 | Other | AFUDC-Equity | Not assigned | 003/2021 | 31.88
35219591 | CWSP - OLETA 1101754718 | Other | Benefits OH | Not assigned | 002/2021 | 434.05
35219591 | CWSP - OLETA 1101754718 | Other | Benefits OH | Not assigned | 003/2021 | 203.57
35219591 | CWSP - OLETA 1101754718 | Other | Building Service Overhead | Not assigned | 002/2021 | 74.51
35219591 | CWSP - OLETA 1101754718 | Other | Building Service Overhead | Not assigned | 003/2021 | 36.8
35219591 | CWSP - OLETA 1101754718 | Other | Capitalized A&G | Not assigned | 002/2021 | 394.97
35219591 | CWSP - OLETA 1101754718 | Other | Capitalized A&G | Not assigned | 003/2021 | 196.2
35219591 | CWSP - OLETA 1101754718 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 234.79
35219591 | CWSP - OLETA 1101754718 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 120.7
35219591 | CWSP - OLETA 1101754718 | Other | Fleet OH - Gas | Not assigned | 002/2021 | 11.18
35219591 | CWSP - OLETA 1101754718 | Other | IT Device OH | Not assigned | 002/2021 | 42.28
35219591 | CWSP - OLETA 1101754718 | Other | IT Device OH | Not assigned | 003/2021 | 20.89
35219591 | CWSP - OLETA 1101754718 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 318.02
35219591 | CWSP - OLETA 1101754718 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 163.47
35219591 | CWSP - OLETA 1101754718 | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 20.02
35219591 | CWSP - OLETA 1101754718 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 146.66
35219591 | CWSP - OLETA 1101754718 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 72.43
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 1112.13
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 5178.94
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 285
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Administrative Services - OT | Not assigned | 001/2021 | 44.01
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 003/2021 | 501.86
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 1480.25
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 458.22
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 76.56
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 226.33
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 684.51
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 30.51
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 245.85
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 95.51
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 91.58
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 259.2
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 4.2
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 15.54
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 461.12
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 18.12
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 204.86
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 6.58
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 17.46
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 24.12
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 17.76
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 47.12
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 65.07
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Benefits OH | Not assigned | 001/2021 | 905.09
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Benefits OH | Not assigned | 002/2021 | 36.22
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Benefits OH | Not assigned | 003/2021 | 370.25
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 155.33
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 6.22
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 66.92
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 843.02
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 33.13
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 374.54
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 457.35
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 20.38
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 164.26
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | IT Device OH | Not assigned | 001/2021 | 88.19
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | IT Device OH | Not assigned | 002/2021 | 3.53
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | IT Device OH | Not assigned | 003/2021 | 38
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 619.49
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 27.61
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 222.49
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 57.21
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 54.85
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 305.78
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 12.24
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 131.74
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 3139.28
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 451.25
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 110.87
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 532.89
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 261.84
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 76.56
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 208.92
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 295.82
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 41.11
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 73.81
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 45.79
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 129.6
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Labor Internal | Mapping | Not assigned | 001/2021 | 1.35
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 10.42
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 217.83
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 24.43
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 71.08
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.92
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 8.61
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 12.19
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 7.88
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 23.22
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 32.88
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Benefits OH | Not assigned | 001/2021 | 422.71
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Benefits OH | Not assigned | 002/2021 | 48.79
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Benefits OH | Not assigned | 003/2021 | 127.51
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 72.54
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 8.37
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 23.04
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 398.23
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 44.66
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 129.96
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 197.66
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 27.47
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | IT Device OH | Not assigned | 001/2021 | 41.19
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | IT Device OH | Not assigned | 002/2021 | 4.75
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | IT Device OH | Not assigned | 003/2021 | 13.09
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 267.72
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 37.21
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 44.21
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 27.42
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 142.8
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 16.48
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 45.36
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Labor Internal | Account Services | Not assigned | 001/2021 | 114.87
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Labor Internal | Account Services | Not assigned | 002/2021 | 393.81
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Labor Internal | Account Services | Not assigned | 003/2021 | 98.45
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1301.52
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 765.6
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 76.56
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 29.74
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 101.96
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 25.49
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 441.22
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 259.54
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.95
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 285.26
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 233.5
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 35.25
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 3.37
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 9.31
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 12.25
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | AFUDC-Equity | Not assigned | 001/2021 | 9.1
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | AFUDC-Equity | Not assigned | 002/2021 | 25.13
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | AFUDC-Equity | Not assigned | 003/2021 | 33.04
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | Benefits OH | Not assigned | 001/2021 | 556.22
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | Benefits OH | Not assigned | 002/2021 | 419.63
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | Benefits OH | Not assigned | 003/2021 | 55.74
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | Building Service Overhead | Not assigned | 001/2021 | 95.47
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | Building Service Overhead | Not assigned | 002/2021 | 72.01
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | Building Service Overhead | Not assigned | 003/2021 | 10.08
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | Capitalized A&G | Not assigned | 001/2021 | 521.52
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | Capitalized A&G | Not assigned | 002/2021 | 426.89
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | Capitalized A&G | Not assigned | 003/2021 | 64.44
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | Fleet OH - Elec | Not assigned | 001/2021 | 294.79
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | Fleet OH - Elec | Not assigned | 002/2021 | 173.41
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | Fleet OH - Elec | Not assigned | 003/2021 | 17.34
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | IT Device OH | Not assigned | 001/2021 | 54.18
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | IT Device OH | Not assigned | 002/2021 | 40.88
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | IT Device OH | Not assigned | 003/2021 | 5.72
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 399.31
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 234.89
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 23.49
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | Payroll Taxes OH | Not assigned | 001/2021 | 187.91
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | Payroll Taxes OH | Not assigned | 002/2021 | 141.76
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Other | Payroll Taxes OH | Not assigned | 003/2021 | 19.83
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 001/2021 | 1148
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 2991.15
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 403.75
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor Internal | Account Services | Not assigned | 003/2021 | 49.23
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 110.87
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 236.84
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 218.2
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 76.56
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 139.28
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 104.46
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 12.75
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 101.5
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 40.96
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 156.01
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 49.2
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 36.91
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor Internal | Mapping | Not assigned | 001/2021 | 4.65
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor Internal | Mapping | Not assigned | 002/2021 | 9.97
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 88.35
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 24.34
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 123.63
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.24
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 7.14
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 11.21
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 6.06
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 19.26
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 30.24
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Benefits OH | Not assigned | 001/2021 | 168.19
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Benefits OH | Not assigned | 002/2021 | 48.61
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Benefits OH | Not assigned | 003/2021 | 223.05
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Building Service Overhead | Not assigned | 001/2021 | 28.87
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Building Service Overhead | Not assigned | 002/2021 | 8.34
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Building Service Overhead | Not assigned | 003/2021 | 40.32
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Capitalized A&G | Not assigned | 001/2021 | 161.53
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Capitalized A&G | Not assigned | 002/2021 | 44.49
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Capitalized A&G | Not assigned | 003/2021 | 226.03
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 67.81
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 27.37
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 104.23
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | IT Device OH | Not assigned | 001/2021 | 16.38
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | IT Device OH | Not assigned | 002/2021 | 4.73
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | IT Device OH | Not assigned | 003/2021 | 22.89
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 91.86
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 37.07
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 141.18
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 29.48
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 22.1
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 56.83
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 16.42
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 79.37
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 1827.03
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 831.25
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 194.4
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Labor Internal | Design Services | Not assigned | 003/2021 | 118.42
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 914.16
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 70.32
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 492.24
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 139.28
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 309.9
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 23.84
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 209.71
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 140.79
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 64.8
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Labor Internal | Management Services | Not assigned | 001/2021 | 235.48
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Labor Internal | Management Services | Not assigned | 002/2021 | 5180.59
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Labor Internal | Management Services | Not assigned | 003/2021 | 5916.47
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Labor Internal | Mapping | Not assigned | 003/2021 | 7.97
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 184.11
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.16
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 204.85
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 2.53
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 12.09
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 31.33
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | AFUDC-Equity | Not assigned | 001/2021 | 6.84
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | AFUDC-Equity | Not assigned | 002/2021 | 32.64
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | AFUDC-Equity | Not assigned | 003/2021 | 84.53
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | Benefits OH | Not assigned | 001/2021 | 413.48
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | Benefits OH | Not assigned | 002/2021 | 1033.46
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | Benefits OH | Not assigned | 003/2021 | 1456.1
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | Building Service Overhead | Not assigned | 001/2021 | 70.96
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | Building Service Overhead | Not assigned | 002/2021 | 177.38
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | Building Service Overhead | Not assigned | 003/2021 | 263.19
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | Capitalized A&G | Not assigned | 001/2021 | 423.29
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | Capitalized A&G | Not assigned | 002/2021 | 1933.39
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | Capitalized A&G | Not assigned | 003/2021 | 2552.93
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | Fleet OH - Elec | Not assigned | 001/2021 | 207.05
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | Fleet OH - Elec | Not assigned | 002/2021 | 15.93
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | Fleet OH - Elec | Not assigned | 003/2021 | 140.12
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | IT Device OH | Not assigned | 001/2021 | 40.29
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | IT Device OH | Not assigned | 002/2021 | 100.67
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | IT Device OH | Not assigned | 003/2021 | 149.39
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 280.47
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 21.57
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 189.8
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 84.32
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | Payroll Taxes OH | Not assigned | 001/2021 | 139.69
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | Payroll Taxes OH | Not assigned | 002/2021 | 349.16
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Other | Payroll Taxes OH | Not assigned | 003/2021 | 518.09
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Labor Internal | Design Drafting Services | Not assigned | 002/2021 | 3611.81
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Labor Internal | Design Drafting Services | Not assigned | 003/2021 | 7578.88
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 002/2021 | 1396.48
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 003/2021 | 3534.84
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 1065.78
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Labor Internal | Electric Estimating | Not assigned | 004/2021 | 131.1
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 1352.84
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 335.03
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 210.54
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 1357.98
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Labor Internal | Environmental Services | Not assigned | 003/2021 | 17.41
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1861.86
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 4709.32
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 600.4
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 324
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1106.13
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 3140.05
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Labor Internal | Project Management Services | Not assigned | 002/2021 | 148.9
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 148.9
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 13.36
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 63.85
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 36.05
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 172.3
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Other | Benefits OH | Not assigned | 002/2021 | 2209.8
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Other | Benefits OH | Not assigned | 003/2021 | 5860.47
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Other | Building Service Overhead | Not assigned | 002/2021 | 379.26
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Other | Building Service Overhead | Not assigned | 003/2021 | 1059.23
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Other | Capitalized A&G | Not assigned | 002/2021 | 2022.23
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Other | Capitalized A&G | Not assigned | 003/2021 | 5740.66
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1243.99
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 3146.5
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Other | IT Device OH | Not assigned | 002/2021 | 215.26
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Other | IT Device OH | Not assigned | 003/2021 | 601.18
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1685.01
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 4261.99
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 359.59
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 746.59
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 2085.13
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 71.25
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Labor Internal | Account Services | Not assigned | 003/2021 | 16.41
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Labor Internal | Design Drafting Services | Not assigned | 003/2021 | 5269.79
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 3789.44
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Labor Internal | Electric Estimating | Not assigned | 004/2021 | 721.05
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 327.3
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Labor Internal | Electric Estimating Overtime | Not assigned | 004/2021 | 227.98
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 38.28
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 591.94
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 4.25
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 75.17
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 3232.66
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 209.13
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.21
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 44.66
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 2043.05
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Labor Internal | Project Management Overtime | Not assigned | 002/2021 | 221.74
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 110.87
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.54
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 25.45
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.46
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 68.67
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Other | Benefits OH | Not assigned | 002/2021 | 89.21
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Other | Benefits OH | Not assigned | 003/2021 | 3840.34
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.31
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Other | Building Service Overhead | Not assigned | 003/2021 | 694.13
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Other | Capitalized A&G | Not assigned | 002/2021 | 81.64
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Other | Capitalized A&G | Not assigned | 003/2021 | 3735.11
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 50.22
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 2159.88
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Other | IT Device OH | Not assigned | 002/2021 | 8.69
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Other | IT Device OH | Not assigned | 003/2021 | 393.95
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 68.03
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 2925.6
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 125.26
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.14
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 1366.38
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 2738.19
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 1773.51
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 1068.75
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 352.04
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 2068.25
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Engineering Services - OT | Not assigned | 003/2021 | 55.44
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 76.56
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 76.56
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 002/2021 | 1181.62
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 34.82
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 25.95
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 430.39
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 20.59
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 640.34
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 2539.33
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 64.8
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 1360.8
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 5119.2
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Mapping | Not assigned | 002/2021 | 11.42
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Mapping | Not assigned | 003/2021 | 5.32
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 15.42
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 620.73
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1459.79
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.19
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 10.29
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 36.85
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | AFUDC-Equity | Not assigned | 001/2021 | 0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | AFUDC-Equity | Not assigned | 002/2021 | 27.77
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | AFUDC-Equity | Not assigned | 003/2021 | 99.45
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Benefits OH | Not assigned | 001/2021 | 30.81
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Benefits OH | Not assigned | 002/2021 | 1131.98
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Benefits OH | Not assigned | 003/2021 | 2362.18
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Building Service Overhead | Not assigned | 001/2021 | 5.29
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Building Service Overhead | Not assigned | 002/2021 | 194.29
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Building Service Overhead | Not assigned | 003/2021 | 426.95
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Capitalized A&G | Not assigned | 001/2021 | 28.19
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Capitalized A&G | Not assigned | 002/2021 | 1134.82
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Capitalized A&G | Not assigned | 003/2021 | 2668.79
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Fleet OH - Elec | Not assigned | 001/2021 | 17.34
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Fleet OH - Elec | Not assigned | 002/2021 | 287.56
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Fleet OH - Elec | Not assigned | 003/2021 | 13.76
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | IT Device OH | Not assigned | 001/2021 | 3
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | IT Device OH | Not assigned | 002/2021 | 110.26
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | IT Device OH | Not assigned | 003/2021 | 242.32
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Lodging | VICTOR T RASGADO | 004/2021 | 327.44
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Meals Expense | VICTOR T RASGADO | 004/2021 | 59.62
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 23.49
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 389.51
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 18.64
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 383.52
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 1520.86
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Payroll Taxes OH | Not assigned | 001/2021 | 10.41
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Payroll Taxes OH | Not assigned | 002/2021 | 382.43
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Other | Payroll Taxes OH | Not assigned | 003/2021 | 840.45
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 4683.64
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 95
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 55.44
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Labor Internal | Design Overtime Services | Not assigned | 002/2021 | 87.28
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Labor Internal | Design Services | Not assigned | 002/2021 | 473.68
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 59.21
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 738.36
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 140.64
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 69.64
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 20.07
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 445.33
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 66.64
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 24.6
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 11.45
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 32.4
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Labor Internal | Mapping | Not assigned | 002/2021 | 14.34
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Labor Internal | Mapping | Not assigned | 003/2021 | 0.5
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 25.95
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 271.1
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 39.59
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.29
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 7.61
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 15.11
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | AFUDC-Equity | Not assigned | 001/2021 | 0.79
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | AFUDC-Equity | Not assigned | 002/2021 | 20.53
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | AFUDC-Equity | Not assigned | 003/2021 | 40.78
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Benefits OH | Not assigned | 001/2021 | 47.68
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Benefits OH | Not assigned | 002/2021 | 539.67
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Benefits OH | Not assigned | 003/2021 | 75.14
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Building Service Overhead | Not assigned | 001/2021 | 8.2
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Building Service Overhead | Not assigned | 002/2021 | 92.62
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Building Service Overhead | Not assigned | 003/2021 | 13.59
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Capitalized A&G | Not assigned | 001/2021 | 47.44
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Capitalized A&G | Not assigned | 002/2021 | 495.62
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Capitalized A&G | Not assigned | 003/2021 | 72.37
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Fleet OH - Elec | Not assigned | 001/2021 | 13.41
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Fleet OH - Elec | Not assigned | 002/2021 | 297.55
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Fleet OH - Elec | Not assigned | 003/2021 | 44.52
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | IT Device OH | Not assigned | 001/2021 | 4.64
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | IT Device OH | Not assigned | 002/2021 | 52.56
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | IT Device OH | Not assigned | 003/2021 | 7.72
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 18.17
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 403.03
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 60.31
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 14.74
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 6.86
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Payroll Taxes OH | Not assigned | 001/2021 | 16.12
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Payroll Taxes OH | Not assigned | 002/2021 | 182.34
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Other | Payroll Taxes OH | Not assigned | 003/2021 | 26.72
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 1626.11
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 118.75
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Account Services | Not assigned | 003/2021 | 131.26
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 88.82
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Engineering Services - OT | Not assigned | 003/2021 | 55.44
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 773.52
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 002/2021 | 100.63
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 69.64
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 139.28
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 33.98
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 298.11
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 48.9
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 36.05
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 11.45
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 80.13
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 32.4
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 32.4
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 226.8
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 004/2021 | 129.6
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Mapping | Not assigned | 002/2021 | 5.23
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 20.56
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 183.63
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 101.18
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.22
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4.01
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 8.65
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | AFUDC-Equity | Not assigned | 001/2021 | 0.58
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | AFUDC-Equity | Not assigned | 002/2021 | 10.83
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | AFUDC-Equity | Not assigned | 003/2021 | 23.35
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | Benefits OH | Not assigned | 001/2021 | 34.96
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | Benefits OH | Not assigned | 002/2021 | 364.9
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | Benefits OH | Not assigned | 003/2021 | 164.23
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | Building Service Overhead | Not assigned | 001/2021 | 6.01
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | Building Service Overhead | Not assigned | 002/2021 | 62.63
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | Building Service Overhead | Not assigned | 003/2021 | 29.7
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | Capitalized A&G | Not assigned | 001/2021 | 37.57
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | Capitalized A&G | Not assigned | 002/2021 | 335.72
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | Capitalized A&G | Not assigned | 003/2021 | 184.95
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | Fleet OH - Elec | Not assigned | 002/2021 | 199.17
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | Fleet OH - Elec | Not assigned | 003/2021 | 32.68
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | IT Device OH | Not assigned | 001/2021 | 3.41
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | IT Device OH | Not assigned | 002/2021 | 35.55
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | IT Device OH | Not assigned | 003/2021 | 16.87
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 269.79
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 44.26
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 21.6
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 6.86
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 47.99
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | Payroll Taxes OH | Not assigned | 001/2021 | 11.83
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | Payroll Taxes OH | Not assigned | 002/2021 | 123.3
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Other | Payroll Taxes OH | Not assigned | 003/2021 | 58.44
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 3697.45
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 8250.19
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 166.25
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 145.8
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Construction | Not assigned | 003/2021 | 670.05
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Design Services | Not assigned | 001/2021 | 177.63
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Design Services | Not assigned | 002/2021 | 118.42
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Design Services | Not assigned | 003/2021 | 532.89
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 29.61
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 148.9
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 446.7
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 104.46
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 70.25
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 94.55
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 569.66
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 59.79
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 11.45
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 51.51
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 64.8
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 32.4
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Mapping | Not assigned | 002/2021 | 11.59
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Mapping | Not assigned | 003/2021 | 30.78
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 75.83
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 62.7
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 367.78
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.86
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 5.51
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 18.19
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | AFUDC-Equity | Not assigned | 001/2021 | 2.33
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | AFUDC-Equity | Not assigned | 002/2021 | 14.88
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | AFUDC-Equity | Not assigned | 003/2021 | 49.09
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Benefits OH | Not assigned | 001/2021 | 141.4
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Benefits OH | Not assigned | 002/2021 | 123.33
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Benefits OH | Not assigned | 003/2021 | 689.45
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Building Service Overhead | Not assigned | 001/2021 | 24.28
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Building Service Overhead | Not assigned | 002/2021 | 21.16
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Building Service Overhead | Not assigned | 003/2021 | 124.62
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Capitalized A&G | Not assigned | 001/2021 | 138.63
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Capitalized A&G | Not assigned | 002/2021 | 114.62
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Capitalized A&G | Not assigned | 003/2021 | 672.41
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Fleet OH - Elec | Not assigned | 001/2021 | 46.94
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Fleet OH - Elec | Not assigned | 002/2021 | 63.18
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Fleet OH - Elec | Not assigned | 003/2021 | 380.62
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | IT Device OH | Not assigned | 001/2021 | 13.78
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | IT Device OH | Not assigned | 002/2021 | 12.02
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | IT Device OH | Not assigned | 003/2021 | 70.73
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 63.58
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 85.57
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 515.55
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 35.82
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 6.86
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 30.85
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Payroll Taxes OH | Not assigned | 001/2021 | 47.76
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Payroll Taxes OH | Not assigned | 002/2021 | 41.68
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Other | Payroll Taxes OH | Not assigned | 003/2021 | 245.31
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 3970.63
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 380
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Labor Internal | Design Overtime Services | Not assigned | 002/2021 | 698.24
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Labor Internal | Design Services | Not assigned | 002/2021 | 473.68
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 59.21
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 174.1
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 20.07
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 401.7
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 84.39
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 11.45
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 64.8
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 32.4
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Labor Internal | Mapping | Not assigned | 002/2021 | 13.05
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 60.04
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 245.18
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.65
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 7.68
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 14.05
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.75
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | AFUDC-Equity | Not assigned | 002/2021 | 20.71
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | AFUDC-Equity | Not assigned | 003/2021 | 37.92
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | Benefits OH | Not assigned | 001/2021 | 105.69
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | Benefits OH | Not assigned | 002/2021 | 487.87
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | Building Service Overhead | Not assigned | 001/2021 | 18.17
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | Building Service Overhead | Not assigned | 002/2021 | 83.73
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | Capitalized A&G | Not assigned | 001/2021 | 109.76
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | Capitalized A&G | Not assigned | 002/2021 | 448.24
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | Fleet OH - Elec | Not assigned | 001/2021 | 13.41
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | Fleet OH - Elec | Not assigned | 002/2021 | 268.4
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | IT Device OH | Not assigned | 001/2021 | 10.29
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | IT Device OH | Not assigned | 002/2021 | 47.53
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 18.17
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 363.55
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 50.56
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 6.86
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | Payroll Taxes OH | Not assigned | 001/2021 | 35.72
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | Other | Payroll Taxes OH | Not assigned | 002/2021 | 164.83
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 3249.33
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 1744.94
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 261.25
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 220.03
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 1408.17
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 76.56
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 533.81
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 34.82
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 34.82
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 25.95
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 184.53
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1.77
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 12.3
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 639.49
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 1733.77
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 32.4
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 1522.8
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 3499.2
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Mapping | Not assigned | 002/2021 | 10.53
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Mapping | Not assigned | 003/2021 | 5.23
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 22.43
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 474.17
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 989.39
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.26
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 8.44
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 28.07
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | AFUDC-Equity | Not assigned | 001/2021 | 0.7
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | AFUDC-Equity | Not assigned | 002/2021 | 22.76
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | AFUDC-Equity | Not assigned | 003/2021 | 75.73
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Benefits OH | Not assigned | 001/2021 | 42.75
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Benefits OH | Not assigned | 002/2021 | 839.35
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Benefits OH | Not assigned | 003/2021 | 1598.97
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Building Service Overhead | Not assigned | 001/2021 | 7.34
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Building Service Overhead | Not assigned | 002/2021 | 144.06
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Building Service Overhead | Not assigned | 003/2021 | 289.01
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Capitalized A&G | Not assigned | 001/2021 | 41.01
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Capitalized A&G | Not assigned | 002/2021 | 866.89
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Capitalized A&G | Not assigned | 003/2021 | 1808.82
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Fleet OH - Elec | Not assigned | 001/2021 | 17.34
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Fleet OH - Elec | Not assigned | 002/2021 | 123.3
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1.18
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | IT Device OH | Not assigned | 001/2021 | 4.16
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | IT Device OH | Not assigned | 002/2021 | 81.75
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | IT Device OH | Not assigned | 003/2021 | 164.04
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Lodging | VICTOR T RASGADO | 004/2021 | 348.58
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Meals Expense | VICTOR T RASGADO | 004/2021 | 66.88
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 23.49
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 167
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1.6
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 7.37
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 383.01
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 1038.4
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Other Expenses | Not assigned | 003/2021 | 21.62
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Other Expenses | Not assigned | 004/2021 | -21.62
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Payroll Taxes OH | Not assigned | 001/2021 | 14.44
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Payroll Taxes OH | Not assigned | 002/2021 | 283.57
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Other | Payroll Taxes OH | Not assigned | 003/2021 | 568.92
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 1908.97
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 118.75
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 44.01
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Labor Internal | Design Overtime Services | Not assigned | 002/2021 | 523.68
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Labor Internal | Design Services | Not assigned | 002/2021 | 355.26
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 59.21
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 20.07
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 300.02
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 15.55
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 6.08
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 11.92
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 187.1
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.14
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4.13
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 7.97
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 0.39
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 11.15
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 21.51
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 23.82
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 371.18
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 4.1
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 63.71
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 21.8
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 342.07
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 13.41
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 200.46
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 2.31
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 36.15
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 18.17
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 271.53
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 9.31
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 8.05
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 125.4
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 3919.15
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 213.75
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 44.01
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 21.82
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 563.08
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 002/2021 | 257.63
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 34.82
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 7.4
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 282.42
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 12.3
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 15.55
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Labor Internal | Mapping | Not assigned | 002/2021 | 12.4
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 11.4
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 176.65
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.13
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 5.63
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | AFUDC-Borrowed | Not assigned | 003/2021 | -5.76
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | AFUDC-Equity | Not assigned | 001/2021 | 0.34
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | AFUDC-Equity | Not assigned | 002/2021 | 15.18
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | AFUDC-Equity | Not assigned | 003/2021 | -15.52
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | Benefits OH | Not assigned | 001/2021 | 20.7
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | Benefits OH | Not assigned | 002/2021 | 350.28
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | Building Service Overhead | Not assigned | 001/2021 | 3.55
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | Building Service Overhead | Not assigned | 002/2021 | 60.11
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | Canceled Capital Order | Not assigned | 003/2021 | -6984.88
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | Capitalized A&G | Not assigned | 001/2021 | 20.85
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | Capitalized A&G | Not assigned | 002/2021 | 322.95
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | Fleet OH - Elec | Not assigned | 001/2021 | 4.94
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | Fleet OH - Elec | Not assigned | 002/2021 | 188.7
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | IT Device OH | Not assigned | 001/2021 | 2.01
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | IT Device OH | Not assigned | 002/2021 | 34.12
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 6.69
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 255.6
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 7.37
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 9.31
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | Payroll Taxes OH | Not assigned | 001/2021 | 7
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W | Other | Payroll Taxes OH | Not assigned | 002/2021 | 118.32
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 3970.62
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 142.5
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 55.44
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 43.64
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 140.64
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 668.56
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 140.64
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 34.82
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 62.47
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 230.82
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 66.64
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 12.3
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 11.45
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 32.4
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Labor Internal | Mapping | Not assigned | 002/2021 | 12.34
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Labor Internal | Mapping | Not assigned | 003/2021 | 0.5
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 44.12
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 143.67
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 39.59
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.52
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 6.01
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 11.45
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.41
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | AFUDC-Equity | Not assigned | 002/2021 | 16.21
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | AFUDC-Equity | Not assigned | 003/2021 | 30.89
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Benefits OH | Not assigned | 001/2021 | 86.07
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Benefits OH | Not assigned | 002/2021 | 285.1
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Benefits OH | Not assigned | 003/2021 | 75.14
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Building Service Overhead | Not assigned | 001/2021 | 14.78
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Building Service Overhead | Not assigned | 002/2021 | 48.92
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Building Service Overhead | Not assigned | 003/2021 | 13.59
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Capitalized A&G | Not assigned | 001/2021 | 80.67
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Capitalized A&G | Not assigned | 002/2021 | 262.64
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Capitalized A&G | Not assigned | 003/2021 | 72.37
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Fleet OH - Elec | Not assigned | 001/2021 | 41.73
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Fleet OH - Elec | Not assigned | 002/2021 | 154.23
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Fleet OH - Elec | Not assigned | 003/2021 | 44.52
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | IT Device OH | Not assigned | 001/2021 | 8.39
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | IT Device OH | Not assigned | 002/2021 | 27.77
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | IT Device OH | Not assigned | 003/2021 | 7.72
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 56.54
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 208.91
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 60.31
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 7.37
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 6.86
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Payroll Taxes OH | Not assigned | 001/2021 | 29.07
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Payroll Taxes OH | Not assigned | 002/2021 | 96.32
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Other | Payroll Taxes OH | Not assigned | 003/2021 | 26.72
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 3089.11
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 380
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Labor Internal | Design Drafting Services | Not assigned | 001/2021 | 59.21
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Labor Internal | Design Drafting Services - Overtime | Not assigned | 001/2021 | 87.28
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 43.64
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 69.64
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 64.45
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 3.53
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 58.94
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 97.2
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Labor Internal | Mapping | Not assigned | 002/2021 | 10.41
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 71.89
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 2.1
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.82
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4.39
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 7.14
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | AFUDC-Equity | Not assigned | 001/2021 | 2.2
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | AFUDC-Equity | Not assigned | 002/2021 | 11.84
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | AFUDC-Equity | Not assigned | 003/2021 | 19.28
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | Benefits OH | Not assigned | 001/2021 | 133.69
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | Benefits OH | Not assigned | 002/2021 | 4.19
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | Building Service Overhead | Not assigned | 001/2021 | 22.94
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | Building Service Overhead | Not assigned | 002/2021 | 0.72
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | Capitalized A&G | Not assigned | 001/2021 | 131.44
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | Capitalized A&G | Not assigned | 002/2021 | 3.83
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | Fleet OH - Elec | Not assigned | 001/2021 | 43.06
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | Fleet OH - Elec | Not assigned | 002/2021 | 2.36
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | IT Device OH | Not assigned | 001/2021 | 13.01
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | IT Device OH | Not assigned | 002/2021 | 0.41
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 58.33
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 3.19
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 35.31
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | Payroll Taxes OH | Not assigned | 001/2021 | 45.16
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Other | Payroll Taxes OH | Not assigned | 002/2021 | 1.42
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Contract | Contracts | Not assigned | 002/2021 | 29786.32
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Contract | Gas Construction Contract | ENERGY EXPERTS INTERNATIONAL | 003/2021 | 10092.6
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Contract | Gas Construction Contract | ENERGY EXPERTS INTERNATIONAL | 004/2021 | -10092.6
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 259.2
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Administration | Not assigned | 001/2021 | 139.28
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Administration | Not assigned | 003/2021 | 139.28
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Administration | Not assigned | 004/2021 | 139.28
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Design Drafting Services | Not assigned | 003/2021 | 355.26
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 003/2021 | 1047.36
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 004/2021 | 319.17
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Drafting Doubletime | Not assigned | 003/2021 | 118.4
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 691.27
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 6898
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Electric Estimating | Not assigned | 004/2021 | 622.73
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 2443.84
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 37.23
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 37.23
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 221.99
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 121.87
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | GAS Activity Charge - Non-Type A | Not assigned | 002/2021 | 73.82
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 277.25
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 3943.37
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 49.21
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 78.43
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 412.77
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 648
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Management Services | Not assigned | 003/2021 | 523.84
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Management Services - OT | Not assigned | 003/2021 | 178.16
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Mapping | Not assigned | 002/2021 | 89.36
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Mapping | Not assigned | 003/2021 | 30.28
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 28.05
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 209.43
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 2584.68
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Materials | Electl & Electronic Equipment Component | Not assigned | 002/2021 | 9231.51
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Materials | Electrical Specialties | Not assigned | 002/2021 | 2159.31
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Materials | Material Burden | Not assigned | 002/2021 | 1663.06
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.29
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 41.59
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 119.65
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 0.79
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 112.23
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 322.87
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Benefits OH | Not assigned | 001/2021 | 47.73
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Benefits OH | Not assigned | 002/2021 | 754.54
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Benefits OH | Not assigned | 003/2021 | 4833.3
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Building Service Overhead | Not assigned | 001/2021 | 8.19
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Building Service Overhead | Not assigned | 002/2021 | 129.5
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Building Service Overhead | Not assigned | 003/2021 | 873.56
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Capitalized A&G | Not assigned | 001/2021 | 51.28
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Capitalized A&G | Not assigned | 002/2021 | 410.05
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Capitalized A&G | Not assigned | 003/2021 | 4725.32
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Cost Adjustments | Not assigned | 002/2021 | 4451.69
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 185.24
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 2634.73
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Fleet OH - Gas | Not assigned | 002/2021 | 22.86
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | IT Device OH | Not assigned | 001/2021 | 4.65
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | IT Device OH | Not assigned | 002/2021 | 73.5
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | IT Device OH | Not assigned | 003/2021 | 495.83
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Minor Material OH | Not assigned | 002/2021 | 928.13
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 250.92
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 3568.81
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 29.47
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 46.97
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 247.22
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 40.96
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 16.13
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 254.93
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 1719.67
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Contract | Contracts | Not assigned | 002/2021 | 53362.25
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Contract | Electric Construction Contract | C&C UTILITY INC | 002/2021 | 3505
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Contract | Electric Construction Contract | C&C UTILITY INC | 003/2021 | -3505
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Contract | Electric Construction Contract | CHINCHEN ELECTRIC | 002/2021 | 3505
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Contract | Electric Construction Contract | CHINCHEN ELECTRIC | 003/2021 | -1500
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Contract | Electric Construction Contract | CHINCHEN ELECTRIC | 004/2021 | -2005
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 6644.17
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 003/2021 | 18994.92
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 004/2021 | -3186.24
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Contract | Gas Construction Contract | VETERAN POWER INC | 002/2021 | 920179
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Contract | Gas Construction Contract | VETERAN POWER INC | 003/2021 | 1623013.26
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Contract | Gas Construction Contract | VETERAN POWER INC | 004/2021 | -1623013.26
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Administration | Not assigned | 001/2021 | 34.82
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Administration | Not assigned | 002/2021 | 139.28
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Administration | Not assigned | 004/2021 | 139.28
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 97.81
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Construction | Not assigned | 001/2021 | 1042.3
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Construction | Not assigned | 002/2021 | 2439.22
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Construction | Not assigned | 003/2021 | 2456.85
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 665.22
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 1663.05
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 221.74
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Design Drafting Services | Not assigned | 001/2021 | 532.89
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 001/2021 | 261.84
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 002/2021 | 218.2
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Drafting Doubletime | Not assigned | 001/2021 | 355.2
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 1238.42
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 414.47
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 349.12
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 76.56
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.46
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 397.69
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Environmental Services | Not assigned | 003/2021 | 104.46
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | GAS Activity Charge - Non-Type A | Not assigned | 002/2021 | 132.24
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 973.89
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 2997.69
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 2724.63
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 12.3
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 202.01
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 157.58
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Indirect Labor - Gas | Not assigned | 002/2021 | 74.43
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Maintain & Operate Services | Not assigned | 004/2021 | 76.13
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Manage L&EM | Not assigned | 002/2021 | 34.82
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Manage L&EM | Not assigned | 003/2021 | 243.74
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Mapping | Not assigned | 001/2021 | 15.37
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Mapping | Not assigned | 002/2021 | 2998.51
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Mapping | Not assigned | 003/2021 | 4935.12
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 585.61
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1937.51
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1708.54
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Labor Internal | Warehouse Services | Not assigned | 002/2021 | 787.74
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Materials | Chemicals,Cleaners,Compounds & Lab Suppl | Not assigned | 003/2021 | 12.21
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 002/2021 | 330.24
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 003/2021 | 199427.05
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Materials | Construction Supplies | Not assigned | 003/2021 | 257.33
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Materials | Electl & Electronic Equipment Component | Not assigned | 002/2021 | 16538.27
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Materials | Electl & Electronic Equipment Component | Not assigned | 003/2021 | 52130.39
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Materials | Electrical Specialties | OLDCASTLE PRECAST INC | 002/2021 | 63245.15
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Materials | Electrical Specialties | OLDCASTLE PRECAST INC | 003/2021 | 68574.71
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Materials | Electrical Specialties | Not assigned | 002/2021 | 49192.53
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Materials | Electrical Specialties | Not assigned | 003/2021 | 58313.06
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Materials | Material Burden | Not assigned | 002/2021 | 18878.7
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Materials | Material Burden | Not assigned | 003/2021 | 55321.59
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Materials | Office Supplies Expense | BRYAN C ANDERSON | 003/2021 | 197.8
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 003/2021 | 35.83
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 7.06
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 952.07
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3573.48
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 19.05
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2569.09
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 9642.72
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Benefits OH | Not assigned | 001/2021 | 1167.82
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Benefits OH | Not assigned | 002/2021 | 7714.4
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Benefits OH | Not assigned | 003/2021 | 13408.28
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Building Service Overhead | Not assigned | 001/2021 | 200.42
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Building Service Overhead | Not assigned | 002/2021 | 1324.02
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Building Service Overhead | Not assigned | 003/2021 | 2423.47
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Capitalized A&G | Not assigned | 001/2021 | 1070.59
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Capitalized A&G | Not assigned | 002/2021 | 3880.91
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Capitalized A&G | Not assigned | 003/2021 | 3123.55
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Cash Discount earned | OLDCASTLE PRECAST INC | 003/2021 | -2636.4
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Cost Adjustments | Not assigned | 002/2021 | 7975.22
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 650.69
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 2002.87
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1820.45
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Fleet OH - Gas | Not assigned | 002/2021 | 104.66
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | IT Device OH | Not assigned | 001/2021 | 113.75
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | IT Device OH | Not assigned | 002/2021 | 751.47
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | IT Device OH | Not assigned | 003/2021 | 1375.47
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Minor Material OH | Not assigned | 002/2021 | 10535.94
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Minor Material OH | Not assigned | 003/2021 | 30876.58
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 881.39
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 2712.95
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 2465.85
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 7.37
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 120.99
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 94.37
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 187.5
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 394.57
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 2606.33
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 4770.65
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Construction Inspection | GULF INTERSTATE FIELD SERVICES INC | 003/2021 | 34401.03
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Construction Inspection | GULF INTERSTATE FIELD SERVICES INC | 004/2021 | -25021.27
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Contracts | BESS TESTLAB INC | 003/2021 | 17379.78
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Contracts | BRAY TRUCKING INC | 002/2021 | 29035.97
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Contracts | BRAY TRUCKING INC | 003/2021 | 134109.67
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Contracts | BRAY TRUCKING INC | 004/2021 | -80000
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Contracts | DENBESTE WATER SOLUTIONS INC | 003/2021 | 4719
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Contracts | DISCOVERY HYDROVAC LLC | 002/2021 | 7830
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Contracts | DISCOVERY HYDROVAC LLC | 003/2021 | 10210
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Contracts | GULF INTERSTATE FIELD SERVICES INC | 003/2021 | 214.19
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Contracts | GULF INTERSTATE FIELD SERVICES INC | 004/2021 | -214.19
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Contracts | Not assigned | 002/2021 | 84490.71
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Electric Construction Contract | C&C UTILITY INC | 002/2021 | 37000
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Electric Construction Contract | C&C UTILITY INC | 003/2021 | -37000
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Electric Construction Contract | CHINCHEN ELECTRIC | 002/2021 | 37000
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Electric Construction Contract | CHINCHEN ELECTRIC | 003/2021 | -37000
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 003/2021 | 4715.64
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Electric Construction Contract | PRO ENERGY SERVICES GROUP LLC | 004/2021 | -1593.12
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 199.62
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 392.59
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 1500
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -1500
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Environmental Contract | JOHN C GARCIA | 003/2021 | 13622.59
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Gas Construction Contract | NORTHSTATE AGGREGATE INC | 003/2021 | 56820.52
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Gas Construction Contract | NORTHSTATE AGGREGATE INC | 004/2021 | -285.5
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | T&D Sewer Inspection | Not assigned | 003/2021 | 5256
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | T&D Sewer Inspection | Not assigned | 004/2021 | -5256
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Traffic Control Contracts | ALMENDARIZ CONSULTING INC | 003/2021 | 75081
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Traffic Control Contracts | ALMENDARIZ CONSULTING INC | 004/2021 | -40000
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Traffic Control Contracts | RADER EXCAVATING INC | 003/2021 | 227339
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Contract | Traffic Control Contracts | RADER EXCAVATING INC | 004/2021 | -43250.02
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor External | Consulting Services - Engineering | KLEINFELDER INC | 002/2021 | 2000
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor External | Consulting Services - Engineering | KLEINFELDER INC | 003/2021 | 5000
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor External | Consulting Services - Engineering | KLEINFELDER INC | 004/2021 | -7000
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor External | Consulting Services - Environmental Perm | KLEINFELDER INC | 003/2021 | 3437.29
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Account Services | Not assigned | 003/2021 | 129.68
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 32.4
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Administration | Not assigned | 002/2021 | 783.45
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Administration | Not assigned | 003/2021 | 208.92
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Administration | Not assigned | 004/2021 | 139.28
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 48.91
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Analyst Services | Not assigned | 002/2021 | 111.38
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Analyst Services | Not assigned | 003/2021 | 111.38
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Construction | Not assigned | 002/2021 | 57750.59
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Construction | Not assigned | 003/2021 | 160693.78
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Construction | Not assigned | 004/2021 | 207.17
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Construction Doubletime Services | Not assigned | 002/2021 | 1793.55
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Construction Doubletime Services | Not assigned | 003/2021 | 15435.4
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Construction Doubletime Services | Not assigned | 004/2021 | 652.2
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 33770.43
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 153748
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Construction Overtime Services | Not assigned | 004/2021 | 3560.48
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Design Drafting Services | Not assigned | 001/2021 | 532.89
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Design Drafting Services | Not assigned | 002/2021 | 2901.29
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Design Drafting Services | Not assigned | 003/2021 | 473.68
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 002/2021 | 1527.4
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 003/2021 | 174.56
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Drafting Doubletime | Not assigned | 002/2021 | 1184
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 1960.84
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Engineering Services | Not assigned | 002/2021 | 5695.68
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Engineering Services | Not assigned | 003/2021 | 20884.17
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Engineering Services - OT | Not assigned | 002/2021 | 1902.6
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Engineering Services - OT | Not assigned | 003/2021 | 5898.06
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 229.68
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.46
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 629.68
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 417.84
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 800.86
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Environmental Services | Not assigned | 002/2021 | 644.17
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Environmental Services | Not assigned | 003/2021 | 226.33
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | GAS Activity Charge - Non-Type A | Not assigned | 002/2021 | 209.39
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Hours - Straight Time | Not assigned | 002/2021 | 429.71
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 33.57
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 180.65
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 3940.35
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1467.79
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 1060.44
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 574.48
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Indirect Labor - Gas | Not assigned | 002/2021 | 36948.93
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 129039.37
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Indirect Labor - IT | Not assigned | 002/2021 | 160.28
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Inspection Services DT | Not assigned | 002/2021 | 980.05
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Inspection Services OT | Not assigned | 002/2021 | 2421.44
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 194.4
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Maintain & Operate Services | Not assigned | 002/2021 | 199.3
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Manage L&EM | Not assigned | 002/2021 | 139.28
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Manage L&EM | Not assigned | 003/2021 | 278.56
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Management Services | Not assigned | 003/2021 | 496.8
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Mapping | Not assigned | 002/2021 | 1431.89
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Mapping | Not assigned | 003/2021 | 3607.07
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 107.32
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 23600.02
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 73056.82
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Materials | Automotive | CODY S COPELIN | 003/2021 | 273.31
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 002/2021 | 2078.1
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 003/2021 | 23543.17
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Materials | Construction Supplies | Not assigned | 003/2021 | 817.29
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Materials | Electl & Electronic Equipment Component | Not assigned | 002/2021 | 131199.34
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Materials | Electl & Electronic Equipment Component | Not assigned | 003/2021 | 60266.68
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Materials | Electrical Specialties | OLDCASTLE PRECAST INC | 002/2021 | 58979.19
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Materials | Electrical Specialties | Not assigned | 002/2021 | 109001.93
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Materials | Electrical Specialties | Not assigned | 003/2021 | 13395.65
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Materials | Material Burden | Not assigned | 002/2021 | 44223.08
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Materials | Material Burden | Not assigned | 003/2021 | 14391.14
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Materials | Office Supplies Expense | BRYAN C ANDERSON | 003/2021 | -51.44
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 1591.95
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Materials | Purchasing Card | BRYAN C ANDERSON | 003/2021 | 407.56
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Materials | Purchasing Card | CODY S COPELIN | 002/2021 | 690.86
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Materials | Purchasing Card | CODY S COPELIN | 003/2021 | 6355.76
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Materials | Purchasing Card | ROBERT TENNIGKEIT | 003/2021 | 1694.59
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1.3
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 795.11
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3141.19
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3.5
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2145.54
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 8476.23
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Benefits OH | Not assigned | 001/2021 | 214.41
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Benefits OH | Not assigned | 002/2021 | 62610.84
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Benefits OH | Not assigned | 003/2021 | 164566.95
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Building Service Overhead | Not assigned | 001/2021 | 36.8
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Building Service Overhead | Not assigned | 002/2021 | 10745.7
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Building Service Overhead | Not assigned | 003/2021 | 29744.21
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Capitalized A&G | Not assigned | 001/2021 | 196.21
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Capitalized A&G | Not assigned | 002/2021 | 43222.75
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Capitalized A&G | Not assigned | 003/2021 | 133745.59
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Cash Discount earned | ALMENDARIZ CONSULTING INC | 003/2021 | -701.62
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Cash Discount earned | BESS TESTLAB INC | 003/2021 | -347.6
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Cash Discount earned | BRAY TRUCKING INC | 003/2021 | -1662.91
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Cash Discount earned | DISCOVERY HYDROVAC LLC | 003/2021 | -360.8
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Cash Discount earned | NORTHSTATE AGGREGATE INC | 004/2021 | -1457.74
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Cash Discount earned | OLDCASTLE PRECAST INC | 003/2021 | -1179.58
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Cash Discount earned | RADER EXCAVATING INC | 003/2021 | -1235.4
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Cash Discount earned | UNITED RENTALS (NORTH AMERICA) INC | 003/2021 | -1140.58
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Cost Adjustments | Not assigned | 002/2021 | 12627.5
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 120.7
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 2632.69
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 980.69
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Fleet OH - Gas | Not assigned | 002/2021 | 31693.05
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 110611.27
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | IT Device OH | Not assigned | 001/2021 | 20.88
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | IT Device OH | Not assigned | 002/2021 | 6098.88
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | IT Device OH | Not assigned | 003/2021 | 16881.87
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Land Acquisition Services | INTERWEST CONSULTING GROUP INC | 003/2021 | 2761.6
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Land Acquisition Services | INTERWEST CONSULTING GROUP INC | 004/2021 | -1535.35
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Lodging | MARTHA VILLARREAL | 002/2021 | 1597.9
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Lodging | MARTHA VILLARREAL | 003/2021 | 5438.17
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Meals Expense | Not assigned | 003/2021 | 14.15
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Meals Expense | Not assigned | 004/2021 | -14.15
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Minor Material OH | Not assigned | 002/2021 | 24726.07
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Minor Material OH | Not assigned | 003/2021 | 8609.77
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 163.49
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 3566.06
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1328.37
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 635.12
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 344.07
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 56775.28
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 198150.27
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Operation Mgmt & Support - IT | Not assigned | 002/2021 | 68.96
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 72.44
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 21153.26
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 58552.35
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Other | Rents | UNITED RENTALS (NORTH AMERICA) INC | 003/2021 | 72844.24
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 259.2
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 340.2
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Labor Internal | Acquisition - Misc | Not assigned | 004/2021 | 129.6
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 154.02
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 91.58
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 197.5
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 64.8
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 52.2
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 157.57
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.55
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.81
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.48
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 7.58
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Other | Benefits OH | Not assigned | 002/2021 | 88.82
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Other | Benefits OH | Not assigned | 003/2021 | 267.25
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.25
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Other | Building Service Overhead | Not assigned | 003/2021 | 48.31
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Other | Capitalized A&G | Not assigned | 002/2021 | 95.44
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Other | Capitalized A&G | Not assigned | 003/2021 | 288.07
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Other | IT Device OH | Not assigned | 002/2021 | 8.66
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Other | IT Device OH | Not assigned | 003/2021 | 27.43
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 54.85
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 118.29
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.02
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 95.09
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 38.28
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 12.98
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 7.71
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.09
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.25
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | Benefits OH | Not assigned | 003/2021 | 14.62
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | Building Service Overhead | Not assigned | 003/2021 | 2.64
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | Capitalized A&G | Not assigned | 003/2021 | 14.09
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | Fleet OH - Elec | Not assigned | 003/2021 | 8.67
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | IT Device OH | Not assigned | 003/2021 | 1.49
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 11.74
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE | Other | Payroll Taxes OH | Not assigned | 003/2021 | 5.19
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 219.22
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -219.22
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | 24570
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 004/2021 | -24570
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 003/2021 | 722.28
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 004/2021 | -722.28
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 2781.04
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 001/2021 | 47.5
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 142.5
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Labor Internal | Account Services | Not assigned | 003/2021 | 29.94
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 562.56
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.45
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 139.28
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 7.75
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 190.76
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 2.97
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.24
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 335.38
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 810
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Labor Internal | Mapping | Not assigned | 001/2021 | 0.14
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Labor Internal | Mapping | Not assigned | 002/2021 | 8.77
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 113.33
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1.77
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 212.2
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1.41
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 5.31
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 29.78
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | AFUDC-Equity | Not assigned | 001/2021 | 3.79
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | AFUDC-Equity | Not assigned | 002/2021 | 14.32
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | AFUDC-Equity | Not assigned | 003/2021 | 80.35
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | Benefits OH | Not assigned | 001/2021 | 226.41
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | Benefits OH | Not assigned | 002/2021 | 3.54
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | Benefits OH | Not assigned | 003/2021 | 345.4
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | Building Service Overhead | Not assigned | 001/2021 | 38.84
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | Building Service Overhead | Not assigned | 002/2021 | 0.6
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | Building Service Overhead | Not assigned | 003/2021 | 62.43
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | Capitalized A&G | Not assigned | 001/2021 | 207.18
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | Capitalized A&G | Not assigned | 002/2021 | 3.23
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | Capitalized A&G | Not assigned | 003/2021 | 387.95
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | Fleet OH - Elec | Not assigned | 001/2021 | 127.45
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1.99
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.86
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | IT Device OH | Not assigned | 001/2021 | 22.05
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | IT Device OH | Not assigned | 002/2021 | 0.35
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | IT Device OH | Not assigned | 003/2021 | 35.44
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 172.63
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 2.69
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 22.84
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 200.87
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | Payroll Taxes OH | Not assigned | 001/2021 | 76.49
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | Payroll Taxes OH | Not assigned | 002/2021 | 1.2
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Other | Payroll Taxes OH | Not assigned | 003/2021 | 122.9
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 1926.32
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 166.25
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 55.44
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Labor Internal | Design Overtime Services | Not assigned | 002/2021 | 87.28
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Labor Internal | Design Services | Not assigned | 002/2021 | 473.68
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 003/2021 | 751.94
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 34.82
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 192.3
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 273.87
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 12.3
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 11.45
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 32.4
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 6.28
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.5
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 7.01
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 120.77
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 162.71
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.07
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 3.24
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 8.29
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 0.2
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 8.75
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 22.37
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | Benefits OH | Not assigned | 001/2021 | 11.94
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | Benefits OH | Not assigned | 002/2021 | 239.34
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | Benefits OH | Not assigned | 003/2021 | 308.67
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 2.05
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 41.07
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 55.8
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 12.82
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 220.79
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 297.45
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 128.48
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 182.98
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | IT Device OH | Not assigned | 001/2021 | 1.16
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | IT Device OH | Not assigned | 002/2021 | 23.31
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | IT Device OH | Not assigned | 003/2021 | 31.67
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 174.03
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 247.86
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 7.37
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 6.86
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 4.03
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 80.87
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 109.84
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 002/2021 | 219.22
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | BLACK & VEATCH CONSTRUCTION INC | 003/2021 | -219.22
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 3163.46
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 403.75
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 55.44
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Labor Internal | Design Drafting Services | Not assigned | 001/2021 | 236.84
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 2411.64
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 153.12
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 002/2021 | 644.52
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 208.92
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 80.29
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1039.67
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 70.87
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 85.25
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 32.4
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 10.7
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.5
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 96.31
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 617.66
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 42.11
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1.09
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 12.61
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 23.39
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2.93
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 34.04
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 63.11
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | Benefits OH | Not assigned | 001/2021 | 177.99
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | Benefits OH | Not assigned | 002/2021 | 1233.96
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | Benefits OH | Not assigned | 003/2021 | 79.89
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | Building Service Overhead | Not assigned | 001/2021 | 30.56
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 211.78
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 14.45
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | Capitalized A&G | Not assigned | 001/2021 | 176.05
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 1129.22
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 76.97
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 53.64
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 694.64
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 47.35
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | IT Device OH | Not assigned | 001/2021 | 17.34
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | IT Device OH | Not assigned | 002/2021 | 120.19
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | IT Device OH | Not assigned | 003/2021 | 8.2
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 72.66
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 940.91
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 64.14
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 51.07
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 60.15
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 416.89
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 28.43
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Labor Internal | Construction | Not assigned | 002/2021 | 670.05
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 229.19
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 68.68
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 389.2
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 194.4
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 1101.6
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Labor Internal | Mapping | Not assigned | 002/2021 | 6.03
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 175.31
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 221.86
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.06
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 6.43
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 5.55
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 17.34
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Other | Benefits OH | Not assigned | 002/2021 | 338.65
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Other | Benefits OH | Not assigned | 003/2021 | 358.5
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Other | Building Service Overhead | Not assigned | 002/2021 | 58.12
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Other | Building Service Overhead | Not assigned | 003/2021 | 64.79
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Other | Capitalized A&G | Not assigned | 002/2021 | 320.51
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Other | Capitalized A&G | Not assigned | 003/2021 | 405.61
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 153.14
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Other | IT Device OH | Not assigned | 002/2021 | 32.98
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Other | IT Device OH | Not assigned | 003/2021 | 36.78
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 207.42
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 41.14
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 233.1
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 114.41
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 127.55
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 105.06
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Labor Internal | Construction | Not assigned | 002/2021 | 670.05
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 229.19
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.11
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Labor Internal | Mapping | Not assigned | 002/2021 | 6.03
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.32
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 136.16
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 0.06
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.64
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3.37
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 4.44
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 9.1
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Other | Benefits OH | Not assigned | 002/2021 | 272.03
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Other | Benefits OH | Not assigned | 003/2021 | 0.13
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Other | Building Service Overhead | Not assigned | 002/2021 | 46.69
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.02
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Other | Capitalized A&G | Not assigned | 002/2021 | 248.93
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Other | Capitalized A&G | Not assigned | 003/2021 | 0.12
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 153.14
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.07
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Other | IT Device OH | Not assigned | 002/2021 | 26.49
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Other | IT Device OH | Not assigned | 003/2021 | 0.02
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 207.42
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.1
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 91.91
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 0.04
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 002/2021 | 31647.51
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | -7077.51
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 004/2021 | -24570
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 421.14
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 218.49
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 136.41
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 24.92
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 45.89
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 67.25
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 123.82
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Other | Benefits OH | Not assigned | 003/2021 | 255.06
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Other | Building Service Overhead | Not assigned | 003/2021 | 46.09
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Other | Capitalized A&G | Not assigned | 003/2021 | 249.38
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 145.98
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Other | IT Device OH | Not assigned | 003/2021 | 26.17
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 197.73
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 90.75
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 002/2021 | 28447.2
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | -3877.2
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 004/2021 | -24570
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Labor Internal | Account Services | Not assigned | 003/2021 | 49.23
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 34.82
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 12.75
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 103.88
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 259.2
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 114.11
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 22.4
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 43
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 60.45
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 116.02
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Other | Benefits OH | Not assigned | 003/2021 | 194.27
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Other | Building Service Overhead | Not assigned | 003/2021 | 35.12
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Other | Capitalized A&G | Not assigned | 003/2021 | 208.63
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Other | IT Device OH | Not assigned | 003/2021 | 19.94
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 62.22
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 69.13
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Contract | Contracts | Not assigned | 003/2021 | 327.85
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 71.25
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Construction | Not assigned | 002/2021 | 744.51
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Construction | Not assigned | 003/2021 | 670.05
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Design Overtime Services | Not assigned | 003/2021 | 2880.24
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Design Services | Not assigned | 003/2021 | 1243.43
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Design Services Double Time | Not assigned | 003/2021 | 1006.4
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 2605.24
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 5624.95
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Electric Estimating Doubletime | Not assigned | 002/2021 | 2249.6
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Electric Estimating Doubletime | Not assigned | 003/2021 | 6808
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 2269.28
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 5716.84
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 914.5
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1675.13
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 278.56
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 626.76
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 139.28
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 2979.76
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 8689.34
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 98.42
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 278.66
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 162
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Mapping | Not assigned | 002/2021 | 6.7
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Mapping | Not assigned | 003/2021 | 7.23
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1826.37
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 5321.19
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Other | Benefits OH | Not assigned | 002/2021 | 3632.06
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Other | Benefits OH | Not assigned | 003/2021 | 10049.68
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Other | Building Service Overhead | Not assigned | 002/2021 | 623.35
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Other | Building Service Overhead | Not assigned | 003/2021 | 1816.39
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Other | Capitalized A&G | Not assigned | 002/2021 | 3338.98
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Other | Capitalized A&G | Not assigned | 003/2021 | 9728.22
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1990.9
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 5805.71
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Other | IT Device OH | Not assigned | 002/2021 | 353.8
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Other | IT Device OH | Not assigned | 003/2021 | 1030.93
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 2696.73
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 7863.98
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 58.94
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 166.9
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 1227.12
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 3575.67
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 199.62
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 23.75
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Labor External | Consulting Services - Environmental Perm | BENDER ROSENTHAL INC | 003/2021 | 30
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 110.87
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 223.35
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 409.48
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 75.72
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 138.81
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 38.18
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 45.79
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 129.6
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 1.76
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 44.98
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 108.57
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 22.68
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.54
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.36
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 4.1
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 1.47
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6.36
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 11.06
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | Benefits OH | Not assigned | 001/2021 | 89.88
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 209.18
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 43.03
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | Building Service Overhead | Not assigned | 001/2021 | 15.42
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 35.9
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 7.78
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | Capitalized A&G | Not assigned | 001/2021 | 82.24
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 198.49
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 41.47
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 50.59
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 92.75
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 25.51
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | IT Device OH | Not assigned | 001/2021 | 8.76
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | IT Device OH | Not assigned | 002/2021 | 20.37
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 4.41
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 68.52
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 125.63
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 34.55
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 27.42
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 30.36
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 70.67
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 15.31
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 199.62
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 3907.86
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 872.8
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 148.9
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 409.48
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 50.48
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 138.81
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1620.84
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.6
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 29.99
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 82.47
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 962.94
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.36
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.72
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 14.43
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | AFUDC-Equity | Not assigned | 001/2021 | 0.98
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 4.64
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 38.93
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | Benefits OH | Not assigned | 001/2021 | 59.91
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | Benefits OH | Not assigned | 002/2021 | 164.75
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | Benefits OH | Not assigned | 003/2021 | 1826.72
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | Building Service Overhead | Not assigned | 001/2021 | 10.28
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 28.28
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 330.17
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | Capitalized A&G | Not assigned | 001/2021 | 54.82
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 150.77
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 1760.46
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 33.73
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 92.75
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1082.96
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | IT Device OH | Not assigned | 001/2021 | 5.83
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | IT Device OH | Not assigned | 002/2021 | 16.04
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | IT Device OH | Not assigned | 003/2021 | 187.39
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 45.68
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 125.63
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1466.89
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 20.24
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 55.67
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 649.95
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 199.62
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 1108.7
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 003/2021 | 21.82
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 11072.31
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 916.44
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 148.9
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 707.28
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1042.31
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 50.48
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 239.77
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 4804.35
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Labor Internal | Mapping | Not assigned | 003/2021 | 10.58
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 29.99
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 142.45
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 2854.27
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.36
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.44
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 38.56
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 0.98
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6.6
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 104.06
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | Benefits OH | Not assigned | 001/2021 | 59.91
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | Benefits OH | Not assigned | 002/2021 | 284.57
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | Benefits OH | Not assigned | 003/2021 | 5414.59
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | Building Service Overhead | Not assigned | 001/2021 | 10.28
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 48.84
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 978.64
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | Capitalized A&G | Not assigned | 001/2021 | 54.82
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 260.42
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 5218.18
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 33.73
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 160.2
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 3209.99
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | IT Device OH | Not assigned | 001/2021 | 5.83
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | IT Device OH | Not assigned | 002/2021 | 27.72
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | IT Device OH | Not assigned | 003/2021 | 555.43
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 45.68
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 216.99
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 4348.01
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 20.24
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 96.14
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 1926.49
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 199.62
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Labor Internal | Account Services | Not assigned | 003/2021 | 16.41
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 1125
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 610.96
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 148.9
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 632.83
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 4.25
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 50.48
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 214.53
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 664.41
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.6
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 29.99
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 127.45
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 398.02
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.36
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.26
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 8.72
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | AFUDC-Equity | Not assigned | 001/2021 | 0.98
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6.11
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 23.54
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | Benefits OH | Not assigned | 001/2021 | 59.91
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | Benefits OH | Not assigned | 002/2021 | 254.61
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | Benefits OH | Not assigned | 003/2021 | 753.22
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | Building Service Overhead | Not assigned | 001/2021 | 10.28
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 43.7
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 136.14
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | Capitalized A&G | Not assigned | 001/2021 | 54.82
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 233.01
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 727.68
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 33.73
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 143.34
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 443.92
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | IT Device OH | Not assigned | 001/2021 | 5.83
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | IT Device OH | Not assigned | 002/2021 | 24.8
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | IT Device OH | Not assigned | 003/2021 | 77.27
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 45.68
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 194.15
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 601.29
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 20.24
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 86.04
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 267.98
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Contract | Contracts | Not assigned | 002/2021 | 27225.64
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Administration | Not assigned | 001/2021 | 208.92
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Administration | Not assigned | 003/2021 | 139.28
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 631.85
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 37.23
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 37.23
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 202.9
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 121.87
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | GAS Activity Charge - Non-Type A | Not assigned | 002/2021 | 67.47
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 254.51
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 12.62
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 135.32
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 96.28
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 116.87
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Manage L&EM | Not assigned | 001/2021 | 174.1
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Manage L&EM | Not assigned | 002/2021 | 69.64
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Manage L&EM | Not assigned | 003/2021 | 69.64
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Mapping | Not assigned | 002/2021 | 81.68
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 77.14
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 206.1
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 80.73
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Materials | Electl & Electronic Equipment Component | Not assigned | 002/2021 | 8437.89
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Materials | Electrical Specialties | Not assigned | 002/2021 | 1973.68
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Materials | Material Burden | Not assigned | 002/2021 | 1520.09
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.81
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 39.25
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 77.73
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 2.19
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 105.92
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 209.75
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Benefits OH | Not assigned | 001/2021 | 131.28
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Benefits OH | Not assigned | 002/2021 | 714.81
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Benefits OH | Not assigned | 003/2021 | 130.72
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Building Service Overhead | Not assigned | 001/2021 | 22.53
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Building Service Overhead | Not assigned | 002/2021 | 122.68
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Building Service Overhead | Not assigned | 003/2021 | 23.62
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Capitalized A&G | Not assigned | 001/2021 | 141.03
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Capitalized A&G | Not assigned | 002/2021 | 401.62
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Capitalized A&G | Not assigned | 003/2021 | 147.59
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Cost Adjustments | Not assigned | 002/2021 | 4068.99
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 170.04
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 8.43
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Fleet OH - Gas | Not assigned | 002/2021 | 20.9
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | IT Device OH | Not assigned | 001/2021 | 12.78
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | IT Device OH | Not assigned | 002/2021 | 69.63
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | IT Device OH | Not assigned | 003/2021 | 13.41
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Minor Material OH | Not assigned | 002/2021 | 848.34
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 230.33
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 11.42
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 81.05
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 57.67
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 70
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 37.43
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 44.34
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 241.5
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 46.5
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Contract | Construction Inspection | GULF INTERSTATE FIELD SERVICES INC | 003/2021 | 6132.46
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Contract | Construction Inspection | GULF INTERSTATE FIELD SERVICES INC | 004/2021 | -6132.46
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Contract | Construction Management Contracts | TRC SOLUTIONS INC | 003/2021 | 802.75
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Contract | Contracts | DISCOVERY HYDROVAC LLC | 003/2021 | 24265
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Contract | Contracts | Not assigned | 002/2021 | 33241.77
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Contract | Electric Construction Contract | NORTHSTATE AGGREGATE INC | 003/2021 | 115887.31
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 2057.18
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 252.37
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -252.37
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 1500
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -1500
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Contract | Traffic Control Contracts | BASIN ENTERPRISES INC | 003/2021 | 57795.22
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Contract | Traffic Control Contracts | BASIN ENTERPRISES INC | 004/2021 | 34865.42
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 95
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor External | Consulting Services - Environmental Perm | KLEINFELDER INC | 003/2021 | 1686.79
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Administration | Not assigned | 001/2021 | 34.82
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Administration | Not assigned | 002/2021 | 470.07
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Administration | Not assigned | 004/2021 | 139.28
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Analyst Services | Not assigned | 002/2021 | 111.38
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Analyst Services | Not assigned | 003/2021 | 111.38
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Construction | Not assigned | 002/2021 | 1489
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Construction | Not assigned | 003/2021 | 82422.94
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Construction | Not assigned | 004/2021 | 14438.65
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Construction Doubletime Services | Not assigned | 003/2021 | 14955.95
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Construction Doubletime Services | Not assigned | 004/2021 | 652.62
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 72308.3
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Construction Overtime Services | Not assigned | 004/2021 | 7130.68
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Design Drafting Services | Not assigned | 002/2021 | 888.15
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 002/2021 | 392.76
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 771.47
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Engineering Doubletime | Not assigned | 003/2021 | 5581.54
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Engineering Services | Not assigned | 003/2021 | 1853.6
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Engineering Services - OT | Not assigned | 003/2021 | 6731.94
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 37.23
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 113.79
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 247.74
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 348.2
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 1183.88
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 34.82
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Environmental Services | Not assigned | 003/2021 | 121.87
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | GAS Activity Charge - Non-Type A | Not assigned | 002/2021 | 82.38
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1251.5
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1619.34
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 12.3
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 415.97
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 537.57
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 66099.69
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Inspection Services | Not assigned | 003/2021 | 614.65
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Inspection Services DT | Not assigned | 003/2021 | 172.95
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Inspection Services OT | Not assigned | 003/2021 | 735.08
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Manage L&EM | Not assigned | 003/2021 | 104.46
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Mapping | Not assigned | 002/2021 | 113.13
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Mapping | Not assigned | 003/2021 | 1982.81
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 7.01
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 980.65
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 38063.63
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Materials | Chemicals,Cleaners,Compounds & Lab Suppl | Not assigned | 003/2021 | 2855.63
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Materials | Electl & Electronic Equipment Component | Not assigned | 002/2021 | 10302.44
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Materials | Electl & Electronic Equipment Component | Not assigned | 003/2021 | 51063.42
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Materials | Electrical Specialties | OLDCASTLE PRECAST INC | 003/2021 | 44768.5
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Materials | Electrical Specialties | Not assigned | 002/2021 | 2409.8
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Materials | Electrical Specialties | Not assigned | 003/2021 | 48659.36
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Materials | Material Burden | Not assigned | 002/2021 | 1855.99
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Materials | Material Burden | Not assigned | 003/2021 | 21583.99
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 488.62
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 0.07
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 54.63
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 944.04
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | AFUDC-Equity | Not assigned | 001/2021 | 0.2
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 147.42
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2547.41
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Benefits OH | Not assigned | 001/2021 | 11.94
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Benefits OH | Not assigned | 002/2021 | 2278.81
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Benefits OH | Not assigned | 003/2021 | 88013.41
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Building Service Overhead | Not assigned | 001/2021 | 2.05
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Building Service Overhead | Not assigned | 002/2021 | 391.08
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Building Service Overhead | Not assigned | 003/2021 | 15907.76
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Capitalized A&G | Not assigned | 001/2021 | 12.82
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Capitalized A&G | Not assigned | 002/2021 | 1823.15
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Capitalized A&G | Not assigned | 003/2021 | 69588.01
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Cash Discount earned | DISCOVERY HYDROVAC LLC | 004/2021 | -65.8
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Cash Discount earned | NORTHSTATE AGGREGATE INC | 004/2021 | -1903.17
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Cash Discount earned | OLDCASTLE PRECAST INC | 003/2021 | -895.37
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Cost Adjustments | Not assigned | 002/2021 | 4968.12
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 836.19
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1081.95
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Fleet OH - Gas | Not assigned | 002/2021 | 25.51
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 56581.18
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | IT Device OH | Not assigned | 001/2021 | 1.16
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | IT Device OH | Not assigned | 002/2021 | 221.98
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | IT Device OH | Not assigned | 003/2021 | 9028.75
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Minor Material OH | Not assigned | 002/2021 | 1035.8
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Minor Material OH | Not assigned | 003/2021 | 12045.73
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1132.63
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1465.54
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 7.37
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 249.14
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 321.97
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 45.7
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 101360.15
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 4.03
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 769.88
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 31314.87
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Contract | Construction Inspection | GULF INTERSTATE FIELD SERVICES INC | 003/2021 | 25747.76
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Contract | Construction Inspection | GULF INTERSTATE FIELD SERVICES INC | 004/2021 | -25747.76
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Contract | Construction Management Contracts | TRC SOLUTIONS INC | 003/2021 | 3304
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Contract | Contracts | Not assigned | 002/2021 | 43207.82
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 2120.22
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 252.37
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -252.37
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 1500
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -1500
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 213.75
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor External | Consulting Services - Environmental Perm | KLEINFELDER INC | 003/2021 | 3413.7
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 64.8
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Administration | Not assigned | 002/2021 | 783.45
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Administration | Not assigned | 004/2021 | 208.92
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 44.01
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Analyst Services | Not assigned | 002/2021 | 111.38
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Analyst Services | Not assigned | 003/2021 | 111.38
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Construction | Not assigned | 002/2021 | 2177.92
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Construction | Not assigned | 003/2021 | 3715.11
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Construction | Not assigned | 004/2021 | 154.29
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 120.18
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 756.65
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 1002.76
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 76.56
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.46
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 322.01
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 313.38
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 974.96
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 34.82
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Environmental Services | Not assigned | 002/2021 | 34.82
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Environmental Services | Not assigned | 003/2021 | 34.82
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | GAS Activity Charge - Non-Type A | Not assigned | 002/2021 | 107.08
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 921.61
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1118.73
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 637.16
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 418.99
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Indirect Labor - Gas | Not assigned | 002/2021 | 292.73
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 501.49
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 194.4
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Mapping | Not assigned | 002/2021 | 150.3
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Mapping | Not assigned | 003/2021 | 139.98
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1073.7
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1189.26
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 003/2021 | 22811.05
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Materials | Construction Supplies | Not assigned | 003/2021 | 461.14
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Materials | Electl & Electronic Equipment Component | Not assigned | 002/2021 | 13391.17
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Materials | Electrical Specialties | Not assigned | 002/2021 | 3132.28
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Materials | Electrical Specialties | Not assigned | 003/2021 | 317.72
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Materials | Material Burden | Not assigned | 002/2021 | 2412.42
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Materials | Material Burden | Not assigned | 003/2021 | 3444.12
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 68.7
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 201.57
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | AFUDC-Equity | Not assigned | 002/2021 | 185.37
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 543.92
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Benefits OH | Not assigned | 002/2021 | 2599.83
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Benefits OH | Not assigned | 003/2021 | 2910.12
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Building Service Overhead | Not assigned | 002/2021 | 446.18
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Building Service Overhead | Not assigned | 003/2021 | 526
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Capitalized A&G | Not assigned | 002/2021 | 2002.36
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Capitalized A&G | Not assigned | 003/2021 | 2174.2
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Cost Adjustments | Not assigned | 002/2021 | 6457.59
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 615.78
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 747.46
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Fleet OH - Gas | Not assigned | 002/2021 | 283.74
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 429.28
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | IT Device OH | Not assigned | 002/2021 | 253.23
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | IT Device OH | Not assigned | 003/2021 | 298.55
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Lodging | JEFFREY M DULLUM | 003/2021 | 117.72
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Lodging | Not assigned | 002/2021 | 117.72
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Lodging | Not assigned | 003/2021 | -117.72
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Minor Material OH | Not assigned | 002/2021 | 1346.34
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Minor Material OH | Not assigned | 003/2021 | 1922.12
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 834.09
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1012.47
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 381.62
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 250.95
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 508.3
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 769.01
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 878.32
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 1035.39
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Contract | Contracts | Not assigned | 002/2021 | 71522.48
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 48.6
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Administration | Not assigned | 001/2021 | 208.92
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Administration | Not assigned | 002/2021 | 139.28
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 97.81
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Construction | Not assigned | 001/2021 | 1116.75
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Construction | Not assigned | 002/2021 | 2456.85
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Construction | Not assigned | 003/2021 | 3132.29
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 554.35
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 1330.44
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 776.09
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Design Drafting Services | Not assigned | 001/2021 | 1953.93
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 001/2021 | 1309.2
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Electric Activity Charge - Type A | Not assigned | 002/2021 | 1659.88
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 355.26
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 261.84
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 76.56
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 148.91
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Env & Land Activity Charge - Type A | Not assigned | 002/2021 | 533.04
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 1044.6
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 383.02
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | GAS Activity Charge - Non-Type A | Not assigned | 002/2021 | 177.25
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Hours - Straight Time | Not assigned | 002/2021 | 93.11
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1887
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1956.84
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1335.05
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 182.56
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 237.53
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 452.82
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 55.82
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Indirect Labor - IT | Not assigned | 002/2021 | 34.73
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 259.2
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Manage L&EM | Not assigned | 003/2021 | 139.28
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Mapping | Not assigned | 001/2021 | 15.04
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Mapping | Not assigned | 002/2021 | 248.66
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Mapping | Not assigned | 003/2021 | 35.17
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 1225.14
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1316.71
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1082.35
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 002/2021 | 238453.97
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Materials | Electl & Electronic Equipment Component | Not assigned | 002/2021 | 22166.58
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Materials | Electrical Specialties | Not assigned | 001/2021 | 27584.36
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Materials | Electrical Specialties | Not assigned | 002/2021 | 52691.68
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Materials | Material Burden | Not assigned | 001/2021 | 4027.32
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Materials | Material Burden | Not assigned | 002/2021 | 47047.83
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Materials | Transformers, Regulators & Capacitors | Not assigned | 002/2021 | 8933.14
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 42.27
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 488.21
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 904.51
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | AFUDC-Equity | Not assigned | 001/2021 | 114.05
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1317.39
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2440.75
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Benefits OH | Not assigned | 001/2021 | 3198.09
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Benefits OH | Not assigned | 002/2021 | 11776.89
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Benefits OH | Not assigned | 003/2021 | 1990.75
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Building Service Overhead | Not assigned | 001/2021 | 548.89
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Building Service Overhead | Not assigned | 002/2021 | 2021.24
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Building Service Overhead | Not assigned | 003/2021 | 359.81
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Capitalized A&G | Not assigned | 001/2021 | 2239.79
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Capitalized A&G | Not assigned | 002/2021 | 2472.48
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Capitalized A&G | Not assigned | 003/2021 | 1978.77
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Cost Adjustments | Not assigned | 002/2021 | 10689.34
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1260.78
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1307.44
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 891.99
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Fleet OH - Gas | Not assigned | 002/2021 | 54.89
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Fleet OH - Gas | Not assigned | 003/2021 | 47.79
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | IT Device OH | Not assigned | 001/2021 | 311.54
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | IT Device OH | Not assigned | 002/2021 | 1147.16
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | IT Device OH | Not assigned | 003/2021 | 204.23
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Minor Material OH | Not assigned | 001/2021 | 2247.59
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Minor Material OH | Not assigned | 002/2021 | 26256.76
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1707.75
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1770.97
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1208.23
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 109.34
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 142.26
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 271.2
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 98.34
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 85.6
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Operation Mgmt & Support - IT | Not assigned | 002/2021 | 14.94
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 1080.52
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 3978.84
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 708.28
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 1647.39
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 5129.73
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 1211.25
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Labor Internal | Construction | Not assigned | 003/2021 | 670.05
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Labor Internal | Design Drafting Services | Not assigned | 002/2021 | 488.49
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 002/2021 | 1352.84
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Labor Internal | Drafting Doubletime | Not assigned | 002/2021 | 29.6
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Labor Internal | Engineering Services - OT | Not assigned | 003/2021 | 110.88
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 153.12
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 34.82
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 637.16
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 323.91
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 35.19
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 58.09
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 64.8
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 129.6
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Labor Internal | Management Services | Not assigned | 002/2021 | 34.82
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Labor Internal | Mapping | Not assigned | 002/2021 | 8.58
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 21.42
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 398.6
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 225.54
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 7.03
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 20.76
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 18.98
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 56.02
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | Benefits OH | Not assigned | 002/2021 | 790.38
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | Benefits OH | Not assigned | 003/2021 | 418.55
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 135.66
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 75.64
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 728.72
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 412.35
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 425.71
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 216.42
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | IT Device OH | Not assigned | 002/2021 | 76.98
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | IT Device OH | Not assigned | 003/2021 | 42.94
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 576.63
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 293.14
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 21.08
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 34.79
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 267.01
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 148.92
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 55.44
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 2449.92
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 002/2021 | 644.52
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 003/2021 | 859.36
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 139.28
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 104.46
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 218.49
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1140.81
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 49.21
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 129.81
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 705.81
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.57
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 11.56
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 4.23
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 31.19
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Other | Benefits OH | Not assigned | 002/2021 | 259.32
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Other | Benefits OH | Not assigned | 003/2021 | 1331.07
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 44.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 240.6
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 237.31
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 1290.35
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 145.98
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 762.22
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Other | IT Device OH | Not assigned | 002/2021 | 25.26
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Other | IT Device OH | Not assigned | 003/2021 | 136.54
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 197.74
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1032.44
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 29.47
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 87.61
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 473.6
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 55.44
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 382.8
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 76.56
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 69.64
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 104.46
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 129.77
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 44.91
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 24.6
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.5
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 77.1
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 40.72
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.93
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.33
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2.51
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6.28
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Other | Benefits OH | Not assigned | 002/2021 | 154.03
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Other | Benefits OH | Not assigned | 003/2021 | 73.3
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 26.44
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 13.27
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 140.95
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 74.42
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 86.7
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 30.01
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Other | IT Device OH | Not assigned | 002/2021 | 15
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Other | IT Device OH | Not assigned | 003/2021 | 7.53
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 117.44
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 40.65
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 14.74
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 52.04
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 26.09
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 55.44
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 153.12
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 76.56
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 002/2021 | 214.84
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 124.74
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 44.91
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.5
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 74.11
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 26.69
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.89
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.11
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2.41
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 5.69
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Other | Benefits OH | Not assigned | 002/2021 | 148.05
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Other | Benefits OH | Not assigned | 003/2021 | 50.64
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 25.41
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 9.17
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 135.48
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 48.78
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 83.34
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 30.01
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Other | IT Device OH | Not assigned | 002/2021 | 14.42
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Other | IT Device OH | Not assigned | 003/2021 | 5.2
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 112.89
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 40.65
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 50.02
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 18.02
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 55.44
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 229.68
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 76.56
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 77.86
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 44.91
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.5
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 46.26
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 26.69
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.56
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.44
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.51
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.88
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Other | Benefits OH | Not assigned | 002/2021 | 92.4
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Other | Benefits OH | Not assigned | 003/2021 | 50.64
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.86
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 9.17
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 84.57
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 48.78
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 52.02
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 30.01
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Other | IT Device OH | Not assigned | 002/2021 | 9
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Other | IT Device OH | Not assigned | 003/2021 | 5.2
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 70.47
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 40.65
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 31.22
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 18.02
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 2405.78
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 252.15
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 002/2021 | 118.75
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Labor Internal | Analyst Services | Not assigned | 003/2021 | 55.69
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 221.74
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 002/2021 | 87.28
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Labor Internal | Drafting Doubletime | Not assigned | 002/2021 | 177.6
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 11575.69
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Labor Internal | Electric Estimating Doubletime | Not assigned | 002/2021 | 532.8
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 4451.28
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 632.83
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 744.51
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 626.76
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 330.79
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 5994.06
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 255.1
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 241.1
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Labor Internal | Mapping | Not assigned | 002/2021 | 2.36
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Labor Internal | Mapping | Not assigned | 003/2021 | 7.98
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 3561.06
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 288.99
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 37.15
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 77.28
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 100.26
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 208.54
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Other | Benefits OH | Not assigned | 002/2021 | 7114.23
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Other | Benefits OH | Not assigned | 003/2021 | 509.58
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Other | Building Service Overhead | Not assigned | 002/2021 | 1220.99
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Other | Building Service Overhead | Not assigned | 003/2021 | 92.12
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Other | Capitalized A&G | Not assigned | 002/2021 | 6510.36
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Other | Capitalized A&G | Not assigned | 003/2021 | 528.35
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 4004.87
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 170.44
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Other | IT Device OH | Not assigned | 002/2021 | 693.01
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Other | IT Device OH | Not assigned | 003/2021 | 52.29
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 5424.7
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 230.87
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 144.41
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 2403.53
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 181.33
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 1560.5
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 105.06
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 498.75
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 421.2
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 453.6
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Administration | Not assigned | 003/2021 | 104.46
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Administration | Not assigned | 004/2021 | 174.1
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 352.05
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 264.03
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Design Drafting Services | Not assigned | 002/2021 | 3182.55
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Design Drafting Services | Not assigned | 003/2021 | 962.18
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 002/2021 | 1112.82
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 003/2021 | 130.92
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Design Services | Not assigned | 002/2021 | 59.21
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 4677.63
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 1421.05
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 3273
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 87.28
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 628.7
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 744.51
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 104.46
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 4384.6
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1136.47
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 616.6
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 544.84
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 972
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 615.6
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Mapping | Not assigned | 003/2021 | 6.49
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 2956.38
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 985.75
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 35.15
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 78.55
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 94.84
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 211.96
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | Benefits OH | Not assigned | 002/2021 | 5802.1
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | Benefits OH | Not assigned | 003/2021 | 1782.68
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | Building Service Overhead | Not assigned | 002/2021 | 995.8
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | Building Service Overhead | Not assigned | 003/2021 | 322.23
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | Capitalized A&G | Not assigned | 002/2021 | 5404.87
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | Capitalized A&G | Not assigned | 003/2021 | 1802.19
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 2929.53
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 759.32
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | IT Device OH | Not assigned | 002/2021 | 565.19
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | IT Device OH | Not assigned | 003/2021 | 182.89
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 3968.12
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1028.54
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 369.29
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 326.32
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 1960.27
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 634.27
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 22.89
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 64.8
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 64.64
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.73
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.98
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Other | Benefits OH | Not assigned | 003/2021 | 115.26
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 20.83
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 118.18
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Other | IT Device OH | Not assigned | 003/2021 | 11.83
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 13.71
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 41
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 148.9
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 50.48
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 22.89
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 64.8
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 49.65
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.55
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.5
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Other | Benefits OH | Not assigned | 003/2021 | 86.82
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 15.69
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 90.76
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 33.73
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Other | IT Device OH | Not assigned | 003/2021 | 8.9
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 45.68
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 13.71
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 30.88
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 44.98
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.54
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.46
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Other | Benefits OH | Not assigned | 003/2021 | 85.33
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 15.42
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 82.24
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Other | IT Device OH | Not assigned | 003/2021 | 8.76
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 30.36
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 44.98
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.54
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.46
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | Other | Benefits OH | Not assigned | 003/2021 | 85.33
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 15.42
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 82.24
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | Other | IT Device OH | Not assigned | 003/2021 | 8.76
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 30.36
35226625 | FRRB - ELK CREEK 1101 LR 2106 | Labor Internal | Management Services | Not assigned | 002/2021 | 765.31
35226625 | FRRB - ELK CREEK 1101 LR 2106 | Labor Internal | Management Services | Not assigned | 003/2021 | 971.36
35226625 | FRRB - ELK CREEK 1101 LR 2106 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.01
35226625 | FRRB - ELK CREEK 1101 LR 2106 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3.3
35226625 | FRRB - ELK CREEK 1101 LR 2106 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2.73
35226625 | FRRB - ELK CREEK 1101 LR 2106 | Other | AFUDC-Equity | Not assigned | 003/2021 | 8.91
35226625 | FRRB - ELK CREEK 1101 LR 2106 | Other | Benefits OH | Not assigned | 002/2021 | 148.5
35226625 | FRRB - ELK CREEK 1101 LR 2106 | Other | Benefits OH | Not assigned | 003/2021 | 178.97
35226625 | FRRB - ELK CREEK 1101 LR 2106 | Other | Building Service Overhead | Not assigned | 002/2021 | 25.48
35226625 | FRRB - ELK CREEK 1101 LR 2106 | Other | Building Service Overhead | Not assigned | 003/2021 | 32.35
35226625 | FRRB - ELK CREEK 1101 LR 2106 | Other | Capitalized A&G | Not assigned | 002/2021 | 281.79
35226625 | FRRB - ELK CREEK 1101 LR 2106 | Other | Capitalized A&G | Not assigned | 003/2021 | 357.65
35226625 | FRRB - ELK CREEK 1101 LR 2106 | Other | IT Device OH | Not assigned | 002/2021 | 14.46
35226625 | FRRB - ELK CREEK 1101 LR 2106 | Other | IT Device OH | Not assigned | 003/2021 | 18.36
35226625 | FRRB - ELK CREEK 1101 LR 2106 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 50.17
35226625 | FRRB - ELK CREEK 1101 LR 2106 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 63.68
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 210.6
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 1425.6
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Acquisition - Misc | Not assigned | 004/2021 | 356.4
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Construction | Not assigned | 001/2021 | 1635.36
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 559.38
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 177.43
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 560.9
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 291.6
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 129.6
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Land Rights - Misc | Not assigned | 004/2021 | 162
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Manage L&EM | Not assigned | 003/2021 | 32.4
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Management Services | Not assigned | 002/2021 | 941.92
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Management Services | Not assigned | 003/2021 | 235.48
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Mapping | Not assigned | 001/2021 | 14.72
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 332.32
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 101.14
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 319.75
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 4.01
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 10.33
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 16.29
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | AFUDC-Equity | Not assigned | 001/2021 | 10.83
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | AFUDC-Equity | Not assigned | 002/2021 | 27.89
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | AFUDC-Equity | Not assigned | 003/2021 | 43.95
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Benefits OH | Not assigned | 001/2021 | 663.91
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Benefits OH | Not assigned | 002/2021 | 354.87
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Benefits OH | Not assigned | 003/2021 | 560.02
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Building Service Overhead | Not assigned | 001/2021 | 113.95
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Building Service Overhead | Not assigned | 002/2021 | 60.91
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Building Service Overhead | Not assigned | 003/2021 | 101.22
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Capitalized A&G | Not assigned | 001/2021 | 607.56
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Capitalized A&G | Not assigned | 002/2021 | 531.72
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Capitalized A&G | Not assigned | 003/2021 | 671.26
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 373.74
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | IT Device OH | Not assigned | 001/2021 | 64.67
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | IT Device OH | Not assigned | 002/2021 | 34.56
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | IT Device OH | Not assigned | 003/2021 | 57.46
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 506.25
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 106.27
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 335.94
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 224.31
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 119.88
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 199.27
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | 24570
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 004/2021 | -24570
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 266.45
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 69.64
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 90.33
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 24.6
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 67.69
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 20.14
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 54.34
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 124.46
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 22.49
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 123.75
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 60.35
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 12.78
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 81.75
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 14.74
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 44.29
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | 24570
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 004/2021 | -24570
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 97.2
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 97.2
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 34.34
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 74.4
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 113.4
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 19.58
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 42.41
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.21
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 20.2
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 0.55
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 54.51
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Other | Benefits OH | Not assigned | 002/2021 | 33.31
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Other | Benefits OH | Not assigned | 003/2021 | 68.52
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.72
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 12.38
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 35.79
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 77.54
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Other | IT Device OH | Not assigned | 002/2021 | 3.25
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Other | IT Device OH | Not assigned | 003/2021 | 7.03
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 20.57
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 44.56
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 11.26
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 24.38
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | 24570
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 004/2021 | -24570
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 97.2
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 97.2
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 34.34
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 68.68
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 97.2
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 19.58
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 39.15
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.21
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 20.17
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 0.55
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 54.42
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Other | Benefits OH | Not assigned | 002/2021 | 33.31
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Other | Benefits OH | Not assigned | 003/2021 | 63.26
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.72
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 11.43
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 35.79
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 71.58
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Other | IT Device OH | Not assigned | 002/2021 | 3.25
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Other | IT Device OH | Not assigned | 003/2021 | 6.49
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 20.57
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 41.14
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 11.26
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 22.5
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | 24570
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 004/2021 | -24570
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 34.82
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 12.3
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 7.01
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 19.42
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 52.41
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Other | Benefits OH | Not assigned | 003/2021 | 11.33
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 2.05
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 12.82
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Other | IT Device OH | Not assigned | 003/2021 | 1.16
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 7.37
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 4.03
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | 24570
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 004/2021 | -24570
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 97.2
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 97.2
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 174.56
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 59.18
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 34.34
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 74.4
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 113.4
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 19.58
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 77.57
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.21
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 20.62
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 0.55
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 55.65
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Other | Benefits OH | Not assigned | 002/2021 | 33.31
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Other | Benefits OH | Not assigned | 003/2021 | 135.22
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.72
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Other | Building Service Overhead | Not assigned | 003/2021 | 24.43
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Other | Capitalized A&G | Not assigned | 002/2021 | 35.79
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Other | Capitalized A&G | Not assigned | 003/2021 | 141.81
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 39.54
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Other | IT Device OH | Not assigned | 002/2021 | 3.25
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Other | IT Device OH | Not assigned | 003/2021 | 13.87
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 53.56
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 20.57
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 44.56
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 11.26
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 48.12
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 100.95
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 22.89
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 64.8
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 59.98
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 64.64
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Labor Internal | Project Management Services | Not assigned | 002/2021 | 297.8
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.72
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.18
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.95
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 5.89
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 119.83
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 115.26
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 20.57
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 20.83
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 109.65
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 118.18
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 67.45
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Other | IT Device OH | Not assigned | 002/2021 | 11.67
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 11.83
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 91.37
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 13.71
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 40.48
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 41
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | 24250
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 004/2021 | -24250
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 70.32
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 23.84
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.16
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.17
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 19.44
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 0.46
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 52.45
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Other | Benefits OH | Not assigned | 002/2021 | 28.31
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Other | Building Service Overhead | Not assigned | 002/2021 | 4.86
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Other | Capitalized A&G | Not assigned | 002/2021 | 25.89
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 15.93
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Other | IT Device OH | Not assigned | 002/2021 | 2.76
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 21.57
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 9.56
35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | 24250
35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 004/2021 | -24250
35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 19.1
35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 51.53
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 44.98
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.54
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.46
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 85.33
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 15.42
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 82.24
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 8.76
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 30.36
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Contract | Contracts | Not assigned | 003/2021 | 655.7
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Labor Internal | Design Drafting Services | Not assigned | 003/2021 | 5624.95
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 003/2021 | 174.56
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 1953.93
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 8585.45
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 218.2
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 1134.64
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 260.59
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 521.16
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 824.69
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 5438.48
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Labor Internal | Mapping | Not assigned | 003/2021 | 1.97
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 489.95
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 3231.01
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 5.92
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 50.94
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 15.97
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 137.45
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Other | Benefits OH | Not assigned | 002/2021 | 978.8
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Other | Benefits OH | Not assigned | 003/2021 | 6129.26
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Other | Building Service Overhead | Not assigned | 002/2021 | 167.99
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Other | Building Service Overhead | Not assigned | 003/2021 | 1107.81
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Other | Capitalized A&G | Not assigned | 002/2021 | 895.73
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Other | Capitalized A&G | Not assigned | 003/2021 | 5906.94
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 551.01
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 3633.68
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Other | IT Device OH | Not assigned | 002/2021 | 95.36
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Other | IT Device OH | Not assigned | 003/2021 | 628.76
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 746.36
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 4921.9
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 330.69
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 2180.77
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 237.5
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Labor Internal | Construction | Not assigned | 002/2021 | 297.8
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Labor Internal | Construction | Not assigned | 003/2021 | 744.5
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Labor Internal | Design Services | Not assigned | 003/2021 | 858.55
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 210.96
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 841.72
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 173.38
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 831.28
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 2.68
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 7.41
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 103.01
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 493.87
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.24
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 8.6
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3.36
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 23.21
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Other | Benefits OH | Not assigned | 002/2021 | 205.77
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Other | Benefits OH | Not assigned | 003/2021 | 936.88
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 35.32
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 169.34
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 188.32
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 902.89
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 115.84
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 555.42
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Other | IT Device OH | Not assigned | 002/2021 | 20.04
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Other | IT Device OH | Not assigned | 003/2021 | 96.12
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 156.91
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 752.33
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 69.53
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 333.32
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 95
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Labor Internal | Construction | Not assigned | 002/2021 | 297.8
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Labor Internal | Construction | Not assigned | 003/2021 | 893.4
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 105.48
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 806.56
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 137.62
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 579.12
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 2.68
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 8.33
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 81.76
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 344.05
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.99
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 6.18
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2.66
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 16.67
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Other | Benefits OH | Not assigned | 002/2021 | 163.34
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Other | Benefits OH | Not assigned | 003/2021 | 652.66
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 28.04
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 117.96
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 149.48
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 629
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 91.95
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 386.93
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Other | IT Device OH | Not assigned | 002/2021 | 15.91
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Other | IT Device OH | Not assigned | 003/2021 | 66.95
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 124.55
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 524.11
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 55.19
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 232.21
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 105.06
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Labor Internal | Account Services | Not assigned | 003/2021 | 262.52
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 221.74
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 74.45
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 2090.85
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Labor Internal | Hours - Straight Time | Not assigned | 003/2021 | 558.64
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 67.97
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 25.24
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 784.76
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Labor Internal | Indirect Labor - IT | Not assigned | 003/2021 | 208.37
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 2.32
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 14.99
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 631.6
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.18
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 7.66
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 0.49
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 20.68
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Other | Benefits OH | Not assigned | 002/2021 | 29.96
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Other | Benefits OH | Not assigned | 003/2021 | 1133.63
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.14
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 204.92
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 27.41
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 1154.71
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 16.86
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 524.33
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Other | IT Device OH | Not assigned | 002/2021 | 2.92
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Other | IT Device OH | Not assigned | 003/2021 | 116.28
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 22.84
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 710.22
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Other | Operation Mgmt & Support - IT | Not assigned | 003/2021 | 89.67
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.12
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 403.33
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 105.06
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 71.25
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 521.15
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 483.93
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 176.67
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 164.23
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 80.13
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 34.34
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 002/2021 | 226.8
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 97.2
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.53
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 150.64
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 117.15
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.75
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 5.01
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 4.71
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 13.51
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | Benefits OH | Not assigned | 002/2021 | 287.4
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | Benefits OH | Not assigned | 003/2021 | 216.72
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 49.32
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 39.17
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 275.4
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 214.17
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 118.04
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 109.73
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | IT Device OH | Not assigned | 002/2021 | 28
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | IT Device OH | Not assigned | 003/2021 | 22.24
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 159.89
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 148.63
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 47.99
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 20.57
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 97.11
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 77.11
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 003/2021 | 510.38
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | SPECIALIST STAFFING SOLUTIONS INC | 004/2021 | -510.38
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 105.06
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 190
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Labor Internal | Account Services | Not assigned | 003/2021 | 65.63
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Labor Internal | Administration | Not assigned | 003/2021 | 139.28
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Labor Internal | Construction | Not assigned | 003/2021 | 681.4
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 628.7
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1298.76
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 452.66
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 69.64
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 16.99
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 213.13
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 673.65
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 209.13
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Labor Internal | Mapping | Not assigned | 003/2021 | 7.02
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 126.62
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 532.65
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.53
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 9.75
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 4.13
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 26.3
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Other | Benefits OH | Not assigned | 002/2021 | 252.97
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Other | Benefits OH | Not assigned | 003/2021 | 969.51
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 43.41
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 175.24
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 231.49
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 973.79
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 142.4
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 450.1
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Other | IT Device OH | Not assigned | 002/2021 | 24.64
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Other | IT Device OH | Not assigned | 003/2021 | 99.48
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 192.88
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 609.66
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 125.25
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 85.47
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 344.96
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 105.06
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 23.75
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Labor Internal | Account Services | Not assigned | 003/2021 | 65.63
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Labor Internal | Administration | Not assigned | 004/2021 | 139.28
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 550.12
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1563.46
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 139.28
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 16.99
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 186.49
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 530.14
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.39
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 110.79
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 328.18
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.34
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 6.67
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3.61
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 18.01
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Other | Benefits OH | Not assigned | 002/2021 | 221.32
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Other | Benefits OH | Not assigned | 003/2021 | 615.14
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 37.99
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 111.17
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 202.55
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 599.97
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 124.6
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 354.21
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Other | IT Device OH | Not assigned | 002/2021 | 21.56
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Other | IT Device OH | Not assigned | 003/2021 | 63.11
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 168.78
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 479.79
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 74.78
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 218.85
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Labor Internal | Account Services | Not assigned | 003/2021 | 131.26
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Labor Internal | Construction | Not assigned | 002/2021 | 521.15
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Labor Internal | Construction | Not assigned | 003/2021 | 670.05
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 1006.57
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 13618.3
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 174.56
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 3403.92
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 744.5
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 33.98
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 578.66
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 6252.1
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 4.69
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 6.03
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 343.78
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 3740.82
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 4.15
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 53.1
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 11.2
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 143.28
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Other | Benefits OH | Not assigned | 002/2021 | 686.79
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Other | Benefits OH | Not assigned | 003/2021 | 7081.55
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 117.87
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 1279.93
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 628.51
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 6838.97
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 386.63
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 4177.3
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Other | IT Device OH | Not assigned | 002/2021 | 66.9
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Other | IT Device OH | Not assigned | 003/2021 | 726.44
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 523.7
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 5658.25
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 232.03
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 2519.61
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Labor Internal | Account Services | Not assigned | 003/2021 | 65.63
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Labor Internal | Construction | Not assigned | 002/2021 | 297.8
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Labor Internal | Construction | Not assigned | 003/2021 | 772.26
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Labor Internal | Design Drafting Services | Not assigned | 003/2021 | 947.36
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 3434.22
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 13440.84
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 2007.44
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 37.23
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 744.51
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 16.99
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1278.69
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 6074.67
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 2.68
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 6.95
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 759.67
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 3622.18
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 9.17
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 61.76
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 24.75
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 166.66
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Other | Benefits OH | Not assigned | 002/2021 | 1517.64
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Other | Benefits OH | Not assigned | 003/2021 | 6863.9
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 260.47
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 1240.61
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 1388.83
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 6622.07
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 854.34
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 4058.75
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Other | IT Device OH | Not assigned | 002/2021 | 147.83
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Other | IT Device OH | Not assigned | 003/2021 | 704.13
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1157.23
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 5497.66
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 512.74
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 2442.16
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Labor Internal | Construction | Not assigned | 002/2021 | 297.8
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Labor Internal | Construction | Not assigned | 003/2021 | 670.05
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 3078.92
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 10302.54
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Labor Internal | Electric Estimating Doubletime | Not assigned | 002/2021 | 710.4
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Labor Internal | Electric Estimating Doubletime | Not assigned | 003/2021 | 1361.6
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 3142.08
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 12088.28
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 744.5
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 2451.6
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 8533.64
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 2.68
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Labor Internal | Mapping | Not assigned | 003/2021 | 6.03
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1456.5
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 5069.83
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 17.59
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 96
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 47.46
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 259.05
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Other | Benefits OH | Not assigned | 002/2021 | 2909.75
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Other | Benefits OH | Not assigned | 003/2021 | 9617.57
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 499.39
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 1738.28
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 2662.78
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 9268.7
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1638.02
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 5701.69
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Other | IT Device OH | Not assigned | 002/2021 | 283.43
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Other | IT Device OH | Not assigned | 003/2021 | 986.61
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 2218.74
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 7723.07
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 983.07
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 3421.91
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Labor Internal | Construction | Not assigned | 002/2021 | 297.8
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Labor Internal | Construction | Not assigned | 003/2021 | 670.05
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 947.36
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 2782.88
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 1047.36
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 670.05
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 423.02
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1754.78
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Labor Internal | Mapping | Not assigned | 002/2021 | 2.68
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Labor Internal | Mapping | Not assigned | 003/2021 | 6.03
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 251.32
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1042.52
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 3.03
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 18.58
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 8.19
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 50.13
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Other | Benefits OH | Not assigned | 002/2021 | 502.08
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Other | Benefits OH | Not assigned | 003/2021 | 1977.69
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 86.18
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 357.46
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 459.46
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 1905.93
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 282.64
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 1172.45
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Other | IT Device OH | Not assigned | 002/2021 | 48.92
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Other | IT Device OH | Not assigned | 003/2021 | 202.88
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 382.84
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1588.11
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 169.64
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 703.65
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 132.02
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 75.17
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 100.95
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 46.64
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 71.25
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 59.98
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Labor Internal | Project Management Overtime | Not assigned | 002/2021 | 221.74
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 297.8
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.82
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.36
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 2.21
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6.36
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Other | Benefits OH | Not assigned | 002/2021 | 134.44
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Other | Benefits OH | Not assigned | 003/2021 | 113.77
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 23.08
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 20.57
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 130.25
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 109.65
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 50.22
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 67.45
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Other | IT Device OH | Not assigned | 002/2021 | 13.1
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Other | IT Device OH | Not assigned | 003/2021 | 11.67
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 68.03
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 91.37
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 27.94
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 45.42
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 40.48
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 37.58
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 100.95
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 22.33
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 59.98
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Labor Internal | Project Management Overtime | Not assigned | 002/2021 | 110.87
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 297.8
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.27
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.26
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 0.73
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.4
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Other | Benefits OH | Not assigned | 002/2021 | 44.61
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Other | Benefits OH | Not assigned | 003/2021 | 113.77
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 7.66
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 20.57
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 40.82
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 109.65
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 25.11
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 67.45
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Other | IT Device OH | Not assigned | 002/2021 | 4.34
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Other | IT Device OH | Not assigned | 003/2021 | 11.67
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 34.01
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 91.37
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 15.07
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 40.48
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Labor Internal | Account Services | Not assigned | 003/2021 | 65.63
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 335.03
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 16.99
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 37.58
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 214.53
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 22.33
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 140.67
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Labor Internal | Project Management Overtime | Not assigned | 002/2021 | 110.87
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 297.8
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.27
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.19
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 0.73
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 5.9
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Other | Benefits OH | Not assigned | 002/2021 | 44.61
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Other | Benefits OH | Not assigned | 003/2021 | 259.44
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 7.66
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 46.9
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 40.82
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 257.17
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 25.11
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 143.34
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Other | IT Device OH | Not assigned | 002/2021 | 4.34
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Other | IT Device OH | Not assigned | 003/2021 | 26.61
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 34.01
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 194.15
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 15.07
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 92.32
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 335.03
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 37.58
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 239.77
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 22.33
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 142.45
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Labor Internal | Project Management Overtime | Not assigned | 002/2021 | 110.87
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 372.25
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.27
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.25
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 0.73
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6.07
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Other | Benefits OH | Not assigned | 002/2021 | 44.61
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Other | Benefits OH | Not assigned | 003/2021 | 270.21
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 7.66
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 48.84
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 40.82
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 260.42
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 25.11
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 160.2
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Other | IT Device OH | Not assigned | 002/2021 | 4.34
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Other | IT Device OH | Not assigned | 003/2021 | 27.72
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 34.01
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 216.99
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 15.07
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 96.14
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 335.03
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 37.58
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 201.64
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 22.33
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 119.79
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Labor Internal | Project Management Overtime | Not assigned | 002/2021 | 110.87
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 110.87
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 148.9
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.27
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.98
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 0.73
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 5.33
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Other | Benefits OH | Not assigned | 002/2021 | 44.61
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Other | Benefits OH | Not assigned | 003/2021 | 227.25
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Other | Building Service Overhead | Not assigned | 002/2021 | 7.66
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Other | Building Service Overhead | Not assigned | 003/2021 | 41.08
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Other | Capitalized A&G | Not assigned | 002/2021 | 40.82
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Other | Capitalized A&G | Not assigned | 003/2021 | 219.01
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 25.11
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 134.72
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Other | IT Device OH | Not assigned | 002/2021 | 4.34
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Other | IT Device OH | Not assigned | 003/2021 | 23.32
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 34.01
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 182.48
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 15.07
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 80.86
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 335.03
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 264.46
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 157.12
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 221.74
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 223.35
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.88
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 5.09
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Other | Benefits OH | Not assigned | 003/2021 | 298.06
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 53.87
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 287.24
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 176.7
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Other | IT Device OH | Not assigned | 003/2021 | 30.57
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 239.34
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 106.04
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 335.03
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 264.46
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 157.12
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 221.74
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 223.35
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.88
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 5.09
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Other | Benefits OH | Not assigned | 003/2021 | 298.06
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 53.87
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 287.24
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 176.7
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Other | IT Device OH | Not assigned | 003/2021 | 30.57
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 239.34
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 106.04
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 335.03
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 264.46
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 157.12
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 221.74
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 223.35
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.88
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 5.09
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Other | Benefits OH | Not assigned | 003/2021 | 298.06
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 53.87
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 287.24
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 176.7
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Other | IT Device OH | Not assigned | 003/2021 | 30.57
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 239.34
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 106.04
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 113.3
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 67.31
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 110.87
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 223.35
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.81
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.18
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Other | Benefits OH | Not assigned | 003/2021 | 127.69
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 23.07
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 123.06
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 75.7
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Other | IT Device OH | Not assigned | 003/2021 | 13.1
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 102.54
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 45.44
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 335.03
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 189.29
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 112.46
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 223.35
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.35
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.64
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Other | Benefits OH | Not assigned | 003/2021 | 213.33
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Other | Building Service Overhead | Not assigned | 003/2021 | 38.55
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Other | Capitalized A&G | Not assigned | 003/2021 | 205.6
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 126.47
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Other | IT Device OH | Not assigned | 003/2021 | 21.88
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 171.31
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 75.91
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 125.65
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 91.58
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 259.2
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 126.85
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 221.74
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 148.9
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.44
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.89
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Other | Benefits OH | Not assigned | 003/2021 | 225.97
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Other | Building Service Overhead | Not assigned | 003/2021 | 40.85
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Other | Capitalized A&G | Not assigned | 003/2021 | 231.91
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 83.95
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Other | IT Device OH | Not assigned | 003/2021 | 23.2
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 113.71
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 54.85
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 80.41
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 125.65
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 137.36
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 388.8
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 152.95
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 221.74
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 148.9
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.71
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4.62
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Other | Benefits OH | Not assigned | 003/2021 | 268.13
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Other | Building Service Overhead | Not assigned | 003/2021 | 48.47
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Other | Capitalized A&G | Not assigned | 003/2021 | 279.63
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 83.95
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Other | IT Device OH | Not assigned | 003/2021 | 27.52
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 113.71
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 82.27
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 95.41
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 335.03
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 251.57
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 45.79
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 129.6
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 175.56
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 332.61
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 74.45
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.07
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Other | AFUDC-Equity | Not assigned | 003/2021 | 5.57
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Other | Benefits OH | Not assigned | 003/2021 | 325.7
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Other | Building Service Overhead | Not assigned | 003/2021 | 58.86
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Other | Capitalized A&G | Not assigned | 003/2021 | 320.96
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 168.08
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Other | IT Device OH | Not assigned | 003/2021 | 33.42
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 227.67
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 27.42
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 115.86
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 100.41
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 57.23
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 162
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 92.28
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 221.74
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 74.45
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.06
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.85
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Other | Benefits OH | Not assigned | 003/2021 | 165.88
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Other | Building Service Overhead | Not assigned | 003/2021 | 29.97
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Other | Capitalized A&G | Not assigned | 003/2021 | 168.71
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 67.09
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Other | IT Device OH | Not assigned | 003/2021 | 17.03
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 90.87
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 34.28
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 59.01
35226900 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 003/2021 | 25250
35226900 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | EN ENGINEERING LLC | 004/2021 | -25250
35226900 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 19.88
35226900 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 53.66
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 335.03
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 176.4
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 57.23
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 162
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 137.43
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 110.87
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 74.45
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.6
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4.31
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Other | Benefits OH | Not assigned | 003/2021 | 251.52
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Other | Building Service Overhead | Not assigned | 003/2021 | 45.45
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Other | Capitalized A&G | Not assigned | 003/2021 | 251.24
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 117.86
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Other | IT Device OH | Not assigned | 003/2021 | 25.8
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 159.64
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 34.28
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 89.5
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 335.03
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 176.4
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 11.45
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 32.4
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 111.33
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 110.87
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 74.45
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.33
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.58
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Other | Benefits OH | Not assigned | 003/2021 | 209.36
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Other | Building Service Overhead | Not assigned | 003/2021 | 37.84
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Other | Capitalized A&G | Not assigned | 003/2021 | 203.52
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 117.86
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Other | IT Device OH | Not assigned | 003/2021 | 21.47
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 159.64
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 6.86
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 74.5
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 44.01
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 335.03
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 176.4
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 61.34
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 129.6
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 139.77
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 110.87
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 74.45
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.62
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4.38
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Other | Benefits OH | Not assigned | 003/2021 | 255.31
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Other | Building Service Overhead | Not assigned | 003/2021 | 46.14
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Other | Capitalized A&G | Not assigned | 003/2021 | 255.51
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 117.86
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Other | IT Device OH | Not assigned | 003/2021 | 26.18
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 159.64
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 36.74
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 90.84
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 44.01
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 335.03
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 176.4
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 15.55
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 113.66
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 110.87
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 74.45
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.35
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.64
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Other | Benefits OH | Not assigned | 003/2021 | 213.13
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Other | Building Service Overhead | Not assigned | 003/2021 | 38.52
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Other | Capitalized A&G | Not assigned | 003/2021 | 207.79
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 117.86
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Other | IT Device OH | Not assigned | 003/2021 | 21.86
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 159.64
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 9.31
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 75.83
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 88.01
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 100.41
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 31.09
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 68.68
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 194.4
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 17.73
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 98.8
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 221.74
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 74.45
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.19
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.5
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 0.5
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4.04
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Other | Benefits OH | Not assigned | 002/2021 | 30.16
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Other | Benefits OH | Not assigned | 003/2021 | 176.43
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.18
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 31.88
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 32.41
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 180.64
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 67.09
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Other | IT Device OH | Not assigned | 002/2021 | 2.93
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Other | IT Device OH | Not assigned | 003/2021 | 18.11
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 90.87
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 18.62
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 41.14
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.19
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 62.75
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 176.02
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 264.03
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 211.74
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 172.19
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 62.19
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 93.28
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 35.45
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 155.47
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 221.74
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 74.45
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.37
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.53
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 6.82
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Other | Benefits OH | Not assigned | 002/2021 | 60.32
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Other | Benefits OH | Not assigned | 003/2021 | 279.98
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 10.35
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 50.6
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 64.81
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 284.24
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 115.05
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Other | IT Device OH | Not assigned | 002/2021 | 5.88
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Other | IT Device OH | Not assigned | 003/2021 | 28.74
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 155.83
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 37.25
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 55.87
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 20.38
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 99.61
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 100.41
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 59.65
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 221.74
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 74.45
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.72
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.93
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Other | Benefits OH | Not assigned | 003/2021 | 113.17
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 20.45
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 109.06
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 67.09
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Other | IT Device OH | Not assigned | 003/2021 | 11.62
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 90.87
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 40.25
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Labor Internal | Administrative Services - Double Time | Not assigned | 003/2021 | 121.39
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 220.03
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 100.41
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 77.74
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 42.89
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 44.31
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 84.1
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 221.74
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 74.45
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.47
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.9
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.26
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 5.13
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Other | Benefits OH | Not assigned | 002/2021 | 75.41
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Other | Benefits OH | Not assigned | 003/2021 | 152.68
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Other | Building Service Overhead | Not assigned | 002/2021 | 12.94
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Other | Building Service Overhead | Not assigned | 003/2021 | 27.59
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Other | Capitalized A&G | Not assigned | 002/2021 | 81.02
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Other | Capitalized A&G | Not assigned | 003/2021 | 153.76
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 67.09
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Other | IT Device OH | Not assigned | 002/2021 | 7.35
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Other | IT Device OH | Not assigned | 003/2021 | 15.67
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 90.87
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 46.56
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 25.69
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 25.48
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 54.3
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 220.03
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 62.82
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 77.74
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 44.31
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 37.32
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 110.87
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 74.45
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.47
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.38
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.26
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.72
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Other | Benefits OH | Not assigned | 002/2021 | 75.41
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Other | Benefits OH | Not assigned | 003/2021 | 70.8
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Other | Building Service Overhead | Not assigned | 002/2021 | 12.94
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Other | Building Service Overhead | Not assigned | 003/2021 | 12.79
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Other | Capitalized A&G | Not assigned | 002/2021 | 81.02
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Other | Capitalized A&G | Not assigned | 003/2021 | 68.23
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 41.97
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Other | IT Device OH | Not assigned | 002/2021 | 7.35
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Other | IT Device OH | Not assigned | 003/2021 | 7.25
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 56.86
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 46.56
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 25.48
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 25.19
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 88.01
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 62.82
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 31.09
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 17.73
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 37.32
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 110.87
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 74.45
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.19
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.82
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Other | AFUDC-Equity | Not assigned | 002/2021 | 0.5
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.21
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Other | Benefits OH | Not assigned | 002/2021 | 30.16
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Other | Benefits OH | Not assigned | 003/2021 | 70.8
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Other | Building Service Overhead | Not assigned | 002/2021 | 5.18
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Other | Building Service Overhead | Not assigned | 003/2021 | 12.79
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Other | Capitalized A&G | Not assigned | 002/2021 | 32.41
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Other | Capitalized A&G | Not assigned | 003/2021 | 68.23
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 41.97
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Other | IT Device OH | Not assigned | 002/2021 | 2.93
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Other | IT Device OH | Not assigned | 003/2021 | 7.25
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 56.86
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 18.62
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 10.19
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 25.19
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 11.45
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 32.4
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 58.12
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.67
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.8
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Other | Benefits OH | Not assigned | 003/2021 | 104.72
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 18.92
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 106.25
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Other | IT Device OH | Not assigned | 003/2021 | 10.75
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 6.86
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 37.26
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Labor Internal | Account Services | Not assigned | 003/2021 | 32.82
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 8.5
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 11.45
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 32.4
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 58.12
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.67
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.8
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Other | Benefits OH | Not assigned | 003/2021 | 104.72
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 18.92
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 106.25
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Other | IT Device OH | Not assigned | 003/2021 | 10.75
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 6.86
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 37.26
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 11.45
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 32.4
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 51.51
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.61
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.64
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Other | Benefits OH | Not assigned | 003/2021 | 95.88
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 17.33
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 94.17
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Other | IT Device OH | Not assigned | 003/2021 | 9.84
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 6.86
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 34.12
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 132.02
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 149.66
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 291.6
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 130.3
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.43
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.86
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Other | Benefits OH | Not assigned | 003/2021 | 223.19
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 40.34
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 238.22
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Other | IT Device OH | Not assigned | 003/2021 | 22.9
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 89.64
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 79.41
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 97.2
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 176.03
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 199.55
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 291.6
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 158.74
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.73
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4.66
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Other | Benefits OH | Not assigned | 003/2021 | 269.14
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Other | Building Service Overhead | Not assigned | 003/2021 | 48.64
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Other | Capitalized A&G | Not assigned | 003/2021 | 290.21
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Other | IT Device OH | Not assigned | 003/2021 | 27.62
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 119.52
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 95.77
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Labor Internal | Administration | Not assigned | 003/2021 | 104.46
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 139.28
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 37.58
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 37.58
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 86.12
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 22.33
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 71.42
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Labor Internal | Project Management Overtime | Not assigned | 002/2021 | 110.87
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 110.87
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.27
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.32
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 0.73
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.56
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 44.61
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 121.68
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 7.66
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 22
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 40.82
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 130.56
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 25.11
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 25.11
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Other | IT Device OH | Not assigned | 002/2021 | 4.34
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 12.48
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 34.01
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 34.01
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 51.57
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 15.07
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 43.3
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Labor Internal | Administration | Not assigned | 003/2021 | 104.46
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 139.28
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 37.58
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 86.12
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 71.42
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 110.87
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.78
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.1
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Other | Benefits OH | Not assigned | 003/2021 | 121.68
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 22
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 130.56
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 25.11
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Other | IT Device OH | Not assigned | 003/2021 | 12.48
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 34.01
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 51.57
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 43.3
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Contract | Construction Inspection | CANUS CORPORATION | 003/2021 | 864.22
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Contract | Contracts | ARBORWORKS INC | 004/2021 | 17205.16
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 6502.49
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 29833.67
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Contract | Helicopter Contract | Not assigned | 003/2021 | 200802.43
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 002/2021 | 37106.52
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Contract | Traffic Control Contracts | TRAFFIC MANAGEMENT INC | 003/2021 | 65346.85
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 674.87
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Construction | Not assigned | 002/2021 | 6758
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Construction | Not assigned | 003/2021 | 89543.5
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Construction Doubletime Services | Not assigned | 002/2021 | 1351.6
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Construction Doubletime Services | Not assigned | 003/2021 | 27572.64
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 443.48
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 1013.7
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 384.87
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Electric Estimating Doubletime | Not assigned | 001/2021 | 2782.4
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 70.32
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1377.33
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 769.34
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 522.3
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 2158.84
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1097.54
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 3392.49
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 40753.92
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 560.32
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 762.72
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 003/2021 | 144.12
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Manage L&EM | Not assigned | 002/2021 | 388.8
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Mapping | Not assigned | 002/2021 | 76.98
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Mapping | Not assigned | 003/2021 | 1174.77
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 652.05
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 2334.9
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 24646.72
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 002/2021 | 986.66
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Materials | Construction Supplies | Not assigned | 002/2021 | 2862.56
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Materials | Electl & Electronic Equipment Component | Not assigned | 002/2021 | 3691.41
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Materials | Fabricated Structures | Not assigned | 002/2021 | 7425.45
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Materials | Fabricated Structures | Not assigned | 003/2021 | -26406.54
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Materials | Material Burden | Not assigned | 002/2021 | 14938.16
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Materials | Material Burden | Not assigned | 003/2021 | -264.07
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 002/2021 | 81757.48
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 12502.55
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 002/2021 | 100.23
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 7.46
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 170.53
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 395.22
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | AFUDC-Equity | Not assigned | 001/2021 | 20.12
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 460.15
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1066.48
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Benefits OH | Not assigned | 001/2021 | 1302.68
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Benefits OH | Not assigned | 002/2021 | 7468.39
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Benefits OH | Not assigned | 003/2021 | 46584.27
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Building Service Overhead | Not assigned | 001/2021 | 223.58
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Building Service Overhead | Not assigned | 002/2021 | 1281.78
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Building Service Overhead | Not assigned | 003/2021 | 8419.73
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Capitalized A&G | Not assigned | 001/2021 | 1192.08
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Capitalized A&G | Not assigned | 002/2021 | 4268.67
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Capitalized A&G | Not assigned | 003/2021 | 45059.18
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Cash Discount earned | STELLA-JONES CORPORATION | 002/2021 | -1335.97
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Cash Discount earned | TRAFFIC MANAGEMENT INC | 003/2021 | -1564.56
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Cash Discount earned | TRAFFIC MANAGEMENT INC | 004/2021 | -389.24
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 733.32
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 2266.66
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 27229.39
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | IT Device OH | Not assigned | 001/2021 | 126.9
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | IT Device OH | Not assigned | 002/2021 | 727.5
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | IT Device OH | Not assigned | 003/2021 | 4778.79
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Minor Material OH | Not assigned | 002/2021 | 8835.2
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Minor Material OH | Not assigned | 003/2021 | -1896.28
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 993.29
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 3070.26
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 36882.91
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 335.6
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 456.81
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Other Land Fees | PALM SRINGS VILLAGE 309 LLC | 003/2021 | 1000
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 440.1
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 2523.2
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 16574.54
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Labor Internal | Administrative Services - Double Time | Not assigned | 003/2021 | 30.35
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 10.72
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 51.09
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.6
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.63
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Other | Benefits OH | Not assigned | 003/2021 | 95.2
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 17.2
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 93.41
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Other | IT Device OH | Not assigned | 003/2021 | 9.77
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 6.42
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 33.88
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 44.98
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.54
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.46
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Other | Benefits OH | Not assigned | 003/2021 | 85.33
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 15.42
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 82.24
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Other | IT Device OH | Not assigned | 003/2021 | 8.76
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 30.36
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Labor Internal | Administrative Services - Double Time | Not assigned | 003/2021 | 30.35
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 10.72
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 51.09
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.6
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.63
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Other | Benefits OH | Not assigned | 003/2021 | 95.2
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 17.2
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 93.41
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Other | IT Device OH | Not assigned | 003/2021 | 9.77
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 6.42
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 33.88
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 44.98
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.54
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.46
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Other | Benefits OH | Not assigned | 003/2021 | 85.33
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Other | Building Service Overhead | Not assigned | 003/2021 | 15.42
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Other | Capitalized A&G | Not assigned | 003/2021 | 82.24
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Other | IT Device OH | Not assigned | 003/2021 | 8.76
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 30.36
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 44.98
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.54
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.46
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Other | Benefits OH | Not assigned | 003/2021 | 85.33
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Other | Building Service Overhead | Not assigned | 003/2021 | 15.42
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Other | Capitalized A&G | Not assigned | 003/2021 | 82.24
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Other | IT Device OH | Not assigned | 003/2021 | 8.76
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 30.36
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 91.58
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 259.2
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 97.18
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.08
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.93
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Other | Benefits OH | Not assigned | 003/2021 | 169.69
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 30.67
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 177.68
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Other | IT Device OH | Not assigned | 003/2021 | 17.42
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 54.85
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 60.38
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 22.89
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 64.8
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 58.03
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.68
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.82
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Other | Benefits OH | Not assigned | 003/2021 | 106.42
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 19.24
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 106.1
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Other | IT Device OH | Not assigned | 003/2021 | 10.92
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 13.71
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 37.86
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 22.89
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 64.8
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 58.03
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.68
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.82
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Other | Benefits OH | Not assigned | 003/2021 | 106.42
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 19.24
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 106.1
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Other | IT Device OH | Not assigned | 003/2021 | 10.92
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 13.71
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 37.86
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Contract | Construction Inspection | CANUS CORPORATION | 003/2021 | 7179.81
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Contract | Contracts | ARBORWORKS INC | 003/2021 | 54902.59
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 9226.22
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 18490.23
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Contract | Helicopter Contract | Not assigned | 003/2021 | 199548.73
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Construction | Not assigned | 003/2021 | 45548.92
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Construction Doubletime Services | Not assigned | 003/2021 | 58591.86
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 33.79
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Electric Estimating | Not assigned | 001/2021 | 236.84
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Electric Estimating Doubletime | Not assigned | 001/2021 | 473.6
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 1091
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1182.94
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1129.2
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 174.1
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 34.82
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Hours - Overtime | Not assigned | 002/2021 | 269.2
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Hours - Overtime | Not assigned | 003/2021 | 403.79
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Hours - Straight Time | Not assigned | 002/2021 | 4696.96
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Hours - Straight Time | Not assigned | 003/2021 | 2038.3
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 610.69
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 602.7
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 36510.72
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 61.51
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 12.3
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Indirect Labor - IT | Not assigned | 002/2021 | 1852.38
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Indirect Labor - IT | Not assigned | 003/2021 | 910.9
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 003/2021 | 467.47
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 002/2021 | 315.9
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 003/2021 | 212.03
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Maintain & Operate Services | Not assigned | 002/2021 | 279.02
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Maintain & Operate Services | Not assigned | 003/2021 | 511
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Management Services | Not assigned | 003/2021 | 201.42
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Mapping | Not assigned | 003/2021 | 1206.97
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 397.87
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1365.27
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 22182.87
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Materials | Communication & Signaling Equipment | Not assigned | 002/2021 | 75.15
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Materials | Communication & Signaling Equipment | Not assigned | 003/2021 | 614.88
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 002/2021 | 1465.49
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Materials | Conductors, Cable & Wire Connectors | Not assigned | 003/2021 | 286.12
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Materials | Construction Supplies | Not assigned | 002/2021 | 1309.42
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Materials | Construction Supplies | Not assigned | 003/2021 | 5340.01
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Materials | Electl & Electronic Equipment Component | Not assigned | 002/2021 | 18457.02
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Materials | Electrical Specialties | Not assigned | 002/2021 | 3486.73
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Materials | Electrical Specialties | Not assigned | 003/2021 | 7760.77
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Materials | Fabricated Structures | Not assigned | 002/2021 | 629.86
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Materials | Material Burden | Not assigned | 002/2021 | 20916.8
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Materials | Material Burden | Not assigned | 003/2021 | 2210.88
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Materials | Materials Not Otherwise Classified | Not assigned | 002/2021 | 6758.66
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 002/2021 | 78054.12
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 32579.18
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 1714.01
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 002/2021 | 116.32
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Materials | Transformers, Regulators & Capacitors | Not assigned | 002/2021 | 1098.87
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Benefits OH | Not assigned | 001/2021 | 784.48
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Benefits OH | Not assigned | 002/2021 | 6457.31
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Benefits OH | Not assigned | 003/2021 | 42373.27
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Building Service Overhead | Not assigned | 001/2021 | 134.65
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Building Service Overhead | Not assigned | 002/2021 | 1108.23
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Building Service Overhead | Not assigned | 003/2021 | 7658.63
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Capitalized A&G | Not assigned | 001/2021 | 727.39
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Capitalized A&G | Not assigned | 002/2021 | 2495.97
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Capitalized A&G | Not assigned | 003/2021 | 40628.93
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Cash Discount earned | STELLA-JONES CORPORATION | 002/2021 | -1449.84
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Cellular Phone Use | VERIZON WIRELESS | 003/2021 | 0.57
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 408.03
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 402.68
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 24394.33
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | IT Device OH | Not assigned | 001/2021 | 76.43
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | IT Device OH | Not assigned | 002/2021 | 629.01
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | IT Device OH | Not assigned | 003/2021 | 4346.8
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Minor Material OH | Not assigned | 002/2021 | 11727.77
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Minor Material OH | Not assigned | 003/2021 | 1274.59
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 552.68
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 545.45
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 33042.75
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 36.84
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 7.37
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Operation Mgmt & Support - IT | Not assigned | 002/2021 | 797.07
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Operation Mgmt & Support - IT | Not assigned | 003/2021 | 391.96
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 265.05
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 2181.63
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 15076.26
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Other | Reimbursed Mileage Expense | JESSE RAMIREZ RODRIGUEZ | 003/2021 | 84
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 105.06
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 23.75
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Labor Internal | Design Overtime Services | Not assigned | 004/2021 | 615.54
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Labor Internal | Design Services | Not assigned | 004/2021 | 1917.36
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 6794.42
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Labor Internal | Electric Estimating | Not assigned | 004/2021 | 5112.95
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Labor Internal | Electric Estimating Doubletime | Not assigned | 003/2021 | 1184
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Labor Internal | Electric Estimating Doubletime | Not assigned | 004/2021 | 731.82
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 1396.48
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Labor Internal | Electric Estimating Overtime | Not assigned | 004/2021 | 410.37
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 75.72
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 3253.94
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.39
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 44.98
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 1933.16
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.54
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 24.38
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 1.47
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 65.79
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 89.88
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 3667.24
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 15.42
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 662.81
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 82.24
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 3534.22
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 50.59
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 2174.09
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Other | IT Device OH | Not assigned | 002/2021 | 8.76
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 376.21
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 68.52
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 2944.86
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 30.36
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 1304.79
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 261.25
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Labor Internal | Design Drafting Services | Not assigned | 002/2021 | 917.77
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Labor Internal | Design Drafting Services | Not assigned | 003/2021 | 5047.67
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Labor Internal | Design Drafting Services | Not assigned | 004/2021 | 557.18
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 002/2021 | 174.56
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 003/2021 | 196.38
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 1894.72
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 4144.71
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Labor Internal | Electric Estimating Doubletime | Not assigned | 003/2021 | 769.6
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 1003.72
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 4298.54
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1182.94
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1428.59
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 5302.17
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.78
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 848.72
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 3150.02
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 10.25
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 57.93
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 27.66
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 156.33
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Other | Benefits OH | Not assigned | 002/2021 | 1695.56
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Other | Benefits OH | Not assigned | 003/2021 | 5975.69
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 291
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 1080.06
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 1551.64
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 5758.87
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 954.5
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 3542.6
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Other | IT Device OH | Not assigned | 002/2021 | 165.17
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Other | IT Device OH | Not assigned | 003/2021 | 613.01
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1292.89
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 4798.54
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 572.84
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 2126.12
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 47.5
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 129.6
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor Internal | Administration | Not assigned | 003/2021 | 104.46
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor Internal | Construction | Not assigned | 003/2021 | 391.44
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 84.38
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 3537.8
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 11338.74
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor Internal | Electric Estimating | Not assigned | 004/2021 | 262.2
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor Internal | Electric Estimating Doubletime | Not assigned | 003/2021 | 355.2
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 480.04
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 4538.56
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 223.35
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1927.44
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1437.77
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 6319.03
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 94.14
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 32.4
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor Internal | Mapping | Not assigned | 003/2021 | 4.42
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 854.17
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 3807.8
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 10.32
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 65.27
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 27.83
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 176.14
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Other | Benefits OH | Not assigned | 002/2021 | 1706.46
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Other | Benefits OH | Not assigned | 003/2021 | 7208.34
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 292.86
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 1302.82
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 1561.61
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 6961.43
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 960.63
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 4221.99
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Other | IT Device OH | Not assigned | 002/2021 | 166.24
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Other | IT Device OH | Not assigned | 003/2021 | 739.45
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1301.19
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 5718.8
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 56.38
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 576.54
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 2564.71
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 105.06
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Labor Internal | Design Drafting Services | Not assigned | 003/2021 | 148.03
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 003/2021 | 785.52
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 5980.35
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 12389.89
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 2356.56
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 2051.08
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1228.43
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 446.71
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 3242.65
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 5363.5
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.32
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1926.46
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 3186.46
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 23.26
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 76.64
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 62.78
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 206.82
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | Benefits OH | Not assigned | 002/2021 | 3848.63
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | Benefits OH | Not assigned | 003/2021 | 6044.78
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | Building Service Overhead | Not assigned | 002/2021 | 660.54
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | Building Service Overhead | Not assigned | 003/2021 | 1092.54
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | Capitalized A&G | Not assigned | 002/2021 | 3521.96
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | Capitalized A&G | Not assigned | 003/2021 | 5825.5
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 2166.55
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 3583.58
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | IT Device OH | Not assigned | 002/2021 | 374.9
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | IT Device OH | Not assigned | 003/2021 | 620.1
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | Lodging | BRYCE J HAYES | 003/2021 | 412.07
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | Meals Expense | BRYCE J HAYES | 003/2021 | 88.34
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 2934.64
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 4854.05
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 1300.27
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 2150.69
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 23.75
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Labor Internal | Construction | Not assigned | 002/2021 | 37.23
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 12.74
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.74
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 0.34
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.07
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 7.57
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 44.99
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.09
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.74
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 0.25
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 15.12
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 85.35
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 2.59
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 15.42
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 13.84
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 82.27
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 8.51
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.61
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Other | IT Device OH | Not assigned | 002/2021 | 1.48
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 8.76
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 11.52
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.54
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 5.1
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 30.36
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Labor Internal | Account Services | Not assigned | 003/2021 | 16.41
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 4.25
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 48.28
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.57
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.54
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 89.74
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 16.22
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 88.28
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 9.21
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 31.92
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Labor Internal | Account Services | Not assigned | 003/2021 | 16.41
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 4.25
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 48.28
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.57
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.54
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Other | Benefits OH | Not assigned | 003/2021 | 89.74
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 16.22
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 88.28
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Other | IT Device OH | Not assigned | 003/2021 | 9.21
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 31.92
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Labor Internal | Account Services | Not assigned | 003/2021 | 49.23
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 12.75
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 54.89
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.63
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.69
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Other | Benefits OH | Not assigned | 003/2021 | 98.58
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 17.81
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 100.37
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Other | IT Device OH | Not assigned | 003/2021 | 10.12
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 35.07
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Labor Internal | Account Services | Not assigned | 003/2021 | 49.23
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 12.75
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 54.89
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.63
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.69
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Other | Benefits OH | Not assigned | 003/2021 | 98.58
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 17.81
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 100.37
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Other | IT Device OH | Not assigned | 003/2021 | 10.12
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 35.07
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Labor Internal | Account Services | Not assigned | 003/2021 | 16.41
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 4.25
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 114.47
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 324
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 113.53
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.25
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.37
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Other | Benefits OH | Not assigned | 003/2021 | 195.17
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Other | Building Service Overhead | Not assigned | 003/2021 | 35.27
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Other | Capitalized A&G | Not assigned | 003/2021 | 207.58
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Other | IT Device OH | Not assigned | 003/2021 | 20.03
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 68.56
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 69.44
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Labor Internal | Account Services | Not assigned | 003/2021 | 16.41
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 4.25
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 48.28
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.57
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.54
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Other | Benefits OH | Not assigned | 003/2021 | 89.74
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Other | Building Service Overhead | Not assigned | 003/2021 | 16.22
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Other | Capitalized A&G | Not assigned | 003/2021 | 88.28
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Other | IT Device OH | Not assigned | 003/2021 | 9.21
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 31.92
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Contract | Construction Inspection | PRO ENERGY SERVICES GROUP LLC | 002/2021 | 8493.49
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Contract | Construction Inspection | PRO ENERGY SERVICES GROUP LLC | 003/2021 | -8493.49
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Labor Internal | Account Services | Not assigned | 003/2021 | 16.41
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 4.25
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 8.64
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 67.08
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Labor Internal | Mapping | Not assigned | 002/2021 | 25.48
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Labor Internal | Mapping | Not assigned | 003/2021 | -25.48
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 5.13
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 43.15
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 6.75
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 7.32
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Other | AFUDC-Equity | Not assigned | 002/2021 | 18.22
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Other | AFUDC-Equity | Not assigned | 003/2021 | 19.75
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Other | Benefits OH | Not assigned | 002/2021 | 10.26
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Other | Benefits OH | Not assigned | 003/2021 | 80.01
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Other | Building Service Overhead | Not assigned | 002/2021 | 1.76
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Other | Building Service Overhead | Not assigned | 003/2021 | 14.46
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Other | Capitalized A&G | Not assigned | 002/2021 | 9.38
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Other | Capitalized A&G | Not assigned | 003/2021 | 78.9
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 5.77
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 44.82
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Other | IT Device OH | Not assigned | 002/2021 | 1
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Other | IT Device OH | Not assigned | 003/2021 | 8.21
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 7.82
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 60.7
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 3.46
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 28.46
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Labor Internal | Account Services | Not assigned | 003/2021 | 16.41
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 4.25
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 22.89
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 64.8
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 61.33
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.71
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.9
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Other | Benefits OH | Not assigned | 003/2021 | 110.83
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Other | Building Service Overhead | Not assigned | 003/2021 | 20.04
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Other | Capitalized A&G | Not assigned | 003/2021 | 112.14
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Other | IT Device OH | Not assigned | 003/2021 | 11.37
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 13.71
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 39.42
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Labor Internal | Account Services | Not assigned | 003/2021 | 16.41
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 4.25
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 22.89
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 64.8
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 61.33
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.71
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.9
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Other | Benefits OH | Not assigned | 003/2021 | 110.83
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 20.04
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 112.14
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Other | IT Device OH | Not assigned | 003/2021 | 11.37
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 13.71
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 39.42
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Labor Internal | Account Services | Not assigned | 003/2021 | 49.23
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 12.75
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 54.89
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.63
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.69
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Other | Benefits OH | Not assigned | 003/2021 | 98.58
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 17.81
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 100.37
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Other | IT Device OH | Not assigned | 003/2021 | 10.12
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 35.07
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Labor Internal | Account Services | Not assigned | 003/2021 | 16.41
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 223.35
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 4.25
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.72
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 48.28
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.57
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.54
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Other | Benefits OH | Not assigned | 003/2021 | 89.74
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 16.22
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 88.28
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.59
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Other | IT Device OH | Not assigned | 003/2021 | 9.21
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.52
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 31.92
35228449 | RIO DELL STORM REBUILD | Contract | Contracts | CANUS CORPORATION | 002/2021 | 46764.92
35228449 | RIO DELL STORM REBUILD | Contract | Contracts | CANUS CORPORATION | 003/2021 | 75408.57
35228449 | RIO DELL STORM REBUILD | Contract | Contracts | WRIGHT TREE SERVICE OF THE WEST INC | 003/2021 | 49801.05
35228449 | RIO DELL STORM REBUILD | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 003/2021 | 35692.91
35228449 | RIO DELL STORM REBUILD | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 004/2021 | -17319.24
35228449 | RIO DELL STORM REBUILD | Contract | Electric Construction Contract | SJL CONSTRUCTION INC | 003/2021 | 868921.12
35228449 | RIO DELL STORM REBUILD | Contract | Electric Construction Contract | SJL CONSTRUCTION INC | 004/2021 | 3970
35228449 | RIO DELL STORM REBUILD | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 22294.25
35228449 | RIO DELL STORM REBUILD | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 1037.55
35228449 | RIO DELL STORM REBUILD | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -1037.55
35228449 | RIO DELL STORM REBUILD | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 15730
35228449 | RIO DELL STORM REBUILD | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -11000
35228449 | RIO DELL STORM REBUILD | Contract | Helicopter Contract | Not assigned | 002/2021 | 42632.1
35228449 | RIO DELL STORM REBUILD | Contract | Helicopter Contract | Not assigned | 003/2021 | 166710.6
35228449 | RIO DELL STORM REBUILD | Labor Internal | Administration | Not assigned | 002/2021 | 974.96
35228449 | RIO DELL STORM REBUILD | Labor Internal | Administration | Not assigned | 003/2021 | 69.64
35228449 | RIO DELL STORM REBUILD | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 88.01
35228449 | RIO DELL STORM REBUILD | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 831.39
35228449 | RIO DELL STORM REBUILD | Labor Internal | Apprentice | Not assigned | 002/2021 | 238.49
35228449 | RIO DELL STORM REBUILD | Labor Internal | Apprentice DT | Not assigned | 003/2021 | 1017.71
35228449 | RIO DELL STORM REBUILD | Labor Internal | Apprentice OT | Not assigned | 002/2021 | 3212.31
35228449 | RIO DELL STORM REBUILD | Labor Internal | Apprentice OT | Not assigned | 003/2021 | 2543.09
35228449 | RIO DELL STORM REBUILD | Labor Internal | Construction | Not assigned | 002/2021 | 12828.34
35228449 | RIO DELL STORM REBUILD | Labor Internal | Construction | Not assigned | 003/2021 | 5519.34
35228449 | RIO DELL STORM REBUILD | Labor Internal | Construction Doubletime Services | Not assigned | 002/2021 | 15823.83
35228449 | RIO DELL STORM REBUILD | Labor Internal | Construction Doubletime Services | Not assigned | 003/2021 | 2045.97
35228449 | RIO DELL STORM REBUILD | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 44762.47
35228449 | RIO DELL STORM REBUILD | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 9117.91
35228449 | RIO DELL STORM REBUILD | Labor Internal | Design Drafting Services - Overtime | Not assigned | 001/2021 | 785.52
35228449 | RIO DELL STORM REBUILD | Labor Internal | Design Overtime Services | Not assigned | 002/2021 | 1047.36
35228449 | RIO DELL STORM REBUILD | Labor Internal | Design Services | Not assigned | 002/2021 | 473.68
35228449 | RIO DELL STORM REBUILD | Labor Internal | Design Services Double Time | Not assigned | 001/2021 | 1213.6
35228449 | RIO DELL STORM REBUILD | Labor Internal | Design Services Double Time | Not assigned | 002/2021 | 2841.6
35228449 | RIO DELL STORM REBUILD | Labor Internal | Electric Estimating | Not assigned | 002/2021 | 710.52
35228449 | RIO DELL STORM REBUILD | Labor Internal | Electric Estimating Doubletime | Not assigned | 002/2021 | 1598.4
35228449 | RIO DELL STORM REBUILD | Labor Internal | Electric Estimating Overtime | Not assigned | 001/2021 | 523.68
35228449 | RIO DELL STORM REBUILD | Labor Internal | Electric Estimating Overtime | Not assigned | 002/2021 | 2051.08
35228449 | RIO DELL STORM REBUILD | Labor Internal | Engineering Doubletime | Not assigned | 002/2021 | 3107.83
35228449 | RIO DELL STORM REBUILD | Labor Internal | Engineering Services - OT | Not assigned | 002/2021 | 2308.08
35228449 | RIO DELL STORM REBUILD | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 113.79
35228449 | RIO DELL STORM REBUILD | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 37.23
35228449 | RIO DELL STORM REBUILD | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 330.79
35228449 | RIO DELL STORM REBUILD | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 295.97
35228449 | RIO DELL STORM REBUILD | Labor Internal | Environmental Services | Not assigned | 002/2021 | 940.14
35228449 | RIO DELL STORM REBUILD | Labor Internal | Environmental Services | Not assigned | 003/2021 | 417.84
35228449 | RIO DELL STORM REBUILD | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 855.23
35228449 | RIO DELL STORM REBUILD | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 14283
35228449 | RIO DELL STORM REBUILD | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 8057.09
35228449 | RIO DELL STORM REBUILD | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 1076.4
35228449 | RIO DELL STORM REBUILD | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 593.42
35228449 | RIO DELL STORM REBUILD | Labor Internal | Indirect Labor - Gas | Not assigned | 002/2021 | 19321.56
35228449 | RIO DELL STORM REBUILD | Labor Internal | Indirect Labor - Gas | Not assigned | 003/2021 | 408.99
35228449 | RIO DELL STORM REBUILD | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 712.8
35228449 | RIO DELL STORM REBUILD | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 64.8
35228449 | RIO DELL STORM REBUILD | Labor Internal | Mapping | Not assigned | 002/2021 | 832.08
35228449 | RIO DELL STORM REBUILD | Labor Internal | Mapping | Not assigned | 003/2021 | 3388.84
35228449 | RIO DELL STORM REBUILD | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 508.09
35228449 | RIO DELL STORM REBUILD | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 19854.68
35228449 | RIO DELL STORM REBUILD | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 5352.68
35228449 | RIO DELL STORM REBUILD | Labor Internal | Project Management Overtime | Not assigned | 002/2021 | 2591.45
35228449 | RIO DELL STORM REBUILD | Labor Internal | Project Management Overtime | Not assigned | 003/2021 | 110.87
35228449 | RIO DELL STORM REBUILD | Labor Internal | Project Management Services | Not assigned | 002/2021 | 744.5
35228449 | RIO DELL STORM REBUILD | Labor Internal | Project Management Services | Not assigned | 003/2021 | 1116.75
35228449 | RIO DELL STORM REBUILD | Labor Internal | Vegetation Management - Misc | Not assigned | 002/2021 | 250.88
35228449 | RIO DELL STORM REBUILD | Materials | Conductors, Cable & Wire Connectors | Not assigned | 002/2021 | 53825.82
35228449 | RIO DELL STORM REBUILD | Materials | Construction Supplies | Not assigned | 002/2021 | 927.69
35228449 | RIO DELL STORM REBUILD | Materials | Electl & Electronic Equipment Component | Not assigned | 002/2021 | 7367.43
35228449 | RIO DELL STORM REBUILD | Materials | Electrical Specialties | Not assigned | 002/2021 | 14390.57
35228449 | RIO DELL STORM REBUILD | Materials | Fabricated Structures | Not assigned | 002/2021 | 13480.26
35228449 | RIO DELL STORM REBUILD | Materials | Material Burden | Not assigned | 002/2021 | 50165.83
35228449 | RIO DELL STORM REBUILD | Materials | Material Burden | Not assigned | 003/2021 | -72.85
35228449 | RIO DELL STORM REBUILD | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 002/2021 | 240666.09
35228449 | RIO DELL STORM REBUILD | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 25490.19
35228449 | RIO DELL STORM REBUILD | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | -498.96
35228449 | RIO DELL STORM REBUILD | Materials | Printed Matls, Signs, Off Suppl & Furn | Not assigned | 002/2021 | 152.89
35228449 | RIO DELL STORM REBUILD | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 6.14
35228449 | RIO DELL STORM REBUILD | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 641.52
35228449 | RIO DELL STORM REBUILD | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1104.36
35228449 | RIO DELL STORM REBUILD | Other | AFUDC-Equity | Not assigned | 001/2021 | 16.56
35228449 | RIO DELL STORM REBUILD | Other | AFUDC-Equity | Not assigned | 002/2021 | 1731.09
35228449 | RIO DELL STORM REBUILD | Other | AFUDC-Equity | Not assigned | 003/2021 | 2980.01
35228449 | RIO DELL STORM REBUILD | Other | Benefits OH | Not assigned | 001/2021 | 1015.05
35228449 | RIO DELL STORM REBUILD | Other | Benefits OH | Not assigned | 002/2021 | 52884.99
35228449 | RIO DELL STORM REBUILD | Other | Benefits OH | Not assigned | 003/2021 | 10119.26
35228449 | RIO DELL STORM REBUILD | Other | Building Service Overhead | Not assigned | 001/2021 | 174.21
35228449 | RIO DELL STORM REBUILD | Other | Building Service Overhead | Not assigned | 002/2021 | 9076.5
35228449 | RIO DELL STORM REBUILD | Other | Building Service Overhead | Not assigned | 003/2021 | 1828.96
35228449 | RIO DELL STORM REBUILD | Other | Capitalized A&G | Not assigned | 001/2021 | 928.89
35228449 | RIO DELL STORM REBUILD | Other | Capitalized A&G | Not assigned | 002/2021 | 36298.4
35228449 | RIO DELL STORM REBUILD | Other | Capitalized A&G | Not assigned | 003/2021 | 9785.77
35228449 | RIO DELL STORM REBUILD | Other | Cash Discount earned | SJL CONSTRUCTION INC | 003/2021 | -17297.03
35228449 | RIO DELL STORM REBUILD | Other | Cash Discount earned | SJL CONSTRUCTION INC | 004/2021 | -81.4
35228449 | RIO DELL STORM REBUILD | Other | Cash Discount earned | STELLA-JONES CORPORATION | 003/2021 | -4470.29
35228449 | RIO DELL STORM REBUILD | Other | Fleet OH - Elec | Not assigned | 001/2021 | 571.41
35228449 | RIO DELL STORM REBUILD | Other | Fleet OH - Elec | Not assigned | 002/2021 | 9543.08
35228449 | RIO DELL STORM REBUILD | Other | Fleet OH - Elec | Not assigned | 003/2021 | 5383.29
35228449 | RIO DELL STORM REBUILD | Other | Fleet OH - Gas | Not assigned | 002/2021 | 16539.21
35228449 | RIO DELL STORM REBUILD | Other | Fleet OH - Gas | Not assigned | 003/2021 | 350.09
35228449 | RIO DELL STORM REBUILD | Other | IT Device OH | Not assigned | 001/2021 | 98.88
35228449 | RIO DELL STORM REBUILD | Other | IT Device OH | Not assigned | 002/2021 | 5151.52
35228449 | RIO DELL STORM REBUILD | Other | IT Device OH | Not assigned | 003/2021 | 1038.06
35228449 | RIO DELL STORM REBUILD | Other | Land Acquisition Services | ASSOCIATED RIGHT OF WAY SVCS INC | 003/2021 | 673.18
35228449 | RIO DELL STORM REBUILD | Other | Land Acquisition Services | ASSOCIATED RIGHT OF WAY SVCS INC | 004/2021 | -566.3
35228449 | RIO DELL STORM REBUILD | Other | Minor Material OH | Not assigned | 002/2021 | 28899.8
35228449 | RIO DELL STORM REBUILD | Other | Minor Material OH | Not assigned | 003/2021 | -40.66
35228449 | RIO DELL STORM REBUILD | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 774
35228449 | RIO DELL STORM REBUILD | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 12926.31
35228449 | RIO DELL STORM REBUILD | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 7291.81
35228449 | RIO DELL STORM REBUILD | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 644.69
35228449 | RIO DELL STORM REBUILD | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 355.41
35228449 | RIO DELL STORM REBUILD | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 29628.53
35228449 | RIO DELL STORM REBUILD | Other | Operation Mgmt & Support - Gas | Not assigned | 003/2021 | 627.16
35228449 | RIO DELL STORM REBUILD | Other | Other Expenses | BRIAN K VOSBURG | 003/2021 | 1008.28
35228449 | RIO DELL STORM REBUILD | Other | Other Expenses | MAURO CORTES | 003/2021 | 363.6
35228449 | RIO DELL STORM REBUILD | Other | Other Expenses | Not assigned | 002/2021 | 363.6
35228449 | RIO DELL STORM REBUILD | Other | Other Expenses | Not assigned | 003/2021 | -363.6
35228449 | RIO DELL STORM REBUILD | Other | Other Land Fees | HUMBOLDT REDWOOD COMPANY LLC | 003/2021 | 2000
35228449 | RIO DELL STORM REBUILD | Other | Payroll Taxes OH | Not assigned | 001/2021 | 342.93
35228449 | RIO DELL STORM REBUILD | Other | Payroll Taxes OH | Not assigned | 002/2021 | 17867.32
35228449 | RIO DELL STORM REBUILD | Other | Payroll Taxes OH | Not assigned | 003/2021 | 3600.41
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 341.98
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 475
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 518.4
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Labor Internal | Design Drafting Services - Overtime | Not assigned | 003/2021 | 414.58
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 141.37
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 211.77
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 81
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Labor Internal | Management Services | Not assigned | 002/2021 | 4032.62
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Labor Internal | Management Services | Not assigned | 003/2021 | 4827.38
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Labor Internal | Mapping | Not assigned | 003/2021 | 2.45
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 204.71
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 5.34
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 19.93
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Other | AFUDC-Equity | Not assigned | 002/2021 | 14.4
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Other | AFUDC-Equity | Not assigned | 003/2021 | 53.78
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Other | Benefits OH | Not assigned | 002/2021 | 782.42
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Other | Benefits OH | Not assigned | 003/2021 | 1243.79
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Other | Building Service Overhead | Not assigned | 002/2021 | 134.29
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Other | Building Service Overhead | Not assigned | 003/2021 | 224.8
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Other | Capitalized A&G | Not assigned | 002/2021 | 1484.81
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Other | Capitalized A&G | Not assigned | 003/2021 | 2151.7
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Other | Fleet OH - Elec | Not assigned | 003/2021 | 94.45
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Other | IT Device OH | Not assigned | 002/2021 | 76.21
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Other | IT Device OH | Not assigned | 003/2021 | 127.58
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 127.94
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 126.83
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Other | Payroll Taxes OH | Not assigned | 002/2021 | 264.34
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | Other | Payroll Taxes OH | Not assigned | 003/2021 | 442.52
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 23.75
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Labor Internal | Account Services | Not assigned | 002/2021 | 16.41
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Labor Internal | Administrative Services - OT | Not assigned | 002/2021 | 88.01
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 335.03
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 4.25
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 239.77
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 0.02
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 31.09
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 45.79
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 129.6
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.07
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 163.48
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 26.11
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Labor Internal | Project Management Services | Not assigned | 002/2021 | 372.25
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.94
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 19.52
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 5.22
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 52.66
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 319.38
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 42.2
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 54.82
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 7.62
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 298.87
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 47.75
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 160.2
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 0.02
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | IT Device OH | Not assigned | 002/2021 | 31.1
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 4.33
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 216.99
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 0.02
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 18.62
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 27.42
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 107.89
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 15
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Other | Permits/FeesLand Surveying Services | MARK THOMAS & COMPANY INC | 003/2021 | 19497.02
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 23.75
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 32.4
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Labor Internal | Construction | Not assigned | 002/2021 | 37.23
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 110.87
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 297.8
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 50.66
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 100.97
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 57.23
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 129.6
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 004/2021 | 97.2
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Labor Internal | Management Services | Not assigned | 003/2021 | 699.34
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Labor Internal | Mapping | Not assigned | 002/2021 | 1.33
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.07
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 30.1
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 92.62
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.36
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3.11
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Other | AFUDC-Equity | Not assigned | 002/2021 | 0.98
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 8.39
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Other | Benefits OH | Not assigned | 002/2021 | 60.14
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 364.06
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Other | Building Service Overhead | Not assigned | 002/2021 | 10.31
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 65.79
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Other | Capitalized A&G | Not assigned | 002/2021 | 55.02
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 426.83
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 33.84
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 225.87
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Other | IT Device OH | Not assigned | 002/2021 | 5.86
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 37.35
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 45.85
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 305.95
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 34.28
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 20.32
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 129.53
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 23.75
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Labor Internal | Construction | Not assigned | 002/2021 | 37.23
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 110.87
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 297.8
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 50.66
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 100.97
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Labor Internal | Management Services | Not assigned | 003/2021 | 107.59
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Labor Internal | Mapping | Not assigned | 002/2021 | 1.33
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 0.07
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 30.1
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 59.99
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.36
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.67
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Other | AFUDC-Equity | Not assigned | 002/2021 | 0.98
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4.49
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Other | Benefits OH | Not assigned | 002/2021 | 60.14
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Other | Benefits OH | Not assigned | 003/2021 | 144.18
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Other | Building Service Overhead | Not assigned | 002/2021 | 10.31
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 26.06
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Other | Capitalized A&G | Not assigned | 002/2021 | 55.02
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 149.29
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 33.84
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 91.84
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Other | IT Device OH | Not assigned | 002/2021 | 5.86
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Other | IT Device OH | Not assigned | 003/2021 | 14.78
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 45.85
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 124.4
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 20.32
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 51.3
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 23.75
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Labor Internal | Account Services | Not assigned | 003/2021 | 65.63
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Labor Internal | Construction | Not assigned | 002/2021 | 297.8
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Labor Internal | Construction | Not assigned | 003/2021 | 893.4
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 175.8
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 670.05
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 609.35
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 16.99
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 161.46
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 532.76
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 215.28
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Labor Internal | Mapping | Not assigned | 002/2021 | 2.68
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Labor Internal | Mapping | Not assigned | 003/2021 | 8.11
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 95.93
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 452.45
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.16
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 7.53
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3.13
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 20.32
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Other | Benefits OH | Not assigned | 002/2021 | 191.64
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Other | Benefits OH | Not assigned | 003/2021 | 816.38
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Other | Building Service Overhead | Not assigned | 002/2021 | 32.89
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 147.55
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Other | Capitalized A&G | Not assigned | 002/2021 | 175.37
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 827.17
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 107.88
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 355.96
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Other | IT Device OH | Not assigned | 002/2021 | 18.67
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Other | IT Device OH | Not assigned | 003/2021 | 83.76
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 146.13
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 482.16
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 128.93
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 64.74
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 290.44
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Labor Internal | Construction | Not assigned | 002/2021 | 595.6
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Labor Internal | Construction | Not assigned | 003/2021 | -595.6
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Labor Internal | Electric Estimating | Not assigned | 004/2021 | 65.55
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 35.16
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 203.73
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | -191.81
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Labor Internal | Mapping | Not assigned | 002/2021 | 5.36
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Labor Internal | Mapping | Not assigned | 003/2021 | -5.36
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 121.03
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | -113.95
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.46
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.56
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3.94
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4.2
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Other | Benefits OH | Not assigned | 002/2021 | 241.8
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Other | Benefits OH | Not assigned | 003/2021 | -216.17
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Other | Building Service Overhead | Not assigned | 002/2021 | 41.49
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Other | Building Service Overhead | Not assigned | 003/2021 | -39.06
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Other | Capitalized A&G | Not assigned | 002/2021 | 221.27
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Other | Capitalized A&G | Not assigned | 003/2021 | -208.32
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 136.11
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | -128.15
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Other | IT Device OH | Not assigned | 002/2021 | 23.55
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Other | IT Device OH | Not assigned | 003/2021 | -22.18
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 184.37
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | -173.58
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 81.69
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | -76.92
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Labor Internal | Account Services | Not assigned | 003/2021 | 65.63
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 259.2
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Labor Internal | Construction | Not assigned | 002/2021 | 595.6
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Labor Internal | Construction | Not assigned | 003/2021 | 744.5
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 140.64
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 372.25
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Labor Internal | Hours - Overtime | Not assigned | 003/2021 | 269.2
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 16.99
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 251.41
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 380.85
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 91.58
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Labor Internal | Indirect Labor - IT | Not assigned | 003/2021 | 100.41
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Labor Internal | Mapping | Not assigned | 002/2021 | 5.36
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Labor Internal | Mapping | Not assigned | 003/2021 | 6.7
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 149.35
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 345.9
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.8
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 7.54
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | AFUDC-Equity | Not assigned | 002/2021 | 4.87
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 20.35
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | Benefits OH | Not assigned | 002/2021 | 298.37
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | Benefits OH | Not assigned | 003/2021 | 617.3
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | Building Service Overhead | Not assigned | 002/2021 | 51.2
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 111.57
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | Capitalized A&G | Not assigned | 002/2021 | 273.05
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 632.38
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 167.96
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 254.46
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | IT Device OH | Not assigned | 002/2021 | 29.07
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | IT Device OH | Not assigned | 003/2021 | 63.35
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 227.52
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 344.68
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 54.84
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | Operation Mgmt & Support - IT | Not assigned | 003/2021 | 43.21
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 100.8
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 219.62
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 003/2021 | 20264.81
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Contract | Engr/Dsgn and Engr, Proc & Constr Contra | QUANTA ENERGY SERVICES LLC | 004/2021 | -20264.81
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 003/2021 | 536.88
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 285
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Labor Internal | Account Services | Not assigned | 003/2021 | 65.63
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Labor Internal | Administration | Not assigned | 002/2021 | 139.28
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Labor Internal | Administration | Not assigned | 003/2021 | 557.12
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Labor Internal | Administration | Not assigned | 004/2021 | 278.56
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 1273.02
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Labor Internal | Electric Estimating Overtime | Not assigned | 003/2021 | 305.48
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 407.41
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1747.51
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 16.99
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 138.11
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 1128.36
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 49.21
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 196.83
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Labor Internal | Mapping | Not assigned | 003/2021 | 2.47
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 110.1
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 795.78
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1.29
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 26.69
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3.47
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 72.02
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | Benefits OH | Not assigned | 002/2021 | 211.64
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | Benefits OH | Not assigned | 003/2021 | 1470.62
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | Building Service Overhead | Not assigned | 002/2021 | 36.33
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | Building Service Overhead | Not assigned | 003/2021 | 265.81
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | Capitalized A&G | Not assigned | 002/2021 | 201.29
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | Capitalized A&G | Not assigned | 003/2021 | 1454.84
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 92.27
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 753.9
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | IT Device OH | Not assigned | 002/2021 | 20.61
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | IT Device OH | Not assigned | 003/2021 | 150.85
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 125
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 1021.18
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 29.47
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 117.89
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 71.5
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 523.21
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Labor External | Consulting Services - Engineering | BENDER ROSENTHAL INC | 003/2021 | 522.5
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Labor Internal | Administration | Not assigned | 003/2021 | 139.28
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Labor Internal | Administration | Not assigned | 004/2021 | 139.28
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 221.74
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 229.68
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Labor Internal | Engineering/Mapping Services Overtime | Not assigned | 002/2021 | 107.42
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 417.84
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 69.64
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 114.28
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 76.38
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 354.85
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 666.15
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 1004.4
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 1328.4
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 3.57
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 270.18
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 425.12
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.94
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 10.7
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 7.94
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 28.86
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | Benefits OH | Not assigned | 002/2021 | 479.85
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | Benefits OH | Not assigned | 003/2021 | 699.66
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 82.36
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 126.47
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 493.94
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 777.21
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 76.35
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 51.03
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | IT Device OH | Not assigned | 002/2021 | 46.73
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | IT Device OH | Not assigned | 003/2021 | 71.78
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 103.42
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 69.12
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 212.53
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 398.98
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 162.12
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 248.94
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | Labor Internal | Construction | Not assigned | 003/2021 | 670.05
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 229.19
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 6.03
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 136.16
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.63
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4.41
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | Other | Benefits OH | Not assigned | 003/2021 | 258.31
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 46.69
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 248.93
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 153.14
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | Other | IT Device OH | Not assigned | 003/2021 | 26.49
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 207.42
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 91.91
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | Labor Internal | Construction | Not assigned | 003/2021 | 670.05
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 229.19
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | Labor Internal | Mapping | Not assigned | 003/2021 | 6.03
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 136.16
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.63
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4.41
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | Other | Benefits OH | Not assigned | 003/2021 | 258.31
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 46.69
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 248.93
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 153.14
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | Other | IT Device OH | Not assigned | 003/2021 | 26.49
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 207.42
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 91.91
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 221.74
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.85
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | Labor Internal | Mapping | Not assigned | 003/2021 | 2
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 45.06
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.54
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.46
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | Other | Benefits OH | Not assigned | 003/2021 | 85.49
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 15.45
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 82.38
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.67
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | Other | IT Device OH | Not assigned | 003/2021 | 8.77
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.64
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 30.41
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 259.2
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Administration | Not assigned | 003/2021 | 139.28
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 386.35
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 221.74
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Design Drafting Services | Not assigned | 003/2021 | 236.84
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Design Drafting Services | Not assigned | 004/2021 | 589.95
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 003/2021 | 305.48
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 004/2021 | 227.98
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 76.56
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 800.86
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 69.64
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 285.65
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 377.75
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 628.91
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 810
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 453.6
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Land Rights - Misc | Not assigned | 004/2021 | 129.6
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Mapping | Not assigned | 003/2021 | 2
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 215.34
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 528.21
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 2.26
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 10.19
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Other | AFUDC-Equity | Not assigned | 002/2021 | 6.1
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 27.49
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Other | Benefits OH | Not assigned | 002/2021 | 366.43
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Other | Benefits OH | Not assigned | 003/2021 | 901.22
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Other | Building Service Overhead | Not assigned | 002/2021 | 62.88
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 162.9
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Other | Capitalized A&G | Not assigned | 002/2021 | 393.68
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 965.68
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 190.85
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Other | IT Device OH | Not assigned | 002/2021 | 35.7
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Other | IT Device OH | Not assigned | 003/2021 | 92.45
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 258.51
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 226.24
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 376.66
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 123.79
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 320.66
35232960 | CWSP - DESCHUTES 11049718 PH1.2 | Labor Internal | Account Services | Not assigned | 003/2021 | 65.63
35232960 | CWSP - DESCHUTES 11049718 PH1.2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 16.99
35232960 | CWSP - DESCHUTES 11049718 PH1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 13.22
35232960 | CWSP - DESCHUTES 11049718 PH1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.12
35232960 | CWSP - DESCHUTES 11049718 PH1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.32
35232960 | CWSP - DESCHUTES 11049718 PH1.2 | Other | Benefits OH | Not assigned | 003/2021 | 17.66
35232960 | CWSP - DESCHUTES 11049718 PH1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 3.2
35232960 | CWSP - DESCHUTES 11049718 PH1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 24.16
35232960 | CWSP - DESCHUTES 11049718 PH1.2 | Other | IT Device OH | Not assigned | 003/2021 | 1.81
35232960 | CWSP - DESCHUTES 11049718 PH1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 6.28
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 110.87
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 151.01
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 89.11
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Labor Internal | Mapping | Not assigned | 003/2021 | 1
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 52.94
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.64
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.71
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 100.43
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 18.14
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 96.79
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 59.54
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 10.29
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 80.66
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 35.73
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.46
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.24
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 15
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.49
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Other | Benefits OH | Not assigned | 003/2021 | 28.45
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.14
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 27.42
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.87
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Other | IT Device OH | Not assigned | 003/2021 | 2.92
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 22.84
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.12
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.45
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.24
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 14.99
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.49
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Other | Benefits OH | Not assigned | 003/2021 | 28.44
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.14
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 27.41
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.86
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Other | IT Device OH | Not assigned | 003/2021 | 2.92
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 22.84
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.12
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.45
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.24
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 14.99
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.49
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Other | Benefits OH | Not assigned | 003/2021 | 28.44
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.14
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 27.41
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.86
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Other | IT Device OH | Not assigned | 003/2021 | 2.92
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 22.84
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.12
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.45
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.24
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 14.99
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.49
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Other | Benefits OH | Not assigned | 003/2021 | 28.44
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.14
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Other | Capitalized A&G | Not assigned | 003/2021 | 27.41
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.86
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Other | IT Device OH | Not assigned | 003/2021 | 2.92
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 22.84
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.12
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 110.87
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.45
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 63.16
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Labor Internal | Mapping | Not assigned | 003/2021 | 1
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 37.52
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.45
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.21
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Other | Benefits OH | Not assigned | 003/2021 | 71.18
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Other | Building Service Overhead | Not assigned | 003/2021 | 12.85
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Other | Capitalized A&G | Not assigned | 003/2021 | 68.6
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 42.2
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Other | IT Device OH | Not assigned | 003/2021 | 7.29
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 57.17
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 25.32
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.45
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.24
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 14.99
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.49
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Other | Benefits OH | Not assigned | 003/2021 | 28.44
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.14
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Other | Capitalized A&G | Not assigned | 003/2021 | 27.41
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.86
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Other | IT Device OH | Not assigned | 003/2021 | 2.92
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 22.84
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.12
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.45
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.24
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 14.99
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.49
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Other | Benefits OH | Not assigned | 003/2021 | 28.44
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.14
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Other | Capitalized A&G | Not assigned | 003/2021 | 27.41
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.86
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Other | IT Device OH | Not assigned | 003/2021 | 2.92
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 22.84
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.12
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.45
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.24
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 14.99
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.49
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Other | Benefits OH | Not assigned | 003/2021 | 28.44
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.14
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Other | Capitalized A&G | Not assigned | 003/2021 | 27.41
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.86
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Other | IT Device OH | Not assigned | 003/2021 | 2.92
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 22.84
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.12
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 110.87
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 37.92
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Labor Internal | Mapping | Not assigned | 003/2021 | 1
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 22.53
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.27
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.73
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Other | Benefits OH | Not assigned | 003/2021 | 42.74
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Other | Building Service Overhead | Not assigned | 003/2021 | 7.72
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Other | Capitalized A&G | Not assigned | 003/2021 | 41.19
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 25.34
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Other | IT Device OH | Not assigned | 003/2021 | 4.38
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 34.32
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 15.2
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Labor Internal | Design Drafting Services | Not assigned | 003/2021 | 148.03
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.45
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 75.42
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 44.8
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.54
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.45
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Other | Benefits OH | Not assigned | 003/2021 | 84.99
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 15.36
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 81.91
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 50.39
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Other | IT Device OH | Not assigned | 003/2021 | 8.72
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 68.26
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 30.24
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Labor Internal | Design Drafting Services | Not assigned | 004/2021 | 524.41
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 004/2021 | 91.19
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.45
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.24
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 14.99
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.49
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Other | Benefits OH | Not assigned | 003/2021 | 28.44
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.14
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 27.41
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.86
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Other | IT Device OH | Not assigned | 003/2021 | 2.92
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 22.84
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.12
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 110.87
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Labor Internal | Design Drafting Services | Not assigned | 003/2021 | 473.69
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 003/2021 | 349.12
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Labor Internal | Drafting Doubletime | Not assigned | 003/2021 | 177.6
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Labor Internal | Drafting Doubletime | Not assigned | 004/2021 | 304.93
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 148.9
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 427.54
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Labor Internal | Mapping | Not assigned | 003/2021 | 1
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 254
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 3.05
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 8.22
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Other | Benefits OH | Not assigned | 003/2021 | 481.85
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 87.08
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 464.37
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 285.66
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Other | IT Device OH | Not assigned | 003/2021 | 49.43
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 386.94
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 171.43
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 110.87
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.45
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 63.16
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Labor Internal | Mapping | Not assigned | 003/2021 | 1
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 37.52
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.45
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.21
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Other | Benefits OH | Not assigned | 003/2021 | 71.18
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 12.85
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 68.6
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 42.2
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Other | IT Device OH | Not assigned | 003/2021 | 7.29
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 57.17
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 25.32
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 229.68
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 69.64
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 77.86
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 24.6
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 60.29
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.7
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.89
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Other | Benefits OH | Not assigned | 003/2021 | 110.41
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Other | Building Service Overhead | Not assigned | 003/2021 | 19.96
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Other | Capitalized A&G | Not assigned | 003/2021 | 110.21
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 52.02
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Other | IT Device OH | Not assigned | 003/2021 | 11.33
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 70.47
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 14.74
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 39.29
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Labor Internal | Administration | Not assigned | 003/2021 | 139.28
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 153.12
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 383.02
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 69.64
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 51.91
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 184.53
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Labor Internal | Land Rights - Misc | Not assigned | 004/2021 | 129.6
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Labor Internal | Management Services | Not assigned | 003/2021 | 591.77
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 136.03
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 2.16
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 5.84
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Other | Benefits OH | Not assigned | 003/2021 | 395.63
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 71.51
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 466.58
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 168.72
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Other | IT Device OH | Not assigned | 003/2021 | 40.58
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 228.54
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 110.52
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 140.78
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 | Labor Internal | Administration | Not assigned | 003/2021 | 139.28
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 382.8
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 278.56
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 004/2021 | 69.64
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 129.77
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 147.62
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 161.25
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.69
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 4.57
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 | Other | Benefits OH | Not assigned | 003/2021 | 282.22
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 51.01
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 294.8
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 86.7
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 | Other | IT Device OH | Not assigned | 003/2021 | 28.95
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 117.44
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 88.41
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 100.42
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 76.56
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.95
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 15.42
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.5
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 | Other | Benefits OH | Not assigned | 003/2021 | 29.25
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.29
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 | Other | Capitalized A&G | Not assigned | 003/2021 | 28.19
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 17.34
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 | Other | IT Device OH | Not assigned | 003/2021 | 3
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 23.49
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.41
35235674 | FRRB - BIG BEND 1102 - B1 PH1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 76.56
35235674 | FRRB - BIG BEND 1102 - B1 PH1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.95
35235674 | FRRB - BIG BEND 1102 - B1 PH1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 15.42
35235674 | FRRB - BIG BEND 1102 - B1 PH1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35235674 | FRRB - BIG BEND 1102 - B1 PH1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.5
35235674 | FRRB - BIG BEND 1102 - B1 PH1 | Other | Benefits OH | Not assigned | 003/2021 | 29.25
35235674 | FRRB - BIG BEND 1102 - B1 PH1 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.29
35235674 | FRRB - BIG BEND 1102 - B1 PH1 | Other | Capitalized A&G | Not assigned | 003/2021 | 28.19
35235674 | FRRB - BIG BEND 1102 - B1 PH1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 17.34
35235674 | FRRB - BIG BEND 1102 - B1 PH1 | Other | IT Device OH | Not assigned | 003/2021 | 3
35235674 | FRRB - BIG BEND 1102 - B1 PH1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 23.49
35235674 | FRRB - BIG BEND 1102 - B1 PH1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.41
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 76.56
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.95
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 15.42
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.5
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | Other | Benefits OH | Not assigned | 003/2021 | 29.25
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.29
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | Other | Capitalized A&G | Not assigned | 003/2021 | 28.19
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 17.34
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | Other | IT Device OH | Not assigned | 003/2021 | 3
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 23.49
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.41
35235677 | FRRB - BIG BEND 1102 - B4 PH4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 76.56
35235677 | FRRB - BIG BEND 1102 - B4 PH4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.95
35235677 | FRRB - BIG BEND 1102 - B4 PH4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 15.42
35235677 | FRRB - BIG BEND 1102 - B4 PH4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35235677 | FRRB - BIG BEND 1102 - B4 PH4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.5
35235677 | FRRB - BIG BEND 1102 - B4 PH4 | Other | Benefits OH | Not assigned | 003/2021 | 29.25
35235677 | FRRB - BIG BEND 1102 - B4 PH4 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.29
35235677 | FRRB - BIG BEND 1102 - B4 PH4 | Other | Capitalized A&G | Not assigned | 003/2021 | 28.19
35235677 | FRRB - BIG BEND 1102 - B4 PH4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 17.34
35235677 | FRRB - BIG BEND 1102 - B4 PH4 | Other | IT Device OH | Not assigned | 003/2021 | 3
35235677 | FRRB - BIG BEND 1102 - B4 PH4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 23.49
35235677 | FRRB - BIG BEND 1102 - B4 PH4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.41
35235702 | FRRB - KANAKA 1101 - K3 PH3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 76.56
35235702 | FRRB - KANAKA 1101 - K3 PH3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.95
35235702 | FRRB - KANAKA 1101 - K3 PH3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 15.42
35235702 | FRRB - KANAKA 1101 - K3 PH3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35235702 | FRRB - KANAKA 1101 - K3 PH3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.5
35235702 | FRRB - KANAKA 1101 - K3 PH3 | Other | Benefits OH | Not assigned | 003/2021 | 29.25
35235702 | FRRB - KANAKA 1101 - K3 PH3 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.29
35235702 | FRRB - KANAKA 1101 - K3 PH3 | Other | Capitalized A&G | Not assigned | 003/2021 | 28.19
35235702 | FRRB - KANAKA 1101 - K3 PH3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 17.34
35235702 | FRRB - KANAKA 1101 - K3 PH3 | Other | IT Device OH | Not assigned | 003/2021 | 3
35235702 | FRRB - KANAKA 1101 - K3 PH3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 23.49
35235702 | FRRB - KANAKA 1101 - K3 PH3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.41
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 76.56
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.95
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 15.42
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.5
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 | Other | Benefits OH | Not assigned | 003/2021 | 29.25
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.29
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 | Other | Capitalized A&G | Not assigned | 003/2021 | 28.19
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 17.34
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 | Other | IT Device OH | Not assigned | 003/2021 | 3
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 23.49
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.41
35235704 | FRRB - KANAKA 1101 - K5 PH5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 153.12
35235704 | FRRB - KANAKA 1101 - K5 PH5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 51.91
35235704 | FRRB - KANAKA 1101 - K5 PH5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 30.84
35235704 | FRRB - KANAKA 1101 - K5 PH5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.37
35235704 | FRRB - KANAKA 1101 - K5 PH5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1
35235704 | FRRB - KANAKA 1101 - K5 PH5 | Other | Benefits OH | Not assigned | 003/2021 | 58.5
35235704 | FRRB - KANAKA 1101 - K5 PH5 | Other | Building Service Overhead | Not assigned | 003/2021 | 10.57
35235704 | FRRB - KANAKA 1101 - K5 PH5 | Other | Capitalized A&G | Not assigned | 003/2021 | 56.38
35235704 | FRRB - KANAKA 1101 - K5 PH5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 34.68
35235704 | FRRB - KANAKA 1101 - K5 PH5 | Other | IT Device OH | Not assigned | 003/2021 | 6
35235704 | FRRB - KANAKA 1101 - K5 PH5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 46.98
35235704 | FRRB - KANAKA 1101 - K5 PH5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 20.82
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Labor Internal | Design Drafting Services | Not assigned | 004/2021 | 524.41
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 004/2021 | 364.76
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.45
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.24
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 14.99
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.49
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Other | Benefits OH | Not assigned | 003/2021 | 28.44
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.14
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Other | Capitalized A&G | Not assigned | 003/2021 | 27.41
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.86
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Other | IT Device OH | Not assigned | 003/2021 | 2.92
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 22.84
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.12
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Labor Internal | Design Drafting Services - Overtime | Not assigned | 004/2021 | 273.58
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.45
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.24
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 14.99
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.49
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Other | Benefits OH | Not assigned | 003/2021 | 28.44
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.14
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Other | Capitalized A&G | Not assigned | 003/2021 | 27.41
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.86
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Other | IT Device OH | Not assigned | 003/2021 | 2.92
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 22.84
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.12
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Labor Internal | Account Services | Not assigned | 003/2021 | 89.82
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Labor Internal | Drafting Doubletime | Not assigned | 004/2021 | 60.99
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 74.45
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 23.25
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.24
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Labor Internal | Management Services | Not assigned | 003/2021 | 235.48
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 33.08
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.65
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.75
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Other | Benefits OH | Not assigned | 003/2021 | 95.99
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Other | Building Service Overhead | Not assigned | 003/2021 | 17.35
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Other | Capitalized A&G | Not assigned | 003/2021 | 147.18
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.86
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Other | IT Device OH | Not assigned | 003/2021 | 9.85
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 22.84
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 34.16
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.24
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 14.99
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 74.45
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.49
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Other | Benefits OH | Not assigned | 003/2021 | 28.44
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.14
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Other | Capitalized A&G | Not assigned | 003/2021 | 27.41
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.86
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Other | IT Device OH | Not assigned | 003/2021 | 2.92
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 22.84
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.12
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.24
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 14.99
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Labor Internal | Project Management Services | Not assigned | 003/2021 | 74.45
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.49
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Other | Benefits OH | Not assigned | 003/2021 | 28.44
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.14
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Other | Capitalized A&G | Not assigned | 003/2021 | 27.41
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 16.86
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Other | IT Device OH | Not assigned | 003/2021 | 2.92
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 22.84
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.12
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | Labor Internal | Account Services | Not assigned | 003/2021 | 16.41
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 4.25
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 3.3
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.03
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.08
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | Other | Benefits OH | Not assigned | 003/2021 | 4.41
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 0.8
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 6.04
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | Other | IT Device OH | Not assigned | 003/2021 | 0.45
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 1.56
35236982 | NCF - RG - K1101 - REMOVAL 33 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 153.12
35236982 | NCF - RG - K1101 - REMOVAL 33 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 51.91
35236982 | NCF - RG - K1101 - REMOVAL 33 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 30.84
35236982 | NCF - RG - K1101 - REMOVAL 33 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.37
35236982 | NCF - RG - K1101 - REMOVAL 33 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1
35236982 | NCF - RG - K1101 - REMOVAL 33 | Other | Benefits OH | Not assigned | 003/2021 | 58.5
35236982 | NCF - RG - K1101 - REMOVAL 33 | Other | Building Service Overhead | Not assigned | 003/2021 | 10.57
35236982 | NCF - RG - K1101 - REMOVAL 33 | Other | Capitalized A&G | Not assigned | 003/2021 | 56.38
35236982 | NCF - RG - K1101 - REMOVAL 33 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 34.68
35236982 | NCF - RG - K1101 - REMOVAL 33 | Other | IT Device OH | Not assigned | 003/2021 | 6
35236982 | NCF - RG - K1101 - REMOVAL 33 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 46.98
35236982 | NCF - RG - K1101 - REMOVAL 33 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 20.82
35236985 | NCF - RG - K1101- REMOVAL 28, 105,150 | Labor Internal | Management Services | Not assigned | 003/2021 | 235.48
35236985 | NCF - RG - K1101- REMOVAL 28, 105,150 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.31
35236985 | NCF - RG - K1101- REMOVAL 28, 105,150 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.84
35236985 | NCF - RG - K1101- REMOVAL 28, 105,150 | Other | Benefits OH | Not assigned | 003/2021 | 43.38
35236985 | NCF - RG - K1101- REMOVAL 28, 105,150 | Other | Building Service Overhead | Not assigned | 003/2021 | 7.84
35236985 | NCF - RG - K1101- REMOVAL 28, 105,150 | Other | Capitalized A&G | Not assigned | 003/2021 | 86.7
35236985 | NCF - RG - K1101- REMOVAL 28, 105,150 | Other | IT Device OH | Not assigned | 003/2021 | 4.45
35236985 | NCF - RG - K1101- REMOVAL 28, 105,150 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 15.44
35236989 | NCF - RG - K1101 - REMOVAL 1 | Labor Internal | Management Services | Not assigned | 003/2021 | 235.48
35236989 | NCF - RG - K1101 - REMOVAL 1 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.31
35236989 | NCF - RG - K1101 - REMOVAL 1 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.84
35236989 | NCF - RG - K1101 - REMOVAL 1 | Other | Benefits OH | Not assigned | 003/2021 | 43.38
35236989 | NCF - RG - K1101 - REMOVAL 1 | Other | Building Service Overhead | Not assigned | 003/2021 | 7.84
35236989 | NCF - RG - K1101 - REMOVAL 1 | Other | Capitalized A&G | Not assigned | 003/2021 | 86.7
35236989 | NCF - RG - K1101 - REMOVAL 1 | Other | IT Device OH | Not assigned | 003/2021 | 4.45
35236989 | NCF - RG - K1101 - REMOVAL 1 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 15.44
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 | Labor Internal | Management Services | Not assigned | 003/2021 | 161.39
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.17
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.47
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 | Other | Benefits OH | Not assigned | 003/2021 | 45.59
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 | Other | Building Service Overhead | Not assigned | 003/2021 | 8.24
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 | Other | Capitalized A&G | Not assigned | 003/2021 | 59.42
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 36.55
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 | Other | IT Device OH | Not assigned | 003/2021 | 4.68
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 49.51
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 16.21
35236993 | FRRB - WYANDOTTE 1103 - W4 PH4.9 | Labor Internal | Management Services | Not assigned | 003/2021 | 235.48
35236993 | FRRB - WYANDOTTE 1103 - W4 PH4.9 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.31
35236993 | FRRB - WYANDOTTE 1103 - W4 PH4.9 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.84
35236993 | FRRB - WYANDOTTE 1103 - W4 PH4.9 | Other | Benefits OH | Not assigned | 003/2021 | 43.38
35236993 | FRRB - WYANDOTTE 1103 - W4 PH4.9 | Other | Building Service Overhead | Not assigned | 003/2021 | 7.84
35236993 | FRRB - WYANDOTTE 1103 - W4 PH4.9 | Other | Capitalized A&G | Not assigned | 003/2021 | 86.7
35236993 | FRRB - WYANDOTTE 1103 - W4 PH4.9 | Other | IT Device OH | Not assigned | 003/2021 | 4.45
35236993 | FRRB - WYANDOTTE 1103 - W4 PH4.9 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 15.44
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 | Labor Internal | Account Services | Not assigned | 003/2021 | 59.88
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 15.5
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 | Labor Internal | Management Services | Not assigned | 003/2021 | 235.48
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 12.06
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.42
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.12
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 | Other | Benefits OH | Not assigned | 003/2021 | 59.49
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 | Other | Building Service Overhead | Not assigned | 003/2021 | 10.75
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 | Other | Capitalized A&G | Not assigned | 003/2021 | 108.75
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 | Other | IT Device OH | Not assigned | 003/2021 | 6.1
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 21.17
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 | Labor Internal | Account Services | Not assigned | 003/2021 | 59.88
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 15.5
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 | Labor Internal | Management Services | Not assigned | 003/2021 | 235.48
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 12.06
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.42
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.12
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 | Other | Benefits OH | Not assigned | 003/2021 | 59.49
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 | Other | Building Service Overhead | Not assigned | 003/2021 | 10.75
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 | Other | Capitalized A&G | Not assigned | 003/2021 | 108.75
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 | Other | IT Device OH | Not assigned | 003/2021 | 6.1
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 21.17
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 76.56
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.95
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 15.42
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.5
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 | Other | Benefits OH | Not assigned | 003/2021 | 29.25
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.29
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 28.19
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 17.34
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 | Other | IT Device OH | Not assigned | 003/2021 | 3
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 23.49
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.41
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 229.68
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 77.86
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 46.26
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.55
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.5
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 | Other | Benefits OH | Not assigned | 003/2021 | 87.75
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 15.86
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 84.57
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 52.02
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 | Other | IT Device OH | Not assigned | 003/2021 | 9
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 70.47
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 31.22
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 229.68
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 77.86
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 46.26
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.55
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.5
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 | Other | Benefits OH | Not assigned | 003/2021 | 87.75
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 15.86
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 84.57
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 52.02
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 | Other | IT Device OH | Not assigned | 003/2021 | 9
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 70.47
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 31.22
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 306.24
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 103.82
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 61.68
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.74
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 | Other | Benefits OH | Not assigned | 003/2021 | 117
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 | Other | Building Service Overhead | Not assigned | 003/2021 | 21.15
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 | Other | Capitalized A&G | Not assigned | 003/2021 | 112.76
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 69.36
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 | Other | IT Device OH | Not assigned | 003/2021 | 12.01
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 93.95
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 41.63
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 153.12
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 51.91
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 30.84
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.37
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 | Other | Benefits OH | Not assigned | 003/2021 | 58.5
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 | Other | Building Service Overhead | Not assigned | 003/2021 | 10.57
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 | Other | Capitalized A&G | Not assigned | 003/2021 | 56.38
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 34.68
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 | Other | IT Device OH | Not assigned | 003/2021 | 6
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 46.98
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 20.82
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 76.56
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 25.95
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 15.42
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.18
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 | Other | AFUDC-Equity | Not assigned | 003/2021 | 0.5
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 | Other | Benefits OH | Not assigned | 003/2021 | 29.25
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 | Other | Building Service Overhead | Not assigned | 003/2021 | 5.29
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 | Other | Capitalized A&G | Not assigned | 003/2021 | 28.19
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 17.34
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 | Other | IT Device OH | Not assigned | 003/2021 | 3
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 23.49
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 10.41
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 153.12
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 51.91
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 30.84
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.37
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 | Other | Benefits OH | Not assigned | 003/2021 | 58.5
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 | Other | Building Service Overhead | Not assigned | 003/2021 | 10.57
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 | Other | Capitalized A&G | Not assigned | 003/2021 | 56.38
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 34.68
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 | Other | IT Device OH | Not assigned | 003/2021 | 6
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 46.98
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 20.82
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 382.8
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 129.77
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 77.1
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.92
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.5
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 | Other | Benefits OH | Not assigned | 003/2021 | 146.25
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 | Other | Building Service Overhead | Not assigned | 003/2021 | 26.44
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 | Other | Capitalized A&G | Not assigned | 003/2021 | 140.95
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 86.7
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 | Other | IT Device OH | Not assigned | 003/2021 | 15
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 117.44
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 52.04
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 | Labor Internal | Land Rights - Misc | Not assigned | 004/2021 | 129.6
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 | Labor Internal | Management Services | Not assigned | 003/2021 | 430.36
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.63
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 | Other | AFUDC-Equity | Not assigned | 003/2021 | 1.71
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 | Other | Benefits OH | Not assigned | 003/2021 | 121.58
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 | Other | Building Service Overhead | Not assigned | 003/2021 | 21.98
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 | Other | Capitalized A&G | Not assigned | 003/2021 | 158.46
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 97.48
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 | Other | IT Device OH | Not assigned | 003/2021 | 12.47
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 132.03
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 43.26
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 | Labor Internal | Land Rights - Misc | Not assigned | 004/2021 | 162
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 | Labor Internal | Management Services | Not assigned | 003/2021 | 537.96
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.79
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.13
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 | Other | Benefits OH | Not assigned | 003/2021 | 151.98
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 | Other | Building Service Overhead | Not assigned | 003/2021 | 27.47
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 | Other | Capitalized A&G | Not assigned | 003/2021 | 198.08
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 121.85
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 | Other | IT Device OH | Not assigned | 003/2021 | 15.59
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 165.05
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 54.06
35237891 | FRRB - WYANDOTTE 1103 - W3 PH3.4 | Labor Internal | Land Rights - Misc | Not assigned | 004/2021 | 129.6
35238088 | REMG 531 - MARIPOSA 2101, SLAUGHTER HOUS | Labor Internal | Management Services | Not assigned | 003/2021 | 4650.76
35238088 | REMG 531 - MARIPOSA 2101, SLAUGHTER HOUS | Other | Benefits OH | Not assigned | 003/2021 | 856.85
35238088 | REMG 531 - MARIPOSA 2101, SLAUGHTER HOUS | Other | Building Service Overhead | Not assigned | 003/2021 | 154.87
35238088 | REMG 531 - MARIPOSA 2101, SLAUGHTER HOUS | Other | Capitalized A&G | Not assigned | 003/2021 | 1712.41
35238088 | REMG 531 - MARIPOSA 2101, SLAUGHTER HOUS | Other | IT Device OH | Not assigned | 003/2021 | 87.9
35238088 | REMG 531 - MARIPOSA 2101, SLAUGHTER HOUS | Other | Payroll Taxes OH | Not assigned | 003/2021 | 304.88
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 473.68
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 160.58
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 22.89
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 | Labor Internal | Land Surveying & Engineering Supprt-Misc | Not assigned | 003/2021 | 64.8
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 108.45
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1.28
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3.46
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 | Other | Benefits OH | Not assigned | 003/2021 | 202.07
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 | Other | Building Service Overhead | Not assigned | 003/2021 | 36.52
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 | Other | Capitalized A&G | Not assigned | 003/2021 | 198.27
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 107.29
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 | Other | IT Device OH | Not assigned | 003/2021 | 20.73
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 145.33
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 13.71
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 71.88
74011865 | PH.3 - RECON. ECHO SUMMIT 1101 11,600' | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 195.83
74011865 | PH.3 - RECON. ECHO SUMMIT 1101 11,600' | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 165.43
74011865 | PH.3 - RECON. ECHO SUMMIT 1101 11,600' | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 165.43
74011865 | PH.3 - RECON. ECHO SUMMIT 1101 11,600' | Other | AFUDC-Equity | Not assigned | 001/2021 | 446.4
74011865 | PH.3 - RECON. ECHO SUMMIT 1101 11,600' | Other | AFUDC-Equity | Not assigned | 002/2021 | 446.4
74011865 | PH.3 - RECON. ECHO SUMMIT 1101 11,600' | Other | AFUDC-Equity | Not assigned | 003/2021 | 446.4
74014860 | R2 REPL OH COND/ ALTERNTE BACKTIE CE2104 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 25.69
74014860 | R2 REPL OH COND/ ALTERNTE BACKTIE CE2104 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 21.7
74014860 | R2 REPL OH COND/ ALTERNTE BACKTIE CE2104 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 21.7
74014860 | R2 REPL OH COND/ ALTERNTE BACKTIE CE2104 | Other | AFUDC-Equity | Not assigned | 001/2021 | 58.55
74014860 | R2 REPL OH COND/ ALTERNTE BACKTIE CE2104 | Other | AFUDC-Equity | Not assigned | 002/2021 | 58.55
74014860 | R2 REPL OH COND/ ALTERNTE BACKTIE CE2104 | Other | AFUDC-Equity | Not assigned | 003/2021 | 58.55
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Contract | Construction Inspection | CANUS CORPORATION | 002/2021 | 2354.57
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 105.54
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 106.97
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 001/2021 | 216.18
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Labor Internal | Maint & Operate Doubletime Services | Not assigned | 002/2021 | 175.28
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Labor Internal | Maintain & Operate Services | Not assigned | 001/2021 | 95.16
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Labor Internal | Maintain & Operate Services | Not assigned | 002/2021 | 133.23
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Labor Internal | Mapping | Not assigned | 002/2021 | 7.06
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 62.7
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 63.55
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Other | Benefits OH | Not assigned | 001/2021 | 125.26
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Other | Benefits OH | Not assigned | 002/2021 | 126.97
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Other | Building Service Overhead | Not assigned | 001/2021 | 21.5
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Other | Building Service Overhead | Not assigned | 002/2021 | 21.79
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Other | Capitalized A&G | Not assigned | 001/2021 | 114.64
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Other | Capitalized A&G | Not assigned | 002/2021 | 116.19
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Other | Fleet OH - Elec | Not assigned | 001/2021 | 70.52
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Other | Fleet OH - Elec | Not assigned | 002/2021 | 71.48
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Other | IT Device OH | Not assigned | 001/2021 | 12.2
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Other | IT Device OH | Not assigned | 002/2021 | 12.36
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 95.52
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 96.82
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Other | Payroll Taxes OH | Not assigned | 001/2021 | 42.32
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | Other | Payroll Taxes OH | Not assigned | 002/2021 | 42.9
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Contract | Construction Inspection | CANUS CORPORATION | 002/2021 | 1778.75
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 1.81
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Labor Internal | Mapping | Not assigned | 002/2021 | 5.34
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 1.08
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Materials | Electl & Electronic Equipment Component | Not assigned | 001/2021 | 115.84
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Materials | Material Burden | Not assigned | 001/2021 | 16.91
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Other | Benefits OH | Not assigned | 001/2021 | 3.28
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Other | Benefits OH | Not assigned | 002/2021 | 2.15
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Other | Building Service Overhead | Not assigned | 001/2021 | 0.56
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Other | Building Service Overhead | Not assigned | 002/2021 | 0.37
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Other | Capitalized A&G | Not assigned | 002/2021 | 1.97
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 1.21
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Other | IT Device OH | Not assigned | 001/2021 | 0.32
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Other | IT Device OH | Not assigned | 002/2021 | 0.21
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Other | Minor Material OH | Not assigned | 001/2021 | 9.44
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 1.64
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 1.1
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.73
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Contract | Contracts | WILHELM LLC | 004/2021 | -2480.5
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Contract | Contracts | Not assigned | 002/2021 | -262939.11
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Labor Internal | Account Services | Not assigned | 002/2021 | 32.82
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Labor Internal | Account Services | Not assigned | 003/2021 | 131.28
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 297.8
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1116.75
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 446.7
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 8.5
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 33.99
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 100.95
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 111.17
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 151.43
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 22.89
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 64.8
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Labor Internal | Mapping | Not assigned | 002/2021 | -788.82
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 73.03
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 72.65
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 116.41
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Benefits OH | Not assigned | 001/2021 | 142.04
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Benefits OH | Not assigned | 002/2021 | 141.24
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Benefits OH | Not assigned | 003/2021 | 205.99
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Billing Credit - CIAC Non Taxable | Not assigned | 003/2021 | 14895
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Building Service Overhead | Not assigned | 001/2021 | 24.39
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Building Service Overhead | Not assigned | 002/2021 | 24.24
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Building Service Overhead | Not assigned | 003/2021 | 37.23
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Capitalized A&G | Not assigned | 001/2021 | 133.51
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Capitalized A&G | Not assigned | 002/2021 | 132.83
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Capitalized A&G | Not assigned | 003/2021 | 212.81
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Encroachment Permit Fees | COUNTY OF SONOMA | 003/2021 | 992
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 67.45
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 74.27
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 101.18
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | IT Device OH | Not assigned | 001/2021 | 13.83
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | IT Device OH | Not assigned | 002/2021 | 13.77
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | IT Device OH | Not assigned | 003/2021 | 21.12
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 91.37
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 100.61
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 137.05
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 13.71
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 47.98
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 47.72
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 73.29
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Contract | Contracts | CANUS CORPORATION | 001/2021 | 1084.18
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Contract | Contracts | CANUS CORPORATION | 002/2021 | 787.6
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Contract | Contracts | THE ORIGINAL MOWBRAY'S TREE SERVICE | 001/2021 | -78589.16
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Contract | Contracts | THE ORIGINAL MOWBRAY'S TREE SERVICE | 003/2021 | 2798.85
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Contract | Electric Construction Contract | PIKE CORPORATION | 003/2021 | 2730
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 002/2021 | 128277.43
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Contract | Electric Construction Contract | Not assigned | 001/2021 | -94376.57
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Contract | Electric Construction Contract | Not assigned | 002/2021 | -128277.43
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Labor Internal | Construction | Not assigned | 001/2021 | -503.66
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 831.53
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 243.74
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -62.66
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 0.8
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 5.63
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 86.11
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Labor Internal | Mapping | Not assigned | 001/2021 | -512.7
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Labor Internal | Mapping | Not assigned | 002/2021 | 2.36
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Labor Internal | Mapping | Not assigned | 003/2021 | 16.59
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 11.86
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 0.48
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 3.34
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Materials | Electrical Specialties | Not assigned | 003/2021 | -924.41
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Materials | Material Burden | Not assigned | 003/2021 | -134.96
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Benefits OH | Not assigned | 001/2021 | 9.17
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Benefits OH | Not assigned | 002/2021 | 0.96
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Benefits OH | Not assigned | 003/2021 | -18.53
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Building Service Overhead | Not assigned | 001/2021 | 1.59
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Building Service Overhead | Not assigned | 002/2021 | 0.16
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Building Service Overhead | Not assigned | 003/2021 | -3.35
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Capitalized A&G | Not assigned | 001/2021 | 21.7
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Capitalized A&G | Not assigned | 002/2021 | 0.87
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Capitalized A&G | Not assigned | 003/2021 | 6.11
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Cash Discount earned | QUANTA ENERGY SERVICES LLC | 002/2021 | -2565.55
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Fleet OH - Elec | Not assigned | 001/2021 | -41.86
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Fleet OH - Elec | Not assigned | 002/2021 | 0.53
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Fleet OH - Elec | Not assigned | 003/2021 | 3.76
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | IT Device OH | Not assigned | 001/2021 | 0.9
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | IT Device OH | Not assigned | 002/2021 | 0.09
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | IT Device OH | Not assigned | 003/2021 | -1.9
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Minor Material OH | Not assigned | 003/2021 | -75.33
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -56.69
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 0.72
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 5.09
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 51.58
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Payroll Taxes OH | Not assigned | 001/2021 | 3.1
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Payroll Taxes OH | Not assigned | 002/2021 | 0.33
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | Other | Payroll Taxes OH | Not assigned | 003/2021 | -6.59
74022383 | CWSP-EL DORADO PH 2102 LR19542 PH 1.0 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 62.36
74022383 | CWSP-EL DORADO PH 2102 LR19542 PH 1.0 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 52.68
74022383 | CWSP-EL DORADO PH 2102 LR19542 PH 1.0 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 52.68
74022383 | CWSP-EL DORADO PH 2102 LR19542 PH 1.0 | Other | AFUDC-Equity | Not assigned | 001/2021 | 142.14
74022383 | CWSP-EL DORADO PH 2102 LR19542 PH 1.0 | Other | AFUDC-Equity | Not assigned | 002/2021 | 142.14
74022383 | CWSP-EL DORADO PH 2102 LR19542 PH 1.0 | Other | AFUDC-Equity | Not assigned | 003/2021 | 142.14
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Construction Management Contracts | TRC SOLUTIONS INC | 001/2021 | 1583.69
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Construction Management Contracts | TRC SOLUTIONS INC | 002/2021 | -875.69
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Contracts | CANUS CORPORATION | 001/2021 | 7602.9
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Contracts | CANUS CORPORATION | 002/2021 | 4330.39
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Contracts | CANUS CORPORATION | 003/2021 | 13428.6
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Contracts | CANUS CORPORATION | 004/2021 | 4367.65
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Contracts | EPPLER & EPPLER INC | 003/2021 | 46862.5
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Contracts | WILHELM LLC | 001/2021 | 122132.99
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Contracts | WILHELM LLC | 002/2021 | 12742.18
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Contracts | WILHELM LLC | 003/2021 | 19050.38
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Contracts | WILHELM LLC | 004/2021 | -40869.85
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Electric Construction Contract | PARMETER GENERAL ENGINEERS | 001/2021 | 44471.55
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Electric Construction Contract | PARMETER GENERAL ENGINEERS | 002/2021 | 53213.41
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Electric Construction Contract | PARMETER GENERAL ENGINEERS | 003/2021 | 56974.08
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Environmental Contract | AECOM TECHNICAL SERVICES INC | 002/2021 | 1288.52
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 741.01
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 325.63
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 1726.27
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -785.18
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Environmental Contract | HANFORD APPLIED RESTORATION & | 001/2021 | 1200
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Environmental Contract | HANFORD APPLIED RESTORATION & | 002/2021 | 2878
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Environmental Contract | HANFORD APPLIED RESTORATION & | 003/2021 | 1200
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Environmental Contract | HANFORD APPLIED RESTORATION & | 004/2021 | -1200
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -3000
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 6750
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 12695
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -1500
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Helicopter Contract | Not assigned | 003/2021 | 28266.75
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Traffic Control Contracts | DONAHOO INC | 001/2021 | 5900
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Traffic Control Contracts | DONAHOO INC | 002/2021 | 5197.5
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Contract | Traffic Control Contracts | DONAHOO INC | 003/2021 | 61690
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 43.05
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 82.28
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor External | Consulting Services - Environmental Perm | CH2M HILL ENGINEERS INC | 002/2021 | 20
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor External | Consulting Services - Environmental Perm | CH2M HILL ENGINEERS INC | 003/2021 | 78.42
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Account Services | Not assigned | 001/2021 | 508.65
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Account Services | Not assigned | 002/2021 | 1033.69
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Account Services | Not assigned | 003/2021 | 2295.14
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Acquisition - Misc | Not assigned | 001/2021 | 64.8
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Acquisition - Misc | Not assigned | 002/2021 | 32.4
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Acquisition - Misc | Not assigned | 003/2021 | 194.4
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Administration | Not assigned | 001/2021 | 1253.52
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Administration | Not assigned | 002/2021 | 1114.24
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Administration | Not assigned | 003/2021 | 139.28
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Administrative Services - OT | Not assigned | 001/2021 | 1100.13
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Administrative Services - OT | Not assigned | 003/2021 | 44.01
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Construction | Not assigned | 001/2021 | 49541.18
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Construction | Not assigned | 002/2021 | 79049.96
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Construction | Not assigned | 003/2021 | 143231.55
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Construction Doubletime Services | Not assigned | 001/2021 | 326.31
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Construction Doubletime Services | Not assigned | 002/2021 | 2416.11
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Construction Doubletime Services | Not assigned | 003/2021 | 598.7
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 5213.5
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Construction Overtime Services | Not assigned | 002/2021 | 11046.83
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Construction Overtime Services | Not assigned | 003/2021 | 19496.46
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1005.08
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 818.95
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1228.44
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 131.69
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 002/2021 | 267.62
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 003/2021 | 594.21
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 17499.31
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 31626.73
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 56952.8
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 1054.76
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 565.36
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 556.98
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Indirect Labor - Gas | Not assigned | 001/2021 | 1982.98
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Indirect Labor - Gas | Not assigned | 002/2021 | 403.42
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Indirect Labor - Nuclear Gen | Not assigned | 002/2021 | 15.15
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Indirect Labor - Nuclear Gen | Not assigned | 003/2021 | 44.19
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Land Rights - Misc | Not assigned | 001/2021 | 567
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Land Rights - Misc | Not assigned | 002/2021 | 453.6
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Land Rights - Misc | Not assigned | 003/2021 | 810
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Maintain & Operate Overtime Services | Not assigned | 003/2021 | 99.34
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Maintain & Operate Services | Not assigned | 003/2021 | 1421.6
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Manage L&EM | Not assigned | 003/2021 | 388.8
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Management Services | Not assigned | 003/2021 | 42.3
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Mapping | Not assigned | 001/2021 | 1015.18
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Mapping | Not assigned | 002/2021 | 1077.39
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Mapping | Not assigned | 003/2021 | 1926.25
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 12203.9
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 19645.21
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 34909.13
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Technical Services | Not assigned | 002/2021 | 500.04
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Labor Internal | Technical Services | Not assigned | 003/2021 | 1458.45
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Materials | Electl & Electronic Equipment Component | Not assigned | 002/2021 | 3713.82
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Materials | Material Burden | Not assigned | 001/2021 | 4764.65
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Materials | Material Burden | Not assigned | 002/2021 | 586.43
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Materials | Material Burden | Not assigned | 003/2021 | 4567.95
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 001/2021 | 32634.62
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Materials | Poles, Insulators & Hardware Bushing & B | STELLA-JONES CORPORATION | 003/2021 | 31002.88
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 002/2021 | 299.4
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Materials | Poles, Insulators & Hardware Bushing & B | Not assigned | 003/2021 | 284.43
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Materials | Purchasing Card | DARYL S SATTELBERG | 002/2021 | 50.08
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Benefits OH | Not assigned | 001/2021 | 25442.87
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Benefits OH | Not assigned | 002/2021 | 39190.16
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Benefits OH | Not assigned | 003/2021 | 66645.44
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Building Service Overhead | Not assigned | 001/2021 | 4366.66
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Building Service Overhead | Not assigned | 002/2021 | 6726.07
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Building Service Overhead | Not assigned | 003/2021 | 12045.64
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Capitalized A&G | Not assigned | 001/2021 | 22311.2
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Capitalized A&G | Not assigned | 002/2021 | 35915.4
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Capitalized A&G | Not assigned | 003/2021 | 63836.56
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Cash Discount earned | DONAHOO INC | 001/2021 | -222.57
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Cash Discount earned | DONAHOO INC | 003/2021 | -1214.14
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Cash Discount earned | PARMETER GENERAL ENGINEERS | 001/2021 | -293.54
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Cash Discount earned | PARMETER GENERAL ENGINEERS | 002/2021 | -1028.03
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Cash Discount earned | PARMETER GENERAL ENGINEERS | 003/2021 | -1414.87
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Cash Discount earned | PARMETER GENERAL ENGINEERS | 004/2021 | -81.57
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Cash Discount earned | STELLA-JONES CORPORATION | 002/2021 | -599.28
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Cash Discount earned | STELLA-JONES CORPORATION | 003/2021 | -569.32
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 11692.03
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 21131.14
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 38052.52
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Fleet OH - Gas | Not assigned | 001/2021 | 1697.42
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Fleet OH - Gas | Not assigned | 002/2021 | 345.33
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | IT Device OH | Not assigned | 001/2021 | 2478.41
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | IT Device OH | Not assigned | 002/2021 | 3817.53
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | IT Device OH | Not assigned | 003/2021 | 6836.71
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Land Acquisition Services | ASSOCIATED RIGHT OF WAY SVCS INC | 001/2021 | 2150
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Land Acquisition Services | ASSOCIATED RIGHT OF WAY SVCS INC | 002/2021 | 1125
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Land Acquisition Services | ASSOCIATED RIGHT OF WAY SVCS INC | 003/2021 | 235.3
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Land Acquisition Services | ASSOCIATED RIGHT OF WAY SVCS INC | 004/2021 | -566.3
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Minor Material OH | Not assigned | 001/2021 | 2659.09
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Minor Material OH | Not assigned | 002/2021 | 330.6
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Minor Material OH | Not assigned | 003/2021 | 2549.31
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 15837.12
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 28622.68
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 51543.11
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 631.72
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 338.61
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 333.58
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Operation Mgmt & Support - Gas | Not assigned | 001/2021 | 3040.78
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Operation Mgmt & Support - Gas | Not assigned | 002/2021 | 618.62
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Operation Mgmt & Support - Nuclear Gen | Not assigned | 002/2021 | 274.92
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Operation Mgmt & Support - Nuclear Gen | Not assigned | 003/2021 | 801.86
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Other Expenses | DARYL S SATTELBERG | 002/2021 | 609
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Other Land Fees | DAVID L NELSON | 003/2021 | 7000
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 8595.95
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 13240.52
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 23712.2
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Reimbursed Mileage Expense | DARYL S SATTELBERG | 002/2021 | 159.6
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Reimbursed Mileage Expense | LINDA CLIFTON | 002/2021 | 30.24
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Other | Reimbursed Mileage Expense | LINDA CLIFTON | 003/2021 | 31.92
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 297.8
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 001/2021 | 17.41
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 002/2021 | 17.41
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Labor Internal | Environmental Planning & Permitting-Misc | Not assigned | 003/2021 | 121.87
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 100.95
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 001/2021 | 6.15
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 6.15
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 003/2021 | 43.06
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 3.51
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 63.49
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 24.54
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1630.56
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 1380.38
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 1381.37
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | AFUDC-Equity | Not assigned | 001/2021 | 3722.77
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | AFUDC-Equity | Not assigned | 002/2021 | 3724.85
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | AFUDC-Equity | Not assigned | 003/2021 | 3727.5
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | Benefits OH | Not assigned | 001/2021 | 5.97
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | Benefits OH | Not assigned | 002/2021 | 125.8
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | Benefits OH | Not assigned | 003/2021 | 39.66
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | Building Service Overhead | Not assigned | 001/2021 | 1.02
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | Building Service Overhead | Not assigned | 002/2021 | 21.59
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | Building Service Overhead | Not assigned | 003/2021 | 7.17
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | Capitalized A&G | Not assigned | 001/2021 | 6.41
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | Capitalized A&G | Not assigned | 002/2021 | 116.06
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | Capitalized A&G | Not assigned | 003/2021 | 44.87
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 67.45
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | IT Device OH | Not assigned | 001/2021 | 0.58
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | IT Device OH | Not assigned | 002/2021 | 12.25
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | IT Device OH | Not assigned | 003/2021 | 4.07
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 91.37
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 001/2021 | 3.68
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 3.68
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 003/2021 | 25.79
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 2.01
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 42.49
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 14.11
74022386 | *CANC* CWSP - LOS GATOS 1106 - LB4 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | -250.11
74022386 | *CANC* CWSP - LOS GATOS 1106 - LB4 | Other | AFUDC-Equity | Not assigned | 001/2021 | 630.17
74022386 | *CANC* CWSP - LOS GATOS 1106 - LB4 | Other | Canceled Capital Order | Not assigned | 001/2021 | 9556.95
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 702.25
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | -1450
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1116.75
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 1191.2
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | -1.47
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 379.3
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 403.82
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Labor Internal | Mapping | Not assigned | 001/2021 | -4.35
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Labor Internal | Mapping | Not assigned | 002/2021 | 2.11
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Labor Internal | Paid Time Off | Not assigned | 001/2021 | -0.88
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 225.33
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 239.91
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Benefits OH | Not assigned | 001/2021 | -1.75
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Benefits OH | Not assigned | 002/2021 | 450.17
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Benefits OH | Not assigned | 003/2021 | 455.11
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Building Service Overhead | Not assigned | 001/2021 | -0.3
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Building Service Overhead | Not assigned | 002/2021 | 77.27
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Building Service Overhead | Not assigned | 003/2021 | 82.26
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Capitalized A&G | Not assigned | 001/2021 | -1.6
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Capitalized A&G | Not assigned | 002/2021 | 411.97
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Capitalized A&G | Not assigned | 003/2021 | 438.6
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Cash Discount earned | MCE CORPORATION | 001/2021 | -4253.98
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Encroachment Permit Fees | CITY OF OAKLAND | 002/2021 | 2613
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Encroachment Permit Fees | CITY OF OAKLAND | 003/2021 | 1206
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Fleet OH - Elec | Not assigned | 001/2021 | -0.99
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Fleet OH - Elec | Not assigned | 002/2021 | 253.42
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Fleet OH - Elec | Not assigned | 003/2021 | 269.81
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | IT Device OH | Not assigned | 001/2021 | -0.17
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | IT Device OH | Not assigned | 002/2021 | 43.86
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | IT Device OH | Not assigned | 003/2021 | 46.69
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | -1.33
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 343.27
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 365.46
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Payroll Taxes OH | Not assigned | 001/2021 | -0.59
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Payroll Taxes OH | Not assigned | 002/2021 | 152.09
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Other | Payroll Taxes OH | Not assigned | 003/2021 | 161.92
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 003/2021 | 380
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Contract | Electric Construction Contract | ENERGY EXPERTS INTERNATIONAL | 004/2021 | -380
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Contract | Electric Construction Contract | QUANTA ENERGY SERVICES LLC | 003/2021 | 111994.22
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 126.19
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 114.28
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Labor Internal | Mapping | Not assigned | 003/2021 | 337.12
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 74.97
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 67.9
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Labor Internal | Project Management Services | Not assigned | 001/2021 | 372.25
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Other | Benefits OH | Not assigned | 001/2021 | 149.77
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Other | Benefits OH | Not assigned | 003/2021 | 128.8
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Other | Building Service Overhead | Not assigned | 001/2021 | 25.71
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Other | Building Service Overhead | Not assigned | 003/2021 | 23.28
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Other | Capitalized A&G | Not assigned | 001/2021 | 137.06
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Other | Capitalized A&G | Not assigned | 003/2021 | 124.13
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Other | Fleet OH - Elec | Not assigned | 001/2021 | 84.31
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Other | Fleet OH - Elec | Not assigned | 003/2021 | 76.36
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Other | IT Device OH | Not assigned | 001/2021 | 14.59
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Other | IT Device OH | Not assigned | 003/2021 | 13.21
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 114.21
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 103.43
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Other | Payroll Taxes OH | Not assigned | 001/2021 | 50.6
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | Other | Payroll Taxes OH | Not assigned | 003/2021 | 45.82
74022615 | CWSP - CAMP FIRE PADSE 1105 PENTZ RD | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 1.02
74022615 | CWSP - CAMP FIRE PADSE 1105 PENTZ RD | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 0.86
74022615 | CWSP - CAMP FIRE PADSE 1105 PENTZ RD | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 0.86
74022615 | CWSP - CAMP FIRE PADSE 1105 PENTZ RD | Other | AFUDC-Equity | Not assigned | 001/2021 | 2.33
74022615 | CWSP - CAMP FIRE PADSE 1105 PENTZ RD | Other | AFUDC-Equity | Not assigned | 002/2021 | 2.33
74022615 | CWSP - CAMP FIRE PADSE 1105 PENTZ RD | Other | AFUDC-Equity | Not assigned | 003/2021 | 2.33
74022663 | CAMP FIRE RECOND LINE HONEY RN BUTTE 05 | Other | AFUDC-Borrowed | Not assigned | 001/2021 | -246.24
74022664 | CAMP FIRE RECONDUCTOR LINE DEPOT RD | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 160.87
74022664 | CAMP FIRE RECONDUCTOR LINE DEPOT RD | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 135.86
74022664 | CAMP FIRE RECONDUCTOR LINE DEPOT RD | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 135.86
74022664 | CAMP FIRE RECONDUCTOR LINE DEPOT RD | Other | AFUDC-Equity | Not assigned | 001/2021 | 366.62
74022664 | CAMP FIRE RECONDUCTOR LINE DEPOT RD | Other | AFUDC-Equity | Not assigned | 002/2021 | 366.62
74022664 | CAMP FIRE RECONDUCTOR LINE DEPOT RD | Other | AFUDC-Equity | Not assigned | 003/2021 | 366.62
74022720 | CWSP-CAMP FIRE PADSE 1105 INST BIKE PATH | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 33.47
74022720 | CWSP-CAMP FIRE PADSE 1105 INST BIKE PATH | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 28.26
74022720 | CWSP-CAMP FIRE PADSE 1105 INST BIKE PATH | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 28.26
74022720 | CWSP-CAMP FIRE PADSE 1105 INST BIKE PATH | Other | AFUDC-Equity | Not assigned | 001/2021 | 76.25
74022720 | CWSP-CAMP FIRE PADSE 1105 INST BIKE PATH | Other | AFUDC-Equity | Not assigned | 002/2021 | 76.25
74022720 | CWSP-CAMP FIRE PADSE 1105 INST BIKE PATH | Other | AFUDC-Equity | Not assigned | 003/2021 | 76.25
74022721 | CWSP - CAMP FIRE PADSE 1106 BILLIE RD | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 75.29
74022721 | CWSP - CAMP FIRE PADSE 1106 BILLIE RD | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 63.55
74022721 | CWSP - CAMP FIRE PADSE 1106 BILLIE RD | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 63.55
74022721 | CWSP - CAMP FIRE PADSE 1106 BILLIE RD | Other | AFUDC-Equity | Not assigned | 001/2021 | 171.49
74022721 | CWSP - CAMP FIRE PADSE 1106 BILLIE RD | Other | AFUDC-Equity | Not assigned | 002/2021 | 171.49
74022721 | CWSP - CAMP FIRE PADSE 1106 BILLIE RD | Other | AFUDC-Equity | Not assigned | 003/2021 | 171.49
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD | Labor Internal | Electric Estimating | Not assigned | 003/2021 | 118.42
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 40.14
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 23.85
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 371.44
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 313.65
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 313.89
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD | Other | AFUDC-Equity | Not assigned | 001/2021 | 846.37
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD | Other | AFUDC-Equity | Not assigned | 002/2021 | 846.37
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD | Other | AFUDC-Equity | Not assigned | 003/2021 | 847
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD | Other | Benefits OH | Not assigned | 003/2021 | 45.24
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD | Other | Building Service Overhead | Not assigned | 003/2021 | 8.17
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD | Other | Capitalized A&G | Not assigned | 003/2021 | 43.6
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD | Other | Fleet OH - Elec | Not assigned | 003/2021 | 26.82
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD | Other | IT Device OH | Not assigned | 003/2021 | 4.65
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 36.33
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD | Other | Payroll Taxes OH | Not assigned | 003/2021 | 16.1
74022723 | CWSP - CAMP FIRE PDSE 1106 PONDEROSA WAY | Other | AFUDC-Borrowed | Not assigned | 001/2021 | 101.97
74022723 | CWSP - CAMP FIRE PDSE 1106 PONDEROSA WAY | Other | AFUDC-Borrowed | Not assigned | 002/2021 | 86.11
74022723 | CWSP - CAMP FIRE PDSE 1106 PONDEROSA WAY | Other | AFUDC-Borrowed | Not assigned | 003/2021 | 86.11
74022723 | CWSP - CAMP FIRE PDSE 1106 PONDEROSA WAY | Other | AFUDC-Equity | Not assigned | 001/2021 | 232.36
74022723 | CWSP - CAMP FIRE PDSE 1106 PONDEROSA WAY | Other | AFUDC-Equity | Not assigned | 002/2021 | 232.36
74022723 | CWSP - CAMP FIRE PDSE 1106 PONDEROSA WAY | Other | AFUDC-Equity | Not assigned | 003/2021 | 232.36
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | Contract | Contracts | WRIGHT TREE SERVICE OF THE WEST INC | 001/2021 | 1845.71
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 1.88
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | Labor Internal | Mapping | Not assigned | 001/2021 | 5.54
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 1.12
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | Other | Benefits OH | Not assigned | 001/2021 | 2.23
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | Other | Building Service Overhead | Not assigned | 001/2021 | 0.38
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | Other | Capitalized A&G | Not assigned | 001/2021 | 2.04
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | Other | Cellular Phone Use | VERIZON WIRELESS | 002/2021 | 7
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | Other | Cellular Phone Use | VERIZON WIRELESS | 003/2021 | 7.02
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | Other | Cellular Phone Use | Not assigned | 001/2021 | -17.8
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | Other | Fleet OH - Elec | Not assigned | 001/2021 | 1.25
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | Other | IT Device OH | Not assigned | 001/2021 | 0.21
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 1.7
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | Other | Payroll Taxes OH | Not assigned | 001/2021 | 0.76
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Contract | Contracts | Not assigned | 002/2021 | 262939.11
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Contract | Environmental Contract | BTCONSULTING INC | 001/2021 | 392.03
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Contract | Environmental Contract | BTCONSULTING INC | 002/2021 | 308.3
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Contract | Environmental Contract | BTCONSULTING INC | 003/2021 | 799.24
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Contract | Environmental Contract | BTCONSULTING INC | 004/2021 | -392.59
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 001/2021 | 1500
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 002/2021 | 4170
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 003/2021 | 8965
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Contract | Environmental Contract | JACOBSON JAMES & ASSOCIATES INC | 004/2021 | -500
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 002/2021 | 57.4
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 003/2021 | 123.48
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor External | Consulting Services - Engineering | BTCONSULTING INC | 004/2021 | -41.08
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor External | Outside Attorney Fees | LEE LAW OFFICES | 001/2021 | 2494
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Account Services | Not assigned | 001/2021 | 196.9
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Administration | Not assigned | 002/2021 | 835.68
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Construction | Not assigned | 001/2021 | 534.83
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Construction | Not assigned | 002/2021 | 446.7
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Construction | Not assigned | 003/2021 | 74.45
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Construction Overtime Services | Not assigned | 001/2021 | 221.74
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Engineering/Mapping | Not assigned | 001/2021 | 1005.08
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Engineering/Mapping | Not assigned | 002/2021 | 1414.55
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Engineering/Mapping | Not assigned | 003/2021 | 372.25
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Indirect Labor - Cust Care | Not assigned | 001/2021 | 50.98
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Indirect Labor - Electric | Not assigned | 001/2021 | 601.44
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Indirect Labor - Electric | Not assigned | 002/2021 | 904.34
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Indirect Labor - Electric | Not assigned | 003/2021 | 161.71
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Indirect Labor - Environmental Land | Not assigned | 002/2021 | 295.25
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Mapping | Not assigned | 001/2021 | 12.49
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Mapping | Not assigned | 002/2021 | 806.44
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Mapping | Not assigned | 003/2021 | 30.33
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Paid Time Off | Not assigned | 001/2021 | 396.97
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Paid Time Off | Not assigned | 002/2021 | 705.59
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Labor Internal | Paid Time Off | Not assigned | 003/2021 | 96.07
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | Benefits OH | Not assigned | 001/2021 | 769.63
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | Benefits OH | Not assigned | 002/2021 | 1359.74
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | Benefits OH | Not assigned | 003/2021 | 182.26
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | Building Service Overhead | Not assigned | 001/2021 | 132.09
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | Building Service Overhead | Not assigned | 002/2021 | 233.37
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | Building Service Overhead | Not assigned | 003/2021 | 32.94
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | Capitalized A&G | Not assigned | 001/2021 | 725.74
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | Capitalized A&G | Not assigned | 002/2021 | 1289.94
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | Capitalized A&G | Not assigned | 003/2021 | 175.64
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | Fleet OH - Elec | Not assigned | 001/2021 | 401.84
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | Fleet OH - Elec | Not assigned | 002/2021 | 604.23
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | Fleet OH - Elec | Not assigned | 003/2021 | 108.05
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | IT Device OH | Not assigned | 001/2021 | 74.97
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | IT Device OH | Not assigned | 002/2021 | 132.45
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | IT Device OH | Not assigned | 003/2021 | 18.69
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | Operation Mgmt & Support - Electric | Not assigned | 001/2021 | 544.3
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | Operation Mgmt & Support - Electric | Not assigned | 002/2021 | 818.44
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | Operation Mgmt & Support - Electric | Not assigned | 003/2021 | 146.36
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | Operation Mgmt & Support - Environ Land | Not assigned | 002/2021 | 176.83
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | Payroll Taxes OH | Not assigned | 001/2021 | 260.01
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | Payroll Taxes OH | Not assigned | 002/2021 | 459.4
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Other | Payroll Taxes OH | Not assigned | 003/2021 | 64.84

## 2021 pivot (hidden)
Order Desc | (Multiple Items) |  |  |  | Order Desc | FRRB - MONTICELLO 1101 CB
Sum of $ | Column Labels |  |  |  | Sum of $ | Column Labels
Row Labels | 001/2021 | 002/2021 | 003/2021 | Grand Total | Row Labels | 001/2021 | 002/2021 | 003/2021 | Grand Total
Contract | 4167401.42 | 4226230.08 | 12981987.15 | 21375618.65 | Contract | -45250000 | 29674441.66 | -3252662.66 | -18828221
Labor External | 75240.11 | 87753.5 | 101876.86 | 264870.47 | Labor Internal | -209109.3 | 137131.53 | -15031.21 | -87008.98
Labor Internal | 1061670.27 | 2190695.82 | 3785801.61 | 7038167.7 | Materials | -15783799.55 | 8508664.94 | -2254125.85 | -9529260.46
Materials | 81797.35 | 2175025.77 | 1370972.37 | 3627795.49 | Other | -1755203.73 | 1201194.9 | -43539.95 | -597548.78
Other | 2434706.99 | 3935559.58 | 5815904.28 | 12186170.85 | Grand Total | -62998112.58 | 39521433.03 | -5565359.67 | -29042039.22
Grand Total | 7820816.14 | 12615264.75 | 24056542.27 | 44492623.16

## 2021 working pivot
Sum of $ | Column Labels
Row Labels | 001/2021 | 002/2021 | 003/2021 | Grand Total
Contract | -41082598.58 | 33900671.74 | 9729324.49 | 2547397.65
Labor External | 75240.11 | 87753.5 | 101876.86 | 264870.47
Labor Internal | 852560.97 | 2327827.35 | 3770770.4 | 6951158.72
Materials | -15702002.2 | 10683690.71 | -883153.48 | -5901464.97
Other | 679503.26 | 5136754.48 | 5772364.33 | 11588622.07
Grand Total | -55177296.44 | 52136697.78 | 18491182.6 | 15450583.94