## Workbook Description
System Hardening Update
Information Updated as of 31 March, 2021
Contents
1 | Workbook Description - Overview of workbook contents and key definitions
2 | Summary Reporting - Summary Statistics for on-going System Hardening efforts
3 | Approved CPZ List - Current list of Circuit Protection Zones (CPZ's) approved by the Wildfire Risk Governance Committee for work over the three year period*
3 | O8W Project List - List of projects in Scoping, Estimating, Dependency Clearing, Construction*
*Total approved CPZ miles (1,473) reflects the miles which the hardening team has been approved to scope by the Wildfire Governance Committee (WGC). Planned miles (825) reflects the number of miles that the system hardening team has estimated based on existing projects in the pipeline for the years 2021-2023.
Glossary - In order of presentation
Summary Reporting
| CPZ's Approved | Number of CPZ's approved by the WGC based on risk characteristics and other considerations.
| CPZ Miles Approved | Number of miles the hardening team has been approved to scope within the approved CPZs.
| CPZs with Active Jobs | Number of CPZs where the hardening team is actively pursuing a projects (some CPZs have many projects)
| Active Job Planned Miles | Number of planned miles being pursued with active projects.
| Mitigation Approved | Number of planned miles which have had a specific mitigation approved by the WGC.
| Mitigation Not Approved | Number of planned miles which have yet to be approved for a specific mitigation by the WGC
| Scoping | Initial phase of project lifecycle which ends once a mitigation is approved by the WGC.
| Estimating | Second phase of project lifecycle; Refining project scope and estimates with detailed estimates and project planning.
| Dependencies | Third phase of project lifecycle; Clearing all dependencies required to execute the project (e.g., Easements, Permitting, etc.)
| Construction | Fourth phase of project lifecycle; field team execute the project as scoped.
| Close-out | Final phase of the project lifecycle; Closing and documenting the project.
| Overhead | Miles mitigated with Overhead Hardening.
| Underground | Miles mitigated with Underground Hardening.
| Removal | Miles mitigated with line Removal.
| Remote Grid | Miles mitigated with a Remote Grid Solution.
Approved CPZ List
| PZ_idx | Unique ID for each Circuit Protection Zone.
| circuit_protection_zone_id | Unique name for each Circuit Protection Zone.
| feeder_id | Unique ID for each circuit.
| feeder_name | Unique name for each circuit.
| Miles | Total miles in each .
| pixel_count | Number of 100mx100m pixels in each CPZ. As the risk model has the risk score at this 100mx100m pixel level
| mean_mavf_core_risk | Average - Multi Attribute Value Framework (MAVF) risk score per pixel; used to rank the CPZs from riskiest to least risky. The MAVF developed via regulatory proceedings
| Total Risk Value | Total risk associated with each CPZ, per the 2021 approved conductor risk model.
| mean_mavf_core_risk_rank | Rank of CPZs based on the average risk score (mean_mavf_core_risk).
| Number of Projects | Number of active projects / jobs within the CPZ.
| Residual Miles | Number of miles being hardened within each CPZ, as of the latest revision.
| Scoping | Number of miles in the scoping phase.
| Estimating | Number of miles in the estimating phase.
| Dependencies | Number of miles in the decency clearing phase.
| Construction | Number of miles in the construction phase.
| Close-out | Number of miles in the close-out phase.
| Work Bucket | Justification for approval of work in the CPZ by WGC.
| Date Approved | Date work was approved for scoping by the WGC.
08W Project List
| Order | SAP order number for the system hardening job / project.
| Exec. Status | Detailed view of current status.
| Planned Miles (SAP EST) | Number of miles anticipated to be hardened within the CPZ from the years 2021-2023, based on current assumptions on the mitigation.
| Completed Miles (SAP ACT) | Number of miles constructed within the years 2021-2023. Completed means constructed and in operation but not necessarily in close-out
| Residual Miles (SAP EST) | Number of miles remaining to be hardened within the CPZ, based on current assumptions on the mitigaiton.
| Circuit Name | Unique name for each circuit.
| Circuit Protection Zone | Unique name for each Circuit Protection Zone.
| Pixel(s) | Number of 100mx100m pixels in each CPZ.
| Total HFTD Zone Miles | Number of miles within High Fire Threat Districts (HFTD)
| Mean MAVF Core Risk Rank | Rank of CPZs based on the average risk score (mean_mavf_core_risk).
| Total MAVF Core Risk Value | Total risk associated with each CPZ, per the 2021 approved conductor risk model.
| Mean MAVF Core Risk Value | Average MAVF risk score per pixel; used to rank the CPZs from riskiest to least risky.
| Mean Risk Rank | The rank of the circuit protection zone from 1-N based on the 2021 Wildfire Risk Model
| HFTD Tier | Description of HFTD tiers in the CPZ (e.g., Tier 2, Tier 3).
| OH - Feet | Number of feet estimated to be overhead hardened, given current scoping assumptions.
| UG - Feet | Number of feet estimated to be underground hardened, given current scoping assumptions.
| Remove - Feet | Number of feet estimated to be removed, given current scoping assumptions.
| Remote Grid - Feet | Number of feet estimated to be replace with a remote grid solution, given current scoping assumptions.
| Planned Mitigation | Mitigation planned (e.g., Overhead Harden, Underground Harden, Line Removal / Remote Grid).
| Status | Current status of project (e.g., Scoping, Estimating, Dependencies, Construction, Close-out).
| Work Bucket | Justification for approval of work in the CPZ by Wildfire Risk Governance Committee (WGC).

## Summary Reporting
System Hardening Summary Reporting
Information Updated as of 31 March, 2021
Approved CPZs
|  | CPZ's Approved (#) | CPZ Miles Approved | CPZs with Active Jobs (#) | Active Job Planned Miles
| Total | 140 | 1473.4076 | 110 | 825.2025
08W Opportunity Hopper by Phase (Planned Miles)
|  | Total | Scoping | Estimating | Dependencies | Construction | Close-Out
| Total | 825.2025 | 609.1841 | 123.7654 | 20.9347 | 65.4647 | 5.8537
08W Opportunity Hopper (Planned Miles)
|  | Total | Mitigation Approved | Mitigation Not Approved
| Total | 825.2025 | 515.8324 | 309.3701
08W Opportunity Hopper - Approved Scope by Mitigation Type (Planned Miles)
|  | Total | Overhead | Underground | Removal | Remote Grid
| Total | 515.5356 | 282.9198 | 204.9805 | 9.2324 | 18.403
8762
15000
Supplemental Information:
The top 20% riskiest CPZ's represent 73% of total system Risk and 8,762 miles.
The 08W Project list (orange dots) represents all CPZ's where there is an on-going system hardening project. All on-going projects have been approved by the WGC for risk characteristics or other factors on a case-by-case basis.
Top 20% Riskiest CPZs
08W projects outside of the Top 20% CPZs have been approved directly by the Wildfire Governance Comitteee (WGC). Rational includes: Fire Rebuild, In-construction work, CalTrans Permitting Pilots

## 08W Project List
#N/A | Detailed view of current status. | #N/A | [7 empty] | Unique name for each circuit. | Unique name for each Circuit Protection Zone. | Number of 100mx100m pixels in each CPZ. | Number of miles within High Fire Threat Districts (HFTD) | The rank of the circuit protection zone from 1-N based on the 2021 Wildfire Risk Model | Total risk associated with each CPZ, per the 2021 approved conductor risk model. | Average MAVF risk score per pixel; used to rank the CPZs from riskiest to least risky. | Description of HFTD tiers in the CPZ (e.g., Tier 2, Tier 3). | Number of feet estimated to be overhead hardened, given current scoping assumptions. | Number of feet estimated to be underground hardened, given current scoping assumptions. | Number of feet estimated to be removed, given current scoping assumptions. | Number of feet estimated to be replace with a remote grid solution, given current scoping assumptions. |  | Mitigation planned (e.g., Overhead Harden, Underground Harden, Line Removal / Remote Grid). | Current status of project (e.g., Scoping, Estimating, Dependencies, Construction, Close-out). | Justification for approval of work in the CPZ by Wildfire Risk Governance Committee (WGC).
Order (SH Project) | Exec. Status | Planned Miles (SAP EST) Includes 2020 Hide Column | Residual Miles (SAP EST) Includes 2020 Hide Column | Completed Miles (SAP ACT) Includes 2020 Hide Column | Primary Planned Year Hide Column | Miles Primary Year Hide Column | Miles Secondary Year Hide Column | Planned Miles (SAP EST) | Completed Miles (SAP ACT) | Circuit Name | Circuit Protection Zone | Pixel(s) | Total HFTD Zone Miles | Mean Risk Rank | Total MAVF Core Risk Value | Mean MAVF Core Risk Value | HFTD Tier | OH - Feet | UG - Feet | Remove - Feet | Remote Grid - Feet | Order Status (Hide Column) | Planned Mitigation | Status | Work Bucket
74022384 | 20 | 5.4458 | 2.0458 | 3.4 | 2020 | 0.96 | 2.44 | 4.4858 | 2.44 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 111324918 | 49 | 5.4965 | 481 | 7.7177 | 0.1575 | Tier 3 | 28754 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35119965 | 18 | 0.84905 | 0.84905 | 0 | 2020 | 0 |  | 0.84905 | 0 | LOS GATOS 1106 | LOS GATOS 1106LB44 | 213 | 19.3536 | 1864 | 2.6623 | 0.012499 | Tier 3 | 4483 | 0 | 0 | 0 | PEND | Overhead | Dependencies | In-Construction
35094397 | 20 | 1.0646 | 0.0045833 | 1.06 | 2020 | 0 |  | 1.0646 | 1.06 | KONOCTI 1102 | KONOCTI 1102532 | 124 | 9.7315 | 1999 | 1.1234 | 0.0090595 | Tier 3 | 5621 | 0 | 0 | 0 | FICL | Overhead | Close-Out | In-Construction
35061206 | 20 | 1.7652 | 0.93515 | 0.83 | 2020 | 0 |  | 1.7652 | 0.83 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | Tier 3 | 9320 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35061212 | 20 | 1.7888 | 1.7888 | 0 | 2020 | 0 |  | 1.7888 | 0 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | Tier 3 | 9445 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35115151 | 20 | 1.8964 | 0.5664 | 1.33 | 2020 | 0 |  | 1.8964 | 1.33 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | Tier 3 | 10013 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35115152 | 20 | 1.57 | 1.57 | 0 | 2021 |  |  | 1.57 | 0 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | Tier 3 | 8271 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35117443 | 20 | 2.1581 | 0.88814 | 1.27 | 2021 | 1.27 |  | 2.1581 | 1.27 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | Tier 3 | 11395 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35116383 | 20 | 1.3862 | 1.3862 | 0 | 2020 | 0 |  | 1.3862 | 0 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | Tier 3 | 7319 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35116384 | 20 | 1.8371 | 1.6671 | 0.17 | 2020 | 0.17 |  | 1.6671 | 0 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | Tier 3 | 9700 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35116385 | 18 | 1.4 | 1.4 | 0 |  |  |  | 1.4 | 0 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | Tier 3 | 7392 | 0 | 0 | 0 | PEND | Overhead | Dependencies | In-Construction
35114048 | 20 | 1.3909 | 1.3909 | 0 | 2020 | 0 |  | 1.3909 | 0 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | Tier 3 | 7344 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35114051 | 20 | 1.44 | 1.44 | 0 | 2021 |  |  | 1.44 | 0 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | Tier 3 | 7698 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35052821 | 20 | 2.0744 | 1.8344 | 0.24 | 2020 | 0 |  | 2.0744 | 0.24 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | Tier 3 | 10953 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35115050 | 20 | 1.6121 | 1.3121 | 0.3 | 2020 | 0 |  | 1.6121 | 0.3 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | Tier 3 | 8512 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35115053 | 20 | 1.7203 | 1.7203 | 0 | 2020 | 0 |  | 1.7203 | 0 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | Tier 3 | 9083 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35056746 | 20 | 2.0335 | 2.0335 | 0 | 2020 | 0 |  | 2.0335 | 0 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | Tier 3 | 10737 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35115054 | 20 | 1.4259 | 1.3959 | 0.03 | 2020 | 0.03 |  | 1.3959 | 0 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | Tier 3 | 7529 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35115055 | 20 | 2.1343 | 2.1343 | 0 | 2020 | 0 |  | 2.1343 | 0 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | Tier 2 | 11269 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35116391 | 20 | 2.0902 | 0.060152 | 2.03 | 2020 | 1.38 | 0.65 | 0.71015 | 0.65 | MIWUK 1702 | MIWUK 1702CB | 110 | 9.055 | 2369 | 0.30977 | 0.0028161 | Tier 3 | 11036 | 0 | 0 | 0 | DOCC | Overhead | Close-Out | In-Construction
35116395 | 20 | 1.7106 | 1.0206 | 0.69 | 2021 | 0.69 |  | 1.7106 | 0.69 | MIWUK 1702 | MIWUK 1702CB | 110 | 9.055 | 2369 | 0.30977 | 0.0028161 | Tier 3 | 9032 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35116800 | 20 | 1.4252 | 0.41519 | 1.01 | 2020 | 0.74 | 0.27 | 0.68519 | 0.27 | MIWUK 1702 | MIWUK 1702823548 | 231 | 19.7318 | 2411 | 0.57976 | 0.0025098 | Tier 3 | 7525 | 0 | 0 | 0 | DOCC | Overhead | Close-Out | In-Construction
35114100 | 20 | 1.0392 | 1.0392 | 0 | 2020 | 0 |  | 1.0392 | 0 | CAMP EVERS 2106 | CAMP EVERS 21065020 | 185 | 15.0734 | 2464 | 0.3934 | 0.0021265 | Tier 3 | 5487 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35052825 | 20 | 1.1682 | 0.86818 | 0.3 | 2020 | 0 |  | 1.1682 | 0.3 | MIWUK 1702 | MIWUK 1702S2247 | 21 | 1.4879 | 2737 | 0.010338 | 0.00049228 | Tier 3 | 6168 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35116442 | 20 | 2.29 | 0 | 2.29 | 2020 | 1.79 | 0.5 | 0.5 | 0.5 | MIWUK 1702 | MIWUK 170238218 | 132 | 10.9416 | 2678 | 0.098599 | 0.00074696 | Tier 3 | 12386 | 0 | 0 | 0 | DOCC | Overhead | Close-Out | In-Construction
35116444 | 20 | 2.1023 | 2.1023 | 0 | 2020 | 0 |  | 2.1023 | 0 | MIWUK 1702 | MIWUK 170238218 | 132 | 10.9416 | 2678 | 0.098599 | 0.00074696 | Tier 3 | 11100 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
31361965 | 20 | 0.45 | 0.45 | 0 | 2021 |  |  | 0.45 | 0 | DUNBAR 1101 | DUNBAR 110147964 | 68 | 6.5107 | 1794 | 0.99704 | 0.014662 | Tier 3 | 0 | 2367 | 0 | 0 | CONS | Underground | Construction | In-Construction
31334291 | 18 | 0.51 | 0.51 | 0 | 2021 |  |  | 0.51 | 0 | FORT BRAGG A 1101 | FORT BRAGG A 11013113 | 68 | 10.0269 | 2140 | 0.42396 | 0.0062347 | Tier 3 | 2710 | 0 | 0 | 0 | PEND | Overhead | Dependencies | In-Construction
35085847 | 18 | 0.86 | 0.86 | 0 | 2021 |  |  | 0.86 | 0 | ROB ROY 2105 | ROB ROY 210512474 | 105 | 3.4104 | 3283 | 0.00048831 | 4.6505e-06 | Tier 3 | 4555 | 0 | 0 | 0 | PEND | Overhead | Dependencies | In-Construction
35015704 | 18 | 1 | 1 | 0 | 2021 |  |  | 1 | 0 | ROB ROY 2105 | ROB ROY 210512474 | 105 | 3.4104 | 3283 | 0.00048831 | 4.6505e-06 | Tier 3 | 5300 | 0 | 0 | 0 | PEND | Overhead | Dependencies | In-Construction
35052731 | 19 | 1.4733 | 1.4733 | 0 | 2020 | 0 |  | 1.4733 | 0 | BIG BASIN 1101 | BIG BASIN 110110296 | 181 | 14.4211 | 2456 | 0.3928 | 0.0021702 | Tier 3 | 7779 | 0 | 0 | 0 | PEND | Overhead | Construction | DSDD
35113950 | 19 | 3.57 | 3.57 | 0 |  |  |  | 3.57 | 0 | BIG BASIN 1101 | BIG BASIN 110110296 | 181 | 14.4211 | 2456 | 0.3928 | 0.0021702 | Tier 3 | 18849.6 | 0 | 0 | 0 | PEND | Overhead | Construction | DSDD
35113951 | 19 | 2.58 | 2.58 | 0 |  |  |  | 2.58 | 0 | BIG BASIN 1101 | BIG BASIN 110110296 | 181 | 14.4211 | 2456 | 0.3928 | 0.0021702 | Tier 3 | 13622.4 | 0 | 0 | 0 | UNSC | Overhead | Construction | DSDD
35145540 | 18 | 1.2739 | 1.2739 | 0 | 2020 | 0 |  | 1.2739 | 0 | FROGTOWN 1702 | FROGTOWN 1702CB | 47 | 1.4614 | 1316 | 1.844 | 0.039234 | Tier 3 | 0 | 2272 | 4454 | 0 | PEND | Remote Grid / Removal | Dependencies | PSPS
35094513 | 18 | 1.9112 | 1.9112 | 0 | 2020 | 0 |  | 1.9112 | 0 | STANISLAUS 1702 | STANISLAUS 17021804 | 118 | 8.3797 | 2712 | 0.069602 | 0.00058985 | Tier 3 | 10091 | 0 | 0 | 0 | PEND | Overhead | Dependencies | DSDD
35145525 | 18 | 1.78 | 1.78 | 0 | 2020 | 0 |  | 1.78 | 0 | RINCON 1104 | RINCON 1104CB | 34 | 0.56024 | 3302 | 0.00014935 | 4.3928e-06 | Tier 2 | 0 | 9398.4 | 0 | 0 | PEND | Underground | Dependencies | PSPS
35145524 | 18 | 1.5 | 1.5 | 0 | 2020 | 0 |  | 1.5 | 0 | RINCON 1103 | RINCON 1103CB | 41 | 2.4433 | 1755 | 0.67489 | 0.016461 | Tier 3 | 0 | 7920 | 0 | 0 | PEND | Underground | Dependencies | PSPS
35137590 | 14 | 0.53485 | 0.53485 | 0 | 2021 |  |  | 0.53485 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101CB | 146 | 4.731 | 86 | 52.8144 | 0.36174 | Tier 3 | 2824 | 0 | 0 | 0 | ESTS | Overhead | Estimating | ECOP
35137593 | 14 | 1.3775 | 1.3775 | 0 | 2021 |  |  | 1.3775 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 11014646 | 165 | 18.5633 | 328 | 32.9712 | 0.19983 | Tier 3 | 7273 | 0 | 0 | 0 | ESTS | Overhead | Estimating | ECOP
35137596 | 14 | 0.97178 | 0.97178 | 0 | 2021 |  |  | 0.97178 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 11014646 | 165 | 18.5633 | 328 | 32.9712 | 0.19983 | Tier 3 | 5131 | 0 | 0 | 0 | PEND | Overhead | Estimating | ECOP
35192284 | 13 | 1.086 | 1.086 | 0 | 2021 |  |  | 1.086 | 0 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | Tier 3 | 0 | 5734 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35223024 | 13 | 1.2659 | 1.2659 | 0 | 2021 |  |  | 1.2659 | 0 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | Tier 3 | 0 | 6684 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35223026 | 13 | 1.0348 | 1.0348 | 0 | 2021 |  |  | 1.0348 | 0 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | Tier 3 | 5464 | 0 | 0 | 0 | UNSE | Overhead | Scoping | ECOP
35223027 | 14 | 1.5674 | 1.5674 | 0 | 2021 |  |  | 1.5674 | 0 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | Tier 3 | 8276 | 0 | 0 | 0 | ESTS | Overhead | Estimating | ECOP
35223028 | 14 | 1.208 | 1.208 | 0 | 2021 |  |  | 1.208 | 0 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | Tier 3 | 6378 | 0 | 0 | 0 | ESTS | Overhead | Estimating | ECOP
35238098 | 14 | 0 | 0 | 0 |  |  |  | 0 | 0 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | Tier 3 | 0 | 0 | 0 | 0 | ESTS | TBD | Estimating | ECOP
35225593 | 14 | 1.1756 | 1.1756 | 0 | 2021 |  |  | 1.1756 | 0 | CLAYTON 2212 | CLAYTON 221296224 | 174 | 19.3992 | 377 | 32.6329 | 0.18755 | Tier 3 | 6207 | 0 | 0 | 0 | ESTS | Overhead | Estimating | ECOP
35192281 | 13 | 0.30663 | 0.30663 | 0 | 2021 |  |  | 0.30663 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 1619 | 0 | 0 | 0 | UNSE | Overhead | Scoping | ECOP
35227027 | 13 | 0.97576 | 0.97576 | 0 | 2021 |  |  | 0.97576 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 5152 | 0 | 0 | 0 | UNSE | Overhead | Scoping | ECOP
35227028 | 13 | 0.61723 | 0.61723 | 0 | 2021 |  |  | 0.61723 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 3259 | 0 | 0 | 0 | UNSE | Overhead | Scoping | ECOP
35227029 | 13 | 1.0886 | 1.0886 | 0 | 2021 |  |  | 1.0886 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 5748 | 0 | 0 | 0 | UNSE | Overhead | Scoping | ECOP
35236437 | 13 | 0.34 | 0.34 | 0 |  |  |  | 0.34 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 0 | 1795.2 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35236438 | 13 | 0.48 | 0.48 | 0 |  |  |  | 0.48 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 0 | 2534.4 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35226622 | 13 | 0.87841 | 0.87841 | 0 | 2021 |  |  | 0.87841 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 4638 | 0 | 0 | 0 | UNSE | Overhead | Scoping | ECOP
35226623 | 13 | 1.2953 | 1.2953 | 0 | 2021 |  |  | 1.2953 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 6839 | 0 | 0 | 0 | UNSE | Overhead | Scoping | ECOP
35226624 | 13 | 0.70795 | 0.70795 | 0 | 2021 |  |  | 0.70795 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 3738 | 0 | 0 | 0 | UNSE | Overhead | Scoping | ECOP
35225595 | 13 | 0.87803 | 0.87803 | 0 | 2021 |  |  | 0.87803 | 0 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | Tier 3 | 4636 | 0 | 0 | 0 | UNSE | Overhead | Scoping | ECOP
35225597 | 14 | 0.77576 | 0.77576 | 0 | 2021 |  |  | 0.77576 | 0 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | Tier 3 | 4096 | 0 | 0 | 0 | ESTS | Overhead | Estimating | ECOP
35225598 | 14 | 0.88144 | 0.88144 | 0 | 2021 |  |  | 0.88144 | 0 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | Tier 3 | 4654 | 0 | 0 | 0 | ESTS | Overhead | Estimating | ECOP
35174479 | 14 | 0.72159 | 0.72159 | 0 | 2021 |  |  | 0.72159 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 3810 | 0 | 0 | 0 | ESTS | Overhead | Estimating | ECOP
35226863 | 14 | 0.52765 | 0.52765 | 0 | 2021 |  |  | 0.52765 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 2786 | 0 | 0 | 0 | ESTS | Overhead | Estimating | ECOP
35226864 | 14 | 0.32652 | 0.32652 | 0 | 2021 |  |  | 0.32652 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 1724 | 0 | 0 | 0 | ESTS | Overhead | Estimating | ECOP
35226865 | 14 | 0.23542 | 0.23542 | 0 | 2021 |  |  | 0.23542 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 1243 | 0 | 0 | 0 | ESTS | Overhead | Estimating | ECOP
35226866 | 14 | 0.51818 | 0.51818 | 0 | 2021 |  |  | 0.51818 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 2736 | 0 | 0 | 0 | ESTS | Overhead | Estimating | ECOP
35226870 | 14 | 0.41951 | 0.41951 | 0 | 2021 |  |  | 0.41951 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 2215 | 0 | 0 | 0 | ESTS | Overhead | Estimating | ECOP
35226871 | 13 | 1.9117 | 1.9117 | 0 | 2021 |  |  | 1.9117 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 420 | 6124 | 3550 | 0 | UNSE | Hybrid | Scoping | ECOP
35226872 | 13 | 1.4881 | 1.4881 | 0 | 2021 |  |  | 1.4881 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 1168 | 2552 | 4137 | 0 | UNSE | Hybrid | Scoping | ECOP
35226873 | 13 | 1.0394 | 1.0394 | 0 | 2021 |  |  | 1.0394 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 0 | 0 | 5488 | UNSE | Remote Grid / Removal | Scoping | ECOP
35226878 | 13 | 0.58883 | 0.58883 | 0 | 2021 |  |  | 0.58883 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 3109 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35227001 | 13 | 0.7214 | 0.7214 | 0 | 2021 |  |  | 0.7214 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 3809 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35227002 | 13 | 0.43295 | 0.43295 | 0 | 2021 |  |  | 0.43295 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 2286 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35227003 | 13 | 0.58087 | 0.58087 | 0 | 2021 |  |  | 0.58087 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 3067 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35227004 | 13 | 0.3483 | 0.3483 | 0 | 2021 |  |  | 0.3483 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 1839 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35236439 | 13 | 1.12 | 1.12 | 0 |  |  |  | 1.12 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 5913.6 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35236660 | 13 | 0.48 | 0.48 | 0 |  |  |  | 0.48 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 2534.4 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35191383 | 14 | 1.3286 | 1.3286 | 0 | 2021 |  |  | 1.3286 | 0 | SILVERADO 2102 | SILVERADO 210258626 | 125 | 15.2217 | 663 | 14.6249 | 0.117 | Tier 3 | 7015 | 0 | 0 | 0 | ESTS | Overhead | Estimating | ECOP
35191318 | 14 | 2.2159 | 2.2159 | 0 | 2021 |  |  | 2.2159 | 0 | SILVERADO 2102 | SILVERADO 210258626 | 125 | 15.2217 | 663 | 14.6249 | 0.117 | Tier 3 | 11700 | 0 | 0 | 0 | ESTS | Overhead | Estimating | ECOP
35192290 | 15 | 5.0004 | 5.0004 | 0 | 2021 |  |  | 5.0004 | 0 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | 541 | 44.1915 | 811 | 49.924 | 0.092281 | Tier 3 | 26402 | 0 | 0 | 0 | ADER | Overhead | Estimating | ECOP
35226845 | 14 | 2.3674 | 2.3674 | 0 | 2021 |  |  | 2.3674 | 0 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | 541 | 44.1915 | 811 | 49.924 | 0.092281 | Tier 3 | 12500 | 0 | 0 | 0 | ESTS | Overhead | Estimating | ECOP
35231544 | 14 | 1.2 | 1.2 | 0 | 2021 |  |  | 1.2 | 0 | TIDEWATER 2106 | TIDEWATER 210614072 | 30 | 3.6652 | 18 | 19.5994 | 0.65331 | Tier 2 | 6336 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 50 Miles
35226627 | 13 | 0.31231 | 0.31231 | 0 | 2021 |  |  | 0.31231 | 0 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | Tier 3 | 1649 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 50 Miles
35226630 | 13 | 1.4061 | 1.4061 | 0 | 2021 |  |  | 1.4061 | 0 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | Tier 3 | 7424 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 50 Miles
35226631 | 13 | 1.5326 | 1.5326 | 0 | 2021 |  |  | 1.5326 | 0 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | Tier 3 | 8092 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 50 Miles
35217267 | 14 | 0.71 | 0.71 | 0 | 2021 |  |  | 0.71 | 0 | MARIPOSA 2102 | MARIPOSA 2102241564 | 14 | 0.71281 | 10 | 10.8148 | 0.77248 | Tier 2 & 3 | 3748.8 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 50 Miles
35227860 | 13 | 0.19583 | 0.19583 | 0 | 2021 |  |  | 0.19583 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 1034 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 50 Miles
35227861 | 13 | 1.5339 | 1.5339 | 0 | 2021 |  |  | 1.5339 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 8099 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 50 Miles
35227862 | 13 | 0.93466 | 0.93466 | 0 | 2021 |  |  | 0.93466 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 4935 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 50 Miles
35227863 | 13 | 0.79129 | 0.79129 | 0 | 2021 |  |  | 0.79129 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 4178 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 50 Miles
35227866 | 13 | 0.52386 | 0.52386 | 0 | 2021 |  |  | 0.52386 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 2766 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 50 Miles
35227867 | 13 | 0.99527 | 0.99527 | 0 | 2021 |  |  | 0.99527 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 5255 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 50 Miles
35227868 | 13 | 0.51686 | 0.51686 | 0 | 2021 |  |  | 0.51686 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 2729 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 50 Miles
35228187 | 13 | 0.62879 | 0.62879 | 0 | 2021 |  |  | 0.62879 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 3320 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 50 Miles
35228188 | 13 | 3.73 | 3.73 | 0 | 2021 |  |  | 3.73 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 0 | 0 | 19694.4 | 0 | UNSE | Remote Grid / Removal | Scoping | Top 50 Miles
35236661 | 13 | 0.22 | 0.22 | 0 |  |  |  | 0.22 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 1161.6 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 50 Miles
35222045 | 13 | 0.88864 | 0.88864 | 0 | 2021 |  |  | 0.88864 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 4692 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 50 Miles
35226846 | 14 | 1.5714 | 1.5714 | 0 | 2021 |  |  | 1.5714 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 8297 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 20% MAVF CPZ
35226847 | 14 | 1.9839 | 1.9839 | 0 | 2021 |  |  | 1.9839 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 10475 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 20% MAVF CPZ
35231607 | 14 | 1.646 | 1.646 | 0 | 2021 |  |  | 1.646 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 8691 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 20% MAVF CPZ
35231609 | 14 | 1.3301 | 1.3301 | 0 | 2021 |  |  | 1.3301 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 7023 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 20% MAVF CPZ
35226848 | 14 | 2.4445 | 2.4445 | 0 | 2021 |  |  | 2.4445 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 12907 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 20% MAVF CPZ
35226850 | 14 | 1.5451 | 1.5451 | 0 | 2021 |  |  | 1.5451 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 8158 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 20% MAVF CPZ
35226851 | 14 | 1.8784 | 1.8784 | 0 | 2021 |  |  | 1.8784 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 9918 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 20% MAVF CPZ
35232280 | 18 | 0.6 | 0.6 | 0 | 2021 |  |  | 0.6 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 3168 | 0 | 0 | 0 | PEND | Overhead | Dependencies | Top 20% MAVF CPZ
35226852 | 14 | 2.4932 | 2.4932 | 0 | 2021 |  |  | 2.4932 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | Tier 3 | 13164 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 20% MAVF CPZ
35226853 | 14 | 2.8044 | 2.8044 | 0 | 2021 |  |  | 2.8044 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | Tier 3 | 14807 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 20% MAVF CPZ
35226854 | 14 | 1.0299 | 1.0299 | 0 | 2021 |  |  | 1.0299 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | Tier 3 | 5438 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 20% MAVF CPZ
35226856 | 14 | 1.9436 | 1.9436 | 0 | 2021 |  |  | 1.9436 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | Tier 3 | 10262 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 20% MAVF CPZ
35026643 | 13 | 1.6339 | 1.6339 | 0 | 2021 |  |  | 1.6339 | 0 | DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 11052102 | 417 | 37.4816 | 666 | 48.4576 | 0.11621 | Tier 2 | 5727 | 0 | 2900 | 0 | UNSE | Remote Grid / Removal | Scoping | Top 20% MAVF CPZ
35075103 | 18 | 0.59 | 0.59 | 0 | 2021 |  |  | 0.59 | 0 | FROGTOWN 1701 | FROGTOWN 17011623 | 152 | 15.2605 | 721 | 16.3546 | 0.1076 | Tier 3 | 3115.2 | 0 | 0 | 0 | PEND | Overhead | Dependencies | Top 20% MAVF CPZ
77799999 | 0 | 31.8 | 31.8 | 0 | 2021 |  |  | 31.8 | 0 | VARIOUS | VARIOUS | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 167904 | 0 | UNSE | Remote Grid / Removal | Scoping | Line Removal
35226625 | 2 | 7.9 | 7.9 | 0 | 2021 |  |  | 7.9 | 0 | ELK CREEK 1101 | ELK CREEK 11012106 | 67 | 13.2402 | 340 | 13.1388 | 0.1961 |  | 0 | 0 | 0 | 41712 | UNSE | Remote Grid / Removal | Scoping | FRRB
35217274 | 13 | 2.52 | 2.52 | 0 | 2021 |  |  | 2.52 | 0 | HALF MOON BAY 1103 | HALF MOON BAY 110369412 | 150 | 15.5679 | 2055 | 1.1767 | 0.0078448 |  | 0 | 13305.6 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35217275 | 13 | 2.9 | 2.9 | 0 | 2021 |  |  | 2.9 | 0 | HALF MOON BAY 1103 | HALF MOON BAY 110369412 | 150 | 15.5679 | 2055 | 1.1767 | 0.0078448 |  | 0 | 15312 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35226626 | 2 | 4.03 | 4.03 | 0 | 2021 |  |  | 4.03 | 0 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 11136751 | 139 | 22.6749 | 945 | 10.2759 | 0.073927 |  | 0 | 0 | 0 | 21278.4 | UNSE | Remote Grid / Removal | Scoping | FRRB
35199565 | 14 | 2.56 | 2.56 | 0 | 2021 |  |  | 2.56 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 13516.8 | 0 | 0 | 0 | ESTS | Overhead | Estimating | FRRB
35200051 | 14 | 4.8 | 4.8 | 0 | 2021 |  |  | 4.8 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 25344 | 0 | 0 | ESTS | Underground | Estimating | FRRB
35199565 | 14 | 6.72 | 6.72 | 0 | 2021 |  |  | 6.72 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 |  | 35481.6 | 0 | 0 | 0 | ESTS | Overhead | Estimating | FRRB
35200051 | 14 | 7.25 | 7.25 | 0 | 2021 |  |  | 7.25 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 |  | 0 | 38280 | 0 | 0 | ESTS | Underground | Estimating | FRRB
35220936 | 5 | 0.95 | 0.95 | 0 | 2021 |  |  | 0.95 | 0 | HALF MOON BAY 1103 | HALF MOON BAY 11036012 | 79 | 6.6683 | 2186 | 0.42722 | 0.0054078 |  | 0 | 5016 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35223343 | 14 | 0.85019 | 0.85019 | 0 | 2021 |  |  | 0.85019 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | Tier 3 | 0 | 4489 | 0 | 0 | ESTS | Underground | Estimating | FRRB
35225821 | 14 | 0.63371 | 0.63371 | 0 | 2021 |  |  | 0.63371 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 3346 | 0 | 0 | ESTS | Underground | Estimating | FRRB
35235139 | 7 | 1.3186 | [5 empty] | 1.3186 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 6962 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35235676 | 7 | 2.3958 | 2.3958 | 0 |  |  |  | 2.3958 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 12650 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35229043 | 7 | 0.41345 | 0.41345 | 0 | 2021 | 0.41 |  | 0.41345 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | Tier 3 | 0 | 2183 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35223344 | 19 | 4.1617 | 4.1617 | 0 | 2021 |  |  | 4.1617 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | Tier 3 | 0 | 21974 | 0 | 0 | UNSC | Underground | Construction | FRRB
35223345 | 19 | 4.454 | 4.454 | 0 | 2021 |  |  | 4.454 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | Tier 3 | 0 | 23517 | 0 | 0 | UNSC | Underground | Construction | FRRB
35225822 | 20 | 1.8693 | 1.8693 | 0 | 2021 |  |  | 1.8693 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | Tier 3 | 0 | 9870 | 0 | 0 | CONS | Underground | Construction | FRRB
35225823 | 20 | 1.7159 | 1.7159 | 0 | 2021 |  |  | 1.7159 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 9060 | 0 | 0 | CONS | Underground | Construction | FRRB
35225824 | 19 | 2.9364 | 2.9364 | 0 | 2021 |  |  | 2.9364 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 |  | 0 | 15504 | 0 | 0 | UNSC | Underground | Construction | FRRB
35222234 | 10 | 1.39 | 1.39 | 0 | 2021 |  |  | 1.39 | 0 | OAKHURST 1101 | OAKHURST 110110090 | 435 | 44.0886 | 421 | 75.8506 | 0.17437 |  | 0 | 0 | 0 | 7339.2 | UNSE | Remote Grid / Removal | Scoping | Remote Grid
35232298 | 14 | 0.24 | 0.24 | 0 | 2021 |  |  | 0.24 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1267.2 | 0 | 0 | ESTS | Underground | Estimating | FRRB
35233038 | 16 | 0.23 | 0.23 | 0 | 2021 |  |  | 0.23 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1214.4 | 0 | 0 | ESTS | Underground | Estimating | FRRB
35233039 | 13 | 0.37 | 0.37 | 0 | 2021 |  |  | 0.37 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1953.6 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35233300 | 13 | 0.32 | 0.32 | 0 | 2021 |  |  | 0.32 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1689.6 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35233301 | 13 | 0.36 | 0.36 | 0 | 2021 |  |  | 0.36 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1900.8 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35233302 | 16 | 0.12 | 0.12 | 0 | 2021 |  |  | 0.12 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 633.6 | 0 | 0 | UNSE | Underground | Estimating | FRRB
35233303 | 14 | 0.09 | 0.09 | 0 | 2021 |  |  | 0.09 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 475.2 | 0 | 0 | ESTS | Underground | Estimating | FRRB
35233304 | 14 | 0.3 | 0.3 | 0 | 2021 |  |  | 0.3 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1584 | 0 | 0 | UNSE | Underground | Estimating | FRRB
35233305 | 13 | 0.29 | 0.29 | 0 | 2021 |  |  | 0.29 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1531.2 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35233306 | 14 | 0.26 | 0.26 | 0 | 2021 |  |  | 0.26 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1372.8 | 0 | 0 | UNSE | Underground | Estimating | FRRB
35233307 | 16 | 0.6 | 0.6 | 0 | 2021 |  |  | 0.6 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 3168 | 0 | 0 | ESTS | Underground | Estimating | FRRB
35233308 | 16 | 0.93 | 0.93 | 0 | 2021 |  |  | 0.93 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 4910.4 | 0 | 0 | ESTS | Underground | Estimating | FRRB
35233309 | 13 | 0.37 | 0.37 | 0 | 2021 |  |  | 0.37 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1953.6 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35233310 | 14 | 0.15 | 0.15 | 0 | 2021 |  |  | 0.15 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 792 | 0 | 0 | UNSE | Underground | Estimating | FRRB
35232718 | 13 | 0.5 | 0.5 | 0 | 2021 |  |  | 0.5 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 2640 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35233311 | 13 | 0.58996 | 0.58996 | 0 | 2021 |  |  | 0.58996 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 3115 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35233312 | 13 | 1.1 | 1.1 | 0 | 2021 |  |  | 1.1 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 5808 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35233314 | 13 | 1.6 | 1.6 | 0 | 2021 |  |  | 1.6 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 8448 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35233315 | 13 | 0.96 | 0.96 | 0 | 2021 |  |  | 0.96 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 5068.8 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35235705 | 13 | 1.32 | 1.32 | 0 |  |  |  | 1.32 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 6969.6 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35235706 | 13 | 1.16 | 1.16 | 0 |  |  |  | 1.16 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 6125 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35235707 | 13 | 0.95 | 0.95 | 0 |  |  |  | 0.95 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 5016 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35239522 | 13 | 0.25 | 0.25 | 0 |  |  |  | 0.25 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1320 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35239523 | 13 | 0.25 | 0.25 | 0 |  |  |  | 0.25 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 1320 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35239937 | 13 | 0.58712 | 0.58712 | 0 |  |  |  | 0.58712 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 |  | 0 | 3100 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35235320 | 13 | 1.0015 | 1.0015 | 0 |  |  |  | 1.0015 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 5288 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35237889 | 13 | 1.3674 | 1.3674 | 0 |  |  |  | 1.3674 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 7220 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35237890 | 13 | 0.80795 | 0.80795 | 0 |  |  |  | 0.80795 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 4266 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35237891 | 13 | 0.45833 | 0.45833 | 0 |  |  |  | 0.45833 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 2420 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35237893 | 13 | 0.28958 | 0.28958 | 0 |  |  |  | 0.28958 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 1529 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35237894 | 13 | 0.85985 | 0.85985 | 0 |  |  |  | 0.85985 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 4540 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35237895 | 13 | 0.78939 | 0.78939 | 0 |  |  |  | 0.78939 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 4168 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35237896 | 13 | 1.1121 | 1.1121 | 0 |  |  |  | 1.1121 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 5872 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35236990 | 13 | 0.77652 | 0.77652 | 0 |  |  |  | 0.77652 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 4100 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35235669 | 13 | 0.41098 | 0.41098 | 0 |  |  |  | 0.41098 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 2170 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35235671 | 13 | 0.49242 | 0.49242 | 0 |  |  |  | 0.49242 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 2600 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35239095 | 13 | 1.1326 | 1.1326 | 0 |  |  |  | 1.1326 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 5980 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35239096 | 13 | 0.88125 | 0.88125 | 0 |  |  |  | 0.88125 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 4653 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35239097 | 13 | 1.0127 | 1.0127 | 0 |  |  |  | 1.0127 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 5347 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35239098 | 13 | 1.3792 | 1.3792 | 0 |  |  |  | 1.3792 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 7282 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35239099 | 13 | 0.65758 | 0.65758 | 0 |  |  |  | 0.65758 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 3472 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35236991 | 13 | 1.5188 | 1.5188 | 0 |  |  |  | 1.5188 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 8019 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35236993 | 13 | 0.39773 | 0.39773 | 0 |  |  |  | 0.39773 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 0 | 0 | 2100 | UNSE | Remote Grid / Removal | Scoping | FRRB
35236995 | 3 | 1.972 | 1.972 | 0 |  |  |  | 1.972 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 0 | 0 | 10412 | UNSE | Remote Grid / Removal | Scoping | FRRB
35235670 | 3 | 3.91 | 3.91 | 0 |  |  |  | 3.91 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 20645 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35235672 | 3 | 1.64 | 1.64 | 0 |  |  |  | 1.64 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 8659 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35235673 | 2 | 2.14 | 2.14 | 0 |  |  |  | 2.14 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 |  | 0 | 11299 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35235674 | 13 | 4.3 | 4.3 | 0 |  |  |  | 4.3 | 0 | BIG BEND 1102 | BIG BEND 1102CB | 139 | 17.0366 | 865 | 11.7994 | 0.084888 |  | 0 | 22704 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35235675 | 2 | 1 | 1 | 0 |  |  |  | 1 | 0 | BIG BEND 1102 | BIG BEND 1102CB | 139 | 17.0366 | 865 | 11.7994 | 0.084888 |  | 0 | 5280 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35235677 | 13 | 6.7297 | 6.7297 | 0 |  |  |  | 6.7297 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 35533 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35233166 | 14 | 0 |  | 0 | 2021 |  |  | 0 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 0 | 0 | 0 | UNSE | TBD | Estimating | FRRB
35235678 | 3 | 4.4 | 4.4 | 0 |  |  |  | 4.4 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 23232 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35235679 | 6 | 6.5 | 6.5 | 0 |  |  |  | 6.5 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 34320 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35235700 | 3 | 5.44 | 5.44 | 0 |  |  |  | 5.44 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 28723 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35235701 | 6 | 3.49 | 3.49 | 0 |  |  |  | 3.49 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 18427 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35235702 | 13 | 2.14 | 2.14 | 0 |  |  |  | 2.14 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 11299 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35235703 | 13 | 8.44 | 8.44 | 0 |  |  |  | 8.44 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 44563 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35235704 | 13 | 6.1 | 6.1 | 0 |  |  |  | 6.1 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 32208 | 0 | 0 | UNSE | Underground | Scoping | FRRB
35237021 | 13 | 0 | 0 | 0 |  |  |  | 0 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 0 | 0 | 0 | UNSE | TBD | Scoping | FRRB
35236983 | 3 | 0.30303 | 0.30303 | 0 |  |  |  | 0.30303 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 0 | 0 | 1600 | UNSE | Remote Grid / Removal | Scoping | FRRB
35236997 | 6 | 1.6562 | 1.6562 | 0 |  |  |  | 1.6562 | 0 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 |  | 0 | 0 | 0 | 8745 | UNSE | Remote Grid / Removal | Scoping | FRRB
35236982 | 2 | 1.9248 | 1.9248 | 0 |  |  |  | 1.9248 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 0 | 0 | 10163 | UNSE | Remote Grid / Removal | Scoping | FRRB
35236985 | 3 | 1.5911 | 1.5911 | 0 |  |  |  | 1.5911 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 0 | 0 | 8401 | UNSE | Remote Grid / Removal | Scoping | FRRB
35236986 | 13 | 1.5748 | 1.5748 | 0 |  |  |  | 1.5748 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 0 | 0 | 8315 | UNSE | Remote Grid / Removal | Scoping | FRRB
35236988 | 13 | 0.24489 | 0.24489 | 0 |  |  |  | 0.24489 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 0 | 0 | 1293 | UNSE | Remote Grid / Removal | Scoping | FRRB
35236989 | 6 | 0.47216 | 0.47216 | 0 |  |  |  | 0.47216 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 0 | 0 | 2493 | UNSE | Remote Grid / Removal | Scoping | FRRB
35236992 | 3 | 0.58712 | 0.58712 | 0 |  |  |  | 0.58712 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 0 | 0 | 3100 | UNSE | Remote Grid / Removal | Scoping | FRRB
35236999 | 13 | 1.0038 | 1.0038 | 0 |  |  |  | 1.0038 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 0 | 0 | 5300 | UNSE | Remote Grid / Removal | Scoping | FRRB
35237020 | 13 | 0.39773 | 0.39773 | 0 |  |  |  | 0.39773 | 0 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 |  | 0 | 0 | 0 | 2100 | UNSE | Remote Grid / Removal | Scoping | FRRB
35236984 | 3 | 1.8559 | 1.8559 | 0 |  |  |  | 1.8559 | 0 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 |  | 0 | 0 | 0 | 9799 | UNSE | Remote Grid / Removal | Scoping | FRRB
35222236 | 11 | 0.84 | 0.84 | 0 | 2021 |  |  | 0.84 | 0 | MARIPOSA 2101 | MARIPOSA 210135244 | 146 | 17.4635 | 428 | 25.237 | 0.17286 |  | 0 | 0 | 0 | 4435.2 | UNSE | Remote Grid / Removal | Scoping | Remote Grid
35175853 | 13 | 0.7 | 0.7 | 0 | 2021 |  |  | 0.7 | 0 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 |  | 0 | 0 | 0 | 3696 | UNSE | Remote Grid / Removal | Scoping | Remote Grid
35222235 | 10 | 2.48 | 2.48 | 0 | 2021 |  |  | 2.48 | 0 | DUNLAP 1102 | DUNLAP 1102778286 | 5 | 2.6029 | 2738 | 0.0024545 | 0.0004909 |  | 0 | 0 | 0 | 13094.4 | UNSE | Remote Grid / Removal | Scoping | Remote Grid
35229051 | 10 | 3.04 | 3.04 | 0 | 2021 |  |  | 3.04 | 0 | CORNING 1102 | CORNING 110253184 | 123 | 31.8239 | 413 | 21.5791 | 0.17544 |  | 0 | 0 | 0 | 16051 | UNSE | Remote Grid / Removal | Scoping | Remote Grid
35219543 | 13 | 0.24015 | 0.24015 | 0 | 2021 |  |  | 0.24015 | 0 | PLACERVILLE 1112 | PLACERVILLE 1112CB | 117 | 8.513 | 2123 | 0.76223 | 0.0065148 | Tier 2 | 0 | 1268 | 0 | 0 | UNSE | Underground | Scoping | PSPS
35223036 | 13 | 0.055871 | 0.055871 | 0 | 2021 |  |  | 0.055871 | 0 | BRUNSWICK 1110 | BRUNSWICK 1110CB | 26 | 0.0034177 | 2134 | 0.16685 | 0.0064174 |  | 0 | 295 | 0 | 0 | UNSE | Underground | Scoping | PSPS
35223030 | 13 | 0.85 | 0.85 | 0 | 2021 |  |  | 0.85 | 0 | BANGOR 1101 | BANGOR 1101CB | 171 | 18.7561 | 355 | 33.1366 | 0.19378 |  | 0 | 4488 | 0 | 0 | UNSE | Underground | Scoping | PSPS
35223062 | 13 | 0.18 | 0.18 | 0 | 2021 |  |  | 0.18 | 0 | CALISTOGA 1102 | CALISTOGA 1102184814 | 20 | 0.42402 | 3098 | 0.00017414 | 8.707e-06 | Tier 2 | 0 | 950.4 | 0 | 0 | UNSE | Underground | Scoping | PSPS
35223038 | 10 | 0.46 | 0.46 | 0 | 2021 |  |  | 0.46 | 0 | MARTELL 1101 | MARTELL 1101CB | 171 | 5.879 | 999 | 11.5263 | 0.067405 | Tier 2 | 0 | 2428.8 | 0 | 0 | UNSE | Underground | Scoping | PSPS
35234284 | 10 | 0.45 | 0.45 | 0 | 2021 |  |  | 0.45 | 0 | MARTELL 1101 | MARTELL 1101CB | 171 | 5.879 | 999 | 11.5263 | 0.067405 | Tier 2 | 0 | 2376 | 0 | 0 | UNSE | Underground | Scoping | PSPS
35234526 | 10 | 0.4 | 0.4 | 0 | 2021 |  |  | 0.4 | 0 | MARTELL 1101 | MARTELL 1101CB | 171 | 5.879 | 999 | 11.5263 | 0.067405 | Tier 2 | 2112 | 0 | 0 | 0 | UNSE | Overhead | Scoping | PSPS
35223060 | 9 | 1.74 | 1.74 | 0 | 2021 |  |  | 1.74 | 0 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 |  | 0 | 9187.2 | 0 | 0 | UNSE | Underground | Scoping | PSPS
35234527 | 9 | 0 | 0 | 0 | 2021 |  |  | 0 | 0 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 |  | 0 | 0 | 0 | 0 | UNSE | TBD | Scoping | PSPS
35234528 | 9 |  |  | 0 | 2021 |  |  | 0 | 0 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 |  | 0 | 0 | 0 | 0 | UNSE | TBD | Scoping | PSPS
35234529 | 9 |  |  | 0 | 2021 |  |  | 0 | 0 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 |  | 0 | 0 | 0 | 0 | UNSE | TBD | Scoping | PSPS
35223063 | 10 | 0.15114 | 0.15114 | 0 | 2021 |  |  | 0.15114 | 0 | DUNBAR 1101 | DUNBAR 1101CB | 191 | 3.1203 | 2048 | 1.5267 | 0.007993 | Tier 2 | 0 | 798 | 0 | 0 | UNSE | Underground | Scoping | PSPS
35228774 | 10 | 0.97405 | 0.97405 | 0 | 2021 |  |  | 0.97405 | 0 | DUNBAR 1101 | DUNBAR 1101CB | 191 | 3.1203 | 2048 | 1.5267 | 0.007993 | Tier 2 | 0 | 5143 | 0 | 0 | UNSE | Underground | Scoping | PSPS
35228775 | 10 | 0.88617 | 0.88617 | 0 | 2021 |  |  | 0.88617 | 0 | DUNBAR 1101 | DUNBAR 1101CB | 191 | 3.1203 | 2048 | 1.5267 | 0.007993 | Tier 2 | 0 | 4679 | 0 | 0 | UNSE | Underground | Scoping | PSPS
35223032 | 13 | 0.43087 | 0.43087 | 0 | 2021 |  |  | 0.43087 | 0 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 2101CB | 262 | 24.9941 | 68 | 101.3032 | 0.38665 | Tier 2 | 0 | 2275 | 0 | 0 | UNSE | Underground | Scoping | PSPS
35223037 | 18 | 0.052083 | 0.052083 | 0 | 2021 |  |  | 0.052083 | 0 | OAKHURST 1101 | OAKHURST 1101CB | 47 | 2.3149 | 847 | 4.0694 | 0.086583 | Tier 3 | 0 | 275 | 0 | 0 | PEND | Underground | Dependencies | PSPS
35224377 | 13 | 0.13996 | 0.13996 | 0 | 2021 |  |  | 0.13996 | 0 | PLACERVILLE 2106 | PLACERVILLE 21067522 | 745 | 67.3656 | 1363 | 26.4689 | 0.035529 | Tier 3 | 0 | 739 | 0 | 0 | UNSE | Underground | Scoping | PSPS
35233995 | 13 | 0.5 | 0.5 | 0 | 2021 |  |  | 0.5 | 0 | PLACERVILLE 2106 | PLACERVILLE 21067522 | 745 | 67.3656 | 1363 | 26.4689 | 0.035529 | Tier 3 | 0 | 2640 | 0 | 0 | UNSE | Underground | Scoping | PSPS
35233996 | 13 | 0.71 | 0.71 | 0 | 2021 |  |  | 0.71 | 0 | PLACERVILLE 2106 | PLACERVILLE 21067522 | 745 | 67.3656 | 1363 | 26.4689 | 0.035529 | Tier 3 | 0 | 3748.8 | 0 | 0 | UNSE | Underground | Scoping | PSPS
35223039 | 13 | 0.60739 | 0.60739 | 0 | 2021 |  |  | 0.60739 | 0 | WYANDOTTE 1109 | WYANDOTTE 1109702710 | 49 | 2.6641 | 218 | 12.174 | 0.24845 | Tier 2 | 705 | 2502 | 0 | 0 | UNSE | Hybrid | Scoping | PSPS
35219542 | 11 | 0.14 | 0.14 | 0 | 2021 |  |  | 0.14 | 0 | PLACERVILLE 1112 | PLACERVILLE 1112CB | 117 | 8.513 | 2123 | 0.76223 | 0.0065148 | Tier 2 | 0 | 739.2 | 0 | 0 | UNSE | Underground | Scoping | PSPS
35144944 | 18 | 0.26 | 0.26 | 0 |  |  |  | 0.26 | 0 | SNEATH LANE 1107 | SNEATH LANE 1107CB | 45 | 1.0038 | 2336 | 0.14045 | 0.003121 |  | 1372.8 | 0 | 0 | 0 | PEND | Overhead | Dependencies | PSPS
35219291 | 18 | 0.39811 | 0.39811 | 0 | 2021 |  |  | 0.39811 | 0 | VACA DIXON 1101 | VACA DIXON 1101126774 | 11 | 0.78766 | 20 | 6.8232 | 0.62029 | Tier 2 | 2102 | 0 | 0 | 0 | PEND | Overhead | Dependencies | Top 250 Miles
35219097 | 14 | 2.36 | 2.36 | 0 | 2021 |  |  | 2.36 | 0 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | Tier 2 | 12460.8 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 250 Miles
35227260 | 14 | 2.36 | 2.36 | 0 | 2021 |  |  | 2.36 | 0 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | Tier 2 | 12460.8 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 250 Miles
35227261 | 14 | 2.16 | 2.16 | 0 | 2021 |  |  | 2.16 | 0 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | Tier 2 | 11404.8 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 250 Miles
35227262 | 14 | 1.4015 | 1.4015 | 0 | 2021 |  |  | 1.4015 | 0 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | Tier 2 | 7400 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 250 Miles
35219098 | 14 | 0.72 | 0.72 | 0 | 2021 |  |  | 0.72 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101118494 | 12 | 1.0659 | 23 | 6.971 | 0.58092 | Tier 2 & 3 | 3801.6 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 250 Miles
35229119 | 13 | 0.61 | 0.61 | 0 | 2021 |  |  | 0.61 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101118494 | 12 | 1.0659 | 23 | 6.971 | 0.58092 | Tier 2 & 3 | 0 | 3220.8 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35219099 | 13 | 2.7269 | 2.7269 | 0 | 2021 |  |  | 2.7269 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 14398 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35231620 | 13 | 2.6782 | 2.6782 | 0 | 2021 |  |  | 2.6782 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 0 | 14141 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35231621 | 13 | 1.3655 | 1.3655 | 0 | 2021 |  |  | 1.3655 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 0 | 7210 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35231622 | 13 | 2.8339 | 2.8339 | 0 | 2021 |  |  | 2.8339 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 0 | 0 | 0 | 14963 | UNSE | Remote Grid / Removal | Scoping | Top 250 Miles
35231623 | 13 | 1.3784 | 1.3784 | 0 | 2021 |  |  | 1.3784 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 1078 | 0 | 0 | 6200 | UNSE | Remote Grid / Removal | Scoping | Top 250 Miles
35231624 | 13 | 0.77576 | 0.77576 | 0 | 2021 |  |  | 0.77576 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 4096 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35231625 | 13 | 0.7392 | 0.7392 | 0 | 2021 |  |  | 0.7392 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 0 | 0 | 0 | 3903 | UNSE | Remote Grid / Removal | Scoping | Top 250 Miles
35231626 | 13 | 0.68314 | 0.68314 | 0 | 2021 |  |  | 0.68314 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 3607 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35231627 | 13 | 0.39867 | 0.39867 | 0 | 2021 |  |  | 0.39867 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 2105 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35231628 | 13 | 7.2661 | 7.2661 | 0 | 2021 |  |  | 7.2661 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 7861 | 0 | 0 | 30504 | UNSE | Remote Grid / Removal | Scoping | Top 250 Miles
35231629 | 13 | 1.3808 | 1.3808 | 0 | 2021 |  |  | 1.3808 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 902 | 0 | 0 | 6388.8 | UNSE | Remote Grid / Removal | Scoping | Top 250 Miles
35231630 | 13 | 0.36345 | 0.36345 | 0 | 2021 |  |  | 0.36345 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 1919 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35231631 | 13 | 0.46686 | 0.46686 | 0 | 2021 |  |  | 0.46686 | 0 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | Tier 2 & 3 | 2465 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35219260 | 15 | 0.84432 | 0.84432 | 0 | 2021 |  |  | 0.84432 | 0 | WYANDOTTE 1109 | WYANDOTTE 110932586 | 15 | 1.3417 | 29 | 7.9481 | 0.52987 | Tier 2 | 4458 | 0 | 0 | 0 | ADER | Overhead | Estimating | Top 250 Miles
35219266 | 15 | 2.6 | 2.6 | 0 | 2021 |  |  | 2.6 | 0 | MARIPOSA 2102 | MARIPOSA 2102CB | 31 | 5.2539 | 35 | 14.6212 | 0.47165 | Tier 2 | 13728 | 0 | 0 | 0 | ADER | Overhead | Estimating | Top 250 Miles
35227263 | 14 | 0.25 | 0.25 | 0 | 2021 |  |  | 0.25 | 0 | MARIPOSA 2102 | MARIPOSA 2102CB | 31 | 5.2539 | 35 | 14.6212 | 0.47165 | Tier 2 | 1320 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 250 Miles
35219268 | 14 | 1.6212 | 1.6212 | 0 | 2021 |  |  | 1.6212 | 0 | MARIPOSA 2101 | MARIPOSA 210197142 | 40 | 4.6029 | 36 | 18.8487 | 0.47122 | Tier 2 | 8560 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 250 Miles
35226241 | 15 | 1.4799 | 1.4799 | 0 | 2021 |  |  | 1.4799 | 0 | MARIPOSA 2101 | MARIPOSA 210197142 | 40 | 4.6029 | 36 | 18.8487 | 0.47122 | Tier 2 | 7814 | 0 | 0 | 0 | ADER | Overhead | Estimating | Top 250 Miles
35226240 | 18 | 1.4625 | 1.4625 | 0 | 2021 |  |  | 1.4625 | 0 | MARIPOSA 2101 | MARIPOSA 210197142 | 40 | 4.6029 | 36 | 18.8487 | 0.47122 | Tier 2 | 7722 | 0 | 0 | 0 | PEND | Overhead | Dependencies | Top 250 Miles
35238567 | 14 | 0 | 0 | 0 |  |  |  | 0 | 0 | MARIPOSA 2101 | MARIPOSA 210197142 | 40 | 4.6029 | 36 | 18.8487 | 0.47122 | Tier 2 | 0 | 0 | 0 | 0 | UNSE | TBD | Estimating | Top 250 Miles
35219269 | 10 | 2.14 | 2.14 | 0 | 2021 |  |  | 2.14 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 11299.2 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35237258 | 10 | 2.15 | 2.15 | 0 |  |  |  | 2.15 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 11352 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35237259 | 10 | 3.2 | 3.2 | 0 |  |  |  | 3.2 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 16896 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35237360 | 10 | 3.01 | 3.01 | 0 |  |  |  | 3.01 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 15892.8 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35237361 | 10 | 2.87 | 2.87 | 0 |  |  |  | 2.87 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 15153.6 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35237364 | 10 | 3.03 | 3.03 | 0 |  |  |  | 3.03 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 15998.4 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35237365 | 10 | 2.81 | 2.81 | 0 |  |  |  | 2.81 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 14836.8 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35237366 | 10 | 2.19 | 2.19 | 0 |  |  |  | 2.19 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 11563.2 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35237368 | 10 | 2.93 | 2.93 | 0 |  |  |  | 2.93 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 15470.4 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35237369 | 10 | 2.38 | 2.38 | 0 |  |  |  | 2.38 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 12566.4 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35237370 | 10 | 3.53 | 3.53 | 0 |  |  |  | 3.53 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 18638.4 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35237371 | 10 | 0.34 | 0.34 | 0 |  |  |  | 0.34 | 0 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 |  | 1795.2 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35219272 | 14 | 0.85436 | 0.85436 | 0 | 2021 |  |  | 0.85436 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101481876 | 14 | 0.8534 | 38 | 6.5476 | 0.46769 | Tier 2 & 3 | 4511 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 250 Miles
35219273 | 14 | 3.461 | 3.461 | 0 | 2021 |  |  | 3.461 | 0 | VOLTA 1101 | VOLTA 110149742 | 28 | 3.4766 | 39 | 13.0013 | 0.46433 | Tier 2 | 18274 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 250 Miles
35219275 | 18 | 0.52 | 0.52 | 0 | 2021 |  |  | 0.52 | 0 | PUTAH CREEK 1102 | PUTAH CREEK 110246012 | 38 | 0.63713 | 41 | 17.3115 | 0.45557 | Tier 2 | 2745.6 | 0 | 0 | 0 | PEND | Overhead | Dependencies | Top 250 Miles
35219276 | 13 | 2.16 | 2.16 | 0 | 2021 |  |  | 2.16 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 0 | 11404.8 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35227651 | 13 | 2.31 | 2.31 | 0 | 2021 |  |  | 2.31 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 12196.8 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35227652 | 13 | 0.41 | 0.41 | 0 | 2021 |  |  | 0.41 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 0 | 2164.8 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35227653 | 13 | 2 | 2 | 0 | 2021 |  |  | 2 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 10560 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35227654 | 13 | 0.72 | 0.72 | 0 | 2021 |  |  | 0.72 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 3801.6 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35224378 | 13 | 3.14 | 3.14 | 0 | 2021 |  |  | 3.14 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 16579.2 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35227870 | 13 | 1.42 | 1.42 | 0 | 2021 |  |  | 1.42 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 316.8 | 7180.8 | 0 | 0 | UNSE | Hybrid | Scoping | Top 250 Miles
35227656 | 13 | 1.33 | 1.33 | 0 | 2021 |  |  | 1.33 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 1742.4 | 5280 | 0 | 0 | UNSE | Hybrid | Scoping | Top 250 Miles
35227657 | 13 | 0.46 | 0.46 | 0 | 2021 |  |  | 0.46 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 2428.8 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35227658 | 13 | 0.54 | 0.54 | 0 | 2021 |  |  | 0.54 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 1478.4 | 1372.8 | 0 | 0 | UNSE | Hybrid | Scoping | Top 250 Miles
35227659 | 13 | 0.24 | 0.24 | 0 | 2021 |  |  | 0.24 | 0 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | Tier 3 | 1267.2 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35219280 | 13 | 0.15152 | 0.15152 | 0 | 2021 |  |  | 0.15152 | 0 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110564118 | 101 | 1.6451 | 43 | 44.7046 | 0.44262 | Tier 2 | 0 | 800 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35226632 | 13 | 1.6828 | 1.6828 | 0 | 2021 |  |  | 1.6828 | 0 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110564118 | 101 | 1.6451 | 43 | 44.7046 | 0.44262 |  | 8885 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35232651 | 13 | 1.74 | 1.74 | 0 | 2021 |  |  | 1.74 | 0 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | 58 | 5.7104 | 45 | 25.2473 | 0.4353 |  | 9187 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35219286 | 13 | 3.4547 | 3.4547 | 0 | 2021 |  |  | 3.4547 | 0 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | Tier 2 | 18241 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35232960 | 13 | 3.0411 | 3.0411 | 0 | 2021 |  |  | 3.0411 | 0 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | Tier 2 | 16057 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35225825 | 13 | 1.5562 | 1.5562 | 0 | 2021 |  |  | 1.5562 | 0 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | Tier 2 | 8217 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35232442 | 13 | 3.0778 | 3.0778 | 0 | 2021 |  |  | 3.0778 | 0 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | Tier 2 | 16251 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35232443 | 13 | 1.0356 | 1.0356 | 0 | 2021 |  |  | 1.0356 | 0 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | Tier 2 | 5468 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35232444 | 13 | 3.5318 | 3.5318 | 0 | 2021 |  |  | 3.5318 | 0 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | Tier 2 | 18648 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35232445 | 13 | 2.6038 | 2.6038 | 0 | 2021 |  |  | 2.6038 | 0 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | Tier 2 | 13748 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35219289 | 13 | 4.3544 | 4.3544 | 0 | 2021 |  |  | 4.3544 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 22991 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35233947 | 13 | 1.8436 | 1.8436 | 0 | 2021 |  |  | 1.8436 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 9734 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35233948 | 13 | 2.5871 | 2.5871 | 0 | 2021 |  |  | 2.5871 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 13660 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35233949 | 13 | 1.9769 | 1.9769 | 0 | 2021 |  |  | 1.9769 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 10438 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35233950 | 13 | 2.7542 | 2.7542 | 0 | 2021 |  |  | 2.7542 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 14542 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35233951 | 13 | 1.5648 | 1.5648 | 0 | 2021 |  |  | 1.5648 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 8262 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35225826 | 13 | 2.5424 | 2.5424 | 0 | 2021 |  |  | 2.5424 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 13424 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35233952 | 13 | 2.1616 | 2.1616 | 0 | 2021 |  |  | 2.1616 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 11413 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35233953 | 13 | 0.84034 | 0.84034 | 0 | 2021 |  |  | 0.84034 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 4437 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35233955 | 13 | 0.54924 | 0.54924 | 0 | 2021 |  |  | 0.54924 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 2900 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35233957 | 13 | 0.10208 | 0.10208 | 0 | 2021 |  |  | 0.10208 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 539 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35233959 | 13 | 0.34602 | 0.34602 | 0 | 2021 |  |  | 0.34602 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 1827 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35234381 | 13 | 1.5468 | 1.5468 | 0 | 2021 |  |  | 1.5468 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 8167 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35234382 | 13 | 1.5875 | 1.5875 | 0 | 2021 |  |  | 1.5875 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 8382 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35225827 | 13 | 0.84564 | 0.84564 | 0 | 2021 |  |  | 0.84564 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 4465 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35233954 | 13 | 0.21212 | 0.21212 | 0 | 2021 |  |  | 0.21212 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 1120 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35233956 | 13 | 0.25455 | 0.25455 | 0 | 2021 |  |  | 0.25455 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 1344 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35233958 | 13 | 0.20814 | 0.20814 | 0 | 2021 |  |  | 0.20814 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 1099 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35234380 | 13 | 2.2419 | 2.2419 | 0 | 2021 |  |  | 2.2419 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 11837 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35234383 | 13 | 1.1985 | 1.1985 | 0 | 2021 |  |  | 1.1985 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 6328 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35234384 | 13 | 0.058144 | 0.058144 | 0 | 2021 |  |  | 0.058144 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 307 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35234385 | 13 | 0.67443 | 0.67443 | 0 | 2021 |  |  | 0.67443 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 3561 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35234386 | 13 | 0.85777 | 0.85777 | 0 | 2021 |  |  | 0.85777 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 4529 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35225828 | 13 | 2.5314 | 2.5314 | 0 | 2021 |  |  | 2.5314 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 13366 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35234387 | 13 | 0.93996 | 0.93996 | 0 | 2021 |  |  | 0.93996 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 4963 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35234388 | 13 | 2.0402 | 2.0402 | 0 | 2021 |  |  | 2.0402 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 10772 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35234389 | 13 | 0.9 | 0.9 | 0 | 2021 |  |  | 0.9 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 4752 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35234390 | 13 | 0.52008 | 0.52008 | 0 | 2021 |  |  | 0.52008 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 2746 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35234391 | 13 | 1.26 | 1.26 | 0 | 2021 |  |  | 1.26 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 6653 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35234392 | 13 | 1.66 | 1.66 | 0 | 2021 |  |  | 1.66 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 8765 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35225829 | 13 | 2.19 | 2.19 | 0 | 2021 |  |  | 2.19 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 11563.2 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35234393 | 13 | 2.42 | 2.42 | 0 | 2021 |  |  | 2.42 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 12777.6 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35234394 | 13 | 2.3858 | 2.3858 | 0 | 2021 |  |  | 2.3858 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 9451.2 | 0 | 3146 | 0 | UNSE | Remote Grid / Removal | Scoping | Top 250 Miles
35234395 | 13 | 2.71 | 2.71 | 0 | 2021 |  |  | 2.71 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 14308.8 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35234396 | 13 | 1.69 | 1.69 | 0 | 2021 |  |  | 1.69 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 8923.2 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35234397 | 13 | 0.72 | 0.72 | 0 | 2021 |  |  | 0.72 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 3801.6 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35219287 | 11 | 2.3962 | 2.3962 | 0 | 2021 |  |  | 2.3962 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 12652 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35234398 | 11 | 2.8525 | 2.8525 | 0 | 2021 |  |  | 2.8525 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 15061 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35234399 | 11 | 0.48011 | 0.48011 | 0 | 2021 |  |  | 0.48011 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 0 | 2535 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35234400 | 11 | 1.39 | 1.39 | 0 | 2021 |  |  | 1.39 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 7339 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35234401 | 11 | 1.85 | 1.85 | 0 | 2021 |  |  | 1.85 | 0 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 |  | 9768 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35219267 | 9 | 4.27 | 4.27 | 0 | 2021 |  |  | 4.27 | 0 | MARIPOSA 2102 | MARIPOSA 2102440236 | 38 | 4.2727 | 50 | 15.979 | 0.4205 | Tier 2 & 3 | 22545.6 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35219587 | 9 | 2.16 | 2.16 | 0 | 2021 |  |  | 2.16 | 0 | MARIPOSA 2102 | MARIPOSA 2102440236 | 38 | 4.2727 | 50 | 15.979 | 0.4205 |  | 11404.8 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35219588 | 9 | 2.16 | 2.16 | 0 | 2021 |  |  | 2.16 | 0 | MARIPOSA 2102 | MARIPOSA 2102440236 | 38 | 4.2727 | 50 | 15.979 | 0.4205 |  | 11404.8 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35219589 | 13 | 2.81 | 2.81 | 0 | 2021 |  |  | 2.81 | 0 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | Tier 2 | 14836.8 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35224321 | 14 | 2.46 | 2.46 | 0 | 2021 |  |  | 2.46 | 0 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | Tier 2 | 12988.8 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 250 Miles
35226798 | 13 | 1.72 | 1.72 | 0 | 2021 |  |  | 1.72 | 0 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | Tier 2 | 9081.6 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35226799 | 13 | 0.19 | 0.19 | 0 | 2021 |  |  | 0.19 | 0 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | Tier 2 | 1003.2 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35226900 | 13 | 0.69 | 0.69 | 0 | 2021 |  |  | 0.69 | 0 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | Tier 2 | 3643.2 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35219590 | 10 | 0.75 | 0.75 | 0 | 2021 |  |  | 0.75 | 0 | VACA DIXON 1105 | VACA DIXON 1105965390 | 21 | 0.75147 | 53 | 8.6971 | 0.41415 | Tier 2 | 3960 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35219591 | 11 | 1.34 | 1.34 | 0 | 2021 |  |  | 1.34 | 0 | OLETA 1101 | OLETA 1101754718 | 29 | 2.8841 | 54 | 11.8066 | 0.40712 |  | 7075.2 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35236662 | 11 | 1.67 | 1.67 | 0 |  |  |  | 1.67 | 0 | OLETA 1101 | OLETA 1101754718 | 29 | 2.8841 | 54 | 11.8066 | 0.40712 |  | 8817.6 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35192053 | 20 | 2.19 | 0 | 2.19 | 2021 | 2.19 |  | 2.19 | 2.19 | OAKHURST 1103 | OAKHURST 11035120 | 19 | 6.1606 | 1975 | 0.18333 | 0.0096488 | Tier 3 | 10401.6 | 0 | 0 | 0 | CONS | Overhead | Construction | Storm Rebuild
35227096 | 20 | 1.09 | 0 | 1.09 | 2021 | 1.09 |  | 1.09 | 1.09 | OAKHURST 1103 | OAKHURST 11035120 | 19 | 6.1606 | 1975 | 0.18333 | 0.0096488 | Tier 3 | 5598 | 0 | 0 | 0 | CONS | Overhead | Construction | Storm Rebuild
35227201 | 20 | 0.95 | 0 | 0.95 | 2021 | 0.95 |  | 0.95 | 0.95 | OAKHURST 1103 | OAKHURST 11035120 | 19 | 6.1606 | 1975 | 0.18333 | 0.0096488 | Tier 3 | 4355 | 0 | 0 | 0 | CONS | Overhead | Construction | Storm Rebuild
35228449 | 19 | 2.8937 | 0.08375 | 2.81 | 2021 | 2.81 |  | 2.8937 | 2.81 | RIO DELL 1102 | Rio Dell 11024230 | 59 | 22.9009 | 585 | 7.9721 | 0.13512 | Tier 2 | 15279 | 0 | 0 | 0 | DOCC | Overhead | Close-Out | Storm Rebuild
35056733 | 18 | 2.13 | 2.13 | 0 |  |  |  | 2.13 | 0 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | Tier 3 | 11246.4 | 0 | 0 | 0 | PEND | Overhead | Dependencies | PSS Approved
35109541 | 14 | 2.67 | 2.67 | 0 |  |  |  | 2.67 | 0 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | Tier 3 | 14097.6 | 0 | 0 | 0 | ESTS | Overhead | Estimating | PSS Approved
35057010 | 14 | 10.8799 | 10.8799 | 0 |  |  |  | 10.8799 | 0 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | Tier 3 | 57446 | 0 | 0 | 0 | ESTS | Overhead | Estimating | PSS Approved
35109546 | 15 | 2.77 | 2.77 | 0 |  |  |  | 2.77 | 0 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | Tier 3 | 14625 | 0 | 0 | 0 | ADER | Overhead | Estimating | PSS Approved
35057018 | 18 | 2.2511 | 2.2511 | 0 |  |  |  | 2.2511 | 0 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | Tier 3 | 507 | 11379 | 0 | 0 | PEND | Hybrid | Dependencies | PSS Approved
31272374 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | POINT MORETTI 1101 | POINT MORETTI 11015076 | 67 | 7.4948 | 1393 | 2.2618 | 0.033758 |  | 0 | 0 | 0 | 0 | DOCC | TBD | Close-Out | DSDD
35114040 | 20 | 1.4847 | 1.4847 | 0 | 2020 | 0 |  | 1.4847 | 0 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | Tier 3 | 7839 | 0 | 0 | 0 | CONS | Overhead | Construction | In-Construction
35052737 | 18 | 1.5867 | 1.5867 | 0 | 2020 | 0 |  | 1.5867 | 0 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | Tier 3 | 8378 | 0 | 0 | 0 | PEND | Overhead | Dependencies | DSDD
35192280 | 14 | 1.643 | 1.643 | 0 | 2021 |  |  | 1.643 | 0 | CLAYTON 2212 | CLAYTON 221296224 | 174 | 19.3992 | 377 | 32.6329 | 0.18755 | Tier 3 | 0 | 8675 | 0 | 0 | UNSE | Underground | Estimating | ECOP
35225589 | 14 | 1.0983 | 1.0983 | 0 | 2021 |  |  | 1.0983 | 0 | KONOCTI 1102 | KONOCTI 1102965078 | 59 | 6.2704 | 9 | 51.7008 | 0.87629 | Tier 3 | 5799 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 50 Miles
35225591 | 14 | 1.4723 | 1.4723 | 0 | 2021 |  |  | 1.4723 | 0 | KONOCTI 1102 | KONOCTI 1102965078 | 59 | 6.2704 | 9 | 51.7008 | 0.87629 | Tier 3 | 4527 | 0 | 3247 | 0 | UNSE | Remote Grid / Removal | Estimating | Top 50 Miles
35217268 | 14 | 0.25795 | 0.25795 | 0 | 2021 |  |  | 0.25795 | 0 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | 13 | 4.8008 | 11 | 9.5539 | 0.73491 | Tier 2 & 3 | 1158 | 204 | 0 | 0 | UNSE | Hybrid | Estimating | Top 50 Miles
35224712 | 14 | 3.2869 | 3.2869 | 0 | 2021 |  |  | 3.2869 | 0 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | 13 | 4.8008 | 11 | 9.5539 | 0.73491 | Tier 2 & 3 | 1222 | 16133 | 0 | 0 | UNSE | Hybrid | Estimating | Top 50 Miles
35224713 | 14 | 1.8655 | 1.8655 | 0 | 2021 |  |  | 1.8655 | 0 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | 13 | 4.8008 | 11 | 9.5539 | 0.73491 | Tier 2 & 3 | 160 | 9690 | 0 | 0 | UNSE | Hybrid | Estimating | Top 50 Miles
35062375 | 14 | 1.0902 | 1.0902 | 0 | 2021 |  |  | 1.0902 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 0 | 5756 | 0 | 0 | UNSE | Underground | Estimating | Top 20% MAVF CPZ
35191319 | 13 | 1.1705 | 1.1705 | 0 | 2021 |  |  | 1.1705 | 0 | LAS GALLINAS A 1105 | LAS GALLINAS A 110599904 | 54 | 5.5621 | 215 | 13.5032 | 0.25006 | Tier 3 | 0 | 6180 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35223615 | 13 | 1.6258 | 1.6258 | 0 | 2021 |  |  | 1.6258 | 0 | LAS GALLINAS A 1105 | LAS GALLINAS A 110599904 | 54 | 5.5621 | 215 | 13.5032 | 0.25006 | Tier 3 | 0 | 8584 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35227030 | 13 | 1.7072 | 1.7072 | 0 | 2021 |  |  | 1.7072 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 2233 | 6781 | 0 | 0 | UNSE | Hybrid | Scoping | ECOP
35227031 | 13 | 2.03 | 2.03 | 0 | 2021 |  |  | 2.03 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 2534.4 | 8184 | 0 | 0 | UNSE | Hybrid | Scoping | ECOP
35192282 | 13 | 2.2621 | 2.2621 | 0 | 2021 |  |  | 2.2621 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 0 | 11944 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35226621 | 13 | 2.6562 | 2.6562 | 0 | 2021 |  |  | 2.6562 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | Tier 3 | 2941 | 11084 | 0 | 0 | UNSE | Hybrid | Scoping | ECOP
35192292 | 13 | 0.95114 | 0.95114 | 0 | 2021 |  |  | 0.95114 | 0 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | Tier 3 | 830 | 4192 | 0 | 0 | UNSE | Hybrid | Scoping | ECOP
35225594 | 13 | 0.5286 | 0.5286 | 0 | 2021 |  |  | 0.5286 | 0 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | Tier 3 | 261 | 2530 | 0 | 0 | UNSE | Hybrid | Scoping | ECOP
35174478 | 13 | 1.79 | 1.79 | 0 | 2021 |  |  | 1.79 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 9451.2 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35226857 | 13 | 1.94 | 1.94 | 0 | 2021 |  |  | 1.94 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 10243.2 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35226858 | 14 | 0.74295 | 0.74295 | 0 | 2021 |  |  | 0.74295 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 1900.8 | 0 | 2022 | 0 | ESTS | Remote Grid / Removal | Estimating | ECOP
35226859 | 14 | 0.88 | 0.88 | 0 | 2021 |  |  | 0.88 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 4646.4 | 0 | 0 | 0 | ESTS | Overhead | Estimating | ECOP
35226861 | 14 | 0.75 | 0.75 | 0 | 2021 |  |  | 0.75 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 3960 | 0 | 0 | 0 | ESTS | Overhead | Estimating | ECOP
35226862 | 14 | 0.58 | 0.58 | 0 | 2021 |  |  | 0.58 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 3062.4 | 0 | 0 | 0 | ESTS | Overhead | Estimating | ECOP
35174501 | 13 | 1.683 | 1.683 | 0 | 2021 |  |  | 1.683 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 8886 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35227007 | 13 | 1.1288 | 1.1288 | 0 | 2021 |  |  | 1.1288 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 5960 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35227010 | 13 | 0.15985 | 0.15985 | 0 | 2021 |  |  | 0.15985 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 844 | 0 | 0 | 0 | UNSE | Overhead | Scoping | ECOP
35227013 | 13 | 0.026894 | 0.026894 | 0 | 2021 |  |  | 0.026894 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 142 | 0 | 0 | 0 | UNSE | Overhead | Scoping | ECOP
35227015 | 13 | 0.95758 | 0.95758 | 0 | 2021 |  |  | 0.95758 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 5056 | 0 | 0 | 0 | UNSE | Overhead | Scoping | ECOP
35227018 | 13 | 1.2 | 1.2 | 0 | 2021 |  |  | 1.2 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 6336 | 0 | 0 | 0 | UNSE | Overhead | Scoping | ECOP
35227021 | 13 | 0.21989 | 0.21989 | 0 | 2021 |  |  | 0.21989 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 1161 | 0 | 0 | 0 | UNSE | Overhead | Scoping | ECOP
35227025 | 13 | 0.7536 | 0.7536 | 0 | 2021 |  |  | 0.7536 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 2259 | 1720 | 0 | 0 | UNSE | Hybrid | Scoping | ECOP
35234756 | 13 | 2.782 | 2.782 | 0 | 2021 |  |  | 2.782 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 14689 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35234758 | 13 | 0.58201 | 0.58201 | 0 | 2021 |  |  | 0.58201 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 3073 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35234862 | 13 | 0.079924 | 0.079924 | 0 | 2021 |  |  | 0.079924 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 422 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35234865 | 13 | 0.64754 | 0.64754 | 0 | 2021 |  |  | 0.64754 | 0 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | Tier 3 | 0 | 3419 | 0 | 0 | UNSE | Underground | Scoping | ECOP
35192291 | 13 | 1.0972 | 1.0972 | 0 | 2021 |  |  | 1.0972 | 0 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | 541 | 44.1915 | 811 | 49.924 | 0.092281 | Tier 3 | 521 | 5272 | 0 | 0 | UNSE | Hybrid | Scoping | ECOP
35191937 | 13 | 1.4528 | 1.4528 | 0 | 2021 |  |  | 1.4528 | 0 | PUEBLO 2102 | PUEBLO 2102792 | 180 | 19.3407 | 951 | 13.2101 | 0.073389 | Tier 3 | 7671 | 0 | 0 | 0 | UNSE | Overhead | Scoping | ECOP
35227032 | 13 | 0.575 | 0.575 | 0 | 2021 |  |  | 0.575 | 0 | PUEBLO 2102 | PUEBLO 2102792 | 180 | 19.3407 | 951 | 13.2101 | 0.073389 | Tier 3 | 3036 | 0 | 0 | 0 | UNSE | Overhead | Scoping | ECOP
35227033 | 13 | 1.31 | 1.31 | 0 | 2021 |  |  | 1.31 | 0 | PUEBLO 2102 | PUEBLO 2102792 | 180 | 19.3407 | 951 | 13.2101 | 0.073389 | Tier 3 | 0 | 0 | 0 | 6917 | UNSE | Remote Grid / Removal | Scoping | ECOP
35219093 | 13 | 1.14 | 1.14 | 0 | 2021 |  |  | 1.14 | 0 | TIDEWATER 2106 | TIDEWATER 210614072 | 30 | 3.6652 | 18 | 19.5994 | 0.65331 | Tier 2 | 0 | 6019.2 | 0 | 0 | ESTS | Underground | Scoping | Top 50 Miles
35231543 | 13 | 1.3 | 1.3 | 0 | 2021 |  |  | 1.3 | 0 | TIDEWATER 2106 | TIDEWATER 210614072 | 30 | 3.6652 | 18 | 19.5994 | 0.65331 | Tier 2 | 0 | 6864 | 0 | 0 | UNSE | Underground | Scoping | Top 50 Miles
35217273 | 13 | 1.1055 | 1.1055 | 0 | 2021 |  |  | 1.1055 | 0 | UPPER LAKE 1101 | UPPER LAKE 1101CB | 3 | 1.1133 | 6 | 3.7676 | 1.2559 | Tier 2 | 240 | 0 | 5596.8 | 0 | UNSE | Remote Grid / Removal | Scoping | Top 50 Miles
35217272 | 13 | 0.34053 | 0.34053 | 0 | 2021 |  |  | 0.34053 | 0 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | Tier 3 | 94 | 1704 | 0 | 0 | UNSE | Hybrid | Scoping | Top 50 Miles
35226628 | 13 | 0.81913 | 0.81913 | 0 | 2021 |  |  | 0.81913 | 0 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | Tier 3 | 0 | 4325 | 0 | 0 | UNSE | Underground | Scoping | Top 50 Miles
35226629 | 13 | 4.6972 | 4.6972 | 0 | 2021 |  |  | 4.6972 | 0 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | Tier 3 | 0 | 24801 | 0 | 0 | UNSE | Underground | Scoping | Top 50 Miles
35217269 | 13 | 0.52083 | 0.52083 | 0 | 2021 |  |  | 0.52083 | 0 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | Tier 2 | 630 | 2120 | 0 | 0 | UNSE | Hybrid | Scoping | Top 50 Miles
35226819 | 13 | 1.321 | 1.321 | 0 | 2021 |  |  | 1.321 | 0 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | Tier 2 | 6975 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 50 Miles
35227160 | 13 | 2.843 | 2.843 | 0 | 2021 |  |  | 2.843 | 0 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | Tier 2 | 176 | 14835 | 0 | 0 | UNSE | Hybrid | Scoping | Top 50 Miles
35227161 | 13 | 0.73068 | 0.73068 | 0 | 2021 |  |  | 0.73068 | 0 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | Tier 2 | 3858 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 50 Miles
35227162 | 13 | 0.4178 | 0.4178 | 0 | 2021 |  |  | 0.4178 | 0 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | Tier 2 | 0 | 2206 | 0 | 0 | UNSE | Underground | Scoping | Top 50 Miles
35227163 | 13 | 0.41117 | 0.41117 | 0 | 2021 |  |  | 0.41117 | 0 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | Tier 2 | 2171 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 50 Miles
35227164 | 13 | 0.5589 | 0.5589 | 0 | 2021 |  |  | 0.5589 | 0 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | Tier 2 | 2951 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 50 Miles
35217270 | 14 | 0.57614 | 0.57614 | 0 | 2021 |  |  | 0.57614 | 0 | KONOCTI 1102 | KONOCTI 1102965078 | 59 | 6.2704 | 9 | 51.7008 | 0.87629 | Tier 3 | 3042 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 50 Miles
35217271 | 13 | 2.8496 | 2.8496 | 0 | 2021 |  |  | 2.8496 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 0 | 15046 | 0 | 0 | UNSE | Underground | Scoping | Top 50 Miles
35227864 | 13 | 1.8392 | 1.8392 | 0 | 2021 |  |  | 1.8392 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 0 | 9711 | 0 | 0 | UNSE | Underground | Scoping | Top 50 Miles
35220895 | 13 | 2.1489 | 2.1489 | 0 | 2021 |  |  | 2.1489 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 1137 | 10209 | 0 | 0 | UNSE | Hybrid | Scoping | Top 50 Miles
35228186 | 13 | 1.4847 | 1.4847 | 0 | 2021 |  |  | 1.4847 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 0 | 7839 | 0 | 0 | UNSE | Underground | Scoping | Top 50 Miles
35220896 | 13 | 0.2803 | 0.2803 | 0 | 2021 |  |  | 0.2803 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 0 | 1480 | 0 | 0 | UNSE | Underground | Scoping | Top 50 Miles
35227165 | 13 | 1.0112 | 1.0112 | 0 | 2021 |  |  | 1.0112 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 0 | 5339 | 0 | 0 | UNSE | Underground | Scoping | Top 50 Miles
35227167 | 13 | 1.7975 | 1.7975 | 0 | 2021 |  |  | 1.7975 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 0 | 9491 | 0 | 0 | UNSE | Underground | Scoping | Top 50 Miles
35227168 | 13 | 1.5741 | 1.5741 | 0 | 2021 |  |  | 1.5741 | 0 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 |  | 0 | 8311 | 0 | 0 | UNSE | Underground | Scoping | Top 50 Miles
35062374 | 13 | 1.5352 | 1.5352 | 0 | 2021 |  |  | 1.5352 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 0 | 8106 | 0 | 0 | UNSE | Underground | Scoping | Top 20% MAVF CPZ
35231608 | 14 | 0.16212 | 0.16212 | 0 | 2021 |  |  | 0.16212 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 856 | 0 | 0 | 0 | ESTS | Overhead | Estimating | Top 20% MAVF CPZ
35226849 | 13 | 1.7833 | 1.7833 | 0 | 2021 |  |  | 1.7833 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | Tier 3 | 0 | 9416 | 0 | 0 | UNSE | Underground | Scoping | Top 20% MAVF CPZ
35062376 | 13 | 4.3231 | 4.3231 | 0 | 2021 |  |  | 4.3231 | 0 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | Tier 3 | 0 | 22826 | 0 | 0 | UNSE | Underground | Scoping | Top 20% MAVF CPZ
35219096 | 13 | 1.67 | 1.67 | 0 | 2021 |  |  | 1.67 | 0 | KIRKER 2104 | KIRKER 2104442850 | 30 | 5.7542 | 21 | 18.4361 | 0.61454 | Tier 2 | 0 | 8817.6 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35227655 | 13 | 3.77 | 3.77 | 0 | 2021 |  |  | 3.77 | 0 | KIRKER 2104 | KIRKER 2104442850 | 30 | 5.7542 | 21 | 18.4361 | 0.61454 | Tier 2 | 19905.6 | 0 | 0 | 0 | UNSE | Overhead | Scoping | Top 250 Miles
35226700 | 13 | 0.45758 | 0.45758 | 0 | 2021 |  |  | 0.45758 | 0 | WYANDOTTE 1109 | WYANDOTTE 110932586 | 15 | 1.3417 | 29 | 7.9481 | 0.52987 | Tier 2 | 0 | 2416 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35219281 | 13 | 2.5 | 2.5 | 0 | 2021 |  |  | 2.5 | 0 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | 58 | 5.7104 | 45 | 25.2473 | 0.4353 |  | 0 | 13200 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35232650 | 13 | 1.71 | 1.71 | 0 | 2021 |  |  | 1.71 | 0 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | 58 | 5.7104 | 45 | 25.2473 | 0.4353 |  | 0 | 9029 | 0 | 0 | UNSE | Underground | Scoping | Top 250 Miles
35240160 | 2 | 28.09 | 28.09 | 0 |  |  |  | 28.09 | 0 | COARSEGOLD 2104 | COARSEGOLD 21045310 | 299 | 28.0892 | 61 | 117.8076 | 0.39401 |  | 148315.2 | 0 | 0 | 0 | UNSE | Overhead | Scoping | CWSP 2022-2023
35240162 | 2 | 0 | 0 | 0 |  |  |  | 0 | 0 | COARSEGOLD 2104 | COARSEGOLD 21045310 | 299 | 28.0892 | 61 | 117.8076 | 0.39401 |  | 0 | 0 | 0 | 0 | UNSE | TBD | Scoping | CWSP 2022-2023
35240163 | 2 | 0 | 0 | 0 |  |  |  | 0 | 0 | COARSEGOLD 2104 | COARSEGOLD 21045310 | 299 | 28.0892 | 61 | 117.8076 | 0.39401 |  | 0 | 0 | 0 | 0 | UNSE | TBD | Scoping | CWSP 2022-2023
35240164 | 2 | 2.03 | 2.03 | 0 |  |  |  | 2.03 | 0 | COARSEGOLD 2104 | COARSEGOLD 2104570682 | 26 | 2.0288 | 78 | 9.6995 | 0.37306 |  | 10718.4 | 0 | 0 | 0 | UNSE | Overhead | Scoping | CWSP 2022-2023
35240165 | 2 | 10.68 | 10.68 | 0 |  |  |  | 10.68 | 0 | COARSEGOLD 2104 | COARSEGOLD 21046210 | 49 | 10.6757 | 132 | 14.9278 | 0.30465 |  | 56390.4 | 0 | 0 | 0 | UNSE | Overhead | Scoping | CWSP 2022-2023
35240166 | 2 | 9.21 | 9.21 | 0 |  |  |  | 9.21 | 0 | VOLTA 1101 | VOLTA 1101CB | 80 | 9.2089 | 76 | 30.036 | 0.37545 |  | 48628.8 | 0 | 0 | 0 | UNSE | Overhead | Scoping | CWSP 2022-2023
35240167 | 2 | 0 | 0 | 0 |  |  |  | 0 | 0 | VOLTA 1101 | VOLTA 1101CB | 80 | 9.2089 | 76 | 30.036 | 0.37545 |  | 0 | 0 | 0 | 0 | UNSE | TBD | Scoping | CWSP 2022-2023
35240168 | 2 | 9.62 | 9.62 | 0 |  |  |  | 9.62 | 0 | VOLTA 1101 | VOLTA 110153118 | 47 | 9.6273 | 157 | 13.1375 | 0.27952 |  | 50793.6 | 0 | 0 | 0 | UNSE | Overhead | Scoping | CWSP 2022-2023
35240169 | 2 | 23.11 | 23.11 | 0 |  |  |  | 23.11 | 0 | VOLTA 1101 | VOLTA 11011568 | 136 | 23.1053 | 85 | 49.2203 | 0.36191 |  | 122020.8 | 0 | 0 | 0 | UNSE | Overhead | Scoping | CWSP 2022-2023
35240170 | 2 | 0 | 0 | 0 |  |  |  | 0 | 0 | VOLTA 1101 | VOLTA 11011568 | 136 | 23.1053 | 85 | 49.2203 | 0.36191 |  | 0 | 0 | 0 | 0 | UNSE | TBD | Scoping | CWSP 2022-2023
35240171 | 2 | 0 | 0 | 0 |  |  |  | 0 | 0 | VOLTA 1101 | VOLTA 11011568 | 136 | 23.1053 | 85 | 49.2203 | 0.36191 |  | 0 | 0 | 0 | 0 | UNSE | TBD | Scoping | CWSP 2022-2023
35240173 | 2 | 6.4 | 6.4 | 0 |  |  |  | 6.4 | 0 | PUTAH CREEK 1102 | PUTAH CREEK 11028352 | 133 | 6.4005 | 171 | 36.3202 | 0.27308 |  | 33792 | 0 | 0 | 0 | UNSE | Overhead | Scoping | CWSP 2022-2023
35240174 | 2 | 0 | 0 | 0 |  |  |  | 0 | 0 | PUTAH CREEK 1102 | PUTAH CREEK 11028352 | 133 | 6.4005 | 171 | 36.3202 | 0.27308 |  | 0 | 0 | 0 | 0 | UNSE | TBD | Scoping | CWSP 2022-2023
35240175 | 2 | 11.42 | 11.42 | 0 |  |  |  | 11.42 | 0 | PUTAH CREEK 1102 | PUTAH CREEK 110267858 | 107 | 11.4216 | 92 | 38.201 | 0.35702 |  | 60297.6 | 0 | 0 | 0 | UNSE | Overhead | Scoping | CWSP 2022-2023
35240176 | 2 | 6 | 6 | 0 |  |  |  | 6 | 0 | PUTAH CREEK 1102 | PUTAH CREEK 110264044 | 46 | 5.9969 | 529 | 6.8236 | 0.14834 |  | 31680 | 0 | 0 | 0 | UNSE | Overhead | Scoping | CWSP 2022-2023
35240177 | 2 | 0 | 0 | 0 |  |  |  | 0 | 0 | PUTAH CREEK 1102 | PUTAH CREEK 110264044 | 46 | 5.9969 | 529 | 6.8236 | 0.14834 |  | 0 | 0 | 0 | 0 | UNSE | TBD | Scoping | CWSP 2022-2023
35240178 | 2 | 5.34 | 5.34 | 0 |  |  |  | 5.34 | 0 | PUTAH CREEK 1102 | PUTAH CREEK 1102710384 | 84 | 5.3351 | 418 | 14.6739 | 0.17469 |  | 28195.2 | 0 | 0 | 0 | UNSE | Overhead | Scoping | CWSP 2022-2023
35240179 | 2 | 0.38 | 0.38 | 0 |  |  |  | 0.38 | 0 | SANTA YNEZ 1104 | SANTA YNEZ 1104CB | 105 | 0.035126 | 137 | 31.6947 | 0.30185 |  | 2006.4 | 0 | 0 | 0 | UNSE | Overhead | Scoping | CWSP 2022-2023
35240220 | 2 | 15.65 | 15.65 | 0 |  |  |  | 15.65 | 0 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y04 | 238 | 15.6586 | 108 | 77.261 | 0.32463 |  | 82632 | 0 | 0 | 0 | UNSE | Overhead | Scoping | CWSP 2022-2023
35240221 | 2 | 0 | 0 | 0 |  |  |  | 0 | 0 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y04 | 238 | 15.6586 | 108 | 77.261 | 0.32463 |  | 0 | 0 | 0 | 0 | UNSE | TBD | Scoping | CWSP 2022-2023
35240222 | 2 | 16.94 | 16.94 | 0 |  |  |  | 16.94 | 0 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y66 | 138 | 16.9474 | 153 | 39.0253 | 0.28279 |  | 89443.2 | 0 | 0 | 0 | UNSE | Overhead | Scoping | CWSP 2022-2023
35240223 | 2 | 0 | 0 | 0 |  |  |  | 0 | 0 | SANTA YNEZ 1104 | SANTA YNEZ 1104Y66 | 138 | 16.9474 | 153 | 39.0253 | 0.28279 |  | 0 | 0 | 0 | 0 | UNSE | TBD | Scoping | CWSP 2022-2023
35240224 | 2 | 11.96 | 11.96 | 0 |  |  |  | 11.96 | 0 | SANTA YNEZ 1104 | SANTA YNEZ 110477098 | 112 | 11.9643 | 308 | 23.5673 | 0.21042 |  | 63148.8 | 0 | 0 | 0 | UNSE | Overhead | Scoping | CWSP 2022-2023
Totals |  | 830.2725 | [10 empty] | 9077.6335 |  | 25681.378 |  |  | 2622250.8 | 1287579 | 216651.2 | 255791

## HFTD CPZ (hidden)
PZ_idx | circuit_protection_zone_id | feeder_id | feeder_name | Miles | pixel_count | mean_mavf_core_risk | Total Risk Value | mean_mavf_core_risk_rank | Cumulative Miles | Decreasing Risk | Project List | CPZs Approved | Active Job | Active Miles | Approved CPZ Overwrite | Approved CPZ
10544 | OREGON TRAIL 1103CUS391 | 103521103 | OREGON TRAIL 1103 | 0.022596 | 1 | 3.1639 | 3.1639 | 1 | 0.022596 | 24761.6364 | #N/A | 24761.6364 | FALSE | 0 | TRUE | TRUE
11024 | CALPINE 1144276-G | 48011144 | CALPINE 1144 | 0.014759 | 1 | 1.8786 | 1.8786 | 2 | 0.037356 | 24759.7577 | #N/A | 24759.7577 | FALSE | 0 | TRUE | TRUE
9665 | MARIPOSA 210190130 | 254452101 | MARIPOSA 2101 | 0.09394 | 1 | 1.6924 | 1.6924 | 3 | 0.1313 | 24758.0654 | #N/A | 24758.0654 | FALSE | 0 | TRUE | TRUE
9783 | SHEPHERD 2111688294 | 252062111 | SHEPHERD 2111 | 0.01514 | 1 | 1.4425 | 1.4425 | 4 | 0.14644 | 24756.6229 | #N/A | 24756.6229 | FALSE | 0 | TRUE | TRUE
10354 | MIDDLETOWN 1103CB | 43141103 | MIDDLETOWN 1103 | 0.052975 | 4 | 1.3006 | 5.2026 | 5 | 0.19941 | 24751.4203 | #N/A | 24751.4203 | FALSE | 0 | TRUE | TRUE
10600 | UPPER LAKE 1101CB | 42871101 | UPPER LAKE 1101 | 1.1133 | 3 | 1.2559 | 3.7676 | 6 | 1.3127 | 24747.6528 | 24747.6528 | #N/A | TRUE | 1.1055 | TRUE | TRUE
8894 | KESWICK 11011586 | 103451101 | KESWICK 1101 | 7.4478 | 39 | 1.2524 | 48.8434 | 7 | 8.7605 | 24698.8094 | 24698.8094 | #N/A | TRUE | 9.1078 | TRUE | TRUE
6776 | MIDDLETOWN 1102302610 | 43141102 | MIDDLETOWN 1102 | 4.7058 | 53 | 0.91632 | 48.565 | 8 | 13.4663 | 24650.2444 | 24650.2444 | #N/A | TRUE | 6.8034 | TRUE | TRUE
2373 | KONOCTI 1102965078 | 43311102 | KONOCTI 1102 | 6.2704 | 59 | 0.87629 | 51.7008 | 9 | 19.7367 | 24598.5436 | 24598.5436 | #N/A | TRUE | 3.1468 | TRUE | TRUE
5527 | MARIPOSA 2102241564 | 254452102 | MARIPOSA 2102 | 0.71281 | 14 | 0.77248 | 10.8148 | 10 | 20.4495 | 24587.7288 | 24587.7288 | #N/A | TRUE | 0.71 | TRUE | TRUE
7968 | BUCKS CREEK 1101CB | 102211101 | BUCKS CREEK 1101 | 4.8008 | 13 | 0.73491 | 9.5539 | 11 | 25.2503 | 24578.1749 | 24578.1749 | #N/A | TRUE | 5.4104 | TRUE | TRUE
10918 | DEL MAR 2109378446 | 152582109 | DEL MAR 2109 | 0.098166 | 3 | 0.73151 | 2.1945 | 12 | 25.3484 | 24575.9804 | #N/A | 24575.9804 | FALSE | 0 | TRUE | TRUE
6966 | MIDDLETOWN 1102CB | 43141102 | MIDDLETOWN 1102 | 0.46739 | 12 | 0.72481 | 8.6977 | 13 | 25.8158 | 24567.2827 | #N/A | 24567.2827 | FALSE | 0 | TRUE | TRUE
3511 | MIDDLETOWN 1103830 | 43141103 | MIDDLETOWN 1103 | 27.7328 | 212 | 0.71618 | 151.8291 | 14 | 53.5487 | 24415.4536 | 24415.4536 | #N/A | TRUE | 23.9445 | TRUE | TRUE
9537 | POSO MOUNTAIN 2104CB | 253642104 | POSO MOUNTAIN 2104 | 5.3534 | 38 | 0.70423 | 26.7607 | 15 | 58.9021 | 24388.6929 | #N/A | 24388.6929 | FALSE | 0 | TRUE | TRUE
10827 | INDIAN FLAT 11044440 | 252691104 | INDIAN FLAT 1104 | 0.23386 | 4 | 0.68656 | 2.7463 | 16 | 59.136 | 24385.9466 | #N/A | 24385.9466 | FALSE | 0 | TRUE | TRUE
10242 | ELK CREEK 1101CB | 102781101 | ELK CREEK 1101 | 0.084235 | 1 | 0.67079 | 0.67079 | 17 | 59.2202 | 24385.2758 | #N/A | 24385.2758 | FALSE | 0 | TRUE | TRUE
5791 | TIDEWATER 210614072 | 14652106 | TIDEWATER 2106 | 3.6652 | 30 | 0.65331 | 19.5994 | 18 | 62.8854 | 24365.6765 | 24365.6765 | #N/A | TRUE | 3.64 | TRUE | TRUE
10735 | HARTLEY 1101980662 | 43211101 | HARTLEY 1101 | 0.22763 | 3 | 0.64187 | 1.9256 | 19 | 63.113 | 24363.7509 | #N/A | 24363.7509 | FALSE | 0 | TRUE | TRUE
10532 | VACA DIXON 1101126774 | 63591101 | VACA DIXON 1101 | 0.78766 | 11 | 0.62029 | 6.8232 | 20 | 63.9007 | 24356.9277 | 24356.9277 | #N/A | TRUE | 0.39811 | TRUE | TRUE
10277 | KIRKER 2104442850 | 14452104 | KIRKER 2104 | 5.7542 | 30 | 0.61454 | 18.4361 | 21 | 69.6549 | 24338.4916 | 24338.4916 | #N/A | TRUE | 5.44 | TRUE | TRUE
8742 | COARSEGOLD 2104CB | 254432104 | COARSEGOLD 2104 | 2.4277 | 27 | 0.59573 | 16.0848 | 22 | 72.0826 | 24322.4068 | 24322.4068 | #N/A | TRUE | 8.2815 | TRUE | TRUE
8905 | MIDDLETOWN 1101118494 | 43141101 | MIDDLETOWN 1101 | 1.0659 | 12 | 0.58092 | 6.971 | 23 | 73.1484 | 24315.4357 | 24315.4357 | #N/A | TRUE | 1.33 | TRUE | TRUE
10515 | STAFFORD 1102784704 | 43201102 | STAFFORD 1102 | 0.027274 | 1 | 0.564 | 0.564 | 24 | 73.1757 | 24314.8717 | #N/A | 24314.8717 | FALSE | 0 | TRUE | TRUE
10181 | PEABODY 2108113684 | 63642108 | PEABODY 2108 | 0.36709 | 4 | 0.55276 | 2.211 | 25 | 73.5428 | 24312.6607 | #N/A | 24312.6607 | FALSE | 0 | TRUE | TRUE
7688 | PEABODY 2106250154 | 63642106 | PEABODY 2106 | 0.28499 | 4 | 0.55243 | 2.2097 | 26 | 73.8278 | 24310.451 | #N/A | 24310.451 | FALSE | 0 | TRUE | TRUE
7743 | HIGHLANDS 1102628 | 43361102 | HIGHLANDS 1102 | 14.2224 | 51 | 0.5487 | 27.9838 | 27 | 88.0502 | 24282.4672 | 24282.4672 | #N/A | TRUE | 23.057 | TRUE | TRUE
6480 | TASSAJARA 21123202 | 14662112 | TASSAJARA 2112 | 0.39174 | 9 | 0.53731 | 4.8358 | 28 | 88.442 | 24277.6315 | #N/A | 24277.6315 | FALSE | 0 | TRUE | TRUE
10043 | WYANDOTTE 110932586 | 102911109 | WYANDOTTE 1109 | 1.3417 | 15 | 0.52987 | 7.9481 | 29 | 89.7837 | 24269.6834 | 24269.6834 | #N/A | TRUE | 1.3019 | TRUE | TRUE
10052 | POSO MOUNTAIN 2103CB | 253642103 | POSO MOUNTAIN 2103 | 2.3287 | 10 | 0.51619 | 5.1619 | 30 | 92.1124 | 24264.5215 | #N/A | 24264.5215 | FALSE | 0 | TRUE | TRUE
10924 | CALPINE 1146200-G | 48011146 | CALPINE 1146 | 0.0085246 | 1 | 0.50979 | 0.50979 | 31 | 92.121 | 24264.0117 | #N/A | 24264.0117 | FALSE | 0 | TRUE | TRUE
11090 | CALPINE 1146394G | 48011146 | CALPINE 1146 | 0.011292 | 1 | 0.50979 | 0.50979 | 32 | 92.1323 | 24263.5019 | #N/A | 24263.5019 | FALSE | 0 | TRUE | TRUE
4828 | CRESTA 1101546650 | 102251101 | CRESTA 1101 | 0.89694 | 6 | 0.50291 | 3.0174 | 33 | 93.0292 | 24260.4844 | #N/A | 24260.4844 | FALSE | 0 | TRUE | TRUE
9923 | CLOVERDALE 110247214 | 42821102 | CLOVERDALE 1102 | 0.027329 | 1 | 0.48427 | 0.48427 | 34 | 93.0565 | 24260.0002 | #N/A | 24260.0002 | FALSE | 0 | TRUE | TRUE
8034 | MARIPOSA 2102CB | 254452102 | MARIPOSA 2102 | 5.2539 | 31 | 0.47165 | 14.6212 | 35 | 98.3104 | 24245.379 | 24245.379 | #N/A | TRUE | 2.85 | TRUE | TRUE
7873 | MARIPOSA 210197142 | 254452101 | MARIPOSA 2101 | 4.6029 | 40 | 0.47122 | 18.8487 | 36 | 102.9133 | 24226.5303 | 24226.5303 | #N/A | TRUE | 4.5636 | TRUE | TRUE
4526 | VACA DIXON 110540092 | 63591105 | VACA DIXON 1105 | 23.1653 | 464 | 0.46772 | 217.022 | 37 | 126.0786 | 24009.5083 | 24009.5083 | #N/A | TRUE | 30.58 | TRUE | TRUE
2215 | MIDDLETOWN 1101481876 | 43141101 | MIDDLETOWN 1101 | 0.8534 | 14 | 0.46769 | 6.5476 | 38 | 126.932 | 24002.9607 | 24002.9607 | #N/A | TRUE | 0.85436 | TRUE | TRUE
9655 | VOLTA 110149742 | 102541101 | VOLTA 1101 | 3.4766 | 28 | 0.46433 | 13.0013 | 39 | 130.4086 | 23989.9594 | 23989.9594 | #N/A | TRUE | 3.461 | TRUE | TRUE
10699 | SUNOL 110148180 | 14241101 | SUNOL 1101 | 0.013145 | 2 | 0.46103 | 0.92206 | 40 | 130.4218 | 23989.0374 | #N/A | 23989.0374 | FALSE | 0 | TRUE | TRUE
7414 | PUTAH CREEK 110246012 | 63681102 | PUTAH CREEK 1102 | 0.63713 | 38 | 0.45557 | 17.3115 | 41 | 131.0589 | 23971.7259 | 23971.7259 | #N/A | TRUE | 0.52 | TRUE | TRUE
4076 | VACAVILLE 11046542 | 63601104 | VACAVILLE 1104 | 14.6602 | 140 | 0.44642 | 62.4985 | 42 | 145.719 | 23909.2273 | 23909.2273 | #N/A | TRUE | 14.73 | TRUE | TRUE
7056 | POTTER VALLEY P H 110564118 | 42281105 | POTTER VALLEY P H 1105 | 1.6451 | 101 | 0.44262 | 44.7046 | 43 | 147.3641 | 23864.5228 | 23864.5228 | #N/A | TRUE | 1.8343 | TRUE | TRUE
10934 | POINT MORETTI 1101CB | 82931101 | POINT MORETTI 1101 | 0.012787 | 1 | 0.44218 | 0.44218 | 44 | 147.3769 | 23864.0806 | #N/A | 23864.0806 | FALSE | 0 | TRUE | TRUE
5032 | MOUNTAIN QUARRIES 21016953 | 152282101 | MOUNTAIN QUARRIES 2101 | 5.7104 | 58 | 0.4353 | 25.2473 | 45 | 153.0873 | 23838.8333 | 23838.8333 | #N/A | TRUE | 5.95 | TRUE | TRUE
9729 | BRENTWOOD 210596324 | 14592105 | BRENTWOOD 2105 | 0.48214 | 6 | 0.4317 | 2.5902 | 46 | 153.5694 | 23836.2431 | #N/A | 23836.2431 | FALSE | 0 | TRUE | TRUE
6662 | NORTH DUBLIN 2101CB | 14052101 | NORTH DUBLIN 2101 | 1.7629 | 23 | 0.42859 | 9.8576 | 47 | 155.3324 | 23826.3855 | #N/A | 23826.3855 | FALSE | 0 | TRUE | TRUE
1690 | DESCHUTES 11049718 | 103351104 | DESCHUTES 1104 | 18.6049 | 357 | 0.42526 | 151.8163 | 48 | 173.9373 | 23674.5692 | 23674.5692 | #N/A | TRUE | 18.3011 | TRUE | TRUE
193 | OREGON TRAIL 110335002 | 103521103 | OREGON TRAIL 1103 | 57.1429 | 641 | 0.42185 | 270.4028 | 49 | 231.0802 | 23404.1664 | 23404.1664 | #N/A | TRUE | 62.2442 | TRUE | TRUE
7274 | MARIPOSA 2102440236 | 254452102 | MARIPOSA 2102 | 4.2727 | 38 | 0.4205 | 15.979 | 50 | 235.3529 | 23388.1874 | 23388.1874 | #N/A | TRUE | 8.59 | TRUE | TRUE
10024 | CLEAR LAKE 1101881362 | 42141101 | CLEAR LAKE 1101 | 0.29834 | 10 | 0.41959 | 4.1959 | 51 | 235.6513 | 23383.9915 | #N/A | 23383.9915 | FALSE | 0 | TRUE | TRUE
7141 | WILDWOOD 11011454 | 103611101 | WILDWOOD 1101 | 7.8323 | 31 | 0.41883 | 12.9837 | 52 | 243.4835 | 23371.0078 | 23371.0078 | #N/A | TRUE | 7.87 | TRUE | TRUE
7033 | VACA DIXON 1105965390 | 63591105 | VACA DIXON 1105 | 0.75147 | 21 | 0.41415 | 8.6971 | 53 | 244.235 | 23362.3107 | 23362.3107 | #N/A | TRUE | 0.75 | TRUE | TRUE
9936 | OLETA 1101754718 | 163541101 | OLETA 1101 | 2.8841 | 29 | 0.40712 | 11.8066 | 54 | 247.1191 | 23350.5042 | 23350.5042 | #N/A | TRUE | 3.01 | TRUE | TRUE
10113 | CALISTOGA 1101CB | 42711101 | CALISTOGA 1101 | 0.13777 | 9 | 0.40561 | 3.6505 | 55 | 247.2569 | 23346.8537 | #N/A | 23346.8537 | FALSE | 0 | TRUE | TRUE
9252 | STANISLAUS 1701CB | 162821701 | STANISLAUS 1701 | 6.8569 | 54 | 0.40353 | 21.7909 | 56 | 254.1138 | 23325.0628 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9014 | MARIPOSA 2101CB | 254452101 | MARIPOSA 2101 | 2.5043 | 34 | 0.39837 | 13.5444 | 57 | 256.6181 | 23311.5183 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4909 | HARTLEY 1101698 | 43211101 | HARTLEY 1101 | 6.8807 | 97 | 0.39723 | 38.5312 | 58 | 263.4988 | 23272.9871 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9239 | BANGOR 1101979830 | 103191101 | BANGOR 1101 | 0.42309 | 7 | 0.3972 | 2.7804 | 59 | 263.9219 | 23270.2067 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4242 | POTTER VALLEY P H 110495878 | 42281104 | POTTER VALLEY P H 1104 | 6.126 | 191 | 0.3965 | 75.7306 | 60 | 270.0479 | 23194.4761 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2058 | COARSEGOLD 21045310 | 254432104 | COARSEGOLD 2104 | 28.0892 | 299 | 0.39401 | 117.8076 | 61 | 298.1371 | 23076.6685 | 23076.6685 | #N/A | TRUE | 28.09 | FALSE | TRUE
8298 | STAFFORD 1102361952 | 43201102 | STAFFORD 1102 | 1.3652 | 9 | 0.39288 | 3.536 | 62 | 299.5023 | 23073.1326 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1488 | AUBERRY 1101CB | 254151101 | AUBERRY 1101 | 18.1661 | 204 | 0.39206 | 79.9801 | 63 | 317.6684 | 22993.1524 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3596 | VACAVILLE 11088762 | 63601108 | VACAVILLE 1108 | 13.8344 | 147 | 0.39138 | 57.5327 | 64 | 331.5028 | 22935.6197 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6014 | OREGON TRAIL 11041634 | 103521104 | OREGON TRAIL 1104 | 18.0925 | 192 | 0.39094 | 75.0607 | 65 | 349.5953 | 22860.5591 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6392 | COARSEGOLD 210410335 | 254432104 | COARSEGOLD 2104 | 5.8229 | 69 | 0.39082 | 26.9663 | 66 | 355.4182 | 22833.5927 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7352 | JAMESON 1102865502 | 63801102 | JAMESON 1102 | 0.40084 | 27 | 0.38957 | 10.5185 | 67 | 355.819 | 22823.0743 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3943 | MOUNTAIN QUARRIES 2101CB | 152282101 | MOUNTAIN QUARRIES 2101 | 24.9941 | 262 | 0.38665 | 101.3032 | 68 | 380.8131 | 22721.7711 | 22721.7711 | #N/A | TRUE | 0.43087 | TRUE | TRUE
2633 | PASO ROBLES 1103N54 | 182611103 | PASO ROBLES 1103 | 20.0132 | 221 | 0.38568 | 85.2354 | 69 | 400.8263 | 22636.5357 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6808 | PHILO 110137222 | 42601101 | PHILO 1101 | 25.4153 | 152 | 0.3839 | 58.3523 | 70 | 426.2416 | 22578.1834 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8006 | RISING RIVER 11011532 | 103551101 | RISING RIVER 1101 | 3.8118 | 27 | 0.38077 | 10.2807 | 71 | 430.0534 | 22567.9027 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10120 | DEL MAR 210975802 | 152582109 | DEL MAR 2109 | 0.35808 | 6 | 0.37901 | 2.2741 | 72 | 430.4114 | 22565.6287 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8754 | NOTRE DAME 11042408 | 102041104 | NOTRE DAME 1104 | 11.5235 | 76 | 0.37815 | 28.7393 | 73 | 441.9349 | 22536.8893 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5603 | HIGHLANDS 1102623120 | 43361102 | HIGHLANDS 1102 | 6.5476 | 67 | 0.3774 | 25.2855 | 74 | 448.4825 | 22511.6038 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2079 | POTTER VALLEY P H 11051904 | 42281105 | POTTER VALLEY P H 1105 | 31.8476 | 332 | 0.37685 | 125.1141 | 75 | 480.3302 | 22386.4897 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8836 | VOLTA 1101CB | 102541101 | VOLTA 1101 | 9.2089 | 80 | 0.37545 | 30.036 | 76 | 489.5391 | 22356.4537 | 22356.4537 | #N/A | TRUE | 9.21 | FALSE | TRUE
10966 | HICKS 2101984788 | 83432101 | HICKS 2101 | 0.0031475 | 1 | 0.37348 | 0.37348 | 77 | 489.5422 | 22356.0802 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6191 | COARSEGOLD 2104570682 | 254432104 | COARSEGOLD 2104 | 2.0288 | 26 | 0.37306 | 9.6995 | 78 | 491.571 | 22346.3807 | 22346.3807 | #N/A | TRUE | 2.03 | FALSE | TRUE
8841 | NORTH DUBLIN 210311101 | 14052103 | NORTH DUBLIN 2103 | 3.6863 | 37 | 0.36793 | 13.6135 | 79 | 495.2573 | 22332.7673 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7776 | NORTH DUBLIN 21039473 | 14052103 | NORTH DUBLIN 2103 | 2.4179 | 27 | 0.36547 | 9.8678 | 80 | 497.6753 | 22322.8995 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9266 | WILLOW PASS 2107445650 | 13912107 | WILLOW PASS 2107 | 0.66278 | 5 | 0.36477 | 1.8239 | 81 | 498.3381 | 22321.0756 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2272 | MIDDLETOWN 1102414 | 43141102 | MIDDLETOWN 1102 | 5.9319 | 114 | 0.36434 | 41.5353 | 82 | 504.27 | 22279.5404 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3625 | CAYETANO 2109884904 | 14422109 | CAYETANO 2109 | 11.6368 | 77 | 0.36326 | 27.9711 | 83 | 515.9068 | 22251.5693 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10903 | PEABODY 2106592742 | 63642106 | PEABODY 2106 | 0.3398 | 5 | 0.36227 | 1.8113 | 84 | 516.2466 | 22249.7579 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5260 | VOLTA 11011568 | 102541101 | VOLTA 1101 | 23.1053 | 136 | 0.36191 | 49.2203 | 85 | 539.352 | 22200.5377 | 22200.5377 | #N/A | TRUE | 23.11 | FALSE | TRUE
4693 | MIDDLETOWN 1101CB | 43141101 | MIDDLETOWN 1101 | 4.731 | 146 | 0.36174 | 52.8144 | 86 | 544.083 | 22147.7233 | 22147.7233 | #N/A | TRUE | 0.53485 | TRUE | TRUE
10547 | PASO ROBLES 1103N02 | 182611103 | PASO ROBLES 1103 | 0.044086 | 1 | 0.36094 | 0.36094 | 87 | 544.127 | 22147.3624 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2088 | COARSEGOLD 21035020 | 254432103 | COARSEGOLD 2103 | 16.1994 | 159 | 0.36009 | 57.2543 | 88 | 560.3265 | 22090.108 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7913 | JESSUP 11023105 | 103441102 | JESSUP 1102 | 6.0031 | 65 | 0.35978 | 23.3856 | 89 | 566.3296 | 22066.7225 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10257 | CAYETANO 2111389190 | 14422111 | CAYETANO 2111 | 2.2019 | 18 | 0.35946 | 6.4703 | 90 | 568.5315 | 22060.2522 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10351 | VACAVILLE 1109799940 | 63601109 | VACAVILLE 1109 | 0.59339 | 9 | 0.35844 | 3.2259 | 91 | 569.1249 | 22057.0263 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
745 | PUTAH CREEK 110267858 | 63681102 | PUTAH CREEK 1102 | 11.4216 | 107 | 0.35702 | 38.201 | 92 | 580.5464 | 22018.8252 | 22018.8252 | #N/A | TRUE | 11.42 | FALSE | TRUE
10611 | PEABODY 2113945670 | 63642113 | PEABODY 2113 | 0.20785 | 3 | 0.35536 | 1.0661 | 93 | 580.7543 | 22017.7592 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
835 | ZACA 1102Y54 | 182681102 | ZACA 1102 | 34.0882 | 296 | 0.35181 | 104.1359 | 94 | 614.8425 | 21913.6233 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9806 | OLETA 1101CB | 163541101 | OLETA 1101 | 0.084664 | 2 | 0.35138 | 0.70277 | 95 | 614.9272 | 21912.9205 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7864 | SISQUOC 1103867486 | 182811103 | SISQUOC 1103 | 2.1165 | 20 | 0.35061 | 7.0121 | 96 | 617.0437 | 21905.9084 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10173 | CALPINE 1146400 | 48011146 | CALPINE 1146 | 3.1431 | 8 | 0.34896 | 2.7917 | 97 | 620.1868 | 21903.1167 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
615 | KERCKHOFF 1101CB | 252561101 | KERCKHOFF 1101 | 17.0284 | 154 | 0.348 | 53.5915 | 98 | 637.2152 | 21849.5252 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1695 | DESCHUTES 110449024 | 103351104 | DESCHUTES 1104 | 16.5991 | 209 | 0.34786 | 72.7038 | 99 | 653.8143 | 21776.8214 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3728 | DESCHUTES 11041370 | 103351104 | DESCHUTES 1104 | 13.5869 | 272 | 0.34561 | 94.0068 | 100 | 667.4013 | 21682.8146 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10316 | CORNING 110135974 | 103331101 | CORNING 1101 | 0.2479 | 11 | 0.34404 | 3.7844 | 101 | 667.6492 | 21679.0302 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10256 | VACAVILLE 1104874798 | 63601104 | VACAVILLE 1104 | 0.41158 | 3 | 0.33623 | 1.0087 | 102 | 668.0608 | 21678.0215 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6277 | WILLITS 1103964 | 42661103 | WILLITS 1103 | 3.1073 | 41 | 0.33456 | 13.717 | 103 | 671.1681 | 21664.3045 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6777 | BELL 11085703 | 152701108 | BELL 1108 | 5.2984 | 96 | 0.33328 | 31.9947 | 104 | 676.4664 | 21632.3099 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10040 | PANORAMA 11021632 | 103461102 | PANORAMA 1102 | 8.5467 | 19 | 0.33244 | 6.3164 | 105 | 685.0131 | 21625.9934 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9960 | WILLITS 1103CB | 42661103 | WILLITS 1103 | 2.9857 | 44 | 0.32751 | 14.4105 | 106 | 687.9988 | 21611.583 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6501 | SAN MIGUEL 1104895760 | 182661104 | SAN MIGUEL 1104 | 9.1711 | 96 | 0.32643 | 31.3373 | 107 | 697.17 | 21580.2456 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4461 | SANTA YNEZ 1104Y04 | 182721104 | SANTA YNEZ 1104 | 15.6586 | 238 | 0.32463 | 77.261 | 108 | 712.8286 | 21502.9846 | 21502.9846 | #N/A | TRUE | 15.65 | FALSE | TRUE
10609 | PEABODY 2106CB | 63642106 | PEABODY 2106 | 0.32679 | 9 | 0.32442 | 2.9197 | 109 | 713.1553 | 21500.0649 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3147 | HOPLAND 1101768 | 42251101 | HOPLAND 1101 | 16.9261 | 115 | 0.32431 | 37.2953 | 110 | 730.0814 | 21462.7695 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6991 | COVELO 1101478952 | 43061101 | COVELO 1101 | 0.71079 | 39 | 0.32368 | 12.6234 | 111 | 730.7922 | 21450.1461 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9010 | STAFFORD 11021202 | 43201102 | STAFFORD 1102 | 7.9017 | 41 | 0.32328 | 13.2544 | 112 | 738.694 | 21436.8917 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5081 | RED BLUFF 11041566 | 103541104 | RED BLUFF 1104 | 12.0889 | 94 | 0.3225 | 30.3149 | 113 | 750.7829 | 21406.5768 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9508 | ANDERSON 1101426745 | 103261101 | ANDERSON 1101 | 0.20439 | 3 | 0.32224 | 0.96673 | 114 | 750.9873 | 21405.6101 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10637 | SYCAMORE CREEK 1111153260 | 102971111 | SYCAMORE CREEK 1111 | 0.2638 | 2 | 0.32186 | 0.64373 | 115 | 751.2511 | 21404.9664 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3800 | DESCHUTES 11049726 | 103351104 | DESCHUTES 1104 | 15.6976 | 197 | 0.32131 | 63.2977 | 116 | 766.9487 | 21341.6686 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4142 | GIRVAN 1101323094 | 103401101 | GIRVAN 1101 | 36.1569 | 208 | 0.32037 | 66.6373 | 117 | 803.1056 | 21275.0313 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4869 | BELL 11082202 | 152701108 | BELL 1108 | 32.5292 | 363 | 0.32016 | 116.2183 | 118 | 835.6348 | 21158.813 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9492 | OLETA 1101296804 | 163541101 | OLETA 1101 | 3.2862 | 12 | 0.31954 | 3.8345 | 119 | 838.921 | 21154.9785 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10541 | CLARKSVILLE 2105CB | 153612105 | CLARKSVILLE 2105 | 0.80419 | 9 | 0.31824 | 2.8642 | 120 | 839.7252 | 21152.1143 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5372 | TEMPLETON 2113A20 | 183052113 | TEMPLETON 2113 | 7.4575 | 92 | 0.3179 | 29.2466 | 121 | 847.1827 | 21122.8677 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8293 | VACAVILLE 110838316 | 63601108 | VACAVILLE 1108 | 15.9209 | 232 | 0.31672 | 73.4796 | 122 | 863.1036 | 21049.3881 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
907 | COTTONWOOD 1102544790 | 102931102 | COTTONWOOD 1102 | 16.3719 | 185 | 0.31273 | 57.8548 | 123 | 879.4755 | 20991.5333 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6176 | COARSEGOLD 21045525 | 254432104 | COARSEGOLD 2104 | 13.1465 | 175 | 0.31171 | 54.5497 | 124 | 892.622 | 20936.9836 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3989 | MIDDLETOWN 1102878 | 43141102 | MIDDLETOWN 1102 | 3.3752 | 49 | 0.31109 | 15.2435 | 125 | 895.9972 | 20921.7401 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2201 | RACETRACK 1704CB | 163761704 | RACETRACK 1704 | 22.8928 | 193 | 0.31093 | 60.0095 | 126 | 918.89 | 20861.7305 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4707 | HIGHLANDS 1103828 | 43361103 | HIGHLANDS 1103 | 8.5948 | 112 | 0.31086 | 34.8164 | 127 | 927.4847 | 20826.9141 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8759 | KERCKHOFF 1101R308 | 252561101 | KERCKHOFF 1101 | 3.8641 | 22 | 0.30901 | 6.7983 | 128 | 931.3489 | 20820.1158 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7918 | FORESTHILL 1102CB | 152181102 | FORESTHILL 1102 | 1.6448 | 13 | 0.30873 | 4.0135 | 129 | 932.9936 | 20816.1023 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9076 | SYCAMORE CREEK 1111976428 | 102971111 | SYCAMORE CREEK 1111 | 8.7518 | 82 | 0.30752 | 25.2165 | 130 | 941.7454 | 20790.8858 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6711 | PUTAH CREEK 110396792 | 63681103 | PUTAH CREEK 1103 | 3.9739 | 30 | 0.30689 | 9.2067 | 131 | 945.7193 | 20781.6791 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9779 | COARSEGOLD 21046210 | 254432104 | COARSEGOLD 2104 | 10.6757 | 49 | 0.30465 | 14.9278 | 132 | 956.3951 | 20766.7513 | 20766.7513 | #N/A | TRUE | 10.68 | FALSE | TRUE
7407 | TEMPLETON 2113A12 | 183052113 | TEMPLETON 2113 | 40.3073 | 180 | 0.30414 | 54.7453 | 133 | 996.7024 | 20712.006 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6929 | CLARKSVILLE 2104CB | 153612104 | CLARKSVILLE 2104 | 8.8028 | 107 | 0.30391 | 32.5187 | 134 | 1005.5052 | 20679.4873 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8076 | NORTH DUBLIN 2103CB | 14052103 | NORTH DUBLIN 2103 | 13.884 | 147 | 0.30349 | 44.6134 | 135 | 1019.3892 | 20634.8739 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9798 | BALCH NO 1 1101CB | 252501101 | BALCH NO 1 1101 | 10.5522 | 33 | 0.30244 | 9.9805 | 136 | 1029.9414 | 20624.8934 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8821 | SANTA YNEZ 1104CB | 182721104 | SANTA YNEZ 1104 | 0.035126 | 105 | 0.30185 | 31.6947 | 137 | 1029.9765 | 20593.1987 | 20593.1987 | #N/A | TRUE | 0.38 | FALSE | TRUE
12 | PASO ROBLES 1103N50 | 182611103 | PASO ROBLES 1103 | 2.2288 | 24 | 0.30039 | 7.2094 | 138 | 1032.2054 | 20585.9893 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
461 | KONOCTI 1102354890 | 43311102 | KONOCTI 1102 | 9.3328 | 131 | 0.29712 | 38.9233 | 139 | 1041.5382 | 20547.0661 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4081 | OREGON TRAIL 11021382 | 103521102 | OREGON TRAIL 1102 | 5.4675 | 67 | 0.29503 | 19.7671 | 140 | 1047.0057 | 20527.299 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
207 | AUBERRY 1102CB | 254151102 | AUBERRY 1102 | 34.7177 | 368 | 0.29173 | 107.3565 | 141 | 1081.7235 | 20419.9425 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
929 | CORRAL 1101CB | 162991101 | CORRAL 1101 | 26.2967 | 280 | 0.29054 | 81.3506 | 142 | 1108.0201 | 20338.5918 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3287 | ANDERSON 11031600 | 103261103 | ANDERSON 1103 | 4.4944 | 106 | 0.2889 | 30.6232 | 143 | 1112.5145 | 20307.9686 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1107 | COARSEGOLD 210410030 | 254432104 | COARSEGOLD 2104 | 33.9336 | 227 | 0.28655 | 65.0478 | 144 | 1146.4481 | 20242.9208 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9519 | ARBUCKLE 1104669720 | 62081104 | ARBUCKLE 1104 | 2.245 | 22 | 0.28655 | 6.3042 | 145 | 1148.6932 | 20236.6166 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3809 | WISE 11022230 | 152271102 | WISE 1102 | 23.7482 | 278 | 0.28438 | 79.0585 | 146 | 1172.4414 | 20157.5581 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2464 | SHEPHERD 2111327814 | 252062111 | SHEPHERD 2111 | 11.5731 | 119 | 0.28428 | 33.8288 | 147 | 1184.0144 | 20123.7293 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3815 | PANORAMA 1102280170 | 103461102 | PANORAMA 1102 | 13.0164 | 102 | 0.28426 | 28.9943 | 148 | 1197.0308 | 20094.735 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10166 | TEMPLETON 21132949 | 183052113 | TEMPLETON 2113 | 0.47643 | 6 | 0.28416 | 1.7049 | 149 | 1197.5072 | 20093.03 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6611 | DESCHUTES 1101CB | 103351101 | DESCHUTES 1101 | 4.9829 | 118 | 0.28403 | 33.5157 | 150 | 1202.4902 | 20059.5143 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
195 | COARSEGOLD 21045300 | 254432104 | COARSEGOLD 2104 | 55.8005 | 507 | 0.28372 | 143.8456 | 151 | 1258.2906 | 19915.6687 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5871 | FLINT 1101750 | 152531101 | FLINT 1101 | 4.5636 | 93 | 0.28318 | 26.3354 | 152 | 1262.8543 | 19889.3333 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
952 | SANTA YNEZ 1104Y66 | 182721104 | SANTA YNEZ 1104 | 16.9474 | 138 | 0.28279 | 39.0253 | 153 | 1279.8017 | 19850.3081 | 19850.3081 | #N/A | TRUE | 16.94 | FALSE | TRUE
1401 | SAN JOAQUIN #2 110310320 | 252521103 | SAN JOAQUIN #2 1103 | 11.785 | 133 | 0.28179 | 37.4782 | 154 | 1291.5867 | 19812.8299 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10123 | FULTON 110258990 | 42561102 | FULTON 1102 | 0.26599 | 6 | 0.28025 | 1.6815 | 155 | 1291.8527 | 19811.1484 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3591 | SANTA YNEZ 1101277014 | 182721101 | SANTA YNEZ 1101 | 5.5008 | 149 | 0.28002 | 41.7232 | 156 | 1297.3535 | 19769.4252 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2737 | VOLTA 110153118 | 102541101 | VOLTA 1101 | 9.6273 | 47 | 0.27952 | 13.1375 | 157 | 1306.9808 | 19756.2877 | 19756.2877 | #N/A | TRUE | 9.62 | FALSE | TRUE
9393 | PUTAH CREEK 1103654021 | 63681103 | PUTAH CREEK 1103 | 0.2046 | 12 | 0.27878 | 3.3454 | 158 | 1307.1854 | 19752.9423 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5717 | SHINGLE SPRINGS 210935598 | 153652109 | SHINGLE SPRINGS 2109 | 10.847 | 122 | 0.27855 | 33.9836 | 159 | 1318.0323 | 19718.9587 | 19718.9587 | #N/A | TRUE | 12.5941 | TRUE | TRUE
1630 | OREGON TRAIL 11041574 | 103521104 | OREGON TRAIL 1104 | 16.9108 | 221 | 0.27852 | 61.5533 | 160 | 1334.9432 | 19657.4053 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2168 | HOPLAND 11014626 | 42251101 | HOPLAND 1101 | 27.0525 | 238 | 0.27841 | 66.2609 | 161 | 1361.9956 | 19591.1444 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10275 | SAN MIGUEL 1105873457 | 182661105 | SAN MIGUEL 1105 | 1.5169 | 18 | 0.27723 | 4.9901 | 162 | 1363.5125 | 19586.1543 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5141 | AUBERRY 1101R2578 | 254151101 | AUBERRY 1101 | 46.3393 | 506 | 0.27714 | 140.2335 | 163 | 1409.8519 | 19445.9209 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
710 | COARSEGOLD 2103CB | 254432103 | COARSEGOLD 2103 | 38.4248 | 420 | 0.27679 | 116.2539 | 164 | 1448.2766 | 19329.667 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9397 | BEAR VALLEY 21059570 | 252192105 | BEAR VALLEY 2105 | 8.0496 | 59 | 0.27669 | 16.3249 | 165 | 1456.3262 | 19313.3421 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4772 | COARSEGOLD 2102CB | 254432102 | COARSEGOLD 2102 | 14.0441 | 79 | 0.2766 | 21.851 | 166 | 1470.3703 | 19291.4911 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
11028 | NARROWS PH 1151CB | 153131151 | NARROWS PH 1151 | 0.17836 | 2 | 0.27613 | 0.55227 | 167 | 1470.5487 | 19290.9388 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5439 | KONOCTI 110264664 | 43311102 | KONOCTI 1102 | 27.7628 | 263 | 0.27567 | 72.501 | 168 | 1498.3115 | 19218.4378 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
307 | MOUNTAIN QUARRIES 21011350 | 152282101 | MOUNTAIN QUARRIES 2101 | 21.7526 | 212 | 0.27537 | 58.3793 | 169 | 1520.0641 | 19160.0586 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8396 | NORTH DUBLIN 2101MR765 | 14052101 | NORTH DUBLIN 2101 | 2.0702 | 15 | 0.2736 | 4.104 | 170 | 1522.1343 | 19155.9545 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6379 | PUTAH CREEK 11028352 | 63681102 | PUTAH CREEK 1102 | 6.4005 | 133 | 0.27308 | 36.3202 | 171 | 1528.5348 | 19119.6343 | 19119.6343 | #N/A | TRUE | 6.4 | FALSE | TRUE
7979 | KONOCTI 1102716 | 43311102 | KONOCTI 1102 | 15.342 | 109 | 0.27295 | 29.7514 | 172 | 1543.8768 | 19089.8829 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1249 | PENRYN 11032198 | 152561103 | PENRYN 1103 | 20.2312 | 248 | 0.27291 | 67.6807 | 173 | 1564.108 | 19022.2022 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10021 | OLETA 1101400470 | 163541101 | OLETA 1101 | 0.20759 | 3 | 0.27287 | 0.81862 | 174 | 1564.3156 | 19021.3836 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3674 | AUBERRY 1102R309 | 254151102 | AUBERRY 1102 | 8.5928 | 92 | 0.27286 | 25.1032 | 175 | 1572.9084 | 18996.2804 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1420 | MIDDLETOWN 1102998 | 43141102 | MIDDLETOWN 1102 | 14.8545 | 205 | 0.27124 | 55.6044 | 176 | 1587.7629 | 18940.676 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6398 | CAYETANO 2109MR572 | 14422109 | CAYETANO 2109 | 8.2926 | 80 | 0.27121 | 21.6967 | 177 | 1596.0555 | 18918.9793 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6361 | APPLE HILL 21026552 | 153662102 | APPLE HILL 2102 | 12.4854 | 139 | 0.2712 | 37.6964 | 178 | 1608.5409 | 18881.2829 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5677 | BANGOR 110180670 | 103191101 | BANGOR 1101 | 14.4199 | 158 | 0.27059 | 42.753 | 179 | 1622.9608 | 18838.5299 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7666 | JAMESON 1103118944 | 63801103 | JAMESON 1103 | 2.3449 | 41 | 0.27039 | 11.0862 | 180 | 1625.3058 | 18827.4438 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5313 | HIGHLANDS 1103482 | 43361103 | HIGHLANDS 1103 | 24.5081 | 188 | 0.26975 | 50.7128 | 181 | 1649.8138 | 18776.7309 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5299 | HIGGINS 1109CB | 152691109 | HIGGINS 1109 | 22.6477 | 254 | 0.26784 | 68.0313 | 182 | 1672.4615 | 18708.6996 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7848 | OAKHURST 1101636114 | 254421101 | OAKHURST 1101 | 20.4936 | 153 | 0.26702 | 40.8546 | 183 | 1692.9551 | 18667.8449 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10324 | SANTA YNEZ 1104564710 | 182721104 | SANTA YNEZ 1104 | 0.17013 | 7 | 0.26624 | 1.8637 | 184 | 1693.1252 | 18665.9812 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10018 | LINCOLN 1104275986 | 153701104 | LINCOLN 1104 | 0.58085 | 5 | 0.26526 | 1.3263 | 185 | 1693.7061 | 18664.6549 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5709 | HIGGINS 110950072 | 152691109 | HIGGINS 1109 | 42.3943 | 424 | 0.26524 | 112.4633 | 186 | 1736.1003 | 18552.1917 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3710 | MARIPOSA 210110070 | 254452101 | MARIPOSA 2101 | 26.137 | 249 | 0.2644 | 65.835 | 187 | 1762.2373 | 18486.3566 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3891 | MARIPOSA 210210880 | 254452102 | MARIPOSA 2102 | 39.6903 | 362 | 0.2637 | 95.458 | 188 | 1801.9276 | 18390.8986 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1822 | BELL 110750172 | 152701107 | BELL 1107 | 17.4906 | 210 | 0.2635 | 55.3341 | 189 | 1819.4182 | 18335.5645 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7084 | VACAVILLE 111113652 | 63601111 | VACAVILLE 1111 | 4.2976 | 58 | 0.26339 | 15.2768 | 190 | 1823.7158 | 18320.2877 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3429 | CLOVERDALE 1101399855 | 42821101 | CLOVERDALE 1101 | 2.7408 | 19 | 0.26331 | 5.0028 | 191 | 1826.4566 | 18315.2848 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9762 | HARTLEY 11014710 | 43211101 | HARTLEY 1101 | 1.5003 | 18 | 0.26308 | 4.7355 | 192 | 1827.9569 | 18310.5493 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2103 | DOBBINS 11011808 | 153741101 | DOBBINS 1101 | 15.5397 | 171 | 0.26282 | 44.9426 | 193 | 1843.4966 | 18265.6067 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3817 | DESCHUTES 11011380 | 103351101 | DESCHUTES 1101 | 17.8201 | 204 | 0.26207 | 53.462 | 194 | 1861.3167 | 18212.1447 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1392 | SAND CREEK 110345190 | 254601103 | SAND CREEK 1103 | 37.5908 | 416 | 0.26095 | 108.5552 | 195 | 1898.9075 | 18103.5895 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4741 | BRENTWOOD 2105B504R | 14592105 | BRENTWOOD 2105 | 8.7475 | 97 | 0.26071 | 25.289 | 196 | 1907.655 | 18078.3005 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7636 | VACA DIXON 110118292 | 63591101 | VACA DIXON 1101 | 0.045391 | 73 | 0.26015 | 18.9907 | 197 | 1907.7004 | 18059.3098 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4859 | OREGON TRAIL 1102CB | 103521102 | OREGON TRAIL 1102 | 9.3555 | 98 | 0.25991 | 25.4708 | 198 | 1917.0559 | 18033.839 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1063 | MARIPOSA 210110990 | 254452101 | MARIPOSA 2101 | 40.0451 | 390 | 0.25971 | 101.2865 | 199 | 1957.101 | 17932.5525 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9382 | CORNING 110185162 | 103331101 | CORNING 1101 | 5.7598 | 28 | 0.2589 | 7.2492 | 200 | 1962.8608 | 17925.3033 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1035 | CORRAL 110136652 | 162991101 | CORRAL 1101 | 36.1423 | 357 | 0.25884 | 92.4048 | 201 | 1999.003 | 17832.8985 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4603 | UPPER LAKE 1101660 | 42871101 | UPPER LAKE 1101 | 6.1619 | 91 | 0.25883 | 23.5531 | 202 | 2005.165 | 17809.3454 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
521 | WILLITS 1103696 | 42661103 | WILLITS 1103 | 6.5038 | 87 | 0.25793 | 22.4395 | 203 | 2011.6688 | 17786.9059 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
134 | SAN JOAQUIN #2 1103CB | 252521103 | SAN JOAQUIN #2 1103 | 67.9182 | 589 | 0.25597 | 150.7655 | 204 | 2079.587 | 17636.1404 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3686 | UKIAH 1111534 | 42771111 | UKIAH 1111 | 18.9138 | 142 | 0.25577 | 36.3189 | 205 | 2098.5008 | 17599.8215 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8712 | ELK CREEK 110193504 | 102781101 | ELK CREEK 1101 | 2.1512 | 15 | 0.25426 | 3.8139 | 206 | 2100.652 | 17596.0075 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10786 | PEABODY 2113873304 | 63642113 | PEABODY 2113 | 0.816 | 5 | 0.25419 | 1.2709 | 207 | 2101.468 | 17594.7366 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9423 | CLAY 110359714 | 163341103 | CLAY 1103 | 4.6637 | 34 | 0.25391 | 8.6328 | 208 | 2106.1317 | 17586.1038 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9267 | POTTER VALLEY P H 1105990354 | 42281105 | POTTER VALLEY P H 1105 | 0.1059 | 2 | 0.25341 | 0.50682 | 209 | 2106.2376 | 17585.597 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4480 | LUCERNE 1106526 | 43351106 | LUCERNE 1106 | 10.1036 | 100 | 0.25318 | 25.318 | 210 | 2116.3412 | 17560.279 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3034 | HOPLAND 1101558 | 42251101 | HOPLAND 1101 | 2.9946 | 72 | 0.25266 | 18.1915 | 211 | 2119.3358 | 17542.0874 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4451 | HIGHLANDS 1103568 | 43361103 | HIGHLANDS 1103 | 8.0426 | 118 | 0.25222 | 29.7625 | 212 | 2127.3784 | 17512.3249 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5062 | AUBERRY 1102R902 | 254151102 | AUBERRY 1102 | 15.0784 | 156 | 0.25137 | 39.2136 | 213 | 2142.4568 | 17473.1113 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5371 | SUNOL 1101MR169 | 14241101 | SUNOL 1101 | 3.0929 | 96 | 0.25044 | 24.0426 | 214 | 2145.5497 | 17449.0687 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8139 | LAS GALLINAS A 110599904 | 42991105 | LAS GALLINAS A 1105 | 5.5621 | 54 | 0.25006 | 13.5032 | 215 | 2151.1119 | 17435.5655 | 17435.5655 | #N/A | TRUE | 2.7962 | TRUE | TRUE
4462 | WILLITS 110337504 | 42661103 | WILLITS 1103 | 1.1752 | 41 | 0.24974 | 10.2392 | 216 | 2152.2871 | 17425.3263 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4593 | POSO MOUNTAIN 2101CB | 253642101 | POSO MOUNTAIN 2101 | 4.3034 | 22 | 0.24862 | 5.4697 | 217 | 2156.5905 | 17419.8566 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6909 | WYANDOTTE 1109702710 | 102911109 | WYANDOTTE 1109 | 2.6641 | 49 | 0.24845 | 12.174 | 218 | 2159.2546 | 17407.6826 | 17407.6826 | #N/A | TRUE | 0.60739 | TRUE | TRUE
9944 | WYANDOTTE 110366146 | 102911103 | WYANDOTTE 1103 | 0.15681 | 4 | 0.24793 | 0.99171 | 219 | 2159.4114 | 17406.6909 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10031 | SOLEDAD 2102346006 | 182052102 | SOLEDAD 2102 | 2.2688 | 5 | 0.24765 | 1.2382 | 220 | 2161.6802 | 17405.4527 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
905 | CORNING 110290036 | 103331102 | CORNING 1102 | 13.4004 | 87 | 0.24724 | 21.5103 | 221 | 2175.0805 | 17383.9424 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5847 | OAKHURST 11035732 | 254421103 | OAKHURST 1103 | 3.3843 | 37 | 0.24719 | 9.1461 | 222 | 2178.4648 | 17374.7963 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5505 | MARIPOSA 210237282 | 254452102 | MARIPOSA 2102 | 53.7171 | 498 | 0.24522 | 122.1205 | 223 | 2232.1819 | 17252.6758 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4841 | OAKHURST 110363334 | 254421103 | OAKHURST 1103 | 17.2902 | 154 | 0.24446 | 37.6467 | 224 | 2249.4721 | 17215.0291 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8342 | BANGOR 110131502 | 103191101 | BANGOR 1101 | 11.8734 | 102 | 0.24429 | 24.9173 | 225 | 2261.3455 | 17190.1118 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9205 | POINT MORETTI 110135874 | 82931101 | POINT MORETTI 1101 | 0.20478 | 4 | 0.24298 | 0.97191 | 226 | 2261.5503 | 17189.1399 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2854 | SHINGLE SPRINGS 21099372 | 153652109 | SHINGLE SPRINGS 2109 | 17.8687 | 190 | 0.24281 | 46.1342 | 227 | 2279.419 | 17143.0056 | 17143.0056 | #N/A | TRUE | 17.5703 | TRUE | TRUE
10573 | GEYSERVILLE 1102756 | 42891102 | GEYSERVILLE 1102 | 0.58944 | 7 | 0.24238 | 1.6966 | 228 | 2280.0084 | 17141.309 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6313 | SAN MIGUEL 1104N60 | 182661104 | SAN MIGUEL 1104 | 8.2764 | 66 | 0.24236 | 15.9958 | 229 | 2288.2848 | 17125.3131 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2085 | LINCOLN 1104685276 | 153701104 | LINCOLN 1104 | 6.4838 | 216 | 0.24208 | 52.2897 | 230 | 2294.7686 | 17073.0234 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7825 | HORSESHOE 1101416226 | 152571101 | HORSESHOE 1101 | 0.11601 | 5 | 0.24182 | 1.2091 | 231 | 2294.8846 | 17071.8143 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9295 | BROWNS VALLEY 110117011 | 152921101 | BROWNS VALLEY 1101 | 1.8678 | 22 | 0.24153 | 5.3136 | 232 | 2296.7524 | 17066.5007 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1428 | ZACA 1102Y02 | 182681102 | ZACA 1102 | 10.449 | 158 | 0.24142 | 38.1442 | 233 | 2307.2014 | 17028.3565 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6825 | OLETA 1102186326 | 163541102 | OLETA 1102 | 11.8638 | 123 | 0.24114 | 29.6596 | 234 | 2319.0652 | 16998.6969 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7670 | STANISLAUS 1702CB | 162821702 | STANISLAUS 1702 | 8.1208 | 67 | 0.24096 | 16.1444 | 235 | 2327.186 | 16982.5525 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9773 | MADISON 2101117644 | 63172101 | MADISON 2101 | 0.67144 | 12 | 0.23987 | 2.8784 | 236 | 2327.8574 | 16979.6741 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10170 | PUTAH CREEK 1105617260 | 63681105 | PUTAH CREEK 1105 | 1.1665 | 15 | 0.2396 | 3.5941 | 237 | 2329.0239 | 16976.08 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10828 | BUELLTON 110163389 | 183041101 | BUELLTON 1101 | 0 | 2 | 0.23935 | 0.47871 | 238 | 2329.0239 | 16975.6013 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8291 | CLEAR LAKE 1102904 | 42141102 | CLEAR LAKE 1102 | 3.3845 | 30 | 0.23862 | 7.1587 | 239 | 2332.4084 | 16968.4425 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6235 | SHINGLE SPRINGS 210519522 | 153652105 | SHINGLE SPRINGS 2105 | 9.6738 | 113 | 0.23827 | 26.9251 | 240 | 2342.0822 | 16941.5175 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9843 | SUNOL 1101MR387 | 14241101 | SUNOL 1101 | 5.013 | 24 | 0.23776 | 5.7062 | 241 | 2347.0952 | 16935.8113 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
109 | WISE 11022054 | 152271102 | WISE 1102 | 13.0143 | 147 | 0.23735 | 34.8898 | 242 | 2360.1095 | 16900.9214 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9387 | ANTELOPE 1101318686 | 252021101 | ANTELOPE 1101 | 1.4578 | 7 | 0.23683 | 1.6578 | 243 | 2361.5673 | 16899.2636 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2465 | JESSUP 11021314 | 103441102 | JESSUP 1102 | 6.0148 | 161 | 0.23664 | 38.0983 | 244 | 2367.5821 | 16861.1654 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4610 | KERCKHOFF 1101R353 | 252561101 | KERCKHOFF 1101 | 13.7915 | 53 | 0.23576 | 12.4952 | 245 | 2381.3736 | 16848.6702 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7566 | CORRAL 110112608 | 162991101 | CORRAL 1101 | 16.8621 | 187 | 0.23545 | 44.029 | 246 | 2398.2357 | 16804.6412 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5704 | SHEPHERD 2111707358 | 252062111 | SHEPHERD 2111 | 18.9795 | 219 | 0.23489 | 51.4409 | 247 | 2417.2152 | 16753.2003 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10861 | PEORIA 170492888 | 163781704 | PEORIA 1704 | 0.24898 | 4 | 0.23471 | 0.93885 | 248 | 2417.4642 | 16752.2615 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5055 | FROGTOWN 17028482 | 163451702 | FROGTOWN 1702 | 14.5376 | 117 | 0.23437 | 27.4214 | 249 | 2432.0018 | 16724.84 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10192 | MADISON 2101725408 | 63172101 | MADISON 2101 | 0.95102 | 9 | 0.23427 | 2.1085 | 250 | 2432.9528 | 16722.7316 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
852 | PASO ROBLES 1104R56 | 182611104 | PASO ROBLES 1104 | 11.5141 | 117 | 0.2342 | 27.401 | 251 | 2444.4669 | 16695.3306 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9420 | FRENCH GULCH 11011892 | 103381101 | FRENCH GULCH 1101 | 3.2034 | 12 | 0.23339 | 2.8006 | 252 | 2447.6703 | 16692.53 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2713 | ELK CREEK 110137334 | 102781101 | ELK CREEK 1101 | 9.5668 | 70 | 0.23311 | 16.3175 | 253 | 2457.2371 | 16676.2125 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8722 | POSO MOUNTAIN 21033988 | 253642103 | POSO MOUNTAIN 2103 | 16.9159 | 68 | 0.23303 | 15.8463 | 254 | 2474.1531 | 16660.3662 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6130 | OREGON TRAIL 1104CB | 103521104 | OREGON TRAIL 1104 | 10.5844 | 164 | 0.23182 | 38.0188 | 255 | 2484.7374 | 16622.3474 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6781 | PALMER 1101M84 | 183031101 | PALMER 1101 | 23.4425 | 145 | 0.23169 | 33.5958 | 256 | 2508.1799 | 16588.7517 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7251 | PASO ROBLES 1103N58 | 182611103 | PASO ROBLES 1103 | 4.5492 | 91 | 0.23099 | 21.0205 | 257 | 2512.7291 | 16567.7312 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9345 | CHOLAME 21025597 | 182562102 | CHOLAME 2102 | 5.1149 | 22 | 0.23009 | 5.062 | 258 | 2517.844 | 16562.6692 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6582 | UPPER LAKE 1101412 | 42871101 | UPPER LAKE 1101 | 10.317 | 152 | 0.23008 | 34.9724 | 259 | 2528.161 | 16527.6968 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7180 | PASO ROBLES 11032731 | 182611103 | PASO ROBLES 1103 | 1.6349 | 13 | 0.2296 | 2.9847 | 260 | 2529.7959 | 16524.712 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6731 | DEL MAR 2109CB | 152582109 | DEL MAR 2109 | 1.4773 | 72 | 0.22956 | 16.5281 | 261 | 2531.2732 | 16508.1839 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4193 | ANDERSON 1103226050 | 103261103 | ANDERSON 1103 | 4.876 | 160 | 0.22913 | 36.6601 | 262 | 2536.1492 | 16471.5238 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2449 | COARSEGOLD 210410400 | 254432104 | COARSEGOLD 2104 | 42.6149 | 539 | 0.22826 | 123.0305 | 263 | 2578.7641 | 16348.4933 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6456 | HIGGINS 110950078 | 152691109 | HIGGINS 1109 | 48.4307 | 427 | 0.22791 | 97.3194 | 264 | 2627.1948 | 16251.1739 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6171 | WYANDOTTE 110737472 | 102911107 | WYANDOTTE 1107 | 9.2827 | 157 | 0.22739 | 35.7007 | 265 | 2636.4775 | 16215.4732 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1604 | COARSEGOLD 210310820 | 254432103 | COARSEGOLD 2103 | 28.8331 | 327 | 0.2269 | 74.1966 | 266 | 2665.3106 | 16141.2766 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3581 | JESSUP 110296554 | 103441102 | JESSUP 1102 | 8.0717 | 172 | 0.22645 | 38.9486 | 267 | 2673.3823 | 16102.328 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10176 | CLARK ROAD 1102CB | 103091102 | CLARK ROAD 1102 | 0.89192 | 20 | 0.22632 | 4.5263 | 268 | 2674.2742 | 16097.8016 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1714 | BUELLTON 1102Y50 | 183041102 | BUELLTON 1102 | 10.6284 | 147 | 0.22624 | 33.2573 | 269 | 2684.9026 | 16064.5443 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2661 | CLAY 11031230 | 163341103 | CLAY 1103 | 16.8239 | 136 | 0.22608 | 30.7471 | 270 | 2701.7264 | 16033.7972 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
511 | COTTONWOOD 11029026 | 102931102 | COTTONWOOD 1102 | 12.5262 | 282 | 0.22599 | 63.7295 | 271 | 2714.2527 | 15970.0677 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5682 | CLOVERDALE 1102672 | 42821102 | CLOVERDALE 1102 | 21.8079 | 140 | 0.22571 | 31.5995 | 272 | 2736.0605 | 15938.4682 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
920 | RED BLUFF 11041630 | 103541104 | RED BLUFF 1104 | 2.499 | 152 | 0.22562 | 34.2944 | 273 | 2738.5596 | 15904.1738 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6155 | AUBERRY 1101R2839 | 254151101 | AUBERRY 1101 | 12.8085 | 121 | 0.22501 | 27.2266 | 274 | 2751.3681 | 15876.9472 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
252 | CLARK ROAD 11022582 | 103091102 | CLARK ROAD 1102 | 19.895 | 186 | 0.22449 | 41.7559 | 275 | 2771.2631 | 15835.1913 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5168 | CORNING 11021622 | 103331102 | CORNING 1102 | 33.9975 | 126 | 0.22413 | 28.2406 | 276 | 2805.2606 | 15806.9507 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2620 | AUBERRY 1101R2579 | 254151101 | AUBERRY 1101 | 34.9054 | 286 | 0.22394 | 64.0469 | 277 | 2840.166 | 15742.9037 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7109 | AUBERRY 1102R1013 | 254151102 | AUBERRY 1102 | 12.4639 | 132 | 0.22385 | 29.5483 | 278 | 2852.6299 | 15713.3555 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1039 | SILVERADO 2104726 | 43432104 | SILVERADO 2104 | 30.3762 | 263 | 0.22347 | 58.7725 | 279 | 2883.0061 | 15654.583 | 15654.583 | #N/A | TRUE | 6.1621 | TRUE | TRUE
8364 | PEORIA 1705CB | 163781705 | PEORIA 1705 | 7.0494 | 33 | 0.22294 | 7.3571 | 280 | 2890.0555 | 15647.226 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
42 | CEDAR CREEK 11011664 | 103321101 | CEDAR CREEK 1101 | 29.572 | 244 | 0.22209 | 54.1896 | 281 | 2919.6274 | 15593.0364 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8613 | ZACA 1101Y72 | 182681101 | ZACA 1101 | 6.3801 | 36 | 0.2213 | 7.967 | 282 | 2926.0076 | 15585.0694 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5656 | PANORAMA 1102508502 | 103461102 | PANORAMA 1102 | 11.7575 | 115 | 0.22043 | 25.3491 | 283 | 2937.7651 | 15559.7203 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2018 | SMARTVILLE 1101CB | 153791101 | SMARTVILLE 1101 | 16.1753 | 152 | 0.21931 | 33.3354 | 284 | 2953.9404 | 15526.3848 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8459 | CAYETANO 21099504 | 14422109 | CAYETANO 2109 | 14.471 | 97 | 0.21922 | 21.2645 | 285 | 2968.4114 | 15505.1203 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3475 | SO. CAL. EDISON #3 1101CB | 258861101 | SO. CAL. EDISON #3 1101 | 8.5384 | 32 | 0.21869 | 6.998 | 286 | 2976.9499 | 15498.1224 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5637 | NARROWS 2101CB | 153132101 | NARROWS 2101 | 15.5673 | 65 | 0.21823 | 14.185 | 287 | 2992.5172 | 15483.9374 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8049 | BROWNS VALLEY 110136622 | 152921101 | BROWNS VALLEY 1101 | 5.1447 | 42 | 0.21771 | 9.1438 | 288 | 2997.6619 | 15474.7936 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5251 | WYANDOTTE 110313018 | 102911103 | WYANDOTTE 1103 | 0.67768 | 20 | 0.21662 | 4.3325 | 289 | 2998.3396 | 15470.4611 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7438 | OREGON TRAIL 1103CB | 103521103 | OREGON TRAIL 1103 | 2.7062 | 38 | 0.21644 | 8.2246 | 290 | 3001.0458 | 15462.2365 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9233 | PASO ROBLES 1103N52 | 182611103 | PASO ROBLES 1103 | 6.5701 | 32 | 0.21643 | 6.9258 | 291 | 3007.616 | 15455.3107 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5544 | TYLER 11051536 | 103571105 | TYLER 1105 | 17.7774 | 79 | 0.21608 | 17.0703 | 292 | 3025.3933 | 15438.2404 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8708 | PUTAH CREEK 1105665952 | 63681105 | PUTAH CREEK 1105 | 0.15126 | 13 | 0.21591 | 2.8069 | 293 | 3025.5446 | 15435.4336 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9580 | SUMMIT 110147786 | 152591101 | SUMMIT 1101 | 1.8121 | 13 | 0.21513 | 2.7967 | 294 | 3027.3567 | 15432.6368 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10253 | CLOVERDALE 1102736078 | 42821102 | CLOVERDALE 1102 | 0.23224 | 3 | 0.2146 | 0.64381 | 295 | 3027.589 | 15431.993 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10589 | DEL MAR 2109306972 | 152582109 | DEL MAR 2109 | 0.051859 | 2 | 0.21455 | 0.4291 | 296 | 3027.6408 | 15431.5639 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9314 | CALPINE 1146CB | 48011146 | CALPINE 1146 | 3.0749 | 21 | 0.21399 | 4.4937 | 297 | 3030.7157 | 15427.0702 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5389 | BEAR VALLEY 210511210 | 252192105 | BEAR VALLEY 2105 | 17.0869 | 139 | 0.21387 | 29.7273 | 298 | 3047.8026 | 15397.3429 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9003 | HARTLEY 1102385838 | 43211102 | HARTLEY 1102 | 1.2468 | 11 | 0.21349 | 2.3484 | 299 | 3049.0494 | 15394.9945 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4243 | CLAYTON 22122944 | 12022212 | CLAYTON 2212 | 15.0792 | 148 | 0.21331 | 31.5694 | 300 | 3064.1286 | 15363.4251 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3022 | DESCHUTES 11041582 | 103351104 | DESCHUTES 1104 | 6.3798 | 173 | 0.21327 | 36.8955 | 301 | 3070.5085 | 15326.5296 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5186 | DUNLAP 11027360 | 254061102 | DUNLAP 1102 | 8.9138 | 83 | 0.21272 | 17.6557 | 302 | 3079.4222 | 15308.8739 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7188 | UPPER LAKE 1101472084 | 42871101 | UPPER LAKE 1101 | 4.6331 | 66 | 0.21229 | 14.0108 | 303 | 3084.0554 | 15294.863 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1958 | CURTIS 170411290 | 163351704 | CURTIS 1704 | 7.8695 | 75 | 0.21224 | 15.9178 | 304 | 3091.9249 | 15278.9452 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10301 | SCE VEGAS 1701CB | 188881701 | SCE VEGAS 1701 | 0.10467 | 1 | 0.2122 | 0.2122 | 305 | 3092.0295 | 15278.733 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4384 | AUBERRY 110237466 | 254151102 | AUBERRY 1102 | 31.3612 | 345 | 0.21127 | 72.8874 | 306 | 3123.3908 | 15205.8456 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2676 | BUELLTON 1102CB | 183041102 | BUELLTON 1102 | 7.0863 | 148 | 0.21085 | 31.2055 | 307 | 3130.4771 | 15174.6401 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5276 | SANTA YNEZ 110477098 | 182721104 | SANTA YNEZ 1104 | 11.9643 | 112 | 0.21042 | 23.5673 | 308 | 3142.4414 | 15151.0728 | 15151.0728 | #N/A | TRUE | 11.96 | FALSE | TRUE
7565 | SILVERADO 2104806 | 43432104 | SILVERADO 2104 | 21.0265 | 229 | 0.21008 | 48.1076 | 309 | 3163.4679 | 15102.9653 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1159 | LONE TREE 210521210 | 13232105 | LONE TREE 2105 | 12.8566 | 111 | 0.20896 | 23.1943 | 310 | 3176.3245 | 15079.7709 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1515 | WYANDOTTE 110979932 | 102911109 | WYANDOTTE 1109 | 22.0664 | 345 | 0.20828 | 71.8562 | 311 | 3198.3909 | 15007.9148 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4727 | REDBUD 1101454 | 43191101 | REDBUD 1101 | 5.5371 | 54 | 0.20738 | 11.1984 | 312 | 3203.928 | 14996.7164 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2411 | MARIPOSA 210190180 | 254452101 | MARIPOSA 2101 | 4.9571 | 49 | 0.20688 | 10.1373 | 313 | 3208.8851 | 14986.5791 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6630 | MIDDLETOWN 1101644756 | 43141101 | MIDDLETOWN 1101 | 17.325 | 163 | 0.20636 | 33.6372 | 314 | 3226.2101 | 14952.9419 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8301 | ELK CREEK 11012002 | 102781101 | ELK CREEK 1101 | 21.7811 | 109 | 0.20473 | 22.3155 | 315 | 3247.9912 | 14930.6264 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1537 | BELL 11072400 | 152701107 | BELL 1107 | 25.7395 | 320 | 0.20423 | 65.3543 | 316 | 3273.7307 | 14865.2721 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2016 | PETALUMA C 1108296 | 42631108 | PETALUMA C 1108 | 14.7695 | 123 | 0.20401 | 25.0928 | 317 | 3288.5001 | 14840.1792 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1327 | DESCHUTES 1104CB | 103351104 | DESCHUTES 1104 | 13.5086 | 273 | 0.20316 | 55.4629 | 318 | 3302.0088 | 14784.7163 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10175 | JESSUP 1102936897 | 103441102 | JESSUP 1102 | 0.41364 | 12 | 0.20267 | 2.432 | 319 | 3302.4224 | 14782.2843 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2512 | CLAY 110334338 | 163341103 | CLAY 1103 | 9.7742 | 66 | 0.2022 | 13.3455 | 320 | 3312.1966 | 14768.9388 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3530 | AUBERRY 1102R2850 | 254151102 | AUBERRY 1102 | 26.3694 | 222 | 0.20166 | 44.7693 | 321 | 3338.566 | 14724.1695 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4238 | NORTH BRANCH 1101CB | 163231101 | NORTH BRANCH 1101 | 15.7926 | 114 | 0.20132 | 22.9503 | 322 | 3354.3586 | 14701.2192 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
11083 | NARROWS 2104CB | 153132104 | NARROWS 2104 | 0.0028415 | 1 | 0.20132 | 0.20132 | 323 | 3354.3615 | 14701.0179 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
389 | VASCO 1102MR176 | 13751102 | VASCO 1102 | 38.828 | 256 | 0.20121 | 51.5086 | 324 | 3393.1894 | 14649.5093 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7455 | SAN MIGUEL 1104514987 | 182661104 | SAN MIGUEL 1104 | 8.3156 | 63 | 0.20048 | 12.6303 | 325 | 3401.505 | 14636.879 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7507 | NORTH BRANCH 110111158 | 163231101 | NORTH BRANCH 1101 | 12.7408 | 229 | 0.20008 | 45.8175 | 326 | 3414.2458 | 14591.0614 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3193 | AUBERRY 1101R314 | 254151101 | AUBERRY 1101 | 42.4149 | 390 | 0.20004 | 78.017 | 327 | 3456.6606 | 14513.0444 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1293 | MIDDLETOWN 11014646 | 43141101 | MIDDLETOWN 1101 | 18.5633 | 165 | 0.19983 | 32.9712 | 328 | 3475.2239 | 14480.0732 | 14480.0732 | #N/A | TRUE | 2.3492 | TRUE | TRUE
9642 | LUCERNE 11034200 | 43351103 | LUCERNE 1103 | 4.0371 | 37 | 0.19927 | 7.3729 | 329 | 3479.261 | 14472.7003 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7729 | AUBERRY 110149122 | 254151101 | AUBERRY 1101 | 3.9629 | 40 | 0.19907 | 7.9627 | 330 | 3483.224 | 14464.7376 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
464 | WOODACRE 110196844 | 43021101 | WOODACRE 1101 | 5.9393 | 63 | 0.19881 | 12.5249 | 331 | 3489.1633 | 14452.2127 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4726 | SHINGLE SPRINGS 210985766 | 153652109 | SHINGLE SPRINGS 2109 | 18.4877 | 166 | 0.19865 | 32.9759 | 332 | 3507.651 | 14419.2368 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9424 | VINEYARD 2110391250 | 14502110 | VINEYARD 2110 | 0.92065 | 3 | 0.19841 | 0.59524 | 333 | 3508.5716 | 14418.6416 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
308 | CALPINE 1144CB | 48011144 | CALPINE 1144 | 26.271 | 131 | 0.19817 | 25.9607 | 334 | 3534.8426 | 14392.6809 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7335 | UPPER LAKE 11011276 | 42871101 | UPPER LAKE 1101 | 12.9316 | 116 | 0.19794 | 22.9608 | 335 | 3547.7742 | 14369.7201 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3179 | CHOLAME 2102796386 | 182562102 | CHOLAME 2102 | 35.6693 | 159 | 0.19792 | 31.4686 | 336 | 3583.4435 | 14338.2515 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9031 | SAND CREEK 1103CB | 254601103 | SAND CREEK 1103 | 13.0411 | 77 | 0.19768 | 15.2216 | 337 | 3596.4847 | 14323.0299 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6545 | TULUCAY 1101628 | 42301101 | TULUCAY 1101 | 4.1726 | 98 | 0.19686 | 19.2923 | 338 | 3600.6572 | 14303.7376 | #N/A | 14303.7376 | FALSE | 0 | TRUE | TRUE
4963 | BEAR VALLEY 210190550 | 252192101 | BEAR VALLEY 2101 | 8.0244 | 47 | 0.19624 | 9.2235 | 339 | 3608.6816 | 14294.5141 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8575 | ELK CREEK 11012106 | 102781101 | ELK CREEK 1101 | 13.2402 | 67 | 0.1961 | 13.1388 | 340 | 3621.9218 | 14281.3753 | 14281.3753 | #N/A | TRUE | 7.9 | TRUE | TRUE
3500 | DUNLAP 11037040 | 254061103 | DUNLAP 1103 | 24.7794 | 230 | 0.19605 | 45.0921 | 341 | 3646.7012 | 14236.2832 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2568 | LAYTONVILLE 1102500 | 42681102 | LAYTONVILLE 1102 | 21.3647 | 214 | 0.19576 | 41.8921 | 342 | 3668.0659 | 14194.3911 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2190 | DIAMOND SPRINGS 110519910 | 152261105 | DIAMOND SPRINGS 1105 | 20.699 | 226 | 0.19568 | 44.2238 | 343 | 3688.7649 | 14150.1673 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9927 | FITCH MOUNTAIN 1111555644 | 42751111 | FITCH MOUNTAIN 1111 | 0.16699 | 19 | 0.19539 | 3.7125 | 344 | 3688.9319 | 14146.4548 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
41 | REDBUD 1101708166 | 43191101 | REDBUD 1101 | 11.5048 | 162 | 0.19539 | 31.6535 | 345 | 3700.4367 | 14114.8013 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8428 | CALPELLA 11013419 | 43411101 | CALPELLA 1101 | 7.9853 | 38 | 0.19531 | 7.4218 | 346 | 3708.4219 | 14107.3795 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4645 | OLETA 110241396 | 163541102 | OLETA 1102 | 6.7546 | 75 | 0.19503 | 14.6272 | 347 | 3715.1765 | 14092.7523 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1354 | CORRAL 1102CB | 162991102 | CORRAL 1102 | 16.8855 | 236 | 0.19501 | 46.0213 | 348 | 3732.0621 | 14046.731 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6647 | TIVY VALLEY 1107584840 | 252941107 | TIVY VALLEY 1107 | 45.0784 | 449 | 0.19446 | 87.311 | 349 | 3777.1404 | 13959.42 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4112 | JESSUP 110141356 | 103441101 | JESSUP 1101 | 32.4662 | 318 | 0.19445 | 61.8351 | 350 | 3809.6067 | 13897.5849 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1219 | APPLE HILL 21021532 | 153662102 | APPLE HILL 2102 | 38.9629 | 465 | 0.19412 | 90.2637 | 351 | 3848.5696 | 13807.3212 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4008 | OLETA 11011208 | 163541101 | OLETA 1101 | 33.0009 | 334 | 0.19404 | 64.811 | 352 | 3881.5705 | 13742.5102 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9763 | WISHON 1101CB | 251511101 | WISHON 1101 | 7.6405 | 36 | 0.19398 | 6.9834 | 353 | 3889.211 | 13735.5268 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4721 | COPPERMINE 1104613086 | 252411104 | COPPERMINE 1104 | 5.1231 | 63 | 0.19391 | 12.2166 | 354 | 3894.3341 | 13723.3102 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8166 | BANGOR 1101CB | 103191101 | BANGOR 1101 | 18.7561 | 171 | 0.19378 | 33.1366 | 355 | 3913.0902 | 13690.1736 | 13690.1736 | #N/A | TRUE | 0.85 | TRUE | TRUE
10364 | MADISON 2101745850 | 63172101 | MADISON 2101 | 0.47947 | 7 | 0.19369 | 1.3558 | 356 | 3913.5697 | 13688.8178 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10620 | OLETA 1102793776 | 163541102 | OLETA 1102 | 1.2163 | 6 | 0.19328 | 1.1597 | 357 | 3914.7859 | 13687.6581 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1881 | PENRYN 1103604 | 152561103 | PENRYN 1103 | 26.4244 | 240 | 0.19315 | 46.357 | 358 | 3941.2103 | 13641.301 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10174 | LAS GALLINAS A 1105532 | 42991105 | LAS GALLINAS A 1105 | 4.4122 | 34 | 0.19264 | 6.5497 | 359 | 3945.6225 | 13634.7514 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9563 | ELK CREEK 11012032 | 102781101 | ELK CREEK 1101 | 8.7618 | 52 | 0.19237 | 10.0031 | 360 | 3954.3843 | 13624.7483 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7617 | WYANDOTTE 110213044 | 102911102 | WYANDOTTE 1102 | 4.7699 | 51 | 0.19229 | 9.8065 | 361 | 3959.1542 | 13614.9417 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3855 | SAND CREEK 11037140 | 254601103 | SAND CREEK 1103 | 26.29 | 296 | 0.19202 | 56.8394 | 362 | 3985.4442 | 13558.1024 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5056 | BANGOR 110182350 | 103191101 | BANGOR 1101 | 19.6266 | 230 | 0.19196 | 44.1515 | 363 | 4005.0708 | 13513.9509 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
523 | DUNLAP 11037220 | 254061103 | DUNLAP 1103 | 24.8305 | 188 | 0.19171 | 36.0414 | 364 | 4029.9013 | 13477.9095 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8426 | FORT ROSS 1121CB | 42851121 | FORT ROSS 1121 | 0.016118 | 1 | 0.19152 | 0.19152 | 365 | 4029.9174 | 13477.7179 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8629 | FOOTHILL 1101645910 | 182951101 | FOOTHILL 1101 | 0.48143 | 14 | 0.19134 | 2.6788 | 366 | 4030.3989 | 13475.0391 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7469 | PALMER 110198478 | 183031101 | PALMER 1101 | 6.0154 | 34 | 0.19124 | 6.5022 | 367 | 4036.4142 | 13468.5369 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5366 | WYANDOTTE 11095607 | 102911109 | WYANDOTTE 1109 | 4.5158 | 71 | 0.19115 | 13.5714 | 368 | 4040.93 | 13454.9654 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9473 | HARTLEY 1102524 | 43211102 | HARTLEY 1102 | 0.24826 | 31 | 0.19015 | 5.8946 | 369 | 4041.1783 | 13449.0708 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6494 | WISE 1102697216 | 152271102 | WISE 1102 | 13.2842 | 145 | 0.18992 | 27.5378 | 370 | 4054.4625 | 13421.533 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4257 | REDBUD 1102CB | 43191102 | REDBUD 1102 | 17.4931 | 170 | 0.18973 | 32.2538 | 371 | 4071.9556 | 13389.2792 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9558 | BRENTWOOD 21056512 | 14592105 | BRENTWOOD 2105 | 0.65121 | 5 | 0.18909 | 0.94545 | 372 | 4072.6068 | 13388.3338 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10458 | DEL MAR 2109805882 | 152582109 | DEL MAR 2109 | 0.29665 | 6 | 0.18904 | 1.1343 | 373 | 4072.9035 | 13387.1995 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2068 | OLETA 11021228 | 163541102 | OLETA 1102 | 10.8452 | 368 | 0.18877 | 69.4681 | 374 | 4083.7487 | 13317.7315 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2280 | DESCHUTES 11011580 | 103351101 | DESCHUTES 1101 | 47.4617 | 383 | 0.18779 | 71.9249 | 375 | 4131.2104 | 13245.8065 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6271 | COTTONWOOD 110131500 | 102931101 | COTTONWOOD 1101 | 4.6622 | 111 | 0.18759 | 20.823 | 376 | 4135.8726 | 13224.9836 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
449 | CLAYTON 221296224 | 12022212 | CLAYTON 2212 | 19.3992 | 174 | 0.18755 | 32.6329 | 377 | 4155.2718 | 13192.3507 | 13192.3507 | #N/A | TRUE | 2.8186 | TRUE | TRUE
9225 | BUCKS CREEK 1102CB | 102211102 | BUCKS CREEK 1102 | 29.5832 | 121 | 0.1873 | 22.6633 | 378 | 4184.8549 | 13169.6874 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4556 | MARIPOSA 210237288 | 254452102 | MARIPOSA 2102 | 85.2905 | 678 | 0.18718 | 126.9051 | 379 | 4270.1454 | 13042.7824 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9851 | PANORAMA 1101885215 | 103461101 | PANORAMA 1101 | 2.0047 | 23 | 0.18705 | 4.3021 | 380 | 4272.1501 | 13038.4803 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1129 | PETALUMA C 1109128 | 42631109 | PETALUMA C 1109 | 34.9319 | 269 | 0.18687 | 50.2671 | 381 | 4307.082 | 12988.2132 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5974 | DOBBINS 110169722 | 153741101 | DOBBINS 1101 | 6.6336 | 68 | 0.18675 | 12.6993 | 382 | 4313.7155 | 12975.5139 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6088 | TYLER 110585132 | 103571105 | TYLER 1105 | 31.133 | 217 | 0.18633 | 40.4342 | 383 | 4344.8486 | 12935.0798 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6487 | STILLWATER 110248952 | 103561102 | STILLWATER 1102 | 10.597 | 123 | 0.18561 | 22.8305 | 384 | 4355.4456 | 12912.2492 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7029 | PENRYN 1106212772 | 152561106 | PENRYN 1106 | 1.0001 | 11 | 0.18554 | 2.041 | 385 | 4356.4457 | 12910.2083 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7958 | GEYSERVILLE 110179788 | 42891101 | GEYSERVILLE 1101 | 39.5659 | 157 | 0.18551 | 29.1256 | 386 | 4396.0116 | 12881.0826 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2772 | WYANDOTTE 110913052 | 102911109 | WYANDOTTE 1109 | 19.5651 | 213 | 0.18514 | 39.4358 | 387 | 4415.5767 | 12841.6469 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9699 | LOGAN CREEK 2102795010 | 103142102 | LOGAN CREEK 2102 | 3.7072 | 12 | 0.18505 | 2.2206 | 388 | 4419.2839 | 12839.4263 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2290 | JESSUP 11021550 | 103441102 | JESSUP 1102 | 19.2725 | 237 | 0.18396 | 43.5983 | 389 | 4438.5564 | 12795.828 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
881 | RED BLUFF 11011556 | 103541101 | RED BLUFF 1101 | 38.4898 | 411 | 0.18357 | 75.4478 | 390 | 4477.0462 | 12720.3803 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
11061 | SAN LUIS OBISPO 1103365572 | 182631103 | SAN LUIS OBISPO 1103 | 0.38027 | 2 | 0.18299 | 0.36597 | 391 | 4477.4265 | 12720.0143 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6935 | CEDAR CREEK 1101CB | 103321101 | CEDAR CREEK 1101 | 15.4219 | 127 | 0.18254 | 23.1832 | 392 | 4492.8484 | 12696.8311 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3564 | JAMESON 1105466348 | 63801105 | JAMESON 1105 | 16.1835 | 294 | 0.18223 | 53.5743 | 393 | 4509.0319 | 12643.2568 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2550 | COTTONWOOD 110335470 | 102931103 | COTTONWOOD 1103 | 20.5787 | 174 | 0.18214 | 31.6926 | 394 | 4529.6106 | 12611.5642 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2265 | BELL 1108CB | 152701108 | BELL 1108 | 0 | 83 | 0.18213 | 15.1167 | 395 | 4529.6106 | 12596.4475 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6694 | POTTER VALLEY P H 110537476 | 42281105 | POTTER VALLEY P H 1105 | 2.63 | 82 | 0.18107 | 14.8479 | 396 | 4532.2406 | 12581.5996 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2442 | CORRAL 110112612 | 162991101 | CORRAL 1101 | 19.3235 | 195 | 0.18095 | 35.2855 | 397 | 4551.564 | 12546.3141 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2325 | COTTONWOOD 11011510 | 102931101 | COTTONWOOD 1101 | 0.38123 | 35 | 0.18088 | 6.3309 | 398 | 4551.9453 | 12539.9832 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6987 | TEMPLETON 2113641367 | 183052113 | TEMPLETON 2113 | 39.7012 | 278 | 0.18079 | 50.2607 | 399 | 4591.6465 | 12489.7225 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1077 | CLAYTON 2212Y504R | 12022212 | CLAYTON 2212 | 11.708 | 112 | 0.18021 | 20.1836 | 400 | 4603.3546 | 12469.5389 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6538 | DUNLAP 11027060 | 254061102 | DUNLAP 1102 | 17.8746 | 162 | 0.18019 | 29.1914 | 401 | 4621.2291 | 12440.3474 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8223 | POSO MOUNTAIN 210448268 | 253642104 | POSO MOUNTAIN 2104 | 5.0668 | 30 | 0.17977 | 5.3932 | 402 | 4626.296 | 12434.9542 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7847 | OILFIELDS 11032757 | 182391103 | OILFIELDS 1103 | 2.6245 | 16 | 0.1791 | 2.8656 | 403 | 4628.9205 | 12432.0886 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1905 | TIVY VALLEY 1107R1817 | 252941107 | TIVY VALLEY 1107 | 19.2848 | 145 | 0.17888 | 25.9373 | 404 | 4648.2053 | 12406.1513 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3840 | SAND CREEK 11037070 | 254601103 | SAND CREEK 1103 | 17.5579 | 103 | 0.17873 | 18.4097 | 405 | 4665.7632 | 12387.7417 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1011 | CALISTOGA 1101890 | 42711101 | CALISTOGA 1101 | 24.3702 | 203 | 0.17857 | 36.2505 | 406 | 4690.1334 | 12351.4912 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1851 | KONOCTI 1102CB | 43311102 | KONOCTI 1102 | 3.9318 | 97 | 0.1779 | 17.2565 | 407 | 4694.0653 | 12334.2347 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7708 | COLUMBIA HILL 110190730 | 152471101 | COLUMBIA HILL 1101 | 8.33 | 77 | 0.17712 | 13.6383 | 408 | 4702.3952 | 12320.5964 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10514 | SCE TEHACHAPI 1101CB | 258131101 | SCE TEHACHAPI 1101 | 1.1573 | 2 | 0.17665 | 0.3533 | 409 | 4703.5526 | 12320.2431 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5375 | TASSAJARA 2109CB | 14662109 | TASSAJARA 2109 | 1.9336 | 12 | 0.17607 | 2.1128 | 410 | 4705.4862 | 12318.1303 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8181 | APPLE HILL 210289934 | 153662102 | APPLE HILL 2102 | 5.5425 | 56 | 0.17581 | 9.8455 | 411 | 4711.0287 | 12308.2848 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3827 | HIGGINS 1109594 | 152691109 | HIGGINS 1109 | 14.3437 | 155 | 0.17563 | 27.2219 | 412 | 4725.3724 | 12281.0628 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
329 | CORNING 110253184 | 103331102 | CORNING 1102 | 31.8239 | 123 | 0.17544 | 21.5791 | 413 | 4757.1963 | 12259.4838 | 12259.4838 | #N/A | TRUE | 3.04 | FALSE | TRUE
6969 | PETALUMA C 1108208 | 42631108 | PETALUMA C 1108 | 12.4785 | 95 | 0.1754 | 16.663 | 414 | 4769.6748 | 12242.8208 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8229 | GARBERVILLE 11012026 | 192221101 | GARBERVILLE 1101 | 6.352 | 26 | 0.17512 | 4.5532 | 415 | 4776.0269 | 12238.2677 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8173 | ZACA 1101CB | 182681101 | ZACA 1101 | 7.4782 | 60 | 0.17499 | 10.4995 | 416 | 4783.5051 | 12227.7682 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5131 | PHILO 11013700 | 42601101 | PHILO 1101 | 18.1206 | 116 | 0.17472 | 20.2673 | 417 | 4801.6257 | 12207.5009 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
908 | PUTAH CREEK 1102710384 | 63681102 | PUTAH CREEK 1102 | 5.3351 | 84 | 0.17469 | 14.6739 | 418 | 4806.9608 | 12192.827 | 12192.827 | #N/A | TRUE | 5.34 | FALSE | TRUE
9983 | JAMESON 1105913400 | 63801105 | JAMESON 1105 | 0.10712 | 14 | 0.17457 | 2.444 | 419 | 4807.0679 | 12190.383 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6899 | FORT SEWARD 11211690 | 192321121 | FORT SEWARD 1121 | 10.8003 | 77 | 0.17449 | 13.4358 | 420 | 4817.8683 | 12176.9472 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2810 | OAKHURST 110110090 | 254421101 | OAKHURST 1101 | 44.0886 | 435 | 0.17437 | 75.8506 | 421 | 4861.9569 | 12101.0967 | 12101.0967 | #N/A | TRUE | 1.39 | TRUE | TRUE
8488 | BROWNS VALLEY 1101CB | 152921101 | BROWNS VALLEY 1101 | 2.2619 | 17 | 0.1743 | 2.9631 | 422 | 4864.2187 | 12098.1336 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1886 | REDBUD 1101323962 | 43191101 | REDBUD 1101 | 20.5821 | 282 | 0.17389 | 49.0357 | 423 | 4884.8008 | 12049.0979 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7655 | SHINGLE SPRINGS 210851476 | 153652108 | SHINGLE SPRINGS 2108 | 4.9262 | 74 | 0.1736 | 12.8462 | 424 | 4889.727 | 12036.2517 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6143 | OILFIELDS 1103N64 | 182391103 | OILFIELDS 1103 | 11.0139 | 101 | 0.17314 | 17.4874 | 425 | 4900.7409 | 12018.7643 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3312 | OLETA 11011217 | 163541101 | OLETA 1101 | 14.1973 | 116 | 0.17295 | 20.0623 | 426 | 4914.9382 | 11998.7021 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10420 | SANTA YNEZ 1101673618 | 182721101 | SANTA YNEZ 1101 | 0.10651 | 4 | 0.17294 | 0.69175 | 427 | 4915.0447 | 11998.0103 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
50 | MARIPOSA 210135244 | 254452101 | MARIPOSA 2101 | 17.4635 | 146 | 0.17286 | 25.237 | 428 | 4932.5082 | 11972.7733 | 11972.7733 | #N/A | TRUE | 0.84 | TRUE | TRUE
6824 | MARIPOSA 21021960 | 254452102 | MARIPOSA 2102 | 24.6717 | 223 | 0.17242 | 38.4488 | 429 | 4957.1798 | 11934.3245 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7293 | WISE 11022234 | 152271102 | WISE 1102 | 15.1336 | 179 | 0.17198 | 30.784 | 430 | 4972.3135 | 11903.5405 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6103 | CALPELLA 1102421412 | 43411102 | CALPELLA 1102 | 1.0045 | 38 | 0.17127 | 6.5083 | 431 | 4973.318 | 11897.0323 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8262 | DESCHUTES 11019722 | 103351101 | DESCHUTES 1101 | 3.1941 | 55 | 0.17084 | 9.3959 | 432 | 4976.5121 | 11887.6363 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3350 | OAKHURST 110310570 | 254421103 | OAKHURST 1103 | 9.5965 | 92 | 0.17053 | 15.6885 | 433 | 4986.1086 | 11871.9478 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7252 | OILFIELDS 1103N42 | 182391103 | OILFIELDS 1103 | 3.7274 | 30 | 0.17017 | 5.105 | 434 | 4989.836 | 11866.8428 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2738 | SAN BENITO 2101221165 | 182742101 | SAN BENITO 2101 | 4.3859 | 39 | 0.17016 | 6.6364 | 435 | 4994.2219 | 11860.2064 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10162 | MADISON 210113372 | 63172101 | MADISON 2101 | 3.8236 | 5 | 0.17014 | 0.85069 | 436 | 4998.0455 | 11859.3557 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4788 | COTTONWOOD 11039072 | 102931103 | COTTONWOOD 1103 | 28.8029 | 279 | 0.1698 | 47.3736 | 437 | 5026.8484 | 11811.9821 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10660 | CLAYTON 2212334476 | 12022212 | CLAYTON 2212 | 0.0559 | 2 | 0.16961 | 0.33922 | 438 | 5026.9043 | 11811.6428 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5708 | HARTLEY 1101658 | 43211101 | HARTLEY 1101 | 2.8348 | 136 | 0.16943 | 23.042 | 439 | 5029.7391 | 11788.6009 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
52 | HIGHLANDS 1103520 | 43361103 | HIGHLANDS 1103 | 46.6894 | 437 | 0.16915 | 73.9165 | 440 | 5076.4285 | 11714.6843 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5485 | ZACA 1102CB | 182681102 | ZACA 1102 | 15.6783 | 190 | 0.16908 | 32.1248 | 441 | 5092.1067 | 11682.5595 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2709 | CHOLAME 2102X10 | 182562102 | CHOLAME 2102 | 21.4267 | 156 | 0.16893 | 26.3532 | 442 | 5113.5335 | 11656.2063 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2509 | HIGGINS 111051794 | 152691110 | HIGGINS 1110 | 3.9179 | 32 | 0.16883 | 5.4026 | 443 | 5117.4513 | 11650.8036 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3144 | MORGAN HILL 2105XR564 | 83242105 | MORGAN HILL 2105 | 5.6724 | 81 | 0.16792 | 13.6018 | 444 | 5123.1237 | 11637.2018 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8832 | PEORIA 17046090 | 163781704 | PEORIA 1704 | 0.54664 | 10 | 0.16726 | 1.6726 | 445 | 5123.6703 | 11635.5292 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6712 | CORNING 110182846 | 103331101 | CORNING 1101 | 4.7401 | 61 | 0.16626 | 10.1421 | 446 | 5128.4104 | 11625.3871 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3069 | NARROWS 21052228 | 153132105 | NARROWS 2105 | 20.9616 | 199 | 0.16595 | 33.0243 | 447 | 5149.372 | 11592.3628 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10116 | SANTA YNEZ 1104117616 | 182721104 | SANTA YNEZ 1104 | 0.18542 | 5 | 0.16564 | 0.82819 | 448 | 5149.5574 | 11591.5346 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10070 | SILVERADO 2102772792 | 43432102 | SILVERADO 2102 | 2.3506 | 19 | 0.16509 | 3.1366 | 449 | 5151.908 | 11588.398 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6113 | MIDDLETOWN 1101439572 | 43141101 | MIDDLETOWN 1101 | 1.229 | 18 | 0.16479 | 2.9663 | 450 | 5153.1369 | 11585.4317 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1940 | NORTH BRANCH 1101TS1115 | 163231101 | NORTH BRANCH 1101 | 17.6137 | 147 | 0.16462 | 24.1996 | 451 | 5170.7507 | 11561.2321 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7043 | ANDERSON 1101514412 | 103261101 | ANDERSON 1101 | 1.0314 | 5 | 0.16405 | 0.82024 | 452 | 5171.7821 | 11560.4118 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7318 | PUEBLO 2102226562 | 43292102 | PUEBLO 2102 | 0.8527 | 7 | 0.16403 | 1.1482 | 453 | 5172.6348 | 11559.2636 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9693 | WILDWOOD 110198896 | 103611101 | WILDWOOD 1101 | 5.0283 | 25 | 0.16402 | 4.1004 | 454 | 5177.6631 | 11555.1632 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8907 | SHINGLE SPRINGS 1103CB | 153651103 | SHINGLE SPRINGS 1103 | 6.6178 | 143 | 0.16378 | 23.42 | 455 | 5184.2809 | 11531.7432 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3737 | KESWICK 110148480 | 103451101 | KESWICK 1101 | 10.5208 | 125 | 0.16355 | 20.4433 | 456 | 5194.8017 | 11511.2999 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9178 | CORNING 1102915324 | 103331102 | CORNING 1102 | 2.228 | 27 | 0.16319 | 4.406 | 457 | 5197.0297 | 11506.8939 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9985 | BOLINAS 1101530 | 42261101 | BOLINAS 1101 | 10.9659 | 23 | 0.16273 | 3.7427 | 458 | 5207.9956 | 11503.1512 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10086 | NAPA 1102561208 | 42021102 | NAPA 1102 | 0.8375 | 15 | 0.1626 | 2.439 | 459 | 5208.8331 | 11500.7122 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7995 | HOPLAND 110194006 | 42251101 | HOPLAND 1101 | 13.8855 | 112 | 0.1626 | 18.2107 | 460 | 5222.7186 | 11482.5015 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5192 | HIGHLANDS 1103CB | 43361103 | HIGHLANDS 1103 | 10.5955 | 144 | 0.16238 | 23.3827 | 461 | 5233.3141 | 11459.1188 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10927 | SCE REFUGIO 1701CB | 188071701 | SCE REFUGIO 1701 | 0.0022454 | 1 | 0.16185 | 0.16185 | 462 | 5233.3164 | 11458.957 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1961 | NARROWS 210534069 | 153132105 | NARROWS 2105 | 15.7438 | 156 | 0.16138 | 25.1758 | 463 | 5249.0602 | 11433.7812 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
11018 | CLAY 110398680 | 163341103 | CLAY 1103 | 0.02896 | 1 | 0.16135 | 0.16135 | 464 | 5249.0892 | 11433.6198 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5283 | ANDERSON 11011752 | 103261101 | ANDERSON 1101 | 8.4222 | 96 | 0.16096 | 15.4521 | 465 | 5257.5114 | 11418.1677 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4672 | LOW GAP 110137498 | 192411101 | LOW GAP 1101 | 16.282 | 129 | 0.16073 | 20.7336 | 466 | 5273.7934 | 11397.4341 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1841 | NARROWS 21057203 | 153132105 | NARROWS 2105 | 18.5859 | 197 | 0.16043 | 31.6051 | 467 | 5292.3793 | 11365.8291 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
652 | MIDDLETOWN 110148212 | 43141101 | MIDDLETOWN 1101 | 10.6994 | 110 | 0.1603 | 17.6327 | 468 | 5303.0787 | 11348.1963 | 11348.1963 | #N/A | TRUE | 15.3455 | TRUE | TRUE
1128 | SAN MIGUEL 1106605393 | 182661106 | SAN MIGUEL 1106 | 20.7432 | 119 | 0.15998 | 19.0373 | 469 | 5323.8219 | 11329.1591 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3473 | COTTONWOOD 11011610 | 102931101 | COTTONWOOD 1101 | 38.4226 | 295 | 0.15996 | 47.1875 | 470 | 5362.2445 | 11281.9716 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1571 | SAN MIGUEL 1106428314 | 182661106 | SAN MIGUEL 1106 | 14.7129 | 73 | 0.15993 | 11.675 | 471 | 5376.9574 | 11270.2966 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6359 | FROGTOWN 1702592404 | 163451702 | FROGTOWN 1702 | 1.6422 | 20 | 0.15963 | 3.1926 | 472 | 5378.5996 | 11267.104 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7337 | WYANDOTTE 110738438 | 102911107 | WYANDOTTE 1107 | 16.8604 | 181 | 0.15947 | 28.8637 | 473 | 5395.46 | 11238.2402 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
932 | MIDDLETOWN 1101548 | 43141101 | MIDDLETOWN 1101 | 27.4082 | 298 | 0.15935 | 47.4878 | 474 | 5422.8682 | 11190.7525 | 11190.7525 | #N/A | TRUE | 28.3644 | TRUE | TRUE
9379 | SUNOL 11018721 | 14241101 | SUNOL 1101 | 2.7351 | 29 | 0.1593 | 4.6198 | 475 | 5425.6033 | 11186.1327 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1763 | RED BLUFF 110451238 | 103541104 | RED BLUFF 1104 | 39.2404 | 335 | 0.15926 | 53.3509 | 476 | 5464.8437 | 11132.7818 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1814 | CLOVERDALE 110184088 | 42821101 | CLOVERDALE 1101 | 16.1366 | 127 | 0.15858 | 20.1391 | 477 | 5480.9803 | 11112.6427 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4306 | RAWSON 1103428534 | 103531103 | RAWSON 1103 | 4.5381 | 18 | 0.15819 | 2.8474 | 478 | 5485.5183 | 11109.7952 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8922 | CLOVERDALE 1101964556 | 42821101 | CLOVERDALE 1101 | 5.0445 | 31 | 0.15803 | 4.8988 | 479 | 5490.5628 | 11104.8964 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7447 | BELL 1109CB | 152701109 | BELL 1109 | 0.30133 | 53 | 0.15794 | 8.3708 | 480 | 5490.8641 | 11096.5256 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5391 | FITCH MOUNTAIN 111324918 | 42751113 | FITCH MOUNTAIN 1113 | 5.4965 | 49 | 0.1575 | 7.7177 | 481 | 5496.3606 | 11088.8079 | 11088.8079 | #N/A | TRUE | 4.4858 | TRUE | TRUE
6800 | GEYSERVILLE 1101705777 | 42891101 | GEYSERVILLE 1101 | 6.1467 | 46 | 0.15746 | 7.2434 | 482 | 5502.5073 | 11081.5646 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
29 | CALPELLA 1101542 | 43411101 | CALPELLA 1101 | 33.5352 | 311 | 0.15746 | 48.9707 | 483 | 5536.0426 | 11032.5939 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9538 | PIT NO 1 1101CB | 103721101 | PIT NO 1 1101 | 6.5478 | 40 | 0.15705 | 6.2822 | 484 | 5542.5904 | 11026.3117 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7813 | CLOVERDALE 1102383183 | 42821102 | CLOVERDALE 1102 | 14.6467 | 53 | 0.15687 | 8.3141 | 485 | 5557.2371 | 11017.9977 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8188 | LAKEVILLE 1102152632 | 43371102 | LAKEVILLE 1102 | 1.9263 | 13 | 0.15681 | 2.0385 | 486 | 5559.1634 | 11015.9592 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5065 | WOODACRE 11011456 | 43021101 | WOODACRE 1101 | 3.8256 | 46 | 0.15596 | 7.1739 | 487 | 5562.989 | 11008.7852 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5726 | POINT MORETTI 11015104 | 82931101 | POINT MORETTI 1101 | 1.8014 | 11 | 0.15579 | 1.7137 | 488 | 5564.7904 | 11007.0715 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3142 | MOLINO 110279306 | 42571102 | MOLINO 1102 | 3.7837 | 73 | 0.15551 | 11.352 | 489 | 5568.5741 | 10995.7194 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10072 | BALCH NO 1 1101R372 | 252501101 | BALCH NO 1 1101 | 4.1665 | 14 | 0.15539 | 2.1754 | 490 | 5572.7406 | 10993.544 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1776 | TIVY VALLEY 1107869946 | 252941107 | TIVY VALLEY 1107 | 29.7395 | 197 | 0.15534 | 30.6024 | 491 | 5602.4801 | 10962.9417 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9099 | BELL 1110946229 | 152701110 | BELL 1110 | 0.21901 | 27 | 0.15489 | 4.1819 | 492 | 5602.6991 | 10958.7597 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
11045 | CLARK ROAD 1101CB | 103091101 | CLARK ROAD 1101 | 0.017868 | 2 | 0.15464 | 0.30929 | 493 | 5602.717 | 10958.4504 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1243 | SHINGLE SPRINGS 110419502 | 153651104 | SHINGLE SPRINGS 1104 | 44.9701 | 672 | 0.15447 | 103.8019 | 494 | 5647.6872 | 10854.6485 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3579 | WILLITS 1102CB | 42661102 | WILLITS 1102 | 5.3142 | 114 | 0.15412 | 17.5695 | 495 | 5653.0014 | 10837.0791 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6413 | UKIAH 1114408 | 42771114 | UKIAH 1114 | 37.319 | 280 | 0.15401 | 43.1236 | 496 | 5690.3204 | 10793.9554 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4125 | SAND CREEK 11037420 | 254601103 | SAND CREEK 1103 | 23.1951 | 263 | 0.15397 | 40.4954 | 497 | 5713.5154 | 10753.4601 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6897 | SALMON CREEK 110188998 | 43161101 | SALMON CREEK 1101 | 7.9521 | 116 | 0.15352 | 17.8079 | 498 | 5721.4675 | 10735.6522 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4452 | SILVERADO 2102942170 | 43432102 | SILVERADO 2102 | 3.1315 | 99 | 0.15348 | 15.1945 | 499 | 5724.5991 | 10720.4577 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
59 | VACAVILLE 1111CB | 63601111 | VACAVILLE 1111 | 7.3197 | 154 | 0.15336 | 23.6178 | 500 | 5731.9188 | 10696.8399 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5605 | SANTA YNEZ 1101Y52 | 182721101 | SANTA YNEZ 1101 | 19.5955 | 141 | 0.15332 | 21.6184 | 501 | 5751.5143 | 10675.2215 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4437 | STILLWATER 1102CB | 103561102 | STILLWATER 1102 | 25.0474 | 275 | 0.15318 | 42.1242 | 502 | 5776.5617 | 10633.0973 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3264 | BEAR VALLEY 21059480 | 252192105 | BEAR VALLEY 2105 | 12.4123 | 80 | 0.15314 | 12.251 | 503 | 5788.974 | 10620.8463 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1519 | FROGTOWN 17021573 | 163451702 | FROGTOWN 1702 | 18.0653 | 156 | 0.15282 | 23.8402 | 504 | 5807.0393 | 10597.0062 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1732 | NARROWS 21022220 | 153132102 | NARROWS 2102 | 27.4869 | 266 | 0.15235 | 40.5244 | 505 | 5834.5262 | 10556.4817 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2529 | FULTON 1102287172 | 42561102 | FULTON 1102 | 20.4403 | 258 | 0.15216 | 39.2578 | 506 | 5854.9666 | 10517.2239 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9038 | OTTER 11022012 | 182941102 | OTTER 1102 | 9.2069 | 64 | 0.15189 | 9.7211 | 507 | 5864.1734 | 10507.5028 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6205 | OILFIELDS 1103N48 | 182391103 | OILFIELDS 1103 | 47.6716 | 292 | 0.15188 | 44.3489 | 508 | 5911.8451 | 10463.1538 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6912 | BANGOR 1101301886 | 103191101 | BANGOR 1101 | 2.635 | 90 | 0.15165 | 13.6484 | 509 | 5914.48 | 10449.5055 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10865 | PASO ROBLES 1103N04 | 182611103 | PASO ROBLES 1103 | 0.53424 | 4 | 0.1516 | 0.60641 | 510 | 5915.0143 | 10448.899 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10126 | WINDSOR 1103701650 | 43501103 | WINDSOR 1103 | 0.74025 | 12 | 0.15159 | 1.8191 | 511 | 5915.7545 | 10447.0799 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2118 | LUCERNE 11031280 | 43351103 | LUCERNE 1103 | 8.0384 | 238 | 0.1512 | 35.9845 | 512 | 5923.7929 | 10411.0954 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7467 | CORRAL 110214026 | 162991102 | CORRAL 1102 | 10.1358 | 101 | 0.15084 | 15.2344 | 513 | 5933.9287 | 10395.861 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2447 | SAN LUIS OBISPO 110342344 | 182631103 | SAN LUIS OBISPO 1103 | 9.438 | 123 | 0.15077 | 18.5441 | 514 | 5943.3667 | 10377.3169 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9162 | PUTAH CREEK 1105748272 | 63681105 | PUTAH CREEK 1105 | 0.74961 | 26 | 0.15028 | 3.9074 | 515 | 5944.1163 | 10373.4095 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6146 | PETALUMA C 1108618 | 42631108 | PETALUMA C 1108 | 8.6329 | 119 | 0.15 | 17.8498 | 516 | 5952.7492 | 10355.5597 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7759 | BUELLTON 1101Y26 | 183041101 | BUELLTON 1101 | 15.1717 | 133 | 0.14946 | 19.8785 | 517 | 5967.9208 | 10335.6812 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8614 | WILLOW CREEK 110237374 | 192171102 | WILLOW CREEK 1102 | 2.2478 | 9 | 0.14938 | 1.3444 | 518 | 5970.1686 | 10334.3367 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1351 | FULTON 11024522 | 42561102 | FULTON 1102 | 8.8123 | 128 | 0.14919 | 19.0963 | 519 | 5978.9809 | 10315.2405 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5116 | APPLE HILL 210251792 | 153662102 | APPLE HILL 2102 | 9.3569 | 99 | 0.14914 | 14.7646 | 520 | 5988.3378 | 10300.4759 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2803 | ZACA 1102Y48 | 182681102 | ZACA 1102 | 4.3905 | 157 | 0.14907 | 23.4041 | 521 | 5992.7283 | 10277.0719 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
453 | GARBERVILLE 11011604 | 192221101 | GARBERVILLE 1101 | 4.1852 | 166 | 0.14905 | 24.7419 | 522 | 5996.9134 | 10252.33 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10386 | CALISTOGA 1101537148 | 42711101 | CALISTOGA 1101 | 0.5737 | 14 | 0.14902 | 2.0863 | 523 | 5997.4871 | 10250.2436 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1087 | GRASS VALLEY 11032180 | 152031103 | GRASS VALLEY 1103 | 44.1964 | 444 | 0.1487 | 66.0238 | 524 | 6041.6836 | 10184.2198 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6232 | POSO MOUNTAIN 21012181 | 253642101 | POSO MOUNTAIN 2101 | 16.8531 | 120 | 0.14869 | 17.8426 | 525 | 6058.5367 | 10166.3773 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1083 | CLARK ROAD 11022044 | 103091102 | CLARK ROAD 1102 | 8.5077 | 67 | 0.14865 | 9.9595 | 526 | 6067.0444 | 10156.4177 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1119 | MERCED FALLS 110287352 | 252811102 | MERCED FALLS 1102 | 26.6195 | 215 | 0.14862 | 31.9523 | 527 | 6093.6639 | 10124.4654 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3359 | WISE 1102307494 | 152271102 | WISE 1102 | 31.0496 | 279 | 0.14841 | 41.4062 | 528 | 6124.7134 | 10083.0592 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8461 | PUTAH CREEK 110264044 | 63681102 | PUTAH CREEK 1102 | 5.9969 | 46 | 0.14834 | 6.8236 | 529 | 6130.7103 | 10076.2356 | 10076.2356 | #N/A | TRUE | 6 | FALSE | TRUE
7436 | MENLO 110212249 | 24131102 | MENLO 1102 | 2.4049 | 25 | 0.14826 | 3.7065 | 530 | 6133.1153 | 10072.5291 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
170 | NORTH BRANCH 110111206 | 163231101 | NORTH BRANCH 1101 | 17.8882 | 146 | 0.14787 | 21.5893 | 531 | 6151.0035 | 10050.9398 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2440 | VOLTA 110180454 | 102541101 | VOLTA 1101 | 31.8338 | 254 | 0.14786 | 37.5574 | 532 | 6182.8373 | 10013.3824 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6322 | SALMON CREEK 1101196 | 43161101 | SALMON CREEK 1101 | 5.6122 | 36 | 0.14755 | 5.3118 | 533 | 6188.4495 | 10008.0706 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6558 | MOLINO 110266006 | 42571102 | MOLINO 1102 | 9.0433 | 98 | 0.14747 | 14.4519 | 534 | 6197.4928 | 9993.6188 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6860 | GARBERVILLE 1101CB | 192221101 | GARBERVILLE 1101 | 7.023 | 87 | 0.14742 | 12.8257 | 535 | 6204.5158 | 9980.793 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2892 | WYANDOTTE 11071026 | 102911107 | WYANDOTTE 1107 | 22.4808 | 273 | 0.14732 | 40.2177 | 536 | 6226.9966 | 9940.5753 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1817 | COARSEGOLD 210410110 | 254432104 | COARSEGOLD 2104 | 49.621 | 518 | 0.1471 | 76.1986 | 537 | 6276.6176 | 9864.3767 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5315 | GIRVAN 11011636 | 103401101 | GIRVAN 1101 | 18.0679 | 200 | 0.14693 | 29.387 | 538 | 6294.6854 | 9834.9897 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7739 | OILFIELDS 1103N40 | 182391103 | OILFIELDS 1103 | 2.8763 | 23 | 0.14681 | 3.3766 | 539 | 6297.5618 | 9831.6131 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1598 | COTTONWOOD 11031348 | 102931103 | COTTONWOOD 1103 | 29.1887 | 357 | 0.14666 | 52.3583 | 540 | 6326.7505 | 9779.2548 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2008 | OAKHURST 11015490 | 254421101 | OAKHURST 1101 | 25.0102 | 276 | 0.14657 | 40.4521 | 541 | 6351.7607 | 9738.8027 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6294 | OLETA 1101239062 | 163541101 | OLETA 1101 | 12.193 | 113 | 0.14634 | 16.5367 | 542 | 6363.9537 | 9722.266 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6920 | LAYTONVILLE 110268436 | 42681102 | LAYTONVILLE 1102 | 9.1143 | 45 | 0.14627 | 6.582 | 543 | 6373.068 | 9715.684 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1698 | GARBERVILLE 11022010 | 192221102 | GARBERVILLE 1102 | 6.6674 | 39 | 0.14585 | 5.6882 | 544 | 6379.7355 | 9709.9958 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2911 | SHINGLE SPRINGS 210819762 | 153652108 | SHINGLE SPRINGS 2108 | 4.3995 | 72 | 0.14549 | 10.4755 | 545 | 6384.135 | 9699.5204 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2598 | ELK CREEK 11012008 | 102781101 | ELK CREEK 1101 | 5.734 | 154 | 0.14517 | 22.3567 | 546 | 6389.8689 | 9677.1637 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2127 | OILFIELDS 1103N44 | 182391103 | OILFIELDS 1103 | 18.1527 | 109 | 0.14496 | 15.8008 | 547 | 6408.0217 | 9661.3629 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
381 | MOUNTAIN QUARRIES 21011102 | 152282101 | MOUNTAIN QUARRIES 2101 | 43.4367 | 431 | 0.14479 | 62.4048 | 548 | 6451.4583 | 9598.9582 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3913 | CORNING 110164090 | 103331101 | CORNING 1101 | 13.6692 | 170 | 0.1444 | 24.5486 | 549 | 6465.1275 | 9574.4096 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2481 | BROWNS VALLEY 11011268 | 152921101 | BROWNS VALLEY 1101 | 10.9003 | 106 | 0.14435 | 15.3013 | 550 | 6476.0278 | 9559.1083 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
948 | MARIPOSA 21029590 | 254452102 | MARIPOSA 2102 | 36.2878 | 387 | 0.144 | 55.7277 | 551 | 6512.3156 | 9503.3806 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4109 | TEMPLETON 2113A60 | 183052113 | TEMPLETON 2113 | 7.2773 | 88 | 0.14391 | 12.6644 | 552 | 6519.5929 | 9490.7162 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9361 | CLOVERDALE 1102429006 | 42821102 | CLOVERDALE 1102 | 1.9972 | 23 | 0.1436 | 3.3029 | 553 | 6521.59 | 9487.4133 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
429 | COTTONWOOD 11021578 | 102931102 | COTTONWOOD 1102 | 30.142 | 269 | 0.14355 | 38.6147 | 554 | 6551.732 | 9448.7986 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3755 | INDIAN FLAT 1104CB | 252691104 | INDIAN FLAT 1104 | 12.7765 | 85 | 0.14347 | 12.1951 | 555 | 6564.5085 | 9436.6035 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5039 | OREGON TRAIL 11031448 | 103521103 | OREGON TRAIL 1103 | 30.7551 | 232 | 0.14347 | 33.2848 | 556 | 6595.2636 | 9403.3187 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5385 | MONTICELLO 110137384 | 43051101 | MONTICELLO 1101 | 9.3736 | 71 | 0.14324 | 10.17 | 557 | 6604.6372 | 9393.1487 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9323 | POSO MOUNTAIN 21013990 | 253642101 | POSO MOUNTAIN 2101 | 4.3279 | 25 | 0.14297 | 3.5744 | 558 | 6608.9651 | 9389.5744 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8609 | PETALUMA C 1108636 | 42631108 | PETALUMA C 1108 | 9.4338 | 108 | 0.14279 | 15.4213 | 559 | 6618.3989 | 9374.1531 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9301 | VOLTA 110165764 | 102541101 | VOLTA 1101 | 10.3601 | 34 | 0.1423 | 4.8382 | 560 | 6628.759 | 9369.3149 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10478 | STONE CORRAL 1110189488 | 252921110 | STONE CORRAL 1110 | 0.8249 | 8 | 0.14211 | 1.1369 | 561 | 6629.5839 | 9368.178 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1096 | CABRILLO 1103Y12 | 183101103 | CABRILLO 1103 | 26.5393 | 274 | 0.14205 | 38.9225 | 562 | 6656.1232 | 9329.2556 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9878 | CEDAR CREEK 1101451856 | 103321101 | CEDAR CREEK 1101 | 0.065349 | 2 | 0.14172 | 0.28345 | 563 | 6656.1886 | 9328.9721 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9745 | TASSAJARA 21126392 | 14662112 | TASSAJARA 2112 | 5.4935 | 37 | 0.14162 | 5.2399 | 564 | 6661.682 | 9323.7322 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4697 | CALISTOGA 1101242919 | 42711101 | CALISTOGA 1101 | 1.3123 | 15 | 0.14151 | 2.1226 | 565 | 6662.9943 | 9321.6095 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5376 | FORT SEWARD 1121CB | 192321121 | FORT SEWARD 1121 | 9.2029 | 54 | 0.14139 | 7.6353 | 566 | 6672.1973 | 9313.9743 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4876 | SISQUOC 1102M54 | 182811102 | SISQUOC 1102 | 19.8162 | 166 | 0.14114 | 23.4289 | 567 | 6692.0135 | 9290.5454 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4881 | LINCOLN 11042070 | 153701104 | LINCOLN 1104 | 17.9936 | 303 | 0.14111 | 42.7554 | 568 | 6710.007 | 9247.7901 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8866 | SAN RAMON 2101CB | 14232101 | SAN RAMON 2101 | 0.79388 | 11 | 0.14108 | 1.5519 | 569 | 6710.8009 | 9246.2382 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10487 | HIGGINS 1107746082 | 152691107 | HIGGINS 1107 | 0.81177 | 6 | 0.14016 | 0.84097 | 570 | 6711.6127 | 9245.3972 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3139 | WILLITS 11044650 | 42661104 | WILLITS 1104 | 3.8474 | 80 | 0.14007 | 11.2058 | 571 | 6715.4601 | 9234.1914 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
474 | COTTONWOOD 11031616 | 102931103 | COTTONWOOD 1103 | 46.9461 | 454 | 0.13915 | 63.1735 | 572 | 6762.4062 | 9171.0179 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4424 | POSO MOUNTAIN 21014456 | 253642101 | POSO MOUNTAIN 2101 | 23.5315 | 102 | 0.13881 | 14.1582 | 573 | 6785.9377 | 9156.8597 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7546 | LAYTONVILLE 11022502 | 42681102 | LAYTONVILLE 1102 | 17.8061 | 80 | 0.13859 | 11.0874 | 574 | 6803.7438 | 9145.7723 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7849 | BEAR VALLEY 21014160 | 252192101 | BEAR VALLEY 2101 | 22.8241 | 192 | 0.13839 | 26.57 | 575 | 6826.5679 | 9119.2023 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10064 | WILLOW PASS 1101152874 | 13911101 | WILLOW PASS 1101 | 0.61051 | 10 | 0.13803 | 1.3803 | 576 | 6827.1784 | 9117.822 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2621 | LINCOLN 1101186060 | 153701101 | LINCOLN 1101 | 10.9028 | 161 | 0.13732 | 22.1085 | 577 | 6838.0812 | 9095.7135 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5254 | SHINGLE SPRINGS 21092679 | 153652109 | SHINGLE SPRINGS 2109 | 7.1071 | 70 | 0.13732 | 9.6123 | 578 | 6845.1883 | 9086.1012 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3959 | SILVERADO 210234959 | 43432102 | SILVERADO 2102 | 25.7758 | 205 | 0.13657 | 27.9958 | 579 | 6870.9641 | 9058.1054 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4389 | VOLTA 11011516 | 102541101 | VOLTA 1101 | 25.3925 | 123 | 0.13616 | 16.7471 | 580 | 6896.3566 | 9041.3583 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9812 | CURTIS 170411300 | 163351704 | CURTIS 1704 | 3.6748 | 41 | 0.1361 | 5.5803 | 581 | 6900.0314 | 9035.778 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4676 | NARROWS 210551582 | 153132105 | NARROWS 2105 | 9.5278 | 105 | 0.13574 | 14.2523 | 582 | 6909.5592 | 9021.5257 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
430 | TEJON 1102732836 | 252931102 | TEJON 1102 | 11.6772 | 154 | 0.1353 | 20.8364 | 583 | 6921.2364 | 9000.6893 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4932 | MONTICELLO 1101720 | 43051101 | MONTICELLO 1101 | 6.7891 | 70 | 0.1353 | 9.4707 | 584 | 6928.0255 | 8991.2186 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6310 | RIO DELL 11024230 | 192251102 | RIO DELL 1102 | 22.9009 | 59 | 0.13512 | 7.9721 | 585 | 6950.9265 | 8983.2465 | 8983.2465 | #N/A | TRUE | 2.8937 | FALSE | TRUE
517 | CLARKSVILLE 210413352 | 153612104 | CLARKSVILLE 2104 | 34.7401 | 409 | 0.13486 | 55.1568 | 586 | 6985.6666 | 8928.0897 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7402 | MARIPOSA 2102594143 | 254452102 | MARIPOSA 2102 | 0.50625 | 60 | 0.13461 | 8.0769 | 587 | 6986.1728 | 8920.0128 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
19 | CLEAR LAKE 1101406 | 42141101 | CLEAR LAKE 1101 | 12.4205 | 312 | 0.1343 | 41.9011 | 588 | 6998.5934 | 8878.1117 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4720 | DUNLAP 11027849F | 254061102 | DUNLAP 1102 | 8.6698 | 61 | 0.13395 | 8.1711 | 589 | 7007.2631 | 8869.9406 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6125 | JESSUP 1103348657 | 103441103 | JESSUP 1103 | 2.0223 | 29 | 0.13388 | 3.8825 | 590 | 7009.2854 | 8866.0581 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9100 | BANGOR 1101870548 | 103191101 | BANGOR 1101 | 5.0876 | 56 | 0.13326 | 7.4625 | 591 | 7014.373 | 8858.5956 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7774 | RED BLUFF 110176020 | 103541101 | RED BLUFF 1101 | 9.3423 | 137 | 0.13318 | 18.2456 | 592 | 7023.7153 | 8840.35 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5975 | HARTLEY 11011306 | 43211101 | HARTLEY 1101 | 9.4843 | 117 | 0.13303 | 15.5648 | 593 | 7033.1996 | 8824.7852 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3100 | GARBERVILLE 11022540 | 192221102 | GARBERVILLE 1102 | 16.2351 | 135 | 0.13296 | 17.9496 | 594 | 7049.4348 | 8806.8356 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9542 | OLETA 1102CB | 163541102 | OLETA 1102 | 0.3708 | 11 | 0.13274 | 1.4601 | 595 | 7049.8056 | 8805.3755 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6900 | SALT SPRINGS 210110416 | 163692101 | SALT SPRINGS 2101 | 0.68999 | 7 | 0.1325 | 0.92748 | 596 | 7050.4956 | 8804.448 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1019 | HOPLAND 1101770 | 42251101 | HOPLAND 1101 | 8.6005 | 110 | 0.13217 | 14.5382 | 597 | 7059.096 | 8789.9098 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9774 | WILDWOOD 1101384582 | 103611101 | WILDWOOD 1101 | 4.5397 | 8 | 0.13184 | 1.0547 | 598 | 7063.6357 | 8788.8551 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6290 | WYANDOTTE 110796390 | 102911107 | WYANDOTTE 1107 | 8.5479 | 124 | 0.13125 | 16.2749 | 599 | 7072.1836 | 8772.5802 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8217 | VINEYARD 2110CB | 14502110 | VINEYARD 2110 | 5.5901 | 86 | 0.1308 | 11.2491 | 600 | 7077.7737 | 8761.3311 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7155 | PEORIA 1701CB | 163781701 | PEORIA 1701 | 8.7743 | 70 | 0.13063 | 9.1442 | 601 | 7086.548 | 8752.1869 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1707 | HIGGINS 11039753 | 152691103 | HIGGINS 1103 | 2.0548 | 23 | 0.13059 | 3.0036 | 602 | 7088.6028 | 8749.1833 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10679 | COVELO 1101627416 | 43061101 | COVELO 1101 | 0.6038 | 14 | 0.13024 | 1.8234 | 603 | 7089.2066 | 8747.3599 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2248 | CORRAL 110313474 | 162991103 | CORRAL 1103 | 2.9373 | 99 | 0.13001 | 12.8713 | 604 | 7092.1439 | 8734.4886 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6056 | MARIPOSA 2101309438 | 254452101 | MARIPOSA 2101 | 3.6909 | 93 | 0.12966 | 12.0584 | 605 | 7095.8347 | 8722.4301 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5806 | COLUMBIA HILL 11012212 | 152471101 | COLUMBIA HILL 1101 | 9.1336 | 76 | 0.12922 | 9.8207 | 606 | 7104.9684 | 8712.6094 | #N/A | 8712.6094 | FALSE | 0 | TRUE | TRUE
5628 | PUEBLO 11041304 | 43291104 | PUEBLO 1104 | 19.2267 | 175 | 0.12902 | 22.578 | 607 | 7124.195 | 8690.0314 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5578 | VASCO 1102886522 | 13751102 | VASCO 1102 | 6.7797 | 154 | 0.12899 | 19.8644 | 608 | 7130.9747 | 8670.167 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2390 | WYANDOTTE 11091520 | 102911109 | WYANDOTTE 1109 | 4.1643 | 230 | 0.1287 | 29.6011 | 609 | 7135.139 | 8640.5659 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2104 | LINCOLN 11045391 | 153701104 | LINCOLN 1104 | 0.95101 | 7 | 0.12868 | 0.90075 | 610 | 7136.09 | 8639.6651 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
826 | TASSAJARA 210419042 | 14662104 | TASSAJARA 2104 | 6.2584 | 89 | 0.12861 | 11.4466 | 611 | 7142.3484 | 8628.2185 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7172 | FITCH MOUNTAIN 1113356 | 42751113 | FITCH MOUNTAIN 1113 | 10.7179 | 136 | 0.12847 | 17.4723 | 612 | 7153.0663 | 8610.7463 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
761 | BANGOR 11017446 | 103191101 | BANGOR 1101 | 43.5002 | 427 | 0.12828 | 54.7764 | 613 | 7196.5665 | 8555.9699 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9800 | CALISTOGA 110135588 | 42711101 | CALISTOGA 1101 | 3.0795 | 18 | 0.12786 | 2.3016 | 614 | 7199.646 | 8553.6683 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9664 | PASO ROBLES 110359763 | 182611103 | PASO ROBLES 1103 | 2.8168 | 30 | 0.12716 | 3.8149 | 615 | 7202.4628 | 8549.8533 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5583 | RED BLUFF 11031702 | 103541103 | RED BLUFF 1103 | 16.7546 | 177 | 0.12716 | 22.5069 | 616 | 7219.2174 | 8527.3465 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4955 | WILLITS 1104188268 | 42661104 | WILLITS 1104 | 4.2682 | 66 | 0.1264 | 8.3425 | 617 | 7223.4856 | 8519.004 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9342 | SAND CREEK 11037823F | 254601103 | SAND CREEK 1103 | 4.6783 | 49 | 0.12636 | 6.1917 | 618 | 7228.1639 | 8512.8123 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7895 | PEORIA 1704877670 | 163781704 | PEORIA 1704 | 6.585 | 28 | 0.12626 | 3.5352 | 619 | 7234.7489 | 8509.2772 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1593 | MENLO 1102W80 | 24131102 | MENLO 1102 | 18.9504 | 129 | 0.12598 | 16.2519 | 620 | 7253.6993 | 8493.0253 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9134 | SAN LUIS OBISPO 1104350030 | 182631104 | SAN LUIS OBISPO 1104 | 5.7957 | 107 | 0.12598 | 13.4795 | 621 | 7259.495 | 8479.5457 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10634 | EDENVALE 2107288980 | 82952107 | EDENVALE 2107 | 0.33085 | 6 | 0.12531 | 0.75188 | 622 | 7259.8259 | 8478.7939 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8835 | SOLEDAD 2102955138 | 182052102 | SOLEDAD 2102 | 2.6274 | 16 | 0.12515 | 2.0024 | 623 | 7262.4533 | 8476.7915 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6170 | GIRVAN 11011330 | 103401101 | GIRVAN 1101 | 31.0696 | 264 | 0.12503 | 33.0087 | 624 | 7293.5228 | 8443.7828 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9760 | RINCON 11035152 | 43321103 | RINCON 1103 | 1.6688 | 17 | 0.1239 | 2.1064 | 625 | 7295.1916 | 8441.6764 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6631 | HIGHLANDS 11031282 | 43361103 | HIGHLANDS 1103 | 14.2542 | 164 | 0.12376 | 20.2971 | 626 | 7309.4457 | 8421.3793 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7124 | SANTA YNEZ 1102CB | 182721102 | SANTA YNEZ 1102 | 1.4593 | 124 | 0.12375 | 15.3456 | 627 | 7310.9051 | 8406.0337 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
547 | STILLWATER 11021644 | 103561102 | STILLWATER 1102 | 22.8387 | 244 | 0.12375 | 30.1941 | 628 | 7333.7438 | 8375.8396 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6046 | WOODWARD 210878448 | 255292108 | WOODWARD 2108 | 19.5076 | 188 | 0.12365 | 23.2453 | 629 | 7353.2514 | 8352.5943 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7443 | GARBERVILLE 11011770 | 192221101 | GARBERVILLE 1101 | 8.6077 | 66 | 0.12342 | 8.1457 | 630 | 7361.8591 | 8344.4486 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2056 | BUELLTON 1101Y06 | 183041101 | BUELLTON 1101 | 30.3639 | 304 | 0.12317 | 37.4433 | 631 | 7392.2231 | 8307.0054 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1863 | DIAMOND SPRINGS 110610587 | 152261106 | DIAMOND SPRINGS 1106 | 21.9618 | 212 | 0.12297 | 26.0703 | 632 | 7414.1849 | 8280.9351 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5060 | CLOVERDALE 1102156 | 42821102 | CLOVERDALE 1102 | 6.1652 | 110 | 0.12268 | 13.4944 | 633 | 7420.3501 | 8267.4407 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8874 | BRIDGEVILLE 110169866 | 192461101 | BRIDGEVILLE 1101 | 6.5701 | 46 | 0.12256 | 5.6379 | 634 | 7426.9202 | 8261.8028 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7200 | DIAMOND SPRINGS 1104705100 | 152261104 | DIAMOND SPRINGS 1104 | 7.3867 | 78 | 0.12223 | 9.5341 | 635 | 7434.3068 | 8252.2687 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5273 | SAND CREEK 11037110 | 254601103 | SAND CREEK 1103 | 18.6347 | 132 | 0.12197 | 16.0996 | 636 | 7452.9416 | 8236.1691 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3234 | FULTON 1107604 | 42561107 | FULTON 1107 | 17.4386 | 169 | 0.12169 | 20.5661 | 637 | 7470.3801 | 8215.603 | 8215.603 | #N/A | TRUE | 4.015 | TRUE | TRUE
8992 | TIDEWATER 2106781445 | 14652106 | TIDEWATER 2106 | 0.25204 | 6 | 0.12145 | 0.72871 | 638 | 7470.6322 | 8214.8743 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9503 | SAN LUIS OBISPO 1103153199 | 182631103 | SAN LUIS OBISPO 1103 | 2.9525 | 53 | 0.1214 | 6.4339 | 639 | 7473.5847 | 8208.4404 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8489 | LAYTONVILLE 1102572 | 42681102 | LAYTONVILLE 1102 | 21.398 | 155 | 0.12097 | 18.7503 | 640 | 7494.9826 | 8189.6901 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1408 | ATASCADERO 1103A16 | 182541103 | ATASCADERO 1103 | 19.7861 | 122 | 0.12088 | 14.7476 | 641 | 7514.7688 | 8174.9425 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
68 | TEJON 11022455 | 252931102 | TEJON 1102 | 6.3179 | 84 | 0.12034 | 10.1082 | 642 | 7521.0867 | 8164.8343 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6764 | MAXWELL 11053008 | 62881105 | MAXWELL 1105 | 8.4754 | 55 | 0.1202 | 6.6112 | 643 | 7529.5621 | 8158.2231 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3997 | APPLE HILL 2102CB | 153662102 | APPLE HILL 2102 | 41.2823 | 448 | 0.12006 | 53.7868 | 644 | 7570.8445 | 8104.4363 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4706 | WYANDOTTE 11031504 | 102911103 | WYANDOTTE 1103 | 11.0226 | 186 | 0.12006 | 22.3307 | 645 | 7581.8671 | 8082.1056 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8185 | CLARKSVILLE 2109CB | 153612109 | CLARKSVILLE 2109 | 0.99037 | 15 | 0.11989 | 1.7983 | 646 | 7582.8575 | 8080.3073 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5862 | HOLLISTER 2102855412 | 182492102 | HOLLISTER 2102 | 28.4042 | 108 | 0.11956 | 12.9123 | 647 | 7611.2617 | 8067.395 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2833 | MARTELL 11033152 | 163011103 | MARTELL 1103 | 16.733 | 134 | 0.11956 | 16.0208 | 648 | 7627.9946 | 8051.3742 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3141 | DIAMOND SPRINGS 11057722 | 152261105 | DIAMOND SPRINGS 1105 | 60.1507 | 572 | 0.11928 | 68.2291 | 649 | 7688.1454 | 7983.1451 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
501 | DOBBINS 11011264 | 153741101 | DOBBINS 1101 | 34.9826 | 307 | 0.11917 | 36.585 | 650 | 7723.1279 | 7946.5601 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
855 | HIGGINS 1103CB | 152691103 | HIGGINS 1103 | 28.0762 | 315 | 0.11916 | 37.536 | 651 | 7751.2042 | 7909.0241 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
491 | TIVY VALLEY 1107822606 | 252941107 | TIVY VALLEY 1107 | 13.4878 | 144 | 0.11894 | 17.1275 | 652 | 7764.692 | 7891.8966 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8121 | CAYETANO 2109MR186 | 14422109 | CAYETANO 2109 | 0.50894 | 27 | 0.11874 | 3.2061 | 653 | 7765.201 | 7888.6905 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2634 | APPLE HILL 21028372 | 153662102 | APPLE HILL 2102 | 58.7208 | 629 | 0.11858 | 74.5861 | 654 | 7823.9218 | 7814.1044 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1440 | MARIPOSA 21019400 | 254452101 | MARIPOSA 2101 | 63.1061 | 667 | 0.11849 | 79.0304 | 655 | 7887.0279 | 7735.074 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8059 | OILFIELDS 1103N62 | 182391103 | OILFIELDS 1103 | 5.5613 | 39 | 0.11842 | 4.6183 | 656 | 7892.5893 | 7730.4558 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1860 | SHINGLE SPRINGS 2105CB | 153652105 | SHINGLE SPRINGS 2105 | 19.0248 | 245 | 0.11812 | 28.9401 | 657 | 7911.614 | 7701.5157 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1237 | NARROWS 2102CB | 153132102 | NARROWS 2102 | 22.5529 | 243 | 0.11807 | 28.6917 | 658 | 7934.1669 | 7672.824 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9931 | CORTINA 1101528460 | 63121101 | CORTINA 1101 | 1.8916 | 12 | 0.11792 | 1.415 | 659 | 7936.0585 | 7671.409 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6877 | COARSEGOLD 21036110 | 254432103 | COARSEGOLD 2103 | 11.0096 | 179 | 0.11737 | 21.0097 | 660 | 7947.0681 | 7650.3993 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3126 | HORSESHOE 110150140 | 152571101 | HORSESHOE 1101 | 3.9511 | 82 | 0.11734 | 9.6215 | 661 | 7951.0192 | 7640.7778 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9916 | SAN LUIS OBISPO 1104777686 | 182631104 | SAN LUIS OBISPO 1104 | 1.6826 | 17 | 0.11731 | 1.9944 | 662 | 7952.7018 | 7638.7835 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8080 | SILVERADO 210258626 | 43432102 | SILVERADO 2102 | 15.2217 | 125 | 0.117 | 14.6249 | 663 | 7967.9235 | 7624.1586 | 7624.1586 | #N/A | TRUE | 3.5445 | TRUE | TRUE
4277 | SAN JOAQUIN #2 1103157026 | 252521103 | SAN JOAQUIN #2 1103 | 3.2319 | 44 | 0.11682 | 5.1403 | 664 | 7971.1554 | 7619.0183 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6827 | PEORIA 170411232 | 163781704 | PEORIA 1704 | 12.7443 | 222 | 0.11656 | 25.8772 | 665 | 7983.8997 | 7593.1411 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
772 | DIAMOND SPRINGS 11052102 | 152261105 | DIAMOND SPRINGS 1105 | 37.4816 | 417 | 0.11621 | 48.4576 | 666 | 8021.3813 | 7544.6834 | 7544.6834 | #N/A | TRUE | 1.6339 | TRUE | TRUE
1946 | WILLITS 1104CB | 42661104 | WILLITS 1104 | 3.8906 | 90 | 0.11609 | 10.4477 | 667 | 8025.2719 | 7534.2357 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2370 | GEYSERVILLE 1102484 | 42891102 | GEYSERVILLE 1102 | 33.3678 | 379 | 0.11607 | 43.9888 | 668 | 8058.6397 | 7490.2469 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7186 | HIGGINS 1104CB | 152691104 | HIGGINS 1104 | 11.2182 | 124 | 0.11592 | 14.3743 | 669 | 8069.8579 | 7475.8727 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9814 | PENRYN 1105119949 | 152561105 | PENRYN 1105 | 1.3809 | 25 | 0.11529 | 2.8822 | 670 | 8071.2388 | 7472.9905 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7423 | CLAY 1103CB | 163341103 | CLAY 1103 | 6.0162 | 110 | 0.11521 | 12.6729 | 671 | 8077.255 | 7460.3176 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7292 | TIDEWATER 2106745811 | 14652106 | TIDEWATER 2106 | 0.39857 | 8 | 0.11506 | 0.92047 | 672 | 8077.6536 | 7459.3971 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8864 | WOODACRE 110191900 | 43021101 | WOODACRE 1101 | 9.0238 | 91 | 0.11491 | 10.4566 | 673 | 8086.6774 | 7448.9405 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9782 | SAND CREEK 110397354 | 254601103 | SAND CREEK 1103 | 8.8056 | 59 | 0.11488 | 6.7778 | 674 | 8095.483 | 7442.1627 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7321 | CLARKSVILLE 210619642 | 153612106 | CLARKSVILLE 2106 | 0.77467 | 17 | 0.11477 | 1.9511 | 675 | 8096.2577 | 7440.2116 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1291 | MERCED FALLS 11029470 | 252811102 | MERCED FALLS 1102 | 22.84 | 277 | 0.11474 | 31.7833 | 676 | 8119.0977 | 7408.4283 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10278 | PUEBLO 2102943820 | 43292102 | PUEBLO 2102 | 1.8891 | 13 | 0.11464 | 1.4903 | 677 | 8120.9868 | 7406.938 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2358 | WHITMORE 11011594 | 103601101 | WHITMORE 1101 | 24.2649 | 160 | 0.11449 | 18.3178 | 678 | 8145.2517 | 7388.6202 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
892 | MARIPOSA 210110240 | 254452101 | MARIPOSA 2101 | 21.5594 | 189 | 0.11431 | 21.6045 | 679 | 8166.8111 | 7367.0158 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4813 | CLOVERDALE 1102674 | 42821102 | CLOVERDALE 1102 | 16.9652 | 122 | 0.11401 | 13.9092 | 680 | 8183.7763 | 7353.1066 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4778 | SHINGLE SPRINGS 210961892 | 153652109 | SHINGLE SPRINGS 2109 | 30.116 | 318 | 0.11372 | 36.1635 | 681 | 8213.8923 | 7316.9431 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9093 | BANGOR 110155206 | 103191101 | BANGOR 1101 | 0 | 28 | 0.11351 | 3.1783 | 682 | 8213.8923 | 7313.7647 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
395 | CALISTOGA 1101734 | 42711101 | CALISTOGA 1101 | 13.7047 | 162 | 0.11348 | 18.3842 | 683 | 8227.597 | 7295.3805 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7143 | COTATI 1103CB | 42271103 | COTATI 1103 | 12.0712 | 106 | 0.11341 | 12.0218 | 684 | 8239.6682 | 7283.3587 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2744 | WHITMORE 110145262 | 103601101 | WHITMORE 1101 | 28.7967 | 221 | 0.11334 | 25.0485 | 685 | 8268.4649 | 7258.3102 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4167 | COTTONWOOD 11031344 | 102931103 | COTTONWOOD 1103 | 10.1214 | 152 | 0.11327 | 17.2178 | 686 | 8278.5863 | 7241.0924 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9035 | CLEAR LAKE 1101699062 | 42141101 | CLEAR LAKE 1101 | 0.84503 | 20 | 0.11322 | 2.2645 | 687 | 8279.4314 | 7238.8279 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2015 | SHINGLE SPRINGS 210912392 | 153652109 | SHINGLE SPRINGS 2109 | 14.6504 | 178 | 0.11309 | 20.1293 | 688 | 8294.0818 | 7218.6986 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2546 | PLACERVILLE 1110421358 | 153081110 | PLACERVILLE 1110 | 14.8357 | 169 | 0.11286 | 19.0733 | 689 | 8308.9175 | 7199.6253 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6240 | SILVERADO 2104722 | 43432104 | SILVERADO 2104 | 7.8964 | 99 | 0.11274 | 11.1613 | 690 | 8316.8139 | 7188.464 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6314 | TEJON 11023751 | 252931102 | TEJON 1102 | 9.8215 | 65 | 0.11269 | 7.325 | 691 | 8326.6355 | 7181.139 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8377 | CAYETANO 2111CB | 14422111 | CAYETANO 2111 | 3.3871 | 81 | 0.11258 | 9.1187 | 692 | 8330.0225 | 7172.0203 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
84 | LINCOLN 110451756 | 153701104 | LINCOLN 1104 | 10.8395 | 264 | 0.11252 | 29.7041 | 693 | 8340.8621 | 7142.3162 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4410 | MC ARTHUR 1101501106 | 103491101 | MC ARTHUR 1101 | 9.9962 | 86 | 0.11248 | 9.6734 | 694 | 8350.8583 | 7132.6427 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1376 | CLARKSVILLE 210419772 | 153612104 | CLARKSVILLE 2104 | 17.9244 | 185 | 0.11233 | 20.7806 | 695 | 8368.7827 | 7111.8621 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
138 | CLARKSVILLE 2103593454 | 153612103 | CLARKSVILLE 2103 | 32.0092 | 324 | 0.11221 | 36.3549 | 696 | 8400.7919 | 7075.5073 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6028 | RISING RIVER 11011530 | 103551101 | RISING RIVER 1101 | 11.2915 | 167 | 0.11218 | 18.7349 | 697 | 8412.0834 | 7056.7724 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6687 | CLARK ROAD 110281296 | 103091102 | CLARK ROAD 1102 | 10.9205 | 124 | 0.11218 | 13.9107 | 698 | 8423.0039 | 7042.8618 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2672 | APPLE HILL 210277546 | 153662102 | APPLE HILL 2102 | 43.0994 | 403 | 0.11214 | 45.1922 | 699 | 8466.1033 | 6997.6696 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4377 | MARIPOSA 2101752630 | 254452101 | MARIPOSA 2101 | 18.9925 | 154 | 0.11205 | 17.2553 | 700 | 8485.0958 | 6980.4143 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5474 | COTATI 1105213984 | 42271105 | COTATI 1105 | 6.9378 | 47 | 0.11198 | 5.263 | 701 | 8492.0335 | 6975.1513 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6448 | MERCED FALLS 110238748 | 252811102 | MERCED FALLS 1102 | 15.354 | 178 | 0.11192 | 19.9215 | 702 | 8507.3876 | 6955.2298 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1645 | COTATI 110599720 | 42271105 | COTATI 1105 | 9.1863 | 134 | 0.11177 | 14.9768 | 703 | 8516.5739 | 6940.2531 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
439 | HIGGINS 1110CB | 152691110 | HIGGINS 1110 | 8.7129 | 134 | 0.11172 | 14.9707 | 704 | 8525.2868 | 6925.2824 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6646 | UPPER LAKE 110175370 | 42871101 | UPPER LAKE 1101 | 11.0775 | 133 | 0.11161 | 14.8441 | 705 | 8536.3643 | 6910.4383 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3320 | LAYTONVILLE 110237586 | 42681102 | LAYTONVILLE 1102 | 13.9571 | 72 | 0.11137 | 8.0187 | 706 | 8550.3215 | 6902.4196 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8527 | HIGGINS 11097831 | 152691109 | HIGGINS 1109 | 8.8881 | 86 | 0.1113 | 9.5719 | 707 | 8559.2096 | 6892.8477 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8404 | TEMPLETON 2110317796 | 183052110 | TEMPLETON 2110 | 5.0644 | 65 | 0.11087 | 7.2063 | 708 | 8564.2739 | 6885.6414 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9399 | CALAVERAS CEMENT 1101585 | 162211101 | CALAVERAS CEMENT 1101 | 14.1272 | 95 | 0.11082 | 10.5283 | 709 | 8578.4011 | 6875.1132 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9168 | CAL WATER 1102690954 | 255451102 | CAL WATER 1102 | 3.9839 | 12 | 0.11057 | 1.3268 | 710 | 8582.385 | 6873.7863 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1850 | OAKHURST 1103CB | 254421103 | OAKHURST 1103 | 32.1872 | 417 | 0.11044 | 46.0525 | 711 | 8614.5722 | 6827.7338 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4124 | CALPELLA 1102CB | 43411102 | CALPELLA 1102 | 0.16351 | 61 | 0.1104 | 6.7341 | 712 | 8614.7357 | 6820.9997 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10720 | OCEANO 1103839302 | 182601103 | OCEANO 1103 | 1.1227 | 8 | 0.11001 | 0.88007 | 713 | 8615.8584 | 6820.1196 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2355 | OLETA 11021204 | 163541102 | OLETA 1102 | 25.7145 | 233 | 0.10989 | 25.6033 | 714 | 8641.5729 | 6794.5163 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
635 | BRUNSWICK 11062790 | 152481106 | BRUNSWICK 1106 | 9.9616 | 115 | 0.10954 | 12.5971 | 715 | 8651.5345 | 6781.9193 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6919 | COTTONWOOD 110168190 | 102931101 | COTTONWOOD 1101 | 23.9832 | 238 | 0.10937 | 26.0311 | 716 | 8675.5177 | 6755.8881 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10335 | PETALUMA C 1109664732 | 42631109 | PETALUMA C 1109 | 0.89361 | 6 | 0.10842 | 0.65051 | 717 | 8676.4113 | 6755.2376 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4157 | CALPELLA 1101600 | 43411101 | CALPELLA 1101 | 19.186 | 164 | 0.10818 | 17.7408 | 718 | 8695.5973 | 6737.4968 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3546 | LUCERNE 1103CB | 43351103 | LUCERNE 1103 | 2.2493 | 59 | 0.10789 | 6.3658 | 719 | 8697.8466 | 6731.131 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6463 | SONOMA 1105229588 | 42721105 | SONOMA 1105 | 9.6526 | 149 | 0.10786 | 16.0708 | 720 | 8707.4992 | 6715.0603 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2133 | FROGTOWN 17011623 | 163451701 | FROGTOWN 1701 | 15.2605 | 152 | 0.1076 | 16.3546 | 721 | 8722.7597 | 6698.7057 | 6698.7057 | #N/A | TRUE | 0.59 | TRUE | TRUE
10925 | GOLDTREE 1105551904 | 182581105 | GOLDTREE 1105 | 0.022199 | 1 | 0.10733 | 0.10733 | 722 | 8722.7819 | 6698.5984 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9605 | NOTRE DAME 1104937710 | 102041104 | NOTRE DAME 1104 | 0.85279 | 8 | 0.10733 | 0.85862 | 723 | 8723.6347 | 6697.7397 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3953 | JAMESON 11059472 | 63801105 | JAMESON 1105 | 3.0669 | 90 | 0.10731 | 9.6577 | 724 | 8726.7016 | 6688.0821 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6952 | OLETA 110151740 | 163541101 | OLETA 1101 | 15.5571 | 129 | 0.107 | 13.8028 | 725 | 8742.2587 | 6674.2793 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4360 | CORRAL 110236666 | 162991102 | CORRAL 1102 | 16.9644 | 207 | 0.10683 | 22.1131 | 726 | 8759.2231 | 6652.1662 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10467 | BIG BEND 11011704 | 103751101 | BIG BEND 1101 | 2.9988 | 9 | 0.1065 | 0.95854 | 727 | 8762.2219 | 6651.2077 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2963 | KONOCTI 110275382 | 43311102 | KONOCTI 1102 | 23.2045 | 198 | 0.10636 | 21.0588 | 728 | 8785.4264 | 6630.1489 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7719 | GEYSERVILLE 1102220154 | 42891102 | GEYSERVILLE 1102 | 0.26588 | 30 | 0.10579 | 3.1738 | 729 | 8785.6923 | 6626.9751 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4276 | NARROWS 2105CB | 153132105 | NARROWS 2105 | 36.093 | 382 | 0.10567 | 40.3677 | 730 | 8821.7853 | 6586.6073 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4123 | MARIPOSA 21014410 | 254452101 | MARIPOSA 2101 | 22.8107 | 232 | 0.10548 | 24.471 | 731 | 8844.596 | 6562.1363 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5996 | MONTICELLO 1101630 | 43051101 | MONTICELLO 1101 | 18.7154 | 93 | 0.10515 | 9.7794 | 732 | 8863.3114 | 6552.3569 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7010 | WILLITS 1103966 | 42661103 | WILLITS 1103 | 0.96697 | 34 | 0.10505 | 3.5716 | 733 | 8864.2783 | 6548.7854 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6094 | PARADISE 110443008 | 102831104 | PARADISE 1104 | 12.8637 | 145 | 0.10501 | 15.2269 | 734 | 8877.1421 | 6533.5584 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6540 | MORGAN HILL 2105XR070 | 83242105 | MORGAN HILL 2105 | 6.5379 | 90 | 0.10473 | 9.4261 | 735 | 8883.68 | 6524.1324 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1104 | BRUNSWICK 11042112 | 152481104 | BRUNSWICK 1104 | 19.3921 | 222 | 0.1046 | 23.2211 | 736 | 8903.0721 | 6500.9113 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3331 | NARROWS 21052216 | 153132105 | NARROWS 2105 | 56.6762 | 663 | 0.10438 | 69.2068 | 737 | 8959.7484 | 6431.7045 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10962 | POINT ARENA 1101CB | 43381101 | POINT ARENA 1101 | 0.040346 | 2 | 0.10413 | 0.20825 | 738 | 8959.7887 | 6431.4963 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7695 | JAMESON 110265516 | 63801102 | JAMESON 1102 | 7.7033 | 137 | 0.104 | 14.2484 | 739 | 8967.492 | 6417.2479 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4131 | CURTIS 170565908 | 163351705 | CURTIS 1705 | 13.9093 | 205 | 0.10393 | 21.3052 | 740 | 8981.4013 | 6395.9427 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
386 | CORRAL 110112606 | 162991101 | CORRAL 1101 | 22.4639 | 216 | 0.10392 | 22.4476 | 741 | 9003.8652 | 6373.4951 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1298 | DESCHUTES 11011652 | 103351101 | DESCHUTES 1101 | 21.066 | 170 | 0.10352 | 17.5982 | 742 | 9024.9312 | 6355.8969 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10344 | CLARKSVILLE 210319572 | 153612103 | CLARKSVILLE 2103 | 0.37003 | 12 | 0.10348 | 1.2418 | 743 | 9025.3013 | 6354.6551 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2338 | CLAY 110113442 | 163341101 | CLAY 1101 | 25.3259 | 272 | 0.10338 | 28.1191 | 744 | 9050.6272 | 6326.536 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1080 | PLACER 1103284874 | 152461103 | PLACER 1103 | 2.1447 | 56 | 0.10322 | 5.7804 | 745 | 9052.7719 | 6320.7556 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2572 | VACA DIXON 11059792 | 63591105 | VACA DIXON 1105 | 0.78022 | 329 | 0.10322 | 33.9591 | 746 | 9053.5521 | 6286.7965 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10829 | MILPITAS 110962157 | 82831109 | MILPITAS 1109 | 0.044811 | 3 | 0.10257 | 0.30771 | 747 | 9053.5969 | 6286.4888 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9526 | DOBBINS 110191464 | 153741101 | DOBBINS 1101 | 7.0318 | 81 | 0.10229 | 8.2855 | 748 | 9060.6286 | 6278.2032 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4686 | ELK CREEK 11012212 | 102781101 | ELK CREEK 1101 | 15.6044 | 136 | 0.10222 | 13.9025 | 749 | 9076.2331 | 6264.3007 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2703 | COTATI 110536536 | 42271105 | COTATI 1105 | 17.2163 | 206 | 0.10219 | 21.0515 | 750 | 9093.4494 | 6243.2492 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
261 | CLARK ROAD 11022584 | 103091102 | CLARK ROAD 1102 | 9.0835 | 83 | 0.1019 | 8.4581 | 751 | 9102.5329 | 6234.7911 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6202 | COARSEGOLD 210490356 | 254432104 | COARSEGOLD 2104 | 4.8161 | 148 | 0.10189 | 15.079 | 752 | 9107.3489 | 6219.7121 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10164 | CALPELLA 1101345230 | 43411101 | CALPELLA 1101 | 1.186 | 22 | 0.10181 | 2.2398 | 753 | 9108.5349 | 6217.4723 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10372 | CLOVERDALE 11024646 | 42821102 | CLOVERDALE 1102 | 0.15065 | 8 | 0.10163 | 0.81301 | 754 | 9108.6855 | 6216.6593 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10615 | STAFFORD 1102CB | 43201102 | STAFFORD 1102 | 0.59497 | 10 | 0.10116 | 1.0116 | 755 | 9109.2805 | 6215.6478 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10097 | GARBERVILLE 110256048 | 192221102 | GARBERVILLE 1102 | 4.9779 | 27 | 0.10102 | 2.7275 | 756 | 9114.2584 | 6212.9202 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2214 | MONTICELLO 11014360 | 43051101 | MONTICELLO 1101 | 7.564 | 76 | 0.10101 | 7.6765 | 757 | 9121.8224 | 6205.2438 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2869 | NARROWS 21011202 | 153132101 | NARROWS 2101 | 45.7737 | 459 | 0.10087 | 46.3007 | 758 | 9167.5961 | 6158.9431 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2918 | JESSUP 110338864 | 103441103 | JESSUP 1103 | 1.8068 | 94 | 0.10076 | 9.4715 | 759 | 9169.4029 | 6149.4716 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8434 | FORT ROSS 1121204 | 42851121 | FORT ROSS 1121 | 19.6108 | 107 | 0.10067 | 10.7713 | 760 | 9189.0138 | 6138.7003 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9462 | BEAR VALLEY 210110019 | 252192101 | BEAR VALLEY 2101 | 1.981 | 11 | 0.10052 | 1.1057 | 761 | 9190.9948 | 6137.5945 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3132 | MORGAN HILL 210542348 | 83242105 | MORGAN HILL 2105 | 1.343 | 53 | 0.10037 | 5.3194 | 762 | 9192.3378 | 6132.2751 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10415 | SAN LUIS OBISPO 1103934355 | 182631103 | SAN LUIS OBISPO 1103 | 0.56909 | 12 | 0.10029 | 1.2035 | 763 | 9192.9068 | 6131.0716 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
800 | NARROWS 210248484 | 153132102 | NARROWS 2102 | 41.6749 | 450 | 0.09998 | 44.991 | 764 | 9234.5817 | 6086.0806 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3794 | HIGGINS 11077559 | 152691107 | HIGGINS 1107 | 4.4708 | 52 | 0.099807 | 5.1899 | 765 | 9239.0525 | 6080.8907 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4136 | MONTICELLO 1101718 | 43051101 | MONTICELLO 1101 | 27.0127 | 247 | 0.099744 | 24.6369 | 766 | 9266.0652 | 6056.2538 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2696 | OLETA 110163500 | 163541101 | OLETA 1101 | 0.20333 | 46 | 0.099652 | 4.584 | 767 | 9266.2685 | 6051.6698 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3595 | CEDAR CREEK 11011608 | 103321101 | CEDAR CREEK 1101 | 33.4541 | 252 | 0.099644 | 25.1102 | 768 | 9299.7226 | 6026.5596 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
80 | WHEATLAND 1105248490 | 152811105 | WHEATLAND 1105 | 11.0172 | 228 | 0.099611 | 22.7114 | 769 | 9310.7397 | 6003.8482 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
24 | FITCH MOUNTAIN 1113443164 | 42751113 | FITCH MOUNTAIN 1113 | 2.7965 | 111 | 0.099321 | 11.0246 | 770 | 9313.5363 | 5992.8236 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6194 | CLARK ROAD 110292622 | 103091102 | CLARK ROAD 1102 | 31.2685 | 257 | 0.098498 | 25.314 | 771 | 9344.8048 | 5967.5096 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
643 | PENRYN 1105154362 | 152561105 | PENRYN 1105 | 2.163 | 90 | 0.098415 | 8.8574 | 772 | 9346.9678 | 5958.6522 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10663 | SAN RAMON 2102CB | 14232102 | SAN RAMON 2102 | 1.763 | 16 | 0.098349 | 1.5736 | 773 | 9348.7308 | 5957.0787 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7571 | BROWNS VALLEY 110193870 | 152921101 | BROWNS VALLEY 1101 | 18.5376 | 342 | 0.098287 | 33.6143 | 774 | 9367.2684 | 5923.4643 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9322 | MONTICELLO 1101CB | 43051101 | MONTICELLO 1101 | 0.53443 | 5 | 0.098274 | 0.49137 | 775 | 9367.8028 | 5922.973 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5943 | TEMPLETON 2113A10 | 183052113 | TEMPLETON 2113 | 31.0415 | 264 | 0.098002 | 25.8725 | 776 | 9398.8442 | 5897.1005 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5478 | PENRYN 11072706 | 152561107 | PENRYN 1107 | 5.783 | 190 | 0.09785 | 18.5915 | 777 | 9404.6273 | 5878.509 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3757 | WILLITS 1104934 | 42661104 | WILLITS 1104 | 30.8641 | 279 | 0.097599 | 27.2301 | 778 | 9435.4914 | 5851.2789 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7329 | CORRAL 110213498 | 162991102 | CORRAL 1102 | 0.98568 | 13 | 0.097071 | 1.2619 | 779 | 9436.4771 | 5850.017 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6184 | PEORIA 170190090 | 163781701 | PEORIA 1701 | 30.0386 | 168 | 0.09692 | 16.2826 | 780 | 9466.5157 | 5833.7343 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1027 | OILFIELDS 110383158 | 182391103 | OILFIELDS 1103 | 17.6694 | 132 | 0.09689 | 12.7894 | 781 | 9484.185 | 5820.9449 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3208 | WILLITS 11032500 | 42661103 | WILLITS 1103 | 29.917 | 143 | 0.096773 | 13.8385 | 782 | 9514.102 | 5807.1065 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9576 | LLAGAS 2104603392 | 83182104 | LLAGAS 2104 | 2.9124 | 17 | 0.096621 | 1.6426 | 783 | 9517.0144 | 5805.4639 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
211 | APPLE HILL 110313312 | 153661103 | APPLE HILL 1103 | 13.1484 | 190 | 0.096554 | 18.3453 | 784 | 9530.1627 | 5787.1186 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1106 | BANGOR 11011958 | 103191101 | BANGOR 1101 | 33.8504 | 353 | 0.096142 | 33.9382 | 785 | 9564.0132 | 5753.1804 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5073 | LAYTONVILLE 1102CB | 42681102 | LAYTONVILLE 1102 | 11.9747 | 95 | 0.095782 | 9.0993 | 786 | 9575.9879 | 5744.0811 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7859 | MOUNTAIN QUARRIES 210135466 | 152282101 | MOUNTAIN QUARRIES 2101 | 7.3565 | 82 | 0.095562 | 7.8361 | 787 | 9583.3444 | 5736.245 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
871 | PEORIA 17019811 | 163781701 | PEORIA 1701 | 3.5901 | 92 | 0.095333 | 8.7707 | 788 | 9586.9345 | 5727.4744 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
669 | CABRILLO 1103CB | 183101103 | CABRILLO 1103 | 0.54422 | 45 | 0.095165 | 4.2824 | 789 | 9587.4788 | 5723.1919 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3438 | CALISTOGA 1102CB | 42711102 | CALISTOGA 1102 | 0.32187 | 37 | 0.095153 | 3.5207 | 790 | 9587.8006 | 5719.6713 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8923 | SUNOL 1101CB | 14241101 | SUNOL 1101 | 3.2822 | 53 | 0.095135 | 5.0422 | 791 | 9591.0828 | 5714.6291 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5883 | SILVERADO 2104632 | 43432104 | SILVERADO 2104 | 18.3299 | 193 | 0.094959 | 18.327 | 792 | 9609.4127 | 5696.3021 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5762 | CHALLENGE 11021064 | 103201102 | CHALLENGE 1102 | 19.6711 | 179 | 0.094905 | 16.9879 | 793 | 9629.0837 | 5679.3141 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
847 | CURTIS 17026008 | 163351702 | CURTIS 1702 | 23.3091 | 236 | 0.094797 | 22.3721 | 794 | 9652.3928 | 5656.942 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7905 | CAYETANO 2109CB | 14422109 | CAYETANO 2109 | 1.4107 | 51 | 0.094773 | 4.8334 | 795 | 9653.8035 | 5652.1086 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6145 | OAKHURST 110210100 | 254421102 | OAKHURST 1102 | 10.3936 | 142 | 0.094733 | 13.4521 | 796 | 9664.1971 | 5638.6565 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6083 | MILPITAS 1109XR524 | 82831109 | MILPITAS 1109 | 10.891 | 59 | 0.09443 | 5.5714 | 797 | 9675.0882 | 5633.0852 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
370 | UKIAH 1114CB | 42771114 | UKIAH 1114 | 0.66327 | 93 | 0.094346 | 8.7742 | 798 | 9675.7514 | 5624.311 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7085 | MESA 1103854149 | 182821103 | MESA 1103 | 0.97169 | 12 | 0.094333 | 1.132 | 799 | 9676.7231 | 5623.179 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8026 | PEORIA 1704CB | 163781704 | PEORIA 1704 | 8.3718 | 64 | 0.094159 | 6.0262 | 800 | 9685.0949 | 5617.1528 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4910 | PUEBLO 2103373667 | 43292103 | PUEBLO 2103 | 3.275 | 45 | 0.09414 | 4.2363 | 801 | 9688.3699 | 5612.9165 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3504 | MOLINO 1102396 | 42571102 | MOLINO 1102 | 16.102 | 182 | 0.093951 | 17.099 | 802 | 9704.4719 | 5595.8175 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8266 | LAS POSITAS 2108MR182 | 14402108 | LAS POSITAS 2108 | 6.6928 | 56 | 0.093921 | 5.2596 | 803 | 9711.1648 | 5590.5579 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6506 | CALAVERAS CEMENT 11014786 | 162211101 | CALAVERAS CEMENT 1101 | 18.0074 | 173 | 0.09378 | 16.224 | 804 | 9729.1722 | 5574.3339 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1161 | WYANDOTTE 110777578 | 102911107 | WYANDOTTE 1107 | 21.3971 | 389 | 0.09328 | 36.2858 | 805 | 9750.5693 | 5538.0481 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5393 | GARBERVILLE 11024744 | 192221102 | GARBERVILLE 1102 | 17.3636 | 161 | 0.093231 | 15.0101 | 806 | 9767.9329 | 5523.038 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5755 | PENRYN 11072704 | 152561107 | PENRYN 1107 | 1.4297 | 76 | 0.093023 | 7.0698 | 807 | 9769.3626 | 5515.9682 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8038 | WILLITS 1103826 | 42661103 | WILLITS 1103 | 7.7413 | 89 | 0.092902 | 8.2683 | 808 | 9777.1039 | 5507.6999 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5718 | PETALUMA C 1108233646 | 42631108 | PETALUMA C 1108 | 9.3863 | 127 | 0.092653 | 11.7669 | 809 | 9786.4902 | 5495.933 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7314 | CLARKSVILLE 210575884 | 153612105 | CLARKSVILLE 2105 | 10.6684 | 94 | 0.09258 | 8.7025 | 810 | 9797.1586 | 5487.2305 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
837 | DIAMOND SPRINGS 11071402 | 152261107 | DIAMOND SPRINGS 1107 | 44.1915 | 541 | 0.092281 | 49.924 | 811 | 9841.3501 | 5437.3065 | 5437.3065 | #N/A | TRUE | 8.465 | TRUE | TRUE
1640 | JESSUP 1101CB | 103441101 | JESSUP 1101 | 1.5303 | 66 | 0.092174 | 6.0835 | 812 | 9842.8804 | 5431.223 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2558 | PENRYN 1103660 | 152561103 | PENRYN 1103 | 10.1639 | 233 | 0.092166 | 21.4747 | 813 | 9853.0443 | 5409.7483 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9244 | KERN OIL 110646960 | 252721106 | KERN OIL 1106 | 0.91054 | 14 | 0.092145 | 1.29 | 814 | 9853.9548 | 5408.4583 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4181 | MONTICELLO 1101666 | 43051101 | MONTICELLO 1101 | 12.0959 | 90 | 0.092048 | 8.2843 | 815 | 9866.0507 | 5400.174 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8910 | BRIDGEVILLE 110255612 | 192461102 | BRIDGEVILLE 1102 | 22.2384 | 93 | 0.090894 | 8.4532 | 816 | 9888.2891 | 5391.7208 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3415 | PARADISE 1104409622 | 102831104 | PARADISE 1104 | 12.7625 | 156 | 0.090831 | 14.1696 | 817 | 9901.0516 | 5377.5512 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4056 | CALAVERAS CEMENT 110113424 | 162211101 | CALAVERAS CEMENT 1101 | 1.4942 | 43 | 0.090714 | 3.9007 | 818 | 9902.5458 | 5373.6504 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
345 | COTTONWOOD 1101384360 | 102931101 | COTTONWOOD 1101 | 4.9052 | 70 | 0.090426 | 6.3298 | 819 | 9907.451 | 5367.3206 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
287 | WHITMORE 11011598 | 103601101 | WHITMORE 1101 | 33.5165 | 251 | 0.09042 | 22.6955 | 820 | 9940.9674 | 5344.6251 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8279 | LOW GAP 110186816 | 192411101 | LOW GAP 1101 | 4.4149 | 51 | 0.090319 | 4.6062 | 821 | 9945.3823 | 5340.0189 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7426 | SANTA MARIA 1108M18 | 182671108 | SANTA MARIA 1108 | 15.2655 | 81 | 0.090027 | 7.2922 | 822 | 9960.6477 | 5332.7267 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7586 | KONOCTI 1102948 | 43311102 | KONOCTI 1102 | 6.3142 | 73 | 0.089784 | 6.5542 | 823 | 9966.962 | 5326.1725 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8787 | GIRVAN 1102212096 | 103401102 | GIRVAN 1102 | 2.5631 | 42 | 0.089733 | 3.7688 | 824 | 9969.5251 | 5322.4037 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10586 | LOS MOLINOS 1101297862 | 103481101 | LOS MOLINOS 1101 | 0.31276 | 4 | 0.089567 | 0.35827 | 825 | 9969.8378 | 5322.0455 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6573 | SISQUOC 1103858898 | 182811103 | SISQUOC 1103 | 19.6096 | 152 | 0.089508 | 13.6052 | 826 | 9989.4474 | 5308.4403 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10830 | PETALUMA C 1109373772 | 42631109 | PETALUMA C 1109 | 0.017818 | 2 | 0.089417 | 0.17883 | 827 | 9989.4652 | 5308.2615 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
817 | CLOVERDALE 1102570 | 42821102 | CLOVERDALE 1102 | 17.7483 | 199 | 0.089292 | 17.7691 | 828 | 10007.2135 | 5290.4923 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5781 | SAN JOAQUIN #3 11035100 | 252531103 | SAN JOAQUIN #3 1103 | 21.334 | 204 | 0.089218 | 18.2004 | 829 | 10028.5475 | 5272.2919 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6729 | SAN LUIS OBISPO 110788962 | 182631107 | SAN LUIS OBISPO 1107 | 2.4841 | 45 | 0.089174 | 4.0128 | 830 | 10031.0316 | 5268.2791 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5238 | DIAMOND SPRINGS 110656026 | 152261106 | DIAMOND SPRINGS 1106 | 15.1269 | 158 | 0.089061 | 14.0716 | 831 | 10046.1585 | 5254.2074 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4137 | UKIAH 1114528 | 42771114 | UKIAH 1114 | 3.7591 | 110 | 0.08906 | 9.7966 | 832 | 10049.9177 | 5244.4108 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2145 | CALISTOGA 1101736 | 42711101 | CALISTOGA 1101 | 34.6626 | 350 | 0.088841 | 31.0945 | 833 | 10084.5802 | 5213.3163 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8817 | WYANDOTTE 1105CB | 102911105 | WYANDOTTE 1105 | 11.4973 | 14 | 0.088539 | 1.2395 | 834 | 10096.0776 | 5212.0768 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3899 | PEORIA 170510580 | 163781705 | PEORIA 1705 | 7.7172 | 129 | 0.088489 | 11.415 | 835 | 10103.7948 | 5200.6617 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5666 | WOODSIDE 110147872 | 24251101 | WOODSIDE 1101 | 4.17 | 52 | 0.088422 | 4.5979 | 836 | 10107.9648 | 5196.0638 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7241 | ATASCADERO 1103A14 | 182541103 | ATASCADERO 1103 | 25.119 | 152 | 0.088418 | 13.4395 | 837 | 10133.0838 | 5182.6243 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
878 | FROGTOWN 170275252 | 163451702 | FROGTOWN 1702 | 57.9081 | 401 | 0.088153 | 35.3494 | 838 | 10190.9919 | 5147.2749 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4836 | GRASS VALLEY 11031700 | 152031103 | GRASS VALLEY 1103 | 21.7093 | 255 | 0.087918 | 22.4191 | 839 | 10212.7011 | 5124.8558 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7987 | BELL 1108339792 | 152701108 | BELL 1108 | 2.6235 | 43 | 0.087729 | 3.7723 | 840 | 10215.3246 | 5121.0835 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8725 | LLAGAS 2101984552 | 83182101 | LLAGAS 2101 | 4.5399 | 53 | 0.087511 | 4.6381 | 841 | 10219.8645 | 5116.4454 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4715 | GIRVAN 110280726 | 103401102 | GIRVAN 1102 | 7.8692 | 217 | 0.087369 | 18.9591 | 842 | 10227.7337 | 5097.4863 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5678 | SAN LUIS OBISPO 1102348318 | 182631102 | SAN LUIS OBISPO 1102 | 0.37106 | 6 | 0.087346 | 0.52408 | 843 | 10228.1048 | 5096.9622 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8497 | BEAR VALLEY 210576694 | 252192105 | BEAR VALLEY 2105 | 4.5478 | 37 | 0.087295 | 3.2299 | 844 | 10232.6525 | 5093.7323 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4933 | RACETRACK 17039190 | 163761703 | RACETRACK 1703 | 8.9738 | 104 | 0.087115 | 9.06 | 845 | 10241.6264 | 5084.6723 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10437 | RIO DELL 110275970 | 192251102 | RIO DELL 1102 | 7.072 | 33 | 0.08694 | 2.869 | 846 | 10248.6984 | 5081.8033 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3279 | OAKHURST 1101CB | 254421101 | OAKHURST 1101 | 2.3149 | 47 | 0.086583 | 4.0694 | 847 | 10251.0133 | 5077.7339 | 5077.7339 | #N/A | TRUE | 0.052083 | TRUE | TRUE
6810 | KESWICK 11011590 | 103451101 | KESWICK 1101 | 6.4567 | 63 | 0.086534 | 5.4516 | 848 | 10257.47 | 5072.2823 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2304 | SAN JOAQUIN #3 1103CB | 252531103 | SAN JOAQUIN #3 1103 | 28.3844 | 294 | 0.086354 | 25.3881 | 849 | 10285.8544 | 5046.8942 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7373 | TIVY VALLEY 11077380 | 252941107 | TIVY VALLEY 1107 | 12.9556 | 240 | 0.086218 | 20.6923 | 850 | 10298.81 | 5026.2019 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1492 | STILLWATER 110148950 | 103561101 | STILLWATER 1101 | 12.4809 | 145 | 0.085979 | 12.467 | 851 | 10311.2909 | 5013.735 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3172 | RED BLUFF 1105161818 | 103541105 | RED BLUFF 1105 | 0.13198 | 59 | 0.08588 | 5.0669 | 852 | 10311.4229 | 5008.668 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5834 | SANTA YNEZ 1102320270 | 182721102 | SANTA YNEZ 1102 | 8.4827 | 137 | 0.08574 | 11.7464 | 853 | 10319.9055 | 4996.9216 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
742 | MORGAN HILL 2105XR176 | 83242105 | MORGAN HILL 2105 | 22.5311 | 309 | 0.085689 | 26.478 | 854 | 10342.4366 | 4970.4437 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8450 | MARTELL 1102CB | 163011102 | MARTELL 1102 | 5.6818 | 69 | 0.08567 | 5.9113 | 855 | 10348.1185 | 4964.5324 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3883 | COTATI 1102167726 | 42271102 | COTATI 1102 | 3.8001 | 50 | 0.08544 | 4.272 | 856 | 10351.9186 | 4960.2605 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10186 | CLAYTON 22159765 | 12022215 | CLAYTON 2215 | 0.26445 | 16 | 0.085394 | 1.3663 | 857 | 10352.183 | 4958.8941 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5425 | CORNING 110187304 | 103331101 | CORNING 1101 | 2.8806 | 100 | 0.085339 | 8.5339 | 858 | 10355.0636 | 4950.3602 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4113 | PHILO 1101CB | 42601101 | PHILO 1101 | 31.8871 | 469 | 0.085283 | 39.9976 | 859 | 10386.9507 | 4910.3627 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10106 | GEYSERVILLE 1102537096 | 42891102 | GEYSERVILLE 1102 | 0.48227 | 6 | 0.085228 | 0.51137 | 860 | 10387.433 | 4909.8513 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9409 | CLAY 1102CB | 163341102 | CLAY 1102 | 0.92759 | 19 | 0.085217 | 1.6191 | 861 | 10388.3606 | 4908.2322 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6247 | ELK CREEK 11012004 | 102781101 | ELK CREEK 1101 | 25 | 174 | 0.085175 | 14.8204 | 862 | 10413.3606 | 4893.4117 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2719 | SAN LUIS OBISPO 1104V10 | 182631104 | SAN LUIS OBISPO 1104 | 2.1783 | 54 | 0.085103 | 4.5956 | 863 | 10415.5389 | 4888.8162 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
541 | TEMPLETON 2113R82 | 183052113 | TEMPLETON 2113 | 38.4024 | 563 | 0.084913 | 47.806 | 864 | 10453.9413 | 4841.0101 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7060 | BIG BEND 1102CB | 103751102 | BIG BEND 1102 | 17.0366 | 139 | 0.084888 | 11.7994 | 865 | 10470.9778 | 4829.2107 | 4829.2107 | #N/A | TRUE | 5.3 | FALSE | TRUE
7634 | IONE 1101L3141 | 163881101 | IONE 1101 | 13.8321 | 97 | 0.084539 | 8.2002 | 866 | 10484.8099 | 4821.0105 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1449 | FORT SEWARD 1122CB | 192321122 | FORT SEWARD 1122 | 17.6589 | 111 | 0.084457 | 9.3748 | 867 | 10502.4688 | 4811.6357 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3137 | MOLINO 1102104 | 42571102 | MOLINO 1102 | 21.7475 | 235 | 0.084332 | 19.818 | 868 | 10524.2162 | 4791.8177 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4967 | NARROWS 21052748 | 153132105 | NARROWS 2105 | 12.9469 | 245 | 0.084145 | 20.6156 | 869 | 10537.1631 | 4771.2021 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9631 | EDENVALE 2107739448 | 82952107 | EDENVALE 2107 | 1.7776 | 12 | 0.084104 | 1.0093 | 870 | 10538.9407 | 4770.1929 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5449 | PENRYN 110351658 | 152561103 | PENRYN 1103 | 8.1666 | 108 | 0.084002 | 9.0722 | 871 | 10547.1073 | 4761.1207 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9940 | MILPITAS 110598568 | 82831105 | MILPITAS 1105 | 0.1045 | 7 | 0.083995 | 0.58797 | 872 | 10547.2118 | 4760.5327 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4281 | PUEBLO 1105637242 | 43291105 | PUEBLO 1105 | 16.8339 | 193 | 0.083893 | 16.1913 | 873 | 10564.0457 | 4744.3414 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9696 | LAS GALLINAS A 1104507389 | 42991104 | LAS GALLINAS A 1104 | 0.13197 | 4 | 0.083842 | 0.33537 | 874 | 10564.1776 | 4744.0061 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3446 | ELK CREEK 11012228 | 102781101 | ELK CREEK 1101 | 3.3625 | 80 | 0.082955 | 6.6364 | 875 | 10567.5401 | 4737.3697 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2644 | WILLITS 110391948 | 42661103 | WILLITS 1103 | 7.4224 | 69 | 0.082927 | 5.7219 | 876 | 10574.9625 | 4731.6477 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2263 | SWIFT 2110XR366 | 83392110 | SWIFT 2110 | 8.4324 | 129 | 0.082848 | 10.6874 | 877 | 10583.3949 | 4720.9604 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9623 | SANTA YNEZ 1104685160 | 182721104 | SANTA YNEZ 1104 | 0.58655 | 17 | 0.082766 | 1.407 | 878 | 10583.9815 | 4719.5534 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7942 | FULTON 11024994 | 42561102 | FULTON 1102 | 1.3585 | 45 | 0.082765 | 3.7244 | 879 | 10585.34 | 4715.8289 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4041 | FROGTOWN 1702737236 | 163451702 | FROGTOWN 1702 | 8.7642 | 88 | 0.082425 | 7.2534 | 880 | 10594.1042 | 4708.5755 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4759 | COTATI 110379140 | 42271103 | COTATI 1103 | 9.7839 | 154 | 0.082367 | 12.6845 | 881 | 10603.8881 | 4695.891 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1164 | BEAR VALLEY 2105454432 | 252192105 | BEAR VALLEY 2105 | 14.4352 | 112 | 0.08233 | 9.221 | 882 | 10618.3233 | 4686.67 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4634 | SHINGLE SPRINGS 211051790 | 153652110 | SHINGLE SPRINGS 2110 | 7.909 | 106 | 0.082229 | 8.7163 | 883 | 10626.2323 | 4677.9538 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4491 | CALPELLA 1102144510 | 43411102 | CALPELLA 1102 | 3.1138 | 41 | 0.08218 | 3.3694 | 884 | 10629.3461 | 4674.5844 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3945 | DOBBINS 11015202 | 153741101 | DOBBINS 1101 | 16.3256 | 162 | 0.082155 | 13.3091 | 885 | 10645.6717 | 4661.2753 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5174 | CALAVERAS CEMENT 110111236 | 162211101 | CALAVERAS CEMENT 1101 | 19.7501 | 143 | 0.081838 | 11.7029 | 886 | 10665.4218 | 4649.5724 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4695 | SILVERADO 21043485 | 43432104 | SILVERADO 2104 | 1.7427 | 23 | 0.081749 | 1.8802 | 887 | 10667.1645 | 4647.6922 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5312 | PETALUMA C 1108632 | 42631108 | PETALUMA C 1108 | 14.7283 | 81 | 0.081559 | 6.6063 | 888 | 10681.8928 | 4641.0858 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8333 | BEAR VALLEY 21054609 | 252192105 | BEAR VALLEY 2105 | 4.5506 | 41 | 0.081381 | 3.3366 | 889 | 10686.4434 | 4637.7492 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7354 | JOLON 11027004 | 182981102 | JOLON 1102 | 7.9213 | 128 | 0.081062 | 10.3759 | 890 | 10694.3647 | 4627.3733 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4785 | MORGAN HILL 2111XR398 | 83242111 | MORGAN HILL 2111 | 37.7039 | 341 | 0.080766 | 27.5412 | 891 | 10732.0686 | 4599.8321 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9589 | CLAY 11031821 | 163341103 | CLAY 1103 | 3.5846 | 33 | 0.080483 | 2.6559 | 892 | 10735.6531 | 4597.1762 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1075 | LINCOLN 110195756 | 153701101 | LINCOLN 1101 | 7.4272 | 200 | 0.080379 | 16.0759 | 893 | 10743.0804 | 4581.1003 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3754 | PALMER 1101M82 | 183031101 | PALMER 1101 | 10.8435 | 149 | 0.080327 | 11.9687 | 894 | 10753.9239 | 4569.1316 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5126 | CRESCENT MILLS 21012056 | 103132101 | CRESCENT MILLS 2101 | 5.0155 | 70 | 0.080308 | 5.6215 | 895 | 10758.9394 | 4563.51 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7701 | SILVERADO 2102808 | 43432102 | SILVERADO 2102 | 2.5368 | 39 | 0.0803 | 3.1317 | 896 | 10761.4762 | 4560.3783 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1034 | HOOPA 11013290 | 192401101 | HOOPA 1101 | 13.5618 | 135 | 0.080281 | 10.8379 | 897 | 10775.038 | 4549.5404 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7166 | GANSNER 1101372132 | 103021101 | GANSNER 1101 | 0.41841 | 13 | 0.08025 | 1.0433 | 898 | 10775.4564 | 4548.4971 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9769 | UKIAH 1111807988 | 42771111 | UKIAH 1111 | 4.168 | 15 | 0.080023 | 1.2003 | 899 | 10779.6244 | 4547.2968 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6682 | OILFIELDS 1103643162 | 182391103 | OILFIELDS 1103 | 3.4384 | 41 | 0.079941 | 3.2776 | 900 | 10783.0628 | 4544.0192 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10896 | CMC 1102CB | 183111102 | CMC 1102 | 0.36161 | 5 | 0.079905 | 0.39953 | 901 | 10783.4244 | 4543.6197 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2989 | KONOCTI 11024300 | 43311102 | KONOCTI 1102 | 26.9634 | 268 | 0.079811 | 21.3893 | 902 | 10810.3878 | 4522.2304 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10408 | POSO MOUNTAIN 21011703 | 253642101 | POSO MOUNTAIN 2101 | 0.90462 | 7 | 0.079525 | 0.55668 | 903 | 10811.2924 | 4521.6737 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6364 | PLACERVILLE 2106935216 | 153082106 | PLACERVILLE 2106 | 21.0371 | 204 | 0.079474 | 16.2127 | 904 | 10832.3295 | 4505.461 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4098 | WYANDOTTE 11071510 | 102911107 | WYANDOTTE 1107 | 25.4992 | 243 | 0.079411 | 19.297 | 905 | 10857.8287 | 4486.164 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7076 | CLARKSVILLE 210419632 | 153612104 | CLARKSVILLE 2104 | 5.5922 | 110 | 0.07935 | 8.7285 | 906 | 10863.4209 | 4477.4355 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1230 | TEMPLETON 2113A08 | 183052113 | TEMPLETON 2113 | 10.4677 | 257 | 0.079335 | 20.3891 | 907 | 10873.8886 | 4457.0464 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5155 | FOOTHILL 1101CB | 182951101 | FOOTHILL 1101 | 13.3962 | 149 | 0.079316 | 11.8181 | 908 | 10887.2848 | 4445.2283 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2049 | FRUITLAND 1141CB | 192311141 | FRUITLAND 1141 | 3.1918 | 17 | 0.079299 | 1.3481 | 909 | 10890.4766 | 4443.8802 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4771 | OCEANO 1104Q12 | 182601104 | OCEANO 1104 | 11.3133 | 142 | 0.079257 | 11.2544 | 910 | 10901.7898 | 4432.6258 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10844 | SPRING GAP 1702188426 | 162831702 | SPRING GAP 1702 | 0.0028415 | 1 | 0.078773 | 0.078773 | 911 | 10901.7927 | 4432.547 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1175 | HIGGINS 11044281 | 152691104 | HIGGINS 1104 | 13.3249 | 138 | 0.078646 | 10.8532 | 912 | 10915.1176 | 4421.6938 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9778 | HIGGINS 11097863 | 152691109 | HIGGINS 1109 | 4.2244 | 42 | 0.078616 | 3.3019 | 913 | 10919.342 | 4418.3919 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6230 | MONTICELLO 110193384 | 43051101 | MONTICELLO 1101 | 16.1387 | 101 | 0.078583 | 7.9369 | 914 | 10935.4808 | 4410.455 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9152 | MIDDLETOWN 11011314 | 43141101 | MIDDLETOWN 1101 | 0.92556 | 13 | 0.078235 | 1.0171 | 915 | 10936.4063 | 4409.438 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10292 | BIG MEADOWS 21012248 | 102812101 | BIG MEADOWS 2101 | 9.1535 | 28 | 0.077859 | 2.18 | 916 | 10945.5598 | 4407.2579 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3275 | OCEANO 1104Q10 | 182601104 | OCEANO 1104 | 23.6364 | 289 | 0.077836 | 22.4946 | 917 | 10969.1963 | 4384.7634 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5179 | HARTLEY 1102CB | 43211102 | HARTLEY 1102 | 3.428 | 135 | 0.077778 | 10.5 | 918 | 10972.6243 | 4374.2633 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8256 | MORGAN HILL 2105XR268 | 83242105 | MORGAN HILL 2105 | 7.9569 | 61 | 0.077596 | 4.7333 | 919 | 10980.5811 | 4369.53 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1037 | MIDDLETOWN 11021312 | 43141102 | MIDDLETOWN 1102 | 9.834 | 120 | 0.077577 | 9.3092 | 920 | 10990.4151 | 4360.2207 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3607 | OCEANO 1104V38 | 182601104 | OCEANO 1104 | 12.0606 | 212 | 0.077544 | 16.4392 | 921 | 11002.4757 | 4343.7815 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9877 | CLOVERDALE 1102307342 | 42821102 | CLOVERDALE 1102 | 0.22003 | 6 | 0.077416 | 0.46449 | 922 | 11002.6958 | 4343.317 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3974 | FITCH MOUNTAIN 111324550 | 42751113 | FITCH MOUNTAIN 1113 | 11.0612 | 203 | 0.077338 | 15.6996 | 923 | 11013.757 | 4327.6174 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
962 | MIDDLETOWN 1102514 | 43141102 | MIDDLETOWN 1102 | 3.3507 | 71 | 0.077302 | 5.4884 | 924 | 11017.1076 | 4322.129 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10365 | CURTIS 170349746 | 163351703 | CURTIS 1703 | 0.37408 | 3 | 0.077172 | 0.23152 | 925 | 11017.4817 | 4321.8974 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3098 | PETALUMA C 1108630 | 42631108 | PETALUMA C 1108 | 1.6495 | 55 | 0.077168 | 4.2442 | 926 | 11019.1312 | 4317.6532 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6234 | SAN JUSTO 1101201311 | 183181101 | SAN JUSTO 1101 | 7.8594 | 108 | 0.077053 | 8.3218 | 927 | 11026.9906 | 4309.3315 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6221 | GARBERVILLE 110135706 | 192221101 | GARBERVILLE 1101 | 10.1113 | 97 | 0.076898 | 7.4591 | 928 | 11037.1019 | 4301.8723 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2802 | PENRYN 11072410 | 152561107 | PENRYN 1107 | 3.2618 | 96 | 0.076748 | 7.3678 | 929 | 11040.3637 | 4294.5045 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8295 | COTATI 110387402 | 42271103 | COTATI 1103 | 11.3572 | 42 | 0.07664 | 3.2189 | 930 | 11051.721 | 4291.2856 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10268 | TEJON 11023760 | 252931102 | TEJON 1102 | 6.4735 | 6 | 0.076506 | 0.45904 | 931 | 11058.1945 | 4290.8266 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10279 | VOLTA 1102CB | 102541102 | VOLTA 1102 | 3.2988 | 25 | 0.076253 | 1.9063 | 932 | 11061.4933 | 4288.9202 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9092 | FORT ROSS 11214614 | 42851121 | FORT ROSS 1121 | 12.5587 | 95 | 0.075773 | 7.1985 | 933 | 11074.052 | 4281.7218 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3923 | AUBERRY 110137536 | 254151101 | AUBERRY 1101 | 5.3994 | 60 | 0.075515 | 4.5309 | 934 | 11079.4514 | 4277.1909 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5756 | CABRILLO 11031437 | 183101103 | CABRILLO 1103 | 2.8448 | 39 | 0.075332 | 2.9379 | 935 | 11082.2963 | 4274.2529 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6109 | FITCH MOUNTAIN 1113583202 | 42751113 | FITCH MOUNTAIN 1113 | 4.8942 | 106 | 0.075101 | 7.9607 | 936 | 11087.1905 | 4266.2923 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4163 | WILLITS 1103538 | 42661103 | WILLITS 1103 | 6.3249 | 48 | 0.074937 | 3.597 | 937 | 11093.5154 | 4262.6953 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9780 | SONOMA 1107854266 | 42721107 | SONOMA 1107 | 0.19976 | 6 | 0.074827 | 0.44896 | 938 | 11093.7152 | 4262.2463 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
260 | BRUNSWICK 11067099 | 152481106 | BRUNSWICK 1106 | 7.7312 | 83 | 0.074794 | 6.2079 | 939 | 11101.4464 | 4256.0384 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3084 | GEYSERVILLE 1102274 | 42891102 | GEYSERVILLE 1102 | 6.4625 | 173 | 0.074787 | 12.9382 | 940 | 11107.9089 | 4243.1002 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6342 | MADISON 21011606 | 63172101 | MADISON 2101 | 0.15808 | 280 | 0.074511 | 20.863 | 941 | 11108.067 | 4222.2372 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10492 | DRUM 1101CB | 152321101 | DRUM 1101 | 2.1651 | 16 | 0.074456 | 1.1913 | 942 | 11110.232 | 4221.0459 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
874 | RISING RIVER 1101CB | 103551101 | RISING RIVER 1101 | 9.9169 | 121 | 0.074106 | 8.9669 | 943 | 11120.1489 | 4212.0791 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8386 | PEORIA 1705999 | 163781705 | PEORIA 1705 | 2.3089 | 22 | 0.074075 | 1.6297 | 944 | 11122.4578 | 4210.4494 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7502 | FITCH MOUNTAIN 11136751 | 42751113 | FITCH MOUNTAIN 1113 | 22.6749 | 139 | 0.073927 | 10.2759 | 945 | 11145.1327 | 4200.1735 | 4200.1735 | #N/A | TRUE | 4.03 | TRUE | TRUE
5338 | SAN JOAQUIN #3 1102CB | 252531102 | SAN JOAQUIN #3 1102 | 9.6963 | 97 | 0.073848 | 7.1632 | 946 | 11154.8291 | 4193.0103 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7052 | CALISTOGA 1101134232 | 42711101 | CALISTOGA 1101 | 1.6277 | 89 | 0.0737 | 6.5593 | 947 | 11156.4567 | 4186.451 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10249 | SILVERADO 2102CB | 43432102 | SILVERADO 2102 | 0.59218 | 22 | 0.073682 | 1.621 | 948 | 11157.0489 | 4184.8299 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6791 | CABRILLO 1104Y24 | 183101104 | CABRILLO 1104 | 19.1707 | 91 | 0.073569 | 6.6947 | 949 | 11176.2196 | 4178.1352 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3606 | HORSESHOE 1101CB | 152571101 | HORSESHOE 1101 | 0.35258 | 55 | 0.073561 | 4.0458 | 950 | 11176.5721 | 4174.0894 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2673 | PUEBLO 2102792 | 43292102 | PUEBLO 2102 | 19.3407 | 180 | 0.073389 | 13.2101 | 951 | 11195.9128 | 4160.8793 | 4160.8793 | #N/A | TRUE | 3.3379 | TRUE | TRUE
4637 | SAN LUIS OBISPO 1104V40 | 182631104 | SAN LUIS OBISPO 1104 | 14.7 | 194 | 0.073389 | 14.2374 | 952 | 11210.6128 | 4146.6419 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2241 | CURTIS 170247488 | 163351702 | CURTIS 1702 | 19.011 | 207 | 0.07338 | 15.1897 | 953 | 11229.6238 | 4131.4522 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9651 | PURISIMA 1101Y44 | 182971101 | PURISIMA 1101 | 10.4077 | 45 | 0.073295 | 3.2983 | 954 | 11240.0315 | 4128.1539 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1008 | TEMPLETON 2113A70 | 183052113 | TEMPLETON 2113 | 24.7135 | 659 | 0.073157 | 48.2106 | 955 | 11264.745 | 4079.9434 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3782 | AUBERRY 1101R322 | 254151101 | AUBERRY 1101 | 7.6672 | 44 | 0.073065 | 3.2149 | 956 | 11272.4122 | 4076.7285 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
700 | MERCED FALLS 11029460 | 252811102 | MERCED FALLS 1102 | 11.1412 | 91 | 0.073014 | 6.6443 | 957 | 11283.5534 | 4070.0842 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1286 | CURTIS 170384944 | 163351703 | CURTIS 1703 | 58.219 | 439 | 0.072725 | 31.9262 | 958 | 11341.7723 | 4038.158 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8476 | ALTO 1124810594 | 42031124 | ALTO 1124 | 0.55899 | 6 | 0.072684 | 0.4361 | 959 | 11342.3313 | 4037.7219 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1350 | PENRYN 1107CB | 152561107 | PENRYN 1107 | 5.429 | 200 | 0.072647 | 14.5295 | 960 | 11347.7603 | 4023.1925 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10196 | SANTA YNEZ 1101980192 | 182721101 | SANTA YNEZ 1101 | 3.8401 | 19 | 0.072592 | 1.3793 | 961 | 11351.6004 | 4021.8132 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4126 | VACAVILLE 1104CB | 63601104 | VACAVILLE 1104 | 0.43299 | 36 | 0.07222 | 2.5999 | 962 | 11352.0333 | 4019.2133 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6142 | JOLON 1103CB | 182981103 | JOLON 1103 | 13.1598 | 91 | 0.072102 | 6.5613 | 963 | 11365.1932 | 4012.652 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4505 | LOW GAP 11014086 | 192411101 | LOW GAP 1101 | 11.4942 | 66 | 0.072098 | 4.7585 | 964 | 11376.6874 | 4007.8935 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5220 | COTATI 1103132 | 42271103 | COTATI 1103 | 25.2965 | 184 | 0.071994 | 13.2468 | 965 | 11401.9839 | 3994.6467 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2886 | VOLTA 11011596 | 102541101 | VOLTA 1101 | 21.8176 | 132 | 0.071922 | 9.4937 | 966 | 11423.8015 | 3985.1529 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7748 | PEORIA 170413490 | 163781704 | PEORIA 1704 | 4.2731 | 49 | 0.071878 | 3.522 | 967 | 11428.0746 | 3981.6309 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1885 | OREGON TRAIL 110249144 | 103521102 | OREGON TRAIL 1102 | 18.3805 | 169 | 0.071512 | 12.0855 | 968 | 11446.4551 | 3969.5454 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3676 | COTTONWOOD 1101CB | 102931101 | COTTONWOOD 1101 | 0.11437 | 188 | 0.0715 | 13.442 | 969 | 11446.5694 | 3956.1035 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7714 | FROGTOWN 17027134 | 163451702 | FROGTOWN 1702 | 20.2101 | 172 | 0.071297 | 12.2631 | 970 | 11466.7796 | 3943.8404 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4319 | MESA 11016111 | 182821101 | MESA 1101 | 24.2535 | 202 | 0.071153 | 14.3729 | 971 | 11491.0331 | 3929.4675 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5571 | CLEAR LAKE 1101740076 | 42141101 | CLEAR LAKE 1101 | 0.39302 | 106 | 0.071071 | 7.5335 | 972 | 11491.4261 | 3921.934 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9268 | OLETA 1102799924 | 163541102 | OLETA 1102 | 0.38634 | 4 | 0.070818 | 0.28327 | 973 | 11491.8125 | 3921.6507 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1141 | BELL 1109724884 | 152701109 | BELL 1109 | 14.0392 | 167 | 0.070791 | 11.822 | 974 | 11505.8517 | 3909.8287 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9406 | EDENVALE 2107469810 | 82952107 | EDENVALE 2107 | 2.153 | 14 | 0.070672 | 0.98941 | 975 | 11508.0047 | 3908.8393 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2788 | WYANDOTTE 1110980944 | 102911110 | WYANDOTTE 1110 | 10.4309 | 198 | 0.070566 | 13.9721 | 976 | 11518.4355 | 3894.8671 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3339 | JESSUP 110276068 | 103441102 | JESSUP 1102 | 17.1802 | 232 | 0.070348 | 16.3207 | 977 | 11535.6157 | 3878.5465 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6626 | CLAY 1101CB | 163341101 | CLAY 1101 | 0.56812 | 33 | 0.070136 | 2.3145 | 978 | 11536.1838 | 3876.232 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9158 | COVELO 1101306476 | 43061101 | COVELO 1101 | 1.9306 | 49 | 0.069853 | 3.4228 | 979 | 11538.1145 | 3872.8092 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5752 | MONTICELLO 110165454 | 43051101 | MONTICELLO 1101 | 1.3526 | 23 | 0.069594 | 1.6007 | 980 | 11539.4671 | 3871.2085 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2727 | OREGON TRAIL 11031500 | 103521103 | OREGON TRAIL 1103 | 26.0289 | 261 | 0.069495 | 18.1383 | 981 | 11565.4959 | 3853.0702 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10741 | HALF MOON BAY 11038920 | 24101103 | HALF MOON BAY 1103 | 0.098275 | 2 | 0.069477 | 0.13895 | 982 | 11565.5942 | 3852.9313 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2684 | BEAR VALLEY 210110000 | 252192101 | BEAR VALLEY 2101 | 29.2711 | 230 | 0.069198 | 15.9156 | 983 | 11594.8653 | 3837.0157 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1190 | OCEANO 1104V36 | 182601104 | OCEANO 1104 | 11.205 | 150 | 0.069118 | 10.3677 | 984 | 11606.0703 | 3826.648 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9260 | DIAMOND SPRINGS 110777086 | 152261107 | DIAMOND SPRINGS 1107 | 2.717 | 47 | 0.068998 | 3.2429 | 985 | 11608.7873 | 3823.4051 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
87 | CORNING 110185152 | 103331101 | CORNING 1101 | 23.2021 | 279 | 0.068983 | 19.2463 | 986 | 11631.9894 | 3804.1589 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2893 | UKIAH 1114544 | 42771114 | UKIAH 1114 | 0.48867 | 98 | 0.068781 | 6.7406 | 987 | 11632.478 | 3797.4183 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
69 | BROWNS VALLEY 110197188 | 152921101 | BROWNS VALLEY 1101 | 6.7867 | 71 | 0.068613 | 4.8715 | 988 | 11639.2647 | 3792.5468 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1342 | AUBERRY 1101R2838 | 254151101 | AUBERRY 1101 | 20.4455 | 210 | 0.068544 | 14.3942 | 989 | 11659.7102 | 3778.1526 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9647 | GARCIA 0401CB | 43040401 | GARCIA 0401 | 0.029031 | 1 | 0.068469 | 0.068469 | 990 | 11659.7392 | 3778.0841 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2407 | FROGTOWN 1702835115 | 163451702 | FROGTOWN 1702 | 18.143 | 191 | 0.068398 | 13.0639 | 991 | 11677.8822 | 3765.0202 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3939 | ZACA 1101Y70 | 182681101 | ZACA 1101 | 6.7366 | 61 | 0.068291 | 4.1658 | 992 | 11684.6188 | 3760.8544 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3966 | SAN BENITO 2101295566 | 182742101 | SAN BENITO 2101 | 0.46708 | 18 | 0.068263 | 1.2287 | 993 | 11685.0859 | 3759.6257 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1800 | BANGOR 11011804 | 103191101 | BANGOR 1101 | 42.8988 | 394 | 0.068197 | 26.8697 | 994 | 11727.9846 | 3732.756 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1078 | BIG MEADOWS 21012260 | 102812101 | BIG MEADOWS 2101 | 15.795 | 185 | 0.067786 | 12.5404 | 995 | 11743.7797 | 3720.2156 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8083 | ANDERSON 1101583708 | 103261101 | ANDERSON 1101 | 0.62857 | 11 | 0.067762 | 0.74538 | 996 | 11744.4082 | 3719.4702 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6638 | SAN RAMON 2117CB | 14232117 | SAN RAMON 2117 | 0.68297 | 23 | 0.067722 | 1.5576 | 997 | 11745.0912 | 3717.9126 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7538 | CABRILLO 1103Y46 | 183101103 | CABRILLO 1103 | 31.4816 | 277 | 0.067522 | 18.7037 | 998 | 11776.5728 | 3699.2089 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4175 | MARTELL 1101CB | 163011101 | MARTELL 1101 | 5.879 | 171 | 0.067405 | 11.5263 | 999 | 11782.4518 | 3687.6826 | 3687.6826 | #N/A | TRUE | 1.31 | TRUE | TRUE
9619 | PETALUMA C 1108456397 | 42631108 | PETALUMA C 1108 | 1.3916 | 19 | 0.067328 | 1.2792 | 1000 | 11783.8434 | 3686.4034 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3701 | FRENCH GULCH 1101CB | 103381101 | FRENCH GULCH 1101 | 2.298 | 32 | 0.067293 | 2.1534 | 1001 | 11786.1414 | 3684.25 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4093 | RED BLUFF 1105146070 | 103541105 | RED BLUFF 1105 | 12.7281 | 167 | 0.067012 | 11.191 | 1002 | 11798.8695 | 3673.059 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1562 | LAYTONVILLE 110264908 | 42681102 | LAYTONVILLE 1102 | 3.877 | 84 | 0.066995 | 5.6276 | 1003 | 11802.7465 | 3667.4314 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7452 | SAN RAMON 210853732 | 14232108 | SAN RAMON 2108 | 7.7954 | 77 | 0.066862 | 5.1484 | 1004 | 11810.5419 | 3662.283 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
509 | CALISTOGA 110143924 | 42711101 | CALISTOGA 1101 | 7.7836 | 107 | 0.066852 | 7.1532 | 1005 | 11818.3255 | 3655.1298 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2808 | PASO ROBLES 1104P02 | 182611104 | PASO ROBLES 1104 | 0.32009 | 93 | 0.06682 | 6.2143 | 1006 | 11818.6456 | 3648.9155 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6977 | CLOVERDALE 1102172096 | 42821102 | CLOVERDALE 1102 | 0.26446 | 12 | 0.06657 | 0.79884 | 1007 | 11818.9101 | 3648.1167 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6400 | PHILO 1102CB | 42601102 | PHILO 1102 | 7.699 | 131 | 0.06648 | 8.7089 | 1008 | 11826.6091 | 3639.4078 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1390 | CURTIS 170539256 | 163351705 | CURTIS 1705 | 26.4643 | 287 | 0.066296 | 19.0271 | 1009 | 11853.0734 | 3620.3808 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9080 | SUMMIT 110249484 | 152591102 | SUMMIT 1102 | 2.646 | 27 | 0.06627 | 1.7893 | 1010 | 11855.7194 | 3618.5915 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
493 | BRUNSWICK 11102664 | 152481110 | BRUNSWICK 1110 | 8.0242 | 132 | 0.066185 | 8.7364 | 1011 | 11863.7436 | 3609.8551 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6828 | SILVERADO 210298998 | 43432102 | SILVERADO 2102 | 0.073401 | 136 | 0.066014 | 8.9779 | 1012 | 11863.817 | 3600.8772 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
828 | ATASCADERO 1103A18 | 182541103 | ATASCADERO 1103 | 8.8187 | 188 | 0.065994 | 12.4068 | 1013 | 11872.6357 | 3588.4703 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7881 | CALISTOGA 1102141073 | 42711102 | CALISTOGA 1102 | 1.2408 | 27 | 0.065722 | 1.7745 | 1014 | 11873.8765 | 3586.6958 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5591 | CURTIS 17029220 | 163351702 | CURTIS 1702 | 11.0031 | 123 | 0.065661 | 8.0763 | 1015 | 11884.8796 | 3578.6196 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1187 | PENRYN 11051342 | 152561105 | PENRYN 1105 | 20.7279 | 440 | 0.065366 | 28.7609 | 1016 | 11905.6075 | 3549.8587 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8143 | CLAYTON 2215W531R | 12022215 | CLAYTON 2215 | 6.4908 | 100 | 0.065356 | 6.5356 | 1017 | 11912.0983 | 3543.3231 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2291 | SHINGLE SPRINGS 210913322 | 153652109 | SHINGLE SPRINGS 2109 | 41.4032 | 490 | 0.065331 | 32.0124 | 1018 | 11953.5015 | 3511.3107 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2286 | BEAR VALLEY 210521160 | 252192105 | BEAR VALLEY 2105 | 23.7846 | 194 | 0.065187 | 12.6462 | 1019 | 11977.2861 | 3498.6645 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9841 | MESA 1103126697 | 182821103 | MESA 1103 | 1.0204 | 10 | 0.065062 | 0.65062 | 1020 | 11978.3065 | 3498.0139 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9670 | FRENCH GULCH 1102CB | 103381102 | FRENCH GULCH 1102 | 1.6961 | 12 | 0.06474 | 0.77689 | 1021 | 11980.0026 | 3497.237 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2589 | FORT ROSS 1121124 | 42851121 | FORT ROSS 1121 | 18.4975 | 99 | 0.064597 | 6.3951 | 1022 | 11998.5001 | 3490.8419 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2518 | OCEANO 1104Q08 | 182601104 | OCEANO 1104 | 12.4187 | 148 | 0.064559 | 9.5547 | 1023 | 12010.9188 | 3481.2872 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10030 | MC ARTHUR 1102542920 | 103491102 | MC ARTHUR 1102 | 1.2647 | 10 | 0.064427 | 0.64427 | 1024 | 12012.1834 | 3480.6429 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4185 | PASO ROBLES 1104R12 | 182611104 | PASO ROBLES 1104 | 32.8131 | 278 | 0.064341 | 17.8868 | 1025 | 12044.9965 | 3462.7561 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7956 | JESSUP 11011993 | 103441101 | JESSUP 1101 | 2.7783 | 39 | 0.064212 | 2.5043 | 1026 | 12047.7749 | 3460.2518 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10640 | CALISTOGA 110266730 | 42711102 | CALISTOGA 1102 | 1.0586 | 6 | 0.064035 | 0.38421 | 1027 | 12048.8335 | 3459.8676 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9262 | LAKEVILLE 110287432 | 43371102 | LAKEVILLE 1102 | 9.7629 | 81 | 0.063901 | 5.176 | 1028 | 12058.5964 | 3454.6916 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6678 | MIDDLETOWN 11011325 | 43141101 | MIDDLETOWN 1101 | 8.5951 | 80 | 0.063613 | 5.0891 | 1029 | 12067.1915 | 3449.6025 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5737 | UKIAH 11151216 | 42771115 | UKIAH 1115 | 13.4422 | 182 | 0.063522 | 11.561 | 1030 | 12080.6337 | 3438.0415 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1518 | DIAMOND SPRINGS 110518935 | 152261105 | DIAMOND SPRINGS 1105 | 6.696 | 76 | 0.063224 | 4.805 | 1031 | 12087.3297 | 3433.2365 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8962 | TEMPLETON 2110N30 | 183052110 | TEMPLETON 2110 | 20.3656 | 120 | 0.063152 | 7.5782 | 1032 | 12107.6954 | 3425.6583 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5800 | CLARK ROAD 11022070 | 103091102 | CLARK ROAD 1102 | 9.1899 | 72 | 0.063106 | 4.5436 | 1033 | 12116.8853 | 3421.1147 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1728 | TEMPLETON 2112116402 | 183052112 | TEMPLETON 2112 | 2.3685 | 64 | 0.062979 | 4.0307 | 1034 | 12119.2538 | 3417.084 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
727 | APPLE HILL 2102186912 | 153662102 | APPLE HILL 2102 | 58.5914 | 606 | 0.06292 | 38.1293 | 1035 | 12177.8452 | 3378.9548 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7181 | BEAR VALLEY 21054170 | 252192105 | BEAR VALLEY 2105 | 9.5212 | 45 | 0.062779 | 2.8251 | 1036 | 12187.3664 | 3376.1297 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8856 | GARBERVILLE 11028189 | 192221102 | GARBERVILLE 1102 | 1.0475 | 11 | 0.062553 | 0.68809 | 1037 | 12188.4139 | 3375.4416 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1917 | PANORAMA 1101CB | 103461101 | PANORAMA 1101 | 1.1366 | 175 | 0.062374 | 10.9155 | 1038 | 12189.5506 | 3364.5261 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9789 | TASSAJARA 2106203380 | 14662106 | TASSAJARA 2106 | 0.50317 | 26 | 0.062335 | 1.6207 | 1039 | 12190.0537 | 3362.9054 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8449 | VACAVILLE 111112342 | 63601111 | VACAVILLE 1111 | 0.21883 | 16 | 0.062293 | 0.99668 | 1040 | 12190.2726 | 3361.9087 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3572 | OLETA 110113478 | 163541101 | OLETA 1101 | 12.3348 | 169 | 0.062159 | 10.5049 | 1041 | 12202.6073 | 3351.4038 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1028 | LOW GAP 11012094 | 192411101 | LOW GAP 1101 | 15.6921 | 139 | 0.062103 | 8.6323 | 1042 | 12218.2995 | 3342.7715 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3105 | NOTRE DAME 11042028 | 102041104 | NOTRE DAME 1104 | 10.8376 | 86 | 0.062015 | 5.3333 | 1043 | 12229.1371 | 3337.4382 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2667 | FROGTOWN 170212282 | 163451702 | FROGTOWN 1702 | 36.3469 | 261 | 0.061928 | 16.1631 | 1044 | 12265.4839 | 3321.2751 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7606 | NOTRE DAME 11042537 | 102041104 | NOTRE DAME 1104 | 4.9907 | 37 | 0.061762 | 2.2852 | 1045 | 12270.4747 | 3318.9899 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2093 | ATASCADERO 1103A46 | 182541103 | ATASCADERO 1103 | 0.39348 | 94 | 0.06175 | 5.8045 | 1046 | 12270.8682 | 3313.1854 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7485 | SHINGLE SPRINGS 210551738 | 153652105 | SHINGLE SPRINGS 2105 | 0.016582 | 19 | 0.061564 | 1.1697 | 1047 | 12270.8847 | 3312.0157 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
284 | PERRY 1101V78 | 183071101 | PERRY 1101 | 29.5036 | 164 | 0.061453 | 10.0783 | 1048 | 12300.3884 | 3301.9374 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10468 | CALPINE 1144962 | 48011144 | CALPINE 1144 | 0.039381 | 1 | 0.061428 | 0.061428 | 1049 | 12300.4278 | 3301.876 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8597 | ORO FINO 1102127563 | 103031102 | ORO FINO 1102 | 6.9024 | 63 | 0.061336 | 3.8642 | 1050 | 12307.3301 | 3298.0118 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6425 | MADISON 2101351038 | 63172101 | MADISON 2101 | 1.6542 | 130 | 0.061316 | 7.971 | 1051 | 12308.9844 | 3290.0408 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5524 | JESSUP 11011496 | 103441101 | JESSUP 1101 | 14.6221 | 201 | 0.06121 | 12.3032 | 1052 | 12323.6065 | 3277.7376 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10127 | SPAULDING 1101CB | 152251101 | SPAULDING 1101 | 0.035269 | 1 | 0.061207 | 0.061207 | 1053 | 12323.6417 | 3277.6764 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4318 | HIGGINS 11102408 | 152691110 | HIGGINS 1110 | 11.569 | 124 | 0.060864 | 7.5471 | 1054 | 12335.2108 | 3270.1292 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7906 | PIT NO 7 1101CB | 103501101 | PIT NO 7 1101 | 2.7084 | 3 | 0.060819 | 0.18246 | 1055 | 12337.9192 | 3269.9468 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7035 | SYCAMORE CREEK 1111CB | 102971111 | SYCAMORE CREEK 1111 | 0.48337 | 85 | 0.060715 | 5.1608 | 1056 | 12338.4026 | 3264.786 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4688 | UPPER LAKE 1101452 | 42871101 | UPPER LAKE 1101 | 5.0523 | 207 | 0.060708 | 12.5666 | 1057 | 12343.4548 | 3252.2194 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7853 | CLOVERDALE 1102670 | 42821102 | CLOVERDALE 1102 | 0.36491 | 43 | 0.06056 | 2.6041 | 1058 | 12343.8197 | 3249.6153 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9980 | BRIDGEVILLE 1101CB | 192461101 | BRIDGEVILLE 1101 | 8.5166 | 51 | 0.060495 | 3.0852 | 1059 | 12352.3363 | 3246.53 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3075 | REDBUD 11022013 | 43191102 | REDBUD 1102 | 0.14852 | 51 | 0.06048 | 3.0845 | 1060 | 12352.4848 | 3243.4455 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
377 | FROGTOWN 1702L5407 | 163451702 | FROGTOWN 1702 | 18.279 | 153 | 0.060463 | 9.2508 | 1061 | 12370.7638 | 3234.1948 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
599 | CURTIS 170356972 | 163351703 | CURTIS 1703 | 8.5712 | 57 | 0.060186 | 3.4306 | 1062 | 12379.335 | 3230.7642 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9546 | COTATI 1102CB | 42271102 | COTATI 1102 | 1.805 | 19 | 0.05984 | 1.137 | 1063 | 12381.1401 | 3229.6272 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9754 | CALPELLA 1102708161 | 43411102 | CALPELLA 1102 | 1.0037 | 12 | 0.059606 | 0.71527 | 1064 | 12382.1438 | 3228.9119 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7941 | FRUITLAND 11426064 | 192311142 | FRUITLAND 1142 | 6.6979 | 66 | 0.059515 | 3.928 | 1065 | 12388.8417 | 3224.9839 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1172 | CORRAL 110336680 | 162991103 | CORRAL 1103 | 9.357 | 265 | 0.059472 | 15.7601 | 1066 | 12398.1987 | 3209.2239 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7127 | SONOMA 1107844168 | 42721107 | SONOMA 1107 | 4.5426 | 100 | 0.059437 | 5.9437 | 1067 | 12402.7413 | 3203.2802 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2372 | GRASS VALLEY 11032110 | 152031103 | GRASS VALLEY 1103 | 19.7627 | 224 | 0.059423 | 13.3106 | 1068 | 12422.504 | 3189.9695 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2173 | PUEBLO 1105696 | 43291105 | PUEBLO 1105 | 3.7526 | 79 | 0.059025 | 4.663 | 1069 | 12426.2566 | 3185.3066 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2604 | JESSUP 11031540 | 103441103 | JESSUP 1103 | 0.15935 | 157 | 0.058865 | 9.2418 | 1070 | 12426.4159 | 3176.0648 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8024 | PENRYN 11072708 | 152561107 | PENRYN 1107 | 9.3816 | 124 | 0.058775 | 7.2881 | 1071 | 12435.7975 | 3168.7766 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
660 | GABILAN 1101460414 | 182331101 | GABILAN 1101 | 5.3792 | 38 | 0.058719 | 2.2313 | 1072 | 12441.1768 | 3166.5453 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2838 | MENDOCINO 110148750 | 42951101 | MENDOCINO 1101 | 17.9237 | 165 | 0.058621 | 9.6724 | 1073 | 12459.1005 | 3156.8729 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5642 | ALHAMBRA 110582622 | 14101105 | ALHAMBRA 1105 | 25.9188 | 254 | 0.058508 | 14.8609 | 1074 | 12485.0193 | 3142.012 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5965 | JOLON 1102CB | 182981102 | JOLON 1102 | 23.5798 | 181 | 0.058399 | 10.5701 | 1075 | 12508.5991 | 3131.4419 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5646 | SANTA YNEZ 1104512912 | 182721104 | SANTA YNEZ 1104 | 0.89193 | 23 | 0.058383 | 1.3428 | 1076 | 12509.491 | 3130.099 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1584 | COLUMBIA HILL 1101CB | 152471101 | COLUMBIA HILL 1101 | 39.3563 | 375 | 0.058367 | 21.8875 | 1077 | 12548.8473 | 3108.2116 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8255 | CRESCENT MILLS 21012562 | 103132101 | CRESCENT MILLS 2101 | 19.3429 | 222 | 0.057915 | 12.8572 | 1078 | 12568.1902 | 3095.3543 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2533 | MOLINO 1101338 | 42571101 | MOLINO 1101 | 7.7669 | 176 | 0.05791 | 10.1921 | 1079 | 12575.9571 | 3085.1622 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9899 | LLAGAS 21014523 | 83182101 | LLAGAS 2101 | 0.91427 | 28 | 0.057806 | 1.6186 | 1080 | 12576.8714 | 3083.5436 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10017 | PASO ROBLES 1107289947 | 182611107 | PASO ROBLES 1107 | 0.27821 | 21 | 0.057658 | 1.2108 | 1081 | 12577.1496 | 3082.3328 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
451 | CALISTOGA 11011087 | 42711101 | CALISTOGA 1101 | 1.9622 | 22 | 0.05764 | 1.2681 | 1082 | 12579.1117 | 3081.0648 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
90 | TYLER 1105816852 | 103571105 | TYLER 1105 | 12.7692 | 423 | 0.057549 | 24.3431 | 1083 | 12591.881 | 3056.7217 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
67 | WOODACRE 1102CB | 43021102 | WOODACRE 1102 | 12.4834 | 141 | 0.057543 | 8.1136 | 1084 | 12604.3644 | 3048.6081 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3103 | JOLON 11027070 | 182981102 | JOLON 1102 | 6.4059 | 132 | 0.057494 | 7.5892 | 1085 | 12610.7703 | 3041.0189 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6894 | DESCHUTES 11011654 | 103351101 | DESCHUTES 1101 | 17.5396 | 168 | 0.057486 | 9.6576 | 1086 | 12628.3099 | 3031.3613 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1819 | ALTO 11243745 | 42031124 | ALTO 1124 | 4.5042 | 52 | 0.057415 | 2.9856 | 1087 | 12632.8141 | 3028.3757 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1989 | ELECTRA 1101CB | 162161101 | ELECTRA 1101 | 31.6879 | 293 | 0.05741 | 16.8213 | 1088 | 12664.502 | 3011.5544 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
994 | BUTTE 1105751990 | 103081105 | BUTTE 1105 | 24.51 | 243 | 0.057382 | 13.9439 | 1089 | 12689.012 | 2997.6106 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7429 | MOUNTAIN QUARRIES 210151584 | 152282101 | MOUNTAIN QUARRIES 2101 | 21.7785 | 224 | 0.057318 | 12.8393 | 1090 | 12710.7905 | 2984.7712 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7628 | WISE 11011404 | 152271101 | WISE 1101 | 1.4934 | 47 | 0.057199 | 2.6884 | 1091 | 12712.2839 | 2982.0829 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7386 | SAN RAMON 2108CB | 14232108 | SAN RAMON 2108 | 8.709 | 102 | 0.057183 | 5.8326 | 1092 | 12720.9928 | 2976.2502 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9327 | CALISTOGA 110189150 | 42711101 | CALISTOGA 1101 | 9.5291 | 88 | 0.057148 | 5.029 | 1093 | 12730.5219 | 2971.2212 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4436 | SAN RAMON 2119CB | 14232119 | SAN RAMON 2119 | 0.73831 | 21 | 0.057097 | 1.199 | 1094 | 12731.2602 | 2970.0222 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4471 | ELECTRA 11024756 | 162161102 | ELECTRA 1102 | 9.4092 | 95 | 0.057032 | 5.4181 | 1095 | 12740.6694 | 2964.6041 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10516 | GARBERVILLE 11022124 | 192221102 | GARBERVILLE 1102 | 3.1238 | 6 | 0.057006 | 0.34203 | 1096 | 12743.7932 | 2964.2621 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10428 | ANNAPOLIS 1101CB | 42861101 | ANNAPOLIS 1101 | 0.658 | 7 | 0.057005 | 0.39904 | 1097 | 12744.4512 | 2963.863 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5436 | TEMPLETON 2110901690 | 183052110 | TEMPLETON 2110 | 37.3078 | 306 | 0.056927 | 17.4196 | 1098 | 12781.759 | 2946.4434 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1208 | HOPLAND 1101CB | 42251101 | HOPLAND 1101 | 14.6549 | 190 | 0.056867 | 10.8047 | 1099 | 12796.4139 | 2935.6387 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
582 | SWIFT 2110853720 | 83392110 | SWIFT 2110 | 31.2472 | 140 | 0.056625 | 7.9275 | 1100 | 12827.6612 | 2927.7112 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6471 | SALMON CREEK 110137368 | 43161101 | SALMON CREEK 1101 | 6.0824 | 48 | 0.056596 | 2.7166 | 1101 | 12833.7436 | 2924.9946 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7036 | WOODACRE 1101CB | 43021101 | WOODACRE 1101 | 2.7686 | 35 | 0.056508 | 1.9778 | 1102 | 12836.5121 | 2923.0168 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9354 | FRUITLAND 114137410 | 192311141 | FRUITLAND 1141 | 5.2288 | 42 | 0.056472 | 2.3718 | 1103 | 12841.7409 | 2920.645 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8408 | GOLDTREE 1105CB | 182581105 | GOLDTREE 1105 | 7.4012 | 76 | 0.056447 | 4.29 | 1104 | 12849.1421 | 2916.355 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1036 | FRUITLAND 1142CB | 192311142 | FRUITLAND 1142 | 10.504 | 116 | 0.056321 | 6.5332 | 1105 | 12859.6461 | 2909.8218 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5437 | FITCH MOUNTAIN 1113775992 | 42751113 | FITCH MOUNTAIN 1113 | 2.1016 | 34 | 0.056251 | 1.9125 | 1106 | 12861.7477 | 2907.9093 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8868 | SALMON CREEK 1101461703 | 43161101 | SALMON CREEK 1101 | 0.87921 | 8 | 0.05614 | 0.44912 | 1107 | 12862.627 | 2907.4602 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1882 | SHINGLE SPRINGS 211051800 | 153652110 | SHINGLE SPRINGS 2110 | 9.1961 | 128 | 0.05603 | 7.1719 | 1108 | 12871.8231 | 2900.2883 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3611 | SANTA MARIA 1108M80 | 182671108 | SANTA MARIA 1108 | 58.257 | 397 | 0.055911 | 22.1966 | 1109 | 12930.0801 | 2878.0917 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6376 | MONTE RIO 11131991 | 42811113 | MONTE RIO 1113 | 7.1257 | 51 | 0.055786 | 2.8451 | 1110 | 12937.2058 | 2875.2466 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1111 | PEORIA 17056697 | 163781705 | PEORIA 1705 | 4.1376 | 46 | 0.055767 | 2.5653 | 1111 | 12941.3434 | 2872.6813 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3012 | RACETRACK 170311270 | 163761703 | RACETRACK 1703 | 12.6241 | 123 | 0.055685 | 6.8493 | 1112 | 12953.9675 | 2865.832 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
722 | MONTE RIO 11125040 | 42811112 | MONTE RIO 1112 | 4.0445 | 46 | 0.055628 | 2.5589 | 1113 | 12958.0119 | 2863.2731 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9716 | WINDSOR 1103171410 | 43501103 | WINDSOR 1103 | 1.3785 | 40 | 0.055603 | 2.2241 | 1114 | 12959.3904 | 2861.049 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
15 | MENDOCINO 1101450 | 42951101 | MENDOCINO 1101 | 5.7869 | 208 | 0.055438 | 11.531 | 1115 | 12965.1774 | 2849.518 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6036 | PLACER 1103CB | 152461103 | PLACER 1103 | 6.9691 | 99 | 0.05535 | 5.4797 | 1116 | 12972.1464 | 2844.0383 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6178 | GEYSERVILLE 110135492 | 42891101 | GEYSERVILLE 1101 | 9.9907 | 219 | 0.055239 | 12.0973 | 1117 | 12982.1371 | 2831.941 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6625 | WYANDOTTE 1107829470 | 102911107 | WYANDOTTE 1107 | 10.3139 | 93 | 0.055226 | 5.136 | 1118 | 12992.451 | 2826.805 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7721 | CURTIS 17058110 | 163351705 | CURTIS 1705 | 8.1481 | 99 | 0.055185 | 5.4634 | 1119 | 13000.5991 | 2821.3417 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8806 | CLAYTON 2212859443 | 12022212 | CLAYTON 2212 | 0.29539 | 5 | 0.055167 | 0.27584 | 1120 | 13000.8945 | 2821.0658 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8792 | DUNLAP 1103CB | 254061103 | DUNLAP 1103 | 5.6118 | 38 | 0.055113 | 2.0943 | 1121 | 13006.5063 | 2818.9715 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4534 | MERCED FALLS 110285002 | 252811102 | MERCED FALLS 1102 | 35.4838 | 394 | 0.055026 | 21.6802 | 1122 | 13041.9901 | 2797.2913 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2247 | FROGTOWN 170113412 | 163451701 | FROGTOWN 1701 | 38.8065 | 333 | 0.055018 | 18.321 | 1123 | 13080.7966 | 2778.9703 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3205 | COTATI 110361736 | 42271103 | COTATI 1103 | 12.1558 | 129 | 0.054986 | 7.0932 | 1124 | 13092.9524 | 2771.8771 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9516 | WILDWOOD 11011576 | 103611101 | WILDWOOD 1101 | 8.0638 | 51 | 0.054922 | 2.801 | 1125 | 13101.0162 | 2769.0761 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4729 | FITCH MOUNTAIN 1113352 | 42751113 | FITCH MOUNTAIN 1113 | 5.6471 | 123 | 0.054876 | 6.7498 | 1126 | 13106.6633 | 2762.3263 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6906 | IONE 1101CB | 163881101 | IONE 1101 | 1.8464 | 85 | 0.054859 | 4.663 | 1127 | 13108.5097 | 2757.6633 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1910 | FROGTOWN 17016807 | 163451701 | FROGTOWN 1701 | 4.9065 | 49 | 0.054517 | 2.6713 | 1128 | 13113.4162 | 2754.992 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1099 | HIGHLANDS 110275140 | 43361102 | HIGHLANDS 1102 | 8.6818 | 238 | 0.054483 | 12.967 | 1129 | 13122.098 | 2742.025 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9073 | CORRAL 1103831781 | 162991103 | CORRAL 1103 | 0.73719 | 19 | 0.054336 | 1.0324 | 1130 | 13122.8352 | 2740.9926 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1018 | APPLE HILL 21029722 | 153662102 | APPLE HILL 2102 | 38.8052 | 359 | 0.054308 | 19.4965 | 1131 | 13161.6404 | 2721.4961 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
882 | MORGAN HILL 2105XR152 | 83242105 | MORGAN HILL 2105 | 8.7296 | 156 | 0.054285 | 8.4685 | 1132 | 13170.3699 | 2713.0276 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7464 | CLARKSVILLE 2106CB | 153612106 | CLARKSVILLE 2106 | 0.1396 | 9 | 0.054215 | 0.48794 | 1133 | 13170.5095 | 2712.5396 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8313 | RED BLUFF 1104135854 | 103541104 | RED BLUFF 1104 | 1.4451 | 34 | 0.053974 | 1.8351 | 1134 | 13171.9546 | 2710.7045 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8191 | KESWICK 11011588 | 103451101 | KESWICK 1101 | 8.6957 | 33 | 0.053968 | 1.7809 | 1135 | 13180.6504 | 2708.9236 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5209 | OLETA 11022642 | 163541102 | OLETA 1102 | 4.6599 | 27 | 0.053841 | 1.4537 | 1136 | 13185.3103 | 2707.4699 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2961 | SYCAMORE CREEK 11112014 | 102971111 | SYCAMORE CREEK 1111 | 22.3643 | 181 | 0.053762 | 9.731 | 1137 | 13207.6746 | 2697.7389 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5221 | EL DORADO PH 210163464 | 152762101 | EL DORADO PH 2101 | 13.6239 | 70 | 0.05356 | 3.7492 | 1138 | 13221.2985 | 2693.9897 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1685 | WILLOW CREEK 110347966 | 192171103 | WILLOW CREEK 1103 | 16.9492 | 167 | 0.053445 | 8.9254 | 1139 | 13238.2477 | 2685.0643 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1361 | RED BLUFF 11051564 | 103541105 | RED BLUFF 1105 | 1.1756 | 133 | 0.053412 | 7.1038 | 1140 | 13239.4234 | 2677.9605 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
566 | MORGAN HILL 2110814616 | 83242110 | MORGAN HILL 2110 | 0.097826 | 28 | 0.053409 | 1.4955 | 1141 | 13239.5212 | 2676.4651 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9804 | FROGTOWN 1702694042 | 163451702 | FROGTOWN 1702 | 0.60413 | 8 | 0.053395 | 0.42716 | 1142 | 13240.1253 | 2676.0379 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
548 | SHINGLE SPRINGS 21107742 | 153652110 | SHINGLE SPRINGS 2110 | 45.7027 | 475 | 0.053392 | 25.3612 | 1143 | 13285.828 | 2650.6767 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4014 | CURTIS 1704CB | 163351704 | CURTIS 1704 | 13.8938 | 170 | 0.053282 | 9.058 | 1144 | 13299.7218 | 2641.6187 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5744 | WOODSIDE 11018974 | 24251101 | WOODSIDE 1101 | 13.2248 | 149 | 0.05299 | 7.8956 | 1145 | 13312.9466 | 2633.7232 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4200 | MOLINO 1101322 | 42571101 | MOLINO 1101 | 14.2081 | 167 | 0.052976 | 8.847 | 1146 | 13327.1547 | 2624.8762 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7680 | PALMER 1101M88 | 183031101 | PALMER 1101 | 3.0885 | 85 | 0.052933 | 4.4993 | 1147 | 13330.2431 | 2620.3768 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2401 | WOODSIDE 11018884 | 24251101 | WOODSIDE 1101 | 7.4789 | 74 | 0.052785 | 3.9061 | 1148 | 13337.7221 | 2616.4708 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5333 | GARBERVILLE 11022500 | 192221102 | GARBERVILLE 1102 | 16.0206 | 106 | 0.052654 | 5.5813 | 1149 | 13353.7427 | 2610.8895 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3787 | BEAR VALLEY 21014500 | 252192101 | BEAR VALLEY 2101 | 24.1783 | 516 | 0.052537 | 27.1089 | 1150 | 13377.921 | 2583.7806 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8553 | RED BLUFF 11041302 | 103541104 | RED BLUFF 1104 | 13.9155 | 113 | 0.052453 | 5.9272 | 1151 | 13391.8365 | 2577.8535 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10783 | BEAR VALLEY 2105CB | 252192105 | BEAR VALLEY 2105 | 3.838 | 9 | 0.052345 | 0.4711 | 1152 | 13395.6745 | 2577.3824 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10429 | BUTTE 1105244246 | 103081105 | BUTTE 1105 | 1.2034 | 11 | 0.052269 | 0.57496 | 1153 | 13396.8779 | 2576.8074 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1753 | BRUNSWICK 110651484 | 152481106 | BRUNSWICK 1106 | 15.3771 | 195 | 0.052211 | 10.1812 | 1154 | 13412.255 | 2566.6262 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7841 | STONE CORRAL 1110975698 | 252921110 | STONE CORRAL 1110 | 0.89608 | 44 | 0.052194 | 2.2966 | 1155 | 13413.1511 | 2564.3296 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10305 | MIDDLETOWN 1101612 | 43141101 | MIDDLETOWN 1101 | 3.9544 | 25 | 0.05213 | 1.3033 | 1156 | 13417.1055 | 2563.0264 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9510 | PUEBLO 2103776244 | 43292103 | PUEBLO 2103 | 0.17065 | 5 | 0.052117 | 0.26059 | 1157 | 13417.2762 | 2562.7658 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2874 | FORT ROSS 11214947 | 42851121 | FORT ROSS 1121 | 10.3498 | 56 | 0.052018 | 2.913 | 1158 | 13427.626 | 2559.8528 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5370 | FROGTOWN 17027108 | 163451702 | FROGTOWN 1702 | 9.6202 | 99 | 0.05186 | 5.1341 | 1159 | 13437.2462 | 2554.7187 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7742 | WEST POINT 110272036 | 163201102 | WEST POINT 1102 | 12.9673 | 105 | 0.051819 | 5.441 | 1160 | 13450.2135 | 2549.2777 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8013 | WILLITS 110337506 | 42661103 | WILLITS 1103 | 11.5613 | 77 | 0.051705 | 3.9812 | 1161 | 13461.7748 | 2545.2964 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8123 | OTTER 1102CB | 182941102 | OTTER 1102 | 6.7693 | 40 | 0.051564 | 2.0626 | 1162 | 13468.5441 | 2543.2338 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7649 | HARTLEY 1101CB | 43211101 | HARTLEY 1101 | 1.4678 | 33 | 0.051416 | 1.6967 | 1163 | 13470.0119 | 2541.5371 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4094 | HOPLAND 1101960 | 42251101 | HOPLAND 1101 | 3.8765 | 33 | 0.051413 | 1.6966 | 1164 | 13473.8884 | 2539.8405 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7517 | PENRYN 110790970 | 152561107 | PENRYN 1107 | 1.4404 | 45 | 0.051234 | 2.3055 | 1165 | 13475.3289 | 2537.535 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
371 | CURTIS 1701CB | 163351701 | CURTIS 1701 | 8.0631 | 159 | 0.051116 | 8.1275 | 1166 | 13483.392 | 2529.4074 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8728 | CORRAL 1103569005 | 162991103 | CORRAL 1103 | 0.71634 | 38 | 0.051027 | 1.939 | 1167 | 13484.1083 | 2527.4684 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3664 | PLACERVILLE 2106CB | 153082106 | PLACERVILLE 2106 | 6.554 | 31 | 0.050873 | 1.5771 | 1168 | 13490.6623 | 2525.8914 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10993 | MESA 1103737698 | 182821103 | MESA 1103 | 0.2019 | 3 | 0.050749 | 0.15225 | 1169 | 13490.8642 | 2525.7391 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7973 | PENRYN 110550548 | 152561105 | PENRYN 1105 | 0.095853 | 58 | 0.050695 | 2.9403 | 1170 | 13490.96 | 2522.7988 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9859 | CUYAMA 1103684566 | 253141103 | CUYAMA 1103 | 3.0185 | 4 | 0.050626 | 0.20251 | 1171 | 13493.9785 | 2522.5963 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7777 | GANSNER 11012424 | 103021101 | GANSNER 1101 | 18.7613 | 141 | 0.050559 | 7.1288 | 1172 | 13512.7398 | 2515.4675 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10622 | TEJON 1103286542 | 252931103 | TEJON 1103 | 2.1764 | 25 | 0.050527 | 1.2632 | 1173 | 13514.9162 | 2514.2043 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2224 | COTATI 1103148 | 42271103 | COTATI 1103 | 15.4446 | 107 | 0.050374 | 5.39 | 1174 | 13530.3608 | 2508.8143 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2728 | MESA 1103M72 | 182821103 | MESA 1103 | 8.4225 | 180 | 0.050224 | 9.0403 | 1175 | 13538.7833 | 2499.774 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4743 | WYANDOTTE 11031508 | 102911103 | WYANDOTTE 1103 | 27.2173 | 249 | 0.050062 | 12.4656 | 1176 | 13566.0006 | 2487.3085 | 2487.3085 | #N/A | TRUE | 18.7622 | TRUE | TRUE
1729 | LUCERNE 1106664 | 43351106 | LUCERNE 1106 | 9.6353 | 140 | 0.050043 | 7.006 | 1177 | 13575.6359 | 2480.3024 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1094 | HIGGINS 110332120 | 152691103 | HIGGINS 1103 | 40.6428 | 485 | 0.049959 | 24.23 | 1178 | 13616.2787 | 2456.0724 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1827 | BELL 11082226 | 152701108 | BELL 1108 | 24.0911 | 329 | 0.049738 | 16.3638 | 1179 | 13640.3699 | 2439.7086 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
971 | KANAKA 110183288 | 103221101 | KANAKA 1101 | 17.3628 | 140 | 0.049736 | 6.9631 | 1180 | 13657.7327 | 2432.7455 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6396 | MC ARTHUR 11011490 | 103491101 | MC ARTHUR 1101 | 10.5575 | 122 | 0.0497 | 6.0634 | 1181 | 13668.2901 | 2426.6822 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1501 | PIERCY 2110XR258 | 83912110 | PIERCY 2110 | 21.9439 | 117 | 0.049692 | 5.814 | 1182 | 13690.234 | 2420.8682 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4371 | BELLEVUE 2103552 | 43182103 | BELLEVUE 2103 | 9.4678 | 172 | 0.049565 | 8.5251 | 1183 | 13699.7017 | 2412.343 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
774 | MORGAN HILL 2110654924 | 83242110 | MORGAN HILL 2110 | 2.749 | 61 | 0.049343 | 3.0099 | 1184 | 13702.4507 | 2409.3331 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4796 | SISQUOC 1102M52 | 182811102 | SISQUOC 1102 | 33.8908 | 131 | 0.04915 | 6.4386 | 1185 | 13736.3415 | 2402.8945 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
899 | RACETRACK 170455798 | 163761704 | RACETRACK 1704 | 23.5467 | 246 | 0.049086 | 12.0752 | 1186 | 13759.8882 | 2390.8193 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8632 | STELLING 11102243 | 83481110 | STELLING 1110 | 1.8963 | 16 | 0.049051 | 0.78482 | 1187 | 13761.7845 | 2390.0345 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4409 | HIGGINS 11071070 | 152691107 | HIGGINS 1107 | 7.9153 | 100 | 0.048737 | 4.8737 | 1188 | 13769.6998 | 2385.1608 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2076 | SAN JUSTO 110136902 | 183181101 | SAN JUSTO 1101 | 12.4242 | 147 | 0.048735 | 7.1641 | 1189 | 13782.124 | 2377.9967 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6423 | TASSAJARA 2113MR276 | 14662113 | TASSAJARA 2113 | 3.8533 | 42 | 0.048684 | 2.0447 | 1190 | 13785.9773 | 2375.952 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7009 | PENRYN 110551676 | 152561105 | PENRYN 1105 | 8.0239 | 145 | 0.048603 | 7.0475 | 1191 | 13794.0012 | 2368.9045 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9522 | STONE CORRAL 1110894956 | 252921110 | STONE CORRAL 1110 | 0.77267 | 16 | 0.048471 | 0.77554 | 1192 | 13794.7739 | 2368.129 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4908 | DIVIDE 1103567884 | 182571103 | DIVIDE 1103 | 2.5019 | 27 | 0.048164 | 1.3004 | 1193 | 13797.2758 | 2366.8286 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
537 | FORT SEWARD 11211602 | 192321121 | FORT SEWARD 1121 | 18.2149 | 109 | 0.048111 | 5.244 | 1194 | 13815.4906 | 2361.5845 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
522 | MONTE RIO 1111292 | 42811111 | MONTE RIO 1111 | 15.5718 | 165 | 0.048057 | 7.9294 | 1195 | 13831.0625 | 2353.6552 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6679 | LAYTONVILLE 11011760 | 42681101 | LAYTONVILLE 1101 | 9.7018 | 73 | 0.048043 | 3.5072 | 1196 | 13840.7643 | 2350.148 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7262 | LOW GAP 11014160 | 192411101 | LOW GAP 1101 | 21.7466 | 194 | 0.047994 | 9.3109 | 1197 | 13862.5109 | 2340.8371 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2115 | GARBERVILLE 1102CB | 192221102 | GARBERVILLE 1102 | 11.9953 | 191 | 0.047992 | 9.1665 | 1198 | 13874.5063 | 2331.6707 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
859 | SALT SPRINGS 21011216 | 163692101 | SALT SPRINGS 2101 | 5.4829 | 32 | 0.04796 | 1.5347 | 1199 | 13879.9891 | 2330.136 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4717 | CAMBRIA 1101V76 | 182771101 | CAMBRIA 1101 | 18.9625 | 59 | 0.047925 | 2.8276 | 1200 | 13898.9516 | 2327.3084 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3890 | KANAKA 110165606 | 103221101 | KANAKA 1101 | 12.7444 | 145 | 0.047918 | 6.9481 | 1201 | 13911.696 | 2320.3603 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
11044 | SAN LUIS OBISPO 1104753254 | 182631104 | SAN LUIS OBISPO 1104 | 0.34876 | 2 | 0.047657 | 0.095314 | 1202 | 13912.0447 | 2320.2649 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
868 | PEORIA 170459596 | 163781704 | PEORIA 1704 | 20.8818 | 294 | 0.047553 | 13.9806 | 1203 | 13932.9265 | 2306.2844 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5643 | CLEAR LAKE 1102991285 | 42141102 | CLEAR LAKE 1102 | 0.32685 | 24 | 0.047469 | 1.1393 | 1204 | 13933.2534 | 2305.1451 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2996 | BURNEY 11012402 | 103311101 | BURNEY 1101 | 1.4989 | 18 | 0.047353 | 0.85235 | 1205 | 13934.7523 | 2304.2928 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
982 | WEST POINT 11024788 | 163201102 | WEST POINT 1102 | 69.5307 | 673 | 0.047319 | 31.8454 | 1206 | 14004.283 | 2272.4474 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6337 | MIWUK 170219772 | 163661702 | MIWUK 1702 | 3.8525 | 41 | 0.047283 | 1.9386 | 1207 | 14008.1354 | 2270.5088 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1317 | MOLINO 1102178 | 42571102 | MOLINO 1102 | 12.1979 | 182 | 0.047227 | 8.5954 | 1208 | 14020.3334 | 2261.9135 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2756 | AUBERRY 1101R2845 | 254151101 | AUBERRY 1101 | 17.8248 | 172 | 0.047182 | 8.1154 | 1209 | 14038.1581 | 2253.7981 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1878 | JESSUP 110168362 | 103441101 | JESSUP 1101 | 5.1662 | 96 | 0.047076 | 4.5193 | 1210 | 14043.3243 | 2249.2788 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1899 | SAN BENITO 2104785888 | 182742104 | SAN BENITO 2104 | 4.8047 | 49 | 0.047021 | 2.304 | 1211 | 14048.129 | 2246.9748 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1312 | MOUNTAIN QUARRIES 210192474 | 152282101 | MOUNTAIN QUARRIES 2101 | 15.1059 | 173 | 0.046937 | 8.12 | 1212 | 14063.2349 | 2238.8547 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9280 | FREMONT 1104MR339 | 14351104 | FREMONT 1104 | 1.1941 | 73 | 0.046887 | 3.4227 | 1213 | 14064.4289 | 2235.432 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10367 | PEORIA 170488630 | 163781704 | PEORIA 1704 | 0.77849 | 6 | 0.046842 | 0.28105 | 1214 | 14065.2074 | 2235.151 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3920 | LLAGAS 2107XR178 | 83182107 | LLAGAS 2107 | 5.9005 | 138 | 0.04683 | 6.4625 | 1215 | 14071.108 | 2228.6884 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9293 | DUNLAP 110239190 | 254061102 | DUNLAP 1102 | 1.7882 | 17 | 0.046743 | 0.79463 | 1216 | 14072.8962 | 2227.8938 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9995 | GEYSERVILLE 1102180193 | 42891102 | GEYSERVILLE 1102 | 2.161 | 23 | 0.046684 | 1.0737 | 1217 | 14075.0572 | 2226.82 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2795 | BELL 1108467470 | 152701108 | BELL 1108 | 1.857 | 40 | 0.046424 | 1.857 | 1218 | 14076.9142 | 2224.9631 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6866 | EDENVALE 1102XR064 | 82951102 | EDENVALE 1102 | 0.73065 | 35 | 0.046387 | 1.6236 | 1219 | 14077.6449 | 2223.3395 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2884 | MC ARTHUR 110137388 | 103491101 | MC ARTHUR 1101 | 8.1109 | 56 | 0.046193 | 2.5868 | 1220 | 14085.7557 | 2220.7527 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8090 | PENRYN 1105817491 | 152561105 | PENRYN 1105 | 1.4167 | 24 | 0.046183 | 1.1084 | 1221 | 14087.1724 | 2219.6443 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
196 | MILPITAS 1109XR082 | 82831109 | MILPITAS 1109 | 19.6858 | 186 | 0.046133 | 8.5807 | 1222 | 14106.8583 | 2211.0636 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9874 | JARVIS 1108767280 | 13501108 | JARVIS 1108 | 0.5074 | 11 | 0.046117 | 0.50728 | 1223 | 14107.3657 | 2210.5563 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3653 | PUEBLO 2103678 | 43292103 | PUEBLO 2103 | 35.3374 | 325 | 0.046077 | 14.9751 | 1224 | 14142.7031 | 2195.5812 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4529 | MC ARTHUR 110138998 | 103491101 | MC ARTHUR 1101 | 0.11777 | 61 | 0.046064 | 2.8099 | 1225 | 14142.8208 | 2192.7713 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9562 | MOLINO 1101600112 | 42571101 | MOLINO 1101 | 0.798 | 18 | 0.045774 | 0.82393 | 1226 | 14143.6188 | 2191.9473 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8471 | MONTICELLO 1101654 | 43051101 | MONTICELLO 1101 | 8.2164 | 71 | 0.045547 | 3.2338 | 1227 | 14151.8352 | 2188.7135 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9084 | SWIFT 2110XR254 | 83392110 | SWIFT 2110 | 25.1775 | 134 | 0.045544 | 6.1028 | 1228 | 14177.0127 | 2182.6107 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5247 | MOLINO 1102658 | 42571102 | MOLINO 1102 | 10.8829 | 107 | 0.045341 | 4.8515 | 1229 | 14187.8955 | 2177.7592 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1624 | CLAY 11037124 | 163341103 | CLAY 1103 | 11.0615 | 286 | 0.045279 | 12.9498 | 1230 | 14198.9571 | 2164.8094 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6683 | UKIAH 11143606 | 42771114 | UKIAH 1114 | 10.702 | 129 | 0.045178 | 5.828 | 1231 | 14209.6591 | 2158.9814 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6114 | GANSNER 110137550 | 103021101 | GANSNER 1101 | 0.36702 | 33 | 0.045042 | 1.4864 | 1232 | 14210.0261 | 2157.495 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10276 | LAKEVILLE 1102367100 | 43371102 | LAKEVILLE 1102 | 0.55985 | 6 | 0.04493 | 0.26958 | 1233 | 14210.5859 | 2157.2254 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3592 | CURTIS 17039330 | 163351703 | CURTIS 1703 | 41.3401 | 345 | 0.044648 | 15.4037 | 1234 | 14251.9261 | 2141.8217 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1338 | SILVERADO 210437632 | 43432104 | SILVERADO 2104 | 26.5819 | 304 | 0.044601 | 13.5588 | 1235 | 14278.508 | 2128.2629 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9592 | BELL 1107912460 | 152701107 | BELL 1107 | 0.1406 | 6 | 0.044495 | 0.26697 | 1236 | 14278.6486 | 2127.996 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9543 | GARBERVILLE 110237054 | 192221102 | GARBERVILLE 1102 | 8.9461 | 76 | 0.044439 | 3.3774 | 1237 | 14287.5946 | 2124.6186 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
528 | PLACERVILLE 210692012 | 153082106 | PLACERVILLE 2106 | 18.5175 | 219 | 0.044304 | 9.7026 | 1238 | 14306.1121 | 2114.916 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2289 | PASO ROBLES 1103351084 | 182611103 | PASO ROBLES 1103 | 2.3702 | 91 | 0.044255 | 4.0272 | 1239 | 14308.4824 | 2110.8888 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4151 | SHINGLE SPRINGS 2109CB | 153652109 | SHINGLE SPRINGS 2109 | 27.3462 | 341 | 0.044085 | 15.0331 | 1240 | 14335.8286 | 2095.8557 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8694 | MC ARTHUR 11011544 | 103491101 | MC ARTHUR 1101 | 16.9615 | 135 | 0.044056 | 5.9476 | 1241 | 14352.7901 | 2089.9081 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5303 | STONE CORRAL 11087100 | 252921108 | STONE CORRAL 1108 | 2.3355 | 130 | 0.04396 | 5.7148 | 1242 | 14355.1256 | 2084.1933 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5138 | SUMMIT 11022302 | 152591102 | SUMMIT 1102 | 1.3381 | 19 | 0.043905 | 0.8342 | 1243 | 14356.4637 | 2083.3591 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3403 | PENRYN 11051378 | 152561105 | PENRYN 1105 | 0.89964 | 25 | 0.043839 | 1.096 | 1244 | 14357.3633 | 2082.2631 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5562 | GARBERVILLE 110139524 | 192221101 | GARBERVILLE 1101 | 5.1162 | 138 | 0.04372 | 6.0334 | 1245 | 14362.4795 | 2076.2298 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3303 | BIG BEND 1101180398 | 103751101 | BIG BEND 1101 | 5.56 | 48 | 0.04366 | 2.0957 | 1246 | 14368.0395 | 2074.1341 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5481 | VACAVILLE 110847860 | 63601108 | VACAVILLE 1108 | 0.28963 | 54 | 0.043573 | 2.353 | 1247 | 14368.3291 | 2071.7811 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8994 | SAN LUIS OBISPO 1104982992 | 182631104 | SAN LUIS OBISPO 1104 | 8.9436 | 52 | 0.043526 | 2.2633 | 1248 | 14377.2727 | 2069.5178 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6482 | UKIAH 1113691436 | 42771113 | UKIAH 1113 | 1.0446 | 28 | 0.043449 | 1.2166 | 1249 | 14378.3173 | 2068.3012 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7283 | COVELO 1101112804 | 43061101 | COVELO 1101 | 10.2626 | 67 | 0.043443 | 2.9107 | 1250 | 14388.5799 | 2065.3906 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2688 | STILLWATER 11021466 | 103561102 | STILLWATER 1102 | 20.5343 | 211 | 0.043245 | 9.1248 | 1251 | 14409.1142 | 2056.2658 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6122 | EEL RIVER 11024814 | 192381102 | EEL RIVER 1102 | 26.9939 | 117 | 0.043216 | 5.0562 | 1252 | 14436.1081 | 2051.2096 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8658 | MENLO 11037902 | 24131103 | MENLO 1103 | 11.6992 | 143 | 0.043162 | 6.1722 | 1253 | 14447.8072 | 2045.0373 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5986 | SILVERADO 210478268 | 43432104 | SILVERADO 2104 | 9.7249 | 114 | 0.043133 | 4.9171 | 1254 | 14457.5321 | 2040.1202 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3705 | ALTO 11221212 | 42031122 | ALTO 1122 | 1.8503 | 25 | 0.043056 | 1.0764 | 1255 | 14459.3824 | 2039.0438 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
565 | CALPELLA 1101CB | 43411101 | CALPELLA 1101 | 11.7762 | 226 | 0.043018 | 9.722 | 1256 | 14471.1587 | 2029.3218 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1815 | OTTER 110298036 | 182941102 | OTTER 1102 | 9.2007 | 64 | 0.042868 | 2.7435 | 1257 | 14480.3594 | 2026.5782 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5821 | HIGHLANDS 11034630 | 43361103 | HIGHLANDS 1103 | 1.0747 | 42 | 0.042814 | 1.7982 | 1258 | 14481.4341 | 2024.78 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1927 | HIGGINS 1110166282 | 152691110 | HIGGINS 1110 | 23.9909 | 256 | 0.042498 | 10.8796 | 1259 | 14505.425 | 2013.9005 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6705 | GIRVAN 11021028 | 103401102 | GIRVAN 1102 | 17.6533 | 208 | 0.042483 | 8.8364 | 1260 | 14523.0782 | 2005.0641 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3470 | OILFIELDS 1103370932 | 182391103 | OILFIELDS 1103 | 0.38529 | 6 | 0.042464 | 0.25478 | 1261 | 14523.4635 | 2004.8093 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9825 | GIRVAN 1101CB | 103401101 | GIRVAN 1101 | 1.5361 | 31 | 0.042406 | 1.3146 | 1262 | 14524.9996 | 2003.4947 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4531 | CRESCENT MILLS 21013113 | 103132101 | CRESCENT MILLS 2101 | 1.1931 | 9 | 0.042389 | 0.3815 | 1263 | 14526.1927 | 2003.1132 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4502 | WILLITS 1103968 | 42661103 | WILLITS 1103 | 26.7055 | 283 | 0.042383 | 11.9944 | 1264 | 14552.8982 | 1991.1188 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
293 | MENDOCINO 110131322 | 42951101 | MENDOCINO 1101 | 5.8546 | 310 | 0.04237 | 13.1348 | 1265 | 14558.7527 | 1977.984 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
332 | MESA 1101CB | 182821101 | MESA 1101 | 13.8593 | 230 | 0.042367 | 9.7444 | 1266 | 14572.6121 | 1968.2396 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6761 | HORSESHOE 11011682 | 152571101 | HORSESHOE 1101 | 0.20299 | 112 | 0.042324 | 4.7402 | 1267 | 14572.8151 | 1963.4994 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4789 | APPLE HILL 110412842 | 153661104 | APPLE HILL 1104 | 15.8199 | 209 | 0.042311 | 8.8429 | 1268 | 14588.6349 | 1954.6565 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5435 | SUNOL 1101MR299 | 14241101 | SUNOL 1101 | 4.9442 | 58 | 0.042276 | 2.452 | 1269 | 14593.5791 | 1952.2045 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5875 | MESA 11016113 | 182821101 | MESA 1101 | 1.7404 | 100 | 0.042268 | 4.2268 | 1270 | 14595.3195 | 1947.9777 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6536 | PINE GROVE 11026080 | 163751102 | PINE GROVE 1102 | 34.374 | 322 | 0.042249 | 13.6042 | 1271 | 14629.6935 | 1934.3734 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10453 | RIO DELL 11027124 | 192251102 | RIO DELL 1102 | 0.67208 | 5 | 0.042229 | 0.21114 | 1272 | 14630.3656 | 1934.1623 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9767 | SAN BERNARD 1101641042 | 253191101 | SAN BERNARD 1101 | 1.4299 | 22 | 0.042194 | 0.92827 | 1273 | 14631.7956 | 1933.234 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7173 | OTTER 110237132 | 182941102 | OTTER 1102 | 5.8068 | 50 | 0.042173 | 2.1086 | 1274 | 14637.6024 | 1931.1254 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7839 | FROGTOWN 1702204480 | 163451702 | FROGTOWN 1702 | 0.50198 | 28 | 0.04209 | 1.1785 | 1275 | 14638.1044 | 1929.9469 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1556 | HOPLAND 110180620 | 42251101 | HOPLAND 1101 | 1.2417 | 51 | 0.04205 | 2.1446 | 1276 | 14639.3461 | 1927.8023 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
796 | MESA 1101M86 | 182821101 | MESA 1101 | 12.7414 | 217 | 0.041844 | 9.0801 | 1277 | 14652.0875 | 1918.7222 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4020 | CABRILLO 1103Y10 | 183101103 | CABRILLO 1103 | 4.8408 | 122 | 0.041779 | 5.0971 | 1278 | 14656.9283 | 1913.6251 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4294 | FITCH MOUNTAIN 11134566 | 42751113 | FITCH MOUNTAIN 1113 | 12.5097 | 180 | 0.041761 | 7.5169 | 1279 | 14669.438 | 1906.1082 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3368 | PEORIA 17051834 | 163781705 | PEORIA 1705 | 23.5691 | 217 | 0.041581 | 9.0231 | 1280 | 14693.0071 | 1897.0852 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4811 | CALAVERAS CEMENT 1101502 | 162211101 | CALAVERAS CEMENT 1101 | 37.6576 | 331 | 0.041554 | 13.7543 | 1281 | 14730.6646 | 1883.3309 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8493 | COTATI 1102282 | 42271102 | COTATI 1102 | 2.7813 | 62 | 0.041526 | 2.5746 | 1282 | 14733.4459 | 1880.7562 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3229 | WISE 1102CB | 152271102 | WISE 1102 | 14.0667 | 177 | 0.041442 | 7.3353 | 1283 | 14747.5126 | 1873.4209 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2423 | APPLE HILL 110413512 | 153661104 | APPLE HILL 1104 | 28.4598 | 345 | 0.041392 | 14.2801 | 1284 | 14775.9724 | 1859.1408 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3013 | BIG MEADOWS 21012586 | 102812101 | BIG MEADOWS 2101 | 6.2589 | 91 | 0.041237 | 3.7526 | 1285 | 14782.2313 | 1855.3882 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6401 | COPPERMINE 1104556430 | 252411104 | COPPERMINE 1104 | 4.8433 | 122 | 0.041063 | 5.0096 | 1286 | 14787.0746 | 1850.3785 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9989 | ORO FINO 11022236 | 103031102 | ORO FINO 1102 | 2.5609 | 11 | 0.040994 | 0.45093 | 1287 | 14789.6355 | 1849.9276 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3633 | BIG BEND 11021972 | 103751102 | BIG BEND 1102 | 21.2964 | 177 | 0.040961 | 7.25 | 1288 | 14810.932 | 1842.6776 | 1842.6776 | #N/A | TRUE | 32.1473 | TRUE | TRUE
7419 | MARTELL 110299214 | 163011102 | MARTELL 1102 | 1.8356 | 21 | 0.040838 | 0.85759 | 1289 | 14812.7676 | 1841.82 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5589 | BUELLTON 1101Y36 | 183041101 | BUELLTON 1101 | 37.7365 | 283 | 0.0408 | 11.5464 | 1290 | 14850.5041 | 1830.2737 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2824 | GEYSERVILLE 1101166 | 42891101 | GEYSERVILLE 1101 | 6.1958 | 110 | 0.040759 | 4.4835 | 1291 | 14856.6999 | 1825.7901 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
612 | DIAMOND SPRINGS 11062100 | 152261106 | DIAMOND SPRINGS 1106 | 39.0796 | 403 | 0.040696 | 16.4004 | 1292 | 14895.7795 | 1809.3897 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4758 | LAYTONVILLE 1101402 | 42681101 | LAYTONVILLE 1101 | 23.359 | 151 | 0.040695 | 6.145 | 1293 | 14919.1385 | 1803.2447 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7625 | ATASCADERO 1103440856 | 182541103 | ATASCADERO 1103 | 34.8114 | 349 | 0.040647 | 14.1857 | 1294 | 14953.9499 | 1789.059 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3291 | FRUITLAND 11426054 | 192311142 | FRUITLAND 1142 | 7.1968 | 58 | 0.040642 | 2.3572 | 1295 | 14961.1467 | 1786.7018 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2753 | CALPELLA 11011204 | 43411101 | CALPELLA 1101 | 9.4816 | 124 | 0.040535 | 5.0263 | 1296 | 14970.6283 | 1781.6755 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6226 | FULTON 1107214 | 42561107 | FULTON 1107 | 11.7268 | 142 | 0.040503 | 5.7514 | 1297 | 14982.3551 | 1775.924 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6297 | PEORIA 170176030 | 163781701 | PEORIA 1701 | 5.1103 | 55 | 0.040366 | 2.2201 | 1298 | 14987.4654 | 1773.7039 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4946 | WYANDOTTE 11031976 | 102911103 | WYANDOTTE 1103 | 23.7815 | 217 | 0.040282 | 8.7412 | 1299 | 15011.2469 | 1764.9627 | 1764.9627 | #N/A | TRUE | 31.1777 | TRUE | TRUE
3803 | CALAVERAS CEMENT 1101CB | 162211101 | CALAVERAS CEMENT 1101 | 10.4702 | 203 | 0.040232 | 8.1671 | 1300 | 15021.717 | 1756.7956 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
601 | FORESTHILL 11022106 | 152181102 | FORESTHILL 1102 | 27.8816 | 264 | 0.040196 | 10.6117 | 1301 | 15049.5987 | 1746.1839 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3937 | AUBERRY 1101176050 | 254151101 | AUBERRY 1101 | 21.128 | 168 | 0.040157 | 6.7464 | 1302 | 15070.7267 | 1739.4374 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3563 | SHINGLE SPRINGS 21092053 | 153652109 | SHINGLE SPRINGS 2109 | 5.7415 | 74 | 0.040131 | 2.9697 | 1303 | 15076.4681 | 1736.4677 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
639 | LAYTONVILLE 1101CB | 42681101 | LAYTONVILLE 1101 | 5.954 | 90 | 0.040116 | 3.6104 | 1304 | 15082.4222 | 1732.8573 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8583 | UKIAH 1111168892 | 42771111 | UKIAH 1111 | 0.16428 | 8 | 0.040099 | 0.32079 | 1305 | 15082.5864 | 1732.5365 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6071 | SHINGLE SPRINGS 210981390 | 153652109 | SHINGLE SPRINGS 2109 | 18.6189 | 208 | 0.039915 | 8.3022 | 1306 | 15101.2053 | 1724.2343 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5271 | WILLITS 1104504 | 42661104 | WILLITS 1104 | 22.5315 | 205 | 0.039748 | 8.1484 | 1307 | 15123.7368 | 1716.0859 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8156 | PIKE CITY 1102CB | 152201102 | PIKE CITY 1102 | 9.5189 | 44 | 0.03956 | 1.7406 | 1308 | 15133.2557 | 1714.3452 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1834 | CASTRO VALLEY 1110MR748 | 14091110 | CASTRO VALLEY 1110 | 6.2313 | 86 | 0.039516 | 3.3984 | 1309 | 15139.487 | 1710.9468 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4232 | GABILAN 1101989608 | 182331101 | GABILAN 1101 | 0.75178 | 6 | 0.039513 | 0.23708 | 1310 | 15140.2388 | 1710.7098 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2029 | OCEANO 1102V56 | 182601102 | OCEANO 1102 | 9.3367 | 115 | 0.039442 | 4.5359 | 1311 | 15149.5755 | 1706.1739 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6282 | MOLINO 1101891 | 42571101 | MOLINO 1101 | 3.1513 | 41 | 0.03939 | 1.615 | 1312 | 15152.7268 | 1704.5589 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7224 | MIRABEL 1101116 | 42091101 | MIRABEL 1101 | 10.3331 | 112 | 0.039363 | 4.4087 | 1313 | 15163.0599 | 1700.1502 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3752 | MONTE RIO 1113539938 | 42811113 | MONTE RIO 1113 | 2.7721 | 26 | 0.039354 | 1.0232 | 1314 | 15165.8319 | 1699.127 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8901 | BRIDGEVILLE 110237486 | 192461102 | BRIDGEVILLE 1102 | 6.9374 | 85 | 0.039237 | 3.3351 | 1315 | 15172.7693 | 1695.7919 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3640 | FROGTOWN 1702CB | 163451702 | FROGTOWN 1702 | 1.4614 | 47 | 0.039234 | 1.844 | 1316 | 15174.2307 | 1693.9479 | 1693.9479 | #N/A | TRUE | 1.2739 | TRUE | TRUE
4627 | SAN LUIS OBISPO 1107V02 | 182631107 | SAN LUIS OBISPO 1107 | 18.189 | 202 | 0.039184 | 7.9151 | 1317 | 15192.4197 | 1686.0327 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2477 | CEDAR CREEK 11011656 | 103321101 | CEDAR CREEK 1101 | 32.2308 | 208 | 0.039176 | 8.1485 | 1318 | 15224.6505 | 1677.8842 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6350 | NAPA 11121302 | 42021112 | NAPA 1112 | 20.0955 | 317 | 0.039053 | 12.3798 | 1319 | 15244.7461 | 1665.5044 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
798 | HIGGINS 1107CB | 152691107 | HIGGINS 1107 | 5.7283 | 243 | 0.03873 | 9.4114 | 1320 | 15250.4743 | 1656.093 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10498 | CLAYTON 2212158138 | 12022212 | CLAYTON 2212 | 0.5155 | 10 | 0.038704 | 0.38704 | 1321 | 15250.9898 | 1655.706 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9150 | SPANISH CREEK 4401CB | 103104401 | SPANISH CREEK 4401 | 7.7363 | 22 | 0.038702 | 0.85144 | 1322 | 15258.7262 | 1654.8545 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
561 | ALTO 11221260 | 42031122 | ALTO 1122 | 2.9876 | 36 | 0.038665 | 1.3919 | 1323 | 15261.7138 | 1653.4626 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2054 | PUEBLO 1104580658 | 43291104 | PUEBLO 1104 | 9.3918 | 107 | 0.038518 | 4.1214 | 1324 | 15271.1056 | 1649.3412 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3362 | REDBUD 110191960 | 43191101 | REDBUD 1101 | 6.5181 | 90 | 0.038488 | 3.4639 | 1325 | 15277.6237 | 1645.8773 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3879 | WILLITS 11032506 | 42661103 | WILLITS 1103 | 12.608 | 89 | 0.038425 | 3.4198 | 1326 | 15290.2317 | 1642.4575 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2472 | SANTA ROSA A 1104220 | 42151104 | SANTA ROSA A 1104 | 9.5948 | 105 | 0.038284 | 4.0198 | 1327 | 15299.8265 | 1638.4376 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2655 | TEMPLETON 2110R90 | 183052110 | TEMPLETON 2110 | 30.1931 | 259 | 0.038279 | 9.9144 | 1328 | 15330.0196 | 1628.5233 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4442 | OCEANO 1104Q06 | 182601104 | OCEANO 1104 | 12.4701 | 154 | 0.038111 | 5.8691 | 1329 | 15342.4896 | 1622.6542 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3161 | MARTELL 110368192 | 163011103 | MARTELL 1103 | 2.7363 | 72 | 0.037972 | 2.734 | 1330 | 15345.2259 | 1619.9202 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7038 | MIRABEL 1102334 | 42091102 | MIRABEL 1102 | 5.9568 | 84 | 0.037896 | 3.1833 | 1331 | 15351.1827 | 1616.7369 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6568 | GEYSERVILLE 110137454 | 42891101 | GEYSERVILLE 1101 | 6.5152 | 114 | 0.037721 | 4.3002 | 1332 | 15357.6979 | 1612.4367 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9085 | SAN LUIS OBISPO 1107V62 | 182631107 | SAN LUIS OBISPO 1107 | 6.904 | 50 | 0.037409 | 1.8704 | 1333 | 15364.6019 | 1610.5663 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3181 | SONOMA 110478372 | 42721104 | SONOMA 1104 | 16.6264 | 198 | 0.037304 | 7.3862 | 1334 | 15381.2283 | 1603.1801 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
296 | TASSAJARA 2112D514R | 14662112 | TASSAJARA 2112 | 3.1274 | 73 | 0.037278 | 2.7213 | 1335 | 15384.3557 | 1600.4588 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5732 | SWIFT 2107XR526 | 83392107 | SWIFT 2107 | 2.0918 | 64 | 0.037122 | 2.3758 | 1336 | 15386.4474 | 1598.083 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4671 | PURISIMA 1101Y42 | 182971101 | PURISIMA 1101 | 3.4981 | 127 | 0.037118 | 4.714 | 1337 | 15389.9456 | 1593.369 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7642 | PENRYN 1105168616 | 152561105 | PENRYN 1105 | 3.1566 | 102 | 0.03705 | 3.7791 | 1338 | 15393.1022 | 1589.5899 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2287 | OCEANO 1104104102 | 182601104 | OCEANO 1104 | 3.3123 | 32 | 0.03704 | 1.1853 | 1339 | 15396.4145 | 1588.4046 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9499 | OILFIELDS 1103N46 | 182391103 | OILFIELDS 1103 | 5.8177 | 29 | 0.036988 | 1.0726 | 1340 | 15402.2322 | 1587.332 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5619 | NARROWS 21052426 | 153132105 | NARROWS 2105 | 8.566 | 226 | 0.036874 | 8.3335 | 1341 | 15410.7982 | 1578.9985 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3889 | RINCON 1103474 | 43321103 | RINCON 1103 | 18.3351 | 174 | 0.036813 | 6.4055 | 1342 | 15429.1333 | 1572.593 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6070 | CRESCENT MILLS 21012230 | 103132101 | CRESCENT MILLS 2101 | 6.8196 | 112 | 0.036587 | 4.0978 | 1343 | 15435.9529 | 1568.4952 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7395 | HALF MOON BAY 11018902 | 24101101 | HALF MOON BAY 1101 | 14.1623 | 145 | 0.036496 | 5.2919 | 1344 | 15450.1152 | 1563.2033 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8155 | PIT NO 5 11011606 | 101321101 | PIT NO 5 1101 | 5.527 | 40 | 0.036482 | 1.4593 | 1345 | 15455.6422 | 1561.744 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6340 | ELECTRA 11011238 | 162161101 | ELECTRA 1101 | 3.6201 | 81 | 0.036431 | 2.9509 | 1346 | 15459.2622 | 1558.7932 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
988 | FROGTOWN 1701CB | 163451701 | FROGTOWN 1701 | 10.062 | 76 | 0.036334 | 2.7614 | 1347 | 15469.3242 | 1556.0317 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6703 | POTTER VALLEY P H 110576498 | 42281105 | POTTER VALLEY P H 1105 | 14.8806 | 119 | 0.036331 | 4.3234 | 1348 | 15484.2049 | 1551.7084 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10138 | LLAGAS 2107870396 | 83182107 | LLAGAS 2107 | 0.82442 | 40 | 0.036327 | 1.4531 | 1349 | 15485.0293 | 1550.2553 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7528 | LAYTONVILLE 110189606 | 42681101 | LAYTONVILLE 1101 | 11.6322 | 100 | 0.036226 | 3.6226 | 1350 | 15496.6615 | 1546.6327 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1489 | CURTIS 1702CB | 163351702 | CURTIS 1702 | 22.0674 | 293 | 0.036175 | 10.5993 | 1351 | 15518.7289 | 1536.0334 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3159 | SALMON CREEK 1101194 | 43161101 | SALMON CREEK 1101 | 6.7792 | 62 | 0.03614 | 2.2407 | 1352 | 15525.5081 | 1533.7927 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5649 | MORGAN HILL 2111XR186 | 83242111 | MORGAN HILL 2111 | 2.8908 | 191 | 0.036035 | 6.8827 | 1353 | 15528.3989 | 1526.91 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
972 | BRUNSWICK 11062392 | 152481106 | BRUNSWICK 1106 | 6.098 | 111 | 0.036 | 3.996 | 1354 | 15534.4969 | 1522.914 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4961 | TEMPLETON 2110R94 | 183052110 | TEMPLETON 2110 | 13.9097 | 179 | 0.035946 | 6.4343 | 1355 | 15548.4066 | 1516.4797 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2592 | CAYUCOS 11014701 | 182551101 | CAYUCOS 1101 | 2.1061 | 65 | 0.035932 | 2.3356 | 1356 | 15550.5127 | 1514.1441 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
160 | MOUNTAIN QUARRIES 21011346 | 152282101 | MOUNTAIN QUARRIES 2101 | 30.8214 | 410 | 0.035841 | 14.6948 | 1357 | 15581.3341 | 1499.4493 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3187 | SAN MIGUEL 1104R58 | 182661104 | SAN MIGUEL 1104 | 0.54102 | 130 | 0.035811 | 4.6554 | 1358 | 15581.8751 | 1494.7939 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8179 | LOS OSITOS 21037062 | 182082103 | LOS OSITOS 2103 | 12.2213 | 53 | 0.035805 | 1.8977 | 1359 | 15594.0965 | 1492.8962 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7911 | OAKLAND K 110217430 | 12101102 | OAKLAND K 1102 | 1.4697 | 15 | 0.035767 | 0.5365 | 1360 | 15595.5662 | 1492.3597 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
88 | SILVERADO 2105658898 | 43432105 | SILVERADO 2105 | 17.1737 | 151 | 0.035763 | 5.4002 | 1361 | 15612.7399 | 1486.9595 | #N/A | 1486.9595 | FALSE | 0 | TRUE | TRUE
2757 | BURNEY 11011358 | 103311101 | BURNEY 1101 | 8.4314 | 51 | 0.035574 | 1.8143 | 1362 | 15621.1713 | 1485.1452 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2335 | PLACERVILLE 21067522 | 153082106 | PLACERVILLE 2106 | 67.3656 | 745 | 0.035529 | 26.4689 | 1363 | 15688.537 | 1458.6763 | 1458.6763 | #N/A | TRUE | 1.35 | TRUE | TRUE
10054 | GARBERVILLE 110197300 | 192221101 | GARBERVILLE 1101 | 3.2078 | 32 | 0.035439 | 1.1341 | 1364 | 15691.7448 | 1457.5422 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2680 | SAN RAMON 2107MR284 | 14232107 | SAN RAMON 2107 | 14.6886 | 134 | 0.035373 | 4.7399 | 1365 | 15706.4333 | 1452.8023 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6323 | FORT ROSS 112170288 | 42851121 | FORT ROSS 1121 | 11.7339 | 94 | 0.035369 | 3.3247 | 1366 | 15718.1672 | 1449.4776 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4070 | CLAYTON 2213CB | 12022213 | CLAYTON 2213 | 3.8725 | 51 | 0.03535 | 1.8029 | 1367 | 15722.0398 | 1447.6747 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5947 | GARCIA 0401666 | 43040401 | GARCIA 0401 | 2.4068 | 12 | 0.035311 | 0.42373 | 1368 | 15724.4466 | 1447.251 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8699 | UKIAH 1113548420 | 42771113 | UKIAH 1113 | 5.2018 | 54 | 0.035261 | 1.9041 | 1369 | 15729.6484 | 1445.3469 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7081 | NOVATO 110455398 | 42211104 | NOVATO 1104 | 3.6541 | 82 | 0.035221 | 2.8881 | 1370 | 15733.3025 | 1442.4588 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2938 | PETALUMA C 110948000 | 42631109 | PETALUMA C 1109 | 9.4991 | 115 | 0.035167 | 4.0442 | 1371 | 15742.8016 | 1438.4145 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9847 | PENRYN 1105CB | 152561105 | PENRYN 1105 | 0.60814 | 7 | 0.035133 | 0.24593 | 1372 | 15743.4097 | 1438.1686 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1921 | WYANDOTTE 110641650 | 102911106 | WYANDOTTE 1106 | 1.1575 | 152 | 0.035126 | 5.3392 | 1373 | 15744.5672 | 1432.8294 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7481 | OTTER 11012052 | 182941101 | OTTER 1101 | 4.8364 | 53 | 0.034981 | 1.854 | 1374 | 15749.4036 | 1430.9754 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3295 | REDBUD 1102510 | 43191102 | REDBUD 1102 | 4.2062 | 101 | 0.03495 | 3.5299 | 1375 | 15753.6097 | 1427.4454 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4887 | WOODSIDE 11018972 | 24251101 | WOODSIDE 1101 | 6.2151 | 60 | 0.034933 | 2.096 | 1376 | 15759.8249 | 1425.3494 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9433 | JAMESON 11028842 | 63801102 | JAMESON 1102 | 0.14985 | 42 | 0.03478 | 1.4608 | 1377 | 15759.9747 | 1423.8887 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5225 | SHADY GLEN 110248894 | 152431102 | SHADY GLEN 1102 | 8.8833 | 119 | 0.034658 | 4.1244 | 1378 | 15768.858 | 1419.7643 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4594 | WEIMAR 11012058 | 152491101 | WEIMAR 1101 | 21.327 | 256 | 0.034582 | 8.853 | 1379 | 15790.185 | 1410.9113 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10315 | CLAYTON 2212523764 | 12022212 | CLAYTON 2212 | 0.11036 | 5 | 0.034478 | 0.17239 | 1380 | 15790.2954 | 1410.7389 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4872 | SUNOL 1101MR196 | 14241101 | SUNOL 1101 | 3.9361 | 96 | 0.034417 | 3.304 | 1381 | 15794.2315 | 1407.4349 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1388 | MIWUK 170193062 | 163661701 | MIWUK 1701 | 8.2823 | 84 | 0.034301 | 2.8813 | 1382 | 15802.5138 | 1404.5537 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10333 | SAN ARDO 1101650772 | 182191101 | SAN ARDO 1101 | 0.78395 | 10 | 0.03426 | 0.3426 | 1383 | 15803.2977 | 1404.2111 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
132 | APPLE HILL 1103CB | 153661103 | APPLE HILL 1103 | 19.3465 | 268 | 0.034245 | 9.1777 | 1384 | 15822.6442 | 1395.0334 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7451 | LOW GAP 1101CB | 192411101 | LOW GAP 1101 | 2.1692 | 23 | 0.034029 | 0.78267 | 1385 | 15824.8135 | 1394.2507 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10038 | JESSUP 110194468 | 103441101 | JESSUP 1101 | 1.7135 | 21 | 0.033993 | 0.71385 | 1386 | 15826.527 | 1393.5368 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3608 | PIT NO 1 11011552 | 103721101 | PIT NO 1 1101 | 14.8177 | 221 | 0.033912 | 7.4946 | 1387 | 15841.3446 | 1386.0422 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5359 | SAN LUIS OBISPO 1104CB | 182631104 | SAN LUIS OBISPO 1104 | 0.077221 | 65 | 0.033863 | 2.2011 | 1388 | 15841.4218 | 1383.8412 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9613 | REEDLEY 1112477952 | 252341112 | REEDLEY 1112 | 0.17579 | 14 | 0.033843 | 0.47381 | 1389 | 15841.5976 | 1383.3674 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6901 | JESSUP 11019752 | 103441101 | JESSUP 1101 | 3.8145 | 41 | 0.033837 | 1.3873 | 1390 | 15845.4121 | 1381.98 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8898 | RACETRACK 17036014 | 163761703 | RACETRACK 1703 | 6.9405 | 73 | 0.033829 | 2.4695 | 1391 | 15852.3526 | 1379.5105 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7674 | LLAGAS 21011451 | 83182101 | LLAGAS 2101 | 6.1922 | 61 | 0.03381 | 2.0624 | 1392 | 15858.5448 | 1377.4481 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5880 | POINT MORETTI 11015076 | 82931101 | POINT MORETTI 1101 | 7.4948 | 67 | 0.033758 | 2.2618 | 1393 | 15866.0396 | 1375.1863 | 1375.1863 | #N/A | TRUE | 0 | FALSE | TRUE
8948 | CLARKSVILLE 2109102734 | 153612109 | CLARKSVILLE 2109 | 0.593 | 7 | 0.033754 | 0.23628 | 1394 | 15866.6326 | 1374.9501 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10958 | CURTIS 170511790 | 163351705 | CURTIS 1705 | 0.014232 | 1 | 0.033732 | 0.033732 | 1395 | 15866.6468 | 1374.9163 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10247 | MILPITAS 1108342498 | 82831108 | MILPITAS 1108 | 0.030458 | 9 | 0.033722 | 0.3035 | 1396 | 15866.6773 | 1374.6128 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5434 | MADISON 1105495270 | 63171105 | MADISON 1105 | 0.53656 | 50 | 0.033688 | 1.6844 | 1397 | 15867.2139 | 1372.9284 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5420 | PETALUMA C 1108600 | 42631108 | PETALUMA C 1108 | 3.7082 | 107 | 0.033514 | 3.586 | 1398 | 15870.9221 | 1369.3425 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5203 | HALSEY 11012414 | 152241101 | HALSEY 1101 | 14.7877 | 168 | 0.033489 | 5.6261 | 1399 | 15885.7098 | 1363.7163 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
322 | PIKE CITY 11011730 | 152201101 | PIKE CITY 1101 | 8.4807 | 73 | 0.033438 | 2.441 | 1400 | 15894.1905 | 1361.2753 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5994 | RED BLUFF 11011334 | 103541101 | RED BLUFF 1101 | 1.7937 | 155 | 0.033359 | 5.1706 | 1401 | 15895.9842 | 1356.1047 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3212 | HALF MOON BAY 1103H82 | 24101103 | HALF MOON BAY 1103 | 32.6223 | 262 | 0.033242 | 8.7095 | 1402 | 15928.6066 | 1347.3952 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1462 | GIRVAN 11029012 | 103401102 | GIRVAN 1102 | 15.6409 | 176 | 0.033219 | 5.8466 | 1403 | 15944.2475 | 1341.5486 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10706 | GONZALES 1104807000 | 182131104 | GONZALES 1104 | 0.8417 | 7 | 0.033203 | 0.23242 | 1404 | 15945.0892 | 1341.3162 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5652 | CORRAL 110214028 | 162991102 | CORRAL 1102 | 3.812 | 103 | 0.033074 | 3.4066 | 1405 | 15948.9012 | 1337.9096 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7408 | KANAKA 11011044 | 103221101 | KANAKA 1101 | 6.1466 | 17 | 0.033036 | 0.56161 | 1406 | 15955.0478 | 1337.348 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2114 | WYANDOTTE 11091040 | 102911109 | WYANDOTTE 1109 | 1.046 | 62 | 0.032999 | 2.0459 | 1407 | 15956.0938 | 1335.3021 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9307 | LINCOLN 11012310 | 153701101 | LINCOLN 1101 | 0.81088 | 34 | 0.032911 | 1.119 | 1408 | 15956.9046 | 1334.1831 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4870 | BEAR VALLEY 2101CB | 252192101 | BEAR VALLEY 2101 | 18.7781 | 154 | 0.03289 | 5.065 | 1409 | 15975.6828 | 1329.118 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3833 | APPLE HILL 110412832 | 153661104 | APPLE HILL 1104 | 14.4402 | 166 | 0.032787 | 5.4427 | 1410 | 15990.123 | 1323.6754 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10090 | TIVY VALLEY 1107599142 | 252941107 | TIVY VALLEY 1107 | 0.35631 | 19 | 0.03274 | 0.62205 | 1411 | 15990.4793 | 1323.0533 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2297 | STANISLAUS 17011812 | 162821701 | STANISLAUS 1701 | 19.2124 | 234 | 0.032657 | 7.6418 | 1412 | 16009.6917 | 1315.4116 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8485 | HOLLISTER 2102113634 | 182492102 | HOLLISTER 2102 | 1.8279 | 76 | 0.032654 | 2.4817 | 1413 | 16011.5196 | 1312.9299 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7193 | ELECTRA 1102CB | 162161102 | ELECTRA 1102 | 2.654 | 7 | 0.032515 | 0.22761 | 1414 | 16014.1736 | 1312.7023 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5731 | PLACERVILLE 21062224 | 153082106 | PLACERVILLE 2106 | 10.51 | 123 | 0.032512 | 3.999 | 1415 | 16024.6836 | 1308.7033 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4312 | MENDOCINO 110137462 | 42951101 | MENDOCINO 1101 | 2.3591 | 63 | 0.032457 | 2.0448 | 1416 | 16027.0427 | 1306.6585 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8959 | OLETA 1101894006 | 163541101 | OLETA 1101 | 0.39028 | 8 | 0.03239 | 0.25912 | 1417 | 16027.433 | 1306.3994 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4513 | SAN LUIS OBISPO 1104V14 | 182631104 | SAN LUIS OBISPO 1104 | 8.1438 | 69 | 0.03238 | 2.2342 | 1418 | 16035.5768 | 1304.1652 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4357 | APPLE HILL 11038412 | 153661103 | APPLE HILL 1103 | 19.5828 | 201 | 0.032352 | 6.5027 | 1419 | 16055.1596 | 1297.6625 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2717 | JOLON 11027002 | 182981102 | JOLON 1102 | 8.3578 | 117 | 0.032323 | 3.7818 | 1420 | 16063.5174 | 1293.8807 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5768 | BIG BASIN 110210254 | 82841102 | BIG BASIN 1102 | 2.1441 | 11 | 0.03232 | 0.35552 | 1421 | 16065.6615 | 1293.5252 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5734 | APPLE HILL 1104CB | 153661104 | APPLE HILL 1104 | 4.0885 | 51 | 0.032289 | 1.6467 | 1422 | 16069.75 | 1291.8784 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7601 | JARVIS 1111907698 | 13501111 | JARVIS 1111 | 1.5329 | 14 | 0.03225 | 0.4515 | 1423 | 16071.2829 | 1291.4269 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7801 | HALF MOON BAY 11012500 | 24101101 | HALF MOON BAY 1101 | 6.5201 | 74 | 0.032243 | 2.3859 | 1424 | 16077.8029 | 1289.041 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4135 | BRUNSWICK 11041020 | 152481104 | BRUNSWICK 1104 | 28.7752 | 311 | 0.032187 | 10.0103 | 1425 | 16106.5782 | 1279.0307 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7772 | FRUITLAND 11422006 | 192311142 | FRUITLAND 1142 | 8.327 | 75 | 0.03216 | 2.412 | 1426 | 16114.9051 | 1276.6187 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10311 | MADISON 2101760730 | 63172101 | MADISON 2101 | 0.59926 | 17 | 0.032096 | 0.54562 | 1427 | 16115.5044 | 1276.0731 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1525 | CHALLENGE 11025462 | 103201102 | CHALLENGE 1102 | 23.2735 | 248 | 0.032082 | 7.9564 | 1428 | 16138.7779 | 1268.1167 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7510 | FRUITLAND 114263170 | 192311142 | FRUITLAND 1142 | 12.4496 | 86 | 0.031951 | 2.7478 | 1429 | 16151.2275 | 1265.3689 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8635 | MOLINO 11026917 | 42571102 | MOLINO 1102 | 6.9789 | 58 | 0.031941 | 1.8526 | 1430 | 16158.2064 | 1263.5163 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5301 | REEDLEY 1104887932 | 252341104 | REEDLEY 1104 | 1.698 | 34 | 0.031896 | 1.0845 | 1431 | 16159.9044 | 1262.4319 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8600 | CALPELLA 1101619542 | 43411101 | CALPELLA 1101 | 1.4967 | 21 | 0.031874 | 0.66935 | 1432 | 16161.4011 | 1261.7625 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
145 | MOUNTAIN QUARRIES 21011130 | 152282101 | MOUNTAIN QUARRIES 2101 | 20.0341 | 231 | 0.031834 | 7.3538 | 1433 | 16181.4353 | 1254.4088 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8867 | FORESTHILL 110137238 | 152181101 | FORESTHILL 1101 | 11.4259 | 79 | 0.031693 | 2.5038 | 1434 | 16192.8612 | 1251.905 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10121 | COARSEGOLD 210210610 | 254432102 | COARSEGOLD 2102 | 1.3653 | 22 | 0.031595 | 0.6951 | 1435 | 16194.2265 | 1251.2099 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8481 | PERRY 110185870 | 183071101 | PERRY 1101 | 11.4413 | 109 | 0.031502 | 3.4337 | 1436 | 16205.6678 | 1247.7762 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3885 | BELLEVUE 2103478 | 43182103 | BELLEVUE 2103 | 8.3261 | 213 | 0.031296 | 6.6661 | 1437 | 16213.9939 | 1241.1101 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1942 | UKIAH 1113CB | 42771113 | UKIAH 1113 | 0.046885 | 69 | 0.031266 | 2.1574 | 1438 | 16214.0408 | 1238.9527 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10742 | GEYSERVILLE 1101463260 | 42891101 | GEYSERVILLE 1101 | 0.54302 | 6 | 0.031168 | 0.18701 | 1439 | 16214.5838 | 1238.7657 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8417 | CURTIS 1703CB | 163351703 | CURTIS 1703 | 9.0466 | 119 | 0.031137 | 3.7053 | 1440 | 16223.6304 | 1235.0604 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1279 | ORO FINO 11022556 | 103031102 | ORO FINO 1102 | 6.6622 | 41 | 0.031032 | 1.2723 | 1441 | 16230.2926 | 1233.7881 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1200 | OCEANO 1106CB | 182601106 | OCEANO 1106 | 1.1261 | 57 | 0.03103 | 1.7687 | 1442 | 16231.4187 | 1232.0194 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
766 | SISQUOC 1103M98 | 182811103 | SISQUOC 1103 | 7.8401 | 56 | 0.030988 | 1.7353 | 1443 | 16239.2588 | 1230.284 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8592 | STELLING 11109265 | 83481110 | STELLING 1110 | 5.5411 | 45 | 0.03098 | 1.3941 | 1444 | 16244.7999 | 1228.8899 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5933 | MIRABEL 1102524356 | 42091102 | MIRABEL 1102 | 1.2978 | 29 | 0.030872 | 0.89528 | 1445 | 16246.0977 | 1227.9947 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
802 | ALLEGHANY 1101806 | 152101101 | ALLEGHANY 1101 | 11.2762 | 65 | 0.030867 | 2.0063 | 1446 | 16257.3739 | 1225.9883 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1506 | GARBERVILLE 11011750 | 192221101 | GARBERVILLE 1101 | 8.4428 | 62 | 0.030822 | 1.911 | 1447 | 16265.8167 | 1224.0773 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4004 | COARSEGOLD 21025380 | 254432102 | COARSEGOLD 2102 | 14.2766 | 143 | 0.030806 | 4.4053 | 1448 | 16280.0933 | 1219.672 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1308 | RINCON 1101578 | 43321101 | RINCON 1101 | 17.1022 | 170 | 0.030756 | 5.2285 | 1449 | 16297.1955 | 1214.4436 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10309 | BOLINAS 1101806 | 42261101 | BOLINAS 1101 | 3.0444 | 17 | 0.030667 | 0.52134 | 1450 | 16300.2399 | 1213.9222 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6983 | BASALT 1106657038 | 42461106 | BASALT 1106 | 2.5995 | 72 | 0.030657 | 2.2073 | 1451 | 16302.8394 | 1211.715 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3194 | DIAMOND SPRINGS 1103467046 | 152261103 | DIAMOND SPRINGS 1103 | 15.3228 | 266 | 0.030581 | 8.1346 | 1452 | 16318.1622 | 1203.5803 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4703 | WISE 1101CB | 152271101 | WISE 1101 | 4.7624 | 112 | 0.030561 | 3.4229 | 1453 | 16322.9246 | 1200.1575 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6843 | DUNBAR 11033127 | 43071103 | DUNBAR 1103 | 9.3565 | 78 | 0.030422 | 2.3729 | 1454 | 16332.2811 | 1197.7845 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3373 | VOLTA 11021646 | 102541102 | VOLTA 1102 | 23.9497 | 215 | 0.030417 | 6.5396 | 1455 | 16356.2307 | 1191.2449 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9167 | WILDWOOD 1101CB | 103611101 | WILDWOOD 1101 | 0.12484 | 2 | 0.030413 | 0.060827 | 1456 | 16356.3556 | 1191.1841 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1377 | FROGTOWN 170211212 | 163451702 | FROGTOWN 1702 | 22.3393 | 155 | 0.030264 | 4.691 | 1457 | 16378.6949 | 1186.4931 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2196 | ATASCADERO 1101A02 | 182541101 | ATASCADERO 1101 | 25.4858 | 253 | 0.030233 | 7.649 | 1458 | 16404.1807 | 1178.844 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6596 | STELLING 111060090 | 83481110 | STELLING 1110 | 6.554 | 62 | 0.030171 | 1.8706 | 1459 | 16410.7347 | 1176.9735 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6029 | PANORAMA 1101713592 | 103461101 | PANORAMA 1101 | 10.3886 | 152 | 0.030005 | 4.5608 | 1460 | 16421.1233 | 1172.4126 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3261 | CRESCENT MILLS 2101CB | 103132101 | CRESCENT MILLS 2101 | 2.8253 | 60 | 0.029932 | 1.7959 | 1461 | 16423.9486 | 1170.6167 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4399 | PLACERVILLE 210619552 | 153082106 | PLACERVILLE 2106 | 21.3424 | 238 | 0.029928 | 7.123 | 1462 | 16445.291 | 1163.4937 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10240 | LLAGAS 2105534019 | 83182105 | LLAGAS 2105 | 0.71346 | 5 | 0.029893 | 0.14947 | 1463 | 16446.0045 | 1163.3442 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5361 | HOOPA 11013174 | 192401101 | HOOPA 1101 | 18.4899 | 162 | 0.029875 | 4.8397 | 1464 | 16464.4943 | 1158.5046 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5027 | PEORIA 17048040 | 163781704 | PEORIA 1704 | 7.325 | 145 | 0.02987 | 4.3312 | 1465 | 16471.8194 | 1154.1733 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9000 | CASTRO VALLEY 11088971 | 14091108 | CASTRO VALLEY 1108 | 7.9032 | 72 | 0.029749 | 2.1419 | 1466 | 16479.7226 | 1152.0314 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3972 | CORRAL 1103936674 | 162991103 | CORRAL 1103 | 0.66102 | 56 | 0.029729 | 1.6648 | 1467 | 16480.3836 | 1150.3666 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5038 | MOLINO 110241392 | 42571102 | MOLINO 1102 | 4.3895 | 171 | 0.029696 | 5.078 | 1468 | 16484.7731 | 1145.2886 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8758 | PUTAH CREEK 11033783 | 63681103 | PUTAH CREEK 1103 | 0.088571 | 96 | 0.029685 | 2.8498 | 1469 | 16484.8617 | 1142.4388 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10009 | OREGON TRAIL 110346860 | 103521103 | OREGON TRAIL 1103 | 0.71448 | 15 | 0.029648 | 0.44471 | 1470 | 16485.5761 | 1141.9941 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
944 | CURTIS 17036064 | 163351703 | CURTIS 1703 | 18.9875 | 199 | 0.029564 | 5.8832 | 1471 | 16504.5637 | 1136.1109 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5754 | SANTA YNEZ 1102Y18 | 182721102 | SANTA YNEZ 1102 | 4.8831 | 60 | 0.029555 | 1.7733 | 1472 | 16509.4468 | 1134.3376 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1748 | CLAY 110113450 | 163341101 | CLAY 1101 | 0.93803 | 42 | 0.029532 | 1.2403 | 1473 | 16510.3848 | 1133.0972 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2073 | WILLOW CREEK 11032936 | 192171103 | WILLOW CREEK 1103 | 33.1751 | 249 | 0.029513 | 7.3486 | 1474 | 16543.5599 | 1125.7486 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3589 | MIRABEL 1101688780 | 42091101 | MIRABEL 1101 | 0.57358 | 14 | 0.029456 | 0.41239 | 1475 | 16544.1334 | 1125.3362 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4182 | GARBERVILLE 11021510 | 192221102 | GARBERVILLE 1102 | 13.1584 | 107 | 0.029417 | 3.1476 | 1476 | 16557.2918 | 1122.1886 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3154 | CALISTOGA 1102634 | 42711102 | CALISTOGA 1102 | 11.216 | 178 | 0.029373 | 5.2284 | 1477 | 16568.5078 | 1116.9603 | #N/A | 1116.9603 | FALSE | 0 | TRUE | TRUE
133 | GEYSERVILLE 1102522 | 42891102 | GEYSERVILLE 1102 | 8.0023 | 109 | 0.029361 | 3.2003 | 1478 | 16576.5102 | 1113.76 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10360 | OLEMA 110175686 | 42291101 | OLEMA 1101 | 4.6305 | 31 | 0.029281 | 0.90772 | 1479 | 16581.1406 | 1112.8523 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9801 | KANAKA 1101CB | 103221101 | KANAKA 1101 | 4.7271 | 37 | 0.029281 | 1.0834 | 1480 | 16585.8678 | 1111.7689 | 1111.7689 | #N/A | TRUE | 33.4063 | FALSE | TRUE
4062 | WHITMORE 1101CB | 103601101 | WHITMORE 1101 | 5.9029 | 69 | 0.029248 | 2.0181 | 1481 | 16591.7707 | 1109.7508 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1547 | WILLITS 110391810 | 42661103 | WILLITS 1103 | 29.4465 | 296 | 0.029203 | 8.6442 | 1482 | 16621.2172 | 1101.1066 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8861 | GEYSERVILLE 1102331444 | 42891102 | GEYSERVILLE 1102 | 2.225 | 44 | 0.029048 | 1.2781 | 1483 | 16623.4421 | 1099.8285 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3080 | PIKE CITY 1101CB | 152201101 | PIKE CITY 1101 | 19.6536 | 162 | 0.029034 | 4.7034 | 1484 | 16643.0957 | 1095.125 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9245 | FRUITLAND 1142899734 | 192311142 | FRUITLAND 1142 | 3.4006 | 36 | 0.028754 | 1.0351 | 1485 | 16646.4963 | 1094.0899 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2842 | SAN LUIS OBISPO 1101CB | 182631101 | SAN LUIS OBISPO 1101 | 3.5923 | 75 | 0.028742 | 2.1556 | 1486 | 16650.0886 | 1091.9342 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8606 | PUEBLO 1105684564 | 43291105 | PUEBLO 1105 | 0.27557 | 28 | 0.02858 | 0.80024 | 1487 | 16650.3641 | 1091.134 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3749 | VINEYARD 2107978364 | 14502107 | VINEYARD 2107 | 0.96809 | 36 | 0.028543 | 1.0276 | 1488 | 16651.3322 | 1090.1064 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1264 | TEMPLETON 2113CB | 183052113 | TEMPLETON 2113 | 0.899 | 288 | 0.028499 | 8.2077 | 1489 | 16652.2312 | 1081.8987 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6493 | POINT ARENA 11013702 | 43381101 | POINT ARENA 1101 | 4.8876 | 35 | 0.028477 | 0.99668 | 1490 | 16657.1188 | 1080.902 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2973 | TEMPLETON 2111R86 | 183052111 | TEMPLETON 2111 | 10.9225 | 160 | 0.028407 | 4.5451 | 1491 | 16668.0413 | 1076.3569 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2170 | MC KEE 1111711900 | 83531111 | MC KEE 1111 | 8.9846 | 116 | 0.028347 | 3.2883 | 1492 | 16677.0259 | 1073.0686 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7676 | JARVIS 1108289662 | 13501108 | JARVIS 1108 | 0.33148 | 11 | 0.028227 | 0.31049 | 1493 | 16677.3574 | 1072.7581 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5235 | BELLEVUE 2103648 | 43182103 | BELLEVUE 2103 | 3.802 | 187 | 0.028161 | 5.2662 | 1494 | 16681.1594 | 1067.492 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10298 | PIT NO 5 11011618 | 101321101 | PIT NO 5 1101 | 6.0573 | 15 | 0.028087 | 0.42131 | 1495 | 16687.2167 | 1067.0706 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5972 | TASSAJARA 2104CB | 14662104 | TASSAJARA 2104 | 0.098921 | 22 | 0.028017 | 0.61638 | 1496 | 16687.3156 | 1066.4543 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2469 | ELECTRA 11026014 | 162161102 | ELECTRA 1102 | 4.9988 | 50 | 0.027926 | 1.3963 | 1497 | 16692.3144 | 1065.058 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1225 | SUNOL 1101MR298 | 14241101 | SUNOL 1101 | 5.1238 | 39 | 0.027925 | 1.0891 | 1498 | 16697.4382 | 1063.9689 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
739 | COTATI 1105CB | 42271105 | COTATI 1105 | 2.6781 | 35 | 0.027854 | 0.97488 | 1499 | 16700.1163 | 1062.994 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1612 | CABRILLO 1104Y22 | 183101104 | CABRILLO 1104 | 10.3926 | 178 | 0.027743 | 4.9383 | 1500 | 16710.5089 | 1058.0558 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2769 | ANNAPOLIS 110176842 | 42861101 | ANNAPOLIS 1101 | 5.6909 | 33 | 0.027724 | 0.91488 | 1501 | 16716.1998 | 1057.1409 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2631 | TEMPLETON 2111A66 | 183052111 | TEMPLETON 2111 | 33.7563 | 429 | 0.027639 | 11.8573 | 1502 | 16749.9561 | 1045.2836 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2379 | SAN LUIS OBISPO 1103CB | 182631103 | SAN LUIS OBISPO 1103 | 0 | 68 | 0.027594 | 1.8764 | 1503 | 16749.9561 | 1043.4072 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4288 | SAN LUIS OBISPO 1103V82 | 182631103 | SAN LUIS OBISPO 1103 | 8.7819 | 174 | 0.027572 | 4.7975 | 1504 | 16758.738 | 1038.6096 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3496 | APPLE HILL 21027502 | 153662102 | APPLE HILL 2102 | 22.9542 | 267 | 0.027532 | 7.351 | 1505 | 16781.6922 | 1031.2586 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3795 | SAN LUIS OBISPO 1101V12 | 182631101 | SAN LUIS OBISPO 1101 | 21.0492 | 127 | 0.027414 | 3.4815 | 1506 | 16802.7414 | 1027.7771 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5816 | PAUL SWEET 210710986 | 83252107 | PAUL SWEET 2107 | 9.3155 | 180 | 0.027411 | 4.9339 | 1507 | 16812.0569 | 1022.8431 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9709 | LAYTONVILLE 1102682 | 42681102 | LAYTONVILLE 1102 | 14.8195 | 97 | 0.027282 | 2.6464 | 1508 | 16826.8764 | 1020.1968 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1461 | LOS OSITOS 21033010 | 182082103 | LOS OSITOS 2103 | 31.1134 | 229 | 0.027281 | 6.2474 | 1509 | 16857.9898 | 1013.9493 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6161 | HIGHLANDS 1102556 | 43361102 | HIGHLANDS 1102 | 0.1777 | 90 | 0.027227 | 2.4505 | 1510 | 16858.1674 | 1011.4989 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8442 | MARTELL 11016074 | 163011101 | MARTELL 1101 | 3.6816 | 34 | 0.027132 | 0.92248 | 1511 | 16861.849 | 1010.5764 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7912 | HALF MOON BAY 1101818874 | 24101101 | HALF MOON BAY 1101 | 5.6859 | 42 | 0.02708 | 1.1374 | 1512 | 16867.5349 | 1009.439 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5790 | HIGGINS 1110869408 | 152691110 | HIGGINS 1110 | 0.44171 | 6 | 0.027041 | 0.16225 | 1513 | 16867.9766 | 1009.2768 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9590 | OILFIELDS 11037006 | 182391103 | OILFIELDS 1103 | 0 | 42 | 0.027015 | 1.1346 | 1514 | 16867.9766 | 1008.1421 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9570 | SWIFT 2102889948 | 83392102 | SWIFT 2102 | 0.43933 | 8 | 0.026886 | 0.21509 | 1515 | 16868.4159 | 1007.927 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9335 | SAN MIGUEL 1106N34 | 182661106 | SAN MIGUEL 1106 | 3.7549 | 62 | 0.02675 | 1.6585 | 1516 | 16872.1708 | 1006.2685 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8060 | MONTE RIO 1112120 | 42811112 | MONTE RIO 1112 | 6.4178 | 67 | 0.026687 | 1.788 | 1517 | 16878.5886 | 1004.4805 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2780 | HIGHLANDS 1102CB | 43361102 | HIGHLANDS 1102 | 7.4098 | 78 | 0.026652 | 2.0789 | 1518 | 16885.9984 | 1002.4017 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5253 | HOOPA 110182542 | 192401101 | HOOPA 1101 | 12.1274 | 150 | 0.026646 | 3.9969 | 1519 | 16898.1259 | 998.4048 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9493 | BRUNSWICK 1103904574 | 152481103 | BRUNSWICK 1103 | 1.5654 | 25 | 0.026628 | 0.6657 | 1520 | 16899.6913 | 997.7391 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2834 | WILLOW PASS 1101CB | 13911101 | WILLOW PASS 1101 | 1.1805 | 75 | 0.026552 | 1.9914 | 1521 | 16900.8718 | 995.7477 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4322 | WYANDOTTE 11095973 | 102911109 | WYANDOTTE 1109 | 0.085914 | 35 | 0.026544 | 0.92904 | 1522 | 16900.9577 | 994.8186 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9896 | PUEBLO 2102773926 | 43292102 | PUEBLO 2102 | 0.43924 | 25 | 0.026524 | 0.66311 | 1523 | 16901.3969 | 994.1555 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7392 | WINDSOR 1103CB | 43501103 | WINDSOR 1103 | 0 | 64 | 0.026458 | 1.6933 | 1524 | 16901.3969 | 992.4623 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7312 | PEABODY 2113CB | 63642113 | PEABODY 2113 | 0.36506 | 40 | 0.026426 | 1.057 | 1525 | 16901.762 | 991.4052 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5020 | BONNIE NOOK 1101CB | 152301101 | BONNIE NOOK 1101 | 14.4507 | 153 | 0.026396 | 4.0386 | 1526 | 16916.2126 | 987.3666 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2080 | NEWBURG 11313446 | 192151131 | NEWBURG 1131 | 0.29522 | 87 | 0.026372 | 2.2944 | 1527 | 16916.5079 | 985.0722 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5621 | FORT ROSS 112137326 | 42851121 | FORT ROSS 1121 | 5.1046 | 31 | 0.026358 | 0.8171 | 1528 | 16921.6124 | 984.2551 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7707 | SUMMIT 110148632 | 152591101 | SUMMIT 1101 | 2.7294 | 38 | 0.026323 | 1.0003 | 1529 | 16924.3418 | 983.2548 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4086 | WEST POINT 110236676 | 163201102 | WEST POINT 1102 | 16.9707 | 173 | 0.026145 | 4.5232 | 1530 | 16941.3126 | 978.7317 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3634 | CHALLENGE 11021902 | 103201102 | CHALLENGE 1102 | 4.8728 | 44 | 0.026064 | 1.1468 | 1531 | 16946.1854 | 977.5849 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5849 | HOPLAND 11011100 | 42251101 | HOPLAND 1101 | 3.7166 | 68 | 0.026059 | 1.772 | 1532 | 16949.9019 | 975.8128 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9887 | NOVATO 1104676060 | 42211104 | NOVATO 1104 | 0.44921 | 9 | 0.026046 | 0.23441 | 1533 | 16950.3511 | 975.5784 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6186 | CALAVERAS CEMENT 110111188 | 162211101 | CALAVERAS CEMENT 1101 | 29.9581 | 294 | 0.02599 | 7.641 | 1534 | 16980.3092 | 967.9374 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6575 | CLARK ROAD 110247006 | 103091102 | CLARK ROAD 1102 | 4.4715 | 51 | 0.025936 | 1.3227 | 1535 | 16984.7807 | 966.6146 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5041 | MARTELL 1103CB | 163011103 | MARTELL 1103 | 1.7681 | 76 | 0.025924 | 1.9702 | 1536 | 16986.5488 | 964.6444 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7535 | PARADISE 11042034 | 102831104 | PARADISE 1104 | 10.9756 | 99 | 0.025842 | 2.5583 | 1537 | 16997.5244 | 962.0861 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3586 | PENRYN 1107346 | 152561107 | PENRYN 1107 | 14.0643 | 309 | 0.025706 | 7.9433 | 1538 | 17011.5887 | 954.1428 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8624 | JESSUP 11012839 | 103441101 | JESSUP 1101 | 1.4657 | 20 | 0.02569 | 0.5138 | 1539 | 17013.0544 | 953.629 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2763 | GOLDTREE 1108CB | 182581108 | GOLDTREE 1108 | 2.2661 | 50 | 0.025673 | 1.2836 | 1540 | 17015.3205 | 952.3454 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9750 | COVELO 1101430286 | 43061101 | COVELO 1101 | 3.6933 | 13 | 0.025652 | 0.33348 | 1541 | 17019.0138 | 952.0119 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8494 | BRENTWOOD 2105502672 | 14592105 | BRENTWOOD 2105 | 1.4203 | 127 | 0.025636 | 3.2558 | 1542 | 17020.4341 | 948.7561 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5780 | GREEN VALLEY 210111054 | 83192101 | GREEN VALLEY 2101 | 24.3425 | 272 | 0.025605 | 6.9646 | 1543 | 17044.7766 | 941.7916 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5526 | LLAGAS 2107XR188 | 83182107 | LLAGAS 2107 | 0.37797 | 43 | 0.025596 | 1.1006 | 1544 | 17045.1546 | 940.6909 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3427 | COTATI 1105616 | 42271105 | COTATI 1105 | 2.6399 | 198 | 0.025585 | 5.0659 | 1545 | 17047.7944 | 935.625 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9956 | CLARKSVILLE 2109781566 | 153612109 | CLARKSVILLE 2109 | 0.69205 | 11 | 0.025518 | 0.28069 | 1546 | 17048.4865 | 935.3443 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1199 | BEAR VALLEY 21059560 | 252192105 | BEAR VALLEY 2105 | 22.0236 | 226 | 0.025353 | 5.7297 | 1547 | 17070.5101 | 929.6146 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4849 | ELECTRA 11017104 | 162161101 | ELECTRA 1101 | 12.0762 | 148 | 0.025302 | 3.7447 | 1548 | 17082.5863 | 925.87 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4914 | JESSUP 11019002 | 103441101 | JESSUP 1101 | 0.97482 | 74 | 0.025292 | 1.8716 | 1549 | 17083.5611 | 923.9984 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6329 | SILVERADO 2102636 | 43432102 | SILVERADO 2102 | 5.465 | 81 | 0.025287 | 2.0483 | 1550 | 17089.0262 | 921.9501 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7235 | BRIDGEVILLE 110137484 | 192461101 | BRIDGEVILLE 1101 | 7.8861 | 74 | 0.025267 | 1.8698 | 1551 | 17096.9122 | 920.0803 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4335 | UKIAH 1114844294 | 42771114 | UKIAH 1114 | 2.4113 | 55 | 0.025242 | 1.3883 | 1552 | 17099.3235 | 918.692 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5817 | TIVY VALLEY 110737522 | 252941107 | TIVY VALLEY 1107 | 0.5181 | 43 | 0.025221 | 1.0845 | 1553 | 17099.8416 | 917.6075 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
402 | REDBUD 1102922 | 43191102 | REDBUD 1102 | 7.8244 | 84 | 0.025187 | 2.1157 | 1554 | 17107.666 | 915.4918 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4837 | SAN LUIS OBISPO 1104V46 | 182631104 | SAN LUIS OBISPO 1104 | 19.9362 | 206 | 0.025184 | 5.1879 | 1555 | 17127.6022 | 910.3039 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6418 | DUNLAP 1102CB | 254061102 | DUNLAP 1102 | 6.7372 | 79 | 0.025156 | 1.9873 | 1556 | 17134.3394 | 908.3166 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8607 | ANNAPOLIS 1101608 | 42861101 | ANNAPOLIS 1101 | 17.8111 | 74 | 0.025135 | 1.86 | 1557 | 17152.1505 | 906.4566 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8805 | FRUITLAND 114293234 | 192311142 | FRUITLAND 1142 | 11.4803 | 96 | 0.025062 | 2.4059 | 1558 | 17163.6308 | 904.0507 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3300 | FULTON 1102CB | 42561102 | FULTON 1102 | 0.20314 | 48 | 0.025061 | 1.2029 | 1559 | 17163.8339 | 902.8477 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4515 | GIRVAN 11019732 | 103401101 | GIRVAN 1101 | 20.9813 | 267 | 0.025046 | 6.6872 | 1560 | 17184.8152 | 896.1605 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
602 | STAFFORD 1102524 | 43201102 | STAFFORD 1102 | 6.1352 | 162 | 0.02502 | 4.0533 | 1561 | 17190.9504 | 892.1072 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6121 | OTTER 110263868 | 182941102 | OTTER 1102 | 15.8771 | 171 | 0.024964 | 4.2689 | 1562 | 17206.8275 | 887.8383 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4102 | SPAULDING 1101578852 | 152251101 | SPAULDING 1101 | 20.6406 | 173 | 0.024946 | 4.3156 | 1563 | 17227.4681 | 883.5227 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9390 | COAST RD 04015134 | 88820401 | COAST RD 0401 | 0.63308 | 23 | 0.024922 | 0.57321 | 1564 | 17228.1011 | 882.9495 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9959 | BRIDGEVILLE 1102384530 | 192461102 | BRIDGEVILLE 1102 | 3.8189 | 12 | 0.024779 | 0.29735 | 1565 | 17231.9201 | 882.6522 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2322 | KANAKA 11011034 | 103221101 | KANAKA 1101 | 11.1511 | 80 | 0.024689 | 1.9751 | 1566 | 17243.0711 | 880.6771 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5230 | BANGOR 11011806 | 103191101 | BANGOR 1101 | 4.0291 | 17 | 0.024567 | 0.41764 | 1567 | 17247.1003 | 880.2594 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4084 | JOLON 11027040 | 182981102 | JOLON 1102 | 20.8303 | 119 | 0.02433 | 2.8953 | 1568 | 17267.9305 | 877.3642 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7751 | MIWUK 17018050 | 163661701 | MIWUK 1701 | 12.1121 | 137 | 0.024311 | 3.3307 | 1569 | 17280.0426 | 874.0335 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10676 | KERN OIL 1106397902 | 252721106 | KERN OIL 1106 | 0.44595 | 9 | 0.024302 | 0.21872 | 1570 | 17280.4885 | 873.8148 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5615 | ELECTRA 110161816 | 162161101 | ELECTRA 1101 | 23.5096 | 228 | 0.0243 | 5.5405 | 1571 | 17303.9981 | 868.2743 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
801 | OCEANO 1102CB | 182601102 | OCEANO 1102 | 15.8171 | 183 | 0.024236 | 4.4352 | 1572 | 17319.8153 | 863.8391 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8403 | MOLINO 1101472660 | 42571101 | MOLINO 1101 | 1.4504 | 18 | 0.024226 | 0.43606 | 1573 | 17321.2657 | 863.403 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4244 | BRUNSWICK 1104CB | 152481104 | BRUNSWICK 1104 | 0.38641 | 28 | 0.024194 | 0.67743 | 1574 | 17321.6521 | 862.7256 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10152 | SPENCE 1102321000 | 182201102 | SPENCE 1102 | 1.4483 | 13 | 0.024187 | 0.31443 | 1575 | 17323.1004 | 862.4112 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3391 | COTATI 1105734248 | 42271105 | COTATI 1105 | 0.48145 | 9 | 0.024166 | 0.2175 | 1576 | 17323.5819 | 862.1937 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9545 | WYANDOTTE 110942650 | 102911109 | WYANDOTTE 1109 | 0.90716 | 37 | 0.024082 | 0.89104 | 1577 | 17324.489 | 861.3026 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4392 | CLARK ROAD 110290548 | 103091102 | CLARK ROAD 1102 | 17.9431 | 168 | 0.024003 | 4.0325 | 1578 | 17342.4321 | 857.2701 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9548 | FROGTOWN 1702224708 | 163451702 | FROGTOWN 1702 | 0.64211 | 9 | 0.02399 | 0.21591 | 1579 | 17343.0743 | 857.0542 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2473 | COLUMBIA HILL 110135424 | 152471101 | COLUMBIA HILL 1101 | 13.8646 | 147 | 0.023757 | 3.4923 | 1580 | 17356.9388 | 853.5619 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3207 | SHADY GLEN 110151696 | 152431101 | SHADY GLEN 1101 | 17.4501 | 238 | 0.023753 | 5.6532 | 1581 | 17374.3889 | 847.9088 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7684 | PETALUMA C 1109738866 | 42631109 | PETALUMA C 1109 | 2.0387 | 28 | 0.023732 | 0.66451 | 1582 | 17376.4276 | 847.2443 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10885 | MORGAN HILL 2111940112 | 83242111 | MORGAN HILL 2111 | 0.2828 | 2 | 0.023701 | 0.047401 | 1583 | 17376.7104 | 847.1969 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10683 | SAN BERNARD 1101438074 | 253191101 | SAN BERNARD 1101 | 0.32085 | 6 | 0.023646 | 0.14187 | 1584 | 17377.0313 | 847.055 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
274 | GEYSERVILLE 1102350 | 42891102 | GEYSERVILLE 1102 | 5.199 | 194 | 0.023632 | 4.5846 | 1585 | 17382.2303 | 842.4704 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6780 | FOOTHILL 1102CB | 182951102 | FOOTHILL 1102 | 7.8927 | 97 | 0.023627 | 2.2918 | 1586 | 17390.123 | 840.1786 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5469 | FROGTOWN 1701L3361 | 163451701 | FROGTOWN 1701 | 1.8743 | 21 | 0.023616 | 0.49595 | 1587 | 17391.9973 | 839.6827 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
279 | GEYSERVILLE 1101122 | 42891101 | GEYSERVILLE 1101 | 1.3131 | 54 | 0.023602 | 1.2745 | 1588 | 17393.3103 | 838.4082 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1737 | FORT BRAGG A 110195294 | 42761101 | FORT BRAGG A 1101 | 27.0321 | 186 | 0.023449 | 4.3615 | 1589 | 17420.3425 | 834.0467 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1091 | COLUMBIA HILL 1101764 | 152471101 | COLUMBIA HILL 1101 | 14.6945 | 146 | 0.023389 | 3.4148 | 1590 | 17435.037 | 830.6318 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9377 | COVELO 1101516510 | 43061101 | COVELO 1101 | 3.7746 | 73 | 0.02337 | 1.706 | 1591 | 17438.8116 | 828.9258 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2700 | PINE GROVE 11023172 | 163751102 | PINE GROVE 1102 | 37.6855 | 448 | 0.023346 | 10.4588 | 1592 | 17476.4971 | 818.4669 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10187 | LLAGAS 2105154256 | 83182105 | LLAGAS 2105 | 0.26763 | 2 | 0.023318 | 0.046636 | 1593 | 17476.7647 | 818.4203 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8561 | FROGTOWN 1702307998 | 163451702 | FROGTOWN 1702 | 0.5565 | 6 | 0.023314 | 0.13989 | 1594 | 17477.3212 | 818.2804 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4078 | PENNGROVE 1101170 | 43471101 | PENNGROVE 1101 | 17.9647 | 223 | 0.023285 | 5.1925 | 1595 | 17495.286 | 813.0879 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7270 | LAKEVILLE 1102347280 | 43371102 | LAKEVILLE 1102 | 7.9316 | 99 | 0.023256 | 2.3024 | 1596 | 17503.2176 | 810.7855 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2895 | ALHAMBRA 11058302 | 14101105 | ALHAMBRA 1105 | 8.1754 | 83 | 0.023206 | 1.9261 | 1597 | 17511.393 | 808.8594 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9502 | WILLOW CREEK 11033090 | 192171103 | WILLOW CREEK 1103 | 10.8102 | 58 | 0.023177 | 1.3443 | 1598 | 17522.2032 | 807.5152 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6394 | ORO FINO 11022040 | 103031102 | ORO FINO 1102 | 9.1516 | 21 | 0.023168 | 0.48652 | 1599 | 17531.3548 | 807.0286 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2990 | HICKS 2101XR548 | 83432101 | HICKS 2101 | 1.6831 | 95 | 0.023159 | 2.2001 | 1600 | 17533.0379 | 804.8285 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
633 | RACETRACK 170310870 | 163761703 | RACETRACK 1703 | 1.909 | 28 | 0.023077 | 0.64616 | 1601 | 17534.9469 | 804.1824 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4692 | PINE GROVE 11023168 | 163751102 | PINE GROVE 1102 | 29.9741 | 285 | 0.023045 | 6.5678 | 1602 | 17564.921 | 797.6146 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10488 | HALF MOON BAY 1103531594 | 24101103 | HALF MOON BAY 1103 | 2.4852 | 25 | 0.022917 | 0.57293 | 1603 | 17567.4062 | 797.0416 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1419 | CURTIS 17048140 | 163351704 | CURTIS 1704 | 26.3871 | 260 | 0.022915 | 5.958 | 1604 | 17593.7934 | 791.0836 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5050 | ATASCADERO 1101A22 | 182541101 | ATASCADERO 1101 | 0 | 167 | 0.022889 | 3.8224 | 1605 | 17593.7934 | 787.2613 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10722 | TASSAJARA 2103557000 | 14662103 | TASSAJARA 2103 | 0.20822 | 3 | 0.022855 | 0.068564 | 1606 | 17594.0016 | 787.1927 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4033 | GANSNER 11012006 | 103021101 | GANSNER 1101 | 17.1356 | 151 | 0.022834 | 3.4479 | 1607 | 17611.1372 | 783.7448 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5518 | BIG BEND 1101641808 | 103751101 | BIG BEND 1101 | 25.7525 | 234 | 0.022822 | 5.3404 | 1608 | 17636.8897 | 778.4044 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8814 | CLAY 11037142 | 163341103 | CLAY 1103 | 3.9003 | 100 | 0.022773 | 2.2773 | 1609 | 17640.7899 | 776.1271 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9514 | HALF MOON BAY 110258448 | 24101102 | HALF MOON BAY 1102 | 4.4382 | 22 | 0.022766 | 0.50086 | 1610 | 17645.2282 | 775.6262 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4404 | EEL RIVER 1102630456 | 192381102 | EEL RIVER 1102 | 5.3553 | 37 | 0.022761 | 0.84216 | 1611 | 17650.5834 | 774.784 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9626 | SAUSALITO 110284278 | 42491102 | SAUSALITO 1102 | 1.5476 | 18 | 0.022717 | 0.4089 | 1612 | 17652.1311 | 774.3751 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5345 | ELK 11011300 | 42981101 | ELK 1101 | 3.5496 | 64 | 0.02261 | 1.447 | 1613 | 17655.6806 | 772.9281 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3272 | KESWICK 11019712 | 103451101 | KESWICK 1101 | 18.589 | 214 | 0.022607 | 4.838 | 1614 | 17674.2697 | 768.0901 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7529 | EEL RIVER 11021902 | 192381102 | EEL RIVER 1102 | 6.5648 | 43 | 0.022585 | 0.97115 | 1615 | 17680.8344 | 767.119 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9292 | PUEBLO 2102895310 | 43292102 | PUEBLO 2102 | 0.36853 | 31 | 0.022565 | 0.69951 | 1616 | 17681.203 | 766.4195 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3684 | VASCO 1102MR178 | 13751102 | VASCO 1102 | 1.6033 | 117 | 0.022562 | 2.6398 | 1617 | 17682.8062 | 763.7797 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6059 | RINCON 1103198 | 43321103 | RINCON 1103 | 6.4238 | 62 | 0.02256 | 1.3987 | 1618 | 17689.23 | 762.381 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8232 | FOOTHILL 1101251688 | 182951101 | FOOTHILL 1101 | 6.9818 | 68 | 0.022486 | 1.5291 | 1619 | 17696.2118 | 760.8519 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9659 | CAMBRIA 1101858200 | 182771101 | CAMBRIA 1101 | 5.718 | 31 | 0.022446 | 0.69582 | 1620 | 17701.9297 | 760.1561 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5819 | COTTONWOOD 110359128 | 102931103 | COTTONWOOD 1103 | 0.74702 | 65 | 0.022397 | 1.4558 | 1621 | 17702.6768 | 758.7002 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9234 | WILDWOOD 110185112 | 103611101 | WILDWOOD 1101 | 6.7944 | 54 | 0.022386 | 1.2088 | 1622 | 17709.4712 | 757.4914 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2051 | LAYTONVILLE 1101518 | 42681101 | LAYTONVILLE 1101 | 3.0081 | 165 | 0.02237 | 3.6911 | 1623 | 17712.4793 | 753.8003 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4400 | CALISTOGA 1102769230 | 42711102 | CALISTOGA 1102 | 11.021 | 160 | 0.022338 | 3.574 | 1624 | 17723.5003 | 750.2263 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1232 | VOLTA 110237350 | 102541102 | VOLTA 1102 | 24.2821 | 255 | 0.02227 | 5.6788 | 1625 | 17747.7824 | 744.5475 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1076 | MC ARTHUR 1101648698 | 103491101 | MC ARTHUR 1101 | 10.6495 | 173 | 0.022255 | 3.85 | 1626 | 17758.4319 | 740.6975 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6771 | HALSEY 1102CB | 152241102 | HALSEY 1102 | 7.8822 | 86 | 0.022172 | 1.9068 | 1627 | 17766.3141 | 738.7907 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1966 | GARBERVILLE 11011514 | 192221101 | GARBERVILLE 1101 | 14.7717 | 123 | 0.022168 | 2.7266 | 1628 | 17781.0858 | 736.0641 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7554 | SAN LUIS OBISPO 1105512313 | 182631105 | SAN LUIS OBISPO 1105 | 0.48845 | 10 | 0.022063 | 0.22063 | 1629 | 17781.5743 | 735.8434 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6120 | PUEBLO 2103895784 | 43292103 | PUEBLO 2103 | 7.793 | 110 | 0.022046 | 2.4251 | 1630 | 17789.3673 | 733.4184 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
63 | CORRAL 110175204 | 162991101 | CORRAL 1101 | 0.85548 | 130 | 0.021935 | 2.8515 | 1631 | 17790.2227 | 730.5669 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9574 | MONROE 2103848530 | 43302103 | MONROE 2103 | 0.44461 | 17 | 0.021849 | 0.37143 | 1632 | 17790.6673 | 730.1954 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7210 | WEST POINT 110234416 | 163201102 | WEST POINT 1102 | 10.4546 | 113 | 0.021823 | 2.466 | 1633 | 17801.122 | 727.7294 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2105 | WEST POINT 1102CB | 163201102 | WEST POINT 1102 | 17.7877 | 195 | 0.02173 | 4.2374 | 1634 | 17818.9097 | 723.492 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6954 | WYANDOTTE 1110144140 | 102911110 | WYANDOTTE 1110 | 0.25917 | 20 | 0.021719 | 0.43439 | 1635 | 17819.1689 | 723.0576 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9884 | ELK 1101311906 | 42981101 | ELK 1101 | 0.69139 | 12 | 0.021675 | 0.2601 | 1636 | 17819.8603 | 722.7975 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1046 | GARBERVILLE 11028652 | 192221102 | GARBERVILLE 1102 | 13.1503 | 114 | 0.021633 | 2.4661 | 1637 | 17833.0106 | 720.3314 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3164 | BRUNSWICK 11062416 | 152481106 | BRUNSWICK 1106 | 28.9391 | 360 | 0.021547 | 7.7569 | 1638 | 17861.9497 | 712.5745 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3168 | LUCERNE 1103630 | 43351103 | LUCERNE 1103 | 12.4377 | 154 | 0.021529 | 3.3154 | 1639 | 17874.3874 | 709.259 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9831 | HALF MOON BAY 1101771258 | 24101101 | HALF MOON BAY 1101 | 0.19165 | 4 | 0.021484 | 0.085935 | 1640 | 17874.5791 | 709.1731 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8239 | FRUITLAND 11413902 | 192311141 | FRUITLAND 1141 | 5.111 | 9 | 0.021389 | 0.1925 | 1641 | 17879.6901 | 708.9806 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4880 | CURTIS 1705CB | 163351705 | CURTIS 1705 | 13.3382 | 163 | 0.021383 | 3.4854 | 1642 | 17893.0284 | 705.4952 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1762 | VINEYARD 2108609690 | 14502108 | VINEYARD 2108 | 4.8318 | 72 | 0.021383 | 1.5396 | 1643 | 17897.8601 | 703.9556 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7400 | CLARKSVILLE 21096502 | 153612109 | CLARKSVILLE 2109 | 0.93268 | 52 | 0.021251 | 1.1051 | 1644 | 17898.7928 | 702.8506 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10207 | MONTE RIO 111159046 | 42811111 | MONTE RIO 1111 | 3.506 | 15 | 0.021246 | 0.31869 | 1645 | 17902.2988 | 702.5319 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4878 | PLACERVILLE 21069712 | 153082106 | PLACERVILLE 2106 | 24.7147 | 226 | 0.021241 | 4.8004 | 1646 | 17927.0135 | 697.7315 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2046 | LINCOLN 11042072 | 153701104 | LINCOLN 1104 | 0.31166 | 193 | 0.021197 | 4.091 | 1647 | 17927.3252 | 693.6404 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7243 | SILVERADO 2104708 | 43432104 | SILVERADO 2104 | 3.7544 | 61 | 0.02118 | 1.292 | 1648 | 17931.0796 | 692.3484 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
593 | BRUNSWICK 11021010 | 152481102 | BRUNSWICK 1102 | 44.3718 | 479 | 0.021168 | 10.1396 | 1649 | 17975.4514 | 682.2089 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5896 | CHALLENGE 11015460 | 103201101 | CHALLENGE 1101 | 11.7964 | 91 | 0.021116 | 1.9215 | 1650 | 17987.2478 | 680.2873 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9400 | BELL 110880680 | 152701108 | BELL 1108 | 0.64051 | 24 | 0.021095 | 0.50627 | 1651 | 17987.8883 | 679.7811 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6134 | CALAVERAS CEMENT 110180930 | 162211101 | CALAVERAS CEMENT 1101 | 18.3521 | 180 | 0.021019 | 3.7835 | 1652 | 18006.2404 | 675.9976 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5626 | WYANDOTTE 1103CB | 102911103 | WYANDOTTE 1103 | 0.24488 | 100 | 0.021017 | 2.1017 | 1653 | 18006.4852 | 673.8959 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5183 | ALTO 1125902 | 42031125 | ALTO 1125 | 12.0907 | 83 | 0.020905 | 1.7351 | 1654 | 18018.5759 | 672.1607 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7644 | LLAGAS 2101783467 | 83182101 | LLAGAS 2101 | 10.2229 | 61 | 0.020785 | 1.2679 | 1655 | 18028.7988 | 670.8929 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7011 | MOUNTAIN QUARRIES 21011180 | 152282101 | MOUNTAIN QUARRIES 2101 | 12.9566 | 141 | 0.020771 | 2.9287 | 1656 | 18041.7554 | 667.9642 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
11063 | APPLE HILL 1104814656 | 153661104 | APPLE HILL 1104 | 0.01748 | 1 | 0.020643 | 0.020643 | 1657 | 18041.7729 | 667.9435 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9926 | BUCKS CREEK 1103CB | 102211103 | BUCKS CREEK 1103 | 2.3045 | 31 | 0.020623 | 0.63931 | 1658 | 18044.0774 | 667.3042 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3649 | FROGTOWN 1702812366 | 163451702 | FROGTOWN 1702 | 2.7477 | 28 | 0.020596 | 0.57668 | 1659 | 18046.8251 | 666.7275 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9417 | DUNBAR 1102694641 | 43071102 | DUNBAR 1102 | 4.0571 | 49 | 0.020553 | 1.0071 | 1660 | 18050.8822 | 665.7204 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8194 | STANISLAUS 17017144 | 162821701 | STANISLAUS 1701 | 4.6557 | 52 | 0.020479 | 1.0649 | 1661 | 18055.5379 | 664.6556 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10788 | FITCH MOUNTAIN 1111752596 | 42751111 | FITCH MOUNTAIN 1111 | 0.24558 | 6 | 0.020465 | 0.12279 | 1662 | 18055.7835 | 664.5328 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3463 | WOODACRE 1102851 | 43021102 | WOODACRE 1102 | 1.2611 | 14 | 0.020416 | 0.28582 | 1663 | 18057.0446 | 664.247 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
331 | WEST POINT 11024790 | 163201102 | WEST POINT 1102 | 32.7726 | 305 | 0.020377 | 6.2151 | 1664 | 18089.8171 | 658.0318 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8939 | STELLING 111060080 | 83481110 | STELLING 1110 | 9.5829 | 64 | 0.020345 | 1.3021 | 1665 | 18099.4001 | 656.7297 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5387 | PLACERVILLE 210611132 | 153082106 | PLACERVILLE 2106 | 43.2776 | 420 | 0.020262 | 8.5102 | 1666 | 18142.6777 | 648.2195 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3326 | ORO FINO 110265932 | 103031102 | ORO FINO 1102 | 4.5225 | 48 | 0.020219 | 0.97052 | 1667 | 18147.2002 | 647.249 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7230 | PINE GROVE 110283098 | 163751102 | PINE GROVE 1102 | 7.9173 | 104 | 0.020137 | 2.0942 | 1668 | 18155.1175 | 645.1548 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2235 | MOLINO 1102318 | 42571102 | MOLINO 1102 | 19.3375 | 228 | 0.020097 | 4.5821 | 1669 | 18174.455 | 640.5727 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9552 | JOLON 11027068 | 182981102 | JOLON 1102 | 3.8155 | 12 | 0.019995 | 0.23993 | 1670 | 18178.2705 | 640.3327 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7621 | UKIAH 1115CB | 42771115 | UKIAH 1115 | 4.3108 | 73 | 0.019906 | 1.4531 | 1671 | 18182.5813 | 638.8796 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5118 | SAN LUIS OBISPO 1107V60 | 182631107 | SAN LUIS OBISPO 1107 | 16.042 | 142 | 0.0199 | 2.8258 | 1672 | 18198.6233 | 636.0538 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1916 | MOLINO 1104368158 | 42571104 | MOLINO 1104 | 2.7874 | 105 | 0.019862 | 2.0855 | 1673 | 18201.4107 | 633.9684 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8812 | ANTLER 11011376 | 103271101 | ANTLER 1101 | 8.998 | 70 | 0.019836 | 1.3885 | 1674 | 18210.4087 | 632.5799 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3393 | SILVERADO 2102714 | 43432102 | SILVERADO 2102 | 3.4609 | 121 | 0.019829 | 2.3993 | 1675 | 18213.8697 | 630.1806 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8102 | FORESTHILL 110175340 | 152181101 | FORESTHILL 1101 | 4.7831 | 62 | 0.01968 | 1.2202 | 1676 | 18218.6528 | 628.9604 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7713 | DUNBAR 11014817 | 43071101 | DUNBAR 1101 | 3.1568 | 42 | 0.019666 | 0.82599 | 1677 | 18221.8096 | 628.1344 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6368 | EAST QUINCY 1101951424 | 102551101 | EAST QUINCY 1101 | 0.69872 | 49 | 0.019501 | 0.95554 | 1678 | 18222.5083 | 627.1789 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6762 | HOOPA 11013304 | 192401101 | HOOPA 1101 | 17.341 | 88 | 0.019486 | 1.7148 | 1679 | 18239.8493 | 625.4641 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4845 | SAN JOAQUIN #3 110210342 | 252531102 | SAN JOAQUIN #3 1102 | 1.8216 | 23 | 0.019463 | 0.44766 | 1680 | 18241.6709 | 625.0165 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3381 | LUCERNE 110638436 | 43351106 | LUCERNE 1106 | 4.5081 | 62 | 0.019424 | 1.2043 | 1681 | 18246.179 | 623.8122 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8990 | HALF MOON BAY 1103540991 | 24101103 | HALF MOON BAY 1103 | 1.5814 | 16 | 0.019417 | 0.31068 | 1682 | 18247.7604 | 623.5015 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1522 | RIO DELL 11021504 | 192251102 | RIO DELL 1102 | 10.8482 | 64 | 0.019342 | 1.2379 | 1683 | 18258.6086 | 622.2636 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6286 | DUNBAR 1101416 | 43071101 | DUNBAR 1101 | 2.6414 | 28 | 0.019316 | 0.54085 | 1684 | 18261.25 | 621.7228 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2445 | MC ARTHUR 11011546 | 103491101 | MC ARTHUR 1101 | 13.7936 | 102 | 0.019258 | 1.9643 | 1685 | 18275.0436 | 619.7585 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2748 | HALF MOON BAY 11036018 | 24101103 | HALF MOON BAY 1103 | 15.6741 | 160 | 0.019223 | 3.0757 | 1686 | 18290.7177 | 616.6828 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4766 | CLOVERDALE 1101807953 | 42821101 | CLOVERDALE 1101 | 0.46353 | 11 | 0.019176 | 0.21093 | 1687 | 18291.1812 | 616.4718 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3508 | CLEAR LAKE 1102223792 | 42141102 | CLEAR LAKE 1102 | 0.78455 | 10 | 0.019106 | 0.19106 | 1688 | 18291.9658 | 616.2808 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3278 | KONOCTI 1108CB | 43311108 | KONOCTI 1108 | 6.3576 | 98 | 0.019021 | 1.864 | 1689 | 18298.3233 | 614.4167 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
218 | MADISON 21017702 | 63172101 | MADISON 2101 | 0 | 168 | 0.018893 | 3.174 | 1690 | 18298.3233 | 611.2427 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5100 | RIO DELL 110270960 | 192251102 | RIO DELL 1102 | 5.7786 | 103 | 0.018609 | 1.9167 | 1691 | 18304.102 | 609.3261 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1226 | FORT ROSS 11212987 | 42851121 | FORT ROSS 1121 | 1.9714 | 18 | 0.018603 | 0.33485 | 1692 | 18306.0733 | 608.9912 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4217 | CHALLENGE 1102CB | 103201102 | CHALLENGE 1102 | 15.3169 | 123 | 0.0185 | 2.2755 | 1693 | 18321.3902 | 606.7157 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4592 | PHILO 1102928 | 42601102 | PHILO 1102 | 13.9642 | 125 | 0.018489 | 2.3111 | 1694 | 18335.3544 | 604.4046 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4143 | MENDOCINO 1101CB | 42951101 | MENDOCINO 1101 | 2.6352 | 54 | 0.018327 | 0.98966 | 1695 | 18337.9897 | 603.4149 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5556 | WEST POINT 11021305 | 163201102 | WEST POINT 1102 | 11.3122 | 105 | 0.01831 | 1.9226 | 1696 | 18349.3019 | 601.4923 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7818 | SONOMA 1105575872 | 42721105 | SONOMA 1105 | 1.1851 | 12 | 0.018279 | 0.21935 | 1697 | 18350.487 | 601.273 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1713 | HALF MOON BAY 1103H80 | 24101103 | HALF MOON BAY 1103 | 19.8193 | 164 | 0.018248 | 2.9927 | 1698 | 18370.3063 | 598.2803 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3304 | DIAMOND SPRINGS 11039432 | 152261103 | DIAMOND SPRINGS 1103 | 17.4645 | 251 | 0.018233 | 4.5765 | 1699 | 18387.7708 | 593.7038 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1922 | ALLEGHANY 1102CB | 152101102 | ALLEGHANY 1102 | 18.012 | 104 | 0.018204 | 1.8932 | 1700 | 18405.7828 | 591.8106 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4888 | DUNBAR 110179086 | 43071101 | DUNBAR 1101 | 6.8083 | 82 | 0.018179 | 1.4907 | 1701 | 18412.5911 | 590.3199 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1290 | FROGTOWN 170232556 | 163451702 | FROGTOWN 1702 | 0.1169 | 19 | 0.018147 | 0.34478 | 1702 | 18412.708 | 589.9751 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4459 | CLARK ROAD 11022094 | 103091102 | CLARK ROAD 1102 | 3.4289 | 11 | 0.018088 | 0.19897 | 1703 | 18416.1369 | 589.7761 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8596 | SAN JOAQUIN #3 1101CB | 252531101 | SAN JOAQUIN #3 1101 | 11.8429 | 80 | 0.018079 | 1.4463 | 1704 | 18427.9798 | 588.3298 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7985 | MERCED FALLS 1102482838 | 252811102 | MERCED FALLS 1102 | 8.8777 | 52 | 0.018057 | 0.93898 | 1705 | 18436.8575 | 587.3908 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5651 | MOUNTAIN QUARRIES 21012422 | 152282101 | MOUNTAIN QUARRIES 2101 | 8.671 | 81 | 0.018043 | 1.4615 | 1706 | 18445.5285 | 585.9293 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9070 | SILVERADO 2102437194 | 43432102 | SILVERADO 2102 | 1.0584 | 17 | 0.018026 | 0.30645 | 1707 | 18446.5869 | 585.6229 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2577 | HARTLEY 110186876 | 43211101 | HARTLEY 1101 | 2.4524 | 110 | 0.018007 | 1.9808 | 1708 | 18449.0393 | 583.6421 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5850 | GEYSERVILLE 1101711966 | 42891101 | GEYSERVILLE 1101 | 3.9317 | 122 | 0.017908 | 2.1848 | 1709 | 18452.971 | 581.4573 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8508 | PIKE CITY 11011720 | 152201101 | PIKE CITY 1101 | 5.8975 | 34 | 0.017864 | 0.60738 | 1710 | 18458.8685 | 580.8499 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4021 | GRASS VALLEY 11012766 | 152031101 | GRASS VALLEY 1101 | 3.2943 | 31 | 0.017834 | 0.55287 | 1711 | 18462.1628 | 580.297 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5421 | DUNBAR 1102261774 | 43071102 | DUNBAR 1102 | 13.5246 | 142 | 0.01783 | 2.5319 | 1712 | 18475.6874 | 577.7652 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1746 | TEMPLETON 2111CB | 183052111 | TEMPLETON 2111 | 2.2544 | 118 | 0.017802 | 2.1007 | 1713 | 18477.9418 | 575.6645 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2820 | ALTO 1124432 | 42031124 | ALTO 1124 | 7.8461 | 72 | 0.017729 | 1.2765 | 1714 | 18485.7878 | 574.388 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5452 | PUEBLO 2102850102 | 43292102 | PUEBLO 2102 | 0.17865 | 23 | 0.01772 | 0.40756 | 1715 | 18485.9665 | 573.9804 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3283 | CURTIS 170390320 | 163351703 | CURTIS 1703 | 27.8742 | 282 | 0.017701 | 4.9917 | 1716 | 18513.8407 | 568.9887 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3501 | CRESCENT MILLS 21012232 | 103132101 | CRESCENT MILLS 2101 | 15.8568 | 128 | 0.017667 | 2.2614 | 1717 | 18529.6976 | 566.7274 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10143 | GRASS VALLEY 1101750804 | 152031101 | GRASS VALLEY 1101 | 0.24243 | 5 | 0.017655 | 0.088275 | 1718 | 18529.94 | 566.6391 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3289 | MONTICELLO 11011589 | 43051101 | MONTICELLO 1101 | 4.2717 | 52 | 0.01765 | 0.91781 | 1719 | 18534.2117 | 565.7213 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1138 | ELECTRA 110136816 | 162161101 | ELECTRA 1101 | 4.9869 | 60 | 0.017625 | 1.0575 | 1720 | 18539.1986 | 564.6638 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9331 | WILLOW CREEK 1102CB | 192171102 | WILLOW CREEK 1102 | 7.3272 | 71 | 0.017606 | 1.25 | 1721 | 18546.5257 | 563.4138 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6284 | ANTLER 11011378 | 103271101 | ANTLER 1101 | 24.5436 | 201 | 0.017574 | 3.5323 | 1722 | 18571.0694 | 559.8814 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8843 | HOLLISTER 2104117328 | 182492104 | HOLLISTER 2104 | 6.1496 | 44 | 0.017549 | 0.77216 | 1723 | 18577.2189 | 559.1093 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
106 | WYANDOTTE 11101954 | 102911110 | WYANDOTTE 1110 | 2.625 | 132 | 0.017468 | 2.3057 | 1724 | 18579.8439 | 556.8035 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7269 | CURTIS 17046060 | 163351704 | CURTIS 1704 | 4.0652 | 50 | 0.01746 | 0.873 | 1725 | 18583.9091 | 555.9305 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4024 | MOLINO 11015042 | 42571101 | MOLINO 1101 | 6.0518 | 90 | 0.01743 | 1.5687 | 1726 | 18589.9609 | 554.3619 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8422 | FROGTOWN 1702739858 | 163451702 | FROGTOWN 1702 | 4.8793 | 46 | 0.017426 | 0.80161 | 1727 | 18594.8402 | 553.5602 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3353 | KANAKA 11011406 | 103221101 | KANAKA 1101 | 27.2731 | 204 | 0.017352 | 3.5397 | 1728 | 18622.1132 | 550.0205 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10623 | MORGAN HILL 2111477914 | 83242111 | MORGAN HILL 2111 | 0.19132 | 3 | 0.017329 | 0.051987 | 1729 | 18622.3045 | 549.9685 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1703 | SAN LUIS OBISPO 1105796050 | 182631105 | SAN LUIS OBISPO 1105 | 0.2385 | 45 | 0.017291 | 0.7781 | 1730 | 18622.543 | 549.1904 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2587 | MENLO 11031721 | 24131103 | MENLO 1103 | 6.7914 | 52 | 0.01726 | 0.89751 | 1731 | 18629.3344 | 548.2929 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5617 | MIRABEL 1101298 | 42091101 | MIRABEL 1101 | 12.5878 | 123 | 0.017238 | 2.1202 | 1732 | 18641.9222 | 546.1727 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
183 | CLEAR LAKE 110192870 | 42141101 | CLEAR LAKE 1101 | 0.11557 | 187 | 0.017207 | 3.2176 | 1733 | 18642.0378 | 542.9551 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5761 | SAN LUIS OBISPO 1102597518 | 182631102 | SAN LUIS OBISPO 1102 | 0.0405 | 30 | 0.017175 | 0.51524 | 1734 | 18642.0783 | 542.4398 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
694 | PIT NO 1 11013312 | 103721101 | PIT NO 1 1101 | 8.045 | 82 | 0.017169 | 1.4079 | 1735 | 18650.1233 | 541.0319 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6571 | MC ARTHUR 11011488 | 103491101 | MC ARTHUR 1101 | 2.4678 | 217 | 0.01714 | 3.7195 | 1736 | 18652.5911 | 537.3125 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7993 | STILLWATER 1101CB | 103561101 | STILLWATER 1101 | 4.198 | 47 | 0.017137 | 0.80543 | 1737 | 18656.789 | 536.5071 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3453 | LOS GATOS 110760114 | 82021107 | LOS GATOS 1107 | 24.3201 | 220 | 0.016971 | 3.7337 | 1738 | 18681.1091 | 532.7734 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3503 | CLAYTON 2215184604 | 12022215 | CLAYTON 2215 | 2.0891 | 106 | 0.016935 | 1.7951 | 1739 | 18683.1982 | 530.9783 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5231 | BURNEY 1101CB | 103311101 | BURNEY 1101 | 1.2417 | 29 | 0.016895 | 0.48997 | 1740 | 18684.4399 | 530.4883 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5033 | ALTO 11243121 | 42031124 | ALTO 1124 | 2.7976 | 36 | 0.016885 | 0.60788 | 1741 | 18687.2375 | 529.8804 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4749 | FRUITLAND 11418860 | 192311141 | FRUITLAND 1141 | 1.9962 | 34 | 0.016867 | 0.57347 | 1742 | 18689.2337 | 529.307 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8284 | FRENCH GULCH 11011464 | 103381101 | FRENCH GULCH 1101 | 0.85238 | 10 | 0.01686 | 0.1686 | 1743 | 18690.0861 | 529.1384 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10232 | TIGER CREEK 0201CB | 161380201 | TIGER CREEK 0201 | 3.7431 | 20 | 0.016801 | 0.33603 | 1744 | 18693.8292 | 528.8024 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5809 | TEMPLETON 2110N32 | 183052110 | TEMPLETON 2110 | 29.5034 | 251 | 0.016765 | 4.208 | 1745 | 18723.3326 | 524.5943 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7289 | PLACERVILLE 111019582 | 153081110 | PLACERVILLE 1110 | 7.2707 | 80 | 0.016762 | 1.341 | 1746 | 18730.6033 | 523.2534 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9046 | OTTER 11022166 | 182941102 | OTTER 1102 | 4.0764 | 41 | 0.016743 | 0.68648 | 1747 | 18734.6798 | 522.5669 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3955 | GRAYS FLAT 0401CB | 102530401 | GRAYS FLAT 0401 | 10.7279 | 77 | 0.016728 | 1.2881 | 1748 | 18745.4076 | 521.2788 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4383 | FRUITLAND 114195324 | 192311141 | FRUITLAND 1141 | 6.4826 | 40 | 0.016671 | 0.66685 | 1749 | 18751.8902 | 520.612 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9718 | GARBERVILLE 1101323694 | 192221101 | GARBERVILLE 1101 | 6.4004 | 17 | 0.016661 | 0.28324 | 1750 | 18758.2906 | 520.3287 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7551 | GARBERVILLE 1101438596 | 192221101 | GARBERVILLE 1101 | 11.0232 | 69 | 0.016624 | 1.1471 | 1751 | 18769.3137 | 519.1817 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9937 | OTTER 11022002 | 182941102 | OTTER 1102 | 2.8257 | 27 | 0.01654 | 0.44657 | 1752 | 18772.1395 | 518.7351 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5432 | ALLEGHANY 1101804 | 152101101 | ALLEGHANY 1101 | 21.8915 | 163 | 0.016525 | 2.6936 | 1753 | 18794.031 | 516.0415 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6356 | NORTH BRANCH 110113496 | 163231101 | NORTH BRANCH 1101 | 1.9962 | 58 | 0.016506 | 0.95734 | 1754 | 18796.0272 | 515.0842 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
249 | RINCON 1103CB | 43321103 | RINCON 1103 | 2.4433 | 41 | 0.016461 | 0.67489 | 1755 | 18798.4705 | 514.4093 | 514.4093 | #N/A | TRUE | 1.5 | TRUE | TRUE
1025 | MARIPOSA 2101439030 | 254452101 | MARIPOSA 2101 | 19.621 | 200 | 0.016434 | 3.2868 | 1756 | 18818.0914 | 511.1225 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8791 | GLENN 11012012 | 102601101 | GLENN 1101 | 2.3047 | 73 | 0.016401 | 1.1972 | 1757 | 18820.3962 | 509.9252 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10780 | CALPINE 1144962 | 48011144 | CALPINE 1144 | 4.0181 | 13 | 0.01639 | 0.21307 | 1758 | 18824.4143 | 509.7121 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
715 | ALTO 1124430 | 42031124 | ALTO 1124 | 7.0575 | 92 | 0.016311 | 1.5006 | 1759 | 18831.4718 | 508.2116 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9633 | MONTE RIO 11131067 | 42811113 | MONTE RIO 1113 | 0.81192 | 11 | 0.016 | 0.176 | 1760 | 18832.2837 | 508.0356 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1412 | PLACERVILLE 1109CB | 153081109 | PLACERVILLE 1109 | 10.8452 | 133 | 0.015996 | 2.1275 | 1761 | 18843.1289 | 505.9081 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8245 | BEAR VALLEY 210513430 | 252192105 | BEAR VALLEY 2105 | 13.1178 | 129 | 0.015945 | 2.057 | 1762 | 18856.2467 | 503.8511 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8966 | MORAGA 1101772781 | 13801101 | MORAGA 1101 | 1.4399 | 12 | 0.015766 | 0.1892 | 1763 | 18857.6866 | 503.6619 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3619 | PINE GROVE 11013166 | 163751101 | PINE GROVE 1101 | 12.2922 | 147 | 0.015763 | 2.3172 | 1764 | 18869.9788 | 501.3447 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4486 | WEST POINT 1101CB | 163201101 | WEST POINT 1101 | 4.7938 | 20 | 0.015736 | 0.31472 | 1765 | 18874.7727 | 501.03 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3894 | BONNIE NOOK 110186696 | 152301101 | BONNIE NOOK 1101 | 9.641 | 86 | 0.015606 | 1.3421 | 1766 | 18884.4137 | 499.6879 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1913 | OLEMA 1101416 | 42291101 | OLEMA 1101 | 16.1787 | 79 | 0.015542 | 1.2278 | 1767 | 18900.5923 | 498.4601 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2787 | PINE GROVE 11013170 | 163751101 | PINE GROVE 1101 | 39.8073 | 445 | 0.015534 | 6.9125 | 1768 | 18940.3996 | 491.5476 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8370 | SWIFT 2110XR332 | 83392110 | SWIFT 2110 | 18.4582 | 83 | 0.015532 | 1.2892 | 1769 | 18958.8578 | 490.2584 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6569 | CURTIS 17058170 | 163351705 | CURTIS 1705 | 7.6995 | 109 | 0.015509 | 1.6904 | 1770 | 18966.5573 | 488.568 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9835 | SPRING GAP 1702CB | 162831702 | SPRING GAP 1702 | 7.4405 | 18 | 0.015422 | 0.27759 | 1771 | 18973.9978 | 488.2904 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1693 | BUCKS CREEK 1103338520 | 102211103 | BUCKS CREEK 1103 | 7.8641 | 87 | 0.015412 | 1.3409 | 1772 | 18981.8619 | 486.9496 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4370 | OREGON TRAIL 11021584 | 103521102 | OREGON TRAIL 1102 | 13.0507 | 136 | 0.015387 | 2.0926 | 1773 | 18994.9126 | 484.857 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6223 | MOLINO 1101152 | 42571101 | MOLINO 1101 | 1.6586 | 125 | 0.015258 | 1.9072 | 1774 | 18996.5712 | 482.9497 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
991 | PEORIA 170413494 | 163781704 | PEORIA 1704 | 2.7686 | 93 | 0.015212 | 1.4148 | 1775 | 18999.3399 | 481.535 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10392 | VINEYARD 2108383748 | 14502108 | VINEYARD 2108 | 0.36191 | 4 | 0.015207 | 0.060827 | 1776 | 18999.7018 | 481.4741 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5782 | GARBERVILLE 11026084 | 192221102 | GARBERVILLE 1102 | 15.311 | 120 | 0.015158 | 1.8189 | 1777 | 19015.0127 | 479.6552 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8670 | COTATI 1102462 | 42271102 | COTATI 1102 | 2.8283 | 40 | 0.015132 | 0.6053 | 1778 | 19017.841 | 479.0499 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5839 | SOLEDAD 21027048 | 182052102 | SOLEDAD 2102 | 11.5993 | 173 | 0.015069 | 2.607 | 1779 | 19029.4403 | 476.4429 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5090 | BRIDGEVILLE 1102CB | 192461102 | BRIDGEVILLE 1102 | 2.9355 | 52 | 0.015061 | 0.78316 | 1780 | 19032.3758 | 475.6597 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10131 | CMC 1101CB | 183111101 | CMC 1101 | 2.0423 | 16 | 0.014989 | 0.23983 | 1781 | 19034.4181 | 475.4199 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4953 | FRENCH GULCH 11021462 | 103381102 | FRENCH GULCH 1102 | 10.0162 | 51 | 0.01495 | 0.76245 | 1782 | 19044.4343 | 474.6575 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8365 | GRASS VALLEY 110358498 | 152031103 | GRASS VALLEY 1103 | 1.1937 | 34 | 0.01494 | 0.50797 | 1783 | 19045.628 | 474.1495 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4523 | TIDEWATER 210665866 | 14652106 | TIDEWATER 2106 | 3.419 | 65 | 0.014918 | 0.9697 | 1784 | 19049.047 | 473.1798 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7430 | FOOTHILL 1101549904 | 182951101 | FOOTHILL 1101 | 0.15565 | 54 | 0.014902 | 0.80473 | 1785 | 19049.2026 | 472.3751 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10743 | ANDERSON 1101909424 | 103261101 | ANDERSON 1101 | 0.3992 | 8 | 0.014888 | 0.1191 | 1786 | 19049.6018 | 472.256 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6685 | OCEANO 1102749231 | 182601102 | OCEANO 1102 | 5.5563 | 141 | 0.014847 | 2.0934 | 1787 | 19055.1582 | 470.1626 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2541 | BRUNSWICK 110651486 | 152481106 | BRUNSWICK 1106 | 56.6847 | 656 | 0.014797 | 9.7068 | 1788 | 19111.8429 | 460.4558 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7750 | BRUNSWICK 110765574 | 152481107 | BRUNSWICK 1107 | 0.58392 | 23 | 0.014793 | 0.34024 | 1789 | 19112.4268 | 460.1156 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5279 | MC ARTHUR 110137344 | 103491101 | MC ARTHUR 1101 | 0.1127 | 75 | 0.014768 | 1.1076 | 1790 | 19112.5395 | 459.008 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7132 | ANTLER 11011612 | 103271101 | ANTLER 1101 | 9.1773 | 86 | 0.014748 | 1.2683 | 1791 | 19121.7168 | 457.7396 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3386 | NEWBURG 1132665674 | 192151132 | NEWBURG 1132 | 0.43431 | 20 | 0.014722 | 0.29443 | 1792 | 19122.1511 | 457.4452 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7872 | PIT NO 1 110170952 | 103721101 | PIT NO 1 1101 | 1.6934 | 29 | 0.014692 | 0.42606 | 1793 | 19123.8445 | 457.0192 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5114 | DUNBAR 110147964 | 43071101 | DUNBAR 1101 | 6.5107 | 68 | 0.014662 | 0.99704 | 1794 | 19130.3552 | 456.0221 | 456.0221 | #N/A | TRUE | 0.45 | FALSE | TRUE
7691 | POINT ARENA 110198224 | 43381101 | POINT ARENA 1101 | 2.3915 | 23 | 0.014654 | 0.33704 | 1795 | 19132.7467 | 455.6851 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2530 | BRUNSWICK 111061602 | 152481110 | BRUNSWICK 1110 | 9.8175 | 137 | 0.014648 | 2.0068 | 1796 | 19142.5641 | 453.6783 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7167 | FRENCH GULCH 11012905 | 103381101 | FRENCH GULCH 1101 | 9.692 | 83 | 0.014648 | 1.2158 | 1797 | 19152.2561 | 452.4625 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4457 | HIGGINS 11041006 | 152691104 | HIGGINS 1104 | 10.8946 | 266 | 0.014639 | 3.8939 | 1798 | 19163.1507 | 448.5686 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7710 | CARLOTTA 11214045 | 192291121 | CARLOTTA 1121 | 0.35805 | 18 | 0.014618 | 0.26312 | 1799 | 19163.5088 | 448.3055 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9405 | SILVERADO 2105861266 | 43432105 | SILVERADO 2105 | 1.5562 | 31 | 0.014616 | 0.45311 | 1800 | 19165.065 | 447.8524 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
463 | WEIMAR 11012084 | 152491101 | WEIMAR 1101 | 18.4732 | 219 | 0.014579 | 3.1928 | 1801 | 19183.5382 | 444.6596 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3551 | WILLOW CREEK 11014904 | 192171101 | WILLOW CREEK 1101 | 18.2331 | 121 | 0.014552 | 1.7608 | 1802 | 19201.7713 | 442.8987 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6996 | KONOCTI 1102714370 | 43311102 | KONOCTI 1102 | 2.1274 | 28 | 0.014533 | 0.40694 | 1803 | 19203.8987 | 442.4918 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1102 | MC KEE 1107XR010 | 83531107 | MC KEE 1107 | 2.7862 | 160 | 0.014407 | 2.3052 | 1804 | 19206.6849 | 440.1866 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2551 | SOLEDAD 2102823854 | 182052102 | SOLEDAD 2102 | 2.0556 | 33 | 0.01437 | 0.47422 | 1805 | 19208.7405 | 439.7124 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2101 | SAN BENITO 210488772 | 182742104 | SAN BENITO 2104 | 24.323 | 474 | 0.014358 | 6.8057 | 1806 | 19233.0635 | 432.9067 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7410 | RIO DELL 11028852 | 192251102 | RIO DELL 1102 | 4.6451 | 46 | 0.014354 | 0.66027 | 1807 | 19237.7086 | 432.2464 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5404 | PIT NO 3 21011386 | 103732101 | PIT NO 3 2101 | 6.8695 | 47 | 0.014294 | 0.67181 | 1808 | 19244.5781 | 431.5746 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4186 | MARIPOSA 210110170 | 254452101 | MARIPOSA 2101 | 16.3165 | 149 | 0.014293 | 2.1297 | 1809 | 19260.8946 | 429.4449 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7884 | SONOMA 11045661 | 42721104 | SONOMA 1104 | 2.8951 | 66 | 0.014289 | 0.94309 | 1810 | 19263.7898 | 428.5018 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
967 | DUNBAR 1102903030 | 43071102 | DUNBAR 1102 | 1.4552 | 17 | 0.014278 | 0.24273 | 1811 | 19265.245 | 428.2591 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3516 | NARROWS 21022718 | 153132102 | NARROWS 2102 | 0.30804 | 114 | 0.014276 | 1.6275 | 1812 | 19265.553 | 426.6316 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5103 | SAN LUIS OBISPO 1107V18 | 182631107 | SAN LUIS OBISPO 1107 | 2.6999 | 41 | 0.014215 | 0.5828 | 1813 | 19268.2529 | 426.0488 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
177 | KING CITY 11037038 | 182031103 | KING CITY 1103 | 18.3291 | 186 | 0.014161 | 2.6339 | 1814 | 19286.5819 | 423.4149 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4472 | WEST POINT 110277204 | 163201102 | WEST POINT 1102 | 7.4073 | 68 | 0.014094 | 0.95841 | 1815 | 19293.9893 | 422.4565 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8017 | PIT NO 3 2101CB | 103732101 | PIT NO 3 2101 | 4.532 | 7 | 0.01407 | 0.098493 | 1816 | 19298.5213 | 422.358 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4764 | ALLEGHANY 1101CB | 152101101 | ALLEGHANY 1101 | 4.3721 | 40 | 0.014057 | 0.5623 | 1817 | 19302.8934 | 421.7957 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2091 | STELLING 111060094 | 83481110 | STELLING 1110 | 9.8619 | 95 | 0.014041 | 1.3339 | 1818 | 19312.7553 | 420.4618 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2701 | PEORIA 170567898 | 163781705 | PEORIA 1705 | 4.2992 | 70 | 0.014037 | 0.98259 | 1819 | 19317.0545 | 419.4792 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8037 | CAYUCOS 1102613456 | 182551102 | CAYUCOS 1102 | 13.4475 | 145 | 0.014028 | 2.0341 | 1820 | 19330.5021 | 417.4452 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4958 | WILLOW CREEK 11035012 | 192171103 | WILLOW CREEK 1103 | 11.1274 | 131 | 0.014012 | 1.8356 | 1821 | 19341.6295 | 415.6095 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1586 | MARTELL 110111244 | 163011101 | MARTELL 1101 | 20.6924 | 202 | 0.01399 | 2.826 | 1822 | 19362.3219 | 412.7835 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8222 | DUNBAR 1102528 | 43071102 | DUNBAR 1102 | 3.4314 | 50 | 0.013987 | 0.69934 | 1823 | 19365.7534 | 412.0842 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6649 | SAN LUIS OBISPO 1108337126 | 182631108 | SAN LUIS OBISPO 1108 | 0.70138 | 28 | 0.013964 | 0.39101 | 1824 | 19366.4547 | 411.6932 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
716 | LAKEVILLE 1102280 | 43371102 | LAKEVILLE 1102 | 0.68764 | 52 | 0.013918 | 0.72376 | 1825 | 19367.1424 | 410.9694 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1162 | DUNBAR 1101302 | 43071101 | DUNBAR 1101 | 8.7659 | 123 | 0.013839 | 1.7022 | 1826 | 19375.9083 | 409.2672 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5443 | DUNBAR 1103534 | 43071103 | DUNBAR 1103 | 15.8602 | 162 | 0.01369 | 2.2178 | 1827 | 19391.7685 | 407.0495 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3834 | STILLWATER 11011320 | 103561101 | STILLWATER 1101 | 19.8125 | 179 | 0.013687 | 2.4499 | 1828 | 19411.5809 | 404.5996 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3066 | SHADY GLEN 1102CB | 152431102 | SHADY GLEN 1102 | 21.1633 | 240 | 0.01359 | 3.2616 | 1829 | 19432.7443 | 401.338 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8639 | GREEN VALLEY 2101135762 | 83192101 | GREEN VALLEY 2101 | 0.7393 | 28 | 0.013539 | 0.3791 | 1830 | 19433.4836 | 400.9589 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1363 | BURNEY 11011322 | 103311101 | BURNEY 1101 | 16.0665 | 81 | 0.01351 | 1.0943 | 1831 | 19449.5501 | 399.8645 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5427 | PENRYN 1103CB | 152561103 | PENRYN 1103 | 2.4031 | 37 | 0.013499 | 0.49946 | 1832 | 19451.9533 | 399.3651 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8202 | DUNBAR 1102861496 | 43071102 | DUNBAR 1102 | 4.4679 | 51 | 0.013491 | 0.68805 | 1833 | 19456.4211 | 398.677 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3776 | ALTO 1125510 | 42031125 | ALTO 1125 | 7.3721 | 77 | 0.013466 | 1.0369 | 1834 | 19463.7932 | 397.6402 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2524 | PHILO 1102920 | 42601102 | PHILO 1102 | 17.7725 | 258 | 0.013411 | 3.4601 | 1835 | 19481.5657 | 394.1801 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8287 | LUCERNE 11034624 | 43351103 | LUCERNE 1103 | 0.031493 | 42 | 0.013292 | 0.55825 | 1836 | 19481.5972 | 393.6218 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3582 | SAN RAFAEL 1108516 | 42011108 | SAN RAFAEL 1108 | 10.9401 | 135 | 0.013281 | 1.7929 | 1837 | 19492.5373 | 391.8289 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6863 | GREEN VALLEY 2101942143 | 83192101 | GREEN VALLEY 2101 | 5.0581 | 74 | 0.013216 | 0.97798 | 1838 | 19497.5954 | 390.8509 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7880 | POINT ARENA 110183354 | 43381101 | POINT ARENA 1101 | 5.1341 | 36 | 0.013182 | 0.47457 | 1839 | 19502.7295 | 390.3763 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2799 | TASSAJARA 211238868 | 14662112 | TASSAJARA 2112 | 1.9386 | 61 | 0.01315 | 0.80215 | 1840 | 19504.6681 | 389.5742 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10912 | TOCALOMA 0241CB | 43150241 | TOCALOMA 0241 | 0.016479 | 1 | 0.013124 | 0.013124 | 1841 | 19504.6845 | 389.5611 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6124 | ANDERSON 1101CB | 103261101 | ANDERSON 1101 | 1.1835 | 85 | 0.013117 | 1.115 | 1842 | 19505.868 | 388.4461 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6165 | BRUNSWICK 1105CB | 152481105 | BRUNSWICK 1105 | 1.1628 | 21 | 0.013096 | 0.27501 | 1843 | 19507.0308 | 388.1711 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9119 | SONOMA 1106296492 | 42721106 | SONOMA 1106 | 0.78968 | 29 | 0.013092 | 0.37968 | 1844 | 19507.8205 | 387.7914 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3902 | SOLEDAD 2102858388 | 182052102 | SOLEDAD 2102 | 4.7963 | 72 | 0.013047 | 0.93942 | 1845 | 19512.6168 | 386.852 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6187 | JESSUP 11013383 | 103441101 | JESSUP 1101 | 1.4095 | 24 | 0.012944 | 0.31066 | 1846 | 19514.0263 | 386.5413 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4407 | APPLE HILL 210297982 | 153662102 | APPLE HILL 2102 | 9.6617 | 104 | 0.012892 | 1.3407 | 1847 | 19523.688 | 385.2006 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7041 | JAMESON 1105371694 | 63801105 | JAMESON 1105 | 0.2273 | 40 | 0.012819 | 0.51277 | 1848 | 19523.9153 | 384.6878 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3447 | WYANDOTTE 11031974 | 102911103 | WYANDOTTE 1103 | 22.4168 | 259 | 0.012814 | 3.3188 | 1849 | 19546.3321 | 381.369 | 381.369 | #N/A | TRUE | 20.3416 | TRUE | TRUE
7950 | SONOMA 11033052 | 42721103 | SONOMA 1103 | 12.5899 | 163 | 0.012795 | 2.0855 | 1850 | 19558.922 | 379.2835 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5166 | LOS GATOS 1106LB48 | 82021106 | LOS GATOS 1106 | 14.71 | 142 | 0.012757 | 1.8115 | 1851 | 19573.632 | 377.4719 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3055 | LAS POSITAS 2108MR190 | 14402108 | LAS POSITAS 2108 | 0.83091 | 130 | 0.012744 | 1.6567 | 1852 | 19574.4629 | 375.8152 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8820 | HICKS 2101CB | 83432101 | HICKS 2101 | 5.3825 | 20 | 0.012742 | 0.25483 | 1853 | 19579.8454 | 375.5604 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
987 | OAKHURST 110310140 | 254421103 | OAKHURST 1103 | 16.6091 | 188 | 0.012696 | 2.3869 | 1854 | 19596.4545 | 373.1735 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1124 | COARSEGOLD 210210040 | 254432102 | COARSEGOLD 2102 | 17.6377 | 213 | 0.01266 | 2.6967 | 1855 | 19614.0922 | 370.4768 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6998 | PUEBLO 1104640 | 43291104 | PUEBLO 1104 | 1.0173 | 43 | 0.012658 | 0.54429 | 1856 | 19615.1095 | 369.9326 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2113 | HALSEY 11025739 | 152241102 | HALSEY 1102 | 6.6699 | 74 | 0.012582 | 0.93104 | 1857 | 19621.7794 | 369.0015 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9463 | ATASCADERO 1103A06 | 182541103 | ATASCADERO 1103 | 0.27446 | 27 | 0.012566 | 0.33927 | 1858 | 19622.0538 | 368.6622 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
673 | FLINT 110140666 | 152531101 | FLINT 1101 | 0.35747 | 18 | 0.012564 | 0.22615 | 1859 | 19622.4113 | 368.4361 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6086 | SONOMA 1102113082 | 42721102 | SONOMA 1102 | 6.1264 | 75 | 0.012535 | 0.94012 | 1860 | 19628.5377 | 367.496 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4138 | ORO FINO 11022096 | 103031102 | ORO FINO 1102 | 14.1535 | 129 | 0.012531 | 1.6166 | 1861 | 19642.6912 | 365.8794 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8669 | HORSESHOE 1101663244 | 152571101 | HORSESHOE 1101 | 0.28862 | 6 | 0.012526 | 0.075153 | 1862 | 19642.9798 | 365.8043 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1101 | HOOPA 110137202 | 192401101 | HOOPA 1101 | 24.9008 | 190 | 0.012512 | 2.3773 | 1863 | 19667.8806 | 363.427 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1135 | LOS GATOS 1106LB44 | 82021106 | LOS GATOS 1106 | 19.3536 | 213 | 0.012499 | 2.6623 | 1864 | 19687.2342 | 360.7647 | 360.7647 | #N/A | TRUE | 0.84905 | TRUE | TRUE
5450 | FORESTHILL 11011802 | 152181101 | FORESTHILL 1101 | 22.2318 | 259 | 0.012496 | 3.2365 | 1865 | 19709.466 | 357.5283 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5898 | WISE 1102465074 | 152271102 | WISE 1102 | 4.7621 | 57 | 0.012495 | 0.7122 | 1866 | 19714.2281 | 356.8161 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7150 | FRUITLAND 1141200856 | 192311141 | FRUITLAND 1141 | 2.5758 | 31 | 0.012452 | 0.38602 | 1867 | 19716.8039 | 356.43 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6814 | SAN ARDO 11017632 | 182191101 | SAN ARDO 1101 | 2.2163 | 35 | 0.012428 | 0.43499 | 1868 | 19719.0202 | 355.995 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4514 | SOLEDAD 2101526864 | 182052101 | SOLEDAD 2101 | 3.1129 | 18 | 0.012408 | 0.22335 | 1869 | 19722.1331 | 355.7717 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10395 | CLARKSVILLE 2109649874 | 153612109 | CLARKSVILLE 2109 | 0.37816 | 5 | 0.012324 | 0.061618 | 1870 | 19722.5113 | 355.7101 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
368 | POINT MORETTI 11015078 | 82931101 | POINT MORETTI 1101 | 14.8373 | 154 | 0.012313 | 1.8962 | 1871 | 19737.3486 | 353.8139 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4025 | CARLOTTA 1121CB | 192291121 | CARLOTTA 1121 | 2.6253 | 255 | 0.012302 | 3.1369 | 1872 | 19739.9739 | 350.677 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9319 | GONZALES 11013094 | 182131101 | GONZALES 1101 | 4.0888 | 63 | 0.012298 | 0.77477 | 1873 | 19744.0627 | 349.9022 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5655 | CHALLENGE 1101CB | 103201101 | CHALLENGE 1101 | 16.5645 | 128 | 0.012215 | 1.5636 | 1874 | 19760.6272 | 348.3386 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9730 | MC KEE 1108976553 | 83531108 | MC KEE 1108 | 1.0843 | 20 | 0.012197 | 0.24394 | 1875 | 19761.7115 | 348.0947 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8214 | BRUNSWICK 1106CB | 152481106 | BRUNSWICK 1106 | 8.7425 | 88 | 0.012162 | 1.0703 | 1876 | 19770.454 | 347.0244 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3779 | NOTRE DAME 1103317782 | 102041103 | NOTRE DAME 1103 | 0.54331 | 53 | 0.012141 | 0.64349 | 1877 | 19770.9973 | 346.3809 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1366 | HALF MOON BAY 11036014 | 24101103 | HALF MOON BAY 1103 | 6.192 | 106 | 0.012138 | 1.2867 | 1878 | 19777.1894 | 345.0943 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7316 | HOLLISTER 2102676164 | 182492102 | HOLLISTER 2102 | 0.30298 | 26 | 0.012062 | 0.3136 | 1879 | 19777.4923 | 344.7807 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2140 | BRUNSWICK 1102CB | 152481102 | BRUNSWICK 1102 | 6.2764 | 73 | 0.01204 | 0.87889 | 1880 | 19783.7688 | 343.9018 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9978 | FROGTOWN 1702411508 | 163451702 | FROGTOWN 1702 | 0.45171 | 6 | 0.012026 | 0.072157 | 1881 | 19784.2205 | 343.8296 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5364 | FULTON 1104466 | 42561104 | FULTON 1104 | 0.38717 | 21 | 0.01202 | 0.25243 | 1882 | 19784.6077 | 343.5772 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
916 | WYANDOTTE 1105329930 | 102911105 | WYANDOTTE 1105 | 6.5421 | 137 | 0.012012 | 1.6456 | 1883 | 19791.1497 | 341.9315 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4781 | SONOMA 1105539450 | 42721105 | SONOMA 1105 | 1.4938 | 28 | 0.011978 | 0.33537 | 1884 | 19792.6436 | 341.5962 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5493 | SHADY GLEN 11012768 | 152431101 | SHADY GLEN 1101 | 7.6253 | 88 | 0.011963 | 1.0528 | 1885 | 19800.2688 | 340.5434 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8268 | LLAGAS 2101587857 | 83182101 | LLAGAS 2101 | 0.10681 | 28 | 0.011944 | 0.33442 | 1886 | 19800.3756 | 340.209 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1441 | MIWUK 170111800 | 163661701 | MIWUK 1701 | 9.5248 | 116 | 0.011866 | 1.3764 | 1887 | 19809.9005 | 338.8326 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2749 | ELK 1101900 | 42981101 | ELK 1101 | 8.7791 | 185 | 0.011859 | 2.1939 | 1888 | 19818.6795 | 336.6387 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1288 | CALAVERAS CEMENT 11012646 | 162211101 | CALAVERAS CEMENT 1101 | 17.6594 | 149 | 0.01184 | 1.7642 | 1889 | 19836.339 | 334.8745 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8429 | FOOTHILL 1101386844 | 182951101 | FOOTHILL 1101 | 0.3826 | 19 | 0.01183 | 0.22478 | 1890 | 19836.7216 | 334.6497 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6057 | LLAGAS 2101XR264 | 83182101 | LLAGAS 2101 | 0 | 258 | 0.011726 | 3.0254 | 1891 | 19836.7216 | 331.6243 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5358 | UKIAH 1113968652 | 42771113 | UKIAH 1113 | 0.99825 | 25 | 0.011684 | 0.2921 | 1892 | 19837.7198 | 331.3322 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9622 | SAN RAFAEL 110863598 | 42011108 | SAN RAFAEL 1108 | 1.9122 | 24 | 0.011681 | 0.28035 | 1893 | 19839.632 | 331.0519 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6523 | ALTO 1124870444 | 42031124 | ALTO 1124 | 2.95 | 35 | 0.011666 | 0.40831 | 1894 | 19842.582 | 330.6436 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4747 | SANTA ROSA A 1104716 | 42151104 | SANTA ROSA A 1104 | 8.8999 | 109 | 0.01165 | 1.2698 | 1895 | 19851.4819 | 329.3738 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9188 | HALF MOON BAY 1102350336 | 24101102 | HALF MOON BAY 1102 | 1.2038 | 13 | 0.011629 | 0.15117 | 1896 | 19852.6857 | 329.2226 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10068 | SAN LUIS OBISPO 1108809986 | 182631108 | SAN LUIS OBISPO 1108 | 1.0323 | 18 | 0.011626 | 0.20927 | 1897 | 19853.7181 | 329.0133 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3493 | MARTELL 110198374 | 163011101 | MARTELL 1101 | 0.8271 | 46 | 0.011616 | 0.53436 | 1898 | 19854.5452 | 328.479 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3767 | HOLLISTER 210491424 | 182492104 | HOLLISTER 2104 | 0.18842 | 95 | 0.01155 | 1.0973 | 1899 | 19854.7336 | 327.3817 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7603 | CLOVERDALE 1102262 | 42821102 | CLOVERDALE 1102 | 1.2848 | 61 | 0.011548 | 0.70445 | 1900 | 19856.0183 | 326.6772 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
712 | SILVERADO 2105247660 | 43432105 | SILVERADO 2105 | 2.3981 | 35 | 0.011541 | 0.40392 | 1901 | 19858.4164 | 326.2733 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4631 | BRUNSWICK 11052210 | 152481105 | BRUNSWICK 1105 | 22.9574 | 280 | 0.01151 | 3.2229 | 1902 | 19881.3738 | 323.0504 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1236 | OAKHURST 11035480 | 254421103 | OAKHURST 1103 | 16.9994 | 180 | 0.011505 | 2.0709 | 1903 | 19898.3733 | 320.9796 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2425 | PIT NO 3 21011360 | 103732101 | PIT NO 3 2101 | 22.4404 | 92 | 0.011504 | 1.0584 | 1904 | 19920.8137 | 319.9212 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9598 | MILPITAS 1109XR044 | 82831109 | MILPITAS 1109 | 0.42126 | 18 | 0.011436 | 0.20585 | 1905 | 19921.2349 | 319.7153 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3999 | CALAVERAS CEMENT 11011419 | 162211101 | CALAVERAS CEMENT 1101 | 15.0161 | 130 | 0.011428 | 1.4856 | 1906 | 19936.2511 | 318.2297 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3421 | HIGGINS 1104324510 | 152691104 | HIGGINS 1104 | 12.4758 | 154 | 0.011404 | 1.7562 | 1907 | 19948.7269 | 316.4735 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6037 | COARSEGOLD 210210050 | 254432102 | COARSEGOLD 2102 | 7.0172 | 81 | 0.01137 | 0.92095 | 1908 | 19955.7441 | 315.5525 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
942 | WEST POINT 110293116 | 163201102 | WEST POINT 1102 | 42.3267 | 453 | 0.011348 | 5.1406 | 1909 | 19998.0708 | 310.4119 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1810 | CABRILLO 1104CB | 183101104 | CABRILLO 1104 | 4.128 | 121 | 0.011318 | 1.3695 | 1910 | 20002.1988 | 309.0424 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1626 | MOLINO 110251788 | 42571102 | MOLINO 1102 | 5.0892 | 153 | 0.011264 | 1.7234 | 1911 | 20007.288 | 307.319 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6259 | RISING RIVER 11019032 | 103551101 | RISING RIVER 1101 | 22.8885 | 175 | 0.011207 | 1.9611 | 1912 | 20030.1765 | 305.3578 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1825 | FORT BRAGG A 11014622 | 42761101 | FORT BRAGG A 1101 | 13.456 | 109 | 0.011136 | 1.2138 | 1913 | 20043.6325 | 304.144 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5920 | CASTRO VALLEY 1110MR243 | 14091110 | CASTRO VALLEY 1110 | 5.5499 | 72 | 0.011084 | 0.79807 | 1914 | 20049.1824 | 303.346 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3864 | PLACER 1103429574 | 152461103 | PLACER 1103 | 4.9745 | 114 | 0.011083 | 1.2634 | 1915 | 20054.1569 | 302.0826 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4013 | LAURELES 1111CB | 182371111 | LAURELES 1111 | 7.1569 | 82 | 0.011075 | 0.90815 | 1916 | 20061.3139 | 301.1744 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9810 | MENLO 11028896 | 24131102 | MENLO 1102 | 0.95586 | 14 | 0.011065 | 0.15491 | 1917 | 20062.2698 | 301.0195 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8395 | CARLOTTA 112142896 | 192291121 | CARLOTTA 1121 | 2.2912 | 71 | 0.011029 | 0.78303 | 1918 | 20064.561 | 300.2365 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5390 | SOLEDAD 2102304826 | 182052102 | SOLEDAD 2102 | 5.2196 | 61 | 0.010995 | 0.6707 | 1919 | 20069.7806 | 299.5658 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4943 | PINE GROVE 1102CB | 163751102 | PINE GROVE 1102 | 10.8527 | 136 | 0.010952 | 1.4895 | 1920 | 20080.6332 | 298.0762 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2277 | ORO FINO 11022560 | 103031102 | ORO FINO 1102 | 16.7269 | 179 | 0.010913 | 1.9534 | 1921 | 20097.3601 | 296.1228 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8219 | CAMPHORA 1101613562 | 182071101 | CAMPHORA 1101 | 3.695 | 29 | 0.010904 | 0.31622 | 1922 | 20101.0552 | 295.8066 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8001 | MOLINO 1102189602 | 42571102 | MOLINO 1102 | 0.62848 | 9 | 0.010902 | 0.098117 | 1923 | 20101.6837 | 295.7085 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8797 | CAMP EVERS 210533542 | 83622105 | CAMP EVERS 2105 | 2.6827 | 39 | 0.010901 | 0.42515 | 1924 | 20104.3664 | 295.2833 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6026 | ROSSMOOR 110837848 | 14161108 | ROSSMOOR 1108 | 5.9544 | 60 | 0.010901 | 0.65406 | 1925 | 20110.3208 | 294.6293 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9862 | MONTE RIO 11113891 | 42811111 | MONTE RIO 1111 | 3.4699 | 23 | 0.010887 | 0.2504 | 1926 | 20113.7907 | 294.3789 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9761 | HALF MOON BAY 1103341542 | 24101103 | HALF MOON BAY 1103 | 6.0713 | 47 | 0.010885 | 0.5116 | 1927 | 20119.862 | 293.8673 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6971 | WILLOW CREEK 11037514 | 192171103 | WILLOW CREEK 1103 | 9.0713 | 118 | 0.010882 | 1.2841 | 1928 | 20128.9333 | 292.5832 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8324 | MONTE RIO 1112999 | 42811112 | MONTE RIO 1112 | 0.8778 | 7 | 0.010787 | 0.075506 | 1929 | 20129.8111 | 292.5077 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3097 | ATASCADERO 1103492068 | 182541103 | ATASCADERO 1103 | 7.4298 | 75 | 0.010772 | 0.80789 | 1930 | 20137.2409 | 291.6998 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1425 | CLAY 110184572 | 163341101 | CLAY 1101 | 0.52505 | 27 | 0.010769 | 0.29075 | 1931 | 20137.766 | 291.409 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8269 | COTATI 1105893 | 42271105 | COTATI 1105 | 0.19405 | 91 | 0.010724 | 0.9759 | 1932 | 20137.96 | 290.4331 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1839 | VOLTA 11021650 | 102541102 | VOLTA 1102 | 21.7104 | 154 | 0.010701 | 1.6479 | 1933 | 20159.6704 | 288.7852 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5835 | APPLE HILL 110497086 | 153661104 | APPLE HILL 1104 | 25.6961 | 301 | 0.010689 | 3.2174 | 1934 | 20185.3665 | 285.5678 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7014 | ALTO 1122591122 | 42031122 | ALTO 1122 | 0.46531 | 7 | 0.010649 | 0.074542 | 1935 | 20185.8319 | 285.4933 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1545 | MARTELL 110191216 | 163011101 | MARTELL 1101 | 40.579 | 380 | 0.010587 | 4.0231 | 1936 | 20226.4109 | 281.4701 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
812 | DUNBAR 1102246 | 43071102 | DUNBAR 1102 | 13.3609 | 148 | 0.010561 | 1.563 | 1937 | 20239.7718 | 279.9071 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6481 | DEL MONTE 21043088 | 182222104 | DEL MONTE 2104 | 15.4183 | 175 | 0.010503 | 1.8381 | 1938 | 20255.1901 | 278.069 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
336 | CAMBRIA 1102CB | 182771102 | CAMBRIA 1102 | 16.0058 | 153 | 0.010468 | 1.6015 | 1939 | 20271.1959 | 276.4675 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3334 | VOLTA 110297816 | 102541102 | VOLTA 1102 | 5.2562 | 50 | 0.010402 | 0.52009 | 1940 | 20276.4521 | 275.9474 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1241 | CALAVERAS CEMENT 110147968 | 162211101 | CALAVERAS CEMENT 1101 | 40.4602 | 306 | 0.010385 | 3.1777 | 1941 | 20316.9123 | 272.7697 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8572 | LOS GATOS 110760024 | 82021107 | LOS GATOS 1107 | 3.9764 | 27 | 0.010381 | 0.28029 | 1942 | 20320.8887 | 272.4894 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8425 | PINE GROVE 110194936 | 163751101 | PINE GROVE 1101 | 9.1674 | 82 | 0.010365 | 0.84992 | 1943 | 20330.0561 | 271.6395 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10220 | ALLEGHANY 1101808 | 152101101 | ALLEGHANY 1101 | 6.1786 | 23 | 0.010361 | 0.23829 | 1944 | 20336.2347 | 271.4012 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7876 | PUEBLO 2103706399 | 43292103 | PUEBLO 2103 | 0.33435 | 16 | 0.010338 | 0.1654 | 1945 | 20336.5691 | 271.2358 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1021 | EL DORADO PH 210119752 | 152762101 | EL DORADO PH 2101 | 36.5225 | 436 | 0.0103 | 4.4909 | 1946 | 20373.0916 | 266.7448 | 266.7448 | #N/A | TRUE | 20.7011 | FALSE | TRUE
5417 | SILVERADO 2105131568 | 43432105 | SILVERADO 2105 | 4.1385 | 57 | 0.010281 | 0.58604 | 1947 | 20377.2301 | 266.1588 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3018 | LUCERNE 110638632 | 43351106 | LUCERNE 1106 | 4.6833 | 58 | 0.010245 | 0.59423 | 1948 | 20381.9133 | 265.5646 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9909 | OLEMA 1101337220 | 42291101 | OLEMA 1101 | 4.9471 | 28 | 0.010237 | 0.28665 | 1949 | 20386.8604 | 265.2779 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7162 | BIG BEND 1101CB | 103751101 | BIG BEND 1101 | 23.2301 | 171 | 0.010207 | 1.7454 | 1950 | 20410.0905 | 263.5325 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9067 | PEORIA 170570198 | 163781705 | PEORIA 1705 | 2.255 | 36 | 0.010197 | 0.36709 | 1951 | 20412.3455 | 263.1654 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6816 | REDBUD 1101400 | 43191101 | REDBUD 1101 | 0.87662 | 14 | 0.010195 | 0.14273 | 1952 | 20413.2221 | 263.0227 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5252 | POINT ARENA 110137426 | 43381101 | POINT ARENA 1101 | 0.78956 | 65 | 0.010169 | 0.66101 | 1953 | 20414.0117 | 262.3617 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7444 | HOLLISTER 21064004 | 182492106 | HOLLISTER 2106 | 8.7531 | 180 | 0.010124 | 1.8224 | 1954 | 20422.7648 | 260.5393 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2021 | WOODACRE 11021280 | 43021102 | WOODACRE 1102 | 8.5847 | 111 | 0.010109 | 1.1221 | 1955 | 20431.3496 | 259.4173 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9350 | WEST POINT 1101L3355 | 163201101 | WEST POINT 1101 | 2.2487 | 27 | 0.010104 | 0.2728 | 1956 | 20433.5983 | 259.1445 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4549 | ALHAMBRA 110595016 | 14101105 | ALHAMBRA 1105 | 0.76011 | 69 | 0.010066 | 0.69458 | 1957 | 20434.3584 | 258.4499 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5052 | BIG MEADOWS 21012474 | 102812101 | BIG MEADOWS 2101 | 8.3349 | 83 | 0.010035 | 0.83287 | 1958 | 20442.6933 | 257.617 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
616 | SONOMA 1104414 | 42721104 | SONOMA 1104 | 1.3137 | 260 | 0.009991 | 2.5977 | 1959 | 20444.007 | 255.0193 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8621 | FELTON 0401CB | 83140401 | FELTON 0401 | 2.5249 | 34 | 0.0099584 | 0.33859 | 1960 | 20446.5319 | 254.6808 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10564 | WISE 110163199 | 152271101 | WISE 1101 | 0.61492 | 8 | 0.0099235 | 0.079388 | 1961 | 20447.1469 | 254.6014 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6010 | MORGAN HILL 2111XR292 | 83242111 | MORGAN HILL 2111 | 11.1721 | 130 | 0.0098996 | 1.287 | 1962 | 20458.319 | 253.3144 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
222 | DUNBAR 1102CB | 43071102 | DUNBAR 1102 | 7.9142 | 113 | 0.0098816 | 1.1166 | 1963 | 20466.2331 | 252.1978 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8045 | PERRY 1101W26 | 183071101 | PERRY 1101 | 2.7287 | 18 | 0.0098794 | 0.17783 | 1964 | 20468.9618 | 252.02 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7530 | BUCKS CREEK 11031131 | 102211103 | BUCKS CREEK 1103 | 2.7496 | 33 | 0.0098607 | 0.3254 | 1965 | 20471.7114 | 251.6946 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7965 | RINCON 1103568 | 43321103 | RINCON 1103 | 12.6078 | 129 | 0.0098399 | 1.2694 | 1966 | 20484.3192 | 250.4252 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7623 | PANOCHE 11034008 | 253671103 | PANOCHE 1103 | 35.3757 | 138 | 0.0097859 | 1.3505 | 1967 | 20519.6949 | 249.0748 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1557 | WILLOW CREEK 11015002 | 192171101 | WILLOW CREEK 1101 | 13.6356 | 161 | 0.0097721 | 1.5733 | 1968 | 20533.3305 | 247.5015 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2260 | EL DORADO PH 210152456 | 152762101 | EL DORADO PH 2101 | 10.2017 | 96 | 0.0097493 | 0.93593 | 1969 | 20543.5323 | 246.5655 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4474 | SPENCE 1104965598 | 182201104 | SPENCE 1104 | 9.2081 | 139 | 0.0097442 | 1.3544 | 1970 | 20552.7404 | 245.2111 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9612 | DIAMOND SPRINGS 1107203504 | 152261107 | DIAMOND SPRINGS 1107 | 0.14077 | 4 | 0.0097327 | 0.038931 | 1971 | 20552.8811 | 245.1721 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7259 | SUMMIT 1101742 | 152591101 | SUMMIT 1101 | 1.2955 | 21 | 0.009698 | 0.20366 | 1972 | 20554.1766 | 244.9685 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3486 | GRASS VALLEY 11012208 | 152031101 | GRASS VALLEY 1101 | 11.791 | 159 | 0.0096885 | 1.5405 | 1973 | 20565.9676 | 243.428 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6926 | EL DORADO PH 210113532 | 152762101 | EL DORADO PH 2101 | 5.3305 | 46 | 0.0096754 | 0.44507 | 1974 | 20571.2981 | 242.9829 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4034 | OAKHURST 11035120 | 254421103 | OAKHURST 1103 | 6.1606 | 19 | 0.0096488 | 0.18333 | 1975 | 20577.4587 | 242.7996 | 242.7996 | #N/A | TRUE | 4.23 | FALSE | TRUE
3547 | RINCON 1101539980 | 43321101 | RINCON 1101 | 0.295 | 4 | 0.0096291 | 0.038517 | 1976 | 20577.7537 | 242.7611 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2441 | SILVERADO 2103617828 | 43432103 | SILVERADO 2103 | 1.4315 | 28 | 0.0096279 | 0.26958 | 1977 | 20579.1852 | 242.4915 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5129 | NEWBURG 1131380686 | 192151131 | NEWBURG 1131 | 1.8735 | 34 | 0.0095954 | 0.32624 | 1978 | 20581.0587 | 242.1653 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2275 | BUTTE 11051243 | 103081105 | BUTTE 1105 | 5.1707 | 50 | 0.0095359 | 0.47679 | 1979 | 20586.2295 | 241.6885 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4445 | PINE GROVE 1102467560 | 163751102 | PINE GROVE 1102 | 2.038 | 27 | 0.009532 | 0.25736 | 1980 | 20588.2675 | 241.4311 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6213 | JESSUP 1103728460 | 103441103 | JESSUP 1103 | 0.72903 | 17 | 0.0095302 | 0.16201 | 1981 | 20588.9965 | 241.2691 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3085 | SHINGLE SPRINGS 210819622 | 153652108 | SHINGLE SPRINGS 2108 | 5.6185 | 165 | 0.0095283 | 1.5722 | 1982 | 20594.615 | 239.6969 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9214 | SAN RAFAEL 11081250 | 42011108 | SAN RAFAEL 1108 | 3.5686 | 26 | 0.0094996 | 0.24699 | 1983 | 20598.1837 | 239.4499 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10597 | MONTE RIO 11135024 | 42811113 | MONTE RIO 1113 | 0.32729 | 4 | 0.0094858 | 0.037943 | 1984 | 20598.5109 | 239.412 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2882 | WILLOW PASS 2108CB | 13912108 | WILLOW PASS 2108 | 0.19769 | 91 | 0.0094639 | 0.86121 | 1985 | 20598.7086 | 238.5508 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5172 | LOS OSITOS 2103220608 | 182082103 | LOS OSITOS 2103 | 1.0434 | 10 | 0.009449 | 0.09449 | 1986 | 20599.752 | 238.4563 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1655 | BRUNSWICK 110750010 | 152481107 | BRUNSWICK 1107 | 6.1163 | 117 | 0.0094406 | 1.1046 | 1987 | 20605.8683 | 237.3518 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3494 | WILLITS 110434008 | 42661104 | WILLITS 1104 | 22.9249 | 259 | 0.0094239 | 2.4408 | 1988 | 20628.7932 | 234.911 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7626 | RESERVATION ROAD 11023030 | 182731102 | RESERVATION ROAD 1102 | 10.026 | 186 | 0.0094083 | 1.7499 | 1989 | 20638.8193 | 233.161 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10686 | HARTLEY 110158095 | 43211101 | HARTLEY 1101 | 0.15657 | 2 | 0.0094017 | 0.018803 | 1990 | 20638.9758 | 233.1422 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7656 | PHILO 11022600 | 42601102 | PHILO 1102 | 20.0154 | 114 | 0.0093006 | 1.0603 | 1991 | 20658.9912 | 232.0819 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7863 | SANTA ROSA A 1104642 | 42151104 | SANTA ROSA A 1104 | 9.3201 | 127 | 0.0092364 | 1.173 | 1992 | 20668.3112 | 230.9089 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
581 | POINT ARENA 1101474 | 43381101 | POINT ARENA 1101 | 9.0096 | 77 | 0.0092125 | 0.70936 | 1993 | 20677.3209 | 230.1996 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9791 | LOS OSITOS 2103695270 | 182082103 | LOS OSITOS 2103 | 0.69372 | 12 | 0.009199 | 0.11039 | 1994 | 20678.0146 | 230.0892 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9383 | CASTRO VALLEY 1110MR525 | 14091110 | CASTRO VALLEY 1110 | 0.011114 | 2 | 0.0091967 | 0.018393 | 1995 | 20678.0257 | 230.0708 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5023 | MC ARTHUR 11021324 | 103491102 | MC ARTHUR 1102 | 1.0184 | 169 | 0.0091756 | 1.5507 | 1996 | 20679.0441 | 228.5201 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7662 | CASTRO VALLEY 1110610800 | 14091110 | CASTRO VALLEY 1110 | 2.4009 | 33 | 0.0091096 | 0.30062 | 1997 | 20681.445 | 228.2195 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6717 | NEWBURG 1132910230 | 192151132 | NEWBURG 1132 | 0.96986 | 27 | 0.0090947 | 0.24556 | 1998 | 20682.4148 | 227.9739 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10 | KONOCTI 1102532 | 43311102 | KONOCTI 1102 | 9.7315 | 124 | 0.0090595 | 1.1234 | 1999 | 20692.1463 | 226.8505 | 226.8505 | #N/A | TRUE | 1.0646 | TRUE | TRUE
5170 | EL DORADO PH 2102542272 | 152762102 | EL DORADO PH 2102 | 7.8219 | 80 | 0.0090446 | 0.72357 | 2000 | 20699.9682 | 226.127 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8963 | MIRABEL 1101253331 | 42091101 | MIRABEL 1101 | 0.06691 | 5 | 0.0090171 | 0.045085 | 2001 | 20700.0351 | 226.0819 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10053 | ROB ROY 21046577 | 83692104 | ROB ROY 2104 | 3.4689 | 33 | 0.0089943 | 0.29681 | 2002 | 20703.504 | 225.7851 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8505 | NEWBURG 113190242 | 192151131 | NEWBURG 1131 | 4.1346 | 51 | 0.0089934 | 0.45866 | 2003 | 20707.6386 | 225.3264 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
283 | SAN RAFAEL 1104802 | 42011104 | SAN RAFAEL 1104 | 8.5661 | 162 | 0.0089568 | 1.451 | 2004 | 20716.2047 | 223.8754 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9446 | ECHO SUMMIT 1101481660 | 158031101 | ECHO SUMMIT 1101 | 1.0879 | 21 | 0.0089565 | 0.18809 | 2005 | 20717.2925 | 223.6873 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1636 | LOS COCHES 1101625902 | 182151101 | LOS COCHES 1101 | 2.6193 | 26 | 0.0089147 | 0.23178 | 2006 | 20719.9118 | 223.4555 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8007 | SAN JUSTO 11014002 | 183181101 | SAN JUSTO 1101 | 18.3678 | 140 | 0.0088999 | 1.246 | 2007 | 20738.2796 | 222.2095 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4827 | ATASCADERO 1103A88 | 182541103 | ATASCADERO 1103 | 0.93649 | 41 | 0.008869 | 0.36363 | 2008 | 20739.2161 | 221.8459 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6300 | DRUM 11011602 | 152321101 | DRUM 1101 | 16.2013 | 121 | 0.0088619 | 1.0723 | 2009 | 20755.4174 | 220.7736 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7254 | ALLEGHANY 1101VR816 | 152101101 | ALLEGHANY 1101 | 4.1491 | 49 | 0.0088541 | 0.43385 | 2010 | 20759.5665 | 220.3398 | 220.3398 | #N/A | TRUE | 1.74 | TRUE | TRUE
2986 | PINE GROVE 110235576 | 163751102 | PINE GROVE 1102 | 7.8788 | 77 | 0.0088445 | 0.68102 | 2011 | 20767.4453 | 219.6588 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8230 | SAN LUIS OBISPO 1102357407 | 182631102 | SAN LUIS OBISPO 1102 | 0.23782 | 5 | 0.0088377 | 0.044188 | 2012 | 20767.6831 | 219.6146 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1189 | PEORIA 170575274 | 163781705 | PEORIA 1705 | 0.38764 | 43 | 0.0088331 | 0.37982 | 2013 | 20768.0708 | 219.2347 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
299 | MONTE RIO 111164758 | 42811111 | MONTE RIO 1111 | 10.4662 | 97 | 0.0087918 | 0.8528 | 2014 | 20778.537 | 218.3819 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8131 | HARTLEY 1101534548 | 43211101 | HARTLEY 1101 | 0.40005 | 7 | 0.008746 | 0.061222 | 2015 | 20778.937 | 218.3207 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3395 | BOLINAS 1101504 | 42261101 | BOLINAS 1101 | 6.6893 | 53 | 0.0087025 | 0.46123 | 2016 | 20785.6264 | 217.8595 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6220 | LAKEVILLE 1102530 | 43371102 | LAKEVILLE 1102 | 0.071467 | 55 | 0.0087005 | 0.47853 | 2017 | 20785.6978 | 217.381 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8104 | MONTE RIO 111137520 | 42811111 | MONTE RIO 1111 | 2.1367 | 20 | 0.0086846 | 0.17369 | 2018 | 20787.8345 | 217.2073 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5024 | MONTE RIO 1113180 | 42811113 | MONTE RIO 1113 | 1.9628 | 28 | 0.0086779 | 0.24298 | 2019 | 20789.7973 | 216.9643 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2418 | CLEAR LAKE 11011302 | 42141101 | CLEAR LAKE 1101 | 7.5749 | 189 | 0.0086777 | 1.6401 | 2020 | 20797.3722 | 215.3242 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6344 | WEST POINT 11021303 | 163201102 | WEST POINT 1102 | 15.6665 | 146 | 0.0086648 | 1.2651 | 2021 | 20813.0387 | 214.0591 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
147 | SHADY GLEN 11022232 | 152431102 | SHADY GLEN 1102 | 10.4684 | 88 | 0.0086414 | 0.76044 | 2022 | 20823.5072 | 213.2987 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8652 | LOYOLA 1102725939 | 82161102 | LOYOLA 1102 | 0.093558 | 14 | 0.0086108 | 0.12055 | 2023 | 20823.6007 | 213.1782 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10013 | GREEN VALLEY 21016601 | 83192101 | GREEN VALLEY 2101 | 1.904 | 19 | 0.0085862 | 0.16314 | 2024 | 20825.5048 | 213.015 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3970 | PUEBLO 1105348368 | 43291105 | PUEBLO 1105 | 2.7804 | 107 | 0.0085797 | 0.91803 | 2025 | 20828.2852 | 212.097 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5419 | MIRABEL 11014859 | 42091101 | MIRABEL 1101 | 1.8699 | 22 | 0.0085572 | 0.18826 | 2026 | 20830.155 | 211.9087 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3836 | PURISIMA 1101CB | 182971101 | PURISIMA 1101 | 3.6778 | 32 | 0.0085315 | 0.27301 | 2027 | 20833.8328 | 211.6357 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
589 | EL DORADO PH 21016852 | 152762101 | EL DORADO PH 2101 | 25.2481 | 309 | 0.0085289 | 2.6354 | 2028 | 20859.081 | 209.0003 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7704 | GOLDTREE 1107CB | 182581107 | GOLDTREE 1107 | 0.9199 | 28 | 0.0085282 | 0.23879 | 2029 | 20860.0009 | 208.7615 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10273 | POINT ARENA 11014923 | 43381101 | POINT ARENA 1101 | 2.866 | 12 | 0.008518 | 0.10222 | 2030 | 20862.8668 | 208.6593 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
327 | CURTIS 170463502 | 163351704 | CURTIS 1704 | 10.4643 | 107 | 0.0084952 | 0.90898 | 2031 | 20873.3311 | 207.7503 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7937 | CLARK ROAD 11022068 | 103091102 | CLARK ROAD 1102 | 10.8871 | 90 | 0.0084897 | 0.76407 | 2032 | 20884.2182 | 206.9862 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4769 | WYANDOTTE 1107CB | 102911107 | WYANDOTTE 1107 | 1.2619 | 199 | 0.0084763 | 1.6868 | 2033 | 20885.4801 | 205.2995 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7564 | COLUMBIA HILL 11018233 | 152471101 | COLUMBIA HILL 1101 | 4.9588 | 51 | 0.008467 | 0.43182 | 2034 | 20890.4389 | 204.8676 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2536 | HALSEY 1101CB | 152241101 | HALSEY 1101 | 17.1811 | 231 | 0.0084422 | 1.9501 | 2035 | 20907.62 | 202.9175 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2174 | DIAMOND SPRINGS 1104CB | 152261104 | DIAMOND SPRINGS 1104 | 5.6226 | 127 | 0.008393 | 1.0659 | 2036 | 20913.2426 | 201.8516 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4975 | EL DORADO PH 210119612 | 152762101 | EL DORADO PH 2101 | 9.1294 | 102 | 0.0083743 | 0.85418 | 2037 | 20922.372 | 200.9974 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7088 | SAUSALITO 11021500 | 42491102 | SAUSALITO 1102 | 1.1618 | 8 | 0.0083473 | 0.066779 | 2038 | 20923.5338 | 200.9306 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4510 | CAMP EVERS 210511010 | 83622105 | CAMP EVERS 2105 | 2.176 | 26 | 0.0083235 | 0.21641 | 2039 | 20925.7098 | 200.7142 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7509 | WESTLEY 1103237522 | 162671103 | WESTLEY 1103 | 0.92354 | 39 | 0.0082937 | 0.32346 | 2040 | 20926.6334 | 200.3908 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2971 | CASTRO VALLEY 1111MR334 | 14091111 | CASTRO VALLEY 1111 | 5.666 | 80 | 0.0082358 | 0.65886 | 2041 | 20932.2994 | 199.7319 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
143 | RACETRACK 1703CB | 163761703 | RACETRACK 1703 | 15.7571 | 216 | 0.008163 | 1.7632 | 2042 | 20948.0565 | 197.9687 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1117 | MORGAN HILL 2104152774 | 83242104 | MORGAN HILL 2104 | 6.4135 | 84 | 0.0081314 | 0.68304 | 2043 | 20954.4699 | 197.2857 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3526 | SILVERADO 2103920793 | 43432103 | SILVERADO 2103 | 6.5094 | 51 | 0.008033 | 0.40968 | 2044 | 20960.9794 | 196.876 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7263 | FORESTHILL 11011820 | 152181101 | FORESTHILL 1101 | 5.735 | 51 | 0.0080276 | 0.40941 | 2045 | 20966.7144 | 196.4666 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4807 | PLACER 1103238990 | 152461103 | PLACER 1103 | 0.040446 | 84 | 0.0080184 | 0.67354 | 2046 | 20966.7548 | 195.793 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7786 | UPPER LAKE 11016663 | 42871101 | UPPER LAKE 1101 | 2.3539 | 17 | 0.0079953 | 0.13592 | 2047 | 20969.1088 | 195.6571 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
797 | DUNBAR 1101CB | 43071101 | DUNBAR 1101 | 3.1203 | 191 | 0.007993 | 1.5267 | 2048 | 20972.2291 | 194.1304 | 194.1304 | #N/A | TRUE | 2.0114 | TRUE | TRUE
1103 | HOOPA 1101CB | 192401101 | HOOPA 1101 | 23.229 | 440 | 0.0079104 | 3.4806 | 2049 | 20995.4581 | 190.6499 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8668 | BIG BASIN 110211062 | 82841102 | BIG BASIN 1102 | 13.3177 | 88 | 0.007899 | 0.69511 | 2050 | 21008.7758 | 189.9548 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7844 | ELK 11011260 | 42981101 | ELK 1101 | 15.6786 | 120 | 0.0078966 | 0.94759 | 2051 | 21024.4544 | 189.0072 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2387 | HALSEY 110239104 | 152241102 | HALSEY 1102 | 30.6812 | 346 | 0.007888 | 2.7292 | 2052 | 21055.1356 | 186.2779 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1085 | MORAGA 1101CB | 13801101 | MORAGA 1101 | 8.4595 | 92 | 0.0078811 | 0.72506 | 2053 | 21063.5951 | 185.5529 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6726 | MARTELL 110292172 | 163011102 | MARTELL 1102 | 0.11858 | 45 | 0.0078638 | 0.35387 | 2054 | 21063.7137 | 185.199 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1984 | HALF MOON BAY 110369412 | 24101103 | HALF MOON BAY 1103 | 15.5679 | 150 | 0.0078448 | 1.1767 | 2055 | 21079.2816 | 184.0223 | 184.0223 | #N/A | TRUE | 5.42 | TRUE | TRUE
2299 | VINEYARD 2107CB | 14502107 | VINEYARD 2107 | 1.9079 | 111 | 0.0077955 | 0.8653 | 2056 | 21081.1895 | 183.157 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9627 | POINT ARENA 11011296 | 43381101 | POINT ARENA 1101 | 3.4995 | 37 | 0.007772 | 0.28757 | 2057 | 21084.6891 | 182.8694 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2765 | FORESTHILL 1101CB | 152181101 | FORESTHILL 1101 | 9.1111 | 110 | 0.0077431 | 0.85174 | 2058 | 21093.8002 | 182.0177 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4087 | BURNEY 11011340 | 103311101 | BURNEY 1101 | 18.0215 | 144 | 0.0077101 | 1.1103 | 2059 | 21111.8216 | 180.9074 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8844 | MIDDLETOWN 1101614 | 43141101 | MIDDLETOWN 1101 | 1.3814 | 18 | 0.0076984 | 0.13857 | 2060 | 21113.2031 | 180.7688 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3083 | MONTE RIO 1113320 | 42811113 | MONTE RIO 1113 | 2.7766 | 29 | 0.0076924 | 0.22308 | 2061 | 21115.9796 | 180.5458 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7740 | POINT MORETTI 110136514 | 82931101 | POINT MORETTI 1101 | 6.8677 | 64 | 0.0076624 | 0.4904 | 2062 | 21122.8473 | 180.0554 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
898 | COTATI 11055156 | 42271105 | COTATI 1105 | 4.8381 | 114 | 0.0076261 | 0.86938 | 2063 | 21127.6854 | 179.186 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3027 | PHILO 11021308 | 42601102 | PHILO 1102 | 32.0022 | 245 | 0.0076242 | 1.8679 | 2064 | 21159.6876 | 177.3181 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10504 | KANAKA 11011036 | 103221101 | KANAKA 1101 | 0.61495 | 4 | 0.0076073 | 0.030429 | 2065 | 21160.3026 | 177.2876 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2446 | FOOTHILL 1102V06 | 182951102 | FOOTHILL 1102 | 2.2392 | 66 | 0.007606 | 0.50199 | 2066 | 21162.5417 | 176.7856 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4588 | COARSEGOLD 21025722 | 254432102 | COARSEGOLD 2102 | 1.978 | 23 | 0.0076053 | 0.17492 | 2067 | 21164.5197 | 176.6107 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8714 | OTTER 1101CB | 182941101 | OTTER 1101 | 6.4437 | 54 | 0.0075954 | 0.41015 | 2068 | 21170.9634 | 176.2006 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9866 | DUNBAR 1101343 | 43071101 | DUNBAR 1101 | 4.4381 | 39 | 0.0075606 | 0.29486 | 2069 | 21175.4015 | 175.9057 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
723 | BIG BASIN 110296986 | 82841102 | BIG BASIN 1102 | 5.9027 | 63 | 0.0075562 | 0.47604 | 2070 | 21181.3043 | 175.4297 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5272 | NEWBURG 1133CB | 192151133 | NEWBURG 1133 | 3.163 | 92 | 0.0075338 | 0.69311 | 2071 | 21184.4672 | 174.7365 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6817 | HALF MOON BAY 1103695411 | 24101103 | HALF MOON BAY 1103 | 8.2989 | 99 | 0.0075292 | 0.74539 | 2072 | 21192.7662 | 173.9911 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9735 | EEL RIVER 1103216324 | 192381103 | EEL RIVER 1103 | 2.2883 | 23 | 0.0075204 | 0.17297 | 2073 | 21195.0545 | 173.8182 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
803 | DIAMOND SPRINGS 1107CB | 152261107 | DIAMOND SPRINGS 1107 | 0 | 51 | 0.0074949 | 0.38224 | 2074 | 21195.0545 | 173.4359 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2229 | EL DORADO PH 210136764 | 152762101 | EL DORADO PH 2101 | 3.129 | 46 | 0.0074941 | 0.34473 | 2075 | 21198.1835 | 173.0912 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5945 | SANTA ROSA A 1111758024 | 42151111 | SANTA ROSA A 1111 | 4.7171 | 72 | 0.007484 | 0.53884 | 2076 | 21202.9007 | 172.5524 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
726 | DIAMOND SPRINGS 1106930190 | 152261106 | DIAMOND SPRINGS 1106 | 17.1408 | 207 | 0.0074761 | 1.5476 | 2077 | 21220.0415 | 171.0048 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
353 | CURTIS 170210940 | 163351702 | CURTIS 1702 | 8.5923 | 138 | 0.0073788 | 1.0183 | 2078 | 21228.6337 | 169.9865 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1231 | RED BLUFF 1103CB | 103541103 | RED BLUFF 1103 | 0.10234 | 261 | 0.0073172 | 1.9098 | 2079 | 21228.7361 | 168.0767 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10001 | PANOCHE 11034036 | 253671103 | PANOCHE 1103 | 9.9443 | 57 | 0.0073003 | 0.41612 | 2080 | 21238.6804 | 167.6606 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9426 | GREEN VALLEY 2101380922 | 83192101 | GREEN VALLEY 2101 | 0.98732 | 30 | 0.0072901 | 0.2187 | 2081 | 21239.6677 | 167.4419 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1700 | LUCERNE 110676850 | 43351106 | LUCERNE 1106 | 2.1492 | 51 | 0.0072691 | 0.37072 | 2082 | 21241.8169 | 167.0712 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2002 | HOLLISTER 21054018 | 182492105 | HOLLISTER 2105 | 44.4195 | 280 | 0.0072679 | 2.035 | 2083 | 21286.2364 | 165.0362 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2867 | MONTE RIO 1113346 | 42811113 | MONTE RIO 1113 | 10.0437 | 101 | 0.0072159 | 0.72881 | 2084 | 21296.2802 | 164.3074 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7311 | LOS OSITOS 2102258878 | 182082102 | LOS OSITOS 2102 | 3.3295 | 26 | 0.0072141 | 0.18757 | 2085 | 21299.6097 | 164.1198 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1213 | WOODACRE 1102137662 | 43021102 | WOODACRE 1102 | 8.585 | 104 | 0.0071841 | 0.74714 | 2086 | 21308.1947 | 163.3727 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2384 | BONNIE NOOK 1102CB | 152301102 | BONNIE NOOK 1102 | 34.0109 | 337 | 0.0071702 | 2.4164 | 2087 | 21342.2056 | 160.9563 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
324 | PLACERVILLE 1110953474 | 153081110 | PLACERVILLE 1110 | 10.6374 | 133 | 0.0071239 | 0.94748 | 2088 | 21352.843 | 160.0088 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9849 | FOOTHILL 1101722270 | 182951101 | FOOTHILL 1101 | 0.17623 | 5 | 0.0070957 | 0.035479 | 2089 | 21353.0192 | 159.9733 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3510 | MONTE RIO 1111140 | 42811111 | MONTE RIO 1111 | 8.4064 | 96 | 0.0070376 | 0.67561 | 2090 | 21361.4256 | 159.2977 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1551 | CARLOTTA 11214914 | 192291121 | CARLOTTA 1121 | 10.6261 | 138 | 0.0070374 | 0.97117 | 2091 | 21372.0518 | 158.3266 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4560 | COARSEGOLD 210210330 | 254432102 | COARSEGOLD 2102 | 9.6646 | 90 | 0.0069896 | 0.62906 | 2092 | 21381.7164 | 157.6975 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6442 | PIT NO 1 11019702 | 103721101 | PIT NO 1 1101 | 0.64383 | 91 | 0.006985 | 0.63564 | 2093 | 21382.3602 | 157.0619 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8877 | WILLOW CREEK 11013050 | 192171101 | WILLOW CREEK 1101 | 2.6251 | 18 | 0.0069828 | 0.12569 | 2094 | 21384.9852 | 156.9362 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9559 | SONOMA 1103581588 | 42721103 | SONOMA 1103 | 0.19454 | 14 | 0.0069585 | 0.097419 | 2095 | 21385.1798 | 156.8388 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2326 | BRUNSWICK 11052140 | 152481105 | BRUNSWICK 1105 | 34.5738 | 373 | 0.0069513 | 2.5928 | 2096 | 21419.7536 | 154.2459 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7797 | SAUSALITO 1101331806 | 42491101 | SAUSALITO 1101 | 0.49662 | 5 | 0.0069274 | 0.034637 | 2097 | 21420.2502 | 154.2113 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1778 | WEIMAR 11026175 | 152491102 | WEIMAR 1102 | 2.7461 | 30 | 0.0069045 | 0.20713 | 2098 | 21422.9963 | 154.0042 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2962 | CURTIS 1704803 | 163351704 | CURTIS 1704 | 9.7146 | 93 | 0.0068944 | 0.64118 | 2099 | 21432.7109 | 153.363 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5429 | MIRABEL 1101228 | 42091101 | MIRABEL 1101 | 2.115 | 123 | 0.0068367 | 0.84091 | 2100 | 21434.8259 | 152.5221 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8011 | HORSESHOE 1101603250 | 152571101 | HORSESHOE 1101 | 0.57636 | 21 | 0.0068337 | 0.14351 | 2101 | 21435.4023 | 152.3786 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7095 | PUEBLO 2102618 | 43292102 | PUEBLO 2102 | 0.46132 | 118 | 0.0068234 | 0.80516 | 2102 | 21435.8636 | 151.5734 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8240 | WOODSIDE 11018601 | 24251101 | WOODSIDE 1101 | 0.59766 | 9 | 0.0067792 | 0.061013 | 2103 | 21436.4613 | 151.5124 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3848 | REEDLEY 11127240 | 252341112 | REEDLEY 1112 | 0.96577 | 234 | 0.0067642 | 1.5828 | 2104 | 21437.427 | 149.9296 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4429 | SONOMA 1105138 | 42721105 | SONOMA 1105 | 0.064666 | 197 | 0.0067556 | 1.3309 | 2105 | 21437.4917 | 148.5987 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1588 | CORRAL 110359770 | 162991103 | CORRAL 1103 | 4.8165 | 97 | 0.0067467 | 0.65443 | 2106 | 21442.3082 | 147.9443 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6984 | GABILAN 1101566352 | 182331101 | GABILAN 1101 | 0.42309 | 9 | 0.0067421 | 0.060679 | 2107 | 21442.7313 | 147.8836 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8546 | SPENCE 1102990464 | 182201102 | SPENCE 1102 | 2.092 | 53 | 0.0067321 | 0.3568 | 2108 | 21444.8233 | 147.5268 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9813 | BOLINAS 110137034 | 42261101 | BOLINAS 1101 | 4.5289 | 16 | 0.006701 | 0.10722 | 2109 | 21449.3522 | 147.4196 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8495 | PENRYN 110550550 | 152561105 | PENRYN 1105 | 0 | 127 | 0.0066813 | 0.84852 | 2110 | 21449.3522 | 146.5711 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
533 | HIGHLANDS 110439458 | 43361104 | HIGHLANDS 1104 | 1.1825 | 72 | 0.0066627 | 0.47971 | 2111 | 21450.5347 | 146.0913 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6908 | MENLO 11038512 | 24131103 | MENLO 1103 | 24.7387 | 228 | 0.0066372 | 1.5133 | 2112 | 21475.2734 | 144.5781 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1455 | LAS GALLINAS A 1105904 | 42991105 | LAS GALLINAS A 1105 | 1.5346 | 78 | 0.0066274 | 0.51694 | 2113 | 21476.808 | 144.0611 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2184 | GEYSERVILLE 110289714 | 42891102 | GEYSERVILLE 1102 | 0.11077 | 71 | 0.0066271 | 0.47052 | 2114 | 21476.9188 | 143.5906 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2865 | MOLINO 1102344 | 42571102 | MOLINO 1102 | 1.5085 | 77 | 0.0066172 | 0.50953 | 2115 | 21478.4273 | 143.0811 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2057 | SHINGLE SPRINGS 210911092 | 153652109 | SHINGLE SPRINGS 2109 | 22.4365 | 239 | 0.0066099 | 1.5798 | 2116 | 21500.8638 | 141.5013 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10095 | SILVERADO 2104645 | 43432104 | SILVERADO 2104 | 1.0111 | 13 | 0.0065604 | 0.085285 | 2117 | 21501.8749 | 141.416 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6812 | CLOVERDALE 1101474708 | 42821101 | CLOVERDALE 1101 | 0.2623 | 13 | 0.0065356 | 0.084962 | 2118 | 21502.1372 | 141.3311 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
891 | TEMPLETON 2108A64 | 183052108 | TEMPLETON 2108 | 2.0152 | 150 | 0.0065293 | 0.9794 | 2119 | 21504.1525 | 140.3517 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
851 | HIGGINS 1110861610 | 152691110 | HIGGINS 1110 | 1.0502 | 99 | 0.0065286 | 0.64633 | 2120 | 21505.2027 | 139.7053 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10050 | MIRABEL 110286326 | 42091102 | MIRABEL 1102 | 0.70422 | 5 | 0.0065228 | 0.032614 | 2121 | 21505.9069 | 139.6727 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1904 | SONOMA 1105404 | 42721105 | SONOMA 1105 | 2.3529 | 63 | 0.0065164 | 0.41053 | 2122 | 21508.2598 | 139.2622 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4884 | PLACERVILLE 1112CB | 153081112 | PLACERVILLE 1112 | 8.513 | 117 | 0.0065148 | 0.76223 | 2123 | 21516.7728 | 138.5 | 138.5 | #N/A | TRUE | 0.38015 | TRUE | TRUE
3571 | OAKHURST 110377384 | 254421103 | OAKHURST 1103 | 4.7207 | 61 | 0.0065145 | 0.39738 | 2124 | 21521.4935 | 138.1026 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2586 | VOLTA 11021504 | 102541102 | VOLTA 1102 | 8.2955 | 95 | 0.0065125 | 0.61869 | 2125 | 21529.789 | 137.4839 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5574 | PARADISE 1104920400 | 102831104 | PARADISE 1104 | 4.6854 | 66 | 0.0064968 | 0.42879 | 2126 | 21534.4744 | 137.0551 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3679 | SUNOL 1101MR297 | 14241101 | SUNOL 1101 | 5.9239 | 66 | 0.0064881 | 0.42822 | 2127 | 21540.3983 | 136.6269 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3379 | GEYSERVILLE 1101354 | 42891101 | GEYSERVILLE 1101 | 0.62784 | 79 | 0.0064828 | 0.51214 | 2128 | 21541.0262 | 136.1147 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5354 | FORT ROSS 1121560 | 42851121 | FORT ROSS 1121 | 5.0625 | 31 | 0.0064599 | 0.20026 | 2129 | 21546.0887 | 135.9145 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1701 | CALAVERAS CEMENT 110136880 | 162211101 | CALAVERAS CEMENT 1101 | 6.1526 | 92 | 0.0064477 | 0.59319 | 2130 | 21552.2412 | 135.3213 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3076 | PLACERVILLE 21061104 | 153082106 | PLACERVILLE 2106 | 49.4989 | 462 | 0.0064469 | 2.9785 | 2131 | 21601.7401 | 132.3428 | 132.3428 | #N/A | TRUE | 0.7 | TRUE | TRUE
6813 | CASTRO VALLEY 111010315 | 14091110 | CASTRO VALLEY 1110 | 5.489 | 53 | 0.006431 | 0.34084 | 2132 | 21607.2291 | 132.002 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7135 | MOLINO 1102982462 | 42571102 | MOLINO 1102 | 1.4422 | 18 | 0.006427 | 0.11569 | 2133 | 21608.6713 | 131.8863 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8349 | BRUNSWICK 1110CB | 152481110 | BRUNSWICK 1110 | 0.0034177 | 26 | 0.0064174 | 0.16685 | 2134 | 21608.6748 | 131.7194 | 131.7194 | #N/A | TRUE | 0.055871 | TRUE | TRUE
3244 | PLACERVILLE 111219712 | 153081112 | PLACERVILLE 1112 | 12.9125 | 151 | 0.0064118 | 0.96818 | 2135 | 21621.5873 | 130.7513 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3409 | PINE GROVE 110213438 | 163751102 | PINE GROVE 1102 | 16.5438 | 172 | 0.0063999 | 1.1008 | 2136 | 21638.1311 | 129.6505 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9640 | OLEMA 110149756 | 42291101 | OLEMA 1101 | 1.0738 | 40 | 0.0063622 | 0.25449 | 2137 | 21639.2049 | 129.396 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5813 | PERRY 1101CB | 183071101 | PERRY 1101 | 2.539 | 27 | 0.0062536 | 0.16885 | 2138 | 21641.7438 | 129.2271 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5598 | FROGTOWN 170236870 | 163451702 | FROGTOWN 1702 | 0.33642 | 29 | 0.0062483 | 0.1812 | 2139 | 21642.0803 | 129.0459 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7823 | FORT BRAGG A 11013113 | 42761101 | FORT BRAGG A 1101 | 10.0269 | 68 | 0.0062347 | 0.42396 | 2140 | 21652.1072 | 128.622 | 128.622 | #N/A | TRUE | 0.51 | FALSE | TRUE
3839 | PARADISE 11052214 | 102831105 | PARADISE 1105 | 15.0808 | 233 | 0.0062243 | 1.4503 | 2141 | 21667.188 | 127.1717 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
955 | STANISLAUS 170179826 | 162821701 | STANISLAUS 1701 | 10.3076 | 95 | 0.0062159 | 0.59051 | 2142 | 21677.4956 | 126.5812 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
165 | CHALLENGE 110198174 | 103201101 | CHALLENGE 1101 | 12.2322 | 66 | 0.0062048 | 0.40952 | 2143 | 21689.7278 | 126.1717 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2120 | BRUNSWICK 110350070 | 152481103 | BRUNSWICK 1103 | 17.7473 | 201 | 0.0062036 | 1.2469 | 2144 | 21707.475 | 124.9248 | 124.9248 | #N/A | TRUE | 9.1785 | TRUE | TRUE
4607 | SARATOGA 1107413816 | 83371107 | SARATOGA 1107 | 11.1426 | 104 | 0.0061927 | 0.64404 | 2145 | 21718.6176 | 124.2807 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1564 | SAN LUIS OBISPO 1101483444 | 182631101 | SAN LUIS OBISPO 1101 | 2.0579 | 67 | 0.0061552 | 0.4124 | 2146 | 21720.6754 | 123.8683 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4427 | PLACERVILLE 11118582 | 153081111 | PLACERVILLE 1111 | 9.4809 | 163 | 0.0061345 | 0.99993 | 2147 | 21730.1563 | 122.8684 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9649 | LOS GATOS 1107LA60 | 82021107 | LOS GATOS 1107 | 8.6744 | 61 | 0.0061263 | 0.3737 | 2148 | 21738.8308 | 122.4947 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3992 | VOLTA 11021502 | 102541102 | VOLTA 1102 | 7.2593 | 80 | 0.0061144 | 0.48915 | 2149 | 21746.0901 | 122.0056 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4576 | VALLEY VIEW 1106CB | 14341106 | VALLEY VIEW 1106 | 3.7553 | 50 | 0.0060781 | 0.30391 | 2150 | 21749.8454 | 121.7016 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10363 | SAN LEANDRO U 1114653758 | 13111114 | SAN LEANDRO U 1114 | 0.36194 | 5 | 0.0060671 | 0.030336 | 2151 | 21750.2074 | 121.6713 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7007 | ORO FINO 110238698 | 103031102 | ORO FINO 1102 | 15.6488 | 103 | 0.0060349 | 0.62159 | 2152 | 21765.8562 | 121.0497 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3531 | HALF MOON BAY 11039112 | 24101103 | HALF MOON BAY 1103 | 0.86172 | 68 | 0.0060009 | 0.40806 | 2153 | 21766.7179 | 120.6417 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9344 | HALF MOON BAY 1101821698 | 24101101 | HALF MOON BAY 1101 | 0.84831 | 9 | 0.0060008 | 0.054007 | 2154 | 21767.5662 | 120.5876 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10526 | SANTA ROSA A 1108409621 | 42151108 | SANTA ROSA A 1108 | 0.13619 | 4 | 0.0059943 | 0.023977 | 2155 | 21767.7024 | 120.5637 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3796 | CAMP EVERS 210612518 | 83622106 | CAMP EVERS 2106 | 15.6477 | 145 | 0.0059295 | 0.85978 | 2156 | 21783.3501 | 119.7039 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2601 | BRUNSWICK 11062104 | 152481106 | BRUNSWICK 1106 | 9.8261 | 123 | 0.0059169 | 0.72777 | 2157 | 21793.1763 | 118.9761 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2204 | OAKHURST 11035470 | 254421103 | OAKHURST 1103 | 9.3162 | 104 | 0.0059093 | 0.61457 | 2158 | 21802.4925 | 118.3616 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2618 | ARVIN 110194892 | 253801101 | ARVIN 1101 | 0.21503 | 66 | 0.0059064 | 0.38983 | 2159 | 21802.7075 | 117.9717 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6041 | CAMP EVERS 210694770 | 83622106 | CAMP EVERS 2106 | 2.3658 | 55 | 0.0059058 | 0.32482 | 2160 | 21805.0733 | 117.6469 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1981 | COTATI 1105328 | 42271105 | COTATI 1105 | 1.5009 | 173 | 0.0058817 | 1.0175 | 2161 | 21806.5742 | 116.6294 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
519 | POINT ARENA 110147952 | 43381101 | POINT ARENA 1101 | 10.3901 | 88 | 0.0058506 | 0.51485 | 2162 | 21816.9643 | 116.1145 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2535 | COTATI 1102825 | 42271102 | COTATI 1102 | 0.46579 | 26 | 0.0058122 | 0.15112 | 2163 | 21817.4301 | 115.9634 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
698 | RESERVATION ROAD 11013026 | 182731101 | RESERVATION ROAD 1101 | 21.8777 | 238 | 0.0057671 | 1.3726 | 2164 | 21839.3078 | 114.5908 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4296 | MORGAN HILL 2105XR494 | 83242105 | MORGAN HILL 2105 | 0.45836 | 98 | 0.0057504 | 0.56354 | 2165 | 21839.7662 | 114.0273 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
875 | FULTON 110777670 | 42561107 | FULTON 1107 | 6.7586 | 98 | 0.0057454 | 0.56305 | 2166 | 21846.5248 | 113.4642 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2839 | CAMP EVERS 210510294 | 83622105 | CAMP EVERS 2105 | 8.3915 | 95 | 0.0057046 | 0.54194 | 2167 | 21854.9163 | 112.9223 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4923 | GEYSERVILLE 1101480 | 42891101 | GEYSERVILLE 1101 | 1.5553 | 161 | 0.0057021 | 0.91803 | 2168 | 21856.4716 | 112.0043 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5117 | WOODSIDE 11018912 | 24251101 | WOODSIDE 1101 | 3.8961 | 52 | 0.0056974 | 0.29627 | 2169 | 21860.3677 | 111.708 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6008 | GEYSERVILLE 1101482 | 42891101 | GEYSERVILLE 1101 | 0.36983 | 38 | 0.0056711 | 0.2155 | 2170 | 21860.7375 | 111.4925 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3612 | BIG BASIN 110212992 | 82841102 | BIG BASIN 1102 | 14.242 | 160 | 0.0056575 | 0.90521 | 2171 | 21874.9796 | 110.5873 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
151 | SUMMIT 1102CB | 152591102 | SUMMIT 1102 | 1.0531 | 22 | 0.0056462 | 0.12422 | 2172 | 21876.0327 | 110.4631 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
585 | LUCERNE 110647198 | 43351106 | LUCERNE 1106 | 3.0699 | 70 | 0.0056207 | 0.39345 | 2173 | 21879.1026 | 110.0696 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7910 | SILVERADO 2105167360 | 43432105 | SILVERADO 2105 | 9.5796 | 70 | 0.0056116 | 0.39281 | 2174 | 21888.6822 | 109.6768 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1304 | CURTIS 17028000 | 163351702 | CURTIS 1702 | 14.3291 | 174 | 0.0056032 | 0.97497 | 2175 | 21903.0112 | 108.7018 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
417 | RALSTON 1101CB | 24141101 | RALSTON 1101 | 0.37713 | 37 | 0.0055946 | 0.207 | 2176 | 21903.3884 | 108.4948 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1975 | RALSTON 11022028 | 24141102 | RALSTON 1102 | 2.0968 | 38 | 0.0055851 | 0.21223 | 2177 | 21905.4852 | 108.2826 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6769 | ATASCADERO 1101A50 | 182541101 | ATASCADERO 1101 | 19.3404 | 269 | 0.0055802 | 1.5011 | 2178 | 21924.8256 | 106.7815 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2377 | GUALALA 11121294 | 42841112 | GUALALA 1112 | 19.8593 | 234 | 0.0055387 | 1.2961 | 2179 | 21944.6849 | 105.4855 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5858 | FAIRVIEW 2207P150 | 13432207 | FAIRVIEW 2207 | 2.2703 | 18 | 0.0055206 | 0.09937 | 2180 | 21946.9552 | 105.3861 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2861 | PIT NO 5 11011660 | 101321101 | PIT NO 5 1101 | 4.8823 | 43 | 0.0055185 | 0.23729 | 2181 | 21951.8375 | 105.1488 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4568 | RINCON 1101CB | 43321101 | RINCON 1101 | 1.6038 | 68 | 0.0054995 | 0.37397 | 2182 | 21953.4413 | 104.7748 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8511 | SAN ARDO 1101610148 | 182191101 | SAN ARDO 1101 | 1.9606 | 58 | 0.0054812 | 0.31791 | 2183 | 21955.4019 | 104.4569 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4730 | HARTLEY 110194178 | 43211101 | HARTLEY 1101 | 2.1488 | 57 | 0.0054615 | 0.3113 | 2184 | 21957.5507 | 104.1456 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1445 | BIG BASIN 1102CB | 82841102 | BIG BASIN 1102 | 6.1923 | 59 | 0.0054141 | 0.31943 | 2185 | 21963.743 | 103.8262 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6388 | HALF MOON BAY 11036012 | 24101103 | HALF MOON BAY 1103 | 6.6683 | 79 | 0.0054078 | 0.42722 | 2186 | 21970.4113 | 103.399 | 103.399 | #N/A | TRUE | 0.95 | TRUE | TRUE
629 | LAURELES 11112020 | 182371111 | LAURELES 1111 | 34.3538 | 281 | 0.005376 | 1.5107 | 2187 | 22004.7651 | 101.8883 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3079 | OCEANO 1102V50 | 182601102 | OCEANO 1102 | 7.1582 | 107 | 0.005367 | 0.57427 | 2188 | 22011.9233 | 101.3141 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
342 | WOODACRE 1101404 | 43021101 | WOODACRE 1101 | 12.4146 | 152 | 0.0053668 | 0.81576 | 2189 | 22024.3378 | 100.4983 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4506 | TIDEWATER 210657926 | 14652106 | TIDEWATER 2106 | 0.12479 | 97 | 0.0053561 | 0.51954 | 2190 | 22024.4626 | 99.9788 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6794 | CAMP EVERS 21055188 | 83622105 | CAMP EVERS 2105 | 2.0389 | 19 | 0.0053482 | 0.10162 | 2191 | 22026.5016 | 99.8771 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4962 | MONTE RIO 1113652 | 42811113 | MONTE RIO 1113 | 1.6208 | 25 | 0.0053427 | 0.13357 | 2192 | 22028.1224 | 99.7436 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5950 | COTATI 1102260 | 42271102 | COTATI 1102 | 2.6831 | 68 | 0.0053405 | 0.36316 | 2193 | 22030.8055 | 99.3804 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2816 | HICKS 2101574315 | 83432101 | HICKS 2101 | 7.399 | 78 | 0.005318 | 0.4148 | 2194 | 22038.2045 | 98.9656 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4882 | NARROWS 210276952 | 153132102 | NARROWS 2102 | 2.2675 | 161 | 0.0052383 | 0.84337 | 2195 | 22040.472 | 98.1222 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8374 | SAN JOAQUIN #3 1103501771 | 252531103 | SAN JOAQUIN #3 1103 | 4.9047 | 54 | 0.0052248 | 0.28214 | 2196 | 22045.3767 | 97.8401 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4446 | OTTER 1101440 | 182941101 | OTTER 1101 | 8.3237 | 107 | 0.0051543 | 0.5515 | 2197 | 22053.7004 | 97.2886 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1813 | PUEBLO 210375612 | 43292103 | PUEBLO 2103 | 0 | 114 | 0.0051135 | 0.58294 | 2198 | 22053.7004 | 96.7057 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3962 | POINT MORETTI 110112122 | 82931101 | POINT MORETTI 1101 | 6.5695 | 63 | 0.0051004 | 0.32133 | 2199 | 22060.2699 | 96.3843 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6972 | BRUNSWICK 1102940 | 152481102 | BRUNSWICK 1102 | 1.1878 | 46 | 0.005067 | 0.23308 | 2200 | 22061.4577 | 96.1513 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2994 | SHADY GLEN 110132726 | 152431101 | SHADY GLEN 1101 | 12.17 | 146 | 0.00506 | 0.73876 | 2201 | 22073.6277 | 95.4125 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5931 | EAST QUINCY 11012452 | 102551101 | EAST QUINCY 1101 | 0.14202 | 87 | 0.0050248 | 0.43716 | 2202 | 22073.7697 | 94.9753 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1799 | MORGAN HILL 2105XR578 | 83242105 | MORGAN HILL 2105 | 0.16225 | 12 | 0.0050174 | 0.060209 | 2203 | 22073.932 | 94.9151 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5416 | ANNAPOLIS 1101528344 | 42861101 | ANNAPOLIS 1101 | 26.9559 | 171 | 0.0049999 | 0.85498 | 2204 | 22100.8879 | 94.0601 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7537 | LOS OSITOS 2102148504 | 182082102 | LOS OSITOS 2102 | 0.17139 | 14 | 0.0049963 | 0.069948 | 2205 | 22101.0593 | 93.9902 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
235 | KONOCTI 11022293 | 43311102 | KONOCTI 1102 | 1.753 | 21 | 0.0049653 | 0.10427 | 2206 | 22102.8123 | 93.8859 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3072 | ANTLER 1101CB | 103271101 | ANTLER 1101 | 1.6 | 18 | 0.0049349 | 0.088829 | 2207 | 22104.4123 | 93.7971 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8410 | CAMP EVERS 210611533 | 83622106 | CAMP EVERS 2106 | 2.6412 | 28 | 0.0048855 | 0.13679 | 2208 | 22107.0535 | 93.6603 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3050 | AUBERRY 1101R324 | 254151101 | AUBERRY 1101 | 10.7137 | 119 | 0.0048731 | 0.5799 | 2209 | 22117.7672 | 93.0804 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9906 | POINT MORETTI 110183716 | 82931101 | POINT MORETTI 1101 | 2.503 | 22 | 0.0048588 | 0.10689 | 2210 | 22120.2703 | 92.9735 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5631 | PARADISE 1105878870 | 102831105 | PARADISE 1105 | 2.5217 | 29 | 0.0048412 | 0.1404 | 2211 | 22122.792 | 92.8331 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1901 | MOUNTAIN QUARRIES 21011184 | 152282101 | MOUNTAIN QUARRIES 2101 | 11.6971 | 136 | 0.0048403 | 0.65828 | 2212 | 22134.4891 | 92.1748 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4871 | BRUNSWICK 11052130 | 152481105 | BRUNSWICK 1105 | 14.4069 | 163 | 0.0048209 | 0.78581 | 2213 | 22148.896 | 91.389 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10520 | CASTRO VALLEY 1110MR273 | 14091110 | CASTRO VALLEY 1110 | 0.72381 | 13 | 0.0047919 | 0.062294 | 2214 | 22149.6198 | 91.3267 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9367 | REDBUD 110244119 | 43191102 | REDBUD 1102 | 0.31866 | 35 | 0.0047623 | 0.16668 | 2215 | 22149.9385 | 91.1601 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1147 | STAFFORD 11011082 | 43201101 | STAFFORD 1101 | 1.5607 | 36 | 0.0047619 | 0.17143 | 2216 | 22151.4992 | 90.9886 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2516 | MIWUK 17028130 | 163661702 | MIWUK 1702 | 9.9199 | 123 | 0.0047602 | 0.5855 | 2217 | 22161.4191 | 90.4031 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2340 | JESSUP 1102CB | 103441102 | JESSUP 1102 | 0.099243 | 47 | 0.0047601 | 0.22372 | 2218 | 22161.5184 | 90.1794 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10932 | CALPELLA 1102127462 | 43411102 | CALPELLA 1102 | 0.11763 | 2 | 0.0047158 | 0.0094316 | 2219 | 22161.636 | 90.17 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9177 | MORAGA 1105829530 | 13801105 | MORAGA 1105 | 1.6704 | 32 | 0.0047024 | 0.15048 | 2220 | 22163.3064 | 90.0195 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1591 | SAN JOAQUIN #3 1101673480 | 252531101 | SAN JOAQUIN #3 1101 | 12.7333 | 88 | 0.0046984 | 0.41346 | 2221 | 22176.0397 | 89.606 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7450 | WILLOW CREEK 1103CB | 192171103 | WILLOW CREEK 1103 | 3.92 | 54 | 0.0046671 | 0.25202 | 2222 | 22179.9596 | 89.354 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3048 | LAURELES 1111432 | 182371111 | LAURELES 1111 | 49.3307 | 320 | 0.0046501 | 1.488 | 2223 | 22229.2903 | 87.866 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9657 | PIT NO 5 1101CB | 101321101 | PIT NO 5 1101 | 0.72234 | 10 | 0.0046279 | 0.046279 | 2224 | 22230.0127 | 87.8197 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2107 | MIRABEL 110238514 | 42091102 | MIRABEL 1102 | 10.7254 | 102 | 0.0046099 | 0.47021 | 2225 | 22240.7381 | 87.3495 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4382 | WOODSIDE 11011922 | 24251101 | WOODSIDE 1101 | 4.594 | 70 | 0.004588 | 0.32116 | 2226 | 22245.3321 | 87.0283 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4539 | LOS GATOS 110760118 | 82021107 | LOS GATOS 1107 | 27.9074 | 323 | 0.0045775 | 1.4785 | 2227 | 22273.2395 | 85.5498 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8332 | VINEYARD 2108MR172 | 14502108 | VINEYARD 2108 | 0.5325 | 26 | 0.0045679 | 0.11876 | 2228 | 22273.772 | 85.431 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4690 | CORRAL 1103681991 | 162991103 | CORRAL 1103 | 1.3748 | 50 | 0.0045171 | 0.22586 | 2229 | 22275.1468 | 85.2052 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10188 | BOLINAS 11011232 | 42261101 | BOLINAS 1101 | 2.2606 | 22 | 0.0045024 | 0.099054 | 2230 | 22277.4074 | 85.1061 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4590 | REDBUD 11021212 | 43191102 | REDBUD 1102 | 0 | 62 | 0.0044984 | 0.2789 | 2231 | 22277.4074 | 84.8272 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6700 | TIVY VALLEY 1107CB | 252941107 | TIVY VALLEY 1107 | 0.18027 | 155 | 0.0044835 | 0.69495 | 2232 | 22277.5876 | 84.1323 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7824 | CAYUCOS 1102317156 | 182551102 | CAYUCOS 1102 | 2.3719 | 67 | 0.0044039 | 0.29506 | 2233 | 22279.9595 | 83.8372 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9117 | WEST POINT 11021535 | 163201102 | WEST POINT 1102 | 3.0662 | 30 | 0.0043786 | 0.13136 | 2234 | 22283.0257 | 83.7058 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1000 | MORGAN HILL 2111CB | 83242111 | MORGAN HILL 2111 | 0.2194 | 38 | 0.0043636 | 0.16582 | 2235 | 22283.2451 | 83.54 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9339 | LAKEWOOD 2109432198 FM | 13532109 | LAKEWOOD 2109 | 0.56371 | 31 | 0.004363 | 0.13525 | 2236 | 22283.8088 | 83.4048 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
420 | ARCATA 11225384 | 192021122 | ARCATA 1122 | 15.5688 | 202 | 0.0043604 | 0.88081 | 2237 | 22299.3777 | 82.524 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
268 | MIRABEL 1102332 | 42091102 | MIRABEL 1102 | 5.7022 | 67 | 0.0043573 | 0.29194 | 2238 | 22305.0799 | 82.232 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6281 | MONTE RIO 11131989 | 42811113 | MONTE RIO 1113 | 0.74282 | 9 | 0.0043487 | 0.039138 | 2239 | 22305.8227 | 82.1929 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
11081 | OAKHURST 110310723 | 254421103 | OAKHURST 1103 | 0.0039412 | 1 | 0.0043094 | 0.0043094 | 2240 | 22305.8266 | 82.1886 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8151 | SILVERADO 2105309298 | 43432105 | SILVERADO 2105 | 1.0992 | 23 | 0.0043094 | 0.099116 | 2241 | 22306.9259 | 82.0895 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4858 | GUALALA 111223444 | 42841112 | GUALALA 1112 | 14.5312 | 135 | 0.0042666 | 0.57599 | 2242 | 22321.457 | 81.5135 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2658 | CAMP EVERS 210660124 | 83622106 | CAMP EVERS 2106 | 22.4613 | 267 | 0.0042657 | 1.1389 | 2243 | 22343.9183 | 80.3745 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7144 | BELLEVUE 1102392 | 43181102 | BELLEVUE 1102 | 0.25165 | 68 | 0.0042431 | 0.28853 | 2244 | 22344.17 | 80.086 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5164 | MORAGA 1104N532R | 13801104 | MORAGA 1104 | 3.6935 | 65 | 0.004228 | 0.27482 | 2245 | 22347.8635 | 79.8112 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9096 | BIG BASIN 11022253 | 82841102 | BIG BASIN 1102 | 1.4514 | 12 | 0.0041981 | 0.050377 | 2246 | 22349.3149 | 79.7608 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4580 | WEST POINT 11021341 | 163201102 | WEST POINT 1102 | 9.8988 | 87 | 0.0041901 | 0.36454 | 2247 | 22359.2137 | 79.3962 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2630 | MC ARTHUR 110153120 | 103491101 | MC ARTHUR 1101 | 0.10763 | 92 | 0.004183 | 0.38483 | 2248 | 22359.3213 | 79.0114 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9114 | LAS GALLINAS A 1105CB | 42991105 | LAS GALLINAS A 1105 | 0.44146 | 26 | 0.0041416 | 0.10768 | 2249 | 22359.7628 | 78.9037 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2500 | EL DORADO PH 2101CB | 152762101 | EL DORADO PH 2101 | 7.4577 | 74 | 0.0041406 | 0.3064 | 2250 | 22367.2205 | 78.5973 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2083 | ALTO 11201214 | 42031120 | ALTO 1120 | 3.4493 | 45 | 0.004132 | 0.18594 | 2251 | 22370.6698 | 78.4114 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1240 | EL DORADO PH 210126000 | 152762101 | EL DORADO PH 2101 | 34.3764 | 339 | 0.0041222 | 1.3974 | 2252 | 22405.0461 | 77.014 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2830 | MENLO 11029110 | 24131102 | MENLO 1102 | 0.92693 | 138 | 0.0040502 | 0.55893 | 2253 | 22405.9731 | 76.455 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8665 | BRUNSWICK 111094368 | 152481110 | BRUNSWICK 1110 | 0.37065 | 9 | 0.0040353 | 0.036317 | 2254 | 22406.3437 | 76.4187 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2181 | MERCED FALLS 110222774 | 252811102 | MERCED FALLS 1102 | 1.0094 | 27 | 0.0040151 | 0.10841 | 2255 | 22407.3531 | 76.3103 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2725 | BIG BASIN 110212124 | 82841102 | BIG BASIN 1102 | 4.4856 | 59 | 0.0040119 | 0.2367 | 2256 | 22411.8387 | 76.0736 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1448 | PARADISE 1103CB | 102831103 | PARADISE 1103 | 1.3783 | 61 | 0.0039747 | 0.24245 | 2257 | 22413.2169 | 75.8311 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3467 | WEIMAR 11012740 | 152491101 | WEIMAR 1101 | 19.2287 | 235 | 0.003969 | 0.93271 | 2258 | 22432.4457 | 74.8984 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
497 | AUBURN 1101173014 | 152161101 | AUBURN 1101 | 3.2881 | 43 | 0.0039357 | 0.16924 | 2259 | 22435.7338 | 74.7292 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7194 | WEST POINT 1101L373 | 163201101 | WEST POINT 1101 | 7.3956 | 93 | 0.0039044 | 0.36311 | 2260 | 22443.1294 | 74.3661 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6474 | STAFFORD 11021048 | 43201102 | STAFFORD 1102 | 5.2734 | 72 | 0.0039018 | 0.28093 | 2261 | 22448.4027 | 74.0851 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4378 | RESERVATION ROAD 110222136 | 182731102 | RESERVATION ROAD 1102 | 1.7669 | 59 | 0.0038829 | 0.22909 | 2262 | 22450.1697 | 73.856 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7747 | ANITA 1106552724 | 102841106 | ANITA 1106 | 1.4691 | 77 | 0.0038689 | 0.29791 | 2263 | 22451.6388 | 73.5581 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6189 | PLACER 1101106534 | 152461101 | PLACER 1101 | 1.2115 | 38 | 0.0038425 | 0.14601 | 2264 | 22452.8503 | 73.4121 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8134 | MORAGA 110518396 | 13801105 | MORAGA 1105 | 0.18228 | 16 | 0.0038298 | 0.061277 | 2265 | 22453.0325 | 73.3509 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2828 | PANORAMA 11019092 | 103461101 | PANORAMA 1101 | 0.15856 | 113 | 0.0038237 | 0.43208 | 2266 | 22453.1911 | 72.9188 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1451 | MIWUK 1701953336 | 163661701 | MIWUK 1701 | 11.8581 | 132 | 0.0038168 | 0.50381 | 2267 | 22465.0492 | 72.415 | 72.415 | #N/A | TRUE | 6.04 | TRUE | TRUE
8189 | CAMP EVERS 210660120 | 83622106 | CAMP EVERS 2106 | 4.3466 | 42 | 0.0038109 | 0.16006 | 2268 | 22469.3957 | 72.2549 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3086 | PANOCHE 11034016 | 253671103 | PANOCHE 1103 | 2.3473 | 59 | 0.0038045 | 0.22447 | 2269 | 22471.7431 | 72.0304 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3744 | FORESTHILL 110150486 | 152181101 | FORESTHILL 1101 | 11.6759 | 163 | 0.0037623 | 0.61325 | 2270 | 22483.419 | 71.4172 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1371 | PINE GROVE 11021222 | 163751102 | PINE GROVE 1102 | 17.2598 | 218 | 0.0037571 | 0.81905 | 2271 | 22500.6788 | 70.5981 | 70.5981 | #N/A | TRUE | 4.3156 | TRUE | TRUE
2904 | MONTE RIO 111153477 | 42811111 | MONTE RIO 1111 | 2.0483 | 21 | 0.0037529 | 0.078812 | 2272 | 22502.7271 | 70.5193 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4467 | RINCON 1102CB | 43321102 | RINCON 1102 | 2.9661 | 49 | 0.0037209 | 0.18233 | 2273 | 22505.6933 | 70.337 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4949 | BRENTWOOD 210598606 | 14592105 | BRENTWOOD 2105 | 0.086065 | 88 | 0.0037138 | 0.32681 | 2274 | 22505.7793 | 70.0102 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8946 | MIRABEL 110213597 | 42091102 | MIRABEL 1102 | 0.46726 | 6 | 0.0037122 | 0.022273 | 2275 | 22506.2466 | 69.9879 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3893 | FAIRVIEW 2207P304 | 13432207 | FAIRVIEW 2207 | 5.2458 | 47 | 0.0037077 | 0.17426 | 2276 | 22511.4924 | 69.8137 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7178 | BURNEY 11019042 | 103311101 | BURNEY 1101 | 3.1577 | 31 | 0.0036996 | 0.11469 | 2277 | 22514.6501 | 69.699 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8790 | MONTICELLO 110152910 | 43051101 | MONTICELLO 1101 | 2.182 | 41 | 0.0036877 | 0.1512 | 2278 | 22516.8321 | 69.5478 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8586 | WEST POINT 1102L3733 | 163201102 | WEST POINT 1102 | 1.7527 | 22 | 0.0036798 | 0.080956 | 2279 | 22518.5848 | 69.4668 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2143 | VOLTA 11029742 | 102541102 | VOLTA 1102 | 9.1272 | 120 | 0.0036718 | 0.44061 | 2280 | 22527.712 | 69.0262 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8195 | SAUSALITO 11021268 | 42491102 | SAUSALITO 1102 | 4.9334 | 46 | 0.0036642 | 0.16855 | 2281 | 22532.6454 | 68.8577 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
200 | PETALUMA C 1109270 | 42631109 | PETALUMA C 1109 | 2.1115 | 101 | 0.0036568 | 0.36934 | 2282 | 22534.7569 | 68.4883 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9326 | COARSEGOLD 2102383092 | 254432102 | COARSEGOLD 2102 | 0.3811 | 5 | 0.0036345 | 0.018173 | 2283 | 22535.138 | 68.4701 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10306 | SOLEDAD 1114413916 | 182051114 | SOLEDAD 1114 | 1.4145 | 24 | 0.0036248 | 0.086994 | 2284 | 22536.5525 | 68.3832 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6836 | LLAGAS 2106338878 | 83182106 | LLAGAS 2106 | 2.051 | 23 | 0.0036203 | 0.083266 | 2285 | 22538.6034 | 68.2999 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
685 | MONTE RIO 1113524 | 42811113 | MONTE RIO 1113 | 6.2639 | 76 | 0.0036171 | 0.2749 | 2286 | 22544.8674 | 68.025 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3555 | DUNBAR 1103CB | 43071103 | DUNBAR 1103 | 2.6944 | 149 | 0.0036086 | 0.53768 | 2287 | 22547.5617 | 67.4873 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6157 | IGNACIO 11041290 | 42481104 | IGNACIO 1104 | 4.0937 | 126 | 0.0035797 | 0.45104 | 2288 | 22551.6554 | 67.0363 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1177 | ORO FINO 1101CB | 103031101 | ORO FINO 1101 | 22.3304 | 271 | 0.0035789 | 0.96987 | 2289 | 22573.9859 | 66.0664 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3178 | PENNGROVE 1101461338 | 43471101 | PENNGROVE 1101 | 1.7854 | 24 | 0.0035591 | 0.085418 | 2290 | 22575.7713 | 65.981 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3360 | GRASS VALLEY 1101CB | 152031101 | GRASS VALLEY 1101 | 0.87991 | 32 | 0.0035509 | 0.11363 | 2291 | 22576.6512 | 65.8673 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10815 | HICKS 2101949522 | 83432101 | HICKS 2101 | 0.44016 | 2 | 0.0035464 | 0.0070929 | 2292 | 22577.0914 | 65.8603 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6548 | WEST POINT 110113444 | 163201101 | WEST POINT 1101 | 17.021 | 221 | 0.0035258 | 0.77919 | 2293 | 22594.1124 | 65.0811 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2950 | HICKS 2101XR162 | 83432101 | HICKS 2101 | 0.61478 | 122 | 0.0035232 | 0.42983 | 2294 | 22594.7272 | 64.6512 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9560 | VINEYARD 2107246084 | 14502107 | VINEYARD 2107 | 0.23943 | 7 | 0.0035033 | 0.024523 | 2295 | 22594.9666 | 64.6267 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3073 | CAMP EVERS 210510728 | 83622105 | CAMP EVERS 2105 | 10.4737 | 134 | 0.0034865 | 0.46719 | 2296 | 22605.4403 | 64.1595 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7203 | BRUNSWICK 110663124 | 152481106 | BRUNSWICK 1106 | 5.893 | 65 | 0.0034764 | 0.22596 | 2297 | 22611.3333 | 63.9336 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7594 | SHINGLE SPRINGS 2108CB | 153652108 | SHINGLE SPRINGS 2108 | 1.4768 | 18 | 0.0034725 | 0.062504 | 2298 | 22612.81 | 63.871 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
180 | HIGGINS 11041374 | 152691104 | HIGGINS 1104 | 7.7503 | 117 | 0.0034694 | 0.40592 | 2299 | 22620.5603 | 63.4651 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8764 | TRES PINOS 1111203126 | 183221111 | TRES PINOS 1111 | 0.066788 | 58 | 0.0034419 | 0.19963 | 2300 | 22620.6271 | 63.2655 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6133 | SALT SPRINGS 210237300 | 163692102 | SALT SPRINGS 2102 | 6.9662 | 41 | 0.0034152 | 0.14002 | 2301 | 22627.5932 | 63.1255 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8353 | VOLTA 110254932 | 102541102 | VOLTA 1102 | 4.377 | 46 | 0.0034144 | 0.15706 | 2302 | 22631.9703 | 62.9684 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1504 | HUMBOLDT BAY 1102741980 | 192341102 | HUMBOLDT BAY 1102 | 5.7434 | 81 | 0.0034064 | 0.27592 | 2303 | 22637.7137 | 62.6925 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
341 | COTATI 1102464 | 42271102 | COTATI 1102 | 2.1402 | 103 | 0.0034005 | 0.35026 | 2304 | 22639.8539 | 62.3422 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1877 | FORT BRAGG A 110231304 | 42761102 | FORT BRAGG A 1102 | 21.6783 | 119 | 0.0033857 | 0.40289 | 2305 | 22661.5322 | 61.9394 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9731 | FITCH MOUNTAIN 1111792628 | 42751111 | FITCH MOUNTAIN 1111 | 0.22723 | 13 | 0.0033779 | 0.043913 | 2306 | 22661.7594 | 61.8954 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10338 | FRANKLIN 1104P146 | 13921104 | FRANKLIN 1104 | 3.6318 | 36 | 0.0033674 | 0.12123 | 2307 | 22665.3912 | 61.7742 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
11025 | CALPINE 1144304 | 48011144 | CALPINE 1144 | 0.046368 | 2 | 0.0033555 | 0.006711 | 2308 | 22665.4376 | 61.7675 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7073 | RINCON 1101663641 | 43321101 | RINCON 1101 | 0.72937 | 13 | 0.0033545 | 0.043609 | 2309 | 22666.1669 | 61.7239 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
37 | CURTIS 17019230 | 163351701 | CURTIS 1701 | 2.5262 | 41 | 0.0033425 | 0.13704 | 2310 | 22668.6931 | 61.5868 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7129 | GANSNER 1101336664 | 103021101 | GANSNER 1101 | 0.72016 | 16 | 0.0033324 | 0.053319 | 2311 | 22669.4133 | 61.5335 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6003 | CALPELLA 1102477890 | 43411102 | CALPELLA 1102 | 1.0733 | 35 | 0.0033264 | 0.11642 | 2312 | 22670.4866 | 61.4171 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6936 | LAMONT 11024222 | 253911102 | LAMONT 1102 | 2.6385 | 87 | 0.0033258 | 0.28934 | 2313 | 22673.1251 | 61.1278 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1031 | VOLTA 110253130 | 102541102 | VOLTA 1102 | 13.8057 | 168 | 0.0033207 | 0.55788 | 2314 | 22686.9308 | 60.5699 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
729 | RADUM 1105806392 | 13151105 | RADUM 1105 | 3.3853 | 79 | 0.0033155 | 0.26192 | 2315 | 22690.3161 | 60.308 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6737 | POINT ARENA 1101476 | 43381101 | POINT ARENA 1101 | 2.9988 | 97 | 0.0032902 | 0.31915 | 2316 | 22693.3149 | 59.9888 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9971 | LOS OSITOS 2103258688 | 182082103 | LOS OSITOS 2103 | 1.0735 | 17 | 0.0032882 | 0.0559 | 2317 | 22694.3884 | 59.9329 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2467 | HARRIS 1109183860 | 192431109 | HARRIS 1109 | 4.9361 | 92 | 0.0032843 | 0.30215 | 2318 | 22699.3245 | 59.6308 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3741 | PINE GROVE 110152088 | 163751101 | PINE GROVE 1101 | 2.4775 | 28 | 0.0032783 | 0.091793 | 2319 | 22701.802 | 59.539 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8487 | PIT NO 3 21011482 | 103732101 | PIT NO 3 2101 | 12.0356 | 43 | 0.0032735 | 0.14076 | 2320 | 22713.8376 | 59.3982 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9213 | GREEN VALLEY 210197574 | 83192101 | GREEN VALLEY 2101 | 3.5697 | 60 | 0.0032547 | 0.19528 | 2321 | 22717.4072 | 59.2029 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6945 | CHOLAME 2102X06 | 182562102 | CHOLAME 2102 | 0.40519 | 40 | 0.0032533 | 0.13013 | 2322 | 22717.8124 | 59.0728 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1559 | PAUL SWEET 21065178 | 83252106 | PAUL SWEET 2106 | 7.1789 | 84 | 0.0032408 | 0.27223 | 2323 | 22724.9914 | 58.8006 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8048 | DEL MONTE 21042762 | 182222104 | DEL MONTE 2104 | 9.3599 | 138 | 0.0032245 | 0.44498 | 2324 | 22734.3513 | 58.3556 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
394 | WOODSIDE 11049032 | 24251104 | WOODSIDE 1104 | 2.1459 | 72 | 0.0032245 | 0.23216 | 2325 | 22736.4972 | 58.1234 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3140 | BAYWOOD 1101CB | 182801101 | BAYWOOD 1101 | 4.6156 | 214 | 0.003207 | 0.6863 | 2326 | 22741.1128 | 57.4371 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
197 | BRUNSWICK 1105733408 | 152481105 | BRUNSWICK 1105 | 3.447 | 45 | 0.0032065 | 0.14429 | 2327 | 22744.5598 | 57.2928 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1600 | RINCON 1104786782 | 43321104 | RINCON 1104 | 2.2059 | 46 | 0.0032053 | 0.14745 | 2328 | 22746.7657 | 57.1454 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7931 | PIT NO 5 11011658 | 101321101 | PIT NO 5 1101 | 4.5409 | 25 | 0.0031839 | 0.079597 | 2329 | 22751.3066 | 57.0658 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4023 | DUNLAP 11037080 | 254061103 | DUNLAP 1103 | 10.5819 | 67 | 0.0031698 | 0.21238 | 2330 | 22761.8885 | 56.8534 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7290 | ARCATA 1121716954 | 192021121 | ARCATA 1121 | 6.9085 | 97 | 0.0031691 | 0.30741 | 2331 | 22768.7969 | 56.546 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8705 | CARLOTTA 112144150 | 192291121 | CARLOTTA 1121 | 3.5717 | 13 | 0.0031685 | 0.04119 | 2332 | 22772.3686 | 56.5048 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5063 | WOODSIDE 11043583 | 24251104 | WOODSIDE 1104 | 2.8372 | 38 | 0.0031615 | 0.12014 | 2333 | 22775.2057 | 56.3847 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8125 | PINE GROVE 1101CB | 163751101 | PINE GROVE 1101 | 4.3027 | 57 | 0.0031502 | 0.17956 | 2334 | 22779.5084 | 56.2051 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6730 | CAMP EVERS 210637210 | 83622106 | CAMP EVERS 2106 | 6.0576 | 65 | 0.0031442 | 0.20437 | 2335 | 22785.566 | 56.0007 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
82 | SNEATH LANE 1107CB | 22721107 | SNEATH LANE 1107 | 1.0038 | 45 | 0.003121 | 0.14045 | 2336 | 22786.5698 | 55.8603 | 55.8603 | #N/A | TRUE | 0.26 | FALSE | TRUE
1487 | STAFFORD 11021258 | 43201102 | STAFFORD 1102 | 0.31195 | 65 | 0.0031184 | 0.2027 | 2337 | 22786.8817 | 55.6576 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
201 | RESERVATION ROAD 1101CB | 182731101 | RESERVATION ROAD 1101 | 5.1043 | 106 | 0.0031059 | 0.32923 | 2338 | 22791.9861 | 55.3284 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9832 | WILLOW CREEK 1101CB | 192171101 | WILLOW CREEK 1101 | 0.28641 | 6 | 0.0031037 | 0.018622 | 2339 | 22792.2725 | 55.3097 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
22 | PARADISE 1104457900 | 102831104 | PARADISE 1104 | 12.0452 | 208 | 0.0030985 | 0.64448 | 2340 | 22804.3177 | 54.6653 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7703 | SILVERADO 21051306 | 43432105 | SILVERADO 2105 | 0.24462 | 55 | 0.0030939 | 0.17016 | 2341 | 22804.5623 | 54.4951 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8415 | BIG MEADOWS 21012476 | 102812101 | BIG MEADOWS 2101 | 8.1111 | 75 | 0.0030704 | 0.23028 | 2342 | 22812.6734 | 54.2648 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2480 | REDBUD 1101CB | 43191101 | REDBUD 1101 | 3.3608 | 91 | 0.0030523 | 0.27776 | 2343 | 22816.0342 | 53.987 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10178 | MAPLE CREEK 1101555034 | 192101101 | MAPLE CREEK 1101 | 1.4947 | 8 | 0.0030461 | 0.024368 | 2344 | 22817.5289 | 53.9627 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1443 | MENLO 11028952 | 24131102 | MENLO 1102 | 6.6746 | 82 | 0.0030386 | 0.24916 | 2345 | 22824.2034 | 53.7135 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5316 | PAUL SWEET 210610424 | 83252106 | PAUL SWEET 2106 | 5.688 | 87 | 0.0030267 | 0.26332 | 2346 | 22829.8914 | 53.4502 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2267 | ELK 11011298 | 42981101 | ELK 1101 | 12.4112 | 119 | 0.0030233 | 0.35978 | 2347 | 22842.3026 | 53.0904 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6724 | CURTIS 17039210 | 163351703 | CURTIS 1703 | 22.4939 | 124 | 0.0030209 | 0.37459 | 2348 | 22864.7965 | 52.7158 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3063 | ELECTRA 1101L1697 | 162161101 | ELECTRA 1101 | 5.7698 | 70 | 0.0030208 | 0.21145 | 2349 | 22870.5662 | 52.5044 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8682 | CLARKSVILLE 210951744 | 153612109 | CLARKSVILLE 2109 | 1.3051 | 25 | 0.0030149 | 0.075372 | 2350 | 22871.8713 | 52.429 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6410 | SILVERADO 2105616 | 43432105 | SILVERADO 2105 | 0.4965 | 103 | 0.0030112 | 0.31016 | 2351 | 22872.3678 | 52.1188 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2231 | HICKS 2103LB50 | 83432103 | HICKS 2103 | 11.268 | 65 | 0.0029902 | 0.19436 | 2352 | 22883.6359 | 51.9245 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1742 | MIWUK 1701CB | 163661701 | MIWUK 1701 | 16.2494 | 187 | 0.0029901 | 0.55914 | 2353 | 22899.8853 | 51.3653 | 51.3653 | #N/A | TRUE | 10.9706 | TRUE | TRUE
4916 | SARATOGA 1107167792 | 83371107 | SARATOGA 1107 | 4.6865 | 48 | 0.0029842 | 0.14324 | 2354 | 22904.5718 | 51.2221 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
55 | CURTIS 170234426 | 163351702 | CURTIS 1702 | 4.718 | 81 | 0.0029697 | 0.24054 | 2355 | 22909.2898 | 50.9816 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4236 | LOS GATOS 1106LA64 | 82021106 | LOS GATOS 1106 | 12.6946 | 152 | 0.0029684 | 0.4512 | 2356 | 22921.9844 | 50.5304 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6476 | PAUL SWEET 21068091 | 83252106 | PAUL SWEET 2106 | 6.0152 | 69 | 0.0029648 | 0.20457 | 2357 | 22927.9996 | 50.3258 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7197 | BIG BASIN 110212758 | 82841102 | BIG BASIN 1102 | 5.982 | 70 | 0.002947 | 0.20629 | 2358 | 22933.9816 | 50.1195 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2069 | BIG BASIN 11025066 | 82841102 | BIG BASIN 1102 | 13.7481 | 121 | 0.0029066 | 0.35169 | 2359 | 22947.7297 | 49.7678 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8715 | OLEMA 1101602 | 42291101 | OLEMA 1101 | 16.1792 | 115 | 0.0028981 | 0.33328 | 2360 | 22963.9089 | 49.4345 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5548 | ANTLER 11011384 | 103271101 | ANTLER 1101 | 9.1423 | 106 | 0.0028857 | 0.30589 | 2361 | 22973.0512 | 49.1286 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2497 | ROB ROY 210410714 | 83692104 | ROB ROY 2104 | 14.1675 | 212 | 0.002884 | 0.61141 | 2362 | 22987.2187 | 48.5172 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2343 | OCEANO 1104CB | 182601104 | OCEANO 1104 | 4.5697 | 146 | 0.0028615 | 0.41777 | 2363 | 22991.7883 | 48.0995 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7790 | SANTA ROSA A 1111147198 | 42151111 | SANTA ROSA A 1111 | 1.3511 | 24 | 0.0028527 | 0.068464 | 2364 | 22993.1395 | 48.031 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5803 | BEN LOMOND 04015206 | 83040401 | BEN LOMOND 0401 | 7.16 | 78 | 0.0028387 | 0.22141 | 2365 | 23000.2994 | 47.8096 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6276 | MONTE RIO 1113202 | 42811113 | MONTE RIO 1113 | 5.2711 | 55 | 0.0028293 | 0.15561 | 2366 | 23005.5705 | 47.654 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6911 | DEL MONTE 21042624 | 182222104 | DEL MONTE 2104 | 18.5151 | 148 | 0.0028273 | 0.41844 | 2367 | 23024.0856 | 47.2355 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3771 | CURTIS 170510590 | 163351705 | CURTIS 1705 | 16.3818 | 199 | 0.0028226 | 0.56169 | 2368 | 23040.4674 | 46.6738 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2714 | MIWUK 1702CB | 163661702 | MIWUK 1702 | 9.055 | 110 | 0.0028161 | 0.30977 | 2369 | 23049.5224 | 46.3641 | 46.3641 | #N/A | TRUE | 2.4208 | TRUE | TRUE
3825 | SARATOGA 1105LC14 | 83371105 | SARATOGA 1105 | 9.869 | 137 | 0.0028157 | 0.38575 | 2370 | 23059.3914 | 45.9783 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5150 | HAMILTON BRANCH 11012046 | 102361101 | HAMILTON BRANCH 1101 | 9.1511 | 57 | 0.0028141 | 0.1604 | 2371 | 23068.5425 | 45.8179 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6397 | BRUNSWICK 110584480 | 152481105 | BRUNSWICK 1105 | 4.7332 | 50 | 0.0028064 | 0.14032 | 2372 | 23073.2758 | 45.6776 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7609 | SAN LUIS OBISPO 1107V58 | 182631107 | SAN LUIS OBISPO 1107 | 1.1426 | 25 | 0.0027879 | 0.069698 | 2373 | 23074.4184 | 45.6079 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10167 | HAMILTON BRANCH 11012436 | 102361101 | HAMILTON BRANCH 1101 | 5.3051 | 19 | 0.0027598 | 0.052436 | 2374 | 23079.7235 | 45.5555 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
289 | BIG BASIN 110169550 | 82841101 | BIG BASIN 1101 | 17.5407 | 188 | 0.0027545 | 0.51784 | 2375 | 23097.2642 | 45.0376 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3662 | SONOMA 1107294 | 42721107 | SONOMA 1107 | 0 | 66 | 0.002743 | 0.18104 | 2376 | 23097.2642 | 44.8566 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6355 | BIG RIVER 11017273 | 43081101 | BIG RIVER 1101 | 6.618 | 38 | 0.0027408 | 0.10415 | 2377 | 23103.8822 | 44.7524 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7672 | POINT ARENA 11012637 | 43381101 | POINT ARENA 1101 | 4.0402 | 28 | 0.0027385 | 0.076678 | 2378 | 23107.9223 | 44.6758 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1790 | CAMP EVERS 210510912 | 83622105 | CAMP EVERS 2105 | 4.8632 | 54 | 0.0027343 | 0.14765 | 2379 | 23112.7856 | 44.5281 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10750 | BOGARD 1101CB | 103301101 | BOGARD 1101 | 0.51616 | 7 | 0.0027213 | 0.019049 | 2380 | 23113.3017 | 44.5091 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6610 | GREEN VALLEY 210112824 | 83192101 | GREEN VALLEY 2101 | 0.87637 | 97 | 0.0027199 | 0.26383 | 2381 | 23114.1781 | 44.2452 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6375 | HOLLISTER 21054048 | 182492105 | HOLLISTER 2105 | 18.1541 | 157 | 0.0027194 | 0.42694 | 2382 | 23132.3322 | 43.8183 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
317 | PARADISE 11042206 | 102831104 | PARADISE 1104 | 4.1388 | 227 | 0.0027 | 0.61291 | 2383 | 23136.4709 | 43.2054 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6305 | WILLOW CREEK 110191926 | 192171101 | WILLOW CREEK 1101 | 6.438 | 48 | 0.0026935 | 0.12929 | 2384 | 23142.9089 | 43.0761 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5185 | SILVERADO 21023010 | 43432102 | SILVERADO 2102 | 0.35395 | 106 | 0.0026922 | 0.28537 | 2385 | 23143.2629 | 42.7907 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
122 | STANISLAUS 17021888 | 162821702 | STANISLAUS 1702 | 18.9186 | 231 | 0.0026855 | 0.62036 | 2386 | 23162.1815 | 42.1704 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7468 | ROB ROY 210410298 | 83692104 | ROB ROY 2104 | 10.9608 | 138 | 0.0026825 | 0.37018 | 2387 | 23173.1423 | 41.8002 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3981 | CAMP EVERS 210510214 | 83622105 | CAMP EVERS 2105 | 13.9276 | 149 | 0.0026769 | 0.39885 | 2388 | 23187.0699 | 41.4013 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4982 | WEST POINT 110136674 | 163201101 | WEST POINT 1101 | 9.4121 | 125 | 0.0026639 | 0.33299 | 2389 | 23196.4821 | 41.0683 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7345 | WILLOW CREEK 110129362 | 192171101 | WILLOW CREEK 1101 | 7.6889 | 74 | 0.0026559 | 0.19654 | 2390 | 23204.171 | 40.8718 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8996 | FORT ORD 210637286 | 182402106 | FORT ORD 2106 | 2.5798 | 25 | 0.0026543 | 0.066357 | 2391 | 23206.7508 | 40.8054 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8063 | COARSEGOLD 210210207 | 254432102 | COARSEGOLD 2102 | 3.5622 | 38 | 0.0026426 | 0.10042 | 2392 | 23210.313 | 40.705 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4536 | TASSAJARA 2108437582 | 14662108 | TASSAJARA 2108 | 0.72879 | 31 | 0.0026389 | 0.081807 | 2393 | 23211.0418 | 40.6232 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1013 | CASTRO VALLEY 1108MR337 | 14091108 | CASTRO VALLEY 1108 | 9.0923 | 193 | 0.0026206 | 0.50578 | 2394 | 23220.1341 | 40.1174 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1167 | BIG BASIN 110195690 | 82841101 | BIG BASIN 1101 | 3.8701 | 58 | 0.0026164 | 0.15175 | 2395 | 23224.0042 | 39.9657 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7588 | IGNACIO 1104450582 | 42481104 | IGNACIO 1104 | 2.9881 | 50 | 0.0026097 | 0.13049 | 2396 | 23226.9923 | 39.8352 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
976 | BRUNSWICK 1103CB | 152481103 | BRUNSWICK 1103 | 1.6787 | 82 | 0.0026094 | 0.21397 | 2397 | 23228.671 | 39.6212 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3119 | BIG BASIN 1101CB | 82841101 | BIG BASIN 1101 | 4.6531 | 45 | 0.0025849 | 0.11632 | 2398 | 23233.3241 | 39.5049 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8530 | MORRO BAY 1102CB | 183011102 | MORRO BAY 1102 | 4.5245 | 36 | 0.0025799 | 0.092875 | 2399 | 23237.8485 | 39.412 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1372 | TASSAJARA 2112CB | 14662112 | TASSAJARA 2112 | 0.17367 | 22 | 0.0025794 | 0.056746 | 2400 | 23238.0222 | 39.3553 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1496 | BRUNSWICK 1103173934 | 152481103 | BRUNSWICK 1103 | 10.9458 | 125 | 0.0025705 | 0.32131 | 2401 | 23248.968 | 39.034 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1818 | MORRO BAY 1101V66 | 183011101 | MORRO BAY 1101 | 3.6296 | 151 | 0.0025703 | 0.38811 | 2402 | 23252.5976 | 38.6459 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3089 | CAMBRIA 1101CB | 182771101 | CAMBRIA 1101 | 0.25849 | 45 | 0.0025606 | 0.11523 | 2403 | 23252.8561 | 38.5306 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3722 | BRUNSWICK 11032784 | 152481103 | BRUNSWICK 1103 | 14.6627 | 202 | 0.0025529 | 0.51568 | 2404 | 23267.5187 | 38.0149 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3654 | PENNGROVE 1101247511 | 43471101 | PENNGROVE 1101 | 1.2047 | 26 | 0.0025357 | 0.065929 | 2405 | 23268.7235 | 37.949 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2397 | MILPITAS 1109XR374 | 82831109 | MILPITAS 1109 | 0.47477 | 29 | 0.002531 | 0.073398 | 2406 | 23269.1982 | 37.8756 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1430 | ANTLER 11011520 | 103271101 | ANTLER 1101 | 8.972 | 69 | 0.002519 | 0.17381 | 2407 | 23278.1702 | 37.7018 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9020 | EAST QUINCY 1101424048 | 102551101 | EAST QUINCY 1101 | 0.66413 | 12 | 0.002517 | 0.030204 | 2408 | 23278.8344 | 37.6716 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5728 | HALF MOON BAY 1101CB | 24101101 | HALF MOON BAY 1101 | 1.5982 | 80 | 0.0025158 | 0.20127 | 2409 | 23280.4326 | 37.4703 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2399 | MONTE RIO 1113477 | 42811113 | MONTE RIO 1113 | 1.8313 | 25 | 0.002515 | 0.062875 | 2410 | 23282.2639 | 37.4075 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5291 | MIWUK 1702823548 | 163661702 | MIWUK 1702 | 19.7318 | 231 | 0.0025098 | 0.57976 | 2411 | 23301.9958 | 36.8277 | 36.8277 | #N/A | TRUE | 0.68519 | TRUE | TRUE
2843 | PLACERVILLE 111219742 | 153081112 | PLACERVILLE 1112 | 6.5567 | 92 | 0.0025093 | 0.23086 | 2412 | 23308.5525 | 36.5968 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7112 | BELLEVUE 2103646 | 43182103 | BELLEVUE 2103 | 8.4179 | 154 | 0.0025033 | 0.3855 | 2413 | 23316.9703 | 36.2113 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
637 | DUNBAR 1101160 | 43071101 | DUNBAR 1101 | 2.7777 | 77 | 0.0024952 | 0.19213 | 2414 | 23319.748 | 36.0192 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
551 | MC KEE 1103XR028 | 83531103 | MC KEE 1103 | 0.76232 | 134 | 0.0024946 | 0.33428 | 2415 | 23320.5103 | 35.6849 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4532 | RESERVATION ROAD 1102CB | 182731102 | RESERVATION ROAD 1102 | 7.8257 | 180 | 0.0024688 | 0.44438 | 2416 | 23328.336 | 35.2405 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2736 | ROSSMOOR 110845268 | 14161108 | ROSSMOOR 1108 | 2.735 | 112 | 0.0024458 | 0.27393 | 2417 | 23331.071 | 34.9666 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4245 | SONOMA 1104914376 | 42721104 | SONOMA 1104 | 0.53577 | 93 | 0.0024267 | 0.22569 | 2418 | 23331.6068 | 34.7409 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9993 | STELLING 1109478699 | 83481109 | STELLING 1109 | 0.8256 | 14 | 0.0024262 | 0.033967 | 2419 | 23332.4324 | 34.707 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1421 | ORO FINO 11012022 | 103031101 | ORO FINO 1101 | 16.0901 | 207 | 0.0024209 | 0.50113 | 2420 | 23348.5225 | 34.2058 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4226 | RIO DELL 1102772210 | 192251102 | RIO DELL 1102 | 0.82646 | 32 | 0.0023979 | 0.076733 | 2421 | 23349.3489 | 34.1291 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3489 | WEIMAR 1101CB | 152491101 | WEIMAR 1101 | 9.2589 | 116 | 0.0023893 | 0.27716 | 2422 | 23358.6078 | 33.8519 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9667 | NORTH TOWER 2101CB | 42042101 | NORTH TOWER 2101 | 1.3545 | 22 | 0.0023847 | 0.052462 | 2423 | 23359.9623 | 33.7995 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8228 | GONZALES 1104415382 | 182131104 | GONZALES 1104 | 0.060313 | 8 | 0.0023723 | 0.018978 | 2424 | 23360.0226 | 33.7805 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4259 | DIAMOND SPRINGS 110676088 | 152261106 | DIAMOND SPRINGS 1106 | 11.0106 | 124 | 0.0023715 | 0.29407 | 2425 | 23371.0332 | 33.4864 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9364 | MIWUK 170236888 | 163661702 | MIWUK 1702 | 0.60778 | 7 | 0.0023702 | 0.016592 | 2426 | 23371.641 | 33.4698 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5480 | PUEBLO 2102647842 | 43292102 | PUEBLO 2102 | 0.11668 | 6 | 0.0023697 | 0.014218 | 2427 | 23371.7576 | 33.4556 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1607 | MONTE RIO 11133970 | 42811113 | MONTE RIO 1113 | 7.3031 | 87 | 0.0023638 | 0.20565 | 2428 | 23379.0608 | 33.25 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4343 | BOLINAS 11011236 | 42261101 | BOLINAS 1101 | 3.6104 | 34 | 0.0023633 | 0.080354 | 2429 | 23382.6712 | 33.1696 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4341 | PLACERVILLE 210623190 | 153082106 | PLACERVILLE 2106 | 3.6786 | 45 | 0.0023536 | 0.10591 | 2430 | 23386.3497 | 33.0637 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6831 | INDIAN FLAT 110410270 | 252691104 | INDIAN FLAT 1104 | 3.8035 | 39 | 0.002349 | 0.091612 | 2431 | 23390.1533 | 32.9721 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10358 | KONOCTI 11024421 | 43311102 | KONOCTI 1102 | 0.3638 | 5 | 0.0023217 | 0.011609 | 2432 | 23390.5171 | 32.9605 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
822 | PERRY 1101V74 | 183071101 | PERRY 1101 | 4.2891 | 61 | 0.0023119 | 0.14103 | 2433 | 23394.8061 | 32.8195 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1876 | HATTON 1102CB | 182291102 | HATTON 1102 | 1.9684 | 66 | 0.0022934 | 0.15136 | 2434 | 23396.7745 | 32.6681 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5363 | BIG BASIN 110110720 | 82841101 | BIG BASIN 1101 | 4.71 | 44 | 0.002283 | 0.10045 | 2435 | 23401.4845 | 32.5676 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3635 | PERRY 1101V88 | 183071101 | PERRY 1101 | 1.0768 | 48 | 0.002278 | 0.10934 | 2436 | 23402.5613 | 32.4583 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4348 | SANTA ROSA A 110432180 | 42151104 | SANTA ROSA A 1104 | 2.4675 | 36 | 0.0022763 | 0.081948 | 2437 | 23405.0288 | 32.3763 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9525 | BIG BASIN 11028403 | 82841102 | BIG BASIN 1102 | 4.8898 | 42 | 0.0022738 | 0.095499 | 2438 | 23409.9186 | 32.2808 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7227 | SAN RAFAEL 11071415 | 42011107 | SAN RAFAEL 1107 | 0.79554 | 14 | 0.0022706 | 0.031789 | 2439 | 23410.7141 | 32.2491 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
649 | ORO FINO 11022090 | 103031102 | ORO FINO 1102 | 14.7459 | 183 | 0.0022675 | 0.41496 | 2440 | 23425.4601 | 31.8341 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2752 | FULTON 1107CB | 42561107 | FULTON 1107 | 0.54401 | 166 | 0.0022645 | 0.37591 | 2441 | 23426.0041 | 31.4582 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8081 | CAMP EVERS 210612840 | 83622106 | CAMP EVERS 2106 | 3.9298 | 50 | 0.002258 | 0.1129 | 2442 | 23429.9339 | 31.3453 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
365 | PURISIMA 110149394 | 182971101 | PURISIMA 1101 | 1.1416 | 111 | 0.0022509 | 0.24985 | 2443 | 23431.0755 | 31.0954 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
707 | DEL MONTE 21042760 | 182222104 | DEL MONTE 2104 | 2.7091 | 28 | 0.0022393 | 0.062701 | 2444 | 23433.7846 | 31.0327 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7540 | LUCERNE 11062327 | 43351106 | LUCERNE 1106 | 1.1901 | 20 | 0.0022381 | 0.044762 | 2445 | 23434.9747 | 30.988 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9432 | GUALALA 1111445166 | 42841111 | GUALALA 1111 | 7.5601 | 71 | 0.0022354 | 0.15871 | 2446 | 23442.5349 | 30.8293 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2414 | PINE GROVE 110245292 | 163751102 | PINE GROVE 1102 | 10.7835 | 132 | 0.002235 | 0.29501 | 2447 | 23453.3183 | 30.5342 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7039 | IGNACIO 1101CB | 42481101 | IGNACIO 1101 | 1.6722 | 19 | 0.0022279 | 0.042331 | 2448 | 23454.9905 | 30.4919 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6713 | LAURELES 1112438 | 182371112 | LAURELES 1112 | 5.1127 | 48 | 0.0022241 | 0.10675 | 2449 | 23460.1033 | 30.3852 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1808 | HARTLEY 1101738 | 43211101 | HARTLEY 1101 | 2.6156 | 106 | 0.0022159 | 0.23488 | 2450 | 23462.7189 | 30.1503 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9055 | ORO FINO 1102CB | 103031102 | ORO FINO 1102 | 2.0983 | 27 | 0.0021922 | 0.059189 | 2451 | 23464.8172 | 30.0911 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
500 | ALTO 112278672 | 42031122 | ALTO 1122 | 3.778 | 123 | 0.0021883 | 0.26916 | 2452 | 23468.5952 | 29.8219 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9919 | MONTE RIO 1113678 | 42811113 | MONTE RIO 1113 | 1.867 | 17 | 0.002188 | 0.037196 | 2453 | 23470.4622 | 29.7847 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8710 | SUMMIT 110186658 | 152591101 | SUMMIT 1101 | 0.63954 | 7 | 0.0021861 | 0.015303 | 2454 | 23471.1017 | 29.7694 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3183 | PINE GROVE 11011021 | 163751101 | PINE GROVE 1101 | 4.1659 | 56 | 0.0021716 | 0.12161 | 2455 | 23475.2676 | 29.6478 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3039 | BIG BASIN 110110296 | 82841101 | BIG BASIN 1101 | 14.4211 | 181 | 0.0021702 | 0.3928 | 2456 | 23489.6887 | 29.255 | 29.255 | #N/A | TRUE | 7.6233 | TRUE | TRUE
10621 | EEL RIVER 1103987714 | 192381103 | EEL RIVER 1103 | 0.75759 | 6 | 0.0021699 | 0.01302 | 2457 | 23490.4463 | 29.242 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2552 | HALSEY 11022514 | 152241102 | HALSEY 1102 | 10.9686 | 212 | 0.0021687 | 0.45975 | 2458 | 23501.4149 | 28.7823 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1900 | PLACERVILLE 1111508410 | 153081111 | PLACERVILLE 1111 | 4.6805 | 73 | 0.002162 | 0.15783 | 2459 | 23506.0954 | 28.6244 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7805 | POINT MORETTI 11015074 | 82931101 | POINT MORETTI 1101 | 1.3653 | 34 | 0.0021548 | 0.073264 | 2460 | 23507.4607 | 28.5512 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9738 | ECHO SUMMIT 1101344250 | 158031101 | ECHO SUMMIT 1101 | 0.8075 | 10 | 0.0021484 | 0.021484 | 2461 | 23508.2682 | 28.5297 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3248 | HARRIS 1109355914 | 192431109 | HARRIS 1109 | 8.0813 | 104 | 0.0021471 | 0.2233 | 2462 | 23516.3495 | 28.3064 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5158 | MORRO BAY 1101W20 | 183011101 | MORRO BAY 1101 | 2.2074 | 48 | 0.0021357 | 0.10251 | 2463 | 23518.5569 | 28.2039 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5206 | CAMP EVERS 21065020 | 83622106 | CAMP EVERS 2106 | 15.0734 | 185 | 0.0021265 | 0.3934 | 2464 | 23533.6303 | 27.8105 | 27.8105 | #N/A | TRUE | 1.0392 | TRUE | TRUE
8641 | PETALUMA C 1109857148 | 42631109 | PETALUMA C 1109 | 0.93456 | 31 | 0.0021126 | 0.065491 | 2465 | 23534.5649 | 27.745 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4750 | PENNGROVE 1101554 | 43471101 | PENNGROVE 1101 | 0 | 130 | 0.0021107 | 0.2744 | 2466 | 23534.5649 | 27.4706 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5805 | PARADISE 110439216 | 102831104 | PARADISE 1104 | 1.6313 | 41 | 0.0021 | 0.086098 | 2467 | 23536.1962 | 27.3845 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3222 | WEST POINT 11014706 | 163201101 | WEST POINT 1101 | 11.4541 | 138 | 0.0020959 | 0.28923 | 2468 | 23547.6503 | 27.0953 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2065 | EL DORADO PH 21026645 | 152762102 | EL DORADO PH 2102 | 4.2184 | 52 | 0.0020868 | 0.10851 | 2469 | 23551.8687 | 26.9867 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6903 | VINEYARD 2107MR332 | 14502107 | VINEYARD 2107 | 0.32359 | 31 | 0.0020705 | 0.064186 | 2470 | 23552.1923 | 26.9226 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3802 | MORRO BAY 1102868170 | 183011102 | MORRO BAY 1102 | 9.071 | 59 | 0.0020479 | 0.12083 | 2471 | 23561.2632 | 26.8017 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3290 | TAR FLAT 04023144 | 163240402 | TAR FLAT 0402 | 4.8657 | 58 | 0.0020462 | 0.11868 | 2472 | 23566.1289 | 26.683 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9541 | RINCON 1101839669 | 43321101 | RINCON 1101 | 0.6148 | 12 | 0.0020383 | 0.02446 | 2473 | 23566.7437 | 26.6586 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
671 | CAMP EVERS 21045096 | 83622104 | CAMP EVERS 2104 | 20.3112 | 232 | 0.0020379 | 0.4728 | 2474 | 23587.0549 | 26.1858 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6416 | PLACER 1102CB | 152461102 | PLACER 1102 | 2.0893 | 23 | 0.0020369 | 0.046849 | 2475 | 23589.1443 | 26.1389 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9674 | GUALALA 1112CB | 42841112 | GUALALA 1112 | 1.5966 | 22 | 0.0020177 | 0.044389 | 2476 | 23590.7409 | 26.0946 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1510 | MONTE RIO 1113CB | 42811113 | MONTE RIO 1113 | 4.5284 | 49 | 0.0020136 | 0.098667 | 2477 | 23595.2693 | 25.9959 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1572 | ECHO SUMMIT 11012500 | 158031101 | ECHO SUMMIT 1101 | 2.1886 | 26 | 0.0019811 | 0.05151 | 2478 | 23597.4579 | 25.9444 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
808 | PEORIA 1701169700 | 163781701 | PEORIA 1701 | 8.3415 | 63 | 0.001973 | 0.1243 | 2479 | 23605.7994 | 25.8201 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1792 | MORAGA 1102CB | 13801102 | MORAGA 1102 | 5.3075 | 130 | 0.0019722 | 0.25639 | 2480 | 23611.1069 | 25.5637 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6608 | FORT ROSS 1121134 | 42851121 | FORT ROSS 1121 | 8.2489 | 99 | 0.0019671 | 0.19475 | 2481 | 23619.3559 | 25.3689 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5795 | HIGGINS 1103995672 | 152691103 | HIGGINS 1103 | 3.6847 | 79 | 0.0019604 | 0.15487 | 2482 | 23623.0405 | 25.2141 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7320 | FAIRVIEW 220799096 | 13432207 | FAIRVIEW 2207 | 9.8793 | 56 | 0.0019603 | 0.10978 | 2483 | 23632.9199 | 25.1043 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1460 | PARADISE 1105121988 | 102831105 | PARADISE 1105 | 6.9728 | 92 | 0.0019488 | 0.17929 | 2484 | 23639.8926 | 24.925 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
223 | ROB ROY 210410960 | 83692104 | ROB ROY 2104 | 18.7275 | 320 | 0.0019454 | 0.62252 | 2485 | 23658.6201 | 24.3025 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9882 | VOLTA 1102453266 | 102541102 | VOLTA 1102 | 0.31706 | 5 | 0.0019312 | 0.0096562 | 2486 | 23658.9372 | 24.2928 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2825 | COTATI 1104CB | 42271104 | COTATI 1104 | 4.5242 | 93 | 0.0019107 | 0.17769 | 2487 | 23663.4613 | 24.1151 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9868 | VOLTA 110293418 | 102541102 | VOLTA 1102 | 2.5767 | 23 | 0.0019038 | 0.043787 | 2488 | 23666.0381 | 24.0713 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7915 | LOS GATOS 1106697500 | 82021106 | LOS GATOS 1106 | 6.735 | 74 | 0.0019029 | 0.14082 | 2489 | 23672.7731 | 23.9305 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9296 | DUNBAR 1103835658 | 43071103 | DUNBAR 1103 | 0.0311 | 11 | 0.0018987 | 0.020885 | 2490 | 23672.8042 | 23.9096 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6742 | ALTO 11251158 | 42031125 | ALTO 1125 | 2.2302 | 65 | 0.0018981 | 0.12337 | 2491 | 23675.0344 | 23.7863 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4000 | RINCON 1101576 | 43321101 | RINCON 1101 | 0.98357 | 116 | 0.0018636 | 0.21618 | 2492 | 23676.0179 | 23.5701 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4995 | SOLEDAD 21027008 | 182052102 | SOLEDAD 2102 | 5.0272 | 122 | 0.0018473 | 0.22537 | 2493 | 23681.0451 | 23.3447 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6887 | HATTON 1102648928 | 182291102 | HATTON 1102 | 3.9523 | 44 | 0.0018437 | 0.081123 | 2494 | 23684.9974 | 23.2636 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9513 | GREEN VALLEY 2101535998 | 83192101 | GREEN VALLEY 2101 | 4.4378 | 43 | 0.0018414 | 0.079178 | 2495 | 23689.4352 | 23.1844 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2632 | APPLE HILL 110412947 | 153661104 | APPLE HILL 1104 | 3.5483 | 49 | 0.0018388 | 0.0901 | 2496 | 23692.9835 | 23.0943 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7783 | MIRABEL 110257840 | 42091102 | MIRABEL 1102 | 2.6345 | 29 | 0.0018331 | 0.053161 | 2497 | 23695.6181 | 23.0411 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
26 | TASSAJARA 2103CB | 14662103 | TASSAJARA 2103 | 0.48966 | 259 | 0.0018283 | 0.47354 | 2498 | 23696.1077 | 22.5676 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8978 | BIG RIVER 1101954 | 43081101 | BIG RIVER 1101 | 7.6897 | 78 | 0.0018244 | 0.1423 | 2499 | 23703.7974 | 22.4253 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
85 | HALSEY 11011704 | 152241101 | HALSEY 1101 | 13.1957 | 160 | 0.001823 | 0.29168 | 2500 | 23716.9931 | 22.1336 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2388 | CAMP EVERS 21059031 | 83622105 | CAMP EVERS 2105 | 1.0823 | 17 | 0.0018195 | 0.030932 | 2501 | 23718.0754 | 22.1027 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2038 | MORAGA 1104CB | 13801104 | MORAGA 1104 | 9.7831 | 214 | 0.0018118 | 0.38772 | 2502 | 23727.8585 | 21.715 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6140 | OCEANO 1106V28 | 182601106 | OCEANO 1106 | 1.2171 | 99 | 0.0018053 | 0.17873 | 2503 | 23729.0756 | 21.5362 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9346 | LAURELES 11116421 | 182371111 | LAURELES 1111 | 1.7261 | 20 | 0.0018044 | 0.036089 | 2504 | 23730.8017 | 21.5002 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
680 | CAMP EVERS 210612760 | 83622106 | CAMP EVERS 2106 | 26.3906 | 299 | 0.0017903 | 0.53531 | 2505 | 23757.1923 | 20.9648 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1725 | BOLINAS 1101CB | 42261101 | BOLINAS 1101 | 2.1394 | 26 | 0.0017811 | 0.04631 | 2506 | 23759.3317 | 20.9185 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1486 | BEN LOMOND 1101BL 1101 | 83041101 | BEN LOMOND 1101 | 8.4328 | 101 | 0.0017681 | 0.17858 | 2507 | 23767.7645 | 20.74 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8439 | OAKHURST 110310190 | 254421103 | OAKHURST 1103 | 8.4469 | 61 | 0.0017583 | 0.10725 | 2508 | 23776.2114 | 20.6327 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10411 | BURNEY 1102272636 | 103311102 | BURNEY 1102 | 0.2681 | 5 | 0.0017542 | 0.0087708 | 2509 | 23776.4795 | 20.6239 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9794 | SONOMA 1106510055 | 42721106 | SONOMA 1106 | 0.50815 | 11 | 0.0017489 | 0.019238 | 2510 | 23776.9877 | 20.6047 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1870 | TEMPLETON 2110307832 | 183052110 | TEMPLETON 2110 | 1.6247 | 133 | 0.0017438 | 0.23192 | 2511 | 23778.6123 | 20.3728 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4149 | EL DORADO PH 210219542 | 152762102 | EL DORADO PH 2102 | 9.5212 | 111 | 0.0017374 | 0.19285 | 2512 | 23788.1335 | 20.1799 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5394 | BRUNSWICK 11052100 | 152481105 | BRUNSWICK 1105 | 3.9724 | 47 | 0.0017366 | 0.081621 | 2513 | 23792.106 | 20.0983 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7138 | MONTE RIO 11138299 | 42811113 | MONTE RIO 1113 | 1.2021 | 13 | 0.0017192 | 0.02235 | 2514 | 23793.3081 | 20.076 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2315 | MORAGA 1101108540 | 13801101 | MORAGA 1101 | 4.8175 | 44 | 0.001717 | 0.075547 | 2515 | 23798.1256 | 20.0004 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
110 | RACETRACK 17038120 | 163761703 | RACETRACK 1703 | 8.932 | 108 | 0.0017068 | 0.18434 | 2516 | 23807.0576 | 19.8161 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1996 | MORAGA 1103E510R | 13801103 | MORAGA 1103 | 0.50207 | 84 | 0.0017029 | 0.14305 | 2517 | 23807.5597 | 19.673 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2784 | FRENCH GULCH 11022902 | 103381102 | FRENCH GULCH 1102 | 6.9875 | 8 | 0.0016954 | 0.013563 | 2518 | 23814.5472 | 19.6595 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4648 | HALF MOON BAY 1102863822 | 24101102 | HALF MOON BAY 1102 | 0.10488 | 8 | 0.0016933 | 0.013546 | 2519 | 23814.6521 | 19.6459 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4537 | LAKEWOOD 2107396264 | 13532107 | LAKEWOOD 2107 | 4.7882 | 95 | 0.0016927 | 0.16081 | 2520 | 23819.4403 | 19.4851 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6727 | BRUNSWICK 11032200 | 152481103 | BRUNSWICK 1103 | 5.5723 | 64 | 0.0016888 | 0.10808 | 2521 | 23825.0126 | 19.377 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5446 | PENRYN 11052406 | 152561105 | PENRYN 1105 | 0.076795 | 50 | 0.0016854 | 0.084272 | 2522 | 23825.0894 | 19.2928 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9065 | OTTER 11017611 | 182941101 | OTTER 1101 | 4.3928 | 42 | 0.0016834 | 0.070701 | 2523 | 23829.4822 | 19.2221 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4321 | BRUNSWICK 110633050 | 152481106 | BRUNSWICK 1106 | 1.1145 | 56 | 0.0016799 | 0.094072 | 2524 | 23830.5967 | 19.128 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7573 | ROSSMOOR 110639424 | 14161106 | ROSSMOOR 1106 | 0.92086 | 36 | 0.0016754 | 0.060313 | 2525 | 23831.5175 | 19.0677 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1005 | ROB ROY 21045082 | 83692104 | ROB ROY 2104 | 19.896 | 215 | 0.0016672 | 0.35844 | 2526 | 23851.4135 | 18.7092 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5885 | LAURELES 11122768 | 182371112 | LAURELES 1112 | 6.2832 | 92 | 0.0016647 | 0.15315 | 2527 | 23857.6968 | 18.5561 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2281 | VOLTA 110185234 | 102541101 | VOLTA 1101 | 7.9123 | 92 | 0.0016524 | 0.15202 | 2528 | 23865.609 | 18.404 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3545 | PACIFICA 1104230272 | 22811104 | PACIFICA 1104 | 0.85605 | 18 | 0.0016485 | 0.029673 | 2529 | 23866.4651 | 18.3744 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6564 | NEWBURG 1131557468 | 192151131 | NEWBURG 1131 | 0.88482 | 28 | 0.0016475 | 0.046129 | 2530 | 23867.3499 | 18.3282 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2123 | IGNACIO 11011300 | 42481101 | IGNACIO 1101 | 3.1977 | 84 | 0.0016445 | 0.13814 | 2531 | 23870.5476 | 18.1901 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7516 | SAN LUIS OBISPO 1107CB | 182631107 | SAN LUIS OBISPO 1107 | 0.77757 | 19 | 0.0016436 | 0.031229 | 2532 | 23871.3252 | 18.1589 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1994 | SILVERADO 2103218894 | 43432103 | SILVERADO 2103 | 0.33574 | 14 | 0.00163 | 0.022819 | 2533 | 23871.6609 | 18.1361 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10204 | DUNBAR 110113481 | 43071101 | DUNBAR 1101 | 0 | 14 | 0.0016289 | 0.022805 | 2534 | 23871.6609 | 18.1133 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3837 | AUBERRY 1101D4982 | 254151101 | AUBERRY 1101 | 2.6805 | 21 | 0.0016248 | 0.034121 | 2535 | 23874.3414 | 18.0791 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
586 | WEIMAR 11022038 | 152491102 | WEIMAR 1102 | 13.3691 | 155 | 0.0016155 | 0.2504 | 2536 | 23887.7105 | 17.8287 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5218 | SYCAMORE CREEK 11112268 | 102971111 | SYCAMORE CREEK 1111 | 21.8256 | 217 | 0.0016039 | 0.34805 | 2537 | 23909.5361 | 17.4807 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1040 | GANSNER 110152664 | 103021101 | GANSNER 1101 | 0.17676 | 44 | 0.0016028 | 0.070524 | 2538 | 23909.7128 | 17.4102 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3804 | POINT MORETTI 110110726 | 82931101 | POINT MORETTI 1101 | 10.5262 | 124 | 0.0016007 | 0.19849 | 2539 | 23920.2391 | 17.2117 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1389 | STANISLAUS 17011331 | 162821701 | STANISLAUS 1701 | 4.3908 | 63 | 0.0015977 | 0.10065 | 2540 | 23924.6299 | 17.111 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8302 | VALLEY VIEW 1106P166 | 14341106 | VALLEY VIEW 1106 | 4.3931 | 27 | 0.0015975 | 0.043133 | 2541 | 23929.023 | 17.0679 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7677 | POINT MORETTI 110136516 | 82931101 | POINT MORETTI 1101 | 4.1639 | 53 | 0.0015908 | 0.08431 | 2542 | 23933.1869 | 16.9836 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9231 | ROB ROY 21045304 | 83692104 | ROB ROY 2104 | 3.5819 | 60 | 0.0015784 | 0.094707 | 2543 | 23936.7688 | 16.8889 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10838 | LAS GALLINAS A 1106685852 | 42991106 | LAS GALLINAS A 1106 | 0.065216 | 3 | 0.0015648 | 0.0046945 | 2544 | 23936.834 | 16.8842 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1125 | LAS GALLINAS A 1106CB | 42991106 | LAS GALLINAS A 1106 | 0.095554 | 111 | 0.0015644 | 0.17365 | 2545 | 23936.9295 | 16.7105 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6613 | HICKS 111660050 | 83431116 | HICKS 1116 | 8.1518 | 98 | 0.0015546 | 0.15235 | 2546 | 23945.0813 | 16.5582 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10410 | PUEBLO 2102391312 | 43292102 | PUEBLO 2102 | 0.14272 | 13 | 0.0015528 | 0.020186 | 2547 | 23945.2241 | 16.538 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3988 | SAN RAFAEL 1108322 | 42011108 | SAN RAFAEL 1108 | 7.1787 | 88 | 0.0015474 | 0.13618 | 2548 | 23952.4028 | 16.4018 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3811 | OAKLAND X 1106950688 | 12541106 | OAKLAND X 1106 | 3.6566 | 50 | 0.0015407 | 0.077034 | 2549 | 23956.0594 | 16.3248 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1254 | CURTIS 17039240 | 163351703 | CURTIS 1703 | 10.9736 | 151 | 0.0015394 | 0.23246 | 2550 | 23967.033 | 16.0923 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9703 | VOLTA 110280982 | 102541102 | VOLTA 1102 | 0.5199 | 8 | 0.0015382 | 0.012305 | 2551 | 23967.5529 | 16.08 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8204 | BEN LOMOND 04015144 | 83040401 | BEN LOMOND 0401 | 3.9583 | 36 | 0.0015295 | 0.055061 | 2552 | 23971.5112 | 16.025 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4922 | BIG RIVER 11013019 | 43081101 | BIG RIVER 1101 | 0.26534 | 11 | 0.0015165 | 0.016682 | 2553 | 23971.7766 | 16.0083 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4844 | SANTA ROSA A 1104173590 | 42151104 | SANTA ROSA A 1104 | 4.2891 | 46 | 0.0015131 | 0.069603 | 2554 | 23976.0657 | 15.9387 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7483 | FLINT 1101CB | 152531101 | FLINT 1101 | 0.64467 | 36 | 0.0015072 | 0.054259 | 2555 | 23976.7104 | 15.8844 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6669 | DUNBAR 1101234 | 43071101 | DUNBAR 1101 | 3.4708 | 81 | 0.0015051 | 0.12191 | 2556 | 23980.1812 | 15.7625 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7886 | OAKHURST 1102CB | 254421102 | OAKHURST 1102 | 2.6438 | 61 | 0.0014997 | 0.091479 | 2557 | 23982.825 | 15.671 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1710 | ELK 110191336 | 42981101 | ELK 1101 | 7.9184 | 78 | 0.0014969 | 0.11676 | 2558 | 23990.7434 | 15.5543 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
583 | MONTE RIO 1111969182 | 42811111 | MONTE RIO 1111 | 5.3314 | 64 | 0.0014937 | 0.095599 | 2559 | 23996.0748 | 15.4587 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3182 | KONOCTI 1108950 | 43311108 | KONOCTI 1108 | 6.2017 | 85 | 0.0014937 | 0.12697 | 2560 | 24002.2765 | 15.3317 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5332 | CLAYTON 2212CB | 12022212 | CLAYTON 2212 | 1.1805 | 140 | 0.0014894 | 0.20851 | 2561 | 24003.4571 | 15.1232 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4270 | LAS GALLINAS A 1104304 | 42991104 | LAS GALLINAS A 1104 | 0.13738 | 27 | 0.0014798 | 0.039953 | 2562 | 24003.5945 | 15.0832 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
886 | SALT SPRINGS 21024796 | 163692102 | SALT SPRINGS 2102 | 7.1917 | 114 | 0.0014707 | 0.16766 | 2563 | 24010.7862 | 14.9156 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1846 | BIG RIVER 11013002 | 43081101 | BIG RIVER 1101 | 7.2444 | 76 | 0.001464 | 0.11126 | 2564 | 24018.0306 | 14.8043 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6005 | MIRABEL 1101201156 | 42091101 | MIRABEL 1101 | 1.4513 | 26 | 0.0014632 | 0.038044 | 2565 | 24019.4819 | 14.7663 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9286 | SOLEDAD 2101315500 | 182052101 | SOLEDAD 2101 | 1.1082 | 22 | 0.0014578 | 0.032073 | 2566 | 24020.59 | 14.7342 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2001 | SAN RAFAEL 110839156 | 42011108 | SAN RAFAEL 1108 | 3.4686 | 62 | 0.0014467 | 0.089693 | 2567 | 24024.0586 | 14.6445 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2593 | HIGGINS 1104533648 | 152691104 | HIGGINS 1104 | 6.7544 | 93 | 0.0014323 | 0.13321 | 2568 | 24030.813 | 14.5113 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2853 | EL DORADO PH 2101668674 | 152762101 | EL DORADO PH 2101 | 9.5082 | 112 | 0.0014289 | 0.16003 | 2569 | 24040.3212 | 14.3513 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
701 | CAMP EVERS 210512590 | 83622105 | CAMP EVERS 2105 | 5.1174 | 69 | 0.0014267 | 0.09844 | 2570 | 24045.4386 | 14.2528 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9206 | SISQUOC 110245261 | 182811102 | SISQUOC 1102 | 0.10255 | 10 | 0.001423 | 0.01423 | 2571 | 24045.5411 | 14.2386 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6505 | MONTE RIO 11131313 | 42811113 | MONTE RIO 1113 | 1.2408 | 19 | 0.0014057 | 0.026709 | 2572 | 24046.7819 | 14.2119 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4406 | COTATI 110475972 | 42271104 | COTATI 1104 | 3.3475 | 61 | 0.0013938 | 0.085021 | 2573 | 24050.1294 | 14.1269 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7967 | MENLO 11038982 | 24131103 | MENLO 1103 | 4.6205 | 50 | 0.0013928 | 0.06964 | 2574 | 24054.7499 | 14.0572 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9897 | ORO FINO 110239154 | 103031102 | ORO FINO 1102 | 0.88247 | 11 | 0.0013923 | 0.015315 | 2575 | 24055.6324 | 14.0419 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5536 | GUALALA 1111CB | 42841111 | GUALALA 1111 | 3.8705 | 47 | 0.0013913 | 0.065391 | 2576 | 24059.5029 | 13.9765 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3869 | PINE GROVE 11021765 | 163751102 | PINE GROVE 1102 | 1.4523 | 20 | 0.0013887 | 0.027774 | 2577 | 24060.9553 | 13.9487 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2705 | FORT ORD 210736596 | 182402107 | FORT ORD 2107 | 4.0848 | 145 | 0.0013847 | 0.20079 | 2578 | 24065.04 | 13.7479 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5302 | BIG BASIN 11015000 | 82841101 | BIG BASIN 1101 | 1.9571 | 23 | 0.0013814 | 0.031772 | 2579 | 24066.9972 | 13.7162 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10692 | ROSSMOOR 1109CB | 14161109 | ROSSMOOR 1109 | 0.0047054 | 6 | 0.001321 | 0.0079259 | 2580 | 24067.0019 | 13.7082 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5396 | FORT BRAGG A 11041316 | 42761104 | FORT BRAGG A 1104 | 13.7359 | 166 | 0.0013124 | 0.21786 | 2581 | 24080.7378 | 13.4904 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6380 | GUALALA 111135562 | 42841111 | GUALALA 1111 | 14.2412 | 147 | 0.0013006 | 0.19119 | 2582 | 24094.979 | 13.2992 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5878 | OLEMA 11011318 | 42291101 | OLEMA 1101 | 8.5105 | 113 | 0.0012974 | 0.14661 | 2583 | 24103.4895 | 13.1526 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7013 | SALT SPRINGS 2102L491 | 163692102 | SALT SPRINGS 2102 | 2.2154 | 31 | 0.0012903 | 0.039999 | 2584 | 24105.7048 | 13.1126 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3314 | LLAGAS 2101XR244 | 83182101 | LLAGAS 2101 | 0 | 157 | 0.0012825 | 0.20135 | 2585 | 24105.7048 | 12.9112 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
595 | GARBERVILLE 1103CB | 192221103 | GARBERVILLE 1103 | 0.60372 | 31 | 0.0012726 | 0.039451 | 2586 | 24106.3086 | 12.8718 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
842 | ELK 11011272 | 42981101 | ELK 1101 | 22.0935 | 236 | 0.0012681 | 0.29926 | 2587 | 24128.4021 | 12.5725 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3308 | SNEATH LANE 1106CB | 22721106 | SNEATH LANE 1106 | 3.0362 | 66 | 0.0012656 | 0.083532 | 2588 | 24131.4383 | 12.489 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4674 | WEST POINT 110112256 | 163201101 | WEST POINT 1101 | 6.4793 | 86 | 0.0012622 | 0.10855 | 2589 | 24137.9176 | 12.3804 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
141 | MORRO BAY 1102W34 | 183011102 | MORRO BAY 1102 | 7.5967 | 112 | 0.0012584 | 0.14094 | 2590 | 24145.5142 | 12.2395 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8023 | HOLLISTER 2105903238 | 182492105 | HOLLISTER 2105 | 4.0092 | 30 | 0.001258 | 0.037741 | 2591 | 24149.5235 | 12.2018 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
53 | DUNBAR 1102448 | 43071102 | DUNBAR 1102 | 2.4441 | 116 | 0.001256 | 0.1457 | 2592 | 24151.9676 | 12.0561 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5111 | ALHAMBRA 110581514 | 14101105 | ALHAMBRA 1105 | 2.9716 | 65 | 0.0012525 | 0.08141 | 2593 | 24154.9392 | 11.9746 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
347 | BRUNSWICK 11052204 | 152481105 | BRUNSWICK 1105 | 7.2254 | 84 | 0.0012429 | 0.1044 | 2594 | 24162.1646 | 11.8702 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2860 | CAMP EVERS 210311046 | 83622103 | CAMP EVERS 2103 | 16.0762 | 194 | 0.0012326 | 0.23912 | 2595 | 24178.2407 | 11.6311 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5152 | WOODSIDE 11018522 | 24251101 | WOODSIDE 1101 | 1.9088 | 123 | 0.0012059 | 0.14833 | 2596 | 24180.1495 | 11.4828 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10217 | PAUL SWEET 2102959032 | 83252102 | PAUL SWEET 2102 | 0.79772 | 11 | 0.0012034 | 0.013238 | 2597 | 24180.9472 | 11.4696 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6918 | DUNBAR 1103872066 | 43071103 | DUNBAR 1103 | 0.53256 | 13 | 0.0011906 | 0.015478 | 2598 | 24181.4798 | 11.4541 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5057 | WEIMAR 11012764 | 152491101 | WEIMAR 1101 | 6.1351 | 68 | 0.0011906 | 0.080958 | 2599 | 24187.6149 | 11.3731 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8401 | IGNACIO 11051943 | 42481105 | IGNACIO 1105 | 1.2181 | 17 | 0.0011872 | 0.020183 | 2600 | 24188.833 | 11.3529 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2098 | VOLTA 1102641544 | 102541102 | VOLTA 1102 | 4.9448 | 58 | 0.0011816 | 0.068531 | 2601 | 24193.7779 | 11.2844 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5971 | SANTA ROSA A 110464565 | 42151104 | SANTA ROSA A 1104 | 0.79819 | 13 | 0.001175 | 0.015275 | 2602 | 24194.576 | 11.2691 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1887 | NAPA 1112CB | 42021112 | NAPA 1112 | 0.58483 | 226 | 0.0011724 | 0.26497 | 2603 | 24195.1609 | 11.0042 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5833 | DEL MONTE 21049500 | 182222104 | DEL MONTE 2104 | 5.698 | 71 | 0.0011663 | 0.082807 | 2604 | 24200.8589 | 10.9214 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3301 | RALSTON 1101836528 | 24141101 | RALSTON 1101 | 2.9084 | 39 | 0.0011552 | 0.045051 | 2605 | 24203.7673 | 10.8763 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1278 | LOS GATOS 1107CB | 82021107 | LOS GATOS 1107 | 15.2993 | 192 | 0.0011504 | 0.22088 | 2606 | 24219.0666 | 10.6554 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1215 | SAN RAMON 2106CB | 14232106 | SAN RAMON 2106 | 0.46931 | 25 | 0.001149 | 0.028724 | 2607 | 24219.5359 | 10.6267 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10840 | CLOVERDALE 1101704542 | 42821101 | CLOVERDALE 1101 | 0.215 | 3 | 0.0011475 | 0.0034424 | 2608 | 24219.7509 | 10.6233 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9582 | LOS OSITOS 2102624200 | 182082102 | LOS OSITOS 2102 | 1.5487 | 6 | 0.0011432 | 0.0068593 | 2609 | 24221.2996 | 10.6164 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6642 | STANISLAUS 1702L5381 | 162821702 | STANISLAUS 1702 | 1.2153 | 15 | 0.0011429 | 0.017144 | 2610 | 24222.515 | 10.5993 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10129 | VALLEY VIEW 1103218424 | 14341103 | VALLEY VIEW 1103 | 0.53854 | 4 | 0.0011372 | 0.0045488 | 2611 | 24223.0535 | 10.5947 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2575 | BIG RIVER 110155402 | 43081101 | BIG RIVER 1101 | 2.4826 | 104 | 0.0011234 | 0.11683 | 2612 | 24225.5361 | 10.4779 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2609 | MIRABEL 1102503000 | 42091102 | MIRABEL 1102 | 4.5824 | 54 | 0.0011185 | 0.060401 | 2613 | 24230.1185 | 10.4175 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8405 | MONTE RIO 1111240 | 42811111 | MONTE RIO 1111 | 3.0785 | 42 | 0.0011134 | 0.046762 | 2614 | 24233.1971 | 10.3707 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1947 | ROB ROY 210410930 | 83692104 | ROB ROY 2104 | 0.98524 | 149 | 0.0011126 | 0.16578 | 2615 | 24234.1823 | 10.2049 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6789 | MIRABEL 11021139 | 42091102 | MIRABEL 1102 | 2.0454 | 25 | 0.0011071 | 0.027677 | 2616 | 24236.2277 | 10.1773 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10452 | PIT NO 3 21011480 | 103732101 | PIT NO 3 2101 | 2.1529 | 20 | 0.0011038 | 0.022077 | 2617 | 24238.3806 | 10.1552 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3881 | CORRAL 110275622 | 162991102 | CORRAL 1102 | 1.2162 | 78 | 0.0010989 | 0.085711 | 2618 | 24239.5968 | 10.0695 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
656 | MORAGA 1105CB | 13801105 | MORAGA 1105 | 5.7453 | 121 | 0.001078 | 0.13044 | 2619 | 24245.3422 | 9.939 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7044 | SALT SPRINGS 210297924 | 163692102 | SALT SPRINGS 2102 | 5.1507 | 49 | 0.0010653 | 0.052198 | 2620 | 24250.4928 | 9.8868 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1866 | HIGGINS 1104842642 | 152691104 | HIGGINS 1104 | 5.8135 | 80 | 0.0010503 | 0.084021 | 2621 | 24256.3063 | 9.8028 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1316 | SHADY GLEN 1101CB | 152431101 | SHADY GLEN 1101 | 3.5282 | 72 | 0.0010502 | 0.075616 | 2622 | 24259.8345 | 9.7272 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8148 | MIWUK 1702S1547 | 163661702 | MIWUK 1702 | 2.7718 | 39 | 0.0010487 | 0.040901 | 2623 | 24262.6064 | 9.6863 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4763 | SNEATH LANE 11071277 | 22721107 | SNEATH LANE 1107 | 0 | 30 | 0.001018 | 0.030539 | 2624 | 24262.6064 | 9.6558 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10287 | DUNLAP 11027290 | 254061102 | DUNLAP 1102 | 0.66837 | 8 | 0.0010126 | 0.0081011 | 2625 | 24263.2747 | 9.6477 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9998 | RESEARCH 2102644462 | 14692102 | RESEARCH 2102 | 0.35278 | 24 | 0.0010124 | 0.024298 | 2626 | 24263.6275 | 9.6234 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1937 | SARATOGA 1107LC12 | 83371107 | SARATOGA 1107 | 7.4858 | 86 | 0.0010097 | 0.086838 | 2627 | 24271.1133 | 9.5365 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3 | HIGGINS 1104498932 | 152691104 | HIGGINS 1104 | 3.7441 | 57 | 0.0010076 | 0.057431 | 2628 | 24274.8574 | 9.4791 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7928 | HALSEY 11015731 | 152241101 | HALSEY 1101 | 3.1259 | 41 | 0.0010067 | 0.041274 | 2629 | 24277.9833 | 9.4378 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5582 | TAMARACK 1101CB | 152291101 | TAMARACK 1101 | 17.479 | 148 | 0.0010065 | 0.14896 | 2630 | 24295.4623 | 9.2889 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5935 | MORAGA 1103CB | 13801103 | MORAGA 1103 | 1.3309 | 82 | 0.0010058 | 0.082476 | 2631 | 24296.7932 | 9.2064 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6299 | PEORIA 170587222 | 163781705 | PEORIA 1705 | 5.1212 | 57 | 0.0010031 | 0.057176 | 2632 | 24301.9144 | 9.1492 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2943 | PAUL SWEET 2105CB | 83252105 | PAUL SWEET 2105 | 7.4461 | 86 | 0.0010024 | 0.086208 | 2633 | 24309.3606 | 9.063 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9018 | GREEN VALLEY 2101509068 | 83192101 | GREEN VALLEY 2101 | 1.0289 | 22 | 0.0010019 | 0.022042 | 2634 | 24310.3894 | 9.041 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8604 | MORGAN HILL 2105975388 | 83242105 | MORGAN HILL 2105 | 0.48181 | 18 | 0.0010016 | 0.018029 | 2635 | 24310.8713 | 9.0229 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5120 | PAUL SWEET 21045394 | 83252104 | PAUL SWEET 2104 | 14.5061 | 180 | 0.00099214 | 0.17859 | 2636 | 24325.3774 | 8.8443 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6690 | GUALALA 1111887180 | 42841111 | GUALALA 1111 | 5.3384 | 61 | 0.00098628 | 0.060163 | 2637 | 24330.7158 | 8.7842 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3875 | FORT BRAGG A 11014698 | 42761101 | FORT BRAGG A 1101 | 8.0068 | 101 | 0.00097756 | 0.098734 | 2638 | 24338.7226 | 8.6854 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8479 | SALT SPRINGS 2102L7283 | 163692102 | SALT SPRINGS 2102 | 0.65475 | 12 | 0.00097446 | 0.011693 | 2639 | 24339.3774 | 8.6738 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1105 | PLACER 110451732 | 152461104 | PLACER 1104 | 0.67967 | 110 | 0.00097323 | 0.10706 | 2640 | 24340.0571 | 8.5667 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6916 | BEN LOMOND 110196738 | 83041101 | BEN LOMOND 1101 | 6.7078 | 84 | 0.00097276 | 0.081712 | 2641 | 24346.7649 | 8.485 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5851 | SAN RAFAEL 1109692576 | 42011109 | SAN RAFAEL 1109 | 2.4083 | 51 | 0.0009691 | 0.049424 | 2642 | 24349.1732 | 8.4356 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1894 | HALF MOON BAY 11028848 | 24101102 | HALF MOON BAY 1102 | 3.8535 | 117 | 0.00096385 | 0.11277 | 2643 | 24353.0266 | 8.3228 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3844 | OLEMA 110150396 | 42291101 | OLEMA 1101 | 12.9443 | 162 | 0.00096084 | 0.15566 | 2644 | 24365.971 | 8.1671 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8685 | SANTA ROSA A 1111114 | 42151111 | SANTA ROSA A 1111 | 0.010871 | 40 | 0.00096055 | 0.038422 | 2645 | 24365.9818 | 8.1287 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3877 | LOS GATOS 110660116 | 82021106 | LOS GATOS 1106 | 12.2027 | 151 | 0.00095505 | 0.14421 | 2646 | 24378.1846 | 7.9845 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
46 | MONTE RIO 11111703 | 42811111 | MONTE RIO 1111 | 1.376 | 16 | 0.00095446 | 0.015271 | 2647 | 24379.5606 | 7.9692 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2992 | EMERALD LAKE 0401CB | 24080401 | EMERALD LAKE 0401 | 9.3444 | 130 | 0.00094726 | 0.12314 | 2648 | 24388.905 | 7.8461 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5798 | DIAMOND SPRINGS 1107217974 | 152261107 | DIAMOND SPRINGS 1107 | 4.0976 | 44 | 0.00093976 | 0.04135 | 2649 | 24393.0026 | 7.8047 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5351 | TEMPLETON 2113A32 | 183052113 | TEMPLETON 2113 | 1.6367 | 76 | 0.00093807 | 0.071294 | 2650 | 24394.6393 | 7.7334 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5142 | STANISLAUS 17021850 | 162821702 | STANISLAUS 1702 | 13.4625 | 182 | 0.00093342 | 0.16988 | 2651 | 24408.1018 | 7.5636 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7375 | ARCATA 11224218 | 192021122 | ARCATA 1122 | 4.7795 | 27 | 0.00093079 | 0.025131 | 2652 | 24412.8813 | 7.5384 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2956 | BIG BASIN 110276752 | 82841102 | BIG BASIN 1102 | 2.7224 | 36 | 0.00091318 | 0.032874 | 2653 | 24415.6037 | 7.5056 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3629 | BRUNSWICK 11051030 | 152481105 | BRUNSWICK 1105 | 15.89 | 217 | 0.00090994 | 0.19746 | 2654 | 24431.4937 | 7.3081 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9250 | MIWUK 17021808 | 163661702 | MIWUK 1702 | 1.8333 | 27 | 0.00090929 | 0.024551 | 2655 | 24433.327 | 7.2835 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8540 | DEL MONTE 210436720 | 182222104 | DEL MONTE 2104 | 5.9526 | 87 | 0.00089535 | 0.077895 | 2656 | 24439.2796 | 7.2056 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
950 | JARVIS 1108MR366 | 13501108 | JARVIS 1108 | 0 | 134 | 0.00088159 | 0.11813 | 2657 | 24439.2796 | 7.0875 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1888 | ROB ROY 2104CB | 83692104 | ROB ROY 2104 | 14.3153 | 170 | 0.0008744 | 0.14865 | 2658 | 24453.595 | 6.9389 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
311 | SALT SPRINGS 21023142 | 163692102 | SALT SPRINGS 2102 | 17.9625 | 256 | 0.00086175 | 0.22061 | 2659 | 24471.5575 | 6.7183 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
978 | BRYANT 0402CB | 13090402 | BRYANT 0402 | 2.3419 | 111 | 0.00085884 | 0.095332 | 2660 | 24473.8994 | 6.6229 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7054 | STANISLAUS 1702L3151 | 162821702 | STANISLAUS 1702 | 0.99155 | 13 | 0.00085242 | 0.011082 | 2661 | 24474.8909 | 6.6118 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3980 | BIG BASIN 110112838 | 82841101 | BIG BASIN 1101 | 2.3664 | 32 | 0.00085046 | 0.027215 | 2662 | 24477.2573 | 6.5846 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8804 | SILVERADO 2103403102 | 43432103 | SILVERADO 2103 | 0.4901 | 18 | 0.00084561 | 0.015221 | 2663 | 24477.7474 | 6.5694 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6283 | HATTON 11022010 | 182291102 | HATTON 1102 | 3.9836 | 43 | 0.00084365 | 0.036277 | 2664 | 24481.731 | 6.5331 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
164 | CORONA 11034446 | 43491103 | CORONA 1103 | 0 | 124 | 0.00084052 | 0.10422 | 2665 | 24481.731 | 6.4289 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5512 | MORAGA 1101669542 | 13801101 | MORAGA 1101 | 3.5232 | 49 | 0.0008334 | 0.040836 | 2666 | 24485.2542 | 6.3881 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5671 | CURTIS 170190120 | 163351701 | CURTIS 1701 | 3.1334 | 64 | 0.00082387 | 0.052727 | 2667 | 24488.3875 | 6.3353 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5328 | OROSI 11027948F | 252841102 | OROSI 1102 | 1.064 | 74 | 0.00082174 | 0.060809 | 2668 | 24489.4516 | 6.2745 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3271 | STAFFORD 1101CB | 43201101 | STAFFORD 1101 | 1.3605 | 180 | 0.0008192 | 0.14746 | 2669 | 24490.812 | 6.1271 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3349 | STANISLAUS 17026028 | 162821702 | STANISLAUS 1702 | 8.3097 | 115 | 0.0008147 | 0.09369 | 2670 | 24499.1217 | 6.0334 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4063 | REDBUD 1102432 | 43191102 | REDBUD 1102 | 1.1202 | 130 | 0.00080536 | 0.1047 | 2671 | 24500.2419 | 5.9287 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4207 | SPRING GAP 170210720 | 162831702 | SPRING GAP 1702 | 4.7701 | 25 | 0.00079114 | 0.019779 | 2672 | 24505.012 | 5.9089 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6208 | BIG MEADOWS 2101CB | 102812101 | BIG MEADOWS 2101 | 2.106 | 21 | 0.00079069 | 0.016605 | 2673 | 24507.118 | 5.8923 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
682 | ROSSMOOR 110676468 | 14161106 | ROSSMOOR 1106 | 0.79619 | 35 | 0.00078905 | 0.027617 | 2674 | 24507.9142 | 5.8647 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5936 | OAKLAND K 1102CB | 12101102 | OAKLAND K 1102 | 2.9934 | 40 | 0.0007688 | 0.030752 | 2675 | 24510.9076 | 5.8339 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5479 | ROSSMOOR 1108CB | 14161108 | ROSSMOOR 1108 | 4.1821 | 92 | 0.00076238 | 0.070139 | 2676 | 24515.0896 | 5.7638 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3739 | WEIMAR 1102CB | 152491102 | WEIMAR 1102 | 12.1849 | 151 | 0.00075189 | 0.11354 | 2677 | 24527.2746 | 5.6503 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4477 | MIWUK 170238218 | 163661702 | MIWUK 1702 | 10.9416 | 132 | 0.00074696 | 0.098599 | 2678 | 24538.2162 | 5.5517 | 5.5517 | #N/A | TRUE | 2.6023 | TRUE | TRUE
262 | ROB ROY 21055090 | 83692105 | ROB ROY 2105 | 21.267 | 245 | 0.00074249 | 0.18191 | 2679 | 24559.4832 | 5.3698 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
459 | HARTLEY 1102824 | 43211102 | HARTLEY 1102 | 0.085463 | 103 | 0.00072721 | 0.074902 | 2680 | 24559.5687 | 5.2949 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3196 | SPRING GAP 17029280 | 162831702 | SPRING GAP 1702 | 6.3783 | 80 | 0.00072124 | 0.057699 | 2681 | 24565.9469 | 5.2372 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1359 | CAMP EVERS 210311056 | 83622103 | CAMP EVERS 2103 | 4.1747 | 48 | 0.00071991 | 0.034556 | 2682 | 24570.1216 | 5.2026 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2485 | EEL RIVER 1102530 | 192381102 | EEL RIVER 1102 | 0.073044 | 255 | 0.00070447 | 0.17964 | 2683 | 24570.1947 | 5.023 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6651 | PINECREST 04011818 | 163160401 | PINECREST 0401 | 3.0718 | 26 | 0.00069935 | 0.018183 | 2684 | 24573.2664 | 5.0048 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
413 | BRUNSWICK 11062796 | 152481106 | BRUNSWICK 1106 | 19.8767 | 253 | 0.00069507 | 0.17585 | 2685 | 24593.1431 | 4.8289 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4105 | CAMP EVERS 210410442 | 83622104 | CAMP EVERS 2104 | 5.6589 | 133 | 0.00069444 | 0.092361 | 2686 | 24598.802 | 4.7366 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2116 | LUCERNE 1106CB | 43351106 | LUCERNE 1106 | 1.8914 | 48 | 0.00069407 | 0.033315 | 2687 | 24600.6935 | 4.7032 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10094 | HARRIS 1109237791 | 192431109 | HARRIS 1109 | 1.4173 | 23 | 0.00069283 | 0.015935 | 2688 | 24602.1108 | 4.6873 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9596 | BRUNSWICK 1104285704 | 152481104 | BRUNSWICK 1104 | 1.0477 | 17 | 0.00068515 | 0.011648 | 2689 | 24603.1585 | 4.6757 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
591 | MIWUK 170110600 | 163661701 | MIWUK 1701 | 13.2797 | 161 | 0.000683 | 0.10996 | 2690 | 24616.4382 | 4.5657 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7040 | PAUL SWEET 2106428102 | 83252106 | PAUL SWEET 2106 | 12.2622 | 158 | 0.00068264 | 0.10786 | 2691 | 24628.7005 | 4.4578 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9535 | HOLLISTER 2105480430 | 182492105 | HOLLISTER 2105 | 0.90126 | 39 | 0.00068138 | 0.026574 | 2692 | 24629.6017 | 4.4313 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
751 | GUALALA 1112662 | 42841112 | GUALALA 1112 | 6.2273 | 104 | 0.00067921 | 0.070638 | 2693 | 24635.8291 | 4.3606 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9192 | PURISIMA 110154728 | 182971101 | PURISIMA 1101 | 1.0366 | 37 | 0.00066262 | 0.024517 | 2694 | 24636.8657 | 4.3361 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6603 | MIRABEL 11027347 | 42091102 | MIRABEL 1102 | 0.81751 | 10 | 0.00065864 | 0.0065864 | 2695 | 24637.6832 | 4.3295 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6890 | CHALLENGE 110113026 | 103201101 | CHALLENGE 1101 | 8.0255 | 70 | 0.00065269 | 0.045688 | 2696 | 24645.7086 | 4.2838 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4651 | PACIFICA 1102320094 | 22811102 | PACIFICA 1102 | 0.2735 | 11 | 0.00064788 | 0.0071266 | 2697 | 24645.9821 | 4.2767 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7773 | MONTE RIO 111215401 | 42811112 | MONTE RIO 1112 | 0.86276 | 11 | 0.00064146 | 0.0070561 | 2698 | 24646.8449 | 4.2697 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8375 | MONTE RIO 1111256 | 42811111 | MONTE RIO 1111 | 1.5013 | 17 | 0.00063627 | 0.010817 | 2699 | 24648.3462 | 4.2588 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6923 | OLEMA 1101758594 | 42291101 | OLEMA 1101 | 1.2079 | 21 | 0.00062774 | 0.013182 | 2700 | 24649.5541 | 4.2457 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10215 | IGNACIO 11011779 | 42481101 | IGNACIO 1101 | 0.33618 | 5 | 0.00062625 | 0.0031313 | 2701 | 24649.8903 | 4.2425 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4571 | TEMPLETON 2113A30 | 183052113 | TEMPLETON 2113 | 0.24929 | 25 | 0.00062089 | 0.015522 | 2702 | 24650.1396 | 4.227 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5501 | FORT BRAGG A 11013100 | 42761101 | FORT BRAGG A 1101 | 12.2041 | 198 | 0.00061511 | 0.12179 | 2703 | 24662.3436 | 4.1052 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7330 | HAMILTON BRANCH 110190334 | 102361101 | HAMILTON BRANCH 1101 | 3.3524 | 44 | 0.00061497 | 0.027059 | 2704 | 24665.696 | 4.0782 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3053 | HIGGINS 11032194 | 152691103 | HIGGINS 1103 | 1.3317 | 36 | 0.00060703 | 0.021853 | 2705 | 24667.0277 | 4.0563 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9597 | MORGAN HILL 2105XR602 | 83242105 | MORGAN HILL 2105 | 0.24324 | 13 | 0.00060529 | 0.0078688 | 2706 | 24667.2709 | 4.0484 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5378 | DIAMOND SPRINGS 1105CB | 152261105 | DIAMOND SPRINGS 1105 | 2.0698 | 47 | 0.00059825 | 0.028118 | 2707 | 24669.3407 | 4.0203 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1437 | HORSESHOE 110450142 | 152571104 | HORSESHOE 1104 | 2.2351 | 55 | 0.00059558 | 0.032757 | 2708 | 24671.5758 | 3.9876 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4026 | MIRABEL 1101CB | 42091101 | MIRABEL 1101 | 0.49245 | 70 | 0.00059471 | 0.04163 | 2709 | 24672.0682 | 3.9459 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7798 | LOS GATOS 110712041 | 82021107 | LOS GATOS 1107 | 6.3044 | 65 | 0.00059297 | 0.038543 | 2710 | 24678.3727 | 3.9074 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1553 | MEADOW LANE 2106C558R | 14302106 | MEADOW LANE 2106 | 1.2073 | 180 | 0.00059158 | 0.10648 | 2711 | 24679.5799 | 3.8009 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
380 | STANISLAUS 17021804 | 162821702 | STANISLAUS 1702 | 8.3797 | 118 | 0.00058985 | 0.069602 | 2712 | 24687.9596 | 3.7313 | 3.7313 | #N/A | TRUE | 1.9112 | TRUE | TRUE
10645 | DIAMOND SPRINGS 1103635040 | 152261103 | DIAMOND SPRINGS 1103 | 0.20148 | 2 | 0.0005888 | 0.0011776 | 2713 | 24688.1611 | 3.7301 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7077 | CORONA 1103776806 | 43491103 | CORONA 1103 | 0.25631 | 15 | 0.00058477 | 0.0087716 | 2714 | 24688.4174 | 3.7213 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4432 | BRUNSWICK 11053611 | 152481105 | BRUNSWICK 1105 | 1.6143 | 23 | 0.00057745 | 0.013281 | 2715 | 24690.0317 | 3.7081 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5741 | HICKS 2101XR250 | 83432101 | HICKS 2101 | 0 | 80 | 0.00057262 | 0.04581 | 2716 | 24690.0317 | 3.6623 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8362 | CASTRO VALLEY 1111CB | 14091111 | CASTRO VALLEY 1111 | 0.22209 | 16 | 0.00057058 | 0.0091293 | 2717 | 24690.2538 | 3.6531 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4792 | HALF MOON BAY 1102CB | 24101102 | HALF MOON BAY 1102 | 0.16592 | 50 | 0.0005603 | 0.028015 | 2718 | 24690.4197 | 3.6251 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2151 | MIWUK 170153038 | 163661701 | MIWUK 1701 | 6.6683 | 62 | 0.00055181 | 0.034212 | 2719 | 24697.088 | 3.5909 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5668 | ALLEGHANY 1101978 | 152101101 | ALLEGHANY 1101 | 13.9579 | 130 | 0.00055148 | 0.071692 | 2720 | 24711.0459 | 3.5192 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6116 | IGNACIO 1105908 | 42481105 | IGNACIO 1105 | 0.70005 | 42 | 0.00055062 | 0.023126 | 2721 | 24711.7459 | 3.4961 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2452 | OAKHURST 1103719490 | 254421103 | OAKHURST 1103 | 3.0184 | 44 | 0.00054847 | 0.024132 | 2722 | 24714.7643 | 3.4719 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1532 | HAMILTON BRANCH 1101CB | 102361101 | HAMILTON BRANCH 1101 | 2.3343 | 56 | 0.00054657 | 0.030608 | 2723 | 24717.0986 | 3.4413 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8732 | EL CERRITO G 1112418480 | 12501112 | EL CERRITO G 1112 | 0.75636 | 13 | 0.0005464 | 0.0071032 | 2724 | 24717.855 | 3.4342 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4263 | HALF MOON BAY 11038894 | 24101103 | HALF MOON BAY 1103 | 11.2506 | 110 | 0.00053494 | 0.058844 | 2725 | 24729.1056 | 3.3754 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4900 | CHESTER 11022564 | 103181102 | CHESTER 1102 | 2.2364 | 21 | 0.00053291 | 0.011191 | 2726 | 24731.3421 | 3.3642 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1003 | SANTA ROSA A 1111CB | 42151111 | SANTA ROSA A 1111 | 0.30506 | 88 | 0.00052634 | 0.046318 | 2727 | 24731.6472 | 3.3179 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8503 | SAN RAFAEL 11071276 | 42011107 | SAN RAFAEL 1107 | 3.7367 | 56 | 0.00052522 | 0.029412 | 2728 | 24735.3839 | 3.2885 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6580 | MIWUK 170247143 | 163661702 | MIWUK 1702 | 4.8991 | 67 | 0.00052216 | 0.034985 | 2729 | 24740.283 | 3.2535 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4101 | LAURELES 1112562376 | 182371112 | LAURELES 1112 | 7.9218 | 82 | 0.00052151 | 0.042763 | 2730 | 24748.2047 | 3.2107 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5934 | FITCH MOUNTAIN 1113154 | 42751113 | FITCH MOUNTAIN 1113 | 0.012787 | 108 | 0.00051973 | 0.056131 | 2731 | 24748.2175 | 3.1546 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5473 | EL DORADO PH 2102CB | 152762102 | EL DORADO PH 2102 | 5.5428 | 46 | 0.00051722 | 0.023792 | 2732 | 24753.7603 | 3.1308 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4174 | CAMP EVERS 210610718 | 83622106 | CAMP EVERS 2106 | 8.4677 | 98 | 0.0005122 | 0.050195 | 2733 | 24762.228 | 3.0806 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4155 | BRUNSWICK 110532536 | 152481105 | BRUNSWICK 1105 | 10.8995 | 144 | 0.00050182 | 0.072262 | 2734 | 24773.1275 | 3.0083 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4857 | SEACLIFF 040112946 | 83500401 | SEACLIFF 0401 | 2.4314 | 41 | 0.00050028 | 0.020511 | 2735 | 24775.5589 | 2.9878 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3888 | PUEBLO 1105716 | 43291105 | PUEBLO 1105 | 0.10016 | 124 | 0.00049954 | 0.061943 | 2736 | 24775.6591 | 2.9259 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6409 | MIWUK 1702S2247 | 163661702 | MIWUK 1702 | 1.4879 | 21 | 0.00049228 | 0.010338 | 2737 | 24777.1469 | 2.9156 | 2.9156 | #N/A | TRUE | 1.1682 | TRUE | TRUE
9855 | DUNLAP 1102778286 | 254061102 | DUNLAP 1102 | 2.6029 | 5 | 0.0004909 | 0.0024545 | 2738 | 24779.7498 | 2.9131 | 2.9131 | #N/A | TRUE | 2.48 | TRUE | TRUE
9129 | ROSSMOOR 1102457174 | 14161102 | ROSSMOOR 1102 | 0.57523 | 14 | 0.00048348 | 0.0067687 | 2739 | 24780.325 | 2.9063 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8205 | ATASCADERO 1102825520 | 182541102 | ATASCADERO 1102 | 1.1789 | 21 | 0.00047064 | 0.0098834 | 2740 | 24781.504 | 2.8964 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2233 | IGNACIO 11011264 | 42481101 | IGNACIO 1101 | 1.9136 | 50 | 0.00046357 | 0.023178 | 2741 | 24783.4175 | 2.8733 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4702 | BURNEY 110145984 | 103311101 | BURNEY 1101 | 4.8309 | 68 | 0.00046238 | 0.031442 | 2742 | 24788.2484 | 2.8418 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
911 | PEORIA 170590374 | 163781705 | PEORIA 1705 | 4.0885 | 48 | 0.0004592 | 0.022042 | 2743 | 24792.337 | 2.8198 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4097 | SILVERADO 2103CB | 43432103 | SILVERADO 2103 | 0 | 197 | 0.00045724 | 0.090077 | 2744 | 24792.337 | 2.7297 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5992 | MIWUK 17029270 | 163661702 | MIWUK 1702 | 5.8239 | 68 | 0.00045602 | 0.03101 | 2745 | 24798.1609 | 2.6987 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9472 | LLAGAS 2105XR234 | 83182105 | LLAGAS 2105 | 0.0025635 | 26 | 0.00045563 | 0.011846 | 2746 | 24798.1635 | 2.6869 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6378 | WOODACRE 11011238 | 43021101 | WOODACRE 1101 | 3.6817 | 30 | 0.0004533 | 0.013599 | 2747 | 24801.8452 | 2.6733 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1227 | MORAGA 110381146 | 13801103 | MORAGA 1103 | 0.7625 | 79 | 0.00045161 | 0.035677 | 2748 | 24802.6076 | 2.6376 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2519 | CAMPHORA 110122412 | 182071101 | CAMPHORA 1101 | 2.2876 | 130 | 0.0004496 | 0.058447 | 2749 | 24804.8952 | 2.5791 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2793 | CAMP EVERS 21065302 | 83622106 | CAMP EVERS 2106 | 5.9332 | 57 | 0.00044854 | 0.025567 | 2750 | 24810.8284 | 2.5536 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5402 | PACIFICA 1101CB | 22811101 | PACIFICA 1101 | 0.13437 | 38 | 0.00044808 | 0.017027 | 2751 | 24810.9628 | 2.5365 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6879 | SEACLIFF 0401CB | 83500401 | SEACLIFF 0401 | 5.7464 | 73 | 0.00044728 | 0.032652 | 2752 | 24816.7092 | 2.5039 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5244 | DUNBAR 1103440 | 43071103 | DUNBAR 1103 | 2.057 | 158 | 0.00044177 | 0.0698 | 2753 | 24818.7662 | 2.4341 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4679 | ROB ROY 210412596 | 83692104 | ROB ROY 2104 | 8.033 | 140 | 0.00043371 | 0.060719 | 2754 | 24826.7992 | 2.3734 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4037 | EL DORADO PH 21019759 | 152762101 | EL DORADO PH 2101 | 2.5547 | 32 | 0.00043106 | 0.013794 | 2755 | 24829.354 | 2.3596 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
909 | TULE POWER HOUSE 1101CB | 258591101 | TULE POWER HOUSE 1101 | 4.0838 | 11 | 0.00042329 | 0.0046561 | 2756 | 24833.4378 | 2.3549 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7552 | WEST POINT 1101L2219 | 163201101 | WEST POINT 1101 | 3.3854 | 41 | 0.00042266 | 0.017329 | 2757 | 24836.8232 | 2.3376 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3464 | SERRAMONTE 110412705 | 22861104 | SERRAMONTE 1104 | 0 | 74 | 0.00042265 | 0.031276 | 2758 | 24836.8232 | 2.3063 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7216 | BIG RIVER 110169032 | 43081101 | BIG RIVER 1101 | 8.487 | 101 | 0.00041877 | 0.042296 | 2759 | 24845.3102 | 2.264 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2590 | WOODSIDE 1104520832 | 24251104 | WOODSIDE 1104 | 6.0406 | 90 | 0.00040636 | 0.036573 | 2760 | 24851.3507 | 2.2274 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8755 | HALF MOON BAY 1101903182 | 24101101 | HALF MOON BAY 1101 | 0.65426 | 15 | 0.00040533 | 0.0060799 | 2761 | 24852.005 | 2.2214 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4732 | BIG RIVER 11011286 | 43081101 | BIG RIVER 1101 | 4.775 | 92 | 0.00040112 | 0.036903 | 2762 | 24856.78 | 2.1845 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3369 | ORO FINO 110276008 | 103031102 | ORO FINO 1102 | 15.9545 | 170 | 0.000401 | 0.068169 | 2763 | 24872.7345 | 2.1163 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9255 | LAS GALLINAS A 1106228906 | 42991106 | LAS GALLINAS A 1106 | 0.61442 | 21 | 0.00039716 | 0.0083403 | 2764 | 24873.3489 | 2.1079 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2888 | FOOTHILL 110299432 | 182951102 | FOOTHILL 1102 | 1.4661 | 115 | 0.00039549 | 0.045481 | 2765 | 24874.8151 | 2.0625 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7168 | STANISLAUS 17024905 | 162821702 | STANISLAUS 1702 | 2.3021 | 35 | 0.00038885 | 0.01361 | 2766 | 24877.1172 | 2.0489 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4177 | LOS GATOS 110760092 | 82021107 | LOS GATOS 1107 | 9.7136 | 108 | 0.00038814 | 0.041919 | 2767 | 24886.8308 | 2.0069 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9726 | SALT SPRINGS 21028442 | 163692102 | SALT SPRINGS 2102 | 12.0752 | 50 | 0.00038233 | 0.019117 | 2768 | 24898.9059 | 1.9878 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1168 | SAN RAFAEL 11081210 | 42011108 | SAN RAFAEL 1108 | 3.2645 | 73 | 0.00038163 | 0.027859 | 2769 | 24902.1705 | 1.96 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9856 | PUEBLO 1105419634 | 43291105 | PUEBLO 1105 | 0.10261 | 14 | 0.00037832 | 0.0052965 | 2770 | 24902.2731 | 1.9547 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1493 | SAN RAMON 2107CB | 14232107 | SAN RAMON 2107 | 0.30216 | 107 | 0.00037788 | 0.040433 | 2771 | 24902.5752 | 1.9142 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
531 | SAN RAFAEL 1109418 | 42011109 | SAN RAFAEL 1109 | 5.135 | 130 | 0.00037742 | 0.049065 | 2772 | 24907.7102 | 1.8652 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10509 | PAUL SWEET 2102337544 | 83252102 | PAUL SWEET 2102 | 0.35989 | 13 | 0.00037689 | 0.0048996 | 2773 | 24908.0701 | 1.8603 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
910 | DUNLAP 11027050 | 254061102 | DUNLAP 1102 | 9.4119 | 67 | 0.0003702 | 0.024804 | 2774 | 24917.482 | 1.8355 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3656 | HALF MOON BAY 11038089 | 24101103 | HALF MOON BAY 1103 | 2.8145 | 29 | 0.00036614 | 0.010618 | 2775 | 24920.2965 | 1.8248 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6207 | CAMP EVERS 210584166 | 83622105 | CAMP EVERS 2105 | 8.2232 | 97 | 0.00036427 | 0.035334 | 2776 | 24928.5197 | 1.7895 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6326 | OLEMA 11011252 | 42291101 | OLEMA 1101 | 4.1073 | 50 | 0.00036141 | 0.018071 | 2777 | 24932.627 | 1.7714 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
872 | FAIRVIEW 2207M501R | 13432207 | FAIRVIEW 2207 | 2.4962 | 60 | 0.00035751 | 0.021451 | 2778 | 24935.1232 | 1.75 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6151 | EDENVALE 2113CB | 82952113 | EDENVALE 2113 | 0.015269 | 24 | 0.00035038 | 0.0084091 | 2779 | 24935.1385 | 1.7416 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6316 | BIG RIVER 11011052 | 43081101 | BIG RIVER 1101 | 3.3289 | 49 | 0.00034866 | 0.017084 | 2780 | 24938.4674 | 1.7245 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4831 | ROB ROY 2105CB | 83692105 | ROB ROY 2105 | 0.73407 | 17 | 0.00034683 | 0.0058961 | 2781 | 24939.2014 | 1.7186 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5876 | OAKLAND X 1106CR020 | 12541106 | OAKLAND X 1106 | 2.4443 | 15 | 0.00034485 | 0.0051727 | 2782 | 24941.6458 | 1.7134 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8254 | DOLAN ROAD 1101857972 | 182381101 | DOLAN ROAD 1101 | 1.0395 | 18 | 0.00034064 | 0.0061316 | 2783 | 24942.6852 | 1.7073 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7697 | PARADISE 1103143744 | 102831103 | PARADISE 1103 | 1.0604 | 13 | 0.00033981 | 0.0044176 | 2784 | 24943.7456 | 1.7029 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4615 | PEORIA 170184318 | 163781701 | PEORIA 1701 | 10.2462 | 142 | 0.00033804 | 0.048002 | 2785 | 24953.9917 | 1.6549 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8175 | WEST POINT 1101L1969 | 163201101 | WEST POINT 1101 | 1.0992 | 16 | 0.00032448 | 0.0051917 | 2786 | 24955.0909 | 1.6497 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2671 | LOS GATOS 1101LB40 | 82021101 | LOS GATOS 1101 | 8.5234 | 131 | 0.00032354 | 0.042384 | 2787 | 24963.6143 | 1.6073 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1669 | SPRING GAP 17029690 | 162831702 | SPRING GAP 1702 | 17.3503 | 185 | 0.00031402 | 0.058094 | 2788 | 24980.9646 | 1.5492 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1740 | GUALALA 1111402866 | 42841111 | GUALALA 1111 | 1.5913 | 20 | 0.0003137 | 0.0062739 | 2789 | 24982.5559 | 1.5429 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6457 | ATASCADERO 1103CB | 182541103 | ATASCADERO 1103 | 0.18914 | 18 | 0.00031227 | 0.0056208 | 2790 | 24982.745 | 1.5373 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4913 | SAN LUIS OBISPO 1108CB | 182631108 | SAN LUIS OBISPO 1108 | 0.0063814 | 69 | 0.00031202 | 0.02153 | 2791 | 24982.7514 | 1.5158 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3199 | EL CERRITO G 1105BR160 | 12501105 | EL CERRITO G 1105 | 8.3249 | 132 | 0.00031068 | 0.04101 | 2792 | 24991.0763 | 1.4748 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7182 | EEL RIVER 1102720639 | 192381102 | EEL RIVER 1102 | 1.6537 | 25 | 0.0003062 | 0.0076549 | 2793 | 24992.73 | 1.4671 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6389 | PERRY 1101W10 | 183071101 | PERRY 1101 | 1.4636 | 29 | 0.00030601 | 0.0088744 | 2794 | 24994.1936 | 1.4582 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5102 | DEL MONTE 21049096 | 182222104 | DEL MONTE 2104 | 3.2966 | 78 | 0.00030601 | 0.023869 | 2795 | 24997.4902 | 1.4344 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
483 | EL CERRITO G 1105CB | 12501105 | EL CERRITO G 1105 | 7.4474 | 97 | 0.00030421 | 0.029509 | 2796 | 25004.9376 | 1.4049 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8801 | WOODSIDE 1104420146 | 24251104 | WOODSIDE 1104 | 2.728 | 43 | 0.00030412 | 0.013077 | 2797 | 25007.6656 | 1.3918 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2740 | SUNOL 1101MR650 | 14241101 | SUNOL 1101 | 1.2969 | 30 | 0.00029523 | 0.0088568 | 2798 | 25008.9624 | 1.3829 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1558 | RINCON 1103472 | 43321103 | RINCON 1103 | 3.0645 | 71 | 0.00029462 | 0.020918 | 2799 | 25012.027 | 1.362 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1849 | FORT BRAGG A 11044690 | 42761104 | FORT BRAGG A 1104 | 11.6289 | 161 | 0.00029439 | 0.047396 | 2800 | 25023.6558 | 1.3146 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1214 | ROB ROY 21055166 | 83692105 | ROB ROY 2105 | 5.4945 | 81 | 0.00028991 | 0.023482 | 2801 | 25029.1503 | 1.2911 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6981 | HALF MOON BAY 110148868 | 24101101 | HALF MOON BAY 1101 | 0 | 21 | 0.00028316 | 0.0059463 | 2802 | 25029.1503 | 1.2852 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5899 | VOLTA 11011640 | 102541101 | VOLTA 1101 | 10.4439 | 59 | 0.00028287 | 0.016689 | 2803 | 25039.5941 | 1.2685 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7108 | RESERVATION ROAD 11023032 | 182731102 | RESERVATION ROAD 1102 | 3.6042 | 84 | 0.00028141 | 0.023638 | 2804 | 25043.1984 | 1.2449 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5988 | SPRING GAP 1702693441 | 162831702 | SPRING GAP 1702 | 4.2634 | 59 | 0.00027928 | 0.016478 | 2805 | 25047.4618 | 1.2284 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5979 | BIG RIVER 11012183 | 43081101 | BIG RIVER 1101 | 2.6394 | 33 | 0.00027436 | 0.009054 | 2806 | 25050.1012 | 1.2193 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
760 | BIG RIVER 1101952 | 43081101 | BIG RIVER 1101 | 10.1564 | 130 | 0.00027431 | 0.03566 | 2807 | 25060.2576 | 1.1837 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1378 | PARADISE 1105CB | 102831105 | PARADISE 1105 | 6.1048 | 86 | 0.00026897 | 0.023131 | 2808 | 25066.3624 | 1.1605 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4711 | RESEARCH 2102446423 | 14692102 | RESEARCH 2102 | 0.70566 | 23 | 0.00026534 | 0.0061027 | 2809 | 25067.0681 | 1.1544 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
534 | STANISLAUS 170237278 | 162821702 | STANISLAUS 1702 | 6.7927 | 99 | 0.00026318 | 0.026055 | 2810 | 25073.8608 | 1.1284 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
956 | PAUL SWEET 2106CB | 83252106 | PAUL SWEET 2106 | 5.2845 | 115 | 0.00025895 | 0.029779 | 2811 | 25079.1453 | 1.0986 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
832 | ROSSMOOR 110168920 | 14161101 | ROSSMOOR 1101 | 6.4273 | 91 | 0.0002577 | 0.02345 | 2812 | 25085.5726 | 1.0751 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5459 | PARADISE 1106CB | 102831106 | PARADISE 1106 | 4.6443 | 53 | 0.0002457 | 0.013022 | 2813 | 25090.2169 | 1.0621 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8168 | SAUSALITO 1102410 | 42491102 | SAUSALITO 1102 | 1.5556 | 28 | 0.00024476 | 0.0068532 | 2814 | 25091.7724 | 1.0553 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2941 | DIAMOND SPRINGS 1103CB | 152261103 | DIAMOND SPRINGS 1103 | 0.55038 | 109 | 0.00024231 | 0.026412 | 2815 | 25092.3228 | 1.0289 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5531 | MAPLE CREEK 1101CB | 192101101 | MAPLE CREEK 1101 | 8.8674 | 60 | 0.00023784 | 0.01427 | 2816 | 25101.1902 | 1.0146 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6907 | BRUNSWICK 111063100 | 152481110 | BRUNSWICK 1110 | 4.0969 | 55 | 0.00023675 | 0.013021 | 2817 | 25105.2871 | 1.0016 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2877 | MONTE RIO 11111701 | 42811111 | MONTE RIO 1111 | 1.3978 | 18 | 0.00023556 | 0.0042401 | 2818 | 25106.6849 | 0.99733 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6347 | PACIFICA 11015001 | 22811101 | PACIFICA 1101 | 0 | 25 | 0.00023403 | 0.0058507 | 2819 | 25106.6849 | 0.99148 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1625 | SAN LUIS OBISPO 1105CB | 182631105 | SAN LUIS OBISPO 1105 | 0.041946 | 43 | 0.000232 | 0.0099759 | 2820 | 25106.7268 | 0.9815 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5409 | SAN RAFAEL 1108CB | 42011108 | SAN RAFAEL 1108 | 5.8855 | 102 | 0.00023023 | 0.023483 | 2821 | 25112.6123 | 0.95802 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8271 | ROSSMOOR 1107857172 | 14161107 | ROSSMOOR 1107 | 0.094493 | 15 | 0.00022992 | 0.0034488 | 2822 | 25112.7068 | 0.95457 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10147 | WINDSOR 11035060 | 43501103 | WINDSOR 1103 | 0.18121 | 12 | 0.00022663 | 0.0027196 | 2823 | 25112.888 | 0.95185 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8566 | CORONA 1103114284 | 43491103 | CORONA 1103 | 0.28075 | 11 | 0.00022547 | 0.0024802 | 2824 | 25113.1688 | 0.94937 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
849 | STANISLAUS 170237276 | 162821702 | STANISLAUS 1702 | 11.651 | 168 | 0.00022047 | 0.037039 | 2825 | 25124.8198 | 0.91233 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3868 | HATTON 11012026 | 182291101 | HATTON 1101 | 5.2447 | 126 | 0.00021753 | 0.027409 | 2826 | 25130.0646 | 0.88492 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
427 | SAUSALITO 1101688590 | 42491101 | SAUSALITO 1101 | 1.0513 | 32 | 0.00021706 | 0.0069459 | 2827 | 25131.1158 | 0.87798 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4476 | CALISTOGA 1102705 | 42711102 | CALISTOGA 1102 | 0.38677 | 20 | 0.00021298 | 0.0042596 | 2828 | 25131.5026 | 0.87372 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1205 | MIWUK 17028090 | 163661702 | MIWUK 1702 | 4.0407 | 53 | 0.00021162 | 0.011216 | 2829 | 25135.5433 | 0.8625 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
61 | CAMBRIA 1102W50 | 182771102 | CAMBRIA 1102 | 0.62023 | 40 | 0.00021093 | 0.0084371 | 2830 | 25136.1636 | 0.85406 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
189 | BIG RIVER 110179628 | 43081101 | BIG RIVER 1101 | 14.8005 | 156 | 0.00021051 | 0.032839 | 2831 | 25150.964 | 0.82123 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3166 | ALTO 11251226 | 42031125 | ALTO 1125 | 7.6339 | 96 | 0.00020916 | 0.02008 | 2832 | 25158.598 | 0.80115 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6809 | OAKLAND D 1112CR192 | 12041112 | OAKLAND D 1112 | 2.463 | 54 | 0.00020828 | 0.011247 | 2833 | 25161.061 | 0.7899 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4374 | OCEANO 1103V22 | 182601103 | OCEANO 1103 | 0.031381 | 14 | 0.00020377 | 0.0028528 | 2834 | 25161.0924 | 0.78705 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9957 | DEL MONTE 21043066 | 182222104 | DEL MONTE 2104 | 0.016181 | 2 | 0.00020359 | 0.00040718 | 2835 | 25161.1086 | 0.78664 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4818 | ROSSMOOR 11018132 | 14161101 | ROSSMOOR 1101 | 2.6402 | 47 | 0.00020337 | 0.0095582 | 2836 | 25163.7487 | 0.77708 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2856 | SAN RAFAEL 11071166 | 42011107 | SAN RAFAEL 1107 | 12.5314 | 213 | 0.00020294 | 0.043227 | 2837 | 25176.2802 | 0.73385 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
445 | MONTE RIO 1112CB | 42811112 | MONTE RIO 1112 | 3.5299 | 43 | 0.00020121 | 0.0086519 | 2838 | 25179.8101 | 0.7252 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10280 | SAUSALITO 1102964592 | 42491102 | SAUSALITO 1102 | 0.58542 | 15 | 0.00019824 | 0.0029736 | 2839 | 25180.3955 | 0.72223 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1145 | OLEMA 11011200 | 42291101 | OLEMA 1101 | 2.8955 | 34 | 0.00019566 | 0.0066525 | 2840 | 25183.291 | 0.71558 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6437 | HAMILTON BRANCH 110153192 | 102361101 | HAMILTON BRANCH 1101 | 0.55299 | 30 | 0.0001937 | 0.0058109 | 2841 | 25183.844 | 0.70976 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7381 | PACIFICA 1102660408 | 22811102 | PACIFICA 1102 | 0.35468 | 26 | 0.00019086 | 0.0049624 | 2842 | 25184.1987 | 0.7048 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5360 | ALHAMBRA 1105CB | 14101105 | ALHAMBRA 1105 | 0.82879 | 33 | 0.00018865 | 0.0062254 | 2843 | 25185.0275 | 0.69858 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1909 | MORAGA 1104750618 | 13801104 | MORAGA 1104 | 0.95612 | 13 | 0.0001837 | 0.002388 | 2844 | 25185.9836 | 0.69619 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7663 | SOBRANTE 1103CB | 14671103 | SOBRANTE 1103 | 4.1925 | 55 | 0.00018024 | 0.0099135 | 2845 | 25190.1761 | 0.68627 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4846 | ORINDA 0402402/2 LR | 12350402 | ORINDA 0402 | 6.554 | 91 | 0.00017917 | 0.016305 | 2846 | 25196.7301 | 0.66997 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6268 | CURTIS 1702S2123 | 163351702 | CURTIS 1702 | 1.8577 | 25 | 0.00017177 | 0.0042941 | 2847 | 25198.5878 | 0.66568 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1067 | DIAMOND SPRINGS 1106290705 | 152261106 | DIAMOND SPRINGS 1106 | 3.2275 | 38 | 0.00016712 | 0.0063506 | 2848 | 25201.8153 | 0.65933 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3874 | PARADISE 1105829194 | 102831105 | PARADISE 1105 | 11.2644 | 142 | 0.00016422 | 0.023319 | 2849 | 25213.0797 | 0.63601 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1686 | CAMP EVERS 210312990 | 83622103 | CAMP EVERS 2103 | 13.2243 | 161 | 0.00016127 | 0.025964 | 2850 | 25226.304 | 0.61004 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6595 | HIGGINS 110432747 | 152691104 | HIGGINS 1104 | 0.65102 | 26 | 0.00016086 | 0.0041824 | 2851 | 25226.955 | 0.60586 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2910 | HALSEY 110176178 | 152241101 | HALSEY 1101 | 20.219 | 248 | 0.00015934 | 0.039517 | 2852 | 25247.174 | 0.56634 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2602 | PRUNEDALE 11103716 | 182961110 | PRUNEDALE 1110 | 0.42929 | 157 | 0.00015488 | 0.024316 | 2853 | 25247.6033 | 0.54203 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6371 | BAY MEADOWS 210257886 | 24012102 | BAY MEADOWS 2102 | 4.0705 | 81 | 0.00015101 | 0.012232 | 2854 | 25251.6738 | 0.52979 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3718 | TEMPLETON 2108A40 | 183052108 | TEMPLETON 2108 | 3.7814 | 174 | 0.00015079 | 0.026237 | 2855 | 25255.4552 | 0.50356 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8208 | BRUNSWICK 11038918 | 152481103 | BRUNSWICK 1103 | 1.5109 | 30 | 0.0001494 | 0.0044819 | 2856 | 25256.9661 | 0.49908 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
833 | BRUNSWICK 110456468 | 152481104 | BRUNSWICK 1104 | 5.538 | 85 | 0.0001483 | 0.012606 | 2857 | 25262.5041 | 0.48647 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8651 | MORGAN HILL 2111419718 | 83242111 | MORGAN HILL 2111 | 2.2684 | 25 | 0.0001469 | 0.0036725 | 2858 | 25264.7725 | 0.4828 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4060 | KONOCTI 11081278 | 43311108 | KONOCTI 1108 | 5.6556 | 96 | 0.00014529 | 0.013948 | 2859 | 25270.4281 | 0.46885 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5993 | LAS GALLINAS A 11041220 | 42991104 | LAS GALLINAS A 1104 | 0 | 57 | 0.00013353 | 0.0076113 | 2860 | 25270.4281 | 0.46124 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1481 | SOBRANTE 1101CB | 14671101 | SOBRANTE 1101 | 14.2302 | 209 | 0.00012965 | 0.027098 | 2861 | 25284.6583 | 0.43414 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6330 | CURTIS 170268380 | 163351702 | CURTIS 1702 | 6.6575 | 88 | 0.00012865 | 0.011322 | 2862 | 25291.3158 | 0.42282 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2410 | SAN LEANDRO U 1114MR544 | 13111114 | SAN LEANDRO U 1114 | 0.017391 | 62 | 0.00012274 | 0.0076101 | 2863 | 25291.3332 | 0.41521 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5853 | ROB ROY 210410954 | 83692104 | ROB ROY 2104 | 7.103 | 90 | 0.00012262 | 0.011036 | 2864 | 25298.4363 | 0.40417 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4344 | NOVATO 11041282 | 42211104 | NOVATO 1104 | 0 | 56 | 0.00012029 | 0.0067363 | 2865 | 25298.4363 | 0.39744 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8432 | SNEATH LANE 110715341 | 22721107 | SNEATH LANE 1107 | 0.24318 | 18 | 0.00011859 | 0.0021346 | 2866 | 25298.6794 | 0.3953 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6986 | RESERVATION ROAD 1102303870 | 182731102 | RESERVATION ROAD 1102 | 0.63919 | 7 | 0.0001185 | 0.00082948 | 2867 | 25299.3186 | 0.39447 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4626 | COTATI 1104426 | 42271104 | COTATI 1104 | 2.0009 | 52 | 0.00011662 | 0.0060642 | 2868 | 25301.3196 | 0.38841 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8778 | PAUL SWEET 2107774760 | 83252107 | PAUL SWEET 2107 | 3.3243 | 37 | 0.00011197 | 0.0041429 | 2869 | 25304.6439 | 0.38427 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4484 | FROGTOWN 170274648 | 163451702 | FROGTOWN 1702 | 0.16296 | 63 | 0.00011106 | 0.0069966 | 2870 | 25304.8069 | 0.37727 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6192 | PEORIA 170169124 | 163781701 | PEORIA 1701 | 2.7019 | 33 | 0.00010917 | 0.0036026 | 2871 | 25307.5087 | 0.37367 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8000 | DIAMOND SPRINGS 1107116815 | 152261107 | DIAMOND SPRINGS 1107 | 1.5788 | 33 | 0.00010723 | 0.0035385 | 2872 | 25309.0875 | 0.37013 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8610 | HOOPA 110193038 | 192401101 | HOOPA 1101 | 1.3098 | 39 | 0.00010645 | 0.0041517 | 2873 | 25310.3973 | 0.36598 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
995 | HALF MOON BAY 11022032 | 24101102 | HALF MOON BAY 1102 | 0.56279 | 103 | 0.0001063 | 0.010949 | 2874 | 25310.9601 | 0.35503 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7250 | ORINDA 04013442 | 12350401 | ORINDA 0401 | 3.4803 | 68 | 0.00010618 | 0.0072205 | 2875 | 25314.4404 | 0.34781 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
367 | ARCATA 112233060 | 192021122 | ARCATA 1122 | 0.53218 | 64 | 9.9531e-05 | 0.00637 | 2876 | 25314.9726 | 0.34144 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2545 | FAIRVIEW 2207P148 | 13432207 | FAIRVIEW 2207 | 0.84643 | 54 | 9.8792e-05 | 0.0053348 | 2877 | 25315.819 | 0.3361 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5688 | STANISLAUS 170275348 | 162821702 | STANISLAUS 1702 | 5.3029 | 77 | 9.5481e-05 | 0.0073521 | 2878 | 25321.122 | 0.32875 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5946 | SALT SPRINGS 21011232 | 163692101 | SALT SPRINGS 2101 | 7.7196 | 64 | 9.0864e-05 | 0.0058153 | 2879 | 25328.8415 | 0.32293 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4735 | ELK 11018779 | 42981101 | ELK 1101 | 4.2669 | 41 | 8.9792e-05 | 0.0036815 | 2880 | 25333.1084 | 0.31925 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
744 | GABILAN 11013034 | 182331101 | GABILAN 1101 | 0.04993 | 193 | 8.716e-05 | 0.016822 | 2881 | 25333.1583 | 0.30243 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8975 | SPRING GAP 170286032 | 162831702 | SPRING GAP 1702 | 1.0042 | 23 | 8.538e-05 | 0.0019637 | 2882 | 25334.1625 | 0.30047 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6252 | CHESTER 1101922138 | 103181101 | CHESTER 1101 | 1.5691 | 24 | 8.4169e-05 | 0.00202 | 2883 | 25335.7316 | 0.29845 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
320 | GREEN VALLEY 210112106 | 83192101 | GREEN VALLEY 2101 | 0.34608 | 139 | 8.0919e-05 | 0.011248 | 2884 | 25336.0776 | 0.2872 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
390 | PETALUMA C 110856774 | 42631108 | PETALUMA C 1108 | 0.23933 | 39 | 7.8722e-05 | 0.0030702 | 2885 | 25336.317 | 0.28413 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3580 | SOBRANTE 1102CB | 14671102 | SOBRANTE 1102 | 10.4408 | 132 | 7.4597e-05 | 0.0098468 | 2886 | 25346.7578 | 0.27428 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5433 | HATTON 110137088 | 182291101 | HATTON 1101 | 7.1066 | 135 | 7.338e-05 | 0.0099063 | 2887 | 25353.8644 | 0.26438 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2226 | FORT BRAGG A 11021226 | 42761102 | FORT BRAGG A 1102 | 1.6891 | 102 | 7.0366e-05 | 0.0071773 | 2888 | 25355.5535 | 0.2572 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7611 | DIAMOND SPRINGS 1106279670 | 152261106 | DIAMOND SPRINGS 1106 | 3.8807 | 54 | 7.0093e-05 | 0.003785 | 2889 | 25359.4342 | 0.25341 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9967 | CRESTA 1101103126 | 102251101 | CRESTA 1101 | 0.30269 | 5 | 6.9083e-05 | 0.00034541 | 2890 | 25359.7369 | 0.25307 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6701 | BRUNSWICK 11064639 | 152481106 | BRUNSWICK 1106 | 3.2493 | 44 | 6.7888e-05 | 0.0029871 | 2891 | 25362.9862 | 0.25008 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8130 | LAURELES 111110141 | 182371111 | LAURELES 1111 | 2.9178 | 21 | 6.784e-05 | 0.0014246 | 2892 | 25365.9041 | 0.24866 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
17 | SAN RAFAEL 1106910 | 42011106 | SAN RAFAEL 1106 | 1.6921 | 89 | 6.6955e-05 | 0.005959 | 2893 | 25367.5962 | 0.2427 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
428 | SOBRANTE 1102690098 | 14671102 | SOBRANTE 1102 | 7.3859 | 108 | 6.6684e-05 | 0.0072019 | 2894 | 25374.9821 | 0.2355 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6532 | PARADISE 110536656 | 102831105 | PARADISE 1105 | 0.13723 | 14 | 6.4706e-05 | 0.00090588 | 2895 | 25375.1194 | 0.23459 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1066 | JARVIS 1101MR210 | 13501101 | JARVIS 1101 | 0.81682 | 103 | 6.2939e-05 | 0.0064828 | 2896 | 25375.9362 | 0.22811 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5877 | OAKLAND K 1102CR014 | 12101102 | OAKLAND K 1102 | 10.5071 | 137 | 6.2366e-05 | 0.0085442 | 2897 | 25386.4432 | 0.21956 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7339 | BIG BASIN 110165444 | 82841101 | BIG BASIN 1101 | 0.47064 | 9 | 6.0572e-05 | 0.00054514 | 2898 | 25386.9139 | 0.21902 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1476 | BOLINAS 1101528 | 42261101 | BOLINAS 1101 | 1.7811 | 46 | 5.4065e-05 | 0.002487 | 2899 | 25388.695 | 0.21653 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9601 | CAMP EVERS 2104189010 | 83622104 | CAMP EVERS 2104 | 0.036695 | 4 | 5.2348e-05 | 0.00020939 | 2900 | 25388.7317 | 0.21632 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4401 | SILVERADO 2103507513 | 43432103 | SILVERADO 2103 | 2.9853 | 65 | 4.9269e-05 | 0.0032025 | 2901 | 25391.717 | 0.21312 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
625 | ROSSMOOR 1101L503R | 14161101 | ROSSMOOR 1101 | 4.2951 | 62 | 4.8731e-05 | 0.0030213 | 2902 | 25396.0121 | 0.2101 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7021 | DOLAN ROAD 1101590402 | 182381101 | DOLAN ROAD 1101 | 2.4338 | 78 | 4.8446e-05 | 0.0037788 | 2903 | 25398.4459 | 0.20632 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7515 | PARADISE 1103468200 | 102831103 | PARADISE 1103 | 0.33044 | 4 | 4.8111e-05 | 0.00019244 | 2904 | 25398.7764 | 0.20613 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8899 | NAPA 11025039 | 42021102 | NAPA 1102 | 0 | 28 | 4.5334e-05 | 0.0012694 | 2905 | 25398.7764 | 0.20486 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10522 | PARADISE 11042486 | 102831104 | PARADISE 1104 | 0.091002 | 2 | 4.4268e-05 | 8.8537e-05 | 2906 | 25398.8674 | 0.20477 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
11006 | PARADISE 1105828400 | 102831105 | PARADISE 1105 | 0.031143 | 2 | 4.4154e-05 | 8.8308e-05 | 2907 | 25398.8985 | 0.20468 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10495 | CEDAR CREEK 11011362 | 103321101 | CEDAR CREEK 1101 | 0.015507 | 1 | 4.3827e-05 | 4.3827e-05 | 2908 | 25398.914 | 0.20464 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4622 | EL CERRITO G 1105BR194 | 12501105 | EL CERRITO G 1105 | 3.8214 | 74 | 4.3185e-05 | 0.0031957 | 2909 | 25402.7355 | 0.20144 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7319 | PARADISE 11061212 | 102831106 | PARADISE 1106 | 2.0091 | 33 | 4.2503e-05 | 0.0014026 | 2910 | 25404.7445 | 0.20004 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10489 | CAMP EVERS 210510996 | 83622105 | CAMP EVERS 2105 | 0.76209 | 8 | 4.2365e-05 | 0.00033892 | 2911 | 25405.5066 | 0.1997 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7716 | PARADISE 110599226 | 102831105 | PARADISE 1105 | 1.1447 | 42 | 4.1187e-05 | 0.0017299 | 2912 | 25406.6514 | 0.19797 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6446 | FORT BRAGG A 1102956 | 42761102 | FORT BRAGG A 1102 | 11.3603 | 145 | 4.0908e-05 | 0.0059316 | 2913 | 25418.0117 | 0.19204 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2257 | BIG TREES 04025300 | 83050402 | BIG TREES 0402 | 9.7951 | 115 | 3.9714e-05 | 0.0045672 | 2914 | 25427.8068 | 0.18747 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9775 | CAMP EVERS 210595050 | 83622105 | CAMP EVERS 2105 | 0.13873 | 5 | 3.9532e-05 | 0.00019766 | 2915 | 25427.9455 | 0.18727 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2020 | DUNLAP 11037170 | 254061103 | DUNLAP 1103 | 5.4237 | 54 | 3.9493e-05 | 0.0021326 | 2916 | 25433.3692 | 0.18514 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9147 | BEN LOMOND 04015400 | 83040401 | BEN LOMOND 0401 | 0.45458 | 4 | 3.9445e-05 | 0.00015778 | 2917 | 25433.8238 | 0.18498 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2924 | ROB ROY 210538430 | 83692105 | ROB ROY 2105 | 3.7665 | 90 | 3.7768e-05 | 0.0033991 | 2918 | 25437.5903 | 0.18158 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2345 | MORGAN HILL 2106CB | 83242106 | MORGAN HILL 2106 | 0.62349 | 47 | 3.5184e-05 | 0.0016536 | 2919 | 25438.2138 | 0.17993 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4552 | SHINGLE SPRINGS 2108449638 | 153652108 | SHINGLE SPRINGS 2108 | 0.026093 | 1 | 3.5151e-05 | 3.5151e-05 | 2920 | 25438.2399 | 0.17989 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2359 | PACIFICA 1101777484 | 22811101 | PACIFICA 1101 | 0.90431 | 50 | 3.5066e-05 | 0.0017533 | 2921 | 25439.1442 | 0.17814 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6715 | PARADISE 11032534 | 102831103 | PARADISE 1103 | 3.1733 | 49 | 3.3375e-05 | 0.0016354 | 2922 | 25442.3175 | 0.17651 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
416 | PACIFICA 1102CB | 22811102 | PACIFICA 1102 | 0.34812 | 51 | 3.2507e-05 | 0.0016578 | 2923 | 25442.6657 | 0.17485 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4774 | PARADISE 11042488 | 102831104 | PARADISE 1104 | 3.5364 | 47 | 3.2259e-05 | 0.0015162 | 2924 | 25446.2021 | 0.17333 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10872 | WILLOW CREEK 1103181562 | 192171103 | WILLOW CREEK 1103 | 0.0028415 | 1 | 3.208e-05 | 3.208e-05 | 2925 | 25446.2049 | 0.1733 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5198 | PARADISE 1104283794 | 102831104 | PARADISE 1104 | 2.3684 | 37 | 3.2004e-05 | 0.0011841 | 2926 | 25448.5733 | 0.17212 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2421 | FORT BRAGG A 110235592 | 42761102 | FORT BRAGG A 1102 | 13.1322 | 149 | 3.1961e-05 | 0.0047622 | 2927 | 25461.7055 | 0.16735 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6748 | BRUNSWICK 11103907 | 152481110 | BRUNSWICK 1110 | 0.89367 | 16 | 3.1747e-05 | 0.00050795 | 2928 | 25462.5991 | 0.16685 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1323 | PEORIA 17013186 | 163781701 | PEORIA 1701 | 9.8236 | 143 | 3.1551e-05 | 0.0045118 | 2929 | 25472.4227 | 0.16233 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6182 | BERESFORD 0403435168 | 24040403 | BERESFORD 0403 | 1.2855 | 26 | 3.1131e-05 | 0.00080941 | 2930 | 25473.7082 | 0.16152 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8329 | BRUNSWICK 1104244027 | 152481104 | BRUNSWICK 1104 | 0.30625 | 6 | 3.093e-05 | 0.00018558 | 2931 | 25474.0145 | 0.16134 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10464 | CAMP EVERS 210595394 | 83622105 | CAMP EVERS 2105 | 0.49123 | 8 | 3.0854e-05 | 0.00024683 | 2932 | 25474.5057 | 0.16109 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4342 | PARADISE 110636042 | 102831106 | PARADISE 1106 | 8.1942 | 119 | 3.0817e-05 | 0.0036673 | 2933 | 25482.7 | 0.15742 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9818 | ANDERSON 1101561686 | 103261101 | ANDERSON 1101 | 0.091487 | 1 | 2.9674e-05 | 2.9674e-05 | 2934 | 25482.7914 | 0.1574 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2309 | BEN LOMOND 040116010 | 83040401 | BEN LOMOND 0401 | 1.696 | 25 | 2.9564e-05 | 0.00073909 | 2935 | 25484.4875 | 0.15666 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2259 | LAKEWOOD 210738404 | 13532107 | LAKEWOOD 2107 | 3.5616 | 47 | 2.9507e-05 | 0.0013868 | 2936 | 25488.0491 | 0.15527 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6756 | FAIRMOUNT 0401395180 | 12650401 | FAIRMOUNT 0401 | 1.407 | 20 | 2.9412e-05 | 0.00058824 | 2937 | 25489.4561 | 0.15468 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9891 | RIO DELL 1102214052 | 192251102 | RIO DELL 1102 | 0.58493 | 7 | 2.933e-05 | 0.00020531 | 2938 | 25490.041 | 0.15448 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9611 | DIAMOND SPRINGS 1106176130 | 152261106 | DIAMOND SPRINGS 1106 | 0.019934 | 1 | 2.9315e-05 | 2.9315e-05 | 2939 | 25490.0609 | 0.15445 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9648 | CAMP EVERS 2103CB | 83622103 | CAMP EVERS 2103 | 0.11832 | 6 | 2.9049e-05 | 0.00017429 | 2940 | 25490.1793 | 0.15427 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7669 | PARADISE 1104CB | 102831104 | PARADISE 1104 | 1.3747 | 46 | 2.9018e-05 | 0.0013348 | 2941 | 25491.5539 | 0.15294 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8116 | BRUNSWICK 1107969778 | 152481107 | BRUNSWICK 1107 | 0.66562 | 9 | 2.8554e-05 | 0.00025699 | 2942 | 25492.2196 | 0.15268 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1751 | PARADISE 1104954322 | 102831104 | PARADISE 1104 | 4.3027 | 63 | 2.8353e-05 | 0.0017862 | 2943 | 25496.5223 | 0.15089 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6559 | BIG BASIN 11015479 | 82841101 | BIG BASIN 1101 | 0.17979 | 3 | 2.7773e-05 | 8.3319e-05 | 2944 | 25496.7021 | 0.15081 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
11110 | CAMP EVERS 2105BL 2101 | 83622105 | CAMP EVERS 2105 | 0.0032262 | 1 | 2.7401e-05 | 2.7401e-05 | 2945 | 25496.7053 | 0.15078 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7068 | BURNS 2101CB | 183582101 | BURNS 2101 | 1.7044 | 19 | 2.7081e-05 | 0.00051453 | 2946 | 25498.4097 | 0.15027 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10401 | POINT MORETTI 110110722 | 82931101 | POINT MORETTI 1101 | 0.58294 | 9 | 2.6688e-05 | 0.00024019 | 2947 | 25498.9926 | 0.15003 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2162 | SOBRANTE 1102L510R | 14671102 | SOBRANTE 1102 | 9.6575 | 136 | 2.6158e-05 | 0.0035575 | 2948 | 25508.6501 | 0.14647 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8264 | MIRABEL 1101781318 | 42091101 | MIRABEL 1101 | 0.10698 | 3 | 2.5377e-05 | 7.6132e-05 | 2949 | 25508.7571 | 0.14639 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2959 | PARADISE 110453544 | 102831104 | PARADISE 1104 | 0.64333 | 19 | 2.5314e-05 | 0.00048097 | 2950 | 25509.4004 | 0.14591 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2047 | VALLEY VIEW 1103CB | 14341103 | VALLEY VIEW 1103 | 0.16939 | 83 | 2.5206e-05 | 0.0020921 | 2951 | 25509.5698 | 0.14382 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3341 | CAMP EVERS 21055146 | 83622105 | CAMP EVERS 2105 | 5.9259 | 63 | 2.4561e-05 | 0.0015473 | 2952 | 25515.4957 | 0.14227 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4945 | CASTRO VALLEY 1102837904 | 14091102 | CASTRO VALLEY 1102 | 1.0374 | 25 | 2.4435e-05 | 0.00061089 | 2953 | 25516.5331 | 0.14166 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5852 | PARADISE 1104961990 | 102831104 | PARADISE 1104 | 6.8193 | 91 | 2.3677e-05 | 0.0021547 | 2954 | 25523.3524 | 0.13951 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8958 | PARADISE 1103772517 | 102831103 | PARADISE 1103 | 1.7261 | 24 | 2.3519e-05 | 0.00056446 | 2955 | 25525.0785 | 0.13894 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5973 | BEN LOMOND 0401CB | 83040401 | BEN LOMOND 0401 | 7.7747 | 106 | 2.3026e-05 | 0.0024408 | 2956 | 25532.8532 | 0.1365 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10776 | GRASS VALLEY 1101528232 | 152031101 | GRASS VALLEY 1101 | 0.093008 | 2 | 2.2245e-05 | 4.449e-05 | 2957 | 25532.9462 | 0.13646 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10760 | FLINT 1102CB | 152531102 | FLINT 1102 | 0.092864 | 2 | 2.218e-05 | 4.436e-05 | 2958 | 25533.0391 | 0.13641 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3909 | MORRO BAY 1102V84 | 183011102 | MORRO BAY 1102 | 0.22982 | 126 | 2.1832e-05 | 0.0027508 | 2959 | 25533.2689 | 0.13366 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7549 | PLACERVILLE 1111CB | 153081111 | PLACERVILLE 1111 | 1.3954 | 16 | 2.1827e-05 | 0.00034924 | 2960 | 25534.6644 | 0.13331 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6107 | POINT MORETTI 110139126 | 82931101 | POINT MORETTI 1101 | 2.259 | 31 | 2.101e-05 | 0.00065131 | 2961 | 25536.9234 | 0.13266 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9485 | CAMP EVERS 2106834583 | 83622106 | CAMP EVERS 2106 | 0.60972 | 7 | 1.9977e-05 | 0.00013984 | 2962 | 25537.5331 | 0.13252 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6136 | BIG TREES 0402737512 | 83050402 | BIG TREES 0402 | 6.7852 | 89 | 1.9465e-05 | 0.0017324 | 2963 | 25544.3183 | 0.13079 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
940 | CAMP EVERS 210511384 | 83622105 | CAMP EVERS 2105 | 5.2222 | 59 | 1.9223e-05 | 0.0011342 | 2964 | 25549.5405 | 0.12966 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8260 | DIAMOND SPRINGS 1106762780 | 152261106 | DIAMOND SPRINGS 1106 | 0.24908 | 11 | 1.9222e-05 | 0.00021145 | 2965 | 25549.7896 | 0.12945 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9711 | BRUNSWICK 1103262343 | 152481103 | BRUNSWICK 1103 | 0.76623 | 11 | 1.9193e-05 | 0.00021112 | 2966 | 25550.5558 | 0.12923 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6422 | BIG BASIN 11029741 | 82841102 | BIG BASIN 1102 | 0.64417 | 10 | 1.8794e-05 | 0.00018794 | 2967 | 25551.2 | 0.12905 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
471 | BIG BASIN 11015028 | 82841101 | BIG BASIN 1101 | 5.0266 | 59 | 1.8516e-05 | 0.0010925 | 2968 | 25556.2265 | 0.12795 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5836 | BRUNSWICK 1103851116 | 152481103 | BRUNSWICK 1103 | 0.1964 | 4 | 1.8459e-05 | 7.3835e-05 | 2969 | 25556.4229 | 0.12788 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10320 | DIAMOND SPRINGS 1106926235 | 152261106 | DIAMOND SPRINGS 1106 | 0.18979 | 4 | 1.8372e-05 | 7.3487e-05 | 2970 | 25556.6127 | 0.12781 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10026 | SARATOGA 1103981056 | 83371103 | SARATOGA 1103 | 0.082049 | 2 | 1.8259e-05 | 3.6518e-05 | 2971 | 25556.6948 | 0.12777 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7034 | DIAMOND SPRINGS 110699658 | 152261106 | DIAMOND SPRINGS 1106 | 0 | 39 | 1.8228e-05 | 0.0007109 | 2972 | 25556.6948 | 0.12706 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4269 | BRUNSWICK 110378862 | 152481103 | BRUNSWICK 1103 | 0.076823 | 17 | 1.8213e-05 | 0.00030962 | 2973 | 25556.7716 | 0.12675 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3650 | ROB ROY 210512584 | 83692105 | ROB ROY 2105 | 3.5122 | 297 | 1.8188e-05 | 0.0054019 | 2974 | 25560.2838 | 0.12135 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2640 | PERRY 1101V72 | 183071101 | PERRY 1101 | 5.9727 | 101 | 1.8115e-05 | 0.0018297 | 2975 | 25566.2565 | 0.11952 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7574 | CAMP EVERS 210611006 | 83622106 | CAMP EVERS 2106 | 2.0392 | 24 | 1.8001e-05 | 0.00043202 | 2976 | 25568.2957 | 0.11909 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10111 | ALLEGHANY 11011101/2 | 152101101 | ALLEGHANY 1101 | 0.020437 | 1 | 1.7836e-05 | 1.7836e-05 | 2977 | 25568.3161 | 0.11907 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7350 | SUMMIT 1101CB | 152591101 | SUMMIT 1101 | 0.1374 | 2 | 1.7744e-05 | 3.5488e-05 | 2978 | 25568.4535 | 0.11903 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10523 | CAMP EVERS 2104710556 | 83622104 | CAMP EVERS 2104 | 0.040934 | 2 | 1.7662e-05 | 3.5324e-05 | 2979 | 25568.4944 | 0.119 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5707 | FLINT 1101958726 | 152531101 | FLINT 1101 | 0.9978 | 13 | 1.7619e-05 | 0.00022904 | 2980 | 25569.4922 | 0.11877 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8628 | POINT MORETTI 11015401 | 82931101 | POINT MORETTI 1101 | 2.5155 | 34 | 1.7505e-05 | 0.00059516 | 2981 | 25572.0078 | 0.11817 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10455 | POTTER VALLEY P H 1104CB | 42281104 | POTTER VALLEY P H 1104 | 0.098474 | 2 | 1.7411e-05 | 3.4822e-05 | 2982 | 25572.1063 | 0.11814 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1795 | BOLINAS 11011064 | 42261101 | BOLINAS 1101 | 0.62485 | 51 | 1.7391e-05 | 0.00088693 | 2983 | 25572.7311 | 0.11725 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
11067 | BRUNSWICK 1104761310 | 152481104 | BRUNSWICK 1104 | 0.02679 | 1 | 1.7283e-05 | 1.7283e-05 | 2984 | 25572.7579 | 0.11723 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
130 | CAMP EVERS 21055232 | 83622105 | CAMP EVERS 2105 | 4.5152 | 50 | 1.7257e-05 | 0.00086284 | 2985 | 25577.2731 | 0.11637 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9051 | BRUNSWICK 1103956424 | 152481103 | BRUNSWICK 1103 | 1.0328 | 21 | 1.7224e-05 | 0.00036171 | 2986 | 25578.3059 | 0.11601 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7122 | CAMP EVERS 210510786 | 83622105 | CAMP EVERS 2105 | 4.5943 | 58 | 1.7083e-05 | 0.0009908 | 2987 | 25582.9002 | 0.11502 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7997 | CAMP EVERS 210411048 | 83622104 | CAMP EVERS 2104 | 0.91592 | 19 | 1.6894e-05 | 0.00032099 | 2988 | 25583.8161 | 0.1147 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10098 | RALSTON 1101100040 | 24141101 | RALSTON 1101 | 0.82301 | 7 | 1.6779e-05 | 0.00011745 | 2989 | 25584.6392 | 0.11458 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4770 | CAMP EVERS 210574170 | 83622105 | CAMP EVERS 2105 | 3.5755 | 43 | 1.6759e-05 | 0.00072063 | 2990 | 25588.2146 | 0.11386 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10059 | POTTER VALLEY P H 1105CB | 42281105 | POTTER VALLEY P H 1105 | 0.055533 | 2 | 1.6548e-05 | 3.3096e-05 | 2991 | 25588.2702 | 0.11383 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1470 | PLACERVILLE 210619732 | 153082106 | PLACERVILLE 2106 | 9.2596 | 125 | 1.6359e-05 | 0.0020448 | 2992 | 25597.5297 | 0.11178 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5865 | CAMP EVERS 210611044 | 83622106 | CAMP EVERS 2106 | 7.6394 | 144 | 1.6316e-05 | 0.0023496 | 2993 | 25605.1691 | 0.10943 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4584 | BRUNSWICK 1107357568 | 152481107 | BRUNSWICK 1107 | 1.1981 | 35 | 1.6214e-05 | 0.0005675 | 2994 | 25606.3672 | 0.10886 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4170 | SAN RAFAEL 11042651 | 42011104 | SAN RAFAEL 1104 | 0.76975 | 10 | 1.6143e-05 | 0.00016143 | 2995 | 25607.1369 | 0.1087 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4250 | SAN RAFAEL 1106837 | 42011106 | SAN RAFAEL 1106 | 0.67349 | 22 | 1.6143e-05 | 0.00035514 | 2996 | 25607.8104 | 0.10835 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8770 | MIRABEL 11027401 | 42091102 | MIRABEL 1102 | 1.0628 | 12 | 1.5859e-05 | 0.00019031 | 2997 | 25608.8732 | 0.10816 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5879 | BIG BASIN 11019773 | 82841101 | BIG BASIN 1101 | 0.4505 | 6 | 1.5808e-05 | 9.4849e-05 | 2998 | 25609.3237 | 0.10806 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4254 | BRUNSWICK 111095576 | 152481110 | BRUNSWICK 1110 | 0 | 30 | 1.5765e-05 | 0.00047296 | 2999 | 25609.3237 | 0.10759 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5644 | BRUNSWICK 1103234378 | 152481103 | BRUNSWICK 1103 | 0.6406 | 13 | 1.5727e-05 | 0.00020445 | 3000 | 25609.9643 | 0.10739 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
644 | CAMP EVERS 210511004 | 83622105 | CAMP EVERS 2105 | 4.3389 | 60 | 1.5545e-05 | 0.00093268 | 3001 | 25614.3032 | 0.10645 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10461 | GIRVAN 1102296428 | 103401102 | GIRVAN 1102 | 1.7207 | 14 | 1.5492e-05 | 0.00021689 | 3002 | 25616.0239 | 0.10624 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8135 | WOODSIDE 1101CB | 24251101 | WOODSIDE 1101 | 0 | 59 | 1.545e-05 | 0.00091153 | 3003 | 25616.0239 | 0.10532 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
555 | BRUNSWICK 110750008 | 152481107 | BRUNSWICK 1107 | 1.1366 | 64 | 1.5377e-05 | 0.0009841 | 3004 | 25617.1606 | 0.10434 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4851 | DIAMOND SPRINGS 1106910235 | 152261106 | DIAMOND SPRINGS 1106 | 0.52893 | 16 | 1.5283e-05 | 0.00024453 | 3005 | 25617.6895 | 0.1041 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
436 | SARATOGA 1107LC26 | 83371107 | SARATOGA 1107 | 5.6293 | 74 | 1.5103e-05 | 0.0011176 | 3006 | 25623.3188 | 0.10298 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3317 | PLACERVILLE 1110CB | 153081110 | PLACERVILLE 1110 | 0.86396 | 28 | 1.5035e-05 | 0.00042097 | 3007 | 25624.1827 | 0.10256 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4169 | GRASS VALLEY 1102CB | 152031102 | GRASS VALLEY 1102 | 0.081891 | 81 | 1.4894e-05 | 0.0012064 | 3008 | 25624.2646 | 0.10135 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1767 | MONTE RIO 111264682 | 42811112 | MONTE RIO 1112 | 1.762 | 22 | 1.4883e-05 | 0.00032742 | 3009 | 25626.0267 | 0.10102 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7374 | MIRABEL 1102841 | 42091102 | MIRABEL 1102 | 0.81233 | 12 | 1.4849e-05 | 0.00017819 | 3010 | 25626.839 | 0.10085 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9494 | SAN RAFAEL 1101546438 | 42011101 | SAN RAFAEL 1101 | 0.95798 | 14 | 1.4698e-05 | 0.00020577 | 3011 | 25627.797 | 0.10064 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7746 | SALT SPRINGS 21014913 | 163692101 | SALT SPRINGS 2101 | 3.7696 | 54 | 1.4645e-05 | 0.00079082 | 3012 | 25631.5666 | 0.099849 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7346 | OAKLAND K 1101CR346 | 12101101 | OAKLAND K 1101 | 0.20568 | 3 | 1.4607e-05 | 4.3821e-05 | 3013 | 25631.7723 | 0.099805 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
112 | EL DORADO PH 210219562 | 152762102 | EL DORADO PH 2102 | 7.2492 | 98 | 1.4503e-05 | 0.0014213 | 3014 | 25639.0214 | 0.098384 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3957 | LOS GATOS 1106LA42 | 82021106 | LOS GATOS 1106 | 2.7716 | 35 | 1.445e-05 | 0.00050575 | 3015 | 25641.793 | 0.097878 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10681 | GEYSERVILLE 1101975350 | 42891101 | GEYSERVILLE 1101 | 0.045436 | 3 | 1.4284e-05 | 4.2852e-05 | 3016 | 25641.8384 | 0.097835 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10208 | SHINGLE SPRINGS 2110CB | 153652110 | SHINGLE SPRINGS 2110 | 0.83703 | 15 | 1.4099e-05 | 0.00021149 | 3017 | 25642.6755 | 0.097624 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10739 | FORT BRAGG A 1104920850 | 42761104 | FORT BRAGG A 1104 | 0.20025 | 3 | 1.406e-05 | 4.2181e-05 | 3018 | 25642.8757 | 0.097581 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9733 | AUBURN 11028611 | 152161102 | AUBURN 1102 | 1.7986 | 22 | 1.3867e-05 | 0.00030508 | 3019 | 25644.6743 | 0.097276 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6925 | MIRABEL 11022043 | 42091102 | MIRABEL 1102 | 0.56074 | 8 | 1.3842e-05 | 0.00011074 | 3020 | 25645.235 | 0.097166 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6206 | SAN RAFAEL 11081247 | 42011108 | SAN RAFAEL 1108 | 0.27562 | 3 | 1.3714e-05 | 4.1142e-05 | 3021 | 25645.5107 | 0.097124 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9515 | HARRIS 1109661309 | 192431109 | HARRIS 1109 | 0.28204 | 16 | 1.3667e-05 | 0.00021867 | 3022 | 25645.7927 | 0.096906 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10016 | CAMP EVERS 2104600529 | 83622104 | CAMP EVERS 2104 | 0.26277 | 4 | 1.3356e-05 | 5.3422e-05 | 3023 | 25646.0555 | 0.096852 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10551 | PUEBLO 1104968601 | 43291104 | PUEBLO 1104 | 0.0076071 | 1 | 1.3316e-05 | 1.3316e-05 | 3024 | 25646.0631 | 0.096839 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8097 | SARATOGA 11075696 | 83371107 | SARATOGA 1107 | 5.0666 | 90 | 1.3265e-05 | 0.0011939 | 3025 | 25651.1297 | 0.095645 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9710 | GEYSERVILLE 1101216442 | 42891101 | GEYSERVILLE 1101 | 0.2035 | 4 | 1.2906e-05 | 5.1625e-05 | 3026 | 25651.3332 | 0.095593 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8869 | BRUNSWICK 11047181 | 152481104 | BRUNSWICK 1104 | 0.77324 | 11 | 1.2843e-05 | 0.00014128 | 3027 | 25652.1065 | 0.095452 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8464 | CAMP EVERS 21067603 | 83622106 | CAMP EVERS 2106 | 0.94918 | 11 | 1.278e-05 | 0.00014058 | 3028 | 25653.0556 | 0.095312 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1616 | SARATOGA 1106LC24 | 83371106 | SARATOGA 1106 | 8.2403 | 154 | 1.2747e-05 | 0.001963 | 3029 | 25661.2959 | 0.093349 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10877 | MORAGA 110183424 | 13801101 | MORAGA 1101 | 1.6162 | 7 | 1.2546e-05 | 8.7822e-05 | 3030 | 25662.9121 | 0.093261 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7661 | CAMP EVERS 210616000 | 83622106 | CAMP EVERS 2106 | 2.0843 | 51 | 1.2496e-05 | 0.0006373 | 3031 | 25664.9964 | 0.092623 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
11062 | KESWICK 1101CB | 103451101 | KESWICK 1101 | 0.016574 | 1 | 1.2413e-05 | 1.2413e-05 | 3032 | 25665.0129 | 0.092611 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10730 | STAFFORD 1101344092 | 43201101 | STAFFORD 1101 | 0.071671 | 2 | 1.2368e-05 | 2.4736e-05 | 3033 | 25665.0846 | 0.092586 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2899 | PLACER 1101208930 | 152461101 | PLACER 1101 | 0.1163 | 10 | 1.2302e-05 | 0.00012302 | 3034 | 25665.2009 | 0.092463 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3721 | SHINGLE SPRINGS 210511172 | 153652105 | SHINGLE SPRINGS 2105 | 2.0001 | 38 | 1.2003e-05 | 0.00045612 | 3035 | 25667.2011 | 0.092007 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8829 | MONTE RIO 1111CB | 42811111 | MONTE RIO 1111 | 0.25414 | 4 | 1.1845e-05 | 4.7378e-05 | 3036 | 25667.4552 | 0.09196 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3789 | LOS GATOS 1106LA46 | 82021106 | LOS GATOS 1106 | 1.4989 | 20 | 1.1694e-05 | 0.00023387 | 3037 | 25668.9541 | 0.091726 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8577 | SARATOGA 1115463510 | 83371115 | SARATOGA 1115 | 2.9197 | 41 | 1.1648e-05 | 0.00047756 | 3038 | 25671.8739 | 0.091248 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8231 | HALF MOON BAY 11038898 | 24101103 | HALF MOON BAY 1103 | 0.64313 | 9 | 1.1558e-05 | 0.00010403 | 3039 | 25672.517 | 0.091144 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3716 | CASTRO VALLEY 1102MR359 | 14091102 | CASTRO VALLEY 1102 | 0 | 90 | 1.1476e-05 | 0.0010328 | 3040 | 25672.517 | 0.090112 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9742 | MONROE 210392868 | 43302103 | MONROE 2103 | 0.1265 | 14 | 1.1443e-05 | 0.0001602 | 3041 | 25672.6435 | 0.089951 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
830 | OAKLAND X 1104391688 | 12541104 | OAKLAND X 1104 | 1.2876 | 16 | 1.1434e-05 | 0.00018295 | 3042 | 25673.9311 | 0.089768 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3807 | CAMP EVERS 210355638 | 83622103 | CAMP EVERS 2103 | 1.8332 | 42 | 1.1416e-05 | 0.00047946 | 3043 | 25675.7643 | 0.089289 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2161 | LAKEWOOD 2227W503R | 13532227 | LAKEWOOD 2227 | 0.075745 | 89 | 1.1363e-05 | 0.0010113 | 3044 | 25675.84 | 0.088278 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10225 | CLOVERDALE 1101409224 | 42821101 | CLOVERDALE 1101 | 0.086215 | 4 | 1.131e-05 | 4.524e-05 | 3045 | 25675.9262 | 0.088232 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9704 | DEL MAR 210938684 | 152582109 | DEL MAR 2109 | 0.023864 | 1 | 1.1274e-05 | 1.1274e-05 | 3046 | 25675.9501 | 0.088221 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6951 | MONTE RIO 1111506 | 42811111 | MONTE RIO 1111 | 1.2565 | 18 | 1.1203e-05 | 0.00020165 | 3047 | 25677.2066 | 0.088019 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7579 | WOODSIDE 11012299 | 24251101 | WOODSIDE 1101 | 1.8197 | 25 | 1.1198e-05 | 0.00027996 | 3048 | 25679.0263 | 0.08774 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4426 | SHINGLE SPRINGS 11038752 | 153651103 | SHINGLE SPRINGS 1103 | 1.8569 | 32 | 1.0889e-05 | 0.00034845 | 3049 | 25680.8832 | 0.087391 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3276 | CAMP EVERS 210310946 | 83622103 | CAMP EVERS 2103 | 5.6546 | 112 | 1.0851e-05 | 0.0012153 | 3050 | 25686.5379 | 0.086176 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4220 | OAKLAND X 1104CR214 | 12541104 | OAKLAND X 1104 | 2.882 | 35 | 1.0841e-05 | 0.00037942 | 3051 | 25689.4199 | 0.085796 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3032 | OAKLAND X 1104CR288 | 12541104 | OAKLAND X 1104 | 2.7237 | 46 | 1.0814e-05 | 0.00049744 | 3052 | 25692.1436 | 0.085299 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3352 | OAKLAND X 1104CR022 | 12541104 | OAKLAND X 1104 | 4.0194 | 48 | 1.073e-05 | 0.00051505 | 3053 | 25696.163 | 0.084784 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9828 | ALLEGHANY 11021101/2 | 152101102 | ALLEGHANY 1102 | 0.019385 | 1 | 1.0723e-05 | 1.0723e-05 | 3054 | 25696.1824 | 0.084773 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9784 | CAMP EVERS 2104496570 | 83622104 | CAMP EVERS 2104 | 0.24196 | 8 | 1.0717e-05 | 8.5734e-05 | 3055 | 25696.4243 | 0.084687 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6309 | MONTE RIO 1113250 | 42811113 | MONTE RIO 1113 | 1.2339 | 14 | 1.0662e-05 | 0.00014927 | 3056 | 25697.6582 | 0.084538 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10893 | FROGTOWN 1702390720 | 163451702 | FROGTOWN 1702 | 0.12582 | 2 | 1.055e-05 | 2.11e-05 | 3057 | 25697.784 | 0.084517 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4614 | SAN RAFAEL 11081262 | 42011108 | SAN RAFAEL 1108 | 3.9225 | 57 | 1.0529e-05 | 0.00060016 | 3058 | 25701.7065 | 0.083917 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9095 | LLAGAS 2107250129 | 83182107 | LLAGAS 2107 | 0.24964 | 5 | 1.046e-05 | 5.23e-05 | 3059 | 25701.9561 | 0.083865 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8911 | CAMP EVERS 2106CB | 83622106 | CAMP EVERS 2106 | 0.68456 | 37 | 1.0397e-05 | 0.00038468 | 3060 | 25702.6407 | 0.08348 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10545 | PASO ROBLES 1103451760 | 182611103 | PASO ROBLES 1103 | 0.061067 | 2 | 1.0297e-05 | 2.0594e-05 | 3061 | 25702.7018 | 0.083459 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1830 | SANTA ROSA A 1104210 | 42151104 | SANTA ROSA A 1104 | 6.512 | 107 | 1.0255e-05 | 0.0010973 | 3062 | 25709.2138 | 0.082362 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10656 | MIWUK 170179118 | 163661701 | MIWUK 1701 | 0.019364 | 2 | 1.0238e-05 | 2.0475e-05 | 3063 | 25709.2332 | 0.082342 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7888 | MONTE RIO 1112212 | 42811112 | MONTE RIO 1112 | 2.2487 | 27 | 1.0234e-05 | 0.00027631 | 3064 | 25711.4819 | 0.082065 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5285 | CAMP EVERS 21061625 | 83622106 | CAMP EVERS 2106 | 0.87071 | 10 | 1.0231e-05 | 0.00010231 | 3065 | 25712.3526 | 0.081963 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7246 | HUMBOLDT BAY 1102104220 | 192341102 | HUMBOLDT BAY 1102 | 0.91788 | 45 | 1.0177e-05 | 0.00045796 | 3066 | 25713.2705 | 0.081505 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3485 | SAN RAFAEL 1107CB | 42011107 | SAN RAFAEL 1107 | 4.8541 | 107 | 9.9897e-06 | 0.0010689 | 3067 | 25718.1246 | 0.080436 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1447 | OAKLAND K 1104CR204 | 12101104 | OAKLAND K 1104 | 4.1265 | 49 | 9.9677e-06 | 0.00048842 | 3068 | 25722.2511 | 0.079948 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10822 | GRASS VALLEY 1103CB | 152031103 | GRASS VALLEY 1103 | 0.11882 | 2 | 9.9558e-06 | 1.9912e-05 | 3069 | 25722.3699 | 0.079928 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3457 | OAKLAND K 1101CR178 | 12101101 | OAKLAND K 1101 | 0.32933 | 7 | 9.8623e-06 | 6.9036e-05 | 3070 | 25722.6992 | 0.079859 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3129 | SYCAMORE CREEK 1109CB | 102971109 | SYCAMORE CREEK 1109 | 0.16852 | 108 | 9.8448e-06 | 0.0010632 | 3071 | 25722.8678 | 0.078795 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2013 | SHINGLE SPRINGS 210851474 | 153652108 | SHINGLE SPRINGS 2108 | 0.36925 | 68 | 9.839e-06 | 0.00066905 | 3072 | 25723.237 | 0.078126 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4677 | MIDDLETOWN 1101932140 | 43141101 | MIDDLETOWN 1101 | 0.53555 | 15 | 9.669e-06 | 0.00014503 | 3073 | 25723.7726 | 0.077981 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3638 | WOODSIDE 1104CB | 24251104 | WOODSIDE 1104 | 0.10424 | 114 | 9.6632e-06 | 0.0011016 | 3074 | 25723.8768 | 0.07688 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8277 | MONTE RIO 1113532 | 42811113 | MONTE RIO 1113 | 0.52475 | 8 | 9.6241e-06 | 7.6993e-05 | 3075 | 25724.4016 | 0.076803 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
854 | SHINGLE SPRINGS 1104CB | 153651104 | SHINGLE SPRINGS 1104 | 0.70184 | 32 | 9.5675e-06 | 0.00030616 | 3076 | 25725.1034 | 0.076497 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6660 | HALSEY 11026129 | 152241102 | HALSEY 1102 | 3.2042 | 39 | 9.5328e-06 | 0.00037178 | 3077 | 25728.3076 | 0.076125 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10561 | BIG RIVER 1101CB | 43081101 | BIG RIVER 1101 | 0.02199 | 1 | 9.4951e-06 | 9.4951e-06 | 3078 | 25728.3295 | 0.076115 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4323 | GIRVAN 1102CB | 103401102 | GIRVAN 1102 | 1.0934 | 102 | 9.4726e-06 | 0.0009662 | 3079 | 25729.423 | 0.075149 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5228 | MONTE RIO 11135026 | 42811113 | MONTE RIO 1113 | 1.844 | 23 | 9.4686e-06 | 0.00021778 | 3080 | 25731.267 | 0.074931 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7379 | CALPELLA 1102379946 | 43411102 | CALPELLA 1102 | 0.75316 | 15 | 9.4131e-06 | 0.0001412 | 3081 | 25732.0202 | 0.07479 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8927 | ELK 1101CB | 42981101 | ELK 1101 | 0.02481 | 1 | 9.4072e-06 | 9.4072e-06 | 3082 | 25732.045 | 0.074781 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6426 | ALTO 1125296476 | 42031125 | ALTO 1125 | 0.65944 | 11 | 9.3993e-06 | 0.00010339 | 3083 | 25732.7044 | 0.074677 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7763 | BRUNSWICK 1105297538 | 152481105 | BRUNSWICK 1105 | 1.0588 | 15 | 9.367e-06 | 0.0001405 | 3084 | 25733.7632 | 0.074537 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6048 | SILVERADO 2105337226 | 43432105 | SILVERADO 2105 | 0.28495 | 13 | 9.3615e-06 | 0.0001217 | 3085 | 25734.0481 | 0.074415 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
785 | MIRABEL 1102CB | 42091102 | MIRABEL 1102 | 0.22303 | 85 | 9.286e-06 | 0.00078931 | 3086 | 25734.2711 | 0.073626 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10915 | CLARKSVILLE 210551478 | 153612105 | CLARKSVILLE 2105 | 0.050375 | 3 | 9.2483e-06 | 2.7745e-05 | 3087 | 25734.3215 | 0.073598 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3642 | AUBURN 1102CB | 152161102 | AUBURN 1102 | 1.3908 | 99 | 9.2292e-06 | 0.00091369 | 3088 | 25735.7123 | 0.072684 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10606 | BERKELEY F 1105BR166 | 12061105 | BERKELEY F 1105 | 0.038182 | 2 | 9.2229e-06 | 1.8446e-05 | 3089 | 25735.7505 | 0.072666 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2771 | RIO DELL 1102CB | 192251102 | RIO DELL 1102 | 0 | 86 | 9.2139e-06 | 0.0007924 | 3090 | 25735.7505 | 0.071874 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10346 | EEL RIVER 1103241646 | 192381103 | EEL RIVER 1103 | 0.3626 | 13 | 9.1396e-06 | 0.00011881 | 3091 | 25736.1131 | 0.071755 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
964 | SAN RAFAEL 110991742 | 42011109 | SAN RAFAEL 1109 | 2.3895 | 67 | 9.0186e-06 | 0.00060425 | 3092 | 25738.5026 | 0.07115 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5348 | EEL RIVER 11033820 | 192381103 | EEL RIVER 1103 | 0 | 115 | 8.9864e-06 | 0.0010334 | 3093 | 25738.5026 | 0.070117 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3020 | SARATOGA 1104209146 | 83371104 | SARATOGA 1104 | 3.0679 | 85 | 8.9692e-06 | 0.00076238 | 3094 | 25741.5705 | 0.069355 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10029 | MONTICELLO 11011780 | 43051101 | MONTICELLO 1101 | 0.071678 | 1 | 8.9608e-06 | 8.9608e-06 | 3095 | 25741.6422 | 0.069346 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10582 | OAKLAND X 1101328808 | 12541101 | OAKLAND X 1101 | 0.11589 | 1 | 8.9528e-06 | 8.9528e-06 | 3096 | 25741.7581 | 0.069337 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8839 | BIG BASIN 11026219 | 82841102 | BIG BASIN 1102 | 0.92519 | 11 | 8.7836e-06 | 9.662e-05 | 3097 | 25742.6832 | 0.06924 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2096 | CALISTOGA 1102184814 | 42711102 | CALISTOGA 1102 | 0.42402 | 20 | 8.707e-06 | 0.00017414 | 3098 | 25743.1073 | 0.069066 | 0.069066 | #N/A | TRUE | 0.18 | TRUE | TRUE
10342 | FROGTOWN 1702832694 | 163451702 | FROGTOWN 1702 | 0.28686 | 5 | 8.7057e-06 | 4.3529e-05 | 3099 | 25743.3941 | 0.069022 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2914 | EUREKA E 110435934 | 192331104 | EUREKA E 1104 | 0.048733 | 46 | 8.6658e-06 | 0.00039863 | 3100 | 25743.4429 | 0.068624 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4896 | IGNACIO 1105490728 | 42481105 | IGNACIO 1105 | 0.649 | 11 | 8.6628e-06 | 9.5291e-05 | 3101 | 25744.0919 | 0.068529 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9315 | LAKEWOOD 2224798018 | 13532224 | LAKEWOOD 2224 | 0.90013 | 13 | 8.6422e-06 | 0.00011235 | 3102 | 25744.992 | 0.068416 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9391 | WATERSHED 0402CB | 24240402 | WATERSHED 0402 | 0.21316 | 11 | 8.6414e-06 | 9.5055e-05 | 3103 | 25745.2052 | 0.068321 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9903 | PACIFICA 1102894156 | 22811102 | PACIFICA 1102 | 0.38867 | 4 | 8.6111e-06 | 3.4445e-05 | 3104 | 25745.5938 | 0.068287 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7834 | GREENBRAE 1103718674 | 43091103 | GREENBRAE 1103 | 0.80908 | 16 | 8.6092e-06 | 0.00013775 | 3105 | 25746.4029 | 0.068149 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10810 | PLACERVILLE 1111610322 | 153081111 | PLACERVILLE 1111 | 0.13716 | 3 | 8.5935e-06 | 2.578e-05 | 3106 | 25746.5401 | 0.068123 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10497 | FORT ORD 21069658 | 182402106 | FORT ORD 2106 | 0.096962 | 3 | 8.4949e-06 | 2.5485e-05 | 3107 | 25746.637 | 0.068098 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5369 | OAKLAND K 1104CR206 | 12101104 | OAKLAND K 1104 | 1.7882 | 22 | 8.4479e-06 | 0.00018585 | 3108 | 25748.4252 | 0.067912 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6668 | PAUL SWEET 21075291 | 83252107 | PAUL SWEET 2107 | 0.031348 | 14 | 8.4226e-06 | 0.00011792 | 3109 | 25748.4565 | 0.067794 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4822 | CAMP EVERS 21035404 | 83622103 | CAMP EVERS 2103 | 2.7208 | 63 | 8.4149e-06 | 0.00053014 | 3110 | 25751.1774 | 0.067264 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10986 | RINCON 1101205854 | 43321101 | RINCON 1101 | 0.31393 | 5 | 8.3652e-06 | 4.1826e-05 | 3111 | 25751.4913 | 0.067222 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1364 | CAMP EVERS 21035402 | 83622103 | CAMP EVERS 2103 | 2.8564 | 87 | 8.3234e-06 | 0.00072413 | 3112 | 25754.3477 | 0.066498 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9661 | SARATOGA 1105431214 | 83371105 | SARATOGA 1105 | 0.31096 | 9 | 8.308e-06 | 7.4772e-05 | 3113 | 25754.6587 | 0.066423 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6999 | JESSUP 1102158468 | 103441102 | JESSUP 1102 | 0.69613 | 11 | 8.3063e-06 | 9.1369e-05 | 3114 | 25755.3548 | 0.066332 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7019 | FORT BRAGG A 1102816 | 42761102 | FORT BRAGG A 1102 | 2.4498 | 29 | 8.2407e-06 | 0.00023898 | 3115 | 25757.8046 | 0.066093 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9287 | SOBRANTE 1103N510R | 14671103 | SOBRANTE 1103 | 0.24969 | 15 | 8.2224e-06 | 0.00012334 | 3116 | 25758.0543 | 0.065969 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10537 | FROGTOWN 1702798032 | 163451702 | FROGTOWN 1702 | 0.15196 | 2 | 8.1969e-06 | 1.6394e-05 | 3117 | 25758.2062 | 0.065953 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7405 | HARRIS 11082062 | 192431108 | HARRIS 1108 | 1.5887 | 83 | 8.1613e-06 | 0.00067739 | 3118 | 25759.795 | 0.065276 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3886 | SAN RAFAEL 11081457 | 42011108 | SAN RAFAEL 1108 | 0.76406 | 9 | 8.1539e-06 | 7.3385e-05 | 3119 | 25760.559 | 0.065202 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9639 | IGNACIO 1105967039 | 42481105 | IGNACIO 1105 | 0.18205 | 3 | 8.139e-06 | 2.4417e-05 | 3120 | 25760.7411 | 0.065178 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10422 | OAKLAND J 1102CR102 | 12091102 | OAKLAND J 1102 | 0.1966 | 6 | 8.0835e-06 | 4.8501e-05 | 3121 | 25760.9377 | 0.065129 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10726 | CALISTOGA 1102960240 | 42711102 | CALISTOGA 1102 | 0.50732 | 5 | 8.0789e-06 | 4.0394e-05 | 3122 | 25761.445 | 0.065089 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9181 | MIWUK 1702531976 | 163661702 | MIWUK 1702 | 1.3067 | 17 | 8.0236e-06 | 0.0001364 | 3123 | 25762.7517 | 0.064952 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10385 | ALLEGHANY 11011101/2 | 152101101 | ALLEGHANY 1101 | 0.022986 | 1 | 8.0126e-06 | 8.0126e-06 | 3124 | 25762.7747 | 0.064944 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9316 | FORT BRAGG A 1103284356 | 42761103 | FORT BRAGG A 1103 | 0.13557 | 4 | 7.9902e-06 | 3.1961e-05 | 3125 | 25762.9103 | 0.064913 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10880 | OAKLAND X 1104CR101 | 12541104 | OAKLAND X 1104 | 0.017646 | 1 | 7.9011e-06 | 7.9011e-06 | 3126 | 25762.9279 | 0.064905 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4441 | OAKLAND X 1101CR224 | 12541101 | OAKLAND X 1101 | 0.40793 | 17 | 7.8938e-06 | 0.0001342 | 3127 | 25763.3358 | 0.06477 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10513 | OILFIELDS 1103441010 | 182391103 | OILFIELDS 1103 | 0.36823 | 4 | 7.8772e-06 | 3.1509e-05 | 3128 | 25763.7041 | 0.064739 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1793 | SAN RAFAEL 1109535284 | 42011109 | SAN RAFAEL 1109 | 0.0067505 | 9 | 7.8608e-06 | 7.0747e-05 | 3129 | 25763.7108 | 0.064668 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8925 | FRUITLAND 11418746 | 192311141 | FRUITLAND 1141 | 0.4013 | 8 | 7.8216e-06 | 6.2573e-05 | 3130 | 25764.1121 | 0.064606 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8734 | LOS GATOS 110160052 | 82021101 | LOS GATOS 1101 | 1.9696 | 28 | 7.8045e-06 | 0.00021853 | 3131 | 25766.0817 | 0.064387 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6798 | SAN CARLOS 110475210 | 24181104 | SAN CARLOS 1104 | 0.38467 | 6 | 7.7312e-06 | 4.6387e-05 | 3132 | 25766.4663 | 0.064341 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6381 | OAKLAND X 1106CR008 | 12541106 | OAKLAND X 1106 | 4.4615 | 65 | 7.7074e-06 | 0.00050098 | 3133 | 25770.9279 | 0.06384 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10638 | SAN RAFAEL 11092213 | 42011109 | SAN RAFAEL 1109 | 0.42875 | 6 | 7.6893e-06 | 4.6136e-05 | 3134 | 25771.3566 | 0.063794 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9009 | ALTO 1124553571 | 42031124 | ALTO 1124 | 0.1087 | 4 | 7.6617e-06 | 3.0647e-05 | 3135 | 25771.4653 | 0.063763 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1292 | EEL RIVER 1103CB | 192381103 | EEL RIVER 1103 | 0 | 374 | 7.6507e-06 | 0.0028614 | 3136 | 25771.4653 | 0.060902 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2486 | LOYOLA 110260082 | 82161102 | LOYOLA 1102 | 0 | 57 | 7.6477e-06 | 0.00043592 | 3137 | 25771.4653 | 0.060466 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9942 | BRUNSWICK 1104327226 | 152481104 | BRUNSWICK 1104 | 0.049461 | 2 | 7.6459e-06 | 1.5292e-05 | 3138 | 25771.5148 | 0.06045 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10778 | PIT NO 5 110190846 | 101321101 | PIT NO 5 1101 | 0.092731 | 2 | 7.6083e-06 | 1.5217e-05 | 3139 | 25771.6075 | 0.060435 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9691 | STELLING 1109787007 | 83481109 | STELLING 1109 | 0.19092 | 5 | 7.5915e-06 | 3.7958e-05 | 3140 | 25771.7984 | 0.060397 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1439 | TAR FLAT 0402CB | 163240402 | TAR FLAT 0402 | 0.7963 | 18 | 7.5882e-06 | 0.00013659 | 3141 | 25772.5947 | 0.060261 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4239 | TAR FLAT 0401CB | 163240401 | TAR FLAT 0401 | 3.4952 | 45 | 7.5759e-06 | 0.00034092 | 3142 | 25776.0899 | 0.05992 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6173 | OAKLAND X 1104645092 | 12541104 | OAKLAND X 1104 | 1.3857 | 16 | 7.5529e-06 | 0.00012085 | 3143 | 25777.4756 | 0.059799 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9734 | HIGHLANDS 110484640 | 43361104 | HIGHLANDS 1104 | 0.41053 | 14 | 7.5307e-06 | 0.00010543 | 3144 | 25777.8862 | 0.059693 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10502 | TRIDAM POWERHOUSE 2101CB | 168152101 | TRIDAM POWERHOUSE 2101 | 0.050339 | 3 | 7.4775e-06 | 2.2433e-05 | 3145 | 25777.9365 | 0.059671 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3266 | UKIAH 1113658899 | 42771113 | UKIAH 1113 | 0.58507 | 8 | 7.4661e-06 | 5.9729e-05 | 3146 | 25778.5216 | 0.059611 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10496 | FROGTOWN 1702814784 | 163451702 | FROGTOWN 1702 | 0.17406 | 3 | 7.4475e-06 | 2.2342e-05 | 3147 | 25778.6956 | 0.059589 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9921 | OAKLAND X 1106CR266 | 12541106 | OAKLAND X 1106 | 1.1819 | 8 | 7.421e-06 | 5.9368e-05 | 3148 | 25779.8775 | 0.05953 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7361 | SARATOGA 11076867 | 83371107 | SARATOGA 1107 | 0.61277 | 11 | 7.4136e-06 | 8.155e-05 | 3149 | 25780.4903 | 0.059448 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7276 | SAN CARLOS 11049052 | 24181104 | SAN CARLOS 1104 | 4.7995 | 65 | 7.4082e-06 | 0.00048153 | 3150 | 25785.2897 | 0.058966 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9123 | UKIAH 1114296894 | 42771114 | UKIAH 1114 | 0.17288 | 6 | 7.398e-06 | 4.4388e-05 | 3151 | 25785.4626 | 0.058922 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10484 | SANTA ROSA A 1111407286 | 42151111 | SANTA ROSA A 1111 | 0.06092 | 1 | 7.3466e-06 | 7.3466e-06 | 3152 | 25785.5235 | 0.058915 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6588 | HARRIS 1108705523 | 192431108 | HARRIS 1108 | 0.20008 | 11 | 7.293e-06 | 8.0224e-05 | 3153 | 25785.7236 | 0.058834 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3678 | RESEARCH 2102183888 | 14692102 | RESEARCH 2102 | 1.1802 | 43 | 7.2344e-06 | 0.00031108 | 3154 | 25786.9038 | 0.058523 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9265 | ROSSMOOR 1104892332 | 14161104 | ROSSMOOR 1104 | 0.25496 | 4 | 7.2035e-06 | 2.8814e-05 | 3155 | 25787.1588 | 0.058495 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5151 | EDES 1112CR312 | 13681112 | EDES 1112 | 3.6881 | 42 | 7.189e-06 | 0.00030194 | 3156 | 25790.8469 | 0.058193 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6055 | SILVERADO 2105191725 | 43432105 | SILVERADO 2105 | 0.34689 | 8 | 7.1671e-06 | 5.7337e-05 | 3157 | 25791.1938 | 0.058135 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8973 | DIAMOND SPRINGS 1103394169 | 152261103 | DIAMOND SPRINGS 1103 | 0.39906 | 7 | 7.1481e-06 | 5.0037e-05 | 3158 | 25791.5928 | 0.058085 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9966 | MONROE 2107380760 | 43302107 | MONROE 2107 | 0.65446 | 12 | 7.1451e-06 | 8.5741e-05 | 3159 | 25792.2473 | 0.058 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2463 | OAKLAND K 1103CR188 | 12101103 | OAKLAND K 1103 | 3.58 | 47 | 7.1432e-06 | 0.00033573 | 3160 | 25795.8273 | 0.057664 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7755 | HICKS 1116983580 | 83431116 | HICKS 1116 | 2.4602 | 33 | 7.1402e-06 | 0.00023563 | 3161 | 25798.2875 | 0.057428 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2292 | OAKLAND K 1104CR326 | 12101104 | OAKLAND K 1104 | 1.3045 | 17 | 7.0989e-06 | 0.00012068 | 3162 | 25799.592 | 0.057307 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10476 | SAN RAFAEL 1106618957 | 42011106 | SAN RAFAEL 1106 | 0.18715 | 4 | 7.0643e-06 | 2.8257e-05 | 3163 | 25799.7791 | 0.057279 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3538 | CORTINA 1101302192 | 63121101 | CORTINA 1101 | 0 | 79 | 7.0599e-06 | 0.00055773 | 3164 | 25799.7791 | 0.056721 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3533 | OAKLAND K 1104432850 | 12101104 | OAKLAND K 1104 | 1.2358 | 26 | 6.9884e-06 | 0.0001817 | 3165 | 25801.0149 | 0.05654 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9797 | DEL MONTE 21032204 | 182222103 | DEL MONTE 2103 | 0.36833 | 8 | 6.9782e-06 | 5.5825e-05 | 3166 | 25801.3832 | 0.056484 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10205 | BERKELEY F 1103813976 | 12061103 | BERKELEY F 1103 | 0.19409 | 4 | 6.9422e-06 | 2.7769e-05 | 3167 | 25801.5773 | 0.056456 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
398 | ROSSMOOR 1104CB | 14161104 | ROSSMOOR 1104 | 0 | 150 | 6.9228e-06 | 0.0010384 | 3168 | 25801.5773 | 0.055418 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
465 | MOLINO 1102111666 | 42571102 | MOLINO 1102 | 0.11349 | 13 | 6.9214e-06 | 8.9978e-05 | 3169 | 25801.6908 | 0.055328 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9817 | SUMMIT 11016627 | 152591101 | SUMMIT 1101 | 0.56581 | 8 | 6.9114e-06 | 5.5291e-05 | 3170 | 25802.2566 | 0.055273 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6657 | SAN RAFAEL 110168970 | 42011101 | SAN RAFAEL 1101 | 0.047002 | 44 | 6.892e-06 | 0.00030325 | 3171 | 25802.3036 | 0.054969 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8713 | GANSNER 1101489276 | 103021101 | GANSNER 1101 | 0.44978 | 9 | 6.8546e-06 | 6.1691e-05 | 3172 | 25802.7534 | 0.054908 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6405 | ROB ROY 210571630 | 83692105 | ROB ROY 2105 | 1.3562 | 26 | 6.8241e-06 | 0.00017743 | 3173 | 25804.1096 | 0.05473 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1284 | SARATOGA 1106LC22 | 83371106 | SARATOGA 1106 | 7.4822 | 114 | 6.8223e-06 | 0.00077774 | 3174 | 25811.5918 | 0.053952 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4762 | SAN RAFAEL 110668694 | 42011106 | SAN RAFAEL 1106 | 0 | 32 | 6.7736e-06 | 0.00021675 | 3175 | 25811.5918 | 0.053736 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9002 | PAUL SWEET 2102168368 | 83252102 | PAUL SWEET 2102 | 0.36697 | 8 | 6.7491e-06 | 5.3993e-05 | 3176 | 25811.9588 | 0.053682 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8371 | RINCON 1102782389 | 43321102 | RINCON 1102 | 0.36418 | 8 | 6.7151e-06 | 5.3721e-05 | 3177 | 25812.3229 | 0.053628 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7829 | UKIAH 111472990 | 42771114 | UKIAH 1114 | 0.73068 | 38 | 6.7147e-06 | 0.00025516 | 3178 | 25813.0536 | 0.053373 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4895 | SARATOGA 1103LC16 | 83371103 | SARATOGA 1103 | 4.2817 | 72 | 6.7061e-06 | 0.00048284 | 3179 | 25817.3353 | 0.05289 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2902 | WAYNE 0401954811 | 13810401 | WAYNE 0401 | 0.17582 | 9 | 6.7055e-06 | 6.0349e-05 | 3180 | 25817.5111 | 0.05283 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6002 | SAN RAFAEL 1105818262 | 42011105 | SAN RAFAEL 1105 | 0.18205 | 11 | 6.6573e-06 | 7.3231e-05 | 3181 | 25817.6932 | 0.052756 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9719 | PIT NO 5 11011614 | 101321101 | PIT NO 5 1101 | 1.8648 | 5 | 6.6513e-06 | 3.3257e-05 | 3182 | 25819.558 | 0.052723 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5122 | RIDGE 0401CB | 12840401 | RIDGE 0401 | 2.654 | 36 | 6.6432e-06 | 0.00023916 | 3183 | 25822.212 | 0.052484 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1193 | FORT BRAGG A 1102418 | 42761102 | FORT BRAGG A 1102 | 14.0083 | 178 | 6.6205e-06 | 0.0011785 | 3184 | 25836.2202 | 0.051305 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8138 | FRANKLIN 1101P138 | 13921101 | FRANKLIN 1101 | 1.404 | 15 | 6.5684e-06 | 9.8527e-05 | 3185 | 25837.6242 | 0.051207 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
11032 | HIGHLANDS 1101CB | 43361101 | HIGHLANDS 1101 | 0.026415 | 1 | 6.536e-06 | 6.536e-06 | 3186 | 25837.6506 | 0.0512 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3671 | CAMP EVERS 2104CB | 83622104 | CAMP EVERS 2104 | 0.39105 | 71 | 6.5265e-06 | 0.00046338 | 3187 | 25838.0417 | 0.050737 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8113 | WOODSIDE 110411555 | 24251104 | WOODSIDE 1104 | 0.85767 | 11 | 6.5136e-06 | 7.165e-05 | 3188 | 25838.8994 | 0.050665 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8611 | CAROLANDS 04018888 | 24060401 | CAROLANDS 0401 | 0 | 25 | 6.5082e-06 | 0.0001627 | 3189 | 25838.8994 | 0.050503 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10705 | CLOVERDALE 1102801904 | 42821102 | CLOVERDALE 1102 | 0.013914 | 1 | 6.5066e-06 | 6.5066e-06 | 3190 | 25838.9133 | 0.050496 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7620 | CASTRO VALLEY 1110MR341 | 14091110 | CASTRO VALLEY 1110 | 0.25931 | 11 | 6.5027e-06 | 7.1529e-05 | 3191 | 25839.1726 | 0.050425 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6399 | ROB ROY 21049973 | 83692104 | ROB ROY 2104 | 0.57273 | 7 | 6.4944e-06 | 4.5461e-05 | 3192 | 25839.7453 | 0.050379 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4710 | VIEJO 220255787 | 182852202 | VIEJO 2202 | 0.036622 | 1 | 6.491e-06 | 6.491e-06 | 3193 | 25839.7819 | 0.050373 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3931 | LAS AROMAS 04013342 | 13600401 | LAS AROMAS 0401 | 2.2944 | 30 | 6.402e-06 | 0.00019206 | 3194 | 25842.0764 | 0.050181 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
738 | SAN RAFAEL 1104CB | 42011104 | SAN RAFAEL 1104 | 3.4557 | 140 | 6.3852e-06 | 0.00089393 | 3195 | 25845.5321 | 0.049287 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9201 | HICKS 1116583284 | 83431116 | HICKS 1116 | 0.14703 | 4 | 6.3368e-06 | 2.5347e-05 | 3196 | 25845.6791 | 0.049261 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7050 | EAST QUINCY 1101678650 | 102551101 | EAST QUINCY 1101 | 1.1243 | 14 | 6.2788e-06 | 8.7903e-05 | 3197 | 25846.8034 | 0.049173 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9107 | OAKLAND K 1103CR422 | 12101103 | OAKLAND K 1103 | 2.0126 | 24 | 6.2703e-06 | 0.00015049 | 3198 | 25848.816 | 0.049023 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2296 | LAURELES 11112028 | 182371111 | LAURELES 1111 | 8.7309 | 107 | 6.2585e-06 | 0.00066966 | 3199 | 25857.5469 | 0.048353 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4668 | KONOCTI 11084041 | 43311108 | KONOCTI 1108 | 1.3514 | 54 | 6.2484e-06 | 0.00033741 | 3200 | 25858.8984 | 0.048016 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4517 | SILVERADO 2105CB | 43432105 | SILVERADO 2105 | 0.62873 | 66 | 6.2313e-06 | 0.00041127 | 3201 | 25859.5271 | 0.047605 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1407 | SAN RAFAEL 11061230 | 42011106 | SAN RAFAEL 1106 | 1.0861 | 57 | 6.2233e-06 | 0.00035473 | 3202 | 25860.6132 | 0.04725 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7332 | LOS GATOS 1101184035 | 82021101 | LOS GATOS 1101 | 0.56304 | 9 | 6.0721e-06 | 5.4649e-05 | 3203 | 25861.1763 | 0.047195 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10579 | SAN CARLOS 11049048 | 24181104 | SAN CARLOS 1104 | 0.015283 | 1 | 6.06e-06 | 6.06e-06 | 3204 | 25861.1916 | 0.047189 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2032 | LUCERNE 11031663 | 43351103 | LUCERNE 1103 | 1.2105 | 17 | 6.0525e-06 | 0.00010289 | 3205 | 25862.402 | 0.047086 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9700 | SAN RAMON 2103MR279 | 14232103 | SAN RAMON 2103 | 0.0028415 | 5 | 6.0521e-06 | 3.0261e-05 | 3206 | 25862.4049 | 0.047056 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5325 | SAN RAFAEL 1105534 | 42011105 | SAN RAFAEL 1105 | 0.97555 | 22 | 6.0384e-06 | 0.00013284 | 3207 | 25863.3804 | 0.046923 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8122 | HATTON 1101CB | 182291101 | HATTON 1101 | 1.5858 | 22 | 6.0227e-06 | 0.0001325 | 3208 | 25864.9662 | 0.046791 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6886 | ALTO 1124526955 | 42031124 | ALTO 1124 | 0.44373 | 6 | 6.0133e-06 | 3.608e-05 | 3209 | 25865.41 | 0.046755 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5909 | CAMP EVERS 210392582 | 83622103 | CAMP EVERS 2103 | 0.15274 | 41 | 5.9997e-06 | 0.00024599 | 3210 | 25865.5627 | 0.046509 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6632 | SAN RAFAEL 1106588020 | 42011106 | SAN RAFAEL 1106 | 0.23943 | 19 | 5.9904e-06 | 0.00011382 | 3211 | 25865.8021 | 0.046395 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
763 | LOS GATOS 1108LB86 | 82021108 | LOS GATOS 1108 | 4.5188 | 69 | 5.9458e-06 | 0.00041026 | 3212 | 25870.321 | 0.045985 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10570 | EL CERRITO G 1105BR164 | 12501105 | EL CERRITO G 1105 | 0.05692 | 2 | 5.9372e-06 | 1.1874e-05 | 3213 | 25870.3779 | 0.045973 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9932 | ALTO 1125291744 | 42031125 | ALTO 1125 | 0.12168 | 3 | 5.9276e-06 | 1.7783e-05 | 3214 | 25870.4996 | 0.045955 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8178 | DOLAN ROAD 1101156268 | 182381101 | DOLAN ROAD 1101 | 0.032781 | 31 | 5.914e-06 | 0.00018333 | 3215 | 25870.5323 | 0.045772 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6600 | VIEJO 2202CB | 182852202 | VIEJO 2202 | 2.1443 | 23 | 5.9077e-06 | 0.00013588 | 3216 | 25872.6767 | 0.045636 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4067 | LAS AROMAS 0401LA401R | 13600401 | LAS AROMAS 0401 | 3.0804 | 55 | 5.9068e-06 | 0.00032487 | 3217 | 25875.7571 | 0.045311 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
807 | RESEARCH 210263274 | 14692102 | RESEARCH 2102 | 0.046218 | 119 | 5.8646e-06 | 0.00069789 | 3218 | 25875.8033 | 0.044613 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10104 | LAKEWOOD 1102964292 | 13531102 | LAKEWOOD 1102 | 0.079652 | 2 | 5.8569e-06 | 1.1714e-05 | 3219 | 25875.8829 | 0.044601 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8987 | ROSSMOOR 110181770 | 14161101 | ROSSMOOR 1101 | 0.068628 | 21 | 5.8019e-06 | 0.00012184 | 3220 | 25875.9516 | 0.044479 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9943 | FRANKLIN 1104P136 | 13921104 | FRANKLIN 1104 | 4.9295 | 43 | 5.7997e-06 | 0.00024939 | 3221 | 25880.881 | 0.04423 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9679 | DOBBINS 1101CB | 153741101 | DOBBINS 1101 | 0.67066 | 8 | 5.7961e-06 | 4.6369e-05 | 3222 | 25881.5517 | 0.044184 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
734 | SILVERADO 21051308 | 43432105 | SILVERADO 2105 | 0.15225 | 60 | 5.7874e-06 | 0.00034724 | 3223 | 25881.7039 | 0.043836 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5907 | ORINDA 0401401/2 LR | 12350401 | ORINDA 0401 | 0.098352 | 4 | 5.7731e-06 | 2.3093e-05 | 3224 | 25881.8023 | 0.043813 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
648 | KONOCTI 11084039 | 43311108 | KONOCTI 1108 | 1.8946 | 32 | 5.7609e-06 | 0.00018435 | 3225 | 25883.6969 | 0.043629 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5547 | KONOCTI 11084037 | 43311108 | KONOCTI 1108 | 1.1437 | 22 | 5.7543e-06 | 0.0001266 | 3226 | 25884.8406 | 0.043502 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3274 | RACETRACK 170310850 | 163761703 | RACETRACK 1703 | 0.61832 | 28 | 5.704e-06 | 0.00015971 | 3227 | 25885.4589 | 0.043343 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5740 | SUMMIT 110148636 | 152591101 | SUMMIT 1101 | 0.053712 | 38 | 5.6861e-06 | 0.00021607 | 3228 | 25885.5127 | 0.043127 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8762 | VASONA 1102944560 | 83771102 | VASONA 1102 | 0.17566 | 9 | 5.6635e-06 | 5.0971e-05 | 3229 | 25885.6883 | 0.043076 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5538 | BERKELEY F 1103162952 | 12061103 | BERKELEY F 1103 | 1.7693 | 25 | 5.6583e-06 | 0.00014146 | 3230 | 25887.4576 | 0.042934 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
319 | DUNBAR 1103725292 | 43071103 | DUNBAR 1103 | 0.21105 | 13 | 5.658e-06 | 7.3554e-05 | 3231 | 25887.6686 | 0.042861 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5356 | SOBRANTE 110142914 | 14671101 | SOBRANTE 1101 | 0.4137 | 51 | 5.6577e-06 | 0.00028854 | 3232 | 25888.0823 | 0.042572 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4656 | OAKLAND K 1104CR208 | 12101104 | OAKLAND K 1104 | 2.421 | 29 | 5.6453e-06 | 0.00016371 | 3233 | 25890.5034 | 0.042408 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1498 | SAN RAFAEL 1101189400 | 42011101 | SAN RAFAEL 1101 | 2.7637 | 45 | 5.6305e-06 | 0.00025337 | 3234 | 25893.267 | 0.042155 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9302 | NEWBURG 1131987158 | 192151131 | NEWBURG 1131 | 0.24716 | 2 | 5.6215e-06 | 1.1243e-05 | 3235 | 25893.5142 | 0.042144 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1260 | PALO SECO 0401CB | 13180401 | PALO SECO 0401 | 4.745 | 55 | 5.6154e-06 | 0.00030885 | 3236 | 25898.2592 | 0.041835 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7087 | OAKLAND K 1101CR170 | 12101101 | OAKLAND K 1101 | 1.251 | 17 | 5.5684e-06 | 9.4663e-05 | 3237 | 25899.5102 | 0.04174 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9325 | TASSAJARA 2108189700 | 14662108 | TASSAJARA 2108 | 0.19063 | 22 | 5.5512e-06 | 0.00012213 | 3238 | 25899.7009 | 0.041618 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8529 | ROSSMOOR 110479146 | 14161104 | ROSSMOOR 1104 | 0.05321 | 28 | 5.451e-06 | 0.00015263 | 3239 | 25899.7541 | 0.041465 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5159 | PAUL SWEET 2109634576 | 83252109 | PAUL SWEET 2109 | 1.8241 | 29 | 5.4462e-06 | 0.00015794 | 3240 | 25901.5782 | 0.041308 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
176 | TASSAJARA 2108D520R | 14662108 | TASSAJARA 2108 | 0 | 50 | 5.4455e-06 | 0.00027228 | 3241 | 25901.5782 | 0.041035 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2934 | LAKEWOOD 210769586 | 13532107 | LAKEWOOD 2107 | 0.42817 | 80 | 5.4423e-06 | 0.00043538 | 3242 | 25902.0064 | 0.0406 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2160 | HIGHLANDS 1104CB | 43361104 | HIGHLANDS 1104 | 4.7619 | 102 | 5.4342e-06 | 0.00055429 | 3243 | 25906.7683 | 0.040046 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7487 | GANSNER 1101174072 | 103021101 | GANSNER 1101 | 0.10734 | 3 | 5.3939e-06 | 1.6182e-05 | 3244 | 25906.8756 | 0.040029 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10550 | SANTA ROSA A 1104834094 | 42151104 | SANTA ROSA A 1104 | 0.096633 | 3 | 5.3913e-06 | 1.6174e-05 | 3245 | 25906.9723 | 0.040013 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6137 | CAROLANDS 04049024 | 24060404 | CAROLANDS 0404 | 3.5095 | 62 | 5.3873e-06 | 0.00033401 | 3246 | 25910.4818 | 0.039679 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8307 | SAN RAFAEL 11042235 | 42011104 | SAN RAFAEL 1104 | 0.18438 | 10 | 5.3477e-06 | 5.3477e-05 | 3247 | 25910.6662 | 0.039626 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4970 | CASTRO VALLEY 1110264914 | 14091110 | CASTRO VALLEY 1110 | 0.868 | 14 | 5.3219e-06 | 7.4507e-05 | 3248 | 25911.5342 | 0.039551 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6336 | SAN RAFAEL 1101310 | 42011101 | SAN RAFAEL 1101 | 0.19876 | 48 | 5.3143e-06 | 0.00025509 | 3249 | 25911.7329 | 0.039296 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5625 | LAURELES 11116617 | 182371111 | LAURELES 1111 | 1.8171 | 13 | 5.304e-06 | 6.8952e-05 | 3250 | 25913.55 | 0.039227 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4819 | GANSNER 1101590690 | 103021101 | GANSNER 1101 | 0.063412 | 4 | 5.2923e-06 | 2.1169e-05 | 3251 | 25913.6134 | 0.039206 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3357 | TASSAJARA 210812712 | 14662108 | TASSAJARA 2108 | 0.76312 | 46 | 5.2813e-06 | 0.00024294 | 3252 | 25914.3765 | 0.038963 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4164 | ELK 11014628 | 42981101 | ELK 1101 | 2.4709 | 54 | 5.2551e-06 | 0.00028378 | 3253 | 25916.8475 | 0.038679 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5329 | ROSSMOOR 1106L522R | 14161106 | ROSSMOOR 1106 | 1.8843 | 56 | 5.255e-06 | 0.00029428 | 3254 | 25918.7318 | 0.038385 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10811 | STAFFORD 1101803535 | 43201101 | STAFFORD 1101 | 0.16314 | 3 | 5.2193e-06 | 1.5658e-05 | 3255 | 25918.8949 | 0.038369 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7133 | DEL MONTE 21032000 | 182222103 | DEL MONTE 2103 | 9.0089 | 101 | 5.2097e-06 | 0.00052618 | 3256 | 25927.9038 | 0.037843 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5982 | SAN RAFAEL 1107434 | 42011107 | SAN RAFAEL 1107 | 0.030591 | 16 | 5.2024e-06 | 8.3238e-05 | 3257 | 25927.9344 | 0.03776 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7562 | IGNACIO 1105784032 | 42481105 | IGNACIO 1105 | 0.53682 | 11 | 5.1906e-06 | 5.7096e-05 | 3258 | 25928.4712 | 0.037703 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4422 | ROSSMOOR 1106CB | 14161106 | ROSSMOOR 1106 | 1.8254 | 60 | 5.1594e-06 | 0.00030957 | 3259 | 25930.2967 | 0.037393 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
788 | OAKLAND K 1104CR210 | 12101104 | OAKLAND K 1104 | 2.8257 | 35 | 5.1591e-06 | 0.00018057 | 3260 | 25933.1224 | 0.037213 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5398 | HARTLEY 1101471 | 43211101 | HARTLEY 1101 | 0 | 16 | 5.1543e-06 | 8.2468e-05 | 3261 | 25933.1224 | 0.03713 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3021 | SAN RAFAEL 1101494 | 42011101 | SAN RAFAEL 1101 | 5.6152 | 114 | 5.1065e-06 | 0.00058215 | 3262 | 25938.7376 | 0.036548 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2946 | WOODSIDE 11049116 | 24251104 | WOODSIDE 1104 | 0.83032 | 53 | 5.0499e-06 | 0.00026765 | 3263 | 25939.5679 | 0.03628 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8964 | MARIPOSA 2102527766 | 254452102 | MARIPOSA 2102 | 0.041619 | 1 | 5.0408e-06 | 5.0408e-06 | 3264 | 25939.6096 | 0.036275 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8147 | LAS GALLINAS A 1105648439 | 42991105 | LAS GALLINAS A 1105 | 0.0067816 | 3 | 5.033e-06 | 1.5099e-05 | 3265 | 25939.6163 | 0.03626 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6797 | EMERALD LAKE 04028858 | 24080402 | EMERALD LAKE 0402 | 1.9103 | 27 | 4.9935e-06 | 0.00013482 | 3266 | 25941.5266 | 0.036125 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8050 | BIG RIVER 11015065 | 43081101 | BIG RIVER 1101 | 2.2023 | 27 | 4.9756e-06 | 0.00013434 | 3267 | 25943.729 | 0.035991 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6040 | RACETRACK 17032553 | 163761703 | RACETRACK 1703 | 0.96229 | 32 | 4.9535e-06 | 0.00015851 | 3268 | 25944.6912 | 0.035833 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4959 | VALLEY VIEW 1105305072 | 14341105 | VALLEY VIEW 1105 | 3.1349 | 45 | 4.9532e-06 | 0.0002229 | 3269 | 25947.8261 | 0.03561 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1675 | CASTRO VALLEY 1111227862 | 14091111 | CASTRO VALLEY 1111 | 0.19847 | 26 | 4.952e-06 | 0.00012875 | 3270 | 25948.0246 | 0.035481 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9676 | PACIFICA 1103885952 | 22811103 | PACIFICA 1103 | 0.17616 | 4 | 4.9074e-06 | 1.963e-05 | 3271 | 25948.2008 | 0.035461 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8421 | EL CERRITO G 1112779030 | 12501112 | EL CERRITO G 1112 | 0.51428 | 11 | 4.881e-06 | 5.3691e-05 | 3272 | 25948.715 | 0.035408 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2317 | VACAVILLE 1112CB | 63601112 | VACAVILLE 1112 | 0.23531 | 52 | 4.847e-06 | 0.00025204 | 3273 | 25948.9504 | 0.035156 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2187 | NEWBURG 1131CB | 192151131 | NEWBURG 1131 | 0.15993 | 91 | 4.8414e-06 | 0.00044057 | 3274 | 25949.1103 | 0.034715 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8107 | EMERALD LAKE 0402CB | 24080402 | EMERALD LAKE 0402 | 1.8968 | 23 | 4.8042e-06 | 0.0001105 | 3275 | 25951.0071 | 0.034605 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1133 | SAN CARLOS 1103586832 | 24181103 | SAN CARLOS 1103 | 3.8195 | 53 | 4.7995e-06 | 0.00025437 | 3276 | 25954.8267 | 0.03435 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9839 | SAN RAFAEL 11073323 | 42011107 | SAN RAFAEL 1107 | 0.13345 | 2 | 4.7655e-06 | 9.5309e-06 | 3277 | 25954.9601 | 0.034341 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3598 | PAUL SWEET 210210290 | 83252102 | PAUL SWEET 2102 | 0.0028415 | 75 | 4.7388e-06 | 0.00035541 | 3278 | 25954.963 | 0.033985 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4237 | PAUL SWEET 2109687295 | 83252109 | PAUL SWEET 2109 | 0.92949 | 14 | 4.7113e-06 | 6.5958e-05 | 3279 | 25955.8925 | 0.033919 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4104 | GREENBRAE 1103CB | 43091103 | GREENBRAE 1103 | 0 | 61 | 4.6915e-06 | 0.00028618 | 3280 | 25955.8925 | 0.033633 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9040 | SAN RAFAEL 1101CB | 42011101 | SAN RAFAEL 1101 | 0 | 17 | 4.6868e-06 | 7.9676e-05 | 3281 | 25955.8925 | 0.033553 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9787 | ATASCADERO 1103395936 | 182541103 | ATASCADERO 1103 | 0.42621 | 6 | 4.6656e-06 | 2.7994e-05 | 3282 | 25956.3187 | 0.033525 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3209 | ROB ROY 210512474 | 83692105 | ROB ROY 2105 | 3.4104 | 105 | 4.6505e-06 | 0.00048831 | 3283 | 25959.729 | 0.033037 | 0.033037 | #N/A | TRUE | 1.86 | FALSE | TRUE
10084 | SAN RAFAEL 1106307651 | 42011106 | SAN RAFAEL 1106 | 0.10506 | 4 | 4.6267e-06 | 1.8507e-05 | 3284 | 25959.8341 | 0.033019 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8574 | BIG RIVER 1101262924 | 43081101 | BIG RIVER 1101 | 1.8846 | 30 | 4.6224e-06 | 0.00013867 | 3285 | 25961.7187 | 0.03288 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9375 | BIG MEADOWS 2101439 | 102812101 | BIG MEADOWS 2101 | 0.66455 | 12 | 4.6178e-06 | 5.5413e-05 | 3286 | 25962.3832 | 0.032825 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10457 | ALTO 1124319320 | 42031124 | ALTO 1124 | 0.1309 | 3 | 4.6148e-06 | 1.3844e-05 | 3287 | 25962.5141 | 0.032811 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9137 | BERKELEY F 1103620294 | 12061103 | BERKELEY F 1103 | 0.15517 | 4 | 4.6109e-06 | 1.8443e-05 | 3288 | 25962.6693 | 0.032792 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10199 | SALT SPRINGS 21023116 | 163692102 | SALT SPRINGS 2102 | 0.054163 | 2 | 4.5851e-06 | 9.1703e-06 | 3289 | 25962.7235 | 0.032783 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7887 | EAST QUINCY 1101782320 | 102551101 | EAST QUINCY 1101 | 0.2115 | 5 | 4.5524e-06 | 2.2762e-05 | 3290 | 25962.935 | 0.03276 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5305 | SAN RAFAEL 1105CB | 42011105 | SAN RAFAEL 1105 | 0 | 124 | 4.5504e-06 | 0.00056425 | 3291 | 25962.935 | 0.032196 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8451 | GUALALA 11124431 | 42841112 | GUALALA 1112 | 1.4093 | 16 | 4.548e-06 | 7.2768e-05 | 3292 | 25964.3443 | 0.032123 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2628 | EAST QUINCY 1101186938 | 102551101 | EAST QUINCY 1101 | 1.6607 | 41 | 4.5458e-06 | 0.00018638 | 3293 | 25966.005 | 0.031937 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8531 | VALLEY VIEW 1106602871 | 14341106 | VALLEY VIEW 1106 | 0.82315 | 14 | 4.5365e-06 | 6.3511e-05 | 3294 | 25966.8282 | 0.031873 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6262 | HIGHLANDS 110448262 | 43361104 | HIGHLANDS 1104 | 6.1995 | 74 | 4.5315e-06 | 0.00033533 | 3295 | 25973.0277 | 0.031538 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3513 | FLORENCE 0401CR220 | 12690401 | FLORENCE 0401 | 0.20224 | 19 | 4.51e-06 | 8.5689e-05 | 3296 | 25973.2299 | 0.031452 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5570 | SAN CARLOS 11048942 | 24181104 | SAN CARLOS 1104 | 2.118 | 35 | 4.5084e-06 | 0.00015779 | 3297 | 25975.3479 | 0.031295 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5867 | ARLINGTON 0401404226 | 13700401 | ARLINGTON 0401 | 0.87233 | 15 | 4.4777e-06 | 6.7165e-05 | 3298 | 25976.2203 | 0.031227 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1380 | HARRIS 11084674 | 192431108 | HARRIS 1108 | 0.045245 | 85 | 4.4584e-06 | 0.00037897 | 3299 | 25976.2655 | 0.030848 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7856 | FORT BRAGG A 1102CB | 42761102 | FORT BRAGG A 1102 | 2.234 | 73 | 4.4533e-06 | 0.00032509 | 3300 | 25978.4995 | 0.030523 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7134 | DEL MONTE 2103617344 | 182222103 | DEL MONTE 2103 | 1.8348 | 34 | 4.4076e-06 | 0.00014986 | 3301 | 25980.3342 | 0.030373 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3773 | RINCON 1104CB | 43321104 | RINCON 1104 | 0.56024 | 34 | 4.3928e-06 | 0.00014935 | 3302 | 25980.8945 | 0.030224 | 0.030224 | #N/A | TRUE | 1.78 | TRUE | TRUE
7255 | VIEJO 2203CB | 182852203 | VIEJO 2203 | 2.9383 | 42 | 4.392e-06 | 0.00018447 | 3303 | 25983.8328 | 0.03004 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1976 | LAURELES 111268454 | 182371112 | LAURELES 1112 | 8.4458 | 142 | 4.3912e-06 | 0.00062355 | 3304 | 25992.2786 | 0.029416 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1047 | DOLAN ROAD 110122158 | 182381101 | DOLAN ROAD 1101 | 0.11487 | 119 | 4.3836e-06 | 0.00052165 | 3305 | 25992.3934 | 0.028894 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4984 | PAUL SWEET 210212850 | 83252102 | PAUL SWEET 2102 | 0.66094 | 52 | 4.3733e-06 | 0.00022741 | 3306 | 25993.0544 | 0.028667 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10216 | GUALALA 1111498 | 42841111 | GUALALA 1111 | 2.8569 | 18 | 4.3648e-06 | 7.8567e-05 | 3307 | 25995.9113 | 0.028588 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5466 | WEST POINT 11025357 | 163201102 | WEST POINT 1102 | 3.3572 | 37 | 4.3621e-06 | 0.0001614 | 3308 | 25999.2685 | 0.028427 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5373 | VIEJO 22019490 | 182852201 | VIEJO 2201 | 1.2455 | 21 | 4.3539e-06 | 9.1432e-05 | 3309 | 26000.514 | 0.028336 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3074 | GANSNER 1101480328 | 103021101 | GANSNER 1101 | 0.29358 | 7 | 4.3254e-06 | 3.0278e-05 | 3310 | 26000.8076 | 0.028305 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2211 | DEL MONTE 21032654 | 182222103 | DEL MONTE 2103 | 1.8419 | 23 | 4.3113e-06 | 9.916e-05 | 3311 | 26002.6495 | 0.028206 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8914 | CLAYTON 2217CB | 12022217 | CLAYTON 2217 | 0.23231 | 8 | 4.2861e-06 | 3.4288e-05 | 3312 | 26002.8818 | 0.028172 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9870 | PUEBLO 2103253312 | 43292103 | PUEBLO 2103 | 0.42436 | 2 | 4.2859e-06 | 8.5718e-06 | 3313 | 26003.3061 | 0.028163 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10448 | DOLAN ROAD 1101173702 | 182381101 | DOLAN ROAD 1101 | 0.053872 | 3 | 4.2778e-06 | 1.2834e-05 | 3314 | 26003.36 | 0.028151 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7265 | ALTO 112265474 | 42031122 | ALTO 1122 | 2.3852 | 47 | 4.2638e-06 | 0.0002004 | 3315 | 26005.7452 | 0.02795 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6511 | PACIFICA 1103218962 | 22811103 | PACIFICA 1103 | 0.053658 | 2 | 4.2591e-06 | 8.5182e-06 | 3316 | 26005.7988 | 0.027942 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10670 | VACAVILLE 1111772224 | 63601111 | VACAVILLE 1111 | 0.057152 | 2 | 4.2158e-06 | 8.4316e-06 | 3317 | 26005.856 | 0.027933 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5386 | CAROLANDS 040484797 | 24060404 | CAROLANDS 0404 | 0.041454 | 21 | 4.2155e-06 | 8.8525e-05 | 3318 | 26005.8974 | 0.027845 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1724 | LAURELES 1112CB | 182371112 | LAURELES 1112 | 0.30651 | 38 | 4.2137e-06 | 0.00016012 | 3319 | 26006.204 | 0.027685 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1512 | ATASCADERO 1102CB | 182541102 | ATASCADERO 1102 | 0 | 67 | 4.207e-06 | 0.00028187 | 3320 | 26006.204 | 0.027403 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
557 | GREENBRAE 11021254 | 43091102 | GREENBRAE 1102 | 5.991 | 130 | 4.1869e-06 | 0.0005443 | 3321 | 26012.195 | 0.026858 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9628 | SAN CARLOS 110436864 | 24181104 | SAN CARLOS 1104 | 0.55297 | 10 | 4.1763e-06 | 4.1763e-05 | 3322 | 26012.748 | 0.026817 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7091 | HATTON 11029642 | 182291102 | HATTON 1102 | 1.197 | 18 | 4.1709e-06 | 7.5077e-05 | 3323 | 26013.9449 | 0.026742 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
757 | LAKEWOOD 1102CB | 13531102 | LAKEWOOD 1102 | 0.014663 | 121 | 4.1691e-06 | 0.00050446 | 3324 | 26013.9596 | 0.026237 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10987 | ECHO SUMMIT 1101CB | 158031101 | ECHO SUMMIT 1101 | 0.030563 | 1 | 4.1622e-06 | 4.1622e-06 | 3325 | 26013.9901 | 0.026233 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9358 | PACIFICA 1102267868 | 22811102 | PACIFICA 1102 | 0.84745 | 13 | 4.157e-06 | 5.4041e-05 | 3326 | 26014.8376 | 0.026179 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5985 | BERESFORD 04039154 | 24040403 | BERESFORD 0403 | 4.2117 | 95 | 4.1518e-06 | 0.00039442 | 3327 | 26019.0493 | 0.025784 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7732 | BIG MEADOWS 21012510 | 102812101 | BIG MEADOWS 2101 | 7.9419 | 22 | 4.1333e-06 | 9.0933e-05 | 3328 | 26026.9912 | 0.025694 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3692 | LAS GALLINAS A 1107554 | 42991107 | LAS GALLINAS A 1107 | 0.032931 | 35 | 4.1303e-06 | 0.00014456 | 3329 | 26027.0241 | 0.025549 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7653 | WOOD 0401265211 | 13380401 | WOOD 0401 | 0.14802 | 4 | 4.1276e-06 | 1.651e-05 | 3330 | 26027.1722 | 0.025532 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7212 | VIEJO 2201CB | 182852201 | VIEJO 2201 | 5.0859 | 67 | 4.1068e-06 | 0.00027516 | 3331 | 26032.2581 | 0.025257 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4015 | DOLAN ROAD 11013012 | 182381101 | DOLAN ROAD 1101 | 0.18766 | 160 | 4.0749e-06 | 0.00065198 | 3332 | 26032.4458 | 0.024605 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6661 | HICKS 2103XR248 | 83432103 | HICKS 2103 | 0 | 22 | 4.0743e-06 | 8.9634e-05 | 3333 | 26032.4458 | 0.024516 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9871 | SARATOGA 1103709451 | 83371103 | SARATOGA 1103 | 0.18799 | 5 | 4.0301e-06 | 2.0151e-05 | 3334 | 26032.6337 | 0.024496 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3396 | SARATOGA 1107CB | 83371107 | SARATOGA 1107 | 0.17019 | 135 | 4.0299e-06 | 0.00054404 | 3335 | 26032.8039 | 0.023951 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
697 | SANTA ROSA A 1107CB | 42151107 | SANTA ROSA A 1107 | 3.0326 | 92 | 3.9708e-06 | 0.00036531 | 3336 | 26035.8365 | 0.023586 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7511 | BERKELEY F 1105189500 | 12061105 | BERKELEY F 1105 | 0.76177 | 17 | 3.9708e-06 | 6.7503e-05 | 3337 | 26036.5983 | 0.023519 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5683 | OAKLAND K 1104CB | 12101104 | OAKLAND K 1104 | 1.4708 | 17 | 3.9555e-06 | 6.7244e-05 | 3338 | 26038.0691 | 0.023451 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4165 | VIEJO 22022606 | 182852202 | VIEJO 2202 | 0.79514 | 52 | 3.9158e-06 | 0.00020362 | 3339 | 26038.8642 | 0.023248 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5028 | PUEBLO 21031970 | 43292103 | PUEBLO 2103 | 0 | 60 | 3.9099e-06 | 0.00023459 | 3340 | 26038.8642 | 0.023013 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4499 | MORGAN HILL 2109145998 | 83242109 | MORGAN HILL 2109 | 2.5034 | 28 | 3.8997e-06 | 0.00010919 | 3341 | 26041.3676 | 0.022904 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1014 | VIEJO 22019114 | 182852201 | VIEJO 2201 | 6.8226 | 92 | 3.8947e-06 | 0.00035832 | 3342 | 26048.1902 | 0.022546 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
230 | CAROLANDS 04049026 | 24060404 | CAROLANDS 0404 | 0.73595 | 71 | 3.8932e-06 | 0.00027642 | 3343 | 26048.9262 | 0.022269 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10928 | FORT ORD 21069656 | 182402106 | FORT ORD 2106 | 0.11746 | 2 | 3.8714e-06 | 7.7429e-06 | 3344 | 26049.0436 | 0.022262 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5034 | OAKLAND J 1102CR184 | 12091102 | OAKLAND J 1102 | 3.4612 | 43 | 3.8445e-06 | 0.00016531 | 3345 | 26052.5048 | 0.022096 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4211 | FAIRVIEW 2207P142 | 13432207 | FAIRVIEW 2207 | 1.2204 | 41 | 3.8432e-06 | 0.00015757 | 3346 | 26053.7252 | 0.021939 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10430 | BELL 1107643778 | 152701107 | BELL 1107 | 0.168 | 4 | 3.7919e-06 | 1.5168e-05 | 3347 | 26053.8932 | 0.021923 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9697 | DOLAN ROAD 1101882610 | 182381101 | DOLAN ROAD 1101 | 0.1419 | 8 | 3.7868e-06 | 3.0295e-05 | 3348 | 26054.0351 | 0.021893 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
238 | LOS GATOS 1102526868 | 82021102 | LOS GATOS 1102 | 1.1066 | 20 | 3.7614e-06 | 7.5227e-05 | 3349 | 26055.1417 | 0.021818 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7260 | SUMMIT 110158642 | 152591101 | SUMMIT 1101 | 1.7974 | 13 | 3.7548e-06 | 4.8812e-05 | 3350 | 26056.9391 | 0.021769 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
535 | ATASCADERO 11012379 | 182541101 | ATASCADERO 1101 | 0.72801 | 11 | 3.7546e-06 | 4.1301e-05 | 3351 | 26057.6671 | 0.021728 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4492 | DEL MONTE 2103468158 | 182222103 | DEL MONTE 2103 | 0.51374 | 12 | 3.7407e-06 | 4.4889e-05 | 3352 | 26058.1808 | 0.021683 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8753 | HALF MOON BAY 1102650808 | 24101102 | HALF MOON BAY 1102 | 0.52415 | 8 | 3.6894e-06 | 2.9515e-05 | 3353 | 26058.705 | 0.021653 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
43 | WOODSIDE 1104555372 | 24251104 | WOODSIDE 1104 | 4.1545 | 54 | 3.6721e-06 | 0.0001983 | 3354 | 26062.8594 | 0.021455 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10659 | ECHO SUMMIT 110155262 | 158031101 | ECHO SUMMIT 1101 | 0.16565 | 4 | 3.653e-06 | 1.4612e-05 | 3355 | 26063.0251 | 0.021441 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7441 | SAN LUIS OBISPO 110596874 | 182631105 | SAN LUIS OBISPO 1105 | 0.83624 | 16 | 3.6408e-06 | 5.8253e-05 | 3356 | 26063.8613 | 0.021382 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9136 | VIEJO 2204CB | 182852204 | VIEJO 2204 | 2.3167 | 24 | 3.64e-06 | 8.736e-05 | 3357 | 26066.178 | 0.021295 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4971 | EDES 1112CR282 | 13681112 | EDES 1112 | 4.0852 | 45 | 3.6364e-06 | 0.00016364 | 3358 | 26070.2632 | 0.021131 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7343 | ATASCADERO 1101CB | 182541101 | ATASCADERO 1101 | 0.03803 | 24 | 3.6135e-06 | 8.6724e-05 | 3359 | 26070.3012 | 0.021045 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8700 | VIEJO 22029488 | 182852202 | VIEJO 2202 | 0.90765 | 18 | 3.6034e-06 | 6.486e-05 | 3360 | 26071.2088 | 0.02098 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3541 | SEACLIFF 0402558727 | 83500402 | SEACLIFF 0402 | 0.13496 | 22 | 3.5926e-06 | 7.9037e-05 | 3361 | 26071.3438 | 0.020901 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7420 | DEL MONTE 210342226 | 182222103 | DEL MONTE 2103 | 0.58433 | 32 | 3.588e-06 | 0.00011482 | 3362 | 26071.9281 | 0.020786 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7115 | LAS GALLINAS A 1104309087 | 42991104 | LAS GALLINAS A 1104 | 0.188 | 6 | 3.575e-06 | 2.145e-05 | 3363 | 26072.1161 | 0.020764 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5040 | TEMPLETON 2112238418 | 183052112 | TEMPLETON 2112 | 0.20587 | 6 | 3.5615e-06 | 2.1369e-05 | 3364 | 26072.322 | 0.020743 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
77 | ALTO 1124428 | 42031124 | ALTO 1124 | 0 | 21 | 3.5167e-06 | 7.3852e-05 | 3365 | 26072.322 | 0.020669 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
288 | MORGAN HILL 2110XR326 | 83242110 | MORGAN HILL 2110 | 0 | 163 | 3.509e-06 | 0.00057196 | 3366 | 26072.322 | 0.020097 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1912 | SANTA ROSA A 110439786 | 42151104 | SANTA ROSA A 1104 | 0.28262 | 44 | 3.496e-06 | 0.00015383 | 3367 | 26072.6046 | 0.019943 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6503 | VIEJO 22029118 | 182852202 | VIEJO 2202 | 0.78669 | 41 | 3.4915e-06 | 0.00014315 | 3368 | 26073.3913 | 0.0198 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4440 | SANTA ROSA A 1104991788 | 42151104 | SANTA ROSA A 1104 | 0.75952 | 43 | 3.4631e-06 | 0.00014892 | 3369 | 26074.1508 | 0.019651 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8382 | MORGAN HILL 2109XR246 | 83242109 | MORGAN HILL 2109 | 0.044495 | 61 | 3.4559e-06 | 0.00021081 | 3370 | 26074.1953 | 0.019441 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8657 | OCEANO 110376678 | 182601103 | OCEANO 1103 | 0.05516 | 8 | 3.4511e-06 | 2.7609e-05 | 3371 | 26074.2505 | 0.019413 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9324 | ECHO SUMMIT 1101741586 | 158031101 | ECHO SUMMIT 1101 | 0.70714 | 9 | 3.4334e-06 | 3.09e-05 | 3372 | 26074.9576 | 0.019382 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
392 | BELMONT 11038958 | 24031103 | BELMONT 1103 | 3.3803 | 73 | 3.4119e-06 | 0.00024907 | 3373 | 26078.3379 | 0.019133 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9058 | LOS GATOS 1101502026 | 82021101 | LOS GATOS 1101 | 0.11221 | 17 | 3.4024e-06 | 5.784e-05 | 3374 | 26078.4502 | 0.019075 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2028 | HICKS 1116LB16 | 83431116 | HICKS 1116 | 2.734 | 97 | 3.3964e-06 | 0.00032945 | 3375 | 26081.1842 | 0.018746 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10450 | OAKLAND J 1102951816 | 12091102 | OAKLAND J 1102 | 0.3351 | 6 | 3.3923e-06 | 2.0354e-05 | 3376 | 26081.5193 | 0.018725 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3081 | SARATOGA 1103LC40 | 83371103 | SARATOGA 1103 | 0.016639 | 28 | 3.3827e-06 | 9.4717e-05 | 3377 | 26081.5359 | 0.018631 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5298 | SAN LEANDRO U 1109CR182 | 13111109 | SAN LEANDRO U 1109 | 4.8284 | 56 | 3.38e-06 | 0.00018928 | 3378 | 26086.3643 | 0.018441 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9781 | SAN LUIS OBISPO 1108903036 | 182631108 | SAN LUIS OBISPO 1108 | 0.19058 | 5 | 3.3474e-06 | 1.6737e-05 | 3379 | 26086.5549 | 0.018425 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1847 | ALTO 1122CB | 42031122 | ALTO 1122 | 2.2447 | 46 | 3.3325e-06 | 0.0001533 | 3380 | 26088.7995 | 0.018271 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
559 | PACIFICA 110266732 | 22811102 | PACIFICA 1102 | 0.20817 | 23 | 3.3135e-06 | 7.6211e-05 | 3381 | 26089.0077 | 0.018195 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7812 | LUCERNE 11062355 | 43351106 | LUCERNE 1106 | 0.40047 | 13 | 3.2963e-06 | 4.2852e-05 | 3382 | 26089.4082 | 0.018152 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9811 | PACIFICA 1103119798 | 22811103 | PACIFICA 1103 | 0.080612 | 2 | 3.2867e-06 | 6.5735e-06 | 3383 | 26089.4888 | 0.018146 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10195 | ALTO 112081716 | 42031120 | ALTO 1120 | 0.2528 | 5 | 3.2689e-06 | 1.6345e-05 | 3384 | 26089.7416 | 0.018129 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6620 | LOS GATOS 1101950286 | 82021101 | LOS GATOS 1101 | 1.0633 | 17 | 3.2625e-06 | 5.5462e-05 | 3385 | 26090.8049 | 0.018074 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5964 | RALSTON 1102CB | 24141102 | RALSTON 1102 | 0.94477 | 66 | 3.2502e-06 | 0.00021451 | 3386 | 26091.7496 | 0.017859 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8215 | GREENBRAE 1104107508 | 43091104 | GREENBRAE 1104 | 0 | 2 | 3.214e-06 | 6.4279e-06 | 3387 | 26091.7496 | 0.017853 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1635 | OAKLAND K 1101CR172 | 12101101 | OAKLAND K 1101 | 0.56244 | 30 | 3.209e-06 | 9.6271e-05 | 3388 | 26092.3121 | 0.017757 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3774 | PAUL SWEET 210411074 | 83252104 | PAUL SWEET 2104 | 2.9324 | 41 | 3.1905e-06 | 0.00013081 | 3389 | 26095.2445 | 0.017626 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8087 | SAN RAMON 2107MR441 | 14232107 | SAN RAMON 2107 | 0.024985 | 8 | 3.1892e-06 | 2.5513e-05 | 3390 | 26095.2695 | 0.0176 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7720 | SAN RAFAEL 1106764698 | 42011106 | SAN RAFAEL 1106 | 0.082913 | 5 | 3.1867e-06 | 1.5933e-05 | 3391 | 26095.3524 | 0.017584 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3736 | VALLEY VIEW 1105P126 | 14341105 | VALLEY VIEW 1105 | 1.0446 | 25 | 3.1848e-06 | 7.9621e-05 | 3392 | 26096.3971 | 0.017505 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2670 | GREENBRAE 11037315 | 43091103 | GREENBRAE 1103 | 0 | 32 | 3.1589e-06 | 0.00010108 | 3393 | 26096.3971 | 0.017404 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6253 | FORT BRAGG A 110233064 | 42761102 | FORT BRAGG A 1102 | 0 | 49 | 3.15e-06 | 0.00015435 | 3394 | 26096.3971 | 0.017249 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4022 | EDES 1112CR100 | 13681112 | EDES 1112 | 3.3555 | 40 | 3.1366e-06 | 0.00012546 | 3395 | 26099.7526 | 0.017124 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1730 | LOS GATOS 1101CB | 82021101 | LOS GATOS 1101 | 0.029616 | 34 | 3.1364e-06 | 0.00010664 | 3396 | 26099.7822 | 0.017017 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5067 | EL CERRITO G 1112BR178 | 12501112 | EL CERRITO G 1112 | 0.029957 | 93 | 3.1309e-06 | 0.00029117 | 3397 | 26099.8122 | 0.016726 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3732 | SOBRANTE 1101L534R | 14671101 | SOBRANTE 1101 | 0.80294 | 34 | 3.1282e-06 | 0.00010636 | 3398 | 26100.6151 | 0.01662 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4550 | VALLEY VIEW 1106P176 | 14341106 | VALLEY VIEW 1106 | 0.2203 | 44 | 3.1268e-06 | 0.00013758 | 3399 | 26100.8354 | 0.016482 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7024 | VIEJO 220292792 | 182852202 | VIEJO 2202 | 0 | 21 | 3.1236e-06 | 6.5595e-05 | 3400 | 26100.8354 | 0.016416 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8774 | TULUCAY 1101504524 | 42301101 | TULUCAY 1101 | 0.37918 | 15 | 3.1216e-06 | 4.6823e-05 | 3401 | 26101.2146 | 0.01637 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9561 | ATASCADERO 1101747522 | 182541101 | ATASCADERO 1101 | 0.25664 | 16 | 3.1133e-06 | 4.9813e-05 | 3402 | 26101.4712 | 0.01632 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1757 | OAKLAND X 1106121588 | 12541106 | OAKLAND X 1106 | 0.84288 | 27 | 3.0983e-06 | 8.3654e-05 | 3403 | 26102.3141 | 0.016236 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
641 | ALTO 11251256 | 42031125 | ALTO 1125 | 7.46 | 88 | 3.098e-06 | 0.00027263 | 3404 | 26109.7741 | 0.015964 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7693 | SARATOGA 1103595689 | 83371103 | SARATOGA 1103 | 0.027822 | 4 | 3.0826e-06 | 1.233e-05 | 3405 | 26109.802 | 0.015951 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1201 | RINCON 1102640 | 43321102 | RINCON 1102 | 0 | 56 | 3.0722e-06 | 0.00017204 | 3406 | 26109.802 | 0.015779 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8249 | VIEJO 22029089 | 182852202 | VIEJO 2202 | 1.4419 | 20 | 3.0684e-06 | 6.1368e-05 | 3407 | 26111.2438 | 0.015718 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4500 | PACIFICA 1102968736 | 22811102 | PACIFICA 1102 | 0.70371 | 9 | 3.0372e-06 | 2.7334e-05 | 3408 | 26111.9475 | 0.01569 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5121 | BURNEY 110237284 | 103311102 | BURNEY 1102 | 0.18836 | 15 | 3.0199e-06 | 4.5299e-05 | 3409 | 26112.1359 | 0.015645 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3124 | SAN RAFAEL 110648752 | 42011106 | SAN RAFAEL 1106 | 0.014424 | 28 | 2.9974e-06 | 8.3928e-05 | 3410 | 26112.1503 | 0.015561 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
292 | RIDGE 0402CB | 12840402 | RIDGE 0402 | 1.8211 | 31 | 2.9927e-06 | 9.2772e-05 | 3411 | 26113.9715 | 0.015468 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5812 | LAS GALLINAS A 11051218 | 42991105 | LAS GALLINAS A 1105 | 0.066343 | 28 | 2.9904e-06 | 8.3731e-05 | 3412 | 26114.0378 | 0.015385 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5928 | IGNACIO 110584764 | 42481105 | IGNACIO 1105 | 0.21126 | 33 | 2.9818e-06 | 9.8398e-05 | 3413 | 26114.2491 | 0.015286 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
231 | PAUL SWEET 210912828 | 83252109 | PAUL SWEET 2109 | 1.1399 | 66 | 2.9651e-06 | 0.0001957 | 3414 | 26115.389 | 0.015091 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5926 | CASTRO VALLEY 1110CB | 14091110 | CASTRO VALLEY 1110 | 0.32525 | 23 | 2.9632e-06 | 6.8153e-05 | 3415 | 26115.7142 | 0.015023 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8452 | HARRIS 1108395498 | 192431108 | HARRIS 1108 | 0.1063 | 8 | 2.9622e-06 | 2.3698e-05 | 3416 | 26115.8205 | 0.014999 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8569 | IGNACIO 1105683542 | 42481105 | IGNACIO 1105 | 0.13854 | 2 | 2.9468e-06 | 5.8935e-06 | 3417 | 26115.9591 | 0.014993 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6289 | STAFFORD 1101405812 | 43201101 | STAFFORD 1101 | 0.1835 | 7 | 2.9445e-06 | 2.0611e-05 | 3418 | 26116.1426 | 0.014972 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8541 | ROSSMOOR 1106L541R | 14161106 | ROSSMOOR 1106 | 0 | 11 | 2.9324e-06 | 3.2256e-05 | 3419 | 26116.1426 | 0.01494 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3241 | OAKLAND K 1101CB | 12101101 | OAKLAND K 1101 | 0.33465 | 40 | 2.9186e-06 | 0.00011674 | 3420 | 26116.4772 | 0.014823 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6045 | OAKLAND J 1105CR256 | 12091105 | OAKLAND J 1105 | 1.2215 | 27 | 2.9181e-06 | 7.879e-05 | 3421 | 26117.6987 | 0.014745 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8780 | SAN LUIS OBISPO 1108144690 | 182631108 | SAN LUIS OBISPO 1108 | 0.26037 | 10 | 2.905e-06 | 2.905e-05 | 3422 | 26117.9591 | 0.014715 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10157 | CASTRO VALLEY 1108MR233 | 14091108 | CASTRO VALLEY 1108 | 0.23054 | 7 | 2.9035e-06 | 2.0325e-05 | 3423 | 26118.1897 | 0.014695 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3481 | IGNACIO 1105318 | 42481105 | IGNACIO 1105 | 1.7945 | 150 | 2.9031e-06 | 0.00043547 | 3424 | 26119.9841 | 0.01426 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1523 | HAMILTON BRANCH 110187784 | 102361101 | HAMILTON BRANCH 1101 | 1.4473 | 23 | 2.8956e-06 | 6.6598e-05 | 3425 | 26121.4314 | 0.014193 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10922 | PINECREST 0401CB | 163160401 | PINECREST 0401 | 0.013801 | 1 | 2.8911e-06 | 2.8911e-06 | 3426 | 26121.4452 | 0.01419 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1324 | SONOMA 11054456 | 42721105 | SONOMA 1105 | 0 | 62 | 2.8714e-06 | 0.00017803 | 3427 | 26121.4452 | 0.014012 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8419 | SAN CARLOS 1103785521 | 24181103 | SAN CARLOS 1103 | 0.067757 | 3 | 2.8654e-06 | 8.5962e-06 | 3428 | 26121.513 | 0.014004 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6629 | BIG MEADOWS 21012246 | 102812101 | BIG MEADOWS 2101 | 1.8257 | 23 | 2.8555e-06 | 6.5676e-05 | 3429 | 26123.3387 | 0.013938 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
692 | ECHO SUMMIT 11018922 | 158031101 | ECHO SUMMIT 1101 | 1.206 | 11 | 2.852e-06 | 3.1372e-05 | 3430 | 26124.5446 | 0.013907 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5593 | SNEATH LANE 1102CB | 22721102 | SNEATH LANE 1102 | 1.3642 | 37 | 2.8459e-06 | 0.0001053 | 3431 | 26125.9088 | 0.013801 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7382 | VIEJO 220235388 | 182852202 | VIEJO 2202 | 0.32133 | 8 | 2.8344e-06 | 2.2676e-05 | 3432 | 26126.2301 | 0.013779 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5265 | IGNACIO 1103CB | 42481103 | IGNACIO 1103 | 0.21773 | 34 | 2.8181e-06 | 9.5817e-05 | 3433 | 26126.4479 | 0.013683 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9102 | HICKS 1116733078 | 83431116 | HICKS 1116 | 0.34299 | 7 | 2.777e-06 | 1.9439e-05 | 3434 | 26126.7909 | 0.013663 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
199 | OAKLAND K 1103CB | 12101103 | OAKLAND K 1103 | 0.47804 | 66 | 2.758e-06 | 0.00018203 | 3435 | 26127.2689 | 0.013481 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2072 | RALSTON 1101420730 | 24141101 | RALSTON 1101 | 0.80338 | 21 | 2.7513e-06 | 5.7777e-05 | 3436 | 26128.0723 | 0.013423 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8913 | WOOD 0401880795 | 13380401 | WOOD 0401 | 0.10191 | 6 | 2.7412e-06 | 1.6447e-05 | 3437 | 26128.1742 | 0.013407 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7811 | VIEJO 2203947314 | 182852203 | VIEJO 2203 | 0.28676 | 22 | 2.7164e-06 | 5.9761e-05 | 3438 | 26128.461 | 0.013347 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8336 | OLEMA 110137074 | 42291101 | OLEMA 1101 | 0.013639 | 6 | 2.7134e-06 | 1.628e-05 | 3439 | 26128.4746 | 0.013331 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6224 | SAN CARLOS 110479774 | 24181104 | SAN CARLOS 1104 | 0.89241 | 24 | 2.698e-06 | 6.4753e-05 | 3440 | 26129.367 | 0.013266 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2094 | ROB ROY 210512586 | 83692105 | ROB ROY 2105 | 1.8902 | 85 | 2.697e-06 | 0.00022925 | 3441 | 26131.2572 | 0.013037 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8276 | OAKLAND J 1102CR254 | 12091102 | OAKLAND J 1102 | 1.0485 | 20 | 2.6941e-06 | 5.3882e-05 | 3442 | 26132.3057 | 0.012983 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5380 | CASTROVILLE 210436922 | 182352104 | CASTROVILLE 2104 | 0 | 37 | 2.6705e-06 | 9.8808e-05 | 3443 | 26132.3057 | 0.012884 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6593 | FOOTHILL 1101798137 | 182951101 | FOOTHILL 1101 | 0.042272 | 5 | 2.6637e-06 | 1.3319e-05 | 3444 | 26132.348 | 0.012871 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1687 | BIG MEADOWS 21012016 | 102812101 | BIG MEADOWS 2101 | 0.09383 | 65 | 2.6614e-06 | 0.00017299 | 3445 | 26132.4418 | 0.012698 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10145 | GREENBRAE 1104317890 | 43091104 | GREENBRAE 1104 | 0.078205 | 2 | 2.6567e-06 | 5.3133e-06 | 3446 | 26132.52 | 0.012693 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3009 | GREENBRAE 1102CB | 43091102 | GREENBRAE 1102 | 0 | 28 | 2.6553e-06 | 7.4348e-05 | 3447 | 26132.52 | 0.012618 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9193 | LOS GATOS 1106CB | 82021106 | LOS GATOS 1106 | 0.10208 | 11 | 2.651e-06 | 2.9161e-05 | 3448 | 26132.6221 | 0.012589 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6430 | FORT BRAGG A 110465894 | 42761104 | FORT BRAGG A 1104 | 0 | 12 | 2.6468e-06 | 3.1761e-05 | 3449 | 26132.6221 | 0.012557 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6292 | RIO DEL MAR 0401931192 | 83260401 | RIO DEL MAR 0401 | 2.2472 | 87 | 2.6467e-06 | 0.00023026 | 3450 | 26134.8692 | 0.012327 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8372 | LAURELES 11122142 | 182371112 | LAURELES 1112 | 0.094397 | 26 | 2.6301e-06 | 6.8383e-05 | 3451 | 26134.9636 | 0.012259 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4353 | FLORENCE 0401CB | 12690401 | FLORENCE 0401 | 0.64714 | 39 | 2.6231e-06 | 0.0001023 | 3452 | 26135.6108 | 0.012156 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1560 | SANTA ROSA A 1104CB | 42151104 | SANTA ROSA A 1104 | 0.22934 | 76 | 2.617e-06 | 0.00019889 | 3453 | 26135.8401 | 0.011958 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9790 | PAUL SWEET 2109680537 | 83252109 | PAUL SWEET 2109 | 0.22544 | 9 | 2.5979e-06 | 2.3381e-05 | 3454 | 26136.0656 | 0.011934 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9764 | PACIFICA 1102512070 | 22811102 | PACIFICA 1102 | 0.17379 | 5 | 2.586e-06 | 1.293e-05 | 3455 | 26136.2393 | 0.011921 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2324 | ALTO 1124CB | 42031124 | ALTO 1124 | 1.6988 | 81 | 2.5838e-06 | 0.00020929 | 3456 | 26137.9381 | 0.011712 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2547 | CASTRO VALLEY 1102MR204 | 14091102 | CASTRO VALLEY 1102 | 0.20294 | 46 | 2.5759e-06 | 0.00011849 | 3457 | 26138.1411 | 0.011593 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
885 | EDES 1112CR308 | 13681112 | EDES 1112 | 3.2124 | 53 | 2.5524e-06 | 0.00013527 | 3458 | 26141.3535 | 0.011458 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7145 | HICKS 111512494 | 83431115 | HICKS 1115 | 0.1368 | 35 | 2.5505e-06 | 8.9268e-05 | 3459 | 26141.4903 | 0.011369 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
970 | CAYUCOS 1102CB | 182551102 | CAYUCOS 1102 | 0 | 41 | 2.5468e-06 | 0.00010442 | 3460 | 26141.4903 | 0.011265 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7960 | LOS GATOS 1101206248 | 82021101 | LOS GATOS 1101 | 0.051587 | 10 | 2.5435e-06 | 2.5435e-05 | 3461 | 26141.5419 | 0.011239 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2461 | HAMILTON BRANCH 110137436 | 102361101 | HAMILTON BRANCH 1101 | 0.75082 | 33 | 2.5374e-06 | 8.3735e-05 | 3462 | 26142.2927 | 0.011155 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5208 | VIEJO 22029120 | 182852202 | VIEJO 2202 | 1.7763 | 112 | 2.5361e-06 | 0.00028404 | 3463 | 26144.069 | 0.010871 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10027 | PACIFICA 1103398620 | 22811103 | PACIFICA 1103 | 0.47115 | 7 | 2.531e-06 | 1.7717e-05 | 3464 | 26144.5401 | 0.010854 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4053 | OAKLAND X 1105184672 | 12541105 | OAKLAND X 1105 | 1.657 | 46 | 2.5255e-06 | 0.00011617 | 3465 | 26146.1971 | 0.010737 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5327 | FAIRVIEW 2207CB | 13432207 | FAIRVIEW 2207 | 0.24062 | 57 | 2.5112e-06 | 0.00014314 | 3466 | 26146.4377 | 0.010594 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1098 | VIEJO 22012064 | 182852201 | VIEJO 2201 | 0.87595 | 15 | 2.486e-06 | 3.729e-05 | 3467 | 26147.3136 | 0.010557 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3180 | STAFFORD 110242542 | 43201102 | STAFFORD 1102 | 0.53595 | 52 | 2.465e-06 | 0.00012818 | 3468 | 26147.8496 | 0.010429 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4684 | SNEATH LANE 110134438 | 22721101 | SNEATH LANE 1101 | 2.3055 | 67 | 2.4545e-06 | 0.00016445 | 3469 | 26150.1551 | 0.010264 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5609 | BURNEY 110297318 | 103311102 | BURNEY 1102 | 0.18333 | 18 | 2.4455e-06 | 4.4019e-05 | 3470 | 26150.3385 | 0.01022 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3808 | HAMILTON BRANCH 11013049 | 102361101 | HAMILTON BRANCH 1101 | 1.0261 | 23 | 2.4445e-06 | 5.6224e-05 | 3471 | 26151.3646 | 0.010164 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10978 | ALTO 1124965060 | 42031124 | ALTO 1124 | 0.061936 | 1 | 2.4396e-06 | 2.4396e-06 | 3472 | 26151.4265 | 0.010162 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10767 | SAUSALITO 1102758798 | 42491102 | SAUSALITO 1102 | 0.033105 | 2 | 2.4159e-06 | 4.8318e-06 | 3473 | 26151.4596 | 0.010157 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2223 | PAUL SWEET 2109CB | 83252109 | PAUL SWEET 2109 | 0.012889 | 171 | 2.3948e-06 | 0.00040951 | 3474 | 26151.4725 | 0.0097474 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4848 | VALLEY VIEW 1103P160 | 14341103 | VALLEY VIEW 1103 | 0 | 96 | 2.3734e-06 | 0.00022785 | 3475 | 26151.4725 | 0.0095195 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1157 | MORAGA 1105116034 | 13801105 | MORAGA 1105 | 0.33531 | 41 | 2.3641e-06 | 9.6928e-05 | 3476 | 26151.8078 | 0.0094226 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6537 | SNEATH LANE 110275844 | 22721102 | SNEATH LANE 1102 | 0.16947 | 10 | 2.3271e-06 | 2.3271e-05 | 3477 | 26151.9773 | 0.0093993 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1692 | SAN CARLOS 11048846 | 24181104 | SAN CARLOS 1104 | 2.2303 | 61 | 2.3218e-06 | 0.00014163 | 3478 | 26154.2076 | 0.0092577 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5922 | SNEATH LANE 1101CB | 22721101 | SNEATH LANE 1101 | 0.46322 | 19 | 2.3127e-06 | 4.3942e-05 | 3479 | 26154.6708 | 0.0092137 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3263 | SAN LEANDRO U 1109936988 | 13111109 | SAN LEANDRO U 1109 | 6.7688 | 86 | 2.3051e-06 | 0.00019824 | 3480 | 26161.4397 | 0.0090155 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7536 | WILLITS 11021270 | 42661102 | WILLITS 1102 | 0 | 21 | 2.3027e-06 | 4.8357e-05 | 3481 | 26161.4397 | 0.0089671 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2607 | WALDO 0402258792 | 13350402 | WALDO 0402 | 2.9795 | 36 | 2.3019e-06 | 8.287e-05 | 3482 | 26164.4191 | 0.0088843 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2976 | STAFFORD 1101902998 | 43201101 | STAFFORD 1101 | 1.0766 | 81 | 2.2981e-06 | 0.00018615 | 3483 | 26165.4958 | 0.0086981 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
28 | RALSTON 110148936 | 24141101 | RALSTON 1101 | 4.6223 | 86 | 2.2943e-06 | 0.00019731 | 3484 | 26170.118 | 0.0085008 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6723 | VALLEY VIEW 1106P128 | 14341106 | VALLEY VIEW 1106 | 0.11865 | 31 | 2.2678e-06 | 7.0301e-05 | 3485 | 26170.2367 | 0.0084305 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6528 | LAS GALLINAS A 1106206332 | 42991106 | LAS GALLINAS A 1106 | 0.30383 | 7 | 2.2569e-06 | 1.5798e-05 | 3486 | 26170.5405 | 0.0084147 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2106 | SPRUCE 0402BR304 | 13340402 | SPRUCE 0402 | 1.4871 | 53 | 2.2492e-06 | 0.00011921 | 3487 | 26172.0276 | 0.0082955 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3661 | LAS GALLINAS A 1106685656 | 42991106 | LAS GALLINAS A 1106 | 1.1954 | 43 | 2.2325e-06 | 9.5996e-05 | 3488 | 26173.223 | 0.0081995 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3471 | LOS GATOS 110160136 | 82021101 | LOS GATOS 1101 | 0 | 57 | 2.2252e-06 | 0.00012684 | 3489 | 26173.223 | 0.0080727 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4292 | EMERALD LAKE 04028872 | 24080402 | EMERALD LAKE 0402 | 4.5022 | 77 | 2.2015e-06 | 0.00016952 | 3490 | 26177.7252 | 0.0079032 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1116 | SNEATH LANE 110168070 | 22721101 | SNEATH LANE 1101 | 0.23226 | 30 | 2.1953e-06 | 6.5858e-05 | 3491 | 26177.9575 | 0.0078373 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9555 | IGNACIO 1103504941 | 42481103 | IGNACIO 1103 | 0.41221 | 6 | 2.194e-06 | 1.3164e-05 | 3492 | 26178.3697 | 0.0078241 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4494 | VIEJO 22019704 | 182852201 | VIEJO 2201 | 0.48887 | 29 | 2.1872e-06 | 6.3429e-05 | 3493 | 26178.8586 | 0.0077607 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3505 | WOODSIDE 11049030 | 24251104 | WOODSIDE 1104 | 2.0338 | 37 | 2.1865e-06 | 8.0902e-05 | 3494 | 26180.8924 | 0.0076798 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4601 | HATTON 11022070 | 182291102 | HATTON 1102 | 0.52422 | 26 | 2.1767e-06 | 5.6595e-05 | 3495 | 26181.4166 | 0.0076232 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10245 | GREENBRAE 1104972264 | 43091104 | GREENBRAE 1104 | 0 | 4 | 2.1732e-06 | 8.6927e-06 | 3496 | 26181.4166 | 0.0076145 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6525 | HAMILTON BRANCH 11012082 | 102361101 | HAMILTON BRANCH 1101 | 1.5197 | 46 | 2.1552e-06 | 9.9139e-05 | 3497 | 26182.9363 | 0.0075154 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7268 | HICKS 1116203897 | 83431116 | HICKS 1116 | 0.22866 | 9 | 2.1509e-06 | 1.9358e-05 | 3498 | 26183.165 | 0.007496 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5472 | CHESTER 1101656108 | 103181101 | CHESTER 1101 | 0.52126 | 10 | 2.1478e-06 | 2.1478e-05 | 3499 | 26183.6862 | 0.0074745 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
659 | EL CERRITO G 1112BR196 | 12501112 | EL CERRITO G 1112 | 0 | 51 | 2.127e-06 | 0.00010848 | 3500 | 26183.6862 | 0.0073661 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
286 | OAKLAND X 1106CB | 12541106 | OAKLAND X 1106 | 3.2846 | 136 | 2.1195e-06 | 0.00028825 | 3501 | 26186.9709 | 0.0070778 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3401 | VIEJO 22029104 | 182852202 | VIEJO 2202 | 5.6859 | 79 | 2.113e-06 | 0.00016692 | 3502 | 26192.6567 | 0.0069109 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
617 | OAK 0401CB | 12600401 | OAK 0401 | 3.4715 | 68 | 2.0871e-06 | 0.00014192 | 3503 | 26196.1282 | 0.006769 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5991 | VIEJO 22019698 | 182852201 | VIEJO 2201 | 0.57779 | 10 | 2.0607e-06 | 2.0607e-05 | 3504 | 26196.706 | 0.0067484 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2044 | SPRUCE 0401BR316 | 13340401 | SPRUCE 0401 | 4.1073 | 56 | 2.0588e-06 | 0.00011529 | 3505 | 26200.8133 | 0.0066331 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7179 | EL CERRITO G 111257953 | 12501112 | EL CERRITO G 1112 | 0.21956 | 11 | 2.0515e-06 | 2.2566e-05 | 3506 | 26201.0329 | 0.0066105 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5036 | FRANKLIN 1104CB | 13921104 | FRANKLIN 1104 | 0.28979 | 63 | 2.0367e-06 | 0.00012831 | 3507 | 26201.3227 | 0.0064822 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6325 | LOS GATOS 1108CB | 82021108 | LOS GATOS 1108 | 0 | 15 | 2.0334e-06 | 3.0501e-05 | 3508 | 26201.3227 | 0.0064517 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6874 | LOS GATOS 1102CB | 82021102 | LOS GATOS 1102 | 0 | 70 | 2.0154e-06 | 0.00014108 | 3509 | 26201.3227 | 0.0063106 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1424 | PACIFICA 1103CB | 22811103 | PACIFICA 1103 | 0.068073 | 62 | 2.0046e-06 | 0.00012428 | 3510 | 26201.3907 | 0.0061863 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10000 | ALTO 1125781759 | 42031125 | ALTO 1125 | 0.13082 | 4 | 2.0026e-06 | 8.0105e-06 | 3511 | 26201.5216 | 0.0061783 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
254 | HICKS 1116CB | 83431116 | HICKS 1116 | 0.20893 | 165 | 1.9553e-06 | 0.00032262 | 3512 | 26201.7305 | 0.0058557 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1238 | STAFFORD 11021019 | 43201102 | STAFFORD 1102 | 0.26853 | 10 | 1.946e-06 | 1.946e-05 | 3513 | 26201.999 | 0.0058362 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10590 | CHESTER 1102546744 | 103181102 | CHESTER 1102 | 0.26654 | 7 | 1.934e-06 | 1.3538e-05 | 3514 | 26202.2656 | 0.0058227 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6891 | ALTO 1124994213 | 42031124 | ALTO 1124 | 0.12354 | 8 | 1.9051e-06 | 1.5241e-05 | 3515 | 26202.3891 | 0.0058075 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9434 | BERKELEY F 1105849701 | 12061105 | BERKELEY F 1105 | 0.13286 | 2 | 1.8894e-06 | 3.7788e-06 | 3516 | 26202.522 | 0.0058037 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6092 | VIEJO 22049540 | 182852204 | VIEJO 2204 | 1.4417 | 32 | 1.8885e-06 | 6.0431e-05 | 3517 | 26203.9637 | 0.0057433 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9394 | ALTO 1124884949 | 42031124 | ALTO 1124 | 0.19437 | 5 | 1.8768e-06 | 9.3841e-06 | 3518 | 26204.1581 | 0.0057339 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8014 | WALDO 0401965216 | 13350401 | WALDO 0401 | 1.6425 | 21 | 1.868e-06 | 3.9227e-05 | 3519 | 26205.8005 | 0.0056946 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4883 | LAS PULGAS 0401104588 | 24120401 | LAS PULGAS 0401 | 0.36135 | 11 | 1.8653e-06 | 2.0518e-05 | 3520 | 26206.1619 | 0.0056741 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8033 | MORAGA 110531512 | 13801105 | MORAGA 1105 | 0 | 29 | 1.8558e-06 | 5.3819e-05 | 3521 | 26206.1619 | 0.0056203 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4423 | SAN RAFAEL 1105344 | 42011105 | SAN RAFAEL 1105 | 0.81713 | 97 | 1.8552e-06 | 0.00017996 | 3522 | 26206.979 | 0.0054403 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3011 | PERRY 1101W52 | 183071101 | PERRY 1101 | 3.1282 | 51 | 1.8539e-06 | 9.4548e-05 | 3523 | 26210.1072 | 0.0053458 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2767 | EL CERRITO G 1112BR180 | 12501112 | EL CERRITO G 1112 | 0.41956 | 25 | 1.8513e-06 | 4.6282e-05 | 3524 | 26210.5268 | 0.0052995 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7505 | EDES 1112CR306 | 13681112 | EDES 1112 | 1.0066 | 16 | 1.8377e-06 | 2.9404e-05 | 3525 | 26211.5334 | 0.0052701 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
349 | ALHAMBRA 1102CB | 14101102 | ALHAMBRA 1102 | 0.26794 | 75 | 1.7835e-06 | 0.00013376 | 3526 | 26211.8013 | 0.0051363 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5900 | CHESTER 1102CB | 103181102 | CHESTER 1102 | 0.025045 | 38 | 1.7766e-06 | 6.751e-05 | 3527 | 26211.8264 | 0.0050688 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6024 | WOODSIDE 11028862 | 24251102 | WOODSIDE 1102 | 0 | 38 | 1.7665e-06 | 6.7125e-05 | 3528 | 26211.8264 | 0.0050017 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4122 | BURNEY 110257046 | 103311102 | BURNEY 1102 | 0.030397 | 12 | 1.7587e-06 | 2.1104e-05 | 3529 | 26211.8568 | 0.0049806 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2110 | CASTRO VALLEY 1108MR205 | 14091108 | CASTRO VALLEY 1108 | 0 | 73 | 1.7478e-06 | 0.00012759 | 3530 | 26211.8568 | 0.004853 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2448 | VIEJO 22029112 | 182852202 | VIEJO 2202 | 0.84488 | 43 | 1.7421e-06 | 7.4909e-05 | 3531 | 26212.7016 | 0.0047781 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8885 | EL CERRITO G 1110BR236 | 12501110 | EL CERRITO G 1110 | 0.50957 | 7 | 1.7373e-06 | 1.2161e-05 | 3532 | 26213.2112 | 0.004766 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7598 | ALTO 1123820379 | 42031123 | ALTO 1123 | 0.15245 | 2 | 1.7362e-06 | 3.4724e-06 | 3533 | 26213.3637 | 0.0047625 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1294 | VIEJO 2203573610 | 182852203 | VIEJO 2203 | 0 | 41 | 1.7259e-06 | 7.0764e-05 | 3534 | 26213.3637 | 0.0046917 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2844 | SAN CARLOS 11039148 | 24181103 | SAN CARLOS 1103 | 0 | 51 | 1.7214e-06 | 8.7791e-05 | 3535 | 26213.3637 | 0.0046039 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
469 | VIEJO 22039094 | 182852203 | VIEJO 2203 | 0.099611 | 32 | 1.7132e-06 | 5.4823e-05 | 3536 | 26213.4633 | 0.0045491 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7298 | VIEJO 22032634 | 182852203 | VIEJO 2203 | 0 | 23 | 1.6721e-06 | 3.8458e-05 | 3537 | 26213.4633 | 0.0045106 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8157 | OAKLAND J 1105CR150 | 12091105 | OAKLAND J 1105 | 0.21662 | 6 | 1.667e-06 | 1.0002e-05 | 3538 | 26213.6799 | 0.0045006 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7733 | FORT BRAGG A 1103CB | 42761103 | FORT BRAGG A 1103 | 0.094139 | 40 | 1.6633e-06 | 6.6534e-05 | 3539 | 26213.774 | 0.0044341 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9029 | MORGAN HILL 2105375239 | 83242105 | MORGAN HILL 2105 | 0.090219 | 4 | 1.6455e-06 | 6.5821e-06 | 3540 | 26213.8642 | 0.0044275 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9198 | MORGAN HILL 2105345099 | 83242105 | MORGAN HILL 2105 | 0.1823 | 5 | 1.6312e-06 | 8.156e-06 | 3541 | 26214.0465 | 0.0044194 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8274 | SALT SPRINGS 21013116 | 163692101 | SALT SPRINGS 2101 | 0.77748 | 10 | 1.6267e-06 | 1.6267e-05 | 3542 | 26214.824 | 0.0044031 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1788 | BERKELEY F 0402502466 | 12060402 | BERKELEY F 0402 | 0.14047 | 10 | 1.6151e-06 | 1.6151e-05 | 3543 | 26214.9645 | 0.004387 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2459 | BERKELEY F 1105CB | 12061105 | BERKELEY F 1105 | 1.0374 | 103 | 1.6033e-06 | 0.00016514 | 3544 | 26216.0019 | 0.0042218 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
179 | EL CERRITO G 1108BR346 | 12501108 | EL CERRITO G 1108 | 0 | 102 | 1.5894e-06 | 0.00016212 | 3545 | 26216.0019 | 0.0040597 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1332 | HOLLYWOOD 0401CB | 13170401 | HOLLYWOOD 0401 | 2.862 | 70 | 1.5619e-06 | 0.00010933 | 3546 | 26218.8639 | 0.0039504 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6502 | ESTUDILLO 0401850884 | 13480401 | ESTUDILLO 0401 | 0.85032 | 19 | 1.5552e-06 | 2.9549e-05 | 3547 | 26219.7142 | 0.0039208 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1386 | PACIFICA 1103915474 | 22811103 | PACIFICA 1103 | 0.43345 | 98 | 1.5073e-06 | 0.00014771 | 3548 | 26220.1476 | 0.0037731 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1210 | COTATI 110283200 | 42271102 | COTATI 1102 | 0 | 48 | 1.471e-06 | 7.0606e-05 | 3549 | 26220.1476 | 0.0037025 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7453 | SNEATH LANE 110748338 | 22721107 | SNEATH LANE 1107 | 0.11259 | 17 | 1.4569e-06 | 2.4768e-05 | 3550 | 26220.2602 | 0.0036777 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4821 | RALSTON 11029126 | 24141102 | RALSTON 1102 | 1.0077 | 25 | 1.4329e-06 | 3.5823e-05 | 3551 | 26221.2679 | 0.0036419 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7237 | PACIFIC GROVE 04222614 | 182440422 | PACIFIC GROVE 0422 | 0.64463 | 28 | 1.4317e-06 | 4.0087e-05 | 3552 | 26221.9126 | 0.0036018 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1100 | DEL MONTE 210386496 | 182222103 | DEL MONTE 2103 | 0.99474 | 94 | 1.4269e-06 | 0.00013413 | 3553 | 26222.9073 | 0.0034677 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8851 | SAN CARLOS 1103888954 | 24181103 | SAN CARLOS 1103 | 0 | 6 | 1.4152e-06 | 8.4914e-06 | 3554 | 26222.9073 | 0.0034592 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2645 | OAKLAND J 1106CR164 | 12091106 | OAKLAND J 1106 | 1.495 | 85 | 1.4079e-06 | 0.00011967 | 3555 | 26224.4023 | 0.0033395 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7417 | EL CERRITO G 1112209865 | 12501112 | EL CERRITO G 1112 | 0.2629 | 11 | 1.4074e-06 | 1.5482e-05 | 3556 | 26224.6652 | 0.003324 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
45 | OAKLAND J 1105153228 | 12091105 | OAKLAND J 1105 | 0.28806 | 54 | 1.4041e-06 | 7.5821e-05 | 3557 | 26224.9532 | 0.0032482 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8437 | SWIFT 2109XR300 | 83392109 | SWIFT 2109 | 0.32738 | 14 | 1.3951e-06 | 1.9531e-05 | 3558 | 26225.2806 | 0.0032287 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10517 | EL CERRITO G 1110173396 | 12501110 | EL CERRITO G 1110 | 0.16516 | 3 | 1.3889e-06 | 4.1666e-06 | 3559 | 26225.4458 | 0.0032245 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9170 | SAN CARLOS 1103313472 | 24181103 | SAN CARLOS 1103 | 0.026825 | 9 | 1.3509e-06 | 1.2158e-05 | 3560 | 26225.4726 | 0.0032124 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9880 | IGNACIO 1103151462 | 42481103 | IGNACIO 1103 | 0.15399 | 3 | 1.3417e-06 | 4.025e-06 | 3561 | 26225.6266 | 0.0032083 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8103 | WOODSIDE 1102472928 | 24251102 | WOODSIDE 1102 | 0.077579 | 14 | 1.3331e-06 | 1.8663e-05 | 3562 | 26225.7042 | 0.0031897 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
657 | OAKLAND J 1102CR252 | 12091102 | OAKLAND J 1102 | 1.0971 | 92 | 1.3184e-06 | 0.0001213 | 3563 | 26226.8013 | 0.0030684 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
146 | CASTRO VALLEY 1110MR379 | 14091110 | CASTRO VALLEY 1110 | 1.0874 | 22 | 1.3088e-06 | 2.8794e-05 | 3564 | 26227.8887 | 0.0030396 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9441 | MORRO BAY 11013487 | 183011101 | MORRO BAY 1101 | 0 | 20 | 1.2622e-06 | 2.5244e-05 | 3565 | 26227.8887 | 0.0030143 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5751 | FORT BRAGG A 1104CB | 42761104 | FORT BRAGG A 1104 | 0.0738 | 41 | 1.2596e-06 | 5.1642e-05 | 3566 | 26227.9625 | 0.0029627 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8075 | ALTO 1124246034 | 42031124 | ALTO 1124 | 0.12572 | 4 | 1.2578e-06 | 5.0314e-06 | 3567 | 26228.0882 | 0.0029577 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
447 | OCEANO 1105V44 | 182601105 | OCEANO 1105 | 0.78295 | 17 | 1.2575e-06 | 2.1378e-05 | 3568 | 26228.8711 | 0.0029363 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3262 | OAKLAND J 1106CR330 | 12091106 | OAKLAND J 1106 | 0.7182 | 31 | 1.2463e-06 | 3.8635e-05 | 3569 | 26229.5893 | 0.0028977 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
650 | OAKLAND J 1116CR328 | 12091116 | OAKLAND J 1116 | 0.59424 | 68 | 1.2458e-06 | 8.4712e-05 | 3570 | 26230.1836 | 0.0028129 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4530 | VIEJO 220285904 | 182852202 | VIEJO 2202 | 1.0472 | 24 | 1.2443e-06 | 2.9864e-05 | 3571 | 26231.2308 | 0.0027831 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4873 | ALHAMBRA 110213333 | 14101102 | ALHAMBRA 1102 | 0.043994 | 4 | 1.2398e-06 | 4.9594e-06 | 3572 | 26231.2748 | 0.0027781 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5686 | MORRO BAY 1102V80 | 183011102 | MORRO BAY 1102 | 0.13844 | 28 | 1.2121e-06 | 3.3939e-05 | 3573 | 26231.4132 | 0.0027442 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
495 | BELMONT 11109090 | 24031110 | BELMONT 1110 | 0 | 38 | 1.2039e-06 | 4.5748e-05 | 3574 | 26231.4132 | 0.0026984 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1032 | ALTO 1123CB | 42031123 | ALTO 1123 | 0.5554 | 84 | 1.1648e-06 | 9.7839e-05 | 3575 | 26231.9686 | 0.0026006 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4356 | BELMONT 11038956 | 24031103 | BELMONT 1103 | 0.29497 | 18 | 1.1529e-06 | 2.0752e-05 | 3576 | 26232.2636 | 0.0025798 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3862 | GREENBRAE 1104751 | 43091104 | GREENBRAE 1104 | 0.16446 | 31 | 1.1521e-06 | 3.5714e-05 | 3577 | 26232.4281 | 0.0025441 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3522 | CHESTER 1101CB | 103181101 | CHESTER 1101 | 0.080148 | 69 | 1.1453e-06 | 7.9023e-05 | 3578 | 26232.5082 | 0.0024651 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1797 | BERKELEY F 1103BR110 | 12061103 | BERKELEY F 1103 | 0 | 45 | 1.1415e-06 | 5.1365e-05 | 3579 | 26232.5082 | 0.0024137 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3950 | MONTEREY 04022644 | 182090402 | MONTEREY 0402 | 1.1362 | 23 | 1.1355e-06 | 2.6115e-05 | 3580 | 26233.6444 | 0.0023876 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3110 | KIRKER 2104CB | 14452104 | KIRKER 2104 | 0.04631 | 140 | 1.1257e-06 | 0.0001576 | 3581 | 26233.6907 | 0.00223 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
973 | DEL MONTE 110138582 | 182221101 | DEL MONTE 1101 | 0.53069 | 53 | 1.1245e-06 | 5.9598e-05 | 3582 | 26234.2214 | 0.0021704 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
72 | PACIFICA 11026783 | 22811102 | PACIFICA 1102 | 0 | 50 | 1.1229e-06 | 5.6147e-05 | 3583 | 26234.2214 | 0.0021143 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6129 | PERRY 1101W12 | 183071101 | PERRY 1101 | 3.7577 | 70 | 1.0833e-06 | 7.5829e-05 | 3584 | 26237.9791 | 0.0020385 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3828 | ALTO 1120500 | 42031120 | ALTO 1120 | 0.2649 | 39 | 1.0777e-06 | 4.203e-05 | 3585 | 26238.244 | 0.0019964 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2036 | SAN LEANDRO U 1114MR218 | 13111114 | SAN LEANDRO U 1114 | 6.4554 | 134 | 1.0693e-06 | 0.00014329 | 3586 | 26244.6994 | 0.0018531 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
66 | OAKLAND X 1105CB | 12541105 | OAKLAND X 1105 | 1.0411 | 153 | 1.0578e-06 | 0.00016184 | 3587 | 26245.7405 | 0.0016913 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3740 | BERKELEY F 0402CB | 12060402 | BERKELEY F 0402 | 0.029225 | 21 | 1.0552e-06 | 2.2159e-05 | 3588 | 26245.7698 | 0.0016691 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2665 | VALLEY VIEW 1105P190 | 14341105 | VALLEY VIEW 1105 | 0 | 28 | 1.0539e-06 | 2.951e-05 | 3589 | 26245.7698 | 0.0016396 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
62 | BAY MEADOWS 2102CB | 24012102 | BAY MEADOWS 2102 | 0.099037 | 95 | 1.0373e-06 | 9.8546e-05 | 3590 | 26245.8688 | 0.0015411 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3225 | VALLEY VIEW 1105CB | 14341105 | VALLEY VIEW 1105 | 0 | 59 | 1.0169e-06 | 5.9995e-05 | 3591 | 26245.8688 | 0.0014811 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1682 | OAKLAND J 1118CR198 | 12091118 | OAKLAND J 1118 | 0.32037 | 70 | 1.006e-06 | 7.0418e-05 | 3592 | 26246.1892 | 0.0014107 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6551 | EL CERRITO G 1111760530 | 12501111 | EL CERRITO G 1111 | 0.21291 | 13 | 9.624e-07 | 1.2511e-05 | 3593 | 26246.4021 | 0.0013982 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
838 | MORRO BAY 1102W22 | 183011102 | MORRO BAY 1102 | 2.5943 | 85 | 9.5877e-07 | 8.1495e-05 | 3594 | 26248.9964 | 0.0013167 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2660 | CASTRO VALLEY 1105MR201 | 14091105 | CASTRO VALLEY 1105 | 1.252 | 112 | 9.5698e-07 | 0.00010718 | 3595 | 26250.2483 | 0.0012095 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6961 | SAUSALITO 11021224 | 42491102 | SAUSALITO 1102 | 0.010738 | 29 | 9.3531e-07 | 2.7124e-05 | 3596 | 26250.2591 | 0.0011824 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2515 | EL CERRITO G 1113CB | 12501113 | EL CERRITO G 1113 | 0.098306 | 63 | 9.1814e-07 | 5.7843e-05 | 3597 | 26250.3574 | 0.0011245 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3037 | EL CERRITO G 1108CB | 12501108 | EL CERRITO G 1108 | 0.0026991 | 99 | 9.0819e-07 | 8.9911e-05 | 3598 | 26250.3601 | 0.0010346 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2758 | VALLEY VIEW 1105P124 | 14341105 | VALLEY VIEW 1105 | 0 | 43 | 9.0411e-07 | 3.8877e-05 | 3599 | 26250.3601 | 0.00099572 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3672 | EDES 1112CB | 13681112 | EDES 1112 | 0.043792 | 16 | 8.9903e-07 | 1.4384e-05 | 3600 | 26250.4039 | 0.00098134 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2376 | VIEJO 22049110 | 182852204 | VIEJO 2204 | 0.29392 | 58 | 8.7872e-07 | 5.0966e-05 | 3601 | 26250.6978 | 0.00093037 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
552 | ALTO 112088190 | 42031120 | ALTO 1120 | 0.10133 | 34 | 8.5763e-07 | 2.9159e-05 | 3602 | 26250.7991 | 0.00090121 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5498 | VIEJO 22049440 | 182852204 | VIEJO 2204 | 0.076905 | 55 | 8.5438e-07 | 4.6991e-05 | 3603 | 26250.876 | 0.00085422 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10858 | SOLEDAD 2101125484 | 182052101 | SOLEDAD 2101 | 0.74739 | 4 | 8.4928e-07 | 3.3971e-06 | 3604 | 26251.6234 | 0.00085082 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
10655 | OCEANO 1104793774 | 182601104 | OCEANO 1104 | 0.069539 | 3 | 8.3998e-07 | 2.52e-06 | 3605 | 26251.6929 | 0.0008483 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4160 | EL CERRITO G 1110CB | 12501110 | EL CERRITO G 1110 | 0.26297 | 35 | 8.2339e-07 | 2.8819e-05 | 3606 | 26251.9559 | 0.00081949 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5087 | EDES 1112714759 | 13681112 | EDES 1112 | 0.22493 | 11 | 8.1071e-07 | 8.9178e-06 | 3607 | 26252.1808 | 0.00081057 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2691 | BOSTON 0401CR242 | 13320401 | BOSTON 0401 | 0.31043 | 59 | 8.0537e-07 | 4.7517e-05 | 3608 | 26252.4913 | 0.00076305 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
425 | CASTRO VALLEY 1105MR236 | 14091105 | CASTRO VALLEY 1105 | 1.3753 | 112 | 8.0193e-07 | 8.9816e-05 | 3609 | 26253.8666 | 0.00067323 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5569 | MORRO BAY 1101CB | 183011101 | MORRO BAY 1101 | 0 | 28 | 8.0102e-07 | 2.2429e-05 | 3610 | 26253.8666 | 0.00065081 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
513 | OAKLAND J 1116CB | 12091116 | OAKLAND J 1116 | 0 | 253 | 7.8965e-07 | 0.00019978 | 3611 | 26253.8666 | 0.00045102 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4433 | MONTEREY 04012642 | 182090401 | MONTEREY 0401 | 0 | 28 | 7.8793e-07 | 2.2062e-05 | 3612 | 26253.8666 | 0.00042896 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1060 | SAN LEANDRO U 1114MR545 | 13111114 | SAN LEANDRO U 1114 | 2.1728 | 66 | 7.6919e-07 | 5.0766e-05 | 3613 | 26256.0394 | 0.0003782 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8159 | SAN LUIS OBISPO 1103191498 | 182631103 | SAN LUIS OBISPO 1103 | 0.118 | 2 | 7.2794e-07 | 1.4559e-06 | 3614 | 26256.1574 | 0.00037674 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
749 | WALDO 0401CB | 13350401 | WALDO 0401 | 0 | 56 | 6.8547e-07 | 3.8386e-05 | 3615 | 26256.1574 | 0.00033835 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8960 | OCEANO 1104337754 | 182601104 | OCEANO 1104 | 0.060732 | 3 | 6.1054e-07 | 1.8316e-06 | 3616 | 26256.2181 | 0.00033652 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
11035 | SOLEDAD 2101404754 | 182052101 | SOLEDAD 2101 | 0.86267 | 2 | 5.7048e-07 | 1.141e-06 | 3617 | 26257.0808 | 0.00033538 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
2616 | DEL MONTE 21029060 | 182222102 | DEL MONTE 2102 | 0.94774 | 98 | 5.5361e-07 | 5.4254e-05 | 3618 | 26258.0285 | 0.00028113 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3316 | SAN LEANDRO U 1114501762 | 13111114 | SAN LEANDRO U 1114 | 0.4817 | 23 | 5.5098e-07 | 1.2672e-05 | 3619 | 26258.5102 | 0.00026845 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
9297 | PACIFICA 1102934870 | 22811102 | PACIFICA 1102 | 0.091704 | 7 | 5.496e-07 | 3.8472e-06 | 3620 | 26258.602 | 0.00026461 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
7940 | SAN LEANDRO U 1109CR284 | 13111109 | SAN LEANDRO U 1109 | 0.76807 | 14 | 5.1364e-07 | 7.191e-06 | 3621 | 26259.37 | 0.00025742 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3930 | SAN LEANDRO U 1109CR002 | 13111109 | SAN LEANDRO U 1109 | 0.16771 | 16 | 5.1358e-07 | 8.2173e-06 | 3622 | 26259.5377 | 0.0002492 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
5801 | BELMONT 1110330790 | 24031110 | BELMONT 1110 | 0.12403 | 8 | 5.0999e-07 | 4.0799e-06 | 3623 | 26259.6618 | 0.00024512 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
915 | WALDO 0402CB | 13350402 | WALDO 0402 | 0 | 27 | 5.064e-07 | 1.3673e-05 | 3624 | 26259.6618 | 0.00023145 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
472 | BANCROFT 0401CB | 13030401 | BANCROFT 0401 | 0.043075 | 103 | 4.9968e-07 | 5.1467e-05 | 3625 | 26259.7048 | 0.00017998 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4940 | BERKELEY T 0404CB | 12660404 | BERKELEY T 0404 | 0 | 20 | 4.9106e-07 | 9.8213e-06 | 3626 | 26259.7048 | 0.00017016 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
206 | PACIFICA 110252715 | 22811102 | PACIFICA 1102 | 0 | 60 | 4.8039e-07 | 2.8824e-05 | 3627 | 26259.7048 | 0.00014133 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
4875 | OCEANO 1105V48 | 182601105 | OCEANO 1105 | 0.12351 | 39 | 4.6154e-07 | 1.8e-05 | 3628 | 26259.8283 | 0.00012333 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3910 | SAN LEANDRO U 1114458451 | 13111114 | SAN LEANDRO U 1114 | 1.2228 | 29 | 4.5289e-07 | 1.3134e-05 | 3629 | 26261.0511 | 0.0001102 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1300 | BANCROFT 0402CB | 13030402 | BANCROFT 0402 | 0.37117 | 58 | 4.3467e-07 | 2.5211e-05 | 3630 | 26261.4223 | 8.4989e-05 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
1186 | VIEJO 220436948 | 182852204 | VIEJO 2204 | 0.50319 | 109 | 3.9816e-07 | 4.34e-05 | 3631 | 26261.9255 | 4.1589e-05 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
8981 | CASTRO VALLEY 1105132304 | 14091105 | CASTRO VALLEY 1105 | 0.07375 | 13 | 3.785e-07 | 4.9205e-06 | 3632 | 26261.9992 | 3.6669e-05 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
3358 | FORT BRAGG A 110436526 | 42761104 | FORT BRAGG A 1104 | 0.044913 | 84 | 3.6398e-07 | 3.0574e-05 | 3633 | 26262.0442 | 6.0945e-06 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
6760 | MORRO BAY 1101W04 | 183011101 | MORRO BAY 1101 | 0.27175 | 26 | 2.344e-07 | 6.0945e-06 | 3634 | 26262.3159 | 2.6486e-11 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
11118 | DIABLO CANYON 1101CB | 189001101 | DIABLO CANYON 1101 | 0 |  |  | 0 | 3635 | 26262.3159 | 2.6486e-11 | #N/A | #N/A | FALSE | 0 | FALSE | FALSE
| Various | [11 empty] | TRUE | 31.8 | TRUE | TRUE

## Approved CPZ List (hidden)
Unique ID for each Circuit Protection Zone. | Unique name for each Circuit Protection Zone. | Unique ID for each circuit. | Unique name for each circuit. | Total miles in each . | Number of 100mx100m pixels in each CPZ. As the risk model has the risk score at this 100mx100m pixel level | Average - Multi Attribute Value Framework (MAVF) risk score per pixel; used to rank the CPZs from riskiest to least risky. The MAVF developed via regulatory proceedings | Total risk associated with each CPZ, per the 2021 approved conductor risk model. | Rank of CPZs based on the average risk score (mean_mavf_core_risk). | Number of active projects / jobs within the CPZ. | #N/A | Number of miles in the scoping phase. | Number of miles in the estimating phase. | Number of miles in the decency clearing phase. | Number of miles in the construction phase. | Number of miles in the close-out phase. | Justification for approval of work in the CPZ by WGC. | Date work was approved for scoping by the WGC.
PZ_idx | circuit_protection_zone_id | feeder_id | feeder_name | Miles | pixel_count | mean_mavf_core_risk | Total Risk Value | mean_mavf_core_risk_rank | Number of Projects | Planned Miles | Scoping | Estimating | Dependencies | Construction | Close-out | Work Bucket | Date Approved
10544 | OREGON TRAIL 1103CUS391 | 103521103 | OREGON TRAIL 1103 | 0.022596 | 1 | 3.1639 | 3.1639 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
11024 | CALPINE 1144276-G | 48011144 | CALPINE 1144 | 0.014759 | 1 | 1.8786 | 1.8786 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
9665 | MARIPOSA 210190130 | 254452101 | MARIPOSA 2101 | 0.09394 | 1 | 1.6924 | 1.6924 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
9783 | SHEPHERD 2111688294 | 252062111 | SHEPHERD 2111 | 0.01514 | 1 | 1.4425 | 1.4425 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10354 | MIDDLETOWN 1103CB | 43141103 | MIDDLETOWN 1103 | 0.052975 | 4 | 1.3006 | 5.2026 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10600 | UPPER LAKE 1101CB | 42871101 | UPPER LAKE 1101 | 1.1133 | 3 | 1.2559 | 3.7676 | 6 | 1 | 1.1055 | 1.1055 | 0 | 0 | 0 | 0 | Top 50 Miles | 2020-11-13
8894 | KESWICK 11011586 | 103451101 | KESWICK 1101 | 7.4478 | 39 | 1.2524 | 48.8434 | 7 | 6 | 9.1078 | 9.1078 | 0 | 0 | 0 | 0 | Top 50 Miles | 2020-11-13
6776 | MIDDLETOWN 1102302610 | 43141102 | MIDDLETOWN 1102 | 4.7058 | 53 | 0.91632 | 48.565 | 8 | 7 | 6.8034 | 6.8034 | 0 | 0 | 0 | 0 | Top 50 Miles | 2020-11-13
2373 | KONOCTI 1102965078 | 43311102 | KONOCTI 1102 | 6.2704 | 59 | 0.87629 | 51.7008 | 9 | 3 | 3.1468 | 0 | 3.1468 | 0 | 0 | 0 | Top 50 Miles | 2020-11-13
5527 | MARIPOSA 2102241564 | 254452102 | MARIPOSA 2102 | 0.71281 | 14 | 0.77248 | 10.8148 | 10 | 1 | 0.71 | 0 | 0.71 | 0 | 0 | 0 | Top 50 Miles | 2020-11-13
7968 | BUCKS CREEK 1101CB | 102211101 | BUCKS CREEK 1101 | 4.8008 | 13 | 0.73491 | 9.5539 | 11 | 3 | 5.4104 | 0 | 5.4104 | 0 | 0 | 0 | Top 50 Miles | 2020-11-13
10918 | DEL MAR 2109378446 | 152582109 | DEL MAR 2109 | 0.098166 | 3 | 0.73151 | 2.1945 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
6966 | MIDDLETOWN 1102CB | 43141102 | MIDDLETOWN 1102 | 0.46739 | 12 | 0.72481 | 8.6977 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
3511 | MIDDLETOWN 1103830 | 43141103 | MIDDLETOWN 1103 | 27.7328 | 212 | 0.71618 | 151.8291 | 14 | 19 | 23.9445 | 23.9445 | 0 | 0 | 0 | 0 | Top 50 Miles | 2020-11-13
9537 | POSO MOUNTAIN 2104CB | 253642104 | POSO MOUNTAIN 2104 | 5.3534 | 38 | 0.70423 | 26.7607 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10827 | INDIAN FLAT 11044440 | 252691104 | INDIAN FLAT 1104 | 0.23386 | 4 | 0.68656 | 2.7463 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10242 | ELK CREEK 1101CB | 102781101 | ELK CREEK 1101 | 0.084235 | 1 | 0.67079 | 0.67079 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
5791 | TIDEWATER 210614072 | 14652106 | TIDEWATER 2106 | 3.6652 | 30 | 0.65331 | 19.5994 | 18 | 3 | 3.64 | 2.44 | 1.2 | 0 | 0 | 0 | Top 50 Miles | 2020-11-13
10735 | HARTLEY 1101980662 | 43211101 | HARTLEY 1101 | 0.22763 | 3 | 0.64187 | 1.9256 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10532 | VACA DIXON 1101126774 | 63591101 | VACA DIXON 1101 | 0.78766 | 11 | 0.62029 | 6.8232 | 20 | 1 | 0.39811 | 0 | 0 | 0.39811 | 0 | 0 | Top 250 Miles | 2020-11-13
10277 | KIRKER 2104442850 | 14452104 | KIRKER 2104 | 5.7542 | 30 | 0.61454 | 18.4361 | 21 | 2 | 5.44 | 5.44 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
8742 | COARSEGOLD 2104CB | 254432104 | COARSEGOLD 2104 | 2.4277 | 27 | 0.59573 | 16.0848 | 22 | 4 | 8.2815 | 0 | 8.2815 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
8905 | MIDDLETOWN 1101118494 | 43141101 | MIDDLETOWN 1101 | 1.0659 | 12 | 0.58092 | 6.971 | 23 | 2 | 1.33 | 0.61 | 0.72 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10515 | STAFFORD 1102784704 | 43201102 | STAFFORD 1102 | 0.027274 | 1 | 0.564 | 0.564 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10181 | PEABODY 2108113684 | 63642108 | PEABODY 2108 | 0.36709 | 4 | 0.55276 | 2.211 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
7688 | PEABODY 2106250154 | 63642106 | PEABODY 2106 | 0.28499 | 4 | 0.55243 | 2.2097 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
7743 | HIGHLANDS 1102628 | 43361102 | HIGHLANDS 1102 | 14.2224 | 51 | 0.5487 | 27.9838 | 27 | 13 | 23.057 | 23.057 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
6480 | TASSAJARA 21123202 | 14662112 | TASSAJARA 2112 | 0.39174 | 9 | 0.53731 | 4.8358 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10043 | WYANDOTTE 110932586 | 102911109 | WYANDOTTE 1109 | 1.3417 | 15 | 0.52987 | 7.9481 | 29 | 2 | 1.3019 | 0.45758 | 0.84432 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10052 | POSO MOUNTAIN 2103CB | 253642103 | POSO MOUNTAIN 2103 | 2.3287 | 10 | 0.51619 | 5.1619 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10924 | CALPINE 1146200-G | 48011146 | CALPINE 1146 | 0.0085246 | 1 | 0.50979 | 0.50979 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
11090 | CALPINE 1146394G | 48011146 | CALPINE 1146 | 0.011292 | 1 | 0.50979 | 0.50979 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
4828 | CRESTA 1101546650 | 102251101 | CRESTA 1101 | 0.89694 | 6 | 0.50291 | 3.0174 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
9923 | CLOVERDALE 110247214 | 42821102 | CLOVERDALE 1102 | 0.027329 | 1 | 0.48427 | 0.48427 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
8034 | MARIPOSA 2102CB | 254452102 | MARIPOSA 2102 | 5.2539 | 31 | 0.47165 | 14.6212 | 35 | 2 | 2.85 | 0 | 2.85 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
7873 | MARIPOSA 210197142 | 254452101 | MARIPOSA 2101 | 4.6029 | 40 | 0.47122 | 18.8487 | 36 | 4 | 4.5636 | 0 | 3.1011 | 1.4625 | 0 | 0 | Top 250 Miles | 2020-11-13
4526 | VACA DIXON 110540092 | 63591105 | VACA DIXON 1105 | 23.1653 | 464 | 0.46772 | 217.022 | 37 | 12 | 30.58 | 30.58 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
2215 | MIDDLETOWN 1101481876 | 43141101 | MIDDLETOWN 1101 | 0.8534 | 14 | 0.46769 | 6.5476 | 38 | 1 | 0.85436 | 0 | 0.85436 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
9655 | VOLTA 110149742 | 102541101 | VOLTA 1101 | 3.4766 | 28 | 0.46433 | 13.0013 | 39 | 1 | 3.461 | 0 | 3.461 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10699 | SUNOL 110148180 | 14241101 | SUNOL 1101 | 0.013145 | 2 | 0.46103 | 0.92206 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
7414 | PUTAH CREEK 110246012 | 63681102 | PUTAH CREEK 1102 | 0.63713 | 38 | 0.45557 | 17.3115 | 41 | 1 | 0.52 | 0 | 0 | 0.52 | 0 | 0 | Top 250 Miles | 2020-11-13
4076 | VACAVILLE 11046542 | 63601104 | VACAVILLE 1104 | 14.6602 | 140 | 0.44642 | 62.4985 | 42 | 11 | 14.73 | 14.73 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
7056 | POTTER VALLEY P H 110564118 | 42281105 | POTTER VALLEY P H 1105 | 1.6451 | 101 | 0.44262 | 44.7046 | 43 | 2 | 1.8343 | 1.8343 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10934 | POINT MORETTI 1101CB | 82931101 | POINT MORETTI 1101 | 0.012787 | 1 | 0.44218 | 0.44218 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
5032 | MOUNTAIN QUARRIES 21016953 | 152282101 | MOUNTAIN QUARRIES 2101 | 5.7104 | 58 | 0.4353 | 25.2473 | 45 | 3 | 5.95 | 5.95 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
9729 | BRENTWOOD 210596324 | 14592105 | BRENTWOOD 2105 | 0.48214 | 6 | 0.4317 | 2.5902 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
6662 | NORTH DUBLIN 2101CB | 14052101 | NORTH DUBLIN 2101 | 1.7629 | 23 | 0.42859 | 9.8576 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
1690 | DESCHUTES 11049718 | 103351104 | DESCHUTES 1104 | 18.6049 | 357 | 0.42526 | 151.8163 | 48 | 7 | 18.3011 | 18.3011 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
193 | OREGON TRAIL 110335002 | 103521103 | OREGON TRAIL 1103 | 57.1429 | 641 | 0.42185 | 270.4028 | 49 | 41 | 62.2442 | 62.2442 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
7274 | MARIPOSA 2102440236 | 254452102 | MARIPOSA 2102 | 4.2727 | 38 | 0.4205 | 15.979 | 50 | 3 | 8.59 | 8.59 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10024 | CLEAR LAKE 1101881362 | 42141101 | CLEAR LAKE 1101 | 0.29834 | 10 | 0.41959 | 4.1959 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
7141 | WILDWOOD 11011454 | 103611101 | WILDWOOD 1101 | 7.8323 | 31 | 0.41883 | 12.9837 | 52 | 5 | 7.87 | 5.41 | 2.46 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
7033 | VACA DIXON 1105965390 | 63591105 | VACA DIXON 1105 | 0.75147 | 21 | 0.41415 | 8.6971 | 53 | 1 | 0.75 | 0.75 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
9936 | OLETA 1101754718 | 163541101 | OLETA 1101 | 2.8841 | 29 | 0.40712 | 11.8066 | 54 | 2 | 3.01 | 3.01 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
10113 | CALISTOGA 1101CB | 42711101 | CALISTOGA 1101 | 0.13777 | 9 | 0.40561 | 3.6505 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 250 Miles | 2020-11-13
3943 | MOUNTAIN QUARRIES 2101CB | 152282101 | MOUNTAIN QUARRIES 2101 | 24.9941 | 262 | 0.38665 | 101.3032 | 68 | 1 | 0.43087 | 0.43087 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
4693 | MIDDLETOWN 1101CB | 43141101 | MIDDLETOWN 1101 | 4.731 | 146 | 0.36174 | 52.8144 | 86 | 1 | 0.53485 | 0 | 0.53485 | 0 | 0 | 0 | ECOP - Top 20% | 2020-11-13
5717 | SHINGLE SPRINGS 210935598 | 153652109 | SHINGLE SPRINGS 2109 | 10.847 | 122 | 0.27855 | 33.9836 | 159 | 5 | 12.5941 | 4.3231 | 8.271 | 0 | 0 | 0 | Top 20% MAVF CPZ | 2020-11-13
8139 | LAS GALLINAS A 110599904 | 42991105 | LAS GALLINAS A 1105 | 5.5621 | 54 | 0.25006 | 13.5032 | 215 | 2 | 2.7962 | 2.7962 | 0 | 0 | 0 | 0 | ECOP - Top 20% | 2020-11-13
6909 | WYANDOTTE 1109702710 | 102911109 | WYANDOTTE 1109 | 2.6641 | 49 | 0.24845 | 12.174 | 218 | 1 | 0.60739 | 0.60739 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
2854 | SHINGLE SPRINGS 21099372 | 153652109 | SHINGLE SPRINGS 2109 | 17.8687 | 190 | 0.24281 | 46.1342 | 227 | 12 | 17.5703 | 3.3186 | 13.6517 | 0.6 | 0 | 0 | Top 20% MAVF CPZ | 2020-11-13
1039 | SILVERADO 2104726 | 43432104 | SILVERADO 2104 | 30.3762 | 263 | 0.22347 | 58.7725 | 279 | 6 | 6.1621 | 3.3867 | 2.7754 | 0 | 0 | 0 | ECOP - Top 20% | 2020-11-13
1293 | MIDDLETOWN 11014646 | 43141101 | MIDDLETOWN 1101 | 18.5633 | 165 | 0.19983 | 32.9712 | 328 | 2 | 2.3492 | 0 | 2.3492 | 0 | 0 | 0 | ECOP - Top 20% | 2020-11-13
6545 | TULUCAY 1101628 | 42301101 | TULUCAY 1101 | 4.1726 | 98 | 0.19686 | 19.2923 | 338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 20% MAVF CPZ | 2020-11-13
8575 | ELK CREEK 11012106 | 102781101 | ELK CREEK 1101 | 13.2402 | 67 | 0.1961 | 13.1388 | 340 | 1 | 7.9 | 7.9 | 0 | 0 | 0 | 0 | FRRB - REMG - 2021 | 2020-11-13
8166 | BANGOR 1101CB | 103191101 | BANGOR 1101 | 18.7561 | 171 | 0.19378 | 33.1366 | 355 | 1 | 0.85 | 0.85 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
449 | CLAYTON 221296224 | 12022212 | CLAYTON 2212 | 19.3992 | 174 | 0.18755 | 32.6329 | 377 | 2 | 2.8186 | 0 | 2.8186 | 0 | 0 | 0 | ECOP - Top 20% | 2020-11-13
2810 | OAKHURST 110110090 | 254421101 | OAKHURST 1101 | 44.0886 | 435 | 0.17437 | 75.8506 | 421 | 1 | 1.39 | 1.39 | 0 | 0 | 0 | 0 | Remote Grid Pilot | 2020-12-18
50 | MARIPOSA 210135244 | 254452101 | MARIPOSA 2101 | 17.4635 | 146 | 0.17286 | 25.237 | 428 | 1 | 0.84 | 0.84 | 0 | 0 | 0 | 0 | Remote Grid Pilot | 2020-12-18
652 | MIDDLETOWN 110148212 | 43141101 | MIDDLETOWN 1101 | 10.6994 | 110 | 0.1603 | 17.6327 | 468 | 13 | 15.3455 | 15.3455 | 0 | 0 | 0 | 0 | ECOP - Top 20% | 2020-11-13
932 | MIDDLETOWN 1101548 | 43141101 | MIDDLETOWN 1101 | 27.4082 | 298 | 0.15935 | 47.4878 | 474 | 34 | 28.3644 | 22.6626 | 5.7018 | 0 | 0 | 0 | ECOP - Top 20% | 2020-11-13
5391 | FITCH MOUNTAIN 111324918 | 42751113 | FITCH MOUNTAIN 1113 | 5.4965 | 49 | 0.1575 | 7.7177 | 481 | 1 | 4.4858 | 0 | 0 | 0 | 5.4458 | 0 | In-Construction | 2020-12-01
5806 | COLUMBIA HILL 11012212 | 152471101 | COLUMBIA HILL 1101 | 9.1336 | 76 | 0.12922 | 9.8207 | 606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Top 20% MAVF CPZ | 2020-11-13
3234 | FULTON 1107604 | 42561107 | FULTON 1107 | 17.4386 | 169 | 0.12169 | 20.5661 | 637 | 5 | 4.015 | 2.3578 | 1.6572 | 0 | 0 | 0 | ECOP - Top 20% | 2020-11-13
8080 | SILVERADO 210258626 | 43432102 | SILVERADO 2102 | 15.2217 | 125 | 0.117 | 14.6249 | 663 | 2 | 3.5445 | 0 | 3.5445 | 0 | 0 | 0 | ECOP - Top 20% | 2020-11-13
772 | DIAMOND SPRINGS 11052102 | 152261105 | DIAMOND SPRINGS 1105 | 37.4816 | 417 | 0.11621 | 48.4576 | 666 | 1 | 1.6339 | 1.6339 | 0 | 0 | 0 | 0 | Top 20% MAVF CPZ | 2020-11-13
2133 | FROGTOWN 17011623 | 163451701 | FROGTOWN 1701 | 15.2605 | 152 | 0.1076 | 16.3546 | 721 | 1 | 0.59 | 0 | 0 | 0.59 | 0 | 0 | Top 20% MAVF CPZ | 2020-11-13
837 | DIAMOND SPRINGS 11071402 | 152261107 | DIAMOND SPRINGS 1107 | 44.1915 | 541 | 0.092281 | 49.924 | 811 | 3 | 8.465 | 1.0972 | 7.3678 | 0 | 0 | 0 | ECOP | 2020-12-11
3279 | OAKHURST 1101CB | 254421101 | OAKHURST 1101 | 2.3149 | 47 | 0.086583 | 4.0694 | 847 | 1 | 0.052083 | 0 | 0 | 0.052083 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
7502 | FITCH MOUNTAIN 11136751 | 42751113 | FITCH MOUNTAIN 1113 | 22.6749 | 139 | 0.073927 | 10.2759 | 945 | 1 | 4.03 | 4.03 | 0 | 0 | 0 | 0 | FRRB - REMG - 2021 | 2020-11-13
2673 | PUEBLO 2102792 | 43292102 | PUEBLO 2102 | 19.3407 | 180 | 0.073389 | 13.2101 | 951 | 3 | 3.3379 | 3.3379 | 0 | 0 | 0 | 0 | ECOP | 2020-12-11
4175 | MARTELL 1101CB | 163011101 | MARTELL 1101 | 5.879 | 171 | 0.067405 | 11.5263 | 999 | 3 | 1.31 | 1.31 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
4743 | WYANDOTTE 11031508 | 102911103 | WYANDOTTE 1103 | 27.2173 | 249 | 0.050062 | 12.4656 | 1176 | 4 | 18.7622 | 1.8559 | 13.97 | 0 | 2.9364 | 0 | FRRB - OH - 2021 | 2020-11-13
3633 | BIG BEND 11021972 | 103751102 | BIG BEND 1102 | 21.2964 | 177 | 0.040961 | 7.25 | 1288 | 12 | 32.1473 | 23.3034 | 8.8439 | 0 | 0 | 0 | FRRB - OH - 2021 | 2020-11-13
4946 | WYANDOTTE 11031976 | 102911103 | WYANDOTTE 1103 | 23.7815 | 217 | 0.040282 | 8.7412 | 1299 | 24 | 31.1777 | 25.0078 | 0 | 0 | 6.1699 | 0 | FRRB - UG - 2021 | 2020-11-13
3640 | FROGTOWN 1702CB | 163451702 | FROGTOWN 1702 | 1.4614 | 47 | 0.039234 | 1.844 | 1316 | 1 | 1.2739 | 0 | 0 | 1.2739 | 0 | 0 | PSPS - Scoped | 2020-12-18
88 | SILVERADO 2105658898 | 43432105 | SILVERADO 2105 | 17.1737 | 151 | 0.035763 | 5.4002 | 1361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In-Construction | 2020-12-01
2335 | PLACERVILLE 21067522 | 153082106 | PLACERVILLE 2106 | 67.3656 | 745 | 0.035529 | 26.4689 | 1363 | 3 | 1.35 | 1.35 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
3154 | CALISTOGA 1102634 | 42711102 | CALISTOGA 1102 | 11.216 | 178 | 0.029373 | 5.2284 | 1477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
249 | RINCON 1103CB | 43321103 | RINCON 1103 | 2.4433 | 41 | 0.016461 | 0.67489 | 1755 | 1 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | PSPS - Scoped | 2020-12-18
3447 | WYANDOTTE 11031974 | 102911103 | WYANDOTTE 1103 | 22.4168 | 259 | 0.012814 | 3.3188 | 1849 | 28 | 20.3416 | 11.3906 | 2.92 | 0 | 6.0311 | 0 | FRRB - UG - 2021 | 2020-11-13
1135 | LOS GATOS 1106LB44 | 82021106 | LOS GATOS 1106 | 19.3536 | 213 | 0.012499 | 2.6623 | 1864 | 1 | 0.84905 | 0 | 0 | 0.84905 | 0 | 0 | In-Construction | 2020-12-01
10 | KONOCTI 1102532 | 43311102 | KONOCTI 1102 | 9.7315 | 124 | 0.0090595 | 1.1234 | 1999 | 1 | 1.0646 | 0 | 0 | 0 | 0 | 1.0646 | In-Construction | 2020-12-01
7254 | ALLEGHANY 1101VR816 | 152101101 | ALLEGHANY 1101 | 4.1491 | 49 | 0.0088541 | 0.43385 | 2010 | 4 | 1.74 | 1.74 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
797 | DUNBAR 1101CB | 43071101 | DUNBAR 1101 | 3.1203 | 191 | 0.007993 | 1.5267 | 2048 | 3 | 2.0114 | 2.0114 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
1984 | HALF MOON BAY 110369412 | 24101103 | HALF MOON BAY 1103 | 15.5679 | 150 | 0.0078448 | 1.1767 | 2055 | 2 | 5.42 | 5.42 | 0 | 0 | 0 | 0 | FRRB - UG - 2021 | 2020-11-13
4884 | PLACERVILLE 1112CB | 153081112 | PLACERVILLE 1112 | 8.513 | 117 | 0.0065148 | 0.76223 | 2123 | 2 | 0.38015 | 0.38015 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
3076 | PLACERVILLE 21061104 | 153082106 | PLACERVILLE 2106 | 49.4989 | 462 | 0.0064469 | 2.9785 | 2131 | 1 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | Remote Grid Pilot | 2020-12-18
8349 | BRUNSWICK 1110CB | 152481110 | BRUNSWICK 1110 | 0.0034177 | 26 | 0.0064174 | 0.16685 | 2134 | 1 | 0.055871 | 0.055871 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
2120 | BRUNSWICK 110350070 | 152481103 | BRUNSWICK 1103 | 17.7473 | 201 | 0.0062036 | 1.2469 | 2144 | 5 | 9.1785 | 0 | 0 | 0 | 9.1785 | 0 | In-Construction | 2020-12-01
6388 | HALF MOON BAY 11036012 | 24101103 | HALF MOON BAY 1103 | 6.6683 | 79 | 0.0054078 | 0.42722 | 2186 | 1 | 0.95 | 0.95 | 0 | 0 | 0 | 0 | FRRB - OH - 2021 | 2020-11-13
1451 | MIWUK 1701953336 | 163661701 | MIWUK 1701 | 11.8581 | 132 | 0.0038168 | 0.50381 | 2267 | 4 | 6.04 | 0 | 0 | 2.9867 | 3.2233 | 0 | In-Construction | 2020-12-01
1371 | PINE GROVE 11021222 | 163751102 | PINE GROVE 1102 | 17.2598 | 218 | 0.0037571 | 0.81905 | 2271 | 3 | 4.3156 | 0 | 0 | 0 | 4.3156 | 0 | In-Construction | 2020-12-01
1742 | MIWUK 1701CB | 163661701 | MIWUK 1701 | 16.2494 | 187 | 0.0029901 | 0.55914 | 2353 | 6 | 10.9706 | 0 | 0 | 0 | 11.0006 | 0 | In-Construction | 2020-12-01
2714 | MIWUK 1702CB | 163661702 | MIWUK 1702 | 9.055 | 110 | 0.0028161 | 0.30977 | 2369 | 2 | 2.4208 | 0 | 0 | 0 | 1.7106 | 2.0902 | In-Construction | 2020-12-01
5291 | MIWUK 1702823548 | 163661702 | MIWUK 1702 | 19.7318 | 231 | 0.0025098 | 0.57976 | 2411 | 1 | 0.68519 | 0 | 0 | 0 | 0 | 1.4252 | In-Construction | 2020-12-01
3039 | BIG BASIN 110110296 | 82841101 | BIG BASIN 1101 | 14.4211 | 181 | 0.0021702 | 0.3928 | 2456 | 3 | 7.6233 | 0 | 0 | 0 | 7.6233 | 0 | DSDD | 2020-12-18
5206 | CAMP EVERS 21065020 | 83622106 | CAMP EVERS 2106 | 15.0734 | 185 | 0.0021265 | 0.3934 | 2464 | 1 | 1.0392 | 0 | 0 | 0 | 1.0392 | 0 | In-Construction | 2020-12-01
4477 | MIWUK 170238218 | 163661702 | MIWUK 1702 | 10.9416 | 132 | 0.00074696 | 0.098599 | 2678 | 2 | 2.6023 | 0 | 0 | 0 | 2.1023 | 2.29 | In-Construction | 2020-12-01
380 | STANISLAUS 17021804 | 162821702 | STANISLAUS 1702 | 8.3797 | 118 | 0.00058985 | 0.069602 | 2712 | 1 | 1.9112 | 0 | 0 | 1.9112 | 0 | 0 | DSDD | 2020-12-18
6409 | MIWUK 1702S2247 | 163661702 | MIWUK 1702 | 1.4879 | 21 | 0.00049228 | 0.010338 | 2737 | 1 | 1.1682 | 0 | 0 | 0 | 1.1682 | 0 | In-Construction | 2020-12-01
9855 | DUNLAP 1102778286 | 254061102 | DUNLAP 1102 | 2.6029 | 5 | 0.0004909 | 0.0024545 | 2738 | 1 | 2.48 | 2.48 | 0 | 0 | 0 | 0 | Remote Grid Pilot | 2020-12-18
2096 | CALISTOGA 1102184814 | 42711102 | CALISTOGA 1102 | 0.42402 | 20 | 8.707e-06 | 0.00017414 | 3098 | 1 | 0.18 | 0.18 | 0 | 0 | 0 | 0 | PSPS - Community Resiliency | 2020-12-18
3773 | RINCON 1104CB | 43321104 | RINCON 1104 | 0.56024 | 34 | 4.3928e-06 | 0.00014935 | 3302 | 1 | 1.78 | 0 | 0 | 1.78 | 0 | 0 | PSPS - Scoped | 2020-12-18
n/a | VARIOUS | n/a | VARIOUS | 31.8 | 34 |  |  |  |  | 31.8 | 31.8 | 0 | 0 | 0 | 0 | Line Removal | 2020-12-11
|  |  | Totals: | 1201.0946 |  |  | 2328.1944 |  | 388 | 595.7215 | 410.6079 | 107.4455 | 13.9235 | 61.9447 | 6.8699

## Mapping (hidden)
Phase | Exec Status
Scoping | 0
Scoping | 1
Scoping | 2
Scoping | 3
Scoping | 4
Scoping | 5
Scoping | 6
Scoping | 7
Scoping | 8
Scoping | 9
Scoping | 10
Scoping | 11
Scoping | 12
Scoping | 13
Estimating | 14
Estimating | 15
Estimating | 16
Estimating | 17
Dependencies | 18
Construction | 19
Construction | 20
Scoping
Estimating
Dependencies
Construction