## Master
25 | [36 empty] | 18.5445 | 14.1369 | 17.8 | 33705 | 17.8812 |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | 0 | 507.5 | 0 | 50 | 3746.8 | 9387.3 | 12996.6 | 3250 | 1153.3 | 0 | 0 | 0
Order | MAT | Order Description | Reg | Div | Job Owner Name | Project Managed? | Tree Wire? | User Status | Phase | Reason Missed 8/1 Date | Risk of not completing by 8/1 | Notes | Estimating Resource | Const. Resource | Contractor | EOD Date as of 6/6 | % of Estimate Complete | Current Out of PEND Date | % Const. Complete | In-Service Date (Forecasted) | Matts Cons Start | Matts Cons End | Click Start Date | Click End Date | P6 CSTRT Forecast (as of 5/8/18) | P6 FISD Forecast (as of 5/8/18) | FISD Week | Click Start Week | Click Finish Week | P6 Con Start Week | P6 Con End Week | Matts Cons Start Week | Matts Cons End Week | Matts Year | Matts Mo | Ckt Feet (Adjusted/Actual) | Ckt Miles (Adjusted/Actual) | Tier 3 Ckt Miles | 4/3/18 Planned Ckt Miles | Total Estimated Hours | Total Miles including partial completions. | # of Crews | Weeks of Const. Calc 5-10s 5 man crew | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
31234873 | 08J | X1104 (Oakland)- RELIAIBLITY 2017 - UWF X-1104 | BA - Bay Area | EB | Tony Chan | Y | NO | #N/A | ?? | NA | 1 - Complete | Risk: NA NOTES: 5/31 - CN24 complete & units posted to SA Project Complete. Not tree wire. - 5/31 - CN24 complete & units posted to SA | CONTRACT - PAR | CONTRACT | Intren | Estimate Complete |  |  | 100% | 2018-03-28 | 2018-02-17 20:24 | 2018-02-28 | ? | ? | 2018-02-01 | 2018-03-13 | 13 | #VALUE! | #VALUE! | 5 | 11 | 7 | 9 | 2018 | 2 | 2100 | 0.39773 |  | 0.4 | 507.5 | 0.39773 | 1 | 2.03 | [32 empty] | 507.5
31095523 | 08W | OAKLAND K 1103 - MERRIEWOOD DR EB-RELIAIBLITY -K1103, REPL #4ACSR W | BA - Bay Area | EB | Michael Lee | N | YES | FICL | 5 Post-Constr | NA | 1 - Complete | Risk: NA NOTES: Complete 5/30 - 5/31 - completed per Joe Marino | RMC | GC | NA | Estimate Complete | 100% | NA | 100% | 2018-05-30 | 2018-05-22 | 2018-05-30 | 09/22/2017 | 05/30/2018 | ? | ? | 22 | 38 | 22 | #VALUE! | #VALUE! | 21 | 22 | 2018 | 5 | 1838 | 0.34811 | 0.34811 | 0.4 | 538.9 | 0.34811 | 1 | 2.1556 |  |  |  | C | C | [32 empty] | 538.9
31218981 | 08J | CEDAR CREEK 1101(Round Mountain)- UPGRADE 9 SPANS | NO - Northern | NV | Anandi De La Fuente | N | NO | CLSD | 5 Post-Constr | NA | 1 - Complete | Risk: NA NOTES: 5/31 - CN24 complete & units posted to SAP Click Dates Start back up in June. AFW in for 5/16? - 5/31 - CN24 complete & units posted to SAP | CONTRACT - EEI | DIV | NA | Estimate Complete |  |  | 100% | 2018-06-04 | 2018-06-04 | 2018-06-04 | ? | ? | ? | ? | 23 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 23 | 23 | 2018 | 6 | 4200 | 0.79545 |  | 0.51 | 308.4 | 0.79545 | 1 | 1.2336 | [5 empty] | X | [28 empty] | 50
31206912 | 08W | CAMP EVERS 2103(Santa Cruz) - WDN 15-0073161 CE2103-OLD GRAHM HL R | CC - Central Coast | CC | Ola Lamidi | N | YES | DOCC | 5 Post-Constr | NA | 1 - Complete | Risk: NOTES: - Permiting issue arose on 6/20, resolved now scheduled 7/12. - AFW in for 7/12 - Permit extended to 9/30. | CONTRACT - EEI | GC | NA | Estimate Complete | 100% | NA | 100% | 2018-07-16 | 2018-06-11 | 2018-07-12 | ? | ? | ? | ? | 29 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 24 | 28 | 2018 | 7 | 705 | 0.13352 | 0.13352 | 0.16 | 192 | 0.13352 | 1 | 0.768 | [6 empty] | C | C | C | C | C | [25 empty] | 191.5
31205198 | 08W | ALTO 1125 (Mill Valley)- REED ST, COUNTY | BA - Bay Area | NB | Steve Jackson | Y | YES | FICL | 5 Post-Constr | NA | 1 - Complete | Risk: NA NOTES: - 5/31 - expect construction to start on 6/25 & complete on 7/16 | RMC | CONTRACT | Wilson | Estimate Complete | 100% | NA | 100% | 2018-07-16 | 2018-06-25 | 2018-07-16 | # | # | 2018-06-25 | 2018-07-16 | 29 | #VALUE! | #VALUE! | 26 | 29 | 26 | 29 | 2018 | 7 | 3900 | 0.73864 | 0.6178 | 0.73 | 1907.9 | 0.73864 | 2 | 3.8158 | [8 empty] | C | C | C | C | [24 empty] | 807.9 | 1100
31169729 | 08W | Oakland D 1112 (Oakland) - 2017 D1112/K1101 UWF | BA - Bay Area | EB | Carolina Huerta | Y | YES | FICL | 5 Post-Constr | NA | 1 - Complete | Risk: NOTES: - D1112 (Tier 3) complete and K1101 (Tier 1) is planned for July. - Added Scope: Planning may want to extend 3 spans to enhance the ckt. May cause some delays for estimating and dependencies. Redline? -GC click scheduled to complete on 8/1. Will do tree wire section first. - 5/31 - 1st clearance next week. Expect to complete mid July | CONTRACT - EEI | GC | NA | Estimate Complete | 100% | NA | 100% | 2018-07-17 | 2018-05-23 | 2018-07-17 | 05/23/2018 | 07/23/2018 | 2018-05-23 | 2018-07-17 | 29 | 21 | 30 | 21 | 29 | 21 | 29 | 2018 | 7 | 4171 | 0.78996 | 0.21136 | 0.94 | 1404.5 | 0.78996 | 1 | 5.618 |  |  |  | C | C | C |  |  |  | C | C | C | [23 empty] | 304.5 | 1100
31207126 | 08W | ALTO 1125 (Mill Valley) -PANORAMIC HWY, COUNTY, | BA - Bay Area | NB | Steve Jackson | Y | YES | FICL | 5 Post-Constr | NA | 1 - Complete | Risk: NA NOTES: AFW 7/18 | RMC | CONTRACT | Wilson | Estimate Complete | 100% | NA | 100% | 2018-07-18 | 2018-05-30 | 2018-07-18 | 05/30/2018 | 07/17/2018 | 2018-05-31 | 2018-07-18 | 29 | 22 | 29 | 22 | 29 | 22 | 29 | 2018 | 7 | 5300 | 1.0038 | 1.0038 | 1.05 | 1927.3 | 1.0038 | 2 | 3.8546 |  |  |  |  | C | C | C | C | C | C | C | C | [24 empty] | 827.3 | 1100
31264915 | 08W | RINCON 1103 (Santa Rosa) - R7 RECONDUCTOR WILSON RD- | NO - Northern | SO | Jeffrey Jung | N | YES | DOCC | 5 Post-Constr | NA | 1 - Complete | Risk: -JPA: Verbal approval requested. NOTES: AFW in for 7/26 | CONTRACT - PAR | CONTRACT | Wilson | Estimate Complete | 100% | 2018-07-07 | 100% | 2018-07-25 | 2018-07-16 | 2018-07-25 | # | # | ? | ? | 30 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 29 | 30 | 2018 | 7 | 957 | 0.18125 | 0.18125 | 0.13 | 80.3 | 0.18125 | 1 | 0.3212 | [11 empty] | C | C | [23 empty] | 200
31255868 | 08W | ROB ROY 2104 (Day Valley)- HIGH SPLICE CABLE REPLACE | CC - Central Coast | CC | Sharon Kennedy | Y | YES | PREC | 5 Post-Constr | NA | 1 - Complete | Risk: NOTES: AFW7/27 | DC - Fresno | GC | NA | Estimate Complete | 100% | 2018-07-11 | 100% | 2018-07-27 | 2018-07-16 | 2018-07-27 | 07/16/2018 | 07/31/2018 | 2018-07-17 | 2018-07-27 | 30 | 29 | 31 | 29 | 30 | 29 | 30 | 2018 | 7 | 1439 | 0.27254 | 0.27254 | 0.27 | 497 | 0.27254 | 1 | 1.988 | [10 empty] | C | C | C | [24 empty] | 350
31205343 | 08W | ALTO 1124 (Mill Valley) - SUMMIT AVE , CITY | BA - Bay Area | NB | Steve Jackson | Y | YES | FICL | 5 Post-Constr | NA | 1 - Complete | Risk: ROW issue. Customer doesn’t want us to replace pole and damage landscaping. Steve working with land and others to resolve. 3 Spans. NOTES: Remove shoofly on 7/5. ROW issue pole. | RMC | CONTRACT | Wilson | Estimate Complete | 100% | NA | 100% | 2018-07-28 | 2018-06-04 | 2018-07-28 | 06/04/2018 | 06/29/2018 | 2018-06-04 | 2018-07-28 | 30 | 23 | 26 | 23 | 30 | 23 | 30 | 2018 | 7 | 5006 | 0.94811 | 0.94811 | 0.94 | 2562.1 | 0.94811 | 2 | 5.1242 | [5 empty] | C | C | C | C | C | C | C | C | [22 empty] | 407.1 | 1050 | 1100
31205418 | 08W | ALTO 1125 (Mill Valley)- BROOKLINE AVE, COUNTY, | BA - Bay Area | NB | Steve Jackson | Y | YES | FICL | 5 Post-Constr | NA | 1 - Complete | Risk: NA NOTES: - Update click dates - 5/31 - expected construction start on 6/26 & completion on 7/30 | RMC | CONTRACT | Wilson | Estimate Complete | 100% | NA | 100% | 2018-07-30 | 2018-06-26 | 2018-07-30 | 06/25/2019 | 07/25/2019 | 2018-06-26 | 2018-07-27 | 31 | 26 | 30 | 26 | 30 | 26 | 31 | 2018 | 7 | 5480 | 1.0379 | 1.0379 | 1.04 | 2110.6 | 1.0379 | 2 | 4.2212 | [8 empty] | C | C | C | C | C | C | [22 empty] | 1010.6 | 1100
31204706 | 08W | ALTO 1124 (Mill Valley)- THROCKMORTON LANE | BA - Bay Area | NB | Steve Jackson | Y | YES | FICL | 5 Post-Constr | NA | 1 - Complete | Risk: NA NOTES: AFW/CWC submiting error. - 5/31 - expect to complete 7/2 | RMC | CONTRACT | Wilson | Estimate Complete | 100% | NA | 100% | 2018-07-30 | 2018-06-18 | 2018-07-30 | 06/18/2018 | 07/30/2018 | 2018-06-18 | 2018-07-30 | 31 | 25 | 31 | 25 | 31 | 25 | 31 | 2018 | 7 | 1613 | 0.30549 | 0.30549 | 0.29 | 1348.6 | 0.30549 | 2 | 2.6972 | [7 empty] | C | C | C | C | C | C | C | [21 empty] | 500
31132867 | 08W | Half Moon Bay 1101 (Half Moon Bay)- SKYLINE BLVD | CC - Central Coast | PN | Les Beeghly | Y | YES | #N/A | ?? | Caltrans Permit: Dan Pantoja (Land Agent) and Jeff McDougal helping to expedite. Land: Lam Vu (Sr. Land Tech) and Jeff McDougal helping to expedite. | 1 - Complete | Risk: Permit: Caltrans permit application submitted 5/10. Working with Jeff McDougal to expedite. Didn't have JPA, which could cause an issue. Typically 2 month process. Revised TCON needed, amendment. Land/Easement: 3 locations are in SFPUC property, 1 year process for easement. Looking to redesign to stay in current easement or eliminate these locations from scope. NOTES: - JPA sent 4/28, June 12th. -Environmental Planned to finish 6/29. -Click dates are contract unassigned. -RFP issued to ILB 4/19. - 5/31 - no change to rick status. Not sure about status of Cal Trans permit submitted by contractor | CONTRACT - EEI | CONTRACT | ILB | Estimate Complete | 100% | TBD | 100% | 2018-07-31 | 2018-07-16 | 2018-07-31 | ? | ? | 2018-07-16 | 2018-07-31 | 31 | #VALUE! | #VALUE! | 29 | 31 | 29 | 31 | 2018 | 7 | 4638 | 0.87841 | 0.87841 | 0.41 | 1068.9 | 0.87841 | 1 | 4.2756 | [11 empty] | C | C | C | [25 empty] | 629.4
31286571 | 08W | EL DORADO PH 2102 (Pollock Pines) - HIGH SPLICE AREA | NO - Northern | SI | Brian Ritchie | Y | YES | FICL | 5 Post-Constr | Resources Pulled to Fire | 1 - Complete | Reason for Missing Date: Crews Pulled to support Fires. | DC - W. Sac | GC | NA | 2018-06-08 | 100% | 2018-07-11 | 100% | 2018-09-11 | 2018-07-11 | 2018-09-11 | 07/10/2018 | 2018-07-27 | 2018-07-10 | 2018-09-18 | 37 | 28 | 30 | 28 | 38 | 28 | 37 | 2018 | 9 | 1928 | 0.36515 | 0.36515 | 0.4 | 611.4 | 0.36515 | 1 | 2.4456 | [7 empty] | 0 |  |  | C | C | C | C | C | C | C | C | C | C | [17 empty] | 600
31246140 | 08W | WYANDOTTE 1105 (Oroville)- RECONDUCTOR 3000 FT OF DET 4AR - WY1105 | NO - Northern | NV | Aaron Patane | Y | YES | FICL | 5 Post-Constr | Outage Restrictions (Heat/Loading) | 1 - Complete | Reason for Missing Date: Crews Pulled to support north valley fire in late june. Work replanned for 7/18, but canceled by DO due to loading concerns being it was over 100 degrees. | RMC | GC | NA | Estimate Complete | 100% | NA | 100% | 2018-09-13 | 2018-06-04 | 2018-09-13 | 06/04/2018 | 09/13/2018 | 2018-06-04 | 2018-09-13 | 37 | 23 | 37 | 23 | 37 | 23 | 37 | 2018 | 9 | 3309 | 0.6267 | 0.6267 | 0.57 | 617.9 | 0.6267 | 1 | 2.4716 | [5 empty] | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | [17 empty] | 1000
31082394 | 08W | Molino 1102 (Santa Rosa) - SIX SPANS FRATI LN | NO - Northern | SO | Jeffrey Jung | N | YES | MAPP | 5 Post-Constr | Permitting | 1 - Complete | Reason for missing date: 2 months to obtain SO Count Permit, due to volume of rebuild work taking place. When received agency added special conditions to full road closure that would not allow crew to perform work. Permit revision couldn't be obtain in time to cmplete by 8/1. | RMC | GC | NA | Estimate Complete | 100% | 2018-06-28 | 100% | 2018-09-16 | 2018-08-27 | 2018-09-15 | 09/10/2018 | 09/13/2018 | ? | ? | 38 | 37 | 37 | #VALUE! | #VALUE! | 35 | 37 | 2018 | 9 | 1486 | 0.28144 | 0.28144 | 0.09 | 208.6 | 0.28144 | 1 | 0.8344 | [17 empty] | C | C | C | [15 empty] | 208
31207089 | 08J | GB 1103 (Mill Valley) - HAWTHORN | BA - Bay Area | NB | Steve Jackson | Y | YES | FICL | 5 Post-Constr | Resources Pulled to Fire | 1 - Complete | Reason for Missing Date: Crews Pulled to support Fires. | RMC | CONTRACT | Wilson | Estimate Complete | 100% | NA | 100% | 2018-09-25 | 2018-07-10 | 2018-09-25 | 07/10/2018 | 07/31/2018 | 2018-07-10 | 2019-01-28 | 39 | 28 | 31 | 28 | 5 | 28 | 39 | 2018 | 9 | 4687 | 0.92614 | 0.92614 | 0.85 | 2834.1 | 0.92614 | 2 | 5.6682 | [10 empty] | C | C | C | C | C | C | C | C | C | C | C | C | [13 empty] | 563.5 | 1050 | 1100
31234871 | 08W | Oakland K 1104 (Oakland) - UWF K1104/X1105/6 | BA - Bay Area | EB | Matt Herron | Y | YES | MAPP | 5 Post-Constr | NA | 1 - Complete | Risk: Tier 3 section on track to complete by 7/30. Tier 1 8/30 NOTES: - Half of the project is in Tier 1. - Work areas without dependencies first. - Need permit extensions for expired permits - Need to issue CWA & obtain work plan - Click dates are contract unassigned. - 5/31 - no change in risk status. Expects the Tier 3 portion to be completed by 8/1 | CONTRACT - PAR | CONTRACT | Intren | Estimate Complete | 100% | NA | 100% | 2018-09-25 | 2018-06-18 | 2018-09-25 | 2018-07-09 | 09/25/2018 | 2018-06-26 | 2018-10-29 | 39 | 28 | 39 | 26 | 44 | 25 | 39 | 2018 | 9 | 7271 | 1.3771 | 0.57348 | 1.38 | 3201.1 | 1.3771 | 2 | 6.4022 | [6 empty] | C | C | C | C | C | C | C |  |  | C | C | C | C | C | C | C | [13 empty] | 1051.1 | 1050 | 1100
31330635 | 08W | FORESTHILL 1102 (Foresthill) - SPRING GARDEN RD | NO - Northern | SI | Brian Ritchie | Y | YES | FICL | 5 Post-Constr | Timing/Size of Project | 1 - Complete | Reason for missing date: Size of project. Project is over 2 miles and didn’t become construction ready till July. Every activity (Estimating/Dependancy/Construction) was put at its critical path, but too large to complete in time. | CONTRACT - PAR | GC | NA | 2018-05-31 | 100% | 2018-07-13 | 100% | 2018-10-04 | 2018-07-16 | 2018-10-04 | 07/16/2018 | 10/05/2018 | 2018-07-13 | 2018-12-03 | 40 | 29 | 40 | 28 | 49 | 29 | 40 | 2018 | 10 | 11308 | 2.1417 | 2.1417 | 1.89 | 3200 | 2.1417 | 2.5 | 5.12 | [10 empty] | C | C | C | C | C | C | C | C | C | C | C | C | C | [14 empty] | 1050 | 1100 | 450
31275384 | 08W | MIRABEL 1101 (Santa Rosa)- R7 RECONDUCTOR MAYS CANYON | NO - Northern | SO | Jeffrey Jung | N | YES | MAPP | 5 Post-Constr | Permitting | 1 - Complete | Reason for missing date: - 2 months to obtain SO Count Permit, due to volume of rebuild work taking place. When received agency added special conditions to full road closure that would not allow crew to perform work. Permit revision couldn't be obtain in time to cmplete by 8/1. | RMC | GC | NA | Estimate Complete | 100% | 2018-06-28 | 100% | 2018-10-09 | 2018-08-27 | 2018-10-09 | 09/10/2018 | 10/09/2018 | ? | ? | 41 | 37 | 41 | #VALUE! | #VALUE! | 35 | 41 | 2018 | 10 | 1986 | 0.37614 | 0.37614 | 0.34 | 362.6 | 0.37614 | 1 | 1.4504 | [17 empty] | C | C | C | C | C | C | C | [11 empty] | 362.6
31338871 | 08W | El Cerrito G 1112 (Berkeley) Cal Berkeley | BA - Bay Area | EB | Jeff Kringler | Y | YES | FICL | 5 Post-Constr | NA | 1 - Complete | Risk: Access/Permit: Short window to work with two adjacent city projects. City will not allow full road closure without exstensive review. • TCP/Encroachment permit - Meeting with city and contractor again on 6/28/18 to discuss TCP’s. The Following dependences are still needed before the City of Berkeley will issue the work permit. - Temporary Construction Easement (TCE) for resident parking during the full road closure at locations 71 -89. (The land team is currently working on Easement) - Stand by fire and emergency services has been agreed on and confirmed by Berkeley Fire. (Berkeley Fire has agreed to staff project for 1 one) - PG&E has notified residents affected by road closure and outage by the first week on July . - City of Oakland’s approval for the one day road closure on Panoramic way (the top portion is the City of Oakland’s jurisdiction) . • 7/26 locations 90 – 97, assuming (two) 4-man crews • 7/27 locations 90 – 97, assuming (two) 4-man crews • 7/30 locations 63 – 70, assuming (four) 4-man crews • 7/31 locations 71 – 89, assuming (nine) 4-man crews Please note: Project has started 7/26 and planned to complete 7/31, but has so many variables and pieces that need to fall in place it is still be considered high risk. NOTES: - Estimate complete 5/16. -Environmental Planned to finish 6/26. - Multiple crews? - Need to award to contractor. - Need to update click. - 5/31 - no change to risk staus. Traffic control plan sent to the city. EBMUD still working in area and likely there until end of June. Kim to help secure contractor | CONTRACT - EEI | CONTRACT | Intren | Estimate Complete | 100% | TBD | 100% | 2018-10-13 | 2018-07-26 | 2018-10-13 | 07/25/2018 | 10/13/2018 | 2018-09-04 | 2018-10-14 | 41 | 30 | 41 | 36 | 42 | 30 | 41 | 2018 | 10 | 3505 | 0.66383 | 0.66383 | 0.64 | 1540 | 0.66383 | 1 | 6.16 | [12 empty] | C | C |  |  |  | C | C | C | C | C | C | C | [14 empty] | 1000
31205937 | 08W | ALTO 1125 (Mill Valley) -HELENS LN,CITY/CNTY,ALTO | BA - Bay Area | NB | Steve Jackson | Y | YES | MAPP | 5 Post-Constr | Resources Pulled to Fire | 1 - Complete | Reason for Missing Date: Crews Pulled to support Fires. | DC - Santa Rosa | CONTRACT | Wilson | Estimate Complete | 100% | NA | 100% | 2018-10-17 | 2018-07-09 | 2018-10-17 | 09/09/2018 | 10/05/2018 | 2018-07-09 | 2018-09-17 | 42 | 37 | 40 | 28 | 38 | 28 | 42 | 2018 | 10 | 5000 | 0.94697 | 0.94697 | 0.85 | 1999.5 | 0.94697 | 2 | 3.999 | [10 empty] | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | [11 empty] | 1050 | 842.6
31206678 | 08W | ALTO 1125 (Mill Valley) -SEQUOIA VLY RD CTY/CNTY | BA - Bay Area | NB | Steve Jackson | Y | YES | UNSC | 3 Constr Ready | Resources Pulled to Fire | 4 - High Risk | Reason for Missing Date: Crews Pulled to support Fires. | DC - Concord | CONTRACT | Wilson | Estimate Complete | 100% | 2018-06-15 | 90% | 2019-01-30 | 2018-07-19 | 2019-02-15 | 03/29/2019 | 03/29/2019 | 2018-07-25 | 2019-02-06 | 5 | 13 | 13 | 30 | 6 | 29 | 7 | 2019 | 2 | 2817 | 0.53352 | 0.53352 | 0.53 | 965.1 | 0.48017 | 2 | 1.9302 | [11 empty] | C | C | C | C | C | C | C | C | C | C | C | C | C | C | [12 empty] | 915.1 | 50
31169728 | 08W | Oakland K 1102 GRIZZLY PEAK | BA - Bay Area | EB | Linda Swartz | Y | YES | CONS | 4 Construction | NA | 1 - Complete | Risk: - New Contractor: Power Contracting (Pike) just starting working on ED work. This will be their first complex project. Contractor concerned with working #6 copper hot, requesting clearance. This would take customers out 2-3 time for work in same month. Needed to Meet 8/1: Contractor to execute work without major issue. NOTES: AFW lead me to believe work will be complete 7/18? JPA cleared 6/7. -Vegetation: Concerns with contract resources to support this project in time. - Scope Reduction: 2876ft of project has shifted to pilot project to underground existing OH lines for wild fire resiliency. - Environmental planned to finish 6/11. -Update crew foreman sheet with Planned units. - Out to bid. - Click is contract unassigned. | CONTRACT - PAR | CONTRACT | Power Contracting | Estimate Complete | 100% | TBD | 100% | 2018-11-15 | 2018-06-22 | 2018-11-15 | 06/22/2018 | 11/15/2018 | 2018-06-18 | 2018-09-28 | 46 | 25 | 46 | 25 | 39 | 25 | 46 | 2018 | 11 | 5016 | 0.95 | 0.54489 | 1.47 | 1183.4 | 0.95 | 1 | 4.7336 | [7 empty] | C | C | C | C | C |  |  |  | C | C | C | C | C | C | C | C | C | C | [13 empty] | 1100 | 73.9
31098626 | 08W | CLARKSVILLE 2104 (El Dorado Hills) - PH 3 Y2018 | NO - Northern | SI | Brian Ritchie | Y | YES | UNSC | 3 Constr Ready | Resources Pulled to Fire | 1a - Complete (Tier 3 only) | Reason for Missing Date: Crews Pulled to support Fires. | DC - W. Sac | GC | NA | 2018-06-30 | 100% | 2018-06-30 | 60% | 2019-03-31 | 2018-07-16 | 2019-02-28 | 2018-07-16 | 2018-09-28 | 2018-07-16 | 2019-01-30 | 14 | 29 | 39 | 29 | 5 | 29 | 9 | 2019 | 2 | 8052 | 1.525 | 0.21875 | 1.52 | 2527.3 | 0.915 | 1 | 10.1092 | [12 empty] | C | C | C | C | C | C | C | C |  | C | C | C | C | C | C | C | C | [6 empty] | 350 | 1050 | 1100

## Gantt
Order | Order Description | Tree Wire? | User Status | Phase | Ckt Miles | Risk of not completing by 8/1 | May |  |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November
Order | Order Description | Tree Wire? | User Status | Phase | Ckt Miles | Risk of not completing by 8/1 | Week - 18 | Week - 19 | Week - 20 | Week - 21 | Week - 22 | Week - 23 | Week - 24 | Week - 25 | Week - 26 | Week - 27 | Week - 28 | Week - 29 | Week - 30 | Week - 31 | Week - 32 | Week - 33 | Week - 34 | Week - 35 | Week - 36 | Week - 37 | Week - 38 | Week - 39 | Week - 40 | Week - 41 | Week - 42 | Week - 43 | Week - 44 | Week - 45 | Week - 46 | Week - 47 | Week - 48 | Reg | Matt End
31095523 | OAKLAND K 1103 - MERRIEWOOD DR EB-RELIAIBLITY -K1103, REPL #4ACSR W | YES | FICL | Post-Constr | 0.34811 | 1 - Complete | 0 | 0 | 0 | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-05-30
31206912 | CAMP EVERS 2103(Santa Cruz) - WDN 15-0073161 CE2103-OLD GRAHM HL R | YES | DOCC | Post-Constr | 0.13352 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC - Central Coast | 2018-07-12
31205198 | ALTO 1125 (Mill Valley)- REED ST, COUNTY | YES | FICL | Post-Constr | 0.73864 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-07-16
31169729 | Oakland D 1112 (Oakland) - 2017 D1112/K1101 UWF | YES | FICL | Post-Constr | 0.78996 | 1 - Complete | 0 | 0 | 0 | C | C | C | 0 | 0 | 0 | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-07-17
31207126 | ALTO 1125 (Mill Valley) -PANORAMIC HWY, COUNTY, | YES | FICL | Post-Constr | 1.0038 | 1 - Complete | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-07-18
31264915 | RINCON 1103 (Santa Rosa) - R7 RECONDUCTOR WILSON RD- | YES | DOCC | Post-Constr | 0.18125 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO - Northern | 2018-07-25
31255868 | ROB ROY 2104 (Day Valley)- HIGH SPLICE CABLE REPLACE | YES | PREC | Post-Constr | 0.27254 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC - Central Coast | 2018-07-27
31205343 | ALTO 1124 (Mill Valley) - SUMMIT AVE , CITY | YES | FICL | Post-Constr | 0.94811 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-07-28
31205418 | ALTO 1125 (Mill Valley)- BROOKLINE AVE, COUNTY, | YES | FICL | Post-Constr | 1.0379 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-07-30
31204706 | ALTO 1124 (Mill Valley)- THROCKMORTON LANE | YES | FICL | Post-Constr | 0.30549 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-07-30
31132867 | Half Moon Bay 1101 (Half Moon Bay)- SKYLINE BLVD | YES | #N/A | ?? | 0.87841 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC - Central Coast | 2018-07-31
31286571 | EL DORADO PH 2102 (Pollock Pines) - HIGH SPLICE AREA | YES | DOCC | Post-Constr | 0.36515 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO - Northern | 2018-09-11
31246140 | WYANDOTTE 1105 (Oroville)- RECONDUCTOR 3000 FT OF DET 4AR - WY1105 | YES | DOCC | Post-Constr | 0.6267 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO - Northern | 2018-09-13
31082394 | Molino 1102 (Santa Rosa) - SIX SPANS FRATI LN | YES | DOCC | Post-Constr | 0.28144 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO - Northern | 2018-09-15
31207089 | GB 1103 (Mill Valley) - HAWTHORN | YES | FICL | Post-Constr | 0.92614 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-09-25
31234871 | Oakland K 1104 (Oakland) - UWF K1104/X1105/6 | YES | MAPP | Post-Constr | 1.3771 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | 0 | 0 | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-09-25
31330635 | FORESTHILL 1102 (Foresthill) - SPRING GARDEN RD | YES | CONS | Construction | 2.1417 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO - Northern | 2018-10-04
31275384 | MIRABEL 1101 (Santa Rosa)- R7 RECONDUCTOR MAYS CANYON | YES | MAPP | Post-Constr | 0.37614 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO - Northern | 2018-10-09
31338871 | El Cerrito G 1112 (Berkeley) Cal Berkeley | YES | CONS | Construction | 0.66383 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | 0 | 0 | 0 | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-10-13
31169728 | Oakland K 1102 GRIZZLY PEAK | YES | CONS | Construction | 0.95 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | 0 | 0 | 0 | C | C | C | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-11-15
31205937 | ALTO 1125 (Mill Valley) -HELENS LN,CITY/CNTY,ALTO | YES | CONS | Construction | 0.94697 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-10-17
31206678 | ALTO 1125 (Mill Valley) -SEQUOIA VLY RD CTY/CNTY | YES | CONS | Construction | 0.53352 | 4 - High Risk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2019-02-15
31098626 | CLARKSVILLE 2104 (El Dorado Hills) - PH 3 Y2018 | YES | CONS | Construction | 1.525 | 1a - Complete (Tier 3 only) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | C | 0 | C | C | C | C | C | C | C | C | 0 | 0 | NO - Northern | 2019-02-28
|  |  |  | Cumulative Miles by Month |  |  | 0.348 |  |  |  |  | 0.35 |  |  |  | 6.56 |  |  |  |  | 6.56 |  |  |  | 10.14 |  |  |  | 15.65 |  |  |  |  | 17.17
| Region | [7 empty] | Phase | [5 empty] | Miles |  | # Proj
| Northern | [7 empty] | In Estimating | [5 empty] | 0 |  | 0
| Central Coast | [7 empty] | Pending
| Bay | [7 empty] | Construction Ready
[9 empty] | In Construction | [5 empty] | 4.89 |  | 6
[9 empty] | Complete | [5 empty] | 12.32 |  | 17
[9 empty] | Total | [5 empty] | 17.21 |  | 23
[5 empty] | 17.3513 |  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
[6 empty] | Low | 18: 10; 19: 11; Total 20: 12; Total 21: 13; Total 22: 13; Total 23: 13; Total 24: 14; Total 25: 13; 17.21 26: 16; 23 29: 11; 23 30: 10
[6 empty] | Medium | 18: 4; 19: 5; Total 20: 4; Total 21: 4; Total 22: 4; Total 23: 5; Total 24: 4; Total 25: 6; 17.21 26: 4; 23 29: 3; 23 30: 2
[6 empty] | High | 18: 9; 19: 7; Total 20: 7; Total 21: 6; Total 22: 5; Total 23: 4; Total 24: 4; Total 25: 3; 17.21 26: 2; 23 29: 4; 23 30: 5
[6 empty] | Complete | Total 22: 1; Total 23: 1; Total 24: 1; Total 25: 1; 17.21 26: 1; 23 29: 4; 23 30: 6
Formulas:
Matt End = VLOOKUP([Order],Master!A:W,23,FALSE)

## Pivot
Projects by Phase
[6 empty] | Phase | # Projects | Ckt Miles | [13 empty] | Tree Wire? | YES
[6 empty] | Estimating | 0 | 0 | [13 empty] | Project Status - by Project
[6 empty] | Pending | 0 | 0 | [13 empty] | Sum of Total Miles including partial completions. | Column Labels
[6 empty] | Constr Ready | 0 | 0 | 10.97 | 12 | [11 empty] | Row Labels | 5 | 7 | 9 | 10 | 11 | 12 | Grand Total
[6 empty] | Construction | 6 | 4.89 | 6.562 | 11 | [11 empty] | 1 - Complete | 0.34811 | 6.2568 | 3.5761 | 4.5606 |  |  | 14.7417
[6 empty] | Post-Constr | 17 | 12.32 | [13 empty] | 1a - Complete (Tier 3 only) |  |  |  |  | 0.9025 | 0.76693 | 1.6694
[6 empty] | Grand Total | 23 | 17.21 | [13 empty] | Grand Total | 0.34811 | 6.2568 | 3.5761 | 4.5606 | 0.9025 | 0.76693 | 16.4111
[6 empty] | Tree Wire? | YES
[6 empty] | Project Status - by Unit |  |  |  |  | Risk | May | June | July | Aug | Sep | Oct | Nov |  |  |  | Project Status - by Project
[6 empty] | Row Labels | Count of Order | Sum of Ckt Miles (Adjusted/Actual) |  |  | Complete | 1 |  | 10 |  | 5 | 1 | [5 empty] | Months
[6 empty] | 2 Pending | 3 | 4.0318 |  |  | Risk: Tier 3 Complete; Oct: 2; Nov: 1 |  |  |  | Status | 5 | 7 | 9 | 10 | 11 | 12 | Grand Total
[6 empty] | 3 Constr Ready | 2 | 1.4635 | [13 empty] | 1 - Complete | 0.34811 | 6.2568 | 3.5761 | 4.5606 |  |  | 14.7417
[6 empty] | 4 Construction | 7 | 5.0964 |  |  | Risk: Missed Goal; Oct: 3 |  |  |  | 1a - Partial Completions |  |  |  |  | 0.9025 | 0.76693 | 1.6694
[6 empty] | 5 Post-Constr | 11 | 6.5621 | [13 empty] | Grand Total - Miles | 0.34811 | 6.2568 | 3.5761 | 4.5606 | 0.9025 | 0.76693 | 16.4111
[6 empty] | Grand Total | 23 | 17.1539
Contractor | (All) | [9 empty] | Risk: Tree Wire?; May: YES | Tree Wire? | YES
Hours per Month | [5 empty] | Project Status - by Project |  |  |  |  | Risk: Project Status - by Project | Project Status - by Project
Sum of Feb | Sum of Apr | Sum of May | Sum of Jun | Sum of Jul |  | Row Labels | Count of Order |  |  |  | Risk: Count of Order; May: Column Labels | Row Labels | Count of Order | Sum of Total Miles including partial completions.
507.5 | 50 | 3746.8 | 9387.3 | 12996.6 |  | 2 Pending | 3 |  |  |  | Row Labels | 5 | 7 | 9 | 10 | 11 | 12 | Grand Total | 1 - Complete | 21 | 14.7417
[6 empty] | 3 Constr Ready | 2 |  |  |  | 1 - Complete | 1 | 10 | 5 | 5 |  |  | 21 | 1a - Complete (Tier 3 only) | 2 | 1.6694
[6 empty] | 4 Construction | 7 |  |  |  | Risk: 1a - Complete (Tier 3 only); Sep: 1; Oct: 1; Nov: 2 | Grand Total | 23 | 16.4111
[6 empty] | 5 Post-Constr | 13 |  |  |  | Grand Total | 1 | 10 | 5 | 5 | 1 | 1 | 23
[6 empty] | Grand Total | 25
Estimate Crews Needed
| Feb | Apr | May | Jun | Jul
507.5 |  |  | 8.1629 | 12.3777 | 0
0 |  |  | 0 | 0 | 0
0 |  |  | 0 | 0 | 0
Avail - ST Man Hours |  | 1050 | 1150 | 1050 | 1100
Risk Summary - by Project
Row Labels | Count of Order | [9 empty] | Risk: Project Status - by Unit
1 - Complete | 13 | [9 empty] | Risk: Row Labels
4 - High Risk | 9 | [9 empty] | Risk: 3 Constr Ready
1a - Complete (Tier 3 only) | 3 | [9 empty] | Risk: 4 Construction
Grand Total | 25 | [9 empty] | Risk: 5 Post-Constr
??
Grand Total
Risk Summary - by Unit | [5 empty] | Project Status - by Project
Row Labels | [5 empty] | Row Labels | Count of Order
1 - Complete | [5 empty] | CC | 2
4 - High Risk | [5 empty] | EB | 6
1a - Complete (Tier 3 only) | [5 empty] | NB | 8
Grand Total | [5 empty] | NV | 2
[6 empty] | PN | 1
[6 empty] | SI | 3
[6 empty] | SO | 3
[6 empty] | Grand Total | 25

## High Risk Detail
Order | Order Description | Div | Project Manager | Const. Resource | User Status | Current Reason Off Track | % of Estimate Complete | Current Out of PEND Date | Risk of not completing by 8/1 | Notes | Who is Working on the Projects Major Hurdles
31338871 | El Cerrito G 1112 (Berkeley) Cal Berkeley | EB | Jeff Kringler | CONTRACT | FICL | Access/Permit | 100% | TBD | 1 - Complete | Risk: Access/Permit: Short window to work with two adjacent city projects. City will not allow full road closure without exstensive review. • TCP/Encroachment permit - Meeting with city and contractor again on 6/28/18 to discuss TCP’s. The Following dependences are still needed before the City of Berkeley will issue the work permit. - Temporary Construction Easement (TCE) for resident parking during the full road closure at locations 71 -89. (The land team is currently working on Easement) - Stand by fire and emergency services has been agreed on and confirmed by Berkeley Fire. (Berkeley Fire has agreed to staff project for 1 one) - PG&E has notified residents affected by road closure and outage by the first week on July . - City of Oakland’s approval for the one day road closure on Panoramic way (the top portion is the City of Oakland’s jurisdiction) . • 7/26 locations 90 – 97, assuming (two) 4-man crews • 7/27 locations 90 – 97, assuming (two) 4-man crews • 7/30 locations 63 – 70, assuming (four) 4-man crews • 7/31 locations 71 – 89, assuming (nine) 4-man crews Please note: Project has started 7/26 and planned to complete 7/31, but has so many variables and pieces that need to fall in place it is still be considered high risk. | Access/Permit: Jeff Kringler (Project Manager) & Claudia Luna (Agency Liaison)
31082394 | Molino 1102 (Santa Rosa) - SIX SPANS FRATI LN | SO | Jeffrey Jung | GC | MAPP | Access/Permit | 100% | 2018-06-28 | 1 - Complete | Reason for missing date: - 2 months to obtain SO Count Permit, due to volume of rebuild work taking place. When received agency added special conditions to full road closure that would not allow crew to perform work. Permit revision couldn't be obtain in time to cmplete by 8/1. | NA
31275384 | MIRABEL 1101 (Santa Rosa)- R7 RECONDUCTOR MAYS CANYON | SO | Jeffrey Jung | GC | MAPP | Access/Permit | 100% | 2018-06-28 | 1 - Complete | Reason for missing date: - 2 months to obtain SO Count Permit, due to volume of rebuild work taking place. When received agency added special conditions to full road closure that would not allow crew to perform work. Permit revision couldn't be obtain in time to cmplete by 8/1. | NA
31246140 | WYANDOTTE 1105 (Oroville)- RECONDUCTOR 3000 FT OF DET 4AR - WY1105 | NV | Aaron Patane | GC | FICL | Outage Restrictions (Heat) | 100% | NA | 1 - Complete | Reason for missing date: - 7/18 Clearance canceled due to heat restrictions. - 6/27 Clearance canceled as crew was send to support NV fires. | NA
31330635 | FORESTHILL 1102 (Foresthill) - SPRING GARDEN RD | SI | Brian Ritchie | GC | FICL | Timing/Size of Project | 100% | 2018-07-13 | 1 - Complete | Risk: Timing/Size of Project: Large project 2.14 miles, EOD 6/20. Challenging Terrain: Helicopter Sets and heavy TW (4/0) causing all poles to be replaced. Very remote. Needed to Meet 8/1: Addtional crews will be needed to complete by 8/1. GC evaluating if crews can be added and work safely. | Timing/Size of Project: Brian Ritchee (Project Manager)
Formulas:
Current Out of PEND Date = VLOOKUP([Order],Master!A:S,19,FALSE)

## Tree Wire
3 | [10 empty] | 59993
Order | MAT | Order Description | Reg | Div | Job Owner Name | Project Managed? | User Status | Risk of not completing by 8/1 | Tree Wire MCODE | DESC | QTY | Planned Ckt Miles | Status | Notes | Construction Resource | Contractor | In-Service Date (Forecasted) | Click Start Date | Click End Date
31246140 | 08W | WYANDOTTE 1105 (Oroville)- RECONDUCTOR 3000 FT OF DET 4AR - WY1105 | NO - Northern | NV | Aaron Patane | Y | FICL | 2 - Low Risk | M290398 | WIRE ELEC INSUL AL 2 AWG 22KV 7/1 ACSR | 15000 | 3309 | Delivered |  | GC | NA | 2018-09-13 | 06/04/2018 | 09/13/2018
31082394 | 08W | Molino 1102 (Santa Rosa) - SIX SPANS FRATI LN | NO - Northern | SO | Jeffrey Jung | N | MAPP | 3 - Medium Risk | M290398 | WIRE ELEC INSUL AL 2 AWG 22KV 7/1 ACSR | 2500 | 1486 | Delivered |  | GC | NA | 2018-09-16 | 09/10/2018 | 09/13/2018
31095523 | 08W | OAKLAND K 1103 (Oakland) - EB-RELIAIBLITY -K1103, REPL #4ACSR W | BA - Bay Area | EB | Michael Lee | N | FICL | 2 - Low Risk | M290398 | WIRE ELEC INSUL AL 2 AWG 22KV 7/1 ACSR | 7500 | 1838 | Delivered |  | GC | NA | 2018-05-30 | 09/22/2017 | 05/30/2018
31206912 | 08W | CAMP EVERS 2103(Santa Cruz) - WDN 15-0073161 CE2103-OLD GRAHM HL R | CC - Central Coast | CC | Ola Lamidi | N | #N/A | 2 - Low Risk | M295046 | WIRE ELEC INSL AL 4/0 AWG 22KV 7 STRAND | 2200 | 705 | Delivered |  | GC | NA | 2018-07-16 | ? | ?
31204706 | 08W | ALTO 1124 (Mill Valley)- THROCKMORTON LANE | BA - Bay Area | NB | Steve Jackson | Y | FICL | 2 - Low Risk | M295046 | WIRE ELEC INSL AL 4/0 AWG 22KV 7 STRAND | 4856 | 1613 | Delivered |  | CONTRACT | Wilson | 2018-07-30 | 06/18/2018 | 07/30/2018
31169729 | 08W | Oakland D 1112 (Oakland) - 2017 D1112/K1101 UWF | BA - Bay Area | EB | Carolina Huerta | Y | FICL | 2 - Low Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 3642 | 4171 | Delivered |  | GC | NA | 2018-07-17 | 05/23/2018 | 07/23/2018
31338871 | 08W | El Cerrito G 1112 (Richmond) - RICHMOND-REPL #6 CU-UWF_PH2 | BA - Bay Area | EB | Jeff Kringler (Tony Chan till 5/21) | Y | FICL | 4 - High Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 12004 | 3505 | Delivered |  | CONTRACT | Intren | 2018-10-13 | 07/25/2018 | 10/13/2018
31169728 | 08W | Oakland K 1102 (Oakland)- GRIZZLY PEAK REPL #6 CU-UWF | BA - Bay Area | EB | Linda Swartz / Carolina Huerta | Y | CONS | 4 - High Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 12000 | 5016 | Delivered |  | CONTRACT | Power | 2018-11-15 | 06/22/2018 | 11/15/2018
31234871 | 08W | Oakland K 1104 (Oakland) - UWF K1104/X1105/6 | BA - Bay Area | EB | Matt Herron/ Peter Siu | Y | MAPP | 4 - High Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 11778 | 7271 | Delivered |  | CONTRACT | Intren | 2018-09-25 | 06/26/2018 | 09/25/2018
31207089 | 08J | GREENBRAE 1103 (Mill Valley) - HAWTHORN, GB 1103 | BA - Bay Area | NB | Steve Jackson | Y | FICL | 2 - Low Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 3954 | 4687 | Delivered |  | CONTRACT | Wilson | 2018-09-25 | 07/10/2018 | 07/31/2018
31207126 | 08W | ALTO 1125 (Mill Valley) -PANORAMIC HWY, COUNTY, | BA - Bay Area | NB | Steve Jackson | Y | FICL | 2 - Low Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 16454 | 5300 | Delivered |  | CONTRACT | Wilson | 2018-07-18 | 05/30/2018 | 07/17/2018
31205343 | 08W | ALTO 1124 (Mill Valley) - SUMMIT AVE , CITY | BA - Bay Area | NB | Steve Jackson | Y | FICL | 2 - Low Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 11994 | 5006 | Delivered |  | CONTRACT | Wilson | 2018-07-28 | 06/04/2018 | 06/29/2018
31205198 | 08W | ALTO 1125 (Mill Valley)- REED ST, COUNTY | BA - Bay Area | NB | Steve Jackson | Y | FICL | 2 - Low Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 12002 | 3900 | Delivered |  | CONTRACT | Wilson | 2018-07-16 | # | #
31205418 | 08W | ALTO 1125 (Mill Valley)- BROOKLINE AVE, COUNTY, | BA - Bay Area | NB | Steve Jackson | Y | FICL | 2 - Low Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 16000 | 5480 | Delivered |  | CONTRACT | Wilson | 2018-07-30 | 06/25/2019 | 07/25/2019
31330635 | 08W | FORESTHILL 1101 (Foresthill) - SPRING GARDEN RD 08J | NO - Northern | SI | Brian Ritchie | Y | FICL | 4 - High Risk | M290398 | WIRE ELEC INSUL AL 2 AWG 22KV 7/1 ACSR | 28373 | 11308 | Ordered |  | GC | NA | 2018-10-04 | 07/16/2018 | 10/05/2018
31255868 | 08W | ROB ROY 2104 (Day Valley)- HIGH SPLICE CABLE REPLACE | CC - Central Coast | CC | Sharon Kennedy | Y | PREC | 4 - High Risk | M290398 | WIRE ELEC INSUL AL 2 AWG 22KV 7/1 ACSR | 4350 | 1439 | Delivered |  | GC | NA | 2018-07-27 | 07/16/2018 | 07/31/2018
31275384 | 08W | MIRABEL 1101 (Santa Rosa)- R7 RECONDUCTOR MAYS CANYON | NO - Northern | SO | Jeffrey Jung | N | MAPP | 3 - Medium Risk | M295046 | WIRE ELEC INSL AL 4/0 AWG 22KV 7 STRAND | 6256 | 1986 | Not Ordered |  | GC | NA | 2018-10-09 | 09/10/2018 | 10/09/2018
31286571 | 08W | EL DORADO PH 2102 (Pollock Pines) - HIGH SPLICE AREA | NO - Northern | SI | Brian Ritchie | Y | FICL | 3 - Medium Risk | M290398 | WIRE ELEC INSUL AL 2 AWG 22KV 7/1 ACSR | 6300 | 1928 | Delivered |  | GC | NA | 2018-09-11 | 07/10/2018 | 09/11/2018
31264915 | 08W | RINCON 1103 (Santa Rosa) - R7 RECONDUCTOR WILSON RD- | NO - Northern | SO | Jeffrey Jung | N | FICL | 2 - Low Risk | M290398 | WIRE ELEC INSUL AL 2 AWG 22KV 7/1 ACSR | 2397 | 957 | Delivered |  | CONTRACT | Wilson | 2018-07-26 | # | #
31098626 | 08W | CLARKSVILLE 2104 (El Dorado Hills) - ECONDUCTOR -PH 3 Y2018 | NO - Northern | SI | Brian Ritchie | Y | UNSC | 4 - High Risk | M295046 | WIRE ELEC INSL AL 4/0 AWG 22KV 7 STRAND | 25364 | 8052 | Ordered | 9355 ft remaining. Not need for a away Tier 1/2. | GC | NA | 2019-03-31 | 09/12/2018 | 10/01/2018
31206678 | 08W | ALTO 1125 (Mill Valley) -SEQUOIA VLY RD CTY/CNTY | BA - Bay Area | NB | Steve Jackson | Y | UNSC | 3 - Medium Risk | M295046 | WIRE ELEC INSL AL 4/0 AWG 22KV 7 STRAND | 8877 | 2817 | Delivered |  | CONTRACT | Wilson | 2019-01-30 | 03/29/2019 | 03/29/2019
31205937 | 08W | ALTO 1125 (Mill Valley) -HELENS LN,CITY/CNTY,ALTO | BA - Bay Area | NB | Steve Jackson | Y | MAPP | 3 - Medium Risk | M295046 | WIRE ELEC INSL AL 4/0 AWG 22KV 7 STRAND | 14387 | 5000 | Delivered |  | CONTRACT | Wilson | 2018-10-17 | 09/09/2018 | 10/05/2018
31132867 | 08W | Half Moon Bay 1101 (Half Moon Bay)- REPLACE OH LINE SKYLINE BLVD | CC - Central Coast | PN | Les Beeghly | Y | #N/A | 4 - High Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 14624.7 | 4638 | Delivered |  | CONTRACT | ILB | 2018-07-31 | ? | ?
Formulas:
In-Service Date (Forecasted) = IFERROR(INDEX([2]Tracker!$A1:BK10017, MATCH([Order],[2]Tracker!$A1:A10017,0), MATCH([2]Tracker!$AA1,[2]Tracker!$A1:BK1,0)),"?")

## Drop Down
1 - Complete | JO | JO Name | PM? | Region | Abbr. | Division | Abbr. | Status | Phase | Status | Phase
2 - Low Risk | ? | UNKNOWN | N | BA - Bay Area | BA | Central Coast | CC | ADER | 1 Estimating | ADER | Estimating
3 - Medium Risk | A1CO | Tony Chan | Y | CC - Central Coast | CC | De Anza | DA | APPR | 1 Estimating | APPR | Estimating
4 - High Risk | A1L6 | Alexis Herrera | Y | CV - Central Valley | CV | Diablo | DI | CNCL | 6 Other | CNCL | Other
1a - Complete (Tier 3 only) | A2LH | Tony Lucero | Y | NO - Northern | NO | East Bay | EB | CONS | 4 Construction | CONS | Construction
| A3PC | Portilla, Alex | N |  |  | Fresno | FR | DCNL | 1 Estimating | DCNL | Estimating
| AAD3 | De La Rocha, Arthur | Y |  |  | Humboldt | HB | DOCC | 5 Post-Constr | DOCC | Post-Constr
| ACF4 | Allen Fong | Y |  |  | Kern | KE | ERDY | 1 Estimating | ERDY | Estimating
| AEH0 | Alex Herrera | N |  |  | Los Padres | LP | ESTS | 1 Estimating | ESTS | Estimating
| AHC5 | Angie Kim | Y |  |  | Mission | MI | FICL | 5 Post-Constr | FICL | Post-Constr
| ALWK | Alyssa Wright | N |  |  | North Bay | NB | MAPP | 5 Post-Constr | MAPP | Post-Constr
| APE3 | Everson, Andrew | N |  |  | North Valley | NV | PEND | 2 Pending | PEND | Pending
| ATO3 | Abraham Ortiz | N |  |  | Peninsula | PN | PREC | 5 Post-Constr | PREC | Post-Constr
| AVP4 | Aaron Patane | Y |  |  | Sacramento | SA | PROD | 6 Other | PROD | Other
| AXDJ | Anandi De La Fuente | N |  |  | San Francisco | SF | SRDY | 4 Construction | SRDY | Construction
| AXHP | Alex Hom | Y |  |  | San Jose | SJ | UNSC | 3 Constr Ready | UNSC | Constr Ready
| AXWJ | Andre Williams | Y |  |  | Sierra | SI | UNSE | 1 Estimating | UNSE | Estimating
| B1C9 | Carretero, Brenda | Y |  |  | Sonoma | SO | UNSE HOLD | 1 Estimating | UNSE HOLD | Estimating
| B1LF | Laemmlen, Brandt | Y |  |  | Stockton | ST | CLSD | 5 Post-Constr | CLSD | Post-Constr
| BCF1 | Feis, Brian | N |  |  | Yosemite | YO
| BDK5 | Koelling, Brad | N
| BER5 | Brian Ritchie | Y
| BGW5 | Bruce Whitcomb | N
| BJTA | Tonegato, Brian J | Y
| BMT2 | Brian To | N
| BNLB | Bruce Lozano | N
| C3CJ | Cris Cabanillas | N
| C4CU | Candace Caulkins | Y
| CAHW | Carolina Huerta | Y
| CHM7 | Moncrief, Connor | N
| CJA8 | Carlos Araquistain | N
| CMP5 | Powell, Christopher | N
| CNL3 | Connie Lam | Y
| CSC1 | Cynthia Chan-Wong | Y
| CTD7 | Christopher Dux | N
| D3LL | Daniel Lidyoff | N
| D7CJ | Caponpon, Danielle | N
| DAV0 | Daniel Van Groningen | Y
| DET3 | Daniel Thomas | N
| DEWI | Daniel Waters | N
| DHN4 | Dan Nguyen | N
| DMAL | Aguiar, Demetrio | N
| DRCF | Daniel Chung | Y
| DRM9 | Metzker, David | N
| DRN3 | Dale Novakovich | N
| DSMC | David Moore | N
| DSGB | Gerpheide, Dan | Y (Sub)
| DVN5 | Nguyen, Du | N
| DWS8 | Daniel Spencer | N
| E2MA | Erik Madsen | N
| EMGA | Eddie Gerani | N
| EXE5 | Embaye, Eyob | Y
| EXNN | Emilio Nunez | N
| EXVH | Eric Vazquez | N
| FCR1 | Felix Regacho | N
| FMB6 | Fatima Colorado | N
| FXRZ | Fernando Recoder | N
| GAE9 | Esguerra, Glenn | N
| GHD2 | Gregory Do | N
| GMK5 | Gregory Kacherginsky | N
| GSD5 | Gurshawn Dhillon | N
| GXFF | Grigoriy Frenkel | N
| HGL3 | Hilton Law | N
| HSA1 | Harinderpal Aulakh | N
| INM2 | Ignacio Martinez | N
| IRB2 | Ivan Baez | N
| JIHH | Haji-Amiri, Joe Amiri | Y
| J1M9 | Monson, Jennifer M | Y
| J1PE | Jaime Pantoja | Y
| J1RL | Richards, Jon | N
| J5CP | Juan Castillo | N
| J91F | Justin Stabe | Y
| JBJ8 | Jeffrey Jung | N
| JCS9 | James Shin | N
| JDLM | Lorz, Jesse | N
| JJV7 | Joaquin Valencia | N
| JKH3 | Jackie Henry | Y
| JLDE | Goncalves, Jennifer | N
| JMB4 | Jeff Brewer | N
| JRAC | Justin Altmiller | N
| JSKE | Jasjit Khangura | N
| JXF8 | Joe Fong | N
| JZF1 | Fernandez, John | N
| JZHC | Josh Hinkey | Y
| KGH6 | Kenneth Huffman | N
| KRBK | Kevin Banister | N
| KWB6 | Ken Brem | Y
| KXAV | Unknown | N
| L3MP | Martinez, Leticia | N
| LLD1 | Lisa Derita | N
| LLM0 | Linda Swartz | Y
| LMSQ | Soria, Luis | N
| M0S4 | Shaeffer, Michael | Y
| MAJC | Jimenez, Mark A | N
| M2HM | Matthew Herron | Y
| M2KU | Mamadou Keita | N
| M3ML | Mauricio Morquecho | N
| M3SE | Mohinder Singh | Y
| M4GV | Giovannetti, Michael | Y
| MAPY | Miguel Plascencia | N
| MBA4 | Mark Abrams | Y
| MENE | Mark Nicholson | Y
| MFN3 | Fran Nunez | N
| MJL9 | Lew, Michael | N
| MLMW | Michelle Myles | Y
| MSJ9 | Maria Joves | N
| MTN6 | Minhhang Nguyen | N
| MTP9 | May Nguyen | N
| MTTA | Musie Tesfasilassie | N
| MUSF | Maria Silva | N
| MXEN | Mohamed Elzain | N
| MXT7 | Ming Tsai | N
| MXUA | Mason Ung | N
| MYL5 | Michael Lee | N
| NHH1 | Harris, Norman | N
| NONE | ? | N
| ODD2 | Orbie Davis | Y
| PJMW | Patrick McCabe | N
| PLO2 | Unknown | N
| PPT1 | Pablo Torres | N
| POM1 | Mullapudi, Phani R | Y
PXCO
| R4BA | Angelo Barron | N
| R8SL | Rahma Said | N
| RDR1 | Richard Raths | N
| RERE | Renee Romo | Y
| RJSM | RJ Snook | N
| RPBK | Raj Bhula | N
| RSKB | Khangura, Ravinder | Y (TL)
| RVS7 | Richard Salcedo | N
| RWC7 | Rick Cowin | Y
| S1GP | Scott Garvey | Y
| S2J9 | Jackson, Steve | Y
| S2WT | Steve Whitman | Y
| S3B2 | Shahryar Bayat | N
| S4CV | Steve Chu | Y
| S8BY | Beeghly, Les | Y
| SDK6 | Scott Kostka | N
| SGBA | Steve Barrow | Y
| SJJ8 | Steve Jackson | N
| SKA1 | Scott Avery | N
| SKJ4 | Stan Jang | Y
| SKV4 | ? | N
| SLH8 | Shawn Howard | N
| SLKD | Sharon Kennedy | Y
| SMM9 | Steve Marchetti | N
| SREB | Evers, Scott | Y (Sub)
| SRH2 | Steve Henke | N
| SYST | SYSTEM | N
| SZC1 | Scott Chen | N
| T1SI | Soe, Thiha | N
| TEJ2 | Jones, Todd | N
| TJCA | Tom Cannon | N
| TJO9 | O'Keefe, Tracy | Y (Sub)
| TRA1 | Ted Albrigo | N
| TVC1 | Tom Chan | Y
| TXY6 | Tom Yang | N
| VXLA | Victor Lopez | N
| VXRO | Rodriguez-Ruiz, Vincent | N
| WCL5 | Warren Lau | N
| WMA1 | Abbott, William | Y
| WPS3 | William Salvador | N
| JSBY | Jason Barrett | Y
| JFCG | Juan Clara | N
| OXL3 | Ola Lamidi | N
| J1JD | Jesse Joyner | Y
| S4BZ | Steven Beeny | Y
| HSB5 | Harpreet Bassi | N
| DEBO | David Bales | N
| J6KF | Jeff Kringler | Y
| DWPH | David Phillips | Y
| HXYE | Helen Yu-Lei | Y
| GSH6 | Jerry Hostler | N
| PXSO | Peter Sui | Y
| S3AC | Sergey Asratyan | N