## SH Data
Order | Order Description | Program | Contractor | Planned Conductor Miles | Total Installed Miles | Installed / Planned | QA Pass | QA Fix | Total QA Span Length | QA Remaining | Percent QA | QA Trailing Installed | IA Pass | IA Fix | IA Remaining | Percent IA | iAudit Uploaded | Span Notes | Sub-Category | 2019 Miles Installed | 2020 Miles Installed
30977614 | WDDB OTTER 1102 PHASE 4 | SH | MGE | 0.69716 | 0 | 0 | 0 | 0 | 0.69735 | 0.69735 | 0% | 0 | 0 | 0 | 0.69735 | 0% |  |  |  | 0 | 0
31088475 | CCM REM IDLE LINE^ 17171 SFD BVD INVERV | IF |  | 0.69564 | 0.69564 | 1 | 0.69564 | 0 | 0.69564 | 0 | 100% | 0 | 0.69564 | 0 | 0 | 100% |  |  |  | 0.69564 | 0
31209950 | R7 RECON POTTER VLY 1105 ( VAN ARSDALE) | SH |  | 0.5697 | 0.5697 | 1 | 0.5697 | 0 | 0.5697 | 0 | 100% | 0 | 0.5697 | 0 | 0 | 100% |  |  |  | 0.5697 | 0
31254545 | POLE_IDLE_REMV-SEWER TREATMENT PLANT | IF |  | 0.16231 | 0.16231 | 1 | 0.16231 | 0 | 0.16231 | 0 | 100% | 0 | 0.16231 | 0 | 0 | 100% |  |  |  | 0.16231 | 0
31290145 | R7 SAN RAFAEL 1107 COND REPLACEMENT | SH |  | 0.1517 | 0.1517 | 1 | 0.1517 | 0 | 0.1517 | 0 | 100% | 0 | 0.1517 | 0 | 0 | 100% |  |  |  | 0.1517 | 0
31326034 | STS-POLE_IDLE_REMV - 27218 FAIRVIEW AVE | IF |  | 0.025379 | 0.025379 | 1 | 0.025379 | 0 | 0.025379 | 0 | 100% | 0 | 0.025379 | 0 | 0 | 100% |  |  |  | 0.025379 | 0
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT | SH | Wilson | 1.5074 | 1.5074 | 1 | 1.5074 | 0 | 1.5074 | 0 | 100% | 0 | 1.5074 | 0 | 0 | 100% | 11/3/2020 |  | 220 Mile Plan | 0 | 1.5074
31366453 | STS-COND_BROK_REPL - LANDERGEN RD HONEYD | IF |  | 0.038826 | 0.038826 | 1 | 0.038826 | 0 | 0.038826 | 0 | 100% | 0 | 0.038826 | 0 | 0 | 100% |  |  |  | 0.038826 | 0
31406815 | POD REMV IDLE FAC 4800 MUNIZ RANCH*W | IF |  | 0.072159 | 0.072159 | 1 | 0.072159 | 0 | 0.072159 | 0 | 100% | 0 | 0.072159 | 0 | 0 | 100% |  |  |  | 0.072159 | 0
35014742 | 0628 IDLE FACIREPL - 1S/O 16823 COLEMAN | IF |  | 0.15208 | 0.15208 | 1 | 0.15208 | 0 | 0.15208 | 0 | 100% | 0 | 0.15208 | 0 | 0 | 100% |  |  |  | 0.15208 | 0
35016357 | STS-COND_IDLE_REMV-LCO 2961 DENNY RD | IF |  | 0.12254 | 0.12254 | 1 | 0.12254 | 0 | 0.12254 | 0 | 100% | 0 | 0.12254 | 0 | 0 | 100% |  |  |  | 0.12254 | 0
35016714 | 12/31-ST-CON_IDL_RMV-2 S/O TX-WHEEL BARR | IF |  | 0.16212 | 0.16212 | 1 | 0.16212 | 0 | 0.16212 | 0 | 100% | 0 | 0.16212 | 0 | 0 | 100% |  |  |  | 0 | 0.16212
30977613 | WDDB OTTER 1102 PHASE 3 | SH | MGE | 0.68883 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
31215474 | RECONDUCTOR ROB ROY 2104-MCDONALD RD | SH | MGE | 0.51496 | 0.51 | 0.99036 | 0.51496 | 0 | 0.51496 | 0 | 100% | -0.0049621 | 0.51496 | 0 | 0 | 100% | 8/4/2020 |  |  | 0.51 | 0
31291071 | OCGC 14043533 WRO - HWY 175 MIDDLETOWN |  |  | 1.2468 | 1.2468 | 1 | 1.2468 | 0 | 1.2468 | 0 | 100% | 0 | 1.2468 | 0 | 0 | 100% |  |  |  | 1.2468 | 0
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  |  | 0.58712 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
31298793 | OFAC_IDLE_REMV - 2 S/O 5 W/O 5245 HWY 49 | IF |  | 0.053977 | 0.053977 | 1 | 0.053977 | 0 | 0.053977 | 0 | 100% | 0 | 0.053977 | 0 | 0 | 100% |  |  |  | 0.053977 | 0
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | SH | Source Power (ARB) | 0.51326 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | SH |  | 1.42 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | SH | Source Power (ARB) | 0.4483 | 0 | 0 | 0 | 0 | 0.4483 | 0.4483 | 0% | 0 | 0 | 0 | 0.4483 | 0% |  |  |  | 0 | 0
31475979 | NC-SO-SONOMA 10/23/19 KINCADE FIRE UG CA |  |  | 0.99924 | 0.99924 | 1 | 0.99924 | 0 | 0.99924 | 0 | 100% | 0 | 0.99924 | 0 | 0 | 100% |  |  |  | 0.99924 | 0
35011276 | STS-COND_IDLE_REMV-#2E CO#9975 W/O SHIRL | IF |  | 0.056818 | 0.056818 | 1 | 0.056818 | 0 | 0.056818 | 0 | 100% | 0 | 0.056818 | 0 | 0 | 100% |  |  |  | 0 | 0.056818
35018787 | HALSEY 1101 - S039NO112 HIGH SPLICE 08J | SH |  | 0.54053 | 0.54053 | 1 | 0.54053 | 0 | 0.54053 | 0 | 100% | 0 | 0.54053 | 0 | 0 | 100% |  |  |  | 0.54053 | 0
35026643 | RECONDUCTOR DIAMOND SPRINGS 1105 | SH |  | 1.9 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35032266 | APPLE HILL 1104 RECONDUCTOR | SH |  | 0.1661 | 0.1661 | 1 | 0.1661 | 0 | 0.1661 | 0 | 100% | 0 | 0.1661 | 0 | 0 | 100% |  |  |  | 0.1661 | 0
35038141 | STS-COND_IDLE_REMV-BRUSH CREEL LANE | IF |  | 0.061174 | 0.061174 | 1 | 0.061174 | 0 | 0.061174 | 0 | 100% | 0 | 0.061174 | 0 | 0 | 100% |  |  |  | 0.061174 | 0
30962842 | REM OH FAC -408 MILL RD. FEATHER FA | IF |  | 1.3258 | 1.3258 | 1 | 1.3258 | 0 | 1.3258 | 0 | 100% | 0 | 1.3258 | 0 | 0 | 100% |  |  |  | 1.3258 | 0
31254945 | 4/30/18 REMV IF -750 CHILENO VALLEY*OCLH | IF |  | 0.051136 | 0.051136 | 1 | 0.051136 | 0 | 0.051136 | 0 | 100% | 0 | 0.051136 | 0 | 0 | 100% |  |  |  | 0.051136 | 0
31272375 | CWSP PT. MORETTI BEYOND 5995 |  |  | 0.97538 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
31289238 | FRUITLAND 1142 INS TREE WIRE LR 6064 | SH |  | 1.1877 | 1.1877 | 1 | 1.1877 | 0 | 1.1877 | 0 | 100% | 0 | 1.1877 | 0 | 0 | 100% |  |  |  | 1.1877 | 0
31297994 | 12/31/18-T2-PLE_IDL_REM-1E/O 16N/O C/O P | IF |  | 0.16951 | 0.16951 | 1 | 0.16951 | 0 | 0.16951 | 0 | 100% | 0 | 0.16951 | 0 | 0 | 100% |  |  |  | 0.16951 | 0
31360766 | FROGTOWN 1701 RECOND 1153FTTO 1/0ACSR TW | SH | Intren | 0.22 | 0.22 | 1 | 0.21837 | 0 | 0.21837 | 0 | 99.26% | 0.0016288 | 0.21837 | 0 | 0 | 99.26% |  |  |  | 0.22 | 0
35008479 | R2 2019 AUBERRY 1101 RECONDUCTOR | SH | Intren | 0.31 | 0.31 | 1 | 0 | 0 |  | 0 | 0% | 0.31 | 0 | 0 | 0 | 0% |  |  |  | 0.31 | 0
35012324 | STS-TRAN_IDLE_REMV-2 POLES EAST OF C/O'S | IF |  | 0.049811 | 0.049811 | 1 | 0.049811 | 0 | 0.049811 | 0 | 100% | 0 | 0.049811 | 0 | 0 | 100% |  |  |  | 0.049811 | 0
35023687 | R2RPL OH WIRE ON B LOMND 0401 17-0095503 | SH | MGE | 1.3341 | 1.3341 | 1 | 1.3341 | 0 | 1.3341 | 0 | 100% | -1.7225e-16 | 1.3341 | 0 | 0 | 100% |  |  |  | 1.3341 | 0
35025977 | REMV 4 IDLE POLES 12099 HWY 12 KEN*OCLH | IF |  | 0.13485 | 0.13485 | 1 | 0.13485 | 0 | 0.13485 | 0 | 100% | 0 | 0.13485 | 0 | 0 | 100% |  |  |  | 0.13485 | 0
35028500 | *FT-REPL POLE:17SW/O C/O 7943 TO KATE H. | IF |  | 0.65152 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35037728 | REMV IF 3 LOCS-STEWARTS PT SKAGGS *OCLH | IF |  | 0.098485 | 0.098485 | 1 | 0.097538 | 0 | 0.097538 | 0 | 99.04% | 0.00094697 | 0.097538 | 0 | 0 | 99.04% |  |  |  | 0 | 0.098485
35052718 | OCGC CWSP: ANGWIN OH TO UG DEMO - PH 2 | SH |  | 0.42898 | 0.42898 | 1 | 0.42898 | 0 | 0.42898 | 0 | 100% | 0 | 0.42898 | 0 | 0 | 100% |  |  |  | 0.42898 | 0
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | SH |  | 2.0153 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35060991 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH2.01 |  |  | 0.46686 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35060992 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH1.01 |  |  | 0.47992 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35061709 | SILVERADO 2104 RECONDUCTOR PROJECT | SH |  | 1.5157 | 1.5157 | 1 | 1.5157 | 0 | 1.6388 | 0.12311 | 100% | 0 | 1.5157 | 0 | 0.12311 | 100% |  |  |  | 1.5157 | 0
31081464 | STS-REMV IDLE FAC 8110 DICK COOK RD | IF |  | 0.15511 | 0.15511 | 1 | 0.15511 | 0 | 0.15511 | 0 | 100% | 0 | 0.15511 | 0 | 0 | 100% |  |  |  | 0.15511 | 0
31082393 | RECON THREE SPANS CHERRY RIDGE RD | SH |  | 0.25473 | 0.25473 | 1 | 0.25473 | 0 | 0.25473 | 0 | 100% | 4.3063e-17 | 0.25473 | 0 | 0 | 100% |  |  |  | 0.25473 | 0
31098626 | CLARKSVILLE 2104 RECONDUCTOR -PH 3 Y2018 | SH | GC | 1.5223 | 1.5223 | 1 | 1.525 | 0 | 1.525 | 0 | 100.2% | -0.0026515 | 1.525 | 0 | 0 | 100.2% | 7/31/2020 |  | 220 Mile Plan | 0 | 1.5223
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 | SH | WIlson | 1.7968 | 1.7968 | 1 | 1.7968 | 0 | 1.7968 | 0 | 100% | -3.1006e-15 | 1.7968 | 0 | 0 | 100% | 11/9/2020 |  | 220 Mile Plan | 0 | 1.7968
31254690 | CCM COND_IDLE_REMV+-3640 HWY 128 | IF |  | 0.056818 | 0.056818 | 1 | 0.056818 | 0 | 0.056818 | 0 | 100% | 0 | 0.056818 | 0 | 0 | 100% |  |  |  | 0.056818 | 0
31323810 | T3-COND_IDLE_REMV-2042 HIDDEN VALL*OCLH | IF |  | 0.034091 | 0 | 0 | 0 | 0 | 0.034091 | 0.034091 | 0% | 0 | 0 | 0 | 0.034091 | 0% |  |  |  | 0 | 0
31415330 | NO-NV-BUTTE-11/08/18 CAMP FIRE |  |  | 4.6129 | 4.6129 | 1 | 4.6129 | 0 | 4.6129 | 0 | 100% | 0 | 4.6129 | 0 | 0 | 100% |  |  |  | 4.6129 | 0
35018788 | APPLE HILL 1104 - S049NO119 HIGH SPLICE | SH |  | 1.1593 | 1.1593 | 1 | 1.1593 | 0 | 1.1593 | 0 | 100% | -1.7225e-16 | 1.1593 | 0 | 0 | 100% |  |  |  | 1.1593 | 0
35019006 | ROB ROY 2104 CO11865 REPLACE OH LINE | SH | GC | 1.804 | 1.804 | 1 | 1.804 | 0 | 1.804 | 0 | 100% | 0 | 1.804 | 0 | 0 | 100% |  |  |  | 1.804 | 0
35022707 | XSTS-COND_IDLE_REMV-HWY 1 (AREA 3 SPANS | IF |  | 0.074811 | 0.074811 | 1 | 0.074811 | 0 | 0.074811 | 0 | 100% | 0 | 0.074811 | 0 | 0 | 100% |  |  |  | 0.074811 | 0
35026994 | STS-POLE_IDLE_REMV - 7140 KELSEY CREEK D | IF |  | 0.073864 | 0.073864 | 1 | 0.073864 | 0 | 0.073864 | 0 | 100% | 0 | 0.073864 | 0 | 0 | 100% |  |  |  | 0.073864 | 0
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | SH |  | 0.68996 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
31153500 | STS-COND_IDLE_REMV-27534 GRANDVIEW | IF |  | 0.25852 | 0.25852 | 1 | 0.25852 | 0 | 0.25852 | 0 | 100% | 0 | 0.25852 | 0 | 0 | 100% |  |  |  | 0.25852 | 0
31232280 | ZACA 1102 LONG CYN RD, SANTA YNEZ | SH | MGE | 1.1081 | 1.1081 | 1 | 1.1081 | 0 | 1.1081 | 0 | 100% | 0 | 1.1081 | 0 | 0 | 100% |  |  |  | 1.1081 | 0
31252335 | 0611POLE_IDLE_REMV-12398 SHALE RIDGE LN | IF |  | 0.094508 | 0.094508 | 1 | 0.094508 | 0 | 0.094508 | 0 | 100% | 0 | 0.094508 | 0 | 0 | 100% |  |  |  | 0.094508 | 0
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  |  | 1.6098 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
31364361 | 0428OFAC_IDLE_REMV 12310 OLD AUBURN 4TA | IF |  | 0.074621 | 0.074621 | 1 | 0.074621 | 0 | 0.074621 | 0 | 100% | 0 | 0.074621 | 0 | 0 | 100% |  |  |  | 0.074621 | 0
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE | SH |  | 1.27 | 1.27 | 1 | 1.27 | 0 | 1.27 | 0 | 100% | 0 | 1.27 | 0 | 0 | 100% |  |  |  | 1.27 | 0
31429487 | OTTER-1101 S030CC121 - TRANS POLES | SH |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35010118 | STS-COND_IDLE_REMV - 695 ORCHARD AVE SON | IF |  | 0.028409 | 0.028409 | 1 | 0.028409 | 0 | 0.028409 | 0 | 100% | 0 | 0.028409 | 0 | 0 | 100% |  |  |  | 0.028409 | 0
35011253 | STS-POLE_IDLE_REMV-OPP 5865 POOLE STATIO | IF |  | 0.15152 | 0.15152 | 1 | 0.15152 | 0 | 0.15152 | 0 | 100% | 0 | 0.15152 | 0 | 0 | 100% |  |  |  | 0.15152 | 0
35011254 | STS-TRAN_IDLE_REMV-OLD BULK OIL PLANT 1/ | IF |  | 0.066288 | 0.066288 | 1 | 0.066288 | 0 | 0.066288 | 0 | 100% | 0 | 0.066288 | 0 | 0 | 100% |  |  |  | 0.066288 | 0
35024926 | MARTELL 1101 RECONDCUTOR 3,700FT | SH | Intren | 0.13 | 0.13 | 1 | 0.13 | 0 | 0.13 | 0 | 100% | 0 | 0.13 | 0 | 0 | 100% |  |  |  | 0.13 | 0
35037594 | COND_IDLE_REMV-JUNCTION @ HWY 36 & R | IF |  | 0.094129 | 0.094129 | 1 | 0.094129 | 0 | 0.094129 | 0 | 100% | 0 | 0.094129 | 0 | 0 | 100% |  |  |  | 0.094129 | 0
35038312 | +STS-COND_IDLE_REMV-S OF 7100 FOXEN CYN | IF |  | 0.060606 | 0.060606 | 1 | 0.060606 | 0 | 0.060606 | 0 | 100% | 0 | 0.060606 | 0 | 0 | 100% |  |  |  | 0.060606 | 0
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 | SH | GC | 2.8733 | 2.8733 | 1 | 2.8735 | 0 | 2.8735 | 0 | 100% | -0.00018939 | 2.8735 | 0 | 0 | 100% |  |  | 220 Mile Plan | 2.8733 | 0
35054959 | STS-POLE_IDLE_REMV - 4215 HOLLIS LN FIDD | IF |  | 0.076894 | 0.076894 | 1 | 0.076894 | 0 | 0.076894 | 0 | 100% | 0 | 0.076894 | 0 | 0 | 100% |  |  |  | 0.076894 | 0
35055474 | OCGC REDBUD 1101 RECONDUCTOR FOR NB LOAD | SH | GC | 1.4309 | 1.4309 | 1 | 1.4309 | 0 | 1.4309 | 0 | 100% | 0 | 1.4309 | 0 | 0 | 100% |  |  |  | 1.4309 | 0
31048050 | STS-OFAC_IDLE_REMV-WENTWORTH SPRINGS | IF |  | 0.22443 | 0.22443 | 1 | 0.22443 | 0 | 0.22443 | 0 | 100% | 0 | 0.22443 | 0 | 0 | 100% |  |  |  | 0.22443 | 0
31252580 | 3/1/18 REMV IF IRO COURTNEY DR KENW*OCLH | IF |  | 0.032386 | 0.032386 | 1 | 0.032386 | 0 | 0.032386 | 0 | 100% | 0 | 0.032386 | 0 | 0 | 100% |  |  |  | 0 | 0.032386
31511571 | NR-NB-NAPA- 8/17/20-LNU COMPLEX FIRE OH |  |  | 29 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  | T1 A Tag | 0 | 0
35011295 | *FT-OFAC_IDLE_REMV-6301 ECHO LN | IF |  | 0.29981 | 0.29981 | 1 | 0.29981 | 0 | 0.29981 | 0 | 100% | 0 | 0.29981 | 0 | 0 | 100% |  |  |  | 0.29981 | 0
35018047 | +STS-POLE_IDLE_REMV - TABLE MTNSAN MIGUE | IF |  | 0.1589 | 0.1589 | 1 | 0.1589 | 0 | 0.1589 | 0 | 100% | 0 | 0.1589 | 0 | 0 | 100% |  |  |  | 0.1589 | 0
35022861 | STS-POLE_IDLE_REMV-CHURCH MINE RD | IF |  | 0.41061 | 0.41061 | 1 | 0.41061 | 0 | 0.41061 | 0 | 100% | 0 | 0.41061 | 0 | 0 | 100% |  |  |  | 0.41061 | 0
35037701 | TRAN_IDLE_REMV-M.P. 4.39 AVE OF THE | IF |  | 0.15019 | 0.15019 | 1 | 0.05928 | 0 | 0.05928 | 0 | 39.47% | 0.090909 | 0.05928 | 0 | 0 | 39.47% |  |  |  | 0 | 0.15019
35038571 | POLE_IDLE_REMV-NEXT TO BUSCH CR | IF |  | 0.051705 | 0.051705 | 1 | 0.051705 | 0 | 0.051705 | 0 | 100% | 0 | 0.051705 | 0 | 0 | 100% |  |  |  | 0.051705 | 0
35042366 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 4 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35047429 | CWSP - WILLITS 1104 - LR 34008 PH 1 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | SH |  | 1.1328 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35056438 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 5 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35060229 | 2018 OH COND RPLC: FRUITLAND 42 C/O 7449 | SH |  | 1.2366 | 1.2366 | 1 | 1.2366 | 0 | 1.2366 | 0 | 100% | 0 | 1.2366 | 0 | 0 | 100% |  |  |  | 1.2366 | 0
35060582 | SLO 1107 RECOD 3884 FT WITH 2CU TW | SH | MGE | 0.73561 | 0.73561 | 1 | 0.73561 | 0 | 0.73561 | 0 | 100% | 0 | 0.73561 | 0 | 0 | 100% |  |  |  | 0.73561 | 0
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 | SH | Quanta | 0.69773 | 0.69773 | 1 | 0.69773 | 0 | 0.69773 | 0 | 100% | 0 | 0.69773 | 0 | 0 | 100% |  |  |  | 0.69773 | 0
35075103 | FROGTOWN 1701 - 3115FT RECOND HFTD TIER2 | SH |  | 0.59 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35023234 | STS-OFAC_IDLE_REMV-34039 HIGHWAY 44 | IF |  | 0.07197 | 0.07197 | 1 | 0.07197 | 0 | 0.07197 | 0 | 100% | 0 | 0.07197 | 0 | 0 | 100% |  |  |  | 0.07197 | 0
35026735 | X STS-COND_BROK_REPA - NEAR 19145 BIG | IF |  | 0.079545 | 0.079545 | 1 | 0.079545 | 0 | 0.079545 | 0 | 100% | 0 | 0.079545 | 0 | 0 | 100% |  |  |  | 0.079545 | 0
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  |  | 0.88826 | 0 | 0 | 0 | 0 | 0.83712 | 0.83712 | 0% | 0 | 0 | 0 | 0.83712 | 0% |  |  |  | 0 | 0
35030654 | TW ON WOODSIDE1101 N/O 7573 | SH | Alvah | 0.9983 | 0.9983 | 1 | 0.9983 | 0 | 0.9983 | 0 | 100% | 0 | 0.9983 | 0 | 0 | 100% |  |  |  | 0.9983 | 0
35037345 | STS-OFAC_IDLE_REMV-6645 E. HWY 246 | IF |  | 0.047348 | 0.047348 | 1 | 0.047348 | 0 | 0.047348 | 0 | 100% | 0 | 0.047348 | 0 | 0 | 100% |  |  |  | 0.047348 | 0
35037395 | POD T2 REMV IDLE -21335 PINE ST | IF |  | 0.0066288 | 0.0066288 | 1 | 0.0066288 | 0 | 0.0066288 | 0 | 100% | 0 | 0.0066288 | 0 | 0 | 100% |  |  |  | 0 | 0.0066288
35038067 | STS-COND_IDLE_REMV-202 OBERT DRIVE ( MAP | IF |  | 0.034848 | 0.034848 | 1 | 0.034848 | 0 | 0.034848 | 0 | 100% | 0 | 0.034848 | 0 | 0 | 100% |  |  |  | 0 | 0.034848
35038685 | REMV IDLE TAP-X ST FROM 2997 RD. 30 | IF |  | 0.11818 | 0.11818 | 1 | 0.11818 | 0 | 0.11818 | 0 | 100% | 0 | 0.11818 | 0 | 0 | 100% |  |  |  | 0.11818 | 0
35042368 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  |  | 2.0903 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35050942 | CWSP: GARBERVILLE 1101 HENDRIX PILOT |  |  | 1.7045 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | SH | GC | 2.1867 | 0 | 0 | 0 | 0 | 1.9125 | 1.9125 | 0% | 0 | 0 | 0 | 1.9125 | 0% |  |  |  | 0 | 0
35052821 | CWSP - MIWUK 1701 - OCB - PH 1.1 | SH | Quanta/Summit | 1.7203 | 0 | 0 | 0 | 0 | 2.1303 | 2.1303 | 0% | 0 | 0 | 0 | 2.1303 | 0% |  |  | 220 Mile Plan | 0 | 0
35056433 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | SH | GC | 2.1311 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | SH | Quanta/Par | 2.1108 | 2.1108 | 1 | 2.1108 | 0 | 2.1108 | 0 | 100% | 0 | 2.1108 | 0 | 0 | 100% | 8/24/2020 |  | 220 Mile Plan | 1.3587 | 0.75208
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | SH |  | 4.5506 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | SH | Quanta/Summit | 2.0104 | 0 | 0 | 0 | 0 | 2.0242 | 2.0242 | 0% | 0 | 0 | 0 | 2.0242 | 0% |  |  | 220 Mile Plan | 0 | 0
35058267 | IDLE FACILITY-R/O15140 GOLD DUST VOLCANO | IF |  | 0.11553 | 0.11553 | 1 | 0.11553 | 0 | 0.11553 | 0 | 100% | 0 | 0.11553 | 0 | 0 | 100% |  |  |  | 0.11553 | 0
35060990 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH3.01 |  |  | 0.86402 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35061811 | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35062376 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH3 | SH |  | 12.07 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR | SH | Source Power (ARB) | 0.3553 | 0.3553 | 1 | 0.3553 | 0 | 0.3553 | 0 | 100% | 0 | 0.3553 | 0 | 0 | 100% |  |  |  | 0.3553 | 0
35083685 | STS-POLE_IDLE_REMV-MERCED FALLS RD 1/P/S | IF |  | 0.19811 | 0.18996 | 0.95889 | 0.19394 | 0 | 0.19394 | 0 | 97.9% | -0.0039773 | 0.19394 | 0 | 0 | 97.9% |  |  |  | 0 | 0.18996
35083704 | STS-COND_IDLE_REMV-17715 HARVARD MINE RD | IF |  | 0.011932 | 0.011932 | 1 | 0.011932 | 0 | 0.011932 | 0 | 100% | 0 | 0.011932 | 0 | 0 | 100% |  |  |  | 0 | 0.011932
35083721 | STS-COND_IDLE_REMV-8/10MI N/O BEAR TRAP | IF |  | 0.015152 | 0.015152 | 1 | 0.015152 | 0 | 0.015152 | 0 | 100% | 0 | 0.015152 | 0 | 0 | 100% |  |  |  | 0 | 0.015152
35083885 | STS-COND_IDLE_REMV-6/P/E OF C/OUTS 38296 | IF |  | 0.045076 | 0.05 | 1.1092 | 0.046402 | 0 | 0.046402 | 0 | 102.9% | 0.0035985 | 0.046402 | 0 | 0 | 102.9% |  |  |  | 0 | 0.05
35087462 | STS-OFAC_IDLE_DEEN - 6 N/O 2 W/O R/O 930 | IF |  | 0.29129 | 0.29129 | 1 | 0.29129 | 0 | 0.29129 | 0 | 100% | 0 | 0.29129 | 0 | 0 | 100% |  |  |  | 0.29129 | 0
35094082 | STS-POLE_IDLE_REMV - 5549 GLEN DR#1PNPAR | IF |  | 0.1072 | 0.1072 | 1 | 0.1072 | 0 | 0.1072 | 0 | 100% | 0 | 0.1072 | 0 | 0 | 100% |  |  |  | 0.1072 | 0
35094514 | CWSP-ORO FINO 1101 LR-2022 PH 1.1 | SH |  | 1.2795 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | SH |  | 1.4458 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35095167 | CWSP - STANISLAUS 1702 - LR1888 - PH 2.1 | SH | Intren | 1.1172 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
30748101 | OCGC R7 EP ED WRO - HWY 29 - KELSEYVILLE | SH | GC | 3.3142 | 3.3142 | 1 | 3.3142 | 0 | 3.3142 | 0 | 100% | 0 | 3.3142 | 0 | 0 | 100% | 11/9/2020 |  | 220 Mile Plan | 0 | 3.3142
31159702 | TRAN_IDLE_REMV-CHIMNEY ROCK RD | IF |  | 0.07197 | 0.07197 | 1 | 0.07197 | 0 | 0.07197 | 0 | 100% | 0 | 0.07197 | 0 | 0 | 100% |  |  |  | 0.07197 | 0
31211614 | IDLE OH 4004 BONES RD SEBASTOPOL*OCLH | IF |  | 0.032197 | 0.029924 | 0.92941 | 0.032197 | 0 | 0.032197 | 0 | 100% | -0.0022727 | 0 | 0.032197 | 0 | 0% |  |  |  | 0 | 0.029924
31257161 | STS-POLE_IDLE_REMV-R/O 7652 WARREN RD | IF |  | 0.092803 | 0.092803 | 1 | 0.092803 | 0 | 0.092803 | 0 | 100% | 0 | 0.092803 | 0 | 0 | 100% |  |  |  | 0.092803 | 0
31326119 | WEIMAR 1101 - NATURE'S WAY RECONDUCTOR | SH | Wilson | 0.56629 | 0.56629 | 1 | 0.56629 | 0 | 0.56629 | 0 | 100% | 0 | 0.56629 | 0 | 0 | 100% |  |  |  | 0.56629 | 0
31434881 | 0P 3100 SKYWAY RD PARADISE TUSCAN RIDGE | SH |  | 3.3589 | 3.3589 | 1 | 3.3589 | 0 | 3.3589 | 0 | 100% | 0 | 3.3589 | 0 | 0 | 100% |  |  |  | 3.3589 | 0
35010356 | X*FT-OFAC_IDLE_REMV-OLD ADOBE RD 13 POLE | IF |  | 0.063826 | 0.063826 | 1 | 0.063826 | 0 | 0.063826 | 0 | 100% | 0 | 0.063826 | 0 | 0 | 100% |  |  |  | 0.063826 | 0
35012964 | 7/9-STS-COND_IDLE_REMV-CRN ELM DR | IF |  | 0.23371 | 0.23371 | 1 | 0.23371 | 0 | 0.23371 | 0 | 100% | 0 | 0.23371 | 0 | 0 | 100% |  |  |  | 0.23371 | 0
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  |  | 1.0038 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35018537 | STS-COND_IDLE_REMV - 17059 VAN ARSDALE R | IF |  | 0.73693 | 0.73996 | 1.0041 | 0.73693 | 0 | 0.73693 | 0 | 100% | 0.0030303 | 0.73693 | 0 | 0 | 100% |  |  |  | 0 | 0.73996
35023526 | 1/6/19-STS-POLE_IDLE_REMV-7050 BOGGS KEL | IF |  | 0.077652 | 0.077652 | 1 | 0.077652 | 0 | 0.077652 | 0 | 100% | 0 | 0.077652 | 0 | 0 | 100% |  |  |  | 0.077652 | 0
35031139 | SHADY GLEN 1102 RECONDUCTOR BEYOND 6343 | SH |  | 1.5182 | 1.5182 | 1 | 1.5182 | 0 | 1.5182 | 0 | 100% | -3.4451e-16 | 1.5182 | 0 | 0 | 100% |  |  |  | 1.5182 | 0
35037596 | TRAN_IDLE_REMV-OLD LIGHTHOUSE RD E.O | IF |  | 0.2197 | 0 | 0 | 0 | 0 | 0.2197 | 0.2197 | 0% | 0 | 0 | 0 | 0.2197 | 0% |  |  |  | 0 | 0
35039002 | OCGC 2018 CALISTOGA 1101 LEVEL 2 DEMO | SH |  | 1.1377 | 1.1377 | 1 | 1.14 | 0 | 1.14 | 0 | 100.2% | -0.0023106 | 1.14 | 0 | 0 | 100.2% |  |  |  | 1.1377 | 0
35042369 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 1 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35043303 | CWSP-OH COND RPLC: EEL RIVER 1102 FU1909 | SH |  | 1.5417 | 1.5417 | 1 | 1.5417 | 0 | 1.5417 | 0 | 100% | 0 | 1.5417 | 0 | 0 | 100% |  |  |  | 1.5417 | 0
35062127 | *FT-OFAC_IDLE_REMV - 5000 HWY 49COOL | IF |  | 1.1384 | 1.1384 | 1 | 1.1384 | 0 | 1.1384 | 0 | 100% | 0 | 1.1384 | 0 | 0 | 100% |  |  |  | 1.1384 | 0
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  |  | 2.0644 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35066689 | OCLH STS-OFAC_IDLE_REMV-16275 HWY 88 | IF |  | 0.019508 | 0.019508 | 1 | 0.019508 | 0 | 0.019508 | 0 | 100% | 0 | 0.019508 | 0 | 0 | 100% |  |  |  | 0.019508 | 0
35081748 | OH RECONDUCTOR - ROB ROY 2105 -S028CC119 | SH | MGE | 0.16098 | 0.16098 | 1 | 0.16098 | 0 | 0.16098 | 0 | 100% | 0 | 0.16098 | 0 | 0 | 100% |  |  | 220 Mile Plan | 0.16098 | 0
35083670 | STS-TRAN_IDLE_REMV-LOC 1-3/P/E & 1/P S/O | IF |  | 0.063258 | 0.010038 | 0.15868 | 0.0094697 | 0 | 0.0094697 | 0 | 14.97% | 0.00056818 | 0.0094697 | 0 | 0 | 14.97% |  |  |  | 0 | 0.010038
35083905 | STS-COND_IDLE_REMV-MARKER 1000 USONA RD | IF |  | 0.017992 | 0.017992 | 1 | 0 | 0 | 0.017992 | 0.017992 | 0% | 0.017992 | 0 | 0 | 0.017992 | 0% |  |  |  | 0 | 0.017992
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 | SH |  | 1.6521 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | SH |  | 1.9508 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | SH | Quanta/Summit | 1.4284 | 1.4284 | 1 | 1.4038 | 0 | 1.4038 | 0 | 98.28% | 0.024621 | 1.4038 | 0 | 0 | 98.28% | 8/13/2020 |  | 220 Mile Plan | 0 | 1.4284
35098578 | CWSP-COLUMBIA HILL 1101-LR 2212 PH2 | SH | Quanta | 1.7955 | 1.7955 | 1 | 1.7955 | 0 | 1.7955 | 0 | 100% | 0 | 1.7955 | 0 | 0 | 100% |  |  |  | 1.7955 | 0
35103325 | CWSP - MORAGA 1102 & 1104 - OCB | SH | Alvah | 1.3095 | 1.3095 | 1 | 1.3095 | 0 | 1.3095 | 0 | 100% | 1.7225e-16 | 1.3095 | 0 | 0 | 100% | 11/9/2020 |  | 220 Mile Plan | 0 | 1.3095
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | SH | Quanta/Par | 1.7972 | 1.7972 | 1 | 1.7972 | 0 | 1.7972 | 0 | 100% | 0 | 1.7972 | 0 | 0 | 100% | 11/9/2020 |  | 220 Mile Plan | 0.086364 | 1.7108
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | SH | GC | 2.6678 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35037647 | STS-POLE_IDLE_REMV-44141 LITTLE LAKE RD | IF |  | 0.099811 | 0.099811 | 1 | 0.099811 | 0 | 0.099811 | 0 | 100% | 0 | 0.099811 | 0 | 0 | 100% |  |  |  | 0.099811 | 0
35038058 | STS-COND_IDLE_REMV-LA PORTE RD 1 PL E/O | IF |  | 0.02178 | 0.020076 | 0.92174 | 0.02178 | 0 | 0.02178 | 0 | 100% | -0.0017045 | 0.02178 | 0 | 0 | 100% |  |  |  | 0 | 0.020076
35038190 | X-STS-TRAN_IDLE_REMV-A/O 30445 CHUALAR | IF |  | 0.097538 | 0.097538 | 1 | 0.097538 | 0 | 0.097538 | 0 | 100% | 0 | 0.097538 | 0 | 0 | 100% |  |  |  | 0.097538 | 0
35038608 | STS-COND_IDLE_REMV-8100 PLEASANTS VALLEY | IF |  | 0.21591 | 0.21591 | 1 | 0.21591 | 0 | 0.21591 | 0 | 100% | 0 | 0.21591 | 0 | 0 | 100% |  |  |  | 0.21591 | 0
35042670 | STS-POLE_DECA_REPL - 4300 SOFAR RD PLACE | IF |  | 0.088447 | 0.088447 | 1 | 0.088447 | 0 | 0.088447 | 0 | 100% | 0 | 0.088447 | 0 | 0 | 100% |  |  |  | 0.088447 | 0
35046371 | ECOP - STANISLAUS 1702 LR 37276 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  |  | 1.4015 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | SH | Quanta/Summit | 1.5341 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 | SH |  | 5.41 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | SH | GC | 1.3095 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | SH | Quanta | 1.7057 | 1.7057 | 1 | 1.7057 | 0 | 1.7057 | 0 | 100% | 0 | 1.7057 | 0 | 0 | 100% |  |  |  | 1.7057 | 0
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 | SH |  | 1.0502 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35066745 | BIG BEND 1102 - BLOOMER HILL 08W PHS 2 | SH |  | 1.6856 | 1.6856 | 1 | 1.6856 | 0 | 1.6856 | 0 | 100% | 0 | 1.6856 | 0 | 0 | 100% |  |  |  | 1.6856 | 0
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | SH |  | 1.4589 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35078734 | COND_IDLE_REMV-16333 TRINITY MOUNTAI | IF |  | 0.063826 | 0.063826 | 1 | 0.063826 | 0 | 0.063826 | 0 | 100% | 0 | 0.063826 | 0 | 0 | 100% |  |  |  | 0.063826 | 0
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | SH | GC | 1.3445 | 1.3445 | 1 | 1.3445 | 0 | 1.4511 | 0.10663 | 100% | 0 | 1.3445 | 0 | 0.10663 | 100% | 11/3/2020 |  | 220 Mile Plan | 0 | 1.3445
35062374 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1 | SH |  | 8.14 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35072720 | RPL OH WIRE ON GABILN 1101 17-0077248 | SH | GC | 2.2244 | 2.2244 | 1 | 2.2244 | 0 | 2.2244 | 0 | 100% | 0 | 2.2244 | 0 | 0 | 100% |  |  |  | 2.2244 | 0
35079972 | STS-COND_IDLE_REMV-12655 RATTLESNAKE GUL | IF |  | 0.017424 | 0.017424 | 1 | 0.017424 | 0 | 0.017424 | 0 | 100% | 0 | 0.017424 | 0 | 0 | 100% |  |  |  | 0 | 0.017424
35083741 | STS-COND_IDLE_REMV-2120 S. HWY 49 | IF |  | 0.029356 | 0.029356 | 1 | 0 | 0 | 0.029356 | 0.029356 | 0% | 0.029356 | 0 | 0 | 0.029356 | 0% |  |  |  | 0 | 0.029356
35083784 | STS-COND_IDLE_REMV-5811 E. WHITLOCK RD | IF |  | 0.047727 | 0.05 | 1.0476 | 0.045455 | 0 | 0.045455 | 0 | 95.24% | 0.0045455 | 0.045455 | 0 | 0 | 95.24% |  |  |  | 0 | 0.05
35083823 | OCLH STS-COND_IDLE_RMV-1 PLE S/OF D89103 | IF |  | 0.011364 | 0.011364 | 1 | 0.011364 | 0 | 0.011364 | 0 | 100% | 0 | 0.011364 | 0 | 0 | 100% |  |  |  | 0 | 0.011364
35085538 | SILVERADO 2105 WIRE DOWN - PH 1 | SH | Source Power (ARB) | 1.9722 | 1.9722 | 1 | 1.9722 | 0 | 1.9722 | 0 | 100% | 0 | 1.9722 | 0 | 0 | 100% | 11/4/2020 |  | 220 Mile Plan | 0.96326 | 1.0089
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | SH | GC | 1.4706 | 1.4706 | 1 | 1.4706 | 0 | 1.4706 | 0 | 100% | 0 | 1.4706 | 0 | 0 | 100% | 8/24/2020 |  | 220 Mile Plan | 0 | 1.4706
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | SH | GC | 1.8161 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | SH |  | 1.2117 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | SH | Quanta/UECCo | 2.4282 | 2.4282 | 1 | 2.4282 | 0 | 2.4282 | 0 | 100% | 3.1006e-15 | 2.4282 | 0 | 0 | 100% | 11/4/2020 |  | 220 Mile Plan | 0 | 2.4282
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | SH | Quanta/UECCo | 2.1165 | 2.1165 | 1 | 2.1165 | 0 | 2.1165 | 0 | 100% | 3.4451e-16 | 2.1165 | 0 | 0 | 100% | 11/4/2020 |  | 220 Mile Plan | 1.8341 | 0.28239
35083727 | STS-POLE_IDLE_REMV-INDIAN PEAK RD | IF |  | 0.027462 | 0.029924 | 1.0897 | 0.027462 | 0 | 0.027462 | 0 | 100% | 0.0024621 | 0.027462 | 0 | 0 | 100% |  |  |  | 0 | 0.029924
35085533 | CWSP - SILVERADO 2104 - LR722 PH 1D | SH | Source Power (ARB) | 1.0161 | 1.0161 | 1 | 1.0161 | 0 | 1.0161 | 0 | 100% | 0 | 1.0161 | 0 | 0 | 100% |  |  |  | 1.0161 | 0
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | SH | GC | 0.60606 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | SH |  | 0.68655 | 0 | 0 | 0 | 0 | 0.77973 | 0.77973 | 0% | 0 | 0 | 0 | 0.77973 | 0% |  |  |  | 0 | 0
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | SH |  | 0.71155 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | SH | Quanta/UECCo | 2.8519 | 2.8519 | 1 | 2.8519 | 0 | 2.8519 | 0 | 100% | 0 | 2.8519 | 0 | 0 | 100% | 8/24/2020 |  | 220 Mile Plan | 0 | 2.8519
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | SH | Quanta/UECCo | 1.915 | 1.915 | 1 | 1.915 | 0 | 1.915 | 0 | 100% | 0 | 1.915 | 0 | 0 | 100% | 11/9/2020 |  | 220 Mile Plan | 1.6239 | 0.2911
35111037 | +STS-COND_IDLE_REMV - 14655 HWY 41 1/P/N | IF |  | 0.030682 | 0.030682 | 1 | 0 | 0 | 0.030682 | 0.030682 | 0% | 0.030682 | 0 | 0 | 0.030682 | 0% |  |  |  | 0 | 0.030682
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | SH |  | 0.80455 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  |  | 1.4458 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | SH |  | 0.54451 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35113109 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.2 | SH | GC | 0.12898 | 0.12898 | 1 | 0.12898 | 0 | 0.12898 | 0 | 100% | 0 | 0.12898 | 0 | 0 | 100% |  |  |  | 0.12898 | 0
35083689 | STS-TRAN_IDLE_REMV-LOC #8 8655 HUNTERS V | IF |  | 0.067045 | 0.070076 | 1.0452 | 0.065909 | 0 | 0.065909 | 0 | 98.31% | 0.0041667 | 0.065909 | 0 | 0 | 98.31% |  |  |  | 0 | 0.070076
35085536 | CWSP - SILVERADO 2104 - LR722 PH 1G | SH |  | 1.3277 | 1.3277 | 1 | 1.3277 | 0 | 1.3277 | 0 | 100% | 0 | 1.3277 | 0 | 0 | 100% |  |  |  | 1.3277 | 0
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  |  | 0.84659 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35094321 | XSTS-POLE_IDLE-REMOV - 6PSE1PSW 6700 CRO | IF |  | 0.10322 | 0.10322 | 1 | 0.10322 | 0 | 0.10322 | 0 | 100% | 0 | 0.10322 | 0 | 0 | 100% |  |  |  | 0.10322 | 0
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | SH |  | 0.93958 | 0 | 0 | 0 | 0 | 0.82405 | 0.82405 | 0% | 0 | 0 | 0 | 0.82405 | 0% |  |  |  | 0 | 0
35095164 | CWSP-ORO FINO 1101 LR-2022 PH 3.1 | SH |  | 1.9373 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 | SH |  | 2.4813 | 2.4813 | 1 | 2.4813 | 0 | 2.4813 | 0 | 100% | 3.4451e-16 | 2.4813 | 0 | 0 | 100% |  |  |  | 2.4813 | 0
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 | SH | Quanta/Par | 1.8193 | 1.8193 | 1 | 1.8193 | 0 | 1.8193 | 0 | 100% | 0 | 1.8193 | 0 | 0 | 100% | 11/9/2020 |  | 220 Mile Plan | 0.73466 | 1.0847
35107689 | OCGC CWSP - PINE GROVE 1102 - LR1222 - | SH | GC | 2.0335 | 2.09 | 1.0278 | 2.0942 | 0 | 2.0942 | 0 | 103% | -0.0042045 | 2.0942 | 0 | 0 | 103% | 11/9/2020 |  | 220 Mile Plan | 0 | 2.09
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | SH | Quanta | 1.6898 | 1.6898 | 1 | 1.6898 | 0 | 1.6898 | 0 | 100% | 0 | 1.6898 | 0 | 0 | 100% |  |  |  | 1.6898 | 0
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | SH | Quanta/UECCo | 1.2578 | 1.2578 | 1 | 1.2578 | 0 | 1.2578 | 0 | 100% | 0 | 1.2578 | 0 | 0 | 100% | 8/24/2020 |  | 220 Mile Plan | 0 | 1.2578
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 | SH | Quanta/Par | 2.6447 | 2.6447 | 1 | 2.6447 | 0 | 2.6447 | 0 | 100% | 0 | 2.6447 | 0 | 0 | 100% | 8/13/2020 |  | 220 Mile Plan | 0 | 2.6447
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | SH | Quanta/Par | 1.1739 | 1.1739 | 1 | 1.1739 | 0 | 1.1739 | 0 | 100% | 0 | 1.1739 | 0 | 0 | 100% | 11/3/2020 |  | 220 Mile Plan | 0 | 1.1739
35112076 | OCGC FULTON 1107-OH TO UG MARK W SPG | SH | GC | 2.2019 | 2.2019 | 1 | 2.2019 | 0 | 2.2019 | 0 | 100% | -3.4451e-16 | 2.2019 | 0 | 0 | 100% | 11/9/2020 |  | 220 Mile Plan | 0.16856 | 2.0333
35095168 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.1 | SH |  | 1.2723 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | SH | Alvah | 1.1127 | 1.1127 | 1 | 1.1127 | 0 | 1.1127 | 0 | 100% | 1.7225e-16 | 1.1127 | 0 | 0 | 100% | 11/4/2020 |  | 220 Mile Plan | 0 | 1.1127
35103324 | CWSP - ROSSMOOR 1102 - OCB | SH | Alvah | 0.76629 | 0.76629 | 1 | 0.76629 | 0 | 0.76629 | 0 | 100% | 0 | 0.76629 | 0 | 0 | 100% | 11/4/2020 |  | 220 Mile Plan | 0.45587 | 0.31042
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | SH | Quanta/Par | 2.3269 | 2.3269 | 1 | 2.3309 | 0.15909 | 2.49 | 0 | 100.2% | -0.0039773 | 2.3309 | 0 | 0.15909 | 100.2% | 11/3/2020 |  | 220 Mile Plan | 0 | 2.3269
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | SH | Quanta/UECCo | 1.3381 | 1.3381 | 1 | 1.3381 | 0 | 1.3381 | 0 | 100% | 0 | 1.3381 | 0 | 0 | 100% | 8/24/2020 |  | 220 Mile Plan | 0 | 1.3381
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 | SH | Quanta/Par | 1.2557 | 1.2557 | 1 | 1.2557 | 0 | 1.2557 | 0 | 100% | 0 | 1.2557 | 0 | 0 | 100% | 11/4/2020 |  | 220 Mile Plan | 1.0956 | 0.16004
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 | SH | Quanta/Par | 1.4741 | 1.4741 | 1 | 1.4741 | 0 | 1.4741 | 0 | 100% | 0 | 1.4741 | 0 | 0 | 100% | 11/4/2020 |  | 220 Mile Plan | 0.7858 | 0.68826
35112433 | CWSP - EL DORADO 2102 - LR19562 - PH 1.3 | SH | Quanta/Summit | 2 | 2 | 1 | 1.9968 | 0 | 1.9968 | 0 | 99.84% | 0.0032197 | 1.9968 | 0 | 0 | 99.84% | 8/24/2020 |  | 220 Mile Plan | 0 | 2
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | SH | ARB | 2.0511 | 2.0511 | 1 | 2.0496 | 0 | 2.1045 | 0.054924 | 99.93% | 0.0015152 | 2.0496 | 0 | 0.054924 | 99.93% | 11/3/2020 |  | 220 Mile Plan | 0 | 2.0511
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | SH |  | 2.4241 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | SH |  | 1.4447 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | SH |  | 0.81269 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | SH |  | 1.3259 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | SH | GC | 1.0496 | 1.0496 | 1 | 1.0496 | 0 | 1.1271 | 0.077462 | 100% | 0 | 1.0496 | 0 | 0.077462 | 100% | 8/24/2020 |  | 220 Mile Plan | 0 | 1.0496
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | SH |  | 1.4398 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | SH |  | 2.25 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35115147 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.2 | SH | GC | 1.2269 | 1.2269 | 1 | 1.2269 | 0 | 1.2269 | 0 | 100% | 0 | 1.2269 | 0 | 0 | 100% | 8/12/2020 |  | 220 Mile Plan | 0 | 1.2269
35115149 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.4 | SH | GC | 1.2674 | 1.2674 | 1 | 1.2674 | 0 | 1.2674 | 0 | 100% | 0 | 1.2674 | 0 | 0 | 100% | 11/4/2020 |  | 220 Mile Plan | 0 | 1.2674
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | SH | Michels Pacific Energy | 1.7398 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | SH |  | 1.2034 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | SH | Wilson | 1.3862 | 0 | 0 | 0 | 0 | 1.3919 | 1.3919 | 0% | 0 | 0 | 0 | 1.3919 | 0% |  |  | 220 Mile Plan | 0 | 0
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | SH | Quanta/Summit | 1.5161 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116517 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.5 | SH |  | 2.4009 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116519 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.4 | SH |  | 1.7553 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | SH | GC | 2.41 | 2.41 | 1 | 2.2167 | 0 | 2.2237 | 0.0070076 | 91.98% | 0.19337 | 2.2167 | 0 | 0.0070076 | 91.98% | 11/4/2020 |  | 220 Mile Plan | 0 | 2.41
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | SH |  | 1.832 | 1.832 | 1 | 1.832 | 0 | 1.832 | 0 | 100% | 0 | 1.832 | 0 | 0 | 100% |  |  |  | 1.832 | 0
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | SH | Quanta/UECCo | 0.30644 | 0.30644 | 1 | 0.30644 | 0 | 0.30644 | 0 | 100% | 0 | 0.30644 | 0 | 0 | 100% | 8/24/2020 |  | 220 Mile Plan | 0 | 0.30644
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 | SH | Quanta/Par | 2.2331 | 2.2331 | 1 | 2.2331 | 0 | 2.2331 | 0 | 100% | -3.4451e-16 | 2.2331 | 0 | 0 | 100% | 8/24/2020 |  | 220 Mile Plan | 0 | 2.2331
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | SH | Quanta | 1.3551 | 1.3551 | 1 | 1.3551 | 0 | 1.3551 | 0 | 100% | 1.7225e-16 | 1.3551 | 0 | 0 | 100% | 11/9/2020 |  | 220 Mile Plan | 1.3244 | 0.030682
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | SH | Quanta/Summit | 1.5375 | 1.5373 | 0.99988 | 1.5373 | 0 | 1.5373 | 0 | 99.99% | 0 | 1.5373 | 0 | 0 | 99.99% | 10/5/2020 |  | 220 Mile Plan | 0 | 1.5373
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | SH | Quanta/Summit | 2.51 | 2.51 | 1 | 2.5053 | 0 | 2.5053 | 0 | 99.81% | 0.0047348 | 2.5053 | 0 | 0 | 99.81% | 11/18/2020 |  | 220 Mile Plan | 0 | 2.51
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | SH |  | 1.9381 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | SH |  | 1.5553 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | SH | GC | 1.2566 | 0 | 0 | 0 | 0 | 1.3197 | 1.3197 | 0% | 0 | 0 | 0 | 1.3197 | 0% |  |  | 220 Mile Plan | 0 | 0
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | SH | GC | 1.472 | 1.472 | 1 | 1.4725 | 0 | 1.4725 | 0 | 100% | -0.00053788 | 1.4725 | 0 | 0 | 100% | 11/3/2020 |  | 220 Mile Plan | 0 | 1.472
35115054 | CWSP - MIWUK 1701 - OCB - PH 2.2 | SH | Quanta/Summit | 1.4248 | 0 | 0 | 0 | 0 | 1.4612 | 1.4612 | 0% | 0 | 0 | 0 | 1.4612 | 0% |  |  | 220 Mile Plan | 0 | 0
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | SH | Quanta/Summit | 2.5858 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35112426 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.3 | SH | Quanta | 1.7191 | 1.7191 | 1 | 1.7191 | 0 | 1.7191 | 0 | 100% | 2.067e-15 | 1.7191 | 0 | 0 | 100% | 11/9/2020 |  | 220 Mile Plan | 1.7117 | 0.0073864
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | SH | Quanta/Summit | 2.7557 | 2.7557 | 1 | 2.6938 | 0 | 2.6938 | 0 | 97.75% | 0.061932 | 2.6655 | 0.02822 | 0 | 96.73% | 8/17/2020 |  | 220 Mile Plan | 0 | 2.7557
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | SH | GC | 0.71629 | 0.71629 | 1 | 0.71629 | 0 | 0.71629 | 0 | 100% | 0 | 0.71629 | 0 | 0 | 100% | 11/9/2020 |  | 220 Mile Plan | 0 | 0.71629
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  |  | 1.1187 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | SH |  | 1.3028 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | SH | GC | 1.3909 | 0 | 0 | 0 | 0 | 0.94792 | 0.94792 | 0% | 0 | 0 | 0 | 0.94792 | 0% |  |  | 220 Mile Plan | 0 | 0
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | SH | Quanta/Summit | 1.6195 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | SH | GC | 1.6023 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | SH |  | 1.6011 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | SH | Quanta/Summit | 2.4828 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | SH | GC | 1.7106 | 0 | 0 | 0 | 0 | 1.593 | 1.593 | 0% | 0 | 0 | 0 | 1.593 | 0% |  |  | 220 Mile Plan | 0 | 0
35116513 | CWSP - STANISLAUS 1702 - LR1888 - PH 2.4 | SH |  | 2.1305 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | SH |  | 1.8769 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 | SH | Quanta/Par | 2.0756 | 2.0756 | 1 | 2.0756 | 0 | 2.0756 | 0 | 100% | 0 | 2.0756 | 0 | 0 | 100% | 11/4/2020 |  | 220 Mile Plan | 0 | 2.0756
35112428 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.5 | SH | Quanta/Summit | 1.6233 | 1.6233 | 1 | 1.6233 | 0 | 1.6233 | 0 | 100% | 0 | 1.6233 | 0 | 0 | 100% | 8/24/2020 |  | 220 Mile Plan | 0 | 1.6233
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | SH | Quanta/Summit | 1.3269 | 1.3269 | 1 | 1.1178 | 0 | 1.3269 | 0.20909 | 84.24% | 0.20909 | 1.1178 | 0 | 0.20909 | 84.24% | 11/9/2020 |  | 220 Mile Plan | 0 | 1.3269
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | SH |  | 1.6055 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35113103 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.3 | SH | GC | 0.21818 | 0.21818 | 1 | 0.21818 | 0 | 0.21818 | 0 | 100% | 0 | 0.21818 | 0 | 0 | 100% |  |  |  | 0.21818 | 0
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | SH |  | 3.5697 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | SH |  | 1.3972 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | SH | GC | 1.0392 | 0 | 0 | 0 | 0 | 0.95076 | 0.95076 | 0% | 0 | 0 | 0 | 0.95076 | 0% |  |  | 220 Mile Plan | 0 | 0
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | SH | Quanta/Summit | 1.6121 | 0 | 0 | 0 | 0 | 1.6241 | 1.6241 | 0% | 0 | 0 | 0 | 1.6241 | 0% |  |  | 220 Mile Plan | 0 | 0
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | SH | GC | 1.182 | 1.182 | 1 | 1.182 | 0 | 1.2155 | 0.033523 | 100% | 1.7225e-16 | 1.182 | 0 | 0.033523 | 100% | 11/9/2020 |  | 220 Mile Plan | 0 | 1.182
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | SH | Intren | 1.1205 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | SH | Wilson | 0.9 | 0.9 | 1 | 0.9036 | 0 | 0.95606 | 0.052462 | 100.4% | -0.0035985 | 0.9036 | 0 | 0.052462 | 100.4% | 11/9/2020 |  | 220 Mile Plan | 0 | 0.9
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | SH | Quanta/Summit | 2.0102 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35046211 | CWSP - GARBERVILLE 1102 HENDRIX PILOT |  |  | 0.75758 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35051268 | CWSP - WILLITS 1104 - LR 34008 - PH 2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35051827 | STS-POLE_DECA_REMV - 44243 ROAD 619AHWAH | IF |  | 0.12008 | 0.12008 | 1 | 0.12008 | 0 | 0.12008 | 0 | 100% | 0 | 0.12008 | 0 | 0 | 100% |  |  |  | 0.12008 | 0
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | SH |  | 1.4733 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  | 220 Mile Plan | 0 | 0
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | SH | GC | 5.9004 | 5.9004 | 1 | 5.9042 | 0 | 5.9042 | 0 | 100.1% | -0.0037879 | 5.9042 | 0 | 0 | 100.1% | 11/9/2020 |  | 220 Mile Plan | 0 | 5.9004
35056439 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | SH |  | 2.0121 | 0 | 0 | 0 | 0 | 2.4557 | 2.4557 | 0% | 0 | 0 | 0 | 2.4557 | 0% |  |  |  | 0 | 0
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | SH |  | 1.0809 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | SH | Michels Pacific Energy | 1.0494 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35079380 | STS-POLE_IDLE_REMV-17425 BAKER RILEY | IF |  | 0.14072 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35083747 | STS-COND_IDLE_REMV-23736 SKY HARBOUR RD | IF |  | 0.0094697 | 0.0094697 | 1 | 0.0094697 | 0 | 0.0094697 | 0 | 100% | 0 | 0.0094697 | 0 | 0 | 100% |  |  |  | 0 | 0.0094697
35085362 | ASAP REMV IDLE R/O 17020 ARMSTRON*AE | IF |  | 0.05 | 0.05 | 1 | 0 | 0 |  | 0 | 0% | 0.05 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0.05
35094388 | CWSP-KONOCTI 1102-LR 532 PH 1 | SH |  | 0.42443 | 0.42443 | 1 | 0.42443 | 0 | 0.42443 | 0 | 100% | 0 | 0.42443 | 0 | 0 | 100% |  |  |  | 0.42443 | 0
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | SH |  | 1.9174 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35098264 | FT-POLE_IDLE_REMV - NE/O ENTR. 5756 RAI | IF |  | 0.10322 | 0.10322 | 1 | 0.10322 | 0 | 0.10322 | 0 | 100% | 0 | 0.10322 | 0 | 0 | 100% |  |  |  | 0.10322 | 0
35103110 | STS-COND_IDLE_REMV-2920 HOLLOWAY DR | IF |  | 0.019886 | 0.019886 | 1 | 0.019886 | 0 | 0.019886 | 0 | 100% | 0 | 0.019886 | 0 | 0 | 100% |  |  |  | 0 | 0.019886
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | SH | GC | 0.74034 | 0.16004 | 0.21617 | 0.1589 | 0 | 0.78542 | 0.62652 | 21.46% | 0.0011364 | 0.1589 | 0 | 0.62652 | 21.46% | 11/9/2020 |  | 220 Mile Plan | 0 | 0.16004
35115055 | CWSP - MIWUK 1701 - OCB - PH 2.3 | SH | GC | 2.1343 | 0 | 0 | 0 | 0 | 2.3053 | 2.3053 | 0% | 0 | 0 | 0 | 2.3053 | 0% |  |  | 220 Mile Plan | 0 | 0
35115056 | CWSP - MIWUK 1701 - OCB - PH 2.4 | SH | Quanta/Summit | 1.7492 | 0 | 0 | 0 | 0 | 1.8169 | 1.8169 | 0% | 0 | 0 | 0 | 1.8169 | 0% |  |  |  | 0 | 0
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | SH | GC | 1.78 | 1.78 | 1 | 1.7833 | 0 | 1.7833 | 0 | 100.2% | -0.0033333 | 1.7833 | 0 | 0 | 100.2% | 8/24/2020 |  | 220 Mile Plan | 0 | 1.78
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | SH | GC | 1.9006 | 1.9006 | 1 | 1.9006 | 0 | 1.9006 | 0 | 100% | 0 | 1.9006 | 0 | 0 | 100% | 8/24/2020 |  | 220 Mile Plan | 0 | 1.9006
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | SH |  | 2.0725 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | SH | Alvah | 2.0705 | 1.3841 | 0.6685 | 1.3841 | 0 | 2.0902 | 0.70606 | 66.85% | 0 | 1.3841 | 0 | 0.70606 | 66.85% | 11/9/2020 |  | 220 Mile Plan | 0 | 1.3841
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | SH |  | 2.2756 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | SH | Alvah | 2.0956 | 1.79 | 0.85413 | 1.7888 | 0 | 2.3491 | 0.56023 | 85.36% | 0.0011364 | 1.7888 | 0 | 0.56023 | 85.36% | 11/3/2020 |  | 220 Mile Plan | 0 | 1.79
35119600 | STS-OFAC_IDLE_REMV- 1NE/O 24099 DERSCH | IF |  | 0.39905 | 0 | 0 | 0 | 0 | 0.39905 | 0.39905 | 0% | 0 | 0 | 0 | 0.39905 | 0% |  |  |  | 0 | 0
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | SH |  | 0.41 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | SH |  | 1.9148 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | SH |  | 1.3831 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | SH |  | 1.2059 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | SH |  | 1.2583 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | SH | GC | 1.6462 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  | 220 Mile Plan | 0 | 0
35115157 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.4 | SH | GC | 1.98 | 1.98 | 1 | 1.7909 | 0 | 1.7909 | 0 | 90.45% | 0.18909 | 1.7909 | 0 | 0 | 90.45% | 11/3/2020 |  | 220 Mile Plan | 0 | 1.98
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | SH |  | 1.2206 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | SH | Intren | 1.3036 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116393 | CWSP - MIWUK 1702 - OCB - PH 1.3 | SH | GC | 2.5705 | 2.5705 | 1 | 2.5705 | 0 | 2.5705 | 0 | 100% | 0 | 2.5705 | 0 | 0 | 100% | 8/24/2020 |  | 220 Mile Plan | 0 | 2.5705
35116394 | CWSP - MIWUK 1702 - OCB - PH 1.4 | SH | GC | 1.6777 | 1.6777 | 1 | 1.6777 | 0 | 1.6777 | 0 | 100% | 4.8231e-15 | 1.6777 | 0 | 0 | 100% | 11/9/2020 |  | 220 Mile Plan | 0 | 1.6777
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | SH | Alvah | 1.9411 | 0 | 0 | 0 | 0 | 1.9134 | 1.9134 | 0% | 0 | 0 | 0 | 1.9134 | 0% |  |  |  | 0 | 0
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | SH | GC | 2.1023 | 0 | 0 | 0 | 0 | 2.065 | 2.065 | 0% | 0 | 0 | 0 | 2.065 | 0% |  |  | 220 Mile Plan | 0 | 0
35116511 | CWSP - STANISLAUS 1702 - LR1888 - PH 2.2 | SH |  | 1.2023 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 | SH |  | 1.4604 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35117444 | CWSP - VOLTA 1102 LR 1648 PH 2.1 | SH | Quanta/Par | 2.397 | 2.397 | 1 | 2.397 | 0 | 2.397 | 0 | 100% | 3.1006e-15 | 2.397 | 0 | 0 | 100% | 8/24/2020 |  | 220 Mile Plan | 0 | 2.397
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | SH | GC | 1.0799 | 1.08 | 1.0001 | 1.0763 | 0 | 1.0763 | 0 | 99.67% | 0.0036742 | 1.0763 | 0 | 0 | 99.67% | 11/9/2020 |  | 220 Mile Plan | 0 | 1.08
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | SH | GC | 1.2835 | 1.2799 | 0.9972 | 1.2835 | 0 | 1.2835 | 0 | 100% | -0.0035985 | 1.2835 | 0 | 0 | 100% | 8/21/2020 |  | 220 Mile Plan | 0 | 1.2799
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 | SH | GC | 1.7856 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | SH |  | 1.9278 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | SH |  | 1.733 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | SH |  | 1.0837 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | SH |  | 1.4549 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | SH |  | 1.6572 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 |  |  | 1.2648 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  |  | 1.7563 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35144944 | PSPS - SNEATH LANE 1107 - LR 48338 | SH | Bess Test Labs | 0.2553 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155691 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.13 |  |  | 0.57008 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155693 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.15 |  |  | 1.1553 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155742 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.09 |  |  | 1.1553 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155757 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.07 |  |  | 0.5517 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155759 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.09 |  |  | 0.66288 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155842 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.12 |  |  | 0.15303 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35174475 | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 |  |  | 2.96 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35174477 | ECOP-CALISTOGA 1101-H01-LR736-PH3 |  |  | 9.53 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | SH | Quanta/Par | 1.6337 | 1.6337 | 1 | 1.6337 | 0 | 1.6337 | 0 | 100% | 0 | 1.6337 | 0 | 0 | 100% | 8/24/2020 |  | 220 Mile Plan | 0 | 1.6337
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | SH | Quanta/UECCo | 2.6667 | 2.6667 | 1 | 2.6667 | 0 | 2.6667 | 0 | 100% | 0 | 2.6667 | 0 | 0 | 100% | 8/24/2020 |  | 220 Mile Plan | 1.4146 | 1.2521
35109753 | STS-COND_IDLE_REMV - R/O 32660 SECORT AL | IF |  | 0.013826 | 0.013826 | 1 | 0.013826 | 0 | 0.013826 | 0 | 100% | 0 | 0.013826 | 0 | 0 | 100% |  |  |  | 0 | 0.013826
35109755 | STS-COND_IDLE_REMV - 5280 FARVIEW CT W/T | IF |  | 0.0085227 | 0.0085227 | 1 | 0.0085227 | 0 | 0.0085227 | 0 | 100% | 0 | 0.0085227 | 0 | 0 | 100% |  |  |  | 0 | 0.0085227
35111500 | CWSP-RECON UPPER LAKE 01 HUNTERS PT RD | SH | WIlson | 0.35038 | 0.35038 | 1 | 0.35038 | 0 | 0.35038 | 0 | 100% | 0 | 0.35038 | 0 | 0 | 100% |  |  |  | 0.35038 | 0
35112427 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.4 | SH | Quanta/Summit | 0.96004 | 0.96004 | 1 | 0.96004 | 0 | 0.96004 | 0 | 100% | 0 | 0.96004 | 0 | 0 | 100% | 8/24/2020 |  | 220 Mile Plan | 0.071402 | 0.88864
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | SH | Wilson | 1.3903 | 1.3903 | 1 | 1.3903 | 0 | 1.3903 | 0 | 100% | 0 | 1.3903 | 0 | 0 | 100% | 7/13/2020 |  | 220 Mile Plan | 0 | 1.3903
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | SH | Quanta/Summit | 1.5299 | 1.5299 | 1 | 1.5008 | 0 | 1.5008 | 0 | 98.09% | 0.029167 | 1.5008 | 0 | 0 | 98.09% | 10/5/2020 |  | 220 Mile Plan | 0 | 1.5299
35112436 | CWSP - EL DORADO 2102 - LR19562 - PH 1.6 | SH | Quanta/Summit | 1.8 | 1.8 | 1 | 1.8047 | 0 | 1.8047 | 0 | 100.3% | -0.0047348 | 1.8047 | 0 | 0 | 100.3% | 8/24/2020 |  | 220 Mile Plan | 0 | 1.8
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | SH |  | 1.2595 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35113104 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.2 | SH | GC | 0.25081 | 0.25081 | 1 | 0.25081 | 0 | 0.25081 | 0 | 100% | 0 | 0.25081 | 0 | 0 | 100% |  |  |  | 0.25081 | 0
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | SH |  | 0.86894 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  |  | 1.2235 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  |  | 1.6932 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | SH | GC | 1.4847 | 0 | 0 | 0 | 0 | 1.4017 | 1.4017 | 0% | 0 | 0 | 0 | 1.4017 | 0% |  |  | 220 Mile Plan | 0 | 0
35114140 | STS-POLE_IDLE_REMV - #1E 15986 HWY 26GLE | IF |  | 0.023485 | 0.023485 | 1 | 0.023485 | 0 | 0.023485 | 0 | 100% | -2.6914e-18 | 0.023485 | 0 | 0 | 100% |  |  |  | 0 | 0.023485
35116512 | CWSP - STANISLAUS 1702 - LR1888 - PH 2.3 | SH |  | 1.7492 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116514 | CWSP - STANISLAUS 1702 - LR1888 - PH 2.5 | SH |  | 2.0553 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 | SH |  | 1.5913 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35117550 | STS-OFAC_IDLE_REMV-21495 DRY CREEK RD*KS | IF |  | 0.15019 | 0.15019 | 1 | 0.15019 | 0 | 0.15019 | 0 | 100% | 0 | 0.15019 | 0 | 0 | 100% |  |  |  | 0 | 0.15019
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | SH | GC | 1.9223 | 1.9223 | 1 | 1.9223 | 0 | 1.9223 | 0 | 100% | 0 | 1.9223 | 0 | 0 | 100% |  |  |  | 1.9223 | 0
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | SH | GC | 1.7661 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | SH |  | 1.8545 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | SH |  | 1.5098 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | SH | GC | 1.3017 | 1.3017 | 1 | 1.3017 | 0 | 1.3017 | 0 | 100% | 0 | 1.3017 | 0 | 0 | 100% | 8/5/2020 |  | 220 Mile Plan | 0 | 1.3017
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | SH |  | 1.686 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35149197 | STS-POLE_IDLE_REMV-HWY 169 MP 29.32 | IF |  | 0.064205 | 0.064205 | 1 | 0.037879 | 0 | 0.037879 | 0 | 59% | 0.026326 | 0.037879 | 0 | 0 | 59% |  |  |  | 0 | 0.064205
35145003 | PSPS CWSP - MORAGA 1103 - CB | SH |  | 0.3197 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | SH |  | 0.95417 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | SH |  | 3.9451 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35145540 | PSPS - FROGTOWN 1702 - CB | SH |  | 1.0947 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155682 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.04 |  |  | 0.36553 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155685 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.07 |  |  | 0.71591 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155699 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.06 |  |  | 0.45739 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155749 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.15 |  |  | 0.50417 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155750 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.16 |  |  | 1.6803 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 | SH |  | 1.1955 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 | SH |  | 2.0691 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35168821 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.5 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35174469 | ECOP-PINE GROVE 1102-H01-LR45292 | SH |  | 10.88 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35174470 | ECOP-MOLINO 1102-H01-LR318 | SH |  | 2.6 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3 | SH |  | 9.7201 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35175855 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.5 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35175856 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35177109 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.6 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35177110 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.7 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35192282 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH2 | SH |  | 7.5199 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | SH |  | 4.04 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219275 | CWSP - PUTAH CREEK 110246012 | SH |  | 0.52 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219276 | CWSP - VACAVILLE 11046542 | SH |  | 14.66 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | SH |  | 0.20833 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35222234 | OAKHURST 1101 - #581 MIAMI MOUNTAIN | SH |  | 2.62 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE | SH |  | 1 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | SH | ARB/EEI Build Design | 4.767 | 4.767 | 1 | 4.767 | 0 | 8.0506 | 3.2835 | 100% | -6.8901e-16 | 4.767 | 0 | 3.2835 | 100% |  |  |  | 4.767 | 0
31159701 | +TRAN_IDLE_REMV-KLAU MINE RD | IF |  | 0.13447 | 0.13447 | 1 | 0.13447 | 0 | 0.13447 | 0 | 100% | 0 | 0.13447 | 0 | 0 | 100% |  |  |  | 0.13447 | 0
31401029 | NO-NV-SHASTA CO-07/23/18 CARR FIRE |  |  | 3.104 | 3.104 | 1 | 3.104 | 0 | 3.104 | 0 | 100% | -4.8149e-08 | 3.104 | 0 | 0 | 100% |  |  | T1 A Tag | 3.104 | 0
35016855 | 10/31-ST-POLE_IDLE_REMV-43451 EUREKA HIL | IF |  | 0.04053 | 0.04053 | 1 | 0.04053 | 0 | 0.04053 | 0 | 100% | 0 | 0.04053 | 0 | 0 | 100% |  |  |  | 0.04053 | 0
35030877 | 12/31 REMV IDLE 5 PLS 25050 HWY 1 C*OCLH | IF |  | 0.15076 | 0.15076 | 1 | 0.15076 | 0 | 0.15076 | 0 | 100% | 0 | 0.15076 | 0 | 0 | 100% |  |  |  | 0.15076 | 0
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | SH | GC | 1.6297 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  | 2021 Rsrv | 0 | 0
35085393 | CWSP - SILVERADO 2104 - LR722 PH 1B | SH | Quanta/UECCo | 0.35436 | 0.35436 | 1 | 0.35436 | 0 | 0.35436 | 0 | 100% | 0 | 0.35436 | 0 | 0 | 100% |  |  |  | 0.35436 | 0
35098579 | CWSP-COLUMBIA HILL 1101-LR 2212 PH3 | SH |  | 1.4343 | 1.4343 | 1 | 1.4343 | 0 | 1.4343 | 0 | 100% | 0 | 1.4343 | 0 | 0 | 100% |  |  |  | 1.4343 | 0
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | SH | GC | 1.472 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 | SH |  | 0.9892 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | SH |  | 1.9487 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | SH |  | 1.1847 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | SH |  | 1.628 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | SH |  | 2.5947 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35130803 | STS-POLE_IDLE_REMV-BEHIND EEL R. SAWMILL | IF |  | 0.37273 | 0.4 | 1.0732 | 0.39905 | 0 | 0.39905 | 0 | 107.1% | 0.00094697 | 0.39905 | 0 | 0 | 107.1% |  |  |  | 0 | 0.4
35135297 | STS-REM IDLE 12KV-110 PARKHILL,S.MARGAR | IF |  | 0.098864 | 0 | 0 | 0 | 0 | 0.098864 | 0.098864 | 0% | 0 | 0 | 0 | 0.098864 | 0% |  |  |  | 0 | 0
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | SH |  | 0.49242 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35144943 | PSPS - ROB ROY 2105 - CB | SH |  | 0.62992 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | SH | GC | 1.6809 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
31334292 | RECON 9-SPANS, AUSTIN CREEK RD | SH |  | 0.47595 | 0.47216 | 0.99204 | 0.47216 | 0 | 0.47216 | 0 | 99.2% | 0 | 0.47216 | 0 | 0 | 99.2% |  |  |  | 0.47216 | 0
35009046 | CCM POLE_IDLE+_REMV-2E/O 8S/O 4890 CHILE | IF |  | 0.16875 | 0.16875 | 1 | 0.16875 | 0 | 0.16875 | 0 | 100% | 0 | 0.16875 | 0 | 0 | 100% |  |  |  | 0.16875 | 0
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 | SH |  | 1.5689 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 | SH |  | 2.6879 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | SH |  | 7.35 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35193585 | SR-CC-MONTEREY-08-16-20 RIVER/CARMEL/DOL |  |  | 2.92 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219289 | CWSP - OREGON TRAIL 110335002 PH1 | SH |  | 57.14 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | SH |  | 1.0655 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | SH |  | 1.6244 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | SH |  | 1.3294 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | SH |  | 2.0585 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | SH |  | 1.1578 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 |  |  | 1.3809 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155681 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.03 |  |  | 0.25284 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155686 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.08 |  |  | 0.61364 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155688 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.10 |  |  | 0.5608 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155747 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.13 |  |  | 0.76231 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155754 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.04 |  |  | 1.2549 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155756 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.06 |  |  | 1.7451 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35157258 | STS-COND_IDLE_REMV - 2712-2734 E WESTFAL | IF |  | 0.018939 | 0.018939 | 1 | 0 | 0 | 0.018939 | 0.018939 | 0% | 0.018939 | 0 | 0 | 0.018939 | 0% |  |  |  | 0 | 0.018939
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | SH |  | 0.67008 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | SH |  | 1.2299 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 | SH |  | 1.0417 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35168822 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.6 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | SH |  | 9 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35199234 | NO-NV-BUTTE 9/8/20- NORTH COMPLEX FIRE |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  | T1 A Tag | 0 | 0
35206136 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.4 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35219272 | CWSP - MIDDLETOWN 1101481876 | SH |  | 0.92 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219590 | CWSP - VACA DIXON 1105965390 | SH |  | 0.75 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155689 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.11 |  |  | 0.92803 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155696 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.03 |  |  | 0.46212 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155746 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.12 |  |  | 1.1193 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155753 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.03 |  |  | 1.0627 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35171354 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | SH | GC | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 220 Mile Plan | 0 | 0
35173755 | ECOP-WEST POINT 1101-H02-LR36674 | SH |  | 2.28 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 | SH |  | 1.8201 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35175852 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35175859 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.5 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35176209 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.3 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35193618 | NR-SO-SONOMA 8/17/20-LNU COMPLEX FIRES |  |  | 16.6 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  | T2/T3 A Tag | 0 | 0
35204446 | NR-NB-NAPA- 9/27/20- GLASS FIRE SYS HARD |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35042719 | CWSP-AMGWIN STEEL POLE & TW DEMO PH | SH |  | 0.24148 | 0.24148 | 1 | 0.24148 | 0 | 0.24148 | 0 | 100% | 0 | 0.24148 | 0 | 0 | 100% |  |  |  | 0.24148 | 0
35043296 | WDDB - WILLOW CRK 1103 LR 3090 | SH | Wilson | 1.2686 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | SH |  | 2.2094 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | SH |  | 1.1146 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35047601 | ECOP-BRUNSWICK 1105-H01-LR32536 ZONE PH2 | SH |  | 8.78 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35048678 | ECOP-BRUNSWICK 1105-H01-LR32536 ZONE PH3 | SH |  | 7 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35049537 | CWSP - BIG BASIN 1102 - 9741 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35052822 | CWSP - MIWUK 1701 - LR 8050 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35052824 | CWSP - MIWUK 1702 - LR6018 - PH 2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35055289 | STS-POLE_DECA_REPL - 6999 ARROYO RDLIVER | IF |  | 0.05947 | 0.05947 | 1 | 0.05947 | 0 | 0.05947 | 0 | 100% | 0 | 0.05947 | 0 | 0 | 100% |  |  |  | 0.05947 | 0
35056298 | STS-COND_IDLE_REMV-45828 AUBERRY RD | IF |  | 0.061742 | 0.061742 | 1 | 0.061742 | 0 | 0.061742 | 0 | 100% | 0 | 0.061742 | 0 | 0 | 100% |  |  |  | 0 | 0.061742
35056434 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | SH | GC | 1.7888 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  | 220 Mile Plan | 0 | 0
35062375 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2 | SH |  | 9.39 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35078217 | STS-COND_IDLE_REMV-2290 BANDERILLA DR | IF |  | 0.22936 | 0.26004 | 1.1338 | 0.26061 | 0 | 0.26061 | 0 | 113.6% | -0.00056818 | 0.26061 | 0 | 0 | 113.6% |  |  |  | 0 | 0.26004
35078728 | COND_IDLE_REMV-17351 TRINITY MOUNTAI | IF |  | 0.036553 | 0.036553 | 1 | 0.036553 | 0 | 0.036553 | 0 | 100% | 0 | 0.036553 | 0 | 0 | 100% |  |  |  | 0.036553 | 0
30977615 | WDDB OTTER 1102 PHASE 5 | SH | MGE | 0.50455 | 0 | 0 | 0 | 0 | 0.50455 | 0.50455 | 0% | 0 | 0 | 0 | 0.50455 | 0% |  |  |  | 0 | 0
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | SH |  | 1.8902 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116515 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.2 | SH |  | 1.7466 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | SH |  | 1.1593 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35119966 | CWSP - LOS GATOS 1106 - LB44 - PH 2.6F | SH | GC | 0.81913 | 0.81913 | 1 | 0.81913 | 0 | 0.81913 | 0 | 100% | 0 | 0.81913 | 0 | 0 | 100% | 11/4/2020 |  | 220 Mile Plan | 0 | 0.81913
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | SH |  | 1.6625 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | SH |  | 1.403 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 | SH |  | 1.4701 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | SH |  | 2.0814 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129640 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 | SH |  | 1.6167 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | SH | GC | 0.97178 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | SH | GC | 1.5932 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  | 2020 Rsrv | 0 | 0
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 | SH |  | 2.5854 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35175847 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35176549 | ECOP-MONTE RIO 1113-H07-LR180 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35185022 | INSTALL 3RD PHASE ON ALLEGHANY 1101 |  | GC | 0.15152 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | SH |  | 3.1 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35193614 | NO-SA-SOLANO-8/18/20-LNU COMPLEX FIRE OH |  |  | 7.94 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35198909 | CV-YO-MADERA CNTY- 9-6-20 CREEK FIRE EVE |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35204191 | NO-NV- SHASTA 9/27/20 ZOGG FIRE SYS HRDN |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  | T1 A Tag | 0 | 0
35204225 | NR-SO-SONOMA- 9/28/20- GLASS FIRE SYS H |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  | T2/T3 A Tag | 0 | 0
35219099 | CWSP - HIGHLANDS 1102628 | SH |  | 17.3 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35037854 | X STS-TRAN_IDLE_REMV-16 POLES FROM E.O. | IF |  | 0.086553 | 0 | 0 | 0 | 0 | 0.086553 | 0.086553 | 0% | 0 | 0 | 0 | 0.086553 | 0% |  |  |  | 0 | 0
35219265 | CWSP - CRESTA 1101546650 | SH |  | 0.9 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219267 | CWSP - MARIPOSA 2102440236 PH1 | SH |  | 4.27 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219282 | CWSP - NORTH DUBLIN 2101 CB | SH |  | 1 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35223026 | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | SH |  | 1.0348 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
31089263 | MOVE FUSE 1179/RECON WITH TREE WIRE | SH |  | 0.075758 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
31269259 | ZACA 1101 FOXEN CYN RD, LOS OLIVOS | SH | MGE | 1.2095 | 1.2095 | 1 | 1.2095 | 0 | 1.2095 | 0 | 100% | 0 | 1.2095 | 0 | 0 | 100% |  |  |  | 1.2095 | 0
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 | SH |  | 0.48864 | 0.48864 | 1 | 0.48864 | 0 | 0.48864 | 0 | 100% | 0 | 0.48864 | 0 | 0 | 100% |  |  |  | 0.48864 | 0
31278200 | +OCEANO 1102 S HALCYON & PINE RDGE | SH |  | 0.39413 | 0.39 | 0.98952 | 0.39 | 0 | 0.39 | 0 | 98.95% | 0 | 0.39 | 0 | 0 | 98.95% |  |  |  | 0.39 | 0
31286573 | APPLE HILL 2102 HIGH SPLICE AREA | SH |  | 0.66136 | 0.66136 | 1 | 0.66136 | 0 | 0.66136 | 0 | 100% | 0 | 0.66136 | 0 | 0 | 100% |  |  |  | 0.66136 | 0
31290147 | OCCCR7 OLEMA 1101 REPLACE COND VISION RD | SH |  | 0.60114 | 0.60114 | 1 | 0.60114 | 0 | 0.60114 | 0 | 100% | 8.6126e-17 | 0.60114 | 0 | 0 | 100% |  |  |  | 0.60114 | 0
31319444 | RECON 5-SPANS PORTER CRK RD-RINCON 1103 | SH | Source Power (ARB) | 0.24318 | 0.24223 | 0.99611 | 0.24223 | 0 | 0.24223 | 0 | 99.61% | 0 | 0.24223 | 0 | 0 | 99.61% |  |  |  | 0.24223 | 0
35011247 | STS-COND_IDLE_REMV-3054 CALAVERITAS RD ( | IF |  | 0.20644 | 0.20644 | 1 | 0.20644 | 0 | 0.20644 | 0 | 100% | 0 | 0.20644 | 0 | 0 | 100% |  |  |  | 0.20644 | 0
35011264 | STS-POLE_IDLE_REMV-11700 WHISKEY SLIDE R | IF |  | 0.042235 | 0.039962 | 0.94619 | 0.042235 | 0 | 0.042235 | 0 | 100% | -0.0022727 | 0.042235 | 0 | 0 | 100% |  |  |  | 0 | 0.039962
35014889 | STS-POLE_DECA_REPL - #1E ON LINE @ R/O 2 | IF |  | 0.10455 | 0.10455 | 1 | 0.10455 | 0 | 0.10455 | 0 | 100% | 0 | 0.10455 | 0 | 0 | 100% |  |  |  | 0.10455 | 0
35022860 | STS-POLE_IDLE_REMV-END OF CALDERWOOD RD | IF |  | 0.069697 | 0.069697 | 1 | 0.069697 | 0 | 0.069697 | 0 | 100% | 0 | 0.069697 | 0 | 0 | 100% |  |  |  | 0.069697 | 0
35038136 | STS-COND_IDLE_REMV-7660 PONDEROSA WAY | IF |  | 0.035606 | 0.035606 | 1 | 0.035606 | 0 | 0.035606 | 0 | 100% | 0 | 0.035606 | 0 | 0 | 100% |  |  |  | 0 | 0.035606
35040225 | HIGGINS 1110 RECONDUCTOR | SH | Quanta/Summit | 1.6258 | 1.6258 | 1 | 1.6258 | 0 | 1.6258 | 0 | 100% | 0 | 1.6258 | 0 | 0 | 100% |  |  |  | 1.6258 | 0
35040742 | OCGC - 2018 MONTE RIO 1112 OH TO UG DEMO | SH |  | 0.53 | 0.53 | 1 | 0.53 | 0 | 0.53 | 0 | 100% | 0 | 0.53 | 0 | 0 | 100% |  |  |  | 0.53 | 0
35042365 | CWSP - CAMP EVERS 2106 - LR 60124 - PH 5 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35043299 | CWSP-OH COND RPLC: EEL RIVER 1102 FU1907 | SH | Wilson | 1.2076 | 1.2076 | 1 | 1.2076 | 0 | 1.2076 | 0 | 100% | 0 | 1.2076 | 0 | 0 | 100% |  |  |  | 1.2076 | 0
35089880 | OCGC PIH SILVERADO 2104 - ANGWIN UG_PH 2 | SH |  | 0.40095 | 0.40095 | 1 | 0.40095 | 0 | 0.40095 | 0 | 100% | 0 | 0.40095 | 0 | 0 | 100% |  |  |  | 0.40095 | 0
35217271 | SH - MIDDLETOWN 1103 LR 830 | SH |  | 7.9 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 | SH |  | 1.6915 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | SH | ARB | 2.18 | 2.25 | 1.0321 | 2.1784 | 0 | 2.2267 | 0.048295 | 99.93% | 0.071591 | 2.1784 | 0 | 0.048295 | 99.93% | 11/4/2020 |  | 220 Mile Plan | 0 | 2.25
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | SH |  | 1.6848 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
31048480 | STS-POLE_IDLE_REMV-S/O 21604 DONNER P | IF |  | 0.043561 | 0.043561 | 1 | 0.043561 | 0 | 0.043561 | 0 | 100% | 0 | 0.043561 | 0 | 0 | 100% |  |  |  | 0.043561 | 0
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | SH | GC | 2.0112 | 2.0112 | 1 | 2.0112 | 0 | 2.015 | 0.0037879 | 100% | 0 | 2.0112 | 0 | 0.0037879 | 100% | 8/24/2020 |  | 220 Mile Plan | 0 | 2.0112
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 | SH |  | 1.89 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35174474 | ECOP-CALISTOGA 1101-H01-LR736 PH1 | SH |  | 4.4 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35175844 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.3 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35176210 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.4 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | SH |  | 2.01 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | SH |  | 6.25 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35199565 | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  | T1 A Tag | 0 | 0
35212401 | FRRB - MONTICELLO 1101 CB |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35219096 | CWSP - KIRKER 2104442850 | SH |  | 5.75 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 | SH |  | 1 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219587 | CWSP - MARIPOSA 2102440236 PH2 | SH |  | 2.155 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219589 | CWSP - WILDWOOD 11011454 | SH |  | 7.83 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35222236 | MARIPOSA 2101 - #531 SLAUGHTER HOUSE | SH |  | 0.99 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35018539 | 6/30-STS-POLE_IDLE_REMV-#1S/O 3000GUIDIV | IF |  | 0.047727 | 0.047727 | 1 | 0.047727 | 0 | 0.047727 | 0 | 100% | 0 | 0.047727 | 0 | 0 | 100% |  |  |  | 0.047727 | 0
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | SH | GC | 0.58523 | 0.58523 | 1 | 0.58523 | 0 | 0.58523 | 0 | 100% | 0 | 0.58523 | 0 | 0 | 100% | 8/21/2020 |  | 220 Mile Plan | 0 | 0.58523
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | SH |  | 1.9886 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | SH |  | 1.3027 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | SH |  | 1.1358 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | SH |  | 0.9875 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 | SH |  | 1.2176 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35135864 | CWSP - GRAYS FLAT 401 FUSE 3079 ZONE | SH | ET Contractor | 1.7644 | 1.7644 | 1 | 1.7492 | 0 | 1.7492 | 0 | 99.14% | 0.015152 | 1.7492 | 0 | 0 | 99.14% | 11/9/2020 |  | 220 Mile Plan | 0 | 1.7644
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 | SH | GC | 1.2932 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35145005 | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 |  | Rokstad | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35145523 | *CANC* PSPS - FULTON 1102 HARDENING |  | GC | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | SH | GC | 0.7197 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155683 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.05 |  |  | 1.2405 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155684 | CWSP-BRUNSWICK 1105 LR2140 - PH 1.06 |  |  | 0.62273 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155751 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.17 |  |  | 0.49754 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155752 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.02 |  |  | 0.51648 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | SH |  | 1.7799 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219093 | CWSP - TIDEWATER 210614072 | SH |  | 4.74 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219286 | CWSP - DESCHUTES 11049718 PH1 | SH |  | 18.6 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
74022383 | CWSP-EL DORADO PH 2102 LR19542 PH 1.0 |  |  | 11.2 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35038669 | ANCH_SOIL_ADJU-2701 BLACKHAWK RI*DIV | IF |  | 0.075379 | 0.089962 | 1.1935 | 0.092803 | 0 | 0.092803 | 0 | 123.1% | -0.0028409 | 0.092803 | 0 | 0 | 123.1% |  |  |  | 0 | 0.089962
35175845 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.4 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35219097 | CWSP - COARSEGOLD 2104CB | SH |  | 8.58 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155680 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.02 |  |  | 1.3239 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155687 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.09 |  |  | 1.683 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155755 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.05 |  |  | 0.27102 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | SH | GC | 1.2676 | 0 | 0 | 0 | 0 | 1.2676 | 1.2676 | 0% | 0 | 0 | 0 | 1.2676 | 0% |  |  | 220 Mile Plan | 0 | 0
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 | SH |  | 1.4848 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35168823 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.7 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35173253 | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35173321 | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35174471 | ECOP-MONTE RIO 1113-H07-LR180 | SH |  | 1 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35175843 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35175850 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.5 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35176211 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.5 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | SH |  | 2.4201 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35191937 | ECOP - PUEBLO 2102 - H01-LR792 | SH |  | 4.2324 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | SH | GC | 2.39 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35193416 | EP 9265 ALHAMBRA AVE MORADA |  |  | 10.0928 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | SH |  | 1.8117 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35206134 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 |  |  | 1.5903 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219268 | CWSP - MARIPOSA 210197142 PH 1 | SH |  | 4.6 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
74022040 | 2019 CALISTOGA 1101 HIGH SPLICE COUNT | SH |  | 1.2646 | 1.2646 | 1 | 1.26 | 0 | 1.26 | 0 | 99.64% | 0.0045833 | 1.26 | 0 | 0 | 99.64% |  |  |  | 1.2646 | 0
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | SH |  | 0.6267 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35111038 | +STS-COND_IDLE_REMV-11010 FUENTEDS R | IF |  | 0.9233 | 0.9233 | 1 | 0.9233 | 0 | 0.9233 | 0 | 100% | 0 | 0.9233 | 0 | 0 | 100% |  |  |  | 0.9233 | 0
35155694 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.16 |  |  | 1.1174 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | SH | Quanta/Summit | 1.0686 | 0.5464 | 0.51134 | 0.33523 | 0 | 1.7326 | 1.3973 | 31.37% | 0.21117 | 0.33523 | 0 | 1.3973 | 31.37% |  |  | 220 Mile Plan | 0 | 0.5464
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | SH | Quanta/UECCo | 1.4354 | 1.4354 | 1 | 1.4354 | 0 | 1.4354 | 0 | 100% | -1.7225e-16 | 1.4354 | 0 | 0 | 100% | 11/4/2020 |  | 220 Mile Plan | 1.0926 | 0.3428
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | SH | Wilson | 1.3013 | 1.3013 | 1 | 1.3013 | 0 | 1.3013 | 0 | 100% | 0 | 1.3013 | 0 | 0 | 100% | 7/9/2020 |  |  | 0 | 1.3013
35114431 | CWSP - MORAGA 1101 - LR108540 - PH5 | SH | Alvah | 1.4369 | 1.4369 | 1 | 1.4369 | 0 | 1.4369 | 0 | 100% | 1.8948e-15 | 1.4369 | 0 | 0 | 100% | 11/4/2020 |  | 220 Mile Plan | 0 | 1.4369
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | SH | GC | 0.82822 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35051472 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3 | SH |  | 7.28 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | SH | GC | 1.1682 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  | 220 Mile Plan | 0 | 0
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 | SH | MPE | 1.06 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35064793 | LP RECONDUCTOR, CABRILLO 1104 S006CC102 | SH | MGE | 2.2996 | 2.2996 | 1 | 2.2996 | 0 | 2.2996 | 0 | 100% | 0 | 2.2996 | 0 | 0 | 100% |  |  |  | 2.2996 | 0
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | SH |  | 1.4902 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 | SH |  | 1.0098 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 | SH |  | 3.3182 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 | SH |  | 0.56061 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35168820 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.4 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 | SH |  | 6 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35174468 | ECOP-STANISLAUS 1702-H01-LR37276-PH2 | SH |  | 5.7201 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35175854 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.4 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35175857 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.3 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35177108 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.7 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35191130 | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 |  |  | 8.1 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | SH |  | 1.2301 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | SH |  | 6.51 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35194291 | SO-SJ-SANTA CLARA - 08/18/20 - SCU LIGHT |  |  | 8.7198 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35199922 | CV-FR - CREEK 9/13/20 - CREEK FIRE SYS H |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35206138 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.5 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35092061 | STS-COND_IDLE_REMV - 19501 OLD CAZ *OCLH | IF |  | 0.022727 | 0.022727 | 1 | 0.022727 | 0 | 0.022727 | 0 | 100% | 0 | 0.022727 | 0 | 0 | 100% |  |  |  | 0 | 0.022727
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | SH | Quanta | 1.6417 | 1.6417 | 1 | 1.6417 | 0 | 1.6417 | 0 | 100% | 0 | 1.6417 | 0 | 0 | 100% | 8/13/2020 |  | 220 Mile Plan | 1.4508 | 0.19091
35113871 | SILVERADO 2104 RECONDUCTOR - PHASE 2 | SH | Source Power (ARB) | 0.12311 | 0.12311 | 1 | 0.12311 | 0 | 0.12311 | 0 | 100% | 0 | 0.12311 | 0 | 0 | 100% |  |  |  | 0.12311 | 0
35038059 | STS-COND_IDLE_REMV-11648 LA PORTE ROAD | IF |  | 0.02178 | 0.02178 | 1 | 0.02178 | 0 | 0.02178 | 0 | 100% | 0 | 0.02178 | 0 | 0 | 100% |  |  |  | 0.02178 | 0
35083751 | STS-COND_IDLE_REMV-1355 TULE RD/FAMOSO L | IF |  | 0.11364 | 0.11364 | 1 | 0.11364 | 0 | 0.11364 | 0 | 100% | 0 | 0.11364 | 0 | 0 | 100% |  |  |  | 0.11364 | 0
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | SH | Quanta/UECCo | 2.2117 | 2.2117 | 1 | 2.2117 | 0 | 2.2117 | 0 | 100% | 0 | 2.2117 | 0 | 0 | 100% | 8/24/2020 |  | 220 Mile Plan | 0.75303 | 1.4587
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | SH | GC | 2.1581 | 0 | 0 | 0 | 0 | 2.1347 | 2.1347 | 0% | 0 | 0 | 0 | 2.1347 | 0% |  |  | 220 Mile Plan | 0 | 0
35177107 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.6 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35010358 | X STS-COND_IDLE_REMV-OLD GIRL SCOUT | IF |  | 0.097727 | 0.097727 | 1 | 0.097727 | 0 | 0.097727 | 0 | 100% | 0 | 0.097727 | 0 | 0 | 100% |  |  |  | 0.097727 | 0
35038502 | STS-TRAN_IDLE_REMV-CHOLAME VALLEY RD | IF |  | 0.16402 | 0.16402 | 1 | 0.16402 | 0 | 0.16402 | 0 | 100% | 0 | 0.16402 | 0 | 0 | 100% |  |  |  | 0.16402 | 0
35078144 | STS-TRAN_IDLE_REMV - SIERRA NATIONAL FOR | IF |  | 0.085227 | 0.085227 | 1 | 0.085227 | 0 | 0.085227 | 0 | 100% | 0 | 0.085227 | 0 | 0 | 100% |  |  |  | 0.085227 | 0
35100238 | STS-COND_IDLE_REMV-3750 SUNRISE RIDGE | IF |  | 0.12595 | 0.12595 | 1 | 0.12595 | 0 | 0.12595 | 0 | 100% | 0 | 0.12595 | 0 | 0 | 100% |  |  |  | 0.12595 | 0
35109764 | STS-COND_IDLE_REMV - YELLOW WOOD RD ON K | IF |  | 0.0075758 | 0.0075758 | 1 | 0.0075758 | 0 | 0.0075758 | 0 | 100% | 0 | 0.0075758 | 0 | 0 | 100% |  |  |  | 0 | 0.0075758
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | SH | GC | 1.3491 | 1.3496 | 1.0004 | 1.172 | 0 | 1.3803 | 0.20833 | 86.87% | 0.17765 | 1.172 | 0 | 0.20833 | 86.87% | 11/3/2020 |  | 220 Mile Plan | 0 | 1.3496
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 | SH |  | 1.9924 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | SH |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219264 | CWSP - POSO MOUNTAIN 2103CB | SH |  | 2.33 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | SH |  | 1.208 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | SH |  | 4.771 | 4.771 | 1 | 4.771 | 0 | 4.771 | 0 | 100% | 6.8901e-16 | 4.771 | 0 | 0 | 100% |  |  |  | 4.771 | 0
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | SH | VPI | 0.84754 | 0.84754 | 1 | 0.72159 | 0 | 0.72159 | 0 | 85.14% | 0.12595 | 0.72159 | 0 | 0 | 85.14% | 11/4/2020 |  | 220 Mile Plan | 0 | 0.84754
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | SH | Quanta/UECCo | 0.96742 | 0.96742 | 1 | 0.96742 | 0 | 0.96742 | 0 | 100% | 0 | 0.96742 | 0 | 0 | 100% | 11/4/2020 |  | 220 Mile Plan | 0 | 0.96742
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | SH | GC | 1.8402 | 1.8402 | 1 | 1.8402 | 0 | 1.8402 | 0 | 100% | 0 | 1.8402 | 0 | 0 | 100% | 7/30/2020 |  | 220 Mile Plan | 0 | 1.8402
35083680 | STS-TRAN_IDLE_REMV-LOC #1, RADIAL TAP 4 | IF |  | 0.074053 | 0.089962 | 1.2148 | 0.086742 | 0 | 0.086742 | 0 | 117.1% | 0.0032197 | 0.086742 | 0 | 0 | 117.1% |  |  |  | 0 | 0.089962
35083780 | STS-COND_IDLE_REMV-5088 TIPTOP RD | IF |  | 0.034091 | 0.034091 | 1 | 0 | 0 | 0.034091 | 0.034091 | 0% | 0.034091 | 0 | 0 | 0.034091 | 0% |  |  |  | 0 | 0.034091
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  |  | 1.1875 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | SH | GC | 1.0256 | 1.0256 | 1 | 1.0167 | 0 | 1.0167 | 0 | 99.13% | 0.0089015 | 1.0167 | 0 | 0 | 99.13% | 11/4/2020 |  | 220 Mile Plan | 0 | 1.0256
35155744 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.11 |  |  | 0.50587 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35067619 | CWSP - MONTE RIO 1112 - LR 120 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35083897 | STS-COND_IDLE_REMV-14403 LAS MORAS ST | IF |  | 0.052273 | 0.05 | 0.95652 | 0.051136 | 0 | 0.051136 | 0 | 97.83% | -0.0011364 | 0.051136 | 0 | 0 | 97.83% |  |  |  | 0 | 0.05
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | SH | Source Power (ARB) | 1.6653 | 1.6653 | 1 | 1.6653 | 0 | 1.6653 | 0 | 100% | 0 | 1.6653 | 0 | 0 | 100% | 11/4/2020 |  | 220 Mile Plan | 0 | 1.6653
35217273 | SH - UPPER LAKE 1101 CB | SH |  | 1.1 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219588 | CWSP - MARIPOSA 2102440236 PH3 | SH |  | 2.155 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35222235 | DUNLAP 1102 - #631 UC BERKELEY WHITAKER | SH |  | 2.6 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | SH |  | 5.8756 | 5.8756 | 1 | 5.8756 | 0 | 5.8756 | 0 | 100% | 6.8901e-16 | 5.8756 | 0 | 0 | 100% |  |  |  | 5.8756 | 0
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | SH | GC | 2.4191 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | SH | Wilson | 2.61 | 2.61 | 1 | 2.6098 | 0 | 2.6098 | 0 | 99.99% | 0.00018939 | 2.6098 | 0 | 0 | 99.99% |  |  |  | 2.61 | 0
35037374 | COND_IDLE_REMV-15587 38TH AVE CLK * KS | IF |  | 0.018939 | 0.018939 | 1 | 0.018939 | 0 | 0.018939 | 0 | 100% | 0 | 0.018939 | 0 | 0 | 100% |  |  |  | 0 | 0.018939
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | SH | GC | 1.7652 | 0 | 0 | 0 | 0 | 1.7652 | 1.7652 | 0% | 0 | 0 | 0 | 1.7652 | 0% |  |  | 220 Mile Plan | 0 | 0
35115404 | STS-COND_IDLE_REMV-5745 GOLD ST | IF |  | 0.022917 | 0.020076 | 0.87603 | 0.022917 | 0 | 0.022917 | 0 | 100% | -0.0028409 | 0.022917 | 0 | 0 | 100% |  |  |  | 0 | 0.020076
35145002 | PSPS - IGNACIO 1101 - CB | SH |  | 1.2968 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155698 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.05 |  |  | 1.1992 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35072362 | CWSP-OH COND RPLC: EEL RIVER 1102 FU1913 | SH | Wilson | 2.7068 | 2.7068 | 1 | 2.7068 | 0 | 2.7068 | 0 | 100% | 3.4451e-16 | 2.7068 | 0 | 0 | 100% |  |  |  | 2.7068 | 0
35079416 | STS-COND_IDLE_REMV-3/P/N/3/P/E/O ROCKY C | IF |  | 0.052841 | 0 | 0 | 0 | 0 | 0.052841 | 0.052841 | 0% | 0 | 0 | 0 | 0.052841 | 0% |  |  |  | 0 | 0
35085532 | CWSP - SILVERADO 2104 - LR722 PH 1C | SH | Quanta/UECCo | 1.1265 | 1.1265 | 1 | 1.1265 | 0 | 1.1265 | 0 | 100% | 0 | 1.1265 | 0 | 0 | 100% |  |  |  | 1.1265 | 0
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E | SH | Source Power (ARB) | 0.79375 | 0.79375 | 1 | 0.79375 | 0 | 0.79375 | 0 | 100% | 0 | 0.79375 | 0 | 0 | 100% | 11/9/2020 |  | 220 Mile Plan | 0.069697 | 0.72405
35094390 | CWSP-KONOCTI 1102-LR 532 PH 3 | SH | Wilson | 0.54564 | 0.54564 | 1 | 0.54564 | 0 | 0.54564 | 0 | 100% | 0 | 0.54564 | 0 | 0 | 100% |  |  |  | 0.54564 | 0
35094392 | OCGC CWSP-KONOCTI 1102-LR 532 PH 5 | SH |  | 0.37045 | 0.37045 | 1 | 0.37045 | 0 | 0.37045 | 0 | 100% | 0 | 0.37045 | 0 | 0 | 100% |  |  |  | 0.37045 | 0
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 | SH |  | 1.5905 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 | SH | Alvah | 2.3862 | 2.3862 | 1 | 2.3862 | 0 | 2.3862 | 0 | 100% | 0 | 2.3862 | 0 | 0 | 100% | 11/4/2020 |  | 220 Mile Plan | 2.3163 | 0.069886
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | SH | Quanta/UECCo | 1.5261 | 1.5261 | 1 | 1.5261 | 0 | 1.5261 | 0 | 100% | 0 | 1.5261 | 0 | 0 | 100% | 11/4/2020 |  | 220 Mile Plan | 0 | 1.5261
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | SH | Quanta/UECCo | 1.3375 | 1.3375 | 1 | 1.3375 | 0 | 1.3375 | 0 | 100% | -1.7225e-16 | 1.3375 | 0 | 0 | 100% | 11/3/2020 |  | 220 Mile Plan | 0.68485 | 0.65265
35147045 | *CANC* *DO NOT USE* PSPS - CASTRO V*CANC |  |  | 0.39773 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35177111 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.8 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35219260 | CWSP - WYANDOTTE 110932586 | SH |  | 1.34 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35217269 | SH - MIDDLETOWN 1102 - LR 302610 | SH |  | 5.75 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | SH |  | 2.9299 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219092 | CWSP - POSO MOUNTAIN 2104CB | SH |  | 5.35 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219273 | CWSP - VOLTA 110149742 | SH |  | 3.48 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219291 | CWSP - VACA DIXON 1101126774 | SH |  | 0.79 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | SH |  | 1 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219591 | CWSP - OLETA 1101754718 | SH |  | 2.88 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35220895 | SH - MIDDLETOWN 1103 - LR 830 PH2 | SH |  | 11.35 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35220896 | SH - MIDDLETOWN 1103 - LR 830 PH3 | SH |  | 3.64 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | SH |  | 1 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
44119915 | STS-OFAC_IDLE_DEEN - 41569 LILLEY MT DR |  |  | 0.075758 | 0 | 0 | 0 | 0 | 0.075758 | 0.075758 | 0% | 0 | 0 | 0 | 0.075758 | 0% |  |  |  | 0 | 0
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  |  | 1.15 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | SH |  | 2.25 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | SH |  | 1.5263 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35175849 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.4 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  |  | 1.7085 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  |  | 1.828 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | SH | GC | 0.72102 | 0 | 0 | 0 | 0 | 0.72102 | 0.72102 | 0% | 0 | 0 | 0 | 0.72102 | 0% |  |  | 220 Mile Plan | 0 | 0
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | SH |  | 1.5 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35113959 | STS-OFAC_IDLE_REMV-1229 APPLEMONT RANCH | IF |  | 0.0875 | 0.089962 | 1.0281 | 0.0875 | 0 | 0.0875 | 0 | 100% | 0.0024621 | 0.0875 | 0 | 0 | 100% |  |  |  | 0 | 0.089962
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | SH |  | 2.117 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | SH |  | 1.4106 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | SH | GC | 1.1602 | 0.90947 | 0.78387 | 0.081061 | 0 | 1.0966 | 1.0155 | 6.987% | 0.82841 | 0.081061 | 0 | 1.0155 | 6.987% | 11/9/2020 |  | 220 Mile Plan | 0 | 0.90947
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | SH |  | 1.2792 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | SH |  | 2.45 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | SH |  | 2.15 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | SH | GC | 2.1439 | 2.1439 | 1 | 2.0127 | 0 | 2.1231 | 0.11042 | 93.88% | 0.13125 | 2.0127 | 0 | 0.11042 | 93.88% | 11/9/2020 |  | 220 Mile Plan | 0 | 2.1439
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | SH | Intren | 1.6472 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | SH |  | 1.2854 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | SH | GC | 1.8371 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  | 220 Mile Plan | 0 | 0
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | SH |  | 1.8347 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116516 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.3 | SH |  | 0.91383 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116518 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.6 | SH |  | 2.0686 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | SH | Quanta/Par | 1.2835 | 0.37008 | 0.28833 | 0.3661 | 0 | 1.2919 | 0.92576 | 28.52% | 0.0039773 | 0.3661 | 0 | 0.92576 | 28.52% | 11/4/2020 |  | 220 Mile Plan | 0 | 0.37008
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | SH |  | 2.2884 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | SH |  | 2.0447 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | SH |  | 2.028 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 | SH |  | 1.3201 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | SH |  | 1.5799 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129622 | STS-COND_IDLE_REMV - A/F 1EO 3600 BLACKT | IF |  | 0.060606 | 0.070076 | 1.1562 | 0.067235 | 0 | 0.067235 | 0 | 110.9% | 0.0028409 | 0.067235 | 0 | 0 | 110.9% |  |  |  | 0 | 0.070076
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | SH |  | 1.0403 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  |  | 1.9884 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | SH | GC | 1.3775 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35146183 | STS-OFAC_IDLE_REMV - R/O 3200 AUBURN FOL | IF |  | 0.056818 | 0.060038 | 1.0567 | 0.064015 | 0 | 0.064015 | 0 | 112.7% | -0.0039773 | 0.064015 | 0 | 0 | 112.7% |  |  |  | 0 | 0.060038
35155690 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.12 |  |  | 0.9625 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155748 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.14 |  |  | 0.51894 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | SH | Wilson | 1.1771 | 1.1771 | 1 | 1.1771 | 0 | 1.1771 | 0 | 100% | 0 | 1.1771 | 0 | 0 | 100% | 11/9/2020 |  |  | 0 | 1.1771
35085681 | SILVERADO 2105 WIRE DOWN - PH 4 | SH |  | 0.55814 | 0.55568 | 0.99559 | 0.55568 | 0 | 0.55568 | 0 | 99.56% | 0 | 0.55568 | 0 | 0 | 99.56% |  |  |  | 0.55568 | 0
35176497 | ECOP-STANISLAUS 1702-H03-LR1850 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35155692 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.14 |  |  | 0.99773 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155741 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.08 |  |  | 0.16856 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155743 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.10 |  |  | 0.69924 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155758 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.08 |  |  | 0.66477 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155841 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.11 |  |  | 0.85057 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | SH |  | 1.432 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35173255 | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35173959 | CWSP-MIWUK 1702-LR 38218-PH 1.6 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35174174 | ECOP-STANISLAUS 1702-H03-LR1850 | SH |  | 0.6 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35174476 | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 |  |  | 8.78 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1 | SH |  | 4.6402 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35174993 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35175846 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.5 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35175848 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.3 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35192043 | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35192292 | ECOP - FULTON 1107 - H02-LR604 | SH |  | 3.75 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219098 | CWSP - MIDDLETOWN 1101118494 | SH |  | 1.33 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | SH | Quanta | 2.7609 | 2.7605 | 0.99985 | 2.7609 | 0 | 2.7609 | 0 | 100% | -0.00041667 | 2.7609 | 0 | 0 | 100% |  |  | 220 Mile Plan | 2.4753 | 0.28519
74022382 | CWSP-COLUMBIA HILL 1101-LR 2212 PH1 | SH | Quanta | 2.3464 | 2.3464 | 1 | 2.3464 | 0 | 2.3464 | 0 | 100% | -3.4451e-16 | 2.3464 | 0 | 0 | 100% |  |  |  | 2.3464 | 0
35031662 | CWSP - LOS GATOS 1106 - LB44 - PHASE 2.1 | SH | MGE -CIVIL ONLY | 0.56402 | 0.56402 | 1 | 0.56402 | 0 | 0.56402 | 0 | 100% | -5.1676e-16 | 0.56402 | 0 | 0 | 100% | 11/9/2020 |  | 220 Mile Plan | 0 | 0.56402
35078758 | COND_IDLE_REMV-20508 HIGHWAY 116 *OCLH | IF |  | 0.0094697 | 0.0098485 | 1.04 | 0.0098485 | 0 | 0.0098485 | 0 | 104% | -1.3457e-18 | 0.0098485 | 0 | 0 | 104% |  |  |  | 0 | 0.0098485
35115158 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.5 | SH | GC | 2.1462 | 2.1462 | 1 | 2.1462 | 0 | 2.1462 | 0 | 100% | -3.4451e-16 | 2.1462 | 0 | 0 | 100% | 8/5/2020 |  | 220 Mile Plan | 0 | 2.1462
35145006 | PSPS - STAFFORD 1101 LR 1298 | SH |  | 0.27008 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219266 | CWSP - MARIPOSA 2102CB | SH |  | 5.25 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 | SH |  | 5.71 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219283 | CWSP - NORTH DUBLIN 2101 CB | SH |  | 0.82 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | SH |  | 1.5674 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
74008802 | INST ROSSMOOR 1109 FDR_MORAGA BK5 EMERG |  | GC | 2.3748 | 0 | 0 | 0 | 0 | 1.1604 | 1.1604 | 0% | 0 | 0 | 0 | 1.1604 | 0% |  |  |  | 0 | 0
74022387 | CWSP-MIDDLETOWN 1101-TS 1079 | SH |  | 3.9701 | 3.9701 | 1 | 3.9701 | 0 | 3.9701 | 0 | 100% | 0 | 3.9701 | 0 | 0 | 100% |  |  |  | 3.9701 | 0
74022389 | *CANC* CWSP - PARADISE 1106 - OCB & LR 2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
99999998 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 | SH | Quanta/UECCo | 1.9432 | 1.9432 | 1 | 1.9432 | 0 | 1.9432 | 0 | 100% | 0 | 1.9432 | 0 | 0 | 100% | 11/9/2020 |  | 220 Mile Plan | 1.1089 | 0.83428
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | SH | Quanta/Par | 2.3379 | 2.3379 | 1 | 2.3379 | 0 | 2.3379 | 0 | 100% | 0 | 2.3379 | 0 | 0 | 100% | 8/24/2020 |  | 220 Mile Plan | 1.2381 | 1.0998
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | SH |  | 0.87 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | SH |  | 0.86004 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
31102666 | REMV IDLE FAC 6 LOCS WO C/O5095 NAP+++++ | IF |  | 0.2358 | 0.2358 | 1 | 0.2358 | 0 | 0.2358 | 0 | 100% | 0 | 0.2358 | 0 | 0 | 100% |  |  |  | 0.2358 | 0
31248532 | CWSP HALF MOON BAY 1101 LS CO4063 | SH | Michels | 0.73788 | 0.73996 | 1.0028 | 0.74356 | 0 | 0.74356 | 0 | 100.8% | -0.0035985 | 0.74356 | 0 | 0 | 100.8% | 11/9/2020 |  | 220 Mile Plan | 0 | 0.73996
35065058 | STS-POLE_IDLE_REMV - BETWEEN 1860 & 1850 | IF |  | 0.10038 | 0.10038 | 1 | 0.10038 | 0 | 0.10038 | 0 | 100% | 0 | 0.10038 | 0 | 0 | 100% |  |  |  | 0.10038 | 0
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | SH | Alvah | 1.3684 | 0.73996 | 0.54076 | 0.7358 | 0 | 1.3864 | 0.65057 | 53.77% | 0.0041667 | 0.7358 | 0 | 0.65057 | 53.77% | 11/9/2020 |  | 220 Mile Plan | 0 | 0.73996
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | SH | GC | 0.53485 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155740 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.07 |  |  | 0.68864 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155840 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.10 |  |  | 0.49167 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | SH |  | 2.035 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | SH |  | 9 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35223024 | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | SH |  | 1.2659 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35083742 | STS-COND_IDLE_REMV-56060 NORTH FORK RD ( | IF |  | 0.029356 | 0.029356 | 1 | 0 | 0 | 0.029356 | 0.029356 | 0% | 0.029356 | 0 | 0 | 0.029356 | 0% |  |  |  | 0 | 0.029356
35083765 | STS-COND_IDLE_REMV - 9711 DUBLIN CANYON | IF |  | 0.011364 | 0.0094697 | 0.83333 | 0.0094697 | 0 | 0.0094697 | 0 | 83.33% | 0 | 0.0094697 | 0 | 0 | 83.33% |  |  |  | 0 | 0.0094697
35083840 | OLCH STS-COND_IDLE_RMV-41524 ACORN | IF |  | 0.11534 | 0.11534 | 1 | 0.11534 | 0 | 0.11534 | 0 | 100% | 0 | 0.11534 | 0 | 0 | 100% |  |  |  | 0 | 0.11534
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H | SH | Quanta | 0.71061 | 0.71061 | 1 | 0.71061 | 0 | 0.71061 | 0 | 100% | 0 | 0.71061 | 0 | 0 | 100% | 11/4/2020 |  | 220 Mile Plan | 0.59167 | 0.11894
35085680 | SILVERADO 2105 WIRE DOWN - PH 3 |  |  | 0 | 0 |  | 0 | 0 | 1.6538 | 1.6538 |  | 0 | 0 | 0 | 1.6538 |  |  |  |  | 0 | 0
35087207 | STS-REPL POLE 16E/O 2S/O CO 19161 BLA | IF |  | 0.2017 | 0.2017 | 1 | 0.2017 | 0 | 0.2017 | 0 | 100% | 0 | 0.2017 | 0 | 0 | 100% |  |  |  | 0.2017 | 0
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | SH | GC | 2.0153 | 2.0153 | 1 | 2.0153 | 0 | 2.0153 | 0 | 100% | -3.4451e-16 | 2.0153 | 0 | 0 | 100% | 8/13/2020 |  | 220 Mile Plan | 0 | 2.0153
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | SH |  | 1.3826 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | SH |  | 1.2422 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 | SH |  | 0.69432 | 0.69432 | 1 | 0.69432 | 0 | 0.69432 | 0 | 100% | 0 | 0.69432 | 0 | 0 | 100% | 7/22/2020 |  |  | 0.69432 | 0
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | SH | GC | 2.7725 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35094397 | CWSP-KONOCTI 1102-LR 532 PH 10 | SH | GC | 1.0646 | 0 | 0 | 0 | 0 | 1.0617 | 1.0617 | 0% | 0 | 0 | 0 | 1.0617 | 0% |  |  | 220 Mile Plan | 0 | 0
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | SH |  | 1.6985 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 | SH |  | 1 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 | SH | Quanta/Par | 2.1989 | 2.1989 | 1 | 2.1989 | 0 | 2.1989 | 0 | 100% | 0 | 2.1989 | 0 | 0 | 100% | 8/24/2020 |  | 220 Mile Plan | 0.37273 | 1.8261
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 | SH | Quanta/Par | 2.1593 | 2.1593 | 1 | 2.1593 | 0 | 2.1593 | 0 | 100% | 0 | 2.1593 | 0 | 0 | 100% | 8/24/2020 |  | 220 Mile Plan | 0 | 2.1593
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 | SH | Quanta/Par | 1.9892 | 1.9892 | 1 | 1.9892 | 0 | 1.9892 | 0 | 100% | 0 | 1.9892 | 0 | 0 | 100% | 8/24/2020 |  | 220 Mile Plan | 0 | 1.9892
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | SH |  | 1.0097 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | SH |  | 0.77 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | SH | GC | 1.5894 | 0.7589 | 0.47748 | 0.70663 | 0.047727 | 1.5191 | 0.76477 | 44.46% | 0.052273 | 0.70663 | 0 | 0.8125 | 44.46% |  |  | 220 Mile Plan | 0 | 0.7589
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | SH | Quanta/Summit | 1.0386 | 0 | 0 | 0 | 0 | 2.1413 | 2.1413 | 0% | 0 | 0 | 0 | 2.1413 | 0% |  |  |  | 0 | 0
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | SH | GC | 1.8127 | 0 | 0 | 0 | 0 | 1.7366 | 1.7366 | 0% | 0 | 0 | 0 | 1.7366 | 0% |  |  | 220 Mile Plan | 0 | 0
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | SH | GC | 1.8958 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  | 220 Mile Plan | 0 | 0
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | SH | GC | 1.7947 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  | 220 Mile Plan | 0 | 0
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | SH |  | 1.6047 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | SH | Wilson | 1.1201 | 1.1201 | 1 | 1.0847 | 0 | 1.308 | 0.2233 | 96.84% | 0.035417 | 1.0847 | 0 | 0.2233 | 96.84% |  |  | 220 Mile Plan | 0 | 1.1201
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | SH |  | 1.8883 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | SH | Quanta/Summit | 2.1242 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | SH |  | 1.8428 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | SH |  | 1.1981 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | SH | GC | 0.84905 | 0 | 0 | 0 | 0 | 0.84905 | 0.84905 | 0% | 0 | 0 | 0 | 0.84905 | 0% |  |  | 220 Mile Plan | 0 | 0
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | SH |  | 1.6201 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | SH |  | 2.0208 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | SH |  | 1.1481 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  |  | 1.4235 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | SH |  | 0.90777 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35144940 | *CANC* PSPS - HICKS 2101 - CB |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35144942 | *CANC* PSPS - PAUL SWEET 2105 - CB |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35145001 | PSPS - CLAYTON 2215 - CB | SH |  | 1.9119 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155695 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.02 |  |  | 1.035 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35155697 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.04 |  |  | 0.39394 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 | SH |  | 1.5464 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 | SH |  | 2.6278 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | SH |  | 0.94697 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35173320 | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35173754 | ECOP-BRUNSWICK 1106-H08-LR51486 | SH |  | 6.3 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2 | SH |  | 10.2701 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35175858 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.4 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35181199 | ECOP-WEST POINT 1101-H03-TS L373 | SH |  | 2.5201 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35193574 | SR-CC-SANTA CRUZ-08-16-20 CZU AUG FIRE |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  | T2/T3 A Tag | 0 | 0
35199649 | CV-YO-MADERA - 9/10/20 CREEK FIRE SYS H |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35206135 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.3 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35217272 | SH - KESWICK 1101 LR 1586 | SH |  | 10.0301 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219269 | CWSP - VACA DIXON 110540092 | SH |  | 23.17 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35219280 | CWSP - POTTER VALLEY P H 110564118 | SH |  | 1.86 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | SH |  | 0.74 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  |  |  | 0 | 0
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | SH | GC | 5.5545 | 0.96004 | 0.17284 | 0.96061 | 0 | 5.2551 | 4.2945 | 17.29% | -0.00056818 | 0.96061 | 0 | 4.2945 | 17.29% |  |  | 220 Mile Plan | 0 | 0.96004
99999999 |  |  |  | 0.051136 | 0.051136 | 1 | 0 | 0 |  | 0 | 0% | 0.051136 | 0 | 0 | 0 | 0% |  |  |  | 0.051136 | 0
Totals | [6 empty] | 287.7295 | 0.20682 |  | 62.5062 |  |  | 287.6691 | 0.060417 | 62.713 |  |  |  |  | 140.088 | 150.69
Note on B1: Mason, Derek: Double click on a description to view span information for that order.

## Summary
| Total (All Years) | 2019 Total | 2020 Total for LTIP (Computed)
QA Pass | 287.7295 | 140.088 | 147.6415
QA Fix | 0.20682
Total QA Reviewed | 287.9363
IA Pass | 287.6691 | 140.088 | 147.5811
IA Fix | 0.060417