## Q3-Q4 Restoration AI (hidden)
PG&E Tower Assessment | [8 empty] | PRIVILEGED AND CONFIDENTIAL DRAFT FOR DISCUSSION
Action Items Tracker Template | [8 empty] | 2021-04-14 16:15
Actions from Restoration Q3-Q4 Workshop
# | Functional Group | Date Identified | Identified by | Objective | Item | Owner (s) | Due date / RAG Status | Status | Comments
1 | PMO | 2016-08-22 | Workshop | Tower Restoration | Name for "Pilot" |  | 2016-08-24 | Closed | Initial restoration, Phase 1; 2016 Restoration
2 | Operations | 2016-08-22 | Workshop | Tower Restoration | Determine additional customers need to reach 50/50 LBP/non-LBP | E. Hemus | 2016-08-22 | Closed | Would this change our engagement strategy?
3 | Operations | 2016-08-22 | Workshop | Tower Restoration | List of Towers | E. Hemus | 2016-08-24 | Closed
4 | Operations | 2016-08-22 | Workshop | Tower Restoration | Identify site walk participants | E. Hemus | 2016-08-26 | Closed
5 | Operations | 2016-08-22 | Workshop | Tower Restoration | Hot procedure work pkg | S. Clesen | 2016-09-27 | Closed | PGE approval needed by 9/27
6 | Operations | 2016-08-22 | Workshop | Tower Restoration | Clearance | E. Hemus | 2016-09-01 | Closed | Waiting to hear back from BJ
7 | Operations | 2016-08-22 | Workshop | Tower Restoration | Detailed schedule | E. Hemus | 2016-08-31 | Closed | Send with dependency dates
8 | Operations | 2016-08-22 | Workshop | Tower Restoration | Veg. review | Y. Davarzadeh | 2016-08-31 | Closed
9 | Operations | 2016-08-22 | Workshop | Tower Restoration | Laydown yards and LZ | E. Hemus | 2016-09-09 | Closed | Handoff to Phil; ensure that Nate has a chance to review in advance of mobilization
10 | Operations | 2016-08-22 | Workshop | Tower Restoration | Engineering approval soils | S. Clesen; Y. Davarzadeh | 2016-09-09 | Closed | Threshold
53 | PMO | 2016-09-26 | Workshop | Tower Restoration | Review non-responsive customer towers with Joe | S. Clesen | 2016-09-28 | Closed | Vanessa to provide names
12 | Customer | 2016-08-22 | Workshop | Tower Restoration | Customer research | Matt | 2016-08-24 | Closed
13 | Customer | 2016-08-22 | Workshop | Tower Restoration | Customer letter, confirmation e-mail | N. Liebelt | 2016-08-29 | Closed | Letter, email approved. Talking points to be updated
14 | Customer | 2016-08-22 | Workshop | Tower Restoration | Gen Ref update - rapid response | N. Liebelt | 2016-09-02 | Closed
15 | Customer | 2016-08-22 | Workshop | Tower Restoration | 200, 500-ft radius list | V. Bryan | 2016-11-01 | Closed | Revisit with potential customer sites south of Oroville
16 | Customer | 2016-08-22 | Workshop | Tower Restoration | Customer health related talking points | Keadjian | 2016-10-31 | Open | Draft send to M. Dudley for initial review
17 | Land | 2016-08-22 | Workshop | Tower Restoration | Confirm P1 status | S. Hughes | 2016-08-24 | Closed
45 | Land | 2016-09-09 | Working Team | Tower Restoration | FAI veg, confirm they are using same access protocol | S. Clesen | 2016-10-07 | Closed | Create CAP, request messaging, if available
19 | Land | 2016-08-22 | Workshop | Tower Restoration | Determination Of Rights | S. Hughes | 2016-09-02 | Closed | Stored on land site
20 | Environmental | 2016-08-22 | Workshop | Tower Restoration | Determine allowed work hours in Butte County | N. Lishman | 2016-08-23 | Closed | 7am - 6
21 | Environmental | 2016-08-22 | Workshop | Tower Restoration | AEA check | N. Lishman | 2016-08-26 | Closed
22 | Environmental | 2016-08-22 | Workshop | Tower Restoration | Soil sampling validation/assessment | D. Starring | 2016-08-31 | Closed
23 | Environmental | 2016-08-22 | Workshop | Tower Restoration | Confirm NEA update needed | D. Starring | 2016-08-31 | Closed
24 | Environmental | 2016-08-22 | Workshop | Tower Restoration | AUS/PSC oversight (waste management contract) | D. Starring | 2016-09-12 | Closed
25 | Public Affairs | 2016-08-22 | Workshop | Tower Restoration | Identify key stakeholders (ex. Butte) | S. Isaacson | 2016-08-26 | Closed | City manager, electeds, police, fire, county health
26 | Corporate comms | 2016-08-22 | Workshop | Tower Restoration | Draft content and conversations with digital strategies regarding website development | N. Liebelt | 2016-08-25 | Closed
27 | Corporate comms | 2016-08-22 | Workshop | Tower Restoration | Develop envelope messaging for letter | J. Hirsch | 2016-09-30 | Closed
28 | Corporate comms | 2016-08-24 | Working Team | Tower Restoration | Printing of letter, envelope, return label, mailing etc. | J. Hirsch; V. Bryan | 2016-09-06 | Closed
29 | Land | 2016-08-26 | Working Team | Tower Restoration | Develop talking points regarding customer soil removal refusal | Keadjian | 2016-09-02 | Closed
30 | PMO | 2016-08-31 | Working Team | Tower Restoration | Soil removal depth standards per guidelines | S. Clesen | 2016-08-31 | Closed | Status on Tuesday morning
31 | Environmental | 2016-08-31 | Working Team | Tower Restoration | Identify towers for use in soil sampling | D. Starring | 2016-09-07 | Closed
32 | LCE | 2016-09-02 | Working Team | Tower Restoration | Updates to customer phone script | Keadjian | 2016-09-07 | Closed
33 | Corporate comms | 2016-09-02 | Working Team | Tower Restoration | Gen Ref update - NV Letter | P. Doherty | 2016-09-07 | Closed
34 | Operations | 2016-09-06 | Working Team | Tower Restoration | PAR Contract - Final scope of work | E. Hemus | 2016-09-09 | Closed
35 | Operations | 2016-09-06 | Working Team | Tower Restoration | PAR Contract - Approved work plan | E. Hemus | 2016-09-09 | Closed
36 | Operations | 2016-09-06 | Working Team | Tower Restoration | PAR Contract - Price Sheet | E. Hemus, S. Clesen | 2016-09-09 | Closed
37 | Operations | 2016-09-06 | Working Team | Tower Restoration | PAR Contract RFP - Land & Environmental RTC, access info, permits (if any), etc. | E. Hemus | 2016-09-20 | Closed
38 | Operations | 2016-09-06 | Working Team | Tower Restoration | PAR Contract - Lead disposal provisions | N. Lishman | 2016-09-09 | Closed | PSC is handling for 2016. 2017 under evaluation
39 | Operations | 2016-09-06 | Workshop | Tower Restoration | Confirm contractor qualification list | E. Hemus | 2016-09-12 | Closed
40 | Operations | 2016-09-06 | Workshop | Tower Restoration | Determine if walk downs are needed | Y. Davarzadeh | 2016-09-09 | Closed
41 | Operations | 2016-09-06 | Workshop | Tower Restoration | Full detailed schedule | E. Hemus | 2016-09-09 | Closed | Project milestone report; Keadjian calendar placemat
42 | Operations | 2016-09-09 | Working Team | Tower Restoration | Determine schedule and processes for T-30/32 restoration | Y. Davarzadeh | 2016-09-14 | Closed | MOVE
44 | Land | 2016-09-09 | Working Team | Tower Restoration | Update procedure, letter, door hangers for accessing property with a lock | Keadjian | 2016-10-21 | Open | KA to revise and re-circulate to team based on workshop discussion.
18 | Land | 2016-08-22 | Workshop | Tower Restoration | Workshop item: Review customer acknowledgement and soil restoration letters | Keadjian | 2016-10-17 | Closed | Under team review; acknowledgement letter, soil agreement, refusal agreement; Potential Workshop topic
43 | PMO | 2016-09-09 | Working Team | Governance | Identify PMO approval process | E. Geisert | 2016-11-30 | Open | Exponent
51 | Operations | 2016-09-26 | Workshop | Tower Restoration | Update restoration schedule to highlight schedule changes, customer notification | E. Hemus | 2016-09-26 | Closed | Sent 9/27
47 | Customer | 2016-09-09 | Working Team | Tower Restoration | Customer contact log / tracker | V. Bryan | 2016-09-12 | Closed
48 | Land | 2016-09-09 | Working Team | Tower Restoration | Develop talking points regarding potential encroachments | Keadjian; S. Hughes | 2016-09-23 | Closed | Review guidelines coming out of meeting with legal
49 | PMO | 2016-09-12 | Working Team | Tower Restoration | Confirm final dates needed for South Oroville lines to determine whether 2016 restoration is appropriate | E. Hemus | 2016-09-16 | Closed
50 | PMO | 2016-09-12 | Working Team | Tower Restoration | Add agenda item for reviewing South Orville tower restoration feasibility | E. Geisert | 2016-10-15 | Closed
51 | Operations | 2016-09-12 | Working Team | Tower Restoration | Prepare Q3 / Q4 tower restoration calendar placemat | Keadjian | 2016-09-16 | Closed
52 | PMO | 2016-09-26 | Workshop | Tower Restoration | Develop procedure for feedback loop regarding customer notification of schedule changes | E. Geisert | 2016-11-30 | Closed | weekly update (E. Hemus) and customer review (V. Bryan)
11 | Customer | 2016-08-22 | Workshop | Tower Restoration | Customer tool kit | N. Liebelt | TBD | Open

## Action Items
Community Wildfire Safety Program | [6 empty] | CONFIDENTIAL
Leadership Team Meeting Action Items Tracker | [6 empty] | 2021-04-14 16:15
Action Items
WORKSTREAM | DATE IDENTIFIED | DESCRIPTION | OWNER(S) | RESOURCE | DUE DATE/ RAG STATUS | STATUS | COMMENTS/NOTES
2021 Planning Questions | 2021-12-08 | Coordinate with Meteorology/S. Strenfel on PSPS decision making updates related to Alsup order. | M. Pender, S. Strenfel |  | 2021-03-31 | Open | Discussing summary with the CPUC on 3/16. 3/30 Update: Coordination ongoing
Internal | 2021-02-09 | Coordinate regarding 2021 meeting structure/approach | A. Johnson, T. Maratukulam |  | 2021-02-16 | Closed | Meeting held on 2/19 to discuss; will include in discussions for 2/23 meeting
Customer | 2021-01-12 | Schedule working group to build out in-event communications strategy for communities de-scoped but not cancelled | A. Tau |  | 2021-02-19 | Closed | Now moving forward with a "hard cancel" approach for descoped customers within 2 hours of the decision. Testing messaging this week regarding messaging for descoped customers. Phase III decision includes 2 hour requirement "to the extent possible."
Vegetation Management | 2021-02-09 | Coordinate regarding Judge Alsup P1/P2 veg proposal and potential impacts to PSPS | M. Pender, A. Johnson | Law | 2021-02-19 | Closed | Ongoing discussions regarding PSPS scope impacts. 3/30 Update: Close action item, ongoing coordination.
EVM | 2021-03-31 | Steven Fischer II/EVM team to include Filsinger and Keadjian on 4/1 customer refusal call | S. Fischer II |  | 2021-04-01 | Closed
External Engagement | 2021-02-02 | Coordinate regarding external messaging related to 2021 risk model for inclusion in external engagements i.e. Regional Working Groups, Wildfire Safety Working Sessions, etc. | E. Hunter, K. Kniel | J. Borders, Keadjian | 2021-03-05 | Closed | Messaging has been reviewed/approved, may revisit based on feedback received after it is used externally.
Wood Management | 2021-03-09 | Develop statement/talking points on wood management proposal | A. Brooks, Keadjian |  | 2021-03-23 | Closed | Talking points being updated to reflect ongoing discussions with counties, MarComm team has a statement prepared to be used if necessary.
Full Scale Exercises | 2021-04-07 | Angie Gibson to coordinate with team to ensure full scale exercise one invitations are shared with the Federal Monitor and Filsinger. | A. Gibson |  | 2021-04-09 | Open
Exercises | 2021-02-23 | Work to communicate as a part of the Phase 3 scoping process a potential to revise timeline requirement for exercises to 8/1 instead of 7/1 to align with current plans/approach | A. Gibson, K. Lee | Law | 2021-03-31 | Closed | A. Gibson/K. Lee to discuss potential path forward, if needed. 3/30 Update: Confirmed compliance with K. Lee.
Customer Outreach and Preparedness | 2021-02-09 | Coordinate regarding list of “most likely” impacted customers (HFRA); targeting communication in March | S. Holder, V. Bryan |  | 2021-04-12 | Closed | Data provided week of 3/29
Long Term Temp Gen Planning/Vision 2030 | 2021-04-07 | Quinn Nakayama to include R. Robinson, T. Paroo and K. Khamou on the 4/9 temp gen long-term planning meeting. | Q. Nakayama |  | 2021-04-09 | Closed
Vegetation Management | 2021-02-18 | Coordinate with EVM team regarding strategy for previously marked veg work that is no longer in scope. | M. Pender, S. Sharp |  | 2021-04-12 | Open | Veg team working on reassessment plan, timeline TBD.
System Inspections | 2021-04-07 | Jason Regan to coordinate with Matt Pender regarding system inspections RAG status. | J. Regan, M. Pender |  | 2021-04-13 | Open
Data Quality | 2021-04-07 | Tracy Maratukulam to coordinate with Ali Moazed for future meeting updates regarding data quality. | T. Maratukulam | A. Moazed | 2021-04-13 | Open
CCA/Temp Gen | 2021-04-07 | Vanessa Bryan to have Tom Smith follow up with Claire Halbrook regarding CCA/temporary power coordination | V. Bryan, T. Smith | C. Halbrooks | 2021-04-13 | Closed
EVM | 2021-03-31 | Steven Fischer to provide data outlining where fuel reduction projects are planned. | S. Fischer II |  | 2021-04-15 | Open
EVM | 2021-03-31 | Sarah Sharp to coordinate with EVM team regarding communications approach for 2021. | S. Sharp, S. Fischer |  | 2021-04-15 | Open
REFCL | 2021-04-07 | Matt Pender to schedule meeting regarding REFCL with Mark Quinlan and Harry Marks | M. Pender, M. Quinlan | H. Marks | 2021-04-16 | Closed
Sectionalizing | 2021-04-13 | Matt Pender to follow up with Karen Khamou regarding if estimating is holding up distribution sectionalizing workflow | M. Pender |  | 2021-04-16 | Open
Substation Temp Gen | 2021-04-13 | Elise Hunter/Richard Dye to discuss potential updates to Substation Temporary Generation talking points based on recent feedback | E. Hunter, R. Dye | Keadjian | 2021-04-23 | Open
Judge Alsup/ Frequency | 2021-04-13 | Shawn Holder/Tracy Maratukulam to look into if 2020 Judge Alsup/Frequency data can be pulled by County and follow up with Keadjian | S. Holder, T. Maratukulam | Keadjian | 2021-04-23 | Closed
Regional Working Groups | 2021-03-02 | Review Regional Working Group (RWG) regions based on new regionalization boundaries included in filing and coordinate with A. Brooks to potentially update for Q2 RWG meetings. | E. Hunter, Keadjian | A. Brooks | 2021-05-01 | Open | 3/30 Update: Continue coordination based on ongoing changes as needed.
REFCL | 2021-04-07 | Matt Pender to confirm if there were outages related to the REFCL issue in Calistoga and synch-up with Anna Brooks on any potential engagement needs. | M. Pender | A. Brooks | 2021-05-01 | Open
EP&R | 2021-01-12 | Schedule meeting to identify gaps and next steps regarding procedures and messaging related to capacity outages. | A. Gibson |  | 2021-06-01 | Open | 4/6 Update: Internal coordination meeting occurring on 4/7, additional stakeholders (to include Elise Hunter and Vanessa Bryan) will be pulled in for coordination after this meeting.

## Sheet1 (hidden)
Identified By:
Working Team
OSC

## Sheet3 (hidden)
Category
Action
Decision
Completed
Incomplete
In-Progress