## Sheet1
Layer | Responsible Dept. | Jan 2021 Commitment | June 2021 Progress/Proposed Changes | Additional Information
1 | VM Quality Control | Ramp-up verification to include all vegetation management work (T&D) in HFTD areas on a 100% basis; Shift towards near real-time quality assessment | 100% work verification: EVM Routine Distribution HFTD Transmission ROW - 2022
1 | VM Quality Control | Proposed WV workforce of ~360 FTE, steady-state, targeting a 1:3 ratio of WV inspector to tree crews | On target to have over 200 WV inspectors by the end of 2021. Commitment in WMP is to achieve a WV headcount (internal + external) of over 200 by end of 2021. The ratio is constantly in flux due to dynamic resource loading in Execution.
1 | VM Quality Control | Staff the VM team with PG&E inspection employees to ensure internal expertise on all aspects of Vegetation work, targeting a 1:20 ratio of VMI to tree crew | On target to have over 95 VM inspectors by end of 2021, if current tree crew counts hold, that would result in a 1:15 ration of Sr VMI to tree crews.
2 | VM Quality Control | Dedicated & Specialized Arborist Team, part of the VM organization, to directly liaison with Federal Monitor and CPUC’s Wildfire Safety Division to be responsive on a timely basis to potential field audit findings | On target to have 8 specialized arborist by end of 2021
2 | EO Quality Mgmt | Quality Verification Reviews will be performed using a statistically valid sampling of the previous month’s completed work and reported weekly | Commitment stays the same | Note that the audit was originally scheduled to start in March but due to scoping alignment issues, audit was delayed until May. All segments dating back to January 2021 were still audited.
2 | EO Quality Mgmt | Conduct two EVM QA audits to assess efficacy of the EVM program (1st audit) and evaluate the EVM process (2nd audit) | 1st audit will be completed in August 2021. 2nd audit will be focused on any high risk findings from first audit and performed at least six months after completion of 1st audit.
3 | Internal Audit | Perform Internal Audit for all Vegetation Management Programs including Routine, CEMA, EVM and Vegetation Control | Audit the EVM processes over the reporting of completed miles (in progress)
3 | Internal Audit | Review of 2021 risk-informed EVM work plan prior to work initiation (in progress) | Audited 2021 EVM Work Plan prior to implementation
3 | Internal Audit | Perform advisory over all QA findings and tracking of all actions to ensure full extent of condition is addressed and systemic issues are being addressed | Validated the action plan provided to CPUC in response to Enhanced Oversight and will validate future progress reports
Note on C2: Name Redacted :100% work verification on HFTD routine distriution and Transmission ROW.
Note on C3: Name Redacted Changed QV to WV, believe it was meant to be work verification not quality verification resources. Verify ratio and timing of verification- no lag Name Redacted.
Note on C4: Name Redacted:Verify ratio (Name Redacted and timing.
Note on D3: Name Redacted:Have offers out for 25 internal, expect to bring them in July. ~215 total.