## Preferred-BC1101CB-Seg1
ECOP - Bucks Creek 1101 - CB Segment 1 - PM#35217268 - Preferred
Op Number | SAP ID | Sketch Location | Existing Type | Feet | Miles | Replacement Type | Customer count | Description of Work | Lat | Long
n/a | n/a |  | 1/0 AR | 1158 | 0.21932 | 3-1/0 ACSR TW | n/a | replace 1158' of 1/0 AR with 3-1/0 ACSR TW total | n/a | n/a
n/a | n/a |  | 2C/2AR | 204 | 0.038636 | 3-600 AL EPR + 6” spare | n/a | replace 204' of 2C/2AR with 3-600 AL EPR + 6” spare total | n/a | n/a
n/a | n/a | B to BA | 2C/2AR | 1136 | 0.21515 | 3-1/0 ACSR TW | 0 | replace 1136' of 2C/2AR with 3-1/0 ACSR TW | n/a | n/a
n/a | n/a | AD to AB | 2C/2AR | 204 | 0.038636 | 3-600 AL EPR + 6” spare | 0 | replace 204' of 2C/2AR with 3-600 AL EPR + 6” spare | n/a | n/a
n/a | n/a | AB to AC | 2C/2AR | 22 | 0.0041667 | 3-1/0 ACSR TW | 0 | replace 22' of 2C/2AR with 3-1/0 ACSR TW | n/a | n/a
17137 | 100391541 | B | 900A OH SW | n/a | n/a | 900A SW | n/a | replace 900A OH SW with 900A SW under PM# 35212441 | 39.9112 | -121.3273
n/a | 100391541 | AD | n/a | n/a | n/a | US SW | n/a | install US SW toward Loc AC | 39.9112 | -121.3272
n/a | 100391535 | AB | n/a | n/a | n/a | US SW | n/a | install US SW toward Loc AD | 39.9107 | -121.3275
7141 | 100391535 | AB | 40T | n/a | n/a | G&W Viper LR | n/a | replace 40T fuse with G&W Viper LR P MTT: 120A, P Curve; 163, P TD: 1, P Adder: 0, P Inst: 1200A G MTT: 70A, G Curve: 132, G TD: 1, G Adder: 0, G Inst: 770A | 39.9107 | -121.3275

## Preferred-BC1101CB-Seg2
ECOP - Bucks Creek 1101 - CB Segment 2 - PM#35224712 - Preferred
Op Number | SAP ID | Sketch Location | Existing Type | Feet | Miles | Replacement Type | Customer count | Description of Work | Lat | Long
n/a | n/a |  | 1/0 AR | 503 | 0.095265 | 3-1/0 ACSR TW | n/a | replace 503' of 1/0 AR with 3-1/0 ACSR TW total | n/a | n/a
n/a | n/a |  | 1/0 AR | 719 | 0.13617 | 2-1/0 ACSR TW | n/a | replace 719' of 1/0 AR with 2-1/0 ACSR TW total | n/a | n/a
n/a | n/a |  | 2C/2AR | 9175 | 1.7377 | 3-600AL EPR + 6” spare | n/a | replace 9175' of 2C/2AR with 3-600AL EPR + 6” spare total | n/a | n/a
n/a | n/a |  | 2C | 6958 | 1.3178 | 2-1/0 AL EPR | n/a | replace 6958' of 2C with 2-1/0 AL EPR total | n/a | n/a
n/a | n/a | BA to BB | 2C/2AR | 1930 | 0.36553 | 3-600AL EPR + 6” spare | 0 | replace 1930' of 2C/2AR with 3-600AL EPR + 6” spare | n/a | n/a
n/a | n/a | BB to BC | 2C/2AR | 75 | 0.014205 | 2-1/0 AL EPR | 1 | replace 75' of 2C/2AR with 2-1/0 AL EPR | n/a | n/a
n/a | n/a | BB to CA | 2C/2AR | 3843 | 0.72784 | 2-1/0 AL EPR | 0 | replace 3843' of 2C/2AR with 2-1/0 AL EPR | n/a | n/a
n/a | n/a | CA to CB | 2C/2AR | 719 | 0.13617 | 2-1/0 ACSR TW | 0 | replace 719' of 2C/2AR with 2-1/0 ACSR TW | n/a | n/a
n/a | n/a | BB to D | 2C/2AR | 4810 | 0.91098 | 3-600AL EPR + 6” spare | 0 | replace 4810' of 2C/2AR with 3-600AL EPR + 6” spare | n/a | n/a
n/a | n/a | D to DA | 2C/2AR | 667 | 0.12633 | 2-1/0 AL EPR | 1 | replace 667' of 2C/2AR with 2-1/0 AL EPR | n/a | n/a
n/a | n/a | D to EA | 2C/2AR | 2373 | 0.44943 | 2-1/0 AL EPR | 0 | replace 2373' of 2C/2AR with 2-1/0 AL EPR | n/a | n/a
n/a | n/a | D to EB | 2C/2AR | 2435 | 0.46117 | 3-600AL EPR + 6” spare | 0 | replace 2435' of 2C/2AR with 3-600AL EPR + 6” spare | n/a | n/a
n/a | n/a | EB to EC | 2C/2AR | 503 | 0.095265 | 3-1/0 ACSR TW | 1 | replace 503' of 2C/2AR with 3-1/0 ACSR TW | n/a | n/a
n/a | n/a | BA to CB | 2C/2AR | 5290 | 1.0019 | remove | 0 | remove 5290' of 2C/2AR | n/a | n/a
n/a | n/a | CA to H | 2C/2AR | 3499 | 0.66269 | remove | 0 | remove 3499' of 2C/2AR | n/a | n/a
n/a | 100391529 | BA | n/a | n/a | n/a | US SW w/FI | n/a | install US SW w/FI | 39.9101 | -121.3297
n/a | new PMI-9TT | BB | n/a | n/a | n/a | PMI-9TT | n/a | Install PMI-9TT Interrupter Setting: SEL751 PMTT: 120A, P Curve: U3, P TD: 1, P Adder: 0, P INST: 1,200A GMTT: 80A, G Curve: U3, G TD: 1, G Adder: 0, G INST: 1,000A | 39.9079 | -121.3359
n/a | 100391518 | BC | n/a | n/a | n/a | PM TX | n/a | install PM TX | 39.9082 | -121.336
n/a | 100391318 | CA | n/a | n/a | n/a | US SW w/FI | n/a | install US SW w/FI | 39.9041 | -121.3481
n/a | new PMI-9TT | D | n/a | n/a | n/a | PMI-9TT | n/a | Install PMI-9TT Interrupter Setting: SEL751 PMTT: 120A, P Curve: U3, P TD: 1, P Adder: 0, P INST: 1,200A GMTT: 80A, G Curve: U3, G TD: 1, G Adder: 0, G INST: 1,000A | 39.9026 | -121.3514
n/a | 100391309 | DA | n/a | n/a | n/a | PM TX | n/a | install PM TX | 39.9021 | -121.3534
n/a | 100391300 | EA | n/a | n/a | n/a | PM TX | n/a | install PM TX | 39.9007 | -121.3594
941 | 100391300 | EA | OH SW | n/a | n/a | remove | n/a | remove OH SW | 39.9007 | -121.3594
n/a | n/a | EB | n/a | n/a | n/a | US SW w/FI | n/a | install US SW w/FI on new pole | 39.9003 | -121.3593

## Preferred-BC1101CB-Seg3
ECOP - Bucks Creek 1101 - CB Segment 3 - PM#35224713 - Preferred
Op Number | SAP ID | Sketch Location | Existing Type | Feet | Miles | Replacement Type | Customer count | Description of Work | Lat | Long
n/a | n/a |  | 1/0 AR | 160 | 0.030303 | 3-1/0 ACSR TW | n/a | replace 160' of 1/0 AR with 3-1/0 ACSR TW total | n/a | n/a
n/a | n/a |  | 2C/2AR | 9690 | 1.8352 | 3-600 AL EPR + 6” spare | n/a | replace 9690' of 2C/2AR with 3-600 AL EPR + 6” spare total | n/a | n/a
n/a | n/a | EC to H | 2C/2AR | 9690 | 1.8352 | 3-600 AL EPR + 6” spare | 0 | replace 9690' of 2C/2AR with 3-600 AL EPR + 6” spare | n/a | n/a
n/a | n/a | H to HB | 2C/2AR | 40 | 0.0075758 | 3-1/0 ACSR TW | 1 | replace 40' of 2C/2AR with 3-1/0 ACSR TW | n/a | n/a
n/a | n/a | H to G | 1/0 AR | 110 | 0.020833 | 3-1/0 ACSR TW | 1 | replace 110' of 1/0 AR with 3-1/0 ACSR TW | n/a | n/a
n/a | n/a | EA to H | 2C/2AR | 14309 | 2.71 | remove | 0 | remove 14309' of 2C/2AR | n/a | n/a
n/a | n/a | EC | n/a | n/a | n/a | US SW w/FI | n/a | install US SW w/FI on new pole | 39.899 | -121.3596
n/a | n/a | H | n/a | n/a | n/a | 18 ELF | n/a | install 18 ELF fuse on new pole | 39.8761 | -121.3728
n/a | 100403879 | F | 10 kVA | n/a | n/a | relocate | n/a | relocate RR siding service to near Cresta Dam | 39.8868 | -121.3703
17183 | 100403903 | I | 600A SW | n/a | n/a | remove | n/a | remove OH SW | 39.8763 | -121.3788
17733 | 100403908 | J | 10E | n/a | n/a | remove | n/a | remove 10E fuse | 39.8745 | -121.3793
805SW | n/a | HA | SW | n/a | n/a | remove | n/a | remove OH SW | 39.876 | -121.3729
805 | n/a | HA | 40T | n/a | n/a | remove | n/a | remove 40T fuse | 39.876 | -121.3729

## Alt 1-BC1101CB-Seg1
ECOP - Bucks Creek 1101 - CB Segment 1 - PM#35217268 - Alternative 1
Op Number | SAP ID | Sketch Location | Existing Type | Feet | Miles | Replacement Type | Customer count | Description of Work | Lat | Long
n/a | n/a |  | 2C/2AR | 1351 | 0.25587 | 3-1/0 ACSR TW | n/a | replace 1351' of 2C/2AR with 3-1/0 ACSR TW total | n/a | n/a
n/a | n/a | AD to AC | 2C/2AR | 215 | 0.04072 | 3-1/0 ACSR TW | 0 | replace 215' of 2C/2AR with 3-1/0 ACSR TW | n/a | n/a
n/a | n/a | B to BA | 2C/2AR | 1136 | 0.21515 | 3-1/0 ACSR TW | 5 | replace 1136' of 2C/2AR with 3-1/0 ACSR TW | n/a | n/a
17137 | 100391541 | B | 900A OH SW | n/a | n/a | 900A SW | n/a | replace 900A OH SW with 900A SW under PM# 35212441 | 39.9112 | -121.3273
7141 | 100391535 | AB | 40T | n/a | n/a | G&W Viper LR | n/a | replace 40T fuse with G&W Viper LR P MTT: 120A, P Curve; 163, P TD: 1, P Adder: 0, P Inst: 1200A G MTT: 70A, G Curve: 132, G TD: 1, G Adder: 0, G Inst: 770A | 39.9107 | -121.3275

## Alt 1-BC1101CB-Seg2
ECOP - Bucks Creek 1101 - CB Segment 2 - PM#35224712 - Alternative 1
Op Number | SAP ID | Sketch Location | Existing Type | Feet | Miles | Replacement Type | Customer count | Description of Work | Lat | Long
n/a | n/a |  | 2C/2AR | 9379 | 1.7763 | 3-1/0 ACSR TW | n/a | replace 9379' of 2C/2AR with 3-1/0 ACSR TW total | n/a | n/a
n/a | n/a | BA to D | 2C/2AR | 9379 | 1.7763 | 3-1/0 ACSR TW | 5 | replace 9379' of 2C/2AR with 3-1/0 ACSR TW | n/a | n/a
n/a | n/a | BA to BB | 2C | 1130 | 0.21402 | remove | 0 | remove 1130' of 2C | n/a | n/a
941 | 100391300 | D | OH SW | n/a | n/a | US SW w/FI | n/a | replace OH SW with US SW w/FI | 39.9007 | -121.3594

## Alt 1-BC1101CB-Seg3
ECOP - Bucks Creek 1101 - CB Segment 3 - PM#35224713 - Alternative 1
Op Number | SAP ID | Sketch Location | Existing Type | Feet | Miles | Replacement Type | Customer count | Description of Work | Lat | Long
n/a | n/a |  | 2C/2AR | 14249 | 2.6987 | 3-1/0 ACSR TW | n/a | replace 14249' of 2C/2AR with 3-1/0 ACSR TW total | n/a | n/a
n/a | n/a | D to H | 2C/2AR | 14249 | 2.6987 | 3-1/0 ACSR TW | 5 | replace 14249' of 2C/2AR with 3-1/0 ACSR TW | n/a | n/a
17183 | 100403903 | E | 600A SW | n/a | n/a | US SW w/FI | n/a | replace 600A SW with US SW w/FI | 39.8763 | -121.3788
17733 | 100403908 | F | 10E | n/a | n/a | remove | n/a | remove 10E fuse | 39.8745 | -121.3793
805SW | 100403915 | G | OH SW | n/a | n/a | remove | n/a | remove SW | 39.8758 | -121.373
805 | 100403915 | HA | 40T | n/a | n/a | 18 ELF | n/a | replace 40T fuse with 18 ELF | 39.8758 | -121.373

## Alt 2-BC1101CB-Seg1
ECOP - Bucks Creek 1101 - CB Segment 1 - PM#35217268 - Alternative 2
Op Number | SAP ID | Sketch Location | Existing Type | Feet | Miles | Replacement Type | Customer count | Description of Work | Lat | Long
n/a | n/a |  | 1/0 AR | 1351 | 0.25587 | 3-1/0 ACSR TW | n/a | replace 1351' of 1/0 AR with 3-1/0 ACSR TW total | n/a | n/a
n/a | n/a | AD to AC | 2C/2AR | 215 | 0.04072 | 3-1/0 ACSR TW | 0 | replace 215' of 2C/2AR with 3-1/0 ACSR TW | n/a | n/a
n/a | n/a | B to BA | 2C/2AR | 1136 | 0.21515 | 3-1/0 ACSR TW | 2 | replace 1136' of 2C/2AR with 3-1/0 ACSR TW | n/a | n/a
17137 | 100391541 | B | 900A OH SW | n/a | n/a | 900A SW | n/a | replace 900A OH SW with 900A SW under PM# 35212441 | 39.9112 | -121.3273
7141 | 100391535 | AB | 40T | n/a | n/a | G&W Viper LR | n/a | replace 40T fuse with G&W Viper LR P MTT: 120A, P Curve; 163, P TD: 1, P Adder: 0, P Inst: 1200A G MTT: 70A, G Curve: 132, G TD: 1, G Adder: 0, G Inst: 770A | 39.9107 | -121.3275

## Alt 2-BC1101CB-Seg2
ECOP - Bucks Creek 1101 - CB Segment 2 - PM#35224712 - Alternative 2
Op Number | SAP ID | Sketch Location | Existing Type | Feet | Miles | Replacement Type | Customer count | Description of Work | Lat | Long
n/a | n/a |  | 1/0 AR | 9988 | 1.8917 | 3-1/0 ACSR TW | n/a | replace 9988' of 1/0 AR with 3-1/0 ACSR TW total | n/a | n/a
n/a | n/a | BA to D | 2C/2AR | 9360 | 1.7727 | 3-1/0 ACSR TW | 5 | replace 9360' of 2C/2AR with 3-1/0 ACSR TW | n/a | n/a
n/a | n/a | D to E | 2C/2AR | 628 | 0.11894 | 3-1/0 ACSR TW | 0 | replace 628' of 2C/2AR with 3-1/0 ACSR TW | n/a | n/a
n/a | n/a | BA to BB | 2C | 1130 | 0.21402 | remove | 0 | remove 1130' of 2C | n/a | n/a
941 | 100391300 | D | OH SW | n/a | n/a | remove | n/a | remove OH SW | 39.9007 | -121.3594

## Alt 2-BC1101CB-Seg3
ECOP - Bucks Creek 1101 - CB Segment 3 - PM#35224713 - Alternative 2
Op Number | SAP ID | Sketch Location | Existing Type | Feet | Miles | Replacement Type | Customer count | Description of Work | Lat | Long
n/a | n/a |  | 2C/2AR | 9690 | 1.8352 | 3-600 AL EPR + 6” spare | n/a | replace 9690' of 2C/2AR with 3-600 AL EPR + 6” spare total | n/a | n/a
n/a | n/a |  | 1/0 AR | 160 | 0.030303 | 3-1/0 ACSR TW | n/a | replace 160' of 1/0 AR with 3-1/0 ACSR TW total | n/a | n/a
n/a | n/a | E to H | 2C/2AR | 9690 | 1.8352 | 3-600 AL EPR + 6” spare | 2 | replace 9690' of 2C/2AR with 3-600 AL EPR + 6” spare | n/a | n/a
n/a | n/a | H to HB | 2C/2AR | 50 | 0.0094697 | 3-1/0 ACSR TW | 0 | replace 50' of 2C/2AR with 3-1/0 ACSR TW | n/a | n/a
n/a | n/a | H to G | 1/0 AR | 110 | 0.020833 | 3-1/0 ACSR TW | 0 | replace 110' of 1/0 AR with 3-1/0 ACSR TW | n/a | n/a
n/a | n/a | E | n/a | n/a | n/a | US SW w/FI | n/a | install US SW w/FI on new pole | 39.899 | -121.3596
n/a | n/a | H | n/a | n/a | n/a | 18 ELF | n/a | install 18 ELF fuse on new pole | 39.8761 | -121.3728
n/a | 100403879 | F | 10 kVA | n/a | n/a | relocate | n/a | relocate RR siding service to near Cresta Dam | 39.8868 | -121.3703
17183 | 100403903 | I | 600A SW | n/a | n/a | remove | n/a | remove OH SW | 39.8763 | -121.3788
17733 | 100403908 | J | 10E | n/a | n/a | remove | n/a | remove 10E fuse | 39.8745 | -121.3793
805SW | n/a | HB | SW | n/a | n/a | remove | n/a | remove OH SW | 39.876 | -121.3729
805 | n/a | HB | 40T | n/a | n/a | remove | n/a | remove 40T fuse | 39.876 | -121.3729